## Example
#VALUE!
5.7 Project Timeline Template
Milestone Period
| Program Milestone | Start (Month) | Duration (Months)
|  |  |  | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
| Planning/Detailed Engineering | 1 | 6
| Permitting/Make Ready | 6 | 20
| Material & Equipment Procurement | 6 | 12
| Network Deployment (Construction) | 16 | 24
| Subscriber Activations | 32 | 15
| CEQA Approvals | 12 | 6
| Program Closeout Submission | 44 | 3
Directions:
To allow the CPUC to assess your proposed project timeline in a consistent manner, it must be submitted via this standard program template.
For each program milestone, enter in the starting month (Cells C8 to C13) and milestone duration (Cells D8 to D13).
The project start (the beginning of Month 1) occurs when an awarded applicant receives its subgrantee award from CPUC, the start of each individual milestone must be provided in relation to the project start.
Milestone durations must be provided in units of months and are not to be tied to specific calendar dates.
Per program requirements, the project milestones may not extend beyond the four year timeframe (48 months)
The Program Closeout Submission milestone represents the month in which the applicant proposes to complete the project by submitting the required closeout materials.
The milestones must only encompass BEAD-funded deployment activities. Items such has ongoing subscriber activations (post program) and ongoing maintenance should not be included in the timeline.

## Template Timeline
#VALUE!
Project Timeline Template CPUC BEAD Program: BEAD 2.0
Milestone Period
| Program Milestone | Start (Month) | Duration (Months)
|  |  |  | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
| Planning/Detailed Engineering | 0 | 0
| Permitting/Make Ready | 0 | 0
| Material & Equipment Procurement | 0 | 0
| Network Deployment (Construction) | 0 | 0
| Subscriber Activations | 0 | 0
| CEQA Approvals | 0 | 0
| Program Closeout Submission | 0 | 0
Directions:
To allow the CPUC to assess your proposed project timeline in a consistent manner, it must be submitted via this standard program template.
For each program milestone, enter in the starting month (Cells C8 to C13) and milestone duration (Cells D8 to D13).
The project start (the beginning of Month 1) occurs when an awarded applicant receives its subgrantee award from CPUC, the start of each individual milestone must be provided in relation to the project start.
Milestone durations must be provided in units of months and are not to be tied to specific calendar dates.
Per program requirements, the project milestones may not extend beyond the four year timeframe (48 months)
The Program Closeout Submission milestone represents the month in which the applicant proposes to complete the project by submitting the required closeout materials.
The milestones must only encompass BEAD-funded deployment activities. Items such has ongoing subscriber activations (post program) and ongoing maintenance should not be included in the timeline.