## 9.1 Application Data
Plan ID | Project Name | Applicant Name | County | CPCN or U Number | Contact Person | Contact Position | FFA Amount Requested | Project Cost | Median Household Income | Number of Business Locations | Number of Anchor Institutions | Number of Public Safety Locations | Maximum Download Speed (Mbps) | Maximum Upload Speed (Mbps) | Number of Mass Market Unserved Locations | Description of the major infrastructure to be deployed | Estimated percentage of infrastructure proposed for underground installation | Major equipment expenses | Estimated project plan with major milestones and construction timeline | Description of the proposed broadband project plan
a0Kcs00000PaMbXEAV | Antioch Broadband Expansion | TeraFiber | Contra Costa | U-7446-C | Mark Kitten | GIS Director | 5631080 | 18731758 | 94256 | 1069 | 163 | 15 | 5000 | 5000 | 123 | This project will construct a 100% underground open-access fiber network using microtrenching . The network design follows a distributed architecture with fiber hut(s) , each capable of serving up to 3,500 premises. Each hut will be equipped with XGS-PON Optical Line Terminals (OLTs) , core switching equipment, 1×32 splitters , and redundant power systems (battery backup and generator) to ensure service reliability. From each hut, a dual-duct feeder pathway will support up to 288-strand feeder cables , designed to reach up to 22 distribution vaults . These vaults will each serve approximately 90 demand points , including SFUs, MDUs, and businesses, with fiber strand allocations tailored to the type and unit count of each property. Each vault will also include 6 spare microducts to accommodate future growth and flexibility. Distribution will utilize single loose tube microducts , each supporting up to 24-strand fiber cables . Every home will be served by a dedicated duct, with toby boxes installed between every two homes to facilitate efficient access and drop installation. Drops will be constructed on a service-on-demand basis , ensuring cost-effective deployment and rapid subscriber activation. The entire network will operate as an open-access system , allowing multiple ISPs to deliver service over the same infrastructure. | 100 | Fiber Huts : Prefabricated enclosures housing core network equipment, providing environmental protection and physical security for critical infrastructure. Optical Line Terminals (OLTs) : Installed within each fiber hut to manage and distribute high-speed broadband services across the fiber network using XGS-PON or GPON technology. Core and Distribution Network Equipment : Includes routers, switches, and supporting infrastructure necessary to manage and route broadband traffic from the core network to local distribution areas. Battery Backup Systems and Generators : Ensure continuous network operation during power outages by providing immediate and sustained backup power to the fiber huts and key network nodes. 1×32 XGS-PON/GPON Optical Splitters : Deployed within distribution points to efficiently split a single optical fiber signal into 32 separate subscriber lines, enabling high-density fiber-to-the-premises (FTTP) service. Distribution Vaults : Underground infrastructure that houses fiber splicing and network distribution points, providing accessible yet protected environments for fiber management. Toby Boxes : Smaller access points that serve individual or small clusters of customers, facilitating efficient last-mile fiber connections. Microducts : Narrow, flexible conduits used to house and protect individual fiber strands within the larger network architecture, supporting rapid deployment and future scalability. | Q2 2025 – Q3 2025 Final engineering design and field verification Submission and processing of permit applications Procurement of major materials (fiber, huts, OLTs, vaults, splitters, microducts, etc.) Q3 2025 – Q4 2025 Begin trenching for main conduit routes Deploy fiber huts at designated hub sites Install primary duct bank infrastructure Q4 2025 – Q1 2026 Installation of distribution vaults across network zones Deployment of active core equipment (OLTs, routers, switches) into fiber huts Installation of battery backup and generator systems Q1 2026 – Q2 2026 Fiber optic cable pulling across installed duct routes Fiber splicing at distribution vaults and huts Systematic fiber network testing and validation Q2 2026 – Q3 2026 Phased service activations begin in priority service areas Customer premise connection work initiated in early activation zones Q3 2026 – Q1 2027 Continued phased activations across remaining service areas Completion of all construction activities Final system testing, verification, and project closeout Full service available to all designated addresses | The proposed project will deploy a citywide underground fiber optic broadband network in Antioch, California. Leveraging XGS-PON (10-Gigabit Symmetrical Passive Optical Network) technology, the network will deliver symmetrical internet speeds of up to 5 Gbps to residential homes, businesses, and community anchor institutions within the identified service areas. This open-access network will enable multiple Internet Service Providers (ISPs) to offer competitive, high-performance broadband services, ensuring long-term infrastructure scalability and affordability. The project specifically targets unserved and underserved locations, with infrastructure design optimized to avoid overbuilding areas that already have access to qualifying broadband service. The network will be constructed primarily underground to maximize system resiliency and minimize environmental and community impacts
a0Kcs00000Pb7NVEAZ | Calaveras - Volcano Telephone | Volcano Telephone Company | Calaveras | U-1019C | John Lundgren | VP & Director of Network Services | 23272087.5 | 25857875 | 79887 | 15 | 0 | 0 | 1000 | 1000 | 0 | Volcano Telephone Company (Volcano) proposes to deploy 96.3 miles of new fiber as an extension of its existing and in-construction network assets to serve high-speed, symmetrical broadband up to 1000/1000 Mbps, and scalable to 10 Gbps via Fiber-to-the-Premises (FTTP) for each location within the project area. The proposed infrastructure will provide a stable, reliable, and future-proof network capable of upgrade through the replacement of basic electronics. The current copper-DSL network is aging and is not considered qualifying broadband by the Federal Communications Commission (FCC) as it is unable to consistently deliver 100/20 Mbps to all locations simultaneously or maintain speed thresholds at distances from Central Offices. Volcano will deploy FTTP via XGS-PON technology and Active Ethernet via a common network architecture to serve locations within the project area. An optical fiber will be dedicated to each premise from central aggregation points. Thus, either type of FTTP architecture and associated electronics can be deployed to each subscriber depending on their needs. Volcano will leverage existing facilities to maximize network efficiencies and reduce overall project costs. The existing Volcano Telephone Central Office (CO), located in Pine Grove CA, will aggregate traffic from existing equipment huts and CO sites hosting the FTTP access electronics. The subtending traffic will be aggregated at existing and new redundant Cisco routers. The existing CO equipment provides voice and data traffic services or is transported to upstream facilities via six Fiber Network redundant links of 10 Gbps optical fiber paths, to Internet PoPs in Stockton, CA, San Jose, CA, and Fresno, CA. The proposed electronics aggregation points include battery backup power designed for a minimum of 4 to 8 hours of service in the event of commercial power failure and full-time standby generators at all sites. The proposed equipment also includes the ability to line power the customer ONT and continue to provide essential dial tone for access to 911 emergency services during extended power outages. Each deployed equipment type includes redundancies for the main transmission interfaces and paths, and spares are strategically located throughout the network for critical components. Network monitoring will include hardware and software to identify and locate the causes of any service outages. Trained personnel are ready and on call to be notified automatically in the event of outages that directly affect service. | 100 | Major Equipment Expenses include fiber optic cable, duct, handholes, splice cases, for the distribution cables. The customer premises equipment expenses include Optical Network Terminals (ONT), and Uninterruptable Power Supply (UPS). | Assuming grant award in the second Quarter of 2026, Volcano and its engineering consultant will begin the process to meet all CEQA cultural and environmental requirements upon submission of this application. Volcano will prepare resources to complete the detailed low-level design in 1Q 2026, to meet any requirements and obligations resulting from any required studies and in-depth analysis of the area and its needs. Milestones for this function will include full consultation and engagement with all parties with any interest and jurisdiction. The engineering design will incorporate the natural environment and existing infrastructure, including Rights-of-Way, Easements, and areas of concern identified during the route staking process. Specific permitting efforts will begin in Q2 2026 and build upon the engineering and the requirements of the residents, businesses, and community facilities in the areas. The engineering and permitting processes will result in Plans and Specifications for assembly into bid packages for contractors and equipment vendors. The applicable milestones will be contract awards, which will initiate the construction milestone. Volcano’s build-out and operation of the networks in the project area will function as an extension of its existing facilities and upstream connections. Construction of Outside Plant (OSP) facilities will commence upon receipt of all permitting and consultation approvals for the obligations of the environment and historical sites. This is anticipated to start as early as July 2026, with follow-through that may continue until the end of 2027 with full consideration for all drop cabling and customer premises electronics deployments and turn-up of customers. The construction milestones will include notice of construction completion, close-out of contract documents, and as-built records of all facilities and connections. Each individual subscriber's specific requirements will be accommodated as efficiently as possible, and every effort will be made to meet all network obligations and timeframes for network implementation and service delivery. | Volcano will deploy FTTP via XGS-PON technology and Active Ethernet via a common network architecture to serve locations within the project area to be completed within 24 months of project award. An optical fiber will be dedicated to each premise from central aggregation points. Thus, either type of FTTP architecture and associated electronics can be deployed to each subscriber depending on their needs. The existing Volcano Telephone Central Office (CO), located in Pine Grove CA, will aggregate traffic from existing equipment huts and CO sites hosting the FTTP access electronics. The subtending traffic will be aggregated at existing and new redundant Cisco routers. The existing equipment provides voice and data traffic services or is transported to upstream facilities via four Fiber Network redundant links of 10 Gbps optical fiber paths, to Internet PoPs in Stockton, CA, and Fresno, CA. The proposed electronics aggregation points include battery backup power designed for a minimum of 4 to 8 hours of service in the event of commercial power failure and full-time standby generators at all sites. The proposed equipment also includes the ability to line power the customer ONT and continue to provide essential dial tone for access to 911 emergency services during extended power outages. Each deployed equipment type includes redundancies for the main transmission interfaces and paths, and spares are strategically located throughout the network for critical components. Network monitoring will include hardware and software to identify and locate the causes of any service outages. Trained personnel are ready and on call to be notified automatically in the event of outages that directly affect service.
a0Kcs00000QkdNZEAZ | Calaveras - Volcano Vision | Volcano Vision, Inc. | Calaveras | Pending Application Number--Materials submitted to CPUC are available upon request. | John Lundgren | VP/Director of Network Services | 28116738 | 31240820 | 79887 | 1 | 0 | 0 | 1000 | 1000 | 0 | Volcano Vision, Inc (Vision) proposes to deploy 90.2 miles of new fiber as an extension of its existing and in-construction network assets to serve high-speed, symmetrical broadband up to 1000/1000 Mbps, and scalable to 10 Gbps via Fiber-to-the-Premises (FTTP) for each location within the project area. The proposed infrastructure will provide a stable, reliable, and future-proof network capable of upgrade through the replacement of basic electronics. The current fixed wireless and copper-DSL network is aging and is not considered qualifying broadband by the Federal Communications Commission (FCC) as it is unable to consistently deliver 100/20 Mbps to all locations simultaneously or maintain speed thresholds at distances from Central Offices. Vision will deploy FTTP via XGS-PON technology and Active Ethernet via a common network architecture to serve locations within the project area. An optical fiber will be dedicated to each premise from central aggregation points. Thus either type of FTTP architecture and associated electronics can be deployed to each subscriber depending on their needs. Volcano will leverage existing facilities to maximize network efficiencies and reduce overall project costs. The existing Vision Central Office (CO), located in Pine Grove CA, will aggregate traffic from existing equipment huts and CO sites hosting the FTTP access electronics. The subtending traffic will be aggregated at existing and new redundant Cisco routers. The existing CO equipment provides voice and data traffic services or is transported to upstream facilities via six Fiber Network redundant links of 10 Gbps optical fiber paths, to Internet PoPs in Stockton, CA, San Jose, CA, and Fresno, CA. The proposed electronics aggregation points include battery backup power designed for a minimum of 4 to 8 hours of service in the event of commercial power failure and full-time standby generators at all sites. The proposed equipment also includes the ability to line power the customer ONT and continue to provide essential dial tone for access to 911 emergency services during extended power outages. Each deployed equipment type includes redundancies for the main transmission interfaces and paths, and spares are strategically located throughout the network for critical components. Network monitoring will include hardware and software to identify and locate the causes of any service outages. Trained personnel are ready and on call to be notified automatically in the event of outages that directly affect service. | 100 | Major Equipment Expenses include fiber optic cable, duct, handholes, splice cases, for the distribution cables. The customer premises equipment expenses include Optical Network Terminals (ONT), and Uninterruptible Power Supply (UPS). | Under the assumption the FFA Last Mile grant is authorized in the second Quarter of 2026, Volcano Vision, Inc. (Vision) and its engineering consultant will begin the process to meet all CEQA cultural and environmental requirements upon submission of this application. Vision will prepare resources to complete the detailed low-level design in 1Q 2026, to meet any requirements and obligations resulting from any required studies and in-depth analysis of the area and its needs. Milestones for this function will include full consultation and engagement with all parties with any interest and jurisdiction. The engineering design will incorporate the natural environment and existing infrastructure, including Rights-of-Way, Easements, and areas of concern identified during the route staking process. Specific permitting efforts will begin in Q2 2026 and build upon the engineering and the requirements of the residents, businesses, and community facilities in the areas. The engineering and permitting processes will result in Plans and Specifications for assembly into bid packages for contractors and equipment vendors. The applicable milestones will be contract awards, which will initiate the construction milestone. Vision’s build-out and operation of the networks in the project area will function as an extension of its existing facilities and upstream connections. Construction of Outside Plant (OSP) facilities will commence upon receipt of all permitting and consultation approvals for the obligations of the environment and historical sites. This is anticipated to start as early as July 2026, with follow-through that may continue until the end of 2027 with full consideration for all drop cabling and customer premises electronics deployments and turn-up of customers. The construction milestones will include notice of construction completion, close-out of contract documents, and as-built records of all facilities and connections. Each individual subscriber's specific requirements will be accommodated as efficiently as possible, and every effort will be made to meet all network obligations and timeframes for network implementation and service delivery. | Vision will deploy FTTP via XGS-PON technology and Active Ethernet via a common network architecture to serve locations within the project area to be completed within 24 months of project award. An optical fiber will be dedicated to each premise from central aggregation points. Thus, either type of FTTP architecture and associated electronics can be deployed to each subscriber depending on their needs. The existing Vision Central Office (CO), located in Pine Grove CA, will aggregate traffic from existing equipment huts and CO sites hosting the FTTP access electronics. The subtending traffic will be aggregated at existing and new redundant Cisco routers. The existing equipment provides voice and data traffic services or is transported to upstream facilities via four Fiber Network redundant links of 10 Gbps optical fiber paths, to Internet PoPs in Stockton, CA, and Fresno, CA. The proposed electronics aggregation points include battery backup power designed for a minimum of 4 to 8 hours of service in the event of commercial power failure and full-time standby generators at all sites. The proposed equipment also includes the ability to line power the customer ONT and continue to provide essential dial tone for access to 911 emergency services during extended power outages. Each deployed equipment type includes redundancies for the main transmission interfaces and paths, and spares are strategically located throughout the network for critical components. Network monitoring will include hardware and software to identify and locate the causes of any service outages. Trained personnel are ready and on call to be notified automatically in the event of outages that directly affect service.
a0Kcs00000PZnU9EAL | Calaveras 1 | Comcast Cable Communications Management, LLC | Calaveras |  | John A. Gutierrez | Vice President Regulatory Affairs - California | 8840345 | 11754568 | 66333 | 35 | 3 | 1 | 1250 | 1250 | 447 | Comcast proposes to construct a fiber network capable of symmetrical service of 1 gigabit or higher speeds (the “Project”) to the project area identified in section 2 (the “Project Area”) which will include 53.4 miles of fiber, and 0 number of hubs. This Project will not require any additional headends. The network will be highly reliable, with low latency, and bandwidth can be scaled well beyond foreseeable needs. The fiber network would be constructed to connect Comcast’s existing network to additional homes, businesses, and community anchor institutions (“CAIs”) in the Project Area. The newly constructed network will be capable of meeting or exceeding the level of service required by the California Public Utilities Commission’s (“CPUC”) Federal Funding Account (“FFA”) program, with rates and terms consistent with those offered by Comcast in California. Households, businesses, and CAIs in the Project Area would have access to Comcast’s full suite of products and services, which, in addition to broadband service, includes voice, video, and home security services. | 41.3 | Major equipment expenses will include the following: conduit for new underground deployment; messenger strand for aerial deployment; fiber-optic cable; power supplies; vaults and pedestals; fiber-optic transmitters and receivers; Optical Line Terminal (“OLTs”); and all cabling and combiner equipment needed to connect network hubs to the new network. | Comcast has completed the planning and preliminary engineering phase for the Project. Final engineering, design, and construction will commence upon CPUC approval of the proposed Project. The initial tasks of design and construction will include project engineering and right of way preparation. This Project includes a combination of aerial and underground infrastructure as noted above. Comcast will, to the extent feasible, leverage its existing facilities near the Project Area. Based on Comcast’s initial assessment, Comcast anticipates it will complete the Project, which is categorically exempt from CEQA, on a rolling basis within 18 months after CPUC approval is received and necessary permits are obtained. This means that Comcast will activate service as areas are completed so many locations will be able to access service earlier than the completion of the Project. Comcast expects the following milestones: 10% of the Project Area to be complete in 4 months, 35% of the Project to be complete in 8 months, 85% of the Project to be complete in 16 months, with 100% of the Project completed in approximately 18 months. Comcast will use commercially reasonable efforts to complete construction within 18 months after CPUC approval. However, delays in the issuance of permits or other factors beyond Comcast’s reasonable control, such as extreme weather conditions, strikes, fires, pandemics and epidemics, embargoes, actions of civil or military law enforcement authorities, acts of God or other acts of legislative, judicial, executive, or administrative authorities may necessitate an extension of the construction completion date. The chart below is for illustrative purposes only based on Comcast’s current understanding of similar proposed projects, contains assumptions based on current market dynamics, and is subject to change. Date(s) Activity Month 0 Project Approved / Approval Issued Months 1-3 Finalized Design and Engineering Months 3-6 Municipal and Pole Attachment Permits Months 6-18 Construction and Make-Ready work Total Estimated Project Completion = 18 Months | Comcast will build a fiber network capable of symmetrical service of 1 gigabit or higher speeds, serving unserved communities in the Project Area. This Project will provide service for approximately 447 locations of which 447 are unserved, and 0 are served. Access to reliable, high-speed broadband services will enable Project Area customers to take advantage of essential online resources. See response to “A description of the major infrastructure to be deployed” for technologies used. The preliminary CEQA analysis shows all Project construction will meet one or more categorical CEQA exemptions (i.e . , CEQA Guidelines §§ 15301-03: construction involving existing facilities, replacement or reconstruction, and new construction or conversion of small structures), and does not contain any environmentally sensitive areas. Comcast plans to install approximately 53.4 total miles of broadband network infrastructure. For aerial installation, Comcast will follow GO 95 pole safety and loading requirements and obtain permits and traffic control for proper placement of aerial equipment. For underground installation, Comcast will follow the permitting jurisdiction’s requirements for underground, including obtaining permits and traffic control for access to manholes/handholes and operating underground equipment. Comcast will reasonably return the site to its original condition to the extent feasible following installation. Comcast will leverage compatible and available facilities to support the Project, relying on existing utility poles in rights-of-way for aerial installation where attachments are permitted by the pole owner. Comcast will support make ready to condition poles, where feasible or required for attachment, and rely on its existing core network infrastructure (including hubs) to support the Project. Open access requirements do not apply because Comcast only seeks FFA funds for last mile infrastructure and does not intend to interconnect with the open access statewide Middle Mile Network or any other provider’s infrastructure, but Comcast will keep evaluating middle-mile infrastructure opportunities available to the Project. See Application Section 8. Comcast will connect the Project to its core network in Calaveras County using a newly constructed transport facility detailed in Section 8.
a0Kcs00000QCo3hEAD | Calaveras 2 | Comcast Cable Communications Management, LLC | Calaveras |  | John A. Gutierrez | Vice President Regulatory Affairs - California | 9021588 | 11252868 | 73046 | 33 | 7 | 4 | 1250 | 1250 | 601 | Comcast proposes to construct a fiber network capable of symmetrical service of 1 gigabit or higher speeds (the “Project”) to the project area identified in section 2 (the “Project Area”) which will include 53 miles of fiber, 0 number of hubs. This Project will not require any additional headends. The network will be highly reliable, with low latency, and bandwidth can be scaled well beyond foreseeable needs. The fiber network would be constructed to connect Comcast’s existing network to additional homes, businesses, and community anchor institutions (“CAIs”) in the Project Area. The newly constructed network will be capable of meeting or exceeding the level of service required by the California Public Utilities Commission’s (“CPUC”) Federal Funding Account (“FFA”) program, with rates and terms consistent with those offered by Comcast in California. Households, businesses, and CAIs in the Project Area would have access to Comcast’s full suite of products and services, which, in addition to broadband service, includes voice, video, and home security services. | 41.3 | Major equipment expenses will include the following: conduit for new underground deployment; messenger strand for aerial deployment; fiber-optic cable; power supplies; vaults and pedestals; fiber-optic transmitters and receivers; Optical Line Terminal (“OLTs”); and all cabling and combiner equipment needed to connect network hubs to the new network. | Comcast has completed the planning and preliminary engineering phase for the Project. Final engineering, design, and construction will commence upon CPUC approval of the proposed Project. The initial tasks of design and construction will include project engineering and right of way preparation. This Project includes a combination of aerial and underground infrastructure as noted above. Comcast will, to the extent feasible, leverage its existing facilities near the Project Area. Based on Comcast’s initial assessment, Comcast anticipates it will complete the Project, which is categorically exempt from CEQA, on a rolling basis within 18 months after CPUC approval is received and necessary permits are obtained. This means that Comcast will activate service as areas are completed so many locations will be able to access service earlier than the completion of the Project. Comcast expects the following milestones: 10% of the Project Area to be complete in 4 months, 35% of the Project to be complete in 8 months, 85% of the Project to be complete in 16 months, with 100% of the Project completed in approximately 18 months. Comcast will use commercially reasonable efforts to complete construction within 18 months after CPUC approval. However, delays in the issuance of permits or other factors beyond Comcast’s reasonable control, such as extreme weather conditions, strikes, fires, pandemics and epidemics, embargoes, actions of civil or military law enforcement authorities, acts of God or other acts of legislative, judicial, executive, or administrative authorities may necessitate an extension of the construction completion date. The chart below is for illustrative purposes only based on Comcast’s current understanding of similar proposed projects, contains assumptions based on current market dynamics, and is subject to change. Date(s) Activity Month 0 Project Approved / Approval Issued Months 1-3 Finalized Design and Engineering Months 3-6 Municipal and Pole Attachment Permits Months 6-18 Construction and Make-Ready work Total Estimated Project Completion = 18 Months | Comcast will build a fiber network capable of symmetrical service of 1 gigabit or higher speeds, serving unserved and underserved communities in the Project Area. This Project will provide service for approximately 601 locations of which 601 are unserved. Access to reliable, high-speed broadband services will enable Project Area customers to take advantage of essential online resources. See response to “A description of the major infrastructure to be deployed” for technologies used. The preliminary CEQA analysis shows all Project construction will meet one or more categorical CEQA exemptions (i.e . , CEQA Guidelines §§ 15301-03: construction involving existing facilities, replacement or reconstruction, and new construction or conversion of small structures), and does not contain any environmentally sensitive areas. Comcast plans to install approximately 53.27 total miles of broadband network infrastructure. For aerial installation, Comcast will follow GO 95 pole safety and loading requirements and obtain permits and traffic control for proper placement of aerial equipment. For underground installation, Comcast will follow the permitting jurisdiction’s requirements for underground, including obtaining permits and traffic control for access to manholes/handholes and operating underground equipment. Comcast will reasonably return the site to its original condition to the extent feasible following installation. Comcast will leverage compatible and available facilities to support the Project, relying on existing utility poles in rights-of-way for aerial installation where attachments are permitted by the pole owner. Comcast will support make ready to condition poles, where feasible or required for attachment, and rely on its existing core network infrastructure (including hubs) to support the Project. Open access requirements do not apply because Comcast only seeks FFA funds for last mile infrastructure and does not intend to interconnect with the open access statewide Middle Mile Network or any other provider’s infrastructure, but Comcast will keep evaluating middle-mile infrastructure opportunities available to the Project. See Application Section 8. Comcast will connect the Project to its core network in Calaveras County using a newly constructed transport facility detailed in Section 8.
a0Kcs00000PbvYoEAJ | Calaveras 3 | Comcast Cable Communications Management, LLC | Calaveras |  | John A. Gutierrez | Vice President Regulatory Affairs - California | 2796394 | 3487222 | 68398 | 0 | 0 | 0 | 1250 | 1250 | 172 | Comcast proposes to construct a fiber network capable of symmetrical service of 1 gigabit or higher speeds (the “Project”) to the project area identified in section 2 (the “Project Area”) which will include 15.29 miles of fiber, 0 number of hubs. This Project will not require any additional headends. The network will be highly reliable, with low latency, and bandwidth can be scaled well beyond foreseeable needs. The fiber network would be constructed to connect Comcast’s existing network to additional homes, businesses, and community anchor institutions (“CAIs”) in the Project Area. The newly constructed network will be capable of meeting or exceeding the level of service required by the California Public Utilities Commission’s (“CPUC”) Federal Funding Account (“FFA”) program, with rates and terms consistent with those offered by Comcast in California. Households, businesses, and CAIs in the Project Area would have access to Comcast’s full suite of products and services, which, in addition to broadband service, includes voice, video, and home security services. | 71 | Major equipment expenses will include the following: conduit for new underground deployment; messenger strand for aerial deployment; fiber-optic cable; power supplies; vaults and pedestals; fiber-optic transmitters and receivers; Optical Line Terminal (“OLTs”); and all cabling and combiner equipment needed to connect network hubs to the new network. | Comcast has completed the planning and preliminary engineering phase for the Project. Final engineering, design, and construction will commence upon CPUC approval of the proposed Project. The initial tasks of design and construction will include project engineering and right of way preparation. This Project includes a combination of aerial and underground infrastructure as noted above. Comcast will, to the extent feasible, leverage its existing facilities near the Project Area. Based on Comcast’s initial assessment, Comcast anticipates it will complete the Project, which is categorically exempt from CEQA, on a rolling basis within 18 months after CPUC approval is received and necessary permits are obtained. This means that Comcast will activate service as areas are completed so many locations will be able to access service earlier than the completion of the Project. Comcast expects the following milestones: 10% of the Project Area to be complete in 4 months, 35% of the Project to be complete in 8 months, 85% of the Project to be complete in 16 months, with 100% of the Project completed in approximately 18 months. Comcast will use commercially reasonable efforts to complete construction within 18 months after CPUC approval. However, delays in the issuance of permits or other factors beyond Comcast’s reasonable control, such as extreme weather conditions, strikes, fires, pandemics and epidemics, embargoes, actions of civil or military law enforcement authorities, acts of God or other acts of legislative, judicial, executive, or administrative authorities may necessitate an extension of the construction completion date. The chart below is for illustrative purposes only based on Comcast’s current understanding of similar proposed projects, contains assumptions based on current market dynamics, and is subject to change. Date(s) Activity Month 0 Project Approved / Approval Issued Months 1-3 Finalized Design and Engineering Months 3-6 Municipal and Pole Attachment Permits Months 6-18 Construction and Make-Ready work Total Estimated Project Completion = 18 Months | Comcast will build a fiber network capable of symmetrical service of 1 gigabit or higher speeds, serving unserved and underserved communities in the Project Area. This Project will provide service for approximately 172 locations of which 172 are unserved. Access to reliable, high-speed broadband services will enable Project Area customers to take advantage of essential online resources. See response to “A description of the major infrastructure to be deployed” for technologies used. The preliminary CEQA analysis shows all Project construction will meet one or more categorical CEQA exemptions (i.e . , CEQA Guidelines §§ 15301-03: construction involving existing facilities, replacement or reconstruction, and new construction or conversion of small structures), and does not contain any environmentally sensitive areas. Comcast plans to install approximately 15.29total miles of broadband network infrastructure. For aerial installation, Comcast will follow GO 95 pole safety and loading requirements and obtain permits and traffic control for proper placement of aerial equipment. For underground installation, Comcast will follow the permitting jurisdiction’s requirements for underground, including obtaining permits and traffic control for access to manholes/handholes and operating underground equipment. Comcast will reasonably return the site to its original condition to the extent feasible following installation. Comcast will leverage compatible and available facilities to support the Project, relying on existing utility poles in rights-of-way for aerial installation where attachments are permitted by the pole owner. Comcast will support make ready to condition poles, where feasible or required for attachment, and rely on its existing core network infrastructure (including hubs) to support the Project. Open access requirements do not apply because Comcast only seeks FFA funds for last mile infrastructure and does not intend to interconnect with the open access statewide Middle Mile Network or any other provider’s infrastructure, but Comcast will keep evaluating middle-mile infrastructure opportunities available to the Project. See Application Section 8. Comcast will connect the Project to its core network in Calaveras County using a newly constructed transport facility detailed in Section 8.
a0Kcs00000PcN5FEAV | Calaveras 4 | Comcast Cable Communications Management, LLC | Calaveras |  | John A. Gutierrez | Vice President Regulatory Affairs - California | 14565766 | 18169640 | 61524 | 20 | 5 | 4 | 1250 | 1250 | 1082 | Comcast proposes to construct a fiber network capable of symmetrical service of 1 gigabit or higher speeds (the “Project”) to the project area identified in section 2 (the “Project Area”) which will include 131.88 miles of fiber, 0 number of hubs. This Project will not require any additional headends. The network will be highly reliable, with low latency, and bandwidth can be scaled well beyond foreseeable needs. The fiber network would be constructed to connect Comcast’s existing network to additional homes, businesses, and community anchor institutions (“CAIs”) in the Project Area. The newly constructed network will be capable of meeting or exceeding the level of service required by the California Public Utilities Commission’s (“CPUC”) Federal Funding Account (“FFA”) program, with rates and terms consistent with those offered by Comcast in California. Households, businesses, and CAIs in the Project Area would have access to Comcast’s full suite of products and services, which, in addition to broadband service, includes voice, video, and home security services. | 28.8 | Major equipment expenses will include the following: conduit for new underground deployment; messenger strand for aerial deployment; fiber-optic cable; power supplies; vaults and pedestals; fiber-optic transmitters and receivers; Optical Line Terminal (“OLTs”); and all cabling and combiner equipment needed to connect network hubs to the new network. | Comcast has completed the planning and preliminary engineering phase for the Project. Final engineering, design, and construction will commence upon CPUC approval of the proposed Project. The initial tasks of design and construction will include project engineering and right of way preparation. This Project includes a combination of aerial and underground infrastructure as noted above. Comcast will, to the extent feasible, leverage its existing facilities near the Project Area. Based on Comcast’s initial assessment, Comcast anticipates it will complete the Project, which is categorically exempt from CEQA, on a rolling basis within 18 months after CPUC approval is received and necessary permits are obtained. This means that Comcast will activate service as areas are completed so many locations will be able to access service earlier than the completion of the Project. Comcast expects the following milestones: 10% of the Project Area to be complete in 4 months, 35% of the Project to be complete in 8 months, 85% of the Project to be complete in 16 months, with 100% of the Project completed in approximately 18 months. Comcast will use commercially reasonable efforts to complete construction within 18 months after CPUC approval. However, delays in the issuance of permits or other factors beyond Comcast’s reasonable control, such as extreme weather conditions, strikes, fires, pandemics and epidemics, embargoes, actions of civil or military law enforcement authorities, acts of God or other acts of legislative, judicial, executive, or administrative authorities may necessitate an extension of the construction completion date. The chart below is for illustrative purposes only based on Comcast’s current understanding of similar proposed projects, contains assumptions based on current market dynamics, and is subject to change. Date(s) Activity Month 0 Project Approved / Approval Issued Months 1-3 Finalized Design and Engineering Months 3-6 Municipal and Pole Attachment Permits Months 6-18 Construction and Make-Ready work Total Estimated Project Completion = 18 Months | Comcast will build a fiber network capable of symmetrical service of 1 gigabit or higher speeds, serving unserved and underserved communities in the Project Area. This Project will provide service for approximately 1082 locations of which 1082 are unserved. Access to reliable, high-speed broadband services will enable Project Area customers to take advantage of essential online resources. See response to “A description of the major infrastructure to be deployed” for technologies used. The preliminary CEQA analysis shows all Project construction will meet one or more categorical CEQA exemptions (i.e . , CEQA Guidelines §§ 15301-03: construction involving existing facilities, replacement or reconstruction, and new construction or conversion of small structures), and does not contain any environmentally sensitive areas. Comcast plans to install approximately 131.88 total miles of broadband network infrastructure. For aerial installation, Comcast will follow GO 95 pole safety and loading requirements and obtain permits and traffic control for proper placement of aerial equipment. For underground installation, Comcast will follow the permitting jurisdiction’s requirements for underground, including obtaining permits and traffic control for access to manholes/handholes and operating underground equipment. Comcast will reasonably return the site to its original condition to the extent feasible following installation. Comcast will leverage compatible and available facilities to support the Project, relying on existing utility poles in rights-of-way for aerial installation where attachments are permitted by the pole owner. Comcast will support make ready to condition poles, where feasible or required for attachment, and rely on its existing core network infrastructure (including hubs) to support the Project. Open access requirements do not apply because Comcast only seeks FFA funds for last mile infrastructure and does not intend to interconnect with the open access statewide Middle Mile Network or any other provider’s infrastructure, but Comcast will keep evaluating middle-mile infrastructure opportunities available to the Project. See Application Section 8. Comcast will connect the Project to its core network in Calaveras County using a newly constructed transport facility detailed in Section 8.
a0Kcs00000PciPpEAJ | Calaveras Telephone Company | Calaveras Telephone Company | Calaveras | U-1004-C | Sara Yocum | Chief Financial Officer | 1069321.75 | 1188135.28 | 59438 | 0 | 0 | 1 | 2000 | 2000 | 74 | The proposed project will deploy buried fiber optic infrastructure, with all fiber placed in conduit and accessed via strategically located handholes. This construction approach ensures long-term network durability, enhances fire and weather resistance, and supports safe, efficient maintenance access. It is especially well-suited to the rural, wildfire-prone terrain of Calaveras County. Both mainline distribution fiber and individual service drops to customer premises will be installed in conduit, providing a fully protected, underground fiber network from the central office all the way to the home or business. This comprehensive conduit-based approach significantly extends the lifespan of the network and minimizes long-term repair and restoration costs. The network will utilize XGS-PON (10 Gigabit Symmetrical Passive Optical Network) technology to deliver high-capacity, symmetrical broadband to every location served. XGS-PON supports multi-gigabit service levels with low latency and is ideal for supporting bandwidth-intensive applications like streaming, remote work, and smart home technologies. Critically, the chosen passive optical network architecture is highly scalable and future-proof. The infrastructure being deployed today is designed to coexist with future PON technologies, including 25G and 50G PON, which operate on different wavelengths over the same fiber. This allows Calaveras Telephone Company to upgrade service offerings over time with minimal physical changes, requiring only optical component updates at the central office and customer gateway. Together, this infrastructure plan—featuring fully conduit-based buried fiber, XGS-PON deployment, and next-generation customer equipment—positions Calaveras Telephone Company to deliver a resilient, high-performance broadband solution that exceeds today’s standards and supports seamless evolution into the future. | 100 | The project consists of the material and installation of underground multipath conduit, fiber, handholes, splice cases, and miscellaneous materials required for an underground fiber distribution network. The project also includes connecting the fiber distribution network to eligible customer premise locations by installing underground micro-duct with drop fiber being placed in the micro-duct. The equipment required includes FTTH access network electronic equipment chassis, Optical Line Terminal (OLT), XGS-PON SFP, optical splitters and the required Optical Network Unit (ONU) required at the customer premise. This project is an extension of the existing Calaveras Telephone broadband network; items such as core routers, switches, and other transport networks are already part of the existing network. | Calaveras Telephone Milestones and Timeline 09/01/25 Grant Acceptance Milestone #1: CPUC Grant Contract Finalized by September 1, 2025 09/01 - 09/18/25 Owner/Engineer Mobilization (Gating Factor: Grant Acceptance) 09/01 - 09/18/25 Final Desktop Design (Gating Factor: Grant Acceptance) Milestone #2: Final Office Engineering Completed by September 18, 2025 9/18 - 09/30/25 Field Engineering for Construction Detail (Gating Factor: Final Desktop Design) 09/30 - 10/31/25 Engineering: Final Engineering (Gating Factor: Field Engineering Completion) Milestone #3: Construction Implementation, Reviews, and Permits Completed by April 30, 2026. 11/01/25 - 04/30/26 Permitting and CEQA Clearance (Gating Factor: Final Engineering) 01/01 - 04/30/26 Equipment and Material Order (Gating Factor: Final Engineering) 02/01 - 03/15/26 Fiber Construction Contract Preparation (Gating Factor: Final Engineering) 05/01 - 05/31/26 Fiber Construction Contract Bidding (Gating Factor: Contract Preparation) 06/01 - 06/01/26 Notice of Award for OSP Contract (Gating Factor: Contract Bidding) 06/02 - 07/01/26 OSP Fiber Contractor Mobilization (Gating Factor: Notice of Contract Award) 07/01 - 10/31/26 OSP Fiber Construction (Gating Factor: Contract Award and Mobilization) 10/01 - 12/31/26 Customer Activation (Gating Factor: 90 Days After OSP Construction) Milestone #4: Construction of Grant Funded Network Completed by December 31, 2026. Milestone #5: Grant closeout completed by February 1, 2027. | The proposed project will deploy buried fiber optic infrastructure, with all fiber placed in conduit and accessed via strategically located handholes. This construction approach ensures long-term network durability, enhances fire and weather resistance, and supports safe, efficient maintenance access. It is especially well-suited to the rural, wildfire-prone terrain of Calaveras County. Both mainline distribution fiber and individual service drops to customer premises will be installed in conduit, providing a fully protected, underground fiber network from the central office all the way to the home or business. This comprehensive conduit-based approach significantly extends the lifespan of the network and minimizes long-term repair and restoration costs. The network will utilize XGS-PON (10 Gigabit Symmetrical Passive Optical Network) technology to deliver high-capacity, symmetrical broadband to every location served. XGS-PON supports multi-gigabit service levels with low latency and is ideal for supporting bandwidth-intensive applications like streaming, remote work, and smart home technologies. Critically, the chosen passive optical network architecture is highly scalable and future-proof. The infrastructure being deployed today is designed to coexist with future PON technologies, including 25G and 50G PON, which operate on different wavelengths over the same fiber. This allows Calaveras Telephone Company to upgrade service offerings over time with minimal physical changes, requiring only optical component updates at the central office and customer gateway. Together, this infrastructure plan—featuring fully conduit-based buried fiber, XGS-PON deployment, and next-generation customer equipment—positions Calaveras Telephone Company to deliver a resilient, high-performance broadband solution that exceeds today’s standards and supports seamless evolution into the future.
a0Kcs00000PcmzhEAB | CalTel Connections_Burson | CalTel Connections | Calaveras | U-6509-C | Sara Yocum | Chief Financial Officer | 6076272.64 | 6751414.04 | 86188 | 69 | 3 | 1 | 2000 | 2000 | 369 | The proposed project will deploy buried fiber optic infrastructure, with all fiber placed in conduit and accessed via strategically located handholes. This construction approach ensures long-term network durability, enhances fire and weather resistance, and supports safe, efficient maintenance access. It is especially well-suited to the rural, wildfire-prone terrain of Calaveras County. Both mainline distribution fiber and individual service drops to customer premises will be installed in conduit, providing a fully protected, underground fiber network from the central office all the way to the home or business. This comprehensive conduit-based approach significantly extends the lifespan of the network and minimizes long-term repair and restoration costs. The network will utilize XGS-PON (10 Gigabit Symmetrical Passive Optical Network) technology to deliver high-capacity, symmetrical broadband to every location served. XGS-PON supports multi-gigabit service levels with low latency and is ideal for supporting bandwidth-intensive applications like streaming, remote work, and smart home technologies. Critically, the chosen passive optical network architecture is highly scalable and future-proof. The infrastructure being deployed today is designed to coexist with future PON technologies, including 25G and 50G PON, which operate on different wavelengths over the same fiber. This allows CalTel Connections to upgrade service offerings over time with minimal physical changes, requiring only optical component updates at the central office and customer gateway. Together, this infrastructure plan—featuring fully conduit-based buried fiber, XGS-PON deployment, and next-generation customer equipment—positions CalTel Connections to deliver a resilient, high-performance broadband solution that exceeds today’s standards and supports seamless evolution into the future | 100 | The project consists of the material and installation of underground multipath conduit, fiber, handholes, splice cases, and miscellaneous materials required for an underground fiber distribution network. The project also includes connecting the fiber distribution network to eligible customer premise locations by installing underground micro-duct with drop fiber being placed in the micro-duct. The equipment required includes FTTH access network electronic equipment chassis, Optical Line Terminal (OLT), XGS-PON SFP, optical splitters and the required Optical Network Unit (ONU) required at the customer premise. This project is an extension of the existing Calaveras Telephone broadband network; items such as core routers, switches, and other transport networks are already part of the existing network. | CalTel Connections_Burson Milestones and Timeline * All construction dates listed below are prospective and based on a grant award date of September 1, 2025. If an award date is different than 9-1-2025, listed dates will shift accordingly. 09/01/25 Grant Acceptance Milestone #1: CPUC Grant Contract Finalized by September 1, 2025 09/01 - 09/18/25 Owner/Engineer Mobilization (Gating Factor: Grant Acceptance) 09/01 - 10/01/25 Final Desktop Design (Gating Factor: Grant Acceptance) Milestone #2: Final Office Engineering Completed by October 1, 2025 10/01 - 11/30/25 Field Engineering for Construction Detail (Gating Factor: Final Desktop Design) 11/30 - 12/31/25 Engineering: Final Engineering (Gating Factor: Field Engineering Completion) Milestone #3: Final Engineering Completed by December 31, 2025. 12/01/25 - 04/30/26 Permitting and CEQA Clearance (Gating Factor: Final Engineering) 01/01 - 04/30/26 Equipment and Material Order (Gating Factor: Final Engineering) 02/01 - 03/15/26 Fiber Construction Contract Preparation (Gating Factor: Final Engineering) 05/01 - 05/31/26 Fiber Construction Contract Bidding (Gating Factor: Contract Preparation) 06/01 - 06/01/26 Notice of Award for OSP Contract (Gating Factor: Contract Bidding) 06/02 - 07/01/26 OSP Fiber Contractor Mobilization (Gating Factor: Notice of Contract Award) 10/31 - 11/30/2027 OSP Fiber Construction (Gating Factor: Contract Award and Mobilization) 02/01 - 12/31/2027 Customer Activation (Gating Factor: 90 Days After OSP Construction) Milestone #4: Construction of Grant Funded Network Completed by December 31, 2027. Milestone #5: Grant closeout completed by February 1, 2028. | The proposed project will deploy buried fiber optic infrastructure, with all fiber placed in conduit and accessed via strategically located handholes. This construction approach ensures long-term network durability, enhances fire and weather resistance, and supports safe, efficient maintenance access. It is especially well-suited to the rural, wildfire-prone terrain of Calaveras County. Both mainline distribution fiber and individual service drops to customer premises will be installed in conduit, providing a fully protected, underground fiber network from the central office all the way to the home or business. This comprehensive conduit-based approach significantly extends the lifespan of the network and minimizes long-term repair and restoration costs. The network will utilize XGS-PON (10 Gigabit Symmetrical Passive Optical Network) technology to deliver high-capacity, symmetrical broadband to every location served. XGS-PON supports multi-gigabit service levels with low latency and is ideal for supporting bandwidth-intensive applications like streaming, remote work, and smart home technologies. Critically, the chosen passive optical network architecture is highly scalable and future-proof. The infrastructure being deployed today is designed to coexist with future PON technologies, including 25G and 50G PON, which operate on different wavelengths over the same fiber. This allows Calaveras Telephone Company to upgrade service offerings over time with minimal physical changes, requiring only optical component updates at the central office and customer gateway. Together, this infrastructure plan—featuring fully conduit-based buried fiber, XGS-PON deployment, and next-generation customer equipment—positions Calaveras Telephone Company to deliver a resilient, high-performance broadband solution that exceeds today’s standards and supports seamless evolution into the future.
a0Kcs00000Q63gzEAB | CalTel Connections_Rancho Calaveras | CalTel Connections | Calaveras | U-6509-C | Sara Yocum | Chief Financial Officer | 2866213.38 | 3184681.53 | 58298 | 5 | 4 | 0 | 2000 | 2000 | 262 | The proposed project will deploy buried fiber optic infrastructure, with all fiber placed in conduit and accessed via strategically located handholes. This construction approach ensures long-term network durability, enhances fire and weather resistance, and supports safe, efficient maintenance access. It is especially well-suited to the rural, wildfire-prone terrain of Calaveras County. Both mainline distribution fiber and individual service drops to customer premises will be installed in conduit, providing a fully protected, underground fiber network from the central office all the way to the home or business. This comprehensive conduit-based approach significantly extends the lifespan of the network and minimizes long-term repair and restoration costs. The network will utilize XGS-PON (10 Gigabit Symmetrical Passive Optical Network) technology to deliver high-capacity, symmetrical broadband to every location served. XGS-PON supports multi-gigabit service levels with low latency and is ideal for supporting bandwidth-intensive applications like streaming, remote work, and smart home technologies. Critically, the chosen passive optical network architecture is highly scalable and future-proof. The infrastructure being deployed today is designed to coexist with future PON technologies, including 25G and 50G PON, which operate on different wavelengths over the same fiber. This allows CalTel Connections to upgrade service offerings over time with minimal physical changes, requiring only optical component updates at the central office and customer gateway. All customers will receive Wi-Fi 7 capable gateways, ensuring end-to-end delivery of multi-gigabit performance across both the wired and wireless portions of the network. Together, this infrastructure plan—featuring fully conduit-based buried fiber, XGS-PON deployment, and next-generation customer equipment—positions CalTel Connections to deliver a resilient, high-performance broadband solution that exceeds today’s standards and supports seamless evolution into the future | 100 | The project consists of the material and installation of underground multipath conduit, fiber, handholes, splice cases, and miscellaneous materials required for an underground fiber distribution network. The project also includes connecting the fiber distribution network to eligible customer premise locations by installing underground micro-duct with drop fiber being placed in the micro-duct. The equipment required includes FTTH access network electronic equipment chassis, Optical Line Terminal (OLT), XGS-PON SFP, optical splitters and the required Optical Network Unit (ONU) required at the customer premise. This project is an extension of the existing Calaveras Telephone broadband network; items such as core routers, switches, and other transport networks are already part of the existing network. | CalTel Connections_Rancho Milestones and Timeline * All construction dates listed below are prospective and based on a grant award date of September 1, 2025. If an award date is different than 9-1-2025, listed dates will shift accordingly. 09/01/25 Grant Acceptance Milestone #1: CPUC Grant Contract Finalized by September 1, 2025 09/01 - 09/18/25 Owner/Engineer Mobilization (Gating Factor: Grant Acceptance) 09/01 - 10/01/25 Final Desktop Design (Gating Factor: Grant Acceptance) Milestone #2: Final Office Engineering Completed by October 1, 2025 10/01 - 11/30/25 Field Engineering for Construction Detail (Gating Factor: Final Desktop Design) 11/30 - 12/31/25 Engineering: Final Engineering (Gating Factor: Field Engineering Completion) Milestone #3: Final Engineering Completed by December 31, 2025. 12/01/25 - 04/30/26 Permitting and CEQA Clearance (Gating Factor: Final Engineering) 01/01 - 04/30/26 Equipment and Material Order (Gating Factor: Final Engineering) 02/01 - 03/15/26 Fiber Construction Contract Preparation (Gating Factor: Final Engineering) 05/01 - 05/31/26 Fiber Construction Contract Bidding (Gating Factor: Contract Preparation) 06/01 - 06/01/26 Notice of Award for OSP Contract (Gating Factor: Contract Bidding) 06/02 - 07/01/26 OSP Fiber Contractor Mobilization (Gating Factor: Notice of Contract Award) 09/30 - 04/30/2027 OSP Fiber Construction (Gating Factor: Contract Award and Mobilization) 12/01/26 – 6/01/27 Customer Activation (Gating Factor: 90 Days After OSP Construction) Milestone #4: Construction of Grant Funded Network Completed by June 1, 2027. Milestone #5: Grant closeout completed by August 1, 2027. | The proposed project will deploy buried fiber optic infrastructure, with all fiber placed in conduit and accessed via strategically located handholes. This construction approach ensures long-term network durability, enhances fire and weather resistance, and supports safe, efficient maintenance access. It is especially well-suited to the rural, wildfire-prone terrain of Calaveras County. Both mainline distribution fiber and individual service drops to customer premises will be installed in conduit, providing a fully protected, underground fiber network from the central office all the way to the home or business. This comprehensive conduit-based approach significantly extends the lifespan of the network and minimizes long-term repair and restoration costs. The network will utilize XGS-PON (10 Gigabit Symmetrical Passive Optical Network) technology to deliver high-capacity, symmetrical broadband to every location served. XGS-PON supports multi-gigabit service levels with low latency and is ideal for supporting bandwidth-intensive applications like streaming, remote work, and smart home technologies. Critically, the chosen passive optical network architecture is highly scalable and future-proof. The infrastructure being deployed today is designed to coexist with future PON technologies, including 25G and 50G PON, which operate on different wavelengths over the same fiber. This allows Calaveras Telephone Company to upgrade service offerings over time with minimal physical changes, requiring only optical component updates at the central office and customer gateway. Together, this infrastructure plan—featuring fully conduit-based buried fiber, XGS-PON deployment, and next-generation customer equipment—positions Calaveras Telephone Company to deliver a resilient, high-performance broadband solution that exceeds today’s standards and supports seamless evolution into the future.
a0Kcs00000TEHujEAH | CCTA - East Contra Costa County | Contra Costa Transportation Authority with Etheric Communications | Contra Costa | U7401C | John Hoang | Director, Planning | 10610159 | 10822362 | 82708 | 690 | 62 | 7 | 10000 | 10000 | 1652 | The proposed FTTP deployment utilizes XGS-PON technology, delivering future-proof, high-speed broadband to unserved and underserved rural areas in Contra Costa County. The network is designed for maximum scalability, reliability, and cost-efficiency, leveraging redundant fiber architecture and robust backhaul solutions. Major Infrastructure Components The project integrates a combination of aerial fiber, selective underground conduit, and network support structures to optimize efficiency: Pole-mounted aerial fiber optic cable → The primary installation method leverages existing utility poles, significantly reducing costs, expediting deployment, and minimizing permitting delays. Selective underground conduit & handholes → Deployed only where necessary to comply with CPUC G.O. 95 clearance requirements, Rule 20A undergrounding mandates, or to mitigate aging pole deficiencies. Fiber huts (Points of Presence - PoPs), splice enclosures, and fiber marker posts → Essential for network operations, maintenance, and resiliency. Redundant backhaul architecture → Multiple interconnection points with Etheric’s Bay Area 8 Data Center Fiber Ring, ensuring long-term scalability and failover capacity. Before attachment, the project team will: Enter into or extend joint-use agreements with PG&E and incumbent local exchange carriers (LECs) where necessary. Conduct field surveys, load calculations, and pole integrity assessments in accordance with CPUC regulatory safety standards. Replace or augment poles when structural integrity concerns are identified, ensuring full compliance with state safety mandates. Network Transit & Middle-Mile Connectivity The project is strategically positioned to intersect the state middle-mile network, providing enhanced redundancy and future scalability: Core network transit connects via the state middle mile, interfacing with Etheric’s Bay Area 8 Data Center Fiber Ring at 720 2nd Street Oakland. One central office positioned near Los Medanos College Brentwood, offering XGS-PON OLT services for optimized last-mile delivery. Redundant fiber intersections with the state middle-mile at multiple points, supporting resilient backhaul capabilities and ring architecture. Total fiber deployment: 118 miles of distribution and feeder fiber, complemented by 22 miles of drop cable. | 0 | The proposed project incorporates industry-leading network infrastructure designed to support high-speed, fiber-to-the-premises (FTTP) broadband service with redundancy, scalability, and long-term reliability. Below is a detailed breakdown of major equipment expenditures, ensuring optimal performance and compliance with project goals: Core Network & Switching Infrastructure The backbone of the network is built upon high-performance routing and optical transmission equipment, ensuring stability and minimal latency: Arista 7280R4 Switch Routers ($50,000 per unit, 2 total = $100,000) High-capacity core aggregation switches designed for carrier-grade performance. Supports multi-terabit throughput and advanced traffic management for residential and enterprise clients. Adtran XGS-PON Optical Line Terminals (OLTs) ($30,000 per unit, 2 total = $60,000) Next-generation XGS-PON technology, supporting up to 10 Gbps symmetrical speeds per customer. Allows for seamless scalability and future expansion, ensuring long-term service availability. OLT Optics ($600 per unit, 32 total = $19,200) Enables high-speed fiber transmission with low-latency optical connections across distribution fiber rings. Customer Premises Equipment (CPE) & Optical Network Terminals (ONTs) To provide high-speed connectivity directly to homes and businesses, a mix of GPON and XGS-PON ONTs will be deployed: 10G ONTs ($1,250 per unit, 59.25 total = $74,063) Designed for business-class and high-demand residential users, ensuring ultra-low latency and maximum bandwidth availability. Adtran SDX 601qv GPON ONTs ($200 per unit, 1007.25 total = $201,450) Provides high-speed gigabit broadband for residential subscribers, exceeding CPUC minimum service thresholds. Power & Backup Systems Resilience is critical for maintaining continuous broadband service, even in adverse conditions: Battery Backup (40 KWH, $25,000 per unit, 2 total = $50,000) Supports 72-hour emergency power backup, ensuring operational continuity during outages. Located at the central office, preventing network disruption in case of grid failure. Servers ($30,000 per unit, 2 total = $60,000) Critical for network provisioning, authentication, and traffic management. Enables high-performance data routing and customer access controls. Fiber Optic Infrastructure The physical transmission network consists of aerial fiber deployment, leveraging existing pole infrastructure for cost-efficiency: MSTs ($700 per unit, 233 total = $163,331) Multi-service terminals, facilitating fiber drops to customer premises while ensuring efficient signal distribution. Fiber Cable (G.657.A2, multiple variants) High-density 288-count and 96-count fiber for core and distribution networks. 24-count fiber utilized in last-mile access points, ensuring flexible deployments. Additional Installation & Testing Components The project integrates high-quality installation and testing equipment, ensuring compliance with industry standards and regulatory requirements: Lasher Rental/Purchase ($7,000 per unit) → Essential for securing aerial fiber onto strand infrastructure. Fiber Splice Closures ($800 per unit, 26 total) → Provides weather-sealed fiber junctions for long-term durability. Fiber Optic Testing Equipment (OTDR kit, $12,000 per unit) → Mandated for quality assurance and signal integrity verification. | Project Milestones: 10% Milestone – 4 Months After Start Construction drawings finalized and released for bidding. Vendors identified and engaged across all project areas. Initial orders for critical and long-lead materials placed. 25% Milestone – 10 Months After Start Majority of material procurement completed, and delivery schedules finalized. All required permit applications submitted. Initial construction activities initiated in areas where permits are secured. 50% Milestone – 15 Months After Start All permitting finalized. Full construction underway in all project areas. Contractor bids awarded and full field deployment teams operational. 75% Milestone – 18 Months After Start Approximately 60% of project construction completed. Service activated in completed zones, with active marketing and customer installations underway. Ongoing testing and quality assurance initiated in completed segments. 100% Milestone – 22-24 Months After Start Construction completed across all funded project areas. Final acceptance testing and validation completed. Full service availability to all grant-eligible addresses. Submission of final project reporting, as-built documentation, and compliance certifications to CPUC. Ongoing Communication: Any timeline adjustments outside of the submitted Gantt chart or significant project changes will be immediately communicated to the CPUC FFA Program Team to ensure full transparency and ongoing compliance. | Proposed Broadband Project: High-Speed Fiber-to-the-Premises (FTTP) Network The proposed project is a fiber-to-the-premises (FTTP) deployment designed to deliver high-speed, scalable, and affordable broadband to unserved and underserved communities in Contra Costa County. The network will leverage XGS-PON (10 Gbps Passive Optical Network) technology, ensuring future-proof capacity, low latency, and energy-efficient operations while maintaining a minimal visual impact with its compact ½-inch fiber cabling. Technology & Performance This FTTP deployment will initially provide 1 Gbps symmetrical service to all subscribers, with the capability to scale to 10 Gbps or greater as demand grows. The underlying infrastructure supports 100 Gbps-capable active routing, ensuring that the network can accommodate evolving bandwidth needs. To ensure complete service coverage, the project prioritizes direct fiber connectivity to over 95% of homes and businesses in the targeted region. In limited cases (~5%), alternative access technologies will be deployed where direct fiber installation is infeasible due to terrain, permitting, or structural constraints. Infrastructure & Deployment Strategy The network architecture is designed for high reliability and cost efficiency, utilizing existing utility poles and minimizing permitting delays through strategic aerial deployment. Aerial Fiber Optic Cabling → The primary installation method, leveraging PG&E and local utility poles for streamlined deployment. Selective Underground Conduit & Handholes → Deployed where necessary to comply with CPUC G.O. 95 clearance regulations, Rule 20A undergrounding, or address structural deficiencies on aging poles. Fiber Huts (Points of Presence - PoPs), Splice Enclosures, and Fiber Marker Posts → Supporting network operations, maintenance, and long-term resiliency. Before deployment, the project will: ✔ Extend joint-use agreements with PG&E and incumbent local exchange carriers (LECs) as necessary. ✔ Conduct field surveys, load calculations, and structural integrity assessments per CPUC guidelines. ✔ Replace or augment poles when needed to meet engineering and safety standards. Network Connectivity & Middle-Mile Integration The project intersects California’s Middle Mile Network, ensuring redundant backhaul capacity and network resilience while eliminating single points of failure. Primary transit connects via the state middle mile, interfacing with Etheric’s Bay Area 8 Data Center Fiber Ring at 720 2nd Street, Oakland. One central office positioned near Los Medanos College Brentwood to house XGS-PON OLT services. Redundant backhaul solutions through multiple interconnection points, supporting high-bandwidth enterprise and residential connectivity. Interim & backup fiber solutions through dark fiber and wave transport, ensuring continuous service availability. Total fiber deployment: 118 miles of distribution and feeder fiber, complemented by 22 miles of drop cable. Regulatory & Sustainability Commitment This publicly owned infrastructure complies fully with SB 156, ensuring open access availability where applicable. Etheric Networks will operate and maintain the system under a lease and management agreement, ensuring professional service delivery and long-term sustainability. To support financial transparency, all cost estimates have been developed in collaboration with industry-leading subcontractors and engineering experts. If project costs exceed standard allowances, the application will include detailed documentation explaining the unique high-cost characteristics of these rural service areas. Conclusion: Bringing Reliable, High-Speed Broadband to Contra Costa County This advanced fiber deployment will modernize broadband infrastructure in Contra Costa County, addressing longstanding service gaps along Marsh Creek Road, Clayton, Byron, Brentwood, Oakley, and Knightsen. The network ensures high-performance, scalable service delivery while maintaining cost efficiency and regulatory compliance.
a0Kcs00000TPtrpEAD | CCTA - West Contra Costa County | Contra Costa Transportation Authority with Etheric Communications | Contra Costa | U7401C | John Hoang | Director, Planning | 5455941.78 | 5455941.78 | 85350 | 158 | 173 | 42 | 10000 | 10000 | 656 | The proposed FTTP deployment utilizes XGS-PON technology, delivering future-proof, high-speed broadband to unserved and underserved rural areas in Contra Costa County. The network is designed for maximum scalability, reliability, and cost-efficiency, leveraging redundant fiber architecture and robust backhaul solutions. Major Infrastructure Components The project integrates a combination of aerial fiber, selective underground conduit, and network support structures to optimize efficiency: Pole-mounted aerial fiber optic cable → The primary installation method leverages existing utility poles, significantly reducing costs, expediting deployment, and minimizing permitting delays. Selective underground conduit & handholes → Deployed only where necessary to comply with CPUC G.O. 95 clearance requirements, Rule 20A undergrounding mandates, or to mitigate aging pole deficiencies. Fiber huts (Points of Presence - PoPs), splice enclosures, and fiber marker posts → Essential for network operations, maintenance, and resiliency. Redundant backhaul architecture → Multiple interconnection points with Etheric’s Bay Area 8 Data Center Fiber Ring, ensuring long-term scalability and failover capacity. Before attachment, the project team will: Enter into or extend joint-use agreements with PG&E and incumbent local exchange carriers (LECs) where necessary. Conduct field surveys, load calculations, and pole integrity assessments in accordance with CPUC regulatory safety standards. Replace or augment poles when structural integrity concerns are identified, ensuring full compliance with state safety mandates. Network Transit & Middle-Mile Connectivity The project is strategically positioned to intersect the state middle-mile network, providing enhanced redundancy and future scalability: Core network transit connects via the state middle mile, interfacing with Etheric’s Bay Area 8 Data Center Fiber Ring at 720 2nd Street Oakland. One central office positioned near Los Medanos College Brentwood, offering XGS-PON OLT services for optimized last-mile delivery. Redundant fiber intersections with the state middle-mile at multiple points, supporting resilient backhaul capabilities and ring architecture. Total fiber deployment: 52 miles of distribution and feeder fiber, complemented 16 miles of drop cable. | 11.4 | The proposed fiber-to-the-premises (FTTP) network is designed to deliver high-speed, scalable, and future-proof broadband services utilizing XGS-PON technology. The major equipment expenses reflect the necessary routing, transmission, and distribution components required to ensure network resilience, reliability, and cost-efficiency. Below is a detailed breakdown and justification of major expenditures. 1. Core Network & Optical Line Terminals (OLTs) The backbone of the network features carrier-grade switching, routing, and optical access components, ensuring low latency, multi-terabit throughput, and high-capacity data transmission. Arista 7280R4 Switch Routers ($50,000 each, 2 total = $100,000) Provides multi-terabit data processing, ensuring robust routing and traffic management. Supports future scalability, enabling network expansion beyond initial capacity. Adtran XGS-PON OLT ($30,000 each, 2 total = $60,000) The primary optical access platform, delivering up to 10 Gbps symmetrical broadband to end-users. Efficient traffic handling, ensuring seamless data flow from fiber distribution hubs to individual premises. OLT Optics ($600 each, 32 total = $19,200) Provides high-performance optical interfaces, enabling ultra-low latency transmission. 2. Customer Premises Equipment (ONTs & MSTs) To ensure direct fiber connectivity to homes and businesses, the project deploys high-speed Optical Network Terminals (ONTs) and Multi-Service Terminals (MSTs). MSTs ($700 each, 104 total = $72,766) Fiber distribution hubs that facilitate scalable subscriber connections. 10G ONTs ($1,250 each, 28.45 total = $35,563) Designed for enterprise-grade and heavy-use residential subscribers, providing ultra-low latency and dedicated bandwidth. Adtran SDX 601qv GPON ONTs ($200 each, 483.65 total = $96,730) Affordable high-speed GPON connectivity, ensuring broadband access for all serviceable locations. 3. Power Backup & Core Infrastructure To ensure uninterrupted service and disaster recovery, the project incorporates battery backup systems and critical network servers. 40 KWH Battery Backup ($25,000 each, 1 total = $25,000) Provides emergency power redundancy for critical switching and fiber access nodes. Network Servers ($30,000 each, 2 total = $60,000) Enables advanced network management, authentication, and routing functionalities. Cost Justification Summary The total major equipment expenses of $384,259 support a high-performance, scalable broadband network with redundancy measures ensuring long-term service sustainability. These investments enable carrier-grade data throughput, future expansion capabilities, and compliance with industry regulations. | Project Milestones: 10% Milestone – 4 Months After Start Construction drawings finalized and released for bidding. Vendors identified and engaged across all project areas. Initial orders for critical and long-lead materials placed. 25% Milestone – 8 Months After Start Majority of material procurement completed, and delivery schedules finalized. All required permit applications submitted. Initial construction activities initiated in areas where permits are secured. 50% Milestone – 15 Months After Start All permitting finalized. Full construction underway in all project areas. Contractor bids awarded and full field deployment teams operational. 75% Milestone – 18 Months After Start Approximately 60% of project construction completed. Service activated in completed zones, with active marketing and customer installations underway. Ongoing testing and quality assurance initiated in completed segments. 100% Milestone – 22-24 Months After Start Construction completed across all funded project areas. Final acceptance testing and validation completed. Full service availability to all grant-eligible addresses. Submission of final project reporting, as-built documentation, and compliance certifications to CPUC. Ongoing Communication: Any timeline adjustments outside of the submitted Gantt chart or significant project changes will be immediately communicated to the CPUC FFA Program Team to ensure full transparency and ongoing compliance.4 | Proposed Broadband Project: High-Speed Fiber-to-the-Premises (FTTP) Network The proposed project is a fiber-to-the-premises (FTTP) deployment designed to deliver high-speed, scalable, and affordable broadband to unserved and underserved communities in Contra Costa County. The network will leverage XGS-PON (10 Gbps Passive Optical Network) technology, ensuring future-proof capacity, low latency, and energy-efficient operations while maintaining a minimal visual impact with its compact ½-inch fiber cabling. Technology & Performance This FTTP deployment will initially provide 1 Gbps symmetrical service to all subscribers, with the capability to scale to 10 Gbps or greater as demand grows. The underlying infrastructure supports 100 Gbps-capable active routing, ensuring that the network can accommodate evolving bandwidth needs. To ensure complete service coverage, the project prioritizes direct fiber connectivity to over 95% of homes and businesses in the targeted region. In limited cases (~5%), alternative access technologies will be deployed where direct fiber installation is infeasible due to terrain, permitting, or structural constraints. Infrastructure & Deployment Strategy The network architecture is designed for high reliability and cost efficiency, utilizing existing utility poles and minimizing permitting delays through strategic aerial deployment. Aerial Fiber Optic Cabling → The primary installation method, leveraging PG&E and local utility poles for streamlined deployment. Selective Underground Conduit & Handholes → Deployed where necessary to comply with CPUC G.O. 95 clearance regulations, Rule 20A undergrounding, or address structural deficiencies on aging poles. Fiber Huts (Points of Presence - PoPs), Splice Enclosures, and Fiber Marker Posts → Supporting network operations, maintenance, and long-term resiliency. Before deployment, the project will: ✔ Extend joint-use agreements with PG&E and incumbent local exchange carriers (LECs) as necessary. ✔ Conduct field surveys, load calculations, and structural integrity assessments per CPUC guidelines. ✔ Replace or augment poles when needed to meet engineering and safety standards. Network Connectivity & Middle-Mile Integration The project intersects California’s Middle Mile Network, ensuring redundant backhaul capacity and network resilience while eliminating single points of failure. Primary transit connects via the state middle mile, interfacing with Etheric’s Bay Area 8 Data Center Fiber Ring at 720 2nd Street, Oakland. One central office positioned near Los Medanos College Brentwood to house XGS-PON OLT services. Redundant backhaul solutions through multiple interconnection points, supporting high-bandwidth enterprise and residential connectivity. Interim & backup fiber solutions through dark fiber and wave transport, ensuring continuous service availability. Total fiber deployment: 52 miles of distribution and feeder fiber, complemented by 16 miles of drop cable. Regulatory & Sustainability Commitment This publicly owned infrastructure complies fully with SB 156, ensuring open access availability where applicable. Etheric Networks will operate and maintain the system under a lease and management agreement, ensuring professional service delivery and long-term sustainability. To support financial transparency, all cost estimates have been developed in collaboration with industry-leading subcontractors and engineering experts. If project costs exceed standard allowances, the application will include detailed documentation explaining the unique high-cost characteristics of these rural service areas. Conclusion: Bringing Reliable, High-Speed Broadband to Contra Costa County This advanced fiber deployment will modernize broadband infrastructure in Contra Costa County, addressing longstanding service gaps along the greater Richmond area. The network ensures high-performance, scalable service delivery while maintaining cost efficiency and regulatory compliance.
a0Kcs00000Q6NxTEAV | Contra Costa - 1 | Pacific Bell Telephone Company d/b/a AT&T California | Contra Costa | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 4994037 | 7423479 | 113091 | 20 | 0 | 0 | 5000 | 5000 | 258 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 75.4 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $7,408,632.04 Access Network Electronics $14,846.96 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $ 7,423,479 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITIES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QVfXlEAL | Contra Costa - 1A | Pacific Bell Telephone Company d/b/a AT&T California | Contra Costa | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 5795481 | 9856261 | 127020.65 | 123 | 0 | 0 | 5000 | 5000 | 448 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 69.7 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $9,836,548.48 Access Network Electronics $19,712.52 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $ 9,856,261 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QVgTpEAL | Contra Costa - 1B | Pacific Bell Telephone Company d/b/a AT&T California | Contra Costa | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 2794173 | 3913407 | 149794.79 | 40 | 0 | 0 | 5000 | 5000 | 262 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 65.6 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $3,905,580.19 Access Network Electronics $7,826.81 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $3,913,407 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QVi5pEAD | Contra Costa - 1C | Pacific Bell Telephone Company d/b/a AT&T California | Contra Costa | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 957541 | 1487651 | 189995.79 | 9 | 0 | 0 | 5000 | 5000 | 48 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 75.3 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $1,484,675.70 Access Network Electronics $2,975.30 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $1,487,651 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QVlDNEA1 | Contra Costa - 1D | Pacific Bell Telephone Company d/b/a AT&T California | Contra Costa | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 707890.45 | 1415780.9 | 78265.73 | 15 | 0 | 0 | 5000 | 5000 | 52 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 71.8 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $1,412,949.44 Access Network Electronics $2,831.56 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $1,415,781 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QVlJpEAL | Contra Costa - 1E | Pacific Bell Telephone Company d/b/a AT&T California | Contra Costa | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 1226542.16 | 2453084.33 | 93416.42 | 55 | 0 | 0 | 5000 | 5000 | 202 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 91.9 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $2,448,177.83 Access Network Electronics $4,906.17 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $2,453,084 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QVfkgEAD | Contra Costa - 1F | Pacific Bell Telephone Company d/b/a AT&T California | Contra Costa | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 736899.96 | 1473799.93 | 52090.81 | 42 | 0 | 0 | 5000 | 5000 | 57 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 82.4 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $1,470,852.40 Access Network Electronics $2,947.60 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $1,473,800 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QW0qjEAD | Contra Costa - 1G | Pacific Bell Telephone Company d/b/a AT&T California | Contra Costa | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 916699.47 | 1833398.94 | 100822.26 | 48 | 0 | 0 | 5000 | 5000 | 122 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 79.9 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $1,829,732.20 Access Network Electronics $3,666.80 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $1,833,399 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QWPltEAH | Contra Costa 1 | Comcast Cable Communications Management, LLC | Contra Costa |  | John A. Gutierrez | Vice President Regulatory Affairs - California | 6281294 | 8352758 | 128970 | 7 | 0 | 0 | 1250 | 1250 | 329 | Comcast proposes to construct a fiber network capable of symmetrical service of 1 gigabit or higher speeds (the “Project”) to the project area identified in section 2 (the “Project Area”) which will include 35 miles of fiber, 0 number of hubs. This Project will not require any additional headends. The network will be highly reliable, with low latency, and bandwidth can be scaled well beyond foreseeable needs. The fiber network would be constructed to connect Comcast’s existing network to additional homes, businesses, and community anchor institutions (“CAIs”) in the Project Area. The newly constructed network will be capable of meeting or exceeding the level of service required by the California Public Utilities Commission’s (“CPUC”) Federal Funding Account (“FFA”) program, with rates and terms consistent with those offered by Comcast in California. Households, businesses, and CAIs in the Project Area would have access to Comcast’s full suite of products and services, which, in addition to broadband service, includes voice, video, and home security services. | 80.6 | Major equipment expenses will include the following: conduit for new underground deployment; messenger strand for aerial deployment; fiber-optic cable; power supplies; vaults and pedestals; fiber-optic transmitters and receivers; Optical Line Terminal (“OLTs”); and all cabling and combiner equipment needed to connect network hubs to the new network. | Comcast has completed the planning and preliminary engineering phase for the Project. Final engineering, design, and construction will commence upon CPUC approval of the proposed Project. The initial tasks of design and construction will include project engineering and right of way preparation. This Project includes a combination of aerial and underground infrastructure as noted above. Comcast will, to the extent feasible, leverage its existing facilities near the Project Area. Based on Comcast’s initial assessment, Comcast anticipates it will complete the Project, which is categorically exempt from CEQA, on a rolling basis within 18 months after CPUC approval is received and necessary permits are obtained. This means that Comcast will activate service as areas are completed so many locations will be able to access service earlier than the completion of the Project. Comcast expects the following milestones: 10% of the Project Area to be complete in 4 months, 35% of the Project to be complete in 8 months, 85% of the Project to be complete in 16 months, with 100% of the Project completed in approximately 18 months. Comcast will use commercially reasonable efforts to complete construction within 18 months after CPUC approval. However, delays in the issuance of permits or other factors beyond Comcast’s reasonable control, such as extreme weather conditions, strikes, fires, pandemics and epidemics, embargoes, actions of civil or military law enforcement authorities, acts of God or other acts of legislative, judicial, executive, or administrative authorities may necessitate an extension of the construction completion date. The chart below is for illustrative purposes only based on Comcast’s current understanding of similar proposed projects, contains assumptions based on current market dynamics, and is subject to change. Date(s) Activity Month 0 Project Approved / Approval Issued Months 1-3 Finalized Design and Engineering Months 3-6 Municipal and Pole Attachment Permits Months 6-18 Construction and Make-Ready work Total Estimated Project Completion = 18 Months | Comcast will build a fiber network capable of symmetrical service of 1 gigabit or higher speeds, serving unserved and underserved communities in the Project Area. This Project will provide service for approximately 329 locations of which 329 are unserved. Access to reliable, high-speed broadband services will enable Project Area customers to take advantage of essential online resources. See response to “A description of the major infrastructure to be deployed” for technologies used. The preliminary CEQA analysis shows all Project construction will meet one or more categorical CEQA exemptions (i.e . , CEQA Guidelines §§ 15301-03: construction involving existing facilities, replacement or reconstruction, and new construction or conversion of small structures), and does not contain any environmentally sensitive areas. Comcast plans to install approximately 35 total miles of broadband network infrastructure. For aerial installation, Comcast will follow GO 95 pole safety and loading requirements and obtain permits and traffic control for proper placement of aerial equipment. For underground installation, Comcast will follow the permitting jurisdiction’s requirements for underground, including obtaining permits and traffic control for access to manholes/handholes and operating underground equipment. Comcast will reasonably return the site to its original condition to the extent feasible following installation. Comcast will leverage compatible and available facilities to support the Project, relying on existing utility poles in rights-of-way for aerial installation where attachments are permitted by the pole owner. Comcast will support make ready to condition poles, where feasible or required for attachment, and rely on its existing core network infrastructure (including hubs) to support the Project. Open access requirements do not apply because Comcast only seeks FFA funds for last mile infrastructure and does not intend to interconnect with the open access statewide Middle Mile Network or any other provider’s infrastructure, but Comcast will keep evaluating middle-mile infrastructure opportunities available to the Project. See Application Section 8. Comcast will connect the Project to its core network in Contra Costa County using a newly constructed transport facility detailed in Section 8.
a0Kcs00000PnSxeEAF | Contra Costa 2 | Comcast Cable Communications Management, LLC | Contra Costa |  | John A. Gutierrez | Vice President Regulatory Affairs - California | 7657659 | 9549781 | 194970 | 20 | 3 | 1 | 1250 | 1250 | 386 | Comcast proposes to construct a fiber network capable of symmetrical service of 1 gigabit or higher speeds (the “Project”) to the project area identified in section 2 (the “Project Area”) which will include 40 miles of fiber, 0 number of hubs. This Project will not require any additional headends. The network will be highly reliable, with low latency, and bandwidth can be scaled well beyond foreseeable needs. The fiber network would be constructed to connect Comcast’s existing network to additional homes, businesses, and community anchor institutions (“CAIs”) in the Project Area. The newly constructed network will be capable of meeting or exceeding the level of service required by the California Public Utilities Commission’s (“CPUC”) Federal Funding Account (“FFA”) program, with rates and terms consistent with those offered by Comcast in California. Households, businesses, and CAIs in the Project Area would have access to Comcast’s full suite of products and services, which, in addition to broadband service, includes voice, video, and home security services. | 45.2 | Major equipment expenses will include the following: conduit for new underground deployment; messenger strand for aerial deployment; fiber-optic cable; power supplies; vaults and pedestals; fiber-optic transmitters and receivers; Optical Line Terminal (“OLTs”); and all cabling and combiner equipment needed to connect network hubs to the new network. | Comcast has completed the planning and preliminary engineering phase for the Project. Final engineering, design, and construction will commence upon CPUC approval of the proposed Project. The initial tasks of design and construction will include project engineering and right of way preparation. This Project includes a combination of aerial and underground infrastructure as noted above. Comcast will, to the extent feasible, leverage its existing facilities near the Project Area. Based on Comcast’s initial assessment, Comcast anticipates it will complete the Project, which is categorically exempt from CEQA, on a rolling basis within 18 months after CPUC approval is received and necessary permits are obtained. This means that Comcast will activate service as areas are completed so many locations will be able to access service earlier than the completion of the Project. Comcast expects the following milestones: 10% of the Project Area to be complete in 4 months, 35% of the Project to be complete in 8 months, 85% of the Project to be complete in 16 months, with 100% of the Project completed in approximately 18 months. Comcast will use commercially reasonable efforts to complete construction within 18 months after CPUC approval. However, delays in the issuance of permits or other factors beyond Comcast’s reasonable control, such as extreme weather conditions, strikes, fires, pandemics and epidemics, embargoes, actions of civil or military law enforcement authorities, acts of God or other acts of legislative, judicial, executive, or administrative authorities may necessitate an extension of the construction completion date. The chart below is for illustrative purposes only based on Comcast’s current understanding of similar proposed projects, contains assumptions based on current market dynamics, and is subject to change. Date(s) Activity Month 0 Project Approved / Approval Issued Months 1-3 Finalized Design and Engineering Months 3-6 Municipal and Pole Attachment Permits Months 6-18 Construction and Make-Ready work Total Estimated Project Completion = 18 Months | Comcast will build a fiber network capable of symmetrical service of 1 gigabit or higher speeds, serving unserved and underserved communities in the Project Area. This Project will provide service for approximately 386 locations of which 386 are unserved. Access to reliable, high-speed broadband services will enable Project Area customers to take advantage of essential online resources. See response to “A description of the major infrastructure to be deployed” for technologies used. The preliminary CEQA analysis shows all Project construction will meet one or more categorical CEQA exemptions (i.e . , CEQA Guidelines §§ 15301-03: construction involving existing facilities, replacement or reconstruction, and new construction or conversion of small structures), and does not contain any environmentally sensitive areas. Comcast plans to install approximately 40 total miles of broadband network infrastructure. For aerial installation, Comcast will follow GO 95 pole safety and loading requirements and obtain permits and traffic control for proper placement of aerial equipment. For underground installation, Comcast will follow the permitting jurisdiction’s requirements for underground, including obtaining permits and traffic control for access to manholes/handholes and operating underground equipment. Comcast will reasonably return the site to its original condition to the extent feasible following installation. Comcast will leverage compatible and available facilities to support the Project, relying on existing utility poles in rights-of-way for aerial installation where attachments are permitted by the pole owner. Comcast will support make ready to condition poles, where feasible or required for attachment, and rely on its existing core network infrastructure (including hubs) to support the Project. Open access requirements do not apply because Comcast only seeks FFA funds for last mile infrastructure and does not intend to interconnect with the open access statewide Middle Mile Network or any other provider’s infrastructure, but Comcast will keep evaluating middle-mile infrastructure opportunities available to the Project. See Application Section 8. Comcast will connect the Project to its core network in Contra Costa County sing a newly constructed transport facility detailed in Section 8.
a0Kcs00000QW0SXEA1 | Contra Costa Fiber | Another Corporate ISP DBA monkeybrains | Contra Costa | U-7327-C | Mason Carroll | Lead engineer | 6455000 | 6455000 | 58645 | 1200 | 11 | 5 | 1000 | 1000 | 60 | A description of the major infrastructure to be deployed Another corporate ISP DBA Monkeybrains will construct a hybrid middle mile/last mile ring, consisting of 4.6 miles of new underground conduit (144-count SMFO cable). This will combine with 2.15 miles of California middle mile network to build a 6.75mile ring as the backbone of a new network serving the most underserved section of Richmond CA. Our ring will be completed by connecting to the State’s middle mile network at 2 locations. T The proposed network infrastructure aligns with the CPUC Last Mile program goal to close the digital divide by investing in last mile connections for residents of affordable housing in disadvantaged neighborhoods where the lack of reliable, highspeed broadband access impedes economic mobility. Estimated breakdown of aerial and underground installation The proposed fiber build will be 100% underground in previously disturbed rights-of-way throughout the city and 0% aerial. Major Equipment Expenses Major equipment expenses for the build include: 24300 LF of Conduit and constuction 24300 LF of 144-count SMFO cable. 100 Splice enclosures, 150 fiber access pull boxes and 2 connections to state middle mile network. Switching equipment Mikrotik 2216 for connections to: GOLDEN GATE RICHMOND RICHMOND SENIOR CENTER STORM SHELTER LIFELONG MEDICAL CARE RICHMOND WEST COUNTY OLDER ADULTS CLINIC YWCA OF CONTRA COSTA - RICHMOND CHILDREN'S CENTER LOVONYA DEJEAN MIDDLE STORM SHELTER CONTRA COSTA COUNTY GEORGE D CARROLL COURTHOUSE RICHMOND DIALYSIS ASIAN FAMILY RESOURCE CENTER GRACE HOMES 2, LLC FAMILY COURTYARD CONTRA COSTA COUNTY HEAD START-BROOKSIDE | 100 | Major Equipment Expenses Major equipment expenses for the build include: 24300 LF of Conduit and constuction 24300 LF of 144-count SMFO cable. 100 Splice enclosures, 100 radio Access points 100 2216 Mikroitk switches 150 fiber access pull boxes and 2 connections to state middle mile network. Switching equipment Mikrotik 2216 for connections to: GOLDEN GATE RICHMOND RICHMOND SENIOR CENTER STORM SHELTER LIFELONG MEDICAL CARE RICHMOND WEST COUNTY OLDER ADULTS CLINIC YWCA OF CONTRA COSTA - RICHMOND CHILDREN'S CENTER LOVONYA DEJEAN MIDDLE STORM SHELTER CONTRA COSTA COUNTY GEORGE D CARROLL COURTHOUSE RICHMOND DIALYSIS ASIAN FAMILY RESOURCE CENTER GRACE HOMES 2, LLC FAMILY COURTYARD CONTRA COSTA COUNTY HEAD START-BROOKSIDE | Estimated project plan with major milestones and construction timeline Project Initiation (January 2024 - April 2024 ) Establish Oakland Connect Governance Task Force with representatives from City of Oakland; #OaklandUndivided, Oakland Housing Authority, and relevant community-based groups; Execute agreement between OHA and City of Oakland to facilitate project; Project kickoff and coordination with CPUC and external partners. Network Design and Engineering (February 2024 - May 2024) Review & document requirements to be satisfied by the materials, designs, and services requisite for completing the fiber buildout (City of Oakland; Kimley-Horn); Finalize routes and network design (Kimley-Horn); Prepare Construction Documents (Kimley-Horn); Confirm governance, ownership, and management strategy (addressing zoning and ROW ordinances, legal ramifications, and structure of leasing and asset sharing agreements) (City of Oakland); Finalize environmental documents. Confirm CEQA exemption & NEPA Categorical Exclusion (City of Oakland). Construction (June 2024 – July 2025) Publish construction bids pursuant to the City’s public works standard competitive contracting process; Materials Ordering and Acquisition; Coordinate construction activities with external partners (including OHA, Caltrans & AC Transit, to the extent necessary); Make-Ready Engineering/Duct Work; Fiber Placement & Street/Sidewalk Restoration; Fiber Splicing and Termination; Network Equipment Installation and Configuration; System Testing & Acceptance. Permit Acquisition (June 2024 – Nov 2024) Obtain PX permits (city-issued permit) for work in Oakland streets and sidewalks; Obtain building permits for fiber-cable branch cable terminations and equipment and in-building wiring improvements; Obtain Caltrans Encroachment Permit (State ROW locations). Request for Proposal & Agreements: Internet Service Provider (March 2025 – July 2025) Release RFP to solicit proposals from eligible ISP partner to provide last mile connections to 27 un/underserved MDUs with 2,544 units of housing, 9 public safety buildings, and 14 CAI’s throughout Oakland. The RFP will include requirements for speeds, latency, and pricing, in accordance with CPUC Federal Funding Account guidance. When selected, the City will negotiate and enter into formal agreements with one or more service providers to lease the network to deliver Internet service to customers. Last Mile Connectivity & Maintenance August 2025 - Ongoing | Description of proposed broadband project Monkeybrains proposes to construct and lease a 6.75-mile fiber-optic ring. This includes 4.6miles of new underground fiber and 2.15miles of state middle fiber. That will interconnect a first set of multi-dwelling units (MDUs), public-safety sites, and community-anchor institutions (CAIs) in the Iron Triangle / North & Central Richmond flatlands. Fiber laterals will feed building MPOEs, and participating rooftops will host point-to-multipoint fixed-wireless radios (Ubiquiti Wave 60 GHz with 5 GHz fail-over) to extend gigabit service into surrounding residential blocks that are currently unserved or underserved. Technology • Middle-/last-mile fiber: 144-count SMF trunk in new 1 ¼-in HDPE conduit; 12-count laterals into each MDU/CAI.<br> • Fixed wireless overlay: Wave APs (WAVE-AP/t) on 10–12 MDU rooftops; Wave LR CPE dishes on subscriber premises—supports ≤ 5 Gbps sector capacity, 1 Gbps symmetrical per client at ≤ 500 m LOS.<br> • Inside plant: 10 G/25 G SFP+ aggregation switches and PoE++ edge switches sized for PON or additional Wave sectors in future. Speeds & Service Tiers • Fiber-served MDUs / CAIs / PS sites: 1 G × 1 G standard, 10 G × 10 G upgradeable • Wave fixed-wireless customers: up to 1 G × 1 G sustained, engineered for < 4 ms RTT; typical edge RSSI ≥ -65 dBm ensures 99.99 % availability. Middle-Mile Installing the underground trunk is essential for (a) feeding last-mile laterals into MDUs, family housing and CAIs, and (b) creating fiber hand-off points for third-party wireless ISPs that may wish to collocate. The ring also future-proofs the corridor for small-cell 5G and municipal IoT backhaul.
a0Kcs00000QAT6bEAH | Cruzio - Equal Access San Miguel Canyon | California Broadband Alliance and Cruzio Media | Monterey | U7150C | James Hackett | COO | 4142193 | 4142193 | 74326 | 0 | 1 | 0 | 10000 | 10000 | 514 | New Poles needed to replace existing defective poles Optical Cable Splicing Enclosures and Consumables Materials Distribution Terminals Cabinets Active Electronics Drop Cable Customer Premise Optical to Electrical Converter Battery Backup and related power equipment Splicing vehicle | 0 | New Poles needed to replace existing defective poles Optical Cable Splicing Enclosures and Consumables Materials Distribution Terminals Cabinets Active Electronics Drop Cable Customer Premise Optical to Electrical Converter Battery Backup and related power equipment Splicing Vehicle | Dates are estimated based on expedited approval of grant and permitting where applicable. Project milestones as follows: 10% Milestone – 1 Month after Start Construction drawings ready for bidding Vendors for all project areas identified and engaged. Initial orders for materials placed. 35% Milestone – 3 Months after Start Material ordering completed and deliveries scheduled. Permits for Project Areas Submitted Some contractors are working on projects. 60% Milestone – 8 Months after Start All permits received. Contractors identified and bids awarded for all projects. All contractors actively working on projects. 85% Milestone – 12 Months after Start 50% of projects completed. The project areas that have been acceptance tested are ready for sales and marking efforts. 100% Milestone – 15 Months after Start All construction is completed and service available to all areas within the scope of the grant funding. Final Report written and submitted. Project timelines and projections of completion outside of the proposed Gantt chart will be communicated with the FFA team immediately, if identified. | The proposed project is a fiber-to-the-premises (FTTP) deployment designed for high performance, scalability, and cost-effective delivery of broadband service to the San Miguel Canyon area. The technical design employs 10 Gbps-capable active equipment, offering 1 Gbps symmetrical service at launch, with the ability to upgrade service offerings to 10 Gbps speeds as future demand grows. Project costs have been carefully estimated, incorporating subcontracted construction services and professional pole engineering analysis. Preliminary designs call for fiber-to-the-home (FTTH) or fiber-to-the-premises (FTTP) for nearly all locations, with less than 5% of sites potentially using alternative technologies where necessary due to engineering constraints. The project will interconnect with the California Middle Mile Network or other available middle-mile infrastructure to ensure high-capacity backhaul. Cruzio affirms compliance with SB 156 requirements for open access and public ownership. The resulting infrastructure will be 100% publicly owned and operated under a lease and maintenance agreement by Cruzio to ensure long-term sustainability and community benefit. Internet backhaul will be provided through Cruzio’s existing network assets or through new carrier interconnections where needed, using an active headend model for efficient service distribution. Network distribution equipment will be housed in existing or newly installed environmentally compliant cabinets along the route. The project will use XGS-PON (Passive Optical Network) technology, a highly efficient, low-impact solution that utilizes compact ½-inch fiber cabling. This design minimizes visual impact and energy use while maximizing scalability for future service upgrades. All new fiber cabling will be installed aerially on existing joint-use utility poles, primarily owned by PG&E, which reduces permitting requirements and generally avoids CEQA review. Pole inspections will be conducted, and all necessary joint occupancy applications will be submitted using PG&E-approved processes. This project is designed to meet ministerial review criteria, and Cruzio respectfully requests full funding in line with the proposed budget. The San Miguel Canyon area represents a high-cost, low-density rural region, consistent with FFA program priorities to close the digital divide in underserved communities.
a0Kcs00000QrFd3EAF | D299 Trinity County East | Vero Fiber Networks LLC | Trinity | 19-08-043 | Andrea Giersdorf | VP, Project Management Office | 29471897.24 | 31690212.09 | 56179 | 166 | 12 | 6 | 2300 | 2300 | 1382 | Vero's proposed project will provide a major infrastructure improvement to the area by installing new fiber optic cabling to all of the identified premises. This will include new fiber place in rights of way, along roadways, and along aerial poles to reach all locations. | 5.9 | As with all standard deployments for FTTH, Vero will be installing the following equipment categories: Core Network Routing hardware Core XGS-PON Optical distribution equipment Customer premise equipment Core network routing hardware will be placed at our headend location, and is used to route traffic from our customer facing network to the greater internet. Vero uses equipment from top vendors such as Cisco and Juniper in all of our network deployments. This location also requires carrier grade power and environmental stability, as well as monitoring equipment. The Core XGS-PON equipment Vero uses is from Calix. Calix is the industry leading manufacturer of fiber to the premise distribution equipment. Finally, the equipment used at the customer premises will also be purchased through Calix. | A comprehensive project plan with milestones will be developed upon successful award of the grant. We've provided a high level schedule as part of the required grant application submittal items. | Vero Fiber Networks proposes to extend its high-performance fiber-to-the-home (FTTH) services to unserved communities in Trinity County by leveraging the newly constructed middle-mile infrastructure along Highway 299 (the “D299 Project”). This initiative will directly serve the communities of Junction City, Douglas City, and Lewiston. The proposed project will deploy a 100% fiber-optic network using state-of-the-art XGS-PON technology, capable of delivering symmetrical speeds up to 10 Gbps. This future-proof infrastructure will enable reliable, high-speed broadband for residents, businesses, and institutions. Based on FCC location data, the project is expected to connect 1,382 unserved locations and 12 Community Anchor Institutions, totaling 1,568 potential connections. This investment will significantly improve broadband access in Trinity County, supporting essential needs such as remote work, telehealth, distance learning, and economic development. As part of a broader vision for the Highway 299 corridor, Vero has developed a scalable plan that could ultimately connect approximately 3,000 locations across Trinity and adjacent areas of Humboldt County (including Willow Creek, a unified community that straddles county lines). While planning through the FFA Round 2 process, Vero identified a path to reach an additional 1,595 locations; however, the total estimated cost exceeded the $29 million currently allocated to Trinity County. The complete buildout—covering both Trinity and relevant Humboldt County locations—is estimated at $60 million. Due to existing funding constraints, Vero is submitting a focused proposal—the Trinity County East application—that remains within the County’s allocation and provides the best opportunity for near-term deployment. Vero is actively pursuing other funding sources, including the BEAD and CASF programs, to support its long-term broadband vision along the D299 route. However, limitations associated with BEAD’s project area requirements have made it infeasible to submit a complementary application under that program for this region. Given these constraints, Vero believes that the FFA grant program is the most appropriate and effective vehicle to achieve meaningful broadband expansion in Trinity County—particularly if additional funding could be allocated to support a larger, more comprehensive project. Vero respectfully encourages the State to engage with us to explore opportunities for expanding the project scope. Doing so would create greater cost efficiency, maximize the impact of public investment, and better fulfill California’s Broadband for All mission in these remote and underserved communities.
a0Kcs00000PZH9GEAX | Digital Equity for Coastal and North Orange County and Catalina Island | AVX Networks / Digital Equity Foundation | Orange; Los Angeles | U-7406-C | Lance Ware | CEO | 38205197 | 41935197 | 74000 | 609 | 10 | 5 | 10000 | 10000 | 1655 | A full FTTP XGS-PON network with supporting dark fiber Middle Mile Redundant Ring. ISP capacity lit at 400Gbps to begin. Committed customer for 2nd dark fiber pair on major middle mile route. | 64.9 | DWDN Optoelectronics XGS PON OLTs Redundant Routing Equipment 1x permanent Genset (Avalon CO/Facility) 4x portable Gensets (3 Island/1 mainland) Vehicles | 3 years upon permit approval - see attached project timeline w/permits and Gantt chart. | XGS-PON for residential + SMB Active Ethernet for enterprise/non-mass market/wholesale DWDM/Dark Fiber in middle mile
a0Kcs00000QA6hvEAD | Etheric - Prunedale/Castroville | California Broadband Alliance and Etheric Communications LLC | Monterey | U7401C | Andrew Brickweg | Government & Regulatory Affairs Director | 4294595.24 | 4294595.24 | 73893 | 24 | 11 | 2 | 10000 | 10000 | 478 | The proposed project is a fiber-to-the-premises (FTTP) build utilizing XGS-PON technology, delivering future-proof, high-speed broadband service to unserved and underserved rural areas in Monterey County. The major infrastructure to be deployed includes: Pole-mounted aerial fiber optic cable as the primary installation method , leveraging existing utility poles to reduce costs, speed deployment, and minimize permitting delays. Conduit and handholes , selectively deployed where required to comply with CPUC G.O. 95 clearance requirements, Rule 20A undergrounding specifications, or to address structural deficiencies on aging poles. Fiber huts (Points of Presence, PoPs) , splice enclosures , and fiber marker posts to support network operations, maintenance, and resiliency. Before attachment, we will enter into or extend joint use agreements with PG&E and/or the incumbent local exchange carriers (LECs) where necessary. As a licensed CLEC, we already maintain active agreements for joint occupancy. All poles will be field surveyed, load calculations performed, and structural integrity verified in accordance with CPUC requirements. Pole replacements or augmentation with temporary poles will occur when necessary to meet safety and engineering standards. The project will connect to Etheric's existing fiber Points of Presence (PoPs) in San Juan Bautista and Salinas, utilizing the California Middle Mile Network as appropriate to enhance backhaul connectivity. This infrastructure plan ensures a reliable, scalable, and cost-effective deployment with aerial fiber as the preferred installation method to expedite timelines and maximize project viability. | 7.4 | The total project cost of $4,294,595.24 is carefully structured to cover essential infrastructure and equipment necessary for a high-performance fiber-to-the-premises (FTTP) deployment in Monterey County. Below is a detailed breakdown of key expenditures, along with justifications for each category: Core Network Equipment & Optical Components The backbone of the network consists of switch routers, OLTs, and optical components , ensuring high-capacity and reliable service delivery: Arista 7280R4 Switch Routers ($100,000 for two units) → Supports high-speed aggregation and multi-terabit throughput , essential for handling residential and business traffic efficiently. Adtran XGS-PON Optical Line Terminals (OLTs) ($50,000 for two units) → Enables future-proof broadband, scaling up to 10 Gbps symmetrical speeds per customer. OLT Optics ($600 per unit, 32 total) → Provides fiber transmission interfaces for connecting subscribers to the core network. Customer Premises Equipment (CPE) & ONTs To ensure end-users receive high-speed service, the project includes high-performance Optical Network Terminals (ONTs) : 10G ONTs ($1,250 each, 42 total) → Supports business-class users who require higher bandwidth and low-latency connections. 1-2.5G ONTs ($300 each, 378 total) → Ensures reliable residential service with speeds exceeding federal affordability and reliability standards . Power & Backup Systems To safeguard network uptime and disaster resilience , the project incorporates battery backup and server infrastructure: 40 KWH Battery Backup ($25,000 per unit, 2 total) → Ensures continuous operation in case of power disruptions. Network Servers ($30,000 per unit, 3 total) → Handles authentication, service provisioning, and routing functions. Fiber Optic Infrastructure The project prioritizes aerial deployment , leveraging existing utility poles to minimize costs while maintaining network durability : Fiber Cable (Aerial G.657.A2, 288-count, 96-count, and 24-count) → High-quality, low-loss fiber suited for long-distance aerial installations. Aerial Strand ($0.08 per foot) → Supports aerial fiber attachment, ensuring stability. Lashing Wire ($0.05 per foot) → Secures fiber to strand with durable stainless-steel wrapping. Installation & Testing Components Additional project costs ensure high-quality deployment and compliance with industry standards : Fiber Splice Closures ($800 per unit, 26 total) → Provides environmentally sealed protection at fiber junctions. Slack Storage Loops ($100 per unit, 65 total) → Allows for maintenance flexibility in aerial fiber deployments. OTDR Fiber Testing Kit ($12,000) → Guarantees fiber integrity through optical time-domain reflectometry. Traffic Control Supplies ($3,000 project-wide) → Ensures safe work zones during construction. Underground Fiber Costs & Protective Materials While the project is primarily aerial, a small portion (~5%) involves underground fiber deployment , requiring specialized materials: HDPE Conduit ($6,600 feet, 1.5"-2" SDR 11) → Shields buried fiber against environmental damage. Handholes/Vaults ($24"x36", Tier 22, 8 total) → Provides access points for underground cable maintenance. Warning Tape & Marker Posts → Complies with CPU Code 95 safety regulations , ensuring fiber is correctly labeled. Overall Cost Justification Summary Each component of this budget has been carefully selected based on real-world network deployments and aligns with industry-standard pricing. The use of XGS-PON technology ensures the network is future-proof , capable of scaling to meet growing broadband demands in rural communities. By leveraging existing utility infrastructure where possible, the project optimizes cost efficiency while maintaining high reliability and performance . | Project Milestones: 10% Milestone – 2 Months After Start Construction drawings finalized and released for bidding. Vendors identified and engaged across all project areas. Initial orders for critical and long-lead materials placed. 25% Milestone – 6 Months After Start Majority of material procurement completed, and delivery schedules finalized. All required permit applications submitted. Initial construction activities initiated in areas where permits are secured. 50% Milestone – 12 Months After Start All permitting finalized. Full construction underway in all project areas. Contractor bids awarded and full field deployment teams operational. 75% Milestone – 18 Months After Start Approximately 60% of project construction completed. Service activated in completed zones, with active marketing and customer installations underway. Ongoing testing and quality assurance initiated in completed segments. 100% Milestone – 22-24 Months After Start Construction completed across all funded project areas. Final acceptance testing and validation completed. Full service availability to all grant-eligible addresses. Submission of final project reporting, as-built documentation, and compliance certifications to CPUC. Ongoing Communication: Any timeline adjustments outside of the submitted Gantt chart or significant project changes will be immediately communicated to the CPUC FFA Program Team to ensure full transparency and ongoing compliance. | The proposed project is a fiber-to-the-premises (FTTP) deployment focused on achieving high reliability, affordability, and scalability. The network will utilize 100 Gbps-capable active equipment, delivering 1 Gbps symmetrical service at launch with the ability to scale to 10 Gbps or greater as community needs evolve. The project design employs XGS-PON (Passive Optical Network) technology, which is highly efficient, minimizes energy usage, and has limited visual impact thanks to its small ½-inch fiber cabling. The construction plan targets over 95% fiber connectivity directly to homes and businesses. In limited instances (less than 5%), alternative technologies may be deployed where direct fiber installation is not feasible, ensuring complete service coverage across all targeted areas. The network will interconnect with California’s Middle Mile Network and leverage existing infrastructure wherever possible to ensure robust backhaul connections. Service distribution will be handled through strategically located "active" headend and cabinet sites housing necessary routing and distribution equipment. The preferred construction method is aerial fiber deployment on existing poles, primarily owned by PG&E or other local utilities. This method minimizes environmental disruption, reduces permitting complexity, and helps avoid California Environmental Quality Act (CEQA) review requirements. All poles will be field-surveyed, tested for structural integrity, and applications for joint occupancy will follow PG&E and CPUC standards. The project will comply fully with the public policy requirements of SB 156, ensuring that the resulting infrastructure is 100% publicly owned and available for open access where applicable. The ISP partner will operate the network under a lease and maintenance agreement to ensure professional service delivery and long-term sustainability. All cost estimates have been carefully developed with the support of qualified subcontractors and engineering partners. If discrepancies arise between estimated subsidy needs and program allowances, detailed documentation demonstrating the unique high-cost characteristics of these rural and underserved areas will be provided.
a0Kcs00000QRMn3EAH | GSCA R2 Calaveras County Broadband Network | Golden State Connect Authority | Calaveras | N/A | Barbara Hayes | Chief Economic Development Officer | 28446525 | 30446525 | 52443 | 135 | 8 | 6 | 10000 | 10000 | 918 | DESIGN/ARCHITECTURE Golden State Connect Authority (GSCA) broadband network architecture will consist of Point to Point (PtP) Ethernet, open access, fiber infrastructure. Ethernet infrastructure provides dedicated capacity for every home/business; easily upgradable to 10X speed, supports Enterprise call services; supports open access; and, is vendor neutral. Point to Point (PtP)/Ethernet Design The design consists of a built network with a dedicated fiber strand end-to-end from a fiber hut to each end-user location. The strands will be in cables of varying sizes. The speed is infinite and is determined by the electronics on the end of each fiber span. The minimum installed connection is 1 Gbps, but any location in communities served by GSCA will be capable of 10 Gbps or even 100 Gbps. PtP/Ethernet is preferred for open access because: · Each subscriber has a dedicated fiber connection - not shared with adjacent subscribers or across multiple providers. Delivers more reliable connectivity and better performance - lower latency and lower jitter. Most widely deployed and supported network technology in the world. Ensures a future-proof deployment. Open Access GSCA will own and operate a signal fiber infrastructure that private service providers utilize to deliver services to their subscribers. Open-access fiber can support various competing providers of Internet, metro-Ethernet, phone, video, security, telemedicine, and other services. GSCA’s Operational Partner, UTOPIA Fiber, has developed unique processes, tools, and protections to enable providers to co-exist on open access system, thus enabling providers to view their own subscribers, device information, troubleshooting information, etc., without interfering with or having access to that of subscribers of other providers. Fiber Huts GSCA’s broadband network will utilize walk-in fiber huts instead of cabinets. Fiber huts provide: · Better insulation, protection, and security of equipment Better for making connections, repairs, and performing maintenance during inclement weather Protected from vehicular damage or vandalism Support more battery capacity and stand-by generators to run indefinitely in the event of extended power outages Support redundant cooling units for greater reliability Support instant/automatic failover to redundant fiber routes (all huts connected via multiple fiber paths) Provides facility to support smart city applications such as air-quality sensors, weather sensors, etc. | 100 | Major equipment and installation expenses include: Various strand densities of fiber optics Conduit (HDPE) Hut and Cabinet Configuration Directional Bore 2” to 4” Conduit Pkg Bore – Rock Adder Assorted traffic control material/personnel Outside Plant Construction (OSP) personnel For a complete list of major installation and equipment expenses with associated cost and useful life, please see Proposed Project Expenditures – Estimated Direct Costs. | Milestone 1: Complete Low-Level Designs · Initial forty miles of low-level construction-ready designs for selected project areas will be complete prior to grant award; result of CPUC Local Agency Technical Assistance grant. · Remainder of low-level network design to continue concurrent with following milestones. Milestone 2: Secure Necessary Permits · CEQA - GSCA will be Lead Agency and has completed filing and required posting of Notice of Exemption for project area with California Office of Planning and Research and with corresponding County Clerk · Execute MOU with local governments securing right-of-way access prior to grant award (draft MOU attached) · Local Encroachment Permits – will secure within 4 months of grant award. · CalTrans Encroachment Permits – (if needed) will secure within 5 months of grant award. (Unknown at present if will be needed due to California Department of Technology’s failure to release Shape files for state middle mile routes, thus do not know which side of street interconnection will be present) · State Water Resources Control Board – (if needed) will secure within 5 months of grant award. · Coastal Commission (where required) – will secure permit within 6 months of grant award. Milestone 3: Bid Package Release/Contractor Selection · Pre-qualification packages will be released prior to grant award to identify preferred contractors and bid packages released concurrently with securing of FFA Last Mile and Loan Loss Reserve awards. · Once grant award confirmed, execute agreements with selected firms/individuals Milestone 4: Construction · Assume 18-month buildout period, with one-third of build progressing every 6 months. Milestone 5: Drive Take-Rate/Customer Sign-Ups · Community marketing begins upon grant award and extends through construction period. · Assume two-thirds of customers over 12 months starting in months 4-6, as network is lit, with equal monthly increases. Remaining one-third of customers over following 6-12 months. | GSCA will construct and operate an open access, last mile, municipal, fiber network. Customers will have multiple providers at varying speed/price points from which to choose. The design consists of a built network with a dedicated fiber strand end-to-end from a fiber hut to each end-user location. The strands will be in cables of varying sizes. The speed is infinite and is determined by the electronics on the end of each fiber span. The minimum installed connection is 1 Gbps, but any location in communities served by GSCA will be capable of 10 Gbps or even 100 Gbps. PtP/Ethernet is preferred for open access because: · Each subscriber has a dedicated fiber connection - not shared with adjacent subscribers or across multiple providers. Delivers more reliable connectivity and better performance - lower latency and lower jitter. Most widely deployed and supported network technology in the world. Ensures a future-proof deployment.
a0Kcs00000QRQaXEAX | GSCA R2 Inyo County Broadband Network | Golden State Connect Authority | Inyo |  | Barbara Hayes | Chief Economic Development Officer | 12148200 | 16648200 | 65825 | 403 | 21 | 6 | 10000 | 10000 | 298 | DESCRIPTION OF MAJOR INFRASTRUCTURE TO BE DEPLOYED DESIGN/ARCHITECTURE Golden State Connect Authority (GSCA) broadband network architecture will consist of Point to Point (PtP) Ethernet, open access, fiber infrastructure. Ethernet infrastructure provides dedicated capacity for every home/business; easily upgradable to 10X speed, supports Enterprise call services; supports open access; and, is vendor neutral. Point to Point (PtP)/Ethernet Design The design consists of a built network with a dedicated fiber strand end-to-end from a fiber hut to each end-user location. The strands will be in cables of varying sizes. The speed is infinite and is determined by the electronics on the end of each fiber span. The minimum installed connection is 1 Gbps, but any location in communities served by GSCA will be capable of 10 Gbps or even 100 Gbps. PtP/Ethernet is preferred for open access because: · Each subscriber has a dedicated fiber connection - not shared with adjacent subscribers or across multiple providers. Delivers more reliable connectivity and better performance - lower latency and lower jitter. Most widely deployed and supported network technology in the world. Ensures a future-proof deployment. Open Access GSCA will own and operate a signal fiber infrastructure that private service providers utilize to deliver services to their subscribers. Open-access fiber can support various competing providers of Internet, metro-Ethernet, phone, video, security, telemedicine, and other services. GSCA’s Operational Partner, UTOPIA Fiber, has developed unique processes, tools, and protections to enable providers to co-exist on open access system, thus enabling providers to view their own subscribers, device information, troubleshooting information, etc., without interfering with or having access to that of subscribers of other providers. Fiber Huts GSCA’s broadband network will utilize walk-in fiber huts instead of cabinets. Fiber huts provide: · Better insulation, protection, and security of equipment Better for making connections, repairs, and performing maintenance during inclement weather Protected from vehicular damage or vandalism Support more battery capacity and stand-by generators to run indefinitely in the event of extended power outages Support redundant cooling units for greater reliability Support instant/automatic failover to redundant fiber routes (all huts connected via multiple fiber paths) Provides facility to support smart city applications such as air-quality sensors, weather sensors, etc. | 100 | Major equipment and installation expenses include: Various strand densities of fiber optics Conduit (HDPE) Hut and Cabinet Configuration Directional Bore 2” to 4” Conduit Pkg Bore – Rock Adder Assorted traffic control material/personnel Outside Plant Construction (OSP) personnel For a complete list of major installation and equipment expenses with associated cost and useful life, please see Proposed Project Expenditures – Estimated Direct Costs. | Milestone 1: Complete Low-Level Designs · Initial forty miles of low-level construction-ready designs for selected project areas will be complete prior to grant award; result of CPUC Local Agency Technical Assistance grant. · Remainder of low-level network design to continue concurrent with following milestones. Milestone 2: Secure Necessary Permits · CEQA - GSCA will be Lead Agency and has completed filing and required posting of Notice of Exemption for project area with California Office of Planning and Research and with corresponding County Clerk · Execute MOU with local governments securing right-of-way access prior to grant award (draft MOU attached) · Local Encroachment Permits – will secure within 4 months of grant award. · CalTrans Encroachment Permits – (if needed) will secure within 5 months of grant award. (Unknown at present if will be needed due to California Department of Technology’s failure to release Shape files for state middle mile routes, thus do not know which side of street interconnection will be present) · State Water Resources Control Board – (if needed) will secure within 5 months of grant award. · Coastal Commission (where required) – will secure permit within 6 months of grant award. Milestone 3: Bid Package Release/Contractor Selection · Pre-qualification packages will be released prior to grant award to identify preferred contractors and bid packages released concurrently with securing of FFA Last Mile and Loan Loss Reserve awards. · Once grant award confirmed, execute agreements with selected firms/individuals Milestone 4: Construction · Assume 18-month buildout period, with one-third of build progressing every 6 months. Milestone 5: Drive Take-Rate/Customer Sign-Ups · Community marketing begins upon grant award and extends through construction period. · Assume two-thirds of customers over 12 months starting in months 4-6, as network is lit, with equal monthly increases. Remaining one-third of customers over following 6-12 months. | GSCA will construct and operate an open access, last mile, municipal, fiber network. Customers will have multiple providers at varying speed/price points from which to choose. The design consists of a built network with a dedicated fiber strand end-to-end from a fiber hut to each end-user location. The strands will be in cables of varying sizes. The speed is infinite and is determined by the electronics on the end of each fiber span. The minimum installed connection is 1 Gbps, but any location in communities served by GSCA will be capable of 10 Gbps or even 100 Gbps. PtP/Ethernet is preferred for open access because: · Each subscriber has a dedicated fiber connection - not shared with adjacent subscribers or across multiple providers. Delivers more reliable connectivity and better performance - lower latency and lower jitter. Most widely deployed and supported network technology in the world. Ensures a future-proof deployment.
a0Kcs00000PixE7EAJ | GSCA R2 Monterey County Broadband Network | Golden State Connect Authority | Monterey |  | Barbara Hayes | Chief Economic Development Officer | 17275944 | 19736944 | 83158 | 155 | 8 | 3 | 10000 | 10000 | 776 | Golden State Connect Authority (GSCA) broadband network architecture will consist of Point to Point (PtP) Ethernet, open access, fiber infrastructure. Ethernet infrastructure provides dedicated capacity for every home/business; easily upgradable to 10X speed, supports Enterprise call services; supports open access; and, is vendor neutral. Point to Point (PtP)/Ethernet Design The design consists of a built network with a dedicated fiber strand end-to-end from a fiber hut to each end-user location. The strands will be in cables of varying sizes. The speed is infinite and is determined by the electronics on the end of each fiber span. The minimum installed connection is 1 Gbps, but any location in communities served by GSCA will be capable of 10 Gbps or even 100 Gbps. PtP/Ethernet is preferred for open access because: · Each subscriber has a dedicated fiber connection - not shared with adjacent subscribers or across multiple providers. Delivers more reliable connectivity and better performance - lower latency and lower jitter. Most widely deployed and supported network technology in the world. Ensures a future-proof deployment. Open Access GSCA will own and operate a signal fiber infrastructure that private service providers utilize to deliver services to their subscribers. Open-access fiber can support various competing providers of Internet, metro-Ethernet, phone, video, security, telemedicine, and other services. GSCA’s Operational Partner, UTOPIA Fiber, has developed unique processes, tools, and protections to enable providers to co-exist on open access system, thus enabling providers to view their own subscribers, device information, troubleshooting information, etc., without interfering with or having access to that of subscribers of other providers. Fiber Huts GSCA’s broadband network will utilize walk-in fiber huts instead of cabinets. Fiber huts provide: · Better insulation, protection, and security of equipment Better for making connections, repairs, and performing maintenance during inclement weather Protected from vehicular damage or vandalism Support more battery capacity and stand-by generators to run indefinitely in the event of extended power outages Support redundant cooling units for greater reliability Support instant/automatic failover to redundant fiber routes (all huts connected via multiple fiber paths) Provides facility to support smart city applications such as air-quality sensors, weather sensors, etc. | 100 | Major equipment and installation expenses include: Various strand densities of fiber optics Conduit (HDPE) Hut and Cabinet Configuration Directional Bore 2” to 4” Conduit Pkg Bore – Rock Adder Assorted traffic control material/personnel Outside Plant Construction (OSP) personnel For a complete list of major installation and equipment expenses with associated cost and useful life, please see Proposed Project Expenditures – Estimated Direct Costs. | Milestone 1: Complete Low-Level Designs · Initial forty miles of low-level construction-ready designs for selected project areas will be complete prior to grant award; result of CPUC Local Agency Technical Assistance grant. · Remainder of low-level network design to continue concurrent with following milestones. Milestone 2: Secure Necessary Permits · CEQA - GSCA will be Lead Agency and has completed filing and required posting of Notice of Exemption for project area with California Office of Planning and Research and with corresponding County Clerk · Execute MOU with local governments securing right-of-way access prior to grant award (draft MOU attached) · Local Encroachment Permits – will secure within 4 months of grant award. · CalTrans Encroachment Permits – (if needed) will secure within 5 months of grant award. (Unknown at present if will be needed due to California Department of Technology’s failure to release Shape files for state middle mile routes, thus do not know which side of street interconnection will be present) · State Water Resources Control Board – (if needed) will secure within 5 months of grant award. Milestone 3: Bid Package Release/Contractor Selection · Pre-qualification packages will be released prior to grant award to identify preferred contractors and bid packages released concurrently with securing of FFA Last Mile and Loan Loss Reserve awards. · Once grant award confirmed, execute agreements with selected firms/individuals Milestone 4: Construction · Assume 18-month buildout period, with one-third of build progressing every 6 months. Milestone 5: Drive Take-Rate/Customer Sign-Ups · Community marketing begins upon grant award and extends through construction period. · Assume two-thirds of customers over 12 months starting in months 4-6, as network is lit, with equal monthly increases. Remaining one-third of customers over following 6-12 months. | GSCA will construct and operate an open access, last mile, municipal, fiber network. Customers will have multiple providers at varying speed/price points from which to choose. The design consists of a built network with a dedicated fiber strand end-to-end from a fiber hut to each end-user location. The strands will be in cables of varying sizes. The speed is infinite and is determined by the electronics on the end of each fiber span. The minimum installed connection is 1 Gbps, but any location in communities served by GSCA will be capable of 10 Gbps or even 100 Gbps. PtP/Ethernet is preferred for open access because: · Each subscriber has a dedicated fiber connection - not shared with adjacent subscribers or across multiple providers. Delivers more reliable connectivity and better performance - lower latency and lower jitter. Most widely deployed and supported network technology in the world. Ensures a future-proof deployment.
a0Kcs00000QRQ2fEAH | GSCA R2 Trinity County Broadband Network | Golden State Connect Authority | Trinity |  | Barbara Hayes | Chief Economic Development Officer | 18923040 | 20923040 | 46375 | 314 | 11 | 4 | 10000 | 10000 | 907 | DESCRIPTION OF MAJOR INFRASTRUCTURE TO BE DEPLOYED DESIGN/ARCHITECTURE Golden State Connect Authority (GSCA) broadband network architecture will consist of Point to Point (PtP) Ethernet, open access, fiber infrastructure. Ethernet infrastructure provides dedicated capacity for every home/business; easily upgradable to 10X speed, supports Enterprise call services; supports open access; and, is vendor neutral. Point to Point (PtP)/Ethernet Design The design consists of a built network with a dedicated fiber strand end-to-end from a fiber hut to each end-user location. The strands will be in cables of varying sizes. The speed is infinite and is determined by the electronics on the end of each fiber span. The minimum installed connection is 1 Gbps, but any location in communities served by GSCA will be capable of 10 Gbps or even 100 Gbps. PtP/Ethernet is preferred for open access because: · Each subscriber has a dedicated fiber connection - not shared with adjacent subscribers or across multiple providers. Delivers more reliable connectivity and better performance - lower latency and lower jitter. Most widely deployed and supported network technology in the world. Ensures a future-proof deployment. Open Access GSCA will own and operate a signal fiber infrastructure that private service providers utilize to deliver services to their subscribers. Open-access fiber can support various competing providers of Internet, metro-Ethernet, phone, video, security, telemedicine, and other services. GSCA’s Operational Partner, UTOPIA Fiber, has developed unique processes, tools, and protections to enable providers to co-exist on open access system, thus enabling providers to view their own subscribers, device information, troubleshooting information, etc., without interfering with or having access to that of subscribers of other providers. Fiber Huts GSCA’s broadband network will utilize walk-in fiber huts instead of cabinets. Fiber huts provide: · Better insulation, protection, and security of equipment Better for making connections, repairs, and performing maintenance during inclement weather Protected from vehicular damage or vandalism Support more battery capacity and stand-by generators to run indefinitely in the event of extended power outages Support redundant cooling units for greater reliability Support instant/automatic failover to redundant fiber routes (all huts connected via multiple fiber paths) Provides facility to support smart city applications such as air-quality sensors, weather sensors, etc. | 100 | Major equipment and installation expenses include: Various strand densities of fiber optics Conduit (HDPE) Hut and Cabinet Configuration Directional Bore 2” to 4” Conduit Pkg Bore – Rock Adder Assorted traffic control material/personnel Outside Plant Construction (OSP) personnel For a complete list of major installation and equipment expenses with associated cost and useful life, please see Proposed Project Expenditures – Estimated Direct Costs. | Milestone 1: Complete Low-Level Designs · Initial forty miles of low-level construction-ready designs for selected project areas will be complete prior to grant award; result of CPUC Local Agency Technical Assistance grant. · Remainder of low-level network design to continue concurrent with following milestones. Milestone 2: Secure Necessary Permits · CEQA - GSCA will be Lead Agency and has completed filing and required posting of Notice of Exemption for project area with California Office of Planning and Research and with corresponding County Clerk · Execute MOU with local governments securing right-of-way access prior to grant award (draft MOU attached) · Local Encroachment Permits – will secure within 4 months of grant award. · CalTrans Encroachment Permits – (if needed) will secure within 5 months of grant award. (Unknown at present if will be needed due to California Department of Technology’s failure to release Shape files for state middle mile routes, thus do not know which side of street interconnection will be present) · State Water Resources Control Board – (if needed) will secure within 5 months of grant award. · Coastal Commission (where required) – will secure permit within 6 months of grant award. Milestone 3: Bid Package Release/Contractor Selection · Pre-qualification packages will be released prior to grant award to identify preferred contractors and bid packages released concurrently with securing of FFA Last Mile and Loan Loss Reserve awards. · Once grant award confirmed, execute agreements with selected firms/individuals Milestone 4: Construction · Assume 18-month buildout period, with one-third of build progressing every 6 months. Milestone 5: Drive Take-Rate/Customer Sign-Ups · Community marketing begins upon grant award and extends through construction period. · Assume two-thirds of customers over 12 months starting in months 4-6, as network is lit, with equal monthly increases. Remaining one-third of customers over following 6-12 months. | GSCA will construct and operate an open access, last mile, municipal, fiber network. Customers will have multiple providers at varying speed/price points from which to choose. The design consists of a built network with a dedicated fiber strand end-to-end from a fiber hut to each end-user location. The strands will be in cables of varying sizes. The speed is infinite and is determined by the electronics on the end of each fiber span. The minimum installed connection is 1 Gbps, but any location in communities served by GSCA will be capable of 10 Gbps or even 100 Gbps. PtP/Ethernet is preferred for open access because: · Each subscriber has a dedicated fiber connection - not shared with adjacent subscribers or across multiple providers. Delivers more reliable connectivity and better performance - lower latency and lower jitter. Most widely deployed and supported network technology in the world. Ensures a future-proof deployment.
a0Kcs00000QATZdEAP | Hankins - Aromas | California Broadband Alliance and Hankins Information Technology | Monterey | U7386C | James Hankins | CEO | 4530721 | 4530721 | 143516 | 0 | 0 | 0 | 10000 | 10000 | 450 | The proposed project is an extension of HIT’s current FTTP XGS-PON build in San Benito County, in and around Hollister, San Juan, and Aromas, CA. The major infrastructure to be deployed includes fiber optic cable to unserved, low-income communities primarily in rural environments. Additional project infrastructure includes conduit, handholes, fiber marker posts, splice enclosures, and fiber huts (PoPs). |  | As further detailed in the project cost estimates, our major equipment expenses include: conduit; high count fiber; tracer wire; handholes; splice enclosures; fiber marker posts; optical line terminals (OLT) and switching equipment; points of presence (PoP); small count (drop) fiber; optical network terminals (ONT) and outdoor NIDs; drilling equipment; and customer premise equipment. | Upon notification of grant award, we will immediately begin project engineering and applying for permits. We estimate it will take approximately 3-6 months to complete all permitting requirements, as well as the detailed engineering and fiber design work. We expect to be ready to start construction immediately upon final grant award, with an 18-month project construction schedule. Based on our recent and ongoing experience installing fiber in nearby areas, we estimate an overall construction rate of 36,067 ft/month. While this rate refers to total fiber installed, it encompasses all aspects of project construction and grant administration, including ordering/staging materials, scheduling direct and contract labor, coordinating with Caltrans and other relevant authorities, drilling, setting handholes, installing conduit and fiber, splicing, installing splitters, OLTs and PoPs, and installing drop fiber, ONTs and NIDs on customer premises, as well as project monitoring and reporting and other grant compliance activities. Our major project milestones include: (1) grant award / construction start; (3) 10% construction complete; (4) 35% construction complete; (5) 60% construction complete; (6) 85% construction complete; and (7)100% construction complete / completion report approved. | The proposed project is a fiber-to-the-premises (FTTP) deployment designed to deliver high-performance, scalable, and cost-effective broadband service to unserved households and businesses in the Aromas area of Monterey County. This infrastructure will provide symmetrical 1 Gbps service at launch, utilizing XGS-PON (10-Gigabit-capable Symmetric Passive Optical Network) technology and 10 Gbps-capable active electronics, enabling seamless future upgrades to multi-gigabit speeds as demand increases. The technical design prioritizes underground fiber construction to enhance network resilience, reduce exposure to wildfire and storm-related damage, and minimize visual and environmental impacts. The project will employ compact ½-inch fiber cabling and low-impact trenching and boring methods to reduce construction disturbance, conserve energy, and lower long-term maintenance costs. The project is engineered to provide FTTP to 100% of unserved locations within the proposed project area. Backhaul will be sourced via interconnection with the state-owned Middle Mile Broadband Network (MMBN), ensuring high-capacity, reliable transport. Distribution and aggregation electronics will be housed in weather-resistant, environmentally compliant cabinets installed at strategic nodes along the fiber route. These may include both existing facilities and new cabinet installations, depending on engineering feasibility. This project will be implemented under a lease and operations agreement with HIT (Hankin’s Information Technology), a qualified ISP, while 100% infrastructure ownership will be retained by the California Broadband Alliance (CBA), a 501(c)(3) nonprofit organization committed to expanding digital equity. In alignment with SB 156 and FFA Round 2 goals, this publicly owned infrastructure will be open-access and designed to support future service competition and community control. Project costs have been conservatively and responsibly estimated to reflect actual construction and engineering conditions, with adequate contingency for labor, materials, and permitting. Because the design is primarily underground, the need for pole attachments or aerial deployment is minimal and limited to rare edge cases with no feasible underground access. CBA and HIT affirm a 10-year pricing commitment, including the availability of a low-cost broadband plan for the full project term and beyond. This ensures long-term affordability and broadband adoption across income levels. This project qualifies for ministerial review and is designed to meet the state’s highest priorities for broadband expansion. The project area is among the most underserved in Monterey County, lacking infrastructure capable of delivering 100 Mbps down / 20 Mbps up. This investment will directly help close the digital divide, advancing universal access to fast, reliable, and affordable broadband service.
a0Kcs00000PbVuTEAV | Hoopa Trinity Rural Access Initiative Linkup (Hoopa TRAIL) | Hoopa Valley Public Utilities District | Trinity; Humboldt |  | Linnea Jackson | General Manager | 38874077 | 38874077 | 53498 | 261 | 37 | 12 | 1000 | 1000 | 1866 | Hoopa Valley Public Utilities District (HVPUD) proposes to primarily serve Trinity County and we request remaining funds to deploy fiber to unserved locations in Willow Creek in Humboldt County. Throughout the application, we have separated Trinity and Humboldt County project details where possible. HVPUD will deploy 80 miles of fiber to serve 1,425 broadband serviceable locations (BSLs) in the Trinity County portion of the proposed project and 27 miles of fiber to serve 695 BSLs in the Humboldt County portion of the project. While Trinity County is our primary project request, we are requesting the remaining LMFFA funds from Humboldt County because this portion of the proposed project not only improves financial viability of the network, it’s also a critical and logical expansion of our funded network that will be deployed in and around Willow Creek. Additionally, we have nearly completed the high level design and environmental reviews of the Willow Creek portion of the project with funds from the CPUC LATA grant program. Including the Humboldt County portion of the project, therefore, will ensure CPUC’s previous investment in broadband planning is fully leveraged to serve the residents in this area. The combined Trinity County and Humboldt County project approach reduces our cost per pass and provides cost-effective use of State funds. The proposed project expands our broadband network and will connect to the central office in Hoopa, CA. We will deploy both XGS-PON and G-PON fiber. We will utilize G-PON for last mile connections requiring longer lengths than XGS-PON technology can reliably provide and only in areas where XGS-PON speeds will not be in demand in the foreseeable future. We will deploy 6 new active and 9 new inactive cabinets in Trinity County and 1 new active and 2 new inactive cabinets in Humboldt County. We have defaulted to aerial deployment to reach as many BSLs as possible, which enhances deployment cost efficiency. 96% of the proposed fiber will be deployed aerially. To enhance network resilience and minimize downtime risks from environmental and above-ground hazards, we have incorporated underground deployment segments between cabinets where financially feasible. These segments will connect active and inactive cabinets within the proposed network. Underground deployment across the proposed project is not financially viable. There are many BSLs in the project area, for example, that require long fiber runs to serve a single location, making aerial deployment more cost effective. There also is a lot of granite terrain in the project area, making trenching, boring, or drilling cost prohibitive to deploy underground fiber. HVPUD plans to interconnect with the statewide Middle Mile Broadband Network at 7 points across the project area. As a contingency alternative, HVPUD is seeking clarification on the use of Digital 299 for HVPUD’s middle mile use to serve the proposed project area. Our budget assumes that we will be required to obtain an IRU to connect to the statewide Middle Mile Broadband Network. We will secure pole attachment agreements with Frontier, ATT, PG&E, Trinity PUD, Hunter Communications for aerial fiber deployment across the proposed project area. | 3.6 | We have designed the proposed project with the use of high-quality, carrier-grade equipment to avoid frequent replacements and ensure reliable service. All installation and equipment costs will be included in the RFP for a construction contractor. We anticipate the possible installation equipment will include Bucket Trucks (Aerial Lifts), Pole Auger/Drill Rigs, Horizontal Directional Drill (HDD) Rig, Fluid Mixing and Containment Systems, Trenchers, Excavators, and other standard broadband installation equipment. We have budgeted $15,501,392 or our partnership with a construction contractor. HVPUD uses XGS-PON capable core network equipment, including border routers, core routers, transport switches and customer aggregation routers. Edge and distribution equipment proposed for the active cabinets will include battery backups, generators, fencing, and environmental controls. We will deploy fiber counts with a minimum 15% excess capacity to allow for sufficient future expansion. ​​The last mile and customer serving equipment includes NIDs and Wifi 7-capable ONTs. HVPUD will offer up to 1 Gbps synchronous speeds in the proposed project area. This network equipment will enable HVPUD to easily supply those speeds and less than 10-millisecond latency over the proposed network by following the manufacturing build specifications. | HVPUD anticipates the following timeline(s) to complete, based on a grant award date of September 1, 2025. Timeline Based on 24 months for CEQA Review: Kickoff/Planning – 1 month Begins: 9/1/25 Ends: 9/30/25 Environmental/Engineering Permitting – 13 months Beings: 9/2/25 Ends: 10/31/26 Staking and Locates - 1 month Begins: 10/1/26 Ends:10/31/26 Construction – 9 months Begins: 11/1/26 Ends: 8/31/27 Project planning and kickoff will involve coordination with a range of internal and external stakeholders, the procurement of subcontractors, and the assignment of responsibilities to existing HVPUD personnel. The environmental, engineering, and permitting phase will provide the necessary time to conduct all required surveys, prepare reports, submit permit applications, and secure approvals from relevant agencies, including State of California (CEQA/NEPA lead), Trinity County, Humboldt County, Caltrans, USFS, and BLM. Once all necessary approvals have been obtained, construction will begin. This phase will include pre-construction meetings with the selected contractor, ongoing progress reporting, fiber installation, splicing, testing, and comprehensive documentation of the plant infrastructure. Service installations and turn up will happen throughout this time as locations become available. | HVPUD will deploy XGS-PON and G-PON fiber capable of gigabit symmetric speeds with less than 100ms latency across the project area in Trinity County and Humboldt County. While we plan to install all fiber within previously disturbed rights-of-way when possible, we will not know the full scope of environmental review until environmental review discovery is complete. Based on the project’s minimal ground disturbance, adherence to existing utility corridors, limited new infrastructure, and design focused on impact avoidance, the project as a whole (including both the Humboldt County and Trinity County portions of the project together) may qualify for a Categorical Exemption under CEQA (rationale below). However, we conservatively budgeted for an Initial Study and Mitigated Negative Declaration (IS/MND) in case the project is not found to be CEQA exempt. The Willow Creek/ Humboldt County portion alone is likely CEQA exempt. We will leverage the infrastructure that we are currently deploying across the Hoopa Valley Reservation, including a data center in Hoopa, backhaul and middle mile fiber, and potentially our Digital 299 IRU for dark fiber from Vero Networks if allowed. We will also connect with the statewide middle mile network for a 10GB north and 10GB south connection. The section of the statewide MMBN that we proposed to connect with in this project is ahead of schedule and we are optimistic that we will be able to interconnect with it by our deadline by Jan 1, 2027. This project will not include any middle mile construction. We acknowledge that FFA funded middle-mile infrastructure must be made available to provide nondiscriminatory interconnection, internet access, and the provision of dark fiber, at reasonable and equal terms to any communications service provider that wishes to interconnect with that infrastructure, wherever technically feasible and that the middle-mile segment(s) shall be deemed open access for the duration of the lifetime of that infrastructure.
a0Kcs00000PYUjdEAH | Inyo-Bishop | Frontier California Inc. | Inyo | U-1002-C | Diane Williams-Stinson | Vice President, Grant Administration | 5905494 | 6482430 | 57189 | 29 | 0 | 0 | 7000 | 7000 | 294 | INFRASTRUCTURE Frontier’s FTTP infrastructure far exceeds the minimum speed, performance, operational, and latency requirements of the FFA program. Frontier follows industry standard fiber network architecture and utilizes a Centralized Split (CS) architecture, in which a single split point is added between the central office and end user customers. This architecture provides a balance between upfront costs, bandwidth capability, and future scalability and reflects a network design consistent with industry best practices. NETWORK DESIGN Frontier is proposing XGS-PON FTTP architecture because of its superior performance, scalability, resiliency, and speeds that far exceed both minimum FFA requirements and current and future bandwidth needs. Frontier’s design includes an Optical Line Terminal (OLT) and other Central Office (CO) fiber-capable electronics, as needed, to support fiber services to the end user. The OLT connects to Fiber Distribution Hubs (FDHs) and Fiber Distribution Terminals (FDTs), within the community, to provide a dedicated fiber connection to each customer location. Following standard CS architecture, Frontier uses feeder cables with a lower fiber count to connect to a centralized FDH located closer to the premises. A splitter at the FDH provides a transition between feeder and distribution fibers and to support a dedicated connection to the premises. Frontier deploys fiber facilities, including splitters and OLTs with sufficient ports to meet both current requirements and anticipated future growth. Split ratios are adjustable to accommodate network needs or to improve OLT efficiency, providing adaptability across diverse geographical densities. The project network design includes fiber deployed past each project location in public rights-of-way and authorized easements. Frontier intends to exceed minimum speed and latency requirements through its use of XGS-PON technology, the deployment of 4 FDHs and 279 FDTs strategically placed and of sufficient capacity to serve the project area. The proposed project includes approximately 10 miles of underground fiber (39%) and approximately 16 miles of aerial fiber (61%). Frontier intends to leverage use of its 298 owned poles and 188 jointly owned poles and existing pole attachments in the project area. Frontier plans to utilize the equipment or components of its existing network as appropriate. For example, it may over-lash new fiber facilities onto existing aerial copper infrastructure, and repurpose existing central office buildings, conduits, and other assets that are still within their useful lives, to support the FTTP deployment and help minimize overall subsidy investment. Frontier intends to leverage its existing operations to support services to the grant locations, including field technicians for service installation upon customer order, maintenance and repair, customer service personnel, and its Network Operations Centers to monitor and maintain network performance, among other established corporate functions. Frontier has created a high-level design using its existing tools and data about the project area, including the location and capabilities of existing network facilities, as well as its local knowledge. Once a project is awarded (i.e., approved) Frontier undertakes a more in-depth detailed planning and engineering process to finalize the project specifications and ensure it has accurately articulated the planned project routes and necessary project equipment, including: OLTs, fiber equipment and electronics, cable sizes, FDHs, and FDTs to be constructed as part of the project. A Bill of Materials is generated to order project materials. Frontier’s network architecture design process follows stringent design principles to support the scalability and reliability of the network. Frontier exclusively uses XGS-PON (10 Gigabit Symmetrical Passive Optical Network) architecture, which supports a range of high-speed broadband services, including Frontier’s newly launched 7 Gbps symmetrical tier. XGS-PON can support even higher speeds using the same fiber infrastructure. Frontier's network is designed for scalability and supports a range of high-speed configurations, including 25 GPON, 50 GPON, and 100 GPON services. In collaboration with Nokia, Frontier was the first in North America to successfully trial simultaneous speeds of 10 Gbps, 25 Gbps, 50 Gbps, and 100 Gbps on its existing infrastructure. Frontier’s design process adheres to established industry standards, including network resiliency and hardening standards such as Telcordia Blue Book and FEMA guidelines. In addition, Frontier takes weather- and climate-related risks into account when planning and constructing its networks by assessing climate risks and implementing mitigation strategies. Frontier plans and builds its networks in a climate-resilient manner to provide sustainability far beyond the project's performance period. | 38.5 | Major expenses for this project include detailed engineering and design, inside plant and outside plant construction (both aerial and buried), permitting, installation of fiber equipment and electronics. Frontier utilizes the same equipment in its independently funded and grant funded FTTP network deployments. In addition, a breakdown of the estimated major equipment expenses for this FTTP project are included in the Estimated Direct Costs attachment. Below is a list of network components Frontier typically utilizes: [BEGIN CONFIDENTIAL] Network Routers Nokia 7750 SR-1, a two-rack unit Broadband Network Gateway (BNG) router, which aggregates all the traffic, northbound from the XGS-OLT’s Nokia 7750 SR-2s, a five-rack unit Broadband Network Gateway (BNG) router, which aggregates all the traffic, northbound from the XGS-OLT’s Nokia 7750 SR-7, an eight-rack unit Broadband Network Gateway (BNG) router, which aggregates all the traffic, northbound from the XGS-OLT’s Juniper Networks MX960. a Core Aggregation Router (CAR) router, which aggregates all the traffic, northbound from the BNG’s Network Switches : Nokia 7360 FX-8 XGS-PON Optical Line Terminal (OLT), which aggregates all XGS-PON terminations from the Fiber Distribution Hubs (FDH) Cisco 4900M (VOIP), which provides Voice over Internet Protocol connections through all network routers and distributes it to the XGS-OLT’s, then eventually the ONT Cambridge Industries Group (CIG) switches (utilized in some instances). The initial and expansion capacities for each subsystem as initially purchased are as follows: Nokia 7750 SR-1, SR-2s, & SR-7: 2.4 Terabit per second (TB/s) total capacity with initial 10G/s or 100G/s capacity, depending on configuration and density Juniper Networks MX960: 10.56 Terabit per second (TB/s) total capacity with initial 10G/s or 100G/s capacity, depending on configuration and density Nokia 7360 FX-8 XGS-PON OLT: 480 Gigabit per second (GB/s) total capacity with initial 10G/s capacity, depending on configuration and density Cisco 4900M (VOIP): 1.44 Terabit per second (TB/s) total capacity with initial FRX523 ONT: Initial 100G/100G speed offering, up to 5G/5G speed offering Frontier typically uses cable sizes ranging from a minimum of 144 fiber strands to 864 strands. The appropriate cable size is determined by the number of customers to be served; however, Frontier generally does not use less than 144 fiber strand sized cable [END CONFIDENTIAL] | Frontier intends to complete the project within 24 months of award, which based on the date of this submission, will not permit completion by year end 2026. Accordingly, Frontier recommends that state funding be used for this project, if selected for award. Frontier’s project management leverages its established and effective tools and protocols. Activities may occur concurrently, and the budget is tracked throughout the performance period. Frontier’s established project phases, which are consistent with its standard business practices, have supported the deployment of new FTTP infrastructure past approximately 4.9 million locations since 2021. TIMELINE AND MILESTONES The basis for the project plan and estimated timeframes identified in the construction timeline includes the following considerations: Engineering: (Months 1-6) This phase encompasses all detailed planning and engineering for project deployment and the creation of a comprehensive network design. This process involves an analysis of geographical, environmental, and technical factors to create and finalize a detailed network architecture design. The finalized design addresses the aerial and underground installation needs, resilience to environmental factors, and scalability to meet future demand, among other considerations. Engineering includes the following activities: 1) Final Planning Completed; 2) Environmental Assessment; 3) Site Walks & Detailed Engineering; 4) Submit Permit Requests; 5) Third Party Agreements (if needed); and 6) Procurement/Materials Ordering. Construction: (Months 3-15) The Construction phase includes all inside plant and outside plant construction activities, including central office equipment and broadband electronics upgrades, if needed, and all field work to place, splice, and test feeder and distribution fiber, FDHs, and FDTs. Make Ready involves activities needed to complete the proposed fiber deployment project. This process includes verifying the Rights-of-Way (ROWs) and evaluating the existing infrastructure to fully understand the requirements for completing the engineered design. The objective is to determine the optimal path or layout for construction and leverage Frontier’s existing infrastructure, such as existing facilities on poles for over-lashing fiber, to the extent feasible. Additionally, it consists of securing necessary permits and legal clearances for work within both public and private ROWs. Prior to starting construction, Frontier meets with local officials and permitting authorities to discuss the project scope and timeline and works with local officials to ensure that they are prepared to respond to community members’ questions about the project. Frontier coordinates with local utility companies and permitting authorities throughout the build to ensure permits are obtained timely and support the overall deployment schedule. The phase involves confirmation that existing poles and supporting structures are sufficiently strong and that the required height clearances for new cable installations can be achieved. Frontier owns 298 poles and co-owns 188 poles in the project area has existing pole attachment rights and existing attachments. Construction includes the following activities: 1) Equipment Installation – Inside (CO) and Outside Plant Work; 2) Obtain Permits; 3) Pole Make-Ready; 4) Fiber Placement; 5) Fiber Hub Placement; 6) Electronics Installation; 7) Splicing; and 8) Fiber Testing. Test and Turn Up (Months 9-23): During this phase, Frontier tests deployed facilities and the network to confirm functionality, reliability, and speed and adjustments necessary so that the system is ready for provisioning of high-speed fiber broadband service, upon a customer order. Specific addresses are open for sale and customers may order and receive broadband service on a rolling basis as construction is completed in phases and the network is confirmed operational. Test and Turn Up includes the following activities: 1) Network Continuity Testing and Production Ready; and 2) Offer Service (fiber sales generally begin within 48 hours of construction completion/hub activation). Project Closeout (Months 22-24): This is the final project phase and involves audits to verify that construction and installation work is complete, permits are closed, and post-installation testing confirms compliance with grant requirements. In addition, required documentation is submitted, along with final performance and financial reports. As noted above, the project requires 24 months to complete, which does not permit completion by year end 2026. | Frontier proposes deploying a last mile FTTP XGS-PON network that will make up to 7 Gbps symmetrical service available to 294 locations in the community of Bishop, Inyo County. Based on expansion capability of up to 10 Gbps (without the addition of system electronics or major fiber builds), the project proposes to deploy infrastructure to meet current and future needs. The proposed XPON fiber network is capable of scaling to support 25 Gbps and 50 Gbps symmetrical speeds as capacity needs grow. In general, proposed fiber routes are located along local roadways; however, some segments are on or adjacent to highways. Please refer to the response to Question #2 in the CEQA Section for additional details. Fiber is installed using a combination of existing infrastructure, where available, supplemented by new underground conduit and/or aerial installations. Required new infrastructure is installed within existing ROWs and utility easements. For this project, the proposed fiber deployment is to take place in developed areas where previous ground-disturbance activities have occurred. Underground conduit is generally installed at a depth of 18 to 48 inches by either boring, trenching, or plowing, depending on the location and local, state, and federal requirements. In some cases, to avoid existing infrastructure, new underground conduits may be required to be installed significantly deeper. Frontier anticipates the proposed project will either be categorically exempt from CEQA review, pursuant to CEQA guidelines 14 C.C.R. § 15303 (Class 3) regarding new construction or conversion of small structures; or will require development of a Mitigated Negative Declaration (MND). Final engineering design and planning work, which takes place at the first stage following an award and involves a more detailed review of resources present helps to determine the level of CEQA review required for the project. Frontier intends to leverage its existing infrastructure within public ROWs and authorized easements in addition to existing poles, underground systems, and where Frontier currently has underground conduit and facilities. Frontier is not seeking grant funding for middle mile facilities as part of this application.
a0Kcs00000PmzxGEAR | Inyo-Lone Pine | Frontier California Inc. | Inyo | U-1002-C | Diane Williams-Stinson | Vice President, Grant Administration | 3887745 | 4207516 | 63466 | 36 | 0 | 1 | 7000 | 7000 | 172 | INFRASTRUCTURE Frontier’s FTTP infrastructure far exceeds the minimum speed, performance, operational, and latency requirements of the FFA program. Frontier follows industry standard fiber network architecture and utilizes a Centralized Split (CS) architecture, in which a single split point is added between the central office and end user customers. This architecture provides a balance between upfront costs, bandwidth capability, and future scalability and reflects a network design consistent with industry best practices. NETWORK DESIGN Frontier is proposing XGS-PON FTTP architecture because of its superior performance, scalability, resiliency, and speeds that far exceed both minimum FFA requirements and current and future bandwidth needs. Frontier’s design includes an Optical Line Terminal (OLT) and other Central Office (CO) fiber-capable electronics, as needed, to support fiber services to the end user. The OLT connects to Fiber Distribution Hubs (FDHs) and Fiber Distribution Terminals (FDTs), within the community, to provide a dedicated fiber connection to each customer location. Following standard CS architecture, Frontier uses feeder cables with a lower fiber count to connect to a centralized FDH located closer to the premises. A splitter at the FDH provides a transition between feeder and distribution fibers and to support a dedicated connection to the premises. Frontier deploys fiber facilities, including splitters and OLTs with sufficient ports to meet both current requirements and anticipated future growth. Split ratios are adjustable to accommodate network needs or to improve OLT efficiency, providing adaptability across diverse geographical densities. The project network design includes fiber deployed past each project location in public rights-of-way and authorized easements. Frontier intends to exceed minimum speed and latency requirements through its use of XGS-PON technology, the deployment of 1 OLT in the central office serving the project area, 2 FDHs and 152 FDTs strategically placed and of sufficient capacity to serve the project area. The proposed project includes approximately 9 miles of underground fiber (40%) and approximately 13 miles of aerial fiber (60%). Frontier intends to leverage use of its 21 owned poles and 308 jointly owned poles and existing pole attachments in the project area. Frontier plans to utilize the equipment or components of its existing network as appropriate. For example, it may over-lash new fiber facilities onto existing aerial copper infrastructure, and repurpose existing central office buildings, conduits, and other assets that are still within their useful lives, to support the FTTP deployment and help minimize overall subsidy investment. Frontier intends to leverage its existing operations to support services to the grant locations, including field technicians for service installation upon customer order, maintenance and repair, customer service personnel, and its Network Operations Centers to monitor and maintain network performance, among other established corporate functions. Frontier has created a high-level design using its existing tools and data about the project area, including the location and capabilities of existing network facilities, as well as its local knowledge. Once a project is awarded (i.e., approved) Frontier undertakes a more in-depth detailed planning and engineering process to finalize the project specifications and ensure it has accurately articulated the planned project routes and necessary project equipment, including: OLTs, fiber equipment and electronics, cable sizes, FDHs, and FDTs to be constructed as part of the project. A Bill of Materials is generated to order project materials. Frontier’s network architecture design process follows stringent design principles to support the scalability and reliability of the network. Frontier exclusively uses XGS-PON (10 Gigabit Symmetrical Passive Optical Network) architecture, which supports a range of high-speed broadband services, including Frontier’s newly launched 7 Gbps symmetrical tier. XGS-PON can support even higher speeds using the same fiber infrastructure. Frontier's network is designed for scalability and supports a range of high-speed configurations, including 25 GPON, 50 GPON, and 100 GPON services. In collaboration with Nokia, Frontier was the first in North America to successfully trial simultaneous speeds of 10 Gbps, 25 Gbps, 50 Gbps, and 100 Gbps on its existing infrastructure. Frontier’s design process adheres to established industry standards, including network resiliency and hardening standards such as Telcordia Blue Book and FEMA guidelines. In addition, Frontier takes weather- and climate-related risks into account when planning and constructing its networks by assessing climate risks and implementing mitigation strategies. Frontier plans and builds its networks in a climate-resilient manner to provide sustainability far beyond the project's performance period. | 40.9 | Major expenses for this project include detailed engineering and design, inside plant and outside plant construction (both aerial and buried), permitting, installation of fiber equipment and electronics. Frontier utilizes the same equipment in its independently funded and grant funded FTTP network deployments. In addition, a breakdown of the estimated major equipment expenses for this FTTP project are included in the Estimated Direct Costs attachment. Below is a list of network components Frontier typically utilizes: [BEGIN CONFIDENTIAL] Network Routers Nokia 7750 SR-1, a two-rack unit Broadband Network Gateway (BNG) router, which aggregates all the traffic, northbound from the XGS-OLT’s Nokia 7750 SR-2s, a five-rack unit Broadband Network Gateway (BNG) router, which aggregates all the traffic, northbound from the XGS-OLT’s Nokia 7750 SR-7, an eight-rack unit Broadband Network Gateway (BNG) router, which aggregates all the traffic, northbound from the XGS-OLT’s Juniper Networks MX960. a Core Aggregation Router (CAR) router, which aggregates all the traffic, northbound from the BNG’s Network Switches : Nokia 7360 FX-8 XGS-PON Optical Line Terminal (OLT), which aggregates all XGS-PON terminations from the Fiber Distribution Hubs (FDH) Cisco 4900M (VOIP), which provides Voice over Internet Protocol connections through all network routers and distributes it to the XGS-OLT’s, then eventually the ONT Cambridge Industries Group (CIG) switches (utilized in some instances). The initial and expansion capacities for each subsystem as initially purchased are as follows: Nokia 7750 SR-1, SR-2s, & SR-7: 2.4 Terabit per second (TB/s) total capacity with initial 10G/s or 100G/s capacity, depending on configuration and density Juniper Networks MX960: 10.56 Terabit per second (TB/s) total capacity with initial 10G/s or 100G/s capacity, depending on configuration and density Nokia 7360 FX-8 XGS-PON OLT: 480 Gigabit per second (GB/s) total capacity with initial 10G/s capacity, depending on configuration and density Cisco 4900M (VOIP): 1.44 Terabit per second (TB/s) total capacity with initial FRX523 ONT: Initial 100G/100G speed offering, up to 5G/5G speed offering Frontier typically uses cable sizes ranging from a minimum of 144 fiber strands to 864 strands. The appropriate cable size is determined by the number of customers to be served; however, Frontier generally does not use less than 144 fiber strand sized cable [END CONFIDENTIAL] | Frontier intends to complete the project within 24 months of award, which based on the date of this submission, will not permit completion by year end 2026. Accordingly, Frontier recommends that state funding be used for this project, if selected for award. Frontier’s project management leverages its established and effective tools and protocols. Activities may occur concurrently, and the budget is tracked throughout the performance period. Frontier’s established project phases, which are consistent with its standard business practices, have supported the deployment of new FTTP infrastructure past approximately 4.9 million locations since 2021. TIMELINE AND MILESTONES The basis for the project plan and estimated timeframes identified in the construction timeline includes the following considerations: Engineering: (Months 1-6) This phase encompasses all detailed planning and engineering for project deployment and the creation of a comprehensive network design. This process involves an analysis of geographical, environmental, and technical factors to create and finalize a detailed network architecture design. The finalized design addresses the aerial and underground installation needs, resilience to environmental factors, and scalability to meet future demand, among other considerations. Engineering includes the following activities: 1) Final Planning Completed; 2) Environmental Assessment; 3) Site Walks & Detailed Engineering; 4) Submit Permit Requests; 5) Third Party Agreements (if needed); and 6) Procurement/Materials Ordering. Construction: (Months 3-15) The Construction phase includes all inside plant and outside plant construction activities, including central office equipment and broadband electronics upgrades, if needed, and all field work to place, splice, and test feeder and distribution fiber, FDHs, and FDTs. Make Ready involves activities needed to complete the proposed fiber deployment project. This process includes verifying the Rights-of-Way (ROWs) and evaluating the existing infrastructure to fully understand the requirements for completing the engineered design. The objective is to determine the optimal path or layout for construction and leverage Frontier’s existing infrastructure, such as existing facilities on poles for over-lashing fiber, to the extent feasible. Additionally, it consists of securing necessary permits and legal clearances for work within both public and private ROWs. Prior to starting construction, Frontier meets with local officials and permitting authorities to discuss the project scope and timeline and works with local officials to ensure that they are prepared to respond to community members’ questions about the project. Frontier coordinates with local utility companies and permitting authorities throughout the build to ensure permits are obtained timely and support the overall deployment schedule. The phase involves confirmation that existing poles and supporting structures are sufficiently strong and that the required height clearances for new cable installations can be achieved. Frontier owns 21 poles and co-owns 308 poles in the project area has existing pole attachment rights and existing attachments. Construction includes the following activities: 1) Equipment Installation – Inside (CO) and Outside Plant Work; 2) Obtain Permits; 3) Pole Make-Ready; 4) Fiber Placement; 5) Fiber Hub Placement; 6) Electronics Installation; 7) Splicing; and 8) Fiber Testing. Test and Turn Up (Months 9-23): During this phase, Frontier tests deployed facilities and the network to confirm functionality, reliability, and speed and adjustments necessary so that the system is ready for provisioning of high-speed fiber broadband service, upon a customer order. Specific addresses are open for sale and customers may order and receive broadband service on a rolling basis as construction is completed in phases and the network is confirmed operational. Test and Turn Up includes the following activities: 1) Network Continuity Testing and Production Ready; and 2) Offer Service (fiber sales generally begin within 48 hours of construction completion/hub activation). Project Closeout (Months 22-24): This is the final project phase and involves audits to verify that construction and installation work is complete, permits are closed, and post-installation testing confirms compliance with grant requirements. In addition, required documentation is submitted, along with final performance and financial reports. As noted above, the project requires 24 months to complete, which does not permit completion by year end 2026. | Frontier proposes deploying a last mile FTTP XGS-PON network that will make up to 7 Gbps symmetrical service available to 172 locations in the communities of Olancha and Lone Pine, Inyo County. Based on expansion capability of up to 10 Gbps (without the addition of system electronics or major fiber builds), the project proposes to deploy infrastructure to meet current and future needs. The proposed XPON fiber network is capable of scaling to support 25 Gbps and 50 Gbps symmetrical speeds as capacity needs grow. In general, proposed fiber routes are located along local roadways; however, some segments are on or adjacent to highways. Please refer to the response to Question #2 in the CEQA Section for additional details. Fiber is installed using a combination of existing infrastructure, where available, supplemented by new underground conduit and/or aerial installations. Required new infrastructure is installed within existing ROWs and utility easements. For this project, the proposed fiber deployment is to take place in developed areas where previous ground-disturbance activities have occurred. Underground conduit is generally installed at a depth of 18 to 48 inches by either boring, trenching, or plowing, depending on the location and local, state, and federal requirements. In some cases, to avoid existing infrastructure, new underground conduits may be required to be installed significantly deeper. Frontier anticipates the proposed project will either be categorically exempt from CEQA review, pursuant to CEQA guidelines 14 C.C.R. § 15303 (Class 3) regarding new construction or conversion of small structures; or will require development of a Mitigated Negative Declaration (MND). Final engineering design and planning work, which takes place at the first stage following an award and involves a more detailed review of resources present helps to determine the level of CEQA review required for the project. Frontier intends to leverage its existing infrastructure within public ROWs and authorized easements in addition to existing poles, underground systems, and where Frontier currently has underground conduit and facilities.
a0Kcs00000QnAvKEAV | Marina Broadband Expansion | TeraFiber | Monterey | U-7446-C | Mark Kitten | GIS Director | 3762523 | 8908431 | 88518 | 55 | 38 | 12 | 5000 | 5000 | 492 | This project will construct a 100% underground open-access fiber network using microtrenching . The network design follows a distributed architecture with fiber hut(s) , each capable of serving up to 3,500 premises. Each hut will be equipped with XGS-PON Optical Line Terminals (OLTs) , core switching equipment, 1×32 splitters , and redundant power systems (battery backup and generator) to ensure service reliability. From each hut, a dual-duct feeder pathway will support up to 288-strand feeder cables , designed to reach up to 22 distribution vaults . These vaults will each serve approximately 90 demand points , including SFUs, MDUs, and businesses, with fiber strand allocations tailored to the type and unit count of each property. Each vault will also include 6 spare microducts to accommodate future growth and flexibility. Distribution will utilize single loose tube microducts , each supporting up to 24-strand fiber cables . Every home will be served by a dedicated duct, with toby boxes installed between every two homes to facilitate efficient access and drop installation. Drops will be constructed on a service-on-demand basis , ensuring cost-effective deployment and rapid subscriber activation. The entire network will operate as an open-access system , allowing multiple ISPs to deliver service over the same infrastructure. | 100 | Fiber Huts : Prefabricated enclosures housing core network equipment, providing environmental protection and physical security for critical infrastructure. Optical Line Terminals (OLTs) : Installed within each fiber hut to manage and distribute high-speed broadband services across the fiber network using XGS-PON or GPON technology. Core and Distribution Network Equipment : Includes routers, switches, and supporting infrastructure necessary to manage and route broadband traffic from the core network to local distribution areas. Battery Backup Systems and Generators : Ensure continuous network operation during power outages by providing immediate and sustained backup power to the fiber huts and key network nodes. 1×32 XGS-PON/GPON Optical Splitters : Deployed within distribution points to efficiently split a single optical fiber signal into 32 separate subscriber lines, enabling high-density fiber-to-the-premises (FTTP) service. Distribution Vaults : Underground infrastructure that houses fiber splicing and network distribution points, providing accessible yet protected environments for fiber management. Toby Boxes : Smaller access points that serve individual or small clusters of customers, facilitating efficient last-mile fiber connections. Microducts : Narrow, flexible conduits used to house and protect individual fiber strands within the larger network architecture, supporting rapid deployment and future scalability. | Q2 2025 – Q3 2025 Final engineering design and field verification Submission and processing of permit applications Procurement of major materials (fiber, huts, OLTs, vaults, splitters, microducts, etc.) Q3 2025 – Q4 2025 Begin trenching for main conduit routes Deploy fiber huts at designated hub sites Install primary duct bank infrastructure Q4 2025 – Q1 2026 Installation of distribution vaults across network zones Deployment of active core equipment (OLTs, routers, switches) into fiber huts Installation of battery backup and generator systems Q1 2026 – Q2 2026 Fiber optic cable pulling across installed duct routes Fiber splicing at distribution vaults and huts Systematic fiber network testing and validation Q2 2026 – Q3 2026 Phased service activations begin in priority service areas Customer premise connection work initiated in early activation zones Q3 2026 – Q1 2027 Continued phased activations across remaining service areas Completion of all construction activities Final system testing, verification, and project closeout Full service available to all designated addresses | The proposed project will deploy a citywide underground fiber optic broadband network in Marina, California. Leveraging XGS-PON (10-Gigabit Symmetrical Passive Optical Network) technology, the network will deliver symmetrical internet speeds of up to 5 Gbps to residential homes, businesses, and community anchor institutions within the identified service areas. This open-access network will enable multiple Internet Service Providers (ISPs) to offer competitive, high-performance broadband services, ensuring long-term infrastructure scalability and affordability. The project specifically targets unserved and underserved locations, with infrastructure design optimized to avoid overbuilding areas that already have access to qualifying broadband service. The network will be constructed primarily underground to maximize system resiliency and minimize environmental and community impacts
a0Kcs00000QYN3FEAX | Monterey | Comcast Cable Communications Management, LLC | Monterey |  | John A. Gutierrez | Vice President Regulatory Affairs - California | 12339114 | 15388013 | 103480 | 38 | 3 | 1 | 1250 | 1250 | 994 | Comcast proposes to construct a fiber network capable of symmetrical service of 1 gigabit or higher speeds (the “Project”) to the project area identified in section 2 (the “Project Area”) which will include 52 miles of fiber, 0 number of hubs. This Project will not require any additional headends. The network will be highly reliable, with low latency, and bandwidth can be scaled well beyond foreseeable needs. The fiber network would be constructed to connect Comcast’s existing network to additional homes, businesses, and community anchor institutions (“CAIs”) in the Project Area. The newly constructed network will be capable of meeting or exceeding the level of service required by the California Public Utilities Commission’s (“CPUC”) Federal Funding Account (“FFA”) program, with rates and terms consistent with those offered by Comcast in California. Households, businesses, and CAIs in the Project Area would have access to Comcast’s full suite of products and services, which, in addition to broadband service, includes voice, video, and home security services. | 65.4 | Major equipment expenses will include the following: conduit for new underground deployment; messenger strand for aerial deployment; fiber-optic cable; power supplies; vaults and pedestals; fiber-optic transmitters and receivers; Optical Line Terminal (“OLTs”); and all cabling and combiner equipment needed to connect network hubs to the new network. | Comcast has completed the planning and preliminary engineering phase for the Project. Final engineering, design, and construction will commence upon CPUC approval of the proposed Project. The initial tasks of design and construction will include project engineering and right of way preparation. This Project includes a combination of aerial and underground infrastructure as noted above. Comcast will, to the extent feasible, leverage its existing facilities near the Project Area. Based on Comcast’s initial assessment, Comcast anticipates it will complete the Project, which is categorically exempt from CEQA, on a rolling basis within 18 months after CPUC approval is received and necessary permits are obtained. This means that Comcast will activate service as areas are completed so many locations will be able to access service earlier than the completion of the Project. Comcast expects the following milestones: 10% of the Project Area to be complete in 4 months, 35% of the Project to be complete in 8 months, 85% of the Project to be complete in 16 months, with 100% of the Project completed in approximately 18 months. Comcast will use commercially reasonable efforts to complete construction within 18 months after CPUC approval. However, delays in the issuance of permits or other factors beyond Comcast’s reasonable control, such as extreme weather conditions, strikes, fires, pandemics and epidemics, embargoes, actions of civil or military law enforcement authorities, acts of God or other acts of legislative, judicial, executive, or administrative authorities may necessitate an extension of the construction completion date. The chart below is for illustrative purposes only based on Comcast’s current understanding of similar proposed projects, contains assumptions based on current market dynamics, and is subject to change. Date(s) Activity Month 0 Project Approved / Approval Issued Months 1-3 Finalized Design and Engineering Months 3-6 Municipal and Pole Attachment Permits Months 6-18 Construction and Make-Ready work Total Estimated Project Completion = 18 Months | Comcast will build a fiber network capable of symmetrical service of 1 gigabit or higher speeds, serving unserved and underserved communities in the Project Area. This Project will provide service for approximately 994 locations of which 994 are unserved. Access to reliable, high-speed broadband services will enable Project Area customers to take advantage of essential online resources. See response to “A description of the major infrastructure to be deployed” for technologies used. The preliminary CEQA analysis shows all Project construction will meet one or more categorical CEQA exemptions (i.e . , CEQA Guidelines §§ 15301-03: construction involving existing facilities, replacement or reconstruction, and new construction or conversion of small structures), and does not contain any environmentally sensitive areas. Comcast plans to install approximately 52 total miles of broadband network infrastructure. For aerial installation, Comcast will follow GO 95 pole safety and loading requirements and obtain permits and traffic control for proper placement of aerial equipment. For underground installation, Comcast will follow the permitting jurisdiction’s requirements for underground, including obtaining permits and traffic control for access to manholes/handholes and operating underground equipment. Comcast will reasonably return the site to its original condition to the extent feasible following installation. Comcast will leverage compatible and available facilities to support the Project, relying on existing utility poles in rights-of-way for aerial installation where attachments are permitted by the pole owner. Comcast will support make ready to condition poles, where feasible or required for attachment, and rely on its existing core network infrastructure (including hubs) to support the Project. Open access requirements do not apply because Comcast only seeks FFA funds for last mile infrastructure and does not intend to interconnect with the open access statewide Middle Mile Network or any other provider’s infrastructure, but Comcast will keep evaluating middle-mile infrastructure opportunities available to the Project. See Application Section 8. Comcast will connect the Project to its core network in Monterey County sing a newly constructed transport facility detailed in Section 8.
a0Kcs00000QVtsUEAT | Monterey - 1 | Pacific Bell Telephone Company d/b/a AT&T California | Monterey | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 721793.5 | 1443587 | 152446.31 | 232 | 0 | 0 | 5000 | 5000 | 272 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 54.2 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $1,440,699.83 Access Network Electronics $2,887.17 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $1,443,587 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QW6uXEAT | Monterey - 1A | Pacific Bell Telephone Company d/b/a AT&T California | Monterey | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 373918.27 | 747836.54 | 104514.14 | 2 | 0 | 0 | 5000 | 5000 | 112 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 77.3 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $746,341.33 Access Network Electronics $1,495.67 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $747,837 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QW7DtEAL | Monterey - 1B | Pacific Bell Telephone Company d/b/a AT&T California | Monterey | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 2166802.75 | 2601203.78 | 42816.09 | 55 | 0 | 0 | 5000 | 5000 | 125 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 78.1 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $2,596,001.59 Access Network Electronics $5,202.41 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $2,601,204 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QW7DuEAL | Monterey - 1C | Pacific Bell Telephone Company d/b/a AT&T California | Monterey | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 726746.4 | 1453492.79 | 77243 | 0 | 0 | 0 | 5000 | 5000 | 266 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 86.6 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $1,450,586.01 Access Network Electronics $2,906.99 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $1,453,493 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QW7x3EAD | Monterey - 1D | Pacific Bell Telephone Company d/b/a AT&T California | Monterey | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 2792105.09 | 5584210.18 | 72781.56 | 89 | 0 | 0 | 5000 | 5000 | 177 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 77.9 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $5,573,041.58 Access Network Electronics $11,168.42 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $5,584,210 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QVohYEAT | Monterey - 1E | Pacific Bell Telephone Company d/b/a AT&T California | Monterey | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 2719431.29 | 5170021.47 | 76902.36 | 66 | 0 | 0 | 5000 | 5000 | 319 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 80.4 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $5,159,680.96 Access Network Electronics $10,340.04 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $5,170,021 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QW5IZEA1 | Monterey - 1F | Pacific Bell Telephone Company d/b/a AT&T California | Monterey | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 5334519.93 | 10669039.86 | 95744.78 | 75 | 0 | 0 | 5000 | 5000 | 1311 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 70.9 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $10,647,701.92 Access Network Electronics $21,338.08 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $10,669,040 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QW6UkEAL | Monterey - 1G | Pacific Bell Telephone Company d/b/a AT&T California | Monterey | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 4833545.42 | 5623124.46 | 97334.83 | 107 | 0 | 0 | 5000 | 5000 | 311 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 79.7 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $5,611,877.75 Access Network Electronics $11,246.25 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $5,623,124 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QW8xxEAD | Monterey - 1H | Pacific Bell Telephone Company d/b/a AT&T California | Monterey | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 2677271.77 | 3749680.34 | 148652.85 | 22 | 0 | 0 | 5000 | 5000 | 396 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 59.7 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $3,742,180.64 Access Network Electronics $7,499.36 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $3,749,680 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QW94PEAT | Monterey - 1I | Pacific Bell Telephone Company d/b/a AT&T California | Monterey | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 6158690.92 | 6158690.92 | 110547.04 | 5 | 0 | 0 | 5000 | 5000 | 433 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 69.1 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $6,146,373.62 Access Network Electronics $12,317.38 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $6,158,691 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QCdLBEA1 | Monterey Broadband Project | South Valley Internet/LCB Communications LLC | Monterey | U-7243-C | Elise Brentnall | President/Chief Operations Officer | 14311535.83 | 16790262.83 | 109743 | 6 | 2 | 1 | 5000 | 5000 | 1546 | Infrastructure Deployment Description South Valley Internet/LCB Communications LLC Overview of Infrastructure to be Deployed The proposed project will deploy a combination of aerial and underground fiber infrastructure to deliver gigabit-speed broadband services to unserved and underserved areas. The project is designed to be efficient, cost-effective, and minimally disruptive to the environment. Deployment Details Aerial vs. Underground Construction : Approximately 80% of the fiber construction will be aerial, utilizing existing utility poles wherever possible. The remaining 20% of the fiber construction will be underground, installed through directional boring and trenching where allowed. Use of Existing Infrastructure : Existing utility poles will be utilized for aerial fiber placement. All underground fiber will be placed in new conduit. No fiber will be placed in existing underground conduit systems. Trenching and Boring : All underground construction will occur within the existing disturbed public right-of-way (ROW) to minimize environmental impact and facilitate streamlined permitting. Conduit will be placed 36 to 48 inches underground. Fiber and Equipment Specifications : Fiber-optic cables will be installed capable of delivering speeds of 1 Gbps/1 Gbps , 2.5 Gbps , and 5 Gbps service to end-users. New handholes and other outside plant hardware will be installed as needed to support the network. Technology and Services : Tarana Wireless technology will also be utilized to extend gigabit-speed broadband services to rural areas where fiber deployment is not feasible. This hybrid approach ensures maximum coverage while controlling costs. Environmental Compliance : The project is expected to be categorically exempt from CEQA (California Environmental Quality Act) review, as construction will occur in previously disturbed ROW and on existing structures. Project Commitment South Valley Internet/LCB Communications LLC is fully prepared to execute this deployment efficiently, using experienced internal crews and trusted engineering and construction partners. The infrastructure deployed will meet or exceed all applicable industry standards and regulatory requirements. | 43.4 | MST (Multiport Service Terminals) $135,712.50 ONTs (Optical Network Terminals) $173,712.00 Plume 6e SuperPods $134,000.00 ONT Battery $30,000.00 Cat 5e $130.00 Telecom cabinet $25,000.00 SDX Combo PON OLT $12,000.00 SFP+ Combo OLT D2 $450.00 SDX 632V XGS 10G $120.00 SDX UPS Telemetry Cable $80,000.00 SDX Fiber Tray $17,000.00 SFP+ 11.3G 40KM $250.00 Juniper ACX7348 Router $177,038.17 | Project Deployment Timeline South Valley Internet/LCB Communications LLC Infrastructure Deployment Schedule Permitting Start: August 1, 2025 End: October 1, 2025 Materials Procurement Start: September 1, 2025 End: November 30, 2025 Aerial Fiber Construction Start: October 2025 End: May 2026 Underground Fiber Construction Start: January 2026 End: June 2026 Project Completion End of construction: June 2026 Infrastructure and Construction Notes Aerial Build : 80% of the total project will be deployed aerially using existing poles wherever possible. Underground Build : 20% will be constructed underground by directional boring and trenching within existing disturbed public right-of-way (ROW). Fiber Specifications : The network will deliver service options of 1 Gbps/1 Gbps, 2.5 Gbps, and 5 Gbps. Environmental Compliance : Construction will take place in areas previously disturbed to support a CEQA exemption. Use of Existing Infrastructure : Existing poles will be used where feasible. All underground conduit will be newly placed — no use of existing conduit. | Infrastructure Deployment Description South Valley Internet/LCB Communications LLC Overview of Infrastructure to be Deployed The proposed project will deploy a combination of aerial and underground fiber infrastructure to deliver gigabit-speed broadband services to unserved and underserved areas. The project is designed to be efficient, cost-effective, and minimally disruptive to the environment. Deployment Details Aerial vs. Underground Construction : Approximately 80% of the fiber construction will be aerial, utilizing existing utility poles wherever possible. The remaining 20% of the fiber construction will be underground, installed through directional boring and trenching where allowed. Use of Existing Infrastructure : Existing utility poles will be utilized for aerial fiber placement. All underground fiber will be placed in new conduit. No fiber will be placed in existing underground conduit systems. Trenching and Boring : All underground construction will occur within the existing disturbed public right-of-way (ROW) to minimize environmental impact and facilitate streamlined permitting. Conduit will be placed 36 to 48 inches underground. Fiber and Equipment Specifications : Fiber-optic cables will be installed capable of delivering speeds of 1 Gbps/1 Gbps , 2.5 Gbps , and 5 Gbps service to end-users. New handholes and other outside plant hardware will be installed as needed to support the network. Technology and Services : Tarana Wireless technology will also be utilized to extend gigabit-speed broadband services to rural areas where fiber deployment is not feasible. This hybrid approach ensures maximum coverage while controlling costs. Environmental Compliance : The project is expected to be categorically exempt from CEQA (California Environmental Quality Act) review, as construction will occur in previously disturbed ROW and on existing structures. Project Commitment South Valley Internet/LCB Communications LLC is fully prepared to execute this deployment efficiently, using experienced internal crews and trusted engineering and construction partners. The infrastructure deployed will meet or exceed all applicable industry standards and regulatory requirements.
a0Kcs00000QW2cPEAT | Orange - 1 | Pacific Bell Telephone Company d/b/a AT&T California | Orange | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 273947.07 | 547894.14 | 169722 | 19 | 0 | 0 | 5000 | 5000 | 30 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 98.9 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $546,798.21 Access Network Electronics $1,095.79 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $547,894 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QW2uAEAT | Orange - 1A | Pacific Bell Telephone Company d/b/a AT&T California | Orange | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 552204.46 | 1104408.92 | 103553.5 | 91 | 0 | 0 | 5000 | 5000 | 114 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 72.2 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $1,102,200.18 Access Network Electronics $2,208.82 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $1,104,409 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QW4hREAT | Orange - 1B | Pacific Bell Telephone Company d/b/a AT&T California | Orange | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 1327464.7 | 2654929.39 | 62037 | 162 | 0 | 0 | 5000 | 5000 | 290 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 82.9 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $2,649,619.14 Access Network Electronics $5,309.86 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $2,654,929 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QW6UjEAL | Orange - 1C | Pacific Bell Telephone Company d/b/a AT&T California | Orange | U-1001-C | Ross Johnson | Director – Regulatory External and Legislative Affairs | 873244.22 | 1751108.43 | 176428.49 | 1 | 0 | 0 | 5000 | 5000 | 384 | AT&T proposes construction of a ten gigabit per second passive optic network fiber-to-the-premise (XGS-PON FTTP) network, as depicted in Figure 1. The design of the XGS-PON fiber-to-the-premises network is comprised of the Nokia 7360 Optical Line Terminating equipment (OLTs) located primarily in AT&T Central Offices with Corning FlexNap fiber optic cables extending into each area. The fiber optic cable from the OLT is fusion spliced at a (Either Corning or Commscope) distribution cabinet (called Primary Flexibility Points, or PFPs) located in each neighborhood. The PFP contains optical splitters and fiber connectors. Trenching/Poles On the other side of the optical splitter, fiber optic cables are placed in the public Rights of Way (ROW), so they pass each customer location within the service area. The construction and installation of the proposed fiber network will generally follow the existing copper facilities. That is to say, if the current facilities are placed on poles, the new fiber will be placed on poles. Likewise, if the current facilities are buried, the new fiber will be buried using the trenching method. Customer drops to serviceable addresses Customer connections are provided by individual fiber optic cable “drops” from the Corning Evol Fiber Serving Terminal (FST) to each customer location when service is ordered. In a buried environment the “drop” cable is armored with a hardened covering to prevent damage. Customer Premise Equipment At the customer’s home, the fiber optic “drop” connects to an Optical Network Termination (“ONT”) device on the side of the house or, more typically, at an AT&T-installed FiberJack wall plate inside the home. When the ONT is attached to the side of the house, AT&T provides a BGW320 Wi- Fi router for use inside the house. With a FiberJack installation, AT&T provides a combined BGW320 ONT/Wi-Fi router. This network provides the customer with a dedicated internet connection to the home. | 94.3 | Total Cost of materials, engineering, furnishing, and installation of outside plant construction and equipment: Item Cost (USD) Access Network Outside Plant (include structure, cable) $1,747,605.78 Access Network Electronics $3,502.22 Access Network Customer Premise Equipment $0.00 Middle Mile Outside Plant (include structure, cable) $0.00 Middle Mile Electronics $0.00 Land and Building $0.00 Total Project Capital Cost $1,751,108 PROPRIETARY AND CONFIDENTIAL INFORMATION UNDER California Government Code §7927.705; Cal Evid. Code §(1040)(b)(2); Cal. Pub. Util. Comm’n General Order 133-D; Order Instituting Rulemaking to Evaluate Telecommunications Corporations Service Quality Performance and Consider Modification to Service Quality Rules, R.11-12-00, Decision 20-12-021; 118 U.S.C. §1905; the Critical Infrastructure Information Act of 2002, 6 U.S.C. §673(a)(1)(E); Executive Order 12600; and Re New Part 4 of the Commission's Rules Concerning Disruptions to Communications, ET Docket No. 04-35, Report and Order (FCC 04-188), 19 FCC Rcd 16830, ¶40 (2004); MAY NOT BE DISCLOSED PURSUANT TO PUBLIC UTILITES CODE SECTION 583. See the declaration of Ross Johnson dated April 22, 2025. | Anticipated Implementation Schedule Month(s) Grant Funding Approval Zero - Start Ministerial approval or final resolution. Project Plan Development 1 through 10 The local AT&T Network Planner will develop a collaborative plan to ensure a fully optimized fiber network is deployed that will provide the residents with a high performing broadband connection. Detailed Design Creation and Permitting 2 through 13 The local AT&T Engineering team will provide the detailed design of the fiber network from the central office to the customer premises locations. This includes following all required permit submittal processes to secure the necessary approval to place fiber facilities within the respective area. Cable Ordering and Receipt 5 through 14 The local AT&T Scheduling Team will follow the detailed design provided by the AT&T engineering team to order the required fiber optic cable along with all associated material required for the respective projects. They will follow the open material orders to ensure timely receipt of material. Construction Cable and Equipment Placement 6 through 17 The local AT&T Construction team will coordinate the placement of the buried and/or aerial fiber cable along with all associated equipment required to provide end to end connectivity, including handholes, flowerpots, fiber access points, etc. Construction Cable Splicing 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform all splicing activities required to provide fiber service to the residents. This includes performing fusion splices at the various fiber access points and connecting fiber tethers for distribution service. Final Testing and Inventory Validation 9 through 18 AT&T Communication Workers of America (CWA) Technicians will perform OTDR (Optical Time Domain Reflectometer) Testing to ensure connectivity throughout the fiber network, along with quality assurance, and address inventory verification. ﻿ To fully meet all the needs of the state, AT&T will develop a comprehensive work plan for the selected project areas to develop the optimal schedule to meet the State of California objectives. Upon contract execution, AT&T will commit to completing the build in the designated areas within 18 months. The timeline in the table above is only illustrative. Our design team/engineers will perform field visits and provide accurate data for the build path to serve customer locations. We plan to utilize our serving area central office that helps connect the State of California. This is not for any specific location, as the homes on the streets are not served with just one fiber cable but utilize a path which runs east/west or north/south as applicable to the service. | AT&T will deploy a passive optical fiber network using 10 Gigabit per second Symmetrical Passive Optical Network (XGS-PON) technology with a Fiber-to-the-Premises (FTTP) architecture and upgrade its existing FTTP network, which serves Tiers 1-3 customer locations, to XGS-PON. An XGS-PON network operates at 10 Gbps symmetric and AT&T proposes to offer up to 5 Gbps broadband services to residential consumers. AT&T will deploy XGS-PON/FTTP to both existing and new construction customer locations. Aerial fiber will be placed along existing conduit and utility poles. Underground (buried) fiber will be placed in existing rights-of-way, or within private utility easements, on a limited basis. In areas where trenching is performed, the site will be restored by industry-accepted practices. To the extent possible, AT&T will leverage any existing available facilities in the project area including central office equipment, and other deployed facilities.
a0Kcs00000QddybEAB | Pittsburg Broadband Expansion | TeraFiber | Contra Costa | U-7446-C | Mark Kitten | GIS Director | 4889905 | 21416065 | 101099 | 659 | 71 | 10 | 5000 | 5000 | 264 | This project will construct a 100% underground open-access fiber network using microtrenching . The network design follows a distributed architecture with fiber hut(s) , each capable of serving up to 3,500 premises. Each hut will be equipped with XGS-PON Optical Line Terminals (OLTs) , core switching equipment, 1×32 splitters , and redundant power systems (battery backup and generator) to ensure service reliability. From each hut, a dual-duct feeder pathway will support up to 288-strand feeder cables , designed to reach up to 22 distribution vaults . These vaults will each serve approximately 90 demand points , including SFUs, MDUs, and businesses, with fiber strand allocations tailored to the type and unit count of each property. Each vault will also include 6 spare microducts to accommodate future growth and flexibility. Distribution will utilize single loose tube microducts , each supporting up to 24-strand fiber cables . Every home will be served by a dedicated duct, with toby boxes installed between every two homes to facilitate efficient access and drop installation. Drops will be constructed on a service-on-demand basis , ensuring cost-effective deployment and rapid subscriber activation. The entire network will operate as an open-access system , allowing multiple ISPs to deliver service over the same infrastructure. | 100 | Fiber Huts : Prefabricated enclosures housing core network equipment, providing environmental protection and physical security for critical infrastructure. Optical Line Terminals (OLTs) : Installed within each fiber hut to manage and distribute high-speed broadband services across the fiber network using XGS-PON or GPON technology. Core and Distribution Network Equipment : Includes routers, switches, and supporting infrastructure necessary to manage and route broadband traffic from the core network to local distribution areas. Battery Backup Systems and Generators : Ensure continuous network operation during power outages by providing immediate and sustained backup power to the fiber huts and key network nodes. 1×32 XGS-PON/GPON Optical Splitters : Deployed within distribution points to efficiently split a single optical fiber signal into 32 separate subscriber lines, enabling high-density fiber-to-the-premises (FTTP) service. Distribution Vaults : Underground infrastructure that houses fiber splicing and network distribution points, providing accessible yet protected environments for fiber management. Toby Boxes : Smaller access points that serve individual or small clusters of customers, facilitating efficient last-mile fiber connections. Microducts : Narrow, flexible conduits used to house and protect individual fiber strands within the larger network architecture, supporting rapid deployment and future scalability. | Q2 2025 – Q3 2025 Final engineering design and field verification Submission and processing of permit applications Procurement of major materials (fiber, huts, OLTs, vaults, splitters, microducts, etc.) Q3 2025 – Q4 2025 Begin trenching for main conduit routes Deploy fiber huts at designated hub sites Install primary duct bank infrastructure Q4 2025 – Q1 2026 Installation of distribution vaults across network zones Deployment of active core equipment (OLTs, routers, switches) into fiber huts Installation of battery backup and generator systems Q1 2026 – Q2 2026 Fiber optic cable pulling across installed duct routes Fiber splicing at distribution vaults and huts Systematic fiber network testing and validation Q2 2026 – Q3 2026 Phased service activations begin in priority service areas Customer premise connection work initiated in early activation zones Q3 2026 – Q1 2027 Continued phased activations across remaining service areas Completion of all construction activities Final system testing, verification, and project closeout Full service available to all designated addresses | The proposed project will deploy a citywide underground fiber optic broadband network in Pittsburg, California. Leveraging XGS-PON (10-Gigabit Symmetrical Passive Optical Network) technology, the network will deliver symmetrical internet speeds of up to 5 Gbps to residential homes, businesses, and community anchor institutions within the identified service areas. This open-access network will enable multiple Internet Service Providers (ISPs) to offer competitive, high-performance broadband services, ensuring long-term infrastructure scalability and affordability. The project specifically targets unserved and underserved locations, with infrastructure design optimized to avoid overbuilding areas that already have access to qualifying broadband service. The network will be constructed primarily underground to maximize system resiliency and minimize environmental and community impacts.
a0Kcs00000TEtggEAD | Salinas Broadband Expansion | TeraFiber | Monterey | U-7446-C | Mark Kitten | GIS Director | 4016935 | 32795637 | 89150 | 984 | 117 | 21 | 5000 | 5000 | 207 | This project will construct a 100% underground open-access fiber network using microtrenching . The network design follows a distributed architecture with fiber hut(s) , each capable of serving up to 3,500 premises. Each hut will be equipped with XGS-PON Optical Line Terminals (OLTs) , core switching equipment, 1×32 splitters , and redundant power systems (battery backup and generator) to ensure service reliability. From each hut, a dual-duct feeder pathway will support up to 288-strand feeder cables , designed to reach up to 22 distribution vaults . These vaults will each serve approximately 90 demand points , including SFUs, MDUs, and businesses, with fiber strand allocations tailored to the type and unit count of each property. Each vault will also include 6 spare microducts to accommodate future growth and flexibility. Distribution will utilize single loose tube microducts , each supporting up to 24-strand fiber cables . Every home will be served by a dedicated duct, with toby boxes installed between every two homes to facilitate efficient access and drop installation. Drops will be constructed on a service-on-demand basis , ensuring cost-effective deployment and rapid subscriber activation. The entire network will operate as an open-access system , allowing multiple ISPs to deliver service over the same infrastructure. | 100 | Fiber Huts : Prefabricated enclosures housing core network equipment, providing environmental protection and physical security for critical infrastructure. Optical Line Terminals (OLTs) : Installed within each fiber hut to manage and distribute high-speed broadband services across the fiber network using XGS-PON or GPON technology. Core and Distribution Network Equipment : Includes routers, switches, and supporting infrastructure necessary to manage and route broadband traffic from the core network to local distribution areas. Battery Backup Systems and Generators : Ensure continuous network operation during power outages by providing immediate and sustained backup power to the fiber huts and key network nodes. 1×32 XGS-PON/GPON Optical Splitters : Deployed within distribution points to efficiently split a single optical fiber signal into 32 separate subscriber lines, enabling high-density fiber-to-the-premises (FTTP) service. Distribution Vaults : Underground infrastructure that houses fiber splicing and network distribution points, providing accessible yet protected environments for fiber management. Toby Boxes : Smaller access points that serve individual or small clusters of customers, facilitating efficient last-mile fiber connections. Microducts : Narrow, flexible conduits used to house and protect individual fiber strands within the larger network architecture, supporting rapid deployment and future scalability. | Q2 2025 – Q3 2025 Final engineering design and field verification Submission and processing of permit applications Procurement of major materials (fiber, huts, OLTs, vaults, splitters, microducts, etc.) Q3 2025 – Q4 2025 Begin trenching for main conduit routes Deploy fiber huts at designated hub sites Install primary duct bank infrastructure Q4 2025 – Q1 2026 Installation of distribution vaults across network zones Deployment of active core equipment (OLTs, routers, switches) into fiber huts Installation of battery backup and generator systems Q1 2026 – Q2 2026 Fiber optic cable pulling across installed duct routes Fiber splicing at distribution vaults and huts Systematic fiber network testing and validation Q2 2026 – Q3 2026 Phased service activations begin in priority service areas Customer premise connection work initiated in early activation zones Q3 2026 – Q1 2027 Continued phased activations across remaining service areas Completion of all construction activities Final system testing, verification, and project closeout Full service available to all designated addresses | The proposed project will deploy a citywide underground fiber optic broadband network in Salinas, California. Leveraging XGS-PON (10-Gigabit Symmetrical Passive Optical Network) technology, the network will deliver symmetrical internet speeds of up to 5 Gbps to residential homes, businesses, and community anchor institutions within the identified service areas. This open-access network will enable multiple Internet Service Providers (ISPs) to offer competitive, high-performance broadband services, ensuring long-term infrastructure scalability and affordability. The project specifically targets unserved and underserved locations, with infrastructure design optimized to avoid overbuilding areas that already have access to qualifying broadband service. The network will be constructed primarily underground to maximize system resiliency and minimize environmental and community impacts
a0Kcs00000PaAwwEAF | Seaside Broadband Expansion | TeraFiber | Monterey | U-7446-C | Mark Kitten | GIS Director | 3724187 | 6438173 | 82303 | 288 | 29 | 13 | 5000 | 5000 | 280 | This project will construct a 100% underground open-access fiber network using microtrenching . The network design follows a distributed architecture with fiber hut(s) , each capable of serving up to 3,500 premises. Each hut will be equipped with XGS-PON Optical Line Terminals (OLTs) , core switching equipment, 1×32 splitters , and redundant power systems (battery backup and generator) to ensure service reliability. From each hut, a dual-duct feeder pathway will support up to 288-strand feeder cables , designed to reach up to 22 distribution vaults . These vaults will each serve approximately 90 demand points , including SFUs, MDUs, and businesses, with fiber strand allocations tailored to the type and unit count of each property. Each vault will also include 6 spare microducts to accommodate future growth and flexibility. Distribution will utilize single loose tube microducts , each supporting up to 24-strand fiber cables . Every home will be served by a dedicated duct, with toby boxes installed between every two homes to facilitate efficient access and drop installation. Drops will be constructed on a service-on-demand basis , ensuring cost-effective deployment and rapid subscriber activation. The entire network will operate as an open-access system , allowing multiple ISPs to deliver service over the same infrastructure. | 100 | Fiber Huts : Prefabricated enclosures housing core network equipment, providing environmental protection and physical security for critical infrastructure. Optical Line Terminals (OLTs) : Installed within each fiber hut to manage and distribute high-speed broadband services across the fiber network using XGS-PON or GPON technology. Core and Distribution Network Equipment : Includes routers, switches, and supporting infrastructure necessary to manage and route broadband traffic from the core network to local distribution areas. Battery Backup Systems and Generators : Ensure continuous network operation during power outages by providing immediate and sustained backup power to the fiber huts and key network nodes. 1×32 XGS-PON/GPON Optical Splitters : Deployed within distribution points to efficiently split a single optical fiber signal into 32 separate subscriber lines, enabling high-density fiber-to-the-premises (FTTP) service. Distribution Vaults : Underground infrastructure that houses fiber splicing and network distribution points, providing accessible yet protected environments for fiber management. Toby Boxes : Smaller access points that serve individual or small clusters of customers, facilitating efficient last-mile fiber connections. Microducts : Narrow, flexible conduits used to house and protect individual fiber strands within the larger network architecture, supporting rapid deployment and future scalability. | Q2 2025 – Q3 2025 Final engineering design and field verification Submission and processing of permit applications Procurement of major materials (fiber, huts, OLTs, vaults, splitters, microducts, etc.) Q3 2025 – Q4 2025 Begin trenching for main conduit routes Deploy fiber huts at designated hub sites Install primary duct bank infrastructure Q4 2025 – Q1 2026 Installation of distribution vaults across network zones Deployment of active core equipment (OLTs, routers, switches) into fiber huts Installation of battery backup and generator systems Q1 2026 – Q2 2026 Fiber optic cable pulling across installed duct routes Fiber splicing at distribution vaults and huts Systematic fiber network testing and validation Q2 2026 – Q3 2026 Phased service activations begin in priority service areas Customer premise connection work initiated in early activation zones Q3 2026 – Q1 2027 Continued phased activations across remaining service areas Completion of all construction activities Final system testing, verification, and project closeout Full service available to all designated addresses | The proposed project will deploy a citywide underground fiber optic broadband network in Seaside, California. Leveraging XGS-PON (10-Gigabit Symmetrical Passive Optical Network) technology, the network will deliver symmetrical internet speeds of up to 5 Gbps to residential homes, businesses, and community anchor institutions within the identified service areas. This open-access network will enable multiple Internet Service Providers (ISPs) to offer competitive, high-performance broadband services, ensuring long-term infrastructure scalability and affordability. The project specifically targets unserved and underserved locations, with infrastructure design optimized to avoid overbuilding areas that already have access to qualifying broadband service. The network will be constructed primarily underground to maximize system resiliency and minimize environmental and community impacts.
a0Kcs00000Pao6LEAR | Stimulus - Inyo 1 | Stimulus Technologies California, LLC | Inyo | Video Franchise Certificate 0046. Stimulus showed it has sufficient financial and other capabilities to when it obtained its franchise under ? 5840(e)(9) of the Public Utilities Code and should be exempt in the same manner as CPCN holder. | Nathan Whittacre | CEO | 21639160.6 | 21639160.6 | 57500 | 57 | 6 | 2 | 1000 | 1000 | 197 | The proposed broadband network will deploy a carrier-grade, XGS-PON (10 Gigabit-capable Passive Optical Network) fiber-to-the-premises (FTTP) system to serve all Broadband Service Locations (BSLs) within the awarded project areas. This architecture provides symmetrical gigabit services (and higher) and is highly scalable to meet future bandwidth demands. Major Infrastructure Components The following major infrastructure elements will be deployed: 1. Fiber-Optic Cable Fiber Strand Counts: Fiber optic cables will vary from 12-count to 288-count configurations based on network topology, population density, and aggregation needs. Fiber Cable Type: Standard single-mode fiber (SMF-28 or equivalent) suitable for long-distance PON deployments and future wavelength-division multiplexing (WDM) upgrades. Placement Strategy: Approximately 75% of fiber will be placed underground in conduit to improve resilience, longevity, and climate protection. Underground conduit sizes will range from 1” to 2” depending on fiber counts and environmental constraints. Aerial Deployment: The remaining 25% of the fiber infrastructure will be deployed aerially on existing utility poles where feasible and cost-effective, utilizing pole attachments under existing Joint Pole Agreements or permits. 2. Conduit and Handholes Conduit Sizing: Conduit will typically be HDPE (High-Density Polyethylene) material in 1” or 2” diameter sizes. Larger conduit sizes or multiple conduits may be used for backbone fiber or in denser service areas to future-proof the network. Handholes: Handholes will be strategically placed to provide access points for splicing, maintenance, and future expansion without major construction disruption. 3. Optical Line Terminals (OLTs) Equipment: Calix AXOS E7-2 and/or E3-2 hardened OLT platforms will be deployed. Location: OLTs will be installed in environmentally hardened outdoor cabinets or in controlled-environment shelters at central locations within each project area. Capacity: Each OLT chassis can serve thousands of end-points with scalable upgrade paths from 10G XGS-PON to higher next-generation standards (e.g., 25G PON). 4. Fiber Distribution Hubs (FDHs) FDHs will be installed strategically throughout the network to allow for the splitting and distribution of optical signals. Splitter Technology: Passive optical splitters (1:32 split ratio) will be used, depending on service density and engineering design. FDHs will be equipped to allow easy field expansion and reconfiguration as service demand grows. 5. Drop Fibers and Network Interface Devices (NIDs) Individual fibers will run from FDHs to customer premises using hardened fiber drop cables. Termination equipment at the customer premises will include optical network terminals (ONTs) capable of delivering gigabit+ services and integrated with Wi-Fi services where applicable. Existing Facilities to Be Leveraged Stimulus Technologies plans to leverage and interconnect with the following existing assets: Existing Backbone Fiber: Where possible, Stimulus will utilize its existing backbone fiber routes or leased dark fiber assets to connect new project areas to core network aggregation points. Data Centers and Colocation Sites: Our primary points of presence (POPs) in Nevada and California — interconnected via long-haul fiber networks — provide upstream IP transit, peering, and routing capabilities. These will support backhaul for the new networks. Core Network Infrastructure: Stimulus operates existing core routers, switches, and transport systems which are scalable and modular to integrate newly built service areas without requiring significant upgrades. Indefeasible Rights of Use (IRUs): Where necessary, Stimulus may execute IRU agreements with regional fiber owners or consortia to obtain long-term, low-cost access to middle-mile and backhaul transport. We intend to use middle-mile infrastructure built by Stimulus in Nevada along the California border and California MMBN to service the network. If IRUs are available for the CA MMBN, Stimulus will attempt negotiations to use dark-fiber for infrastructure, otherwise Stimulus will utilize metro-ethernet circuits for service. Indefeasible Right of Use (IRU) Details At the time of application, Stimulus Technologies is not in discussions to secure IRUs for dark fiber strands that will complement our owned backbone assets in certain rural areas of California. In the event that IRUs are available, these IRUs will typically have terms of 20 years or longer, aligning with the asset life of the fiber network and ensuring stable, long-term backhaul capacity. If IRUs are finalized during the project implementation phase, documentation and agreements will be provided to the California Public Utilities Commission (CPUC) as required. | 75 | The majority of costs for the project will be related to fiber cable material and construction. For portions of the network where fiber is placed on existing or new pole lines, the construction costs and make ready costs from the pole owners will be the larger costs. For underground construction, the cost of trenching or boring and fiber placement within conduits will outweigh the other costs of hand holes/vaults and splicing. OLT infrastructure costs including fiber distribution hubs are another key cost item but are relatively small in comparison to the fiber material and construction costs. | Stimulus has assumed a 24-month duration for completion of the project. Project planning and engineering will be completed within the first 4 months of project commencement. Environmental and highway permitting has been estimated at 5 months and will start once a portion of the detailed engineering is completed. Procurement activities are expected to take six months but will be able to run in parallel with engineering and permitting. The expectation is that by late Q3 2026, construction build activities will commence. Stimulus will break the work down into four phases so that portions of the project area can be completed and released for customers in 3 to 4 month intervals, the first of which would be expected in December 2026. Marketing activities will commence before completion of construction on the first phase of the build to generate service demand within the project area. Subscriber activations will commence at the end of the first construction phase and continue through to the end of the project. Testing and hand off to operations will also commence at the end of the first construction phase and subsequent phases thereafter followed by final reporting and project closure. | Stimulus will be deploying a fully fiber XGS-PON network to service all eligible BSLs within the project area. Customers will be able to subscribe initially to service with symmetrical speeds of 1Gbps with latency less than 100ms and with the ability for speeds to increase over time as customer demand and usage dictate. The scalable nature of the OLT technology to be used will make the upgrade path to higher speeds cost effective for Stimulus when required. The fiber will be placed through a combination of underground and aerial construction methodologies based upon the location and permitting requirements.
a0Kcs00000QMSRhEAP | Stimulus - Inyo 2 | Stimulus Technologies of California, LLC | Inyo | Video Franchise Certificate 0046. Stimulus showed it has sufficient financial and other capabilities to when it obtained its franchise under ? 5840(e)(9) of the Public Utilities Code and should be exempt in the same manner as CPCN holder. | Nathan Whittacre | CEO | 28481946.72 | 28481946.72 | 57500 | 11 | 2 | 2 | 1000 | 1000 | 76 | The proposed broadband network will deploy a carrier-grade, XGS-PON (10 Gigabit-capable Passive Optical Network) fiber-to-the-premises (FTTP) system to serve all Broadband Service Locations (BSLs) within the awarded project areas. This architecture provides symmetrical gigabit services (and higher) and is highly scalable to meet future bandwidth demands. Major Infrastructure Components The following major infrastructure elements will be deployed: 1. Fiber-Optic Cable Fiber Strand Counts: Fiber optic cables will vary from 12-count to 288-count configurations based on network topology, population density, and aggregation needs. Fiber Cable Type: Standard single-mode fiber (SMF-28 or equivalent) suitable for long-distance PON deployments and future wavelength-division multiplexing (WDM) upgrades. Placement Strategy: Approximately 75% of fiber will be placed underground in conduit to improve resilience, longevity, and climate protection. Underground conduit sizes will range from 1” to 2” depending on fiber counts and environmental constraints. Aerial Deployment: The remaining 25% of the fiber infrastructure will be deployed aerially on existing utility poles where feasible and cost-effective, utilizing pole attachments under existing Joint Pole Agreements or permits. 2. Conduit and Handholes Conduit Sizing: Conduit will typically be HDPE (High-Density Polyethylene) material in 1” or 2” diameter sizes. Larger conduit sizes or multiple conduits may be used for backbone fiber or in denser service areas to future-proof the network. Handholes: Handholes will be strategically placed to provide access points for splicing, maintenance, and future expansion without major construction disruption. 3. Optical Line Terminals (OLTs) Equipment: Calix AXOS E7-2 and/or E3-2 hardened OLT platforms will be deployed. Location: OLTs will be installed in environmentally hardened outdoor cabinets or in controlled-environment shelters at central locations within each project area. Capacity: Each OLT chassis can serve thousands of end-points with scalable upgrade paths from 10G XGS-PON to higher next-generation standards (e.g., 25G PON). 4. Fiber Distribution Hubs (FDHs) FDHs will be installed strategically throughout the network to allow for the splitting and distribution of optical signals. Splitter Technology: Passive optical splitters (1:32 split ratio) will be used, depending on service density and engineering design. FDHs will be equipped to allow easy field expansion and reconfiguration as service demand grows. 5. Drop Fibers and Network Interface Devices (NIDs) Individual fibers will run from FDHs to customer premises using hardened fiber drop cables. Termination equipment at the customer premises will include optical network terminals (ONTs) capable of delivering gigabit+ services and integrated with Wi-Fi services where applicable. Existing Facilities to Be Leveraged Stimulus Technologies plans to leverage and interconnect with the following existing assets: Existing Backbone Fiber: Where possible, Stimulus will utilize its existing backbone fiber routes or leased dark fiber assets to connect new project areas to core network aggregation points. Data Centers and Colocation Sites: Our primary points of presence (POPs) in Nevada and California — interconnected via long-haul fiber networks — provide upstream IP transit, peering, and routing capabilities. These will support backhaul for the new networks. Core Network Infrastructure: Stimulus operates existing core routers, switches, and transport systems which are scalable and modular to integrate newly built service areas without requiring significant upgrades. Indefeasible Rights of Use (IRUs): Where necessary, Stimulus may execute IRU agreements with regional fiber owners or consortia to obtain long-term, low-cost access to middle-mile and backhaul transport. We intend to use middle-mile infrastructure built by Stimulus in Nevada along the California border and California MMBN to service the network. If IRUs are available for the CA MMBN, Stimulus will attempt negotiations to use dark-fiber for infrastructure, otherwise Stimulus will utilize metro-ethernet circuits for service. Indefeasible Right of Use (IRU) Details At the time of application, Stimulus Technologies is not in discussions to secure IRUs for dark fiber strands that will complement our owned backbone assets in certain rural areas of California. In the event that IRUs are available, these IRUs will typically have terms of 20 years or longer, aligning with the asset life of the fiber network and ensuring stable, long-term backhaul capacity. If IRUs are finalized during the project implementation phase, documentation and agreements will be provided to the California Public Utilities Commission (CPUC) as required. | 75 | The majority of costs for the project will be related to fiber cable material and construction. For portions of the network where fiber is placed on existing or new pole lines, the construction costs and make ready costs from the pole owners will be the larger costs. For underground construction, the cost of trenching or boring and fiber placement within conduits will outweigh the other costs of hand holes/vaults and splicing. OLT infrastructure costs including fiber distribution hubs are another key cost item but are relatively small in comparison to the fiber material and construction costs. | Stimulus has assumed a 24-month duration for completion of the project. Project planning and engineering will be completed within the first 4 months of project commencement. Environmental and highway permitting has been estimated at 5 months and will start once a portion of the detailed engineering is completed. Procurement activities are expected to take six months but will be able to run in parallel with engineering and permitting. The expectation is that by late Q3 2026, construction build activities will commence. Stimulus will break the work down into four phases so that portions of the project area can be completed and released for customers in 3 to 4 month intervals, the first of which would be expected in December 2026. Marketing activities will commence before completion of construction on the first phase of the build to generate service demand within the project area. Subscriber activations will commence at the end of the first construction phase and continue through to the end of the project. Testing and hand off to operations will also commence at the end of the first construction phase and subsequent phases thereafter followed by final reporting and project closure. | Stimulus will be deploying a fully fiber XGS-PON network to service all eligible BSLs within the project area. Customers will be able to subscribe initially to service with symmetrical speeds of 1Gbps with latency less than 100ms and with the ability for speeds to increase over time as customer demand and usage dictate. The scalable nature of the OLT technology to be used will make the upgrade path to higher speeds cost effective for Stimulus when required. The fiber will be placed through a combination of underground and aerial construction methodologies based upon the location and permitting requirements.
a0Kcs00000QMYTtEAP | Stimulus - Inyo 3 | Stimulus Technologies of California, LLC | Inyo | Video Franchise Certificate 0046. Stimulus showed it has sufficient financial and other capabilities to when it obtained its franchise under ? 5840(e)(9) of the Public Utilities Code and should be exempt in the same manner as CPCN holder. | Nathan Whittacre | CEO | 6881447.12 | 6881447.12 | 58750 | 13 | 1 | 1 | 1000 | 1000 | 86 | The proposed broadband network will deploy a carrier-grade, XGS-PON (10 Gigabit-capable Passive Optical Network) fiber-to-the-premises (FTTP) system to serve all Broadband Service Locations (BSLs) within the awarded project areas. This architecture provides symmetrical gigabit services (and higher) and is highly scalable to meet future bandwidth demands. Major Infrastructure Components The following major infrastructure elements will be deployed: 1. Fiber-Optic Cable Fiber Strand Counts: Fiber optic cables will vary from 12-count to 288-count configurations based on network topology, population density, and aggregation needs. Fiber Cable Type: Standard single-mode fiber (SMF-28 or equivalent) suitable for long-distance PON deployments and future wavelength-division multiplexing (WDM) upgrades. Placement Strategy: Approximately 75% of fiber will be placed underground in conduit to improve resilience, longevity, and climate protection. Underground conduit sizes will range from 1” to 2” depending on fiber counts and environmental constraints. Aerial Deployment: The remaining 25% of the fiber infrastructure will be deployed aerially on existing utility poles where feasible and cost-effective, utilizing pole attachments under existing Joint Pole Agreements or permits. 2. Conduit and Handholes Conduit Sizing: Conduit will typically be HDPE (High-Density Polyethylene) material in 1” or 2” diameter sizes. Larger conduit sizes or multiple conduits may be used for backbone fiber or in denser service areas to future-proof the network. Handholes: Handholes will be strategically placed to provide access points for splicing, maintenance, and future expansion without major construction disruption. 3. Optical Line Terminals (OLTs) Equipment: Calix AXOS E7-2 and/or E3-2 hardened OLT platforms will be deployed. Location: OLTs will be installed in environmentally hardened outdoor cabinets or in controlled-environment shelters at central locations within each project area. Capacity: Each OLT chassis can serve thousands of end-points with scalable upgrade paths from 10G XGS-PON to higher next-generation standards (e.g., 25G PON). 4. Fiber Distribution Hubs (FDHs) FDHs will be installed strategically throughout the network to allow for the splitting and distribution of optical signals. Splitter Technology: Passive optical splitters (1:32 split ratio) will be used, depending on service density and engineering design. FDHs will be equipped to allow easy field expansion and reconfiguration as service demand grows. 5. Drop Fibers and Network Interface Devices (NIDs) Individual fibers will run from FDHs to customer premises using hardened fiber drop cables. Termination equipment at the customer premises will include optical network terminals (ONTs) capable of delivering gigabit+ services and integrated with Wi-Fi services where applicable. Existing Facilities to Be Leveraged Stimulus Technologies plans to leverage and interconnect with the following existing assets: Existing Backbone Fiber: Where possible, Stimulus will utilize its existing backbone fiber routes or leased dark fiber assets to connect new project areas to core network aggregation points. Data Centers and Colocation Sites: Our primary points of presence (POPs) in Nevada and California — interconnected via long-haul fiber networks — provide upstream IP transit, peering, and routing capabilities. These will support backhaul for the new networks. Core Network Infrastructure: Stimulus operates existing core routers, switches, and transport systems which are scalable and modular to integrate newly built service areas without requiring significant upgrades. Indefeasible Rights of Use (IRUs): Where necessary, Stimulus may execute IRU agreements with regional fiber owners or consortia to obtain long-term, low-cost access to middle-mile and backhaul transport. We intend to use middle-mile infrastructure built by Stimulus in Nevada along the California border and California MMBN to service the network. If IRUs are available for the CA MMBN, Stimulus will attempt negotiations to use dark-fiber for infrastructure, otherwise Stimulus will utilize metro-ethernet circuits for service. Indefeasible Right of Use (IRU) Details At the time of application, Stimulus Technologies is not in discussions to secure IRUs for dark fiber strands that will complement our owned backbone assets in certain rural areas of California. In the event that IRUs are available, these IRUs will typically have terms of 20 years or longer, aligning with the asset life of the fiber network and ensuring stable, long-term backhaul capacity. If IRUs are finalized during the project implementation phase, documentation and agreements will be provided to the California Public Utilities Commission (CPUC) as required. | 75 | The majority of costs for the project will be related to fiber cable material and construction. For portions of the network where fiber is placed on existing or new pole lines, the construction costs and make ready costs from the pole owners will be the larger costs. For underground construction, the cost of trenching or boring and fiber placement within conduits will outweigh the other costs of hand holes/vaults and splicing. OLT infrastructure costs including fiber distribution hubs are another key cost item but are relatively small in comparison to the fiber material and construction costs. | Stimulus has assumed a 24-month duration for completion of the project. Project planning and engineering will be completed within the first 4 months of project commencement. Environmental and highway permitting has been estimated at 5 months and will start once a portion of the detailed engineering is completed. Procurement activities are expected to take six months but will be able to run in parallel with engineering and permitting. The expectation is that by late Q3 2026, construction build activities will commence. Stimulus will break the work down into four phases so that portions of the project area can be completed and released for customers in 3 to 4 month intervals, the first of which would be expected in December 2026. Marketing activities will commence before completion of construction on the first phase of the build to generate service demand within the project area. Subscriber activations will commence at the end of the first construction phase and continue through to the end of the project. Testing and hand off to operations will also commence at the end of the first construction phase and subsequent phases thereafter followed by final reporting and project closure. | Stimulus will be deploying a fully fiber XGS-PON network to service all eligible BSLs within the project area. Customers will be able to subscribe initially to service with symmetrical speeds of 1Gbps with latency less than 100ms and with the ability for speeds to increase over time as customer demand and usage dictate. The scalable nature of the OLT technology to be used will make the upgrade path to higher speeds cost effective for Stimulus when required. The fiber will be placed through a combination of underground and aerial construction methodologies based upon the location and permitting requirements.
a0Kcs00000QMZcrEAH | Stimulus - Inyo 4 | Stimulus Technologies of California, LLC | Inyo | Video Franchise Certificate 0046. Stimulus showed it has sufficient financial and other capabilities to when it obtained its franchise under ? 5840(e)(9) of the Public Utilities Code and should be exempt in the same manner as CPCN holder. | Nathan Whittacre | CEO | 13557408.52 | 13557408.52 | 58750 | 53 | 3 | 4 | 1000 | 1000 | 203 | The proposed broadband network will deploy a carrier-grade, XGS-PON (10 Gigabit-capable Passive Optical Network) fiber-to-the-premises (FTTP) system to serve all Broadband Service Locations (BSLs) within the awarded project areas. This architecture provides symmetrical gigabit services (and higher) and is highly scalable to meet future bandwidth demands. Major Infrastructure Components The following major infrastructure elements will be deployed: 1. Fiber-Optic Cable Fiber Strand Counts: Fiber optic cables will vary from 12-count to 288-count configurations based on network topology, population density, and aggregation needs. Fiber Cable Type: Standard single-mode fiber (SMF-28 or equivalent) suitable for long-distance PON deployments and future wavelength-division multiplexing (WDM) upgrades. Placement Strategy: Approximately 75% of fiber will be placed underground in conduit to improve resilience, longevity, and climate protection. Underground conduit sizes will range from 1” to 2” depending on fiber counts and environmental constraints. Aerial Deployment: The remaining 25% of the fiber infrastructure will be deployed aerially on existing utility poles where feasible and cost-effective, utilizing pole attachments under existing Joint Pole Agreements or permits. 2. Conduit and Handholes Conduit Sizing: Conduit will typically be HDPE (High-Density Polyethylene) material in 1” or 2” diameter sizes. Larger conduit sizes or multiple conduits may be used for backbone fiber or in denser service areas to future-proof the network. Handholes: Handholes will be strategically placed to provide access points for splicing, maintenance, and future expansion without major construction disruption. 3. Optical Line Terminals (OLTs) Equipment: Calix AXOS E7-2 and/or E3-2 hardened OLT platforms will be deployed. Location: OLTs will be installed in environmentally hardened outdoor cabinets or in controlled-environment shelters at central locations within each project area. Capacity: Each OLT chassis can serve thousands of end-points with scalable upgrade paths from 10G XGS-PON to higher next-generation standards (e.g., 25G PON). 4. Fiber Distribution Hubs (FDHs) FDHs will be installed strategically throughout the network to allow for the splitting and distribution of optical signals. Splitter Technology: Passive optical splitters (1:32 split ratio) will be used, depending on service density and engineering design. FDHs will be equipped to allow easy field expansion and reconfiguration as service demand grows. 5. Drop Fibers and Network Interface Devices (NIDs) Individual fibers will run from FDHs to customer premises using hardened fiber drop cables. Termination equipment at the customer premises will include optical network terminals (ONTs) capable of delivering gigabit+ services and integrated with Wi-Fi services where applicable. Existing Facilities to Be Leveraged Stimulus Technologies plans to leverage and interconnect with the following existing assets: Existing Backbone Fiber: Where possible, Stimulus will utilize its existing backbone fiber routes or leased dark fiber assets to connect new project areas to core network aggregation points. Data Centers and Colocation Sites: Our primary points of presence (POPs) in Nevada and California — interconnected via long-haul fiber networks — provide upstream IP transit, peering, and routing capabilities. These will support backhaul for the new networks. Core Network Infrastructure: Stimulus operates existing core routers, switches, and transport systems which are scalable and modular to integrate newly built service areas without requiring significant upgrades. Indefeasible Rights of Use (IRUs): Where necessary, Stimulus may execute IRU agreements with regional fiber owners or consortia to obtain long-term, low-cost access to middle-mile and backhaul transport. We intend to use middle-mile infrastructure built by Stimulus in Nevada along the California border and California MMBN to service the network. If IRUs are available for the CA MMBN, Stimulus will attempt negotiations to use dark-fiber for infrastructure, otherwise Stimulus will utilize metro-ethernet circuits for service. Indefeasible Right of Use (IRU) Details At the time of application, Stimulus Technologies is not in discussions to secure IRUs for dark fiber strands that will complement our owned backbone assets in certain rural areas of California. In the event that IRUs are available, these IRUs will typically have terms of 20 years or longer, aligning with the asset life of the fiber network and ensuring stable, long-term backhaul capacity. If IRUs are finalized during the project implementation phase, documentation and agreements will be provided to the California Public Utilities Commission (CPUC) as required. | 75 | The majority of costs for the project will be related to fiber cable material and construction. For portions of the network where fiber is placed on existing or new pole lines, the construction costs and make ready costs from the pole owners will be the larger costs. For underground construction, the cost of trenching or boring and fiber placement within conduits will outweigh the other costs of hand holes/vaults and splicing. OLT infrastructure costs including fiber distribution hubs are another key cost item but are relatively small in comparison to the fiber material and construction costs. | Stimulus has assumed a 24-month duration for completion of the project. Project planning and engineering will be completed within the first 4 months of project commencement. Environmental and highway permitting has been estimated at 5 months and will start once a portion of the detailed engineering is completed. Procurement activities are expected to take six months but will be able to run in parallel with engineering and permitting. The expectation is that by late Q3 2026, construction build activities will commence. Stimulus will break the work down into four phases so that portions of the project area can be completed and released for customers in 3 to 4 month intervals, the first of which would be expected in December 2026. Marketing activities will commence before completion of construction on the first phase of the build to generate service demand within the project area. Subscriber activations will commence at the end of the first construction phase and continue through to the end of the project. Testing and hand off to operations will also commence at the end of the first construction phase and subsequent phases thereafter followed by final reporting and project closure. | Stimulus will be deploying a fully fiber XGS-PON network to service all eligible BSLs within the project area. Customers will be able to subscribe initially to service with symmetrical speeds of 1Gbps with latency less than 100ms and with the ability for speeds to increase over time as customer demand and usage dictate. The scalable nature of the OLT technology to be used will make the upgrade path to higher speeds cost effective for Stimulus when required. The fiber will be placed through a combination of underground and aerial construction methodologies based upon the location and permitting requirements.
a0Kcs00000QMa97EAD | Stimulus - Inyo 5 | Stimulus Technologies of California, LLC | Inyo | Video Franchise Certificate 0046. Stimulus showed it has sufficient financial and other capabilities to when it obtained its franchise under ? 5840(e)(9) of the Public Utilities Code and should be exempt in the same manner as CPCN holder. | Nathan Whittacre | CEO | 2767851.45 | 2767851.45 | 34286 | 8 | 0 | 0 | 1000 | 1000 | 27 | The proposed broadband network will deploy a carrier-grade, XGS-PON (10 Gigabit-capable Passive Optical Network) fiber-to-the-premises (FTTP) system to serve all Broadband Service Locations (BSLs) within the awarded project areas. This architecture provides symmetrical gigabit services (and higher) and is highly scalable to meet future bandwidth demands. Major Infrastructure Components The following major infrastructure elements will be deployed: 1. Fiber-Optic Cable Fiber Strand Counts: Fiber optic cables will vary from 12-count to 288-count configurations based on network topology, population density, and aggregation needs. Fiber Cable Type: Standard single-mode fiber (SMF-28 or equivalent) suitable for long-distance PON deployments and future wavelength-division multiplexing (WDM) upgrades. Placement Strategy: Approximately 75% of fiber will be placed underground in conduit to improve resilience, longevity, and climate protection. Underground conduit sizes will range from 1” to 2” depending on fiber counts and environmental constraints. Aerial Deployment: The remaining 25% of the fiber infrastructure will be deployed aerially on existing utility poles where feasible and cost-effective, utilizing pole attachments under existing Joint Pole Agreements or permits. 2. Conduit and Handholes Conduit Sizing: Conduit will typically be HDPE (High-Density Polyethylene) material in 1” or 2” diameter sizes. Larger conduit sizes or multiple conduits may be used for backbone fiber or in denser service areas to future-proof the network. Handholes: Handholes will be strategically placed to provide access points for splicing, maintenance, and future expansion without major construction disruption. 3. Optical Line Terminals (OLTs) Equipment: Calix AXOS E7-2 and/or E3-2 hardened OLT platforms will be deployed. Location: OLTs will be installed in environmentally hardened outdoor cabinets or in controlled-environment shelters at central locations within each project area. Capacity: Each OLT chassis can serve thousands of end-points with scalable upgrade paths from 10G XGS-PON to higher next-generation standards (e.g., 25G PON). 4. Fiber Distribution Hubs (FDHs) FDHs will be installed strategically throughout the network to allow for the splitting and distribution of optical signals. Splitter Technology: Passive optical splitters (1:32 split ratio) will be used, depending on service density and engineering design. FDHs will be equipped to allow easy field expansion and reconfiguration as service demand grows. 5. Drop Fibers and Network Interface Devices (NIDs) Individual fibers will run from FDHs to customer premises using hardened fiber drop cables. Termination equipment at the customer premises will include optical network terminals (ONTs) capable of delivering gigabit+ services and integrated with Wi-Fi services where applicable. Existing Facilities to Be Leveraged Stimulus Technologies plans to leverage and interconnect with the following existing assets: Existing Backbone Fiber: Where possible, Stimulus will utilize its existing backbone fiber routes or leased dark fiber assets to connect new project areas to core network aggregation points. Data Centers and Colocation Sites: Our primary points of presence (POPs) in Nevada and California — interconnected via long-haul fiber networks — provide upstream IP transit, peering, and routing capabilities. These will support backhaul for the new networks. Core Network Infrastructure: Stimulus operates existing core routers, switches, and transport systems which are scalable and modular to integrate newly built service areas without requiring significant upgrades. Indefeasible Rights of Use (IRUs): Where necessary, Stimulus may execute IRU agreements with regional fiber owners or consortia to obtain long-term, low-cost access to middle-mile and backhaul transport. We intend to use middle-mile infrastructure built by Stimulus in Nevada along the California border and California MMBN to service the network. If IRUs are available for the CA MMBN, Stimulus will attempt negotiations to use dark-fiber for infrastructure, otherwise Stimulus will utilize metro-ethernet circuits for service. Indefeasible Right of Use (IRU) Details At the time of application, Stimulus Technologies is not in discussions to secure IRUs for dark fiber strands that will complement our owned backbone assets in certain rural areas of California. In the event that IRUs are available, these IRUs will typically have terms of 20 years or longer, aligning with the asset life of the fiber network and ensuring stable, long-term backhaul capacity. If IRUs are finalized during the project implementation phase, documentation and agreements will be provided to the California Public Utilities Commission (CPUC) as required. | 75 | The majority of costs for the project will be related to fiber cable material and construction. For portions of the network where fiber is placed on existing or new pole lines, the construction costs and make ready costs from the pole owners will be the larger costs. For underground construction, the cost of trenching or boring and fiber placement within conduits will outweigh the other costs of hand holes/vaults and splicing. OLT infrastructure costs including fiber distribution hubs are another key cost item but are relatively small in comparison to the fiber material and construction costs. | Stimulus has assumed a 24-month duration for completion of the project. Project planning and engineering will be completed within the first 4 months of project commencement. Environmental and highway permitting has been estimated at 5 months and will start once a portion of the detailed engineering is completed. Procurement activities are expected to take six months but will be able to run in parallel with engineering and permitting. The expectation is that by late Q3 2026, construction build activities will commence. Stimulus will break the work down into four phases so that portions of the project area can be completed and released for customers in 3 to 4 month intervals, the first of which would be expected in December 2026. Marketing activities will commence before completion of construction on the first phase of the build to generate service demand within the project area. Subscriber activations will commence at the end of the first construction phase and continue through to the end of the project. Testing and hand off to operations will also commence at the end of the first construction phase and subsequent phases thereafter followed by final reporting and project closure. | Stimulus will be deploying a fully fiber XGS-PON network to service all eligible BSLs within the project area. Customers will be able to subscribe initially to service with symmetrical speeds of 1Gbps with latency less than 100ms and with the ability for speeds to increase over time as customer demand and usage dictate. The scalable nature of the OLT technology to be used will make the upgrade path to higher speeds cost effective for Stimulus when required. The fiber will be placed through a combination of underground and aerial construction methodologies based upon the location and permitting requirements.
a0Kcs00000QMIAcEAP | Stimulus - Inyo 6 | Stimulus Technologies of California, LLC | Inyo | Video Franchise Certificate 0046. Stimulus showed it has sufficient financial and other capabilities to when it obtained its franchise under ? 5840(e)(9) of the Public Utilities Code and should be exempt in the same manner as CPCN holder. | Nathan Whittacre | CEO | 879029.73 | 1098787.16 | 57500 | 13 | 20 | 6 | 1000 | 1000 | 50 | The proposed broadband network will deploy a carrier-grade, XGS-PON (10 Gigabit-capable Passive Optical Network) fiber-to-the-premises (FTTP) system to serve all Broadband Service Locations (BSLs) within the awarded project areas. This architecture provides symmetrical gigabit services (and higher) and is highly scalable to meet future bandwidth demands. Major Infrastructure Components The following major infrastructure elements will be deployed: 1. Fiber-Optic Cable Fiber Strand Counts: Fiber optic cables will vary from 12-count to 288-count configurations based on network topology, population density, and aggregation needs. Fiber Cable Type: Standard single-mode fiber (SMF-28 or equivalent) suitable for long-distance PON deployments and future wavelength-division multiplexing (WDM) upgrades. Placement Strategy: Approximately 75% of fiber will be placed underground in conduit to improve resilience, longevity, and climate protection. Underground conduit sizes will range from 1” to 2” depending on fiber counts and environmental constraints. Aerial Deployment: The remaining 25% of the fiber infrastructure will be deployed aerially on existing utility poles where feasible and cost-effective, utilizing pole attachments under existing Joint Pole Agreements or permits. 2. Conduit and Handholes Conduit Sizing: Conduit will typically be HDPE (High-Density Polyethylene) material in 1” or 2” diameter sizes. Larger conduit sizes or multiple conduits may be used for backbone fiber or in denser service areas to future-proof the network. Handholes: Handholes will be strategically placed to provide access points for splicing, maintenance, and future expansion without major construction disruption. 3. Optical Line Terminals (OLTs) Equipment: Calix AXOS E7-2 and/or E3-2 hardened OLT platforms will be deployed. Location: OLTs will be installed in environmentally hardened outdoor cabinets or in controlled-environment shelters at central locations within each project area. Capacity: Each OLT chassis can serve thousands of end-points with scalable upgrade paths from 10G XGS-PON to higher next-generation standards (e.g., 25G PON). 4. Fiber Distribution Hubs (FDHs) FDHs will be installed strategically throughout the network to allow for the splitting and distribution of optical signals. Splitter Technology: Passive optical splitters (1:32 split ratio) will be used, depending on service density and engineering design. FDHs will be equipped to allow easy field expansion and reconfiguration as service demand grows. 5. Drop Fibers and Network Interface Devices (NIDs) Individual fibers will run from FDHs to customer premises using hardened fiber drop cables. Termination equipment at the customer premises will include optical network terminals (ONTs) capable of delivering gigabit+ services and integrated with Wi-Fi services where applicable. Existing Facilities to Be Leveraged Stimulus Technologies plans to leverage and interconnect with the following existing assets: Existing Backbone Fiber: Where possible, Stimulus will utilize its existing backbone fiber routes or leased dark fiber assets to connect new project areas to core network aggregation points. Data Centers and Colocation Sites: Our primary points of presence (POPs) in Nevada and California — interconnected via long-haul fiber networks — provide upstream IP transit, peering, and routing capabilities. These will support backhaul for the new networks. Core Network Infrastructure: Stimulus operates existing core routers, switches, and transport systems which are scalable and modular to integrate newly built service areas without requiring significant upgrades. Indefeasible Rights of Use (IRUs): Where necessary, Stimulus may execute IRU agreements with regional fiber owners or consortia to obtain long-term, low-cost access to middle-mile and backhaul transport. We intend to use middle-mile infrastructure built by Stimulus in Nevada along the California border and California MMBN to service the network. If IRUs are available for the CA MMBN, Stimulus will attempt negotiations to use dark-fiber for infrastructure, otherwise Stimulus will utilize metro-ethernet circuits for service. Indefeasible Right of Use (IRU) Details At the time of application, Stimulus Technologies is not in discussions to secure IRUs for dark fiber strands that will complement our owned backbone assets in certain rural areas of California. In the event that IRUs are available, these IRUs will typically have terms of 20 years or longer, aligning with the asset life of the fiber network and ensuring stable, long-term backhaul capacity. If IRUs are finalized during the project implementation phase, documentation and agreements will be provided to the California Public Utilities Commission (CPUC) as required. | 75 | The majority of costs for the project will be related to fiber cable material and construction. For portions of the network where fiber is placed on existing or new pole lines, the construction costs and make ready costs from the pole owners will be the larger costs. For underground construction, the cost of trenching or boring and fiber placement within conduits will outweigh the other costs of hand holes/vaults and splicing. OLT infrastructure costs including fiber distribution hubs are another key cost item but are relatively small in comparison to the fiber material and construction costs. | Stimulus has assumed a 24-month duration for completion of the project. Project planning and engineering will be completed within the first 4 months of project commencement. Environmental and highway permitting has been estimated at 5 months and will start once a portion of the detailed engineering is completed. Procurement activities are expected to take six months but will be able to run in parallel with engineering and permitting. The expectation is that by late Q3 2026, construction build activities will commence. Stimulus will break the work down into four phases so that portions of the project area can be completed and released for customers in 3 to 4 month intervals, the first of which would be expected in December 2026. Marketing activities will commence before completion of construction on the first phase of the build to generate service demand within the project area. Subscriber activations will commence at the end of the first construction phase and continue through to the end of the project. Testing and hand off to operations will also commence at the end of the first construction phase and subsequent phases thereafter followed by final reporting and project closure. | Stimulus will be deploying a fully fiber XGS-PON network to service all eligible BSLs within the project area. Customers will be able to subscribe initially to service with symmetrical speeds of 1Gbps with latency less than 100ms and with the ability for speeds to increase over time as customer demand and usage dictate. The scalable nature of the OLT technology to be used will make the upgrade path to higher speeds cost effective for Stimulus when required. The fiber will be placed through a combination of underground and aerial construction methodologies based upon the location and permitting requirements.
a0Kcs00000QMb8PEAT | Stimulus - Inyo 7 | Stimulus Technologies of California, LLC | Inyo | Video Franchise Certificate 0046. Stimulus showed it has sufficient financial and other capabilities to when it obtained its franchise under ? 5840(e)(9) of the Public Utilities Code and should be exempt in the same manner as CPCN holder. | Nathan Whittacre | CEO | 1914154.27 | 2392692.84 | 54107 | 44 | 14 | 2 | 1000 | 1000 | 183 | The proposed broadband network will deploy a carrier-grade, XGS-PON (10 Gigabit-capable Passive Optical Network) fiber-to-the-premises (FTTP) system to serve all Broadband Service Locations (BSLs) within the awarded project areas. This architecture provides symmetrical gigabit services (and higher) and is highly scalable to meet future bandwidth demands. Major Infrastructure Components The following major infrastructure elements will be deployed: 1. Fiber-Optic Cable Fiber Strand Counts: Fiber optic cables will vary from 12-count to 288-count configurations based on network topology, population density, and aggregation needs. Fiber Cable Type: Standard single-mode fiber (SMF-28 or equivalent) suitable for long-distance PON deployments and future wavelength-division multiplexing (WDM) upgrades. Placement Strategy: Approximately 75% of fiber will be placed underground in conduit to improve resilience, longevity, and climate protection. Underground conduit sizes will range from 1” to 2” depending on fiber counts and environmental constraints. Aerial Deployment: The remaining 25% of the fiber infrastructure will be deployed aerially on existing utility poles where feasible and cost-effective, utilizing pole attachments under existing Joint Pole Agreements or permits. 2. Conduit and Handholes Conduit Sizing: Conduit will typically be HDPE (High-Density Polyethylene) material in 1” or 2” diameter sizes. Larger conduit sizes or multiple conduits may be used for backbone fiber or in denser service areas to future-proof the network. Handholes: Handholes will be strategically placed to provide access points for splicing, maintenance, and future expansion without major construction disruption. 3. Optical Line Terminals (OLTs) Equipment: Calix AXOS E7-2 and/or E3-2 hardened OLT platforms will be deployed. Location: OLTs will be installed in environmentally hardened outdoor cabinets or in controlled-environment shelters at central locations within each project area. Capacity: Each OLT chassis can serve thousands of end-points with scalable upgrade paths from 10G XGS-PON to higher next-generation standards (e.g., 25G PON). 4. Fiber Distribution Hubs (FDHs) FDHs will be installed strategically throughout the network to allow for the splitting and distribution of optical signals. Splitter Technology: Passive optical splitters (1:32 split ratio) will be used, depending on service density and engineering design. FDHs will be equipped to allow easy field expansion and reconfiguration as service demand grows. 5. Drop Fibers and Network Interface Devices (NIDs) Individual fibers will run from FDHs to customer premises using hardened fiber drop cables. Termination equipment at the customer premises will include optical network terminals (ONTs) capable of delivering gigabit+ services and integrated with Wi-Fi services where applicable. Existing Facilities to Be Leveraged Stimulus Technologies plans to leverage and interconnect with the following existing assets: Existing Backbone Fiber: Where possible, Stimulus will utilize its existing backbone fiber routes or leased dark fiber assets to connect new project areas to core network aggregation points. Data Centers and Colocation Sites: Our primary points of presence (POPs) in Nevada and California — interconnected via long-haul fiber networks — provide upstream IP transit, peering, and routing capabilities. These will support backhaul for the new networks. Core Network Infrastructure: Stimulus operates existing core routers, switches, and transport systems which are scalable and modular to integrate newly built service areas without requiring significant upgrades. Indefeasible Rights of Use (IRUs): Where necessary, Stimulus may execute IRU agreements with regional fiber owners or consortia to obtain long-term, low-cost access to middle-mile and backhaul transport. We intend to use middle-mile infrastructure built by Stimulus in Nevada along the California border and California MMBN to service the network. If IRUs are available for the CA MMBN, Stimulus will attempt negotiations to use dark-fiber for infrastructure, otherwise Stimulus will utilize metro-ethernet circuits for service. Indefeasible Right of Use (IRU) Details At the time of application, Stimulus Technologies is not in discussions to secure IRUs for dark fiber strands that will complement our owned backbone assets in certain rural areas of California. In the event that IRUs are available, these IRUs will typically have terms of 20 years or longer, aligning with the asset life of the fiber network and ensuring stable, long-term backhaul capacity. If IRUs are finalized during the project implementation phase, documentation and agreements will be provided to the California Public Utilities Commission (CPUC) as required. | 75 | The majority of costs for the project will be related to fiber cable material and construction. For portions of the network where fiber is placed on existing or new pole lines, the construction costs and make ready costs from the pole owners will be the larger costs. For underground construction, the cost of trenching or boring and fiber placement within conduits will outweigh the other costs of hand holes/vaults and splicing. OLT infrastructure costs including fiber distribution hubs are another key cost item but are relatively small in comparison to the fiber material and construction costs. | Stimulus has assumed a 24-month duration for completion of the project. Project planning and engineering will be completed within the first 4 months of project commencement. Environmental and highway permitting has been estimated at 5 months and will start once a portion of the detailed engineering is completed. Procurement activities are expected to take six months but will be able to run in parallel with engineering and permitting. The expectation is that by late Q3 2026, construction build activities will commence. Stimulus will break the work down into four phases so that portions of the project area can be completed and released for customers in 3 to 4 month intervals, the first of which would be expected in December 2026. Marketing activities will commence before completion of construction on the first phase of the build to generate service demand within the project area. Subscriber activations will commence at the end of the first construction phase and continue through to the end of the project. Testing and hand off to operations will also commence at the end of the first construction phase and subsequent phases thereafter followed by final reporting and project closure. | Stimulus will be deploying a fully fiber XGS-PON network to service all eligible BSLs within the project area. Customers will be able to subscribe initially to service with symmetrical speeds of 1Gbps with latency less than 100ms and with the ability for speeds to increase over time as customer demand and usage dictate. The scalable nature of the OLT technology to be used will make the upgrade path to higher speeds cost effective for Stimulus when required. The fiber will be placed through a combination of underground and aerial construction methodologies based upon the location and permitting requirements.
a0Kcs00000QMbWbEAL | Stimulus - Inyo 8 | Stimulus Technologies of California, LLC | Inyo | Video Franchise Certificate 0046. Stimulus showed it has sufficient financial and other capabilities to when it obtained its franchise under ? 5840(e)(9) of the Public Utilities Code and should be exempt in the same manner as CPCN holder. | Nathan Whittacre | CEO | 8799098.96 | 12570141.37 | 51949 | 186 | 16 | 11 | 1000 | 1000 | 790 | The proposed broadband network will deploy a carrier-grade, XGS-PON (10 Gigabit-capable Passive Optical Network) fiber-to-the-premises (FTTP) system to serve all Broadband Service Locations (BSLs) within the awarded project areas. This architecture provides symmetrical gigabit services (and higher) and is highly scalable to meet future bandwidth demands. Major Infrastructure Components The following major infrastructure elements will be deployed: 1. Fiber-Optic Cable Fiber Strand Counts: Fiber optic cables will vary from 12-count to 288-count configurations based on network topology, population density, and aggregation needs. Fiber Cable Type: Standard single-mode fiber (SMF-28 or equivalent) suitable for long-distance PON deployments and future wavelength-division multiplexing (WDM) upgrades. Placement Strategy: Approximately 75% of fiber will be placed underground in conduit to improve resilience, longevity, and climate protection. Underground conduit sizes will range from 1” to 2” depending on fiber counts and environmental constraints. Aerial Deployment: The remaining 25% of the fiber infrastructure will be deployed aerially on existing utility poles where feasible and cost-effective, utilizing pole attachments under existing Joint Pole Agreements or permits. 2. Conduit and Handholes Conduit Sizing: Conduit will typically be HDPE (High-Density Polyethylene) material in 1” or 2” diameter sizes. Larger conduit sizes or multiple conduits may be used for backbone fiber or in denser service areas to future-proof the network. Handholes: Handholes will be strategically placed to provide access points for splicing, maintenance, and future expansion without major construction disruption. 3. Optical Line Terminals (OLTs) Equipment: Calix AXOS E7-2 and/or E3-2 hardened OLT platforms will be deployed. Location: OLTs will be installed in environmentally hardened outdoor cabinets or in controlled-environment shelters at central locations within each project area. Capacity: Each OLT chassis can serve thousands of end-points with scalable upgrade paths from 10G XGS-PON to higher next-generation standards (e.g., 25G PON). 4. Fiber Distribution Hubs (FDHs) FDHs will be installed strategically throughout the network to allow for the splitting and distribution of optical signals. Splitter Technology: Passive optical splitters (1:32 split ratio) will be used, depending on service density and engineering design. FDHs will be equipped to allow easy field expansion and reconfiguration as service demand grows. 5. Drop Fibers and Network Interface Devices (NIDs) Individual fibers will run from FDHs to customer premises using hardened fiber drop cables. Termination equipment at the customer premises will include optical network terminals (ONTs) capable of delivering gigabit+ services and integrated with Wi-Fi services where applicable. Existing Facilities to Be Leveraged Stimulus Technologies plans to leverage and interconnect with the following existing assets: Existing Backbone Fiber: Where possible, Stimulus will utilize its existing backbone fiber routes or leased dark fiber assets to connect new project areas to core network aggregation points. Data Centers and Colocation Sites: Our primary points of presence (POPs) in Nevada and California — interconnected via long-haul fiber networks — provide upstream IP transit, peering, and routing capabilities. These will support backhaul for the new networks. Core Network Infrastructure: Stimulus operates existing core routers, switches, and transport systems which are scalable and modular to integrate newly built service areas without requiring significant upgrades. Indefeasible Rights of Use (IRUs): Where necessary, Stimulus may execute IRU agreements with regional fiber owners or consortia to obtain long-term, low-cost access to middle-mile and backhaul transport. We intend to use middle-mile infrastructure built by Stimulus in Nevada along the California border and California MMBN to service the network. If IRUs are available for the CA MMBN, Stimulus will attempt negotiations to use dark-fiber for infrastructure, otherwise Stimulus will utilize metro-ethernet circuits for service. Indefeasible Right of Use (IRU) Details At the time of application, Stimulus Technologies is not in discussions to secure IRUs for dark fiber strands that will complement our owned backbone assets in certain rural areas of California. In the event that IRUs are available, these IRUs will typically have terms of 20 years or longer, aligning with the asset life of the fiber network and ensuring stable, long-term backhaul capacity. If IRUs are finalized during the project implementation phase, documentation and agreements will be provided to the California Public Utilities Commission (CPUC) as required. | 75 | The majority of costs for the project will be related to fiber cable material and construction. For portions of the network where fiber is placed on existing or new pole lines, the construction costs and make ready costs from the pole owners will be the larger costs. For underground construction, the cost of trenching or boring and fiber placement within conduits will outweigh the other costs of hand holes/vaults and splicing. OLT infrastructure costs including fiber distribution hubs are another key cost item but are relatively small in comparison to the fiber material and construction costs. | Stimulus has assumed a 24-month duration for completion of the project. Project planning and engineering will be completed within the first 4 months of project commencement. Environmental and highway permitting has been estimated at 5 months and will start once a portion of the detailed engineering is completed. Procurement activities are expected to take six months but will be able to run in parallel with engineering and permitting. The expectation is that by late Q3 2026, construction build activities will commence. Stimulus will break the work down into four phases so that portions of the project area can be completed and released for customers in 3 to 4 month intervals, the first of which would be expected in December 2026. Marketing activities will commence before completion of construction on the first phase of the build to generate service demand within the project area. Subscriber activations will commence at the end of the first construction phase and continue through to the end of the project. Testing and hand off to operations will also commence at the end of the first construction phase and subsequent phases thereafter followed by final reporting and project closure. | Stimulus will be deploying a fully fiber XGS-PON network to service all eligible BSLs within the project area. Customers will be able to subscribe initially to service with symmetrical speeds of 1Gbps with latency less than 100ms and with the ability for speeds to increase over time as customer demand and usage dictate. The scalable nature of the OLT technology to be used will make the upgrade path to higher speeds cost effective for Stimulus when required. The fiber will be placed through a combination of underground and aerial construction methodologies based upon the location and permitting requirements.
a0Kcs00000QMbrZEAT | Stimulus - Trinity 1 | Stimulus Technologies of California, LLC | Trinity | Video Franchise Certificate 0046. Stimulus showed it has sufficient financial and other capabilities to when it obtained its franchise under ? 5840(e)(9) of the Public Utilities Code and should be exempt in the same manner as CPCN holder. | Nathan Whittacre | CEO | 10756452.65 | 11951614.05 | 38750 | 52 | 2 | 2 | 1000 | 1000 | 558 | The proposed broadband network will deploy a carrier-grade, XGS-PON (10 Gigabit-capable Passive Optical Network) fiber-to-the-premises (FTTP) system to serve all Broadband Service Locations (BSLs) within the awarded project areas. This architecture provides symmetrical gigabit services (and higher) and is highly scalable to meet future bandwidth demands. Major Infrastructure Components The following major infrastructure elements will be deployed: 1. Fiber-Optic Cable Fiber Strand Counts: Fiber optic cables will vary from 12-count to 288-count configurations based on network topology, population density, and aggregation needs. Fiber Cable Type: Standard single-mode fiber (SMF-28 or equivalent) suitable for long-distance PON deployments and future wavelength-division multiplexing (WDM) upgrades. Placement Strategy: Approximately 75% of fiber will be placed underground in conduit to improve resilience, longevity, and climate protection. Underground conduit sizes will range from 1” to 2” depending on fiber counts and environmental constraints. Aerial Deployment: The remaining 25% of the fiber infrastructure will be deployed aerially on existing utility poles where feasible and cost-effective, utilizing pole attachments under existing Joint Pole Agreements or permits. 2. Conduit and Handholes Conduit Sizing: Conduit will typically be HDPE (High-Density Polyethylene) material in 1” or 2” diameter sizes. Larger conduit sizes or multiple conduits may be used for backbone fiber or in denser service areas to future-proof the network. Handholes: Handholes will be strategically placed to provide access points for splicing, maintenance, and future expansion without major construction disruption. 3. Optical Line Terminals (OLTs) Equipment: Calix AXOS E7-2 and/or E3-2 hardened OLT platforms will be deployed. Location: OLTs will be installed in environmentally hardened outdoor cabinets or in controlled-environment shelters at central locations within each project area. Capacity: Each OLT chassis can serve thousands of end-points with scalable upgrade paths from 10G XGS-PON to higher next-generation standards (e.g., 25G PON). 4. Fiber Distribution Hubs (FDHs) FDHs will be installed strategically throughout the network to allow for the splitting and distribution of optical signals. Splitter Technology: Passive optical splitters (1:32 split ratio) will be used, depending on service density and engineering design. FDHs will be equipped to allow easy field expansion and reconfiguration as service demand grows. 5. Drop Fibers and Network Interface Devices (NIDs) Individual fibers will run from FDHs to customer premises using hardened fiber drop cables. Termination equipment at the customer premises will include optical network terminals (ONTs) capable of delivering gigabit+ services and integrated with Wi-Fi services where applicable. Existing Facilities to Be Leveraged Stimulus Technologies plans to leverage and interconnect with the following existing assets: Existing Backbone Fiber: Where possible, Stimulus will utilize its existing backbone fiber routes or leased dark fiber assets to connect new project areas to core network aggregation points. Data Centers and Colocation Sites: Our primary points of presence (POPs) in Nevada and California — interconnected via long-haul fiber networks — provide upstream IP transit, peering, and routing capabilities. These will support backhaul for the new networks. Core Network Infrastructure: Stimulus operates existing core routers, switches, and transport systems which are scalable and modular to integrate newly built service areas without requiring significant upgrades. Indefeasible Rights of Use (IRUs): Where necessary, Stimulus may execute IRU agreements with regional fiber owners or consortia to obtain long-term, low-cost access to middle-mile and backhaul transport. We intend to use middle-mile infrastructure built by Stimulus in Nevada along the California border and California MMBN to service the network. If IRUs are available for the CA MMBN, Stimulus will attempt negotiations to use dark-fiber for infrastructure, otherwise Stimulus will utilize metro-ethernet circuits for service. Indefeasible Right of Use (IRU) Details At the time of application, Stimulus Technologies is not in discussions to secure IRUs for dark fiber strands that will complement our owned backbone assets in certain rural areas of California. In the event that IRUs are available, these IRUs will typically have terms of 20 years or longer, aligning with the asset life of the fiber network and ensuring stable, long-term backhaul capacity. If IRUs are finalized during the project implementation phase, documentation and agreements will be provided to the California Public Utilities Commission (CPUC) as required. | 75 | The majority of costs for the project will be related to fiber cable material and construction. For portions of the network where fiber is placed on existing or new pole lines, the construction costs and make ready costs from the pole owners will be the larger costs. For underground construction, the cost of trenching or boring and fiber placement within conduits will outweigh the other costs of hand holes/vaults and splicing. OLT infrastructure costs including fiber distribution hubs are another key cost item but are relatively small in comparison to the fiber material and construction costs. | Stimulus has assumed a 24-month duration for completion of the project. Project planning and engineering will be completed within the first 4 months of project commencement. Environmental and highway permitting has been estimated at 5 months and will start once a portion of the detailed engineering is completed. Procurement activities are expected to take six months but will be able to run in parallel with engineering and permitting. The expectation is that by late Q3 2026, construction build activities will commence. Stimulus will break the work down into four phases so that portions of the project area can be completed and released for customers in 3 to 4 month intervals, the first of which would be expected in December 2026. Marketing activities will commence before completion of construction on the first phase of the build to generate service demand within the project area. Subscriber activations will commence at the end of the first construction phase and continue through to the end of the project. Testing and hand off to operations will also commence at the end of the first construction phase and subsequent phases thereafter followed by final reporting and project closure. | Stimulus will be deploying a fully fiber XGS-PON network to service all eligible BSLs within the project area. Customers will be able to subscribe initially to service with symmetrical speeds of 1Gbps with latency less than 100ms and with the ability for speeds to increase over time as customer demand and usage dictate. The scalable nature of the OLT technology to be used will make the upgrade path to higher speeds cost effective for Stimulus when required. The fiber will be placed through a combination of underground and aerial construction methodologies based upon the location and permitting requirements.
a0Kcs00000QMcE9EAL | Stimulus - Trinity 2 | Stimulus Technologies of California, LLC | Trinity | Video Franchise Certificate 0046. Stimulus showed it has sufficient financial and other capabilities to when it obtained its franchise under ? 5840(e)(9) of the Public Utilities Code and should be exempt in the same manner as CPCN holder. | Nathan Whittacre | CEO | 5838870.71 | 6146179.69 | 50486 | 11 | 2 | 0 | 1000 | 1000 | 151 | The proposed broadband network will deploy a carrier-grade, XGS-PON (10 Gigabit-capable Passive Optical Network) fiber-to-the-premises (FTTP) system to serve all Broadband Service Locations (BSLs) within the awarded project areas. This architecture provides symmetrical gigabit services (and higher) and is highly scalable to meet future bandwidth demands. Major Infrastructure Components The following major infrastructure elements will be deployed: 1. Fiber-Optic Cable Fiber Strand Counts: Fiber optic cables will vary from 12-count to 288-count configurations based on network topology, population density, and aggregation needs. Fiber Cable Type: Standard single-mode fiber (SMF-28 or equivalent) suitable for long-distance PON deployments and future wavelength-division multiplexing (WDM) upgrades. Placement Strategy: Approximately 75% of fiber will be placed underground in conduit to improve resilience, longevity, and climate protection. Underground conduit sizes will range from 1” to 2” depending on fiber counts and environmental constraints. Aerial Deployment: The remaining 25% of the fiber infrastructure will be deployed aerially on existing utility poles where feasible and cost-effective, utilizing pole attachments under existing Joint Pole Agreements or permits. 2. Conduit and Handholes Conduit Sizing: Conduit will typically be HDPE (High-Density Polyethylene) material in 1” or 2” diameter sizes. Larger conduit sizes or multiple conduits may be used for backbone fiber or in denser service areas to future-proof the network. Handholes: Handholes will be strategically placed to provide access points for splicing, maintenance, and future expansion without major construction disruption. 3. Optical Line Terminals (OLTs) Equipment: Calix AXOS E7-2 and/or E3-2 hardened OLT platforms will be deployed. Location: OLTs will be installed in environmentally hardened outdoor cabinets or in controlled-environment shelters at central locations within each project area. Capacity: Each OLT chassis can serve thousands of end-points with scalable upgrade paths from 10G XGS-PON to higher next-generation standards (e.g., 25G PON). 4. Fiber Distribution Hubs (FDHs) FDHs will be installed strategically throughout the network to allow for the splitting and distribution of optical signals. Splitter Technology: Passive optical splitters (1:32 split ratio) will be used, depending on service density and engineering design. FDHs will be equipped to allow easy field expansion and reconfiguration as service demand grows. 5. Drop Fibers and Network Interface Devices (NIDs) Individual fibers will run from FDHs to customer premises using hardened fiber drop cables. Termination equipment at the customer premises will include optical network terminals (ONTs) capable of delivering gigabit+ services and integrated with Wi-Fi services where applicable. Existing Facilities to Be Leveraged Stimulus Technologies plans to leverage and interconnect with the following existing assets: Existing Backbone Fiber: Where possible, Stimulus will utilize its existing backbone fiber routes or leased dark fiber assets to connect new project areas to core network aggregation points. Data Centers and Colocation Sites: Our primary points of presence (POPs) in Nevada and California — interconnected via long-haul fiber networks — provide upstream IP transit, peering, and routing capabilities. These will support backhaul for the new networks. Core Network Infrastructure: Stimulus operates existing core routers, switches, and transport systems which are scalable and modular to integrate newly built service areas without requiring significant upgrades. Indefeasible Rights of Use (IRUs): Where necessary, Stimulus may execute IRU agreements with regional fiber owners or consortia to obtain long-term, low-cost access to middle-mile and backhaul transport. We intend to use middle-mile infrastructure built by Stimulus in Nevada along the California border and California MMBN to service the network. If IRUs are available for the CA MMBN, Stimulus will attempt negotiations to use dark-fiber for infrastructure, otherwise Stimulus will utilize metro-ethernet circuits for service. Indefeasible Right of Use (IRU) Details At the time of application, Stimulus Technologies is not in discussions to secure IRUs for dark fiber strands that will complement our owned backbone assets in certain rural areas of California. In the event that IRUs are available, these IRUs will typically have terms of 20 years or longer, aligning with the asset life of the fiber network and ensuring stable, long-term backhaul capacity. If IRUs are finalized during the project implementation phase, documentation and agreements will be provided to the California Public Utilities Commission (CPUC) as required. | 75 | The majority of costs for the project will be related to fiber cable material and construction. For portions of the network where fiber is placed on existing or new pole lines, the construction costs and make ready costs from the pole owners will be the larger costs. For underground construction, the cost of trenching or boring and fiber placement within conduits will outweigh the other costs of hand holes/vaults and splicing. OLT infrastructure costs including fiber distribution hubs are another key cost item but are relatively small in comparison to the fiber material and construction costs. | Stimulus has assumed a 24-month duration for completion of the project. Project planning and engineering will be completed within the first 4 months of project commencement. Environmental and highway permitting has been estimated at 5 months and will start once a portion of the detailed engineering is completed. Procurement activities are expected to take six months but will be able to run in parallel with engineering and permitting. The expectation is that by late Q3 2026, construction build activities will commence. Stimulus will break the work down into four phases so that portions of the project area can be completed and released for customers in 3 to 4 month intervals, the first of which would be expected in December 2026. Marketing activities will commence before completion of construction on the first phase of the build to generate service demand within the project area. Subscriber activations will commence at the end of the first construction phase and continue through to the end of the project. Testing and hand off to operations will also commence at the end of the first construction phase and subsequent phases thereafter followed by final reporting and project closure. | Stimulus will be deploying a fully fiber XGS-PON network to service all eligible BSLs within the project area. Customers will be able to subscribe initially to service with symmetrical speeds of 1Gbps with latency less than 100ms and with the ability for speeds to increase over time as customer demand and usage dictate. The scalable nature of the OLT technology to be used will make the upgrade path to higher speeds cost effective for Stimulus when required. The fiber will be placed through a combination of underground and aerial construction methodologies based upon the location and permitting requirements.
a0Kcs00000QMcfZEAT | Stimulus - Trinity 3 | Stimulus Technologies of California, LLC | Trinity | Video Franchise Certificate 0046. Stimulus showed it has sufficient financial and other capabilities to when it obtained its franchise under ? 5840(e)(9) of the Public Utilities Code and should be exempt in the same manner as CPCN holder. | Nathan Whittacre | CEO | 11991270.99 | 12622390.52 | 50486 | 27 | 6 | 2 | 1000 | 1000 | 372 | The proposed broadband network will deploy a carrier-grade, XGS-PON (10 Gigabit-capable Passive Optical Network) fiber-to-the-premises (FTTP) system to serve all Broadband Service Locations (BSLs) within the awarded project areas. This architecture provides symmetrical gigabit services (and higher) and is highly scalable to meet future bandwidth demands. Major Infrastructure Components The following major infrastructure elements will be deployed: 1. Fiber-Optic Cable Fiber Strand Counts: Fiber optic cables will vary from 12-count to 288-count configurations based on network topology, population density, and aggregation needs. Fiber Cable Type: Standard single-mode fiber (SMF-28 or equivalent) suitable for long-distance PON deployments and future wavelength-division multiplexing (WDM) upgrades. Placement Strategy: Approximately 75% of fiber will be placed underground in conduit to improve resilience, longevity, and climate protection. Underground conduit sizes will range from 1” to 2” depending on fiber counts and environmental constraints. Aerial Deployment: The remaining 25% of the fiber infrastructure will be deployed aerially on existing utility poles where feasible and cost-effective, utilizing pole attachments under existing Joint Pole Agreements or permits. 2. Conduit and Handholes Conduit Sizing: Conduit will typically be HDPE (High-Density Polyethylene) material in 1” or 2” diameter sizes. Larger conduit sizes or multiple conduits may be used for backbone fiber or in denser service areas to future-proof the network. Handholes: Handholes will be strategically placed to provide access points for splicing, maintenance, and future expansion without major construction disruption. 3. Optical Line Terminals (OLTs) Equipment: Calix AXOS E7-2 and/or E3-2 hardened OLT platforms will be deployed. Location: OLTs will be installed in environmentally hardened outdoor cabinets or in controlled-environment shelters at central locations within each project area. Capacity: Each OLT chassis can serve thousands of end-points with scalable upgrade paths from 10G XGS-PON to higher next-generation standards (e.g., 25G PON). 4. Fiber Distribution Hubs (FDHs) FDHs will be installed strategically throughout the network to allow for the splitting and distribution of optical signals. Splitter Technology: Passive optical splitters (1:32 split ratio) will be used, depending on service density and engineering design. FDHs will be equipped to allow easy field expansion and reconfiguration as service demand grows. 5. Drop Fibers and Network Interface Devices (NIDs) Individual fibers will run from FDHs to customer premises using hardened fiber drop cables. Termination equipment at the customer premises will include optical network terminals (ONTs) capable of delivering gigabit+ services and integrated with Wi-Fi services where applicable. Existing Facilities to Be Leveraged Stimulus Technologies plans to leverage and interconnect with the following existing assets: Existing Backbone Fiber: Where possible, Stimulus will utilize its existing backbone fiber routes or leased dark fiber assets to connect new project areas to core network aggregation points. Data Centers and Colocation Sites: Our primary points of presence (POPs) in Nevada and California — interconnected via long-haul fiber networks — provide upstream IP transit, peering, and routing capabilities. These will support backhaul for the new networks. Core Network Infrastructure: Stimulus operates existing core routers, switches, and transport systems which are scalable and modular to integrate newly built service areas without requiring significant upgrades. Indefeasible Rights of Use (IRUs): Where necessary, Stimulus may execute IRU agreements with regional fiber owners or consortia to obtain long-term, low-cost access to middle-mile and backhaul transport. We intend to use middle-mile infrastructure built by Stimulus in Nevada along the California border and California MMBN to service the network. If IRUs are available for the CA MMBN, Stimulus will attempt negotiations to use dark-fiber for infrastructure, otherwise Stimulus will utilize metro-ethernet circuits for service. Indefeasible Right of Use (IRU) Details At the time of application, Stimulus Technologies is not in discussions to secure IRUs for dark fiber strands that will complement our owned backbone assets in certain rural areas of California. In the event that IRUs are available, these IRUs will typically have terms of 20 years or longer, aligning with the asset life of the fiber network and ensuring stable, long-term backhaul capacity. If IRUs are finalized during the project implementation phase, documentation and agreements will be provided to the California Public Utilities Commission (CPUC) as required. | 75 | The majority of costs for the project will be related to fiber cable material and construction. For portions of the network where fiber is placed on existing or new pole lines, the construction costs and make ready costs from the pole owners will be the larger costs. For underground construction, the cost of trenching or boring and fiber placement within conduits will outweigh the other costs of hand holes/vaults and splicing. OLT infrastructure costs including fiber distribution hubs are another key cost item but are relatively small in comparison to the fiber material and construction costs. | Stimulus has assumed a 24-month duration for completion of the project. Project planning and engineering will be completed within the first 4 months of project commencement. Environmental and highway permitting has been estimated at 5 months and will start once a portion of the detailed engineering is completed. Procurement activities are expected to take six months but will be able to run in parallel with engineering and permitting. The expectation is that by late Q3 2026, construction build activities will commence. Stimulus will break the work down into four phases so that portions of the project area can be completed and released for customers in 3 to 4 month intervals, the first of which would be expected in December 2026. Marketing activities will commence before completion of construction on the first phase of the build to generate service demand within the project area. Subscriber activations will commence at the end of the first construction phase and continue through to the end of the project. Testing and hand off to operations will also commence at the end of the first construction phase and subsequent phases thereafter followed by final reporting and project closure. | Stimulus will be deploying a fully fiber XGS-PON network to service all eligible BSLs within the project area. Customers will be able to subscribe initially to service with symmetrical speeds of 1Gbps with latency less than 100ms and with the ability for speeds to increase over time as customer demand and usage dictate. The scalable nature of the OLT technology to be used will make the upgrade path to higher speeds cost effective for Stimulus when required. The fiber will be placed through a combination of underground and aerial construction methodologies based upon the location and permitting requirements.
a0Kcs00000QMGwoEAH | Stimulus - Trinity 4 | Stimulus Technologies of California, LLC | Trinity | Video Franchise Certificate 0046. Stimulus showed it has sufficient financial and other capabilities to when it obtained its franchise under ? 5840(e)(9) of the Public Utilities Code and should be exempt in the same manner as CPCN holder. | Nathan Whittacre | CEO | 5104615.72 | 6380769.65 | 50486 | 11 | 0 | 2 | 1000 | 1000 | 117 | The proposed broadband network will deploy a carrier-grade, XGS-PON (10 Gigabit-capable Passive Optical Network) fiber-to-the-premises (FTTP) system to serve all Broadband Service Locations (BSLs) within the awarded project areas. This architecture provides symmetrical gigabit services (and higher) and is highly scalable to meet future bandwidth demands. Major Infrastructure Components The following major infrastructure elements will be deployed: 1. Fiber-Optic Cable Fiber Strand Counts: Fiber optic cables will vary from 12-count to 288-count configurations based on network topology, population density, and aggregation needs. Fiber Cable Type: Standard single-mode fiber (SMF-28 or equivalent) suitable for long-distance PON deployments and future wavelength-division multiplexing (WDM) upgrades. Placement Strategy: Approximately 75% of fiber will be placed underground in conduit to improve resilience, longevity, and climate protection. Underground conduit sizes will range from 1” to 2” depending on fiber counts and environmental constraints. Aerial Deployment: The remaining 25% of the fiber infrastructure will be deployed aerially on existing utility poles where feasible and cost-effective, utilizing pole attachments under existing Joint Pole Agreements or permits. 2. Conduit and Handholes Conduit Sizing: Conduit will typically be HDPE (High-Density Polyethylene) material in 1” or 2” diameter sizes. Larger conduit sizes or multiple conduits may be used for backbone fiber or in denser service areas to future-proof the network. Handholes: Handholes will be strategically placed to provide access points for splicing, maintenance, and future expansion without major construction disruption. 3. Optical Line Terminals (OLTs) Equipment: Calix AXOS E7-2 and/or E3-2 hardened OLT platforms will be deployed. Location: OLTs will be installed in environmentally hardened outdoor cabinets or in controlled-environment shelters at central locations within each project area. Capacity: Each OLT chassis can serve thousands of end-points with scalable upgrade paths from 10G XGS-PON to higher next-generation standards (e.g., 25G PON). 4. Fiber Distribution Hubs (FDHs) FDHs will be installed strategically throughout the network to allow for the splitting and distribution of optical signals. Splitter Technology: Passive optical splitters (1:32 split ratio) will be used, depending on service density and engineering design. FDHs will be equipped to allow easy field expansion and reconfiguration as service demand grows. 5. Drop Fibers and Network Interface Devices (NIDs) Individual fibers will run from FDHs to customer premises using hardened fiber drop cables. Termination equipment at the customer premises will include optical network terminals (ONTs) capable of delivering gigabit+ services and integrated with Wi-Fi services where applicable. Existing Facilities to Be Leveraged Stimulus Technologies plans to leverage and interconnect with the following existing assets: Existing Backbone Fiber: Where possible, Stimulus will utilize its existing backbone fiber routes or leased dark fiber assets to connect new project areas to core network aggregation points. Data Centers and Colocation Sites: Our primary points of presence (POPs) in Nevada and California — interconnected via long-haul fiber networks — provide upstream IP transit, peering, and routing capabilities. These will support backhaul for the new networks. Core Network Infrastructure: Stimulus operates existing core routers, switches, and transport systems which are scalable and modular to integrate newly built service areas without requiring significant upgrades. Indefeasible Rights of Use (IRUs): Where necessary, Stimulus may execute IRU agreements with regional fiber owners or consortia to obtain long-term, low-cost access to middle-mile and backhaul transport. We intend to use middle-mile infrastructure built by Stimulus in Nevada along the California border and California MMBN to service the network. If IRUs are available for the CA MMBN, Stimulus will attempt negotiations to use dark-fiber for infrastructure, otherwise Stimulus will utilize metro-ethernet circuits for service. Indefeasible Right of Use (IRU) Details At the time of application, Stimulus Technologies is not in discussions to secure IRUs for dark fiber strands that will complement our owned backbone assets in certain rural areas of California. In the event that IRUs are available, these IRUs will typically have terms of 20 years or longer, aligning with the asset life of the fiber network and ensuring stable, long-term backhaul capacity. If IRUs are finalized during the project implementation phase, documentation and agreements will be provided to the California Public Utilities Commission (CPUC) as required. | 75 | The majority of costs for the project will be related to fiber cable material and construction. For portions of the network where fiber is placed on existing or new pole lines, the construction costs and make ready costs from the pole owners will be the larger costs. For underground construction, the cost of trenching or boring and fiber placement within conduits will outweigh the other costs of hand holes/vaults and splicing. OLT infrastructure costs including fiber distribution hubs are another key cost item but are relatively small in comparison to the fiber material and construction costs. | Stimulus has assumed a 24-month duration for completion of the project. Project planning and engineering will be completed within the first 4 months of project commencement. Environmental and highway permitting has been estimated at 5 months and will start once a portion of the detailed engineering is completed. Procurement activities are expected to take six months but will be able to run in parallel with engineering and permitting. The expectation is that by late Q3 2026, construction build activities will commence. Stimulus will break the work down into four phases so that portions of the project area can be completed and released for customers in 3 to 4 month intervals, the first of which would be expected in December 2026. Marketing activities will commence before completion of construction on the first phase of the build to generate service demand within the project area. Subscriber activations will commence at the end of the first construction phase and continue through to the end of the project. Testing and hand off to operations will also commence at the end of the first construction phase and subsequent phases thereafter followed by final reporting and project closure. | Stimulus will be deploying a fully fiber XGS-PON network to service all eligible BSLs within the project area. Customers will be able to subscribe initially to service with symmetrical speeds of 1Gbps with latency less than 100ms and with the ability for speeds to increase over time as customer demand and usage dictate. The scalable nature of the OLT technology to be used will make the upgrade path to higher speeds cost effective for Stimulus when required. The fiber will be placed through a combination of underground and aerial construction methodologies based upon the location and permitting requirements.
a0Kcs00000QMbd4EAD | Stimulus - Trinity 5 | Stimulus Technologies of California, LLC | Trinity | Video Franchise Certificate 0046. Stimulus showed it has sufficient financial and other capabilities to when it obtained its franchise under ? 5840(e)(9) of the Public Utilities Code and should be exempt in the same manner as CPCN holder. | Nathan Whittacre | CEO | 23832978.2 | 26481086.89 | 47098 | 72 | 5 | 2 | 1000 | 1000 | 1016 | The proposed broadband network will deploy a carrier-grade, XGS-PON (10 Gigabit-capable Passive Optical Network) fiber-to-the-premises (FTTP) system to serve all Broadband Service Locations (BSLs) within the awarded project areas. This architecture provides symmetrical gigabit services (and higher) and is highly scalable to meet future bandwidth demands. Major Infrastructure Components The following major infrastructure elements will be deployed: 1. Fiber-Optic Cable Fiber Strand Counts: Fiber optic cables will vary from 12-count to 288-count configurations based on network topology, population density, and aggregation needs. Fiber Cable Type: Standard single-mode fiber (SMF-28 or equivalent) suitable for long-distance PON deployments and future wavelength-division multiplexing (WDM) upgrades. Placement Strategy: Approximately 75% of fiber will be placed underground in conduit to improve resilience, longevity, and climate protection. Underground conduit sizes will range from 1” to 2” depending on fiber counts and environmental constraints. Aerial Deployment: The remaining 25% of the fiber infrastructure will be deployed aerially on existing utility poles where feasible and cost-effective, utilizing pole attachments under existing Joint Pole Agreements or permits. 2. Conduit and Handholes Conduit Sizing: Conduit will typically be HDPE (High-Density Polyethylene) material in 1” or 2” diameter sizes. Larger conduit sizes or multiple conduits may be used for backbone fiber or in denser service areas to future-proof the network. Handholes: Handholes will be strategically placed to provide access points for splicing, maintenance, and future expansion without major construction disruption. 3. Optical Line Terminals (OLTs) Equipment: Calix AXOS E7-2 and/or E3-2 hardened OLT platforms will be deployed. Location: OLTs will be installed in environmentally hardened outdoor cabinets or in controlled-environment shelters at central locations within each project area. Capacity: Each OLT chassis can serve thousands of end-points with scalable upgrade paths from 10G XGS-PON to higher next-generation standards (e.g., 25G PON). 4. Fiber Distribution Hubs (FDHs) FDHs will be installed strategically throughout the network to allow for the splitting and distribution of optical signals. Splitter Technology: Passive optical splitters (1:32 split ratio) will be used, depending on service density and engineering design. FDHs will be equipped to allow easy field expansion and reconfiguration as service demand grows. 5. Drop Fibers and Network Interface Devices (NIDs) Individual fibers will run from FDHs to customer premises using hardened fiber drop cables. Termination equipment at the customer premises will include optical network terminals (ONTs) capable of delivering gigabit+ services and integrated with Wi-Fi services where applicable. Existing Facilities to Be Leveraged Stimulus Technologies plans to leverage and interconnect with the following existing assets: Existing Backbone Fiber: Where possible, Stimulus will utilize its existing backbone fiber routes or leased dark fiber assets to connect new project areas to core network aggregation points. Data Centers and Colocation Sites: Our primary points of presence (POPs) in Nevada and California — interconnected via long-haul fiber networks — provide upstream IP transit, peering, and routing capabilities. These will support backhaul for the new networks. Core Network Infrastructure: Stimulus operates existing core routers, switches, and transport systems which are scalable and modular to integrate newly built service areas without requiring significant upgrades. Indefeasible Rights of Use (IRUs): Where necessary, Stimulus may execute IRU agreements with regional fiber owners or consortia to obtain long-term, low-cost access to middle-mile and backhaul transport. We intend to use middle-mile infrastructure built by Stimulus in Nevada along the California border and California MMBN to service the network. If IRUs are available for the CA MMBN, Stimulus will attempt negotiations to use dark-fiber for infrastructure, otherwise Stimulus will utilize metro-ethernet circuits for service. Indefeasible Right of Use (IRU) Details At the time of application, Stimulus Technologies is not in discussions to secure IRUs for dark fiber strands that will complement our owned backbone assets in certain rural areas of California. In the event that IRUs are available, these IRUs will typically have terms of 20 years or longer, aligning with the asset life of the fiber network and ensuring stable, long-term backhaul capacity. If IRUs are finalized during the project implementation phase, documentation and agreements will be provided to the California Public Utilities Commission (CPUC) as required. | 75 | The majority of costs for the project will be related to fiber cable material and construction. For portions of the network where fiber is placed on existing or new pole lines, the construction costs and make ready costs from the pole owners will be the larger costs. For underground construction, the cost of trenching or boring and fiber placement within conduits will outweigh the other costs of hand holes/vaults and splicing. OLT infrastructure costs including fiber distribution hubs are another key cost item but are relatively small in comparison to the fiber material and construction costs. | Stimulus has assumed a 24-month duration for completion of the project. Project planning and engineering will be completed within the first 4 months of project commencement. Environmental and highway permitting has been estimated at 5 months and will start once a portion of the detailed engineering is completed. Procurement activities are expected to take six months but will be able to run in parallel with engineering and permitting. The expectation is that by late Q3 2026, construction build activities will commence. Stimulus will break the work down into four phases so that portions of the project area can be completed and released for customers in 3 to 4 month intervals, the first of which would be expected in December 2026. Marketing activities will commence before completion of construction on the first phase of the build to generate service demand within the project area. Subscriber activations will commence at the end of the first construction phase and continue through to the end of the project. Testing and hand off to operations will also commence at the end of the first construction phase and subsequent phases thereafter followed by final reporting and project closure. | Stimulus will be deploying a fully fiber XGS-PON network to service all eligible BSLs within the project area. Customers will be able to subscribe initially to service with symmetrical speeds of 1Gbps with latency less than 100ms and with the ability for speeds to increase over time as customer demand and usage dictate. The scalable nature of the OLT technology to be used will make the upgrade path to higher speeds cost effective for Stimulus when required. The fiber will be placed through a combination of underground and aerial construction methodologies based upon the location and permitting requirements.
a0Kcs00000PuHr0EAF | Surfnet - Fiber Calaveras North | California Broadband Alliance and Surfnet Communications Inc | Calaveras | U7265C | Ken Nye | COO | 8435776.38 | 8435776.38 | 110901 | 11 | 0 | 0 | 1000 | 1000 | 759 | This project is entirely fiber based. All cables will be placed onto existing poles. Prior to attaching to these poles, we will enter into joint use agreements with either PG&E or the appropriate incumbent LEC for that area. As a licensed CLEC we have active agreements in place with those companies for joint occupancy. We will perform load calculations and make applications for joint occupancy according to CPUC requirements and guidelines. Each pole will be field surveyed and tested for structural integrity. Due to aging, some poles will need to be replaced or augmented with temporary poles to meet loading requirements as determined in G.O. 95. In some cases, it may become necessary to install short lengths of conduit to mitigate G.O. 95 deficiencies or to conform Rule 20A undergrounding specifications. | 0 | Major expenses include splicing van, pole line hardware, fiber optic cable, routers, hubs and customer premise equipment. | Dates are estimated based on expedited approval of grant and permitting where applicable. Project milestones as follows: 10% Milestone – 1 Month after Start Construction drawings ready for bidding Vendors for all project areas identified and engaged. Initial orders for materials placed. 35% Milestone – 3 Months after Start Material ordering completed and deliveries scheduled. Permits for Project Areas Submitted Some contractors are working on projects. 60% Milestone – 8 Months after Start All permits received. Contractors identified and bids awarded for all projects. All contractors actively working on projects. 85% Milestone – 12 Months after Start 50% of projects completed. The project areas that have been acceptance tested are ready for sales and marking efforts. 100% Milestone – 15 Months after Start All construction is completed and service available to all areas within the scope of the grant funding. Final Report written and submitted. Project timelines and projections of completion outside of the proposed Gantt chart will be communicated with the FFA team immediately, if identified. | Our FTTP construction plans have been preliminary designed, focusing on viability, cost, timeline, and execution. The technical design employs 100Gbps-capable equipment, offering 1Gbps service now and room for future enhancements. With 20 years in business and 70 years of leadership experience, Surfnet is well-positioned for success. Project costs have been precisely estimated, including subcontracted construction and pole engineering by qualified companies. A $2.5 million line of credit is in place to ensure completion without affecting operational reserves, backed by our shareholder support for all FFA grants. Preliminary designs are fiber to the home or premise with less than 5% of the locations a possibility of alternative technology. The project will interconnect with middle-mile infrastructure. We affirm that we will align with SB 156 for open access and public ownership. We've partnered with public agencies and non-profits, ensuring 100% public ownership of the resulting infrastructure, which Surfnet will lease and maintain. Internet backhaul will be achieved through our existing network or new carrier connections, using an "active" headend for service distribution. Cabinets, either existing or new, will house backhaul routers. The project utilizes Passive Optical Networking (PON), a power-efficient technology with minimal visual impact due to its small 1/2" cables. PON can deliver up to 10Gbps speeds. All new cabling will be on existing poles, primarily owned by PG&E, eliminating CEQA review needs. We will conduct pole inspections and apply for joint occupancy using PG&E-approved methods. The cost of each project meets the ministerial review criteria, and we request that it be funded as budgeted in our plan. We are local and familiar with the project area and are confident in the cost estimates we have done. Instances where there is a discrepancy between the estimated subsidy needed, we would demonstrate the low populations and development costs in this high-cost region
a0Kcs00000PuJMYEA3 | Surfnet - Fiber Calaveras South | California Broadband Alliance and Surfnet Communications Inc | Calaveras | U7265C | Ken Nye | Operations Manager | 6793089.84 | 6793089.84 | 110901 | 1 | 0 | 0 | 1000 | 1000 | 693 | This project is entirely fiber based. All cables will be placed onto existing poles. Prior to attaching to these poles, we will enter into joint use agreements with either PG&E or the appropriate incumbent LEC for that area. As a licensed CLEC we have active agreements in place with those companies for joint occupancy. We will perform load calculations and make applications for joint occupancy according to CPUC requirements and guidelines. Each pole will be field surveyed and tested for structural integrity. Due to aging, some poles will need to be replaced or augmented with temporary poles to meet loading requirements as determined in G.O. 95. In some cases, it may become necessary to install short lengths of conduit to mitigate G.O. 95 deficiencies or to conform Rule 20A undergrounding specifications. | 0 | Major expenses include splicing van, pole line hardware, fiber optic cable, routers, hubs and customer premise equipment. | Dates are estimated based on expedited approval of grant and permitting where applicable. Project milestones as follows: 10% Milestone – 1 Month after Start Construction drawings ready for bidding Vendors for all project areas identified and engaged. Initial orders for materials placed. 35% Milestone – 3 Months after Start Material ordering completed and deliveries scheduled. Permits for Project Areas Submitted Some contractors are working on projects. 60% Milestone – 8 Months after Start All permits received. Contractors identified and bids awarded for all projects. All contractors actively working on projects. 85% Milestone – 12 Months after Start 50% of projects completed. The project areas that have been acceptance tested are ready for sales and marking efforts. 100% Milestone – 15 Months after Start All construction is completed and service available to all areas within the scope of the grant funding. Final Report written and submitted. Project timelines and projections of completion outside of the proposed Gantt chart will be communicated with the FFA team immediately, if identified. | Our FTTP construction plans have been preliminary designed, focusing on viability, cost, timeline, and execution. The technical design employs 100Gbps-capable equipment, offering 1Gbps service now and room for future enhancements. With 20 years in business and 70 years of leadership experience, Surfnet is well-positioned for success. Project costs have been precisely estimated, including subcontracted construction and pole engineering by qualified companies. A $2.5 million line of credit is in place to ensure completion without affecting operational reserves, backed by our shareholder support for all FFA grants. Preliminary designs are fiber to the home or premise with less than 5% of the locations a possibility of alternative technology. The project will interconnect with middle-mile infrastructure. We affirm that we will align with SB 156 for open access and public ownership. We've partnered with public agencies and non-profits, ensuring 100% public ownership of the resulting infrastructure, which Surfnet will lease and maintain. Internet backhaul will be achieved through our existing network or new carrier connections, using an "active" headend for service distribution. Cabinets, either existing or new, will house backhaul routers. The project utilizes Passive Optical Networking (PON), a power-efficient technology with minimal visual impact due to its small 1/2" cables. PON can deliver up to 10Gbps speeds. All new cabling will be on existing poles, primarily owned by PG&E, eliminating CEQA review needs. We will conduct pole inspections and apply for joint occupancy using PG&E-approved methods. The cost of each project meets the ministerial review criteria, and we request that it be funded as budgeted in our plan. We are local and familiar with the project area and are confident in the cost estimates we have done. Instances where there is a discrepancy between the estimated subsidy needed, we would demonstrate the low populations and development costs in this high-cost region
a0Kcs00000PcL6gEAF | Surfnet - Salinas | California Broadband Alliance and Surfnet Communications Inc | Monterey | U7265C | Ken Nye | COO | 3296421.45 | 3296421.45 | 53068 | 73 | 1 | 0 | 1000 | 1000 | 256 | This project is entirely fiber based. All cables will be placed onto existing poles. Prior to attaching to these poles, we will enter into joint use agreements with either PG&E or the appropriate incumbent LEC for that area. As a licensed CLEC we have active agreements in place with those companies for joint occupancy. We will perform load calculations and make applications for joint occupancy according to CPUC requirements and guidelines. Each pole will be field surveyed and tested for structural integrity. Due to aging, some poles will need to be replaced or augmented with temporary poles to meet loading requirements as determined in G.O. 95. In some cases, it may become necessary to install short lengths of conduit to mitigate G.O. 95 deficiencies or to conform Rule 20A undergrounding specifications. | 0 | Major expenses include splicing van, pole line hardware, fiber optic cable, routers, hubs and customer premise equipment. | Dates are estimated based on expedited approval of grant and permitting where applicable. Project milestones as follows: 10% Milestone – 1 Month after Start Construction drawings ready for bidding Vendors for all project areas identified and engaged. Initial orders for materials placed. 35% Milestone – 3 Months after Start Material ordering completed and deliveries scheduled. Permits for Project Areas Submitted Some contractors are working on projects. 60% Milestone – 8 Months after Start All permits received. Contractors identified and bids awarded for all projects. All contractors actively working on projects. 85% Milestone – 12 Months after Start 50% of projects completed. The project areas that have been acceptance tested are ready for sales and marking efforts. 100% Milestone – 15 Months after Start All construction is completed and service available to all areas within the scope of the grant funding. Final Report written and submitted. Project timelines and projections of completion outside of the proposed Gantt chart will be communicated with the FFA team immediately, if identified. | Our FTTP construction plans have been preliminary designed, focusing on viability, cost, timeline, and execution. The technical design employs 100Gbps-capable equipment, offering 1Gbps service now and room for future enhancements. With 20 years in business and 70 years of leadership experience, Surfnet is well-positioned for success. Project costs have been precisely estimated, including subcontracted construction and pole engineering by qualified companies. A $2.5 million line of credit is in place to ensure completion without affecting operational reserves, backed by our shareholder support for all FFA grants. Preliminary designs are fiber to the home or premise with less than 5% of the locations a possibility of alternative technology. The project will interconnect with middle-mile infrastructure. We affirm that we will align with SB 156 for open access and public ownership. We've partnered with public agencies and non-profits, ensuring 100% public ownership of the resulting infrastructure, which Surfnet will lease and maintain. Internet backhaul will be achieved through our existing network or new carrier connections, using an "active" headend for service distribution. Cabinets, either existing or new, will house backhaul routers. The project utilizes Passive Optical Networking (PON), a power-efficient technology with minimal visual impact due to its small 1/2" cables. PON can deliver up to 10Gbps speeds. All new cabling will be on existing poles, primarily owned by PG&E, eliminating CEQA review needs. We will conduct pole inspections and apply for joint occupancy using PG&E-approved methods. The cost of each project meets the ministerial review criteria, and we request that it be funded as budgeted in our plan. We are local and familiar with the project area and are confident in the cost estimates we have done. Instances where there is a discrepancy between the estimated subsidy needed, we would demonstrate the low populations and development costs in this high-cost region.
a0Kcs00000PcoVGEAZ | Surfnet - San Ardo | California Broadband Alliance and Surfnet Communications Inc | Monterey | U7265C | Ken Nye | COO | 971056.8 | 971056.8 | 74712 | 5 | 4 | 1 | 1000 | 1000 | 133 | This project is entirely fiber based. All cables will be placed onto existing poles. Prior to attaching to these poles, we will enter into joint use agreements with either PG&E or the appropriate incumbent LEC for that area. As a licensed CLEC we have active agreements in place with those companies for joint occupancy. We will perform load calculations and make applications for joint occupancy according to CPUC requirements and guidelines. Each pole will be field surveyed and tested for structural integrity. Due to aging, some poles will need to be replaced or augmented with temporary poles to meet loading requirements as determined in G.O. 95. In some cases, it may become necessary to install short lengths of conduit to mitigate G.O. 95 deficiencies or to conform Rule 20A undergrounding specifications. | 0 | Major expenses include splicing van, pole line hardware, fiber optic cable, routers, hubs and customer premise equipment. | Dates are estimated based on expedited approval of grant and permitting where applicable. Project milestones as follows: 10% Milestone – 1 Month after Start Construction drawings ready for bidding Vendors for all project areas identified and engaged. Initial orders for materials placed. 35% Milestone – 3 Months after Start Material ordering completed and deliveries scheduled. Permits for Project Areas Submitted Some contractors are working on projects. 60% Milestone – 8 Months after Start All permits received. Contractors identified and bids awarded for all projects. All contractors actively working on projects. 85% Milestone – 12 Months after Start 50% of projects completed. The project areas that have been acceptance tested are ready for sales and marking efforts. 100% Milestone – 15 Months after Start All construction is completed and service available to all areas within the scope of the grant funding. Final Report written and submitted. Project timelines and projections of completion outside of the proposed Gantt chart will be communicated with the FFA team immediately, if identified. | ﻿ Our FTTP construction plans have been preliminary designed, focusing on viability, cost, timeline, and execution. The technical design employs 100Gbps-capable equipment, offering 1Gbps service now and room for future enhancements. With 20 years in business and 70 years of leadership experience, Surfnet is well-positioned for success. Project costs have been precisely estimated, including subcontracted construction and pole engineering by qualified companies. A $2.5 million line of credit is in place to ensure completion without affecting operational reserves, backed by our shareholder support for all FFA grants. Preliminary designs are fiber to the home or premise with less than 5% of the locations a possibility of alternative technology. The project will interconnect with middle-mile infrastructure. We affirm that we will align with SB 156 for open access and public ownership. We've partnered with public agencies and non-profits, ensuring 100% public ownership of the resulting infrastructure, which Surfnet will lease and maintain. Internet backhaul will be achieved through our existing network or new carrier connections, using an "active" headend for service distribution. Cabinets, either existing or new, will house backhaul routers. The project utilizes Passive Optical Networking (PON), a power-efficient technology with minimal visual impact due to its small 1/2" cables. PON can deliver up to 10Gbps speeds. All new cabling will be on existing poles, primarily owned by PG&E, eliminating CEQA review needs. We will conduct pole inspections and apply for joint occupancy using PG&E-approved methods. The cost of each project meets the ministerial review criteria, and we request that it be funded as budgeted in our plan. We are local and familiar with the project area and are confident in the cost estimates we have done. Instances where there is a discrepancy between the estimated subsidy needed, we would demonstrate the low populations and development costs in this high-cost region.