## Monthly Contractor Report on GM
Monthly Contractor Report
Reporting Period |  | Awardee | Name of the Project | Type of Contract | Contractor Name | Contractor License Number | Location of Work to be Performed | Anticipated Start Date | Anticipated End Date | Certification | Name of Signatory | Title of Signatory
September 2024 |  | Plumas-Sierra Telecommunications | PST Plumas Pines-Graeagle | Contract | Curtis & Sons Construction, Inc. | 751460 | Jamison Road, Graeagle, CA 96103 | 9/9/2024 | 9/20/2024 | Yes | Corby Erwin | Consultant
September 2024 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | Sierra Earthworks, Inc. | 811008 | Grizzly Ranch Road | 9/4/2024 | 10/31/2024 | Yes | Corby Erwin | Consultant
September 2024 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | Curtis & Sons Construction, Inc. | 751460 | Grizzly Ranch Road, Portola, CA 96122 | 9/9/2024 | 10/7/2024 | Yes | Corby Erwin | Consultant
September 2024 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | Wasatch Electric, LLC | 1114927 | Whitehawk Valley, Clio, CA 96106 | 9/23/2024 | 10/4/2024 | Yes | Corby Erwin | Consultant
October 2024 |  | Plumas-Sierra Telecommunications | PST Plumas Pines-Graeagle | Contract | Folchi Logging and Construction, Inc. | 798126 | Sugar Pine Drive, and Aspen Circle, Graeagle, CA 96103 | 10/22/2024 | 11/24/2024 | Yes | Corby Erwin | Consultant
October 2024 |  | Plumas-Sierra Telecommunications | PST Plumas Pines-Graeagle | Contract | Curtis & Sons Construction, Inc. | 751460 | Iroquois Trail, and Gold Ridge Drive, Graeagle, CA 96103 | 10/28/2024 | 11/29/2024 | Yes | Corby Erwin | Consultant
October 2024 |  | Plumas-Sierra Telecommunications | PST Plumas Pines-Graeagle | Contract | Sierra Earthworks, Inc. | 811008 | Smith Creek Road, Graeagle, CA 96103 | 10/22/2024 | 11/11/2024 | Yes | Corby Erwin | Consultant
October 2024 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | Curtis & Sons Construction, Inc. | 751460 | Ridgewood Dr., Gulling St., W. Quincy Ave., Green St., Ridge St., W. Loyalton Ave., W. Spruce Ave., and West St., Portola, CA 96122; Quail View Cir., Graeagle, CA 96103 | 10/24/2024 | 1/31/2025 | Yes | Corby Erwin | Consultant
October 2024 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | Sierra Earthworks, Inc. | 811008 | Rheinfelder St., Fox Sparrow, Spring Meadow Dr., S. Ridge Rd., Starflower Dr., and Blacktail Ridge, Portola, CA 96122 | 11/1/2024 | 8/6/2025 | Yes | Corby Erwin | Consultant
October 2024 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | B&E Telecom LLC | 1079668 | Miners Passage, Quail View Cir., McKenzie Trail, Deer Creek Crossing, Bridle Path, Fox Tail, and Prospector Dr., Graeagle, CA 96103 | 10/24/2024 | 1/31/2025 | Yes | Corby Erwin | Consultant
November 2024 |  | VARCOMM Broadband, Inc. | Terra Bella | Contract | McKuin Pipeline Inc | 835764 | Terra Bella, Tulare County, California | 3/31/2025 | 10/31/2025 | Yes | Eric N. Votaw | Chief Executive Officer
December 2024 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Integrity Data and Fiber Inc. | 778249 | Backbone infrastructure surveys 24th St, Greenhaven Dr, Fruitridge Rd, Main Ave, Norwood Ave & Bell Ave. | 11/1/2024 | 12/31/2024 | Yes | Pedro Sanchez | Telecommunications Engineer
December 2024 |  | Plumas-Sierra Telecommunications | PST Plumas Pines-Graeagle | Contract | Sierra Earthworks, Inc. | 811008 | Evergreen Cr, Eureka Springs Dr, Cedar Ln | 12/2/2024 | 12/31/2024 | Yes | Corby Erwin | Consultant
December 2024 |  | Plumas-Sierra Telecommunications | PST Plumas Pines-Graeagle | Contract | B&E Telecom LLC | 1079668 | Gold Ridge Dr. Smith Creek, Gold Nugget, Graeagle, CA 96103 | 12/4/2024 | 12/23/2024 | Yes | Corby Erwin | Consultant
December 2024 |  | Plumas-Sierra Telecommunications | PST Plumas Pines-Graeagle | Contract | Curtis & Sons Construction, Inc. | 751460 | Graeagle Meadows Rd, Eagles Ridge, Graeagle, CA 96103 | 12/2/2024 | 12/6/2024 | Yes | Corby Erwin | Consultant
December 2024 |  | Plumas-Sierra Telecommunications | PST Plumas Pines-Graeagle | Contract | Folchi Logging and Construction, Inc. | 798126 | Aspen Circle, Graeagle, CA 96103 | 12/2/2024 | 12/31/2024 | Yes | Corby Erwin | Consultant
December 2024 |  | Plumas-Sierra Telecommunications | PST Plumas Pines-Graeagle | Contract | JIM WEST TREE SERVICE | 1027258 | Paiute Trl, Tolowa Trl, Yokut Trl, Graeagle, CA 96103 | 12/9/2024 | 12/31/2024 | Yes | Corby Erwin | Consultant
December 2024 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | McGarr Excavation, Inc. | 746805 | Delleker Dr., N. Horseshoe Trail, Horseshoe Trail, Delleker, CA 96122 | 12/4/2024 | 12/24/2024 | Yes | Corby Erwin | Consultant
December 2024 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | Curtis & Sons Construction, Inc. | 751460 | N. Gulling St., West St., Ridge St., Colorado St., 2nd Ave., Portola, CA 96122 | 12/2/2024 | 12/20/2024 | Yes | Corby Erwin | Consultant
December 2024 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | Sierra Earthworks, Inc. | 811008 | Spring Meadow Dr, Portola, CA 96122 | 12/2/2024 | 12/31/2024 | Yes | Corby Erwin | Consultant
December 2024 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | JIM WEST TREE SERVICE | 1027258 | N. Gulling St., S. Gulling St., Third Ave., Ellen St., 3rd St., Portola, CA 96122 | 12/3/2024 | 12/31/2024 | Yes | Corby Erwin | Consultant
December 2024 |  | VARCOMM Broadband, Inc. | Terra Bella | Contract | McKuin Pipeline Inc | 835764 | Terra Bella, Tulare County, California | 4/30/2025 | 11/28/2025 | Yes | Eric N. Votaw | Chief Executive Officer
January 2025 |  | Astound Broadband, LLC | Atascadero-Paso Robles | Contract | Taro Communications | 848981 | Atascadero, Paso Robles | 1/24/2025 | 3/30/2025 | Yes | Timothy Williams | VP Expansion
January 2025 |  | City of Chico | Providing Broadband Service to Butte County Locations in Need of Investment | Contract | Fibertel CA, LLC | 1111985 | 411 Main St, Chico, CA 95928 | 12/31/2024 | 12/19/2026 | Yes | Josh Marquis | Deputy Director - Information Systems
January 2025 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Integrity Data & Fiber Inc. | 778249 | Backbone fiber infrastructure surveys on Howe Ave, 65th Expressway, Elder Creek Rd, Valley Hi Dr, Center Pkwy, Florin Perkings Rd, Folsom Blvd | 1/2/2025 | 2/21/2025 | Yes | Pedro Sanchez | Telecommunications Engineer
January 2025 |  | City of Vallejo | Mare Island Build | Contract | Smart Fiber | #937603 | Mare Island: 487 Nimitz Ave, Vallejo CA 94592 | 1/1/2025 | 7/1/2026 | Yes | Sidney Wilson | Administrative Analyst
January 2025 |  | City of Vallejo | N. Sonoma Blvd. | Contract | Smart Fiber | #937603 | N. Sonoma Blvd: 700 Sereno Dr, Vallejo CA 94590 | 1/1/2025 | 7/1/2026 | Yes | Sidney Wilson | Administrative Analyst
January 2025 |  | City of Vallejo | Porter St to Seaport | Contract | Smart Fiber | 937603 | Porter to Seaport: 333 Curtola Pkwy, Vallejo CA 94590 | 1/1/2025 | 7/1/2026 | Yes | Sidney Wilson | Administrative Analyst
January 2025 |  | City of Vallejo | Trailer City Park Project | Contract | Smart Fiber | 937603 | Trailer City Park: 1201 Georgia St, Vallejo CA 94590 | 1/1/2025 | 7/1/2026 | Yes | Sidney Wilson | Administrative Analyst
January 2025 |  | Plumas-Sierra Telecommunications | PST Plumas Pines-Graeagle | Contract | McGarr Excavation, Inc. | 746805 | Gold Ridge, Gold Nugget, Graeagle, CA 96103 | 1/20/2025 | 6/13/2025 | Yes | Corby Erwin | Consultant
January 2025 |  | Plumas-Sierra Telecommunications | PST Plumas Pines-Graeagle | Contract | Sierra Earthworks, Inc. | 811008 | Evergreen, Eureka, Cedar, Graeagle, CA 96103 | 1/20/2025 | 6/13/2025 | Yes | Corby Erwin | Consultant
January 2025 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | Folchi Logging and Construction, Inc. | 798126 | 3rd Ave., Portola, CA 96122 | 1/13/2025 | 1/31/2025 | Yes | Corby Erwin | Consultant
January 2025 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | McGarr Excavation, Inc. | 746805 | One Horse Way, Deer Creek Xing, Black Bear Trl, Clio, CA 96103 | 1/13/2025 | 2/28/2025 | Yes | Corby Erwin | Consultant
January 2025 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | Sierra Earthworks, Inc. | 811008 | Grizzly Rd, Blacktail Ridge, Club House Dr., Grizzly Ranch Rd., Portola, CA 96122 | 1/21/2025 | 1/31/2025 | Yes | Corby Erwin | Consultant
January 2025 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | B&E Telecom LLC | 1079668 | Blacktail Ridge, Pepper Grass Ln, Portola, CA 96122 | 1/8/2025 | 1/31/2025 | Yes | Corby Erwin | Consultant
January 2025 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | Curtis & Sons Construction, Inc. | 751460 | Joy Way, E. Magnolia Ave., N. Pine St., Ponderosa Ave., E. Spruce St., Portola, CA 96122 | 1/13/2025 | 1/31/2025 | Yes | Corby Erwin | Consultant
January 2025 |  | Plumas-Sierra Telecommunications | PST Quincy Coax Conversion | Contract | Curtis & Sons Construction, Inc. | 751460 | Shelley Ln., Forest View, Sierra, Clough St., Quincy, CA 95971 | 1/6/2025 | 2/28/2025 | Yes | Corby Erwin | Consultant
January 2025 |  | Plumas-Sierra Telecommunications | PST Quincy Coax Conversion | Contract | JIM WEST TREE SERVICE | 1027258 | Lee Rd, Carol Ln, Quincy, CA 95971 | 1/2/2025 | 1/10/2025 | Yes | Corby Erwin | Consultant
January 2025 |  | unWired Broadband, LLC | City of Gustine | Contract | Telcon Services | 1103061 | City of Gustine | 4/15/2025 | 6/1/2026 | Yes | Mitzi McMahan | Director of Grants and Regulatory Administration
January 2025 |  | VARCOMM Broadband, Inc. | Terra Bella | Contract | McKuin Pipeline Inc | 835764 | Terra Bella, Tulare County, California | 6/2/2025 | 1/9/2026 | Yes | Eric N. Votaw | Chief Executive Officer
February 2025 |  | California Broadband Alliance | Hutchinson | Subcontract | EDTtech | 3387PB | West of Highway 17 | 2/1/2025 | 10/15/2026 | Yes | Kiran Bengard | Operations Manager
February 2025 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Integrity Data & Fiber Inc | 778249 | 65th Expwy, Elder Creek Rd, Florin Perkins Rd | 1/15/2025 | 2/28/2025 | Yes | Pedro Sanchez | Telecommunications Engineer
February 2025 |  | County of Placer | Foothills - Broadband Expansion in Placer County | Contract | CableCom LLC | 82695 | Applegate, Capehorn, Magra, and Alta. Placer County Foothills | 1/16/2025 | 11/27/2026 | Yes | Richard Weisbecker | Project Manager
February 2025 |  | Plumas-Sierra Telecommunications | PST Plumas Pines-Graeagle | Contract | McGarr Excavation, Inc. | 746805 | Brian Dr., Tamarack Ct., Cedar Ln., Sequoia Cir., Tamarack Pl., Oak Ct., Blairsden-Graeagle, CA 96103 | 2/1/2025 | 2/28/2025 | Yes | Corby Erwin | Consultant
February 2025 |  | Plumas-Sierra Telecommunications | PST Portola-Delleker-Whitehawk | Contract | B&E Telecom LLC | 1079668 | Blacktail Ridge, Peppergrass Ln, Sorrel Ln, Grizzly Ranch Rd, Clubhouse Dr, Fox Sparrow, Portola, CA 96122 | 2/3/2025 | 3/15/2025 | Yes | Corby Erwin | Consultant
February 2025 |  | Plumas-Sierra Telecommunications | PST Quincy Coax Conversion | Contract | Curtis & Sons Construction, Inc. | 751460 | 1st St. and Center St., Quincy, CA 95971 | 2/3/2025 | 3/15/2025 | Yes | Corby Erwin | Consultant
February 2025 |  | Santa Ynez Band of Chumash Indians | Chumash Fiber Network | Contract | HP Communications Inc. | 752762, Class A, C7, C10, C31 | Santa Ynez Chumash Reservation and Camp 4, Santa Ynez, CA | 2/24/2025 | 7/25/2026 | Yes | Columba Quintero | Senior Grants Manager
February 2025 |  | VARCOMM Broadband, Inc. | Terra Bella | Contract | McKuin Pipeline Inc | 835764 | Terra Bella, Tulare County, California | 4/28/2025 | 11/28/2025 | Yes | Eric N. Votaw | Chief Executive Officer
March 2025 |  | Astound Broadband, LLC | Atascadero-Paso Robles | Contract | Structure Leasing & Engineering, Inc | 480096 | Atascadero, Paso Robles | 3/5/2025 | 10/31/2025 | Yes | Tim Williams | VP of Expansion
March 2025 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Integrity Data & Fiber Inc. | 778249 | College Town Dr, Hornet Dr, Folsom Bl, Fruitridge Rd, Natomas Bl, Club Center Dr, Gateway Park Bl, Arena Bl | 3/3/2025 | 3/31/2025 | Yes | Pedro Sanchez | Telecommunications Engineer
March 2025 |  | Santa Ynez Band of Chumash Indians | Chumash Fiber Network | Contract | HP Communications Inc. | 752762, Class A, C7, C10, C31 | Chumash Reservation and Camp 4, Santa Ynez, CA | 4/15/2025 | 8/31/2025 | Yes | Columba Quintero | Senior Tribal Grants Manager
March 2025 |  | unWired Broadband, LLC | City of Gustine | Contract | JD Wouters | 861483 | City of Gustine | 3/31/2025 | 6/1/2026 | Yes | Mitzi McMahan | Director of Grants and Regulatory Admin
April 2025 |  | California Broadband Alliance | Radonich | Subcontract | EDTTech, Inc | 830873 | Radonich, Hillside , Firhaven | 1/17/2025 | 8/1/2025 | Yes | Kiran Bengard | Operations Manager
May 2025 |  | AT&T Services, Inc. (on behalf of Pacific Bell Telephone Company) | San Bernadino - 1 | Contract | VCI | 765716 | FONTANA, COLTON | 7/1/2025 | 9/30/2026 | Yes | Antonio R Davis | Principal Program Manager
May 2025 |  | AT&T Services, Inc. on behalf of AT&T California | San Mateo - 1 | Contract | WEST VALLEY CONST. | 174968 | SAN MATEO | 7/1/2025 | 9/30/2026 | Yes | Antonio R Davis | Principal Program Manager
May 2025 |  | AT&T Services, Inc. on behalf of its affiliate Pacific Bell Telephone Company | Kern - 1 | Contract | Mastec | 760562 | BAKERSFIELD/EXPO, TEHACHAPI | 7/1/2025 | 9/30/2026 | Yes | Antonio R Davis | Principal Program Manager
May 2025 |  | AT&T Services, Inc. on behalf of its affiliate Pacific Bell Telephone Company | Riverside - 1 | Contract | PACIFIC WEST SPACE COMM. | 597074 | CORONA | 7/1/2025 | 9/30/2026 | Yes | Antonio R Davis | Principal Program Manager
May 2025 |  | AT&T Services, Inc. on behalf of its affiliate Pacific Bell Telephone Company | Riverside - 1 | Contract | HHS | not available | ARLINGTON | 7/1/2025 | 9/30/2026 | Yes | Antonio R Davis | Principal Program Manager
May 2025 |  | AT&T Services, Inc. on behalf of its affiliate Pacific Bell Telephone Company | Riverside/San Bernadino - 1 | Contract | HP Communications | 752762 | RIVERSIDE | 7/1/2025 | 9/30/2026 | Yes | Antonio R Davis | Principal Program Manager
May 2025 |  | AT&T Services, Inc. on behalf of its affiliate Pacific Bell Telephone Company | Riverside/San Bernadino - 1 | Contract | VCI | 765716 | RIVERSIDE | 7/1/2025 | 9/30/2026 | Yes | Antonio R Davis | Principal Program Manager
May 2025 |  | AT&T Services, Inc. on behalf of its affiliate Pacific Bell Telephone Company d/b/a AT&T California | Stanislaus - 1 | Contract | MASTEC | 760562 | HUGHSON | 7/1/2025 | 9/30/2026 | Yes | Antonio R Davis | Principal Program Manager
May 2025 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Integrity Data & Fiber Inc. | 778249 | Power Inn Rd (Folsom Bl to 14th Ave) | 5/1/2025 | 6/30/2025 | Yes | Pedro Sanchez | Telecommunications Engineer
June 2025 |  | Astound Broadband, LLC | Atascadero-Paso Robles | Contract | EDT | 830873 | Atascadero and Paso Robles, California | 9/30/2025 | 5/30/2026 | Yes | Tim Williams | VP Network Expansion
June 2025 |  | AT&T Services, Inc. on behalf of AT&T California | San Mateo - 1 | Subcontract | West Valley Construction | 174968 | SAN CARLOS, SAN MATEO | 7/1/2025 | 9/30/2025 | Yes | Antonio R Davis | Principal Program Manager
June 2025 |  | AT&T Services, Inc. on behalf of its affiliate Pacific Bell Telephone Company | Riverside - 1 | Subcontract | VCI | 765716 | ARLINGTON, CORONA, PEDLEY, RIVERSIDE | 7/1/2025 | 9/30/2025 | Yes | Antonio R Davis | Principal Program Manager
June 2025 |  | AT&T Services, Inc. on behalf of its affiliate Pacific Bell Telephone Company d/b/a AT&T California | Napa - 1B | Subcontract | Pacific Utility | not available | ANGWIN-ST HELEN, LAKE BERRYESSA | 7/1/2025 | 9/30/2025 | Yes | Antonio R Davis | Principal Program Manager
June 2025 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Integrity Data & Fiber Inc. | 778249 | Power Inn Rd (Folsom to 14th Ave), Arena Blvd (El Centro to Duckhorn Dr.) | 6/2/2025 | 8/29/2025 | Yes | Pedro Sanchez | Telecommunications Engineer
June 2025 |  | Plumas-Sierra Telecommunications | PST Loyalton-Sierra Brooks | Contract | Curtis & Sons Construction, Inc. | 751460 | Smithneck Rd., Loyalton, CA 96118 | 6/2/2025 | 6/20/2025 | Yes | Corby Erwin | Consultant
July 2025 |  | City of Chico | Providing Broadband Service to Butte County Locations in Need of Investment | Subcontract | Sun Communications | 1030609 | Park Vista/E. 8th Street (Zone 1), Chico, CA 95928 | 7/8/2025 | 6/30/2026 | Yes | Joe Moralli | Management Analyst
July 2025 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Integrity Data & Fiber Inc | 778249 | Natomas Blvd (Elkhorn Bl to Del Paso Rd) | 7/1/2025 | 8/29/2025 | Yes | Pedro Sanchez | Telecommunications Engineer
July 2025 |  | Plumas-Sierra Telecommunications | PST Loyalton-Sierra Brooks | Contract | Wasatch Electric LLC | 1114927 | Sage Dr Loyalton, CA 96118 | 7/14/2025 | 7/31/2025 | Yes | Jeff Blagg | ROW Engineer Senior Grants Administrator
July 2025 |  | Plumas-Sierra Telecommunications | PST Loyalton-Sierra Brooks | Subcontract | NL Builders Inc. | 847534 | HWY 49 Loyalton, CA 96118 | 7/1/2025 | 7/31/2025 | Yes | Jeff Blagg | ROW Engineer and Senior Grants Administrator
July 2025 |  | Plumas-Sierra Telecommunications | PST Loyalton-Sierra Brooks | Contract | Jim West Tree Service | 1027258 | Sage Dr Loyalton, CA 96118 | 7/1/2025 | 7/31/2025 | Yes | Jeff Blagg | ROW Engineer Senior Grants Administrator
August 2025 |  | City of Chico | Providing Broadband Service to Butte County Locations in Need of Investment | Subcontract | Sennza Construction, LLC | 1053155 | E 10th Street (Zone 2) , Chico, CA 95928 | 8/1/2025 | 6/30/2026 | Yes | Joe Moralli | Management Analyst
August 2025 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Integrity Data & Fiber Inc. | 778249 | Natomas Blvd Splicing, Fire Station 99 cable installation and splicing, Fire Station 9 fiber installation, Florin Perkins Rd fiber installation (Fruitridge to Unsworth) | 8/1/2025 | 9/30/2025 | Yes | Pedro Sanchez | Telecommunications Engineer
August 2025 |  | Plumas-Sierra Telecommunications | PST Calpine | Contract | Wasatch Electric, LLC | 1114927 | Yuba Pass, Calpine, CA 96124 | 8/18/2025 | 9/5/2025 | Yes | Corby Erwin | Consultant
August 2025 |  | Plumas-Sierra Telecommunications | PST Loyalton-Sierra Brooks | Contract | Wasatch Electric, LLC | 1114927 | Sage Dr., Poole Ln., Highway 49, Loyalton, CA 96118 | 8/1/2025 | 9/8/2025 | Yes | Corby Erwin | Consultant
August 2025 |  | Plumas-Sierra Telecommunications | PST Loyalton-Sierra Brooks | Contract | Folchi Logging and Construction, Inc. | 798126 | W. Sierra Brooks Dr., Longhorn Dr., Wrangler Dr., Smith Creek Rd., Loyalton, CA 96118 | 8/1/2025 | 8/29/2025 | Yes | Corby Erwin | Consultant
August 2025 |  | Plumas-Sierra Telecommunications | PST Loyalton-Sierra Brooks | Subcontract | NL Builders Inc. | 847534 | W. Sierra Brooks Dr., Loyalton, CA 96118 | 8/1/2025 | 8/29/2025 | Yes | Corby Erwin | Consultant
September 2025 |  | Santa Ynez Band of Chumash Indians | Chumash Fiber Network | Contract | HP Communications Inc. | 752762, Class A, C7, C10, C31 | Chumash Reservation and Camp 4, Santa Ynez, CA | 4/15/2025 | 2/27/2026 | Yes | David Fein | Sr. Project Manager
October 2025 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Integrity Data & Fiber Inc. | 778249 | Fire Station 8, Fire Station 9, Fire Station 30, Franklin Blvd (47th to Florin), Fruitridge Rd/Freeport | 10/1/2025 | 10/31/2025 | Yes | Pedro Sanchez | Telecommunications Engineer
October 2025 |  | Plumas-Sierra Telecommunications | PST Loyalton-Sierra Brooks | Contract | B&E Telecom LLC | 1079668 | Sage Dr. Loyalton , CA 96118 | 10/1/2025 | 10/31/2025 | Yes | Jeff Blagg | ROW Engineer and Senior Grants Administrator
November 2025 |  | Comcast Cable Communications Management, LLC | Tulare Agriculture County | Subcontract | Network Connections | 1061886 | Rolt 16 Visalia Lincoln Rd | 11/1/2025 | 12/2/2025 | Yes | John A. Gutierrez | Vice President, Regulatory Affairs
November 2025 |  | Comcast Cable Communications Management, LLC | Tulare Agriculture County | Subcontract | Nacom USA Inc | 1097076 | Rolt 22 Sultana | 11/1/2025 | 12/2/2025 | Yes | John A. Gutierrez | Vice President, Regulatory Affairs
November 2025 |  | Plumas-Sierra Telecommunications | PST Loyalton-Sierra Brooks | Contract | B&E Telecom LLC | 1079668 | Pine Rd., Bell Rd., Edelweiss Dr., and Moss Dr., Loyalton 96118 | 11/3/2025 | 11/26/2025 | Yes | Jeff Blagg | ROW Engineer and Senior Grants Administrator
December 2025 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Bear Electrical Solutions LLC | 982079 | City wide locations for Sacramento Last Mile Project existing backbone infrastructure repairs. | 1/20/2026 | 4/30/2026 | Yes | Pedro Sanchez | Telecommunications Engineer
December 2025 |  | County of Placer | Foothills - Broadband Expansion in Placer County | Contract | HP COMMUNICATIONS INC | 752762 | Applegate, Capehorn, Magra, and Alta. Placer County Foothills | 12/17/2025 | 11/13/2026 | Yes | Richard Weisbecker | Project Manager
December 2025 |  | Gateway Cities Council of Governments | Gateway Cities Council of Governments Last Mile Broadband Project | Contract | California Department of Technology | N/A | Los Angeles County | 9/1/2025 | 12/31/2026 | Yes | Alex Telthorst | Sr. Broadband Consultant
December 2025 |  | Gateway Cities Council of Governments | Gateway Cities Council of Governments Last Mile Broadband Project | Contract | Jones Mayer Law | n/a | Los Angeles County | 1/1/2025 | 12/31/2026 | Yes | Alex Telthorst | Sr. Broadband Consultant
December 2025 |  | Gateway Cities Council of Governments | Gateway Cities Council of Governments Last Mile Broadband Project | Contract | Entrust Solutions Group | N/A | Los Angeles County | 1/15/2025 | 12/31/2026 | Yes | Alex Telthorst | Sr. Broadband Consultant
December 2025 |  | Plumas-Sierra Telecommunications | PST Loyalton-Sierra Brooks | Contract | B&E Telecom LLC | 1079668 | Smithneck Rd., Loyalton 96118 | 12/1/2025 | 12/31/2025 | Yes | Corby Erwin | Consultant
January 2026 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Bear Electrical Solutions LLC | 982079 | Main Ave, Bell/Norwood Ave, Valley Hi Dr, Pocket/Greenhaven, 65th/21st Ave/Fruitridge, Florin Perkins/Folsom/Jackson/23rd Ave/25th Ave, Fruitridge Rd/Monterey/Freeport, Franklin Bl from Fruitridge to 38th ave | 1/20/2026 | 4/30/2026 | Yes | Pedro Sanchez | Telecommunications Engineer
February 2026 |  | City of Fort Bragg | Fort Bragg Gig | Subcontract | Liberty Contracting & Consulting, Inc. | 1000023057 | Various throughout City limits | 2/16/2026 | 6/30/2026 | Yes | Lacy Sallas | Grants Coordinator
February 2026 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Integrity Data & Fiber Inc. | 778249 | Challenge Way, Campus Commons Neighborhood R&R, Granada Way | 2/2/2026 | 7/31/2026 | Yes | Pedro Sanchez | Telecommunications Engineer
February 2026 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Bear Electrical Solutions LLC | 982079 | Worked on the following segments fixing conduit issues Florin Perkins, 65th Expressway, Heritage Lane, Bell Ave, Fruitridge Rd, Franklin Blvd, 24th St, Folsom Blvd | 1/20/2026 | 4/30/2026 | Yes | Pedro Sanchez | Telecommunications Engineer
February 2026 |  | MCC Telephony of the West LLC | Lake County Grant Build | Subcontract | Groundwater Service and Supply Inc | 3637040 | Clearlake CA | 3/31/2026 | 12/1/2026 | Yes | Amy Scanlon | Manager
March 2026 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Integrity Data & Fiber Inc. | 778249 | Pocket Rd, Greenhaven Dr, Valley Hi Dr, Center Pkwy | 3/1/2026 | 3/31/2026 | Yes | Pedro Sanchez | Telecommunications Engineer
March 2026 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Bear Electrical Solutions LLC | 982079 | Arena Blvd, Gateway Park Blvd, Howe Ave, Folsom Blvd, Florin Perkins, 65th Expwy, Fruitridge Rd, Franklin Blvd, Pocket Rd, Valley Hi Dr, Center Pkwy, 24th St, Heritage Ln, Bell Ave | 1/20/2026 | 6/19/2026 | Yes | Pedro Sanchez | Telecommunications Engineer
April 2026 |  | City of Sacramento | Sacramento Last Mile Connectivity Project | Contract | Pacific Excavation Inc. | 952071 | Franklin Blvd (47th to Florin Rd) | 4/1/2026 | 5/29/2026 | Yes | Pedro Sanchez | Telecommunications Engineer
June 2026 |  | Golden State Connect Authority | GSCA Glenn County Broadband Network | Contract | HP Communications | 752762 | Glenn County | 6/15/2026 | 12/26/2026 | Yes | Shayne Pope | OSP Construction Management Lead
June 2026 |  | Nevada County Fiber | Banner Mountain Area Community | Contract | BPS Underground Inc | 0985109 | Banner Mountain , Nevada City, CA 9595 | 6/1/2026 | 6/30/2027 | Yes | Andrew Wilkinson | CEO
Total | Count | 101