## Sheet1
SUMMARY OF IOU IRP RELIABILITY TRACK PROCUREMENT INFORMATION PROVIDED IN 2/18/2020 PUBLIC FILINGS
LSE NAME | MW | NEW IN-STATE RESOURCES | NEW DERs | IMPORTS | EXISTING/EXECUTED CONTRACTS NOT IN BASELINE | RFO STATUS
PGE | 765.11 | PG&E is preparing to issue its next System Reliability Solicitation on Feburary 28, 2020. PG&E will be seeking new and existing resources to provide system-level qualifying resource adequacy capacity beginning August 1, 2021. | PG&E plans to solicit offers for demand-side resources in future solicitations. Procurement of demand-side resources will be dependent on offers received and applicable evaluations. 100% of any demand-side resources procured would need to be dispatchable by the CAISO in order for PG&E to count it system Resource Adequacy. D.19-06-026 requires DR resources to receive QC values based on the application of the LIPs. | As part of the solicitation that will be released on February 28, 2020, PG&E will be seeking offers for imports. | PG&E is currently evaluating existing resources that may be eligible to meet the IRP procurement requirements. | PG&E issued the Distributed Generation Enabled Microgrid Services (DGEMS) Request for Offers on December 11, 2019, to procure energy resources that can serve customer demand in targeted locations during future Public Safety Power Shutoff (PSPS) events and meet IRP reliability procurement decision requirements. PG&E identified and requested offers for 20 substations, with a preference for projects that can be online by June 1, 2020 and no later than September 1, 2020. DGEMS Phase Schedule: RFO issuance: 12/11/19; Deadline to Submit Notice of Intent: 12/17/19; Deadline to Submit Offers: 01/17/20; Shortlist Notification: In Progress; Contract Negotiations: Will begin 02/20; PG&E Submits Executed Contracts for CPUC Approval: TBD
SDGE | 301.29 | SDG&E has not yet selected or contracted for any projects. At this time, SDG&E is focused on its RFO efforts and is currently in the bid evaluation process. | SDG&E expects to meet its requirement based on projects shortlisted in the RFO, or otherwise negotiated, which may include demand-side resources. At this time, SDG&E is focused on its RFO efforts and is currently in the bid evaluation process. | SDG&E expects to meet its requirement based on projects shortlisted in the RFO, or otherwise negotiated, which may include dynamically scheduled or pseudo-tied imports. At this time, SDG&E is focused on its RFO efforts and is currently in the bid evaluation process. | SDG&E expects to meet its requirement based on projects shortlisted in the RFO, or otherwise negotiated, which may include existing resources that bid into SDG&E solicitation. At this time, SDG&E is focused on its RFO efforts and is currently in the bid evaluation process. | SDG&E launched its IRP Procurement Track RFO on 12/13/19. RFO Schedule: Pre-Bid Conference, 01/10/20; Deadline for RFO bid submissions, 2/07/20; PRG Review of Shortlist, 4/24/20; Notifies Offerors of selection, 4/27/20; Shortlist acceptance/withdrawal, 5/04/20; Contract Execution, 8/03/20; Collateral Posted, 8/07/20; IOU files Tier 3 advice letter seeking CPUC approval, 8/31/20. SDG&E revised its schedule to expedite the process in response to a request by the Energy Division.
SCE | 1241.31 | FAST TRACK SHORT-LISTED PROJECTS - REDACTED. STANDARD TRACK SHORT-LISTED PROJECTS - REDACTED. | Redacted | Redacted | Redacted | SCE launched its System Reliability RFO (SRRFO) to meet its own procurement requirement and the requirements of "Opt Out" LSEs on September 19. 2019. The RFO is s open to all technology types, with a preference for preferred and energy storage resources located in Disadvantaged Communities, and is structurd with two tracks: a Fast Track for projects to come online by August 1, 2020, and a Standard Track for projects to come online by August 1, 2022 and August 1, 2023. On November 22, 2019, SCE received offers for the Fast Track and indicative offers for the Standard Track and initiated review of the offers. SCE developed shortlists of projects and presented them for review by its Procurement Review Group on December 19, 2019. SCE is currently negotiating with shortlisted Fast Track bidders and plans to execute contracts as soon as possible. Shortlisted bidders in the Standard Track will be given the opportunity to negotiate contracts and submit final offers for SCE evaluation and selection. FAST TRACK SCHEDULE - RFO Launch - 9/19/19, Offer Submittal - 11/22/19; Shortlisting Notification - 12/20/19, Contract Extension - Late February 2020, (In Progress ) STANDARD TRACK SCHEDULE - RFO Launch - 09/19/19, Offer Submittal (Indicative) - 11/22/19; Shortlisting Notification - 12/20/19; Offer Submittal (Final) - 03/31/20 ; Contract Extension - End of April 2020. -- SCE is also considering utility-owned resources. On September 20, 2019, SCE released an RFP for consideration of Reliability Utility-Owned ES Projects for three energy storage systems (ESS) to be located within existing SCE substations with a total capacity of 700 MW. RFP Release Date - 09/20/19, Bidder's Conference 09/26/19, SCE/Bidder Site Visits, 10/02/19, Bidder's Response to Terms and Conditions - 11/01/19, RFP Responses Due, 11/07/19, Shortlist Notification - 01/14/20, - Negotiations of Terms and Conditions - 02/28/20, In progress; Final Bids Due, 03/13/20, Award Project(s) (Binding Terms and Conditions and Pricing) - 04/30/20.
Total (incl opt-outs) | 2307.71