## Q2
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 2
Summary Tables by Line of Business | [6 empty] | Summary Tables by Line of Business
Utility | GRC General Line of Business | 2019 Actuals | 2019 Imputed Authorized | $ Variance | % Variance |  | Utility | GRC General Line of Business | 2019 Actuals | 2019 Imputed Authorized | $ Variance | % Variance
SoCalGas O&M | Gas Distribution (incl Gas Control) | 148480.1755 | 164476.6272 | -15996.4517 | -9.726% |  | SoCalGas Capital | Gas Distribution | 301933.9281 | 391406.461 | -89472.5329 | -22.86%
| Gas Engineering (incl TIMP/DIMP) | 140732.2156 | 123850.5919 | 16881.6237 | 13.63% |  |  | Gas Engineering | 239214.6341 | 253040.2395 | -13825.6054 | -5.464%
| Gas Transmission (incl GT, MP, GSI) | 49214.1387 | 73099.0839 | -23884.9451 | -32.67% |  |  | Gas Transmission | 231283.1635 | 250153.1515 | -18869.988 | -7.543%
| Underground Storage | 53082.6709 | 64365.0768 | -11282.4059 | -17.53% |  |  | Underground Storage | 135432.9203 | 194001.526 | -58568.6057 | -30.19%
| PSEP | 8900.1445 | 60582.4937 | -51682.3492 | -85.31% |  |  | PSEP | 66003.144 | 131027.025 | -65023.881 | -49.63%
| Gas Acquisition | 4687.1892 | 4603.6704 | 83.5188 | 1.814% |  |  | Sub-Total Gas | 973867.79 | 1219628.403 | -245760.613 | -20.15%
| Sub-Total Gas | 405096.5345 | 490977.5439 | -85881.0094 | -17.49% |  |  | Sub-Total Other | 140071.9285 | 147083.6217 | -7011.6932 | -4.767%
| Sub-Total Other | 408818.4027 | 438510.7853 | -29692.3826 | -6.771% |  |  | SoCalGas TOTAL Capital | 1113939.7185 | 1366712.0247 | -252772.3062 | -18.49%
| SoCalGas TOTAL O&M | 813914.9372 | 929488.3291 | -115573.3919 | -12.43%
Summary Tables by GRC Witness Area | [6 empty] | Summary Tables by GRC Witness Area
Utility | GRC Witness Areas | 2019 Actuals | 2019 Imputed Authorized | $ Variance | % Variance | 2019 RSAR Page Reference | Utility | GRC Witness Areas | 2019 Actuals | 2019 Imputed Authorized | $ Variance | % Variance | 2019 RSAR Page Reference
SoCalGas Non-Balanced O&M | Gas Distribution | 139780.1287 | 154806.7704 | -15026.6417 | -9.707% | B-2 | SoCalGas Non-Balanced Capital | Gas Distribution | 301933.9281 | 391406.461 | -89472.5329 | -22.86% | B-8
| Gas Control & System Operations/Planning | 8700.0469 | 9669.8568 | -969.8099 | -10.03% | B-17 |  | Gas Engineering | 11635.6341 | 9768.2395 | 1867.3946 | 19.12% | B-24
| Gas Major Projects | 1987.5404 | 4301.2753 | -2313.7349 | -53.79% | B-25 |  | Gas Major Projects | 346.9147 | 42673.391 | -42326.4763 | -99.19% | B-26
| Gas Engineering | 20495.1248 | 31109.9589 | -10614.8341 | -34.12% | B-19 |  | Gas Transmission | 230936.2488 | 207479.7605 | 23456.4883 | 11.31% | B-41
| Gas System Integrity | 14993.454 | 35582.2661 | -20588.8122 | -57.86% | B-28 |  | PSEP | 66003.144 | 131027.025 | -65023.881 | -49.63% | B-56
| Gas Acquisition | 4687.1892 | 4603.6704 | 83.5188 | 1.814% | B-58 |  | Underground Storage | 71314.9203 | 133599.526 | -62284.6057 | -46.62% | B-49
| Gas Transmission | 32233.1443 | 33215.5424 | -982.3981 | -2.958% | B-38 |  | Sub-Total Gas | 682170.79 | 915954.403 | -233783.613 | -25.52%
| PSEP | 8900.1445 | 60582.4937 | -51682.3492 | -85.31% | B-54 |  | Cyber Security | 18218.8648 | 25688.1315 | -7469.2667 | -29.08% | B-74
| Underground Storage | 39287.6709 | 44041.0768 | -4753.4059 | -10.79% | B-48 |  | Information Technology | 102285.1762 | 88675.9047 | 13609.2715 | 15.35% | B-73
| Sub-Total Gas | 271064.4436 | 377912.9109 | -106848.4672 | -28.27% |  |  | Facilities/Other | 19567.8874 | 32719.5855 | -13151.698 | -40.2% | B-81
| Accounting & Finance | 1064.0339 | 1253.8316 | -189.7977 | -15.14% | B-83 |  | Sub-Total Other | 140071.9285 | 147083.6217 | -7011.6932 | -4.767%
| Human Resources | 16454.0046 | 20888.7724 | -4434.7678 | -21.23% | B-86 |  | Sub-Total Non-Balanced Capital | 822242.7185 | 1063038.0247 | -240795.3062 | -22.65% | page 18 (pdf 23 of 240)
| Risk Management | 808.6174 | 315.0117 | 493.6057 | 156.7% | B-84 | SoCalGas Balanced Capital | Gas - TIMP & DIMP | 227579 | 243272 | -15693 | -6.451% | B-94
| Compensation & Benefits | 328.0702 | 777 | -448.9298 | -57.78% | B-83 |  | Gas - SIMP | 64118 | 60402 | 3716 | 6.152% | B-95
| Corporate Center - General Administration | 78715.056 | 63114 | 15601.056 | 24.72% | B-83 |  | Sub-Total Balanced Capital | 291697 | 303674 | -11977 | -3.944%
| Advanced Metering | 8974.6732 | 11244.6 | -2269.9268 | -20.19% | B-59 |  | TOTAL SoCalGas Capital | 1113939.7185 | 1366712.0247 | -252772.3062 | -18.49%
| CS - Field & Meter Reading | 180411.6511 | 187371.2861 | -6959.635 | -3.714% | B-60
| CS - Office Operations | 36590.0277 | 42144.6893 | -5554.6616 | -13.18% | B-63
| CS - Information | 19648.0614 | 24665.5396 | -5017.4782 | -20.34% | B-64
| CS - Technologies, Policies & Solutions | 3401.2503 | 5294.1346 | -1892.8843 | -35.75% | B-65
| Environmental | 4490.118 | 7562.4102 | -3072.2922 | -40.63% | B-77
| Cyber Security | 505.1583 | 763 | -257.8417 | -33.79% | B-71
| Information Technology | 21286.7297 | 31458.1299 | -10171.4003 | -32.33% | B-70
| Fleet & Facilities | 20552.8388 | 22745.3045 | -2192.4657 | -9.639% | B-78
| Supply Management & Supplier Diversity | 2445.1124 | 3518.0754 | -1072.963 | -30.5% | B-79
| Sub-Total Other | 395675.4027 | 423115.7853 | -27440.3826 | -6.485%
| Sub-Total Non-Balanced O&M | 666739.8463 | 801028.6961 | -134288.8498 | -16.76% | page 18 (pdf 23 of 240)
SoCalGas Balanced O&M | Gas - TIMP & DIMP | 120237.0909 | 92740.633 | 27496.4579 | 29.65% | B-89
| Gas - SIMP | 13795 | 20324 | -6529 | -32.12% | B-90
| Other - RD&D | 13143 | 15395 | -2252 | -14.63% | B-90
| Sub-Total Balanced O&M | 147175.0909 | 128459.633 | 18715.4579 | 14.57%
| TOTAL SoCalGas O&M | 813914.9372 | 929488.3291 | -115573.3919 | -12.43%

## Q3
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 3
High Level Summary Table - Excludes 'Other' Line of Business Costs
Utility | GRC Witness Areas | 2019 Actuals | 2019 Imputed Authorized | $ Variance | % Variance
SoCalGas | O&M Spend - Gas | 405096.5345 | 490977.5439 | -85881.0094 | -17.49%
| Capital Spend - Gas | 973867.79 | 1219628.403 | -245760.613 | -20.15%
| SoCalGas TOTAL | 1378964.3244 | 1710605.9469 | -331641.6224 | -19.39%

## GDO
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - O&M Variance Tables, Question 1
1.A. Gas Distribution
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas Distribution |  | 139780.1287 | 154806.7704 | -15026.6417 | -9.707% |  | Unless noted, units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Field Services Leadership & Operations Assessment | Non-RAMP | 392.1121 | 296.3675 | 95.7446 | 32.31% |  | 1 FTE | 1 FTE | 0 | 0%
Field Support | Non-RAMP | 13603.1691 | 13896.2247 | -293.0556 | -2.109% |  | 175 FTE
Field Support | Maintenance - Pipeline observation "Standby" (From Field Support) | 0 | 3580 | -3580 | -100% | Yes
Field Support | PPE and Safety Equipment | 0 | 21 | -21 | -100%
Field Support | Qualifications of Pipeline Personnel | 2707 | 2547 | 160 | 6.282% |  | 80,200 Hours
Field Support | Contractor Management and Traffic Control | 917 | 1587 | -670 | -42.22% |  |  | 15 FTE
Field Support | QA Job Observations Field Rides and Job Monitoring | 77 | 62 | 15 | 24.19% |  | 3,200 FACT Entries
Sub-Total Field Support |  | 17304.1691 | 21693.2247 | -4389.0556 | -20.23% | Yes
Leak Survey | Non-RAMP | 1196.4243 | 2641.908 | -1445.4837 | -54.71% | Yes
Leak Survey | Maintenance - Leak Survey | 8605 | 9138 | -533 | -5.833% |  | 31,784 Miles
Sub-Total Leak Survey |  | 9801.4243 | 11779.908 | -1978.4837 | -16.8%
Locate & Mark | Non-RAMP | 1611.0035 | 41 | 1570.0035 | 3829% | Yes
Locate & Mark | Locate & Mark Activities | 13882 | 15729 | -1847 | -11.74% |  | 462,231 USA Tickets | 400,222 USA Tickets | 62009 | 15.49%
Locate & Mark | QA Job Observations Field Rides and Job Monitoring | 2326 | 1696 | 630 | 37.15% |  | 2,935 Orders
Sub-Total Locate & Mark |  | 17819.0035 | 17466 | 353.0035 | 2.021%
Main Maintenance | Non-RAMP | 20636.5634 | 16717.2332 | 3919.3302 | 23.44% | Yes
Main Maintenance | Contracting for Traffic Control Delineation materials -- Distribution Only. Outside vendors | 827 | 1763 | -936 | -53.09%
Main Maintenance | Maintenance - Valve Inspection and Maintenance (From Field Support) | 945 | 888 | 57 | 6.419% |  | 6,644 Orders
Main Maintenance | High-Pressure Pipeline Failure, Project Maintenance - Valve Maintenance and Installation (Distribution High Pressure) (From Field Support) | 65 | 61 | 4 | 6.557% |  | 454 Orders
Main Maintenance | Maintenance - Pipeline Patrol (From Field Support) | 84 | 204 | -120 | -58.82% |  | 535 Orders
Main Maintenance | Maintenance - Bridge and Span (From Field Support) | 101 | 125 | -24 | -19.2% |  | 735 Orders
Main Maintenance | Maintenance - Unstable Earth Inspection (From Field Support) | 6 | 8 | -2 | -25% |  | 141 Orders
Sub-Total Main Maintenance |  | 22664.5634 | 19766.2332 | 2898.3302 | 14.66%
Service Maintenance | Non-RAMP | 11384.2389 | 17147.2945 | -5763.0556 | -33.61% | Yes
Tools Fittings & Materials | Non-RAMP | 11166.0792 | 8526.3238 | 2639.7554 | 30.96% | Yes
Tools Fittings & Materials | PPE and Safety Equipment - Company wide purchases of personal protective equipment (PPE) | 1560 | 714 | 846 | 118.5%
Tools Fittings & Materials | PPE and Safety Equipment - Uniform rentals for employees - both protective and for security | 551 | 1063 | -512 | -48.17%
Sub-Total Tools Fittings & Materials |  | 13277.0792 | 10303.3238 | 2973.7554 | 28.86% | Yes
Asset Management | Non-RAMP | 7515.2077 | 7578.361 | -63.1533 | -0.8333% |  | 74 FTE | 65 FTE | 9 | 13.85%
Measurement & Regulation | Non-RAMP | 12294.7157 | 14413.545 | -2118.8293 | -14.7%
Measurement & Regulation | Maintenance - Inspect meters, regulators, and gauges to evaluate and confirm overpressure protection is in place and maintained. | 1271 | 383 | 888 | 231.9% |  | 3,233 Orders
Measurement & Regulation | Maintenance - Maintenance and inspections of meter set assemblies (MSA) in the system. | 1492 | 1380 | 112 | 8.116% |  | 9,110 Orders
Sub-Total Measurement & Regulation |  | 15057.7157 | 16176.545 | -1118.8293 | -6.916%
Cathodic Protection | Non-RAMP | 1565.4262 | 1981.4801 | -416.0539 | -21%
Cathodic Protection | Requirements for Corrosion Control | 12921 | 16892 | -3971 | -23.51% | Yes | 44,957 Orders
Cathodic Protection | Gas Facility and Pipeline Inspections | 1005 | 953 | 52 | 5.456% |  | 8,991 Orders
Sub-Total Cathodic Protection |  | 15491.4262 | 19826.4801 | -4335.0539 | -21.86% | Yes
Operations And Management | Non-RAMP | 5151.7329 | 6976 | -1824.2671 | -26.15% | Yes
Operations And Management | Policy, Procedures, Standards and ESCMP | 0 | 996 | -996 | -100%
Sub-Total Operations And Management |  | 5151.7329 | 7972 | -2820.2671 | -35.38% | Yes
Regional Public Affairs | Non-RAMP | 3921.4557 | 4801.0326 | -879.5769 | -18.32% |  | 30 FTE | 33 FTE | -3 | -9.091%

## GC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - O&M Variance Tables, Question 1
1.B. Gas Control & System Operations
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas Control & System Operations - Planning |  | 8700.0469 | 9669.8568 | -969.8099 | -10.03% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Energy Markets & Capacity Products - Director | Non-RAMP | 0 | 340.1221 | -340.1221 | -100%
Energy Markets & Capacity Products - Support | Non-RAMP | 882.4872 | 667.3118 | 215.1754 | 32.25%
Energy Markets & Capacity Products - Manager | Non-RAMP | 876.1842 | 662.7855 | 213.3987 | 32.2%
Gas Scheduling | Non-RAMP | 821.448 | 780.4703 | 40.9777 | 5.25%
Gas Control & SCADA Operation Group - USS | Non-RAMP | 0.49536 | 13.6239 | -13.1286 | -96.36%
Gas Control & SCADA Operation Group - USS | Fatigue Management | 385 | 463 | -78 | -16.85%
Gas Control & SCADA Operation Group - USS | Operation | 0 | 2 | -2 | -100%
Gas Control & SCADA Operation Group - USS | Gas Control Operation | 2032 | 1741 | 291 | 16.71%
Gas Control & SCADA Operation Group - USS | Catastrophic Damage / Cyber Security | 1071 | 1036 | 35 | 3.378%
Sub-Total Gas Control & SCADA Operation Group - USS |  | 3488.4954 | 3255.6239 | 232.8714 | 7.153%
Gas Transmission Planning | Non-RAMP | 709.9858 | 745.2296 | -35.2438 | -4.729%
Storage Products Manager | Non-RAMP | 170.4462 | 170.3135 | 0.13273 | 0.07793%
Emergency Services | Non-RAMP | 0 | 127 | -127 | -100%
Emergency Services | Safety, Wellness and Emergency Services Support | 1751 | 2921 | -1170 | -40.05% | Yes
Sub-Total Emergency Services |  | 1751 | 3048 | -1297 | -42.55% | Yes

## GE
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - O&M Variance Tables, Question 1
1.C. Gas Engineering
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas Engineering |  | 20495.1248 | 31109.9589 | -10614.8341 | -34.12% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Dir Eng & Tech Services | Non-RAMP | 505.4757 | 546.2127 | -40.737 | -7.458%
Dir Eng & Tech Services | Information Management Systems |  | 325 | -325 | -100%
Sub-Total Dir Eng & Tech Service |  | 505.4757 | 871.2127 | -365.737 | -41.98%
MRC Management & Special Projects | Non-RAMP | 225.3097 | 967.4513 | -742.1416 | -76.71%
Measurement & Design | Non-RAMP | 507.7803 | 1255.1972 | -747.4169 | -59.55%
Measurement Technologies | Non-RAMP | 955.2152 | 1379.5638 | -424.3485 | -30.76%
Measurement Field Support | Non-RAMP | 829.7115 | 1347.6639 | -517.9523 | -38.43%
Engineering Design Management Process Engineering & Design | Non-RAMP | 974.6064 | 2004.4005 | -1029.7941 | -51.38% | Yes, at the WP
Engineering Design Management Process Engineering & Design | Information Management Systems | 105 | 237 | -132 | -55.7%
Sub-Total Engineering Design Management Process Engineering & Design |  | 1079.6064 | 2241.4005 | -1161.7941 | -51.83% | Yes
Pipeline Materials | Non-RAMP | 715.6139 | 428.6013 | 287.0126 | 66.96%
Mechanical Design | Non-RAMP | 108.4311 | 193.5549 | -85.1238 | -43.98%
Pipeline Engineering | Non-RAMP | 472.4522 | 723.8911 | -251.4389 | -34.73%
Research, Planning & Development | Non-RAMP | 1.8331 | 43.2158 | -41.3827 | -95.76%
MRC - Intrumentation Repair and Field Support | Non-RAMP | 441.3842 | 1428.168 | -986.7838 | -69.09%
Engineering Analysis Center - Chemical Lab | Non-RAMP | 1966.1391 | 2218.9843 | -252.8452 | -11.39%
MRC Standards | Non-RAMP | 135.2529 | 786.721 | -651.4681 | -82.81%
High Pressure & Distribution Engineering | Non-RAMP | 617.1297 | 1230.8412 | -613.7115 | -49.86%
Electrical Design | Non-RAMP | 136.4042 | 166.2891 | -29.8849 | -17.97%
Gas Engineering Analysis Center, NGV and Electrical Field | Non-RAMP | 6451.9228 | 6597.2655 | -145.3427 | -2.203%
Land Services & Right Of Way | Non-RAMP | 2899.7861 | 3900.1459 | -1000.3598 | -25.65% | Yes
Civil Structural & Hazard Mitigation Engineering | Non-RAMP | 333.0141 | 1070.6013 | -737.5872 | -68.89%
Civil Structural & Hazard Mitigation Engineering | Monitoring of Land Movement & Flood zones | 238 | 1176 | -938 | -79.76%
Civil Structural & Hazard Mitigation Engineering | Gas Infrastructure Resilience & Vulnerability Report | 149 | 349 | -200 | -57.31%
Civil Structural & Hazard Mitigation Engineering | Real time monitoring of land movement via stress acting on infrastructure | 1 | 107 | -106 | -99.07%
Sub-Total Civil Structural & Hazard Mitigation Engineering |  | 721.0141 | 2702.6013 | -1981.5872 | -73.32% | Yes
Meter Shop & Records |  | 1724.6626 | 2627.1903 | -902.5277 | -34.35%

## MPO
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - O&M Variance Tables, Question 1
1.D. Gas Major Projects
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Major Projects |  | 1987.5404 | 4301.2753 | -2313.7349 | -53.79% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Major Projects Management & Outreach | Non-RAMP | 661 | 2433.7514 | -1772.7514 | -72.84% | Yes, at the total WP
Major Projects Management & Outreach | Real-time pressure data and providing remote control to high priority distribution sites. | 95 | 1516 | -1421 | -93.73% | Yes, at the total WP
Sub-Total Major Projects Management & Outreach |  | 756 | 3949.7514 | -3193.7514 | -80.86% | Yes
Project & Construction Management | Non-RAMP | 513.3096 | 216.8677 | 296.4419 | 136.7%
Project Controls And Estimating | Non-RAMP | 718.2308 | 134.6562 | 583.5746 | 433.4%

## GSI
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - O&M Variance Tables, Question 1
1.E. Gas System Integrity
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas System Integrity |  | 14993.454 | 35582.2661 | -20588.8122 | -57.86% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
USS - VP Gas System Integrity | Non-RAMP | 0.02939 | 677.6578 | -677.6284 | -100%
Business Process ESS Implementation and ESS Mobile Solution | Non-RAMP | 1038.386 | 206.3576 | 832.0284 | 403.2%
Business Process ESS Implementation and ESS Mobile Solution | Information Management System | 110 | 119 | -9 | -7.563%
Sub-Total Business Process ESS Implementation and ESS Mobile Solution |  | 1148.386 | 325.3576 | 823.0284 | 253%
Applications | Non-RAMP | 0.38408 | 515.3561 | -514.9721 | -99.93%
ESS Production Support | Non-RAMP | 69.45 | 610.1793 | -540.7293 | -88.62%
ESS Production Support | Information Management Systems | 0 | 108 | -108 | -100%
Sub-Total ESS Production Support |  | 69.45 | 718.1793 | -648.7293 | -90.33%
Wrk Mgmt & Databases | Non-RAMP | 794.8151 | 1786.1511 | -991.336 | -55.5%
Wrk Mgmt & Databases | Operational Compliance and Oversight | 293 | 216 | 77 | 35.65%
Sub-Total Wrk Mgmt & Databases |  | 1087.8151 | 2002.1511 | -914.336 | -45.67%
Contract & Maintenance | Non-RAMP | 617.3124 | 602.5421 | 14.7703 | 2.451%
Field Technologies | Non-RAMP | 222.033 | 447.6766 | -225.6436 | -50.4%
Gas System Integrity Staff &Programs | Non-RAMP | 109.3747 | 344.7562 | -235.3815 | -68.27%
Operator Qualification | Non-RAMP | 927.1945 | 1247.7782 | -320.5837 | -25.69%
Operator Qualification | Operations | 750 | 856 | -106 | -12.38%
Sub-Total Operator Qualification |  | 1677.1945 | 2103.7782 | -426.5837 | -20.28%
Pipeline System Construction Policy | Locate & Mark Activities | 0 | 932 | -932 | -100%
Pipeline System Construction Policy | Locate & Mark Activities | 0 | 270 | -270 | -100%
Pipeline System Construction Policy | Locate & Mark Activities | 0 | 120 | -120 | -100%
Pipeline System Construction Policy | Policy Procedures Standards and ESCMP | 771 | 668 | 103 | 15.42%
Sub-Total Pipeline System Construction Policy |  | 771 | 1990 | -1219 | -61.26% | Yes
Quality & Risk | Non-RAMP | 418.5832 | 969.2977 | -550.7145 | -56.82%
Quality & Risk | Operational Compliance and Oversight | 0 | 340 | -340 | -100%
Sub-Total Quality & Risk |  | 418.5832 | 1309.2977 | -890.7145 | -68.03%
Enterprise Geographic Information System (eGIS) | Non-RAMP | 756.85 | 2126.0448 | -1369.1948 | -64.4% | Yes
Enterprise Geographic Information System (eGIS) | Operational Compliance and Oversight | 0 | 625 | -625 | -100%
Sub-Total Enterprise Geographic Information System (eGIS) |  | 756.85 | 2751.0448 | -1994.1948 | -72.49% | Yes
Shared Public Awareness Activities | Non-RAMP | 0 | -303.0596 | 303.0596 | -100%
Shared Public Awareness Activities | Analysis | 146.2945 | 882 | -735.7055 | -83.41%
Sub-Total Shared Public Awareness Activities |  | 146.2945 | 578.9404 | -432.6459 | -74.73%
Pipeline Safety & Compliance Manager | Non-RAMP | 678.2117 | 919.6014 | -241.3897 | -26.25%
Pipeline Safety Oversight | Non-RAMP | 599.0046 | 617.3066 | -18.302 | -2.965%
Records Management - From 2200-2361 | Operational Compliance and Oversight | 0 | 1778 | -1778 | -100% | Yes
Records Management - From 2200-2361 | Policy Procedures Standards and ESCMP | 0 | 970 | -970 | -100%
Sub-Total Records Management - From 2200-2361 |  | 0 | 2748 | -2748 | -100% | Yes
Gas Operations Training & Development | Non-RAMP | 315 | 1592 | -1277 | -80.21% | Yes
Gas Operations Training & Development | Qualification of Pipeline Personnel | 108 | 1050 | -942 | -89.71%
Gas Operations Training & Development | Qualifications of Pipeline Personnel | 540 | 664 | -124 | -18.67%
Gas Operations Training & Development | Qualifications of Pipeline Personnel | 158 | 267 | -109 | -40.82%
Gas Operations Training & Development | Qualifications of Pipeline Personnel | 117 | 323 | -206 | -63.78%
Gas Operations Training & Development | Qualifications of Pipeline Personnel | 108 | 99 | 9 | 9.091%
Gas Operations Training & Development | Expand “Situation City” training props at Pico Rivera campus | 0 | 250 | -250 | -100%
Gas Operations Training & Development | Qualifications of Pipeline Personnel | 154 | 99 | 55 | 55.56%
Gas Operations Training & Development | Qualifications of Pipeline Personnel | 4 | 5 | -1 | -20%
Gas Operations Training & Development | Qualifications of Pipeline Personnel | 17 | 15 | 2 | 13.33%
Gas Operations Training & Development | Employee Skills Training | 100 | 597 | -497 | -83.25%
Gas Operations Training & Development | Locate & Mark Training | 73 | 152 | -79 | -51.97%
Sub-Total Gas Operations Training & Development |  | 1694 | 5113 | -3419 | -66.87% | Yes
Pipeline Safety & Compliance | Non-RAMP | 139.3173 | 399.6988 | -260.3815 | -65.14%
Pipeline Safety & Compliance | Operational Compliance and Oversight | 0 | 120 | -120 | -100%
Pipeline Safety & Compliance | Operational Compliance and Oversight | 250 | 354 | -104 | -29.38%
Pipeline Safety & Compliance | Operational Compliance and Oversight | 884 | 938 | -54 | -5.757%
Pipeline Safety & Compliance | Operational Compliance and Oversight | 1230 | 1335 | -105 | -7.865%
Sub-Total Pipeline Safety & Compliance |  | 2503.3173 | 3146.6988 | -643.3815 | -20.45%
Public Awareness | Non-RAMP | 493.2136 | 303.5277 | 189.6859 | 62.49%
Public Awareness | Public Awareness | 0 | 1498 | -1498 | -100% | Yes
Sub-Total Public Awareness |  | 493.2136 | 1801.5277 | -1308.3141 | -72.62% | Yes
Asset Management | Non-RAMP | 2001 | 2386.3938 | -385.3938 | -16.15%
Asset Management | Operational Compliance and Oversight | 0 | 110 | -110 | -100%
Asset Management | Operational Compliance and Oversight | 0 | 226 | -226 | -100%
Sub-Total Asset Management |  | 2001 | 2722.3938 | -721.3938 | -26.5%
Gas Contractor Controls | Contractor Management and Traffic Control | 0 | 4147 | -4147 | -100% | Yes

## GTO
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - O&M Variance Tables, Question 1
1.F. Gas Transmission
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas Transmission |  | 32233.1443 | 33215.5424 | -982.3981 | -2.958% |  | Units are not available for this witness area because there is no single number of like units that would be comparable year over year.
Director Gas Transmission - USS | Non-RAMP | 246.0111 | 258.1091 | -12.0981 | -4.687%
Field Operations Managers - USS | Non-RAMP | 306.8138 | 451.6641 | -144.8503 | -32.07%
Technical Services Manager - USS | Non-RAMP | 299.3327 | 384.4156 | -85.0829 | -22.13%
Pipeline Operations | Non-RAMP | 1353.778 | 10770.5339 | -9416.7559 | -87.43% | Yes
Pipeline Operations | Maintenance - Valve, Meters, Pipe, PLS, Regulators, etc. | 13132 | 4354 | 8778 | 201.6% | Yes
Pipeline Operations | Corrosion Control Operation - Cathodic Protection | 1387 | 271 | 1116 | 411.8% | Yes
Pipeline Operations | Odorization of Natural Gas | 570 | 108 | 462 | 427.8%
Pipeline Operations | Training and Qualification Of Personnel | 44 | 188 | -144 | -76.6%
Sub-Total Pipeline Operations |  | 16486.778 | 15691.5339 | 795.2441 | 5.068%
Compressor Station Operations | Non-RAMP | 9960.2156 | 10799.2325 | -839.0169 | -7.769%
Technical Services | Non-RAMP | 318.9931 | 587.5872 | -268.5941 | -45.71%
Technical Services | Class Location (Hydrotest) - Incremental | 0 | 1439 | -1439 | -100% | Yes
Technical Services | Right of Way - Maintenance of access roads | 1527 | 0 | 1527 | 100% | Yes
Technical Services | Utility Conflict Review, Ops Emergency Preparedness & QA/QC | 587 | 1319 | -732 | -55.5%
Technical Services | Right of Way - Routine | 2501 | 1500 | 1001 | 66.73% | Yes
Technical Services | HCA Class Location Operation | 0 | 785 | -785 | -100%
Sub-Total Technical Services |  | 4933.9931 | 5630.5872 | -696.5941 | -12.37%

## UGSO
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - O&M Variance Tables, Question 1
1.G. Underground Storage
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Underground Storage |  | 39287.6709 | 44041.0768 | -4753.4059 | -10.79% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Underground Storage | Non-RAMP | 32237.3697 | 32408.4555 | -171.0858 | -0.5279%
Underground Storage | Maintenance work performed on gas storage wells | 1195 | 4442 | -3247 | -73.1% | Yes
Underground Storage | Contract Security | 203 | 1407 | -1204 | -85.57% | Yes
Underground Storage | Maintenance of high-pressure storage lines | 3692 | 2973 | 719 | 24.18%
Underground Storage | Internal Corrosion Plan | 255 | 599 | -344 | -57.43%
Sub-Total Underground Storage |  | 37582.3697 | 41829.4555 | -4247.0858 | -10.15%
Storage Risk Management | Non-RAMP | 1705.3012 | 2211.6213 | -506.3201 | -22.89%

## PSEP
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - O&M Variance Tables, Question 1
1.H. PSEP
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Pipeline Safety Enhancement Plan |  | 8900.1445 | 60582.4937 | -51682.3492 | -85.31% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Pipeline Safety Enhancement Program | Approved PSEP program to test or replace High Consequence Area High Pressure pipelines | 2873.9647 | 56325.4937 | -53451.529 | -94.9% | Yes
Pipeline Safety Enhancement Program-PMO Costs | Approved PSEP program to test or replace High Consequence Area High Pressure pipelines | 6026.1798 | 4257 | 1769.1798 | 41.56% | Yes

## GAq
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - O&M Variance Tables, Question 1
1.I. Gas Acquisition
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas Procurement |  | 4687.1892 | 4603.6704 | 83.5188 | 1.814% |  | Units unavailable because this work paper does not have a single number of like units that would be comparable year over year.
Gas Acquisition | Non-RAMP | 4687.1892 | 4603.6704 | 83.5188 | 1.814%

## CS
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - O&M Variance Tables, Question 1
3.A. Customer Services
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Customer Services 2 |  | 249025.6635 | 270720.2496 | -21694.586 | -8.014%
Advance Metering Infrastructure Policy |  | 8974.6732 | 11244.6 | -2269.9268 | -20.19%
Advanced Meter Operations | Non-RAMP | 8420.6732 | 10747.6 | -2326.9268 | -21.65% | Yes | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Advanced Meter Operations | Damaged or down poles may create an unsafe condition. Inspect annually and repair as needed. | 397 | 298 | 99 | 33.22% |  | 4,404 Inspections | 4,600 Inspections | -196 | -4.261%
Advanced Meter Operations | Analyze consumption patterns to identify atypical/unusual consumption | 157 | 199 | -42 | -21.11% |  | 32,900 Accounts | 21,312 Accounts | 11588 | 54.37% | Yes
Sub-Total Advanced Meter Operations |  | 8974.6732 | 11244.6 | -2269.9268 | -20.19% | Yes
Customer Services - Field & Meter Reading |  | 180411.6511 | 187371.2861 | -6959.635 | -3.714%
CS Field Staff Manager | Non-RAMP | 477.5727 | 523.3612 | -45.7885 | -8.749%
CS Field Staff Manager | Policy Procedures Standards and ESCMP | 803 | 938 | -135 | -14.39%
Sub-Total CS Field Staff Manager |  | 1280.5727 | 1461.3612 | -180.7885 | -12.37% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Customer Services Field - Operations | Non-RAMP | 74552.1878 | 79155.9171 | -4603.7293 | -5.816% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Customer Services Field - Operations | Safety-related field Orders, Field Employee meetings and Training | 40462 | 39888 | 574 | 1.439% |  | 805,237 Safety-related field orders | 843,077 Safety-related field orders | -37840 | -4.488%
Customer Services Field - Operations | PPE and Tools | 3237 | 3364 | -127 | -3.775% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Sub-Total CS Field - Operations |  | 118251.1878 | 122407.9171 | -4156.7293 | -3.396%
Customer Services Field - Supervision | Non-RAMP | 12087.1354 | 11102.0354 | 985.0999 | 8.873%
Customer Services Field - Supervision | Job Observations Field Rides and Job Monitoring | 780 | 951 | -171 | -17.98%
Sub-Total CS Field- Supervision |  | 12867.1354 | 12053.0354 | 814.0999 | 6.754% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Customer Services Field - Dispatch | Non-RAMP | 12699.119 | 9464.8631 | 3234.2559 | 34.17% | Yes | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Customer Services Field - Support | Non-RAMP | 11203.3706 | 15160.4439 | -3957.0733 | -26.1% | Yes
Customer Services Field - Support | EmployeeSkills Training and QA inspections | 3661 | 3787 | -126 | -3.327%
Sub-Total CS Field- Support |  | 14864.3706 | 18947.4439 | -4083.0733 | -21.55% | Yes | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
MSA Inspection Program | Non-RAMP | 4004.1108 | 7052.1033 | -3047.9925 | -43.22% | Yes | 72,206 Remediation Orders | 166,509 Remediation Orders | -94303 | 56.64%
MSA Inspection Program | Gas Facility and Pipeline Inspections | 14578 | 12687 | 1891 | 14.91% |  | 2,365,887 MSA Inspections | 2,292,132 MSA Inspections | 73755 | 3.218%
Sub-Total MSA Inspection Program |  | 18582.1108 | 19739.1033 | -1156.9925 | -5.861%
Meter Reading - Operations | Non-RAMP | 702.9484 | 1191.6327 | -488.6843 | -41.01% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Meter Reading - Operations | PPE and Safety Equipment and Gas Facility and Pipeline inspections | 702 | 1226 | -524 | -42.74% |  | 242,278 Manual Meter Reads | 335,744 Manual Meter Reads | -93466 | -27.84% | Yes
Sub-Total Meter Reading - Operations |  | 1404.9484 | 2417.6327 | -1012.6843 | -41.89% | Yes
Meter Reading - Clerical | Non-RAMP | 179.932 | 161.287 | 18.6449 | 11.56% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Meter Reading - Supervision & Training | Non-RAMP | 3.7281 | 386.5323 | -382.8042 | -99.04% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Meter Reading - Support | Non-RAMP | 278.5464 | 332.1101 | -53.5637 | -16.13% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Customer Services - Office Operations |  | 36590.0277 | 42144.6893 | -5554.6616 | -13.18%
CCC - Operations | Non-RAMP | 26955.7874 | 29793.1774 | -2837.39 | -9.524% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
CCC - Operations | Update customer information for access purposes | 702 | 1579 | -877 | -55.54% |  | 4,365,076 Call Volume | 4,908,129 Call Volume | -543053 | -11.06%
CCC - Operations | CSR Training, Quality Observations, CCC Safety Committee Liaison | 264 | 247 | 17 | 6.883% |  | 4,065 Hours | 4,524 Hours | -459 | -10.15%
CCC - Operations | Emergency Call Handling | 756 | 932 | -176 | -18.88% |  | 278,190 Call Volume | 346,767 Call Volume | -68577 | -19.78% | Yes
Sub-Total CCC - Operations |  | 28677.7874 | 32551.1774 | -3873.39 | -11.9%
CCC - Support | Non-RAMP | 7912.2402 | 9593.5119 | -1681.2717 | -17.53% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Customer Services - Information |  | 19648.0614 | 24665.5396 | -5017.4782 | -20.34%
Renewable Gas - Customer Outreach | Non-RAMP | 422.9612 | 1028.2336 | -605.2723 | -58.87% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Clean Transportation - Customer Outreach | Non-RAMP | 1183.9052 | 1463.4088 | -279.5036 | -19.1% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
CI-Customer Strategy and Engagement - | Non-RAMP | 5864.6057 | 7652.0262 | -1787.4205 | -23.36% | Yes | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
CI-Customer Assistance Programs | Non-RAMP | 671.0338 | 761.3835 | -90.3497 | -11.87% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
CI-Customer Assistance Programs | Natural Gas Appliance Testing (NGAT) 1 | 2106 | 2923 | -817 | -27.95% |  | 69,751 NGATs | 103,084 NGATs | -33333 | -32.34% | Yes
Sub-Total CI-Customer Assistance Programs |  | 2777.0338 | 3684.3835 | -907.3497 | -24.63%
CI-Customer Segment Services | Non-RAMP | 9399.5555 | 10837.4875 | -1437.932 | -13.27% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Customer Services - Technologies, Policies & Solutions |  | 3401.2503 | 5294.1346 | -1892.8843 | -35.75% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Business Strategy and Development | Non-RAMP | 898.8446 | 1616.1189 | -717.2743 | -44.38%
Environmental Affairs | Non-RAMP | 511.6444 | 697.3797 | -185.7353 | -26.63%
Energy & Environmental Policy | Non-RAMP | 832.4523 | 1768.1824 | -935.7301 | -52.92%
Planning & Legislative Analysis | Non-RAMP | 220.6253 | 237.5251 | -16.8998 | -7.115%
Policy & Environmental Solutions NSS | Non-RAMP | 937.6837 | 974.9285 | -37.2448 | -3.82%
1 These NGAT numbers are preliminary and subject to change in the final ESA Program annual report expected to be filed May 1, 2020.
2 The Customer Services Total reported in the RSAR on page B-59 in advertantly included the Balanced RD&D Program reported on page B-90. The non-balanced totals are correctly reported here.

## IT & CyO
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - O&M Variance Tables, Question 1
3.B. Information Technology & Cyber Security
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Information Technology & Cyber Security |  | 21791.888 | 32221.1299 | -10429.242 | -32.37%
Information Technology |  | 21286.7297 | 31458.1299 | -10171.4003 | -32.33%
Director IT SoCalGas Applications | Non-RAMP | 563.7904 | 775.4052 | -211.6147 | -27.29% |  | 5 FTE | 2 FTE | 3 | 150%
Director - Computing Infrastructure | Non-RAMP | 178.0723 | 0 | 178.0723 | 0% |  | 1 FTE | 1 FTE | 0 | 0%
SCG Work Management Services | Non-RAMP | 1181.1148 | 1306.7113 | -125.5965 | -9.612% |  | 6 FTE | 11 FTE | -5 | -45.45%
SCG GIS & CAD Services | Non-RAMP | 312.1864 | 184.5022 | 127.6841 | 69.2% |  | 3 FTE | 1 FTE | 2 | 200%
SCG Software Dev - Database | Non-RAMP | 168.667 | 616.0133 | -447.3463 | -72.62% |  | 1 FTE | 4 FTE | -3 | -75%
SCG Apps Maj Mrk App - SCG | Non-RAMP | 1719.4687 | 1561.8028 | 157.6659 | 10.1% |  | 10 FTE | 8 FTE | 2 | 25%
Scalable Platform Servs - SCG | Non-RAMP | 257.6272 | 514.8173 | -257.1901 | -49.96% |  | 1 FTE | 2 FTE | -1 | -50%
CI Compute Support SCG | Non-RAMP | 1807.7075 | 1119.7303 | 687.9772 | 61.44% |  | 9 FTE | 9 FTE | 0 | 0%
CI Compute Provisioning SCG | Non-RAMP | 61.97 | 687.6804 | -625.7104 | -90.99% |  | 0 FTE | 5 FTE | -4 | -80%
CI Standards | Non-RAMP | 566.5767 | 551.1358 | 15.4409 | 2.802% |  | 4 FTE | 5 FTE | -1 | -20%
IT Portfolio Management | Non-RAMP | 415.4234 | 650.1764 | -234.753 | -36.11% |  | 2 FTE | 2 FTE | 0.6 | 50%
Architecture and Integration - SCG | Non-RAMP | 560.141 | 568.8101 | -8.6691 | -1.524% |  | 3 FTE | 3 FTE | 0 | 0%
IT Telecom PMO | Non-RAMP | 79.0306 | 101.0883 | -22.0577 | -21.82% |  | 0 FTE | 1 FTE | -1 | -100%
IT Applications NSS | Non-RAMP | 5795.5468 | 8580.7903 | -2785.2435 | -32.46% | Yes | 24 FTE | 30 FTE | -6 | -20%
IT Infrastructure NSS | Non-RAMP | 7619.4069 | 14239.4664 | -6620.0594 | -46.49% | Yes | 10 FTE | 36 FTE | -26 | -72.22%
Cyber Security |  | 505.1583 | 763 | -257.8417 | -33.79%
IT Information Security SCG | Firewall Admin | 505.1583 | 763 | -257.8417 | -33.79% |  | 1 FTE | 1 FTE | 0 | 0%

## SSO
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - O&M Variance Tables, Question 1
2.C. Support Services
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Support Services |  | 25042.9568 | 30307.7147 | -5264.7579 | -17.37%
Environmental |  | 4490.118 | 7562.4102 | -3072.2922 | -40.63%
Environmental | Non-RAMP | 2023.118 | 4804.4102 | -2781.2922 | -57.89% | Yes |  |  | 0 | 0%
Environmental | Environmental Services and Safety Compliance Management Program (ESCMP) | 85 | 109 | -24 | -22.02% |  | 2 FTE | 2 FTE | 0 | 0%
Environmental | Environmental Self-Assessment | 532 | 469 | 63 | 13.43% |  | 102 Self-Assessments | 121 Self-Assessments | -19 | -15.7%
Environmental | Investigation of environmental exposure incidents | 539 | 474 | 65 | 13.71% |  | 328 Agency Inspections | 245 Agency Inspections | 83 | 33.88% | Yes
Environmental | Compliance program to comply with the Safe Drinking Water and Toxic Enforcement Act of 1986 (Proposition 65) | 2 | 18 | -16 | -88.89%
Environmental | Service Contracting | 0 | 176 | -176 | -100%
Environmental | Asbestos Safety Program | 560 | 770 | -210 | -27.27% |  | 6 FT | 9 FTE | -3 | -33.33% | Yes
Environmental | SoCalGas Environmental Training | 749 | 742 | 7 | 0.9434% |  | 3,545 Attendees | 3,797 Attendees | -252 | -6.637%
Sub-Total Environmental |  | 4490.118 | 7562.4102 | -3072.2922 | -40.63% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Fleet Services & Facilities |  | 20552.8388 | 22745.3045 | -2192.4657 | -9.639%
Facilities-Monterey Park Mgr | Non-RAMP | 1992.9072 | 2513.3042 | -520.397 | -20.71% |  | 5 FTE | 7 FTE | -2 | -28.57%
Facilities GCT | Non-RAMP | 1345.4364 | 1630.5601 | -285.1237 | -17.49% |  | 11 FTE | 10 FTE | 1 | 10%
Director | Non-RAMP | 82.2014 | 124.7561 | -42.5547 | -34.11% |  | 1 FTE | 1 FTE | 0 | 0%
Facility Operations | Non-RAMP | 16569.2938 | 17368.6841 | -799.3903 | -4.602% |  | 51 FTE | 47 FTE | 4 | 8.511%
Facility Operations | New Contract Security | 199 | 233 | -34 | -14.59%
Facility Operations | Physical Security | 351 | 17 | 334 | 1965%
Facility Operations | Site Security Reviews | 13 | 12 | 1 | 8.333%
Facility Operations | Additional Security Guards | 0 | 846 | -846 | -100%
Sub-Total Facility Operations |  | 17132.2938 | 18476.6841 | -1344.3903 | -7.276% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Supply Management, Logistics & Supplier Diversity |  | 2445.1124 | 3518.0754 | -1072.963 | -30.5% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Fabrication & Repair | Non-RAMP | 2445.1124 | 3518.0754 | -1072.963 | -30.5%

## A&G
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - O&M Variance Tables, Question 1
2.D. Administrative & General
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Administrative & General |  | 80915.7775 | 65459.8433 | 15455.9341 | 23.61%
Accounting & Finance, Legal, Regulatory Affairs, External Affairs |  | 1064.0339 | 1253.8316 | -189.7977 | -15.14%
Accounting Systems & Compliance | Non-RAMP | 1064.0339 | 316.8316 | 747.2023 | 235.8% |  | 7 FTE | 7 FTE | 0 | 0%
Accounting Systems & Compliance | Consulting expertise to improve records management program | 0 | 937 | -937 | -100% |  | 1 FTE | 1 FTE | 0 | 0%
Sub-Total Accounting Systems & Compliance |  | 1064.0339 | 1253.8316 | -189.7977 | -15.14%
Compensation & Benefits |  | 328.0702 | 777 | -448.9298 | -57.78% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Health Benefits - Emp Assistance Program | Non-RAMP | 328.0702 | 777 | -448.9298 | -57.78%
Corporate Center - General Administration |  | 78715.056 | 63114 | 15601.056 | 24.72% | Yes | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
SECC Outside Services Employees - F923.1 | Non-RAMP | 75323.056 | 58553 | 16770.056 | 28.64% | Yes
SECC Outside Services Employees - F923.1 | Records Management | 118 | 118 | 0 | 0%
SECC Outside Services Employees - F923.1 | Workplace Violence/Corporate Security | 2601 | 2127 | 474 | 22.28%
SECC Outside Services Employees - F923.1 | Cybersecurity | 673 | 2316 | -1643 | -70.94%
Sub-Total Secc Outside Services Employes - F923.1 |  | 78715.056 | 63114 | 15601.056 | 24.72% | Yes
Risk Management |  | 808.6174 | 315.0117 | 493.6057 | 156.7%
Director of Risk | Non-RAMP | 95.908 | 0 | 95.908 | 100% |  | 1 FTE | 0 FTE | 1 | 100%
Chief Risk Officer | Non-RAMP | 384.8499 | 0 | 384.8499 | 100% |  | 1 FTE | 0 FTE | 1 | 100%
Oper Risk Mgmt-Scg | Non-RAMP | 327.8594 | 315.0117 | 12.8477 | 4.078% |  | 2 FTE | 2 FTE | 0 | 0%

## HR
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - O&M Variance Tables, Question 1
2.E. Human Resources Dept, Safety, LTD & WC
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Human Resources Dept, Safety, LTD & WC |  | 16454.0046 | 20888.7724 | -4434.7678 | -21.23% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
SCG CEO President & COO and Chief of Human Resources & CAO | Non-RAMP | 2272.3229 | 1770 | 502.3229 | 28.38%
SCG Director HR Services | Non-RAMP | 5571.1966 | 3077.4148 | 2493.7818 | 81.03% | Yes
SCG Director HR Services | Workforce Planning - Software/Program Implementation. | 114 | 2599 | -2485 | -95.61% | Yes
Sub-Total SCG Director HR Services |  | 5685.1966 | 5676.4148 | 8.7818 | 0.1547%
SCG Director Safety & Wellness | Non-RAMP | 5163.8574 | 595.6879 | 4568.1695 | 766.9% | Yes
SCG Director Safety & Wellness | HR sponsored employee contractor customer & public safety activities. | 514 | 8698 | -8184 | -94.09% | Yes
Sub-Total SCG Director Safety & Wellness |  | 5677.8574 | 9293.6879 | -3615.8305 | -38.91% | Yes
SCG Director Org Effectiveness | Non-RAMP | 2365.6277 | 1715.6697 | 649.958 | 37.88%
SCG Director Org Effectiveness | Knowledge Management and Training Strategy | 453 | 2433 | -1980 | -81.38% | Yes
Sub-Total SCG Director Org Effectiveness |  | 2818.6277 | 4148.6697 | -1330.042 | -32.06% | Yes

## BalProgO
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - O&M Variance Tables, Question 1
3.A. Balanced Program Direct O&M Expenses
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
TIMP & DIMP |  | 120237.0909 | 92740.633 | 27496.4579 | 29.65%
TIMP Project Support | TIMP Data Maintenance | 905 | 1777.1273 | -872.1273 | -49.08% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
DIMP Project Support | DIMP Data Maintenance | 362 | 1768.5057 | -1406.5057 | -79.53% | Yes | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
TIMP | ILI & ECDA - cleaning and assessing internal conditions of high-pressure pipelines | 76362.8694 | 47817 | 28545.8694 | 59.7% | Yes | 37 ILI 28 ECDA | 21 ILI 20 ECDA | 16 8 | 76% 40% | Yes Yes
DIMP | DIMP Programs (e.g., DREAMS, GIPP) | 42607.2214 | 41378 | 1229.2214 | 2.971% |  | 166,000 Riser Inspections 65,000 Service Inspections 5,660 Site Mitigations | 180,000 Riser Inspections 60,000 Service Inspections 4400 Site Mitigations | -14,000 5,000 1,260 | -8% 8% 29% | No No Yes
Underground Storage - RSIMP | SIMP RAMP | 13795 | 20324 | -6529 | -32% | Yes | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Research Development and Demonstration (RD&D) Technology Dev | Non-RAMP | 13143 | 15395 | -2252 | -15% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.

## 2-GDC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - Capital Variance Tables, Question 1
1.A. Gas Distribution
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas Distribution |  | 301933.9281 | 391406.461 | -89472.5329 | -22.86% |  | Unless noted below, units aren’t available for this Witness Area because there is no single number of like units that would be comparable year over year.
New Business Construction | Non-RAMP | 57751.3843 | 54202.6575 | 3548.7268 | 6.547% |  | 40,151 Meter Installations | 51,388 Meter Installations | -11,237 Meter Installations | -21.87%
New Business - RAMP | MSA Inspections- Customer Service Initial Turn-ons | 3409 | 2858 | 551 | 19.28%
Sub-Total New Business |  | 61160.3843 | 57060.6575 | 4099.7268 | 7.185%
Gas Meters | Non-RAMP | 26153.8128 | 33761.697 | -7607.8842 | -22.53% | Yes | 122,043 Meters Purchased | 184,513 Meters Purchased | -62,470 Meters Purchased | -33.86%
Gas Regulators | Non-RAMP | 7647.978 | 5802.332 | 1845.646 | 31.81% |  | 154,982 Regulators Purchased | 102,444 Regulators Purchased | 52,538 Regulators Purchased | 51.28%
Cathodic Protection | Non-RAMP | 0 | 4436.6115 | -4436.6115 | -100% | Yes
Cathodic Protection - RAMP | Systems are in place to monitor and manage compliance activity schedules | 4302.0659 | 6325.085 | -2023.0191 | -31.98% | Yes | 141 Field Completed Orders
Sub-Total Cathodic Protection |  | 4302.0659 | 10761.6965 | -6459.6306 | -60.02% | Yes
Electronic Pressure Monitors (EPM) | Non-RAMP | 728.5039 | 652.8755 | 75.6284 | 11.58% |  | 140 EPM Installations
Remote Meter Reading | Non-RAMP | 212.9246 | 0 | 212.9246 | 100%
Pressure Betterment Projects | Non-RAMP | 18507.8732 | 26124.072 | -7616.1988 | -29.15% | Yes | 35 Field Completed Orders
Main Replacements | Non-RAMP | 11887.4264 | 35715.7975 | -23828.3711 | -66.72% | Yes | 169 Field Completed Orders
Main Replacements - RAMP | Contracting for Traffic Control Delineation materials | 2015 | 2428.199 | -413.199 | -17.02%
Sub-Total Main Replacements |  | 13902.4264 | 38143.9965 | -24241.5701 | -63.55% | Yes
Main & Service Abandonments | Non-RAMP | 13218.2271 | 13336.9905 | -118.7634 | -0.8905% |  | 4,604 Field Completed Orders
Service Replacements | Non-RAMP | 35590.627 | 38926.9945 | -3336.3675 | -8.571% |  | 3,707 Field Completed Orders
Pipeline Relocations - Freeway | Non-RAMP | 795.5424 | 8867.5655 | -8072.0231 | -91.03% | Yes | 7 Field Completed Orders
Pipeline Relocations - Franchise | Non-RAMP | 14363.2085 | 20247.061 | -5883.8525 | -29.06% | Yes | 8 Field Completed Orders
Meter Guards | Non-RAMP | 1648.0296 | 9390.3185 | -7742.2889 | -82.45% | Yes | 1,803 Completed Remediations | 12,848 Completed Remediations | -11,045 Completed Remediations | -85.97%
Regulator Stations | Non-RAMP | 5443.9696 | 21734.9835 | -16291.0139 | -74.95% | Yes | 20 Regulator Stations
Regulator Stations - RAMP | Systems are in place to monitor and manage compliance activity schedules related to high pressure | 167 | 209.3275 | -42.3275 | -20.22%
Regulator Stations - RAMP | Systems are in place to monitor and manage compliance activity schedules related to medium pressure. | 136 | 47.523 | 88.477 | 186.2%
Sub-Total Regulator Stations |  | 5746.9696 | 21991.834 | -16244.8644 | -73.87% | Yes
Supply Line Replacements | Non-RAMP | 0 | 4762.4835 | -4762.4835 | -100% | Yes
Other Distribution Capital Projects | Non-RAMP | 10313.5049 | 3700.005 | 6613.4999 | 178.7% | Yes | 90 Field Completed Orders
Other Distribution Capital Projects - RAMP | Systems are in place to monitor and manage compliance activity schedules- Maintenance and Inspection of Medium Pressure Valves | 15 | 5.6575 | 9.3425 | 165.1%
Other Distribution Capital Projects - RAMP | Valve Maintenance and Installation (Distribution High Pressure) | 73 | 24.893 | 48.107 | 193.3%
Sub-Total Other Distribution Capital Projects |  | 10401.5049 | 3730.5555 | 6670.9494 | 178.8% | Yes
Gas Energy Measurement Systems (GEMS) | Non-RAMP | 2214.9643 | 1690.461 | 524.5033 | 31.03% |  | 848 GEMS Units | 540 GEMS Units | 308 GEMS Units | 57.04%
Capital Tools & Equipment | Non-RAMP | 6055.3154 | 10935.9475 | -4880.6321 | -44.63% | Yes
Capital Tools & Equipment - RAMP | Prevention and Improvements | 328 | 0 | 328 | 100%
Capital Tools & Equipment - RAMP | Upgrade Nomex Coveralls & Fresh Equipment | 652 | 0 | 652 | 100%
Capital Tools & Equipment - RAMP | Confined space air monitoring system for field personnel | 892 | 0 | 892 | 100%
Sub-Total Capital Tools & Equipment |  | 7927.3154 | 10935.9475 | -3008.6321 | -27.51% | Yes
Field Capital Support | Non-RAMP | 74937.2029 | 84242.438 | -9305.2351 | -11.05% |  | 674 FTE
Field Capital Support - RAMP | Med Pressure Company Crew Inspections | 76 | 65.627 | 10.373 | 15.81% |  | 3,075 Inspections
Field Capital Support – RAMP | Systems are in place to monitor and manage compliance activity schedules | 848 | 122.202 | 725.798 | 593.9% |  | 9 FTE
Sub-Total Field Capital Support |  | 75861.2029 | 84430.267 | -8569.0641 | -10.15%
New Business Construction | Non-RAMP | 1550.3674 | 788.6555 | 761.7119 | 96.58%

## 2-GEC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - Capital Variance Tables, Question 1
1.C. Gas Engineering
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas Engineering |  | 11635.6341 | 9768.2395 | 1867.3946 | 19.12% |  | Units not available for this WP because there is no single number of like units that would be comparable year over year.
Laboratory Equipment - RAMP | Odorization | 2588.1545 | 2540.2175 | 47.937 | 1.887%
Supervision & Engineering Overhead Pool | Non-RAMP | 9047.4796 | 7228.022 | 1819.4576 | 25.17%

## 2-MPC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - Capital Variance Tables, Question 1
1.D. Major Projects
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas Major Projects |  | 346.9147 | 42673.391 | -42326.4763 | -99.19% |  | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.
Supervision & Engineering – Major Projects | Non-RAMP | 24.1918 | 0 | 24.1918 | 100%
Distribution Operations Control Center (DOCC) | Non-RAMP | 322.7229 | 13366.4095 | -13043.6866 | -97.59% | Yes
Distribution Operations Control Center (DOCC) | Gas Control Operation | 0 | 29306.9815 | -29306.9815 | -100% | Yes
Sub-Total (DOCC) |  | 322.7229 | 42673.391 | -42350.6681 | -99.24% | Yes

## 2-GTC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - Capital Variance Tables, Question 1
1.F. Gas Transmission
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas Transmission |  | 230936.2488 | 207479.7605 | 23456.4883 | 11.31% |  | Unless noted below, units are not available for this Witness Area because there is no single number of like units that would be comparable year over year.
Gas Transmission New Pipeline | Non-RAMP | 11489.7278 | 8353.8645 | 3135.8633 | 37.54% | Yes | 14,763 ft
GT - Pipeline Replacements | Non-RAMP | 285.9335 | 0 | 285.9335 | 100%
Gas Transmission Relocations | Non-RAMP | 16666.657 | 6601.171 | 10065.486 | 152.5% | Yes
GT M&R Stations | Non-RAMP | 37756.428 | 21428.347 | 16328.081 | 76.2% | Yes
GT Auxiliary Equipment | Non-RAMP | 2740.8986 | 4922.025 | -2181.1264 | -44.31% | Yes
GT Auxiliary Equipment - RAMP | Operational Resiliency | 0 | 6879.52 | -6879.52 | -100% | Yes
GT Auxiliary Equipment - RAMP | Physical security measures put in place for the security/safety of employees and infrastructure | 361 | 2172.48 | -1811.48 | -83.38%
GT Auxiliary Equipment - RAMP | Strain Gauge Installation Projects | 99 | 452.6 | -353.6 | -78.13%
Sub-Total GT Auxiliary Equipment |  | 3200.8986 | 14426.625 | -11225.7264 | -77.81% | Yes
Gas Transmission Freeway Relocations | Non-RAMP | 1949.5292 | 99.572 | 1849.9572 | 1858% |  | 170 ft
Gas Transmission Cathodic Protection | Non-RAMP | 2029.7731 | 6154.2285 | -4124.4554 | -67.02% | Yes | 2 CP Engines
Gas Transmission Cathodic Protection - RAMP | Requirements for corrosion control | 5266 | 1379.2985 | 3886.7015 | 281.8% | Yes | 4 Deep Wells Anodes
Sub-Total GT Cathodic Protection |  | 7295.7731 | 7533.527 | -237.7539 | -3.156%
Land Rights & Buildings | Non-RAMP | 482.3848 | 5194.7165 | -4712.3316 | -90.71% | Yes
GT Bld'gs & Improve / Quality/Economic Driven | Non-RAMP | 2590.9919 | 0 | 2590.9919 | 100% | Yes
GT & Stor Cap Tools / Quality/Economic Driven | Non-RAMP | 339.7468 | 0 | 339.7468 | 100%
GS Stor Cap Tools | Non-RAMP | 556.0043 | 0 | 556.0043 | 100%
GT Compressor Stations | Non-RAMP | 0 | 218.3795 | -218.3795 | -100%
GT Replacement Pipelines | Non-RAMP | 31445.5658 | 9741.0835 | 21704.4823 | 222.8% | Yes
GT Replacement Pipelines - RAMP | Gas Transmission | 534 | 2138.535 | -1604.535 | -75.03%
Sub-Total GT Replacement Pipelines |  | 31979.5658 | 11879.6185 | 20099.9473 | 169.2% | Yes
GT Compressor Stations | Non-RAMP | 9517.676 | 12616.225 | -3098.549 | -24.56% | Yes
GT Compressor Stations | Non-RAMP | 0 | 1451.7145 | -1451.7145 | -100%
MP PL Rpls / Quality/Economic Driven | Non-RAMP | 431.948 | 0 | 431.948 | 100%
GT Compressor Stations | Non-RAMP | 106392.9841 | 117676 | -11283.0159 | -9.588% | Yes

## 2-UGSC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - Capital Variance Tables, Question 1
1.G. Underground Storage
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Underground Storage |  | 71314.9203 | 133599.526 | -62284.6057 | -46.62% |  | Units are unavailable because these workpapers do not have a single number of like units that would be comparable year over year.
GS Compressor Stations | Non-RAMP | 7524.1429 | 29079.55 | -21555.4071 | -74.13% | Yes
GS Wells - Cushion Gas Purchase | Non-RAMP | 0 | 2340 | -2340 | -100% | Yes
GS Wells - RAMP Base - C1 | Well replacements | 0 | 55443.5 | -55443.5 | -100% | Yes
GS Wells - RAMP Base - C2 | Well plug & abandon | 28632 | 8203.375 | 20428.625 | 249% | Yes
GS Wells - RAMP Base - C4 | Well workovers | 535 | 1096.4235 | -561.4235 | -51.2%
GS Wells - RAMP Base - C7 | Wells blanket projects | 1521 | 1131.5 | 389.5 | 34.42%
GS Wells Sub-Total |  | 30688 | 68214.7985 | -37526.7985 | -55.01% | Yes
GS Pipelines | Non-RAMP | 16334.1112 | 7694.2 | 8639.9113 | 112.3% | Yes
GS Purification | Non-RAMP | 1503.2477 | 6347.715 | -4844.4673 | -76.32% | Yes
GS Auxiliary Equipment | Non-RAMP | 14817.6993 | 19999.2625 | -5181.5632 | -25.91% | Yes
GS - Aliso Canyon | Erosion mitigation | 374 | 1132 | -758 | -66.96%
GS - Playa Del Rey | Erosion mitigation | 33 | 1132 | -1099 | -97.08%
GS Auxiliary Equipment Sub-Total |  | 15224.6993 | 22263.2625 | -7038.5632 | -31.62% | Yes
Storage Lead Abatement | Non-RAMP | 40.7191 | 0 | 40.7191 | 100%

## 2-PSEPC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - Capital Variance Tables, Question 1
1.H. PSEP
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Pipeline Safety Enhancement Program |  | 66003.144 | 131027.025 | -65023.881 | -49.63%
PSEP Pipeline Replacement - RAMP | Approved PSEP program to test or replace High Consequence Area High Pressure pipelines | 28160.4271 | 35890.4195 | -7729.9924 | -21.54% | Yes | 0.922 mi | 0.865 mi | 0.057 mi | 6.59%
PSEP Valve Projects - RAMP |  | 37842.7169 | 83970.9635 | -46128.2466 | -54.93% | Yes | 45 installations | 94 installations | (49) installations | -52.13% | Yes
PSEP PMO - RAMP |  | 0 | 11165.642 | -11165.642 | -100% | Yes | Units unavailable because these work papers do not have a single number of like units that would be comparable year over year.

## 2-ITC_CYC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - Capital Variance Tables, Question 1
2.B. Information Technology & Cyber Security
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Information Technology & Cyber Security |  | 120504.0411 | 114364.0362 | 6140.0049 | 5.369% |  | Units not available for these workpapers because there is no single number of like units that would be comparable year over year.
Sub-Total Information Technology |  | 102285.1762 | 88675.9047 | 13609.2715 | 15.35%
Applications - Utility Operations/Mandated | Non-RAMP | 174.1 | 352.8104 | -178.7104 | -50.65%
Applications - Utility Operations/Mandated - RAMP | Records Management | 16764.3105 | 16202.1427 | 562.1678 | 3.47%
Applications - Utility Operations/Mandated - RAMP | Employee, Contractor, Customer, and Public Safety | 3227.581 | 103.3712 | 3124.2098 | 3022% | Yes
Sub-Total Applications - Utility Operations/Mandated |  | 20165.9915 | 16658.3243 | 3507.6672 | 21.06% | Yes
Infrastructure - Hardware/Reliability/Improvements | Non-RAMP | 32919.1535 | 1068.136 | 31851.0175 | 2982% | Yes
Infrastructure - Software/Reliability/Improvements | Non-RAMP | 680.2828 | 0 | 680.2828 | 100%
Network/Telecom - Hardware/Reliability/Improvements | Non-RAMP | 4280.7427 | 19007.3002 | -14726.5575 | -77.48% | Yes
Applications - Utility Operations/Reliability/Improvements | Non-RAMP | 17399.8823 | 21128.4091 | -3728.5268 | -17.65%
Applications - Utility Operations/Reliability/Improvements - RAMP | Records Management | 1861.179 | 17383.2345 | -15522.0555 | -89.29% | Yes
Sub-Total Applications - Utility Operations/Reliability/Improvements |  | 19261.0613 | 38511.6436 | -19250.5823 | -49.99% | Yes
Hardware - Utility Operations/Reliability/Improvements | Non-RAMP | 18842.3687 | 10518.0196 | 8324.3491 | 79.14% | Yes
Hardware - Utility Operations/Reliability/Improvements - RAMP | Records Management | 5527.386 | 2912.481 | 2614.905 | 89.78% | Yes
Sub-Total Hardware - Utility Operations/Reliability/Improvements |  | 24369.7547 | 13430.5006 | 10939.2541 | 81.45% | Yes
Incorporating AMI Data into Scheduling & Balancing Process | Non-RAMP | 608.1897 | 0 | 608.1897 | 100%
Cyber Security - RAMP | Cyber Security | 18218.8648 | 25688.1315 | -7469.2667 | -29.08% | Yes

## 2-SSC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - Capital Variance Tables, Question 1
2.C. Support Services
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Support Services - Facilities |  | 19567.8874 | 32719.5855 | -13151.698 | -40.2% |  | Units not available for these workpapers because there is no single number of like units that would be comparable year over year.
Infrastructure & Improvements | Non-RAMP | 15508.1815 | 29777.6855 | -14269.504 | -47.92% | Yes
Infrastructure & Improvements - RAMP | Physical Security | 1669 | 678.9 | 990.1 | 145.8%
Sub-Total Infrastructure & Improvements |  | 17177.1815 | 30456.5855 | -13279.404 | -43.6% | Yes
Safety/Environmental | Non-RAMP | 2390.706 | 2263 | 127.706 | 5.643%

## 2-Bal ProgC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Attachment B - Capital Variance Tables, Question 1
4.B. Balanced Programs Direct Capital Expenses
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
TIMP & DIMP Total |  | 227579 | 243272 | -15693 | -6.451%
DIMP | DIMP Programs & records management | 4923 | 3168 | 1755 | 55.4% |  | Not a measurable activity
DIMP | DIMP Programs - High Pressure Risk | 1430 | 109015 | -107585 | -98.69% | Yes | 372 site mitigations | 286 site mitigations | 86 | 30.07% | Yes
DIMP | DIMP Programs - Medium Pressure Risk | 114650 | 68856 | 45794 | 66.51% | Yes | 74 mi | 107 mi | -33 | -30.84% | Yes
Sub-Total DIMP |  | 121003 | 181039 | -60036 | -33.16% | Yes
TIMP – Dist | ILI & ECDA - cleaning and assessing internal conditions of high-pressure pipelines | 9586 | 5748 | 3838 | 66.77% | Yes | See O&M section for TIMP units
TIMP – Trans | ILI & ECDA - cleaning and assessing internal conditions of high-pressure pipelines | 92489 | 52298 | 40191 | 76.85% | Yes | See O&M section for TIMP units
TIMP | TIMP Data Maintenance | 4501 | 4187 | 314 | 7.499% |  | Not a measurable activity
Sub-Total TIMP |  | 106576 | 62233 | 44343 | 71.25% | Yes
SIMP Total | Well Integrity Management inclusive of inspection of wells, plugging and abandonment, data management, etc. | 64118 | 60402 | 3716 | 6.152% |  | 5 Plug & Abandonments 20 Workovers | 0 Plug & Abandonments 68 Workovers | 5 Plug & Abandonments (48) Workovers | 100% -71% | Yes Yes

## Var Criteria
Variance Thresholds Requiring Variance Explanations as of 1/1/2020
SDG&E | O&M |  |  | Capital
| Criteria 1 | Criteria 2 |  | Criteria 1 | Criteria 2
| Anything Over | Greater than 20% AND min $ |  | Anything Over | Greater than 20% AND min $
Elect | 5000 | 2500 | 20% | 10000 | 5000 | 20%
Gas | 2500 | 500 | 20% | 5000 | 1000 | 20%
Other | 5000 | 2500 | 20% | 10000 | 5000 | 20%
SoCal Gas | O&M |  |  | Capital
| Criteria 1 | Criteria 2 |  | Criteria 1 | Criteria 2
| Anything Over | Greater than 20% AND min $ |  | Anything Over | Greater than 20% AND min $
Gas | 5000 | 1000 | 20% | 10000 | 2000 | 20%
Other | 5000 | 1000 | 20% | 10000 | 2000 | 20%