## Q2
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 2
Summary Tables by Line of Business | [6 empty] | Summary Tables by Line of Business
Utility | GRC General Line of Business | 2019 Actuals | 2019 Imputed Authorized | $ Variance | % Variance |  | Utility | GRC General Line of Business | 2019 Actuals | 2019 Imputed Authorized | $ Variance | % Variance
SDG&E O&M | Electric & Fuel Procurement | 7963.7083 | 9349.3825 | -1385.6742 | -14.82% |  | SDG&E Capital | Electric Distribution | 427725 | 634326 | -206601 | -32.57%
| Electric Distribution | 173333.3902 | 168396.0289 | 4937.3612 | 2.932% |  |  | Electric Generation | 12314 | 12971 | -657 | -5.065%
| Electric Generation & SONGS | 36663.6243 | 41069.8788 | -4406.2545 | -10.73% |  |  | Sub-Total Electric | 440039 | 647297 | -207258 | -32.02%
| Sub-Total Electric | 217960.7228 | 218815.2902 | -854.5675 | -0.3905% |  |  | Gas Distribution | 56763.1925 | 110069.4373 | -53306.2449 | -48.43%
| Gas Distribution | 29345.1153 | 31762.1393 | -2417.024 | -7.61% |  |  | Gas Engineering (incl TIMP/DIMP) | 47239.1981 | 55746.742 | -8507.5439 | -15.26%
| Gas Engineering (incl TIMP/DIMP) | 9068.6677 | 11757.6851 | -2689.0174 | -22.87% |  |  | Gas Transmission | 11405.6659 | 9252.5018 | 2153.1641 | 23.27%
| Gas Transmission (incl Gas Sys Integ) | 5081.5165 | 7170.5385 | -2089.022 | -29.13% |  |  | Sub-Total Gas | 115408.0565 | 175068.6811 | -59660.6247 | -34.08%
| Sub-Total Gas | 43495.2994 | 50690.3629 | -7195.0634 | -14.19% |  |  | Sub-Total Other | 115233.2755 | 191022.1996 | -75788.9241 | -39.68%
| Sub-Total Other | 258064.3049 | 273302.2353 | -15237.9304 | -5.575% |  |  | SDG&E TOTAL Capital | 670680.3319 | 1013387.8807 | -342707.5488 | -33.82%
| SDG&E TOTAL O&M | 519520.3271 | 542807.8885 | -23287.5613 | -4.29%
Summary Tables by GRC Witness Area | [6 empty] | Summary Tables by GRC Witness Area
Utility | GRC Witness Areas | 2019 Actuals | 2019 Imputed Authorized | $ Variance | % Variance | 2019 RSAR Page Reference | Utility | GRC Witness Areas | 2019 Actuals | 2019 Imputed Authorized | $ Variance | % Variance | 2019 RSAR Page Reference
SDG&E Non-Balanced O&M | Electric & Fuel Procurement | 7963.7083 | 9349.3825 | -1385.6742 | -14.82% | A-40 | SDG&E Non-Balanced Capital | Electric Distribution 1 | 130146 | 270311 | -140165 | -51.85% | A-23
| Electric Distribution 1 | 92852.0584 | 110134.4718 | -17282.4134 | -15.69% | A-9 |  | Electric Generation | 12314 | 12971 | -657 | -5.065% | A-39
| Electric Generation & SONGS | 36663.6243 | 41069.8788 | -4406.2545 | -10.73% | A-38 |  | Sub-Total Electric | 142460 | 283282 | -140822 | -49.71%
| Sub-Total Electric | 137479.391 | 160553.7331 | -23074.3421 | -14.37% |  |  | Gas Distribution | 56763.1925 | 110069.4373 | -53306.2449 | -48.43% | A-48
| Gas Distribution | 29345.1153 | 31762.1393 | -2417.024 | -7.61% | A-41 |  | Gas Engineering | 495.4556 | 303.242 | 192.2136 | 63.39% | A-58
| Gas Engineering | 0 | 0 | 0 | 0% | A-58 |  | Gas Transmission | 11405.6659 | 9252.5018 | 2153.1641 | 23.27% | A-63
| Gas System Integrity | 325.7987 | 1666.1009 | -1340.3022 | -80.45% | A-59 |  | Sub-Total Gas | 68664.314 | 119625.1811 | -50960.8672 | -42.6%
| Gas Transmission | 4755.7177 | 5504.4376 | -748.7199 | -13.6% | A-61 |  | Cyber Security | 2176.6803 | 5444.9656 | -3268.2853 | -60.02% | A-84
| Sub-Total Gas | 34426.6318 | 38932.6778 | -4506.046 | -11.57% |  |  | Information Technology 1 | 81124.7655 | 63502.5884 | 17622.177 | 27.75% | A-84
| Accounting & Finance | 633 | 795 | -162 | -20.38% | A-92 |  | Facilities/Other | 22885.4502 | 65600.2624 | -42714.8122 | -65.11% | A-89
| Human Resources | 7016.8306 | 7872.7538 | -855.9231 | -10.87% | A-95 |  | Sub-Total Other | 106186.8959 | 134547.8164 | -28360.9205 | -21.08%
| Risk Management | 4086.0164 | 7204.7554 | -3118.739 | -43.29% | A-93 |  | Sub-Total Non-Balanced Capital | 317311.2098 | 537454.9975 | -220143.7877 | -40.96% | page 17 (pdf 22 of 240)
| Compensation & Benefits | 161 | 279 | -118 | -42.29% | A-92 | SDG&E Balanced Capital | Electric Distribution 1 | 297579 | 364015 | -66436 | -18.25% | A-28
| Corporate Center - General Administration | 72520 | 51709 | 20811 | 40.25% | A-93 |  | Gas - TIMP & DIMP | 46743.7425 | 55443.5 | -8699.7575 | -15.69% | A-103
| CS - Field | 21707.4709 | 25751.445 | -4043.9741 | -15.7% | A-67 |  | Other - Information Technology 1 | 9046.3796 | 56474.3832 | -47428.0036 | -83.98% | A-84
| CS - Information & Technologies | 14665.1804 | 21975.017 | -7309.8366 | -33.26% | A-69 |  | Sub-Total Balanced Capital | 353369.1221 | 475932.8832 | -122563.7611 | -25.75%
| CS - Office Operations (incl AMO) | 24415.049 | 28039.4431 | -3624.3941 | -12.93% | A-70 |  | TOTAL SDG&E Capital | 670680.3319 | 1013387.8807 | -342707.5488 | -33.82%
| Cyber Security | 9259.4561 | 8217 | 1042.4561 | 12.69% | A-81
| Information Technology | 66321.9966 | 84080.9352 | -17758.9387 | -21.12% | A-77 |  | Electric Distribution Total | 427725 | 634326 | -206601 | -32.57% | A-14
| Real Estate & Facilities | 32877.1113 | 32335.3435 | 541.7678 | 1.675% | A-87 |  | Information Technology Total | 90171.145 | 119976.9716 | -29805.8266 | -24.84% | A-83
| Environmental | 4401.1936 | 5042.5423 | -641.3487 | -12.72% | A-86
| Sub-Total Other | 258064.3049 | 273302.2353 | -15237.9304 | -5.575% |  |  | Note 1: Wildfire Mitigation Plan costs are reported separately, but in the line of business where they're incurred.
| Sub-Total Non-Balanced O&M | 429970.3277 | 472788.6462 | -42818.3185 | -9.057% | page 17 (pdf 22 of 240)
SDG&E Balanced O&M | Electric Distribution 1 | 45972.3318 | 34093.0879 | 11879.2438 | 34.84% | A-10
| Electric - Tree Trimming | 34509 | 24168.4692 | 10340.5308 | 42.79% | A-99
| Gas - TIMP & DIMP | 9068.6677 | 11757.6851 | -2689.0174 | -22.87% | A-99
| Sub-Total Balanced O&M | 89549.9994 | 70019.2422 | 19530.7572 | 27.89%
| TOTAL SDG&E O&M | 519520.3271 | 542807.8885 | -23287.5613 | -4.29%
| Electric Distribution Total 1 | 138824.3902 | 144227.5597 | -5403.1696 | -3.746% | A-2
Note 1: Wildfire Mitigation Plan costs are reported separately, but in the line of business where they're incurred.

## Q3
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 3
High Level Summary Table - Excludes 'Other' Line of Business Costs
Utility | GRC Witness Areas | 2019 Actuals | 2019 Imputed Authorized | $ Variance | % Variance
SDG&E | O&M Spend - Electric | 217960.7227 | 218815.2902 | -854.5675 | -0.3905%
| O&M Spend - Gas | 43495.2994 | 50690.3629 | -7195.0634 | -14.19%
| Capital Spend - Electric | 440039 | 647297 | -207258 | -32.02%
| Capital Spend - Gas | 115408.0565 | 175068.6811 | -59660.6247 | -34.08%
| SDG&E TOTAL | 816903.0787 | 1091871.3343 | -274968.2556 | -25.18%

## EDO
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - O&M Variance Tables
1.A. Electric Distribution
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Electric Distribution |  | 138824.3902 | 144227.5597 | -5403.1696 | -3.746% |  | Unless noted below, units not available for this Witness Area because there is no single number of like units that would be comparable year over year
Reliability & Capacity | Non-RAMP | 208.3843 | 283 | -74.6157 | -26.37%
Reliability & Capacity | Improved modeling tools for DER's | 59 | 80 | -21 | -26.25% |  | 1 Software license | 1 Software license | 0 | 0%
Sub-Total Reliability & Capacity |  | 267.3843 | 363 | -95.6157 | -26.34%
Construction Services | Non-RAMP | 767.9735 | 928.6899 | -160.7164 | -17.31%
Construction Services | Contractor Safety Review | 663 | 802 | -139 | -17.33%
Construction Services | System Hardening and Grid Modernization | 2360 | 2853 | -493 | -17.28% |  | See capital programs
Construction Services | Workforce Planning | 15 | 18 | -3 | -16.67% |  | 5 Training modules
Sub-Total Construction Services |  | 3805.9735 | 4601.6899 | -795.7164 | -17.29%
Distops Enterprise Geographic Information System Standards | Non-RAMP | 1199.6913 | 284.0901 | 915.6012 | 322.3%
Distops Enterprise Geographic Information System Standards | Records Management | 0 | 1077.4708 | -1077.4708 | -100% |  | See program Asset Management, RAMP activity Annual records management compliance
Sub-Total Distops Enterprise Geographic Information System Standards |  | 1199.6913 | 1361.5609 | -161.8696 | -11.89%
Electric Distribution Operations | Non-RAMP | 18242.8023 | 18539.5714 | -296.7692 | -1.601%
Electric Distribution Operations | Workforce Planning | 26 | 30 | -4 | -13.33% |  | 9 Operators trained
Electric Distribution Operations | Records Management | 0 | 2166.518 | -2166.518 | -100% |  | See program Asset Management, RAMP activity Annual records management compliance
Sub-Total Electric Distribution Operations |  | 18268.8023 | 20736.0894 | -2467.2872 | -11.9%
Kearny Operations Services | Non-RAMP | 1493.0617 | 2135.9694 | -642.9077 | -30.1%
Grid Operations | Non-RAMP | 618.619 | 607.0788 | 11.5402 | 1.901%
Grid Operations | Workforce Planning | 4 | 4 | 0 | 0% |  | 21 Engineers in training
Sub-Total Construction Services |  | 622.619 | 611.0788 | 11.5402 | 1.888%
Project Management | Non-RAMP | 2041.6581 | 1361.4195 | 680.2386 | 49.97%
Electric Regional Operations | Non-RAMP | 13336.8933 | 14749.7227 | -1412.8294 | -9.579%
Electric Regional Operations | Safety Policies & Programs | 18157 | 20234.1536 | -2077.1536 | -10.27% |  | 53,300 Employee hours in safety meetings
Electric Regional Operations | Aviation Safety | 395 | 440.1637 | -45.1637 | -10.26% |  | 1 Aviation Safety Management System | 1 Aviation Safety Management System | 0 | 0%
Electric Regional Operations | Distribution Switch Maintenance Program | 1001 | 1115.4393 | -114.4393 | -10.26% |  | 420 Switches inspected
Electric Regional Operations | Employee Records Management training course | 38 | 41.8692 | -3.8692 | -9.241% |  | 170 Trainings completed
Electric Regional Operations | Workforce Planning | 1054 | 1174.4856 | -120.4856 | -10.26% |  | 12 Apprentice Linemen | Unable to impute
Electric Regional Operations | Inspection and Preventative Maintenance | 0 | 1179 | -1179 | -100%
Sub-Total Electric Regional Operations |  | 33981.8933 | 38934.8342 | -4952.9409 | -12.72%
Skills & Compliance Training | Non-RAMP | 1681.4191 | 2095.1565 | -413.7374 | -19.75%
Skills & Compliance Training | Ongoing maintenance programs | 2371 | 2954.0562 | -583.0562 | -19.74% |  | 112 Classes
Sub-Total Skills & Compliance Training |  | 4052.4191 | 5049.2127 | -996.7936 | -19.74%
Service Order Team (SOT) | Non-RAMP | 1876.6202 | 173.1124 | 1703.5078 | 984%
Substation C&O | Non-RAMP | 3939.1018 | 4821.523 | -882.4212 | -18.3%
Substation C&O | Condition Base Maintenance (CBM) - Distribution | 256 | 313 | -57 | -18.21% |  | 5 CBM monitors replaced | 15 CBM monitors replaced | -10 | -66.67% | Yes
Sub-Total Substation C&O |  | 4195.1018 | 5134.523 | -939.4212 | -18.3%
System Protection | Non-RAMP | 2165.3301 | 1949.7649 | 215.5652 | 11.06%
System Protection | Replace failed SCADA remote terminal units (RTU's) | 64 | 58 | 6 | 10.34% |  | 5 RTU's replaced | 7 RTU's replaced | -2 | -28.57% | Yes
System Protection | Workforce Planning | 8 | 7 | 1 | 14.29% |  | 143 Hours job shadowed | 125 Hours job shadowed | 18 | 14.4%
Sub-Total System Protection |  | 2237.3301 | 2014.7649 | 222.5652 | 11.05%
Distribution and Engineering | Non-RAMP | 559.2028 | 2975 | -2415.7972 | -81.2%
Distribution and Engineering | Safety Policies & Programs | 1535 | 868 | 667 | 76.84% |  | 485 Published updates to standards
Distribution and Engineering | Workforce Planning | 388 | 220 | 168 | 76.36% |  | 4,836 Hours of training | 4,108 Hours of training | 728 | 17.72%
Distribution and Engineering | Records Management | 0 | 42.5312 | -42.5312 | -100% |  | See program Asset Management, RAMP activity Annual records management compliance
Sub-Total Distribution and Engineering |  | 2482.2028 | 4105.5312 | -1623.3284 | -39.54%
Asset Management | Utility Asset Management (Non-WMP) | 660 | 2341.7457 | -1681.7457 | -71.82% |  | See program Utility Asset Management - (WMP)
Asset Management | Annual records management compliance | 391 | 901.1043 | -510.1043 | -56.61% |  | 90 records and information management certifications | Unable to impute
Sub-Total Asset Management |  | 1051 | 3242.85 | -2191.85 | -67.59%
Troubleshooting | Non-RAMP | 7095.717 | 8465.2552 | -1369.5382 | -16.18%
Regional Public Affairs | Non-RAMP | 1252.4284 | 1825.1236 | -572.6952 | -31.38%
Major Projects | Non-RAMP | 375.6334 | 111.6584 | 263.9751 | 236.4%
Major Projects | Contractor Safety Program | 20 | 6 | 14 | 233.3%
Sub-Total Major Projects |  | 395.6334 | 117.6584 | 277.9751 | 236.3%
Technology Utilization | Non-RAMP | 1164.7708 | 1326.4177 | -161.6469 | -12.19%
Compliance Management | Non-RAMP | 1540.0626 | 2520.4049 | -980.3423 | -38.9%
Compliance Management | Records Management | 0 | 545.3831 | -545.3831 | -100% |  | See program Asset Management, RAMP activity Annual records management compliance
Sub-Total Compliance Management |  | 1540.0626 | 3065.788 | -1525.7254 | -49.77%
Tech Solutions and Reliability | Non-RAMP | 2328.1037 | 2137.0005 | 191.1032 | 8.943%
Tech Solutions and Reliability | Records Management | 0 | 1379.0969 | -1379.0969 | -100% |  | See program Asset Management, RAMP activity Annual records management compliance
Sub-Total Tech Solutions And Reliability |  | 2328.1037 | 3516.0974 | -1187.9937 | -33.79%
Emergency Management | Non-RAMP | 443.5849 | 587.8114 | -144.2265 | -24.54%
Emergency Management | Meteorology Studies and Education | 325 | 431.7983 | -106.7983 | -24.73% |  | 1 Climate vulnerability assessment
Emergency Management | Emergency Prep Trainings | 731 | 972.8855 | -241.8855 | -24.86% |  | 81 Training sessions for first responders, Incident Response, and EOC
Sub-Total Emergency Management |  | 1499.5849 | 1992.4952 | -492.9103 | -24.74%
Sub-Total ED Non-Balanced Workpapers |  | 92852.0584 | 110134.4718 | -17282.4134 | -15.69% | Yes
Wildfire Mitigation Program | Non-RAMP | 21001.7215 | 0 | 21001.7215 | 0% | Yes, at total WP
Wildfire Mitigation Program | Utility Asset Management - (WMP) | 107 | 1260.94 | -1153.94 | -91.51% |  | 1 Consultant contract | 1 Consultant contract | 0 | 0%
Wildfire Mitigation Program | Wildfire Communications | 2527 | 264 | 2263 | 857.2% |  | 103,031,368 gross impressions
Wildfire Mitigation Program | Fire Science & Climate Adaptation | 4903 | 4202 | 701 | 16.68%
Wildfire Mitigation Program | UAS Safety Program | 277 | 173.9183 | 103.0817 | 59.27% |  | 1 UAS Safety Management System | 1 UAS Safety Management System | 0 | 0%
Wildfire Mitigation Program | System Hardening and Helo | 11032 | 11522.8703 | -490.8703 | -4.26% |  | 12 months of Helo availability; For hardening units, see capital programs | 12 months of Helo availability | 0 | 0%
Wildfire Mitigation Program | Inspection and Preventative Maintenance | 2254 | 12196.6219 | -9942.6219 | -81.52% | Yes, at total WP | Multiple inspection types result in no single unit of measure Preventative maintenance, see capital programs
Wildfire Mitigation Program | Records Management | 0 | 485.21 | -485.21 | -100%
Sub-Total Wildfire Mitigation Program |  | 42101.7215 | 30105.5605 | 11996.161 | 39.85% | Yes
Vegetation Management (Pole Brushing) | Non-RAMP | 270.6102 | 278.5274 | -7.9172 | -2.843%
Vegetation Management (Pole Brushing) | Safety Policies & Programs | 3564 | 3671.91 | -107.91 | -2.939% |  | 59,475 Poles brushed | 54,706 Poles brushed | 4769 | 8.718%
Vegetation Management (Pole Brushing) | Joint Power Line Inspections with CalFire | 36 | 37.09 | -1.09 | -2.939% |  | 0 FTEs utilized | 0.3 FTEs utilized | -0.3 | -100% | Yes
Sub-Total Vegetation Management (Pole Brushing) |  | 3870.6102 | 3987.5274 | -116.9172 | -2.932%
Sub-Total ED Wildfire Mitigation Balanced Program 1 |  | 45972.3318 | 34093.0879 | 11879.2438 | 34.84%
1 Electric Distribution's Vegetation Management (Tree Trimming) workpaper (1ED021.001) was also authorized two-way balancing account treatment in the 2019 GRC Decision. The costs related to the Tree Trimming Balancing Account are not included in these figures. Rather, the Tree Trimming Balancing Account is addressed in the Balanced section of this 2019 RSAR.
Note: on page A-10 the unit variance should have been (0.3)

## EGO
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - O&M Variance Tables
1.B. Electric Generation
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Electric Generation |  | 36663.6243 | 41069.8788 | -4406.2545 | -10.73% |  | Units not available for this Witness Area because there is no single number of like units that would be comparable year over year
Generation - Plant - Admin | Non-RAMP | 246.3765 | 379.1292 | -132.7527 | -35.02%
Generation Plant Miramar | Non-RAMP | 1313.2632 | 2520.0916 | -1206.8284 | -47.89%
Generation Plant Miramar | Maintenance Certification and testing of existing Blackstart Resources | 15 | 22 | -7 | -31.82%
Sub-Total Generation Plant Miramar |  | 1328.2632 | 2542.0916 | -1213.8284 | -47.75%
Generation Plant Palomar | Non-RAMP | 19985.0335 | 19712.3364 | 272.6971 | 1.383%
Electric Project Development | Non-RAMP | 0.59979 | 131.4044 | -130.8046 | -99.54%
Generation Plant Desert Star | Non-RAMP | 13462.4588 | 16281.5432 | -2819.0844 | -17.31%
Generation Plant Cuyamaca Peak | Non-RAMP | 733.2388 | 1130.628 | -397.3891 | -35.15%
Generation Plant Cuyamaca Peak | Add blackstart capabilities to the southern part of the SDG&E electric system. | 0 | 22 | -22 | -100%
Sub-Total Generation Plant Cuyamaca Peak |  | 733.2388 | 1152.628 | -419.3891 | -36.39%
Resource Planning Director | Non-RAMP | 907.6536 | 870.746 | 36.9076 | 4.239%

## EFP
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - O&M Variance Tables
1.C. Electric & Fuel Procurement
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Electric & Fuel Procurement |  | 7963.7083 | 9349.3825 | -1385.6742 | -14.82% |  | 0 | 0 | 0 | 0%
Long Term Procurement | Non-RAMP | 1805.2541 | 2388.9599 | -583.7058 | -24.43% |  | 11 FTE | 15 FTE | -4 | -27.21%
Trading & Scheduling | Non-RAMP | 2069.6294 | 3191.6545 | -1122.0251 | -35.15% |  | 16 FTE | 20 FT | -4 | -19.61%
Mid and Back Office | Non-RAMP | 4088.8248 | 3768.7681 | 320.0567 | 8.492% |  | 22 FTE | 25 FTE | -3 | 12.2%

## GDO
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - O&M Variance Tables
2.A. Gas Distribution
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas Distribution |  | 29345.1153 | 31762.1393 | -2417.024 | -7.61% |  | Unless noted, units not available for this Witness Area because there is no single number of like units that would be comparable year over year
Field O&M - Other Services | Non-RAMP | 315 | 218 | 97 | 44.5%
Field O&M - Leak Survey | Non-RAMP | 0 | 2 | -2 | -100% |  | 0
Field O&M - Leak Survey | Maintenance | 1868 | 1776 | 92 | 5.18% |  | 990 Inspections and Surveys
Field O&M - Leak Survey | Employee, Contractor, and Public Safety | 0 | 220 | -220 | -100% |  | 0
Sub-Total Field O&M - Leak Survey |  | 1868 | 1998 | -130 | -6.507%
Field O&M - Locate & Mark | Non-RAMP | 495 | 495 | 0 | 0%
Field O&M - Locate & Mark | Training Locate & Mark Activities Prevention and Improvements | 4795 | 3365 | 1430 | 42.5% | Yes, at the total WP | 150,747 Tickets transmitted
Sub-Total Field Field O&M - Locate & Mark |  | 5290 | 3860 | 1430 | 37.05% | Yes
Field O&M - Main Maintenance | Non-RAMP | 2209.6867 | 2347 | -137.3133 | -5.851%
Field O&M - Main Maintenance | Safety Policies & Programs | 968 | 1351 | -383 | -28.35% |  | 842 Projects
Sub-Total Field O&M - Main Maintenance |  | 3177.6867 | 3698 | -520.3133 | -14.07%
Field O&M - Service Maintenance | Non-RAMP | 1897 | 2025 | -128 | -6.321%
Field O&M - Tools Fittings & Materials | Non-RAMP | 1219 | 1085 | 134 | 12.35%
Field O&M - Electric Support | Non-RAMP | 263 | 458 | -195 | -42.58%
Field O&M - Supervision & Training | Non-RAMP | 2310.6237 | 1785.1393 | 525.4844 | 29.44% | Yes
Field O&M - Supervision & Training | Safety Policies & Programs | 220 | 2034 | -1814 | -89.18% | Yes
Field O&M - Supervision & Training | Improvements | 1415 | 346 | 1069 | 309% | Yes
Sub-Total Field O&M - Supervision & Training |  | 3945.6237 | 4165.1393 | -219.5156 | -5.27%
Asset Management | Non-RAMP | 1037.193 | 1844 | -806.807 | -43.75% | Yes
Asset Management | Maintenance | 0 | 188 | -188 | -100%
Asset Management | Operations | 39 | 74 | -35 | -47.3% |  | 192 Standards Reviewed
Asset Management | Coat or remove affected buried piping in vaults | 120 | 235 | -115 | -48.94% |  | 13 Projects Reviewed
Sub-Total Field O&M - Asset Management |  | 1196.193 | 2341 | -1144.807 | -48.9% | Yes
Measurement & Regulation | Non-RAMP | 1965 | 1965 | 0 | 0%
Measurement & Regulation | Scheduled monitoring and survey activities | 2664 | 2597 | 67 | 2.58% |  | 5,798 Compliance components maintained
Sub-Total Field O&M - Measurement & Regulation |  | 4629 | 4562 | 67 | 1.469%
Cathodic Protection (CP) | Non-RAMP | 332 | 856 | -524 | -61.21% | Yes, at the total WP
Cathodic Protection | Requirements for Corrosion Control | 1627 | 1627 | 0 | 0% |  | 20,845 CP reads
Sub-Total Field Cathodic Protection |  | 1959 | 2483 | -524 | -21.1% | Yes
Operations Management & Training | Non-RAMP | 1882.6119 | 2850 | -967.3881 | -33.94% | Yes, at the total WP
Operations Management & Training | Qualifications of Pipeline Personnel | 608 | 702 | -94 | -13.39%
Operations Management & Training | Operations | 50 | 97 | -47 | -48.45%
Operations Management & Training | Operations | 22 | 73 | -51 | -69.86%
Operations Management & Training | Mandatrory employee refresher training programs | 748 | 864 | -116 | -13.43% |  | 996 Employees trained
Operations Management & Training | Customer Communications & First Responder training | 275 | 283 | -8 | -2.827% |  | 58 First responder, agency, and internal personnel training sessions
Sub-Total Operations Management & Training |  | 3585.6119 | 4869 | -1283.3881 | -26.36% | Yes

## GSI
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - O&M Variance Tables
2.C. Gas System Integrity
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas System Integrity |  | 325.7987 | 1666.1009 | -1340.3022 | -80.45% |  | Units not available for this Witness Area because there is no single number of like units that would be comparable year over year
Gas Contractor Controls | Safety Policies & Programs | 0 | 138 | -138 | -100%
Pipeline Safety & Compliance | Non-RAMP | 130.7987 | 115.1009 | 15.6978 | 13.64%
Damage Prevention and Public Awareness | Non-RAMP | 195 | 106 | 89 | 83.96%
Damage Prevention and Public Awareness | Public Awareness | 0 | 666 | -666 | -100% | Yes, at total WP
Sub-Total Field O&M -Damage Prevention And Public Awareness |  | 195 | 772 | -577 | -74.74% | Yes
Codes Standards and Records | Information Management Systems | 0 | 641 | -641 | -100% | Yes

## GTO
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - O&M Variance Tables
2.D. Gas Transmission
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas Transmission |  | 4755.7177 | 5504.4376 | -748.7199 | -13.6% |  | Units not available for this Witness Area because there is no single number of like units that would be comparable year over year
Pipeline Operations | Non-RAMP | 224.8845 | 1925 | -1700.1155 | -88.32% | Yes
Pipeline Operations | Patrol Pipeline for Leaks | 65.641 | 21 | 44.641 | 212.6%
Pipeline Operations | MAXIMO Tracking | 41.136 | 29 | 12.136 | 41.85%
Pipeline Operations | M&I Maintenance | 1509.022 | 8 | 1501.022 | 18763% | Yes
Sub-Total Pipeline Operations |  | 1840.6835 | 1983 | -142.3165 | -7.177%
Compression Station Operations | Non-RAMP | 2852.8448 | 3361.4376 | -508.5928 | -15.13%
Technical Services | Non-RAMP | 44.9455 | 8 | 36.9455 | 461.8%
Technical Services | Operator Qualification | 6.579 | 117 | -110.421 | -94.38%
Technical Services | Operations | 10.665 | 35 | -24.335 | -69.53%
Sub-Total Technical Services |  | 62.1895 | 160 | -97.8105 | -61.13%

## CS
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - O&M Variance Tables
3.A. Customer Services
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Customer Services |  | 60787.7004 | 75765.9051 | -14978.2047 | -19.77%
Customer Services Field |  | 21707.4709 | 25751.445 | -4043.9741 | -15.7%
Customer Services Field - Operations | Non-RAMP | 9334.4502 | 12048.7203 | -2714.2701 | -22.53% | Yes | 175,962 Orders | 255,096 Orders | -79134 | -31.02%
Customer Services Field - Operations | Job Observation and Behavior Based Safety. | 133 | 160 | -27 | -16.88% |  | 0 | 0 | 0 | 0%
Customer Services Field - Operations | CSF Emergency Orders - include carbon monoxide, fumigation and hazardous and non hazardous gas leaks and atmospheric corrosion orders | 5091 | 4973 | 118 | 2.373% |  | 75,211 Orders | 78,812 Orders | -3601 | -4.569%
Customer Services Field - Operations | Workforce Planning Technical Training for Critical Roles - Service Technicians and Appliance Mechanics backfill for retirements | 201 | 54 | 147 | 272.2%
Sub-Total Customer Services Field - Operations |  | 14759.4502 | 17235.7203 | -2476.2701 | -14.37%
Customer Services Field - Supervision | Non-RAMP | 1084.2113 | 1544.3342 | -460.1229 | -29.79% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year.
Customer Services Field - Dispatch | Non-RAMP | 3243.7305 | 4242.4424 | -998.7119 | -23.54%
Customer Services Field - Dispatch | Field observations of employee and contractors activities and safety behaviors | 1 | 1 | 0 | 0%
Sub-Total Customer Services Field - Dispatch |  | 3244.7305 | 4243.4424 | -998.7119 | -23.54% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year.
Customer Services Field - Support | Non-RAMP | 2511.079 | 2647.9481 | -136.8691 | -5.169%
Customer Services Field - Support | Field observations of employee and contractors activities and safety behaviors | 108 | 80 | 28 | 35%
Sub-Total Customer Services Field - Support |  | 2619.079 | 2727.9481 | -108.8691 | -3.991% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year.
Customer Service Information & Technology |  | 14665.1804 | 21975.017 | -7309.8366 | -33.26%
Marketing Research & Analytics | Non-RAMP | 6834.4831 | 8074.9704 | -1240.4873 | -15.36%
Marketing Research & Analytics | Safety Communications (Summer/Winter Preparedness; Emergency Preparedness) | 340 | 426 | -86 | -20.19%
Marketing Research & Analytics | Safety Communications (Wire Down) | 1852 | 6550 | -4698 | -71.73% | Yes, at the WP
Sub-Total Marketing Research & Analytics |  | 9026.4831 | 15050.9704 | -6024.4873 | -40.03% | Yes | Units not available for this workpaper because there is no single number of like units that would be comparable year over year.
Customer Programs Pricing And Other Office | Non-RAMP | 5450.6973 | 6615.0466 | -1164.3493 | -17.6%
Customer Programs Pricing And Other Office | Natural Gas Appliance Testing is a safety-related program for Customer Assistance's Energy Savings Assistance (ESA) Program participants. 2 | 188 | 309 | -121 | -39.16% |  | 4,972 NGAT's | 7,391 NGAT's | -2419 | -32.73% | Yes
Sub-Total Customer Programs Pricing And Other Office |  | 5638.6973 | 6924.0466 | -1285.3493 | -18.56%
Customer Service - Office Operations |  | 24415.049 | 28039.4431 | -3624.3941 | -12.93%
Advanced Metering Ops | Non-RAMP | 7659.229 | 10710.6553 | -3051.4263 | -28.49% | Yes
Advanced Metering Ops | Job Observation and Behavior Based Safety. | 118 | 40 | 78 | 195%
Advanced Metering Ops | Workforce Planning | 100 | 117 | -17 | -14.53%
Sub-Total Advanced Metering Op |  | 7877.229 | 10867.6553 | -2990.4263 | -27.52% | Yes | Units not available for this workpaper because there is no single number of like units that would be comparable year over year.
Credit & Collections | Non-RAMP | 2091.704 | 3064 | -972.296 | -31.73%
Credit & Collections | Meter Tampering and meter bypass investigation and remediation. | 279 | 258 | 21 | 8.14% |  | 2,652 Investigations/leads | 2,208 Investigations/leads | 444 | 20.11% | Yes
Sub-Total Credit & Collections |  | 2370.704 | 3322 | -951.296 | -28.64%
CCC Operations | Non-RAMP | 10587.4142 | 10362 | 225.4142 | 2.175%
CCC Operations | Emergency calls taken by the Customer Contact Center including outage calls. | 280 | 403 | -123 | -30.52% |  | 142,618 Emergency/ outage calls | 185,605 Emergency/ outage calls | -42987 | -23.16% | Yes
CCC Operations | Capture Customer Email Program to update customer contact information | 164 | 180 | -16 | -8.889% |  | 1,138,569 email solicitation/ verification residential non-move calls | 1,053,335 email solicitation/ verification residential non-move calls | 85234 | 8.092%
CCC Operations | ESS Emergency call training: 5 hrs per ESS. | 24 | 22 | 2 | 9.091% |  | 0.4 FTE | 0.4 FTE | 0 | 0%
Sub-Total CCC Operations |  | 11055.4142 | 10967 | 88.4142 | 0.8062%
CCC Support | Non-RAMP | 3111.7019 | 2882.7878 | 228.9141 | 7.941% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year.

## ITO_CYO
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - O&M Variance Tables
3.B. Information Technology & Cyber Security
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Information Technology & Cyber Security |  | 75581.4526 | 92297.9352 | -16716.4826 | -18.11%
Information Technology |  | 66321.9966 | 84080.9352 | -17758.9387 | -21.12%
IT Applications NSS | Non-RAMP | 17097.7761 | 18748.0676 | -1650.2915 | -8.802% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
IT Infrastructure NSS | Non-RAMP | 5842.6852 | 12934.2994 | -7091.6142 | -54.83% | Yes | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
Telecom Field Voice - SDG&E | Non-RAMP | 1562.8983 | 2184.878 | -621.9797 | -28.47% |  | 12 FTE | 15 FTE | -3 | -20%
Enterprise Integration Services | Non-RAMP | 1372.814 | 1766.3857 | -393.5717 | -22.28% |  | 11 FTE | 14 FTE | -3 | -21.43%
SSDS Project Office | Non-RAMP | 1114.8635 | 698.1994 | 416.6641 | 59.68% |  | 9 FTE | 5 FTE | 4 | 80%
Software Dev - Work Meas Systems | Non-RAMP | 781.6446 | 347.3368 | 434.3078 | 125% |  | 6 FTE | 3 FTE | 3 | 100%
Software Dev - Database Administrator | Non-RAMP | 595.3922 | 2210.7333 | -1615.3411 | -73.07% |  | 5 FTE | 16 FTE | -11.5 | -70.55% |  | was 58% on page A-78
Network Communication Services Director | Non-RAMP | 2469.6455 | 36.0051 | 2433.6405 | 6759% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
Client Technology & Depot Services | Non-RAMP | 1354.8794 | 1768.3088 | -413.4295 | -23.38% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
Middleware and Internet Engineering | Non-RAMP | 423.6064 | 608.1333 | -184.5269 | -30.34% |  | 3 FTE | 5 FTE | -2 | -40%
Infrastructure Eng & Ops Director | Non-RAMP | 361.4726 | 579.9275 | -218.455 | -37.67% |  | 2 FTE | 4 FTE | -2 | -50%
Network/Telecom Services - SDG&E | Non-RAMP | 7737.6479 | 6353.668 | 1383.9799 | 21.78% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
Enterprise Operations | Non-RAMP | -0.0013 | 2.03 | -2.0313 | -100.1% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
Server Management | Non-RAMP | 480.6745 | 948.6324 | -467.9579 | -49.33% |  | 4 FTE | 8 FTE | -4 | -50%
Infrastructure Program Office | Non-RAMP | 51.1027 | 393.1712 | -342.0685 | -87% |  | 0 FTE | 2 FTE | -2 | -100%
IT Network Field - LAN/WAN Voice | Non-RAMP | 0 | 0.64104 | -0.64104 | -100% |  | 0 FTE | 0 FTE | 0 | 0%
Enterprise Command Center | Non-RAMP | 1297.5907 | 2229.7508 | -932.1601 | -41.81% |  | 9 FTE | 17 FTE | -8 | -47.06%
Shared Software Development Contracts | Non-RAMP | 5467.7703 | 6679.4231 | -1211.6529 | -18.14% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
Project Improvement Office-NCS | Non-RAMP | 192.1592 | 231.0949 | -38.9357 | -16.85% |  | 2 FTE | 2 FTE | 0 | 0%
Service Delivery - NCS | Non-RAMP | 735.8322 | 819.8902 | -84.058 | -10.25% |  | 5 FTE | 7 FTE | -2 | -28.57%
Service Development Program Management | Non-RAMP | 342.96 | 313.2549 | 29.7051 | 9.483% |  | 3 FTE | 3 FTE | 0 | 0%
Customer Analytics System | Non-RAMP | 533.657 | 519.5629 | 14.0941 | 2.713% |  | 2 FTE | 2 FTE | 0 | 0%
Field Force Program Delivery Team | Non-RAMP | 539.6102 | 58.6552 | 480.9551 | 820% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
SVO & CITO | Non-RAMP | 905.9569 | 458.8364 | 447.1204 | 97.45% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
Director IT Infrastructure | Non-RAMP | 1335.7403 | 1173.4237 | 162.3166 | 13.83% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
Infrast Prgrm Office | Non-RAMP | 710.7706 | 809.313 | -98.5424 | -12.18% |  | 6 FTE | 5 FTE | 1 | 20%
Clint Services Maintenance & Support | Non-RAMP | 0 | 2.3505 | -2.3505 | -100% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
Voice Leased Circuits | Non-RAMP | 983.2481 | 1041.049 | -57.8008 | -5.552% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
Mgd Svc Voice Enterp | Non-RAMP | 842.3273 | 2561.0616 | -1718.7343 | -67.11% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
Voice Enterp Support | Non-RAMP | 158.1743 | 536.7642 | -378.5899 | -70.53% |  | 1 FTE | 3 FTE | -2 | -66.67%
Client Tech Svcs | Non-RAMP | 0 | 72.0102 | -72.0102 | -100% |  | 0 FTE | 1 FTE | -1 | -100%
IT Portfolio Management | Non-RAMP | 132.3538 | 307.806 | -175.4522 | -57% |  | 0 FTE | 2 FTE | -2 | -100%
Bi & Analytics Engineering-SAS Contracts | Non-RAMP | 5167.4512 | 5147.4444 | 20.0068 | 0.3887% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
IT& OTI Contracts SS | Non-RAMP | 5382.4172 | 11151.5318 | -5769.1146 | -100% | Yes | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
IT Telecom PMO | Non-RAMP | 65.0409 | 94.2329 | -29.192 | -57% |  | 0 FTE | 1 FTE | -1 | -100%
SDG&E Network Engineering | Non-RAMP | 281.8348 | 293.0621 | -11.2273 | 0.3887% |  | 2 FTE | 1 FTE | 1 | 100%
Cyber Security |  | 9259.4561 | 8217 | 1042.4561 | 12.69%
Security Policy and Awareness | Cyber security risk and vulnerability | 1402.4561 | 1022 | 380.4561 | 37.23% |  | 8 FTE | 8 FTE | 0 | 0%
Director - Information Security | Cyber security risk and vulnerability | 400 | 392 | 8 | 2.041% |  | 2 FTE | 2 FTE | 0 | 0%
Security Engineering | Cyber security risk and vulnerability | 1435 | 1532 | -97 | -6.332% |  | 10 FTE | 10 FTE | 0 | 0%
Security Operations | Cyber security risk and vulnerability | 2460 | 1877 | 583 | 31.06% |  | 16 FTE | 16 FTE | 0 | 0%
Critical Infrastructure Protection* | Non-RAMP | 2635 | 2950 | -315 | -10.68%
Critical Infrastructure Protection | Incremental maintenance costs associated with Grid Modernization capital projects | 0 | 420 | -420 | -100%
Sub-Total Critical Infrastructure Protection |  | 2635 | 3370 | -735 | -21.81% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
Information Security Programs | Cyber security risk and vulnerability | 927 | 24 | 903 | 3762% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
*Error found while working on ED-DR-01 found that $106k was missing from the actuals for the Critical Infrastructure Protection line item, however, the overall total $9,259 was correct. This was originally reported as $2,529 on page A-81.

## SSO
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - O&M Variance Tables
3.C. Support Services
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Support Services Total |  | 37278.3049 | 37377.8858 | -99.5809 | -0.2664%
Environmental |  | 4401.1936 | 5042.5423 | -641.3487 | -12.72%
Environmental SDG&E NSS Cost Center | Non-RAMP | 4401.1936 | 5042.5423 | -641.3487 | -12.72% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
Real Estate and Facilities |  | 32877.1113 | 32335.3435 | 541.7678 | 1.675%
SDG&E Facility Operations | Non-RAMP | 5413.4092 | 5133 | 280.4092 | 5.463% |  | 13 FTE | 13 FTE | 0 | 0%
SDG&E Facility Operations | Physical Security | 3176 | 3814 | -638 | -16.73% |  | 76 Security Guards | 91 Security Guards | -15 | -16.48%
Sub-Total SDG&E Facility Operations |  | 8589.4092 | 8947 | -357.5908 | -3.997%
Land Services | Non-RAMP | 844.9466 | 741.6815 | 103.2651 | 13.92% |  | 3 FTE | 3 FTE | 0 | 0%
SDG&E Rents & Maintenance | Non-RAMP | 19092.2572 | 17513 | 1579.2572 | 9.018% |  | 31,000sq' | 28,400sq' | 2600 | 9.155%
Re Planning | Non-RAMP | 876.4042 | 1134.1066 | -257.7024 | -22.72% |  | 5 FTE | 5 FTE | 0 | 0%
Hq Rent & Facilities Maintenance | Non-RAMP | 1282.9607 | 2371.848 | -1088.8873 | -45.91% |  | 4,200sq' | 7,800sq' | -3600 | -46.15%
Facilities & Capital Programs - Admin | Non-RAMP | 108.7441 | 138.1441 | -29.4 | -21.28% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
Re Resources | Non-RAMP | 248.1375 | 525.0118 | -276.8743 | -52.74% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year
Facilities Operations South Manager | Non-RAMP | 658.1553 | 525.1186 | 133.0367 | 25.33% |  | 4 FTE | 4 FTE | 0 | 0%
RB Data Center | Non-RAMP | 723.1483 | 427.36 | 295.7883 | 69.21% |  | 12,000sq' | 7,100sq' | 4900 | 69.01%
Re Planning-Mac | Non-RAMP | 452.9482 | 12.0729 | 440.8753 | 3652% |  | Units not available for this workpaper because there is no single number of like units that would be comparable year over year

## A&G
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - O&M Variance Tables
3.D. Administrative & General
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Administrative & General |  | 77400.0164 | 59987.7554 | 17412.261 | 29.03%
Accounting & Finance, Legal, Regulatory Affairs, External Affairs |  | 633 | 795 | -162 | -20.38%
Operations Cost Center -USS-Controllers-Business Controls | Non-RAMP | 633 | 260 | 373 | 143.5% |  | 3 FTE | 3 FTE | 0 | 0%
Operations Cost Center -USS-Controllers-Business Controls | Consulting expertise to improve records management program | 0 | 535 | -535 | -100%
Sub-Total Operations Cost Center -USS-Controllers-Business Controls |  | 633 | 795 | -162 | -20.38%
Compensation & Benefits |  | 161 | 279 | -118 | -42.29% |  | Units unavailable because this workpaper does not have a single number of like units that would be comparable year over year
Health Benefits - Emp Assistance Program | Non-RAMP | 161 | 279 | -118 | -42.29%
Corporate Center - General Administration |  | 72520 | 51709 | 20811 | 40.25% | Yes | Units not available for this workpaper because there is no single number of like units that would be comparable year over year; Corporate Center is considered Outside Services and does not report any FTE units.
SECC Outside Services Employees - F923.1 | Non-RAMP | 70095 | 49045 | 21050 | 42.92% | Yes
SECC Outside Services Employees - F923.1 | Records Management | 103 | 103 | 0 | 0%
SECC Outside Services Employees - F923.1 | Workplace Violence/Corporate Security | 1787 | 1291 | 496 | 38.42%
SECC Outside Services Employees - F923.1 | Cybersecurity | 535 | 1270 | -735 | -57.87%
Sub-Total SECC Outside Services Employees - F923.1 |  | 72520 | 51709 | 20811 | 40.25% | Yes
Risk Management |  | 4086.0164 | 7204.7554 | -3118.739 | -43.29%
Risk Management | Non-RAMP | 1930.631 | 4124.2377 | -2193.6066 | -53.19% |  | 1 FTE | 1 FTE | 0 | 0%
VP Enterprise Risk Management | Non-RAMP | 190.5645 | 460.4804 | -269.9159 | -58.62% |  | 2 FTE | 2 FTE | 0 | 0%
Operations Risk Management SDG&E | Non-RAMP | 1964.8209 | 2620.0373 | -655.2164 | -25.01% |  | 1 FTE | 1 FTE | 0 | 0%

## HR
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - O&M Variance Tables
3.E. Human Resources Dept, Safety, LTD & WC
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Human Resources Dept, Safety, LTD & WC |  | 7016.8306 | 7872.7538 | -855.9231 | -10.87%
Safety, Wellness & Disability Services | Non-RAMP | 0 | 0 | 0 | 0%
Safety, Wellness & Disability Services | Safety Training, Workshops and campaigns | 1712 | 1358.313 | 353.687 | 26.04%
Safety, Wellness & Disability Services | AED Maintenance | 17 | 42.9098 | -25.9098 | -60.38%
Safety, Wellness & Disability Services | OSHA Voluntary Protection Programs | 3 | 53.6372 | -50.6372 | -94.41%
Safety, Wellness & Disability Services | VPP Application and Implementation | 0 | 107.2745 | -107.2745 | -100%
Safety, Wellness & Disability Services | Contractor Safety Database | 18 | 42.9098 | -24.9098 | -58.05%
Safety, Wellness & Disability Services | Program Manager FY Impact | 115 | 134.0931 | -19.0931 | -14.24% |  | 1 FTE | 1 FTE | 0 | 0%
Safety, Wellness & Disability Services | Contractor Safety Program Analyst | 88 | 80.4559 | 7.5441 | 9.377% |  | 1 FTE | 1 FTE | 0 | 0%
Sub-Total Safety, Wellness & Disability Services |  | 1953 | 1819.5932 | 133.4068 | 7.332% |  | Except where noted, units not available for this WP because there is no single number of like units that would be comparable year over year
Organizational Effectiveness | Non-RAMP | 1780.4278 | 1919 | -138.5722 | -7.221%
Organizational Effectiveness | Supervisor Effectiveness Training | 0 | 107 | -107 | -100%
Organizational Effectiveness | Working Foreman Training and Human Performance | 0 | 85 | -85 | -100%
Organizational Effectiveness | Workforce Planning Efforts / Supervisor Effectiveness Program | 42 | 241 | -199 | -82.57%
Organizational Effectiveness | Training |  | 0 | 0 | 0%
Sub-Total Organizational Effectiveness |  | 1822.4278 | 2352 | -529.5722 | -22.52% |  | Units unavailable because this workpaper does not have a single number of like units that would be comparable year over year
Offices Of The President And COO | Non-RAMP | 1489.9463 | 1707.633 | -217.6867 | -12.75% |  | Units unavailable because this workpaper does not have a single number of like units that would be comparable year over year
SDG&E Field Safety | Field Safety Advisor | 885.7675 | 1037.6301 | -151.8626 | -14.64% |  | 1 FTE | 1 FTE | 0 | 0%
Safety Compliance | Increased substance abuse prevention, testing and contractor monitoring | 585.8697 | 642.3221 | -56.4523 | -8.789% |  | Units unavailable because this workpaper does not have a single number of like units that would be comparable year over year
Employee Assistance Program (EAP) And Wellness Programs | Non-RAMP | 279.8193 | 313.5754 | -33.7561 | -10.76% |  | Units unavailable because this workpaper does not have a single number of like units that would be comparable year over year

## BalProgO
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - O&M Variance Tables
4.A. Balanced Program Direct O&M Expenses
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
TIMP | Assessments of transmission pipelines in High Consequence Areas (49 CFR Part 192 Subpart O) to evaluate and remediate threats and minimize risk. | 7682.4525 | 5336.3539 | 2346.0986 | 43.96% | Yes | 7 ILI 5 ECDA | 1 ILI 9 ECDA | 6 -4 | 600% 44% | Yes Yes
DIMP | Programs in place to minimize integrity risks to distribution pipelines and minimize infrastructure damage. | 1386.2152 | 6421.3312 | -5035.116 | -78.41% | Yes | Units not available for this Witness Area because there is no single number of like units that would be comparable year over year
Vegetation Management (Tree Trimming) | Programs to inspect and maintain trees in SDG&E’s service territory that have the potential to encroach within the minimum required compliance distance between vegetation and overhead power lines. | 34509 | 24168.4692 | 10340.5308 | 42.79% | Yes | Units not available for this workpaper because there is no single number of like units that would be comparable year over year

## EDC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - Capital Variance Tables
1.A. Electric Distribution
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Electric Distribution |  | 427725 | 634326 | -206601 | -32.57% |  | Unless specified above, units not available for this workpaper because there is no single number of like units that would be comparable year over year.
Field Shunt Capacitors | Non-RAMP | 27 | 660 | -633 | -95.91%
Rancho Carmel 3rd Bank & Cir 937 & 938 | Non-RAMP | 80 | 0 | 80 | 100%
Mira Sorrento 138/12KV Substation | Non-RAMP | 10 | 0 | 10 | 100%
Ocean Ranch 69/12KV Substation | Non-RAMP | 5919 | 16365 | -10446 | -63.83% | Yes
Substation 12kV Capacitor Upgrades | Non-RAMP | 0 | 1038 | -1038 | -100% |  | 0 | 4 Capacitor banks installed | -4 | -100%
C1139 Santee - New circuit | Non-RAMP | 2 | 0 | 2 | 100%
Jamacha New Bank & New 12KV Circuit | Non-RAMP | 4 | 5821 | -5817 | -99.93% | Yes
Doheny Desalination 15MW Project | Non-RAMP | 0 | 411 | -411 | -100%
Wabash Canyon Sub 60/12kV Bank 32 | Non-RAMP | 612 | 0 | 612 | 100% |  | 1 Substation bank | 0 | 1 | 100%
Distribution System Capacity Improvement | Non-RAMP | 3288 | 1948 | 1340 | 68.79%
Sub-Total Capacity/Expansion |  | 9942 | 26243 | -16301 | -62.12% | [6 empty] | Row missing from pg A-14/A-15
Electric Distribution Tools/Equipment | Non-RAMP | 1436 | 1166 | 270 | 23.16% | [6 empty] | Row missing from pg A-14/A-15
Sub-Total Equip/Tools/Misc. |  | 1436 | 1166 | 270 | 23.16%
RAMP Base - Corrective Maint Program (CMP) | Inspection, Repair, Maintenance & Replacement Programs | 13921 | 12144 | 1777 | 14.63% |  | 1,667 Padmounted transformers and terminators | 1,454 Padmounted transformers and terminators | 213 | 14.65%
RAMP Base - DOE Switch/Manhole Replacement | Distribution Switch Maintenance Program | 8684 | 6113 | 2571 | 42.06% |  | 390 Manhole and handhole vault repairs and switches | 315 Manhole and handhole vault repairs and switches | 75 | 23.81% | Yes
RAMP Base - Replacement of Live Front Equipment | Live Front Transformer and Terminator Replacement | 165 | 770 | -605 | -78.57%
Aerial Marking for Safety | Non-RAMP | 0 | 134 | -134 | -100%
RAMP Base -– Annual Pole Reinforcement (Non-WMP) | GO165: Distribution Inspect and Repair program | 7332 | 8107 | -775 | -9.56% |  | 511 poles replaced | 565 poles replaced | -54 | -9.558%
Sub-Total Mandated |  | 30102 | 27268 | 2834 | 10.39%
Electric Meters & Regulators | Non-RAMP | 3839 | 5166 | -1327 | -25.69% |  | 22,220 Meters purchased | 29,903 Meters purchased | -7683 | -25.69%
Transformers | Non-RAMP | 22706 | 24415 | -1709 | -7% |  | 5,017 Transformers purchased | 5,395 Transformers purchased | -378 | -7.006%
Sub-Total Materials |  | 26545 | 29581 | -3036 | -10.26%
Reliability/Improvements Capital Projects | Non-RAMP | 1660 | 1764 | -104 | -5.896%
Management of Overhead Distribution Service | Non-RAMP | 6902 | 7125 | -223 | -3.13%
Management of Underground Distribution Service | Non-RAMP | 3614 | 3926 | -312 | -7.947%
Reactive Small Capital Projects | Non-RAMP | 985 | 2058 | -1073 | -52.14%
RAMP Base - Cable Replacement | Proactive cable replacement | 5404 | 17495 | -12091 | -69.11% | Yes
RAMP Incremental Capital Restoration of Service | Capital improvements | 10815 | 12929 | -2114 | -16.35%
Planned Cable Replacements | Non-RAMP | 858 | 0 | 858 | 100%
CMP-D1144756-SCADA | Non-RAMP | 6 | 0 | 6 | 100%
Shadow Ridge-Install 3rd Bank & Cir 937 & 938 | Non-RAMP | 5 | 0 | 5 | 100%
SF6 DOE Work | Non-RAMP | 278 | 0 | 278 | 100%
Rebuild Pt Loma Substation | Non-RAMP | 113 | 0 | 113 | 100%
Emergency Substation Equipment | Non-RAMP | 1 | 56 | -55 | -98.21%
RAMP Incremental - 4 kV Modernization - Distribution | Overhead distribution modernization and hardening | 0 | 4269 | -4269 | -100% |  |  | Unable to impute authorized units
Clairemont Substation Rebuild | Non-RAMP | -12 | 0 | -12 | -100%
Ramp Base - Install SCADA on Line Capacitors | Expand and Maintain Distribution Advanced SCADA infrastructure | 206 | 5952 | -5746 | -96.54% | Yes | 4 Capacitors | Unable to impute authorized units
Sewage Pump Station Rebuilds RAMP Incremental | Rebuild and repair aging infrastructure | 352 | 0 | 352 | 100% |  | 3 Transformers | 0 | 3 | 100% | Yes
RAMP Base - Weather Station Adv Detection | Advanced Detection | 0 | 1111 | -1111 | -100%
RAMP Base - Condition Based Maintenance - Smart Grid | Conditioned Based Monitoring System | 572 | 1738 | -1166 | -67.09% |  | 50 Transformers | 145 Transformers | -95 | -65.52% | Yes
Rebuild Kearny 69/12kV Substation | Non-RAMP | 2607 | 0 | 2607 | 100% |  | 4 Transformers | 0 | 4 | 100%
New Vine 69/12KV Substation | Non-RAMP | 648 | 0 | 648 | 100%
Streamview 69/12KV Sub Rebuild-Pre Eng | Non-RAMP | 580 | 56 | 524 | 935.7%
Poway Substation Rebuild | Non-RAMP | 1351 | 0 | 1351 | 100% |  | 2 Transformers | 0 | 2 | 100%
Rancho Santa Fe Sub Fire Hardening | Non-RAMP | 1315 | 0 | 1315 | 100% |  | 19 Breakers | 0 | 19 | 100%
Vault Restoration | Non-RAMP | 0 | 1124 | -1124 | -100%
OIR Worst Circuits | Non-RAMP | 0 | 2812 | -2812 | -100%
Morro Hill Substation Rebuild - RAMP Post-Filing | Replaces existing and obsolete infrastructure | 0 | 4216 | -4216 | -100%
San Mateo Substation Rebuild (start in 2019) | Non-RAMP | 1226 | 0 | 1226 | 100%
SCADA Head-End Replacement | Non-RAMP | 4338 | 0 | 4338 | 100%
RTU Replacement Project RMS900 | Non-RAMP | 155 | 0 | 155 | 100% |  | 34 RTUs | 0 | 34 | 100%
Avocado Sub 69KV Rebuild | Non-RAMP | 1029 | 0 | 1029 | 100% |  | 1 Transofrmer | 0 | 1 | 100%
Substation Mod to Support FLSR | Non-RAMP | 43 | 0 | 43 | 100%
Electric Distribution Grid Analytics | Non-RAMP | 0 | 3710 | -3710 | -100%
4kV Modernization | Non-RAMP | 542 | 0 | 542 | 100% |  | 1 Substation |  | 1 | 100%
New Downtown 69/12kV Substation | Non-RAMP | 91 | 0 | 91 | 100%
Distribution Circuit Reliability Construction - RAMP | Expand and Maintain Distribution Advanced SCADA infrastructure | 527 | 5563 | -5036 | -90.53% | Yes | 5 Switches Replaced | Unable to impute authorized units
Power Quality Program | Non-RAMP | 27 | 0 | 27 | 100%
Replace Obsolete Substation Equipment - RAMP | Substation rebuild/replacements based on operational significance and SDG&E reliability standards | 49 | 17023 | -16974 | -99.71% | Yes
Sub-Total Reliability/Improvements |  | 46287 | 92927 | -46640 | -50.19%
SF6 Switch Replacement | Replace with new technology | 3504 | 7918 | -4414 | -55.75% |  | 14 Switches | Unable to impute authorized units
C589 & C753 Damaged Pole Replacements | Non-RAMP | 7 | 0 | 7 | 100%
Substation Security Proj under $500K | Non-RAMP | 17 | 0 | 17 | 100%
Meteorology - Fire Behavior Modeling | Non-RAMP | 7 | 0 | 7 | 100%
Elect Integrity - RAMP (Non-WMP) | Wire Correction, Switch Replacement and Underground Connector Upgrade Program | 177 | 52489 | -52312 | -99.66% | Yes | 5 Switches Replaced | Unable to impute authorized units
RTU Modernization - RAMP Incremental - SCADA Master Modernization | Modernize Equipment | 0 | 4159 | -4159 | -100%
NCW New Bank 32 RAMP Incremental - Undergrounding New Circuits | Undergrounding | 0 | 4319 | -4319 | -100%
Rancho Santa Fe C1001 Wire Down Mit | Non-RAMP | -64 | 0 | -64 | -100%
Mobile Command Trailers (MCT) | Non-RAMP | 8 | 0 | 8 | 100%
Twin Engine Helicopter | Purchase a Twin-Engine Helicopter | 218 | 0 | 218 | 100% |  | 3 Communication nodes installed | 0 | 3 | 100% | Yes
Tee Modernization Program | Non-RAMP | 573 | 6441 | -5868 | -91.1% | Yes | 60 Tees | Unable to impute authorized units
Proactive Dead Front Terminator Deploy | Non-RAMP | 12 | 0 | 12 | 100%
Aerial Mesh Network Expansion | Non-RAMP | 141 | 0 | 141 | 100% |  | 4 Communication nodes installed | 0 | 4 | 100%
Sub-Total Safety & Risk Management |  | 4600 | 75326 | -70726 | -93.89%
Advanced Energy Storage | Non-RAMP | 0 | 11241 | -11241 | -100% | Yes
Borrego Microgrid 2.0 | Non-RAMP | 61 | 0 | 61 | 100%
AB2868 Energy Storage | Non-RAMP | -58 | 0 | -58 | -100%
Safety Enhancements for Battery | Non-RAMP | 118 | 0 | 118 | 100%
Sub-Total DER Integration |  | 121 | 11241 | -11120 | -98.92%
Elect Transm Line Reliability Projects | Non-RAMP | 2600 | 1124 | 1476 | 131.3% |  | 147 Poles replaced | Unable to impute authorized units
Transmission Substation Reliability | Non-RAMP | 0 | 111 | -111 | -100%
Orange County Long Range Plan - SOCRE | Non-RAMP | 6021 | 4884 | 1137 | 23.28%
Fiber Optic for Relay Protect & Telecom | Non-RAMP | 35 | 440 | -405 | -92.05% |  | 21 Distribution underbuilt circuit miles | 0 | 21 | 100% |  | Row missing from pages A-22/A-23
TL676-Mission to Mesa Heights Reconductor | Non-RAMP | 1894 | 0 | 1894 | 100% |  | 1 Distribution underbuilt circuit miles
Los Coches Substation 138/69kV Rebuild | Non-RAMP | 1 | 0 | 1 | 100% |  | 0
TL663 Mission to Kearny Reconductor | Non-RAMP | 342 | 0 | 342 | 100% |  | 0
TL600 – Reliability Pole Replacements | Non-RAMP | 2 | 0 | 2 | 100% |  | 0
TL674A Del Mar Reconfigure/TL666D RFS | Non-RAMP | 1 | 0 | 1 | 100% |  | 0
TL690A Pendleton South W2S | Non-RAMP | 12 | 0 | 12 | 100% |  | 0
Rose Canyon TL617 Tap Removal | Non-RAMP | 2 | 0 | 2 | 100% |  | 0
Miguel Substation 230kV Rebuild | Non-RAMP | 203 | 0 | 203 | 100%
Sub-Total Transm/FERC Driven Projects |  | 11113 | 6559 | 4554 | 69.43%
Sub-Total ED Non-Balanced Projects |  | 130146 | 270311 | -140165 | -51.85%
RAMP Base – Annual Pole Reinforcement (WMP) | GO165: Distribution Inspect and Repair program | 10413 | 9404 | 1009 | 10.73% |  | 726 Poles replaced | 656 Poles replaced | 70 | 10.67%
RAMP Base - Wireless Fault Indicators | Non-RAMP | 895 | 4884 | -3989 | -81.67% |  | 535 Wireless fault indicators | Unable to impute authorized units
TL685 Fiber Optics Warner/Santa Ysabel Subs | Non-RAMP | 14 | 0 | 14 | 100% |  | 0 Distribution underbuilt circuit miles
Distribution Circuit Reliability - RAMP Base - FiRM | System Hardening | 90663 | 64950 | 25713 | 39.59% | Yes | 1,701 Circuit miles | 1,227 Circuit miles | 474 | 38.63% | Yes
Fire Threat Zone Adv Protect & SCADA Upgrade | Inspection Repair Maintenance & Replacement Programs | 4064 | 13496 | -9432 | -69.89% | Yes | 8 Circuits | 8 Circuits | 0 | 0%
Elect Integrity – RAMP (WMP) | Wire Safety Enhancement (WiSE) Program | 4624 | 6421 | -1797 | -27.99% |  | 5.6 Distribution circuit miles | 5.1 Distribution circuit miles | 0.5 | 9.804%
Accelerated Pole Loading - RAMP Base | Inspection Repair Maintenance & Replacement Programs | 31327 | 45447 | -14120 | -31.07% | Yes | 699 Poles replaced | 1,800 Poles replaced | -1101 | -61.17% | Yes
HFTD Fuse Replacements | Non-RAMP | 3711 | 0 | 3711 | 100% |  | 2,490 Fuses replaced | 0 | 2490 | 100%
PSPS Engineering Enhancements | Non-RAMP | 1411 | 0 | 1411 | 100% |  | 7 Switches | 0 | 7 | 100%
HTD Undergrounding | Non-RAMP | 194 | 0 | 194 | 100% |  | 1 Circuit miles | 0 | 1 | 100%
Meteorology – SDG&E Weather Network | Non-RAMP | 632 | 0 | 632 | 100% |  | 70 Weather stations | 0 | 70 | 100%
Meteorology – Fire Science Enhancements | Non-RAMP | 315 | 0 | 315 | 100% |  | 47 Registered users | 0 | 47 | 100%
Backup Power for Resiliency | Non-RAMP | 205 | 0 | 205 | 100%
SDG&E ENS Enhancements | Non-RAMP | 880 | 0 | 880 | 100% |  | 390 Hours of enhancements |  | 390 | 100%
CNF – RAMP | System Hardening | 24943 | 45003 | -20060 | -44.57% | Yes | 28 Distribution circuit miles | 43 Distribution circuit miles | -15 | -34.88% | Yes
TL649 Otay-San Ysidro-Border SW Pole Repl - RAMP Incremental | Inspection Repair Maintenance & Replacement Programs | 1362 | 0 | 1362 | 100% |  | 4 Distribution underbuilt circuit miles | 4 Distribution underbuilt circuit miles | 0 | 0%
TL697 San Luis Rey Wood to Steel - RAMP Incremental | Non-RAMP | 1 | 0 | 1 | 100%
TL6916 Sycamore Canyon to Scripps Wood to Steel | Non-RAMP | 0 | 290 | -290 | -100% |  | 0 Distribution underbuilt circuit miles | 1 Distribution underbuilt circuit miles | -1 | -100%
TL694 Wood To Steel | Non-RAMP | 0 | 857 | -857 | -100%
TL698 Monserate - Avocado Wood to Steel | Non-RAMP | 57 | 857 | -800 | -93.35% |  | 0.33 Distribution underbuilt circuit miles | 5 Distribution underbuilt circuit miles | -4.67 | -93.4%
Sub-Total WMP Projects (Balanced Costs) |  | 175711 | 191609 | -15898 | -8.297%
Local Engineering Pool - Electric Distribution | Non-RAMP | 91555 | 102725 | -11170 | -10.87% | Yes
Local Engineering Pool - ED RAMP | Works Standards and Methods | 1032 | 849 | 183 | 21.55%
Sub-Total Local Engineering Pool – Electric Distribution |  | 92587 | 103574 | -10987 | -10.61% | Yes
Local Engineering Pool - Substation | Non-RAMP | 2328 | 51296 | -48968 | -95.46% | Yes
Department Overhead Pool | Non-RAMP | 10924 | 7594 | 3330 | 43.85%
Contract Admin Pool - RAMP Base | Administration of Projects performed by Contractors | 16029 | 9942 | 6087 | 61.23% | Yes
Sub-Total ED Overhead Pools (Balanced Costs) |  | 121868 | 172406 | -50538 | -29.31%
Sub-Total ED Balanced Projects |  | 297579 | 364015 | -66436 | -18.25%

## EGC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - Capital Variance Tables
1.B. Electric Generation
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Electric Generation |  | 12314 | 12971 | -657 | -5.065% |  | Units are unavailable because these workpapers do not have a single number of like units that would be comparable year over year.
Generation Capital Tools & Test Eqpt. | Non-RAMP | 56.0681 | 296.7525 | -240.6844 | -81.11%
Miramar | Non-RAMP | 975.3724 | 2784.078 | -1808.7056 | -64.97% | [6 empty] | Missing row pgs A-39/A-40
Palomar Plan Operational Improvements | Non-RAMP | 5751.4843 | 5774.2641 | -22.7798 | -0.3945%
Desert Star Energy Ctr Oper. Enhance | Non-RAMP | 3579.3715 | 3626.8551 | -47.4836 | -1.309% | [6 empty] | Missing row pg A-40
Cuyamaca Peak Energy Plant Oper Enhance | Non-RAMP | 1946.0469 | 488.8323 | 1457.2146 | 298.1%
Ramona Solar Plant Oper Enhance | Non-RAMP | 5.9001 | 0 | 5.9001 | 100%

## GDC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - Capital Variance Tables
2.A. Gas Distribution
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas Distribution |  | 56763.1925 | 110069.4373 | -53306.2449 | -48.43% |  |  | Unless noted, units not available for this Witness Area because there is no single number of like units that would be comparable year over year.
New Business | Non-RAMP | 7283.7658 | 8780.44 | -1496.6742 | -17.05% |  | 1,535 projects | Unable to impute authorized units
New Business - RAMP | Odorization of gas | 0 | 50.9175 | -50.9175 | -100%
Sub-Total New Business |  | 7283.7658 | 8831.3575 | -1547.5917 | -17.52%
System Minor Additions, Relocations, & Retirements | Non-RAMP | 3760.6303 | 3904.8065 | -144.1762 | -3.692% |  | 303 projects | Unable to impute authorized units
System Minor Additions, Relocations, & Retirements - RAMP | Locate and Mark | 6 | 274.9545 | -268.9545 | -97.82% |  | 303 tickets | Unable to impute authorized units
Sub-Total System Minor Additions, Relocations, & Retirements |  | 3766.6303 | 4179.761 | -413.1307 | -9.884%
Meters and Regulator Materials | Non-RAMP | 5684.8267 | 8240.7145 | -2555.8878 | -31.02% | Yes | 31,843 meters/regulators purchased | Unable to impute authorized units
Pressure Betterment | Non-RAMP | 12.8446 | 1917.8925 | -1905.0479 | -99.33% | Yes | 1 project | Unable to impute authorized units
Easements | Non-RAMP | 36.8597 | 42.997 | -6.1373 | -14.27%
Franchise Relocations | Non-RAMP | 4665.9893 | 7541.4475 | -2875.4582 | -38.13% | Yes | 58 projects | Unable to impute authorized units
Tools and Equipment | Non-RAMP | 2797.6046 | 2143.061 | 654.5436 | 30.54%
Tools and Equipment | Training props | 114 | 367.7375 | -253.7375 | -69%
Sub-Total Tools and Equipment |  | 2911.6046 | 2510.7985 | 400.8061 | 15.96%
Code Compliance | Non-RAMP | 1451.8311 | 1328.381 | 123.4501 | 9.293%
Replacements of Mains and Services (Combine with RAMP) | Non-RAMP | 0 | 465.0465 | -465.0465 | -100% |  | 0 | Unable to impute authorized units
Replacements of Mains and Services - RAMP1 | Early Vintage Steel Replacement | 1795 | 8356.1275 | -6561.1275 | -78.52% | Yes | 3 mi replaced | Unable to impute authorized units
Replacements of Mains and Services - RAMP2 | Early Vintage Threaded Main Removal | 0 | 8356.1275 | -8356.1275 | -100% | Yes | 0 mi replaced | Unable to impute authorized units
Replacements of Mains and Services - RAMP3 | Pipeline Observations (Standby) | 0 | 14.7095 | -14.7095 | -100% |  | 0 projects | Unable to impute authorized units
Replacements of Mains and Services - RAMP4 | Leak Repair | 9247 | 1183.549 | 8063.451 | 681.3% | Yes | 334 projects | Unable to impute authorized units
Replacements of Mains and Services - RAMP5 | EPOCH Planned Replacement of Pipe | 0 | 2938.5055 | -2938.5055 | -100% | Yes | 0 mi replaced | Unable to impute authorized units
Sub-Total Replacements of Mains and Services |  | 11042 | 21314.0655 | -10272.0655 | -48.19% | Yes
Cathodic Protection | Non-RAMP | 4976.3707 | 2201.899 | 2774.4717 | 126% | Yes | 52 projects | Unable to impute authorized units
Regulator Station Improvements and Other | Non-RAMP | 416.6405 | 862.203 | -445.5625 | -51.68% |  | 4 projects | Unable to impute authorized units
Regulator Station Improvements and Other - RAMP | Improvements | 0 | 8913 | -8913 | -100% | Yes | 0 couplings removed | Unable to impute authorized units
Regulator Station Improvements and Other - RAMP | Improvements | 0 | 10495 | -10495 | -100% | Yes | 0 oil drips removed | Unable to impute authorized units
Regulator Station Improvements and Other - RAMP | Improvements | 0 | 8734 | -8734 | -100% | Yes | 0 buried vault pipes repaired or replaced | Unable to impute authorized units
Sub-Total Regulator Station Improvements and Other |  | 416.6405 | 29004.203 | -28587.5625 | -98.56% | Yes
GD Local Engineering Pool | Non-RAMP | 8735.301 | 1973.5242 | 6761.7768 | 342.6% | Yes
GD Local Engineering Pool | Local Engineering overhead costs associated with large RAMP proposed projects | 1988 | 8796.7575 | -6808.7575 | -77.4% | Yes
GD Local Engineering Pool | Improvements to Cathodic Protection reliability | 33 | 3789.3935 | -3756.3935 | -99.13% | Yes
GD Local Engineering Pool | Safety policies and Programs | 127 | 3569.252 | -3442.252 | -96.44% | Yes
GD Local Engineering Pool | Gas standards review | 58 | 59.8838 | -1.8838 | -3.146%
GD Local Engineering Pool | Operational QA/QC | 2037 | 337.2868 | 1699.7132 | 503.9% | Yes
Sub-Total GD Local Engineering Pool |  | 12978.301 | 18526.0978 | -5547.7969 | -29.95% | Yes
Cathodic Protection System Enhancement | Non-RAMP | 0 | 1736.8525 | -1736.8525 | -100% | Yes
Cathodic Protection System Enhancement - RAMP | Cathodic Protection | 1535.5281 | 2692.97 | -1157.4419 | -42.98% | Yes | 39 projects | Unable to impute authorized units
Sub-Total Cathodic Protection System Enhancement |  | 1535.5281 | 4429.8225 | -2894.2944 | -65.34% | Yes

## GE
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - Capital Variance Tables
2.B. Gas Engineering
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas Engineering |  | 495.4556 | 303.242 | 192.2136 | 63.39% |  | Units are unavailable because these workpapers do not have a single number of like units that would be comparable year over year.
GT Land Rights | Non-RAMP | 0 | 127.8595 | -127.8595 | -100%
GT Auxiliary Equipment | Non-RAMP | 129.2277 | 20.367 | 108.8607 | 534.5%
GT Capital Tools | Non-RAMP | 109.8892 | 61.101 | 48.7882 | 79.85%
GT Auxiliary Equipment | Non-RAMP | 0 | 11.315 | -11.315 | -100%
GT Supervision & Engineering Pool | Non-RAMP | 256.3386 | 82.5995 | 173.7391 | 210.3%

## GTC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - Capital Variance Tables
2.D. Gas Transmission
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Gas Transmission |  | 11405.6659 | 9252.5018 | 2153.1641 | 23.27% |  | Units not available for this WP because there is no single number of like units that would be comparable year over year.
New Gas Transmission Pipeline | Non-RAMP | -36.6419 | 2303.9603 | -2340.6022 | -101.6% | Yes
GT Relocation | Non-RAMP | 0 | 2.263 | -2.263 | -100%
GT Cathodic Protection | Requirements for corrosion control | 135.5585 | 208.196 | -72.6375 | -34.89%
GT M&R Stations | Non-RAMP | 3181.1239 | 548.7775 | 2632.3464 | 479.7% | Yes
GT Replacements | Non-RAMP | 1623.8759 | 0 | 1623.8759 | 100% | Yes
GT Replacements | HCA Class Location Follow-up Mitigation | 0 | 1702.9075 | -1702.9075 | -100% | Yes
Sub-Total GT Replacements |  | 1623.8759 | 1702.9075 | -79.0316 | -4.641%
Compressor Stations (415) | Non-RAMP | 3106.7267 | 1756.088 | 1350.6387 | 76.91% | Yes
Compressor Stations (435) | Non-RAMP | 3395.0229 | 2730.3095 | 664.7134 | 24.35%

## ITC_CYC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - Capital Variance Tables
3.B. Information Technology & Cyber Security
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
IT & Cyber Security |  | 92347.8253 | 125421.9372 | -33074.1119 | -26.37% |  | Units not available for these workpapers because there is no single number of like units that would be comparable year over year.
Sub-Total Information Technology |  | 90171.145 | 119976.9716 | -29805.8266 | -24.84%
IT - Enterprise - Application | Records Management | 6632.906 | 2152 | 4480.906 | 208.2%
IT - Enterprise - Application | Electric Infrastructure Integrity | 5158.281 | 0 | 5158.281 | 100% | Yes
IT - Enterprise - Application | Non-RAMP | 10995.9918 | 2080.9072 | 8915.0846 | 428.4% | Yes
Sub-Total IT Applications |  | 22787.1788 | 4232.9072 | 18554.2716 | 438.3% | Yes
IT - Enterprise - Network - RAMP | Records Management | 0 | 4494.4 | -4494.4 | -100%
IT - Enterprise - Network | Non-RAMP | 25482.2519 | 40655 | -15172.7481 | -37.32% | Yes
Sub-Total IT Network |  | 25482.2519 | 45149.4 | -19667.1481 | -43.56% | Yes
IT - Enterprise – Infrastructure | Non-RAMP | 25012.4968 | 2103.3792 | 22909.1176 | 1089% | Yes
IT - Enterprise – Infrastructure | Records Management | 12.78 | 0 | 12.78 | 100%
Sub-Total IT - Enterprise – Infrastructure |  | 25025.2768 | 2103.3792 | 22921.8976 | 1090% | Yes
Customer Services | Non-RAMP | 7810.6404 | 12016.902 | -4206.2615 | -35%
Locator Phase 2: USA Ticket Automation | Non-RAMP | 19.4174 | 0 | 19.4174 | 100%
Sub-Total IT Non-Balanced Projects |  | 81124.7655 | 63502.5884 | 17622.177 | 27.75% | Yes
IT WMP - Balanced | Non-RAMP | 9046.3796 | 56474.3832 | -47428.0036 | -83.98% | Yes
IT - Enterprise - Cyber - RAMP | Cyber Security | 2176.6803 | 5444.9656 | -3268.2853 | -60.02%

## SSC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - Capital Variance Tables
3.C. Support Services
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
Support Services - Real Estate, Land Services & Facilities |  | 22885.4502 | 65600.2624 | -42714.8122 | -65.11% |  | Units not available for these workpapers due to highly variable project scope and the absence of like units that would be comparable year over year.
Land Blanket | Non-RAMP | 159.4794 | 339.3272 | -179.8478 | -53%
Structures and Improvements | Non-RAMP | 4435.1969 | 5417.9992 | -982.8023 | -18.14%
Environmental/Safety Blanket | Facility improvements necessary to comply with safety and environmental code or regulations and also to implement best practices towards mitigating risk to either the environment or safety of employees or the public. | 2197.4673 | 2411.2456 | -213.7783 | -8.866%
Misc. Equipment Blanket | Non-RAMP | 830.7919 | 2320.234 | -1489.442 | -64.19%
Security Systems | Physical Security Systems | 3158.3206 | 4547.2092 | -1388.8886 | -30.54%
Infrastructure & Reliability | Non-RAMP | 3589.2542 | 5976.4284 | -2387.1742 | -39.94%
Remodel/Relocate/Reconfig Blanket | Non-RAMP | 4884.7041 | 25782.1256 | -20897.4215 | -81.05% | Yes
Business Unit Expansion/Miramar Welding Room Expansion | Non-RAMP | 2239.8281 | 3396.6428 | -1156.8147 | -34.06%
Archibus Business Systems Improvements | Non-RAMP | 1094.9477 | 566.2944 | 528.6533 | 93.35%
Mission Control Modernization | Modernization of Grid Control Centers | -101.873 | 0 | -101.873 | -100%
CP East IT Improvements | Non-RAMP | 645.0986 | 5558.4492 | -4913.3506 | -88.39%
RBDC Power Reliability Improvements | Non-RAMP | -247.7657 | 9284.3068 | -9532.0725 | -102.7% | Yes

## BalProgC
SDG&E and SoCalGas 2019 Risk Spending Accountability Report
Energy Division Data Request 01, Question 1
Attachment A - Capital Variance Tables
4.B. Balanced Program Direct Capital Expenses
WP Activity Description | RAMP Mitigation Activity | 2019 Actuals ($000) | 2019 Imputed Authorized ($000) | $ Variance ($000) | % Variance | Meets Variance Criteria? | 2019 Actual Units | 2019 Imputed Authorized Units | Unit Variance | % Unit Variance | Meets Variance Criteria?
TIMP & DIMP |  | 46743.7425 | 55443.5 | -8699.7575 | -15.69%
TIMP | TIMP ILI/ECDA | 5374.5489 | 4526 | 848.5489 | 18.75% |  | See O&M Section for TIMP units
DIMP | DIMP DREAMS | 41369.1936 | 50917.5 | -9548.3064 | -18.75% | Yes | 46 Miles | 27 Miles | 19 mi | 70.37% | Yes

## Var. Criteria
Variance Thresholds Requiring Variance Explanations as of 1/1/2020
SDG&E | O&M |  |  | Capital
| Criteria 1 | Criteria 2 |  | Criteria 1 | Criteria 2
| Anything Over | Greater than 20% AND min $ |  | Anything Over | Greater than 20% AND min $
Elect | 5000 | 2500 | 20% | 10000 | 5000 | 20%
Gas | 2500 | 500 | 20% | 5000 | 1000 | 20%
Other | 5000 | 2500 | 20% | 10000 | 5000 | 20%
SoCal Gas | O&M |  |  | Capital
| Criteria 1 | Criteria 2 |  | Criteria 1 | Criteria 2
| Anything Over | Greater than 20% AND min $ |  | Anything Over | Greater than 20% AND min $
Gas | 5000 | 1000 | 20% | 10000 | 2000 | 20%
Other | 5000 | 1000 | 20% | 10000 | 2000 | 20%