## Electric MAT Table Expense
Table 3-3 2024 RSAR 2023 GRC CYCLE ELECTRIC DISTRIBUTION EXPENSE COMPARISON BY MAT FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | C6 | C7 | D | E | F | G1 | G2 | H | I1 | I2 | J | K1 | K2 | L1 | L2 | L3 | L4 | M | N1 | N2 | O | P1 | P2 | Q | R1 | R2 | S1 | S2 | S3 | T | U | V1 | V2 | V3 | W | X
[13 empty] | Imputed Adopted Costs |  |  | Actual Costs | [9 empty] | Imputed Annual Units |  |  | Actual Annual Units | [9 empty] | Forecast
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name | MAT | MAT Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program / Project Life (years) | Program / Project Year | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs | Imputed Cost for 2023 GRC Cycle to Date ($) (G1+G2) | 2023 Actual Costs | 2024 Actual Costs | Actual Cost for 2023 GRC Cycle to Date ($) (I1+I2) | Difference for 2024 ($) (I2-G2) | Difference for 2023 GRC Cycle to Date ($) (J-H) | Spending Percent Variance for 2024 (%) (K1)/G2*100) | Spending Percent Variance for 2023 GRC Cycle (%) (K2/H*100) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | Unit Type | 2023 Imputed Adopted Units | 2024 Imputed Adopted Units | Imputed Units for 2023 GRC Cycle to Date | 2023 Actual Units | 2024 Actual Units | Actual Units for 2023 GRC Cycle to Date | Difference for 2024 (# of Units) (P2-N2) | Difference for 2023 GRC Cycle to Date (# of Units) (Q-O) | Unit Percent Variance for 2024 (%) (R1/N2*100) | Percent Variance for 2023 GRC Cycle to Date (%) (R2/O) | Unit Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | 2024 Unit Variance Explanation | Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T) | Status | 2024 Completion Status Statement
1 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | SRM Total | SRM Total | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | No | On-going | Annual | 193108.353 | 196495.5021 | 389603.8551 | 31503.0268 | 41146.9351 | 72649.9619 | -155348.567 | -316953.8932 | -79.06% | -81.35% | YES | YES | # of wildfire cameras | 10 | 10 | 20 | 0 | 0 | 0 | -10 | -20 | -100% | -100% | YES | Program expenses were below imputed regulatory values because several programs that were forecast in AB6 are being recorded in new MAT codes under MWC WF, which was created after the 2023 GRC was filed. The following program expenses were forecast in MAT AB6 in the 2023 GRC and are reflected in the imputed regulatory values: Emergency Preparedness and Response (EP&R), Cameras, Public Safety Power Shutoffs (PSPS), the Safety and Infrastructure Protection Team (SIPT), and Wildfire Mitigation Support. Actual expenses for EP&R remain recorded in MAT AB6 with a small portion also recorded to MAT IG#. Actual expenses for Cameras, EPSS, PSPS, SIPT and Weather Station Maintenance are recorded in various MAT codes under MWC WF and are explained further below. The difference between the imputed regulatory value and actual expenses for the EP&R portion remaining in MAT AB6 is below the variance threshold. | Actual units were lower than imputed units because actual units are reported in MAT Code WFC. There were 10 cameras forecasted in AB6 and 25 completed in WFC in 2024. See MAT WFC for an explanation of why PG&E completed more units than forecasted. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The following wildfire mitigation initiatives were forecast in MAT AB6 in the 2023 GRC and are reflected in the imputed regulatory values: EP&R, Cameras, EPSS, PSPS, SIPT, and Wildfire Mitigation Support. EP&R remains under MAT AB6 with a small portion also in MAT IG#. Cameras, EPSS, PSPS, SIPT and Weather Station Maintenance actual costs are reported in various MATs in MWC 3U and are explained in further detail in MWC WF below. The scope and budget is represented as under because for the remainder of the GRC cycle MAT AB6 will show under costs and units because the actuals are captured in MWC WF. Otherwise the programs forecasted in AB6 and remaining as recorded in AB6 are proceeding as planned.
2 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C000: EP&R Controls | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 5397.4967 | 5461.0783 | 10858.5751 | 3670.2988 | 5914.8362 | 9585.135 | 453.7579 | -1273.44 | 8.309% | -11.73% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C001: Situational Awareness and Forecasting Initiatives - SOPP Improvements | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 2206.5298 | 2232.5224 | 4439.0522 | 0 | 0 | 0 | -2232.5224 | -4439.0522 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
4 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C002: Situational Awareness and Forecasting Initiatives - WSOC | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 7808.5788 | 7900.5626 | 15709.1415 | 4644.7696 | 5824.2497 | 10469.0193 | -2076.3129 | -5240.1222 | -26.28% | -33.36% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C004: EP&R Field Operations Technology | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 0.10075 | 0.10075 | 0.10075 | 0.10075 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C005: EP&R Field Operations | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 634.8764 | 642.3551 | 1277.2316 | 610.5359 | 0 | 610.5359 | -642.3551 | -666.6956 | -100% | -52.2% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C006: EP&R Distribution Support Headcount | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 7506.5454 | 7594.9713 | 15101.5167 | 4577.3593 | 0 | 4577.3593 | -7594.9713 | -10524.1574 | -100% | -69.69% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-M000: EP&R Mitigations | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 4416.132 | 4468.1533 | 8884.2852 | 3005.8982 | 4839.4114 | 7845.3096 | 371.2581 | -1038.9756 | 8.309% | -11.69% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M005: Public Safety Power Shutoff - PSPS Event (Distribution) | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 75968.2247 | 77374.8368 | 153343.0615 | 0 | 0 | 0 | -77374.8368 | -153343.0615 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 43987.727 | 44802.1952 | 88789.9222 | 0 | 1074.1592 | 1074.1592 | -43728.036 | -87715.763 | -97.6% | -98.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07B: Situational Awareness and Forecasting Initiatives - Weather Station | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 1836.2456 | 1870.2451 | 3706.4907 | 0 | 0 | 0 | -1870.2451 | -3706.4907 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07D: Situational Awareness and Forecasting Initiatives - Cameras | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 8568.7652 | 8727.4227 | 17296.1879 | 0 | 0 | 0 | -8727.4227 | -17296.1879 | -100% | -100% | N/A | N/A | # of wildfire cameras | 10 | 10 | 20 | 0 | 0 | 0 | -10 | -20 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07E: Situational Awareness and Forecasting Initiatives - Satellite Fire Detection | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 376.812 | 383.789 | 760.601 | 0 | 0 | 0 | -383.789 | -760.601 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07G: Situational Awareness and Forecasting Initiatives - Partial Voltage Detection | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 242.23 | 246.7151 | 488.945 | 0 | 0 | 0 | -246.7151 | -488.945 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07I: Situational Awareness and Forecasting Initiatives - Advanced Fire Modeling | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 6602.7424 | 6724.9974 | 13327.7399 | 0 | 0 | 0 | -6724.9974 | -13327.7399 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
16 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07J: Situational Awareness and Forecasting Initiatives - Meteorology | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 455.329 | 463.7597 | 919.0887 | 0 | 10.8834 | 10.8834 | -452.8763 | -908.2053 | -97.65% | -98.82% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07K: Situational Awareness and Forecasting Initiatives - Fire Potential Index | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 180.8615 | 184.2103 | 365.0718 | 0 | 0 | 0 | -184.2103 | -365.0718 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
18 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M008: Safety and Infrastructure Protection Teams | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 26919.2562 | 27417.6877 | 54336.9439 | 0 | 0 | 0 | -27417.6877 | -54336.9439 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M009: Community Wildfire Safety Program PMO | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 14994.1649 | 18500.3762 | 33494.541 | 18500.3762 | 33494.541 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
20 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M017: System Hardening - Remote Grid | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 18.7605 | 18.7605 | 18.7605 | 18.7605 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 4964.158 | 4964.158 | 4964.158 | 4964.158 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
22 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | SRM Total | SRM Total | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | No | On-going | Annual | 63301.3873 | 63700.064 | 127001.4513 | 76372.3953 | 90989.645 | 167362.0403 | 27289.581 | 40360.589 | 42.84% | 31.78% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values due to a reduction in funding to this program in the 2023 GRC Final Decision. PG&E's forecast for AB# miscellaneous expense for Electric Distribution in the 2023 GRC was reduced in the 2023 GRC Final Decision. PG&E continues to incur costs for the support activities forecasted in the 2023 GRC as well as some new activities, for amounts at and above PG&E's GRC forecast. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. MAT AB# tracks costs for miscellaneous ongoing programs that include several activities that support electric operations including but not limited to Regulatory Compliance and Quality Assurance, the Corrective Actions Program, Data Response Unit, and the Compliance Group. PG&E expects to continue to be over the adopted amount for this program in the 2023 GRC cycle.
23 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Distribution Overhead | DOVHD-M005: Additional Asset Data Capture | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 688.1409 | 682.8827 | 1371.0236 | 0 | 0 | 0 | -682.8827 | -1371.0236 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
24 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Distribution Overhead | DOVHD-M009: Improved Distribution Risk Model | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 802.9983 | 796.9055 | 1599.9037 | 0 | 0 | 0 | -796.9055 | -1599.9037 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
25 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M002: System Hardening | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 689.195 | 689.195 | 689.195 | 689.195 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
26 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 2037.0957 | 2074.8141 | 4111.9099 | 0 | 0 | 0 | -2074.8141 | -4111.9099 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
27 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M009: Community Wildfire Safety Program PMO | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 14007.291 | 14266.6471 | 28273.9381 | 10987.5866 | 5380.278 | 16367.8647 | -8886.3691 | -11906.0734 | -62.29% | -42.11% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
28 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M07F: Situational Awareness and Forecasting Initiatives - Sensor IQ | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 3936.4324 | 4009.3186 | 7945.751 | 6e-05 | 0 | 6e-05 | -4009.3186 | -7945.7509 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
29 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M017: System Hardening - Remote Grid | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 1523.7359 | 1551.9491 | 3075.685 | 2494.8968 | 2867.3509 | 5362.2477 | 1315.4018 | 2286.5627 | 84.76% | 74.34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
30 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M002: System Hardening | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 0 | 0 | 0 | 877.683 | 422.072 | 1299.755 | 422.072 | 1299.755 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
31 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Distribution Overhead | DOVHD-M011: Remote Grid | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 1523.7359 | 1551.9491 | 3075.685 | 0 | 0 | 0 | -1551.9491 | -3075.685 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
32 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | POST-GRC: Post-GRC Mitigation | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 0 | 0 | 0 | 24.9751 | 1.0327 | 26.0079 | 1.0327 | 26.0079 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
33 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 40305.3969 | 40317.1647 | 80622.5616 | 61987.2537 | 81629.7164 | 143616.9701 | 41312.5517 | 62994.4085 | 102.5% | 78.13% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
34 | Expense | Electric Distribution | AR | Read & Investigate Meters | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 10437.6496 | 10773.4238 | 21211.0734 | 9189.4821 | 9666.4487 | 18855.9309 | -1106.9751 | -2355.1426 | -10.28% | -11.1% | NO | NO | Field orders | 854733 | 854733 | 1709466 | 765469 | 705075 | 1470544 | -149658 | -238922 | -17.51% | -13.98% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
35 | Expense | Electric Distribution | AT | Emerging Technology | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 21 | No | On-going | Annual | 2185.0619 | 2210.4564 | 4395.5183 | 0 | 0 | 0 | -2210.4564 | -4395.5183 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to fund Research and Development (R&D) Emerging Technology public partnerships. Actual research and development (R&D) support costs that were adopted in MAT Code AT# in the 2023 GRC were recorded in MAT Code AB#. PG&E incurred approximately two million dollars in 2023 & 2024, recorded in MAT AB#, for emerging technology utility partnerships, which is aligned with the GRC-adopted amounts.
36 | Expense | Electric Distribution | BA | E Dist Operate System | BAF | Genl Operate | SRM Total | SRM Total | Ex 4, Ch 4.6 Ex 4, Ch 7 | No | On-going | Annual | 27814.8879 | 28667.4965 | 56482.3843 | 18147.8013 | 19098.6238 | 37246.425 | -9568.8727 | -19235.9593 | -33.38% | -34.06% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses were below imputed regulatory values due to some work forecast in this MAT code being recorded to routine and major emergency. In addition, weather conditions were favorable in 2024 and weather related costs, like distribution operations to support storms, heat events and EPSS, were lower than forecasted. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program is on-going work and will continue in PG&E's 2023 GRC Period. The purpose of the work is to manage and control the electric distribution systems that directly benefit customers by reducing the frequency and duration of power outages while ensuring a more reliable power supply and regulatory compliance. For the remainder of the GRC cycle Operations including EPSS is on proceeding as planned.
37 | Expense | Electric Distribution | BA | E Dist Operate System | BAF | Genl Operate | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.6 Ex 4, Ch 7 | Yes | N/A | N/A | 1821.9541 | 1856.9878 | 3678.9419 | 791.8355 | 1225.6732 | 2017.5087 | -631.3146 | -1661.4331 | -34% | -45.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
38 | Expense | Electric Distribution | BA | E Dist Operate System | BAF | Genl Operate | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.6 Ex 4, Ch 7 | Yes | N/A | N/A | 25992.9338 | 26810.5087 | 52803.4425 | 17355.9657 | 17872.9506 | 35228.9163 | -8937.5581 | -17574.5261 | -33.34% | -33.28% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
39 | Expense | Electric Distribution | BA | E Dist Operate System | BAH | FLISR Maintenance | SRM Total | SRM Total | Ex 4, Ch 4.6 Ex 4, Ch 7 | No | On-going | Annual | 4252.9219 | 4380.7067 | 8633.6286 | 3784.9457 | 3541.101 | 7326.0467 | -839.6057 | -1307.5819 | -19.17% | -15.15% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
40 | Expense | Electric Distribution | BA | E Dist Operate System | BAH | FLISR Maintenance | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.6 Ex 4, Ch 7 | Yes | N/A | N/A | 489.6046 | 499.019 | 988.6236 | 348.0288 | 323.5671 | 671.5959 | -175.4519 | -317.0277 | -35.16% | -32.07% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
41 | Expense | Electric Distribution | BA | E Dist Operate System | BAH | FLISR Maintenance | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.6 Ex 4, Ch 7 | Yes | N/A | N/A | 3763.3173 | 3881.6877 | 7645.005 | 3436.9169 | 3217.5339 | 6654.4507 | -664.1538 | -990.5543 | -17.11% | -12.96% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | Expense | Electric Distribution | BA | E Dist Operate System | BA# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 4.6 Ex 4, Ch 7 | No | On-going | Annual | 0 | 0 | 0 | 2450.2555 | 3524.7446 | 5975.0001 | 3524.7446 | 5975.0001 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | N/A
43 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF1 | Dist. Aerial Inspections | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 10 | No | On-going | Annual | 0 | 0 | 0 | 7431.7981 | 24648.0359 | 32079.834 | 24648.0359 | 32079.834 | 100% | 100% | YES | YES | # of Equipment Inspections | N/A | N/A | N/A | 64000 | 216926 | 280926 | 216926 | 280926 | 100% | 100% | YES | Program expenses exceeded imputed regulatory values due to this program not being forecasted in the 2023 GRC. PG&E incurred costs in 2024 to conduct aerial inspections in HFTDs, which allows us to detect conditions that are challenging to detect from ground inspections. The addition of aerial inspections to PG&E's distribution inspection portfolio enabled PG&E to address an "Area for Continuous Improvement" from the WMP proceeding, and brings PG&E into consistency with SDG&E and SCE, who also conduct risk-based aerial inspections in HFTD. | Actual units were higher than imputed units because PG&E transitioned to aerial inspections in HFTD instead of ground inspections beginning in 2024. | Over | On-Target | Over | Proceeding as Planned | This program was piloted in 2023 and fully implemented in 2024. This work is ongoing and will continue through PG&E’s 2023 GRC period where it was not forecasted. The purpose of this program is a continuing effort to identify abnormal conditions on PG&E assets through aerial inspection.
44 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF3 | UG BART Cable Test/Insp | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 58.9724 | 59.0572 | 118.0296 | 0 | 39.58 | 39.58 | -19.4772 | -78.4496 | -32.98% | -66.47% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
45 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF3 | UG BART Cable Test/Insp | Underground | DUNGD-C001: Patrols | Ex 4, Ch 10 | No | N/A | N/A | 58.9724 | 59.0572 | 118.0296 | 32.5747 | 39.58 | 72.1547 | -19.4772 | -45.8749 | -32.98% | -38.87% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
46 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF4 | UG Auto Xfer Swch Test/Insp | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 145.2468 | 145.4557 | 290.7025 | 68.9669 | 134.042 | 203.0089 | -11.4136 | -87.6936 | -7.847% | -30.17% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
47 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF4 | UG Auto Xfer Swch Test/Insp | Underground | DUNGD-C001: Patrols | Ex 4, Ch 10 | No | N/A | N/A | 145.2468 | 145.4557 | 290.7025 | 68.9669 | 134.042 | 203.0089 | -11.4136 | -87.6936 | -7.847% | -30.17% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
48 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFA | OH Patrol | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 5056.3369 | 5063.6072 | 10119.9441 | 7613.2939 | 10773.5725 | 18386.8664 | 5709.9653 | 8266.9223 | 112.8% | 81.69% | NO | YES | # of Equipment Inspections | 1366233.24 | 1366233.2433 | 2732466.4833 | 1344289 | 1934507 | 3278796 | 568273.7567 | 546329.5167 | 41.59% | 19.99% | YES | Program expenses exceeded imputed regulatory values because more units were patrolled than originally forecasted. Every pole that doesn't get a detailed inspection received a patrol, including non-HFTD rural maps that are being patrolled annually which exceeds the GO165 requirements | Actual units were higher than imputed units because more units were patrolled than originally forecasted. Every pole that doesn't get a detailed inspection received a patrol, including non-HFTD rural maps that are being patrolled annually which exceeds the GO165 requirements and was not forecast in the 2023 GRC. | Over | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue through PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to identify abnormal conditions on PG&E assets through patrols
49 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFA | OH Patrol | Distribution Overhead | DOVHD-C013: Patrols - Distribution Overhead | Ex 4, Ch 10 | No | N/A | N/A | 5056.3369 | 5063.6072 | 10119.9441 | 7613.2939 | 10773.5725 | 18386.8664 | 5709.9653 | 8266.9223 | 112.8% | 81.69% | N/A | N/A | # poles patrolled | 1366233.24 | 1366233.2433 | 2732466.4833 | 1344289 | 1934507 | 3278796 | 568273.7567 | 546329.5167 | 41.59% | 19.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
50 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFA | OH Patrol | Wildfire | WLDFR-C001: Patrols - Distribution Overhead | Ex 4, Ch 10 | No | N/A | N/A | 5056.3369 | 5063.6072 | 10119.9441 | 7613.2939 | 10773.5725 | 18386.8664 | 5709.9653 | 8266.9223 | 112.8% | 81.69% | N/A | N/A | # poles patrolled | 1366233.24 | 1366233.2433 | 2732466.4833 | 1344289 | 1934507 | 3278796 | 568273.7567 | 546329.5167 | 41.59% | 19.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
51 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFB | OH Insp | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 53673.6169 | 53750.7918 | 107424.4087 | 65428.3223 | 26451.5516 | 91879.8739 | -27299.2402 | -15544.5348 | -50.79% | -14.47% | YES | YES | # of Poles Inspected | 508807.48 | 508806.59 | 1017614.07 | 550762 | 331105 | 881867 | -177701.59 | -135747.07 | -34.93% | -13.34% | YES | Program expenses were below imputed regulatory values because PG&E completed less units than originally planned as PG&E transitioned to conduct aerial inspections in HFTDs instead of ground inspections. | Actual units were lower than imputed units because PG&E transitioned to aerial inspections in HFTD instead of ground inspections. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to identify abnormal conditions on PG&E assets through detailed inspections.
52 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFB | OH Insp | Distribution Overhead | DOVHD-C005: Inspections - Distribution Overhead | Ex 4, Ch 10 | No | N/A | N/A | 53673.6169 | 53750.7918 | 107424.4087 | 65428.3223 | 26451.5516 | 91879.8739 | -27299.2402 | -15544.5348 | -50.79% | -14.47% | N/A | N/A | # poles inspected | 508807.48 | 508806.59 | 1017614.07 | 550762 | 331105 | 881867 | -177701.59 | -135747.07 | -34.93% | -13.34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
53 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFB | OH Insp | Wildfire | WLDFR-C01A: Inspections - Distribution Overhead | Ex 4, Ch 10 | No | N/A | N/A | 53673.6169 | 53750.7918 | 107424.4087 | 65428.3223 | 26451.5516 | 91879.8739 | -27299.2402 | -15544.5348 | -50.79% | -14.47% | N/A | N/A | # poles inspected | 508807.48 | 508806.59 | 1017614.07 | 550762 | 331105 | 881867 | -177701.59 | -135747.07 | -34.93% | -13.34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
54 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFC | OH Insp Infrared | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 2833.9513 | 2838.0261 | 5671.9773 | 20.9235 | 1500.9111 | 1521.8347 | -1337.1149 | -4150.1427 | -47.11% | -73.17% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
55 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFC | OH Insp Infrared | Distribution Overhead | DOVHD-C006: Infrared Inspections -Distribution Overhead | Ex 4, Ch 10 | No | N/A | N/A | 2833.9513 | 2838.0261 | 5671.9773 | 20.9235 | 1500.9111 | 1521.8347 | -1337.1149 | -4150.1427 | -47.11% | -73.17% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
56 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFC | OH Insp Infrared | Wildfire | WLDFR-C01B: Infrared Inspections - Distribution Overhead | Ex 4, Ch 10 | No | N/A | N/A | 2833.9513 | 2838.0261 | 5671.9773 | 20.9235 | 1500.9111 | 1521.8347 | -1337.1149 | -4150.1427 | -47.11% | -73.17% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
57 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFD | UG Patrol | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 2681.0599 | 2684.9148 | 5365.9747 | 3142.43 | 2974.7458 | 6117.1758 | 289.831 | 751.2011 | 10.79% | 14% | NO | NO | # of Enclosures Patrolled | 270158 | 270158.0008 | 540316.0008 | 268305 | 279676 | 547981 | 9517.9992 | 7664.9992 | 3.523% | 1.419% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The purpose of this program is a continuing effort to identify abnormal conditions on PG&E assets.
58 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFD | UG Patrol | Underground | DUNGD-C001: Patrols | Ex 4, Ch 10 | No | N/A | N/A | 2681.0599 | 2684.9148 | 5365.9747 | 3142.43 | 2974.7458 | 6117.1758 | 289.831 | 751.2011 | 10.79% | 14% | N/A | N/A | # enclosures patrolled | 270158 | 270158.0008 | 540316.0008 | 268305 | 279676 | 547981 | 9517.9992 | 7664.9992 | 3.523% | 1.419% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
59 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFE | UG Insp Infrared | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 14545.4322 | 14566.3465 | 29111.7787 | 16029.1789 | 14941.0189 | 30970.1978 | 374.6724 | 1858.4191 | 2.572% | 6.384% | NO | NO | # of Enclosures Inspected | 134979 | 134978.9999 | 269957.9999 | 148998 | 155381 | 304379 | 20402.0001 | 34421.0001 | 15.11% | 12.75% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The purpose of this program is a continuing effort to identify abnormal conditions on PG&E assets.
60 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFE | UG Insp Infrared | Underground | DUNGD-C001: Patrols | Ex 4, Ch 10 | No | N/A | N/A | 14545.4322 | 14566.3465 | 29111.7787 | 16029.1789 | 14941.0189 | 30970.1978 | 374.6724 | 1858.4191 | 2.572% | 6.384% | N/A | N/A | # enclosures inspected | 134979 | 134978.9999 | 269957.9999 | 148998 | 155381 | 304379 | 20402.0001 | 34421.0001 | 15.11% | 12.75% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
61 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFF | UG Manhole Insp Annual | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 10 | No | On-going | Annual | 506.7258 | 507.4544 | 1014.1801 | 0 | 160.2093 | 160.2093 | -347.2451 | -853.9708 | -68.43% | -84.2% | NO | NO | # of Manholes/Vaults Inspected | 1546 | 1546 | 3092 | 0 | 474 | 474 | -1072 | -2618 | -69.34% | -84.67% | YES | Below variance threshold. | Actual units were lower than imputed units due to funding for annual manhole inspections being re-prioritized to other high priority work in MWC BF, including aerial inspections in MAT BF1. A limited number of manhole inspections were completed in 2024 based on locations of high public safety consequence, typically located in densely populated areas. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to inspect manholes. Note that manholes are also inspected as part of GO 165 underground inspections program.
62 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFG | OH Equip Test | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 10 | No | On-going | Annual | 2653.7578 | 2657.5735 | 5311.3313 | 3717.2796 | 3553.9803 | 7271.2599 | 896.4067 | 1959.9286 | 33.73% | 36.9% | NO | NO | # of Equip Inspections | 25576.24 | 25576.24 | 51152.48 | 24130 | 21099 | 45229 | -4477.24 | -5923.48 | -17.51% | -11.58% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The purpose of this program is a continuing effort to identify abnormal conditions on PG&E assets.
63 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFH | Inspection Projects | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 4832.4602 | 4839.4086 | 9671.8688 | 6469.977 | 2699.2956 | 9169.2726 | -2140.113 | -502.5962 | -44.22% | -5.196% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
64 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFH | Inspection Projects | Wildfire | WLDFR-C01E: Inspections | Ex 4, Ch 10 | Yes | N/A | N/A | 4832.4602 | 4839.4086 | 9671.8688 | 6469.977 | 2699.3 | 9169.2771 | -2140.1086 | -502.5918 | -44.22% | -5.196% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
65 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFJ | OH Patrol ORT Post Outage | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 165.9964 | 166.2351 | 332.2314 | 146.3 | 127.5662 | 273.8662 | -38.6688 | -58.3652 | -23.26% | -17.57% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
66 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFJ | OH Patrol ORT Post Outage | Distribution Overhead | DOVHD-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 10 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 47.9 | 47.9 | 47.9 | 47.9 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
67 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFJ | OH Patrol ORT Post Outage | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 10 | Yes | N/A | N/A | 0 | 0 | 0 | 51.4 | 47.9 | 99.3 | 47.9 | 99.3 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
68 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFJ | OH Patrol ORT Post Outage | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 10 | Yes | N/A | N/A | 165.9964 | 166.2351 | 332.2314 | 94.8353 | 79.6022 | 174.4375 | -86.6328 | -157.7939 | -52.11% | -47.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
69 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 10 | No | On-going | Annual | 0 | 0 | 0 | 39972.1868 | 41526.8863 | 81499.0731 | 41526.8863 | 81499.0731 | 100% | 100% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values due to the program not being forecasted in the 2023 GRC. These increased expenses are associated with headcount for the System Inspections Quality Control (QC) team, formed to perform system inspection QC audits and achieve the associated quality pass rate for HFTD areas. | N/A | Over | Over | Over | Emergent | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is System Inspection QC, which was not forecasted in the 2023 GRC. PG&E anticipates that System Inspection QC costs will continue to be incurred in this MAT for the remainder of the GRC cycle.
70 | Expense | Electric Distribution | BH | E Dist Routine Emergency | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 4.6 Ex 4, Ch 6 | No | On-going | Annual | 193157.4894 | 197204.9399 | 390362.4293 | 119478.7682 | 137877.1335 | 257355.9017 | -59327.8064 | -133006.5275 | -30.08% | -34.07% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses were below imputed regulatory values due to favorable weather conditions in 2024. Costs for EPSS have variability according to the weather; certain costs like Patrols and Post-Patrol investigation (includes helicopter) will increase or decrease related to weather events that require EPSS mitigation. In addition, when this program was forecasted in the 2023 GRC it was a new program and outages were expected to increase with the full implementation of EPSS. The level of outages, and therefore associated patrols was not realized as forecasted. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to patrol, including the use of helicopters, following an outage event and to restore customers to service as soon as possible. Program spend over the course of the remainder of the GRC cycle is expected to be under what was forecasted for EPSS. The routine emergency portion of this work is emergent depending on weather and the number of events. Overall the EPSS and routine emergency programs are proceeding as planned though the spend is likely to be under for the GRC cycle as explained in the cost variance explanation.
71 | Expense | Electric Distribution | BH | E Dist Routine Emergency | N/A | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.6 Ex 4, Ch 6 | Yes | N/A | N/A | 117183.7596 | 119437.0415 | 236620.8011 | 10276.8746 | 10771.359 | 21048.2336 | -108665.6825 | -215572.5675 | -90.98% | -91.1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
72 | Expense | Electric Distribution | BH | E Dist Routine Emergency | N/A | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.6 Ex 4, Ch 6 | Yes | N/A | N/A | 75973.7298 | 77767.8984 | 153741.6282 | 109201.8936 | 127105.7746 | 236307.6681 | 49337.8762 | 82566.04 | 63.44% | 53.7% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
73 | Expense | Electric Distribution | BK | Maint Other Equip | BKA | Transformer Repr Emeryville | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 1975.33 | 2019.5532 | 3994.8832 | 1597.5867 | 1633.4152 | 3231.0019 | -386.1381 | -763.8813 | -19.12% | -19.12% | NO | NO | Equipment overhauls | 1023 | 1023 | 2046 | 1603 | 1506 | 3109 | 483 | 1063 | 47.21% | 51.96% | YES | Below variance threshold. | Actual units were higher than imputed units due to operational need. This is a demand-driven program for transformer repair/refurbishment supporting maintenance, new construction, emergency response, and other programs. Demand for this program is determined by logistical planners, but is dependent on the availability of transformers from the manufacturer or refurbished/repaired transformer inventory. If transformer supplies are unavailable from the manufacturer, PG&E considers repairing/refurbishing to meet the demand. In 2024 the need for transformer repair/refurbishment was higher than forecast in the 2023 GRC. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to repair and refurbish transformers to meet demand.
74 | Expense | Electric Distribution | BK | Maint Other Equip | BKJ | Equip Overhaul Emeryville | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 0 | 0 | 0 | 104.1453 | 234.3877 | 338.533 | 234.3877 | 338.533 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | N/A
75 | Expense | Electric Distribution | BK | Maint Other Equip | BKK | Equip Warranty Repr Emeryville | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 0 | 0 | 0 | 299.56 | 237.3134 | 536.8733 | 237.3134 | 536.8733 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | N/A
76 | Expense | Electric Distribution | DD | Provide Field Service | DDC | Electric Start/Stop | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 482.2666 | 498.3348 | 980.6014 | 245.6925 | 279.178 | 524.8704 | -219.1568 | -455.731 | -43.98% | -46.47% | NO | NO | Field orders | 3603.81 | 3603.8094 | 7207.6194 | 1710 | 1731 | 3441 | -1872.8094 | -3766.6194 | -51.97% | -52.26% | YES | Below variance threshold. | Actual units were lower than imputed units due to fewer customer-generated start/stop requests than forecast. | Under | On-Target | On-Target | Proceeding as Planned | This program is on-going work and will continue in PG&E's 2023 GRC Period. The work supports customer-generated start/stop requests while ensuring safe delivery of electric service.
77 | Expense | Electric Distribution | DD | Provide Field Service | DDH | Electric Trouble Cust Equipt | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 7 | No | On-going | Annual | 6092.1497 | 6300.8473 | 12392.997 | 7159.0458 | 7444.1703 | 14603.2161 | 1143.323 | 2210.2191 | 18.15% | 17.83% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program is on-going work and will continue in PG&E's 2023 GRC Period. The work supports timely response to trouble on customer-owned equipment and maintains safety and reliability of the electric grid. PG&E changed from unitized to non-unitized in the 2023 GRC due to inconsistency in the unit cost per outage event.
78 | Expense | Electric Distribution | DD | Provide Field Service | DDJ | Electric - Other | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 7 | No | On-going | Annual | 11131.8549 | 11513.1968 | 22645.0517 | 17159.1279 | 13491.2097 | 30650.3376 | 1978.0129 | 8005.286 | 17.18% | 35.35% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program is on-going and will continue in PG&E's 2023 GRC Period. The work is driven by customer-initiated electrical service connections, particularly connects/reconnects like solar PV installations, Electric Main Panel Upgrades, and electric vehicle connections. PG&E changed from unitized to non-unitized in the 2023 GRC due to inconsistency in the unit cost per outage event.
79 | Expense | Electric Distribution | DD | Provide Field Service | DD# | Not assigned | SRM Total | SRM Total | Ex 4, Ch 7 | No | On-going | Annual | 6608.3486 | 6834.7296 | 13443.0781 | 7217.0524 | 8813.3711 | 16030.4235 | 1978.6416 | 2587.3454 | 28.95% | 19.25% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
80 | Expense | Electric Distribution | DD | Provide Field Service | DD# | Not assigned | Distribution Overhead | DOVHD-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 7 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 148.3995 | 148.3995 | 148.3995 | 148.3995 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
81 | Expense | Electric Distribution | DD | Provide Field Service | DD# | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 7 | Yes | N/A | N/A | 0 | 0 | 0 | 258.3307 | 148.3995 | 406.7302 | 148.3995 | 406.7302 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
82 | Expense | Electric Distribution | DD | Provide Field Service | DD# | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 7 | Yes | N/A | N/A | 6608.3486 | 6834.7296 | 13443.0781 | 6958.7217 | 8664.9716 | 15623.6933 | 1830.242 | 2180.6152 | 26.78% | 16.22% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
83 | Expense | Electric Distribution | EY | Change/Maint Used Elec Meter | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 8478.8029 | 8499.0083 | 16977.8113 | 9001.3117 | 9684.3638 | 18685.6756 | 1185.3555 | 1707.8643 | 13.95% | 10.06% | NO | NO | Field orders | 36757.8 | 36757.8009 | 73515.6009 | 35924 | 38531 | 74455 | 1773.1991 | 939.3991 | 4.824% | 1.278% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
84 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZA | Genl Engineer | SRM Total | SRM Total | Ex 4, Ch 17 | No | On-going | Annual | 22543.5406 | 23198.0713 | 45741.6119 | 17070.6936 | 18939.0259 | 36009.7195 | -4259.0454 | -9731.8924 | -18.36% | -21.28% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
85 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZA | Genl Engineer | Distribution Overhead | DOVHD-C008: Annual Protection Reviews | Ex 4, Ch 17 | Yes | N/A | N/A | 16913.6291 | 17422.1695 | 34335.7985 | 12145.3497 | 13551.7821 | 25697.1318 | -3870.3874 | -8638.6668 | -22.22% | -25.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
86 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZA | Genl Engineer | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.6 | Yes | N/A | N/A | 2111.442 | 2166.1942 | 4277.6362 | 2226.5793 | 2846.6561 | 5073.2354 | 680.4619 | 795.5991 | 31.41% | 18.6% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
87 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZA | Genl Engineer | Wildfire | WLDFR-M07A: Situational Awareness and Forecasting Initiatives - Line Sensors | Ex 4, Ch 4.3 | Yes | N/A | N/A | 3518.4132 | 3609.6498 | 7128.063 | 2698.7647 | 2540.5877 | 5239.3524 | -1069.0621 | -1888.7107 | -29.62% | -26.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
88 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZB | Voltage Complaints Invest | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 653.4074 | 673.0534 | 1326.4608 | 1761.7722 | 1652.2503 | 3414.0224 | 979.1969 | 2087.5616 | 145.5% | 157.4% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
89 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZC | Transformer Reports Manage | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 237.0501 | 244.1775 | 481.2277 | 0 | 0 | 0 | -244.1775 | -481.2277 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
90 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZD | Field Work Plan | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 859.0535 | 884.8826 | 1743.9361 | 283.2546 | 573.4817 | 856.7363 | -311.4009 | -887.1998 | -35.19% | -50.87% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
91 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZE | Troublemen Field Work | SRM Total | SRM Total | Ex 4, Ch 17 | No | On-going | Annual | 1538.7999 | 1585.0668 | 3123.8667 | 5160.3261 | 4619.1347 | 9779.4609 | 3034.0679 | 6655.5942 | 191.4% | 213.1% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
92 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZE | Troublemen Field Work | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 2617.5919 | 2291.5817 | 4909.1736 | 2291.5817 | 4909.1736 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
93 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZE | Troublemen Field Work | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 17 | Yes | N/A | N/A | 1538.7999 | 1585.0668 | 3123.8667 | 2542.7342 | 2327.553 | 4870.2872 | 742.4862 | 1746.4206 | 46.84% | 55.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
94 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAA | Pole Test & Treat | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 21669.7722 | 21556.4696 | 43226.2418 | 34048.7679 | 13491.0593 | 47539.8271 | -8065.4103 | 4313.5853 | -37.42% | 9.979% | NO | YES | # Poles Tested & Treated | 259832.68 | 259832.6754 | 519665.3554 | 117091 | 62845 | 179936 | -196987.6754 | -339729.3554 | -75.81% | -65.37% | YES | Program expenses were below imputed regulatory values due to fewer units being completed. | Actual units were lower than imputed units due to PG&E temporarily shifting to a 20-year inspection cycle from a 10-year inspection cycle. | Under | Under | Over | Rescheduled | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to inspect and treat wood poles intrusively, to ensure the poles are in good condition and prevent premature failure in accordance with GO165. During the 2023 GRC cycle PG&E expects to continue to perform units to meet 20-year inspection cycle.
95 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAA | Pole Test & Treat | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | No | N/A | N/A | 21669.7722 | 21556.4696 | 43226.2418 | 34048.7679 | 13491.0593 | 47539.8271 | -8065.4103 | 4313.5853 | -37.42% | 9.979% | N/A | N/A | # inspections | 259832.68 | 259832.6754 | 519665.3554 | 117091 | 62845 | 179936 | -196987.6754 | -339729.3554 | -75.81% | -65.37% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
96 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAA | Pole Test & Treat | Wildfire | WLDFR-C12A: Wood Pole Inspection Program | Ex 4, Ch 12 | No | N/A | N/A | 21669.7722 | 21556.4696 | 43226.2418 | 34048.7679 | 13491.0593 | 47539.8271 | -8065.4103 | 4313.5853 | -37.42% | 9.979% | N/A | N/A | # inspections | 259832.68 | 259832.6754 | 519665.3554 | 117091 | 62845 | 179936 | -196987.6754 | -339729.3554 | -75.81% | -65.37% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
97 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAB | Pole Joint Util Maint Reimb | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | 0 | 0 | 0 | 177.4772 | 551.1657 | 728.6429 | 551.1657 | 728.6429 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. Joint Utilities Maintenance Reimbursements are not forecast in the GRC and therefore will continue to appear over budget.
98 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAC | Pole Analyze Loading | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 22710.056 | 22591.3141 | 45301.37 | 13502.0972 | 12431.0901 | 25933.1873 | -10160.224 | -19368.1827 | -44.97% | -42.75% | YES | YES | Poles Analyzed | 200000 | 200000 | 400000 | 162050 | 32008 | 194058 | -167992 | -205942 | -84% | -51.49% | YES | Program expenses were below imputed values due to the completion of a lower unit volume than forecasted at a higher unit cost. In 2024, the work focused on completing units in HFTD, which required more detailed engineering calculations for which desktop review was indeterminate. PG&E delayed transition of desktop reviews to non-HFTD poles in efforts to complete the outstanding HFTD poles. | Actual units were lower than imputed units due to work focused on completing units in HFTD, which required more detailed engineering calculations for which desktop review was indeterminate. PG&E delayed transition of desktop reviews to non-HFTD poles in efforts to complete the outstanding HFTD poles. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to review and analyze pole loading in order to prevent overloaded poles and premature pole failure. This program has concentrated on poles in Tier 2 and 3 HFTDs, through the performance of a desktop pole review calculation. PG&E has completed the desktop review pole loading analysis for all poles in the Tier 2 and 3 HFTDs. However, PG&E is now performing more detailed engineering calculations for all poles in the Tier 2 and 3 HFTDs for which the desktop review indicated a data anomaly (e.g., change of conductor type) or that could not be sufficiently analyzed because of obstructions to LiDAR data capture (e.g., dense vegetation). PG&E will transition to analysis of non-HFTD poles after completion of the HFTD poles.
99 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAC | Pole Analyze Loading | Wildfire | WLDFR-C12B: Pole Analyze Loading | Ex 4, Ch 12 | No | N/A | N/A | 22710.056 | 22591.3141 | 45301.37 | 13502.0972 | 12431.0901 | 25933.1873 | -10160.224 | -19368.1827 | -44.97% | -42.75% | N/A | N/A | # poles analyzed | 200000 | 200000 | 400000 | 162050 | 32008 | 194058 | -167992 | -205942 | -84% | -51.49% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
100 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAD | Pole Reinforce | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 4403.5311 | 4380.5068 | 8784.0379 | 7609.0663 | -1777.6728 | 5831.3935 | -6158.1796 | -2952.6445 | -140.6% | -33.61% | NO | YES | Poles Reinforced | 4500 | 4500 | 9000 | 3982 | 0 | 3982 | -4500 | -5018 | -100% | -55.76% | YES | Program expenses were below imputed adopted values due to recorded costs being transferred from MAT Code GAD to MAT Code 07R. MAT code 07R was created after 2023 GRC filing when costs for pole reinforcements were capitalized, beginning in 2024. | Actual units were lower than imputed units because costs and units were recorded to MAT 07R. See costs variance explanation for this program. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period, but under MAT 07R. The purpose of this program is a continuing effort to make safe degraded poles that would otherwise require replacement.
101 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAD | Pole Reinforce | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | No | N/A | N/A | 4403.5311 | 4380.5068 | 8784.0379 | 7609.0663 | -1777.6728 | 5831.3935 | -6158.1796 | -2952.6445 | -140.6% | -33.61% | N/A | N/A | # reinforcements | 4500 | 4500 | 9000 | 3982 | 0 | 3982 | -4500 | -5018 | -100% | -55.76% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
102 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAD | Pole Reinforce | Wildfire | WLDFR-C12E: Pole Restoration Program | Ex 4, Ch 12 | No | N/A | N/A | 4403.5311 | 4380.5068 | 8784.0379 | 7609.0663 | -1777.6728 | 5831.3935 | -6158.1796 | -2952.6445 | -140.6% | -33.61% | N/A | N/A | # reinforcements | 4500 | 4500 | 9000 | 3982 | 0 | 3982 | -4500 | -5018 | -100% | -55.76% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
103 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAF | Telco Engr Revw Non-Reimbursed | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 176.1861 | 175.2649 | 351.4511 | 0 | 0 | 0 | -175.2649 | -351.4511 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
104 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAF | Telco Engr Revw Non-Reimbursed | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | No | N/A | N/A | 176.1861 | 175.2649 | 351.4511 | 0 | 0 | 0 | -175.2649 | -351.4511 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
105 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAH | Pole Joint Util Maint Non-Reim | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 475.8148 | 473.3269 | 949.1417 | 444.3824 | 706.2257 | 1150.6081 | 232.8987 | 201.4664 | 49.2% | 21.23% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
106 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAH | Pole Joint Util Maint Non-Reim | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | No | N/A | N/A | 475.8148 | 473.3269 | 949.1417 | 444.3824 | 706.2257 | 1150.6081 | 232.8987 | 201.4664 | 49.2% | 21.23% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
107 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GA# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | -5287.8284 | -5260.1804 | -10548.0089 | -5807.0151 | 1869.4175 | -3937.5975 | 7129.598 | 6610.4113 | -135.5% | -62.67% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For the 2023 GRC forecast, MAT GA# was used to track joint pole credits and pole management personnel costs for the intrusive inspection and pole restoration programs and therefore the imputed amount is negative. In 2024, GA# was only used to track the costs associated with management of pole test and treat, pole reinforcement, and comprehensive inspection programs. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The revised purpose of this program is to track pole management personnel costs.
108 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC1 | El DSub-Engrg_Maint Support | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 5700.5611 | 5776.4015 | 11476.9626 | 4630.9512 | 4148.5711 | 8779.5223 | -1627.8305 | -2697.4403 | -28.18% | -23.5% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
109 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC1 | El DSub-Engrg_Maint Support | Substation | SBSTN-C008: Design Criteria | Ex 4, Ch 15 | Yes | N/A | N/A | 544.2725 | 551.5135 | 1095.786 | 2289.1948 | 2492.7396 | 4781.9344 | 1941.2261 | 3686.1485 | 352% | 336.4% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
110 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC1 | El DSub-Engrg_Maint Support | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 4024.3681 | 4077.9084 | 8102.2765 | 2341.7564 | 1655.8315 | 3997.5878 | -2422.077 | -4104.6887 | -59.4% | -50.66% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
111 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC1 | El DSub-Engrg_Maint Support | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 15 | Yes | N/A | N/A | 1131.9034 | 1146.9623 | 2278.8657 | 0 | 0 | 0 | -1146.9623 | -2278.8657 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
112 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC2 | El DSub-Major Emerg_Corr Maint | SRM Total | SRM Total | Ex 4, Ch 15 Ex 4, Ch 4.6 | No | On-going | Annual | 15750.297 | 15964.9815 | 31715.2784 | 4651.2106 | 5092.7712 | 9743.9818 | -10872.2103 | -21971.2966 | -68.1% | -69.28% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses were below imputed regulatory values due to reprioritizing and funding overruns in our preventative substation programs. | N/A | Under | Under | Under | Rescheduled | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is substation corrective work. PG&E anticipates completing this work as the need arises within the overall priority of the substation portfolio of work over the remainder of the course of the GRC cycle.
113 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC2 | El DSub-Major Emerg_Corr Maint | Distribution Overhead | DOVHD-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 15 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 54.6225 | 54.6225 | 54.6225 | 54.6225 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
114 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC2 | El DSub-Major Emerg_Corr Maint | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 15 Ex 4, Ch 4.6 | Yes | N/A | N/A | 867.9081 | 884.5968 | 1752.5048 | 210.8075 | 54.6225 | 265.4299 | -829.9743 | -1487.0749 | -93.83% | -84.85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
115 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC2 | El DSub-Major Emerg_Corr Maint | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 15 Ex 4, Ch 4.6 | Yes | N/A | N/A | 14882.3889 | 15080.3847 | 29962.7736 | 4440.4032 | 5038.1487 | 9478.5519 | -10042.236 | -20484.2217 | -66.59% | -68.37% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
116 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC5 | Dist Sub enhanced inspections | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 15 | No | On-going | Annual | 0 | 0 | 0 | 1083.5342 | 1000.4815 | 2084.0157 | 1000.4815 | 2084.0157 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | N/A
117 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCA | Dsbn: TXfmr - prev maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 1146.6707 | 1161.926 | 2308.5967 | 1519.1547 | 1485.4577 | 3004.6124 | 323.5316 | 696.0157 | 27.84% | 30.15% | NO | NO | Transformers Maintained | 4574.24 | 4574.2385 | 9148.4785 | 5373 | 4940 | 10313 | 365.7615 | 1164.5215 | 7.996% | 12.73% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The scope of this work is ongoing in accordance with General Order (GO) 174, which sets forth requirements for electric utility substations inspections and maintenance.
118 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCA | Dsbn: TXfmr - prev maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 1146.6707 | 1161.926 | 2308.5967 | 1519.1547 | 1485.4577 | 3004.6124 | 323.5316 | 696.0157 | 27.84% | 30.15% | N/A | N/A | # of Transformers Maintained | 4574.24 | 4574.2385 | 9148.4785 | 5373 | 4940 | 10313 | 365.7615 | 1164.5215 | 7.996% | 12.73% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
119 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCB | Dsbn: Breaker - prevent maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 833.5576 | 844.6473 | 1678.205 | 962.1027 | 1050.2965 | 2012.3993 | 205.6492 | 334.1943 | 24.35% | 19.91% | NO | NO | Breakers Maintained | 1881.95 | 1881.9471 | 3763.8971 | 1167 | 1232 | 2399 | -649.9471 | -1364.8971 | -34.54% | -36.26% | YES | Below variance threshold. | Actual units were lower than imputed units due to higher actual unit costs than forecast. Higher unit costs are generally driven by labor, and resulted in fewer program units achieved. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
120 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCB | Dsbn: Breaker - prevent maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 833.5576 | 844.6473 | 1678.205 | 962.1027 | 1050.2965 | 2012.3993 | 205.6492 | 334.1943 | 24.35% | 19.91% | N/A | N/A | # of Breakers Maintained | 1881.95 | 1881.9471 | 3763.8971 | 1167 | 1232 | 2399 | -649.9471 | -1364.8971 | -34.54% | -36.26% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
121 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCC | Dist Sub: Substation Test Dpt | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 1599.4152 | 1620.6938 | 3220.109 | 3607.2022 | 3910.7222 | 7517.9243 | 2290.0283 | 4297.8153 | 141.3% | 133.5% | NO | NO | Relays Maintained | 1422.95 | 1422.9522 | 2845.9022 | 1364 | 1475 | 2839 | 52.0478 | -6.9022 | 3.658% | -0.2425% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The scope of this work is ongoing in accordance with GO174, which sets forth requirements for electric utility substations inspections and maintenance.
122 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCC | Dist Sub: Substation Test Dpt | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 1599.4152 | 1620.6938 | 3220.109 | 3607.2022 | 3910.7222 | 7517.9243 | 2290.0283 | 4297.8153 | 141.3% | 133.5% | N/A | N/A | # of Relays Maintained | 1422.95 | 1422.9522 | 2845.9022 | 1364 | 1475 | 2839 | 52.0478 | -6.9022 | 3.658% | -0.2425% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
123 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCD | Dsbn: Station Read_prev maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 3310.9587 | 3355.0078 | 6665.9664 | 3254.1144 | 3208.7438 | 6462.8581 | -146.264 | -203.1083 | -4.36% | -3.047% | NO | NO | Substation Inspections | 6849.81 | 6849.8134 | 13699.6234 | 6671 | 6319 | 12990 | -530.8134 | -709.6234 | -7.749% | -5.18% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The scope of this work is ongoing in accordance with GO174, which sets forth requirements for electric utility substations inspections and maintenance.
124 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCD | Dsbn: Station Read_prev maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 3310.9587 | 3355.0078 | 6665.9664 | 3254.1144 | 3208.7438 | 6462.8581 | -146.264 | -203.1083 | -4.36% | -3.047% | N/A | N/A | # of Substation Inspections | 6849.81 | 6849.8134 | 13699.6234 | 6671 | 6319 | 12990 | -530.8134 | -709.6234 | -7.749% | -5.18% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
125 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCD | Dsbn: Station Read_prev maint. | Wildfire | WLDFR-C003: Patrols and Inspections - Substation | Ex 4, Ch 15 | No | N/A | N/A | 3310.9587 | 3355.0078 | 6665.9664 | 3254.1144 | 3208.7438 | 6462.8581 | -146.264 | -203.1083 | -4.36% | -3.047% | N/A | N/A | # of Substation Inspections | 6849.81 | 6849.8134 | 13699.6234 | 6671 | 6319 | 12990 | -530.8134 | -709.6234 | -7.749% | -5.18% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
126 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCE | Dsbn: Gnrl station_prev maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 539.4853 | 546.6626 | 1086.1479 | 676.5371 | 546.3868 | 1222.9239 | -0.27579 | 136.776 | -0.05045% | 12.59% | NO | NO | Substation Preventative | 1176.97 | 1176.9733 | 2353.9433 | 1866 | 1487 | 3353 | 310.0267 | 999.0567 | 26.34% | 42.44% | YES | Below variance threshold. | Actual units were higher than imputed units due to the bundling of work for executional efficiencies, which resulted in additional program units being pulled into scope for a lower unit cost. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
127 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCE | Dsbn: Gnrl station_prev maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 539.4853 | 546.6626 | 1086.1479 | 676.5371 | 546.3868 | 1222.9239 | -0.27579 | 136.776 | -0.05045% | 12.59% | N/A | N/A | # of Substation Preventative tasks | 1176.97 | 1176.9733 | 2353.9433 | 1866 | 1487 | 3353 | 310.0267 | 999.0567 | 26.34% | 42.44% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
128 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCF | Dsbn: Batteries - prev maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 528.9071 | 535.9437 | 1064.8509 | 456.1467 | 499.9527 | 956.0994 | -35.991 | -108.7514 | -6.715% | -10.21% | NO | NO | Batteries Maintained | 1238.98 | 1238.9791 | 2477.9591 | 1306 | 1200 | 2506 | -38.9791 | 28.0409 | -3.146% | 1.132% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The scope of this work is ongoing in accordance with GO174, which sets forth requirements for electric utility substations inspections and maintenance.
129 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCF | Dsbn: Batteries - prev maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 528.9071 | 535.9437 | 1064.8509 | 456.1467 | 499.9527 | 956.0994 | -35.991 | -108.7514 | -6.715% | -10.21% | N/A | N/A | # of Batteries Maintained | 1238.98 | 1238.9791 | 2477.9591 | 1306 | 1200 | 2506 | -38.9791 | 28.0409 | -3.146% | 1.132% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
130 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCG | Vegetation Management | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 10476.5925 | 10615.9734 | 21092.5659 | 8039.823 | 6484.1992 | 14524.0222 | -4131.7743 | -6568.5438 | -38.92% | -31.14% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
131 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCG | Vegetation Management | Substation | SBSTN-C021: Vegetation Management | Ex 4, Ch 15 | No | N/A | N/A | 10476.5925 | 10615.9734 | 21092.5659 | 8039.823 | 6484.1992 | 14524.0222 | -4131.7743 | -6568.5438 | -38.92% | -31.14% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
132 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCG | Vegetation Management | Wildfire | WLDFR-C006: Vegetation Management - Substation | Ex 4, Ch 15 | No | N/A | N/A | 10476.5925 | 10615.9734 | 21092.5659 | 8039.823 | 6484.1992 | 14524.0222 | -4131.7743 | -6568.5438 | -38.92% | -31.14% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
133 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCH | Building Maintenance | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 1101.1846 | 1115.8349 | 2217.0195 | 3638.9453 | 3330.0338 | 6968.9791 | 2214.199 | 4751.9596 | 198.4% | 214.3% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
134 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCH | Building Maintenance | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 1101.1846 | 1115.8349 | 2217.0195 | 3638.9453 | 3330.0338 | 6968.9791 | 2214.199 | 4751.9596 | 198.4% | 214.3% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
135 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCI | Dsbn: Switches_prevent maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 106.8392 | 108.2606 | 215.0999 | 152.7471 | 30.4673 | 183.2143 | -77.7934 | -31.8855 | -71.86% | -14.82% | NO | NO | Switches Maintained | 112 | 112.0001 | 224.0001 | 70 | 24 | 94 | -88.0001 | -130.0001 | -78.57% | -58.04% | YES | Below variance threshold. | Actual units were lower than imputed units due to higher actual unit costs than forecast. Higher unit costs are generally driven by labor, and resulted in fewer program units achieved. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
136 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCI | Dsbn: Switches_prevent maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 106.8392 | 108.2606 | 215.0999 | 152.7471 | 30.4673 | 183.2143 | -77.7934 | -31.8855 | -71.86% | -14.82% | N/A | N/A | N/A | 112 | N/A | N/A | 70 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
137 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCJ | Dist Sub: Corrective (T80) | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 15 | No | On-going | Annual | 10080.9699 | 10215.0875 | 20296.0575 | 13311.7023 | 13822.7529 | 27134.4552 | 3607.6654 | 6838.3977 | 35.32% | 33.69% | NO | NO | Substation Corrective | 4726.85 | 4726.8456 | 9453.6956 | 8631 | 10577 | 19208 | 5850.1544 | 9754.3044 | 123.8% | 103.2% | YES | Below variance threshold. | Actual units were higher than imputed units due to the bundling of work for executional efficiencies, which resulted in additional program units being pulled into scope for a lower unit cost. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
138 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCM | Breaker Mechanism Services | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 1588.837 | 1609.975 | 3198.812 | 2527.6063 | 2115.5727 | 4643.179 | 505.5977 | 1444.367 | 31.4% | 45.15% | NO | NO | # Mech Services | 709.98 | 709.9775 | 1419.9575 | 844 | 682 | 1526 | -27.9775 | 106.0425 | -3.941% | 7.468% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The scope of this work is ongoing in accordance with GO174, which sets forth requirements for electric utility substations inspections and maintenance.
139 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCM | Breaker Mechanism Services | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 1588.837 | 1609.975 | 3198.812 | 2527.6063 | 2115.5727 | 4643.179 | 505.5977 | 1444.367 | 31.4% | 45.15% | N/A | N/A | # of Mechanism Services | 709.98 | 709.9775 | 1419.9575 | 844 | 682 | 1526 | -27.9775 | 106.0425 | -3.941% | 7.468% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
140 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCO | Transformer Overhauls | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 1291.5912 | 1308.7746 | 2600.3658 | 824.1389 | 1244.4521 | 2068.5911 | -64.3225 | -531.7747 | -4.915% | -20.45% | NO | NO | # Mech Services | 151 | 150.9977 | 301.9977 | 60 | 102 | 162 | -48.9977 | -139.9977 | -32.45% | -46.36% | YES | Below variance threshold. | Actual units were lower than imputed units due to higher actual unit costs than forecast. Higher unit costs are generally driven by labor, and resulted in fewer program units achieved. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
141 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCO | Transformer Overhauls | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 1291.5912 | 1308.7746 | 2600.3658 | 824.1389 | 1244.4521 | 2068.5911 | -64.3225 | -531.7747 | -4.915% | -20.45% | N/A | N/A | # of Mechanism Services | 151 | 150.9977 | 301.9977 | 60 | 102 | 162 | -48.9977 | -139.9977 | -32.45% | -46.36% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
142 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCS | CKSW MOAS Mechanism Services | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 214.7363 | 217.5932 | 432.3295 | 256.403 | 555.6226 | 812.0256 | 338.0294 | 379.6961 | 155.3% | 87.83% | NO | NO | # Overhauls | 82 | 82.0024 | 164.0024 | 51 | 88 | 139 | 5.9976 | -25.0024 | 7.314% | -15.25% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The scope of this work is ongoing in accordance with GO174, which sets forth requirements for electric utility substations inspections and maintenance.
143 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCS | CKSW MOAS Mechanism Services | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 214.7363 | 217.5932 | 432.3295 | 256.403 | 555.6226 | 812.0256 | 338.0294 | 379.6961 | 155.3% | 87.83% | N/A | N/A | # of Overhauls | 82 | 82.0024 | 164.0024 | 51 | 88 | 139 | 5.9976 | -25.0024 | 7.314% | -15.25% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
144 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCV | Breaker Overhauls | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 21.1563 | 21.4378 | 42.594 | 105.3334 | 83.9332 | 189.2666 | 62.4954 | 146.6725 | 291.5% | 344.3% | NO | NO | # Overhauls | 5 | 5.0012 | 10.0012 | 19 | 13 | 32 | 7.9988 | 21.9988 | 159.9% | 220% | YES | Below variance threshold. | Actual units were higher than imputed units based on objective to ensure circuit breakers are operating as intended, resulting in more overhauls than forecast. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
145 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCV | Breaker Overhauls | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 21.1563 | 21.4378 | 42.594 | 105.3334 | 83.9332 | 189.2666 | 62.4954 | 146.6725 | 291.5% | 344.3% | N/A | N/A | N/A | 5 | N/A | N/A | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
146 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCW | Dist Sub: Station Washes | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 463.3227 | 469.4867 | 932.8094 | 410.2365 | 472.6186 | 882.855 | 3.1318 | -49.9543 | 0.6671% | -5.355% | NO | NO | Substation Preventative | 429.99 | 429.9895 | 859.9795 | 458 | 457 | 915 | 27.0105 | 55.0205 | 6.282% | 6.398% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The scope of this work is ongoing in accordance with GO174, which sets forth requirements for electric utility substations inspections and maintenance.
147 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCW | Dist Sub: Station Washes | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 463.3227 | 469.4867 | 932.8094 | 410.2365 | 472.6186 | 882.855 | 3.1318 | -49.9543 | 0.6671% | -5.355% | N/A | N/A | N/A | 429.99 | N/A | N/A | 458 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
148 | Expense | Electric Distribution | GE | E Dist Mapping | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 20 | No | On-going | Annual | 19272.2306 | 19284.6971 | 38556.9277 | 24668.3532 | 29589.4787 | 54257.8319 | 10304.7816 | 15700.9042 | 53.44% | 40.72% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values due to: (1) expenses to develop and implement PG&E’s Asset Data Management Plan, data management standards, tools, analytic products, and data quality improvement projects, and (2) expenses from emergent programs created to improve wildfire-related data, develop wildfire data and analytic products, and respond to wildfire related data requirements including the Wildfire Safety Division GIS Data Standard. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to: 1) manage the Electric Asset Registry including GIS systems of record, mapping of new assets, and conversion of records into digital form; 2) manage data quality; 3) provide data access and integration; and 4) develop new analytic tools in support of Electric Asset Management. PG&E may continue to spend more than adopted in this program over the course of the GRC cycle in order to manage data critical to Electric Operations.
149 | Expense | Electric Distribution | GE | E Dist Mapping | N/A | Not assigned | Wildfire | WLDFR-M002: System Hardening | Ex 4, Ch 20 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 199.4234 | 199.4234 | 199.4234 | 199.4234 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
150 | Expense | Electric Distribution | GE | E Dist Mapping | N/A | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 20 | Yes | On-going | Annual | 19272.2306 | 19284.6971 | 38556.9277 | 24668.3532 | 29390.0553 | 54058.4085 | 10105.3582 | 15501.4808 | 52.4% | 40.2% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
151 | Expense | Electric Distribution | HG | Elec Trans Ops Engr & Tech | HG# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 21 | No | On-going | Annual | 0 | 0 | 0 | 0 | 2970.3987 | 2970.3987 | 2970.3987 | 2970.3987 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | The DERMS program work is ongoing and will continue into PG&E's 2023 GRC period. New tools and processes for orchestration of Distributed Energy Resources (DERs) are required to safely and cost-effectively operate the grid. The Distributed Energy Resources Management (DERMS) Program includes the development, deployment, and operation of these tools and processes to enable these objectives. These costs support the ongoing operation and maintenance of these tools and processes. Note: DERMS program costs were originally adopted under the HGC MAT code, but have since been moved under HG#.
152 | Expense | Electric Distribution | HG | Elec Trans Ops Engr & Tech | HGC | Advanced Dist Mgmt System Dev | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 21 | No | 10 | 8 | 17229.2774 | 17159.8721 | 34389.1495 | 11058.9714 | 10731.9297 | 21790.9011 | -6427.9424 | -12598.2484 | -37.46% | -36.63% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses were below imputed regulatory values due to the availability of a technological solution for obtaining phase identification data necessary to support the immediate needs of ADMS, eliminating the need to manually collect this data. | N/A | On-Target | On-Target | Under | Proceeding as Planned | The ADMS program is a one-time program, and is projected to be completed in 2026, prior to the end of the 2023 GRC cycle. PG&E anticipates continuing to spend below imputed amounts for the remainder of the GRC cycle because the program involves project-based work that may have peaked in the GRC Test Year.
153 | Expense | Electric Distribution | HG | Elec Trans Ops Engr & Tech | HGD | Distribution Operational Tech | SRM Total | SRM Total | Ex 4, Ch 7 | No | On-going | Annual | 5978.0311 | 5953.9495 | 11931.9806 | 7481.5202 | 9306.6721 | 16788.1924 | 3352.7226 | 4856.2117 | 56.31% | 40.7% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This MAT Code is being used for ongoing maintenance tied to Distribution Operational Technology.
154 | Expense | Electric Distribution | HG | Elec Trans Ops Engr & Tech | HGD | Distribution Operational Tech | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 7 | Yes | N/A | N/A | 0 | 0 | 0 | 82.8474 | 173.8516 | 256.699 | 173.8516 | 256.699 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
155 | Expense | Electric Distribution | HG | Elec Trans Ops Engr & Tech | HGD | Distribution Operational Tech | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 7 | Yes | N/A | N/A | 5978.0311 | 5953.9495 | 11931.9806 | 7398.6728 | 9132.8206 | 16531.4934 | 3178.871 | 4599.5128 | 53.39% | 38.55% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
156 | Expense | Electric Distribution | HN | E Dist Tree Trim Bal Acct | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 9 | No | On-going | Annual | 972012.9814 | 965868.48 | 1937881.4615 | 859187.0852 | 1002998.7474 | 1862185.8327 | 37130.2674 | -75695.6288 | 3.844% | -3.906% | YES | NO | # of Veg. Mgmt Trees | 1546783 | 1546783 | 3093566 | 1241025 | 1410201.22 | 2651226.22 | -136581.78 | -442339.78 | -8.83% | -14.3% | NO | Program expenses exceeded imputed regulatory values, primarily as the result of increased units completed due to a rebalance of work, based upon a risk-informed assessment of available tree work. Funding for work was reallocated to Distribution Routine to prioritize work in areas that held higher risk in the marked tree inventory and reduced the overall carryover. In addition, incremental Pole Clearing units were added to the work plan to address ignition risk identified using the Utility Fire Potential Index (FPI). | Below variance threshold. | On-Target | Under | Under | Rescheduled | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to perform routine tree work. PG&E anticipates continuing to perform fewer units than adopted over the remainder of the GRC cycle.
157 | Expense | Electric Distribution | HN | E Dist Tree Trim Bal Acct | N/A | Not assigned | Distribution Overhead | DOVHD-C001: Vegetation Management - Distribution Overhead | Ex 4, Ch 9 | No | N/A | N/A | 972012.9814 | 965868.48 | 1937881.4615 | 859187.1 | 1002998.7474 | 1862185.8474 | 37130.2674 | -75695.6141 | 3.844% | -3.906% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
158 | Expense | Electric Distribution | HN | E Dist Tree Trim Bal Acct | N/A | Not assigned | Wildfire | WLDFR-C004: Vegetation Management - Distribution Overhead | Ex 4, Ch 9 | No | N/A | N/A | 972012.9814 | 965868.48 | 1937881.4615 | 859187.1 | 1002998.7474 | 1862185.8474 | 37130.2674 | -75695.6141 | 3.844% | -3.906% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
159 | Expense | Electric Distribution | HX | E T&D Automation & Protection | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 16 | No | On-going | Annual | 3118.3174 | 3184 | 6302.3175 | 2693.8379 | 1990.0543 | 4683.8922 | -1193.9457 | -1618.4252 | -37.5% | -25.68% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
160 | Expense | Electric Distribution | HX | E T&D Automation & Protection | N/A | Not assigned | Distribution Overhead | DOVHD-C007: Supervisory Control and Data Acquisition | Ex 4, Ch 16 | Yes | N/A | N/A | 3118.3174 | 3184 | 6302.3175 | 2693.8379 | 1990.0543 | 4683.8922 | -1193.9457 | -1618.4252 | -37.5% | -25.68% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
161 | Expense | Electric Distribution | HX | E T&D Automation & Protection | N/A | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 16 | Yes | N/A | N/A | 0 | 0 | 0 | 72.5254 | 57.1026 | 129.628 | 57.1026 | 129.628 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
162 | Expense | Electric Distribution | HY | Change/Maint Used Gas Meters | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 687.1 | 710.3007 | 1397.4007 | 250.6 | 289.4958 | 540.0958 | -420.8049 | -857.3049 | -59.24% | -61.35% | NO | NO | Field orders | 1466 | 1466 | 2932 | 2927 | 3478 | 6405 | 2012 | 3473 | 137.2% | 118.5% | YES | Below variance threshold. | Actual units were higher than imputed units because of an increase in the need to maintain or change used gas meters. This demand is from either 1) customer requests e.g., usage inquiries; or 2) automated system notification for resolution of a meter issue. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to provide gas meter maintenance, based on 1) customer-driven requests; and 2) automated system notifications for meter issue resolution.
163 | Expense | Electric Distribution | IF | E Dist Major Emergency | N/A | N/A | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 6 | No | On-going | Annual | 45380.7998 | 45908.2092 | 91289.009 | 38356.8805 | 214333.8032 | 252690.6837 | 168425.594 | 161401.6747 | 366.9% | 176.8% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values due the February Winter Storms and the July Weather Event which caused a significant deviation from historical trends. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is for major emergencies. This is a demand driven program. This program has no end and is responsive to conditions that require immediate attention.
164 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IGI | Dead and Dying Trees | SRM Total | SRM Total | Ex 4, Ch 9 | No | On-going | Annual | 77991.4684 | 77468.8654 | 155460.3338 | 136577.1456 | 139861.4302 | 276438.5758 | 62392.5648 | 120978.242 | 80.54% | 77.82% | YES | YES | # of Veg. Mgmt Trees | 65000 | 65000 | 130000 | 81281 | 225345.35 | 306626.35 | 160345.35 | 176626.35 | 246.7% | 135.9% | YES | Program expenses exceeded imputed regulatory values due to increased tree units. Volume of work increased due to 1) rescheduled work from previous year; and 2) more work was identified due to changes in scope of patrol procedure. For example, including not just dead trees but healthy trees with defects and trees with growth that could break compliance distance. | Actual units were higher than imputed units of work due to 1) rescheduled work from previous year; and 2) more work was identified due to changes in scope of patrol procedure. For example, including not just dead trees but healthy trees with defects and growth that could break compliance distance. | Over | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. This program is scheduled to continue through 2026, and PG&E anticipates continuing to perform more units than adopted in the 2023 GRC.
165 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IGI | Dead and Dying Trees | Distribution Overhead | DOVHD-C002: Vegetation Management - CEMA/Tree Mortality | Ex 4, Ch 9 | No | N/A | N/A | 77991.4684 | 77468.8654 | 155460.3338 | 136577.1456 | 139861.4302 | 276438.5758 | 62392.5648 | 120978.242 | 80.54% | 77.82% | N/A | N/A | N/A | 65000 | N/A | N/A | 81281 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
166 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IGI | Dead and Dying Trees | Wildfire | WLDFR-C007: Vegetation Management - CEMA/Tree Mortality | Ex 4, Ch 9 | No | N/A | N/A | 77991.4684 | 77468.8654 | 155460.3338 | 136577.1456 | 139861.4302 | 276438.5758 | 62392.5648 | 120978.242 | 80.54% | 77.82% | N/A | N/A | N/A | 65000 | N/A | N/A | 81281 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
167 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IGJ | Enhanced Vegetation Management | SRM Total | SRM Total | Ex 4, Ch 9 | No | On-going | Annual | 131815.9685 | 130932.6999 | 262748.6684 | 161012.919 | 180873.9783 | 341886.8973 | 49941.2784 | 79138.2289 | 38.14% | 30.12% | YES | YES | # Miles | 1800 | 1800 | 3600 | 274 | N/A | 274 | -1800 | -3326 | -100% | -92.39% | YES | Program expenses exceed imputed regulatory values due to MAT IGJ imputed adopted values would have reflected a forecast for EVM which was discontinued at the end of 2022 and superseded by Wildfire Mitigation Plan programs: Focused Tree Inspection (FTI), Tree Removal Inventory (TRI) & VM for Operational Mitigations (VMOM). Wood Management for Wildfire Mitigation Programs is also included in MAT IGJ. Forecast Cost for EVM anticipated clearing overhanging branches for 1,800 miles, whereas the mitigation programs include 1,500 miles of FTI, detailed inspection, and TRI is whole tree removals listed under the previous EVM program. Under both of these programs work is predominantly tree removals rather than the anticipated clearing overhanging branches in 2023 GRC. | Actual units were lower than imputed units because the Enhanced Vegetation Management (EVM) program was discontinued at the end of 2022. The scope of work changed in 2023 to focus on four primary programs: Focused Tree Inspection (FTI), Tree Removal Inventory (TRI), VM for Operational Mitigations (VMOM) and Wood Management. The imputed adopted value reflected a unit forecast for EVM measured in miles, whereas the unit of measure for the new programs were a combination of trees, wood managed, and miles. | Under | Over | Over | Emergent | Work is ongoing and will continue in PG&E’s 2023 GRC period. The Enhanced Vegetation Management (EVM) program concluded in 2022, and the scope of the program was changed as described in the unit variance explanation. PG&E anticipates continuing with the adjusted scope of the program, focusing on Focused Tree Inspection, VMOM, Tree Removal Inventory, and Wood Management.
168 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IGJ | Enhanced Vegetation Management | Wildfire | WLDFR-M001: Enhanced Vegetation Management | Ex 4, Ch 9 | No | N/A | N/A | 131815.9685 | 130932.6999 | 262748.6684 | 161012.919 | 180873.9783 | 341886.8973 | 49941.2784 | 79138.2289 | 38.14% | 30.12% | N/A | N/A | N/A | 1800 | N/A | N/A | 274 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
169 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | SRM Total | SRM Total | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | No | On-going | Annual | 76787.2006 | 77665.1635 | 154452.3641 | 132422.3794 | 78133.3166 | 210555.696 | 468.1531 | 56103.3319 | 0.6028% | 36.32% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | Over | Over | Emergent | This work is ongoing and will continue in PG&Es 2023 GRC period. This MAT is used to record various balancing and memorandum account activities. PG&E anticipates that this program will be over the 2023 GRC cycle imputed regulatory values for MAT Code IG# due to activities for mitigating wildfire risk that were not forecast in IG# in the 2023 GRC. These include EPSS costs for helicopter standby, temporary generation, and battery programs.
170 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Distribution Overhead | DOVHD-C002: Vegetation Management - CEMA/Tree Mortality | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 2442.7271 | 2442.7271 | 2442.7271 | 2442.7271 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
171 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Distribution Overhead | DOVHD-M005: Additional Asset Data Capture | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 183.895 | 0 | 183.895 | 0 | 183.895 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
172 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Emergency Preparedness & Response | EPNDR-C000: EP&R Controls | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 232.201 | 350.6866 | 582.8875 | 350.6866 | 582.8875 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
173 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Emergency Preparedness & Response | EPNDR-C002: Situational Awareness and Forecasting Initiatives - WSOC | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 2724.6525 | 0 | 2724.6525 | 0 | 2724.6525 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
174 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Emergency Preparedness & Response | EPNDR-M000: EP&R Mitigations | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 189.9826 | 286.9254 | 476.908 | 286.9254 | 476.908 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
175 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Wildfire | WLDFR-C007: Vegetation Management - CEMA/Tree Mortality | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 2442.7271 | 2442.7271 | 2442.7271 | 2442.7271 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
176 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 7202.4815 | 4883.8865 | 12086.368 | 4883.8865 | 12086.368 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
177 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Wildfire | WLDFR-M0IT: Wildfire IT Work | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 38734.4 | 38882.8461 | 77617.2461 | 36120.5247 | 37507.9374 | 73628.4622 | -1374.9087 | -3988.7839 | -3.536% | -5.139% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
178 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 34895.7218 | 35566.7184 | 70462.4401 | 64233.3524 | 30783.913 | 95017.2655 | -4782.8053 | 24554.8253 | -13.45% | 34.85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
179 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Wildfire | POST-GRC: Post-GRC Mitigation | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 18404.1181 | 1353.332 | 19757.4501 | 1353.332 | 19757.4501 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
180 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 3157 | 3215.599 | 6372.599 | 3131.1716 | 523.9086 | 3655.0802 | -2691.6904 | -2717.5189 | -83.71% | -42.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
181 | Expense | Electric Distribution | IS | Bill Customers | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 22 | No | On-going | Annual | 1830.672 | 1819.0996 | 3649.7716 | 572.5527 | 672.9663 | 1245.5189 | -1146.1333 | -2404.2527 | -63.01% | -65.87% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
182 | Expense | Electric Distribution | IU | Collect Revenue | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 1589.8684 | 1659.8259 | 3249.6943 | 1088.0359 | 1274.3272 | 2362.3631 | -385.4988 | -887.3313 | -23.23% | -27.31% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
183 | Expense | Electric Distribution | JV | Maintain IT Apps & Infra | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 20 Ex 4, Ch 21 | No | On-going | Annual | 8419.0283 | 8471.7026 | 16890.7308 | 4430.1601 | 4715.7107 | 9145.8708 | -3755.9919 | -7744.86 | -44.34% | -45.85% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
184 | Expense | Electric Distribution | JV | Maintain IT Apps & Infra | N/A | Not assigned | Emergency Preparedness & Response | EPNDR-C002: Situational Awareness and Forecasting Initiatives - WSOC | Ex 4, Ch 20 Ex 4, Ch 21 | Yes | N/A | N/A | 0 | 0 | 0 | 755.5872 | 0 | 755.5872 | 0 | 755.5872 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
185 | Expense | Electric Distribution | JV | Maintain IT Apps & Infra | N/A | Not assigned | IT Asset Failure | ITAFL-M005: Multi-Faceted Mitigations | Ex 4, Ch 20 Ex 4, Ch 21 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 71.0928 | 71.0928 | 71.0928 | 71.0928 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
186 | Expense | Electric Distribution | JV | Maintain IT Apps & Infra | N/A | Not assigned | Wildfire | WLDFR-M0IT: Wildfire IT Work | Ex 4, Ch 20 Ex 4, Ch 21 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 293.8195 | 293.8195 | 293.8195 | 293.8195 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
187 | Expense | Electric Distribution | JV | Maintain IT Apps & Infra | N/A | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 20 Ex 4, Ch 21 | Yes | N/A | N/A | 8419.0283 | 8471.7026 | 16890.7308 | 3674.5729 | 4350.7984 | 8025.3713 | -4120.9042 | -8865.3595 | -48.64% | -52.49% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
188 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAA | OH Genl CM Tag | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 22085.7202 | 22135.0216 | 44220.7418 | 75395.0109 | 139875.0479 | 215270.0588 | 117740.0263 | 171049.317 | 531.9% | 386.8% | YES | YES | # of Notifications Completed | 24150.66 | 24150.6645 | 48301.3245 | 26555 | 58049 | 84604 | 33898.3355 | 36302.6755 | 140.4% | 75.16% | YES | Program expenses exceeded imputed regulatory values due to higher volume of units completed at higher unit costs than adopted in the 2023 GRC Final Decision. PG&E's actual unit cost remain higher than imputed unit costs driven by the higher labor costs for this work. | Actual units were higher than imputed units due to address WMP commitments for the maintenance log. | Over | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is the repair of overhead (OH) facilities or replacement of individual components that are not an imminent hazard. PG&E anticipates the program scope will remain on target while spending more than the GRC imputed adopted costs over the remainder of the cycle to address the maintenance log and meet WMP commitments.
189 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAA | OH Genl CM Tag | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 22085.7202 | 22135.0216 | 44220.7418 | 75395.0109 | 139875.0479 | 215270.0588 | 117740.0263 | 171049.317 | 531.9% | 386.8% | N/A | N/A | # of Notifications Completed | 24150.66 | 24150.6645 | 48301.3245 | 26555 | 58049 | 84604 | 33898.3355 | 36302.6755 | 140.4% | 75.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
190 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAA | OH Genl CM Tag | Wildfire | WLDFR-C008: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 22085.7202 | 22135.0216 | 44220.7418 | 75395.0109 | 139875.0479 | 215270.0588 | 117740.0263 | 171049.317 | 531.9% | 386.8% | N/A | N/A | # of Notifications Completed | 24150.66 | 24150.6645 | 48301.3245 | 26555 | 58049 | 84604 | 33898.3355 | 36302.6755 | 140.4% | 75.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
191 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAC | Bird Safe Retrofit | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1231.4039 | 1234.1528 | 2465.5567 | 683.0583 | 586.3039 | 1269.3623 | -647.8489 | -1196.1945 | -52.49% | -48.52% | NO | NO | # of Notifications Completed | 638.16 | 638.1579 | 1276.3179 | 402 | 228 | 630 | -410.1579 | -646.3179 | -64.27% | -50.64% | YES | Below variance threshold. | Actual units were lower than imputed units due to lower find rates than forecasted. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is the replacement or installation of bird guard materials such as jumper covers, bushing covers, perch guards, or perching platforms on incident and/or adjacent poles in response to a bird electrocution, per U.S. Fish and Wildlife Service (USFWS) requirements and Utility Operating Standard S2321.
192 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAC | Bird Safe Retrofit | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 1231.4039 | 1234.1528 | 2465.5567 | 683.0583 | 586.3039 | 1269.3623 | -647.8489 | -1196.1945 | -52.49% | -48.52% | N/A | N/A | # of Notifications Completed | 638.16 | 638.1579 | 1276.3179 | 402 | 228 | 630 | -410.1579 | -646.3179 | -64.27% | -50.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
193 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAC | Bird Safe Retrofit | Wildfire | WLDFR-C011: Animal Abatement | Ex 4, Ch 11 | No | N/A | N/A | 1231.4039 | 1234.1528 | 2465.5567 | 683.0583 | 586.3039 | 1269.3623 | -647.8489 | -1196.1945 | -52.49% | -48.52% | N/A | N/A | # of Notifications Completed | 638.16 | 638.1579 | 1276.3179 | 402 | 228 | 630 | -410.1579 | -646.3179 | -64.27% | -50.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
194 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAD | Bird Safe Retrofit Annual | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1436.2747 | 1439.4809 | 2875.7555 | 312.6943 | 3467.5951 | 3780.2894 | 2028.1142 | 904.5339 | 140.9% | 31.45% | NO | NO | # of Notifications Completed | 1022 | 1022.0001 | 2044.0001 | 224 | 974 | 1198 | -48.0001 | -846.0001 | -4.697% | -41.39% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
195 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAD | Bird Safe Retrofit Annual | Wildfire | WLDFR-C011: Animal Abatement | Ex 4, Ch 11 | No | N/A | N/A | 1436.2747 | 1439.4809 | 2875.7555 | 312.6943 | 3467.5951 | 3780.2894 | 2028.1142 | 904.5339 | 140.9% | 31.45% | N/A | N/A | # of Notifications Completed | 1022 | 1022.0001 | 2044.0001 | 224 | 974 | 1198 | -48.0001 | -846.0001 | -4.697% | -41.39% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
196 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAF | OH COE CM Tag | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 7212.9759 | 7229.0772 | 14442.0531 | 6418.8636 | 5790.394 | 12209.2576 | -1438.6832 | -2232.7955 | -19.9% | -15.46% | NO | NO | # of Notifications Completed | 1380 | 1380.0002 | 2760.0002 | 1141 | 1250 | 2391 | -130.0002 | -369.0002 | -9.42% | -13.37% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
197 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAF | OH COE CM Tag | Wildfire | WLDFR-C008: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 7212.9759 | 7229.0772 | 14442.0531 | 6418.8636 | 5790.394 | 12209.2576 | -1438.6832 | -2232.7955 | -19.9% | -15.46% | N/A | N/A | # of Notifications Completed | 1380 | 1380.0002 | 2760.0002 | 1141 | 1250 | 2391 | -130.0002 | -369.0002 | -9.42% | -13.37% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
198 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAH | Streetlights Repl Burnouts | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 2171.8479 | 2176.696 | 4348.5439 | 1769.6744 | 1895.4349 | 3665.1093 | -281.2611 | -683.4345 | -12.92% | -15.72% | NO | NO | # of Burnout Repairs | 11714.32 | 11714.3214 | 23428.6414 | 6191 | 0 | 6191 | -11714.3214 | -17237.6414 | -100% | -73.58% | YES | Below variance threshold. | With the near completion of the LED conversion program, fewer HPSV bulb replacements will be needed (instead LED fixtures will need to be replaced under MAT 2AH) and replacements will be done ad-hoc. Therefore the costs are no longer unitized. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to repair streetlights when a streetlight outage has occurred. Since the LED conversion program is almost complete, a lower find rate for streetlights requiring bulb replacement is expected and the work will be tracked programmatically.
199 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAH | Streetlights Repl Burnouts | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 2171.8479 | 2176.696 | 4348.5439 | 1769.6744 | 1895.4349 | 3665.1093 | -281.2611 | -683.4345 | -12.92% | -15.72% | N/A | N/A | # of Burnout Repairs | 11714.32 | 11714.3214 | 23428.6414 | 6191 | 0 | 6191 | -11714.3214 | -17237.6414 | -100% | -73.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
200 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAK | RTVI Invest/Repr | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 126.4096 | 126.6918 | 253.1014 | 88.7648 | 80.9353 | 169.7001 | -45.7565 | -83.4013 | -36.12% | -32.95% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
201 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAM | Insulators Wash | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 246.2808 | 246.8306 | 493.1114 | 304.7772 | 237.1062 | 541.8835 | -9.7243 | 48.7721 | -3.94% | 9.891% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
202 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAM | Insulators Wash | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 246.2808 | 246.8306 | 493.1114 | 304.7772 | 237.1062 | 541.8835 | -9.7243 | 48.7721 | -3.94% | 9.891% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
203 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAO | Idle Fac Invest - Svc Plng | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 214.6784 | 215.1576 | 429.836 | 2054.0632 | 1820.8959 | 3874.9591 | 1605.7383 | 3445.1231 | 746.3% | 801.5% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
204 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAO | Idle Fac Invest - Svc Plng | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 214.6784 | 215.1576 | 429.836 | 2054.0632 | 1820.8959 | 3874.9591 | 1605.7383 | 3445.1231 | 746.3% | 801.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
205 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAP | OH EXP Projects | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1792.619 | 1796.6206 | 3589.2397 | 25.5764 | 3496.9548 | 3522.5311 | 1700.3341 | -66.7085 | 94.64% | -1.859% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
206 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAP | OH EXP Projects | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 1792.619 | 1796.6206 | 3589.2397 | 25.5764 | 3496.9548 | 3522.5311 | 1700.3341 | -66.7085 | 94.64% | -1.859% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
207 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAQ | Wood Pole Bridge Bonding | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1.0897 | 1.0922 | 2.1819 | 881.7755 | 671.5721 | 1553.3476 | 670.48 | 1551.1657 | 61390% | 71092% | NO | NO | # of Notifications Completed | 2 | 2 | 4 | 296 | 237 | 533 | 235 | 529 | 11750% | 13225% | YES | Below variance threshold. | Actual units were higher than imputed units based on actual find rate (i.e. inspections that identified the need for a higher number of wood pole bridge bonding retrofits than anticipated) and targeted focus to complete this work as it is a control for reducing the risk of wildfire. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is Wood Pole Bridge Bonding to prevent ignitions by ensuring grounding protection. Wood pole bonding is a maintenance activity where an existing wood pole supporting both electric transmission and distribution line facilities is retrofitted with grounding protection to prevent fires which can occur at the location on the pole where the electric distribution cross arm is bolted to the pole.
208 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAQ | Wood Pole Bridge Bonding | Wildfire | WLDFR-C008: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 1.0897 | 1.0922 | 2.1819 | 881.7755 | 671.5721 | 1553.3476 | 670.48 | 1551.1657 | 61390% | 71092% | N/A | N/A | # of Notifications Completed | 2 | 2 | 4 | 296 | 237 | 533 | 235 | 529 | 11750% | 13225% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
209 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAS | FAS Overhead Expense | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1796.978 | 1800.9893 | 3597.9673 | 1150.2837 | 1051.3607 | 2201.6444 | -749.6286 | -1396.3229 | -41.62% | -38.81% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | 10453.34 | N/A | N/A | 8302 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | MAT KAS work is identified and performed by Troubleshooters in the field and is demand driven. Due to the variable nature of the work performed in MAT KAS, MAT KAS is non-unitized beginning in 2024. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This is a demand driven program. The program repairs overhead facilities identified during a field job and completed by a single PG&E Troubleshooter. The work could involve repairing overhead facilities such as: electric distribution conductors, components, structures, and associated equipment constructed above ground level. Due to the variable nature of the work performed in MAT KAS, MAT KAS is non-unitized beginning in 2024.
210 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAS | FAS Overhead Expense | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 1796.978 | 1800.9893 | 3597.9673 | 1150.2837 | 1051.3607 | 2201.6444 | -749.6286 | -1396.3229 | -41.62% | -38.81% | N/A | N/A | N/A | 10453.34 | N/A | N/A | 8302 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
211 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAT | Remote Grid SPS Maintenance | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | On-going | Annual | 1038.7214 | 1041.0401 | 2079.7615 | 125.6272 | 667.0175 | 792.6447 | -374.0226 | -1287.1168 | -35.93% | -61.89% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
212 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAT | Remote Grid SPS Maintenance | Distribution Overhead | DOVHD-M011: Remote Grid | Ex 4, Ch 4.3 | No | N/A | N/A | 1038.7214 | 1041.0401 | 2079.7615 | 25.839 | 667.0175 | 692.8565 | -374.0226 | -1386.905 | -35.93% | -66.69% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
213 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAT | Remote Grid SPS Maintenance | Wildfire | WLDFR-M017: System Hardening - Remote Grid | Ex 4, Ch 4.3 | No | N/A | N/A | 1038.7214 | 1041.0401 | 2079.7615 | 125.6272 | 667.0175 | 792.6447 | -374.0226 | -1287.1168 | -35.93% | -61.89% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
214 | Expense | Electric Distribution | KA | E Dist Maint OH General | KA# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 888.1365 | 890.119 | 1778.2555 | -34.2349 | 1591.6165 | 1557.3817 | 701.4975 | -220.8739 | 78.81% | -12.42% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
215 | Expense | Electric Distribution | KB | E Dist Maint UG | KBA | UG Genl CM Tag | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 17135.2076 | 17270.4231 | 34405.6308 | 15657.4038 | 18614.1991 | 34271.603 | 1343.776 | -134.0278 | 7.781% | -0.3896% | NO | NO | # of Notifications Completed | 6162.85 | 6162.8494 | 12325.6994 | 4916 | 4328 | 9244 | -1834.8494 | -3081.6994 | -29.77% | -25% | YES | Below variance threshold. | Actual units were lower than imputed units due to optimizing resources to focus on completing higher priority maintenance tags within MWCs KA and KB. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is underground corrective maintenance that does not pose an imminent hazard and have not caused an outage. PG&E will continue to complete notifications based on the workplan maintenance schedule and priority of the tags.
216 | Expense | Electric Distribution | KB | E Dist Maint UG | KBA | UG Genl CM Tag | Underground | DUNGD-C002: Underground Notifications | Ex 4, Ch 11 | No | N/A | N/A | 17135.2076 | 17270.4231 | 34405.6308 | 15657.4038 | 18614.1991 | 34271.603 | 1343.776 | -134.0278 | 7.781% | -0.3896% | N/A | N/A | # of Notifications Completed | 6162.85 | 6162.8494 | 12325.6994 | 4916 | 4328 | 9244 | -1834.8494 | -3081.6994 | -29.77% | -25% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
217 | Expense | Electric Distribution | KB | E Dist Maint UG | KBC | UG COE CM Tag | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1547.5023 | 1559.7138 | 3107.2161 | 403.6052 | 809.2628 | 1212.868 | -750.451 | -1894.3481 | -48.11% | -60.97% | NO | NO | # of Notifications Completed | 175 | 175.0001 | 350.0001 | 103 | 134 | 237 | -41.0001 | -113.0001 | -23.43% | -32.29% | YES | Below variance threshold. | Actual units were lower than imputed units due to optimizing resources to focus on completing higher priority maintenance tags within MWCs KA and KB. | Under | Under | Under | Rescheduled | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of the program is to repair of underground Critical Operating Equipment (COE). During the GRC cycle PG&E expects to continue to reprioritize the work in MAT KBC to other higher priority maintenance work in MWCs KA and KB.
218 | Expense | Electric Distribution | KB | E Dist Maint UG | KBC | UG COE CM Tag | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 11 | No | N/A | N/A | 1547.5023 | 1559.7138 | 3107.2161 | 403.6052 | 809.2628 | 1212.868 | -750.451 | -1894.3481 | -48.11% | -60.97% | N/A | N/A | # of Notifications Completed | 175 | 175.0001 | 350.0001 | 103 | 134 | 237 | -41.0001 | -113.0001 | -23.43% | -32.29% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
219 | Expense | Electric Distribution | KB | E Dist Maint UG | KBD | Nitrogen Cylinders CM | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 24.6828 | 24.8775 | 49.5603 | 8.4286 | 9.834 | 18.2627 | -15.0435 | -31.2977 | -60.47% | -63.15% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
220 | Expense | Electric Distribution | KB | E Dist Maint UG | KBD | Nitrogen Cylinders CM | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 11 | No | N/A | N/A | 24.6828 | 24.8775 | 49.5603 | 8.4286 | 9.834 | 18.2627 | -15.0435 | -31.2977 | -60.47% | -63.15% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
221 | Expense | Electric Distribution | KB | E Dist Maint UG | KBE | BART Cable Repr | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 70.8288 | 71.3877 | 142.2165 | 0.53587 | 2.1424 | 2.6782 | -69.2454 | -139.5383 | -97% | -98.12% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
222 | Expense | Electric Distribution | KB | E Dist Maint UG | KBE | BART Cable Repr | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 11 | No | N/A | N/A | 70.8288 | 71.3877 | 142.2165 | 0.53587 | 2.1424 | 2.6782 | -69.2454 | -139.5383 | -97% | -98.12% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
223 | Expense | Electric Distribution | KB | E Dist Maint UG | KBP | UG EXP Projects | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 788.7754 | 794.9997 | 1583.7752 | 1.0978 | 0.14433 | 1.2422 | -794.8554 | -1582.533 | -99.98% | -99.92% | NO | NO | # of Locations | 255.24 | 255.2413 | 510.4813 | 0 | 3 | 3 | -252.2413 | -507.4813 | -98.82% | -99.41% | YES | Below variance threshold. | Actual units were lower than imputed units because this is a project-based repair program. In 2024, PG&E did not identify any underground repair projects. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. This program supports major project underground work. Completion of work is dependent on the scope of the project.
224 | Expense | Electric Distribution | KB | E Dist Maint UG | KBP | UG EXP Projects | Underground | DUNGD-C004: Planned Major Projects | Ex 4, Ch 11 | No | N/A | N/A | 788.7754 | 794.9997 | 1583.7752 | 1.0978 | 0.14433 | 1.2422 | -794.8554 | -1582.533 | -99.98% | -99.92% | N/A | N/A | # of Locations | 255.24 | 255.2413 | 510.4813 | 0 | 3 | 3 | -252.2413 | -507.4813 | -98.82% | -99.41% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
225 | Expense | Electric Distribution | KB | E Dist Maint UG | KB# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 757.6537 | 763.6324 | 1521.2861 | 0 | -63.9728 | -63.9728 | -827.6052 | -1585.2589 | -108.4% | -104.2% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
226 | Expense | Electric Distribution | KC | E Dist Maint Network | KCA | Ntwk Equip Correct Maint NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 449.8004 | 460.8723 | 910.6727 | 39.5717 | 322.0862 | 361.6578 | -138.7862 | -549.0149 | -30.11% | -60.29% | NO | NO | # of Locations | 80 | 80 | 160 | 17 | 63 | 80 | -17 | -80 | -21.25% | -50% | YES | Below variance threshold. | Actual units were lower than imputed units because this is demand-driven work and fluctuates year over year because there is a wide range of repairs covered in this MAT code and a varying number of repairs per year. Through 2024, fewer tags have been generated from abnormal operating conditions than expected. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to make repairs on network equipment e.g., transformers and protectors.
227 | Expense | Electric Distribution | KC | E Dist Maint Network | KCA | Ntwk Equip Correct Maint NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | No | N/A | N/A | 449.8004 | 460.8723 | 910.6727 | 39.5717 | 322.0862 | 361.6578 | -138.7862 | -549.0149 | -30.11% | -60.29% | N/A | N/A | # locations | 80 | 80 | 160 | 17 | 63 | 80 | -17 | -80 | -21.25% | -50% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
228 | Expense | Electric Distribution | KC | E Dist Maint Network | KCB | Ntwk Oil Repl & 60Day F/U NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 33.8891 | 34.7233 | 68.6123 | 5.2245 | 16.0789 | 21.3033 | -18.6444 | -47.309 | -53.69% | -68.95% | NO | NO | # of Locations | 25 | 25 | 50 | 8 | 7 | 15 | -18 | -35 | -72% | -70% | YES | Below variance threshold. | Actual units were lower than imputed units because fewer than expected transformers were identified as needing oil replacement as a result of dissolved gas analysis (DGA) testing. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to replace oil in network transformers based on dissolved gas analysis, and to perform 60-day follow-up re-torque requirement in order to maintain a safe and reliable distribution network system.
229 | Expense | Electric Distribution | KC | E Dist Maint Network | KCB | Ntwk Oil Repl & 60Day F/U NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | No | N/A | N/A | 33.8891 | 34.7233 | 68.6123 | 5.2245 | 16.0789 | 21.3033 | -18.6444 | -47.309 | -53.69% | -68.95% | N/A | N/A | # locations | 25 | 25 | 50 | 8 | 7 | 15 | -18 | -35 | -72% | -70% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
230 | Expense | Electric Distribution | KC | E Dist Maint Network | KCC | Ntwk Vault Correct Maint NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 134.5293 | 137.8408 | 272.3701 | 7.6588 | 310.5539 | 318.2127 | 172.7131 | 45.8426 | 125.3% | 16.83% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
231 | Expense | Electric Distribution | KC | E Dist Maint Network | KCC | Ntwk Vault Correct Maint NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | No | N/A | N/A | 134.5293 | 137.8408 | 272.3701 | 7.6588 | 310.5539 | 318.2127 | 172.7131 | 45.8426 | 125.3% | 16.83% | N/A | N/A | N/A | 7658.82 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
232 | Expense | Electric Distribution | KC | E Dist Maint Network | KCD | Ntwk Xfmr PrevMaint/Retst NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 2808.6851 | 2877.8214 | 5686.5065 | 4486.7169 | 4056.2771 | 8542.994 | 1178.4557 | 2856.4875 | 40.95% | 50.23% | NO | NO | Transformer Oil Tests | 3600 | 3600 | 7200 | 1363 | 1403 | 2766 | -2197 | -4434 | -61.03% | -61.58% | YES | Below variance threshold. | PG&E changed the unit of measure for this MAT in 2023 from (1) the number of chambers for which we drew oil samples from, to (2) the number of transformers maintained. The 2023 GRC unit forecast was based on the number of chambers that each network transformer can have; network transformers can have up to 3 chambers. The imputed and recorded + forecast units are not comparable. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to perform preventive maintenance on network transformers to maintain a safe and reliable distribution network system.
233 | Expense | Electric Distribution | KC | E Dist Maint Network | KCD | Ntwk Xfmr PrevMaint/Retst NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | No | N/A | N/A | 2808.6851 | 2877.8214 | 5686.5065 | 4486.7169 | 4056.2771 | 8542.994 | 1178.4557 | 2856.4875 | 40.95% | 50.23% | N/A | N/A | # Transformers | 3600 | 3600 | 7200 | 1363 | 1403 | 2766 | -2197 | -4434 | -61.03% | -61.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
234 | Expense | Electric Distribution | KC | E Dist Maint Network | KCE | Ntwk Protector Prev Maint NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 718.8591 | 736.5539 | 1455.413 | 1428.0841 | 1615.0506 | 3043.1347 | 878.4967 | 1587.7217 | 119.3% | 109.1% | NO | NO | Network Protectors | 402 | 402 | 804 | 374 | 474 | 848 | 72 | 44 | 17.91% | 5.473% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
235 | Expense | Electric Distribution | KC | E Dist Maint Network | KCE | Ntwk Protector Prev Maint NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | No | N/A | N/A | 718.8591 | 736.5539 | 1455.413 | 1428.0841 | 1615.0506 | 3043.1347 | 878.4967 | 1587.7217 | 119.3% | 109.1% | N/A | N/A | # network protectors | 402 | 402 | 804 | 374 | 474 | 848 | 72 | 44 | 17.91% | 5.473% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
236 | Expense | Electric Distribution | KC | E Dist Maint Network | KCF | Fiber/SCADA Comm Repr NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 1011.5374 | 1036.4366 | 2047.974 | 185.5123 | 1184.3166 | 1369.8289 | 147.88 | -678.1451 | 14.27% | -33.11% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
237 | Expense | Electric Distribution | KC | E Dist Maint Network | KCF | Fiber/SCADA Comm Repr NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | No | N/A | N/A | 1011.5374 | 1036.4366 | 2047.974 | 185.5123 | 1184.3166 | 1369.8289 | 147.88 | -678.1451 | 14.27% | -33.11% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
238 | Expense | Electric Distribution | OM | Operational Management | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 22 | No | On-going | Annual | 19950.3775 | 20477.3794 | 40427.757 | 12752.99 | 20920.0181 | 33673.0081 | 442.6387 | -6754.7488 | 2.162% | -16.71% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
239 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFC | Cameras | SRM Total | SRM Total | Ex 4, Ch 4.1 | No | On-going | Annual | 0 | 0 | 0 | 12340.4302 | 11018.4514 | 23358.8816 | 11018.4514 | 23358.8816 | 100% | 100% | YES | YES | # of wildfire cameras | 0 | 0 | 0 | 10 | 25 | 35 | 25 | 35 | 100% | 100% | YES | Program expenses exceeded imputed regulatory values because costs for this program were imputed in MAT AB6. Actual expenses for cameras recorded in MAT WFC are within the variance threshold, although they exceeded imputed regulatory values due to 1) the implementation of artificial intelligence (AI) detection on the cameras which was not forecast in the 2023 GRC, and 2) the installation of more units than forecasted. See mitigation WLDFR-M07D in AB6 for the imputed amount for this program. | Actual units were higher than imputed units because 1) wildfire cameras were forecasted in AB6 and recorded in WFC, and 2) PG&E installed more units than forecasted. There were 10 cameras forecasted in AB6 and 25 completed in WFC in 2024. PG&E completed more units than forecasted because the wildfire risk team, working with CAL FIRE, identified numerous locations where additional cameras would reduce overall risk through enhanced situational awareness. See mitigation WLDFR-M07D in AB6 for the imputed units for this program. | Over | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. This program supports the installation, operation and maintenance of wildfire cameras. Scope and Budget forecast status are shown as over because for the remainder of the GRC cycle, costs and units will show over for MAT WFC because imputed amounts are captured in AB6. This program is otherwise proceeding as planned.
240 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFC | Cameras | Wildfire | WLDFR-M07D: Situational Awareness and Forecasting Initiatives - Cameras | Ex 4, Ch 4.1 | No | N/A | N/A | 0 | 0 | 0 | 12340.4302 | 11018.4514 | 23358.8816 | 11018.4514 | 23358.8816 | 100% | 100% | N/A | N/A | # of wildfire cameras | 0 | 0 | 0 | 10 | 25 | 35 | 25 | 35 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
241 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | SRM Total | SRM Total | Ex 4, Ch 4.1 Ex 4, Ch 5 | No | On-going | Annual | 0 | 0 | 0 | 8309.7448 | 9432.6035 | 17742.3483 | 9432.6035 | 17742.3483 | 100% | 100% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values because costs for this program were imputed in MAT AB6. Actual expenses for Other Wildfire Support are recorded in MAT WFM, and the difference between the imputed regulatory value and actual expenses is below the variance threshold. See mitigation EPNDR-C001, WLDFR-M07E, WLDFR-M071, WLDFR-M07J and WLDFR-M07K in AB6 for the imputed amount for this program. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. This program supports PG&E's development operations, and maintenance of the fire potential index and other models that support PSPS, EPSS, and wildfire mitigations. Budget status is shown as over because imputed amounts are captured in AB6. This program is otherwise proceeding as planned.
242 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | Emergency Preparedness & Response | EPNDR-C001: Situational Awareness and Forecasting Initiatives - SOPP Improvements | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 1880.6446 | 0 | 1880.6446 | 0 | 1880.6446 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
243 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | Wildfire | WLDFR-M07E: Situational Awareness and Forecasting Initiatives - Satellite Fire Detection | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 89.732 | 187.3436 | 277.0756 | 187.3436 | 277.0756 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
244 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | Wildfire | WLDFR-M07I: Situational Awareness and Forecasting Initiatives - Advanced Fire Modeling | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 6044.7454 | 6996.5688 | 13041.3143 | 6996.5688 | 13041.3143 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
245 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | Wildfire | WLDFR-M07J: Situational Awareness and Forecasting Initiatives - Meteorology | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 153.6489 | 2139.0933 | 2292.7423 | 2139.0933 | 2292.7423 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
246 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | Wildfire | WLDFR-M07K: Situational Awareness and Forecasting Initiatives - Fire Potential Index | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 140.9738 | 109.5977 | 250.5715 | 109.5977 | 250.5715 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
247 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
248 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFN | PSPS Non-Event Expense | SRM Total | SRM Total | Ex 4, Ch 4.2 | No | On-going | Annual | 0 | 0 | 0 | 19942.8022 | 28489.808 | 48432.6101 | 28489.808 | 48432.6101 | 100% | 100% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values because costs for this program were imputed in MAT AB6 and imputed and recorded to MAT IG#. When comparing to MAT AB6, and IG#, PSPS non-event actual expenses were below forecast due to: 1) lower than forecast costs for exclusive use helicopter contracts, and 2) lower than forecast costs for Community Resource Center (CRC) preparedness. See mitigation WLDFR-M006 in AB6 and IG# for the imputed amount for this program as well as some recorded amounts. The underspend in PSPS was offset by additional spend in Non-RAMP work in this program. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to prepare for PSPS events and improve the PSPS program when activated. Budget status is shown as over, even though actual expenses were under, because there are no imputed amounts in WFN, they are in AB6 and IG#. This program is otherwise proceeding as planned.
249 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFN | PSPS Non-Event Expense | Emergency Preparedness & Response | EPNDR-C005: EP&R Field Operations | Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 203.512 | 0 | 203.512 | 0 | 203.512 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
250 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFN | PSPS Non-Event Expense | Emergency Preparedness & Response | EPNDR-C006: EP&R Distribution Support Headcount | Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 1525.7864 | 6861.7804 | 8387.5668 | 6861.7804 | 8387.5668 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
251 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFN | PSPS Non-Event Expense | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 4.2 | Yes | N/A | N/A | 0 | 0 | 0 | 16155.7024 | 19661.0999 | 35816.8023 | 19661.0999 | 35816.8023 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
252 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFN | PSPS Non-Event Expense | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.2 | Yes | N/A | N/A | 0 | 0 | 0 | 2057.8014 | 1966.9277 | 4024.729 | 1966.9277 | 4024.729 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
253 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFP | PSPS Event Expense | SRM Total | SRM Total | Ex 4, Ch 4.2 | No | On-going | Annual | 0 | 0 | 0 | 5556.1937 | 24510.8988 | 30067.0925 | 24510.8988 | 30067.0925 | 100% | 100% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values because costs for this program were imputed in MAT AB6. Actual expenses for active PSPS events are recorded in MAT WFP and were below imputed regulatory values in AB6 because PSPS events that occurred in 2024 were small in geographic scope and impacted fewer customers. See mitigation WLDFR-M005 in AB6 for the imputed amount for this program. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. This program supports PSPS and the spend is dependent on weather. This programs budget is presented as over, even though the actuals were under, because there were no imputed amounts in WFP, they were in AB6.
254 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFP | PSPS Event Expense | Wildfire | WLDFR-M005: Public Safety Power Shutoff - PSPS Event (Distribution) | Ex 4, Ch 4.2 | Yes | N/A | N/A | 0 | 0 | 0 | 5455.4428 | 23955.7118 | 29411.1546 | 23955.7118 | 29411.1546 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
255 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFP | PSPS Event Expense | Wildfire | POST-GRC: Post-GRC Mitigation | Ex 4, Ch 4.2 | Yes | N/A | N/A | 0 | 0 | 0 | 100.7509 | 555.187 | 655.9379 | 555.187 | 655.9379 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
256 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFS | Safety Infra Protect Team(SIPT) | SRM Total | SRM Total | Ex 4, Ch 4.1 | No | On-going | Annual | 0 | 0 | 0 | 19869.7115 | 20667.55 | 40537.2614 | 20667.55 | 40537.2614 | 100% | 100% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values because costs for this program were imputed in MAT AB6. Actual expenses for SIPT are recorded in MAT WFS and were below imputed regulatory values due to: 1) staffing constraints causing labor costs to be lower than forecast, 2) equipment delivery delays, and 3) fewer catastrophic events requiring deployment of the SIPT. See mitigation WLDFR-M008 in AB6 for the imputed amount for this program. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing. This program supports PG&E crews performing work in high fire risk areas. This programs budget is presented as over, even though the actuals were under, because there were no imputed amounts in WFS, they were in AB6. This program is otherwise proceeding as planned.
257 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFS | Safety Infra Protect Team(SIPT) | Wildfire | WLDFR-M008: Safety and Infrastructure Protection Teams | Ex 4, Ch 4.1 | No | N/A | N/A | 0 | 0 | 0 | 19869.7115 | 20667.55 | 40537.2614 | 20667.55 | 40537.2614 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
258 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFW | Weather Station Maintenance | SRM Total | SRM Total | Ex 4, Ch 4.1 | No | On-going | Annual | 0 | 0 | 0 | 2468.4283 | 2914.8629 | 5383.2911 | 2914.8629 | 5383.2911 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing. This program is for the maintenance of weather stations. This programs budget is presented as over, because there were no imputed amounts in WFW, they were in AB6 for WLDFR-M07B. This program is otherwise proceeding as planned.
259 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFW | Weather Station Maintenance | Wildfire | WLDFR-M07B: Situational Awareness and Forecasting Initiatives - Weather Station | Ex 4, Ch 4.1 | No | N/A | N/A | 0 | 0 | 0 | 2468.4283 | 2914.8629 | 5383.2911 | 2914.8629 | 5383.2911 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
(a) | Program work for Cameras, PSPS, SIPT, Wildfire Mitigation Support, and Weather Station Maintenance were imputed in MAT code AB6 and recorded in MWC WF MAT codes, | [14 empty] | `

## Electric MAT Capital
Table 3-4 2024 RSAR 2023 GRC CYCLE ELECTRIC DISTRIBUTION CAPITAL COMPARISON BY MAT FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | C6 | C7 | D | E | F | G1 | G2 | H | I1 | I2 | J | K1 | K2 | L1 | L2 | L3 | L4 | M | N1 | N2 | O | P1 | P2 | Q | R1 | R2 | S1 | S2 | S3 | T | U | V1 | V2 | V3 | W | X
[13 empty] | Imputed Adopted Costs |  |  | Actual Costs | [9 empty] | Imputed Annual Units |  |  | Actual Annual Units | [9 empty] | Forecast
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name | MAT | MAT Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program/ Project Life (years) | Program/ Project Year | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs | Imputed Cost for 2023 GRC Cycle to Date ($) (G1+G2) | 2023 Actual Costs | 2024 Actual Costs | Actual Cost for 2023 GRC Cycle to Date ($) (I1+I2) | Difference for 2024 ($) (I2-G2) | Difference for 2023 GRC Cycle to Date ($) (J-H) | Spending Percent Variance for 2024 (%) (K1)/G2*100) | Spending Percent Variance for 2023 GRC Cycle (%) (K2/H*100) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | Unit Type | 2023 Imputed Adopted Units | 2024 Imputed Adopted Units | Imputed Units for 2023 GRC Cycle to Date | 2023 Actual Units | 2024 Actual Units | Actual Units for 2023 GRC Cycle to Date | Difference for 2024 (# of Units) (P2-N2) | Difference for 2023 GRC Cycle to Date (# of Units) (Q-O) | Unit Percent Variance for 2024 (%) (R1/N2*100) | Percent Variance for 2023 GRC Cycle to Date (%) (R2/O) | Unit Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | 2024 Unit Variance Explanation | Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T) | Status | 2024 Completion Status Statement
1 | Capital | Electric Distribution | 05 | Tools & Equipment | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 22 | No | On-going | Annual | 7607.7394 | 7913.0622 | 15520.8016 | 9412.6643 | 12978.765 | 22391.4293 | 5065.7028 | 6870.6277 | 64.02% | 44.27% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program that includes the cost of tools and test equipment used by Maintenance, Construction, Substation, Test, and Restoration employees to perform distribution-related work.
2 | Capital | Electric Distribution | 05 | Tools & Equipment | N/A | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 22 | Yes | N/A | N/A | 0 | 0 | 0 | 89.9042 | 190.41 | 280.3142 | 190.41 | 280.3142 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | Capital | Electric Distribution | 05 | Tools & Equipment | N/A | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 22 | Yes | N/A | N/A | 7607.7394 | 7913.0622 | 15520.8016 | 9322.7601 | 12788.355 | 22111.1151 | 4875.2928 | 6590.3135 | 61.61% | 42.46% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
4 | Capital | Electric Distribution | 06 | E Dist. Line Capacity | 06A | Fdr Prj Assoc w/Subst Capacity | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 10498.7578 | 10964.7954 | 21463.5532 | 24351.0927 | 38077.5071 | 62428.5998 | 27112.7117 | 40965.0466 | 247.3% | 190.9% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to additional capacity funding deployed in 2024 via SB 410 and Energization Capacity New Business Interim Memorandum Account (ECNBIMA) to provide distribution line capacity to energize customer loads. | N/A | Over | Over | Over | Expanded | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to conduct distribution capacity line work associated with substation capacity projects. PG&E expects to continue to do more work in this program than forecasted due to SB410 requirements, as discussed in PG&E's 2023 GRC capacity phase filing.
5 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06B | Transformer Repl Overloaded | SRM Total | SRM Total | Ex 4, Ch 17 | No | On-going | Annual | 8523.8734 | 8902.2463 | 17426.1197 | 1383.8001 | 10254.0898 | 11637.8899 | 1351.8435 | -5788.2298 | 15.19% | -33.22% | NO | NO | # transformers | 240 | 240 | 480 | 34 | 320 | 354 | 80 | -126 | 33.33% | -26.25% | YES | Below variance threshold. | Actual units were higher than imputed units because additional funding was provided in 2024, because of SB 410 and Energization Capacity New Business Interim Memorandum Account (ECNBIMA) to provide distribution line capacity to energize customer loads. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform overloaded secondary transformer replacements. In the 2023 GRC cycle, PG&E expects to replace overloaded transformers at a higher pace than in 2023 and 2024, in support of the Distribution Overhead risk.
6 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06B | Transformer Repl Overloaded | Distribution Overhead | DOVHD-C09A: Overloaded Transformers Replacement | Ex 4, Ch 17 | No | N/A | N/A | 8523.8734 | 8902.2463 | 17426.1197 | 1383.8001 | 10254.0898 | 11637.8899 | 1351.8435 | -5788.2298 | 15.19% | -33.22% | N/A | N/A | # transformers | 240 | 240 | 480 | 34 | 320 | 354 | 80 | -126 | 33.33% | -26.25% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06D | Circuits Reinforce-DP Managed | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 4674.2293 | 4881.7173 | 9555.9467 | 377.4545 | 881.7948 | 1259.2493 | -3999.9225 | -8296.6974 | -81.94% | -86.82% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program which performs distribution circuit reinforcements. This is part of a continuing effort to mitigate distribution line overloads and planning criteria violations.
8 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06E | Circuits Reinforce-PS Managed | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 25025.8287 | 26136.7196 | 51162.5483 | 12634.5253 | 23951.6321 | 36586.1574 | -2185.0875 | -14576.3909 | -8.36% | -28.49% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program which performs distribution circuit reinforcements. This is part of a continuing effort to mitigate distribution line overloads and planning criteria violations.
9 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06G | Voltage Correct Secondary | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 2869.6654 | 2997.0492 | 5866.7145 | 4022.729 | 4451.4666 | 8474.1955 | 1454.4174 | 2607.481 | 48.53% | 44.45% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program which addresses secondary voltage violations through work such as service replacements.
10 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06H | Dist Line New Business Perf | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 74966.2895 | 78294.0263 | 153260.3158 | 102998.7147 | 137056.0211 | 240054.7357 | 58761.9948 | 86794.42 | 75.05% | 56.63% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to additional capacity funding deployed in 2024 via SB 410 and Energization Capacity New Business Interim Memorandum Account (ECNBIMA) to provide distribution line capacity to energize customer loads. | N/A | Over | Over | Over | Expanded | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to provides the capacity necessary to complete new customer applications for service. There has been an increase in new applications for service and added loads that require capacity work to serve, especially in the areas of: transportation electrification, internet based distribution centers, high tech campuses, state and local infrastructure, agricultural well pumping, dairy bio digesters, and indoor cultivation. PG&E expects to continue to do more work in this program than forecasted due to SB410 requirements, as discussed in PG&E's 2023 GRC capacity Phase filing.
11 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06I | Operational Capacity Proj | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 7014.6541 | 7326.033 | 14340.6872 | 1975.9135 | 2347.5295 | 4323.443 | -4978.5035 | -10017.2441 | -67.96% | -69.85% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program which improves operational capacity for clearances and emergencies, and will continue through the remainder of the 2023 GRC cycle.
12 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06K | Power Factor Management | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 1167.3831 | 1219.203 | 2386.5861 | 162.4885 | -4.3113 | 158.1772 | -1223.5143 | -2228.4089 | -100.4% | -93.37% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program which improves distribution power factor for more efficient use of distribution line and substation assets. PG&E underspent in this program due to increased spending in MAT 06H, which provides capacity for new customer applications for service.
13 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06P | 06P_Enable DG Dist Line | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 1401.3385 | 1463.5436 | 2864.8821 | 109.1745 | 0.4291 | 109.6036 | -1463.1145 | -2755.2785 | -99.97% | -96.17% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program which replaces voltage regulator controls to enable two-way power flow on distribution lines. PG&E underspent in this program due to increased spending in MAT 06H, which provides capacity for new customer applications for service.
14 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 7438.2606 | 7768.4433 | 15206.704 | 7246.1295 | 706.1002 | 7952.2296 | -7062.3432 | -7254.4743 | -90.91% | -47.71% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | The purpose of the MAT 06# is to provide line voltage regulator revolving stock. This MAT centrally managed equipment stock to use as needed which minimizes surplus stock, and is expected to continue through the remainder of PG&E's 2023 GRC period.
15 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07A | Tree Connect VM Assessments | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | 0 | 0 | 0 | -1366.6593 | -173.216 | -1539.8754 | -173.216 | -1539.8754 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program records costs and reimbursements for joint utility pole replacements and arborist assessments as part of vegetation management. This program will continue through the remainder of PG&E's 2023 GRC period.
16 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07C | Special Criteria Pole Repl | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 3150.422 | 3290.2686 | 6440.6906 | 15717.3808 | 11218.7095 | 26936.0903 | 7928.4409 | 20495.3997 | 241% | 318.2% | NO | NO | # poles | 269.69 | 269.6914 | 539.3814 | 581 | 469 | 1050 | 199.3086 | 510.6186 | 73.9% | 94.67% | YES | Below variance threshold. | Actual units were higher than imputed units due to higher volume of tree connect attachments identified as needing replacement than forecast in the 2023 GRC. Tree connects are identified during inspections and prioritized according to the urgency for replacement. For this program the costs are directly associated with the number of poles installed. | Over | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to proactively replace dead, dying, and declining trees being used as a utility power pole prior to premature failure. This program is demand driven based on find rates and associated notifications, and the urgency of the notifications. In the 2023 GRC Final Decision, the Commission adopted a lower unit cost than PG&E forecasted, also contributing to the higher amount of actuals for this program.
17 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07C | Special Criteria Pole Repl | Wildfire | WLDFR-M013: Pole Programs - Replace Tree Attachments | Ex 4, Ch 12 | No | N/A | N/A | 3150.422 | 3290.2686 | 6440.6906 | 15717.3808 | 11218.7095 | 26936.0903 | 7928.4409 | 20495.3997 | 241% | 318.2% | N/A | N/A | # poles | 269.69 | 269.6914 | 539.3814 | 581 | 469 | 1050 | 199.3086 | 510.6186 | 73.9% | 94.67% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
18 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07D | Pole Repl | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 352006.1026 | 367631.5748 | 719637.6774 | 333775.75 | 543832.6285 | 877608.3785 | 176201.0537 | 157970.7012 | 47.93% | 21.95% | YES | YES | # poles | 15963.85 | 15963.8524 | 31927.7024 | 13786 | 17546 | 31332 | 1582.1476 | -595.7024 | 9.911% | -1.866% | NO | Program expenditures exceeded imputed regulatory values due to larger volume of units completed to address notifications in HFTD and higher unit cost than was adopted in the 2023 GRC. | Below variance threshold | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to proactively replace degraded or deteriorated poles, prior to premature failure. PG&E will prioritize this work for the remainder of the 2023 GRC cycle to meet WMP commitments. PG&E anticipates the program scope will remain on target and spending will remain higher than imputed over the remainder of the cycle due to higher volumes of degraded pole replacements to address the maintenance log.
19 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07D | Pole Repl | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | No | N/A | N/A | 352006.1026 | 367631.5748 | 719637.6774 | 333775.75 | 543832.6285 | 877608.3785 | 176201.0537 | 157970.7012 | 47.93% | 21.95% | N/A | N/A | # poles | 15963.85 | 15963.8524 | 31927.7024 | 13786 | 17546 | 31332 | 1582.1476 | -595.7024 | 9.911% | -1.866% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
20 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07D | Pole Repl | Wildfire | WLDFR-C12C: Pole Replacement | Ex 4, Ch 12 | No | N/A | N/A | 352006.1026 | 367631.5748 | 719637.6774 | 333775.75 | 543832.6285 | 877608.3785 | 176201.0537 | 157970.7012 | 47.93% | 21.95% | N/A | N/A | # poles | 15963.85 | 15963.8524 | 31927.7024 | 13786 | 17546 | 31332 | 1582.1476 | -595.7024 | 9.911% | -1.866% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07G | Pole Joint Util Telco Reimb | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | 0 | 0 | 0 | 0.0001 | 0.08685 | 0.08695 | 0.08685 | 0.08695 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is for reimbursement of costs incurred with other utilities for joint use of poles.
22 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07L | Steel Lattice Structures | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | 0 | 0 | 0 | 7.1779 | 0.61025 | 7.7882 | 0.61025 | 7.7882 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is for steel lattice tower - pole replacements in non-HFTD zones.
23 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07O | Overloaded Pole Replacements | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 7488.796 | 7821.222 | 15310.018 | 12424.3815 | 8228.4568 | 20652.8383 | 407.2348 | 5342.8203 | 5.207% | 34.9% | NO | NO | # poles | 261.88 | 261.8795 | 523.7595 | 304 | 163 | 467 | -98.8795 | -56.7595 | -37.76% | -10.84% | YES | Below variance threshold. | Actual units were lower than imputed units due to higher unit cost of external contractors. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to proactively replaced all overloaded poles, prior to premature failure.
24 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07O | Overloaded Pole Replacements | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | No | N/A | N/A | 7488.796 | 7821.222 | 15310.018 | 12424.3815 | 8228.4568 | 20652.8383 | 407.2348 | 5342.8203 | 5.207% | 34.9% | N/A | N/A | # poles | 261.88 | 261.8795 | 523.7595 | 304 | 163 | 467 | -98.8795 | -56.7595 | -37.76% | -10.84% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
25 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07O | Overloaded Pole Replacements | Wildfire | WLDFR-C12D: Overloaded Pole Replacement | Ex 4, Ch 12 | No | N/A | N/A | 7488.796 | 7821.222 | 15310.018 | 12424.3815 | 8228.4568 | 20652.8383 | 407.2348 | 5342.8203 | 5.207% | 34.9% | N/A | N/A | # poles | 261.88 | 261.8795 | 523.7595 | 304 | 163 | 467 | -98.8795 | -56.7595 | -37.76% | -10.84% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
26 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07R | Dist Pole Reinforce | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | 0 | 0 | 0 | 0 | 10531.2996 | 10531.2996 | 10531.2996 | 10531.2996 | 100% | 100% | NO | YES | # poles | 0 | 0 | 0 | 0 | 5139 | 5139 | 5139 | 5139 | 100% | 100% | YES | Program expenditures exceeded imputed regulatory values because imputed costs are in MAT GAD but starting in 2024 PG&E started managing this program in MAT 07R. In comparing imputed costs in GAD to recorded costs in 07R, this program is over imputed amounts and above the percentage variance threshold, but below the minimum variance it is subject to ($10M). | Actual units were higher than imputed units because this program was forecasted in MAT GAD. In comparing imputed units in GAD to recorded in 07R, this program is over imputed but within the variance threshold for units. | Over | Over | Over | Emergent | This program's work is ongoing and will continue in PG&E's 2023 GRC period. Work that was previously performed under MAT GAD for pole reinforcements will be completed under MAT 07R moving forward. In 2024 PG&E determined that this program could be capitalized.
27 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07R | Dist Pole Reinforce | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | No | N/A | N/A | 0 | 0 | 0 | 0 | 10531.2996 | 10531.2996 | 10531.2996 | 10531.2996 | 100% | 100% | N/A | N/A | # poles | 0 | 0 | 0 | 0 | 5139 | 5139 | 5139 | 5139 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
28 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07R | Dist Pole Reinforce | Wildfire | WLDFR-C12E: Pole Restoration Program | Ex 4, Ch 12 | No | N/A | N/A | 0 | 0 | 0 | 0 | 10531.2996 | 10531.2996 | 10531.2996 | 10531.2996 | 100% | 100% | N/A | N/A | # poles | 0 | 0 | 0 | 0 | 5139 | 5139 | 5139 | 5139 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
29 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | 0 | 0 | 0 | 426.3886 | -2023.3251 | -1596.9366 | -2023.3251 | -1596.9366 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Under | Proceeding as Planned | PG&E expects to continue using this MAT to record other costs for installing or replacing overhead poles if needed.
30 | Capital | Electric Distribution | 08 | E Dist Replace OH Asset | 08J | Repl Deteriorated OH Conductor | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 44888.0629 | 46880.634 | 91768.697 | 17008.8034 | 4948.2993 | 21957.1027 | -41932.3347 | -69811.5943 | -89.44% | -76.07% | YES | YES | # circuit miles | 73.6 | 73.6354 | 147.2354 | 26.8 | 0 | 26.8 | -73.6354 | -120.4354 | -100% | -81.8% | YES | Program expenditures were below imputed regulatory values due to reprioritization to System Hardening work in HFTD areas to reduce ignition risk. | Actual units were lower than imputed units due to reprioritization of the MWC to focus on System Hardening work (08W) in HFTD areas, to reduce ignition risk. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace deteriorated OH conductor in non-HFTDs prior to premature failure. For the remainder of the GRC cycle, PG&E anticipates that this program will continue to be lower priority than other work in Electric Distribution like wildfire mitigation and capacity work.
31 | Capital | Electric Distribution | 08 | E Dist Replace OH Asset | 08J | Repl Deteriorated OH Conductor | Distribution Overhead | DOVHD-C004: Overhead Conductor Replacement | Ex 4, Ch 13 | No | N/A | N/A | 44888.0629 | 46880.634 | 91768.697 | 17008.8034 | 4948.2993 | 21957.1027 | -41932.3347 | -69811.5943 | -89.44% | -76.07% | N/A | N/A | # circuit miles | 73.6 | 73.6354 | 147.2354 | 26.8 | 0 | 26.8 | -73.6354 | -120.4354 | -100% | -81.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
32 | Capital | Electric Distribution | 08 | E Dist Replace OH Asset | 08S | Replace Obsolete OH Switches | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 314.8767 | 328.854 | 643.7306 | 124.9971 | 910.3932 | 1035.3902 | 581.5392 | 391.6596 | 176.8% | 60.84% | NO | NO | # of Switches Installed/replaced | 9.29 | 9.2898 | 18.5798 | 1 | 15 | 16 | 5.7102 | -2.5798 | 61.47% | -13.89% | YES | Below variance threshold. | Actual units were higher than imputed units due to performing work that was originally planned for 2023, but was delayed due to reprioritization of the MWC to focus on System Hardening work (08W) in HFTD areas, to reduce ignition risk. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to replace obsolete OH switches and minimize potential safety issues.
33 | Capital | Electric Distribution | 08 | E Dist Replace OH Asset | 08S | Replace Obsolete OH Switches | Distribution Overhead | DOVHD-M006: Grasshopper and KPF Switch Replacement | Ex 4, Ch 13 | No | N/A | N/A | 314.8767 | 328.854 | 643.7306 | 124.9971 | 910.3932 | 1035.3902 | 581.5392 | 391.6596 | 176.8% | 60.84% | N/A | N/A | # of Switches Installed/replaced | 9.29 | 9.2898 | 18.5798 | 1 | 15 | 16 | 5.7102 | -2.5798 | 61.47% | -13.89% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
34 | Capital | Electric Distribution | 08 | E Dist Replace OH Asset | 08# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 13 | No | On-going | Annual | 0 | 0 | 0 | -89.4184 | -1757.2754 | -1846.6938 | -1757.2754 | -1846.6938 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Under | Proceeding as Planned | N/A
35 | Capital | Electric Distribution | 08/3U | E Dist Replace OH Asset | 08W/3UG | Wildfire Resiliency projects | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | On-going | Annual | 768193.114 | 1011990.476 | 1780183.59 | 1091088.0691 | 990537.8456 | 2081625.9147 | -21452.6304 | 301442.3247 | -2.12% | 16.93% | YES | NO | # circuit miles | 303.56 | 414 | 717.56 | 424.9 | N/A | 424.9 | -414 | -292.66 | -100% | -40.79% | YES | Program expenditures were below imputed regulatory values due to a lower volume of Underground and Overhead miles completed. The program executed mileage in 2024 in closer alignment to the 2023-2025 Wildfire Mitigation Plan 2024 Change Order, resulting in an underrun in dollars and miles. | Actual units were lower than imputed units due to a lower volume of Underground and Overhead miles completed. The program executed mileage in 2024 in closer alignment to the 2023-2025 Wildfire Mitigation Plan 2024 Change Order, resulting in an underrun in dollars and miles. | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to conduct System Hardening for wildfire mitigation. Since filing the 2023 GRC, PG&E began recording undergrounding costs associated with this program to new MAT code 3UG, so PG&E is combining the codes because the work is the same as what was imputed in 08W. PG&E is reporting the status as "Proceeding as Planned" because PG&E intends, over the 2023 GRC cycle, to manage the program according to the 2023 GRC Final Decision; adjusting volumes of units in the later years to account for overage in year 2023.
36 | Capital | Electric Distribution | 08/3U | E Dist Replace OH Asset | 08W/3UG | Wildfire Resiliency projects | Distribution Overhead | DOVHD-M002: System Hardening | Ex 4, Ch 4.3 | No | N/A | N/A | 768193.114 | 1011990.476 | 1780183.59 | 1090579.7795 | 990457.307 | 2081037.0866 | -21533.169 | 300853.4966 | -2.128% | 16.9% | N/A | N/A | # circuit miles | 303.56 | 414 | 717.56 | 424.9 | 326 | 750.9 | -88 | 33.34 | -21.26% | 4.646% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
37 | Capital | Electric Distribution | 08/3U | E Dist Replace OH Asset | 08W/3UG | Wildfire Resiliency projects | Wildfire | WLDFR-M002: System Hardening | Ex 4, Ch 4.3 | No | N/A | N/A | 768193.114 | 1011990.476 | 1780183.59 | 1090579.7795 | 990457.307 | 2081037.0866 | -21533.169 | 300853.4966 | -2.128% | 16.9% | N/A | N/A | # circuit miles | 303.56 | 414 | 717.56 | 424.9 | 326 | 750.9 | -88 | 33.34 | -21.26% | 4.646% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
38 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09A | ED Line SCADA Inst/Repl | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 16 | No | On-going | Annual | 0 | 0 | 0 | 3.046 | 0.5084 | 3.5544 | 0.5084 | 3.5544 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program work for SCADA / RTU replacements outside of substations is ongoing and is recorded in MAT 49A. Minimal costs may still be recorded but MAT 09A has been retired.
39 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09B | ED Sub SCADA/RTU Replace | SRM Total | SRM Total | Ex 4, Ch 16 | No | On-going | Annual | 20074.1028 | 20879.7403 | 40953.8431 | 16712.95 | 29257.2056 | 45970.1556 | 8377.4653 | 5016.3125 | 40.12% | 12.25% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC cycle. The purpose of this program is a continuing effort to replace aging infrastructure.
40 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09B | ED Sub SCADA/RTU Replace | Distribution Overhead | DOVHD-C007: Supervisory Control and Data Acquisition | Ex 4, Ch 16 | Yes | N/A | N/A | 20074.1028 | 20879.7403 | 40953.8431 | 2825.896 | 11253.5883 | 14079.4843 | -9626.152 | -26874.3588 | -46.1% | -65.62% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
41 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09B | ED Sub SCADA/RTU Replace | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 16 | Yes | N/A | N/A | 0 | 0 | 0 | 13887.054 | 18003.6173 | 31890.6713 | 18003.6173 | 31890.6713 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09D | ED Sub SCADA/RTU Install | SRM Total | SRM Total | Ex 4, Ch 16 | No | On-going | Annual | 517.6538 | 538.4289 | 1056.0828 | 421.6553 | 866.9467 | 1288.602 | 328.5178 | 232.5192 | 61.01% | 22.02% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC cycle. The purpose of this program is a continuing effort to implement new infrastructure.
43 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09D | ED Sub SCADA/RTU Install | Distribution Overhead | DOVHD-C007: Supervisory Control and Data Acquisition | Ex 4, Ch 16 | No | N/A | N/A | 517.6538 | 538.4289 | 1056.0828 | 421.6553 | 866.9467 | 1288.602 | 328.5178 | 232.5192 | 61.01% | 22.02% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
44 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09E | ED Sub Protect Relay Inst/Repl | SRM Total | SRM Total | Ex 4, Ch 16 | No | On-going | Annual | 3032.8639 | 3167.492 | 6200.3559 | 226.3845 | 2520.3042 | 2746.6887 | -647.1878 | -3453.6672 | -20.43% | -55.7% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC cycle. The purpose of this program is a continuing effort to replace aging infrastructure. The recorded values were lower that imputed due to increase in emergency replacements of failed equipment as described in the emergency work MWC 09F.
45 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09E | ED Sub Protect Relay Inst/Repl | Distribution Overhead | DOVHD-C007: Supervisory Control and Data Acquisition | Ex 4, Ch 16 | No | N/A | N/A | 3032.8639 | 3167.492 | 6200.3559 | 226.3845 | 2520.3042 | 2746.6887 | -647.1878 | -3453.6672 | -20.43% | -55.7% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
46 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09F | ED Sub SCADA Emergency Repl | SRM Total | SRM Total | Ex 4, Ch 16 | No | On-going | Annual | 5970.5152 | 6210.1309 | 12180.6461 | 11181.4725 | 11110.7664 | 22292.2389 | 4900.6355 | 10111.5928 | 78.91% | 83.01% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC cycle. PG&E's recorded amount is higher than the imputed due to an increase is equipment failure higher than the 3-year average used to develop the forecast.
47 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09F | ED Sub SCADA Emergency Repl | Distribution Overhead | DOVHD-C007: Supervisory Control and Data Acquisition | Ex 4, Ch 16 | No | N/A | N/A | 5970.5152 | 6210.1309 | 12180.6461 | 11181.4725 | 11110.7664 | 22292.2389 | 4900.6355 | 10111.5928 | 78.91% | 83.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
48 | Capital | Electric Distribution | 17 | E Dist Routine Emergency | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 6 | No | On-going | Annual | 249483.0313 | 260557.5273 | 510040.5587 | 395409.8326 | 480188.8797 | 875598.7123 | 219631.3524 | 365558.1537 | 84.29% | 71.67% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to higher than forecast volume of emergency events, driving higher overall contract spend, over head costs, and higher labor charges. | N/A | Over | Over | Over | Emergent | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This is a demand driven program. The purpose of this program is to address routine emergencies and conditions in the field that require immediate attention. PG&E expects to continue to spend more on this program than forecasted.
49 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | No | On-going | Annual | 28274.9198 | 29475.8313 | 57750.7511 | 33687.5719 | 40138.2776 | 73825.8494 | 10662.4463 | 16075.0983 | 36.17% | 27.84% | NO | YES | # weather stations | 150 | 150 | 300 | 102 | 50 | 152 | -100 | -148 | -66.67% | -49.33% | YES | Program expenditures exceeded imputed regulatory values due to increases in environmental and federal permitting costs since forecasted in the 2023 GRC. Lower costs for EP&R and the Sensor IQ program, which has been discontinued, was off-set by 1) costs for wildfire risk model development which were not forecasted in the 2023 GRC; and 2) new budgeting, forecasting for integrated grid planning (IGP) systems. | Actual units were lower than imputed units due to two factors: 1) through 2022, weather stations were installed ahead of plan allowing for a scale back of program units in 2024; 2) and costs for environmental and federal land permitting has increased since the GRC was forecasted; therefore fewer program units were completed for the costs allocated. | Under | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is for various capital activities that enable electric operations. This program includes costs for activities like the Emergency Operating Centers (EOCs), facilities upgrades, IT enhancements, and Applied Technology Services (ATS) lab safety and upgrades. For the remainder of the GRC cycle this program will proceed with some program costs being lower, off-set by some being higher than forecasted.
50 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Emergency Preparedness & Response | EPNDR-C000: EP&R Controls | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 2427.2369 | 2427.2369 | 2427.2369 | 2427.2369 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
51 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Emergency Preparedness & Response | EPNDR-C002: Situational Awareness and Forecasting Initiatives - WSOC | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 113.14 | 118.1621 | 231.3021 | 21.2327 | -88.4717 | -67.2391 | -206.6338 | -298.5411 | -174.9% | -129.1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
52 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Emergency Preparedness & Response | EPNDR-C004: EP&R Field Operations Technology | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 3582.896 | 3726.6888 | 7309.5848 | 1471.8155 | 0 | 1471.8155 | -3726.6888 | -5837.7693 | -100% | -79.86% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
53 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Emergency Preparedness & Response | EPNDR-M000: EP&R Mitigations | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 2235.569 | 2334.8052 | 4570.3742 | 4574.6291 | 1985.9211 | 6560.5502 | -348.8841 | 1990.176 | -14.94% | 43.55% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
54 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Distribution Overhead | DOVHD-M002: System Hardening | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | No | N/A | N/A | 0 | 0 | 0 | 0 | 2906.4889 | 2906.4889 | 2906.4889 | 2906.4889 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
55 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M002: System Hardening | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 2906.4889 | 2906.4889 | 2906.4889 | 2906.4889 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
56 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 276.9734 | 289.2665 | 566.2399 | 4.9574 | 3.0238 | 7.9812 | -286.2427 | -558.2587 | -98.95% | -98.59% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
57 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M07B: Situational Awareness and Forecasting Initiatives - Weather Station | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 3587.1379 | 3731.0793 | 7318.2172 | 3955.822 | 1991.0631 | 5946.8851 | -1740.0162 | -1371.3321 | -46.64% | -18.74% | N/A | N/A | # weather stations | 150 | 150 | 300 | 102 | 50 | 152 | -100 | -148 | -66.67% | -49.33% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
58 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M07F: Situational Awareness and Forecasting Initiatives - Sensor IQ | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 11118.9587 | 11612 | 22730.9587 | -0.00012 | 0 | -0.00012 | -11612 | -22730.9588 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
59 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M07G: Situational Awareness and Forecasting Initiatives - Partial Voltage Detection | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 0 | 0 | 0 | 0.1292 | 0 | 0.1292 | 0 | 0.1292 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
60 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M07J: Situational Awareness and Forecasting Initiatives - Meteorology | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 1187.7069 | 1235.3662 | 2423.0731 | 904.3723 | 2609.1909 | 3513.5631 | 1373.8247 | 1090.49 | 111.2% | 45% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
61 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M008: Safety and Infrastructure Protection Teams | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 262.2296 | 273.8683 | 536.0979 | 6.1137 | 224.0285 | 230.1422 | -49.8398 | -305.9558 | -18.2% | -57.07% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
62 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M009: Community Wildfire Safety Program PMO | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 0 | 0 | 0 | 12915.1254 | 6503.9591 | 19419.0845 | 6503.9591 | 19419.0845 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
63 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M017: System Hardening - Remote Grid | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 0 | 0 | 0 | 4538.5339 | 1614.6187 | 6153.1526 | 1614.6187 | 6153.1526 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
64 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 2282.2344 | 2282.2344 | 2282.2344 | 2282.2344 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
65 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | POST-GRC: Post 2023 GRC Mitigation | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 1627.5547 | 1627.5547 | 1627.5547 | 1627.5547 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
66 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 5910.309 | 6154.1363 | 12064.4453 | 5294.8408 | 16051.4292 | 21346.27 | 9897.2929 | 9281.8247 | 160.8% | 76.94% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
67 | Capital | Electric Distribution | 25 | Install New Electric Meters | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 31396.1237 | 32789.7907 | 64185.9144 | 30468.9532 | 31179.4303 | 61648.3836 | -1610.3603 | -2537.5308 | -4.911% | -3.953% | NO | NO | # of Field Orders | 129889.51 | 129889.5111 | 259779.0211 | 142998 | 151935 | 294933 | 22045.4889 | 35153.9789 | 16.97% | 13.53% | NO | Below variance threshold. | Below variance threshold | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC cycle. The purpose of this program is a continuing effort to perform electric meter installations, exchanges, and removals at customer locations.
68 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AA | OH Genl Repl | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 138779.5103 | 144939.9018 | 283719.4121 | 291909.6035 | 252206.6457 | 544116.2492 | 107266.7439 | 260396.8371 | 74.01% | 91.78% | YES | YES | # notifications | 19547.77 | 19547.7738 | 39095.5438 | 20136 | 17825 | 37961 | -1722.7738 | -1134.5438 | -8.813% | -2.902% | NO | Program expenditures exceeded imputed regulatory values due to higher unit costs than adopted in the 2023 GRC Final Decision. | Below variance threshold | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of the program is to replace deteriorated overhead facilities that are not an imminent hazard. PG&E will continue to prioritize this work throughout the 2023 GRC cycle to meet WMP commitments. PG&E anticipates the program scope will remain on target and spending will remain higher than imputed over the remainder of the cycle, due to higher unit costs than the GRC imputed adopted unit costs and higher volumes to address the maintenance log.
69 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AA | OH Genl Repl | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 138779.5103 | 144939.9018 | 283719.4121 | 291909.6035 | 252206.6457 | 544116.2492 | 107266.7439 | 260396.8371 | 74.01% | 91.78% | N/A | N/A | # notifications | 19547.77 | 19547.7738 | 39095.5438 | 20136 | 17825 | 37961 | -1722.7738 | -1134.5438 | -8.813% | -2.902% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
70 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AA | OH Genl Repl | Wildfire | WLDFR-C008: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 138779.5103 | 144939.9018 | 283719.4121 | 291909.6035 | 252206.6457 | 544116.2492 | 107266.7439 | 260396.8371 | 74.01% | 91.78% | N/A | N/A | # notifications | 19547.77 | 19547.7738 | 39095.5438 | 20136 | 17825 | 37961 | -1722.7738 | -1134.5438 | -8.813% | -2.902% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
71 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AB | Bird Safe Inst/Repl | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 3623.2476 | 3784.0828 | 7407.3304 | 2018.6656 | 1430.9482 | 3449.6138 | -2353.1346 | -3957.7166 | -62.19% | -53.43% | NO | NO | # notifications | 967 | 966.7397 | 1933.7397 | 407 | 354 | 761 | -612.7397 | -1172.7397 | -63.38% | -60.65% | YES | Below variance threshold. | Actual units were lower than imputed units because there was a lower occurrence of bird-safety incidents and associated notifications for this program in 2024. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of the program is to perform capital modifications to bird-safe incident and/or adjacent poles in response to a bird electrocution, per US Fish and Wildlife Services (USFWS) requirements and utility operating standard S2321. Spending in this program is based on volume of bird-safe incidents and the prioritization of tags within the 2A MWC.
72 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AB | Bird Safe Inst/Repl | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 3623.2476 | 3784.0828 | 7407.3304 | 2018.6656 | 1430.9482 | 3449.6138 | -2353.1346 | -3957.7166 | -62.19% | -53.43% | N/A | N/A | # notifications | 967 | 966.7397 | 1933.7397 | 407 | 354 | 761 | -612.7397 | -1172.7397 | -63.38% | -60.65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
73 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AB | Bird Safe Inst/Repl | Wildfire | WLDFR-C011: Animal Abatement | Ex 4, Ch 11 | No | N/A | N/A | 3623.2476 | 3784.0828 | 7407.3304 | 2018.6656 | 1430.9482 | 3449.6138 | -2353.1346 | -3957.7166 | -62.19% | -53.43% | N/A | N/A | # notifications | 967 | 966.7397 | 1933.7397 | 407 | 354 | 761 | -612.7397 | -1172.7397 | -63.38% | -60.65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
74 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AC | Bird Safe Inst/Repl Annual | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 3770.4302 | 3937.7988 | 7708.2291 | 1728.3523 | 5142.0416 | 6870.3939 | 1204.2428 | -837.8352 | 30.58% | -10.87% | NO | NO | # notifications | 977.7 | 977.6961 | 1955.3961 | 296 | 879 | 1175 | -98.6961 | -780.3961 | -10.09% | -39.91% | NO | Below variance threshold. | Below variance threshold | On-Target | On-Target | On-Target | Proceeding as Planned | This program is ongoing. The purpose of this program is to perform capital work as part of an annual pole retrofit program to prevent bird electrocutions, per US Fish and Wildlife Services (USFWS) requirements and utility operating standard.
75 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AC | Bird Safe Inst/Repl Annual | Wildfire | WLDFR-C011: Animal Abatement | Ex 4, Ch 11 | No | N/A | N/A | 3770.4302 | 3937.7988 | 7708.2291 | 1728.3523 | 5142.0416 | 6870.3939 | 1204.2428 | -837.8352 | 30.58% | -10.87% | N/A | N/A | # notifications | 977.7 | 977.6961 | 1955.3961 | 296 | 879 | 1175 | -98.6961 | -780.3961 | -10.09% | -39.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
76 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AE | OH COE Repl | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 29330.0649 | 30632.02 | 59962.0849 | 65524.2854 | 68336.649 | 133860.9344 | 37704.629 | 73898.8495 | 123.1% | 123.2% | YES | YES | # of Notifications Completed | 822.85 | 822.848 | 1645.698 | 1031 | 1050 | 2081 | 227.152 | 435.302 | 27.61% | 26.45% | YES | Program expenditures exceeded imputed regulatory values due to the higher volume of tags completed, increased unit costs, and increased costs associated with the types of facilities addressed in 2024. | Actual units were higher than imputed units because PG&E needed to complete more program units to improve customer reliability and prevent outages. | Over | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to identify equipment (through failure/inspections) that impacts the reliability of system operations. Spending in this program is based on find rates and the prioritization of tags within the MWC 2A.
77 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AE | OH COE Repl | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 29330.0649 | 30632.02 | 59962.0849 | 65524.2854 | 68336.649 | 133860.9344 | 37704.629 | 73898.8495 | 123.1% | 123.2% | N/A | N/A | # of Notifications Completed | 822.85 | 822.848 | 1645.698 | 1031 | 1050 | 2081 | 227.152 | 435.302 | 27.61% | 26.45% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
78 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AF | OH Idle Facility Remove | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 2843.6999 | 2969.9311 | 5813.631 | 9538.3149 | 16500.6034 | 26038.9182 | 13530.6723 | 20225.2873 | 455.6% | 347.9% | NO | YES | # facilities | 322.86 | 322.861 | 645.721 | 1005 | 1877 | 2882 | 1554.139 | 2236.279 | 481.4% | 346.3% | YES | Program expenditures exceeded imputed regulatory values due to higher volume of idle faculties identified for removal combined with the mix in the scope of the work/type of facility removed. | Actual units were higher than imputed units because of the volume of idle facilities identified and PG&E's commitment to wildfire mitigation; more program units were completed to mitigate fire risk and reduce system hazards. | Over | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to identify overhead idle facilities through investigations and take appropriate remedial measures. In the 2023 GRC cycle, PG&E expects to continue to complete more units than imputed as idle facility removals are an important wildfire mitigation.
79 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AF | OH Idle Facility Remove | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 2843.6999 | 2969.9311 | 5813.631 | 9538.3149 | 16500.6034 | 26038.9182 | 13530.6723 | 20225.2873 | 455.6% | 347.9% | N/A | N/A | # facilities | 322.86 | 322.861 | 645.721 | 1005 | 1877 | 2882 | 1554.139 | 2236.279 | 481.4% | 346.3% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
80 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AF | OH Idle Facility Remove | Wildfire | WLDFR-C008: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 2843.6999 | 2969.9311 | 5813.631 | 9538.3149 | 16500.6034 | 26038.9182 | 13530.6723 | 20225.2873 | 455.6% | 347.9% | N/A | N/A | # facilities | 322.86 | 322.861 | 645.721 | 1005 | 1877 | 2882 | 1554.139 | 2236.279 | 481.4% | 346.3% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
81 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AG | SF Series Streetlights | SRM Total | SRM Total | Ex 4, Ch 11 | No | 12 | 11 | 2594.9448 | 2710.1338 | 5305.0786 | 280.8016 | 302.2637 | 583.0653 | -2407.8701 | -4722.0133 | -88.85% | -89.01% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period as the remaining streetlights are changed out. This program replaces regulated output (“RO”) streetlights, also referred to as constant current streetlight systems, in San Francisco.
82 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AG | SF Series Streetlights | Distribution Overhead | DOVHD-M007: Regulated Output Streetlight Replacement | Ex 4, Ch 11 | No | 12 | 11 | 2594.9448 | 2710.1338 | 5305.0786 | 280.8016 | 302.2637 | 583.0653 | -2407.8701 | -4722.0133 | -88.85% | -89.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
83 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AH | LED Streetlights | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 7379.7059 | 7707.2894 | 15086.9952 | 608.8757 | 1706.5052 | 2315.3809 | -6000.7842 | -12771.6143 | -77.86% | -84.65% | NO | NO | # of Streetlights | 8000 | 8000 | 16000 | 392 | 1130 | 1522 | -6870 | -14478 | -85.88% | -90.49% | YES | Below variance threshold. | Actual units were lower than imputed units because wildfire risk mitigation work in HFTD was prioritized and the work in this MAT code shifted to higher unit cost items (decorative pole replacements) due to the lower cost items (Cobrahead replacement) being completed. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace PG&E's LS-1 streetlights with Light Emitting Diode (LED) fixtures and new photocells. The vast majority of fixtures remaining to be converted are decorative (LS-1D).
84 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AH | LED Streetlights | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 7379.7059 | 7707.2894 | 15086.9952 | 608.8757 | 1706.5052 | 2315.3809 | -6000.7842 | -12771.6143 | -77.86% | -84.65% | N/A | N/A | # of Streetlights | 8000 | 8000 | 16000 | 392 | 1130 | 1522 | -6870 | -14478 | -85.88% | -90.49% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
85 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AI | SF Historical Streetlights | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1037.9781 | 1084.0537 | 2122.0319 | 8.006 | -1.1603 | 6.8457 | -1085.214 | -2115.1862 | -100.1% | -99.68% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Rescheduled | The high priority poles identified during the comprehensive inspection program as needing refurbishment or replacement were addressed between 2019-2022, earlier than expected. Currently, the program is expected to continue to refurbish or replace poles as identified by inspection results in a future round of comprehensive inspections.
86 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AI | SF Historical Streetlights | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 1037.9781 | 1084.0537 | 2122.0319 | 8.006 | -1.1603 | 6.8457 | -1085.214 | -2115.1862 | -100.1% | -99.68% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
87 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AJ | CWSP Non-Exempt Fuse Replacement | SRM Total | SRM Total | Ex 4, Ch 11 Ex 4, Ch 4.3 | No | On-going | Annual | 0 | 0 | 0 | 18271.0254 | 0 | 18271.0254 | 0 | 18271.0254 | 0% | 100% | NO | NO | # replacements | 0 | 0 | 0 | 3114 | 0 | 3114 | 0 | 3114 | 0% | 100% | NO | Below variance threshold. | Below variance threshold | On-Target | On-Target | Over | Proceeding as Planned | This program was reflected in MAT 2AP imputed adopted costs for the 2023 GRC cycle, but recorded to MAT 2AJ in 2023 and 3UT in 2024. The non-exempt fuse replacement program data can be found under the new MAT 3UT.
88 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AJ | CWSP Non-Exempt Fuse Replacement | Distribution Overhead | DOVHD-M004: Expulsion Fuse Replacement | Ex 4, Ch 11 Ex 4, Ch 4.3 | No | N/A | N/A | 0 | 0 | 0 | 18271.0254 | 0 | 18271.0254 | 0 | 18271.0254 | 0% | 100% | N/A | N/A | # replacements | 0 | 0 | 0 | 3114 | 0 | 3114 | 0 | 3114 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
89 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AJ | CWSP Non-Exempt Fuse Replacement | Wildfire | WLDFR-M004: Expulsion Fuse Replacement | Ex 4, Ch 11 Ex 4, Ch 4.3 | No | N/A | N/A | 0 | 0 | 0 | 18271.0254 | 0 | 18271.0254 | 0 | 18271.0254 | 0% | 100% | N/A | N/A | # replacements | 0 | 0 | 0 | 3114 | 0 | 3114 | 0 | 3114 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
90 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AP | OH CAP Projects | SRM Total | SRM Total | Ex 4, Ch 11 Ex 4, Ch 4.3 | No | On-going | Annual | 17835.374 | 18627.0823 | 36462.4563 | 1808.121 | 1967.2188 | 3775.3398 | -16659.8635 | -32687.1165 | -89.44% | -89.65% | NO | YES | # of Locations | 1186.03 | 1186.03 | 2372.06 | 0 | 0 | 0 | -1186.03 | -2372.06 | -100% | -100% | YES | Program expenditures were below imputed adopted costs because the imputed adopted costs for MAT 2AP in 2024 ($18,627) included imputed adopted costs for replacing non-exempt fuses ($17, 495). The actual costs for replacing non-exempt fuses were recorded under MAT 2AJ in 2023 and MAT 3UT in 2024. If the 2024 actual costs for replacing non-exempt fuses recorded in MAT 3UT ($16,932) were recorded to MAT 2AP in 2024, MAT 2AP actual costs would be in line with the imputed adopted costs for 2024. | Actual units were lower than imputed units because recorded costs and units for this program are now tracked in MAT 3UT for the Wildfire and Distribution Overhead mitigations. The remaining non-RAMP portion of this program is not unitized because it is project based work that varies in volume, scope, and costs. | Under | On-Target | Under | Proceeding as Planned | For the reminder of the 2023 GRC cycle, PG&E will continue to record only project based work in MAT 2AP. MAT 2AP will no longer be unitized as project based work varies in volume, scope and costs and has no meaningful units of measure. Costs and units for the wildfire and distribution overhead mitigations were recorded in MAT 2AJ in 2023 and finally in 3UT starting in 2024. PG&E plans to record costs and units for the mitigation in MAT 3UT for the remainder of the GRC cycle.
91 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AP | OH CAP Projects | Distribution Overhead | DOVHD-M004: Expulsion Fuse Replacement | Ex 4, Ch 11 Ex 4, Ch 4.3 | Yes | N/A | N/A | 16635.8756 | 17374.3384 | 34010.2141 | 1808.121 | 1967.2188 | 3775.3398 | -15407.1 | -30234.9 | -88.7% | -88.9% | N/A | N/A | # of Locations | 1186.03 | 1186.03 | 2372.06 | 0 | 0 | 0 | -1186.03 | -2372.06 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
92 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AP | OH CAP Projects | Wildfire | WLDFR-M004: Expulsion Fuse Replacement | Ex 4, Ch 11 Ex 4, Ch 4.3 | Yes | N/A | N/A | 16635.8756 | 17374.3384 | 34010.2141 | 1808.121 | 1967.2188 | 3775.3398 | -15407.1 | -30234.9 | -88.7% | -88.9% | N/A | N/A | # of Locations | 1186.03 | 1186.03 | 2372.06 | 0 | 0 | 0 | -1186.03 | -2372.06 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
93 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AP | OH CAP Projects | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 11 Ex 4, Ch 4.3 | Yes | N/A | N/A | 1199.4984 | 1252.7439 | 2452.2423 | 0 | 0 | 0 | 0 | 0 | -100% | -100% | N/A | N/A | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
94 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AQ | Ceramic Post Insulators | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 6071.0807 | 6340.5746 | 12411.6553 | -8.7619 | 0 | -8.7619 | -6340.5746 | -12420.4172 | -100% | -100.1% | NO | NO | # of Ceramic Post Insulators Replaced | 2092.57 | 2092.5679 | 4185.1379 | 0 | 0 | 0 | -2092.5679 | -4185.1379 | -100% | -100% | YES | Below variance threshold. | Actual units were lower than imputed units due to the bundling of ceramic post insulator replacements with cross-arm replacements recorded in MAT Code 2AA. The majority of locations with old ceramic post insulators also have deteriorated cross-arms that are replaced under one maintenance tag. As a result, the recording of individual ceramic post insulators is no longer captured. | Under | Under | Under | Canceled | This program's work is the replacement of ceramic post insulators that were manufactured in or prior to 1972 and are currently installed on PG&E poles and cross-arms. These ceramic post insulators are addressed proactively during pole and crossarm replacements and a dedicated program is no longer needed to support the insulator replacements. This replacement work is bundled with pole and cross-arm replacements, and will continue through the 2023 GRC cycle.
95 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AQ | Ceramic Post Insulators | Distribution Overhead | DOVHD-M008: Ceramic Post Insulator Replacement | Ex 4, Ch 11 | No | N/A | N/A | 6071.0807 | 6340.5746 | 12411.6553 | -8.7619 | 0 | -8.7619 | -6340.5746 | -12420.4172 | -100% | -100.1% | N/A | N/A | # of Ceramic Post Insulators Replaced | 2092.57 | 2092.5679 | 4185.1379 | 0 | 0 | 0 | -2092.5679 | -4185.1379 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
96 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AR | Surge Arrester Replacement | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 18522.9745 | 19345.2052 | 37868.1796 | 5194.563 | 7643.3056 | 12837.8686 | -11701.8996 | -25030.311 | -60.49% | -66.1% | NO | YES | # replacements | 3952.06 | 3952.0624 | 7904.1224 | 663 | 756 | 1419 | -3196.0624 | -6485.1224 | -80.87% | -82.05% | YES | Program expenditures were below imputed regulatory values in 2024 because PG&E met its 2023-2025 WMP target for surge arrestor removals in 2023. Actual costs in 2024 reflect completed remediation work on newly identified surge arrestors in 2024. | Actual units were lower than imputed units because PG&E met its WMP target for surge arrestor removal in 2023 and in 2024 work was limited to remediation work on newly identified surge arrestors. | Under | On-Target | Under | Proceeding as Planned | PG&E met its 2023‑2025 WMP target for surge arrestor removals in 2023 and completed remediation work on identified surge arrestors in 2024. However, some costs are forecasted in 2025 and 2026 for the mapping of constructed jobs from prior years, addressing QA findings, and closure of orders.
97 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AR (k) | Surge Arrester Replacement | Distribution Overhead | DOVHD-M003: Non-Exempt Surge Arrester Replacement | Ex 4, Ch 11 | No | N/A | N/A | 18522.9745 | 19345.2052 | 37868.1796 | 5194.563 | 7643.3056 | 12837.8686 | -11701.8996 | -25030.311 | -60.49% | 33.9% | N/A | N/A | # replacements | 3952.06 | 3952.0624 | 7904.1224 | 663 | 756 | 1419 | -3196.0624 | -6485.1224 | -80.87% | -82.05% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
98 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AR (k) | Surge Arrester Replacement | Wildfire | WLDFR-M003: Non-Exempt Surge Arrester Replacement | Ex 4, Ch 11 | No | N/A | N/A | 18522.9745 | 19345.2052 | 37868.1796 | 5194.563 | 7643.3056 | 12837.8686 | -11701.8996 | -25030.311 | -60.49% | -66.1% | N/A | N/A | # replacements | 3952.06 | 3952.0624 | 7904.1224 | 663 | 756 | 1419 | -3196.0624 | -6485.1224 | -80.87% | -82.05% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
99 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AS | FAS Overhead Capital | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 865.3244 | 903.736 | 1769.0604 | 330.9953 | 301.1842 | 632.1795 | -602.5517 | -1136.8809 | -66.67% | -64.26% | NO | NO | # of Notifications Completed | 2624.75 | 2624.7529 | 5249.5029 | 0 | 0 | 0 | -2624.7529 | -5249.5029 | -100% | -100% | YES | Below variance threshold. | Actual units were lower than imputed units because this program is no longer recording actual units as the work is identified during a field job and completed by a single PG&E Troubleshooter. The work could involve either replacing or installing overhead facilities such as: electric distribution conductors, components, structures, and associated equipment constructed above ground level. As such there is no meaningful single unit of measure. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The program either replaces or installs overhead facilities identified during a field job and completed by a single PG&E Troubleshooter. The work could involve either replacing or installing overhead facilities such as: electric distribution conductors, components, structures, and associated equipment constructed above ground level.
100 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AS | FAS Overhead Capital | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 865.3244 | 903.736 | 1769.0604 | 330.9953 | 301.1842 | 632.1795 | -602.5517 | -1136.8809 | -66.67% | -64.26% | N/A | N/A | # of Notifications Completed | 2624.75 | 2624.7529 | 5249.5029 | 0 | 0 | 0 | -2624.7529 | -5249.5029 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
101 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2A# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 0 | 0 | 0 | -90.1955 | 2192.1838 | 2101.9883 | 2192.1838 | 2101.9883 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | MAT 2A# covers Standard Cost Variance (SCV) for the Electric Distribution Preventative Maintenance OH program. SCV is the difference between actual costs incurred and the amount charged out by employees at a pre-determined rate. PG&E does not forecast Standard Cost Variance.
102 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BA | UG Genl Repl | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 49864.3218 | 52077.7879 | 101942.1097 | 73659.2773 | 97293.0995 | 170952.3769 | 45215.3116 | 69010.2671 | 86.82% | 67.7% | YES | YES | # of Notifications Completed | 1816.54 | 1816.5422 | 3633.0822 | 2235 | N/A | 2235 | -1816.5422 | -1398.0822 | -100% | -38.48% | YES | Program expenditures exceeded imputed regulatory values due to higher than forecasted unit costs and the completion of a higher volume of units than forecasted, in addition to an increased spend in contract labor and material costs. | Actual units were lower than imputed units because more work was identified than forecasted. | Under | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to provide underground preventative maintenance for deteriorated facilities that are not an imminent hazard, and have not caused an outage. Facilities include transformers, conduit, enclosures, pads, and idle equipment.
103 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BA | UG Genl Repl | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 11 | No | N/A | N/A | 49864.3218 | 52077.7879 | 101942.1097 | 73659.2773 | 97293.0995 | 170952.3769 | 45215.3116 | 69010.2671 | 86.82% | 67.7% | N/A | N/A | # of Notifications Completed | 1816.54 | 1816.5422 | 3633.0822 | 2235 | 2861 | 5096 | 1044.4578 | 1462.9178 | 57.5% | 40.27% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
104 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BB | Fault Indicator Replacements | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 899.6593 | 939.5949 | 1839.2542 | 566.4909 | 484.6311 | 1051.1219 | -454.9639 | -788.1322 | -48.42% | -42.85% | NO | NO | # of Notifications Completed | 3238.2 | 3238.1975 | 6476.3975 | 2241 | N/A | 2241 | -3238.1975 | -4235.3975 | -100% | -65.4% | YES | Below variance threshold. | Actual units were lower than imputed units because fewer than expected Fault Indicators were identified as needing replacement during inspections. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is for the replacement of deteriorated fault indicators that are not an imminent hazard, and have not caused an outage. Spending in this program is based on inspection find rates.
105 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BB | Fault Indicator Replacements | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 11 | No | N/A | N/A | 899.6593 | 939.5949 | 1839.2542 | 566.4909 | 484.6311 | 1051.1219 | -454.9639 | -788.1322 | -48.42% | -42.85% | N/A | N/A | # of Notifications Completed | 3238.2 | 3238.1975 | 6476.3975 | 2241 | 1685 | 3926 | -1553.1975 | -2550.3975 | -47.96% | -39.38% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
106 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BD | UG COE Repl | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 7223.8884 | 7544.5552 | 14768.4435 | 9026.6331 | 9089.6097 | 18116.2427 | 1545.0545 | 3347.7992 | 20.48% | 22.67% | NO | NO | # of Tags Completed | 144 | 144 | 288 | 88 | 100 | 188 | -44 | -100 | -30.56% | -34.72% | YES | Below variance threshold. | Actual units were lower than imputed units because unit costs were above forecasted. In order to manage overall costs in the 2BD program, PG&E did fewer program units. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is the replacement of Underground Critical Operating Equipment (COE), which is equipment determined to be necessary for operations. COE is identified for replacement by the division operators, M&C, & restoration, and validated by Distribution Engineers based on damage and criticality to operations. For the GRC cycle, PG&E expects that it will continue to prioritize other work in MWC 2B over work in MAT 2BD. Going forward, PG&E may spend the imputed amount but anticipates completing fewer units than imputed due to the increase in unit costs.
107 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BD | UG COE Repl | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 11 | No | N/A | N/A | 7223.8884 | 7544.5552 | 14768.4435 | 9026.6331 | 9089.6097 | 18116.2427 | 1545.0545 | 3347.7992 | 20.48% | 22.67% | N/A | N/A | # of Tags Completed | 144 | 144 | 288 | 88 | 100 | 188 | -44 | -100 | -30.56% | -34.72% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
108 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BF | UG Idle Facility Remove | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 29.6349 | 30.9504 | 60.5853 | 317.2541 | 194.0678 | 511.3219 | 163.1174 | 450.7365 | 527% | 744% | NO | NO | # locations | 2 | 2 | 4 | 14 | N/A | 14 | -2 | 10 | -100% | 250% | YES | Below variance threshold. | Actual units were lower than imputed units because more idle facilities were identified for removal than forecasted. | Over | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is the removal of underground idle facilities deemed necessary for removal.
109 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BF | UG Idle Facility Remove | Underground | DUNGD-C005: UG Idle Facility Removal | Ex 4, Ch 11 | No | N/A | N/A | 29.6349 | 30.9504 | 60.5853 | 317.2541 | 194.0678 | 511.3219 | 163.1174 | 450.7365 | 527% | 744% | N/A | N/A | # locations | 2 | 2 | 4 | 14 | 6 | 20 | 4 | 16 | 200% | 400% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
110 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BP | UG CAP Projects | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 8456.6769 | 8832.0669 | 17288.7439 | 2988.0757 | 196.5628 | 3184.6385 | -8635.5041 | -14104.1054 | -97.77% | -81.58% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and performs major project (underground) work that meets the financial threshold between $25,000 and $100,000. Completion of work is dependent on the scope of the project.
111 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BP | UG CAP Projects | Underground | DUNGD-C004: Planned Major Projects | Ex 4, Ch 11 | No | N/A | N/A | 8456.6769 | 8832.0669 | 17288.7439 | 2988.0757 | 196.5628 | 3184.6385 | -8635.5041 | -14104.1054 | -97.77% | -81.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
112 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2B# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 0 | 0 | 0 | 31.6759 | 890.1578 | 921.8337 | 890.1578 | 921.8337 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | MAT 2B# covers Standard Cost Variance (SCV) for the Electric Distribution Preventative Maintenance UG program. SCV is the difference between actual costs incurred and the amount charged out by employees at a pre-determined rate. PG&E does not forecast Standard Cost Variance.
113 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CA | Network Misc | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 338.948 | 353.9938 | 692.9418 | 6.9008 | 3.4623 | 10.3631 | -350.5315 | -682.5787 | -99.02% | -98.5% | NO | NO | # relays replaced | 25 | 25 | 50 | 3 | N/A | 3 | -25 | -47 | -100% | -94% | YES | Below variance threshold. | Actual units were lower than imputed units due to priority relay replacements related to weather-related events which depleted inventory that could be used for MAT 2CA. In addition many of the failures of relays required the replacement of entire network protector units, which is recorded to MAT 2CC, resulting in fewer 2CA units. Relay installations and replacements are performed for both reliability (2CA), and in connection with emergency or weather-related events in other MWC like 17. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace network protector relays to maintain a safe and reliable distribution network system. Relay installations and replacements are performed for both reliability in MAT 2CA, and in connection with emergency or weather-related events in other programs, both of which are dependent of PG&E's available inventory. This is a defect demand-driven program.
114 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CA | Network Misc | Distribution Network | DNTWK-C003: Network Component Replacements - Condition Based | Ex 4, Ch 14 | No | N/A | N/A | 338.948 | 353.9938 | 692.9418 | 6.9008 | 3.4623 | 10.3631 | -350.5315 | -682.5787 | -99.02% | -98.5% | N/A | N/A | # relays replaced | 25 | 25 | 50 | 3 | 7 | 10 | -18 | -40 | -72% | -80% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
115 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CB | Fiber/SCADA Communication Repl | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 14 | No | On-going | Annual | 0 | 0 | 0 | 2.6261 | 1.4042 | 4.0303 | 1.4042 | 4.0303 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | The SCADA communication replacements work has shifted from being recorded under this MAT code to Install/Replace Network MAT 2CE.
116 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CC | Transformer & Protector Repl | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 4057.4911 | 4237.6022 | 8295.0933 | 6051.3747 | 6809.8419 | 12861.2166 | 2572.2397 | 4566.1233 | 60.7% | 55.05% | NO | NO | # transformers/network protector replaced | 25 | 25 | 50 | 46 | 39 | 85 | 14 | 35 | 56% | 70% | YES | Below variance threshold. | Actual units were higher than imputed units due to an unexpected high volume of condition-based replacements due to adverse weather events and, as explained in MAT 2CA above, the failure of many relays requiring replacement of entire network protector units. | Over | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to replace network transformers and protectors to maintain a safe and reliable distribution network system.
117 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CC | Transformer & Protector Repl | Distribution Network | DNTWK-C003: Network Component Replacements - Condition Based | Ex 4, Ch 14 | Yes | N/A | N/A | 1029.0203 | 1074.725 | 2103.7453 | 3206.279 | 6809.8419 | 10016.1209 | 5735.1169 | 7912.3756 | 533.6% | 376.1% | N/A | N/A | # transformers/network protector replaced | 2 | 2 | 4 | 27 | 39 | 66 | 37 | 62 | 1850% | 1550% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
118 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CC | Transformer & Protector Repl | Distribution Network | DNTWK-M005: Network Component Replacements - High-Rise Dry-Type Transformers | Ex 4, Ch 14 | Yes | N/A | N/A | 2799.75 | 2924 | 5723.75 | 2092.554 | 6809.8419 | 8902.3959 | 3885.8419 | 3178.6459 | 132.9% | 55.53% | N/A | N/A | # transformers/network protector replaced | 8 | 8 | 16 | 4 | 0 | 4 | -8 | -12 | -100% | -75% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
119 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CC | Transformer & Protector Repl | Distribution Network | DNTWK-M006: Network Component Replacements - Targeted Network Protector Replacements | Ex 4, Ch 14 | Yes | N/A | N/A | 228.6761 | 238.827 | 467.5031 | 752.542 | 0 | 752.542 | -238.827 | 285.0389 | -100% | 60.97% | N/A | N/A | # transformers/network protector replaced | 15 | 15 | 30 | 15 | 0 | 15 | -15 | -15 | -100% | -50% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
120 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CD | Venting Manhole Covers Repl | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 0 | 0 | 0 | 88.2583 | 9.3661 | 97.6244 | 9.3661 | 97.6244 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program was completed for the network areas. Venting-manhole cover replacements will continue for non-Network locations under the 2BP program. The work is not canceled but PG&E is recording the work in those other MAT codes.
121 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CD | Venting Manhole Covers Repl | Distribution Network | DNTWK-M002: Venting Manhole Cover Replacements | Ex 4, Ch 14 | No | N/A | N/A | 0 | 0 | 0 | 88.2583 | 9.3661 | 97.6244 | 9.3661 | 97.6244 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
122 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CE | SCADA Communications Upgrade | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 9738.8839 | 10171.1908 | 19910.0748 | 9937.5503 | 9461.1168 | 19398.6672 | -710.074 | -511.4076 | -6.981% | -2.569% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program has no end date. The purpose of this program is a continuing effort to upgrade the Distribution Network SCADA system to maintain a safe and reliable distribution network system. Starting in 2021, PG&E began recording SCADA communication replacements under 2CB under the 2CE program.
123 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CE | SCADA Communications Upgrade | Distribution Network | DNTWK-M003: Installation of SCADA Equipment for Safety Monitoring | Ex 4, Ch 14 | No | N/A | N/A | 9738.8839 | 10171.1908 | 19910.0748 | 9937.5503 | 9461.1168 | 19398.6672 | -710.074 | -511.4076 | -6.981% | -2.569% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
124 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2C# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 14 | No | On-going | Annual | 0 | 0 | 0 | -22.5286 | -109.4638 | -131.9924 | -109.4638 | -131.9924 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Under | Proceeding as Planned | MAT 2C# covers Standard Cost Variance for the Electric Distribution Preventative Maintenance Network program. SCV is the difference between actual costs incurred and the amount charged out by employees at a predetermined rate. PG&E does not forecast Standard Cost Variance.
125 | Capital | Electric Distribution | 2F | Build IT Apps & Infra | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 4.5 Ex 4, Ch 20-21 | No | On-going | Annual | 70173.5 | 72989.7811 | 143163.2811 | 105258.7746 | 139198.3082 | 244457.0827 | 66208.527 | 101293.8016 | 90.71% | 70.75% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values for Wildfire Mitigations due to the capitalization of a five year pre-paid agreement for a software as a service (SaaS) application (Foundry) that provides the capability of harnessing highly available data to analyze, build, visualize and deploy technology solutions that support Wildfire Mitigations. Electric Distribution technology program expenditures were above imputed regulatory values due to unplanned general IT expenditures on Field Area Network assets that experienced performance issues. The asset replacements have been prioritized to address the areas of greatest risk first. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is 1) provide technology solution support for the development and implementation of the Integrated Grid Platform; and 2) provide technology solutions that support wildfire mitigations. The program specifically provides hardware and software network and telecommunications solutions as well as enhancements to software planning tools in support of wildfire mitigation.
126 | Capital | Electric Distribution | 2F | Build IT Apps & Infra | N/A | Not assigned | Distribution Overhead | DOVHD-M005: Additional Asset Data Capture | Ex 4, Ch 4.5 Ex 4, Ch 20-21 | Yes | N/A | N/A | 0 | 0 | 0 | 677.8 | 0 | 677.8 | 0 | 677.8 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
127 | Capital | Electric Distribution | 2F | Build IT Apps & Infra | N/A | Not assigned | IT Asset Failure | ITAFL-M005: Multi-Faceted Mitigations | Ex 4, Ch 4.5 Ex 4, Ch 20-21 | Yes | N/A | N/A | 0 | 0 | 0 | 34788.0418 | 23275.123 | 58063.1648 | 23275.123 | 58063.1648 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
128 | Capital | Electric Distribution | 2F | Build IT Apps & Infra | N/A | Not assigned | Emergency Preparedness & Response | EPNDR-C002: Situational Awareness and Forecasting Initiatives - WSOC | Ex 4, Ch 4.5 Ex 4, Ch 20-21 | Yes | N/A | N/A | 0 | 0 | 0 | 2408 | 0 | 2408 | 0 | 2408 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
129 | Capital | Electric Distribution | 2F | Build IT Apps & Infra | N/A | Not assigned | Wildfire | WLDFR-M0IT: Wildfire IT Work | Ex 4, Ch 4.5 Ex 4, Ch 20-21 | Yes | N/A | N/A | 27890.2385 | 29009.5624 | 56899.8009 | 45036.3254 | 76595.7747 | 121632.1001 | 47586.2124 | 64732.2993 | 164% | 113.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
130 | Capital | Electric Distribution | 2F | Build IT Apps & Infra | N/A | Not assigned | Wildfire | POST-GRC: Post-GRC Mitigation | Ex 4, Ch 4.5 Ex 4, Ch 20-21 | Yes | N/A | N/A | 0 | 0 | 0 | 4257.9144 | 0 | 4257.9144 | 0 | 4257.9144 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
131 | Capital | Electric Distribution | 2F | Build IT Apps & Infra | N/A | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.5 Ex 4, Ch 20-21 | Yes | N/A | N/A | 42283.2615 | 43980.2188 | 86263.4802 | 18090.6758 | 39327.4104 | 57418.0863 | -4652.8083 | -28845.394 | -10.58% | -33.44% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
132 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49M/3UA (a) | ED WFM PIH Microgrids | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | 5 | 7 | 0 | 0 | 0 | 262.3767 | 652.3173 | 914.694 | 652.3173 | 914.694 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program is for the instillation of temporary distribution microgrids to reduce the number of customers impacted by PSPS events. This program began in 2018 and was forecasted to be completed in 2022. PG&E now anticipates that this program will be completed in 2025.
133 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49M/3UA | ED WFM PIH Microgrids | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 4.3 | No | N/A | N/A | 0 | 0 | 0 | 262.3767 | 652.3173 | 914.694 | 652.3173 | 914.694 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A
134 | Capital | Electric Distribution | 3U | Inst/Rpl WildFire Mitgt Eqpmnt | 3UC (b) | ED WFM Dist Line MSO Device | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | 4 | 6 | 0 | 0 | 0 | 0 | 2352.5784 | 2352.5784 | 2352.5784 | 2352.5784 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | Over | Over | Over | Emergent | This program is to address ignition risk created by some Motorized Switch Operators (MSO) that were initially installed by PG&E in 2019 as sectionalizing devices. Despite the switches being understood to meet CalFire's exempt criteria for not posing an ignition risk during normal operations, PG&E crews noted that some MSO switches exhibited an arc flash during the opening operation requiring replacement. In the 2023 GRC, PG&E had planned to replace or retrofit all MSO switches by 2022. However, the program required expansion to mitigate wildfire risk, and PG&E continued to replace MSO switches in 2024.
135 | Capital | Electric Distribution | 3U | Inst/Rpl WildFire Mitgt Eqpmnt | 3UC | ED WFM Dist Line MSO Device | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 4.3 | No | N/A | N/A | 0 | 0 | 0 | 0 | 2352.5784 | 2352.5784 | 2352.5784 | 2352.5784 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A
136 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49I/3UD (c) | ED WFM Dist Fault Anticipation | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | On-going | Annual | 9468.4874 | 9888.7914 | 19426.0244 | 180.3752 | 2394.9425 | 2575.3177 | -7493.849 | -16850.7067 | -75.78% | -86.74% | NO | NO | # of sensor locations | 116 | 116 | 232 | 5 | 17 | 22 | -99 | -210 | -85.34% | -90.52% | YES | Below variance threshold. | Actual units were lower than imputed units because PG&E is aligning the work to meet the current WMP commitment for this program. PG&E installed 17 DFA sensors in 2024 exceeding the WMP Commit, rather than the 116 units imputed in the GRC (See PG&E's 2023-2025 WMP Revision 8, Initiative Activity Tracking ID SA-10, Section 8.3.3.1) | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to install distribution grid sensors in substations which individually and in combination with other sensors, provide real-time monitoring capability of the grid. During the 2023 GRC cycle PG&E anticipates that it will continue to be below GRC imputed amounts but will meet its WMP commitments.
137 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49I/3UD | ED WFM Dist Fault Anticipation | Wildfire | WLDFR-M012: Situational Awareness and Forecasting Initiatives - DFA | Ex 4, Ch 4.3 | No | N/A | N/A | 9468.4874 | 9888.7914 | 19426.0244 | 180.3752 | 2394.9425 | 2575.3177 | -7493.849 | -16850.7067 | -75.78% | -86.74% | N/A | N/A | # of sensor locations | 116 | 116 | 232 | 5 | 17 | 22 | -99 | -210 | -85.34% | -90.52% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
138 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49I/3UE (d) | ED WFM Dist Fault Anticipation | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | On-going | Annual | 5739.5277 | 5994.3041 | 11733.8318 | 890.9217 | 2802.7873 | 3693.709 | -3191.5168 | -8040.1228 | -53.24% | -68.52% | NO | NO | # of sensor locations | 250 | 250 | 500 | 55 | 97 | 152 | -153 | -348 | -61.2% | -69.6% | YES | Below variance threshold. | Actual units were lower than imputed units because PG&E is aligning the work to meet the current WMP commitment for this program. The current commitment is 2 circuits for 2024. PG&E met that commitment which only resulted in the need for 97 units rather than the 250 units imputed in the GRC. (See PG&E's 2023-2025 WMP Revision 8, Initiative Activity Tracking ID SA-11, Section 8.3.3.1). | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to install distribution grid sensors that use radio frequency signals to locate the source of a disturbance along a conductor. During the 2023 GRC cycle PG&E anticipates that it will continue to be below GRC imputed amounts but will meet its WMP commitments.
139 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49I/3UE (d) | ED WFM Dist Fault Anticipation | Wildfire | WLDFR-M011: Situational Awareness and Forecasting Initiatives - EFD | Ex 4, Ch 4.3 | No | N/A | N/A | 5739.5277 | 5994.3041 | 11733.8318 | 890.9217 | 2802.7873 | 3693.709 | -3191.5168 | -8040.1228 | -53.24% | -68.52% | N/A | N/A | # of sensor locations | 250 | 250 | 500 | 55 | 97 | 152 | -153 | -348 | -61.2% | -69.6% | N/A |  |  | N/A | N/A | N/A | N/A | N/A
140 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49T/3UF (e) | ED FuseSaver | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | On-going | Annual | 3105.025 | 3242.8563 | 6347.8813 | 7061.8317 | 4033.1964 | 11095.028 | 790.3401 | 4747.1468 | 24.37% | 74.78% | NO | NO | # of FuseSavers installed | 79.72 | 80 | 159.72 | 49 | 35 | 84 | -45 | -75.72 | -56.25% | -47.41% | YES | Below variance threshold. | Actual units were lower than imputed units because unit costs went up and priority was given to EPSS capital programs in WLDFR-M020. | Under | Under | On-Target | Rescheduled | The purpose of this program is to install Fuse Savers. PG&E anticipated that it will reallocate funding to other priorities like EPSS capital programs, for the remainder of the GRC cycle. The budget is listed as on-target because it is likely that overspend in 2023-2024 will balance out with underspend in 2025-2026 due to fewer, if any installations, because of reprioritization of other wildfire capital programs, like EPSS.
141 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49T/3UF | ED FuseSaver | Wildfire | WLDFR-M10B: Additional System Automation and Protection - FuseSaver | Ex 4, Ch 4.3 | No | N/A | N/A | 3105.025 | 3242.8563 | 6347.8813 | 7061.8317 | 4033.1964 | 11095.028 | 790.3401 | 4747.1468 | 24.37% | 74.78% | N/A | N/A | # of FuseSavers installed | 79.72 | 80 | 159.72 | 49 | 35 | 84 | -45 | -75.72 | -56.25% | -47.41% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
142 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49I/3UL (f) | ED WFM Dist Fault Anticipation | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | On-going | Annual | 8717.0196 | 9103.9662 | 17820.9858 | 3037.2378 | 1682.5363 | 4719.7742 | -7421.4298 | -13101.2116 | -81.52% | -73.52% | NO | NO | # of sensor locations | 900 | 900 | 1800 | 247 | 194 | 441 | -706 | -1359 | -78.44% | -75.5% | YES | Below variance threshold. | Actual units were lower than imputed units because PG&E planned the work to meet the WMP commitment for this program which was 40 circuits for 2024. PG&E did 45 circuits which only resulted in the need for 194 units rather than the 900 units imputed in the GRC (see PG&E's 2023-2025 WMP Revision 8, Initiative Activity Tracking ID SA-02, Section 8.3.3.1). | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to install distribution grid sensors which individually and in combination with other sensors, provide real-time monitoring capability of the grid. During the 2023 GRC cycle PG&E anticipates that it will continue to be below GRC imputed amounts but will meet its WMP commitments.
143 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49I/3UL | ED WFM Dist Fault Anticipation | Wildfire | WLDFR-M07A: Situational Awareness and Forecasting Initiatives - Line Sensors | Ex 4, Ch 4.3 | No | N/A | N/A | 8717.0196 | 9103.9662 | 17820.9858 | 3037.2378 | 1682.5363 | 4719.7742 | -7421.4298 | -13101.2116 | -81.52% | -73.52% | N/A | N/A | # of sensor locations | 900 | 900 | 1800 | 741 | 194 | 935 | -706 | -865 | -78.44% | -48.06% | N/A |  |  | N/A | N/A | N/A | N/A | N/A
144 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49H/3UP (g) | ED WFM Dist Protective Device | SRM Total | SRM Total | Ex. 4, Ch 4.3 | No | On-going | Annual | 12602.4165 | 13161.835 | 25764.2515 | 13992.6051 | 4040.0563 | 18032.6615 | -9121.7786 | -7731.5901 | -69.3% | -30.01% | NO | NO | # of installations or replacements of sectionalizing devices | 100 | 100 | 200 | 82 | 38 | 120 | -62 | -80 | -62% | -40% | YES | Below variance threshold. | Actual units were lower than imputed units because most of the highest impact locations have already been sectionalized with automated equipment, so there is a reduced benefit (in terms of number of customers likely to benefit from such devices during PSPS events) when compared to work performed in previous years. Therefore PG&E will focus on reducing reliability impacts with additional protective devices as part of the WMP GH-07 initiative (Distribution Sectionalizing Devices). See PG&E's 2023-2025 WMP Revision 8, Section 8.1.2.11.2. | Under | Under | Under | Rescheduled | This program is ongoing and will continue in PG&E 2023 GRC time period though at a slower pace than forecasted driven by current WMP commitments. The purpose of this program is to install automated electrical equipment designed to isolate faulted lines, limit line reclosing and facilitate the remote opening and closing of switches necessary to efficiently implement PSPS. PG&E anticipated that it will continue to reallocate funding to other priority wildfire mitigation work for the remainder of the GRC cycle.
145 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49H/3UP | ED WFM Dist Protective Device | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex. 4, Ch 4.3 | No | N/A | N/A | 12602.4165 | 13161.835 | 25764.2515 | 13992.6051 | 4040.0563 | 18032.6615 | -9121.7786 | -7731.5901 | -69.3% | -30.01% | N/A | N/A | # of installations or replacements of sectionalizing devices | 100 | 100 | 200 | 82 | 38 | 120 | -62 | -80 | -62% | -40% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
146 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49R/3UR ( e) | ED WFM REFCL | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | On-going | Annual | 18304.0778 | 19116.592 | 37420.6698 | 71.5858 | 4.4605 | 76.0463 | -19112.1315 | -37344.6234 | -99.98% | -99.8% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures were below imputed regulatory values because of delays in the Rapid Earth Fault Current Limiter (REFCL) demonstration project due to technology and system integration challenges. | N/A | Under | Under | Under | Rescheduled | The purpose of this program is the evaluation of the effectiveness of the REFCL technology to mitigate the need for PSPS. PG&E may continue to evaluate REFCL if challenges with the technology are resolved, but is not pursuing it as a widespread solution for wildfire mitigation at this time. Funding has been reallocated to other priority Wildfire programs like EPSS capital.
147 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49R/3UR | ED WFM REFCL | Wildfire | WLDFR-M10C: Additional System Automation and Protection - REFCL | Ex 4, Ch 4.3 | Yes | N/A | N/A | 17901.0778 | 19116.592 | 37017.6698 | 71.5858 | 4.4605 | 76.0463 | -19112.1315 | -36941.6234 | -99.98% | -99.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
148 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49R/3UR | ED WFM REFCL | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.3 | Yes | N/A | N/A | 403 | 0 | 403 | 0 |  | 0 | 0 | -403 | 0% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
149 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49A/3US | ED WFM SCADA Non Reclose | SRM Total | SRM Total | Ch 4.3, Ch 4.6 | No | On-going | Annual | 0 | 0 | 0 | 12795.0286 | 11576.517 | 24371.5456 | 11576.517 | 24371.5456 | 100% | 100% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to the introduction of the Downed Conductor Detection (DCD) program. In 2023 PG&E began the DCD program for EPSS and recorded costs and units to MAT 49A. In 2024 PG&E began recording this work in MAT 3US. The DCD program mitigates ignitions for high impedance faults and is a wildfire mitigation. Note that PG&E did not forecast EPSS capital costs in the 2023 GRC. | N/A | Over | Over | Over | Emergent | This program's work is ongoing and will continue in PG&E's 2023 GRC period. PG&E is listing the status of this program as Emergent because we did not forecast EPSS capital or the EPSS DCD program in the 2023 GRC.
150 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49A/3US (b) | ED WFM SCADA Non Reclose | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ch 4.3, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 12744.4235 | 11576.517 | 24320.9404 | 11576.517 | 24320.9404 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
151 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49A/3US (b) | ED WFM SCADA Non Reclose | Wildfire | WLDFR-M10A: Additional System Automation and Protection | Ch 4.3, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 50.6051 | 0 | 50.6051 | 0 | 50.6051 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
152 | Capital | Electric Distribution | 3U | Inst/Rpl WildFire Mitgt Eqpmnt | 3UT (j) | ED WFM Non-Exempt Expulsion | SRM Total | SRM Total | Ex 4, Ch 11 Ex 4, Ch 4.3 | No | 7 | 6 | 0 | 0 | 0 | 0 | 16932.2832 | 16932.2832 | 16932.2832 | 16932.2832 | 100% | 100% | NO | YES | # Expulsion Fuses Replaced | 0 | 0 | 0 | 0 | 3106 | 3106 | 3106 | 3106 | 100% | 100% | YES | Program expenditures exceeded imputed regulatory values because the imputed adopted costs for replacing non-exempt fuses ($17, 495) was included in MAT 2AP total imputed adopted costs ($18,627). The actual costs for replacing non-exempt fuses were recorded under MAT 2AJ in 2023 and MAT 3UT in 2024. If the 2024 imputed adopted costs for replacing non-exempt fuses ($17,495) in MAT 2AP were compared to the recorded costs in MAT 3UT ($16,932) for 2024, the actual costs would be in line with the imputed adopted costs for 2024. | Actual units were higher than imputed units because 1) this programs was imputed in MAT 2AP and 2) PG&E ramped up the program to focus on approximately 3,000 replacements in HFTDs per year to meet our 2023-2025 WMP commitments. | Over | On-Target | Over | Proceeding as Planned | PG&E is on-target to replace the remaining known population of non exempt fuses in HFTDs and conclude the program at the end of 2025.
153 | Capital | Electric Distribution | 3U | Inst/Rpl WildFire Mitgt Eqpmnt | 3UT (j) | ED WFM Non-Exempt Expulsion | Distribution Overhead | DOVHD-M004: Expulsion Fuse Replacement | Ex 4, Ch 11 Ex 4, Ch 4.3 | No | N/A | N/A | 0 | 0 | 0 | 0 | 16932.2832 | 16932.2832 | 16932.2832 | 16932.2832 | 100% | 100% | N/A | N/A | # Expulsion Fuses Replaced | 0 | 0 | 0 | 0 | 3106 | 3106 | 3106 | 3106 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
154 | Capital | Electric Distribution | 3U | Inst/Rpl WildFire Mitgt Eqpmnt | 3UT (j) | ED WFM Non-Exempt Expulsion | Wildfire | WLDFR-M004: Expulsion Fuse Replacement | Ex 4, Ch 11 Ex 4, Ch 4.3 | No | N/A | N/A | 0 | 0 | 0 | 0 | 16932.2832 | 16932.2832 | 16932.2832 | 16932.2832 | 100% | 100% | N/A | N/A | # Expulsion Fuses Replaced | 0 | 0 | 0 | 0 | 3106 | 3106 | 3106 | 3106 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
155 | Capital | Electric Distribution | 46 | E Dist Subst Capacity | 46A | DSub Nor Capacity | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 16420.3602 | 17149.2563 | 33569.6165 | 18203.8827 | 20546.4814 | 38750.3642 | 3397.2252 | 5180.7477 | 19.81% | 15.43% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This program includes projects to support general distribution substation capacity increases.
156 | Capital | Electric Distribution | 46 | E Dist Subst Capacity | 46F | DSub Em and Op Capacity | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 1019.1721 | 1064.4129 | 2083.585 | 2547.3234 | 2930.4395 | 5477.7628 | 1866.0266 | 3394.1779 | 175.3% | 162.9% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. MAT 46F includes: (1) work to address emergency capacity deficiencies; and (2) operational capacity work to reduce the number of customers on a circuit to no more than 6,000 and circuit loading to a maximum of 600 amperes (amps).
157 | Capital | Electric Distribution | 46 | E Dist Subst Capacity | 46H | DSub New Bus Related Capacity | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 43142.8658 | 45057.968 | 88200.8337 | 46817.4292 | 76589.4811 | 123406.9103 | 31531.5131 | 35206.0765 | 69.98% | 39.92% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to additional capacity funding deployed in 2024 via SB 410 and Energization Capacity New Business Interim Memorandum Account (ECNBIMA) to provide distribution line capacity to energize customer loads. | N/A | Over | Over | Over | Expanded | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to provides substation capacity necessary to complete new customer applications for service. PG&E expects to continue to do more work in this program than forecasted due to SB410 requirements, as discussed in PG&E's 2023 GRC capacity phase filing.
158 | Capital | Electric Distribution | 46 | E Dist Subst Capacity | 46N | DSub Land Purchase_ New Sub | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 0 | 0 | 0 | -286.038 | 173.6568 | -112.3812 | 173.6568 | -112.3812 | 100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Under | Proceeding as Planned | N/A
159 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48A | Repl Dsub Other Equipment | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 4401.5604 | 4596.9447 | 8998.5051 | 769.6422 | 1974.7278 | 2744.37 | -2622.2169 | -6254.1352 | -57.04% | -69.5% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is ongoing capital infrastructure replacement work to maintain system operations and reliability. In 2023 & 2024, PG&E prioritized substation work (for example in MAT 48L, 54A, and MWC 59) over MAT 48A. For the 2023 GRC cycle, PG&E anticipates that this work will continue to be lower priority than other Substation work.
160 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48A | Repl Dsub Other Equipment | Substation | SBSTN-C16A: Proactive Asset Replacement - Ground Grid | Ex 4, Ch 15 | Yes | N/A | N/A | 4401.5604 | 4596.9447 | 8998.5051 | 769.6422 | 1974.7278 | 2744.37 | -2622.2169 | -6254.1352 | -57.04% | -69.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
161 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48A | Repl Dsub Other Equipment | Wildfire | WLDFR-C10A: Substation Proactive Asset Replacement - Ground Grid | Ex 4, Ch 15 | Yes | N/A | N/A | 4401.5604 | 4596.9447 | 8998.5051 | 759.3567 | 1974.7278 | 2734.0845 | -2622.2169 | -6264.4206 | -57.04% | -69.62% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
162 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48A | Repl Dsub Other Equipment | Wildfire | POST-GRC: Post-GRC Mitigation | Ex 4, Ch 15 | Yes | N/A | N/A | 0 | 0 | 0 | 10.2854 | 0 | 10.2854 | 0 | 10.2854 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
163 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48B | Repl DSub Regulators | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 15 | No | On-going | Annual | 0 | 0 | 0 | 2.1574 | 1.1531 | 3.3105 | 1.1531 | 3.3105 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program was not forecasted in the 2023 GRC. Replacement of distribution substation regulators is integrated under MAT 54A. The program has not been canceled but this MAT code is no longer being used for that purpose.
164 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48C | Repl DSub Batteries | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 3389.481 | 3539.9393 | 6929.4204 | 2.1074 | 40.4627 | 42.5702 | -3499.4766 | -6886.8502 | -98.86% | -99.39% | NO | NO | # of Batteries | 10 | 10 | 20 | 0 | 0 | 0 | -10 | -20 | -100% | -100% | YES | Below variance threshold. | Actual units were lower than imputed units because of the decision to reschedule proactive battery replacements to support higher priority substation work. Rescheduling of these proactive replacements does not compromise safety or reliability. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is capital infrastructure replacement work to maintain system operations and reliability. In 2023, PG&E prioritized substation work (for example in MAT 48L, 54A, and MWC 59) over MAT 48C. At this time, PG&E anticipates that this program will continue to be prioritized below other substation work.
165 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48C | Repl DSub Batteries | Substation | SBSTN-C16C: Proactive Asset Replacement - Batteries | Ex 4, Ch 15 | No | N/A | N/A | 3389.481 | 3539.9393 | 6929.4204 | 2.1074 | 40.4627 | 42.5702 | -3499.4766 | -6886.8502 | -98.86% | -99.39% | N/A | N/A | N/A | 10 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
166 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48C | Repl DSub Batteries | Wildfire | WLDFR-C10C: Substation Proactive Asset Replacement - Batteries | Ex 4, Ch 15 | No | N/A | N/A | 3389.481 | 3539.9393 | 6929.4204 | 2.1074 | 40.4627 | 42.5702 | -3499.4766 | -6886.8502 | -98.86% | -99.39% | N/A | N/A | N/A | 10 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
167 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48D | Repl DSub Breakers | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 29793.9318 | 31116.4778 | 60910.4096 | 9239.0055 | 13632.274 | 22871.2796 | -17484.2038 | -38039.1301 | -56.19% | -62.45% | NO | YES | # of circuit breakers | 40 | 40 | 80 | 9 | 3 | 12 | -37 | -68 | -92.5% | -85% | YES | Program expenditures were below imputed regulatory values due to prioritizing work in Emergency Replacements (MWC 17 and 59), and Overhead Maintenance Replacements (MWC 2A). | Actual units were lower than imputed units due to reprioritization of funding as explained in the cost variance explanation for this MAT code. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is capital infrastructure replacement work, like breakers, to maintain system operations and reliability. For 2023, PG&E reprioritized funding from MAT 48D to higher priority work in other programs as described in the cost variance explanation. At this time, PG&E anticipates that this program will continue to be lower priority for the remainder of the GRC cycle. Breakers may be replaced under MWC 59, on an just-in-time basis.
168 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48D | Repl DSub Breakers | Substation | SBSTN-C16D: Proactive Asset Replacement - Circuit Breakers | Ex 4, Ch 15 | Yes | N/A | N/A | 29793.9318 | 31116.4778 | 60910.4096 | 4708.8085 | 13632.274 | 18341.0826 | -17484.2038 | -42569.3271 | -56.19% | -69.89% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
169 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48D | Repl DSub Breakers | Wildfire | WLDFR-C10D: Substation Proactive Asset Replacement - Circuit Breakers | Ex 4, Ch 15 | Yes | N/A | N/A | 29793.9318 | 31116.4778 | 60910.4096 | 4708.8085 | 13632.274 | 18341.0826 | -17484.2038 | -42569.3271 | -56.19% | -69.89% | N/A | N/A | # of circuit breakers | 40 | 40 | 80 | 9 | 3 | 12 | -37 | -68 | -93% | -85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
170 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48D | Repl DSub Breakers | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 15 | Yes | N/A | N/A | 0 | 0 | 0 | 4530.197 | 0 | 4530.197 | 0 | 4530.197 | 0% | 100% | N/A | N/A | # of circuit breakers | 40 | 40 | 80 | 9 | 3 | 12 | -37 | -68 | -93% | -85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
171 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48E | Repl DSub Switches | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 2303.9531 | 2406.2251 | 4710.1781 | -244.0113 | 1067.6994 | 823.6881 | -1338.5257 | -3886.4901 | -55.63% | -82.51% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is ongoing capital infrastructure replacement work to maintain system operations and reliability. In 2023 & 2024, PG&E prioritized substation work (for example in MAT 48L, 54A, and MWC 59) over MAT 48E. For the 2023 GRC cycle, PG&E anticipates that this work will continue to be lower priority than other Substation work.
172 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48E | Repl DSub Switches | Substation | SBSTN-C16E: Substation Proactive Asset Replacement Switches | Ex 4, Ch 15 | No | N/A | N/A | 2303.9531 | 2406.2251 | 4710.1781 | -244.0113 | 1067.6994 | 823.6881 | -1338.5257 | -3886.4901 | -55.63% | -82.51% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
173 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48E | Repl DSub Switches | Wildfire | WLDFR-C10E: Substation Proactive Asset Replacement - Switches | Ex 4, Ch 15 | No | N/A | N/A | 2303.9531 | 2406.2251 | 4710.1781 | -244.0113 | 1067.6994 | 823.6881 | -1338.5257 | -3886.4901 | -55.63% | -82.51% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
174 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48F | Repl DSub Switchgear | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 33829.2322 | 35330.9042 | 69160.1364 | 17542.3511 | 20310.948 | 37853.2992 | -15019.9562 | -31306.8372 | -42.51% | -45.27% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures were below imputed regulatory values to support higher priority emergency work in MWC 59. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is capital infrastructure replacement work to maintain system operations and reliability. PG&E reprioritized this work to higher priority emergency work in MWC 59. At this time, PG&E foresees this program will continue to be lower priority.
175 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48F | Repl DSub Switchgear | Substation | SBSTN-C16F: Substation Proactive Asset Replacement - Switchgear | Ex 4, Ch 15 | No | N/A | N/A | 33829.2322 | 35330.9042 | 69160.1364 | 17542.3511 | 20310.948 | 37853.2992 | -15019.9562 | -31306.8372 | -42.51% | -45.27% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
176 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48F | Repl DSub Switchgear | Wildfire | WLDFR-C10F: Substation Proactive Asset Replacement - Switchgear | Ex 4, Ch 15 | No | N/A | N/A | 33829.2322 | 35330.9042 | 69160.1364 | 17542.3511 | 20310.948 | 37853.2992 | -15019.9562 | -31306.8372 | -42.51% | -45.27% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
177 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48H | Repl DSub Civil Structures | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 5649.1347 | 5899.8985 | 11549.0332 | 832.961 | 653.1139 | 1486.075 | -5246.7846 | -10062.9583 | -88.93% | -87.13% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is ongoing capital infrastructure replacement work to maintain system operations and reliability. In 2023 & 2024, PG&E prioritized substation work (for example in MAT 48L, 54A, and MWC 59) over MAT 48H. For the 2023 GRC cycle, PG&E anticipates that this work will continue to be lower priority than other Substation work.
178 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48H | Repl DSub Civil Structures | Substation | SBSTN-C005: Civil Structures Replacement | Ex 4, Ch 15 | Yes | N/A | N/A | 4230.5805 | 4418.375 | 8648.9555 | 835.5416 | 653.1139 | 1488.6555 | -3765.2611 | -7160.3 | -85.22% | -82.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
179 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48H | Repl DSub Civil Structures | Substation | SBSTN-M006: Minimize Wood in Substations | Ex 4, Ch 15 | Yes | N/A | N/A | 1418.5542 | 1481.5235 | 2900.0777 | -2.5806 | 0 | -2.5806 | -1481.5235 | -2902.6583 | -100% | -100.1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
180 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48L | Dist Line Work Support Substat | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 9496.7522 | 9918.3109 | 19415.063 | 29062.35 | 38379.321 | 67441.671 | 28461.0101 | 48026.608 | 287% | 247.4% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to a higher volume of substation replacements, in MWC 59, requiring a higher volume of distribution line support work in MAT 48L. | N/A | Over | Over | Over | Emergent | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This is a demand driven program. The purpose of this program is substation capital infrastructure replacement work which to support distribution line work. This program includes both proactive and emergency substation replacements. Due to aging infrastructure and the reprioritization of funding in related areas of MWC 48, PG&E anticipates there will continue to be an increased amount of costs than forecasted through the 2023 GRC cycle.
181 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48L | Dist Line Work Support Substat | Substation | SBSTN-C16G: Proactive Asset Replacement - Line Support Work | Ex 4, Ch 15 | No | N/A | N/A | 9496.7522 | 9918.3109 | 19415.063 | 29062.35 | 38379.321 | 67441.671 | 28461.0101 | 48026.608 | 287% | 247.4% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
182 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48L | Dist Line Work Support Substat | Wildfire | WLDFR-C10H: Substation Proactive Asset Replacement - Line Support Work | Ex 4, Ch 15 | No | N/A | N/A | 9496.7522 | 9918.3109 | 19415.063 | 29062.35 | 38379.321 | 67441.671 | 28461.0101 | 48026.608 | 287% | 247.4% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
183 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48N | DSub Insulators | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 5649.1347 | 5899.8985 | 11549.0332 | 0.30676 | 0.16404 | 0.4708 | -5899.7345 | -11548.5624 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is ongoing capital infrastructure replacement work to maintain system operations and reliability. In 2023 & 2024, PG&E prioritized substation work (for example in MAT 48L, 54A, and MWC 59) over MAT 48N. For the 2023 GRC cycle, PG&E anticipates that this work will continue to be lower priority than other Substation work.
184 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48N | DSub Insulators | Substation | SBSTN-C16H: Proactive Asset Replacement - Insulators | Ex 4, Ch 15 | No | N/A | N/A | 5649.1347 | 5899.8985 | 11549.0332 | 0.30676 | 0.16404 | 0.4708 | -5899.7345 | -11548.5624 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
185 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48N | DSub Insulators | Wildfire | WLDFR-C10I: Substation Proactive Asset Replacement - Insulators | Ex 4, Ch 15 | No | N/A | N/A | 5649.1347 | 5899.8985 | 11549.0332 | 0.30676 | 0.16404 | 0.4708 | -5899.7345 | -11548.5624 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
186 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48X | DSub Animal Abatement | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 6008.154 | 6274.8546 | 12283.0085 | 149.0098 | 62.3456 | 211.3555 | -6212.509 | -12071.6531 | -99.01% | -98.28% | NO | NO | # of locations | 17 | 17 | 34 | 0 | 0 | 0 | -17 | -34 | -100% | -100% | YES | Below variance threshold. | Actual units were lower than imputed units due to reprioritization of proactive animal abatement work to support higher priority work in MWC 48, such as distribution line work to support substation work under MAT 48L. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is capital infrastructure replacement work, like Animal Abatement, to maintain system operations and reliability. At this time, PG&E foresees this program to continue to be lower priority than other programs.
187 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48X | DSub Animal Abatement | Substation | SBSTN-C002: Animal Abatement Substation | Ex 4, Ch 15 | No | N/A | N/A | 6008.154 | 6274.8546 | 12283.0085 | 149.0098 | 62.3456 | 211.3555 | -6212.509 | -12071.6531 | -99.01% | -98.28% | N/A | N/A | N/A | 17 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
188 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49A | Distribution Line Automation | SRM Total | SRM Total | Ex 4, Ch 13 Ex 4, Ch 4.3 | No | On-going | Annual | 1920.7057 | 2005.9654 | 3926.671 | -9.493 | -3.6884 | -13.1813 | -2009.6537 | -3939.8524 | -100.2% | -100.3% | NO | NO | # of Devices | 18 | 18 | 36 | 0 | 0 | 0 | -18 | -36 | -100% | -100% | YES | Below variance threshold. | Actual units were lower than imputed units due to a change in how the program mitigates risk from what was forecasted in the 2023 GRC. In 2023 PG&E began recording work associated with the new Downed Conductor Detection (DCD) program. The DCD program mitigate ignitions for high impedance faults and is a wildfire risk mitigation. The DCD program uses harmonic analysis to detect arching present during high impedance faults and provides an immediate trip response. Note that the program units forecasted in 49A for risk DOVHD-M010 were completed in MAT 49B. | Under | On-Target | Under | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This program was forecasted in the 2023 GRC for the replacement of Reclosers and Recloser controllers for reliability and wildfire risks. In 2023 PG&E began implementing the Downed Conductor Detection (DCD) program and recording costs to 49A. In 2024 PG&E began recording the DCD costs to MAT 3US. For the forecasted costs for risk DOVHD-M010, the costs and units that were forecasted to MAT 49A in 2023 were recorded in MAT 49B. For the remaining GRC cycle, PG&E will continue to record DCD costs to 3US and DOVHD-M010 to MAT 49B. Therefore for 49A, even though work is continuing on other MAT codes, scope and budget will be reported as under but the overall status is proceeding as planned because the work will continue being done but recorded elsewhere.
189 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49A | Distribution Line Automation | Distribution Overhead | DOVHD-M010: 3A and 4C Line Recloser Replacement | Ex 4, Ch 13 Ex 4, Ch 4.3 | No | N/A | N/A | 1920.7057 | 2005.9654 | 3926.671 | -9.493 | -3.6884 | -13.1813 | -2009.6537 | -3939.8524 | -100.2% | -100.3% | N/A | N/A | # of Devices | 18 | 18 | 36 | 0 | 0 | 0 | -18 | -36 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
190 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49B | Recl Ctrls Inst/Repl | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 4587.0978 | 4790.718 | 9377.8158 | 1684.8762 | 2913.5386 | 4598.4148 | -1877.1794 | -4779.401 | -39.18% | -50.96% | NO | NO | # of line recloser locations | 44 | 44 | 88 | 18 | 36 | 54 | -8 | -34 | -18.18% | -38.64% | NO | Below variance threshold. | Below variance threshold | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is the replacement of line reclosers and controllers. For the remainder of the GRC cycle, PG&E will continue to record to 49B the costs and units that were forecasted in 49A for DOVHD-M010. In addition costs for EPSS, WLDFR-M020 are being recorded here that were not forecasted in the 2023 GRC.
191 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49B | Recl Ctrls Inst/Repl | Distribution Overhead | DOVHD-M010: 3A and 4C Line Recloser Replacement | Ex 4, Ch 13 | Yes | N/A | N/A | 4587.0978 | 4790.718 | 9377.8158 | 1684.8762 | 591.3909 | 2276.2671 | -4199.3271 | -7101.5487 | -87.66% | -75.73% | N/A | N/A | # of line recloser locations | 44 | 44 | 88 | 18 | 36 | 54 | -8 | -34 | -18.18% | -38.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
192 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49B | Recl Ctrls Inst/Repl | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex. 4, Ch 4.3 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 2332.1477 | 2332.1477 | 2332.1477 | 2332.1477 | 100% | 100% | N/A | N/A | # of line recloser locations | 44 | 44 | 88 | 18 | 36 | 54 | -8 | -34 | -18.18% | -38.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
193 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49C | OH Fuses Inst/Repl | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 1626.9506 | 1699.1706 | 3326.1212 | 2178.1721 | 2483.6664 | 4661.8385 | 784.4958 | 1335.7173 | 46.17% | 40.16% | NO | NO | # of Fused locations | 128.86 | 128.8596 | 257.7196 | 75 | 86 | 161 | -42.8596 | -96.7196 | -33.26% | -37.53% | YES | Below variance threshold. | Actual units were lower than imputed units due to recent updates to the standard requirements for this program, which have triggered additional work such as the full replacement of the pole. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is the installation and replacement of overhead fuses. As noted in the unit variance explanation, total cost for this work has increased driven by higher unit costs. In addition, there can be an annual disconnect between when dollars are spent and units are recorded for this program. For the remainder of the GRC cycle, PG&E expects to complete fewer units for the costs allocated.
194 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49C | OH Fuses Inst/Repl | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 13 | No | N/A | N/A | 1626.9506 | 1699.1706 | 3326.1212 | 2178.1721 | 2483.6664 | 4661.8385 | 784.4958 | 1335.7173 | 46.17% | 40.16% | N/A | N/A | N/A | 128.86 | 129 | 258 | 75 | 86 | 161 | -43 | -97 | -33.33% | -37.6% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
195 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49D | OH Recl/Sect/Swch Inst/Repl | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 13 | No | On-going | Annual | 0 | 0 | 0 | 1537.5867 | -52.0482 | 1485.5385 | -52.0482 | 1485.5385 | -100% | 100% | NO | NO | # of TripSavers installed | 0 | 0 | 0 | 35 | 1 | 36 | 1 | 36 | 100% | 100% | YES | Below variance threshold. | Actual units were higher than imputed units due to the installation of trip savers that remained in inventory and were not forecasted in the 2023 GRC. | Over | Over | Over | Emergent | The purpose of this program is the installation of Trip Saver devices and was not forecasted in the 2023 GRC because similar work is now being performed in MAT 49T. In 2024, PG&E conducted a one-time effort to install 1 trip saver remaining in inventory. The program has completed and the MAT Code has been re-purposed.
196 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49E | Genl Inst/Repl Circuit/Zone | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 0 | 0 | 0 | 1597.5643 | 1955.9164 | 3553.4807 | 1955.9164 | 3553.4807 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | The work for this program is recorded costs for circuit installation / replacement to enable EPSS for wildfire mitigation. The program work will continue through the remainder of the 2023 GRC period.
197 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49E | Genl Inst/Repl Circuit/Zone | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 13 | Yes | N/A | N/A | 0 | 0 | 0 | 6.4337 | 0 | 6.4337 | 0 | 6.4337 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
198 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49E | Genl Inst/Repl Circuit/Zone | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 13 | Yes | N/A | N/A | 0 | 0 | 0 | 1591.1306 | 1955.9164 | 3547.0469 | 1955.9164 | 3547.0469 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
199 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49G | UG Recl/Sect/Swch Inst/Repl | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 13 | No | On-going | Annual | 0 | 0 | 0 | 0.06224 | 0.18723 | 0.24947 | 0.18723 | 0.24947 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program was not forecast in the 2023 GRC. Any recorded amounts are from prior years' carry-over work.
200 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49S | Elect Reliability Inst FLISR | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 13 | No | On-going | Annual | 3881.6561 | 4053.9619 | 7935.618 | 964.3304 | 1175.6303 | 2139.9607 | -2878.3317 | -5795.6573 | -71% | -73.03% | NO | NO | # of FLISR Circuit Activations | 12 | 12 | 24 | 1 | 2 | 3 | -10 | -21 | -83.33% | -87.5% | YES | Below variance threshold. | Actual units were lower than imputed units due to reprioritization to other higher priority programs like Emergency Replacements (MWC 17 and 59), and Overhead Maintenance Replacements (MWC 2A). | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is the installation of technology to detect and isolate outages, and restore service to customers. PG&E anticipates that this program will continue to be lower priority for the remainder of the GRC cycle.
201 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49T | D-Single Phase Recloser | SRM Total | SRM Total | Ex 4, Ch 13 Ex 4, Ch 4.3 | No | On-going | Annual | 1452.7636 | 1517.2515 | 2970.0151 | 0 | 0 | 0 | -1517.2515 | -2970.0151 | -100% | -100% | NO | NO | # FuseSavers installed | 37.77 | 38 | 75.77 | 0 | 0 | 84 | -3 | 8.23 | -7.895% | 10.86% | NO | Below variance threshold. | Below variance threshold | On-Target | On-Target | Under | Canceled | The installation of fuse savers previously forecast and recorded under MAT 49T has transitioned to a new MAT 3UF. The original scope of trip saver work under MAT 49T has sunsetted.
202 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49T | D-Single Phase Recloser | Distribution Overhead | DOVHD-C014: Additional System Automation and Protection - FuseSaver | Ex 4, Ch 13 Ex 4, Ch 4.3 | No | N/A | N/A | 1452.7636 | 1517.2515 | 2970.0151 | 0 | 0 | 0 | -1517.2515 | -2970.0151 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
203 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49X | Emerging Dist Rel Improvements | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 3868.2593 | 4039.9704 | 7908.2297 | 16114.6244 | 32322.9499 | 48437.5744 | 28282.9795 | 40529.3447 | 700.1% | 512.5% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to EPSS work being recorded to this program. PG&E did not forecast EPSS capital work in the 2023 GRC due to the program was new and PG&E was not able to develop a forecast for the 2023 GRC. | N/A | Over | Over | Over | Emergent | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is reliability work to address routine, localized reliability issues as they emerge. In 2023, PG&E recorded to this MAT non-forecasted costs for EPSS sectionalizing, which reduces customer impact of EPSS. Starting in 2024 through 2025, the EPSS work is being recorded to 49D.
204 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49X | Emerging Dist Rel Improvements | Distribution Overhead | DOVHD-C012: Targeted Reliability Programs | Ex 4, Ch 13 | Yes | N/A | N/A | 3868.2593 | 4039.9704 | 7908.2297 | 9114.6262 | 32322.9499 | 41437.5761 | 28282.9795 | 33529.3464 | 700.1% | 424% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
205 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49X | Emerging Dist Rel Improvements | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 13 | Yes | N/A | N/A | 0 | 0 | 0 | 6999.9982 | 0 | 6999.9982 | 0 | 6999.9982 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
206 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49# | Not assigned | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 13025.7745 | 13603.9857 | 26629.7602 | -294.1035 | 1540.8805 | 1246.777 | -12063.1052 | -25382.9832 | -88.67% | -95.32% | NO | YES | # of line reclosers inventory received | 694 | 693.7919 | 1387.7919 | 1307 | 671 | 1978 | -22.7919 | 590.2081 | -3.285% | 42.53% | NO | Program expenditures were below imputed regulatory values due to PG&E's decision to record the associated material costs to the actual projects in various other programs such as critical operating equipment, EPSS related work, and capacity projects, rather than to this MAT code. This program purchases and maintains inventory of line reclosers. | Below variance threshold | On-Target | On-Target | Under | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is for purchases and maintains inventory of line reclosers; the costs were centrally forecasted in 49# in the 2023 GRC. In the 2023 GRC cycle, PG&E will record the recloser material costs to individual projects in various programs however the reclosers will be captured here in 49#.
207 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49# | Not assigned | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 13 | Yes | N/A | N/A | 0 | 0 | 0 | 31.7594 | 0 | 31.7594 | 0 | 31.7594 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
208 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49# | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 13 | Yes | N/A | N/A | 13025.7745 | 13603.9857 | 26629.7602 | -325.8629 | 1540.8805 | 1215.0176 | -12063.1052 | -25414.7426 | -88.67% | -95.44% | N/A | N/A | # of line reclosers inventory received | 694 | 693.7919 | 1387.7919 | 1307 | 671 | 1978 | -22.7919 | 590.2081 | -3.285% | 42.53% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
209 | Capital | Electric Distribution | 54 | E Dist Subst Repl Transformer | 54A | E Dist Subst-Repl Transfm | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 18767.4771 | 19600.5612 | 38368.0383 | 24806.1031 | 7094.1477 | 31900.2507 | -12506.4136 | -6467.7876 | -63.81% | -16.86% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures were below imputed regulatory values due to prioritizing work in Emergency Replacements (MWC 59). | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is capital infrastructure replacement work, like transformers, to maintain system operations and reliability. For 2023, PG&E reprioritized funding from MAT 54A to higher priority work in other programs as described in the cost variance explanation. At this time, PG&E anticipates that this program will continue to be lower priority for the remainder of the GRC cycle. Transformers may be replaced under MWC 59.
210 | Capital | Electric Distribution | 54 | E Dist Subst Repl Transformer | 54A | E Dist Subst-Repl Transfm | Substation | SBSTN-C16J: Proactive Asset Replacement - Transformer | Ex 4, Ch 15 | Yes | N/A | N/A | 16703.0546 | 17444.4995 | 34147.5541 | 22502.5842 | 3859.8901 | 26362.4744 | -13584.6094 | -7785.0797 | -77.87% | -22.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
211 | Capital | Electric Distribution | 54 | E Dist Subst Repl Transformer | 54A | E Dist Subst-Repl Transfm | Substation | SBSTN-M002: Increase Capitalized Emergency (CEM) Stock for Transformers, Emergency Mobile Transformers | Ex 4, Ch 15 | Yes | N/A | N/A | 2064.4225 | 2156.0617 | 4220.4842 | 2204.8708 | 3234.2575 | 5439.1283 | 1078.1958 | 1218.6441 | 50.01% | 28.87% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
212 | Capital | Electric Distribution | 54 | E Dist Subst Repl Transformer | 54A | E Dist Subst-Repl Transfm | Wildfire | WLDFR-C10K: Substation Proactive Asset Replacement - Transformer | Ex 4, Ch 15 | Yes | N/A | N/A | 16703.0546 | 17444.4995 | 34147.5541 | 22502.5842 | 3859.8901 | 26362.4744 | -13584.6093 | -7785.0797 | -77.87% | -22.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
213 | Capital | Electric Distribution | 54 | E Dist Subst Repl Transformer | 54A | E Dist Subst-Repl Transfm | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 15 | Yes | N/A | N/A | 0 | 0 | 0 | 98.648 | 0 | 98.648 | 0 | 98.648 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
214 | Capital | Electric Distribution | 54 | E Dist Subst Repl Transformer | 54L | E Dist Subst-Life Ext Transfm | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 3389.481 | 3539.9393 | 6929.4204 | 15.4234 | 504.4323 | 519.8557 | -3035.5071 | -6409.5647 | -85.75% | -92.5% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to recondition older substation transformers to extend their life expectancy by replacing a specific combination of components. For 2024, PG&E re-prioritized funding from MAT 54L to higher priority work in MAT 54A. Over the GRC cycle, PG&E expects to continue to reprioritize this program to higher priority work within the MWC 54 program.
215 | Capital | Electric Distribution | 54 | E Dist Subst Repl Transformer | 54L | E Dist Subst-Life Ext Transfm | Substation | SBSTN-M001: Transformer Life Extension | Ex 4, Ch 15 | No | N/A | N/A | 3389.481 | 3539.9393 | 6929.4204 | 15.4234 | 504.4323 | 519.8557 | -3035.5071 | -6409.5647 | -85.75% | -92.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
216 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 14 | No | On-going | Annual | 0 | 0 | 0 | -226.305 | -413.5741 | -639.8791 | -413.5741 | -639.8791 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program covers miscellaneous standard costs and adjustments that are not directly attributable to a specific MAT code. PG&E does not forecast costs for these activities.
217 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56A | UG Cable Other Repl | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 38567.0412 | 40279.0235 | 78846.0648 | 20512.8025 | 24281.3748 | 44794.1773 | -15997.6487 | -34051.8875 | -39.72% | -43.19% | NO | YES | # miles | 17.5 | 17.5 | 35 | 6.87 | 12.4 | 19.27 | -5.1 | -15.73 | -29.14% | -44.94% | YES | Program expenditures were below imputed regulatory values due to reprioritizing to emergency replacements (MWC 17), and capacity improvements (MWC 06, 46). | Actual units were lower than imputed units due to reprioritization as discussed in the cost variance explanation. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace underground primary cables in areas with history of failures.
218 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56A | UG Cable Other Repl | Underground | DUNGD-C06A: Primary Cable Replacement Program | Ex 4, Ch 13 | No | N/A | N/A | 38567.0412 | 40279.0235 | 78846.0648 | 20512.8025 | 24281.3748 | 44794.1773 | -15997.6487 | -34051.8875 | -39.72% | -43.19% | N/A | N/A | # miles | 17.5 | 17.5 | 35 | 6.87 | 12.4 | 19.27 | -5.1 | -15.73 | -29.14% | -44.94% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
219 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56B | UG Cable Inject | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 1164.6483 | 1216.3467 | 2380.995 | 45.8496 | 119.069 | 164.9186 | -1097.2777 | -2216.0765 | -90.21% | -93.07% | NO | NO | # of Miles | 6 | 6 | 12 | 0 | 0 | 0 | -6 | -12 | -100% | -100% | YES | Below variance threshold. | Actual units were lower than imputed units due to reprioritizing emergency replacements (MWC 17) and underground/network maintenance replacements (MWCs 2B & 2C). | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to test or rejuvenate UG primary cables as part of targeted replacement strategy. PG&E anticipates that this program will continue to be lower priority for the remainder of the GRC cycle.
220 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56B | UG Cable Inject | Underground | DUNGD-C06B: Primary Cable Rejuvenation Program | Ex 4, Ch 13 | No | N/A | N/A | 1164.6483 | 1216.3467 | 2380.995 | 45.8496 | 119.069 | 164.9186 | -1097.2777 | -2216.0765 | -90.21% | -93.07% | N/A | N/A | # of Miles | 5.5 | 6 | 11.5 | 0 | 0 | 0 | -6 | -11.5 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
221 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56C | UG Cable COE Repl | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 37551.0869 | 39217.9713 | 76769.0582 | 7943.626 | 782.2413 | 8725.8674 | -38435.7299 | -68043.1908 | -98.01% | -88.63% | YES | YES | # projects | 197 | 197 | 394 | 23 | 1 | 24 | -196 | -370 | -99.49% | -93.91% | YES | Program expenditures were below imputed regulatory values due to reprioritizing emergency replacements (MWC 17). | Actual units were lower than imputed units due to reprioritization as discussed in the cost variance explanation. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program to replace failed underground primary cables in 200A loop systems.
222 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56C | UG Cable COE Repl | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 13 | No | N/A | N/A | 37551.0869 | 39217.9713 | 76769.0582 | 7943.626 | 782.2413 | 8725.8674 | -38435.7299 | -68043.1908 | -98.01% | -88.63% | N/A | N/A | # projects | 197 | 197 | 394 | 23 | 1 | 24 | -196 | -370 | -99.49% | -93.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
223 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56D | TGram/TGral Switch Replacement | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 13 | No | On-going | Annual | 0 | 0 | 0 | -7.6184 | 0.64595 | -6.9724 | 0.64595 | -6.9724 | 100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Under | Proceeding as Planned | The purpose of this program is to replace UG switches to the extent that TGRAM/TGRAL switches are identified. This program will continue through the remainder of the 2023 GRC period.
224 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56N(l) | Network Cable Replacement | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 32200.0672 | 33629.421 | 65829.4882 | 261.3623 | 382.4805 | 643.8428 | -33246.9405 | -65185.6454 | -98.86% | -99.02% | YES | YES | # of Circuit Feet | 56889.32 | 56889.32 | 113778.64 | 0 | 0 | 0 | -56889.32 | -113778.64 | -100% | -100% | YES | Program expenditures were below imputed regulatory values due to reprioritizing work to emergency replacements (MWC 17), and capacity improvements (MWC 06, 46). | Actual units were lower than imputed units due to reprioritization as discussed in the cost variance explanation. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a to replace network cable assets, prior to premature failure. PG&E anticipates that this program will continue to be lower priority for the remainder of the GRC cycle.
225 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56N | Network Cable Replacement | Distribution Network | DNTWK-C001: Network Cable Replacement | Ex 4, Ch 14 | No | N/A | N/A | 32200.0672 | 33629.421 | 65829.4882 | 261.3623 | 382.4805 | 643.8428 | -33246.9405 | -65185.6454 | -98.86% | -99.02% | N/A | N/A | # of Circuit Feet | 56889.32 | 56889.32 | 113778.64 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
226 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56S | Replace Obsolete UG Switches | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 8473.8585 | 8850.0112 | 17323.8697 | -834.7214 | 11151.9769 | 10317.2555 | 2301.9657 | -7006.6142 | 26.01% | -40.44% | NO | NO | # of LBOR Switch Replacements | 77 | 77 | 154 | 0 | 39 | 39 | -38 | -115 | -49.35% | -74.68% | YES | Below variance threshold. | Actual units were lower than imputed units due to delays in construction due to permitting and unforeseen additions, such as cable replacement, to some jobs that were only identified at the time of construction. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace older oil-filled LBOR switches with no oil inspection sight glass which poses a greater safety risk than other types of switches.
227 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56S | Replace Obsolete UG Switches | Underground | DUNGD-C007: LBOR Switch Replacement | Ex 4, Ch 13 | No | N/A | N/A | 8473.8585 | 8850.0112 | 17323.8697 | -834.7214 | 11151.9769 | 10317.2555 | 2301.9657 | -7006.6142 | 26.01% | -40.44% | N/A | N/A | # of LBOR Switch Replacements | 77 | 77 | 154 | 0 | 39 | 39 | -38 | -115 | -49.35% | -74.68% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
228 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56T | Install Temperature Indicator | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 8837.6017 | 9229.9009 | 18067.5026 | 3575.1812 | 5432.7437 | 9007.9248 | -3797.1572 | -9059.5777 | -41.14% | -50.14% | NO | NO | # of Installations | 2294 | 2294 | 4588 | 0 | 1019 | 1019 | -1275 | -3569 | -55.58% | -77.79% | YES | Below variance threshold. | Actual units were lower than imputed units due to quality and performance issues with the TAD devices. PG&E switched to a different manufacturer but did not receive TAD units until later in the year, impacting the ability to install the imputed amount of units. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to install temperature alarm devices to monitor UG asset condition and identify proactive replacements, prior to premature failure.
229 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56T | Install Temperature Indicator | Underground | DUNGD-C008: UG Transformers Temperature Sensor | Ex 4, Ch 13 | No | N/A | N/A | 8837.6017 | 9229.9009 | 18067.5026 | 3575.1812 | 5432.7437 | 9007.9248 | -3797.1572 | -9059.5777 | -41.14% | -50.14% | N/A | N/A | # of Installations | 2294 | 2294 | 4588 | 0 | 1019 | 1019 | -1275 | -3569 | -55.58% | -77.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
230 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58A | DSub Safety&Envir&Fire Protect | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 3389.481 | 3539.9393 | 6929.4204 | -4.7059 | 36.0829 | 31.377 | -3503.8564 | -6898.0433 | -98.98% | -99.55% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program concerns fire protection and suppression installs, replacements, or upgrades as required by local fire marshals and state regulations. PG&E foresees this program to continue to be lower priority than other programs.
231 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58A | DSub Safety&Envir&Fire Protect | Substation | SBSTN-C009: Fire Protection / Suppression Systems | Ex 4, Ch 15 | No | N/A | N/A | 3389.481 | 3539.9393 | 6929.4204 | -4.7059 | 36.0829 | 31.377 | -3503.8564 | -6898.0433 | -98.98% | -99.55% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
232 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58A | DSub Safety&Envir&Fire Protect | Wildfire | WLDFR-C018: Fire Protection / Suppression Systems | Ex 4, Ch 15 | No | N/A | N/A | 3389.481 | 3539.9393 | 6929.4204 | -4.7059 | 36.0829 | 31.377 | -3503.8564 | -6898.0433 | -98.98% | -99.55% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
233 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58B | Repl Dist Sub Civil Structures | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 0 | 0 | 0 | 0 | 95.2426 | 95.2426 | 95.2426 | 95.2426 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This MAT 58B program is for as-needed civil structure improvements driven by environmental & security requirements i.e., concrete reinforcements and seismic work. Work may continue to be charged to this MAT program through the remainder of the 2023 GRC period.
234 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58C | Repl Dist Sub Misc Equip | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 15 | No | On-going | Annual | 0 | 0 | 0 | 9.2229 | 0 | 9.2229 | 0 | 9.2229 | 0% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program is for replacement of miscellaneous substation equipment may incur minimal carry-over costs through the remainder of the 2023 GRC peiod.
235 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58S | DSub Security Upgrades | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 5197.2044 | 5427.9071 | 10625.1115 | 3405.633 | 7752.3435 | 11157.9765 | 2324.4363 | 532.8649 | 42.82% | 5.015% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is installs, upgrades, or replacements of physical security measures within substations. This program represents ongoing capital infrastructure replacement work to maintain system operations and reliability. For the remainder of the 2023 GRC PG&E expects to spend more than imputed on the program in order to include physical security improvement at five substations to meet CPUC Decision 19-01-018 (SB 699) requirements. This decision has requirements for critical distribution security commitments. PG&E developed and revised a mitigation plan to upgrade the physical security at five critical distribution substations by 2026.
236 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58S | DSub Security Upgrades | Substation | SBSTN-C001: Substation Security Enhancements | Ex 4, Ch 15 | No | N/A | N/A | 5197.2044 | 5427.9071 | 10625.1115 | 3405.633 | 7752.3435 | 11157.9765 | 2324.4363 | 532.8649 | 42.82% | 5.015% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
237 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58S | DSub Security Upgrades | Wildfire | WLDFR-C10M: Substation Security Enhancements | Ex 4, Ch 15 | No | N/A | N/A | 5197.2044 | 5427.9071 | 10625.1115 | 3405.633 | 7752.3435 | 11157.9765 | 2324.4363 | 532.8649 | 42.82% | 5.015% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
238 | Capital | Electric Distribution | 59 | E Dist Subst Emergency Repl | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 15 | No | On-going | Annual | 85866.848 | 89678.4582 | 175545.3061 | 172615.2136 | 184247.2258 | 356862.4394 | 94568.7677 | 181317.1333 | 105.5% | 103.3% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to a higher volume of emergency replacement work than forecasted in the 2023 GRC. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is for emergency capital infrastructure replacement work to maintain system operations and reliability. PG&E anticipates that a higher volume of work in this program may materialize due to reprioritization of other substation work.
239 | Capital | Electric Distribution | 63 | E T&D Control System/ Facility | 63C | Advanced Dist Mgmt System Dev | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 21 | No | 7 | 6 | 113742.7965 | 118791.8138 | 232534.6102 | 112433.5182 | 104114.1288 | 216547.647 | -14677.685 | -15986.9633 | -12.36% | -6.875% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program includes ongoing work to design, build, and test the Advanced Distribution Management System (ADMS).
240 | Capital | Electric Distribution | 63 | E T&D Control System/ Facility | 63D | Distribution Operational Tech | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 7 | No | On-going | Annual | 4776.4117 | 4968.1043 | 9744.516 | 4878.2743 | 5942.8016 | 10821.0758 | 974.6973 | 1076.5599 | 19.62% | 11.05% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program that includes minor enhancements & bug fixes to distribution operations technology, and the development of reporting capabilities used in PG&E distribution operations. The work will continue through the remainder of the 2023 GRC period.
241 | Capital | Electric Distribution | 63 | E T&D Control System/ Facility | 63# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 7 | No | On-going | Annual | 0 | 0 | 0 | 7055.8779 | 8553.0284 | 15608.9064 | 8553.0284 | 15608.9064 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program includes work in PG&E's Distribution Energy Resource Management Systems (DERMS), is on-going and will continue through the remainder of the 2023 GRC period. The DERMS costs that were forecast in the 2023 GRC in MAT 63C, are being been recorded in MAT 63#.
242 | Capital | Electric Distribution | 95 | E Dist Major Emergency | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 6 | No | On-going | Annual | 66359.7164 | 69305.4093 | 135665.1257 | 49287.4677 | 192225.3094 | 241512.7771 | 122919.9001 | 105847.6514 | 177.4% | 78.02% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due the February Winter Storms and the July Weather Event which caused a significant deviation from historical trends | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This is a demand driven program. The purpose of this program is for major emergencies. This program has no end and is responsive to conditions that require immediate attention.
Notes:
(a) | During 2023 PG&E began recording costs for expulsion fuse replacements that were imputed in MAT 2AP to MAT 2AJ.
(b) | The Distributed Energy Resource Management System (DERMS) costs that were forecasted in the 2023 GRC as 63C, are being been recorded in 63#.
(c) | MAT 3UA includes 2023 costs that were reported in 49M in the 2023 RSAR.
(d) | MAT 3UC was introduced in 2024 to track costs to replace or retrofit Motorized Switch Operators (MSO).
(e) | MAT 3UD Includes 2023 costs that were reported in 49I for WLDFR-M012 in the 2023 RSAR. In addition, 2023 unit data has been updated to correct the 2023 RSAR units previously reported in 49I for this program.
(f) | MAT 3UE Includes 2023 costs that were reported in 49I for WLDFR-M011 in the 2023 RSAR. In addition, 2023 unit data has been updated to correct the 2023 RSAR units previously reported in 49I for this program..
(g) | MAT 3UF includes 2023 costs that were reported in 49T for WLDFR-M10B in the 2023 RSAR.
(h) | MAT 3UL includes 2023 costs that were reported in 49I for WLDFR-M07A in the 2023 RSAR. In addition, 2023 unit data has been updated to correct the 2023 RSAR units previously reported in 49I for this program.
(i) | MAT 3UP includes 2023 costs that were reported in 49H in the 2023 RSAR.
(j) | MAT 3UR includes 2023 costs that were reported in 49R in the 2023 RSAR.
(k) | MAT 3US includes 2023 costs that were reported in 49A in the 2023 RSAR.
(l) | MAT 3UT Imputed adopted costs for WLDFR-M004 were imputed and are shown in MAT 2AP.
(m) | MAT 2AR was reported in the 2023 RSAR as RAMP mitigation DOVHD-M003 and is corrected here to be WLDFR-M003 as well.
(n) | MAT 56N 2023 imputed adopted amounts have been updated with values from the 2023 GRC.
(o) | MAT 49D was reported in the 2023 RSAR as a RAMP mitigation DOVHD-C014 and is corrected here to be SRM Non-RAMP.