## GD SRM MAT Table Expense
Table 2-3 2024 RSAR 2023 GRC CYCLE GAS DISTRIBUTION EXPENSE COMPARISON BY MAT FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | C6 | C7 | D | E | F | G1 | G2 | G3 | H1 | H2 | H3 | I1 | I2 | J1 | J2 | K | L | M | N1 | N2 | N3 | O1 | O2 | O3 | P1 | P2 | Q1 | Q2 | R | S | T | U1 | U2 | U3 | V | W
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name | MAT | MAT Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program/ Project Life (years) | Program/ Project Year | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs | Imputed Costs for 2023 GRC Cycle to date($) (G1+G2) | 2023 Actual Costs | 2024 Actual Costs | Actual Costs for 2023 GRC Cycle to date($) (H1+H2) | Difference for 2024 ($) (H2-G2) | Difference for 2023 GRC Cycle to Date ($) (H3-G3) | Spending Percent Variance for 2024 (%) ((H-G)/G*100) | Spending Percent Variance for 2023 GRC Cycle (%) ((H3-G3)/G3*100) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | Unit Type | 2023 Imputed Adopted Units | 2024 Imputed Adopted Units | Imputed Units for 2023 GRC Cycle to Date (N2+N1) | 2023 Actual Units | 2024 Actual Units | Actual Units for 2023 GRC Cycle to Date (O2+O1) | Difference for 2024 (# of Units) (O2-N2) | Difference for 2023 GRC Cycle to Date (# of Units)​ (O3-N3) | Unit Percent Variance for 2024 (%) ((O2-N2)/N2*100) | Unit Percent Variance for 2023 GRC Cycle to Date (%)​ ((O3-N3)/N3) | Unit Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | 2024 Unit Variance Explanation | Forecast Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T) | Status | Completion Status Statement
1 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDA | Field Services: Other | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 8 | No | On-Going | Annual | 0 | 0 | 0 | -25.8246 | 140.1379 | 114.3132 | 140.1379 | 114.3132 | 100% | 100% | N | N | non-unitized: This MAT has no measurable units because it is used for other support costs for field services. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
2 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDD | Pilot Relight | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 8 | No | On-Going | Annual | 12170.1951 | 12585.3507 | 24755.5459 | 11078.2963 | 10643.0721 | 21721.3684 | -1942.2787 | -3034.1775 | -15.43% | -12.26% | N | N | # of Service Tickets | 138946 | 138946 | 277892 | 110292 | 104897 | 215189 | -34049 | -62703 | -24.51% | -22.56% | Y | N/A | Actual units were lower than imputed due to lower customer demand of Pilot Relight calls. | Under | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
3 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDE | Appliance Adjs | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 8 | No | On-Going | Annual | 1153.0407 | 1192.3738 | 2345.4145 | 1557.4131 | 1324.5453 | 2881.9583 | 132.1715 | 536.5438 | 11.08% | 22.88% | N | N | # of Service Tickets | 12142 | 12142 | 24284 | 13949 | 11725 | 25674 | -417 | 1390 | -3.434% | 5.724% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
4 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDF | Gas Fumigation Activity | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 3595.0683 | 3717.705 | 7312.7734 | 2841.5014 | 3128.0413 | 5969.5428 | -589.6637 | -1343.2306 | -15.86% | -18.37% | N | N | # of Service Tickets | 34152 | 34152 | 68304 | 23250 | 25153 | 48403 | -8999 | -19901 | -26.35% | -29.14% | Y | N/A | Actual units were lower than imputed due to lower customer demand of Fumigation Activity calls. | Under | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
5 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDF | Gas Fumigation Activity | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C015 Gas Fumigation | Ex 3, Ch 8 | No | On-Going | Annual | 3595.0683 | 3717.705 | 7312.7734 | 2840.5014 | 3128.0413 | 5968.5428 | -589.6637 | -1344.2306 | -15.86% | -18.38% | N/A | N/A | N/A | 34152 | 34152 | 68304 | 23250 | 25153 | 48403 | -8999 | -19901 | -26.35% | -29.14% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDG | Gas Leaks & Emergencies | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 31400.9614 | 32472.1262 | 63873.0876 | 32228.0245 | 30186.1826 | 62414.2071 | -2285.9437 | -1458.8806 | -7.04% | -2.284% | N | N | # of Service Tickets | 160514 | 160514 | 321028 | 120636 | 106801 | 227437 | -53713 | -93591 | -33.46% | -29.15% | Y | N/A | Actual units were lower than imputed due to lower customer demand of Gas Leak & Emergency calls. | Under | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
7 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDG | Gas Leaks & Emergencies | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C007 Gas Leaks and Emergencies | Ex 3, Ch 8 | No | On-Going | Annual | 31400.9614 | 32472.1262 | 63873.0876 | 32227.0245 | 30186.1826 | 62413.2071 | -2285.9437 | -1459.8806 | -7.04% | -2.286% | N/A | N/A | N/A | 160514 | 160514 | 321028 | 120636 | 106801 | 227437 | -53713 | -93591 | -33.46% | -29.15% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDK | Gas Start | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 8 | No | On-Going | Annual | 5142.1119 | 5317.5221 | 10459.6339 | 4243.0061 | 3915.5849 | 8158.591 | -1401.9371 | -2301.0429 | -26.36% | -22% | N | N | # of Service Tickets | 45509 | 45509 | 91018 | 32056 | 29221 | 61277 | -16288 | -29741 | -35.79% | -32.68% | Y | N/A | Actual units were lower than imputed due to lower customer demand of Gas Start calls. | Under | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
9 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDL | Gas Stop | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 8 | No | On-Going | Annual | 4594.6895 | 4751.4258 | 9346.1154 | 1525.5136 | 1414.8455 | 2940.3591 | -3336.5803 | -6405.7563 | -70.22% | -68.54% | N | N | # of Service Tickets | 77877 | 77877 | 155754 | 16453 | 17194 | 33647 | -60683 | -122107 | -77.92% | -78.4% | Y | N/A | Actual units were lower than imputed due to lower customer demand of Gas Stop calls. | Under | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
10 | O&M Expense | Gas Distribution | DD | Provide Field Service | DD# | Not assigned | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 8 | No | On-Going | Annual | 0 | 0 | 0 | 0.09522 | 0 | 0.09522 | 0 | 0.09522 | 0% | 0% | N | N | non-unitized: This MAT has no measurable units because it is used for adjustments related to labor and overheads under MWC DD. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | N/A | N/A | N/A | N/A | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
11 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEA | Leak Survey | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 10306.7242 | 10467.1392 | 20773.8634 | 15560.1884 | 17899.549 | 33459.7374 | 7432.4098 | 12685.874 | 71.01% | 61.07% | N | Y | Services Surveyed | 455760 | 455760 | 911520 | 1233158 | 1364697 | 2597855 | 908937 | 1686335 | 199.4% | 185% | Y | Actual costs were higher than imputed regulatory values due to a shift from MAT DEF to MAT DEA, leveraging Advanced Mobile Leak Detection (Picarro) cars to reduce emissions in the gas system faster, and drive down risk in the system utilizing the Super Emitter Program. | Actual units were higher than imputed units due to a shift from MAT DEF to MAT DEA, leveraging Advanced Mobile Leak Detection (Picarro) cars to reduce emissions in the gas system faster, and drive down risk in the system utilizing the Super Emitter Program. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
12 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEA | Leak Survey | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 10306.7242 | 10467.1392 | 20773.8634 | 15558.1884 | 17899.547 | 33457.7354 | 7432.4078 | 12683.872 | 71.01% | 61.06% | N/A | N/A | N/A | 455760 | 455760 | 911520 | 1233158 | 1364697 | 2597855 | 908937 | 1686335 | 199.4% | 185% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEA | Leak Survey | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 10306.7242 | 10467.1392 | 20773.8634 | 15559.1884 | 17899.548 | 33458.7364 | 7432.4088 | 12684.873 | 71.01% | 61.06% | N/A | N/A | N/A | 455760 | 455760 | 911520 | 1233158 | 1364697 | 2597855 | 908937 | 1686335 | 199.4% | 185% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEB | Special Leak Survey | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 2810.1416 | 2853.8789 | 5664.0205 | 3438.2013 | 2850.7662 | 6288.9675 | -3.1127 | 624.947 | -0.1091% | 11.03% | N | N | # Customer Calls | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
15 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEB | Special Leak Survey | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 2810.1416 | 2853.8789 | 5664.0205 | 3436.2013 | 2850.7642 | 6286.9655 | -3.1147 | 622.945 | -0.1091% | 11% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
16 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEB | Special Leak Survey | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 2810.1416 | 2853.8789 | 5664.0205 | 3437.2013 | 2850.7652 | 6287.9665 | -3.1137 | 623.946 | -0.1091% | 11.02% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEC | Downgrade No Repair | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 3522.1487 | 3576.9678 | 7099.1164 | 4341.4318 | 3193.87 | 7535.3018 | -383.0978 | 436.1854 | -10.71% | 6.144% | N | N | Services Surveyed | 8936 | 8936 | 17872 | 2272 | 2703 | 4975 | -6233 | -12897 | -69.75% | -72.16% | Y | N/A | Actual units were lower than imputed units due to grade three leaks that were downgraded from a grade two leak now being charged to the respective repair MAT (FIG, FIP or FIH). | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
18 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEC | Downgrade No Repair | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 3522.1487 | 3576.9678 | 7099.1164 | 4340.4318 | 3193.87 | 7534.3018 | -383.0978 | 435.1854 | -10.71% | 6.13% | N/A | N/A | N/A | 8936 | 8936 | 17872 | 2272 | 2703 | 4975 | -6233 | -12897 | -69.75% | -72.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DED | Rechecks | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 2561.9606 | 2601.8352 | 5163.7958 | 863.4317 | 675.5844 | 1539.0162 | -1926.2508 | -3624.7797 | -74.03% | -70.2% | N | N | # of Rechecks Performed | 43484 | 43484 | 86968 | 22431 | 20175 | 42606 | -23309 | -44362 | -53.6% | -51.01% | Y | N/A | Actual units were lower than imputed units due: 1) leak find rates have decreased since the years 2020-2023 due to more frequent leak surveys; 2) the program was targeting leak repairs prior to the leak's first required recheck date, regardless of the compliance due date; and 3) Grade three leaks were added to the schedule for repair versus prior years where these leaks were not on a repair cycle. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
20 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DED | Rechecks | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 2561.9606 | 2601.8352 | 5163.7958 | 862.4317 | 675.5834 | 1538.0152 | -1926.2518 | -3625.7807 | -74.03% | -70.22% | N/A | N/A | N/A | 43484 | 43484 | 86968 | 22431 | 20175 | 42606 | -23309 | -44362 | -53.6% | -51.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEE | Customer Calls | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 789.096 | 801.3776 | 1590.4735 | 2 | 0 | 2 | -801.3776 | -1588.4735 | -100% | -99.87% | N | N | Services Surveyed | 3693 | 3693 | 7386 | 0 | N/A | N/A | N/A | N/A | -100% | N/A | Y | N/A | Actual units were lower than imputed due to MAT no longer used, imputed will show up but no actuals | Under | Under | On-Target | Cancelled | MAT DEE no longer used, imputed will show up but no actuals
22 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEE | Customer Calls | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 789.096 | 801.3776 | 1590.4735 | 0 | 0 | 0 | -801.3776 | -1590.4735 | -100% | -100% | N/A | N/A | N/A | 3693 | 3693 | 7386 | 0 | N/A | N/A | N/A | N/A | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
23 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEE | Customer Calls | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 789.096 | 801.3776 | 1590.4735 | 1 | 0 | 1 | -801.3776 | -1589.4735 | -100% | -99.94% | N/A | N/A | N/A | 3693 | 3693 | 7386 | 0 | N/A | N/A | N/A | N/A | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
24 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEF | Advanced Mobile Technology | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 12396.0127 | 12588.9456 | 24984.9582 | 2787.5462 | -0.59873 | 2786.9475 | -12589.5443 | -22198.0107 | -100% | -88.85% | Y | Y | Services Surveyed | 905956 | 905956 | 1811912 | 244897 | 0 | 244897 | -905956 | -1567015 | -100% | -86.48% | Y | Actual costs were lower than imputed regulatory values due to a shift from MAT DEF to MAT DEA, leveraging Advanced Mobile Leak Detection (Picarro) cars to reduce emissions in the gas system faster, and drive down risk in the system utilizing the Super Emitter Program. | Actual units were lower than imputed units due to a shift from MAT DEF to MAT DEA, leveraging Advanced Mobile Leak Detection (Picarro) cars to reduce emissions in the gas system faster, and drive down risk in the system utilizing the Super Emitter Program. | Under | Under | Under | Rescheduled | This program will not meet the imputed units as all DEF units have now been optimized to DEA units.
25 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEF | Advanced MobileTechnology | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 12396.0127 | 12588.9456 | 24984.9582 | 2785.5462 | -0.60073 | 2784.9455 | -12589.5463 | -22200.0127 | -100% | -88.85% | N/A | N/A | N/A | 905956 | 905956 | 1811912 | 244897 | 0 | 244897 | -905956 | -1567015 | -100% | -86.48% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
26 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEF | Advanced MobileTechnology | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 12396.0127 | 12588.9456 | 24984.9582 | 2786.5462 | -0.59973 | 2785.9465 | -12589.5453 | -22199.0117 | -100% | -88.85% | N/A | N/A | N/A | 905956 | 905956 | 1811912 | 244897 | 0 | 244897 | -905956 | -1567015 | -100% | -86.48% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
27 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEH | GD Capacity Uprates | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 2434.7536 | 2474.5924 | 4909.346 | 1963.5864 | 1144.8425 | 3108.4289 | -1329.7499 | -1800.9171 | -53.74% | -36.68% | N | N | non-unitized: This program has no measurable units because it includes various activities to support pressure changes (e.g. engineering activities, repairs as needed, temporary piping needed) which cannot be measured in a meaningful way using a single unit of measure. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
28 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEH | GD Capacity Uprates | Insufficient Capacity to Meet Customer Demand | CPCTY-M007 Distribution Uprates and Downrates | Ex 3, Ch 11 | No | On-Going | Annual | 2434.7536 | 2474.5924 | 4909.346 | 1962.5864 | 1144.8415 | 3107.4279 | -1329.7509 | -1801.9181 | -53.74% | -36.7% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
29 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DE# | Not assigned | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 3036.9453 | 3084.2127 | 6121.158 | 1179.4048 | 1102 | 2281.4048 | -1982.2127 | -3839.7532 | -64.27% | -62.73% | N | N | non-unitized: This MAT has no measurable units because it is used to record other support costs for leak survey. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
30 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DE# | Not assigned | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 3036.9453 | 3084.2127 | 6121.158 | 1179.4048 | 1102 | 2281.4048 | -1982.2127 | -3839.7532 | -64.27% | -62.73% | N | N | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | N/A | N/A | N/A | N/A | N/A
31 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DE# | Not assigned | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 3036.9453 | 3084.2127 | 6121.158 | 1179.4048 | 1102 | 2281.4048 | -1982.2127 | -3839.7532 | -64.27% | -62.73% | N | N | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | N/A | N/A | N/A | N/A | N/A
32 | O&M Expense | Gas Distribution | DF | G&E T&D Locate and Mark | DFA | Locate and Mark | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 75271.7222 | 77495.6162 | 152767.3383 | 57525.8466 | 59562.5885 | 117088.4351 | -17933.0277 | -35678.9033 | -23.14% | -23.36% | Y | Y | # of Tickets | 863682 | 863682 | 1727364 | 611600 | 600706 | 1212306 | -262976 | -515058 | -30.45% | -29.82% | Y | Actual costs were lower than imputed imputed regulatory values due to the ticket increase from third-party driven work not materializing as expected. | Actual units were lower than imputed units due to the ticket increase from third-party driven work not materializing as expected. | Under | On-Target | Under | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2027 GRC periond. The purpose of this program is to field mark PG&E's underground facilities in response to 811 tickets as required by CA GC 4216.
33 | O&M Expense | Gas Distribution | DF | G&E T&D Locate and Mark | DFA | Locate and Mark | Loss of Containment on Gas Distribution Main or Service | LOCDM-C017 Locate and Mark - Distribution | Ex 3, Ch 8 | No | On-Going | Annual | 75271.7222 | 77495.6162 | 152767.3383 | 57524.8466 | 59562.5875 | 117087.4341 | -17933.0287 | -35679.9043 | -23.14% | -23.36% | N/A | N/A | N/A | 863682 | 863682 | 1727364 | 611600 | 600706 | 1212306 | -262976 | -515058 | -30.45% | -29.82% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
34 | O&M Expense | Gas Distribution | DF | G&E T&D Locate and Mark | DFB | Locate and Mark - Standby | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 447.9214 | 461.1552 | 909.0766 | 289.107 | 353.6488 | 642.7558 | -107.5064 | -266.3208 | -23.31% | -29.3% | N | N | # of times standby is required onsite | 642 | 642 | 1284 | 528 | 311.65 | 839.65 | -330.35 | -444.35 | -51.46% | -34.61% | Y | N/A | Actual units were lower than imputed units due to the ticket increase from third-party driven work not materializing as expected. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2027 GRC periond. The purpose of this program is to perform watch and protect activies when an excavator is operating in the vacinitiy of an underground critical facility.
35 | O&M Expense | Gas Distribution | DF | G&E T&D Locate and Mark | DFB | Locate and Mark - Standby | Loss of Containment on Gas Distribution Main or Service | LOCDM-C017 Locate and Mark - Distribution | Ex 3, Ch 8 | No | On-Going | Annual | 447.9214 | 461.1552 | 909.0766 | 288.107 | 353.6477 | 641.7548 | -107.5074 | -267.3218 | -23.31% | -29.41% | N/A | N/A | N/A | 642 | 642 | 1284 | 528 | 311.65 | 839.65 | -330.35 | -444.35 | -51.46% | -34.61% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
36 | O&M Expense | Gas Distribution | DF | G&E T&D Locate and Mark | DF# | Not assigned | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 2191.2173 | 2255.9565 | 4447.1737 | 2235.1451 | 2775.6593 | 5010.8044 | 519.7028 | 563.6307 | 23.04% | 12.67% | N | N | non-unitized: This MAT has no measurable units because it is used to record other support costs and fees for locate and mark. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2027 GRC periond. The purpose of this program is to perform watch and protect activies when an excavator is operating in the vacinitiy of an underground critical facility.
37 | O&M Expense | Gas Distribution | DF | G&E T&D Locate and Mark | DF# | Not assigned | Loss of Containment on Gas Distribution Main or Service | LOCDM-C017 Locate and Mark - Distribution | Ex 3, Ch 8 | No | On-Going | Annual | 2191.2173 | 2255.9565 | 4447.1737 | 0 | 2775.6593 | 2775.6593 | 519.7028 | -1671.5144 | 23.04% | -37.59% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
38 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGA | Cath Protect - Monitoring | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 4189.2806 | 4265.5739 | 8454.8545 | 5056.6783 | 5092.9976 | 10149.6759 | 827.4236 | 1694.8213 | 19.4% | 20.05% | N | N | # of monitoring points read (P/S reads) | 79622 | 79622 | 159244 | 97642 | 96906 | 194548 | 17284 | 35304 | 21.71% | 22.17% | Y | N/A | Actual units were higher than imputed units due to because imputed units were based on 2023 planned units that did not factor the increased units for the Electrically connected isolated steel(ECIS) Program that added ECIS monitoring units into SAP. | Over | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
39 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGA | Cath Protect - Monitoring | Loss of Containment on Gas Distribution Main or Service | LOCDM-C018 Distribution Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 4189.2806 | 4265.5739 | 8454.8545 | 5055.6783 | 5092.9966 | 10148.6749 | 827.4226 | 1693.8203 | 19.4% | 20.03% | N/A | N/A | N/A | 79622 | 79622 | 159244 | 97642 | 96906 | 194548 | 17284 | 35304 | 21.71% | 22.17% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
40 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGB | Cath Protect-Troubleshoot | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 5017.1741 | 5108.5447 | 10125.7189 | 7484.5753 | 8553.7191 | 16038.2944 | 3445.1744 | 5912.5756 | 67.44% | 58.39% | N | N | # of CPA's troubleshot | 14103 | 14103 | 28206 | 14872 | 16636 | 31508 | 2533 | 3302 | 17.96% | 11.71% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
41 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGB | Cath Protect-Troubleshoot | Loss of Containment on Gas Distribution Main or Service | LOCDM-C018 Distribution Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 5017.1741 | 5108.5447 | 10125.7189 | 7483.5753 | 8553.7181 | 16037.2934 | 3445.1734 | 5911.5746 | 67.44% | 58.38% | N/A | N/A | N/A | 14103 | 14103 | 28206 | 14872 | 16636 | 31508 | 2533 | 3302 | 17.96% | 11.71% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGC | Cath Protect - Rectifier Maint | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 633.2267 | 644.7587 | 1277.9854 | 1360.7235 | 804.4499 | 2165.1735 | 159.6912 | 887.1881 | 24.77% | 69.42% | N | N | # of Rectifiers Maintained | 3942 | 3942 | 7884 | 4060 | 4108 | 8168 | 166 | 284 | 4.211% | 3.602% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
43 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGC | Cath Protect - Rectifier Maint | Loss of Containment on Gas Distribution Main or Service | LOCDM-C018 Distribution Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 633.2267 | 644.7587 | 1277.9854 | 1359.7235 | 804.4489 | 2164.1725 | 159.6902 | 886.1871 | 24.77% | 69.34% | N/A | N/A | N/A | 3942 | 3942 | 7884 | 4060 | 4108 | 8168 | 166 | 284 | 4.211% | 3.602% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
44 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGD | Cath Protect - Resurvey | SRM Total | SRM Total | Ex 3, Ch 9 | No | 9 years | 8 | 3795.7013 | 3864.827 | 7660.5282 | 3570.7036 | 3463.7449 | 7034.4485 | -401.0821 | -626.0797 | -10.38% | -8.173% | N | N | non-unitized: This program has no measurable units because of the mixture of work, however, survey mileage is tracked to indicate overall program progress. Survey findings may lead to additional work in MAT DGB or MAT FII. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
45 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGD | Cath Protect - Resurvey | Loss of Containment on Gas Distribution Main or Service | LOCDM-M003 Enhanced CP Survey and Unprotected Main Evaluation | Ex 3, Ch 9 | No | 9 years | 8 | 3795.7013 | 3864.827 | 7660.5282 | 3569.7036 | 3463.7439 | 7033.4475 | -401.0831 | -627.0807 | -10.38% | -8.186% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
46 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGE | G:Isolated Steel Svc Evaluatn | SRM Total | SRM Total | Ex 3, Ch 9 | No | 9 years | 8 | 6548.2234 | 6667.4768 | 13215.7002 | 4084.4837 | 2904.5521 | 6989.0358 | -3762.9247 | -6226.6643 | -56.44% | -47.12% | N | N | non-unitized: This program has no measurable units because there are multiple aspects of the work including field survey, SAP record updates, and GIS mapping to complete the survey, however, service risers surveyed are tracked to indicate overall program progress. Survey findings may lead to additional work in MAT DGB or MAT FII. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
47 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGE | G:Isolated Steel Svc Evaluatn | Loss of Containment on Gas Distribution Main or Service | LOCDM-C022 Electrically Connected Isolated Steel Services | Ex 3, Ch 9 | No | 9 years | 8 | 6548.2234 | 6667.4768 | 13215.7002 | 4083.4837 | 2904.5511 | 6988.0348 | -3762.9257 | -6227.6653 | -56.44% | -47.12% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
48 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGG | Install casing test stations | SRM Total | SRM Total | Ex 3, Ch 9 | No | 8 years | 5 | 3249.6289 | 3308.8097 | 6558.4385 | 2496.5023 | 1068.0399 | 3564.5423 | -2240.7697 | -2993.8963 | -67.72% | -45.65% | N | N | # of Casing Test Stations Installed | 140 | 140 | 280 | 37 | 14 | 51 | -126 | -229 | -90% | -81.79% | Y | N/A | Actual units were lower than imputed units due to: 1) reprioritization in support of higher risk or compliance work; and 2) higher than expected unit costs due to the need for more detailed permit sketches to meet agency requirements, permitting and restoration costs, and increases in contract labor costs. | Under | Under | On-Target | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This program is to install casing test stations to support electrical isolation testing to meet the requirement of 49 CFR § 192.467 External corrosion control.
49 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGG | Install casing test stations | Loss of Containment on Gas Distribution Main or Service | LOCDM-C019 Casings | Ex 3, Ch 9 | No | 8 years | 5 | 3249.6289 | 3308.8097 | 6558.4385 | 2495.5023 | 1068.0389 | 3563.5413 | -2240.7707 | -2994.8973 | -67.72% | -45.66% | N/A | N/A | N/A | 140 | 140 | 280 | 37 | 14 | 51 | -126 | -229 | -90% | -81.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
50 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGH | Casing mitigate < than 100ft | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 4263.4941 | 4341.139 | 8604.6332 | 1911.81 | 703.3024 | 2615.1123 | -3637.8367 | -5989.5209 | -83.8% | -69.61% | N | N | # of Casings Mitigated | 33 | 33 | 66 | 12 | 6 | 18 | -27 | -48 | -81.82% | -72.73% | Y | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This program is to mitigate casings less than 40 feet to meet the requirement of 49 CFR § 192.467 External corrosion control.
51 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGH | Casing mitigate < than 100ft | Loss of Containment on Gas Distribution Main or Service | LOCDM-C019 Casings | Ex 3, Ch 9 | No | On-Going | Annual | 4263.4941 | 4341.139 | 8604.6332 | 1910.81 | 703.3014 | 2614.1113 | -3637.8377 | -5990.5219 | -83.8% | -69.62% | N/A | N/A | N/A | 33 | 33 | 66 | 12 | 6 | 18 | -27 | -48 | -81.82% | -72.73% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
52 | O&M Expense | Gas Distribution | EX | G Dist Meter Protection | EXB | MPP Protections | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 12709.0353 | 13133.4042 | 25842.4395 | 1006.3817 | 76.9891 | 1083.3708 | -13056.4151 | -24759.0687 | -99.41% | -95.81% | Y | Y | # of Locations | 15429 | 15429 | 30858 | 1255 | 0 | 1255 | -15429 | -29603 | -100% | -95.93% | Y | Actual costs were lower than imputed due to the reclassification of all Meter Protection Post installations from expense (MAT EXB) to capital (MAT 27A). | Actual units were lower than imputed units due to the reclassification of Meter Protection Post installations from Expense to Capital in addition to the delay of units to 2025-2026 | Under | Under | Under | Cancelled | MAT EXB formerly included the installtion of the Meter Protection Post ; however, this type of work is now being capitalized. Therefore, starting in 2024, this type of work is captured under MAT 27A.
53 | O&M Expense | Gas Distribution | EX | G Dist Meter Protection | EXB | MPP Protections | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C001 Meter Protection | Ex 3, Ch 8 | No | On-Going | Annual | 12709.0353 | 13133.4042 | 25842.4395 | 1005.3817 | 76.9881 | 1082.3698 | -13056.4161 | -24760.0697 | -99.41% | -95.81% | N/A | N/A | N/A | 15429 | 15429 | 30858 | 1255 | 0 | 1255 | -15429 | -29603 | -100% | -95.93% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
54 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGA | Gas Distribution Control Centr | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 8861.5069 | 9125.6869 | 17987.1938 | 4 | 7798.0317 | 7802.0317 | -1327.6552 | -10185.1621 | -14.55% | -56.62% | N | N | non-unitized: This MAT has no measurable units because it is used to record staffing related costs for Gas Distribution Control Center employees. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
55 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGA | Gas Distribution Control Centr | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C006 Gas Distribution Control Center Operations | Ex 3, Ch 11 | No | On-Going | Annual | 8861.5069 | 9125.6869 | 17987.1938 | 0 | 7798.0277 | 7798.0277 | -1327.6592 | -10189.1661 | -14.55% | -56.65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
56 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGA | Gas Distribution Control Centr | Insufficient Capacity to Meet Customer Demand | CPCTY-C001 Gas Distribution Control Center Operations | Ex 3, Ch 11 | No | On-Going | Annual | 8861.5069 | 9125.6869 | 17987.1938 | 1 | 7798.0287 | 7799.0287 | -1327.6582 | -10188.1651 | -14.55% | -56.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
57 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGA | Gas Distribution Control Centr | Loss of Containment on Gas Distribution Main or Service | LOCDM-C015 Gas Distribution Control Center Operations | Ex 3, Ch 11 | No | On-Going | Annual | 8861.5069 | 9125.6869 | 17987.1938 | 2 | 7798.0297 | 7800.0297 | -1327.6572 | -10187.1641 | -14.55% | -56.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
58 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGA | Gas Distribution Control Centr | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C014 Gas Distribution Control Center Operations | Ex 3, Ch 11 | No | On-Going | Annual | 8861.5069 | 9125.6869 | 17987.1938 | 3 | 7798.0307 | 7801.0307 | -1327.6562 | -10186.1631 | -14.55% | -56.63% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
59 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGB | Op Distr-G Mns/Svcs | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 968.0893 | 996.95 | 1965.0393 | 703.1888 | 655.53 | 1358.7188 | -341.42 | -606.3205 | -34.25% | -30.86% | N | N | non-unitized: This program has no measurable units because it encompasses a variety of different O&M activities. A count of the operations completed is captured in SAP. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
60 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGB | Op Distr-G Mns/Svcs | Loss of Containment on Gas Distribution Main or Service | LOCDM-C015 Gas Distribution Control Center Operations | Ex 3, Ch 11 | No | On-Going | Annual | 968.0893 | 996.95 | 1965.0393 | 702.1888 | 655.53 | 1357.7188 | -341.42 | -607.3205 | -34.25% | -30.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
61 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGC | Op Distr-G Reg Genl | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 180.2244 | 185.5973 | 365.8217 | 222.9603 | 134.4546 | 357.4149 | -51.1427 | -8.4068 | -27.56% | -2.298% | N | N | # of valves repaired/replaced | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
62 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGC | Op Distr-G Reg Genl | Loss of Containment on Gas Distribution Main or Service | LOCDM-C015 Gas Distribution Control Center Operations | Ex 3, Ch 11 | No | On-Going | Annual | 180.2244 | 185.5973 | 365.8217 | 221.9603 | 134.4536 | 356.4139 | -51.1437 | -9.4078 | -27.56% | -2.572% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
63 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHA | Maint-Prev-G Mains | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 2855.2508 | 2912.0449 | 5767.2957 | 1068.0082 | 1179.6821 | 2247.6903 | -1732.3628 | -3519.6054 | -59.49% | -61.03% | N | N | # Mains Maintained | 605 | 605 | 1210 | 192 | 165 | 357 | -440 | -853 | -72.73% | -70.5% | Y | N/A | Actual units lower than imputed due to unit delay for other higher priority work. Delayed units will be completed in 2025 and 2026. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to complete corrective maintenance on main distribution pipe lines < 100'.
64 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHA | Maint-Prev-G Mains | Loss of Containment on Gas Distribution Main or Service | LOCDM-C027 Preventive Maintenance Gas Mains | Ex 3, Ch 8 | No | On-Going | Annual | 2855.2508 | 2912.0449 | 5767.2957 | 1067.0082 | 1179.6811 | 2246.6893 | -1732.3638 | -3520.6064 | -59.49% | -61.04% | N/A | N/A | N/A | 605 | 605 | 1210 | 192 | 165 | 357 | -440 | -853 | -72.73% | -70.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
65 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHB | Maint-Prev-G Reg Sta | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 5161.5429 | 5264.2119 | 10425.7548 | 4396.4122 | 5698.302 | 10094.7142 | 434.0901 | -331.0405 | 8.246% | -3.175% | N | N | # Services Maintained | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
66 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHB | Maint-Prev-G Reg Sta | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C018 Distribution Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 5161.5429 | 5264.2119 | 10425.7548 | 4394.4122 | 5698.3 | 10092.7122 | 434.0881 | -333.0425 | 8.246% | -3.194% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
67 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHB | Maint-Prev-G Reg Sta | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C011 Distribution Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 5161.5429 | 5264.2119 | 10425.7548 | 4395.4122 | 5698.301 | 10093.7132 | 434.0891 | -332.0415 | 8.246% | -3.185% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
68 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHC | Maint-Prev-G Farm Tap | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 422.3104 | 430.7106 | 853.021 | 172.2999 | 349.9913 | 522.2912 | -80.7193 | -330.7298 | -18.74% | -38.77% | N | N | # of inspections completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
69 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHC | Maint-Prev-G Farm Tap | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C019 Farm Tap Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 422.3104 | 430.7106 | 853.021 | 170.2999 | 349.9893 | 520.2892 | -80.7213 | -332.7318 | -18.74% | -39.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
70 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHC | Maint-Prev-G Farm Tap | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C012 Farm Tap Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 422.3104 | 430.7106 | 853.021 | 171.2999 | 349.9903 | 521.2902 | -80.7203 | -331.7308 | -18.74% | -38.89% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
71 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHE | Maint-Prev-G Svcs | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 4808.3129 | 4903.9557 | 9712.2686 | 4348.9547 | 4194.99 | 8543.9447 | -708.9657 | -1168.3239 | -14.46% | -12.03% | N | N | # of Spans Mitigated | 2606 | 2606 | 5212 | 1656 | 1753 | 3409 | -853 | -1803 | -32.73% | -34.59% | Y | N/A | Actual units lower than imputed due to unit delay for other higher priority work. Delayed units will be completed in 2025 and 2026. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to complete corrective maintenance on services lines that do not include full service replacement.
72 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHE | Maint-Prev-G Svcs | Loss of Containment on Gas Distribution Main or Service | LOCDM-C023 Preventive Maintenance Gas Services | Ex 3, Ch 8 | No | On-Going | Annual | 4808.3129 | 4903.9557 | 9712.2686 | 4347.9547 | 4194.99 | 8542.9447 | -708.9657 | -1169.3239 | -14.46% | -12.04% | N/A | N/A | N/A | 2606 | 2606 | 5212 | 1656 | 1753 | 3409 | -853 | -1803 | -32.73% | -34.59% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
73 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHG | Maint-Prev-G Main Vlv | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 2503.6078 | 2553.4074 | 5057.0152 | 1463.3043 | 1487.5099 | 2950.8142 | -1065.8975 | -2106.201 | -41.74% | -41.65% | N | N | non-unitized: This program has no measurable units because it encompasses a variety of different O&M activities. A count of the operations completed is captured in SAP. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
74 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHG | Maint-Prev-G Main Vlv | Loss of Containment on Gas Distribution Main or Service | LOCDM-C026 Maintenance, Preventative, Gas Valves | Ex 3, Ch 8 | No | On-Going | Annual | 2503.6078 | 2553.4074 | 5057.0152 | 1462.3043 | 1487.5089 | 2949.8132 | -1065.8985 | -2107.202 | -41.74% | -41.67% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
75 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHI | Maint-Corr G Svc Valves | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 8267.1855 | 8431.6292 | 16698.8146 | 1905.797 | 5389.71 | 7295.507 | -3041.9192 | -9403.3076 | -36.08% | -56.31% | N | N | # of valves repaired/replaced | 32345 | 32345 | 64690 | 3045 | 9864 | 12909 | -22481 | -51781 | -69.5% | -80.04% | Y | N/A | Actual units lower than imputed due to unit delay for other higher priority work. Delayed units will be completed in 2025 and 2026. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace service valves < 2"
76 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHI | Maint-Corr G Svc Valves | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C011 Corrective Maintenance, Gas Service Valves | Ex 3, Ch 8 | No | On-Going | Annual | 8267.1855 | 8431.6292 | 16698.8146 | 1904.797 | 5389.71 | 7294.507 | -3041.9192 | -9404.3076 | -36.08% | -56.32% | N/A | N/A | N/A | 32345 | 32345 | 64690 | 3045 | 9864 | 12909 | -22481 | -51781 | -69.5% | -80.04% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
77 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHJ | Gas Non-Recurring Projects | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 3884.0044 | 3961.2617 | 7845.2661 | 1380.3384 | 1429.4887 | 2809.8271 | -2531.7729 | -5035.4389 | -63.91% | -64.18% | N | N | non-unitized: This MAT has no measurable units because it includes one‑time non‑recurring maintenance projects. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
78 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHJ | Gas Non-Recurring Projects | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C028 Preventive Maintenance Gas Valves | Ex 3, Ch 8 | No | On-Going | Annual | 3884.0044 | 3961.2617 | 7845.2661 | 1379.3384 | 1429.4878 | 2808.8261 | -2531.7739 | -5036.4399 | -63.91% | -64.2% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
79 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHK | GD Corrosion AC Inspections | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 145.3046 | 149.1743 | 294.4789 | 201.5149 | 108.2098 | 309.7247 | -40.9645 | 15.2458 | -27.46% | 5.177% | N | N | # of inspections completed | 461 | 461 | 922 | 597 | 454 | 1051 | -7 | 129 | -1.518% | 13.99% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
80 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHK | GD Corrosion AC Inspections | Loss of Containment on Gas Distribution Main or Service | LOCDM-C020 Atmospheric Corrosion, Mains and Services | Ex 3, Ch 9 | No | On-Going | Annual | 145.3046 | 149.1743 | 294.4789 | 200.5149 | 108.2088 | 308.7237 | -40.9655 | 14.2448 | -27.46% | 4.837% | N/A | N/A | N/A | 461 | 461 | 922 | 597 | 454 | 1051 | -7 | 129 | -1.518% | 13.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
81 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHL | Atmospheric Corsn Main Rep | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 3243.1871 | 3329.5597 | 6572.7468 | 2414.6908 | 1574.3474 | 3989.0382 | -1755.2123 | -2583.7087 | -52.72% | -39.31% | N | N | # of Riser Replacements & Service Spans | 145 | 145 | 290 | 143 | 73 | 216 | -72 | -74 | -49.66% | -25.52% | Y | N/A | Actual units were lower than imputed due to work pulled forward the previous year and job cancellation. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to maintain and re-coat facilities that have observed corrosion or have deteriorated coating.
82 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHL | Atmospheric Corsn Main Rep | Loss of Containment on Gas Distribution Main or Service | LOCDM-C020 Atmospheric Corrosion, Mains and Services | Ex 3, Ch 9 | No | On-Going | Annual | 3243.1871 | 3329.5597 | 6572.7468 | 2413.6908 | 1574.3464 | 3988.0372 | -1755.2133 | -2584.7097 | -52.72% | -39.32% | N/A | N/A | N/A | 145 | 145 | 290 | 143 | 73 | 216 | -72 | -74 | -49.66% | -25.52% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
83 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHM | Atmospheric Corsn Serv Rep | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 12498.84 | 12831.7092 | 25330.5492 | 3702.0644 | 5509.0262 | 9211.0906 | -7322.683 | -16119.4586 | -57.07% | -63.64% | N | Y | # of Riser Replacements & Service Spans | 56822 | 56822 | 113644 | 13229 | 18607 | 31836 | -38215 | -81808 | -67.25% | -71.99% | Y | Actual costs were lower than imputed due to reprioritization for higher priority/risk work. | Actual units were lower than imputed units due to reprioritized for higher priority/risk work. | Under | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
84 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHM | Atmospheric Corsn Serv Rep | Loss of Containment on Gas Distribution Main or Service | LOCDM-C020 Atmospheric Corrosion, Mains and Services | Ex 3, Ch 9 | No | On-Going | Annual | 12498.84 | 12831.7092 | 25330.5492 | 3701.0644 | 5509.0252 | 9210.0896 | -7322.684 | -16120.4596 | -57.07% | -63.64% | N/A | N/A | N/A | 56822 | 56822 | 113644 | 13229 | 18607 | 31836 | -38215 | -81808 | -67.25% | -71.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
85 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHN | Atmospheric Corsn Reg Stn Rprs | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 1050.6304 | 1078.6108 | 2129.2413 | 1747.6164 | 1246.0606 | 2993.6769 | 167.4497 | 864.4357 | 15.52% | 40.6% | N | N | # of Stations Mitigated | 60 | 60 | 120 | 51 | 30 | 81 | -30 | -39 | -50% | -32.5% | Y | N/A | Actual units were lower than imputed due to work pulled forward the previous year and job cancellation. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to maintain and re-coat facilities that have observed corrosion or have deteriorated coating.
86 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHN | Atmospheric Corsn Reg Stn Rprs | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C017 Facility Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 1050.6304 | 1078.6108 | 2129.2413 | 1746.6164 | 1246.0595 | 2992.6759 | 167.4487 | 863.4347 | 15.52% | 40.55% | N/A | N/A | N/A | 60 | 60 | 120 | 51 | 30 | 81 | -30 | -39 | -50% | -32.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
87 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHO | PM SCADA | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1501.4811 | 1531.3473 | 3032.8283 | 1135.3622 | 1244.5014 | 2379.8636 | -286.8458 | -652.9647 | -18.73% | -21.53% | N | N | non-unitized: This program has no measurable units because it encompasses a variety of different O&M activities. A count of the operations completed is captured in SAP. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
88 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHO | PM SCADA | Insufficient Capacity to Meet Customer Demand | CPCTY-C006 Distribution SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1501.4811 | 1531.3473 | 3032.8283 | 1132.3622 | 1244.4984 | 2376.8606 | -286.8488 | -655.9677 | -18.73% | -21.63% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
89 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHO | PM SCADA | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C017 Distribution SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1501.4811 | 1531.3473 | 3032.8283 | 1133.3622 | 1244.4994 | 2377.8616 | -286.8478 | -654.9667 | -18.73% | -21.6% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
90 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHO | PM SCADA | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C003 Distribution SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1501.4811 | 1531.3473 | 3032.8283 | 1134.3622 | 1244.5004 | 2378.8627 | -286.8468 | -653.9657 | -18.73% | -21.56% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
91 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHP | CM SCADA | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 776.843 | 792.2953 | 1569.1384 | 578.7979 | 643.6947 | 1222.4926 | -148.6007 | -346.6458 | -18.76% | -22.09% | N | N | non-unitized: This program has no measurable units because it encompasses a variety of different O&M activities. A count of the operations completed is captured in SAP. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
92 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHP | CM SCADA | Insufficient Capacity to Meet Customer Demand | CPCTY-C006 Distribution SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 776.843 | 792.2953 | 1569.1384 | 575.7979 | 643.6917 | 1219.4896 | -148.6037 | -349.6488 | -18.76% | -22.28% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
93 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHP | CM SCADA | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C017 Distribution SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 776.843 | 792.2953 | 1569.1384 | 576.7979 | 643.6927 | 1220.4906 | -148.6027 | -348.6478 | -18.76% | -22.22% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
94 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHP | CM SCADA | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C003 Distribution SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 776.843 | 792.2953 | 1569.1384 | 577.7979 | 643.6937 | 1221.4916 | -148.6017 | -347.6468 | -18.76% | -22.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
95 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHQ | GD Over Pressure Protectn Exp. | SRM Total | SRM Total | Ex 3, Ch 6 | No | 5 | 4 | 0 | 0 | 0 | 1057.3792 | 859.5179 | 1916.8971 | 859.5179 | 1916.8971 | 100% | 100% | N | N | non-unitized: This program has no measurable units because it encompasses a variety of different expense-related activities that are associated with the Overpressure Protection Program, like sulfur filter installations and minor sense line work on low pressure stations, in addition to conducting studies, emergency response to an overpressure event, and other miscellaneous activities. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
96 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHQ | GD Over Pressure Protectn Exp. | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-M003 GD Overpressure Protection | Ex 3, Ch 6 | No | 5 | 4 | 0 | 0 | 0 | 1056.3792 | 859.5169 | 1915.8961 | 859.5169 | 1915.8961 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
97 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHR | Distribution Pipeline Markers | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1852.6175 | 1889.4682 | 3742.0857 | 16.9692 | 75.212 | 92.1811 | -1814.2562 | -3649.9046 | -96.02% | -97.54% | N | N | non-unitized: This MAT has no measurable units because it is used for multiple work activities (e.g. distribution patrol and pipeline marker maintenance). | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
98 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHR | Distribution Pipeline Markers | Loss of Containment on Gas Distribution Main or Service | LOCDM-C017 Locate and Mark - Distribution | Ex 3, Ch 8 | No | On-Going | Annual | 1852.6175 | 1889.4682 | 3742.0857 | 15.9692 | 75.211 | 91.1801 | -1814.2572 | -3650.9056 | -96.02% | -97.56% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
99 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHS | GD One-Time Non-Recur Exp Pjts | SRM Total | SRM Total | N/A | No | On-Going | Annual | 0 | 0 | 0 | 1977.5283 | 0 | 1977.5283 | 0 | 1977.5283 | 0% | 100% | N | N | non-unitized: This MAT has no measurable units because it includes one‑time non‑recurring maintenance projects. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
100 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FH# | Not assigned | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1212.3067 | 1236.4209 | 2448.7276 | 760.9022 | 936.2351 | 1697.1373 | -300.1858 | -751.5903 | -24.28% | -30.69% | N | N | non-unitized: This MAT has no measurable units because it is used to record other support costs for the gas distribution system or can reflect standard cost variance. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
101 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FH# | Not assigned | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C018 Distribution Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1212.3067 | 1236.4209 | 2448.7276 | 759.9022 | 936.2341 | 1696.1363 | -300.1868 | -752.5913 | -24.28% | -30.73% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
102 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIB | Maint-Corr-G Reg Genl | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 2301.1064 | 2368.5142 | 4669.6207 | 1529.59 | 1795.9874 | 3325.5774 | -572.5268 | -1344.0432 | -24.17% | -28.78% | N | N | non-unitized: This program has no measurable units because it encompasses a variety of different O&M activities. A count of the operations completed is captured in SAP. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
103 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIB | Maint-Corr-G Reg Genl | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C018 Distribution Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 2301.1064 | 2368.5142 | 4669.6207 | 1527.59 | 1795.9854 | 3323.5754 | -572.5288 | -1346.0452 | -24.17% | -28.83% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
104 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIB | Maint-Corr-G Reg Genl | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C011 Distribution Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 2301.1064 | 2368.5142 | 4669.6207 | 1528.59 | 1795.9864 | 3324.5764 | -572.5278 | -1345.0442 | -24.17% | -28.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
105 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIC | Maint-Corr-G Farm Tap | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 995.0182 | 1024.1659 | 2019.1842 | 141.9053 | 163.1803 | 305.0855 | -860.9857 | -1714.0986 | -84.07% | -84.89% | N | N | # of Main Leaks Repaired (non-NERBA) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
106 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIC | Maint-Corr-G Farm Tap | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C019 Farm Tap Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 995.0182 | 1024.1659 | 2019.1842 | 139.9053 | 163.1782 | 303.0835 | -860.9877 | -1716.1006 | -84.07% | -84.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
107 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIC | Maint-Corr-G Farm Tap | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C012 Farm Tap Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 995.0182 | 1024.1659 | 2019.1842 | 140.9053 | 163.1792 | 304.0845 | -860.9867 | -1715.0996 | -84.07% | -84.94% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
108 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIF | Maint-Corr-G Main Vlv | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 395.2436 | 406.8218 | 802.0654 | 1027.1477 | 750.2145 | 1777.3623 | 343.3928 | 975.2969 | 84.41% | 121.6% | N | N | # Svc Leak Repairs_AG | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
109 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIF | Maint-Corr-G Main Vlv | Loss of Containment on Gas Distribution Main or Service | LOCDM-C024 Corrective Maintenance, Gas, Main Valve | Ex 3, Ch 8 | No | On-Going | Annual | 395.2436 | 406.8218 | 802.0654 | 1026.1477 | 750.2135 | 1776.3612 | 343.3918 | 974.2959 | 84.41% | 121.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
110 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIG/ LWG (a) | Maint-Corr-G Main Lk | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 35095.9718 | 35680.4333 | 70776.4051 | 35102.5885 | 32775 | 67877.5885 | -2905.4333 | -2898.8166 | -8.143% | -4.096% | N | N | # of corrosion tags cleared | 3828 | 3828 | 7656 | 2592 | 2459 | 5051 | -1369 | -2605 | -35.76% | -34.03% | Y | Actual costs were lower than imputed due to decreased leak find rates in the last three years resulting in reduced leak finds and repairs. A second factor driving cost down is the implementation of process improvement initiatives such as leak bundling. | Actual units lower than imputed due to decreased leak find rates in the last three years resulting in reduced leak finds and repairs | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to repair gradeable leaks on distribution main lines.
111 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIG/ LWG (a) | Maint-Corr-G Main Lk | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 35095.9718 | 35680.4333 | 70776.4051 | 35102.5885 | 32775 | 67877.5885 | -2905.4333 | -2898.8166 | -8.143% | -4.096% | N/A | N/A | N/A | 3828 | 3828 | 7656 | 2592 | 2459 | 5051 | -1369 | -2605 | -35.76% | -34.03% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
112 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIH | Maint-Corr_G_Svc Leak_AG | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 4097.634 | 4165.8729 | 8263.5069 | 2696.9242 | 2693.28 | 5390.2042 | -1472.5929 | -2873.3028 | -35.35% | -34.77% | N | N | # of Main Dig-ins Repaired | 7838 | 7838 | 15676 | 2044 | 1726 | 3770 | -6112 | -11906 | -77.98% | -75.95% | Y | N/A | Actual units lower than imputed due to decreased leak find rates in the last three years resulting in reduced leak finds and repairs | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to repair above ground gradeable leaks.
113 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIH | Maint-Corr_G_Svc Leak_AG | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 4097.634 | 4165.8729 | 8263.5069 | 2697.9242 | 2693.28 | 5391.2042 | -1472.5929 | -2872.3028 | -35.35% | -34.76% | N/A | N/A | N/A | 7838 | 7838 | 15676 | 2044 | 1726 | 3770 | -6112 | -11906 | -77.98% | -75.95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
114 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIH | Maint-Corr_G_Svc Leak_AG | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 4097.634 | 4165.8729 | 8263.5069 | 2698.9242 | 2693.28 | 5392.2042 | -1472.5929 | -2871.3028 | -35.35% | -34.75% | N/A | N/A | N/A | 7838 | 7838 | 15676 | 2044 | 1726 | 3770 | -6112 | -11906 | -77.98% | -75.95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
115 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FII | Maint-Corr-G Cath Prot | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 6233.1691 | 6341.376 | 12574.5451 | 2699.9242 | 8860.48 | 11560.4042 | 2519.104 | -1014.1409 | 39.72% | -8.065% | N | N | # of Main Dig-ins Repaired | 7838 | 5375 | 13213 | 2044 | 2555 | 4599 | -2820 | -8614 | -52.47% | -65.19% | Y | N/A | Actual units were less than imputed due to less work materialized than what was planned. | Under | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
116 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FII | Maint-Corr-G Cath Prot | Loss of Containment on Gas Distribution Main or Service | LOCDM-C018 Distribution Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 6233.1691 | 6341.376 | 12574.5451 | 7351.0475 | 8860.48 | 16211.5275 | 2519.104 | 3636.9824 | 39.72% | 28.92% | N/A | N/A | N/A | 5375 | 5375 | 10750 | 1364 | 2555 | 3919 | -2820 | -6831 | -52.47% | -63.54% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
117 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FII | Maint-Corr-G Cath Prot | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C018 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 6233.1691 | 6341.376 | 12574.5451 | 7352.0475 | 8860.48 | 16212.5275 | 2519.104 | 3637.9824 | 39.72% | 28.93% | N/A | N/A | N/A | 5375 | 5375 | 10750 | 1364 | 2555 | 3919 | -2820 | -6831 | -52.47% | -63.54% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
118 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIJ | Maint-Corr G Main Dig-in | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 995.6968 | 1012.2784 | 2007.9752 | 1277.8729 | 3039.13 | 4317.0029 | 2026.8516 | 2309.0277 | 200.2% | 115% | N | N | # of Main Dig-ins Repaired | 298 | 298 | 596 | 158 | 161 | 319 | -137 | -277 | -45.97% | -46.48% | Y | N/A | Actual units lower than imputed due to improved performance in dig-in prevention activities resulting in decreased volume of 3rd party damages. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to fix distribution main pipeline damages caused by 3rd parties and includes expense pipe replacements < 100' of pipe
119 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIJ | Maint-Corr G Main Dig-in | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 995.6968 | 1012.2784 | 2007.9752 | 1278.8729 | 3039.13 | 4318.0029 | 2026.8516 | 2310.0277 | 200.2% | 115% | N/A | N/A | N/A | 298 | 298 | 596 | 158 | 161 | 319 | -137 | -277 | -45.97% | -46.48% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
120 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIK | Maint-Corr G Svc Dig-in | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 1595.9294 | 1622.5068 | 3218.4363 | 2084.2267 | 1713.1621 | 3797.3888 | 90.6553 | 578.9526 | 5.587% | 17.99% | N | N | # of Svc Dig-ins Repaired | 1617 | 1617 | 3234 | 1221 | 1305 | 2526 | -312 | -708 | -19.29% | -21.89% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to fix service damages caused by 3rd parties and includes expense repairs to services.
121 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIK | Maint-Corr G Svc Dig-in | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 1595.9294 | 1622.5068 | 3218.4363 | 2085.2267 | 1713.1631 | 3798.3898 | 90.6563 | 579.9536 | 5.587% | 18.02% | N/A | N/A | N/A | 1617 | 1617 | 3234 | 1221 | 1305 | 2526 | -312 | -708 | -19.29% | -21.89% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
122 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIM | Major Event-Distribution Gas | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 490.2497 | 498.4139 | 988.6636 | 185.5336 | 116.8002 | 302.3338 | -381.6138 | -686.3299 | -76.57% | -69.42% | N | N | # Services Repaired | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | Over | On-Target | Emergent | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to perform emergency response work related to a major event such as fire, storm, earthquakes, etc.
123 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIM | Major Event-Distribution Gas | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C009 Major Event - Distribution Gas | Ex 3, Ch 10 | No | On-Going | Annual | 490.2497 | 498.4139 | 988.6636 | 186.5336 | 116.8012 | 303.3347 | -381.6128 | -685.3289 | -76.57% | -69.32% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
124 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIM | Major Event-Distribution Gas | Insufficient Capacity to Meet Customer Demand | CPCTY-C007 Operate Transmission Regulator Station | Ex 3, Ch 10 | No | On-Going | Annual | 490.2497 | 498.4139 | 988.6636 | 187.5336 | 116.8022 | 304.3358 | -381.6118 | -684.3279 | -76.57% | -69.22% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
125 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIM | Major Event-Distribution Gas | Insufficient Capacity to Meet Customer Demand | CPCTY-C008 Major Event - Distribution Gas | Ex 3, Ch 10 | No | On-Going | Annual | 490.2497 | 498.4139 | 988.6636 | 188.5336 | 116.8032 | 305.3367 | -381.6108 | -683.3269 | -76.57% | -69.12% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
126 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIM | Major Event-Distribution Gas | Loss of Containment on Gas Distribution Main or Service | LOCDM-C008 Major Event - Distribution Gas | Ex 3, Ch 10 | No | On-Going | Annual | 490.2497 | 498.4139 | 988.6636 | 189.5336 | 116.8042 | 306.3378 | -381.6098 | -682.3259 | -76.56% | -69.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
127 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIM | Major Event-Distribution Gas | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C013 Major Event - Distribution Gas | Ex 3, Ch 10 | No | On-Going | Annual | 490.2497 | 498.4139 | 988.6636 | 190.5336 | 116.8052 | 307.3388 | -381.6088 | -681.3249 | -76.56% | -68.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
128 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIM | Major Event-Distribution Gas | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C013 Major Event - Distribution Gas | Ex 3, Ch 10 | No | On-Going | Annual | 490.2497 | 498.4139 | 988.6636 | 191.5336 | 116.8062 | 308.3397 | -381.6078 | -680.3239 | -76.56% | -68.81% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
129 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIO | Gas Overbuild - G | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-Going | Annual | 853.884 | 868.1419 | 1722.0259 | 765.65 | 2506.2 | 3271.85 | 1638.0581 | 1549.8241 | 188.7% | 90% | N | N | # Svc Leak Repairs_BG (non-NERBA) | 19 | 76 | 95 | 42.75 | 139 | 181.75 | 63 | 86.75 | 82.89% | 91.32% | Y | N/A | Actual units were hihger than imputed due to the Encroachment program is based on find-it-fix-it work that needs to be field verified to determine capital or expense scope. More work was field verified as expense encroachments (partial service replacement and/or less than 100' of main relocation based on overbuilt gas pipe) than imputed. | Over | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to relocation of partial gas service and/or main (<100') to clear overbuild conflicts. For the remainder of the GRC cycle, PG&E will prioritize this work and execute within six months of identification (subject to extension with notification to regulators).
130 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIO | Gas Overbuild - G | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C002 Encroachment Program | Ex 3, Ch 4 | Yes | On-Going | Annual | 213.47 | 868.1419 | 1081.6119 | 766.65 | 2506.2 | 3272.85 | 1638.0581 | 2191.2381 | 188.7% | 202.6% | N/A | N/A | N/A | 19 | 76 | 95 | 42.75 | 139 | 181.75 | 63 | 86.75 | 82.89% | 91.32% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
131 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIO | Gas Overbuild - G | Loss of Containment on Gas Distribution Main or Service | LOCDM-C009 Encroachment Program | Ex 3, Ch 4 | Yes | On-Going | Annual | 640.43 | 868.1419 | 1508.5719 | 767.65 | 2506.2 | 3273.85 | 1638.0581 | 1765.2781 | 188.7% | 117% | N/A | N/A | N/A | 19 | 76 | 95 | 42.75 | 139 | 181.75 | 63 | 86.75 | 82.89% | 91.32% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
132 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIP/ LWH (a) | Maint-Corr_G_Svc Leak_BG | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 31649.4275 | 32176.4929 | 63825.9205 | 27892.7822 | 27819 | 55711.7822 | -4357.4929 | -8114.1383 | -13.54% | -12.71% | N | N | # Locations Inspected | 7484 | 7484 | 14968 | 4509 | 4024 | 8533 | -3460 | -6435 | -46.23% | -42.99% | Y | Actual costs were lower than imputed due to decreased leak find rates in the last three years resulting in reduced leak finds and repairs. A second factor driving cost down is the implementation of process improvement initiatives such as leak bundling. | Actual units lower than imputed due to decreased leak find rates in the last three years resulting in reduced leak finds and repairs | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to complete expense repairs of gradeable leaks on service lines.
133 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIP/ LWH (a) | Maint-Corr_G_Svc Leak_BG | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 31649.4275 | 32176.4929 | 63825.9205 | 27892.7822 | 27819 | 55711.7822 | -4357.4929 | -8114.1383 | -13.54% | -12.71% | N/A | N/A | N/A | 7484 | 7484 | 14968 | 4509 | 4024 | 8533 | -3460 | -6435 | -46.23% | -42.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
134 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIQ | Atmospheric Corrosion Monitorg | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 1356.0955 | 1378.6789 | 2734.7744 | 456.6 | 1245.17 | 1701.77 | -133.5089 | -1033.0044 | -9.684% | -37.77% | N | N | # Tee Caps Replaced | 7762 | 15524 | 23286 | 16754 | 44477 | 61231 | 28953 | 37945 | 186.5% | 163% | Y | N/A | Actual units were higher than imputed due to Covid and post Covid challenges to access of our gas meters resulting in more AC CGI's (can't get In). | Over | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
135 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIQ | Atmospheric Corrosion Monitorg | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C017 Atmospheric Corrosion, Metersets | Ex 3, Ch 10 | No | On-Going | Annual | 678.05 | 1378.6789 | 2056.7289 | 457.6 | 1245.17 | 1702.77 | -133.5089 | -353.9589 | -9.684% | -17.21% | N/A | N/A | N/A | 7762 | 15524 | 23286 | 16754 | 44477 | 61231 | 28953 | 37945 | 186.5% | 163% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
136 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIQ | Atmospheric Corrosion Monitorg | Loss of Containment on Gas Distribution Main or Service | LOCDM-C020 Atmospheric Corrosion, Mains and Services | Ex 3, Ch 10 | No | On-Going | Annual | 678.05 | 1378.6789 | 2056.7289 | 458.6 | 1245.17 | 1703.77 | -133.5089 | -352.9589 | -9.684% | -17.16% | N/A | N/A | N/A | 7762 | 15524 | 23286 | 16754 | 44477 | 61231 | 28953 | 37945 | 186.5% | 163% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
137 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIR | Tee-Cap Replacement Program | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-Going | Annual | 2209.0109 | 2245.8964 | 4454.9073 | 2039.4798 | 2356.3288 | 4395.8086 | 110.4324 | -59.0987 | 4.917% | -1.327% | N | N | # of Meters Repaired | 1165 | 1165 | 2330 | 1196 | 1165 | 2361 | 0 | 31 | 0% | 1.33% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
138 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIR | Tee-Cap Replacement Program | Loss of Containment on Gas Distribution Main or Service | LOCDM-C010 Tee Cap Replacement Program | Ex 3, Ch 4 | No | On-Going | Annual | 2209.0109 | 2245.8964 | 4454.9073 | 2040.4798 | 2356.3298 | 4396.8096 | 110.4334 | -58.0977 | 4.917% | -1.304% | N/A | N/A | N/A | 1165 | 1165 | 2330 | 1196 | 1165 | 2361 | 0 | 31 | 0% | 1.33% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
139 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIS | Leak Survey Meter Repair | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 9658.4871 | 9819.3322 | 19477.8193 | 8214.6477 | 8067.05 | 16281.6977 | -1752.2822 | -3196.1216 | -17.85% | -16.41% | N | N | # of Meters Repaired | 80000 | 80000 | 160000 | 56458 | 43188 | 99646 | -36812 | -60354 | -46.02% | -37.72% | Y | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | On-Target | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
140 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIS | Leak Survey Meter Repair | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 9658.4871 | 9819.3322 | 19477.8193 | 8215.6477 | 8067.05 | 16282.6977 | -1752.2822 | -3195.1216 | -17.85% | -16.4% | N/A | N/A | N/A | 80000 | 80000 | 160000 | 56458 | 43188 | 99646 | -36812 | -60354 | -46.02% | -37.72% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
141 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FI# | Not assigned | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 4148.9624 | 4218.0561 | 8367.0185 | 1726.6783 | 1640 | 3366.6783 | -2578.0561 | -5000.3403 | -61.12% | -59.76% | N | N | non-unitized: This MAT has no measurable units because it is used to record other support costs for corrective maintenance such as leak repair. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
142 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FI# | Not assigned | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 4148.9624 | 4218.0561 | 8367.0185 | 1726.6783 | 1640 | 3366.6783 | -2578.0561 | -5000.3403 | -61.12% | -59.76% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
143 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FI# | Not assigned | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 4148.9624 | 4218.0561 | 8367.0185 | 1726.6783 | 1640 | 3366.6783 | -2578.0561 | -5000.3403 | -61.12% | -59.76% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
144 | O&M Expense | Gas Distribution | GF | Gas Trans & Dist Sys Mapping | GFO | Mapping Support-Distribution | SRM Total | SRM Total | Ex 3, Ch 13 | No | On-Going | Annual | 4307.388 | 4414.517 | 8721.9049 | 4573.2335 | 3192.04 | 7765.2735 | -1222.477 | -956.6314 | -27.69% | -10.97% | N | N | non-unitized: This MAT has no measurable units because it is primarily used by Gas Distribution mappers for performing work that is not billable to orders, including: map correction notifications from the Corrective Action Program (CAP), map delineation requests, request for work notifications (RWs), operating diagrams, Gas Distribution Geographic Information System (GD-GIS) corrections, data requests, and mapping tasks on orders that are financially closed. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
145 | O&M Expense | Gas Distribution | GF | Gas Trans & Dist Sys Mapping | GFQ | GT&D Data Management | SRM Total | SRM Total | N/A | No | On-Going | Annual | 0 | 0 | 0 | 673.7231 | 1613.89 | 2287.6131 | 1613.89 | 2287.6131 | 0% | 100% | N | N | non-unitized: This MAT has no measurable units because it is primarily intended for Gas data enhancements in GD-GIS, Palantir Foundry implementation for Gas to enable data analysis, discrepancy identification and correction across core systems of record (i.e. GD-GIS and SAP), and Gas data maturity work in alignment with company data management standards. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
146 | O&M Expense | Gas Distribution | GG | Gas Trans & Dist Sys Modeling | GGA | Gas System Planning_GSO | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 6923.6213 | 7162.3092 | 14085.9305 | 4934.0604 | 4857.8334 | 9791.8938 | -2304.4758 | -4294.0367 | -32.18% | -30.48% | N | N | non-unitized: This MAT has no measurable units because it is used to record labor costs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
147 | O&M Expense | Gas Distribution | GG | Gas Trans & Dist Sys Modeling | GGA | Gas System Planning_GSO | Insufficient Capacity to Meet Customer Demand | CPCTY-C003 Gas System Planning | Ex 3, Ch 11 | No | On-Going | Annual | 6923.6213 | 7162.3092 | 14085.9305 | 4935.0604 | 4857.8344 | 9792.8948 | -2304.4748 | -4293.0357 | -32.18% | -30.48% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
148 | O&M Expense | Gas Distribution | GG | Gas Trans & Dist Sys Modeling | GG# | Not assigned | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 2522.9469 | 2609.9241 | 5132.871 | 1 | 0 | 1 | -2609.9241 | -5131.871 | -100% | -99.98% | N | N | non-unitized: This MAT has no measurable units because it is used to record labor costs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeeding as Planned | Due to a change in accounting, this MAT is no longer used to charge non-project specific engineering time to and those costs will be recorded as Non-Billable Labor (NBL) overhead instead.
149 | O&M Expense | Gas Distribution | GG | Gas Trans & Dist Sys Modeling | GG# | Not assigned | Insufficient Capacity to Meet Customer Demand | CPCTY-C004 Gas Distribution Portfolio Management and Engineering | Ex 3, Ch 11 | No | On-Going | Annual | 2522.9469 | 2609.9241 | 5132.871 | 0 | 0 | 0 | -2609.9241 | -5132.871 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
150 | O&M Expense | Gas Distribution | GM | Manage Energy Efficiency-NonBA | GMC | GD LNG/CNG Station | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-Going | Annual | 4592.6857 | 4670.9148 | 9263.6005 | 3452.7256 | 3070.7792 | 6523.5048 | -1600.1356 | -2740.0957 | -34.26% | -29.58% | N | N | # of Meters Remediated | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
151 | O&M Expense | Gas Distribution | GM | Manage Energy Efficiency-NonBA | GMC | GD LNG/CNG Station | Loss of Containment on CNG Station Equipment | CNGEQ-C002 Gas Distribution LNG/CNG Station O&M | Ex 3, Ch 6 | No | On-Going | Annual | 4592.6857 | 4670.9148 | 9263.6005 | 3453.7256 | 3070.7802 | 6524.5058 | -1600.1346 | -2739.0947 | -34.26% | -29.57% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
152 | O&M Expense | Gas Distribution | HY | Change/Maint Used Gas Meters | HYI | G Meter Atmospheric Corrosion | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 920.493 | 952.2265 | 1872.7195 | 787.4238 | 788.425 | 1575.8488 | -163.8015 | -296.8707 | -17.2% | -15.85% | N | N | # of Meters Remediated | 16077 | 16077 | 32154 | 0 | 8094 | 8094 | -7983 | -24060 | -49.65% | -74.83% | Y | N/A | Actual units were lower than imputed units due to a reduction in incoming workload due to fewer identified instances of Atmospheric Corrosion. | On-Target | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
153 | O&M Expense | Gas Distribution | HY | Change/Maint Used Gas Meters | HYI | G Meter Atmospheric Corrosion | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C008 Meter Set Atmospheric Corrosion Remediation | Ex 3, Ch 8 | No | On-Going | Annual | 920.493 | 952.2265 | 1872.7195 | 788.4238 | 788.426 | 1576.8498 | -163.8005 | -295.8697 | -17.2% | -15.8% | N/A | N/A | N/A | 16077 | 16077 | 32154 | 0 | 8094 | 8094 | -7983 | -24060 | -49.65% | -74.83% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
154 | O&M Expense | Gas Distribution | HY | Change/Maint Used Gas Meters | HY# | Not assigned | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 0 | 0 | 0 | 5.5846 | 0 | 5.5846 | 0 | 5.5846 | 0% | 100% | N | N | non-unitized: This MAT has no measurable units because it reflects standard cost variance related to field services provider cost centers. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
155 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQA | DIMP Leak Survey | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 861.2795 | 886.2255 | 1747.505 | 842.4522 | 578.2278 | 1420.68 | -307.9977 | -326.825 | -34.75% | -18.7% | N | N | # of Inspections | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
156 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQA | DIMP Leak Survey | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 861.2795 | 886.2255 | 1747.505 | 843.4522 | 578.2288 | 1421.681 | -307.9967 | -325.824 | -34.75% | -18.65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
157 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQC | Mark and Locate Program | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 3581.9039 | 3673.3146 | 7255.2185 | 3089.9506 | 3237.3108 | 6327.2614 | -436.0039 | -927.9572 | -11.87% | -12.79% | N | N | Fittings Mitigated | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
158 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQC | Mark and Locate Program | Loss of Containment on Gas Distribution Main or Service | LOCDM-C025 Dig-In Reduction Team | Ex 3, Ch 8 | No | On-Going | Annual | 3581.9039 | 3673.3146 | 7255.2185 | 3090.9506 | 3237.3118 | 6328.2624 | -436.0029 | -926.9562 | -11.87% | -12.78% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
159 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQD | DIMP Emergent Work | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-Going | Annual | 4162.1311 | 4284.7357 | 8446.8668 | 75.5711 | 1279.6 | 1355.1711 | -3005.1357 | -7091.6958 | -70.14% | -83.96% | N | N | non-unitized: This program has no measurable units because DIMP emergent work consists of work resulting from risk analysis and operational events. This work includes laboratory analysis, engineering, and incident investigations. Projects vary considerably and are not comparable so this work is not unitized. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
160 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQD | DIMP Emergent Work | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C005 DIMP Emergent Work | Ex 3, Ch 4 | No | On-Going | Annual | 208.1066 | 4284.7357 | 4492.8423 | 76.5711 | 1279.6 | 1356.1711 | -3005.1357 | -3136.6712 | -70.14% | -69.81% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
161 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQD | DIMP Emergent Work | Loss of Containment on Gas Distribution Main or Service | LOCDM-C011 DIMP Emergent Work | Ex 3, Ch 4 | No | On-Going | Annual | 3954.0246 | 4284.7357 | 8238.7603 | 77.5711 | 1279.6 | 1357.1711 | -3005.1357 | -6881.5892 | -70.14% | -83.53% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
162 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQE | Plastic Program | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-Going | Annual | 330.7923 | 340.5365 | 671.3288 | 168.8791 | 46.3957 | 215.2748 | -294.1408 | -456.054 | -86.38% | -67.93% | N | N | non-unitized: This program has no measurable units because it oversees selecting, testing, and development of plastic materials, tools and construction methods for PG&E’s plastic gas distribution system. Projects vary considerably and are not comparable so this work is not unitized. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
163 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQE | Plastic Program | Loss of Containment on Gas Distribution Main or Service | LOCDM-C012 Plastics Program | Ex 3, Ch 4 | No | On-Going | Annual | 330.7923 | 340.5365 | 671.3288 | 169.8791 | 46.3967 | 216.2758 | -294.1398 | -455.053 | -86.38% | -67.78% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
164 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQG | Fitting Mitigation Program | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-Going | Annual | 2431.5304 | 2503.1564 | 4934.6868 | 1983.518 | 521.3428 | 2504.8608 | -1981.8136 | -2429.8261 | -79.17% | -49.24% | N | N | Fittings Mitigated | 480 | 480 | 960 | 139 | 0 | 139 | -480 | -821 | -100% | -85.52% | Y | N/A | Actual units were lower than imputed units because MAT JQG consists of the Metfit and Kerotest fitting mitigation programs. The Metfit program is not unitized and the unitized Kerotest work has been delayed indefinitely. No Kerotest fittings were mitigated in 2024. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to focus on removal of compression-style mechanical fittings with risk of corrosion, failure, and leak. For the remainder of the GRC cycle, PG&E anticipates that this program will continue to be lower priority than other work in Gas Distribution.
165 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQG | Fitting Mitigation Program | Loss of Containment on Gas Distribution Main or Service | LOCDM-M005 Fitting Mitigation Program | Ex 3, Ch 4 | No | On-Going | Annual | 2431.5304 | 2503.1564 | 4934.6868 | 1984.518 | 521.3438 | 2505.8618 | -1981.8126 | -2428.8251 | -79.17% | -49.22% | N/A | N/A | N/A | 480 | 480 | 960 | 139 | 0 | 139 | -480 | -821 | -100% | -85.52% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
166 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQK | Cross Bored Sewer Project | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-Going | Annual | 13294.7392 | 13686.3645 | 26981.1037 | 13438.3777 | 6031.8131 | 19470.1907 | -7654.5514 | -7510.9129 | -55.93% | -27.84% | N | Y | # of Inspections | 19313 | 19313 | 38626 | 8085 | 3655 | 11740 | -15658 | -26886 | -81.07% | -69.61% | Y | Actual costs were lower than imputed costs due to reprioritization in support of higher risk or compliance work. | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is locate and repair legacy crossbores.
167 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQK | Cross Bored Sewer Project | Loss of Containment on Gas Distribution Main or Service | LOCDM-M006 Cross Bored Sewer Project | Ex 3, Ch 4 | No | On-Going | Annual | 13294.7392 | 13686.3645 | 26981.1037 | 13439.3777 | 6031.8141 | 19471.1917 | -7654.5504 | -7509.9119 | -55.93% | -27.83% | N/A | N/A | N/A | 19313 | 19313 | 38626 | 8085 | 3655 | 11740 | -15658 | -26886 | -81.07% | -69.61% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
168 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQL | DIMP Program Management | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-Going | Annual | 4868.1104 | 5011.5111 | 9879.6215 | 6.5947 | 158.68 | 165.2747 | -4852.8311 | -9714.3468 | -96.83% | -98.33% | N | N | non-unitized: This MAT has no measurable units because it is used to record labor costs and is not used to measure gas plant units repaired or replaced. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | Actual costs were lower than imputed due to DIMP labor cost being transitioned to OM/OS in 2021. | N/A | Under | Under | On-Target | Cancelled | Cancelled due to DIMP labor cost being transitioned to OM/OS in 2021.
169 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQL | DIMP Program Management | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C010 DIMP Program Management | Ex 3, Ch 4 | Yes | On-Going | Annual | 243.4055 | 5011.5111 | 5254.9166 | 7.5947 | 158.68 | 166.2747 | -4852.8311 | -5088.6419 | -96.83% | -96.84% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
170 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQL | DIMP Program Management | Loss of Containment on Gas Distribution Main or Service | LOCDM-C021 DIMP Program Management | Ex 3, Ch 4 | Yes | On-Going | Annual | 4624.7049 | 5011.5111 | 9636.216 | 8.5947 | 158.68 | 167.2747 | -4852.8311 | -9468.9412 | -96.83% | -98.26% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
171 | O&M Expense | Gas Distribution | OM | Operational Management | OM# | Not assigned | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 13 | No | On-Going | Annual | 13394.3553 | 13773.499 | 27167.8543 | 21468.7997 | 18764.1575 | 40232.9572 | 4990.6585 | 13065.1029 | 36.23% | 48.09% | N | N | non-unitized: This MAT has no measurable units because it is used to record labor and employee‑related costs to provide supervision and management support. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | Actual costs were lower than imputed regulatory values due to higher OM/OS allocation of supervision and management labor costs. MWC OM/OS represents labor costs to supervise or manage PG&E personnel who charge their time directly to orders, net of overhead allocations applied between capital and expense. The overhead is applied to both MWC OM and MWC OS, which represents labor costs in support of personnel. Due to a higher starting point in overall costs, driven by a mixture of different resources, and updated allocations a lower amount remained recorded in expense MWC OM/OS. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to capture supervision and management support costs.
(a) Includes below ground grade 3 leak repairs recorded under Leak Abatement MWC LW.

## GD SRM MAT Table Capital
Table 2-4 2024 RSAR 2023 GRC CYCLE GAS DISTRIBUTION CAPITAL COMPARISON BY MAT FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
.
| A | B | C1 | C2 | C3 | C4 | C5 | C6 | C7 | D | E | F | G1 | G2 | G3 | H1 | H2 | H3 | I1 | I2 | J1 | J2 | K | L | M | N1 | N2 | N3 | O1 | O2 | O3 | P1 | P2 | Q 2024 | Q2 | R | S | T | U1 | U2 | U3 | V | W
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name | MAT | MAT Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program/ Project Life (years) | Program/ Project Year | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs | Imputed Costs for 2023 GRC Cycle to date($) (G1+G2) | 2023 Actual Costs | 2024 Actual Costs | Actual Costs for 2023 GRC Cycle to date($) (H1+H2) | Difference for 2024 ($) (H2-G2) | Difference for 2023 GRC Cycle to Date ($) (H3-G3) | Spending Percent Variance for 2024 (%) ((H-G)/G*100) | Spending Percent Variance for 2023 GRC Cycle (%) ((H3-G3)/G3*100) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | Unit Type | 2023 Imputed Adopted Units | 2024 Imputed Adopted Units | Imputed Units for 2023 GRC Cycle to Date (N2+N1) | 2023 Actual Units | 2024 Actual Units | Actual Units for 2023 GRC Cycle to Date (O2+O1) | Difference for 2024 (# of Units) (O2-N2) | Difference for 2023 GRC Cycle to Date (# of Units)​ (O3-N3) | Unit Percent Variance for 2024 (%) ((O2-N2)/N2*100) | Unit Percent Variance for 2023 GRC Cycle to Date (%)​ ((O3-N3)/N3) | Unit Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | 2024 Unit Variance Explanation | Forecast Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T) | Status | Completion Status Statement
1 | Capital | Gas Distribution | 14 | G Dist Pipeline Repl Program | 14A | Pipeline Repl Pgm-Mains & Svcs | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 102467.7272 | 103701.0957 | 206168.8229 | 97303.4542 | 108139.8325 | 205443.2867 | 4438.7368 | -725.5361 | 4.28% | -0.3519% | N | N | Feet of main | 128832 | 128832 | 257664 | 93523 | 112647 | 206170 | -16185 | -51494 | -12.56% | -19.98% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period
2 | Capital | Gas Distribution | 14 | G Dist Pipeline Repl Program | 14A | Pipeline Repl Pgm-Mains & Svcs | Loss of Containment on Gas Distribution Main or Service | LOCDM-M001 Pipeline Replacement Program (Steel) | Ex 3, Ch 4 | No | On-going | Annual | 102467.7272 | 103701.0957 | 206168.8229 | 97302.4542 | 108139.8325 | 205442.2867 | 4438.7368 | -726.5361 | 4.28% | -0.3524% | N/A | N/A | N/A | 128832 | 128832 | 257664 | 93523 | 112647 | 206170 | -16185 | -51494 | -12.56% | -19.98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | Capital | Gas Distribution | 14 | G Dist Pipeline Repl Program | 14B | Copper Service Replacements | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 0 | 0 | 0 | 758.817 | 208.5084 | 967.3254 | 208.5084 | 967.3254 | 100% | 100% | N | N | # of services replaced | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0% | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
4 | Capital | Gas Distribution | 14 | G Dist Pipeline Repl Program | 14B | Copper Service Replacements | Loss of Containment on Gas Distribution Main or Service | LOCDM-M007 Copper Service Replacements | Ex 3, Ch 4 | No | On-going | Annual | 0 | 0 | 0 | 757.817 | 208.5084 | 966.3254 | 208.5084 | 966.3254 | 100% | 100% | N/A | N/A | N/A | 0 | - | N/A | 2 | 0 | 2 | N/A | N/A | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | Capital | Gas Distribution | 14 | G Dist Pipeline Repl Program | 14D | Plastic Pipe Replace_Main/Svc | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 407664.7895 | 412571.7092 | 820236.4987 | 372666.7336 | 398172.1975 | 770838.9311 | -14399.5117 | -49397.5676 | -3.49% | -6.022% | N | N | Feet of main | 733920 | 733920 | 1467840 | 444837 | 563665 | 1008502 | -170255 | -459338 | -23.2% | -31.29% | Y | N/A | Actual units were lower than imputed due to units target required a unit cost of $562/ft. Program was able to complete the 2024 portfolio with a unit cost of $706/ft. As such, we did not have sufficient funding to complete the imputed units. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to pre-1985 Aldyl-A and related plastic pipe.
6 | Capital | Gas Distribution | 14 | G Dist Pipeline Repl Program | 14D | Plastic Pipe Replace_Main/Svc | Loss of Containment on Gas Distribution Main or Service | LOCDM-M002 Pipeline Replacement Program (Plastic) | Ex 3, Ch 4 | No | On-going | Annual | 407664.7895 | 412571.7092 | 820236.4987 | 372665.7336 | 398172.1975 | 770837.9311 | -14399.5117 | -49398.5676 | -3.49% | -6.022% | N/A | N/A | N/A | 733920 | 733920 | 1467840 | 444837 | 563665 | 1008502 | -170255 | -459338 | -23.2% | -31.29% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 | Capital | Gas Distribution | 27 | Gas Meter Protection-Capital | 27A | Meter Protection-Capital | SRM Total | SRM Total | Ex 3, Ch 8 | Yes | On-going | Annual | 5475.6773 | 5541.6 | 11017.2773 | 245.4286 | 7031.8 | 7277.2286 | 1490.2 | -3740.0487 | 26.89% | -33.95% | N | N | # of service replacements | 7.36 | 184 | 191.36 | 3.56 | 2991 | 2994.56 | 2807 | 2803.2 | 1526% | 1465% | Y | N/A | Actual units were higher than imputed due to the reclassification of Meter Protection Post installations from Expense (MAT EXB) to Capital (MAT 27A). | Over | Over | On-Target | Expanded | MAT 27A now includes the installtion of Meter Protection Work (MPP), previously captured as expense with MAT EXB. Additionally, this MAT also captures costs related to full service relocations due to service meters at risk of vehicular damage not possible to protect via MPP, or unaccessible service valves.
8 | Capital | Gas Distribution | 27 | Gas Meter Protection-Capital | 27A | Meter Protection-Capital | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C001 Meter Protection | Ex 3, Ch 8 | Yes | On-going | Annual | 219.0271 | 221.7 | 440.7271 | 121.7143 | 281.272 | 402.9863 | 59.572 | -37.7408 | 26.87% | -8.563% | N/A | N/A | N/A | 7.36 | 184 | 191.36 | 3.56 | 2991 | 2994.56 | 2807 | 2803.2 | 1526% | 1465% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 | Capital | Gas Distribution | 27 | Gas Meter Protection-Capital | 27A | Meter Protection-Capital | Loss of Containment on Gas Distribution Main or Service | LOCDM-C001 Meter Protection | Ex 3, Ch 8 | Yes | On-going | Annual | 5256.6502 | 5319.9 | 10576.5502 | 123.7143 | 6750.528 | 6874.2423 | 1430.628 | -3702.3079 | 26.89% | -35% | N/A | N/A | N/A | 7.36 | 184 | 191.36 | 3.56 | 2991 | 2994.56 | 2807 | 2803.2 | 1526% | 1465% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10 | Capital | Gas Distribution | 2K | G Dist Repl/Convert Cust HPR | 2K (a) | Cust HPR Reg Sta Convert Main | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 18630.5544 | 17329.1714 | 35959.7258 | 17329.1714 | 35959.7258 | 100% | 100% | N | Y | # of HPRs | 0 | 0 | 0 | 73 | 88 | 161 | 88 | 161 | 100% | N/A | Y | Actual costs were higher than imputed due to program having no adopted funding in the 2023 GRC. However, program was deemed important and continued to be performed by Gas Operations | Actual units were higher than imputed due to Program having no adopted funding in the 2023 GRC. However, program was deemed important and continued to be performed by Gas Operations | Over | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's GRC period. The purpose of this program is to replace or remove out of spec HPR reg sets to improve reliability and safety. This program will continue to be a lower priority as fewer units remain in the system.
11 | Capital | Gas Distribution | 2K | G Dist Repl/Convert Cust HPR | 2K (a) | Cust HPR Reg Sta Convert Main | 'Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-M005 HPR Replacement | Ex 3, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 18630.5544 | 17329.1714 | 35959.7258 | 17329.1714 | 35959.7258 | 100% | 100% | N/A | N/A | N/A | 0 | 0 | 0 | 73 | 88 | 161 | 88 | 161 | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | Capital | Gas Distribution | 2K | G Dist Repl/Convert Cust HPR | 2K (a) | Cust HPR Reg Sta Convert Main | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M002 HPR Replacement | Ex 3, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 18630.5544 | 17329.1714 | 35959.7258 | 17329.1714 | 35959.7258 | 100% | 100% | N/A | N/A | N/A | 0 | 0 | 0 | 73 | 88 | 161 | 88 | 161 | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | Capital | Gas Distribution | 31 | NGV - Station Infrastructure | 31A | 31A-LNG/CNG Stations | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 4889.4942 | 4948.3474 | 9837.8416 | 3490.6997 | 4512.0681 | 8002.7678 | -436.2793 | -1835.0739 | -8.817% | -18.65% | N | N | non-unitized: This MAT has no measurable units because it is used to record costs for CNG station upgrades. The type of upgrades performed at stations are not comparable. | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
14 | Capital | Gas Distribution | 31 | NGV - Station Infrastructure | 31A | 31A-LNG/CNG Stations | Loss of Containment on CNG Station Equipment | CNGEQ-C001 GV-Station Infrastructure | Ex 3, Ch 6 | No | On-going | Annual | 4889.4942 | 4948.3474 | 9837.8416 | 3489.6997 | 4512.0681 | 8001.7678 | -436.2793 | -1836.0739 | -8.817% | -18.66% | N/A | N/A | N/A | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | Capital | Gas Distribution | 47 | G Dist Capacity | 47B | Cons/Acq New Fac-G-Cap-Mains | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 35760.9508 | 36191.393 | 71952.3438 | 20683.0323 | 8749.0644 | 29432.0967 | -27442.3286 | -42520.2471 | -75.83% | -59.1% | Y | Y | feet of main installed | 46200 | 46200 | 92400 | 11612 | 13621 | 25233 | -32579 | -67167 | -70.52% | -72.69% | Y | Actual costs were lower than imputed due to reprioritization of funds to higher risk work. | Actual Units were lower than imputed due to reprioritization of funds to higher risk work. | Under | On-Target | Under | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to ensure sufficient gas capacity as determined by system planning.
16 | Capital | Gas Distribution | 47 | G Dist Capacity | 47B | Cons/Acq New Fac-G-Cap-Mains | Insufficient Capacity to Meet Customer Demand | CPCTY-C009 Construct/Acquire New Facilities - Gas - Capital Mains | Ex 3, Ch 11 | No | On-going | Annual | 35760.9508 | 36191.393 | 71952.3438 | 20682.0323 | 8749.0644 | 29431.0967 | -27442.3286 | -42521.2471 | -75.83% | -59.1% | N/A | N/A | N/A | 46200 | 46200 | 92400 | 11612 | 13621 | 25233 | -32579 | -67167 | -70.52% | -72.69% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17 | Capital | Gas Distribution | 47 | G Dist Capacity | 47C | Cons/Acq New Fac-G-Cap-RegSta | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 5881.9291 | 5952.7279 | 11834.657 | 923.8518 | 598.3589 | 1522.2107 | -5354.369 | -10312.4464 | -89.95% | -87.14% | N | N | # of reg stations addressed | 3 | 3 | 6 | 1 | 2 | 3 | -1 | -3 | -33.33% | -50% | Y | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to rebuild/replace capacity driven distribution regulator stations.
18 | Capital | Gas Distribution | 47 | G Dist Capacity | 47C | Cons/Acq New Fac-G-Cap-RegSta | Insufficient Capacity to Meet Customer Demand | CPCTY-C010 Construct/Acquire New Facilities - Gas Capital Regulator Sta | Ex 3, Ch 11 | No | On-going | Annual | 5881.9291 | 5952.7279 | 11834.657 | 922.8518 | 598.3589 | 1521.2107 | -5354.369 | -10313.4464 | -89.95% | -87.15% | N/A | N/A | N/A | 3 | 3 | 6 | 1 | 2 | 3 | -1 | -3 | -33.33% | -50% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19 | Capital | Gas Distribution | 47 | G Dist Capacity | 47D | Cons/Acq New Fac-G-Cap-ReplReg | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 128.6485 | 130.197 | 258.8455 | 367.3599 | 249.66 | 617.0199 | 119.463 | 358.1744 | 91.76% | 138.4% | N | N | # of Reg station components | 4 | 4 | 8 | 6 | 0 | 6 | -4 | -2 | -100% | -25% | Y | N/A | Actual units were lower than imputed units due to a need for redesign on the one planned project, which includes all four units, causing adjusted completion forecast of 2025 for these 4 units. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace capacity driven valves/filters in distribution regulator stations.
20 | Capital | Gas Distribution | 47 | G Dist Capacity | 47D | Cons/Acq New Fac-G-Cap-ReplReg | Insufficient Capacity to Meet Customer Demand | CPCTY-C011 Construct/Acquire New Facilities - Gas Capital Replace Regul | Ex 3, Ch 11 | No | On-going | Annual | 128.6485 | 130.197 | 258.8455 | 366.3599 | 249.66 | 616.0199 | 119.463 | 357.1744 | 91.76% | 138% | N/A | N/A | N/A | 4 | 4 | 8 | 6 | 0 | 6 | -4 | -2 | -100% | -25% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | Capital | Gas Distribution | 47 | G Dist Capacity | 47F | Cons/Acquire New Fac G-Cap-Oth | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 58.9754 | 59.6852 | 118.6606 | 9.0343 | 19.8113 | 28.8456 | -39.8739 | -89.815 | -66.81% | -75.69% | N | N | non-unitized: This MAT has no measurable units because it is used to record capacity related costs that are not captured by any other MAT. | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
22 | Capital | Gas Distribution | 47 | G Dist Capacity | 47F | Cons/Acquire New Fac G-Cap-Oth | Insufficient Capacity to Meet Customer Demand | CPCTY-C012 Construct/Acquire New Facilities - Gas Capital Other | Ex 3, Ch 11 | No | On-going | Annual | 58.9754 | 59.6852 | 118.6606 | 8.0343 | 19.8113 | 27.8456 | -39.8739 | -90.815 | -66.81% | -76.53% | N/A | N/A | N/A | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
23 | Capital | Gas Distribution | 4A | G Dist Ctrl Operations Assets | 4AF | ERX Pressure Monitoring-6 | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 530.5182 | 536.9039 | 1067.4221 | 376.7331 | 1462.4123 | 1839.1454 | 925.5085 | 771.7233 | 172.4% | 72.3% | N | N | # of Electronic pressure recorders installed | 10 | 10 | 20 | 0 | 7 | 7 | -3 | -13 | -30% | -65% | Y | N/A | Actual units were lower than imputed due to a reduction in total units because of high actual costs of completed projects. Costs at reg stations are much higher due to permits, easements and work required to complete projects. | Under | On-Target | On-Target | Proceeding as planned | This program is on going and will continue until no SCADA installations are required for system visability.
24 | Capital | Gas Distribution | 4A | G Dist Ctrl Operations Assets | 4AF | ERX Pressure Monitoring-6 | Insufficient Capacity to Meet Customer Demand | CPCTY-M005 SCADA Service Monitor | Ex 3, Ch 11 | No | On-going | Annual | 530.5182 | 536.9039 | 1067.4221 | 375.7331 | 1462.4123 | 1838.1454 | 925.5085 | 770.7233 | 172.4% | 72.2% | N/A | N/A | N/A | 10 | 10 | 20 | 0 | 7 | 7 | -3 | -13 | -30% | -65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
25 | Capital | Gas Distribution | 4A | G Dist Ctrl Operations Assets | 4AF | ERX Pressure Monitoring-6 | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-M006 SCADA Service Monitor | Ex 3, Ch 11 | No | On-going | Annual | 530.5182 | 536.9039 | 1067.4221 | 377.7331 | 1462.4123 | 1840.1454 | 925.5085 | 772.7233 | 172.4% | 72.39% | N/A | N/A | N/A | 10 | 10 | 20 | 0 | 7 | 7 | -3 | -13 | -30% | -65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
26 | Capital | Gas Distribution | 4A | G Dist Ctrl Operations Assets | 4AF | ERX Pressure Monitoring-6 | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M005 SCADA Service Monitor | Ex 3, Ch 11 | No | On-going | Annual | 530.5182 | 536.9039 | 1067.4221 | 378.7331 | 1462.4123 | 1841.1454 | 925.5085 | 773.7233 | 172.4% | 72.49% | N/A | N/A | N/A | 10 | 10 | 20 | 0 | 7 | 7 | -3 | -13 | -30% | -65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
27 | Capital | Gas Distribution | 4A | G Dist Ctrl Operations Assets | 4AM | Reg Stat Mntr Dual No Flow-3 | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 0 | 0 | 0 | 11317.3585 | 7298.991 | 18616.3496 | 7298.991 | 18616.3496 | 100% | 100% | N | N | # of remote terminal units installed | 0 | - | N/A | 27 | 34 | 61 | N/A | N/A | 100% | N/A | Y | N/A | Actual units were higher than imputed due to program having no adopted units in the 2023 GRC. However, program was deemed important and continued to be performed by Gas Operations. | Over | On-Target | On-Target | Proceeding as planned | This program is on going and will continue until no SCADA installations are required for system visability.
28 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50F | Impr Rel/Dep Gas Other Equip | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 487.9761 | 493.8497 | 981.8258 | 1194.8606 | 1758.9183 | 2953.7788 | 1265.0686 | 1971.953 | 256.2% | 200.8% | N | N | non-unitized: This MAT has no measurable units because units of measure such as number of deactivated services, valves, and mains are not comparable. | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
29 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50F | Impr Rel/Dep Gas Other Equip | Loss of Containment on Gas Distribution Main or Service | LOCDM-C005 Improve Reliability/Dependability - Gas Other Equipment | Ex 3, Ch 4 | No | On-going | Annual | 487.9761 | 493.8497 | 981.8258 | 1193.8606 | 1758.9183 | 2952.7788 | 1265.0686 | 1970.953 | 256.2% | 200.7% | N/A | N/A | N/A | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
30 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50I | Impr Rel/Dep-Deac Only-M/R/V | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 8924.1659 | 9031.583 | 17955.7489 | 10240.5205 | 9219.5867 | 19460.1072 | 188.0037 | 1504.3583 | 2.082% | 8.378% | N | N | non-unitized: This MAT has no measurable units because units of measure such as number of deactivated services, valves, and mains are not comparable. | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
31 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50I | Impr Rel/Dep-Deac Only-M/R/V | Loss of Containment on Gas Distribution Main or Service | LOCDM-C007 Improve ReM/R/V | Ex 3, Ch 4 | No | On-going | Annual | 8924.1659 | 9031.583 | 17955.7489 | 10239.5205 | 9219.5867 | 19459.1072 | 188.0037 | 1503.3583 | 2.082% | 8.373% | N/A | N/A | N/A | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
32 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50N | GD Over Pressure Protection | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 10260.3774 | 6764.8005 | 17025.1779 | 6764.8005 | 17025.1779 | 100% | 100% | N | N | # of secondary OPP installed | 0 | - | N/A | 68 | 60 | 128 | N/A | N/A | 100% | N/A | Y | #N/A | Actual units were higher than imputed due to Program having no adopted funding in the 2023 GRC. However, program was deemed important and continued to be performed by Gas Operations. | Over | On-Target | On-Target | Proceeding as planned | This program is ongoing to install over pressure protection at regulator stations.
33 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50N | GD Over Pressure Protection | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-M003 GD Overpressure Protection | Ex 3, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 10259.3774 | 6764.8005 | 17024.1779 | 6764.8005 | 17024.1779 | 100% | 100% | N/A | N/A | N/A | 0 | - | N/A | 68 | 60 | 128 | N/A | N/A | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
34 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50B | Impr Rel/Dep - Gas Services | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 12094.9319 | 12240.5143 | 24335.4462 | 25006.9426 | 20884.4298 | 45891.3724 | 8643.9155 | 21555.9262 | 70.62% | 88.58% | N | N | # of services replaced | 427 | 427 | 854 | 608 | 571 | 1179 | 144 | 325 | 33.72% | 38.06% | Y | N/A | Actual units were higher than imputed due to significantly more service replacements executed under MAT 50B due to emergent other corrective and compliance work. This includes copper service replacements, shallow/exposed services, and other corrective gas service replacements. | Over | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace gas services due to deterioration or reduced reliability (including corrosion, copper services, exposed/shallow services). For the remainder of the GRC cycle, PG&E will prioritize compliance-driven service replacements due to atmospheric corrosion.
35 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50B | Impr Rel/Dep - Gas Services | Loss of Containment on Gas Distribution Main or Service | LOCDM-C003 Improve Reliability/System Dependability - Gas Services | Ex 3, Ch 4 | No | On-going | Annual | 12094.9319 | 12240.5143 | 24335.4462 | 25005.9426 | 20884.4298 | 45890.3724 | 8643.9155 | 21554.9262 | 70.62% | 88.57% | N/A | N/A | N/A | 427 | 427 | 854 | 608 | 571 | 1179 | 144 | 325 | 33.72% | 38.06% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
36 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50D | Impr Rel/Dep Gas CP Systems | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 1383.4625 | 1400.1148 | 2783.5773 | 1291.9819 | 1894.0557 | 3186.0376 | 493.9409 | 402.4603 | 35.28% | 14.46% | N | N | # of Rectifiers Replaced (50D) | 80 | 80 | 160 | 11 | 82 | 93 | 2 | -67 | 2.5% | -41.88% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | Regarding the coating work in 50D - this program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to maintain and re-coat facilities that have observed corrosion or have deteriorated coating.
37 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50D | Impr Rel/Dep Gas CP Systems | Loss of Containment on Gas Distribution Main or Service | LOCDM-C018 Distribution Corrosion Control Program | Ex 3, Ch 9 | No | On-going | Annual | 1383.4625 | 1400.1148 | 2783.5773 | 1290.9819 | 1894.0557 | 3185.0376 | 493.9409 | 401.4603 | 35.28% | 14.42% | N/A | N/A | N/A | 80 | 80 | 160 | 11 | 82 | 93 | 2 | -67 | 2.5% | -41.88% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
38 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50H | Impr Rel/Dep-CutOff Idle G Svc | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 3160.9599 | 3199.0072 | 6359.9671 | 3925.998 | 5622.3895 | 9548.3875 | 2423.3823 | 3188.4204 | 75.75% | 50.13% | N | N | # of cut off idle services | 313 | 313 | 626 | 215 | 295 | 510 | -18 | -116 | -5.751% | -18.53% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
39 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50H | Impr Rel/Dep-CutOff Idle G Svc | Loss of Containment on Gas Distribution Main or Service | LOCDM-C006 Improve Reliability/System Dependability - Cut-Off Idle Gas | Ex 3, Ch 4 | No | On-going | Annual | 3160.9599 | 3199.0072 | 6359.9671 | 3924.998 | 5622.3895 | 9547.3875 | 2423.3823 | 3187.4204 | 75.75% | 50.12% | N/A | N/A | N/A | 313 | 313 | 626 | 215 | 295 | 510 | -18 | -116 | -5.751% | -18.53% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
40 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50G/3PB (b) | Impr Rel/Dep-Gas Svc Repl Leak | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-going | Annual | 14809.3646 | 14988 | 29797.3646 | 24303.9804 | 20037 | 44340.9803 | 5049 | 14543.6157 | 33.69% | 48.81% | N | N | # of services replaced (NERBA BG Grade 3 unit) | 978 | 978 | 1956 | 1036 | 877 | 1913 | -101 | -43 | -10.33% | -2.198% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
41 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50G/3PB (b) | Impr Rel/Dep-Gas Svc Repl Leak | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-going | Annual | 14809.3646 | 14988 | 29797.3646 | 24302.9804 | 20037 | 44339.9803 | 5049 | 14542.6157 | 33.69% | 48.81% | N/A | N/A | N/A | 978 | 978 | 1956 | 1036 | 877 | 1913 | -101 | -43 | -10.33% | -2.198% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50A | Impr Rel/ Dep - Gas Mains | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 52051.0914 | 52677.6123 | 104728.7037 | 47052.57 | 55122.2757 | 102174.8457 | 2444.6634 | -2553.858 | 4.641% | -2.439% | N | N | Feet of main | 79200 | 79200 | 158400 | 50495 | 65082 | 115577 | -14118 | -42823 | -17.83% | -27.03% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period
43 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50A | Impr Rel/ Dep - Gas Mains | Loss of Containment on Gas Distribution Main or Service | LOCDM-C002 Improve Reliability/System Dependability - Gas Main | Ex 3, Ch 4 | No | On-going | Annual | 52051.0914 | 52677.6123 | 104728.7037 | 47051.57 | 55122.2757 | 102173.8457 | 2444.6634 | -2554.858 | 4.641% | -2.44% | N/A | N/A | N/A | 79200 | 79200 | 158400 | 50495 | 65082 | 115577 | -14118 | -42823 | -17.83% | -27.03% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
44 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50R | Rep/Inst EmerShtdwn&SafeOpsVal | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 5775.7869 | 5845.308 | 11621.0948 | 3245.4239 | 7060.1728 | 10305.5967 | 1214.8648 | -1315.4982 | 20.78% | -11.32% | N | N | # of valves installed | 100 | 100 | 200 | 36 | 76 | 112 | -24 | -88 | -24% | -44% | Y | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to install new valves, 2 inch or greater in size.
45 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50R | Rep/Inst EmerShtdwn&SafeOpsVal | Loss of Containment on Gas Distribution Main or Service | LOCDM-M004 New Valve Installations | Ex 3, Ch 4 | No | On-going | Annual | 5775.7869 | 5845.308 | 11621.0948 | 3244.4239 | 7060.1728 | 10304.5967 | 1214.8648 | -1316.4982 | 20.78% | -11.33% | N/A | N/A | N/A | 100 | 100 | 200 | 36 | 76 | 112 | -24 | -88 | -24% | -44% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
46 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50P | ImprRelb/SysDepd-G-DpWellAnode | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 17989.1148 | 18205.6435 | 36194.7583 | 14506.1367 | 12898.4571 | 27404.5939 | -5307.1864 | -8790.1644 | -29.15% | -24.29% | N | N | # of Groundbeds Installed | 65 | 65 | 130 | 58 | 43 | 101 | -22 | -29 | -33.85% | -22.31% | Y | N/A | Actual units were lower than imputed units due to lower planned units and the delayed construction activities to claim the unit in the year. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to install impressed current ground bed to mitigate the threat of external corrosion (49 CFR Subpart I, Requirement for Corrosion Control).
47 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50P | ImprRelb/SysDepd-G-DpWellAnode | Loss of Containment on Gas Distribution Main or Service | LOCDM-C018 Distribution Corrosion Control Program | Ex 3, Ch 9 | No | On-going | Annual | 17989.1148 | 18205.6435 | 36194.7583 | 14505.1367 | 12898.4571 | 27403.5939 | -5307.1864 | -8791.1644 | -29.15% | -24.29% | N/A | N/A | N/A | 65 | 65 | 130 | 58 | 43 | 101 | -22 | -29 | -33.85% | -22.31% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
48 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50K | Emergent Leaking Main Replace | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-going | Annual | 5757.345 | 5826.6442 | 11583.9892 | 2558.077 | 4941.2833 | 7499.3603 | -885.3609 | -4084.6289 | -15.2% | -35.26% | N | N | feet of main installed | 7707 | 7707 | 15414 | 1947 | 4907 | 6854 | -2800 | -8560 | -36.33% | -55.53% | Y | N/A | Actual units lower than imputted due to decreased leak find rates in the last three years resulting in reduced leaks qualifying for main pipe replacements > 100' | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to fix gradeable leaks by replacing >100' of main distribution pipeline.
49 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50K | Emergent Leaking Main Replace | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-going | Annual | 5757.345 | 5826.6442 | 11583.9892 | 2557.077 | 4941.2833 | 7498.3603 | -885.3609 | -4085.6289 | -15.2% | -35.27% | N/A | N/A | N/A | 7707 | 7707 | 15414 | 1947 | 4907 | 6854 | -2800 | -8560 | -36.33% | -55.53% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
50 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50J | Gas Overbuild - G | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 16738.3637 | 16939.8376 | 33678.2013 | 21050.6232 | 16515.05 | 37565.6733 | -424.7875 | 3887.472 | -2.508% | 11.54% | N | N | # of services replaced | 578 | 578 | 1156 | 462 | 348 | 810 | -230 | -346 | -39.79% | -29.93% | Y | N/A | Actual units were less than imputed due to the Encroachment program is based on find-it-fix-it work that needs to be field verified to determine capital or expense scope. Less work was field verified as capital encroachments (full service replacement and/or greater than 100' of main relocation based on overbuilt gas pipe) than imputed. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to relocate gas main (>100 continuous feet) and/or complete gas service replacements to clear overbuild conflicts. For the remainder of the GRC cycle, PG&E will prioritize this work and execute within six months of identification (subject to extension with notification to regulators).
51 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50J | Gas Overbuild - G | Loss of Containment on Gas Distribution Main or Service | LOCDM-C009 Encroachment Program | Ex 3, Ch 4 | No | On-going | Annual | 16738.3637 | 16939.8376 | 33678.2013 | 21049.6232 | 16515.05 | 37564.6733 | -424.7875 | 3886.472 | -2.508% | 11.54% | N/A | N/A | N/A | 578 | 578 | 1156 | 462 | 348 | 810 | -230 | -346 | -39.79% | -29.93% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
52 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50E | Impr Rel/Dep Gas Valves | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 5775.7869 | 5845.308 | 11621.0948 | 10230.83 | 4916.8981 | 15147.7281 | -928.4099 | 3526.6333 | -15.88% | 30.35% | N | N | # of valves replaced | 100 | 100 | 200 | 74 | 58 | 132 | -42 | -68 | -42% | -34% | Y | N/A | Actual units were lower than imputed units as PG&E performed fewer find-it/fix-it valve replacements than expected. This is because the find rate was lower compared to previous years. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace the existing valves, 2 inch or greater in size.
53 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50E | Impr Rel/Dep Gas Valves | Loss of Containment on Gas Distribution Main or Service | LOCDM-C004 Improve Reliability/Dependability - Gas Valves | Ex 3, Ch 4 | No | On-going | Annual | 5775.7869 | 5845.308 | 11621.0948 | 10229.83 | 4916.8981 | 15146.7281 | -928.4099 | 3525.6333 | -15.88% | 30.34% | N/A | N/A | N/A | 100 | 100 | 200 | 74 | 58 | 132 | -42 | -68 | -42% | -34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
54 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50L | Impr Rel Dep Gas Reg Component | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 10669.2951 | 10797.7177 | 21467.0127 | 13724.2722 | 11002.8427 | 24727.1149 | 205.1251 | 3260.1021 | 1.9% | 15.19% | N | N | # of Reg station components | 150 | 150 | 300 | 130 | 85 | 215 | -65 | -85 | -43.33% | -28.33% | Y | N/A | Actual units were lower than imputed units because unit costs were higher than expected (for example, some projects could only be completed at night, with higher labor costs). | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace valves and filters in distribution regulator stations.
55 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50L | Impr Rel Dep Gas Reg Component | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C009 Gas Distribution Reg Station Component Replacements | Ex 3, Ch 6 | No | On-going | Annual | 10669.2951 | 10797.7177 | 21467.0127 | 13723.2722 | 11002.8427 | 24726.1149 | 205.1251 | 3259.1021 | 1.9% | 15.18% | N/A | N/A | N/A | 150 | 150 | 300 | 130 | 85 | 215 | -65 | -85 | -43.33% | -28.33% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
56 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50L | Impr Rel Dep Gas Reg Component | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C010 Gas Distribution Reg Station Component Replacements | Ex 3, Ch 6 | No | On-going | Annual | 10669.2951 | 10797.7177 | 21467.0127 | 13725.2722 | 11002.8427 | 24728.1149 | 205.1251 | 3261.1021 | 1.9% | 15.19% | N/A | N/A | N/A | 150 | 150 | 300 | 130 | 85 | 215 | -65 | -85 | -43.33% | -28.33% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
57 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50C | Impr Rel/Dep Gas Regulation | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 49887.2427 | 50487.7181 | 100374.9609 | 45584.3776 | 36695.0629 | 82279.4405 | -13792.6552 | -18095.5204 | -27.32% | -18.03% | N | Y | # of Reg stations | 25 | 25 | 50 | 16 | 14 | 30 | -11 | -20 | -44% | -40% | Y | Actual costs were lower than imputed costs due to reprioritization in support of higher risk or compliance work. (Unit costs were higher due increased costs of construction and scope of work in 2024 projects) | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work.(Unit costs were higher due increased costs of construction and scope of work in 2024 projects) | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to rebuild/replace distribution regulator stations.
58 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50C | Impr Rel/Dep Gas Regulation | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C008 Gas Distribution Reg Station Rebuild | Ex 3, Ch 6 | No | On-going | Annual | 49887.2427 | 50487.7181 | 100374.9609 | 45583.3776 | 36695.0629 | 82278.4405 | -13792.6552 | -18096.5204 | -27.32% | -18.03% | N/A | N/A | N/A | 25 | 25 | 50 | 16 | 14 | 30 | -11 | -20 | -44% | -40% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
59 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50C | Impr Rel/Dep Gas Regulation | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C009 Gas Distribution Reg Station Rebuild | Ex 3, Ch 6 | No | On-going | Annual | 49887.2427 | 50487.7181 | 100374.9609 | 45585.3776 | 36695.0629 | 82280.4405 | -13792.6552 | -18094.5204 | -27.32% | -18.03% | N/A | N/A | N/A | 25 | 25 | 50 | 16 | 14 | 30 | -11 | -20 | -44% | -40% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
60 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50Q | Casings | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 2698.4499 | 2730.9302 | 5429.3801 | 3138.0424 | 2483.6831 | 5621.7254 | -247.2472 | 192.3453 | -9.054% | 3.543% | N | N | # of Casings Remediated (50Q) | 10 | 10 | 20 | 8 | 5 | 13 | -5 | -7 | -50% | -35% | Y | N/A | Actual units were lower than imputed units due to: 1) cancellation of jobs (found isolated during testing), 2) permitting delays and challenges with external agencies 3) Scope change (converted to expense) | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This program is to mitigate casings over or equal to 40 feet to meet the requirement of 49 CFR § 192.467 External corrosion control.
61 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50Q | Casings | Loss of Containment on Gas Distribution Main or Service | LOCDM-C019 Casings | Ex 3, Ch 9 | No | On-going | Annual | 2698.4499 | 2730.9302 | 5429.3801 | 3137.0424 | 2483.6831 | 5620.7254 | -247.2472 | 191.3453 | -9.054% | 3.524% | N/A | N/A | N/A | 10 | 10 | 20 | 8 | 5 | 13 | -5 | -7 | -50% | -35% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
62 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50M/ 3PC (b) | Complex-Gas Svc Repl Leak | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-going | Annual | 1125.0113 | 1139 | 2264.0113 | 1718.262 | 989 | 2707.262 | -150 | 443.2508 | -13.17% | 19.58% | N | N | # of services (NERBA BG Grade 3 unit) | 63 | 63 | 126 | 40 | 24 | 64 | -39 | -62 | -61.9% | -49.21% | Y | N/A | Actual units lower than imputed due to lower leak find rates than planned resulting in a decrease of leaks repaired via complex service replacement | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this demand-driven program is a continuing effort to mitigate leaks.
63 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50M/ 3PC (b) | Complex-Gas Svc Repl Leak | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-going | Annual | 1125.0113 | 1139 | 2264.0113 | 1717.262 | 989 | 2706.262 | -150 | 442.2508 | -13.17% | 19.53% | N/A | N/A | N/A | 63 | 63 | 126 | 40 | 24 | 64 | -39 | -62 | -61.9% | -49.21% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
64 | Capital | Gas Distribution | 52 | G Dist Leak Repl/Emergency | 52# | Not assigned | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-going | Annual | 0 | 0 | 0 | 82 | 0 | 82 | 0 | 82 | 0% | 100% | N | N | non-unitized: This MAT has no measurable units because it is used to record other support costs for third party damage service repair. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | N/A | N/A | N/A | N/A | This MAT is expected to continue to incur a minimal amount of spend in PG&E's 2023 GRC period.
65 | Capital | Gas Distribution | 52 | G Dist Leak Repl/Emergency | 52B | Emerg Resp-G-Dig-Ins-Svcs | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-going | Annual | 1343.9403 | 1360.1168 | 2704.0571 | 2856.3368 | 2194.0595 | 5050.3962 | 833.9426 | 2346.3391 | 61.31% | 86.77% | N | N | # of services replaced | 178 | 178 | 356 | 151 | 128 | 279 | -50 | -77 | -28.09% | -21.63% | Y | N/A | Actual units were lower than imputed due to reduced number of emergencies and 3rd party damages reported that required full service replacement or deactivation. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to fix distribution service damages caused by natural forces and 3rd parties. This MAT includes the replacement and deactivation of entire services.
66 | Capital | Gas Distribution | 52 | G Dist Leak Repl/Emergency | 52B | Emerg Resp-G-Dig-Ins-Svcs | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-going | Annual | 1343.9403 | 1360.1168 | 2704.0571 | 2855.3368 | 2194.0595 | 5049.3962 | 833.9426 | 2345.3391 | 61.31% | 86.73% | N/A | N/A | N/A | 178 | 178 | 356 | 151 | 128 | 279 | -50 | -77 | -28.09% | -21.63% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
67 | Capital | Gas Distribution | 52 | G Dist Leak Repl/Emergency | 52C | Emerg Resp-G-Dig-Ins-Main | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-going | Annual | 296.5481 | 300.1175 | 596.6656 | 1711.2389 | 58.6897 | 1769.9287 | -241.4278 | 1173.263 | -80.44% | 196.6% | N | N | feet of main replaced | 1122 | 1122 | 2244 | 1288 | 262.1 | 1550.1 | -859.9 | -693.9 | -76.64% | -30.92% | Y | N/A | Actual units were lower than imputed units due to reduced number of emergencies and 3rd party damages reported that required main deactivation or the replacement of >100 ft of main pipe. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to fix distribution main pipeline damages caused by natural forces and 3rd parties. This MAT includes the repalcement of > 100' of pipe or pipe deactivation.
68 | Capital | Gas Distribution | 52 | G Dist Leak Repl/Emergency | 52C | Emerg Resp-G-Dig-Ins-Main | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-going | Annual | 296.5481 | 300.1175 | 596.6656 | 1710.2389 | 58.6897 | 1768.9287 | -241.4278 | 1172.263 | -80.44% | 196.5% | N/A | N/A | N/A | 1122 | 1122 | 2244 | 1288 | 262.1 | 1550.1 | -859.9 | -693.9 | -76.64% | -30.92% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
69 | Capital | Gas Distribution | 74 | Install New Gas Meters | 74A | Install Regulators | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-going | Annual | 2257.3937 | 2284.5652 | 4541.9589 | 10297.827 | 8882.9085 | 19180.7355 | 6598.3433 | 14638.7765 | 288.8% | 322.3% | N | N | # of regulators | 6833 | 6833 | 13666 | 28283 | 25263 | 53546 | 18430 | 39880 | 269.7% | 291.8% | Y | N/A | Actual units were higher than imputed units due to a change in reporting practice which resulted in more regulator replacement units being captured in this MAT. Historically, regulator changes completed while in the field performing other gas field services work was captured in the MAT that drove the initial job. | Over | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
70 | Capital | Gas Distribution | 74 | Install New Gas Meters | 74A | Install Regulators | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C016 Gas Reg Replacement | Ex 3, Ch 8 | No | On-going | Annual | 2257.3937 | 2284.5652 | 4541.9589 | 10296.827 | 8882.9085 | 19179.7355 | 6598.3433 | 14637.7765 | 288.8% | 322.3% | N/A | N/A | N/A | 6833 | 6833 | 13666 | 28283 | 25263 | 53546 | 18430 | 39880 | 269.7% | 291.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
(a) 2024 actual costs by MAT are as follows: 2KA - $3,163.120, 2KB - $5,503.079, and 2KC - $866.297 (costs in thousands). 2024 actual units by MAT are as follows: 2KA - 9, 2KB - 18, and 2KC -61.
(b) Includes below ground Grade 3 leak repairs recorded under Leak Abatement MWC 3P.

## GTS SRM MAT Table Expense
Table 2-9 2024 RSAR 2023 GRC CYCLE GAS TRANSMISSION AND STORAGE EXPENSE COMPARISON BY MAT FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | C6 | C7 | D | E | F | G1 | G2 | G3 | H | H2 | H3 | I | I2 | J1 | J2 | K | L | M | N1 | N2 | N3 | O1 | O2 | O3 | P1 | P2 | Q | R | S | T | U | V | W | X | Y | Z
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name | MAT | MAT Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program/ Project Life (years) | Program/ Project Year | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs | Imputed Costs for 2023 GRC Cycle to date($) (G1+G2) | 2023 Actual Costs | 2024 Actual Costs | Actual Costs for 2023 GRC Cycle to date($) (H1+H2) | Difference for 2024 ($) (H2-G2) | Difference for 2023 GRC Cycle to Date ($) (H3-G3) | Spending Percent Variance for 2024 (%) ((H2-G2)/G2*100) | Spending Percent Variance for 2023 GRC Cylce (%) (I2/G3) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | Unit Type | 2023 Imputed Adopted Units | 2024 Imputed Adopted Units | Imputed Units for 2023 GRC Cycle to Date (N2+N1) | 2023 Actual Units | 2024 Actual Units | Actual Units for 2023 GRC Cycle to Date (O2+O1) | Difference for 2024 (# of Units) (P2-N2) | Difference for 2023 GRC Cycle to Date (# of Units)​ (O3-N3) | Unit​ Percent​ Variance​ for 2024 (%)​ (P1/N2*100) | Percent Variance for 2023 GRC Cycle to Date (%)​ (P2/N3) | Unit Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | 2024 Unit Variance Explanation | Forecast Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T) | Status | Completion Status Statement
1 | Expense | GT&S | 34 | Maint Gas Trans-Subsid | 34A(a) | Stan-Pac Expense | SRM Total | SRM Total | Ex 3, Ch 13 | No | On-Going | Annual | 2738.2705 | 2737.937 | 5476.2075 | 2090.9097 | 1449 | 3539.9097 | -1288.937 | -1936.2978 | -47.08% | -35.36% | NO | NO | Non-Unitized | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
2 | Expense | GT&S | 34 | Maint Gas Trans-Subsid | 34A(a) | Stan-Pac Expense | Loss of Containment on Gas Transmission Pipeline | LOCTM-C038 Stan-Pac Expense | Ex 3, Ch 13 | No | On-Going | Annual | 2738.2705 | 2737.937 | 5476.2075 | 2090.9097 | 1449 | 3539.9097 | -1288.937 | -1936.2978 | -47.08% | -35.36% | N/A | N/A | N/A | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | Expense | GT&S | AH | Maint Gas Storage Fac | AH1(b) | WELL - Integrity Assessments | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-Going | Annual | 9806.6629 | 9850.9111 | 19657.574 | 6542.8812 | 5813.6108 | 12356.492 | -4037.3003 | -7301.082 | -40.98% | -37.14% | NO | NO | Various | 268 | 268 | 536 | 255 | 265 | 520 | -3 | -16 | -1.119% | -2.985% | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to inspect and survey storage wells.
4 | Expense | GT&S | AH | Maint Gas Storage Fac | AH1(b) | WELL - Integrity Assessments | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C003 Well Inspections and Rework | Ex 3, Ch 7 | No | On-Going | Annual | 9806.6629 | 9850.9111 | 19657.574 | 6542.8812 | 5813.6108 | 12356.492 | -4037.3003 | -7301.082 | -40.98% | -37.14% | N/A | N/A | N/A | 268 | 268 | 536 | 255 | 265 | 520 | -3 | -16 | -1.119% | -2.985% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | Expense | GT&S | AH | Maint Gas Storage Fac | AH2 | WELL - Reworks | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-Going | Annual | 3427.5999 | 3443.065 | 6870.6649 | 0 | 0 | 0 | -3443.065 | -6870.6649 | -100% | -100% | NO | NO | # of Well reworks | 2 | 2 | 4 | 0 | 0 | 0 | -2 | -4 | -100% | -100% | YES | N/A | Actual units were lower than imputed units due to units now being capitalized under WELL Reworks MAT 3L3. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. Units are anticipated to remain capitalized and captured in MAT 3L3.
6 | Expense | GT&S | AH | Maint Gas Storage Fac | AH2 | WELL - Reworks | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C003 Well Inspections and Rework | Ex 3, Ch 7 | No | On-Going | Annual | 3427.5999 | 3443.065 | 6870.6649 | 0 | 0 | 0 | -3443.065 | -6870.6649 | -100% | -100% | N/A | N/A | N/A | 2 | 2 | 4 | 0 | 0 | 0 | -2 | -4 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 | Expense | GT&S | AH | Maint Gas Storage Fac | AH3 | WELL - Other | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-Going | Annual | 2832.4107 | 2845.1907 | 5677.6014 | 1995.5589 | 3382.124 | 5377.6829 | 536.9333 | -299.9185 | 18.87% | -5.282% | NO | NO | non-unitized: This MAT has no measurable units because it captures miscellaneous engineering support. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
8 | Expense | GT&S | AH | Maint Gas Storage Fac | AH3 | WELL - Other | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C004 Well Emergent and Emergency Support | Ex 3, Ch 7 | No | On-Going | Annual | 2832.4107 | 2845.1907 | 5677.6014 | 1995.5589 | 3382.124 | 5377.6829 | 536.9333 | -299.9185 | 18.87% | -5.282% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 | Expense | GT&S | AH | Maint Gas Storage Fac | AH4 | Gill Ranch Operations & Maint | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 7 | No | On-Going | Annual | 3189.0936 | 3202.1564 | 6391.25 | 4539.2451 | 6123.599 | 10662.8441 | 2921.4427 | 4271.5941 | 91.23% | 66.84% | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for Gill Ranch Storage. The type of the work performed at the storage are different and are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
10 | Expense | GT&S | AH | Maint Gas Storage Fac | AH# (c) | Not assigned | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-Going | Annual | 2265.6949 | 2275.918 | 4541.6129 | 476.816 | 437.9405 | 914.7565 | -1837.9775 | -3626.8563 | -80.76% | -79.86% | NO | NO | non-unitized: This MAT has no measurable units because it is used to record various engineering support costs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
11 | Expense | GT&S | AH | Maint Gas Storage Fac | AH# (c) | Not assigned | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C003 Well Inspections and Rework | Ex 3, Ch 7 | No | On-Going | Annual | 2265.6949 | 2275.918 | 4541.6129 | 476.816 | 437.9405 | 914.7565 | -1837.9775 | -3626.8563 | -80.76% | -79.86% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | Expense | GT&S | CM | GT Operate System | CMA | GT&S Operations | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 15572.9448 | 16031.5777 | 31604.5225 | 13898.3144 | 14096.6 | 27994.9144 | -1934.9777 | -3609.6081 | -12.07% | -11.42% | NO | NO | non-unitized: This MAT has no measurable units because MAT CMA represents a chargeback MAT for Gas Control related headcount (operators). It represents non-workstream program thus it is a continuous program with no unit completions associated with the charges. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
13 | Expense | GT&S | CM | GT Operate System | CMA | GT&S Operations | Insufficient Capacity to Meet Customer Demand | CPCTY-C002 GT&S Operations | Ex 3, Ch 11 | No | On-Going | Annual | 15572.9448 | 16031.5777 | 31604.5225 | 13898.3144 | 14096.6 | 27994.9144 | -1934.9777 | -3609.6081 | -12.07% | -11.42% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 | Expense | GT&S | CM | GT Operate System | CMA | GT&S Operations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C021 GT&S Operations | Ex 3, Ch 11 | No | On-Going | Annual | 15572.9448 | 16031.5777 | 31604.5225 | 13898.3144 | 14096.6 | 27994.9144 | -1934.9777 | -3609.6081 | -12.07% | -11.42% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | Expense | GT&S | CM | GT Operate System | CMA | GT&S Operations | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C015 GT&S Operations | Ex 3, Ch 11 | No | On-Going | Annual | 15572.9448 | 16031.5777 | 31604.5225 | 13898.3144 | 14096.6 | 27994.9144 | -1934.9777 | -3609.6081 | -12.07% | -11.42% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
16 | Expense | GT&S | CM | GT Operate System | CMA | GT&S Operations | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C026 GT&S Operations | Ex 3, Ch 11 | No | On-Going | Annual | 15572.9448 | 16031.5777 | 31604.5225 | 13898.3144 | 14096.6 | 27994.9144 | -1934.9777 | -3609.6081 | -12.07% | -11.42% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17 | Expense | GT&S | CM | GT Operate System | CMA | GT&S Operations | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C001 GT&S Operations | Ex 3, Ch 11 | No | On-Going | Annual | 15572.9448 | 16031.5777 | 31604.5225 | 13898.3144 | 14096.6 | 27994.9144 | -1934.9777 | -3609.6081 | -12.07% | -11.42% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
18 | Expense | GT&S | CM | GT Operate System | CMB | ElecPwr CompFuel & Oth Elec Eq | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 11 | No | On-Going | Annual | 27881.2489 | 28702.3689 | 56583.6178 | 35400.077 | 40866.3825 | 76266.4595 | 12164.0137 | 19682.8418 | 42.38% | 34.79% | YES | YES | non-unitized: his MAT has no measurable units because it includes electricity costs for electrically connected gas equipment, and electrically powered gas compressor stations. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | Actual costs were higher than imputed due to higher electricity costs and usage at electrically powered gas compressor stations. | N/A | On-Target | On-Target | Over | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to pay for the electricity costs used to power electrically powered gas compressors, and electrically connected gas field equipment.
19 | Expense | GT&S | DF | G&E T&D Locate and Mark | DFA | Locate and Mark | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1346.3682 | 1386.1465 | 2732.5148 | 697.0116 | 891.7374 | 1588.749 | -494.4091 | -1143.7658 | -35.67% | -41.86% | NO | NO | # of Tickets | 6073 | 6073 | 12146 | 3402 | 3468 | 6870 | -2605 | -5276 | -42.89% | -43.44% | YES | N/A | Actual units were lower than imputed units due to the ticket increase from third-party driven work not materializing as expected. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2027 GRC periond. The purpose of this program is to field mark PG&E's underground facilities in response to 811 tickets as required by CA GC 4216.
20 | Expense | GT&S | DF | G&E T&D Locate and Mark | DFA | Locate and Mark | Loss of Containment on Gas Transmission Pipeline | LOCTM-C009 Locate and Mark - Transmission | Ex 3, Ch 8 | No | On-Going | Annual | 1346.3682 | 1386.1465 | 2732.5148 | 697.0116 | 891.7374 | 1588.749 | -494.4091 | -1143.7658 | -35.67% | -41.86% | N/A | N/A | N/A | 6073 | 6073 | 12146 | 3402 | 3468 | 6870 | -2605 | -5276 | -42.89% | -43.44% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | Expense | GT&S | DF | G&E T&D Locate and Mark | DFB | Locate and Mark - Standby | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 5420.6595 | 5580.8123 | 11001.4718 | 5179.5161 | 7034.3445 | 12213.8607 | 1453.5323 | 1212.3889 | 26.05% | 11.02% | NO | NO | # of times standby is required onsite | 5381 | 5381 | 10762 | 5658 | 5706 | 11364 | 325 | 602 | 6.04% | 5.594% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
22 | Expense | GT&S | DF | G&E T&D Locate and Mark | DFB | Locate and Mark - Standby | Loss of Containment on Gas Transmission Pipeline | LOCTM-C010 Locate and Mark - Transmission Standby | Ex 3, Ch 8 | No | On-Going | Annual | 5420.6595 | 5580.8123 | 11001.4718 | 5179.5161 | 7034.3445 | 12213.8607 | 1453.5323 | 1212.3889 | 26.05% | 11.02% | N/A | N/A | N/A | N | 5381 | N/A | 5658 | 5706 | 11364 | 325 | 11364 | 6.04% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
23 | Expense | GT&S | GF | Gas Trans & Dist Sys Mapping | GFP | Mapping Support-Transmission | SRM Total | SRM Total | Ex 3, Ch 13 | No | On-Going | Annual | 5563.2373 | 5701.6005 | 11264.8379 | 2434.4455 | 2663.7679 | 5098.2134 | -3037.8326 | -6166.6245 | -53.28% | -54.74% | NO | NO | non-unitized: This MAT has no measurable units because the work encompassed is varied with no consistent unit of measure. This largely includes responding to requests, research, and remediation to data in gas systems (T&D) of record for assets not encompassed in an order. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to maintain Gas Transmission asset information in PG&E's systems of record.
24 | Expense | GT&S | GF | Gas Trans & Dist Sys Mapping | GFP | Mapping Support-Transmission | Loss of Containment on Gas Transmission Pipeline | LOCTM-C036 Production Mapping Transmission | Ex 3, Ch 13 | No | On-Going | Annual | 5563.2373 | 5701.6005 | 11264.8379 | 2434.4455 | 2663.7679 | 5098.2134 | -3037.8326 | -6166.6245 | -53.28% | -54.74% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
25 | Expense | GT&S | GF | Gas Trans & Dist Sys Mapping | GFQ | GT&D Data Management | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | N/A | No | On-Going | Annual | 0 | 0 | 0 | 1036.2469 | 2305.3 | 3341.5469 | 2305.3 | 3341.5469 | 0% | N/A | NO | NO | non-unitized: This MAT has no measurable units because the work encompassed is varied with no consistent unit of measure. This largely includes responding to requests, research, and remediation to data in gas systems (T&D) of record for assets not encompassed in an order. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
26 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJA(d) | Electrical Interference - AC | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 1539.3264 | 1552.8877 | 3092.214 | 1266.0421 | 1103.8303 | 2369.8723 | -449.0574 | -722.3417 | -28.92% | -23.36% | NO | NO | Various | 329 | 329 | 658 | 159 | 509 | 668 | 180 | 10 | 54.71% | 1.52% | YES | N/A | Actual units were higher than imputed units due to the catch up of low 2023 actual units. Arc Fault program starts to survey new locations in 2024, while 2023 focused on the clean up of multiple year program with low number of units being surveyed. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to investigate and monitor AC Interference as required by 49 CFR § 192.467 and 473.
27 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJA(d) | Electrical Interference - AC | Loss of Containment on Gas Transmission Pipeline | LOCTM-C033 Electrical Interference Program | Ex 3, Ch 9 | No | On-Going | Annual | 1539.3264 | 1552.8877 | 3092.214 | 1266.0421 | 1103.8303 | 2369.8723 | -449.0574 | -722.3417 | -28.92% | -23.36% | N/A | N/A | N/A | 329 | 329 | 658 | 159 | 509 | 668 | 180 | 10 | 54.71% | 1.52% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
28 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJA(d) | Electrical Interference - AC | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C019 Electrical Interference | Ex 3, Ch 9 | No | On-Going | Annual | 1539.3264 | 1552.8877 | 3092.214 | 1266.0421 | 1103.8303 | 2369.8723 | -449.0574 | -722.3417 | -28.92% | -23.36% | N/A | N/A | N/A | 329 | 329 | 658 | 159 | 509 | 668 | 180 | 10 | 54.71% | 1.52% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
29 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJB | Atmospheric Corrosion | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 3841.7394 | 3875.5847 | 7717.3241 | 7167.4575 | 15031.2045 | 22198.662 | 11155.6197 | 14481.3379 | 287.8% | 187.6% | YES | YES | Various | 94 | 94 | 188 | 62 | 45 | 107 | -49 | -81 | -52.13% | -43.09% | YES | Actual costs were higher than imputed due the majority of the units were on line 300/400, which are large pipelines and complex jobs. In 2024, asbestos abatement became a common mitigating factor which increased unit cost. | Actual units were lower than imputed units MAT was impacted by long lead permit delays and scope changes, including lead abatement requirements. Multiple jobs were underway in 2024, but completion will not be realized until 2025. Furthermore, in 2024 the threshold for capitalizing span re-coates changed from 100 feet to 40 feet, so actual units dropped in GJB and increased in 3KA. | Under | On-Target | Over | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to maintain and re-coat facilities that have observed corrosion or have deteriorated coating.
30 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJB | Atmospheric Corrosion | Loss of Containment on Gas Transmission Pipeline | LOCTM-C034 Atmospheric Corrosion Program | Ex 3, Ch 9 | No | On-Going | Annual | 3841.7394 | 3875.5847 | 7717.3241 | 7167.4575 | 15031.2045 | 22198.662 | 11155.6197 | 14481.3379 | 287.8% | 187.6% | N/A | N/A | N/A | 94 | 94 | 188 | 62 | 45 | 107 | -49 | -81 | -52.13% | -43.09% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
31 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJB | Atmospheric Corrosion | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C017 Facility Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 3841.7394 | 3875.5847 | 7717.3241 | 7167.4575 | 15031.2045 | 22198.662 | 11155.6197 | 14481.3379 | 287.8% | 187.6% | N/A | N/A | N/A | 94 | 94 | 188 | 62 | 45 | 107 | -49 | -81 | -52.13% | -43.09% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
32 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJC(e) | Cathodic Protection Exp | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 414.4137 | 418.0646 | 832.4783 | 291.7303 | 601.4374 | 893.1678 | 183.3728 | 60.6894 | 43.86% | 7.29% | NO | NO | RMU Covered by Service Fees | 1000 | 1000 | 2000 | 889 | 965 | 1854 | -35 | -146 | -3.5% | -7.3% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
33 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJC(e) | Cathodic Protection Exp | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 414.4137 | 418.0646 | 832.4783 | 291.7303 | 601.4374 | 893.1678 | 183.3728 | 60.6894 | 43.86% | 7.29% | N/A | N/A | N/A | 1000 | 1000 | 2000 | 889 | 965 | 1854 | -35 | -146 | -3.5% | -7.3% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
34 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJD | Test Station Exp | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 247.0824 | 249.2592 | 496.3416 | 242.5938 | 136.3159 | 378.9097 | -112.9433 | -117.4319 | -45.31% | -23.66% | NO | NO | # of test stations installed | 10 | 10 | 20 | 2 | 2 | 4 | -8 | -16 | -80% | -80% | YES | N/A | Actual units were lower than imputed units because fewer expense test stations (CTS) needed to be installed to meet requirement for 1 CTS per mile. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to install test station to meet the requirement of "sufficient test stations" required via 49 § 192.469.
35 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJD | Test Station Exp | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 247.0824 | 249.2592 | 496.3416 | 242.5938 | 136.3159 | 378.9097 | -112.9433 | -117.4319 | -45.31% | -23.66% | N/A | N/A | N/A | 10 | 10 | 20 | 2 | 2 | 4 | -8 | -16 | -80% | -80% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
36 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJE(f) | Close Interval Survey (CIS) | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 4141.9315 | 4178.4215 | 8320.3529 | 1877.165 | 1071.0608 | 2948.2257 | -3107.3607 | -5372.1272 | -74.37% | -64.57% | NO | NO | Various | 451 | 451 | 902 | 178.17 | 92 | 270.17 | -359 | -631.83 | -79.6% | -70.05% | YES | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This program is a method for determining the adequacy of cathodic protection between corrosion monitoring points. This data is used to evaluate the health of the corrosion control system. Locations of possible active external corrosion are identified and analyzed through excavation and/or direct examination.
37 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJE(f) | Close Interval Survey (CIS) | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 4141.9315 | 4178.4215 | 8320.3529 | 1877.165 | 1071.0608 | 2948.2257 | -3107.3607 | -5372.1272 | -74.37% | -64.57% | N/A | N/A | N/A | 451 | 451 | 902 | 178 | 92 | 270 | -359 | -632 | -79.6% | -70.07% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
38 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJE(f) | Close Interval Survey (CIS) | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C018 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 4141.9315 | 4178.4215 | 8320.3529 | 1877.165 | 1071.0608 | 2948.2257 | -3107.3607 | -5372.1272 | -74.37% | -64.57% | N/A | N/A | N/A | 451 | 451 | 902 | 178 | 92 | 270 | -359 | -632 | -79.6% | -70.07% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
39 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJF | Electrical Interference - DC | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 801.9187 | 808.9835 | 1610.9022 | 1616.5283 | 2137.7661 | 3754.2943 | 1328.7825 | 2143.3921 | 164.3% | 133.1% | NO | NO | non-unitized: This MAT has no measurable units because this MAT code is to perform Dynamic/Static DC Reactive/Proactive investigation, and it is mainly vendor or employee’s time charged to perform the investigation. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
40 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJF | Electrical Interference - DC | Loss of Containment on Gas Transmission Pipeline | LOCTM-C033 Electrical Interference Program | Ex 3, Ch 9 | No | On-Going | Annual | 801.9187 | 808.9835 | 1610.9022 | 1616.5283 | 2137.7661 | 3754.2943 | 1328.7825 | 2143.3921 | 164.3% | 133.1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
41 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJF | Electrical Interference - DC | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C019 Electrical Interference | Ex 3, Ch 9 | No | On-Going | Annual | 801.9187 | 808.9835 | 1610.9022 | 1616.5283 | 2137.7661 | 3754.2943 | 1328.7825 | 2143.3921 | 164.3% | 133.1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJH(g) | Internal Corrosion | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 6066.0923 | 6119.534 | 12185.6263 | 838.3169 | 2391.9185 | 3230.2354 | -3727.6155 | -8955.3909 | -60.91% | -73.49% | NO | NO | Various | 2743 | 2743 | 5486 | 1395 | 1571 | 2966 | -1172 | -2520 | -42.73% | -45.94% | YES | N/A | Actual units were lower than imputed units because: 1) work was done and paid by a third party, so no rate case units are claimed, 2) fewer internal corrosion monitoring devices were installed than anticipated that required monitoring, 3) drips required less frequent maintenance than anticipated, and 4) fewer internal corrosion non-destructive examinations were performed. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to investigate and monitor Internal Corrosion as required by 49 CFR § 192.475.
43 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJH(g) | Internal Corrosion | Loss of Containment on Gas Transmission Pipeline | LOCTM-C032 Internal Corrosion Program | Ex 3, Ch 9 | No | On-Going | Annual | 6066.0923 | 6119.534 | 12185.6263 | 838.3169 | 2391.9185 | 3230.2354 | -3727.6155 | -8955.3909 | -60.91% | -73.49% | N/A | N/A | N/A | 2743 | 2743 | 5486 | 1395 | 1571 | 2966 | -1172 | -2520 | -42.73% | -45.94% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
44 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJJ | Low Read Investigations | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 290.9477 | 293.5109 | 584.4585 | 0 | 0.5451 | 0.5451 | -292.9658 | -583.9134 | -99.81% | -99.91% | NO | NO | non-unitized: This MAT has no measurable units because the type of work varies by situation. Complex corrosion investigations are driven by requests from corrosion field services to corrosion engineering to help troubleshoot complex corrosion issues as needed, and the level of support varies based on the unique circumstances of each problem. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
45 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJJ | Low Read Investigations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 290.9477 | 293.5109 | 584.4585 | 0 | 0.5451 | 0.5451 | -292.9658 | -583.9134 | -99.81% | -99.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
46 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJK | Corrosion Support | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 2865.1826 | 2890.4246 | 5755.6072 | 1445.9071 | 1667.5743 | 3113.4814 | -1222.8503 | -2642.1258 | -42.31% | -45.91% | NO | NO | non-unitized: This MAT has no measurable units because it reflects labor costs supporting data and program management. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
47 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJK | Corrosion Support | Loss of Containment on Gas Transmission Pipeline | LOCTM-C035 Transmission Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 2865.1826 | 2890.4246 | 5755.6072 | 1445.9071 | 1667.5743 | 3113.4814 | -1222.8503 | -2642.1258 | -42.31% | -45.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
48 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJK | Corrosion Support | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C017 Facility Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 2865.1826 | 2890.4246 | 5755.6072 | 1445.9071 | 1667.5743 | 3113.4814 | -1222.8503 | -2642.1258 | -42.31% | -45.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
49 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJM(h) | Casings | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 4276.6017 | 4314.2782 | 8590.8799 | 2279.9808 | 790.8101 | 3070.7908 | -3523.4681 | -5520.0891 | -81.67% | -64.26% | NO | NO | Various | 1181 | 1181 | 2362 | 1137 | 857 | 1994 | -324 | -368 | -27.43% | -15.58% | YES | N/A | Actual units were lower than imputed units due to the threshold change of expense casing mitigation in April 2024 (casing length between 40 ft to 100 ft are moved to capital bucket) and the lower # of casings that required accelerated casing leak survey. | On-Target | On-Target | Under | Proceeding as planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to test, minitor and test casing to ensure each buried or submerged pipeline being electrically isolated from the metallic casing it is within (49 CFR Part 192.467) and all casings are tested/inspected to assure electrical isolation once per calendar year (49 CFR § 192.465).
50 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJM(h) | Casings | Loss of Containment on Gas Transmission Pipeline | LOCTM-C035 Transmission Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 4276.6017 | 4314.2782 | 8590.8799 | 2279.9808 | 790.8101 | 3070.7908 | -3523.4681 | -5520.0891 | -81.67% | -64.26% | N/A | N/A | N/A | 1181 | 1181 | 2362 | 1137 | 857 | 1994 | -324 | -368 | -27.43% | -15.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
51 | Expense | GT&S | GM | Manage Energy Efficiency-NonBA | GMD | LNG / CNG | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 2650.8404 | 2699.0033 | 5349.8437 | 3616.9924 | 3850.3411 | 7467.3335 | 1151.3378 | 2117.4898 | 42.66% | 39.58% | NO | NO | non-unitized: This MAT has no measurable units due to the variability in O&M activities the MAT includes. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
52 | Expense | GT&S | GM | Manage Energy Efficiency-NonBA | GMD | LNG / CNG | Loss of Containment on LNG/CNG Portable Equipment | LNCNG-C002 LNG/CNG Portable Expense | Ex 3, Ch 5 | No | On-Going | Annual | 2650.8404 | 2699.0033 | 5349.8437 | 3616.9924 | 3850.3411 | 7467.3335 | 1151.3378 | 2117.4898 | 42.66% | 39.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
53 | Expense | GT&S | GM | Manage Energy Efficiency-NonBA | GMD | LNG / CNG | Loss of Containment on Gas Transmission Pipeline | LOCTM-C002 LNG/CNG to Support Strength Testing | Ex 3, Ch 5 | No | On-Going | Annual | 2650.8404 | 2699.0033 | 5349.8437 | 3616.9924 | 3850.3411 | 7467.3335 | 1151.3378 | 2117.4898 | 42.66% | 39.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
54 | Expense | GT&S | HP | CGT Balancing Accounts | HPA | TIMP - Other | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 9804.1524 | 9880.5302 | 19684.6826 | 9706.6025 | 11029.0852 | 20735.6877 | 1148.555 | 1051.0051 | 11.62% | 5.339% | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for Subpart O Integrity Management Risk Analysis. The type of work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
55 | Expense | GT&S | HP | CGT Balancing Accounts | HPA | TIMP - Other | Loss of Containment on Gas Transmission Pipeline | LOCTM-C029 Risk Analysis | Ex 3, Ch 5 | No | On-Going | Annual | 9804.1524 | 9880.5302 | 19684.6826 | 9706.6025 | 11029.0852 | 20735.6877 | 1148.555 | 1051.0051 | 11.62% | 5.339% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
56 | Expense | GT&S | HP | CGT Balancing Accounts | HPB | Traditional ILI Runs | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 33561.7789 | 33823.2368 | 67385.0157 | 70894.1775 | 55800.0629 | 126694.2404 | 21976.8261 | 59309.2247 | 64.98% | 88.02% | YES | YES | Various | 337.27 | 337 | 674.27 | 457 | 358 | 815 | 21 | 140.73 | 6.231% | 20.87% | NO | Actual costs were higher than imputed due to increased costs associated with challenging inspections in the 2024 portfolio. These inspections required more sophisticated tools to assess the pipelines, increase the flow rate to enable inspection, and support customers that would have been impacted by the inspection. | N/A | Over | On-Target | Over | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to assess pipeline integrity for the internal and external condition of transmission line pipe as required by 49 CFR Subpart O.
57 | Expense | GT&S | HP | CGT Balancing Accounts | HPB | Traditional ILI Runs | Loss of Containment on Gas Transmission Pipeline | LOCTM-C005 In-Line Inspection | Ex 3, Ch 5 | No | On-Going | Annual | 33561.7789 | 33823.2368 | 67385.0157 | 70894.1775 | 55800.0629 | 126694.2404 | 21976.8261 | 59309.2247 | 64.98% | 88.02% | N/A | N/A | N/A | 337.27 | 337 | 674.27 | 457 | 358 | 815 | 21 | 140.73 | 6.231% | 20.87% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
58 | Expense | GT&S | HP | CGT Balancing Accounts | HPC | ECDA Indirect Inspections | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 7382.6277 | 7440.1409 | 14822.7687 | 8316.0772 | 8920.3965 | 17236.4737 | 1480.2556 | 2413.705 | 19.9% | 16.28% | NO | NO | Miles inspected | 67.13 | 67 | 134.13 | 38.99 | 37 | 75.99 | -30 | -58.14 | -44.78% | -43.35% | YES | N/A | Actual units were lower than imputed units due to fewer miles of pipeline assessed with ECDA. This was due to the decision to utilize other assessment technologies which led to a lower scope of work materializing. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform indirect inspections along pipelines as part of an ECDA.
59 | Expense | GT&S | HP | CGT Balancing Accounts | HPC | ECDA Indirect Inspections | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-Going | Annual | 7382.6277 | 7440.1409 | 14822.7687 | 8316.0772 | 8920.3965 | 17236.4737 | 1480.2556 | 2413.705 | 19.9% | 16.28% | N/A | N/A | N/A | 67.13 | 67 | 134.13 | 39 | 37 | 76 | -30 | -58.13 | -44.78% | -43.34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
60 | Expense | GT&S | HP | CGT Balancing Accounts | HPE | Integrity Manage Leak Survey | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | annual | 276.1159 | 278.267 | 554.3829 | 179.4054 | 151.3539 | 330.7593 | -126.9131 | -223.6236 | -45.61% | -40.34% | NO | NO | non-unitized: This MAT has no measurable units because this programs records costs associated with transmission leak surveys conducted on conducted on Class 3/4 non HCA pipeline operating under 30 percent Specified Minimum Yield Strength as required by Subpart O. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
61 | Expense | GT&S | HP | CGT Balancing Accounts | HPE | Integrity Manage Leak Survey | Loss of Containment on Gas Transmission Pipeline | LOCTM-C029 Risk Analysis | Ex 3, Ch 5 | No | On-Going | annual | 276.1159 | 278.267 | 554.3829 | 179.4054 | 151.3539 | 330.7593 | -126.9131 | -223.6236 | -45.61% | -40.34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
62 | Expense | GT&S | HP | CGT Balancing Accounts | HPF | Hydrostatic Testing - IM | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 21325.5687 | 21491.7023 | 42817.271 | 35560.2918 | 22551.6239 | 58111.9157 | 1059.9216 | 15294.6447 | 4.932% | 35.72% | NO | NO | Miles | 3.27 | 3 | 6.27 | 12.02 | 5 | 17.02 | 2 | 10.75 | 66.67% | 171.5% | YES | N/A | Actual units were higher than imputed units due to a larger amount of in-year compliance driven work coming due | Over | On-Target | Over | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to conduct hydrostatic tests for the purpose of assessing pipeline identified by TIMP to be in compliance with 49 CFR Part 192, Subpart O. The hydrostatic testing work involves three efforts: 1. Review and validation of records to prove a pipeline has had a prior hydrostatic test performed 2. Pipeline replacement where necessary to prepare a pipeline for testing 3. Filling the inside of the pipeline with water and raising the pressure to a predetermined value and holding it for a period of time.
63 | Expense | GT&S | HP | CGT Balancing Accounts | HPF | Hydrostatic Testing - IM | Loss of Containment on Gas Transmission Pipeline | LOCTM-C026 TIMP Strength Testing | Ex 3, Ch 5 | No | On-Going | Annual | 21325.5687 | 21491.7023 | 42817.271 | 35560.2918 | 22551.6239 | 58111.9157 | 1059.9216 | 15294.6447 | 4.932% | 35.72% | N/A | N/A | N/A | 3.27 | 3 | 6.27 | 12.02 | 5 | 17.02 | 2 | 10.75 | 66.67% | 171.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
64 | Expense | GT&S | HP | CGT Balancing Accounts | HPI | ILI Direct Exam and Repair | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 48185.77 | 48561.1539 | 96746.9239 | 47027.7249 | 24620.6201 | 71648.345 | -23940.5338 | -25098.5789 | -49.3% | -25.94% | YES | YES | non-unitized: This MAT has no measurable units because it involves direct examination and repair work that is based on data collected through both Traditional and Non-Traditional ILI runs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | Actual costs were lower than imputed due to less digs materializing than expected which was driven by less scheduled or immediate anomalies found than on historical ILI runs. | N/A | On-Target | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to conduct direct examination digs and repairs made as a result of the ILI inspections.
65 | Expense | GT&S | HP | CGT Balancing Accounts | HPI | ILI Direct Exam and Repair | Loss of Containment on Gas Transmission Pipeline | LOCTM-C005 In-Line Inspection | Ex 3, Ch 5 | No | On-Going | Annual | 48185.77 | 48561.1539 | 96746.9239 | 47027.7249 | 24620.6201 | 71648.345 | -23940.5338 | -25098.5789 | -49.3% | -25.94% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
66 | Expense | GT&S | HP | CGT Balancing Accounts | HPJ | ICDA Indirect Inspections | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 718.4544 | 724.0514 | 1442.5058 | 32.6216 | 0.03202 | 32.6536 | -724.0194 | -1409.8522 | -100% | -97.74% | NO | NO | # of Projects | 11 | 11 | 22 | 0 | 0 | 0 | -11 | -22 | -100% | -100% | YES | N/A | Actual units were lower than imputed units due to fewer miles of pipeline assessed with ICDA. This was due to the decision to utilize other assessment technologies which led to a lower scope of work materializing. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform engineering as part of ICDA.
67 | Expense | GT&S | HP | CGT Balancing Accounts | HPJ | ICDA Indirect Inspections | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-Going | Annual | 718.4544 | 724.0514 | 1442.5058 | 32.6216 | 0.03202 | 32.6536 | -724.0194 | -1409.8522 | -100% | -97.74% | N/A | N/A | N/A | 11 | 11 | 22 | 0 | 0 | 0 | -11 | -22 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
68 | Expense | GT&S | HP | CGT Balancing Accounts | HPK | SCCDA Indirect Inspections | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 1745.2767 | 1758.8731 | 3504.1498 | 839.7284 | 2190.0242 | 3029.7526 | 431.1512 | -474.3972 | 24.51% | -13.54% | NO | NO | # Miles Assessed | 15.87 | 16 | 31.87 | 0 | 27 | 27 | 11 | -4.87 | 68.75% | -15.28% | YES | N/A | Actual units were higher than imputed units due to more miles of pipeline assessed with SCCDA. This was due to the decision to utilize SCCDA rather than other assessment technologies which led to higher scope of work. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The pupose of this program is to perform indirect inspections along pipelines as part of SCCDA.
69 | Expense | GT&S | HP | CGT Balancing Accounts | HPK | SCCDA Indirect Inspections | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-Going | Annual | 1745.2767 | 1758.8731 | 3504.1498 | 839.7284 | 2190.0242 | 3029.7526 | 431.1512 | -474.3972 | 24.51% | -13.54% | N/A | N/A | N/A | 15.87 | 16 | 31.87 | 0 | 27 | 27 | 11 | -4.87 | 68.75% | -15.28% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
70 | Expense | GT&S | HP | CGT Balancing Accounts | HPM | Repairs / Replace < '50ft | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 4446.3524 | 4480.991 | 8927.3434 | 139.0111 | 1069.429 | 1208.4401 | -3411.562 | -7718.9033 | -76.13% | -86.46% | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for very short pipe replacements in lieu of test (<50ft). | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform pipe replacement in-lieu of strength testing for HCA pipe.
71 | Expense | GT&S | HP | CGT Balancing Accounts | HPM | Repairs / Replace < '50ft | Loss of Containment on Gas Transmission Pipeline | LOCTM-C026 TIMP Strength Testing | Ex 3, Ch 5 | No | On-Going | Annual | 4446.3524 | 4480.991 | 8927.3434 | 139.0111 | 1069.429 | 1208.4401 | -3411.562 | -7718.9033 | -76.13% | -86.46% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
72 | Expense | GT&S | HP | CGT Balancing Accounts | HPN | ECDA Direct Examinations | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 36825.3393 | 37112.2215 | 73937.5609 | 27086.2017 | 21617.6936 | 48703.8954 | -15494.5279 | -25233.6655 | -41.75% | -34.13% | YES | YES | Digs | 168 | 168 | 336 | 122 | 95 | 217 | -73 | -119 | -43.45% | -35.42% | YES | Actual costs were lower than imputed due to fewer miles of pipeline assessed with ECDA. This was due to fewer miles of HCAs that required ECDA assessments which led to lower costs. | Actual units were lower than imputed units due to fewer miles of pipeline assessed with EDCA. This was due to the decision to utilize other assessment technologies which led to lower scope of work. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform direct examinations as part of ECDA.
73 | Expense | GT&S | HP | CGT Balancing Accounts | HPN | ECDA Direct Examinations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-Going | Annual | 36825.3393 | 37112.2215 | 73937.5609 | 27086.2017 | 21617.6936 | 48703.8954 | -15494.5279 | -25233.6655 | -41.75% | -34.13% | N/A | N/A | N/A | 168 | 168 | 336 | 122 | 95 | 217 | -73 | -119 | -43.45% | -35.42% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
74 | Expense | GT&S | HP | CGT Balancing Accounts | HPO | ICDA Direct Examinations | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 12665.5697 | 12764.2389 | 25429.8086 | 1242.7365 | 131.9796 | 1374.7161 | -12632.2593 | -24055.0925 | -98.97% | -94.59% | YES | YES | Digs | 43 | 43 | 86 | 4 | 0 | 4 | -43 | -82 | -100% | -95.35% | YES | Actual costs were lower than imputed due to fewer miles of pipeline assessed with ICDA. This was due to fewer miles of HCAs that required ICDA assessments which led to lower costs. | Actual units were lower than imputed units due to fewer miles of pipeline assessed with IDCA. This was due to the decision to utilize other assessment technologies which led to lower scope of work. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform direct examinations as part of ICDA.
75 | Expense | GT&S | HP | CGT Balancing Accounts | HPO | ICDA Direct Examinations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-Going | Annual | 12665.5697 | 12764.2389 | 25429.8086 | 1242.7365 | 131.9796 | 1374.7161 | -12632.2593 | -24055.0925 | -98.97% | -94.59% | N/A | N/A | N/A | 43 | 43 | 86 | 4 | 0 | 4 | -43 | -82 | -100% | -95.35% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
76 | Expense | GT&S | HP | CGT Balancing Accounts | HPP | SCCDA Direct Examinations | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 17035.1859 | 17167.8959 | 34203.0818 | 17.6374 | 15578.1959 | 15595.8333 | -1589.7001 | -18607.2485 | -9.26% | -54.4% | NO | NO | Digs | 77 | 77 | 154 | 0 | 103 | 103 | 26 | -51 | 33.77% | -33.12% | YES | N/A | Actual units were higher than imputed units due to more miles of pipeline assessed with SCCDCA. This was due to the decision to utilize SCCDA rather than other assessment technologies which led to higher scope of work. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform direct examinations as part of SCCDA.
77 | Expense | GT&S | HP | CGT Balancing Accounts | HPP | SCCDA Direct Examinations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-Going | Annual | 17035.1859 | 17167.8959 | 34203.0818 | 17.6374 | 15578.1959 | 15595.8333 | -1589.7001 | -18607.2485 | -9.26% | -54.4% | N/A | N/A | N/A | 77 | 77 | 154 | 0 | 103 | 103 | 26 | -51 | 33.77% | -33.12% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
78 | Expense | GT&S | HP | CGT Balancing Accounts | HPR | Non-Traditional ILI Runs | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 14392.6442 | 14504.7679 | 28897.4121 | 17293.2659 | 20451.9811 | 37745.2471 | 5947.2133 | 8847.835 | 41% | 30.62% | NO | YES | Miles | 6.23 | 6 | 12.23 | 4.1 | 8 | 12.1 | 2 | -0.13 | 33.33% | -1.063% | YES | Actual costs were higher than imputed due to a larger volume of NT-ILI driven assessments which was driven by less alternative assessment methods, such as ECDA, Pipe Replacement, and Strength Testing, being feasible or more costly to perform integrity assessments in the planned 2024 locations. Furthermore, this program had emergent work and a stuck tool that also contributed to the increase in cost. | Actual units were higher than imputed units because alternative assessment methods, such as ECDA, Pipe Replacement, and Strength Testing, were not feasible or more costly to perform integrity assessments at planned locations in 2024. | On-Target | On-Target | Over | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to conduct non‐traditional ILI cleaning and inspection runs on gas transmission pipelines with tools propelled by any method other than gas flow.
79 | Expense | GT&S | HP | CGT Balancing Accounts | HPR | Non-Traditional ILI Runs | Loss of Containment on Gas Transmission Pipeline | LOCTM-C005 In-Line Inspection | Ex 3, Ch 5 | No | On-Going | Annual | 14392.6442 | 14504.7679 | 28897.4121 | 17293.2659 | 20451.9811 | 37745.2471 | 5947.2133 | 8847.835 | 41% | 30.62% | N/A | N/A | N/A | 6.23 | 6 | 12.23 | 4.1 | 8 | 12.1 | 2 | -0.13 | 33.33% | -1.063% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
80 | Expense | GT&S | HP | CGT Balancing Accounts | HPS | Geo-Hazard Studies | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | annual | 3014.4653 | 3037.9491 | 6052.4144 | 1927.311 | 1969.0724 | 3896.3834 | -1068.8767 | -2156.031 | -35.18% | -35.62% | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for identifying geo-hazards such as soil-creep, dormant landslides with potential to re-activate, and subsidence. The type of work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
81 | Expense | GT&S | HP | CGT Balancing Accounts | HPS | Geo-Hazard Studies | Loss of Containment on Gas Transmission Pipeline | LOCTM-C001 Geo-Hazard Threat Identification and Mitigation | Ex 3, Ch 5 | No | On-Going | annual | 3014.4653 | 3037.9491 | 6052.4144 | 1927.311 | 1969.0724 | 3896.3834 | -1068.8767 | -2156.031 | -35.18% | -35.62% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
82 | Expense | GT&S | HP | CGT Balancing Accounts | HPT | Root Cause Analysis | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 2871.0086 | 2893.3747 | 5764.3833 | 1048.0014 | 1203.1043 | 2251.1057 | -1690.2705 | -3513.2777 | -58.42% | -60.95% | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs to perform root cause analysis of significant incidents or issues on pipelines. The type of work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
83 | Expense | GT&S | HP | CGT Balancing Accounts | HPT | Root Cause Analysis | Loss of Containment on Gas Transmission Pipeline | LOCTM-C030 Root Cause Analysis | Ex 3, Ch 5 | No | On-Going | Annual | 2871.0086 | 2893.3747 | 5764.3833 | 1048.0014 | 1203.1043 | 2251.1057 | -1690.2705 | -3513.2777 | -58.42% | -60.95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 | Expense | GT&S | HP | CGT Balancing Accounts | HPU | TIMP Direct Examinations | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 25659.9366 | 25859.8364 | 51519.773 | 19207.7252 | 4777.069 | 23984.7942 | -21082.7674 | -27534.9788 | -81.53% | -53.45% | YES | YES | # of Direct Examination Projects | 24 | 24 | 48 | 17 | 9 | 26 | -15 | -22 | -62.5% | -45.83% | YES | Actual costs were lower than imputed units due to fewer miles of expense DE HCA assessments than anticipated and the capitalization of units. The capitialization threshold for recoats changed from 100 feet to 40 feet. | Actual units were lower than imputed units due to recapitalization of recoating from 100 feet to 40 feet and fewer miles of pipeline assessed with expense DE. This lead to fewer miles of HCAs that required expense DE assessments which led to lower units. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform 100% Direct Examinations on pipeline segments less than 40 feet.
85 | Expense | GT&S | HP | CGT Balancing Accounts | HPU | TIMP Direct Examinations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-Going | Annual | 25659.9366 | 25859.8364 | 51519.773 | 19207.7252 | 4777.069 | 23984.7942 | -21082.7674 | -27534.9788 | -81.53% | -53.45% | N/A | N/A | N/A | 24 | 24 | 48 | 17 | 9 | 26 | -15 | -22 | -62.5% | -45.83% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
86 | Expense | GT&S | JO | GT Pipeline Maintenance | JO1 | PM Scada Maintenance | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 349.0068 | 356.4646 | 705.4715 | 355.0947 | 376.8816 | 731.9764 | 20.417 | 26.5049 | 5.728% | 3.757% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
87 | Expense | GT&S | JO | GT Pipeline Maintenance | JO1 | PM Scada Maintenance | Insufficient Capacity to Meet Customer Demand | CPCTY-C005 Transmission SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 349.0068 | 356.4646 | 705.4715 | 0 | 376.8816 | 376.8816 | 20.417 | -328.5899 | 5.728% | -46.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
88 | Expense | GT&S | JO | GT Pipeline Maintenance | JO1 | PM Scada Maintenance | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C016 Transmission SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 349.0068 | 356.4646 | 705.4715 | 355.0947 | 376.8816 | 731.9764 | 20.417 | 26.5049 | 5.728% | 3.757% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
89 | Expense | GT&S | JO | GT Pipeline Maintenance | JO1 | PM Scada Maintenance | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C002 Transmission SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 349.0068 | 356.4646 | 705.4715 | 355.0947 | 376.8816 | 731.9764 | 20.417 | 26.5049 | 5.728% | 3.757% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
90 | Expense | GT&S | JO | GT Pipeline Maintenance | JO2 | CM Scada Maintenance | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 251.408 | 256.7802 | 508.1882 | 186.3302 | 185.7377 | 372.0679 | -71.0425 | -136.1203 | -27.67% | -26.79% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
91 | Expense | GT&S | JO | GT Pipeline Maintenance | JO2 | CM Scada Maintenance | Insufficient Capacity to Meet Customer Demand | CPCTY-C005 Transmission SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 251.408 | 256.7802 | 508.1882 | 186.3302 | 185.7377 | 372.0679 | -71.0425 | -136.1203 | -27.67% | -26.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
92 | Expense | GT&S | JO | GT Pipeline Maintenance | JO2 | CM Scada Maintenance | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C016 Transmission SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 251.408 | 256.7802 | 508.1882 | 186.3302 | 185.7377 | 372.0679 | -71.0425 | -136.1203 | -27.67% | -26.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
93 | Expense | GT&S | JO | GT Pipeline Maintenance | JO2 | CM Scada Maintenance | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C002 Transmission SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 251.408 | 256.7802 | 508.1882 | 0 | 185.7377 | 185.7377 | -71.0425 | -322.4505 | -27.67% | -63.45% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
94 | Expense | GT&S | JO | GT Pipeline Maintenance | JOA | Cath Prot Rectifier Maintenanc | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 118.2768 | 120.8067 | 239.0835 | 326.5746 | 212.9497 | 539.5243 | 92.143 | 300.4408 | 76.27% | 125.7% | NO | NO | # of Rectifiers Maintained | 919 | 919 | 1838 | 944 | 886 | 1830 | -33 | -8 | -3.591% | -0.4353% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
95 | Expense | GT&S | JO | GT Pipeline Maintenance | JOA | Cath Prot Rectifier Maintenanc | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 118.2768 | 120.8067 | 239.0835 | 326.5746 | 212.9497 | 539.5243 | 92.143 | 300.4408 | 76.27% | 125.7% | N/A | N/A | N/A | 919 | 919 | 1838 | 944 | 886 | 1830 | -33 | -8 | -3.591% | -0.4353% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
96 | Expense | GT&S | JO | GT Pipeline Maintenance | JOB | Cath Prot Monitoring | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 1289.5719 | 1317.1553 | 2606.7272 | 1882.3828 | 1862.6427 | 3745.0255 | 545.4874 | 1138.2983 | 41.41% | 43.67% | NO | NO | # of CP monitoring point reads (P/S reads) | 13674 | 13674 | 27348 | 18750 | 18640 | 37390 | 4966 | 10042 | 36.32% | 36.72% | YES | N/A | Actual units were higher than Imputed units due to not factoring in Bi-monthly Rectifier Reads for Backbone and GT due to the assumption that automated reads would not report units | Over | On-Target | On-Target | Proceeding as planned | Ongoing and will continue in PG&E's 2023 GRC period
97 | Expense | GT&S | JO | GT Pipeline Maintenance | JOB | Cath Prot Monitoring | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 1289.5719 | 1317.1553 | 2606.7272 | 0 | 1862.6427 | 1862.6427 | 545.4874 | -744.0845 | 41.41% | -28.54% | N/A | N/A | N/A | 13674 | 13674 | 27348 | 18750 | 18640 | 37390 | 4966 | 10042 | 36.32% | 36.72% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
98 | Expense | GT&S | JO | GT Pipeline Maintenance | JOB | Cath Prot Monitoring | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C018 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 1289.5719 | 1317.1553 | 2606.7272 | 1882.3828 | 1862.6427 | 3745.0255 | 545.4874 | 1138.2983 | 41.41% | 43.67% | N/A | N/A | N/A | 13674 | 13674 | 27348 | 18750 | 18640 | 37390 | 4966 | 10042 | 36.32% | 36.72% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
99 | Expense | GT&S | JO | GT Pipeline Maintenance | JOB | Cath Prot Monitoring | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C007 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 1289.5719 | 1317.1553 | 2606.7272 | 1882.3828 | 1862.6427 | 3745.0255 | 545.4874 | 1138.2983 | 41.41% | 43.67% | N/A | N/A | N/A | 13674 | 13674 | 27348 | 18750 | 18640 | 37390 | 4966 | 10042 | 36.32% | 36.72% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
100 | Expense | GT&S | JO | GT Pipeline Maintenance | JOC | Cath Prot Troubleshoot | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 812.5347 | 829.9145 | 1642.4492 | 1299.7089 | 1520.4492 | 2820.1582 | 690.5348 | 1177.709 | 83.21% | 71.7% | NO | NO | # of troubleshoots | 1787 | 1787 | 3574 | 3032 | 3930 | 6962 | 2143 | 3388 | 119.9% | 94.8% | YES | N/A | Actual units were higher than Imputed units due to not factoring in TS resulting from the 850 Off Program or Troubleshoot priority change due to Mega Rule | Over | On-Target | On-Target | Proceeding as planned | Ongoing and will continue in PG&E's 2023 GRC period
101 | Expense | GT&S | JO | GT Pipeline Maintenance | JOC | Cath Prot Troubleshoot | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 812.5347 | 829.9145 | 1642.4492 | 1299.7089 | 1520.4492 | 2820.1582 | 690.5348 | 1177.709 | 83.21% | 71.7% | N/A | N/A | N/A | 1787 | 1787 | 3574 | 3032 | 3930 | 6962 | 2143 | 3388 | 119.9% | 94.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
102 | Expense | GT&S | JO | GT Pipeline Maintenance | JOE | Ground Leak Survey | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | annual | 989.5046 | 1010.6704 | 2000.175 | 637.2403 | 558.3158 | 1195.5561 | -452.3546 | -804.6188 | -44.76% | -40.23% | NO | NO | Miles Ground Leak Surveyed | 440 | 440 | 880 | 477 | 440 | 917 | 0 | 37 | 0% | 4.205% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
103 | Expense | GT&S | JO | GT Pipeline Maintenance | JOE | Ground Leak Survey | Loss of Containment on Gas Transmission Pipeline | LOCTM-C020 Transmission Leak Management | Ex 3, Ch 10 | No | On-Going | annual | 989.5046 | 1010.6704 | 2000.175 | 637.2403 | 558.3158 | 1195.5561 | -452.3546 | -804.6188 | -44.76% | -40.23% | N/A | N/A | N/A | 440 | 440 | 880 | 477 | 440 | 917 | 0 | 37 | 0% | 4.205% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
104 | Expense | GT&S | JO | GT Pipeline Maintenance | JOF | Requird Ground Pipeline Patrol | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1036.6933 | 1058.8459 | 2095.5392 | 842.5786 | 543.4369 | 1386.0155 | -515.4091 | -709.5238 | -48.68% | -33.86% | NO | NO | Hours | 10461 | 10461 | 20922 | 5880 | 3457 | 9337 | -7004 | -11585 | -66.95% | -55.37% | YES | N/A | REVIEW NEEDED - The units listed under "Units Actual" reflect observations, where the imputed reflects hours worked. The correct "Units Actual" is 3,457. The units are lower than imputed due to Ground Patrol shifting to Locate and Mark which reduced overtime and drive time. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform ground patrols in areas where the pipeline is visually obscured by vegetation from the view of aerial patrols. Additionally, ground patrols are performed to investigate aerial patrol observations that pose an immediate risk.
105 | Expense | GT&S | JO | GT Pipeline Maintenance | JOF | Requird Ground Pipeline Patrol | Loss of Containment on Gas Transmission Pipeline | LOCTM-C012 Required Pipeline Patrol Program | Ex 3, Ch 8 | No | On-Going | Annual | 1036.6933 | 1058.8459 | 2095.5392 | 842.5786 | 543.4369 | 1386.0155 | -515.4091 | -709.5238 | -48.68% | -33.86% | N/A | N/A | N/A | 10461 | 10461 | 20922 | 5880 | 3457 | 9337 | -7004 | -11585 | -66.95% | -55.37% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
106 | Expense | GT&S | JO | GT Pipeline Maintenance | JOG | PM G Regulator General | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 3956.9685 | 4041.5233 | 7998.4918 | 3671.0673 | 4147.8971 | 7818.9644 | 106.3737 | -179.5274 | 2.632% | -2.245% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
107 | Expense | GT&S | JO | GT Pipeline Maintenance | JOG | PM G Regulator General | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C020 Transmission Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 3956.9685 | 4041.5233 | 7998.4918 | 3671.0673 | 4147.8971 | 7818.9644 | 106.3737 | -179.5274 | 2.632% | -2.245% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
108 | Expense | GT&S | JO | GT Pipeline Maintenance | JOG | PM G Regulator General | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C014 Transmission Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 3956.9685 | 4041.5233 | 7998.4918 | 3671.0673 | 4147.8971 | 7818.9644 | 106.3737 | -179.5274 | 2.632% | -2.245% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
109 | Expense | GT&S | JO | GT Pipeline Maintenance | JOH | PM Gas Pipeline Valve Manual | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1495.4205 | 1527.3756 | 3022.7961 | 1448.5255 | 1412.6771 | 2861.2027 | -114.6985 | -161.5934 | -7.51% | -5.346% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
110 | Expense | GT&S | JO | GT Pipeline Maintenance | JOH | PM Gas Pipeline Valve Manual | Loss of Containment on Gas Transmission Pipeline | LOCTM-C013 PM Gas Pipeline Valves Program | Ex 3, Ch 8 | No | On-Going | Annual | 1495.4205 | 1527.3756 | 3022.7961 | 1448.5255 | 1412.6771 | 2861.2027 | -114.6985 | -161.5934 | -7.51% | -5.346% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
111 | Expense | GT&S | JO | GT Pipeline Maintenance | JOI | PM Gas Pipeline Valve Automate | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 39.5848 | 40.4306 | 80.0154 | 43.1587 | 59.5732 | 102.7319 | 19.1425 | 22.7164 | 47.35% | 28.39% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
112 | Expense | GT&S | JO | GT Pipeline Maintenance | JOI | PM Gas Pipeline Valve Automate | Loss of Containment on Gas Transmission Pipeline | LOCTM-C013 PM Gas Pipeline Valves Program | Ex 3, Ch 8 | No | On-Going | Annual | 39.5848 | 40.4306 | 80.0154 | 43.1587 | 59.5732 | 102.7319 | 19.1425 | 22.7164 | 47.35% | 28.39% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
113 | Expense | GT&S | JO | GT Pipeline Maintenance | JOJ | Gas Holders Maintenance | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 126.576 | 129.2807 | 255.8567 | 96.6035 | 77.4767 | 174.0802 | -51.8041 | -81.7765 | -40.07% | -31.96% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
114 | Expense | GT&S | JO | GT Pipeline Maintenance | JOJ | Gas Holders Maintenance | Loss of Containment on Gas Transmission Pipeline | LOCTM-C031 Gas Holder Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 126.576 | 129.2807 | 255.8567 | 96.6035 | 77.4767 | 174.0802 | -51.8041 | -81.7765 | -40.07% | -31.96% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
115 | Expense | GT&S | JO | GT Pipeline Maintenance | JOK | Oper Tranmission Pipelines | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 730.8928 | 746.511 | 1477.4039 | 439.9676 | 355.5278 | 795.4953 | -390.9833 | -681.9085 | -52.37% | -46.16% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
116 | Expense | GT&S | JO | GT Pipeline Maintenance | JOK | Oper Tranmission Pipelines | Loss of Containment on Gas Transmission Pipeline | LOCTM-C023 Operate Transmission Pipelines | Ex 3, Ch 8 | No | On-Going | Annual | 730.8928 | 746.511 | 1477.4039 | 439.9676 | 355.5278 | 795.4953 | -390.9833 | -681.9085 | -52.37% | -46.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
117 | Expense | GT&S | JO | GT Pipeline Maintenance | JOK | Oper Tranmission Pipelines | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C010 Operate Transmission Pipelines | Ex 3, Ch 8 | No | On-Going | Annual | 730.8928 | 746.511 | 1477.4039 | 439.9676 | 355.5278 | 795.4953 | -390.9833 | -681.9085 | -52.37% | -46.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
118 | Expense | GT&S | JO | GT Pipeline Maintenance | JOL | Oper Transmission Regl Station | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 461.3197 | 471.1774 | 932.4971 | 627.9131 | 861.0975 | 1489.0105 | 389.92 | 556.5134 | 82.75% | 59.68% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
119 | Expense | GT&S | JO | GT Pipeline Maintenance | JOL | Oper Transmission Regl Station | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C020 Transmission Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 461.3197 | 471.1774 | 932.4971 | 627.9131 | 861.0975 | 1489.0105 | 389.92 | 556.5134 | 82.75% | 59.68% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
120 | Expense | GT&S | JO | GT Pipeline Maintenance | JOL | Oper Transmission Regl Station | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C014 Transmission Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 461.3197 | 471.1774 | 932.4971 | 627.9131 | 861.0975 | 1489.0105 | 389.92 | 556.5134 | 82.75% | 59.68% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
121 | Expense | GT&S | JO | GT Pipeline Maintenance | JOM | CM G Regl Genl | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1117.1112 | 1140.9823 | 2258.0936 | 1276.3045 | 688.0491 | 1964.3535 | -452.9333 | -293.74 | -39.7% | -13.01% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
122 | Expense | GT&S | JO | GT Pipeline Maintenance | JOM | CM G Regl Genl | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C020 Transmission Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1117.1112 | 1140.9823 | 2258.0936 | 1276.3045 | 688.0491 | 1964.3535 | -452.9333 | -293.74 | -39.7% | -13.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
123 | Expense | GT&S | JO | GT Pipeline Maintenance | JOM | CM G Regl Genl | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C014 Transmission Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1117.1112 | 1140.9823 | 2258.0936 | 1276.3045 | 688.0491 | 1964.3535 | -452.9333 | -293.74 | -39.7% | -13.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
124 | Expense | GT&S | JO | GT Pipeline Maintenance | JON | CM Gas Pipeline Valve Manual | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 950.0092 | 970.3095 | 1920.3187 | 724.2313 | 783.6291 | 1507.8603 | -186.6805 | -412.4584 | -19.24% | -21.48% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
125 | Expense | GT&S | JO | GT Pipeline Maintenance | JON | CM Gas Pipeline Valve Manual | Loss of Containment on Gas Transmission Pipeline | LOCTM-C014 CM Gas Pipeline Valves Program | Ex 3, Ch 8 | No | On-Going | Annual | 950.0092 | 970.3095 | 1920.3187 | 724.2313 | 783.6291 | 1507.8603 | -186.6805 | -412.4584 | -19.24% | -21.48% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
126 | Expense | GT&S | JO | GT Pipeline Maintenance | JOO | CM Gas Pipeline Valve Automate | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 222.2539 | 227.0032 | 449.2571 | 603.8278 | 297.3552 | 901.183 | 70.352 | 451.9259 | 30.99% | 100.6% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
127 | Expense | GT&S | JO | GT Pipeline Maintenance | JOO | CM Gas Pipeline Valve Automate | Loss of Containment on Gas Transmission Pipeline | LOCTM-C014 CM Gas Pipeline Valves Program | Ex 3, Ch 8 | No | On-Going | Annual | 222.2539 | 227.0032 | 449.2571 | 603.8278 | 297.3552 | 901.183 | 70.352 | 451.9259 | 30.99% | 100.6% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
128 | Expense | GT&S | JO | GT Pipeline Maintenance | JOP | CM G Main Lk | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 11169.4509 | 11408.3688 | 22577.8196 | 1556.0525 | 932.3083 | 2488.3607 | -10476.0605 | -20089.4589 | -91.83% | -88.98% | YES | YES | # Leaks Repaired | 3281 | 3281 | 6562 | 1041 | 585 | 1626 | -2696 | -4936 | -82.17% | -75.22% | YES | Actual costs were lower than imputed due to decreased leak find rates in the last three years resulting in reduced leak finds and repairs. A second factor driving cost down is the implementation of process improvement initiatives such as leak bundling. | Actual units lower than imputed due to decreased leak find rates in the last three years resulting in reduced leak finds and repairs. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to fix gradeable transmission leaks that require TLA type of repairs.
129 | Expense | GT&S | JO | GT Pipeline Maintenance | JOP | CM G Main Lk | Loss of Containment on Gas Transmission Pipeline | LOCTM-C020 Transmission Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 11169.4509 | 11408.3688 | 22577.8196 | 1556.0525 | 932.3083 | 2488.3607 | -10476.0605 | -20089.4589 | -91.83% | -88.98% | N/A | N/A | N/A | 3281 | 3281 | 6562 | 1041 | 585 | 1626 | -2696 | -4936 | -82.17% | -75.22% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
130 | Expense | GT&S | JO | GT Pipeline Maintenance | JOQ | Cath Protection Corr Maintnc | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 357.9554 | 365.6119 | 723.5673 | 353.6694 | 408.7493 | 762.4187 | 43.1374 | 38.8514 | 11.8% | 5.369% | NO | NO | # of corrective work orders completed | 324 | 324 | 648 | 237 | 302 | 539 | -22 | -109 | -6.79% | -16.82% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
131 | Expense | GT&S | JO | GT Pipeline Maintenance | JOQ | Cath Protection Corr Maintnc | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 357.9554 | 365.6119 | 723.5673 | 353.6694 | 408.7493 | 762.4187 | 43.1374 | 38.8514 | 11.8% | 5.369% | N/A | N/A | N/A | 324 | 324 | 648 | 237 | 302 | 539 | -22 | -109 | -6.79% | -16.82% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
132 | Expense | GT&S | JO | GT Pipeline Maintenance | JOR | Leak Rechecks | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 264.4926 | 270.1502 | 534.6428 | 75.6114 | 24.1365 | 99.7479 | -246.0136 | -434.8949 | -91.07% | -81.34% | NO | NO | # of Rechecks Performed | 2816 | 2816 | 5632 | 884 | 574 | 1458 | -2242 | -4174 | -79.62% | -74.11% | YES | N/A | Actual units were lower than imputed due to accelerated repair timeframes driven by the CARB rules and regulations. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
133 | Expense | GT&S | JO | GT Pipeline Maintenance | JOR | Leak Rechecks | Loss of Containment on Gas Transmission Pipeline | LOCTM-C020 Transmission Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 264.4926 | 270.1502 | 534.6428 | 75.6114 | 24.1365 | 99.7479 | -246.0136 | -434.8949 | -91.07% | -81.34% | N/A | N/A | N/A | 2816 | 2816 | 5632 | 884 | 574 | 1458 | -2242 | -4174 | -79.62% | -74.11% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
134 | Expense | GT&S | JO | GT Pipeline Maintenance | JOS | Pipeline Marker Maintenance | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1761.9545 | 1799.605 | 3561.5595 | 912.0574 | 899.5781 | 1811.6355 | -900.027 | -1749.924 | -50.01% | -49.13% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | 1522 | 1522 | 1522 | 1522 | 0% | 0% | NO | N/A | Actual units were higher than imputed due to this MAT not previously being unitized. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This program involves installing, replacing and maintaining transmission pipeline markers.
135 | Expense | GT&S | JO | GT Pipeline Maintenance | JOS | Pipeline Marker Maintenance | Loss of Containment on Gas Transmission Pipeline | LOCTM-C015 Pipeline Marker Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1761.9545 | 1799.605 | 3561.5595 | 912.0574 | 899.5781 | 1811.6355 | -900.027 | -1749.924 | -50.01% | -49.13% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1522 | 1522 | 1522 | 1522 | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
136 | Expense | GT&S | JO | GT Pipeline Maintenance | JOT | Vegetation Management | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1521.5369 | 1554.05 | 3075.5869 | 1446.9457 | 1569.2983 | 3016.244 | 15.2483 | -59.3429 | 0.9812% | -1.929% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
137 | Expense | GT&S | JO | GT Pipeline Maintenance | JOT | Vegetation Management | Loss of Containment on Gas Transmission Pipeline | LOCTM-C016 Vegetation Management | Ex 3, Ch 8 | No | On-Going | Annual | 1521.5369 | 1554.05 | 3075.5869 | 0 | 1569.2983 | 1569.2983 | 15.2483 | -1506.2886 | 0.9812% | -48.98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
138 | Expense | GT&S | JO | GT Pipeline Maintenance | JOT | Vegetation Management | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C011 Vegetation Management | Ex 3, Ch 8 | No | On-Going | Annual | 1521.5369 | 1554.05 | 3075.5869 | 1446.9457 | 1569.2983 | 3016.244 | 15.2483 | -59.3429 | 0.9812% | -1.929% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
139 | Expense | GT&S | JO | GT Pipeline Maintenance | JOT | Vegetation Management | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C008 Vegetation Management | Ex 3, Ch 8 | No | On-Going | Annual | 1521.5369 | 1554.05 | 3075.5869 | 1446.9457 | 1569.2983 | 3016.244 | 15.2483 | -59.3429 | 0.9812% | -1.929% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
140 | Expense | GT&S | JO | GT Pipeline Maintenance | JOV | Requird Aerial Pipeline Patrol | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 4822.7535 | 4925.809 | 9748.5625 | 2450.6265 | 2278.5588 | 4729.1853 | -2647.2502 | -5019.3772 | -53.74% | -51.49% | NO | NO | Miles Aerial Patroled | 125656 | 125656 | 251312 | 25769.49 | 25724 | 51493.49 | -99932 | -199818.51 | -79.53% | -79.51% | YES | N/A | Actual units were lower than imputed units due to a change in the patrol frequency from monthly to quarterly, in alignment with regulatory requirements. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to observe surface conditions on and adjacent to the pipeline ROW for factors affecting safety and operations.
141 | Expense | GT&S | JO | GT Pipeline Maintenance | JOV | Requird Aerial Pipeline Patrol | Loss of Containment on Gas Transmission Pipeline | LOCTM-C012 Required Pipeline Patrol Program | Ex 3, Ch 8 | No | On-Going | Annual | 4822.7535 | 4925.809 | 9748.5625 | 2450.6265 | 2278.5588 | 4729.1853 | -2647.2502 | -5019.3772 | -53.74% | -51.49% | N/A | N/A | N/A | 125656 | 125656 | 251312 | 25769 | 25724 | 51493 | -99932 | -199819 | -79.53% | -79.51% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
142 | Expense | GT&S | JO | GT Pipeline Maintenance | JOW | Aerial Leak Survey | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | annual | 2493.68 | 2547.0206 | 5040.7006 | 1653.8888 | 1710.4059 | 3364.2947 | -836.6146 | -1676.4058 | -32.85% | -33.26% | NO | NO | Miles Aerial Leak Surveyed | 12807 | 12807 | 25614 | 12487 | 12608 | 25095 | -199 | -519 | -1.554% | -2.026% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
143 | Expense | GT&S | JO | GT Pipeline Maintenance | JOW | Aerial Leak Survey | Loss of Containment on Gas Transmission Pipeline | LOCTM-C020 Transmission Leak Management | Ex 3, Ch 10 | No | On-Going | annual | 2493.68 | 2547.0206 | 5040.7006 | 1653.8888 | 1710.4059 | 3364.2947 | -836.6146 | -1676.4058 | -32.85% | -33.26% | N/A | N/A | N/A | 12807 | 12807 | 25614 | 12487 | 12608 | 25095 | -199 | -519 | -1.554% | -2.026% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
144 | Expense | GT&S | JO | GT Pipeline Maintenance | JOX | PM Meter Maintenance | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1948.5289 | 1990.1662 | 3938.6951 | 2247.6943 | 2202.0198 | 4449.7141 | 211.8535 | 511.019 | 10.65% | 12.97% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
145 | Expense | GT&S | JO | GT Pipeline Maintenance | JOX | PM Meter Maintenance | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C012 Meter Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1948.5289 | 1990.1662 | 3938.6951 | 2247.6943 | 2202.0198 | 4449.7141 | 211.8535 | 511.019 | 10.65% | 12.97% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
146 | Expense | GT&S | JO | GT Pipeline Maintenance | JOY | CM Meter Maintenance | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 288.8485 | 295.0208 | 583.8692 | 301.7828 | 357.2075 | 658.9902 | 62.1867 | 75.121 | 21.08% | 12.87% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
147 | Expense | GT&S | JO | GT Pipeline Maintenance | JOY | CM Meter Maintenance | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C012 Meter Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 288.8485 | 295.0208 | 583.8692 | 301.7828 | 357.2075 | 658.9902 | 62.1867 | 75.121 | 21.08% | 12.87% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
148 | Expense | GT&S | JO | GT Pipeline Maintenance | JOZ | Atmospheric Corrosion Inspect | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 500.2251 | 510.9247 | 1011.1498 | 87.9126 | 186.7792 | 274.6917 | -324.1455 | -736.458 | -63.44% | -72.83% | NO | NO | # of spans patrolled | 487 | 487 | 974 | 226 | 390 | 616 | -97 | -358 | -19.92% | -36.76% | NO | N/A | Actual units were lower than imputed due to original forecast was based on 2023 planned units. Variance is due to less spans in the field than originally input into the maintenance plan in 2020. Additionally, 33 units were recorded as MAT JOB due to object types reflecting Span_U; 3 units were recorded as MAT 34A because they are located at Stanpac Functional Location in the system | Under | On-Target | On-Target | Proceeding as planned | Ongoing and will continue in PG&E's 2023 GRC period
149 | Expense | GT&S | JO | GT Pipeline Maintenance | JOZ | Atmospheric Corrosion Inspect | Loss of Containment on Gas Transmission Pipeline | LOCTM-C034 Atmospheric Corrosion Program | Ex 3, Ch 9 | No | On-Going | Annual | 500.2251 | 510.9247 | 1011.1498 | 87.9126 | 186.7792 | 274.6917 | -324.1455 | -736.458 | -63.44% | -72.83% | N/A | N/A | N/A | 487 | 487 | 974 | 226 | 390 | 616 | -97 | -358 | -19.92% | -36.76% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
150 | Expense | GT&S | JP | GT Station Maintenance | JPA | PM StorCompStat Piping Assets | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 980.5475 | 1000.7219 | 1981.2694 | 1222.2772 | 1361.3641 | 2583.6413 | 360.6422 | 602.3719 | 36.04% | 30.4% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
151 | Expense | GT&S | JP | GT Station Maintenance | JPA | PM StorCompStat Piping Assets | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 980.5475 | 1000.7219 | 1981.2694 | 1222.2772 | 1361.3641 | 2583.6413 | 360.6422 | 602.3719 | 0.36038 | 0.30403 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
152 | Expense | GT&S | JP | GT Station Maintenance | JPB | CM StorCompStat Piping Assets | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 473.1163 | 482.8505 | 955.9669 | 187.997 | 137.6769 | 325.6739 | -345.1736 | -630.293 | -0.71487 | -0.65933 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
153 | Expense | GT&S | JP | GT Station Maintenance | JPB | CM StorCompStat Piping Assets | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 473.1163 | 482.8505 | 955.9669 | 187.997 | 137.6769 | 325.6739 | -345.1736 | -630.293 | -0.71487 | -0.65933 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
154 | Expense | GT&S | JP | GT Station Maintenance | JPC | PM StorCompStat GasProcess | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1919.6246 | 1959.1202 | 3878.7448 | 2374.9648 | 1986.8205 | 4361.7854 | 27.7004 | 483.0406 | 0.014139 | 0.12454 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
155 | Expense | GT&S | JP | GT Station Maintenance | JPC | PM StorCompStat GasProcess | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 1919.6246 | 1959.1202 | 3878.7448 | 2374.9648 | 1986.8205 | 4361.7854 | 27.7004 | 483.0406 | 0.014139 | 0.12454 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
156 | Expense | GT&S | JP | GT Station Maintenance | JPD | PM StorCompStat GasCompressor | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1810.2541 | 1847.4995 | 3657.7536 | 3335.1249 | 3142.0609 | 6477.1858 | 1294.5614 | 2819.4322 | 0.70071 | 0.77081 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
157 | Expense | GT&S | JP | GT Station Maintenance | JPD | PM StorCompStat GasCompressor | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 1810.2541 | 1847.4995 | 3657.7536 | 3335.1249 | 3142.0609 | 6477.1858 | 1294.5614 | 2819.4322 | 0.70071 | 0.77081 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
158 | Expense | GT&S | JP | GT Station Maintenance | JPE | PM StorCompStat Support | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 2279.9418 | 2326.8508 | 4606.7926 | 2467.8784 | 2163.3478 | 4631.2262 | -163.503 | 24.4337 | -0.070268 | 0.0053038 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
159 | Expense | GT&S | JP | GT Station Maintenance | JPE | PM StorCompStat Support | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 2279.9418 | 2326.8508 | 4606.7926 | 2467.8784 | 2163.3478 | 4631.2262 | -163.503 | 24.4337 | -0.070268 | 0.0053038 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
160 | Expense | GT&S | JP | GT Station Maintenance | JPG | CM StorCompStat GasProcess | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 983.5494 | 1003.7856 | 1987.335 | 1628.4306 | 1158.3776 | 2786.8081 | 154.592 | 799.4731 | 0.15401 | 0.40228 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
161 | Expense | GT&S | JP | GT Station Maintenance | JPG | CM StorCompStat GasProcess | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 983.5494 | 1003.7856 | 1987.335 | 1628.4306 | 1158.3776 | 2786.8081 | 154.592 | 799.4731 | 0.15401 | 0.40228 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
162 | Expense | GT&S | JP | GT Station Maintenance | JPH | CM StorCompStat GasCompress | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 2071.3098 | 2113.9263 | 4185.2361 | 2625.2979 | 2996.4714 | 5621.7693 | 882.5451 | 1436.5332 | 0.41749 | 0.34324 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
163 | Expense | GT&S | JP | GT Station Maintenance | JPH | CM StorCompStat GasCompress | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 2071.3098 | 2113.9263 | 4185.2361 | 2625.2979 | 2996.4714 | 5621.7693 | 882.5451 | 1436.5332 | 0.41749 | 0.34324 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
164 | Expense | GT&S | JP | GT Station Maintenance | JPI | CM StorCompStat Support | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1525.448 | 1556.8335 | 3082.2815 | 687.9186 | 572.2763 | 1260.1949 | -984.5572 | -1822.0866 | -0.63241 | -0.59115 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
165 | Expense | GT&S | JP | GT Station Maintenance | JPI | CM StorCompStat Support | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 1525.448 | 1556.8335 | 3082.2815 | 687.9186 | 572.2763 | 1260.1949 | -984.5572 | -1822.0866 | -0.63241 | -0.59115 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
166 | Expense | GT&S | JP | GT Station Maintenance | JPK | PM Power Units | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 139.2082 | 142.0724 | 281.2806 | 330.4969 | 176.3057 | 506.8026 | 34.2333 | 225.522 | 0.24096 | 0.80177 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
167 | Expense | GT&S | JP | GT Station Maintenance | JPK | PM Power Units | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C015 Power Units Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 139.2082 | 142.0724 | 281.2806 | 330.4969 | 176.3057 | 506.8026 | 34.2333 | 225.522 | 0.24096 | 0.80177 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
168 | Expense | GT&S | JP | GT Station Maintenance | JPL | CM Power Units | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 276.8857 | 282.5825 | 559.4682 | 386.6086 | 452.062 | 838.6706 | 169.4795 | 279.2024 | 0.59975 | 0.49905 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
169 | Expense | GT&S | JP | GT Station Maintenance | JPL | CM Power Units | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C015 Power Units Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 276.8857 | 282.5825 | 559.4682 | 386.6086 | 452.062 | 838.6706 | 169.4795 | 279.2024 | 0.59975 | 0.49905 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
170 | Expense | GT&S | JP | GT Station Maintenance | JPN | Station Operations | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 6026.6487 | 6150.6448 | 12177.2936 | 6033.303 | 6531.002 | 12564.3049 | 380.3572 | 387.0114 | 0.06184 | 0.031781 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
171 | Expense | GT&S | JP | GT Station Maintenance | JPN | Station Operations | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C007 Station Operations | Ex 3, Ch 8 | No | On-Going | Annual | 6026.6487 | 6150.6448 | 12177.2936 | 6033.303 | 6531.002 | 12564.3049 | 380.3572 | 387.0114 | 0.06184 | 0.031781 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
172 | Expense | GT&S | JP | GT Station Maintenance | JPN | Station Operations | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C016 Station Operations | Ex 3, Ch 8 | No | On-Going | Annual | 6026.6487 | 6150.6448 | 12177.2936 | 6033.303 | 6531.002 | 12564.3049 | 380.3572 | 387.0114 | 0.06184 | 0.031781 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
173 | Expense | GT&S | JP | GT Station Maintenance | JPO | PM Storage Wells | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 570.257 | 581.9898 | 1152.2468 | 384.923 | 330.7638 | 715.6868 | -251.226 | -436.56 | -0.43167 | -0.37888 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
174 | Expense | GT&S | JP | GT Station Maintenance | JPO | PM Storage Wells | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C005 Preventive and Corrective Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 570.257 | 581.9898 | 1152.2468 | 384.923 | 330.7638 | 715.6868 | -251.226 | -436.56 | -0.43167 | -0.37888 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
175 | Expense | GT&S | JP | GT Station Maintenance | JPP | CM Storage Wells | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 81.2991 | 82.9718 | 164.2709 | 9.7878 | 69.4431 | 79.2309 | -13.5287 | -85.04 | -0.16305 | -0.51768 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
176 | Expense | GT&S | JP | GT Station Maintenance | JPP | CM Storage Wells | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C005 Preventive and Corrective Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 81.2991 | 82.9718 | 164.2709 | 9.7878 | 69.4431 | 79.2309 | -13.5287 | -85.04 | -0.16305 | -0.51768 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
177 | Expense | GT&S | JP | GT Station Maintenance | JPQ | CARB Leak Survey | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | annual | 3270.321 | 3337.6128 | 6607.9337 | 3332.4759 | 3756.9934 | 7089.4693 | 419.3806 | 481.5355 | 0.12565 | 0.072872 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
178 | Expense | GT&S | JP | GT Station Maintenance | JPQ | CARB Leak Survey | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C006 CARB Leak Management | Ex 3, Ch 10 | No | On-Going | annual | 3270.321 | 3337.6128 | 6607.9337 | 3332.4759 | 3756.9934 | 7089.4693 | 419.3806 | 481.5355 | 0.12565 | 0.072872 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
179 | Expense | GT&S | JP | GT Station Maintenance | JPR | CARB Leak Repairs | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 2544.7033 | 2597.0645 | 5141.7678 | 416.1063 | 504.534 | 920.6403 | -2092.5305 | -4221.1275 | -0.80573 | -0.82095 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
180 | Expense | GT&S | JP | GT Station Maintenance | JPR | CARB Leak Repairs | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 10 | No | On-Going | Annual | 2544.7033 | 2597.0645 | 5141.7678 | 416.1063 | 504.534 | 920.6403 | -2092.5305 | -4221.1275 | -0.80573 | -0.82095 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
181 | Expense | GT&S | JP | GT Station Maintenance | JPR | CARB Leak Repairs | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C006 CARB Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 2544.7033 | 2597.0645 | 5141.7678 | 416.1063 | 504.534 | 920.6403 | -2092.5305 | -4221.1275 | -0.80573 | -0.82095 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
182 | Expense | GT&S | JP | GT Station Maintenance | JP#(c) | Not assigned | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 0 | 0 | 0 | 401.0857 | 0.35357 | 401.4393 | 0.35357 | 401.4393 | 0% | N/A | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
183 | Expense | GT&S | JT | GT Reliability & General Maint | JT0 | Public Awareness | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 3436.5769 | 3473.6995 | 6910.2764 | 2117.3198 | 1995.4611 | 4112.781 | -1478.2384 | -2797.4954 | -0.42555 | -0.40483 | NO | NO | non-unitized: This MAT has no measurable units because it is our funding for the Public Awareness program management. This MAT supports the outreach required pursuant to API RP 1162 which contains many activities to include direct mailings to parties with properties within 1000’ of a pipeline, other educational material publication, social media postings, etc. This program also manages our Public Awareness and Damage Prevention program documentation. There are no specific units associated with the activities performed in the Public Awareness MAT to meet the requirements of RP 1162. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
184 | Expense | GT&S | JT | GT Reliability & General Maint | JT0 | Public Awareness | Loss of Containment on Gas Transmission Pipeline | LOCTM-C011 Public Awareness | Ex 3, Ch 5 | No | On-Going | Annual | 3436.5769 | 3473.6995 | 6910.2764 | 2117.3198 | 1995.4611 | 4112.781 | -1478.2384 | -2797.4954 | -0.42555 | -0.40483 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
185 | Expense | GT&S | JT | GT Reliability & General Maint | JT1 | Engineering Support | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 2572.1801 | 2599.9653 | 5172.1453 | -33.8536 | 23.2923 | -10.5613 | -2576.673 | -5182.7066 | -0.99104 | -1.002 | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for various types of non-capitalizable work related to pipe investigations and field engineering support. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is pipeline engineering support to perform pipe investigations.
186 | Expense | GT&S | JT | GT Reliability & General Maint | JT1 | Engineering Support | Loss of Containment on Gas Transmission Pipeline | LOCTM-C027 Pipe Investigations and Field Engineering | Ex 3, Ch 5 | No | On-Going | Annual | 2572.1801 | 2599.9653 | 5172.1453 | -33.8536 | 23.2923 | -10.5613 | -2576.673 | -5182.7066 | -0.99104 | -1.002 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
187 | Expense | GT&S | JT | GT Reliability & General Maint | JT2 | Water and Levee Crossings | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | annual | 1386.5269 | 1401.5044 | 2788.0312 | 465.6519 | 553.6942 | 1019.3462 | -847.8101 | -1768.6851 | -0.60493 | -0.63438 | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for monitoring jurisdictional water crossings, jurisdictional levee crossings, and non-jurisdictional water crossings. The type of work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
188 | Expense | GT&S | JT | GT Reliability & General Maint | JT2 | Water and Levee Crossings | Loss of Containment on Gas Transmission Pipeline | LOCTM-C007 Shallow and Exposed Pipe (Including Water and Levee Crossing | Ex 3, Ch 5 | No | On-Going | annual | 1386.5269 | 1401.5044 | 2788.0312 | 465.6519 | 553.6942 | 1019.3462 | -847.8101 | -1768.6851 | -0.60493 | -0.63438 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
189 | Expense | GT&S | JT | GT Reliability & General Maint | JT3(i) | Fault Crossings | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 1076.1995 | 1087.8248 | 2164.0244 | 180.2654 | 147.798 | 328.0635 | -940.0268 | -1835.9609 | -0.86413 | -0.8484 | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for conducting studies of where gas transmission pipelines cross active and potentially active earthquake fault lines, and monitoring fault creep. The type of work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
190 | Expense | GT&S | JT | GT Reliability & General Maint | JT3(i) | Fault Crossings | Loss of Containment on Gas Transmission Pipeline | LOCTM-C004 Earthquake Fault Crossings | Ex 3, Ch 5 | No | On-Going | Annual | 1076.1995 | 1087.8248 | 2164.0244 | 180.2654 | 147.798 | 328.0635 | -940.0268 | -1835.9609 | -0.86413 | -0.8484 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
191 | Expense | GT&S | JT | GT Reliability & General Maint | JT4 | Shallow and Exposed Pipe | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | annual | 2751.2681 | 2780.9878 | 5532.256 | 942.1452 | 234.9186 | 1177.0638 | -2546.0692 | -4355.1921 | -0.91553 | -0.78724 | NO | NO | Projects | 4 | 4 | 8 | 1 | 0 | 1 | -4 | -7 | -100% | -87.5% | YES | N/A | Actual units were lower than Imputed units due to no projects were executed under this MAT, as funds were reallocated to other risk and compliance-driven programs. Additionally, the planned Project A-513 was canceled due to a low likelihood of further erosion at the site, which is being monitored under the TIMP Geohazards Program. | Under | On-Target | On-Target | Proceeding as planned | This programs work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to mitigate locations where a pipeline has insufficient cover, is vulnerable to damage from third parties, or has become exposed due to natural forces.
192 | Expense | GT&S | JT | GT Reliability & General Maint | JT4 | Shallow and Exposed Pipe | Loss of Containment on Gas Transmission Pipeline | LOCTM-C007 Shallow and Exposed Pipe (Including Water and Levee Crossing | Ex 3, Ch 5 | No | On-Going | annual | 2751.2681 | 2780.9878 | 5532.256 | 942.1452 | 234.9186 | 1177.0638 | -2546.0692 | -4355.1921 | -0.91553 | -0.78724 | N/A | N/A | N/A | 4 | 4 | 8 | 1 | 0 | 1 | -4 | -7 | -100% | -87.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
193 | Expense | GT&S | JT | GT Reliability & General Maint | JT6 | Pipe Replacements - (<50Ft) | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 11283.8702 | 11405.7607 | 22689.6309 | 697.6098 | 139.1123 | 836.7221 | -11266.6484 | -21852.9088 | -0.9878 | -0.96312 | YES | YES | Miles | 0.17 | 0 | 0.17 | 0 | 0 | 0 | 0 | -0.17 | 0% | -100% | NO | Actual costs were lower than imputed because less work materialized owing to more scopes of work that reached 50 foot threshold for Capitalization. | Actual units were less than imputed because less work materialized owing to more scopes of work that reached 50 foot threshold for Capitalization. | Under | On-Target | Under | Proceeding as planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to implement Non-TIMP expense pipe replacements as an alternative option to strength testing.
194 | Expense | GT&S | JT | GT Reliability & General Maint | JT6 | Pipe Replacements - (<50Ft) | Loss of Containment on Gas Transmission Pipeline | LOCTM-M003 Non-TIMP Strength Testing | Ex 3, Ch 5 | No | On-Going | Annual | 11283.8702 | 11405.7607 | 22689.6309 | 697.6098 | 139.1123 | 836.7221 | -11266.6484 | -21852.9088 | -0.9878 | -0.96312 | N/A | N/A | N/A | 0.17 | 0 | 0.17 | 0 | 0 | 0 | 0 | -0.17 | 0% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
195 | Expense | GT&S | JT | GT Reliability & General Maint | JT8 | Gas Quality Assessment - Exp | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-Going | Annual | 2124.3321 | 2146.4864 | 4270.8185 | 1559.8324 | 2731.3066 | 4291.139 | 584.8202 | 20.3204 | 0.27245 | 0.004758 | NO | NO | non-unitized: This MAT has no measurable units because MAT includes programmatic costs for ongoing activities which are not unitized. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
196 | Expense | GT&S | JT | GT Reliability & General Maint | JT8 | Gas Quality Assessment - Exp | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C005 Gas Quality Assessment - Expense | Ex 3, Ch 6 | No | On-Going | Annual | 2124.3321 | 2146.4864 | 4270.8185 | 1559.8324 | 2731.3066 | 4291.139 | 584.8202 | 20.3204 | 0.27245 | 0.004758 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
197 | Expense | GT&S | JT | GT Reliability & General Maint | JT8 | Gas Quality Assessment - Exp | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C027 Gas Quality Assessment - Expense | Ex 3, Ch 6 | No | On-Going | Annual | 2124.3321 | 2146.4864 | 4270.8185 | 1559.8324 | 2731.3066 | 4291.139 | 584.8202 | 20.3204 | 0.27245 | 0.004758 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
198 | Expense | GT&S | JT | GT Reliability & General Maint | JT9 | Hydrostatic Tstng - Class Lctn | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 899.4658 | 909.182 | 1808.6478 | 179.0848 | 4148.3875 | 4327.4723 | 3239.2056 | 2518.8246 | 3.5628 | 1.3927 | NO | NO | non-unitized: This MAT has no measurable units because mitigation lengths for class location change cannot be ascertained until the completion of annual class location studies. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
199 | Expense | GT&S | JT | GT Reliability & General Maint | JT9 | Hydrostatic Tstng - Class Lctn | Loss of Containment on Gas Transmission Pipeline | LOCTM-C025 Class Location Change | Ex 3, Ch 5 | No | On-Going | Annual | 899.4658 | 909.182 | 1808.6478 | 179.0848 | 4148.3875 | 4327.4723 | 3239.2056 | 2518.8246 | 3.5628 | 1.3927 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
200 | Expense | GT&S | JT | GT Reliability & General Maint | JTB | Pipeline Repair | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 6834.6356 | 6908.4645 | 13743.1001 | 4751.8962 | 12361.05 | 17112.9462 | 5452.5855 | 3369.8461 | 0.78926 | 0.2452 | NO | YES | non-unitized: This MAT has no measurable units because it is used to record costs for various types of expense work related to TIMP pipeline repair. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | Actual costs were higher than imputed due to more than anticipated higher-risk or compliance-driven repairs and replacement shorter than 50 feet | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to mitigate graded leaks and reliability risks along gas transmission pipelines.
201 | Expense | GT&S | JT | GT Reliability & General Maint | JTB | Pipeline Repair | Loss of Containment on Gas Transmission Pipeline | LOCTM-C008 Pipeline Safety and Reliability | Ex 3, Ch 5 | No | On-Going | Annual | 6834.6356 | 6908.4645 | 13743.1001 | 4751.8962 | 12361.05 | 17112.9462 | 5452.5855 | 3369.8461 | 0.78926 | 0.2452 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
202 | Expense | GT&S | JT | GT Reliability & General Maint | JTD | Pipeline Other | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 18984.9792 | 19190.0584 | 38175.0376 | 4525.1633 | 5400.3807 | 9925.5441 | -13789.6777 | -28249.4935 | -0.71858 | -0.74 | YES | YES | non-unitized: This MAT has no measurable units because it is used to record costs for various types of expense work related to TIMP pipeline investigation. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | Actual costs were lower than imputed due to overestimated execution in the 2023 rate case, driven by uncertainty around Mega Rule Part 1 (RIN1) compliance. In practice, compliance was achieved at much lower cost. Additional savings came from deferring lower-risk investigations to prioritize higher-risk, non-JTD work, while maintaining RIN1 and JTD compliance. | N/A | On-Target | On-Target | Under | Proceeding as planned | This JTD Pipe Investigations program's work is ongoing and will continue in PG&E's 2027 GRC period. The purpose of this program is to perform material properties testing, verify pipeline segments and fittings, establish MAOP to comply with 49 CFR § 192.619 by validating unknown or assumed pipe and fitting specifications and potentially mitigating MAOP Design and underrated pipe issues, perform data validation, perform research for valid and invalid strength test records and pipeline material records, manage Opportunistic Inspection Program (OIP) and targeted inspections to comply with federal codes 49 CFR § 192.607 and § 192.712, investigate anomalous conditions and potential mechanical damage, and investigate cause and extent of failures or incidents to comply with 49 CFR § 192.617. This JTD program will continue to be medium priority compared to other gas tranmission pipe programs.
203 | Expense | GT&S | JT | GT Reliability & General Maint | JTD | Pipeline Other | Loss of Containment on Gas Transmission Pipeline | LOCTM-C027 Pipe Investigations and Field Engineering | Ex 3, Ch 5 | No | On-Going | Annual | 18984.9792 | 19190.0584 | 38175.0376 | 4525.1633 | 5400.3807 | 9925.5441 | -13789.6777 | -28249.4935 | -0.71858 | -0.74 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
204 | Expense | GT&S | JT | GT Reliability & General Maint | JTH | Permits & Fees Projects | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 8 | No | On-Going | Annual | 7906.4386 | 7991.8318 | 15898.2704 | 8973.6743 | 9450.8214 | 18424.4956 | 1458.9895 | 2526.2252 | 0.18256 | 0.1589 | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for permits and fees associated with the operations of Gas Transmission stations. (Examples include McDonald Island Reclamation Fees, Gas Lease Fees, Department of Transportation Fees). | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
205 | Expense | GT&S | JT | GT Reliability & General Maint | JTK | Vegetation Manage Project | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 16877.2154 | 17059.4972 | 33936.7126 | 7397.9605 | 5357.349 | 12755.3096 | -11702.1482 | -21181.4031 | -0.68596 | -0.62414 | YES | YES | Non-unitized: This MAT has no measurable units because this MAT includes a mix of work involved in maintaining transmission Right-Of-Ways (ROW), some of which can be tracked in units (ex: tree removals), while some cannot like inspections. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | Actual costs were lower than imputed due to work reprioritization driven by Transmission Integrity Management Program, the budget was reduced by $11M. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to support the safety and integrity of gas pipeline by inspecting, removing and maintaining vegetation in the ROW. This program continues to be reassessed for its priority relative to other emerging work and is rescheduled accordingly.
206 | Expense | GT&S | JT | GT Reliability & General Maint | JTK | Vegetation Manage Project | Loss of Containment on Gas Transmission Pipeline | LOCTM-C017 Vegetation Manage Project | Ex 3, Ch 8 | No | On-Going | Annual | 16877.2154 | 17059.4972 | 33936.7126 | 7397.9605 | 5357.349 | 12755.3096 | -11702.1482 | -21181.4031 | -0.68596 | -0.62414 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
207 | Expense | GT&S | JT | GT Reliability & General Maint | JTL | FIMP Risk Management | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-Going | Annual | 2790.5397 | 2819.6418 | 5610.1815 | 1842.9263 | 1746.991 | 3589.9173 | -1072.6507 | -2020.2642 | -0.38042 | -0.36011 | NO | NO | non-unitized: This MAT has no measurable units because MAT includes programmatic costs for ongoing activities which are not unitized. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
208 | Expense | GT&S | JT | GT Reliability & General Maint | JTL | FIMP Risk Management | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C006 FIMP Risk Assessment | Ex 3, Ch 6 | No | On-Going | Annual | 2790.5397 | 2819.6418 | 5610.1815 | 1842.9263 | 1746.991 | 3589.9173 | -1072.6507 | -2020.2642 | -0.38042 | -0.36011 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
209 | Expense | GT&S | JT | GT Reliability & General Maint | JTL | FIMP Risk Management | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C022 FIMP Risk Assessment | Ex 3, Ch 6 | No | On-Going | Annual | 2790.5397 | 2819.6418 | 5610.1815 | 1842.9263 | 1746.991 | 3589.9173 | -1072.6507 | -2020.2642 | -0.38042 | -0.36011 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
210 | Expense | GT&S | JT | GT Reliability & General Maint | JTM | Uprates | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 997.7546 | 1008.5804 | 2006.335 | 72.0873 | 3321.1296 | 3393.2169 | 2312.5492 | 1386.8819 | 2.2929 | 0.69125 | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs to increase capacity of a hydraulically independent system as an alternative to increasing capacity by installing new facilities. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
211 | Expense | GT&S | JT | GT Reliability & General Maint | JTM | Uprates | Insufficient Capacity to Meet Customer Demand | CPCTY-M004 GT Capacity Uprates | Ex 3, Ch 11 | No | On-Going | Annual | 997.7546 | 1008.5804 | 2006.335 | 72.0873 | 3321.1296 | 3393.2169 | 2312.5492 | 1386.8819 | 2.2929 | 0.69125 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
212 | Expense | GT&S | JT | GT Reliability & General Maint | JTO | Encroachments Structures & ROW | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1264.5425 | 1278.2002 | 2542.7427 | 981.8896 | 1393.9931 | 2375.8827 | 115.7929 | -166.8599 | 0.090591 | -0.065622 | NO | NO | non-unitized: This MAT has no measurable units because it combines different workstreams, access roads and structural encroachments, in a single MAT. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
213 | Expense | GT&S | JT | GT Reliability & General Maint | JTO | Encroachments Structures & ROW | Loss of Containment on Gas Transmission Pipeline | LOCTM-C018 Encroachments | Ex 3, Ch 8 | No | On-Going | Annual | 1264.5425 | 1278.2002 | 2542.7427 | 981.8896 | 1393.9931 | 2375.8827 | 115.7929 | -166.8599 | 0.090591 | -0.065622 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
214 | Expense | GT&S | JT | GT Reliability & General Maint | JTQ | Class Location Studies | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 2185.0905 | 2208.6942 | 4393.7847 | 1588.1424 | 1580.8793 | 3169.0217 | -627.8149 | -1224.763 | -0.28425 | -0.27875 | NO | NO | non-unitized: This MAT has no measurable units because it is an continuous, annual class location study. The annual class location study includes: orthographically-corrected aerial photography; occupancy field verification; creation of a digitized structures layer; and annual class analysis, completed via a qualified third-party firm and verified internally. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
215 | Expense | GT&S | JT | GT Reliability & General Maint | JTQ | Class Location Studies | Loss of Containment on Gas Transmission Pipeline | LOCTM-C025 Class Location Change | Ex 3, Ch 5 | No | On-Going | Annual | 2185.0905 | 2208.6942 | 4393.7847 | 1588.1424 | 1580.8793 | 3169.0217 | -627.8149 | -1224.763 | -0.28425 | -0.27875 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
216 | Expense | GT&S | JT | GT Reliability & General Maint | JTR | Valve Program | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 1370.7326 | 1385.5395 | 2756.2722 | 930.1459 | 789.1906 | 1719.3366 | -596.3489 | -1036.9356 | -0.43041 | -0.37621 | NO | NO | non-unitized: This MAT is non-unitized because it is used to record costs for various types of non-capitalizable work related to valve program | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
217 | Expense | GT&S | JT | GT Reliability & General Maint | JTR | Valve Program | Loss of Containment on Gas Transmission Pipeline | LOCTM-C024 Valve Safety and Reliability | Ex 3, Ch 5 | No | On-Going | Annual | 1370.7326 | 1385.5395 | 2756.2722 | 930.1459 | 789.1906 | 1719.3366 | -596.3489 | -1036.9356 | -0.43041 | -0.37621 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
218 | Expense | GT&S | JT | GT Reliability & General Maint | JTT | Geo-Hazard Mitigations | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | annual | 127.2186 | 128.5928 | 255.8114 | 158.9091 | 396.1266 | 555.0357 | 267.5338 | 299.2243 | 2.0805 | 1.1697 | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for mitigating geo-hazards such as soil-creep, dormant landslides with potential to re-activate, and subsidence. The type of mitigation work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
219 | Expense | GT&S | JT | GT Reliability & General Maint | JTT | Geo-Hazard Mitigations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C001 Geo-Hazard Threat Identification and Mitigation | Ex 3, Ch 5 | No | On-Going | annual | 127.2186 | 128.5928 | 255.8114 | 158.9091 | 396.1266 | 555.0357 | 267.5338 | 299.2243 | 2.0805 | 1.1697 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
220 | Expense | GT&S | JT | GT Reliability & General Maint | JTV | Station Strength Test Exp C&P | SRM Total | SRM Total | Ex 3, Ch 6 | No | #N/A | 9 | 2279.0093 | 2302.7767 | 4581.786 | 555.1061 | -113.5968 | 441.5092 | -2416.3735 | -4140.2768 | -1.0493 | -0.90364 | NO | NO | non-unitized: This MAT has no measurable units because project work that occurs under this MAT is non-fungible and covers a wide range of asset types, and scope of assets requiring work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
221 | Expense | GT&S | JT | GT Reliability & General Maint | JTV | Station Strength Test Exp C&P | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M006 Station Strength Test | Ex 3, Ch 6 | No | #N/A | 9 | 2279.0093 | 2302.7767 | 4581.786 | 555.1061 | -113.5968 | 441.5092 | -2416.3735 | -4140.2768 | -1.0493 | -0.90364 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
222 | Expense | GT&S | JT | GT Reliability & General Maint | JTW | Routine Spend M&C - Expense | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-Going | Annual | 4676.4595 | 4725.2294 | 9401.6889 | 4102.8884 | 4445.0676 | 8547.9559 | -280.1619 | -853.733 | -0.059291 | -0.090806 | NO | NO | non-unitized: This MAT has no measurable units because this is a routine spend MAT. Includes a combination non-fungible project work and programmatic activities. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
223 | Expense | GT&S | JT | GT Reliability & General Maint | JTW | Routine Spend M&C - Expense | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C004 Routine Spend M&C | Ex 3, Ch 6 | No | On-Going | Annual | 4676.4595 | 4725.2294 | 9401.6889 | 4102.8884 | 4445.0676 | 8547.9559 | -280.1619 | -853.733 | -0.059291 | -0.090806 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
224 | Expense | GT&S | JT | GT Reliability & General Maint | JTW | Routine Spend M&C - Expense | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C007 Routine Spend M&C | Ex 3, Ch 6 | No | On-Going | Annual | 4676.4595 | 4725.2294 | 9401.6889 | 4102.8884 | 4445.0676 | 8547.9559 | -280.1619 | -853.733 | -0.059291 | -0.090806 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
225 | Expense | GT&S | JT | GT Reliability & General Maint | JTX | GT Over Pressure Protection | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-Going | Annual | 0 | 0 | 0 | 1056.6352 | 1086.9829 | 2143.6181 | 1086.9829 | 2143.6181 | 0% | N/A | NO | NO | non-unitized: This MAT has no measurable units because it is an expense code that captures a variety of studies, reports, and small projects that support PG&E’s Overpressure Elimination program objectives, all of which have different tasks and costs that are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
226 | Expense | GT&S | JT | GT Reliability & General Maint | JTX | GT Over Pressure Protection | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-M002 GT Overpressure Protection | Ex 3, Ch 6 | No | On-Going | Annual | 0 | 0 | 0 | 1056.6352 | 1086.9829 | 2143.6181 | 1086.9829 | 2143.6181 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
227 | Expense | GT&S | JT | GT Reliability & General Maint | JTY | Routine Spend C&P Expense | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-Going | Annual | 8776.6785 | 8868.2089 | 17644.8875 | 9186.6865 | 6494.9808 | 15681.6673 | -2373.2281 | -1963.2202 | -0.26761 | -0.11126 | NO | NO | non-unitized: This MAT has no measurable units because this is a routine spend MAT. Includes a combination non-fungible project work and programmatic activities. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
228 | Expense | GT&S | JT | GT Reliability & General Maint | JTY | Routine Spend C&P Expense | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C020 Routine Spend C&P | Ex 3, Ch 6 | No | On-Going | Annual | 8776.6785 | 8868.2089 | 17644.8875 | 9186.6865 | 6494.9808 | 15681.6673 | -2373.2281 | -1963.2202 | -0.26761 | -0.11126 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
229 | Expense | GT&S | LV | GTS Station Assessments-BA | LV1 | Engineering Crtcl Assmnt 1 | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-Going | Annual | 0 | 0 | 0 | 1.63 | 15.5528 | 17.1828 | 15.5528 | 17.1828 | 0% | N/A | NO | NO | non-unitized: This MAT has no measurable units because project work that occurs under this MAT is non-fungible and covers a wide range of asset types, and scope of assets requiring work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
230 | Expense | GT&S | LV | GTS Station Assessments-BA | LV1 | Engineering Crtcl Assmnt 1 | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M007 Engineering Critical Assessment 1 | Ex 3, Ch 6 | No | On-Going | Annual | 0 | 0 | 0 | 1.63 | 15.5528 | 17.1828 | 15.5528 | 17.1828 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
231 | Expense | GT&S | LV | GTS Station Assessments-BA | LV2 | Engineering Crtcl Assmnt 2 | SRM Total | SRM Total | Ex 3, Ch 6 | No | #N/A | 9 | 5474.1818 | 5546.7649 | 11020.9468 | 3061.8889 | 2525.9326 | 5587.8216 | -3020.8323 | -5433.1252 | -0.54461 | -0.49298 | NO | NO | non-unitized: This MAT has no measurable units because project work that occurs under this MAT is non-fungible and covers a wide range of asset types, and scope of assets requiring work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
232 | Expense | GT&S | LV | GTS Station Assessments-BA | LV2 | Engineering Crtcl Assmnt 2 | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M008 Engineering Critical Assessment 2 | Ex 3, Ch 6 | No | #N/A | 9 | 5474.1818 | 5546.7649 | 11020.9468 | 3061.8889 | 2525.9326 | 5587.8216 | -3020.8323 | -5433.1252 | -0.54461 | -0.49298 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
233 | Expense | GT&S | OM | Operational Management | OM# (c) | Not assigned | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 13 | No | On-Going | Annual | 8663.7549 | 8908.993 | 17572.7479 | 3708.9081 | 5415.1061 | 9124.0141 | -3493.8869 | -8448.7338 | -0.39218 | -0.48079 | NO | NO | non-unitized: This MAT has no measurable units because this program records labor costs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to capture supervision and management support costs.
(a) StanPac MAT 34A is a consolidation of the recorded spend and work completed under various programs including ILI Direct Exam & Repair, Requird Ground Patrols and Electrical Interference-AC .
(b) Units for WELL Integrity Assessments MAT AH1 can include # Barrier Inspection Surveys, # Gamma-Ray Neutron Surveys, # Noise/Temperature Surveys.
(c) A MWC with a # captures other support costs and miscellaneous orders recorded within a MWC, that are not assigned to a specific MAT.
(d) Units for Electrical Interference - AC MAT GJA can include # of electric poles/towers investigated, # of electric poles/towers mitigated, # of AC Induced investigations completed, and # of stations investigated (arc fault).
(e) Units for Cathodic Protection MAT GJC can include # of miles surveyed and # of RMU covered by service fees.
(f) Units for Close Interval Survey (CIS) MAT GJE can include # of CIS miles surveyed and # of CIS Digs.
(g) Units for Internal Corrosion MAT GJH can include # of cleaning projects completed, # of corrosometers replaced/installed, # of IC investigations performed, # of UT probes installed, # of non destructive examinations performed, # of filter separator read points taken, # of monitoring point reads taken, # of well-head monitoring reads taken, # of bi-monthly drip monitoring reads taken, # of EM Coupon installations, # of EM Coupon reads taken, # of weightloss coupon reads taken, # of UT probes reads taken, # of drip monitoring reads taken, and # of corrosometer monitoring reads taken.
(h) Units for Casings MAT GJM can include # of casing test stations installed, # of leak surveys performed on cased crossings, and # of projects completed.
(i) Units for Fault Crossings MAT JT3 can include # of surveys and # of marker balls / arrays.

## GTS SRM MAT Table Capital
Table 2-10 2024 RSAR 2023 GRC CYCLE GAS TRANSMISSION AND STORAGE CAPITAL COMPARISON BY MAT FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | C6 | C7 | D | 2024 | 2024 | G1 | G2 | G3 | H | H2 | H3 | I | I2 | J1 | J2 | K | L | M | N1 | N2 | N3 | O1 | O2 | O3 | P1 | P2 | P3 | Q | R | S | T | V | W | X | Y | Z
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name | MAT | MAT Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program/ Project Life (years) | Program/ Project Year | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs | Imputed Costs for 2023 GRC Cycle to date($) (G1+G2) | 2023 Actual Costs | 2024 Actual Costs | Actual Costs for 2023 GRC Cycle to date ($) (H1+H2) | Difference for 2024 ($) (H2-G2) | Difference for 2023 GRC Cycle to Date ($) (H3-G3) | Spending Percent Variance for 2024 (%) ((H2-G2)/G2*100) | Spending Percent Variance for 2023 GRC Cylce (%) (I2/G3) (K2/H) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | Unit Type | 2023 Imputed Adopted Units | 2024 Imputed Adopted Units | Imputed Units for 2023 GRC Cycle to Date (N2+N1) | 2023 Actual Units | 2024 Actual Units | Actual Units for 2023 GRC Cycle to Date (O1+O2) | Difference for 2024 (# of Units) (O2-N2) | Difference for 2023 GRC Cycle to Date (# of Units)​ (O3-N3) | Unit​ Percent​ Variance​ for 2024 (%)​ ((P2-N2)/N2*100) | Unit Percent Variance for 2023 GRC Cycle to Date (%)​ ((O3-N3)/N3) | Unit Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | 2024 Unit Variance Explanation | Forcast Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T) | Status | Completion Status Statement
1 | Capital | GT&S | 21 | Misc Capital | 21C | GPOM Non-Engineering Capital | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | N/A | No | On-going | Annual | 0 | 0 | 0 | 1373.1321 | 696.0272 | 2069.1593 | 696.0272 | 2069.1593 | 100% | 100% | N | N | non-unitized: This MAT has no measurable units because it encompasses a variety of different activities – it is used to capture GPOM non-engineering capital routine transmission spend. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
2 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K1 | Drip Replacement | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 14161.4891 | 13753.7138 | 27915.2029 | 2622.5309 | 290.789 | 2913.3199 | -13462.9248 | -25001.883 | -97.89% | -89.56% | Y | Y | # of drips replaced | 5 | 5 | 10 | 5 | 4 | 9 | -1 | -1 | -20% | -10% | YES | Actual costs were lower than imputed due to work bundling with projects near a drip resulting in a lower unit cost and work cancellation due to transmission definition change in 2024. | Actual units were lower than imputed units due to the cancellation of bundled drip removal units. Bundled drip removals are executed opportunistically as part of pipeline replacement, strength test or retirement projects, but the planned projects were cancelled due to the TransDef change on the pipelines to which they are installed. | Under | On-Target | Under | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to mitigate Internal Corrosion as required by 49 CFR § 192.475.
3 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K1 | Drip Replacement | Loss of Containment on Gas Transmission Pipeline | LOCTM-C032 Internal Corrosion Program | Ex 3, Ch 9 | No | On-going | Annual | 14161.4891 | 13753.7138 | 27915.2029 | 2622.5309 | 290.789 | 2913.3199 | -13462.9248 | -25001.883 | -97.89% | -89.56% | N/A | N/A | N/A | 5 | 5 | 10 | 5 | 4 | 9 | -1 | -1 | -20% | -10% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
4 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K1 | Drip Replacement | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C017 Facility Corrosion Control Program | Ex 3, Ch 9 | No | On-going | Annual | 14161.4891 | 13753.7138 | 27915.2029 | 2622.5309 | 290.789 | 2913.3199 | -13462.9248 | -25001.883 | -97.89% | -89.56% | N/A | N/A | N/A | 5 | 5 | 10 | 5 | 4 | 9 | -1 | -1 | -20% | -10% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K4 | AC Interf Mitigation | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 3276.5505 | 3171.2 | 6447.7505 | 3813.16 | 5831.2941 | 9644.4541 | 2660.0941 | 3196.7036 | 83.88% | 49.58% | N | N | Various | 14 | 14 | 28 | 9.41 | 33 | 42.41 | 19 | 14.41 | 135.7% | 51.46% | YES | N/A | Actual units were higher than imputed units due to the new timeline requirement in Mega Rule Part 2 to mitigate AC Interference within 12-15 months after the idenfitication of AC Interference starting from 2024. | Over | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to mitigate AC Interference as required by 49 CFR § 192.467 and 473.
6 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K4 | AC Interf Mitigation | Loss of Containment on Gas Transmission Pipeline | LOCTM-C033 Electrical Interference Program | Ex 3, Ch 9 | No | On-going | Annual | 3276.5505 | 3171.2 | 6447.7505 | 3813.16 | 5831.2941 | 9644.4541 | 2660.0941 | 3196.7036 | 83.88% | 49.58% | N/A | N/A | N/A | 14 | 14 | 28 | 9.41 | 33 | 42.41 | 19 | 14.41 | 135.7% | 51.46% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K5 | Casing Mitigation | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 14765.6005 | 14294.3 | 29059.9005 | 12540.6064 | 8657.2865 | 21197.893 | -5637.0135 | -7862.0076 | -39.44% | -27.05% | N | N | Various | 11 | 11 | 22 | 14 | 2 | 16 | -9 | -6 | -81.82% | -27.27% | YES | N/A | Actual units were lower than imputed units due to the postponement of project execution to future years. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to mitigate contacted casing to ensure each buried or submerged pipeline being electrically isolated from the metallic casing it is within (49 CFR § 192.467).
8 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K5 | Casing Mitigation | Loss of Containment on Gas Transmission Pipeline | LOCTM-C035 Transmission Corrosion Control Program | Ex 3, Ch 9 | No | On-going | Annual | 14765.6005 | 14294.3 | 29059.9005 | 12540.6064 | 8657.2865 | 21197.893 | -5637.0135 | -7862.0076 | -39.44% | -27.05% | N/A | N/A | N/A | 11 | 11 | 22 | 14 | 2 | 16 | -9 | -6 | -81.82% | -27.27% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K6 | Cathodic Protection-New | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 1644.0063 | 1591.5289 | 3235.5351 | 2765.7421 | 2928.8464 | 5694.5885 | 1337.3175 | 2459.0534 | 84.03% | 76% | N | N | # of new CP systems installed | 5 | 5 | 10 | 5 | 6 | 11 | 1 | 1 | 20% | 10% | YES | N/A | Actual units were higher than imputed units due to a higher volume of groundbed installations required to maintain effective levels of cathodic protection. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to install cathodic protection (CP) to buried metallic pipeline to mitigate the threat of external corrosion, and if CP levels are inadequate and cannot be made adequate through troubleshooting, PG&E must either replace existing systems or install new equipment (49 CFR § 192.463).
10 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K6 | Cathodic Protection-New | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-going | Annual | 1644.0063 | 1591.5289 | 3235.5351 | 2763.186 | 2928.8464 | 5692.0324 | 1337.3175 | 2456.4973 | 84.03% | 75.92% | N/A | N/A | N/A | 5 | 5 | 10 | 5 | 6 | 11 | 1 | 1 | 20% | 10% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K6 | Cathodic Protection-New | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C018 Cathodic Protection | Ex 3, Ch 9 | No | On-going | Annual | 1644.0063 | 1591.5289 | 3235.5351 | 2765.7421 | 2928.8464 | 5694.5885 | 1337.3175 | 2459.0534 | 84.03% | 76% | N/A | N/A | N/A | 5 | 5 | 10 | 5 | 6 | 11 | 1 | 1 | 20% | 10% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K6 | Cathodic Protection-New | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C007 Cathodic Protection | Ex 3, Ch 9 | No | On-going | Annual | 1644.0063 | 1591.5289 | 3235.5351 | 2765.7421 | 2928.8464 | 5694.5885 | 1337.3175 | 2459.0534 | 84.03% | 76% | N/A | N/A | N/A | 5 | 5 | 10 | 5 | 6 | 11 | 1 | 1 | 20% | 10% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K7 (a) | Cathodic Protection-Replacement | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 4174.7083 | 4041 | 8215.7083 | 7192.2261 | 7063.4841 | 14255.7102 | 3022.4841 | 6040.0018 | 74.8% | 73.52% | N | N | Various | 22 | 22.01 | 44.01 | 30 | 28 | 58 | 5.99 | 13.99 | 27.21% | 31.79% | YES | N/A | Actual units were higher than imputed units due to a higher volume of groundbed replacement required to maintain effective levels of cathodic protection. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to install cathodic protection (CP) to buried metallic pipeline to mitigate the threat of external corrosion, and if CP levels are inadequate and cannot be made adequate through troubleshooting, PG&E must either replace existing systems or install new equipment (49 CFR § 192.463).
14 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K7 (a) | Cathodic Protection-Replacement | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-going | Annual | 4174.7083 | 4041 | 8215.7083 | 7192.2261 | 7063.4841 | 14255.7102 | 3022.4841 | 6040.0018 | 74.8% | 73.52% | N/A | N/A | N/A | 22 | 22.01 | 44.01 | 30 | 28 | 58 | 5.99 | 13.99 | 27.21% | 31.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K7 (a) | Cathodic Protection-Replacement | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C018 Cathodic Protection | Ex 3, Ch 9 | No | On-going | Annual | 4174.7083 | 4041 | 8215.7083 | 7192.2261 | 7063.4841 | 14255.7102 | 3022.4841 | 6040.0018 | 74.8% | 73.52% | N/A | N/A | N/A | 22 | 22.01 | 44.01 | 30 | 28 | 58 | 5.99 | 13.99 | 27.21% | 31.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
16 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K7 (a) | Cathodic Protection-Replacement | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C007 Cathodic Protection | Ex 3, Ch 9 | No | On-going | Annual | 4174.7083 | 4041 | 8215.7083 | 7192.2261 | 7063.4841 | 14255.7102 | 3022.4841 | 6040.0018 | 74.8% | 73.52% | N/A | N/A | N/A | 22 | 22.01 | 44.01 | 30 | 28 | 58 | 5.99 | 13.99 | 27.21% | 31.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K8 | Test Station Installation | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 129.9423 | 125.7636 | 255.706 | 7.2883 | 0.86179 | 8.1501 | -124.9018 | -247.5558 | -99.31% | -96.81% | N | N | # of test stations installed | 5 | 5 | 10 | 0 | 0 | 0 | -5 | -10 | -100% | -100% | YES | N/A | Actual units were lower than imputed units because no capital test station (CTS) installations (over 5 units) needed to be installed to meet requirement for 1 CTS per mile. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to install test station to meet the requirement of "sufficient test stations" required via 49 § 192.469.
18 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K8 | Test Station Installation | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-going | Annual | 129.9423 | 125.7636 | 255.706 | 7.2883 | 0.86179 | 8.1501 | -124.9018 | -247.5558 | -99.31% | -96.81% | N/A | N/A | N/A | 5 | 5 | 10 | 0 | 0 | 0 | -5 | -10 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K9 | Electrical Interference - DC | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 6254.13 | 6053 | 12307.13 | 4724.782 | 9307.0639 | 14031.8459 | 3254.0639 | 1724.7159 | 53.76% | 14.01% | N | N | Dynamic Electrical Interference - DC (# of Projects Completed) | 40 | 40 | 80 | 6 | 23 | 29 | -17 | -51 | -42.5% | -63.75% | YES | N/A | Actual units were lower than imputed units due to the permits and land acquisition delays, which resulted in delayed construction activities. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to mitigate DC Interference as required by 49 CFR § 192.467 and 473.
20 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K9 | Electrical Interference - DC | Loss of Containment on Gas Transmission Pipeline | LOCTM-C033 Electrical Interference Program | Ex 3, Ch 9 | No | On-going | Annual | 6254.13 | 6053 | 12307.13 | 4724.782 | 9307.0639 | 14031.8459 | 3254.0639 | 1724.7159 | 53.76% | 14.01% | N/A | N/A | N/A | 40 | 40 | 80 | 6 | 23 | 29 | -17 | -51 | -42.5% | -63.75% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3KA | Atmospheric Corrosion | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 326.3529 | 315.9356 | 642.2885 | 2047.7624 | 9459.0169 | 11506.7793 | 9143.0813 | 10864.4908 | 2894% | 1692% | Y | Y | # of spans recoated/ upgraded | 5 | 5 | 10 | 1 | 23 | 24 | 18 | 14 | 360% | 140% | YES | Actual costs were higher than imputed due to the majority of the units were on line 300/400, which are large pipelines and complex jobs. In 2024, asbestos abatement became a common mitigating factor which increased unit cost. | Actual units were higher than imputed due to in 2024 the threshold for capitalizing span re-coates changed from 100 feet to 40 feet, so actual units increased in 3KA and dropped in GJB. | Over | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to maintain and re-coat facilities that have observed corrosion or have deteriorated coating.
22 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3KA | Atmospheric Corrosion | Loss of Containment on Gas Transmission Pipeline | LOCTM-C034 Atmospheric Corrosion Program | Ex 3, Ch 9 | No | On-going | Annual | 326.3529 | 315.9356 | 642.2885 | 2047.7624 | 9459.0169 | 11506.7793 | 9143.0813 | 10864.4908 | 2894% | 1692% | N/A | N/A | N/A | 5 | 5 | 10 | 1 | 23 | 24 | 18 | 14 | 360% | 140% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
23 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L1 | WELL - Drilling | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-going | Annual | 19867.0445 | 47373.4 | 67240.4445 | 23992.2606 | 39437.1706 | 63429.4313 | -7936.2294 | -3811.0132 | -16.75% | -5.668% | Y | Y | # of wells drilled | 3 | 4 | 7 | 1 | 3 | 4 | -1 | -3 | -25% | -42.86% | YES | Actual costs were higher than imputed due to pre-mobiliztion material purchase for 2025 well drilling. | Actual units were lower than imputed units due to permit timing pushing completion of units into 2025. Overall unit plan for driling of new wells during the 2023-2026 rate case is expected to be achieved. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
24 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L1 | WELL - Drilling | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-M001 Well - Drilling | Ex 3, Ch 7 | No | On-going | Annual | 19867.0445 | 47373.4 | 67240.4445 | 23992.2606 | 39437.1706 | 63429.4313 | -7936.2294 | -3811.0132 | -16.75% | -5.668% | N/A | N/A | N/A | 3 | 4 | 7 | 1 | 3 | 4 | -1 | -3 | -25% | -42.86% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
25 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L3 (b) | WELL - Reworks | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-Going | Annual | 66326.1588 | 58802.5929 | 125128.7517 | 89198.912 | 86161.2804 | 175360.1924 | 27358.6875 | 50231.4407 | 46.53% | 40.14% | Y | Y | Various | 19.43 | 17.17 | 36.6 | 25 | 21 | 46 | 3.83 | 9.4 | 22.31% | 25.68% | YES | Actual costs were lower than imputed due to carryover work from 2022 and 2023 that hit in 2024. | Actual units were higher than imputed units due to incremental wells scheduled and required by CalGEM. | Over | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
26 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L3 (b) | WELL - Reworks | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C003 Well Inspections and Rework | Ex 3, Ch 7 | No | On-Going | Annual | 66326.1588 | 58802.5929 | 125128.7517 | 89198.912 | 86161.2804 | 175360.1924 | 27358.6875 | 50231.4407 | 46.53% | 40.14% | N/A | N/A | N/A | 19.43 | 17.17 | 36.6 | 25 | 21 | 46 | 3.83 | 9.4 | 22.31% | 25.68% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
27 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L4 (c) | WELL - Repair and Replace | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-Going | Annual | 0 | 0 | 0 | 2290.3426 | 5188.0488 | 7478.3913 | 5188.0488 | 7478.3913 | 100% | 100% | N | N | non-unitized: This MAT has no measurable units because it contains a mix of rework units and other project work which is not unitized. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
28 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L4 (c) | WELL - Repair and Replace | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C008 Well Repair and Replace | Ex 3, Ch 7 | No | On-Going | Annual | 0 | 0 | 0 | 2290.3426 | 5188.0488 | 7478.3913 | 5188.0488 | 7478.3913 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
29 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L5 (d) | WELL - Cntrls & Conts Monitrng | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-Going | Annual | 1436.8 | 7782.8029 | 9219.603 | 154.358 | 337.7732 | 492.1311 | -7445.0297 | -8727.4718 | -95.66% | -94.66% | N | N | non-unitized: This MAT has no measurable units because it contains miscellaneous component work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
30 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L5 (d) | WELL - Cntrls & Conts Monitrng | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C002 Well Control Monitoring | Ex 3, Ch 7 | No | On-Going | Annual | 1436.8 | 7782.8029 | 9219.603 | 154.358 | 337.7732 | 492.1311 | -7445.0297 | -8727.4718 | -95.66% | -94.66% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
31 | Capital | GT&S | 44 | Gas Capital:GasTrans-Sub | 44A (e) | Stan-Pac Capital | SRM Total | SRM Total | Ex 3, Ch 13 | No | On-Going | Annual | 3242.5869 | 3060.943 | 6303.5299 | 434.1505 | 475.458 | 909.6085 | -2585.485 | -5393.9214 |  | -85.57% | N | N | Various | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
32 | Capital | GT&S | 44 | Gas Capital:GasTrans-Sub | 44A (e) | Stan-Pac Capital | Loss of Containment on Gas Transmission Pipeline | LOCTM-C037 Stan-Pac Capital | Ex 3, Ch 13 | No | On-Going | Annual | 3242.5869 | 3060.943 | 6303.5299 | 434.1505 | 475.458 | 909.6085 | -2585.485 | -5393.9214 |  | -85.57% | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
33 | Capital | GT&S | 73 | GT Pipeline Capacity | 73A | Capacity for Load Growth | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 6757.3396 | 6540.0377 | 13297.3773 | 22032.5611 | 3489.2485 | 25521.8096 | -3050.7892 | 12224.4323 | -46.65% | 91.93% | N | N | non-unitized: This MAT has no measurable units because the program features multiple asset types without a common unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | Over | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
34 | Capital | GT&S | 73 | GT Pipeline Capacity | 73A | Capacity for Load Growth | Insufficient Capacity to Meet Customer Demand | CPCTY-M001 Capacity for Load Growth | Ex 3, Ch 11 | No | On-going | Annual | 6757.3396 | 6540.0377 | 13297.3774 | 22032.5611 | 3489.2485 | 25521.8096 | -3050.7892 | 12224.4322 | -46.65% | 91.93% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
35 | Capital | GT&S | 73 | GT Pipeline Capacity | 73B | Capacity Betterment | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 984.3329 | 952.6788 | 1937.0117 | 2691.7916 | 0.49012 | 2692.2817 | -952.1887 | 755.27 | -99.95% | 38.99% | N | N | non-unitized: This MAT has no measurable units because the program captures expenditures for the incremental capacity work only; costs (and units) for the original capacity projects are captured in the originating MWC or MAT. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
36 | Capital | GT&S | 73 | GT Pipeline Capacity | 73B | Capacity Betterment | Insufficient Capacity to Meet Customer Demand | CPCTY-M002 Capacity Betterment | Ex 3, Ch 11 | No | On-going | Annual | 984.3329 | 952.6788 | 1937.0117 | 2691.7916 | 0.49012 | 2692.2817 | -952.1887 | 755.27 | -99.95% | 38.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
37 | Capital | GT&S | 73 | GT Pipeline Capacity | 73D | LNG / CNG | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 4489.5278 | 4345.154 | 8834.6819 | 5780.9886 | 9346.12 | 15127.1086 | 5000.966 | 6292.4267 | 115.1% | 71.22% | N | N | non-unitized: This MAT has no measurable units due to the extensive variability of the work portfolio. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
38 | Capital | GT&S | 73 | GT Pipeline Capacity | 73D | LNG / CNG | Loss of Containment on LNG/CNG Portable Equipment | LNCNG-C001 LNG/CNG Portable Capital | Ex 3, Ch 5 | No | On-going | Annual | 4489.5278 | 4345.154 | 8834.6819 | 5780.9886 | 9346.12 | 15127.1086 | 5000.966 | 6292.4267 | 115.1% | 71.22% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
39 | Capital | GT&S | 73 | GT Pipeline Capacity | 73D | LNG / CNG | Loss of Containment on Gas Transmission Pipeline | LOCTM-C002 LNG/CNG to Support Strength Testing | Ex 3, Ch 5 | No | On-going | Annual | 4489.5278 | 4345.154 | 8834.6819 | 5780.9886 | 9346.12 | 15127.1086 | 5000.966 | 6292.4267 | 115.1% | 71.22% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
40 | Capital | GT&S | 75 | GT Pipeline Reliability | 75C | Routine Spend M&C - Capital | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 18442.8033 | 17849.7214 | 36292.5247 | 11510.8926 | 11705.4875 | 23216.3801 | -6144.2339 | -13076.1446 | -34.42% | -36.03% | N | N | non-unitized: This MAT has no measurable units because it includes a wide assortment of “find-it and fix-it" projects that are typically routine or unique occurrences and do not qualify for another program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
41 | Capital | GT&S | 75 | GT Pipeline Reliability | 75C | Routine Spend M&C - Capital | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C004 Routine Spend M&C | Ex 3, Ch 6 | No | On-going | Annual | 18442.8033 | 17849.7214 | 36292.5247 | 11510.8926 | 11705.4875 | 23216.3801 | -6144.2339 | -13076.1446 | -34.42% | -36.03% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | Capital | GT&S | 75 | GT Pipeline Reliability | 75C | Routine Spend M&C - Capital | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C007 Routine Spend M&C | Ex 3, Ch 6 | No | On-going | Annual | 18442.8033 | 17849.7214 | 36292.5247 | 11510.8926 | 11705.4875 | 23216.3801 | -6144.2339 | -13076.1446 | -34.42% | -36.03% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
43 | Capital | GT&S | 75 | GT Pipeline Reliability | 75D | Valve Program | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 45830.2626 | 44356.4575 | 90186.7202 | 24644.4969 | 26480.3018 | 51124.7987 | -17876.1557 | -39061.9214 | -40.3% | -43.31% | Y | Y | non-unitized: This MAT has no measurable units because it is used to record costs for various of “find it/fix it" valve replacement work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | Actual costs were lower than imputed due to Gas prioritization in support of higher risk or compliance work. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace inoperable valves, valves that are leaking, or presenting a safety or reliability threat.
44 | Capital | GT&S | 75 | GT Pipeline Reliability | 75D | Valve Program | Loss of Containment on Gas Transmission Pipeline | LOCTM-C024 Valve Safety and Reliability | Ex 3, Ch 5 | No | On-going | Annual | 45830.2626 | 44356.4575 | 90186.7202 | 24644.4969 | 26480.3018 | 51124.7987 | -17876.1557 | -39061.9214 | -40.3% | -43.31% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
45 | Capital | GT&S | 75 | GT Pipeline Reliability | 75E | Vintage Pipe Replacement | SRM Total | SRM Total | Ex 3, Ch 5 | No | on-going | annual | 4146.4466 | 4013.1056 | 8159.5522 | 2250.169 | 1747.9369 | 3998.1059 | -2265.1687 | -4161.4463 | -56.44% | -51% | N | N | Miles | 0.27 | 0 | 0.27 | 0 | 0 | 0 | 0 | -0.27 | N/A | -100% | NO | N/A | N/A | Under | Under | On-Target | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
46 | Capital | GT&S | 75 | GT Pipeline Reliability | 75E | Vintage Pipe Replacement | Loss of Containment on Gas Transmission Pipeline | LOCTM-M001 Vintage Pipe Replacement | Ex 3, Ch 5 | No | on-going | annual | 4146.4466 | 4013.1056 | 8159.5522 | 2250.169 | 1747.9369 | 3998.1059 | -2265.1687 | -4161.4463 | -56.44% | -51% | N/A | N/A | N/A | 0.27 | 0.27 | 0.54 | 0 | 0 | 0 | -0.27 | -0.54 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
47 | Capital | GT&S | 75 | GT Pipeline Reliability | 75H | Pipe Replacement Class Loctn | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 8587.4198 | 8311.2664 | 16898.6862 | 8846.7668 | 25022.1843 | 33868.9511 | 16710.9179 | 16970.2648 | 201.1% | 100.4% | Y | Y | non-unitized: This MAT is non-unitized since scope is identified during LIDAR analysis. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | Actual costs were higher than imputed due to the program expenditures exceeded imputed due to a larger volume of class location pipe replacements being completed. PG&E completed 6 replacements in 2024 driven by 611 flags and assets operating 2 classes out. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is the mitigation of identified class location changes via pipe replacement as required by 49 CFR § 192.611.
48 | Capital | GT&S | 75 | GT Pipeline Reliability | 75H | Pipe Replacement Class Loctn | Loss of Containment on Gas Transmission Pipeline | LOCTM-C025 Class Location Change | Ex 3, Ch 5 | No | On-going | Annual | 8587.4198 | 8311.2664 | 16898.6862 | 8846.7668 | 25022.1843 | 33868.9511 | 16710.9179 | 16970.2648 | 201.1% | 100.4% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
49 | Capital | GT&S | 75 | GT Pipeline Reliability | 75I | Valve Automation | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 23608.1685 | 22848.9794 | 46457.1479 | 5006.1807 | 10314.0233 | 15320.204 | -12534.9561 | -31136.9439 | -54.86% | -67.02% | Y | Y | Valves | 18 | 18 | 36 | 2 | 9 | 11 | -9 | -25 | -50% | -69.44% | YES | Actual costs were lower than imputed due to Gas prioritization in support of higher risk or compliance work. | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to enhance emergency response by installing automated valves to reduce risks associated with pipeline ruptures.
50 | Capital | GT&S | 75 | GT Pipeline Reliability | 75I | Valve Automation | Loss of Containment on Gas Transmission Pipeline | LOCTM-M004 Valve Automation | Ex 3, Ch 5 | No | On-going | Annual | 23608.1685 | 22848.9794 | 46457.1479 | 5006.1807 | 10314.0233 | 15320.204 | -12534.9561 | -31136.9439 | -54.86% | -67.02% | N/A | N/A | N/A | 18 | 18 | 36 | 2 | 9 | 11 | -9 | -25 | -50% | -69.44% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
51 | Capital | GT&S | 75 | GT Pipeline Reliability | 75J | Geo-Hazard Mitigations | SRM Total | SRM Total | Ex 3, Ch 5 | No | on-going | annual | 8486.1046 | 8213.2093 | 16699.3139 | 5199.4349 | 9042.5206 | 14241.9556 | 829.3113 | -2457.3583 | 10.1% | -14.72% | N | N | non-unitized: This MAT has no measurable units because it is used to record costs for mitigating geo-hazards such as soil-creep, dormant landslides with potential to re-activate, and subsidence. The type of mitigation work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
52 | Capital | GT&S | 75 | GT Pipeline Reliability | 75J | Geo-Hazard Mitigations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C001 Geo-Hazard Threat Identification and Mitigation | Ex 3, Ch 5 | No | on-going | annual | 8486.1046 | 8213.2093 | 16699.3139 | 5199.4349 | 9042.5206 | 14241.9556 | 829.3113 | -2457.3583 | 10.1% | -14.72% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
53 | Capital | GT&S | 75 | GT Pipeline Reliability | 75K | Water and Levee Crossings | SRM Total | SRM Total | Ex 3, Ch 5 | No | on-going | annual | 2549.8581 | 2467.86 | 5017.7182 | 12771.9118 | 2916.4718 | 15688.3836 | 448.6117 | 10670.6654 | 18.18% | 212.7% | N | N | Projects | 1 | 1 | 2 | 1 | 0 | 1 | -1 | -1 | -100% | -50% | YES | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. MATs 75M, 75T, and 75K collectively form the Shallow/Exposed/Water and Levee Crossings Mitigation program. Funds and units can be reallocated flexibly among these MATs as required depending on the highest risk. | Under | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to address the risks posed by shallow and exposed pipe on locations of water/levee crossings.
54 | Capital | GT&S | 75 | GT Pipeline Reliability | 75K | Water and Levee Crossings | Loss of Containment on Gas Transmission Pipeline | LOCTM-M002 Shallow and Exposed Pipe (Including Water and Levee Crossing | Ex 3, Ch 5 | No | on-going | annual | 2549.8581 | 2467.86 | 5017.7182 | 12771.9118 | 2916.4718 | 15688.3836 | 448.6117 | 10670.6654 | 18.18% | 212.7% | N/A | N/A | N/A | 1 | 1 | 2 | 1 | 0 | 1 | -1 | -1 | -100% | -50% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
55 | Capital | GT&S | 75 | GT Pipeline Reliability | 75L | Fault Crossings | SRM Total | SRM Total | Ex 3, Ch 5 | No | on-going | annual | 13542.1384 | 13106.6516 | 26648.79 | 9749.3144 | 16625.9264 | 26375.2408 | 3519.2748 | -273.5493 | 26.85% | -1.026% | N | N | Projects | 8 | 8 | 16 | 2 | 3 | 5 | -5 | -11 | -62.5% | -68.75% | YES | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to addresses the specific threat of land movement strains at known earthquake faults damaging a pipeline due to seismic events.
56 | Capital | GT&S | 75 | GT Pipeline Reliability | 75L | Fault Crossings | Loss of Containment on Gas Transmission Pipeline | LOCTM-C004 Earthquake Fault Crossings | Ex 3, Ch 5 | No | on-going | annual | 13542.1384 | 13106.6516 | 26648.79 | 9749.3144 | 16625.9264 | 26375.2408 | 3519.2748 | -273.5493 | 26.85% | -1.026% | N/A | N/A | N/A | 8 | 8 | 16 | 2 | 3 | 5 | -5 | -11 | -62.5% | -68.75% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
57 | Capital | GT&S | 75 | GT Pipeline Reliability | 75M | Shallow Pipe | SRM Total | SRM Total | Ex 3, Ch 5 | No | on-going | annual | 10178.4298 | 9851.1129 | 20029.5427 | 328.2224 | 539.9355 | 868.1579 | -9311.1773 | -19161.3848 | -94.52% | -95.67% | N | N | Projects | 4 | 4 | 8 | 0 | 0 | 0 | -4 | -8 | -100% | -100% | YES | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. MATs 75M, 75T, and 75K collectively form the Shallow/Exposed/Water and Levee Crossings Mitigation program. Funds and units can be reallocated flexibly among these MATs as required depending on the highest risk. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to address the risks posed by shallow pipe on land.
58 | Capital | GT&S | 75 | GT Pipeline Reliability | 75M | Shallow Pipe | Loss of Containment on Gas Transmission Pipeline | LOCTM-M002 Shallow and Exposed Pipe (Including Water and Levee Crossing | Ex 3, Ch 5 | No | on-going | annual | 10178.4298 | 9851.1129 | 20029.5427 | 328.2224 | 539.9355 | 868.1579 | -9311.1773 | -19161.3848 | -94.52% | -95.67% | N/A | N/A | N/A | 4 | 4 | 8 | 0 | 0 | 0 | -4 | -8 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
59 | Capital | GT&S | 75 | GT Pipeline Reliability | 75N | Hydrostatic Testing | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 44061.9104 | 42644.9717 | 86706.8821 | 9545.3329 | 2581.7023 | 12127.0352 | -40063.2694 | -74579.847 | -93.95% | -86.01% | Y | Y | non-unitized: This MAT has no measurable units since scope is identified as capital upgrades during the engineering practice. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | Actual costs were lower than imputed due to a lower volume of identified capital work being executed such as capital upgrades needed to facilitate a strength test. A procedural update to the working assessment plan was implemented to align with Transdef initiative, resulting in a lower amount of scheduled strength tests in 2024 that required capital work. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to assist in faciliating a hydrotest with any captial units of measure either installed, removed or replaced including captial equipment puchases, replacements and piggability improvements driven by the hydrotest.
60 | Capital | GT&S | 75 | GT Pipeline Reliability | 75N | Hydrostatic Testing | Loss of Containment on Gas Transmission Pipeline | LOCTM-M003 Non-TIMP Strength Testing | Ex 3, Ch 5 | No | On-going | Annual | 44061.9104 | 42644.9717 | 86706.8821 | 9545.3329 | 2581.7023 | 12127.0352 | -40063.2694 | -74579.847 | -93.95% | -86.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
61 | Capital | GT&S | 75 | GT Pipeline Reliability | 75O | Pipe Rplcmnt - Oth PL Sfty Inv | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 33831.499 | 32743.5489 | 66575.0479 | 34385.3613 | 49877.5126 | 84262.8739 | 17133.9637 | 17687.826 | 52.33% | 26.57% | Y | Y | non-unitized: This MAT is non-unitized because it is used to record costs for various types of work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | Actual costs were higher than imputed due to a higher volume of projects, largely driven by higher risk scopes and compliance-related requirements. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to mitigate graded leaks and reliability risks along gas transmission pipelines.
62 | Capital | GT&S | 75 | GT Pipeline Reliability | 75O | Pipe Rplcmnt - Oth PL Sfty Inv | Loss of Containment on Gas Transmission Pipeline | LOCTM-C008 Pipeline Safety and Reliability | Ex 3, Ch 5 | No | On-going | Annual | 33831.499 | 32743.5489 | 66575.0479 | 34385.3613 | 49877.5126 | 84262.8739 | 17133.9637 | 17687.826 | 52.33% | 26.57% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
63 | Capital | GT&S | 75 | GT Pipeline Reliability | 75P | ILI Capital Repair (Non-BA) | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 14431.0731 | 13967.0001 | 28398.0732 | 1983.6869 | 23769.4825 | 25753.1694 | 9802.4825 | -2644.9037 | 70.18% | -9.314% | N | N | non-unitized: This MAT has no measurable units since work is not known until anomalous results from previous year's Traditional and Non-Traditional ILI inspections are found. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
64 | Capital | GT&S | 75 | GT Pipeline Reliability | 75P | ILI Capital Repair (Non-BA) | Loss of Containment on Gas Transmission Pipeline | LOCTM-C005 In-Line Inspection | Ex 3, Ch 5 | No | On-going | Annual | 14431.0731 | 13967.0001 | 28398.0732 | 1983.6869 | 23769.4825 | 25753.1694 | 9802.4825 | -2644.9037 | 70.18% | -9.314% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
65 | Capital | GT&S | 75 | GT Pipeline Reliability | 75Q | Pipe Replacement (IM) | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 20044.568 | 19399.9768 | 39444.5448 | 12948.4234 | 30419.4833 | 43367.9066 | 11019.5065 | 3923.3618 | 56.8% | 9.947% | Y | Y | Miles | 0.16 | 0.16 | 0.32 | 0.437 | 0.41 | 0.847 | 0.25 | 0.527 | 156.2% | 164.7% | YES | Actual costs were higher than imputed due to program expenditures exceeded imputed due to a larger volume of projects classified as capital (>50ft and/or capital installation/replacement) and due to more Integrity Management threats coming due in 2024 that required replacement. | Actual units were higher than imputed units due to more projects classified as capital (>50ft and/or capital installation/replacement) and more Integrity Managerment driven threat assessments coming due in 2024 | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to implement TIMP (49 CFR Part 192, Subpart O) capital pipe replacements in lieu of testing when it is a more prudent option.
66 | Capital | GT&S | 75 | GT Pipeline Reliability | 75Q | Pipe Replacement (IM) | Loss of Containment on Gas Transmission Pipeline | LOCTM-C026 TIMP Strength Testing | Ex 3, Ch 5 | No | On-going | Annual | 20044.568 | 19399.9768 | 39444.5448 | 12948.4234 | 30419.4833 | 43367.9066 | 11019.5065 | 3923.3618 | 56.8% | 9.947% | N/A | N/A | N/A | 0.16 | 0.16 | 0.32 | 0.437 | 0.41 | 0.847 | 0.25 | 0.527 | 156.2% | 164.7% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
67 | Capital | GT&S | 75 | GT Pipeline Reliability | 75R | Pipe Rplcmnt In-Lieu of Hydro | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 41134.578 | 39811.7763 | 80946.3543 | 23753.2066 | 19017.7506 | 42770.9573 | -20794.0256 | -38175.397 | -52.23% | -47.16% | Y | Y | Miles | 0.71 | 0.71 | 1.42 | 2.27 | 0.702 | 2.972 | -0.008 | 1.552 | -1.127% | 109.3% | NO | Actual costs were lower than imputed regulatory values due to project cancellations driven by working assessment plan (WAP) updates and Transdef changes as well as other assessment methods selected over replacement. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to implement Non-TIMP capital pipe replacements in lieu of testing when it is a more prudent option.
68 | Capital | GT&S | 75 | GT Pipeline Reliability | 75R | Pipe Rplcmnt In-Lieu of Hydro | Loss of Containment on Gas Transmission Pipeline | LOCTM-M003 Non-TIMP Strength Testing | Ex 3, Ch 5 | No | On-going | Annual | 41134.578 | 39811.7763 | 80946.3543 | 23753.2066 | 19017.7506 | 42770.9573 | -20794.0256 | -38175.397 | -52.23% | -47.16% | N/A | N/A | N/A | 0.71 | 0.71 | 1.42 | 2.27 | 0.702 | 2.972 | -0.008 | 1.552 | -1.127% | 109.3% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
69 | Capital | GT&S | 75 | GT Pipeline Reliability | 75S | Direct Assessment | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 1774.1918 | 1717.1376 | 3491.3294 | 549.2132 | 204.4489 | 753.6621 | -1512.6886 | -2737.6673 | -88.09% | -78.41% | N | N | non-unitized: This MAT has no measurable units because it is used to record costs for direct assessment capital repairs that arise from ECDA, ICDA, SCCDA or Direct Examination findings. The types of repair work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
70 | Capital | GT&S | 75 | GT Pipeline Reliability | 75S | Direct Assessment | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-going | Annual | 1774.1918 | 1717.1376 | 3491.3294 | 549.2132 | 204.4489 | 753.6621 | -1512.6886 | -2737.6673 | -88.09% | -78.41% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
71 | Capital | GT&S | 75 | GT Pipeline Reliability | 75T | Exposed Pipe | SRM Total | SRM Total | Ex 3, Ch 5 | No | on-going | annual | 10178.4298 | 9851.1129 | 20029.5427 | 7012.5263 | 3685.7192 | 10698.2455 | -6165.3936 | -9331.2972 | -62.59% | -46.59% | N | N | Projects | 4 | 4 | 8 | 0 | 1 | 1 | -3 | -7 | -75% | -87.5% | YES | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. MATs 75M, 75T, and 75K collectively form the Shallow/Exposed/Water and Levee Crossings Mitigation program. Funds and units can be reallocated flexibly among these MATs as required depending on the highest risk. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to address the risks posed by exposed pipe on land.
72 | Capital | GT&S | 75 | GT Pipeline Reliability | 75T | Exposed Pipe | Loss of Containment on Gas Transmission Pipeline | LOCTM-M002 Shallow and Exposed Pipe (Including Water and Levee Crossing | Ex 3, Ch 5 | No | on-going | annual | 10178.4298 | 9851.1129 | 20029.5427 | 7012.5263 | 3685.7192 | 10698.2455 | -6165.3936 | -9331.2972 | -62.59% | -46.59% | N/A | N/A | N/A | 4 | 4 | 8 | 0 | 1 | 1 | -3 | -7 | -75% | -87.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
73 | Capital | GT&S | 75 | GT Pipeline Reliability | 75U | Non-TIMP Strength Testing | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 69859.2382 | 67612.7116 | 137471.9497 | 18663.647 | -5245.744 | 13417.903 | -72858.4555 | -124054.0467 | -107.8% | -90.24% | Y | Y | Miles; historically expense program in MAT MC1 | 39.4 | 39.4 | 78.8 | 9 | 0 | 9 | -39.4 | -69.8 | -100% | -88.58% | YES | Actual costs were lower than imputed due to a mid year accounting guidance change, which altered the allocation process for previously tested Non IM Driven footage and their respective costs. This adjustment led to a one time conversion of all existing scopes, causing MAT 75U to reflect a negative spend ( $5 million in 2024). This issue is not expected to recur, as future projects will be scoped according to the new guidance. Furthermore, Transdef initiative delayed or cancelled existing work out from 2024 to allow for asset classification reviews. | Actual units were lower than imputed due to two drivers - 1) a mid year FERC accounting guidance change, which altered the allocation process for previously tested Non IM Driven footage. This adjustment led to a one time conversion of all existing scopes, causing MAT 75U to have no recorded units in 2024. This issue is not expected to recur, as future projects will be scoped according to the new guidance. 2)Transdef initiative delayed or cancelled work out from 2024 to allow for asset classification reviews. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to validate the integrity and assure a margin of safety by strength testing in accordance with 49 CFR § 192.619 for those gas transmission pipelines that: 1) Lack a documented TVC strength test record that is consistent with D.11-06-017, D.12-12-030, and NTSB Safety Recommendation P-10-4 (prioritizing strength testing of gas transmission pipelines with the highest risk factors); 2) Need to have MAOP re-confirmed under 49 CFR §192.624 via either a strength test or pipe replacement; or 3) Need to be either tested or replaced to comply with 49 CFR §192.917 because the manufacturing threat is deemed unstable because it either does not have a TVC record of a test or does not have a 49 CFR Subpart J test to at least 1.25 times MAOP.
74 | Capital | GT&S | 75 | GT Pipeline Reliability | 75U | Non-TIMP Strength Testing | Loss of Containment on Gas Transmission Pipeline | LOCTM-M003 Non-TIMP Strength Testing | Ex 3, Ch 5 | No | On-going | Annual | 69859.2382 | 67612.7116 | 137471.9497 | 18663.647 | -5245.744 | 13417.903 | -72858.4555 | -124054.0467 | -107.8% | -90.24% | N/A | N/A | N/A | 39.4 | 39.4 | 78.8 | 9 | 0 | 9 | -39.4 | -69.8 | -100% | -88.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
75 | Capital | GT&S | 75 | GT Pipeline Reliability | 75V | TIMP Direct Exam-Captal Recoat | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 2328.1523 | 2253.2838 | 4581.436 | 329.8791 | 5789.7573 | 6119.6364 | 3536.4736 | 1538.2004 | 156.9% | 33.57% | N | N | # of DE Projects with Capital Repair/Recoat | 2 | 2 | 4 | 0 | 4 | 4 | 2 | 0 | 100% | 0% | YES | N/A | Actal units were higher than imputed units due to recapitalization of recoating from 100 feet to 40 feet. This led to more work scopes of work materializing that meets the 40 foot threshold. | Over | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform 100% Direct Examinations on pipeline segments greater than 40 feet.
76 | Capital | GT&S | 75 | GT Pipeline Reliability | 75V | TIMP Direct Exam-Captal Recoat | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-going | Annual | 2328.1523 | 2253.2838 | 4581.436 | 329.8791 | 5789.7573 | 6119.6364 | 3536.4736 | 1538.2004 | 156.9% | 33.57% | N/A | N/A | N/A | 2 | 2 | 4 | 0 | 4 | 4 | 2 | 0 | 100% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
77 | Capital | GT&S | 76 | GT Pipeline Reliability | 762 | Gill Ranch Capital | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 6 | No | On-going | Annual | 999.1173 | 967 | 1966.1173 | 289.8077 | 1896.7209 | 2186.5286 | 929.7209 | 220.4113 | 96.14% | 11.21% | N | N | non-unitized: This MAT has no measurable units due to various types of projects included. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
78 | Capital | GT&S | 76 | GT Station Reliability | 763 | Perform Simple Station Rblds | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 7394.0865 | 7156.3082 | 14550.3948 | 10429.0422 | 8954.1065 | 19383.1487 | 1797.7983 | 4832.7539 | 25.12% | 33.21% | N | N | # of Simple Stations Rebuilt | 2 | 2 | 4 | 2 | 1 | 3 | -1 | -1 | -50% | -25% | YES | N/A | Actual units were lower than imputed due to Project execution delayed due to project redesign as original design was determined to not be up to current standard and to avoid year end weather and clearance challenges. | Under | Under | On-Target | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
79 | Capital | GT&S | 76 | GT Station Reliability | 763 | Perform Simple Station Rblds | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C001 Perform Simple Station Rebuilds | Ex 3, Ch 6 | No | On-going | Annual | 7394.0865 | 7156.3082 | 14550.3948 | 10429.0422 | 8954.1065 | 19383.1487 | 1797.7983 | 4832.7539 | 25.12% | 33.21% | N/A | N/A | N/A | 2 | 2 | 4 | 2 | 1 | 3 | -1 | -1 | -50% | -25% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
80 | Capital | GT&S | 76 | GT Station Reliability | 763 | Perform Simple Station Rblds | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C004 Perform Simple Station Rebuilds | Ex 3, Ch 6 | No | On-going | Annual | 7394.0865 | 7156.3082 | 14550.3948 | 10429.0422 | 8954.1065 | 19383.1487 | 1797.7983 | 4832.7539 | 25.12% | 33.21% | N/A | N/A | N/A | 2 | 2 | 4 | 2 | 1 | 3 | -1 | -1 | -50% | -25% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
81 | Capital | GT&S | 76 | GT Station Reliability | 764 | Perform Complex Station Rblds | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 47094.1854 | 45579.7352 | 92673.9205 | 21179.6493 | 55504.3061 | 76683.9554 | 9924.5709 | -15989.9652 | 21.77% | -17.25% | N | N | # of Complex Stations Rebuilt | 1.5 | 1.5 | 3 | 1 | 1 | 2 | -0.5 | -1 | -33.33% | -33.33% | YES | N/A | Actual units were lower than imputed due to the program being impacted by Gas prioritization in support of higher risk/compliance work that needed to be funded which impacted construction at Panoche and engineering at Irvington. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
82 | Capital | GT&S | 76 | GT Station Reliability | 764 | Perform Complex Station Rblds | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C002 Perform Complex Station Rebuilds | Ex 3, Ch 6 | No | On-going | Annual | 47094.1854 | 45579.7352 | 92673.9205 | 21179.6493 | 55504.3061 | 76683.9554 | 9924.5709 | -15989.9652 | 21.77% | -17.25% | N/A | N/A | N/A | 1.5 | 1.5 | 3 | 0 | 1 | 1 | -0.5 | -2 | -33.33% | -66.67% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
83 | Capital | GT&S | 76 | GT Station Reliability | 764 | Perform Complex Station Rblds | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C005 Perform Complex Station Rebuilds | Ex 3, Ch 6 | No | On-going | Annual | 47094.1854 | 45579.7352 | 92673.9205 | 21179.6493 | 55504.3061 | 76683.9554 | 9924.5709 | -15989.9652 | 21.77% | -17.25% | N/A | N/A | N/A | 1.5 | 1.5 | 3 | 0 | 1 | 1 | -0.5 | -2 | -33.33% | -66.67% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 | Capital | GT&S | 76 | GT Station Reliability | 765 | Perform Transm Terminal Upgrd | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 10771.9092 | 10425.5 | 21197.4092 | 8749.9469 | 5281.2737 | 14031.2206 | -5144.2263 | -7166.1885 | -49.34% | -33.81% | N | N | non-unitized: This MAT has no measurable units because it captures individual projects that address specific upgrades inside the terminals in addition to routine terminal work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
85 | Capital | GT&S | 76 | GT Station Reliability | 765 | Perform Transm Terminal Upgrd | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C003 Perform Transmission Terminal Upgrade | Ex 3, Ch 6 | No | On-going | Annual | 10771.9092 | 10425.5 | 21197.4092 | 8749.9469 | 5281.2737 | 14031.2206 | -5144.2263 | -7166.1885 | -49.34% | -33.81% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
86 | Capital | GT&S | 76 | GT Station Reliability | 765 | Perform Transm Terminal Upgrd | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C006 Perform Transmission Terminal Upgrade | Ex 3, Ch 6 | No | On-going | Annual | 10771.9092 | 10425.5 | 21197.4092 | 8749.9469 | 5281.2737 | 14031.2206 | -5144.2263 | -7166.1885 | -49.34% | -33.81% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
87 | Capital | GT&S | 76 | GT Station Reliability | 766 | Becker Sys Upgrade | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 6 | No | On-Going | Annual | 0 | 0 | 0 | 0.85722 | 157.7847 | 158.6419 | 157.7847 | 158.6419 | 100% | 100% | N | N | non-unitized: This MAT was not forecast in the 2023 GRC and includes Becker control valve system upgrade activities. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program was not forecast in the 2023 GRC.
88 | Capital | GT&S | 76 | GT Station Reliability | 76G | GT Over Pressure Protection | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 24613.493 | 22015.7559 | 46629.2489 | 22015.7559 | 46629.2489 | 100% | 100% | Y | Y | # Rebuilds and Retrofits | 0 | 0 | 0 | 0 | 28 | 28 | 28 | 28 | 100 | N/A | YES | Actual costs were higher than imputed due to program having no adopted funding in the 2023 GRC. However, program was deemed important and continued to be performed by Gas Operations | Actual units were higher than imputed due to program having no adopted units in the 2023 GRC. However, program was deemed important and continued to be performed by Gas Operations. | On-Target | On-Target | Over | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
89 | Capital | GT&S | 76 | GT Station Reliability | 76G | GT Over Pressure Protection | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-M002 GT Overpressure Protection | Ex 3, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 24613.493 | 22015.7559 | 46629.2489 | 22015.7559 | 46629.2489 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
90 | Capital | GT&S | 76 | GT Station Reliability | 76M | GT SCADA Visibility | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 3106 | 3006.1987 | 6112.1987 | 2419.8668 | 1264.1081 | 3683.9749 | -1742.0907 | -2428.2238 | -57.95% | -39.73% | N | N | # of Remote Terminal Units Installed | 8 | 8 | 16 | 5 | 1 | 6 | -7 | -10 | -87.5% | -62.5% | YES | N/A | Actual units were lower than imputed adopted units due to either upgrading from the SCADAPack 350 to a newer version of the SCADAPack, permitting delays, or both. | Under | Under | On-Target | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
91 | Capital | GT&S | 76 | GT Station Reliability | 76M | GT SCADA Visibility | Insufficient Capacity to Meet Customer Demand | CPCTY-M003 GT SCADA Visibility | Ex 3, Ch 11 | No | On-going | Annual | 3106 | 3006.1987 | 6112.1987 | 2419.8668 | 1264.1081 | 3683.9749 | -1742.0907 | -2428.2238 | -57.95% | -39.73% | N/A | N/A | N/A | 8 | 8 | 16 | 5 | 1 | 6 | -7 | -10 | -87.5% | -62.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
92 | Capital | GT&S | 76 | GT Station Reliability | 76M | GT SCADA Visibility | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-M001 GT SCADA Visibility | Ex 3, Ch 11 | No | On-going | Annual | 3106 | 3006.1987 | 6112.1987 | 2419.8668 | 1264.1081 | 3683.9749 | -1742.0907 | -2428.2238 | -57.95% | -39.73% | N/A | N/A | N/A | 8 | 8 | 16 | 5 | 1 | 6 | -7 | -10 | -87.5% | -62.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
93 | Capital | GT&S | 76 | GT Station Reliability | 76M | GT SCADA Visibility | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M003 GT SCADA Visibility | Ex 3, Ch 11 | No | On-going | Annual | 3106 | 3006.1987 | 6112.1987 | 2419.8668 | 1264.1081 | 3683.9749 | -1742.0907 | -2428.2238 | -57.95% | -39.73% | N/A | N/A | N/A | 8 | 8 | 16 | 5 | 1 | 6 | -7 | -10 | -87.5% | -62.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
94 | Capital | GT&S | 76 | GT Station Reliability | 76N | Routine Spend C&P Capital | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 58989.1699 | 57710.2766 | 116699.4465 | 33868.6951 | 41534.0143 | 75402.7095 | -16176.2622 | -41296.737 | -28.03% | -35.39% | Y | Y | non-unitized: This MAT has no measurable units because it includes a wide assortment of “find-it and fix-it” projects that are typically routine or unique occurrences and do not qualify for another program. | N/A | N/A | N/A | N/A | - | N/A | N/A | N/A | N/A | N/A | NO | Actual costs were lower due to the program being impacted by Gas prioritization in support of higher risk/compliance work that needed to be funded which impacted project start and construction | N/A | On-Target | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
95 | Capital | GT&S | 76 | GT Station Reliability | 76N | Routine Spend C&P Capital | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C020 Routine Spend C&P | Ex 3, Ch 6 | No | On-going | Annual | 58989.1699 | 57710.2766 | 116699.4465 | 33868.6951 | 41534.0143 | 75402.7095 | -16176.2622 | -41296.737 | -28.03% | -35.39% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
96 | Capital | GT&S | 76 | GT Station Reliability | 76P | GT Elect Upgrd-Hinkley&Topock | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 6303.6591 | 6100.9466 | 12404.6057 | 4040.5185 | 7840.1393 | 11880.6578 | 1739.1927 | -523.9479 | 28.51% | -4.224% | N | N | # of upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
97 | Capital | GT&S | 76 | GT Station Reliability | 76P | GT Elect Upgrd-Hinkley&Topock | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C021 GT Elect Upgrd-Hinkley&Topock | Ex 3, Ch 6 | No | On-going | Annual | 6303.6591 | 6100.9466 | 12404.6057 | 4040.5185 | 7840.1393 | 11880.6578 | 1739.1927 | -523.9479 | 28.51% | -4.224% | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
98 | Capital | GT&S | 76 | GT Station Reliability | 76S | Engineering Critical Assmnt 2 | SRM Total | SRM Total | Ex 3, Ch 6 | No | 20+ | 9 | 9848.5551 | 9531.8462 | 19380.4012 | 1090.0053 | 1371.5149 | 2461.5202 | -8160.3313 | -16918.881 | -85.61% | -87.3% | N | N | non-unitized: This MAT has no measurable units because project work that occurs under this MAT is non-fungible and covers a wide range of asset types, and scope of assets requiring work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
99 | Capital | GT&S | 76 | GT Station Reliability | 76S | Engineering Critical Assmnt 2 | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M008 Engineering Critical Assessment 2 | Ex 3, Ch 6 | No | 20+ | 9 | 9848.5551 | 9531.8462 | 19380.4012 | 1090.0053 | 1371.5149 | 2461.5202 | -8160.3313 | -16918.881 | -85.61% | -87.3% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
100 | Capital | GT&S | 76 | GT Station Reliability | 76T | Compressor Control Upgrades | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 12090.221 | 11838.8719 | 23929.0929 | 6475.0489 | 13549.0196 | 20024.0685 | 1710.1477 | -3905.0244 | 14.45% | -16.32% | N | N | # of Station Upgrades | 1 | 1 | 2 | 2 | 0 | 2 | -1 | 0 | -100% | 0% | YES | N/A | Actual Units were lower than imputed due to Project is being delayed by the required CPCN permit approval process. | Under | Under | On-Target | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
101 | Capital | GT&S | 76 | GT Station Reliability | 76T | Compressor Control Upgrades | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C023 Compressor Control Upgrades | Ex 3, Ch 6 | No | On-going | Annual | 12090.221 | 11838.8719 | 23929.0929 | 6475.0489 | 13549.0196 | 20024.0685 | 1710.1477 | -3905.0244 | 14.45% | -16.32% | N/A | N/A | N/A | 1 | 1 | 2 | 2 | 0 | 2 | -1 | 0 | -100% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
102 | Capital | GT&S | 76 | GT Station Reliability | 76V | Station Strength Tst - Capital | SRM Total | SRM Total | Ex 3, Ch 6 | No | 12 | 9 | 16745.3354 | 16206.8405 | 32952.1759 | 2431.3486 | 1469.3404 | 3900.689 | -14737.5001 | -29051.4869 | -90.93% | -88.16% | Y | Y | non-unitized: This MAT has no measurable units because project work that occurs under this MAT is non-fungible and covers a wide range of asset types, and scope of assets requiring work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | Actual costs were lower due to Station Strength Test projects subject to disallowance based on install date and test record of various features. Disallowed costs are moved to MAT JTU. Projects executed in this year were significantly more disallowed than expected over the rate case period. | N/A | On-Target | On-Target | Under | Proceeding as Planned | Program that includes 76V , 76S, JTV, LV2 to be rolled into single MAT codes for Exp/Capital: 76S and LV2.
103 | Capital | GT&S | 76 | GT Station Reliability | 76V | Station Strength Tst - Capital | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M006 Station Strength Test | Ex 3, Ch 6 | No | 12 | 9 | 16745.3354 | 16206.8405 | 32952.1759 | 2431.3486 | 1469.3404 | 3900.689 | -14737.5001 | -29051.4869 | -90.93% | -88.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
104 | Capital | GT&S | 76 | GT Station Reliability | 76X | Compressor Replacements | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 10487.5673 | 10562.2588 | 21049.8261 | 18757.0257 | 12428.2945 | 31185.3202 | 1866.0357 | 10135.4941 | 17.67% | 48.15% | N | N | # of Compressor Unit Replacements | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | N/A | NO | N/A | N/A | Over | On-Target | Over | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
105 | Capital | GT&S | 76 | GT Station Reliability | 76X | Compressor Replacements | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C024 Compressor Replacements | Ex 3, Ch 6 | No | On-going | Annual | 10487.5673 | 10562.2588 | 21049.8261 | 18757.0257 | 12428.2945 | 31185.3202 | 1866.0357 | 10135.4941 | 17.67% | 48.15% | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
106 | Capital | GT&S | 76 | GT Station Reliability | 76Z | Physical Security - Capital | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 9654.748 | 9344.2715 | 18999.0195 | 585.1428 | 3764.8654 | 4350.0082 | -5579.4061 | -14649.0113 | -59.71% | -77.1% | N | N | # Stations | 2 | 2 | 4 | 0 | 0 | 0 | -2 | -4 | -100% | -100% | YES | N/A | Actual units were lower than imputed units due to 2 parallel security projects expected to execute in 2024, however, due to scope changes from Corporate Security and internal IT as a result of changing standards during design (i.e. rack configurations) and third-party utility design timelines for new telecommunications lines, both projects did not execute as planned. Unit capture (2 units) expected in 2025. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
107 | Capital | GT&S | 76 | GT Station Reliability | 76Z | Physical Security - Capital | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C025 Physical Security - Capital | Ex 3, Ch 6 | No | On-going | Annual | 9654.748 | 9344.2715 | 18999.0195 | 585.1428 | 3764.8654 | 4350.0082 | -5579.4061 | -14649.0113 | -59.71% | -77.1% | N/A | N/A | N/A | 2 | 2 | 4 | 0 | 0 | 0 | -2 | -4 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
108 | Capital | GT&S | 84 | GT Gas Gathering System Manage | 84C | GG- Reliability/Safety | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 5 | No | On-going | Annual | 0 | 0 | 0 | 4.447 | 2.3778 | 6.8248 | 2.3778 | 6.8248 | 100% | 100% | N | N | non-unitized: This MAT has no measurable units as this is no longer used to capture work and reflects close out costs for odorizer installation projects on gas gathering lines. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
109 | Capital | GT&S | 84 | GT Gas Gathering System Manage | 84D | Gas Gathering | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 12290.6286 | 11895.3878 | 24186.0164 | 3278.7936 | 10388.896 | 13667.6897 | -1506.4918 | -10518.3268 | -12.66% | -43.49% | N | N | Meters | 11 | 11 | 22 | 2 | 6 | 8 | -5 | -14 | -45.45% | -63.64% | YES | N/A | Actual units were lower than imputed adopted units due to reprioritization in support of higher risk or compliance work. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to divest idle gas gathering assets to minimize operating risks.
110 | Capital | GT&S | 84 | GT Gas Gathering System Manage | 84D | Gas Gathering | Loss of Containment on Gas Transmission Pipeline | LOCTM-C006 Gas Gathering Divestiture | Ex 3, Ch 5 | No | On-Going | Annual | 12290.6286 | 11895.3878 | 24186.0164 | 3278.7936 | 10388.896 | 13667.6897 | -1506.4918 | -10518.3268 | -12.66% | -43.49% | N/A | N/A | N/A | 11 | 11 | 22 | 2 | 6 | 8 | -5 | -14 | -45.45% | -63.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
111 | Capital | GT&S | 98 | GT Integrity Management | 98C | ILI Upgrades | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 61141.5927 | 59175.4073 | 120317.0001 | 145155.4964 | 100827.3117 | 245982.808 | 41651.9043 | 125665.8079 | 70.39% | 104.4% | Y | Y | # of Projects | 4 | 4 | 8 | 6 | 1 | 7 | -3 | -1 | -75% | -12.5% | YES | Actual costs were higher than imputed regulatory values due to several drivers. Program is working through more complex scopes of work compared to historical upgrades such as smaller diameter pipe projects. The program has also completed a significant amount of non-unitized work (roughly $16M) in 2024 which resulted in a higher program cost without that work being reflected in unit totals | The actual units were lower than imputed adopted units due to exceeding the target in 2023. PG&E forecasted 2 units for 2024 to balance the plan, as the program completed 6 units in 2023 which was 2 units over the imputed target. Of the 2 units forecasted for 2024, one was completed, while the other unit was carried over into 2025 due to risk of tie-in during the critical winter month of December | Under | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to upgrade natural GT pipelines in order to be capable of in-line inspection (where warranted) as outlined in PG&E's Pipeline Safety Enhancement Plan. This includes the installation of traditional pig launchers/receivers, replacement of pipe, elbows and main line valves, and additional retrofits required due to new technology.
112 | Capital | GT&S | 98 | GT Integrity Management | 98C | ILI Upgrades | Loss of Containment on Gas Transmission Pipeline | LOCTM-M005 Traditional ILI Upgrades | Ex 3, Ch 5 | No | On-going | Annual | 61141.5927 | 59175.4073 | 120317.0001 | 145155.4964 | 100827.3117 | 245982.808 | 41651.9043 | 125665.8079 | 70.39% | 104.4% | N/A | N/A | N/A | 4 | 4 | 8 | 6 | 1 | 7 | -3 | -1 | -75% | -12.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
(a) Units for AC Interference Mitigation MAT 3K4 can include # of Alternating Current Coupon Test Station ,# of ground rods installed, and # of zinc ribbons installed.
(a) Units for Cathodic Protection replacement MAT 3K7 can include # of groundbed replacements performed, and # of rectifiers repaired.
(b) Units for WELL - Reworks MAT 3L3 can include # of cementing wells, # of new gas wells, and # of tubing and packer, reliability/down hole safety valves.
(c) Workpapers clearly showed WELL Repair and Replace MAT 3L4 was based on a dollar forecast, not units x unit cost (i.e., non-unitized). WP 6-2 included a “1” under units to represent non-unitized work and this was misinterpreted to be an actual physical unit.
(d) WELL Controls and Continuous Monitoring MAT 3L5 includes unitized (# wells) and non-unitized work.
(e) StanPac MAT 44A is a consolidation of the recorded spend and work completed under various GT Integrity Management and GT Pipeline reliability programs.

## Nuc SRM MWC Expense
TABLE 4-7 2024 RSAR 2023 GRC CYCLE NUCLEAR GENERATION EXPENSE COMPARISON BY MWC FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | D | E | F | G1 | G2 | H | I1 | I2 | J | K1 | K2 | L1 | L2 | L3 | L4 | M | N1 | N2 | N3 | O | P
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program / Project Life (years) | Program / Project Year | Imputed Adopted Annual Costs |  | Imputed Cost for 2023 GRC Cycle to Date ($) (G1+G2) | Actual Annual Costs |  | Actual Cost for 2023 GRC Cycle to Date ($) (I1+I2) | Difference for 2024 ($) (I2-G2) | Difference for 2023 GRC Cycle to Date ($) (J-H) | Spending Percent Variance for 2024 (%) ((I2-G2)/G2*100) | Spending Percent Variance for 2023 GRC Cycle (%) (J/H) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | Forecast |  |  | Status | Completion Status Statement
[11 empty] | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs |  | 2023 Actual Costs | 2024 Actual Costs | [8 empty] | Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T)
1 | O&M Expense | Nuclear Generation | AB | Misc Expense | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 3 | No | On-going | Annual | 0 | 0 | 0 | 339.963 | 54.2897 | 394.2527 | 54.2897 | 394.2527 | 100.0% | 100.0% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs for miscellaneous support from both within and outside of Nuclear Generation.
2 | O&M Expense | Nuclear Generation | BP | Manage DCPP Business | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 3 | No | On-going | Annual | 13681.2538 | 13985.1376 | 27666.3914 | 12752.1994 | 12306.7352 | 25058.9347 | -1678.4024 | -2607.4567 | -12% | -9.425% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs for (1) all activities associated with representing PG&E and providing technical input to committees, owners groups, industry, professional and trade associations that support electric utilities; (2) dues to the Institute of Nuclear Power Operators, Nuclear Energy Institute, Strategic Teaming and Resource Sharing, and Diablo Canyon Independent Safety Committee; (3) land management activities; and (4) planned emergent work funding for the entire Nuclear Generation organization.
3 | O&M Expense | Nuclear Generation | BQ | DCPP Loss Prevention | SRM Total | SRM Total | Ex 5, Ch 3 | No | On-going | Annual | 42009.0817 | 45540.035 | 87549.1167 | 42675.2885 | 45423.0776 | 88098.3661 | -116.9574 | 549.2494 | -0.2568% | 0.6274% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs for management and implementation of the Security, Industrial Safety and Health, Emergency Preparedness and Fire Protection programs.
4 | O&M Expense | Nuclear Generation | BQ | DCPP Loss Prevention | Core Damaging Event | NCORE-C4 - Security from External and Internal Threats, and Emergency Response | Ex 5, Ch 3 | Yes | On-going | Annual | 37808.1735 | 40986.0315 | 78794.205 | 38407.7596 | 40880.7699 | 79288.5295 | -105.2616 | 494.3245 | -0.2568% | 0.6274% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | N/A
5 | O&M Expense | Nuclear Generation | BQ | DCPP Loss Prevention | Extended Shutdown | NSHUT-C4 - Security from External and Internal Threats, and Emergency Response | Ex 5, Ch 3 | Yes | On-going | Annual | 4200.9082 | 4554.0035 | 8754.9117 | 4267.5288 | 4542.3078 | 8809.8366 | -11.6957 | 54.9249 | -0.2568% | 0.6274% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | N/A
6 | O&M Expense | Nuclear Generation | BR | Operate DCPP Plant | SRM Total | SRM Total | Ex 5, Ch 3 | No | On-going | Annual | 76609.161 | 80901.7849 | 157510.946 | 78631.2505 | 80901.779 | 159533.0296 | -0.00592 | 2022.0836 | -7.318e-06% | 1.284% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs for all activities to operate the plant, radiation control, monitoring of plant chemistry, managing radioactive waste and hazardous waste generation, nuclear fuel movement, and reactor physics testing.
7 | O&M Expense | Nuclear Generation | BR | Operate DCPP Plant | Core Damaging Event | NCORE-C2 - Operating the Facility Within Requirements | Ex 5, Ch 3 | Yes | On-going | Annual | 51127.47 | 53242.4465 | 104369.9165 | 46887.75 | 52894.7379 | 99782.4879 | -347.7086 | -4587.4286 | -0.6531% | -4.395% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | N/A. Combined BR NSHUT-C2 & C4
8 | O&M Expense | Nuclear Generation | BR | Operate DCPP Plant | Extended Shutdown | NSHUT-C2 - Operating the Facility Within Requirements | Ex 5, Ch 3 | Yes | On-going | Annual | 5680.83 | 5915.8274 | 11596.6574 | 5209.75 | 5877.1931 | 11086.9431 | -38.6343 | -509.7143 | -0.6531% | -4.395% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | N/A. Combined BR NCORE-C2 & C5
9 | O&M Expense | Nuclear Generation | BR | Operate DCPP Plant | SRM (Non-RAMP) | SRM (Non-RAMP) | Ex 5, Ch 3 | Yes | On-going | Annual | 19800.861 | 21743.511 | 41544.372 | 26533.7505 | 22129.848 | 48663.5986 | 386.337 | 7119.2265 | 1.777% | 17.14% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs for all activities to operate the plant, radiation control, monitoring of plant chemistry, managing radioactive waste and hazardous waste generation, nuclear fuel movement, and reactor physics testing.
10 | O&M Expense | Nuclear Generation | BS | Maintain DCPP Plant Assets | SRM Total | SRM Total | Ex 5, Ch 3 | No | On-going | Annual | 91686.3425 | 91456.8399 | 183143.1825 | 97104.0566 | 91456.8512 | 188560.9078 | 0.01122 | 5417.7253 | 1.227e-05% | 2.958% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs for all preventative and corrective maintenance activities for systems, structures, and components at the plant.
11 | O&M Expense | Nuclear Generation | BS | Maintain DCPP Plant Assets | Core Damaging Event | NCORE-C1 - Maintaining the Systems | Ex 5, Ch 3 | Yes | On-going | Annual | 74928.69 | 74760.3639 | 149689.0539 | 78745.77 | 72020.6767 | 150766.4467 | -2739.6871 | 1077.3929 | -3.665% | 0.7198% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | N/A
12 | O&M Expense | Nuclear Generation | BS | Maintain DCPP Plant Assets | Extended Shutdown | NSHUT-C1 - Maintaining the Systems | Ex 5, Ch 3 | Yes | On-going | Annual | 8325.41 | 8306.7071 | 16632.1171 | 8749.53 | 8002.2974 | 16751.8274 | -304.4097 | 119.7103 | -3.665% | 0.7198% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | N/A
13 | O&M Expense | Nuclear Generation | BS | Maintain DCPP Plant Assets | SRM (Non-RAMP) | SRM (Non-RAMP) | Ex 5, Ch 3 | Yes | On-going | Annual | 8432.2425 | 8389.769 | 16822.0115 | 9608.7566 | 11433.877 | 21042.6336 | 3044.108 | 4220.6221 | 36.28% | 25.09% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs for all preventative and corrective maintenance activities for systems, structures, and components at the plant.
14 | O&M Expense | Nuclear Generation | BV | Maintain DCPP Plant Configurtn | SRM Total | SRM Total | Ex 5, Ch 3 | No | On-going | Annual | 34728.7323 | 35078.3446 | 69807.0769 | 38316.8818 | 35173.5364 | 73490.4182 | 95.1918 | 3683.3414 | 0.2714% | 5.276% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs for design engineering, system engineering, component engineering, reactor engineering, in service testing and inspection, reliability engineering, and fire protection engineering.
15 | O&M Expense | Nuclear Generation | BV | Maintain DCPP Plant Configurtn | Core Damaging Event | NCORE-C3 - Plant and System Configuration Control | Ex 5, Ch 3 | Yes | On-going | Annual | 23881.59 | 24475.0001 | 48356.5901 | 31615.65 | 23645.6616 | 55261.3116 | -829.3385 | 6904.7215 | -3.389% | 14.28% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | N/A
16 | O&M Expense | Nuclear Generation | BV | Maintain DCPP Plant Configurtn | Extended Shutdown | NSHUT-C3 - Plant and System Configuration Control | Ex 5, Ch 3 | Yes | On-going | Annual | 2653.51 | 2719.4445 | 5372.9545 | 3512.85 | 2627.2957 | 6140.1457 | -92.1487 | 767.1913 | -3.389% | 14.28% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | N/A
17 | O&M Expense | Nuclear Generation | BV | Maintain DCPP Plant Configurtn | SRM (Non-RAMP) | SRM (Non-RAMP) | Ex 5, Ch 3 | Yes | On-going | Annual | 8193.6323 | 7883.9 | 16077.5323 | 3188.3818 | 8900.579 | 12088.9608 | 1016.679 | -3988.5715 | 12.9% | -24.81% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | N/A
18 | O&M Expense | Nuclear Generation | IG | Manage Var Bal Acct Processes | SRM Total | SRM Total (Non-RAMP) | Ex 5, Ch 3 | No | On-going | Annual | 2716.6764 | 2744.4614 | 5461.1378 | 2776.0952 | 3243.1599 | 6019.2551 | 498.6985 | 558.1173 | 18.17% | 10.22% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a conti nuing effort to support costssubject to the two-way balancing account established for Nuclear Safety and Security regulatory mandated projects.

## Nuc SRM MWC Capital
TABLE 4-8 2024 RSAR 2023 GRC CYCLE NUCLEAR GENERATION CAPITAL COMPARISON BY MWC FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | D | E | F | G1 | G2 | H | I1 | I2 | J | K1 | K2 | L1 | L2 | L3 | L4 | M | N1 | N2 | N3 | O | P
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program / Project Life (years) | Program / Project Year | Imputed Adopted Annual Costs |  | Imputed Cost for 2023 GRC Cycle to Date ($) (G1+G2) | Actual Annual Costs |  | Actual Cost for 2023 GRC Cycle to Date ($) (I1+I2) | Difference for 2024 ($) (I2-G2) | Difference for 2023 GRC Cycle to Date ($) (J-H) | Spending Percent Variance for 2024 (%) ((I2-G2)/G2*100) | Spending Percent Variance for 2023 GRC Cycle (%) (J/H) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | Forecast |  |  | Status | Completion Status Statement
[11 empty] | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs |  | 2023 Actual Costs | 2024 Actual Costs | [8 empty] | Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T)
1 | Capital | Nuclear Generation | 20 | DCPP Capital | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 3 | No | On-going | annual | 10243.7821 | 5914.3196 | 16158.1017 | 8768.1264 | 4040.2912 | 12808.4175 | -1874.0285 | -3349.6842 | -31.69% | -20.73% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs for replacement of capital structures, systems and components that no longer can be maintained to safely and reliably operate and protect the plant.

## PowGen SRM MWC Expense
TABLE 4-13 2024 RSAR 2023 GRC CYCLE POWER GENERATION EXPENSE COMPARISON BY MWC FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | D | E | F | G1 | G2 | H | I1 | I2 | J | K1 | K2 | L1 | L2 | L3 | L4 | M | N1 | N2 | N3 | O | P
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program / Project Life (years) | Program / Project Year | Imputed Adopted Annual Costs |  | Imputed Cost for 2023 GRC Cycle to Date ($) (G1+G2) | Actual Annual Costs |  | Actual Cost for 2023 GRC Cycle to Date ($) (I1+I2) | Difference for 2024 ($) (I2-G2) | Difference for 2023 GRC Cycle to Date ($) (J-H) | Spending Percent Variance for 2024 (%) ((I2-G2)/G2*100) | Spending Percent Variance for 2023 GRC Cycle (%) (J/H) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | Forecast |  |  | Status | Completion Status Statement
[11 empty] | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs |  | 2023 Actual Costs | 2024 Actual Costs | [8 empty] | Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T)
1 | O&M Expense | Power Generation | AX | Maint Resv,Dams&Waterways | SRM Total | SRM Total | Ex 5, Ch 4 | No | On-going | annual | 30569.0081 | 30952.5299 | 61521.538 | 31022.5245 | 25128.2553 | 56150.7798 | -5824.2746 | -5370.7581 | -18.82% | -8.73% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs to maintain the hydro dams and water conveyance systems.
2 | O&M Expense | Power Generation | AX | Maint Resv,Dams&Waterways | Large Uncontrolled Water Release | C1 - Dam Safety Program | Ex 5, Ch 2 | Yes | N/A | N/A | 340.989 | 11115.0535 | 11456.0425 | 1918.285 | 9023.5523 | 10941.8373 | -2091.5012 | -514.2052 | -18.82% | -4.489% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | O&M Expense | Power Generation | AX | Maint Resv,Dams&Waterways | Large Uncontrolled Water Release | M1 - Internal Erosion Mitigation | Ex 5, Ch 2 | Yes | N/A | N/A | 0 | 15.4763 | 15.4763 | 580.8633 | 12.5614 | 593.4248 | -2.9148 | 577.9485 | -18.83% | 3734% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
4 | O&M Expense | Power Generation | AX | Maint Resv,Dams&Waterways | Large Uncontrolled Water Release | M2 - Spillway Remediation | Ex 5, Ch 2 | Yes | N/A | N/A | 0 | 0 | 0 | 150.2803 | 0 | 150.2803 | 0 | 150.2803 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | O&M Expense | Power Generation | AX | Maint Resv,Dams&Waterways | Large Uncontrolled Water Release | M4 - LLO Refurbishment | Ex 5, Ch 2 | Yes | N/A | N/A | 8754.285 | 0 | 8754.285 | 0 | 0 | 0 | 0 | -8754.285 | 100.0% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | O&M Expense | Power Generation | AX | Maint Resv,Dams&Waterways | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | Yes | N/A | N/A | 21473.7 | 19822.0002 | 41295.7002 | 28373.0963 | 16092.1416 | 44465.2378 | -3729.8586 | 3169.5377 | -18.82% | 7.675% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs to maintain the hydro dams and water conveyance systems.
7 | O&M Expense | Power Generation | BC | Perf Reimburs Wk for Oth | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | No | On-going | annual | 67.1284 | 72.7294 | 139.8578 | 353.2856 | -174.9713 | 178.3143 | -247.7007 | 38.4565 | -340.6% | 27.5% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs associated with performing maintenance work for third parties.
8 | O&M Expense | Power Generation | IG | Manage Var Bal Acct Processes | SRM Total | SRM Total | Ex 5, Ch 4 | No | On-going | annual | 26737.0334 | 26780.6091 | 53517.6425 | 25495.1831 | 31214.4464 | 56709.6295 | 4433.8372 | 3191.987 | 16.56% | 5.964% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs associated with regulatory compliance.
9 | O&M Expense | Power Generation | IG | Manage Var Bal Acct Processes | Large Uncontrolled Water Release | C1 - Dam Safety Program | Ex 5, Ch 2 | Yes | N/A | N/A | 497.731 | 3047.6333 | 3545.3643 | 49.358 | 3201.2612 | 3250.6192 | 153.6279 | -294.7451 | 5.041% | -8.314% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10 | O&M Expense | Power Generation | IG | Manage Var Bal Acct Processes | Large Uncontrolled Water Release | M2 - Spillway Remediation | Ex 5, Ch 2 | Yes | N/A | N/A | 485.934 | 881.082 | 1367.016 | 1396.133 | 925.4964 | 2321.6294 | 44.4144 | 954.6134 | 5.041% | 69.83% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 | O&M Expense | Power Generation | IG | Manage Var Bal Acct Processes | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | Yes | N/A | N/A | 25753.368 | 22851.8938 | 48605.2618 | 24049.68 | 27087.6887 | 51137.3687 | 4235.7949 | 2532.1069 | 18.54% | 5.21% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs associated with regulatory compliance.
12 | O&M Expense | Power Generation | KG | Operate Hydro Generation | SRM Total | SRM Total | Ex 5, Ch 4 | No | On-going | annual | 38215.7644 | 39099.9606 | 77315.725 | 38083.8685 | 40589.7913 | 78673.6599 | 1489.8308 | 1357.9349 | 3.81% | 1.756% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs associated with operating the hydro facilities safely and reliably.
13 | O&M Expense | Power Generation | KG | Operate Hydro Generation | Large Uncontrolled Water Release | M3 - Seismic Retrofit | Ex 5, Ch 2 | Yes | N/A | N/A | 0 | 0 | 0 | 213.4434 | 0 | 213.4434 | 0 | 213.4434 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 | O&M Expense | Power Generation | KG | Operate Hydro Generation | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | Yes | N/A | N/A | 38215.7644 | 39099.9606 | 77315.725 | 37870.4251 | 40589.7913 | 78460.2165 | 1489.8308 | 1144.4914 | 3.81% | 1.48% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs associated with operating the hydro facilities safely and reliably.
15 | O&M Expense | Power Generation | KH | Maint Hydro Generating Equip | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | No | On-going | annual | 24467.7421 | 24988.9983 | 49456.7405 | 24223.5652 | 24234.1136 | 48457.6788 | -754.8847 | -999.0617 | -3.021% | -2.02% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs associated with maintaining the hydro generation equipment.
16 | O&M Expense | Power Generation | KI | Maint Hydro Bldg,Grnd,Infrast | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | No | On-going | annual | 15363.235 | 15586.2717 | 30949.5068 | 13579.1383 | 12155.6218 | 25734.7601 | -3430.6499 | -5214.7467 | -22.01% | -16.85% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs associated with maintaining the buildings, grounds and infrastructure that support hydroelectric generation activities.
17 | O&M Expense | Power Generation | KJ | License Compliance Hydro Gen | SRM Total | SRM Total | Ex 5, Ch 4 | No | On-going | annual | 25712.7587 | 25987.814 | 51700.5727 | 24591.4514 | 24475.5289 | 49066.9803 | -1512.2851 | -2633.5924 | -5.819% | -5.094% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs associated with maintaining FERC license compliance to support hydroelectric generation activities.
18 | O&M Expense | Power Generation | KJ | License Compliance Hydro Gen | Large Uncontrolled Water Release | C1 - Dam Safety Program | Ex 5, Ch 2 | Yes | N/A | N/A | 9068.986 | 10161.2353 | 19230.2213 | 9598.3182 | 9569.9319 | 19168.2501 | -591.3034 | -61.9712 | -5.819% | -0.3223% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19 | O&M Expense | Power Generation | KJ | License Compliance Hydro Gen | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | Yes | N/A | N/A | 16643.772 | 15826.5787 | 32470.3507 | 14993.133 | 14905.597 | 29898.73 | -920.9817 | -2571.6207 | -5.819% | -7.92% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs associated with maintaining FERC license compliance to support hydroelectric generation activities.
20 | O&M Expense | Power Generation | KK | Operate Fossil Generation | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 14949.753 | 15230.3476 | 30180.1007 | 15712.7888 | 15827.5756 | 31540.3644 | 597.228 | 1360.2637 | 3.921% | 4.507% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs to operate the fossil facilities safely and reliably.
21 | O&M Expense | Power Generation | KL | Maint Fossil Generating Equip | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 31949.3183 | 32144.74 | 64094.0583 | 20725.8233 | 22265.4242 | 42991.2475 | -9879.3158 | -21102.8108 | -30.73% | -32.92% | NO | YES | Program expenses were below imputed adopted values due to the Long-Term Service Agreement costs, which are levelized in the imputed adopted value; however, the outage work associated with these costs only occurs on a periodic basis once every 4 to 6 years depending on operating profile. No major outage tied to the Long-Term Service Agreement occurred in 2024 at either Gateway Generation Station or Colusa Generation Station. Thus, no actual costs tied to the Agreement were recorded in 2024. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs to maintain fossil power generating station equipment.
22 | O&M Expense | Power Generation | KM | Maint Fossil Bldg,Grnd,Infrast | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 3318.641 | 3329.8516 | 6648.4927 | 2934.2005 | 2905.8143 | 5840.0148 | -424.0373 | -808.4779 | -12.73% | -12.16% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs associated with maintaining the buildings, grounds and infrastructure that support fossil generation activities.
23 | O&M Expense | Power Generation | KQ | Operate Alternative Gen | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 484.332 | 494.7015 | 979.0336 | 3406.6967 | 2971.6486 | 6378.3453 | 2476.9471 | 5399.3118 | 500.7% | 551.5% | NO | NO | Below variance threshold. | Over | Over | Over | Emergent | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs to operate alternative generation sites. In 2022, PG&E transferred O&M responsibilities for the Elkhorn Battery Energy Storage Station from Electric Distribution (Exhibit 4, MWC AB) to Power Generation (Exhibit 5, MWCs KQ and KR). Since the transfer occurred after the 2023 GRC was filed, the imputed adopted amounts for MWC KQ do not reflect Power Generation's ongoing O&M costs for the facility. Starting in the 2027 GRC, the Elkhorn Battery Energy Storage Station O&M costs will be forecast in the Energy Supply Exhibit.
24 | O&M Expense | Power Generation | KR | Maint AltGen Generating Equip | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 1351.6461 | 1367.03 | 2718.6761 | 3905.7735 | 6745.4943 | 10651.2678 | 5378.4643 | 7932.5917 | 393.4% | 291.8% | NO | YES | Program expenses were above imputed adopted values due to the transfer of maintenance responsibilities of the Elkhorn Battery Energy Storage System from Electric Distribution to Energy Supply in 2022. The transfer happened part-way through 2022, which was not reflected in the imputed regulatory value informed by the 2023 GRC. | Over | Over | Over | Emergent | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs to maintain alternative generation sites. In 2022, PG&E transferred O&M responsibilities for the Elkhorn Battery Energy Storage Station from Electric Distribution (Exhibit 4, MWC AB) to Power Generation (Exhibit 5, MWCs KQ and KR). Since the transfer occurred after the 2023 GRC was filed, the imputed adopted amounts for MWC KR do not reflect Power Generation's ongoing O&M costs for the facility. Starting in the 2027 GRC, the Elkhorn Battery Energy Storage Station O&M costs will be forecast in the Energy Supply Exhibit.
25 | O&M Expense | Power Generation | KS | Maint AltGen Bldg,Grnd,Infrast | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 566.7765 | 569.0329 | 1135.8093 | 911.2686 | 465.2042 | 1376.4728 | -103.8286 | 240.6635 | -18.25% | 21.19% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs associated with maintaining the solar photovoltaic generation common facilities.

## PowGen SRM MWC Capital
TABLE 4-14 2024 RSAR 2023 GRC CYCLE POWER GENERATION CAPITAL COMPARISON BY MWC FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | D | E | F | G1 | G2 | H | I1 | I2 | J | K1 | K2 | L1 | L2 | L3 | L4 | M | N1 | N2 | N3 | O | P
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program / Project Life (years) | Program / Project Year | Imputed Adopted Annual Costs |  | Imputed Cost for 2023 GRC Cycle to Date ($) (G1+G2) | Actual Annual Costs |  | Actual Cost for 2023 GRC Cycle to Date ($) (I1+I2) | Difference for 2024 ($) (I2-G2) | Difference for 2023 GRC Cycle to Date ($) (J-H) | Spending Percent Variance for 2024 (%) ((I2-G2)/G2*100) | Spending Percent Variance for 2023 GRC Cycle (%) (J/H) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | Forecast |  |  | Status | Completion Status Statement
[11 empty] | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs |  | 2023 Actual Costs | 2024 Actual Costs | [8 empty] | Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T)
1 | Capital | Power Generation | 2L | Instl/Rpl for Hydro Safety&Reg | SRM Total | SRM Total | Ex 5, Ch 4 | No | On-going | annual | 63080.1525 | 47169.5723 | 110249.7248 | 25395.9211 | 69798.2683 | 95194.1894 | 22628.696 | -15055.5354 | 47.97% | -13.66% | YES | YES | Program expenses were above imputed adopted values due to rescheduled work from 2023 into the 2024-2026 period, including the following work: Fordyce Dam Leakage Reduction, Pit 3 Powerhouse Seismic Retrofit. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support capital costs primarily related to employee or public safety and regulatory requirements that are not connected with relicensing for hydroelectric generation.
2 | Capital | Power Generation | 2L | Instl/Rpl for Hydro Safety&Reg | Large Uncontrolled Water Release | M1 - Internal Erosion Mitigation | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 25100.8543 | 27825.3307 | 52926.185 | 6464.5766 | 41163.5218 | 47628.0984 | 13338.1911 | -5298.0866 | 47.94% | -10.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | Capital | Power Generation | 2L | Instl/Rpl for Hydro Safety&Reg | Large Uncontrolled Water Release | M2 - Spillway Remediation | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 4225.3609 | 339.6209 | 4564.9819 | 577.827 | 502.4199 | 1080.2469 | 162.7989 | -3484.735 | 47.94% | -76.34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
4 | Capital | Power Generation | 2L | Instl/Rpl for Hydro Safety&Reg | Large Uncontrolled Water Release | M3 - Seismic Retrofit | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 26938.3791 | 292.4513 | 27230.8305 | 333.5723 | 432.639 | 766.2113 | 140.1877 | -26464.6191 | 47.94% | -97.19% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | Capital | Power Generation | 2L | Instl/Rpl for Hydro Safety&Reg | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4, p. 4-78 | Yes | N/A | N/A | 6814.5489 | 18712.1694 | 25526.7182 | 18019.91 | 27699.6876 | 45719.5976 | 8987.5182 | 20192.8794 | 48.03% | 79.1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | Capital | Power Generation | 2M | Instal/Repl Hydro Gneratng Eqp | SRM Total | SRM Total |  | No | On-going | annual | 84621.5813 | 92060.5492 | 176682.1305 | 115907.7139 | 196325.8908 | 312233.6047 | 104265.3416 | 135551.4742 | 113.3% | 76.72% | YES | YES | Program expenses were above imputed adopted values due to: 1) emergent work and 2) rescheduled work. The emergent work includes Spaulding Pressure Relief Valve Discharge Liner Replacement, Runner and Wicket Gate Replacement, Stanislaus Powerhouse Replace Thrust Bearing Cooling Coil, Kings River Replace Turbine Shut-off Valve. The rescheduled work includes Caribou Units 2-5 Generator Rewind, Bucks Creek Powerhouse Replace Unit 2 Turbine Bearing / Shaft, and Helms Units 1, 2 and 3 Replace Turbine Shut-off Valves. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support capital costs to install/replace generating equipment or components to support hydroelectric generation activities.
7 | Capital | Power Generation | 2M | Instal/Repl Hydro Gneratng Eqp | Large Uncontrolled Water Release | M4 - LLO Refurbishments |  | Yes | N/A | N/A | 0 | 18.4121 | 18.4121 | 0 | 39.265 | 39.265 | 20.8529 | 20.8529 | 113.3% | 113.3% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 | Capital | Power Generation | 2M | Instal/Repl Hydro Gneratng Eqp | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | Yes | N/A | N/A | 84621.5813 | 92042.137 | 176663.7184 | 115907.7139 | 196286.6258 | 312194.3397 | 104244.4888 | 135530.6214 | 113.3% | 76.72% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 | Capital | Power Generation | 2N | Instal/Repl Resv,Dams&Waterway | SRM Total | SRM Total | Ex 5, Ch 4 | No | On-going | annual | 42763.8477 | 30166.7524 | 72930.6001 | 46960.5066 | 102332.5806 | 149293.0872 | 72165.8282 | 76362.4872 | 239.2% | 104.7% | YES | YES | Program expenses were above imputed adopted values due to: 1) emergent work and 2) rescheduled work. The emergent work includes South Yuba Pipe Replacement, Lake Almanor Canyon Dam Low Level Outlet Replace Gate 1 Stem, and Courtright Dam Concrete Liner Repairs. The rescheduled work includes Courtright Dam Upgrade I/D Gate Control, J.B. Black Iron Canyon Dam Low Level Outlet Replace Actuator and Piping, Helms Install Incline Tunnel Liner, and Rock Creek Cresta Coffer Dam Installation. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support capital costs to install/replace reservoirs, dams and waterways.
10 | Capital | Power Generation | 2N | Instal/Repl Resv,Dams&Waterway | Large Uncontrolled Water Release | C1 - Dam Safety Program | Ex 5, Ch 4, p. 4-78 | Yes | N/A | N/A | 0 | 199.1006 | 199.1006 | 1034.5864 | 675.3953 | 1709.9817 | 476.2947 | 1510.8811 | 239.2% | 758.9% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 | Capital | Power Generation | 2N | Instal/Repl Resv,Dams&Waterway | Large Uncontrolled Water Release | M1 - Internal Erosion Mitigation | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 416.4343 | 2292.6732 | 2709.1075 | 3433.495 | 7777.2762 | 11210.7712 | 5484.6031 | 8501.6637 | 239.2% | 313.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | Capital | Power Generation | 2N | Instal/Repl Resv,Dams&Waterway | Large Uncontrolled Water Release | M2 - Spillway Remediation | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 173.4929 | 2190.1062 | 2363.5992 | 4727.3818 | 7429.3457 | 12156.7275 | 5239.2395 | 9793.1284 | 239.2% | 414.3% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | Capital | Power Generation | 2N | Instal/Repl Resv,Dams&Waterway | Large Uncontrolled Water Release | M3 - Seismic Retrofit | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 0 | 90.5003 | 90.5003 | 51.4262 | 306.9977 | 358.4239 | 216.4974 | 267.9237 | 239.2% | 296% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 | Capital | Power Generation | 2N | Instal/Repl Resv,Dams&Waterway | Large Uncontrolled Water Release | M4 - LLO Refurbishments | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 8825.6029 | 8051.5062 | 16877.1091 | 8428.131 | 27312.5653 | 35740.6963 | 19261.0591 | 18863.5872 | 239.2% | 111.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | Capital | Power Generation | 2N | Instal/Repl Resv,Dams&Waterway | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4, p. 4-78 | Yes | N/A | N/A | 33348.1037 | 17342.8659 | 50690.9696 | 29285.4841 | 58831.0003 | 88116.4845 | 41488.1344 | 37425.5148 | 239.2% | 73.83% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
16 | Capital | Power Generation | 2P | Instl/Repl Hydr BldgGrndInfrst | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | No | On-going | annual | 26624.6872 | 14275.4778 | 40900.1649 | 41827.1777 | 37028.1366 | 78855.3143 | 22752.6589 | 37955.1494 | 159.4% | 92.8% | YES | YES | Program expenses were above imputed adopted values due to emergent work. The emergent work includes DeSabla Powerhouse Road Improvements, Caribou Road Improvements, Pit 5 Powerhouse Road, Cedar Mill Property Purchase, Spaulding Tram Improvements, and Auburn Regional Service Center Power Generation Command Center. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support capital costs to install/replace buildings, grounds and infrastructure to support hydroelectric generation activities, including roads and bridges.
17 | Capital | Power Generation | 2R | Instl/Rpl for Fosil Safety&Reg | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | No | On-going | annual | 0 | 0 | 0 | 0 | 118.6012 | 118.6012 | 118.6012 | 118.6012 | 100.0% | 100.0% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support capital costs to install or replace equipment related to employee safety or regulatory requirements to support fossil generation activities. As the fossil generating facilities age, the capital replacement costs accelerate.
18 | Capital | Power Generation | 2S | Instal/Repl Fosil Gneratng Eqp | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 3487.4164 | 5524.3601 | 9011.7765 | 14734.9457 | 17887.1264 | 32622.0721 | 12362.7663 | 23610.2956 | 223.8% | 262% | YES | YES | Program expenditures were above imputed adopted values due to: 1) the Humboldt Bay Generating Station annual capital outage program spend, driven by the continued wear and tear of the units, 2) the Humboldt Bay Generating Station UNIC engine control system upgrades, and 3) the Gateway Generating Station Main Steam Stop/Control Valve Replacement following a failure. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support capital costs to install new or replace existing generating equipment or components to support fossil generation activities. As the fossil generating facilities age, the capital replacement costs accelerate.
19 | Capital | Power Generation | 2T | Instl/Repl Fosl BldgGrndInfrst | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 1588.2693 | 108.9352 | 1697.2045 | 1149.2242 | 1251.4916 | 2400.7159 | 1142.5564 | 703.5114 | 1049% | 41.45% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support capital costs to install or replace new buildings, grounds and infrastructure on the plant site to support fossil generation activities. As the fossil generating facilities age, the capital replacement costs accelerate.
20 | Capital | Power Generation | 3A | Instl/Rpl for AltGen Safty&Reg | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 6.5492 | 6.5798 | 13.129 | 0 | 0 | 0 | -6.5798 | -13.129 | -100% | -100% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support capital costs to install or replace safety equipment for solar generation. As the solar generating facilities age, the capital replacement costs accelerate.
21 | Capital | Power Generation | 3B | Instal/Repl AltGen GneratngEqp | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 718.6413 | 722.0008 | 1440.642 | 2064.6789 | 5307.5563 | 7372.2352 | 4585.5555 | 5931.5931 | 635.1% | 411.7% | NO | NO | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support capital costs to install or replace solar photovoltaic generation equipment. As the solar generating facilities age, the capital replacement costs accelerate.
22 | Capital | Power Generation | 3H | Hydroelec Lic & Lic Conditions | SRM Total | SRM Total | Ex 5, Ch 4 | No | On-going | annual | 145223.769 | 154204.4812 | 299428.2502 | 35356.672 | 40795.2604 | 76151.9324 | -113409.2207 | -223276.3178 | -73.54% | -74.57% | YES | YES | Program expenses were below imputed adopted values due to two key drivers: (1) a delay in the regulatory process related to FERC operating license renewals for the Drum-Spaulding license, McCloud-Pit license and the Upper North Fork Feather River license. Delays in license renewals create delays in the forecasted start date of the capital work required as part of the new operating license; and (2) rescheduled capital projects originating from the spillway assessment recommendations resulting from the 2017 Oroville spillway incident. The rescheduled projects include McCloud Spillway improvement and Tiger Creek Regulator Spillway Improvement. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. Some work has been rescheduled to future GRC periods. The purpose of this program is a continuing effort to support capital costs assigned to the HLBA. This MWC includes: costs for relicensing existing FERC licenses; obtaining major license amendments; surrendering licenses for facilities that are no longer economic; complying with the conditions required by existing and newly issued FERC licenses and major license amendments; and anticipated to be required by pending new FERC licenses for licenses. This includes costs for all pending licenses as of January 1, 2014, and new licenses applied for after January 1, 2014. This MWC also includes the costs associated with work required because of the 2017 Oroville spillway incident.
23 | Capital | Power Generation | 3H | Hydroelec Lic & Lic Conditions | Large Uncontrolled Water Release | M2 - Spillway Remediation | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 73892.7582 | 81296.6025 | 155189.3606 | 18869.1714 | 21507.2614 | 40376.4328 | -59789.3411 | -114812.9278 | -73.54% | -73.98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
24 | Capital | Power Generation | 3H | Hydroelec Lic & Lic Conditions | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4, p. 4-78 | Yes | N/A | N/A | 71329.5586 | 72907.8787 | 144237.4373 | 16477.501 | 19287.999 | 35765.5 | -53619.8797 | -108471.9373 | -73.54% | -75.2% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## SharedSvc & IT SRM MWC Expense
TABLE 6-3 2024 RSAR 2023 GRC CYCLE SHARED SERVCES/IT EXPENSE COMPARISON BY MAT FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | D | E | F | G1 | G2 | H | I1 | I2 | J | K1 | K2 | L1 | L2 | L3 | L4 | M | N1 | N2 | N3 | O | P
Line No | Type (O&M Expense or Capital) | Functional Area | MWC (a) | MWC Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program / Project Life (years) | Program / Project Year | Imputed Adopted Annual Costs |  | Imputed Cost for 2023 GRC Cycle to Date ($) (G1+G2) | Actual Annual Costs |  | Actual Cost for 2023 GRC Cycle to Date ($) (I1+I2) | Difference for 2024 ($) (I2-G2) | Difference for 2023 GRC Cycle to Date ($) (J-H) | Spending Percent Variance for 2024 (%) ((I2-G2)/G2*100) | Spending Percent Variance for 2023 GRC Cycle (%) (J/H) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | Forecast |  |  | Status | Completion Status Statement
[11 empty] | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs |  | 2023 Actual Costs | 2024 Actual Costs | [8 empty] | Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T)
1 | O&M Expense | Shared Services | AB | Misc Expense | SRM Total | SRM Total | Ex 7, Ch 1 Ex 7, Ch 2 Ex 7, Ch 7 | No | On-going | Annual | 17179.8844 | 35034.6094 | 52214.4938 | 17249.7296 | 25541.5314 | 42791.261 | -9493.078 | -9423.2328 | -27.1% | -18.05% | NO | YES | Program expense were below imputed regulatory values due to the work being forecast and adopted in MWC AB as a part of the 2023 GRC Final Decision, but executed in MWC TA for Aviation Services and MWC JV for Enterprise Data Management. The decision to execute the forecast work in a different MWC was made after the 2023 GRC was submitted. The Aviation Services program in MWC AB primarily represents labor and non-labor expenditures required to maintain and operate Aviation assets to support both Wildfire Mitigations and Operations & Maintenance work and is in alignment with the safety commitments made in support of stopping Wildfires. The Enterprise Data Management program in MWC AB primarily represents labor and non-labor costs required to establish data management practices that improve the quality and governance of data and drive data informed decision making. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to provide various safety initiatives that address employees, contractors, and customers. The initiatives support mitigations for Employees Safety Incident, Motor Vehicle Safety Incident, Wildfire, and Records and Information Management risks.
2 | O&M Expense | Shared Services | AB | Misc Expense | Employee Safety Incident (EMPSI) | Corrective Action Program (EMPSI-PRGB) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 3553.5893 | 3123.224 | 6676.8133 | 3123.224 | 6676.8133 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | O&M Expense | Shared Services | AB | Misc Expense | Employee Safety Incident (EMPSI) | Employee Health & Safety Guidance, Training & Oversight (EMPSI-PRGA) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 4110 | 510.228 | 4620.228 | 510.228 | 4620.228 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
4 | O&M Expense | Shared Services | AB | Misc Expense | Employee Safety Incident (EMPSI) | Enterprise Safety Management System (EMPSI-M01B) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 678 | 0 | 678 | 0 | 678 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | O&M Expense | Shared Services | AB | Misc Expense | Employee Safety Incident (EMPSI) | PG&E Safety Excellence Management System Implementation (EMPSI-PRGF) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 662 | 2851.409 | 3513.409 | 2851.409 | 3513.409 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | O&M Expense | Shared Services | AB | Misc Expense | Motor Vehicle Safety Incident (MTRSI) | Transportation Safety (PRGA) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 3150 | 2697.426 | 5847.426 | 2697.426 | 5847.426 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 | O&M Expense | Shared Services | AB | Misc Expense | Contractor Safety Incident (CNTSI) | Contractor Pre-Qualification Program (PRGA) Contractor Safety Oversight and Compliance (PRGB) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 4443.961 | 4443.961 | 4443.961 | 4443.961 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 | O&M Expense | Shared Services | AB | Misc Expense | Records and Information Management (RECIM) | Accountability Control (RECIM-C001) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 1047.9856 | 1047.9856 | 1047.9856 | 1047.9856 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 | O&M Expense | Shared Services | AB | Misc Expense | Records and Information Management (RECIM) | Transparency Control (RECIM-C002) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 971.7685 | 971.7685 | 971.7685 | 971.7685 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10 | O&M Expense | Shared Services | AB | Misc Expense | Records and Information Management (RECIM) | Compliance Control (RECIM-C003) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 845.7985 | 845.7985 | 845.7985 | 845.7985 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 | O&M Expense | Shared Services | AB | Misc Expense | Records and Information Management (RECIM) | Retention Control (RECIM-C004) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 2129.4212 | 2129.4212 | 2129.4212 | 2129.4212 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | O&M Expense | Shared Services | AB | Misc Expense | Records and Information Management (RECIM) | Protection Control (RECIM-C005) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 1790.3083 | 1790.3083 | 1790.3083 | 1790.3083 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | O&M Expense | Shared Services | AB | Misc Expense | Records and Information Management (RECIM) | Availability Control (RECIM-C006) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 391.6714 | 391.6714 | 391.6714 | 391.6714 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 | O&M Expense | Shared Services | AB | Misc Expense | Records and Information Management (RECIM) | Disposition Control (RECIM-C007) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 582.2142 | 582.2142 | 582.2142 | 582.2142 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | O&M Expense | Shared Services | AB | Misc Expense | Records and Information Management (RECIM) | Integrity Control (RECIM-C008) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 217.0071 | 217.0071 | 217.0071 | 217.0071 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
16 | O&M Expense | Shared Services | AB | Misc Expense | Records and Information Management (RECIM) | Retention Mitigation (RECIM-M004) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 211.7143 | 211.7143 | 211.7143 | 211.7143 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17 | O&M Expense | Shared Services | AB | Misc Expense | Records and Information Management (RECIM) | Unstructured Mitigation (RECIM-M007) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 961.0499 | 961.0499 | 961.0499 | 961.0499 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
18 | O&M Expense | Shared Services | AB | Misc Expense | Records and Information Management (RECIM) | Integrity Mitigation (RECIM-M011) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 339.9075 | 339.9075 | 339.9075 | 339.9075 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19 | O&M Expense | Shared Services | AB | Misc Expense | Records and Information Management (RECIM) | Structured Mitigation (RECIM-M013) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 542.46 | 542.46 | 542.46 | 542.46 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
20 | O&M Expense | Shared Services | AB | Misc Expense | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 1 Ex 7, Ch 2 Ex 7, Ch 7 | No | On-going | Annual | 0 | 0 | 0 | 5096.1403 | 0.8131 | 5096.9534 | 0.8131 | 5096.9534 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | O&M Expense | Shared Services | AK | Manage Environmental Oper | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 519.603 | 803.1103 | 1322.7133 | 803.1103 | 1322.7133 | 100.0% | 100.0% | NO | NO | Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address environmental operations and compliance support as well as permitting. These program investments specifically address procedures for managing hazardous waste.
22 | O&M Expense | Shared Services | BI | Maint Buildings | SRM Total | SRM Total | Ex 7, Ch 5 | No | On-going | Annual | 6005.6381 | 6122.2379 | 12127.8761 | 690.5606 | 2643.6611 | 3334.2217 | -3478.5769 | -8793.6544 | -56.82% | -72.51% | NO | NO | Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address repair and maintenance of buildings and building components to optimize the life of building components, improve equipment operating efficiencies, and increase operating reliability of buildings and yards.
23 | O&M Expense | Shared Services | BI | Maint Buildings | Real Estate and Facilities Failure (REFFL) | Service Center Optimization (REFFL-C002) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 413.8151 | 0 | 413.8151 | 0 | 413.8151 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
24 | O&M Expense | Shared Services | BI | Maint Buildings | Real Estate and Facilities Failure (REFFL) | Facilities Mgmt and Prevent Maint Prgm (REFFL-C004) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 167.5727 | 1397.0154 | 1564.5881 | 1397.0154 | 1564.5881 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
25 | O&M Expense | Shared Services | BI | Maint Buildings | Real Estate and Facilities Failure (REFFL) | Renovate / Relocate Facilities Other than SFGO (REFFL-M006) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 323.625 | 0 | 323.625 | 0 | 323.625 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
26 | O&M Expense | Shared Services | BI | Maint Buildings | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 5 | No | On-going | Annual | 0 | 0 | 0 | -214.4522 | 1246.6457 | 1032.1935 | 1246.6457 | 1032.1935 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
27 | O&M Expense | Shared Services | CR | Mnge Waste Disp & Transp | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 6 | No | On-going | Annual | 2367.9516 | 2351.1881 | 4719.1396 | 2472.6187 | 3377.0085 | 5849.6272 | 1025.8204 | 1130.4875 | 43.63% | 23.96% | NO | NO | Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address the transportation and disposal of hazardous and other regulated wastes in accordance with federal and state laws and regulations.
28 | O&M Expense | Shared Services | EP | Manage Property & Bldgs | SRM Total | SRM Total | Ex 7, Ch 5 | No | On-going | Annual | 97560.1424 | 99454.2781 | 197014.4205 | 120592.7706 | 198432.192 | 319024.9626 | 98977.9139 | 122010.542 | 99.52% | 61.93% | YES | YES | Program expenses exceeded imputed regulatory values primarily due to required facilities maintenance work driven by an aging portfolio of facilities; escalation of utilities higher than inflation; and increases in planned headcount to support company operations as part of CRESS organization transformation which included the addition of the Site Owner Program. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address operations and maintenance of facilities and shared conference centers to optimize the life of facilities, address safety issues, and improve operations and reliability of facility assets and related equipment.
29 | O&M Expense | Shared Services | EP | Manage Property & Bldgs | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 5 | No | On-going | Annual | 0 | 0 | 0 | 119954.7123 | 198432.192 | 318386.9043 | 198432.192 | 318386.9043 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
30 | O&M Expense | Shared Services | EP | Manage Property & Bldgs | Real Estate and Facilities Failure (REFFL) | Renovate / Relocate Facilities Other than SFGO (REFFL-M006) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 638.0583 | 0 | 638.0583 | 0 | 638.0583 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
31 | O&M Expense | Shared Services | FL | Safety Engineering & OSHA Cmpl | SRM Total | SRM Total | Ex 7, Ch 1 | No | On-going | Annual | 18980.1136 | 19554.9644 | 38535.078 | 4614.2332 | 5410.9301 | 10025.1633 | -14144.0343 | -28509.9147 | -72.33% | -73.98% | YES | YES | Program expense were below imputed regulatory values due to the work being forecast and adopted in MWC FL as a part of the 2023 GRC Final Decision, but executed in MWC OS. The decision to execute the forecast work in a different MWC was made after the 2023 GRC was submitted. This program primarily represents the development and deployment of the Regional Safety Program and is in alignment with the safety commitments made following the Plan of Reorganization. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to provide various safety initiatives that address both employees and contractors. The initiatives support mitigations for Employees Safety Incident, Contractor Safety Incident, and Motor Vehicle Safety Incident risks.
32 | O&M Expense | Shared Services | FL | Safety Engineering & OSHA Cmpl | Contractor Safety Incident (CNTSI) | Contractor Safety Oversight and Compliance (PRGB) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 1200 | 2335.538 | 3535.538 | 2335.538 | 3535.538 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
33 | O&M Expense | Shared Services | FL | Safety Engineering & OSHA Cmpl | Contractor Safety Incident (CNTSI) | Contractor Pre-Qualification Program (PRGA) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 125 | 2335.538 | 2460.538 | 2335.538 | 2460.538 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
34 | O&M Expense | Shared Services | FL | Safety Engineering & OSHA Cmpl | Employee Safety Incident (EMPSI) | Employee Health & Safety Guidance, Training & Oversight (EMPSI-PRGA) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 419.75 | 0 | 419.75 | 0 | 419.75 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
35 | O&M Expense | Shared Services | FL | Safety Engineering & OSHA Cmpl | Employee Safety Incident (EMPSI) | SIF Prevention Program and Field Oversight (PRGC) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 2304.4332 | 464.4626 | 2768.8958 | 464.4626 | 2768.8958 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
36 | O&M Expense | Shared Services | FL | Safety Engineering & OSHA Cmpl | Motor Vehicle Safety Incident (MVSI) | Transportation Safety (PRGA) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 565 | 91.6233 | 656.6233 | 91.6233 | 656.6233 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
37 | O&M Expense | Shared Services | FL | Safety Engineering & OSHA Cmpl | Employee Safety Incident (EMPSI) | Enterprise Safety Management System (EMPSI-M01B) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 183.7682 | 183.7682 | 183.7682 | 183.7682 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
38 | O&M Expense | Shared Services | IG | Manage Var Bal Acct Processes | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7 , Ch 5 | No | On-going | Annual | 0 | 1211.26 | 1211.26 | 1255.9957 | 2476.3541 | 3732.3497 | 1265.0941 | 2521.0897 | 104.4% | 208.1% | NO | NO | Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address ongoing wildfire mitigation program support costs foreacast and described in the 2023 GRC. These investments specifically account for Land and environmental Management's work with the Water Board in compliance with Senate Bill 901 to develop and implement a statewide permit program for wildfire mitigation work activities located in and adjacent to waters of the state.
39 | O&M Expense | Shared Services | JH | Implement RealEstate Strategy | SRM Total | SRM Total | Ex 7 , Ch 5 | No | On-going | Annual | 6780.8434 | 6912.4939 | 13693.3373 | 8411.7406 | 4206.6558 | 12618.3963 | -2705.8381 | -1074.9409 | -39.14% | -7.85% | NO | NO | Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address long-term real estate strategy development which needs to address both resource scalability and company affordability goals.
40 | O&M Expense | Shared Services | JH | Implement RealEstate Strategy | Real Estate and Facilities Failure (REFFL) | Facilities Mgmt and Prevent Maint Prgm (REFFL-C004) | Ex 7 , Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 1566.7282 | 13.7862 | 1580.5145 | 13.7862 | 1580.5145 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
41 | O&M Expense | Shared Services | JH | Implement RealEstate Strategy | Real Estate and Facilities Failure (REFFL) | Renovate / Relocate Facilities Other than SFGO (REFFL-M006) | Ex 7 , Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 791.5879 | 0 | 791.5879 | 0 | 791.5879 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | O&M Expense | Shared Services | JH | Implement RealEstate Strategy | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7 , Ch 5 | No | On-going | Annual | 0 | 0 | 0 | 6053.4244 | 4192.8695 | 10246.2939 | 4192.8695 | 10246.2939 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
43 | O&M Expense | Shared Services | JL | Procure Materials & Services | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 4 | No | On-going | Annual | 0 | 0 | 0 | 3930.4613 | 3001.5704 | 6932.0316 | 3001.5704 | 6932.0316 | 100.0% | 100.0% | NO | NO | Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address the company procurement process to improve organizational effectiveness and to promote positive vendor relationships with a diverse supplier base.
44 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra | SRM Total | SRM Total | Ex 7, Ch 9 | No | On-going | Annual | 32806.2993 | 37893.3312 | 70699.6306 | 32417.7875 | 33765.358 | 66183.1455 | -4127.9732 | -4516.485 | -10.89% | -6.388% | NO | NO | Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address the ongoing operations and maintenance of software and hardware technology assets and supporting systems, a majority of the program will focus spend on supporting expense mitigation and control investments to improve the Cyber Security Incident risk as well as the cross-cutting Records and Information Management risk.
45 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra | Cyber Security Incident (CYBER) | Security Intelligence and Operations Center (CYBER-C001) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 5261.4102 | 6070.862 | 11332.2722 | 6070.862 | 11332.2722 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
46 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra | Cyber Security Incident (CYBER) | Cybersecurity Risk and Strategy (CYBER-C002) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 9228.6591 | 9823.644 | 19052.3031 | 9823.644 | 19052.3031 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
47 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra | Cyber Security Incident (CYBER) | Cybersecurity Services (CYBER-C003) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 13325.5324 | 17175.124 | 30500.6564 | 17175.124 | 30500.6564 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
48 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra | Cyber Security Incident (CYBER) | Communications (CYBER-C004) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | -27.9746 | -49.317 | -77.2916 | -49.317 | -77.2916 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
49 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra | Cyber Security Incident (CYBER) | Identify (CYBER-M001) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 153.6222 | 0 | 153.6222 | 0 | 153.6222 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
50 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra | Cyber Security Incident (CYBER) | Protect (CYBER-M002) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 3628.002 | 0 | 3628.002 | 0 | 3628.002 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
51 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra | Cyber Security Incident (CYBER) | Detect (CYBER-M003) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
52 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra | Cyber Security Incident (CYBER) | Respond (CYBER-M004) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 32.2392 | 0 | 32.2392 | 0 | 32.2392 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
53 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra | Records and Information Management (RECIM) | Unstructured Mitigation (RECIM-M007) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 432.5898 | 432.5898 | 432.5898 | 432.5898 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
54 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra | Records and Information Management (RECIM) | Structured Mitigation (RECIM-M013) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 53.2081 | 53.2081 | 53.2081 | 53.2081 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
55 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra | Employee Safety Incident (EMPSI) | Employee Health & Wellness Programs (EMPSI-PRGD) | Ex 7 , Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 259.248 | 259.248 | 259.248 | 259.248 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
56 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 9 | No | On-going | Annual | 0 | 0 | 0 | 816.3513 | 0 | 816.3513 | 0 | 816.3513 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
57 | O&M Expense | Shared Services | KX | Prov Human Resource Svcs | SRM Total | SRM Total | Ex 7 , Ch 1 | No | On-going | Annual | 7608.8595 | 7839.3091 | 15448.1686 | 8375.5879 | 7355.2655 | 15730.8533 | -484.0437 | 282.6847 | -6.175% | 1.83% | NO | NO | Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to provide various safety initiatives that address both employees and contractorsas well as training development and support at the Company level. The initiatives support mitigations for Employees Safety Incident risk primarily in the Healh & Wellness program.
58 | O&M Expense | Shared Services | KX | Prov Human Resource Svcs | Employee Safety Incident (EMPSI) | Employee Health & Wellness Programs (EMPSI-PRGD) | Ex 7 , Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 8375.5879 | 7355.2655 | 15730.8533 | 7355.2655 | 15730.8533 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
59 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs | SRM Total | SRM Total | Ex 7, Ch 9 | No | On-going | Annual | 24715.4045 | 25140.1531 | 49855.5576 | 23453.5349 | 32328.0526 | 55781.5875 | 7187.8994 | 5926.0299 | 28.59% | 11.89% | NO | YES | Program expenditures were above imputed regulatory values primarily due to required increases in physical security initiatives that directly provide support to the Oakland General Office campus and surrounding community. These required investments were unknown at the time of the 2023 GRC and are attributed to efforts within the Physical Security control program (PHYSA-C001). | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. While the purpose of this program is to address the ongoing development and deployment of physical security solutions, the majority of the program will focus spend on mitigation investments to reduce the Physical Attack Cross Cutter Factor risk.
60 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs | Physical Attack (PHYSA) | Physical Security (PHYSA-C001) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 17461.2577 | 23536.6401 | 40997.8978 | 23536.6401 | 40997.8978 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
61 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs | Physical Attack (PHYSA) | Security Asset and Technology (PHYSA-C002) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 1336.2551 | 1626.687 | 2962.9422 | 1626.687 | 2962.9422 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
62 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs | Physical Attack (PHYSA) | Corporate Security Control Center (PHYSA-C003) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 1394.9862 | 1506.4298 | 2901.416 | 1506.4298 | 2901.416 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
63 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs | Physical Attack (PHYSA) | Investigation and Insider Threats (PHYSA-C004) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 1657.224 | 2180.6491 | 3837.873 | 2180.6491 | 3837.873 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
64 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs | Physical Attack (PHYSA) | Prevent (PHYSA-M001) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 1442.2438 | 1030.3272 | 2472.571 | 1030.3272 | 2472.571 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
65 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs | Physical Attack (PHYSA) | Detect (PHYSA-M002) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 161.5681 | 178.2097 | 339.7778 | 178.2097 | 339.7778 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
66 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 9 | No | On-going | Annual | 0 | 0 | 0 | 0 | 2269.1057 | 2269.1057 | 2269.1057 | 2269.1057 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
67 | O&M Expense | Shared Services | OS | Operations Support | SRM Total | SRM Total | Ex 7 , Ch 1 | No | On-going | Annual | 0 | 0 | 0 | 12485.612 | 11740.5301 | 24226.1421 | 11740.5301 | 24226.1421 | 100.0% | 100.0% | YES | YES | Program expenses exceeded imputed regulatory values due to the work being forecast and adopted in MWC FL as a part of the 2023 GRC Final Decision, but executed in MWC OS. The decision to execute the forecast work in a different MWC was made after the 2023 GRC was submitted. This program primarily represents the development and deployment of the Regional Safety Program and is in alignment with the safety commitments made following the Plan of Reorganization. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to provide various safety initiatives that address both employees and contractors. The initiatives support mitigations for Employees Safety Incident, Contractor Safety Incident, and Motor Vehicle Safety Incident risks.
68 | O&M Expense | Shared Services | OS | Operations Support | Employee Safety Incident (EMPSI) | SIF Prevention Program and Field Oversight (PRGC) includes contract partner workforce field safety observations and compliance | Ex 7 , Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 12485.612 | 11740.5301 | 24226.1421 | 11740.5301 | 24226.1421 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
69 | O&M Expense | Shared Services | ZC | Corporate Items | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7 , Ch 5 | No | On-going | Annual | -63713.981 | -64979.6865 | -128693.6676 | -67971.1612 | -64015.84 | -131987.0012 | 963.8466 | -3293.3336 | -1.483% | 2.559% | NO | NO | Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | This MWC is used to forecast and record specific overhead accounting adjustments that direct a percentage of expense support activites performed by various Shared Services and IT functional areas to capital. The overhead accounting adjustment is ongoing and will continue in PG&E's 2023 GRC.
70 | O&M Expense | IT | JV | Maintain IT Apps & Infra | SRM Total | SRM Total | Ex 7, Ch 8 | No | On-going | Annual | 0 | 0 | 0 | 38841.4705 | 26392.4884 | 65233.9589 | 26392.4884 | 65233.9589 | 100.0% | 100.0% | YES | YES | Program expenses exceeded imputed regulatory values due to enterprise design costs for the Propel program which will upgrade, advance and improve PG&E's SAP system and related processes as well as optimizing how the system is used; various technology solutions in support of mitigating Network core assets; and incremental operations and maintenance costs in support of increased public cloud usage. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address the ongoing operations and maintenance of software and hardware technology assets and supporting systems, a modest percentage of the program will focus spend on supporting capital mitigation investments to improve the IT Asset Failure risk.
71 | O&M Expense | IT | JV | Maintain IT Apps & Infra | IT Asset Failure (ITAFL) | Lifecycle Obsolete and Low Health #Assets (ITAFL-M004) | Ex 7, Ch 8 | Yes | On-going | Annual | 0 | 0 | 0 | 2262.5372 | 3452.9822 | 5715.5194 | 3452.9822 | 5715.5194 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
72 | O&M Expense | IT | JV | Maintain IT Apps & Infra | IT Asset Failure (ITAFL) | Multi-Faceted Mitigations (ITAFL-M005) | Ex 7, Ch 8 | Yes | On-going | Annual | 0 | 0 | 0 | 2950.7719 | 1748.4626 | 4699.2345 | 1748.4626 | 4699.2345 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
73 | O&M Expense | IT | JV | Maintain IT Apps & Infra | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 8 | No | On-going | Annual | 0 | 0 | 0 | 33628.1614 | 21191.0436 | 54819.2051 | 21191.0436 | 54819.2051 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
____________________________________________
(a) The following MWCs have both SRM and non-SRM spend: AB, AK, CR, EP, IG, JL, JV, KX, KZ, OS, ZC.

## SharedSvc & IT SRM MWC Capital
TABLE 6-4 2024 RSAR 2023 GRC CYCLE CORPORATE REAL ESTATE CAPITAL COMPARISON BY MAT FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | D | E | F | G1 | G2 | H | I1 | I2 | J | K1 | K2 | L1 | L2 | L3 | L4 | M | N1 | N2 | N3 | O | P
Line No | Type (O&M Expense or Capital) | Functional Area | MWC (a) | MWC Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program / Project Life (years) | Program / Project Year | Imputed Adopted Annual Costs |  | Imputed Cost for 2023 GRC Cycle to Date ($) (G1+G2) | Actual Annual Costs |  | Actual Cost for 2023 GRC Cycle to Date ($) (I1+I2) | Difference for 2024 ($) (I2-G2) | Difference for 2023 GRC Cycle to Date ($) (J-H) | Spending Percent Variance for 2024 (%) ((I2-G2)/G2*100) | Spending Percent Variance for 2023 GRC Cycle (%) (J/H) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | Forecast |  |  | Status | Completion Status Statement
[11 empty] | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs |  | 2023 Actual Costs | 2024 Actual Costs | [8 empty] | Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T)
1 | Capital | Shared Services | 21 | Miscellaneous Capital | SRM Total | SRM Total | Ex 7, Ch 1 | No | On-going | Annual | 0 | 0 | 0 | 0 | 1291.6975 | 1291.6975 | 1291.6975 | 1291.6975 | 100.0% | 100.0% | NO | NO | Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address miscellaneous capital purchases and/or the disposition and sale of PG&E's surplus, damaged, or obsolete assets. In addition, this program represents small investments that are in support of reducing safety and reliability risks for various functional areas.
2 | Capital | Shared Services | 21 | Miscellaneous Capital | Motor Vehicle Safety Incident (MTRSI) | In-Cab Cameras (MRTSI-M21) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 1291.6975 | 1291.6975 | 1291.6975 | 1291.6975 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | Capital | Shared Services | 22 | Maintain Buildings | SRM Total | SRM Total | Ex 7, Ch 5 | No | On-going | Annual | 41008.5721 | 46002.0909 | 87010.6629 | 59406.8998 | 39823.8192 | 99230.719 | -6178.2717 | 12220.0561 | -13.43% | 14.04% | NO | NO | Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to focus on the replacement and optimization of buildings, building components, and associated equipment to increase the reliability of buildings and yards. The majority of these investments are in support of reducing the Real Estate and Facilities Failure risk.
4 | Capital | Shared Services | 22 | Maintain Buildings | Real Estate and Facilities Failure (REFFL) | Regional Optimization (REFFL-C001) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 2730.3461 | 1.1421 | 2731.4883 | 1.1421 | 2731.4883 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | Capital | Shared Services | 22 | Maintain Buildings | Real Estate and Facilities Failure (REFFL) | Facilities Mgmt and Prevent Maint Prgm (REFFL-C004) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 41175.7615 | 20440.0485 | 61615.81 | 20440.0485 | 61615.81 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | Capital | Shared Services | 22 | Maintain Buildings | Real Estate and Facilities Failure (REFFL) | Renovate / Relocate Facilities Other than SFGO (REFFL-M006) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 6258.4091 | 418.9646 | 6677.3738 | 418.9646 | 6677.3738 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 | Capital | Shared Services | 22 | Maintain Buildings | Real Estate and Facilities Failure (REFFL) | Service Center Optimization (REFFL-C002) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 8746.853 | 510.937 | 9257.79 | 510.937 | 9257.79 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 | Capital | Shared Services | 22 | Maintain Buildings | Real Estate and Facilities Failure (REFFL) | Security System Hardening (REFFL-C008) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 2829.5295 | 2829.5295 | 2829.5295 | 2829.5295 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 | Capital | Shared Services | 22 | Maintain Buildings | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 5 | No | On-going | Annual | 0 | 0 | 0 | 495.53 | 15623.1962 | 16118.7262 | 15623.1962 | 16118.7262 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10 | Capital | Shared Services | 23 | Implement RealEstate Strategy | SRM Total | SRM Total | Ex 7, Ch 5 | No | On-going | Annual | 99788.265 | 155877.5885 | 255665.8535 | 68462.1439 | 131413.592 | 199875.7359 | -24463.9965 | -55790.1177 | -15.69% | -21.82% | YES | NO | Program expenditures were below imputed regulatory values due to work forecast and adopted across both MWC 22 and MWC 23 but executed in MWC 22 more than in MWC 23. Other drivers include a credit received in the General Office Sale Memorandum Account (GOSMA) for re-scheduled capital work which was partially offset by ongoing efforts in Service Center Investments, specifically Stockton properties, as well as Regionalization improvements in the Merced Warehouse and Napa Regional center. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to focus on the purchase and acquisition of facilities, associated land, and required infrastructure to operationalize new facilities. In addition, this program develops and deploys the strategy to optimize the real estate portfolio at the company level. The majority of these investments are in support of reducing the Real Estate and Facilities Failure risk.
11 | Capital | Shared Services | 23 | Implement RealEstate Strategy | Real Estate and Facilities Failure (REFFL) | Regional Optimization (REFFL-C001) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 62494.5216 | 22697.0316 | 85191.5532 | 22697.0316 | 85191.5532 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | Capital | Shared Services | 23 | Implement RealEstate Strategy | Real Estate and Facilities Failure (REFFL) | Facilities Mgmt and Prevent Maint Prgm (REFFL-C004) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 2185.2332 | 10759.6198 | 12944.853 | 10759.6198 | 12944.853 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | Capital | Shared Services | 23 | Implement RealEstate Strategy | Real Estate and Facilities Failure (REFFL) | Renovate / Relocate Facilities Other than SFGO (REFFL-M006) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 10174.93 | 47330.5298 | 57505.4597 | 47330.5298 | 57505.4597 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 | Capital | Shared Services | 23 | Implement RealEstate Strategy | Real Estate and Facilities Failure (REFFL) | Service Center Optimization (REFFL-C002) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 17050.0005 | 36591.3673 | 53641.3678 | 36591.3673 | 53641.3678 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | Capital | Shared Services | 23 | Implement RealEstate Strategy | Real Estate and Facilities Failure (REFFL) | Security System Hardening (REFFL-C008) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 6123.0415 | 2912.5757 | 9035.6172 | 2912.5757 | 9035.6172 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
16 | Capital | Shared Services | 23 | Implement RealEstate Strategy | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 5 | No | On-going | Annual | 0 | 0 | 0 | -29565.5829 | 11122.4674 | -18443.1155 | 11122.4674 | -18443.1155 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17 | Capital | Shared Services | 2F | Build IT Apps & Infra | SRM Total | SRM Total | Ex 7, Ch 7 Ex 7, Ch 9 | No | On-going | Annual | 36141.56 | 39770.6194 | 75912.1794 | 36316.206 | 31151.707 | 67467.913 | -8618.9124 | -8444.2664 | -21.67% | -11.12% | NO | NO | Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address the ongoing development and deployment of software and hardware technology solutions. The majority of the program will focus spend on mitigation investments to improve the Cyber Securty Incident risk as well as the cross-cutting Records and Information Management risk.
18 | Capital | Shared Services | 2F | Build IT Apps & Infra | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 1 Ex 7, Ch 2 Ex 7, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 4891.2257 | 5027.912 | 9919.1377 | 5027.912 | 9919.1377 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19 | Capital | Shared Services | 2F | Build IT Apps & Infra | Records and Information Management (RECIM) | Unstructured Mitigations (RECIM-M007) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 6055.7104 | 6055.7104 | 6055.7104 | 6055.7104 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
20 | Capital | Shared Services | 2F | Build IT Apps & Infra | Cyber Security Incident (CYBER) | Identify (CYBER-M001) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 1509.819 | 332.091 | 1841.91 | 332.091 | 1841.91 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | Capital | Shared Services | 2F | Build IT Apps & Infra | Cyber Security Incident (CYBER) | Protect (CYBER-M002) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 24702.81 | 14364.807 | 39067.617 | 14364.807 | 39067.617 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
22 | Capital | Shared Services | 2F | Build IT Apps & Infra | Cyber Security Incident (CYBER) | Detect (CYBER-M003) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 1533.962 | 4605.314 | 6139.276 | 4605.314 | 6139.276 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
23 | Capital | Shared Services | 2F | Build IT Apps & Infra | Cyber Security Incident (CYBER) | Respond (CYBER-M004) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 3678.389 | 765.873 | 4444.262 | 765.873 | 4444.262 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
24 | Capital | Shared Services | 3N | Security Install/Replace | SRM Total | SRM Total | Ex 7, Ch 9 | No | On-going | Annual | 14690.3288 | 15279.8983 | 29970.2271 | 11808.9614 | 21858.888 | 33667.8494 | 6578.9897 | 3697.6222 | 43.06% | 12.34% | NO | NO | Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address the ongoing development and deployment of Corporate Security assets. The majority of the program will focus spend on mitigation investments to improve the Physical Attack risk.
25 | Capital | Shared Services | 3N | Security Install/Replace | Physical Attack (PHYSA) | Prevent (PHYSA-M001) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 8313.636 | 5986.18 | 14299.816 | 5986.18 | 14299.816 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
26 | Capital | Shared Services | 3N | Security Install/Replace | Physical Attack (PHYSA) | Detect (PHYSA-M002) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 3495.3254 | 15872.708 | 19368.0334 | 15872.708 | 19368.0334 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
27 | Capital | IT | 2F | Build IT Apps & Infra | SRM Total | SRM Total | Ex 7, Ch 8 | No | On-going | Annual | 286508.8139 | 298007.3224 | 584516.1363 | 245521.0151 | 361196.3943 | 606717.4094 | 63189.0719 | 22201.2731 | 21.2% | 3.798% | YES | YES | Program expenditures were above imputed regulatory values due to enterprise design costs for the Propel program which will upgrade, advance and improve PG&E's SAP system and related processes. This scope goes beyond a standard technology upgrade and optimzes the way the system is used. Other key drivers of the variance include increased investment in software application upgrades, capital licensing agreements, and data center infrastructure resiliency (ITAFL-M005). | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address the ongoing development and deployment of software and hardware technology solutions, the majority of the program will focus spend on mitigation investments to improve the IT Asset Failure risk.
28 | Capital | IT | 2F | Build IT Apps & Infra | IT Asset Failure (ITAFL) | Lifecycle Obsolete and Low Health #Assets (ITAFL-M004) | Ex 7, Ch 8 | Yes | On-going | Annual | 0 | 0 | 0 | 86042 | 130354.901 | 216396.901 | 130354.901 | 216396.901 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
29 | Capital | IT | 2F | Build IT Apps & Infra | IT Asset Failure (ITAFL) | Multi-Faceted Mitigations (ITAFL-M005) | Ex 7, Ch 8 | Yes | On-going | Annual | 0 | 0 | 0 | 61471 | 74737.767 | 136208.767 | 74737.767 | 136208.767 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
30 | Capital | IT | 2F | Build IT Apps & Infra | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 8 | No | On-going | Annual | 0 | 0 | 0 | 98007.7 | 156103.727 | 254111.427 | 156103.727 | 254111.427 | 100.0% | 100.0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
________________________________
(a) The following MWCs have both SRM and non-SRM spend: 21, 2F, 3N.

## HR SRM Table Expense
TABLE 7-3 2024 RSAR 2023 GRC CYCLE HUMAN RESOURCES EXPENSE COMPARISON BY FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | D | E | F | G1 | G2 | H | I1 | I2 | J | K1 | K2 | L1 | L2 | L3 | L4 | M | N1 | N2 | N3 | O | P
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name (a) | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program / Project Life (years) | Program / Project Year | Imputed Adopted Annual Costs |  | Imputed Cost for 2023 GRC Cycle to Date ($) (G1+G2) | Actual Annual Costs |  | Actual Cost for 2023 GRC Cycle to Date ($) (I1+I2) | Difference for 2024 ($) (I2-G2) | Difference for 2023 GRC Cycle to Date ($) (J-H) | Spending Percent Variance for 2024 (%) ((I2-G2)/G2*100) | Spending Percent Variance for 2023 GRC Cycle (%) (J/H) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | Forecast |  |  | Status | Completion Status Statement
[11 empty] | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs |  | 2023 Actual Costs | 2024 Actual Costs | [8 empty] | Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T)
1 | O&M Expense | Human Resources | N/A | PG&E Academy | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 8, Ch 6 | No | On-going | Annual | 40427.015 | 41244.3433 | 81671.3583 | 32021.052 | 33323.4654 | 65344.5174 | -7920.8779 | -16326.8409 | -19.2% | -19.99% | NO | NO | Below variance threshold. | Target | Target | Target | Proceeding as Planned | This organization's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this organization is to ensure that employees across Pacific Gas and Electric Company are equipped with the knowledge, skills, and certifications necessary to perform their work safely, reliably, and compliantly.
(a) In the 2023 GRC, PG&E Academy is a department within the Human Resources organization and is not a MWC.

## HR SRM Table Capital
TABLE 7-4 2024 RSAR 2023 GRC CYCLE HUMAN RESOURCES CAPITAL COMPARISON BY FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | D | E | F | G1 | G2 | H | I1 | I2 | J | K1 | K2 | L1 | L2 | L3 | L4 | M | N1 | N2 | N3 | O | P
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name (a) | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program/ Project Life (years) | Program/ Project Year | Imputed Adopted Annual Costs |  | Imputed Cost for 2023 GRC Cycle to Date ($) (G1+G2) | Actual Annual Costs |  | Actual Cost for 2023 GRC Cycle to Date ($) (I1+I2) | Difference for 2024 ($) (I2-G2) | Difference for 2023 GRC Cycle to Date ($) (J-H) | Spending Percent Variance for 2024 (%) ((I2-G2)/G2*100) | Spending Percent Variance for 2023 GRC Cycle (%) (J/H) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | Forecast |  |  | Status | Completion Status Statement
[11 empty] | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs |  | 2023 Actual Costs | 2024 Actual Costs | [8 empty] | Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T)
1 | Capital | Human Resources | 5 | PG&E Academy | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 8, Ch 6 | No | On-going | Annual | 30.6219 | 31.8509 | 62.4728 | 21.5596 | 78.9011 | 100.4607 | -9.0624 | 37.9878 | 147.7% | 60.81% | NO | NO | Below variance threshold. | Target | Target | Target | Proceeding as Planned | This organization's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this organization is to ensure that employees across Pacific Gas and Electric Company are equipped with the knowledge, skills, and certifications necessary to perform their work safely, reliably, and compliantly.
2 | Capital | Human Resources | 22 | PG&E Academy | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 8, Ch 6 | No | On-going | Annual | 1071.759 | 1114.7721 | 2186.5311 | 517.508 | 2535.1305 | 3052.6385 | -554.251 | 866.1074 | 127.4% | 39.61% | NO | NO | Below variance threshold. | Target | Target | Target | Proceeding as Planned | This organization's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this organization is to ensure that employees across Pacific Gas and Electric Company are equipped with the knowledge, skills, and certifications necessary to perform their work safely, reliably, and compliantly.