## Q6 Expense Pivot
Row Labels | Sum of 2024 Imputed Adopted Costs | Sum of Imputed Cost for 2023 GRC Cycle to Date ($) (G1+G2) | Sum of 2024 Actual Costs | Sum of Actual Cost for 2023 GRC Cycle to Date ($) (I1+I2) | Sum of Difference for 2024 ($) (I2-G2) | Sum of Difference for 2023 GRC Cycle to Date ($) (J-H) | Sum of Spending Percent Variance for 2024 (%) (K1)/G2*100) | Sum of Spending Percent Variance for 2023 GRC Cycle (%) (K2/H*100)
AB | 260195.5662 | 516605.3064 | 132136.5801 | 240012.0022 | -128058.986 | -276593.3042 | -36.22% | -49.57%
AR | 10773.4238 | 21211.0734 | 9666.4487 | 18855.9309 | -1106.9751 | -2355.1426 | -10.28% | -11.1%
AT | 2210.4564 | 4395.5183 | 0 | 0 | -2210.4564 | -4395.5183 | -100% | -100%
BA | 33048.2032 | 65116.0129 | 26164.4694 | 50547.4718 | -6883.7338 | -14568.5411 | 47.46% | 50.8%
BF | 87278.8708 | 174432.4273 | 129531.3955 | 279572.0527 | 42252.5248 | 105139.6254 | 85.22% | 47.73%
BH | 197204.9399 | 390362.4293 | 137877.1335 | 257355.9017 | -59327.8064 | -133006.5275 | -30.08% | -34.07%
BK | 2019.5532 | 3994.8832 | 2105.1163 | 4106.4083 | 85.563 | 111.525 | 180.9% | 180.9%
DD | 25147.1084 | 49461.7282 | 30027.9291 | 61808.8477 | 4880.8206 | 12347.1195 | 20.3% | 25.96%
EY | 8499.0083 | 16977.8113 | 9684.3638 | 18685.6756 | 1185.3555 | 1707.8643 | 13.95% | 10.06%
FZ | 26585.2516 | 52417.1031 | 25783.8925 | 50059.9391 | -801.359 | -2357.1641 | 183.4% | 198.3%
GA | 43916.7018 | 88064.2337 | 27271.2854 | 77246.0613 | -16645.4165 | -10818.1724 | -309.3% | -107.8%
GC | 55488.6879 | 110243.7702 | 49083.0357 | 99190.9253 | -6405.6522 | -11052.8449 | 783.1% | 843.7%
GE | 19284.6971 | 38556.9277 | 29589.4787 | 54257.8319 | 10304.7816 | 15700.9042 | 53.44% | 40.72%
HG | 23113.8216 | 46321.1301 | 23009.0005 | 41549.4922 | -104.8211 | -4771.638 | 118.9% | 104.1%
HN | 965868.48 | 1937881.4615 | 1002998.7474 | 1862185.8327 | 37130.2674 | -75695.6288 | 3.844% | -3.906%
HX | 3184 | 6302.3175 | 1990.0543 | 4683.8922 | -1193.9457 | -1618.4252 | -37.5% | -25.68%
HY | 710.3007 | 1397.4007 | 289.4958 | 540.0958 | -420.8049 | -857.3049 | -59.24% | -61.35%
IF | 45908.2092 | 91289.009 | 214333.8032 | 252690.6837 | 168425.594 | 161401.6747 | 366.9% | 176.8%
IG | 286066.7288 | 572661.3664 | 398868.7251 | 828881.1692 | 112801.9963 | 256219.8028 | 119.3% | 144.3%
IS | 1819.0996 | 3649.7716 | 672.9663 | 1245.5189 | -1146.1333 | -2404.2527 | -63.01% | -65.87%
IU | 1659.8259 | 3249.6943 | 1274.3272 | 2362.3631 | -385.4988 | -887.3313 | -23.23% | -27.31%
JV | 8471.7026 | 16890.7308 | 4715.7107 | 9145.8708 | -3755.9919 | -7744.86 | -44.34% | -45.85%
KA | 40332.9697 | 80576.1056 | 161232.235 | 250408.1696 | 120899.2653 | 169832.064 | 62779% | 72094%
KB | 20485.0343 | 40809.685 | 19371.6099 | 35442.6813 | -1113.4245 | -5367.0038 | -406.2% | -426.7%
KC | 5284.2483 | 10441.5487 | 7504.3632 | 13657.1315 | 2220.1149 | 3215.5828 | 216% | 13.8%
OM | 20477.3794 | 40427.757 | 20920.0181 | 33673.0081 | 442.6387 | -6754.7488 | 2.162% | -16.71%
WF | 0 | 0 | 97034.1744 | 165521.485 | 97034.1744 | 165521.485 | 600% | 600%
Grand Total | 2195034.2688 | 4383737.2033 | 2563136.36 | 4713686.4425 | 368102.0912 | 329949.2392 | 64455% | 73555%
Cannot add Variance % of each MAT to equal Total MWC. This is NOT a weighted average of the Total MWC.

## Electric MAT Table Expense
Table 3-3 2024 RSAR 2023 GRC CYCLE ELECTRIC DISTRIBUTION EXPENSE COMPARISON BY MAT FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
[13 empty] | 5415787.6642 | 5419675.9727 | 10835463.6369 | 5325814.9224 |  | 11410603.8354 | 665112.9403 | 575140.1985 | [5 empty] | 10499918.23 | 10339003.0824 | 20678008.8224 | 9768818 | 10788934.57 | 20377765.57
| A | B | C1 | C2 | C3 | C4 | C5 | C6 | C7 | D | E | F | G1 | G2 | H | I1 | I2 | J | K1 | K2 | L1 | L2 | L3 | L4 | M | N1 | N2 | O | P1 | P2 | Q | R1 | R2 | S1 | S2 | S3 | T | U | V1 | V2 | V3 | W | X
[13 empty] | Imputed Adopted Costs |  |  | Actual Costs | [9 empty] | Imputed Annual Units |  |  | Actual Annual Units | [9 empty] | Forecast
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name | MAT | MAT Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program / Project Life (years) | Program / Project Year | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs | Imputed Cost for 2023 GRC Cycle to Date ($) (G1+G2) | 2023 Actual Costs | 2024 Actual Costs | Actual Cost for 2023 GRC Cycle to Date ($) (I1+I2) | Difference for 2024 ($) (I2-G2) | Difference for 2023 GRC Cycle to Date ($) (J-H) | Spending Percent Variance for 2024 (%) (K1)/G2*100) | Spending Percent Variance for 2023 GRC Cycle (%) (K2/H*100) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | Unit Type | 2023 Imputed Adopted Units | 2024 Imputed Adopted Units | Imputed Units for 2023 GRC Cycle to Date | 2023 Actual Units | 2024 Actual Units | Actual Units for 2023 GRC Cycle to Date | Difference for 2024 (# of Units) (P2-N2) | Difference for 2023 GRC Cycle to Date (# of Units) (Q-O) | Unit Percent Variance for 2024 (%) (R1/N2*100) | Percent Variance for 2023 GRC Cycle to Date (%) (R2/O) | Unit Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | 2024 Unit Variance Explanation | Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T) | Status | 2024 Completion Status Statement
1 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | SRM Total | SRM Total | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | No | On-going | Annual | 193108.353 | 196495.5021 | 389603.8551 | 31503.0268 | 41146.9351 | 72649.9619 | -155348.567 | -316953.8932 | -79.06% | -81.35% | YES | YES | # of wildfire cameras | 10 | 10 | 20 | 0 | 0 | 0 | -10 | -20 | -100% | -100% | YES | Program expenses were below imputed regulatory values because several programs that were forecast in AB6 are being recorded in new MAT codes under MWC WF, which was created after the 2023 GRC was filed. The following program expenses were forecast in MAT AB6 in the 2023 GRC and are reflected in the imputed regulatory values: Emergency Preparedness and Response (EP&R), Cameras, Public Safety Power Shutoffs (PSPS), the Safety and Infrastructure Protection Team (SIPT), and Wildfire Mitigation Support. Actual expenses for EP&R remain recorded in MAT AB6 with a small portion also recorded to MAT IG#. Actual expenses for Cameras, EPSS, PSPS, SIPT and Weather Station Maintenance are recorded in various MAT codes under MWC WF and are explained further below. The difference between the imputed regulatory value and actual expenses for the EP&R portion remaining in MAT AB6 is below the variance threshold. | Actual units were lower than imputed units because actual units are reported in MAT Code WFC. There were 10 cameras forecasted in AB6 and 25 completed in WFC in 2024. See MAT WFC for an explanation of why PG&E completed more units than forecasted. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The following wildfire mitigation initiatives were forecast in MAT AB6 in the 2023 GRC and are reflected in the imputed regulatory values: EP&R, Cameras, EPSS, PSPS, SIPT, and Wildfire Mitigation Support. EP&R remains under MAT AB6 with a small portion also in MAT IG#. Cameras, EPSS, PSPS, SIPT and Weather Station Maintenance actual costs are reported in various MATs in MWC 3U and are explained in further detail in MWC WF below. The scope and budget is represented as under because for the remainder of the GRC cycle MAT AB6 will show under costs and units because the actuals are captured in MWC WF. Otherwise the programs forecasted in AB6 and remaining as recorded in AB6 are proceeding as planned.
2 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C000: EP&R Controls | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 5397.4967 | 5461.0783 | 10858.5751 | 3670.2988 | 5914.8362 | 9585.135 | 453.7579 | -1273.44 | 8.309% | -11.73% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C001: Situational Awareness and Forecasting Initiatives - SOPP Improvements | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 2206.5298 | 2232.5224 | 4439.0522 | 0 | 0 | 0 | -2232.5224 | -4439.0522 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
4 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C002: Situational Awareness and Forecasting Initiatives - WSOC | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 7808.5788 | 7900.5626 | 15709.1415 | 4644.7696 | 5824.2497 | 10469.0193 | -2076.3129 | -5240.1222 | -26.28% | -33.36% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C004: EP&R Field Operations Technology | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 0.10075 | 0.10075 | 0.10075 | 0.10075 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C005: EP&R Field Operations | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 634.8764 | 642.3551 | 1277.2316 | 610.5359 | 0 | 610.5359 | -642.3551 | -666.6956 | -100% | -52.2% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C006: EP&R Distribution Support Headcount | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 7506.5454 | 7594.9713 | 15101.5167 | 4577.3593 | 0 | 4577.3593 | -7594.9713 | -10524.1574 | -100% | -69.69% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-M000: EP&R Mitigations | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 4416.132 | 4468.1533 | 8884.2852 | 3005.8982 | 4839.4114 | 7845.3096 | 371.2581 | -1038.9756 | 8.309% | -11.69% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M005: Public Safety Power Shutoff - PSPS Event (Distribution) | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 75968.2247 | 77374.8368 | 153343.0615 | 0 | 0 | 0 | -77374.8368 | -153343.0615 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 43987.727 | 44802.1952 | 88789.9222 | 0 | 1074.1592 | 1074.1592 | -43728.036 | -87715.763 | -97.6% | -98.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07B: Situational Awareness and Forecasting Initiatives - Weather Station | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 1836.2456 | 1870.2451 | 3706.4907 | 0 | 0 | 0 | -1870.2451 | -3706.4907 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07D: Situational Awareness and Forecasting Initiatives - Cameras | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 8568.7652 | 8727.4227 | 17296.1879 | 0 | 0 | 0 | -8727.4227 | -17296.1879 | -100% | -100% | N/A | N/A | # of wildfire cameras | 10 | 10 | 20 | 0 | 0 | 0 | -10 | -20 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07E: Situational Awareness and Forecasting Initiatives - Satellite Fire Detection | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 376.812 | 383.789 | 760.601 | 0 | 0 | 0 | -383.789 | -760.601 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07G: Situational Awareness and Forecasting Initiatives - Partial Voltage Detection | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 242.23 | 246.7151 | 488.945 | 0 | 0 | 0 | -246.7151 | -488.945 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07I: Situational Awareness and Forecasting Initiatives - Advanced Fire Modeling | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 6602.7424 | 6724.9974 | 13327.7399 | 0 | 0 | 0 | -6724.9974 | -13327.7399 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
16 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07J: Situational Awareness and Forecasting Initiatives - Meteorology | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 455.329 | 463.7597 | 919.0887 | 0 | 10.8834 | 10.8834 | -452.8763 | -908.2053 | -97.65% | -98.82% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07K: Situational Awareness and Forecasting Initiatives - Fire Potential Index | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 180.8615 | 184.2103 | 365.0718 | 0 | 0 | 0 | -184.2103 | -365.0718 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
18 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M008: Safety and Infrastructure Protection Teams | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 26919.2562 | 27417.6877 | 54336.9439 | 0 | 0 | 0 | -27417.6877 | -54336.9439 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M009: Community Wildfire Safety Program PMO | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 14994.1649 | 18500.3762 | 33494.541 | 18500.3762 | 33494.541 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
20 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M017: System Hardening - Remote Grid | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 18.7605 | 18.7605 | 18.7605 | 18.7605 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 4964.158 | 4964.158 | 4964.158 | 4964.158 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
22 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | SRM Total | SRM Total | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | No | On-going | Annual | 63301.3873 | 63700.064 | 127001.4513 | 76372.3953 | 90989.645 | 167362.0403 | 27289.581 | 40360.589 | 42.84% | 31.78% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values due to a reduction in funding to this program in the 2023 GRC Final Decision. PG&E's forecast for AB# miscellaneous expense for Electric Distribution in the 2023 GRC was reduced in the 2023 GRC Final Decision. PG&E continues to incur costs for the support activities forecasted in the 2023 GRC as well as some new activities, for amounts at and above PG&E's GRC forecast. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. MAT AB# tracks costs for miscellaneous ongoing programs that include several activities that support electric operations including but not limited to Regulatory Compliance and Quality Assurance, the Corrective Actions Program, Data Response Unit, and the Compliance Group. PG&E expects to continue to be over the adopted amount for this program in the 2023 GRC cycle.
23 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Distribution Overhead | DOVHD-M005: Additional Asset Data Capture | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 688.1409 | 682.8827 | 1371.0236 | 0 | 0 | 0 | -682.8827 | -1371.0236 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
24 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Distribution Overhead | DOVHD-M009: Improved Distribution Risk Model | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 802.9983 | 796.9055 | 1599.9037 | 0 | 0 | 0 | -796.9055 | -1599.9037 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
25 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M002: System Hardening | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 689.195 | 689.195 | 689.195 | 689.195 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
26 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 2037.0957 | 2074.8141 | 4111.9099 | 0 | 0 | 0 | -2074.8141 | -4111.9099 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
27 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M009: Community Wildfire Safety Program PMO | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 14007.291 | 14266.6471 | 28273.9381 | 10987.5866 | 5380.278 | 16367.8647 | -8886.3691 | -11906.0734 | -62.29% | -42.11% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
28 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M07F: Situational Awareness and Forecasting Initiatives - Sensor IQ | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 3936.4324 | 4009.3186 | 7945.751 | 6e-05 | 0 | 6e-05 | -4009.3186 | -7945.7509 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
29 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M017: System Hardening - Remote Grid | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 1523.7359 | 1551.9491 | 3075.685 | 2494.8968 | 2867.3509 | 5362.2477 | 1315.4018 | 2286.5627 | 84.76% | 74.34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
30 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M002: System Hardening | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 0 | 0 | 0 | 877.683 | 422.072 | 1299.755 | 422.072 | 1299.755 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
31 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Distribution Overhead | DOVHD-M011: Remote Grid | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 1523.7359 | 1551.9491 | 3075.685 | 0 | 0 | 0 | -1551.9491 | -3075.685 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
32 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | POST-GRC: Post-GRC Mitigation | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 0 | 0 | 0 | 24.9751 | 1.0327 | 26.0079 | 1.0327 | 26.0079 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
33 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 40305.3969 | 40317.1647 | 80622.5616 | 61987.2537 | 81629.7164 | 143616.9701 | 41312.5517 | 62994.4085 | 102.5% | 78.13% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
34 | Expense | Electric Distribution | AR | Read & Investigate Meters | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 10437.6496 | 10773.4238 | 21211.0734 | 9189.4821 | 9666.4487 | 18855.9309 | -1106.9751 | -2355.1426 | -10.28% | -11.1% | NO | NO | Field orders | 854733 | 854733 | 1709466 | 765469 | 705075 | 1470544 | -149658 | -238922 | -17.51% | -13.98% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
35 | Expense | Electric Distribution | AT | Emerging Technology | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 21 | No | On-going | Annual | 2185.0619 | 2210.4564 | 4395.5183 | 0 | 0 | 0 | -2210.4564 | -4395.5183 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to fund Research and Development (R&D) Emerging Technology public partnerships. Actual research and development (R&D) support costs that were adopted in MAT Code AT# in the 2023 GRC were recorded in MAT Code AB#. PG&E incurred approximately two million dollars in 2023 & 2024, recorded in MAT AB#, for emerging technology utility partnerships, which is aligned with the GRC-adopted amounts.
36 | Expense | Electric Distribution | BA | E Dist Operate System | BAF | Genl Operate | SRM Total | SRM Total | Ex 4, Ch 4.6 Ex 4, Ch 7 | No | On-going | Annual | 27814.8879 | 28667.4965 | 56482.3843 | 18147.8013 | 19098.6238 | 37246.425 | -9568.8727 | -19235.9593 | -33.38% | -34.06% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses were below imputed regulatory values due to some work forecast in this MAT code being recorded to routine and major emergency. In addition, weather conditions were favorable in 2024 and weather related costs, like distribution operations to support storms, heat events and EPSS, were lower than forecasted. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program is on-going work and will continue in PG&E's 2023 GRC Period. The purpose of the work is to manage and control the electric distribution systems that directly benefit customers by reducing the frequency and duration of power outages while ensuring a more reliable power supply and regulatory compliance. For the remainder of the GRC cycle Operations including EPSS is on proceeding as planned.
37 | Expense | Electric Distribution | BA | E Dist Operate System | BAF | Genl Operate | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.6 Ex 4, Ch 7 | Yes | N/A | N/A | 1821.9541 | 1856.9878 | 3678.9419 | 791.8355 | 1225.6732 | 2017.5087 | -631.3146 | -1661.4331 | -34% | -45.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
38 | Expense | Electric Distribution | BA | E Dist Operate System | BAF | Genl Operate | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.6 Ex 4, Ch 7 | Yes | N/A | N/A | 25992.9338 | 26810.5087 | 52803.4425 | 17355.9657 | 17872.9506 | 35228.9163 | -8937.5581 | -17574.5261 | -33.34% | -33.28% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
39 | Expense | Electric Distribution | BA | E Dist Operate System | BAH | FLISR Maintenance | SRM Total | SRM Total | Ex 4, Ch 4.6 Ex 4, Ch 7 | No | On-going | Annual | 4252.9219 | 4380.7067 | 8633.6286 | 3784.9457 | 3541.101 | 7326.0467 | -839.6057 | -1307.5819 | -19.17% | -15.15% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
40 | Expense | Electric Distribution | BA | E Dist Operate System | BAH | FLISR Maintenance | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.6 Ex 4, Ch 7 | Yes | N/A | N/A | 489.6046 | 499.019 | 988.6236 | 348.0288 | 323.5671 | 671.5959 | -175.4519 | -317.0277 | -35.16% | -32.07% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
41 | Expense | Electric Distribution | BA | E Dist Operate System | BAH | FLISR Maintenance | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.6 Ex 4, Ch 7 | Yes | N/A | N/A | 3763.3173 | 3881.6877 | 7645.005 | 3436.9169 | 3217.5339 | 6654.4507 | -664.1538 | -990.5543 | -17.11% | -12.96% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | Expense | Electric Distribution | BA | E Dist Operate System | BA# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 4.6 Ex 4, Ch 7 | No | On-going | Annual | 0 | 0 | 0 | 2450.2555 | 3524.7446 | 5975.0001 | 3524.7446 | 5975.0001 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | N/A
43 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF1 | Dist. Aerial Inspections | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 10 | No | On-going | Annual | 0 | 0 | 0 | 7431.7981 | 24648.0359 | 32079.834 | 24648.0359 | 32079.834 | 100% | 100% | YES | YES | # of Equipment Inspections | N/A | N/A | N/A | 64000 | 216926 | 280926 | 216926 | 280926 | 100% | 100% | YES | Program expenses exceeded imputed regulatory values due to this program not being forecasted in the 2023 GRC. PG&E incurred costs in 2024 to conduct aerial inspections in HFTDs, which allows us to detect conditions that are challenging to detect from ground inspections. The addition of aerial inspections to PG&E's distribution inspection portfolio enabled PG&E to address an "Area for Continuous Improvement" from the WMP proceeding, and brings PG&E into consistency with SDG&E and SCE, who also conduct risk-based aerial inspections in HFTD. | Actual units were higher than imputed units because PG&E transitioned to aerial inspections in HFTD instead of ground inspections beginning in 2024. | Over | On-Target | Over | Proceeding as Planned | This program was piloted in 2023 and fully implemented in 2024. This work is ongoing and will continue through PG&E’s 2023 GRC period where it was not forecasted. The purpose of this program is a continuing effort to identify abnormal conditions on PG&E assets through aerial inspection.
44 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF3 | UG BART Cable Test/Insp | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 58.9724 | 59.0572 | 118.0296 | 0 | 39.58 | 39.58 | -19.4772 | -78.4496 | -32.98% | -66.47% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
45 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF3 | UG BART Cable Test/Insp | Underground | DUNGD-C001: Patrols | Ex 4, Ch 10 | No | N/A | N/A | 58.9724 | 59.0572 | 118.0296 | 32.5747 | 39.58 | 72.1547 | -19.4772 | -45.8749 | -32.98% | -38.87% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
46 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF4 | UG Auto Xfer Swch Test/Insp | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 145.2468 | 145.4557 | 290.7025 | 68.9669 | 134.042 | 203.0089 | -11.4136 | -87.6936 | -7.847% | -30.17% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
47 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF4 | UG Auto Xfer Swch Test/Insp | Underground | DUNGD-C001: Patrols | Ex 4, Ch 10 | No | N/A | N/A | 145.2468 | 145.4557 | 290.7025 | 68.9669 | 134.042 | 203.0089 | -11.4136 | -87.6936 | -7.847% | -30.17% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
48 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFA | OH Patrol | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 5056.3369 | 5063.6072 | 10119.9441 | 7613.2939 | 10773.5725 | 18386.8664 | 5709.9653 | 8266.9223 | 112.8% | 81.69% | NO | YES | # of Equipment Inspections | 1366233.24 | 1366233.2433 | 2732466.4833 | 1344289 | 1934507 | 3278796 | 568273.7567 | 546329.5167 | 41.59% | 19.99% | YES | Program expenses exceeded imputed regulatory values because more units were patrolled than originally forecasted. Every pole that doesn't get a detailed inspection received a patrol, including non-HFTD rural maps that are being patrolled annually which exceeds the GO165 requirements | Actual units were higher than imputed units because more units were patrolled than originally forecasted. Every pole that doesn't get a detailed inspection received a patrol, including non-HFTD rural maps that are being patrolled annually which exceeds the GO165 requirements and was not forecast in the 2023 GRC. | Over | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue through PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to identify abnormal conditions on PG&E assets through patrols
49 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFA | OH Patrol | Distribution Overhead | DOVHD-C013: Patrols - Distribution Overhead | Ex 4, Ch 10 | No | N/A | N/A | 5056.3369 | 5063.6072 | 10119.9441 | 7613.2939 | 10773.5725 | 18386.8664 | 5709.9653 | 8266.9223 | 112.8% | 81.69% | N/A | N/A | # poles patrolled | 1366233.24 | 1366233.2433 | 2732466.4833 | 1344289 | 1934507 | 3278796 | 568273.7567 | 546329.5167 | 41.59% | 19.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
50 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFA | OH Patrol | Wildfire | WLDFR-C001: Patrols - Distribution Overhead | Ex 4, Ch 10 | No | N/A | N/A | 5056.3369 | 5063.6072 | 10119.9441 | 7613.2939 | 10773.5725 | 18386.8664 | 5709.9653 | 8266.9223 | 112.8% | 81.69% | N/A | N/A | # poles patrolled | 1366233.24 | 1366233.2433 | 2732466.4833 | 1344289 | 1934507 | 3278796 | 568273.7567 | 546329.5167 | 41.59% | 19.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
51 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFB | OH Insp | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 53673.6169 | 53750.7918 | 107424.4087 | 65428.3223 | 26451.5516 | 91879.8739 | -27299.2402 | -15544.5348 | -50.79% | -14.47% | YES | YES | # of Poles Inspected | 508807.48 | 508806.59 | 1017614.07 | 550762 | 331105 | 881867 | -177701.59 | -135747.07 | -34.93% | -13.34% | YES | Program expenses were below imputed regulatory values because PG&E completed less units than originally planned as PG&E transitioned to conduct aerial inspections in HFTDs instead of ground inspections. | Actual units were lower than imputed units because PG&E transitioned to aerial inspections in HFTD instead of ground inspections. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to identify abnormal conditions on PG&E assets through detailed inspections.
52 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFB | OH Insp | Distribution Overhead | DOVHD-C005: Inspections - Distribution Overhead | Ex 4, Ch 10 | No | N/A | N/A | 53673.6169 | 53750.7918 | 107424.4087 | 65428.3223 | 26451.5516 | 91879.8739 | -27299.2402 | -15544.5348 | -50.79% | -14.47% | N/A | N/A | # poles inspected | 508807.48 | 508806.59 | 1017614.07 | 550762 | 331105 | 881867 | -177701.59 | -135747.07 | -34.93% | -13.34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
53 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFB | OH Insp | Wildfire | WLDFR-C01A: Inspections - Distribution Overhead | Ex 4, Ch 10 | No | N/A | N/A | 53673.6169 | 53750.7918 | 107424.4087 | 65428.3223 | 26451.5516 | 91879.8739 | -27299.2402 | -15544.5348 | -50.79% | -14.47% | N/A | N/A | # poles inspected | 508807.48 | 508806.59 | 1017614.07 | 550762 | 331105 | 881867 | -177701.59 | -135747.07 | -34.93% | -13.34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
54 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFC | OH Insp Infrared | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 2833.9513 | 2838.0261 | 5671.9773 | 20.9235 | 1500.9111 | 1521.8347 | -1337.1149 | -4150.1427 | -47.11% | -73.17% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
55 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFC | OH Insp Infrared | Distribution Overhead | DOVHD-C006: Infrared Inspections -Distribution Overhead | Ex 4, Ch 10 | No | N/A | N/A | 2833.9513 | 2838.0261 | 5671.9773 | 20.9235 | 1500.9111 | 1521.8347 | -1337.1149 | -4150.1427 | -47.11% | -73.17% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
56 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFC | OH Insp Infrared | Wildfire | WLDFR-C01B: Infrared Inspections - Distribution Overhead | Ex 4, Ch 10 | No | N/A | N/A | 2833.9513 | 2838.0261 | 5671.9773 | 20.9235 | 1500.9111 | 1521.8347 | -1337.1149 | -4150.1427 | -47.11% | -73.17% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
57 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFD | UG Patrol | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 2681.0599 | 2684.9148 | 5365.9747 | 3142.43 | 2974.7458 | 6117.1758 | 289.831 | 751.2011 | 10.79% | 14% | NO | NO | # of Enclosures Patrolled | 270158 | 270158.0008 | 540316.0008 | 268305 | 279676 | 547981 | 9517.9992 | 7664.9992 | 3.523% | 1.419% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
58 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFD | UG Patrol | Underground | DUNGD-C001: Patrols | Ex 4, Ch 10 | No | N/A | N/A | 2681.0599 | 2684.9148 | 5365.9747 | 3142.43 | 2974.7458 | 6117.1758 | 289.831 | 751.2011 | 10.79% | 14% | N/A | N/A | # enclosures patrolled | 270158 | 270158.0008 | 540316.0008 | 268305 | 279676 | 547981 | 9517.9992 | 7664.9992 | 3.523% | 1.419% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
59 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFE | UG Insp Infrared | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 14545.4322 | 14566.3465 | 29111.7787 | 16029.1789 | 14941.0189 | 30970.1978 | 374.6724 | 1858.4191 | 2.572% | 6.384% | NO | NO | # of Enclosures Inspected | 134979 | 134978.9999 | 269957.9999 | 148998 | 155381 | 304379 | 20402.0001 | 34421.0001 | 15.11% | 12.75% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned
60 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFE | UG Insp Infrared | Underground | DUNGD-C001: Patrols | Ex 4, Ch 10 | No | N/A | N/A | 14545.4322 | 14566.3465 | 29111.7787 | 16029.1789 | 14941.0189 | 30970.1978 | 374.6724 | 1858.4191 | 2.572% | 6.384% | N/A | N/A | # enclosures inspected | 134979 | 134978.9999 | 269957.9999 | 148998 | 155381 | 304379 | 20402.0001 | 34421.0001 | 15.11% | 12.75% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
61 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFF | UG Manhole Insp Annual | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 10 | No | On-going | Annual | 506.7258 | 507.4544 | 1014.1801 | 0 | 160.2093 | 160.2093 | -347.2451 | -853.9708 | -68.43% | -84.2% | NO | NO | # of Manholes/Vaults Inspected | 1546 | 1546 | 3092 | 0 | 474 | 474 | -1072 | -2618 | -69.34% | -84.67% | YES | Below variance threshold. | Actual units were lower than imputed units due to funding for annual manhole inspections being re-prioritized to other high priority work in MWC BF, including aerial inspections in MAT BF1. A limited number of manhole inspections were completed in 2024 based on locations of high public safety consequence, typically located in densely populated areas. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to inspect manholes. Note that manholes are also inspected as part of GO 165 underground inspections program.
62 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFG | OH Equip Test | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 10 | No | On-going | Annual | 2653.7578 | 2657.5735 | 5311.3313 | 3717.2796 | 3553.9803 | 7271.2599 | 896.4067 | 1959.9286 | 33.73% | 36.9% | NO | NO | # of Equip Inspections | 25576.24 | 25576.24 | 51152.48 | 24130 | 21099 | 45229 | -4477.24 | -5923.48 | -17.51% | -11.58% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned
63 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFH | Inspection Projects | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 4832.4602 | 4839.4086 | 9671.8688 | 6469.977 | 2699.2956 | 9169.2726 | -2140.113 | -502.5962 | -44.22% | -5.196% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
64 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFH | Inspection Projects | Wildfire | WLDFR-C01E: Inspections | Ex 4, Ch 10 | Yes | N/A | N/A | 4832.4602 | 4839.4086 | 9671.8688 | 6469.977 | 2699.3 | 9169.2771 | -2140.1086 | -502.5918 | -44.22% | -5.196% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
65 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFJ | OH Patrol ORT Post Outage | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 165.9964 | 166.2351 | 332.2314 | 146.3 | 127.5662 | 273.8662 | -38.6688 | -58.3652 | -23.26% | -17.57% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
66 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFJ | OH Patrol ORT Post Outage | Distribution Overhead | DOVHD-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 10 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 47.9 | 47.9 | 47.9 | 47.9 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
67 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFJ | OH Patrol ORT Post Outage | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 10 | Yes | N/A | N/A | 0 | 0 | 0 | 51.4 | 47.9 | 99.3 | 47.9 | 99.3 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
68 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFJ | OH Patrol ORT Post Outage | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 10 | Yes | N/A | N/A | 165.9964 | 166.2351 | 332.2314 | 94.8353 | 79.6022 | 174.4375 | -86.6328 | -157.7939 | -52.11% | -47.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
69 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 10 | No | On-going | Annual | 0 | 0 | 0 | 39972.1868 | 41526.8863 | 81499.0731 | 41526.8863 | 81499.0731 | 100% | 100% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values due to the program not being forecasted in the 2023 GRC. These increased expenses are associated with headcount for the System Inspections Quality Control (QC) team, formed to perform system inspection QC audits and achieve the associated quality pass rate for HFTD areas. | N/A | Over | Over | Over | Emergent | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is System Inspection QC, which was not forecasted in the 2023 GRC. PG&E anticipates that System Inspection QC costs will continue to be incurred in this MAT for the remainder of the GRC cycle.
70 | Expense | Electric Distribution | BH | E Dist Routine Emergency | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 4.6 Ex 4, Ch 6 | No | On-going | Annual | 193157.4894 | 197204.9399 | 390362.4293 | 119478.7682 | 137877.1335 | 257355.9017 | -59327.8064 | -133006.5275 | -30.08% | -34.07% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses were below imputed regulatory values due to favorable weather conditions in 2024. Costs for EPSS have variability according to the weather; certain costs like Patrols and Post-Patrol investigation (includes helicopter) will increase or decrease related to weather events that require EPSS mitigation. In addition, when this program was forecasted in the 2023 GRC it was a new program and outages were expected to increase with the full implementation of EPSS. The level of outages, and therefore associated patrols was not realized as forecasted. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to patrol, including the use of helicopters, following an outage event and to restore customers to service as soon as possible. Program spend over the course of the remainder of the GRC cycle is expected to be under what was forecasted for EPSS. The routine emergency portion of this work is emergent depending on weather and the number of events. Overall the EPSS and routine emergency programs are proceeding as planned though the spend is likely to be under for the GRC cycle as explained in the cost variance explanation.
71 | Expense | Electric Distribution | BH | E Dist Routine Emergency | N/A | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.6 Ex 4, Ch 6 | Yes | N/A | N/A | 117183.7596 | 119437.0415 | 236620.8011 | 10276.8746 | 10771.359 | 21048.2336 | -108665.6825 | -215572.5675 | -90.98% | -91.1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
72 | Expense | Electric Distribution | BH | E Dist Routine Emergency | N/A | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.6 Ex 4, Ch 6 | Yes | N/A | N/A | 75973.7298 | 77767.8984 | 153741.6282 | 109201.8936 | 127105.7746 | 236307.6681 | 49337.8762 | 82566.04 | 63.44% | 53.7% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
73 | Expense | Electric Distribution | BK | Maint Other Equip | BKA | Transformer Repr Emeryville | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 1975.33 | 2019.5532 | 3994.8832 | 1597.5867 | 1633.4152 | 3231.0019 | -386.1381 | -763.8813 | -19.12% | -19.12% | NO | NO | Equipment overhauls | 1023 | 1023 | 2046 | 1603 | 1506 | 3109 | 483 | 1063 | 47.21% | 51.96% | YES | Below variance threshold. | Actual units were higher than imputed units due to operational need. This is a demand-driven program for transformer repair/refurbishment supporting maintenance, new construction, emergency response, and other programs. Demand for this program is determined by logistical planners, but is dependent on the availability of transformers from the manufacturer or refurbished/repaired transformer inventory. If transformer supplies are unavailable from the manufacturer, PG&E considers repairing/refurbishing to meet the demand. In 2024 the need for transformer repair/refurbishment was higher than forecast in the 2023 GRC. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to repair and refurbish transformers to meet demand.
74 | Expense | Electric Distribution | BK | Maint Other Equip | BKJ | Equip Overhaul Emeryville | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 0 | 0 | 0 | 104.1453 | 234.3877 | 338.533 | 234.3877 | 338.533 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | N/A
75 | Expense | Electric Distribution | BK | Maint Other Equip | BKK | Equip Warranty Repr Emeryville | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 0 | 0 | 0 | 299.56 | 237.3134 | 536.8733 | 237.3134 | 536.8733 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | N/A
76 | Expense | Electric Distribution | DD | Provide Field Service | DDC | Electric Start/Stop | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 482.2666 | 498.3348 | 980.6014 | 245.6925 | 279.178 | 524.8704 | -219.1568 | -455.731 | -43.98% | -46.47% | NO | NO | Field orders | 3603.81 | 3603.8094 | 7207.6194 | 1710 | 1731 | 3441 | -1872.8094 | -3766.6194 | -51.97% | -52.26% | YES | Below variance threshold. | Actual units were lower than imputed units due to fewer customer-generated start/stop requests than forecast. | Under | On-Target | On-Target | Proceeding as Planned | This program is on-going work and will continue in PG&E's 2023 GRC Period. The work supports customer-generated start/stop requests while ensuring safe delivery of electric service.
77 | Expense | Electric Distribution | DD | Provide Field Service | DDH | Electric Trouble Cust Equipt | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 7 | No | On-going | Annual | 6092.1497 | 6300.8473 | 12392.997 | 7159.0458 | 7444.1703 | 14603.2161 | 1143.323 | 2210.2191 | 18.15% | 17.83% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program is on-going work and will continue in PG&E's 2023 GRC Period. The work supports timely response to trouble on customer-owned equipment and maintains safety and reliability of the electric grid. PG&E changed from unitized to non-unitized in the 2023 GRC due to inconsistency in the unit cost per outage event.
78 | Expense | Electric Distribution | DD | Provide Field Service | DDJ | Electric - Other | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 7 | No | On-going | Annual | 11131.8549 | 11513.1968 | 22645.0517 | 17159.1279 | 13491.2097 | 30650.3376 | 1978.0129 | 8005.286 | 17.18% | 35.35% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program is on-going and will continue in PG&E's 2023 GRC Period. The work is driven by customer-initiated electrical service connections, particularly connects/reconnects like solar PV installations, Electric Main Panel Upgrades, and electric vehicle connections. PG&E changed from unitized to non-unitized in the 2023 GRC due to inconsistency in the unit cost per outage event.
79 | Expense | Electric Distribution | DD | Provide Field Service | DD# | Not assigned | SRM Total | SRM Total | Ex 4, Ch 7 | No | On-going | Annual | 6608.3486 | 6834.7296 | 13443.0781 | 7217.0524 | 8813.3711 | 16030.4235 | 1978.6416 | 2587.3454 | 28.95% | 19.25% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
80 | Expense | Electric Distribution | DD | Provide Field Service | DD# | Not assigned | Distribution Overhead | DOVHD-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 7 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 148.3995 | 148.3995 | 148.3995 | 148.3995 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
81 | Expense | Electric Distribution | DD | Provide Field Service | DD# | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 7 | Yes | N/A | N/A | 0 | 0 | 0 | 258.3307 | 148.3995 | 406.7302 | 148.3995 | 406.7302 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
82 | Expense | Electric Distribution | DD | Provide Field Service | DD# | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 7 | Yes | N/A | N/A | 6608.3486 | 6834.7296 | 13443.0781 | 6958.7217 | 8664.9716 | 15623.6933 | 1830.242 | 2180.6152 | 26.78% | 16.22% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
83 | Expense | Electric Distribution | EY | Change/Maint Used Elec Meter | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 8478.8029 | 8499.0083 | 16977.8113 | 9001.3117 | 9684.3638 | 18685.6756 | 1185.3555 | 1707.8643 | 13.95% | 10.06% | NO | NO | Field orders | 36757.8 | 36757.8009 | 73515.6009 | 35924 | 38531 | 74455 | 1773.1991 | 939.3991 | 4.824% | 1.278% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
84 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZA | Genl Engineer | SRM Total | SRM Total | Ex 4, Ch 17 | No | On-going | Annual | 22543.5406 | 23198.0713 | 45741.6119 | 17070.6936 | 18939.0259 | 36009.7195 | -4259.0454 | -9731.8924 | -18.36% | -21.28% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
85 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZA | Genl Engineer | Distribution Overhead | DOVHD-C008: Annual Protection Reviews | Ex 4, Ch 17 | Yes | N/A | N/A | 16913.6291 | 17422.1695 | 34335.7985 | 12145.3497 | 13551.7821 | 25697.1318 | -3870.3874 | -8638.6668 | -22.22% | -25.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
86 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZA | Genl Engineer | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.6 | Yes | N/A | N/A | 2111.442 | 2166.1942 | 4277.6362 | 2226.5793 | 2846.6561 | 5073.2354 | 680.4619 | 795.5991 | 31.41% | 18.6% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
87 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZA | Genl Engineer | Wildfire | WLDFR-M07A: Situational Awareness and Forecasting Initiatives - Line Sensors | Ex 4, Ch 4.3 | Yes | N/A | N/A | 3518.4132 | 3609.6498 | 7128.063 | 2698.7647 | 2540.5877 | 5239.3524 | -1069.0621 | -1888.7107 | -29.62% | -26.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
88 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZB | Voltage Complaints Invest | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 653.4074 | 673.0534 | 1326.4608 | 1761.7722 | 1652.2503 | 3414.0224 | 979.1969 | 2087.5616 | 145.5% | 157.4% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
89 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZC | Transformer Reports Manage | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 237.0501 | 244.1775 | 481.2277 | 0 | 0 | 0 | -244.1775 | -481.2277 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
90 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZD | Field Work Plan | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 859.0535 | 884.8826 | 1743.9361 | 283.2546 | 573.4817 | 856.7363 | -311.4009 | -887.1998 | -35.19% | -50.87% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
91 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZE | Troublemen Field Work | SRM Total | SRM Total | Ex 4, Ch 17 | No | On-going | Annual | 1538.7999 | 1585.0668 | 3123.8667 | 5160.3261 | 4619.1347 | 9779.4609 | 3034.0679 | 6655.5942 | 191.4% | 213.1% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
92 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZE | Troublemen Field Work | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 2617.5919 | 2291.5817 | 4909.1736 | 2291.5817 | 4909.1736 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
93 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZE | Troublemen Field Work | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 17 | Yes | N/A | N/A | 1538.7999 | 1585.0668 | 3123.8667 | 2542.7342 | 2327.553 | 4870.2872 | 742.4862 | 1746.4206 | 46.84% | 55.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
94 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAA | Pole Test & Treat | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 21669.7722 | 21556.4696 | 43226.2418 | 34048.7679 | 13491.0593 | 47539.8271 | -8065.4103 | 4313.5853 | -37.42% | 9.979% | NO | YES | # Poles Tested & Treated | 259832.68 | 259832.6754 | 519665.3554 | 117091 | 62845 | 179936 | -196987.6754 | -339729.3554 | -75.81% | -65.37% | YES | Program expenses were below imputed regulatory values due to fewer units being completed. | Actual units were lower than imputed units due to PG&E temporarily shifting to a 20-year inspection cycle from a 10-year inspection cycle. | Under | Under | Over | Rescheduled | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to inspect and treat wood poles intrusively, to ensure the poles are in good condition and prevent premature failure in accordance with GO165. During the 2023 GRC cycle PG&E expects to continue to perform units to meet 20-year inspection cycle.
95 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAA | Pole Test & Treat | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | No | N/A | N/A | 21669.7722 | 21556.4696 | 43226.2418 | 34048.7679 | 13491.0593 | 47539.8271 | -8065.4103 | 4313.5853 | -37.42% | 9.979% | N/A | N/A | # inspections | 259832.68 | 259832.6754 | 519665.3554 | 117091 | 62845 | 179936 | -196987.6754 | -339729.3554 | -75.81% | -65.37% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
96 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAA | Pole Test & Treat | Wildfire | WLDFR-C12A: Wood Pole Inspection Program | Ex 4, Ch 12 | No | N/A | N/A | 21669.7722 | 21556.4696 | 43226.2418 | 34048.7679 | 13491.0593 | 47539.8271 | -8065.4103 | 4313.5853 | -37.42% | 9.979% | N/A | N/A | # inspections | 259832.68 | 259832.6754 | 519665.3554 | 117091 | 62845 | 179936 | -196987.6754 | -339729.3554 | -75.81% | -65.37% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
97 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAB | Pole Joint Util Maint Reimb | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | 0 | 0 | 0 | 177.4772 | 551.1657 | 728.6429 | 551.1657 | 728.6429 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. Joint Utilities Maintenance Reimbursements are not forecast in the GRC and therefore will continue to appear over budget.
98 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAC | Pole Analyze Loading | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 22710.056 | 22591.3141 | 45301.37 | 13502.0972 | 12431.0901 | 25933.1873 | -10160.224 | -19368.1827 | -44.97% | -42.75% | YES | YES | Poles Analyzed | 200000 | 200000 | 400000 | 162050 | 32008 | 194058 | -167992 | -205942 | -84% | -51.49% | YES | Program expenses were below imputed values due to the completion of a lower unit volume than forecasted at a higher unit cost. In 2024, the work focused on completing units in HFTD, which required more detailed engineering calculations for which desktop review was indeterminate. PG&E delayed transition of desktop reviews to non-HFTD poles in efforts to complete the outstanding HFTD poles. | Actual units were lower than imputed units due to work focused on completing units in HFTD, which required more detailed engineering calculations for which desktop review was indeterminate. PG&E delayed transition of desktop reviews to non-HFTD poles in efforts to complete the outstanding HFTD poles. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to review and analyze pole loading in order to prevent overloaded poles and premature pole failure. This program has concentrated on poles in Tier 2 and 3 HFTDs, through the performance of a desktop pole review calculation. PG&E has completed the desktop review pole loading analysis for all poles in the Tier 2 and 3 HFTDs. However, PG&E is now performing more detailed engineering calculations for all poles in the Tier 2 and 3 HFTDs for which the desktop review indicated a data anomaly (e.g., change of conductor type) or that could not be sufficiently analyzed because of obstructions to LiDAR data capture (e.g., dense vegetation). PG&E will transition to analysis of non-HFTD poles after completion of the HFTD poles.
99 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAC | Pole Analyze Loading | Wildfire | WLDFR-C12B: Pole Analyze Loading | Ex 4, Ch 12 | No | N/A | N/A | 22710.056 | 22591.3141 | 45301.37 | 13502.0972 | 12431.0901 | 25933.1873 | -10160.224 | -19368.1827 | -44.97% | -42.75% | N/A | N/A | # poles analyzed | 200000 | 200000 | 400000 | 162050 | 32008 | 194058 | -167992 | -205942 | -84% | -51.49% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
100 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAD | Pole Reinforce | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 4403.5311 | 4380.5068 | 8784.0379 | 7609.0663 | -1777.6728 | 5831.3935 | -6158.1796 | -2952.6445 | -140.6% | -33.61% | NO | YES | Poles Reinforced | 4500 | 4500 | 9000 | 3982 | 0 | 3982 | -4500 | -5018 | -100% | -55.76% | YES | Program expenses were below imputed adopted values due to recorded costs being transferred from MAT Code GAD to MAT Code 07R. MAT code 07R was created after 2023 GRC filing when costs for pole reinforcements were capitalized, beginning in 2024. | Actual units were lower than imputed units because costs and units were recorded to MAT 07R. See costs variance explanation for this program. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period, but under MAT 07R. The purpose of this program is a continuing effort to make safe degraded poles that would otherwise require replacement.
101 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAD | Pole Reinforce | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | No | N/A | N/A | 4403.5311 | 4380.5068 | 8784.0379 | 7609.0663 | -1777.6728 | 5831.3935 | -6158.1796 | -2952.6445 | -140.6% | -33.61% | N/A | N/A | # reinforcements | 4500 | 4500 | 9000 | 3982 | 0 | 3982 | -4500 | -5018 | -100% | -55.76% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
102 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAD | Pole Reinforce | Wildfire | WLDFR-C12E: Pole Restoration Program | Ex 4, Ch 12 | No | N/A | N/A | 4403.5311 | 4380.5068 | 8784.0379 | 7609.0663 | -1777.6728 | 5831.3935 | -6158.1796 | -2952.6445 | -140.6% | -33.61% | N/A | N/A | # reinforcements | 4500 | 4500 | 9000 | 3982 | 0 | 3982 | -4500 | -5018 | -100% | -55.76% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
103 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAF | Telco Engr Revw Non-Reimbursed | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 176.1861 | 175.2649 | 351.4511 | 0 | 0 | 0 | -175.2649 | -351.4511 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
104 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAF | Telco Engr Revw Non-Reimbursed | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | No | N/A | N/A | 176.1861 | 175.2649 | 351.4511 | 0 | 0 | 0 | -175.2649 | -351.4511 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
105 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAH | Pole Joint Util Maint Non-Reim | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 475.8148 | 473.3269 | 949.1417 | 444.3824 | 706.2257 | 1150.6081 | 232.8987 | 201.4664 | 49.2% | 21.23% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
106 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAH | Pole Joint Util Maint Non-Reim | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | No | N/A | N/A | 475.8148 | 473.3269 | 949.1417 | 444.3824 | 706.2257 | 1150.6081 | 232.8987 | 201.4664 | 49.2% | 21.23% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
107 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GA# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | -5287.8284 | -5260.1804 | -10548.0089 | -5807.0151 | 1869.4175 | -3937.5975 | 7129.598 | 6610.4113 | -135.5% | -62.67% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For the 2023 GRC forecast, MAT GA# was used to track joint pole credits and pole management personnel costs for the intrusive inspection and pole restoration programs and therefore the imputed amount is negative. In 2024, GA# was only used to track the costs associated with management of pole test and treat, pole reinforcement, and comprehensive inspection programs. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The revised purpose of this program is to track pole management personnel costs.
108 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC1 | El DSub-Engrg_Maint Support | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 5700.5611 | 5776.4015 | 11476.9626 | 4630.9512 | 4148.5711 | 8779.5223 | -1627.8305 | -2697.4403 | -28.18% | -23.5% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
109 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC1 | El DSub-Engrg_Maint Support | Substation | SBSTN-C008: Design Criteria | Ex 4, Ch 15 | Yes | N/A | N/A | 544.2725 | 551.5135 | 1095.786 | 2289.1948 | 2492.7396 | 4781.9344 | 1941.2261 | 3686.1485 | 352% | 336.4% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
110 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC1 | El DSub-Engrg_Maint Support | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 4024.3681 | 4077.9084 | 8102.2765 | 2341.7564 | 1655.8315 | 3997.5878 | -2422.077 | -4104.6887 | -59.4% | -50.66% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
111 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC1 | El DSub-Engrg_Maint Support | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 15 | Yes | N/A | N/A | 1131.9034 | 1146.9623 | 2278.8657 | 0 | 0 | 0 | -1146.9623 | -2278.8657 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
112 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC2 | El DSub-Major Emerg_Corr Maint | SRM Total | SRM Total | Ex 4, Ch 15 Ex 4, Ch 4.6 | No | On-going | Annual | 15750.297 | 15964.9815 | 31715.2784 | 4651.2106 | 5092.7712 | 9743.9818 | -10872.2103 | -21971.2966 | -68.1% | -69.28% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses were below imputed regulatory values due to reprioritizing and funding overruns in our preventative substation programs. | N/A | Under | Under | Under | Rescheduled | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is substation corrective work. PG&E anticipates completing this work as the need arises within the overall priority of the substation portfolio of work over the remainder of the course of the GRC cycle.
113 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC2 | El DSub-Major Emerg_Corr Maint | Distribution Overhead | DOVHD-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 15 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 54.6225 | 54.6225 | 54.6225 | 54.6225 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
114 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC2 | El DSub-Major Emerg_Corr Maint | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 15 Ex 4, Ch 4.6 | Yes | N/A | N/A | 867.9081 | 884.5968 | 1752.5048 | 210.8075 | 54.6225 | 265.4299 | -829.9743 | -1487.0749 | -93.83% | -84.85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
115 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC2 | El DSub-Major Emerg_Corr Maint | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 15 Ex 4, Ch 4.6 | Yes | N/A | N/A | 14882.3889 | 15080.3847 | 29962.7736 | 4440.4032 | 5038.1487 | 9478.5519 | -10042.236 | -20484.2217 | -66.59% | -68.37% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
116 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC5 | Dist Sub enhanced inspections | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 15 | No | On-going | Annual | 0 | 0 | 0 | 1083.5342 | 1000.4815 | 2084.0157 | 1000.4815 | 2084.0157 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | N/A
117 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCA | Dsbn: TXfmr - prev maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 1146.6707 | 1161.926 | 2308.5967 | 1519.1547 | 1485.4577 | 3004.6124 | 323.5316 | 696.0157 | 27.84% | 30.15% | NO | NO | Transformers Maintained | 4574.24 | 4574.2385 | 9148.4785 | 5373 | 4940 | 10313 | 365.7615 | 1164.5215 | 7.996% | 12.73% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
118 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCA | Dsbn: TXfmr - prev maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 1146.6707 | 1161.926 | 2308.5967 | 1519.1547 | 1485.4577 | 3004.6124 | 323.5316 | 696.0157 | 27.84% | 30.15% | N/A | N/A | # of Transformers Maintained | 4574.24 | 4574.2385 | 9148.4785 | 5373 | 4940 | 10313 | 365.7615 | 1164.5215 | 7.996% | 12.73% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
119 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCB | Dsbn: Breaker - prevent maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 833.5576 | 844.6473 | 1678.205 | 962.1027 | 1050.2965 | 2012.3993 | 205.6492 | 334.1943 | 24.35% | 19.91% | NO | NO | Breakers Maintained | 1881.95 | 1881.9471 | 3763.8971 | 1167 | 1232 | 2399 | -649.9471 | -1364.8971 | -34.54% | -36.26% | YES | Below variance threshold. | Actual units were lower than imputed units due to higher actual unit costs than forecast. Higher unit costs are generally driven by labor, and resulted in fewer program units achieved. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
120 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCB | Dsbn: Breaker - prevent maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 833.5576 | 844.6473 | 1678.205 | 962.1027 | 1050.2965 | 2012.3993 | 205.6492 | 334.1943 | 24.35% | 19.91% | N/A | N/A | # of Breakers Maintained | 1881.95 | 1881.9471 | 3763.8971 | 1167 | 1232 | 2399 | -649.9471 | -1364.8971 | -34.54% | -36.26% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
121 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCC | Dist Sub: Substation Test Dpt | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 1599.4152 | 1620.6938 | 3220.109 | 3607.2022 | 3910.7222 | 7517.9243 | 2290.0283 | 4297.8153 | 141.3% | 133.5% | NO | NO | Relays Maintained | 1422.95 | 1422.9522 | 2845.9022 | 1364 | 1475 | 2839 | 52.0478 | -6.9022 | 3.658% | -0.2425% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
122 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCC | Dist Sub: Substation Test Dpt | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 1599.4152 | 1620.6938 | 3220.109 | 3607.2022 | 3910.7222 | 7517.9243 | 2290.0283 | 4297.8153 | 141.3% | 133.5% | N/A | N/A | # of Relays Maintained | 1422.95 | 1422.9522 | 2845.9022 | 1364 | 1475 | 2839 | 52.0478 | -6.9022 | 3.658% | -0.2425% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
123 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCD | Dsbn: Station Read_prev maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 3310.9587 | 3355.0078 | 6665.9664 | 3254.1144 | 3208.7438 | 6462.8581 | -146.264 | -203.1083 | -4.36% | -3.047% | NO | NO | Substation Inspections | 6849.81 | 6849.8134 | 13699.6234 | 6671 | 6319 | 12990 | -530.8134 | -709.6234 | -7.749% | -5.18% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
124 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCD | Dsbn: Station Read_prev maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 3310.9587 | 3355.0078 | 6665.9664 | 3254.1144 | 3208.7438 | 6462.8581 | -146.264 | -203.1083 | -4.36% | -3.047% | N/A | N/A | # of Substation Inspections | 6849.81 | 6849.8134 | 13699.6234 | 6671 | 6319 | 12990 | -530.8134 | -709.6234 | -7.749% | -5.18% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
125 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCD | Dsbn: Station Read_prev maint. | Wildfire | WLDFR-C003: Patrols and Inspections - Substation | Ex 4, Ch 15 | No | N/A | N/A | 3310.9587 | 3355.0078 | 6665.9664 | 3254.1144 | 3208.7438 | 6462.8581 | -146.264 | -203.1083 | -4.36% | -3.047% | N/A | N/A | # of Substation Inspections | 6849.81 | 6849.8134 | 13699.6234 | 6671 | 6319 | 12990 | -530.8134 | -709.6234 | -7.749% | -5.18% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
126 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCE | Dsbn: Gnrl station_prev maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 539.4853 | 546.6626 | 1086.1479 | 676.5371 | 546.3868 | 1222.9239 | -0.27579 | 136.776 | -0.05045% | 12.59% | NO | NO | Substation Preventative | 1176.97 | 1176.9733 | 2353.9433 | 1866 | 1487 | 3353 | 310.0267 | 999.0567 | 26.34% | 42.44% | YES | Below variance threshold. | Actual units were higher than imputed units due to the bundling of work for executional efficiencies, which resulted in additional program units being pulled into scope for a lower unit cost. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
127 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCE | Dsbn: Gnrl station_prev maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 539.4853 | 546.6626 | 1086.1479 | 676.5371 | 546.3868 | 1222.9239 | -0.27579 | 136.776 | -0.05045% | 12.59% | N/A | N/A | # of Substation Preventative tasks | 1176.97 | 1176.9733 | 2353.9433 | 1866 | 1487 | 3353 | 310.0267 | 999.0567 | 26.34% | 42.44% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
128 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCF | Dsbn: Batteries - prev maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 528.9071 | 535.9437 | 1064.8509 | 456.1467 | 499.9527 | 956.0994 | -35.991 | -108.7514 | -6.715% | -10.21% | NO | NO | Batteries Maintained | 1238.98 | 1238.9791 | 2477.9591 | 1306 | 1200 | 2506 | -38.9791 | 28.0409 | -3.146% | 1.132% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
129 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCF | Dsbn: Batteries - prev maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 528.9071 | 535.9437 | 1064.8509 | 456.1467 | 499.9527 | 956.0994 | -35.991 | -108.7514 | -6.715% | -10.21% | N/A | N/A | # of Batteries Maintained | 1238.98 | 1238.9791 | 2477.9591 | 1306 | 1200 | 2506 | -38.9791 | 28.0409 | -3.146% | 1.132% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
130 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCG | Vegetation Management | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 10476.5925 | 10615.9734 | 21092.5659 | 8039.823 | 6484.1992 | 14524.0222 | -4131.7743 | -6568.5438 | -38.92% | -31.14% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
131 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCG | Vegetation Management | Substation | SBSTN-C021: Vegetation Management | Ex 4, Ch 15 | No | N/A | N/A | 10476.5925 | 10615.9734 | 21092.5659 | 8039.823 | 6484.1992 | 14524.0222 | -4131.7743 | -6568.5438 | -38.92% | -31.14% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
132 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCG | Vegetation Management | Wildfire | WLDFR-C006: Vegetation Management - Substation | Ex 4, Ch 15 | No | N/A | N/A | 10476.5925 | 10615.9734 | 21092.5659 | 8039.823 | 6484.1992 | 14524.0222 | -4131.7743 | -6568.5438 | -38.92% | -31.14% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
133 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCH | Building Maintenance | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 1101.1846 | 1115.8349 | 2217.0195 | 3638.9453 | 3330.0338 | 6968.9791 | 2214.199 | 4751.9596 | 198.4% | 214.3% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
134 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCH | Building Maintenance | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 1101.1846 | 1115.8349 | 2217.0195 | 3638.9453 | 3330.0338 | 6968.9791 | 2214.199 | 4751.9596 | 198.4% | 214.3% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
135 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCI | Dsbn: Switches_prevent maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 106.8392 | 108.2606 | 215.0999 | 152.7471 | 30.4673 | 183.2143 | -77.7934 | -31.8855 | -71.86% | -14.82% | NO | NO | Switches Maintained | 112 | 112.0001 | 224.0001 | 70 | 24 | 94 | -88.0001 | -130.0001 | -78.57% | -58.04% | YES | Below variance threshold. | Actual units were lower than imputed units due to higher actual unit costs than forecast. Higher unit costs are generally driven by labor, and resulted in fewer program units achieved. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
136 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCI | Dsbn: Switches_prevent maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 106.8392 | 108.2606 | 215.0999 | 152.7471 | 30.4673 | 183.2143 | -77.7934 | -31.8855 | -71.86% | -14.82% | N/A | N/A | N/A | 112 | N/A | N/A | 70 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
137 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCJ | Dist Sub: Corrective (T80) | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 15 | No | On-going | Annual | 10080.9699 | 10215.0875 | 20296.0575 | 13311.7023 | 13822.7529 | 27134.4552 | 3607.6654 | 6838.3977 | 35.32% | 33.69% | NO | NO | Substation Corrective | 4726.85 | 4726.8456 | 9453.6956 | 8631 | 10577 | 19208 | 5850.1544 | 9754.3044 | 123.8% | 103.2% | YES | Below variance threshold. | Actual units were higher than imputed units due to the bundling of work for executional efficiencies, which resulted in additional program units being pulled into scope for a lower unit cost. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
138 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCM | Breaker Mechanism Services | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 1588.837 | 1609.975 | 3198.812 | 2527.6063 | 2115.5727 | 4643.179 | 505.5977 | 1444.367 | 31.4% | 45.15% | NO | NO | # Mech Services | 709.98 | 709.9775 | 1419.9575 | 844 | 682 | 1526 | -27.9775 | 106.0425 | -3.941% | 7.468% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
139 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCM | Breaker Mechanism Services | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 1588.837 | 1609.975 | 3198.812 | 2527.6063 | 2115.5727 | 4643.179 | 505.5977 | 1444.367 | 31.4% | 45.15% | N/A | N/A | # of Mechanism Services | 709.98 | 709.9775 | 1419.9575 | 844 | 682 | 1526 | -27.9775 | 106.0425 | -3.941% | 7.468% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
140 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCO | Transformer Overhauls | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 1291.5912 | 1308.7746 | 2600.3658 | 824.1389 | 1244.4521 | 2068.5911 | -64.3225 | -531.7747 | -4.915% | -20.45% | NO | NO | # Mech Services | 151 | 150.9977 | 301.9977 | 60 | 102 | 162 | -48.9977 | -139.9977 | -32.45% | -46.36% | YES | Below variance threshold. | Actual units were lower than imputed units due to higher actual unit costs than forecast. Higher unit costs are generally driven by labor, and resulted in fewer program units achieved. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
141 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCO | Transformer Overhauls | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 1291.5912 | 1308.7746 | 2600.3658 | 824.1389 | 1244.4521 | 2068.5911 | -64.3225 | -531.7747 | -4.915% | -20.45% | N/A | N/A | # of Mechanism Services | 151 | 150.9977 | 301.9977 | 60 | 102 | 162 | -48.9977 | -139.9977 | -32.45% | -46.36% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
142 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCS | CKSW MOAS Mechanism Services | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 214.7363 | 217.5932 | 432.3295 | 256.403 | 555.6226 | 812.0256 | 338.0294 | 379.6961 | 155.3% | 87.83% | NO | NO | # Overhauls | 82 | 82.0024 | 164.0024 | 51 | 88 | 139 | 5.9976 | -25.0024 | 7.314% | -15.25% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
143 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCS | CKSW MOAS Mechanism Services | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 214.7363 | 217.5932 | 432.3295 | 256.403 | 555.6226 | 812.0256 | 338.0294 | 379.6961 | 155.3% | 87.83% | N/A | N/A | # of Overhauls | 82 | 82.0024 | 164.0024 | 51 | 88 | 139 | 5.9976 | -25.0024 | 7.314% | -15.25% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
144 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCV | Breaker Overhauls | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 21.1563 | 21.4378 | 42.594 | 105.3334 | 83.9332 | 189.2666 | 62.4954 | 146.6725 | 291.5% | 344.3% | NO | NO | # Overhauls | 5 | 5.0012 | 10.0012 | 19 | 13 | 32 | 7.9988 | 21.9988 | 159.9% | 220% | YES | Below variance threshold. | Actual units were higher than imputed units based on objective to ensure circuit breakers are operating as intended, resulting in more overhauls than forecast. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
145 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCV | Breaker Overhauls | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 21.1563 | 21.4378 | 42.594 | 105.3334 | 83.9332 | 189.2666 | 62.4954 | 146.6725 | 291.5% | 344.3% | N/A | N/A | N/A | 5 | N/A | N/A | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
146 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCW | Dist Sub: Station Washes | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 463.3227 | 469.4867 | 932.8094 | 410.2365 | 472.6186 | 882.855 | 3.1318 | -49.9543 | 0.6671% | -5.355% | NO | NO | Substation Preventative | 429.99 | 429.9895 | 859.9795 | 458 | 457 | 915 | 27.0105 | 55.0205 | 6.282% | 6.398% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
147 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCW | Dist Sub: Station Washes | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | No | N/A | N/A | 463.3227 | 469.4867 | 932.8094 | 410.2365 | 472.6186 | 882.855 | 3.1318 | -49.9543 | 0.6671% | -5.355% | N/A | N/A | N/A | 429.99 | N/A | N/A | 458 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
148 | Expense | Electric Distribution | GE | E Dist Mapping | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 20 | No | On-going | Annual | 19272.2306 | 19284.6971 | 38556.9277 | 24668.3532 | 29589.4787 | 54257.8319 | 10304.7816 | 15700.9042 | 53.44% | 40.72% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values due to: (1) expenses to develop and implement PG&E’s Asset Data Management Plan, data management standards, tools, analytic products, and data quality improvement projects, and (2) expenses from emergent programs created to improve wildfire-related data, develop wildfire data and analytic products, and respond to wildfire related data requirements including the Wildfire Safety Division GIS Data Standard. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to: 1) manage the Electric Asset Registry including GIS systems of record, mapping of new assets, and conversion of records into digital form; 2) manage data quality; 3) provide data access and integration; and 4) develop new analytic tools in support of Electric Asset Management. PG&E may continue to spend more than adopted in this program over the course of the GRC cycle in order to manage data critical to Electric Operations.
149 | Expense | Electric Distribution | GE | E Dist Mapping | N/A | Not assigned | Wildfire | WLDFR-M002: System Hardening | Ex 4, Ch 20 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 199.4234 | 199.4234 | 199.4234 | 199.4234 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
150 | Expense | Electric Distribution | GE | E Dist Mapping | N/A | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 20 | Yes | On-going | Annual | 19272.2306 | 19284.6971 | 38556.9277 | 24668.3532 | 29390.0553 | 54058.4085 | 10105.3582 | 15501.4808 | 52.4% | 40.2% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
151 | Expense | Electric Distribution | HG | Elec Trans Ops Engr & Tech | HG# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 21 | No | On-going | Annual | 0 | 0 | 0 | 0 | 2970.3987 | 2970.3987 | 2970.3987 | 2970.3987 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | The DERMS program work is ongoing and will continue into PG&E's 2023 GRC period. New tools and processes for orchestration of Distributed Energy Resources (DERs) are required to safely and cost-effectively operate the grid. The Distributed Energy Resources Management (DERMS) Program includes the development, deployment, and operation of these tools and processes to enable these objectives. These costs support the ongoing operation and maintenance of these tools and processes. Note: DERMS program costs were originally adopted under the HGC MAT code, but have since been moved under HG#.
152 | Expense | Electric Distribution | HG | Elec Trans Ops Engr & Tech | HGC | Advanced Dist Mgmt System Dev | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 21 | No | 10 | 8 | 17229.2774 | 17159.8721 | 34389.1495 | 11058.9714 | 10731.9297 | 21790.9011 | -6427.9424 | -12598.2484 | -37.46% | -36.63% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses were below imputed regulatory values due to the availability of a technological solution for obtaining phase identification data necessary to support the immediate needs of ADMS, eliminating the need to manually collect this data. | N/A | On-Target | On-Target | Under | Proceeding as Planned | The ADMS program is a one-time program, and is projected to be completed in 2026, prior to the end of the 2023 GRC cycle. PG&E anticipates continuing to spend below imputed amounts for the remainder of the GRC cycle because the program involves project-based work that may have peaked in the GRC Test Year.
153 | Expense | Electric Distribution | HG | Elec Trans Ops Engr & Tech | HGD | Distribution Operational Tech | SRM Total | SRM Total | Ex 4, Ch 7 | No | On-going | Annual | 5978.0311 | 5953.9495 | 11931.9806 | 7481.5202 | 9306.6721 | 16788.1924 | 3352.7226 | 4856.2117 | 56.31% | 40.7% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This MAT Code is being used for ongoing maintenance tied to Distribution Operational Technology.
154 | Expense | Electric Distribution | HG | Elec Trans Ops Engr & Tech | HGD | Distribution Operational Tech | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 7 | Yes | N/A | N/A | 0 | 0 | 0 | 82.8474 | 173.8516 | 256.699 | 173.8516 | 256.699 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
155 | Expense | Electric Distribution | HG | Elec Trans Ops Engr & Tech | HGD | Distribution Operational Tech | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 7 | Yes | N/A | N/A | 5978.0311 | 5953.9495 | 11931.9806 | 7398.6728 | 9132.8206 | 16531.4934 | 3178.871 | 4599.5128 | 53.39% | 38.55% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
156 | Expense | Electric Distribution | HN | E Dist Tree Trim Bal Acct | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 9 | No | On-going | Annual | 972012.9814 | 965868.48 | 1937881.4615 | 859187.0852 | 1002998.7474 | 1862185.8327 | 37130.2674 | -75695.6288 | 3.844% | -3.906% | YES | NO | # of Veg. Mgmt Trees | 1546783 | 1546783 | 3093566 | 1241025 | 1410201.22 | 2651226.22 | -136581.78 | -442339.78 | -8.83% | -14.3% | NO | Program expenses exceeded imputed regulatory values, primarily as the result of increased units completed due to a rebalance of work, based upon a risk-informed assessment of available tree work. Funding for work was reallocated to Distribution Routine to prioritize work in areas that held higher risk in the marked tree inventory and reduced the overall carryover. In addition, incremental Pole Clearing units were added to the work plan to address ignition risk identified using the Utility Fire Potential Index (FPI). | Below variance threshold. | On-Target | Under | Under | Rescheduled | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to perform routine tree work. PG&E anticipates continuing to perform fewer units than adopted over the remainder of the GRC cycle.
157 | Expense | Electric Distribution | HN | E Dist Tree Trim Bal Acct | N/A | Not assigned | Distribution Overhead | DOVHD-C001: Vegetation Management - Distribution Overhead | Ex 4, Ch 9 | No | N/A | N/A | 972012.9814 | 965868.48 | 1937881.4615 | 859187.1 | 1002998.7474 | 1862185.8474 | 37130.2674 | -75695.6141 | 3.844% | -3.906% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
158 | Expense | Electric Distribution | HN | E Dist Tree Trim Bal Acct | N/A | Not assigned | Wildfire | WLDFR-C004: Vegetation Management - Distribution Overhead | Ex 4, Ch 9 | No | N/A | N/A | 972012.9814 | 965868.48 | 1937881.4615 | 859187.1 | 1002998.7474 | 1862185.8474 | 37130.2674 | -75695.6141 | 3.844% | -3.906% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
159 | Expense | Electric Distribution | HX | E T&D Automation & Protection | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 16 | No | On-going | Annual | 3118.3174 | 3184 | 6302.3175 | 2693.8379 | 1990.0543 | 4683.8922 | -1193.9457 | -1618.4252 | -37.5% | -25.68% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
160 | Expense | Electric Distribution | HX | E T&D Automation & Protection | N/A | Not assigned | Distribution Overhead | DOVHD-C007: Supervisory Control and Data Acquisition | Ex 4, Ch 16 | Yes | N/A | N/A | 3118.3174 | 3184 | 6302.3175 | 2693.8379 | 1990.0543 | 4683.8922 | -1193.9457 | -1618.4252 | -37.5% | -25.68% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
161 | Expense | Electric Distribution | HX | E T&D Automation & Protection | N/A | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 16 | Yes | N/A | N/A | 0 | 0 | 0 | 72.5254 | 57.1026 | 129.628 | 57.1026 | 129.628 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
162 | Expense | Electric Distribution | HY | Change/Maint Used Gas Meters | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 687.1 | 710.3007 | 1397.4007 | 250.6 | 289.4958 | 540.0958 | -420.8049 | -857.3049 | -59.24% | -61.35% | NO | NO | Field orders | 1466 | 1466 | 2932 | 2927 | 3478 | 6405 | 2012 | 3473 | 137.2% | 118.5% | YES | Below variance threshold. | Actual units were higher than imputed units because of an increase in the need to maintain or change used gas meters. This demand is from either 1) customer requests e.g., usage inquiries; or 2) automated system notification for resolution of a meter issue. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to provide gas meter maintenance, based on 1) customer-driven requests; and 2) automated system notifications for meter issue resolution.
163 | Expense | Electric Distribution | IF | E Dist Major Emergency | N/A | N/A | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 6 | No | On-going | Annual | 45380.7998 | 45908.2092 | 91289.009 | 38356.8805 | 214333.8032 | 252690.6837 | 168425.594 | 161401.6747 | 366.9% | 176.8% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values due the February Winter Storms and the July Weather Event which caused a significant deviation from historical trends. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is for major emergencies. This is a demand driven program. This program has no end and is responsive to conditions that require immediate attention.
164 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IGI | Dead and Dying Trees | SRM Total | SRM Total | Ex 4, Ch 9 | No | On-going | Annual | 77991.4684 | 77468.8654 | 155460.3338 | 136577.1456 | 139861.4302 | 276438.5758 | 62392.5648 | 120978.242 | 80.54% | 77.82% | YES | YES | # of Veg. Mgmt Trees | 65000 | 65000 | 130000 | 81281 | 225345.35 | 306626.35 | 160345.35 | 176626.35 | 246.7% | 135.9% | YES | Program expenses exceeded imputed regulatory values due to increased tree units. Volume of work increased due to 1) rescheduled work from previous year; and 2) more work was identified due to changes in scope of patrol procedure. For example, including not just dead trees but healthy trees with defects and trees with growth that could break compliance distance. | Actual units were higher than imputed units of work due to 1) rescheduled work from previous year; and 2) more work was identified due to changes in scope of patrol procedure. For example, including not just dead trees but healthy trees with defects and growth that could break compliance distance. | Over | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. This program is scheduled to continue through 2026, and PG&E anticipates continuing to perform more units than adopted in the 2023 GRC.
165 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IGI | Dead and Dying Trees | Distribution Overhead | DOVHD-C002: Vegetation Management - CEMA/Tree Mortality | Ex 4, Ch 9 | No | N/A | N/A | 77991.4684 | 77468.8654 | 155460.3338 | 136577.1456 | 139861.4302 | 276438.5758 | 62392.5648 | 120978.242 | 80.54% | 77.82% | N/A | N/A | N/A | 65000 | N/A | N/A | 81281 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
166 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IGI | Dead and Dying Trees | Wildfire | WLDFR-C007: Vegetation Management - CEMA/Tree Mortality | Ex 4, Ch 9 | No | N/A | N/A | 77991.4684 | 77468.8654 | 155460.3338 | 136577.1456 | 139861.4302 | 276438.5758 | 62392.5648 | 120978.242 | 80.54% | 77.82% | N/A | N/A | N/A | 65000 | N/A | N/A | 81281 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
167 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IGJ | Enhanced Vegetation Management | SRM Total | SRM Total | Ex 4, Ch 9 | No | On-going | Annual | 131815.9685 | 130932.6999 | 262748.6684 | 161012.919 | 180873.9783 | 341886.8973 | 49941.2784 | 79138.2289 | 38.14% | 30.12% | YES | YES | # Miles | 1800 | 1800 | 3600 | 274 | N/A | 274 | -1800 | -3326 | -100% | -92.39% | YES | Program expenses exceed imputed regulatory values due to MAT IGJ imputed adopted values would have reflected a forecast for EVM which was discontinued at the end of 2022 and superseded by Wildfire Mitigation Plan programs: Focused Tree Inspection (FTI), Tree Removal Inventory (TRI) & VM for Operational Mitigations (VMOM). Wood Management for Wildfire Mitigation Programs is also included in MAT IGJ. Forecast Cost for EVM anticipated clearing overhanging branches for 1,800 miles, whereas the mitigation programs include 1,500 miles of FTI, detailed inspection, and TRI is whole tree removals listed under the previous EVM program. Under both of these programs work is predominantly tree removals rather than the anticipated clearing overhanging branches in 2023 GRC. | Actual units were lower than imputed units because the Enhanced Vegetation Management (EVM) program was discontinued at the end of 2022. The scope of work changed in 2023 to focus on four primary programs: Focused Tree Inspection (FTI), Tree Removal Inventory (TRI), VM for Operational Mitigations (VMOM) and Wood Management. The imputed adopted value reflected a unit forecast for EVM measured in miles, whereas the unit of measure for the new programs were a combination of trees, wood managed, and miles. | Under | Over | Over | Emergent | Work is ongoing and will continue in PG&E’s 2023 GRC period. The Enhanced Vegetation Management (EVM) program concluded in 2022, and the scope of the program was changed as described in the unit variance explanation. PG&E anticipates continuing with the adjusted scope of the program, focusing on Focused Tree Inspection, VMOM, Tree Removal Inventory, and Wood Management.
168 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IGJ | Enhanced Vegetation Management | Wildfire | WLDFR-M001: Enhanced Vegetation Management | Ex 4, Ch 9 | No | N/A | N/A | 131815.9685 | 130932.6999 | 262748.6684 | 161012.919 | 180873.9783 | 341886.8973 | 49941.2784 | 79138.2289 | 38.14% | 30.12% | N/A | N/A | N/A | 1800 | N/A | N/A | 274 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
169 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | SRM Total | SRM Total | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | No | On-going | Annual | 76787.2006 | 77665.1635 | 154452.3641 | 132422.3794 | 78133.3166 | 210555.696 | 468.1531 | 56103.3319 | 0.6028% | 36.32% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | Over | Over | Emergent | This work is ongoing and will continue in PG&Es 2023 GRC period. This MAT is used to record various balancing and memorandum account activities. PG&E anticipates that this program will be over the 2023 GRC cycle imputed regulatory values for MAT Code IG# due to activities for mitigating wildfire risk that were not forecast in IG# in the 2023 GRC. These include EPSS costs for helicopter standby, temporary generation, and battery programs.
170 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Distribution Overhead | DOVHD-C002: Vegetation Management - CEMA/Tree Mortality | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 2442.7271 | 2442.7271 | 2442.7271 | 2442.7271 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
171 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Distribution Overhead | DOVHD-M005: Additional Asset Data Capture | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 183.895 | 0 | 183.895 | 0 | 183.895 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
172 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Emergency Preparedness & Response | EPNDR-C000: EP&R Controls | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 232.201 | 350.6866 | 582.8875 | 350.6866 | 582.8875 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
173 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Emergency Preparedness & Response | EPNDR-C002: Situational Awareness and Forecasting Initiatives - WSOC | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 2724.6525 | 0 | 2724.6525 | 0 | 2724.6525 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
174 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Emergency Preparedness & Response | EPNDR-M000: EP&R Mitigations | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 189.9826 | 286.9254 | 476.908 | 286.9254 | 476.908 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
175 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Wildfire | WLDFR-C007: Vegetation Management - CEMA/Tree Mortality | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 2442.7271 | 2442.7271 | 2442.7271 | 2442.7271 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
176 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 7202.4815 | 4883.8865 | 12086.368 | 4883.8865 | 12086.368 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
177 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Wildfire | WLDFR-M0IT: Wildfire IT Work | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 38734.4 | 38882.8461 | 77617.2461 | 36120.5247 | 37507.9374 | 73628.4622 | -1374.9087 | -3988.7839 | -3.536% | -5.139% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
178 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 34895.7218 | 35566.7184 | 70462.4401 | 64233.3524 | 30783.913 | 95017.2655 | -4782.8053 | 24554.8253 | -13.45% | 34.85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
179 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Wildfire | POST-GRC: Post-GRC Mitigation | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 18404.1181 | 1353.332 | 19757.4501 | 1353.332 | 19757.4501 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
180 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 3157 | 3215.599 | 6372.599 | 3131.1716 | 523.9086 | 3655.0802 | -2691.6904 | -2717.5189 | -83.71% | -42.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
181 | Expense | Electric Distribution | IS | Bill Customers | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 22 | No | On-going | Annual | 1830.672 | 1819.0996 | 3649.7716 | 572.5527 | 672.9663 | 1245.5189 | -1146.1333 | -2404.2527 | -63.01% | -65.87% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
182 | Expense | Electric Distribution | IU | Collect Revenue | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 1589.8684 | 1659.8259 | 3249.6943 | 1088.0359 | 1274.3272 | 2362.3631 | -385.4988 | -887.3313 | -23.23% | -27.31% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
183 | Expense | Electric Distribution | JV | Maintain IT Apps & Infra | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 20 Ex 4, Ch 21 | No | On-going | Annual | 8419.0283 | 8471.7026 | 16890.7308 | 4430.1601 | 4715.7107 | 9145.8708 | -3755.9919 | -7744.86 | -44.34% | -45.85% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
184 | Expense | Electric Distribution | JV | Maintain IT Apps & Infra | N/A | Not assigned | Emergency Preparedness & Response | EPNDR-C002: Situational Awareness and Forecasting Initiatives - WSOC | Ex 4, Ch 20 Ex 4, Ch 21 | Yes | N/A | N/A | 0 | 0 | 0 | 755.5872 | 0 | 755.5872 | 0 | 755.5872 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
185 | Expense | Electric Distribution | JV | Maintain IT Apps & Infra | N/A | Not assigned | IT Asset Failure | ITAFL-M005: Multi-Faceted Mitigations | Ex 4, Ch 20 Ex 4, Ch 21 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 71.0928 | 71.0928 | 71.0928 | 71.0928 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
186 | Expense | Electric Distribution | JV | Maintain IT Apps & Infra | N/A | Not assigned | Wildfire | WLDFR-M0IT: Wildfire IT Work | Ex 4, Ch 20 Ex 4, Ch 21 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 293.8195 | 293.8195 | 293.8195 | 293.8195 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
187 | Expense | Electric Distribution | JV | Maintain IT Apps & Infra | N/A | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 20 Ex 4, Ch 21 | Yes | N/A | N/A | 8419.0283 | 8471.7026 | 16890.7308 | 3674.5729 | 4350.7984 | 8025.3713 | -4120.9042 | -8865.3595 | -48.64% | -52.49% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
188 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAA | OH Genl CM Tag | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 22085.7202 | 22135.0216 | 44220.7418 | 75395.0109 | 139875.0479 | 215270.0588 | 117740.0263 | 171049.317 | 531.9% | 386.8% | YES | YES | # of Notifications Completed | 24150.66 | 24150.6645 | 48301.3245 | 26555 | 58049 | 84604 | 33898.3355 | 36302.6755 | 140.4% | 75.16% | YES | Program expenses exceeded imputed regulatory values due to higher volume of units completed at higher unit costs than adopted in the 2023 GRC Final Decision. PG&E's actual unit cost remain higher than imputed unit costs driven by the higher labor costs for this work. | Actual units were higher than imputed units due to address WMP commitments for the maintenance log. | Over | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is the repair of overhead (OH) facilities or replacement of individual components that are not an imminent hazard. PG&E anticipates the program scope will remain on target while spending more than the GRC imputed adopted costs over the remainder of the cycle to address the maintenance log and meet WMP commitments.
189 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAA | OH Genl CM Tag | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 22085.7202 | 22135.0216 | 44220.7418 | 75395.0109 | 139875.0479 | 215270.0588 | 117740.0263 | 171049.317 | 531.9% | 386.8% | N/A | N/A | # of Notifications Completed | 24150.66 | 24150.6645 | 48301.3245 | 26555 | 58049 | 84604 | 33898.3355 | 36302.6755 | 140.4% | 75.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
190 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAA | OH Genl CM Tag | Wildfire | WLDFR-C008: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 22085.7202 | 22135.0216 | 44220.7418 | 75395.0109 | 139875.0479 | 215270.0588 | 117740.0263 | 171049.317 | 531.9% | 386.8% | N/A | N/A | # of Notifications Completed | 24150.66 | 24150.6645 | 48301.3245 | 26555 | 58049 | 84604 | 33898.3355 | 36302.6755 | 140.4% | 75.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
191 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAC | Bird Safe Retrofit | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1231.4039 | 1234.1528 | 2465.5567 | 683.0583 | 586.3039 | 1269.3623 | -647.8489 | -1196.1945 | -52.49% | -48.52% | NO | NO | # of Notifications Completed | 638.16 | 638.1579 | 1276.3179 | 402 | 228 | 630 | -410.1579 | -646.3179 | -64.27% | -50.64% | YES | Below variance threshold. | Actual units were lower than imputed units due to lower find rates than forecasted. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is the replacement or installation of bird guard materials such as jumper covers, bushing covers, perch guards, or perching platforms on incident and/or adjacent poles in response to a bird electrocution, per U.S. Fish and Wildlife Service (USFWS) requirements and Utility Operating Standard S2321.
192 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAC | Bird Safe Retrofit | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 1231.4039 | 1234.1528 | 2465.5567 | 683.0583 | 586.3039 | 1269.3623 | -647.8489 | -1196.1945 | -52.49% | -48.52% | N/A | N/A | # of Notifications Completed | 638.16 | 638.1579 | 1276.3179 | 402 | 228 | 630 | -410.1579 | -646.3179 | -64.27% | -50.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
193 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAC | Bird Safe Retrofit | Wildfire | WLDFR-C011: Animal Abatement | Ex 4, Ch 11 | No | N/A | N/A | 1231.4039 | 1234.1528 | 2465.5567 | 683.0583 | 586.3039 | 1269.3623 | -647.8489 | -1196.1945 | -52.49% | -48.52% | N/A | N/A | # of Notifications Completed | 638.16 | 638.1579 | 1276.3179 | 402 | 228 | 630 | -410.1579 | -646.3179 | -64.27% | -50.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
194 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAD | Bird Safe Retrofit Annual | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1436.2747 | 1439.4809 | 2875.7555 | 312.6943 | 3467.5951 | 3780.2894 | 2028.1142 | 904.5339 | 140.9% | 31.45% | NO | NO | # of Notifications Completed | 1022 | 1022.0001 | 2044.0001 | 224 | 974 | 1198 | -48.0001 | -846.0001 | -4.697% | -41.39% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
195 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAD | Bird Safe Retrofit Annual | Wildfire | WLDFR-C011: Animal Abatement | Ex 4, Ch 11 | No | N/A | N/A | 1436.2747 | 1439.4809 | 2875.7555 | 312.6943 | 3467.5951 | 3780.2894 | 2028.1142 | 904.5339 | 140.9% | 31.45% | N/A | N/A | # of Notifications Completed | 1022 | 1022.0001 | 2044.0001 | 224 | 974 | 1198 | -48.0001 | -846.0001 | -4.697% | -41.39% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
196 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAF | OH COE CM Tag | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 7212.9759 | 7229.0772 | 14442.0531 | 6418.8636 | 5790.394 | 12209.2576 | -1438.6832 | -2232.7955 | -19.9% | -15.46% | NO | NO | # of Notifications Completed | 1380 | 1380.0002 | 2760.0002 | 1141 | 1250 | 2391 | -130.0002 | -369.0002 | -9.42% | -13.37% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
197 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAF | OH COE CM Tag | Wildfire | WLDFR-C008: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 7212.9759 | 7229.0772 | 14442.0531 | 6418.8636 | 5790.394 | 12209.2576 | -1438.6832 | -2232.7955 | -19.9% | -15.46% | N/A | N/A | # of Notifications Completed | 1380 | 1380.0002 | 2760.0002 | 1141 | 1250 | 2391 | -130.0002 | -369.0002 | -9.42% | -13.37% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
198 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAH | Streetlights Repl Burnouts | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 2171.8479 | 2176.696 | 4348.5439 | 1769.6744 | 1895.4349 | 3665.1093 | -281.2611 | -683.4345 | -12.92% | -15.72% | NO | NO | # of Burnout Repairs | 11714.32 | 11714.3214 | 23428.6414 | 6191 | 0 | 6191 | -11714.3214 | -17237.6414 | -100% | -73.58% | YES | Below variance threshold. | With the near completion of the LED conversion program, fewer HPSV bulb replacements will be needed (instead LED fixtures will need to be replaced under MAT 2AH) and replacements will be done ad-hoc. Therefore the costs are no longer unitized. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to repair streetlights when a streetlight outage has occurred. Since the LED conversion program is almost complete, a lower find rate for streetlights requiring bulb replacement is expected and the work will be tracked programmatically.
199 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAH | Streetlights Repl Burnouts | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 2171.8479 | 2176.696 | 4348.5439 | 1769.6744 | 1895.4349 | 3665.1093 | -281.2611 | -683.4345 | -12.92% | -15.72% | N/A | N/A | # of Burnout Repairs | 11714.32 | 11714.3214 | 23428.6414 | 6191 | 0 | 6191 | -11714.3214 | -17237.6414 | -100% | -73.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
200 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAK | RTVI Invest/Repr | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 126.4096 | 126.6918 | 253.1014 | 88.7648 | 80.9353 | 169.7001 | -45.7565 | -83.4013 | -36.12% | -32.95% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
201 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAM | Insulators Wash | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 246.2808 | 246.8306 | 493.1114 | 304.7772 | 237.1062 | 541.8835 | -9.7243 | 48.7721 | -3.94% | 9.891% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
202 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAM | Insulators Wash | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 246.2808 | 246.8306 | 493.1114 | 304.7772 | 237.1062 | 541.8835 | -9.7243 | 48.7721 | -3.94% | 9.891% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
203 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAO | Idle Fac Invest - Svc Plng | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 214.6784 | 215.1576 | 429.836 | 2054.0632 | 1820.8959 | 3874.9591 | 1605.7383 | 3445.1231 | 746.3% | 801.5% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
204 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAO | Idle Fac Invest - Svc Plng | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 214.6784 | 215.1576 | 429.836 | 2054.0632 | 1820.8959 | 3874.9591 | 1605.7383 | 3445.1231 | 746.3% | 801.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
205 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAP | OH EXP Projects | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1792.619 | 1796.6206 | 3589.2397 | 25.5764 | 3496.9548 | 3522.5311 | 1700.3341 | -66.7085 | 94.64% | -1.859% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
206 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAP | OH EXP Projects | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 1792.619 | 1796.6206 | 3589.2397 | 25.5764 | 3496.9548 | 3522.5311 | 1700.3341 | -66.7085 | 94.64% | -1.859% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
207 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAQ | Wood Pole Bridge Bonding | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1.0897 | 1.0922 | 2.1819 | 881.7755 | 671.5721 | 1553.3476 | 670.48 | 1551.1657 | 61390% | 71092% | NO | NO | # of Notifications Completed | 2 | 2 | 4 | 296 | 237 | 533 | 235 | 529 | 11750% | 13225% | YES | Below variance threshold. | Actual units were higher than imputed units based on actual find rate (i.e. inspections that identified the need for a higher number of wood pole bridge bonding retrofits than anticipated) and targeted focus to complete this work as it is a control for reducing the risk of wildfire. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is Wood Pole Bridge Bonding to prevent ignitions by ensuring grounding protection. Wood pole bonding is a maintenance activity where an existing wood pole supporting both electric transmission and distribution line facilities is retrofitted with grounding protection to prevent fires which can occur at the location on the pole where the electric distribution cross arm is bolted to the pole.
208 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAQ | Wood Pole Bridge Bonding | Wildfire | WLDFR-C008: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 1.0897 | 1.0922 | 2.1819 | 881.7755 | 671.5721 | 1553.3476 | 670.48 | 1551.1657 | 61390% | 71092% | N/A | N/A | # of Notifications Completed | 2 | 2 | 4 | 296 | 237 | 533 | 235 | 529 | 11750% | 13225% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
209 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAS | FAS Overhead Expense | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1796.978 | 1800.9893 | 3597.9673 | 1150.2837 | 1051.3607 | 2201.6444 | -749.6286 | -1396.3229 | -41.62% | -38.81% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | 10453.34 | N/A | N/A | 8302 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | MAT KAS work is identified and performed by Troubleshooters in the field and is demand driven. Due to the variable nature of the work performed in MAT KAS, MAT KAS is non-unitized beginning in 2024. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This is a demand driven program. The program repairs overhead facilities identified during a field job and completed by a single PG&E Troubleshooter. The work could involve repairing overhead facilities such as: electric distribution conductors, components, structures, and associated equipment constructed above ground level. Due to the variable nature of the work performed in MAT KAS, MAT KAS is non-unitized beginning in 2024.
210 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAS | FAS Overhead Expense | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 1796.978 | 1800.9893 | 3597.9673 | 1150.2837 | 1051.3607 | 2201.6444 | -749.6286 | -1396.3229 | -41.62% | -38.81% | N/A | N/A | N/A | 10453.34 | N/A | N/A | 8302 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
211 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAT | Remote Grid SPS Maintenance | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | On-going | Annual | 1038.7214 | 1041.0401 | 2079.7615 | 125.6272 | 667.0175 | 792.6447 | -374.0226 | -1287.1168 | -35.93% | -61.89% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
212 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAT | Remote Grid SPS Maintenance | Distribution Overhead | DOVHD-M011: Remote Grid | Ex 4, Ch 4.3 | No | N/A | N/A | 1038.7214 | 1041.0401 | 2079.7615 | 25.839 | 667.0175 | 692.8565 | -374.0226 | -1386.905 | -35.93% | -66.69% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
213 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAT | Remote Grid SPS Maintenance | Wildfire | WLDFR-M017: System Hardening - Remote Grid | Ex 4, Ch 4.3 | No | N/A | N/A | 1038.7214 | 1041.0401 | 2079.7615 | 125.6272 | 667.0175 | 792.6447 | -374.0226 | -1287.1168 | -35.93% | -61.89% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
214 | Expense | Electric Distribution | KA | E Dist Maint OH General | KA# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 888.1365 | 890.119 | 1778.2555 | -34.2349 | 1591.6165 | 1557.3817 | 701.4975 | -220.8739 | 78.81% | -12.42% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
215 | Expense | Electric Distribution | KB | E Dist Maint UG | KBA | UG Genl CM Tag | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 17135.2076 | 17270.4231 | 34405.6308 | 15657.4038 | 18614.1991 | 34271.603 | 1343.776 | -134.0278 | 7.781% | -0.3896% | NO | NO | # of Notifications Completed | 6162.85 | 6162.8494 | 12325.6994 | 4916 | 4328 | 9244 | -1834.8494 | -3081.6994 | -29.77% | -25% | YES | Below variance threshold. | Actual units were lower than imputed units due to optimizing resources to focus on completing higher priority maintenance tags within MWCs KA and KB. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is underground corrective maintenance that does not pose an imminent hazard and have not caused an outage. PG&E will continue to complete notifications based on the workplan maintenance schedule and priority of the tags.
216 | Expense | Electric Distribution | KB | E Dist Maint UG | KBA | UG Genl CM Tag | Underground | DUNGD-C002: Underground Notifications | Ex 4, Ch 11 | No | N/A | N/A | 17135.2076 | 17270.4231 | 34405.6308 | 15657.4038 | 18614.1991 | 34271.603 | 1343.776 | -134.0278 | 7.781% | -0.3896% | N/A | N/A | # of Notifications Completed | 6162.85 | 6162.8494 | 12325.6994 | 4916 | 4328 | 9244 | -1834.8494 | -3081.6994 | -29.77% | -25% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
217 | Expense | Electric Distribution | KB | E Dist Maint UG | KBC | UG COE CM Tag | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1547.5023 | 1559.7138 | 3107.2161 | 403.6052 | 809.2628 | 1212.868 | -750.451 | -1894.3481 | -48.11% | -60.97% | NO | NO | # of Notifications Completed | 175 | 175.0001 | 350.0001 | 103 | 134 | 237 | -41.0001 | -113.0001 | -23.43% | -32.29% | YES | Below variance threshold. | Actual units were lower than imputed units due to optimizing resources to focus on completing higher priority maintenance tags within MWCs KA and KB. | Under | Under | Under | Rescheduled | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of the program is to repair of underground Critical Operating Equipment (COE). During the GRC cycle PG&E expects to continue to reprioritize the work in MAT KBC to other higher priority maintenance work in MWCs KA and KB.
218 | Expense | Electric Distribution | KB | E Dist Maint UG | KBC | UG COE CM Tag | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 11 | No | N/A | N/A | 1547.5023 | 1559.7138 | 3107.2161 | 403.6052 | 809.2628 | 1212.868 | -750.451 | -1894.3481 | -48.11% | -60.97% | N/A | N/A | # of Notifications Completed | 175 | 175.0001 | 350.0001 | 103 | 134 | 237 | -41.0001 | -113.0001 | -23.43% | -32.29% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
219 | Expense | Electric Distribution | KB | E Dist Maint UG | KBD | Nitrogen Cylinders CM | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 24.6828 | 24.8775 | 49.5603 | 8.4286 | 9.834 | 18.2627 | -15.0435 | -31.2977 | -60.47% | -63.15% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
220 | Expense | Electric Distribution | KB | E Dist Maint UG | KBD | Nitrogen Cylinders CM | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 11 | No | N/A | N/A | 24.6828 | 24.8775 | 49.5603 | 8.4286 | 9.834 | 18.2627 | -15.0435 | -31.2977 | -60.47% | -63.15% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
221 | Expense | Electric Distribution | KB | E Dist Maint UG | KBE | BART Cable Repr | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 70.8288 | 71.3877 | 142.2165 | 0.53587 | 2.1424 | 2.6782 | -69.2454 | -139.5383 | -97% | -98.12% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
222 | Expense | Electric Distribution | KB | E Dist Maint UG | KBE | BART Cable Repr | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 11 | No | N/A | N/A | 70.8288 | 71.3877 | 142.2165 | 0.53587 | 2.1424 | 2.6782 | -69.2454 | -139.5383 | -97% | -98.12% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
223 | Expense | Electric Distribution | KB | E Dist Maint UG | KBP | UG EXP Projects | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 788.7754 | 794.9997 | 1583.7752 | 1.0978 | 0.14433 | 1.2422 | -794.8554 | -1582.533 | -99.98% | -99.92% | NO | NO | # of Locations | 255.24 | 255.2413 | 510.4813 | 0 | 3 | 3 | -252.2413 | -507.4813 | -98.82% | -99.41% | YES | Below variance threshold. | Actual units were lower than imputed units because this is a project-based repair program. In 2024, PG&E did not identify any underground repair projects. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. This program supports major project underground work. Completion of work is dependent on the scope of the project.
224 | Expense | Electric Distribution | KB | E Dist Maint UG | KBP | UG EXP Projects | Underground | DUNGD-C004: Planned Major Projects | Ex 4, Ch 11 | No | N/A | N/A | 788.7754 | 794.9997 | 1583.7752 | 1.0978 | 0.14433 | 1.2422 | -794.8554 | -1582.533 | -99.98% | -99.92% | N/A | N/A | # of Locations | 255.24 | 255.2413 | 510.4813 | 0 | 3 | 3 | -252.2413 | -507.4813 | -98.82% | -99.41% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
225 | Expense | Electric Distribution | KB | E Dist Maint UG | KB# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 757.6537 | 763.6324 | 1521.2861 | 0 | -63.9728 | -63.9728 | -827.6052 | -1585.2589 | -108.4% | -104.2% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
226 | Expense | Electric Distribution | KC | E Dist Maint Network | KCA | Ntwk Equip Correct Maint NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 449.8004 | 460.8723 | 910.6727 | 39.5717 | 322.0862 | 361.6578 | -138.7862 | -549.0149 | -30.11% | -60.29% | NO | NO | # of Locations | 80 | 80 | 160 | 17 | 63 | 80 | -17 | -80 | -21.25% | -50% | YES | Below variance threshold. | Actual units were lower than imputed units because this is demand-driven work and fluctuates year over year because there is a wide range of repairs covered in this MAT code and a varying number of repairs per year. Through 2024, fewer tags have been generated from abnormal operating conditions than expected. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to make repairs on network equipment e.g., transformers and protectors.
227 | Expense | Electric Distribution | KC | E Dist Maint Network | KCA | Ntwk Equip Correct Maint NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | No | N/A | N/A | 449.8004 | 460.8723 | 910.6727 | 39.5717 | 322.0862 | 361.6578 | -138.7862 | -549.0149 | -30.11% | -60.29% | N/A | N/A | # locations | 80 | 80 | 160 | 17 | 63 | 80 | -17 | -80 | -21.25% | -50% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
228 | Expense | Electric Distribution | KC | E Dist Maint Network | KCB | Ntwk Oil Repl & 60Day F/U NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 33.8891 | 34.7233 | 68.6123 | 5.2245 | 16.0789 | 21.3033 | -18.6444 | -47.309 | -53.69% | -68.95% | NO | NO | # of Locations | 25 | 25 | 50 | 8 | 7 | 15 | -18 | -35 | -72% | -70% | YES | Below variance threshold. | Actual units were lower than imputed units because fewer than expected transformers were identified as needing oil replacement as a result of dissolved gas analysis (DGA) testing. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to replace oil in network transformers based on dissolved gas analysis, and to perform 60-day follow-up re-torque requirement in order to maintain a safe and reliable distribution network system.
229 | Expense | Electric Distribution | KC | E Dist Maint Network | KCB | Ntwk Oil Repl & 60Day F/U NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | No | N/A | N/A | 33.8891 | 34.7233 | 68.6123 | 5.2245 | 16.0789 | 21.3033 | -18.6444 | -47.309 | -53.69% | -68.95% | N/A | N/A | # locations | 25 | 25 | 50 | 8 | 7 | 15 | -18 | -35 | -72% | -70% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
230 | Expense | Electric Distribution | KC | E Dist Maint Network | KCC | Ntwk Vault Correct Maint NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 134.5293 | 137.8408 | 272.3701 | 7.6588 | 310.5539 | 318.2127 | 172.7131 | 45.8426 | 125.3% | 16.83% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
231 | Expense | Electric Distribution | KC | E Dist Maint Network | KCC | Ntwk Vault Correct Maint NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | No | N/A | N/A | 134.5293 | 137.8408 | 272.3701 | 7.6588 | 310.5539 | 318.2127 | 172.7131 | 45.8426 | 125.3% | 16.83% | N/A | N/A | N/A | 7658.82 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
232 | Expense | Electric Distribution | KC | E Dist Maint Network | KCD | Ntwk Xfmr PrevMaint/Retst NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 2808.6851 | 2877.8214 | 5686.5065 | 4486.7169 | 4056.2771 | 8542.994 | 1178.4557 | 2856.4875 | 40.95% | 50.23% | NO | NO | Transformer Oil Tests | 3600 | 3600 | 7200 | 1363 | 1403 | 2766 | -2197 | -4434 | -61.03% | -61.58% | YES | Below variance threshold. | PG&E changed the unit of measure for this MAT in 2023 from (1) the number of chambers for which we drew oil samples from, to (2) the number of transformers maintained. The 2023 GRC unit forecast was based on the number of chambers that each network transformer can have; network transformers can have up to 3 chambers. The imputed and recorded + forecast units are not comparable. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to perform preventive maintenance on network transformers to maintain a safe and reliable distribution network system.
233 | Expense | Electric Distribution | KC | E Dist Maint Network | KCD | Ntwk Xfmr PrevMaint/Retst NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | No | N/A | N/A | 2808.6851 | 2877.8214 | 5686.5065 | 4486.7169 | 4056.2771 | 8542.994 | 1178.4557 | 2856.4875 | 40.95% | 50.23% | N/A | N/A | # Transformers | 3600 | 3600 | 7200 | 1363 | 1403 | 2766 | -2197 | -4434 | -61.03% | -61.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
234 | Expense | Electric Distribution | KC | E Dist Maint Network | KCE | Ntwk Protector Prev Maint NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 718.8591 | 736.5539 | 1455.413 | 1428.0841 | 1615.0506 | 3043.1347 | 878.4967 | 1587.7217 | 119.3% | 109.1% | NO | NO | Network Protectors | 402 | 402 | 804 | 374 | 474 | 848 | 72 | 44 | 17.91% | 5.473% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
235 | Expense | Electric Distribution | KC | E Dist Maint Network | KCE | Ntwk Protector Prev Maint NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | No | N/A | N/A | 718.8591 | 736.5539 | 1455.413 | 1428.0841 | 1615.0506 | 3043.1347 | 878.4967 | 1587.7217 | 119.3% | 109.1% | N/A | N/A | # network protectors | 402 | 402 | 804 | 374 | 474 | 848 | 72 | 44 | 17.91% | 5.473% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
236 | Expense | Electric Distribution | KC | E Dist Maint Network | KCF | Fiber/SCADA Comm Repr NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 1011.5374 | 1036.4366 | 2047.974 | 185.5123 | 1184.3166 | 1369.8289 | 147.88 | -678.1451 | 14.27% | -33.11% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
237 | Expense | Electric Distribution | KC | E Dist Maint Network | KCF | Fiber/SCADA Comm Repr NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | No | N/A | N/A | 1011.5374 | 1036.4366 | 2047.974 | 185.5123 | 1184.3166 | 1369.8289 | 147.88 | -678.1451 | 14.27% | -33.11% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
238 | Expense | Electric Distribution | OM | Operational Management | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 22 | No | On-going | Annual | 19950.3775 | 20477.3794 | 40427.757 | 12752.99 | 20920.0181 | 33673.0081 | 442.6387 | -6754.7488 | 2.162% | -16.71% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
239 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFC | Cameras | SRM Total | SRM Total | Ex 4, Ch 4.1 | No | On-going | Annual | 0 | 0 | 0 | 12340.4302 | 11018.4514 | 23358.8816 | 11018.4514 | 23358.8816 | 100% | 100% | YES | YES | # of wildfire cameras | 0 | 0 | 0 | 10 | 25 | 35 | 25 | 35 | 100% | 100% | YES | Program expenses exceeded imputed regulatory values because costs for this program were imputed in MAT AB6. Actual expenses for cameras recorded in MAT WFC are within the variance threshold, although they exceeded imputed regulatory values due to 1) the implementation of artificial intelligence (AI) detection on the cameras which was not forecast in the 2023 GRC, and 2) the installation of more units than forecasted. See mitigation WLDFR-M07D in AB6 for the imputed amount for this program. | Actual units were higher than imputed units because 1) wildfire cameras were forecasted in AB6 and recorded in WFC, and 2) PG&E installed more units than forecasted. There were 10 cameras forecasted in AB6 and 25 completed in WFC in 2024. PG&E completed more units than forecasted because the wildfire risk team, working with CAL FIRE, identified numerous locations where additional cameras would reduce overall risk through enhanced situational awareness. See mitigation WLDFR-M07D in AB6 for the imputed units for this program. | Over | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. This program supports the installation, operation and maintenance of wildfire cameras. Scope and Budget forecast status are shown as over because for the remainder of the GRC cycle, costs and units will show over for MAT WFC because imputed amounts are captured in AB6. This program is otherwise proceeding as planned.
240 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFC | Cameras | Wildfire | WLDFR-M07D: Situational Awareness and Forecasting Initiatives - Cameras | Ex 4, Ch 4.1 | No | N/A | N/A | 0 | 0 | 0 | 12340.4302 | 11018.4514 | 23358.8816 | 11018.4514 | 23358.8816 | 100% | 100% | N/A | N/A | # of wildfire cameras | 0 | 0 | 0 | 10 | 25 | 35 | 25 | 35 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
241 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | SRM Total | SRM Total | Ex 4, Ch 4.1 Ex 4, Ch 5 | No | On-going | Annual | 0 | 0 | 0 | 8309.7448 | 9432.6035 | 17742.3483 | 9432.6035 | 17742.3483 | 100% | 100% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values because costs for this program were imputed in MAT AB6. Actual expenses for Other Wildfire Support are recorded in MAT WFM, and the difference between the imputed regulatory value and actual expenses is below the variance threshold. See mitigation EPNDR-C001, WLDFR-M07E, WLDFR-M071, WLDFR-M07J and WLDFR-M07K in AB6 for the imputed amount for this program. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. This program supports PG&E's development operations, and maintenance of the fire potential index and other models that support PSPS, EPSS, and wildfire mitigations. Budget status is shown as over because imputed amounts are captured in AB6. This program is otherwise proceeding as planned.
242 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | Emergency Preparedness & Response | EPNDR-C001: Situational Awareness and Forecasting Initiatives - SOPP Improvements | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 1880.6446 | 0 | 1880.6446 | 0 | 1880.6446 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
243 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | Wildfire | WLDFR-M07E: Situational Awareness and Forecasting Initiatives - Satellite Fire Detection | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 89.732 | 187.3436 | 277.0756 | 187.3436 | 277.0756 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
244 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | Wildfire | WLDFR-M07I: Situational Awareness and Forecasting Initiatives - Advanced Fire Modeling | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 6044.7454 | 6996.5688 | 13041.3143 | 6996.5688 | 13041.3143 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
245 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | Wildfire | WLDFR-M07J: Situational Awareness and Forecasting Initiatives - Meteorology | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 153.6489 | 2139.0933 | 2292.7423 | 2139.0933 | 2292.7423 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
246 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | Wildfire | WLDFR-M07K: Situational Awareness and Forecasting Initiatives - Fire Potential Index | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 140.9738 | 109.5977 | 250.5715 | 109.5977 | 250.5715 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
247 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
248 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFN | PSPS Non-Event Expense | SRM Total | SRM Total | Ex 4, Ch 4.2 | No | On-going | Annual | 0 | 0 | 0 | 19942.8022 | 28489.808 | 48432.6101 | 28489.808 | 48432.6101 | 100% | 100% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values because costs for this program were imputed in MAT AB6 and imputed and recorded to MAT IG#. When comparing to MAT AB6, and IG#, PSPS non-event actual expenses were below forecast due to: 1) lower than forecast costs for exclusive use helicopter contracts, and 2) lower than forecast costs for Community Resource Center (CRC) preparedness. See mitigation WLDFR-M006 in AB6 and IG# for the imputed amount for this program as well as some recorded amounts. The underspend in PSPS was offset by additional spend in Non-RAMP work in this program. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to prepare for PSPS events and improve the PSPS program when activated. Budget status is shown as over, even though actual expenses were under, because there are no imputed amounts in WFN, they are in AB6 and IG#. This program is otherwise proceeding as planned.
249 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFN | PSPS Non-Event Expense | Emergency Preparedness & Response | EPNDR-C005: EP&R Field Operations | Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 203.512 | 0 | 203.512 | 0 | 203.512 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
250 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFN | PSPS Non-Event Expense | Emergency Preparedness & Response | EPNDR-C006: EP&R Distribution Support Headcount | Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 1525.7864 | 6861.7804 | 8387.5668 | 6861.7804 | 8387.5668 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
251 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFN | PSPS Non-Event Expense | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 4.2 | Yes | N/A | N/A | 0 | 0 | 0 | 16155.7024 | 19661.0999 | 35816.8023 | 19661.0999 | 35816.8023 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
252 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFN | PSPS Non-Event Expense | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.2 | Yes | N/A | N/A | 0 | 0 | 0 | 2057.8014 | 1966.9277 | 4024.729 | 1966.9277 | 4024.729 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
253 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFP | PSPS Event Expense | SRM Total | SRM Total | Ex 4, Ch 4.2 | No | On-going | Annual | 0 | 0 | 0 | 5556.1937 | 24510.8988 | 30067.0925 | 24510.8988 | 30067.0925 | 100% | 100% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values because costs for this program were imputed in MAT AB6. Actual expenses for active PSPS events are recorded in MAT WFP and were below imputed regulatory values in AB6 because PSPS events that occurred in 2024 were small in geographic scope and impacted fewer customers. See mitigation WLDFR-M005 in AB6 for the imputed amount for this program. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. This program supports PSPS and the spend is dependent on weather. This programs budget is presented as over, even though the actuals were under, because there were no imputed amounts in WFP, they were in AB6.
254 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFP | PSPS Event Expense | Wildfire | WLDFR-M005: Public Safety Power Shutoff - PSPS Event (Distribution) | Ex 4, Ch 4.2 | Yes | N/A | N/A | 0 | 0 | 0 | 5455.4428 | 23955.7118 | 29411.1546 | 23955.7118 | 29411.1546 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
255 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFP | PSPS Event Expense | Wildfire | POST-GRC: Post-GRC Mitigation | Ex 4, Ch 4.2 | Yes | N/A | N/A | 0 | 0 | 0 | 100.7509 | 555.187 | 655.9379 | 555.187 | 655.9379 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
256 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFS | Safety Infra Protect Team(SIPT) | SRM Total | SRM Total | Ex 4, Ch 4.1 | No | On-going | Annual | 0 | 0 | 0 | 19869.7115 | 20667.55 | 40537.2614 | 20667.55 | 40537.2614 | 100% | 100% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values because costs for this program were imputed in MAT AB6. Actual expenses for SIPT are recorded in MAT WFS and were below imputed regulatory values due to: 1) staffing constraints causing labor costs to be lower than forecast, 2) equipment delivery delays, and 3) fewer catastrophic events requiring deployment of the SIPT. See mitigation WLDFR-M008 in AB6 for the imputed amount for this program. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing. This program supports PG&E crews performing work in high fire risk areas. This programs budget is presented as over, even though the actuals were under, because there were no imputed amounts in WFS, they were in AB6. This program is otherwise proceeding as planned.
257 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFS | Safety Infra Protect Team(SIPT) | Wildfire | WLDFR-M008: Safety and Infrastructure Protection Teams | Ex 4, Ch 4.1 | No | N/A | N/A | 0 | 0 | 0 | 19869.7115 | 20667.55 | 40537.2614 | 20667.55 | 40537.2614 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
258 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFW | Weather Station Maintenance | SRM Total | SRM Total | Ex 4, Ch 4.1 | No | On-going | Annual | 0 | 0 | 0 | 2468.4283 | 2914.8629 | 5383.2911 | 2914.8629 | 5383.2911 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing. This program is for the maintenance of weather stations. This programs budget is presented as over, because there were no imputed amounts in WFW, they were in AB6 for WLDFR-M07B. This program is otherwise proceeding as planned.
259 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFW | Weather Station Maintenance | Wildfire | WLDFR-M07B: Situational Awareness and Forecasting Initiatives - Weather Station | Ex 4, Ch 4.1 | No | N/A | N/A | 0 | 0 | 0 | 2468.4283 | 2914.8629 | 5383.2911 | 2914.8629 | 5383.2911 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
(a) | Program work for Cameras, PSPS, SIPT, Wildfire Mitigation Support, and Weather Station Maintenance were imputed in MAT code AB6 and recorded in MWC WF MAT codes, | [14 empty] | `

## Electric Non-SRM MAT Table Exp
Table 3-5 2024 RSAR 2023 GRC CYCLE ELECTRIC DISTRIBUTION NON-SRM EXPENSE COMPARISON BY MAT FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | C6 | C7 | D | E | F | G1 | G2 | H | I1 | I2 | J | K1 | K2 | L1 | L2
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name | MAT | MAT Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program / Project Life (years) | Program / Project Year | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs | Imputed Cost for 2023 GRC Cycle to Date ($) (G1+G2) | 2023 Actual Costs | 2024 Actual Costs | Actual Cost for 2023 GRC Cycle to Date ($) (I1+I2) | Difference for 2024 ($) (I2-G2) | Difference for 2023 GRC Cycle to Date ($) (J-H) | Spending Percent Variance for 2024 (%) (K1)/G2*100) | Spending Percent Variance for 2023 GRC Cycle (%) (K2/H*100)
1 | Expense | Electric Distribution | CY | Manage Electric Grid Ops | # | Not assigned | Non-SRM | Non-SRM | Ex 4, Ch 19 | No | On-going | Annual | 0 | 0 | 0 | 0 | 2018.7008 | 2018.7008 | 2018.7008 | 2018.7008 | 100% | 100%
2 | Expense | MWC Name | EV | Manage Service Inquiries | EVA | Service Inquiry | Non-SRM | Non-SRM | Ex 4, Ch 18 | No | On-going | Annual | 5004.1617 | 5192.1373 | 10196.299 | 4047.5463 | 3965.204 | 8012.7502 | -1226.9333 | -2183.5488 | -23.63% | -21.42%
3 | Expense | Electric Distribution | EV | Manage Service Inquiries | EVB | OK to Serve | Non-SRM | Non-SRM | Ex 4, Ch 18 | No | On-going | Annual | 8913.2243 | 9248.0393 | 18161.2637 | 8286.2355 | 9234.8263 | 17521.0618 | -13.213 | -640.2018 | -0.1429% | -3.525%
4 | Expense | Electric Distribution | EV | Manage Service Inquiries | # | Not assigned | Non-SRM | Non-SRM | Ex 4, Ch 18 | No | On-going | Annual | 0 | 0 | 0 | 112.6063 | 166.535 | 279.1413 | 166.535 | 279.1413 | 100% | 100%
5 | Expense | Electric Distribution | EW | E TD WRO | N/A | Not assigned | Non-SRM | Non-SRM | Ex 4, Ch 18 | No | On-going | Annual | 11537.9284 | 11970.6582 | 23508.5866 | 8414.3757 | 22013.9218 | 30428.2976 | 10043.2636 | 6919.711 | 83.9% | 29.43%
6 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | # | Not assigned | Non-SRM | Non-SRM | Ex 4, Ch 19 | No | On-going | Annual | 0 | 0 | 0 | 0 | 199.1674 | 199.1674 | 199.1674 | 199.1674 | 100% | 100%
7 | Expense | Electric Distribution | OS | Operational Support | N/A | Not assigned | Non-SRM | Non-SRM | Ex 4, Ch 22 | No | On-going | Annual | 62153.553 | 63851.7193 | 126005.2723 | 2903.899 | -11896.8444 | -8992.9455 | -75748.5638 | -134998.2178 | -118.6% | -107.1%

## Electric Total Table Expense
TABLE 3-1 2024 RSAR 2023 GRC CYCLE ELECTRIC DISTRIBUTION EXPENSE COMPARISON SUMMARY (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | D1 | D2 | D3 | E1 | E2 | E3 | F1 | F2 | G1 | G2
Line No | Type (O&M Expense or Capital) | Functional Area | Spending Category - MWC | MWC | Imputed Adopted Annual Cost |  | Imputed Cost for 2023 GRC Cycle to Date ($) (D1+D2) | Actual Annual Cost |  | Actual Cost for 2023 GRC Cycle to Date ($) (E1+E2) | Difference for 2024 ($) (E2-D2) | Difference for 2023 GRC Cycle to Date ($) (E3-D3) | Percent Variance for 2024 (%) ((E2-D2)/D2*100) | Percent Variance for 2023 GRC Cycle to Date (%) ((E3-D3)/D3*100)
[5 empty] | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs |  | 2023 Actual Costs | 2024 Actual Costs
1 | O&M Expense | Electric Distribution | Misc Expense | AB | 256409.7403 | 260195.5662 | 516605.3064 | 107875.4221 | 132136.5801 | 240012.0022 | -128058.986 | -276593.3042 | -49.22% | -53.54%
2 | O&M Expense | Electric Distribution | Read & Investigate Meters | AR | 10437.6496 | 10773.4238 | 21211.0734 | 9189.4821 | 9666.4487 | 18855.9309 | -1106.9751 | -2355.1426 | -10.28% | -11.1%
3 | O&M Expense | Electric Distribution | Research & Development | AT | 2185.0619 | 2210.4564 | 4395.5183 | 0 | 0 | 0 | -2210.4564 | -4395.5183 | -100% | -100%
4 | O&M Expense | Electric Distribution | E Dist Operate System | BA | 32067.8098 | 33048.2032 | 65116.0129 | 24383.0024 | 26164.4694 | 50547.4718 | -6883.7338 | -14568.5411 | -20.83% | -22.37%
5 | O&M Expense | Electric Distribution | E T&D Patrol/Insp | BF | 87153.5566 | 87278.8708 | 174432.4273 | 150040.6571 | 129531.3955 | 279572.0527 | 42252.5248 | 105139.6254 | 48.41% | 60.28%
6 | O&M Expense | Electric Distribution | E Dist Routine Emergency | BH | 193157.4894 | 197204.9399 | 390362.4293 | 119478.7682 | 137877.1335 | 257355.9017 | -59327.8064 | -133006.5275 | -30.08% | -34.07%
7 | O&M Expense | Electric Distribution | Maint Other Equip | BK | 1975.33 | 2019.5532 | 3994.8832 | 2001.292 | 2105.1163 | 4106.4083 | 85.563 | 111.525 | 4.237% | 2.792%
8 | O&M Expense | Electric Distribution | Manage Electric Grid Ops | CY | 0 | 0 | 0 | 0 | 2018.7008 | 2018.7008 | 2018.7008 | 2018.7008 | 100% | 100%
9 | O&M Expense | Electric Distribution | Provide Field Service | DD | 24314.6197 | 25147.1084 | 49461.7282 | 31780.9186 | 30027.9291 | 61808.8477 | 4880.8206 | 12347.1195 | 19.41% | 24.96%
10 | O&M Expense | Electric Distribution | Manage Service Inquiries | EV | 13917.386 | 14440.1766 | 28357.5627 | 12446.3882 | 13366.5653 | 25812.9534 | -1073.6113 | -2544.6092 | -7.435% | -8.973%
11 | O&M Expense | Electric Distribution | E TD WRO | EW | 11537.9284 | 11970.6582 | 23508.5866 | 8414.3757 | 22013.9218 | 30428.2976 | 10043.2636 | 6919.711 | 83.9% | 29.43%
12 | O&M Expense | Electric Distribution | Change/Maint Used Elec Meter | EY | 8478.8029 | 8499.0083 | 16977.8113 | 9001.3117 | 9684.3638 | 18685.6756 | 1185.3555 | 1707.8643 | 13.95% | 10.06%
13 | O&M Expense | Electric Distribution | E Dist Planning & Ops Engineer | FZ | 25831.8516 | 26585.2516 | 52417.1031 | 24276.0465 | 25783.8925 | 50059.9391 | -801.359 | -2357.1641 | -3.014% | -4.497%
14 | O&M Expense | Electric Distribution | E T&D Maint OH Poles | GA | 44147.5318 | 43916.7018 | 88064.2337 | 49974.7759 | 27271.2854 | 77246.0613 | -16645.4165 | -10818.1724 | -37.9% | -12.28%
15 | O&M Expense | Electric Distribution | E Dist Subst O&M | GC | 54755.0823 | 55488.6879 | 110243.7702 | 50107.8896 | 49083.0357 | 99190.9253 | -6405.6522 | -11052.8449 | -11.54% | -10.03%
16 | O&M Expense | Electric Distribution | E Dist Mapping | GE | 19272.2306 | 19284.6971 | 38556.9277 | 24668.3532 | 29589.4787 | 54257.8319 | 10304.7816 | 15700.9042 | 53.44% | 40.72%
17 | O&M Expense | Electric Distribution | Elec Trans Ops Engr & Tech | HG | 23207.3085 | 23113.8216 | 46321.1301 | 18540.4916 | 23009.0005 | 41549.4922 | -104.8211 | -4771.638 | -0.4535% | -10.3%
18 | O&M Expense | Electric Distribution | E Dist Tree Trim Bal Acct | HN | 972012.9814 | 965868.48 | 1937881.4615 | 859187.0852 | 1002998.7474 | 1862185.8327 | 37130.2674 | -75695.6288 | 3.844% | -3.906%
19 | O&M Expense | Electric Distribution | E T&D Automation & Protection | HX | 3118.3174 | 3184 | 6302.3175 | 2693.8379 | 1990.0543 | 4683.8922 | -1193.9457 | -1618.4252 | -37.5% | -25.68%
20 | O&M Expense | Electric Distribution | Change/Maint Used Gas Meters | HY | 687.1 | 710.3007 | 1397.4007 | 250.6 | 289.4958 | 540.0958 | -420.8049 | -857.3049 | -59.24% | -61.35%
21 | O&M Expense | Electric Distribution | E Dist Major Emergency | IF | 45380.7998 | 45908.2092 | 91289.009 | 38356.8805 | 214333.8032 | 252690.6837 | 168425.594 | 161401.6747 | 366.9% | 176.8%
22 | O&M Expense | Electric Distribution | Manage Var Bal Acct Processes | IG | 286594.6376 | 286066.7288 | 572661.3664 | 430012.4441 | 399067.8925 | 829080.3366 | 113001.1637 | 256418.9702 | 39.5% | 44.78%
23 | O&M Expense | Electric Distribution | Bill Customers | IS | 1830.672 | 1819.0996 | 3649.7716 | 572.5527 | 672.9663 | 1245.5189 | -1146.1333 | -2404.2527 | -63.01% | -65.87%
24 | O&M Expense | Electric Distribution | Collect Revenue | IU | 1589.8684 | 1659.8259 | 3249.6943 | 1088.0359 | 1274.3272 | 2362.3631 | -385.4988 | -887.3313 | -23.23% | -27.31%
25 | O&M Expense | Electric Distribution | Maintain IT Apps & Infra | JV | 8419.0283 | 8471.7026 | 16890.7308 | 4430.1601 | 4715.7107 | 9145.8708 | -3755.9919 | -7744.86 | -44.34% | -45.85%
26 | O&M Expense | Electric Distribution | E Dist Maint OH General | KA | 40243.1359 | 40332.9697 | 80576.1056 | 89175.9346 | 161232.235 | 250408.1696 | 120899.2653 | 169832.064 | 299.8% | 210.8%
27 | O&M Expense | Electric Distribution | E Dist Maint UG | KB | 20324.6507 | 20485.0343 | 40809.685 | 16071.0714 | 19371.6099 | 35442.6813 | -1113.4245 | -5367.0037 | -5.435% | -13.15%
28 | O&M Expense | Electric Distribution | E Dist Maint Network | KC | 5157.3004 | 5284.2483 | 10441.5487 | 6152.7683 | 7504.3632 | 13657.1315 | 2220.1149 | 3215.5828 | 42.01% | 30.8%
29 | O&M Expense | Electric Distribution | Operational Management | OM | 19950.3775 | 20477.3794 | 40427.757 | 12752.99 | 20920.0181 | 33673.0081 | 442.6387 | -6754.7488 | 2.162% | -16.71%
30 | O&M Expense | Electric Distribution | Operational Support | OS | 62153.553 | 63851.7193 | 126005.2723 | 2903.899 | -11896.8444 | -8992.9455 | -75748.5638 | -134998.2178 | -118.6% | -107.1%
31 | O&M Expense | Electric Distribution | Wildfire Mitigation | WF | 0 | 0 | 0 | 68487.3106 | 97034.1744 | 165521.485 | 97034.1744 | 165521.485 | 100% | 100%
32 | O&M Expense | Electric Distribution | TOTAL |  | 2276311.8018 | 2285296.823 | 4561608.6249 | 2174314.7453 | 2588837.8709 | 4763152.6162 | 303541.0479 | 201543.9914 | 13.28% | 4.418%

## Q6 Analysis Result
This data was created by pivoting the Electric MAT Table Expense: It is a copy of the data in Q6 Expense Pivot tab | [6 empty] | % Variance Calculations |  | Comparison to Electric Total Table Expense
MWC Row Labels | Sum of 2024 Imputed Adopted Costs | Sum of Imputed Cost for 2023 GRC Cycle to Date ($) | Sum of 2024 Actual Costs | Sum of Actual Cost for 2023 GRC Cycle to Date ($) | Sum of Difference for 2024 ($) | Sum of Difference for 2023 GRC Cycle to Date ($) | Sum of Spending Percent Variance for 2024 (%) | Sum of Spending Percent Variance for 2023 GRC Cycle (%) | 2024 Imputed | GRC Cycle Imputed | 2024 Actual | GRC Cycle Actual | 2024 Difference | GRC Cycle Difference | 2024 % variance | GRC Cycle % variance
AB | 260195.5662 | 516605.3064 | 132136.5801 | 240012.0022 | -128058.986 | -276593.3042 | -49.22% | -53.54% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
AR | 10773.4238 | 21211.0734 | 9666.4487 | 18855.9309 | -1106.9751 | -2355.1426 | -10.28% | -11.1% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
AT | 2210.4564 | 4395.5183 | 0 | 0 | -2210.4564 | -4395.5183 | -100% | -100% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
BA | 33048.2032 | 65116.0129 | 26164.4694 | 50547.4718 | -6883.7338 | -14568.5411 | -20.83% | -22.37% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
BF | 87278.8708 | 174432.4273 | 129531.3955 | 279572.0527 | 42252.5248 | 105139.6254 | 48.41% | 60.28% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
BH | 197204.9399 | 390362.4293 | 137877.1335 | 257355.9017 | -59327.8064 | -133006.5275 | -30.08% | -34.07% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
BK | 2019.5532 | 3994.8832 | 2105.1163 | 4106.4083 | 85.563 | 111.525 | 4.237% | 2.792% | 0 | 0 | 0 | 0 | 0 | -5.6843e-13 | 0% | -1.422e-14%
DD | 25147.1084 | 49461.7282 | 30027.9291 | 61808.8477 | 4880.8206 | 12347.1195 | 19.41% | 24.96% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
EY | 8499.0083 | 16977.8113 | 9684.3638 | 18685.6756 | 1185.3555 | 1707.8643 | 13.95% | 10.06% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
FZ | 26585.2516 | 52417.1031 | 25783.8925 | 50059.9391 | -801.359 | -2357.1641 | -3.014% | -4.497% | 0 | 0 | 0 | 0 | 0 | -4.5475e-12 | 0% | -9.021e-15%
GA | 43916.7018 | 88064.2337 | 27271.2854 | 77246.0613 | -16645.4165 | -10818.1724 | -37.9% | -12.28% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
GC | 55488.6879 | 110243.7702 | 49083.0357 | 99190.9253 | -6405.6522 | -11052.8449 | -11.54% | -10.03% | 0 | 0 | 0 | 0 | -2.2737e-11 | 0 | -4.025e-14% | 0%
GE | 19284.6971 | 38556.9277 | 29589.4787 | 54257.8319 | 10304.7816 | 15700.9042 | 53.44% | 40.72% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
HG | 23113.8216 | 46321.1301 | 23009.0005 | 41549.4922 | -104.8211 | -4771.638 | -0.4535% | -10.3% | 0 | 0 | 0 | 0 | -4.5475e-13 | 0 | -1.995e-15% | 0%
HN | 965868.48 | 1937881.4615 | 1002998.7474 | 1862185.8327 | 37130.2674 | -75695.6288 | 3.844% | -3.906% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
HX | 3184 | 6302.3175 | 1990.0543 | 4683.8922 | -1193.9457 | -1618.4252 | -37.5% | -25.68% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
HY | 710.3007 | 1397.4007 | 289.4958 | 540.0958 | -420.8049 | -857.3049 | -59.24% | -61.35% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
IF | 45908.2092 | 91289.009 | 214333.8032 | 252690.6837 | 168425.594 | 161401.6747 | 366.9% | 176.8% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
IG* | 286066.7288 | 572661.3664 | 399067.8925 | 829080.3366 | 113001.1637 | 256418.9702 | 39.5% | 44.78% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
IS | 1819.0996 | 3649.7716 | 672.9663 | 1245.5189 | -1146.1333 | -2404.2527 | -63.01% | -65.87% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
IU | 1659.8259 | 3249.6943 | 1274.3272 | 2362.3631 | -385.4988 | -887.3313 | -23.23% | -27.31% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
JV | 8471.7026 | 16890.7308 | 4715.7107 | 9145.8708 | -3755.9919 | -7744.86 | -44.34% | -45.85% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
KA | 40332.9697 | 80576.1056 | 161232.235 | 250408.1696 | 120899.2653 | 169832.064 | 299.8% | 210.8% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
KB | 20485.0343 | 40809.685 | 19371.6099 | 35442.6813 | -1113.4245 | -5367.0038 | -5.435% | -13.15% | 0 | 0 | 0 | 0 | 0 | -8.1855e-12 | 0% | 0%
KC | 5284.2483 | 10441.5487 | 7504.3632 | 13657.1315 | 2220.1149 | 3215.5828 | 42.01% | 30.8% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
OM | 20477.3794 | 40427.757 | 20920.0181 | 33673.0081 | 442.6387 | -6754.7488 | 2.162% | -16.71% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
WF | 0 | 0 | 97034.1744 | 165521.485 | 97034.1744 | 165521.485 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
* Note that PG&E needed to add the non-SRM amount from the Electric Non-SRM MAT Table Expense. Therefore the data highlighted in green does not match the data for MWC IG from the "Q6 Expense Pivot" tab.