## SAMPLE WorkPlan_BudgetTable
Clean Energy Access: Los Angeles County TECH Grant Work Plan + Budget Table
Detailed Work Plan | [6 empty] | Detailed Budget Request
Task Number | Activities to Accomplish Stated Goals | Project Staff Involved | Start Date | End Date | Performance Measures (used to measure goals) | Expected Outcomes (The outcomes you get when accomplishing your goals) | Budget Item | Detailed Explanation / Justification | Rate | Unit | Number of Units | Cost
Goal 1 | Build Staff Knowledge of building decarbonization, healthy homes, and TECH |  |  |  |  | Community members can consult qualified outreach staff, able to provide detailed explanations of building decarbonization, healthy homes, and TECH Initiative rules, processses, and benefits.
Task 1.1 | Draft Scope of Work | Ben Kinney, Executive Director | 2026-01-01 | 2026-01-15 | Scope of work completed on time | 2 qualified outreach assistants hired and prepared to conduct outreach and education | Gordon Wu, Executive Director | 5 hours/week x 50 weeks @ $30/hour | 30 | hour | 250 | 7500
| Interviews for outreach assistants | Ben Kinney, Executive Director; Concepcion Rui, Chair of the Board | 2026-01-18 | 2026-01-31 | Number of interviews held |  | Miriam Hernandez, Policy Director | 25 hours/week x 2 weeks @ $20 hour | 20 | hour | 50 | 1000
Task 1.2 | Hire 2 outreach assistants | Ben Kinney, Executive Director; Concepcion Rui, Chair of the Board | 2026-02-01 | 2026-02-15 | Number of Outreach Assistants Hired and Trained by End of March |  | Penelope Marbella, HR Director | 6 hours/week x 6 weeks @ $25/hour | 25 | hour | 36 | 900
| Training 2 new outreach assistants | Anny Adams, Outreach Manager; Adalie Amarro, Outreach Associate; 2 new outreach assistants | 2026-02-15 | 2026-03-31 | Hours of training |  | George Williams, Organizing Director | 8 hours/week x 20 weeks @ $17.00/hour | 17 | hour | 180 | 3060
Task 1.3 | In-depth staff research on building decarbonization, healthy homes, heat pumps, and TECH | Anny Adams, Outreach Manager; Adalie Amarro, Outreach Associate; 2 new outreach assistants | 2026-01-01 | 2026-03-07 | Summary report from staff | Staff become knowledgeable about TECH and identify relevant topics for community and topics in need of clarification | Travel Stipends | Mileage for trainees to travel to and from training workshops. | 0.75 | mile | 500 | 375
| Meet with Energy Solutions staff | Anny Adams, Outreach Manager; Adalie Amarro, Outreach Associate; 2 new outreach assistants | 2026-03-07 | 2026-03-14 | Meeting held with Energy Solutions | Staff knowledge gaps filled | Printed surveys | Surveys to gather feedback and data from participants | 1 | participant | 20 | 20
Goal 2 | Create, Conduct, and Evaluate Educational Workshop Series | Darla Ramirez, Organizing Director |  |  | Trained 5 organizers to educate the community on active proceedings | The community will become aware and educated on the High DER proceeding and will provide input on the impacts of the proposed regulations.
Task 2.1 | Secure venues for educational workshops | Anny Adams, Outreach Manager | 2026-03-14 | 2026-03-31 |  |  | Sam Cachu, Senior Community Organizer | 25 hours/week x 50 weeks @ $18 hour | 18 | hour | 1250 | 22500
| Continuous review and updates of workshop materials and structure | Adalie Amarro, Outreach Associate; Outreach Assisant #1 | 2026-05-15 | 2026-08-15 |  |  | Miriam Hernandez, Policy Director | 15 hours/week x 2 weeks @ $20 hour | 20 | hour | 30 | 600
Task 2.2 | Create marketing materials (flyers, registration pages, etc) | Adalie Amarro, Outreach Associate; Outreach Assisant #1 | 2026-04-15 | 2026-04-23 |  |  | Graham Singer, Graphic Designer | 3 hours/week x 1 week @ $50/hour | 50 | hour | 3 | 150
| Create educational presentations and followup surveys | Adalie Amarro, Outreach Associate; Outreach Assisant #1 | 2026-04-01 | 2026-04-30 |  |  | Outreach Mailers / Postcards | Community outreach and engagement materials | 0.75 | cards | 500 | 375
Task 2.3 | Market educational workshops | Adalie Amarro, Outreach Associate; Outreach Assisant #1 | 2026-04-23 | 2026-08-01 |  |  | Food and drinks and incidentals | Participant incentive for participation and engagement | 10 | participant | 100 | 1000
| Hold 6 educational workshops | Anny Adams, Outreach Manager; Adalie Amarro, Outreach Associate; Outreach Assistant #1 | 2026-05-15 | 2026-08-15 |  |  | Consultant: Melanie Harris, Trainer | 8 hours/week x 1 week @ $20/hour | 40 | hour | 10 | 400
Goal 3 | Evaluate and Report out on Door-to-Door Outreach
Task 3.1 | Conduct 3-month followup surveys | Adalie Amarro, Outreach Associate; Outreach Assisant #1 | 2026-08-15 | 2026-08-30 |  |  | Sam Cachu, Senior Community Organizer | 25 hours/week x 50 weeks @ $18 hour | 18 | hour | 1250 | 22500
Task 3.2 | Conduct 6-month followup surveys | Adalie Amarro, Outreach Associate; Outreach Assisant #1 | 2027-04-15 | 2027-04-30 |  |  | Sam Cachu, Senior Community Organizer | 25 hours/week x 50 weeks @ $18 hour | 18 | hour | 1250 | 22500
Task 3.3 | Write summary report analyzing workshop series success and survey data | Anny Adams, Outreach Manager; Adalie Amarro, Outreach Associate; Outreach Assistant #1 | 2026-08-15 | 2027-05-01 |  |  | Gordon Wu, Executive Director | 5 hours/week x 50 weeks @ $30/hour | 30 | hour | 250 | 7500
[10 empty] | TOTAL BUDGET |  | 90380

## WorkPlan_BudgetTable_Blank
Clean Energy Access: Los Angeles County TECH Grant Work Plan + Budget Table
Detailed Work Plan | [6 empty] | Detailed Budget Request
Task Number | Activities to Accomplish Stated Goals | Project Staff Involved | Start Date | End Date | Performance Measures (used to measure goals) | Expected Outcomes (The outcomes you get when accomplishing your goals) | Budget Item | Detailed Explanation / Justification | Rate | Unit | Number of Units | Cost
Goal 1
Task 1.1 | [11 empty] | 0
0
0
0
Task 1.2 | [11 empty] | 0
0
0
Task 1.3 | [11 empty] | 0
0
Goal 2
Task 2.1 | [11 empty] | 0
0
Task 2.2 | [11 empty] | 0
0
Task 2.3 | [11 empty] | 0
Goal 3
Task 3.1 | [11 empty] | 0
0
Task 3.2 | [11 empty] | 0
0
Task 3.3 | [11 empty] | 0
[10 empty] | TOTAL BUDGET |  | 0