## F1 - Table 2
Location # | Site ID | Audit Findings | T-Mobile Response
28 | BA01347A | Incomplete pole transfer. | T-Mobile will reach out to PG&E regarding new pole that was installed by PG&E that is not tall enough to transfer and have proper separations between antenna, comm lines and power lines.
34 | BA22482B (inadvertently refereced as BA22582B in the Audit Report) | Incomplete pole transfer. | T-Mobile will reach out to PG&E regarding new pole that was installed by PG&E that is not tall enough to transfer and have proper separations between antenna, comm lines and power lines.
38 | BA02153A | Incomplete pole transfer. | T-Mobile will reach out to PG&E regarding new pole that was installed by PG&E that is not tall enough to transfer and have proper separations between antenna, comm lines and power lines.

## F2 - Table 3
Location # | Site ID | Audit Findings | T-Mobile Response
3 | BA01373A | The pole has a missing lock on the disconnect switch. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
17 | BA01314A (referred to as BA01354A in the Audit Report) | The pole has a missing lock on the disconnect switch. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
17 | BA01314A (referred to as BA01354A in the Audit Report) | Ground wire on pole mounted metallic box is not connected. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
19 | BA21694A | Pole mounted disconnect lid is damaged and not secured. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
21 | BA22904B | Pole mounted disconnect lid is damaged and not secured. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
24 | BA52576B | The pole has a missing lock on the disconnect switch. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
26 | BA52638C | The pole has a missing lock on the disconnect switch. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
31 | BA02099A | Pole mounted disconnect lid is damaged and not secured. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
32 | BA12847A | The pole has a missing lock on the disconnect switch. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
33 | BA52597A | Pole mounted disconnect lid is damaged and not secured. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
34 | BA22482B (referred to as BA22582B in the Audit Report) | The pole has a missing lock on the disconnect switch. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
35 | BA22521F (referred to as BA22521A in the Audit Report) | The pole has a missing lock on the disconnect switch. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
36 | BA02066A | There is an abandoned ground wire and plate at the base of the pole | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
39 | BA42623A | Ground wire on pole mounted metallic box is damaged | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
40 | BA42624A | The pole has a missing lock on the disconnect switch. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
44 | BA90345A | Pole mounted disconnect lid is damaged and not secured. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.

## F3 -Table 4
Location # | Site ID | Audit Findings | T-Mobile Response
44 | BA90345A | The ground cover is damaged, exposing the ground wire. | T-Mobile has designated this as a Priority Level 2 item and will remediate accordingly.

## F4 - Table 5
Location # | Site ID | Audit Findings | T-Mobile Response
5 | BA02127A | The riser is exposed near the base of the pole. | T-Mobile has designated this as a Priority Level 2 item and will remediate accordingly.
35 | BA22521F (referred to as BA22521A in the Audit Report) | The riser guard is below 8 feet. | T-Mobile has designated this as a Priority Level 2 item and will remediate accordingly.
36 | BA02066A | The riser is missing a suitable covering. | T-Mobile has designated this as a Priority Level 2 item and will remediate accordingly.
36 | BA02066A | The riser is exposed near the base of the pole | T-Mobile has designated this as a Priority Level 2 item and will remediate accordingly.

## F5 - Table 6
Location # | Site ID | Audit Findings | T-Mobile Response
3 | BA01373A | The pole is missing its operator label. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
4 | BA02127A | The equipment is missing its operator label. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
29 | BA02374A | The pole is missing its unique identifier. | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.
44 | BA90345A | The pole is missing its unique identifier | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.

## F6 - Table 7
Location # | Site ID | Audit Findings | T-Mobile Response
7 | BA02717A | The required signage is below 9 feet | T-Mobile has designated this as a Priority Level 3 item and will remediate accordingly.

## F7 - Table 8
Location # | Site ID | Audit Findings | T-Mobile Response
6 | BA02057A (referred to as BA0257A in the Audit Report) | External ground has been cut. | T-Mobile has designated this as a Priority Level 2 item and will remediate accordingly.

## O1 - Table 9
Location # | Site ID | Utility | Audit Findings | T-Mobile Response
3 | BA01373A | AT&T | Communication wire on T-Mobile antenna. | T-Mobile sent a notice on August 20, 2025, to AT&T re the staff's determination that this constitutes a Safety Hazard per GO 95.
5 | BA02127A | PG&E | Pole is leaning over 10 percent. | T-Mobile sent a notice on August 20, 2025, to PG&E re the staff's determination that this constitutes a Safety Hazard per GO 95.
7 | BA02162A (referred to as BA02717A in the Audit Report) | AT&T | Riser guard lower than 8 feet. | T-Mobile sent a notice on August 20, 2025, to AT&T re the staff's determination that this constitutes a Safety Hazard per GO 95.
8 | BA02162A (referred to as BA02717A in the Audit Report) | AT&T | Uncovered cables attached to T-Mobile equipment. | T-Mobile sent a notice on August 20, 2025, to AT&T re the staff's determination that this constitutes a Safety Hazard per GO 95.
9 | BA02087A | AT&T | Uncovered riser cables. | T-Mobile sent a notice on August 20, 2025, to AT&T re the staff's determination that this constitutes a Safety Hazard per GO 95.
11 | BA01228A | AT&T | Uncovered riser cables. | T-Mobile sent a notice on August 20, 2025, to AT&T re the staff's determination that this constitutes a Safety Hazard per GO 95.
12 | BA01361A | Unknown | Slack down guy. | Neither T-Mobile nor the staff were able to identify the owner of the subject facility which was unmarked. Thus, consistent with GO 95, Rule 18.A(4), T-Mobile sent a notice on August 20, 2025, to both PG&E and AT&T re the staff's determination that this item constitutes a Safety Hazard under the General Order.
15 | BA01348A | AT&T | Low span over the road. | T-Mobile sent a notice on August 20, 2025, to AT&T re the staff's determination that this constitutes a Safety Hazard per GO 95.
17 | BA01314A (referred to as BA01354A in the Audit Report) | AT&T | Abandoned fiber hanging to ground. | T-Mobile sent a notice on August 20, 2025, to AT&T re the staff's determination that this constitutes a Safety Hazard per GO 95.
17 | BA01314A (referred to as BA01354A in the Audit Report) | PG&E | Exposed ground rod. | T-Mobile sent a notice on August 20, 2025, to PG&E re the staff's determination that this constitutes a Safety Hazard per GO 95.
19 | BA21694A | AT&T | Slack down guy. | T-Mobile sent a notice on August 20, 2025, to AT&T re the staff's determination that this constitutes a Safety Hazard per GO 95.
25 | BA42625A | PG&E | Loose messenger guy. | T-Mobile sent a notice on August 20, 2025, to PG&E re the staff's determination that this constitutes a Safety Hazard per GO 95.
28 | BA01347A | AT&T | Incomplete pole transfer. | T-Mobile sent a notice on August 20, 2025, to AT&T re the staff's determination that this constitutes a Safety Hazard per GO 95.
28 | BA01347A | Comcast | Incomplete pole transfer. | T-Mobile sent a notice on August 20, 2025, to Comcast re the staff's determination that this constitutes a Safety Hazard per GO 95
31 | BA02099A | AT&T | Wires contacting multiple down guys. | T-Mobile sent a notice on August 20, 2025, to AT&T re the staff's determination that this constitutes a Safety Hazard per GO 95.
31 | BA02099A | Comcast | Wire contacting down guy. | T-Mobile sent a notice on August 20, 2025, to Comcast re the staff's determination that this constitutes a Safety Hazard per GO 95
32 | BA12847A | Comcast | Wire contacting AT&T wire. | T-Mobile sent a notice on August 20, 2025, to Comcast re the staff's determination that this constitutes a Safety Hazard per GO 95
33 | BA52597A | PG&E | Supply service drop contacting communication wires. | T-Mobile sent a notice on August 20, 2025, to PG&E re the staff's determination that this constitutes a Safety Hazard per GO 95.
34 | BA22482B (referred to as BA22582B in the Audit Report) | AT&T | Incomplete pole transfer. | T-Mobile sent a notice on August 20, 2025, to AT&T re the staff's determination that this constitutes a Safety Hazard per GO 95.
38 | BA02153A | AT&T | Incomplete pole transfer. | T-Mobile sent a notice on August 20, 2025, to AT&T re the staff's determination that this constitutes a Safety Hazard per GO 95.
38 | BA02153A | Unknown | Incomplete pole transfer. | Neither T-Mobile nor the staff were able to identify the owner of the subject facility which was unmarked. Thus, consistent with GO 95, Rule 18.A(4), T-Mobile sent a notice on August 20, 2025, to both PG&E and AT&T re the staff's determination that this item constitutes a Safety Hazard under the General Order.
39 | BA42623A | PG&E | Low pole step. | T-Mobile sent a notice on August 20, 2025, to PG&E re the staff's determination that this constitutes a Safety Hazard per GO 95.
41 | BA01367A | PG&E | Pole leaning greater than 10 percent. | T-Mobile sent a notice on August 20, 2025, to PG&E re the staff's determination that this constitutes a Safety Hazard per GO 95.
44 | BA90345A | PG&E | Damage ground cover. | T-Mobile sent a notice on August 20, 2025, to PG&E re the staff's determination that this constitutes a Safety Hazard per GO 95.