## Kern County West
No. | Structure ID | Site | Structure Type | Location | Approximate GPS Coordinates | Address | Ticket Number | Violation | Priority Level | Affected Company | Due Date | Inspection Date | HF Tier | TKT Status | Assigned To | Frontier Response
1 | CRLNCAXF 1884601E |  | Pole | Crestline | 34.2481277, -117.2715006 |  | T-00489844 | Frontier down guy wire attached to each of the following poles was not taut, Abandoned service drops were observed |  |  |  | 2025-09-03 | TIER 3 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
2 | 1818939E |  | Pole | Crestline | [7 empty] | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
3 | 4421525E |  | Pole | Crestline | [7 empty] | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
4 | CRLNCAXF GT140867 |  | Pole | Crestline | 34.2491176, -117.2715293 |  | T-00489845 | Frontier down guy wire attached to each of the following poles was not taut |  |  |  | 2025-09-03 | TIER 3 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
5 | CRLNCAXF 1056803E |  | Pole | Crestline | 34.2495137, -117.2712747 |  | T-00489846 | Frontier’s service drop was in contact with an SCE’s secondary service drop, Frontier down guy wire attached to each of the following poles was not taut |  |  |  | 2025-09-03 | TIER 3 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
6 | 1056802E |  | Pole | Crestline | [7 empty] | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
7 | CRLNCAXF 2250603E |  | Pole | Crestline | 34.2488846, -117.2729252 |  | T-00489847 | The above ground clearance of a Frontier conductor attached to Pole 2250603E was approximately 14 feet over a public thoroughfare |  |  |  | 2025-09-03 | TIER 3 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
8 | 1009063E |  | Pole | Crestline | [7 empty] | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
9 | 1009064E |  | Pole | Crestline | [7 empty] | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
10 | 1261351E |  | Pole | Crestline | [7 empty] | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
11 | CRLNCAXF 1261352E |  | Pole | Crestline | 34.2501266, -117.2733791 |  | T-00489848 | Frontier communication conductor attached to each of the following poles was strained by vegetation: |  |  |  | 2025-09-03 | TIER 3 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
12 | CRLNCAXF 1261353E |  | Pole | Crestline | 34.2504759, -117.2733352 |  | T-00489849 | Abandoned service drops were observed |  |  |  | 2025-09-03 | TIER 3 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
13 | ARHDCAXF 405486E |  | Pole | Lake Arrowhead | 34.2362453, -117.177253 |  | T-00489850 | Frontier communication conductor attached to each of the following poles was strained by vegetation, Abandoned service drops were observed |  |  |  | 2025-09-03 | TIER 3 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
14 | ARHDCAXF 405487E |  | Pole | Lake Arrowhead | 34.236607, -117.1773941 |  | T-00489852 | Frontier communication conductor attached to each of the following poles was strained by vegetation: |  |  |  | 2025-09-03 | TIER 3 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
15 | ARHDCAXF 405488E |  | Pole | Lake Arrowhead | 34.2369574, -117.1775439 |  | T-00489851 | Frontier communication conductor attached to each of the following poles was strained by vegetation: |  |  |  | 2025-09-03 | TIER 3 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
16 | 405489E |  | Pole | Lake Arrowhead | 34.237281994578915, -117.17746504992124 |  | T-00489854 | Frontier communications conductor was in contact with a third-party communications conductor |  |  |  | 2025-09-03 | TIER 3 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
17 | 1589784E |  | Pole | Lake Arrowhead | [7 empty] | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
18 | 405490E |  | Pole | Lake Arrowhead | [7 empty] | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
19 | ARHDCAXF 1818829E |  | Pole | Lake Arrowhead | 34.2379714, -117.1778564 |  | T-00489855 | Frontier communication conductor attached to each of the following poles was strained by vegetation: The Frontier riser casing on pole 1818829E was missing |  |  |  | 2025-09-03 | TIER 3 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
20 | ARHDCAXF 4323899E |  | Pole | Lake Arrowhead | 34.2382386, -117.1782198 |  | T-00489856 | Frontier communication conductor attached to each of the following poles was strained by vegetation, • The above ground clearance of a Frontier conductor attached to Pole 4323899E was approximately 14 feet over a public thoroughfare. Frontier down guy wire attached to each of the following poles was not taut |  |  |  | 2025-09-03 | TIER 3 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
21 | 4323900E |  | Pole | Lake Arrowhead | 34.238629, -117.178453 | OAK RD E/S 1090' N/O SYCAMORE DR | T-00489853 | Frontier down guy wire attached to each of the following poles was not taut, Abandoned service drops were observed |  |  |  | 2025-09-03 | TIER 3 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
22 | GT107966 |  | Pole | Lake Arrowhead | [7 empty] | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
23 | ARHDCAXF 549381E |  | Pole | Lake Arrowhead | 34.2386374, -117.1785796 |  | T-00489857 | The above ground clearance of a Frontier conductor attached to Pole 549381E was approximately 14 feet over a public thoroughfare |  |  |  | 2025-09-03 | TIER 3 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
24 | 1854879E |  | Pole | Lake Arrowhead | [7 empty] | 2025-09-03
25 | 4027172E |  | Pole | Lake Arrowhead | [7 empty] | 2025-09-03
26 | MSCYCAXF 4450226E |  | Pole | Muscoy | 34.2229052, -117.400325 |  | T-00489858 | Frontier communications service drop on Pole 4450226E was in contact with a third-party communication service drop. The Frontier service drop attached to Pole 4450226E was strained by a tree branch |  |  |  | 2025-09-03 | TIER 2 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
27 | F15033Y | MSCYCAXF GT71155 | Pole | Muscoy | 34.2229897, -117.4006785 |  | T-00489859 | Abandoned service drops were observed |  |  |  | 2025-09-03 | TIER 2 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
28 | 2121459E |  | Pole | Muscoy | [7 empty] | 2025-09-03 |  |  | RANDY ORTEGA
29 | 18556 Arrowhead Blvd. |  | Pole | Muscoy | 34.22305065300694, -117.39933653051975 |  | T-00489861 | rope tied around the pole, lowest pole step on each of the following poles was located at a height less than eight feet |  |  |  | 2025-09-03 | TIER 2 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
30 | MSCYCAXF 1714955E |  | Pole | Muscoy | 34.2277929, -117.4045824 |  | T-00489860 | The marker (guard) on the down guy wire supporting each of the following poles was missing |  |  |  | 2025-09-03 | TIER 2 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
31 | MSCYCAXF 1714999E |  | Pole | Muscoy | 34.2277771, -117.4043166 |  | T-00489864 | Incomplete pole transfer |  |  |  | 2025-09-03 | TIER 2 | LOGGED | MICHELE TABER |  | CA POLE ADMIN
32 | 4631047E |  | Pole | Muscoy | 34.22747661086259, -117.40459016825132 |  | T-00489862 | Incomplete pole transfer |  |  |  | 2025-09-03 | TIER 2 | LOGGED | MICHELE TABER |  | CA POLE ADMIN
33 | 1714997E |  | Pole | Muscoy | [7 empty] | 2025-09-03 |  |  | RANDY ORTEGA
34 | 1714996E | MSCYCAXF 1714996E | Pole | Muscoy | 34.2265316, -117.4039194 |  | T-00356485 | The Frontier lashing wire supported on pole 1714996E was broken |  |  |  | 2025-09-03 | Toer 2 | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
35 | MSCYCAXF 1714995E |  | Pole | Muscoy | 34.2261772, -117.4038296 |  | T-00489863 | Incomplete pole transfer |  |  |  | 2025-09-03 | TIER 2 | LOGGED | MICHELE TABER |  | CA POLE ADMIN
36 | BBLKCAXF 37130.CIT |  | Pole | Big Bear Lake | 34.2320824, -116.9303057 |  | T-00489865 | communication span supported on pole attached to a thirdparty communication conductor via a rope |  |  |  | 2025-09-03 | TIER 2 | LOGGED | JARED HAWK |  | CON-CA-VICTORVILLE-SP
37 | BBLKCAXF 37131.CIT |  | Pole | Big Bear Lake | 34.2325167, -116.9300531 |  | T-00489866 | lashing wire broken, Frontier communications conductor was in contact with a third-party communications conductor |  |  |  | 2025-09-03 | TIER 2 | LOGGED | JARED HAWK |  | CON-CA-VICTORVILLE-SP
38 | BBLKCAXF 37129.CIT |  | Pole | Big Bear Lake | 34.2315656, -116.9300572 |  | T-00489867 | Frontier down guy wire attached to each of the following poles was not taut |  |  |  | 2025-09-03 | TIER 2 | LOGGED | JARED HAWK |  | CON-CA-VICTORVILLE-SP
39 | CIT37128 |  | Pole | Big Bear Lake | [7 empty] | 2025-09-03
40 | BBLKCAXF 7407.BV |  | Pole | Big Bear Lake | 34.2308738, -116.9303851 |  | T-00489868 | service drop was not properly secured to pole |  |  |  | 2025-09-03 | TIER 2 | LOGGED | JARED HAWK |  | CON-CA-VICTORVILLE-SP
41 | CIT37392 |  | Pole | Big Bear Lake | [7 empty] | 2025-09-03
42 | CIT37138 |  | Pole | Big Bear Lake | [7 empty] | 2025-09-03
43 | 12526BV |  | Pole | Big Bear Lake | [7 empty] | 2025-09-03
44 | CTC2211075 |  | Pole | Big Bear Lake | [7 empty] | 2025-09-03
45 | 12690BV |  | Pole | Big Bear Lake | 34.236909 -116.927345 | 34.236909 -116.927345 | T-00490092 | Incomplete pole transfer |  |  |  | 2025-09-03 | TIER 2 |  | MICHELE TABER |  | CA POLE ADMIN
46 | 12689BV |  | Pole | Big Bear Lake | [7 empty] | 2025-09-03
47 | 13840BV |  | Pole | Big Bear Lake | [7 empty] | 2025-09-03
48 | BV12211 |  | Pole | Big Bear Lake | [7 empty] | 2025-09-03
49 | 3717BV | BBLKCAXF 13840BV | Pole | Big Bear Lake | 34.2370509, -116.9274843 | 34.2370509, -116.9274843 | T-00490085 | Incomplete pole transfer |  |  |  | 2025-09-03 | TIER 2 |  | MICHELE TABER |  | CA POLE ADMIN
50 | 13845BV |  | Pole | Big Bear Lake | [7 empty] | 2025-09-03
51 | 4869057E |  | Pole | Running Springs | [7 empty] | 2025-09-03
52 | RNSPCAXF 1056841.E |  | Pole | Running Springs | 34.2056273, -117.1011455 |  | T-00489871 | Incomplete pole transfer |  |  |  | 2025-09-03 | TIER 3 | LOGGED | MICHELE TABER |  | CA POLE ADMIN
53 | RNSPCAXF 1056842.E |  | Pole | Running Springs | 34.2060014, -117.1010665 |  | T-00489870 | Abandoned service drops were observed |  |  |  | 2025-09-03 | TIER 3 | LOGGED | JARED HAWK |  | CON-CA-VICTORVILLE-SP
54 | 21266CIT |  | Pole | Running Springs | [7 empty] | 2025-09-03
55 | 4879008E |  | Pole | Running Springs | NEED COORDINATES |  | T-00492977 | Incomplete pole transfer |  |  |  | 2025-09-03 | GEN | LOGGED | MICHELE TABER |  | CA POLE ADMIN
56 | 988538E |  | Pole | Running Springs | [7 empty] | 2025-09-03
57 | 4558826E |  | Pole | Running Springs | [7 empty] | 2025-09-03
58 | 739386E |  | Pole | Running Springs | [7 empty] | 2025-09-03
59 | 739385E |  | Pole | Running Springs | [7 empty] | 2025-09-03
60 | 1384264E |  | Pole | Running Springs | [7 empty] | 2025-09-03
61 | 739384E |  | Pole | Running Springs | [7 empty] | 2025-09-03
62 | 4879009E |  | Pole | Running Springs | NEED COORDINATES |  | T-00492978 | Incomplete pole transfer |  |  |  | 2025-09-03 | GEN | LOGGED | MICHELE TABER |  | CA POLE ADMIN
63 | 739383E |  | Pole | Running Springs | [7 empty] | 2025-09-03
64 | 709873E |  | Pole | Running Springs | 34.2049222, -117.1008347 |  | T-00489869 | Abandoned service drops were observed |  |  |  | 2025-09-03 | TIER 3 | LOGGED | JARED HAWK |  | CON-CA-VICTORVILLE-SP
65 | 4983848E |  | Pole | Running Springs | [7 empty] | 2025-09-03
66 | 4603523E |  | Pole | San Bernardino | [7 empty] | 2025-09-03
67 | 103 E Ninth St. |  | Pole | San Bernardino | 34.115821022562734, -117.28495010399067 |  | T-00489876 | damaged visibility strip, The marker (guard) on the down guy wire supporting each of the following poles was missing, Frontier down guy wire attached to each of the following poles was not taut |  |  |  | 2025-09-03 | GEN | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
68 | 5036583E |  | Pole | San Bernardino | [7 empty] | 2025-09-03
69 | 4691105E |  | Pole | San Bernardino | 34.1157171, -117.2842654 |  | T-00489872 | Abandoned service drops were observed |  |  |  | 2025-09-03 | GEN | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
70 | GT206145 |  | Pole | San Bernardino | [7 empty] | 2025-09-03
71 | 4438199E |  | Pole | San Bernardino | [7 empty] | 2025-09-03
72 | 4542911E |  | Pole | San Bernardino | [7 empty] | 2025-09-03
73 | 2101654E |  | Pole | San Bernardino | [7 empty] | 2025-09-03
74 | 1480796E |  | Pole | San Bernardino | [7 empty] | 2025-09-03
75 | 215 E Ninth St. |  | Pole | San Bernardino | 34.115751100149566, -117.28232457700906 |  | T-00489875 | Abandoned service drops were observed |  |  |  | 2025-09-03 | GEN | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
76 | SNBRCAXK 2042510E |  | Pole | San Bernardino | 34.1156016, -117.2820248 |  | T-00489873 | The marker (guard) on the down guy wire supporting each of the following poles was missing, Frontier down guy wire attached to each of the following poles was not taut, Abandoned service drops were observed |  |  |  | 2025-09-03 | GEN | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
77 | 4986863E |  | Pole | San Bernardino | [7 empty] | 2025-09-03
78 | 2013561E |  | Pole | Redlands | [7 empty] | 2025-09-03
79 | 782443E |  | Pole | Redlands | [7 empty] | 2025-09-03
80 | 2013560E |  | Pole | Redlands | [7 empty] | 2025-09-03
81 | 2013559E |  | Pole | Redlands | [7 empty] | 2025-09-03
82 | 4407979E |  | Pole | Redlands | [7 empty] | 2025-09-03
83 | 2013558E |  | Pole | Redlands | [7 empty] | 2025-09-03
84 | 4703638E |  | Pole | Redlands | [7 empty] | 2025-09-03
85 | 2013556E |  | Pole | Redlands | [7 empty] | 2025-09-03
86 | 33 W Lugonia Ave |  | Pole | Redlands | [7 empty] | 2025-09-03
87 | 1004 Columbia St. |  | Pole | Redlands | 34.066459291889494, -117.18765554387906 |  | T-00489879 | Abandoned service drops were observed |  |  |  | 2025-09-03 | GEN | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
88 | 930 Columbia St. |  | Pole | Redlands | 34.06513815578933, -117.18764984632026 |  | T-00489881 | damaged visibility strip |  |  |  | 2025-09-03 | GEN | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
89 | 918 Columbia St. |  | Pole | Redlands | 34.0647815662103, -117.18774111933872 |  | T-00489882 | lowest pole step on each of the following poles was located at a height less than eight feet |  |  |  | 2025-09-03 | GEN | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
90 | 420 W Sun Ave. |  | Pole | Redlands | 34.0643718154371, -117.18750863282956 |  | T-00489883 | Frontier ground wire attached to pole damaged, Abandoned service drops were observed |  |  |  | 2025-09-03 | GEN | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
91 | YUCPCAXF 1588994E |  | Pole | Yucaipa | 34.0324091, -117.0699821 |  | T-00489887 | Incomplete pole transfer |  |  |  | 2025-09-03 | GEN | LOGGED | MICHELE TABER |  | CA POLE ADMIN
92 | 1044648E |  | Pole | Yucaipa | [7 empty] | 2025-09-03
93 | 1806054E |  | Pole | Yucaipa | [7 empty] | 2025-09-03
94 | 1215194E |  | Pole | Yucaipa | [7 empty] | 2025-09-03
95 | YUCPCAXF 1215193E |  | Pole | Yucaipa | 34.0326426, -117.0683157 |  | DUPLICATE | Abandoned service drops were observed |  |  |  | 2025-09-03 | GEN |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
96 | 1215192E |  | Pole | Yucaipa | [7 empty] | 2025-09-03
97 | 1215191E |  | Pole | Yucaipa | [7 empty] | 2025-09-03
98 | 33792 Washington Dr. |  | Pole | Yucaipa | 34.033324613422494, -117.06727064632172 |  | T-00489890 | Abandoned service drops were observed |  |  |  | 2025-09-03 | GEN | LOGGED | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
99 | 1215190E |  | Pole | Yucaipa | [7 empty] | 2025-09-03
100 | 33816 Washington Dr. |  | Pole | Yucaipa | [7 empty] | 2025-09-03
101 | H2048 |  | Fiber Distribution Hub | Banning | [7 empty] | 2025-09-03
102 | FT2055202 |  | Handhole | Banning | 33.94001726179125, -116.9325066645546 | 5081 Maverick st. | T-00490102 | Frontier handhole covers was missing bolts |  |  |  | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
103 | FT2055203 |  | Handhole | Banning | 33.94040736149086, -116.93330437619943 | 5161Maverick st. | T-00490103 | Frontier handhole covers was missing bolts |  |  |  | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
104 | FT2055204 |  | Handhole | Banning | 33.94056315523737, -116.93406664736389 | 5227 Maverick st. | T-00490107 | Frontier handhole covers was missing bolts |  |  |  | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
105 | H2051 |  | Fiber Distribution Hub | Banning | 33.9428961, -116.9294379 | 33.9428961, -116.9294379 | T-00490106 | Frontier handhole covers was missing bolts |  |  |  | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
106 | H2052 |  | Fiber Distribution Hub | Banning | 33.9428961, -116.9294379 | 33.9428961, -116.9294379 | T-00490109 | Frontier handhole covers was missing bolts |  |  |  | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
107 | FC741 |  | Vault | Banning | [7 empty] | 2025-09-03
108 | 1054 Gilman St. |  | Vault | Banning | 33.936148103087824, -116.88805272832457 | 1054 W. Gilman street | T-00490108 | The cover of the underground vault located in front of 1054 Gilman St was corroded |  |  |  | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
109 | T8158A |  | Pedestal | Beaumont | [7 empty] | 2025-09-03
110 | T8159A |  | Pedestal | Beaumont | [7 empty] | 2025-09-03
111 | T8160 |  | Pedestal | Beaumont | [7 empty] | 2025-09-03
112 | T8164A |  | Pedestal | Beaumont | [7 empty] | 45903
113 | T8170A |  | Pedestal | Beaumont | [7 empty] | 45903
114 | T8166A |  | Pedestal | Beaumont | [7 empty] | 45903
115 | T8167 |  | Pedestal | Beaumont | 33.9382300960597, -116.99579913236322 | 1146 Gainsborough Ct. | T-00490119 | The cover of the pedestal T8167A was damaged |  |  |  | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO
116 | T8168A |  | Pedestal | Beaumont | [7 empty] | 45903
117 | T8169A |  | Pedestal | Beaumont | 33.938481309072465, -116.99560143360993 | 1156 Gainsborough Ct | T-00490120 | The cover of the pedestal T8169A was damaged |  |  |  | 2025-09-03 |  |  | RANDY ORTEGA |  | CON-CA-SAN BERNARDINO

## West LA 12-9-13 (hidden)
Item | City | Structure ID | Type | Ticket ID | Violation | Priority Level | Affected Company | GPS | Inspection Date | Tier | TKT Status | Frontier Response
1 | Playa Del Ray | 396356M | Pole |  |  | 2B |  |  | 2024-12-09
1 | Playa Del Ray | 396356M | Pole | T-00452389 | a Frontier conductor span was touching a third-party communications conductor span near the pole | 2B | Frontier | 33.9812612, -118.4144752 | 2024-12-09 | Tier 2 | Unassigned
2 | Playa Del Ray | 333852M | Pole | [5 empty] | 2024-12-09
3 | Playa Del Ray | 334760M | Pole | T-00452383 | a third-party communications service drop was wrapped around a Frontier conductor span | 2B | Spectrum/Charter | 33.9817871, -118.4134724 | 2024-12-09 | Tier 2 | Logged
4 | Playa Del Ray | 334761M | Pole | T-00452390 | a third-party communications cable span was detached from the messenger span and contacting a Frontier conductor span | 2B | Spectrum/Charter | 33.981649, -118.4135901 | 2024-12-09 | Tier 2 | Logged
4 | Playa Del Ray | 334761M | Pole | T-00452391 | a supply down guy anchor near the pole was abandoned and covered with a section of plastic pipe | 2C | SCE | 33.981649, -118.4135901 | 2024-12-09 | Tier 2 | Logged
5 | Playa Del Ray | 334462M | Pole | [5 empty] | 2024-12-09
6 | Playa Del Ray | 338846M | Pole | [5 empty] | 2024-12-09
7 | Playa Del Ray | 408328M | Pole | [5 empty] | 2024-12-09
8 | Playa Del Ray | 334763M | Pole | [5 empty] | 2024-12-09
9 | Playa Del Ray | 334764M | Pole | [5 empty] | 2024-12-09
10 | Playa Del Ray | 415895M | Pole | [5 empty] | 2024-12-09
11 | Playa Del Ray | 388192M | Pole | [5 empty] | 2024-12-09
12 | Playa Del Ray | 2033138M | Pole | [5 empty] | 2024-12-09
13 | Playa Del Ray | 344776M | Pole | [5 empty] | 2024-12-09
14 | Playa Del Ray | Next to Pole 344776M | Vault | [5 empty] | 2024-12-09
15 | Santa Monica | 2060649E | Pole | [5 empty] | 2024-12-09
16 | Santa Monica | 4314113E | Pole | [5 empty] | 2024-12-09
17 | Santa Monica | 4467773E | Pole | [5 empty] | 2024-12-09
18 | Santa Monica | 4427286E | Pole | [5 empty] | 2024-12-09
19 | Santa Monica | 2255629E | Pole | T-00419351 | a service drop was wrapped around a riser supported on the pole and touching a 6-foot fence at midspan | 2C | Frontier | 34.0283566, -118.4617243 | 2024-12-09 |  | Unassigned
20 | Santa Monica | 2255628E | Pole | [5 empty] | 2024-12-09
21 | Santa Monica | 2255493E | Pole | [5 empty] | 2024-12-09
22 | Santa Monica | 545705E | Pole | [5 empty] | 2024-12-09
23 | Culver City | 93242M | Pole | T-00452503 | the down guy wire supporting the Frontier facilities level of the pole was not maintained taut. | 2C | Frontier | 33.998761, -118.422274 | 2024-12-09 |  | Unassigned
24 | Culver City | 166199M | Pole | [5 empty] | 2024-12-09
25 | Culver City | 313603M | Pole | [5 empty] | 2024-12-09
26 | Culver City | 93241M | Pole | T-00452395 | the ground wire protective covering supported on the pole was damaged, exposing sections of the ground wire at the public level | 2C | Frontier | 33.9990855, 33.9990855 | 2024-12-09 |  | Unassigned
27 | Culver City | 93243M | Pole | T-00452396 | a Frontier service drop was touching a supply service drop at midspan that was supported on the same pole | 2C | Frontier | 33.998761, -118.422274 | 2024-12-09 |  | Unassigned
28 | Culver City | 93239M | Pole | T-00112328 | the ground wire protective covering supported on the pole was damaged, exposing the ground wire at the public leve | 2C | Frontier | 33.9995545, -118.4229008 | 2024-12-09 |  | Unassigned
29 | Culver City | 93238M | Pole | [5 empty] | 2024-12-09
30 | Culver City | 40347M | Pole | [5 empty] | 2024-12-09
31 | Culver City | Rear of 4110 Inglewood Blvd. | Pole | [5 empty] | 2024-12-09
32 | Culver City | 93237M | Pole | T-00450917 | the ground wire protective covering was damaged and loosely secured to the pole, exposing a 5-foot section of ground wire at the public level | 2C | Frontier | 34.0003907, -118.4235614 | 2024-12-09 |  | Unassigned
33 | Culver City | Rear of 4072 Inglewood Blvd. | Pole | [5 empty] | 2024-12-09
34 | Culver City | 93235M | Pole | T-00313636 | a detached service drop was hanging on a pole step located at the communication level. | 2C | Frontier | 34.0010524, -118.4240841 | 2024-12-09 |  | Unassigned
35 | Culver City | 93234M | Pole | T-00452397 | the down guy wire supporting the Frontier facilities level of the pole was not maintained taut | 2C | Frontier | 34.00147, -118.4244141 | 2024-12-09 |  | Unassigned
36 | Culver City | 93233M | Pole | [5 empty] | 2024-12-09
37 | Culver City | 289295M | Pole | [5 empty] | 2024-12-09
38 | Culver City | 429162M | Pole | [5 empty] | 2024-12-09
39 | Culver City | 220030M | Pole | [5 empty] | 2024-12-09
40 | Culver City | 225963M | Pole | [5 empty] | 2024-12-09
41 | Culver City | 137942M | Pole | [5 empty] | 2024-12-09
42 | Culver City | 390218M | Pole | T-00452398 | The down guy marker supported on the pole was damaged | 2C | Frontier??? | 34.00114304, -118.4247856 | 2024-12-09 |  | Unassigned
42 | Culver City | 390218M | Pole | T-00452398 | the down guy wire supporting the Frontier facilities level of the pole was not maintained taut | 2C | Frontier??? | INGLEWOOD BL E/S 291' S/O WASHINGTON PL | 2024-12-09 |  | Unassigned
42.1 | Culver City | 288155M | Pole | [5 empty] | 2024-12-09
43 | Culver City | 221761M | Pole | [5 empty] | 2024-12-09
44 | Culver City | GT142535 | Pole | [5 empty] | 2024-12-09
45 | Culver City | GT142554 | Pole | [5 empty] | 2024-12-09
46 | Culver City | 390209M | Pole | [5 empty] | 2024-12-09
47 | Culver City | 397489M | Pole | [5 empty] | 2024-12-09
48 | Bel Air | 121022M | Pole | [5 empty] | 2024-12-09
49 | Bel Air | 74613M | Pole | [5 empty] | 2024-12-09
50 | Bel Air | 74612M | Pole | [5 empty] | 2024-12-09
51 | Bel Air | 210894M | Pole | [5 empty] | 2024-12-09
52 | West Los Angeles | 296631M | Pole | [5 empty] | 2024-12-09
53 | Manhattan Beach | 943 1st Street | Hand Hole | [5 empty] | 2024-12-09
54 | Manhattan Beach | 934 1st Street | Hand Hole | [5 empty] | 2024-12-09
55 | Manhattan Beach | 922 1st Street | Hand Hole | [5 empty] | 2024-12-09
56 | Manhattan Beach | 910 1st Street | Hand Hole | [5 empty] | 2024-12-09
57 | Manhattan Beach | 106 S. Poinsettia Ave. | Hand Hole | [5 empty] | 2024-12-09
58 | Manhattan Beach | 828 1st Street | Hand Hole | [5 empty] | 2024-12-09
59 | Manhattan Beach | 820 1st street | Hand Hole | [5 empty] | 2024-12-09
60 | Manhattan Beach | 814 1st Street | Hand Hole | [5 empty] | 2024-12-09
61 | Manhattan Beach | 606496E | Pole | T-00452399 | a Frontier conductor span was touching a third-party communications conductor at midspan that was supported on the same pole | 2C | Frontier | 33.8792149, -118.4040553 | 2024-12-09 |  | Unassigned
62 | Manhattan Beach | 441 1st Street | Pole | [5 empty] | 2024-12-09
63 | Manhattan Beach | 429 1st Street | Pole | [5 empty] | 2024-12-09
64 | Manhattan Beach | 4887267E | Pole | T-00452400 | multiple loosely risers attached to the surface of the pole were not covered and protected at the public level | 2C | Frontier | 33.8790399, -118.4044813 | 2024-12-09 |  | Unassigned
65 | Manhattan Beach | 4351255E | Pole | [5 empty] | 2024-12-09
66 | Manhattan Beach | 1486643E | Pole | [5 empty] | 2024-12-09
67 | Manhattan Beach | 1083543E | Pole | [5 empty] | 2024-12-09
68 | Manhattan Beach | 2244687E | Pole | [5 empty] | 2024-12-09
69 | Manhattan Beach | 801 N. Ardmore | Pole | [5 empty] | 2024-12-09
70 | Palos Verde | 1393797E | Pole | [5 empty] | 2024-12-09
71 | Palos Verde | 1393796E | Pole | [5 empty] | 2024-12-09
72 | Palos Verde | 1393795E | Pole | [5 empty] | 2024-12-09
73 | Palos Verde | 1393794E | Pole | [5 empty] | 2024-12-09
74 | Palos Verde | 1394205E | Pole | [5 empty] | 2024-12-09
75 | Redondo Beach | GT10180 | Pole | T-00452401 | The climbing space on Pole GT10180 was obstructed near the base of the pole by branches and foliage | 3 | Frontier | 33.824192, -118.377015 | 2024-12-09 |  | Unassigned
76 | Redondo Beach | A8182Y | Pole | [5 empty] | 2024-12-09
77 | Redondo Beach | 833592E | Pole | [5 empty] | 2024-12-09
78 | Redondo Beach | 833591E | Pole | [5 empty] | 2024-12-09
79 | Redondo Beach | 833590E | Pole | [5 empty] | 2024-12-09
80 | Redondo Beach | 833589E | Pole | [5 empty] | 2024-12-09
81 | Redondo Beach | 4283892E | Pole | [5 empty] | 2024-12-09
82 | Redondo Beach | 900498E | Pole | T-00452402 | multiple Frontier service drops were attached to a third-party communications conductor that was supported on the pole | 2C | Frontier | 33.8249451, -118.3785158 | 2024-12-09 |  | Unassigned
83 | Redondo Beach | 617989E | Pole | [5 empty] | 2024-12-09
84 | Redondo Beach | 617988E | Pole | T-00452403 | a loosely attached riser to the surface of the pole was not covered and protected at the public level | 2C | Frontier | 33.8256249, -118.3787677 | 2024-12-09 |  | Unassigned
85 | Redondo Beach | 913771E | Pole | [5 empty] | 2024-12-09
86 | Redondo Beach | 913770E | Pole | [5 empty] | 2024-12-09
87 | Redondo Beach | 913769E | Pole | [5 empty] | 2024-12-09
88 | Redondo Beach | 913761E | Pole | [5 empty] | 2024-12-09
89 | Redondo Beach | 4840400E | Pole | [5 empty] | 2024-12-09
90 | Redondo Beach | A8185Y | Pole | [5 empty] | 2024-12-09
91 | Redondo Beach | A8184Y | Pole | [5 empty] | 2024-12-09
92 | Redondo Beach | A8183Y | Pole | [5 empty] | 2024-12-09
93 | Torrance | BF44065 | Pole | [5 empty] | 2024-12-09
94 | Torrance | 1035684E | Pole | [5 empty] | 2024-12-09
95 | Torrance | 1035653E | Pole | [5 empty] | 2024-12-09
96 | Torrance | 1035654E | Pole | [5 empty] | 2024-12-09
97 | Torrance | 1035655E | Pole | [5 empty] | 2024-12-09
98 | Torrance | 1083572E | Pole | [5 empty] | 2024-12-09
99 | Torrance | 1035656E | Pole | [5 empty] | 2024-12-09
100 | Torrance | 1035657E | Pole | [5 empty] | 2024-12-09
101 | Torrance | 1035658E | Pole | T-00452404 | a Frontier conductor span was attached to a third-party communications conductor at midspan that was supported on the same pole | 2C | Frontier | 33.8490789, -118.3644138 | 2024-12-09 |  | Unassigned
102 | Torrance | 1035659E | Pole | [5 empty] | 2024-12-09
103 | Torrance | 1035660E | Pole | T00452405 | a service drop supported on the pole sagged to approximately 6 feet above the ground over a walkway | 2A | Frontier | 33.8490767, -118.3633741 | 2024-12-09 |  | Unassigned
104 | Torrance | 1140837E | Pole | [5 empty] | 2024-12-09
105 | Torrance | 4852957E | Pole | [5 empty] | 2024-12-09
106 | Torrance | 1140836E | Pole | T-00452406 | The conductor span had a broken lashing wire | 2B | Frontier | 33.849078, -118.36254 | 2024-12-09 |  | Unassigned
107 | Torrance | 1140835E | Pole | T-00119107 | a Frontier conductor span was touching a third-party communications conductor at midspan that was supported on the same pole | 2C | Frontier | 33.8490004, -118.3624333 | 2024-12-09 |  | Unassigned
108 | Torrance | 1485214E | Pole | [5 empty] | 2024-12-09
109 | Torrance | 1358204E | Pole | T-00452407 | a detached service drop was left to hang off the conductor span near the pole. | 2C | Frontier | 33.848513, -118.363046 | 2024-12-09 |  | Unassigned
110 | Torrance | 1318729E | Pole | [5 empty] | 2024-12-09
111 | Torrance | 1358205E | Pole | [5 empty] | 2024-12-09
112 | Torrance | 1230661E | Pole | [5 empty] | 2024-12-09
113 | Torrance | 1983714E | Pole | [5 empty] | 2024-12-09
114 | Torrance | 4258279E | Pole | T-00452504 | A conductor span was measured to have a vertical clearance of 13 feet, 5 inches from ground. | 2B | Frontier | 33.848421, -118.3651028 | 2024-12-09 |  | Unassigned
115 | Torrance | 1358207E | Pole | [5 empty] | 2024-12-09
116 | Torrance | 4814403E | Pole | [5 empty] | 2024-12-09
117 | Torrance | 1358208E | Pole | [5 empty] | 2024-12-09
118 | Torrance | 1035448E | Pole | [5 empty] | 2024-12-09
119 | Torrance | 1035447E | Pole | [5 empty] | 2024-12-09
120 | Torrance | 1035446E | Pole | [5 empty] | 2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09
2024-12-09

## Riverside (hidden)
Item | City | Ticket ID | Priority Level | Affected Company | Update | TKT Status | Type | Pole | Inspection Date | Violation Description | Frontier Response
1 | Blythe | TK3776327 |  |  | 2025-03-24 |  | Pole | BLYTCAXF 4794493E | 2025-01-13 | Frontier conductor in contact with other conductor
2 | Blythe | TK3776336 |  |  | 2025-03-24 |  | Pole | BLYTCAXF 4794486E | 2025-01-13 | Frontier conductor in contact with other conductor
3 | Blythe | [5 empty] | Pole | 4940062E | 2025-01-13
4 | Blythe | [5 empty] | Pole | 4199757E | 2025-01-13
5 | Blythe | [5 empty] | Pole | 1992534E | 2025-01-13
6 | Blythe | TK3776339 |  |  | 2025-03-24 |  | Pole | BLYTCAXF 1641084.E | 2025-01-13 | Frontier conductor in contact with other conductor
7 | Blythe | TK3776340 |  |  | 2025-03-24 |  | Pole | BLYTCAXF 4260266E | 2025-01-13 | Frontier conductor in contact with other conductor
8 | Palo Verde | [5 empty] | Pole | 1969682 | 2025-01-13
9 | Palo Verde | [5 empty] | Pole | 59599S | 2025-01-13
10 | Palo Verde | TK3776831 |  |  | 2025-03-24 |  | Pole | PLVRCAXF 239462.S | 2025-01-13 | Visibility strips damaged
11 | Palo Verde | [5 empty] | Pole | 239480S | 2025-01-13
12 | Palo Verde | [5 empty] | Pole | 239495 | 2025-01-13
13 | Palo Verde | [5 empty] | Pole | 4758412E | 2025-01-13
14 | Palo Verde | TK3776850 |  |  | 2025-03-24 |  | Pole | PLVRCAXF 4061291E | 2025-01-13 | Unauthorized attachment |  | 33.43264052315786, -114.7324773183161 | 338-50156 | GEN
15 | Palo Verde | TK3776845 |  |  | 2025-03-24 |  | Pole | PLVRCAXF 1162.CRT | 2025-01-13 | Frontier conductor in contact with other conductor
16 | Palo Verde | TK3776851 |  |  | 2025-03-24 |  | Pole | PLVRCAXF 4758411E | 2025-01-13 | Frontier conductor in contact with other conductor |  | 33.430956 -114.732144 | 338-50156 | GEN
17 | Palo Verde | [5 empty] | Pole | 4758410E | 2025-01-13
18 | Palo Verde | TK3776852 |  |  | 2025-03-24 |  | Pole | 4061290E | 2025-01-13 | Guy Wire Loose |  | 33.430101 -114.732098 | 338-50156 | GEN
19 | Palo Verde | [5 empty] | Pole | 4757279E | 2025-01-13
20 | Palo Verde | TK3776847 |  |  | 2025-03-24 |  | Pole | 254673 | 2025-01-13 | Visibility strips damaged |  | REPORTED AS VZ254673
21 | Palo Verde | TK3776848 |  |  | 2025-03-24 |  | Pole | PLVRCAXF 4199809.E | 2025-01-13 | Unauthorized attachment
22 | Palo Verde | [5 empty] | Pole | CTC1110289 | 2025-01-13
23 | Palo Verde | [5 empty] | Pole | CTC1110288 | 2025-01-13
24 | Palo Verde | [5 empty] | Pole | CTC1110287 | 2025-01-13
25 | Palo Verde | [5 empty] | Pole | VZ101791 | 2025-01-13
26 | Palo Verde | [5 empty] | Pole | VZ102228 | 2025-01-13
27 | Palo Verde | TK3776849 |  |  | 2025-03-24 |  | Pole | PLVRCAXF GT-213834 | 2025-01-13 | Drop in contact with the ground in pedestrian area
28 | Palo Verde | [5 empty] | Pole | 439906S | 2025-01-13
29 | Palo Verde | [5 empty] | Pole | VZ101792 | 2025-01-13
30 | Palo Verde | [5 empty] | Pole | 2190925E | 2025-01-13
31 | Palo Verde | [5 empty] | Pole | 4758409E | 2025-01-13
32 | Palo Verde | [5 empty] | Pole | VZ101793 | 2025-01-13
33 | Palo Verde | [5 empty] | Pole | CTC1110281 | 2025-01-13
34 | Palo Verde | [5 empty] | Pole | CTC1110282 | 2025-01-13
35 | Blythe | [5 empty] | Pedestal | 3838 | 2025-01-13
36 | Blythe | TK3776603 |  |  | 2025-03-24 |  | Handhole | FT35626 | 2025-01-13 | Handhole lid unsecured |  |  | 338-50153
37 | Blythe | [5 empty] | Pedestal | 3846 | 2025-01-13
38 | Blythe | [5 empty] | Handhole | FT35630 | 2025-01-13
39 | Blythe | [5 empty] | Pedestal | 3844 | 2025-01-13
40 | Blythe | TK3776604 |  |  | 2025-03-24 |  | Pedestal | 3843 | 2025-01-13 | Locking mechanism broken, cannot secure |  |  | 338-50153
41 | Blythe | [5 empty] | Pedestal | 3813 | 2025-01-13
42 | Blythe | [5 empty] | Pedestal | 3814 | 2025-01-13
43 | Blythe | [5 empty] | Handhole | T-35634 | 2025-01-13
44 | Blythe | TK3776605 |  |  | 2025-03-24 |  | Pedestal | 3818 | 2025-01-13 | Locking mechanism broken, cannot secure |  |  | 338-50153
45 | Blythe | TK3776607 |  |  | 2025-03-24 |  | Pedestal | 3819 | 2025-01-13 | Cannot secure against unauthorized persons |  |  | 338-50153
46 | Blythe | [5 empty] | Cross Box | XTBM | 2025-01-13
47 | Blythe | [5 empty] | Pole | 4793906E | 2025-01-13
48 | Blythe | [5 empty] | Pole | 1840825E | 2025-01-13
49 | Blythe | [5 empty] | Pole | 4320307E | 2025-01-13
50 | Blythe | TK3776634 |  |  | 2025-03-24 |  | Pole | 4973480E | 2025-01-13 | Abandoned Drop |  |  | 338-50153 | GEN
51 | Blythe | [5 empty] | Pole | 4666669E | 2025-01-13
52 | Blythe | [5 empty] | Pole | 4704806E | 2025-01-13
53 | Blythe | [5 empty] | Pole | 59658 | 2025-01-13
54 | Blythe | [5 empty] | Pole | 38007S | 2025-01-13
55 | Blythe | [5 empty] | Pole | 2073454E | 2025-01-13
56 | Blythe | [5 empty] | Pole | 38008S | 2025-01-13
57 | Blythe | [5 empty] | Pole | 1585833E | 2025-01-13
58 | Blythe | TK3776514 |  |  | 2025-03-24 |  | Pole | BLYTCAXF 2073720.E | 2025-01-13 | Pole step too low
59 | Blythe | [5 empty] | Pole | 4639883E | 2025-01-13
60 | Blythe | [5 empty] | Pole | 4507571E | 2025-01-13
61 | Blythe | [5 empty] | Pole | 59603S | 2025-01-13
62 | Blythe | [5 empty] | Pole | 4199795E | 2025-01-13
63 | Blythe | [5 empty] | Pole | 2350576E | 2025-01-13
64 | Blythe | [5 empty] | Pole | 4320314E | 2025-01-13
65 | Blythe | [5 empty] | Pedestal | 2671 Colorado River Rd. | 2025-01-13
66 | Blythe | [5 empty] | Pedestal | 2655 Colorado River Rd. | 2025-01-13
67 | Blythe | TK3776638 |  |  | 2025-03-24 |  | Pedestal | 2654 Colorado River Rd. | 2025-01-13 | Cannot secure against unauthorized persons |  | 33.658252599077045, -114.5272038998854
68 | Blythe | [5 empty] | Pedestal | 2644 Colorado River Rd. | 2025-01-13
69 | Blythe | [5 empty] | Pedestal | 2614 Colorado River Rd. | 2025-01-13
70 | Blythe | [5 empty] | Pedestal | 2667 Sandy Point Dr. | 2025-01-13
71 | Blythe | TK3776639 |  |  | 2025-03-24 |  | Pedestal | 2733 Sandy Point Dr. | 2025-01-13 | Cannot secure against unauthorized persons |  | 33.659483728285004, -114.5282425653086
72 | Blythe | [5 empty] | Pedestal | 3821 Sandy Point Dr. | 2025-01-13
73 | Blythe | TK3776640 |  |  | 2025-03-24 |  | Pedestal | 3839 Sandy Point Dr. | 2025-01-13 | Cannot secure against unauthorized persons |  | 33.65997029908407, -114.52759602948
74 | Blythe | TK3776641 |  |  | 2025-03-24 |  | Pedestal | 3845 Sandy Point Dr. | 2025-01-13 | Locking mechanism broken |  | 33.659919441976776, -114.52718275429956
75 | Blythe | TK3776642 |  |  | 2025-03-24 |  | Pedestal | 3841 Sandy Point Dr. | 2025-01-13 | Cannot secure against unauthorized persons |  |  | 338-50153
76 | Blythe | [5 empty] | Pedestal | 3875 Sandy Point Dr. | 2025-01-13
77 | Blythe | TK3776643 |  |  | 2025-03-24 |  | Pedestal | 3889 Sandy Point Dr. | 2025-01-13 | Cannot secure against unauthorized persons |  | 33.659690857600935, -114.52568470232245
78 | Blythe | [5 empty] | Pole | 4601034E | 2025-01-13
79 | Blythe | [5 empty] | Pole | 4260100E | 2025-01-13
80 | Blythe | [5 empty] | Pole | 4800571E | 2025-01-13
81 | Blythe | [5 empty] | Pole | 4846068E | 2025-01-13
82 | Blythe | [5 empty] | Pole | 1720792E | 2025-01-13
83 | Blythe | [5 empty] | Pole | 38093S | 2025-01-13
84 | Blythe | [5 empty] | Pole | 1585827E | 2025-01-13
85 | Blythe | TK3776515 |  |  | 2025-03-24 |  | Pole | BLYTCAXF 1992484.E | 2025-01-13 | Frontier conductor in contact with other conductor
86 | Mecca | TK3776798 |  |  | 2025-03-24 |  | Pole | 1211126D | 2025-01-13 | Frontier conductor in contact with other conductor |  |  | 338-70038 | GEN
87 | Mecca | [5 empty] | Pole | 922943 | 2025-01-13
88 | Mecca | [5 empty] | Pole | 908060D | 2025-01-13
89 | Mecca | [5 empty] | Pole | 929041D | 2025-01-13
90 | Mecca | [5 empty] | Pole | 911721D | 2025-01-13
91 | Mecca | [5 empty] | Pole | 48403CWT | 2025-01-13
92 | Mecca | [5 empty] | Pole | 929051D | 2025-01-13
93 | Mecca | TK3776721 |  |  | 2025-03-24 |  | Pole | MECCCAXF 906561D | 2025-01-13 | Visibility stripsand down guy damaged
94 | Mecca | [5 empty] | Pole | 910041D | 2025-01-13
95 | Mecca | [5 empty] | Pole | 910042D | 2025-01-13
96 | Mecca | TK3776722 |  |  | 2025-03-24 |  | Pole | MECCCAXF 1218902 | 2025-01-13 | Visibility strips damaged
97 | Mecca | TK3776723 |  |  | 2025-03-24 |  | Pole | MECCCAXF 90626D | 2025-01-13 | Frontier conductor in contact with other conductor
98 | Mecca | [5 empty] | Pole | 911767D | 2025-01-13
99 | Mecca | [5 empty] | Pole | 913944 | 2025-01-13
100 | Mecca | TK3776724 |  |  | 2025-03-24 |  | Pole | MECCCAXF 1188734 | 2025-01-13 | Visibility strips damaged
101 | Mecca | [5 empty] | Pole | 920122D | 2025-01-13
102 | North Shore | [5 empty] | Pole | 906763D | 2025-01-13
103 | North Shore | [5 empty] | Pole | 909764D | 2025-01-13
104 | North Shore | [5 empty] | Pole | 906765D | 2025-01-13
105 | North Shore | TK3776826 |  |  | 2025-03-24 |  | Pole | 906766D | 2025-01-13 | FTR conductor in contact with a 3rd Party guy wire |  |  | 338-70038
106 | North Shore | [5 empty] | Pole | 906962D | 2025-01-13
107 | North Shore | [5 empty] | Pole | 906963D | 2025-01-13
108 | North Shore | [5 empty] | Pole | 906964D | 2025-01-13
109 | North Shore | TK3776827 |  |  | 2025-03-24 |  | Pole | 907335D | 2025-01-13 | Visibility strips damaged |  |  | 338-70038
110 | North Shore | [5 empty] | Pole | 907737D | 2025-01-13
111 | North Shore | [5 empty] | Pole | 907338D | 2025-01-13
112 | North Shore | [5 empty] | Pole | 907339D | 2025-01-13
113 | North Shore | [5 empty] | Pole | 907340D | 2025-01-13
114 | North Shore | TK3776828 |  |  | 2025-03-24 |  | Pole | 907341D | 2025-01-13 | Visibility strips damaged |  |  | 338-70038
115 | North Shore | [5 empty] | Pole | 907342D | 2025-01-13
116 | Salton | TK3776858 |  |  | 2025-03-24 |  | Pole | NSHRCAXF 905153D | 2025-01-13 | Visibility strips damaged
117 | Salton | [5 empty] | Pole | Tagless pole E/O 905153D | 2025-01-13
118 | Salton | TK3776859 |  |  | 2025-03-24 |  | Pole | NSHRCAXF 905155D | 2025-01-13 | Abandoned Drop
119 | Salton | [5 empty] | Pole | 905152D | 2025-01-13
120 | Mecca | TK3776725 |  |  | 2025-03-24 |  | Pole | MECCCAXF 911725D | 2025-01-13 | Frontier conductor in contact with other conductor
121 | Mecca | [5 empty] | Pole | Tagless pole N/O 911725D | 2025-01-13
122 | Mecca | [5 empty] | Pole | 920858 | 2025-01-13
123 | Mecca | [5 empty] | Pole | 322069D | 2025-01-13
124 | Mecca | [5 empty] | Pole | 1218904 | 2025-01-13
125 | Mecca | [5 empty] | Pole | Tagless pole W/O 1218904 | 2025-01-13
126 | Mecca | [5 empty] | Pole | 901195D | 2025-01-13
127 | Mecca | [5 empty] | Pole | 922292 | 2025-01-13
128 | Mecca | TK3776800 |  |  | 2025-03-24 |  | Pole | 40150CWT | 2025-01-13 | Guy Wire Loose |  |  | 338-70038 | GEN
129 | Mecca | TK3776726 |  |  | 2025-03-24 |  | Pole | MECCCAXF 907401D | 2025-01-13 | Unauthorized attachment
130 | Mecca | TK3776727 |  |  | 2025-03-24 |  | Pole | MECCCAXF 922054D | 2025-01-13 | Frontier messanger wire not grounded
131 | Mecca | [5 empty] | Pedestal | S/O 7th St. & Lincoln St. | 2025-01-13 |  |  | 33.575153527647984, -116.0789603768785 | 338-70084 | GEN
132 | Mecca | TK3776801 |  |  | 2025-03-24 |  | Pedestal | N/O 7th St. & Lincoln St. | 2025-01-13 | Dirt and debris buildup cannot close pedestal, Cannot secure against unauthorized persons |  | 33.57533352586921, -116.07895508861422 | 338-70084
133 | Mecca | TK3776802 |  |  | 2025-03-24 |  | Pedestal | S/O 65th St. & Lincoln St | 2025-01-13 | Cannot secure against unauthorized persons |  | 33.57646774668111, -116.07897976955846 | 338-70084
134 | Mecca | [5 empty] | Pedestal | N/O 65th St. & Lincoln St. | 2025-01-13
135 | Mecca | [5 empty] | Pedestal | N/O Previous on Lincoln St. | 2025-01-13
136 | Mecca | [5 empty] | Pedestal | N/O Previous on Lincoln St. | 2025-01-13
137 | Mecca | TK3776803 |  |  | 2025-03-24 |  | Pedestal | 64100 Lincoln St. | 2025-01-13 | Locking mechanism broken |  | 33.58042205629878, -116.07890792584642 | 338-70084
138 | Mecca | [5 empty] | Pedestal | Across from 64100 Lincoln St. | 2025-01-13
139 | Mecca | TK3776822 |  |  | 2025-03-24 |  | Pedestal | 64245 Lincoln St. | 2025-01-13 | Pedestal housing damaged, Cannot secure against unauthorized persons |  | 33.581252374673426, -116.07898698412882 | 338-70084
140 | Mecca | [5 empty] | Pole | 95376D | 2025-01-13
141 | Mecca | [5 empty] | Pedestal | W/O Lincoln St. & 64th Ave. | 2025-01-13
142 | Mecca | TK3776823 |  |  | 2025-03-24 |  | Pedestal | SE/O Lincoln St. & 64th Ave. | 2025-01-13 | Missing cover |  | 33.583831979238596, -116.07886926775966 | 338-70084
143 | Mecca | [5 empty] | Pedestal | NW/O Theodore Wy. & 64th Ave. | 2025-01-13
144 | Mecca | [5 empty] | Pedestal | NE/O Theodore Wy. & 64th Ave. | 2025-01-13
145 | Mecca | TK3776824 |  |  | 2025-03-24 |  | Handhole | E/O Theodore Wy. & 64th Ave | 2025-01-13 | Locking mechanism broken |  |  | 338-70038
146 | Mecca | [5 empty] | Pedestal | Arthur St. & 70th Ave | 2025-01-13