## Header
Full Year
Line No |  | Level 2 Priority "E" | Level 2 Priority "B" | Level 2 Priority "B" from "E" | Level 2 Results
1 | On-time | 3683 | 1500 | 220 | 5403
2 | Past Due | 6262 | 17 | 36 | 6315
3 | % On-Time | 37.03% | 98.88% | 85.94% | 46.11%
Month of Decemebr
Line No |  | Level 2 Priority "E" | Level 2 Priority "B" | Level 2 Priority "B" from "E" | Level 2 Results
1 | On-time | 128 | 49 | 11 | 188
2 | Past Due | 788 | 3 | 0 | 791
3 | % On-Time | 13.97% | 94.23% | 100% | 19.2%

## Sheet1 (hidden)
2022-01-01 | 2021-10-03
2022-12-31 | 2022-10-02
|  | Due | T3 | T2
B | 90 | 2022-01-01 | 2021-07-05 | 2021-01-01
| 90 | 2022-12-31 | 2022-07-04 | 2021-12-31
Formulas:
T3 = [Due]-180

## Pivot
Count of Notification No | Column Labels
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Grand Total
Row Labels
B - Urgt Compliance | 84 | 6 | 86 | 239 | 130 | 341 | 257 | 118 | 69 | 55 | 80 | 52 | 1517
Late | Column Labels Jan: 2; Column Labels Apr: 1; Column Labels May: 1; Column Labels Sep: 1; Column Labels Oct: 1; Column Labels Nov: 8; Column Labels Dec: 3 | 17
On-time | 82 | 6 | 86 | 238 | 129 | 341 | 257 | 118 | 68 | 54 | 72 | 49 | 1500
E - Schd Compl Yr 0 | 416 | 64 | 574 | 1679 | 1226 | 1594 | 906 | 219 | 458 | 918 | 975 | 916 | 9945
Late | 377 | 48 | 193 | 678 | 650 | 887 | 389 | 172 | 353 | 833 | 894 | 788 | 6262
On-time | 39 | 16 | 381 | 1001 | 576 | 707 | 517 | 47 | 105 | 85 | 81 | 128 | 3683
Upgraded | 14 | 1 | 18 | 59 | 30 | 57 | 24 | 4 | 9 | 13 | 16 | 11 | 256
Late | Column Labels Jan: 8; Column Labels Apr: 5; Column Labels May: 2; Column Labels Jun: 15; Column Labels Jul: 4; Column Labels Oct: 1; Column Labels Nov: 1 | 36
On-time | 6 | 1 | 18 | 54 | 28 | 42 | 20 | 4 | 9 | 12 | 15 | 11 | 220
Grand Total | 514 | 71 | 678 | 1977 | 1386 | 1992 | 1187 | 341 | 536 | 986 | 1071 | 979 | 11718

## Raw Data
Notification type | Notification No | Technical identification no. | Description | Main work center | Functional Location | Created On | Notification date | Reference date | Calculated SOMs Due Date | Required End | Late or On-time | Work Type Code | Priority text | Notification Sytem Status | HFTD | Notification User Status | Damage Code text | Object Code text | Activity Code text | Order | Order Number Description | MaintActivityType
LC | 120255824 | 005/112 | T2 BURNS-LONE STAR #2 5/112 RPR SWITCH | MOSSLNDG | ETL.6240.POLE.NWOD | 2021-01-04 | 2021-01-04 | 2021-08-01 | 2022-01-04 | 2022-01-04 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Switch-Wood | Repair | 44610159 | T2 BURNS-LONE STAR #2 5/112 RPR SWITCH | ICW
LC | 120259920 | 026/001 | T2 HARTLEY-CLEARLAKE 26/001 REPL PL | WILLITS | ETL.7515.POLE.WOOD | 2021-01-05 | 2021-01-05 | 2022-02-17 | 2022-01-05 | 2022-01-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31526981 | T2 HARTLEY-CLEARLAKE 26/001 REPL PL | 70Y
LC | 120419118 | 006/054 | T2 CABRILLO-SNT YNZ SS 6/54 REPL INSW | PISMOBCH | ETL.1200.INSL.NCER | 2021-01-11 | 2021-01-11 | 2022-05-16 | 2022-01-11 | 2022-01-11 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31527871 | T2 CABRILLO-SNT YNZ SS 6/54 REPL INSW | 93I
LC | 120423636 | 017/098 | T2 PARKWAY-MORAGA 17/098 RPL INSS | LAKEVLLE | ETL.5930.INSL.NCER | 2021-01-12 | 2021-01-12 | 2021-12-01 | 2022-01-12 | 2022-01-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31530575 | DI PARKWAY-MORAGA RPLC INSS 8T | 93K
LC | 120423658 | 006/071 | T2 WV CLGT-SMRTVILLE #2 06/071 RPL POLE | SACTO | ETL.6520.POLE.WOOD | 2021-01-12 | 2021-01-12 | 2021-06-08 | 2022-01-12 | 2022-01-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31417718 | COLGATE-SMARTVILLE #2 - 60 KV_000/002 | 70Y
LC | 120423830 | 007/045 | T2 WV NEWARK-LIVERMORE 7/045 RPL INSS | CONCORD | ETL.7660.TOWR | 2021-01-12 | 2021-01-12 | 2021-11-10 | 2022-01-12 | 2022-01-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31432044 | EI NEWARK-LIVERMORE RPLC INSLS ON 5TWRS | 93K
LC | 120436039 | 011/399 | T2 SPAULDING-SUMMIT 11/399 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-01-16 | 2021-01-16 | 2021-07-28 | 2022-01-16 | 2022-01-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44630803 | T2 SPAULDING-SUMMIT 11/399 RPR GYWW | ICW
LC | 120452261 | 024/186 | T2 DRUM-HIGGINS 24/186 REPL INSS | SACTO | ETL.4393.INSL.CERA | 2021-01-21 | 2021-01-21 | 2021-04-29 | 2022-01-21 | 2022-01-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31499112 | T2 EI DRUM-HIGGINS REPL INSS 17 TWRS | 93K
LC | 120465189 | 054/235 | WV T2 RND MN-TBL MN#1 54/235 REPL HRD | TABLEMTN | ETL.6060.TOWR | 2021-01-26 | 2021-01-26 | 2022-05-16 | 2022-01-26 | 2022-01-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45240458 | WV T2 RND MN-TBL MN#1 54/235 REPL HRD | ICS
LC | 120465277 | 038/176A | WV T2 RND MTN-TBL MTN#1 38/176A REPL HRD | TABLEMTN | ETL.6060.TOWR | 2021-01-26 | 2021-01-26 | 2022-05-16 | 2022-01-26 | 2022-01-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45240480 | WV T2 RND MTN-TBL MTN#1 38/176A REPL HRD | ICS
LC | 120485139 | 019/087 | T2 EI MORRO BAY-MESA 019/087 RPL INSS | PISMOBCH | ETL.5290.INSL | 2021-02-01 | 2021-02-01 | 2021-02-03 | 2022-02-01 | 2022-02-01 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31529091 | T2 EI MORRO BAY-MESA 019/087 RPL INSS | 93K
LC | 120486583 | 015/186B | WV T2 DELTA-MTN GT JT 15/186B INST DAMPR | TABLEMTN | ETL.6750.POLE.WOOD | 2021-02-01 | 2021-02-01 | 2022-07-27 | 2022-02-01 | 2022-02-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Damper-Wood | Replace | 45226168 | WV T2 DELTA-MTN GT JT 15/186B INST DAMPR | ICW
LC | 120492800 | 011/259 | T2 COLGATE-GRS VALY 11/259 REFRAME | SACTO | ETL.6490.POLE.WOOD | 2021-02-02 | 2021-02-02 | 2022-08-11 | 2022-02-02 | 2022-02-02 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31529823 | T2 COLGATE-GRS VALY 11/259 REFRAME | 93E
LC | 120493057 | 001/022 | WV T2 COTTNWD-PNRAM 1/22 REPL INSW | TABLEMTN | ETL.1340.POLE.WOOD | 2021-02-02 | 2021-02-02 | 2021-11-04 | 2022-02-02 | 2022-02-02 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31529822 | WV T2 COTTNWD-PNRAM 1/22 REPL INSW | 93I
LC | 120493359 | 001/046 | T2 PINE GROVE TAP 1/46 RPR ANCHOR | VICTOR | ETL.8351.POLE.WOOD | 2021-02-02 | 2021-02-02 | 2021-02-02 | 2022-02-02 | 2022-02-02 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 44641205 | T2 PINE GROVE TAP 1/46 RPR ANCHOR | ICW
LC | 120499847 | 005/061 | WV T2 MTN GATE JCT-CSCD 5/061 REPL POLE | TABLEMTN | ETL.7640.POLE.WOOD | 2021-02-04 | 2021-02-04 | 2022-08-10 | 2022-02-04 | 2022-02-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31529824 | WV T2 MTN GATE JCT-CSCD 5/061 REPL POLE | 70Y
LC | 120506833 | 005/055 | T2 WV MTN GATE JCT-CSCDE 5/055 RPL POLE | TABLEMTN | ETL.7640.POLE.WOOD | 2021-02-08 | 2021-02-08 | 2022-08-10 | 2022-02-08 | 2022-02-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31529824 | WV T2 MTN GATE JCT-CSCD 5/061 REPL POLE | 70Y
LC | 120506843 | 006/071 | T2 WV MTN GT JCT-CASCDE 6/071 RPL POLE | TABLEMTN | ETL.7640.POLE.WOOD | 2021-02-08 | 2021-02-08 | 2022-08-10 | 2022-02-08 | 2022-02-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31529824 | WV T2 MTN GATE JCT-CSCD 5/061 REPL POLE | 70Y
LC | 120531658 | 000/002 | T2 WV MTN GATE JCT-CASCDE 0/2 INST DAMPR | TABLEMTN | ETL.7640.POLE.WOOD | 2021-02-12 | 2021-02-12 | 2022-06-07 | 2022-02-12 | 2022-02-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Damper-Wood | Replace | 45291664 | T2 WV MTN GATE JCT-CASCDE 0/2 INST DAMPR | ICW
LC | 120533001 | 004/054 | T2 WV MTN GATE JCT-CASCDE4/54 INST DAMP | TABLEMTN | ETL.7640.POLE.NWOD | 2021-02-12 | 2021-02-12 | 2022-04-28 | 2022-02-12 | 2022-02-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Wood | Install | 45309951 | T2 WV MTN GATE JCT-CASCDE4/54 INST DAMP | ICW
LC | 120533134 | 011/137C | T2 EI DRUM-SUMMIT #2 11/137C RPR GYWW | SACTO | ETL.1450.POLE.WOOD | 2021-02-12 | 2021-02-12 | 2022-06-07 | 2022-02-12 | 2022-02-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44697892 | T2 EI DRUM-SUMMIT #2 11/137C RPR GYWW | ICW
LC | 120552778 | 004/074 | WV T2 CENTERVILLE-TBLE MTN 4/74 INS DMPW | TABLEMTN | ETL.6320.INSL.NCER | 2021-02-18 | 2021-02-18 | 2022-04-25 | 2022-02-18 | 2022-02-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 45197505 | WV T2 CENTERVILLE-TBLE MTN 4/74 INS DMPW | ICW
LC | 120552837 | R001/015 | T2 WV RND MTN-CTTNWD #3 R1/15L RPL POLE | TABLEMTN | ETL.5650.POLE.WDPS | 2021-02-18 | 2021-02-18 | 2022-08-02 | 2022-02-18 | 2022-02-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31539908 | WV T2 RND MTN-CTTNWD #3 R1/15L RPL POLE | 70Y
LC | 120552902 | R001/016 | T2 WV RND MTN-CTTNWD #3 R1/16L RPL PL | TABLEMTN | ETL.5650.POLE.WDPS | 2021-02-18 | 2021-02-18 | 2022-08-03 | 2022-02-18 | 2022-02-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31539908 | WV T2 RND MTN-CTTNWD #3 R1/15L RPL POLE | 70Y
LC | 120554637 | R001/015 | T2 WV RND MTN-CTTNWD #3 R1/15R RPL POLE | TABLEMTN | ETL.5650.POLE.WDPS | 2021-02-19 | 2021-02-18 | 2022-08-02 | 2022-02-18 | 2022-02-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31539908 | WV T2 RND MTN-CTTNWD #3 R1/15L RPL POLE | 70Y
LC | 120554638 | R001/016 | T2 WV RND MTN-CTTNWD #3 R1/16R RPL PL | TABLEMTN | ETL.5650.POLE.WDPS | 2021-02-19 | 2021-02-18 | 2022-08-03 | 2022-02-18 | 2022-02-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31539908 | WV T2 RND MTN-CTTNWD #3 R1/15L RPL POLE | 70Y
LC | 120564484 | 009/187 | T2 COTTONWD-RED BLUFF 9/187 REPLUMB PL | TABLEMTN | ETL.6660.POLE.WOOD | 2021-02-22 | 2021-02-22 | 2022-09-29 | 2022-02-22 | 2022-02-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45242426 | T2 COTTONWD-RED BLUFF 9/187 REPLUMB PL | ICW
LC | 120568864 | 013/257 | WV T2 COLGATE-PALERMO 13/257 REPL POLE | TABLEMTN | ETL.6500.POLE.WOOD | 2021-02-23 | 2021-02-23 | 2021-11-17 | 2022-02-23 | 2022-02-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31517754 | T2 DI COLGT-PALRM 10/200 RPL STRW | 70Y
LC | 120568939 | 011/081 | WV T2 VACA-SSN-JAM 11/81 INST JUMPR INSS | SACTO | ETL.4080.INSL.NCER | 2021-02-23 | 2021-02-23 | 2022-05-16 | 2022-02-23 | 2022-02-23 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31457373 | T2 EI VACA-SUISUN-JAM RPLC INSL 13 STRC | 93K
LC | 120572024 | 003/062 | T2 DEL MONTE-VIEJO 3/062 RPR GYWW | MOSSLNDG | ETL.6710.POLE.WOOD | 2021-02-24 | 2021-02-24 | 2022-04-26 | 2022-02-24 | 2022-02-24 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45122537 | T2 DEL MONTE-VIEJO 3/062 RPR GYWW | ICW
LC | 120572091 | 003/060 | T2 DEL MONTE-VIEJO 3/60 REPLUMB | MOSSLNDG | ETL.6710.POLE.WOOD | 2021-02-24 | 2021-02-24 | 2022-04-27 | 2022-02-24 | 2022-02-24 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45122539 | T2 DEL MONTE-VIEJO 3/60 REPLUMB | ICW
LC | 120572148 | 067/339 | T2 MALIN-ROUND MTN #2 67/339 RPL INSS | TABLEMTN | ETL.6020.INSL | 2021-02-24 | 2021-02-23 | 2021-05-11 | 2022-02-23 | 2022-02-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31527915 | T2 MALIN-ROUND MTN #2 67/339 RPL INSS | 93K
LC | 120573245 | 030/003B | T2 WV PHILO JCT-ELK 30/3B REPL ANCW | WILLITS | ETL.7780.POLE.WOOD | 2021-02-24 | 2021-02-24 | 2022-03-17 | 2022-02-24 | 2022-02-24 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31532672 | T2 PHILO JCT-ELK 30/3B REPL ANCW | 93E
LC | 120573399 | 011/081 | T2 WV VACA-SSN-JN 11/81 INST HRDT CMPLT | SACTO | ETL.4080.INSL.NCER | 2021-02-24 | 2021-02-23 | 2022-05-17 | 2022-02-23 | 2022-02-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | Missing | Hardware-Tower | Install | 44698619 | T2 DI VACA-SUISUN-JAMSN 11/81 INST HRDT | ICQ
LC | 120574688 | 016/119 | T2 EI CARIBOU-TABLE MTN 16/119 RPR FOND | TABLEMTN | ETL.4440.TOWR | 2021-02-24 | 2021-02-24 | 2022-07-19 | 2022-02-24 | 2022-02-24 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160937 | T2 EI CARIBOU-TABLE MTN 16/119 RPR FOND | ICQ
LC | 120574796 | 016/119 | T2 EI CARIBOU-TABLE MTN 16/119 RPR GYSS | TABLEMTN | ETL.4440.TOWR | 2021-02-24 | 2021-02-24 | 2022-06-24 | 2022-02-24 | 2022-02-24 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45212274 | T2 EI CARIBOU-TABLE MTN 16/119 RPR GYSS | ICS
LC | 120574861 | 016/122 | T2 EI CARIBOU-TABLE MTN 16/122 RPR GYWS | TABLEMTN | ETL.4440.TOWR | 2021-02-24 | 2021-02-24 | 2022-06-24 | 2022-02-24 | 2022-02-24 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45212276 | T2 EI CARIBOU-TABLE MTN 16/122 RPR GYWS | ICS
LC | 120578558 | 014/009 | T2 LAYTONVILLE-WILLITS 14/9 RMV TREE | WILLITS | ETL.8360.POLE.NWOD | 2021-02-25 | 2021-02-25 | 2022-02-18 | 2022-02-25 | 2022-02-25 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW PATR COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120582581 | 039/317 | T2 WV RND MTN-CTTNWD #2 39/317 INST DMS | TABLEMTN | ETL.5640.TOWR | 2021-02-26 | 2021-02-26 | 2022-08-01 | 2022-02-26 | 2022-02-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Damper-Steel | Install | 44670022 | T2 EI RND MTN-CTTNWD #2 39/317 INS DAMPS | ICS
LC | 120582632 | 038/002 | T2 WV RIO DELL JCT-BRIDGEVL 38/2 CMPTD | EUREKA | ETL.7850.INSL.NCER | 2021-02-26 | 2021-02-26 | 2022-02-18 | 2022-02-26 | 2022-02-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 45010821 | T2 WV RIO DLL JCT-BRDGEVLLE 38/2 INS DMP | ICS
LC | 120582829 | 002/046 | T2 KILARC-DESCHUTES 2/046 REPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2021-02-26 | 2021-02-26 | 2022-04-18 | 2022-02-26 | 2022-02-26 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31532667 | T2 KILARC-DESCHUTES 2/046 REPL POLE | 70Y
LC | 120582859 | 019/409 | T2 KILARC-DESCHUTES 19/409 RMV TREE | TABLEMTN | ETL.7300.POLE.NWOD | 2021-02-26 | 2021-02-26 | 2021-10-22 | 2022-02-26 | 2022-02-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120582891 | 002/057 | T2 KILARC-DESCHUTES 2/57 RMV TREE | TABLEMTN | ETL.7300.POLE.WOOD | 2021-02-26 | 2021-02-26 | 2021-10-22 | 2022-02-26 | 2022-02-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120582892 | 005/111 | T2 EI KILARC-DESCHUTES 5/111 REPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2021-02-26 | 2021-02-26 | 2022-04-18 | 2022-02-26 | 2022-02-26 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31532667 | T2 KILARC-DESCHUTES 2/046 REPL POLE | 70Y
LC | 120582893 | 006/126 | T2 EI KILARC-DESCHUTES 6/126 REFRAME | TABLEMTN | ETL.7300.POLE.WOOD | 2021-02-26 | 2021-02-26 | 2022-04-19 | 2022-02-26 | 2022-02-26 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31532666 | T2 EI KILARC-DESCHUTES 6/126 REFRAME | 93E
LC | 120582954 | 001/029 | T2 DELTA-MTN GATE JCT 1/29 REPL POLE | TABLEMTN | ETL.6750.POLE.WOOD | 2021-02-26 | 2021-02-26 | 2021-08-18 | 2022-02-26 | 2022-02-26 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31532668 | T2 DELTA-MTN GATE JCT 1/29 REPL POLE | 70Y
LC | 120582971 | 001/034 | T2 DELTA-MTN GATE JCT 1/34 RPL POLE | TABLEMTN | ETL.6750.POLE.WOOD | 2021-02-26 | 2021-02-26 | 2022-08-27 | 2022-02-26 | 2022-02-26 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31602065 | T2 DELTA-MTN GATE JCT 1/34 RPL POLE | 70Y
LC | 120582974 | 002/069 | T2 DELTA-MTN GATE JCT 2/069 RPL STRW | TABLEMTN | ETL.6750.POLE.WOOD | 2021-02-26 | 2021-02-26 | 2022-08-27 | 2022-02-26 | 2022-02-26 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31532669 | T2 DELTA-MTN GATE JCT 2/069 RPL STRW | 70Y
LC | 120583013 | 011/152 | T2 DELTA-MTN GATE JCT 11/152 RPL INSS | TABLEMTN | ETL.6750.TOWR | 2021-02-26 | 2021-02-26 | 2022-08-21 | 2022-02-26 | 2022-02-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31532784 | T2 DELTA-MTN GATE JCT 11/152 REPL INSS | 93K
LC | 120584982 | 002/018 | T2 MTN GATE JCT-CASCAD 2/18 REPL INSW | TABLEMTN | ETL.7640.INSL.CERA | 2021-03-01 | 2021-02-25 | 2022-04-28 | 2022-02-25 | 2022-02-25 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545032 | T2 MTN GATE JCT-CASCAD 2/18 REPL INSW | 93I
LC | 120589873 | 008/055 | T2 DI METCALF-GREEN VALLEY RPLC HRDT | MOSSLNDG | ETL.2540.TOWR | 2021-03-02 | 2021-03-01 | 2021-06-24 | 2022-03-01 | 2022-03-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44805597 | T2 DI METCALF-GREEN VALLEY RPLC HRDT | ICQ
LC | 120589877 | 008/055 | T2 DI METCALF-MORGAN HILL RPLC INSS | MOSSLNDG | ETL.2570.INSL.CERA | 2021-03-02 | 2021-03-01 | 2021-05-09 | 2022-03-01 | 2022-03-01 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31531775 | T2 DI METCALF-MORGAN HILL RPLC INSS 2TWR | 93K
LC | 120590300 | 006/073 | T2 MTN GATE JCT-CASCADE 6/73 REFRAME | TABLEMTN | ETL.7640.POLE.WOOD | 2021-03-02 | 2021-03-02 | 2022-04-29 | 2022-03-02 | 2022-03-02 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31532670 | T2 MTN GATE JCT-CASCADE 6/73 REFRAME | 93E
LC | 120590667 | 037/272 | T2 CARIBOU-TABLE MTN 37/272 ROAD | TABLEMTN | ETL.4440.TOWR | 2021-03-02 | 2021-03-02 | 2021-02-15 | 2022-03-02 | 2022-03-02 | On-time | 374 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Road | Install | 31535140 | T2 CARIBOU-TABLE MTN 37/272 INST RD | 71Y
LC | 120591058 | 044/199 | T2 ROUND MTN-TBL MTN #1 44/199 REPL INSS | TABLEMTN | ETL.6060.TOWR | 2021-03-02 | 2021-03-02 | 2022-05-16 | 2022-03-02 | 2022-03-02 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533505 | T2 ROUND MTN-TBL MTN #1 44/199 REPL INSS | 93K
LC | 120591130 | 007/148 | T2 CNTRVLE-TBL MTN-ORVL 7/148 REPL POLE | TABLEMTN | ETL.6330.POLE.WOOD | 2021-03-02 | 2021-03-02 | 2021-08-23 | 2022-03-02 | 2022-03-02 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31514627 | CENTRVLL-TBL MTN-ORVLL 13/260 RPLC STRW | 70Y
LC | 120592732 | 015/183C | WV T2 KESWICK-TRINITY 15/183C REPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2021-03-02 | 2021-03-02 | 2021-08-16 | 2022-03-02 | 2022-03-02 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31422860 | T3 EI KESWICK-TRINITY 003/055 RPL PL | 70Y
LC | 120592733 | 015/183A | WV T2 KESWICK-TRINITY 15/183A REPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2021-03-02 | 2021-03-02 | 2021-08-16 | 2022-03-02 | 2022-03-02 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31422860 | T3 EI KESWICK-TRINITY 003/055 RPL PL | 70Y
LC | 120592734 | 015/183B | WV T2 KESWICK-TRINITY 15/183B REPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2021-03-02 | 2021-03-02 | 2021-08-16 | 2022-03-02 | 2022-03-02 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31422860 | T3 EI KESWICK-TRINITY 003/055 RPL PL | 70Y
LC | 120592786 | 005/105 | WV T2 HAT CREEK #1-WESTWD 5/105 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2021-03-02 | 2021-03-02 | 2021-05-07 | 2022-03-02 | 2022-03-02 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Crossarm-Wood | Repair
LC | 120596867 | 003/084 | WV T2 COLGATE-GRS VLY 3/84 INST DAM CPT | SACTO | ETL.6490.POLE.NWOD | 2021-03-03 | 2021-03-03 | 2022-07-20 | 2022-03-03 | 2022-03-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE SR22 | Missing | Damper-Wood | Install | 44698252 | WV T2 COLGATE-GRASS VALLEY 3/84 INST DAM | ICW
LC | 120600576 | 058/008 | T2 ELK-GUALALA 58/8 REPL ANCW | LAKEVLLE | ETL.8410.POLE.WOOD | 2021-03-03 | 2021-03-03 | 2022-01-21 | 2022-03-03 | 2022-03-03 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31532675 | T2 ELK-GUALALA 58/8 REPL ANCW | 93E
LC | 120604032 | 017/084 | T2 WV TULACAY-VACA 17/084 INST DAMPS | LAKEVLLE | ETL.5800.INSL | 2021-03-04 | 2021-03-04 | 2022-09-15 | 2022-03-04 | 2022-03-04 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install | 45136638 | T2 WV TULACAY-VACA 17/084 INST DAMPS | ICS
LC | 120606911 | 030/000 | WV T2 COALINGA #1-SAN MIGUEL 30/0 RPR TW | PISMOBCH | ETL.8580.TOWR | 2021-03-05 | 2021-03-05 | 2022-07-28 | 2022-03-05 | 2022-03-05 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 44691151 | WV T2 COALINGA #1-SAN MIGUEL 30/0 RPR TW | ICQ
LC | 120611468 | 009/010 | T2 FULTON-HOPLAND 9/010 REPL INSW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-03-08 | 2021-03-08 | 2021-03-12 | 2022-03-08 | 2022-03-08 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31532704 | T2 FULTON-HOPLAND 9/010 REPL INSW | 93I
LC | 120612734 | 037/001 | T2 FORT ROSS-GUALALA 37/1 REPL CROSSARM | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-03-08 | 2021-03-08 | 2021-08-14 | 2022-03-08 | 2022-03-08 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31532800 | T2 FORT ROSS-GUALALA 37/1 REPL CROSSARM | 93E
LC | 120616932 | 010/009 | T2 FULTON-HOPLAND 10/9 REPL ANCW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-03-09 | 2021-03-09 | 2021-07-15 | 2022-03-09 | 2022-03-09 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31535429 | T2 EI FULTON-HOPLAND 13/2 RPL ANCW | 93E
LC | 120629133 | 035/297 | T2 RND MTN-COTTONWD #3 035/297 RPR FOND | TABLEMTN | ETL.5650.TOWR | 2021-03-10 | 2021-02-21 | 2022-01-25 | 2022-02-21 | 2022-02-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45110444 | T2 RND MTN-COTTONWD #3 035/297 RPR FOND | ICQ
LC | 120632716 | C025/101 | T2 COBURN-LAS AGUILS SS C25/101 REPL INS | MOSSLNDG | ETL.4460.INSL | 2021-03-10 | 2021-03-10 | 2021-04-29 | 2022-03-10 | 2022-03-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533280 | T2 COBURN-LAS AGUILS SS REPL INS | 93K
LC | 120634950 | 008/039 | T2 DI MORRO BAY-MESA 008/039 RMV STEPS | PISMOBCH | ETL.5290.TOWR | 2021-03-11 | 2021-03-11 | 2021-09-12 | 2022-03-11 | 2022-03-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 44691154 | T2 DI MORRO BAY-MESA 008/039 RMV STEPS | ICQ
LC | 120634951 | 033/149 | T2 DI DIABLO-MESA 033/149 RPR INSS | PISMOBCH | ETL.4620.INSL | 2021-03-11 | 2021-03-11 | 2022-06-24 | 2022-03-11 | 2022-03-11 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45098617 | T2 DI DIABLO-MESA 033/149 RPR INSS | ICS
LC | 120640162 | 052/214 | T2 WV MIDWAY-WHIRLWIND 52/214 REPL INSS | MIDWAY | ETL.6030.INSL | 2021-03-12 | 2021-03-12 | 2022-03-08 | 2022-03-12 | 2022-03-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514956 | T2 MIDWAY-WHIRLWIND RPL INSS | 93K
LC | 120644342 | 006/001 | T2 EI DUNLAP 006/001 REPULL GUY | FRESNO | ETL.9061.POLE.WOOD | 2021-03-15 | 2021-03-15 | 2022-08-25 | 2022-03-15 | 2022-03-15 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45073692 | T2 EI DUNLAP 006/001 REPULL GUY | ICW
LC | 120646576 | 028/122 | T2 DI DIABLO-MESA 028/122 RPL INSS | PISMOBCH | ETL.4620.INSL | 2021-03-16 | 2021-03-12 | 2022-12-20 | 2022-03-12 | 2022-03-12 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534103 | T2 DI DIABLO-MESA 18/79 RPLC INSS 6TWRS | 93K
LC | 120647984 | B025/574 | T2 EI DRM-GRSS VLLEY-WEIMAR B025/574 VEG | SACTO | ETL.6760.POLE.WOOD | 2021-03-16 | 2021-03-16 | 2022-03-04 | 2022-03-16 | 2022-03-16 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Trim
LC | 120648047 | 021/181 | T2 EI CRAG VIEW-CASCADE 21/181 RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-03-16 | 2021-03-16 | 2021-06-16 | 2022-03-16 | 2022-03-16 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 44860243 | T2 EI CRAG VIEW-CASCADE 21/181 RPR GYWW | ICS
LC | 120648165 | 021/181 | T2 EI DELTA-COTTONWOOD 21/181 RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-03-16 | 2021-03-16 | 2021-06-16 | 2022-03-16 | 2022-03-16 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 44860244 | T2 EI DELTA-COTTONWOOD 21/181 RPR GYWW | ICS
LC | 120648767 | 010/066 | T2 DI MTCALF-GRN VALLEY 010/066 RPL INSS | MOSSLNDG | ETL.2540.INSL.CERA | 2021-03-16 | 2021-03-16 | 2021-06-02 | 2022-03-16 | 2022-03-16 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31531727 | DI METCALF-GREEN VALLEY RPLC INSS 6TWR | 93K
LC | 120649058 | :002/014 | T2 EI ROCK CREEK-POE 2/14 RPR STRT | TABLEMTN | ETL.5630.TOWR | 2021-03-16 | 2021-03-16 | 2022-08-04 | 2022-03-16 | 2022-03-16 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | Anti-Climbing Guard | Structure-Tower | Repair | 45404467 | T2 EI ROCK CREEK-POE 2/14 RPR STRT | ICQ
LC | 120649103 | :001/008 | T2 EI ROCK CREEK-POE 1/8 RPR STRT | TABLEMTN | ETL.5630.TOWR | 2021-03-16 | 2021-03-16 | 2022-08-07 | 2022-03-16 | 2022-03-16 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45401764 | T2 EI ROCK CREEK-POE 1/8 RPR STRT | ICQ
LC | 120652240 | 024/158 | T2 DI HELMS-GREGG #1 24/158 RPLC INSS | FRESNO | ETL.4870.INSL | 2021-03-17 | 2021-03-16 | 2022-08-23 | 2022-03-16 | 2022-03-16 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533801 | T2 DI HELMS-GREGG #1 RPLC INSS 9 TWRS | 93K
LC | 120652796 | 012/079 | T2 DI METCALF-GRN VALLEY 12/79 RPLC INSW | MOSSLNDG | ETL.2540.INSL.NCER | 2021-03-17 | 2021-03-16 | 2021-07-21 | 2022-03-16 | 2022-03-16 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31534650 | T2 DI METCALF-GRN VALLEY 12/79 RPLC INSW | 93I
LC | 120653747 | 001/014 | T2 EI TRNTY CTTNWOOD 1/14L RPR COND | TABLEMTN | ETL.4040.POLE.STPS | 2021-03-17 | 2021-03-17 | 2021-10-01 | 2022-03-17 | 2022-03-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair | 44905921 | T2 EI TRNTY CTTNWOOD 1/14 RPR COND | ICW
LC | 120654091 | 012/085 | T2 DI METCALF-GREEN VLLY 12/85 RPR CRSW | MOSSLNDG | ETL.2540.POLE.NWOD | 2021-03-17 | 2021-03-16 | 2021-05-25 | 2022-03-16 | 2022-03-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Repair | 44805589 | T2 DI METCALF-GREEN VLLY 12/85 RPR CRSW | ICW
LC | 120654108 | 008/108 | T2 IGNACIO-BOLINAS #2 8/108 RPL INSW | LAKEVLLE | ETL.7180.INSL.CERA | 2021-03-17 | 2021-03-17 | 2022-06-22 | 2022-03-17 | 2022-03-17 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31533724 | T2 IGNACIO-BOLINAS #2 8/108 RPL INSW | 93I
LC | 120654267 | 054/007 | T2 FORT ROSS-GUALALA 54/7 REFRAME | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-03-17 | 2021-03-17 | 2021-08-13 | 2022-03-17 | 2022-03-17 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31533726 | T2 FORT ROSS-GUALALA 54/7 REFRAME | 93E
LC | 120657047 | 044/212 | T2 EI IGNACIO-SOBRANTE 044/212 RPR FOND | CONCORD | ETL.4920.TOWR | 2021-03-18 | 2021-03-18 | 2022-02-25 | 2022-03-18 | 2022-03-18 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45168434 | T2 EI IGNACIO-SOBRANTE 044/212 RPR FOND | ICQ
LC | 120658281 | 001/010 | T2 EI KANAKA TAP 1/010B RPR GYWW | TABLEMTN | ETL.4223.POLE.WDPS | 2021-03-18 | 2021-03-18 | 2022-06-04 | 2022-03-18 | 2022-03-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45212388 | T2 EI KANAKA TAP 1/010B RPR GYWW | ICW
LC | 120658283 | 001/010A | T2 EI KANAKA TAP 1/010A RPL GYWW | TABLEMTN | ETL.4223.POLE.WOOD | 2021-03-18 | 2021-03-18 | 2022-06-04 | 2022-03-18 | 2022-03-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45212390 | T2 EI KANAKA TAP 1/010A RPL GYWW | ICW
LC | 120658647 | 001/012 | T2 EI KANAKA TAP 001/012L RPL STRW | TABLEMTN | ETL.4223.POLE.WDPS | 2021-03-18 | 2021-03-18 | 2022-06-03 | 2022-03-18 | 2022-03-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544831 | T2 EI KANAKA TAP 001/012B RPL STRW | 70Y
LC | 120659403 | 026/125 | T2 CORTINA-MENDOCINO #1 26/125 SW PLAT | LAKEVLLE | ETL.1330.TOWR | 2021-03-18 | 2021-03-18 | 2021-06-14 | 2022-03-18 | 2022-03-18 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair | 44772907 | T2 CORTINA-MENDOCINO #1 26/125 SW PLAT | ICQ
LC | 120659655 | 019/164 | T2 EI CRAG VIEW-CSCDE 19/164R RPR HDWW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-18 | 2021-03-18 | 2021-06-15 | 2022-03-18 | 2022-03-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44860241 | T2 EI CRAG VIEW-CSCDE 19/164R RPR HDWW | ICW
LC | 120659729 | 019/164 | T2 EI CRAG VIEW-CSCDE 19/164L RPR HDWW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-18 | 2021-03-18 | 2021-06-15 | 2022-03-18 | 2022-03-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44860242 | T2 EI CRAG VIEW-CSCDE 19/164L RPR HDWW | ICW
LC | 120660125 | 004/097 | T2 WV KILARC-DESCHUTES 04/097 INST DAMP | TABLEMTN | ETL.7300.INSL.NCER | 2021-03-18 | 2021-03-18 | 2022-04-18 | 2022-03-18 | 2022-03-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 44903366 | T2 WV KILARC-DESCHUTES 04/097 INST DAMP | ICW
LC | 120660280 | 019/401 | T2 WV KILARC-DESCHUTES 019/401 RPL PL | TABLEMTN | ETL.7300.POLE.WOOD | 2021-03-18 | 2021-03-18 | 2022-04-18 | 2022-03-18 | 2022-03-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31532667 | T2 KILARC-DESCHUTES 2/046 REPL POLE | 70Y
LC | 120662493 | 003/025 | T2 EI TRINITY-COTTONWOOD 3/25 RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-03-19 | 2021-03-19 | 2021-09-03 | 2022-03-19 | 2022-03-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 44873891 | T2 EI TRINITY-COTTONWOOD 3/25 RPR GYWW | ICS
LC | 120662770 | 003/026 | T2 EI TRINITY-CTTNWD 3/26 RPL STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-03-19 | 2021-03-19 | 2021-09-17 | 2022-03-19 | 2022-03-19 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31508137 | T3 DI TRINITY-CTTNWD 11/92 RPL STRW(ENG) | 70Y
LC | 120663373 | 006/053 | EI T2 PARDISE-TABLE MTN 006/053 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-03-19 | 2021-03-19 | 2021-07-16 | 2022-03-19 | 2022-03-19 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120663463 | 006/052 | T2 EI PARADISE-TABLE MT 06/052 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-03-19 | 2021-03-19 | 2021-07-14 | 2022-03-19 | 2022-03-19 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120663491 | 005/051 | T2 EI PARADISE-TABLE MT 05/051 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-03-19 | 2021-03-19 | 2021-07-13 | 2022-03-19 | 2022-03-19 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120663527 | 004/030 | T2 EI TRINITY-CTTNWD 4/30 RPR HDWW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-03-19 | 2021-03-19 | 2021-08-28 | 2022-03-19 | 2022-03-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44873985 | T2 EI TRINITY-CTTNWD 4/30 RPR HDWW | ICW
LC | 120663582 | 005/050 | T2 EI PARADISE-TABLE MTN 5/50 RPL INSLS | TABLEMTN | ETL.4316.INSL.CERA | 2021-03-19 | 2021-03-19 | 2021-06-23 | 2022-03-19 | 2022-03-19 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120663624 | 029/177 | T2 DI HELMS-GREGG #1 029/177 RMV NEST | FRESNO | ETL.4870.TOWR | 2021-03-19 | 2021-03-19 | 2022-08-23 | 2022-03-19 | 2022-03-19 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45067693 | T2 DI HELMS-GREGG #1 029/177 RMV NEST | ICS
LC | 120663700 | 000/003B | T2 EI KANAKA TAP 0/3B RPR JMPRW COMPLETE | TABLEMTN | ETL.4223.INSL.NCER | 2021-03-19 | 2021-03-19 | 2022-06-03 | 2022-03-19 | 2022-03-19 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Jumper-Wood | Repair | 45212391 | T2 EI KANAKA TAP 0/3B RPR JMPRW | ICW
LC | 120664092 | 018/156 | T2 EI CRAG VIEW-CASCADE 18/156 RPR HDWW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-19 | 2021-03-19 | 2021-06-15 | 2022-03-19 | 2022-03-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44860240 | T2 EI CRAG VIEW-CASCADE 18/156 RPR HDWW | ICW
LC | 120666972 | 004/037 | T2 EI CTRINITY-CTTNWD 14/37L RPL POLE | TABLEMTN | ETL.4040.POLE.WDPS | 2021-03-20 | 2021-03-20 | 2021-09-19 | 2022-03-20 | 2022-03-20 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31508137 | T3 DI TRINITY-CTTNWD 11/92 RPL STRW(ENG) | 70Y
LC | 120666974 | 004/037 | T2 EI TRINITY-COTTONWOOD 4/37R REPL POLE | TABLEMTN | ETL.4040.POLE.WDPS | 2021-03-20 | 2021-03-20 | 2021-09-19 | 2022-03-20 | 2022-03-20 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31508137 | T3 DI TRINITY-CTTNWD 11/92 RPL STRW(ENG) | 70Y
LC | 120667005 | 004/037 | T2 EI TRINITY-COTTONWD 4/37C REPL POLE | TABLEMTN | ETL.4040.POLE.WDPS | 2021-03-20 | 2021-03-20 | 2021-09-19 | 2022-03-20 | 2022-03-20 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31508137 | T3 DI TRINITY-CTTNWD 11/92 RPL STRW(ENG) | 70Y
LC | 120667197 | 018/154 | T2 EI CRAG VIEW-CASCAD 18/154 INST JUMPR | TABLEMTN | ETL.1350.INSL.CERA | 2021-03-20 | 2021-03-20 | 2021-07-30 | 2022-03-20 | 2022-03-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Jumper-Wood | Repair | 44860238 | T2 EI CRAG VIEW-CASCAD 18/154 INST JUMPR | ICW
LC | 120667415 | 016/304 | T2 EI FLTN-MOLINO-COTATI 16/304 RPR GYWW | LAKEVLLE | ETL.6910.POLE.WOOD | 2021-03-20 | 2021-03-20 | 2022-02-03 | 2022-03-20 | 2022-03-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45138289 | T2 EI FLTN-MOLINO-COTATI 16/304 RPR GYWW | ICW
LC | 120667683 | 005/040 | T2 EI TRINITY-COTTNWD 5/040 UNBURY ANCW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-03-20 | 2021-03-20 | 2021-08-29 | 2022-03-20 | 2022-03-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 44873987 | T2 EI TRINITY-COTTNWD 5/040 UNBURY ANCW | ICW
LC | 120667992 | 015/130 | T2 EI CRAG VIEW-CASCADE 15/130 REPLUMB | TABLEMTN | ETL.1350.INSL.CERA | 2021-03-20 | 2021-03-20 | 2021-07-28 | 2022-03-20 | 2022-03-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44860237 | T2 EI CRAG VIEW-CASCADE 15/130 REPLUMB | ICW
LC | 120668065 | 005/041 | T2 EI TRINITY-CTTNWD 5/41 RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-03-20 | 2021-03-20 | 2021-08-30 | 2022-03-20 | 2022-03-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873893 | T2 EI TRINITY-CTTNWD 5/41 RPR GYWW | ICW
LC | 120668107 | 005/041 | T2 EI TRINITY-COTTONWD 5/41 RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-03-20 | 2021-03-20 | 2021-08-29 | 2022-03-20 | 2022-03-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873894 | T2 EI TRINITY-COTTONWD 5/41 RPR GYWW | ICW
LC | 120669649 | 009/115 | T2 COLGATE-SMARTVILLE #2 9/115 RPL INSS | SACTO | ETL.6520.INSL.NCER | 2021-03-21 | 2021-03-19 | 2021-05-28 | 2022-03-19 | 2022-03-19 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31534159 | T2 COLGATE-SMARTVILLE #2 9/115 RPL INSS | 93I
LC | 120670181 | 004/114 | T2 COLGATE-GRASS VALLEY 004/114 RPL PL | SACTO | ETL.6490.POLE.WOOD | 2021-03-21 | 2021-03-19 | 2022-08-09 | 2022-03-19 | 2022-03-19 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31534577 | T2 COLGATE-GRASS VALLEY 004/114 RPL PL | 70Y
LC | 120670182 | 003/071 | T2 COLGATE-GRASS VALLEY 003/071 REFRAME | SACTO | ETL.6490.POLE.WOOD | 2021-03-21 | 2021-03-21 | 2022-08-09 | 2022-03-21 | 2022-03-21 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31534019 | T2 COLGATE-GRASS VALLEY 003/071 REFRAME | 93E
LC | 120670183 | 002/069 | T2 COLGATE-GRASS VALLEY 002/069 REFRAME | SACTO | ETL.6490.POLE.WOOD | 2021-03-21 | 2021-03-19 | 2022-08-09 | 2022-03-19 | 2022-03-19 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW PATR COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31534019 | T2 COLGATE-GRASS VALLEY 003/071 REFRAME | 93E
LC | 120670184 | 010/127 | T2 COLGATE-SMARTVILLE #1 010/127L RPL PL | SACTO | ETL.6510.POLE.WDPS | 2021-03-21 | 2021-03-19 | 2022-07-26 | 2022-03-19 | 2022-03-19 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31534304 | T2 COLGATE-SMARTVILLE #1 010/127L RPL PL | 70Y
LC | 120670185 | 000/008 | T2 NARROWS #1 TAP 0/8 RPL STRW | SACTO | ETL.6511.POLE.WOOD | 2021-03-21 | 2021-03-19 | 2022-08-29 | 2022-03-19 | 2022-03-19 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31603778 | T2 NARROWS #1 TAP 0/8 RPL STRW | 70Y
LC | 120670231 | 001/014 | T2 NARRWS #2 TAP 001/014 COMPLETE | SACTO | ETL.6521.POLE.WOOD | 2021-03-21 | 2021-03-19 | 2022-06-03 | 2022-03-19 | 2022-03-19 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31535161 | T2 NARRWS #2 TAP 001/014 RPL CRSW | 93E
LC | 120671479 | 023/179 | T2 DI PARADISE-TABLE MTN 23/179 RPL INSS | TABLEMTN | ETL.4316.INSL | 2021-03-22 | 2021-03-16 | 2021-07-31 | 2022-03-16 | 2022-03-16 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31534015 | T2 DI PARADISE-TABLE MTN 023/179 RPL INS | 93I
LC | 120672061 | 004/034 | T2 EI TRINITY-COTTNWD 4/034R RPL POLE | TABLEMTN | ETL.4040.POLE.WDPS | 2021-03-22 | 2021-03-22 | 2021-09-11 | 2022-03-22 | 2022-03-22 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31577970 | T2 TRINITY-COTTNWD 4/31R RPL STRW | 70Y
LC | 120672114 | 015/128 | T2 EI CRAG VIEW-CSCDE 015/128R RPR GYWW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-22 | 2021-03-22 | 2021-07-28 | 2022-03-22 | 2022-03-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44860235 | T2 EI CRAG VIEW-CSCDE 015/128R RPR GYWW | ICW
LC | 120672120 | 012/080 | T2 DI METCLF-GREEN VALLY 12/80 RPL INSS | MOSSLNDG | ETL.2540.INSL.CERA | 2021-03-22 | 2021-03-16 | 2021-07-21 | 2022-03-16 | 2022-03-16 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31534650 | T2 DI METCALF-GRN VALLEY 12/79 RPLC INSW | 93I
LC | 120672123 | 012/080 | T2 DI MTCLF-GREEN VALLY 12/80 RPR GYWW | MOSSLNDG | ETL.2540.POLE.WOOD | 2021-03-22 | 2021-03-16 | 2021-07-21 | 2022-03-16 | 2022-03-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44805598 | T2 DI MTCLF-GREEN VALLY 12/80 RPR GYWW | ICW
LC | 120672148 | 015/128 | T2 EI CRAG VIEW-CASCADE 015/128 RPR GYWW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-22 | 2021-03-22 | 2021-07-28 | 2022-03-22 | 2022-03-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44860236 | T2 EI CRAG VIEW-CASCADE 015/128 RPR GYWW | ICW
LC | 120672348 | 021/296 | T2 EI SQC-SNT YNZ SW ST 21/296 RPR JMPRW | PISMOBCH | ETL.3700.INSL.CERA | 2021-03-22 | 2021-03-22 | 2022-06-28 | 2022-03-22 | 2022-03-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Jumper-Wood | Repair | 45069111 | T2 EI SQC-SNT YNZ SW ST 21/296 RPR JMPRW | ICW
LC | 120672818 | 015/127 | T2 EI CRAG VW-CASCADE 15/127 RPR ANCHW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-22 | 2021-03-22 | 2021-07-23 | 2022-03-22 | 2022-03-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 44860233 | T2 EI CRAG VW-CASCADE 15/127 RPR ANCHW | ICW
LC | 120672962 | 015/127 | T2 EI CRAG VIEW-CASCADE 15/127 RPR GYWW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-22 | 2021-03-22 | 2021-07-22 | 2022-03-22 | 2022-03-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44860234 | T2 EI CRAG VIEW-CASCADE 15/127 RPR GYWW | ICW
LC | 120673447 | 009/041 | T2 EI DIABLO-GATES #1 009/041 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2021-03-22 | 2021-03-22 | 2022-06-09 | 2022-03-22 | 2022-03-22 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 44859533 | T2 EI DIABLO-GATES #1 009/041 RPR GYWS | ICS
LC | 120674511 | 021/097 | T2 DI TASSAJARA-NEWARK 21/97 REPL HANGR | CONCORD | ETL.5920.INSL | 2021-03-22 | 2021-03-22 | 2021-08-11 | 2022-03-22 | 2022-03-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44758700 | T2 DI TASSAJARA-NEWARK 21/97 REPL HANGR | ICQ
LC | 120675004 | 002/054 | T2 WEIMAR-HALSEY 2/054 REFRAME | SACTO | ETL.8340.POLE.WOOD | 2021-03-22 | 2021-03-22 | 2022-03-06 | 2022-03-22 | 2022-03-22 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31534017 | T2 WEIMAR-HALSEY 2/054 REFRAME | 93E
LC | 120675012 | 001/031 | T2 SMARTVILLE-CAMP FAR WEST 01/31 RPL PL | SACTO | ETL.7970.POLE.WOOD | 2021-03-22 | 2021-03-22 | 2022-07-12 | 2022-03-22 | 2022-03-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535917 | SMARTVILLE-CAMP FAR WEST 8/160 RPL PL | 70Y
LC | 120675015 | 000/019 | T2 WEIMAR-HALSEY 0/19 RPL PL | SACTO | ETL.8340.POLE.WOOD | 2021-03-22 | 2021-03-22 | 2021-06-18 | 2022-03-22 | 2022-03-22 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31534016 | T2 WEIMAR-HALSEY 0/19 RPL PL | 70Y
LC | 120675018 | 004/094 | T2 WEIMAR-HALSEY 4/94 RPL PL | SACTO | ETL.8340.POLE.WOOD | 2021-03-22 | 2021-03-22 | 2021-08-29 | 2022-03-22 | 2022-03-22 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31534016 | T2 WEIMAR-HALSEY 0/19 RPL PL | 70Y
LC | 120677192 | 013/194 | T2 DI SSQC-SNT YNZ SW ST 13/194 RPR GYWW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-23 | 2021-03-22 | 2022-04-12 | 2022-03-22 | 2022-03-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069114 | T2 DI SSQC-SNT YNZ SW ST 13/194 RPR GYWW | ICW
LC | 120677271 | 005/099 | T2 DI SISQUOC-SANTA YNEZ 5/99 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-23 | 2021-03-22 | 2021-11-15 | 2022-03-22 | 2022-03-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44963125 | T2 DI SISQUOC-SANTA YNEZ 5/99 RPR STRW | ICW
LC | 120677272 | 005/099 | T2 DI SISQUOC-SANTA YNEZ 5/99 RPR SPLW | PISMOBCH | ETL.3700.INSL.CERA | 2021-03-23 | 2021-03-22 | 2021-11-15 | 2022-03-22 | 2022-03-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 44963135 | T2 DI SISQUOC-SANTA YNEZ 5/99 RPR SPLW | ICW
LC | 120677846 | 024/385 | T2 KESWICK-TRINITY 24/385 RMV VEG | TABLEMTN | ETL.7270.POLE.WOOD | 2021-03-23 | 2021-03-23 | 2021-10-22 | 2022-03-23 | 2022-03-23 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120679216 | 037/171 | T2 EI IGNACIO-SOBRANTE 037/171 RPL INSS | LAKEVLLE | ETL.4920.INSL.CERA | 2021-03-23 | 2021-03-23 | 2022-11-04 | 2022-03-23 | 2022-03-23 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31531905 | DI IGNACIO SOBRANTE RPL INSS 5 TWRS | 93K
LC | 120679682 | 004/022 | T2 DI VASONA-METCALF 4/22 RPR FOND | METCALF | ETL.5932.TOWR | 2021-03-23 | 2021-03-22 | 2022-05-16 | 2022-03-22 | 2022-03-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45233304 | T2 DI VASONA-METCALF 4/22 RPR FOND | ICQ
LC | 120679687 | 015/219 | T2 DI SQC-ST YNZ SW ST 15/219 RPL STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-23 | 2021-03-22 | 2022-04-16 | 2022-03-22 | 2022-03-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE CNCL OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31534654 | T2 DI SQC-ST YNZ SW ST 15/219 RPL STRW | 70Y
LC | 120679751 | 007/058 | T2 EI TRNTY-CTTNWD 7/58L INST HDWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-03-23 | 2021-03-23 | 2021-10-03 | 2022-03-23 | 2022-03-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Missing | Hardware-Wood | Install | 44905922 | T2 EI TRNTY-CTTNWD 7/58L INST HDWW | ICW
LC | 120679776 | 005/097 | T2 DI SSQC-SNT YNEZ SW STA 5/97 RPL HRDD | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-23 | 2021-03-22 | 2021-11-15 | 2022-03-22 | 2022-03-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44963129 | T2 DI SSQC-SNT YNEZ SW STA 5/97 RPL HRDD | ICW
LC | 120679882 | 036/168 | T2 EI IGNACIO-SOBRANTE 036/168 RPR CNDS | LAKEVLLE | ETL.4960.INSL | 2021-03-23 | 2021-03-23 | 2022-04-27 | 2022-03-23 | 2022-03-23 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45144138 | T2 EI IGNACIO-SOBRANTE 036/168 RPR CNDS | ICS
LC | 120679888 | 007/058 | T2 EI TRNTY-CTTNWD 7/58R INST HDWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-03-23 | 2021-03-23 | 2021-10-03 | 2022-03-23 | 2022-03-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Missing | Hardware-Wood | Install | 44905923 | T2 EI TRNTY-CTTNWD 7/58R INST HDWW | ICW
LC | 120679938 | 015/223 | T2NT DI SQC-SNT YNZ SW ST 15/223 RMV DB | PISMOBCH | ETL.3700.POLE.NWOD | 2021-03-23 | 2021-03-22 | 2022-02-01 | 2022-03-22 | 2022-03-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2N PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45069116 | T2NT DI SQC-SNT YNZ SW ST 15/223 RMV DB | ICW
LC | 120680250 | 009/081 | T2 EI EL DRD-MSSRI FLT #1 9/81 RPR STRW | SACTO | ETL.1530.POLE.WOOD | 2021-03-23 | 2021-03-23 | 2022-06-24 | 2022-03-23 | 2022-03-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44711563 | T2 EI EL DRD-MSSRI FLT #1 9/81 RPR STRW | ICW
LC | 120680662 | 055/384 | T2 DI CARIBOU-TABLE MTN 55/384 RPLC INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-03-23 | 2021-03-22 | 2022-06-18 | 2022-03-22 | 2022-03-22 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 120680712 | 014/119 | T2 EI CRG VW-CASCADE 14/119 RPR INSLS | TABLEMTN | ETL.1350.INSL.NCER | 2021-03-23 | 2021-03-23 | 2021-07-29 | 2022-03-23 | 2022-03-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44860230 | T2 EI CRG VW-CASCADE 14/119 RPR INSLS | ICW
LC | 120680714 | 014/120 | T2 EI CRAG VIEW-CASCADE 14/120 RPR INSLS | TABLEMTN | ETL.1350.INSL.NCER | 2021-03-23 | 2021-03-23 | 2021-07-29 | 2022-03-23 | 2022-03-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44860231 | T2 EI CRAG VIEW-CASCADE 14/120 RPR INSLS | ICW
LC | 120680761 | 005/090 | T2 DI SISQUOC-SANTA YNEZ 5/90 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-23 | 2021-03-22 | 2021-11-15 | 2022-03-22 | 2022-03-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44963133 | T2 DI SISQUOC-SANTA YNEZ 5/90 RPR STRW | ICW
LC | 120680794 | 010/127 | T2 COLGATE-SMARTVILLE #1 010/127R RPL PL | SACTO | ETL.6510.POLE.WDPS | 2021-03-23 | 2021-03-19 | 2022-07-26 | 2022-03-19 | 2022-03-19 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31534304 | T2 COLGATE-SMARTVILLE #1 010/127L RPL PL | 70Y
LC | 120680831 | 010/127 | T2 COLGATE-SMARTVILLE #1 010/127C RPL PL | SACTO | ETL.6510.POLE.WDPS | 2021-03-23 | 2021-03-19 | 2022-07-26 | 2022-03-19 | 2022-03-19 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31534304 | T2 COLGATE-SMARTVILLE #1 010/127L RPL PL | 70Y
LC | 120680882 | 004/033 | T2 PIT #4 TAP 4/33 RMV VEG | TABLEMTN | ETL.5432.TOWR | 2021-03-23 | 2021-03-23 | 2022-08-31 | 2022-03-23 | 2022-03-23 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120681256 | 010/003 | T2 EI FULTON-HOPLAND 10/3 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-03-23 | 2021-03-23 | 2021-08-02 | 2022-03-23 | 2022-03-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535421 | T2 EI FULTON-HOPLAND 10/3 RPL POLE | 70Y
LC | 120683563 | 013/198 | T2 DI SISQUOC-SANTA YNEZ 13/198 RPL INSW | PISMOBCH | ETL.3700.INSL.NCER | 2021-03-24 | 2021-03-22 | 2022-04-13 | 2022-03-22 | 2022-03-22 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31534653 | DI SSQC-SNT YNZ SW ST 001/034 RPL INSW | 93I
LC | 120683865 | 025/195 | T2 EI PARADISE-TBL MTN 25/195C RPR ANCHW | TABLEMTN | ETL.4316.POLE.STPS | 2021-03-24 | 2021-03-24 | 2021-07-29 | 2022-03-24 | 2022-03-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 44860248 | T2 EI PARADISE-TBL MTN 25/195M RPR ANCHW | ICW
LC | 120683877 | 025/195 | T2 EI PARADISE-TBL MTN 25/195R RPR GYWW | TABLEMTN | ETL.4316.POLE.STPS | 2021-03-24 | 2021-03-24 | 2021-07-29 | 2022-03-24 | 2022-03-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44860249 | T2 EI PARADISE-TBL MTN 25/195R RPR GYWW | ICW
LC | 120683905 | 025/195 | T2 EI PARADISE-TBL MTN 25/195R RPR ANCHW | TABLEMTN | ETL.4316.POLE.STPS | 2021-03-24 | 2021-03-24 | 2021-07-29 | 2022-03-24 | 2022-03-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 44860250 | T2 EI PARADISE-TBL MTN 25/195R RPR ANCHW | ICW
LC | 120683982 | 012/182 | T2 DI SISQUOC-SANTA YNEZ 12/182 RPL INSW | PISMOBCH | ETL.3700.INSL.CERA | 2021-03-24 | 2021-03-22 | 2022-04-12 | 2022-03-22 | 2022-03-22 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31534653 | DI SSQC-SNT YNZ SW ST 001/034 RPL INSW | 93I
LC | 120683984 | 012/182 | T2 DI SISQUOC-SANTA YNEZ 12/82 RPR GYWW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-24 | 2021-03-22 | 2022-04-12 | 2022-03-22 | 2022-03-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW TNT FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069117 | T2 DI SISQUOC-SANTA YNEZ 12/82 RPR GYWW | ICW
LC | 120684298 | 007/055 | T2 EI TRNTY-CTTNWD 7/55L RPL STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-03-24 | 2021-03-24 | 2021-10-04 | 2022-03-24 | 2022-03-24 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31508137 | T3 DI TRINITY-CTTNWD 11/92 RPL STRW(ENG) | 70Y
LC | 120684394 | 007/056 | T2 EI TRNTY-CTTNWD 7/056 RPR CONDW | TABLEMTN | ETL.4040.INSL.NCER | 2021-03-24 | 2021-03-24 | 2021-10-03 | 2022-03-24 | 2022-03-24 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Conductor-Steel | Repair | 44707044 | T2 EI TRNTY-CTTNWD 7/056 RPR CONDW | ICS
LC | 120685861 | 012/251 | T2 CLMN-STH 012/251 RPL CRSW COMPLETE | TABLEMTN | ETL.6450.POLE.WOOD | 2021-03-24 | 2021-03-24 | 2022-05-23 | 2022-03-24 | 2022-03-24 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31535114 | T2 CLMN-STH 012/251 RPL CRSW | 93E
LC | 120685862 | 008/069 | T2 EI TRNTY-CTTNWD 8/69L RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-03-24 | 2021-03-24 | 2021-08-30 | 2022-03-24 | 2022-03-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873895 | T2 EI TRNTY-CTTNWD 9/69L RPR GYWW | ICW
LC | 120685865 | 012/249 | T2 CLMN-STH 012/249 RPL STRW COMPLETE | TABLEMTN | ETL.6450.POLE.WOOD | 2021-03-24 | 2021-03-24 | 2022-05-23 | 2022-03-24 | 2022-03-24 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535111 | T2 CLMN-STH 012/248 RPL STRW | 70Y
LC | 120685868 | 012/248 | T2 CLMN-STH 012/248 RPL STRW CMPLTD | TABLEMTN | ETL.6450.POLE.WOOD | 2021-03-24 | 2021-03-24 | 2022-05-23 | 2022-03-24 | 2022-03-24 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535111 | T2 CLMN-STH 012/248 RPL STRW | 70Y
LC | 120685881 | 004/021 | T2 EI MORRO BAY-MESA 4/21 RPR STRT | PISMOBCH | ETL.5290.TOWR | 2021-03-24 | 2021-03-24 | 2022-06-15 | 2022-03-24 | 2022-03-24 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 44715208 | T2 EI MORRO BAY-MESA 4/21 RPR STRT | ICQ
LC | 120685887 | 008/069 | T2 EI TRNTY-CTTNWD 9/69R RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-03-24 | 2021-03-24 | 2021-08-29 | 2022-03-24 | 2022-03-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873896 | T2 EI TRNTY-CTTNWD 9/69R RPR GYWW | ICW
LC | 120686134 | 009/190 | T2 VOLTA-DESCHUTES 09/190 RPL PL | TABLEMTN | ETL.8290.POLE.WOOD | 2021-03-24 | 2021-03-24 | 2022-06-09 | 2022-03-24 | 2022-03-24 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535162 | T2 EI VOLTA-DESCHUTES 09/190 RPL PL | 70Y
LC | 120686381 | 020/080 | T2 DI PITTSBURG-SAN MATEO 20/80 RMV NEST | CONCORD | ETL.5463.TOWR | 2021-03-24 | 2021-03-23 | 2021-09-24 | 2022-03-23 | 2022-03-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44959028 | T2 DI PITTSBURG-SAN MATEO 20/80 RMV NEST | ICS
LC | 120686387 | 011/051 | T2 DI MORRO BAY-MESA 11/51 RPLC HRDT | PISMOBCH | ETL.5290.TOWR | 2021-03-24 | 2021-03-23 | 2022-06-16 | 2022-03-23 | 2022-03-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 44715207 | T2 DI MORRO BAY-MESA 11/51 RPLC HRDT | ICQ
LC | 120686462 | 003/028 | T2 EI CTTNWD-LGN CRK 003/028 RPL INSS | TABLEMTN | ETL.4570.INSL | 2021-03-24 | 2021-03-24 | 2022-03-16 | 2022-03-24 | 2022-03-24 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535731 | T2 EI CTTNWD-LGN CRK RPL INSS 8TWR | 93K
LC | 120686757 | 019/264 | T2 EI SQC-SNT YNZ SW STA 19/264 RPR GYWW | PISMOBCH | ETL.3700.POLE.NWOD | 2021-03-24 | 2021-03-24 | 2022-03-02 | 2022-03-24 | 2022-03-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069118 | T2 EI SQC-SNT YNZ SW STA 19/264 RPR GYWW | ICW
LC | 120686888 | 005/024 | T2 EI MORRO BAY-MESA 5/24 RPL INSLS | PISMOBCH | ETL.5290.INSL | 2021-03-24 | 2021-03-24 | 2022-06-21 | 2022-03-24 | 2022-03-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534504 | T2 EI MORRO BAY-MESA RPL INSLS 5TWRS | 93K
LC | 120687146 | 001/010 | T2 EI ROCK CREEK-POE 1/10 RPL INSS | TABLEMTN | ETL.5630.TOWR | 2021-03-24 | 2021-03-24 | 2022-08-06 | 2022-03-24 | 2022-03-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535387 | T2 EI ROCK CREEK-POE RPL INSS 7TWRS | 93K
LC | 120687543 | 006/110 | T2 DI SISQUOC-SANTA YNEZ 6/110 RPLC INSW | PISMOBCH | ETL.3700.INSL.CERA | 2021-03-24 | 2021-03-22 | 2022-04-11 | 2022-03-22 | 2022-03-22 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31534653 | DI SSQC-SNT YNZ SW ST 001/034 RPL INSW | 93I
LC | 120688944 | 021/144 | T2 HELMS-GREGG #1 21/144 RMV NEST | FRESNO | ETL.4870.TOWR | 2021-03-25 | 2021-03-24 | 2022-08-22 | 2022-03-24 | 2022-03-24 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45067694 | T2 HELMS-GREGG #1 21/144 RMV NEST | ICS
LC | 120688946 | 019/129 | T2 HELMS-GREGG #1 19/129 RMV NEST | FRESNO | ETL.4870.TOWR | 2021-03-25 | 2021-03-24 | 2022-08-22 | 2022-03-24 | 2022-03-24 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45067695 | T2 HELMS-GREGG #1 19/129 RMV NEST | ICS
LC | 120689105 | 011/011 | T2 EI FULTON-HOPLAND 11/11 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-03-25 | 2021-03-25 | 2021-08-03 | 2022-03-25 | 2022-03-25 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31535421 | T2 EI FULTON-HOPLAND 10/3 RPL POLE | 70Y
LC | 120689166 | 011/103 | T2 DI ELDRD-MSSRI FLT #1 11/103 RPL INSS | SACTO | ETL.1530.INSL | 2021-03-25 | 2021-03-24 | 2022-06-22 | 2022-03-24 | 2022-03-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535732 | T2 DI ELDRD-MSSRI FLT #1 RPL INSS 10TWRS | 93K
LC | 120689190 | 011/103 | T2 DI ELDRD-MSSRI FLT #2 11/103 RPR SPL | SACTO | ETL.1540.INSL | 2021-03-25 | 2021-03-24 | 2022-06-22 | 2022-03-24 | 2022-03-24 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 44711477 | T2 DI ELDRD-MSSRI FLT #2 11/103 RPR SPL | ICS
LC | 120689398 | 014/121 | T2 EI CRAG VIEW-CASCADE 014/121 RPR INSW | TABLEMTN | ETL.1350.INSL.NCER | 2021-03-25 | 2021-03-24 | 2021-07-29 | 2022-03-24 | 2022-03-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44860232 | T2 EI CRAG VIEW-CASCADE 014/121 RPR INSW | ICW
LC | 120689399 | 013/112B | T2 EI CRG VIEW-CASCADE 013/112B RPR GWRS | TABLEMTN | ETL.1350.POLE.NWOD | 2021-03-25 | 2021-03-24 | 2021-06-15 | 2022-03-24 | 2022-03-24 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 44860229 | T2 EI CRG VIEW-CASCADE 013/112B RPR GWRS | ICS
LC | 120689446 | 013/112A | T2 EI CRG VIEW-CASCADE 013/112A RPR GWRS | TABLEMTN | ETL.1350.POLE.NWOD | 2021-03-25 | 2021-03-24 | 2021-06-15 | 2022-03-24 | 2022-03-24 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 44860228 | T2 EI CRG VIEW-CASCADE 013/112A RPR GWRS | ICS
LC | 120689461 | 013/112C | T2 EI CRG VIEW-CASCADE 013/112C RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-03-25 | 2021-03-24 | 2021-06-15 | 2022-03-24 | 2022-03-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44947135 | T2 EI CRG VIEW-CASCADE 013/112C RPR GYWW | ICW
LC | 120689491 | 007/055 | T2 EI TRNTY-CTTNWOOD 7/55R RPL STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-03-25 | 2021-03-24 | 2021-10-04 | 2022-03-24 | 2022-03-24 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31508137 | T3 DI TRINITY-CTTNWD 11/92 RPL STRW(ENG) | 70Y
LC | 120689589 | 012/107 | T2 EI CRAG VIEW-CASCADE 012/107 RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-03-25 | 2021-03-25 | 2021-06-15 | 2022-03-25 | 2022-03-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44860226 | T2 EI CRAG VIEW-CASCADE 012/107 RPR GYWW | ICW
LC | 120689669 | C004/019 | T2 EI MSS LNDING-CBRN C004/019 RMV BRSH | MOSSLNDG | ETL.5330.TOWR | 2021-03-25 | 2021-03-24 | 2021-05-31 | 2022-03-24 | 2022-03-24 | On-time | 932 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Brush Fuel | Road | Remove
LC | 120689778 | 018/106 | T2 DI STANISLAUS-MNTC #2 18/106 INS BOLT | VICTOR | ETL.3820.TOWR | 2021-03-25 | 2021-03-24 | 2022-02-09 | 2022-03-24 | 2022-03-24 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45123111 | T2 DI STANISLAUS-MNTC #2 18/106 INS BOLT | ICQ
LC | 120689815 | 008/066 | T2EI TRINITY-COTTONWD 8/66 RPL STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-03-25 | 2021-03-25 | 2022-08-08 | 2022-03-25 | 2022-03-25 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31577970 | T2 TRINITY-COTTNWD 4/31R RPL STRW | 70Y
LC | 120690164 | :013/083 | T2 DI GREEN VLY-LLAGAS :13/83 RPLC INSS | MOSSLNDG | ETL.2800.INSL.CERA | 2021-03-25 | 2021-03-24 | 2022-06-21 | 2022-03-24 | 2022-03-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535376 | T2 DI GREEN VLY-LLAGAS RPLC INSS 3TWRS | 93K
LC | 120690575 | 009/147 | T2 DI SISQUOC-SANTA YNEZ 9/47 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-25 | 2021-03-25 | 2022-02-15 | 2022-03-25 | 2022-03-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069119 | T2 DI SISQUOC-SANTA YNEZ 9/47 RPR STRW | ICW
LC | 120690595 | 009/072A | T2EI TRINITY-COTTONWOOD 9/072A RPLC INSW | TABLEMTN | ETL.4040.INSL.NCER | 2021-03-25 | 2021-03-25 | 2021-10-04 | 2022-03-25 | 2022-03-25 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542630 | T2EI TRINITY-COTTONWOOD 9/072A RPLC INSW | 93I
LC | 120690613 | 009/072A | T2EI TRINITY-COTTONWOOD 9/072A RPR SPLC | TABLEMTN | ETL.4040.POLE.WOOD | 2021-03-25 | 2021-03-25 | 2021-10-04 | 2022-03-25 | 2022-03-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Splice-Wood | Repair | 44873991 | T2EI TRINITY-COTTONWOOD 9/072A RPR SPLC | ICW
LC | 120690639 | 018/260A | T2 EI SSQC-SNT YNZ SW 18/260A RPR ANCW | PISMOBCH | ETL.3700.POLE.NWOD | 2021-03-25 | 2021-03-25 | 2022-03-01 | 2022-03-25 | 2022-03-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45069140 | T2 EI SSQC-SNT YNZ SW 18/260A RPR ANCW | ICW
LC | 120690640 | 009/072B | T2EI TRINITY-COTTONWOOD 9/072B RPLC INSW | TABLEMTN | ETL.4040.INSL.NCER | 2021-03-25 | 2021-03-25 | 2021-10-04 | 2022-03-25 | 2022-03-25 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542630 | T2EI TRINITY-COTTONWOOD 9/072A RPLC INSW | 93I
LC | 120690660 | 018/260A | T2 EI SSQC-SNT YNZ SW 18/260A RPR STRW | PISMOBCH | ETL.3700.POLE.NWOD | 2021-03-25 | 2021-03-25 | 2022-03-01 | 2022-03-25 | 2022-03-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069141 | T2 EI SSQC-SNT YNZ SW 18/260A RPR STRW | ICW
LC | 120690696 | 009/072C | T2 EI TRINITY-COTTNWD 9/72C RPL INSW | TABLEMTN | ETL.4040.INSL.NCER | 2021-03-25 | 2021-03-25 | 2021-10-04 | 2022-03-25 | 2022-03-25 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542630 | T2EI TRINITY-COTTONWOOD 9/072A RPLC INSW | 93I
LC | 120690715 | 008/128 | T2 DI SSQC-SNT YNZ SW ST 8/128 RPR SPLW | PISMOBCH | ETL.3700.INSL.CERA | 2021-03-25 | 2021-03-25 | 2022-01-13 | 2022-03-25 | 2022-03-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45069142 | T2 DI SSQC-SNT YNZ SW ST 8/128 RPR SPLW | ICW
LC | 120690907 | 009/073A | T2 EI TRNTY-COTTONWD 009/073A ANC RPR | TABLEMTN | ETL.4040.POLE.NWOD | 2021-03-25 | 2021-03-25 | 2021-09-07 | 2022-03-25 | 2022-03-25 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair | 44873814 | T2 EI TRNTY-COTTONWD 009/073A ANC RPR | ICS
LC | 120690937 | 011/102 | T2 EI CRAG VIEW-CASCADE 011/102 RPR STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-25 | 2021-03-25 | 2021-06-15 | 2022-03-25 | 2022-03-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44860225 | T2 EI CRAG VIEW-CASCADE 011/102 RPR STRW | ICW
LC | 120690941 | 009/073B | T2 EI TRINITY-COTTONWOOD 9/73B RPR ANCH | TABLEMTN | ETL.4040.POLE.NWOD | 2021-03-25 | 2021-03-25 | 2021-09-07 | 2022-03-25 | 2022-03-25 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Steel | Repair | 44873816 | T2 EI TRINITY-COTTONWOOD 9/73B RPR ANCH | ICS
LC | 120690982 | 009/073C | T2 EI TRINITY-COTTONWOOD 009/073C ANC RP | TABLEMTN | ETL.4040.POLE.NWOD | 2021-03-25 | 2021-03-25 | 2021-09-15 | 2022-03-25 | 2022-03-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 44905924 | T2 EI TRINITY-COTTONWOOD 009/073C ANC RP | ICW
LC | 120690987 | 021/167 | T2 EI MDLE FRK-GLD HLL 021/167M RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2021-03-25 | 2021-03-25 | 2021-12-14 | 2022-03-25 | 2022-03-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44711476 | T2 EI MDLE FRK-GLD HLL 021/167M RPR GYWW | ICW
LC | 120691084 | 003/064 | T2 EI CLMN-CTTNWD 003/064 RPR STRW | TABLEMTN | ETL.6430.POLE.WOOD | 2021-03-25 | 2021-03-25 | 2021-06-16 | 2022-03-25 | 2022-03-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44859702 | T2 EI CLMN-CTTNWD 003/064 RPR STRW | ICW
LC | 120691151 | 025/167 | T2 EI POE-RIO OSO 25/167 INS HRDT | TABLEMTN | ETL.5540.TOWR | 2021-03-25 | 2021-03-25 | 2022-05-25 | 2022-03-25 | 2022-03-25 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Hardware-Tower | Install | 45198330 | T2 EI POE-RIO OSO 25/167 INS HRDT | ICQ
LC | 120691164 | 018/259 | T2 EI SSQC-SNT YNZ SW 18/259 RPR GYWW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-25 | 2021-03-25 | 2022-03-01 | 2022-03-25 | 2022-03-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069143 | T2 EI SSQC-SNT YNZ SW 18/259 RPR GYWW | ICW
LC | 120691786 | 009/053 | T2 DI STNISLAUS-MANTECA #2 9/53 RPL HRDT | VICTOR | ETL.3820.TOWR | 2021-03-25 | 2021-03-25 | 2022-01-25 | 2022-03-25 | 2022-03-25 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45122263 | T2 DI STNISLAUS-MANTECA #2 9/53 RPL HRDT | ICQ
LC | 120691841 | 026/169 | T2 EI POE-RIO OSO 26/169 INS HRDT | TABLEMTN | ETL.5540.TOWR | 2021-03-25 | 2021-03-25 | 2022-05-25 | 2022-03-25 | 2022-03-25 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Hardware-Tower | Install | 45198332 | T2 EI POE-RIO OSO 26/169 INS HRDT | ICQ
LC | 120691847 | 009/053 | T2 DI STANISLAUS-MANTECA #2 9/53 INS DAM | VICTOR | ETL.3820.INSL.CERA | 2021-03-25 | 2021-03-25 | 2021-11-30 | 2022-03-25 | 2022-03-25 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Damper-Steel | Install | 44977857 | T2 DI STANISLAUS-MANTECA #2 9/53 INS DAM | ICS
LC | 120691908 | 010/060 | T2 DI STNSLAUS-MANTECA #2 10/60 RPR STRT | VICTOR | ETL.3820.TOWR | 2021-03-25 | 2021-03-25 | 2022-01-31 | 2022-03-25 | 2022-03-25 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45122274 | T2 DI STNSLAUS-MANTECA #2 10/60 RPR STRT | ICQ
LC | 120692151 | 011/098 | T2 DI ELDRDO-MSR FLT #1 11/98 RPL STEP | SACTO | ETL.1530.POLE.NWOD | 2021-03-25 | 2021-03-25 | 2022-06-22 | 2022-03-25 | 2022-03-25 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Steel | Replace | 44711470 | T2 DI ELDRDO-MSR FLT #1 11/98 RPL STEP | ICS
LC | 120692955 | 026/173 | T2 EI POE-RIO OSO 26/173 RMV NEST | TABLEMTN | ETL.5540.TOWR | 2021-03-25 | 2021-03-25 | 2022-08-10 | 2022-03-25 | 2022-03-25 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45213415 | T2 EI POE-RIO OSO 26/173 RMV NEST | ICS
LC | 120693169 | 009/150 | T2 DI SSQC-ST YNZ SW ST 009/150 RPR SPLW | PISMOBCH | ETL.3700.INSL.NCER | 2021-03-26 | 2021-03-25 | 2022-02-15 | 2022-03-25 | 2022-03-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45069144 | T2 DI SSQC-ST YNZ SW ST 009/150 RPR SPLW | ICW
LC | 120694984 | 017/099 | T2 DI SN ML SW ST-RK JT S 17/99 RPR SPLS | VICTOR | ETL.3840.INSL.NCER | 2021-03-26 | 2021-03-25 | 2022-09-16 | 2022-03-25 | 2022-03-25 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45121879 | T2 DI SN ML SW ST-RK JT S 17/99 RPR SPLS | ICS
LC | 120695043 | 005/019 | T2 BRICEBURG -MRPSA TAP 5/19 STRW RPL | FRESNO | ETL.8651.POLE.WOOD | 2021-03-26 | 2021-03-26 | 2022-02-01 | 2022-03-26 | 2022-03-26 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535292 | T2 BRICEBURG -MRPSA TAP 5/19 REFRAME | 93E
LC | 120695048 | 000/008 | T2 EI ROCK CREEK-POE 0/8 RMV STEP | TABLEMTN | ETL.5630.TOWR | 2021-03-26 | 2021-03-25 | 2022-07-20 | 2022-03-25 | 2022-03-25 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45159488 | T2 EI ROCK CREEK-POE 0/8 RMV STEP | ICQ
LC | 120695212 | 009/052 | T2 DI STANISLS-MANTECA #2 9/52 RPR STRT | VICTOR | ETL.3820.TOWR | 2021-03-26 | 2021-03-25 | 2022-01-25 | 2022-03-25 | 2022-03-25 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45122261 | T2 DI STANISLS-MANTECA #2 9/52 RPR STRT | ICQ
LC | 120695219 | 009/054 | T2 DI STANSLS-MLNS-MNTC 9/54 RPR STRT | VICTOR | ETL.3830.TOWR | 2021-03-26 | 2021-03-25 | 2022-01-25 | 2022-03-25 | 2022-03-25 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45122265 | T2 DI STANSLS-MLNS-MNTC 9/54 RPR STRT | ICQ
LC | 120695236 | 013/002 | T2 EI FULTON-HOPLAND 13/2 RPL ANCW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-03-26 | 2021-03-26 | 2021-07-15 | 2022-03-26 | 2022-03-26 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31535429 | T2 EI FULTON-HOPLAND 13/2 RPL ANCW | 93E
LC | 120695345 | :010/003 | T2 DI BLLT-RVRBK-MLS SWST :10/3 RPR GYWW | VICTOR | ETL.1070.POLE.WOOD | 2021-03-26 | 2021-03-25 | 2022-05-03 | 2022-03-25 | 2022-03-25 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45151555 | T2 DI BLLT-RVRBK-MLS SWST :10/3 RPR GYWW | ICW
LC | 120695347 | :010/003 | T2 DI BLLT-RVRBK-MLS SWST :10/3 RPL INSS | VICTOR | ETL.1070.INSL.NCER | 2021-03-26 | 2021-03-25 | 2022-05-03 | 2022-03-25 | 2022-03-25 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535289 | T2 EI BLT-RVBK-MLS SWSTA :2/9 INST INSLW | 93I
LC | 120695349 | :010/008 | T2 DI BLLT-RVRBK-MLS SWST :10/8 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-03-26 | 2021-03-25 | 2022-05-05 | 2022-03-25 | 2022-03-25 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535291 | T2 DI BLLT-RVRBK-MLS SWST :10/8 RPL STRW | 70Y
LC | 120695408 | 008/039 | T2 EI MORRO BAY-MESA 008/039 RMV NEST | PISMOBCH | ETL.5290.TOWR | 2021-03-26 | 2021-03-26 | 2021-09-12 | 2022-03-26 | 2022-03-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44963084 | T2 EI MORRO BAY-MESA 008/039 RMV NEST | ICS
LC | 120695462 | B018/406 | T2 EI DRUM-GV-WEMR B18/406 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2021-03-26 | 2021-03-26 | 2022-07-23 | 2022-03-26 | 2022-03-26 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535167 | T2 EI DRUM-GV-WEIMAR B16/364 RPL POLE | 70Y
LC | 120695548 | 009/060 | T2 DI STLS-MLNS SS-MTC #1 9/60 RPR STRT | VICTOR | ETL.3830.TOWR | 2021-03-26 | 2021-03-25 | 2022-01-31 | 2022-03-25 | 2022-03-25 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45122273 | T2 DI STLS-MLNS SS-MTC #1 9/60 RPR STRT | ICQ
LC | 120695652 | 010/078A | T2 EI TRINITY-CTTONWD 010/078A ANCW RPR | TABLEMTN | ETL.4040.POLE.WOOD | 2021-03-26 | 2021-03-26 | 2021-09-16 | 2022-03-26 | 2022-03-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45073926 | T2 EI TRINITY-COTTNWD 010/078C ANCW RPR | ICW
LC | 120695694 | 023/145 | T2 DI STLS-MLS SS-MTC #1 23/145 RPR INSS | VICTOR | ETL.3830.INSL | 2021-03-26 | 2021-03-25 | 2022-03-07 | 2022-03-25 | 2022-03-25 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44978054 | T2 DI STLS-MLS SS-MTC #1 23/145 RPR INSS | ICS
LC | 120695699 | 011/067 | T2 DI STS-MLS-MTC SS-MN#1 11/67 RPR SPLS | VICTOR | ETL.3830.INSL.CERA | 2021-03-26 | 2021-03-25 | 2022-02-28 | 2022-03-25 | 2022-03-25 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 44978045 | T2 DI STS-MLS-MTC SS-MN#1 11/67 RPR SPLS | ICS
LC | 120695702 | 010/078C | T2 EI TRINITY-COTTNWD 010/078C ANCW RPR | TABLEMTN | ETL.4040.POLE.WOOD | 2021-03-26 | 2021-03-26 | 2021-09-16 | 2022-03-26 | 2022-03-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45073926 | T2 EI TRINITY-COTTNWD 010/078C ANCW RPR | ICW
LC | 120695790 | 023/146 | T2 DI STLS-MLS SS-MTC #1 23/146 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-03-26 | 2021-03-25 | 2022-02-11 | 2022-03-25 | 2022-03-25 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123132 | T2 DI STLS-MLS SS-MTC #1 23/146 RPR FOND | ICQ
LC | 120695833 | 017/098 | T2 DI STANISLAUS-MNTC #2 17/98 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-03-26 | 2021-03-25 | 2022-02-08 | 2022-03-25 | 2022-03-25 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45123104 | T2 DI STANISLAUS-MNTC #2 17/98 RPR FOND | ICQ
LC | 120695835 | 017/098 | T2 DI STANMEL-RVRBNK JCT 17/98 RPR INSS | VICTOR | ETL.3840.INSL.CERA | 2021-03-26 | 2021-03-25 | 2022-05-14 | 2022-03-25 | 2022-03-25 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45122060 | T2 DI STANMEL-RVRBNK JCT 17/98 RPR INSS | ICS
LC | 120695869 | 059/534 | T2 EI PIT #1-COTTONWOOD 59/534 RPR GYWS | TABLEMTN | ETL.5390.TOWR | 2021-03-26 | 2021-03-26 | 2022-02-16 | 2022-03-26 | 2022-03-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45166857 | T2 EI PIT #1-COTTONWOOD 59/534 RPR GYWS | ICS
LC | 120695870 | 000/018 | T2 WEIMAR #1 0/18 RPL STRW | SACTO | ETL.7560.POLE.WOOD | 2021-03-26 | 2021-03-25 | 2021-08-15 | 2022-03-25 | 2022-03-25 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535963 | T3 EI WEIMAR #1 010/159 RPL STRW | 70Y
LC | 120695953 | 010/079A | T2 EI TRINITY-COTTONWOOD 10/79A RPL POLE | TABLEMTN | ETL.4040.POLE.WOOD | 2021-03-26 | 2021-03-26 | 2021-09-17 | 2022-03-26 | 2022-03-26 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31508137 | T3 DI TRINITY-CTTNWD 11/92 RPL STRW(ENG) | 70Y
LC | 120695989 | 008/084B | T2 PIT #5-ROUND MTN #2 8/84B RMV VEG | TABLEMTN | ETL.5430.POLE.NWOD | 2021-03-26 | 2021-03-26 | 2022-02-16 | 2022-03-26 | 2022-03-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120696006 | 010/079B | T2 EI TRINITY-COTTONWD 10/79B RPL POLE | TABLEMTN | ETL.4040.POLE.WOOD | 2021-03-26 | 2021-03-26 | 2021-09-17 | 2022-03-26 | 2022-03-26 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31508137 | T3 DI TRINITY-CTTNWD 11/92 RPL STRW(ENG) | 70Y
LC | 120696029 | 011/117 | T2 PIT #5-ROUND MTN #2 11/117 RPL INSW | TABLEMTN | ETL.5430.INSL.CERA | 2021-03-26 | 2021-03-26 | 2022-06-16 | 2022-03-26 | 2022-03-26 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545049 | T2 PIT #5-ROUND MTN #2 11/117 RPL INSW | 93I
LC | 120696053 | 010/079C | T2 EI TRINITY-COTTONWD 10/79C RPL POLE | TABLEMTN | ETL.4040.POLE.WOOD | 2021-03-26 | 2021-03-26 | 2021-09-17 | 2022-03-26 | 2022-03-26 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31508137 | T3 DI TRINITY-CTTNWD 11/92 RPL STRW(ENG) | 70Y
LC | 120696058 | 005/063 | T2 PIT #5-ROUND MTN #2 5/63 RMV VEG | TABLEMTN | ETL.5430.POLE.WDPS | 2021-03-26 | 2021-03-26 | 2022-02-17 | 2022-03-26 | 2022-03-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120696065 | 002/030 | T2 PIT #5-ROUND MTN #2 2/30 RMV VEG | TABLEMTN | ETL.5430.POLE.WDPS | 2021-03-26 | 2021-03-26 | 2022-02-17 | 2022-03-26 | 2022-03-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120696118 | 002/025 | T2 PIT #5-ROUND MTN #1 2/25 RMV VEG | TABLEMTN | ETL.5420.POLE.STPS | 2021-03-26 | 2021-03-26 | 2022-02-17 | 2022-03-26 | 2022-03-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120696137 | 003/051 | T2 WEIMAR #1 03/51 RPL STRW | SACTO | ETL.7560.POLE.WOOD | 2021-03-26 | 2021-03-25 | 2021-08-13 | 2022-03-25 | 2022-03-25 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535963 | T3 EI WEIMAR #1 010/159 RPL STRW | 70Y
LC | 120696168 | 005/061 | T2 PIT #5-ROUND MTN #1 5/61 RMV VEG | TABLEMTN | ETL.5420.POLE.STPS | 2021-03-26 | 2021-03-26 | 2021-03-30 | 2022-03-26 | 2022-03-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120696181 | :011/007 | T2 DI BELLOT-RVRBNK-MLNS :11/7 RPLC INSW | VICTOR | ETL.1070.INSL.NCER | 2021-03-26 | 2021-03-25 | 2022-05-02 | 2022-03-25 | 2022-03-25 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535289 | T2 EI BLT-RVBK-MLS SWSTA :2/9 INST INSLW | 93I
LC | 120696189 | :009/008 | T2 DI BLT-RVRBNK-MLNS :9/8 RPLC INSW | VICTOR | ETL.1070.INSL.NCER | 2021-03-26 | 2021-03-25 | 2022-05-04 | 2022-03-25 | 2022-03-25 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535289 | T2 EI BLT-RVBK-MLS SWSTA :2/9 INST INSLW | 93I
LC | 120696194 | 003/049 | T2 WEIMAR #1 03/049 RPL STRW | SACTO | ETL.7560.POLE.WOOD | 2021-03-26 | 2021-03-25 | 2021-08-13 | 2022-03-25 | 2022-03-25 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535963 | T3 EI WEIMAR #1 010/159 RPL STRW | 70Y
LC | 120696202 | 018/146 | T2 CARBERRY SW STA-ROUND 18/146 RMV VEG | TABLEMTN | ETL.5410.TOWR | 2021-03-26 | 2021-03-26 | 2022-08-31 | 2022-03-26 | 2022-03-26 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120696336 | 010/080 | T2 EI TRINITY-COTTONWD 010/080 GYWW RPR | TABLEMTN | ETL.4040.POLE.STPS | 2021-03-26 | 2021-03-26 | 2021-09-01 | 2022-03-26 | 2022-03-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44905925 | T2 EI TRINITY-COTTONWD 010/080 GYWW RPR | ICW
LC | 120696346 | :011/006 | T2 DI BLT-RVRBNK-MLNS :11/6 RPLC INSW | VICTOR | ETL.1070.INSL.NCER | 2021-03-26 | 2021-03-25 | 2022-05-02 | 2022-03-25 | 2022-03-25 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535289 | T2 EI BLT-RVBK-MLS SWSTA :2/9 INST INSLW | 93I
LC | 120696349 | :011/006 | T2 DI BLT-RVRBNK-MLNS :11/6 RMV DEBRIS | VICTOR | ETL.1070.POLE.WOOD | 2021-03-26 | 2021-03-25 | 2022-02-24 | 2022-03-25 | 2022-03-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45151556 | T2 DI BLT-RVRBNK-MLNS :11/6 RMV DEBRIS | ICW
LC | 120696352 | 011/097 | T2 EI CRAG VIEW-CASCADE 11/97 RPL SPLS | TABLEMTN | ETL.1350.INSL | 2021-03-26 | 2021-03-26 | 2021-08-03 | 2022-03-26 | 2022-03-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Repair | 44860223 | T2 EI CRAG VIEW-CASCADE 11/97 RPL SPLS | ICS
LC | 120696365 | 011/097 | T2 EI CRAG VIEW-CASCADE 11/97 RMV NEST | TABLEMTN | ETL.1350.TOWR | 2021-03-26 | 2021-03-26 | 2021-08-07 | 2022-03-26 | 2022-03-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Structure-Steel | Remove | 44860224 | T2 EI CRAG VIEW-CASCADE 11/97 RMV NEST | ICS
LC | 120696453 | 010/080 | T2 EI TRINITY-COTTONWD 010/080 GWRS RPR | TABLEMTN | ETL.4040.POLE.STPS | 2021-03-26 | 2021-03-26 | 2021-08-30 | 2022-03-26 | 2022-03-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44905926 | T2 EI TRINITY-COTTONWD 010/080 GWRS RPR | ICW
LC | 120696571 | 023/136 | T2 DI SN ML SW ST-RK JT SW 23/136 RPR CN | VICTOR | ETL.3840.INSL.NCER | 2021-03-26 | 2021-03-25 | 2022-04-22 | 2022-03-25 | 2022-03-25 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45122061 | T2 DI SN ML SW ST-RK JT SW 23/136 RPR CN | ICS
LC | 120696608 | 010/067 | T2 COTTONWOOD #1 10/067 RPR INSS | TABLEMTN | ETL.6620.INSL.CERA | 2021-03-26 | 2021-03-26 | 2022-07-20 | 2022-03-26 | 2022-03-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45212110 | T2 COTTONWOOD #1 10/067 RPR INSS | ICS
LC | 120696782 | 025/111 | T2 EI MSS LNDNG-MTCLF 025/111 REM VEG | MOSSLNDG | ETL.6050.TOWR | 2021-03-26 | 2021-03-26 | 2021-10-02 | 2022-03-26 | 2022-03-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO CLMB FRAB | Overgrown | Vegetation | Remove
LC | 120696895 | 007/116 | T2 EI CTRVL-TBL MTN 007/116 RPR STRW | TABLEMTN | ETL.6320.POLE.WOOD | 2021-03-26 | 2021-03-26 | 2022-02-25 | 2022-03-26 | 2022-03-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45195728 | T2 EI CTRVL-TBL MTN 007/116 RPR STRW | ICW
LC | 120697139 | 008/062 | T2 EI EL DRDO-MSSOURI FLAT 8/62 RPR FOND | SACTO | ETL.1530.TOWR | 2021-03-26 | 2021-03-26 | 2022-06-27 | 2022-03-26 | 2022-03-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44737821 | T2 EI EL DRDO-MSSOURI FLAT 8/62 RPR FOND | ICQ
LC | 120697184 | 016/104 | T2 DI STANIS-MLNS-MNTC 16/104 RPR STRT | VICTOR | ETL.3830.INSL | 2021-03-26 | 2021-03-26 | 2022-02-08 | 2022-03-26 | 2022-03-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Tower | Repair | 45123102 | T2 DI STANIS-MLNS-MNTC 16/104 RPR STRT | ICQ
LC | 120697186 | 016/104 | T2 DI STANIS-MLNS-MNTC 16/104 RPL STEP | VICTOR | ETL.3830.TOWR | 2021-03-26 | 2021-03-26 | 2022-02-08 | 2022-03-26 | 2022-03-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45123103 | T2 DI STANIS-MLNS-MNTC 16/104 RPL STEP | ICQ
LC | 120697188 | 016/104 | T2 DI STANIS-MLNS-MNTC 16/104 RPR INSS | VICTOR | ETL.3830.INSL | 2021-03-26 | 2021-03-26 | 2022-03-04 | 2022-03-26 | 2022-03-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44978052 | T2 DI STANIS-MLNS-MNTC 16/104 RPR INSS | ICS
LC | 120697594 | 025/106 | T2 EI MSS LNDNG-MTCLF 025/106 RPR STRT | MOSSLNDG | ETL.6050.TOWR | 2021-03-26 | 2021-03-26 | 2022-08-08 | 2022-03-26 | 2022-03-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45128281 | T2 EI MSS LNDNG-MTCLF 025/106 RPR STRT | ICQ
LC | 120697878 | 005/042A | T2 WISHON-COPPERMINE 05/042A RMV NEST | FRESNO | ETL.9330.POLE.NWOD | 2021-03-26 | 2021-03-26 | 2021-06-14 | 2022-03-26 | 2022-03-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Structure-Steel | Remove | 44804337 | T2 WISHON-COPPERMINE 05/042A RMV NEST | ICS
LC | 120697967 | 000/006 | T2 WISHON-SAN JOAQUIN #3 0/06 RPL STRW | FRESNO | ETL.9340.POLE.WOOD | 2021-03-26 | 2021-03-26 | 2021-10-22 | 2022-03-26 | 2022-03-26 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535487 | T2 WISHON-SAN JOAQUIN #3 0/06 RPL STRW | 70Y
LC | 120698036 | 010/045 | T2 EI DIABLO-GATES #1 10/45 RPR TURNBUCK | PISMOBCH | ETL.5960.TOWR | 2021-03-26 | 2021-03-26 | 2022-06-25 | 2022-03-26 | 2022-03-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP CREW PGEA COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45070720 | T2 EI DIABLO-GATES #1 10/45 RPR TURNBUCK | ICQ
LC | 120698121 | 011/050 | T2 EI MORRO BAY-MESA 011/050 RPR FONDT | PISMOBCH | ETL.5290.TOWR | 2021-03-26 | 2021-03-26 | 2022-06-16 | 2022-03-26 | 2022-03-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45073824 | T2 EI MORRO BAY-MESA 011/050 RPR FONDT | ICQ
LC | 120698241 | :005/040 | T2 EI ROCK CREEK-POE 5/40 RPR FOND | TABLEMTN | ETL.5630.TOWR | 2021-03-26 | 2021-03-26 | 2022-07-06 | 2022-03-26 | 2022-03-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195426 | T2 EI ROCK CREEK-POE 5/40 RPR FOND | ICQ
LC | 120698543 | 025/156 | T2 DI STLS-MLNS SS-MTC #1 25/156 RPR STR | VICTOR | ETL.3830.TOWR | 2021-03-26 | 2021-03-26 | 2022-02-03 | 2022-03-26 | 2022-03-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45123141 | T2 DI STLS-MLNS SS-MTC #1 25/156 RPR STR | ICQ
LC | 120698741 | 022/099 | T2 EI MSS LNDING-CBURN 022/099 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-03-26 | 2021-03-26 | 2022-05-17 | 2022-03-26 | 2022-03-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45118532 | T2 EI MSS LNDING-CBURN 022/099 RPR FONDT | ICQ
LC | 120698746 | 022/101 | T2 EI MOSS LANDING-COBURN 22/101 RPR FON | MOSSLNDG | ETL.5330.TOWR | 2021-03-26 | 2021-03-26 | 2022-05-17 | 2022-03-26 | 2022-03-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44715150 | T2 EI MOSS LANDING-COBURN 22/101 RPR FON | ICQ
LC | 120699193 | 049/310 | T2 EI MADISON-VACA 49/310 RPR FOND | SACTO | ETL.2170.TOWR | 2021-03-26 | 2021-03-26 | 2022-02-04 | 2022-03-26 | 2022-03-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44737754 | T2 EI MADISON-VACA 49/310 RPR FOND | ICQ
LC | 120699302 | 073/531 | T2 WV BRIDGEVILLE-COTTONWD 73/5 RPR STRW | EUREKA | ETL.1110.POLE.WDPS | 2021-03-26 | 2021-03-26 | 2021-06-25 | 2022-03-26 | 2022-03-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44871500 | T2 WV BRIDGEVILLE-COTTONWD 73/5 RPR STRW | ICW
LC | 120699739 | 007/056 | T2 EI EL DRDO-MSSOURI FLAT 7/56 RPR FOND | SACTO | ETL.1530.TOWR | 2021-03-27 | 2021-03-26 | 2022-05-31 | 2022-03-26 | 2022-03-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44737825 | T2 EI EL DRDO-MSSOURI FLAT 7/56 RPR FOND | ICQ
LC | 120700321 | 028/013 | T2 EI FULTON-HOPLAND 28/13 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-03-27 | 2021-03-27 | 2021-08-05 | 2022-03-27 | 2022-03-27 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31535421 | T2 EI FULTON-HOPLAND 10/3 RPL POLE | 70Y
LC | 120700673 | 007/059 | T2 EI EL DRDO-MSSOURI FLAT 7/59 COMPLETE | SACTO | ETL.1530.TOWR | 2021-03-27 | 2021-03-27 | 2022-06-08 | 2022-03-27 | 2022-03-27 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44737751 | T2 EI EL DRDO-MSSOURI FLAT 7/59 RPR FOND | ICQ
LC | 120701035 | 006/105 | T2 EI CTRVL-TBL MTN 006/105 RPL STRW | TABLEMTN | ETL.6320.POLE.WOOD | 2021-03-27 | 2021-03-27 | 2022-04-26 | 2022-03-27 | 2022-03-27 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535168 | T2 EI CTRVL-TBL MTN 006/105 RPL STRW | 70Y
LC | 120701037 | 000/006 | T2 EI LAYTONVILLE-COVELO 0/6 RPL POLE | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-03-27 | 2021-03-27 | 2021-06-22 | 2022-03-27 | 2022-03-27 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541819 | T2 EI LAYTONVILLE-COVELO 0/6 RPL POLE | 70Y
LC | 120701722 | 009/082 | T2 EI CRAG VIEW-CASCADE 9/82 RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-03-27 | 2021-03-27 | 2021-06-17 | 2022-03-27 | 2022-03-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44860221 | T2 EI CRAG VIEW-CASCADE 9/82 RPR GYWW | ICW
LC | 120701882 | 009/083 | T2 EI CRAG VIEW-CASCADE 9/083 RPR GRWW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-27 | 2021-03-27 | 2021-06-17 | 2022-03-27 | 2022-03-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 44860222 | T2 EI CRAG VIEW-CASCADE 9/083 RPR GRWW | ICW
LC | 120705120 | 009/059 | T2 DI SN ML SW ST-RK JT SW 9/59 RPR SPLS | VICTOR | ETL.3840.INSL.CERA | 2021-03-29 | 2021-03-26 | 2022-05-12 | 2022-03-26 | 2022-03-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122062 | T2 DI SN ML SW ST-RK JT SW 9/59 RPR SPLS | ICS
LC | 120705164 | 009/059 | T2 DI STNISLAUS-MANTECA #2 9/59 INS HDRS | VICTOR | ETL.3820.INSL.CERA | 2021-03-29 | 2021-03-26 | 2021-11-30 | 2022-03-26 | 2022-03-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44977859 | T2 DI STNISLAUS-MANTECA #2 9/59 INS HDRS | ICS
LC | 120705463 | 024/144 | T2 DI STANISLAUS-MNTC #2 24/144 UNBURY | VICTOR | ETL.3820.TOWR | 2021-03-29 | 2021-03-24 | 2022-02-09 | 2022-03-24 | 2022-03-24 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45123137 | T2 DI STANISLAUS-MNTC #2 24/144 UNBURY | ICQ
LC | 120705468 | 024/144 | T2 DI STAN MEL-RVRBK 24/144 RPL INSS | VICTOR | ETL.3840.INSL.NCER | 2021-03-29 | 2021-03-24 | 2022-04-23 | 2022-03-24 | 2022-03-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31512192 | DI STANISLAUS-MELONES #2 RPL INSS 11TWR | 93K
LC | 120705607 | 033/006 | T2 EI FULTON-HOPLAND 33/6 RPL ARMOR | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-03-29 | 2021-03-29 | 2021-08-04 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair | 44877575 | T2 EI FULTON-HOPLAND 33/6 RPL ARMOR | ICW
LC | 120705714 | 018/104 | T2 DI STNISLAUS-MNTC #2 18/104 UNBURY | VICTOR | ETL.3820.TOWR | 2021-03-29 | 2021-03-25 | 2022-02-09 | 2022-03-25 | 2022-03-25 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45123109 | T2 DI STNISLAUS-MNTC #2 18/104 UNBURY | ICQ
LC | 120705716 | :007/041 | T2 DI STNSLS-MLNS-MNTC#1 :7/41 RPLC INSS | VICTOR | ETL.3830.INSL.NCER | 2021-03-29 | 2021-03-26 | 2022-09-20 | 2022-03-26 | 2022-03-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528967 | NN STANISLAUS-MLNS-MNTC RPLC INSS 11TWR | 93K
LC | 120705762 | :007/041 | T2 DI STANMEL-RVRBNK :7/41 COMPLETE | VICTOR | ETL.3840.INSL.NCER | 2021-03-29 | 2021-03-26 | 2022-05-19 | 2022-03-26 | 2022-03-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31512192 | DI STANISLAUS-MELONES #2 RPL INSS 11TWR | 93K
LC | 120706180 | 015/216 | T2 EI SQC-SNT YNZ 15/216 RPL STRW CMPLTD | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-29 | 2021-03-29 | 2022-04-16 | 2022-03-29 | 2022-03-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP TNT COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535450 | T2 DI SSQC-SNT YNZ 010/154 RPL STRW | 70Y
LC | 120706531 | :011/005 | T2 DI BLT-RVRBNK-MLNS :11/5 RPLC INSW | VICTOR | ETL.1070.INSL.NCER | 2021-03-29 | 2021-03-25 | 2022-05-03 | 2022-03-25 | 2022-03-25 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535289 | T2 EI BLT-RVBK-MLS SWSTA :2/9 INST INSLW | 93I
LC | 120706571 | 009/057 | T2 DI STN ML SW ST-RVRB 9/57 RPR SPLS | VICTOR | ETL.3840.INSL.CERA | 2021-03-29 | 2021-03-26 | 2022-05-12 | 2022-03-26 | 2022-03-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122063 | T2 DI STN ML SW ST-RVRB 9/57 RPR SPLS | ICS
LC | 120706617 | 010/063 | T2 DI STNSLS-MNTC #2 10/63 UNBURY | VICTOR | ETL.3820.TOWR | 2021-03-29 | 2021-03-25 | 2022-01-27 | 2022-03-25 | 2022-03-25 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45122277 | T2 DI STNSLS-MNTC #2 10/63 UNBURY | ICQ
LC | 120706692 | 037/171 | T2 EI LAKVILLE-SBRNTE #2 37/171 RPL INSS | CONCORD | ETL.4960.INSL | 2021-03-29 | 2021-03-24 | 2022-07-24 | 2022-03-24 | 2022-03-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31542274 | T2 DI LKVILLE-SBRNTE #2 RPL INSS 3 TWRS | 93K
LC | 120706738 | 004/035 | T2 EI EL DRDO-MSSOURI FLAT 4/35 RPR FOND | SACTO | ETL.1530.TOWR | 2021-03-29 | 2021-03-29 | 2022-05-31 | 2022-03-29 | 2022-03-29 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44737741 | T2 EI EL DRDO-MSSOURI FLAT 4/35 RPR FOND | ICQ
LC | 120706808 | 112/005 | T2 EI HMBLDT-BRDGVLLE 112/5R RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-03-29 | 2021-03-29 | 2022-04-06 | 2022-03-29 | 2022-03-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544963 | T2 EI HMBLDT-BRDGVLLE 112/5C RPL STRW | 70Y
LC | 120706874 | 112/005 | T2 EI HMBLDT-BRDGVLLE 112/5C RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-03-29 | 2021-03-29 | 2022-04-06 | 2022-03-29 | 2022-03-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544963 | T2 EI HMBLDT-BRDGVLLE 112/5C RPL STRW | 70Y
LC | 120706876 | 024/141 | T2 DI STANISLAUS-MNTC #2 24/141 UNBURY | VICTOR | ETL.3820.TOWR | 2021-03-29 | 2021-03-25 | 2022-02-09 | 2022-03-25 | 2022-03-25 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45123136 | T2 DI STANISLAUS-MNTC #2 24/141 UNBURY | ICQ
LC | 120706930 | 004/036 | T2 EI EL DRDO-MISSOURI FLAT 4/35 RMV VEG | SACTO | ETL.1530.TOWR | 2021-03-29 | 2021-03-29 | 2021-07-20 | 2022-03-29 | 2022-03-29 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120706978 | 112/005 | T2 EI HMBLDT-BRDGVLLE 112/5L RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-03-29 | 2021-03-29 | 2022-04-06 | 2022-03-29 | 2022-03-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544963 | T2 EI HMBLDT-BRDGVLLE 112/5C RPL STRW | 70Y
LC | 120707268 | 004/024 | T2 DI KRCKHF-CLVS-SNGR #1 4/24 RPR FOND | FRESNO | ETL.1890.TOWR | 2021-03-29 | 2021-03-29 | 2022-02-09 | 2022-03-29 | 2022-03-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45068124 | T2 DI KRCKHF-CLVS-SNGR #1 4/24 RPR FOND | ICQ
LC | 120707323 | 004/024 | T2 DI KRCKHF-CLVS-SNGR #1 4/24 RPR STRT | FRESNO | ETL.1890.TOWR | 2021-03-29 | 2021-03-29 | 2022-02-09 | 2022-03-29 | 2022-03-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45068125 | T2 DI KRCKHF-CLVS-SNGR #1 4/24 RPR STRT | ICQ
LC | 120707496 | 009/056 | T2 DI STANISLAUS-MNTECA #2 9/56 RPL HRDT | VICTOR | ETL.3820.TOWR | 2021-03-29 | 2021-03-26 | 2022-01-31 | 2022-03-26 | 2022-03-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45122270 | T2 DI STANISLAUS-MNTECA #2 9/56 RPL HRDT | ICQ
LC | 120707537 | 004/085 | T2 EI SSQC-SNT YNZ SW ST 4/85 INS HRDW | PISMOBCH | ETL.3700.INSL.CERA | 2021-03-29 | 2021-03-29 | 2021-10-04 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44963182 | T2 EI SSQC-SNT YNZ SW ST 4/85 INS HRDW | ICW
LC | 120707538 | 004/085 | T2 EI SISQC-SNT YNZ SW ST 4/85 RPR SPLW | PISMOBCH | ETL.3700.INSL.CERA | 2021-03-29 | 2021-03-29 | 2021-10-06 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Repair | 44963123 | T2 EI SISQC-SNT YNZ SW ST 4/85 RPR SPLW | ICW
LC | 120707551 | 005/086 | T2 EI SSQC-SNT YNZ SW STA 5/86 RPL HRDD | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-29 | 2021-03-29 | 2021-10-06 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44963139 | T2 EI SSQC-SNT YNZ SW STA 5/86 RPL HRDD | ICW
LC | 120707625 | 009/056 | T2 DI SN ML SW ST-RK JT SW 9/56 RPL DAMS | VICTOR | ETL.3840.INSL.CERA | 2021-03-29 | 2021-03-26 | 2022-05-12 | 2022-03-26 | 2022-03-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 45122065 | T2 DI SN ML SW ST-RK JT SW 9/56 RPL DAMS | ICS
LC | 120707722 | 008/073 | T2 EI CRAG VIEW-CASCADE 8/73L RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-03-29 | 2021-03-29 | 2021-06-17 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44860199 | T2 EI CRAG VIEW-CASCADE 8/73L RPR GYWW | ICW
LC | 120707753 | 016/096 | T2 DI SN ML SW ST-R JT SW 16/96 RPL INSS | VICTOR | ETL.3840.INSL.CERA | 2021-03-29 | 2021-03-26 | 2022-05-15 | 2022-03-26 | 2022-03-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31512192 | DI STANISLAUS-MELONES #2 RPL INSS 11TWR | 93K
LC | 120707755 | 008/073 | T2 EI CRAG VIEW-CASCADE 8/73R RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-03-29 | 2021-03-29 | 2021-06-17 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44860220 | T2 EI CRAG VIEW-CASCADE 8/73R RPR GYWW | ICW
LC | 120707809 | 004/032 | T2 EI EL DRDO-MSSOURI FLAT 4/32 RPR FOND | SACTO | ETL.1530.TOWR | 2021-03-29 | 2021-03-29 | 2022-03-08 | 2022-03-29 | 2022-03-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44737708 | T2 EI EL DRDO-MSSOURI FLAT 4/32 RPR FOND | ICQ
LC | 120708059 | 000/003 | T2 EI CLMN-CTTNWD 000/003 RPR GWRW | TABLEMTN | ETL.6430.POLE.WOOD | 2021-03-29 | 2021-03-29 | 2021-06-24 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859709 | T2 EI CLMN-CTTNWD 000/003 RPR GWRW | ICW
LC | 120708094 | :002/002 | T2 DI BLLT-RBK-MLS SWSTA :2/2 RMV DB | VICTOR | ETL.1070.POLE.NWOD | 2021-03-29 | 2021-03-29 | 2022-02-25 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45151557 | T2 DI BLLT-RBK-MLS SWSTA :2/2 RMV DB | ICW
LC | 120708100 | 000/007 | T2 EI CLMN-CTTNWD 000/007 RPL STRW | TABLEMTN | ETL.6430.POLE.WOOD | 2021-03-29 | 2021-03-29 | 2021-06-18 | 2022-03-29 | 2022-03-29 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31535163 | T2 EI CLMN-CTTNWD 000/007 RPL STRW | 70Y
LC | 120708125 | 015/360 | T2 EI DRUM-GV-WEIMAR 15/360 RMV DEBRIS | SACTO | ETL.6760.POLE.WOOD | 2021-03-29 | 2021-03-29 | 2022-07-16 | 2022-03-29 | 2022-03-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44737713 | T2 EI DRUM-GV-WEIMAR 15/360 RMV DEBRIS | ICW
LC | 120708331 | 014/080 | T2 BALCH-MCCAL 14/80 RPL INSS | FRESNO | ETL.4350.INSL | 2021-03-29 | 2021-03-29 | 2022-02-07 | 2022-03-29 | 2022-03-29 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31544310 | T2 BALCH-MCCAL 14/80 RPL INSS | 93K
LC | 120708448 | 008/070 | T2 EI CRAG VIEW-CASCADE 8/70R RPR OPGW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-29 | 2021-03-29 | 2021-06-18 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44860198 | T2 EI CRAG VIEW-CASCADE 8/70R RPR OPGW | ICW
LC | 120708554 | 012/089 | T2 EI GREEN VALLEY-LLGS 12/089 RPR ANCW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-03-29 | 2021-03-29 | 2021-09-29 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 44993532 | T2 EI GREEN VALLEY-LLGS 12/089 RPR ANCW | ICW
LC | 120708555 | 012/089 | T2 EI GREEN VALLEY-LLGS 12/89 RPR ANCHW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-03-29 | 2021-03-29 | 2021-09-29 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 44981646 | T2 EI GREEN VALLEY-LLGS 12/89 RPR ANCHW | ICW
LC | 120708745 | 016/102 | T2 DI STLS-MLS SS-MTC #1 16/102 RPR SPLS | VICTOR | ETL.3830.INSL | 2021-03-29 | 2021-03-26 | 2021-05-26 | 2022-03-26 | 2022-03-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 44826341 | T2 DI STLS-MLS SS-MTC #1 16/102 RPR SPLS | ICS
LC | 120708776 | 001/015 | T2 EI ROCK CREEK-POE 1/15 RPR JUMPR | TABLEMTN | ETL.5630.TOWR | 2021-03-29 | 2021-03-29 | 2022-08-06 | 2022-03-29 | 2022-03-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Jumper-Steel | Repair | 45212490 | T2 EI ROCK CREEK-POE 1/15 RPR JUMPR | ICS
LC | 120709021 | 036/014 | T2 EI FULTON-HOPLAND 36/14 RPR WDPKR | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-03-29 | 2021-03-29 | 2021-08-06 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44877573 | T2 EI FULTON-HOPLAND 36/14 RPR WDPKR | ICW
LC | 120709519 | 047/192 | T2 EI DIABLO-GATES #1 47/192 BENT STEEL | PISMOBCH | ETL.5960.TOWR | 2021-03-29 | 2021-03-29 | 2022-06-27 | 2022-03-29 | 2022-03-29 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 44859457 | T2 EI DIABLO-GATES #1 47/192 BENT STEEL | ICQ
LC | 120709685 | 005/088 | T2 EI SSQC-SNT YNEZ SW ST 5/88 RPL HRDW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-29 | 2021-03-29 | 2021-11-15 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44963124 | T2 EI SSQC-SNT YNEZ SW ST 5/88 RPL HRDW | ICW
LC | 120709686 | 005/087 | T2 EI SSQC-SNT YNZ SW STA 5/87 RPR GYWW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-29 | 2021-03-29 | 2021-10-06 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44963131 | T2 EI SSQC-SNT YNZ SW STA 5/87 RPR GYWW | ICW
LC | 120709687 | 005/088 | T2 EI SIQC-SNTA YNZ SW ST 5/88 RPR SPLS | PISMOBCH | ETL.3700.INSL.CERA | 2021-03-29 | 2021-03-29 | 2021-11-15 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Repair | 44963120 | T2 EI SIQC-SNTA YNZ SW ST 5/88 RPR SPLS | ICW
LC | 120709688 | 005/094 | T2 EI SSQC-SNT YNZ SW ST 5/94 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-29 | 2021-03-29 | 2021-10-26 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44963098 | T2 EI SSQC-SNT YNZ SW ST 5/94 RPR STRW | ICW
LC | 120709689 | 005/092 | T2 EI SSQC-SNT YNZ SW ST 5/92 RPL HRDD | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-29 | 2021-03-29 | 2021-10-26 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44963132 | T2 EI SSQC-SNT YNZ SW ST 5/92 RPL HRDD | ICW
LC | 120709710 | 005/087 | T2 EI SSQC-SNT YNZ SW STA 5/87 RPL HRDD | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-29 | 2021-03-29 | 2021-10-26 | 2022-03-29 | 2022-03-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44963099 | T2 EI SSQC-SNT YNZ SW STA 5/87 RPL HRDD | ICW
LC | 120710898 | 112/000 | T2 EI HUMBOLDT-BRDGVLL 112/000 RPR INS | EUREKA | ETL.1810.TOWR | 2021-03-30 | 2021-03-29 | 2022-04-05 | 2022-03-29 | 2022-03-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Repair | 45010823 | T2 EI HUMBOLDT-BRDGVLL 112/000 RPR INS | ICS
LC | 120710926 | 112/008 | T2 EI HMBLDT-BRDGVLLE 112/8 RMV VEG | EUREKA | ETL.1810.POLE.WDPS | 2021-03-30 | 2021-03-29 | 2021-04-08 | 2022-03-29 | 2022-03-29 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120711009 | 023/135 | T2 DI STNSLS-MNTC #2 23/135 RPR SPLS | VICTOR | ETL.3820.INSL.NCER | 2021-03-30 | 2021-03-25 | 2021-11-30 | 2022-03-25 | 2022-03-25 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 44977945 | T2 DI STNSLS-MNTC #2 23/135 RPR SPLS | ICS
LC | 120711034 | 018/105 | T2 DI STNSLS-MNTC #2 18/105 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-03-30 | 2021-03-29 | 2022-02-09 | 2022-03-29 | 2022-03-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45123110 | T2 DI STNSLS-MNTC #2 18/105 RPR FOND | ICQ
LC | 120711067 | 036/005 | T2 EI FULTON-HOPLAND 36/5 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-03-30 | 2021-03-30 | 2021-08-07 | 2022-03-30 | 2022-03-30 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31535421 | T2 EI FULTON-HOPLAND 10/3 RPL POLE | 70Y
LC | 120711082 | :000/007 | T2 EI BLLT-RVRBK-MLNS SWST :0/7 RPR GYWW | VICTOR | ETL.1070.POLE.WOOD | 2021-03-30 | 2021-03-29 | 2022-04-14 | 2022-03-29 | 2022-03-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45151558 | T2 EI BLLT-RVRBK-MLNS SWST :0/7 RPR GYWW | ICW
LC | 120711085 | 036/008 | T2 EI FULTON-HOPLAND 36/8 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-03-30 | 2021-03-30 | 2021-08-07 | 2022-03-30 | 2022-03-30 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31535421 | T2 EI FULTON-HOPLAND 10/3 RPL POLE | 70Y
LC | 120711208 | 003/019 | T2 DI KRCKHFF-CLVS-SNGR #1 3/19 RPR STRT | FRESNO | ETL.1890.TOWR | 2021-03-30 | 2021-03-29 | 2022-02-08 | 2022-03-29 | 2022-03-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45068126 | T2 DI KRCKHFF-CLVS-SNGR #1 3/19 RPR STRT | ICQ
LC | 120711616 | 005/039 | T2 EI EL DRDO-MISRI FLT #1 5/39 RPR SPLS | SACTO | ETL.1530.INSL | 2021-03-30 | 2021-03-30 | 2022-06-17 | 2022-03-30 | 2022-03-30 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Repair | 44737647 | T2 EL DRDO-MISRI FLT #1 5/39 RPR SPLS | ICS
LC | 120711617 | 005/039 | T2 EI EL DRD-MISRI FLT #2 25/39 RPR SPLS | SACTO | ETL.1540.INSL | 2021-03-30 | 2021-03-30 | 2022-05-17 | 2022-03-30 | 2022-03-30 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Repair | 44737648 | T2 EL DRD-MISRI FLT #2 25/39 RPR SPLS | ICS
LC | 120711835 | 005/038 | T2 EI EL DRDO-MSSOURI FLAT 5/38 RPR FOND | SACTO | ETL.1530.TOWR | 2021-03-30 | 2021-03-30 | 2022-06-07 | 2022-03-30 | 2022-03-30 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44737646 | T2 EI EL DRDO-MSSOURI FLAT 5/38 RPR FOND | ICQ
LC | 120711857 | :005/031 | T2 DI SN ML SW ST-RK JT S :5/31 RPL INSS | VICTOR | ETL.3840.INSL.NCER | 2021-03-30 | 2021-03-26 | 2022-05-18 | 2022-03-26 | 2022-03-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31512192 | DI STANISLAUS-MELONES #2 RPL INSS 11TWR | 93K
LC | 120711858 | :005/031 | T2 DI STNS-MLS SS-MTC #1 :5/31 RPL INSS | VICTOR | ETL.3830.INSL.NCER | 2021-03-30 | 2021-03-26 | 2021-12-18 | 2022-03-26 | 2022-03-26 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528967 | NN STANISLAUS-MLNS-MNTC RPLC INSS 11TWR | 93K
LC | 120712111 | 005/040 | T2 EI EL DRDO-MSSOURI FLAT 5/40 RPR FOND | SACTO | ETL.1530.TOWR | 2021-03-30 | 2021-03-30 | 2022-06-07 | 2022-03-30 | 2022-03-30 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44737643 | T2 EI EL DRDO-MSSOURI FLAT 5/40 RPR FOND | ICQ
LC | 120712168 | 025/108B | T2 EI MSS LNDNG-MTCLF 025/108 REM VEG | MOSSLNDG | ETL.6050.TOWR | 2021-03-30 | 2021-03-30 | 2022-06-28 | 2022-03-30 | 2022-03-30 | Late | 932 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Brush Fuel | Road | Remove | 45166677 | T2NT EI MS LNDNG-METCLF 025/109 RMV BRSH | CHS
LC | 120712169 | 025/108B | T2 EI MSS LNDNG-MTCLF 025/108 RPR FOND | MOSSLNDG | ETL.6050.TOWR | 2021-03-30 | 2021-03-30 | 2022-08-08 | 2022-03-30 | 2022-03-30 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45149363 | T2 EI MSS LNDNG-MTCLF 025/108 RPR FOND | ICQ
LC | 120712338 | 008/067 | T2 EI CRAG VIEW-CASCADE 8/67R INS JUMW | TABLEMTN | ETL.1350.INSL.CERA | 2021-03-30 | 2021-03-30 | 2021-08-06 | 2022-03-30 | 2022-03-30 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31536014 | CRAG VIEW-CASCADE 8/67R INS JUMW (ENG) | 93I
LC | 120712461 | 009/143 | T2 DI SSQC-SNT YNZ 9/143 RPR STRW CMPLTD | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-30 | 2021-03-25 | 2022-04-16 | 2022-03-25 | 2022-03-25 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069145 | T2 DI SISQUOC-SANTA YNEZ 9/143 RPR STRW | ICW
LC | 120712462 | 009/143 | T2 DI SISQUOC-SANTA YNEZ 9/143 RPR SPLW | PISMOBCH | ETL.3700.INSL.CERA | 2021-03-30 | 2021-03-25 | 2022-04-16 | 2022-03-25 | 2022-03-25 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45069146 | T2 DI SISQUOC-SANTA YNEZ 9/143 RPR SPLW | ICW
LC | 120712629 | 005/098 | T2 EI SSQC-SNT YNZ SW ST 5/98 RPL HRDD | PISMOBCH | ETL.3700.INSL.CERA | 2021-03-30 | 2021-03-30 | 2021-10-26 | 2022-03-30 | 2022-03-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44963136 | T2 EI SSQC-SNT YNZ SW ST 5/98 RPL HRDD | ICW
LC | 120712647 | 054/488 | T2 EI PIT #1-CTNWD 054/488 RMV DBRS CNDS | TABLEMTN | ETL.5390.TOWR | 2021-03-30 | 2021-03-30 | 2021-05-31 | 2022-03-30 | 2022-03-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Conductor-Steel | Remove
LC | 120712833 | 005/037 | T2 EI EL DRD-MSSR FLAT #1 5/37 RPR SPLS | SACTO | ETL.1530.INSL | 2021-03-30 | 2021-03-30 | 2022-06-17 | 2022-03-30 | 2022-03-30 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Repair | 44737644 | T2 EL DRD-MSSR FLAT #1 5/37 RPR SPLS | ICS
LC | 120712835 | 005/037 | T2 EI EL DRD-MSRI FLT #2 5/37 RPR SPLS | SACTO | ETL.1540.INSL.NCER | 2021-03-30 | 2021-03-30 | 2022-05-17 | 2022-03-30 | 2022-03-30 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Repair | 44737645 | T2 EL DORADO-MSRI FLAT #2 5/37 RPR SPLS | ICS
LC | 120713040 | :007/040 | T2 DI STAN MEL - RVRBNK :7/40 RPL INSS | VICTOR | ETL.3840.INSL.NCER | 2021-03-30 | 2021-03-26 | 2022-05-18 | 2022-03-26 | 2022-03-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31512192 | DI STANISLAUS-MELONES #2 RPL INSS 11TWR | 93K
LC | 120713041 | :007/040 | T2 DI STNS-MEL -MTC #1 :7/040 INS HRDT | VICTOR | ETL.3830.TOWR | 2021-03-30 | 2021-03-26 | 2022-01-06 | 2022-03-26 | 2022-03-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45110985 | T2 DI STNS-MEL -MTC #1 :7/040 INS HRDT | ICQ
LC | 120713044 | 004/025 | T2 DI KRCKHFF-CLVS-SNGR #1 4/25 RMV HRDT | FRESNO | ETL.1890.TOWR | 2021-03-30 | 2021-03-29 | 2022-04-30 | 2022-03-29 | 2022-03-29 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45068128 | T2 DI KRCKHFF-CLVS-SNGR #1 4/25 RMV HRDT | ICQ
LC | 120713046 | 004/025 | T2 DI KRCKHF-CLVS-SGR #1 4/25 COMPLETE | FRESNO | ETL.1890.TOWR | 2021-03-30 | 2021-03-29 | 2022-04-30 | 2022-03-29 | 2022-03-29 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45068130 | T2 DI KRCKHF-CLVS-SGR #1 4/25 UNBRY STUB | ICQ
LC | 120713307 | 017/100 | T2 DI STAN MEL-RVR BNK 17/100 RPL DAMS | VICTOR | ETL.3840.INSL.CERA | 2021-03-30 | 2021-03-25 | 2022-05-14 | 2022-03-25 | 2022-03-25 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 45122067 | T2 DI STAN MEL-RVR BNK 17/100 RPL DAMS | ICS
LC | 120713308 | 017/100 | T2 DI STNSLS-MNTCA #2 17/100 UNBURY | VICTOR | ETL.3820.TOWR | 2021-03-30 | 2021-03-25 | 2022-02-08 | 2022-03-25 | 2022-03-25 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45123106 | T2 DI STNSLS-MNTCA #2 17/100 UNBURY | ICQ
LC | 120713362 | 001/012 | T2 DI KRCKHFF-CLVS-SNGR #1 1/12 RMV DBRS | FRESNO | ETL.1890.TOWR | 2021-03-30 | 2021-03-29 | 2022-05-25 | 2022-03-29 | 2022-03-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45073695 | T2 DI KRCKHFF-CLVS-SNGR #1 1/12 RMV DBRS | ICS
LC | 120713644 | 013/195 | T2 EI SISQUOC-SANTA YNEZ 13/195 RPL STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-30 | 2021-03-30 | 2022-04-16 | 2022-03-30 | 2022-03-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535450 | T2 DI SSQC-SNT YNZ 010/154 RPL STRW | 70Y
LC | 120714058 | 001/003 | T2 EI LAYTONVILLE-COVELO 1/3 RPL STRW | LAKEVLLE | ETL.7390.POLE.WDPS | 2021-03-30 | 2021-03-30 | 2021-06-22 | 2022-03-30 | 2022-03-30 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535424 | T2 EI LAYTONVILLE-COVELO 1/3 RPL STRW | 70Y
LC | 120714059 | 001/003 | T2 EI LAYTONVILLE-COVELO 1/3 RPL STRW | LAKEVLLE | ETL.7390.POLE.WDPS | 2021-03-30 | 2021-03-30 | 2021-06-22 | 2022-03-30 | 2022-03-30 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535424 | T2 EI LAYTONVILLE-COVELO 1/3 RPL STRW | 70Y
LC | 120714109 | 010/153 | T2 DI SSQC-SNTA YNZ 10/153 COMPLETE | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-30 | 2021-03-30 | 2022-04-16 | 2022-03-30 | 2022-03-30 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069148 | T2 DI SSQC-SNTA YNZ 10/153 RPR STRW | ICW
LC | 120714250 | 018/133 | T2 WV CAYUCOS-CAMBRIA 018/133 RPR INSW | PISMOBCH | ETL.8560.INSL.CERA | 2021-03-30 | 2021-03-30 | 2021-07-29 | 2022-03-30 | 2022-03-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44804362 | T2 WV CAYUCOS-CAMBRIA 018/133 RPR INSW | ICW
LC | 120714251 | 001/011 | T2 EI LAYTONVILLE-COVELO 1/011 RPR ANCW | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-03-30 | 2021-03-30 | 2021-07-05 | 2022-03-30 | 2022-03-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 44877571 | T2 EI LAYTONVILLE-COVELO 1/011 RPR ANCW | ICW
LC | 120714344 | 001/012 | T2 EI LAYTONVILLE-COVELO 1/12 RPR HRDW | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-03-30 | 2021-03-30 | 2021-06-22 | 2022-03-30 | 2022-03-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44877570 | T2 EI LAYTONVILLE-COVELO 1/12 RPR HRDW | ICW
LC | 120714400 | 007/063 | T2 EI CRAG VIEW-CASCADE 7/63R RPR IBWW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-30 | 2021-03-30 | 2021-08-02 | 2022-03-30 | 2022-03-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Replace | 44860196 | T2 EI CRAG VIEW-CASCADE 7/63R RPR IBWW | ICW
LC | 120714406 | :004/029A | T2 EI ROCK CREEK-POE :004/29A RPR FOND | TABLEMTN | ETL.5630.POLE.NWOD | 2021-03-30 | 2021-03-30 | 2022-07-26 | 2022-03-30 | 2022-03-30 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195429 | T2 EI ROCK CREEK-POE :004/29A RPR FOND | ICQ
LC | 120714408 | :005/038 | T2 EI RCK CRK-POE :5/38 RPR FOND | TABLEMTN | ETL.5630.TOWR | 2021-03-30 | 2021-03-30 | 2022-07-06 | 2022-03-30 | 2022-03-30 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195430 | T2 EI RCK CRK-POE :5/38 RPR FOND | ICQ
LC | 120714705 | 036/015 | T2 EI FULTON-HOPLAND 36/15 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-03-30 | 2021-03-30 | 2021-08-07 | 2022-03-30 | 2022-03-30 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535421 | T2 EI FULTON-HOPLAND 10/3 RPL POLE | 70Y
LC | 120715504 | 006/104 | T2 EI SSQC-SNT YNZ SW STA 6/104 RPL HRDD | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-30 | 2021-03-30 | 2021-11-03 | 2022-03-30 | 2022-03-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44963122 | T2 EI SSQC-SNT YNZ SW STA 6/104 RPL HRDD | ICW
LC | 120715507 | 006/107 | T2 EI SSQC-SNT YNZ SW STA 6/107 RPR GYWW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-30 | 2021-03-30 | 2021-11-03 | 2022-03-30 | 2022-03-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44963121 | T2 EI SSQC-SNT YNZ SW STA 6/107 RPR GYWW | ICW
LC | 120715508 | 006/103 | T2 EI SSQC-SNT YNZ SW STA 6/103 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-30 | 2021-03-30 | 2021-11-03 | 2022-03-30 | 2022-03-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44963127 | T2 EI SSQC-SNT YNZ SW STA 6/103 RPR STRW | ICW
LC | 120715509 | 006/108 | T2 EI SSQC-SNT YNZ SW STA 6/108 RPL HRDD | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-30 | 2021-03-30 | 2021-11-15 | 2022-03-30 | 2022-03-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44963181 | T2 EI SSQC-SNT YNZ SW STA 6/108 RPL HRDD | ICW
LC | 120715777 | 020/092 | T2 EI MSS LNDNG-LS BNS 020/092 RMV VEG | MOSSLNDG | ETL.6040.TOWR | 2021-03-30 | 2021-03-30 | 2021-10-04 | 2022-03-30 | 2022-03-30 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO CLMB FRAB | Overgrown | Vegetation | Remove
LC | 120715964 | 019/087 | T2 EI MOSS LANDING-COBURN 19/87 COMPLETE | MOSSLNDG | ETL.5330.TOWR | 2021-03-30 | 2021-03-30 | 2022-05-17 | 2022-03-30 | 2022-03-30 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45118539 | T2 EI MOSS LANDING-COBURN 19/87 RPR FOND | ICQ
LC | 120715990 | 018/082 | T2 EI MOSS LANDING-CBURN 18/82 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-03-30 | 2021-03-30 | 2022-05-17 | 2022-03-30 | 2022-03-30 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45118700 | T2 EI MOSS LANDING-CBURN 18/82 RPR FOND | ICQ
LC | 120715992 | 018/086 | T2 EI MSS LNDING-CBRN 18/086 COMPLETE | MOSSLNDG | ETL.5330.TOWR | 2021-03-30 | 2021-03-30 | 2022-05-17 | 2022-03-30 | 2022-03-30 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45118701 | T2 EI MSS LNDING-CBRN 18/086 RPR FOND | ICQ
LC | 120716020 | 018/083 | T2 EI MOSS LANDING-COBURN 18/83 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-03-30 | 2021-03-30 | 2022-05-17 | 2022-03-30 | 2022-03-30 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45118702 | T2 EI MOSS LANDING-COBURN 18/83 RPR FOND | ICQ
LC | 120717032 | 003/072 | T2 EI CLMN-CTNWD 3/72 RMV NEST | TABLEMTN | ETL.6430.POLE.WOOD | 2021-03-31 | 2021-03-25 | 2021-06-16 | 2022-03-25 | 2022-03-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP OTHR FIRE COMP OH TR2 PRTO | Debris/Nest/etc. | Structure-Wood | Remove | 44859700 | T2 EI CLMN-CTNWD 3/72 RMV NEST | ICW
LC | 120717146 | 006/057 | T2 DI PARADISE-TABLE MTN 6/57 RPR FOND | TABLEMTN | ETL.4316.TOWR | 2021-03-31 | 2021-03-30 | 2021-06-10 | 2022-03-30 | 2022-03-30 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44870419 | T2 DI PARADISE-TABLE MTN 6/57 RPR FOND | ICQ
LC | 120717147 | 006/057 | T2 DI PARADISE-TABLE MTN 6/57 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-03-31 | 2021-03-30 | 2021-07-16 | 2022-03-30 | 2022-03-30 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120717191 | 007/064 | T2 DI PARADISE-TABLE MTN 7/64 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-03-31 | 2021-03-29 | 2021-07-16 | 2022-03-29 | 2022-03-29 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120717303 | 037/004 | T2 EI FULTON-HOPLAND 37/4 RMV PL BUTT | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-03-31 | 2021-03-31 | 2021-08-07 | 2022-03-31 | 2022-03-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44877569 | T2 EI FULTON-HOPLAND 37/4 RMV PL BUTT | ICW
LC | 120717361 | 037/246 | T2 EI POE-RIO OSO 037/246 RPR STRT | TABLEMTN | ETL.5540.TOWR | 2021-03-31 | 2021-03-31 | 2022-01-04 | 2022-03-31 | 2022-03-31 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45099109 | T2 EI POE-RIO OSO 037/246 RPR STRT | ICQ
LC | 120717395 | 037/010 | T2 EI FULTON-HOPLAND 37/10 RPR GYWW | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-03-31 | 2021-03-31 | 2021-07-12 | 2022-03-31 | 2022-03-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44877568 | T2 EI FULTON-HOPLAND 37/10 RPR GYWW | ICW
LC | 120717530 | 037/248 | T2 EI POE-RIO OSO 037/248 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-03-31 | 2021-03-31 | 2022-01-05 | 2022-03-31 | 2022-03-31 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45106498 | T2 EI POE-RIO OSO 037/248 RPR FOND | ICQ
LC | 120717712 | 038/250 | T2 EI POE-RIO OSO 038/250 RPL INSS | TABLEMTN | ETL.5540.INSL.CERA | 2021-03-31 | 2021-03-31 | 2022-08-11 | 2022-03-31 | 2022-03-31 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546693 | T2 EI POE-RIO OSO RPL INSS 8TWRS | 93K
LC | 120717713 | 038/250 | T2 EI CRESTA-RIO OSO 038/250 RPL INSS | TABLEMTN | ETL.4590.INSL.CERA | 2021-03-31 | 2021-03-31 | 2022-05-05 | 2022-03-31 | 2022-03-31 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546380 | DI CRESTA-RIO OSO RPLC INSS 8 TWRS | 93K
LC | 120717714 | 038/250 | T2 EI POE-RIO OSO 038/250 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-03-31 | 2021-03-31 | 2022-01-05 | 2022-03-31 | 2022-03-31 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45106660 | T2 EI POE-RIO OSO 038/250 RPR FOND | ICQ
LC | 120717736 | 021/096 | T2 DIABLO-MESA 21/96 RPL DAMPER | PISMOBCH | ETL.4620.INSL | 2021-03-31 | 2021-03-31 | 2021-09-22 | 2022-03-31 | 2022-03-31 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Damper-Steel | Replace | 44986099 | T2 DIABLO-MESA 21/96 RPL DAMPER | ICS
LC | 120717823 | :002/009 | T2 EI BLT-RVBK-MLS SWSTA :2/9 INST INSLW | VICTOR | ETL.1070.INSL.NCER | 2021-03-31 | 2021-03-31 | 2022-04-21 | 2022-03-31 | 2022-03-31 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535289 | T2 EI BLT-RVBK-MLS SWSTA :2/9 INST INSLW | 93I
LC | 120717934 | 010/154 | T2 DI SSQC-SNT YNZ 010/154 RPL STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-31 | 2021-03-30 | 2022-04-15 | 2022-03-30 | 2022-03-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535450 | T2 DI SSQC-SNT YNZ 010/154 RPL STRW | 70Y
LC | 120718012 | :009/051 | T2 EI CRZY HRS CNY-SLNS :9/51 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2021-03-31 | 2021-03-31 | 2021-05-24 | 2022-03-31 | 2022-03-31 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44805599 | T2 EI CRZY HRS CNY-SLNS :9/51 RPL RPTS | ICB
LC | 120718082 | 038/252 | T2 EI POE-RIO OSO 038/252 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-03-31 | 2021-03-31 | 2022-01-11 | 2022-03-31 | 2022-03-31 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45106662 | T2 EI POE-RIO OSO 038/252 RPR FOND | ICQ
LC | 120718257 | 004/063 | T2 DI GRN VLY-PL SWT 4/63 RPLC INSW | MOSSLNDG | ETL.1730.INSL.NCER | 2021-03-31 | 2021-03-30 | 2022-05-03 | 2022-03-30 | 2022-03-30 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535839 | T2 DI GRN VLEY-PAUL SWT 4/61 RPL INSW | 93I
LC | 120718480 | 014/067 | T2 EI MSS LNDNG-LS BANOS 014/067 RPR STR | MOSSLNDG | ETL.6040.TOWR | 2021-03-31 | 2021-03-31 | 2022-06-30 | 2022-03-31 | 2022-03-31 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45150550 | T2 EI MSS LNDNG-LS BANOS 014/067 RPR STR | ICS
LC | 120718574 | 039/256 | T2 EI CRSTA-RIO OSO 39/256 RPL INSS | TABLEMTN | ETL.4590.INSL.CERA | 2021-03-31 | 2021-03-31 | 2022-05-07 | 2022-03-31 | 2022-03-31 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546380 | DI CRESTA-RIO OSO RPLC INSS 8 TWRS | 93K
LC | 120718575 | 039/256 | T2 EI POE-RIO OSO 039/256 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-03-31 | 2021-03-31 | 2022-01-03 | 2022-03-31 | 2022-03-31 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45106667 | T2 EI POE-RIO OSO 039/256 RPR FOND | ICQ
LC | 120718596 | 003/036 | T2 EI BRGEVLE-CTTNWD 003/036 RPR STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2021-03-31 | 2021-03-31 | 2021-04-06 | 2022-03-31 | 2022-03-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 44726473 | T2 EI BRGEVLE-CTTNWD 003/036 RPR STRW | ICW
LC | 120719021 | 006/114 | T2 EI SSQC-SNT YNZ SW STA 6/114 RPR GRWW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-31 | 2021-03-31 | 2021-11-03 | 2022-03-31 | 2022-03-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 44963134 | T2 EI SSQC-SNT YNZ SW STA 6/114 RPR GRWW | ICW
LC | 120719024 | 006/114 | T2 EI SSQC-SNT YNZ SW STA 6/114 RPR GYWW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-31 | 2021-03-31 | 2021-11-03 | 2022-03-31 | 2022-03-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44963180 | T2 EI SSQC-SNT YNZ SW STA 6/114 RPR GYWW | ICW
LC | 120719049 | 014/069 | T2 EI MSS LNDNG-LS BNS 014/069 RPR ANCS | MOSSLNDG | ETL.6040.TOWR | 2021-03-31 | 2021-03-31 | 2022-08-04 | 2022-03-31 | 2022-03-31 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair | 45508524 | T2 EI MSS LNDNG-LS BNS 014/069 RPR ANCS | ICS
LC | 120719246 | 059/536 | T2 EI RND MTN-CTND #3 59/536 RPR FOND | TABLEMTN | ETL.5650.TOWR | 2021-03-31 | 2021-03-31 | 2022-01-19 | 2022-03-31 | 2022-03-31 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45111982 | T2 EI RND MTN-CTND #3 59/536 RPR FOND | ICQ
LC | 120719350 | 017/406 | T2 EI DRUM-GV-WEIMAR 17/406 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2021-03-31 | 2021-03-31 | 2022-07-05 | 2022-03-31 | 2022-03-31 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535298 | T3 DI DRM-GRSS VLLY-WMR B17/384 RPR PL | 70Y
LC | 120719426 | 003/009 | T2 EI LYTNVLLE-CVLO 3/9 RPR STRW | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-03-31 | 2021-03-31 | 2021-06-21 | 2022-03-31 | 2022-03-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44877960 | T2 EI LYTNVLLE-CVLO 3/9 RPR STRW | ICW
LC | 120719429 | 003/009 | T2 EI LYTNVLLE-CVLO 3/9 REFRAME | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-03-31 | 2021-03-31 | 2021-06-21 | 2022-03-31 | 2022-03-31 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31535430 | T2 EI LYTNVLLE-CVLO 3/9 REFRAME | 93E
LC | 120719719 | 029/445 | T2 EI CLAY-MARTEL 029/445 RPL POLE | VICTOR | ETL.8250.POLE.WOOD | 2021-03-31 | 2021-03-31 | 2021-07-20 | 2022-03-31 | 2022-03-31 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535448 | T2 EI CLAY-MARTEL 029/444 RPL STRW | 70Y
LC | 120719726 | 040/266 | T2 EI CRSTA-RIO OSO 40/266 COMPLETE | TABLEMTN | ETL.4590.INSL.CERA | 2021-03-31 | 2021-03-31 | 2022-05-07 | 2022-03-31 | 2022-03-31 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546381 | DI CRESTA-RIO OSO RPL INSS 10TWRS | 93K
LC | 120719965 | 007/118 | T2 EI SSQC-SNT YNZ SW ST 7/118 RPL HRDD | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-31 | 2021-03-31 | 2022-01-13 | 2022-03-31 | 2022-03-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45069149 | T2 EI SSQC-SNT YNZ SW ST 7/118 RPL HRDD | ICW
LC | 120720030 | 031/204 | T2NT DI POE-RIO OSO 31/204 RPLC HRDT | TABLEMTN | ETL.5540.TOWR | 2021-03-31 | 2021-03-22 | 2021-12-27 | 2022-03-22 | 2022-03-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2N PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45099107 | T2NT DI POE-RIO OSO 31/204 RPLC HRDT | ICQ
LC | 120720098 | :004/005 | T2 EI BLT-RVBNK-MLNS SWST :4/5 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-03-31 | 2021-03-31 | 2022-04-18 | 2022-03-31 | 2022-03-31 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31539414 | T2 DI BLLT-RVRBNK-MLS SWS :1/7 RPL STRW | 70Y
LC | 120720544 | 004/002 | T2 EI LYTNVLLE-CVLO 04/002 REFRAME | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-03-31 | 2021-03-31 | 2021-06-22 | 2022-03-31 | 2022-03-31 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31535430 | T2 EI LYTNVLLE-CVLO 3/9 REFRAME | 93E
LC | 120720568 | 003/005 | T2 EI LAYTONVILLE-COVELO 3/5 REPL POLE | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-03-31 | 2021-03-31 | 2021-06-21 | 2022-03-31 | 2022-03-31 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536025 | T2 EI LAYTONVILLE-COVELO 3/5 REPL POLE | 70Y
LC | 120720578 | 064/000 | T2 WV HUMBOLDT-TRINITY 064/000 INS DMPW | EUREKA | ETL.1820.INSL.CERA | 2021-03-31 | 2021-03-31 | 2022-06-05 | 2022-03-31 | 2022-03-31 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44829898 | T2 WV HUMBOLDT-TRINITY 064/000 INS DMPW | ICS
LC | 120720907 | 007/120 | T2 EI SSQC-SNT YNZ SW ST 7/120 RPR INSW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-03-31 | 2021-03-31 | 2022-01-13 | 2022-03-31 | 2022-03-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Repair | 45069150 | T2 EI SSQC-SNT YNZ SW ST 7/120 RPR INSW | ICW
LC | 120720996 | 004/005 | T2 EI LYTNVLLE-CVLO 04/005 RPL STRW | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-03-31 | 2021-03-31 | 2021-06-22 | 2022-03-31 | 2022-03-31 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535424 | T2 EI LAYTONVILLE-COVELO 1/3 RPL STRW | 70Y
LC | 120721277 | 009/038 | T2 EI EGL RCK-FLTN-SILVERD 9/38 RPR FOND | LAKEVLLE | ETL.4392.TOWR | 2021-03-31 | 2021-03-31 | 2022-01-26 | 2022-03-31 | 2022-03-31 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45107540 | T2 EI EGL RCK-FLTN-SILVERD 9/38 RPR FOND | ICQ
LC | 120723749 | 004/032 | T2 DI VAC-VCVL-JMSN-N. TWR 4/32 RPLC INS | LAKEVLLE | ETL.4100.INSL.CERA | 2021-04-01 | 2021-03-29 | 2022-02-24 | 2022-03-29 | 2022-03-29 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549199 | EI VCA-VCVILE-JMESN-NRTH TO RPL INSS 7TW | 93K
LC | 120723791 | 004/032 | T2 DI VACA-VCVL-CORDELIA 4/32 RPR SPLS | SACTO | ETL.4090.INSL.NCER | 2021-04-01 | 2021-03-29 | 2022-05-11 | 2022-03-29 | 2022-03-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 44737719 | T2 DI VACA-VCVL-CORDELIA 4/32 RPR SPLS | ICS
LC | 120723836 | 008/052 | T2 DI STNSLS-MLNS-MNTC 8/52 RPR SPLS | VICTOR | ETL.3830.INSL | 2021-04-01 | 2021-03-31 | 2022-03-03 | 2022-03-31 | 2022-03-31 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 44978044 | T2 DI STNSLS-MLNS-MNTC 8/52 RPR SPLS | ICS
LC | 120724030 | 037/018 | T2 EI FULTON-HOPLAND 37/18 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2021-08-06 | 2022-04-01 | 2022-04-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31535421 | T2 EI FULTON-HOPLAND 10/3 RPL POLE | 70Y
LC | 120724037 | 038/001 | T2 EI FULTON-HOPLAND 38/1 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2021-08-06 | 2022-04-01 | 2022-04-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31535421 | T2 EI FULTON-HOPLAND 10/3 RPL POLE | 70Y
LC | 120724163 | :005/001 | T2 EI BLT-RVRBK-MLS SW ST :5/1 RPR GYWW | VICTOR | ETL.1070.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2022-04-21 | 2022-04-01 | 2022-04-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45151559 | T2 EI BLT-RVRBK-MLS SW ST :5/1 RPR GYWW | ICW
LC | 120724581 | 022/130 | T2 DI STNSLS-MNTCA #2 22/130 UNBURY | VICTOR | ETL.3820.TOWR | 2021-04-01 | 2021-03-31 | 2022-02-14 | 2022-03-31 | 2022-03-31 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45123127 | T2 DI STNSLS-MNTCA #2 22/130 UNBURY | ICQ
LC | 120724585 | 004/017 | T2 DI ORVLL-THM-TBL MTN #1 4/17 RMV STEP | TABLEMTN | ETL.6621.TOWR | 2021-04-01 | 2021-03-22 | 2022-08-11 | 2022-03-22 | 2022-03-22 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45195432 | T2 DI ORVLL-THM-TBL MTN #1 4/17 RMV STEP | ICS
LC | 120724726 | 014/053 | T2 EI DIABLO-MIDWAY #3 14/53 RMV VEG | PISMOBCH | ETL.5980.TOWR | 2021-04-01 | 2021-04-01 | 2021-05-10 | 2022-04-01 | 2022-04-01 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120724758 | 021/288 | T2 DI SSQC-SNT YNZ SW 21/288 RPL STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2022-05-20 | 2022-04-01 | 2022-04-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535451 | T2 DI SISQUOC-SANTA YNZ 17/253 RPLC STRW | 70Y
LC | 120724759 | 017/249 | T2 DI SSQC-SNT YNZ SW 17/249 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2022-06-27 | 2022-04-01 | 2022-04-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069151 | T2 DI SSQC-SNT YNZ SW 17/249 RPR STRW | ICW
LC | 120724887 | 020/278 | T2 DI SSQC-SNT YNZ 20/278 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2022-03-03 | 2022-04-01 | 2022-04-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069152 | T2 DI SSQC-SNT YNZ 20/278 RPR STRW | ICW
LC | 120725062 | 019/268 | T2 DI SSQC-SNT YNZ 19/268 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2022-03-02 | 2022-04-01 | 2022-04-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069153 | T2 DI SSQC-SNT YNZ 19/268 RPR STRW | ICW
LC | 120725152 | 005/042 | T2 DI VACA-VACAVILLE-JMSN 5/42 RPR FOND | LAKEVLLE | ETL.4100.TOWR | 2021-04-01 | 2021-04-01 | 2022-04-27 | 2022-04-01 | 2022-04-01 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45126626 | T2 DI VACA-VACAVILLE-JMSN 5/42 RPR FOND | ICQ
LC | 120725206 | :006/000 | T2 EI BLT-RVRBK-MLS SWST :6/0 INST INSLS | VICTOR | ETL.1070.INSL.NCER | 2021-04-01 | 2021-04-01 | 2022-04-18 | 2022-04-01 | 2022-04-01 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535290 | T2 BLLT-RBK-MLNS SW :005/001 RPL INSW | 93I
LC | 120725787 | :006/007 | T2 DI BLT-RVRBNK-MLNS :6/7 RPR STRW | VICTOR | ETL.1070.POLE.NWOD | 2021-04-01 | 2021-03-26 | 2022-04-08 | 2022-03-26 | 2022-03-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45151560 | T2 DI BLT-RVRBNK-MLNS :6/7 RPR STRW | ICW
LC | 120725815 | :014/074 | T2 EI CRZY HRS CNY-SLN-SL :14/74 RMV VEG | MOSSLNDG | ETL.2900.TOWR | 2021-04-01 | 2021-04-01 | 2021-09-24 | 2022-04-01 | 2022-04-01 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120725818 | 018/425 | T2 EI DRUM-GV-WEIMAR 18/425 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2022-07-05 | 2022-04-01 | 2022-04-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31535167 | T2 EI DRUM-GV-WEIMAR B16/364 RPL POLE | 70Y
LC | 120725900 | 008/132 | T2 EI SSQC-SNT YNZ SW ST 8/132 RPL HRDD | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2022-01-13 | 2022-04-01 | 2022-04-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45069154 | T2 EI SSQC-SNT YNZ SW ST 8/132 RPL HRDD | ICW
LC | 120726305 | 055/495 | T2 EI ROUND MTN-CTTN #2 55/495 RMV VEG | TABLEMTN | ETL.5650.TOWR | 2021-04-01 | 2021-04-01 | 2022-08-31 | 2022-04-01 | 2022-04-01 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120726307 | 055/495 | T2 EI ROUND MTN-CTTN #2 55/495 RMV STEP | TABLEMTN | ETL.5650.TOWR | 2021-04-01 | 2021-04-01 | 2022-02-18 | 2022-04-01 | 2022-04-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45111981 | T2 EI ROUND MTN-CTTN #2 55/495 RMV STEP | ICQ
LC | 120726406 | 018/428 | T2 EI DRUM-GV-WEIMAR 18/428 RPR WDPKR | SACTO | ETL.6760.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2022-03-25 | 2022-04-01 | 2022-04-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44737590 | T2 EI DRUM-GV-WEIMAR 18/428 RPR WDPKR | ICW
LC | 120726683 | 018/432 | T2 EI DRUM-GV-WEIMAR 18/432 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2022-01-13 | 2022-04-01 | 2022-04-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44737591 | T2 EI DRUM-GV-WEIMAR 18/432 RPR GYWW | ICW
LC | 120726762 | 000/015 | T2 WV CLEAR LAKE-HOPLAND 0/15 RPR SPLW | LAKEVLLE | ETL.6390.POLE.NWOD | 2021-04-01 | 2021-04-01 | 2022-02-08 | 2022-04-01 | 2022-04-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Repair | 45136114 | T2 WV CLEAR LAKE-HOPLAND 0/15 RPR SPLW | ICW
LC | 120726791 | 008/135 | T2 EI SQC-ST YZ SW ST 8/135 RPL HRD CMPL | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2022-04-11 | 2022-04-01 | 2022-04-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45069110 | T2 EI SSQC-SNT YNEZ SW ST 8/135 RPL HRDD | ICW
LC | 120726805 | 006/011 | T2 EI LAYTONVILLE-COVELO 6/11 RPR STRW | LAKEVLLE | ETL.7390.POLE.NWOD | 2021-04-01 | 2021-04-01 | 2021-06-23 | 2022-04-01 | 2022-04-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44877565 | T2 EI LAYTONVILLE-COVELO 6/11 RPR STRW | ICW
LC | 120726859 | 044/180 | T2 MIDWAY-WHIRLWIND 44/180 RPL ZENA | MIDWAY | ETL.6030.TOWR | 2021-04-01 | 2021-04-01 | 2021-12-17 | 2022-04-01 | 2022-04-01 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 45000553 | T2 MIDWAY-WHIRLWIND 44/180 RPL ZENA | ICB
LC | 120726908 | 008/156 | T2 EI PIT#1-HAT CRK#2-BRNY 8/156 RPR ANC | TABLEMTN | ETL.7040.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2022-07-19 | 2022-04-01 | 2022-04-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45214063 | T2 EI PIT#1-HAT CRK#2-BRNY 8/156 RPR ANC | ICW
LC | 120726911 | 021/125 | T2 DI STANISLAUS-MNTC #2 21/125 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-01 | 2021-04-01 | 2022-02-14 | 2022-04-01 | 2022-04-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123122 | T2 DI STANISLAUS-MNTC #2 21/125 RPR FOND | ICQ
LC | 120726913 | 017/253 | T2 DI SISQUOC-SANTA YNZ 17/253 RPLC STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2022-05-18 | 2022-04-01 | 2022-04-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535451 | T2 DI SISQUOC-SANTA YNZ 17/253 RPLC STRW | 70Y
LC | 120727075 | 008/137 | T2 EI SSQC-SNT YNEZ SW ST 8/137 RPL HRDD | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2022-04-11 | 2022-04-01 | 2022-04-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45069157 | T2 EI SSQC-SNT YNEZ SW ST 8/137 RPL HRDD | ICW
LC | 120727138 | 055/494 | T2 EI ROUND MTN-CTTN #2 55/494 RMV STEP | TABLEMTN | ETL.5650.TOWR | 2021-04-01 | 2021-04-01 | 2022-02-18 | 2022-04-01 | 2022-04-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45111980 | T2 EI ROUND MTN-CTTN #2 55/494 RMV STEP | ICQ
LC | 120727177 | :009/005 | T2 EI BLT-RVBK-MLNS SW :9/5 INST INSLW | VICTOR | ETL.1070.INSL.NCER | 2021-04-01 | 2021-04-01 | 2022-05-05 | 2022-04-01 | 2022-04-01 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535290 | T2 BLLT-RBK-MLNS SW :005/001 RPL INSW | 93I
LC | 120727226 | 001/003 | T2 EI LAYTONVILLE-COVELO 1/3 RPL POLE | LAKEVLLE | ETL.7390.POLE.WDPS | 2021-04-01 | 2021-03-30 | 2021-06-22 | 2022-03-30 | 2022-03-30 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535424 | T2 EI LAYTONVILLE-COVELO 1/3 RPL STRW | 70Y
LC | 120727230 | :009/006 | T2 EI BLT-RVBK-MLNS SW ST :9/6 RPL INSLW | VICTOR | ETL.1070.INSL.NCER | 2021-04-01 | 2021-04-01 | 2022-05-04 | 2022-04-01 | 2022-04-01 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535290 | T2 BLLT-RBK-MLNS SW :005/001 RPL INSW | 93I
LC | 120727388 | 005/003 | T2 EI LYTNVLE-CVLO 5/3 RPR ANCW | LAKEVLLE | ETL.7390.POLE.WDPS | 2021-04-01 | 2021-04-01 | 2021-06-20 | 2022-04-01 | 2022-04-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 44886439 | T2 EI LYTNVLE-CVLO 5/3 RPR ANCW | ICW
LC | 120727389 | :006/003 | T2 EI BLT-RVRBK-MLS SW ST :6/3 RPL INSLW | VICTOR | ETL.1070.INSL.NCER | 2021-04-01 | 2021-04-01 | 2022-04-12 | 2022-04-01 | 2022-04-01 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31539420 | T2 DI BLLT-RBK-MLS SWS :005/006 RPL INSW | 93I
LC | 120727397 | 006/000 | T2 EI LAYTONVILLE-COVELO 6/0 RPR STRW | LAKEVLLE | ETL.7390.POLE.WDPS | 2021-04-01 | 2021-04-01 | 2021-06-22 | 2022-04-01 | 2022-04-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44877719 | T2 EI LAYTONVILLE-COVELO 6/0 RPR STRW | ICW
LC | 120727501 | 006/012 | T2 EI LAYTONVILLE-COVELO 6/12 REPLUMB | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2021-06-23 | 2022-04-01 | 2022-04-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44877563 | T2 EI LAYTONVILLE-COVELO 6/12 REPLUMB | ICW
LC | 120727502 | 006/012 | T2 EI LAYTONVILLE-COVELO 6/12 REFRAME | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2021-06-23 | 2022-04-01 | 2022-04-01 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31535029 | T2 EI LAYTONVILLE-COVELO 6/12 REFRAME | 93E
LC | 120727593 | :009/003 | T2 EI BLT-RVBK-MLNS SW ST :9/3 INST ARMW | VICTOR | ETL.1070.INSL.NCER | 2021-04-01 | 2021-04-01 | 2022-05-06 | 2022-04-01 | 2022-04-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Conductor-Wood | Repair | 45151561 | T2 EI BLT-RVBK-MLNS SW ST :9/3 INST ARMW | ICW
LC | 120728061 | 009/143 | T2 EI SC-ST YZ SW ST 9/143 RPR GYWW CMPL | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2022-04-16 | 2022-04-01 | 2022-04-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069159 | T2 EI SSQC-SNT YNZ SW STA 9/143 RPR GYWW | ICW
LC | 120733932 | 007/080B | T2 EI GRN VALLEY-PAUL SWT 7/80B RPL INSW | MOSSLNDG | ETL.1730.INSL.NCER | 2021-04-02 | 2021-04-01 | 2022-08-26 | 2022-04-01 | 2022-04-01 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31596079 | T2 EI GRN VALLEY-PAUL SWT 7/80B RPL INSW | 93I
LC | 120733933 | 007/083 | T2 EI GRN VALLEY-PAUL SWT 7/83L RPR GYWW | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-04-02 | 2021-04-01 | 2022-03-09 | 2022-04-01 | 2022-04-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213429 | T2 EI GRN VALLEY-PAUL SWT 7/83L RPR GYWW | ICW
LC | 120733934 | 007/084 | T2 EI GRN VALLEY-PAUL SWT 7/84 COMPLETE | MOSSLNDG | ETL.1730.INSL.CERA | 2021-04-02 | 2021-04-01 | 2022-08-25 | 2022-04-01 | 2022-04-01 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535459 | T2 EI GRN VLLY-PAUL SWT-WD 6/72 RPL INSW | 93I
LC | 120734185 | 006/039 | T2 DI KRKF-CS-SR #1 6/39 RPL INSS CMPLTD | FRESNO | ETL.1890.INSL.CERA | 2021-04-02 | 2021-04-01 | 2022-05-26 | 2022-04-01 | 2022-04-01 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528484 | DI KERCKHOFF-CLVS-SNGR #1 RPLC INSS 22TW | 93K
LC | 120734351 | 022/137 | T2 DI STANSLS-MLNS-MNTC 22/137 RPR SPLS | VICTOR | ETL.3830.INSL | 2021-04-02 | 2021-04-01 | 2022-03-07 | 2022-04-01 | 2022-04-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 44978053 | T2 DI STANSLS-MLNS-MNTC 22/137 RPR SPLS | ICS
LC | 120734412 | 008/154 | T2 EI PT #1-HT CRK #2-BRNY 8/154 REFRAME | TABLEMTN | ETL.7040.POLE.WOOD | 2021-04-02 | 2021-04-02 | 2022-07-21 | 2022-04-02 | 2022-04-02 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31609440 | T2 DI PT#1-HT CRK#2-BRY 8/149 REFRAME | 93E
LC | 120734650 | 055/493 | T2 EI RND MTN-CTTNWD #3 55/493 RMV STEP | TABLEMTN | ETL.5650.TOWR | 2021-04-02 | 2021-04-02 | 2022-02-18 | 2022-04-02 | 2022-04-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45111779 | T2 EI RND MTN-CTTNWD #3 55/493 RMV STEP | ICQ
LC | 120734737 | 054/492 | T2 EI RND MTN-CTTNWD 054/492 RMV STEP | TABLEMTN | ETL.5650.TOWR | 2021-04-02 | 2021-04-02 | 2022-02-18 | 2022-04-02 | 2022-04-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45111778 | T2 EI RND MTN-CTTNWD 054/492 RMV STEP | ICQ
LC | 120734813 | 022/128 | T2 DI STN ML SW ST-RK JT 22/128 RPL INSS | VICTOR | ETL.3840.INSL.CERA | 2021-04-02 | 2021-03-31 | 2022-04-23 | 2022-03-31 | 2022-03-31 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31512192 | DI STANISLAUS-MELONES #2 RPL INSS 11TWR | 93K
LC | 120734837 | 007/079 | T2 EI GRN VLLY-PAUL SWT 7/79 RPR HRDW | MOSSLNDG | ETL.1730.POLE.WOOD | 2021-04-02 | 2021-04-02 | 2022-03-11 | 2022-04-02 | 2022-04-02 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213431 | T2 EI GRN VLLY-PAUL SWT 7/79 RPR HRDW | ICW
LC | 120734838 | 007/079 | T2 EI GRN VALLEY-PAUL SWT 7/79 RPL INSW | MOSSLNDG | ETL.1730.INSL.CERA | 2021-04-02 | 2021-04-02 | 2022-05-06 | 2022-04-02 | 2022-04-02 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535459 | T2 EI GRN VLLY-PAUL SWT-WD 6/72 RPL INSW | 93I
LC | 120734840 | 054/491 | T2 EI RND MTN-CTTNWD #3 54/491 RMV STEP | TABLEMTN | ETL.5650.TOWR | 2021-04-02 | 2021-04-02 | 2022-02-18 | 2022-04-02 | 2022-04-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45111777 | T2 EI RND MTN-CTTNWD #3 54/491 RMV STEP | ICQ
LC | 120734914 | 005/097 | T2 DELTA-MTN GATE JCT 5/97 RPR SPLW | TABLEMTN | ETL.6750.INSL.CERA | 2021-04-02 | 2021-04-02 | 2022-08-20 | 2022-04-02 | 2022-04-02 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Replace | 45296743 | T2 DELTA-MTN GATE JCT 5/97 RPR SPLW | ICW
LC | 120734982 | 008/149 | T2 EI PIT #1-HT CRK #2-BRNY 8/1 RPR COND | TABLEMTN | ETL.7040.POLE.WOOD | 2021-04-02 | 2021-04-02 | 2022-07-20 | 2022-04-02 | 2022-04-02 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Conductor-Wood | Repair | 45213855 | T2 EI PIT #1-HT CRK #2-BRNY 8/1 RPR COND | ICW
LC | 120735135 | :010/003 | T2 EI BLLTA-RVRBNK-MLNES :10/3 RPR ANCW | VICTOR | ETL.1070.POLE.WOOD | 2021-04-02 | 2021-04-02 | 2022-02-23 | 2022-04-02 | 2022-04-02 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45151562 | T2 EI BLLTA-RVRBNK-MLNES :10/3 RPR ANCW | ICW
LC | 120735246 | 054/489 | T2 EI RND MTN-CTTNWD #3 54/489 RMV STEP | TABLEMTN | ETL.5650.TOWR | 2021-04-02 | 2021-04-02 | 2022-02-18 | 2022-04-02 | 2022-04-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45111773 | T2 EI RND MTN-CTTNWD #3 54/489 RMV STEP | ICQ
LC | 120735315 | :010/006 | T2 EI BLLTA-RVRBNK-MLNES :10/6 RPL INSW | VICTOR | ETL.1070.INSL.NCER | 2021-04-02 | 2021-04-02 | 2022-05-03 | 2022-04-02 | 2022-04-02 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31602417 | T2 EI BLLTA-RVRBNK-MLNES :10/6 RPL INSW | 93K
LC | 120735316 | :010/006 | T2 EI BLLTA-RVRBNK-MLNES :10/6 RPR GYWW | VICTOR | ETL.1070.POLE.WOOD | 2021-04-02 | 2021-04-02 | 2022-05-03 | 2022-04-02 | 2022-04-02 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45151564 | T2 EI BLLTA-RVRBNK-MLNES :10/6 RPR GYWW | ICW
LC | 120735525 | :010/001 | T2 EI BLLTA-RVRBNK-MLNS :10/1 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-04-02 | 2021-04-02 | 2022-05-03 | 2022-04-02 | 2022-04-02 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536314 | T2 DI BLT-RVRBNK-MLNS RPL STRW | 70Y
LC | 120735861 | 024/137 | T2 DI TSL-SLD-MNTC 24/137 RPR GYWW | VICTOR | ETL.4000.POLE.WOOD | 2021-04-02 | 2021-03-31 | 2021-10-06 | 2022-03-31 | 2022-03-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44975290 | T2 DI TSL-SLD-MNTC 24/137 RPR GYWW | ICW
LC | 120735872 | 020/129 | T2 DI STNSLS-MLS -MTC #1 20/129 UNBURY | VICTOR | ETL.3830.TOWR | 2021-04-02 | 2021-03-31 | 2022-02-14 | 2022-03-31 | 2022-03-31 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123118 | T2 DI STNSLS-MLS -MTC #1 20/129 UNBURY | ICQ
LC | 120736084 | 006/078 | T2 EI GRN VLLY-PAUL SWT-WD 6/78 RPL INSW | MOSSLNDG | ETL.1730.INSL.NCER | 2021-04-02 | 2021-04-02 | 2022-05-05 | 2022-04-02 | 2022-04-02 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535459 | T2 EI GRN VLLY-PAUL SWT-WD 6/72 RPL INSW | 93I
LC | 120736277 | :010/007 | T2 EI BLLTA-RVRBNK-MLNES :10/7 COMPLETE | VICTOR | ETL.1070.POLE.WOOD | 2021-04-02 | 2021-04-02 | 2022-05-02 | 2022-04-02 | 2022-04-02 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45151565 | T2 EI BLLTA-RVRBNK-MLNES :10/7 RPR STRW | ICW
LC | 120736499 | 037/264 | T2 DI MIDDLE FORK-GLD HL 37/264 INS BOLT | SACTO | ETL.5140.TOWR | 2021-04-02 | 2021-03-31 | 2022-05-23 | 2022-03-31 | 2022-03-31 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 44737592 | T2 DI MIDDLE FORK-GLD HL 37/264 INS BOLT | ICQ
LC | 120736813 | 054/304 | T2 DI TMBLR-SN LS OBISPO 54/304 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-02 | 2021-03-22 | 2022-04-21 | 2022-03-22 | 2022-03-22 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31526478 | T3 EI TMBLOR-SN LS OBSPO RPL INSL 5TWR | 93K
LC | 120736894 | 019/447 | T2 EI DRUM-GV-WEIMAR 19/447 RMV VEG | SACTO | ETL.6760.POLE.WOOD | 2021-04-02 | 2021-04-02 | 2022-02-08 | 2022-04-02 | 2022-04-02 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120737109 | :016/085 | T2 EI CRZY HRS CNYN-SLNS-SL:16/85 RPR TW | MOSSLNDG | ETL.2900.TOWR | 2021-04-02 | 2021-04-02 | 2021-07-08 | 2022-04-02 | 2022-04-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair | 44839307 | T2 EI CRZY HRS CNYN-SLNS-SL:16/85 RPR TW | ICQ
LC | 120737120 | :016/085 | T2 EI CRZY HRS CNYN-SLNS-SL:16/85 RPR FO | MOSSLNDG | ETL.2900.TOWR | 2021-04-02 | 2021-04-02 | 2021-07-11 | 2022-04-02 | 2022-04-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44839308 | T2 EI CRZY HRS CNYN-SLNS-SL:16/85 RPR FO | ICQ
LC | 120737274 | 022/131A | T2 DI STANSLS-MNTC #2 22/131A UNBURY | VICTOR | ETL.3820.TOWR | 2021-04-02 | 2021-03-31 | 2022-02-14 | 2022-03-31 | 2022-03-31 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123128 | T2 DI STANSLS-MNTC #2 22/131A UNBURY | ICQ
LC | 120737370 | 008/051 | T2 DI STN ML SW ST-RK JT 8/51 RPR SPLS | VICTOR | ETL.3840.INSL.CERA | 2021-04-02 | 2021-04-01 | 2022-05-12 | 2022-04-01 | 2022-04-01 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122068 | T2 DI STN ML SW ST-RK JT 8/51 RPR SPLS | ICS
LC | 120737372 | 008/051 | T2 DI STN ML SW ST-RK JT 8/51 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-02 | 2021-04-01 | 2022-01-25 | 2022-04-01 | 2022-04-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45122118 | T2 DI STN ML SW ST-RK JT 8/51 RPR FOND | ICQ
LC | 120737480 | 004/009 | T2 EI LYTNVILLE-COVELO 4/9 RPL HRDW | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-04-02 | 2021-04-02 | 2021-06-22 | 2022-04-02 | 2022-04-02 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44895263 | T2 EI LYTNVILLE-COVELO 4/9 RPL HRDW | ICW
LC | 120737639 | 016/077 | T2 EI MSS LNDNG-LS BNS 16/77 RMV VEG | MOSSLNDG | ETL.6040.TOWR | 2021-04-02 | 2021-04-02 | 2021-09-22 | 2022-04-02 | 2022-04-02 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CNCL OH FMOB TR2 PRTO CLMB FRAB | Overgrown | Vegetation | Remove
LC | 120737746 | 112/002B | T2 WV HUMBOLDT-TRINITY 112/2 INS DAMW | EUREKA | ETL.1820.INSL.NCER | 2021-04-02 | 2021-04-02 | 2022-08-24 | 2022-04-02 | 2022-04-02 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Wood | Install | 45010824 | T2 WV HUMBOLDT-TRINITY 112/2 INS DAMW | ICW
LC | 120738879 | 014/069 | T2 EI MSS LNDING-CBRN 14/69 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-04-03 | 2021-04-02 | 2022-05-18 | 2022-04-02 | 2022-04-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44722397 | T2 EI MSS LNDING-CBRN 14/69 RPR FOND | ICQ
LC | 120738889 | 015/073 | T2 EI MSS LNDG-LS AGLS SW 15/73 RPL INSS | MOSSLNDG | ETL.5340.INSL | 2021-04-03 | 2021-04-02 | 2022-04-12 | 2022-04-02 | 2022-04-02 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31539341 | T2 EI MSS LNDG-LS AGLS SW RPL INSS 6TWR | 93K
LC | 120738892 | 015/070 | T2 EI MOSS LANDING-COBURN 15/70 FOND CMT | MOSSLNDG | ETL.5330.TOWR | 2021-04-03 | 2021-04-02 | 2022-05-18 | 2022-04-02 | 2022-04-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45118704 | T2 EI MOSS LANDING-COBURN 15/70 RPR FOND | ICQ
LC | 120738898 | 016/077 | T2 EI MSS LNDING-COBURN 16/77 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-04-03 | 2021-04-02 | 2022-05-18 | 2022-04-02 | 2022-04-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44722398 | T2 EI MSS LNDING-COBURN 16/77 RPR FOND | ICQ
LC | 120738905 | 015/073 | T2 EI MOSS LANDING-COBURN 15/73 FOND CMP | MOSSLNDG | ETL.5330.TOWR | 2021-04-03 | 2021-04-02 | 2022-05-18 | 2022-04-02 | 2022-04-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45118706 | T2 EI MOSS LANDING-COBURN 15/73 RPR FOND | ICQ
LC | 120739511 | 007/130 | T2 EI PIT #1HT CRK #2-BNY 7/130 PL BUTT | TABLEMTN | ETL.7040.POLE.WOOD | 2021-04-03 | 2021-04-03 | 2022-05-21 | 2022-04-03 | 2022-04-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45213854 | T2 EI PIT #1HT CRK #2-BNY 7/130 PL BUTT | ICW
LC | 120739584 | :012/063 | T2 EI CRY HRS CNN-SLINS-SL:12/63 RPR FND | MOSSLNDG | ETL.2900.TOWR | 2021-04-03 | 2021-04-03 | 2021-07-11 | 2022-04-03 | 2022-04-03 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44722601 | T2 CRZY HRS CNYN-SLINS-SL:12/63 RPR FOND | ICQ
LC | 120739641 | 024/002 | T2 EI GRBRVILE-LYTNVILLE 24/2 RPL DAMPER | WILLITS | ETL.8365.INSL.NCER | 2021-04-03 | 2021-04-03 | 2022-04-13 | 2022-04-03 | 2022-04-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Damper-Wood | Replace | 44754887 | T2 EI GRBRVILE-LYTNVILLE 24/2 RPL DAMPER | ICW
LC | 120739806 | 020/470 | T2 EI DRUM-GV-WEIMAR 20/470 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2021-04-03 | 2021-04-03 | 2022-07-30 | 2022-04-03 | 2022-04-03 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | Rotten | Structure-Wood | Replace | 31535913 | T2 EI DRUM-GV-WEIMAR 21/494 RPL POLE | 70Y
LC | 120739900 | :012/065 | T2 EI CRZY HRS CNY-SLN :12/65 RPR FOND | MOSSLNDG | ETL.2900.TOWR | 2021-04-03 | 2021-04-03 | 2021-07-11 | 2022-04-03 | 2022-04-03 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44839309 | T2 EI CRZY HRS CNY-SLN :12/65 RPR FOND | ICQ
LC | 120740079 | :012/066 | T2 EI CRZY HRS CNN-SNS-SL:12/66 RPR FOND | MOSSLNDG | ETL.2900.TOWR | 2021-04-03 | 2021-04-03 | 2021-07-11 | 2022-04-03 | 2022-04-03 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44722602 | T2 CRZY HRS CNYN-SLNS-SL:12/66 RPR FOND | ICQ
LC | 120740135 | 006/072 | T2 EI GRN VLLY-PAUL SWT-WD 6/72 RPL INSW | MOSSLNDG | ETL.1730.INSL.NCER | 2021-04-03 | 2021-04-03 | 2022-05-06 | 2022-04-03 | 2022-04-03 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535459 | T2 EI GRN VLLY-PAUL SWT-WD 6/72 RPL INSW | 93I
LC | 120740228 | 065/472 | T2 WV BRDGVLLE-CTTNWD 65/472 RPR FOND | EUREKA | ETL.1110.TOWR | 2021-04-03 | 2021-04-03 | 2021-07-13 | 2022-04-03 | 2022-04-03 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44875579 | T2 WV BRDGVLLE-CTTNWD 65/472 RPR FOND | ICQ
LC | 120740262 | 003/025 | T2 WV OLEUM-G 3/25 RPR FOND | CONCORD | ETL.3150.TOWR | 2021-04-03 | 2021-04-03 | 2022-03-07 | 2022-04-03 | 2022-04-03 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45179088 | T2 WV OLEUM-G 3/25 RPR FOND | ICQ
LC | 120740334 | 025/001 | T2 EI GRBRVILE-LAYTNVILE 25/1 RPL DAMPER | WILLITS | ETL.8365.INSL.NCER | 2021-04-03 | 2021-04-03 | 2022-04-18 | 2022-04-03 | 2022-04-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Damper-Wood | Replace | 44754888 | T2 EI GRBRVILE-LAYTNVILE 25/1 RPL DAMPER | ICW
LC | 120740335 | 025/001 | T2 EI GRBRVILE-LAYTNVILE 25/1 RPR STRW | WILLITS | ETL.8365.POLE.NWOD | 2021-04-03 | 2021-04-03 | 2022-04-19 | 2022-04-03 | 2022-04-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44754888 | T2 EI GRBRVILE-LAYTNVILE 25/1 RPL DAMPER | ICW
LC | 120740336 | 025/001 | T2 EI GRBRVILE-LAYTNVILE 25/1 RPR GYWW | WILLITS | ETL.8365.POLE.NWOD | 2021-04-03 | 2021-04-03 | 2022-04-18 | 2022-04-03 | 2022-04-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44754888 | T2 EI GRBRVILE-LAYTNVILE 25/1 RPL DAMPER | ICW
LC | 120740445 | 025/007 | T2 EI GRBRVILE-LAYTNVILE 25/7 RMV VEG | EUREKA | ETL.8365.POLE.WOOD | 2021-04-03 | 2021-04-03 | 2021-06-03 | 2022-04-03 | 2022-04-03 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120741773 | 023/000 | T2 EI GARBRVILLE-LYTNVILE 23/0 RPL POLE | WILLITS | ETL.8365.POLE.WOOD | 2021-04-05 | 2021-04-05 | 2022-04-12 | 2022-04-05 | 2022-04-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP SUBS COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31595721 | T2 EI GARBRVILLE-LYTNVILE 23/0 RPL POLE | 70Y
LC | 120741782 | :005/001 | T2 BLLT-RBK-MLNS SW :005/001 RPL INSW | VICTOR | ETL.1070.INSL.NCER | 2021-04-05 | 2021-04-05 | 2022-04-21 | 2022-04-05 | 2022-04-05 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535290 | T2 BLLT-RBK-MLNS SW :005/001 RPL INSW | 93I
LC | 120741909 | 005/070 | T2 EI GREEN VALLEY-PAUL 05/070 RPL HRDW | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-04-05 | 2021-04-05 | 2022-05-02 | 2022-04-05 | 2022-04-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45211630 | T2 EI GREEN VALLEY-PAUL 05/070 RPL HRDW | ICW
LC | 120741933 | 005/045A | T2 EI CRAG VIEW-CASCADE 5/45A RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-05 | 2021-04-05 | 2021-06-16 | 2022-04-05 | 2022-04-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859919 | T2 EI CRAG VIEW-CASCADE 5/45A RPR GYWW | ICW
LC | 120741955 | 005/045B | T2 EI CRAG VIEW-CASCADE 5/45B RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-05 | 2021-04-05 | 2021-06-18 | 2022-04-05 | 2022-04-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859960 | T2 EI CRAG VIEW-CASCADE 5/45B RPR GYWW | ICW
LC | 120741971 | 005/045C | T2 EI CRAG VIEW-CASCADE 5/045C RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-05 | 2021-04-05 | 2021-06-06 | 2022-04-05 | 2022-04-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859961 | T2 EI CRAG VIEW-CASCADE 5/045C RPR GYWW | ICW
LC | 120742025 | :006/039 | T2 DI STNSLS-MLNS SS-MTC :6/39 RPL INSS | VICTOR | ETL.3830.INSL.NCER | 2021-04-05 | 2021-03-26 | 2022-09-19 | 2022-03-26 | 2022-03-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528967 | NN STANISLAUS-MLNS-MNTC RPLC INSS 11TWR | 93K
LC | 120742027 | :006/039 | T2 DI STN ML SW ST-RBK JT :6/39 RPR INSS | VICTOR | ETL.3840.INSL.NCER | 2021-04-05 | 2021-03-26 | 2022-05-18 | 2022-03-26 | 2022-03-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551875 | T2 DI STN ML SW ST-RBK JT RPL INSS 7TWR | 93K
LC | 120742097 | 025/148 | T2 DI TESLA-SALADO-MNTC 25/148 RPL INSW | VICTOR | ETL.4000.INSL.NCER | 2021-04-05 | 2021-03-31 | 2022-02-01 | 2022-03-31 | 2022-03-31 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535486 | T2 DI TESLA-SALADO-MNTC 25/148 RPL INSW | 93I
LC | 120742182 | 007/080 | T2 DI GRN VLY-PAUL SWT 7/80 RPLC INSW | MOSSLNDG | ETL.1730.INSL.NCER | 2021-04-05 | 2021-03-30 | 2022-08-22 | 2022-03-30 | 2022-03-30 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCM COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535459 | T2 EI GRN VLLY-PAUL SWT-WD 6/72 RPL INSW | 93I
LC | 120742186 | 025/005 | T2 EI GRBRVILE-LAYTNVILE 25/5 RPR GYWW | EUREKA | ETL.8365.POLE.WOOD | 2021-04-05 | 2021-04-05 | 2022-03-24 | 2022-04-05 | 2022-04-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44754890 | T2 EI GRBRVILE-LAYTNVILE 25/5 RPR GYWW | ICW
LC | 120742219 | 025/150 | T2 DI TESLA-SALADO-MNTC 25/150 RPR GYWW | VICTOR | ETL.4000.POLE.WOOD | 2021-04-05 | 2021-03-31 | 2021-09-28 | 2022-03-31 | 2022-03-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44975299 | T2 DI TESLA-SALADO-MNTC 25/150 RPR GYWW | ICW
LC | 120742241 | 025/150 | T2 DI TESLA-SALADO-MNTC 25/150 RPR ANCW | VICTOR | ETL.4000.POLE.WOOD | 2021-04-05 | 2021-03-31 | 2021-09-27 | 2022-03-31 | 2022-03-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 44962483 | T2 DI TESLA-SALADO-MNTC 25/150 RPR ANCW | ICW
LC | 120742370 | 025/006 | T2 EI GRBRVILE-LAYTNVILE 25/6 RMV VEG | WILLITS | ETL.8365.POLE.WOOD | 2021-04-05 | 2021-04-05 | 2022-05-03 | 2022-04-05 | 2022-04-05 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120742449 | 004/042 | T2 EI CRAG VIEW-CASCADE 4/42R RPR STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-05 | 2021-04-05 | 2021-06-16 | 2022-04-05 | 2022-04-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44859918 | T2 EI CRAG VIEW-CASCADE 4/42R RPR STRW | ICW
LC | 120742650 | 023/002 | T2 EI GRBRVILE-LYTNVILE 23/2 RPR GYWW | WILLITS | ETL.8365.POLE.WOOD | 2021-04-05 | 2021-04-05 | 2022-04-11 | 2022-04-05 | 2022-04-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44754891 | T2 EI GRBRVILE-LYTNVILE 23/2 RPR GYWW | ICW
LC | 120742849 | 003/023 | T2 DI KRCKHFF-CLVS-SNGR #1 2/23 INS HRDT | FRESNO | ETL.1890.TOWR | 2021-04-05 | 2021-03-29 | 2022-02-09 | 2022-03-29 | 2022-03-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 44739590 | T2 DI KRCKHFF-CLVS-SNGR #1 2/23 INS HRDT | ICQ
LC | 120742899 | :006/000 | T2 BLLT-RBK-MELNS SW :006/000 RMV VEG | VICTOR | ETL.1070.POLE.WOOD | 2021-04-05 | 2021-04-05 | 2022-04-14 | 2022-04-05 | 2022-04-05 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE CNCL OH TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120742994 | 004/040 | T2 EI CRAG VIEW-CASCADE 4/40R RPR OPGW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-05 | 2021-04-05 | 2021-06-16 | 2022-04-05 | 2022-04-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44859917 | T2 EI CRAG VIEW-CASCADE 4/40R RPR OPGW | ICW
LC | 120743018 | 023/001 | T2 EI GRBRVLE-LYTNVILE 23/1 RPL PL | WILLITS | ETL.8365.POLE.WOOD | 2021-04-05 | 2021-04-05 | 2022-04-12 | 2022-04-05 | 2022-04-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535915 | T2 EI GRBRVLE-LYTNVILE 23/1 RPL PL | 70Y
LC | 120743040 | 025/149 | T2 DI TESLA-SALADO-MNTC 25/149 RPR GYWW | VICTOR | ETL.4000.POLE.WOOD | 2021-04-05 | 2021-04-01 | 2021-10-08 | 2022-04-01 | 2022-04-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44975298 | T2 DI TESLA-SALADO-MNTC 25/149 RPR GYWW | ICW
LC | 120743045 | 018/255 | T2 DI SSQC-SNT YNZ SW 18/255 RPL INSW | PISMOBCH | ETL.3700.INSL.NCER | 2021-04-05 | 2021-04-01 | 2022-06-27 | 2022-04-01 | 2022-04-01 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535452 | T2 DI SSQC-SNT YNZ SW 18/255 RPL INSW | 93I
LC | 120743098 | 029/444 | T2 EI CLAY-MARTEL 029/444 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-05 | 2021-04-05 | 2021-07-19 | 2022-04-05 | 2022-04-05 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535448 | T2 EI CLAY-MARTEL 029/444 RPL STRW | 70Y
LC | 120743190 | 017/250 | T2 DI SSQC-SNT YNZ SW 17/250 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-05 | 2021-04-01 | 2022-06-27 | 2022-04-01 | 2022-04-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069226 | T2 DI SSQC-SNT YNZ SW 17/250 RPR STRW | ICW
LC | 120743196 | 017/250 | T2 DI SSQC-SNT YNZ SW 17/250 RPR GYWW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-05 | 2021-04-01 | 2022-06-27 | 2022-04-01 | 2022-04-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069227 | T2 DI SSQC-SNT YNZ SW 17/250 RPR GYWW | ICW
LC | 120743303 | 023/004 | T2 EI GRBRVILE-LAYTNVILE 23/4 RPR STRW | WILLITS | ETL.8365.POLE.WOOD | 2021-04-05 | 2021-04-05 | 2022-04-13 | 2022-04-05 | 2022-04-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44754980 | T2 EI GRBRVILE-LAYTNVILE 23/4 RPR STRW | ICW
LC | 120743330 | 018/257 | T2 DI SISQUOC-SANTA YNEZ 18/257 RPL INSS | PISMOBCH | ETL.3700.INSL.CERA | 2021-04-05 | 2021-04-01 | 2021-06-07 | 2022-04-01 | 2022-04-01 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535452 | T2 DI SSQC-SNT YNZ SW 18/255 RPL INSW | 93I
LC | 120743367 | 050/205 | T2NT EI DIABLO-GATES #1 50/205 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2021-04-05 | 2021-04-05 | 2022-06-27 | 2022-04-05 | 2022-04-05 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068472 | T2NT EI DIABLO-GATES #1 50/205 RPR GYWS | ICS
LC | 120743445 | 004/039 | T2 EI CRAG VIEW-CASCADE 4/39R RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-05 | 2021-04-05 | 2021-06-16 | 2022-04-05 | 2022-04-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859914 | T2 EI CRAG VIEW-CASCADE 4/39R RPR GYWW | ICW
LC | 120743463 | 004/039 | T2 EI CRAG VIEW-CASCADE 4/39M RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-05 | 2021-04-05 | 2021-06-16 | 2022-04-05 | 2022-04-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859915 | T2 EI CRAG VIEW-CASCADE 4/39M RPR GYWW | ICW
LC | 120743535 | 004/039 | T2 EI CRAG VIEW-CASCADE 4/39L RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-05 | 2021-04-05 | 2021-06-06 | 2022-04-05 | 2022-04-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859916 | T2 EI CRAG VIEW-CASCADE 4/39L RPR GYWW | ICW
LC | 120743564 | 021/296 | T2 DI SSQC-SNT YNZ 21/296 RPL INSW JUMW | PISMOBCH | ETL.3700.INSL.CERA | 2021-04-05 | 2021-04-01 | 2022-06-28 | 2022-04-01 | 2022-04-01 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535452 | T2 DI SSQC-SNT YNZ SW 18/255 RPL INSW | 93I
LC | 120743567 | 021/296 | T2 DI SSQC-SNT YNEZ SW 21/296 RPR IBWW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-05 | 2021-04-01 | 2022-06-28 | 2022-04-01 | 2022-04-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069228 | T2 DI SSQC-SNT YNEZ SW 21/296 RPR STRW | ICW
LC | 120743865 | 050/204 | T2 EI DIABLO-GATES #1 050/204 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2021-04-05 | 2021-04-05 | 2022-06-28 | 2022-04-05 | 2022-04-05 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068473 | T2 EI DIABLO-GATES #1 050/204 RPR GYWS | ICS
LC | 120743919 | 006/043 | T2 DI KRCKHFF-CLVS-SNGR #1 6/43 RPL INSS | FRESNO | ETL.1890.INSL.CERA | 2021-04-05 | 2021-04-01 | 2022-05-25 | 2022-04-01 | 2022-04-01 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528484 | DI KERCKHOFF-CLVS-SNGR #1 RPLC INSS 22TW | 93K
LC | 120744396 | 049/427 | T2 EI PIT #1-COTTONWOOD 49/427 RMV NEST | TABLEMTN | ETL.5390.POLE.STPS | 2021-04-05 | 2021-04-05 | 2022-03-08 | 2022-04-05 | 2022-04-05 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Structure-Steel | Remove | 45182625 | T2 EI PIT #1-COTTONWOOD 49/427 RMV NEST | ICS
LC | 120744501 | 023/006 | T2 EI GRBERVILE-LYTNVILLE 23/6 RPR SPLW | WILLITS | ETL.8365.INSL.NCER | 2021-04-05 | 2021-04-05 | 2022-04-13 | 2022-04-05 | 2022-04-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Damper-Wood | Replace | 44754981 | T2 EI GRBERVILE-LYTNVILLE 23/6 RPR SPLW | ICW
LC | 120744540 | 003/036C | T2 EI CRAG VIEW-CASCADE 3/036C RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-05 | 2021-04-05 | 2021-06-16 | 2022-04-05 | 2022-04-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859913 | T2 EI CRAG VIEW-CASCADE 3/036C RPR GYWW | ICW
LC | 120744549 | 003/036B | T2 EI CRAG VIEW-CASCADE 3/036B RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-05 | 2021-04-05 | 2021-06-16 | 2022-04-05 | 2022-04-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859912 | T2 EI CRAG VIEW-CASCADE 3/036B RPR GYWW | ICW
LC | 120744607 | 003/036A | T2 EI CRAG VIEW-CASCADE 3/036A RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-05 | 2021-04-05 | 2021-06-16 | 2022-04-05 | 2022-04-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859911 | T2 EI CRAG VIEW-CASCADE 3/036A RPR GYWW | ICW
LC | 120745558 | 019/265 | T2 DI SSQC-SNT YNZ SW 19/265 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-05 | 2021-04-01 | 2022-03-02 | 2022-04-01 | 2022-04-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069229 | T2 DI SSQC-SNT YNZ SW 19/265 RPR STRW | ICW
LC | 120745841 | :010/004 | T2 DI BLLT-RVRBNK-MLNES :10/4 RPL INSW | VICTOR | ETL.1070.INSL.NCER | 2021-04-05 | 2021-03-25 | 2022-05-03 | 2022-03-25 | 2022-03-25 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535289 | T2 EI BLT-RVBK-MLS SWSTA :2/9 INST INSLW | 93I
LC | 120745901 | 007/117 | T2 EI PIT #1HT CRK #2-BNY 7/117 PL BUTT | TABLEMTN | ETL.7040.POLE.WOOD | 2021-04-05 | 2021-04-05 | 2022-05-21 | 2022-04-05 | 2022-04-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45213850 | T2 EI PIT #1HT CRK #2-BNY 7/117 PL BUTT | ICW
LC | 120746124 | 046/287 | T2 DI MADISON-VACA 046/287 RPR STRT | SACTO | ETL.2170.TOWR | 2021-04-05 | 2021-03-26 | 2022-02-04 | 2022-03-26 | 2022-03-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 44737827 | T2 DI MADISON-VACA 046/287 RPR STRT | ICQ
LC | 120746125 | 046/287 | T2 DI MADISON-VACA 046/287 INS HRDT | SACTO | ETL.2170.TOWR | 2021-04-05 | 2021-03-26 | 2022-02-04 | 2022-03-26 | 2022-03-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 44737828 | T2 DI MADISON-VACA 046/287 INS HRDT | ICQ
LC | 120746286 | 007/063 | T2 DI PARADISE-TABLE MTN 7/063 RPR STRT | TABLEMTN | ETL.4316.TOWR | 2021-04-05 | 2021-03-29 | 2021-06-10 | 2022-03-29 | 2022-03-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Tower | Repair | 44861526 | T2 DI PARADISE-TABLE MTN 7/063 RPR STRT | ICQ
LC | 120747459 | 012/075 | T2 DI STNSLS-MANTECA #2 12/75 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-06 | 2021-04-05 | 2022-02-01 | 2022-04-05 | 2022-04-05 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2N PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45122325 | T2 DI STNSLS-MANTECA #2 12/75 RPR FOND | ICQ
LC | 120747611 | :012/079 | T2 DI GREEN VALLEY-LLAGAS :012/079 RPL I | MOSSLNDG | ETL.1720.INSL.CERA | 2021-04-06 | 2021-03-24 | 2022-10-23 | 2022-03-24 | 2022-03-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533800 | DI GREEN VALLEY-LLAGAS RPL INSS 1TWR | 93K
LC | 120747853 | 002/013 | T2 DI KRCKHFF-CLVS-SNGR #1 2/13 RPR STRT | FRESNO | ETL.1890.TOWR | 2021-04-06 | 2021-03-29 | 2022-02-08 | 2022-03-29 | 2022-03-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45068402 | T2 DI KRCKHFF-CLVS-SNGR #1 2/13 RPR STRT | ICQ
LC | 120747855 | 002/013 | T2 DI KRCKHFF-CLVS-SNGR #1 2/13 INS HRDT | FRESNO | ETL.1890.TOWR | 2021-04-06 | 2021-03-29 | 2022-02-08 | 2022-03-29 | 2022-03-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45068403 | T2 DI KRCKHFF-CLVS-SNGR #1 2/13 INS HRDT | ICQ
LC | 120747897 | 004/065 | T2 EI GREEN VALLEY-PAUL 04/065 RPL INSW | MOSSLNDG | ETL.1730.INSL.NCER | 2021-04-06 | 2021-04-06 | 2022-05-04 | 2022-04-06 | 2022-04-06 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535839 | T2 DI GRN VLEY-PAUL SWT 4/61 RPL INSW | 93I
LC | 120747903 | 003/035A | T2 EI CRG VIEW-CASCADE 003/035A RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-06 | 2021-04-06 | 2021-06-18 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859908 | T2 EI CRG VIEW-CASCADE 003/035A RPR GYWW | ICW
LC | 120747956 | 003/035C | T2 EI CRG VIEW-CASCADE 003/035C RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-06 | 2021-04-06 | 2021-06-16 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859910 | T2 EI CRG VIEW-CASCADE 003/035C RPR GYWW | ICW
LC | 120747960 | 003/035B | T2 EI CRG VIEW-CASCADE 003/035B RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-06 | 2021-04-06 | 2021-06-16 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859909 | T2 EI CRG VIEW-CASCADE 003/035B RPR GYWW | ICW
LC | 120748296 | 003/034A | T2 EI CRG VIEW-CASCADE 003/034A RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-06 | 2021-04-06 | 2021-06-16 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859902 | T2 EI CRG VIEW-CASCADE 003/034A RPR GYWW | ICW
LC | 120748300 | 003/034B | T2 EI CRG VIEW-CASCADE 003/034B RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-06 | 2021-04-06 | 2021-06-16 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859904 | T2 EI CRG VIEW-CASCADE 003/034B RPR GYWW | ICW
LC | 120748317 | 008/049 | T2 DI STANISLAUS-MNTC #2 8/49 RPR STRT | VICTOR | ETL.3820.TOWR | 2021-04-06 | 2021-04-06 | 2022-01-21 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45122114 | T2 DI STANISLAUS-MNTC #2 8/49 RPR STRT | ICQ
LC | 120748320 | 003/034C | T2 EI CRG VIEW-CASCADE 003/034C RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-06 | 2021-04-06 | 2021-06-16 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859906 | T2 EI CRG VIEW-CASCADE 003/034C RPR GYWW | ICW
LC | 120748513 | 024/003 | T2 EI GRBERVILE-LYTNVILLE 24/3 RMV VEG | WILLITS | ETL.8365.POLE.WOOD | 2021-04-06 | 2021-04-06 | 2022-03-15 | 2022-04-06 | 2022-04-06 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120748514 | 024/003 | T2 EI GRBERVILE-LYTNVILLE 24/3 RPR WDPKR | WILLITS | ETL.8365.POLE.WOOD | 2021-04-06 | 2021-04-06 | 2022-04-18 | 2022-04-06 | 2022-04-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44754983 | T2 EI GRBERVILE-LYTNVILLE 24/3 RPR WDPKR | ICW
LC | 120748702 | 005/016 | T2 EI SONOMA-PUEBLO 5/16 RPR STRW | LAKEVLLE | ETL.3810.POLE.WOOD | 2021-04-06 | 2021-04-05 | 2022-07-25 | 2022-04-05 | 2022-04-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45136695 | T2 EI SONOMA-PUEBLO 5/16 RPR STRW | ICW
LC | 120748782 | 004/064 | T2 EI GREEN VALLEY-PAUL 04/064 COMPLETE | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-04-06 | 2021-04-06 | 2022-05-14 | 2022-04-06 | 2022-04-06 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31535900 | T2 EI GREEN VALLEY-PAUL 04/064 REFRAME | 93E
LC | 120748792 | 034/151 | T2 EI MSS LNDNG-LS BNS 34/151 RPR STRT | MOSSLNDG | ETL.6040.TOWR | 2021-04-06 | 2021-04-06 | 2022-03-09 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45128054 | T2 EI MSS LNDNG-LS BNS 34/151 RPR STRT | ICQ
LC | 120748875 | 009/141 | T2 DI SC-ST YZ SW ST 9/141 RPR PL CMPLTD | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-06 | 2021-03-25 | 2022-04-11 | 2022-03-25 | 2022-03-25 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069230 | T2 DI SSQC-SNT YNZ SW STA 9/141 RPR STRW | ICW
LC | 120748938 | 003/033B | T2 EI CRG VIEW-CASCADE 003/033B RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-06 | 2021-04-06 | 2021-06-16 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859899 | T2 EI CRG VIEW-CASCADE 003/033B RPR GYWW | ICW
LC | 120748942 | 003/033A | T2 EI CRG VIEW-CASCADE 003/033A RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-06 | 2021-04-06 | 2021-06-16 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859897 | T2 EI CRG VIEW-CASCADE 003/033A RPR GYWW | ICW
LC | 120748944 | 026/001 | T2 EI GRBRVILE-LYTNVILLE 26/1 RMV VEG | EUREKA | ETL.8365.POLE.WOOD | 2021-04-06 | 2021-04-06 | 2022-05-03 | 2022-04-06 | 2022-04-06 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120748993 | 003/033C | T2 EI CRG VIEW-CASCADE 003/033C RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-06 | 2021-04-06 | 2021-06-18 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859901 | T2 EI CRG VIEW-CASCADE 003/033C RPR GYWW | ICW
LC | 120749055 | 029/255 | T2 EI RND MTN-CTNWD 29/255 RPL INSS | TABLEMTN | ETL.5640.INSL | 2021-04-06 | 2021-04-06 | 2022-07-29 | 2022-04-06 | 2022-04-06 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535739 | T2 EI RND MTN-CTNWD RPL INSS 11TWRS | 93K
LC | 120749113 | :017/091 | T2 EI CRZY HRSE CNY-SLN :17/91 RPR FOND | MOSSLNDG | ETL.2900.TOWR | 2021-04-06 | 2021-04-06 | 2021-07-08 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44839311 | T2 EI CRZY HRSE CNY-SLN :17/91 RPR FOND | ICQ
LC | 120749121 | 006/097 | T2 EI PIT #1HT CRK #2-BRNY 6/97 RPL INSW | TABLEMTN | ETL.7040.INSL.CERA | 2021-04-06 | 2021-04-06 | 2022-07-20 | 2022-04-06 | 2022-04-06 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535979 | T2 EI PIT #1HT CRK #2-BRNY 6/97 RPL INSW | 93I
LC | 120749265 | 004/005 | T2 EI SNMA-PUEBLO 4/5 RPR GYWW | LAKEVLLE | ETL.3810.POLE.WOOD | 2021-04-06 | 2021-04-06 | 2021-07-27 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44806035 | T2 EI SNMA-PUEBLO 4/5 RPR GYWW | ICW
LC | 120749266 | 023/009 | T2 EI GRBRVILE-LAYTONVILLE 23/9 RPR GYWW | WILLITS | ETL.8365.POLE.WOOD | 2021-04-06 | 2021-04-06 | 2022-04-13 | 2022-04-06 | 2022-04-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44754984 | T2 EI GRBRVILE-LAYTONVILLE 23/9 RPR GYWW | ICW
LC | 120749329 | 011/097 | T2 DI EL DRD-MSSR FLT #1 11/97 RMV HRDS | SACTO | ETL.1530.TOWR | 2021-04-06 | 2021-03-25 | 2022-06-23 | 2022-03-25 | 2022-03-25 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 44738005 | T2 DI EL DRD-MSSR FLT #1 11/97 RMV HRDS | ICS
LC | 120749362 | 011/097 | T2 DI EL DRD-MSSR FLT #1 11/97 RMV NEST | SACTO | ETL.1530.TOWR | 2021-04-06 | 2021-03-25 | 2022-06-23 | 2022-03-25 | 2022-03-25 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44738004 | T2 DI EL DRD-MSSR FLT #1 11/97 RMV NEST | ICS
LC | 120749406 | 003/032 | T2 EI CRAG VIEW-CASCADE 3/32 REGRADE | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-06 | 2021-04-06 | 2021-07-22 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Structure-Wood | Remove | 44859895 | T2 EI CRAG VIEW-CASCADE 3/32 REGRADE | ICW
LC | 120749711 | 004/063 | T2 EI GRN VALLEY-PAUL SWT 4/63 RMV VEG | MOSSLNDG | ETL.1730.POLE.WOOD | 2021-04-06 | 2021-04-06 | 2021-11-12 | 2022-04-06 | 2022-04-06 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Trim
LC | 120749748 | 047/415 | T2 EI RND MT-CTTNWD#3 47/415 INST BOLT | TABLEMTN | ETL.5650.TOWR | 2021-04-06 | 2021-04-06 | 2022-02-24 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Missing | Hardware-Tower | Install | 45110991 | T2 EI RND MT-CTTNWD#3 47/415 INST BOLT | ICQ
LC | 120749876 | 015/089 | T2 DI STANISLAUS-MNTC #2 15/89 RPL INSS | VICTOR | ETL.3820.INSL.CERA | 2021-04-06 | 2021-03-26 | 2021-12-09 | 2022-03-26 | 2022-03-26 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528964 | EI STANISLAUS-MANTECA#2 RPLC INSS 12TWR | 93K
LC | 120749877 | 015/089 | T2 DI STANISLAUS-MNTC #2 15/89 RPR STRT | VICTOR | ETL.3820.TOWR | 2021-04-06 | 2021-03-26 | 2022-02-04 | 2022-03-26 | 2022-03-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45123050 | T2 DI STANISLAUS-MNTC #2 15/89 RPR STRT | ICQ
LC | 120750153 | 026/194 | T2 EI DRUM-RIO OSO #1 26/194 INS ACG | SACTO | ETL.1420.TOWR | 2021-04-06 | 2021-04-06 | 2022-01-18 | 2022-04-06 | 2022-04-06 | On-time | 988 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Anti-Climbing Guard | Structure-Tower | Install | 31518757 | NN DRUM-RIO OSO #1 INST ATCG 8TWRS | 93A
LC | 120750206 | 003/031A | T2 EI CRG VIEW-CASCADE 003/031A REGRADE | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-06 | 2021-04-06 | 2021-07-23 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Structure-Wood | Remove | 44859883 | T2 EI CRG VIEW-CASCADE 003/031A REGRADE | ICW
LC | 120750207 | 003/031A | T2 EI CRG VIEW-CASCADE 003/031A RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-06 | 2021-04-06 | 2021-06-16 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859885 | T2 EI CRG VIEW-CASCADE 003/031A RPR GYWW | ICW
LC | 120750216 | 027/004 | T2 EI GRBRVILE-LYTNVILLE 27/4 RPR GYWW | WILLITS | ETL.8365.POLE.WOOD | 2021-04-06 | 2021-04-06 | 2022-04-19 | 2022-04-06 | 2022-04-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44754985 | T2 EI GRBRVILE-LYTNVILLE 27/4 RPR GYWW | ICW
LC | 120750241 | 003/024 | T2 DI STNLS-MLNS SS-MTC #1 3/24 INS HRDT | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-04-06 | 2022-01-18 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45119710 | T2 DI STNLS-MLNS SS-MTC #1 3/24 INS HRDT | ICQ
LC | 120750243 | 003/024 | T2 DI STNLS-MLNS SS-MTC #1 3/24 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-04-06 | 2022-01-18 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45119711 | T2 DI STNLS-MLNS SS-MTC #1 3/24 RPR FOND | ICQ
LC | 120750275 | 003/031B | T2 EI CRG VIEW-CASCADE 003/031B RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-06 | 2021-04-06 | 2021-06-16 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859886 | T2 EI CRG VIEW-CASCADE 003/031B RPR GYWW | ICW
LC | 120750276 | 003/031B | T2 EI CRG VIEW-CASCADE 003/031B REGRADE | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-06 | 2021-04-06 | 2021-07-23 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Structure-Wood | Remove | 44859888 | T2 EI CRG VIEW-CASCADE 003/031B REGRADE | ICW
LC | 120750277 | 003/031C | T2 EI CRG VIEW-CASCADE 003/031C REGRADE | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-06 | 2021-04-06 | 2021-07-23 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Structure-Wood | Remove | 44859890 | T2 EI CRG VIEW-CASCADE 003/031C REGRADE | ICW
LC | 120750278 | 003/031C | T2 EI CRG VIEW-CASCADE 003/031C RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-04-06 | 2021-04-06 | 2021-06-16 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859893 | T2 EI CRG VIEW-CASCADE 003/031C RPR GYWW | ICW
LC | 120750320 | 007/047 | T2 DI STNLS-MLNS SS-MTC #1 7/47 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-04-06 | 2022-01-21 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45122112 | T2 DI STNLS-MLNS SS-MTC #1 7/47 RPR FOND | ICQ
LC | 120750480 | 003/019 | T2 DI STNISLAUS-MANTECA #2 3/19 RPR STRT | VICTOR | ETL.3820.TOWR | 2021-04-06 | 2021-04-06 | 2022-01-13 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45119706 | T2 DI STNISLAUS-MANTECA #2 3/19 RPR STRT | ICQ
LC | 120750529 | 000/005 | T2 DI STNSLS-MLNS-MNTC 0/5 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-04-06 | 2022-01-10 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45119054 | T2 DI STNSLS-MLNS-MNTC 0/5 RPR FOND | ICQ
LC | 120750551 | 003/019 | T2 DI SN ML SW ST-RK JT 3/19 RPL DAMS | VICTOR | ETL.3840.INSL.CERA | 2021-04-06 | 2021-04-06 | 2022-05-11 | 2022-04-06 | 2022-04-06 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 45122069 | T2 DI SN ML SW ST-RK JT 3/19 RPL DAMS | ICS
LC | 120750666 | 027/001 | T2 EI GARBERVLE-LAYTONVLE 27/1 RPR POLE | WILLITS | ETL.8365.POLE.WOOD | 2021-04-06 | 2021-04-06 | 2022-04-19 | 2022-04-06 | 2022-04-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44754986 | T2 EI GARBERVLE-LAYTONVLE 27/1 RPR POLE | ICW
LC | 120750927 | 003/029 | T2 EI CRAG VIEW-CASCADE 003/29L RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-06 | 2021-04-06 | 2021-07-20 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859839 | T2 EI DELTA-COTTONWODD 003/29L RPR GYWW | ICW
LC | 120750936 | 005/034 | T2 DI KRCKHFF-CLVS-SNGR #1 5/34 INS HRDT | FRESNO | ETL.1890.TOWR | 2021-04-06 | 2021-04-01 | 2022-02-16 | 2022-04-01 | 2022-04-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45068404 | T2 DI KRCKHFF-CLVS-SNGR #1 5/34 INS HRDT | ICQ
LC | 120750940 | 011/099 | T2 DI EL DRD-MSSR FLT #1 11/99 RPL STEP | SACTO | ETL.1530.POLE.NWOD | 2021-04-06 | 2021-03-24 | 2022-06-22 | 2022-03-24 | 2022-03-24 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 44752946 | T2 DI EL DRD-MSSR FLT #1 11/99 RPL STEP | ICS
LC | 120750962 | 003/029 | T2 EI CRAG VIEW-CASCADE 003/29C RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-06 | 2021-04-06 | 2021-07-20 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859882 | T2 EI CRAG VIEW-CASCADE 003/29C RPR GYWW | ICW
LC | 120750974 | 003/029 | T2 EI CRAG VIEW-CASCADE 003/29R RPR ANCW | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-06 | 2021-04-06 | 2021-07-27 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 44938538 | T2 EI CRAG VIEW-CASCADE 003/29R RPR ANCW | ICW
LC | 120751410 | 003/028 | T2 EI CRAG VIEW-CASCADE 3/28 RPR ANCW | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-06 | 2021-04-06 | 2021-06-16 | 2022-04-06 | 2022-04-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Steel | Repair | 44859823 | T2 EI DELTA-COTTONWOOD 3/28 RPR ANCW | ICS
LC | 120751643 | 019/112 | T2 DI STNSLS-MANTCA #2 19/112 RPL HRDS | VICTOR | ETL.3820.INSL.NCER | 2021-04-06 | 2021-04-06 | 2021-05-20 | 2022-04-06 | 2022-04-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Steel | Replace | 44752163 | T2 DI STNSLS-MANTCA #2 19/112 RPL HRDS | ICS
LC | 120751743 | 016/105 | T2 EI METCALF-GRN VLLY 16/105L RPL STRW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-04-06 | 2021-04-06 | 2021-08-25 | 2022-04-06 | 2022-04-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535894 | T2 EI METCALF-GRN VLLY 16/105L RPL STRW | 70Y
LC | 120751744 | 016/105 | T2 EI METCALF-GRN VLLY 16/105R RPL STRW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-04-06 | 2021-04-06 | 2021-08-25 | 2022-04-06 | 2022-04-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535894 | T2 EI METCALF-GRN VLLY 16/105L RPL STRW | 70Y
LC | 120751775 | 013/076 | T2 DI STSLS-MLS SS-MTC #1 13/76 RPR STRT | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-04-06 | 2022-02-01 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45122328 | T2 DI STSLS-MLS SS-MTC #1 13/76 RPR STRT | ICQ
LC | 120751840 | 006/151 | T2 EI DEL MONTE-VIEJO 006/151 RPR FENCE | MOSSLNDG | ETL.6710.POLE.WOOD | 2021-04-06 | 2021-04-02 | 2022-01-21 | 2022-04-02 | 2022-04-02 | On-time | 932 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Fence / Gate | Repair | 45067001 | T2 EI DEL MONTE-VIEJO 006/151 RPR FENCE | CHS
LC | 120751899 | 003/018 | T2 DI STN ML SW ST-RBK JT 3/18 RPR SPLS | VICTOR | ETL.3840.INSL.CERA | 2021-04-06 | 2021-04-06 | 2022-05-11 | 2022-04-06 | 2022-04-06 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122070 | T2 DI STN ML SW ST-RBK JT 3/18 RPR SPLS | ICS
LC | 120751942 | 018/378 | T2 EI CRBOU-WSTWD 18/378 RPL DAMW | TABLEMTN | ETL.6300.INSL | 2021-04-06 | 2021-04-06 | 2021-07-14 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Damper-Wood | Replace | 44915726 | T2 EI CRBOU-WSTWD 18/378 RPL DAMW | ICW
LC | 120751971 | 003/018 | T2 DI STNSLS-MANTCA #2 3/18 INS HRDT | VICTOR | ETL.3820.TOWR | 2021-04-06 | 2021-04-06 | 2022-01-13 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45119705 | T2 DI STNSLS-MANTCA #2 3/18 INS HRDT | ICQ
LC | 120752085 | 007/044 | T2 DI STSLS-MLS SS-MTC #1 7/44 INS HRDT | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-04-06 | 2022-01-20 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45122105 | T2 DI STSLS-MLS SS-MTC #1 7/44 INS HRDT | ICQ
LC | 120752087 | 008/048 | T2 DI STNISLS-MLNS SW ST-R 8/48 RPR SPLS | VICTOR | ETL.3840.INSL.NCER | 2021-04-06 | 2021-04-06 | 2022-05-12 | 2022-04-06 | 2022-04-06 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122071 | T2 DI STNISLS-MLNS SW ST-R 8/48 RPR SPLS | ICS
LC | 120752134 | 000/004 | T2 DI STSLS-MLS SS-MTC #1 0/4 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-04-06 | 2022-01-10 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45119053 | T2 DI STSLS-MLS SS-MTC #1 0/4 RPR FOND | ICQ
LC | 120752714 | :010/000 | T2 DI BELLOTA-RBK-MLS :010/000 RPL INSW | VICTOR | ETL.1070.INSL.NCER | 2021-04-06 | 2021-03-25 | 2022-05-04 | 2022-03-25 | 2022-03-25 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535289 | T2 EI BLT-RVBK-MLS SWSTA :2/9 INST INSLW | 93I
LC | 120752821 | 020/116 | T2 DI STANISLAUS-MNTC #2 20/116 RPR SPLS | VICTOR | ETL.3820.INSL.CERA | 2021-04-06 | 2021-04-06 | 2021-12-08 | 2022-04-06 | 2022-04-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 44977944 | T2 DI STANISLAUS-MNTC #2 20/116 RPR SPLS | ICS
LC | 120752942 | 009/058 | T2 DI STN ML SW STA-RVRBK 9/58 RPR SPLS | VICTOR | ETL.3840.INSL.NCER | 2021-04-06 | 2021-04-06 | 2022-05-12 | 2022-04-06 | 2022-04-06 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122072 | T2 DI STN ML SW STA-RVRBK 9/58 RPR SPLS | ICS
LC | 120752968 | 009/058 | T2 DI STANISLAUS-MANTC #2 9/58 RPLC HRDT | VICTOR | ETL.3820.TOWR | 2021-04-06 | 2021-04-06 | 2022-01-31 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45122272 | T2 DI STANISLAUS-MANTC #2 9/58 RPLC HRDT | ICQ
LC | 120753035 | 015/094 | T2 DI STNSLS-MLNS-MNTC 15/94 RMV VEGN | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-03-26 | 2021-12-16 | 2022-03-26 | 2022-03-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 120754513 | 023/137 | T2 DI STNSLS-MANTCA #2 23/137 UNBURY | VICTOR | ETL.3820.TOWR | 2021-04-07 | 2021-04-06 | 2022-02-11 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123130 | T2 DI STNSLS-MANTCA #2 23/137 UNBURY | ICQ
LC | 120754518 | 023/137 | T2 DI STN ML SW ST-RK JT 23/137 RPR SPLS | VICTOR | ETL.3840.INSL.CERA | 2021-04-07 | 2021-04-06 | 2022-04-22 | 2022-04-06 | 2022-04-06 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122073 | T2 DI STN ML SW ST-RK JT 23/137 RPR SPLS | ICS
LC | 120754598 | 026/163 | T2 DI TSL-SALDO-MANTECA 026/163 RPL HRDD | VICTOR | ETL.4000.POLE.WOOD | 2021-04-07 | 2021-04-06 | 2021-10-12 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44977842 | T2 DI TSL-SALDO-MANTECA 026/163 RPL HRDD | ICW
LC | 120754658 | 004/025 | T2 DI STSLS-MLS SS-MTC #1 4/25 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-07 | 2021-04-06 | 2022-01-18 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45119713 | T2 DI STSLS-MLS SS-MTC #1 4/25 RPR FOND | ICQ
LC | 120754715 | 005/032 | T2 DI KERCKHFF-CLVS-SGR #1 5/32 RPR STRT | FRESNO | ETL.1890.TOWR | 2021-04-07 | 2021-03-29 | 2022-02-16 | 2022-03-29 | 2022-03-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45068405 | T2 DI KERCKHFF-CLVS-SGR #1 5/32 RPR STRT | ICQ
LC | 120754769 | 051/365 | T2 DI CARIBOU-TABLE MTN 51/365 RPR INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-04-07 | 2021-04-01 | 2022-06-11 | 2022-04-01 | 2022-04-01 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45212342 | T2 DI CARIBOU-TABLE MTN 51/365 RPR INSS | ICS
LC | 120755193 | 002/027 | T2 EI CRAG VIEW-CASCADE 2/27L RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-07 | 2021-04-07 | 2021-07-27 | 2022-04-07 | 2022-04-07 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31516883 | T2 CRAG VIEW-CASCADE 17/151A RPL POLE | 70Y
LC | 120755195 | 002/027 | T2 EI CRAG VIEW-CASCADE 2/27R RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-07 | 2021-04-07 | 2021-07-27 | 2022-04-07 | 2022-04-07 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31516883 | T2 CRAG VIEW-CASCADE 17/151A RPL POLE | 70Y
LC | 120755242 | 009/117 | T2 EI WST PINT-VLY SPRNGS 9/117 RPR GYWW | VICTOR | ETL.8350.POLE.WOOD | 2021-04-07 | 2021-04-07 | 2022-03-05 | 2022-04-07 | 2022-04-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45151575 | T2 EI WST PINT-VLY SPRNGS 9/117 RPR GYWW | ICW
LC | 120755274 | 000/003 | T2 EI CHRST-WLLW PSS 0/3 RPR GYWW | CONCORD | ETL.6370.POLE.WOOD | 2021-04-07 | 2021-04-07 | 2021-10-13 | 2022-04-07 | 2022-04-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44959018 | T2 EI CHRST-WLLW PSS 0/3 RPR GYWW | ICW
LC | 120755291 | 027/005 | T2 EI GRBRVILE-LYTNVILLE 27/5 RPR GYWW | WILLITS | ETL.8365.POLE.WOOD | 2021-04-07 | 2021-04-07 | 2022-04-21 | 2022-04-07 | 2022-04-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44754987 | T2 EI GRBRVILE-LYTNVILLE 27/5 RPR GYWW | ICW
LC | 120755298 | 018/256 | T2 DI SISQUOC-SANTA YNEZ 18/256 RPL STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-07 | 2021-04-01 | 2022-06-28 | 2022-04-01 | 2022-04-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600874 | T2 DI SISQUOC-SANTA YNEZ 18/256 RPL STRW | 70Y
LC | 120755494 | 002/026 | T2 EI CRAG VIEW-CASCADE 2/26L RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-07 | 2021-04-07 | 2021-07-27 | 2022-04-07 | 2022-04-07 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31516883 | T2 CRAG VIEW-CASCADE 17/151A RPL POLE | 70Y
LC | 120755917 | 008/050 | T2 DI STNSLS-MLNS-MNTC 8/50 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-07 | 2021-04-06 | 2022-01-21 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45122115 | T2 DI STNSLS-MLNS-MNTC 8/50 RPR FOND | ICQ
LC | 120755978 | 008/050 | T2 DI STNSLS-MLNS-MNTC 8/50 INS HRDT | VICTOR | ETL.3830.TOWR | 2021-04-07 | 2021-04-06 | 2022-01-21 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45122116 | T2 DI STNSLS-MLNS-MNTC 8/50 INS HRDT | ICQ
LC | 120756400 | 028/000 | T2 EI GRBRVILE-LYTNVILLE 28/0 RPL DAMP | WILLITS | ETL.8365.INSL.NCER | 2021-04-07 | 2021-04-07 | 2022-04-21 | 2022-04-07 | 2022-04-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Damper-Wood | Replace | 44754988 | T2 EI GRBRVILE-LYTNVILLE 28/0 RPL DAMP | ICW
LC | 120756409 | 011/056 | T2 EI MSS LNDG-MTCLF 11/56 RMV VEG | MOSSLNDG | ETL.6050.TOWR | 2021-04-07 | 2021-04-07 | 2021-09-23 | 2022-04-07 | 2022-04-07 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120756536 | 093/474 | T2 EI MLN-RND MTN 93/474 RPR STRT | TABLEMTN | ETL.6020.TOWR | 2021-04-07 | 2021-04-07 | 2022-07-14 | 2022-04-07 | 2022-04-07 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45198277 | T2 EI MLN-RND MTN 93/474 RPR STRT | ICQ
LC | 120756560 | 002/023 | T2 EI CRAG VIEW-CASCADE 2/23L RPR STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-07 | 2021-04-07 | 2021-06-16 | 2022-04-07 | 2022-04-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44859821 | T2 EI CRAG VIEW-CASCADE 2/23L RPR STRW | ICW
LC | 120756561 | 004/061 | T2 DI GRN VLEY-PAUL SWT 4/61 RPL INSW | MOSSLNDG | ETL.1730.INSL.NCER | 2021-04-07 | 2021-03-30 | 2022-05-03 | 2022-03-30 | 2022-03-30 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535839 | T2 DI GRN VLEY-PAUL SWT 4/61 RPL INSW | 93I
LC | 120756617 | 005/023 | T2 EI MRRO BY-SLR SS #2 5/23 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-07 | 2021-04-07 | 2022-07-15 | 2022-04-07 | 2022-04-07 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31550475 | EI MORRO BAY-SOLAR SS #2 RPL INSS 5TWRS | 93K
LC | 120756916 | 006/025 | T2 EI MRRO BY-SLR SS #2 6/25 RPL DAMS | PISMOBCH | ETL.5310.INSL | 2021-04-07 | 2021-04-07 | 2022-07-16 | 2022-04-07 | 2022-04-07 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 44963095 | T2 EI MRRO BY-SLR SS #2 6/25 RPL DAMS | ICS
LC | 120756917 | 006/025 | T2 EI MRO BY-SLR SW STA #2 6/25 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-07 | 2021-04-07 | 2022-07-16 | 2022-04-07 | 2022-04-07 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31550475 | EI MORRO BAY-SOLAR SS #2 RPL INSS 5TWRS | 93K
LC | 120756918 | 006/025 | T2 EI MRO BY-SLR SW STA #1 6/25 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-07 | 2021-04-07 | 2022-06-14 | 2022-04-07 | 2022-04-07 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528621 | EI MORRO BAY-SOLAR SS #1 RPLC INNS 18TW | 93K
LC | 120756920 | :010/006 | T2 DI BLT-RVRBNK-MLNS :10/6 RPR STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-04-07 | 2021-03-26 | 2022-05-03 | 2022-03-26 | 2022-03-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45151600 | T2 DI BLT-RVRBNK-MLNS :10/6 RPR STRW | ICW
LC | 120756961 | 007/082 | T2 DI GRN VALLEY-PAUL SWT 7/82 RPL INSW | MOSSLNDG | ETL.1730.INSL.NCER | 2021-04-07 | 2021-03-30 | 2022-08-23 | 2022-03-30 | 2022-03-30 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535459 | T2 EI GRN VLLY-PAUL SWT-WD 6/72 RPL INSW | 93I
LC | 120756966 | 007/082 | T2 DI GRN VALLEY-PAUL SWT 7/82 RPR STRW | MOSSLNDG | ETL.1730.POLE.WOOD | 2021-04-07 | 2021-03-30 | 2022-08-23 | 2022-03-30 | 2022-03-30 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45213422 | T2 DI GRN VALLEY-PAUL SWT 7/82 RPR STRW | ICW
LC | 120757026 | :011/001 | T2 DI BELLOTA-RVRBNK-MLNS :11/1 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-04-07 | 2021-03-25 | 2022-05-05 | 2022-03-25 | 2022-03-25 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535291 | T2 DI BLLT-RVRBK-MLS SWST :10/8 RPL STRW | 70Y
LC | 120757113 | 009/140 | T2 DI SSQC-SNT YNEZ SW ST 9/140 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-07 | 2021-03-25 | 2022-01-13 | 2022-03-25 | 2022-03-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069233 | T2 DI SSQC-SNT YNEZ SW ST 9/140 RPR STRW | ICW
LC | 120757263 | 005/024 | T2 EI MRO BY-SLR SW STA #1 5/24 RPR FOND | PISMOBCH | ETL.5300.TOWR | 2021-04-07 | 2021-04-07 | 2022-06-27 | 2022-04-07 | 2022-04-07 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44765117 | T2 EI MRO BY-SLR SW STA #1 5/24 RPR FOND | ICQ
LC | 120757446 | 002/022 | T2 EI CRAG VIEW-CASCADE 2/22L RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-07 | 2021-04-07 | 2021-06-15 | 2022-04-07 | 2022-04-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859797 | T2 EI CRAG VIEW-CASCADE 2/22L RPR GYWW | ICW
LC | 120757497 | 001/011 | T2 EI CHRSTIE-WLLW PSS 001/011 INS ANMW | CONCORD | ETL.6370.POLE.WOOD | 2021-04-07 | 2021-04-07 | 2021-10-14 | 2022-04-07 | 2022-04-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Missing | Animal Guard-Wood | Install | 44959010 | T2 EI CHRSTIE-WLLW PSS 001/011 INS ANMW | ICW
LC | 120757550 | 002/022 | T2 EI CRAG VIEW-CASCADE 2/022C RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-07 | 2021-04-07 | 2021-06-15 | 2022-04-07 | 2022-04-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859798 | T2 EI CRAG VIEW-CASCADE 2/022C RPR GYWW | ICW
LC | 120757552 | 002/022 | T2 EI CRAG VIEW-CASCADE 2/22R RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-07 | 2021-04-07 | 2021-06-15 | 2022-04-07 | 2022-04-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859799 | T2 EI CRAG VIEW-CASCADE 2/22R RPR GYWW | ICW
LC | 120757565 | 015/224 | T2 DI SSQC-SANTA YNEZ 15/224 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-07 | 2021-03-22 | 2022-03-02 | 2022-03-22 | 2022-03-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069234 | T2 DI SSQC-SANTA YNEZ 15/224 RPR STRW | ICW
LC | 120757997 | 010/125 | T2 EI WST P-VLY SPGS 10/125 RMV ANC | VICTOR | ETL.8350.POLE.NWOD | 2021-04-07 | 2021-04-07 | 2022-05-10 | 2022-04-07 | 2022-04-07 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45151601 | T2 EI WST P-VLY SPGS 10/125 RMV NEST/ANC | ICS
LC | 120758066 | 028/002 | T2 EI GRBRVILE-LAYTNVILLE 28/2 RPR DAMP | WILLITS | ETL.8365.INSL.NCER | 2021-04-07 | 2021-04-07 | 2022-04-21 | 2022-04-07 | 2022-04-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Damper-Wood | Replace | 44754989 | T2 EI GRBRVILE-LAYTNVILLE 28/2 RPR DAMP | ICW
LC | 120758522 | 002/020 | T2 EI CRAG VIEW-CASCADE 2/20L VEG COA | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-07 | 2021-04-07 | 2022-08-29 | 2022-04-07 | 2022-04-07 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO SR22 | Overgrown | Vegetation | Trim
LC | 120758523 | 002/020 | T2 EI CRAG VIEW-CASCADE 2/20L RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-07 | 2021-04-07 | 2021-06-15 | 2022-04-07 | 2022-04-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859794 | T2 EI CRAG VIEW-CASCADE 2/20L RPR GYWW | ICW
LC | 120758524 | 007/029 | T2 EI MORRO BAY-SOLAR SS#1 7/29 REPL INS | PISMOBCH | ETL.5300.TOWR | 2021-04-07 | 2021-04-07 | 2022-06-14 | 2022-04-07 | 2022-04-07 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31529344 | T3 EI MRRO BY-SLR SWST#1 RPL INS 21TWR | 93K
LC | 120758526 | 007/029 | T2 EI MORRO BAY-SLR SS #2 7/29 REPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-07 | 2021-04-07 | 2022-07-16 | 2022-04-07 | 2022-04-07 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528622 | EI MORRO BAY-SOLAR SS#2 RPL INS 8WR | 93K
LC | 120758542 | 002/020 | T2 EI CRAG VIEW-CASCADE 2/20M RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-07 | 2021-04-07 | 2021-06-15 | 2022-04-07 | 2022-04-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859795 | T2 EI CRAG VIEW-CASCADE 2/20M RPR GYWW | ICW
LC | 120758612 | 002/020 | T2 EI CRAG VIEW-CASCADE 2/20R RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-07 | 2021-04-07 | 2021-06-17 | 2022-04-07 | 2022-04-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859796 | T2 EI CRAG VIEW-CASCADE 2/20R RPR GYWW | ICW
LC | 120758769 | 007/030 | T2 EI MORRO BAY-SOLAR SS#2 7/30 REPL INS | PISMOBCH | ETL.5310.INSL | 2021-04-07 | 2021-04-07 | 2022-07-16 | 2022-04-07 | 2022-04-07 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528622 | EI MORRO BAY-SOLAR SS#2 RPL INS 8WR | 93K
LC | 120759292 | 004/010 | T2 EI VLY SPRNGS-CLVRS 4/10 RPLC STRW | VICTOR | ETL.8220.POLE.WOOD | 2021-04-07 | 2021-04-07 | 2022-04-02 | 2022-04-07 | 2022-04-07 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543645 | T2 WV VLLEY SPRNGS-CLVRS CMNT 1/4 RPL PL | 70Y
LC | 120759492 | 013/065 | T2 EI MSS LNDNG-CBRN 013/065 REM VEG | MOSSLNDG | ETL.5330.TOWR | 2021-04-07 | 2021-04-07 | 2021-11-23 | 2022-04-07 | 2022-04-07 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120759493 | 001/017 | T2 EI CRAG VIEW-CASCADE 1/17R RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-07 | 2021-04-07 | 2021-06-16 | 2022-04-07 | 2022-04-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859793 | T2 EI CRAG VIEW-CASCADE 1/17R RPR GYWW | ICW
LC | 120759524 | 008/093 | T2 EI WST PNT-VLY SPNGS 8/93 REPL POLE | VICTOR | ETL.8350.POLE.WOOD | 2021-04-07 | 2021-04-07 | 2022-05-23 | 2022-04-07 | 2022-04-07 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535643 | T2 EI WST PNT-VLY SPNGS 8/93 REPL POLE | 70Y
LC | 120759607 | 013/064 | T2 EI MOSS LANDING-CBRN 13/64 COMPLETE | MOSSLNDG | ETL.5330.TOWR | 2021-04-07 | 2021-04-07 | 2022-05-17 | 2022-04-07 | 2022-04-07 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44739593 | T2 EI MOSS LANDING-CBRN 13/64 RPR FOND | ICQ
LC | 120759619 | 008/095 | T2 EI WST PNT-VLY SPRNGS 8/95 RMV VEG | VICTOR | ETL.8350.POLE.WOOD | 2021-04-07 | 2021-04-07 | 2022-04-13 | 2022-04-07 | 2022-04-07 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120759762 | 001/008 | T2 DI STNSLS-MLNS-MNTC#1 1/8 RPR STRT | VICTOR | ETL.3830.TOWR | 2021-04-07 | 2021-04-06 | 2022-01-11 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45119057 | T2 DI STNSLS-MLNS-MNTC#1 1/8 RPR STRT | ICQ
LC | 120759918 | 013/063 | T2 EI MS LNG-LS GLS SW ST 13/63 RPL INSS | MOSSLNDG | ETL.5340.INSL | 2021-04-07 | 2021-04-07 | 2022-04-12 | 2022-04-07 | 2022-04-07 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31539341 | T2 EI MSS LNDG-LS AGLS SW RPL INSS 6TWR | 93K
LC | 120759919 | 013/063 | T2 EI MSS LNDING-CBRN 013/063 REM VEG | MOSSLNDG | ETL.5330.TOWR | 2021-04-07 | 2021-04-07 | 2021-11-23 | 2022-04-07 | 2022-04-07 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120760005 | 016/214 | T2 EI WST PINT-VLY SPRNG 16/214 RPR GYWW | VICTOR | ETL.8350.POLE.NWOD | 2021-04-07 | 2021-04-06 | 2022-05-10 | 2022-04-06 | 2022-04-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45151603 | T2 EI WST PINT-VLY SPRING 16/21 RPR GYWW | ICW
LC | 120760006 | 015/197 | T2 EI WST PINT-VLY SPRING 15/19 RMV STEP | VICTOR | ETL.8350.POLE.NWOD | 2021-04-07 | 2021-04-07 | 2022-05-27 | 2022-04-07 | 2022-04-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45151604 | T2 EI WST PINT-VLY SPRING 15/19 RMV STEP | ICW
LC | 120760008 | 014/181 | T2 EI WST PNT-VLY SPRNGS 14/181 RPR GYWW | VICTOR | ETL.8350.POLE.NWOD | 2021-04-07 | 2021-04-07 | 2022-05-10 | 2022-04-07 | 2022-04-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45151605 | T2 EI WST PNT-VLY SPRNGS 14/181 RPR GYWW | ICW
LC | 120760036 | 012/059 | T2 EI MSS LNDG-MTCLF 12/59 RMV VEG | MOSSLNDG | ETL.6050.TOWR | 2021-04-07 | 2021-04-07 | 2021-09-23 | 2022-04-07 | 2022-04-07 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120760038 | 012/060 | T2 EI MSS LNDG-MTCLF 12/60 RMV VEG | MOSSLNDG | ETL.6050.TOWR | 2021-04-07 | 2021-04-07 | 2021-09-23 | 2022-04-07 | 2022-04-07 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120760102 | 021/092 | T2 EI PTTSBURG-TSL #1 21/092 COMPLETE | CONCORD | ETL.5510.TOWR | 2021-04-07 | 2021-04-07 | 2022-04-09 | 2022-04-07 | 2022-04-07 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45233261 | T2 EI PTTSBURG-TSL #1 21/092 RPR FOND | ICQ
LC | 120760103 | 020/091 | T2 EI PITTSBRG-TSLA #1 020/091 COMPLETE | CONCORD | ETL.5510.TOWR | 2021-04-07 | 2021-04-07 | 2022-04-09 | 2022-04-07 | 2022-04-07 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45233262 | T2 EI PITTSBRG-TSLA #1 020/091 RPR FOND | ICQ
LC | 120760494 | 092/469 | T2 EI MLN-RND MTN 92/469 RPR GYWT | TABLEMTN | ETL.6020.TOWR | 2021-04-07 | 2021-04-07 | 2022-08-18 | 2022-04-07 | 2022-04-07 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45425720 | T2 EI MLN-RND MTN 92/469 RPR GYWT | ICS
LC | 120761526 | 004/052 | T2 CLGTE-SMRTVILLE #1 004/052 RPL STRW | SACTO | ETL.6510.POLE.WOOD | 2021-04-08 | 2021-04-07 | 2022-07-25 | 2022-04-07 | 2022-04-07 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535911 | T2 CLGTE-SMRTVILLE #1 004/052 RPL STRW | 70Y
LC | 120761607 | 005/026 | T2 DI METCALF-EL PATIO #1 5/26 RPL INSS | METCALF | ETL.2500.INSL | 2021-04-08 | 2021-03-29 | 2021-08-08 | 2022-03-29 | 2022-03-29 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31435259 | DI METCALF-EL PATIO #1 RPL INSS IN 2 TW | 93K
LC | 120761608 | 005/026 | T2 DI METCALF-EL PATIO #2 5/26 RPL INSS | METCALF | ETL.2510.INSL | 2021-04-08 | 2021-03-29 | 2022-01-31 | 2022-03-29 | 2022-03-29 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549061 | DI METCALF-EL PATIO #2 RPLC INSS 4TWRS | 93K
LC | 120761769 | 020/287 | T2 DI SSQC-SNT YNZ SW ST 20/287 RPL STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-08 | 2021-04-01 | 2022-06-27 | 2022-04-01 | 2022-04-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31596782 | T2 DI SISQUOC-SANTA YNEZ 20/286 RPL STRW | 70Y
LC | 120761987 | 021/122 | T2 DI STANISLAUS-MNTCA #2 21/122 UNBURY | VICTOR | ETL.3820.TOWR | 2021-04-08 | 2021-04-05 | 2022-02-22 | 2022-04-05 | 2022-04-05 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123120 | T2 DI STANISLAUS-MNTCA #2 21/122 UNBURY | ICQ
LC | 120761988 | 021/122 | T2 DI STNISLAUS-MTC #2 21/122 RPL INSS | VICTOR | ETL.3820.INSL.NCER | 2021-04-08 | 2021-04-05 | 2021-12-08 | 2022-04-05 | 2022-04-05 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528964 | EI STANISLAUS-MANTECA#2 RPLC INSS 12TWR | 93K
LC | 120762425 | 001/015 | T2 EI CRAG VIEW-CASCADE 1/15 RPR CRSW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-08 | 2021-04-08 | 2021-08-02 | 2022-04-08 | 2022-04-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Crossarm-Wood | Repair | 44859789 | T2 EI CRAG VIEW-CASCADE 1/15 RPR CRSW | ICW
LC | 120762713 | 005/064 | T2 EI WST POINT-VALY SPRGS 5/64C REPL PL | VICTOR | ETL.8350.POLE.WDPS | 2021-04-08 | 2021-04-08 | 2022-05-24 | 2022-04-08 | 2022-04-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535841 | T2 EI WST POINT-VALY SPRGS 5/64L REPL PL | 70Y
LC | 120762758 | 005/064 | T2 EI WST POINT-VALY SPRGS 5/64R REPL PL | VICTOR | ETL.8350.POLE.WDPS | 2021-04-08 | 2021-04-08 | 2022-05-24 | 2022-04-08 | 2022-04-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535841 | T2 EI WST POINT-VALY SPRGS 5/64L REPL PL | 70Y
LC | 120762785 | 005/064 | T2 EI WST POINT-VALY SPRGS 5/64L REPL PL | VICTOR | ETL.8350.POLE.WDPS | 2021-04-08 | 2021-04-08 | 2022-05-24 | 2022-04-08 | 2022-04-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535841 | T2 EI WST POINT-VALY SPRGS 5/64L REPL PL | 70Y
LC | 120763328 | 001/012 | T2 EI CRAG VIEW-CASCADE 1/12R RPR STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-08 | 2021-04-08 | 2021-07-28 | 2022-04-08 | 2022-04-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44859783 | T2 EI CRAG VIEW-CASCADE 1/12R RPR STRW | ICW
LC | 120763602 | 015/101 | T2 EI METCALF-GRN VALLEY 15/101 RPR STRW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-04-08 | 2021-04-08 | 2021-05-19 | 2022-04-08 | 2022-04-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44805592 | T2 EI METCALF-GRN VALLEY 15/101 RPR STRW | ICW
LC | 120763699 | 006/073 | T2 EI WST PINT-VLY SPRINGS 6/73 RPL PL | VICTOR | ETL.8350.POLE.WOOD | 2021-04-08 | 2021-04-08 | 2022-05-26 | 2022-04-08 | 2022-04-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535842 | T2 WST PINT-VLY SPRINGS 6/73 RPL PL | 70Y
LC | 120763720 | 001/011 | T2 EI CRAG VIEW-CASCADE 1/11C RPR GYWW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-08 | 2021-04-08 | 2021-06-17 | 2022-04-08 | 2022-04-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859751 | T2 EI CRAG VIEW-CASCADE 1/11C RPR GYWW | ICW
LC | 120763721 | 001/011 | T2 EI CRAG VIEW-CASCADE 1/11L RPR GYWW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-08 | 2021-04-08 | 2021-06-17 | 2022-04-08 | 2022-04-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859753 | T2 EI CRAG VIEW-CASCADE 1/11L RPR GYWW | ICW
LC | 120763722 | 001/011 | T2 EI CRAG VIEW-CASCADE 1/11R RPR GYWW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-08 | 2021-04-08 | 2021-06-17 | 2022-04-08 | 2022-04-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44859756 | T2 EI CRAG VIEW-CASCADE 1/11R RPR GYWW | ICW
LC | 120763741 | 002/021 | T2 EI CHRISTIE-WLLW PSS 002/021 INS ANMW | CONCORD | ETL.6370.POLE.WOOD | 2021-04-08 | 2021-04-08 | 2021-10-14 | 2022-04-08 | 2022-04-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Missing | Animal Guard-Wood | Install | 44959017 | T2 EI CHRISTIE-WLLW PSS 002/021 INS ANMW | ICW
LC | 120763871 | 006/075 | T2 EI WST PINT-VLY SPRNGS 6/75 RPR WDPKR | VICTOR | ETL.8350.POLE.WOOD | 2021-04-08 | 2021-04-08 | 2022-05-21 | 2022-04-08 | 2022-04-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45151606 | T2 EI WST PINT-VLY SPRNGS 6/75 RPR WDPKR | ICW
LC | 120763909 | 009/102 | T2 EI VEDDER TAP 009/102 RPR HRDW | MIDWAY | ETL.2141.POLE.WOOD | 2021-04-08 | 2021-04-08 | 2022-01-27 | 2022-04-08 | 2022-04-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45068046 | T2 EI VEDDER TAP 009/102 RPR HRDW | ICW
LC | 120764222 | 013/118 | T2 EI DRUM-RIO OSO #1 013/118 RPR SPLS | SACTO | ETL.1420.INSL.CERA | 2021-04-08 | 2021-04-08 | 2021-12-12 | 2022-04-08 | 2022-04-08 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Repair | 44737205 | T2 EI DRUM-RIO OSO #1 013/118 RPR SPLS | ICS
LC | 120764291 | 004/052 | T2 EI PIT #1HT CRK #2-BNY 4/52 RPR GYWW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-04-08 | 2021-04-08 | 2021-05-19 | 2022-04-08 | 2022-04-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 120764308 | 002/023 | T2 EI CHRISTIE-WILLOW 2/23 RPL POLE | CONCORD | ETL.6370.POLE.WDPS | 2021-04-08 | 2021-04-08 | 2022-08-31 | 2022-04-08 | 2022-04-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31535890 | T2 EI CHRISTIE-WILLOW 2/23 RPL POLE | 70Y
LC | 120764323 | 002/023 | T2 EI CHRISTIE-WILLOW 2/23 RPL POLE | CONCORD | ETL.6370.POLE.WDPS | 2021-04-08 | 2021-04-08 | 2022-08-31 | 2022-04-08 | 2022-04-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31535890 | T2 EI CHRISTIE-WILLOW 2/23 RPL POLE | 70Y
LC | 120764510 | 045/391 | T2 EI RND MTN-CTNWD 45/391 RPR FOND | TABLEMTN | ETL.5650.TOWR | 2021-04-08 | 2021-04-08 | 2022-03-04 | 2022-04-08 | 2022-04-08 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45110547 | T2 EI RND MTN-CTNWD 45/391 RPR FOND | ICQ
LC | 120764671 | C017/069 | T2 EI CN-LS GLS C017/069 RMV DBRS CNDS | MOSSLNDG | ETL.4460.INSL | 2021-04-08 | 2021-04-08 | 2021-09-25 | 2022-04-08 | 2022-04-08 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Conductor-Steel | Remove | 44961514 | T2 EI CN-LS GLS C017/069 RMV DBRS CNDS | ICS
LC | 120764971 | 002/026 | T2 EI CRAG VIEW-CASCADE 2/26R RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-08 | 2021-04-07 | 2021-07-27 | 2022-04-07 | 2022-04-07 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31516883 | T2 CRAG VIEW-CASCADE 17/151A RPL POLE | 70Y
LC | 120765204 | 002/027 | T2 EI CRAG VIEW-CASCADE 2/27M RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-08 | 2021-04-07 | 2021-07-27 | 2022-04-07 | 2022-04-07 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31516883 | T2 CRAG VIEW-CASCADE 17/151A RPL POLE | 70Y
LC | 120765382 | C018/072 | T2 EI MSS LANDING-COBURN C18/72 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-04-08 | 2021-04-08 | 2022-03-16 | 2022-04-08 | 2022-04-08 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45118707 | T2 EI MSS LANDING-COBURN C18/72 RPR FOND | ICQ
LC | 120765762 | 052/369 | T2 DI CARIBOU-TABLE MTN 52/369 RPR INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-04-08 | 2021-04-01 | 2022-06-11 | 2022-04-01 | 2022-04-01 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45212345 | T2 DI CARIBOU-TABLE MTN 52/369 RPR INSS | ICS
LC | 120765948 | 022/092 | T2 EI GEYSERS #12-FULTON 22/092 RPR FOND | LAKEVLLE | ETL.4750.TOWR | 2021-04-08 | 2021-04-08 | 2022-01-28 | 2022-04-08 | 2022-04-08 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45150732 | T2 EI GEYSERS #12-FULTON 22/092 RPR FOND | ICQ
LC | 120765990 | 022/091 | T2 EI GEYSERS #12-FULTON 22/091 RPL INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2021-04-08 | 2021-04-08 | 2022-06-13 | 2022-04-08 | 2022-04-08 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31539352 | 02 EI GEYSERS #12-FULTON 7 TWRS | 93K
LC | 120766013 | 017/102 | T2 DI STANISLAUS-MNTCA #2 17/102 RMV VEG | VICTOR | ETL.3820.TOWR | 2021-04-08 | 2021-03-25 | 2021-12-16 | 2022-03-25 | 2022-03-25 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 120766238 | 004/026 | T2 DI KRCKHFF-CLVS-SNGR #1 4/26 COMPLETE | FRESNO | ETL.1890.INSL.CERA | 2021-04-08 | 2021-03-29 | 2022-05-24 | 2022-03-29 | 2022-03-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528484 | DI KERCKHOFF-CLVS-SNGR #1 RPLC INSS 22TW | 93K
LC | 120766284 | 004/026 | T2 DI KRCKHFF-CLVS-SNGR #1 4/26 INS HRDT | FRESNO | ETL.1890.TOWR | 2021-04-08 | 2021-03-29 | 2022-02-10 | 2022-03-29 | 2022-03-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45068406 | T2 DI KRCKHFF-CLVS-SNGR #1 4/26 INS HRDT | ICQ
LC | 120766338 | 004/026 | T2 DI KRCKHFF-CLVS-SNGR #1 4/26 RPR FOND | FRESNO | ETL.1890.TOWR | 2021-04-08 | 2021-03-29 | 2022-02-10 | 2022-03-29 | 2022-03-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45068407 | T2 DI KRCKHFF-CLVS-SNGR #1 4/26 RPR FOND | ICQ
LC | 120766628 | 015/097 | T2 EI METCALF-GRN VALLEY 15/97R RPL STRW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-04-08 | 2021-04-08 | 2021-07-28 | 2022-04-08 | 2022-04-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535758 | T2 EI METCALF-GRN VALLEY 15/97L RPL STRW | 70Y
LC | 120767251 | 008/011 | T2 DI VLLY SPRNGS-MRTEL #1 8/11 RPL POLE | VICTOR | ETL.8240.POLE.WOOD | 2021-04-08 | 2021-04-08 | 2021-08-20 | 2022-04-08 | 2022-04-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535840 | T2 DI VLLY SPRNGS-MRTEL #1 8/11 RPL POLE | 70Y
LC | 120769542 | 013/168 | T2 EI WST PNT-VLY SPRGS 13/168 RPR GYWW | VICTOR | ETL.8350.POLE.NWOD | 2021-04-09 | 2021-04-08 | 2022-03-07 | 2022-04-08 | 2022-04-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45151608 | T2 EI WST PNT-VLY SPRGS 13/168 RPR GYWW | ICW
LC | 120769739 | 027/161 | T2 EI TMBLR-SN LS OBSP 27/161 COMPLETE | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-09 | 2021-04-09 | 2022-04-26 | 2022-04-09 | 2022-04-09 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45069385 | T2 EI TMBLR-SN LS OBSP 27/161 RPR SPLS | ICS
LC | 120769752 | 027/161 | T2 EI TMBLR-SN LS OBSP 27/161 RPL INSLS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-09 | 2021-04-09 | 2022-08-29 | 2022-04-09 | 2022-04-09 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31526478 | T3 EI TMBLOR-SN LS OBSPO RPL INSL 5TWR | 93K
LC | 120769856 | 012/204 | T2 EI TEJON-LEBEC 12/204 RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-05 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44817948 | T2 EI TEJON-LEBEC 12/204 RPR GYWW | ICW
LC | 120770087 | 000/006 | T2 EI CRAG VIEW-CASCADE 00/06 RPR WDPKR | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-09 | 2021-04-09 | 2021-06-15 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Structure-Wood | Remove | 44859744 | T2 EI DELTA-COTTONWOOD 00/06 RPR WDPKR | ICW
LC | 120770117 | 000/006 | EI T2 CRAG VIEW-CASCADE 0/06 RMV PL BUTT | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-09 | 2021-04-09 | 2021-06-15 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Structure-Wood | Remove | 44859747 | EI T2 DELTA-COTTONWOOD 0/006 RMV PL BUTT | ICW
LC | 120770145 | 025/153 | T2 DI TSLA SLDO MNTCA 25/153 RPL HDWW | VICTOR | ETL.4000.POLE.WOOD | 2021-04-09 | 2021-04-06 | 2021-10-09 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44977840 | T2 DI TSLA SLDO MNTCA 25/153 RPL HDWW | ICW
LC | 120770147 | 025/153 | T2 DI TSLA SLDO MNTCA 25/153 RPR GYWW | VICTOR | ETL.4000.POLE.WOOD | 2021-04-09 | 2021-04-06 | 2021-10-09 | 2022-04-06 | 2022-04-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44977841 | T2 DI TSLA SLDO MNTCA 25/153 RPR GYWW | ICW
LC | 120770224 | 024/346 | T2 EI CLAY-MARTEL 24/346 BACKFILL HOLE | VICTOR | ETL.8250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-07-14 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44806289 | T2 EI CLAY-MARTEL 24/346 BACKFILL HOLE | ICW
LC | 120770296 | A006/079 | T2 PALERMO-OROVILLE #2 A6/79 REFRAME | TABLEMTN | ETL.7740.POLE.WOOD | 2021-04-09 | 2021-04-08 | 2022-04-21 | 2022-04-08 | 2022-04-08 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31536000 | T2 PALERMO-OROVILLE #2 A6/79 REFRAME | 93E
LC | 120770309 | 018/257 | T2 EI CLAY-MARTEL 18/257 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-04 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44806271 | T2 EI CLAY-MARTEL 18/257 RPR GYWW | ICW
LC | 120770320 | 002/029 | T2 EI CHRSTIE-WLW PSS 002/029 RPL INSW | CONCORD | ETL.6370.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2022-06-01 | 2022-04-09 | 2022-04-09 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535837 | T2 EI CHRSTIE-WLW PSS 002/029 RPL INSW | 93I
LC | 120770338 | 016/074 | T2 EI PTTSRG-TL #1 16/74 RPR FOND CMPLTD | CONCORD | ETL.5510.TOWR | 2021-04-09 | 2021-04-09 | 2022-03-28 | 2022-04-09 | 2022-04-09 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2N PRTO FRAB NTDE | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45233263 | T2NT EI PITTSBRG-TSLA #1 16/074 RPR FOND | ICQ
LC | 120770373 | 015/097 | T2 EI METCALF-GRN VALLEY 15/97C RPL STRW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-04-09 | 2021-04-08 | 2021-07-28 | 2022-04-08 | 2022-04-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535758 | T2 EI METCALF-GRN VALLEY 15/97L RPL STRW | 70Y
LC | 120770376 | 015/097 | T2 EI METCALF-GRN VALLEY 15/97L RPL STRW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-04-09 | 2021-04-08 | 2021-07-28 | 2022-04-08 | 2022-04-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535758 | T2 EI METCALF-GRN VALLEY 15/97L RPL STRW | 70Y
LC | 120770391 | 003/041 | T2 EI PIT 1-HAT CRK 2-BRNY 3/41 RPR HRDW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2022-07-19 | 2022-04-09 | 2022-04-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213846 | T2 EI PIT 1-HAT CRK 2-BRNY 3/41 RPR HRDW | ICW
LC | 120770464 | 010/074 | T2 EI VC-VCVLL-JMSN-N 10/74 RPL INSS | LAKEVLLE | ETL.4100.INSL.NCER | 2021-04-09 | 2021-04-09 | 2022-02-26 | 2022-04-09 | 2022-04-09 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549400 | T2 DI VC-VACVILLE-JMESN-NH RPL INSS 5TWR | 93K
LC | 120770537 | 014/095 | T2 EI MTCLF-GRN VLLY 14/95 RPL INSW | MOSSLNDG | ETL.2540.INSL.CERA | 2021-04-09 | 2021-04-09 | 2021-08-13 | 2022-04-09 | 2022-04-09 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31534650 | T2 DI METCALF-GRN VALLEY 12/79 RPLC INSW | 93I
LC | 120770544 | 003/040 | T2 EI PIT 1-HAT CRK 2-BRNY 3/40 RPR HRDW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2022-07-19 | 2022-04-09 | 2022-04-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213845 | T2 EI PIT 1-HAT CRK 2-BRNY 3/40 RPR HRDW | ICW
LC | 120770582 | 019/264 | T2 DI SISQUOC-SANTA YNEZ 19/264 RPR INSW | PISMOBCH | ETL.3700.INSL.NCER | 2021-04-09 | 2021-04-01 | 2022-03-02 | 2022-04-01 | 2022-04-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45069236 | T2 DI SISQUOC-SANTA YNEZ 19/264 RPR INSW | ICW
LC | 120770611 | 018/257A | T2 EI CLAY-MARTEL 18/257A RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-04 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44806298 | T2 EI CLAY-MARTEL 18/257A RPR GYWW | ICW
LC | 120770633 | 010/073 | T2 EI VC-VCVLL-JMSN-N 10/73 RPL INSS | LAKEVLLE | ETL.4100.INSL.CERA | 2021-04-09 | 2021-04-09 | 2022-02-26 | 2022-04-09 | 2022-04-09 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549400 | T2 DI VC-VACVILLE-JMESN-NH RPL INSS 5TWR | 93K
LC | 120770709 | 018/257B | T2 EI CLAY-MARTEL 18/257B RPR WDPKR | VICTOR | ETL.8250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-04 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44806225 | T2 EI CLAY-MARTEL 18/257B RPR WDPKR | ICW
LC | 120770720 | 018/257B | T2 EI CLAY-MARTEL 18/257B RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-04 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44806321 | T2 EI CLAY-MARTEL 18/257B RPR GYWW | ICW
LC | 120770871 | 009/067 | T2 EI GREEN VALLEY-LLAGAS 9/67 RPR GYWW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-04-09 | 2021-04-08 | 2021-09-28 | 2022-04-08 | 2022-04-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44981649 | T2 EI GREEN VALLEY-LLAGAS 9/67 RPR GYWW | ICW
LC | 120770872 | 001/011 | T2 EI CRAG VIEW-CASCADE 001/011 RPR OPGW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-09 | 2021-04-09 | 2021-08-07 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44859781 | T2 EI CRAG VIEW-CASCADE 001/011 RPR OPGW | ICW
LC | 120770875 | 009/067 | T2 EI GREEN VALLEY-LLAGS 9/67 RPR GYWW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-04-09 | 2021-04-08 | 2021-09-28 | 2022-04-08 | 2022-04-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44981650 | T2 EI GREEN VALLEY-LLAGS 9/67 RPR GYWW | ICW
LC | 120770966 | 024/337 | T2 EI CLAY-MARTEL 024/337 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-02 | 2022-04-09 | 2022-04-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31535891 | T2 EI CLAY-MARTEL 020/278 RPL STRW | 70Y
LC | 120771009 | 011/201 | T2 EI TEJON-LEBEC 11/201 RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-05 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44817954 | T2 EI TEJON-LEBEC 11/201 RPR GYWW | ICW
LC | 120771067 | 004/026 | T2 DI STNSLS-MNTC #2 4/26 RPR INSLS | VICTOR | ETL.3820.INSL.CERA | 2021-04-09 | 2021-04-06 | 2021-11-29 | 2022-04-06 | 2022-04-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44977854 | T2 DI STNSLS-MNTC #2 4/26 RPR INSLS | ICS
LC | 120771206 | 011/200 | T2 EI TEJON-LEBEC 11/200 RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-05 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44817957 | T2 EI TEJON-LEBEC 11/200 RPR GYWW | ICW
LC | 120771261 | 044/382 | T2 EI PIT #1-COTTONWD 44/382 TIGHTN HRD | TABLEMTN | ETL.5390.TOWR | 2021-04-09 | 2021-04-09 | 2022-03-10 | 2022-04-09 | 2022-04-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Steel | Replace | 45182628 | T2 EI PIT #1-COTTONWD 44/382 TIGHTN HRD | ICS
LC | 120771515 | 023/325 | T2 EI CLAY-MARTEL 023/325 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-20 | 2022-04-09 | 2022-04-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541443 | T2 EI CLAY-MARTEL 023/325 RPL STRW | 70Y
LC | 120771566 | 018/259 | T2 EI CLAY-MARTEL 18/259 RPR WDPKR | VICTOR | ETL.8250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-05 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44806231 | T2 EI CLAY-MARTEL 18/259 RPR WDPKR | ICW
LC | 120771578 | 018/259 | T2 EI CLAY-MARTEL 18/259 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-06 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44806295 | T2 EI CLAY-MARTEL 18/259 RPR GYWW | ICW
LC | 120771603 | 026/165 | T2 DI TSLA SLDO MNTCA 26/165 RPL INSW | VICTOR | ETL.4000.INSL.NCER | 2021-04-09 | 2021-04-06 | 2022-02-03 | 2022-04-06 | 2022-04-06 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535904 | T2 DI TSLA SLDO MNTCA 26/165 RPL INSW | 93I
LC | 120771604 | 016/105 | T2 EI METCALF-GRN VLLY 16/105C RPL STRW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-04-09 | 2021-04-06 | 2021-08-25 | 2022-04-06 | 2022-04-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535894 | T2 EI METCALF-GRN VLLY 16/105L RPL STRW | 70Y
LC | 120771606 | 001/012 | T2 EI CRAG VIEW-CASCADE 1/12 RPR SHLW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-09 | 2021-04-09 | 2021-08-03 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44859786 | T2 EI CRAG VIEW-CASCADE 1/12 RPR SHLW | ICW
LC | 120771608 | 001/012 | T2 EI CRAG VIEW-CASCADE 1/12 RPL INSW | TABLEMTN | ETL.1350.INSL.CERA | 2021-04-09 | 2021-04-09 | 2021-08-03 | 2022-04-09 | 2022-04-09 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31540926 | T2 EI CRAG VIEW-CASCADE 1/12 RPL INSW | 93I
LC | 120771712 | 001/029 | T2 WV WEIMAR #1 1/29 INST DAMP | SACTO | ETL.7560.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-14 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Wood | Install | 44755080 | T2 WV WEIMAR #1 1/29 INST DAMP | ICW
LC | 120771716 | 003/037 | T2 EI CHRSTIE-WLLW PSS 003/037 RPR STRW | CONCORD | ETL.6370.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2022-03-30 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45181069 | T2 EI CHRSTIE-WLLW PSS 003/037 RPR STRW | ICW
LC | 120771717 | 011/198 | T2 EI TEJON-LEBEC 11/198 RPR GYWW | MIDWAY | ETL.9250.POLE.NWOD | 2021-04-09 | 2021-04-09 | 2021-08-05 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44817574 | T2 DI TEJON-LEBEC 011/198 RPR SPLW | ICW
LC | 120771744 | 030/006 | T2 EI GRBRVLL-LYTNVLL 30/6 RPR GYWW | WILLITS | ETL.8365.POLE.NWOD | 2021-04-09 | 2021-04-09 | 2022-04-15 | 2022-04-09 | 2022-04-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44754990 | T2 EI GRBRVLL-LYTNVLL 30/6 RPR GYWW | ICW
LC | 120771751 | 003/017 | T2 DI STNISLS-MANTCA #2 3/17 INST STEP | VICTOR | ETL.3820.TOWR | 2021-04-09 | 2021-04-06 | 2022-01-12 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45119068 | T2 DI STNISLS-MANTCA #2 3/17 INST STEP | ICQ
LC | 120772084 | 011/197 | T2 EI TEJON-LEBEC 11/197 RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-05 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44818003 | T2 EI TEJON-LEBEC 11/197 RPR GYWW | ICW
LC | 120772178 | 001/015 | T2 CRAG VIEW-CASCADE 001/015 RPR OPGW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-04-09 | 2021-04-09 | 2021-06-17 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44859791 | T2 CRAG VIEW-CASCADE 001/015 RPR OPGW | ICW
LC | 120772534 | 011/196 | T2 EI TEJON-LEBEC 11/196 RPL ANCW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-07 | 2022-04-09 | 2022-04-09 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31535903 | T2 EI TEJON-LEBEC 11/196 RPL ANCW | 93E
LC | 120772629 | 008/066 | T2 EI VC-VCVLL-JMSN-N 8/66 RPL INSS | LAKEVLLE | ETL.4100.INSL.NCER | 2021-04-09 | 2021-04-09 | 2022-02-25 | 2022-04-09 | 2022-04-09 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549199 | EI VCA-VCVILE-JMESN-NRTH TO RPL INSS 7TW | 93K
LC | 120772678 | 004/027 | T2 DI STNSLS-MNTCA #2 4/27 RPR STRT | VICTOR | ETL.3820.TOWR | 2021-04-09 | 2021-04-06 | 2022-01-18 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45119716 | T2 DI STNSLS-MNTCA #2 4/27 RPR STRT | ICQ
LC | 120772685 | 022/317 | T2 EI CLAY-MARTEL 022/317 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-09 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44806228 | T2 EI CLAY-MARTEL 022/317 RPR STRW | ICW
LC | 120772704 | 050/206 | T2 EI MIDWAY-WHIRLWIND 50/206 RPR GYWS | MIDWAY | ETL.6030.TOWR | 2021-04-09 | 2021-04-09 | 2022-01-24 | 2022-04-09 | 2022-04-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45067936 | T2 EI MIDWAY-WHIRLWIND 50/206 RPR GYWS | ICS
LC | 120772774 | 050/204 | T2 EI MDWY-WHRLWND 50/204 RPR GYWS | MIDWAY | ETL.6030.TOWR | 2021-04-09 | 2021-04-09 | 2022-01-24 | 2022-04-09 | 2022-04-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45067937 | T2 EI MDWY-WHRLWND 50/204 RPR GYWS | ICS
LC | 120772780 | 004/027 | T2 DI STNSLS-MNTCA #2 4/27 RPL INSLS | VICTOR | ETL.3820.INSL.NCER | 2021-04-09 | 2021-04-06 | 2021-11-29 | 2022-04-06 | 2022-04-06 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528964 | EI STANISLAUS-MANTECA#2 RPLC INSS 12TWR | 93K
LC | 120772900 | 007/043 | T2 DI STAN ML-RVRBNK 7/43 RPL INSS CMPLT | VICTOR | ETL.3840.INSL.CERA | 2021-04-09 | 2021-04-06 | 2022-05-12 | 2022-04-06 | 2022-04-06 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31512192 | DI STANISLAUS-MELONES #2 RPL INSS 11TWR | 93K
LC | 120772903 | 007/043 | T2 DI STANISLAUS-MNTC #2 7/43 RPLC INSS | VICTOR | ETL.3820.INSL.CERA | 2021-04-09 | 2021-04-06 | 2021-12-09 | 2022-04-06 | 2022-04-06 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528964 | EI STANISLAUS-MANTECA#2 RPLC INSS 12TWR | 93K
LC | 120772918 | 013/159 | T2 WV IGNACIO-BOLINS #2 013/159 INS DAMP | LAKEVLLE | ETL.7180.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2022-04-30 | 2022-04-09 | 2022-04-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Wood | Install | 45142928 | T2 WV IGNACIO-BOLINS #2 013/159 INS DAMP | ICW
LC | 120773071 | 011/195 | T2 EI TEJON-LEBEC 11/195 RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-05 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44818004 | T2 EI TEJON-LEBEC 11/195 RPR GYWW | ICW
LC | 120773110 | 050/203 | T2 EI MIDWAY-WHIRLWIND 050/203 RPR GYWS | MIDWAY | ETL.6030.TOWR | 2021-04-09 | 2021-04-09 | 2022-01-24 | 2022-04-09 | 2022-04-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45067938 | T2 EI MIDWAY-WHIRLWIND 050/203 RPR GYWS | ICS
LC | 120773130 | 004/024 | T2 DI STNISLUS-MANTECA #2 4/24 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-09 | 2021-04-06 | 2022-01-18 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45119712 | T2 DI STNISLUS-MANTECA #2 4/24 RPR FOND | ICQ
LC | 120773226 | 019/268 | T2 EI CLAY-MARTEL 19/268 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-07-28 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44806274 | T2 EI CLAY-MARTEL 19/268 RPR STRW | ICW
LC | 120773343 | 050/202 | T2 EI MIDWAY-WHIRLWIND 050/202 RPR GYWS | MIDWAY | ETL.6030.TOWR | 2021-04-09 | 2021-04-09 | 2022-01-24 | 2022-04-09 | 2022-04-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45067939 | T2 EI MIDWAY-WHIRLWIND 050/202 RPR GYWS | ICS
LC | 120773346 | 019/270 | T2 EI CLAY-MARTEL 019/270 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-07-13 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44806239 | T2 EI CLAY-MARTEL 019/270 RPR GYWW | ICW
LC | 120773485 | 011/193 | T2 EI TEJON-LEBEC 11/193 RPL STRW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-08-11 | 2022-04-09 | 2022-04-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541448 | T2 EI TEJON-LEBEC 11/193 RPL STRW | 70Y
LC | 120773523 | 006/004 | T2 EI FULTON-HOPLAND 6/4 RPR GYWW | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-04-09 | 2021-04-09 | 2021-07-15 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 44877521 | T2 EI FULTON-HOPLAND 6/4 RPR GYWW | ICW
LC | 120773734 | 001/002 | T2 WV CLEAR LAKE-HPLND 001/002 RPR STRW | LAKEVLLE | ETL.6390.POLE.NWOD | 2021-04-09 | 2021-04-09 | 2022-02-08 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45136115 | T2 WV CLEAR LAKE-HPLND 001/002 RPR STRW | ICW
LC | 120773828 | 018/267 | T2 EI CLAY-MARTEL 18/267 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-07-28 | 2022-04-09 | 2022-04-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542984 | T2 EI CLAY-MARTEL 18/267 RPL STRW | 70Y
LC | 120773936 | 019/273 | T2 EI CLAY-MARTEL 019/273 RMV DBRS | VICTOR | ETL.8250.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-07-13 | 2022-04-09 | 2022-04-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44806277 | T2 EI CLAY-MARTEL 019/273 RMV DBRS | ICW
LC | 120773957 | 010/078 | T2 WV MORAGA-LAKEWOOD 10/78 RPR SPLS | CONCORD | ETL.3741.INSL.NCER | 2021-04-09 | 2021-04-09 | 2022-06-16 | 2022-04-09 | 2022-04-09 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Repair | 45195782 | T2 WV MORAGA-LAKEWOOD 10/78 RPR SPLS | ICS
LC | 120785585 | 032/001 | T2 EI GRBRVLL-LYTNVLL 32/1 RPL DAMW | WILLITS | ETL.8365.INSL.NCER | 2021-04-10 | 2021-04-08 | 2022-04-22 | 2022-04-08 | 2022-04-08 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 45079408 | T2 EI GRBRVLL-LYTNVLL 32/1 RPL DAMW | ICS
LC | 120785588 | 032/006 | T2 EI GRBRVLL-LYTNVLL 32/6 RPR GYWW | WILLITS | ETL.8365.POLE.WOOD | 2021-04-10 | 2021-04-09 | 2022-04-22 | 2022-04-09 | 2022-04-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44754991 | T2 EI GRBRVLL-LYTNVLL 32/6 RPR GYWW | ICW
LC | 120785595 | 032/005 | T2 EI GRBRVLL-LYTNVLL 32/5 RPR GYWW | WILLITS | ETL.8365.POLE.NWOD | 2021-04-10 | 2021-04-09 | 2022-04-22 | 2022-04-09 | 2022-04-09 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45079409 | T2 EI GRBRVLL-LYTNVLL 32/5 RPR GYWW | ICS
LC | 120785706 | 016/073 | T2 EI PITTSBURG-TESLA #1 16/73 COMPLETE | CONCORD | ETL.5510.TOWR | 2021-04-10 | 2021-04-10 | 2022-03-28 | 2022-04-10 | 2022-04-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45232978 | T2 EI PITTSBURG-TESLA #1 16/73 RPR FOND | ICQ
LC | 120785789 | 022/311 | T2 EI CLAY-MARTEL 022/311 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-08-09 | 2022-04-10 | 2022-04-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44806238 | T2 EI CLAY-MARTEL 022/311 RPR STRW | ICW
LC | 120785913 | 015/071 | T2 EI PTTSBRG-TSL #1 015/071 INS BOLT | CONCORD | ETL.5510.TOWR | 2021-04-10 | 2021-04-10 | 2022-03-28 | 2022-04-10 | 2022-04-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Hardware-Tower | Install | 45233264 | T2 EI PTTSBRG-TSL #1 015/071 INS BOLT | ICQ
LC | 120785966 | 049/200 | T2 EI MIDWAY-WHIRLWIND 049/200 RPR GYWS | MIDWAY | ETL.6030.TOWR | 2021-04-10 | 2021-04-10 | 2022-01-24 | 2022-04-10 | 2022-04-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45067980 | T2 EI MIDWAY-WHIRLWIND 049/200 RPR GYWS | ICS
LC | 120786072 | 049/199 | T2 EI MIDWAY-WHIRLWIND 049/199 RPR GYWS | MIDWAY | ETL.6030.TOWR | 2021-04-10 | 2021-04-10 | 2022-01-19 | 2022-04-10 | 2022-04-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45067981 | T2 EI MIDWAY-WHIRLWIND 049/199 RPR GYWS | ICS
LC | 120786149 | 015/281 | T2 EI FUTON-MLIN-CTTI 015/281 RPR GYWW | LAKEVLLE | ETL.6910.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2022-02-15 | 2022-04-10 | 2022-04-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45138285 | T2 EI FUTON-MLIN-CTTI 015/281 RPR GYWW | ICW
LC | 120786186 | 013/087 | T2 EI METCALF-GREEN VALLY 13/87 RPR SPLW | MOSSLNDG | ETL.2540.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-05-18 | 2022-04-10 | 2022-04-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Repair | 44805590 | T2 EI METCALF-GREEN VALLY 13/87 RPR SPLW | ICW
LC | 120786187 | 013/086 | T2 EI METCALF-GRN VLLY 13/86 RPL INSLW | MOSSLNDG | ETL.2540.INSL.NCER | 2021-04-10 | 2021-04-10 | 2021-07-09 | 2022-04-10 | 2022-04-10 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31534650 | T2 DI METCALF-GRN VALLEY 12/79 RPLC INSW | 93I
LC | 120786216 | 011/189 | T2 EI TEJON-LEBEC 11/189 INS DAMW | MIDWAY | ETL.9250.INSL.NCER | 2021-04-10 | 2021-04-10 | 2021-08-05 | 2022-04-10 | 2022-04-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 44818005 | T2 EI TEJON-LEBEC 11/189 INS DAMW | ICW
LC | 120786263 | 048/198 | T2 EI MIDWAY-WHIRLWIND 048/198 RPR GYWS | MIDWAY | ETL.6030.TOWR | 2021-04-10 | 2021-04-10 | 2022-01-19 | 2022-04-10 | 2022-04-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45067982 | T2 EI MIDWAY-WHIRLWIND 048/198 RPR GYWS | ICS
LC | 120786385 | 012/057 | T2 EI PITTSBURG-TESLA #112/057 INS BOLT | CONCORD | ETL.5510.TOWR | 2021-04-10 | 2021-04-10 | 2022-04-12 | 2022-04-10 | 2022-04-10 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45233266 | T2 EI PITTSBURG-TESLA #112/057 INS BOLT | ICQ
LC | 120786409 | :019/100 | T2 EI CZY HRS CYN-SLS-S :19/100 RPR STRT | MOSSLNDG | ETL.2900.TOWR | 2021-04-10 | 2021-04-10 | 2021-07-14 | 2022-04-10 | 2022-04-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair | 44839312 | T2 EI CZY HRS CYN-SLS-S :19/100 RPR STRT | ICQ
LC | 120786420 | :019/100 | T2 EI CZY HRS CYN-SL SL :019/100 RPR FND | MOSSLNDG | ETL.2900.TOWR | 2021-04-10 | 2021-04-10 | 2021-07-14 | 2022-04-10 | 2022-04-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44839313 | T2 EI CZY HRS CYN-SL SL :019/100 RPR FND | ICQ
LC | 120786621 | 048/196 | T2 EI MIDWAY-WHIRLWIND 048/196 RPR GYWS | MIDWAY | ETL.6030.TOWR | 2021-04-10 | 2021-04-10 | 2022-01-19 | 2022-04-10 | 2022-04-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45067983 | T2 EI MIDWAY-WHIRLWIND 048/196 RPR GYWS | ICS
LC | 120786660 | 011/186 | T2 EI TEJON-LEBEC 11/186 INS DAMW | MIDWAY | ETL.9250.INSL.NCER | 2021-04-10 | 2021-04-10 | 2021-08-05 | 2022-04-10 | 2022-04-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 44817794 | T2 DI TEJON-LEBEC 11/186 RPR GYWW | ICW
LC | 120786790 | 019/275 | T2 EI CLAY-MARTEL 019/275 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-07-13 | 2022-04-10 | 2022-04-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44806196 | T2 EI CLAY-MARTEL 019/275 RPR GYWW | ICW
LC | 120786807 | 011/185 | T2 EI TEJON-LEBEC 11/185 INS DAMW | MIDWAY | ETL.9250.INSL.NCER | 2021-04-10 | 2021-04-10 | 2021-08-05 | 2022-04-10 | 2022-04-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 44818017 | T2 EI TEJON-LEBEC 11/185 INS DAMW | ICW
LC | 120786851 | 011/185 | T2 EI TEJON-LEBEC 11/185 RMV VEG | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-10-28 | 2022-04-10 | 2022-04-10 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120786946 | 020/278 | T2 EI CLAY-MARTEL 020/278 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-08-01 | 2022-04-10 | 2022-04-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535891 | T2 EI CLAY-MARTEL 020/278 RPL STRW | 70Y
LC | 120786951 | 012/056 | T2 EI PTSBRG-TSL #1 12/056 RPR BENT STL | CONCORD | ETL.5510.TOWR | 2021-04-10 | 2021-04-10 | 2022-04-12 | 2022-04-10 | 2022-04-10 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45233267 | T2 EI PTSBRG-TSL #1 12/056 RPR BENT STL | ICQ
LC | 120786978 | 020/279 | T2 EI CLAY-MARTEL 020/279 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-07-31 | 2022-04-10 | 2022-04-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31545721 | T2 EI CLAY-MARTEL 020/279 RPL STRW | 70Y
LC | 120786989 | :020/102 | T2 EI CZY HRS CYN-SN SL :020/102 RPR FND | MOSSLNDG | ETL.2900.TOWR | 2021-04-10 | 2021-04-10 | 2021-07-07 | 2022-04-10 | 2022-04-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44839314 | T2 EI CZY HRS CYN-SN SL :020/102 RPR FND | ICQ
LC | 120787005 | :020/103 | T2 EI CZY HRS CYN- SL S :020/103 RPR FND | MOSSLNDG | ETL.2900.TOWR | 2021-04-10 | 2021-04-10 | 2021-07-07 | 2022-04-10 | 2022-04-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44839315 | T2 EI CZY HRS CYN- SL S :020/103 RPR FND | ICQ
LC | 120787009 | 020/280 | T2 EI CLAY-MARTEL 020/280 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-07-13 | 2022-04-10 | 2022-04-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44806282 | T2 EI CLAY-MARTEL 020/280 RPR GYWW | ICW
LC | 120787033 | 047/194 | T2 EI MIDWAY-WHIRLWIND 047/194 RPR GYWS | MIDWAY | ETL.6030.TOWR | 2021-04-10 | 2021-04-10 | 2022-01-19 | 2022-04-10 | 2022-04-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45067984 | T2 EI MIDWAY-WHIRLWIND 047/194 RPR GYWS | ICS
LC | 120787094 | 020/282 | T2 EI CLAY-MARTEL 020/282 INS ANMW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-07-14 | 2022-04-10 | 2022-04-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Missing | Animal Guard-Wood | Install | 44806234 | T2 EI CLAY-MARTEL 020/282 INS ANMW | ICW
LC | 120787126 | 011/184 | T2 EI TEJON-LEBEC 11/184 RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-08-05 | 2022-04-10 | 2022-04-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44818018 | T2 EI TEJON-LEBEC 11/184 RPR GYWW | ICW
LC | 120787248 | 020/285 | T2 EI CLAY-MARTEL 020/285 INS ANMW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-07-14 | 2022-04-10 | 2022-04-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Missing | Animal Guard-Wood | Install | 44806197 | T2 EI CLAY-MARTEL 020/285 INS ANMW | ICW
LC | 120787604 | 015/155 | T2 EI ARCO-CHOLAME 15/155 RMV NEST | MIDWAY | ETL.8440.POLE.NWOD | 2021-04-10 | 2021-04-10 | 2022-02-23 | 2022-04-10 | 2022-04-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45067920 | T2 EI ARCO-CHOLAME 15/155 RMV NEST | ICS
LC | 120787775 | :020/104 | T2 EI CRZ HRS C-S-SLD :20/104 RPR FND | MOSSLNDG | ETL.2900.TOWR | 2021-04-10 | 2021-04-10 | 2021-07-07 | 2022-04-10 | 2022-04-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44839316 | T2 EI CRZ HRS C-S-SLD :20/104 RPR FND | ICQ
LC | 120787787 | :020/105 | T2 EI CZY HR CNY-S-S #1 :22/105 RPR STRT | MOSSLNDG | ETL.2900.TOWR | 2021-04-10 | 2021-04-10 | 2021-07-07 | 2022-04-10 | 2022-04-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair | 44839317 | T2 EI CZY HR CNY-S-S #1 :22/105 RPR STRT | ICQ
LC | 120788073 | C013/053 | T2 EI MOSS LNDING-CBRN C013/053 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-04-10 | 2021-04-10 | 2022-05-19 | 2022-04-10 | 2022-04-10 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45118711 | T2 EI MOSS LNDING-CBRN C013/053 RPR FOND | ICQ
LC | 120788409 | 028/416 | T2 EI CLAY-MARTEL 028/416 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-07-14 | 2022-04-10 | 2022-04-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44806285 | T2 EI CLAY-MARTEL 028/416 RPR STRW | ICW
LC | 120788565 | 028/417 | T2 EI CLAY-MARTEL 28/417 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-07-15 | 2022-04-10 | 2022-04-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44806226 | T2 EI CLAY-MARTEL 28/417 RPR STRW | ICW
LC | 120788759 | 028/419 | T2 EI CLAY-MARTEL 28/419 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-07-15 | 2022-04-10 | 2022-04-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44806297 | T2 EI CLAY-MARTEL 28/419 RPR STRW | ICW
LC | 120789416 | 031/008 | T2 EI CLY-MRTEL 031/008 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-11-10 | 2022-04-10 | 2022-04-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31535448 | T2 EI CLAY-MARTEL 029/444 RPL STRW | 70Y
LC | 120792753 | 027/199 | T2 EI DRUM-RIO OSO #1 27/199 RMV VEG | SACTO | ETL.1420.TOWR | 2021-04-12 | 2021-04-09 | 2022-01-12 | 2022-04-09 | 2022-04-09 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120792754 | 019/156 | T2 EI DRUM-RIO OSO #1 19/156 RPR FOND | SACTO | ETL.1420.TOWR | 2021-04-12 | 2021-04-10 | 2022-03-07 | 2022-04-10 | 2022-04-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44752915 | T2 EI DRUM-RIO OSO #1 19/156 RPR FOND | ICQ
LC | 120792903 | 006/038 | T2 DI STANISLAUS-MANTEC #2 6/38 INS DAMS | VICTOR | ETL.3820.INSL.NCER | 2021-04-12 | 2021-04-06 | 2021-12-09 | 2022-04-06 | 2022-04-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Damper-Steel | Install | 44977856 | T2 DI STANISLAUS-MANTEC #2 6/38 INS DAMS | ICS
LC | 120792905 | 006/038 | T2 DI STANISLAUS-MANTEC #2 6/38 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-12 | 2021-04-06 | 2022-01-19 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45122101 | T2 DI STANISLAUS-MANTEC #2 6/38 RPR FOND | ICQ
LC | 120793163 | 016/099 | T2 DI STSLS-MLS SS-MTC #1 16/99 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-12 | 2021-04-09 | 2022-02-07 | 2022-04-09 | 2022-04-09 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45123059 | T2 DI STSLS-MLS SS-MTC #1 16/99 RPR FOND | ICQ
LC | 120793701 | 030/457 | T2 EI CLAY-MARTEL 30/457 INS HRDW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-12 | 2021-04-12 | 2021-07-22 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Missing | Hardware-Wood | Install | 44806272 | T2 EI CLAY-MARTEL 30/457 INS HRDW | ICW
LC | 120793811 | 002/012 | T2 DI LOS ESTEROS-METCALF 2/12 RPL INSS | METCALF | ETL.5353.TOWR | 2021-04-12 | 2021-04-08 | 2022-03-12 | 2022-04-08 | 2022-04-08 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31539595 | T2 DI LOS ESTEROS-METCALF 2/12 RPL INSS | 93K
LC | 120793859 | 028/427 | T2 EI CLAY-MARTEL 28/427 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-12 | 2021-04-12 | 2021-07-15 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44806284 | T2 EI CLAY-MARTEL 28/427 RPR STRW | ICW
LC | 120794098 | 028/428 | T2 EI CLAY-MARTEL 28/428 DLFL | VICTOR | ETL.8250.POLE.WOOD | 2021-04-12 | 2021-04-12 | 2021-07-15 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44806195 | T2 EI CLAY-MARTEL 28/428 RPR STRW | ICW
LC | 120794319 | 006/037 | T2 DI STSLS-MLS SS-MTC #1 6/37 RPR SPLS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-06 | 2022-03-04 | 2022-04-06 | 2022-04-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 44978042 | T2 DI STSLS-MLS SS-MTC #1 6/37 RPR SPLS | ICS
LC | 120794361 | 030/458 | T2 EI CLAY-MARTEL 30/458 RPL INSW | VICTOR | ETL.8250.INSL.NCER | 2021-04-12 | 2021-04-12 | 2021-07-22 | 2022-04-12 | 2022-04-12 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535892 | T2 EI CLAY-MARTEL 30/458 RPL INSW | 93I
LC | 120794416 | 023/174 | T2 EI DRUM-RIO OSO #2 23/174 RPL SPLS | SACTO | ETL.1430.INSL.CERA | 2021-04-12 | 2021-04-12 | 2021-09-26 | 2022-04-12 | 2022-04-12 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Replace | 44752916 | T2 EI DRUM-RIO OSO #2 23/174 RPL SPLS | ICS
LC | 120794482 | 030/447 | T2 EI CLAY-MARTEL 30/447 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-12 | 2021-04-12 | 2021-07-14 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44806236 | T2 EI CLAY-MARTEL 30/447 RPR GYWW | ICW
LC | 120794564 | 001/011 | T2 DI STNSLS-MLNS-MNTC 1/11 RPLC DAMS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-09 | 2022-03-01 | 2022-04-09 | 2022-04-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 44977952 | T2 DI STNSLS-MLNS-MNTC 1/11 RPLC DAMS | ICS
LC | 120794758 | 031/010 | T2 EI CLAY-MARTEL 31/10 RPR SPLW | VICTOR | ETL.8250.INSL.CERA | 2021-04-12 | 2021-04-12 | 2021-07-30 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Repair | 44806290 | T2 EI CLAY-MARTEL 31/10 RPR SPLW | ICW
LC | 120794760 | 031/009 | T2 EI CLAY-MARTEL 31/9 RPR SPLW | VICTOR | ETL.8250.INSL.CERA | 2021-04-12 | 2021-04-10 | 2021-11-10 | 2022-04-10 | 2022-04-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Repair | 44806227 | T2 EI CLAY-MARTEL 31/9 RPR SPLW | ICW
LC | 120794896 | 005/001 | T2 LAKEVILLE #1 5/1 REFRAME | LAKEVLLE | ETL.7360.POLE.NWOD | 2021-04-12 | 2021-04-12 | 2022-09-17 | 2022-04-12 | 2022-04-12 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31596396 | T2 LAKEVILLE #1 5/1 REPLACE ANCHOR | 93E
LC | 120794962 | 030/452 | T2 EI CLAY-MARTEL 30/452 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-12 | 2021-04-12 | 2021-07-21 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44806299 | T2 EI CLAY-MARTEL 30/452 RPR STRW | ICW
LC | 120795031 | 045/185 | T2 EI MIDWAY-WHIRLWIND 45/185 RPL INSS | MIDWAY | ETL.6030.INSL | 2021-04-12 | 2021-04-12 | 2022-03-09 | 2022-04-12 | 2022-04-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536505 | MIDWAY-WHIRLWIND RPL INSS 4TWRS | 93K
LC | 120795167 | 030/454 | T2 EI CLAY-MARTEL 30/454 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-12 | 2021-04-12 | 2021-07-21 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44806280 | T2 EI CLAY-MARTEL 30/454 RPR GYWW | ICW
LC | 120795309 | 005/032 | T2 DI STNLS-MLNS-MNTC 5/32 RPLC DAMS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-09 | 2022-03-03 | 2022-04-09 | 2022-04-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 44978040 | T2 DI STNLS-MLNS-MNTC 5/32 RPLC DAMS | ICS
LC | 120795555 | 005/033 | T2 DI STANISLAUS-MANTC #2 5/33 INS DAMS | VICTOR | ETL.3840.INSL.CERA | 2021-04-12 | 2021-04-09 | 2022-05-11 | 2022-04-09 | 2022-04-09 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | Missing | Damper-Steel | Install | 45122074 | T2 DI STANISLAUS-MANTC #2 5/33 INS DAMS | ICS
LC | 120795676 | 005/033 | T2 DI STANISLAUS-MANTC #2 5/33 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-12 | 2021-04-09 | 2022-01-24 | 2022-04-09 | 2022-04-09 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45119923 | T2 DI STANISLAUS-MANTC #2 5/33 RPR FOND | ICQ
LC | 120795697 | 003/018 | T2 DI SLS-MLS SS-MTC #1 3/18 RPL DAMS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-06 | 2022-03-02 | 2022-04-06 | 2022-04-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 44977955 | T2 DI SLS-MLS SS-MTC #1 3/18 RPL DAMS | ICS
LC | 120795723 | 008/074 | T2 EI PARADISE TABLE MTN 8/074 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-12 | 2021-04-12 | 2021-07-16 | 2022-04-12 | 2022-04-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120795859 | 001/009 | T2 DI STANISLAUS-MANTECA #2 1/9 INS DAMS | VICTOR | ETL.3820.INSL.CERA | 2021-04-12 | 2021-04-09 | 2021-11-29 | 2022-04-09 | 2022-04-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Damper-Steel | Install | 45067142 | T2 DI STANISLAUS-MANTECA #2 1/9 INS DAMS | ICS
LC | 120795938 | 001/007 | T2 DI STNSLS-MLNS-MNTC#1 1/7 RPLC DAMS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-09 | 2022-03-01 | 2022-04-09 | 2022-04-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 44977951 | T2 DI STNSLS-MLNS-MNTC#1 1/7 RPLC DAMS | ICS
LC | 120796344 | 033/517 | T2 EI CLAY-MARTEL 33/517 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-12 | 2021-04-12 | 2021-07-24 | 2022-04-12 | 2022-04-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535891 | T2 EI CLAY-MARTEL 020/278 RPL STRW | 70Y
LC | 120796360 | 038/255 | T2 EI POE-RIO OSO 038/255 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-04-12 | 2021-04-12 | 2022-01-10 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45106666 | T2 EI POE-RIO OSO 038/255 RPR FOND | ICQ
LC | 120796371 | 038/254 | T2 EI POE-RIO OSO 038/254 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-04-12 | 2021-04-12 | 2022-01-10 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45106665 | T2 EI POE-RIO OSO 038/254 RPR FOND | ICQ
LC | 120796790 | 038/253 | T2 EI POE-RIO OSO 038/253 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-04-12 | 2021-04-12 | 2022-01-11 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45106663 | T2 EI POE-RIO OSO 038/253 RPR FOND | ICQ
LC | 120796822 | 008/047 | T2 DI STNISLS-MANTECA #2 8/47 RPR FND | VICTOR | ETL.3820.TOWR | 2021-04-12 | 2021-04-06 | 2022-01-21 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45122113 | T2 DI STNISLS-MANTECA #2 8/47 RPR FND | ICQ
LC | 120796827 | 005/034 | T2 DI STANISLAUS-MNTC #2 5/34 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-12 | 2021-04-09 | 2022-01-24 | 2022-04-09 | 2022-04-09 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45119926 | T2 DI STANISLAUS-MNTC #2 5/34 RPR FOND | ICQ
LC | 120797464 | 038/251 | T2 EI POE-RIO OSO 038/251 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-04-12 | 2021-04-12 | 2022-01-06 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45106661 | T2 EI POE-RIO OSO 038/251 RPR FOND | ICQ
LC | 120798096 | 022/161A | T2 EI TRINITY-COTTONWOD 22/161A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2021-04-12 | 2021-04-12 | 2021-10-03 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873817 | T2 EI TRINITY-COTTONWOD 22/161A RPR GYWW | ICW
LC | 120798233 | 015/095 | T2 DI SLS-MLS SS-MTC #1 15/95 RPR SPLS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-09 | 2022-03-04 | 2022-04-09 | 2022-04-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 44978050 | T2 DI SLS-MLS SS-MTC #1 15/95 RPR SPLS | ICS
LC | 120798237 | 015/095 | T2 DI SLS-MLS SS-MTC #1 15/95 RPR STRT | VICTOR | ETL.3830.TOWR | 2021-04-12 | 2021-04-09 | 2022-02-07 | 2022-04-09 | 2022-04-09 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45123054 | T2 DI SLS-MLS SS-MTC #1 15/95 RPR STRT | ICQ
LC | 120798248 | 022/161B | T2 EI TRINITY-COTTONWOD 22/161B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2021-04-12 | 2021-04-12 | 2021-10-03 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873818 | T2 EI TRINITY-COTTONWOD 22/161B RPR GYWW | ICW
LC | 120798339 | 022/161C | T2 EI TRINITY-COTTONWOD 22/161C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2021-04-12 | 2021-04-12 | 2021-10-03 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873819 | T2 EI TRINITY-COTTONWOD 22/161C RPR GYWW | ICW
LC | 120798590 | 001/006 | T2 DI STANISLAUS-MANTECA #2 1/6 RPL SPLS | VICTOR | ETL.3820.INSL.CERA | 2021-04-12 | 2021-04-09 | 2021-12-09 | 2022-04-09 | 2022-04-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Replace | 44977850 | T2 DI STANISLAUS-MANTECA #2 1/6 RPL SPLS | ICS
LC | 120798639 | 001/006 | T2 DI STN ML SW ST-RVRBNK 1/6 INS DAMS | VICTOR | ETL.3840.INSL.CERA | 2021-04-12 | 2021-04-09 | 2022-05-11 | 2022-04-09 | 2022-04-09 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | Missing | Damper-Steel | Install | 45122075 | T2 DI STN ML SW ST-RVRBNK 1/6 INS DAMS | ICS
LC | 120798756 | 032/495 | T2 EI CLAY-MARTEL 32/495 RPR GYWW | VICTOR | ETL.8250.POLE.NWOD | 2021-04-12 | 2021-04-12 | 2021-08-03 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44806260 | T2 EI CLAY-MARTEL 32/495 RPR GYWW | ICW
LC | 120799146 | 005/033 | T2 DI STNSLS-MLNS-MNTC 5/33 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-12 | 2021-04-09 | 2022-01-24 | 2022-04-09 | 2022-04-09 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45119924 | T2 DI STNSLS-MLNS-MNTC 5/33 RPR FOND | ICQ
LC | 120799284 | 005/033 | T2 DI STNSLS-MLNS-MNTC 5/33 RPR SPLS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-09 | 2022-03-03 | 2022-04-09 | 2022-04-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | Missing | Damper-Steel | Install | 44978041 | T2 DI STNSLS-MLNS-MNTC 5/33 RPR SPLS | ICS
LC | 120799373 | 033/500 | T2 EI CLAY-MARTEL 33/500 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-12 | 2021-04-12 | 2022-07-30 | 2022-04-12 | 2022-04-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31547353 | T2 EI CLAY-MARTEL 33/500 RPL STRW | 70Y
LC | 120799847 | 011/054 | T2 DI FULTON-PUEBLO 11/54 RPL INSS | LAKEVLLE | ETL.1600.INSL.NCER | 2021-04-12 | 2021-04-09 | 2022-02-28 | 2022-04-09 | 2022-04-09 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 120799954 | 011/080 | T2 DI VAC-VACVLL-JMSN-NTH 11/80 INS HRDT | LAKEVLLE | ETL.4100.TOWR | 2021-04-12 | 2021-04-12 | 2022-02-02 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45160866 | T2 DI VAC-VACVLL-JMSN-NTH 11/80 INS HRDT | ICQ
LC | 120800017 | 041/269 | T2 EI CRESTA-RIO OSO 41/269 RPL INSS | TABLEMTN | ETL.4590.INSL.CERA | 2021-04-12 | 2021-04-12 | 2022-05-06 | 2022-04-12 | 2022-04-12 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546381 | DI CRESTA-RIO OSO RPL INSS 10TWRS | 93K
LC | 120800037 | 011/054 | T2 DI SLVRD-FLTN JCT 11/54 RPL INSS | LAKEVLLE | ETL.1610.INSL.NCER | 2021-04-12 | 2021-04-09 | 2022-03-15 | 2022-04-09 | 2022-04-09 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536106 | T2 DI SLVRD-FLTN JCT RPL INSS 6TWRS | 93K
LC | 120800141 | 029/439 | T2 EI CLAY-MARTEL 29/439 REPL HRDW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-12 | 2021-04-12 | 2021-07-17 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44806237 | T2 EI CLAY-MARTEL 29/439 REPL HRDW | ICW
LC | 120800143 | 029/439 | T2 EI CLAY-MARTEL 29/439 RPR SPLW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-12 | 2021-04-12 | 2021-07-17 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Splice-Wood | Repair | 44806320 | T2 EI CLAY-MARTEL 29/439 RPR SPLW | ICW
LC | 120800180 | :005/003 | T2 DI BLLT-RVRBNK-MLNS :5/3 RPR GYWW | VICTOR | ETL.1070.POLE.NWOD | 2021-04-12 | 2021-04-12 | 2022-03-08 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45151609 | T2 DI BLLT-RVRBNK-MLNS :5/3 RPR GYWW | ICW
LC | 120800243 | 001/010 | T2 DI STANISLAUS-MANTECA #2 1/10 RPR FND | VICTOR | ETL.3820.TOWR | 2021-04-12 | 2021-04-12 | 2022-01-11 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45119059 | T2 DI STANISLAUS-MANTECA #2 1/10 RPR FND | ICQ
LC | 120800885 | 016/001 | T2 EI LAYTONVILLE-WILLITS 16/1 RPL GYWW | WILLITS | ETL.8360.POLE.NWOD | 2021-04-12 | 2021-04-12 | 2022-10-25 | 2022-04-12 | 2022-04-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45144034 | T2 EI LAYTONVILLE-WILLITS 16/1 RPL GYWW | ICW
LC | 120801237 | 000/022 | T2 EI PINE GROVE TAP 000/022 RPL POLE | VICTOR | ETL.8351.POLE.WOOD | 2021-04-12 | 2021-04-12 | 2022-05-25 | 2022-04-12 | 2022-04-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535895 | T2 EI PINE GROVE TAP 000/022 RPL CRSW | 93E
LC | 120801309 | 005/031 | T2 DI STNSLS-MLNS-MNTC 5/31 RPLC DAMS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-12 | 2022-03-03 | 2022-04-12 | 2022-04-12 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 44977959 | T2 DI STNSLS-MLNS-MNTC 5/31 RPLC DAMS | ICS
LC | 120801581 | 005/031 | T2 DI STNSLS-MLNS-MNTC 5/31 INS STEP | VICTOR | ETL.3830.TOWR | 2021-04-12 | 2021-04-12 | 2022-01-19 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45119920 | T2 DI STNSLS-MLNS-MNTC 5/31 INS STEP | ICQ
LC | 120801659 | 003/022 | T2 DI SLS-MLS SS-MTC #1 3/22 RPR DMPS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-12 | 2022-03-02 | 2022-04-12 | 2022-04-12 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 44977958 | T2 DI SLS-MLS SS-MTC #1 3/22 RPR DMPS | ICS
LC | 120803356 | 002/016 | T2 DI STANISLAUS-MNTC #2 2/16 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-13 | 2021-04-12 | 2022-01-21 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45119066 | T2 DI STANISLAUS-MNTC #2 2/16 RPR FOND | ICQ
LC | 120803366 | 005/030 | T2 DI STN ML SW ST-RVRBNK 5/30 RPR SPLS | VICTOR | ETL.3840.INSL.CERA | 2021-04-13 | 2021-04-09 | 2022-05-11 | 2022-04-09 | 2022-04-09 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 45122076 | T2 DI STN ML SW ST-RVRBNK 5/30 RPR SPLS | ICS
LC | 120803407 | 005/030 | T2 DI STANSLAUS-MANTECA #2 5/30 RPR SPLS | VICTOR | ETL.3820.INSL.CERA | 2021-04-13 | 2021-04-09 | 2021-12-09 | 2022-04-09 | 2022-04-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 44977855 | T2 DI STANSLAUS-MANTECA #2 5/30 RPR SPLS | ICS
LC | 120803554 | 003/021 | T2 DI STNSLS-MLNS-MNTC 3/21 RPR SPLS | VICTOR | ETL.3830.TOWR | 2021-04-13 | 2021-04-12 | 2022-03-02 | 2022-04-12 | 2022-04-12 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 44977957 | T2 DI STNSLS-MLNS-MNTC 3/21 RPR SPLS | ICS
LC | 120803577 | 006/012 | T2 DI BRCBRG JCT-MARPOSA TAP 6/12 RPL PL | FRESNO | ETL.8651.POLE.WOOD | 2021-04-13 | 2021-04-12 | 2022-02-02 | 2022-04-12 | 2022-04-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536316 | T2 DI BRCBRG JCT-MARPOSA TAP 6/12 RPL PL | 70Y
LC | 120803849 | 005/050 | T2 DI PARADISE-TABLE MTN 005/050 RPL HRD | TABLEMTN | ETL.4316.TOWR | 2021-04-13 | 2021-04-12 | 2021-06-09 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44851316 | T2 DI PARADISE-TABLE MTN 005/050 RPL HRD | ICQ
LC | 120803963 | 004/035 | T2 EI VC-VCVLL-JMSN-N 4/35 RPL INSS | LAKEVLLE | ETL.4100.INSL.CERA | 2021-04-13 | 2021-04-13 | 2022-02-24 | 2022-04-13 | 2022-04-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549199 | EI VCA-VCVILE-JMESN-NRTH TO RPL INSS 7TW | 93K
LC | 120804224 | 004/034 | T2 EI VC-VCVLL-JMSN-N 4/34 RPL INSS | LAKEVLLE | ETL.4100.INSL.CERA | 2021-04-13 | 2021-04-13 | 2022-02-24 | 2022-04-13 | 2022-04-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549199 | EI VCA-VCVILE-JMESN-NRTH TO RPL INSS 7TW | 93K
LC | 120804264 | 005/081 | T2 EI CNTRVLL-TBL MTN 5/81 RPR CNDW | TABLEMTN | ETL.6320.INSL.NCER | 2021-04-13 | 2021-04-13 | 2022-04-26 | 2022-04-13 | 2022-04-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Conductor-Wood | Repair | 45197479 | T2 EI CNTRVLL-TBL MTN 5/81 RPR CNDW | ICW
LC | 120804315 | 012/048 | T2 EI DIABLO-MIDWAY #2 012/048 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-04-13 | 2021-04-13 | 2022-05-24 | 2022-04-13 | 2022-04-13 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068533 | T2 EI DIABLO-MIDWAY #2 012/048 RPR GYWS | ICS
LC | 120804401 | 029/191 | T2 DI POE-RIO OSO 29/191 RPLC INSS | TABLEMTN | ETL.5540.INSL | 2021-04-13 | 2021-04-06 | 2022-08-10 | 2022-04-06 | 2022-04-06 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546766 | T2 DI POE-RIO OSO RPL INSS 7 TWRS | 93K
LC | 120804516 | 005/044 | T2 DI PARADISE-TABLE MTN 5/44 RPR FOND | TABLEMTN | ETL.4316.TOWR | 2021-04-13 | 2021-04-13 | 2021-06-07 | 2022-04-13 | 2022-04-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44871401 | T2 DI PARADISE-TABLE MTN 5/44 RPR FOND | ICQ
LC | 120804599 | 005/082 | T2 EI CENTERVLE-TBL MT 5/82 COMPLETE | TABLEMTN | ETL.6320.POLE.NWOD | 2021-04-13 | 2021-04-13 | 2022-04-26 | 2022-04-13 | 2022-04-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Conductor-Wood | Repair | 45197478 | T2 EI CENTERVLE-TBL MT 5/82 RPR CONW | ICW
LC | 120805196 | 013/049 | T2 EI DIABLO-MIDWAY #2 013/049 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-04-13 | 2021-04-13 | 2022-07-28 | 2022-04-13 | 2022-04-13 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068534 | T2 EI DIABLO-MIDWAY #2 013/049 RPR GYWS | ICS
LC | 120805206 | 013/049 | T2 EI DIABLO-MIDWAY #2 013/049 RPR INSS | PISMOBCH | ETL.5970.INSL | 2021-04-13 | 2021-04-13 | 2022-02-17 | 2022-04-13 | 2022-04-13 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB | No Good/Out of Stdrd | Insulator-Steel | Repair | 45068535 | T2 EI DIABLO-MIDWAY #2 013/049 RPR INSS | ICS
LC | 120805544 | 008/053 | T2 DI METCALF-GREEN VALLEY 8/53 INS HRDT | MOSSLNDG | ETL.2540.TOWR | 2021-04-13 | 2021-04-06 | 2021-07-19 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Tower | Install | 44839319 | T2 DI METCALF-GREEN VALLEY 8/53 INS HRDT | ICQ
LC | 120805722 | 018/146 | T2 EI DRUM-RIO OSO #1 18/146 RPR FOND | SACTO | ETL.1420.TOWR | 2021-04-13 | 2021-04-13 | 2022-03-07 | 2022-04-13 | 2022-04-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44752913 | T2 EI DRUM-RIO OSO #1 18/146 RPR FOND | ICQ
LC | 120805731 | 007/045 | T2 DI STANISLAUS-MANTECA #2 7/45 REGRADE | VICTOR | ETL.3820.TOWR | 2021-04-13 | 2021-04-06 | 2022-01-21 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45122109 | T2 DI STANISLAUS-MANTECA #2 7/45 REGRADE | ICQ
LC | 120805800 | 009/081 | T2 DI PRDSE-TBLE MTN 009/081 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-13 | 2021-04-07 | 2021-08-02 | 2022-04-07 | 2022-04-07 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120805834 | 010/043 | T2 EI MR BY-SR SW STA #1 010/043 RPR FON | PISMOBCH | ETL.5300.TOWR | 2021-04-13 | 2021-04-13 | 2022-07-11 | 2022-04-13 | 2022-04-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45073902 | T2 EI MR BY-SR SW STA #1 010/043 RPR FON | ICQ
LC | 120806300 | 006/036 | T2 DI STANISLAUS-MANTCA #2 6/36 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-13 | 2021-04-06 | 2022-01-19 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45119931 | T2 DI STANISLAUS-MANTCA #2 6/36 RPR FOND | ICQ
LC | 120806791 | 021/166 | T2 EI PARADISE-TBLE MTN 21/166L RPR STRW | TABLEMTN | ETL.4316.POLE.STPS | 2021-04-13 | 2021-04-13 | 2022-05-17 | 2022-04-13 | 2022-04-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45200444 | T2 EI PARADISE-TBLE MTN 21/166L RPR STRW | ICW
LC | 120806904 | 010/044 | T2 EI MR BY-SLR SW STA #1 10/44 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-13 | 2021-04-13 | 2022-06-14 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31529344 | T3 EI MRRO BY-SLR SWST#1 RPL INS 21TWR | 93K
LC | 120806906 | 010/044 | T2 EI MR BY-SLR SW STA #2 10/44 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-13 | 2021-04-13 | 2022-07-14 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31550476 | T2 EI MR BY-SLR SW STA #2 RPL INSS 5 TW | 93K
LC | 120806961 | 021/166 | T2 EI PARADISE-TBLE MTN 21/166 RPR DAMPW | TABLEMTN | ETL.4316.INSL.NCER | 2021-04-13 | 2021-04-13 | 2022-05-17 | 2022-04-13 | 2022-04-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Damper-Wood | Replace | 44860252 | T2 EI PARADISE-TBLE MTN 21/166 RPR DAMPW | ICW
LC | 120806965 | :004/004 | T2 DI BLT-RVRBNK-MLNS :4/4 RPR STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-04-13 | 2021-04-12 | 2021-06-16 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 44960722 | T2 DI BLT-RVRBNK-MLNS :4/4 RPR STRW | ICW
LC | 120807074 | 021/166 | T2 EI PARADISE-TBLE MTN 21/166R RPL GYWW | TABLEMTN | ETL.4316.POLE.STPS | 2021-04-13 | 2021-04-13 | 2021-07-31 | 2022-04-13 | 2022-04-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44860253 | T2 EI PARADISE-TBLE MTN 21/166R RPL GYWW | ICW
LC | 120807387 | 005/046 | T2 DI PARADISE-TABLE MTN 005/046 RPR FON | TABLEMTN | ETL.4316.TOWR | 2021-04-13 | 2021-04-12 | 2021-06-09 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44861524 | T2 DI PARADISE-TABLE MTN 005/046 RPR FON | ICQ
LC | 120807629 | 002/015 | T2 DI STNSLS-MLNS-MNTC 2/15 RPR INSS | VICTOR | ETL.3830.INSL | 2021-04-13 | 2021-04-12 | 2022-03-01 | 2022-04-12 | 2022-04-12 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44977954 | T2 DI STNSLS-MLNS-MNTC 2/15 RPR INSS | ICS
LC | 120807761 | 016/138 | T2 EI DRUM-RIO OSO #1 16/138 RPR FOND | SACTO | ETL.1420.TOWR | 2021-04-13 | 2021-04-13 | 2022-03-07 | 2022-04-13 | 2022-04-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44752914 | T2 EI DRUM-RIO OSO #1 16/138 RPR FOND | ICQ
LC | 120807878 | 011/046 | T2 EI MR BY-SL SW STA #1 11/046 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-13 | 2021-04-13 | 2022-06-14 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31529344 | T3 EI MRRO BY-SLR SWST#1 RPL INS 21TWR | 93K
LC | 120807966 | 016/137 | T2 EI DRUM-RIO OSO #1 16/137 COMPLETE | SACTO | ETL.1420.TOWR | 2021-04-13 | 2021-04-13 | 2022-05-23 | 2022-04-13 | 2022-04-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44752912 | T2 EI DRUM-RIO OSO #1 16/137 RPR FOND | ICQ
LC | 120808145 | 011/047 | T2 EI MR BY-SR SW STA #1 11/047 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-13 | 2021-04-13 | 2022-06-15 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31529344 | T3 EI MRRO BY-SLR SWST#1 RPL INS 21TWR | 93K
LC | 120808170 | 011/047 | T2 EI MR BY-SR SW STA #2 11/047 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-13 | 2021-04-13 | 2022-07-14 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528622 | EI MORRO BAY-SOLAR SS#2 RPL INS 8WR | 93K
LC | 120808172 | 010/087 | T2 EI PARADISE-TABLE MTN 10/087 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-13 | 2021-04-13 | 2021-07-17 | 2022-04-13 | 2022-04-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120808173 | :024/127 | T2 EI CHC-SALINAS-SOLE :23/127 RPR FOND | MOSSLNDG | ETL.2900.TOWR | 2021-04-13 | 2021-04-13 | 2021-07-08 | 2022-04-13 | 2022-04-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44839760 | T2 EI CHC-SALINAS-SOLE :23/127 RPR FOND | ICQ
LC | 120808360 | 012/048 | T2 EI MR BY-SLR SW STA #1 12/48 RMV BRSH | PISMOBCH | ETL.5300.TOWR | 2021-04-13 | 2021-04-13 | 2021-06-01 | 2022-04-13 | 2022-04-13 | On-time | 932 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Brush Fuel | Road | Remove | 44598153 | T3NT MORRO BY-SLR SS #1 24/105 RPR ROAD | CHS
LC | 120808670 | 032/135 | T2 EI TESLA-METCALF 32/135 RPR FOND | METCALF | ETL.6110.TOWR | 2021-04-13 | 2021-04-13 | 2021-05-20 | 2022-04-13 | 2022-04-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44809775 | T2 EI TESLA-METCALF 32/135 RPR FOND | ICQ
LC | 120808721 | 027/133 | T2 WV CRNA MNDCNO 31 27/133 RPR FOND | LAKEVLLE | ETL.1330.TOWR | 2021-04-13 | 2021-04-13 | 2022-01-26 | 2022-04-13 | 2022-04-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45107513 | T2 WV CRNA MNDCNO 31 27/133 RPR FOND | ICQ
LC | 120808867 | 051/254 | T2 EI MLN-RND MTN #2 051/254 BENT STEEL | TABLEMTN | ETL.6020.TOWR | 2021-04-13 | 2021-04-13 | 2022-08-04 | 2022-04-13 | 2022-04-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45193982 | T2 EI MLN-RND MTN #2 051/254 BENT STEEL | ICQ
LC | 120808906 | 011/010 | T2 WV TULE-SPRINGVILLE 011/010 INS DAMW | MIDWAY | ETL.9040.SWIT | 2021-04-13 | 2021-04-13 | 2022-06-02 | 2022-04-13 | 2022-04-13 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install | 45068041 | T2 WV TULE-SPRINGVILLE 011/010 INS DAMW | ICS
LC | 120810538 | :002/019 | T2 EI PIT #3-PIT #1 :002/019 RPR FOND | TABLEMTN | ETL.5400.TOWR | 2021-04-14 | 2021-04-13 | 2022-07-29 | 2022-04-13 | 2022-04-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195435 | T2 EI PIT #3-PIT #1 :002/019 RPR FOND | ICQ
LC | 120810796 | 031/007 | T2 EI GRBRVLL-LYTNVILLE 31/7 RPL INSW | WILLITS | ETL.8365.INSL.CERA | 2021-04-14 | 2021-04-12 | 2022-04-22 | 2022-04-12 | 2022-04-12 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542897 | T2 EI GRBRVLL-LYTNVILLE 31/7 RPL INSW | 93I
LC | 120810798 | 031/005 | T2 EI GRBRVLL-LYTNVILLE 31/5 RPR GYWW | WILLITS | ETL.8365.POLE.WOOD | 2021-04-14 | 2021-04-12 | 2022-04-22 | 2022-04-12 | 2022-04-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44754996 | T2 EI GRBRVLL-LYTNVILLE 31/5 RPR GYWW | ICW
LC | 120810831 | 030/005 | T2 EI GRBRVLL-LYTNVILLE 30/5 RPL STRW | WILLITS | ETL.8365.POLE.WOOD | 2021-04-14 | 2021-04-12 | 2022-05-14 | 2022-04-12 | 2022-04-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535915 | T2 EI GRBRVLE-LYTNVILE 23/1 RPL PL | 70Y
LC | 120810841 | 001/012 | T2 DI STAN MEL-RVRBNK JCT 1/12 RPR SPLS | VICTOR | ETL.3840.INSL.CERA | 2021-04-14 | 2021-04-13 | 2022-05-11 | 2022-04-13 | 2022-04-13 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122077 | T2 DI STAN MEL-RVRBNK JCT 1/12 RPR SPLS | ICS
LC | 120810847 | 001/011 | T2 DI STNS MLNS-RVRBNK JCT 1/11 RPR SPLS | VICTOR | ETL.3840.INSL.CERA | 2021-04-14 | 2021-04-13 | 2022-05-11 | 2022-04-13 | 2022-04-13 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122078 | T2 DI STAN MEL-RVRBNK JCT 1/11 RPR SPLS | ICS
LC | 120810896 | 001/011 | T2 DI STANISLAUS-MANTEC #2 1/11 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-14 | 2021-04-13 | 2022-01-27 | 2022-04-13 | 2022-04-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45119047 | T2 DI STANISLAUS-MANTEC #2 1/11 RPR FOND | ICQ
LC | 120810986 | 050/360 | T2 DI CARIBOU-TABLE MTN 50/360 RPLC INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-04-14 | 2021-04-13 | 2022-06-16 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 120810991 | 007/059 | T2 DI EL DRDO-MSSR FLT #2 7/59 RPL INSS | SACTO | ETL.1540.INSL | 2021-04-14 | 2021-04-13 | 2022-05-18 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547631 | T2 WV EL DORADO-MSR FLT #2 RPL INSS 10TW | 93K
LC | 120810995 | 007/059 | T2 DI EL DRDO-MSSR FLT #1 7/59 REPL INSS | SACTO | ETL.1530.INSL | 2021-04-14 | 2021-04-13 | 2022-06-15 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535732 | T2 DI ELDRD-MSSRI FLT #1 RPL INSS 10TWRS | 93K
LC | 120811085 | 007/058 | T2 DI EL DRDO-MSSR FLT #1 7/58 RPR SPLS | SACTO | ETL.1530.INSL | 2021-04-14 | 2021-04-13 | 2022-06-15 | 2022-04-13 | 2022-04-13 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 44752944 | T2 DI EL DRDO-MSSR FLT #1 7/58 RPR SPLS | ICS
LC | 120811545 | 006/044 | T2 DI KRKF-CLVS-SNGR #1 6/44 FOND CMPLTD | FRESNO | ETL.1890.TOWR | 2021-04-14 | 2021-04-01 | 2022-06-03 | 2022-04-01 | 2022-04-01 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45069185 | T2 DI KRCKHFF-CLVS-SNGR #1 6/44 RPR FOND | ICQ
LC | 120811684 | T003/005 | T2 TULUCAY-NAPA #1 T003/005 RPR STRW | LAKEVLLE | ETL.8180.POLE.WOOD | 2021-04-14 | 2021-04-14 | 2021-08-22 | 2022-04-14 | 2022-04-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44877514 | T2 TULUCAY-NAPA #1 T003/005 RPR STRW | ICW
LC | 120812244 | 017/073 | T2 EI MRR BY-SLR #2 17/73 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-14 | 2021-04-14 | 2022-07-12 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548992 | T2 EI MRR BY-SLR SW #2 RPL INSS 10TWRS | 93K
LC | 120812311 | 017/073 | T2 EI MRR BY-SLR SW ST #1 17/73 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-14 | 2021-04-14 | 2022-06-16 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31529344 | T3 EI MRRO BY-SLR SWST#1 RPL INS 21TWR | 93K
LC | 120812312 | 017/074 | T2 EI MRR BY-SLR #2 17/74 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-14 | 2021-04-14 | 2022-07-11 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548992 | T2 EI MRR BY-SLR SW #2 RPL INSS 10TWRS | 93K
LC | 120812313 | 017/074 | T2 EI MRR BY-SLR SW ST #1 17/74 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-14 | 2021-04-14 | 2022-05-16 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31529344 | T3 EI MRRO BY-SLR SWST#1 RPL INS 21TWR | 93K
LC | 120812344 | 017/075 | T2 EI MRR BY-SLR #2 17/75 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-14 | 2021-04-14 | 2022-07-11 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548992 | T2 EI MRR BY-SLR SW #2 RPL INSS 10TWRS | 93K
LC | 120812345 | 017/075 | T2 EI MRR BY-SLR SW ST #1 17/75 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-14 | 2021-04-14 | 2022-06-15 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31529344 | T3 EI MRRO BY-SLR SWST#1 RPL INS 21TWR | 93K
LC | 120812741 | 011/094 | T2 EI PARADISE-TABLE MTN 11/94 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-14 | 2021-04-14 | 2021-07-18 | 2022-04-14 | 2022-04-14 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120813000 | :023/122 | T2 DI CRZY HS CYN-SLS-SLD :23/122 RPL RG | MOSSLNDG | ETL.2900.TOWR | 2021-04-14 | 2021-04-13 | 2021-05-26 | 2022-04-13 | 2022-04-13 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44805760 | T2 DI CRZY HS CYN-SLS-SLD :23/122 RPL RG | ICB
LC | 120813034 | 011/095 | T2 EI PARADISE-TABLE MTN 11/095 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-14 | 2021-04-14 | 2021-07-18 | 2022-04-14 | 2022-04-14 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120813159 | 017/072 | T2 EI MRR BY-SLR #2 17/72 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-14 | 2021-04-14 | 2022-07-14 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548992 | T2 EI MRR BY-SLR SW #2 RPL INSS 10TWRS | 93K
LC | 120813206 | 017/076 | T2 EI MRR BY-SLR SW ST #1 17/76 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-14 | 2021-04-14 | 2022-06-15 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31529344 | T3 EI MRRO BY-SLR SWST#1 RPL INS 21TWR | 93K
LC | 120813207 | 017/076 | EI T2 MRR BY-SLR SW ST #2 17/76 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-14 | 2021-04-14 | 2022-07-11 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548992 | T2 EI MRR BY-SLR SW #2 RPL INSS 10TWRS | 93K
LC | 120813230 | 017/072 | T2 EI MRR BY-SLR SW ST #1 17/72 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-14 | 2021-04-14 | 2022-06-16 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31529344 | T3 EI MRRO BY-SLR SWST#1 RPL INS 21TWR | 93K
LC | 120813265 | 016/071 | T2 EI MRR BY-SLR SW ST #1 16/71 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-14 | 2021-04-14 | 2022-06-16 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31529344 | T3 EI MRRO BY-SLR SWST#1 RPL INS 21TWR | 93K
LC | 120813276 | 016/071 | T2 EI MRR BY-SLR #2 16/71 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-14 | 2021-04-14 | 2022-07-12 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548992 | T2 EI MRR BY-SLR SW #2 RPL INSS 10TWRS | 93K
LC | 120813437 | 016/070 | T2 EI MRR BY-SLR SW #2 16/70 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-14 | 2021-04-14 | 2022-07-14 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548992 | T2 EI MRR BY-SLR SW #2 RPL INSS 10TWRS | 93K
LC | 120813600 | 001/064 | T2 EI SPLDNG-SMMT 1/64 REFRAME | SACTO | ETL.8060.POLE.WOOD | 2021-04-14 | 2021-04-14 | 2021-08-29 | 2022-04-14 | 2022-04-14 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31537117 | T2 EI SPLDNG-SMMT 1/64 REFRAME | 93E
LC | 120813813 | 001/012A | T2 EI CHOWCHILL-KRCKHFF 1/12A RPL INSS | FRESNO | ETL.1250.INSL.NCER | 2021-04-14 | 2021-04-14 | 2022-02-16 | 2022-04-14 | 2022-04-14 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514611 | T2 DI CHOWCHILLA-KERCKHOFF RPL INSS 12TW | 93K
LC | 120813890 | 007/041 | T2 DI STANISLAUS-MANTECA #2 7/41 RPR FON | VICTOR | ETL.3820.TOWR | 2021-04-14 | 2021-04-06 | 2022-01-24 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45122103 | T2 DI STANISLAUS-MANTECA #2 7/41 RPR FON | ICQ
LC | 120813894 | 007/041 | T2 DI STNISLS-MANTCA #2 7/41 BENT STL | VICTOR | ETL.3820.TOWR | 2021-04-14 | 2021-04-06 | 2022-01-24 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45119922 | T2 DI STNISLS-MANTCA #2 7/41 BENT STL | ICQ
LC | 120814048 | 011/097 | T2 EI PARADISE-TABLE MTN 11/097 RMV VEG | TABLEMTN | ETL.4316.TOWR | 2021-04-14 | 2021-04-14 | 2022-01-13 | 2022-04-14 | 2022-04-14 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120814272 | 011/098 | T2 EI PARADISE-TABLE MTN 11/098 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-14 | 2021-04-14 | 2021-07-18 | 2022-04-14 | 2022-04-14 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120814479 | 010/173 | T2 EI TEJON-LEBEC 10/173 RPR SPLW | MIDWAY | ETL.9250.INSL.NCER | 2021-04-14 | 2021-04-14 | 2021-08-05 | 2022-04-14 | 2022-04-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Repair | 44817789 | T2 DI TEJON-LEBEC 10/167 RPR SPLW | ICW
LC | 120814592 | 013/077 | T2 DI STNSLUS-MNTCA #2 13/77 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-14 | 2021-04-06 | 2022-02-02 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45122671 | T2 DI STNSLUS-MNTCA #2 13/77 RPR FOND | ICQ
LC | 120814600 | 012/099 | T2 EI PRDSE-TBLE MTN 12/99 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-14 | 2021-04-14 | 2021-07-18 | 2022-04-14 | 2022-04-14 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120814657 | 000/001 | T2 EI CHOWCHILLA-KERCKHOFF 0/1 RPL INSS | FRESNO | ETL.1250.INSL.NCER | 2021-04-14 | 2021-04-14 | 2022-02-15 | 2022-04-14 | 2022-04-14 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514611 | T2 DI CHOWCHILLA-KERCKHOFF RPL INSS 12TW | 93K
LC | 120814658 | 018/372 | T2 EI COLGATE-PALERMO 18/372 RPR STRW | TABLEMTN | ETL.6500.POLE.WOOD | 2021-04-14 | 2021-04-14 | 2021-08-20 | 2022-04-14 | 2022-04-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44753076 | T2 EI COLGATE-PALERMO 18/372 RPR STRW | ICW
LC | 120814664 | 000/001 | T2 EI CHOWCHILLA-KERCKHOFF 0/1 REGRADE | FRESNO | ETL.1250.POLE.NWOD | 2021-04-14 | 2021-04-14 | 2022-02-14 | 2022-04-14 | 2022-04-14 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45069187 | T2 EI CHOWCHILLA-KERCKHOFF 0/1 REGRADE | ICQ
LC | 120814739 | 016/068 | T2 EI MRR BY-SLR SW ST #1 16/68 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-14 | 2021-04-14 | 2022-06-16 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31529344 | T3 EI MRRO BY-SLR SWST#1 RPL INS 21TWR | 93K
LC | 120814743 | 016/068 | T2 EI MRR BY-SLR SW #2 16/68 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-14 | 2021-04-14 | 2022-07-14 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548992 | T2 EI MRR BY-SLR SW #2 RPL INSS 10TWRS | 93K
LC | 120815370 | 012/089 | T2 EI WISHON-COPPERMINE 012/089 UNBURY | FRESNO | ETL.9330.TOWR | 2021-04-14 | 2021-04-14 | 2021-07-01 | 2022-04-14 | 2022-04-14 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44839761 | T2 EI WISHON-COPPERMINE 012/089 UNBURY | ICQ
LC | 120815419 | 002/007 | T2 EI RIO DELL TAP 002/007 RPL INSW | EUREKA | ETL.7851.INSL | 2021-04-14 | 2021-04-14 | 2022-06-25 | 2022-04-14 | 2022-04-14 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537167 | T2 EI RIO DELL TAP 002/004 RPL INSW | 93I
LC | 120815420 | 002/004 | T2 EI RIO DELL TAP 002/004 RPL INSW CPLT | EUREKA | ETL.7851.POLE.WOOD | 2021-04-14 | 2021-04-14 | 2022-06-26 | 2022-04-14 | 2022-04-14 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537167 | T2 EI RIO DELL TAP 002/004 RPL INSW | 93I
LC | 120815474 | 015/060 | T2 EI DIABLO-MIDWAY #3 015/060 RPR GYWS | PISMOBCH | ETL.5980.TOWR | 2021-04-14 | 2021-04-14 | 2022-05-31 | 2022-04-14 | 2022-04-14 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068584 | T2 EI DIABLO-MIDWAY #3 015/060 RPR GYWS | ICS
LC | 120815505 | 015/060 | T2 EI DIABLO-MIDWAY #2 015/060 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-04-14 | 2021-04-14 | 2022-05-25 | 2022-04-14 | 2022-04-14 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068538 | T2 EI DIABLO-MIDWAY #2 015/060 RPR GYWS | ICS
LC | 120815565 | 005/068 | T2 EI BURNS-LONE STAR #1 5/68 RPL HRDW | MOSSLNDG | ETL.6230.POLE.WOOD | 2021-04-14 | 2021-04-14 | 2021-08-26 | 2022-04-14 | 2022-04-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44805761 | T2 EI BURNS-LONE STAR #1 5/68 RPL HRDW | ICW
LC | 120815729 | 001/039 | T2 PINE GROVE TAP 1/039 RPR GYWW | VICTOR | ETL.8351.POLE.WOOD | 2021-04-14 | 2021-04-14 | 2021-06-22 | 2022-04-14 | 2022-04-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44886344 | T2 PINE GROVE TAP 1/039 RPR GYWW | ICW
LC | 120815896 | 003/031 | T2 EI VAC-VCVILLE-JMSN-NTH 3/31 RMV VEG | LAKEVLLE | ETL.4100.TOWR | 2021-04-14 | 2021-04-14 | 2022-05-23 | 2022-04-14 | 2022-04-14 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120815971 | 012/100 | T2 EI PARADISE-TABLE MTN 12/100 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-14 | 2021-04-14 | 2021-07-19 | 2022-04-14 | 2022-04-14 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120815978 | 014/107 | T2 EI SLT SPRNGS-TGR CRK 14/107 RMV STEP | VICTOR | ETL.3500.TOWR | 2021-04-14 | 2021-04-14 | 2022-03-29 | 2022-04-14 | 2022-04-14 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45150393 | T2 EI SLT SPRNGS-TGR CRK 14/107 RMV STEP | ICQ
LC | 120816028 | 024/187B | T2 EI PRADISE-TABLE MTN 24/187B RPR ANCW | TABLEMTN | ETL.4316.POLE.NWOD | 2021-04-14 | 2021-04-14 | 2021-11-12 | 2022-04-14 | 2022-04-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 44860254 | T2 EI PRADISE-TABLE MTN 24/187B RPR ANCW | ICW
LC | 120816207 | 013/101 | T2 EI SLT SPRGS-TGR CRK 13/101 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-14 | 2021-04-14 | 2022-06-27 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31526477 | T3 DI DSLT SPGS-TGR CRK RPLC INSS 2TWR | 93K
LC | 120817467 | 017/088 | T2 VACA-PARKWAY 17/88 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-14 | 2021-04-14 | 2021-11-18 | 2022-04-14 | 2022-04-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757553 | T2 VACA-PARKWAY 17/88 RPL SHLS | ICS
LC | 120817468 | 017/089 | T2 VACA-PARKWAY 17/89 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-14 | 2021-04-14 | 2021-10-13 | 2022-04-14 | 2022-04-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757257 | T2 VACA-PARKWAY 17/89 RPL SHLS | ICS
LC | 120817469 | 017/090 | T2 VACA-PARKWAY 17/90 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-14 | 2021-04-14 | 2021-10-13 | 2022-04-14 | 2022-04-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757250 | T2 VACA-PARKWAY 17/90 RPL SHLS | ICS
LC | 120817512 | 018/093 | T2 VACA-PARKWAY 18/93 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-14 | 2021-04-14 | 2021-10-12 | 2022-04-14 | 2022-04-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757396 | T2 VACA-PARKWAY 18/93 RPL SHLS | ICS
LC | 120817513 | 019/098 | T2 VACA-PARKWAY 019/098 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-14 | 2021-04-14 | 2021-10-08 | 2022-04-14 | 2022-04-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44752957 | T2 VACA-PARKWAY 019/098 RPR SHLS | ICS
LC | 120817540 | 017/091 | T2 VACA-PARKWAY 17/91 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-14 | 2021-04-14 | 2021-10-13 | 2022-04-14 | 2022-04-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757385 | T2 VACA-PARKWAY 17/91 RPL SHLS | ICS
LC | 120817541 | 017/092 | T2 VACA-PARKWAY 17/92 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-14 | 2021-04-14 | 2021-10-12 | 2022-04-14 | 2022-04-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757283 | T2 VACA-PARKWAY 17/92 RPL SHLS | ICS
LC | 120817542 | 018/094 | T2 VACA-PARKWAY 18/94 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-14 | 2021-04-14 | 2021-10-12 | 2022-04-14 | 2022-04-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757393 | T2 VACA-PARKWAY 18/94 RPL SHLS | ICS
LC | 120817543 | 018/095 | T2 VACA-PARKWAY 18/95 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-14 | 2021-04-14 | 2021-10-12 | 2022-04-14 | 2022-04-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757541 | T2 VACA-PARKWAY 18/95 RPL SHLS | ICS
LC | 120817544 | 018/096 | T2 VACA-PARKWAY 018/096 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-14 | 2021-04-14 | 2021-10-12 | 2022-04-14 | 2022-04-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44752956 | T2 VACA-PARKWAY 018/096 RPR SHLS | ICS
LC | 120817546 | 018/097 | T2 VACA-PARKWAY 018/097 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-14 | 2021-04-14 | 2021-11-19 | 2022-04-14 | 2022-04-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44752958 | T2 VACA-PARKWAY 018/097 RPR SHLS | ICS
LC | 120817547 | 019/099 | T2 VACA-PARKWAY 019/099 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-14 | 2021-04-14 | 2021-10-08 | 2022-04-14 | 2022-04-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44752954 | T2 VACA-PARKWAY 019/099 RPR SHLS | ICS
LC | 120818894 | 053/375 | T2 DI CRBU-TBL MTN 53/375 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-04-15 | 2021-04-14 | 2022-06-16 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 120819621 | 008/061 | T2 DI EL DRD-MSSR FLT #2 8/61 RPL INSS | SACTO | ETL.1540.INSL | 2021-04-15 | 2021-04-14 | 2022-05-18 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547631 | T2 WV EL DORADO-MSR FLT #2 RPL INSS 10TW | 93K
LC | 120819622 | 008/061 | T2 DI EL DRD-MSSR FLT #1 8/61 RPR SPLS | SACTO | ETL.1530.INSL | 2021-04-15 | 2021-04-14 | 2022-06-14 | 2022-04-14 | 2022-04-14 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 44752943 | T2 DI EL DRD-MSSR FLT #1 8/61 RPR SPLS | ICS
LC | 120819718 | 035/297 | T2 EI PIT #1-CTTNWOOD 035/297 RPR GYWS | TABLEMTN | ETL.5390.TOWR | 2021-04-15 | 2021-04-15 | 2022-03-07 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45166845 | T2 EI PIT #1-CTTNWOOD 035/297 RPR GYWS | ICS
LC | 120819798 | 008/151 | T2 EI TEJON-LEBEC 008/151 RPR GYWW | MIDWAY | ETL.9250.POLE.NWOD | 2021-04-15 | 2021-04-15 | 2021-08-12 | 2022-04-15 | 2022-04-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44809659 | T2 EI TEJON-LEBEC 008/151 RPR GYWW | ICW
LC | 120820035 | C021/086 | T2 EI MSS LNDING-CBURN C021/086 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-04-15 | 2021-04-15 | 2022-03-15 | 2022-04-15 | 2022-04-15 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45118714 | T2 EI MSS LNDING-CBURN C021/086 RPR FOND | ICQ
LC | 120820095 | 000/026 | T2 EI SPAULDING-SUMMIT 0/26 REFRAME | SACTO | ETL.8060.POLE.WOOD | 2021-04-15 | 2021-04-15 | 2021-08-19 | 2022-04-15 | 2022-04-15 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31537117 | T2 EI SPLDNG-SMMT 1/64 REFRAME | 93E
LC | 120820354 | 017/355 | T2 EI COLGATE-PALERMO 17/355 RPR STRW | TABLEMTN | ETL.6500.POLE.WOOD | 2021-04-15 | 2021-04-15 | 2021-08-20 | 2022-04-15 | 2022-04-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44753075 | T2 EI COLGATE-PALERMO 17/355 RPR STRW | ICW
LC | 120820387 | 022/163 | T2 EI TRINITY-CTONWD 22/163 RPL ANCW | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-15 | 2021-04-15 | 2022-08-05 | 2022-04-15 | 2022-04-15 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31537118 | T2 EI TRINITY-CTONWD 22/163 RPL ANCW | 93E
LC | 120820461 | 022/163 | T2 EI TRINITY-CTONWD 22/163 RPL ANCW | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-15 | 2021-04-15 | 2022-08-05 | 2022-04-15 | 2022-04-15 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31541591 | T2 EI TRINITY-CTONWD 22/163 RPL ANCW | 93E
LC | 120820497 | 022/163 | T2 EI TRINITY-CTONWD 22/163 RPL ANCW | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-15 | 2021-04-15 | 2022-08-05 | 2022-04-15 | 2022-04-15 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31541591 | T2 EI TRINITY-CTONWD 22/163 RPL ANCW | 93E
LC | 120820713 | 000/032 | T2 EI SPAULDING-SUMMIT 0/32 RPR STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-15 | 2021-04-15 | 2021-08-19 | 2022-04-15 | 2022-04-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44764624 | T2 EI SPAULDING-SUMMIT 0/32 RPR STRW | ICW
LC | 120820746 | 009/082 | T2 DI PARADISE-TABLE MTN 9/82 RPLC INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-15 | 2021-04-09 | 2021-07-17 | 2022-04-09 | 2022-04-09 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120820802 | C021/085 | T2 EI MOSS LNDING-CBRN C021/085 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-04-15 | 2021-04-15 | 2022-03-15 | 2022-04-15 | 2022-04-15 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44757020 | T2 EI MOSS LNDING-CBRN C021/085 RPR FOND | ICQ
LC | 120821304 | 004/042 | T2 WV BRDGEVLLE-CTTNWD 4/42L RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2021-04-15 | 2021-04-15 | 2021-06-29 | 2022-04-15 | 2022-04-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44873801 | T2 WV BRDGEVLLE-CTTNWD 4/42L RPR ADSS | ICW
LC | 120821358 | 015/064 | T2 DI MORRO BAY-SOLAR #1 15/64 RPR FOND | PISMOBCH | ETL.5300.TOWR | 2021-04-15 | 2021-04-09 | 2022-06-07 | 2022-04-09 | 2022-04-09 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45073907 | T2 DI MORRO BAY-SOLAR #1 15/64 RPR FOND | ICQ
LC | 120821416 | 014/077 | T2 VACA-PARKWAY 14/77 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-15 | 2021-04-15 | 2021-11-18 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757228 | T2 VACA-PARKWAY 14/77 RPL SHLS | ICS
LC | 120821418 | 015/079 | T2 VACA-PARKWAY 15/79 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-15 | 2021-04-15 | 2021-10-21 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44756807 | T2 VACA-PARKWAY 15/79 RPL SHLS | ICS
LC | 120821428 | 015/080 | T2 VACA-PARKWAY 15/80 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-15 | 2021-04-15 | 2021-11-18 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44756805 | T2 VACA-PARKWAY 15/80 RPL SHLS | ICS
LC | 120821429 | 015/081 | T2 VACA-PARKWAY 15/81 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-15 | 2021-04-15 | 2021-11-18 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757190 | T2 VACA-PARKWAY 15/81 RPL SHLS | ICS
LC | 120821461 | 015/078 | T2 VACA-PARKWAY 15/78 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-15 | 2021-04-15 | 2021-10-12 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757246 | T2 VACA-PARKWAY 15/78 RPL SHLS | ICS
LC | 120821463 | 016/083 | T2 VACA-PARKWAY 16/83 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-15 | 2021-04-15 | 2021-11-18 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757220 | T2 VACA-PARKWAY 16/83 RPL SHLS | ICS
LC | 120821465 | 016/084 | T2 VACA-PARKWAY 16/84 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-15 | 2021-04-15 | 2021-11-18 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757221 | T2 VACA-PARKWAY 16/84 RPL SHLS | ICS
LC | 120821472 | 016/087 | T2 VACA-PARKWAY 16/87 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-15 | 2021-04-15 | 2021-10-12 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757247 | T2 VACA-PARKWAY 16/87 RPL SHLS | ICS
LC | 120821490 | 016/082 | T2 VACA-PARKWAY 16/82 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-15 | 2021-04-15 | 2021-11-18 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44756811 | T2 VACA-PARKWAY 16/82 RPL SHLS | ICS
LC | 120821491 | 016/085 | T2 VACA-PARKWAY 16/85 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-15 | 2021-04-15 | 2021-10-13 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757223 | T2 VACA-PARKWAY 16/85 RPL SHLS | ICS
LC | 120821505 | 016/086 | T2 VACA-PARKWAY 16/86 RPL SHLS | LAKEVLLE | ETL.5850.TOWR | 2021-04-15 | 2021-04-15 | 2021-10-13 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44757225 | T2 VACA-PARKWAY 16/86 RPL SHLS | ICS
LC | 120821608 | 028/188 | T2 DI POE-RIO OSO 28/188 RPLC INSS | TABLEMTN | ETL.5540.INSL | 2021-04-15 | 2021-04-09 | 2022-08-10 | 2022-04-09 | 2022-04-09 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546766 | T2 DI POE-RIO OSO RPL INSS 7 TWRS | 93K
LC | 120821840 | 009/156 | T2 EI TEJON-LEBEC 009/156 RPR GYWW | MIDWAY | ETL.9250.POLE.NWOD | 2021-04-15 | 2021-04-15 | 2021-08-07 | 2022-04-15 | 2022-04-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44818019 | T2 EI TEJON-LEBEC 009/156 RPR GYWW | ICW
LC | 120822038 | 023/167B | T2 EI TRINITY-CTONWD 23/167B RPL ANCW | TABLEMTN | ETL.4040.POLE.NWOD | 2021-04-15 | 2021-04-15 | 2021-09-03 | 2022-04-15 | 2022-04-15 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31541591 | T2 EI TRINITY-CTONWD 22/163 RPL ANCW | 93E
LC | 120822039 | 023/167A | T2 EI TRINITY-CTONWD 23/167A RPL ANCW | TABLEMTN | ETL.4040.POLE.NWOD | 2021-04-15 | 2021-04-15 | 2021-09-03 | 2022-04-15 | 2022-04-15 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31541591 | T2 EI TRINITY-CTONWD 22/163 RPL ANCW | 93E
LC | 120822370 | 003/119 | T2 EI SPLDNG-SMMT 3/119 REFRAME | SACTO | ETL.8060.POLE.WOOD | 2021-04-15 | 2021-04-15 | 2021-08-14 | 2022-04-15 | 2022-04-15 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31537117 | T2 EI SPLDNG-SMMT 1/64 REFRAME | 93E
LC | 120822845 | 004/055 | T2 EI BURNS-LONE STAR #1 4/55 RPR GYWW | MOSSLNDG | ETL.6230.POLE.NWOD | 2021-04-15 | 2021-04-15 | 2021-06-18 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 44805762 | T2 EI BURNS-LONE STAR #1 4/55 RPR GYWW | ICS
LC | 120823047 | 009/160 | T2 EI TEJON-LEBEC 9/160 RPR SPLW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-15 | 2021-04-15 | 2021-08-17 | 2022-04-15 | 2022-04-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Splice-Wood | Repair | 44818164 | T2 EI TEJON-LEBEC 9/160 RPR SPLW | ICW
LC | 120823456 | 009/161 | T2 EI TEJON-LEBEC 9/161 RPR STRW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-15 | 2021-04-15 | 2021-08-25 | 2022-04-15 | 2022-04-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44960691 | T2 EI TEJON-LEBEC 9/161 RPR STRW | ICW
LC | 120823787 | 017/067 | T2 EI DIABLO-MIDWAY #2 017/067 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-04-15 | 2021-04-15 | 2022-06-16 | 2022-04-15 | 2022-04-15 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068539 | T2 EI DIABLO-MIDWAY #2 017/067 RPR GYWS | ICS
LC | 120823933 | 002/040 | T2 WV WEIMAR #1 2/040 RPR SPLW | SACTO | ETL.7560.POLE.WOOD | 2021-04-15 | 2021-04-15 | 2021-08-17 | 2022-04-15 | 2022-04-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Splice-Wood | Repair | 44754779 | T2 WV WEIMAR #1 2/040 RPR SPLW | ICW
LC | 120824294 | 011/090 | T2 EI SALT SPRING-TGR CRK 11/90 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-15 | 2021-04-15 | 2022-06-20 | 2022-04-15 | 2022-04-15 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540431 | T2 EI SALT SPRNGS-TGR CREK RPL INSS 18TW | 93K
LC | 120824350 | 010/087 | T2 EI SALT SPRING-TGR CRK 10/87 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-15 | 2021-04-15 | 2022-06-23 | 2022-04-15 | 2022-04-15 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540431 | T2 EI SALT SPRNGS-TGR CREK RPL INSS 18TW | 93K
LC | 120824353 | 010/084 | T2 EI SLT SPRNGS-TGR CRK 10/084 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-15 | 2021-04-15 | 2022-06-23 | 2022-04-15 | 2022-04-15 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31601311 | T2 EI SLT SPRNGS-TGR CRK 11/9 RPL INSS | 93K
LC | 120824354 | 010/083 | T2 EI SLT SPRNGS-TGR CRK 10/083 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-15 | 2021-04-15 | 2022-06-23 | 2022-04-15 | 2022-04-15 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540431 | T2 EI SALT SPRNGS-TGR CREK RPL INSS 18TW | 93K
LC | 120824367 | 010/085 | T2 EI SLT SPRING-TIGR CRK 10/85 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-15 | 2021-04-15 | 2022-06-23 | 2022-04-15 | 2022-04-15 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540431 | T2 EI SALT SPRNGS-TGR CREK RPL INSS 18TW | 93K
LC | 120824473 | 007/134A | T2 EI TEJON-LEBEC 7/134A RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-15 | 2021-04-15 | 2021-08-05 | 2022-04-15 | 2022-04-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 44817947 | T2 EI TEJON-LEBEC 7/134 RMV NEST | ICW
LC | 120826198 | 013/255 | T2 EI COLGATE-PALERMO 13/255 RPL HRDW | TABLEMTN | ETL.6500.POLE.WOOD | 2021-04-16 | 2021-04-15 | 2021-11-17 | 2022-04-15 | 2022-04-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44764607 | T2 EI COLGATE-PALERMO 13/255 RPL HRDW | ICW
LC | 120826279 | 000/008 | T2 EI SBRNTE-GRZLY-CLMNT #2 0/8 RPL INSS | CONCORD | ETL.3750.INSL | 2021-04-16 | 2021-04-16 | 2022-07-19 | 2022-04-16 | 2022-04-16 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546696 | T2 DI SBNT GZLY CLT #2 RPL INSS 2TWRS | 93K
LC | 120826420 | 003/020 | T2 EI VACA-LAKEVILLE #1 003/020 RPR FOND | LAKEVLLE | ETL.5840.TOWR | 2021-04-16 | 2021-04-16 | 2022-02-04 | 2022-04-16 | 2022-04-16 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45161081 | T2 EI VACA-LAKEVILLE #1 003/020 RPR FOND | ICQ
LC | 120826591 | 023/150 | T2 DI POE-RIO OSO 23/150 RPL INSS | TABLEMTN | ETL.5540.INSL.CERA | 2021-04-16 | 2021-04-15 | 2022-08-10 | 2022-04-15 | 2022-04-15 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546766 | T2 DI POE-RIO OSO RPL INSS 7 TWRS | 93K
LC | 120827009 | 001/044 | T2 EI SPAULDING-SUMMIT 1/44 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-16 | 2021-04-16 | 2021-08-19 | 2022-04-16 | 2022-04-16 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31527024 | EI SPAULDING-SUMMIT 06/226 RPL PL | 70Y
LC | 120827025 | C005/021 | T2 DI CBRN-LS AGLS SW ST C5/21 RPL INSS | MOSSLNDG | ETL.4460.INSL | 2021-04-16 | 2021-04-15 | 2021-11-18 | 2022-04-15 | 2022-04-15 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31527944 | DI CBN-LS AGLS SW ST-PCH RPL INSS 13TWRS | 93K
LC | 120827097 | 001/045 | T2 EI SPAULDING-SUMMIT 1/45 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-16 | 2021-04-16 | 2021-08-22 | 2022-04-16 | 2022-04-16 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31527024 | EI SPAULDING-SUMMIT 06/226 RPL PL | 70Y
LC | 120827138 | 007/130 | T2 EI TEJON-LEBEC 007/130 RPL ANCW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-16 | 2021-04-16 | 2021-08-17 | 2022-04-16 | 2022-04-16 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31535903 | T2 EI TEJON-LEBEC 11/196 RPL ANCW | 93E
LC | 120827186 | 064/576 | T2 EI CTONWD-DELEVAN #2 64/576 RPL INSS | TABLEMTN | ETL.4580.INSL.CERA | 2021-04-16 | 2021-04-16 | 2022-06-07 | 2022-04-16 | 2022-04-16 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540712 | T2 EI CTONWD-DELEVAN #2 RPL INSS 9TWRS | 93K
LC | 120827202 | 011/097 | T2 DI PARADISE-TABLE MTN 11/97 RPR FOND | TABLEMTN | ETL.4316.TOWR | 2021-04-16 | 2021-04-15 | 2021-06-10 | 2022-04-15 | 2022-04-15 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 120827529 | 012/106 | T2 DI PARADISE-TABLE MTN 12/106 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-16 | 2021-04-15 | 2021-07-19 | 2022-04-15 | 2022-04-15 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120827544 | 002/055 | T2 EI COLGATE-ALLEGHANY 2/55 REPL HRDW | SACTO | ETL.6470.POLE.WOOD | 2021-04-16 | 2021-04-16 | 2021-08-09 | 2022-04-16 | 2022-04-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44753074 | T2 EI COLGATE-ALLEGHANY 2/55 REPL HRDW | ICW
LC | 120827969 | 018/080 | T2 EI MR BY-SLR SW STA #2 18/80 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-16 | 2021-04-16 | 2022-07-12 | 2022-04-16 | 2022-04-16 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548992 | T2 EI MRR BY-SLR SW #2 RPL INSS 10TWRS | 93K
LC | 120828230 | 014/129 | T2 WV BRDGEVL-CTNWD-WD 14/129 RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2021-04-16 | 2021-04-16 | 2021-06-30 | 2022-04-16 | 2022-04-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44873802 | T2 WV BRDGEVL-CTNWD-WD 14/129 RPR ADSS | ICW
LC | 120828273 | 001/015 | T2 EI SBRNT-GRZLY-CLMNT #2 1/15 RPL HWRS | CONCORD | ETL.3750.TOWR | 2021-04-16 | 2021-04-16 | 2022-04-21 | 2022-04-16 | 2022-04-16 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Anti-Climbing Guard | Structure-Tower | Repair | 45277634 | T2 EI SBRNT-GRZLY-CLMNT #2 1/15 RPL HWRS | ICQ
LC | 120828274 | 001/015 | T2 EI SBRNT-GRZLY-CLMNT #2 1/15 REM VEG | CONCORD | ETL.3750.TOWR | 2021-04-16 | 2021-04-16 | 2022-04-14 | 2022-04-16 | 2022-04-16 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120828315 | 019/081 | T2 EI MR BY-SLR SW STA #2 19/81 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-16 | 2021-04-16 | 2022-07-12 | 2022-04-16 | 2022-04-16 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548992 | T2 EI MRR BY-SLR SW #2 RPL INSS 10TWRS | 93K
LC | 120828333 | 001/049 | T2 EI COLGATE-ALLEGHANY 1/49 REFRAME | SACTO | ETL.6470.POLE.WOOD | 2021-04-16 | 2021-04-16 | 2021-08-08 | 2022-04-16 | 2022-04-16 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31549891 | T2 EI COLGATE-ALLEGHANY 1/44 REFRAME | 93E
LC | 120828371 | 010/168 | T2 EI TEJON-LEBEC 10/168 RMV VEG | MIDWAY | ETL.9250.POLE.NWOD | 2021-04-16 | 2021-04-16 | 2021-10-28 | 2022-04-16 | 2022-04-16 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120828406 | 043/208 | T2 WV CRTINA-MNDOCINO #1 43/208 RPL INSS | WILLITS | ETL.1330.INSL | 2021-04-16 | 2021-04-16 | 2022-01-13 | 2022-04-16 | 2022-04-16 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31439888 | T2 DI CORTINA-MNDCNO #1 RPL INSS 4 LSTS | 93K
LC | 120828553 | 006/000 | T2 DI OAKHURST TAP 6/0 RPR SPLW | FRESNO | ETL.1252.INSL.NCER | 2021-04-16 | 2021-04-16 | 2022-03-24 | 2022-04-16 | 2022-04-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45068654 | T2 DI OAKHURST TAP 6/0 RPR SPLW | ICW
LC | 120828681 | 033/003 | T2 EI FULTON-HOPLAND 033/003 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-04-16 | 2021-04-06 | 2021-10-14 | 2022-04-06 | 2022-04-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536640 | T2 EI FULTON-HOPLAND 033/003 RPL STRW | 70Y
LC | 120828828 | 017/065 | T2 EI DIABLO-MIDWAY #2 17/065 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-04-16 | 2021-04-15 | 2022-05-31 | 2022-04-15 | 2022-04-15 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068540 | T2 EI DIABLO-MIDWAY #2 17/065 RPR GYWS | ICS
LC | 120828938 | 006/075 | T2 EI DRUM-SUMMIT#2 6/075 RPL DAMW | SACTO | ETL.1450.INSL.CERA | 2021-04-16 | 2021-04-16 | 2022-06-07 | 2022-04-16 | 2022-04-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Damper-Wood | Replace | 44752917 | EI DRUM-SUMMIT#2 6/075 RPL DAMW | ICW
LC | 120829196 | 001/044 | T2 EI COLGATE-ALLEGHANY 1/44 REFRAME | SACTO | ETL.6470.POLE.WOOD | 2021-04-16 | 2021-04-16 | 2021-08-08 | 2022-04-16 | 2022-04-16 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31549891 | T2 EI COLGATE-ALLEGHANY 1/44 REFRAME | 93E
LC | 120829396 | 007/012 | T2 DI VLY SPRNGS-MRTL #1 7/12 RPL STRW | VICTOR | ETL.8240.POLE.WOOD | 2021-04-16 | 2021-04-08 | 2021-08-08 | 2022-04-08 | 2022-04-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31537229 | T2 DI VLY SPRNGS-MRTL #1 7/12 RPL STRW | 70Y
LC | 120829456 | 062/563 | T2 EI CTONWD-DELEVAN #2 62/563 RPR FOND | TABLEMTN | ETL.4580.TOWR | 2021-04-16 | 2021-04-16 | 2022-06-07 | 2022-04-16 | 2022-04-16 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45107486 | T2 EI CTONWD-DELEVAN #2 62/563 RPR FOND | ICQ
LC | 120829855 | 003/132 | T2 EI SPLDNG-SMMT 3/132 RPR STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-16 | 2021-04-16 | 2021-08-01 | 2022-04-16 | 2022-04-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44764623 | T2 EI SPLDNG-SMMT 3/132 RPR STRW | ICW
LC | 120829974 | 049/280 | T2 DI TMBLR-SN LS OBSPO 49/280 RPR STRT | PISMOBCH | ETL.3960.TOWR | 2021-04-16 | 2021-04-09 | 2022-06-24 | 2022-04-09 | 2022-04-09 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45077883 | T2 DI TMBLR-SN LS OBSPO 49/280 RPR STRT | ICQ
LC | 120830869 | 000/001 | T2 EI SALT SPRINGS-TIGR CRK 0/1 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-16 | 2021-04-16 | 2022-06-17 | 2022-04-16 | 2022-04-16 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31601311 | T2 EI SLT SPRNGS-TGR CRK 11/9 RPL INSS | 93K
LC | 120831376 | 010/204 | T2 EI COLGATE-PALERMO 10/204 RPR WDPKR | SACTO | ETL.6500.POLE.WOOD | 2021-04-16 | 2021-04-16 | 2022-05-22 | 2022-04-16 | 2022-04-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44765928 | T2 EI COLGATE-PALERMO 10/204 RPR WDPKR | ICW
LC | 120831378 | 010/201 | T2 EI COLGATE-PALERMO 10/201 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2021-04-16 | 2021-04-16 | 2022-08-31 | 2022-04-16 | 2022-04-16 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31552691 | T2 EI COLGATE-PALERMO 10/201 RPL STRW | 70Y
LC | 120831379 | 010/202 | T2 EI COLGATE-PALERMO 10/202 RPL STRW | SACTO | ETL.6500.INSL.CERA | 2021-04-16 | 2021-04-16 | 2021-11-18 | 2022-04-16 | 2022-04-16 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31552691 | T2 EI COLGATE-PALERMO 10/201 RPL STRW | 70Y
LC | 120831862 | 007/002 | T2 DI OAKHURST TAP 007/002 RPR SPLW | FRESNO | ETL.1252.INSL.NCER | 2021-04-16 | 2021-04-16 | 2022-03-23 | 2022-04-16 | 2022-04-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45068657 | T2 DI OAKHURST TAP 007/002 RPR SPLW | ICW
LC | 120832162 | 000/005 | T2 EI SLT SPRNGS-TIGER CRK 0/5 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-16 | 2021-04-16 | 2022-06-17 | 2022-04-16 | 2022-04-16 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31601311 | T2 EI SLT SPRNGS-TGR CRK 11/9 RPL INSS | 93K
LC | 120833015 | 014/083 | T2 DI STNSLS-MLNS-MNTC 14/83 RPLC HRDT | VICTOR | ETL.3830.TOWR | 2021-04-17 | 2021-04-16 | 2022-02-02 | 2022-04-16 | 2022-04-16 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45122678 | T2 DI STNSLS-MLNS-MNTC 14/83 RPLC HRDT | ICQ
LC | 120833070 | 007/004 | T2 DI OAKHURST TAP 7/4 RPLC INSW | FRESNO | ETL.1252.INSL.NCER | 2021-04-17 | 2021-04-16 | 2022-03-23 | 2022-04-16 | 2022-04-16 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31536425 | T2 DI OAKHURST TAP 7/4 RPLC INSW | 93I
LC | 120833201 | 009/072 | T2 DI VAC-VCVL-JMSN-NR TWR 9/72 RPL INSS | LAKEVLLE | ETL.4100.INSL.CERA | 2021-04-17 | 2021-04-13 | 2022-02-26 | 2022-04-13 | 2022-04-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549400 | T2 DI VC-VACVILLE-JMESN-NH RPL INSS 5TWR | 93K
LC | 120833212 | 003/017 | T2 DI VASONA-METCALF 003/017 RPL INSS | METCALF | ETL.5932.INSL | 2021-04-17 | 2021-04-09 | 2022-04-20 | 2022-04-09 | 2022-04-09 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31539354 | DI HICKS-METCALF RPL INSS 2TWRS | 93K
LC | 120833336 | 025/159 | T2 EI STN-MLN MAN #1 25/159 RPR STRT | VICTOR | ETL.3830.TOWR | 2021-04-17 | 2021-04-17 | 2022-02-03 | 2022-04-17 | 2022-04-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45123142 | T2 EI STN-MLN MAN #1 25/159 RPR STRT | ICQ
LC | 120833551 | 019/113 | T2 DI STNSLUS-MANTECA #2 19/113 RMV NEST | VICTOR | ETL.3820.TOWR | 2021-04-17 | 2021-04-06 | 2021-09-17 | 2022-04-06 | 2022-04-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44962487 | T2 DI STNSLUS-MANTECA #2 19/113 RMV NEST | ICS
LC | 120833553 | 012/074 | T2 DI STNSLAUS-MANTECA #2 12/74 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-17 | 2021-04-06 | 2022-02-01 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45122323 | T2 DI STNSLAUS-MANTECA #2 12/74 RPR FOND | ICQ
LC | 120833556 | 026/156 | T2 DI TSLA-SLADO-MANTECA 26/156 RPL INSW | VICTOR | ETL.4000.INSL.NCER | 2021-04-17 | 2021-04-06 | 2022-02-01 | 2022-04-06 | 2022-04-06 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31538352 | T2 DI TSLA-SLADO-MANTECA 26/156 RPL INSW | 93I
LC | 120833557 | 004/026 | T2 DI STNSLS-MLS SS-MTC #1 4/26 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-17 | 2021-04-06 | 2022-01-18 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45119715 | T2 DI STNSLS-MLS SS-MTC #1 4/26 RPR FOND | ICQ
LC | 120833608 | 007/140 | T2 EI TEJON-LEBEC 7/140 RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-17 | 2021-04-17 | 2021-08-25 | 2022-04-17 | 2022-04-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 44829772 | T2 EI TEJON-LEBEC 7/140 RPR GYWW | ICW
LC | 120833721 | 005/032 | T2 DI STNISLAUS-MANTECA #2 5/32 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-17 | 2021-04-09 | 2022-01-19 | 2022-04-09 | 2022-04-09 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45119921 | T2 DI STNISLAUS-MANTECA #2 5/32 RPR FOND | ICQ
LC | 120833802 | 062/560 | T2 EI CTONWOD-DELEVAN #2 62/560 RPR FOND | TABLEMTN | ETL.4580.TOWR | 2021-04-17 | 2021-04-17 | 2022-01-12 | 2022-04-17 | 2022-04-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45107485 | T2 EI CTONWOD-DELEVAN #2 62/560 RPR FOND | ICQ
LC | 120833838 | 030/004 | T2 FULTON-HOPLAND 30/4 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-04-17 | 2021-04-07 | 2021-10-13 | 2022-04-07 | 2022-04-07 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536640 | T2 EI FULTON-HOPLAND 033/003 RPL STRW | 70Y
LC | 120834001 | 025/146 | T2 EI STNSLUS-MANTECA #2 025/14 RPR STRT | VICTOR | ETL.3820.TOWR | 2021-04-17 | 2021-04-17 | 2022-02-09 | 2022-04-17 | 2022-04-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45123139 | T2 EI STNSLUS-MANTECA #2 025/14 RPR STRT | ICQ
LC | 120834334 | 009/153 | T2 EI TEJON-LEBEC 9/153 RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-17 | 2021-04-17 | 2021-08-25 | 2022-04-17 | 2022-04-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44829775 | T2 EI TEJON-LEBEC 9/153 RPR GYWW | ICW
LC | 120835005 | 002/015 | T2 EI KRCKHF-CLVS-SNGR #1 2/015 RPR FOND | FRESNO | ETL.1890.TOWR | 2021-04-17 | 2021-04-17 | 2022-02-08 | 2022-04-17 | 2022-04-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45069191 | T2 EI KRCKHF-CLVS-SNGR #1 2/015 RPR FOND | ICQ
LC | 120835905 | 000/006 | T2 EI SLT SPRNGS-TIGR CRK 0/006 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-17 | 2021-04-17 | 2022-06-18 | 2022-04-17 | 2022-04-17 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31601311 | T2 EI SLT SPRNGS-TGR CRK 11/9 RPL INSS | 93K
LC | 120835960 | 000/008 | T2 EI SLT SPRNGS-TIGR CRK 0/8 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-17 | 2021-04-17 | 2022-06-18 | 2022-04-17 | 2022-04-17 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31601311 | T2 EI SLT SPRNGS-TGR CRK 11/9 RPL INSS | 93K
LC | 120835962 | 010/080 | T2 EI SLT SPRNGS-TGR CRK 10/080 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-17 | 2021-04-17 | 2022-06-23 | 2022-04-17 | 2022-04-17 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31601311 | T2 EI SLT SPRNGS-TGR CRK 11/9 RPL INSS | 93K
LC | 120835966 | 009/079 | T2 EI SALT SPRNGS-TIGR CRK 9/79 RPR FOND | VICTOR | ETL.3500.TOWR | 2021-04-17 | 2021-04-17 | 2022-03-21 | 2022-04-17 | 2022-04-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45150395 | T2 EI SALT SPRNGS-TIGR CRK 9/79 RPR FOND | ICQ
LC | 120835969 | 009/078 | T2 EI SALT SPRNGS-TGR CRK 9/078 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-17 | 2021-04-17 | 2022-06-23 | 2022-04-17 | 2022-04-17 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31601311 | T2 EI SLT SPRNGS-TGR CRK 11/9 RPL INSS | 93K
LC | 120836014 | 009/076 | T2 EI SALT SPRNGS-TIGR CRK 9/76 INS HRDT | VICTOR | ETL.3500.TOWR | 2021-04-17 | 2021-04-17 | 2022-03-21 | 2022-04-17 | 2022-04-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45150396 | T2 EI SALT SPRNGS-TIGR CRK 9/07 INS HRDT | ICQ
LC | 120836040 | 009/074 | T2 EI SLT SPG-TGR CREEK 009/07 RPR FOND | VICTOR | ETL.3500.TOWR | 2021-04-17 | 2021-04-17 | 2022-03-21 | 2022-04-17 | 2022-04-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45150397 | T2 EI SLT SPG-TGR CREEK 009/07 RPR FOND | ICQ
LC | 120836044 | 004/147 | T2 EI SPLDNG-SMMT 04/147 RPR STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-17 | 2021-04-17 | 2021-05-03 | 2022-04-17 | 2022-04-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44764622 | T2 EI SPLDNG-SMMT 04/147 RPR STRW | ICW
LC | 120838025 | 007/004 | T2 EI LAYTONVILLE-COVELO 7/4 RPR GYWW | LAKEVLLE | ETL.7390.POLE.NWOD | 2021-04-18 | 2021-04-17 | 2021-06-23 | 2022-04-17 | 2022-04-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44877479 | T2 EI LAYTONVILLE-COVELO 7/4 RPR GYWW | ICW
LC | 120838039 | 007/003C | T2 EI LAYTONVILLE-COVELO 7/3C RMV VEG | WILLITS | ETL.7390.POLE.NWOD | 2021-04-18 | 2021-04-17 | 2022-01-07 | 2022-04-17 | 2022-04-17 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120838093 | 060/298 | T2 EI MALIN-RD MTN #2 060/298 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-04-18 | 2021-04-16 | 2022-08-04 | 2022-04-16 | 2022-04-16 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45193986 | T2 EI MALIN-RD MTN #2 060/298 RPR GYWS | ICS
LC | 120839581 | 006/106 | T2 EI COLGATE-PALERM 06/106 RPR GND WIRE | SACTO | ETL.6500.POLE.WOOD | 2021-04-19 | 2021-04-17 | 2021-08-14 | 2022-04-17 | 2022-04-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 44808057 | T2 EI COLGATE-PALERM 06/106 RPR GND WIRE | ICW
LC | 120839582 | 005/097 | T2 EI COLGATE-PALERMO 5/097 REFRAME | SACTO | ETL.6500.POLE.WOOD | 2021-04-19 | 2021-04-17 | 2021-08-11 | 2022-04-17 | 2022-04-17 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31537106 | T2 EI COLGATE-PALERMO 5/097 REFRAME | 93E
LC | 120839595 | 013/114 | T2 DI PARADISE-TABLE MTN 13/114 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-19 | 2021-04-15 | 2021-07-20 | 2022-04-15 | 2022-04-15 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120839596 | 013/114 | T2 DI PARADISE-TBL MTN 13/114 RPLC HRDT | TABLEMTN | ETL.4316.TOWR | 2021-04-19 | 2021-04-15 | 2021-06-10 | 2022-04-15 | 2022-04-15 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44861525 | T2 DI PARADISE-TBL MTN 13/114 RPLC HRDT | ICQ
LC | 120839624 | 012/090 | T2 DI WISHON-COPPERMINE 012/090 RPR FOND | FRESNO | ETL.9330.POLE.NWOD | 2021-04-19 | 2021-04-16 | 2021-07-01 | 2022-04-16 | 2022-04-16 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44839762 | T2 DI WISHON-COPPERMINE 012/090 RPR FOND | ICQ
LC | 120839722 | 054/381 | T2 DI CARIBOU-TABLE MTN 54/381 RPLC INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-04-19 | 2021-04-12 | 2022-06-17 | 2022-04-12 | 2022-04-12 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 120839806 | 015/087 | T2 DI STANISLAUS-MNTC #2 15/87 RPLC HRDT | VICTOR | ETL.3820.TOWR | 2021-04-19 | 2021-04-12 | 2022-02-04 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45123048 | T2 DI STANISLAUS-MNTC #2 15/87 RPLC HRDT | ICQ
LC | 120839807 | 015/087 | T2 DI STANISLAUS-MNTC #2 15/87 RMV VEG | VICTOR | ETL.3820.TOWR | 2021-04-19 | 2021-04-12 | 2021-12-16 | 2022-04-12 | 2022-04-12 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120839930 | 010/052 | T2 DI SILVERADO-FULTON JCT 10/52 RPL INS | LAKEVLLE | ETL.1610.INSL.NCER | 2021-04-19 | 2021-04-12 | 2022-03-13 | 2022-04-12 | 2022-04-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536106 | T2 DI SLVRD-FLTN JCT RPL INSS 6TWRS | 93K
LC | 120839931 | 013/079 | T2 DI STNSLS-MLNS-MNTC 13/79 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-19 | 2021-04-09 | 2022-02-03 | 2022-04-09 | 2022-04-09 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45122672 | T2 DI STNSLS-MLNS-MNTC 13/79 RPR FOND | ICQ
LC | 120839933 | 010/052 | T2 DI FULTON-PUEBLO 10/52 RPL INSS | LAKEVLLE | ETL.1600.INSL.NCER | 2021-04-19 | 2021-04-12 | 2022-02-25 | 2022-04-12 | 2022-04-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 120840120 | 027/180 | T2 DI POE-RIO OSO 27/180 RPL INSS | TABLEMTN | ETL.5540.INSL.CERA | 2021-04-19 | 2021-04-09 | 2022-08-10 | 2022-04-09 | 2022-04-09 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546766 | T2 DI POE-RIO OSO RPL INSS 7 TWRS | 93K
LC | 120840122 | :008/004 | T2 DI BLLT-RVRBNK-MLS SWST :8/4 RPR STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-04-19 | 2021-04-12 | 2022-05-06 | 2022-04-12 | 2022-04-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45155256 | T2 DI BLLT-RVRBNK-MLS SWST :8/4 RPR STRW | ICW
LC | 120840123 | 010/050 | T2 DI FLTN-PUEBLO SLVR 10/50 RPLC INSS | LAKEVLLE | ETL.1610.INSL.CERA | 2021-04-19 | 2021-04-09 | 2022-03-13 | 2022-04-09 | 2022-04-09 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548684 | T2 DI SILVERADO-FUTON JCT RPL INSS 6TWR | 93K
LC | 120840125 | :008/004 | T2 DI BLT-RVRBNK-MLNS SWST :8/4 RPL INSW | VICTOR | ETL.1070.INSL.NCER | 2021-04-19 | 2021-04-12 | 2022-05-06 | 2022-04-12 | 2022-04-12 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31539420 | T2 DI BLLT-RBK-MLS SWS :005/006 RPL INSW | 93I
LC | 120840126 | 010/050 | T2 DI FULTON-PUEBLO 10/50 RPLC INSS | LAKEVLLE | ETL.1600.INSL.CERA | 2021-04-19 | 2021-04-09 | 2022-02-25 | 2022-04-09 | 2022-04-09 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 120840127 | 010/050 | T2 DI FULTON-PUEBLO 10/50 RPR STRT | LAKEVLLE | ETL.1600.TOWR | 2021-04-19 | 2021-04-09 | 2022-03-15 | 2022-04-09 | 2022-04-09 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45142245 | T2 DI FULTON-PUEBLO 10/50 RPR STRT | ICQ
LC | 120840128 | 006/048 | T2 DI ELDORADO-MSR FLT #1 6/48 RPL INSS | SACTO | ETL.1530.INSL.CERA | 2021-04-19 | 2021-04-16 | 2022-06-15 | 2022-04-16 | 2022-04-16 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535732 | T2 DI ELDRD-MSSRI FLT #1 RPL INSS 10TWRS | 93K
LC | 120840270 | 006/048 | T2 DI ELDORADO-MSR FLT #2 6/48 RPL INSS | SACTO | ETL.1540.INSL.CERA | 2021-04-19 | 2021-04-16 | 2022-05-19 | 2022-04-16 | 2022-04-16 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547631 | T2 WV EL DORADO-MSR FLT #2 RPL INSS 10TW | 93K
LC | 120840351 | :010/056 | T2 DI CZY HRS CN-SLS-SD :10/56 RMV DBRIS | MOSSLNDG | ETL.2900.TOWR | 2021-04-19 | 2021-04-16 | 2021-05-24 | 2022-04-16 | 2022-04-16 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Steel | Remove | 44805763 | T2 DI CZY HRS CN-SLS-SD :10/56 RMV DBRIS | ICS
LC | 120840439 | 023/137 | T2 EI STNSLS-MNTC #2 23/137 RPP CNDS | VICTOR | ETL.3820.TOWR | 2021-04-19 | 2021-04-19 | 2021-12-09 | 2022-04-19 | 2022-04-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Conductor-Steel | Repair | 44977946 | T2 EI STNSLS-MNTC #2 23/137 RPP CNDS | ICS
LC | 120840511 | 024/177 | T2 EI TRINITY-COTTONWOOD 24/177 REPULL | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-19 | 2021-04-19 | 2021-09-02 | 2022-04-19 | 2022-04-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873930 | T2 EI TRINITY-COTTONWOOD 24/177 REPULL | ICW
LC | 120840570 | 024/177 | T2 EI TRINITY-COTTONWOOD 24/177 REPULL | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-19 | 2021-04-19 | 2021-09-02 | 2022-04-19 | 2022-04-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873931 | T2 EI TRINITY-COTTONWOOD 24/177 REPULL | ICW
LC | 120840595 | 027/171 | T2 DI TESLA-SLD-MNTC 27/171 RPL HRDD | VICTOR | ETL.4000.POLE.WOOD | 2021-04-19 | 2021-04-12 | 2021-10-12 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44977845 | T2 DI TESLA-SLD-MNTC 27/171 RPL HRDD | ICW
LC | 120840612 | 024/177 | T2 EI TRINITY-COTTONWOOD 24/177 REPULL | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-19 | 2021-04-19 | 2021-09-02 | 2022-04-19 | 2022-04-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873932 | T2 EI TRINITY-COTTONWOOD 24/177 REPULL | ICW
LC | 120840863 | 011/091 | T2 EI PIT #1-CTTNWD 11/091 INS HRDT | TABLEMTN | ETL.5390.TOWR | 2021-04-19 | 2021-04-19 | 2022-07-26 | 2022-04-19 | 2022-04-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Hardware-Tower | Install | 45180997 | T2 EI PIT #1-CTTNWD 11/091 INS HRDT | ICQ
LC | 120840989 | 004/092 | T2 EI WEIMAR-HALSEY 004/092 RPR STRW | SACTO | ETL.8340.POLE.WOOD | 2021-04-19 | 2021-04-19 | 2022-03-05 | 2022-04-19 | 2022-04-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44756754 | T2 EI WEIMAR-HALSEY 004/092 RPR STRW | ICW
LC | 120841072 | 023/147 | T2 EI STN-MLN MAN #1 23/147 UNBURY | VICTOR | ETL.3830.TOWR | 2021-04-19 | 2021-04-19 | 2022-02-11 | 2022-04-19 | 2022-04-19 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45123133 | T2 EI STN-MLN MAN #1 23/147 UNBURY | ICQ
LC | 120841380 | 011/045 | T2 DI MORRO BAY-SOLAR #2 11/45 RPLC INSS | PISMOBCH | ETL.5310.INSL | 2021-04-19 | 2021-04-09 | 2022-07-14 | 2022-04-09 | 2022-04-09 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31550476 | T2 EI MR BY-SLR SW STA #2 RPL INSS 5 TW | 93K
LC | 120841387 | 010/049 | T2 DI FULTON-PUEBLO 10/49 RPL INSS | LAKEVLLE | ETL.1600.INSL.NCER | 2021-04-19 | 2021-04-12 | 2022-02-25 | 2022-04-12 | 2022-04-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 120841512 | 011/053 | T2 DI FULTON-PUEBLO 011/053 RPL INSS | LAKEVLLE | ETL.1600.INSL.NCER | 2021-04-19 | 2021-04-12 | 2022-02-27 | 2022-04-12 | 2022-04-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 120841530 | 010/049 | T2 DI SLVRDO-FULTON JCT 10/49 RPL INSS | LAKEVLLE | ETL.1610.INSL.NCER | 2021-04-19 | 2021-04-12 | 2022-03-13 | 2022-04-12 | 2022-04-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548684 | T2 DI SILVERADO-FUTON JCT RPL INSS 6TWR | 93K
LC | 120841531 | 010/049 | T2 DI FULTON-PUEBLO 10/49 RPL HRDT | LAKEVLLE | ETL.1600.TOWR | 2021-04-19 | 2021-04-12 | 2022-03-14 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45142244 | T2 DI FULTON-PUEBLO 10/49 RPL HRDT | ICQ
LC | 120841540 | 011/053 | T2 DI SILVERADO-FULTN JCT 11/53 RPL INSS | LAKEVLLE | ETL.1610.INSL.NCER | 2021-04-19 | 2021-04-12 | 2022-03-13 | 2022-04-12 | 2022-04-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536106 | T2 DI SLVRD-FLTN JCT RPL INSS 6TWRS | 93K
LC | 120841850 | 025/143 | T2 DI TESLA-SALADO-MTC 25/143 RPR GYWW | VICTOR | ETL.4000.POLE.WOOD | 2021-04-19 | 2021-04-12 | 2021-10-07 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44975294 | T2 DI TESLA-SALADO-MTC 25/143 RPR GYWW | ICW
LC | 120841854 | 025/143 | T2 DI TESLA-SALADO-MTC 25/143 RPL HRDD | VICTOR | ETL.4000.POLE.WOOD | 2021-04-19 | 2021-04-12 | 2021-10-07 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44975295 | T2 DI TESLA-SALADO-MTC 25/143 RPL HRDD | ICW
LC | 120842001 | 014/089 | T2 DI STNSLS-MLNS-MNTC 14/89 RPR STRT | VICTOR | ETL.3830.TOWR | 2021-04-19 | 2021-04-09 | 2022-02-04 | 2022-04-09 | 2022-04-09 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45123045 | T2 DI STNSLS-MLNS-MNTC 14/89 RPR STRT | ICQ
LC | 120842014 | 023/144 | T2 EI STN-MLN MAN #1 23/144 UNBURY | VICTOR | ETL.3830.TOWR | 2021-04-19 | 2021-04-19 | 2022-02-11 | 2022-04-19 | 2022-04-19 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123131 | T2 EI STN-MLN MAN #1 23/144 UNBURY | ICQ
LC | 120842015 | 006/046 | T2 EI WISHON-COPPERMINE 006/046 RMV VEG | FRESNO | ETL.9330.TOWR | 2021-04-19 | 2021-04-19 | 2022-08-26 | 2022-04-19 | 2022-04-19 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120842114 | 005/035 | T2 DI STNISLAUS-MANTECA #2 5/35 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-19 | 2021-04-12 | 2022-01-24 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45119927 | T2 DI STNISLAUS-MANTECA #2 5/35 RPR FOND | ICQ
LC | 120842139 | 001/009 | T2 DI FULTON-PUEBLO 1/9 RPL INSS | LAKEVLLE | ETL.1600.INSL.NCER | 2021-04-19 | 2021-04-12 | 2022-02-27 | 2022-04-12 | 2022-04-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 120842140 | 005/035 | T2 DI STNISLAUS-MANTECA #2 5/35 INS HRDT | VICTOR | ETL.3820.TOWR | 2021-04-19 | 2021-04-12 | 2022-01-24 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45119928 | T2 DI STNISLAUS-MANTECA #2 5/35 INS HRDT | ICQ
LC | 120842296 | 020/118 | T2 DI STNSLUS-MANTECA #2 20/118 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-19 | 2021-04-12 | 2022-02-22 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45123114 | T2 DI STNSLUS-MANTECA #2 20/118 RPR FOND | ICQ
LC | 120842390 | 032/214 | T2 DI POE-RIO OSO 032/214 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-04-19 | 2021-04-12 | 2022-02-03 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45145303 | T2 DI POE-RIO OSO 032/214 RPR FOND | ICQ
LC | 120842676 | 025/180 | T2 EI TRINITY-COTTONWOOD 25/180 REPULL | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-19 | 2021-04-19 | 2021-09-02 | 2022-04-19 | 2022-04-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873933 | T2 EI TRINITY-COTTONWOOD 25/180 REPULL | ICW
LC | 120842691 | 006/009 | T2 DI BRCBRG JCT-MRPSA TP 6/9 RPL STRW | FRESNO | ETL.8651.POLE.WOOD | 2021-04-19 | 2021-04-12 | 2022-02-02 | 2022-04-12 | 2022-04-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31587924 | T2 BRCBRG JCT-MRPS TAP 07/9 RPL STRW | 70Y
LC | 120842735 | :009/000 | T2 DI BLLT-RBK-MLS SWS :009/000 RPL INSW | VICTOR | ETL.1070.INSL.NCER | 2021-04-19 | 2021-04-12 | 2022-05-02 | 2022-04-12 | 2022-04-12 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31539420 | T2 DI BLLT-RBK-MLS SWS :005/006 RPL INSW | 93I
LC | 120842738 | :009/000 | T2 DI BLLT-RBK-MLS SWS :009/000 COMPLETE | VICTOR | ETL.1070.POLE.WOOD | 2021-04-19 | 2021-04-12 | 2022-05-06 | 2022-04-12 | 2022-04-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45155257 | T2 DI BLLT-RBK-MLS SWS :009/000 RPR STRW | ICW
LC | 120842745 | 025/180 | T2 EI TRINITY-COTTONWOOD 25/180 REPULL | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-19 | 2021-04-19 | 2021-09-02 | 2022-04-19 | 2022-04-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873934 | T2 EI TRINITY-COTTONWOOD 25/180 REPULL | ICW
LC | 120842767 | :009/000 | T2 DI BLLT-RBK-MLS SWS :009/000 RMV BUTT | VICTOR | ETL.1070.POLE.WOOD | 2021-04-19 | 2021-04-12 | 2022-02-18 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45155258 | T2 DI BLLT-RBK-MLS SWS :009/000 RMV BUTT | ICW
LC | 120842796 | :005/001 | T2 DI BLLT-RBK-MLS SWS :005/001 RMV BUTT | VICTOR | ETL.1070.POLE.WOOD | 2021-04-19 | 2021-04-12 | 2022-04-21 | 2022-04-12 | 2022-04-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45155259 | T2 DI BLLT-RBK-MLS SWS :005/001 RMV BUTT | ICW
LC | 120842798 | :005/001 | T2 DI BLLT-RBK-MLS SWS :005/001 RPR STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-04-19 | 2021-04-12 | 2022-04-21 | 2022-04-12 | 2022-04-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45155660 | T2 DI BLLT-RBK-MLS SWS :005/001 RPR STRW | ICW
LC | 120842974 | 002/015 | T2 DI STNISLAUS-MANTECA #2 2/15 INS HRDT | VICTOR | ETL.3820.TOWR | 2021-04-19 | 2021-04-12 | 2022-01-11 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45119063 | T2 DI STNISLAUS-MANTECA #2 2/15 INS HRDT | ICQ
LC | 120843068 | :005/006 | T2 DI BLLT-RBK-MLS SWS :005/006 RPL INSW | VICTOR | ETL.1070.INSL.NCER | 2021-04-19 | 2021-04-12 | 2022-04-25 | 2022-04-12 | 2022-04-12 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31539420 | T2 DI BLLT-RBK-MLS SWS :005/006 RPL INSW | 93I
LC | 120843132 | 006/054 | T2 DI PARADISE-TABLE MTN 6/54 RPR FOND | TABLEMTN | ETL.4316.TOWR | 2021-04-19 | 2021-04-12 | 2021-06-07 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44871403 | T2 DI PARADISE-TABLE MTN 6/54 RPR FOND | ICQ
LC | 120843323 | 005/083 | T2 EI COLGATE-PALERMO 5/083 REFRAME | SACTO | ETL.6500.POLE.WOOD | 2021-04-19 | 2021-04-19 | 2021-08-10 | 2022-04-19 | 2022-04-19 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31537106 | T2 EI COLGATE-PALERMO 5/097 REFRAME | 93E
LC | 120843324 | 004/074 | T2 EI COLGATE-PALERMO 4/074 RPR WDPKR | SACTO | ETL.6500.POLE.WOOD | 2021-04-19 | 2021-04-19 | 2021-08-10 | 2022-04-19 | 2022-04-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44764576 | T2 EI COLGATE-PALERMO 4/074 RPR WDPKR | ICW
LC | 120843329 | 006/002 | T2 EI SALINAS-FORT ORD#1 6/2 RPR SPLS | MOSSLNDG | ETL.7890.INSL.CERA | 2021-04-19 | 2021-04-19 | 2022-04-19 | 2022-04-19 | 2022-04-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP SUBS COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45223969 | T2 EI SALINAS-FORT ORD#1 6/2 RPR SPLS | ICS
LC | 120843337 | 004/078 | T2 EI COLEMAN-RED BLUFF 4/78 RPLC STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2021-04-19 | 2021-04-19 | 2022-04-11 | 2022-04-19 | 2022-04-19 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31539389 | T2 EI COLEMAN-RED BLUFF 4/78 RPLC STRW | 70Y
LC | 120843386 | 000/021 | T2 EI CTTNWD-BNTN #1 000/21 RPL STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-04-19 | 2021-04-19 | 2021-07-22 | 2022-04-19 | 2022-04-19 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536497 | T2 EI CTTNWD-BNTN #1 000/21 RPL STRW | 70Y
LC | 120843862 | 020/081 | T2 EI DIABLO-MIDWAY #2 20/081 RPR INSS | PISMOBCH | ETL.5970.INSL.NCER | 2021-04-19 | 2021-04-19 | 2022-02-17 | 2022-04-19 | 2022-04-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB | No Good/Out of Stdrd | Insulator-Steel | Repair | 45177846 | T2 EI DIABLO-MIDWAY #2 20/081 RPR INSS | ICS
LC | 120844199 | 012/104 | T2 EI PARADISE-TABLE MTN 12/104 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-19 | 2021-04-19 | 2021-07-19 | 2022-04-19 | 2022-04-19 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120844495 | :001/007 | T2 DI BLLT-RVRBNK-MLS SWS :1/7 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-04-19 | 2021-04-12 | 2022-04-16 | 2022-04-12 | 2022-04-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31539414 | T2 DI BLLT-RVRBNK-MLS SWS :1/7 RPL STRW | 70Y
LC | 120844546 | 020/082 | T2 EI DIABLO-MIDWAY #3 20/082 RPR GYWS | PISMOBCH | ETL.5980.TOWR | 2021-04-19 | 2021-04-19 | 2022-05-26 | 2022-04-19 | 2022-04-19 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068587 | T2 EI DIABLO-MIDWAY #3 20/082 RPR GYWS | ICS
LC | 120844552 | 010/051 | T2 DI FULTON-PUEBLO 10/51 RPLC INSS | LAKEVLLE | ETL.1600.INSL.NCER | 2021-04-19 | 2021-04-12 | 2022-02-25 | 2022-04-12 | 2022-04-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 120844585 | 010/051 | T2 DI SILVERADO-FLTN JCT 10/51 RPL INSS | LAKEVLLE | ETL.1610.INSL.NCER | 2021-04-19 | 2021-04-12 | 2022-03-13 | 2022-04-12 | 2022-04-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536106 | T2 DI SLVRD-FLTN JCT RPL INSS 6TWRS | 93K
LC | 120844981 | 022/148 | T2 DI HELMS-GREGG #1 22/148 RPR FOND | FRESNO | ETL.4870.TOWR | 2021-04-19 | 2021-04-19 | 2022-05-26 | 2022-04-19 | 2022-04-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44756797 | T2 DI HELMS-GREGG #1 22/148 RPR FOND | ICQ
LC | 120845071 | 012/106 | T2 EI PARADISE-TABLE MTN 12/106 RMV VEG | TABLEMTN | ETL.4316.TOWR | 2021-04-19 | 2021-04-19 | 2022-01-13 | 2022-04-19 | 2022-04-19 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120845278 | 014/085 | T2 DI STANISLAUS-MNTC#2 14/85 RPR STRT | VICTOR | ETL.3820.TOWR | 2021-04-19 | 2021-04-09 | 2022-02-03 | 2022-04-09 | 2022-04-09 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45123042 | T2 DI STANISLAUS-MNTC#2 14/85 RPR STRT | ICQ
LC | 120845279 | 014/085 | T2 DI STANISLAUS-MNTC#2 14/85 RPLC HRDT | VICTOR | ETL.3820.TOWR | 2021-04-19 | 2021-04-09 | 2022-02-03 | 2022-04-09 | 2022-04-09 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45123043 | T2 DI STANISLAUS-MNTC#2 14/85 RPLC HRDT | ICQ
LC | 120845562 | ;010/092 | T2 DI PARADISE-TABLE MTN ;10/92 UNBURY | TABLEMTN | ETL.4316.TOWR | 2021-04-19 | 2021-04-15 | 2021-06-07 | 2022-04-15 | 2022-04-15 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44871404 | T2 DI PARADISE-TABLE MTN ;10/92 UNBURY | ICQ
LC | 120845956 | 039/312 | T2 WV BRDGEVLLE-CTTNWD 39/312 INS DAMS | TABLEMTN | ETL.1110.INSL.NCER | 2021-04-19 | 2021-04-19 | 2021-06-22 | 2022-04-19 | 2022-04-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Steel | Install | 44873632 | T2 WV BRDGEVLLE-CTTNWD 39/312 INS DAMS | ICS
LC | 120846019 | 021/084 | T2 EI DIABLO-MIDWAY #2 -21/084 RPR STRT | PISMOBCH | ETL.5970.TOWR | 2021-04-19 | 2021-04-19 | 2022-05-26 | 2022-04-19 | 2022-04-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45073724 | T2 EI DIABLO-MIDWAY #2 -21/084 RPR STRT | ICQ
LC | 120846242 | 006/052 | T2 EI SALT SPRNGS-TGR CRK 6/52 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-19 | 2021-04-19 | 2022-06-23 | 2022-04-19 | 2022-04-19 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540431 | T2 EI SALT SPRNGS-TGR CREK RPL INSS 18TW | 93K
LC | 120846271 | 006/053 | T2 EI SALT SPRNGS-TGR CRK 6/53 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-19 | 2021-04-19 | 2022-06-23 | 2022-04-19 | 2022-04-19 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540431 | T2 EI SALT SPRNGS-TGR CREK RPL INSS 18TW | 93K
LC | 120846801 | 006/055 | T2 EI SLT SPS-TGR CRK 6/55 RPR CNDS | VICTOR | ETL.3500.TOWR | 2021-04-19 | 2021-04-19 | 2022-06-23 | 2022-04-19 | 2022-04-19 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45155662 | T2 EI SLT SPS-TGR CRK 6/55 RPR CNDS | ICS
LC | 120846898 | 007/059 | T2 EI SALT SPRGS-TGR CRK 7/59 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-19 | 2021-04-19 | 2022-06-25 | 2022-04-19 | 2022-04-19 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31601311 | T2 EI SLT SPRNGS-TGR CRK 11/9 RPL INSS | 93K
LC | 120846960 | 007/062 | T2 EI SLT SPRNGS-TGR CRK 7/62 RPR STRT | VICTOR | ETL.3500.TOWR | 2021-04-19 | 2021-04-19 | 2022-03-29 | 2022-04-19 | 2022-04-19 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45177724 | T2 EI SLT SPRNGS-TGR CRK 7/62 RPR STRT | ICQ
LC | 120846963 | 079/402 | T2 EI MALIN-RND MTN #2 79/402 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-04-19 | 2021-04-19 | 2022-07-13 | 2022-04-19 | 2022-04-19 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215249 | T2 EI MALIN-RND MTN #2 79/402 RPR OPGW | ICS
LC | 120848552 | 012/108 | T2 EI PRADISE-TABLE MTN 12/108 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-20 | 2021-04-20 | 2021-07-19 | 2022-04-20 | 2022-04-20 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120848644 | 000/024 | T2 EI CTTNWD-BNTN #1 000/024 RPL STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-04-20 | 2021-04-20 | 2021-07-29 | 2022-04-20 | 2022-04-20 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31536497 | T2 EI CTTNWD-BNTN #1 000/21 RPL STRW | 70Y
LC | 120848828 | 013/110 | T2 EI PARADISE-TABLE MTN 13/110 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-20 | 2021-04-20 | 2021-07-19 | 2022-04-20 | 2022-04-20 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120848843 | 006/006 | T2 EI SALINAS-FORT ORD #2 6/6 REPL SPLS | MOSSLNDG | ETL.8423.INSL.CERA | 2021-04-20 | 2021-04-20 | 2022-04-19 | 2022-04-20 | 2022-04-20 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP SUBS COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Steel | Replace | 45122597 | T2 EI SALINAS-FORT ORD #2 6/6 REPL SPLS | ICS
LC | 120848867 | 006/006 | T2 EI SALINAS-FORT ORD #1 6/6 RPR SPLS | MOSSLNDG | ETL.7890.INSL.CERA | 2021-04-20 | 2021-04-20 | 2022-05-11 | 2022-04-20 | 2022-04-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP SUBS COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45223970 | T2 EI SALINAS-FORT ORD #1 6/6 RPR SPLS | ICS
LC | 120849406 | 006/008 | T2 EI SNS-FRT ORD #2 6/8 RPL ANCS CMPLTD | MOSSLNDG | ETL.8423.POLE.NWOD | 2021-04-20 | 2021-04-20 | 2022-05-17 | 2022-04-20 | 2022-04-20 | Late | 93Z | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP SUBS COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Steel | Replace | 31600219 | T2 EI SLNS-FRT ORD #2 6/8 RPL ANCS | 93Z
LC | 120849544 | 019/610 | T2 EI SPLDNG-SMIT 19/610 RPR STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-20 | 2021-04-20 | 2021-08-30 | 2022-04-20 | 2022-04-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44764673 | T2 EI SPLDNG-SMIT 19/610 RPR STRW | ICW
LC | 120849612 | 006/107 | T2 EI CNTRVLLE-TBLE MTN 6/107 RPR STRW | TABLEMTN | ETL.6320.POLE.WOOD | 2021-04-20 | 2021-04-20 | 2022-02-25 | 2022-04-20 | 2022-04-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45197476 | T2 EI CNTRVLLE-TBLE MTN 6/107 RPR STRW | ICW
LC | 120849997 | 006/010 | T2 EI SLNS-FRT ORD #2 6/10 RMV VEG | MOSSLNDG | ETL.8423.POLE.NWOD | 2021-04-20 | 2021-04-20 | 2022-01-18 | 2022-04-20 | 2022-04-20 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP SUBS COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120849998 | 006/010 | T2 EI SLNS-FRT ORD #2 6/10 RPL GYWW | MOSSLNDG | ETL.8423.POLE.NWOD | 2021-04-20 | 2021-04-20 | 2022-05-11 | 2022-04-20 | 2022-04-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP SUBS COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Replace | 45122598 | T2 EI SLNS-FRT ORD #2 6/10 RPL GYWW | ICS
LC | 120850134 | 003/030 | T2 HAT CREEK #1-PIT #1 003/030 RPL POLE | TABLEMTN | ETL.7020.POLE.WOOD | 2021-04-20 | 2021-04-20 | 2021-10-19 | 2022-04-20 | 2022-04-20 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31545142 | T2 HAT CREEK #1-PIT #1 003/030 RPL POLE | 70Y
LC | 120850192 | 005/043 | T2 DI PARADISE-TABLE MTN 5/43 RPR FOND | TABLEMTN | ETL.4316.TOWR | 2021-04-20 | 2021-04-12 | 2021-06-09 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44851314 | T2 DI PARADISE-TABLE MTN 5/43 RPR FOND | ICQ
LC | 120850197 | 006/028 | T2 DI MORRO BAY-SOLAR#1 6/28 RMV VEGN | PISMOBCH | ETL.5300.TOWR | 2021-04-20 | 2021-04-12 | 2022-01-24 | 2022-04-12 | 2022-04-12 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 120850198 | 005/042 | T2 DI PARADISE-TABLE MTN 5/42 RPR FOND | TABLEMTN | ETL.4316.TOWR | 2021-04-20 | 2021-04-12 | 2021-06-09 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44851312 | T2 DI PARADISE-TABLE MTN 5/42 RPR FOND | ICQ
LC | 120850199 | 005/042 | T2 DI PARADISE-TABLE MTN 5/42 INS STEP | TABLEMTN | ETL.4316.TOWR | 2021-04-20 | 2021-04-12 | 2021-06-09 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Tower | Install | 44851313 | T2 DI PARADISE-TABLE MTN 5/42 INS STEP | ICQ
LC | 120850238 | 021/123 | T2 EI STAN-MAN #2 21/123 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-20 | 2021-04-20 | 2022-02-14 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123121 | T2 EI STAN-MAN #2 21/123 RPR FOND | ICQ
LC | 120850290 | 019/603 | T2 EI SPLDNG-SMMT 19/603 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-04-20 | 2021-04-20 | 2021-08-30 | 2022-04-20 | 2022-04-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44764677 | T2 EI SPLDNG-SMMT 19/603 RPR GYWW | ICW
LC | 120850397 | 026/173 | T2 DI POE-RIO OSO 26/173 RPL INSS | TABLEMTN | ETL.5540.INSL | 2021-04-20 | 2021-04-13 | 2022-08-10 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546766 | T2 DI POE-RIO OSO RPL INSS 7 TWRS | 93K
LC | 120850507 | 011/079 | T2 DI VC-VCVL-JMSN-N. TWR 11/79 INS HRDT | LAKEVLLE | ETL.4100.TOWR | 2021-04-20 | 2021-04-12 | 2022-02-02 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45160865 | T2 DI VC-VCVL-JMSN-N. TWR 11/79 INS HRDT | ICQ
LC | 120850905 | 003/081 | T2 EI COLGATE-ALLEGHANY 3/081 RPR WDPKR | SACTO | ETL.6470.POLE.WOOD | 2021-04-20 | 2021-04-20 | 2021-08-07 | 2022-04-20 | 2022-04-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44808048 | T2 EI COLGATE-ALLEGHANY 3/081 RPR WDPKR | ICW
LC | 120850929 | 004/040 | T2 HAT CREEK #1-PIT #1 004/040 REFRAME | TABLEMTN | ETL.7020.POLE.WOOD | 2021-04-20 | 2021-04-20 | 2021-06-26 | 2022-04-20 | 2022-04-20 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31537112 | T2 HAT CREEK #1-PIT #1 004/040 REFRAME | 93E
LC | 120850960 | 012/114 | T2 DI EL DRD-MSSR FLT #2 12/114 COMPLETE | SACTO | ETL.1540.INSL | 2021-04-20 | 2021-04-13 | 2022-05-23 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547631 | T2 WV EL DORADO-MSR FLT #2 RPL INSS 10TW | 93K
LC | 120850969 | 018/085 | T2 DI MOSS LANDING-COBURN 18/85 COMPLETE | MOSSLNDG | ETL.5330.TOWR | 2021-04-20 | 2021-04-13 | 2022-05-17 | 2022-04-13 | 2022-04-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45120454 | T2 DI MOSS LANDING-COBURN 18/85 RPR FOND | ICQ
LC | 120851064 | ;010/091 | T2 DI PARADISE-TABLE MTN ;10/91 RPR FOND | TABLEMTN | ETL.4316.TOWR | 2021-04-20 | 2021-04-13 | 2021-06-11 | 2022-04-13 | 2022-04-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44856964 | T2 DI PARADISE-TABLE MTN ;10/91 RPR FOND | ICQ
LC | 120851067 | ;010/091 | T2 DI PARADISE-TABLE MTN ;10/91 INS HRDT | TABLEMTN | ETL.4316.TOWR | 2021-04-20 | 2021-04-13 | 2021-06-11 | 2022-04-13 | 2022-04-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Tower | Install | 44856965 | T2 DI PARADISE-TABLE MTN ;10/91 INS HRDT | ICQ
LC | 120851080 | 005/061 | T2 HAT CREEK #1-PIT #1 005/061 REFRAME | TABLEMTN | ETL.7020.POLE.WOOD | 2021-04-20 | 2021-04-20 | 2021-06-26 | 2022-04-20 | 2022-04-20 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31537112 | T2 HAT CREEK #1-PIT #1 004/040 REFRAME | 93E
LC | 120851227 | 007/000 | T2 EI SALINAS-FORT ORD#2 7/0 RPR SPLS | MOSSLNDG | ETL.8423.INSL.CERA | 2021-04-20 | 2021-04-20 | 2022-05-12 | 2022-04-20 | 2022-04-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP SUBS COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122599 | T2 EI SALINAS-FORT ORD#2 7/0 RPR SPLS | ICS
LC | 120851292 | 112/000 | T2 EI HUMBOLDT-TRINITY 112/000 RMV VEG | EUREKA | ETL.1820.POLE.WOOD | 2021-04-20 | 2021-04-20 | 2022-05-24 | 2022-04-20 | 2022-04-20 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120851364 | 018/594 | T2 EI SPLDNG-SMMT 18/594 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-04-20 | 2021-04-20 | 2021-08-24 | 2022-04-20 | 2022-04-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44764676 | T2 EI SPLDNG-SMMT 18/594 RPR GYWW | ICW
LC | 120851556 | 011/095 | T2 DI PARADISE-TABLE MTN 11/95 RPL HRDT | TABLEMTN | ETL.4316.TOWR | 2021-04-20 | 2021-04-13 | 2021-05-19 | 2022-04-13 | 2022-04-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44816365 | T2 DI PARADISE-TABLE MTN 11/95 RPL HRDT | ICQ
LC | 120851579 | 018/591 | T2 EI SPLDNG-SMMT 18/591 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-04-20 | 2021-04-20 | 2021-08-25 | 2022-04-20 | 2022-04-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44764678 | T2 EI SPLDNG-SMMT 18/591 RPR GYWW | ICW
LC | 120851604 | 007/082 | T2 EI DRUM-SUMMIT #1 007/082L RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2021-04-20 | 2021-04-20 | 2022-08-21 | 2022-04-20 | 2022-04-20 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544924 | T3 EI DRUM-SUMMIT #1 000/007 RPL STRW | 70Y
LC | 120851665 | 003/029 | T2 EI WISHN-CPPERMINE 003/029 UNBURY | FRESNO | ETL.9330.TOWR | 2021-04-20 | 2021-04-20 | 2021-06-30 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44839763 | T2 EI WISHN-CPPERMINE 003/029 UNBURY | ICQ
LC | 120851736 | 007/082 | T2 EI DRUM-SUMMIT #1 7/082R RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2021-04-20 | 2021-04-20 | 2022-08-21 | 2022-04-20 | 2022-04-20 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544924 | T3 EI DRUM-SUMMIT #1 000/007 RPL STRW | 70Y
LC | 120851748 | 035/239A | T2 EI TRINITY-COTTONWD 35/239A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2021-04-20 | 2021-04-20 | 2021-08-31 | 2022-04-20 | 2022-04-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873880 | T2 EI TRINITY-COTTONWD 35/239A RPR GYWW | ICW
LC | 120851801 | 035/239B | T2 EI TRINITY-COTTONWD 35/239B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2021-04-20 | 2021-04-20 | 2021-08-29 | 2022-04-20 | 2022-04-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44905931 | T2 EI TRINITY-COTTONWD 35/239B RPR GYWW | ICW
LC | 120851847 | 007/083A | T2 EI DRUM-SUMMIT #1 7/083A RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2021-04-20 | 2021-04-20 | 2022-06-13 | 2022-04-20 | 2022-04-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45073789 | T2 EI DRUM-SUMMIT #1 7/083A RPR GYWW | ICW
LC | 120851964 | 007/083C | T2 EI DRUM-SUMMIT #1 007/083C RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2021-04-20 | 2021-04-20 | 2022-06-13 | 2022-04-20 | 2022-04-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45073790 | T2 EI DRUM-SUMMIT #1 007/083C RPR GYWW | ICW
LC | 120852664 | 007/002 | T2 EI SLNS-FRT ORD #2 7/2 RMV VEG | MOSSLNDG | ETL.8423.POLE.NWOD | 2021-04-20 | 2021-04-20 | 2022-01-18 | 2022-04-20 | 2022-04-20 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP SUBS COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120852988 | 111/007 | T2 EI HUMBOLDT-TRINITY 111/007 RMV VEG | EUREKA | ETL.1820.TOWR | 2021-04-20 | 2021-04-20 | 2022-06-24 | 2022-04-20 | 2022-04-20 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120853086 | 019/088 | T2 DI MS LNDNG-LS AGUILAS 19/88 RPL INSS | MOSSLNDG | ETL.5340.INSL | 2021-04-20 | 2021-04-13 | 2022-10-19 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31539341 | T2 EI MSS LNDG-LS AGLS SW RPL INSS 6TWR | 93K
LC | 120853089 | 019/088 | T2 DI MSS LNDNG-LS AGLS 19/88 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-04-20 | 2021-04-13 | 2022-05-17 | 2022-04-13 | 2022-04-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45120455 | T2 DI MSS LNDNG-LS AGLS 19/88 RPR FOND | ICQ
LC | 120853152 | 111/006 | T2 EI HUMBOLDT-TRINITY 111/006 RPR FOND | EUREKA | ETL.1820.TOWR | 2021-04-20 | 2021-04-20 | 2022-07-29 | 2022-04-20 | 2022-04-20 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45079483 | T2 EI HUMBOLDT-TRINITY 111/006 RPR FOND | ICQ
LC | 120853547 | 026/170 | T2 DI POE-RIO OSO 26/170 RPL HRDT | TABLEMTN | ETL.5540.TOWR | 2021-04-20 | 2021-04-13 | 2022-02-02 | 2022-04-13 | 2022-04-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45160910 | T2 DI POE-RIO OSO 26/170 RPL HRDT | ICQ
LC | 120853549 | 026/170 | T2 DI POE-RIO OSO 26/170 RPR STRT | TABLEMTN | ETL.5540.TOWR | 2021-04-20 | 2021-04-13 | 2022-02-02 | 2022-04-13 | 2022-04-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45144694 | T2 DI POE-RIO OSO 26/170 RPR STRT | ICQ
LC | 120853943 | 048/347 | T2 DI CARIBOU-TABLE MTN 48/347 RPLC INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-04-20 | 2021-04-12 | 2022-06-15 | 2022-04-12 | 2022-04-12 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 120854184 | 003/080 | T2 EI COLGATE-ALLEGHANY 3/80 REFRAME | SACTO | ETL.6470.POLE.WOOD | 2021-04-20 | 2021-04-20 | 2021-08-07 | 2022-04-20 | 2022-04-20 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31537105 | T2 EI COLGATE-ALLEGHANY 3/80 REFRAME | 93E
LC | 120854188 | 001/013 | T2 EI SALT SPRNGS-TGR CREK 1/13 RPR FOND | VICTOR | ETL.3500.TOWR | 2021-04-20 | 2021-04-20 | 2022-03-31 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45150398 | T2 EI SALT SPRNGS-TGR CREK 1/13 RPR FOND | ICQ
LC | 120854211 | 001/012 | T2 EI SALT SPRNGS-TGR CREK 1/12 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-20 | 2021-04-20 | 2022-06-19 | 2022-04-20 | 2022-04-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540431 | T2 EI SALT SPRNGS-TGR CREK RPL INSS 18TW | 93K
LC | 120854345 | 010/048 | T2 DI FULTON-PUEBLO 10/48 RPL INSS | LAKEVLLE | ETL.1600.INSL.NCER | 2021-04-20 | 2021-04-12 | 2022-02-24 | 2022-04-12 | 2022-04-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 120854346 | 010/048 | T2 DI SILVERADO-FLTN JCT 10/48 RPL INSS | LAKEVLLE | ETL.1610.INSL.NCER | 2021-04-20 | 2021-04-12 | 2022-03-13 | 2022-04-12 | 2022-04-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548684 | T2 DI SILVERADO-FUTON JCT RPL INSS 6TWR | 93K
LC | 120854492 | 001/018 | T2 EI SALT SPGS-TIGER CRK 1/18 RPR FOND | VICTOR | ETL.3500.TOWR | 2021-04-20 | 2021-04-20 | 2022-03-30 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45150399 | T2 EI SALT SPGS-TIGER CRK 1/18 RPR FOND | ICQ
LC | 120854493 | 001/017 | T2 EI SALT SPRNGS-TGR CREK 1/17 RPR FOND | VICTOR | ETL.3500.TOWR | 2021-04-20 | 2021-04-20 | 2022-03-30 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45150400 | T2 EI SALT SPRNGS-TGR CREK 1/17 RPR FOND | ICQ
LC | 120854540 | C018/074 | T2 DI CBRN-LS AGLS SW ST C18/74 RPL INSS | MOSSLNDG | ETL.4460.INSL | 2021-04-20 | 2021-04-13 | 2021-11-20 | 2022-04-13 | 2022-04-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31527944 | DI CBN-LS AGLS SW ST-PCH RPL INSS 13TWRS | 93K
LC | 120854549 | 005/048 | T2 DI PARADISE-TABLE MTN 5/48 RPR FOND | TABLEMTN | ETL.4316.TOWR | 2021-04-20 | 2021-04-12 | 2021-06-09 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44851315 | T2 DI PARADISE-TABLE MTN 5/48 RPR FOND | ICQ
LC | 120854570 | 002/020 | T2 EI SALT SPRNGS-TGR CREK 2/20 RPR STRT | VICTOR | ETL.3500.TOWR | 2021-04-20 | 2021-04-20 | 2022-03-30 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45150402 | T2 EI SALT SPRNGS-TGR CREK 2/20 RPR STRT | ICQ
LC | 120854650 | 001/010 | T2 EI SLT SPS-TGR CK 1/10 BENT STL CMPLT | VICTOR | ETL.3500.TOWR | 2021-04-20 | 2021-04-20 | 2022-04-28 | 2022-04-20 | 2022-04-20 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45150403 | T2 EI SALT SPGS-TIGER CRK 1/10 BENT STL | ICQ
LC | 120854895 | 009/069 | T2 DI VC-VACVILLE-JMESN-NH 9/69 RPL INSS | LAKEVLLE | ETL.4100.INSL.CERA | 2021-04-20 | 2021-04-13 | 2022-02-25 | 2022-04-13 | 2022-04-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549400 | T2 DI VC-VACVILLE-JMESN-NH RPL INSS 5TWR | 93K
LC | 120855380 | :006/001 | T2 DI BLLT-RVRBK-MLS SWT :006/1 RPR STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-04-20 | 2021-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45155667 | T2 DI BLLT-RVRBK-MLS SWT :006/1 RPR STRW | ICW
LC | 120855381 | :006/001 | T2 DI BLLT-RVRBK-MLS SWT :006/1 RPL INSW | VICTOR | ETL.1070.INSL.NCER | 2021-04-20 | 2021-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-12 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31539420 | T2 DI BLLT-RBK-MLS SWS :005/006 RPL INSW | 93I
LC | 120855779 | 004/029 | T2 DI VACA-BAHIA 004/029 RPL INSS | SACTO | ETL.5810.INSL | 2021-04-20 | 2021-04-20 | 2022-07-24 | 2022-04-20 | 2022-04-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31530364 | DI VACA-BAHIA REPL INSS 5 TWRS. | 93K
LC | 120857397 | 009/073 | T2 DI SLT SPRNGS-TGR CRK 9/73 INS HRDT | VICTOR | ETL.3500.TOWR | 2021-04-21 | 2021-04-20 | 2022-03-21 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45150404 | T2 DI SLT SPRNGS-TGR CRK 9/73 INS HRDT | ICQ
LC | 120857447 | 112/004 | T2 EI HUMBOLDT TRNTY 112/004 RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-04-21 | 2021-04-20 | 2022-05-11 | 2022-04-20 | 2022-04-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45079484 | T2 EI HUMBOLDT TRNTY 112/004 RPR STRW | ICW
LC | 120857766 | :016/084 | T2 DI CZY HRS CYN-SLS-SD :16/84 RPL INSS | MOSSLNDG | ETL.2900.INSL.CERA | 2021-04-21 | 2021-04-20 | 2021-07-18 | 2022-04-20 | 2022-04-20 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31527952 | DI CRZYHS CNY-SLS-SLD #1 RPL INSS 4TWRS | 93K
LC | 120857877 | 003/079 | T2 EI COLGATE-ALLEGHANY 3/079 RPR WDPKR | SACTO | ETL.6470.POLE.WOOD | 2021-04-21 | 2021-04-21 | 2021-08-05 | 2022-04-21 | 2022-04-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44808047 | T2 EI COLGATE-ALLEGHANY 3/079 RPR WDPKR | ICW
LC | 120858090 | 018/590 | T2 EI SPAULDING-SUMMIT 18/590 RPR WDPKR | SACTO | ETL.8060.POLE.WOOD | 2021-04-21 | 2021-04-21 | 2021-08-25 | 2022-04-21 | 2022-04-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44808354 | T2 EI SPAULDING-SUMMIT 18/590 RPR WDPKR | ICW
LC | 120858169 | 009/072 | T2 DI SLT SPRNGS-TGR CRK 9/72 RPLC HRDT | VICTOR | ETL.3500.TOWR | 2021-04-21 | 2021-04-20 | 2022-03-21 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45150390 | T2 DI SLT SPRNGS-TGR CRK 9/72 RPLC HRDT | ICQ
LC | 120858214 | 018/085 | T2 DI MOSS LANDING-COBURN 18/85 RPL INSS | MOSSLNDG | ETL.5330.INSL | 2021-04-21 | 2021-04-13 | 2022-04-14 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536364 | DI MOSS LANDING-COBURN RPL INSS 15TWR | 93K
LC | 120858216 | 021/096 | T2 MORRO BAY-MESA 21/96 RPL DAMPER | PISMOBCH | ETL.5290.INSL.CERA | 2021-04-21 | 2021-03-31 | 2021-09-22 | 2022-03-31 | 2022-03-31 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Damper-Steel | Replace | 44963085 | T2 MORRO BAY-MESA 21/96 RPL DAMPER | ICS
LC | 120858253 | 004/035 | T2 DI ELDORADO-MSR FLT #1 4/35 RPR SPLS | SACTO | ETL.1530.INSL | 2021-04-21 | 2021-04-20 | 2022-06-17 | 2022-04-20 | 2022-04-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 44764483 | T2 DI ELDORADO-MSR FLT #1 4/35 RPR SPLS | ICS
LC | 120858322 | 003/078 | T2 EI COLGATE-ALLEGHANY 3/78 RPL INSW | SACTO | ETL.6470.INSL.CERA | 2021-04-21 | 2021-04-21 | 2021-08-05 | 2022-04-21 | 2022-04-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537434 | T2 EI COLGATE-ALLEGHANY 1/31 RPL INSW | 93I
LC | 120858334 | 008/009 | T2 DI SALINAS-FORT ORD #2 8/9 RPR SPLS | MOSSLNDG | ETL.7890.INSL.CERA | 2021-04-21 | 2021-04-20 | 2022-05-12 | 2022-04-20 | 2022-04-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45232806 | T2 DI SALINAS-FORT ORD #2 8/9 RPR SPLS | ICS
LC | 120858629 | 006/044 | T2 EI WISHON-COPPERMINE 006/044 UNBURY | FRESNO | ETL.9330.TOWR | 2021-04-21 | 2021-04-21 | 2021-07-08 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44839764 | T2 EI WISHON-COPPERMINE 006/044 UNBURY | ICQ
LC | 120858830 | 004/029 | T2 DI EL DRD-MSSR FLT #2 4/29 RPL SPLS | SACTO | ETL.1540.INSL.CERA | 2021-04-21 | 2021-04-20 | 2022-05-17 | 2022-04-20 | 2022-04-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 44764486 | T2 DI EL DRD-MSSR FLT #2 4/29 RPL SPLS | ICS
LC | 120858832 | 004/029 | T2 DI EL DRD-MSSR FLT #1 4/29 RPR SPLS | SACTO | ETL.1530.INSL.CERA | 2021-04-21 | 2021-04-20 | 2022-06-17 | 2022-04-20 | 2022-04-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 44764484 | T2 DI EL DRD-MSSR FLT #1 4/29 RPR SPLS | ICS
LC | 120858844 | 003/076 | T2 EI COLGATE-ALLEGHANY 3/76 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2021-04-21 | 2021-04-21 | 2021-08-04 | 2022-04-21 | 2022-04-21 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31531502 | T3 DI COLGATE-ALLGHNY 14/395 RPL STRW | 70Y
LC | 120859013 | 008/065 | T2 DI VAC-VCVL-JMSN-N. TWR 8/65 RPR FOND | LAKEVLLE | ETL.4100.TOWR | 2021-04-21 | 2021-04-13 | 2022-02-07 | 2022-04-13 | 2022-04-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45161083 | T2 DI VAC-VCVL-JMSN-N. TWR 8/65 RPR FOND | ICQ
LC | 120859169 | 003/075 | T2 EI COLGATE-ALLEGHANY 3/75 RPL INSW | SACTO | ETL.6470.INSL.CERA | 2021-04-21 | 2021-04-21 | 2021-08-04 | 2022-04-21 | 2022-04-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537434 | T2 EI COLGATE-ALLEGHANY 1/31 RPL INSW | 93I
LC | 120859257 | 016/514 | T2 EI SPAULDING-SUMMIT 16/514 INST DAMPR | SACTO | ETL.8060.POLE.WOOD | 2021-04-21 | 2021-04-21 | 2021-08-28 | 2022-04-21 | 2022-04-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Splice-Wood | Repair | 44764668 | T2 EI SPAULDING-SUMMIT 16/514 INST DAMPR | ICW
LC | 120859391 | 002/074 | T2 EI COLGATE-ALLEGHANY 2/74 REFRAME | SACTO | ETL.6470.POLE.WOOD | 2021-04-21 | 2021-04-21 | 2021-08-04 | 2022-04-21 | 2022-04-21 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31549891 | T2 EI COLGATE-ALLEGHANY 1/44 REFRAME | 93E
LC | 120859460 | 003/024 | T2 EI WISHON-COPPERMINE 3/24 RPR FOND | FRESNO | ETL.9330.TOWR | 2021-04-21 | 2021-04-21 | 2021-07-01 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44839765 | T2 EI WISHON-COPPERMINE 3/24 RPR FOND | ICQ
LC | 120859466 | 009/090 | T2 WV BRDGEVLLE-CTTNWD 9/90 RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2021-04-21 | 2021-04-21 | 2021-06-29 | 2022-04-21 | 2022-04-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44873803 | T2 WV BRDGEVLLE-CTTNWD 9/90 RPR ADSS | ICS
LC | 120859470 | 006/011 | T2 DI BRCBRG JCT-MRPS TP 6/11 RPL STRW | FRESNO | ETL.8651.POLE.WOOD | 2021-04-21 | 2021-04-12 | 2022-02-02 | 2022-04-12 | 2022-04-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31587924 | T2 BRCBRG JCT-MRPS TAP 07/9 RPL STRW | 70Y
LC | 120859592 | 003/025 | T2 EI WISHON-COPPERMINE 3/25 RPR STRT | FRESNO | ETL.9330.TOWR | 2021-04-21 | 2021-04-21 | 2021-07-01 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair | 44839766 | T2 EI WISHON-COPPERMINE 3/25 RPR STRT | ICQ
LC | 120859631 | 002/073 | T2 EI COLGATE-ALLEGHANY 2/73 REFRAME | SACTO | ETL.6470.POLE.WOOD | 2021-04-21 | 2021-04-21 | 2021-08-04 | 2022-04-21 | 2022-04-21 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31541791 | T3 EI COLGATE-ALLEGHANY 10/273 REFRAME | 93E
LC | 120859698 | 003/026 | T2 EI WISHON-COPPERMINE 3/26 RPR FOND | FRESNO | ETL.9330.TOWR | 2021-04-21 | 2021-04-21 | 2021-06-30 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44839767 | T2 EI WISHON-COPPERMINE 3/26 RPR FOND | ICQ
LC | 120859772 | 049/353 | T2 DI CRB-TABLE MUNTIN 49/353 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-04-21 | 2021-04-13 | 2022-06-16 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 120859777 | 041/177 | T2 DI FULTON-LAKEVILLE 041/177 RPR FOND | LAKEVLLE | ETL.4950.TOWR | 2021-04-21 | 2021-04-13 | 2022-01-25 | 2022-04-13 | 2022-04-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45147953 | T2 DI FULTON-LAKEVILLE 041/177 RPR FOND | ICQ
LC | 120859812 | 003/027 | T2 EI WISHON-COPPERMINE 003/027 RMV VEG | FRESNO | ETL.9330.TOWR | 2021-04-21 | 2021-04-21 | 2022-08-26 | 2022-04-21 | 2022-04-21 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120859853 | 050/357 | T2 DI CARIBOU-TABLE MTN 50/357 RPR INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-04-21 | 2021-04-13 | 2022-06-17 | 2022-04-13 | 2022-04-13 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45212347 | T2 DI CARIBOU-TABLE MTN 50/357 RPR INSS | ICS
LC | 120859883 | 111/001C | T2 EI HUMBLDT-TRINTY 111/1C RMV VEG | EUREKA | ETL.1820.POLE.NWOD | 2021-04-21 | 2021-04-21 | 2022-03-18 | 2022-04-21 | 2022-04-21 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120859991 | :023/123 | T2 DI CZY HRS CN-SNS-SLD :23/123 RPL INS | MOSSLNDG | ETL.2910.INSL.NCER | 2021-04-21 | 2021-04-13 | 2022-03-11 | 2022-04-13 | 2022-04-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528632 | DI CRZY HRS CYN-SLNS-SLD2 RPL INSS 6TWR | 93K
LC | 120860044 | 004/006 | T2 DI MELONES-RACETRACK 4/6 CORONA | VICTOR | ETL.2400.INSL.NCER | 2021-04-21 | 2021-04-13 | 2022-04-26 | 2022-04-13 | 2022-04-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45121563 | T2 DI MELONES-RACETRACK 4/6 CORONA | ICW
LC | 120860161 | 036/317 | T2 EI PIT #1-COTTONWOOD 36/317 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-04-21 | 2021-04-21 | 2022-08-02 | 2022-04-21 | 2022-04-21 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45198317 | T2 EI PIT #1-COTTONWOOD 36/317 RPR FOND | ICQ
LC | 120860251 | 018/104 | T2 EI STNSLS-MNTC #2 18/104 PNT STRT | VICTOR | ETL.3820.TOWR | 2021-04-21 | 2021-04-21 | 2022-10-21 | 2022-04-21 | 2022-04-21 | Late | ICX | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Paint/Coating | Structure-Tower | Repaint | 45234389 | 2022 PAINT TAGS (MULTIPLE LOCATIONS) | ICX
LC | 120860288 | 035/236 | T2 EI TRINITY-CTTNWD 35/236A RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-21 | 2021-04-21 | 2021-08-29 | 2022-04-21 | 2022-04-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873935 | T2 EI TRINITY-CTTNWD 35/236A RPR GYWW | ICW
LC | 120860306 | 035/236 | T2 EI TRINITY-CTTNWD 35/236B RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-21 | 2021-04-21 | 2021-08-29 | 2022-04-21 | 2022-04-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873936 | T2 EI TRINITY-CTTNWD 35/236B RPR GYWW | ICW
LC | 120860343 | 035/236 | T2 EI TRINITY-CTTNWD 35/236C RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-21 | 2021-04-21 | 2021-08-29 | 2022-04-21 | 2022-04-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873937 | T2 EI TRINITY-CTTNWD 35/236C RPR GYWW | ICW
LC | 120860480 | 016/504 | T2 EI SPALDING-SUMMIT 16/504 RMV STEP | SACTO | ETL.8060.POLE.WOOD | 2021-04-21 | 2021-04-21 | 2021-08-18 | 2022-04-21 | 2022-04-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44808353 | T2 EI SPALDING-SUMMIT 16/504 RMV STEP | ICW
LC | 120860508 | 003/094 | T2 EI COLGATE-ALLEGHANY 003/094 RPL INSW | SACTO | ETL.6470.INSL.CERA | 2021-04-21 | 2021-04-21 | 2021-07-23 | 2022-04-21 | 2022-04-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537434 | T2 EI COLGATE-ALLEGHANY 1/31 RPL INSW | 93I
LC | 120860647 | 001/023 | T2 EI COLGATE-CHALLENGE 1/23 RPR SPLW | SACTO | ETL.6480.POLE.WOOD | 2021-04-21 | 2021-04-21 | 2021-06-11 | 2022-04-21 | 2022-04-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Replace | 44764574 | T2 EI COLGATE-CHALLENGE 1/23 RPR SPLW | ICW
LC | 120860654 | :001/009 | T2 DI STN ML SW ST-RBK JT :1/9 RPL INSS | VICTOR | ETL.3840.INSL.NCER | 2021-04-21 | 2021-04-20 | 2022-05-19 | 2022-04-20 | 2022-04-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546924 | T2 DI STNSLS-MLNS-MNTC RPL INSS 8TWRS | 93K
LC | 120860656 | :001/009 | T2 DI STNSLS-MLS SS-MTC #1 :1/9 RPL INSS | VICTOR | ETL.3830.INSL.NCER | 2021-04-21 | 2021-04-20 | 2021-12-18 | 2022-04-20 | 2022-04-20 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549338 | T2 DI STNSLS-MLNS-MNTC RPL INSS 8TWRS | 93K
LC | 120860659 | :001/009 | T2 DI STNSLS-MLS SS-MTC #1 :1/9 RPR STRT | VICTOR | ETL.3830.TOWR | 2021-04-21 | 2021-04-20 | 2022-02-16 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45107268 | T2 DI STNSLS-MLS SS-MTC #1 :1/9 RPR STRT | ICQ
LC | 120860711 | 112/001 | T2 EI HUMBOLDT-TRINITY 112/001R RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-04-21 | 2021-04-21 | 2022-10-07 | 2022-04-21 | 2022-04-21 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 120860712 | 112/001 | T2 EI HUMBOLDT TRINITY 112/001 RMV VEG | EUREKA | ETL.1820.POLE.WDPS | 2021-04-21 | 2021-04-21 | 2022-04-28 | 2022-04-21 | 2022-04-21 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120860715 | 112/001 | T2 EI HUMBOLDT-TRINITY 112/001L RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-04-21 | 2021-04-21 | 2022-10-07 | 2022-04-21 | 2022-04-21 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 120860719 | 019/002 | T2 EI EXCHEQUER-MARIPOSA 19/2 RPL STRW | FRESNO | ETL.8640.POLE.WOOD | 2021-04-21 | 2021-04-21 | 2022-02-05 | 2022-04-21 | 2022-04-21 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31539804 | T2 EI EXCHEQUER-MARIPOSA 19/2 RPL STRW | 70Y
LC | 120860794 | 007/011 | T2 EI SALINAS-FORT ORD #2 7/011 RMV VEG | MOSSLNDG | ETL.8423.POLE.NWOD | 2021-04-21 | 2021-04-21 | 2022-01-18 | 2022-04-21 | 2022-04-21 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP SUBS COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120860886 | 018/112 | T2 EI STN-MLN MAN #1 18/112 UNBURY | VICTOR | ETL.3830.TOWR | 2021-04-21 | 2021-04-21 | 2022-02-09 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123112 | T2 EI STN-MLN MAN #1 18/112 UNBURY | ICQ
LC | 120860995 | 016/118 | T2 DI HELMS-GREGG #2 16/118 RPL INSS | FRESNO | ETL.4880.INSL | 2021-04-21 | 2021-04-20 | 2022-08-06 | 2022-04-20 | 2022-04-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514720 | HELMS-GREGG #2 REP INS 8TWRS | 93K
LC | 120861091 | 009/078 | T2 EI PARADISE-TABLE MTN 9/078 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-21 | 2021-04-21 | 2021-07-17 | 2022-04-21 | 2022-04-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120861098 | 013/124 | T2 WV BRDGEVLLE-CTTNWD 13/124 RPR ADSS | TABLEMTN | ETL.1110.POLE.STPS | 2021-04-21 | 2021-04-21 | 2021-06-30 | 2022-04-21 | 2022-04-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44873637 | T2 WV BRDGEVLLE-CTTNWD 13/124 RPR ADSS | ICS
LC | 120861175 | :021/112 | T2 DI CHC-SAL-SOL :21/112 RMV NEST | MOSSLNDG | ETL.2900.TOWR | 2021-04-21 | 2021-04-20 | 2021-05-26 | 2022-04-20 | 2022-04-20 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Steel | Remove | 44805765 | T2 DI CHC-SAL-SOL :21/112 RMV NEST | ICS
LC | 120861178 | :021/112 | T2 DI CHC-SAL-SOL :21/112 STEP BOLT | MOSSLNDG | ETL.2900.TOWR | 2021-04-21 | 2021-04-20 | 2021-05-27 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Tower | Install | 44842504 | T2 DI CHC-SAL-SOL :21/112 STEP BOLT | ICQ
LC | 120861256 | 015/062 | T2 EI PITTSBURG-SAN MATEO 15/62 RPR FOND | CONCORD | ETL.5463.TOWR | 2021-04-21 | 2021-04-21 | 2022-03-17 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45179272 | T2 EI PITTSBURG-SAN MATEO 15/62 RPR FOND | ICQ
LC | 120861281 | ;010/090 | T2 EI PARADISE-TABLE MTN ;10/90 RPL INSS | TABLEMTN | ETL.4316.TOWR | 2021-04-21 | 2021-04-21 | 2021-07-18 | 2022-04-21 | 2022-04-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120861299 | ;010/091 | T2 EI PARADISE-TABLE MTN ;10/91 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-21 | 2021-04-21 | 2021-07-18 | 2022-04-21 | 2022-04-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120861322 | 018/125 | T2 DI HELMS-GREGG #2 018/125 RPR INSS | FRESNO | ETL.4880.INSL | 2021-04-21 | 2021-04-21 | 2022-08-04 | 2022-04-21 | 2022-04-21 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45067699 | T2 DI HELMS-GREGG #2 018/125 RPR INSS | ICS
LC | 120861325 | 003/028 | T2 DI MORAGA-OAKLAND #4 3/28 RPL INSS | CONCORD | ETL.2750.INSL.NCER | 2021-04-21 | 2021-04-21 | 2022-07-09 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547719 | DI MORAGA-OAKLAND #4 RPL INSS 5TWRS | 93K
LC | 120861328 | 003/028 | T2 DI MORAGA-OAKLAND #3 3/28 RPL INSS | CONCORD | ETL.2740.INSL.NCER | 2021-04-21 | 2021-04-21 | 2022-07-08 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547469 | T2 EI MORAGA-OAKLAND #3 RPL INSS 5TWRS | 93K
LC | 120861814 | 034/234 | T2 EI TRINITY-COTTNWD 34/234 RPR GYWS | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-21 | 2021-04-21 | 2022-06-24 | 2022-04-21 | 2022-04-21 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45211990 | T2 EI TRINITY-COTTNWD 34/234 RPR GYWS | ICS
LC | 120861873 | 076/386 | T2 EI MLN-RND MT #2 76/386 RPR SHLS/OPGW | TABLEMTN | ETL.6020.INSL.NCER | 2021-04-21 | 2021-04-21 | 2022-07-13 | 2022-04-21 | 2022-04-21 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215248 | T2 EI MLN-RND MT #2 76/386 RPR SHLS/OPGW | ICS
LC | 120861946 | 077/390 | T2 EI MALIN-RND MTN #2 77/390 RPL INSS | TABLEMTN | ETL.6020.INSL | 2021-04-21 | 2021-04-21 | 2021-06-13 | 2022-04-21 | 2022-04-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31543342 | T2 EI MALIN-RND MTN #2 77/390 RPL INSS | 93K
LC | 120862241 | 002/023 | T2 EI SALT SPRNGS-TGR CREK 2/23 RPR FOND | VICTOR | ETL.3500.TOWR | 2021-04-21 | 2021-04-21 | 2022-03-31 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45150406 | T2 EI SALT SPRNGS-TGR CREK 2/23 RPR FOND | ICQ
LC | 120862242 | 002/023 | T2 EI SALT SPRNGS-TGR CREK 2/23 RPR STRT | VICTOR | ETL.3500.TOWR | 2021-04-21 | 2021-04-21 | 2022-03-30 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45150407 | T2 EI SALT SPRNGS-TGR CREK 2/23 RPR STRT | ICQ
LC | 120862268 | 003/030 | T2 EI SALT SPRNGS-TGR CREK 3/30 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-21 | 2021-04-21 | 2022-06-21 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540431 | T2 EI SALT SPRNGS-TGR CREK RPL INSS 18TW | 93K
LC | 120862407 | 066/330 | T2 EI MALIN-RND MTN #2 66/330 RPR STRT | TABLEMTN | ETL.6020.TOWR | 2021-04-21 | 2021-04-21 | 2022-07-20 | 2022-04-21 | 2022-04-21 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45194359 | T2 EI MALIN-RND MTN #2 66/330 RPR STRT | ICQ
LC | 120862408 | 065/329 | T2 EI MALIN-RND MTN #2 65/329A RPR STRT | TABLEMTN | ETL.6020.TOWR | 2021-04-21 | 2021-04-21 | 2022-08-05 | 2022-04-21 | 2022-04-21 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45194353 | T2 EI MALIN-RND MTN #2 65/329A RPR STRT | ICQ
LC | 120862455 | 110/003B | T2 EI HUMBOLDT-TRINITY 110/003B RPL POLE | EUREKA | ETL.1820.POLE.WOOD | 2021-04-21 | 2021-04-21 | 2022-03-30 | 2022-04-21 | 2022-04-21 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 120862473 | 110/003A | T2 EI HUMBOLDT-TRINITY 110/003A RPL POLE | EUREKA | ETL.1820.POLE.WOOD | 2021-04-21 | 2021-04-21 | 2022-03-30 | 2022-04-21 | 2022-04-21 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 120862476 | 110/003A | T2 EI HMBLDT-TRINITY 110/3A RMV VEG | EUREKA | ETL.1820.POLE.WOOD | 2021-04-21 | 2021-04-21 | 2022-01-25 | 2022-04-21 | 2022-04-21 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120862480 | 110/002C | T2 EI CTTNWD-HMBLDT 110/002L RMV VEG | EUREKA | ETL.1820.POLE.NWOD | 2021-04-21 | 2021-04-21 | 2022-01-24 | 2022-04-21 | 2022-04-21 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120862481 | 110/003C | T2 EI HUMBOLDT-TRINITY 110/003C RPL POLE | EUREKA | ETL.1820.POLE.WOOD | 2021-04-21 | 2021-04-21 | 2022-03-30 | 2022-04-21 | 2022-04-21 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 120863561 | 003/097 | T2 EI COLGATE-ALLEGHANY 3/97 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2021-04-22 | 2021-04-21 | 2022-06-22 | 2022-04-21 | 2022-04-21 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548663 | T2 DI COLGATE-ALLEGHANY 3/82 RPL STRW | 70Y
LC | 120864004 | 067/338 | T2 EI MALIN-RD MTN #2 067/338 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-04-22 | 2021-04-22 | 2022-08-08 | 2022-04-22 | 2022-04-22 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45194402 | T2 EI MALIN-RD MTN #2 067/338 RPR GYWS | ICS
LC | 120864033 | 003/029 | T2 DI MORAGA-OAKLAND #1 3/29 RPLC INSS | CONCORD | ETL.2720.INSL | 2021-04-22 | 2021-04-21 | 2022-06-29 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547461 | T2 DI MORAGA-OAKLAND #1 RPLC INSS 5TWRS | 93K
LC | 120864034 | 003/029 | T2 DI MORAGA-OAKLAND #2 3/29 RPLC INSS | CONCORD | ETL.2730.INSL | 2021-04-22 | 2021-04-21 | 2022-03-22 | 2022-04-21 | 2022-04-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547465 | T2 DI MORAGA-OAKLAND #2 RPLC INSS 5TWRS | 93K
LC | 120864058 | 017/108 | T2 EI STN-MLN MAN #1 17/108 UNBURY | VICTOR | ETL.3830.TOWR | 2021-04-22 | 2021-04-22 | 2022-02-09 | 2022-04-22 | 2022-04-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123107 | T2 EI STN-MLN MAN #1 17/108 UNBURY | ICQ
LC | 120864470 | 015/499 | T2 EI SPAULDING-SUMMIT 15/499 REFRAME | SACTO | ETL.8060.POLE.WOOD | 2021-04-22 | 2021-04-22 | 2021-08-18 | 2022-04-22 | 2022-04-22 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31453471 | T2 DI SPAULDING-SUMMIT 002/108 REPL POLE | 70Y
LC | 120864601 | 015/497 | T2 EI SPAULDING-SUMMIT 15/497 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-04-22 | 2021-04-22 | 2021-08-31 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44808350 | T2 EI SPAULDING-SUMMIT 15/497 RPR GYWW | ICW
LC | 120864701 | 037/244 | T2 DI POE-RIO OSO 37/244 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-04-22 | 2021-04-21 | 2022-06-23 | 2022-04-21 | 2022-04-21 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45145304 | T2 DI POE-RIO OSO 37/244 RPR FOND | ICQ
LC | 120864710 | 017/100 | T2 EI SN ML SW ST-RK J S 17/100 RPR SPLS | VICTOR | ETL.3840.INSL.CERA | 2021-04-22 | 2021-04-22 | 2022-09-16 | 2022-04-22 | 2022-04-22 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122121 | T2 EI SN ML SW ST-RK JT S 17/99 RPR SPLS | ICS
LC | 120864744 | 037/248 | T2 DI POE-RIO OSO 037/248 INS HRDT | TABLEMTN | ETL.5540.TOWR | 2021-04-22 | 2021-04-21 | 2021-12-28 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45099110 | T2 DI POE-RIO OSO 037/248 INS HRDT | ICQ
LC | 120864824 | 025/204 | T2 EI PIT #1-COTTONWOOD 25/204 RPL ANCS | TABLEMTN | ETL.5390.TOWR | 2021-04-22 | 2021-04-22 | 2022-08-17 | 2022-04-22 | 2022-04-22 | Late | 93Z | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Missing | Anchor-Steel | Install | 31618945 | T2 EI PIT #1-COTTONWOOD 25/204 RPL ANCS | 93Z
LC | 120864896 | 017/099 | T2 EI STNISLUS-MNTCA#2 17/99 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-22 | 2021-04-22 | 2022-02-08 | 2022-04-22 | 2022-04-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45123105 | T2 EI STNISLUS-MNTCA#2 17/99 RPR FOND | ICQ
LC | 120864920 | 009/000 | T2 DI SALINAS-FORT ORD #2 9/0 RMV NEST | MOSSLNDG | ETL.8423.POLE.NWOD | 2021-04-22 | 2021-04-21 | 2021-06-04 | 2022-04-21 | 2022-04-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Steel | Remove | 44828730 | T2 DI SALINAS-FORT ORD #2 9/0 RMV NEST | ICS
LC | 120864941 | 017/099 | T2 EI SN ML SW ST-RK JT S 17/99 RPR CONS | VICTOR | ETL.3840.INSL.NCER | 2021-04-22 | 2021-04-22 | 2022-09-16 | 2022-04-22 | 2022-04-22 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45122122 | T2 EI SN ML SW ST-RK JT S 17/99 RPR CONS | ICS
LC | 120865069 | 107/000 | T2 EI HUMBOLDT-TRINITY 107/000 RMV VEG | EUREKA | ETL.1820.POLE.STPS | 2021-04-22 | 2021-04-22 | 2022-06-16 | 2022-04-22 | 2022-04-22 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120865073 | 107/000 | T2 EI HUMBOLDT-TRINITY 107/0 RMV DEBRIS | EUREKA | ETL.1820.POLE.STPS | 2021-04-22 | 2021-04-22 | 2022-01-24 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Structure-Wood | Remove | 45079486 | T2 EI HUMBOLDT-TRINITY 107/0 RMV DEBRIS | ICW
LC | 120865074 | 107/003 | T2 EI CTTNWD-HMBLDT 107/003R RMV VEG | EUREKA | ETL.1820.POLE.STPS | 2021-04-22 | 2021-04-22 | 2022-06-16 | 2022-04-22 | 2022-04-22 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120865107 | 013/098A | T2 DI HELMS-GRGG #1 13/98A RPL INSS | FRESNO | ETL.4870.INSL | 2021-04-22 | 2021-04-21 | 2022-08-25 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533801 | T2 DI HELMS-GREGG #1 RPLC INSS 9 TWRS | 93K
LC | 120865328 | 000/001 | T2 DI SLT SPRNGS-TGR CRK 0/1 INS HRDT | VICTOR | ETL.3500.TOWR | 2021-04-22 | 2021-04-20 | 2022-03-31 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45150408 | T2 DI SLT SPRNGS-TGR CRK 0/1 INS HRDT | ICQ
LC | 120865529 | 025/200 | T2 EI PIT #1-COTTONWOOD 25/200 RMV VEG | TABLEMTN | ETL.5390.TOWR | 2021-04-22 | 2021-04-22 | 2022-01-12 | 2022-04-22 | 2022-04-22 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120865629 | 015/493 | T2 EI SPAULDING-SUMMIT 15/493 RPR STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-22 | 2021-04-22 | 2021-06-30 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44808349 | T2 EI SPAULDING-SUMMIT 15/493 RPR STRW | ICW
LC | 120865687 | 002/070 | T2 EI COLGATE-ALLEGHANY 2/70 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2021-04-22 | 2021-04-22 | 2021-08-05 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44764570 | T2 EI COLGATE-ALLEGHANY 2/70 RPR STRW | ICW
LC | 120865734 | 016/097 | T2 EI STNSLS-MNTCA #2 16/95 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-22 | 2021-04-22 | 2022-02-08 | 2022-04-22 | 2022-04-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45123058 | T2 EI STNSLS-MNTCA #2 16/95 RPR FOND | ICQ
LC | 120865786 | 029/176 | T2 DI TMBLR-SN LS OBSP 29/176 RPR SPLS | PISMOBCH | ETL.3960.TOWR | 2021-04-22 | 2021-04-21 | 2022-04-20 | 2022-04-21 | 2022-04-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45069387 | T2 DI TMBLR-SN LS OBSP 29/176 RPR SPLS | ICS
LC | 120865878 | 009/047 | T2 DI SILVERADO-FLTN JCT 9/47 RPLC INSS | LAKEVLLE | ETL.1610.INSL.NCER | 2021-04-22 | 2021-04-13 | 2022-03-13 | 2022-04-13 | 2022-04-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548684 | T2 DI SILVERADO-FUTON JCT RPL INSS 6TWR | 93K
LC | 120865996 | 016/096 | T2 EI STNSLS-MNTCA #2 16/96 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-22 | 2021-04-22 | 2022-02-08 | 2022-04-22 | 2022-04-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45123057 | T2 EI STNSLS-MNTCA #2 16/96 RPR FOND | ICQ
LC | 120866032 | 002/068 | T2 EI COLGATE-ALLEGHANY 2/68 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2021-04-22 | 2021-04-22 | 2021-08-05 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44777238 | T2 EI COLGATE-ALLEGHANY 2/68 RPR STRW | ICW
LC | 120866096 | :032/204 | T2 WV N TWR-MTZ JCT #1 :032/204 INS DAMS | CONCORD | ETL.3130.TOWR | 2021-04-22 | 2021-04-22 | 2022-04-07 | 2022-04-22 | 2022-04-22 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Steel | Install | 45107129 | T2 WV N TWR-MTZ JCT #1 :032/204 INS DAMS | ICS
LC | 120866100 | 009/047 | T2 DI FULTON-PUEBLO 9/47 RPL INSS | LAKEVLLE | ETL.1600.INSL.NCER | 2021-04-22 | 2021-04-13 | 2022-02-24 | 2022-04-13 | 2022-04-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 120866137 | 036/169 | T2 DI IGNACIO-SOBRANTE 36/169 RPL HRDT | LAKEVLLE | ETL.4920.TOWR | 2021-04-22 | 2021-04-14 | 2022-02-04 | 2022-04-14 | 2022-04-14 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45160877 | T2 DI IGNACIO-SOBRANTE 36/169 RPL HRDT | ICQ
LC | 120866256 | 016/095 | T2 EI STNSLS-MNTCA #2 16/95 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-22 | 2021-04-22 | 2022-02-07 | 2022-04-22 | 2022-04-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45123056 | T2 EI STNSLS-MNTCA #2 16/95 RPR FOND | ICQ
LC | 120866273 | C019/077A | T2 DI MOSS LDNG-CBRN C19/77A RPR INSW | MOSSLNDG | ETL.5330.INSL | 2021-04-22 | 2021-04-13 | 2021-10-13 | 2022-04-13 | 2022-04-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44981665 | T2 DI MOSS LDNG-CBRN C19/77A RPR INSW | ICW
LC | 120866441 | 016/101 | T2 EI STAN-MEL SS-MAN 16/101 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-22 | 2021-04-22 | 2022-02-07 | 2022-04-22 | 2022-04-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123100 | T2 EI STAN-MEL SS-MAN 16/101 RPR FOND | ICQ
LC | 120866489 | 015/487 | T2 EI SPAULDING-SUMMIT 15/487 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-04-22 | 2021-04-22 | 2021-07-24 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44808352 | T2 EI SPAULDING-SUMMIT 15/487 RPR GYWW | ICW
LC | 120866698 | 004/028 | T2 DI STSLS-MLS SS-MTC #1 4/28 RPL HRDT | VICTOR | ETL.3830.TOWR | 2021-04-22 | 2021-04-06 | 2022-01-18 | 2022-04-06 | 2022-04-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45119718 | T2 DI STSLS-MLS SS-MTC #1 4/28 RPL HRDT | ICQ
LC | 120866748 | 004/019 | T2 EI PITTSBURG-TESLA #1 4/019 RPR FOND | CONCORD | ETL.5510.TOWR | 2021-04-22 | 2021-04-22 | 2022-04-11 | 2022-04-22 | 2022-04-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190781 | T2 EI PITTSBURG-TESLA #1 4/019 RPR FOND | ICQ
LC | 120866827 | 003/018 | T2 EI PITSURG-TSL #1 3/18 RPR FND CMPLTD | CONCORD | ETL.5510.TOWR | 2021-04-22 | 2021-04-22 | 2022-03-29 | 2022-04-22 | 2022-04-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190782 | T2 EI PITTSBURG-TESLA #1 3/18 RPR FOND | ICQ
LC | 120866893 | 003/017 | T2 EI PITSURG-TSL #1 3/17 RPR FND CMPLTD | CONCORD | ETL.5510.TOWR | 2021-04-22 | 2021-04-22 | 2022-03-29 | 2022-04-22 | 2022-04-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190783 | T2 EI PITTSBURG-TESLA #1 3/17 RPR FOND | ICQ
LC | 120866939 | 109/002A | T2 EI CTTNWD-HMBLDT 109/002A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2021-04-22 | 2021-04-22 | 2022-01-22 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45079946 | T2 EI CTTNWD-HMBLDT 109/002A RPR GYWW | ICW
LC | 120866963 | 109/001 | T2 EI CTTNWD-HMBLDT 109/001L RMV VEG | EUREKA | ETL.1820.POLE.WDPS | 2021-04-22 | 2021-04-22 | 2022-01-25 | 2022-04-22 | 2022-04-22 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120867095 | 015/480 | T2 EI SPAULDING-SUMMIT 15/480 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-22 | 2021-04-22 | 2021-07-29 | 2022-04-22 | 2022-04-22 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31542073 | T2 EI SPAULDING-SUMMIT 14/466 RPL STRW | 70Y
LC | 120867099 | 015/093 | T2 EI STN ML S S-RB J S S 15/93 RPR CONS | VICTOR | ETL.3840.INSL.NCER | 2021-04-22 | 2021-04-22 | 2022-05-14 | 2022-04-22 | 2022-04-22 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45122123 | T2 EI STN ML S S-RB J S S 15/93 RPR CONS | ICS
LC | 120867199 | 008/073 | T2 EI PIT #1-CTTNWD 8/073 RMV NEST | TABLEMTN | ETL.5390.TOWR | 2021-04-22 | 2021-04-22 | 2022-03-04 | 2022-04-22 | 2022-04-22 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45182634 | T2 EI PIT #1-CTTNWD 8/073 RMV NEST | ICS
LC | 120867309 | 000/002 | T2 EI RINCON #1 TAP 000/002 RPR FOND | LAKEVLLE | ETL.1601.POLE.NWOD | 2021-04-22 | 2021-04-22 | 2022-02-02 | 2022-04-22 | 2022-04-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45161080 | T2 EI RINCON #1 TAP 000/002 RPR FOND | ICQ
LC | 120867325 | 002/062 | T2 EI COLGATE-ALLEGHANY 2/62 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2021-04-22 | 2021-04-22 | 2021-08-09 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44764571 | T2 EI COLGATE-ALLEGHANY 2/62 RPR STRW | ICW
LC | 120867344 | 008/072 | T2 EI PIT #1-CTTNWD 8/072 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-04-22 | 2021-04-22 | 2022-02-17 | 2022-04-22 | 2022-04-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45149339 | T2 EI PIT #1-CTTNWD 8/072 RPR STRT | ICQ
LC | 120867390 | 008/010 | T2 EI SALINAS-FORT ORD #2 8/10 RPR SPLS | MOSSLNDG | ETL.8423.INSL.CERA | 2021-04-22 | 2021-04-22 | 2021-06-03 | 2022-04-22 | 2022-04-22 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP SUBS COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Replace | 44828731 | T2 SALINAS-FORT ORD #2 8/10 RPR SPLS | ICS
LC | 120868341 | 030/180 | T2 DI TMBLR-SN LS OBSP 30/180 RPR SPLS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-22 | 2021-04-21 | 2022-04-22 | 2022-04-21 | 2022-04-21 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 45069388 | T2 DI TMBLR-SN LS OBSP 30/180 RPR SPLS | ICS
LC | 120868605 | 028/172 | T2 DI TMBLR-SN LS OBSPO 28/172 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-22 | 2021-04-21 | 2022-04-23 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546830 | T2 DI TEMBLOR-SLO- RPL INSS 6TWRS | 93K
LC | 120868694 | ;010/059A | T2 DI KNS RVR-SNGR-RDLY ;10/59A RPL INSS | FRESNO | ETL.2030.INSL.CERA | 2021-04-22 | 2021-04-21 | 2021-08-12 | 2022-04-21 | 2022-04-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514841 | T2 DI KNGS-SNGR-RDLY RPLC INSS 4TWR | 93K
LC | 120868696 | 001/025 | T2 EI IGNACIO-LAS GLLNA 1/025 RPL STRW | LAKEVLLE | ETL.1860.POLE.WOOD | 2021-04-22 | 2021-04-22 | 2022-11-15 | 2022-04-22 | 2022-04-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAR | No Good/Out of Stdrd | Structure-Wood | Replace | 31536643 | T2 EI IGNACIO-LAS GLLNA 1/025 RPL STRW | 70Y
LC | 120868912 | 001/024 | T2 EI IGNACIO-LAS GALLINAS 1/24 RPR GYWW | LAKEVLLE | ETL.1860.POLE.WOOD | 2021-04-22 | 2021-04-22 | 2022-11-14 | 2022-04-22 | 2022-04-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45142478 | T2 EI IGNACIO-LAS GALLINAS 1/24 RPR GYWW | ICW
LC | 120869470 | 055/307 | T2 WV TEMBLOR-SLO 55/307 RPR INSS | PISMOBCH | ETL.3960.TOWR | 2021-04-22 | 2021-04-22 | 2022-04-26 | 2022-04-22 | 2022-04-22 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Repair | 45069389 | T2 WV TEMBLOR-SLO 55/307 RPR INSS | ICS
LC | 120870560 | C011/046 | T2 EI MOS LNDNG-CBRN C11/46 COMPLETE | MOSSLNDG | ETL.5330.INSL | 2021-04-22 | 2021-04-22 | 2022-04-14 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536364 | DI MOSS LANDING-COBURN RPL INSS 15TWR | 93K
LC | 120870565 | C010/044 | T2 EI MOS LNDNG-CBRN C10/44 RPL INSS | MOSSLNDG | ETL.5330.INSL | 2021-04-22 | 2021-04-22 | 2022-04-14 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536364 | DI MOSS LANDING-COBURN RPL INSS 15TWR | 93K
LC | 120870642 | C011/045 | T2 EI MOS LANDING-CBURN C11/45 COMPLETE | MOSSLNDG | ETL.5330.INSL | 2021-04-22 | 2021-04-22 | 2022-04-14 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536364 | DI MOSS LANDING-COBURN RPL INSS 15TWR | 93K
LC | 120871739 | 074/377 | T2 EI MALIN-RD MTN #2 074/377 COMPLETE | TABLEMTN | ETL.6020.TOWR | 2021-04-23 | 2021-04-22 | 2022-05-02 | 2022-04-22 | 2022-04-22 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH RTNR FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Anchor-Steel | Repair | 45198242 | T2 EI MALIN-RD MTN #2 074/377 RPR ANCW | ICS
LC | 120871983 | 004/043 | T2 EI SALT SPRNGS-TIGR CRK 4/43 COMPLETE | VICTOR | ETL.3500.INSL | 2021-04-23 | 2021-04-22 | 2022-06-18 | 2022-04-22 | 2022-04-22 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540431 | T2 EI SALT SPRNGS-TGR CREK RPL INSS 18TW | 93K
LC | 120871990 | 004/044 | T2 EI SALT SPRNGS-TIGR CRK 4/44 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-23 | 2021-04-22 | 2022-06-17 | 2022-04-22 | 2022-04-22 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540431 | T2 EI SALT SPRNGS-TGR CREK RPL INSS 18TW | 93K
LC | 120871993 | 007/008 | T2 DI CHOWCHILLA-KERCKHOFF 7/8 RPLC INSW | FRESNO | ETL.1250.INSL.NCER | 2021-04-23 | 2021-04-22 | 2022-02-17 | 2022-04-22 | 2022-04-22 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31539801 | T2 DI CHOWCHILLA-KERCKHOFF 4/1 RPLC INSW | 93I
LC | 120871998 | 007/008 | T2 DI CHOWCHILLA-KERCKHOFF 7/8 RPLC HRDW | FRESNO | ETL.1250.POLE.WOOD | 2021-04-23 | 2021-04-22 | 2022-02-17 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45068741 | T2 DI CHOWCHILLA-KERCKHOFF 7/8 RPLC HRDW | ICW
LC | 120872101 | C015/062 | T2 DI COBURN-LAS AGUILA C15/62 RPLC DAMS | MOSSLNDG | ETL.4460.INSL | 2021-04-23 | 2021-04-21 | 2021-11-18 | 2022-04-21 | 2022-04-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 44961512 | T2 DI COBURN-LAS AGUILA C15/62 RPLC DAMS | ICS
LC | 120872105 | 042/276 | T2 DI POE-RIO OSO 42/276 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-04-23 | 2021-04-21 | 2022-01-06 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45106678 | T2 DI POE-RIO OSO 42/276 RPR FOND | ICQ
LC | 120872116 | 042/276 | T2 DI CRESTA-RIO OSO 42/276 RPLC INSS | TABLEMTN | ETL.4590.INSL.CERA | 2021-04-23 | 2021-04-21 | 2022-05-06 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546381 | DI CRESTA-RIO OSO RPL INSS 10TWRS | 93K
LC | 120872241 | 000/007 | T2 DI CHOWCHILLA-KERCKHOFF 0/7 RPLC INSS | FRESNO | ETL.1250.INSL | 2021-04-23 | 2021-04-22 | 2022-02-14 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514611 | T2 DI CHOWCHILLA-KERCKHOFF RPL INSS 12TW | 93K
LC | 120872244 | C010/043 | T2 EI MOS LANDING-COBURN C10/43 RPL INSS | MOSSLNDG | ETL.5330.INSL | 2021-04-23 | 2021-04-23 | 2022-04-14 | 2022-04-23 | 2022-04-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536364 | DI MOSS LANDING-COBURN RPL INSS 15TWR | 93K
LC | 120872285 | 002/011 | T2 DI CHOWCHILLA-KERCKHOFF 2/11 RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-04-23 | 2021-04-22 | 2022-02-15 | 2022-04-22 | 2022-04-22 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536992 | T2 DI CHOWCHILLA-KERCKHOFF 2/11 RPL STRW | 70Y
LC | 120872289 | 008/069 | T2 DI SLT SPRNGS-TGR CRK 8/69 RPR SPLS | VICTOR | ETL.3500.INSL | 2021-04-23 | 2021-04-22 | 2022-06-25 | 2022-04-22 | 2022-04-22 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45155668 | T2 DI SLT SPRNGS-TGR CRK 8/69 RPR SPLS | ICS
LC | 120872295 | 015/097 | T2 EI STNSLS-MLNS-MNTC 15/97 RPR SPLS | VICTOR | ETL.3830.TOWR | 2021-04-23 | 2021-04-23 | 2021-05-26 | 2022-04-23 | 2022-04-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Splice-Steel | Repair | 44871800 | T2 EI STNSLS-MLNS-MNTC 15/97 RPR SPLS | ICS
LC | 120872365 | C010/042 | T2 EI MOS LNDNG-CBRN C10/42 COMPLETE | MOSSLNDG | ETL.5330.INSL | 2021-04-23 | 2021-04-23 | 2021-11-19 | 2022-04-23 | 2022-04-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536364 | DI MOSS LANDING-COBURN RPL INSS 15TWR | 93K
LC | 120872428 | C010/042 | T2 EI MOS LANDING-COBURN C10/42 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-04-23 | 2021-04-23 | 2022-05-19 | 2022-04-23 | 2022-04-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44766635 | T2 EI MOS LANDING-COBURN C10/42 RPR FOND | ICQ
LC | 120872576 | 014/476 | T2 EI SPAULDING-SUMMIT 14/476 RRL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-07-28 | 2022-04-23 | 2022-04-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542073 | T2 EI SPAULDING-SUMMIT 14/466 RPL STRW | 70Y
LC | 120872583 | 008/069 | T2 DI SLT SPRNGS-TGR CRK 8/69 RMV VEG | VICTOR | ETL.3500.TOWR | 2021-04-23 | 2021-04-22 | 2022-04-11 | 2022-04-22 | 2022-04-22 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 120872701 | 014/475 | T2 EI SPAULDING-SUMMIT 14/475 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-07-28 | 2022-04-23 | 2022-04-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542073 | T2 EI SPAULDING-SUMMIT 14/466 RPL STRW | 70Y
LC | 120872874 | 015/095 | T2 EI STNSLS-MLNS-MNTC 15/95 RPR SPLS | VICTOR | ETL.3830.TOWR | 2021-04-23 | 2021-04-23 | 2021-05-26 | 2022-04-23 | 2022-04-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Repair | 44828116 | T2 EI STNSLS-MLNS-MNTC 15/95 RPR SPLS | ICS
LC | 120872938 | 014/473 | T2 EI SPAULDING-SUMMIT 14/473 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-07-28 | 2022-04-23 | 2022-04-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31542073 | T2 EI SPAULDING-SUMMIT 14/466 RPL STRW | 70Y
LC | 120872961 | 015/090 | T2 EI STNLS-MLNS SW ST #2 14/90 UNBURY | VICTOR | ETL.3820.TOWR | 2021-04-23 | 2021-04-23 | 2022-02-07 | 2022-04-23 | 2022-04-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123051 | T2 EI STNLS-MLNS SW ST #2 14/90 UNBURY | ICQ
LC | 120872994 | 011/198 | T2 DI TEJON-LEBEC 011/198 RPR SPLW | MIDWAY | ETL.9250.INSL.NCER | 2021-04-23 | 2021-04-22 | 2021-08-05 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 44817574 | T2 DI TEJON-LEBEC 011/198 RPR SPLW | ICW
LC | 120873096 | C010/041 | T2 EI MOSS LANDING-CBURNC 10/41RPL INSS | MOSSLNDG | ETL.5330.INSL | 2021-04-23 | 2021-04-23 | 2022-04-17 | 2022-04-23 | 2022-04-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536364 | DI MOSS LANDING-COBURN RPL INSS 15TWR | 93K
LC | 120873134 | 106/001A | T2 EI HMBLDT-TRINITY 106/1A RMV VEG | EUREKA | ETL.1820.POLE.NWOD | 2021-04-23 | 2021-04-23 | 2022-02-24 | 2022-04-23 | 2022-04-23 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120873136 | 106/000 | T2 EI HMBLDT-TRINITY 106/0L RMV VEG | EUREKA | ETL.1820.POLE.WDPS | 2021-04-23 | 2021-04-23 | 2022-02-24 | 2022-04-23 | 2022-04-23 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120873137 | 106/001B | T2 EI HMBLDT-TRINITY 106/1B RMV VEG | EUREKA | ETL.1820.POLE.NWOD | 2021-04-23 | 2021-04-23 | 2022-02-24 | 2022-04-23 | 2022-04-23 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120873161 | 105/003 | T2 EI CTTNWD-HMBLDT 105/3 RMV VEG | EUREKA | ETL.1820.POLE.WDPS | 2021-04-23 | 2021-04-23 | 2022-02-24 | 2022-04-23 | 2022-04-23 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120873168 | 007/084B | T2 EI DRUM-SUMMIT #2 7/84B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2021-04-23 | 2021-04-23 | 2022-05-09 | 2022-04-23 | 2022-04-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45073784 | T2 EI DRUM-SUMMIT #2 7/84B RPR GYWW | ICW
LC | 120873207 | C009/040 | T2 EI MOSS LANDING-COBURN C9/40 RPL INSS | MOSSLNDG | ETL.5330.INSL | 2021-04-23 | 2021-04-23 | 2022-04-17 | 2022-04-23 | 2022-04-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536364 | DI MOSS LANDING-COBURN RPL INSS 15TWR | 93K
LC | 120873208 | C009/040 | T2 EI MOSS LANDING-COBURN C9/40 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-04-23 | 2021-04-23 | 2022-05-19 | 2022-04-23 | 2022-04-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45121180 | T2 EI MOSS LANDING-COBURN C9/40 RPR FOND | ICQ
LC | 120873216 | 014/472 | T2 EI SPAULDING-SUMMIT 14/472 RPR STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-07-28 | 2022-04-23 | 2022-04-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44808347 | T2 EI SPAULDING-SUMMIT 14/472 RPR STRW | ICW
LC | 120873229 | C008/036 | T2 DI MOSS LANDING-COBURN C8/36 RPL INSS | MOSSLNDG | ETL.5330.INSL | 2021-04-23 | 2021-04-22 | 2022-04-17 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536364 | DI MOSS LANDING-COBURN RPL INSS 15TWR | 93K
LC | 120873246 | 007/084C | T2 EI DRUM-SUMMIT #2 7/84C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2021-04-23 | 2021-04-23 | 2022-05-09 | 2022-04-23 | 2022-04-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45073793 | T2 EI DRUM-SUMMIT #2 7/84C RPR GYWW | ICW
LC | 120873337 | 008/069 | T2 EI PIT #3-PIT #1 8/69 RPR FOND | TABLEMTN | ETL.5400.TOWR | 2021-04-23 | 2021-04-23 | 2022-07-28 | 2022-04-23 | 2022-04-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45198323 | T2 EI PIT #3-PIT #1 8/69 RPR FOND | ICQ
LC | 120873371 | 008/069 | T2 EI PIT #3-PIT #1 8/69 RMV VEG | TABLEMTN | ETL.5400.TOWR | 2021-04-23 | 2021-04-23 | 2022-02-16 | 2022-04-23 | 2022-04-23 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120873493 | 014/469 | T2 EI SPAULDING-SUMMIT 14/469 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-07-27 | 2022-04-23 | 2022-04-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542073 | T2 EI SPAULDING-SUMMIT 14/466 RPL STRW | 70Y
LC | 120873658 | 018/085 | T2 EI MOSS LANDING-MTCLF 18/085 RPL INSS | MOSSLNDG | ETL.6050.INSL | 2021-04-23 | 2021-04-23 | 2022-02-23 | 2022-04-23 | 2022-04-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31539376 | T2 EI MOSS LANDING-MTCLF RPL INSS 2TWR | 93K
LC | 120873663 | 015/088 | T2 EI STNLS-MLNS SW ST #2 15/88 UNBURY | VICTOR | ETL.3820.TOWR | 2021-04-23 | 2021-04-23 | 2022-02-04 | 2022-04-23 | 2022-04-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123049 | T2 EI STNLS-MLNS SW ST #2 15/88 UNBURY | ICQ
LC | 120873704 | 001/037 | T2 EI COLGATE-ALLEGHANY 1/037 RMV BUTT | SACTO | ETL.6470.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-08-08 | 2022-04-23 | 2022-04-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44777236 | T2 EI COLGATE-ALLEGHANY 1/037 RMV BUTT | ICW
LC | 120873759 | 001/037 | T2 EI COLGATE-ALLEGHANY 01/037 RPR SPLW | SACTO | ETL.6470.INSL.CERA | 2021-04-23 | 2021-04-23 | 2021-08-08 | 2022-04-23 | 2022-04-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Replace | 44777052 | T2 EI COLGATE-ALLEGHANY 01/037 RPR SPLW | ICW
LC | 120873792 | C009/038 | T2 EI MOSS LANDING-COBURN C9/38 RPL INSS | MOSSLNDG | ETL.5330.INSL | 2021-04-23 | 2021-04-23 | 2022-04-17 | 2022-04-23 | 2022-04-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536364 | DI MOSS LANDING-COBURN RPL INSS 15TWR | 93K
LC | 120873801 | 011/009 | T2 MERCED FALLS-EXCHEQUER 11/9 RPR INSS | FRESNO | ETL.8990.POLE.NWOD | 2021-04-23 | 2021-04-23 | 2022-03-21 | 2022-04-23 | 2022-04-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Repair | 45199320 | T2 MERCED FALLS-EXCHEQUER 11/9 RPR INSS | ICS
LC | 120873804 | 011/007 | T2 MERCED FALLS-EXCHEQUER 11/7 RPL INSS | FRESNO | ETL.8990.POLE.NWOD | 2021-04-23 | 2021-04-23 | 2022-03-22 | 2022-04-23 | 2022-04-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31597142 | T2 MERCED FALLS-EXCHEQUER 11/7 RPL INSS | 93K
LC | 120873896 | 019/132 | T2 DI HELMS-GREGG #1 19/132 RPLC INSS | FRESNO | ETL.4870.INSL | 2021-04-23 | 2021-04-21 | 2022-08-22 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533801 | T2 DI HELMS-GREGG #1 RPLC INSS 9 TWRS | 93K
LC | 120873934 | 001/038 | T2 EI COLGATE-ALLEGHANY 1/38 REFRAME | SACTO | ETL.6470.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-08-06 | 2022-04-23 | 2022-04-23 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31541791 | T3 EI COLGATE-ALLEGHANY 10/273 REFRAME | 93E
LC | 120873964 | 007/086A | T2 EI DRUM-SUMMIT #2 7/86A RPR GYWW | SACTO | ETL.1450.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2022-05-11 | 2022-04-23 | 2022-04-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45073795 | T2 EI DRUM-SUMMIT #2 7/86A RPR GYWW | ICW
LC | 120873998 | 001/003 | T2 EI CHWCHLLA-KRCKHFF 1/3A RPR GWRW | FRESNO | ETL.1250.POLE.STPS | 2021-04-23 | 2021-04-23 | 2022-02-15 | 2022-04-23 | 2022-04-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45068745 | T2 EI CHWCHLLA-KRCKHFF 1/3A RPR GWRW | ICW
LC | 120874012 | 014/466 | T2 EI SPAULDING-SUMMIT 14/466 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-07-26 | 2022-04-23 | 2022-04-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31542073 | T2 EI SPAULDING-SUMMIT 14/466 RPL STRW | 70Y
LC | 120874017 | 014/464 | T2 EI SPAULDING-SUMMIT 14/464 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-07-27 | 2022-04-23 | 2022-04-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541924 | T2 DI SPAULDING-SUMMIT 12/419 RPL STRW | 70Y
LC | 120874021 | 014/467 | T2 EI SPAULDING-SUMMIT 14/467 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-07-26 | 2022-04-23 | 2022-04-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31542073 | T2 EI SPAULDING-SUMMIT 14/466 RPL STRW | 70Y
LC | 120874050 | 003/025 | T2 DI MORAGA-OAKLAND #1 3/25 RPR FOND | CONCORD | ETL.2720.TOWR | 2021-04-23 | 2021-04-21 | 2022-02-07 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45161295 | T2 DI MORAGA-OAKLAND #1 3/25 RPR FOND | ICQ
LC | 120874051 | 003/025 | T2 DI MORAGA-OAKLAND #1 3/25 RPLC INSS | CONCORD | ETL.2720.INSL | 2021-04-23 | 2021-04-21 | 2022-06-29 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547461 | T2 DI MORAGA-OAKLAND #1 RPLC INSS 5TWRS | 93K
LC | 120874053 | 003/013 | T2 DI CHOWCHILLA-KERCKHOFF 3/13 RPL INSW | FRESNO | ETL.1250.INSL.NCER | 2021-04-23 | 2021-04-22 | 2022-02-18 | 2022-04-22 | 2022-04-22 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31536991 | T2 DI CHWCHLL-KERCKHOFF 001/008 RPL INSS | 93I
LC | 120874190 | 014/092 | T2 EI STNSLS-MLNS-MNTC 14/92 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-23 | 2021-04-23 | 2022-02-04 | 2022-04-23 | 2022-04-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45123047 | T2 EI STNSLS-MLNS-MNTC 14/92 RPR FOND | ICQ
LC | 120874194 | 001/003 | T2 EI CHWCHLLA-KRCKHFF 1/3 RPR GWRW | FRESNO | ETL.1250.POLE.STPS | 2021-04-23 | 2021-04-23 | 2022-02-15 | 2022-04-23 | 2022-04-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45068724 | T2 EI CHWCHLLA-KRCKHFF 1/3 RPR GWRW | ICW
LC | 120874200 | 014/091 | T2 EI STNLS-MLNS SW ST #1 14/91 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-23 | 2021-04-23 | 2022-03-04 | 2022-04-23 | 2022-04-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Hardware-Steel | Install | 44978048 | T2 EI STNLS-MLNS SW ST #1 14/91 INS HRDS | ICS
LC | 120874201 | 014/091 | T2 EI STNLS-MLNS SW ST #1 14/91 UNBURY | VICTOR | ETL.3830.TOWR | 2021-04-23 | 2021-04-23 | 2022-02-04 | 2022-04-23 | 2022-04-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123046 | T2 EI STNLS-MLNS SW ST #1 14/91 UNBURY | ICQ
LC | 120874209 | 001/003 | T2 EI CHWCHLLA-KRCKHFF 1/3 RPL INSW | FRESNO | ETL.1250.INSL.NCER | 2021-04-23 | 2021-04-23 | 2022-02-13 | 2022-04-23 | 2022-04-23 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO REJC NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31536991 | T2 DI CHWCHLL-KERCKHOFF 001/008 RPL INSS | 93I
LC | 120874304 | 001/040 | T2 EI COLGATE-ALLEGHANY 1/40 RPL INSW | SACTO | ETL.6470.INSL.CERA | 2021-04-23 | 2021-04-23 | 2021-08-06 | 2022-04-23 | 2022-04-23 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537434 | T2 EI COLGATE-ALLEGHANY 1/31 RPL INSW | 93I
LC | 120874309 | 005/022 | T2 EI PITTSBURG-TESLA #1 5/22 RPR FOND | CONCORD | ETL.5510.TOWR | 2021-04-23 | 2021-04-23 | 2022-04-12 | 2022-04-23 | 2022-04-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190789 | T2 EI PITTSBURG-TESLA #1 5/22 RPR FOND | ICQ
LC | 120874345 | 005/021 | T2 EI PITTSBURG-TESLA #1 5/21 RPR FOND | CONCORD | ETL.5510.TOWR | 2021-04-23 | 2021-04-23 | 2022-04-12 | 2022-04-23 | 2022-04-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190791 | T2 EI PITTSBURG-TESLA #1 5/21 RPR FOND | ICQ
LC | 120874353 | 001/040 | T2 EI COLGATE-ALLEGHANY 1/40 REFRAME | SACTO | ETL.6470.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-08-08 | 2022-04-23 | 2022-04-23 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31550567 | T2 EI COLGATE-ALLEGHANY 1/40 REFRAME | 93E
LC | 120874411 | 001/003 | T2 EI CHWCHLLA-KRCKHFF 1/3 RPR GWRW | FRESNO | ETL.1250.POLE.STPS | 2021-04-23 | 2021-04-23 | 2022-02-16 | 2022-04-23 | 2022-04-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45068725 | T2 EI CHWCHLLA-KRCKHFF 1/3 RPR GWRW | ICW
LC | 120874450 | 008/069 | T2 EI PARADIS-TBLE MTN 008/069 RPR STRT | TABLEMTN | ETL.4316.TOWR | 2021-04-23 | 2021-04-23 | 2022-06-23 | 2022-04-23 | 2022-04-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45198302 | T2 EI PARADIS-TBLE MTN 008/069 RPR STRT | ICQ
LC | 120874474 | 007/087C | T2 EI DRUM-SUMMIT#2 7/87 RPR GWRW | SACTO | ETL.1450.POLE.NWOD | 2021-04-23 | 2021-04-23 | 2022-06-04 | 2022-04-23 | 2022-04-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45074175 | T2 EI DRUM-SUMMIT#2 7/87 RPR GWRW | ICW
LC | 120874507 | :014/077 | T2 DI CZY HRS CNYN-SLS-S :14/77 RPR STRT | MOSSLNDG | ETL.2900.TOWR | 2021-04-23 | 2021-04-21 | 2021-07-13 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Tower | Repair | 44839768 | T2 DI CZY HRS CNYN-SLS-S :14/77 RPR STRT | ICQ
LC | 120874558 | 000/003 | T2 DI CHOWCHILLA-KERCKHOFF 0/3 RPL INSS | FRESNO | ETL.1250.INSL | 2021-04-23 | 2021-04-22 | 2022-02-13 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514611 | T2 DI CHOWCHILLA-KERCKHOFF RPL INSS 12TW | 93K
LC | 120874578 | 001/008 | T2 EI CHOWCHILLA-KERCKHOFF 1/8 REPULL | FRESNO | ETL.1250.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2022-11-02 | 2022-04-23 | 2022-04-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45068726 | T2 EI CHOWCHILLA-KERCKHOFF 1/8 REPULL | ICW
LC | 120874667 | 001/036 | T2 EI COLGATE-ALLEGHANY 1/36 RMV BUTT | SACTO | ETL.6470.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-08-08 | 2022-04-23 | 2022-04-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44764563 | T2 EI COLGATE-ALLEGHANY 1/36 RMV BUTT | ICW
LC | 120874682 | 001/036 | T2 EI COLGATE-ALLEGHANY 1/36 RPL INSW | SACTO | ETL.6470.INSL.CERA | 2021-04-23 | 2021-04-23 | 2021-08-08 | 2022-04-23 | 2022-04-23 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537434 | T2 EI COLGATE-ALLEGHANY 1/31 RPL INSW | 93I
LC | 120874692 | 008/072 | T2 EI PARADISE-TABLE MTN 08/072 RPL INSS | TABLEMTN | ETL.4316.INSL | 2021-04-23 | 2021-04-23 | 2021-07-16 | 2022-04-23 | 2022-04-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120874728 | 001/008 | T2 DI CHWCHLL-KERCKHOFF 001/008 RPL INSS | FRESNO | ETL.1250.INSL.NCER | 2021-04-23 | 2021-04-22 | 2022-11-02 | 2022-04-22 | 2022-04-22 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31536991 | T2 DI CHWCHLL-KERCKHOFF 001/008 RPL INSS | 93I
LC | 120874816 | 001/010 | T2 EI CHWCHILLA-KRCKHFF 1/10 RPL INSS | FRESNO | ETL.1250.INSL | 2021-04-23 | 2021-04-23 | 2022-02-13 | 2022-04-23 | 2022-04-23 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31591323 | EI CHOWCHILLA-KERCKHOFF 27/011 RPL INSW | 93I
LC | 120874889 | 011/186 | T2 DI TEJON-LEBEC 11/186 RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-23 | 2021-04-22 | 2021-08-09 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44817794 | T2 DI TEJON-LEBEC 11/186 RPR GYWW | ICW
LC | 120874899 | 009/159 | T2 DI TEJON-LEBEC 9/159 RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-23 | 2021-04-22 | 2021-08-12 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44817796 | T2 DI TEJON-LEBEC 9/159 RPR GYWW | ICW
LC | 120874906 | 105/002 | T2 EI CTTNWD-HMBLDT 105/2 RMV VEG | EUREKA | ETL.1820.POLE.WDPS | 2021-04-23 | 2021-04-23 | 2022-02-24 | 2022-04-23 | 2022-04-23 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120874914 | 011/186 | T2 DI TEJON-LEBEC 11/186 RPL HRDW | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-23 | 2021-04-22 | 2021-08-05 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44817794 | T2 DI TEJON-LEBEC 11/186 RPR GYWW | ICW
LC | 120874954 | 009/163 | T2 DI TEJON-LEBEC 9/163 RPR SPLW | MIDWAY | ETL.9250.INSL.NCER | 2021-04-23 | 2021-04-22 | 2021-08-17 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 44817798 | T2 DI TEJON-LEBEC 9/163 RPR SPLW | ICW
LC | 120874956 | 009/163 | T2 DI TEJON-LEBEC 9/163 RMV HRDS | MIDWAY | ETL.9250.POLE.NWOD | 2021-04-23 | 2021-04-22 | 2021-08-05 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44817798 | T2 DI TEJON-LEBEC 9/163 RPR SPLW | ICW
LC | 120874966 | 003/002 | T2 EI CHWCHILLA-KRCKHFF 3/2 RPR GWRW | FRESNO | ETL.1250.POLE.NWOD | 2021-04-23 | 2021-04-23 | 2022-02-18 | 2022-04-23 | 2022-04-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45067862 | T2 EI CHWCHILLA-KRCKHFF 3/2 RPR GWRW | ICS
LC | 120874993 | 014/462 | T2 EI SPAULDING-SUMMIT 14/462 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-07-26 | 2022-04-23 | 2022-04-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31541924 | T2 DI SPAULDING-SUMMIT 12/419 RPL STRW | 70Y
LC | 120875018 | 008/093 | T2 EI DRUM-SUMMIT # 8/93 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-04-23 | 2021-04-23 | 2022-06-26 | 2022-04-23 | 2022-04-23 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544924 | T3 EI DRUM-SUMMIT #1 000/007 RPL STRW | 70Y
LC | 120875036 | 001/035 | T2 EI COLGATE-ALLEGHANY 1/35 RPL INSW | SACTO | ETL.6470.INSL.CERA | 2021-04-23 | 2021-04-23 | 2021-08-07 | 2022-04-23 | 2022-04-23 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537434 | T2 EI COLGATE-ALLEGHANY 1/31 RPL INSW | 93I
LC | 120875049 | 002/002 | T2 EI CHWCHILLA-KRCKHFF 2/2 RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2022-02-13 | 2022-04-23 | 2022-04-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540445 | T2 EI CHWCHILLA-KRCKHFF 2/2 RPL CRSMW | 93E
LC | 120875050 | 009/159 | T2 DI TEJON-LEBEC 9/159 RPR SPLW | MIDWAY | ETL.9250.INSL.NCER | 2021-04-23 | 2021-04-22 | 2021-08-17 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 44817796 | T2 DI TEJON-LEBEC 9/159 RPR GYWW | ICW
LC | 120875098 | 008/093 | T2 EI DRUM-SUMMIT # 8/93 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-04-23 | 2021-04-23 | 2022-06-26 | 2022-04-23 | 2022-04-23 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544924 | T3 EI DRUM-SUMMIT #1 000/007 RPL STRW | 70Y
LC | 120875115 | 008/093 | T2 EI DRUM-SUMMIT #1 8/93 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-04-23 | 2021-04-23 | 2022-06-26 | 2022-04-23 | 2022-04-23 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544924 | T3 EI DRUM-SUMMIT #1 000/007 RPL STRW | 70Y
LC | 120875180 | 007/092 | T2 DRUM-SUMMIT #1 7/92 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-04-23 | 2021-04-23 | 2022-06-23 | 2022-04-23 | 2022-04-23 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO REJC | No Good/Out of Stdrd | Structure-Wood | Replace | 31544924 | T3 EI DRUM-SUMMIT #1 000/007 RPL STRW | 70Y
LC | 120875195 | 001/034 | T2 EI COLGATE-ALLEGHANY 1/34 RPL INSW | SACTO | ETL.6470.INSL.CERA | 2021-04-23 | 2021-04-23 | 2021-08-07 | 2022-04-23 | 2022-04-23 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537434 | T2 EI COLGATE-ALLEGHANY 1/31 RPL INSW | 93I
LC | 120875234 | 014/454 | T2 EI SPAULDING-SUMMIT 14/454 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-07-29 | 2022-04-23 | 2022-04-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541924 | T2 DI SPAULDING-SUMMIT 12/419 RPL STRW | 70Y
LC | 120875394 | 006/002 | T2 DI SALINAS-FT ORD#2 006/002 RPR FOND | MOSSLNDG | ETL.8423.POLE.NWOD | 2021-04-23 | 2021-04-23 | 2022-03-10 | 2022-04-23 | 2022-04-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149223 | T2 DI SALINAS-FT ORD#2 006/002 RPR FOND | ICQ
LC | 120875419 | 002/004 | T2 EI CHWCHILLA-KRCKHFF 2/4 RPR GWRW | FRESNO | ETL.1250.POLE.NWOD | 2021-04-23 | 2021-04-23 | 2022-02-13 | 2022-04-23 | 2022-04-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45067864 | T2 EI CHWCHILLA-KRCKHFF 2/4 RPR GWRW | ICS
LC | 120875570 | 015/011 | T2 EI FULTON-HOPLAND 015/011 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-10-10 | 2022-04-23 | 2022-04-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536640 | T2 EI FULTON-HOPLAND 033/003 RPL STRW | 70Y
LC | 120875626 | 003/010 | T2 EI CHWCHILLA-KERCKHOFF 3/10 RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2022-02-14 | 2022-04-23 | 2022-04-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536992 | T2 DI CHOWCHILLA-KERCKHOFF 2/11 RPL STRW | 70Y
LC | 120875631 | 014/083 | T2 EI STNLS-MLNS SW ST #2 14/88 UNBURY | VICTOR | ETL.3820.TOWR | 2021-04-23 | 2021-04-23 | 2022-02-03 | 2022-04-23 | 2022-04-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123040 | T2 EI STNLS-MLNS SW ST #2 14/88 UNBURY | ICQ
LC | 120875677 | 008/072 | T2 EI PIT #1-COTTONWOOD 8/72 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-04-23 | 2021-04-23 | 2022-02-17 | 2022-04-23 | 2022-04-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149400 | T2 EI PIT #1-COTTONWOOD 8/72 RPR FOND | ICQ
LC | 120875691 | 108/002 | T2 EI CTTNWD-HMBLDT 108/002 REM VEG | EUREKA | ETL.1820.POLE.WDPS | 2021-04-23 | 2021-04-23 | 2022-03-02 | 2022-04-23 | 2022-04-23 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120875697 | 108/003 | T2 EI CTTNWD-HMBLDT # 1 108/3 RMV VEG | EUREKA | ETL.1820.POLE.STPS | 2021-04-23 | 2021-04-23 | 2022-07-13 | 2022-04-23 | 2022-04-23 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO SR22 | Overgrown | Vegetation | Remove
LC | 120875698 | 001/031 | T2 EI COLGATE-ALLEGHANY 1/31 RPL INSW | SACTO | ETL.6470.INSL.CERA | 2021-04-23 | 2021-04-23 | 2021-08-07 | 2022-04-23 | 2022-04-23 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537434 | T2 EI COLGATE-ALLEGHANY 1/31 RPL INSW | 93I
LC | 120875779 | 034/197 | T2 DI TMBLR-SN LS OBSP 34/197 RPLC INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-23 | 2021-04-23 | 2022-04-20 | 2022-04-23 | 2022-04-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546832 | T2 DI TMBLR-SN LS OBSP RPLC INSS 7TWRS | 93K
LC | 120875811 | 015/010 | T2 EI FULTON-HOPLAND 015/010 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-10-10 | 2022-04-23 | 2022-04-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536640 | T2 EI FULTON-HOPLAND 033/003 RPL STRW | 70Y
LC | 120875897 | 007/062 | T2 DI SLT SPRNGS-TGER CRK 7/62 RPR SPLS | VICTOR | ETL.3500.INSL.CERA | 2021-04-23 | 2021-04-20 | 2022-06-25 | 2022-04-20 | 2022-04-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Replace | 45155669 | T2 DI SLT SPRNGS-TGER CRK 7/62 INS DAMS | ICS
LC | 120876186 | 006/005 | T2 DI SALINAS-FT ORD#1 006/005 RPR SPLS | MOSSLNDG | ETL.7890.INSL.CERA | 2021-04-23 | 2021-04-22 | 2022-05-11 | 2022-04-22 | 2022-04-22 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45224929 | T2 DI SALINAS-FT ORD#1 006/005 RPR SPLS | ICS
LC | 120876342 | 006/026 | T2 EI PITTSBURG-TESLA #1 6/26 RPR FOND | CONCORD | ETL.5510.TOWR | 2021-04-23 | 2021-04-23 | 2022-04-20 | 2022-04-23 | 2022-04-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190792 | T2 EI PITTSBURG-TESLA #1 6/26 RPR FOND | ICQ
LC | 120876485 | 033/230 | T2 EI TRINITY-COTTONWOOD 33/230 RMV BRSH | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-23 | 2021-04-23 | 2021-12-01 | 2022-04-23 | 2022-04-23 | On-time | 932 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Brush Fuel | Road | Remove | 44817913 | EI TRINITY-COTTONWOOD 33/230 RMV BRSH | CHS
LC | 120876486 | 032/222A | T2 EI TRNTY-COTTONWOOD 32/222A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2021-04-23 | 2021-04-23 | 2022-06-24 | 2022-04-23 | 2022-04-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45211991 | T2 EI TRNTY-COTTONWOOD 32/222A RPR GYWW | ICW
LC | 120876488 | 032/222C | T2 EI TRNTY-COTTONWOOD 32/222C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2021-04-23 | 2021-04-23 | 2022-06-24 | 2022-04-23 | 2022-04-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45211992 | T2 EI TRNTY-COTTONWOOD 32/222C RPR GYWW | ICW
LC | 120876536 | 006/027 | T2 EI PITTSBURG-TESLA #1 6/27 RPR FOND | CONCORD | ETL.5510.TOWR | 2021-04-23 | 2021-04-23 | 2022-04-13 | 2022-04-23 | 2022-04-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190815 | T2 EI PITTSBURG-TESLA #1 6/27 RPR FOND | ICQ
LC | 120876566 | 006/028 | T2 EI PTSBURG-TSL #1 6/28 RPR FOND CMPLT | CONCORD | ETL.5510.TOWR | 2021-04-23 | 2021-04-23 | 2022-04-10 | 2022-04-23 | 2022-04-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190816 | T2 EI PITTSBURG-TESLA #1 6/28 RPR FOND | ICQ
LC | 120876826 | 027/190 | T2 EI TRINITY-COTTONWOOD 27/190 RPR HRDW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-04-23 | 2021-04-22 | 2021-09-02 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44873990 | T2 EI TRINITY-COTTONWOOD 27/190 RPR HRDW | ICW
LC | 120876828 | 028/200 | T2 EI TRINITY-CTTNWD 28/200A RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-23 | 2021-04-22 | 2021-09-08 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873938 | T2 EI TRINITY-CTTNWD 28/200A RPR GYWW | ICW
LC | 120876829 | 028/200 | T2 EI TRINITY-CTTNWD 28/200B RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-23 | 2021-04-22 | 2021-09-02 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873939 | T2 EI TRINITY-CTTNWD 28/200B RPR GYWW | ICW
LC | 120876832 | 026/185 | T2 EI TRINITY-COTTONWOOD 26/185 RPR ANCW | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-23 | 2021-04-21 | 2021-09-08 | 2022-04-21 | 2022-04-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 44873980 | T2 EI TRINITY-COTTONWOOD 26/185 RPR ANCW | ICW
LC | 120876841 | 028/200 | T2 EI TRINITY-CTTNWD 28/200C RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-23 | 2021-04-22 | 2021-09-08 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44873981 | T2 EI TRINITY-CTTNWD 28/200C RPR GYWW | ICW
LC | 120876987 | 006/051 | T2 EI SLT SPRNG-TGR CRK 6/051 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-23 | 2021-04-23 | 2022-06-25 | 2022-04-23 | 2022-04-23 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31604893 | T2 EI SLT SPRNG-TGR CRK 6/051 RPL INSS | 93K
LC | 120877066 | 073/372 | T2 EI MALIN-RD MTN #2 073/372 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-04-23 | 2021-04-22 | 2022-07-19 | 2022-04-22 | 2022-04-22 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45198241 | T2 EI MALIN-RD MTN #2 073/372 RPR GYWS | ICS
LC | 120877227 | 014/460 | T2 EI SPAULDING-SUMMIT 14/460 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-23 | 2021-04-23 | 2021-07-28 | 2022-04-23 | 2022-04-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541924 | T2 DI SPAULDING-SUMMIT 12/419 RPL STRW | 70Y
LC | 120877534 | 013/062 | T2 EI MOSS LANDING-COBURN 13/062 RMV VEG | MOSSLNDG | ETL.5330.TOWR | 2021-04-23 | 2021-04-23 | 2022-01-20 | 2022-04-23 | 2022-04-23 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120877538 | 014/067 | T2 EI MSS LANDING-COBURN 14/067 RMV VEG | MOSSLNDG | ETL.5330.TOWR | 2021-04-23 | 2021-04-23 | 2022-01-20 | 2022-04-23 | 2022-04-23 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120878286 | 003/010A | T2 DI CHOWCHILLA-KRCKHF 3/10A RPLC INSW | FRESNO | ETL.1250.INSL.NCER | 2021-04-24 | 2021-04-22 | 2022-02-14 | 2022-04-22 | 2022-04-22 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31536991 | T2 DI CHWCHLL-KERCKHOFF 001/008 RPL INSS | 93I
LC | 120878333 | 000/005 | T2 DI CHOWCHILLA-KERCKHOFF 0/5 RPL HRDT | FRESNO | ETL.1250.TOWR | 2021-04-24 | 2021-04-22 | 2022-02-15 | 2022-04-22 | 2022-04-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45069241 | T2 DI CHOWCHILLA-KERCKHOFF 0/5 RPL HRDT | ICQ
LC | 120878338 | 000/005 | T2 DI CHOWCHILLA-KERCKHOFF 0/5 RPL INSS | FRESNO | ETL.1250.INSL | 2021-04-24 | 2021-04-22 | 2022-02-13 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514611 | T2 DI CHOWCHILLA-KERCKHOFF RPL INSS 12TW | 93K
LC | 120878460 | 000/005 | T2 DI CHOWCHILLA-KERCKHOFF 0/5 RPR STRS | FRESNO | ETL.1250.TOWR | 2021-04-24 | 2021-04-22 | 2022-02-15 | 2022-04-22 | 2022-04-22 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45067865 | T2 DI CHOWCHILLA-KERCKHOFF 0/5 RPR STRS | ICS
LC | 120878462 | 030/132 | T2 DI MRR BY-SLR SS #1 30/132 RPR FOND | PISMOBCH | ETL.5300.TOWR | 2021-04-24 | 2021-04-20 | 2022-07-24 | 2022-04-20 | 2022-04-20 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44765365 | T2 DI MRR BY-SLR SS #1 30/132 RPR FOND | ICQ
LC | 120878581 | 004/033 | T2 EI SOBRANTE-G #2 4/33 RPL INSS | CONCORD | ETL.3730.INSL.CERA | 2021-04-24 | 2021-04-24 | 2022-07-05 | 2022-04-24 | 2022-04-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548690 | T2 EI SOBRANTE-G #2 RPL INSS 3 TSPS. | 93K
LC | 120878582 | 004/033 | T2 EI SOBRANTE-G #1 4/33 RPL INSS | CONCORD | ETL.3720.INSL.CERA | 2021-04-24 | 2021-04-24 | 2022-07-25 | 2022-04-24 | 2022-04-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548691 | T2 EI SOBRANTE-G #1 RPL INSS 5TWRS | 93K
LC | 120878641 | 013/077 | T2 EI STNISLS-MLNS SS-MNT 13/77 RMV VEG | VICTOR | ETL.3830.TOWR | 2021-04-24 | 2021-04-24 | 2022-08-03 | 2022-04-24 | 2022-04-24 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120878647 | 004/032 | T2 EI SOBRANTE-G #2 4/32 RPL INSS | CONCORD | ETL.3730.INSL.CERA | 2021-04-24 | 2021-04-24 | 2022-07-05 | 2022-04-24 | 2022-04-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548690 | T2 EI SOBRANTE-G #2 RPL INSS 3 TSPS. | 93K
LC | 120878648 | 004/032 | T2 EI SOBRANTE-G #1 4/32 RPL INSS | CONCORD | ETL.3720.INSL.CERA | 2021-04-24 | 2021-04-24 | 2022-07-25 | 2022-04-24 | 2022-04-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548691 | T2 EI SOBRANTE-G #1 RPL INSS 5TWRS | 93K
LC | 120878673 | 012/076 | T2 EI STANISLAUS-MANTECA #2 12/76 UNBURY | VICTOR | ETL.3820.TOWR | 2021-04-24 | 2021-04-24 | 2022-02-02 | 2022-04-24 | 2022-04-24 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45122327 | T2 EI STANISLAUS-MANTECA #2 12/76 UNBURY | ICQ
LC | 120878809 | 004/031 | T2 EI SOBRANTE-G #1 4/31 RPL INSS | CONCORD | ETL.3720.INSL.CERA | 2021-04-24 | 2021-04-24 | 2022-07-25 | 2022-04-24 | 2022-04-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548691 | T2 EI SOBRANTE-G #1 RPL INSS 5TWRS | 93K
LC | 120878854 | 001/030 | T2 EI COLGATE-ALLEGHANY 01/030 RPL PL | SACTO | ETL.6470.POLE.WOOD | 2021-04-24 | 2021-04-24 | 2021-08-06 | 2022-04-24 | 2022-04-24 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31531502 | T3 DI COLGATE-ALLGHNY 14/395 RPL STRW | 70Y
LC | 120878871 | 004/031 | T2 EI SOBRANTE-G #2 4/31 RPL INSS | CONCORD | ETL.3730.INSL.CERA | 2021-04-24 | 2021-04-24 | 2022-07-05 | 2022-04-24 | 2022-04-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548690 | T2 EI SOBRANTE-G #2 RPL INSS 3 TSPS. | 93K
LC | 120878967 | 007/033 | T2 EI PTSBRG-TSL #1 7/33 RPR FOND CMPLTD | CONCORD | ETL.5510.TOWR | 2021-04-24 | 2021-04-24 | 2022-04-10 | 2022-04-24 | 2022-04-24 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190817 | T2 EI PITTSBURG-TESLA #1 7/33 RPR FOND | ICQ
LC | 120878999 | 000/029 | T2 EI COLGATE-ALLEGHANY 0/29 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2021-04-24 | 2021-04-24 | 2021-08-09 | 2022-04-24 | 2022-04-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44764562 | T2 EI COLGATE-ALLEGHANY 0/29 RPR STRW | ICW
LC | 120879021 | 014/082 | EI T2 STNISLS-MLNS SS-MNT 14/82 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-24 | 2021-04-24 | 2022-02-02 | 2022-04-24 | 2022-04-24 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45122676 | EI T2 STNISLS-MLNS SS-MNT 14/82 RPR FOND | ICQ
LC | 120879119 | 000/028 | T2 EI COLGATE-ALLEGHANY 0/028 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2021-04-24 | 2021-04-24 | 2021-08-09 | 2022-04-24 | 2022-04-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44764561 | T2 EI COLGATE-ALLEGHANY 0/028 RPR STRW | ICW
LC | 120879168 | 013/081 | T2 EI STN-MLNS SW ST-RVR_13/81 RPR CNDS | VICTOR | ETL.3840.INSL.CERA | 2021-04-24 | 2021-04-24 | 2022-05-13 | 2022-04-24 | 2022-04-24 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45122124 | T2 EI STN-MLNS SW ST-RVR_13/81 RPR CNDS | ICS
LC | 120879170 | 013/081 | T2 EI STANISLAUS-MANTECA #2 13/81 UNBURY | VICTOR | ETL.3820.TOWR | 2021-04-24 | 2021-04-24 | 2022-02-02 | 2022-04-24 | 2022-04-24 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45122674 | T2 EI STANISLAUS-MANTECA #2 13/81 UNBURY | ICQ
LC | 120879262 | 013/448 | T2 EI SPAULDING-SUMMIT 13/448 RPR STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-24 | 2021-04-24 | 2021-07-27 | 2022-04-24 | 2022-04-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44808345 | T2 EI SPAULDING-SUMMIT 13/448 RPR STRW | ICW
LC | 120879264 | 013/447 | T2 EI SPAULDING-SUMMIT 13/447 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-04-24 | 2021-04-24 | 2021-07-27 | 2022-04-24 | 2022-04-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44808346 | T2 EI SPAULDING-SUMMIT 13/447 RPR GYWW | ICW
LC | 120879366 | 029/208 | EI T2 TRINITY-COTTONWOOD 29/208 RPL ANCW | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-24 | 2021-04-24 | 2022-08-24 | 2022-04-24 | 2022-04-24 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31618750 | EI T2 TRINITY-COTTONWOOD 29/208 RPL ANCW | 93E
LC | 120879423 | 029/208 | T2 EI CTTNWD-HUMBOLDT #1 29/208 RPR ANCW | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-24 | 2021-04-24 | 2022-08-24 | 2022-04-24 | 2022-04-24 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45195437 | T2 EI CTTNWD-HUMBOLDT #1 29/208 RPR ANCW | ICW
LC | 120879453 | 029/208 | T2 EI CTTNWD-HUMBLDT #1 29/208R RPR ANCW | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-24 | 2021-04-24 | 2022-08-23 | 2022-04-24 | 2022-04-24 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45195438 | T2 EI CTTNWD-HUMBLDT #1 29/208R RPR ANCW | ICW
LC | 120879544 | 032/221 | T2 EI TRNTY-CTTNWD 32/221B RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-24 | 2021-04-24 | 2022-06-22 | 2022-04-24 | 2022-04-24 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45211993 | T2 EI TRNTY-CTTNWD 32/221B RPR GYWW | ICS
LC | 120879756 | 021/093 | T2 EI PITTSBURG-TESLA #1 21/93 FOUND COA | CONCORD | ETL.5510.TOWR | 2021-04-24 | 2021-04-24 | 2022-04-09 | 2022-04-24 | 2022-04-24 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190819 | T2 EI PITTSBURG-TESLA #1 21/93 RPR FOND | ICQ
LC | 120879853 | 012/075 | T2 EI STAN-MEL-MANTECA 12/75 UNBURY | VICTOR | ETL.3830.TOWR | 2021-04-24 | 2021-04-24 | 2022-02-01 | 2022-04-24 | 2022-04-24 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45122326 | T2 EI STAN-MEL-MANTECA 12/75 UNBURY | ICQ
LC | 120879933 | 013/442 | T2 EI SPAULDING-SUMMIT 13/442 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-24 | 2021-04-24 | 2021-07-27 | 2022-04-24 | 2022-04-24 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31541924 | T2 DI SPAULDING-SUMMIT 12/419 RPL STRW | 70Y
LC | 120880110 | 011/086 | T2 EI MORAGA-LAKEWOOD_011/086 RPL INSS | CONCORD | ETL.3741.INSL | 2021-04-24 | 2021-04-22 | 2022-06-15 | 2022-04-22 | 2022-04-22 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31532654 | DI NN MRG-LKEWD RPR INSLS 6 TWRS. | 93K
LC | 120880153 | 012/073 | T2 EI STAN-MEL-MANTECA 12/73 UNBURY | VICTOR | ETL.3830.TOWR | 2021-04-24 | 2021-04-24 | 2022-02-01 | 2022-04-24 | 2022-04-24 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45122322 | T2 EI STAN-MEL-MANTECA 12/73 UNBURY | ICQ
LC | 120880171 | 012/072 | T2 EI STANISLAUS-MANTECA #2 12/72 UNBURY | VICTOR | ETL.3820.TOWR | 2021-04-24 | 2021-04-24 | 2022-02-01 | 2022-04-24 | 2022-04-24 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45122321 | T2 EI STANISLAUS-MANTECA #2 12/72 UNBURY | ICQ
LC | 120880250 | 000/012 | T2 EI ROLLINS TAP 000/012 RMV VEG | SACTO | ETL.6762.POLE.WOOD | 2021-04-24 | 2021-04-22 | 2021-09-27 | 2022-04-22 | 2022-04-22 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120880317 | 006/029 | EI T2 PITTSBURG-SN MTO 6/29 COMPLETED | CONCORD | ETL.5463.TOWR | 2021-04-24 | 2021-04-24 | 2022-03-17 | 2022-04-24 | 2022-04-24 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45179320 | EI T2 PITTSBURG-SN MTO 006/029 RPR FOND | ICQ
LC | 120880328 | 005/026H | T2 EI PITTSBURG-SAN MATEO 5/26H RPR FOND | CONCORD | ETL.5463.POLE.NWOD | 2021-04-24 | 2021-04-24 | 2022-06-14 | 2022-04-24 | 2022-04-24 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45179323 | T2 EI PITTSBURG-SAN MATEO 5/26H RPR FOND | ICQ
LC | 120880350 | 006/030 | EI T2 PITTSBURG-SN MTO 006/030 RPR FOND | CONCORD | ETL.5463.TOWR | 2021-04-24 | 2021-04-24 | 2022-03-17 | 2022-04-24 | 2022-04-24 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44947102 | EI T2 PITTSBURG-SN MTO 006/030 RPR FOND | ICQ
LC | 120880624 | 012/065A | T2 EI KGS RR-SR-RY 12/65A RPL INSS CMPLT | FRESNO | ETL.2030.INSL.NCER | 2021-04-24 | 2021-04-24 | 2022-03-01 | 2022-04-24 | 2022-04-24 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514841 | T2 DI KNGS-SNGR-RDLY RPLC INSS 4TWR | 93K
LC | 120880688 | 007/034 | T2 EI PITTSBURG-TESLA #1 7/34 COMPLETED | CONCORD | ETL.5510.TOWR | 2021-04-24 | 2021-04-24 | 2022-04-10 | 2022-04-24 | 2022-04-24 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190820 | T2 EI PITTSBURG-TESLA #1 7/34 RPR FOND | ICQ
LC | 120880737 | 030/209 | T2 EI TRINITY-COTTONWD 30/209 RPL ANCW | TABLEMTN | ETL.4040.POLE.STPS | 2021-04-24 | 2021-04-24 | 2022-08-23 | 2022-04-24 | 2022-04-24 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31541591 | T2 EI TRINITY-CTONWD 22/163 RPL ANCW | 93E
LC | 120880824 | 011/091 | T2 EI SLT SPRNGS-TGR CRK 11/9 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-24 | 2021-04-24 | 2022-06-19 | 2022-04-24 | 2022-04-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31601311 | T2 EI SLT SPRNGS-TGR CRK 11/9 RPL INSS | 93K
LC | 120880826 | 012/095 | T2 EI SLT SPRNGS-TGR CRK 12/95 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-24 | 2021-04-24 | 2022-06-25 | 2022-04-24 | 2022-04-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540431 | T2 EI SALT SPRNGS-TGR CREK RPL INSS 18TW | 93K
LC | 120880920 | 005/030 | T2 EI KRKHF-CLS-SANGR 5/30 UNBURY CMPLTD | FRESNO | ETL.1890.TOWR | 2021-04-24 | 2021-04-23 | 2022-05-02 | 2022-04-23 | 2022-04-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44786476 | T2 EI KRCKHFF-CLVS-SANGER 05/030 UNBURY | ICQ
LC | 120881818 | 003/025 | T2 DI MORAGA-OAKLAND #2 3/25 RPLC INSS | CONCORD | ETL.2730.INSL | 2021-04-26 | 2021-04-21 | 2022-03-23 | 2022-04-21 | 2022-04-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547465 | T2 DI MORAGA-OAKLAND #2 RPLC INSS 5TWRS | 93K
LC | 120882127 | 005/035 | EI T2 SOBRANTE-R #1 5/35 RMV HRDT | CONCORD | ETL.3770.TOWR | 2021-04-26 | 2021-04-26 | 2022-05-02 | 2022-04-26 | 2022-04-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAR NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45211294 | EI T2 SOBRANTE-R #1 5/35 RMV HRDT | ICQ
LC | 120882198 | :020/103 | T2 DI CRZY HRS CYN-SLS :20/103 RPL INSS | MOSSLNDG | ETL.2910.INSL.CERA | 2021-04-26 | 2021-04-20 | 2022-03-10 | 2022-04-20 | 2022-04-20 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528632 | DI CRZY HRS CYN-SLNS-SLD2 RPL INSS 6TWR | 93K
LC | 120882375 | 075/382 | EI T2 MALIN-ROUND MTN #2 75/382 RPR STRT | TABLEMTN | ETL.6020.TOWR | 2021-04-26 | 2021-04-26 | 2022-07-19 | 2022-04-26 | 2022-04-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45198243 | EI T2 MALIN-ROUND MTN #2 75/382 RPR STRT | ICQ
LC | 120882379 | 075/384 | T2 EI MALIN-ROUND MTN #2 75/384 RPR STRT | TABLEMTN | ETL.6020.TOWR | 2021-04-26 | 2021-04-26 | 2022-07-19 | 2022-04-26 | 2022-04-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45198244 | EI T2 MALIN-ROUND MTN #2 75/384 RPR STRT | ICQ
LC | 120882446 | 076/388 | EI T2 MALIN-ROUND MTN #2 76/388 RPL ANCS | TABLEMTN | ETL.6020.TOWR | 2021-04-26 | 2021-04-26 | 2022-08-17 | 2022-04-26 | 2022-04-26 | Late | 93Z | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Steel | Replace | 31604433 | EI T2 MALIN-ROUND MTN #2 76/388 RPL ANCS | 93Z
LC | 120882972 | 078/396 | T2 EI MALIN-RD MTN #2 078/396 RPR ANCS | TABLEMTN | ETL.6020.TOWR | 2021-04-26 | 2021-04-26 | 2022-07-15 | 2022-04-26 | 2022-04-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair | 45198246 | T2 EI MALIN-RD MTN #2 078/396 RPR ANCS | ICS
LC | 120883077 | 005/006 | T2 EI MNDCN-WLLITS-FRT BRGG 5/6 RPL PL | WILLITS | ETL.7550.POLE.WOOD | 2021-04-26 | 2021-04-26 | 2022-08-15 | 2022-04-26 | 2022-04-26 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31540801 | T2 DI MENDO-WILL-FT BRAGG 1/6 RPL POLE | 70Y
LC | 120883259 | C018/072 | T2 DI MOSS LDNG-CBRN C18/72 RPLC INSS | MOSSLNDG | ETL.5330.INSL | 2021-04-26 | 2021-04-13 | 2022-08-04 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536364 | DI MOSS LANDING-COBURN RPL INSS 15TWR | 93K
LC | 120883496 | 100/003B | T2 EI HMBLDT-TRNTY 100/3B RMV VEG | EUREKA | ETL.1820.POLE.NWOD | 2021-04-26 | 2021-04-26 | 2022-02-11 | 2022-04-26 | 2022-04-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120883649 | 019/132 | T2 DI HELMS-GREGG #2 19/132 WEIGHT | FRESNO | ETL.4880.INSL | 2021-04-26 | 2021-04-21 | 2022-08-04 | 2022-04-21 | 2022-04-21 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Steel | Replace | 45067867 | T2 DI HELMS-GREGG #1 19/132 WEIGHT | ICS
LC | 120883936 | 006/029 | T2 DI SILVERADO-FULTON JCT 6/29 RPL INSS | LAKEVLLE | ETL.1610.INSL | 2021-04-26 | 2021-04-13 | 2022-03-08 | 2022-04-13 | 2022-04-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31542618 | EI SILVERADO-FULTON JCT RPL INSS 6TWRS | 93K
LC | 120883937 | 006/029 | T2 DI FULTON-PUEBLO 006/029 RPL INSS | LAKEVLLE | ETL.1600.INSL | 2021-04-26 | 2021-04-13 | 2022-02-21 | 2022-04-13 | 2022-04-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 120884654 | 000/006 | T2 DI CHOWCHILLA-KERCKHOFF 0/6 RPR FOND | FRESNO | ETL.1250.TOWR | 2021-04-26 | 2021-04-22 | 2022-02-16 | 2022-04-22 | 2022-04-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 44766637 | T2 DI CHOWCHILLA-KERCKHOFF 0/6 RPR FOND | ICQ
LC | 120884657 | 000/006 | T2 DI CHOWCHILLA-KERCKHOFF 0/6 INS HRDT | FRESNO | ETL.1250.TOWR | 2021-04-26 | 2021-04-22 | 2022-02-15 | 2022-04-22 | 2022-04-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45069243 | T2 DI CHOWCHILLA-KERCKHOFF 0/6 INS HRDT | ICQ
LC | 120884781 | 000/006 | T2 DI CHOWCHILLA-KERCKHOFF 0/6 RPL INSS | FRESNO | ETL.1250.INSL | 2021-04-26 | 2021-04-22 | 2022-02-14 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514611 | T2 DI CHOWCHILLA-KERCKHOFF RPL INSS 12TW | 93K
LC | 120885152 | 004/030 | T2 EI SOBRANTE-G #1 4/30 RPL INSS | CONCORD | ETL.3720.INSL.CERA | 2021-04-26 | 2021-04-26 | 2022-07-25 | 2022-04-26 | 2022-04-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548691 | T2 EI SOBRANTE-G #1 RPL INSS 5TWRS | 93K
LC | 120885649 | 002/001 | T2 DI CHOWCHILLA-KERCKHOFF 2/1 RPL INSW | FRESNO | ETL.1250.INSL.NCER | 2021-04-26 | 2021-04-22 | 2022-02-14 | 2022-04-22 | 2022-04-22 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31536991 | T2 DI CHWCHLL-KERCKHOFF 001/008 RPL INSS | 93I
LC | 120885690 | 002/001 | T2 DI CHOWCHILLA-KERCKHOFF 2/1 RMV DBRS | FRESNO | ETL.1250.POLE.WOOD | 2021-04-26 | 2021-04-22 | 2022-02-14 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45068757 | T2 DI CHOWCHILLA-KERCKHOFF 2/1 RMV DBRS | ICW
LC | 120885692 | 001/002 | T2 DI CHOWCHILLA-KERCKHOFF 1/2 RPL INSS | FRESNO | ETL.1250.INSL.NCER | 2021-04-26 | 2021-04-22 | 2022-02-12 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31593445 | T2 DI CHOWCHILLA-KERCKHOFF 1/2 RPL INSS | 93K
LC | 120885749 | 006/055 | T2 EI PIT #1-CTTNWD 6/055 RMV NEST | TABLEMTN | ETL.5390.TOWR | 2021-04-26 | 2021-04-26 | 2022-08-22 | 2022-04-26 | 2022-04-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove | 45405676 | T2 EI PIT #1-CTTNWD 6/055 RMV NEST | ICS
LC | 120885811 | 008/133 | T2 SISQC-SNT YNZ SW STA 8/133 RPR JMP | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-26 | 2021-04-09 | 2022-04-11 | 2022-04-09 | 2022-04-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Jumper-Wood | Repair | 45069238 | T2 SISQC-SNT YNZ SW STA 8/133 RPR JMP | ICW
LC | 120885896 | 006/009 | T2 DI CHOWCHILLA-KERCKHOFF 6/9 RPLC INSW | FRESNO | ETL.1250.INSL.NCER | 2021-04-26 | 2021-04-22 | 2022-02-17 | 2022-04-22 | 2022-04-22 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31539801 | T2 DI CHOWCHILLA-KERCKHOFF 4/1 RPLC INSW | 93I
LC | 120885991 | :022/117 | T2 DI CZY HRS CN-SLS-SD :22/117 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2021-04-26 | 2021-04-14 | 2021-05-26 | 2022-04-14 | 2022-04-14 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44805767 | T2 DI CZY HRS CN-SLS-SD :22/117 RPL RPTS | ICB
LC | 120886007 | 007/004 | T2 DI CHOWCHILLA-KERCKHOFF 7/4 RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-04-26 | 2021-04-22 | 2022-02-18 | 2022-04-22 | 2022-04-22 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581055 | T2 DI CHOWCHILLA-KERCKHOFF 7/4 RPL STRW | 70Y
LC | 120886078 | 001/007 | T2 DI CHOWCHILLA-KERCKHOFF 1/7 RPL INSW | FRESNO | ETL.1250.INSL.NCER | 2021-04-26 | 2021-04-22 | 2022-02-16 | 2022-04-22 | 2022-04-22 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31536991 | T2 DI CHWCHLL-KERCKHOFF 001/008 RPL INSS | 93I
LC | 120886784 | 004/005 | T2 EI MNDCIN-WLITS-FRT BRG 4/5 RMV DEBRI | WILLITS | ETL.7550.POLE.NWOD | 2021-04-26 | 2021-04-26 | 2022-05-19 | 2022-04-26 | 2022-04-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45145608 | T2 EI MNDCIN-WLITS-FRT BRG 4/5 RMV DEBRI | ICW
LC | 120886808 | 004/004 | T2 EI MNDCIN-WLITS-FRT BRG 4/4 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-04-26 | 2021-04-26 | 2022-05-19 | 2022-04-26 | 2022-04-26 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542636 | T2 DI MNDCN-WLLTS-FT BRGG 16/1 RPL STRW | 70Y
LC | 120886810 | 003/009 | T2 EI MNDCN-WLTS-FRT BRAGG 3/9 RPR WDPKR | WILLITS | ETL.7550.POLE.WOOD | 2021-04-26 | 2021-04-26 | 2022-05-18 | 2022-04-26 | 2022-04-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP TNT COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45145607 | T2 EI MNDCN-WLTS-FRT BRAGG 3/9 RPR WDPKR | ICW
LC | 120886825 | 013/059 | T2 EI PITSBURG-TESLA #1 13/59 RPR FOND | CONCORD | ETL.5510.TOWR | 2021-04-26 | 2021-04-26 | 2022-04-13 | 2022-04-26 | 2022-04-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190821 | T2 EI PITSBURG-TESLA #1 13/59 RPR FOND | ICQ
LC | 120886826 | 012/057 | T2 EI PITTSBURG-TESLA #1 12/57 RPR FOND | CONCORD | ETL.5510.TOWR | 2021-04-26 | 2021-04-26 | 2022-04-13 | 2022-04-26 | 2022-04-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190822 | T2 EI PITTSBURG-TESLA #1 12/57 RPR FOND | ICQ
LC | 120886827 | 012/055 | T2 EI PITTSBURG-TESLA #1 12/55 RPR FOND | CONCORD | ETL.5510.TOWR | 2021-04-26 | 2021-04-26 | 2022-04-12 | 2022-04-26 | 2022-04-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190823 | T2 EI PITTSBURG-TESLA #1 12/55 RPR FOND | ICQ
LC | 120886901 | 037/009 | T2 EI FULTON-HOPLAND 37/9 RPL PL | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-04-26 | 2021-04-26 | 2021-10-11 | 2022-04-26 | 2022-04-26 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536640 | T2 EI FULTON-HOPLAND 033/003 RPL STRW | 70Y
LC | 120886909 | 035/013 | T2 EI FULTON-HOPLAND 35/013 RPL PL | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-04-26 | 2021-04-26 | 2021-12-12 | 2022-04-26 | 2022-04-26 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536640 | T2 EI FULTON-HOPLAND 033/003 RPL STRW | 70Y
LC | 120886956 | 037/151 | T2 EI DIABLO-MIDWAY #3 037/151 RPR STRT | PISMOBCH | ETL.5980.TOWR | 2021-04-26 | 2021-04-26 | 2022-06-05 | 2022-04-26 | 2022-04-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45073733 | T2 EI DIABLO-MIDWAY #3 037/151 RPR STRT | ICQ
LC | 120887340 | 078/398 | EI T2 MALIN-ROUND MTN #2 78/398 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-04-26 | 2021-04-26 | 2022-07-18 | 2022-04-26 | 2022-04-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45198248 | EI T2 MALIN-ROUND MTN #2 78/398 RPR GYWS | ICS
LC | 120887341 | 078/398 | EI T2 MALIN-ROUND MTN #2 78/398 RPR STRT | TABLEMTN | ETL.6020.TOWR | 2021-04-26 | 2021-04-26 | 2022-07-18 | 2022-04-26 | 2022-04-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45198249 | EI T2 MALIN-ROUND MTN #2 78/398 RPR STRT | ICQ
LC | 120887426 | 005/073 | T2 EI VALLEY SPRINGS-CLAY 5/73 RPR GYWW | VICTOR | ETL.8264.POLE.WOOD | 2021-04-26 | 2021-04-26 | 2021-08-26 | 2022-04-26 | 2022-04-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44806264 | T2 EI VALLEY SPRINGS-CLAY 5/73 RPR GYWW | ICW
LC | 120887442 | 101/000 | T2 EI HUMBOLDT-TRINITY 101/000 RMV VEG | EUREKA | ETL.1820.POLE.WDPS | 2021-04-26 | 2021-04-26 | 2022-02-11 | 2022-04-26 | 2022-04-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2N PRTO | Overgrown | Vegetation | Remove
LC | 120887452 | 101/000 | T2 EI HMBLDT-TRNTY 101/000 RMV VEG | EUREKA | ETL.1820.POLE.WDPS | 2021-04-26 | 2021-04-26 | 2022-02-11 | 2022-04-26 | 2022-04-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120887453 | 101/000 | T2 EI HUMBOLDT-TRINITY 101/0 RMV VEG | EUREKA | ETL.1820.POLE.WDPS | 2021-04-26 | 2021-04-26 | 2022-02-11 | 2022-04-26 | 2022-04-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120887980 | 029/213 | T2 DI DRUM-RIO OSO #1 29/213 INS HRDT | SACTO | ETL.1420.TOWR | 2021-04-27 | 2021-04-26 | 2022-01-19 | 2022-04-26 | 2022-04-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 44776400 | T2 DI DRUM-RIO OSO #1 29/213 INS HRDT | ICQ
LC | 120888696 | 099/003B | T2 EI HUMBOLDT-TRINITY 099/3B COMPLETE | EUREKA | ETL.1820.POLE.WOOD | 2021-04-27 | 2021-04-27 | 2022-03-24 | 2022-04-27 | 2022-04-27 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581077 | T2 EI HMBLDT-TRNTY 099/003B RPL POLE | 70Y
LC | 120888702 | 099/003A | T2 EI HUMBOLDT-TRINITY 099/003A COMPLETE | EUREKA | ETL.1820.POLE.WOOD | 2021-04-27 | 2021-04-27 | 2022-03-24 | 2022-04-27 | 2022-04-27 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581077 | T2 EI HMBLDT-TRNTY 099/003B RPL POLE | 70Y
LC | 120888744 | 024/111 | EI T2 TESLA-LOS BANOS #1 24/111 RPL INSS | VICTOR | ETL.6100.INSL | 2021-04-27 | 2021-04-27 | 2022-04-13 | 2022-04-27 | 2022-04-27 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31541683 | DI TESLA-LOS BANOS #1 RPL INSS 7TWRS | 93K
LC | 120888758 | 099/003C | T2 EI HMBLDT-TRNITY 099/003C RMV VEG | EUREKA | ETL.1820.POLE.WOOD | 2021-04-27 | 2021-04-27 | 2022-02-11 | 2022-04-27 | 2022-04-27 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120889055 | 032/188 | T2 EI HELMS-GREGG 32/188 COMPLETE | FRESNO | ETL.4870.TOWR | 2021-04-27 | 2021-04-27 | 2022-05-31 | 2022-04-27 | 2022-04-27 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45069249 | T2 EI HELMS-GREGG 32/188 RPR FOND | ICQ
LC | 120889082 | 011/069 | T2 EI STNSLS-MLNS SS-MNT 11/69 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-27 | 2021-04-27 | 2022-02-01 | 2022-04-27 | 2022-04-27 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45122279 | T2 EI STNSLS-MLNS SS-MNT 11/69 RPR FOND | ICQ
LC | 120889536 | 097/002 | T2 EI HUMBOLDT-TRINITY 97/2 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-04-27 | 2021-04-27 | 2022-03-24 | 2022-04-27 | 2022-04-27 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 120889538 | 097/004 | T2 EI HMBLDT-TRINITY 97/4 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-04-27 | 2021-04-27 | 2022-03-24 | 2022-04-27 | 2022-04-27 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 120889580 | 097/002 | T2 EI HUMBOLDT-TRINITY 97/2 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-04-27 | 2021-04-27 | 2022-03-24 | 2022-04-27 | 2022-04-27 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 120889584 | 097/004 | T2 EI HMBLDT-TRINITY 97/4 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-04-27 | 2021-04-27 | 2022-03-24 | 2022-04-27 | 2022-04-27 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 120889592 | 050/283 | T2 EI TMBLR-SN LS OBSP 50/283 RPL INSS | PISMOBCH | ETL.3960.TOWR | 2021-04-27 | 2021-04-27 | 2022-04-25 | 2022-04-27 | 2022-04-27 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546921 | T3 EI TEMBLOR-SLO RPL INSS 9TWRS | 93K
LC | 120889697 | 021/000 | T2 EI FLTN-HPLND 21/0 RPR GWRW | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-04-27 | 2021-04-27 | 2022-08-22 | 2022-04-27 | 2022-04-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45143941 | T2 EI FLTN-HPLND 21/0 RPR GWRW | ICW
LC | 120889706 | C009/038 | T2 EI COBURN-LAS AGUILAS C9/38 RPL INSS | MOSSLNDG | ETL.4460.INSL | 2021-04-27 | 2021-04-23 | 2021-11-18 | 2022-04-23 | 2022-04-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31527944 | DI CBN-LS AGLS SW ST-PCH RPL INSS 13TWRS | 93K
LC | 120889749 | 007/005 | T2 EI MNDCN-WLTS-FRT BRG 7/5 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-04-27 | 2021-04-27 | 2022-05-19 | 2022-04-27 | 2022-04-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45145615 | T2 EI MNDCN-WLTS-FRT BRG 7/5 RPR STRW | ICW
LC | 120889833 | C009/039 | T2 EI COBURN-LAS AGUILAS C9/39 RPL INSS | MOSSLNDG | ETL.4460.INSL | 2021-04-27 | 2021-04-23 | 2021-11-19 | 2022-04-23 | 2022-04-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31527944 | DI CBN-LS AGLS SW ST-PCH RPL INSS 13TWRS | 93K
LC | 120889835 | C009/040 | T2 EI COBURN-LAS AGUILAS C9/40 RPL INSS | MOSSLNDG | ETL.4460.INSL | 2021-04-27 | 2021-04-23 | 2021-11-18 | 2022-04-23 | 2022-04-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31527944 | DI CBN-LS AGLS SW ST-PCH RPL INSS 13TWRS | 93K
LC | 120889860 | 011/053 | T2 EI PITTSBURG-TESLA #1 11/53 RPR FOND | CONCORD | ETL.5510.TOWR | 2021-04-27 | 2021-04-27 | 2022-04-12 | 2022-04-27 | 2022-04-27 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190824 | T2 EI PITTSBURG-TESLA #1 11/53 RPR FOND | ICQ
LC | 120889868 | 097/000 | T2 EI HUMBOLDT-TRINITY 97/0 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-04-27 | 2021-04-27 | 2022-06-02 | 2022-04-27 | 2022-04-27 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 120889890 | 097/000 | T2 EI HUMBOLDT-TRINITY 97/0 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-04-27 | 2021-04-27 | 2022-06-02 | 2022-04-27 | 2022-04-27 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 120889936 | 099/000A | T2 EI HMBLDT-TRNTY 99/0 INS ANMW | EUREKA | ETL.1820.POLE.NWOD | 2021-04-27 | 2021-04-27 | 2022-06-07 | 2022-04-27 | 2022-04-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Missing | Animal Guard-Wood | Install | 45149551 | T2NT EI HMBLDT-TRNTY 99/0A RPR STRW | ICW
LC | 120889948 | 020/005 | T2 EI FLTN-HPLND 20/5 RMV DEBRIS | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-04-27 | 2021-04-27 | 2022-06-03 | 2022-04-27 | 2022-04-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45143940 | T2 EI FLTN-HPLND 20/5 RMV DEBRIS | ICW
LC | 120890082 | 031/186 | T2 EI HELMS-GREGG #1 31/186 RPR FND CMPT | FRESNO | ETL.4870.TOWR | 2021-04-27 | 2021-04-27 | 2022-05-25 | 2022-04-27 | 2022-04-27 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45069250 | T2 EI HELMS-GREGG #1 31/186 RPR FOND | ICQ
LC | 120890141 | 006/050 | T2 EI PIT #1-CTTNWD 6/050 RMV NEST | TABLEMTN | ETL.5390.TOWR | 2021-04-27 | 2021-04-27 | 2022-02-18 | 2022-04-27 | 2022-04-27 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45180995 | T2 EI PIT #1-CTTNWD 6/050 RMV NEST | ICS
LC | 120890288 | 015/124 | T2 EI PIT #1-CTTNWD 15/124 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-04-27 | 2021-04-27 | 2022-07-20 | 2022-04-27 | 2022-04-27 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45149405 | T2 EI PIT #1-CTTNWD 15/124 RPR STRT | ICQ
LC | 120890318 | 028/210 | T2 DI DRUM-RIO OSO #2 028/210 RPL INSS | SACTO | ETL.1430.INSL.CERA | 2021-04-27 | 2021-04-26 | 2021-09-21 | 2022-04-26 | 2022-04-26 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535386 | EI DRM-RO OSO #2 RPL INSS 12TWRS | 93K
LC | 120890370 | 016/074 | T2 EI PTSRG-TSL #1 16/74 RPR STRT CMPLTD | CONCORD | ETL.5510.TOWR | 2021-04-27 | 2021-04-27 | 2022-04-11 | 2022-04-27 | 2022-04-27 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45190825 | T2 EI PITTSBURG-TESLA #1 16/074 RPR STRT | ICQ
LC | 120890579 | 048/275 | T2 EI TMBLR-SN LS OBISPO 48/275 RPL INSS | PISMOBCH | ETL.3960.TOWR | 2021-04-27 | 2021-04-27 | 2022-04-23 | 2022-04-27 | 2022-04-27 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546921 | T3 EI TEMBLOR-SLO RPL INSS 9TWRS | 93K
LC | 120890628 | 035/204 | T2 DI TMBLR-SAN LS OBSPO 35/204 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-27 | 2021-04-26 | 2022-04-24 | 2022-04-26 | 2022-04-26 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546832 | T2 DI TMBLR-SN LS OBSP RPLC INSS 7TWRS | 93K
LC | 120890690 | 049/280 | T2 EI TMBLR-SN LS OBISPO 49/280 RPL INSS | PISMOBCH | ETL.3960.TOWR | 2021-04-27 | 2021-04-27 | 2022-04-24 | 2022-04-27 | 2022-04-27 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546921 | T3 EI TEMBLOR-SLO RPL INSS 9TWRS | 93K
LC | 120890739 | 031/185 | T2 EI HELMS-GREGG 31/185 RPR FOND CMPLT | FRESNO | ETL.4870.TOWR | 2021-04-27 | 2021-04-27 | 2022-05-25 | 2022-04-27 | 2022-04-27 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45069253 | T2 EI HELMS-GREGG 31/185 RPR FOND | ICQ
LC | 120890834 | C010/042 | T2 EI COBURN-LAS AGUILAS C10/42 RPL INSS | MOSSLNDG | ETL.4460.INSL | 2021-04-27 | 2021-04-23 | 2021-11-18 | 2022-04-23 | 2022-04-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31527944 | DI CBN-LS AGLS SW ST-PCH RPL INSS 13TWRS | 93K
LC | 120890932 | 036/240 | T2 DI POE-RIO OSO 036/240 INS HRDT | TABLEMTN | ETL.5540.TOWR | 2021-04-27 | 2021-04-26 | 2021-12-27 | 2022-04-26 | 2022-04-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45099108 | T2 DI POE-RIO OSO 036/240 INS HRDT | ICQ
LC | 120891013 | 011/102 | T2 WV BRIDGEVILLE-CTTNWD 11/102 RPL HRDS | TABLEMTN | ETL.1110.POLE.STPS | 2021-04-27 | 2021-04-27 | 2022-06-23 | 2022-04-27 | 2022-04-27 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45211359 | T2 WV BRIDGEVILLE-CTTNWD 11/102 RPL HRDS | ICS
LC | 120891039 | 049/277 | T2 EI TMBLR-SN LS OBISPO 49/277 RPL INSS | PISMOBCH | ETL.3960.TOWR | 2021-04-27 | 2021-04-27 | 2022-04-23 | 2022-04-27 | 2022-04-27 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546921 | T3 EI TEMBLOR-SLO RPL INSS 9TWRS | 93K
LC | 120891297 | C010/044 | T2 EI CBRN-LS AGUILAS SW C10/44 RPL INSS | MOSSLNDG | ETL.4460.INSL | 2021-04-27 | 2021-04-22 | 2021-11-18 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31527944 | DI CBN-LS AGLS SW ST-PCH RPL INSS 13TWRS | 93K
LC | 120891298 | C011/046 | T2 EI CBRN-LS AGUILAS SW C11/46 RPL INSS | MOSSLNDG | ETL.4460.INSL.NCER | 2021-04-27 | 2021-04-22 | 2021-11-17 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31527944 | DI CBN-LS AGLS SW ST-PCH RPL INSS 13TWRS | 93K
LC | 120891368 | C011/045 | T2 EI CBRN-LS AGUILAS SW C11/45 RPL INSS | MOSSLNDG | ETL.4460.INSL | 2021-04-27 | 2021-04-22 | 2021-11-18 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31527944 | DI CBN-LS AGLS SW ST-PCH RPL INSS 13TWRS | 93K
LC | 120891376 | 009/105B | T2 EI DRUM-SUMMIT#2 9/105B REPUL GUY | SACTO | ETL.1450.POLE.NWOD | 2021-04-27 | 2021-04-27 | 2022-05-10 | 2022-04-27 | 2022-04-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44776408 | T2 EI DRUM-SUMMIT#2 9/105C REPUL GUY | ICW
LC | 120891387 | 009/105A | T2 EI DRUM-SUMMIT#2 09/105A REPUL GUY | SACTO | ETL.1450.POLE.NWOD | 2021-04-27 | 2021-04-27 | 2022-05-10 | 2022-04-27 | 2022-04-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44776409 | T2 EI DRUM-SUMMIT#2 09/105L REPUL GUY | ICW
LC | 120891397 | 034/146 | T2 DI MRR BY-SLR SW ST #1 34/146 RPL INS | PISMOBCH | ETL.5300.INSL | 2021-04-27 | 2021-04-26 | 2022-06-17 | 2022-04-26 | 2022-04-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528621 | EI MORRO BAY-SOLAR SS #1 RPLC INNS 18TW | 93K
LC | 120891512 | 009/105C | T2 EI DRUM-SUMMIT#2 9/105C REPUL GUY | SACTO | ETL.1450.POLE.NWOD | 2021-04-27 | 2021-04-27 | 2022-05-10 | 2022-04-27 | 2022-04-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44776410 | T2 EI DRUM-SUMMIT#2 9/105R REPUL GUY | ICW
LC | 120891713 | 032/139 | T2 DI MRR BY-SLR SW ST #1 32/139 RPL INS | PISMOBCH | ETL.5300.INSL | 2021-04-27 | 2021-04-26 | 2022-06-18 | 2022-04-26 | 2022-04-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528621 | EI MORRO BAY-SOLAR SS #1 RPLC INNS 18TW | 93K
LC | 120891987 | 010/340 | T2 EI SPAULDING-SUMMIT 10/340 RPR SPLW | SACTO | ETL.8060.POLE.WOOD | 2021-04-27 | 2021-04-27 | 2021-08-12 | 2022-04-27 | 2022-04-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Splice-Wood | Repair | 44808344 | T2 EI SPAULDING-SUMMIT 10/340 RPR SPLW | ICW
LC | 120891988 | 009/327 | T2 EI SPLDING-SMMIT 9/327 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-27 | 2021-04-27 | 2022-09-21 | 2022-04-27 | 2022-04-27 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31537210 | EI SPAULDING-SUMMIT 8/280 RPL POLE | 70Y
LC | 120891989 | 009/331 | T2 EI SPLDING-SMMIT 9/331 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-04-27 | 2021-04-27 | 2022-09-20 | 2022-04-27 | 2022-04-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45074213 | T2 EI SPLDING-SMMIT 9/331 RPR INSBNDWR | ICW
LC | 120892020 | 009/326 | T2 EI SPLDING-SMMIT 9/326 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-27 | 2021-04-27 | 2022-09-21 | 2022-04-27 | 2022-04-27 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31537210 | EI SPAULDING-SUMMIT 8/280 RPL POLE | 70Y
LC | 120892049 | 028/001 | T2 EI FLTN-HPLND 28/1 RPR CNDW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-04-27 | 2021-04-27 | 2022-06-20 | 2022-04-27 | 2022-04-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45143952 | T2 EI FLTN-HPLND 28/1 RPR CNDW | ICW
LC | 120892067 | 049/279 | T2 EI TMBLR-SN LS OBISPO 49/279 RPL INSS | PISMOBCH | ETL.3960.TOWR | 2021-04-27 | 2021-04-27 | 2022-04-24 | 2022-04-27 | 2022-04-27 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546921 | T3 EI TEMBLOR-SLO RPL INSS 9TWRS | 93K
LC | 120892166 | 003/004 | T2 EI MNDCN-WLTS-FRT BRG 3/4 SPLITBOLT | WILLITS | ETL.7550.POLE.WOOD | 2021-04-27 | 2021-04-27 | 2022-05-18 | 2022-04-27 | 2022-04-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Missing | Hardware-Wood | Install | 45145605 | T2 EI MNDCN-WLTS-FRT BRG 3/4 SPLITBOLT | ICW
LC | 120892182 | 003/001 | T2 EI MNDCN-WLTS-FRT BRG 003/01 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-04-27 | 2021-04-27 | 2022-05-17 | 2022-04-27 | 2022-04-27 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540801 | T2 DI MENDO-WILL-FT BRAGG 1/6 RPL POLE | 70Y
LC | 120892277 | 011/189 | T2 SURF TAP 011/189 RPL INSW | PISMOBCH | ETL.1381.POLE.WOOD | 2021-04-27 | 2021-04-27 | 2021-08-23 | 2022-04-27 | 2022-04-27 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31540467 | T2 SURF TAP 011/189 RPL INSW | 93I
LC | 120892356 | 018/165 | T2 WV BRIDGEVLL-CTNWD 18/165 RPL HRDS | TABLEMTN | ETL.1110.POLE.STPS | 2021-04-27 | 2021-04-27 | 2022-08-31 | 2022-04-27 | 2022-04-27 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45211780 | T2 WV BRIDGEVILLE-CTTNWD 18/1 RPL HRDS | ICS
LC | 120892522 | 004/032 | T2 EI MORAGA-OAKLAND #3 004/032 RPL INSS | CONCORD | ETL.2740.INSL.NCER | 2021-04-27 | 2021-04-27 | 2022-07-07 | 2022-04-27 | 2022-04-27 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31606542 | EI MORAGA-OAKLAND #3 RPL INSS IN 1 TWR | 93K
LC | 120892523 | 004/032 | T2 EI MORAGA-OAKLAND #4 4/32 RPL INSS | CONCORD | ETL.2750.INSL.NCER | 2021-04-27 | 2021-04-27 | 2022-07-11 | 2022-04-27 | 2022-04-27 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31606351 | EI MORAGA-OAKLAND #4 RPL INSS IN 1 TWR. | 93K
LC | 120892584 | 005/005 | T2 DI CHOWCHILLA-KERCKHOFF 5/5 RPL GYWW | FRESNO | ETL.1250.POLE.WOOD | 2021-04-27 | 2021-04-22 | 2022-02-18 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45068731 | T2 DI CHOWCHILLA-KERCKHOFF 5/5 RPL GYWW | ICW
LC | 120892609 | 009/046 | T2 DI SILVERADO-FULTON JCT 9/46 RPL INSS | LAKEVLLE | ETL.1610.INSL.NCER | 2021-04-27 | 2021-04-13 | 2022-03-11 | 2022-04-13 | 2022-04-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548684 | T2 DI SILVERADO-FUTON JCT RPL INSS 6TWR | 93K
LC | 120892682 | 008/062 | T2 DI EL DRD-MSSRI FLT#2 8/62 RPL INSS | SACTO | ETL.1540.INSL.CERA | 2021-04-27 | 2021-04-13 | 2022-05-18 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547631 | T2 WV EL DORADO-MSR FLT #2 RPL INSS 10TW | 93K
LC | 120892683 | 003/001 | T2 DI IONE TAP 3/001 REPA STRW | VICTOR | ETL.8253.POLE.NWOD | 2021-04-27 | 2021-04-13 | 2022-03-08 | 2022-04-13 | 2022-04-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45122139 | T2 DI IONE TAP 3/001 REPA STRW | ICW
LC | 120892684 | 003/001 | T2NT DI IONE TAP 3/001 REMV POLE BUTT | VICTOR | ETL.8253.POLE.NWOD | 2021-04-27 | 2021-04-13 | 2021-09-17 | 2022-04-13 | 2022-04-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44961284 | T2NT DI IONE TAP 3/001 REMV POLE BUTT | ICW
LC | 120892720 | 009/046 | T2 DI FULTON-PUEBLO 009/046 RPL INSS | LAKEVLLE | ETL.1600.INSL.NCER | 2021-04-27 | 2021-04-13 | 2022-02-24 | 2022-04-13 | 2022-04-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 120892794 | 004/085 | T2 DI SQUC-SNT YNZ 4/85 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-27 | 2021-04-27 | 2021-10-04 | 2022-04-27 | 2022-04-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44963130 | T2 DI SQUC-SNT YNZ 4/85 RPR STRW | ICW
LC | 120893041 | 081/412 | EI T2 MALIN-ROUND MTN #2 81/412 RPR STRT | TABLEMTN | ETL.6020.TOWR | 2021-04-27 | 2021-04-27 | 2022-07-18 | 2022-04-27 | 2022-04-27 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45198252 | EI T2 MALIN-ROUND MTN #2 81/412 RPR STRT | ICQ
LC | 120893042 | 081/412 | EI T2NT MALIN-RND MTN #2 81/412 RPL HRDT | TABLEMTN | ETL.6020.TOWR | 2021-04-27 | 2021-04-27 | 2022-07-18 | 2022-04-27 | 2022-04-27 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45198253 | EI T2NT MALIN-RND MTN #2 81/412 RPL HRDT | ICQ
LC | 120893357 | 019/004 | T2 DI TULE-SPRINGVILLE 019/004 RPR STRW | MIDWAY | ETL.9040.POLE.WOOD | 2021-04-28 | 2021-04-27 | 2022-06-07 | 2022-04-27 | 2022-04-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45068040 | T2 DI TULE-SPRINGVILLE 019/004 RPR STRW | ICW
LC | 120893430 | 008/137 | T2 DI SSQC-SNT YNZ SW ST 8/137 RPR SPLW | PISMOBCH | ETL.3700.INSL.CERA | 2021-04-28 | 2021-04-27 | 2022-04-11 | 2022-04-27 | 2022-04-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45069239 | T2 DI SSQC-SNT YNZ SW ST 8/137 RPR SPLW | ICW
LC | 120893445 | 006/040 | T2 DI STANISLS-MNTCA #2 6/40 RPL HRDT | VICTOR | ETL.3820.TOWR | 2021-04-28 | 2021-04-27 | 2022-03-22 | 2022-04-27 | 2022-04-27 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45122102 | T2 DI STANISLS-MNTCA #2 6/40 RPL HRDT | ICQ
LC | 120893528 | 032/140 | T2 DI MORRO BY-SLR #1 32/140 RPLC INSS | PISMOBCH | ETL.5300.INSL | 2021-04-28 | 2021-04-27 | 2022-06-17 | 2022-04-27 | 2022-04-27 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528621 | EI MORRO BAY-SOLAR SS #1 RPLC INNS 18TW | 93K
LC | 120893601 | 005/088 | T2 DI SSQC-SNT YNZ 5/88 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-28 | 2021-04-27 | 2021-11-15 | 2022-04-27 | 2022-04-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44963126 | T2 DI SSQC-SNT YNZ 5/88 RPR STRW | ICW
LC | 120893784 | 002/005 | T2 DI CHOWCHILLA-KERCKHOFF 2/5 RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-04-28 | 2021-04-22 | 2022-02-13 | 2022-04-22 | 2022-04-22 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581056 | T2 DI CHOWCHILLA-KERCKHOFF 2/5 RPL STRW | 70Y
LC | 120893787 | 006/006 | T2 DI CHOWCHILLA-KERCKHOFF 6/6 RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-04-28 | 2021-04-22 | 2022-02-18 | 2022-04-22 | 2022-04-22 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581055 | T2 DI CHOWCHILLA-KERCKHOFF 7/4 RPL STRW | 70Y
LC | 120893793 | 030/178 | T2 EI TMBLR-SN LIS OBISP 30/178 RPR STRT | PISMOBCH | ETL.3960.TOWR | 2021-04-28 | 2021-04-28 | 2022-06-23 | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45077889 | T2 EI TMBLR-SN LIS OBISP 30/178 RPR STRT | ICQ
LC | 120893794 | 030/178 | T2 EI TMBR-SN LS OBP 30/178 RPL INSS CMP | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-28 | 2021-04-28 | 2022-04-20 | 2022-04-28 | 2022-04-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546830 | T2 DI TEMBLOR-SLO- RPL INSS 6TWRS | 93K
LC | 120893949 | 030/179 | T2 EI TMBLR-SN LIS OBISP 30/179 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-28 | 2021-04-28 | 2022-04-22 | 2022-04-28 | 2022-04-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546830 | T2 DI TEMBLOR-SLO- RPL INSS 6TWRS | 93K
LC | 120894084 | 010/061 | T2 EI STAN-MAN #2 10/61 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-28 | 2021-04-28 | 2022-01-27 | 2022-04-28 | 2022-04-28 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45122275 | T2 EI STAN-MAN #2 10/61 RPR FOND | ICQ
LC | 120894135 | 004/001 | T2 DI CHOWCHILLA-KERCKHOFF 4/1 RPLC INSW | FRESNO | ETL.1250.INSL.NCER | 2021-04-28 | 2021-04-22 | 2022-02-16 | 2022-04-22 | 2022-04-22 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31539801 | T2 DI CHOWCHILLA-KERCKHOFF 4/1 RPLC INSW | 93I
LC | 120894140 | 030/180 | T2 EI TMBLR-SN LIS OBISP 30/180 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-28 | 2021-04-28 | 2022-04-23 | 2022-04-28 | 2022-04-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546830 | T2 DI TEMBLOR-SLO- RPL INSS 6TWRS | 93K
LC | 120894859 | 031/184 | T2 EI TMBLR-SN LIS OBISP 31/184 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-28 | 2021-04-28 | 2022-04-22 | 2022-04-28 | 2022-04-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546831 | T2 EI TMBLR-SN LIS OBISP RPL INSS 7TWRS | 93K
LC | 120894893 | 022/180 | T2 EI PIT #1-COTONWD 22/180 RPL HRDT | TABLEMTN | ETL.5390.TOWR | 2021-04-28 | 2021-04-28 | 2022-07-22 | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Hardware-Tower | Install | 45149506 | T2 EI PIT #1-COTONWD 22/180 RPL HRDT | ICQ
LC | 120894900 | 019/087 | T2 DI MOSS LANDING-LAS AG 19/87 RPL INSS | MOSSLNDG | ETL.5340.INSL | 2021-04-28 | 2021-04-13 | 2022-10-19 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31539341 | T2 EI MSS LNDG-LS AGLS SW RPL INSS 6TWR | 93K
LC | 120894987 | 031/185 | T2 EI TMBLR-SN LIS OBISP 31/185 RPL INSS | PISMOBCH | ETL.3960.TOWR | 2021-04-28 | 2021-04-28 | 2022-04-22 | 2022-04-28 | 2022-04-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546831 | T2 EI TMBLR-SN LIS OBISP RPL INSS 7TWRS | 93K
LC | 120895159 | 000/017 | EI T2 COLGATE-ALLEGHANY 0/17 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2021-04-28 | 2021-04-28 | 2021-08-06 | 2022-04-28 | 2022-04-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541793 | EI T2 COLGATE-ALLEGHANY 0/17 RPL STRW | 70Y
LC | 120895258 | 007/002 | T2 EI OAKHURST TAP 7/002 INS DAMW | FRESNO | ETL.1252.POLE.NWOD | 2021-04-28 | 2021-04-28 | 2022-03-23 | 2022-04-28 | 2022-04-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Wood | Install | 45068738 | T2 EI OAKHURST TAP 7/002 INS DAMW | ICW
LC | 120895450 | 084/427 | EI T2 MALIN-ROUND MTN #2 84/427 RPR STRT | TABLEMTN | ETL.6020.TOWR | 2021-04-28 | 2021-04-28 | 2022-07-14 | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Structure-Tower | Repair | 45198259 | EI T2 MALIN-ROUND MTN #2 84/427 RPR STRT | ICQ
LC | 120895493 | 005/044 | T2 EI PIT #3-PIT #1 5/044 RMV NEST | TABLEMTN | ETL.5400.TOWR | 2021-04-28 | 2021-04-28 | 2022-10-11 | 2022-04-28 | 2022-04-28 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove | 45213909 | T2 EI PIT #3-PIT #1 5/044 RMV NEST | ICS
LC | 120895688 | 009/055 | T2 EI STSLS-MLNS SW ST-RVR 9/55 RPR SPLS | VICTOR | ETL.3840.INSL.CERA | 2021-04-28 | 2021-04-28 | 2022-09-16 | 2022-04-28 | 2022-04-28 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122125 | T2 EI STSLS-MLNS SW ST-RVR 9/55 RPR SPLS | ICS
LC | 120896037 | 009/053 | T2 EI STAN-MAN #2 9/53 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-28 | 2021-04-28 | 2022-01-25 | 2022-04-28 | 2022-04-28 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45122264 | T2 EI STAN-MAN #2 9/53 RPR FOND | ICQ
LC | 120896069 | 004/030 | T2 EI MORAGA-OAKLAND #1 4/30 RPL INSS | CONCORD | ETL.2720.INSL | 2021-04-28 | 2021-04-28 | 2022-06-29 | 2022-04-28 | 2022-04-28 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31607189 | EI MORAGA-OAKLAND #1 4/30 RPL INSS | 93K
LC | 120896204 | 040/230 | T2 EI TMBLR-SN LIS OBISP 40/230 RPR FOND | PISMOBCH | ETL.3960.TOWR | 2021-04-28 | 2021-04-28 | 2022-06-24 | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45077890 | T2 EI TMBLR-SN LIS OBISP 40/230 RPR FOND | ICQ
LC | 120896206 | 040/228 | T2 EI TMBLR-SN LIS OBISP 40/228 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-28 | 2021-04-28 | 2022-04-24 | 2022-04-28 | 2022-04-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546834 | T2 EI TMBLR-SAN LIS BISP RPL INSS 6TWRS | 93K
LC | 120896208 | 040/229 | T2 EI TMBLR-SN LIS OBISP 40/229 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-28 | 2021-04-28 | 2022-04-24 | 2022-04-28 | 2022-04-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546834 | T2 EI TMBLR-SAN LIS BISP RPL INSS 6TWRS | 93K
LC | 120896228 | 039/226 | T2 EI TMBR-SN LUIS OBISP 39/226 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-28 | 2021-04-28 | 2022-04-25 | 2022-04-28 | 2022-04-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546834 | T2 EI TMBLR-SAN LIS BISP RPL INSS 6TWRS | 93K
LC | 120896230 | 008/053 | T2 EI STAN-MEL SS-MAN 8/53 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-28 | 2021-04-28 | 2022-01-25 | 2022-04-28 | 2022-04-28 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45122260 | T2 EI STAN-MEL SS-MAN 8/53 RPR FOND | ICQ
LC | 120896380 | 039/224 | T2 EI TMBLR-SAN LIS BISP 39/224 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-28 | 2021-04-28 | 2022-04-25 | 2022-04-28 | 2022-04-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546834 | T2 EI TMBLR-SAN LIS BISP RPL INSS 6TWRS | 93K
LC | 120896381 | 039/225 | T2 EI TMBLR-SN LIS OBSP 39/225 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-28 | 2021-04-28 | 2022-04-25 | 2022-04-28 | 2022-04-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546834 | T2 EI TMBLR-SAN LIS BISP RPL INSS 6TWRS | 93K
LC | 120896456 | 038/165 | T2 EI MORRO BAY-SLR #1 38/165 RPLS INSS | PISMOBCH | ETL.5300.TOWR | 2021-04-28 | 2021-04-28 | 2022-06-16 | 2022-04-28 | 2022-04-28 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528621 | EI MORRO BAY-SOLAR SS #1 RPLC INNS 18TW | 93K
LC | 120896591 | 004/040 | T2 EI PIT #1-CTNWD 4/40 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-04-28 | 2021-04-28 | 2022-08-02 | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149336 | T2 EI PIT #1-CTNWD 4/40 RPR FOND | ICQ
LC | 120896615 | 015/005 | T2 EI MNDCNO-WLTS-FRT BRGG 15/5 REPL PL | WILLITS | ETL.7550.POLE.WOOD | 2021-04-28 | 2021-04-28 | 2022-10-04 | 2022-04-28 | 2022-04-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31537422 | T2 EI MNDCNO-WLTS-FRT BRGG 15/5 REPL PL | 70Y
LC | 120896629 | 038/222 | T2 EI TMBLR-SN LIS OBISP 38/222 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-28 | 2021-04-28 | 2022-04-25 | 2022-04-28 | 2022-04-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546833 | T2 EI TMBLR-SN LUIS OBSP RPL INSS 7TWRS | 93K
LC | 120896740 | 037/164B | T2 EI MORRO BAY-SLR #2 37/164B RPLC INSS | PISMOBCH | ETL.5310.INSL | 2021-04-28 | 2021-04-28 | 2022-07-26 | 2022-04-28 | 2022-04-28 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549069 | T2 EI MORRO BAY-SOLAR #2 RPL INSS 5TWRS | 93K
LC | 120896794 | 008/051 | T2 EI STNLS-MLNS SW ST-MNT 8/51 RPR SPL | VICTOR | ETL.3830.TOWR | 2021-04-28 | 2021-04-28 | 2022-03-03 | 2022-04-28 | 2022-04-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 44978043 | T2 EI STNLS-MLNS SW ST-MNT 8/51 RPR SPL | ICS
LC | 120896825 | 008/050 | T2 EI STAN-MAN #2 8/50 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-28 | 2021-04-28 | 2022-01-25 | 2022-04-28 | 2022-04-28 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45122117 | T2 EI STAN-MAN #2 8/50 RPR FOND | ICQ
LC | 120896965 | 004/040 | T2 EI PIT #3-PIT #1 4/40 RMV NEST | TABLEMTN | ETL.5400.TOWR | 2021-04-28 | 2021-04-28 | 2022-10-11 | 2022-04-28 | 2022-04-28 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove | 45213908 | T2 EI PIT #3-PIT #1 4/40 RMV NEST | ICS
LC | 120897008 | 038/254 | T2 DI POE-RIO OSO 038/254 INS HRDT | TABLEMTN | ETL.5540.TOWR | 2021-04-28 | 2021-04-28 | 2021-06-19 | 2022-04-28 | 2022-04-28 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Tower | Install | 44880477 | T2 DI POE-RIO OSO 038/254 INS HRDT | ICQ
LC | 120897043 | 020/165 | T2 EI PIT #1-COTNWOD 20/165 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-04-28 | 2021-04-28 | 2022-07-22 | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45149504 | T2 EI PIT #1-COTNWOD 20/165 RPR STRT | ICQ
LC | 120897440 | 008/047 | T2 EI STAN-MAN #2 8/47 RPR INSS | VICTOR | ETL.3820.INSL.NCER | 2021-04-28 | 2021-04-28 | 2021-12-09 | 2022-04-28 | 2022-04-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45067143 | T2 EI STAN-MAN #2 8/47 RPR INSS | ICS
LC | 120897572 | 039/002 | T2 EI FULTON-HOPLAND 39/2 RPR SWTC | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-04-28 | 2021-04-28 | 2022-06-21 | 2022-04-28 | 2022-04-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45144026 | T2 EI FULTON-HOPLAND 39/2 RPR SWTC | ICW
LC | 120897587 | 010/356 | T2 EI SPAULDING-SUMMIT 10/356 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-28 | 2021-04-28 | 2022-09-19 | 2022-04-28 | 2022-04-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31537210 | EI SPAULDING-SUMMIT 8/280 RPL POLE | 70Y
LC | 120897588 | 010/357 | T2 EI SPAULDING-SUMMIT 10/357 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-28 | 2021-04-28 | 2022-09-19 | 2022-04-28 | 2022-04-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31537210 | EI SPAULDING-SUMMIT 8/280 RPL POLE | 70Y
LC | 120897600 | 010/358 | T2 EI SPAULDING-SUMMIT 10/358 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-28 | 2021-04-28 | 2022-09-18 | 2022-04-28 | 2022-04-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31537210 | EI SPAULDING-SUMMIT 8/280 RPL POLE | 70Y
LC | 120897601 | 010/360 | T2 EI SPAULDING-SUMMIT 10/360 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-28 | 2021-04-28 | 2022-09-18 | 2022-04-28 | 2022-04-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31537210 | EI SPAULDING-SUMMIT 8/280 RPL POLE | 70Y
LC | 120897678 | 019/157 | T2 EI PIT #1-COTNWD 19/157 RPR FOUND | TABLEMTN | ETL.5390.TOWR | 2021-04-28 | 2021-04-28 | 2022-07-21 | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149501 | T2 EI PIT #1-COTNWD 19/157 RPR FOUND | ICQ
LC | 120897731 | 019/156 | T2 EI PIT #1-COTNWOD 19/156 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-04-28 | 2021-04-28 | 2022-07-21 | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149500 | T2 EI PIT #1-COTNWOD 19/156 RPR FOND | ICQ
LC | 120897785 | 001/014 | T2 EI MNDCN-WLTS-FRT BRG 01/014 RMV VEG | LAKEVLLE | ETL.7550.POLE.WOOD | 2021-04-28 | 2021-04-28 | 2022-02-17 | 2022-04-28 | 2022-04-28 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAR | Overgrown | Vegetation | Remove
LC | 120898020 | 083/424 | EI T2 MALIN-ROUND MTN #2 83/424 RPL GYWS | TABLEMTN | ETL.6020.TOWR | 2021-04-28 | 2021-04-28 | 2022-08-09 | 2022-04-28 | 2022-04-28 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Replace | 45198258 | EI T2 MALIN-ROUND MTN #2 83/424 RPL GYWS | ICS
LC | 120898356 | 045/184 | T2 EI DIABLO-MIDWAY #2 45/184 RPR STRT | PISMOBCH | ETL.5970.TOWR | 2021-04-28 | 2021-04-28 | 2022-07-12 | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45073725 | T2 EI DIABLO-MIDWAY #2 45/184 RPR STRT | ICQ
LC | 120898454 | 007/016 | T2 EI MELONES-RACETRACK 7/16 RPL INSW | VICTOR | ETL.2400.INSL.NCER | 2021-04-28 | 2021-04-28 | 2022-04-27 | 2022-04-28 | 2022-04-28 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31601762 | T2 EI MELONES-RACETRACK 7/16 RPL INSW | 93I
LC | 120898675 | 083/421 | EI T2 MALIN-ROUND MTN #2 83/421 RPR STRT | TABLEMTN | ETL.6020.TOWR | 2021-04-29 | 2021-04-27 | 2022-07-15 | 2022-04-27 | 2022-04-27 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Structure-Tower | Repair | 45198257 | EI T2 MALIN-ROUND MTN #2 83/421 RPR STRT | ICQ
LC | 120898888 | 000/005 | T2 EI MORAGA-CSTR VALY 0/5 RPR STRT | CONCORD | ETL.5250.TOWR | 2021-04-29 | 2021-04-28 | 2022-01-22 | 2022-04-28 | 2022-04-28 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45147235 | T2 EI MORAGA-CSTR VALY 0/5 RPR STRT | ICQ
LC | 120899152 | 000/005 | T2 JEFFERSON-STANFORD 0/5 COMPLETE | METCALF | ETL.7220.POLE.WOOD | 2021-04-29 | 2021-04-29 | 2022-06-26 | 2022-04-29 | 2022-04-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH RTNR FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31539808 | T2 JEFFERSON-STANFORD 0/5 RPL STRW | 70Y
LC | 120899170 | 010/048 | T2 EI BRENTWOOD-KELSO 10/48 RPR FOND | CONCORD | ETL.4410.TOWR | 2021-04-29 | 2021-04-27 | 2022-01-06 | 2022-04-27 | 2022-04-27 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45107668 | T2 EI BRENTWOOD-KELSO 10/48 RPR FOND | ICQ
LC | 120899191 | 008/040 | T2 EI BRENTWOOD-KELSO 8/40 RMV STEP | CONCORD | ETL.4410.TOWR | 2021-04-29 | 2021-04-27 | 2022-01-06 | 2022-04-27 | 2022-04-27 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45106482 | T2 EI BRENTWOOD-KELSO 8/40 RMV STEP | ICQ
LC | 120899208 | 007/046 | T2 EI STNSLS-MLNS-MNTC 7/46 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-29 | 2021-04-29 | 2022-01-25 | 2022-04-29 | 2022-04-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45122111 | T2 EI STNSLS-MLNS-MNTC 7/46 RPR FOND | ICQ
LC | 120899304 | 036/158 | T2 EI MORRO BY-SLR SS #1 36/158 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-29 | 2021-04-29 | 2022-06-16 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528621 | EI MORRO BAY-SOLAR SS #1 RPLC INNS 18TW | 93K
LC | 120899305 | 036/158 | T2 EI MORRO BAY-SOLAR #2 36/158 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-29 | 2021-04-29 | 2022-07-26 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549069 | T2 EI MORRO BAY-SOLAR #2 RPL INSS 5TWRS | 93K
LC | 120899481 | 036/157 | T2 EI MORRO BAY-SOLAR #2 36/157 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-29 | 2021-04-29 | 2022-07-26 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549069 | T2 EI MORRO BAY-SOLAR #2 RPL INSS 5TWRS | 93K
LC | 120899482 | 036/157 | T2 EI MORRO BY-SLR SS #1 36/157 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-29 | 2021-04-29 | 2022-06-17 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528621 | EI MORRO BAY-SOLAR SS #1 RPLC INNS 18TW | 93K
LC | 120899483 | 007/044 | T2 EI STNISLAUS-MANTECA #2 7/44 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-04-29 | 2021-04-29 | 2022-01-20 | 2022-04-29 | 2022-04-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP TNT COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45122106 | T2 EI STNISLAUS-MANTECA #2 7/44 RPR FOND | ICQ
LC | 120899529 | 007/045 | T2 EI STNSLS-MLNS-MNTC 7/45 RPR INSS | VICTOR | ETL.3830.INSL | 2021-04-29 | 2021-04-29 | 2021-05-25 | 2022-04-29 | 2022-04-29 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44826340 | T2 EI STNSLS-MLNS-MNTC 7/45 RPR INSS | ICS
LC | 120899540 | 007/045 | T2 EI STNSLS-MLNS-MNTC 7/45 RPR STRT | VICTOR | ETL.3830.TOWR | 2021-04-29 | 2021-04-29 | 2022-01-20 | 2022-04-29 | 2022-04-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45122110 | T2 EI STNSLS-MLNS-MNTC 7/45 RPR STRT | ICQ
LC | 120899655 | 036/156 | T2 EI MORRO BAY-SOLAR #2 36/156 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-29 | 2021-04-29 | 2022-07-26 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549069 | T2 EI MORRO BAY-SOLAR #2 RPL INSS 5TWRS | 93K
LC | 120899657 | 036/156 | T2 EI MORRO BY-SLR SS #1 36/156 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-29 | 2021-04-29 | 2022-06-17 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528621 | EI MORRO BAY-SOLAR SS #1 RPLC INNS 18TW | 93K
LC | 120899860 | 007/044 | T2 EI STNSLS-MLNS-MNTC 7/44 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-29 | 2021-04-29 | 2022-01-20 | 2022-04-29 | 2022-04-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45122107 | T2 EI STNSLS-MLNS-MNTC 7/44 RPR FOND | ICQ
LC | 120899893 | 007/043 | T2 EI STANISLAUS-MANTECA #2 7/43 UNBURY | VICTOR | ETL.3820.TOWR | 2021-04-29 | 2021-04-29 | 2022-01-19 | 2022-04-29 | 2022-04-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45122104 | T2 EI STANISLAUS-MANTECA #2 7/43 UNBURY | ICQ
LC | 120899929 | 008/209 | T2 EI COTTONWD-BNTN #1 8/209 RPR STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-04-29 | 2021-04-29 | 2022-09-01 | 2022-04-29 | 2022-04-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213467 | T2 EI COTTONWD-BNTN #1 8/209 RPR STRW | ICW
LC | 120900018 | 089/452A | EI T2 MALIN-ROUND MTN #2 89/452 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-04-29 | 2021-04-29 | 2022-07-15 | 2022-04-29 | 2022-04-29 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Ground Wire-Tower | Replace | 45198268 | EI T2 MALIN-ROUND MTN #2 89/452 RPR GYWS | ICQ
LC | 120900166 | 013/435 | T2 EI SPAULDING-SUMMIT 13/435 RPR STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-29 | 2021-04-29 | 2021-07-24 | 2022-04-29 | 2022-04-29 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542649 | SPAULDING-SUMMIT 008/275 RPL POLE | 70Y
LC | 120900255 | 035/150 | T2 EI MORRO BAY-SOLAR #2 35/150 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-29 | 2021-04-29 | 2022-07-26 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549068 | T2 DI MR BY-SLR SW ST #2 RPL INSS 7TWRS | 93K
LC | 120900257 | 035/150 | T2 EI MORRO BY-SLR SS #1 35/150 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-29 | 2021-04-29 | 2022-06-17 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528621 | EI MORRO BAY-SOLAR SS #1 RPLC INNS 18TW | 93K
LC | 120900282 | 002/061 | EI T2 COLGATE-ALLEGHANY 2/61 RMV BUTT | SACTO | ETL.6470.POLE.WOOD | 2021-04-29 | 2021-04-29 | 2021-08-09 | 2022-04-29 | 2022-04-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44777229 | EI T2 COLGATE-ALLEGHANY 2/61 RMV BUTT | ICW
LC | 120900287 | 013/433 | T2 EI SPAULDING-SMMT 13/433 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-29 | 2021-04-29 | 2022-09-17 | 2022-04-29 | 2022-04-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542649 | SPAULDING-SUMMIT 008/275 RPL POLE | 70Y
LC | 120900358 | 035/151 | T2 EI MORRO BY-SLR SS #1 35/151 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-29 | 2021-04-29 | 2022-06-17 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528621 | EI MORRO BAY-SOLAR SS #1 RPLC INNS 18TW | 93K
LC | 120900359 | 035/151 | T2 EI MORRO BAY-SOLAR #2 35/151 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-29 | 2021-04-29 | 2022-07-26 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549068 | T2 DI MR BY-SLR SW ST #2 RPL INSS 7TWRS | 93K
LC | 120900375 | 013/432 | T2 EI SPAULDING-SMMT 13/432 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-29 | 2021-04-29 | 2022-09-17 | 2022-04-29 | 2022-04-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542649 | SPAULDING-SUMMIT 008/275 RPL POLE | 70Y
LC | 120900465 | 013/431 | T2 EI SPAULDING-SMMT 13/431 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-29 | 2021-04-29 | 2022-09-17 | 2022-04-29 | 2022-04-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542649 | SPAULDING-SUMMIT 008/275 RPL POLE | 70Y
LC | 120900467 | 035/152 | T2 EI MORRO BAY-SOLAR #2 35/152 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-29 | 2021-04-29 | 2022-07-26 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549068 | T2 DI MR BY-SLR SW ST #2 RPL INSS 7TWRS | 93K
LC | 120900592 | 012/430 | T2 EI SPAULDING-SMMT 12/430 RPL TIED | SACTO | ETL.8060.POLE.WOOD | 2021-04-29 | 2021-04-29 | 2022-09-17 | 2022-04-29 | 2022-04-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45074214 | T2 EI SPAULDING-SMMT 12/430 RPL TIED | ICW
LC | 120900593 | 035/153 | T2 EI MORRO BAY-SOLAR #235/153 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-29 | 2021-04-29 | 2022-07-26 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549068 | T2 DI MR BY-SLR SW ST #2 RPL INSS 7TWRS | 93K
LC | 120900611 | 000/004A | T2 EI HAMILTON BRNCH-CHSTR 0/4A RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-04-29 | 2021-04-29 | 2022-07-29 | 2022-04-29 | 2022-04-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213330 | T2 EI HAMILTON BRNCH-CHSTR 0/4A RPR STRW | ICW
LC | 120900612 | 000/004A | T2 EI HAMILTON BRNCH-CHSTR 0/4A RPR CRSM | TABLEMTN | ETL.7000.POLE.WOOD | 2021-04-29 | 2021-04-29 | 2022-07-29 | 2022-04-29 | 2022-04-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45268042 | T2 EI HAMILTON BRNCH-CHSTR 0/4A RPR CRSM | ICW
LC | 120900732 | 003/035 | T2 EI PIT #3-PIT #1 3/35 RMV NEST | TABLEMTN | ETL.5400.TOWR | 2021-04-29 | 2021-04-29 | 2022-10-10 | 2022-04-29 | 2022-04-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45213907 | T2 EI PIT #3-PIT #1 3/35 RMV NEST | ICS
LC | 120900736 | 035/154 | T2 EI MORRO BY-SLR SS #1 35/154 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-29 | 2021-04-29 | 2022-06-17 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528621 | EI MORRO BAY-SOLAR SS #1 RPLC INNS 18TW | 93K
LC | 120900813 | :000/001 | T2 DI STNSLS-MLNS-MNTC 0/1 RPL INSS | VICTOR | ETL.3840.INSL.NCER | 2021-04-29 | 2021-04-13 | 2022-05-17 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546924 | T2 DI STNSLS-MLNS-MNTC RPL INSS 8TWRS | 93K
LC | 120900818 | :000/001 | T2 DI STNSLS-MLNS-MNTC 0/1 RPL INSS | VICTOR | ETL.3830.INSL.NCER | 2021-04-29 | 2021-04-13 | 2021-12-18 | 2022-04-13 | 2022-04-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549338 | T2 DI STNSLS-MLNS-MNTC RPL INSS 8TWRS | 93K
LC | 120900826 | 036/155 | T2 EI MORRO BY-SLR SS #1 36/155 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-29 | 2021-04-29 | 2022-06-17 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528621 | EI MORRO BAY-SOLAR SS #1 RPLC INNS 18TW | 93K
LC | 120900828 | 036/155 | T2 EI MORRO BAY-SOLAR #2 36/155 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-04-29 | 2021-04-29 | 2022-07-26 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549068 | T2 DI MR BY-SLR SW ST #2 RPL INSS 7TWRS | 93K
LC | 120900888 | 003/034 | T2 EI PIT #3-PIT #1 3/34 RMV NEST | TABLEMTN | ETL.5400.TOWR | 2021-04-29 | 2021-04-29 | 2022-10-10 | 2022-04-29 | 2022-04-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove | 45213906 | T2 EI PIT #3-PIT #1 3/34 RMV NEST | ICS
LC | 120901071 | 009/111 | T2 EI DRUM-SUMMIT #1_009/111 RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2021-04-29 | 2021-04-29 | 2022-08-23 | 2022-04-29 | 2022-04-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31543339 | T2 EI DRUM-SUMMIT #1 9/111 RPL STRW | 70Y
LC | 120901098 | 005/064 | T2 WV IGNACIO-BOLINAS #2 5/64 INS DAMW | LAKEVLLE | ETL.7180.INSL.NCER | 2021-04-29 | 2021-04-29 | 2022-10-05 | 2022-04-29 | 2022-04-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO SR22 | Missing | Damper-Wood | Install | 45142938 | T2 WV IGNACIO-BOLINAS #2 5/64 INS DAMW | ICW
LC | 120901137 | 087/443 | T2 EI MALIN-RND MTN #2 87/443 RPR ANCS | TABLEMTN | ETL.6020.TOWR | 2021-04-29 | 2021-04-29 | 2022-04-20 | 2022-04-29 | 2022-04-29 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair | 45198265 | T2 EI MALIN-RND MTN #2 87/443 RPR ANCS | ICS
LC | 120901201 | 003/032 | T2 EI PIT #1-COTTONWOOD 3/32 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-04-29 | 2021-04-29 | 2022-08-01 | 2022-04-29 | 2022-04-29 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195440 | T2 EI PIT #1-COTTONWOOD 3/32 RPR FOND | ICQ
LC | 120901273 | 042/170 | T2 EI DIABLO-MIDWAY #3 42/170 RPR STRT | PISMOBCH | ETL.5980.TOWR | 2021-04-29 | 2021-04-29 | 2022-06-15 | 2022-04-29 | 2022-04-29 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45073736 | T2 EI DIABLO-MIDWAY #3 42/170 RPR STRT | ICQ
LC | 120901338 | 047/003 | T2 EI HUMBOLDT-TRINITY 47/03 RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-04-29 | 2021-04-29 | 2022-06-03 | 2022-04-29 | 2022-04-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31540677 | T2 EI HUMBOLDT-TRINITY 47/03 RPL POLE | 70Y
LC | 120901561 | 029/180 | T2 EI HELMS-GREGG #1 29/180 RMV NEST | FRESNO | ETL.4870.TOWR | 2021-04-29 | 2021-04-29 | 2022-08-23 | 2022-04-29 | 2022-04-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45067875 | T2 EI HELMS-GREGG #1 29/180 RMV NEST | ICS
LC | 120903209 | 032/187 | T2 EI TMBLR-SN LUS OBSPO 32/187 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-29 | 2021-04-29 | 2022-04-22 | 2022-04-29 | 2022-04-29 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546831 | T2 EI TMBLR-SN LIS OBISP RPL INSS 7TWRS | 93K
LC | 120903215 | 023/203 | T2 WV BRIDGEVILL-CTTNWD 23/203 INS DAMS | TABLEMTN | ETL.1110.INSL.NCER | 2021-04-29 | 2021-04-29 | 2022-06-22 | 2022-04-29 | 2022-04-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install | 45211782 | T2 WV BRIDGEVILL-CTTNWD 23/203 INS DAMS | ICS
LC | 120903289 | 005/005 | T2 DI CHOWCHILLA-KERCKHOFF 5/5 RPL INSW | FRESNO | ETL.1250.INSL.NCER | 2021-04-29 | 2021-04-22 | 2022-02-18 | 2022-04-22 | 2022-04-22 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31539801 | T2 DI CHOWCHILLA-KERCKHOFF 4/1 RPLC INSW | 93I
LC | 120903610 | 032/189 | T2 EI TMBLR-SN LUS OBSPO 32/189 RMV NEST | PISMOBCH | ETL.3960.TOWR | 2021-04-29 | 2021-04-29 | 2022-08-29 | 2022-04-29 | 2022-04-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45069390 | T2 EI TMBLR-SN LUS OBSPO 32/189 RMV NEST | ICS
LC | 120903612 | 012/422 | T2 EI SPAULDING-SMMT 12/422 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-04-29 | 2021-04-29 | 2022-08-05 | 2022-04-29 | 2022-04-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45074217 | T2 EI SPAULDING-SMMT 12/422 RPR GYWW | ICW
LC | 120903615 | 032/188 | T2 EI TMBLR-SN LUS OBSPO 32/188 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-29 | 2021-04-29 | 2022-04-22 | 2022-04-29 | 2022-04-29 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546831 | T2 EI TMBLR-SN LIS OBISP RPL INSS 7TWRS | 93K
LC | 120903616 | 012/421 | T2 EI SPAULDING-SMMT 12/421 RPL TIED | SACTO | ETL.8060.POLE.WOOD | 2021-04-29 | 2021-04-29 | 2022-09-21 | 2022-04-29 | 2022-04-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 44812251 | T2 EI SPAULDING-SMMT 12/421 RPL TIED | ICW
LC | 120903619 | 032/189 | T2 EI TMBLR-SN LUS OBPO 32/189 RPL INSS | PISMOBCH | ETL.3960.INSL.NCER | 2021-04-29 | 2021-04-29 | 2022-08-29 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546831 | T2 EI TMBLR-SN LIS OBISP RPL INSS 7TWRS | 93K
LC | 120903716 | 042/173 | T2 EI DIABLO-MIDWAY #3 42/173 RPR GYWS | PISMOBCH | ETL.5980.TOWR | 2021-04-29 | 2021-04-29 | 2022-06-15 | 2022-04-29 | 2022-04-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068592 | T2 EI DIABLO-MIDWAY #3 42/173 RPR GYWS | ICS
LC | 120903746 | 029/177 | T2 EI HLMS-GRG #1 29/177 RPR FOND CMPLTD | FRESNO | ETL.4870.TOWR | 2021-04-29 | 2021-04-29 | 2022-05-18 | 2022-04-29 | 2022-04-29 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45069257 | T2 EI HELMS-GREGG #1 29/177 RPR FOND | ICQ
LC | 120903958 | 010/116 | T2 EI DRUM-SUMMIT#2 10/116 RPR INSW | SACTO | ETL.1450.INSL.NCER | 2021-04-29 | 2021-04-29 | 2022-06-12 | 2022-04-29 | 2022-04-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44776406 | T2 EI DRUM-SUMMIT#2 10/116 RPR INSW | ICS
LC | 120904189 | 038/010 | T2 EI FLTN-HOPLAND 38/10 RPR GYWW | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-04-29 | 2021-04-29 | 2022-06-21 | 2022-04-29 | 2022-04-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45144022 | T2 EI FLTN-HOPLAND 38/10 RPR GYWS | ICS
LC | 120904504 | 028/174 | T2 EI HELMS-GREGG #1 28/174 RPR ROAD | FRESNO | ETL.4870.TOWR | 2021-04-29 | 2021-04-29 | 2022-05-11 | 2022-04-29 | 2022-04-29 | Late | 932 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Road | Repair | 44658001 | HELMS-GREGG ACCESS ROADS 2/21A VGETATION | CHS
LC | 120904697 | 043/176 | T2 EI DIABLO-MIDWAY #3 43/176 RPR GYWS | PISMOBCH | ETL.5980.TOWR | 2021-04-29 | 2021-04-29 | 2022-06-15 | 2022-04-29 | 2022-04-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | Missing | Guy Wire-Steel | Install | 45068593 | T2 EI DIABLO-MIDWAY #3 43/176 RPR GYWS | ICS
LC | 120905266 | 038/333 | T2 EI PIT #1-COTTONWOOD 38/333 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-04-29 | 2021-04-21 | 2022-08-03 | 2022-04-21 | 2022-04-21 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149531 | T2 EI PIT #1-COTTONWOOD 38/333 RPR FOND | ICQ
LC | 120906945 | 005/035 | T2 EI STNSLS-MNS SW ST-MNT 5/35 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-04-30 | 2021-04-30 | 2022-01-24 | 2022-04-30 | 2022-04-30 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45119929 | T2 EI STNSLS-MNS SW ST-MNT 5/35 RPR FOND | ICQ
LC | 120907084 | 012/413 | T2 EI SPAULDING-SUMMIT 12/413 RPR SPLW | SACTO | ETL.8060.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2021-07-22 | 2022-04-30 | 2022-04-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Repair | 44808342 | T2 EI SPAULDING-SUMMIT 12/413 RPR SPLW | ICW
LC | 120907439 | C004/020 | T2 DI COBURN-LAS AGUILAS C4/20 RPR INSS | MOSSLNDG | ETL.4460.INSL | 2021-04-30 | 2021-04-15 | 2021-11-18 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44961513 | T2 DI COBURN-LAS AGUILAS C4/20 RPR INSS | ICS
LC | 120907580 | 016/228 | T2 DI SSQC-SNT YNZ SW ST 16/228 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-30 | 2021-04-27 | 2022-03-02 | 2022-04-27 | 2022-04-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069324 | T2 DI SSQC-SNT YNZ SW ST 16/228 RPR STRW | ICW
LC | 120907840 | 091/463 | EI T2 MALIN-ROUND MTN #2 91/463 RPR STRT | TABLEMTN | ETL.6020.TOWR | 2021-04-30 | 2021-04-30 | 2022-07-20 | 2022-04-30 | 2022-04-30 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45198272 | EI T2 MALIN-ROUND MTN #2 91/463 RPR STRT | ICQ
LC | 120907884 | 091/464 | EI T2 MALIN-ROUND MTN #2 91/464 RPR STRT | TABLEMTN | ETL.6020.TOWR | 2021-04-30 | 2021-04-30 | 2022-07-20 | 2022-04-30 | 2022-04-30 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45198273 | EI T2 MALIN-ROUND MTN #2 91/464 RPR STRT | ICQ
LC | 120908033 | 010/119C | T2 EI DRUM-SUMMIT #2 10/119C RPL STRW | SACTO | ETL.1450.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2021-11-01 | 2022-04-30 | 2022-04-30 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31531879 | T2 DI DRUM-SUMMIT #2 2/31L RPL STRW | 70Y
LC | 120908046 | 005/029 | T2 EI STNLS-MLNS SW ST-RVR 5/29 RPR SPLS | VICTOR | ETL.3840.INSL.CERA | 2021-04-30 | 2021-04-30 | 2022-05-11 | 2022-04-30 | 2022-04-30 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122130 | T2 EI STNLS-MLNS SW ST-RVR 5/29 RPR SPLS | ICS
LC | 120908047 | 005/029 | T2 EI STNISLS-MNTCA #2 5/2 RPR STRT | VICTOR | ETL.3820.TOWR | 2021-04-30 | 2021-04-30 | 2022-01-19 | 2022-04-30 | 2022-04-30 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45119719 | T2 EI STNISLS-MNTCA #2 5/2 RPR STRT | ICQ
LC | 120908072 | 027/108A | T2 DI DIABLO-MIDWAY #2 27/108A RPR STRT | PISMOBCH | ETL.5970.TOWR | 2021-04-30 | 2021-04-29 | 2022-06-03 | 2022-04-29 | 2022-04-29 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45073726 | T2 DI DIABLO-MIDWAY #2 27/108A RPR STRT | ICQ
LC | 120908165 | 011/400 | T2 EI SPLDING-SMMT 11/400 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2022-09-18 | 2022-04-30 | 2022-04-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542649 | SPAULDING-SUMMIT 008/275 RPL POLE | 70Y
LC | 120908248 | 000/025 | T2 EI HMLTN BRNCH-CHSTR 0/25 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2022-07-25 | 2022-04-30 | 2022-04-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31539905 | T2 EI HMLTN BRNCH-CHSTR 0/25 RPL STRW | 70Y
LC | 120908466 | 011/397 | T2 EI SPLDING-SMMIT 11/397 RPL CRSRMW | SACTO | ETL.8060.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2022-09-22 | 2022-04-30 | 2022-04-30 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31541925 | T2 EI SPLDING-SMMIT 11/397 RPL CRSRMW | 93E
LC | 120908511 | 091/465 | T2 EI MALIN-ROUND MTN #2 91/465 RPR STRT | TABLEMTN | ETL.6020.TOWR | 2021-04-30 | 2021-04-30 | 2022-07-20 | 2022-04-30 | 2022-04-30 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45198274 | EI T2 MALIN-ROUND MTN #2 91/465 RPR STRT | ICQ
LC | 120908642 | 000/027 | T2 EI HMLTN BRNCH-CHSTR 0/27 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2022-07-25 | 2022-04-30 | 2022-04-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31539905 | T2 EI HMLTN BRNCH-CHSTR 0/25 RPL STRW | 70Y
LC | 120908860 | 000/030 | T2 EI HMLTN BRNCH-CHSTR 0/30 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2022-07-25 | 2022-04-30 | 2022-04-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31539905 | T2 EI HMLTN BRNCH-CHSTR 0/25 RPL STRW | 70Y
LC | 120908874 | 010/121 | T2 EI DRUM-SUMMIT #1 10/121R RPL ANCW | SACTO | ETL.1440.POLE.WDPS | 2021-04-30 | 2021-04-30 | 2022-06-25 | 2022-04-30 | 2022-04-30 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31540570 | T2 EI DRUM-SUMMIT #1 10/121 RPL ANCW | 93E
LC | 120908949 | 033/195 | T2 EI TMBLR-SN LUIS OBSP 33/195 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-30 | 2021-04-30 | 2022-04-20 | 2022-04-30 | 2022-04-30 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546831 | T2 EI TMBLR-SN LIS OBISP RPL INSS 7TWRS | 93K
LC | 120908998 | 010/123 | T2 EI DRUM-SUMMIT#2 10/123 RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-04-30 | 2021-04-30 | 2022-07-19 | 2022-04-30 | 2022-04-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31543771 | T3 DI DRUM-SUMMIT #2 0/5C RPL STRW | 70Y
LC | 120909015 | 010/123 | T2 EI DRUM-SUMMIT#2 10/123 RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-04-30 | 2021-04-30 | 2022-07-19 | 2022-04-30 | 2022-04-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31543771 | T3 DI DRUM-SUMMIT #2 0/5C RPL STRW | 70Y
LC | 120909044 | 048/001B | T2 EI HUMBOLDT-TRINITY 048/001B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2021-04-30 | 2021-04-30 | 2022-03-27 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45158837 | T2 EI HUMBOLDT-TRINITY 048/001A RPR STRW | ICW
LC | 120909048 | 048/001C | T2 EI HUMBOLDT-TRINITY 048/001C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2021-04-30 | 2021-04-30 | 2022-03-27 | 2022-04-30 | 2022-04-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45158837 | T2 EI HUMBOLDT-TRINITY 048/001A RPR STRW | ICW
LC | 120909053 | 001/033 | T2 EI HMLTN BRNCH-CHSTR 1/33 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2022-07-25 | 2022-04-30 | 2022-04-30 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213331 | T2 EI HMLTN BRNCH-CHSTR 1/33 RPR STRW | ICW
LC | 120909054 | 048/001A | T2 EI HUMBOLDT-TRINITY 048/001A RPR STRW | EUREKA | ETL.1820.POLE.NWOD | 2021-04-30 | 2021-04-30 | 2022-03-27 | 2022-04-30 | 2022-04-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45158837 | T2 EI HUMBOLDT-TRINITY 048/001A RPR STRW | ICW
LC | 120909131 | 033/196 | T2 EI TMBLR-SN LUIS OBSP 33/196 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-30 | 2021-04-30 | 2022-04-20 | 2022-04-30 | 2022-04-30 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546831 | T2 EI TMBLR-SN LIS OBISP RPL INSS 7TWRS | 93K
LC | 120909295 | 024/159 | T2 DI POE-RIO OSO 24/159 RPR INSS | TABLEMTN | ETL.5540.INSL.CERA | 2021-04-30 | 2021-04-15 | 2022-08-02 | 2022-04-15 | 2022-04-15 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213416 | T2 DI POE-RIO OSO 24/159 RPR INSS | ICS
LC | 120909460 | 007/002 | T2 EI HOWCHILLA-KERCKHOFF 7/2 RPL INSW | FRESNO | ETL.1250.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2022-02-18 | 2022-04-30 | 2022-04-30 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31539801 | T2 DI CHOWCHILLA-KERCKHOFF 4/1 RPLC INSW | 93I
LC | 120909545 | 027/123 | T2 DI TESLA-LOS BANOS #1 27/123 RPR SHLS | VICTOR | ETL.6100.TOWR | 2021-04-30 | 2021-04-30 | 2022-08-04 | 2022-04-30 | 2022-04-30 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45150285 | T2 DI TESLA-LOS BANOS #1 27/123 RPR SHLS | ICS
LC | 120909944 | 094/480 | EI T2 MALIN-ROUND MTN #2 94/480 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-04-30 | 2021-04-30 | 2022-08-11 | 2022-04-30 | 2022-04-30 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45198279 | EI T2 MALIN-ROUND MTN #2 94/480 RPR GYWS | ICS
LC | 120909945 | 094/480 | EI T2 MALIN-ROUND MTN #2 94/480 RPR STRT | TABLEMTN | ETL.6020.TOWR | 2021-04-30 | 2021-04-30 | 2022-08-11 | 2022-04-30 | 2022-04-30 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45198300 | EI T2 MALIN-ROUND MTN #2 94/480 RPR STRT | ICQ
LC | 120910266 | 036/698 | T2 HAT CREEK #1-WESTWOOD 36/698 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2021-06-17 | 2022-04-30 | 2022-04-30 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31541163 | T2 HAT CREEK #1-WESTWOOD 28/556 REFRAME | 93E
LC | 120910289 | 028/556 | T2 HAT CREEK #1-WESTWOOD 28/556 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2021-06-23 | 2022-04-30 | 2022-04-30 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31541163 | T2 HAT CREEK #1-WESTWOOD 28/556 REFRAME | 93E
LC | 120910310 | 022/434 | T2 HAT CREEK #1-WESTWOOD 22/434 RMV VEG | TABLEMTN | ETL.7030.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2022-10-26 | 2022-04-30 | 2022-04-30 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO FRAB SR22 | Overgrown | Vegetation | Remove
LC | 120910401 | 012/007 | T2 EI FLTN-HPLND 12/007 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2022-06-24 | 2022-04-30 | 2022-04-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31596730 | T2 EI FLTN-HPLND 12/007 RPL STRW | 70Y
LC | 120910680 | 019/005 | T2 EI MNDCNO-WLLTS-FRT BRG 19/5 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2022-08-24 | 2022-04-30 | 2022-04-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | Rotten | Structure-Wood | Replace | 31537422 | T2 EI MNDCNO-WLTS-FRT BRGG 15/5 REPL PL | 70Y
LC | 120910707 | 021/005 | T2 EI MNDCN-WLTS-FRT BRG 21/5 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2022-08-21 | 2022-04-30 | 2022-04-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31596073 | T2 EI MNDCN-WLTS-FRT BRG 21/5 RPL POLE | 70Y
LC | 120910709 | 021/003 | T2 EI MNDCN-WLTS-FRT BRG 21/3 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2022-08-23 | 2022-04-30 | 2022-04-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31547473 | T2 EI MNDCN-WLTS-FRT BRG 23/6R RPL POLE | 70Y
LC | 120910750 | 019/008 | T2 EI MNDCN-WLTS-FRT BRG 19/8 RPL POL | WILLITS | ETL.7550.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2022-05-23 | 2022-04-30 | 2022-04-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31537422 | T2 EI MNDCNO-WLTS-FRT BRGG 15/5 REPL PL | 70Y
LC | 120910756 | 017/009 | T2 EI MNDCN-WLTS-FRT BRG 017/9 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2022-08-18 | 2022-04-30 | 2022-04-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31537422 | T2 EI MNDCNO-WLTS-FRT BRGG 15/5 REPL PL | 70Y
LC | 120910868 | 037/001 | T2 EI FULTON-HOPLND 37/1 RPR STRW CMPLTD | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-04-30 | 2021-04-30 | 2022-05-13 | 2022-04-30 | 2022-04-30 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143996 | T2 EI FULTON-HOPLAND 37/1 RPR STRW | ICW
LC | 120911283 | 049/000 | T2 EI HMBLDT-TRNTY-WD 49/0R RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-04-30 | 2021-04-30 | 2022-05-30 | 2022-04-30 | 2022-04-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31581077 | T2 EI HMBLDT-TRNTY 099/003B RPL POLE | 70Y
LC | 120911287 | 049/000 | T2 EI HMBLDT-TRNTY-WD 49/0C RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-04-30 | 2021-04-30 | 2022-05-31 | 2022-04-30 | 2022-04-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31581077 | T2 EI HMBLDT-TRNTY 099/003B RPL POLE | 70Y
LC | 120911294 | 049/000 | T2 EI HMBLDT-TRNTY-WD 49/0L RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-04-30 | 2021-04-30 | 2022-05-30 | 2022-04-30 | 2022-04-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31581077 | T2 EI HMBLDT-TRNTY 099/003B RPL POLE | 70Y
LC | 120911389 | 007/040 | DI T2 PARKWAY-MORAGA 7/40 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-11 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877476 | DI T2 PARKWAY-MORAGA 7/40 RPL SHLS | ICS
LC | 120911397 | 007/039 | DI T2 PARKWAY-MORAGA 7/39 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-11 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877474 | DI T2 PARKWAY-MORAGA 7/39 RPL SHLS | ICS
LC | 120911410 | 007/041 | EI T2 PARKWAY-MORAGA 7/41 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-11 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877475 | EI T2 PARKWAY-MORAGA 7/41 RPL SHLS | ICS
LC | 120911414 | 007/043 | DI T2 PARKWAY-MORAGA 7/43 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-11 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877473 | DI T2 PARKWAY-MORAGA 7/43 RPL SHLS | ICS
LC | 120911416 | 007/045 | DI T2 PARKWAY-MORAGA 7/45 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-11 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877472 | DI T2 PARKWAY-MORAGA 7/45 RPL SHLS | ICS
LC | 120911430 | 007/042 | DI T2 PARKWAY-MORAGA 7/42 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-11 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877471 | DI T2 PARKWAY-MORAGA 7/42 RPL SHLS | ICS
LC | 120911437 | 007/044 | DI T2 PARKWAY-MORAGA 7/44 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-11 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877470 | DI T2 PARKWAY-MORAGA 7/44 RPL SHLS | ICS
LC | 120911438 | 008/046 | DI T2 PARKWAY-MORAGA 8/46 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-11 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877469 | DI T2 PARKWAY-MORAGA 8/46 RPL SHLS | ICS
LC | 120911439 | 008/047 | DI T2 PARKWAY-MORAGA 8/47 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-11 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877468 | DI T2 PARKWAY-MORAGA 8/47 RPL SHLS | ICS
LC | 120911441 | 008/048 | DI T2 PARKWAY-MORAGA 8/48 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-11 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877467 | DI T2 PARKWAY-MORAGA 8/48 RPL SHLS | ICS
LC | 120911445 | 009/052 | T2 DI PARKWAY-MORAGA 9/52 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877465 | T2 DI PARKWAY-MORAGA 9/52 RPL SHLS | ICS
LC | 120911450 | 008/049 | DI T2 PARKWAY-MORAGA 8/49 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-06 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877464 | DI T2 PARKWAY-MORAGA 8/49 RPL SHLS | ICS
LC | 120911527 | 009/057 | T2 DI PARKWAY-MORAGA 9/57 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-10-18 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877462 | T2 DI PARKWAY-MORAGA 9/57 RPL SHLS | ICS
LC | 120911529 | 010/059 | T2 DI PARKWAY-MORAGA 10/59 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877461 | T2 DI PARKWAY-MORAGA 10/59 RPL SHLS | ICS
LC | 120911544 | 009/054 | T2 DI PARKWAY-MORAGA 9/54 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877459 | T2 DI PARKWAY-MORAGA 9/54 RPL SHLS | ICS
LC | 120911549 | 009/058 | T2 DI PARKWAY-MORAGA 9/58 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-10-18 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877456 | T2 DI PARKWAY-MORAGA 9/58 RPL SHLS | ICS
LC | 120911560 | 010/060 | T2 DI PARKWAY-MORAGA 10/60 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877455 | T2 DI PARKWAY-MORAGA 10/60 RPL SHLS | ICS
LC | 120911572 | 010/061 | T2 EI PARKWAY-MORAGA 10/61 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877454 | T2 EI PARKWAY-MORAGA 10/61 RPL SHLS | ICS
LC | 120911596 | 010/062 | T2 DI PARKWAY-MORAGA 10/62 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877453 | T2 DI PARKWAY-MORAGA 10/62 RPL SHLS | ICS
LC | 120911597 | 010/063 | T2 DI PARKWAY-MORAGA 10/63 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877452 | T2 DI PARKWAY-MORAGA 10/63 RPL SHLS | ICS
LC | 120911598 | 011/064 | T2 DI PARKWAY-MORAGA 11/64 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877451 | T2 DI PARKWAY-MORAGA 11/64 RPL SHLS | ICS
LC | 120911599 | 011/065 | T2 DI PARKWAY-MORAGA 11/65 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877450 | T2 DI PARKWAY-MORAGA 11/65 RPL SHLS | ICS
LC | 120911600 | 011/066 | T2 DI PARKWAY-MORAGA 11/66 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877449 | T2 DI PARKWAY-MORAGA 11/66 RPL SHLS | ICS
LC | 120911603 | 011/068 | T2 DI PARKWAY-MORAGA 11/68 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877448 | T2 DI PARKWAY-MORAGA 11/68 RPL SHLS | ICS
LC | 120911604 | 012/070 | T2 DI PARKWAY-MORAGA 12/70 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877447 | T2 DI PARKWAY-MORAGA 12/70 RPL SHLS | ICS
LC | 120911605 | 012/071 | T2 DI PARKWAY-MORAGA 12/71 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877446 | T2 DI PARKWAY-MORAGA 12/71 RPL SHLS | ICS
LC | 120911606 | 012/073 | T2 DI PARKWAY-MORAGA 12/73 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877445 | T2 DI PARKWAY-MORAGA 12/73 RPL SHLS | ICS
LC | 120911625 | 011/067 | T2 DI PARKWAY-MORAGA 11/67 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877444 | T2 DI PARKWAY-MORAGA 11/67 RPL SHLS | ICS
LC | 120911640 | 011/069 | T2 DI PARKWAY-MORAGA 11/69 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877443 | T2 DI PARKWAY-MORAGA 11/69 RPL SHLS | ICS
LC | 120911641 | 012/072 | T2 DI PARKWAY-MORAGA 12/72 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-10 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877442 | T2 DI PARKWAY-MORAGA 12/72 RPL SHLS | ICS
LC | 120911646 | 012/074 | T2 DI PARKWAY-MORAGA 12/74 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-09 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877441 | T2 DI PARKWAY-MORAGA 12/74 RPL SHLS | ICS
LC | 120911647 | 012/075 | T2 DI PARKWAY-MORAGA 12/75 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-04-30 | 2021-04-30 | 2021-12-09 | 2022-04-30 | 2022-04-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877439 | T2 DI PARKWAY-MORAGA 12/75 RPL SHLS | ICS
LC | 120912124 | 026/164 | T2 EI HELMS-GREGG #1 26/164 COMPLETE | FRESNO | ETL.4870.TOWR | 2021-05-01 | 2021-05-01 | 2022-05-19 | 2022-05-01 | 2022-05-01 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45069362 | T2NT EI HELMS-GREGG #1 26/164 RPR FOND | ICQ
LC | 120912165 | :005/032 | T2 EI STSLS-MLN SS-MNT :005/032 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-05-01 | 2021-05-01 | 2022-02-16 | 2022-05-01 | 2022-05-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45107280 | T2 EI STSLS-MLN SS-MNT :005/032 RPR FOND | ICQ
LC | 120912388 | 035/009 | T2 EI FULTON-HOPLAND 35/9 GYWW CMPLTD | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-01 | 2021-05-01 | 2022-05-12 | 2022-05-01 | 2022-05-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45143989 | T2 EI FULTON-HOPLAND 35/9 RPR GYWW | ICW
LC | 120912454 | :003/019 | T2 EI STNSLS-MLN SS-MN :003/019 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-05-01 | 2021-05-01 | 2022-02-16 | 2022-05-01 | 2022-05-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45107272 | T2 EI STNSLS-MLN SS-MN :003/019 RPR FOND | ICQ
LC | 120912520 | 000/009 | T2 EI PIT #3-PIT #1 0/9 RPR FOND | TABLEMTN | ETL.5400.TOWR | 2021-05-01 | 2021-05-01 | 2022-08-03 | 2022-05-01 | 2022-05-01 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195441 | T2 EI PIT #3-PIT #1 0/9 RPR FOND | ICQ
LC | 120912562 | :003/018 | T2 EI STNSLS-MLN SS-MN :003/018 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-05-01 | 2021-05-01 | 2022-02-16 | 2022-05-01 | 2022-05-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45107270 | T2 EI STNSLS-MLN SS-MN :003/018 RPR FOND | ICQ
LC | 120912607 | 016/001 | T2 EI FLTN-HPLND 16/1 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-01 | 2021-05-01 | 2022-03-29 | 2022-05-01 | 2022-05-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143930 | T2 EI FLTN-HPLND 16/1 RPR STRW | ICW
LC | 120912725 | 011/130A | T2 EI DRM-SUMT#2 11/130A RPR GYWW CMPLT | SACTO | ETL.1450.POLE.NWOD | 2021-05-01 | 2021-05-01 | 2022-05-09 | 2022-05-01 | 2022-05-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44812246 | EI DRUM-SUMMIT#2_011/130 RPR GYWW | ICW
LC | 120912811 | :003/022 | T2 EI STNSLS-MLN SS-MN :003/022 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-05-01 | 2021-05-01 | 2022-02-16 | 2022-05-01 | 2022-05-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45107273 | T2 EI STNSLS-MLN SS-MN :003/022 RPR FOND | ICQ
LC | 120912812 | :003/022 | T2 EI STNSLS-MLNS SS-MN :003/022 RMV VEG | VICTOR | ETL.3830.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-15 | 2022-05-01 | 2022-05-01 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120912814 | 009/207 | T2 EI HMLTN BRNCH-CHSTR 9/207 RPR GYWW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-01 | 2021-05-01 | 2022-07-28 | 2022-05-01 | 2022-05-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213332 | T2 EI HMLTN BRNCH-CHSTR 9/207 RPR GYWW | ICW
LC | 120912829 | :003/022 | T2 EI STNSLS-MLN SS-MN :003/022 RPL INSS | VICTOR | ETL.3830.INSL.NCER | 2021-05-01 | 2021-05-01 | 2022-09-20 | 2022-05-01 | 2022-05-01 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31608636 | T2 EI STNSLS-MLN SS-MN :003/022 RPL INSS | 93K
LC | 120912909 | :004/023 | T2 EI STNSLS-MLN SS-MN :004/023 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-05-01 | 2021-05-01 | 2022-02-16 | 2022-05-01 | 2022-05-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45107274 | T2 EI STNSLS-MLN SS-MN :004/023 RPR FOND | ICQ
LC | 120912976 | 009/206 | T2 EI HMLTN BRNCH-CHSTR 9/206 RPR GYWW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-01 | 2021-05-01 | 2022-07-28 | 2022-05-01 | 2022-05-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213333 | T2 EI HMLTN BRNCH-CHSTR 9/206 RPR GYWW | ICW
LC | 120913039 | :004/024 | T2 EI STNSLS-MLN SS-MN :004/024 RPL INSS | VICTOR | ETL.3830.INSL.NCER | 2021-05-01 | 2021-05-01 | 2021-12-18 | 2022-05-01 | 2022-05-01 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528967 | NN STANISLAUS-MLNS-MNTC RPLC INSS 11TWR | 93K
LC | 120913193 | 011/130C | T2 EI DRM-SUMIT#2 11/133C RPR GYWW CMPLT | SACTO | ETL.1450.POLE.NWOD | 2021-05-01 | 2021-05-01 | 2022-05-04 | 2022-05-01 | 2022-05-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44812245 | EI DRUM-SUMMIT#2_011/133 RPR GYWW | ICW
LC | 120913195 | :004/025 | T2 EI STSLS-MLS SS-MNT :004/025 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-05-01 | 2021-05-01 | 2022-02-16 | 2022-05-01 | 2022-05-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45107276 | T2 EI STSLS-MLS SS-MNT :004/025 RPR FOND | ICQ
LC | 120913207 | 009/205 | T2 EI HMLTN BRNCH-CHSTR 9/205 RPR SPLW | TABLEMTN | ETL.7000.INSL.NCER | 2021-05-01 | 2021-05-01 | 2022-07-28 | 2022-05-01 | 2022-05-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Splice-Wood | Repair | 45147441 | T2 EI HMLTN BRNCH-CHSTR 9/205 RPR SPLW | ICW
LC | 120913254 | :004/026 | T2 EI STSLS-MLN SS-MNT :004/026 RPL INSS | VICTOR | ETL.3830.INSL.NCER | 2021-05-01 | 2021-05-01 | 2022-09-20 | 2022-05-01 | 2022-05-01 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528967 | NN STANISLAUS-MLNS-MNTC RPLC INSS 11TWR | 93K
LC | 120913389 | 009/204 | T2 EI HMLTN BRNCH-CHSTR 9/204 RPR GYWW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-01 | 2021-05-01 | 2022-07-28 | 2022-05-01 | 2022-05-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213334 | T2 EI HMLTN BRNCH-CHSTR 9/204 RPR GYWW | ICW
LC | 120913482 | :004/028 | T2 EI SNSLS-MLN SS-MNT :004/028 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-05-01 | 2021-05-01 | 2022-02-16 | 2022-05-01 | 2022-05-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45107277 | T2 EI SNSLS-MLN SS-MNT :004/028 RPR FOND | ICQ
LC | 120913496 | C021/084 | T2 DI MSS LNDNG-CBRN C021/084 RMV NEST | MOSSLNDG | ETL.5330.TOWR | 2021-05-01 | 2021-04-15 | 2021-10-13 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44981666 | T2 DI MSS LNDNG-CBRN C021/084 RMV NEST | ICS
LC | 120913546 | :005/029 | T2 EI STSLS-MLN SS-MNT :005/029 RPL INSS | VICTOR | ETL.3830.INSL | 2021-05-01 | 2021-05-01 | 2022-09-20 | 2022-05-01 | 2022-05-01 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528967 | NN STANISLAUS-MLNS-MNTC RPLC INSS 11TWR | 93K
LC | 120913595 | 000/002 | T2 EI PIT #3-PIT #1 0/2 RPR FOND | TABLEMTN | ETL.5400.TOWR | 2021-05-01 | 2021-05-01 | 2022-07-28 | 2022-05-01 | 2022-05-01 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45194341 | T2 EI PIT #3-PIT #1 0/2 RPR FOND | ICQ
LC | 120913686 | :005/030 | T2 EI STSLS-ML SW STA-RVR :5/30 COMPLETE | VICTOR | ETL.3840.INSL.NCER | 2021-05-01 | 2021-05-01 | 2022-05-17 | 2022-05-01 | 2022-05-01 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551875 | T2 DI STN ML SW ST-RBK JT RPL INSS 7TWR | 93K
LC | 120913687 | :005/030 | T2 EI SNSLS-MLN SS-MNT :005/030 RPL INSS | VICTOR | ETL.3830.INSL.NCER | 2021-05-01 | 2021-05-01 | 2021-12-18 | 2022-05-01 | 2022-05-01 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528967 | NN STANISLAUS-MLNS-MNTC RPLC INSS 11TWR | 93K
LC | 120913824 | 065/000 | T2 EI HUMBOLDT-TRINITY 65/0 RPR FOND | EUREKA | ETL.1820.POLE.STPS | 2021-05-01 | 2021-05-01 | 2022-11-02 | 2022-05-01 | 2022-05-01 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45193980 | T2 EI HUMBOLDT-TRINITY 65/0 RPR FOND | ICQ
LC | 120913828 | 064/006 | T2 EI HUMBOLDT-TRINITY 64/6 RMV VEG | EUREKA | ETL.1820.POLE.STPS | 2021-05-01 | 2021-05-01 | 2022-08-10 | 2022-05-01 | 2022-05-01 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO SR22 | Overgrown | Vegetation | Remove
LC | 120913948 | 000/000A | T2 EI PIT #3-PIT #1 0/0A RPL GWRS | TABLEMTN | ETL.5400.POLE.NWOD | 2021-05-01 | 2021-05-01 | 2022-06-18 | 2022-05-01 | 2022-05-01 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Replace | 45213904 | T2 EI PIT #3-PIT #1 0/0A RPL GWRS | ICS
LC | 120914444 | 036/016 | T2 EI FULTON-HPLND 36/16 RPR STRW CMPLTD | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-01 | 2021-04-30 | 2022-05-13 | 2022-04-30 | 2022-04-30 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143995 | T2 EI FULTON-HOPLAND 36/16 RPR STRW | ICW
LC | 120914452 | 019/001 | T2 EI MNDCNO-WLLTS-FRT BRG 19/1 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-01 | 2021-05-01 | 2022-10-05 | 2022-05-01 | 2022-05-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31537422 | T2 EI MNDCNO-WLTS-FRT BRGG 15/5 REPL PL | 70Y
LC | 120914524 | 036/000 | T2 EI FULTON-HOPLAND 36/0 GYWW CMPLTD | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-01 | 2021-05-01 | 2022-05-12 | 2022-05-01 | 2022-05-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45143990 | T2 EI FULTON-HOPLAND 36/0 RPR GYWW | ICW
LC | 120914525 | 036/000 | T2 EI FULTON-HPLND 36/0 RPR STRW CMPLTD | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-01 | 2021-05-01 | 2022-05-12 | 2022-05-01 | 2022-05-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143990 | T2 EI FULTON-HOPLAND 36/0 RPR GYWW | ICW
LC | 120914576 | 013/079 | T2 DI PARKWAY-MORAGA 13/79 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-09 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877440 | T2 DI PARKWAY-MORAGA 13/79 RPL SHLS | ICS
LC | 120914580 | 013/077 | T2 DI PARKWAY-MORAGA 13/77 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-09 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877438 | T2 DI PARKWAY-MORAGA 13/77 RPL SHLS | ICS
LC | 120914583 | 013/078 | T2 DI PARKWAY-MORAGA 13/78 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-09 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877437 | T2 DI PARKWAY-MORAGA 13/78 RPL SHLS | ICS
LC | 120914595 | 013/080 | T2 DI PARKWAY-MORAGA 13/80 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-09 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877436 | T2 DI PARKWAY-MORAGA 13/80 RPL SHLS | ICS
LC | 120914602 | 013/081 | T2 DI PARKWAY-MORAGA 13/81 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-03 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877435 | T2 DI PARKWAY-MORAGA 13/81 RPL SHLS | ICS
LC | 120914605 | 014/082 | T2 DI PARKWAY-MORAGA 14/82 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-09 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877434 | T2 DI PARKWAY-MORAGA 14/82 RPL SHLS | ICS
LC | 120914606 | 014/084 | T2 DI PARKWAY-MORAGA 14/84 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-09 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877433 | T2 DI PARKWAY-MORAGA 14/84 RPL SHLS | ICS
LC | 120914608 | 014/085 | T2 DI PARKWAY-MORAGA 14/85 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-09 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877432 | T2 DI PARKWAY-MORAGA 14/85 RPL SHLS | ICS
LC | 120914609 | 014/086 | T2 DI PARKWAY-MORAGA 14/86 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-09 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877431 | T2 DI PARKWAY-MORAGA 14/86 RPL SHLS | ICS
LC | 120914611 | 022/005 | T2 EI MNDCN-WLTS-FRT BRG 22/5 RPR POLE | LAKEVLLE | ETL.7550.POLE.WOOD | 2021-05-01 | 2021-05-01 | 2021-08-27 | 2022-05-01 | 2022-05-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44907139 | T2 EI MNDCN-WLTS-FRT BRG 22/5 RPR POLE | ICW
LC | 120914612 | 022/003 | T2 EI MNDCN-WLTS-FRT BRG 22/3 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-01 | 2021-05-01 | 2022-08-19 | 2022-05-01 | 2022-05-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31547473 | T2 EI MNDCN-WLTS-FRT BRG 23/6R RPL POLE | 70Y
LC | 120914613 | 021/007 | T2 EI MNDCN-WLTS-FRT BRG 21/7 RPR POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-05-01 | 2021-05-01 | 2022-08-20 | 2022-05-01 | 2022-05-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45145836 | T2 EI MNDCN-WLTS-FRT BRG 21/7 RPR POLE | ICW
LC | 120914616 | 014/083 | T2 DI PARKWAY-MORAGA 14/83 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-09 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877430 | T2 DI PARKWAY-MORAGA 14/83 RPL SHLS | ICS
LC | 120914630 | 014/087 | T2 DI PARKWAY-MORAGA 14/87 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-09 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877429 | T2 DI PARKWAY-MORAGA 14/87 RPL SHLS | ICS
LC | 120914636 | 015/088 | T2 DI PARKWAY-MORAGA 15/88 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-08 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877428 | T2 DI PARKWAY-MORAGA 15/88 RPL SHLS | ICS
LC | 120914653 | 015/091 | T2 DI PARKWAY-MORAGA 15/91 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-08 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877427 | T2 DI PARKWAY-MORAGA 15/91 RPL SHLS | ICS
LC | 120914654 | 015/092 | T2 DI PARKWAY-MORAGA 15/92 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-08 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877426 | T2 DI PARKWAY-MORAGA 15/92 RPL SHLS | ICS
LC | 120914656 | 016/096 | T2 EI PARKWAY-MORAGA 16/096 RPL SHLS | LAKEVLLE | ETL.5930.INSL.CERA | 2021-05-01 | 2021-05-01 | 2021-12-07 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877425 | T2 PARKWAY-MORAGA 16/096 RPL SHLS | ICS
LC | 120914662 | 015/089 | T2 DI PARKWAY-MORAGA 15/89 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-08 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877424 | T2 DI PARKWAY-MORAGA 15/89 RPL SHLS | ICS
LC | 120914664 | 015/090 | T2 DI PARKWAY-MORAGA 15/90 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-08 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877423 | T2 DI PARKWAY-MORAGA 15/90 RPL SHLS | ICS
LC | 120914682 | 016/094 | T2 EI PARKWAY-MORAGA 16/094 RPL SHLS | LAKEVLLE | ETL.5930.INSL | 2021-05-01 | 2021-05-01 | 2021-12-07 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877422 | T2 PARKWAY-MORAGA 16/094 RPL SHLS | ICS
LC | 120914684 | 019/111 | T2 EI BAHIA-MORAGA 19/111 RPL SHLS | LAKEVLLE | ETL.4340.INSL | 2021-05-01 | 2021-05-01 | 2021-12-07 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877421 | T2 BAHIA-MORAGA 16/095 RPL SHLS | ICS
LC | 120914688 | 017/097 | T2 PARKWAY-MORAGA 17/097 RPL SHLS | LAKEVLLE | ETL.5930.INSL | 2021-05-01 | 2021-05-01 | 2021-12-07 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877420 | T2 PARKWAY-MORAGA 17/097 RPL SHLS | ICS
LC | 120914735 | 012/071 | T2 BAHIA-MORAGA 12/71 RPL SHIELD | LAKEVLLE | ETL.4340.TOWR | 2021-05-01 | 2021-05-01 | 2021-12-09 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877418 | T2 BAHIA-MORAGA 12/71 RPL SHIELD | ICS
LC | 120914878 | 009/057A | EI T2 LONE TREE-CAYETANO 9/057A WASH | CONCORD | ETL.6160.INSL.NCER | 2021-05-01 | 2021-05-01 | 2021-11-02 | 2022-05-01 | 2022-05-01 | On-time | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Contaminated | Insulator | Ground Wash | 44959025 | EI T2 LONE TREE-CAYETANO 9/057A WASH | ICD
LC | 120914998 | 005/003 | T2 EI CHOWCHILLA-KERCKHOFF 5/3 RPR GYWW | FRESNO | ETL.1250.POLE.NWOD | 2021-05-01 | 2021-05-01 | 2022-02-15 | 2022-05-01 | 2022-05-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069000 | T2 EI CHOWCHILLA-KERCKHOFF 5/3 RPR GYWW | ICW
LC | 120914999 | 005/004 | EI T2 CHWCHLLA-KRCKHFF 5/4 RPR GYWW | FRESNO | ETL.1250.POLE.NWOD | 2021-05-01 | 2021-05-01 | 2022-02-18 | 2022-05-01 | 2022-05-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069001 | EI T2 CHWCHLLA-KRCKHFF 5/4 RPR GYWW | ICW
LC | 120919853 | 005/025 | T2 DI MORRO BAY-MESA 5/25 RPLC INSS | PISMOBCH | ETL.5290.INSL | 2021-05-03 | 2021-04-29 | 2022-06-21 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534504 | T2 EI MORRO BAY-MESA RPL INSLS 5TWRS | 93K
LC | 120919854 | 005/025 | T2 DI DIABLO-MESA 5/25 RPLC INSS | PISMOBCH | ETL.4620.INSL.NCER | 2021-05-03 | 2021-04-29 | 2022-07-09 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534103 | T2 DI DIABLO-MESA 18/79 RPLC INSS 6TWRS | 93K
LC | 120920126 | 015/015 | PATR T2 LWER LKE-HMESTKE 15/15 RPR GYWW | LAKEVLLE | ETL.1481.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2021-08-13 | 2022-05-03 | 2022-05-03 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44947981 | PATR T2 LWER LKE-HMESTKE 15/15 RPR GYWW | ICW
LC | 120920219 | 001/008 | T2 EI STN MEL S S-RVERBNK 1/8 RPR SPLS | VICTOR | ETL.3840.INSL.NCER | 2021-05-03 | 2021-05-03 | 2022-05-11 | 2022-05-03 | 2022-05-03 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122131 | T2 EI STN MEL S S-RVERBNK 1/8 RPR SPLS | ICS
LC | 120920224 | 001/008 | T2 EI STNISLS-MANTECA #2 1/8 RPR SPLS | VICTOR | ETL.3820.INSL.NCER | 2021-05-03 | 2021-05-03 | 2021-12-09 | 2022-05-03 | 2022-05-03 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Repair | 44977851 | T2 EI STNISLS-MANTECA #2 1/8 RPR SPLS | ICS
LC | 120920328 | 001/007 | T2 EI STNISLAUS-MANTECA #2 1/7 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-05-03 | 2021-05-03 | 2022-01-11 | 2022-05-03 | 2022-05-03 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45119056 | T2 EI STNISLAUS-MANTECA #2 1/7 RPR FOND | ICQ
LC | 120920540 | 014/361 | T2 EI CTTNWD-BNTN #1 14/361 RPL STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2021-07-21 | 2022-05-03 | 2022-05-03 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31541808 | T2 DI CTTNWD-BENTN #1 002/062 RPL STRW | 70Y
LC | 120921006 | 002/070 | T2 EI HMLTN BRNCH-CHSTR 2/70 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2022-07-23 | 2022-05-03 | 2022-05-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213335 | T2 EI HMLTN BRNCH-CHSTR 2/70 RPR STRW | ICW
LC | 120921156 | 002/072 | T2 EI HMLTN BRNCH-CHSTR 2/72 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2022-07-22 | 2022-05-03 | 2022-05-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213336 | T2 EI HMLTN BRNCH-CHSTR 2/72 RPR STRW | ICW
LC | 120921312 | 001/011 | T2 EI STNISLS-MLONS SS-MNT1/11 REPLUMB | VICTOR | ETL.3830.TOWR | 2021-05-03 | 2021-05-03 | 2022-03-01 | 2022-05-03 | 2022-05-03 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Repair | 44977953 | T2 EI STNISLS-MLONS SS-MNT1/11 REPLUMB | ICS
LC | 120921485 | 001/012 | T2 EI STNISLS-MLNS SS-MNT 1/12 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-05-03 | 2021-05-03 | 2022-01-27 | 2022-05-03 | 2022-05-03 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45119049 | T2 EI STNISLS-MLNS SS-MNT 1/12 RPR FOND | ICQ
LC | 120921580 | 023/157 | T2 DI POE-RIO OSO 23/157 RPR INSS | TABLEMTN | ETL.5540.INSL.CERA | 2021-05-03 | 2021-04-15 | 2022-08-02 | 2022-04-15 | 2022-04-15 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213418 | T2 DI POE-RIO OSO 23/157 RPR INSS | ICS
LC | 120921581 | 007/057 | T2 DI ELDORADO-MSR FLT #2 7/57 RPLC INSS | SACTO | ETL.1540.INSL | 2021-05-03 | 2021-04-14 | 2022-05-19 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547631 | T2 WV EL DORADO-MSR FLT #2 RPL INSS 10TW | 93K
LC | 120921583 | 007/057 | T2 DI ELDORADO-MSR FLT #1 7/57 RPLC INSS | SACTO | ETL.1530.INSL | 2021-05-03 | 2021-04-14 | 2022-06-14 | 2022-04-14 | 2022-04-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535732 | T2 DI ELDRD-MSSRI FLT #1 RPL INSS 10TWRS | 93K
LC | 120921838 | 004/009 | T2 EI CHOWCHILLA-KERCKHOFF 4/9 RMV VEG | FRESNO | ETL.1250.POLE.NWOD | 2021-05-03 | 2021-05-03 | 2022-04-18 | 2022-05-03 | 2022-05-03 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Trim
LC | 120921872 | 004/008B | T2 EI CHOWCHILLA-KERCKHOFF 4/8B RPR GYWW | FRESNO | ETL.1250.POLE.NWOD | 2021-05-03 | 2021-05-03 | 2022-02-14 | 2022-05-03 | 2022-05-03 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069011 | T2 EI CHOWCHILLA-KERCKHOFF 4/8B RPR GYWW | ICW
LC | 120921873 | 004/007 | T2 EI CHOWCHILLA-KERCKHOFF 4/7 RPL INSW | FRESNO | ETL.1250.POLE.NWOD | 2021-05-03 | 2021-05-03 | 2022-02-15 | 2022-05-03 | 2022-05-03 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31539801 | T2 DI CHOWCHILLA-KERCKHOFF 4/1 RPLC INSW | 93I
LC | 120921882 | 037/213 | T2 EI TMBLR-SN LUIS OBSP 37/213 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-05-03 | 2021-04-30 | 2022-04-24 | 2022-04-30 | 2022-04-30 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546833 | T2 EI TMBLR-SN LUIS OBSP RPL INSS 7TWRS | 93K
LC | 120921883 | 037/217 | T2 EI TMBLR-SN LUIS OBSP 37/217 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-05-03 | 2021-04-30 | 2022-04-24 | 2022-04-30 | 2022-04-30 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546833 | T2 EI TMBLR-SN LUIS OBSP RPL INSS 7TWRS | 93K
LC | 120921946 | 002/013 | T2 EI STAISLS-MLONS SS-MNT2/13 RMV VEG | VICTOR | ETL.3830.TOWR | 2021-05-03 | 2021-05-03 | 2021-12-16 | 2022-05-03 | 2022-05-03 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120922193 | 002/080 | T2 EI HMLTN BRNCH-CHSTR 2/80 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2022-07-22 | 2022-05-03 | 2022-05-03 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31539905 | T2 EI HMLTN BRNCH-CHSTR 0/25 RPL STRW | 70Y
LC | 120922304 | 004/005 | T2 EI CHOWCHILLA-KERCKHOFF 4/5 RMV VEG | FRESNO | ETL.1250.POLE.NWOD | 2021-05-03 | 2021-05-03 | 2021-11-02 | 2022-05-03 | 2022-05-03 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Trim
LC | 120922375 | 008/189 | T2 EI HMLTN BRNCH-CHSTR 8/189 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2022-07-27 | 2022-05-03 | 2022-05-03 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544408 | T2 DI HAMLTN BRCH-CHESTR 8/181 RPL POLE | 70Y
LC | 120922436 | 008/188 | T2 EI HMLTN BRNCH-CHSTR 8/188 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2022-07-26 | 2022-05-03 | 2022-05-03 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544408 | T2 DI HAMLTN BRCH-CHESTR 8/181 RPL POLE | 70Y
LC | 120922496 | C003/015 | T2 DI MOSS LANDING-COBURN C3/15 INS HRDT | MOSSLNDG | ETL.5330.TOWR | 2021-05-03 | 2021-04-15 | 2022-05-18 | 2022-04-15 | 2022-04-15 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45121182 | T2 DI MOSS LANDING-COBURN C3/15 INS HRDT | ICQ
LC | 120922806 | 002/003 | T2 DI CHOWCHILLA-KERCKHOFF 2/3 RPL INSW | FRESNO | ETL.1250.INSL | 2021-05-03 | 2021-05-01 | 2022-02-14 | 2022-05-01 | 2022-05-01 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31536991 | T2 DI CHWCHLL-KERCKHOFF 001/008 RPL INSS | 93I
LC | 120922997 | 008/184 | T2 EI HMLTN BRNCH-CHSTR 8/184 RPR GYWW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2022-07-27 | 2022-05-03 | 2022-05-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213337 | T2 EI HMLTN BRNCH-CHSTR 8/184 RPR GYWW | ICW
LC | 120923259 | 034/200 | T2 EI TMBLR-SN LUIS OBSP 34/200 RPR ROAD | PISMOBCH | ETL.3960.TOWR | 2021-05-03 | 2021-05-03 | 2022-04-19 | 2022-05-03 | 2022-05-03 | On-time | 932 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Road | Repair | 45057235 | T2 EI TMBLR-SN LUIS OBSP 34/200 RPR ROAD | CHS
LC | 120923263 | 036/208 | T2 EI TMBLR-SN LUIS OBSP 36/208 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-05-03 | 2021-05-03 | 2022-04-23 | 2022-05-03 | 2022-05-03 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546833 | T2 EI TMBLR-SN LUIS OBSP RPL INSS 7TWRS | 93K
LC | 120923264 | 034/198 | T2 EI TMBLR-SN LUIS OBSP 34/198 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-05-03 | 2021-05-03 | 2022-04-20 | 2022-05-03 | 2022-05-03 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546832 | T2 DI TMBLR-SN LS OBSP RPLC INSS 7TWRS | 93K
LC | 120923265 | 035/202 | T2 EI TMBLR-SN LUIS OBSP 35/202 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-05-03 | 2021-05-03 | 2022-04-20 | 2022-05-03 | 2022-05-03 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546832 | T2 DI TMBLR-SN LS OBSP RPLC INSS 7TWRS | 93K
LC | 120923266 | 034/200 | T2 EI TMBLR-SN LUIS OBSP 34/200 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-05-03 | 2021-05-03 | 2022-04-20 | 2022-05-03 | 2022-05-03 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546832 | T2 DI TMBLR-SN LS OBSP RPLC INSS 7TWRS | 93K
LC | 120923273 | 017/526 | T2 EI SPAULDING-SUMMIT 17/526 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2022-08-05 | 2022-05-03 | 2022-05-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44812239 | T2 EI SPAULDING-SUMMIT 17/526 RPR GYWW | ICW
LC | 120923280 | 035/201 | T2 EI TMBLR-SN LUIS OBSP 35/201 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-05-03 | 2021-05-03 | 2022-04-20 | 2022-05-03 | 2022-05-03 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549402 | TEMBLOR–SN LS OBSP RPLC INSS 6TWRS | 93K
LC | 120923281 | 035/203 | T2 EI TMBLR-SN LUIS OBSP 35/203 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-05-03 | 2021-05-03 | 2022-04-20 | 2022-05-03 | 2022-05-03 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546832 | T2 DI TMBLR-SN LS OBSP RPLC INSS 7TWRS | 93K
LC | 120923282 | 034/199 | T2 EI TMBLR-SN LUIS OBSP 34/199 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-05-03 | 2021-05-03 | 2022-04-20 | 2022-05-03 | 2022-05-03 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546832 | T2 DI TMBLR-SN LS OBSP RPLC INSS 7TWRS | 93K
LC | 120923284 | 036/207 | T2 EI TMBLR-SN LUIS OBSP 36/207 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-05-03 | 2021-05-03 | 2022-04-24 | 2022-05-03 | 2022-05-03 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546833 | T2 EI TMBLR-SN LUIS OBSP RPL INSS 7TWRS | 93K
LC | 120923288 | 017/544 | T2 EI SPAULDING-SUMMIT 17/544 RPR STRW | SACTO | ETL.8060.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2021-08-26 | 2022-05-03 | 2022-05-03 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44812237 | T2 EI SPAULDING-SUMMIT 17/544 RPR STRW | ICW
LC | 120923574 | 002/015 | T2 EI STNISLAUS-MANTECA #2 2/15 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-05-03 | 2021-05-03 | 2022-01-12 | 2022-05-03 | 2022-05-03 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45119065 | T2 EI STNISLAUS-MANTECA #2 2/15 RPR FOND | ICQ
LC | 120924126 | 023/004 | T2 EI MNDCN-WLTS-FRT BRG 23/4 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2022-10-01 | 2022-05-03 | 2022-05-03 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31547473 | T2 EI MNDCN-WLTS-FRT BRG 23/6R RPL POLE | 70Y
LC | 120924135 | 023/007 | T2 EI MNDCINO-FRT BRGG 23/7 RPR STRW | WILLITS | ETL.7550.POLE.WDPS | 2021-05-03 | 2021-05-03 | 2022-05-25 | 2022-05-03 | 2022-05-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45148030 | T2 EI MNDCINO-FRT BRGG 23/7 RPR STRW | ICW
LC | 120924138 | 023/006 | T2 EI MNDCN-WLTS-FRT BRG 23/6R RPL POLE | WILLITS | ETL.7550.POLE.WDPS | 2021-05-03 | 2021-05-03 | 2022-09-30 | 2022-05-03 | 2022-05-03 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31547473 | T2 EI MNDCN-WLTS-FRT BRG 23/6R RPL POLE | 70Y
LC | 120924163 | 023/005 | T2 EI MNDCN-WLTS-FRT BRG 23/5 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2022-08-24 | 2022-05-03 | 2022-05-03 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31547473 | T2 EI MNDCN-WLTS-FRT BRG 23/6R RPL POLE | 70Y
LC | 120924165 | 003/086 | T2 EI HMLTN BRNCH-CHSTR 3/86 RPR GYWW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2022-07-22 | 2022-05-03 | 2022-05-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213338 | T2 EI HMLTN BRNCH-CHSTR 3/86 RPR GYWW | ICW
LC | 120924183 | 003/087 | T2 EI HMLTN BRNCH-CHSTR 3/87 RPR GYWW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2022-07-22 | 2022-05-03 | 2022-05-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213339 | T2 EI HMLTN BRNCH-CHSTR 3/87 RPR GYWW | ICW
LC | 120924220 | 022/000 | T2 EI MNDCN-WLTS-FRT BRG 22/0 RPL DAMW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2022-08-20 | 2022-05-03 | 2022-05-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE SR22 | No Good/Out of Stdrd | Damper-Wood | Replace | 45148028 | T2 EI MNDCN-WLTS-FRT BRG 22/0 RPL DAMW | ICW
LC | 120924221 | 022/000 | T2 EI MNDCN-WLTS-FRT BRG 22/0 RPR JUMW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2022-08-20 | 2022-05-03 | 2022-05-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45148028 | T2 EI MNDCN-WLTS-FRT BRG 22/0 RPL DAMW | ICW
LC | 120924255 | 034/007 | T2 EI FULTON-HOPLAND 34/007 COMPLETE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2022-05-12 | 2022-05-03 | 2022-05-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143979 | T2 EI FULTON-HOPLAND 34/007 RPR STRW | ICW
LC | 120924299 | 064/002 | T2 EI HUMBOLDT-TRINITY 64/2 RMV VEG | EUREKA | ETL.1820.POLE.WDPS | 2021-05-03 | 2021-05-03 | 2022-08-10 | 2022-05-03 | 2022-05-03 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO SR22 | Overgrown | Vegetation | Remove
LC | 120924329 | 064/001 | T2 EI HUMBOLDT-TRINITY 64/1 RMV VEG | EUREKA | ETL.1820.POLE.WDPS | 2021-05-03 | 2021-05-03 | 2022-08-25 | 2022-05-03 | 2022-05-03 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2N PRTO | Overgrown | Vegetation | Remove
LC | 120924345 | 064/005A | T2 EI HUMBOLDT-TRINITY 64/5 RMV VEG | EUREKA | ETL.1820.POLE.NWOD | 2021-05-03 | 2021-05-03 | 2022-08-10 | 2022-05-03 | 2022-05-03 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO SR22 | Overgrown | Vegetation | Remove
LC | 120924477 | 018/003 | T2 EI FULTON-HOPLAND 18/3 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-03 | 2021-05-03 | 2022-08-04 | 2022-05-03 | 2022-05-03 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31580905 | EI FULTON-HOPLAND 15/3 RPL POLE | 70Y
LC | 120927484 | 007/153 | T2 EI HMLTN BRNH-CHTR 7/153 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-04 | 2021-05-04 | 2022-07-26 | 2022-05-04 | 2022-05-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544408 | T2 DI HAMLTN BRCH-CHESTR 8/181 RPL POLE | 70Y
LC | 120927623 | 003/019 | T2 EI STNSLS-MLNS SS-MNT #1 3/19 RPR SPL | VICTOR | ETL.3830.POLE.NWOD | 2021-05-04 | 2021-05-04 | 2022-03-02 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 44977956 | T2 EI STNSLS-MLNS SS-MNT #1 3/19 RPR SPL | ICS
LC | 120927982 | 000/004 | EI T2 CHWCHLLA-KRCKHFF 0/4 RPL INSS | FRESNO | ETL.1250.INSL | 2021-05-04 | 2021-05-04 | 2022-02-12 | 2022-05-04 | 2022-05-04 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514611 | T2 DI CHOWCHILLA-KERCKHOFF RPL INSS 12TW | 93K
LC | 120928230 | 003/094 | T2 EI HMLTN BRNH-CHTR 3/94 RPR GYWW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-04 | 2021-05-04 | 2022-07-23 | 2022-05-04 | 2022-05-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213341 | T2 EI HMLTN BRNH-CHTR 3/94 RPR GYWW | ICW
LC | 120928299 | 003/095 | T2 EI HMLTN BRNH-CHTR 3/95 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-04 | 2021-05-04 | 2022-07-23 | 2022-05-04 | 2022-05-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31539905 | T2 EI HMLTN BRNCH-CHSTR 0/25 RPL STRW | 70Y
LC | 120928499 | 008/180 | T2 EI HMLTN BRNH-CHTR 8/180 RPR GYWW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-04 | 2021-05-04 | 2022-07-27 | 2022-05-04 | 2022-05-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213342 | T2 EI HMLTN BRNH-CHTR 8/180 RPR GYWW | ICW
LC | 120928523 | 003/021 | T2 EI STANISLAUS-MANTECA #2 3/2 RMV VEG | VICTOR | ETL.3820.TOWR | 2021-05-04 | 2021-05-04 | 2021-12-16 | 2022-05-04 | 2022-05-04 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120928524 | 003/021 | T2 EI STANISLAUS-MANTECA #2 3/2 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-05-04 | 2021-05-04 | 2022-01-18 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45119709 | T2 EI STANISLAUS-MANTECA #2 3/2 RPR FOND | ICQ
LC | 120928526 | 003/021 | T2 EI STNISLS-MLNS SS-RVR 3/21 RPR SPLS | VICTOR | ETL.3840.INSL.NCER | 2021-05-04 | 2021-05-04 | 2022-05-11 | 2022-05-04 | 2022-05-04 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122132 | T2 EI STNISLS-MLNS SS-RVR 3/21 RPR SPLS | ICS
LC | 120928571 | 003/022 | T2 EI STNISLS-MLNS SS-MNT#1 3/22 RMV VEG | VICTOR | ETL.3830.TOWR | 2021-05-04 | 2021-05-04 | 2021-12-16 | 2022-05-04 | 2022-05-04 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 120928632 | 017/100 | T2 PARKWAY-MORAGA 17/100 RPR SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-04 | 2021-05-04 | 2021-12-07 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44877415 | T2 PARKWAY-MORAGA 17/100 RPL SHLS | ICS
LC | 120928641 | 014/337 | T2 EI CTTNWD-BENTON #1 14/337 RMV VEG | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-04 | 2021-05-04 | 2022-08-10 | 2022-05-04 | 2022-05-04 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB SR22 | Overgrown | Vegetation | Remove
LC | 120928697 | 020/113 | T2 EI BAHIA-MORAGA 020/113 RPL SHLS | LAKEVLLE | ETL.4340.INSL | 2021-05-04 | 2021-05-04 | 2021-12-07 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877414 | T2 BAHIA-MORAGA 17/097 RPL SHLS | ICS
LC | 120928703 | 020/114 | T2 EI BAHIA-MORAGA 020/114 RMV SHLS | LAKEVLLE | ETL.4340.INSL | 2021-05-04 | 2021-05-04 | 2021-11-19 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877413 | T2 BAHIA-MORAGA 17/098 RPL SHLS | ICS
LC | 120928715 | 019/112 | T2 EI BAHIA-MORAGA 019/112 RPL SHLS | LAKEVLLE | ETL.4340.INSL | 2021-05-04 | 2021-05-04 | 2021-12-07 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877412 | T2 BAHIA-MORAGA 16/096 RPL SHLS | ICS
LC | 120928719 | 029/127 | T2 EI MRR BY-SLR SS#1 29/127 RPR FOND | PISMOBCH | ETL.5300.TOWR | 2021-05-04 | 2021-05-04 | 2022-06-24 | 2022-05-04 | 2022-05-04 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45073918 | T2 EI MRR BY-SLR SS#1 29/127 RPR FOND | ICQ
LC | 120928739 | 006/145 | T2 EI HMLTN BRNH-CHTR 6/145 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-04 | 2021-05-04 | 2022-07-25 | 2022-05-04 | 2022-05-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213343 | T2 EI HMLTN BRNH-CHTR 6/145 RPR STRW | ICW
LC | 120928745 | 016/095 | T2 EI PARKWAY-MORAGA 16/095 RMV SHLS | LAKEVLLE | ETL.5930.INSL | 2021-05-04 | 2021-05-04 | 2021-12-07 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877411 | T2 PARKWAY-MORAGA 16/095 RPL SHLS | ICS
LC | 120928826 | 019/110 | T2 EI BAHIA-MORAGA 19/110 RPL SHLS | LAKEVLLE | ETL.4340.INSL | 2021-05-04 | 2021-05-04 | 2021-12-07 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877410 | T2 BAHIA-MORAGA 19/110 RPL SHLS | ICS
LC | 120928849 | 016/093 | T2 PARKWAY-MORAGA 16/093 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-04 | 2021-05-04 | 2021-12-08 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH RTNR FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44877409 | T2 PARKWAY-MORAGA 16/093 RPL SHLS | ICS
LC | 120928855 | 030/128 | T2 EI MRR BY-SLAR SS#1 30/128 RPR FOND | PISMOBCH | ETL.5300.TOWR | 2021-05-04 | 2021-05-04 | 2022-07-25 | 2022-05-04 | 2022-05-04 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45073962 | T2 EI MRR BY-SLAR SS#1 30/128 RPR FOND | ICQ
LC | 120929006 | C002/011 | T2 DI CBN-LS AS SW ST-PCH C2/11 RPR INSS | MOSSLNDG | ETL.4460.INSL | 2021-05-04 | 2021-04-15 | 2021-09-25 | 2022-04-15 | 2022-04-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44961511 | T2 DI CBN-LS AS SW ST-PCH C2/11 RPR INSS | ICS
LC | 120929106 | 004/104 | T2 EI HMLTN BRNH-CHTR 4/104 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-04 | 2021-05-04 | 2022-07-24 | 2022-05-04 | 2022-05-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31540591 | T2 EI HMLTN BRNH-CHTR 4/104 RPL STRW | 70Y
LC | 120929600 | 001/006 | T2 EI STANISLAUS-MLNS MNTE 1/6 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-05-04 | 2021-05-04 | 2022-01-10 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45119055 | T2 EI STANISLAUS-MLNS MNTE 1/6 RPR FOND | ICQ
LC | 120929665 | 002/017 | T2 DI COTTONWOOD-DELVN #1 2/17 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-05-04 | 2021-05-04 | 2021-06-12 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44795136 | T2 DI COTTONWOOD-DELVN #1 2/17 RPR OPGW | ICS
LC | 120929783 | 005/033 | T2 DI COTTONWOOD-DELVN #1 5/33 RPR FOND | TABLEMTN | ETL.4550.TOWR | 2021-05-04 | 2021-05-04 | 2021-12-20 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45097425 | T2 DI COTTONWOOD-DELVN #1 5/33 RPR FOND | ICQ
LC | 120929806 | 006/135 | T2 EI HMLTN BRNH-CHTR 6/135 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-04 | 2021-05-04 | 2022-07-22 | 2022-05-04 | 2022-05-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31540591 | T2 EI HMLTN BRNH-CHTR 4/104 RPL STRW | 70Y
LC | 120930059 | 004/114 | T2 EI HMLTN BRNH-CHTR 4/114 RPR GYWW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-04 | 2021-05-04 | 2022-07-28 | 2022-05-04 | 2022-05-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213344 | T2 EI HMLTN BRNH-CHTR 4/114 RPR GYWW | ICW
LC | 120930221 | 001/001 | EI T2 CHWCHLLA-KRCKHFF 1/1 RPL INSS | FRESNO | ETL.1250.INSL.CERA | 2021-05-04 | 2021-05-04 | 2022-02-13 | 2022-05-04 | 2022-05-04 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514611 | T2 DI CHOWCHILLA-KERCKHOFF RPL INSS 12TW | 93K
LC | 120930260 | 031/134 | T2 EI MRR BY-SLAR SW S#1 31/1 RPR FOND | PISMOBCH | ETL.5300.TOWR | 2021-05-04 | 2021-05-04 | 2022-07-24 | 2022-05-04 | 2022-05-04 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45073964 | T2 EI MRR BY-SLAR SW S#1 31/1 RPR FOND | ICQ
LC | 120930611 | 045/218 | T2 DI IGNACIO-SOBRANTE 45/218 RPR INSS | LAKEVLLE | ETL.4920.INSL.CERA | 2021-05-04 | 2021-05-04 | 2022-03-16 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45142465 | T2 DI IGNACIO-SOBRANTE 45/218 RPR INSS | ICS
LC | 120930618 | 045/218 | T2 DI LAKVL-SOBRANTE#2 45/218 RPR INSS | CONCORD | ETL.4960.INSL | 2021-05-04 | 2021-05-04 | 2022-02-08 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45149313 | T2 DI LAKVL-SOBRANTE#2 45/218 RPR INSS | ICS
LC | 120930651 | 045/218 | T2 DI IGNACIO-SOBRANTE 45/218 RMV STEP | CONCORD | ETL.4920.TOWR | 2021-05-04 | 2021-05-04 | 2022-03-26 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45190693 | T2 DI IGNACIO-SOBRANTE 45/218 RMV STEP | ICQ
LC | 120930666 | 017/093 | T2 EI HAAS-MCCALL 17/093 FOND | FRESNO | ETL.4850.TOWR | 2021-05-04 | 2021-04-28 | 2022-03-23 | 2022-04-28 | 2022-04-28 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45069379 | T2 EI HAAS-MCCALL 17/093 FOND | ICQ
LC | 120930690 | 017/094 | T2 EI HAAS-MCCALL 17/094 RPR FOND | FRESNO | ETL.4850.TOWR | 2021-05-04 | 2021-04-28 | 2022-03-22 | 2022-04-28 | 2022-04-28 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45069460 | T2 EI HAAS-MCCALL 17/094 RPR FOND | ICQ
LC | 120930806 | 017/548 | T2 EI SPAULDING-SUMMIT 17/548 RPR STRW | SACTO | ETL.8060.POLE.WOOD | 2021-05-04 | 2021-05-04 | 2021-08-21 | 2022-05-04 | 2022-05-04 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44812233 | T2 EI SPAULDING-SUMMIT 17/548 RPR STRW | ICW
LC | 120930834 | 011/077 | T2 DI COTTONWD-LOGAN CRK 11/77 RPR CONS | TABLEMTN | ETL.4570.INSL | 2021-05-04 | 2021-05-04 | 2022-03-15 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45182637 | T2 DI COTTONWD-LOGAN CRK 11/77 RPR CONS | ICS
LC | 120931391 | 027/003 | T2 EI MDCNO-WLLTS-FRT BRG 27/3 GRND WASH | WILLITS | ETL.7550.POLE.WOOD | 2021-05-04 | 2021-05-04 | 2022-05-19 | 2022-05-04 | 2022-05-04 | Late | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Contaminated | Insulator | Ground Wash | 45193187 | T2 EI MDCNO-WLLTS-FRT BRG 27/3 GRND WASH | ICD
LC | 120931393 | 027/008 | T2 EI MNDCNO-WLLTS-FRT BRG 27/8 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-04 | 2021-05-04 | 2022-05-09 | 2022-05-04 | 2022-05-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148571 | T2 EI MNDCNO-WLLTS-FRT BRG 27/8 RPR GYWW | ICW
LC | 120931395 | 027/007 | T2 EI MNDCNO-WLLTS-FRT BRG 27/7 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-04 | 2021-05-04 | 2022-05-09 | 2022-05-04 | 2022-05-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45148570 | T2 EI MNDCNO-WLLTS-FRT BRG 27/7 RPR STRW | ICW
LC | 120931396 | 027/006 | T2 EI MDCNO-WLLTS-FRT BRG 27/6 GRND WASH | WILLITS | ETL.7550.POLE.WOOD | 2021-05-04 | 2021-05-04 | 2022-05-19 | 2022-05-04 | 2022-05-04 | Late | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Contaminated | Insulator | Ground Wash | 45193185 | T2 EI MDCNO-WLLTS-FRT BRG 27/6 GRND WASH | ICD
LC | 120931398 | 024/002 | T2 EI MNDCNO-WLLTS-FT BRG 24/2 GRND WASH | WILLITS | ETL.7550.POLE.WOOD | 2021-05-04 | 2021-05-04 | 2022-05-20 | 2022-05-04 | 2022-05-04 | Late | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Contaminated | Insulator | Ground Wash | 45193181 | T2 EI MNDCNO-WLLTS-FT BRG 24/2 GRND WASH | ICD
LC | 120931401 | 024/001 | T2 EI MNDCNO-WLLTS-FT BRG 24/1 GRND WASH | WILLITS | ETL.7550.INSL.CERA | 2021-05-04 | 2021-05-04 | 2022-05-20 | 2022-05-04 | 2022-05-04 | Late | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Contaminated | Insulator | Ground Wash | 45193184 | T2 EI MNDCNO-WLLTS-FT BRG 24/1 GRND WASH | ICD
LC | 120931713 | 023/006 | T2 EI MNDCN-WLTS-FRT BRG 23/6L RPL POLE | WILLITS | ETL.7550.POLE.WDPS | 2021-05-04 | 2021-05-03 | 2022-09-30 | 2022-05-03 | 2022-05-03 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31547473 | T2 EI MNDCN-WLTS-FRT BRG 23/6R RPL POLE | 70Y
LC | 120931767 | 066/001 | T2 EI HUMBOLDT-TRINITY 66/1R RPR ANCHW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-04 | 2021-05-04 | 2022-06-06 | 2022-05-04 | 2022-05-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 45145525 | T2 EI HUMBOLDT-TRINITY 66/1R RPR ANCHW | ICW
LC | 120931770 | 066/001 | T2 EI HUMBOLDT-TRINITY 66/001 RPR JMPW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-04 | 2021-05-04 | 2022-06-06 | 2022-05-04 | 2022-05-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Jumper-Wood | Repair | 44958544 | T2 EI HUMBOLDT-TRINITY 66/001 RPR JMPW | ICW
LC | 120931782 | 066/002 | T2 EI HUMBOLDT-TRINITY 66/002 RPR SPLW | EUREKA | ETL.1820.INSL.CERA | 2021-05-04 | 2021-05-04 | 2022-06-06 | 2022-05-04 | 2022-05-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45145527 | T2 EI HUMBOLDT-TRINITY 66/002 RPR SPLW | ICW
LC | 120931792 | 066/001 | T2 EI HUMBOLDT-TRINITY 66/1L RMV VEG | EUREKA | ETL.1820.POLE.WDPS | 2021-05-04 | 2021-05-04 | 2022-08-10 | 2022-05-04 | 2022-05-04 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO SR22 | Overgrown | Vegetation | Remove
LC | 120931799 | 066/001 | T2 EI HUMBOLDT-TRINITY 66/1C RPR ANCHW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-04 | 2021-05-04 | 2022-06-06 | 2022-05-04 | 2022-05-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 44958544 | T2 EI HUMBOLDT-TRINITY 66/001 RPR JMPW | ICW
LC | 120932542 | 015/144 | WV T2 BRDGVILL-CTTNWD 15/144 RPL HRDW | TABLEMTN | ETL.1110.POLE.WDPS | 2021-05-04 | 2021-05-04 | 2022-06-29 | 2022-05-04 | 2022-05-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45211797 | WV T2 BRDGVILL-CTTNWD 15/144 RPL HRDW | ICW
LC | 120932702 | 009/036 | T2 EI PITTSBURG-SN MTEO 9/036 RPR FOND | CONCORD | ETL.5463.TOWR | 2021-05-04 | 2021-05-04 | 2022-03-13 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45179329 | T2 EI PITTSBURG-SN MTEO 9/036 RPR FOND | ICQ
LC | 120932729 | 022/148 | T2 DI PO-RIO OSO-RIO OSO 22/148 RPL INSS | TABLEMTN | ETL.5540.INSL.CERA | 2021-05-04 | 2021-04-15 | 2021-06-12 | 2022-04-15 | 2022-04-15 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace
LC | 120932914 | 063/007 | T2 EI HUMBOLDT-TRINITY 063/007 RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2021-05-04 | 2021-05-03 | 2022-06-05 | 2022-05-03 | 2022-05-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 45145455 | T2 EI HUMBOLDT-TRINITY 063/007 RPR INSW | ICW
LC | 120932916 | 063/003 | T2 EI HUMBOLDT-TRINITY 063/3 RMV VEG | EUREKA | ETL.1820.POLE.WDPS | 2021-05-04 | 2021-05-03 | 2022-08-29 | 2022-05-03 | 2022-05-03 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO SR22 | Overgrown | Vegetation | Remove
LC | 120934494 | 011/010 | T2 EI FULTON-HOPLAND 11/10 RPR SPLW | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-05-05 | 2021-05-05 | 2022-08-25 | 2022-05-05 | 2022-05-05 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45143574 | T2NT DI FULTON-HOPLAND 011/010 RMV BUTT | ICW
LC | 120934510 | 160/1215 | T2 DI DELEVAN-VACA #2 160/1215 RPL INSS | SACTO | ETL.4231.INSL.CERA | 2021-05-05 | 2021-05-04 | 2022-04-05 | 2022-05-04 | 2022-05-04 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31530650 | DI DELEVAN-VACA #2 REPL INSS 10 TWRS | 93K
LC | 120934680 | 024/111 | T2 DI QNT SW ST-WSTLY 24/111 RPR OPGW | VICTOR | ETL.5070.TOWR | 2021-05-05 | 2021-05-04 | 2022-03-10 | 2022-05-04 | 2022-05-04 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45166650 | T2 DI QNT SW ST-WSTLY 24/111 RPR OPGW | ICW
LC | 120935155 | 024/161 | T2 DI POE-RIO OSO 24/161 RPL HRDT | TABLEMTN | ETL.5540.TOWR | 2021-05-05 | 2021-04-16 | 2022-05-25 | 2022-04-16 | 2022-04-16 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45198328 | T2 DI POE-RIO OSO 24/161 RPL HRDT | ICQ
LC | 120935306 | 004/116 | T2 EI HMLTN BRNCH-CHSTR 4/116 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-05 | 2021-05-05 | 2022-07-23 | 2022-05-05 | 2022-05-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31540591 | T2 EI HMLTN BRNH-CHTR 4/104 RPL STRW | 70Y
LC | 120935602 | 037/215 | T2 DI TEMBLOR-SAN LUIS 37/215 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-05-05 | 2021-04-15 | 2022-04-24 | 2022-04-15 | 2022-04-15 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546833 | T2 EI TMBLR-SN LUIS OBSP RPL INSS 7TWRS | 93K
LC | 120935788 | 019/006 | T2 EI FULTON-HOPLAND 019/006 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-05 | 2021-05-05 | 2022-05-12 | 2022-05-05 | 2022-05-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541677 | T2 EI FULTON-HOPLAND 019/006 RPL POLE | 70Y
LC | 120936095 | 005/121 | T2 EI HMLTN BRNCH-CHSTR-5/121 RPL ANCW | TABLEMTN | ETL.7000.POLE.WDPS | 2021-05-05 | 2021-05-05 | 2022-07-27 | 2022-05-05 | 2022-05-05 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31542054 | T2 EI HMLTN BRNCH-CHSTR-5/121 RPL ANCW | 93E
LC | 120936106 | 002/035 | T2 EI CLGATE-PALERMO 2/035 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2021-05-05 | 2021-05-05 | 2022-05-22 | 2022-05-05 | 2022-05-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44812230 | T2 EI CLGATE-PALERMO 2/035 RPR STRW | ICW
LC | 120936428 | 021/001 | T2 EI FULTON-HOPLAND 021/001 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-05 | 2021-05-05 | 2022-05-12 | 2022-05-05 | 2022-05-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541677 | T2 EI FULTON-HOPLAND 019/006 RPL POLE | 70Y
LC | 120936482 | 014/068 | T2 DI MS LDG-LS ALS SW ST 14/68 RPL INSS | MOSSLNDG | ETL.5340.INSL | 2021-05-05 | 2021-04-16 | 2022-04-12 | 2022-04-16 | 2022-04-16 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31539341 | T2 EI MSS LNDG-LS AGLS SW RPL INSS 6TWR | 93K
LC | 120936533 | 007/160 | T2 EI HAMILTON BRANCH-CH 07/160 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-05 | 2021-05-05 | 2022-07-26 | 2022-05-05 | 2022-05-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544408 | T2 DI HAMLTN BRCH-CHESTR 8/181 RPL POLE | 70Y
LC | 120936745 | 007/156 | T2 EI HAMILTON BRANCH-CH 07/156 RPR WDPK | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-05 | 2021-05-05 | 2022-07-26 | 2022-05-05 | 2022-05-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213345 | T2 EI HAMILTON BRANCH-CH 07/156 RPR WDPK | ICW
LC | 120937148 | 063/565 | T2 DI COTTNWOOD-DLVN #2 63/565 RMV STEP | TABLEMTN | ETL.4580.TOWR | 2021-05-05 | 2021-05-04 | 2021-06-15 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44875284 | T2 DI COTTNWOOD-DLVN #2 63/565 RMV STEP | ICQ
LC | 120938104 | 023/181 | T2 WV PARADISE-TABLE MTN 23/181 RPL INSW | TABLEMTN | ETL.4316.INSL.CERA | 2021-05-05 | 2021-05-05 | 2022-05-16 | 2022-05-05 | 2022-05-05 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31597163 | T2 WV PARADISE-TABLE MTN 23/181 RPL INSW | 93I
LC | 120938151 | 023/181 | T2 WV PARADISE-TABLE MTN 23/181 INS DAMS | TABLEMTN | ETL.4316.INSL.CERA | 2021-05-05 | 2021-05-05 | 2022-05-16 | 2022-05-05 | 2022-05-05 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install | 45197358 | T2 WV PARADISE-TABLE MTN 23/181 INS DAMS | ICS
LC | 120938255 | 001/021 | T2 EI COLGATE-PALERMO 1/021 INST ANMS | SACTO | ETL.6500.POLE.NWOD | 2021-05-05 | 2021-05-05 | 2022-05-22 | 2022-05-05 | 2022-05-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Missing | Animal Guard-Wood | Install | 45074240 | T2 EI COLGATE-PALERMO 1/021 INST ANMS | ICW
LC | 120938429 | 001/009 | T2 DI KRCKHFF-CLVS-SNGR #1 1/9 RPR STRT | FRESNO | ETL.1890.TOWR | 2021-05-05 | 2021-04-16 | 2022-02-10 | 2022-04-16 | 2022-04-16 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45069463 | T2 DI KRCKHFF-CLVS-SNGR #1 1/9 RPR STRT | ICQ
LC | 120938589 | 032/010 | T2 EI FULTON-HOPLAND 32/10 RPR SPLW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-05 | 2021-05-05 | 2022-06-22 | 2022-05-05 | 2022-05-05 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45143972 | T2 EI FULTON-HOPLAND 32/10 RPR SPLW | ICS
LC | 120938875 | 028/005 | T2 EI MNDCNO-WLLTS-FT BRGG 25/5 RPR WDPK | WILLITS | ETL.7550.POLE.WOOD | 2021-05-05 | 2021-05-05 | 2022-08-21 | 2022-05-05 | 2022-05-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45148575 | T2 EI MNDCNO-WLLTS-FT BRGG 25/5 RPR WDPK | ICW
LC | 120938882 | 028/002 | T2 EI MEND-WILL-FT BRAGG 28/2 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-05-05 | 2021-05-05 | 2022-08-18 | 2022-05-05 | 2022-05-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31542636 | T2 DI MNDCN-WLLTS-FT BRGG 16/1 RPL STRW | 70Y
LC | 120938900 | 021/006 | T2 EI FULTON-HOPLAND 021/006 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-05 | 2021-05-05 | 2022-08-03 | 2022-05-05 | 2022-05-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541677 | T2 EI FULTON-HOPLAND 019/006 RPL POLE | 70Y
LC | 120939354 | 007/060A | T2 EI HELMS-GREGG #1 007/060A RPR FOND | FRESNO | ETL.4870.TOWR | 2021-05-05 | 2021-05-05 | 2022-05-16 | 2022-05-05 | 2022-05-05 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45069466 | T2 EI HELMS-GREGG #1 007/060A RPR FOND | ICQ
LC | 120939432 | 005/060 | WV T2 PRDISE-BUTTE 5/60 INS DMPS | TABLEMTN | ETL.4396.INSL.NCER | 2021-05-05 | 2021-05-05 | 2022-06-27 | 2022-05-05 | 2022-05-05 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install | 45261915 | WV T2 PRDISE-BUTTE 5/60 INS DMPS | ICS
LC | 120939930 | 003/031 | T2 EI MORAGA-OAKLAND #3 3/31 RPL INSS | CONCORD | ETL.2740.INSL.NCER | 2021-05-05 | 2021-05-05 | 2022-07-06 | 2022-05-05 | 2022-05-05 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547469 | T2 EI MORAGA-OAKLAND #3 RPL INSS 5TWRS | 93K
LC | 120940065 | 003/029 | T2 EI MORAGA-OAKLAND #3 3/29 RPL INSS | CONCORD | ETL.2740.INSL.NCER | 2021-05-05 | 2021-05-05 | 2022-07-07 | 2022-05-05 | 2022-05-05 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547469 | T2 EI MORAGA-OAKLAND #3 RPL INSS 5TWRS | 93K
LC | 120940067 | 003/027 | T2 EI MORAGA-OAKLAND #1 3/27 RPL INSS | CONCORD | ETL.2720.INSL | 2021-05-05 | 2021-05-05 | 2022-07-01 | 2022-05-05 | 2022-05-05 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547461 | T2 DI MORAGA-OAKLAND #1 RPLC INSS 5TWRS | 93K
LC | 120940115 | 003/027 | T2 EI MORAGA-OAKLAND #3 3/27 RPL INSS | CONCORD | ETL.2740.INSL.NCER | 2021-05-05 | 2021-05-05 | 2022-12-03 | 2022-05-05 | 2022-05-05 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547469 | T2 EI MORAGA-OAKLAND #3 RPL INSS 5TWRS | 93K
LC | 120941093 | 024/139 | T2 DI TESLA-SLD-MTC 24/139 RPR DAMPR | VICTOR | ETL.4000.INSL.CERA | 2021-05-06 | 2021-05-04 | 2022-01-31 | 2022-05-04 | 2022-05-04 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace | 44975291 | T2 DI TESLA-SLD-MTC 24/139 RPR DAMPR | ICW
LC | 120941095 | 024/139 | T2 DI TESLA-SLD-MTC 24/139 RPR GYWW | VICTOR | ETL.4000.POLE.WOOD | 2021-05-06 | 2021-05-04 | 2021-10-06 | 2022-05-04 | 2022-05-04 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44975292 | T2 DI TESLA-SLD-MTC 24/139 RPR GYWW | ICW
LC | 120941347 | 033/142 | T2 EI MRR BY-SLR S#1 33/142 RPR FOND | PISMOBCH | ETL.5300.TOWR | 2021-05-06 | 2021-05-04 | 2022-07-14 | 2022-05-04 | 2022-05-04 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45073966 | T2 EI MRR BY-SLR S#1 33/142 RPR FOND | ICQ
LC | 120941359 | 031/136 | T2 EI MRR BY-SLAR SW S#1 31/136 RPR FOND | PISMOBCH | ETL.5300.TOWR | 2021-05-06 | 2021-05-04 | 2022-07-22 | 2022-05-04 | 2022-05-04 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45073967 | T2 EI MRR BY-SLAR SW S#1 31/136 RPR FOND | ICQ
LC | 120941371 | 032/137 | T2 EI MORRO BAY-SLR ST#1 32/137 RPR FOND | PISMOBCH | ETL.5300.TOWR | 2021-05-06 | 2021-05-04 | 2022-07-20 | 2022-05-04 | 2022-05-04 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45073968 | T2 EI MORRO BAY-SLR ST#1 32/137 RPR FOND | ICQ
LC | 120941549 | 016/009 | T2 EI HMBLT BY-RIO DLL JCT 16/9 ANTI SPL | EUREKA | ETL.7100.POLE.WOOD | 2021-05-06 | 2021-05-06 | 2022-04-23 | 2022-05-06 | 2022-05-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Hardware-Wood | Install | 44875359 | T2 EI HMBLT BY-RIO DLL JCT 16/9 ANTI SPL | ICW
LC | 120941616 | 024/161 | T2 EI POE-RIO OSO 024/161 RPR JUMS | TABLEMTN | ETL.5540.INSL.CERA | 2021-05-06 | 2021-05-06 | 2022-08-09 | 2022-05-06 | 2022-05-06 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO NTDE | No Good/Out of Stdrd | Jumper-Steel | Repair | 45212493 | T2 EI POE-RIO OSO 024/161 RPR JUMS | ICS
LC | 120941620 | 018/428 | T2 DI DRUM-GRASS VLY-WMR 18/428 RPR SPLS | SACTO | ETL.6760.POLE.WOOD | 2021-05-06 | 2021-05-03 | 2022-07-05 | 2022-05-03 | 2022-05-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 44812241 | T2 DI DRUM-GRASS VLY-WMR 18/428 RPR SPLS | ICW
LC | 120941891 | 002/022 | T2 DI COTTONWOOD-DLVN #1 2/22 RMV STEP | TABLEMTN | ETL.4550.TOWR | 2021-05-06 | 2021-05-04 | 2021-06-12 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44861466 | T2 DI COTTONWOOD-DLVN #1 2/22 RMV STEP | ICQ
LC | 120942085 | 008/163 | T2 EI CTTONWOOD-RED BLUFF 8/163 INS DAMW | TABLEMTN | ETL.6660.POLE.WOOD | 2021-05-06 | 2021-05-06 | 2022-09-29 | 2022-05-06 | 2022-05-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP CREW COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Damper-Wood | Install | 45242423 | T2 EI CTTONWOOD-RED BLUFF 8/163 INS DAMW | ICW
LC | 120942309 | 000/012 | T2 DI AUBERRY TAP 000/012 RPL INSW | FRESNO | ETL.9331.INSL.NCER | 2021-05-06 | 2021-05-05 | 2022-05-02 | 2022-05-05 | 2022-05-05 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31540443 | T2 DI AUBERRY TAP 000/012 RPL INSW | 93I
LC | 120942385 | 000/002 | T2 EI KNGS RVR-SNGR-RDLY 0/2 COMPLETE | FRESNO | ETL.2030.POLE.WOOD | 2021-05-06 | 2021-05-06 | 2022-04-13 | 2022-05-06 | 2022-05-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45066232 | T2 EI KNGS RVR-SNGR-RDLY 0/2 RPR GYWW | ICW
LC | 120942523 | 010/198 | T2 WV CLGT-PLRMO 10/198 INS GYWW CMPLTD | SACTO | ETL.6500.POLE.NWOD | 2021-05-06 | 2021-05-06 | 2022-05-16 | 2022-05-06 | 2022-05-06 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Guy Wire-Steel | Install | 44811961 | T2 COLGATE-PALERMO 010/198 INS GYWW | ICS
LC | 120943094 | 000/002 | T2 EI STNSLAUS-MLNS-MANTE 0/2 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-05-06 | 2021-05-06 | 2022-01-27 | 2022-05-06 | 2022-05-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45119048 | T2 EI STNSLAUS-MLNS-MANTE 0/2 RPR FOND | ICQ
LC | 120943107 | 000/004 | T2 EI STANISLAUS-MNTCA#2 0/4 RPR SPLS | VICTOR | ETL.3820.INSL.CERA | 2021-05-06 | 2021-05-06 | 2021-11-29 | 2022-05-06 | 2022-05-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Repair | 44977849 | T2 EI STANISLAUS-MNTCA#2 0/4 RPR SPLS | ICS
LC | 120943446 | 010/066 | T2 EI STNSLS-MLNES-MANTE 10/66 RPR STRT | VICTOR | ETL.3830.TOWR | 2021-05-06 | 2021-05-06 | 2022-02-01 | 2022-05-06 | 2022-05-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45122278 | T2 EI STNSLS-MLNES-MANTE 10/66 RPR STRT | ICQ
LC | 120943474 | 006/135 | T2 EI COTNWD-RED BLUFF 006/135 RPR STRW | TABLEMTN | ETL.6660.POLE.WOOD | 2021-05-06 | 2021-05-06 | 2022-09-29 | 2022-05-06 | 2022-05-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45053750 | T2 EI COTNWD-RED BLUFF 006/135 RPR STRW | ICW
LC | 120943592 | 023/102 | T2 DI MOSS LDNG-LS AGLS 23/102 RPL INSS | MOSSLNDG | ETL.5340.INSL | 2021-05-06 | 2021-04-15 | 2022-04-12 | 2022-04-15 | 2022-04-15 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31539341 | T2 EI MSS LNDG-LS AGLS SW RPL INSS 6TWR | 93K
LC | 120943744 | 018/427 | T2 DI DRM-GRS VLY-WMR 18/427 RPR SPLW | SACTO | ETL.6760.INSL.NCER | 2021-05-06 | 2021-05-05 | 2022-07-05 | 2022-05-05 | 2022-05-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 44812231 | T2 DI DRM-GRS VLY-WMR 18/427 RPR SPLW | ICW
LC | 120944011 | 014/066 | T2 DI MOSS LANDING-COBURN 14/66 INS HRDT | MOSSLNDG | ETL.5330.TOWR | 2021-05-06 | 2021-04-16 | 2022-05-18 | 2022-04-16 | 2022-04-16 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45121183 | T2 DI MOSS LANDING-COBURN 14/66 INS HRDT | ICQ
LC | 120944028 | 049/003 | T2 EI HUMBOLDT-TRINITY 049/003L RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-05-06 | 2021-05-06 | 2022-05-23 | 2022-05-06 | 2022-05-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31506039 | DI HUMBOLDT-TRINITY REPL POLES(ENG) | 70Y
LC | 120944051 | 049/003 | T2 EI HUMBOLDT-TRINITY 049/003R COMPLETE | EUREKA | ETL.1820.POLE.WDPS | 2021-05-06 | 2021-05-06 | 2022-05-23 | 2022-05-06 | 2022-05-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31506039 | DI HUMBOLDT-TRINITY REPL POLES(ENG) | 70Y
LC | 120944056 | 114/000 | T2 EI HMBLDT-BRDGVLLE 114/0R RPR GYWW | EUREKA | ETL.1810.POLE.STPS | 2021-05-06 | 2021-05-05 | 2022-04-05 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45155485 | T2 EI HMBLDT-BRDGVLLE 114/0R RPR GYWW | ICW
LC | 120944083 | 114/000 | T2 EI HMBLDT-BRDGVLLE 114/0L RPR GYWW | EUREKA | ETL.1810.POLE.STPS | 2021-05-06 | 2021-05-05 | 2022-04-05 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45155485 | T2 EI HMBLDT-BRDGVLLE 114/0R RPR GYWW | ICW
LC | 120944152 | 029/250 | WV T2 BRDGVILL-CTTNWD 29/250 RPL HRDW | TABLEMTN | ETL.1110.POLE.STPS | 2021-05-06 | 2021-05-06 | 2022-06-22 | 2022-05-06 | 2022-05-06 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45223808 | WV T2 BRDGVILL-CTTNWD 29/250 RPL HRDW | ICS
LC | 120944585 | 002/003 | T2 DI VLY SPRNGS-CLVRS CMNT 2/3 RPL STRW | VICTOR | ETL.8220.POLE.WOOD | 2021-05-06 | 2021-03-06 | 2022-03-25 | 2022-03-06 | 2022-03-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543645 | T2 WV VLLEY SPRNGS-CLVRS CMNT 1/4 RPL PL | 70Y
LC | 120944901 | 008/071 | T2 DI PARADISE-TABLE MTN 8/71 RPR FOND | TABLEMTN | ETL.4316.TOWR | 2021-05-06 | 2021-04-09 | 2022-06-23 | 2022-04-09 | 2022-04-09 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45198303 | T2 DI PARADISE-TABLE MTN 8/71 RPR FOND | ICQ
LC | 120945307 | 031/004 | T2 EI FULTON-HOPLAND 31/4 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-06 | 2021-05-06 | 2022-06-24 | 2022-05-06 | 2022-05-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143968 | T2 EI FULTON-HOPLAND 31/4 RPR STRW | ICW
LC | 120946238 | 008/063A | T2 EI HELMS-GREGG #1 8/063A RMV NEST | FRESNO | ETL.4870.TOWR | 2021-05-06 | 2021-05-06 | 2022-08-21 | 2022-05-06 | 2022-05-06 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | Debris/Nest/etc. | Structure-Steel | Remove | 45069449 | T2 EI HELMS-GREGG #1 8/063A RMV NEST | ICS
LC | 120946242 | 008/067A | T2 EI HELMS-GREGG #1 08/067A RPR FOND | FRESNO | ETL.4870.TOWR | 2021-05-06 | 2021-05-06 | 2022-05-16 | 2022-05-06 | 2022-05-06 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45069479 | T2 EI HELMS-GREGG #1 08/067A RPR FOND | ICQ
LC | 120946243 | 008/064A | T2 EI HELMS-GREGG #1 8/064A RPR FOND | FRESNO | ETL.4870.TOWR | 2021-05-06 | 2021-05-06 | 2022-05-16 | 2022-05-06 | 2022-05-06 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45069500 | T2 EI HELMS-GREGG #1 8/064A RPR FOND | ICQ
LC | 120946249 | 008/064A | T2 EI HELMS-GREGG #1 08/064A RMV NEST | FRESNO | ETL.4870.TOWR | 2021-05-06 | 2021-05-06 | 2022-08-27 | 2022-05-06 | 2022-05-06 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | Debris/Nest/etc. | Structure-Steel | Remove | 45069451 | T2 EI HELMS-GREGG #1 08/064A RMV NEST | ICS
LC | 120946270 | 007/062A | T2NT EI HELMS-GREGG #1 7/062A MASTIC | FRESNO | ETL.4870.TOWR | 2021-05-06 | 2021-05-06 | 2021-12-07 | 2022-05-06 | 2022-05-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2N PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45069501 | T2NT EI HELMS-GREGG #1 7/062A MASTIC | ICQ
LC | 120947356 | 006/103 | T2 DI SSQC-SNTA YNEZ SS 006/103 RPR SPLW | PISMOBCH | ETL.3700.INSL.CERA | 2021-05-07 | 2021-05-06 | 2021-11-03 | 2022-05-06 | 2022-05-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 44963138 | T2 DI SSQC-SNTA YNEZ SS 006/103 RPR SPLW | ICW
LC | 120947374 | 030/005 | T2 EI MNDCN-WLLTS-FRT BRGG 30/5 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-07 | 2021-05-06 | 2022-05-16 | 2022-05-06 | 2022-05-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543104 | T2 DI MNDCN-WLTS-FRT BRG 25/0 RPL STRW | 70Y
LC | 120947545 | 013/118 | T2 DI DRUM-RIO OSO #1 013/118 RPL SPLS | SACTO | ETL.1430.INSL.CERA | 2021-05-07 | 2021-05-06 | 2021-12-15 | 2022-05-06 | 2022-05-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Replace | 44811963 | T2 DI DRUM-RIO OSO #1 013/118 RPL SPLS | ICS
LC | 120947831 | 024/181 | T2 DI DRUM-RIO OSO #1 024/181 RPR INSS | SACTO | ETL.1420.INSL.NCER | 2021-05-07 | 2021-05-06 | 2022-02-10 | 2022-05-06 | 2022-05-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44811964 | T2 DI DRUM-RIO OSO #1 024/181 RPR INSS | ICS
LC | 120947971 | :006/038 | T2 EI STNSLS-MLNS S-MNTCA :6/38 RMV VEG | VICTOR | ETL.3830.TOWR | 2021-05-07 | 2021-05-07 | 2021-12-15 | 2022-05-07 | 2022-05-07 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120948046 | :006/036 | T2 EI STSLS-MLNS S-MNT #1 :6/36 RPL INSS | VICTOR | ETL.3830.INSL.NCER | 2021-05-07 | 2021-05-07 | 2022-09-20 | 2022-05-07 | 2022-05-07 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528967 | NN STANISLAUS-MLNS-MNTC RPLC INSS 11TWR | 93K
LC | 120948235 | 012/107 | T2 DI PRDSE-TBLE MTN 12/107 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-05-07 | 2021-04-15 | 2022-05-13 | 2022-04-15 | 2022-04-15 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 120948304 | 016/369 | T2 DI DRUM-GRS VLY-WMR 16/369 RPLC INSW | SACTO | ETL.6760.INSL.NCER | 2021-05-07 | 2021-05-05 | 2022-06-28 | 2022-05-05 | 2022-05-05 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31540566 | T2 DI DRUM-GRS VLY-WMR 16/369 RPLC INSWC | 93I
LC | 120948701 | :011/060 | T2 DI CY HS CN-SS-SD :011/060 RPR INSS | MOSSLNDG | ETL.2910.INSL.CERA | 2021-05-07 | 2021-04-19 | 2021-10-29 | 2022-04-19 | 2022-04-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44981670 | T2 DI CY HS CN-SS-SD :011/060 RPR INSS | ICS
LC | 120948702 | :011/060 | T2 DI CY HS CN-SS-SD :011/060 RPR INSS | MOSSLNDG | ETL.2900.INSL.CERA | 2021-05-07 | 2021-04-19 | 2021-10-29 | 2022-04-19 | 2022-04-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44962407 | T2 DI CY HS CN-SS-SD :011/060 RPR INSS | ICS
LC | 120948921 | 001/000 | T2 DI AUBERRY TAP 1/0 COMPLETE | FRESNO | ETL.9331.INSL.NCER | 2021-05-07 | 2021-05-05 | 2022-05-03 | 2022-05-05 | 2022-05-05 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31540443 | T2 DI AUBERRY TAP 000/012 RPL INSW | 93I
LC | 120949722 | 020/126 | T2 EI STNLS-MLS STA-MTE 20/126 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-05-07 | 2021-05-07 | 2022-02-22 | 2022-05-07 | 2022-05-07 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45123117 | T2 EI STNLS-MLS STA-MTE 20/126 RPR FOND | ICQ
LC | 120949832 | 005/074 | T2 DI VALLEY SPRINGS-CLAY 5/74 RPR STRW | VICTOR | ETL.8264.POLE.WOOD | 2021-05-07 | 2021-05-07 | 2021-11-29 | 2022-05-07 | 2022-05-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44975287 | T2 DI VALLEY SPRINGS-CLAY 5/74 RPR STRW | ICW
LC | 120949855 | :010/057 | T2 DI CZY HRS CN-SS-SD :010/057 RPL HRDT | MOSSLNDG | ETL.2900.TOWR | 2021-05-07 | 2021-04-19 | 2022-07-07 | 2022-04-19 | 2022-04-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45075187 | T2 DI CZY HRS CN-SS-SD :010/057 RPL HRDT | ICQ
LC | 120950157 | :010/055 | T2 DI CRZY HRS CYN-SLS-SLD 10/55 INS GRD | MOSSLNDG | ETL.2900.TOWR | 2021-05-07 | 2021-04-16 | 2021-10-04 | 2022-04-16 | 2022-04-16 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Animal Guard-Steel | Install | 44962401 | T2 DI CRZY HRS CYN-SLS-SLD 10/55 INS GRD | ICS
LC | 120950777 | 000/007 | T2 DI KRCKHFF-CLVS-SNGR #1 0/7 RPR FOND | FRESNO | ETL.1890.TOWR | 2021-05-07 | 2021-04-16 | 2022-02-08 | 2022-04-16 | 2022-04-16 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45069506 | T2 DI KRCKHFF-CLVS-SNGR #1 0/7 RPR FOND | ICQ
LC | 120950847 | 013/098 | T2 DI SLT SPRNGS-TGR CRK 13/98 RPL INSS | VICTOR | ETL.3500.INSL.NCER | 2021-05-07 | 2021-04-16 | 2022-06-19 | 2022-04-16 | 2022-04-16 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31580615 | T2 DI ST SPNGS TGR CK RPL INSS 4TWRS | 93K
LC | 120951354 | 032/001 | T2 EI MEND-WILL-FT BRAGG 32/1 COMPLETED | WILLITS | ETL.7550.POLE.WOOD | 2021-05-07 | 2021-05-07 | 2022-08-16 | 2022-05-07 | 2022-05-07 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31542636 | T2 DI MNDCN-WLLTS-FT BRGG 16/1 RPL STRW | 70Y
LC | 120951461 | 030/002 | T2 EI FULTON-HOPLAND 30/2 GRND WASH | LAKEVLLE | ETL.6890.INSL.NCER | 2021-05-07 | 2021-05-07 | 2022-06-22 | 2022-05-07 | 2022-05-07 | Late | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Contaminated | Insulator | Ground Wash | 45260983 | T2 EI FULTON-HOPLAND 30/2 GRND WASH | ICD
LC | 120951472 | 030/001 | T2 EI FULTON-HOPLAND 30/1 GRND WASH | LAKEVLLE | ETL.6890.INSL | 2021-05-07 | 2021-05-07 | 2022-06-22 | 2022-05-07 | 2022-05-07 | Late | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Contaminated | Insulator | Ground Wash | 45260984 | T2 EI FULTON-HOPLAND 30/1 GRND WASH | ICD
LC | 120952990 | 009/179 | T2 EI MNTA VISTA-LOS GATOS 9/179 RMV VEG | METCALF | ETL.7610.POLE.WOOD | 2021-05-08 | 2021-05-08 | 2022-08-18 | 2022-05-08 | 2022-05-08 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAR | Overgrown | Vegetation | Trim
LC | 120953278 | 009/178 | T2 EI MNTA VSTA-LS GTOS 9/178 RMV VEG | METCALF | ETL.7610.POLE.WOOD | 2021-05-08 | 2021-05-08 | 2022-08-18 | 2022-05-08 | 2022-05-08 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAR | Overgrown | Vegetation | Trim
LC | 120953396 | 000/006 | T2 EI HILLSDALE JCT-HMB 0/6 MASTIC | METCALF | ETL.7060.POLE.NWOD | 2021-05-08 | 2021-05-08 | 2021-08-20 | 2022-05-08 | 2022-05-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAR | No Good/Out of Stdrd | Structure-Wood | Repair | 44931590 | T2 EI HILLSDALE JCT-HMB 0/6 MASTIC | ICW
LC | 120953654 | 041/008 | T2 EI MNDCN-WLLTS-FRT BRGG 41/8 RPR HRDW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-08 | 2021-05-08 | 2022-05-11 | 2022-05-08 | 2022-05-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45150035 | T2 EI MNDCN-WLLTS-FRT BRGG 41/8 RPR HRDW | ICW
LC | 120990839 | 099/003C | T2 EI HUMBOLDT-TRINITY 99/3C COMPLETE | EUREKA | ETL.1820.POLE.WOOD | 2021-05-10 | 2021-04-27 | 2022-03-24 | 2022-04-27 | 2022-04-27 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581077 | T2 EI HMBLDT-TRNTY 099/003B RPL POLE | 70Y
LC | 120991220 | 040/004 | T2 EI MNDCN-WLLTS-FRT BRGG 40/4 RPR INSW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-10 | 2021-05-10 | 2022-08-16 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45150029 | T2 EI MNDCN-WLLTS-FRT BRGG 40/4 RPR INSW | ICW
LC | 120991747 | 009/112 | T2 DI W. PNT-VLY SPRNGS 9/112 RPLC DAMW | VICTOR | ETL.8350.INSL.NCER | 2021-05-10 | 2021-05-07 | 2022-02-25 | 2022-05-07 | 2022-05-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace | 45155672 | T2 DI W. PNT-VLY SPRNGS 9/112 RPLC DAMW | ICW
LC | 120993618 | 001/022 | T2 EI WEIMAR #1 001/022 COMPLETE | SACTO | ETL.7560.POLE.NWOD | 2021-05-10 | 2021-05-10 | 2022-08-28 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44812222 | T2 EI WEIMAR #1 001/022 RPR GYWW | ICW
LC | 120993999 | 009/155 | T2 DI TEJON-LEBEC 9/155 RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-05-10 | 2021-05-08 | 2021-08-12 | 2022-05-08 | 2022-05-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44930592 | T2 DI TEJON-LEBEC 9/155 RPR GYWW | ICW
LC | 120994492 | 039/007 | T2 EI MNDCN-WLLTS-FRT BRGG 39/7 RPR INSW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-10 | 2021-05-10 | 2022-08-17 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE SR22 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45150028 | T2 EI MNDCN-WLLTS-FRT BRGG 39/7 RPR INSW | ICW
LC | 120994773 | 110/003 | T2 EI HMBLDT-BRDGVLLE 110/3 RMV VEG | EUREKA | ETL.1810.POLE.STPS | 2021-05-10 | 2021-05-08 | 2021-07-14 | 2022-05-08 | 2022-05-08 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120994782 | 111/002 | T2 EI HMBLDT-BRDGVLLE 111/002 RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-05-10 | 2021-05-08 | 2022-04-06 | 2022-05-08 | 2022-05-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31541449 | EI HUMBOLDT-BRIDGEVLLE 107/003 RPLC STRW | 70Y
LC | 120994784 | 111/001 | T2 EI HMBLDT-BRDGVLLE 111/1 RPR INSW | EUREKA | ETL.1810.INSL.NCER | 2021-05-10 | 2021-05-08 | 2022-06-17 | 2022-05-08 | 2022-05-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Insulator-Wood | Repair | 44829885 | T2 EI HMBLDT-BRDGVLLE 111/1 RPR INSW | ICW
LC | 120994785 | 110/002 | T2 EI HMBLDT-BRDGVLLE 110/002 RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-05-10 | 2021-05-08 | 2022-04-09 | 2022-05-08 | 2022-05-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31541449 | EI HUMBOLDT-BRIDGEVLLE 107/003 RPLC STRW | 70Y
LC | 120994788 | 110/002 | T2 EI HMBLDT-BRDGVLLE 110/002 RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-05-10 | 2021-05-08 | 2022-04-09 | 2022-05-08 | 2022-05-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31541449 | EI HUMBOLDT-BRIDGEVLLE 107/003 RPLC STRW | 70Y
LC | 120994860 | 111/003 | T2 EI HMBLDT-BRDGVLLE 111/003 RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-05-10 | 2021-05-08 | 2022-04-05 | 2022-05-08 | 2022-05-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31541449 | EI HUMBOLDT-BRIDGEVLLE 107/003 RPLC STRW | 70Y
LC | 120994863 | 111/002 | T2 EI HMBLDT-BRDGVLLE 111/002 RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-05-10 | 2021-05-08 | 2022-04-06 | 2022-05-08 | 2022-05-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31541449 | EI HUMBOLDT-BRIDGEVLLE 107/003 RPLC STRW | 70Y
LC | 120995272 | 111/006 | T2 EI HMBLDT-BRDGVLLE 111/6 RMV VEG | EUREKA | ETL.1810.TOWR | 2021-05-10 | 2021-05-08 | 2022-06-24 | 2022-05-08 | 2022-05-08 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120995277 | 111/000 | T2 EI HMBLDT-BRDGVLLE 111/0 RMV VEG | EUREKA | ETL.1810.POLE.WDPS | 2021-05-10 | 2021-05-08 | 2022-04-26 | 2022-05-08 | 2022-05-08 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120995296 | 111/003 | T2 EI HMBLDT-BRDGVLLE 111/003 RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-05-10 | 2021-05-08 | 2022-04-05 | 2022-05-08 | 2022-05-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31541449 | EI HUMBOLDT-BRIDGEVLLE 107/003 RPLC STRW | 70Y
LC | 120995303 | 111/004 | T2 EI HMBLDT-BRDGVLLE 111/004 RPL ANCW | EUREKA | ETL.1810.POLE.WDPS | 2021-05-10 | 2021-05-08 | 2022-06-17 | 2022-05-08 | 2022-05-08 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31542127 | T2 EI HMBLDT-BRDGVLLE 111/004 RPL ANCW | 93E
LC | 120995305 | 111/004 | T2 EI HMBLDT-BRDGVLLE 111/004 RMV VEG | EUREKA | ETL.1810.POLE.WDPS | 2021-05-10 | 2021-05-08 | 2021-07-22 | 2022-05-08 | 2022-05-08 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 120995730 | 011/074 | T2 EI DELEVAN-VCA #1 11/74 RPR COMPLETE | SACTO | ETL.5010.INSL.CERA | 2021-05-10 | 2021-05-08 | 2022-07-23 | 2022-05-08 | 2022-05-08 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Conductor-Steel | Repair | 44811960 | T2 EI DELEVAN-VACA #1 11/074 RPR CNDT | ICS
LC | 120995769 | 010/187 | T2 EI MNTA VSTA-LS GTS 10/187 RMV VEG | METCALF | ETL.7610.POLE.WOOD | 2021-05-10 | 2021-05-08 | 2021-10-07 | 2022-05-08 | 2022-05-08 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAR | Overgrown | Vegetation | Trim
LC | 120995770 | 041/004 | T2 EI MNDCN-WLLTS-FRT BRGG 41/4 RPL GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-10 | 2021-05-08 | 2022-09-13 | 2022-05-08 | 2022-05-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45150032 | T2 EI MNDCN-WLLTS-FRT BRGG 41/4 RPL GYWW | ICW
LC | 120996556 | 005/056 | T2 EI SNEATH LANE-PACIFICA 5/56 RPL INSW | METCALF | ETL.7575.INSL.NCER | 2021-05-10 | 2021-05-10 | 2022-05-04 | 2022-05-10 | 2022-05-10 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31596140 | T2 EI SNEATH LANE-PACIFICA 5/56 RPL INSW | 93I
LC | 120996682 | 005/056 | T2 EI SNEATH LANE-PACIFICA 5/56 INS DAMW | METCALF | ETL.7575.POLE.WOOD | 2021-05-10 | 2021-05-10 | 2022-05-04 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Damper-Wood | Replace | 45234199 | T2 EI SNEATH LANE-PACIFICA 5/56 INS DAMW | ICW
LC | 120997029 | 039/006 | T2 EI MNDCN-WLLTS-FRT BRGG 39/6 RPR INSW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-10 | 2021-05-10 | 2022-08-16 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45150027 | T2 EI MNDCN-WLLTS-FRT BRGG 39/6 RPR INSW | ICW
LC | 120998119 | 005/007 | T2 DI FULTON-HOPLAND :5/7 RPR INSW | LAKEVLLE | ETL.6890.INSL.CERA | 2021-05-10 | 2021-04-28 | 2022-03-31 | 2022-04-28 | 2022-04-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45143562 | T2 DI FULTON-HOPLAND :5/7 RPR INSW | ICW
LC | 120998159 | :007/009 | T2 DI BELLOTA-RBK-MLS SWST :7/9 RPL HRDD | VICTOR | ETL.1070.POLE.NWOD | 2021-05-10 | 2021-05-07 | 2022-05-07 | 2022-05-07 | 2022-05-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45155673 | T2 DI BELLOTA-RBK-MLS SWST :7/9 RPL HRDD | ICW
LC | 121004964 | 045/393 | T2 EI PIT #1-COTTONWOOD 045/393 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-05-10 | 2021-05-10 | 2021-07-30 | 2022-05-10 | 2022-05-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB | No Good/Out of Stdrd | Structure-Tower | Repair | 44934175 | T2 EI PIT #1-COTTONWOOD 045/393 RPR STRT | ICQ
LC | 121011206 | 045/392 | T2 EI PIT #1-COTTONWOOD 045/392 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-05-10 | 2021-05-10 | 2022-03-04 | 2022-05-10 | 2022-05-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45149566 | T2 EI PIT #1-COTTONWOOD 045/392 RPR STRT | ICQ
LC | 121014354 | 039/002 | T2 EI MNDCN-WLLTS-FRT BRGG 39/2 RPR INSW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-10 | 2021-05-10 | 2022-08-17 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45150026 | T2 EI MNDCN-WLLTS-FRT BRGG 39/2 RPR INSW | ICW
LC | 121015658 | 012/143B | EI T2 DRUM-SUMMIT #1 12/143B RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2021-05-10 | 2021-05-10 | 2022-06-26 | 2022-05-10 | 2022-05-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543339 | T2 EI DRUM-SUMMIT #1 9/111 RPL STRW | 70Y
LC | 121017170 | 012/143C | EI T2 DRUM-SUMMIT #1 12/143C RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2021-05-10 | 2021-05-10 | 2022-06-26 | 2022-05-10 | 2022-05-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543339 | T2 EI DRUM-SUMMIT #1 9/111 RPL STRW | 70Y
LC | 121019898 | 044/382 | T2 EI PIT #1-COTTONWOOD 44/382 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-05-10 | 2021-05-10 | 2022-03-04 | 2022-05-10 | 2022-05-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45149563 | T2 EI PIT #1-COTTONWOOD 44/382 RPR STRT | ICQ
LC | 121022135 | 071/360A | T2 EI MALIN-RND MTN #2 071/360A RPR ANCS | TABLEMTN | ETL.6020.TOWR | 2021-05-10 | 2021-05-10 | 2022-07-19 | 2022-05-10 | 2022-05-10 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair | 45194406 | T2 EI MALIN-RND MTN #2 071/360A RPR ANCS | ICS
LC | 121028924 | 012/145A | EI T2 DRUM-SUMMIT #1 12/145A RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2021-05-10 | 2021-05-10 | 2022-06-30 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Missing | Guy Wire-Wood | Install | 44812191 | EI T2 DRUM-SUMMIT #1 12/145A RPR GYWW | ICW
LC | 121029868 | 012/145B | EI T2 DRUM-SUMMIT #1 12/145B RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2021-05-10 | 2021-05-10 | 2022-06-30 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44812196 | EI T2 DRUM-SUMMIT #1 12/145B RPR GYWW | ICW
LC | 121030489 | 012/145C | EI T2 DRUM-SUMMIT #1 12/145C RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2021-05-10 | 2021-05-10 | 2022-06-30 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44812197 | EI T2 DRUM-SUMMIT #1 12/145C RPR GYWW | ICW
LC | 121030949 | 038/005 | T2 EI MNDCN-WLLTS-FRT BRGG 38/5 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-10 | 2021-05-10 | 2022-08-20 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45150022 | T2 EI MNDCN-WLLTS-FRT BRGG 38/5 RPR GYWW | ICW
LC | 121031301 | 038/005 | T2 EI MNDCN-WLLTS-FRT BRGG 38/5 RPR JUMW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-10 | 2021-05-10 | 2022-08-18 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45465300 | T2 EI MNDCN-WLLTS-FRT BRGG 38/5 RPR JUMW | ICW
LC | 121032607 | 012/147 | EI T2 DRUM-SUMMIT NO. 2 12/147 RPR GYWW | SACTO | ETL.1450.POLE.WDPS | 2021-05-10 | 2021-05-10 | 2022-05-04 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44812220 | EI DRUM-SUMMIT NO. 2 12/147 RPR GYWW | ICW
LC | 121033816 | 012/147 | EI T2 DRUM-SUMMIT NO. 2 12/147 RPR GYWW | SACTO | ETL.1450.POLE.WDPS | 2021-05-10 | 2021-05-10 | 2022-05-04 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44812221 | EI DRUM-SUMMIT NO. 2 12/147 RPR GYWW | ICW
LC | 121037432 | 022/318 | T2 DI CLAY-MARTEL 22/318 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-10 | 2021-05-08 | 2021-08-09 | 2022-05-08 | 2022-05-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44809813 | T2 DI CLAY-MARTEL 22/318 RPR GYWW | ICW
LC | 121041146 | 008/060 | T2 DI EL DRDO-MSSRI FLT #1 8/60 RPL HRDT | SACTO | ETL.1530.TOWR | 2021-05-10 | 2021-04-16 | 2022-11-04 | 2022-04-16 | 2022-04-16 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45078087 | T2 DI EL DRDO-MSSRI FLT #1 8/60 RPL HRDT | ICQ
LC | 121044710 | 001/023 | T2 DI COLGATE-PALERMO 1/23 RPLC STRW | SACTO | ETL.6500.POLE.WOOD | 2021-05-10 | 2021-05-10 | 2022-05-20 | 2022-05-10 | 2022-05-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540562 | T2 DI COLGATE-PALERMO 7/135 RPLC STRW | 70Y
LC | 121045151 | :009/052 | T2 DI CRZY HRS CYN-SL-SLD :9/52 RPR INSS | MOSSLNDG | ETL.2910.INSL.CERA | 2021-05-10 | 2021-04-16 | 2021-10-29 | 2022-04-16 | 2022-04-16 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44981671 | T2 DI CRZY HRS CYN-SL-SLD :9/52 RPR INSS | ICS
LC | 121047511 | 052/004 | T2 EI HUMBOLDT-TRINITY 052/004 RPR CRSW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-10 | 2021-05-10 | 2022-06-06 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45145197 | T2 EI HUMBOLDT-TRINITY 052/004 RPR CRSW | ICW
LC | 121047827 | :024/127 | T2 DI CRZY HS CYN-SL-SD :24/127 RPL INSS | MOSSLNDG | ETL.2910.INSL.NCER | 2021-05-10 | 2021-04-15 | 2022-03-10 | 2022-04-15 | 2022-04-15 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528632 | DI CRZY HRS CYN-SLNS-SLD2 RPL INSS 6TWR | 93K
LC | 121047829 | :024/127 | T2 DI CRZY HS CYN-SL-SD :24/127 RPL INSS | MOSSLNDG | ETL.2900.INSL.NCER | 2021-05-10 | 2021-04-15 | 2021-11-13 | 2022-04-15 | 2022-04-15 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31527952 | DI CRZYHS CNY-SLS-SLD #1 RPL INSS 4TWRS | 93K
LC | 121049882 | 005/096 | T2 DI COLGATE-PALERMO 5/96 RPR SPLW | SACTO | ETL.6500.INSL.NCER | 2021-05-10 | 2021-05-10 | 2022-05-18 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 44812198 | T2 DI COLGATE-PALERMO 5/96 RPR SPLW | ICW
LC | 121053018 | 010/204 | T2 DI COLGATE-PALERMO 10/204 RPR SPLW | SACTO | ETL.6500.INSL.NCER | 2021-05-10 | 2021-05-10 | 2021-11-18 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 44812193 | T2 DI COLGATE-PALERMO 10/204 RPR SPLW | ICW
LC | 121061192 | 043/365 | T2 EI PIT #1-COTTONWOOD 043/365 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-05-10 | 2021-05-10 | 2022-02-25 | 2022-05-10 | 2022-05-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45149539 | T2 EI PIT #1-COTTONWOOD 043/365 RPR STRT | ICQ
LC | 121063798 | 001/018 | T2 DI COLGATE-PALERMO 001/018 RPR SPLW | SACTO | ETL.6500.POLE.WOOD | 2021-05-10 | 2021-05-10 | 2022-05-21 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 44812186 | T2 DI COLGATE-PALERMO 001/018 RPR SPLW | ICW
LC | 121067690 | 013/081 | T2 DI STNSLS-MNTCA #2 013/081 RPL HRDT | VICTOR | ETL.3820.TOWR | 2021-05-10 | 2021-04-16 | 2022-02-02 | 2022-04-16 | 2022-04-16 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45122675 | T2 DI STNSLS-MNTCA #2 013/081 RPL HRDT | ICQ
LC | 121071484 | 009/168 | T2 DI COLGATE-PALERMO 9/168 RPR SPLW | SACTO | ETL.6500.INSL.NCER | 2021-05-10 | 2021-05-10 | 2022-05-17 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 44812188 | T2 DI COLGATE-PALERMO 9/168 RPR SPLW | ICW
LC | 121112837 | 006/045 | T2 DI EL DRDO-MSRI FT #2 6/45 RMV DEBRS | SACTO | ETL.1540.INSL | 2021-05-10 | 2021-04-19 | 2022-05-17 | 2022-04-19 | 2022-04-19 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Steel | Remove | 44812033 | T2 DI EL DRDO-MSRI FT #2 6/45 RMV DEBRS | ICS
LC | 121116450 | 021/098 | T2 DI MSS LNDNG-CBRN 021/098 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-05-10 | 2021-04-12 | 2022-05-17 | 2022-04-12 | 2022-04-12 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45121186 | T2 DI MSS LNDNG-CBRN 021/098 RPR FOND | ICQ
LC | 121129534 | 032/006 | T2 EI MEND-WILL-FT BRAGG 32/6 RPR SPLW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-10 | 2021-05-08 | 2022-05-16 | 2022-05-08 | 2022-05-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45148584 | T2 EI MEND-WILL-FT BRAGG 32/6 RPR SPLW | ICW
LC | 121130223 | 032/007 | T2 EI MEND-WILL-FT BRAGG 32/7 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-10 | 2021-05-08 | 2022-05-16 | 2022-05-08 | 2022-05-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148585 | T2 EI MEND-WILL-FT BRAGG 32/7 RPR GYWW | ICW
LC | 121130234 | 095/006 | T2 EI HUMBOLDT-TRINITY 95/6 BOND | EUREKA | ETL.1820.POLE.WDPS | 2021-05-10 | 2021-05-10 | 2022-03-23 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45149547 | T2 EI HUMBOLDT-TRINITY 95/6 BOND | ICW
LC | 121130236 | 033/000 | T2 EI MEND-WILL-FT BRAGG 33/0 RPR JUMP | WILLITS | ETL.7550.POLE.WOOD | 2021-05-10 | 2021-05-08 | 2022-10-02 | 2022-05-08 | 2022-05-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Jumper-Wood | Repair | 45148586 | T2 EI MEND-WILL-FT BRAGG 33/0 RPR JUMP | ICW
LC | 121130243 | 095/007 | T2 EI HUMBOLDT-TRNTY 95/7 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-05-10 | 2021-05-10 | 2022-03-31 | 2022-05-10 | 2022-05-10 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31554572 | T2 EI HUMBOLDT-TRNTY 95/7 RPL INSW | 93I
LC | 121186583 | 047/003 | T2 EI HUMBOLDT-TRINITY 47/3 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-11 | 2021-05-11 | 2022-06-03 | 2022-05-11 | 2022-05-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31540677 | T2 EI HUMBOLDT-TRINITY 47/03 RPL POLE | 70Y
LC | 121186584 | 008/047 | T2 EI STN-ML-RRBK JT 8/47 RPL INSS CMPLT | VICTOR | ETL.3840.INSL.NCER | 2021-05-11 | 2021-04-28 | 2022-05-13 | 2022-04-28 | 2022-04-28 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551877 | T2 DI STN MEL SW STA-RVRBK RPL INSS 3TW | 93K
LC | 121186770 | 027/015 | T2 DI CLAY-MARTEL 027/015 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-11 | 2021-05-10 | 2021-08-23 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44943377 | T2 DI CLAY-MARTEL 027/015 RPR STRW | ICW
LC | 121186820 | 020/414 | T2 DI COLGATE-PALERMO 20/414 STRW RPL | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-11 | 2021-05-10 | 2022-12-06 | 2022-05-10 | 2022-05-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31604323 | T2 EI CLGTE-PLRMO 017/353 RPL STRW | 70Y
LC | 121186985 | 037/005 | T2 EI MNDCN-WLLTS-FRT BRGG 37/5 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-11 | 2021-05-11 | 2022-05-14 | 2022-05-11 | 2022-05-11 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148608 | T2 EI MNDCN-WLLTS-FRT BRGG 37/5 RPR GYWW | ICW
LC | 121187031 | 037/006 | T2 EI MNDCN-WLLTS-FRT BRGG 37/6 GRND WSH | WILLITS | ETL.7550.POLE.WOOD | 2021-05-11 | 2021-05-11 | 2022-05-14 | 2022-05-11 | 2022-05-11 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Repair | 45193183 | T2 EI MNDCN-WLLTS-FRT BRGG 37/6 GRND WSH | ICW
LC | 121187052 | 016/304 | T2 DI FULTON-MLN-COTATI 16/304 REPL INSW | LAKEVLLE | ETL.6910.INSL.NCER | 2021-05-11 | 2021-05-08 | 2022-02-03 | 2022-05-08 | 2022-05-08 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31540579 | EI FLTN-MLINO-COTATI 1/17 RPL INSW | 93I
LC | 121187159 | 017/254 | T2 DI CLAY-MARTEL 17/254 RPR STRW | VICTOR | ETL.8250.POLE.NWOD | 2021-05-11 | 2021-05-10 | 2022-02-22 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45135006 | T2 DI CLAY-MARTEL 17/254 RPR STRW | ICW
LC | 121187367 | 029/010 | T2 DI CLAY-MARTEL 029/010 RPL POLE CMPLT | VICTOR | ETL.8250.POLE.WOOD | 2021-05-11 | 2021-05-10 | 2022-03-31 | 2022-05-10 | 2022-05-10 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535893 | T2 DI CLAY-MARTEL 27/21 REFRAME | 93E
LC | 121187408 | 030/007 | T2 DI CLAY-MARTEL 030/007 RPR SPLW | VICTOR | ETL.8250.INSL.NCER | 2021-05-11 | 2021-05-10 | 2022-04-01 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45135011 | T2 DI CLAY-MARTEL 030/007 RPR SPLW | ICW
LC | 121187463 | 037/001 | T2 EI MNDOCNO-WLTS-FRT BRG 37/1 REPL INS | WILLITS | ETL.7550.INSL.CERA | 2021-05-11 | 2021-05-11 | 2022-05-15 | 2022-05-11 | 2022-05-11 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31551283 | T2 DI MNDCN-WLTS-FRT BRG 28/10 RPL INSW | 93I
LC | 121187487 | 001/013 | T2 DI SLT SPRNGS-TGR CRK 1/13 RMV STEP | VICTOR | ETL.3500.TOWR | 2021-05-11 | 2021-04-20 | 2022-03-31 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45150412 | T2 DI SLT SPRNGS-TGR CRK 1/13 RMV STEP | ICQ
LC | 121187572 | 012/094 | T2 DI SLT SPRNGS-TGR CRK 12/94 RPL INSS | VICTOR | ETL.3500.INSL | 2021-05-11 | 2021-04-20 | 2022-06-25 | 2022-04-20 | 2022-04-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540431 | T2 EI SALT SPRNGS-TGR CREK RPL INSS 18TW | 93K
LC | 121187720 | 013/103 | T2 DI SLT SPRNGS-TGR CRK 13/103 RPR INSS | VICTOR | ETL.3500.INSL | 2021-05-11 | 2021-04-20 | 2022-06-27 | 2022-04-20 | 2022-04-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45155674 | T2 DI SLT SPRNGS-TGR CRK 13/103 RPR INSS | ICS
LC | 121187738 | 114/002 | T2 EI HUMBOLDT-BRIDGVLLE 114/2L RPR GYWW | EUREKA | ETL.1810.POLE.WDPS | 2021-05-11 | 2021-05-10 | 2022-09-02 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45155491 | T2 EI HMBLDT-BRDGVLLE 114/2L RPR GYWW | ICW
LC | 121187739 | 114/002 | T2 EI HUMBOLDT-BRIDGEVL 114/2L RPL ANCHW | EUREKA | ETL.1810.POLE.WDPS | 2021-05-11 | 2021-05-10 | 2022-09-02 | 2022-05-10 | 2022-05-10 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31540751 | T2 EI HMBLDT-BRDGVLLE 114/2 RPL ANCHW | 93E
LC | 121187743 | 114/002 | T2 EI HUMBOLDT-BRIDGEVL 114/2R RPR GYWW | EUREKA | ETL.1810.POLE.WDPS | 2021-05-11 | 2021-05-10 | 2022-09-02 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45155491 | T2 EI HMBLDT-BRDGVLLE 114/2L RPR GYWW | ICW
LC | 121187750 | 114/002 | T2 EI HMBLDT-BRDGVLLE 114/2 RMV VEG | EUREKA | ETL.1810.POLE.WDPS | 2021-05-11 | 2021-05-10 | 2022-03-18 | 2022-05-10 | 2022-05-10 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 121188001 | 110/000 | T2 EI HMBLDT-BRDGVLLE 110/0 RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-05-11 | 2021-05-11 | 2022-04-08 | 2022-05-11 | 2022-05-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31541449 | EI HUMBOLDT-BRIDGEVLLE 107/003 RPLC STRW | 70Y
LC | 121188025 | 027/170 | T2 EI TSLA-SLDO-MNTCA 27/170 RPL INSW | VICTOR | ETL.4000.INSL.NCER | 2021-05-11 | 2021-05-11 | 2022-02-03 | 2022-05-11 | 2022-05-11 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31580915 | T2 EI TSLA-SLDO-MNTCA 27/170 RPL INSW | 93I
LC | 121188142 | 109/006 | T2 EI HUMBOLDT-BRIDGEVILLE 109/6 RMV VEG | EUREKA | ETL.1810.POLE.WDPS | 2021-05-11 | 2021-05-10 | 2021-07-21 | 2022-05-10 | 2022-05-10 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 121188172 | 013/102 | T2 DI SLT SPRNGS-TGR CRK 13/102 RMV STEP | VICTOR | ETL.3500.TOWR | 2021-05-11 | 2021-04-20 | 2022-02-22 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45150413 | T2 DI SLT SPRNGS-TGR CRK 13/102 RMV STEP | ICQ
LC | 121188352 | 033/139 | T2 EI TESLA-METCALF 33/139 WASH INSS | METCALF | ETL.6110.TOWR | 2021-05-11 | 2021-05-11 | 2021-05-28 | 2022-05-11 | 2022-05-11 | On-time | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | Contaminated | Insulator | Ground Wash | 44825526 | T2 EI TESLA-METCALF 33/139 WASH INSS | ICD
LC | 121188358 | 032/213 | T2 DI POE-RIO OSO 32/213 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-05-11 | 2021-04-12 | 2022-02-03 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45145302 | T2 DI POE-RIO OSO 32/213 RPR FOND | ICQ
LC | 121188467 | 032/213 | T2 DI CRESTA-RIO OSO 32/213 RPL INSS | TABLEMTN | ETL.4590.INSL.CERA | 2021-05-11 | 2021-04-12 | 2022-05-09 | 2022-04-12 | 2022-04-12 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31600459 | T2 DI CRESTA-RIO OSO 32/213 RPL INSS | 93K
LC | 121188598 | 012/097 | T2 DI SLT SPRNGS-TGR CRK 12/97 RPL INSS | VICTOR | ETL.3500.INSL.NCER | 2021-05-11 | 2021-04-20 | 2022-06-25 | 2022-04-20 | 2022-04-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540431 | T2 EI SALT SPRNGS-TGR CREK RPL INSS 18TW | 93K
LC | 121189193 | 030/010 | T2 DI CLAY-MARTEL 30/10 RPL INSW | VICTOR | ETL.8250.INSL.CERA | 2021-05-11 | 2021-05-11 | 2022-03-30 | 2022-05-11 | 2022-05-11 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535892 | T2 EI CLAY-MARTEL 30/458 RPL INSW | 93I
LC | 121189438 | 021/297 | T2 DI CLAY-MARTEL 21/297 RPL SPLW | VICTOR | ETL.8250.INSL.CERA | 2021-05-11 | 2021-05-10 | 2022-07-13 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Replace | 45110663 | T2 DI CLAY-MARTEL 21/297 RPL SPLW | ICW
LC | 121190098 | 033/502 | T2 DI CLAY-MARTEL 33/502 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-11 | 2021-05-11 | 2022-02-17 | 2022-05-11 | 2022-05-11 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543355 | T2 DI CLAY-MARTEL 032/482 RPL STRW | 70Y
LC | 121190289 | :016/087 | T2 DI CZY HRS CNYN SLS :016/087 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2021-05-11 | 2021-04-20 | 2021-10-06 | 2022-04-20 | 2022-04-20 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44962408 | T2 DI CZY HRS CNYN SLS :016/087 RPL RPTS | ICB
LC | 121190380 | 035/009 | T2 EI MNDCN-WLLTS-FRT BRGG 35/9 RPL INSW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-11 | 2021-05-11 | 2022-05-15 | 2022-05-11 | 2022-05-11 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31600242 | T2 EI MNDCN-WLLTS-FRT BRGG 35/9 RPL INSW | 93I
LC | 121190436 | 018/075 | T2 EI TESLA-METCALF 018/075 REPULL | METCALF | ETL.6110.TOWR | 2021-05-11 | 2021-05-11 | 2022-07-07 | 2022-05-11 | 2022-05-11 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45233279 | T2 EI TESLA-METCALF 018/075 REPULL | ICS
LC | 121190537 | 045/331 | T2 EI CARIBOU-TABLE MTN 5/331 RMV VEG | TABLEMTN | ETL.4440.TOWR | 2021-05-11 | 2021-05-11 | 2022-08-08 | 2022-05-11 | 2022-05-11 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 121190546 | 048/343 | T2 EI CARIBOU-TABLE MTN 048/343 RPR STRT | TABLEMTN | ETL.4440.TOWR | 2021-05-11 | 2021-05-11 | 2022-06-24 | 2022-05-11 | 2022-05-11 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45107123 | T2 EI CARIBOU-TABLE MTN 048/343 RPR STRT | ICQ
LC | 121190579 | 094/008 | T2 EI HUMBOLDT-TRINITY 94/8R RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-11 | 2021-05-11 | 2022-03-22 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45160735 | T2 EI HUMBOLDT-TRINITY 94/8R RPR GYWW | ICW
LC | 121190586 | 028/006 | T2 DI CLAY-MARTEL 28/6 REFRAME | VICTOR | ETL.8250.POLE.WOOD | 2021-05-11 | 2021-05-11 | 2022-03-26 | 2022-05-11 | 2022-05-11 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31535893 | T2 DI CLAY-MARTEL 27/21 REFRAME | 93E
LC | 121190615 | 095/010 | T2 EI HUMBOLDT-TRINITY 95/10R RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-11 | 2021-05-11 | 2022-03-25 | 2022-05-11 | 2022-05-11 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 121190624 | 096/000 | T2 EI HUMBOLDT-TRINITY 96/000 RPR CRSW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-11 | 2021-05-11 | 2022-03-24 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45160747 | T2 EI HUMBOLDT-TRINITY 96/000 RPR CRSW | ICW
LC | 121190719 | 002/065 | T2 DI COLGATE-ALLEGHANY 002/065 RPL INSW | SACTO | ETL.6470.INSL.NCER | 2021-05-11 | 2021-05-11 | 2022-06-25 | 2022-05-11 | 2022-05-11 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31540537 | T2 DI COLGATE-ALLEGHANY 002/065 RPL INSW | 93I
LC | 121190962 | 030/002 | T2 DI CLAY-MARTEL 30/002 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-11 | 2021-05-11 | 2022-03-27 | 2022-05-11 | 2022-05-11 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543355 | T2 DI CLAY-MARTEL 032/482 RPL STRW | 70Y
LC | 121191108 | 016/097 | T2 DI STANISLAUS-MNTC #2 16/97 RPR CNDS | VICTOR | ETL.3820.INSL.CERA | 2021-05-11 | 2021-03-26 | 2021-12-09 | 2022-03-26 | 2022-03-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Conductor-Steel | Repair | 44977943 | T2 DI STANISLAUS-MNTC #2 16/97 RPR CNDS | ICS
LC | 121191146 | 027/021 | T2 DI CLAY-MARTEL 27/21 REFRAME | VICTOR | ETL.8250.POLE.WOOD | 2021-05-11 | 2021-05-11 | 2022-03-26 | 2022-05-11 | 2022-05-11 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31535893 | T2 DI CLAY-MARTEL 27/21 REFRAME | 93E
LC | 121191342 | 020/125 | T2 DI STNSLS-MLNS MNTC 20/125 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-05-11 | 2021-04-12 | 2022-02-22 | 2022-04-12 | 2022-04-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45123116 | T2 DI STNSLS-MLNS MNTC 20/125 RPR FOND | ICQ
LC | 121191393 | 006/052 | T2 DI PARADISE-TABLE MTN 6/52 RPR FOND | TABLEMTN | ETL.4316.TOWR | 2021-05-11 | 2021-04-16 | 2022-06-16 | 2022-04-16 | 2022-04-16 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195442 | T2 DI PARADISE-TABLE MTN 6/52 RPR FOND | ICQ
LC | 121191538 | 020/289 | T2 DI CLAY-MARTEL 020/289 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-11 | 2021-05-11 | 2022-07-14 | 2022-05-11 | 2022-05-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543443 | T2 DI CLAY-MARTEL 18/266 RPL STRW | 70Y
LC | 121191549 | 094/009B | T2 EI HUMBOLDT-TRINITY 094/9B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2021-05-11 | 2021-05-11 | 2022-03-22 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45160737 | T2 EI HUMBOLDT-TRINITY_094/09A RPR GYWW | ICS
LC | 121191550 | 030/131 | T2 DI MR BY-SLR SW ST #2 30/131 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-05-11 | 2021-04-20 | 2022-07-26 | 2022-04-20 | 2022-04-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549068 | T2 DI MR BY-SLR SW ST #2 RPL INSS 7TWRS | 93K
LC | 121191556 | 000/006 | T2 DI KNGS RVR-SNGR-RDLY 0/6 RPL STRW | FRESNO | ETL.2030.INSL.CERA | 2021-05-11 | 2021-04-20 | 2022-04-13 | 2022-04-20 | 2022-04-20 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31588482 | T2 DI KNGS RVR-SNGR-RDLY 0/6 RPL STRW | 70Y
LC | 121191580 | 094/009C | T2 EI HUMBOLDT-TRINITY_094/09C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2021-05-11 | 2021-05-11 | 2022-03-22 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45160737 | T2 EI HUMBOLDT-TRINITY_094/09A RPR GYWW | ICS
LC | 121191581 | 094/009A | T2 EI HUMBOLDT-TRINITY_094/09A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2021-05-11 | 2021-05-11 | 2022-03-22 | 2022-05-11 | 2022-05-11 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45160737 | T2 EI HUMBOLDT-TRINITY_094/09A RPR GYWW | ICS
LC | 121191583 | 096/001 | T2 EI HUMBOLDT-TRINITY 96/1 BOND HRDW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-11 | 2021-05-11 | 2022-03-22 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45160748 | T2 EI HUMBOLDT-TRINITY 96/1 BOND HRDW | ICW
LC | 121191632 | :016/086 | T2 DI CZY HRS CNYN SS :16/086 RPR RAPTOR | MOSSLNDG | ETL.2900.TOWR | 2021-05-11 | 2021-04-20 | 2021-10-06 | 2022-04-20 | 2022-04-20 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44962409 | T2 DI CZY HRS CNYN SS :16/086 RPR RAPTOR | ICB
LC | 121191635 | C020/081 | T2 DI MOSS LANDING-COBRN C20/81 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-05-11 | 2021-04-20 | 2022-03-16 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45121187 | T2 DI MOSS LANDING-COBRN C20/81 RPR FOND | ICQ
LC | 121191905 | C016/067 | T2 DI MOSS LANDING-CBURN C16/67 RPL INSS | MOSSLNDG | ETL.5330.INSL | 2021-05-11 | 2021-04-21 | 2022-08-03 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31550478 | DI MOSS LANDING-COBURN RPL INSS 6TWR | 93K
LC | 121191927 | 015/112A | T2 DI HELMS-GREGG #1 015/112A RPL INSS | FRESNO | ETL.4870.INSL | 2021-05-11 | 2021-04-20 | 2022-08-24 | 2022-04-20 | 2022-04-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE SPCR COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533801 | T2 DI HELMS-GREGG #1 RPLC INSS 9 TWRS | 93K
LC | 121191945 | 037/265 | T2 DI MIDDLE FRK-GLD HL 37/265 RPLC INSS | SACTO | ETL.5140.INSL | 2021-05-11 | 2021-04-01 | 2022-10-29 | 2022-04-01 | 2022-04-01 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514338 | T3 DI MDDL FRK-GLD HLL RPL INSS 6TWRS | 93K
LC | 121192003 | 020/004 | T2 DI TULE-SPRINGVILLE 020/004 RMV VEG | MIDWAY | ETL.9040.POLE.WOOD | 2021-05-11 | 2021-04-21 | 2022-04-18 | 2022-04-21 | 2022-04-21 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121192007 | 037/245 | T2 DI POE-RIO OSO 037/245 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-05-11 | 2021-04-20 | 2022-01-04 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45106497 | T2 DI POE-RIO OSO 037/245 RPR FOND | ICQ
LC | 121192009 | 053/378 | T2 DI CRBU-TBL MTN 053/378 RPL INSS | TABLEMTN | ETL.4440.INSL | 2021-05-11 | 2021-04-13 | 2022-06-17 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31606372 | T2 DI CRBU-TBL MTN 053/378 RPL INSS | 93K
LC | 121192088 | 011/089 | T2 DI SLT SPGS-TGR CK 11/89 RMV HRDT | VICTOR | ETL.3500.TOWR | 2021-05-11 | 2021-04-20 | 2022-03-29 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45150389 | T2 DI SLT SPGS-TGR CK 11/89 RMV HRDT | ICQ
LC | 121192124 | 014/082 | T2 DI STNSLS MNTCA #2 14/82 INS HRDT | VICTOR | ETL.3820.TOWR | 2021-05-11 | 2021-04-16 | 2022-02-02 | 2022-04-16 | 2022-04-16 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45122677 | T2 DI STNSLS MNTCA #2 14/82 INS HRDT | ICQ
LC | 121192148 | 003/026 | T2 DI MRGA-OAKLND #1 003/026 RPL INSS | CONCORD | ETL.2720.INSL | 2021-05-11 | 2021-04-21 | 2022-06-30 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547461 | T2 DI MORAGA-OAKLAND #1 RPLC INSS 5TWRS | 93K
LC | 121192149 | 003/026 | T2 DI MRGA-OAKLND #2 3/26 RPL INSS | CONCORD | ETL.2730.INSL | 2021-05-11 | 2021-04-21 | 2022-03-24 | 2022-04-21 | 2022-04-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547465 | T2 DI MORAGA-OAKLAND #2 RPLC INSS 5TWRS | 93K
LC | 121316059 | 004/075 | T2 DI CENTRVL-TBL MTN 4/75 REPL POLE | TABLEMTN | ETL.6320.POLE.WOOD | 2021-05-12 | 2021-05-10 | 2022-04-27 | 2022-05-10 | 2022-05-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535168 | T2 EI CTRVL-TBL MTN 006/105 RPL STRW | 70Y
LC | 121316252 | 004/068 | T2 DI CENTERVILLE-TABLE MTN 4/68 RPR SPL | TABLEMTN | ETL.6320.INSL.NCER | 2021-05-12 | 2021-05-10 | 2022-04-25 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45197506 | T2 DI CENTERVILLE-TABLE MTN 4/68 RPR SPL | ICW
LC | 121316970 | 110/000 | T2 EI HMBLDT-BRDGVLLE 110/0 RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-05-12 | 2021-05-10 | 2022-04-08 | 2022-05-10 | 2022-05-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31541449 | EI HUMBOLDT-BRIDGEVLLE 107/003 RPLC STRW | 70Y
LC | 121317005 | 023/006 | T2 EI MNDCN-WLTS-FRT BRG 23/6C RPL POLE | WILLITS | ETL.7550.POLE.WDPS | 2021-05-12 | 2021-05-03 | 2022-09-30 | 2022-05-03 | 2022-05-03 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO SR22 | Rotten | Structure-Wood | Replace | 31547473 | T2 EI MNDCN-WLTS-FRT BRG 23/6R RPL POLE | 70Y
LC | 121317174 | 023/331 | T2 DI CLAY-MARTEL 23/331 RMV VEGN | VICTOR | ETL.8250.POLE.WOOD | 2021-05-12 | 2021-05-11 | 2022-05-23 | 2022-05-11 | 2022-05-11 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121317961 | 024/163 | T2 DI POE-RIO OSO 24/163 RPL HRDT | TABLEMTN | ETL.5540.TOWR | 2021-05-12 | 2021-04-15 | 2022-05-25 | 2022-04-15 | 2022-04-15 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45198329 | T2 DI POE-RIO OSO 24/163 RPL HRDT | ICQ
LC | 121317971 | 036/209 | T2 DI TMBLR-SN LS OBSP 36/209 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-05-12 | 2021-04-20 | 2022-04-24 | 2022-04-20 | 2022-04-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549402 | TEMBLOR–SN LS OBSP RPLC INSS 6TWRS | 93K
LC | 121317974 | :016/083 | T2 DI CRZY HRS CN-SLS-SD :16/83 RPL ZENA | MOSSLNDG | ETL.2900.TOWR | 2021-05-12 | 2021-04-20 | 2021-10-05 | 2022-04-20 | 2022-04-20 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44961519 | T2 DI CRZY HRS CN-SLS-SD :16/83 RPL ZENA | ICB
LC | 121318133 | 009/075 | T2 DI SLT SPRNGS-TGR CRK 9/75 RPL INSS | VICTOR | ETL.3500.INSL | 2021-05-12 | 2021-04-20 | 2022-06-23 | 2022-04-20 | 2022-04-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31614573 | T2 DI SLT SPRNGS-TGR CRK 9/75 RPL INSS | 93K
LC | 121318136 | 009/075 | T2 DI SLT SPRNGS-TGR CRK 9/75 RMV STEPS | VICTOR | ETL.3500.TOWR | 2021-05-12 | 2021-04-20 | 2022-03-21 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45150414 | T2 DI SLT SPRNGS-TGR CRK 9/75 RMV STEPS | ICQ
LC | 121318320 | 017/248 | T2 DI SISQUOC-SANTA YNEZ 17/248 RPR SPLW | PISMOBCH | ETL.3700.INSL.NCER | 2021-05-12 | 2021-04-27 | 2022-06-27 | 2022-04-27 | 2022-04-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45069327 | T2 DI SISQUOC-SANTA YNEZ 17/248 RPR SPLW | ICW
LC | 121318620 | :015/094 | T2 DI MORGAN HILL-LLAGAS 15/94 RPL INSS | MOSSLNDG | ETL.2800.INSL.CERA | 2021-05-12 | 2021-04-28 | 2022-06-20 | 2022-04-28 | 2022-04-28 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535376 | T2 DI GREEN VLY-LLAGAS RPLC INSS 3TWRS | 93K
LC | 121318624 | 033/509 | T2 EI CLAY-MARTEL 33/509 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-12 | 2021-04-12 | 2022-02-15 | 2022-04-12 | 2022-04-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543355 | T2 DI CLAY-MARTEL 032/482 RPL STRW | 70Y
LC | 121318755 | 016/005 | T2 EI MNDCNO-WLTS-FRT BRG 16/5 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-12 | 2021-05-12 | 2022-08-19 | 2022-05-12 | 2022-05-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31537422 | T2 EI MNDCNO-WLTS-FRT BRGG 15/5 REPL PL | 70Y
LC | 121318797 | 006/050 | T2 EI PIT #1-COTTONWOOD 006/050 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-05-12 | 2021-05-12 | 2022-02-17 | 2022-05-12 | 2022-05-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | Anti-Climbing Guard | Structure-Tower | Repair | 45149337 | T2 EI PIT #1-COTTONWOOD 006/050 RPR STRT | ICQ
LC | 121318798 | 006/050 | T2 EI PIT #1-COTTONWOOD 006/050 RPL HRDS | TABLEMTN | ETL.5390.TOWR | 2021-05-12 | 2021-05-12 | 2022-02-17 | 2022-05-12 | 2022-05-12 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Hardware-Steel | Replace | 45166842 | T2 EI PIT #1-COTTONWOOD 006/050 RPL HRDS | ICS
LC | 121318840 | 005/027 | T2 DI MORRO BAY-MESA 5/27 RPLC INSS | PISMOBCH | ETL.5290.INSL | 2021-05-12 | 2021-04-29 | 2022-06-22 | 2022-04-29 | 2022-04-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534504 | T2 EI MORRO BAY-MESA RPL INSLS 5TWRS | 93K
LC | 121319063 | 041/268 | T2 DI POE-RIO OSO 041/268 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-05-12 | 2021-04-21 | 2022-01-11 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45106672 | T2 DI POE-RIO OSO 041/268 RPR FOND | ICQ
LC | 121319064 | 041/268 | T2 DI POE-RIO OSO 041/268 INS HRDT | TABLEMTN | ETL.5540.TOWR | 2021-05-12 | 2021-04-21 | 2022-01-11 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45099114 | T2 DI POE-RIO OSO 041/268 INS HRDT | ICQ
LC | 121319133 | 014/133 | WV T2 BRDGVILL-CTTNWD 14/133 RPL HRDW | TABLEMTN | ETL.1110.POLE.WDPS | 2021-05-12 | 2021-05-12 | 2022-06-18 | 2022-05-12 | 2022-05-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45211798 | WV T2 BRDGVILL-CTTNWD 14/133 RPL HRDW | ICW
LC | 121319587 | C018/071 | T2 DI MOSS LDNG-COBURN C18/71 INS HRDT | MOSSLNDG | ETL.5330.TOWR | 2021-05-12 | 2021-04-21 | 2022-03-16 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45121188 | T2 DI MOSS LDNG-COBURN C18/71 INS HRDT | ICQ
LC | 121319718 | 016/132 | T2 EI PIT #1-COTTONWOOD 16/132 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-05-12 | 2021-05-12 | 2022-07-21 | 2022-05-12 | 2022-05-12 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45198308 | T2 EI PIT #1-COTTONWOOD 16/132 RPR STRT | ICQ
LC | 121319826 | 011/091 | T2 DI SLT SPRNGS-TGR CRK 11/91 RMV HRDT | VICTOR | ETL.3500.TOWR | 2021-05-12 | 2021-04-20 | 2022-03-29 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45150415 | T2 DI SLT SPRNGS-TGR CRK 11/91 RMV HRDT | ICQ
LC | 121319925 | 015/119 | T2 EI PIT #1-COTTONWOOD 015/119 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-05-12 | 2021-05-12 | 2022-07-20 | 2022-05-12 | 2022-05-12 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45181120 | T2 EI PIT #1-COTTONWOOD 015/119 RPR STRT | ICQ
LC | 121320127 | 057/001 | T2 EI HUMBOLDT-TRINITY 057/001R RPR BOND | EUREKA | ETL.1820.POLE.WDPS | 2021-05-12 | 2021-05-12 | 2022-05-29 | 2022-05-12 | 2022-05-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | Missing | Hardware-Wood | Install | 45145097 | T2 EI HUMBOLDT-TRINITY 057/001 RPR BOND | ICW
LC | 121320135 | 057/001 | T2 EI HUMBOLDT-TRINITY 057/001L RPR BOND | EUREKA | ETL.1820.POLE.WDPS | 2021-05-12 | 2021-05-12 | 2022-05-29 | 2022-05-12 | 2022-05-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | Missing | Hardware-Wood | Install | 45145097 | T2 EI HUMBOLDT-TRINITY 057/001 RPR BOND | ICW
LC | 121320316 | 007/135 | T2 DI COLGT-PLRMO 7/135 RPL POLE CMPLTD | SACTO | ETL.6500.POLE.WOOD | 2021-05-12 | 2021-05-10 | 2022-05-14 | 2022-05-10 | 2022-05-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540562 | T2 DI COLGATE-PALERMO 7/135 RPLC STRW | 70Y
LC | 121320390 | 025/217 | WV T2 BRDGVILL-CTTNWD 25/217 INS DAMW | TABLEMTN | ETL.1110.INSL.NCER | 2021-05-12 | 2021-05-12 | 2022-06-23 | 2022-05-12 | 2022-05-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 45211784 | WV T2 BRDGVILL-CTTNWD 25/217 INS DAMW | ICW
LC | 121320631 | 019/003 | T2 DI TULE-SPRINGVILLE 19/3 RPR STRW | MIDWAY | ETL.9040.POLE.WOOD | 2021-05-12 | 2021-04-21 | 2022-06-07 | 2022-04-21 | 2022-04-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45068043 | T2 DI TULE-SPRINGVILLE 19/3 RPR STRW | ICW
LC | 121321287 | :005/033 | T2 EI STNSLS-MLS SS-MTC #1 :5/33 RMV DBR | VICTOR | ETL.3830.TOWR | 2021-05-12 | 2021-05-01 | 2021-10-04 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44962484 | T2 EI STNSLS-MLS SS-MTC #1 :5/33 RMV DBR | ICS
LC | 121321444 | :003/021 | T2 EI STNSLS-MLS SS-MTC #1 :3/21 RMV DBR | VICTOR | ETL.3830.TOWR | 2021-05-12 | 2021-05-01 | 2021-09-25 | 2022-05-01 | 2022-05-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44962482 | T2 EI STNSLS-MLS SS-MTC #1 :3/21 RMV DBR | ICS
LC | 121322000 | 093/010 | T2 EI HUMBOLDT-TRINITY 93/10L RPR PL | EUREKA | ETL.1820.POLE.WDPS | 2021-05-12 | 2021-05-12 | 2022-03-23 | 2022-05-12 | 2022-05-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45160730 | T2 EI HUMBOLDT-TRINITY 93/10L RPR PL | ICW
LC | 121322009 | 093/010 | T2 EI HUMBOLDT-TRINITY 93/10R RPR PL | EUREKA | ETL.1820.POLE.WDPS | 2021-05-12 | 2021-05-12 | 2022-03-23 | 2022-05-12 | 2022-05-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45160730 | T2 EI HUMBOLDT-TRINITY 93/10L RPR PL | ICW
LC | 121322096 | 014/309 | T2 WV VOLTA-DESCHUTES 14/309 INST DAMP | TABLEMTN | ETL.8290.POLE.NWOD | 2021-05-12 | 2021-05-12 | 2022-06-16 | 2022-05-12 | 2022-05-12 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install | 45212355 | T2 WV VOLTA-DESCHUTES 14/309 INST DAMP | ICS
LC | 121322149 | 014/081 | T2 DI HAAS-MC CALL 014/081 RPL INSS | FRESNO | ETL.4850.INSL | 2021-05-12 | 2021-04-21 | 2022-03-08 | 2022-04-21 | 2022-04-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 31541676 | T2 DI HAAS-MCCALL 11/68 RPLC INSS | 93K
LC | 121322238 | 055/003 | T2 EI HUMBOLDT-TRINITY 55/003 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-12 | 2021-05-12 | 2022-03-29 | 2022-05-12 | 2022-05-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145291 | T2 EI HUMBOLDT-TRINITY 55/003 RPR GYWW | ICW
LC | 121322239 | 055/003 | T2 EI HUMBOLDT-TRINITY 55/003 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-12 | 2021-05-12 | 2022-03-29 | 2022-05-12 | 2022-05-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145291 | T2 EI HUMBOLDT-TRINITY 55/003 RPR GYWW | ICW
LC | 121322255 | 028/241 | WV T2 BRDGVILL-CTTNWD 28/241 COMPLETE | TABLEMTN | ETL.1110.POLE.STPS | 2021-05-12 | 2021-05-12 | 2022-06-22 | 2022-05-12 | 2022-05-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Wood | Install | 45223807 | WV T2 BRDGVILL-CTTNWD 28/241 INS DAMW | ICW
LC | 121322353 | 055/003 | T2 EI HUMBOLDT-TRINITY 55/003 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-12 | 2021-05-12 | 2022-03-29 | 2022-05-12 | 2022-05-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44958546 | T2 EI HUMBOLDT-TRINITY 55/003 RPR GYWW | ICW
LC | 121322354 | 055/003 | T2 EI HUMBLDT-TRINTY 55/3 COMPLETE | EUREKA | ETL.1820.POLE.WDPS | 2021-05-12 | 2021-05-12 | 2022-05-11 | 2022-05-12 | 2022-05-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Structure-Wood | Repair | 44958546 | T2 EI HUMBOLDT-TRINITY 55/003 RPR GYWW | ICW
LC | 121322505 | 037/218 | T2 DI TMBLR-SLO 037/218 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-05-12 | 2021-04-21 | 2022-04-25 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549402 | TEMBLOR–SN LS OBSP RPLC INSS 6TWRS | 93K
LC | 121322651 | 011/057 | T2 DI MSS LNDNG-CBRN 011/057 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-05-12 | 2021-04-21 | 2022-05-17 | 2022-04-21 | 2022-04-21 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45121189 | T2 DI MSS LNDNG-CBRN 011/057 RPR FOND | ICQ
LC | 121322657 | 003/029 | T2 DI MRGA-OAKLND #4 003/029 RPL INSS | CONCORD | ETL.2750.INSL.NCER | 2021-05-12 | 2021-04-21 | 2022-07-10 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547719 | DI MORAGA-OAKLAND #4 RPL INSS 5TWRS | 93K
LC | 121322660 | 037/247 | T2 DI POE-RIO OSO 037/247 RPL INSS | TABLEMTN | ETL.5540.INSL.CERA | 2021-05-12 | 2021-04-21 | 2022-08-11 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546766 | T2 DI POE-RIO OSO RPL INSS 7 TWRS | 93K
LC | 121322721 | 031/206 | T2 DI POE-RIO OSO 031/206 RMV VEG | TABLEMTN | ETL.5540.TOWR | 2021-05-12 | 2021-04-13 | 2022-01-25 | 2022-04-13 | 2022-04-13 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121322726 | 031/209 | T2 DI POE-RIO OSO 031/209 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-05-12 | 2021-04-13 | 2022-02-03 | 2022-04-13 | 2022-04-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45145300 | T2 DI POE-RIO OSO 031/209 RPR FOND | ICQ
LC | 121322728 | 031/209 | T2 DI POE-RIO OSO 031/209 RPL INSS | TABLEMTN | ETL.5540.INSL.CERA | 2021-05-12 | 2021-04-13 | 2022-08-11 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619906 | T2 DI POE-RIO OSO 031/209 RPL INSS | 93K
LC | 121322770 | 011/055 | T2 DI MSS LNDNG-CBRN 011/055 RPR SHLS | MOSSLNDG | ETL.5330.TOWR | 2021-05-12 | 2021-04-21 | 2021-10-14 | 2022-04-21 | 2022-04-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44981668 | T2 DI MSS LNDNG-CBRN 011/055 RPR SHLS | ICS
LC | 121322779 | 028/426 | T2 DI CLAY-MARTEL 028/426 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-12 | 2021-05-10 | 2022-01-28 | 2022-05-10 | 2022-05-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543390 | DI CLAY-MARTEL 026/367 RPL STRW | 70Y
LC | 121322844 | 012/100 | T2 DI PARADISE-TBLE MTN 012/100 RPR FOND | TABLEMTN | ETL.4316.TOWR | 2021-05-12 | 2021-04-21 | 2022-05-25 | 2022-04-21 | 2022-04-21 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195443 | T2 DI PARADISE-TBLE MTN 012/100 RPR FOND | ICQ
LC | 121322941 | C013/053 | T2 DI CBRN-LS AGLS SS C013/053 RPL INSS | MOSSLNDG | ETL.4460.INSL | 2021-05-12 | 2021-04-22 | 2021-11-17 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31527944 | DI CBN-LS AGLS SW ST-PCH RPL INSS 13TWRS | 93K
LC | 121322942 | 006/048 | T2 DI BRUNSWICK #1 TAP 6/48 RMV DBRS | SACTO | ETL.1422.TOWR | 2021-05-12 | 2021-04-22 | 2022-02-16 | 2022-04-22 | 2022-04-22 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44812022 | T2 DI BRUNSWICK #1 TAP 6/48 RMV DBRS | ICS
LC | 121322972 | 027/164 | T2 DI TMBLR-SN LS OBSP 27/164 RPR STRT | PISMOBCH | ETL.3960.TOWR | 2021-05-12 | 2021-04-21 | 2022-06-23 | 2022-04-21 | 2022-04-21 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45077893 | T2 DI TMBLR-SN LS OBSP 27/164 RPR STRT | ICQ
LC | 121324200 | 020/003 | T2 DI TULE-SPRINGVILLE 20/3 RPL STRW | MIDWAY | ETL.9040.POLE.WOOD | 2021-05-13 | 2021-04-21 | 2022-07-26 | 2022-04-21 | 2022-04-21 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536427 | T2 EI TULE-SPRINGVILL 18/22 REPL POLE | 70Y
LC | 121324237 | 003/031 | T2 EI MORAGA-OAKLAND #4 3/31 RPL INSS | CONCORD | ETL.2750.INSL.NCER | 2021-05-13 | 2021-05-05 | 2022-07-09 | 2022-05-05 | 2022-05-05 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547719 | DI MORAGA-OAKLAND #4 RPL INSS 5TWRS | 93K
LC | 121324322 | 003/027 | T2 EI MORAGA-OAKLAND #2 3/27 RPL INSS | CONCORD | ETL.2730.INSL | 2021-05-13 | 2021-05-05 | 2022-03-23 | 2022-05-05 | 2022-05-05 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547465 | T2 DI MORAGA-OAKLAND #2 RPLC INSS 5TWRS | 93K
LC | 121324551 | 057/004 | T2 EI HUMBOLDT-TRINITY 57/4L RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2021-05-13 | 2021-05-13 | 2022-06-08 | 2022-05-13 | 2022-05-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145278 | T2 EI HUMBOLDT-TRINITY 57/4L RPR GYWW | ICW
LC | 121325216 | 033/245 | T2 DI CARIBOU-TABLE MTN 33/245 REPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-05-13 | 2021-05-12 | 2022-06-20 | 2022-05-12 | 2022-05-12 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121326113 | 005/060 | WV T2 PRDISE-TABLE MNTN 5/60 INS DMPS | TABLEMTN | ETL.4316.INSL.NCER | 2021-05-13 | 2021-05-05 | 2022-02-24 | 2022-05-05 | 2022-05-05 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install | 45196972 | WV T2 PRDISE-TABLE MNTN 5/60 INS DMPS | ICS
LC | 121326135 | 004/046 | WV T2 PARADISE-TABLE MTN 4/46 INS DMPS | TABLEMTN | ETL.4316.INSL.NCER | 2021-05-13 | 2021-05-05 | 2022-02-24 | 2022-05-05 | 2022-05-05 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install | 45196970 | WV T2 PARADISE-TABLE MTN 4/46 INS DMPS | ICS
LC | 121326473 | 001/010 | T2 DI PALERMO-NICOLAUS 1/10 INS HRDT | SACTO | ETL.3210.TOWR | 2021-05-13 | 2021-04-21 | 2021-12-27 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45074252 | T2 DI PALERMO-NICOLAUS 1/10 INS HRDT | ICQ
LC | 121326477 | 003/027 | T2 DI MORAGA-OAKLAND #4 3/27 RPLC INSS | CONCORD | ETL.2750.INSL.NCER | 2021-05-13 | 2021-04-21 | 2022-07-09 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547719 | DI MORAGA-OAKLAND #4 RPL INSS 5TWRS | 93K
LC | 121326565 | 009/158 | T2 WV TEJON-LEBEC 9/158 INS DAMS | MIDWAY | ETL.9250.POLE.NWOD | 2021-05-13 | 2021-05-13 | 2021-08-12 | 2022-05-13 | 2022-05-13 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Steel | Install | 44806393 | T2 EI TEJON-LEBEC 9/158 INS DAMS | ICS
LC | 121326572 | 003/027 | T2 DI MORAGA-OAKLAND #3 3/27 RPR FOND | CONCORD | ETL.2740.TOWR | 2021-05-13 | 2021-04-21 | 2022-02-09 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45167874 | T2 DI MORAGA-OAKLAND #3 3/27 RPR FOND | ICQ
LC | 121326576 | 004/036 | T2 DI SALT SPRNGS-TGR CRK 4/36 RPR STRT | VICTOR | ETL.3500.TOWR | 2021-05-13 | 2021-04-21 | 2022-03-30 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45150416 | T2 DI SALT SPRNGS-TGR CRK 4/36 RPR STRT | ICQ
LC | 121327003 | 020/138 | T2 DI HELMS-GREGG #1 20/138 RPR CONS | FRESNO | ETL.4870.TOWR | 2021-05-13 | 2021-04-22 | 2022-08-22 | 2022-04-22 | 2022-04-22 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45069453 | T2 DI HELMS-GREGG #1 20/138 RPR CONS | ICS
LC | 121327704 | 004/039 | T2 DI SLT SPRNGS-TGR CRK 4/39 RPR INSS | VICTOR | ETL.3500.INSL | 2021-05-13 | 2021-04-22 | 2022-06-21 | 2022-04-22 | 2022-04-22 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45155676 | T2 DI SLT SPRNGS-TGR CRK 4/39 RPR INSS | ICS
LC | 121328039 | 058/002 | T2 EI HUMBOLDT-TRINITY 58/2 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-05-13 | 2021-05-13 | 2022-10-19 | 2022-05-13 | 2022-05-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546221 | T2 DI HUMBOLDT-TRINITY RPL INSS 2TWRS | 93K
LC | 121328100 | 055/001 | T2 EI HUMBOLDT-TRINITY 055/001 RPR WDPK | EUREKA | ETL.1820.POLE.WDPS | 2021-05-13 | 2021-05-13 | 2022-03-29 | 2022-05-13 | 2022-05-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Structure-Wood | Remove | 45145290 | T2 EI HUMBOLDT-TRINITY 055/001 RPR WDPK | ICW
LC | 121328213 | 018/123 | T2 DI HELMS-GREGG #2 18/123 RPL INSS | FRESNO | ETL.4880.INSL | 2021-05-13 | 2021-04-21 | 2022-08-04 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514720 | HELMS-GREGG #2 REP INS 8TWRS | 93K
LC | 121328524 | 012/109 | T2 DI ELDRD-MSR FLT #1 12/109 INS HRDS | SACTO | ETL.1530.POLE.NWOD | 2021-05-13 | 2021-04-13 | 2022-05-28 | 2022-04-13 | 2022-04-13 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Steel | Install | 44812035 | T2 DI ELDRD-MSR FLT #1 12/109 INS HRDS | ICS
LC | 121328784 | 040/174 | T2 DI FULTON-LAKEVILLE 040/174 RMV NEST | LAKEVLLE | ETL.4950.TOWR | 2021-05-13 | 2021-04-13 | 2022-06-24 | 2022-04-13 | 2022-04-13 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45144137 | T2 DI FULTON-LAKEVILLE 040/174 RMV DEBRI | ICS
LC | 121328919 | 003/028 | T2 DI MORAGA-OAKLAND #1 3/28 RPL HRDT | CONCORD | ETL.2720.TOWR | 2021-05-13 | 2021-04-21 | 2022-01-25 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45149185 | T2 DI MORAGA-OAKLAND #1 3/28 RPL HRDT | ICQ
LC | 121329008 | 021/142 | T2 DI HELMS-GREGG #1 21/142 RPLC SHLS | FRESNO | ETL.4870.TOWR | 2021-05-13 | 2021-04-21 | 2022-07-20 | 2022-04-21 | 2022-04-21 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 45069454 | T2 DI HELMS-GREGG #1 21/142 RPLC SHLS | ICS
LC | 121329012 | 038/249 | T2 DI POE-RIO OSO 38/249 INS HRDT | TABLEMTN | ETL.5540.TOWR | 2021-05-13 | 2021-04-21 | 2021-12-28 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45099111 | T2 DI POE-RIO OSO 38/249 INS HRDT | ICQ
LC | 121329015 | 038/249 | T2 DI POE-RIO OSO 38/249 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-05-13 | 2021-04-21 | 2022-01-05 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45106499 | T2 DI POE-RIO OSO 38/249 RPR FOND | ICQ
LC | 121329054 | 004/041 | T2 DI SLT SPRNGS-TGR CRK 4/41 RMV HRDT | VICTOR | ETL.3500.TOWR | 2021-05-13 | 2021-04-21 | 2022-03-30 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45150417 | T2 DI SLT SPRNGS-TGR CRK 4/41 RMV HRDT | ICQ
LC | 121329122 | 040/230 | T2 DI TMBLR-SN LS OBSP 40/230 RMV STEP | PISMOBCH | ETL.3960.TOWR | 2021-05-13 | 2021-04-21 | 2022-06-24 | 2022-04-21 | 2022-04-21 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45077894 | T2 DI TMBLR-SN LS OBSP 40/230 RMV STEP | ICQ
LC | 121329124 | 030/177 | T2 DI TMBLR-SN LS OBSP 30/177 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-05-13 | 2021-04-21 | 2022-04-20 | 2022-04-21 | 2022-04-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546830 | T2 DI TEMBLOR-SLO- RPL INSS 6TWRS | 93K
LC | 121329125 | 007/012 | T2 DI SALINAS-FORT ORD #2 7/12 RMV NEST | MOSSLNDG | ETL.8423.POLE.NWOD | 2021-05-13 | 2021-04-22 | 2022-04-19 | 2022-04-22 | 2022-04-22 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45122745 | T2 DI SALINAS-FORT ORD #2 7/12 RMV NEST | ICS
LC | 121329239 | 050/358 | T2 DI CRBU-TBLE MTN 050/358 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-05-13 | 2021-04-13 | 2022-06-16 | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121329494 | 093/001 | T2 EI HUMBOLDT-TRINITY 93/1 RPL IBWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-13 | 2021-05-13 | 2022-06-09 | 2022-05-13 | 2022-05-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45160724 | T2 EI HUMBOLDT-TRINITY 93/1 RPL IBWW | ICW
LC | 121329495 | 093/001 | T2 EI HUMBOLDT-TRINITY 93/1R CMPLTED | EUREKA | ETL.1820.POLE.WDPS | 2021-05-13 | 2021-05-13 | 2022-06-09 | 2022-05-13 | 2022-05-13 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542141 | T2 EI HUMBOLDT-TRINITY 91/3 RPL INSW | 93I
LC | 121329517 | 015/113 | T2 DI HELMS-GREGG #2 015/113 RPL INSS | FRESNO | ETL.4880.INSL | 2021-05-13 | 2021-04-20 | 2022-08-04 | 2022-04-20 | 2022-04-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE SPCR COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514720 | HELMS-GREGG #2 REP INS 8TWRS | 93K
LC | 121329568 | 092/005 | T2 EI HUMBOLDT-TRINITY 92/5 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-13 | 2021-05-13 | 2022-06-07 | 2022-05-13 | 2022-05-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121329595 | 004/032 | T2 DI EL DRDO-MSRI FT #1 4/32 RPR INSS | SACTO | ETL.1530.INSL | 2021-05-13 | 2021-04-20 | 2022-06-17 | 2022-04-20 | 2022-04-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44812028 | T2 DI EL DRDO-MSRI FT #1 4/32 RPR INSS | ICS
LC | 121329620 | 093/002 | T2 EI HUMBOLDT-TRINITY 93/2 RPL INSS | EUREKA | ETL.1820.INSL.NCER | 2021-05-13 | 2021-05-13 | 2022-06-03 | 2022-05-13 | 2022-05-13 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31591949 | T2 EI HUMBOLDT-TRINITY 93/2 RPL INSS | 93I
LC | 121329703 | 004/032 | T2 DI EL DD-MSRFT #2 4/32 RPR INSS CMPLT | SACTO | ETL.1540.INSL | 2021-05-13 | 2021-04-20 | 2022-05-17 | 2022-04-20 | 2022-04-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44812029 | T2 DI EL DRDO-MSRI FT #2 004/32 RPR INSS | ICS
LC | 121329810 | :023/120 | T2 DI CRZY HRS CYN-SNS :023/120 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2021-05-13 | 2021-04-20 | 2021-10-07 | 2022-04-20 | 2022-04-20 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44962404 | T2 DI CRZY HRS CYN-SNS :023/120 RPL RPTS | ICB
LC | 121329874 | 092/006 | T2 EI HUMBOLDT-TRINITY 92/6 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-13 | 2021-05-13 | 2022-06-07 | 2022-05-13 | 2022-05-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121330715 | 016/116 | T2 DI HELMS-GREGG #1 016/116 RPL INSS | FRESNO | ETL.4870.INSL | 2021-05-14 | 2021-04-20 | 2022-08-22 | 2022-04-20 | 2022-04-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE SPCR COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533801 | T2 DI HELMS-GREGG #1 RPLC INSS 9 TWRS | 93K
LC | 121330716 | 016/116 | T2 DI HELMS-GREGG #2 016/116 RPL INSS | FRESNO | ETL.4880.INSL | 2021-05-14 | 2021-04-20 | 2022-08-04 | 2022-04-20 | 2022-04-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE SPCR COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31514720 | HELMS-GREGG #2 REP INS 8TWRS | 93K
LC | 121330719 | :017/092 | T2 DI CRZY HRS CYN-SNS :017/092 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2021-05-14 | 2021-04-20 | 2021-10-06 | 2022-04-20 | 2022-04-20 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE SPCR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44962403 | T2 DI CRZY HRS CYN-SNS :017/092 RPL RPTS | ICB
LC | 121330720 | :017/092 | T2 DI CRZY HRS CYN-SNS :017/092 RMV STEP | MOSSLNDG | ETL.2900.TOWR | 2021-05-14 | 2021-04-20 | 2022-07-07 | 2022-04-20 | 2022-04-20 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE SPCR COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45075190 | T2 DI CRZY HRS CYN-SNS :017/092 RMV STEP | ICQ
LC | 121330739 | C020/080 | T2 DI CBRN-LS AGLS SS C020/080 RPL INSS | MOSSLNDG | ETL.4460.INSL | 2021-05-14 | 2021-04-20 | 2021-11-20 | 2022-04-20 | 2022-04-20 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31527944 | DI CBN-LS AGLS SW ST-PCH RPL INSS 13TWRS | 93K
LC | 121330760 | C020/080 | T2 DI CBRN-LS AS SS PCH C020/80 RPL INSS | MOSSLNDG | ETL.5330.INSL | 2021-05-14 | 2021-04-20 | 2022-08-04 | 2022-04-20 | 2022-04-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31550478 | DI MOSS LANDING-COBURN RPL INSS 6TWR | 93K
LC | 121330762 | C020/080 | T2 DI MSS LNDNG-CBRN C020/080 INS HRDT | MOSSLNDG | ETL.5330.TOWR | 2021-05-14 | 2021-04-20 | 2022-03-15 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45121194 | T2 DI MSS LNDNG-CBRN C020/080 INS HRDT | ICQ
LC | 121330849 | 004/030 | T2 DI EL DRO-MSRI FT #2 004/030 RPR INSS | SACTO | ETL.1540.INSL.CERA | 2021-05-14 | 2021-04-20 | 2022-05-16 | 2022-04-20 | 2022-04-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44812027 | T2 DI EL DRO-MSRI FT #2 004/030 RPR INSS | ICS
LC | 121330931 | 004/030 | T2 DI EL DRO-MSRI FT #1 4/30 RPR INSS | SACTO | ETL.1530.INSL.CERA | 2021-05-14 | 2021-04-20 | 2022-06-17 | 2022-04-20 | 2022-04-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44812026 | T2 DI EL DRO-MSRI FT #1 4/30 RPR INSS | ICS
LC | 121331000 | 008/003 | T2 DI SALINAS-FORT ORD #2 8/3 RMV DEBRI | MOSSLNDG | ETL.8423.POLE.NWOD | 2021-05-14 | 2021-04-20 | 2022-05-20 | 2022-04-20 | 2022-04-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45149994 | T2 DI SALINAS-FORT ORD #2 8/3 RMV DEBRI | ICS
LC | 121331003 | 008/003 | T2 DI SALINAS-FORT ORD #2 8/3 RPL INSS | MOSSLNDG | ETL.7890.INSL.CERA | 2021-05-14 | 2021-04-20 | 2022-05-20 | 2022-04-20 | 2022-04-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31596249 | T2 DI SALINAS-FORT ORD #2 9/2 RPL INSS | 93K
LC | 121331052 | 000/003 | T2 DI SLT SPGS-TG CRK 000/003 RPR STRT | VICTOR | ETL.3500.TOWR | 2021-05-14 | 2021-04-20 | 2022-03-31 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45150418 | T2 DI SLT SPGS-TG CRK 000/003 RPR STRT | ICQ
LC | 121331055 | :023/121 | T2 DI CY HS CYN SS SD :023/121 RPR STRT | MOSSLNDG | ETL.2900.TOWR | 2021-05-14 | 2021-04-20 | 2022-03-13 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45075191 | T2 DI CY HS CYN SS SD :023/121 RPR STRT | ICQ
LC | 121331717 | 008/066 | T2 DI SLT SPGS-TG CRK 008/066 RPL INSS | VICTOR | ETL.3500.INSL | 2021-05-14 | 2021-04-22 | 2022-06-25 | 2022-04-22 | 2022-04-22 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617889 | T2 DI SLT SPGS-TG CRK 008/066 RPL INSS | 93K
LC | 121331774 | 000/001 | T2 DI KRKF-CLVS-SGR #2 000/001 RPL INSS | FRESNO | ETL.1900.INSL.CERA | 2021-05-14 | 2021-04-16 | 2022-09-14 | 2022-04-16 | 2022-04-16 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533802 | DI KERCKHOFF-CLVS-SNGR #2 RPLC INSS 26TW | 93K
LC | 121332191 | 009/002 | T2 DI SALINAS-FORT ORD #2 9/2 RPL INSS | MOSSLNDG | ETL.7890.INSL.NCER | 2021-05-14 | 2021-04-21 | 2022-05-20 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31596249 | T2 DI SALINAS-FORT ORD #2 9/2 RPL INSS | 93K
LC | 121332433 | 042/354 | T2 EI PIT #1-COTTONWOOD 042/354 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-05-14 | 2021-05-14 | 2022-03-01 | 2022-05-14 | 2022-05-14 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45149536 | T2 EI PIT #1-COTTONWOOD 042/354 RPR STRT | ICQ
LC | 121332942 | 033/243 | T2 DI CARIBOU-TABLE MTN 33/243 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-05-14 | 2021-05-14 | 2022-06-20 | 2022-05-14 | 2022-05-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121333093 | 038/330 | T2 EI PIT #1-CTNWD 38/330 RPR STRT CMPT | TABLEMTN | ETL.5390.TOWR | 2021-05-14 | 2021-05-14 | 2022-05-24 | 2022-05-14 | 2022-05-14 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Structure-Tower | Repair | 45149530 | T2 EI PIT #1-COTTONWOOD 038/330 RPR STRT | ICQ
LC | 121333327 | 006/057 | T2 DI SLT SPRNGS-TGR CRK 6/57 RPR INSS | VICTOR | ETL.3500.INSL | 2021-05-14 | 2021-04-26 | 2022-06-20 | 2022-04-26 | 2022-04-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45155678 | T2 DI SLT SPRNGS-TGR CRK 6/57 RPR INSS | ICS
LC | 121333402 | 006/054 | T2 DI SLT SPRNGS-TGR CRK 6/54 RPR INSS | VICTOR | ETL.3500.INSL | 2021-05-14 | 2021-04-26 | 2022-06-25 | 2022-04-26 | 2022-04-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45155679 | T2 DI SLT SPRNGS-TGR CRK 6/54 RPR INSS | ICS
LC | 121333832 | 035/297 | T2 EI PIT #1-COTTONWOOD 035/297 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-05-14 | 2021-05-14 | 2022-03-07 | 2022-05-14 | 2022-05-14 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45149527 | T2 EI PIT #1-COTTONWOOD 035/297 RPR STRT | ICQ
LC | 121334292 | 004/033 | T2 WV EL DORADO-MSR FLT #2 4/33 RPL INSS | SACTO | ETL.1540.INSL | 2021-05-14 | 2021-05-14 | 2022-05-17 | 2022-05-14 | 2022-05-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547631 | T2 WV EL DORADO-MSR FLT #2 RPL INSS 10TW | 93K
LC | 121334648 | 004/004C | T2 DI HSDL JT-HF MN BY 004/004C RPR INSW | METCALF | ETL.7060.INSL.CERA | 2021-05-14 | 2021-04-26 | 2021-08-07 | 2022-04-26 | 2022-04-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44931533 | T2 DI HSDL JT-HF MN BY 004/004C RPR INSW | ICW
LC | 121335029 | 035/261 | T2 DI CRBU-TBLE MTN 035/261 RPR STRT | TABLEMTN | ETL.4440.TOWR | 2021-05-14 | 2021-04-21 | 2022-06-21 | 2022-04-21 | 2022-04-21 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45108137 | T2 DI CRBU-TBLE MTN 035/261 RPR STRT | ICQ
LC | 121335112 | :006/036 | T2 EI STN ML SW ST-RBK JT SW :6/36 RPL I | VICTOR | ETL.3840.INSL.NCER | 2021-05-14 | 2021-05-07 | 2022-05-18 | 2022-05-07 | 2022-05-07 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551875 | T2 DI STN ML SW ST-RBK JT RPL INSS 7TWR | 93K
LC | 121335224 | 068/000 | T2 EI HUMBOLDT-TRNTY 68/0 RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2021-05-14 | 2021-05-14 | 2022-03-30 | 2022-05-14 | 2022-05-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45147631 | T2 EI HUMBOLDT-TRNTY 68/0 RPR GYWW | ICW
LC | 121335245 | 068/001 | T2 EI HUMBOLDT-TRNTY 68/1L RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2021-05-14 | 2021-05-14 | 2022-03-30 | 2022-05-14 | 2022-05-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45147632 | T2 EI HUMBOLDT-TRNTY 68/1L RPR GYWW | ICW
LC | 121335252 | 068/001 | T2 EI HUMBOLDT-TRNTY 68/1R RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2021-05-14 | 2021-05-14 | 2022-03-30 | 2022-05-14 | 2022-05-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45147632 | T2 EI HUMBOLDT-TRNTY 68/1L RPR GYWW | ICW
LC | 121335818 | 033/139 | T2 EI TESLA-METCALF 33/139 INS RPTS | METCALF | ETL.6110.TOWR | 2021-05-14 | 2021-05-14 | 2022-07-15 | 2022-05-14 | 2022-05-14 | Late | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 45151629 | T2 EI TESLA-METCALF 33/139 INS RPTS | ICB
LC | 121336083 | 089/010 | T2 EI HUMBOLDT-TRINITY 89/10 RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2021-05-14 | 2021-05-14 | 2022-10-12 | 2022-05-14 | 2022-05-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45160434 | T2 EI HUMBOLDT-TRINITY 89/10 RPR GYWW | ICW
LC | 121336643 | :017/090 | T2 DI CZY HRS CNYN-SS-SD :17/90 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2021-05-14 | 2021-04-20 | 2021-10-06 | 2022-04-20 | 2022-04-20 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44961517 | T2 DI CZY HRS CNYN-SS-SD :17/90 RPL RPTS | ICB
LC | 121336867 | 089/011 | T2 EI HUMBOLDT-TRINITY 89/11L REPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-05-14 | 2021-05-14 | 2022-10-11 | 2022-05-14 | 2022-05-14 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121336890 | 089/011 | T2 EI HUMBOLDT-TRINITY 89/11R RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-05-14 | 2021-05-14 | 2022-10-11 | 2022-05-14 | 2022-05-14 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121336900 | 022/100 | T2 DI MOSS LANDING-COBURN 22/100 RPL INS | MOSSLNDG | ETL.5330.INSL | 2021-05-14 | 2021-04-15 | 2022-08-05 | 2022-04-15 | 2022-04-15 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31550478 | DI MOSS LANDING-COBURN RPL INSS 6TWR | 93K
LC | 121336910 | 003/029 | T2 DI SLT SPRNGS-TGR CRK 3/29 INS HRDT | VICTOR | ETL.3500.TOWR | 2021-05-14 | 2021-04-26 | 2022-04-28 | 2022-04-26 | 2022-04-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45150423 | T2 DI SLT SPRNGS-TGR CRK 3/29 INS HRDT | ICQ
LC | 121336914 | 006/055 | T2 DI SLT SPG-TGR CK 6/55 RPR STRT CMPLT | VICTOR | ETL.3500.TOWR | 2021-05-14 | 2021-04-26 | 2022-05-04 | 2022-04-26 | 2022-04-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45150424 | T2 DI SLT SPRNGS-TGR CRK 6/55 RPR STRT | ICQ
LC | 121337793 | 018/081 | T2 DI PTTSBRG-TSLA #1 018/081 RMV DEBRIS | CONCORD | ETL.5510.TOWR | 2021-05-15 | 2021-04-26 | 2021-09-28 | 2022-04-26 | 2022-04-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44959038 | T2 DI PTTSBRG-TSLA #1 018/081 RMV DEBRIS | ICS
LC | 121337840 | 032/233 | T2 DI DRUM-RIO OSO #2 032/233 RPL INSS | SACTO | ETL.1430.INSL.CERA | 2021-05-15 | 2021-04-26 | 2021-11-30 | 2022-04-26 | 2022-04-26 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535386 | EI DRM-RO OSO #2 RPL INSS 12TWRS | 93K
LC | 121337846 | C012/050 | T2 DI MSS LNDNG-CBRN C012/050 RPR FOND | MOSSLNDG | ETL.5330.TOWR | 2021-05-15 | 2021-04-26 | 2022-05-19 | 2022-04-26 | 2022-04-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45121195 | T2 DI MSS LNDNG-CBRN C012/050 RPR FOND | ICQ
LC | 121337887 | 037/246 | T2 DI CRESTA-RIO OSO 037/246 RPL INSS | TABLEMTN | ETL.4590.INSL.CERA | 2021-05-15 | 2021-04-21 | 2022-05-10 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546380 | DI CRESTA-RIO OSO RPLC INSS 8 TWRS | 93K
LC | 121337888 | 033/143 | T2 DI MRR BY-SLR SS #1 033/143 RPR FOND | PISMOBCH | ETL.5300.TOWR | 2021-05-15 | 2021-04-26 | 2022-07-19 | 2022-04-26 | 2022-04-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45073976 | T2 DI MRR BY-SLR SS #1 033/143 RPR FOND | ICQ
LC | 121338086 | 041/269 | T2 DI POE-RIO OSO 041/269 INST HRDT | TABLEMTN | ETL.5540.TOWR | 2021-05-15 | 2021-04-21 | 2022-01-11 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45099115 | T2 DI POE-RIO OSO 041/269 INST HRDT | ICQ
LC | 121338088 | 041/269 | T2 DI POE-RIO OSO 041/269 UNBURY | TABLEMTN | ETL.5540.TOWR | 2021-05-15 | 2021-04-21 | 2022-01-11 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45106673 | T2 DI POE-RIO OSO 041/269 UNBURY | ICQ
LC | 121338115 | 040/267 | T2 DI POE-RIO OSO 040/267 UNBURY | TABLEMTN | ETL.5540.TOWR | 2021-05-15 | 2021-04-21 | 2022-01-11 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45106671 | T2 DI POE-RIO OSO 040/267 UNBURY | ICQ
LC | 121338116 | 040/267 | T2 DI POE-RIO OSO 040/267 RPL HRDT | TABLEMTN | ETL.5540.TOWR | 2021-05-15 | 2021-04-21 | 2022-01-11 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45099113 | T2 DI POE-RIO OSO 040/267 RPL HRDT | ICQ
LC | 121338117 | 040/267 | T2 DI CRESTA-RIO OSO 040/267 RPL INSS | TABLEMTN | ETL.4590.INSL.CERA | 2021-05-15 | 2021-04-21 | 2022-05-06 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546381 | DI CRESTA-RIO OSO RPL INSS 10TWRS | 93K
LC | 121338241 | 037/163 | T2 DI MROBAY-SLRSWSTA #1-37/163 RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-05-15 | 2021-04-26 | 2022-06-16 | 2022-04-26 | 2022-04-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528621 | EI MORRO BAY-SOLAR SS #1 RPLC INNS 18TW | 93K
LC | 121338243 | 000/008 | T2 DI ST SPNGS TGR CK 000/008 RPR FOND | VICTOR | ETL.3500.TOWR | 2021-05-15 | 2021-04-26 | 2022-03-31 | 2022-04-26 | 2022-04-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45150425 | T2 DI ST SPNGS TGR CK 000/008 RPR FOND | ICQ
LC | 121338244 | 037/163 | T2 DI MROBAY-SLRSWSTA #2-37/163 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-05-15 | 2021-04-26 | 2022-07-26 | 2022-04-26 | 2022-04-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549069 | T2 EI MORRO BAY-SOLAR #2 RPL INSS 5TWRS | 93K
LC | 121338245 | 000/008 | T2 DI ST SPNGS TGR CK 000/008 INS HRDT | VICTOR | ETL.3500.TOWR | 2021-05-15 | 2021-04-26 | 2022-03-31 | 2022-04-26 | 2022-04-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45150426 | T2 DI ST SPNGS TGR CK 000/008 INS HRDT | ICQ
LC | 121338332 | 004/006 | T2 DI FULTON-HOPLAND 004/006 INST HRDW | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-05-15 | 2021-04-26 | 2022-03-31 | 2022-04-26 | 2022-04-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45143560 | T2 DI FULTON-HOPLAND 004/006 INST HRDW | ICW
LC | 121338380 | 001/010 | T2 DI ST SPNGS TGR CK 001/010 RPL INSS | VICTOR | ETL.3500.INSL | 2021-05-15 | 2021-04-26 | 2022-06-20 | 2022-04-26 | 2022-04-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31580615 | T2 DI ST SPNGS TGR CK RPL INSS 4TWRS | 93K
LC | 121338443 | 001/011 | T2DI SALTSPRINGS-TIGR CREK 1/11 RPR INSS | VICTOR | ETL.3500.INSL | 2021-05-15 | 2021-04-26 | 2022-06-19 | 2022-04-26 | 2022-04-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45155821 | T2DI SALTSPRINGS-TIGR CREK 1/11 RPR INSS | ICS
LC | 121338468 | 008/147 | T2 DI TEJON-LEBEC 008/147 RMV BUTT | MIDWAY | ETL.9250.POLE.NWOD | 2021-05-15 | 2021-04-26 | 2021-08-09 | 2022-04-26 | 2022-04-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE SPCR COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 44930595 | T2 DI TEJON-LEBEC 008/147 RMV BUTT | ICW
LC | 121338592 | 009/082 | T2 DI ELDRD-MSSR FLT #1 9/82 RPL STRW | SACTO | ETL.1530.POLE.WOOD | 2021-05-15 | 2021-04-16 | 2022-06-23 | 2022-04-16 | 2022-04-16 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541910 | T2 DI ELDRD-MSSR FLT #1 9/82 RPL STRW | 70Y
LC | 121338680 | 006/031 | T2 DI SLVRDO-FLTN JCT-06/31 RPL INSS | LAKEVLLE | ETL.1610.INSL | 2021-05-15 | 2021-04-26 | 2022-03-08 | 2022-04-26 | 2022-04-26 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548682 | T2 DI SILVERADO-FULTON JCT RPL INSS 6TWR | 93K
LC | 121338682 | 006/031 | T2 DI FULTON-PUEBLO 6/31 RPL INSS | LAKEVLLE | ETL.1600.INSL | 2021-05-15 | 2021-04-26 | 2022-02-22 | 2022-04-26 | 2022-04-26 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 121338685 | 001/011 | T2 DI CHRISTIE-WILLOW PASS 1/11 RPL HRDW | CONCORD | ETL.6370.POLE.WOOD | 2021-05-15 | 2021-04-22 | 2021-10-14 | 2022-04-22 | 2022-04-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44959019 | T2 DI CHRISTIE-WILLOW PASS 1/11 RPL HRDW | ICW
LC | 121338688 | 027/200 | T2 DI DRUM-RIO OSO #1 027/200 RPL INSS | SACTO | ETL.1420.INSL.CERA | 2021-05-15 | 2021-04-28 | 2022-02-10 | 2022-04-28 | 2022-04-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31531112 | DI DRUM-RIO OSO #1 RPL INSS 12TWRS | 93K
LC | 121338878 | 027/200 | T2 DI DRUM-RIO OSO #1 027/200 RMV STEP | SACTO | ETL.1420.TOWR | 2021-05-15 | 2021-04-28 | 2022-06-14 | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45074266 | T2 DI DRUM-RIO OSO #1 027/200 RMV STEP | ICQ
LC | 121339049 | 029/432 | T2 DI CLAY-MARTEL 29/432 RPR STRW | VICTOR | ETL.8250.POLE.NWOD | 2021-05-15 | 2021-05-11 | 2022-01-27 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45067194 | T2 DI CLAY-MARTEL 29/432 RPR STRW | ICW
LC | 121339080 | 029/432 | T2 DI CLAY-MARTEL 29/432 RPR SPLW | VICTOR | ETL.8250.INSL.NCER | 2021-05-15 | 2021-05-11 | 2022-01-27 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45067195 | T2 DI CLAY-MARTEL 29/432 RPR SPLW | ICW
LC | 121339196 | 003/031 | T2 DI ST SPNGS TGR CK 003/031 RPR INSS | VICTOR | ETL.3500.INSL | 2021-05-15 | 2021-04-16 | 2022-06-20 | 2022-04-16 | 2022-04-16 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45155822 | T2 DI ST SPNGS TGR CK 003/031 RPR INSS | ICS
LC | 121339269 | 039/257 | T2 DI POE RIO OSO 39/257 UNBURY | TABLEMTN | ETL.5540.TOWR | 2021-05-15 | 2021-04-26 | 2022-01-10 | 2022-04-26 | 2022-04-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45106668 | T2 DI POE RIO OSO 39/257 UNBURY | ICQ
LC | 121339308 | 019/086 | T2DI PITSBRG-TSLA #1 19/86 RMV STRS DBRI | CONCORD | ETL.5510.TOWR | 2021-05-15 | 2021-04-26 | 2021-09-28 | 2022-04-26 | 2022-04-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44959061 | T2DI PITSBRG-TSLA #1 19/86 RMV STRS DBRI | ICS
LC | 121339314 | 028/208 | T2 DI DRUM-RIO OSO #1 028/208 INST HRDT | SACTO | ETL.1420.TOWR | 2021-05-15 | 2021-04-26 | 2022-01-19 | 2022-04-26 | 2022-04-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45074278 | T2 DI DRUM-RIO OSO #1 028/208 INST HRDT | ICQ
LC | 121339315 | 028/208 | T2 DI DRUM-RIO OSO #1 028/208 RPR INSS | SACTO | ETL.1420.INSL.NCER | 2021-05-15 | 2021-04-26 | 2021-11-18 | 2022-04-26 | 2022-04-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44811975 | T2 DI DRUM-RIO OSO #1 028/208 RPR INSS | ICS
LC | 121339438 | 011/001 | T2 DI FULTON-HOPLAND 11/1 RPL INSW | LAKEVLLE | ETL.6890.INSL | 2021-05-15 | 2021-04-24 | 2022-08-24 | 2022-04-24 | 2022-04-24 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31596729 | T2 DI FULTON-HOPLAND 11/1 RPL INSW | 93I
LC | 121340568 | 089/000 | T2 EI HUMBOLDT-TRINITY 89/0 RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-05-15 | 2021-05-15 | 2022-06-08 | 2022-05-15 | 2022-05-15 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121340593 | 028/202A | T2 EI CARIBU-TABLE MTN 028/202A RPR FOND | TABLEMTN | ETL.4440.POLE.NWOD | 2021-05-15 | 2021-05-15 | 2022-07-11 | 2022-05-15 | 2022-05-15 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45374191 | T2 EI CARIBU-TABLE MTN 028/202A RPR FOND | ICQ
LC | 121340725 | 070/001X | T2 EI HUMB-TRNTY 070/001X RPR FOND | EUREKA | ETL.1820.TOWR | 2021-05-15 | 2021-05-15 | 2022-07-30 | 2022-05-15 | 2022-05-15 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45166596 | T2 EI HUMBOLDT-TRNTY 70/1X RPR FOND | ICQ
LC | 121341018 | 021/429 | T2 DI COLGATE-PALERMO 21/429 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2021-05-16 | 2021-05-10 | 2022-05-03 | 2022-05-10 | 2022-05-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31599817 | T2 DI COLGATE-PALERMO 6/106 RPL STRW | 70Y
LC | 121341063 | 018/082 | T2 DI PTSBRG-TSL #1 18/82 RPR FOND CMPLT | CONCORD | ETL.5510.TOWR | 2021-05-16 | 2021-04-26 | 2022-04-09 | 2022-04-26 | 2022-04-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190826 | T2 DI PITTSBURG-TESLA #1 18/82 RPR FOND | ICQ
LC | 121341065 | 018/082 | T2 DI PTSBRG-TSL #1 18/82 RPL HRDT CMPLT | CONCORD | ETL.5510.TOWR | 2021-05-16 | 2021-04-26 | 2022-04-09 | 2022-04-26 | 2022-04-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45190827 | T2 DI PITTSBURG-TESLA #1 18/82 RPLC HRDT | ICQ
LC | 121341069 | 011/068 | T2 DI HAAS-MCCALL 11/68 RPLC INSS | FRESNO | ETL.4850.INSL | 2021-05-16 | 2021-04-21 | 2022-03-07 | 2022-04-21 | 2022-04-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31541676 | T2 DI HAAS-MCCALL 11/68 RPLC INSS | 93K
LC | 121341151 | 005/047 | T2NT DI PARADISE-TABLE MTN 5/47 RPR FOND | TABLEMTN | ETL.4316.TOWR | 2021-05-16 | 2021-04-28 | 2022-06-16 | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195445 | T2NT DI PARADISE-TABLE MTN 5/47 RPR FOND | ICQ
LC | 121341156 | 016/139 | T2 DI DRUM-RIO OSO #1 16/139 INS HRDT | SACTO | ETL.1420.TOWR | 2021-05-16 | 2021-04-28 | 2022-01-13 | 2022-04-28 | 2022-04-28 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45074300 | T2 DI DRUM-RIO OSO #1 16/139 INS HRDT | ICQ
LC | 121341158 | 002/014 | T2 DI FULTON-PUEBLO 2/14 INS HRDT | LAKEVLLE | ETL.1600.TOWR | 2021-05-16 | 2021-04-28 | 2022-09-15 | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45142238 | T2 DI FULTON-PUEBLO 2/14 INS HRDT | ICQ
LC | 121341321 | 020/280 | T2 DI SSQC-SNT YNZ SW ST 20/280 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-05-16 | 2021-04-27 | 2022-03-03 | 2022-04-27 | 2022-04-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069328 | T2 DI SSQC-SNT YNZ SW ST 20/280 RPR STRW | ICW
LC | 121341325 | 017/252 | T2 DI SSQC-SNT YNZ SW ST 17/252 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-05-16 | 2021-04-27 | 2022-06-27 | 2022-04-27 | 2022-04-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069329 | T2 DI SSQC-SNT YNZ SW ST 17/252 RPR STRW | ICW
LC | 121341327 | 017/252 | T2 DI SSQC-SNT YNZ SW ST 17/252 RPR GYWW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-05-16 | 2021-04-27 | 2022-06-27 | 2022-04-27 | 2022-04-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069331 | T2 DI SSQC-SNT YNZ SW ST 17/252 RPR GYWW | ICW
LC | 121341360 | 027/202 | T2 DI DRUM-RIO OSO #1 27/202 RMV VEG | SACTO | ETL.1420.TOWR | 2021-05-16 | 2021-04-28 | 2022-01-06 | 2022-04-28 | 2022-04-28 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121341361 | 027/202 | T2 DI DRUM-RIO OSO #1 27/202 RPL INSS | SACTO | ETL.1420.INSL.NCER | 2021-05-16 | 2021-04-28 | 2022-02-10 | 2022-04-28 | 2022-04-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31531112 | DI DRUM-RIO OSO #1 RPL INSS 12TWRS | 93K
LC | 121341363 | 020/275 | T2 DI SISQUOC-SANTA YNEZ 20/275 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-05-16 | 2021-04-27 | 2022-03-03 | 2022-04-27 | 2022-04-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069333 | T2 DI SISQUOC-SANTA YNEZ 20/275 RPR STRW | ICW
LC | 121341385 | 041/198 | T2 DI IGNACIO-SOBRANTE 41/198 INS HRDT | CONCORD | ETL.4920.TOWR | 2021-05-16 | 2021-04-28 | 2022-03-26 | 2022-04-28 | 2022-04-28 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45190695 | T2 DI IGNACIO-SOBRANTE 41/198 INS HRDT | ICQ
LC | 121341468 | C014/058 | T2 DI MSS LNDNG-COBURN C014/058 RPL INSS | MOSSLNDG | ETL.5330.INSL | 2021-05-16 | 2021-04-22 | 2022-08-03 | 2022-04-22 | 2022-04-22 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31550478 | DI MOSS LANDING-COBURN RPL INSS 6TWR | 93K
LC | 121341469 | C014/058 | T2 DI CBRN-LS AGLS SS C14/58 RPL INSS | MOSSLNDG | ETL.4460.INSL | 2021-05-16 | 2021-04-22 | 2021-11-16 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31527944 | DI CBN-LS AGLS SW ST-PCH RPL INSS 13TWRS | 93K
LC | 121343617 | 022/091 | T2 DI GEYSERS #17-FULTON- 22/91 RPR INSS | LAKEVLLE | ETL.4770.INSL.CERA | 2021-05-17 | 2021-05-13 | 2022-07-14 | 2022-05-13 | 2022-05-13 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45144164 | T2 DI GEYSERS #17-FULTON- 22/91 RPR INSS | ICS
LC | 121344172 | 009/102 | T2 EI VEDDER TAP 9/102 RPR GYWW | MIDWAY | ETL.2141.POLE.WOOD | 2021-05-17 | 2021-05-17 | 2021-12-07 | 2022-05-17 | 2022-05-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44992844 | T2 EI VEDDER TAP 9/102 RPR GYWW | ICW
LC | 121344437 | 028/409 | T2 DI CLAY-MARTEL 28/409 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-17 | 2021-05-17 | 2022-01-26 | 2022-05-17 | 2022-05-17 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543390 | DI CLAY-MARTEL 026/367 RPL STRW | 70Y
LC | 121344887 | :001/012 | T2 EI FULTON-PUEBLO :1/012 RPL INSW | LAKEVLLE | ETL.1600.POLE.WOOD | 2021-05-17 | 2021-05-17 | 2022-02-11 | 2022-05-17 | 2022-05-17 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541679 | T2 EI FULTON-PUEBLO :1/012 RPL INSW | 93I
LC | 121344932 | 005/003 | T2 DI FULTON-HOPLAND 5/3 RPL HRDD | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-05-17 | 2021-04-28 | 2022-03-30 | 2022-04-28 | 2022-04-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45143561 | T2 DI FULTON-HOPLAND 5/3 RPL HRDD | ICW
LC | 121345321 | X010/042 | T2 DI DIABLO-MESA X010/042 RPL INSS | PISMOBCH | ETL.4620.INSL | 2021-05-17 | 2021-04-28 | 2022-07-07 | 2022-04-28 | 2022-04-28 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534103 | T2 DI DIABLO-MESA 18/79 RPLC INSS 6TWRS | 93K
LC | 121346084 | 015/155 | T2 DI ARCO-CHOLAME 15/155 GRND WASH | MIDWAY | ETL.8440.SWIT | 2021-05-17 | 2021-05-17 | 2022-02-23 | 2022-05-17 | 2022-05-17 | On-time | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Contaminated | Insulator | Ground Wash | 45067921 | T2 DI ARCO-CHOLAME 15/155 GRND WASH | ICD
LC | 121346683 | B019/433 | T2 DI DRM-GRS VLY-WMR B19/433 RPR SPLW | SACTO | ETL.6760.INSL.CERA | 2021-05-17 | 2021-05-17 | 2022-07-26 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 44812060 | T2 DI DRM-GRS VLY-WMR B19/433 RPR SPLW | ICW
LC | 121346685 | B019/433 | T2 DI DRM-GRS VLY-WMR B19/433 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2021-05-17 | 2021-05-17 | 2022-07-26 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44812039 | T2 DI DRM-GRS VLY-WMR B19/433 RPR STRW | ICW
LC | 121346766 | 021/117 | T2 PARKWAY-MORAGA 021/117 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-17 | 2021-04-20 | 2021-11-06 | 2022-04-20 | 2022-04-20 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44819560 | T2 PARKWAY-MORAGA 021/117 RPL SHLS | ICS
LC | 121346802 | 021/118 | T2 PARKWAY-MORAGA 021/118 RPL SHLS | LAKEVLLE | ETL.5930.TOWR | 2021-05-17 | 2021-04-20 | 2021-11-06 | 2022-04-20 | 2022-04-20 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 44819562 | T2 PARKWAY-MORAGA 021/118 RPL SHLS | ICS
LC | 121347533 | 027/122 | T2 EI TESLA-LOS BANOS #1 27/122 INS RPTS | VICTOR | ETL.6100.TOWR | 2021-05-17 | 2021-05-17 | 2022-04-13 | 2022-05-17 | 2022-05-17 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 45122133 | T2 EI TESLA-LOS BANOS #1 27/122 INS RPTS | ICB
LC | 121347620 | 072/003 | T2 EI HUMBOLDT-TRINITY 72/3 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-17 | 2021-05-17 | 2022-10-17 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45158943 | T2 EI HUMBOLDT-TRINITY 72/3 RPR GYWW | ICW
LC | 121347623 | 072/003 | T2 EI HUMBOLDT-TRINITY 72/3 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-17 | 2021-05-17 | 2022-10-17 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45158943 | T2 EI HUMBOLDT-TRINITY 72/3 RPR GYWW | ICW
LC | 121347644 | 072/003 | T2 EI HUMBOLDT-TRINITY 72/3 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-17 | 2021-05-17 | 2022-10-17 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | Missing | Guy Wire-Wood | Install | 45158943 | T2 EI HUMBOLDT-TRINITY 72/3 RPR GYWW | ICW
LC | 121347648 | 091/006 | T2 EI HUMBOLDT-TRINITY 91/6R RPR WDPKR | EUREKA | ETL.1820.POLE.WDPS | 2021-05-17 | 2021-05-17 | 2022-06-07 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45160721 | T2 EI HUMBOLDT-TRINITY 91/6R RPR WDPKR | ICW
LC | 121347677 | 026/192A | T2 EI CARIBOU-TABLE MTN 26/192A RPR FOND | TABLEMTN | ETL.4440.POLE.NWOD | 2021-05-17 | 2021-05-17 | 2022-07-05 | 2022-05-17 | 2022-05-17 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160950 | T2 EI CARIBOU-TABLE MTN 26/192A RPR FOND | ICQ
LC | 121347804 | 007/009 | T2 DI CHOWCHILLA-KERCKHOFF 7/9 RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-05-17 | 2021-04-22 | 2022-11-02 | 2022-04-22 | 2022-04-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31596158 | T2 DI CHOWCHILLA-KERCKHOFF 7/9 RPL STRW | 70Y
LC | 121348341 | 015/110A | T2 EI HELMS-GREGG #1 15/110A RMV NEST | FRESNO | ETL.4870.TOWR | 2021-05-17 | 2021-05-17 | 2022-08-21 | 2022-05-17 | 2022-05-17 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | Debris/Nest/etc. | Structure-Steel | Remove | 45069456 | T2 EI HELMS-GREGG #1 15/110A RMV NEST | ICS
LC | 121348344 | 015/111A | T2 EI HELMS-GREGG #1 15/111A RMV NEST | FRESNO | ETL.4870.TOWR | 2021-05-17 | 2021-05-17 | 2022-08-21 | 2022-05-17 | 2022-05-17 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | Debris/Nest/etc. | Structure-Steel | Remove | 45069457 | T2 EI HELMS-GREGG #1 15/111A RMV NEST | ICS
LC | 121348538 | :015/095 | T2 DI GRN VLLY-LLGS :15/095 RPL INSS | MOSSLNDG | ETL.2800.INSL.CERA | 2021-05-17 | 2021-04-28 | 2022-06-21 | 2022-04-28 | 2022-04-28 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535376 | T2 DI GREEN VLY-LLAGAS RPLC INSS 3TWRS | 93K
LC | 121348627 | 032/150 | T2 DI TRACY-LOS BANOS 032/150 RPL ZENA | VICTOR | ETL.6130.TOWR | 2021-05-17 | 2021-04-28 | 2022-04-13 | 2022-04-28 | 2022-04-28 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 45150294 | T2 DI TRACY-LOS BANOS 032/150 RPL ZENA | ICB
LC | 121348679 | 026/159 | T2 DI TEMBLOR-SLO- 26/159 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-05-17 | 2021-04-22 | 2022-04-20 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546830 | T2 DI TEMBLOR-SLO- RPL INSS 6TWRS | 93K
LC | 121350076 | 001/023 | T2 DI COLGATE-CHALLENGE 001/023 RPL SPLW | SACTO | ETL.6480.INSL.CERA | 2021-05-18 | 2021-05-17 | 2021-06-11 | 2022-05-17 | 2022-05-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Replace | 44812061 | T2 DI COLGATE-CHALLENGE 001/023 RPL SPLW | ICW
LC | 121350137 | 011/006 | T2 MERCED FALLS-EXCHEQUER 11/6 RPR INSS | FRESNO | ETL.8990.INSL.NCER | 2021-05-18 | 2021-05-18 | 2022-03-21 | 2022-05-18 | 2022-05-18 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair | 45591164 | T2 MERCED FALLS-EXCHEQUER 11/6 RPR INSS | ICS
LC | 121350155 | 011/008 | T2 MERCED FALLS-EXCHEQUER 11/08 RPR INSS | FRESNO | ETL.8990.POLE.NWOD | 2021-05-18 | 2021-05-18 | 2022-03-22 | 2022-05-18 | 2022-05-18 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair | 45199321 | T2 MERCED FALLS-EXCHEQUER 11/08 RPR INSS | ICS
LC | 121350212 | 012/001 | T2 MERCED FALLS-EXCHEQUER 12/00 RPR INSS | FRESNO | ETL.8990.POLE.NWOD | 2021-05-18 | 2021-05-18 | 2022-03-21 | 2022-05-18 | 2022-05-18 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair | 45199322 | T2 MERCED FALLS-EXCHEQUER 12/00 RPR INSS | ICS
LC | 121350893 | 001/000 | T2 EI GARCIA TAP 01/00R RPL ANCW | LAKEVLLE | ETL.8411.POLE.WDPS | 2021-05-18 | 2021-05-18 | 2021-05-17 | 2022-05-18 | 2022-05-18 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31509677 | T2 EI GARCIA TAP 001/000 RPL ANCW | 93E
LC | 121351035 | 072/368 | T2 EI MALIN-ROUND MTN #2 72/368 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-05-18 | 2021-05-17 | 2022-08-10 | 2022-05-17 | 2022-05-17 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45197657 | T2 EI MALIN-ROUND MTN #2 72/368 RPR GYWS | ICS
LC | 121351063 | 020/136 | T2 DI HELMS-GREGG #1 020/136 RPL INSS | FRESNO | ETL.4870.INSL | 2021-05-18 | 2021-04-27 | 2022-08-22 | 2022-04-27 | 2022-04-27 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533801 | T2 DI HELMS-GREGG #1 RPLC INSS 9 TWRS | 93K
LC | 121351094 | 009/044 | T2 DI MORRO BAY-MESA 9/44 RMV VEGN | PISMOBCH | ETL.5290.TOWR | 2021-05-18 | 2021-04-27 | 2022-01-10 | 2022-04-27 | 2022-04-27 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121351366 | 012/095 | T2 DI SLT SPRNGS-TGR CRK 12/95 RPR FOND | VICTOR | ETL.3500.TOWR | 2021-05-18 | 2021-04-20 | 2022-03-29 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45150435 | T2 DI SLT SPRNGS-TGR CRK 12/95 RPR FOND | ICQ
LC | 121351603 | :018/094 | T2 DI CRZY HRS CYN-SS :18/94 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2021-05-18 | 2021-04-20 | 2021-10-07 | 2022-04-20 | 2022-04-20 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44962405 | T2 DI CRZY HRS CYN-SS :18/94 RPL RPTS | ICB
LC | 121352423 | 014/070 | T2 CONTRA COSTA-MORAGA #1 14/0 RPL STRS | CONCORD | ETL.5452.TOWR | 2021-05-18 | 2021-05-18 | 2022-01-11 | 2022-05-18 | 2022-05-18 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45121150 | T2 CONTRA COSTA-MORAGA #1 14/0 RPL STRS | ICQ
LC | 121352612 | 000/029 | T2 DI SPAULDING-SUMMIT 0/29 RPR INSW | SACTO | ETL.8060.INSL.CERA | 2021-05-18 | 2021-05-17 | 2022-09-23 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44812064 | T2 DI SPAULDING-SUMMIT 0/29 RPR INSW | ICW
LC | 121352785 | 070/357 | T2 EI MALIN-ROUND MTN #2 70/357 RPR STRT | TABLEMTN | ETL.6020.TOWR | 2021-05-18 | 2021-05-18 | 2022-06-13 | 2022-05-18 | 2022-05-18 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45194405 | T2 EI MALIN-ROUND MTN #2 70/357 RPR STRT | ICQ
LC | 121352941 | 033/144 | T2 DI MRR BY-SLR SW ST #2 33/144 RPL INS | PISMOBCH | ETL.5310.INSL | 2021-05-18 | 2021-04-26 | 2022-07-26 | 2022-04-26 | 2022-04-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549068 | T2 DI MR BY-SLR SW ST #2 RPL INSS 7TWRS | 93K
LC | 121352942 | 033/144 | T2 DI MRR BY-SLR SW ST #1 33/144 RPL INS | PISMOBCH | ETL.5300.INSL | 2021-05-18 | 2021-04-26 | 2022-06-18 | 2022-04-26 | 2022-04-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528621 | EI MORRO BAY-SOLAR SS #1 RPLC INNS 18TW | 93K
LC | 121352944 | 033/144 | T2 DI MRR BY-SLR SW ST #1 33/144 RPR FON | PISMOBCH | ETL.5300.TOWR | 2021-05-18 | 2021-04-26 | 2022-07-19 | 2022-04-26 | 2022-04-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2N PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45073979 | T2 DI MRR BY-SLR SW ST #1 33/144 RPR FON | ICQ
LC | 121352995 | 020/283 | T2 DI SISQUOC-SANTA YNEZ 20/283 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-05-18 | 2021-04-28 | 2022-02-01 | 2022-04-28 | 2022-04-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069335 | T2 DI SISQUOC-SANTA YNEZ 20/283 RPR STRW | ICW
LC | 121352997 | 014/108 | T2 DI SLT SPRNGS-TGR CRK 14/108 RPR FOND | VICTOR | ETL.3500.TOWR | 2021-05-18 | 2021-04-26 | 2022-03-29 | 2022-04-26 | 2022-04-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45150436 | T2 DI SLT SPRNGS-TGR CRK 14/108 RPR FOND | ICQ
LC | 121352999 | 009/079 | T2 DI SLT SPRNGS-TGR CRK 9/79 RMV STEP | VICTOR | ETL.3500.TOWR | 2021-05-18 | 2021-04-26 | 2022-03-21 | 2022-04-26 | 2022-04-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45150437 | T2 DI SLT SPRNGS-TGR CRK 9/79 RMV STEP | ICQ
LC | 121353333 | 006/112 | T2 DI SSQC-SNT YNZ SW ST 6/112 RPL STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-05-18 | 2021-04-27 | 2022-04-12 | 2022-04-27 | 2022-04-27 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540464 | DI SSQC-SNTA YNEZ SS 011/177 RPL POLE | 70Y
LC | 121353455 | 006/043 | T2 EI BUTTE VALLEY-CARIBOU 6/43 RPR FOND | TABLEMTN | ETL.1180.TOWR | 2021-05-18 | 2021-05-18 | 2022-06-28 | 2022-05-18 | 2022-05-18 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160928 | T2 EI BUTTE VALLEY-CARIBOU 6/43 RPR FOND | ICQ
LC | 121354328 | :001/004 | T2 EI FULTON-PUEBLO :1/4 RPR STRW | LAKEVLLE | ETL.1600.POLE.WOOD | 2021-05-18 | 2021-05-18 | 2022-02-10 | 2022-05-18 | 2022-05-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45147868 | T2 EI FULTON-PUEBLO :1/4 RPR STRW | ICW
LC | 121355053 | 040/265 | T2 DI POE-RIO OSO 40/265 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-05-18 | 2021-04-28 | 2022-01-27 | 2022-04-28 | 2022-04-28 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45106669 | T2 DI POE-RIO OSO 40/265 RPR FOND | ICQ
LC | 121355059 | 004/023 | T2 DI MORR BAY-TEMPLETON 4/23 RPR FOND | PISMOBCH | ETL.5933.TOWR | 2021-05-18 | 2021-04-29 | 2022-05-20 | 2022-04-29 | 2022-04-29 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45098858 | T2 DI MORR BAY-TEMPLETON 4/23 RPR FOND | ICQ
LC | 121355109 | 073/003 | T2 EI HUMBOLDT-TRINITY 73/3L RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-18 | 2021-05-18 | 2022-03-31 | 2022-05-18 | 2022-05-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45147776 | T2 EI HUMBOLDT-TRINITY 73/3L RPR GYWW | ICW
LC | 121355121 | 073/003 | T2 EI HUMBOLDT-TRINITY 73/3R RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-18 | 2021-05-18 | 2022-03-31 | 2022-05-18 | 2022-05-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45147776 | T2 EI HUMBOLDT-TRINITY 73/3L RPR GYWW | ICW
LC | 121355122 | 073/002AA | T2 EI HUMBOLDT-TRINITY 73/2AA RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-18 | 2021-05-18 | 2022-04-02 | 2022-05-18 | 2022-05-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45147773 | T2 EI HUMBOLDT-TRINITY 73/2AA RPR GYWW | ICW
LC | 121355140 | 073/003 | T2 EI HUMBOLDT-TRINITY 73/3C RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-18 | 2021-05-18 | 2022-03-31 | 2022-05-18 | 2022-05-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45147776 | T2 EI HUMBOLDT-TRINITY 73/3L RPR GYWW | ICW
LC | 121355141 | 073/002AA | T2 EI HUMBOLDT-TRINITY 73/2AA RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-18 | 2021-05-18 | 2022-04-02 | 2022-05-18 | 2022-05-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45147773 | T2 EI HUMBOLDT-TRINITY 73/2AA RPR GYWW | ICW
LC | 121355143 | 073/002AA | T2 EI HUMBOLDT-TRINITY 73/2AA RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-18 | 2021-05-18 | 2022-04-02 | 2022-05-18 | 2022-05-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45147773 | T2 EI HUMBOLDT-TRINITY 73/2AA RPR GYWW | ICW
LC | 121355218 | 074/002 | T2 EI CTTNWD-HMBLDT 74/2 RPR SPLW | EUREKA | ETL.1820.INSL.CERA | 2021-05-18 | 2021-05-18 | 2022-04-01 | 2022-05-18 | 2022-05-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 44830122 | T2 EI CTTNWD-HMBLDT 74/2 RPR SPLW | ICW
LC | 121355280 | 091/003 | T2 EI HUMBOLDT-TRINITY 91/3 RPL INSW | EUREKA | ETL.1820.INSL.NCER | 2021-05-18 | 2021-05-18 | 2022-06-07 | 2022-05-18 | 2022-05-18 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542141 | T2 EI HUMBOLDT-TRINITY 91/3 RPL INSW | 93I
LC | 121355390 | 020/274 | T2 DI SISQUOC-SANTA YNEZ 20/274 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-05-18 | 2021-04-27 | 2022-03-02 | 2022-04-27 | 2022-04-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069337 | T2 DI SISQUOC-SANTA YNEZ 20/274 RPR STRW | ICW
LC | 121355537 | X007/031 | T2 DI DIABLO-MESA X7/31 RPR SHLW | PISMOBCH | ETL.4620.TOWR | 2021-05-18 | 2021-04-29 | 2022-01-24 | 2022-04-29 | 2022-04-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45098620 | T2 DI DIABLO-MESA X7/31 RPR SHLW | ICW
LC | 121355663 | 021/290 | T2 DI SISQUOC-SANTA YNEZ 21/290 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-05-18 | 2021-04-27 | 2022-03-03 | 2022-04-27 | 2022-04-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069340 | T2 DI SISQUOC-SANTA YNEZ 21/290 RPR STRW | ICW
LC | 121355810 | 011/090 | T2 DI SLT SPRNGS TGR CK 11/90 INS HRDT | VICTOR | ETL.3500.TOWR | 2021-05-18 | 2021-04-20 | 2022-03-29 | 2022-04-20 | 2022-04-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45150483 | T2 DI SLT SPRNGS TGR CK 11/90 INS HRDT | ICQ
LC | 121355812 | 011/090 | T2 DI SLT SPRNGS TGR CK 011/090 RPR SHLD | VICTOR | ETL.3500.TOWR | 2021-05-18 | 2021-04-20 | 2022-03-03 | 2022-04-20 | 2022-04-20 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45155823 | T2 DI SLT SPRNGS TGR CK 011/090 RPR SHLD | ICS
LC | 121355875 | 010/119A | T2 WV DRUM-SUMMIT #2 010/119A RPL STRW | SACTO | ETL.1450.POLE.WOOD | 2021-05-18 | 2021-05-18 | 2021-11-01 | 2022-05-18 | 2022-05-18 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31531879 | T2 DI DRUM-SUMMIT #2 2/31L RPL STRW | 70Y
LC | 121355943 | 010/119B | T2 WV DRUM-SUMMIT #2 10/119B RPL STRW | SACTO | ETL.1450.POLE.WOOD | 2021-05-18 | 2021-05-18 | 2021-11-01 | 2022-05-18 | 2022-05-18 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31531879 | T2 DI DRUM-SUMMIT #2 2/31L RPL STRW | 70Y
LC | 121356741 | 019/161 | T2 DI CRAG VIEW-CASCADE 19/161 RPL INSW | TABLEMTN | ETL.1350.INSL | 2021-05-18 | 2021-05-18 | 2022-09-02 | 2022-05-18 | 2022-05-18 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541813 | T2 DI CRAG VIEW-CASCADE 19/161 RPL INSW | 93I
LC | 121356742 | 019/161 | T2 DI CRAG VIEW-CASCADE 19/161 RPR OPGW | TABLEMTN | ETL.1350.POLE.STPS | 2021-05-18 | 2021-05-18 | 2022-09-02 | 2022-05-18 | 2022-05-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45309952 | T2 DI CRAG VIEW-CASCADE 19/161 RPR OPGW | ICW
LC | 121356809 | 041/197 | T2 DI IGNACIO-SOBRANTE 041/197 RPL INSS | LAKEVLLE | ETL.4920.INSL.CERA | 2021-05-18 | 2021-04-28 | 2022-03-17 | 2022-04-28 | 2022-04-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31531905 | DI IGNACIO SOBRANTE RPL INSS 5 TWRS | 93K
LC | 121356845 | 026/195 | T2 DI DRUM-RIO OSO #1 026/195 RMV NEST | SACTO | ETL.1420.TOWR | 2021-05-18 | 2021-04-28 | 2021-11-19 | 2022-04-28 | 2022-04-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44811970 | T2 DI DRUM-RIO OSO #1 026/195 RMV NEST | ICS
LC | 121356847 | 026/195 | T2 DI DRUM-RIO OSO #1 026/195 RMV STEP | SACTO | ETL.1420.TOWR | 2021-05-18 | 2021-04-28 | 2022-05-31 | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45074327 | T2 DI DRUM-RIO OSO #1 026/195 RMV STEP | ICQ
LC | 121356973 | 014/106A | T2 EI HELMS-GREGG #1 14/106A RMV VEG | FRESNO | ETL.4870.TOWR | 2021-05-18 | 2021-05-18 | 2022-06-14 | 2022-05-18 | 2022-05-18 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121357033 | 006/049 | T2 DI BRUNSWICK #2 TAP 6/49 RPL INSS | SACTO | ETL.1431.INSL | 2021-05-18 | 2021-04-22 | 2021-12-01 | 2022-04-22 | 2022-04-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540711 | T3 DI BRUNSWICK #1 TAP RPL INSS 3TWRS | 93K
LC | 121357632 | 089/000 | T2 EI HUMBOLDT-TRINITY 89/0 RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-05-19 | 2021-05-15 | 2022-06-08 | 2022-05-15 | 2022-05-15 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121357743 | 008/161 | T2 EI VALLEY SPRINGS #1 8/161 RPR STRW | VICTOR | ETL.8210.POLE.WOOD | 2021-05-19 | 2021-05-19 | 2021-08-24 | 2022-05-19 | 2022-05-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44943371 | T2 EI VALLEY SPRINGS #1 8/161 RPR STRW | ICW
LC | 121357805 | 038/251 | T2 DI CRESTA-RIO OSO 38/251 RPLC INSS | TABLEMTN | ETL.4590.INSL.CERA | 2021-05-19 | 2021-04-21 | 2022-05-06 | 2022-04-21 | 2022-04-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546380 | DI CRESTA-RIO OSO RPLC INSS 8 TWRS | 93K
LC | 121357925 | 005/000 | T2 EI PHILO JCT-ELK 05/000 RPL PL | WILLITS | ETL.7780.POLE.WOOD | 2021-05-19 | 2021-05-19 | 2022-07-07 | 2022-05-19 | 2022-05-19 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541324 | T2 PHILO JCT-ELK 05/000 RPL PL | 70Y
LC | 121358085 | 008/008 | T2 PHILO JCT-ELK 08/008 RPL PL CMPLTD | WILLITS | ETL.7780.POLE.WOOD | 2021-05-19 | 2021-05-19 | 2022-06-21 | 2022-05-19 | 2022-05-19 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541324 | T2 PHILO JCT-ELK 05/000 RPL PL | 70Y
LC | 121359597 | 012/091A | T2 EI HELMS-GREGG #1 12/091A RMV NEST | FRESNO | ETL.4870.TOWR | 2021-05-19 | 2021-05-19 | 2021-07-21 | 2022-05-19 | 2022-05-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Structure-Steel | Remove | 44923428 | T2 EI HELMS-GREGG #1 12/091A RMV NEST | ICS
LC | 121359988 | 014/474 | T2 DI SPAULDING-SUMMIT 014/474 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-05-19 | 2021-05-18 | 2021-07-28 | 2022-05-18 | 2022-05-18 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31542073 | T2 EI SPAULDING-SUMMIT 14/466 RPL STRW | 70Y
LC | 121360333 | 012/093A | T2 EI HLMS-GRG #1 12/93A RPR FOND CMPLTD | FRESNO | ETL.4870.TOWR | 2021-05-19 | 2021-05-19 | 2022-06-14 | 2022-05-19 | 2022-05-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45070017 | T2 EI HELMS-GREGG #1 12/093A RPR FOND | ICQ
LC | 121360976 | 061/258 | T2 WV RND MT TBL MT #2 61/258 RPR INSS | TABLEMTN | ETL.6070.INSL.NCER | 2021-05-19 | 2021-05-19 | 2022-06-02 | 2022-05-19 | 2022-05-19 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45355176 | T2 WV RND MT TBL MT #2 61/258 RPR INSS | ICS
LC | 121361108 | 024/198 | T2 CRESTA-RIO OSO 24/198 RPL INSS CMPLTD | TABLEMTN | ETL.4590.INSL.CERA | 2021-05-19 | 2021-05-19 | 2022-05-06 | 2022-05-19 | 2022-05-19 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31602389 | T2 CRESTA-RIO OSO 24/198 RPL INSS | 93K
LC | 121361627 | 075/005 | T2 EI HUMBOLDT-TRINITY 75/5 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-19 | 2021-05-19 | 2022-04-02 | 2022-05-19 | 2022-05-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148022 | T2 EI HUMBOLDT-TRINITY 75/5 RPR GYWW | ICW
LC | 121361718 | 008/100 | T2 DI VEDDER TAP 008/100 RPR INSW | MIDWAY | ETL.2141.INSL.CERA | 2021-05-19 | 2021-04-27 | 2022-01-27 | 2022-04-27 | 2022-04-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45068047 | T2 DI VEDDER TAP 008/100 RPR INSW | ICW
LC | 121362300 | 020/016 | T2 EI MAPLE CREEK-HOOPA 20/16 RPR STRW | EUREKA | ETL.7490.POLE.WOOD | 2021-05-19 | 2021-05-19 | 2022-08-04 | 2022-05-19 | 2022-05-19 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 44875355 | T2 EI MAPLE CREEK-HOOPA 20/16 RPR STRW | ICW
LC | 121362414 | 033/153 | T2 EI TRACY-LOS BANOS 3/153 RPL INSS | VICTOR | ETL.6130.INSL | 2021-05-19 | 2021-05-19 | 2022-04-10 | 2022-05-19 | 2022-05-19 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW COMP OH FMOB TR2 PRTO CLMB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31543093 | DI TRACY-LOS BANOS RPL INSS 8TWRS | 93K
LC | 121362495 | 075/005 | T2 EI HUMBOLDT-TRINITY 75/5 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-19 | 2021-05-19 | 2022-04-02 | 2022-05-19 | 2022-05-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148022 | T2 EI HUMBOLDT-TRINITY 75/5 RPR GYWW | ICW
LC | 121362496 | 075/005 | T2 EI HUMBOLDT-TRINITY 75/5 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-19 | 2021-05-19 | 2022-04-02 | 2022-05-19 | 2022-05-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148022 | T2 EI HUMBOLDT-TRINITY 75/5 RPR GYWW | ICW
LC | 121362502 | 075/002 | T2 EI HUMBOLDT-TRINITY 75/002 RPR STRW | EUREKA | ETL.1820.POLE.STPS | 2021-05-19 | 2021-05-19 | 2022-06-05 | 2022-05-19 | 2022-05-19 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45147814 | T2 EI HUMBOLDT-TRINITY 75/002 RPR STRW | ICW
LC | 121362665 | 010/078A | T2 EI HELMS-GREGG #1 10/078A RPR FOND | FRESNO | ETL.4870.TOWR | 2021-05-19 | 2021-05-19 | 2022-06-10 | 2022-05-19 | 2022-05-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45070019 | T2 EI HELMS-GREGG #1 10/078A RPR FOND | ICQ
LC | 121362672 | 010/077A | T2 EI HELMS-GREGG #1 10/077A RPR FOND | FRESNO | ETL.4870.TOWR | 2021-05-19 | 2021-05-19 | 2022-06-08 | 2022-05-19 | 2022-05-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45070060 | T2 EI HELMS-GREGG #1 10/077A RPR FOND | ICQ
LC | 121362927 | 020/160 | T2 WV PARADISE-TABLE MTN 20/160 RPL INSW | TABLEMTN | ETL.4316.INSL.NCER | 2021-05-19 | 2021-05-19 | 2022-05-12 | 2022-05-19 | 2022-05-19 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541588 | T3 WV PARADISE-TABLE MTN 22/173 RPL INSW | 93I
LC | 121363537 | 059/002 | T2 EI HUMBOLDT-TRINITY 59/2L RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-19 | 2021-05-19 | 2022-03-30 | 2022-05-19 | 2022-05-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45145441 | T2 EI HUMBOLDT-TRINITY 59/2L RPR STRW | ICW
LC | 121363620 | 059/002B | T2 EI HUMBOLDT-TRINITY 59/2L RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2021-05-19 | 2021-05-19 | 2022-03-30 | 2022-05-19 | 2022-05-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44830121 | T2 EI HUMBOLDT-TRINITY 59/2L RPR INSW | ICW
LC | 121363630 | 061/003 | T2 EI HUMBOLDT-TRINITY 61/3L RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2021-05-19 | 2021-05-19 | 2022-03-30 | 2022-05-19 | 2022-05-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145449 | T2NT EI HUMBOLDT-TRINITY 61/3R RMV DBRS | ICW
LC | 121363714 | 005/009 | T2 DI CHWCHLLA-KRCKHFF 005/009 RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-05-19 | 2021-05-01 | 2022-02-17 | 2022-05-01 | 2022-05-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581055 | T2 DI CHOWCHILLA-KERCKHOFF 7/4 RPL STRW | 70Y
LC | 121363719 | 026/121 | T2 DI TESLA-LOS BNS #1 026/121 RPR GYWS | VICTOR | ETL.6100.TOWR | 2021-05-19 | 2021-04-28 | 2022-05-03 | 2022-04-28 | 2022-04-28 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45150296 | T2 DI TESLA-LOS BNS #1 026/121 RPR GYWS | ICS
LC | 121363834 | 005/006 | T2 DI CHWCHLL-KRCKHFF 5/006 RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-05-19 | 2021-05-01 | 2022-02-11 | 2022-05-01 | 2022-05-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581056 | T2 DI CHOWCHILLA-KERCKHOFF 2/5 RPL STRW | 70Y
LC | 121363843 | 015/061 | T2 DI DIABLO-MIDWAY #2 015/061 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-05-19 | 2021-04-30 | 2022-05-24 | 2022-04-30 | 2022-04-30 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068543 | T2 DI DIABLO-MIDWAY #2 015/061 RPR GYWS | ICS
LC | 121363875 | 011/376 | T2 DI SPAULDING-SUMMIT 11/376 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-05-19 | 2021-05-18 | 2022-09-18 | 2022-05-18 | 2022-05-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600750 | T2 DI SPAULDING-SUMMIT 11/376 RPL STRW | 70Y
LC | 121363877 | X007/032 | T2DI DIABLO-MESA X7/32 RPR SHLS | PISMOBCH | ETL.4620.TOWR | 2021-05-19 | 2021-04-29 | 2022-01-24 | 2022-04-29 | 2022-04-29 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45098624 | T2DI DIABLO-MESA X7/32 RPR SHLS | ICS
LC | 121363917 | 026/120 | T2 DI TSLA-LS BNS #1 026/120 GROUNDWASH | VICTOR | ETL.6100.INSL | 2021-05-19 | 2021-04-30 | 2022-08-01 | 2022-04-30 | 2022-04-30 | Late | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Contaminated | Insulator | Ground Wash | 45150297 | T2 DI TSLA-LS BNS #1 026/120 GROUNDWASH | ICD
LC | 121364041 | 021/294 | T2 DI SSQC SNTA YNZ SS 021/294 RMV DBRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-05-19 | 2021-04-27 | 2022-02-01 | 2022-04-27 | 2022-04-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45069341 | T2 DI SSQC SNTA YNZ SS 021/294 RMV DBRW | ICW
LC | 121364067 | 006/002A | T2 DI CHOWCHILLA-KERCKHOFF 6/2A RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-05-19 | 2021-05-01 | 2022-02-11 | 2022-05-01 | 2022-05-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581055 | T2 DI CHOWCHILLA-KERCKHOFF 7/4 RPL STRW | 70Y
LC | 121364075 | 004/004 | T2 DI FULTON-HOPLAND 004/004 RMV VEG | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-05-19 | 2021-04-26 | 2022-02-10 | 2022-04-26 | 2022-04-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121364118 | 008/007 | T2 DI SLNS-FRTORD#2-FTORD#2 8/7 RPL HRDT | MOSSLNDG | ETL.8423.POLE.NWOD | 2021-05-19 | 2021-04-27 | 2022-03-10 | 2022-04-27 | 2022-04-27 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45149228 | T2 DI SLNS-FRTORD#2-FTORD#2 8/7 RPL HRDT | ICQ
LC | 121364132 | 020/277 | T2 DI SQUC-SNT YNZ S 20/277 RMV BUTT COA | PISMOBCH | ETL.3700.POLE.WOOD | 2021-05-19 | 2021-04-27 | 2022-03-03 | 2022-04-27 | 2022-04-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45069343 | T2 DI SSQUC-SNTA YNEZ SW 20/277 RMV BUTT | ICW
LC | 121364150 | 006/007 | T2 DI CHOWCHILLA-KERCKHOFF 6/7 RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-05-19 | 2021-05-01 | 2022-02-18 | 2022-05-01 | 2022-05-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581055 | T2 DI CHOWCHILLA-KERCKHOFF 7/4 RPL STRW | 70Y
LC | 121364193 | 032/149 | T2 DI TRACY-LOS BANOS- 32/149 RPR GYWS | VICTOR | ETL.6130.TOWR | 2021-05-19 | 2021-04-30 | 2022-05-03 | 2022-04-30 | 2022-04-30 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45150298 | T2 DI TRACY-LOS BANOS- 32/149 RPR GYWS | ICS
LC | 121364260 | 025/113 | T2 DI TESLA-LOS BANOS #1 025/113 RPL INS | VICTOR | ETL.6100.INSL | 2021-05-19 | 2021-04-30 | 2022-04-13 | 2022-04-30 | 2022-04-30 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31541683 | DI TESLA-LOS BANOS #1 RPL INSS 7TWRS | 93K
LC | 121364796 | 030/457 | T2 CLAY-MARTEL 30/457 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-20 | 2021-05-20 | 2022-07-25 | 2022-05-20 | 2022-05-20 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540922 | T2 CLAY-MARTEL 30/457 RPL STRW | 70Y
LC | 121365085 | 088/000 | T2 EI HUMBOLDT-TRINITY 88/0 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-05-20 | 2021-05-19 | 2022-10-11 | 2022-05-19 | 2022-05-19 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542139 | T2 EI HUMBOLDT-TRINITY 088/000 RPL INSW | 93I
LC | 121365088 | 087/003 | T2 EI HUMBOLDT-TRINITY 87/3L RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-05-20 | 2021-05-19 | 2022-10-20 | 2022-05-19 | 2022-05-19 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542138 | T2 EI HUMBOLDT-TRINITY 87/3L RPL INSW | 93I
LC | 121365432 | 005/008 | T2 DI CHOWCHILLA-KERCKHOFF 5/8 RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-05-20 | 2021-05-01 | 2022-02-17 | 2022-05-01 | 2022-05-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581056 | T2 DI CHOWCHILLA-KERCKHOFF 2/5 RPL STRW | 70Y
LC | 121365999 | 033/154 | T2 DI TRACY-LOS BANOS 33/154 RPR GYWS | VICTOR | ETL.6130.TOWR | 2021-05-20 | 2021-04-28 | 2022-05-03 | 2022-04-28 | 2022-04-28 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45150605 | T2 DI TRACY-LOS BANOS 33/154 RPR GYWS | ICS
LC | 121367466 | 006/001 | T2 DI CHOWCHILLA-KERCKHOFF 6/1 RMV BUTT | FRESNO | ETL.1250.POLE.NWOD | 2021-05-20 | 2021-05-01 | 2022-02-18 | 2022-05-01 | 2022-05-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45069216 | T2 DI CHOWCHILLA-KERCKHOFF 6/1 RMV BUTT | ICW
LC | 121369012 | 078/002B | T2 EI HUMBOLDT-TRINITY 78/2B RPR ANCS | EUREKA | ETL.1820.POLE.NWOD | 2021-05-20 | 2021-05-20 | 2022-06-02 | 2022-05-20 | 2022-05-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Steel | Repair | 45148678 | T2 EI HUMBOLDT-TRINITY 78/2B RPR ANCS | ICS
LC | 121369093 | 009/074A | T2 EI HELMS-GREGG #1 9/74A RMV NEST | FRESNO | ETL.4870.TOWR | 2021-05-20 | 2021-05-20 | 2022-08-24 | 2022-05-20 | 2022-05-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Debris/Nest/etc. | Conductor-Steel | Remove | 45069483 | T2 EI HELMS-GREGG #1 9/74A RMV NEST | ICS
LC | 121369103 | 011/080A | T2 EI HELMS-GREGG #1 11/80A COMPLETE | FRESNO | ETL.4870.TOWR | 2021-05-20 | 2021-05-20 | 2022-06-10 | 2022-05-20 | 2022-05-20 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45070061 | T2 EI HELMS-GREGG #1 11/80A RPR FOND | ICQ
LC | 121369104 | 011/081A | T2 EI HELMS-GREGG #1 11/81A RMV NEST | FRESNO | ETL.4870.TOWR | 2021-05-20 | 2021-05-20 | 2022-08-25 | 2022-05-20 | 2022-05-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Debris/Nest/etc. | Conductor-Steel | Remove | 45069484 | T2 EI HELMS-GREGG #1 11/81A RMV NEST | ICS
LC | 121369281 | 076/002A | T2 EI HMBLDT-TRNTY 76/2A-R RPR SPLW COA | EUREKA | ETL.1820.INSL.CERA | 2021-05-20 | 2021-05-20 | 2022-10-19 | 2022-05-20 | 2022-05-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 44888151 | T2 EI HUMBOLDT-TRINITY 76/2A-R RPR SPLW | ICW
LC | 121369414 | 076/003 | T2 EI HUMBOLDT-TRINITY 76/3 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-05-20 | 2021-05-20 | 2022-06-03 | 2022-05-20 | 2022-05-20 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542134 | T2 EI HUMBOLDT-TRINITY 76/3L RPL INSW | 93I
LC | 121369472 | 019/158 | T2 WV PARADISE-TABLE MTN 19/158 RPL INSW | TABLEMTN | ETL.4316.INSL.NCER | 2021-05-20 | 2021-05-20 | 2022-05-14 | 2022-05-20 | 2022-05-20 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541588 | T3 WV PARADISE-TABLE MTN 22/173 RPL INSW | 93I
LC | 121370090 | 005/001 | T2 DI CHOWCHILLA-KRCKHOFF 5/1 RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-05-20 | 2021-05-01 | 2022-02-15 | 2022-05-01 | 2022-05-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581056 | T2 DI CHOWCHILLA-KERCKHOFF 2/5 RPL STRW | 70Y
LC | 121370122 | 062/000 | T2 EI HUMBOLDT-TRINITY 62/000L RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-20 | 2021-05-20 | 2022-06-08 | 2022-05-20 | 2022-05-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45145451 | T2 EI HUMBOLDT-TRINITY 62/000L RPR STRW | ICW
LC | 121370253 | 087/002A | T2 EI HUMBOLDT-TRINITY 87/2A RPR GYWS | EUREKA | ETL.1820.POLE.NWOD | 2021-05-20 | 2021-05-20 | 2022-10-11 | 2022-05-20 | 2022-05-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45149355 | T2 EI HUMBOLDT-TRINITY 87/2A RPR GYWS | ICS
LC | 121370412 | 003/001 | T2 DI CHOWCHILLA-KERCKHOFF 3/1 RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-05-20 | 2021-05-01 | 2022-02-11 | 2022-05-01 | 2022-05-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581056 | T2 DI CHOWCHILLA-KERCKHOFF 2/5 RPL STRW | 70Y
LC | 121370457 | 004/031 | T2 DI COTTONWOOD-DELEVN #1 4/31 RPR SHLS | TABLEMTN | ETL.4550.INSL | 2021-05-20 | 2021-05-04 | 2022-06-10 | 2022-05-04 | 2022-05-04 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45147280 | T2 DI COTTONWOOD-DELEVN #1 4/31 RPR SHLS | ICS
LC | 121370641 | 027/118 | T2 DI QUNTO SW STA-WSTLY 27/118 RPR FOND | FRESNO | ETL.5070.TOWR | 2021-05-20 | 2021-05-04 | 2022-04-06 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45110320 | T2 DI QUNTO SW STA-WSTLY 27/118 RPR FOND | ICQ
LC | 121370642 | 027/118 | T2 DI QUNTO SW STA-WSTLY 27/118 RPL HRDT | FRESNO | ETL.5070.TOWR | 2021-05-20 | 2021-05-04 | 2022-02-25 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45110321 | T2 DI QUNTO SW STA-WSTLY 27/118 RPL HRDT | ICQ
LC | 121370749 | 006/003 | T2 DI CHWCHLLA-KRCKHFF 006/003 RMV BUTT | FRESNO | ETL.1250.POLE.NWOD | 2021-05-20 | 2021-05-01 | 2022-02-11 | 2022-05-01 | 2022-05-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45068309 | T2 DI CHWCHLLA-KRCKHFF 006/003 RMV BUTT | ICW
LC | 121370834 | 004/003 | T2 DI CHOWCHILLA-KERCKHOFF 4/3 RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-05-20 | 2021-05-01 | 2022-02-14 | 2022-05-01 | 2022-05-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581056 | T2 DI CHOWCHILLA-KERCKHOFF 2/5 RPL STRW | 70Y
LC | 121370838 | 001/008 | T2 DI MRG-CSTR VLY 001/008 RPR HRDT | CONCORD | ETL.5250.TOWR | 2021-05-20 | 2021-05-04 | 2022-01-21 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45147227 | T2 DI MRG-CSTR VLY 001/008 RPR HRDT | ICQ
LC | 121370881 | 006/002 | T2 DI CHWCHLLA-KRCKHFF 006/002 RMV BUTT | FRESNO | ETL.1250.POLE.NWOD | 2021-05-20 | 2021-05-01 | 2022-02-17 | 2022-05-01 | 2022-05-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45068302 | T2 DI CHWCHLLA-KRCKHFF 006/002 RMV BUTT | ICW
LC | 121370887 | 039/166 | T2 DI TEMPLETON-GATES 039/166 RPR FOND | PISMOBCH | ETL.5934.TOWR | 2021-05-20 | 2021-05-04 | 2022-06-15 | 2022-05-04 | 2022-05-04 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45077924 | T2 DI TEMPLETON-GATES 039/166 RPR FOND | ICQ
LC | 121370913 | 027/119 | T2 DI QNT SW ST-WSLY-WSLY 27/119 RPL HRD | FRESNO | ETL.5070.TOWR | 2021-05-20 | 2021-05-04 | 2022-02-25 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45110322 | T2 DI QNT SW ST-WSLY-WSLY 27/119 RPL HRD | ICQ
LC | 121370916 | 004/006 | T2 DI CHWCLA-KRCKHFF 4/6 RMV BUTT | FRESNO | ETL.1250.POLE.WOOD | 2021-05-20 | 2021-05-01 | 2022-01-28 | 2022-05-01 | 2022-05-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45068255 | T2 DI CHWCLA-KRCKHFF 4/6 RMV BUTT | ICW
LC | 121370945 | 025/113 | T2 DI QNO STA-WSTL-WSTL 25/113 INS HRDT | FRESNO | ETL.5070.TOWR | 2021-05-20 | 2021-05-04 | 2022-04-08 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45110372 | T2 DI QNO STA-WSTL-WSTL 25/113 INS HRDT | ICQ
LC | 121370946 | 025/113 | T2 DI QNO STA-WSTL-WSTL 25/113 RPR FOND | FRESNO | ETL.5070.TOWR | 2021-05-20 | 2021-05-04 | 2022-04-08 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45110373 | T2 DI QNO STA-WSTL-WSTL 25/113 RPR FOND | ICQ
LC | 121370956 | 071/619 | T2 DI CTNWD-DELEVAN #2 71/69 RPLC HRDT | TABLEMTN | ETL.4580.TOWR | 2021-05-20 | 2021-05-04 | 2021-01-05 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45107507 | T2 DI CTNWD-DELEVAN #2 71/69 RPLC HRDT | ICQ
LC | 121370978 | 001/005 | T2 DI CHOWCHILLA-KERCKHOFF 1/5 RMV BUTT | FRESNO | ETL.1250.POLE.NWOD | 2021-05-20 | 2021-05-01 | 2022-02-14 | 2022-05-01 | 2022-05-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45068254 | T2 DI CHOWCHILLA-KERCKHOFF 1/5 RMV BUTT | ICW
LC | 121371019 | 065/579 | T2 DI COTTONWOD-DLVAN #2 65/579 RPL INSS | TABLEMTN | ETL.4580.INSL.CERA | 2021-05-20 | 2021-05-04 | 2022-06-07 | 2022-05-04 | 2022-05-04 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540712 | T2 EI CTONWD-DELEVAN #2 RPL INSS 9TWRS | 93K
LC | 121371129 | 026/116 | T2 DI QUINTO-WSTLY 26/116 RPR FOND | FRESNO | ETL.5070.TOWR | 2021-05-20 | 2021-05-04 | 2022-04-08 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45110374 | T2 DI QUINTO-WSTLY 26/116 RPR FOND | ICQ
LC | 121371231 | 007/001 | T2 DI CHWCHLLA-KRCKHFF 007/001 RMV BUTT | FRESNO | ETL.1250.POLE.WOOD | 2021-05-20 | 2021-05-01 | 2022-02-10 | 2022-05-01 | 2022-05-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45068250 | T2 DI CHWCHLLA-KRCKHFF 007/001 RMV BUTT | ICW
LC | 121371254 | 087/002C | T2 EI HUMBOLDT-TRINITY 87/2C RPR GYWS | EUREKA | ETL.1820.POLE.NWOD | 2021-05-20 | 2021-05-20 | 2022-10-11 | 2022-05-20 | 2022-05-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45149355 | T2 EI HUMBOLDT-TRINITY 87/2A RPR GYWS | ICS
LC | 121371265 | 087/002B | T2 EI HUMBOLDT-TRINITY 87/2B RPR GYWS | EUREKA | ETL.1820.POLE.NWOD | 2021-05-20 | 2021-05-20 | 2022-10-11 | 2022-05-20 | 2022-05-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45149355 | T2 EI HUMBOLDT-TRINITY 87/2A RPR GYWS | ICS
LC | 121372146 | 012/060 | T2 DI SLVDO FLTN JCT SW 012/060 RPL INSS | LAKEVLLE | ETL.1610.SWIT | 2021-05-21 | 2021-05-17 | 2022-03-07 | 2022-05-17 | 2022-05-17 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548688 | T2 DI SLVDO FLTN JCT SW RPL INSS 6TWRS | 93K
LC | 121372764 | :008/005 | T2 DI BLTA RVK MLNS SS :8/5 RPL INSW | VICTOR | ETL.1070.INSL.NCER | 2021-05-21 | 2021-05-20 | 2022-05-06 | 2022-05-20 | 2022-05-20 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545223 | T2 DI BLTA RVK MLNS SS :011/004 RPL INSW | 93I
LC | 121372765 | :008/005 | T2 DI BLTA RVK MLNS SS :8/5 RMV BUTT | VICTOR | ETL.1070.POLE.WOOD | 2021-05-21 | 2021-05-20 | 2022-02-17 | 2022-05-20 | 2022-05-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45155826 | T2 DI BLTA RVK MLNS SS :8/5 RMV BUTT | ICW
LC | 121372985 | 012/250 | T2 EI COTTONWD-RED BLUFF 12/250 RPR ROAD | TABLEMTN | ETL.6660.POLE.WOOD | 2021-05-21 | 2021-05-21 | 2021-12-02 | 2022-05-21 | 2022-05-21 | On-time | 932 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Fence / Gate | Repair | 31530274 | 2021 TABLE MTN GATES | 71Y
LC | 121373036 | 024/109 | T2 DI QUNTOSWSTA-WSLY-TWR 24/I9 RPR OPGW | VICTOR | ETL.5070.TOWR | 2021-05-21 | 2021-05-04 | 2022-03-10 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45166651 | T2 DI QUNTOSWSTA-WSLY-TWR 24/I9 RPR OPGW | ICS
LC | 121373138 | 026/117 | T2 DI QNTOSWSTA-WSLY-TWR 26/117 RPR SHLW | VICTOR | ETL.5070.TOWR | 2021-05-21 | 2021-05-04 | 2022-06-02 | 2022-05-04 | 2022-05-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45166652 | T2 DI QNTOSWSTA-WSLY-TWR 26/117 RPR SHLW | ICW
LC | 121373176 | 003/024 | T2 DI CTTNWD-DELVN #1 3/24 REPAIR SHLS | TABLEMTN | ETL.4550.TOWR | 2021-05-21 | 2021-05-04 | 2022-05-19 | 2022-05-04 | 2022-05-04 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45240550 | T2 DI CTTNWD-DELVN #1 3/24 REPAIR SHLS | ICS
LC | 121373204 | 005/035 | T2 DI COTTONWOOD-DELEVN #1 5/35 RPR SHLS | TABLEMTN | ETL.4550.INSL | 2021-05-21 | 2021-05-04 | 2021-06-15 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44875338 | T2 DI COTTONWOOD-DELEVN #1 5/35 RPR SHLS | ICS
LC | 121373206 | 048/203 | T2 DI TEMPLETON-GATES 48/203 RPR SHLS | PISMOBCH | ETL.5934.TOWR | 2021-05-21 | 2021-05-04 | 2021-09-14 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44963185 | T2 DI TEMPLETON-GATES 48/203 RPR SHLS | ICS
LC | 121373391 | 027/120 | T2 DI QUINTO-WSTLY 27/120 INS HRDT | FRESNO | ETL.5070.TOWR | 2021-05-21 | 2021-05-04 | 2022-02-25 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45110376 | T2 DI QUINTO-WSTLY 27/120 INS HRDT | ICQ
LC | 121373402 | 005/040 | T2 DI COTTONWOOD-DELEVN #1 5/40 RPR SHLS | TABLEMTN | ETL.4550.INSL | 2021-05-21 | 2021-05-04 | 2022-05-20 | 2022-05-04 | 2022-05-04 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45147281 | T2 DI COTTONWOOD-DELEVN #1 5/40 RPR SHLS | ICS
LC | 121373410 | 026/117 | T2 DI QUNTOSWSTA-WSLY 26/117 WASH INSS | VICTOR | ETL.5070.INSL | 2021-05-21 | 2021-05-04 | 2022-08-25 | 2022-05-04 | 2022-05-04 | Late | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | Contaminated | Insulator | Ground Wash | 45166653 | T2 DI QUNTOSWSTA-WSLY 26/117 WASH INSS | ICD
LC | 121373442 | 027/120 | T2 DI QUINTO-WSTLY 27/120 RPR FOND | FRESNO | ETL.5070.TOWR | 2021-05-21 | 2021-05-04 | 2022-04-05 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45110377 | T2 DI QUINTO-WSTLY 27/120 RPR FOND | ICQ
LC | 121373644 | 036/153 | T2 DI TEMPLETON-GATES 036/153 RPR FOND | PISMOBCH | ETL.5934.TOWR | 2021-05-21 | 2021-05-04 | 2022-06-02 | 2022-05-04 | 2022-05-04 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45077927 | T2 DI TEMPLETON-GATES 036/153 RPR FOND | ICQ
LC | 121373658 | 008/055 | T2 DI COTTONWOOD-LOGAN CRK 8/55 RPR OPGW | TABLEMTN | ETL.4570.INSL | 2021-05-21 | 2021-05-04 | 2022-03-17 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45182721 | T2 DI COTTONWOOD-LOGAN CRK 8/55 RPR OPGW | ICS
LC | 121373737 | 013/057 | T2 DI MORAGA-CASTRO VLY 13/57 RPR STRT | CONCORD | ETL.5250.TOWR | 2021-05-21 | 2021-05-04 | 2022-01-23 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45145855 | T2 DI MORAGA-CASTRO VLY 13/57 RPR STRT | ICQ
LC | 121373739 | 013/057 | T2 DI MORAGA-CASTRO VLY 13/57 RPR SHLS | CONCORD | ETL.5250.TOWR | 2021-05-21 | 2021-05-04 | 2022-02-01 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45137544 | T2 DI MORAGA-CASTRO VLY 13/57 RPR SHLS | ICS
LC | 121373766 | 005/036 | T2 DI COTTONWOOD-DELEVAN#1 5/36 RPR SHLS | TABLEMTN | ETL.4550.TOWR | 2021-05-21 | 2021-05-03 | 2022-05-19 | 2022-05-03 | 2022-05-03 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45147282 | T2 DI COTTONWOOD-DELEVAN#1 5/36 RPR SHLS | ICS
LC | 121373793 | 065/578 | T2 DI COTTONWOOD DLVN #2 65/578 RPL INSS | TABLEMTN | ETL.4580.INSL.CERA | 2021-05-21 | 2021-05-04 | 2022-06-07 | 2022-05-04 | 2022-05-04 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540712 | T2 EI CTONWD-DELEVAN #2 RPL INSS 9TWRS | 93K
LC | 121373796 | 065/578 | T2 DI COTTONWOOD- GELENN 65/578 RPL INSS | TABLEMTN | ETL.4560.INSL | 2021-05-21 | 2021-05-04 | 2022-03-29 | 2022-05-04 | 2022-05-04 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534508 | DI COTTONWOOD-GLENN RPLC INSS 7TWRS | 93K
LC | 121373825 | 000/001 | T2 DI MORAGA-CASTRO VALLEY 0/1 RPL INSS | CONCORD | ETL.5250.INSL | 2021-05-21 | 2021-05-04 | 2022-03-31 | 2022-05-04 | 2022-05-04 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31543053 | T2 DI MORAGA-CASTRO VALLEY RPL INSS 7TWR | 93K
LC | 121374057 | :011/009 | T2 DI BLLTA-RVRBNK-MLNS :11/9 RPR STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-05-21 | 2021-05-06 | 2022-02-25 | 2022-05-06 | 2022-05-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45155831 | T2 DI BLLTA-RVRBNK-MLNS :11/9 RPR STRW | ICW
LC | 121374162 | 039/165 | T2 DI TEMPLETON-GATES 039/165 RPR OPGW | PISMOBCH | ETL.5934.TOWR | 2021-05-21 | 2021-05-04 | 2021-09-14 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44963184 | T2 DI TEMPLETON-GATES 039/165 RPR OPGW | ICS
LC | 121374197 | 014/206 | T2 DI SSQC-SNT YNZ SW ST 14/206 RPL PL | PISMOBCH | ETL.3700.POLE.WOOD | 2021-05-21 | 2021-05-06 | 2022-04-12 | 2022-05-06 | 2022-05-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540464 | DI SSQC-SNTA YNEZ SS 011/177 RPL POLE | 70Y
LC | 121374233 | X005/024 | T2 DI DIABLO-MESA-TOWER X5/24 RPR OPGW | PISMOBCH | ETL.4620.TOWR | 2021-05-21 | 2021-04-28 | 2022-01-24 | 2022-04-28 | 2022-04-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45098623 | T2 DI DIABLO-MESA-TOWER X5/24 RPR OPGW | ICS
LC | 121374274 | 011/196 | T2 DI TEJON-LEBEC 011/196 RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2021-08-11 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44944101 | T2 DI TEJON-LEBEC 011/196 RPR GYWW | ICW
LC | 121374597 | 068/597 | T2 DI CTNWD-DLVN #2 68/597 RPR FOND | TABLEMTN | ETL.4580.TOWR | 2021-05-21 | 2021-05-04 | 2022-01-06 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45107499 | T2 DI CTNWD-DLVN #2 68/597 RPR FOND | ICQ
LC | 121374598 | 003/025 | T2 DI CTNWD-DLVN #1 3/25 RMV STEP | TABLEMTN | ETL.4550.TOWR | 2021-05-21 | 2021-05-04 | 2021-12-16 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45093806 | T2 DI CTNWD-DLVN #1 3/25 RMV STEP | ICQ
LC | 121374650 | 006/044 | T2 WV SAN LUIS OBISPO-CYCS 6/44 RPL INSW | PISMOBCH | ETL.9090.INSL.NCER | 2021-05-21 | 2021-05-21 | 2022-05-05 | 2022-05-21 | 2022-05-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543116 | T2 WV SAN LUIS OBISPO-CYCS 6/44 RPL INSW | 93I
LC | 121374682 | 017/141 | T2 DI DRUM-RIO OSO #1 017/141 INS HWRT | SACTO | ETL.1420.TOWR | 2021-05-21 | 2021-05-06 | 2022-05-23 | 2022-05-06 | 2022-05-06 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45074332 | T2 DI DRUM-RIO OSO #1 017/141 INS HWRT | ICQ
LC | 121374685 | 025/112 | T2 DI QUNTO SW STA-WEST 025/12 RPR FOND | FRESNO | ETL.5070.TOWR | 2021-05-21 | 2021-05-04 | 2022-04-08 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45110378 | T2 DI QUNTO SW STA-WEST 025/12 RPR FOND | ICQ
LC | 121374686 | 025/112 | T2 DI QUNTO SW STA-WST 025/112 RPR OPGW | VICTOR | ETL.5070.TOWR | 2021-05-21 | 2021-05-04 | 2022-06-02 | 2022-05-04 | 2022-05-04 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45166654 | T2 DI QUNTO SW STA-WST 025/112 RPR OPGW | ICS
LC | 121374716 | 064/573 | T2 DI COTTONWD DLVN #2 64/573 RMV STEP | TABLEMTN | ETL.4580.TOWR | 2021-05-21 | 2021-05-04 | 2022-01-11 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45107491 | T2 DI COTTONWD DLVN #2 64/573 RMV STEP | ICQ
LC | 121374752 | 013/066 | T2 EI CONTRA CSTA-MRGA #1 13/66 RPL INSS | CONCORD | ETL.5452.INSL.CERA | 2021-05-21 | 2021-05-19 | 2021-11-03 | 2022-05-19 | 2022-05-19 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO SR21 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31544514 | T2 EI CONTRA CSTA-MRGA #1 13/66 RPL INSS | 93K
LC | 121374767 | 017/391 | T2 DI DRM-GRSS VLLY-WMR 17/391 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2022-06-29 | 2022-05-05 | 2022-05-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45074333 | T2 DI DRM-GRSS VLLY-WMR 17/391 RPR STRW | ICW
LC | 121374873 | 064/574 | T2 DI CTNWD-DLVN #2 64/574 RMV STEP | TABLEMTN | ETL.4580.TOWR | 2021-05-21 | 2021-05-04 | 2022-01-11 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45107492 | T2 DI CTNWD-DLVN #2 64/574 RMV STEP | ICQ
LC | 121374875 | 004/030 | T2 DI COTTONWOOD-DLVN #1 4/30 RMV STEP | TABLEMTN | ETL.4550.TOWR | 2021-05-21 | 2021-05-04 | 2021-12-20 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45097423 | T2 DI COTTONWOOD-DLVN #1 4/30 RMV STEP | ICQ
LC | 121375012 | 001/013 | T2 CHRISTIE-FRANKLIN #1 001/013 RPL POLE | CONCORD | ETL.6350.POLE.WOOD | 2021-05-21 | 2021-05-20 | 2022-02-26 | 2022-05-20 | 2022-05-20 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543395 | T2 CHRISTIE-FRANKLIN #1 001/013 RPL POLE | 70Y
LC | 121375057 | 001/015 | T2 CHRISTIE-FRANKLIN #1 1/015 RPL POLE | CONCORD | ETL.6350.POLE.WOOD | 2021-05-21 | 2021-05-20 | 2022-02-25 | 2022-05-20 | 2022-05-20 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543395 | T2 CHRISTIE-FRANKLIN #1 001/013 RPL POLE | 70Y
LC | 121375085 | 008/056 | T2 DI CTTNWD-DLVN #1 008/056 RPR SHLS | TABLEMTN | ETL.4550.INSL | 2021-05-21 | 2021-05-04 | 2022-05-22 | 2022-05-04 | 2022-05-04 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45147283 | T2 DI CTTNWD-DLVN #1 008/056 RPR SHLS | ICS
LC | 121375104 | 063/568 | T2 DI CTTNWD DLVN #2 063/568 RMV STEP | TABLEMTN | ETL.4580.TOWR | 2021-05-21 | 2021-05-04 | 2022-01-12 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45107489 | T2 DI CTTNWD DLVN #2 063/568 RMV STEP | ICQ
LC | 121375129 | 018/419 | T2 DI DRM-GRS VLY-WMR 18/419 RPR INSS | SACTO | ETL.6760.INSL.CERA | 2021-05-21 | 2021-05-05 | 2022-07-05 | 2022-05-05 | 2022-05-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45074343 | T2 DI DRM-GRS VLY-WMR 18/419 RPR INSS | ICW
LC | 121375149 | 021/492 | T2 DI DRM-GRSS VLLY-WMR 021/492 RMV DEBR | SACTO | ETL.6760.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2022-01-11 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074346 | T2 DI DRM-GRSS VLLY-WMR 021/492 RMV DEBR | ICW
LC | 121375324 | 063/570 | T2 DI CTNWD DLVN #2 63/570 RPR FOND | TABLEMTN | ETL.4580.TOWR | 2021-05-21 | 2021-05-04 | 2022-06-07 | 2022-05-04 | 2022-05-04 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45107490 | T2 DI CTNWD DLVN #2 63/570 RPR FOND | ICQ
LC | 121375326 | 011/191 | T2 DI TEJON-LEBEC 11/191 RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2021-08-11 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44930596 | T2 DI TEJON-LEBEC 11/191 RPR GYWW | ICW
LC | 121375600 | :006/034 | T2 DI STN MEL SS-RVRBNK :6/34 RPR SPLS | VICTOR | ETL.3840.INSL.NCER | 2021-05-21 | 2021-05-21 | 2022-05-18 | 2022-05-21 | 2022-05-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45122134 | T2 DI STN MEL SS-RVRBNK :6/34 RPR SPLS | ICS
LC | 121375928 | 008/102 | T2 DI DRUM-SUMMIT#1 8/102 RPL INSS | SACTO | ETL.1440.TOWR | 2021-05-21 | 2021-05-21 | 2022-08-30 | 2022-05-21 | 2022-05-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31614878 | T2 DI DRUM-SUMMIT#1 8/102 RPL INSS | 93K
LC | 121375963 | 019/450 | T2 DI DRM-GRS VLY-WMR 19/450 RMV BUTT | SACTO | ETL.6760.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2022-01-12 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074349 | T2 DI DRM-GRS VLY-WMR 19/450 RMV BUTT | ICW
LC | 121375965 | 063/564 | T2 DI CTNWD-DLVN #2 63/564 RMV STEP | TABLEMTN | ETL.4580.TOWR | 2021-05-21 | 2021-05-04 | 2022-01-12 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45107487 | T2 DI CTNWD-DLVN #2 63/564 RMV STEP | ICQ
LC | 121376022 | 016/368 | T2 DI DRM-GRS VLY-WMR 16/368 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2022-06-28 | 2022-05-05 | 2022-05-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45074353 | T2 DI DRM-GRS VLY-WMR 16/368 RPR GYWW | ICW
LC | 121376130 | 020/461 | T2 DI DRM-GRSS VLLY-WMR 020/461 RMV DBRS | SACTO | ETL.6760.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2022-01-11 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074354 | T2 DI DRM-GRSS VLLY-WMR 020/461 RMV DBRS | ICW
LC | 121376136 | 020/461 | T2 DI DRM-GRSS VLLY-WMR 020/461 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2022-03-30 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45074358 | T2 DI DRM-GRSS VLLY-WMR 020/461 RPR STRW | ICW
LC | 121376307 | 020/473 | T2 DI DRM-GRSVAL-WEIMAR X20/473 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2022-03-31 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45074361 | T2 DI DRM-GRSVAL-WEIMAR X20/473 RPR STRW | ICW
LC | 121376396 | 034/152 | T2 DI MOSS LDNG-LOS BANS 34/152 RPL INSS | MOSSLNDG | ETL.6040.INSL.CERA | 2021-05-21 | 2021-05-21 | 2021-12-17 | 2022-05-21 | 2022-05-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31544846 | T2 EI MSS LNDING-LOS BNOS RPL INSS 4TWR | 93K
LC | 121376442 | 011/161 | T2 DI SISQUOC-SNTA YNZ 11/161 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-05-21 | 2021-05-06 | 2022-02-15 | 2022-05-06 | 2022-05-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069344 | T2 DI SISQUOC-SNTA YNZ 11/161 RPR STRW | ICW
LC | 121376525 | 017/389 | T2 DI DRM-GRSS VLY-WMR 017/389 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2022-03-25 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45074366 | T2 DI DRM-GRSS VLY-WMR 017/389 RPR STRW | ICW
LC | 121376529 | 017/389 | T2 DI DRM-GRSS VLY-WMR 017/389 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2022-03-25 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45074368 | T2 DI DRM-GRSS VLY-WMR 017/389 RPR GYWW | ICW
LC | 121376589 | 000/005 | T2 DI MRGA-CSTRO VLLY 000/005 RPR SHLS | CONCORD | ETL.5250.TOWR | 2021-05-21 | 2021-05-04 | 2022-02-09 | 2022-05-04 | 2022-05-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45144672 | T2 DI MRGA-CSTRO VLLY 000/005 RPR SHLS | ICS
LC | 121376608 | 003/028 | T2 DI CTTNWD-DLVN #1 003/028 RPL INSS | TABLEMTN | ETL.4550.INSL | 2021-05-21 | 2021-05-04 | 2022-06-10 | 2022-05-04 | 2022-05-04 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546146 | DI COTTONWOOD-DELEVAN #1 RPLC INSS 2TWRS | 93K
LC | 121376672 | 003/028 | T2 DI CTTNWD DLVN #1 003/028 RPR SHLS | TABLEMTN | ETL.4550.TOWR | 2021-05-21 | 2021-05-04 | 2022-06-10 | 2022-05-04 | 2022-05-04 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45147284 | T2 DI CTTNWD DLVN #1 003/028 RPR SHLS | ICS
LC | 121376793 | 011/065 | T2 DI TESLA-NEWARK #1 011/065 RPL INSS | CONCORD | ETL.5720.INSL | 2021-05-21 | 2021-05-04 | 2021-10-01 | 2022-05-04 | 2022-05-04 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31550838 | T2 DI TESLA-NEWARK #1 RPL INSS 2TWRS | 93K
LC | 121377540 | 021/489 | T2 DI DRM-GRS VLY-WMR 21/489 RPR INSW | SACTO | ETL.6760.INSL.NCER | 2021-05-21 | 2021-05-05 | 2022-04-01 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45074380 | T2 DI DRM-GRS VLY-WMR 21/489 RPR INSW | ICW
LC | 121377601 | 020/459 | T2 DI DRUM-GRS VALY-WMAR 20/459 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2022-03-30 | 2022-05-05 | 2022-05-05 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31595647 | T3 DI DRM GRAS VLY WMAR 3/79 RPL STRW | 70Y
LC | 121377780 | 047/227 | T2 DI IGNACIO-SOBRANTE 047/227 RMV STEP | CONCORD | ETL.4920.TOWR | 2021-05-21 | 2021-05-04 | 2022-03-26 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45190696 | T2 DI IGNACIO-SOBRANTE 047/227 RMV STEP | ICQ
LC | 121377788 | 038/159 | T2 DI TEMPLETON-GATES 038/159 RPR FOND | PISMOBCH | ETL.5934.TOWR | 2021-05-21 | 2021-05-04 | 2022-06-16 | 2022-05-04 | 2022-05-04 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45077930 | T2 DI TEMPLETON-GATES 038/159 RPR FOND | ICQ
LC | 121377789 | 038/159 | T2 DI MRR BY-CA. FTS SS 38/159 RPL INSS | PISMOBCH | ETL.5280.INSL.CERA | 2021-05-21 | 2021-05-04 | 2022-07-27 | 2022-05-04 | 2022-05-04 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45098844 | T2 DI MRR BY-CA. FTS SS 38/159 RPL INSS | ICS
LC | 121377792 | :007/002 | T2 DI BLOTA-RVRBNK-MELNS :07/02 RPR STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2022-04-11 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45155836 | T2 DI BLOTA-RVRBNK-MELNS :07/02 RPR STRW | ICW
LC | 121378013 | 063/567 | T2 DI CTTNWD-DLVN #2 063/567 RPL INSS | TABLEMTN | ETL.4580.INSL.CERA | 2021-05-21 | 2021-05-04 | 2022-06-06 | 2022-05-04 | 2022-05-04 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540712 | T2 EI CTONWD-DELEVAN #2 RPL INSS 9TWRS | 93K
LC | 121378014 | 063/567 | T2 DI CTTNWD DLVN #2 063/567 RMV STEP | TABLEMTN | ETL.4580.TOWR | 2021-05-21 | 2021-05-04 | 2022-01-12 | 2022-05-04 | 2022-05-04 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45107488 | T2 DI CTTNWD DLVN #2 063/567 RMV STEP | ICQ
LC | 121378043 | 086/005 | T2 EI HUMBOLDT-TRINITY 86/5R RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-21 | 2021-05-21 | 2022-06-09 | 2022-05-21 | 2022-05-21 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121378045 | 086/005 | T2 EI HUMBOLDT-TRINITY 86/5L RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-21 | 2021-05-21 | 2022-06-09 | 2022-05-21 | 2022-05-21 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121378058 | 086/004 | T2 EI HUMBOLDT-TRINITY 86/4R RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-21 | 2021-05-21 | 2022-10-14 | 2022-05-21 | 2022-05-21 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121378060 | 086/003 | T2 EI HUMBOLDT-TRINITY 86/3C RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-21 | 2021-05-21 | 2021-06-10 | 2022-05-21 | 2022-05-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44851243 | T2 EI HUMBOLDT-TRINITY 86/3C RPR STRW | ICW
LC | 121378061 | 086/004 | T2 EI HUMBOLDT-TRINITY 86/4L RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-21 | 2021-05-21 | 2022-10-14 | 2022-05-21 | 2022-05-21 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121378073 | 001/001 | T2 WV GARCIA TAP 1/1 RPL CNDW | WILLITS | ETL.8411.POLE.WOOD | 2021-05-21 | 2021-05-21 | 2022-07-20 | 2022-05-21 | 2022-05-21 | Late | 638 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Conductor-Wood | Replace | 31541980 | T2 WV GARCIA TAP 1/1 RPL CNDW | 93C
LC | 121378114 | 019/444 | T2 DI DRUM-GRASS VALLEY X19/444 COMPLETE | SACTO | ETL.6760.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2022-03-29 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44896673 | T2 DI DRUM-GRASS VALLEY X19/444 RPR STRW | ICW
LC | 121378215 | 009/080 | T2 DI EL DRD-MSURI FLT #1 9/80 RPL HRDD | SACTO | ETL.1530.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2022-06-24 | 2022-05-05 | 2022-05-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44883160 | T2 DI EL DRD-MSURI FLT #1 9/80 RPL HRDD | ICW
LC | 121378408 | 008/100 | T2 DI W POINT-VLY SPGS 8/100 RPR STRW | VICTOR | ETL.8350.POLE.WOOD | 2021-05-21 | 2021-05-06 | 2022-07-08 | 2022-05-06 | 2022-05-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45156114 | T2 DI W POINT-VLY SPGS 8/100 RPR STRW | ICW
LC | 121378458 | 009/105 | T2 DI W PNT-VLY SPRNGS 9/105 RPL POLE | VICTOR | ETL.8350.INSL.CERA | 2021-05-21 | 2021-05-07 | 2022-05-21 | 2022-05-07 | 2022-05-07 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31543032 | T2 DI WES PNT-VALL SPRG 008/092 REFRAME | 93E
LC | 121378485 | 009/114 | T2 DI W PNT-VLY SPRNGS 9/114 COMPLETE | VICTOR | ETL.8350.POLE.WOOD | 2021-05-21 | 2021-05-07 | 2022-05-25 | 2022-05-07 | 2022-05-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45156040 | T2 DI W PNT-VLY SPRNGS 9/114 RPR STRW | ICW
LC | 121378583 | 009/144 | T2 DI SIQC-SNT YNZ 9/144 RPL STRW CMPLTD | PISMOBCH | ETL.3700.POLE.WOOD | 2021-05-21 | 2021-05-06 | 2022-04-11 | 2022-05-06 | 2022-05-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540464 | DI SSQC-SNTA YNEZ SS 011/177 RPL POLE | 70Y
LC | 121378771 | 012/153 | T2NT DI W PNT-VLY SPRNGS 12/153 RMV STUB | VICTOR | ETL.8350.POLE.NWOD | 2021-05-21 | 2021-05-07 | 2022-05-10 | 2022-05-07 | 2022-05-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2N PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45156041 | T2NT DI W PNT-VLY SPRNGS 12/153 RMV STUB | ICW
LC | 121379050 | 004/007 | T2 DI CHOWCHILLA-KERCKHOFF 4/7 RMV DBRS | FRESNO | ETL.1250.POLE.NWOD | 2021-05-21 | 2021-05-06 | 2022-02-15 | 2022-05-06 | 2022-05-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45068245 | T2 DI CHOWCHILLA-KERCKHOFF 4/7 RMV DBRS | ICW
LC | 121379080 | 009/145 | T2 DI SQC-SNTA YNZ SW STA 9/145 RPR STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-05-21 | 2021-05-06 | 2022-02-15 | 2022-05-06 | 2022-05-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45069345 | T2 DI SQC-SNTA YNZ SW STA 9/145 RPR STRW | ICW
LC | 121379180 | 009/113 | T2 DI WP-VLLEY SPRNGS 9/113 RPR GYWW | VICTOR | ETL.8350.POLE.NWOD | 2021-05-21 | 2021-05-07 | 2022-03-05 | 2022-05-07 | 2022-05-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45156043 | T2 DI WP-VLLEY SPRNGS 9/113 RPR GYWW | ICW
LC | 121379185 | 015/356 | T2 DI DRM-GRSS VLLY-WMR 15/356 RMV BUTT | SACTO | ETL.6760.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2022-03-28 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074407 | T2 DI DRM-GRSS VLLY-WMR 15/356 RMV BUTT | ICW
LC | 121379230 | 018/433 | T2 DI DRM-GRSS VLLY-WMR 18/433 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-05-21 | 2021-05-05 | 2022-07-05 | 2022-05-05 | 2022-05-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541884 | T2 DI DRM-GRS VLY-WMR 15/351 RPL STRW | 70Y
LC | 121379445 | 011/200 | T2 DI TEJON-LEBEC 011/200 RPR SPLW | MIDWAY | ETL.9250.INSL | 2021-05-22 | 2021-05-21 | 2021-08-05 | 2022-05-21 | 2022-05-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 44930597 | T2 DI TEJON-LEBEC 011/200 RPR SPLW | ICW
LC | 121379450 | 007/036 | T2 DI FULTON PUEBLO 007/036 RPL INSS | LAKEVLLE | ETL.1600.INSL | 2021-05-22 | 2021-05-07 | 2022-02-22 | 2022-05-07 | 2022-05-07 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 121379451 | 007/036 | T2 DI SLVERADO-FULTON JCT 7/36 RPL INSS | LAKEVLLE | ETL.1610.INSL | 2021-05-22 | 2021-05-07 | 2022-03-09 | 2022-05-07 | 2022-05-07 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548682 | T2 DI SILVERADO-FULTON JCT RPL INSS 6TWR | 93K
LC | 121379585 | :003/022 | T2 DI STN ML SW ST-RBK JT :3/22 RPL INSS | VICTOR | ETL.3840.INSL.NCER | 2021-05-22 | 2021-05-21 | 2022-05-17 | 2022-05-21 | 2022-05-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551875 | T2 DI STN ML SW ST-RBK JT RPL INSS 7TWR | 93K
LC | 121379587 | 011/070 | T2 DI STSLS-MLS SS-MTC #1 11/70 INS DAMS | VICTOR | ETL.3830.INSL.CERA | 2021-05-22 | 2021-05-21 | 2022-02-28 | 2022-05-21 | 2022-05-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Missing | Damper-Steel | Install | 44978047 | T2 DI STSLS-MLS SS-MTC #1 11/70 INS DAMS | ICS
LC | 121379589 | 011/070 | T2 DI STSLS-MLS SS-MTC #1 11/70 INS HRDT | VICTOR | ETL.3830.TOWR | 2021-05-22 | 2021-05-21 | 2022-02-01 | 2022-05-21 | 2022-05-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45122320 | T2 DI STSLS-MLS SS-MTC #1 11/70 INS HRDT | ICQ
LC | 121379648 | 024/185 | T2 DI DRUM-RIO OSO #1 024/185 INST HRDT | SACTO | ETL.1420.TOWR | 2021-05-22 | 2021-05-06 | 2022-05-23 | 2022-05-06 | 2022-05-06 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45074409 | T2 DI DRUM-RIO OSO #1 024/185 INST HRDT | ICQ
LC | 121379711 | 011/070 | T2 DI STAN-MAN #2 11/70 RPL INSS | VICTOR | ETL.3820.INSL.CERA | 2021-05-22 | 2021-05-21 | 2021-12-09 | 2022-05-21 | 2022-05-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31590775 | T2 DI STAN-MAN #2 11/70 RPL INSS | 93K
LC | 121379804 | 032/488 | T2 DI CLAY-MARTEL 032/488 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-21 | 2022-02-11 | 2022-05-21 | 2022-05-21 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543355 | T2 DI CLAY-MARTEL 032/482 RPL STRW | 70Y
LC | 121379809 | 008/092 | T2 DI WES PNT-VALL SPRG 008/092 REFRAME | VICTOR | ETL.8350.POLE.WOOD | 2021-05-22 | 2021-05-06 | 2022-05-23 | 2022-05-06 | 2022-05-06 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31543032 | T2 DI WES PNT-VALL SPRG 008/092 REFRAME | 93E
LC | 121379904 | 017/228 | T2 DI WST PNT-VLLY SPNGS 17/228 RPR GYWW | VICTOR | ETL.8350.POLE.NWOD | 2021-05-22 | 2021-05-08 | 2022-05-27 | 2022-05-08 | 2022-05-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45156045 | T2 DI WST PNT-VLLY SPNGS 17/228 RPR GYWW | ICW
LC | 121379952 | 006/080 | T2 DI WST PT VLY SPNGS 006/080 RPR STRW | VICTOR | ETL.8350.POLE.WOOD | 2021-05-22 | 2021-05-07 | 2022-05-26 | 2022-05-07 | 2022-05-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45156047 | T2 DI WST PT VLY SPNGS 006/080 RPR STRW | ICW
LC | 121379986 | 023/319 | T2 DI CLAY-MARTEL 023/319 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-08 | 2022-07-11 | 2022-05-08 | 2022-05-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45110665 | T2 DI CLAY-MARTEL 023/319 RPR STRW | ICW
LC | 121379987 | 023/319 | T2 DI CLAY-MARTEL 023/319 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-08 | 2022-07-11 | 2022-05-08 | 2022-05-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45110664 | T2 DI CLAY-MARTEL 023/319 RPR GYWW | ICW
LC | 121380142 | 040/189 | T2 DI IGNCO-SBRNTE 040/189 INST HRDT | LAKEVLLE | ETL.4920.TOWR | 2021-05-22 | 2021-05-06 | 2022-03-16 | 2022-05-06 | 2022-05-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45142469 | T2 DI IGNCO-SBRNTE 040/189 INST HRDT | ICQ
LC | 121380213 | 020/481 | T2 DI DRUM-GRAS VAL-WMR 020/481 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-05-22 | 2021-05-05 | 2022-03-31 | 2022-05-05 | 2022-05-05 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541884 | T2 DI DRM-GRS VLY-WMR 15/351 RPL STRW | 70Y
LC | 121380451 | 016/206 | T2NT DI W PT-VLLY SPRNGS 16/206 RMV BUTT | VICTOR | ETL.8350.POLE.NWOD | 2021-05-22 | 2021-05-08 | 2022-02-08 | 2022-05-08 | 2022-05-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2N PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45156049 | T2NT DI W PT-VLLY SPRNGS 16/206 RMV BUTT | ICW
LC | 121380453 | 016/206 | T2 DI WP-VLLY SPRNGS 16/206 RPL HRDD | VICTOR | ETL.8350.POLE.NWOD | 2021-05-22 | 2021-05-08 | 2022-05-27 | 2022-05-08 | 2022-05-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45156050 | T2 DI WP-VLLY SPRNGS 16/206 RPL HRDD | ICW
LC | 121380569 | 035/154 | T2 DI MOSS LANDNG-LS BNS 35/154 RPL HRDT | MOSSLNDG | ETL.6040.TOWR | 2021-05-22 | 2021-05-21 | 2022-03-09 | 2022-05-21 | 2022-05-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 44819243 | T2 DI MOSS LANDNG-LS BNS 35/154 RPL HRDT | ICQ
LC | 121380583 | 015/007 | T2 DI MNDCN-WLTS-FRT BRG 15/7 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-22 | 2021-05-21 | 2022-05-24 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45145806 | T2 DI MNDCN-WLTS-FRT BRG 15/7 RPR STRW | ICW
LC | 121380589 | :004/028 | T2 DI STNSLS-MLNS-MNTC :4/28 RPLC HRDT | VICTOR | ETL.3830.TOWR | 2021-05-22 | 2021-05-21 | 2022-02-16 | 2022-05-21 | 2022-05-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45107278 | T2 DI STNSLS-MLNS-MNTC :4/28 RPLC HRDT | ICQ
LC | 121380668 | 005/093 | T2 DI SISQUOC SANTA YNEZ 5/93 RPR INSW | PISMOBCH | ETL.3700.INSL.CERA | 2021-05-22 | 2021-05-06 | 2021-10-26 | 2022-05-06 | 2022-05-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44963137 | T2 DI SISQUOC SANTA YNEZ 5/93 RPR INSW | ICW
LC | 121380886 | :004/028 | T2 DI STNSLS-MLNS-MNTC :4/28 RPR STRT | VICTOR | ETL.3830.TOWR | 2021-05-22 | 2021-05-21 | 2022-02-16 | 2022-05-21 | 2022-05-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45107279 | T2 DI STNSLS-MLNS-MNTC :4/28 RPR STRT | ICQ
LC | 121380941 | :015/079 | T2 DI CRZY HRSE CNYN :015/079 RPL RPGS | MOSSLNDG | ETL.2900.TOWR | 2021-05-22 | 2021-05-07 | 2021-10-05 | 2022-05-07 | 2022-05-07 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44961515 | T2 DI CRZY HRSE CNYN :015/079 RPL RPGS | ICB
LC | 121381009 | 009/010 | T2 DI EXCHEQUER-MARIPOS 009/010 RMV BUTT | FRESNO | ETL.8640.POLE.WOOD | 2021-05-22 | 2021-05-06 | 2022-02-04 | 2022-05-06 | 2022-05-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45068244 | T2 DI EXCHEQUER-MARIPOS 009/010 RMV BUTT | ICW
LC | 121381060 | 010/189 | T2 DI COLGATE-PALERMO 10/189 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-08-30 | 2022-05-10 | 2022-05-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31604333 | T2 DI COLGATE-PALERMO 1/19 RPL STRW | 70Y
LC | 121381064 | 007/037 | T2 DI SLVD FLTN JCT 007/037 RPL INSS | LAKEVLLE | ETL.1610.INSL | 2021-05-22 | 2021-05-08 | 2022-03-09 | 2022-05-08 | 2022-05-08 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548682 | T2 DI SILVERADO-FULTON JCT RPL INSS 6TWR | 93K
LC | 121381065 | 007/037 | T2 DI FULTON-PUEBLO 007/037 RPL INSS | LAKEVLLE | ETL.1600.INSL | 2021-05-22 | 2021-05-08 | 2022-02-23 | 2022-05-08 | 2022-05-08 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 121381086 | 021/302 | T2 DI CLAY-MARTEL 21/302 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-07-13 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45110666 | T2 DI CLAY-MARTEL 21/302 RPR STRW | ICW
LC | 121381087 | 021/302 | T2 DI CLAY-MARTEL 21/302 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-07-13 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45110667 | T2NT DI CLAY-MARTEL 21/302 RPR GYWW | ICW
LC | 121381112 | 002/032 | T2 DI COLGATE-PALERMO 2/32 RMV DEBRIS | SACTO | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-05-22 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074413 | T2 DI COLGATE-PALERMO 2/32 RMV DEBRIS | ICW
LC | 121381127 | 014/123 | T2 DI DRUM-RIO OSO #1 014/123 RPR STRT | SACTO | ETL.1420.TOWR | 2021-05-22 | 2021-05-07 | 2022-01-12 | 2022-05-07 | 2022-05-07 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45074414 | T2 DI DRUM-RIO OSO #1 014/123 RPR STRT | ICQ
LC | 121381129 | 014/123 | T2 DI DRUM-RIO OSO #1 014/123 RPR FOND | SACTO | ETL.1420.TOWR | 2021-05-22 | 2021-05-07 | 2022-01-12 | 2022-05-07 | 2022-05-07 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45074415 | T2 DI DRUM-RIO OSO #1 014/123 RPR FOND | ICQ
LC | 121381151 | 018/266 | T2 DI CLAY-MARTEL 18/266 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-03-10 | 2022-05-10 | 2022-05-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543443 | T2 DI CLAY-MARTEL 18/266 RPL STRW | 70Y
LC | 121381152 | 008/158 | T2 DI COLGATE-PALERMO 8/158 RPL STRW | SACTO | ETL.6500.POLE.NWOD | 2021-05-22 | 2021-05-10 | 2022-08-30 | 2022-05-10 | 2022-05-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31606227 | T2 DI COLGATE-PALERMO 009/186 RPL STRW | 70Y
LC | 121381187 | :006/011 | T2 DI FULTON-PUEBLO :006/011 RPR STRW | LAKEVLLE | ETL.1600.POLE.WOOD | 2021-05-22 | 2021-05-06 | 2022-02-10 | 2022-05-06 | 2022-05-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45147861 | T2 DI FULTON-PUEBLO :006/011 RPR STRW | ICW
LC | 121381190 | 005/103 | T2 DI COLGATE-PALERMO 5/103 RMV STUB | SACTO | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-02-25 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074417 | T2 DI COLGATE-PALERMO 5/103 RMV STUB | ICW
LC | 121381196 | 004/002 | T2 DI FULTON-HOPLAND 4/2 RMV STEPS | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-05-22 | 2021-05-06 | 2022-03-31 | 2022-05-06 | 2022-05-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45142797 | T2 DI FULTON-HOPLAND 4/2 RMV STEPS | ICS
LC | 121381231 | 011/214 | T2 DI COLGATE-PALERMO 11/214 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-08-31 | 2022-05-10 | 2022-05-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31595991 | T2 DI COLGATE-PALERMO 11/214 RPL POLE | 70Y
LC | 121381237 | 029/009 | T2 DI CLAY-MARTEL 29/9 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-04-02 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45135018 | T2 DI CLAY-MARTEL 29/9 RPR STRW | ICW
LC | 121381331 | 017/393 | T2 DI DRM-GRS VLY-WIMAR 17/393 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-05-22 | 2021-05-05 | 2022-01-17 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45074440 | T2 DI DRM-GRS VLY-WIMAR 17/393 RPR GYWW | ICW
LC | 121381333 | 020/284 | T2 DI CLAY-MARTEL 20/284 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-03-14 | 2022-05-10 | 2022-05-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543443 | T2 DI CLAY-MARTEL 18/266 RPL STRW | 70Y
LC | 121381390 | :001/014 | T2 DI FULTON-PUEBLO :1/14 REPAIR STRW | LAKEVLLE | ETL.1600.POLE.WOOD | 2021-05-22 | 2021-05-06 | 2022-02-10 | 2022-05-06 | 2022-05-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45147864 | T2 DI FULTON-PUEBLO :1/14 REPAIR STRW | ICW
LC | 121381411 | 011/195 | T2 DI TEJON-LEBEC 011/195 RPR STRW | MIDWAY | ETL.9250.POLE.WOOD | 2021-05-22 | 2021-05-05 | 2021-08-09 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44944235 | T2 DI TEJON-LEBEC 011/195 RPR STRW | ICW
LC | 121381525 | 029/005 | T2 DI CLAY-MARTEL 29/5 RPL HRDW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-12-04 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45135036 | T2 DI CLAY-MARTEL 29/5 RPL HRDW | ICW
LC | 121381559 | 024/341 | T2 DI CLAY-MARTEL 024/341 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-08 | 2022-07-19 | 2022-05-08 | 2022-05-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45110668 | T2 DI CLAY-MARTEL 024/341 RPR GYWW | ICW
LC | 121381565 | 015/303 | T2 DI COLGATE-PALERMO 015/303 RMV BUTT | SACTO | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-04-29 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074441 | T2 DI COLGATE-PALERMO 015/303 RMV BUTT | ICW
LC | 121381568 | 017/336 | T2 DI COLGATE-PALERMO 017/336 RPL HRDD | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-05-06 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45211882 | T2 DI COLGATE-PALERMO 017/336 RPL HRDD | ICW
LC | 121381629 | 015/313 | T2 DI COLGATE-PALERMO 15/313 RMV BUTT | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-11 | 2022-02-27 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45211883 | T2 DI COLGATE-PALERMO 15/313 RMV BUTT | ICW
LC | 121381641 | 030/012 | T2 DI CLAY-MARTEL 30/12 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-03-30 | 2022-05-10 | 2022-05-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543355 | T2 DI CLAY-MARTEL 032/482 RPL STRW | 70Y
LC | 121381699 | 006/124 | T2 DI COLGATE-PALERMO 6/124 RMV HRDW | SACTO | ETL.6500.POLE.NWOD | 2021-05-22 | 2021-05-10 | 2022-05-16 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45074442 | T2 DI COLGATE-PALERMO 6/124 RMV HRDW | ICW
LC | 121381730 | 019/269 | T2 DI CLAY-MARTEL 19/269 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-03-14 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45110669 | T2 DI CLAY-MARTEL 19/269 RPR STRW | ICW
LC | 121381734 | 006/120 | T2 DI COLGATE-PALERMO 6/120 RMV DEBRIS | SACTO | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-05-09 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074443 | T2 DI COLGATE-PALERMO 6/120 RMV DEBRIS | ICW
LC | 121381737 | 027/010 | T2 DI CLAY-MARTEL+ 27/10 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-03-26 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45135068 | T2 DI CLAY-MARTEL+ 27/10 RPR STRW | ICW
LC | 121381771 | 001/025 | T2 DI COLGATE-PALERMO 1/25 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-06 | 2022-05-19 | 2022-05-06 | 2022-05-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540562 | T2 DI COLGATE-PALERMO 7/135 RPLC STRW | 70Y
LC | 121381775 | 021/292 | T2 DI CLAY-MARTEL 21/292 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-07-14 | 2022-05-10 | 2022-05-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543443 | T2 DI CLAY-MARTEL 18/266 RPL STRW | 70Y
LC | 121381778 | 017/255 | T2 DI CLAY-MARTEL 017/255 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-04-04 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45135075 | T2 DI CLAY-MARTEL 017/255 RPR STRW | ICW
LC | 121381789 | 010/192 | T2 DI COLGATE-PALERMO 010/192 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-05-16 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45074444 | T2 DI COLGATE-PALERMO 010/192 RPR STRW | ICW
LC | 121381817 | 019/277 | T2 DI CLAY-MARTEL 019/277 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-11 | 2022-03-14 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45110670 | T2 DI CLAY-MARTEL 019/277 RPR STRW | ICW
LC | 121381819 | 015/304 | T2 DI COLGATE-PALERMO 015/304 RMV BUTT | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-02-22 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45211884 | T2 DI COLGATE-PALERMO 015/304 RMV BUTT | ICW
LC | 121381883 | 003/087 | T2 DI COLGATE-ALLEGHANY 3/87 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2021-05-22 | 2021-05-11 | 2022-06-22 | 2022-05-11 | 2022-05-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR FRAB | Rotten | Structure-Wood | Replace | 31541793 | EI T2 COLGATE-ALLEGHANY 0/17 RPL STRW | 70Y
LC | 121381885 | 024/347 | T2 DI CLAY-MARTEL+ 24/347 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-11 | 2022-07-18 | 2022-05-11 | 2022-05-11 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45110671 | T2 DI CLAY-MARTEL+ 24/347 RPR STRW | ICW
LC | 121381900 | 002/031 | T2 DI COLGATE-PALERMO 002/031 COMPLETE | SACTO | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-05-22 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45074446 | T2 DI COLGATE-PALERMO 002/031 RMV DEBRIS | ICW
LC | 121381913 | 001/037 | T2 DI CLGTE-ALLEGHANY 001/037 RPR GYWW | SACTO | ETL.6470.POLE.WOOD | 2021-05-22 | 2021-05-11 | 2022-06-24 | 2022-05-11 | 2022-05-11 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45074447 | T2 DI CLGTE-ALLEGHANY 001/037 RPR GYWW | ICW
LC | 121381914 | 022/438 | T2 DI COLGATE PALERMO 022/438 RPR STRW | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-04-30 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45211885 | T2 DI COLGATE PALERMO 022/438 RPR STRW | ICW
LC | 121381917 | 020/285 | T2 DI CLAY-MARTEL 020/285 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-08 | 2022-03-14 | 2022-05-08 | 2022-05-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45110672 | T2 DI CLAY-MARTEL 020/285 RPR STRW | ICW
LC | 121381953 | 031/473 | T2 DI CLAY-MARTEL 31/473 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-11 | 2022-07-26 | 2022-05-11 | 2022-05-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31579298 | T2 DI CLAY-MARTEL 31/473 RPL STRW | 70Y
LC | 121381955 | 029/429 | T2 DI CLAY-MARTEL 29/429 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-11 | 2022-01-28 | 2022-05-11 | 2022-05-11 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543355 | T2 DI CLAY-MARTEL 032/482 RPL STRW | 70Y
LC | 121381973 | 020/412 | T2 DI COLGATE-PALERMO 020/412 RPL STRW | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-05-07 | 2022-05-10 | 2022-05-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540562 | T2 DI COLGATE-PALERMO 7/135 RPLC STRW | 70Y
LC | 121382010 | 021/295 | T2 DI CLAY-MARTEL 021/295 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-08 | 2022-07-13 | 2022-05-08 | 2022-05-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543443 | T2 DI CLAY-MARTEL 18/266 RPL STRW | 70Y
LC | 121382057 | 029/013 | T2 DI CLAY-MARTEL 29/13 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-11 | 2022-03-31 | 2022-05-11 | 2022-05-11 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543443 | T2 DI CLAY-MARTEL 18/266 RPL STRW | 70Y
LC | 121382059 | 018/359 | T2DI COLGATE-PALERMO 18/359 RMV BUTT | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-04-29 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45211886 | T2DI COLGATE-PALERMO 18/359 RMV BUTT | ICW
LC | 121382100 | 009/186 | T2 DI COLGATE-PALERMO 009/186 RPL STRW | SACTO | ETL.6500.POLE.NWOD | 2021-05-22 | 2021-05-10 | 2022-08-30 | 2022-05-10 | 2022-05-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31606227 | T2 DI COLGATE-PALERMO 009/186 RPL STRW | 70Y
LC | 121382108 | 004/080 | T2 DI COLGATE-PALERMO 004/080 RMV DEBRIS | SACTO | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-02-25 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44934163 | T2 DI COLGATE-PALERMO 004/080 RMV DEBRIS | ICW
LC | 121382161 | 021/303 | T2 DI CLAY-MARTEL 021/303 RMV BUTT | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2021-08-26 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44943375 | T2 DI CLAY-MARTEL 021/303 RMV BUTT | ICW
LC | 121382162 | 021/303 | T2 DI CLAY-MARTEL 021/303 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2021-08-26 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44943376 | T2 DI CLAY-MARTEL 021/303 RPR GYWW | ICW
LC | 121382163 | 028/007 | T2 DI CLAY-MARTEL 28/7 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-11 | 2022-12-04 | 2022-05-11 | 2022-05-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31591719 | T2 DI CLAY-MARTEL 28/7 RPL STRW | 70Y
LC | 121382214 | 028/422 | T2 DI CLAY-MARTEL 028/422 RPL HRDW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-01-27 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45067197 | T2 DI CLAY-MARTEL 028/422 RPL HRDW | ICW
LC | 121382251 | 004/077 | T2 DI COLGATE-PALERMO 004/077 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-05-15 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45074451 | T2 DI COLGATE-PALERMO 004/077 RPR STRW | ICW
LC | 121382255 | 009/166 | T2 DI COLGATE-PALERMO 009/166 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-05-19 | 2022-05-10 | 2022-05-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540562 | T2 DI COLGATE-PALERMO 7/135 RPLC STRW | 70Y
LC | 121382280 | 007/128 | T2 DI COLGATE-PALERMO 007/128 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-05-16 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45074452 | T2 DI COLGATE-PALERMO 007/128 RPR STRW | ICW
LC | 121382284 | 019/434 | T2 DI DRM-GRSS VLLY-WMR 19/434 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2021-05-22 | 2021-05-05 | 2022-01-13 | 2022-05-05 | 2022-05-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44933395 | T2 DI DRM-GRSS VLLY-WMR 19/434 RPR STRW | ICW
LC | 121382286 | 018/369 | T2 DI COLGATE-PALERMO 018/369 RPL POLE | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-22 | 2021-05-10 | 2022-05-04 | 2022-05-10 | 2022-05-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541805 | T2 DI COLGATE-PALERMO 018/369 RPL POLE | 70Y
LC | 121382655 | 001/034 | T2 DI CLGTE-ALLGHNY 001/034 RMV BUTT | SACTO | ETL.6470.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2021-08-07 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44947901 | T2 DI CLGTE-ALLGHNY 001/034 RMV BUTT | ICW
LC | 121382659 | 028/003 | T2 DI CLAY-MARTEL 28/3 RPR IBWW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-04-01 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45135106 | T2 DI CLAY-MARTEL 28/3 RPR IBWW | ICW
LC | 121382807 | 006/108 | T2 DI CLGTE-PALERMO 006/108 RMV DEBRIS | SACTO | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-02-25 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074453 | T2 DI CLGTE-PALERMO 006/108 RMV DEBRIS | ICW
LC | 121382860 | 028/419 | T2 DI CLAY-MARTEL 28/419 REFRAME | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-01-27 | 2022-05-11 | 2022-05-11 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31579444 | T2 DI CLAY-MARTEL 28/419 REFRAME | 93E
LC | 121382865 | 002/058 | T2 DI SMRTVLL-NCLS #2 002/058 RMV DEBRIS | SACTO | ETL.8000.POLE.NWOD | 2021-05-23 | 2021-05-11 | 2022-04-22 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074454 | T2 DI SMRTVLL-NCLS #2 002/058 RMV DEBRIS | ICW
LC | 121382946 | 002/053 | T2 DI COLGATE-ALEGHANY 2/53 REFRAME | SACTO | ETL.6470.INSL.CERA | 2021-05-23 | 2021-05-11 | 2022-06-23 | 2022-05-11 | 2022-05-11 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31541801 | T2 DI COLGATE-ALLEGHANY 0/22 REFRAME | 93E
LC | 121383203 | 028/004 | T2 DI CLAY-MARTEL 28/4 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-04-01 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45135145 | T2 DI CLAY-MARTEL 28/4 RPR STRW | ICW
LC | 121383273 | 001/029 | T2 DI SMRTVLL-NCLS #2 001/029 RMV VEG | SACTO | ETL.8000.POLE.NWOD | 2021-05-23 | 2021-05-11 | 2022-08-01 | 2022-05-11 | 2022-05-11 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121383290 | 012/248 | T2 DI COLGATE-PALERMO 12/248 RPR INSW | TABLEMTN | ETL.6500.INSL.NCER | 2021-05-23 | 2021-05-10 | 2022-08-31 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45211887 | T2 DI COLGATE-PALERMO 12/248 RPR INSW | ICW
LC | 121383295 | 000/010 | T2 DI COLGATE-ALLEGHANY 0/10 RPR GYWW | SACTO | ETL.6470.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-06-23 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PUBL FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45224551 | T2 DI COLGATE-ALLEGHANY 0/10 RPR GYWW | ICW
LC | 121383297 | 030/001 | T2 DI CLAY-MARTEL 30/1 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-03-29 | 2022-05-10 | 2022-05-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31596222 | T2 DI CLAY-MARTEL 30/1 RPL STRW | 70Y
LC | 121383299 | 031/002 | T2 DI CLAY-MARTEL 31/2 INS HRDW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2021-07-29 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Wood | Install | 44894543 | T2 DI CLAY-MARTEL 31/2 INS HRDW | ICW
LC | 121383302 | 012/243 | T2 DI COLGATE-PALERMO 12/243 RMV STUB | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-02-23 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45211888 | T2 DI COLGATE-PALERMO 12/243 RMV STUB | ICW
LC | 121383348 | 003/053 | T2 DI COLGATE-PALERMO 3/53 RMV DEBRIS | SACTO | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-02-23 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074458 | T2 DI COLGATE-PALERMO 3/53 RMV DEBRIS | ICW
LC | 121383422 | 004/065 | T2 DI COLGATE-PALERMO 004/065 RMV DEBRIS | SACTO | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-02-23 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074459 | T2 DI COLGATE-PALERMO 004/065 RMV DEBRIS | ICW
LC | 121383471 | 013/166 | T2NT DI WP-VLY SPRNGS 13/166 RMV BUTT | VICTOR | ETL.8350.POLE.NWOD | 2021-05-23 | 2021-05-07 | 2022-02-09 | 2022-05-07 | 2022-05-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2N PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45156054 | T2NT DI WP-VLY SPRNGS 13/166 RMV BUTT | ICW
LC | 121383489 | 016/000 | T2 DI FULTON-HOPLAND 016/000 RPR GWWW | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-05-23 | 2021-05-13 | 2022-03-29 | 2022-05-13 | 2022-05-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45143929 | T2 DI FULTON-HOPLAND 016/000 RPR GWWW | ICW
LC | 121383508 | 018/148 | T2 DI DRUM-RIO OSO #1 018/148 RMV DEBRIS | SACTO | ETL.1420.TOWR | 2021-05-23 | 2021-05-07 | 2022-02-10 | 2022-05-07 | 2022-05-07 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45018389 | T2 DI DRUM-RIO OSO #1 018/148 RMV DEBRIS | ICS
LC | 121383542 | 030/016 | T2 DI CLAY-MARTEL 30/16 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-04-01 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45135162 | T2 DI CLAY-MARTEL 30/16 RPR STRW | ICW
LC | 121383587 | 006/100 | T2 DI CENTRVL-TBL MTN 6/100 RPR STRW | TABLEMTN | ETL.6320.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-02-21 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45195719 | T2 DI CENTRVL-TBL MTN 6/100 RPR STRW | ICW
LC | 121383654 | 014/293 | T2 DI COLGATE-PALERMO 14/293 RPR STRW | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-05-11 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45211889 | T2 DI COLGATE-PALERMO 14/293 RPR STRW | ICW
LC | 121383698 | 027/402 | T2 DI CLAY-MARTEL 27/402 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-07-24 | 2022-05-11 | 2022-05-11 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45067198 | T2 DI CLAY-MARTEL 27/402 RPR STRW | ICW
LC | 121383708 | 018/149 | T2 DI DRUM-RIO OSO #1 018/149 RPR FOND | SACTO | ETL.1420.TOWR | 2021-05-23 | 2021-05-06 | 2022-03-07 | 2022-05-06 | 2022-05-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45074481 | T2 DI DRUM-RIO OSO #1 018/149 RPR FOND | ICQ
LC | 121383727 | 008/101 | T2 DI W. PNT-VLY SPRNGS 8/101 RPR STRW | VICTOR | ETL.8350.POLE.WOOD | 2021-05-23 | 2021-05-07 | 2021-06-24 | 2022-05-07 | 2022-05-07 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31541171 | T2 DI W. PNT-VLY SPRNGS 8/101 RPR STRW | 70Y
LC | 121383756 | 004/101 | T2 DI COLGATE-ALLEGHANY 4/101 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-06-22 | 2022-05-11 | 2022-05-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31596504 | T2 DI COLGATE-ALLEGHANY 1/41 RPL STRW | 70Y
LC | 121383758 | 002/060 | T2 DI COLGAT-ALGHANY 02/60 RMV BUTT | SACTO | ETL.6470.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-07-05 | 2022-05-11 | 2022-05-11 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45074484 | T2 DI COLGAT-ALGHANY 02/60 RMV BUTT | ICW
LC | 121383798 | 012/237 | T2 DI COLGATE-PALERMO 12/237 RPR GYWW | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-05-14 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45211890 | T2 DI COLGATE-PALERMO 12/237 RPR GYWW | ICW
LC | 121383799 | 012/237 | T2 DI COLGATE-PALERMO 12/237 RPR STRW | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-05-14 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44953792 | T2 DI COLGATE-PALERMO 12/237 RPR STRW | ICW
LC | 121383850 | 005/084 | T2 DI CENTERVILLE-TBLE MTN 5/84 RMV STEP | TABLEMTN | ETL.6320.POLE.NWOD | 2021-05-23 | 2021-05-10 | 2022-02-25 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45195449 | T2 DI CENTERVILLE-TBLE MTN 5/84 RMV STEP | ICW
LC | 121383874 | 011/223 | T2 DI COLGATE-PALERMO 11/223 REFRAME | TABLEMTN | ETL.6500.INSL.CERA | 2021-05-23 | 2021-05-10 | 2022-05-19 | 2022-05-10 | 2022-05-10 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31590519 | T2 DI COLGATE-PALERMO 11/223 REFRAME | 93E
LC | 121383940 | 015/310 | T2 DI COLGATE-PALERMO 15/310 RMV BUTT | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-05-01 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45211891 | T2 DI COLGATE-PALERMO 15/310 RMV BUTT | ICW
LC | 121384017 | 017/340 | T2 DI COLGATE-PALERMO 17/340 RPR STRW | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-05-05 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45211892 | T2 DI COLGATE-PALERMO 17/340 RPR STRW | ICW
LC | 121384046 | 027/020 | T2 DI CLAY-MARTEL 27/20 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-03-29 | 2022-05-11 | 2022-05-11 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543390 | DI CLAY-MARTEL 026/367 RPL STRW | 70Y
LC | 121384089 | 000/010 | T2 DI SMRTVILE-NICOLAUS #2 0/10 RMV VEG | SACTO | ETL.8000.POLE.NWOD | 2021-05-23 | 2021-05-11 | 2022-08-03 | 2022-05-11 | 2022-05-11 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121384103 | 007/126 | T2 DI COLGATE-PALERMO 7/126 RMV BUTT | SACTO | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-05-16 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44883178 | T2 DI COLGATE-PALERMO 7/126 RMV BUTT | ICW
LC | 121384138 | 000/022 | T2 DI COLGATE-ALLEGHANY 0/22 REFRAME | SACTO | ETL.6470.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-06-23 | 2022-05-11 | 2022-05-11 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31541801 | T2 DI COLGATE-ALLEGHANY 0/22 REFRAME | 93E
LC | 121384171 | 008/214 | T2 DI COTTONWOOD- BNTN #1 8/214 RMV VEG | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-23 | 2021-05-21 | 2022-01-11 | 2022-05-21 | 2022-05-21 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121384289 | 009/036 | T2 DI TESLA-METCALF 009/036 RPR INSS | METCALF | ETL.6110.INSL.CERA | 2021-05-23 | 2021-05-21 | 2021-06-18 | 2022-05-21 | 2022-05-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44817611 | T2 DI TESLA-METCALF 009/036 RPR INSS | ICS
LC | 121384303 | 027/006 | T2 DI CLAY-MARTEL 27/6 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-03-29 | 2022-05-11 | 2022-05-11 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543390 | DI CLAY-MARTEL 026/367 RPL STRW | 70Y
LC | 121384311 | 003/038 | T2 DI HLSDL JCT-HLF MN BY 3/38 RMV VEG | METCALF | ETL.7060.POLE.WOOD | 2021-05-23 | 2021-05-12 | 2022-03-31 | 2022-05-12 | 2022-05-12 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121384312 | 023/328 | T2 DI CLAY-MARTEL 23/328 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-07-11 | 2022-05-11 | 2022-05-11 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45110673 | T2 DI CLAY-MARTEL 23/328 RPR GYWW | ICW
LC | 121384335 | 001/034 | T2 DI SMARTVILLE-NCLS #2 1/34 RPR STRW | SACTO | ETL.8000.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-04-21 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45074492 | T2 DI SMARTVILLE-NCLS #2 1/34 RPR STRW | ICW
LC | 121384406 | 010/093 | T2 DI EL DRD-MSRI FT #1 10/93 RPL INSS | SACTO | ETL.1530.INSL | 2021-05-23 | 2021-05-21 | 2022-06-21 | 2022-05-21 | 2022-05-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535732 | T2 DI ELDRD-MSSRI FLT #1 RPL INSS 10TWRS | 93K
LC | 121384408 | 018/002 | T2 DI FULTON-HOPLAND 018/002 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-23 | 2021-05-12 | 2022-08-04 | 2022-05-12 | 2022-05-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600084 | T2 DI FULTON-HOPLAND 018/002 RPL POLE | 70Y
LC | 121384414 | 027/011 | T2 DI CLAY-MARTEL 27/11 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-03-25 | 2022-05-11 | 2022-05-11 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543390 | DI CLAY-MARTEL 026/367 RPL STRW | 70Y
LC | 121384450 | 004/102 | T2 DI COLGATE-ALLEGHANY 4/102 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-06-22 | 2022-05-11 | 2022-05-11 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44883226 | T2 DI COLGATE-ALLEGHANY 4/102 RPR STRW | ICW
LC | 121384469 | 016/316 | T2 DI COLGATE-PALERMO 16/316 REFRAME CMT | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-05-11 | 2022-05-10 | 2022-05-10 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31541367 | T2 DI COLGATE-PALERMO 16/316 REFRAME | 93E
LC | 121384533 | 001/042 | T2 DI COLGATE-ALLEGHANY 1/42 REFRAME | SACTO | ETL.6470.INSL.CERA | 2021-05-23 | 2021-05-11 | 2022-06-23 | 2022-05-11 | 2022-05-11 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31541801 | T2 DI COLGATE-ALLEGHANY 0/22 REFRAME | 93E
LC | 121384537 | 016/215 | T2NT DI WP-VALY SPRNGS 16/215 RMV BUTT | VICTOR | ETL.8350.POLE.NWOD | 2021-05-23 | 2021-05-07 | 2022-02-08 | 2022-05-07 | 2022-05-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2N PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45156058 | T2NT DI WP-VALY SPRNGS 16/215 RMV BUTT | ICW
LC | 121384562 | 010/193 | T2 DI COLGATE-PALERMO 010/193 RPR INSW | SACTO | ETL.6500.INSL.CERA | 2021-05-23 | 2021-05-10 | 2022-05-16 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45074493 | T2 DI COLGATE-PALERMO 010/193 RPR INSW | ICW
LC | 121384564 | 003/044 | T2 DI COLGATE-PALERMO 003/044 RMV DBRS | SACTO | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-05-22 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074494 | T2 DI COLGATE-PALERMO 003/044 RMV DBRS | ICW
LC | 121384565 | 019/379 | T2 DI COLGATE PALERMO 019/379 RPL STRW | TABLEMTN | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-05-04 | 2022-05-10 | 2022-05-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540562 | T2 DI COLGATE-PALERMO 7/135 RPLC STRW | 70Y
LC | 121384661 | 002/038 | T2 DI COLGATE-PALERMO 002/038 COMPLETE | SACTO | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-05-22 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 44883225 | T2 DI COLGATE-PALERMO 002/038 RMV DBRS | ICW
LC | 121384665 | 032/484 | T2 DI CLAY-MARTEL 32/484 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-02-11 | 2022-05-11 | 2022-05-11 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31579298 | T2 DI CLAY-MARTEL 31/473 RPL STRW | 70Y
LC | 121384725 | 015/305 | T2 DI COLGATE-PALERMO 015/305 RMV BUTT | SACTO | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-04-29 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44883220 | T2 DI COLGATE-PALERMO 015/305 RMV BUTT | ICW
LC | 121384726 | 015/305 | T2 DI COLGATE-PALERMO 015/305 RPR GYWW | SACTO | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-05-11 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44883221 | T2 DI COLGATE-PALERMO 015/305 RPR GYWW | ICW
LC | 121384767 | 001/019 | T2 DI COLGATE-PALERMO 1/19 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-08-31 | 2022-05-10 | 2022-05-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31604333 | T2 DI COLGATE-PALERMO 1/19 RPL STRW | 70Y
LC | 121384769 | 008/099 | T2 DI CLGT-SMRTVLL #2 008/099 RPR STRW | SACTO | ETL.6520.POLE.WOOD | 2021-05-23 | 2021-05-12 | 2021-06-11 | 2022-05-12 | 2022-05-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 44875491 | T2 DI CLGT-SMRTVLL #2 008/099 RPR STRW | ICW
LC | 121384771 | 015/305 | T2 DI COLGATE-PALERMO 015/305 REFRAME | SACTO | ETL.6500.INSL.CERA | 2021-05-23 | 2021-05-10 | 2022-05-11 | 2022-05-10 | 2022-05-10 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31541367 | T2 DI COLGATE-PALERMO 16/316 REFRAME | 93E
LC | 121384846 | 002/035 | T2 DI COLGATE-PALERMO 2/35 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-05-21 | 2022-05-10 | 2022-05-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31599816 | T2 DI COLGATE-PALERMO 2/35 RPL STRW | 70Y
LC | 121384867 | 004/113 | T2 DI HMLTN BRNCH-CHSTR 4/113 RPLC SPLW | TABLEMTN | ETL.7000.INSL.NCER | 2021-05-23 | 2021-05-22 | 2022-07-25 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Replace | 45147359 | T2 DI HMLTN BRNCH-CHSTR 4/113 RPLC SPLW | ICW
LC | 121384868 | 006/141 | T2 DI HMLTN BRNCH-CHSTR 6/141 RPL DAMW | TABLEMTN | ETL.7000.INSL.NCER | 2021-05-23 | 2021-05-22 | 2022-07-25 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Damper-Wood | Replace | 45147440 | T2 DI HMLTN BRNCH-CHSTR 6/141 RPL DAMW | ICW
LC | 121384879 | 002/030 | T2 DI COLGATE-PALERMO 2/30 RMV BUTT | SACTO | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-05-22 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074499 | T2 DI COLGATE-PALERMO 2/30 RMV BUTT | ICW
LC | 121384916 | 009/108 | T2 DI CLGT-SMRTVLL #2 009/108 RPR GYWW | SACTO | ETL.6520.POLE.NWOD | 2021-05-23 | 2021-05-12 | 2021-06-17 | 2022-05-12 | 2022-05-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44876106 | T2 DI CLGT-SMRTVLL #2 009/108 RPR GYWW | ICW
LC | 121384930 | 006/148 | T2 DI HMLTN BRNCH-CHSTR 6/148 RPR SPLW | TABLEMTN | ETL.7000.INSL.NCER | 2021-05-23 | 2021-05-22 | 2022-07-25 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45147358 | T2 DI HMLTN BRNCH-CHSTR 6/148 RPR SPLW | ICW
LC | 121384931 | 004/113 | T2 DI HMLTN BRNCH-CHSTR 4/113 RPLC HRDW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-23 | 2021-05-22 | 2022-07-25 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213346 | T2 DI HMLTN BRNCH-CHSTR 4/113 RPLC HRDW | ICW
LC | 121384933 | 008/176 | T2 DI HMLTN BRNCH-CHSTR 8/176 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-23 | 2021-05-22 | 2022-07-23 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213347 | T2 DI HMLTN BRNCH-CHSTR 8/176 RPR STRW | ICW
LC | 121385108 | 022/441 | T2 DI COLGATE-PALERMO 022/441 RPR INSW | TABLEMTN | ETL.6500.INSL.CERA | 2021-05-23 | 2021-05-10 | 2022-05-02 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45211893 | T2 DI COLGATE-PALERMO 022/441 RPR INSW | ICW
LC | 121385128 | 006/033 | T2 DI FULTON-PUEBLO 006/033 RPL INSS | LAKEVLLE | ETL.1600.INSL | 2021-05-23 | 2021-05-08 | 2022-02-22 | 2022-05-08 | 2022-05-08 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 121385129 | 006/033 | T2 DI FULTON-PUEBLO 006/033 RPL INSS | LAKEVLLE | ETL.1610.INSL | 2021-05-23 | 2021-05-08 | 2022-03-09 | 2022-05-08 | 2022-05-08 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548682 | T2 DI SILVERADO-FULTON JCT RPL INSS 6TWR | 93K
LC | 121385394 | 010/191 | T2 DI COLGATE-PALERMO 010/191 RPL HRDW | SACTO | ETL.6500.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2022-05-16 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45074502 | T2 DI COLGATE-PALERMO 010/191 RPL HRDW | ICW
LC | 121385526 | 029/435 | T2 DI CLAY-MARTEL 029/435 RPR INSW | VICTOR | ETL.8250.INSL.NCER | 2021-05-23 | 2021-05-11 | 2022-02-17 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45067220 | T2 DI CLAY-MARTEL 029/435 RPR INSW | ICW
LC | 121385735 | 027/406 | T2 DI CLAY-MARTEL 027/406 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-02-04 | 2022-05-11 | 2022-05-11 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543390 | DI CLAY-MARTEL 026/367 RPL STRW | 70Y
LC | 121385811 | 029/007 | T2 DI CLAY-MARTEL 029/007 RMV BUTT | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2021-08-09 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44943379 | T2 DI CLAY-MARTEL 029/007 RMV BUTT | ICW
LC | 121385812 | 029/007 | T2 DI CLAY-MARTEL 029/007 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-10 | 2021-08-09 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44943420 | T2 DI CLAY-MARTEL 029/007 RPR STRW | ICW
LC | 121385813 | 027/022 | T2 DI CLAY-MARTEL 027/022 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-12-04 | 2022-05-11 | 2022-05-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31607873 | T2 DI CLAY-MARTEL 027/022 RPL STRW | 70Y
LC | 121385814 | 027/022 | T2 DI CLAY-MARTEL 027/022 REFRAME | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 | 2022-03-26 | 2022-05-11 | 2022-05-11 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31535893 | T2 DI CLAY-MARTEL 27/21 REFRAME | 93E
LC | 121386601 | 006/055 | T2 EI PARADISE-TABLE MTN 6/55 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-05-24 | 2021-05-20 | 2022-05-13 | 2022-05-20 | 2022-05-20 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31533715 | T3 DI PARADISE-BUTTE RPLC INSS 29TWRS | 93K
LC | 121386795 | 003/060 | T2 DI SMRTVLLE-NICLAUS #2 3/60 RPL HRDD | SACTO | ETL.8000.POLE.NWOD | 2021-05-24 | 2021-05-11 | 2022-04-25 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45074509 | T2 DI SMRTVLLE-NICLAUS #2 3/60 RPL HRDD | ICW
LC | 121387106 | 015/002 | T2 DI MNDCNO-WLLTS-FRT BRG 15/2 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-24 | 2021-05-21 | 2022-05-25 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45145805 | T2 DI MNDCNO-WLLTS-FRT BRG 15/2 RPR STRW | ICW
LC | 121387331 | 007/130 | T2 DI OLGATE-PALERMO 7/130 RMV BUTT | SACTO | ETL.6500.POLE.WOOD | 2021-05-24 | 2021-05-10 | 2022-05-16 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074510 | T2 DI OLGATE-PALERMO 7/130 RMV BUTT | ICW
LC | 121387332 | 007/130 | T2 DI OLGATE-PALERMO 7/130 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2021-05-24 | 2021-05-10 | 2022-08-31 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45195639 | T2 DI OLGATE-PALERMO 7/130 RPR STRW | ICW
LC | 121387595 | 007/133 | T2 DI COLGATE-PALERMO 7/133 RMV BUTT | SACTO | ETL.6500.POLE.WOOD | 2021-05-24 | 2021-05-10 | 2022-05-16 | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45074851 | T2 DI COLGATE-PALERMO 7/133 RMV BUTT | ICW
LC | 121387656 | 011/070 | T2 DI STSLS-MANTECA #2 11/70 INS DAMS | VICTOR | ETL.3820.INSL.CERA | 2021-05-24 | 2021-05-21 | 2022-03-07 | 2022-05-21 | 2022-05-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Missing | Damper-Steel | Install | 44977942 | T2 DI STSLS-MLS SS-MTC #2 11/70 INS DAMS | ICS
LC | 121387667 | 029/440 | T2 DI CLAY-MARTEL 29/440 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-24 | 2021-05-10 | 2022-02-02 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45067221 | T2 DI CLAY-MARTEL 29/440 RPR STRW | ICW
LC | 121387843 | 033/512 | T2 DI CLAY-MARTEL 033/512 RPL POLE | VICTOR | ETL.8250.POLE.WOOD | 2021-05-24 | 2021-05-21 | 2022-02-15 | 2022-05-21 | 2022-05-21 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543443 | T2 DI CLAY-MARTEL 18/266 RPL STRW | 70Y
LC | 121387906 | 010/018 | T2 DI TRINTY-MAPLE CREEK 10/18 RPR ANCHR | EUREKA | ETL.8170.POLE.NWOD | 2021-05-24 | 2021-05-21 | 2022-09-12 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45158743 | T2 DI TRNTY-MAPLE CRK 010/018 RMV DBRS | ICW
LC | 121387989 | 001/040 | T2 DI HMLTN BRNCH-CHSTR 1/40 RPR GYWW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-24 | 2021-05-22 | 2022-07-25 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213349 | T2 DI HMLTN BRNCH-CHSTR 1/40 RPR GYWW | ICW
LC | 121388036 | 001/040 | T2 DI HMLTN BRNCH-CHSTR 1/40 RPL INSW | TABLEMTN | ETL.7000.INSL | 2021-05-24 | 2021-05-22 | 2022-07-25 | 2022-05-22 | 2022-05-22 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542053 | T2 DI HMLTN BRNCH-CHSTR 1/40 RPL INSW | 93I
LC | 121388675 | 028/428 | T2 DI CLAY-MARTEL 028/428 RMV BUTT | VICTOR | ETL.8250.POLE.WOOD | 2021-05-24 | 2021-05-10 | 2021-08-27 | 2022-05-10 | 2022-05-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44943378 | T2 DI CLAY-MARTEL 028/428 RMV BUTT | ICW
LC | 121388986 | 021/291 | T2 DI CLAY-MARTEL 021/291 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-24 | 2021-05-11 | 2022-07-14 | 2022-05-11 | 2022-05-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543443 | T2 DI CLAY-MARTEL 18/266 RPL STRW | 70Y
LC | 121389462 | 042/008 | T2 DI FORT ROSS-GUALALA 042/008 INS HRDW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-05-24 | 2021-05-15 | 2022-04-25 | 2022-05-15 | 2022-05-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCM COMP OH TR2 PRTO AIR NTDE | Missing | Hardware-Wood | Install | 45144206 | T2 DI FORT ROSS-GUALALA 042/008 INS HRDW | ICW
LC | 121389466 | 031/471 | T2 DI CLAY-MARTEL 31/471 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-24 | 2021-05-11 | 2022-07-26 | 2022-05-11 | 2022-05-11 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45067226 | T2 DI CLAY-MARTEL 31/471 RPR GYWW | ICW
LC | 121389961 | :012/066 | T2 DI CRZY HRS CYN-SLS-SD :12/66 RPL RPT | MOSSLNDG | ETL.2900.TOWR | 2021-05-24 | 2021-05-21 | 2021-10-04 | 2022-05-21 | 2022-05-21 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44962400 | T2 DI CRZY HRS CYN-SLS-SD :12/66 RPL RPT | ICB
LC | 121391328 | 033/503 | T2 DI CLAY-MARTEL 033/503 RMV STUB | VICTOR | ETL.8250.POLE.WOOD | 2021-05-24 | 2021-05-11 | 2021-08-28 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44943422 | T2 DI CLAY-MARTEL 033/503 RMV STUB | ICW
LC | 121391550 | 033/503 | T2 DI CLAY-MARTEL 033/503 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-24 | 2021-05-11 | 2022-03-16 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45067227 | T2 DI CLAY-MARTEL 033/503 RPR STRW | ICW
LC | 121391559 | 029/125 | T2 DI MOSS LANDING-MTCLF 29/125 RPR GYWS | MOSSLNDG | ETL.6050.TOWR | 2021-05-24 | 2021-05-15 | 2022-06-29 | 2022-05-15 | 2022-05-15 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45149705 | T2 DI MOSS LANDING-MTCLF 29/125 RPR GYWS | ICS
LC | 121391622 | 004/001 | T2 DI MENDOCINO-WILLITS-FT X4/1 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-24 | 2021-05-17 | 2022-05-18 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45145719 | T2 DI MENDOCINO-WILLITS-FT X4/1 RPR STRW | ICW
LC | 121391699 | 012/247 | T2 DI CTTNWD-RD BLFF 012/247 RMV DEBRIS | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-24 | 2021-05-17 | 2022-06-08 | 2022-05-17 | 2022-05-17 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45197170 | T2 DI CTTNWD-RD BLFF 012/247 RMV DEBRIS | ICS
LC | 121391770 | 005/011 | T2 DI MNDCN-WLTS-FRT BRG 5/11 RPL HRDW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-24 | 2021-05-17 | 2022-10-04 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 44905695 | T2 DI COLGATE-CHLNG A0/18 RPL HRDW | ICW
LC | 121391778 | 017/293 | T2 DI ARCO-POLONIO PASS 017/293 RPR JUMS | MIDWAY | ETL.8450.POLE.NWOD | 2021-05-24 | 2021-05-17 | 2022-02-09 | 2022-05-17 | 2022-05-17 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Jumper-Steel | Repair | 44992845 | T2 DI ARCO-POLONIO PASS 017/293 RPR JUMS | ICS
LC | 121391781 | 002/013 | T2 DI MENDO-WILL-FT BRAGG 2/13 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-24 | 2021-05-17 | 2022-05-18 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45144313 | T2 DI MENDO-WILL-FT BRAGG 2/13 RPR GYWW | ICW
LC | 121391785 | 005/001 | T2 DI MENDO-WILITS-FRT BRG 5/1 RPR HRDD | WILLITS | ETL.7550.POLE.NWOD | 2021-05-24 | 2021-05-17 | 2022-05-26 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45145610 | T2 DI MENDO-WILITS-FRT BRG 5/1 RPR HRDD | ICW
LC | 121391802 | 030/127 | T2 DI MOSS LNDNG-MTCLF 30/127 INS GYWS | MOSSLNDG | ETL.6050.TOWR | 2021-05-24 | 2021-05-17 | 2022-08-09 | 2022-05-17 | 2022-05-17 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45149706 | T2 DI MOSS LNDNG-MTCLF 30/127 INS GYWS | ICS
LC | 121391804 | 030/127 | T2 DI MOSS LNDNG-MTCLF 30/12 INS HRDT | MOSSLNDG | ETL.6050.TOWR | 2021-05-24 | 2021-05-17 | 2022-08-04 | 2022-05-17 | 2022-05-17 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45149229 | T2 DI MOSS LNDNG-MTCLF 30/12 INS HRDT | ICQ
LC | 121391835 | 005/001 | T2 DI MENDO-WILITS-FRT BRG 5/1 RPR GYWW | WILLITS | ETL.7550.POLE.NWOD | 2021-05-24 | 2021-05-17 | 2022-05-26 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44987535 | T2 DI MENDO-WILITS-FRT BRG 5/1 RPR GYWW | ICW
LC | 121391894 | 004/009 | T2 DI MENDO-WILTS-FRT BRG 4/9 RPR INSS | WILLITS | ETL.7550.INSL.NCER | 2021-05-24 | 2021-05-17 | 2022-05-26 | 2022-05-17 | 2022-05-17 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45145609 | T2 DI MENDO-WILTS-FRT BRG 4/9 RPR INSS | ICS
LC | 121391933 | 000/012 | T2 DI MEND-WILL-FT BRAGG 1/12 SPLIT BOLT | WILLITS | ETL.7550.POLE.WOOD | 2021-05-24 | 2021-05-17 | 2022-05-19 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Wood | Install | 45144308 | T2 DI MEND-WILL-FT BRAGG 1/12 SPLIT BOLT | ICW
LC | 121391937 | 031/470 | T2 DI CLAY-MARTEL 31/470 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-24 | 2021-05-11 | 2022-02-02 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45067229 | T2 DI CLAY-MARTEL 31/470 RPR STRW | ICW
LC | 121392011 | 004/004A | T2 DI HLSDL JT HLF MN BY 4/4A RMV VEG | METCALF | ETL.7060.POLE.NWOD | 2021-05-24 | 2021-05-17 | 2022-03-07 | 2022-05-17 | 2022-05-17 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121392012 | 004/033 | T2 DI SBRNT-"R" #1 004/033 RPR FND CMPLT | CONCORD | ETL.3770.TOWR | 2021-05-24 | 2021-05-17 | 2022-05-02 | 2022-05-17 | 2022-05-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAR | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45211295 | T2 DI SBRNT-"R" #1 004/033 RPR FOND | ICQ
LC | 121392020 | B020/448 | T2 DI DRUM-GRS VLY-WEMR B20/448 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2021-05-24 | 2021-05-17 | 2022-04-20 | 2022-05-17 | 2022-05-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45075017 | T2 DI DRUM-GRS VLY-WEMR B20/448 RPR STRW | ICW
LC | 121392053 | 020/282 | T2 DI CLAY-MARTEL 20/282 RPL HRDW | VICTOR | ETL.8250.INSL.NCER | 2021-05-24 | 2021-05-11 | 2022-03-14 | 2022-05-11 | 2022-05-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45110674 | T2 DI CLAY-MARTEL 20/282 RPL HRDW | ICW
LC | 121392099 | 005/036 | T2 DI SOBRANTE-R #1 5/036 INST HRWT | CONCORD | ETL.3770.TOWR | 2021-05-24 | 2021-05-17 | 2022-05-10 | 2022-05-17 | 2022-05-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAR NTDE | Missing | Hardware-Tower | Install | 45211297 | T2 DI SOBRANTE-R #1 5/036 INST HRWT | ICQ
LC | 121392147 | 000/018 | T2 DI PLUMAS SIERRA TAP 00/18 RPR GYWW | TABLEMTN | ETL.6291.POLE.WOOD | 2021-05-24 | 2021-05-17 | 2021-12-02 | 2022-05-17 | 2022-05-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45011869 | T2 DI PLUMAS SIERRA TAP 00/18 RPR GYWW | ICW
LC | 121392169 | 004/031 | T2 DI SOBRANTE-"G" #1 4/31 REGRADE | CONCORD | ETL.3720.POLE.NWOD | 2021-05-24 | 2021-05-17 | 2022-06-08 | 2022-05-17 | 2022-05-17 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAR | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190902 | T2 DI SOBRANTE-"G" #1 4/31 REGRADE | ICQ
LC | 121392177 | B019/424 | T2 DI DRM GRSS VLY WMR B19/424 RMV VEG | SACTO | ETL.6760.POLE.WOOD | 2021-05-24 | 2021-05-17 | 2022-02-14 | 2022-05-17 | 2022-05-17 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121392201 | 007/155 | T2 DI COTTNWOOD-RED BLUFF 7/155 INS HRDW | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-24 | 2021-05-17 | 2022-06-22 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45242421 | T2 DI COTTNWOOD-RED BLUFF 7/155 INS HRDW | ICW
LC | 121392202 | 007/155 | T2 DI COTTNWD-RED BLUFF 7/155 RMV DEBRIS | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-24 | 2021-05-17 | 2022-06-06 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45197117 | T2 DI COTTNWD-RED BLUFF 7/155 RMV DEBRIS | ICW
LC | 121392207 | 016/514 | T2 DI SPAULDING-SUMMIT 16/514 RPR INSW | SACTO | ETL.8060.INSL.NCER | 2021-05-24 | 2021-05-17 | 2022-09-15 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45075264 | T2 DI SPAULDING-SUMMIT 16/514 RPR INSW | ICW
LC | 121392247 | 002/107 | T2 DI SPAULDING-SUMMIT 2/107 REFRAME | SACTO | ETL.8060.INSL.CERA | 2021-05-24 | 2021-05-17 | 2022-09-25 | 2022-05-17 | 2022-05-17 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31537117 | T2 EI SPLDNG-SMMT 1/64 REFRAME | 93E
LC | 121392249 | 004/032 | T2 DI SOBRANTE-R #1 4/32 RPL HRDT CMPLTD | CONCORD | ETL.3770.TOWR | 2021-05-24 | 2021-05-17 | 2022-05-10 | 2022-05-17 | 2022-05-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAR | No Good/Out of Stdrd | Hardware-Tower | Replace | 45211298 | T2 DI SOBRANTE-R #1 4/32 RPL HRDT | ICQ
LC | 121392280 | 020/288 | T2 DI CLAY-MARTEL+-WOOD 20/288 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-24 | 2021-05-11 | 2022-07-14 | 2022-05-11 | 2022-05-11 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45110675 | T2 DI CLAY-MARTEL+-WOOD 20/288 RPR STRW | ICW
LC | 121392914 | 002/026 | T2 DI CHRISTIE-WILLOW PSS 2/26 PL CMPLTD | CONCORD | ETL.6370.POLE.WOOD | 2021-05-25 | 2021-05-17 | 2022-08-31 | 2022-05-17 | 2022-05-17 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31543393 | T2 DI CHRISTIE-WILLOW PASS 2/26 RPL STRW | 70Y
LC | 121393015 | 004/089 | T2 DI CTTNWD-RD BLFF 004/089 INS HRDW | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-25 | 2021-05-18 | 2022-09-29 | 2022-05-18 | 2022-05-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45242420 | T2 DI CTTNWD-RD BLFF 004/089 INS HRDW | ICW
LC | 121393151 | 004/138 | T2 DI SPULDNG-SMMIT 4/138 RPR WDPKR | SACTO | ETL.8060.POLE.WOOD | 2021-05-25 | 2021-05-18 | 2022-08-02 | 2022-05-18 | 2022-05-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44883016 | T2 DI SPULDNG-SMMIT 4/138 RPR WDPKR | ICW
LC | 121393199 | 006/031 | T2 EI VACA-LAKEVILLE #1 6/31 RPL INSS | LAKEVLLE | ETL.5840.TOWR | 2021-05-25 | 2021-05-21 | 2022-09-21 | 2022-05-21 | 2022-05-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO SR21 FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549782 | T2 EI VACA-LAKEVILLE #1 6/31 RPL INSS | 93K
LC | 121393237 | 041/330 | T2 DI RND MNTN-CTTNWD #2 41/330 RPL HRDW | TABLEMTN | ETL.5640.TOWR | 2021-05-25 | 2021-05-17 | 2022-02-18 | 2022-05-17 | 2022-05-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45110232 | T2 DI RND MNTN-CTTNWD #2 41/330 RPL HRDW | ICQ
LC | 121393477 | 010/214 | T2 DI CTTNWD-RED BLUFF 10/214 RMV DEBRIS | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-25 | 2021-05-18 | 2022-06-06 | 2022-05-18 | 2022-05-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45197164 | T2 DI CTTNWD-RED BLUFF 10/214 RMV DEBRIS | ICW
LC | 121393772 | 001/014 | T2 DI MENDO-WILL-FT BRAGG 1/14 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-05-25 | 2021-05-17 | 2022-05-27 | 2022-05-17 | 2022-05-17 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCH COMP OH TR2 PRTO AIR FRAR | No Good/Out of Stdrd | Structure-Wood | Replace | 31540801 | T2 DI MENDO-WILL-FT BRAGG 1/6 RPL POLE | 70Y
LC | 121393851 | 003/135 | T2 DI SPAULDING-SUMMIT 3/135 RPR WDPKR | SACTO | ETL.8060.POLE.WOOD | 2021-05-25 | 2021-05-18 | 2022-05-12 | 2022-05-18 | 2022-05-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45075300 | T2 DI SPAULDING-SUMMIT 3/135 RPR WDPKR | ICW
LC | 121393944 | 015/479 | T2 DI SPAULDING-SUMMIT 15/479 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-05-25 | 2021-05-18 | 2022-09-22 | 2022-05-18 | 2022-05-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31542073 | T2 EI SPAULDING-SUMMIT 14/466 RPL STRW | 70Y
LC | 121394136 | 017/534 | T2 DI SPAULDING-SUMMIT 17/534 RPL HRDW | SACTO | ETL.8060.POLE.WOOD | 2021-05-25 | 2021-05-17 | 2022-08-04 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45075218 | T2 DI SPAULDING-SUMMIT 17/534 RPL HRDW | ICW
LC | 121394237 | 008/163 | T2 DI COTTNWD-RED BLUFF 8/163 RMV DEBRIS | TABLEMTN | ETL.6660.POLE.WOOD | 2021-05-25 | 2021-05-18 | 2022-06-06 | 2022-05-18 | 2022-05-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45197160 | T2 DI COTTNWD-RED BLUFF 8/163 RMV DEBRIS | ICW
LC | 121394238 | 008/163 | T2 DI COTTONWOD-RED BLUFF 8/163 RPR STRW | TABLEMTN | ETL.6660.POLE.WOOD | 2021-05-25 | 2021-05-18 | 2022-09-29 | 2022-05-18 | 2022-05-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45242424 | T2 DI COTTONWOD-RED BLUFF 8/163 RPR STRW | ICW
LC | 121394240 | 045/008 | T2 DI FORT ROSS-GUALALA 45/08 RPL INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2021-05-25 | 2021-05-17 | 2021-08-13 | 2022-05-17 | 2022-05-17 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542052 | T2 DI FORT ROSS-GUALALA 45/08 RPL INSW | 93I
LC | 121394402 | 017/560 | T2 DI SPULDNG-SMMIT 017/560 RPR STRW | SACTO | ETL.8060.POLE.WOOD | 2021-05-25 | 2021-05-17 | 2022-08-05 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45075301 | T2 DI SPULDNG-SMMIT 017/560 RPR STRW | ICW
LC | 121394663 | 024/115 | T2 EI SILVERADO-FULTON 24/115 RPL INSS | LAKEVLLE | ETL.1610.INSL.NCER | 2021-05-25 | 2021-05-25 | 2022-03-17 | 2022-05-25 | 2022-05-25 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548688 | T2 DI SLVDO FLTN JCT SW RPL INSS 6TWRS | 93K
LC | 121394750 | 008/068 | T2 EI CRESTA-RIO OSO 8/68 RPL INSS | TABLEMTN | ETL.4590.INSL | 2021-05-25 | 2021-05-25 | 2022-05-04 | 2022-05-25 | 2022-05-25 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534509 | T3 EI CRESTA-RIO OSO RPL INSS 6 TWRS | 93K
LC | 121394870 | 001/006 | T2 DI MENDO-WILL-FT BRAGG 1/6 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-05-25 | 2021-05-15 | 2022-05-17 | 2022-05-15 | 2022-05-15 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540801 | T2 DI MENDO-WILL-FT BRAGG 1/6 RPL POLE | 70Y
LC | 121394918 | 022/169 | T2 EI OCEANO-CLNDR SW ST 22/169 RPL ANCW | PISMOBCH | ETL.2394.POLE.WOOD | 2021-05-25 | 2021-05-25 | 2022-02-10 | 2022-05-25 | 2022-05-25 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31543120 | T2 EI OCEANO-CLNDR SW ST 22/169 RPL ANCW | 93E
LC | 121395157 | 011/235 | T2 DI COTTONWD-RED BLF 11/235 RMV DEBRIS | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-25 | 2021-05-17 | 2022-06-06 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45197168 | T2 DI COTTONWD-RED BLF 11/235 RMV DEBRIS | ICW
LC | 121395309 | 019/235 | T2 EI DRUM-SUMMIT#2 19/235L RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-05-25 | 2021-05-25 | 2022-10-16 | 2022-05-25 | 2022-05-25 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545492 | T2 DI DRUM-SUMMIT #2 18/221L RPL STRW | 70Y
LC | 121395337 | 009/185 | T2 DI COTTONWOD-RED BLF 9/185 COMPLETE | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-25 | 2021-05-17 | 2022-06-06 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45197163 | T2 DI COTTONWOD-RED BLF 9/185 RMV DEBRIS | ICW
LC | 121395339 | 007/156 | T2 DI COTTONWD-RED BLF 7/156 RMV DEBRIS | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-25 | 2021-05-17 | 2022-06-06 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45197119 | T2 DI COTTONWD-RED BLF 7/156 RMV DEBRIS | ICW
LC | 121395366 | 014/458 | T2 DI SPAULDING-SUMMIT 014/458 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-05-25 | 2021-05-18 | 2022-09-17 | 2022-05-18 | 2022-05-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541924 | T2 DI SPAULDING-SUMMIT 12/419 RPL STRW | 70Y
LC | 121395444 | 010/218 | T2 DI COTTONWOOD-RED BLF 10/218 RMV STUB | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-25 | 2021-05-17 | 2022-06-06 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45197165 | T2 DI COTTONWOOD-RED BLF 10/218 RMV STUB | ICW
LC | 121395507 | 001/009 | T2 DI MENDO-WILL-FT BRAGG 1/9 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-05-25 | 2021-05-17 | 2022-05-27 | 2022-05-17 | 2022-05-17 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540801 | T2 DI MENDO-WILL-FT BRAGG 1/6 RPL POLE | 70Y
LC | 121395797 | 009/188 | T2 DI COTTONWOOD-RED BLUFF 9/188 RPL HRD | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-25 | 2021-05-18 | 2022-03-02 | 2022-05-18 | 2022-05-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 121395906 | 005/002 | T2 DI MNDCN-WLTS-FRT BRG 5/2 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-05-25 | 2021-05-15 | 2022-05-24 | 2022-05-15 | 2022-05-15 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540801 | T2 DI MENDO-WILL-FT BRAGG 1/6 RPL POLE | 70Y
LC | 121395986 | 011/226 | T2 DI CTTNWD-RED BLUFF 11/226 RMV DEBRIS | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-25 | 2021-05-18 | 2022-06-06 | 2022-05-18 | 2022-05-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45197167 | T2 DI CTTNWD-RED BLUFF 11/226 RMV DEBRIS | ICW
LC | 121396006 | 025/109 | T2 DI MOSS LNDNG-MTCLF 025/109 RPR GYWS | MOSSLNDG | ETL.6050.TOWR | 2021-05-25 | 2021-05-18 | 2022-08-10 | 2022-05-18 | 2022-05-18 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45149708 | T2 DI MOSS LNDNG-MTCLF 025/109 RPR GYWS | ICS
LC | 121396322 | 020/238 | T2 EI DRUM-SUMMIT#2 20/238L RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-05-25 | 2021-05-25 | 2022-10-19 | 2022-05-25 | 2022-05-25 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP PATR COMP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31545492 | T2 DI DRUM-SUMMIT #2 18/221L RPL STRW | 70Y
LC | 121396360 | 020/238 | T2 EI DRUM-SUMMIT#2 20/238R RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-05-25 | 2021-05-25 | 2022-10-19 | 2022-05-25 | 2022-05-25 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31545492 | T2 DI DRUM-SUMMIT #2 18/221L RPL STRW | 70Y
LC | 121396510 | 002/118 | T2 DI SPAULDING-SUMMIT 2/118 RPR WDPKR | SACTO | ETL.8060.POLE.WOOD | 2021-05-25 | 2021-05-18 | 2022-09-25 | 2022-05-18 | 2022-05-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44883015 | T2 DI SPAULDING-SUMMIT 2/118 RPR WDPKR | ICW
LC | 121396996 | 001/065 | T2 DI SPAULDING-SUMMIT 01/65 RPR INSW | SACTO | ETL.8060.INSL.NCER | 2021-05-25 | 2021-05-18 | 2022-09-25 | 2022-05-18 | 2022-05-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45219529 | T2 DI SPAULDING-SUMMIT 01/65 RPR INSW | ICW
LC | 121397047 | 018/263 | T2 WV EI CLAY-MARTEL 018/263 INS DMPW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-25 | 2021-05-25 | 2021-08-06 | 2022-05-25 | 2022-05-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Wood | Install | 44943374 | T2 WV EI CLAY-MARTEL 018/263 INS DMPW | ICW
LC | 121397221 | 006/126 | T2 DI COTTNWD-RED BLUFF 6/126 RMV DEBRIS | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-25 | 2021-05-17 | 2022-02-02 | 2022-05-17 | 2022-05-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45166814 | T2 DI COTTNWD-RED BLUFF 6/126 RMV DEBRIS | ICW
LC | 121397361 | 014/461 | T2 DI SPAULDING-SUMMIT 014/461 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-05-25 | 2021-05-18 | 2021-07-26 | 2022-05-18 | 2022-05-18 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31541924 | T2 DI SPAULDING-SUMMIT 12/419 RPL STRW | 70Y
LC | 121397367 | 012/245 | T2 DI SPAULDING-SUMMIT 002/089 RPR STRW | TABLEMTN | ETL.6660.POLE.WOOD | 2021-05-25 | 2021-05-18 | 2022-09-29 | 2022-05-18 | 2022-05-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45242429 | T2 DI SPAULDING-SUMMIT 002/089 RPR STRW | ICW
LC | 121397368 | 011/223 | T2 DI CTTNWD-RED BLUFF 11/223 RMV DEBRIS | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-25 | 2021-05-17 | 2022-06-06 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45197166 | T2 DI CTTNWD-RED BLUFF 11/223 RMV DEBRIS | ICW
LC | 121397453 | 007/153 | T2 DI COTTNWD-RED BLUFF 7/153 RMV DEBRIS | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-25 | 2021-05-18 | 2022-06-06 | 2022-05-18 | 2022-05-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45197116 | T2 DI COTTNWD-RED BLUFF 7/153 RMV DEBRIS | ICW
LC | 121397475 | 008/166 | T2 DI CTTNWD-RD BLFF 008/166 RMV DEBRIS | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-25 | 2021-05-18 | 2022-06-06 | 2022-05-18 | 2022-05-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45197161 | T2 DI CTTNWD-RD BLFF 008/166 RMV DEBRIS | ICW
LC | 121397564 | 001/000 | T2 DI MENDO-WILLTS-FT BRG 1/0 RPL HRDW | WILLITS | ETL.7550.INSL.CERA | 2021-05-25 | 2021-05-17 | 2022-05-14 | 2022-05-17 | 2022-05-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45144309 | T2 DI MENDO-WILLTS-FT BRG 1/0 RPL HRDW | ICW
LC | 121397763 | 014/459 | T2 DI SPULDNG-SMMIT 014/459 RPL POLE | SACTO | ETL.8060.POLE.WOOD | 2021-05-25 | 2021-05-18 | 2022-09-17 | 2022-05-18 | 2022-05-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31596203 | T2 DI SPULDNG-SMMIT 014/459 RPL POLE | 70Y
LC | 121397766 | 028/206 | T2 DI DRUM-RIO OSO #2 028/206 RPL INSS | SACTO | ETL.1430.INSL.CERA | 2021-05-25 | 2021-05-17 | 2021-12-01 | 2022-05-17 | 2022-05-17 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535386 | EI DRM-RO OSO #2 RPL INSS 12TWRS | 93K
LC | 121397768 | 020/158 | T2 DI DRUM-RIO OSO #1 20/158 RPR FOND | SACTO | ETL.1420.TOWR | 2021-05-25 | 2021-05-13 | 2022-03-07 | 2022-05-13 | 2022-05-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45168955 | T2 DI DRUM-RIO OSO #1 20/158 RPR FOND | ICQ
LC | 121398012 | 000/004 | T2 DI SPULDNG-SMMIT 000/004 RPR INSUL | SACTO | ETL.8060.INSL.NCER | 2021-05-25 | 2021-05-18 | 2022-09-23 | 2022-05-18 | 2022-05-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45219530 | T2 DI SPULDNG-SMMIT 000/004 RPR INSUL | ICW
LC | 121398041 | 018/597 | T2 DI SPAULDING-SUMMIT 18/597 RPL INSW | SACTO | ETL.8060.INSL.NCER | 2021-05-25 | 2021-05-18 | 2022-09-16 | 2022-05-18 | 2022-05-18 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541926 | T2 DI SPAULDING-SUMMIT 18/597 RPL INSW | 93I
LC | 121398110 | 001/013 | T2 DI SBRT-GRZLY-CLT #2 1/13 RPL HRDT | CONCORD | ETL.3750.TOWR | 2021-05-25 | 2021-05-19 | 2022-06-08 | 2022-05-19 | 2022-05-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45190903 | T2 DI SBRT-GRZLY-CLT #2 1/13 RPL HRDT | ICQ
LC | 121398939 | 010/215 | T2 DI CTTNWD RD BLFF 010/215 RPR STRW | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-26 | 2021-05-18 | 2022-03-02 | 2022-05-18 | 2022-05-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45194419 | T2 DI CTTNWD RD BLFF 010/215 RPR STRW | ICW
LC | 121400055 | 007/172 | T2 DI SALINAS-LAURELES 7/172 RPLC HRDW | MOSSLNDG | ETL.7930.POLE.WOOD | 2021-05-26 | 2021-05-17 | 2022-05-09 | 2022-05-17 | 2022-05-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213174 | T2 DI SALINAS-LAURELES 7/172 RPLC HRDW | ICW
LC | 121400585 | 011/075 | T2 DI CORTINA 11/75 RPR INSU | SACTO | ETL.4540.INSL.CERA | 2021-05-26 | 2021-05-18 | 2022-05-09 | 2022-05-18 | 2022-05-18 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45195683 | T2 DI CORTINA 11/75 RPR INSU | ICS
LC | 121400720 | 019/235 | T2 EI DRUM-SUMMIT#2 19/235R RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-05-26 | 2021-05-25 | 2022-10-16 | 2022-05-25 | 2022-05-25 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545492 | T2 DI DRUM-SUMMIT #2 18/221L RPL STRW | 70Y
LC | 121400952 | 005/107 | T2 DI COTTONWOOD-RED BLF 5/107 RPR STRW | TABLEMTN | ETL.6660.POLE.WOOD | 2021-05-26 | 2021-05-17 | 2022-06-22 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45242098 | T2 DI COTTONWOOD-RED BLF 5/107 RPR STRW | ICW
LC | 121401380 | 025/110 | T2 DI MOSS LNDNG-MTCLF 25/110 RPR SHLS | MOSSLNDG | ETL.6050.TOWR | 2021-05-26 | 2021-05-19 | 2022-02-26 | 2022-05-19 | 2022-05-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 45166396 | T2 DI MOSS LNDNG-MTCLF 25/110 RPR SHLS | ICS
LC | 121401786 | 006/018 | T2 CARIBOU-PLUMAS JCT-WOOD 6/18 RPL POLE | TABLEMTN | ETL.6290.POLE.WOOD | 2021-05-26 | 2021-05-22 | 2022-10-29 | 2022-05-22 | 2022-05-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31541655 | T2 CARIBOU-PLUMAS JCT-WOOD 6/18 RPL POLE | 70Y
LC | 121401917 | 003/121 | T2 DI SPAULDING-SUMMIT 3/121 RPR STRW | SACTO | ETL.8060.POLE.WOOD | 2021-05-26 | 2021-05-18 | 2022-09-25 | 2022-05-18 | 2022-05-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45219531 | T2 DI SPAULDING-SUMMIT 3/121 RPR STRW | ICW
LC | 121402017 | 002/042 | T2 WV HALSEY-PLACER 002/042 INS DAMW | SACTO | ETL.6990.INSL.NCER | 2021-05-26 | 2021-05-26 | 2022-03-17 | 2022-05-26 | 2022-05-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 45078186 | T2 WV HALSEY-PLACER 002/042 INS DAMW | ICW
LC | 121402030 | 020/010 | T2 DI MNDCN-PHL JCT-HPLND 20/10 RPL STRW | WILLITS | ETL.7520.POLE.WOOD | 2021-05-26 | 2021-05-18 | 2022-03-08 | 2022-05-18 | 2022-05-18 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542639 | T2 DI MNDCN-PHL JCT-HPLND 20/10 RPL STRW | 70Y
LC | 121402496 | 008/177 | T2 DI COTTONWOOD RED BLF 8/177 RPR STRW | TABLEMTN | ETL.6660.POLE.WOOD | 2021-05-26 | 2021-05-17 | 2022-09-29 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45242425 | T2 DI COTTONWOOD RED BLF 8/177 RPR STRW | ICW
LC | 121402558 | 030/012 | T2 DI FULTON-HOPLAND 030/012 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-26 | 2021-05-18 | 2022-06-24 | 2022-05-18 | 2022-05-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143966 | T2NT DI FULTON-HOPLAND 030/012 RMV DBRS | ICW
LC | 121403225 | 020/237 | T2 EI DRUM-SUMMIT #1 20/237 RPL INSW | SACTO | ETL.1440.POLE.WDPS | 2021-05-26 | 2021-05-26 | 2022-06-19 | 2022-05-26 | 2022-05-26 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541895 | T2 EI DRUM-SUMMIT #1 20/237 RPL INSW | 93I
LC | 121403713 | 010/007 | T2 CARIBOU-PLUMAS JCT-WOOD 10/7 RPL PL | TABLEMTN | ETL.6290.POLE.WOOD | 2021-05-26 | 2021-05-22 | 2022-10-28 | 2022-05-22 | 2022-05-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541655 | T2 CARIBOU-PLUMAS JCT-WOOD 6/18 RPL POLE | 70Y
LC | 121403907 | 005/033 | T2 WV EI SN LS OBSP-CAYS 5/33 RPR SPLCW | PISMOBCH | ETL.9090.POLE.NWOD | 2021-05-26 | 2021-05-26 | 2022-05-05 | 2022-05-26 | 2022-05-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Repair | 45098881 | T2 WV EI SN LS OBSP-CAYS 5/33 RPR SPLCW | ICW
LC | 121403991 | 053/006 | T2 WV ELK-GUALALA 053/006 RPL ANCW | LAKEVLLE | ETL.8410.POLE.WOOD | 2021-05-26 | 2021-05-26 | 2022-01-21 | 2022-05-26 | 2022-05-26 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31541855 | T2 ELK-GUALALA 053/006 RPL ANCW | 93E
LC | 121404091 | 005/110 | T2 DI CTTNWD RD BLFF 005/110 RPR STRW | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-26 | 2021-05-17 | 2022-09-29 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45242099 | T2 DI CTTNWD RD BLFF 005/110 RPR STRW | ICW
LC | 121404344 | :012/064 | T2 DI CRZY-HRSE CYN-SLNS:12/64 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2021-05-26 | 2021-05-21 | 2021-10-04 | 2022-05-21 | 2022-05-21 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44962406 | T2 DI CRZY-HRSE CYN-SLNS:12/64 RPL RPTS | ICB
LC | 121404512 | :000/009 | T2 DI BLLT-RVRBNK-MLNS S S :0/9 RPL INSW | VICTOR | ETL.1070.INSL.NCER | 2021-05-26 | 2021-05-21 | 2022-04-14 | 2022-05-21 | 2022-05-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545223 | T2 DI BLTA RVK MLNS SS :011/004 RPL INSW | 93I
LC | 121404515 | 002/066 | T2 DI CTTNWD-BNTN #1 2/66 COMPLETE | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2022-10-05 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45213468 | T2 DI CTTNWD-BNTN #1 2/66 RMV BUTT | ICW
LC | 121404577 | :011/004 | T2 DI BLTA-RNK-MLNS SS :011/004 RPR STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-05-26 | 2021-05-20 | 2022-05-03 | 2022-05-20 | 2022-05-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45156059 | T2 DI BLTA-RNK-MLNS SS :011/004 RPR STRW | ICW
LC | 121404578 | :011/004 | T2 DI BLTA-RNK-MLNS SS :011/004 RPL INSW | VICTOR | ETL.1070.INSL.NCER | 2021-05-26 | 2021-05-20 | 2022-05-03 | 2022-05-20 | 2022-05-20 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545223 | T2 DI BLTA RVK MLNS SS :011/004 RPL INSW | 93I
LC | 121404624 | 011/194 | T2 DI TEJON-LEBEC 11/194 RPR INSW | MIDWAY | ETL.9250.INSL | 2021-05-26 | 2021-05-21 | 2021-08-05 | 2022-05-21 | 2022-05-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44930598 | T2 DI TEJON-LEBEC 11/194 RPR INSW | ICW
LC | 121404632 | 003/073 | T2 DI COLMN-COTTONWOOD 3/73 RPR STRW | TABLEMTN | ETL.6430.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2022-07-30 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45212625 | T2 DI COLMN-COTTONWOOD 3/73 RPR STRW | ICW
LC | 121404740 | :007/011 | T2 DI BLTA-RVRBNK-MELNS :7/11 RPL INSW | VICTOR | ETL.1070.INSL.NCER | 2021-05-26 | 2021-05-20 | 2022-05-07 | 2022-05-20 | 2022-05-20 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31577823 | DI BLLT-RBK-MLS SWST :006/006 RPL INSW | 93I
LC | 121404742 | :007/011 | T2 DI BLT-RVBK-MLNS :7/11 RPR STRW CMPLT | VICTOR | ETL.1070.POLE.WOOD | 2021-05-26 | 2021-05-20 | 2022-05-07 | 2022-05-20 | 2022-05-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45156100 | T2 DI BLOTA-RVRBNK-MLONS :07/11 RPR STRW | ICW
LC | 121404772 | :013/072 | T2 DI CRZ HR CYN-SLNS-SLD 13/72 INS RPTS | MOSSLNDG | ETL.2900.TOWR | 2021-05-26 | 2021-05-21 | 2021-10-05 | 2022-05-21 | 2022-05-21 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44961518 | T2 DI CRZ HR CYN-SLNS-SLD 13/72 INS RPTS | ICB
LC | 121404775 | 014/013 | T2 DI MNDCN-WLTS-FRT BRG 14/13 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2022-05-25 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145804 | T2 DI MNDCN-WLTS-FRT BRG 14/13 RPR GYWW | ICW
LC | 121404777 | 041/274 | T2 DI CRESTA-RIO OSO 041/274 RPR INSS | TABLEMTN | ETL.4590.INSL.CERA | 2021-05-26 | 2021-05-21 | 2022-08-29 | 2022-05-21 | 2022-05-21 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213461 | T2 DI POE-RIO OSO 041/274 RPR INSS | ICS
LC | 121404778 | 041/274 | T2 DI POE-RIO OSO 041/274 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-05-26 | 2021-05-21 | 2022-01-10 | 2022-05-21 | 2022-05-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45106676 | T2 DI POE-RIO OSO 041/274 RPR FOND | ICQ
LC | 121404824 | 014/343 | T2 DI COTTNWOOD-BNTN 14/343 RPL HRDW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2022-08-22 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213471 | T2 DI COTTNWOOD-BNTN 14/343 RPL HRDW | ICW
LC | 121404855 | 041/271 | T2 DI POE-RIO OSO 41/271 RPLC INSS | TABLEMTN | ETL.5540.INSL.CERA | 2021-05-26 | 2021-05-21 | 2022-08-11 | 2022-05-21 | 2022-05-21 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546693 | T2 EI POE-RIO OSO RPL INSS 8TWRS | 93K
LC | 121404858 | :004/023 | T2 DI STNS-MELN MTCA #1 :4/23 RPR STRT | VICTOR | ETL.3830.TOWR | 2021-05-26 | 2021-05-20 | 2022-02-16 | 2022-05-20 | 2022-05-20 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45107275 | T2 DI STNS-MELN MTCA #1 :4/23 RPR STRT | ICQ
LC | 121405038 | 011/229 | T2 DI CTTNWD-RD BF 001/229 RPL HRDW | TABLEMTN | ETL.6660.POLE.NWOD | 2021-05-26 | 2021-05-20 | 2022-03-02 | 2022-05-20 | 2022-05-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45195381 | T2 DI CTTNWD-RD BF 001/229 RPL HRDW | ICW
LC | 121405061 | :004/026 | T2 DI STLS-MEL-SWSTA-RVB :04/26 COMPLETE | VICTOR | ETL.3840.INSL.NCER | 2021-05-26 | 2021-05-21 | 2022-05-16 | 2022-05-21 | 2022-05-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551875 | T2 DI STN ML SW ST-RBK JT RPL INSS 7TWR | 93K
LC | 121405102 | :011/002 | T2 DI BELLOTA-RBK-MLS :011/002 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2022-05-05 | 2022-05-21 | 2022-05-21 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536314 | T2 DI BLT-RVRBNK-MLNS RPL STRW | 70Y
LC | 121405123 | 007/006 | T2 DI MNDCN WLT-FRT BRG 007/006 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2022-05-19 | 2022-05-21 | 2022-05-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45145616 | T2 DI MNDCN WLT-FRT BRG 007/006 RPR STRW | ICW
LC | 121405127 | 030/464 | T2NT DI CLAY-MARTEL 30/464 RMV DEBRIS | VICTOR | ETL.8250.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2021-08-23 | 2022-05-21 | 2022-05-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2N PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44943421 | T2NT DI CLAY-MARTEL 30/464 RMV DEBRIS | ICW
LC | 121405172 | 003/063 | T2 DI COLEMAN-COTTONWD 003/063 RPR STRW | TABLEMTN | ETL.6430.POLE.WOOD | 2021-05-26 | 2021-05-22 | 2022-07-30 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45212631 | T2 DI COLEMAN-COTTONWD 003/063 RPR STRW | ICW
LC | 121405210 | :012/063 | T2 DI CR HR CNN-SLINS-SL :12/63 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2021-05-26 | 2021-05-21 | 2021-10-04 | 2022-05-21 | 2022-05-21 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44961516 | T2 DI CR HR CNN-SLINS-SL :12/63 RPL RPTS | ICB
LC | 121405253 | 047/001 | T2 DI FORT ROSS-GUALALA 47/1 RPR STRW | LAKEVLLE | ETL.6980.INSL.NCER | 2021-05-26 | 2021-05-21 | 2022-06-14 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45144212 | T2 DI FORT ROSS-GUALALA 47/1 RPR STRW | ICW
LC | 121405299 | 032/487 | T2 DI CLAY-MARTEL+ 32/487 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2022-02-10 | 2022-05-21 | 2022-05-21 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31579298 | T2 DI CLAY-MARTEL 31/473 RPL STRW | 70Y
LC | 121405300 | 009/202 | T2 DI HAMILTON BRANCH 9/202 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-26 | 2021-05-22 | 2022-07-28 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213350 | T2 DI HAMILTON BRANCH 9/202 RPR STRW | ICW
LC | 121405321 | 008/212 | T2 DI COTTNWD-BENTON #1 8/212 RMV DEBRIS | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2022-07-20 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45213472 | T2 DI COTTNWD-BENTON #1 8/212 RMV DEBRIS | ICW
LC | 121405357 | 016/000 | T2 DI MNDCN-WLTS-FRT BRG 16/0 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2022-05-17 | 2022-05-21 | 2022-05-21 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31537422 | T2 EI MNDCNO-WLTS-FRT BRGG 15/5 REPL PL | 70Y
LC | 121405386 | 015/001 | T2 DI MENDO-WLTS-FRT BRAG 15/1 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2022-08-20 | 2022-05-21 | 2022-05-21 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31537422 | T2 EI MNDCNO-WLTS-FRT BRGG 15/5 REPL PL | 70Y
LC | 121405388 | 002/081 | T2 DI HMILTN BRNCH-CHSTR 2/81 RPR INSW | TABLEMTN | ETL.7000.INSL.NCER | 2021-05-26 | 2021-05-22 | 2022-07-22 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45147443 | T2 DI HMILTN BRNCH-CHSTR 2/81 RPR INSW | ICW
LC | 121405487 | 033/514 | T2 DI CLAY-MARTEL 033/514 RPL POLE | VICTOR | ETL.8250.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2022-02-15 | 2022-05-21 | 2022-05-21 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543355 | T2 DI CLAY-MARTEL 032/482 RPL STRW | 70Y
LC | 121405499 | 001/042 | T2 DI COTTNWD-BENTON #1 001/042 RPR STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2022-07-23 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45213474 | T2 DI COTTNWD-BENTON #1 001/042 RPR STRW | ICW
LC | 121405531 | 041/273 | T2 DI POE-RIO OSO 41/273 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-05-26 | 2021-05-21 | 2022-01-10 | 2022-05-21 | 2022-05-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45106675 | T2 DI POE-RIO OSO 41/273 RPR FOND | ICQ
LC | 121405533 | 041/273 | T2 DI POE-RIO OSO 41/273 RMV HRDT | TABLEMTN | ETL.5540.TOWR | 2021-05-26 | 2021-05-21 | 2022-01-10 | 2022-05-21 | 2022-05-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45099116 | T2 DI POE-RIO OSO 41/273 RMV HRDT | ICQ
LC | 121405534 | 002/058 | T2 DI COTTNWD-BENTON #1 002/058 COMPLETE | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-26 | 2021-05-22 | 2022-06-14 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45213476 | T2 DI COTTNWD-BENTON #1 002/058 RMV BUTT | ICW
LC | 121405557 | 035/153 | T2 DI MOS LNDNG-LOS BNOS 35/153 RPR SHLS | MOSSLNDG | ETL.6040.TOWR | 2021-05-26 | 2021-05-21 | 2022-01-15 | 2022-05-21 | 2022-05-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45066427 | T2 DI MOS LNDNG-LOS BNOS 35/153 RPR SHLS | ICW
LC | 121405558 | 035/153 | T2 DI MOS LNDNG-LOS BNOS 35/153 RPR FOND | MOSSLNDG | ETL.6040.TOWR | 2021-05-26 | 2021-05-21 | 2022-03-09 | 2022-05-21 | 2022-05-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45128057 | T2 DI MOS LNDNG-LOS BNOS 35/153 RPR FOND | ICQ
LC | 121405574 | 009/035 | T2 DI TESLA-METCALF 009/035 RPR SHLS | METCALF | ETL.6110.TOWR | 2021-05-26 | 2021-05-21 | 2021-09-23 | 2022-05-21 | 2022-05-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44959068 | T2 DI TESLA-METCALF 009/035 RPR SHLS | ICS
LC | 121405578 | 006/008 | T2 DI MNDCN-WLTS-FRT BRG 6/8 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2022-08-17 | 2022-05-21 | 2022-05-21 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540801 | T2 DI MENDO-WILL-FT BRAGG 1/6 RPL POLE | 70Y
LC | 121405584 | 002/057 | T2 DI CTTNWD-BENTON #1 002/057 RPR STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-26 | 2021-05-22 | 2022-09-01 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213477 | T2 DI CTTNWD-BENTON #1 002/057 RPR STRW | ICW
LC | 121405588 | 008/200 | T2 DI CTTNWD-BENTON #1 8/200 RMV VEG | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-26 | 2021-05-22 | 2022-04-26 | 2022-05-22 | 2022-05-22 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAR | Overgrown | Vegetation | Trim
LC | 121405590 | 014/340 | T2 DI COTTNWD-BENTON #1 014/340 RPL STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-26 | 2021-05-22 | 2022-08-22 | 2022-05-22 | 2022-05-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31541808 | T2 DI CTTNWD-BENTN #1 002/062 RPL STRW | 70Y
LC | 121405596 | 001/029 | T2 DI COTTONWOOD-BENTON #1 1/29 COMPLETE | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2022-06-10 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45213478 | T2 DI COTTONWOOD-BENTON #1 1/29 RMV BUTT | ICW
LC | 121405612 | :001/011 | T2 DI STNSLS-MLNS-MNTC 1/11 RPLC INSS | VICTOR | ETL.3830.INSL.NCER | 2021-05-26 | 2021-05-21 | 2021-12-18 | 2022-05-21 | 2022-05-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528967 | NN STANISLAUS-MLNS-MNTC RPLC INSS 11TWR | 93K
LC | 121405614 | :001/011 | T2 DI STN ML-RVNK JT 1/11 RPL INSS CMPLT | VICTOR | ETL.3840.INSL.NCER | 2021-05-26 | 2021-05-21 | 2022-05-16 | 2022-05-21 | 2022-05-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546924 | T2 DI STNSLS-MLNS-MNTC RPL INSS 8TWRS | 93K
LC | 121405619 | 034/151 | T2 DI MOSS LDNG-LS BNS 34/151 RPR FOND | MOSSLNDG | ETL.6040.TOWR | 2021-05-26 | 2021-05-21 | 2022-03-09 | 2022-05-21 | 2022-05-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45128058 | T2 DI MOSS LDNG-LS BNS 34/151 RPR FOND | ICQ
LC | 121405665 | 001/032 | T2 DI COTTONWOOD-BENTON #1 1/32 COMPLETE | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-26 | 2021-05-21 | 2022-06-10 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45213480 | T2 DI COTTONWOOD-BENTON #1 1/32 RMV BUTT | ICW
LC | 121405670 | 003/087 | T2 DI HMLTN BRNCH-CHSTR 3/87 RMV DEBRIS | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-26 | 2021-05-22 | 2022-06-27 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45213351 | T2 DI HMLTN BRNCH-CHSTR 3/87 RMV DEBRIS | ICW
LC | 121406169 | 004/004B | T2 DI HLSDL JCT-HLF MN BY 4/4B RMV VEG | METCALF | ETL.7060.POLE.NWOD | 2021-05-27 | 2021-05-17 | 2022-03-07 | 2022-05-17 | 2022-05-17 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | Overgrown | Vegetation | Remove
LC | 121406401 | 004/004B | T2 DI HLSDL JCT-HLF MN BY 4/4B RPR SWTC | METCALF | ETL.7060.SWIT | 2021-05-27 | 2021-05-17 | 2021-08-07 | 2022-05-17 | 2022-05-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Switch-Wood | Repair | 44931530 | T2 DI HLSDL JCT-HLF MN BY 4/4B RPR SWTC | ICW
LC | 121406431 | 003/068 | T2 DI COLEMAN-COTTONWOOD 3/68 COMPLETE | TABLEMTN | ETL.6430.POLE.WOOD | 2021-05-27 | 2021-05-22 | 2022-05-14 | 2022-05-22 | 2022-05-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45212633 | T2 DI COLEMAN-COTTONWOOD 3/68 RMV DBRS | ICW
LC | 121406435 | 003/068 | T2 DI COLEMAN-COTTONWOOD 3/68 RPR STRW | TABLEMTN | ETL.6430.POLE.WOOD | 2021-05-27 | 2021-05-22 | 2022-07-30 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45212635 | T2 DI COLEMAN-COTTONWOOD 3/68 RPR STRW | ICW
LC | 121406670 | :000/003 | T2 DI STAN MEL-RVRBNK JCT 0/3 RPLC INSS | VICTOR | ETL.3840.INSL.NCER | 2021-05-27 | 2021-05-21 | 2022-05-21 | 2022-05-21 | 2022-05-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546924 | T2 DI STNSLS-MLNS-MNTC RPL INSS 8TWRS | 93K
LC | 121406671 | :000/003 | T2 DI STNSLS-MLNS-MNTC 0/3 RPLC INSS | VICTOR | ETL.3830.INSL.NCER | 2021-05-27 | 2021-05-21 | 2021-12-18 | 2022-05-21 | 2022-05-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549338 | T2 DI STNSLS-MLNS-MNTC RPL INSS 8TWRS | 93K
LC | 121407455 | B019/423 | T2 DI DRM-GRS VLY-WMR B19/423 RMV STUB | SACTO | ETL.6760.POLE.WOOD | 2021-05-27 | 2021-05-17 | 2022-01-18 | 2022-05-17 | 2022-05-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45135968 | T2 DI DRM-GRS VLY-WMR B19/423 RMV STUB | ICW
LC | 121407681 | :000/006 | T2 DI BLT-RVRBNK-MLNS :0/6 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-05-27 | 2021-05-21 | 2022-04-14 | 2022-05-21 | 2022-05-21 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31539414 | T2 DI BLLT-RVRBNK-MLS SWS :1/7 RPL STRW | 70Y
LC | 121407688 | :003/018 | T2 DI STNSLS-MLNS-MNTC 3/18 RMV NEST | VICTOR | ETL.3830.TOWR | 2021-05-27 | 2021-05-21 | 2021-09-22 | 2022-05-21 | 2022-05-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44961283 | T2 DI STNSLS-MLNS-MNTC 3/18 RMV NEST | ICS
LC | 121407689 | :003/018 | T2 DI STNSLS-MLNS-MNTC 3/18 INS HRDT | VICTOR | ETL.3830.TOWR | 2021-05-27 | 2021-05-21 | 2022-02-16 | 2022-05-21 | 2022-05-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45107271 | T2 DI STNSLS-MLNS-MNTC 3/18 INS HRDT | ICQ
LC | 121408056 | 011/068 | T2 DI STANISLAUS-MNTC#2 11/68 RPL INSS | VICTOR | ETL.3820.INSL.CERA | 2021-05-27 | 2021-05-21 | 2021-11-30 | 2022-05-21 | 2022-05-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528964 | EI STANISLAUS-MANTECA#2 RPLC INSS 12TWR | 93K
LC | 121408083 | 014/360 | T2 DI CTTONWD-BENTON #1 14/360 RPR GYWW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-27 | 2021-05-21 | 2022-08-22 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213481 | T2 DI CTTONWD-BENTON #1 14/360 RPR GYWW | ICW
LC | 121408155 | 009/229 | T2 DI COTTONWD-BNTN #1 9/229 RMV DEBRIS | TABLEMTN | ETL.6640.POLE.NWOD | 2021-05-27 | 2021-05-22 | 2022-06-13 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45213482 | T2 DI COTTONWD-BNTN #1 9/229 RMV DEBRIS | ICW
LC | 121408467 | 007/128 | T2 DI PT #1-HC #2-BRNY 7/128 RPL INSW | TABLEMTN | ETL.7040.INSL.NCER | 2021-05-27 | 2021-05-24 | 2022-07-20 | 2022-05-24 | 2022-05-24 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542660 | T2 DI PT #1-HC #2-BRNY 7/128 RPL INSW | 93I
LC | 121408579 | 020/242C | T2 EI DRUM-SUMMIT #1 20/242C INS HRDW | SACTO | ETL.1440.POLE.WOOD | 2021-05-27 | 2021-05-27 | 2022-09-16 | 2022-05-27 | 2022-05-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Missing | Hardware-Wood | Install | 45195684 | T2 EI DRUM-SUMMIT #1 20/242C INS HRDW | ICW
LC | 121408614 | 011/068 | T2 DI STANISLAUS-MLNS MNT 11/68 RPR INSS | VICTOR | ETL.3830.INSL.CERA | 2021-05-27 | 2021-05-21 | 2022-02-28 | 2022-05-21 | 2022-05-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44978046 | T2 DI STANISLAUS-MLNS MNT 11/68 RPR INSS | ICS
LC | 121408700 | 001/039 | T2 DI HMILTN BRNCH-CHSTR 1/39 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-27 | 2021-05-22 | 2022-07-25 | 2022-05-22 | 2022-05-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31539905 | T2 EI HMLTN BRNCH-CHSTR 0/25 RPL STRW | 70Y
LC | 121408761 | 010/042 | T2 DI TESLA-METCALF 10/42 UNBURY | METCALF | ETL.6110.TOWR | 2021-05-27 | 2021-05-21 | 2022-06-27 | 2022-05-21 | 2022-05-21 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45211293 | T2 DI TESLA-METCALF 10/42 UNBURY | ICQ
LC | 121408801 | :001/010 | T2 DI STNSLS-MLNS-MNTC 1/10 RPLC INSS | VICTOR | ETL.3830.INSL.NCER | 2021-05-27 | 2021-05-21 | 2021-12-18 | 2022-05-21 | 2022-05-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549338 | T2 DI STNSLS-MLNS-MNTC RPL INSS 8TWRS | 93K
LC | 121408803 | :001/010 | T2 DI STN ML-RVNK JT 1/10 RPL INSS CMPLT | VICTOR | ETL.3840.INSL.NCER | 2021-05-27 | 2021-05-21 | 2022-05-20 | 2022-05-21 | 2022-05-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546924 | T2 DI STNSLS-MLNS-MNTC RPL INSS 8TWRS | 93K
LC | 121408917 | :004/024 | T2 DI STAN MEL-RVRBNK JCT 4/24 INSS COA | VICTOR | ETL.3840.INSL.NCER | 2021-05-27 | 2021-05-21 | 2022-05-13 | 2022-05-21 | 2022-05-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551875 | T2 DI STN ML SW ST-RBK JT RPL INSS 7TWR | 93K
LC | 121409079 | 001/034 | T2 DI HAMILTN BRNCH-CHSTR 01/34 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-27 | 2021-05-22 | 2022-07-25 | 2022-05-22 | 2022-05-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31539905 | T2 EI HMLTN BRNCH-CHSTR 0/25 RPL STRW | 70Y
LC | 121409134 | :002/013 | T2 DI STNSLS-MLNS-MNTC 2/18 INS HRDT | VICTOR | ETL.3830.TOWR | 2021-05-27 | 2021-05-21 | 2022-02-16 | 2022-05-21 | 2022-05-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45107269 | T2 DI STNSLS-MLNS-MNTC 2/18 INS HRDT | ICQ
LC | 121409155 | 008/143 | T2 DI PT #1-HC #2-BRNY 8/143 RPR STRW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-05-27 | 2021-05-24 | 2022-06-19 | 2022-05-24 | 2022-05-24 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45213842 | T2 DI PT #1-HC #2-BRNY 8/143 RPR STRW | ICW
LC | 121409196 | 002/053 | T2 DI COTTONWOOD-BENTON #1 2/53 COMPLETE | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-27 | 2021-05-21 | 2022-06-10 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45213483 | T2 DI COTTONWOOD-BENTON #1 2/53 RMV STUB | ICW
LC | 121410298 | 004/112 | T2 DI HMLTN BRNCH-CHSTR 4/112 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-27 | 2021-05-22 | 2022-07-25 | 2022-05-22 | 2022-05-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31540591 | T2 EI HMLTN BRNH-CHTR 4/104 RPL STRW | 70Y
LC | 121411803 | :005/029 | T2 DI STAN MEL-RVRBNK JCT :5/29 COMPLETE | VICTOR | ETL.3840.INSL.NCER | 2021-05-27 | 2021-05-21 | 2022-05-17 | 2022-05-21 | 2022-05-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551875 | T2 DI STN ML SW ST-RBK JT RPL INSS 7TWR | 93K
LC | 121412436 | 021/251 | T2 EI DRUM-SUMMIT#2 21/251L RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-05-27 | 2021-05-27 | 2022-07-12 | 2022-05-27 | 2022-05-27 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121415034 | 002/064 | T2 DI CTTNWD-BNTN #1 2/64 RMV BUTT | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-27 | 2021-05-21 | 2022-06-13 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45213484 | T2 DI CTTNWD-BNTN #1 2/64 RMV BUTT | ICW
LC | 121416430 | 001/005 | T2 WV IONE TAP 1/5 INS DAMP | VICTOR | ETL.8253.POLE.WOOD | 2021-05-27 | 2021-05-27 | 2022-07-07 | 2022-05-27 | 2022-05-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Wood | Install | 45122300 | T2 WV IONE TAP 1/5 INS DAMP | ICW
LC | 121416473 | 082/006A | T2 EI HUMBOLDT-TRINITY 82/6A RPL INSS | EUREKA | ETL.1820.INSL.CERA | 2021-05-27 | 2021-05-27 | 2022-03-25 | 2022-05-27 | 2022-05-27 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548090 | T2 DI HUMB-TRIN 82/6C RPL INSW | 93I
LC | 121416475 | 082/006C | T2 EI HUMBOLDT-TRINITY 82/6C RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2021-05-27 | 2021-05-27 | 2022-03-25 | 2022-05-27 | 2022-05-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45159556 | T2 EI HUMBOLDT-TRINITY 82/6C RPR GYWS | ICS
LC | 121416476 | 082/003B | T2 EI HUMBOLDT-TRINITY 82/3B RMV VEG | EUREKA | ETL.1820.POLE.WOOD | 2021-05-27 | 2021-05-27 | 2022-08-11 | 2022-05-27 | 2022-05-27 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Trim
LC | 121416479 | 082/006B | T2 EI HUMBOLDT-TRINITY 82/6B RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2021-05-27 | 2021-05-27 | 2022-03-25 | 2022-05-27 | 2022-05-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45159556 | T2 EI HUMBOLDT-TRINITY 82/6C RPR GYWS | ICS
LC | 121416480 | 082/006C | T2 EI HUMBOLDT-TRINITY 82/6C RPL INSS | EUREKA | ETL.1820.INSL.CERA | 2021-05-27 | 2021-05-27 | 2022-10-17 | 2022-05-27 | 2022-05-27 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548090 | T2 DI HUMB-TRIN 82/6C RPL INSW | 93I
LC | 121416481 | 082/006 | T2 EI HUMBOLDT-TRINITY 82/6A RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-27 | 2021-05-27 | 2022-03-25 | 2022-05-27 | 2022-05-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45159556 | T2 EI HUMBOLDT-TRINITY 82/6C RPR GYWS | ICS
LC | 121416555 | 034/165 | T2 EI CRTNA-MENDOCINO #1 34/165 RMV NEST | LAKEVLLE | ETL.1330.TOWR | 2021-05-27 | 2021-05-27 | 2021-12-16 | 2022-05-27 | 2022-05-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45014848 | T2 EI CRTNA-MENDOCINO #1 34/165 RMV NEST | ICW
LC | 121416935 | 008/207 | T2 DI COTTONWOOD-BENTON 008/207 RMV VEG | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-27 | 2021-05-21 | 2022-01-11 | 2022-05-21 | 2022-05-21 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121417321 | 009/006 | PTR T2 CLEAR LAKE-HOPLAND 9/6 RPL STRW | WILLITS | ETL.6390.POLE.WOOD | 2021-05-27 | 2021-05-27 | 2022-02-09 | 2022-05-27 | 2022-05-27 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543021 | PTR T2 CLEAR LAKE-HOPLAND 9/6 RPL STRW | 70Y
LC | 121417633 | 008/172 | T2 DI HAM BRCH-CHSTR 8/172 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-27 | 2021-05-22 | 2022-07-26 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213355 | T2 DI HAM BRCH-CHSTR 8/172 RPR STRW | ICW
LC | 121417754 | 030/009 | T2 DI CLAY-MARTEL 30/09 RPR INSW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-27 | 2021-05-21 | 2022-03-30 | 2022-05-21 | 2022-05-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45135170 | T2 DI CLAY-MARTEL 30/09 RPR INSW | ICW
LC | 121417789 | 001/040 | T2 DI CTNWD-BNTN #1 1/40 COMPLETE | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-27 | 2021-05-21 | 2022-06-10 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45213485 | T2 DI CTNWD-BNTN #1 1/40 RMV BUTT | ICW
LC | 121417808 | 006/140 | T2 DI HMLTN BRNCH CHSTR 006/140 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-27 | 2021-05-22 | 2022-07-22 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213356 | T2 DI HMLTN BRNCH CHSTR 006/140 RPR STRW | ICW
LC | 121417999 | 010/093B | T2 DI ELDRA-MISURI FLT#1 10/93B RPL INSW | SACTO | ETL.1530.INSL | 2021-05-27 | 2021-05-21 | 2022-06-19 | 2022-05-21 | 2022-05-21 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541998 | T2 DI ELDRA-MISURI FLT#1 10/93B RPL INSW | 93I
LC | 121418094 | 041/272 | T2 DI POE-RIO OSO 041/272 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-05-27 | 2021-05-21 | 2022-01-10 | 2022-05-21 | 2022-05-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45106674 | T2 DI POE-RIO OSO 041/272 RPR FOND | ICQ
LC | 121418158 | 028/423 | T2 DI CLAY-MARTEL 28/423 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-27 | 2021-05-21 | 2022-01-26 | 2022-05-21 | 2022-05-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45067231 | T2 DI CLAY-MARTEL 28/423 RPR STRW | ICW
LC | 121418220 | 031/468 | T2 DI CLAY-MARTEL 31/468 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-27 | 2021-05-21 | 2022-02-02 | 2022-05-21 | 2022-05-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45067232 | T2 DI CLAY-MARTEL 31/468 RPR STRW | ICW
LC | 121418225 | 006/134 | T2 DI HMLTN BRNCH-CHSTR 6/134 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-27 | 2021-05-22 | 2022-07-22 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213358 | T2 DI HMLTN BRNCH-CHSTR 6/134 RPR STRW | ICW
LC | 121418229 | 001/033 | T2 DI COTTONWOOD-BNTN #1 1/33 RMV DBRS | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-27 | 2021-05-21 | 2022-06-10 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45213487 | T2 DI COTTONWOOD-BNTN #1 1/33 RMV DBRS | ICW
LC | 121418230 | :009/005 | T2 DI BLTA RVBK MLNS SS :9/5 RPR STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-05-27 | 2021-05-21 | 2022-05-05 | 2022-05-21 | 2022-05-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45156103 | T2 DI BLTA RVBK MLNS SS :9/5 RPR STRW | ICW
LC | 121418235 | :009/007 | T2 DI BLT RVK MNS SS :9/7 RPR STRW CMPLT | VICTOR | ETL.1070.POLE.WOOD | 2021-05-27 | 2021-05-20 | 2022-05-04 | 2022-05-20 | 2022-05-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45156105 | T2 DI BLTA RVBK MLNS SS :9/7 RPR STRW | ICW
LC | 121418239 | :009/007 | T2 DI BLTA RVBK MLNS SS :9/7 RPL INSW | VICTOR | ETL.1070.INSL.NCER | 2021-05-27 | 2021-05-20 | 2022-05-04 | 2022-05-20 | 2022-05-20 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545223 | T2 DI BLTA RVK MLNS SS :011/004 RPL INSW | 93I
LC | 121418283 | :000/004 | T2 DI SN-MLS-ST-MNTC :0/4 RPL INSS CMPLT | VICTOR | ETL.3830.INSL.NCER | 2021-05-27 | 2021-05-21 | 2021-12-18 | 2022-05-21 | 2022-05-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549338 | T2 DI STNSLS-MLNS-MNTC RPL INSS 8TWRS | 93K
LC | 121418285 | :000/004 | T2 DI SN-MS-SWT-MNTC :0/4 RPL INSS CMPLT | VICTOR | ETL.3840.INSL.NCER | 2021-05-27 | 2021-05-21 | 2022-05-16 | 2022-05-21 | 2022-05-21 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546924 | T2 DI STNSLS-MLNS-MNTC RPL INSS 8TWRS | 93K
LC | 121418286 | :000/004 | T2 DI STN-MLS-SWSTA-MNTCA :0/4 RPR JUMPW | VICTOR | ETL.3830.INSL.NCER | 2021-05-27 | 2021-05-21 | 2021-12-18 | 2022-05-21 | 2022-05-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 44977947 | T2 DI STN-MLS-SWSTA-MNTCA :0/4 RPR JUMPW | ICW
LC | 121418305 | 007/184 | T2 DI COTTONWOOD-BETN #1 7/184 RPR STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-27 | 2021-05-22 | 2022-08-31 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213489 | T2 DI COTTONWOOD-BETN #1 7/184 RPR STRW | ICW
LC | 121418315 | 001/038 | T2 DI CTTNWD BNTN #1 001/038 RPR STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-27 | 2021-05-21 | 2022-09-01 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45213490 | T2 DI CTTNWD BNTN #1 001/038 RPR STRW | ICW
LC | 121418340 | 007/187 | T2 DI COTNWOOD-BENTON #1 07/187 RPR STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-27 | 2021-05-22 | 2022-08-31 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAR SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213492 | T2 DI COTNWOOD-BENTON #1 07/187 RPR STRW | ICW
LC | 121418373 | 005/037 | T2 DI SOBRANTE-"G" #1 005/037 RPL INSS | CONCORD | ETL.3720.INSL.CERA | 2021-05-27 | 2021-05-24 | 2022-07-25 | 2022-05-24 | 2022-05-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548691 | T2 EI SOBRANTE-G #1 RPL INSS 5TWRS | 93K
LC | 121418473 | 004/056 | T2 DI PT #1-HT CRK #2-BRNY 4/56 RPL HRDD | TABLEMTN | ETL.7040.POLE.WOOD | 2021-05-27 | 2021-05-24 | 2022-07-19 | 2022-05-24 | 2022-05-24 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213980 | T2 DI PT #1-HT CRK #2-BRNY 4/56 RPL HRDD | ICW
LC | 121418477 | 009/220 | T2 DI COTTONWOD-BENTON #1 9/220 RPR STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-27 | 2021-05-24 | 2022-08-31 | 2022-05-24 | 2022-05-24 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213493 | T2 DI COTTONWOD-BENTON #1 9/220 RPR STRW | ICW
LC | 121418592 | 037/163 | T2 DI MS LNDING-LOS BANS 37/163 RPR SHLS | MOSSLNDG | ETL.6040.TOWR | 2021-05-27 | 2021-05-21 | 2022-01-15 | 2022-05-21 | 2022-05-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45107237 | T2 DI MS LNDING-LOS BANS 37/163 RPR SHLS | ICS
LC | 121419819 | 027/006 | T2 DI BRBRVLL LYTNVLL 027/006 RPR SPLS | WILLITS | ETL.8365.INSL.NCER | 2021-05-28 | 2021-05-27 | 2022-04-19 | 2022-05-27 | 2022-05-27 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 44875358 | T2 DI BRBRVLL LYTNVLL 027/006 RPR SPLS | ICS
LC | 121419925 | 001/005 | T2 DI LYTNVLL-CVL 001/005 RMV BUTT | WILLITS | ETL.7390.POLE.NWOD | 2021-05-28 | 2021-05-27 | 2022-04-01 | 2022-05-27 | 2022-05-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45148131 | T2 DI LYTNVLL-CVL 001/005 RMV DEBRIS | ICW
LC | 121420146 | 052/001 | T2 DI FORT ROSS-GUALALA 052/001 RPR STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-05-28 | 2021-05-21 | 2022-06-14 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45144217 | T2 DI FORT ROSS-GUALALA 052/001 RPR STRW | ICW
LC | 121420251 | 018/003 | T2 DI MNDCN-WLLTS-FRT BRGG 18/3 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-28 | 2021-05-27 | 2022-05-16 | 2022-05-27 | 2022-05-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145814 | T2 DI MNDCN-WLLTS-FRT BRGG 18/3 RPR GYWW | ICW
LC | 121420560 | 000/004 | T2 DI COLEMN-CTTNWD 0/4 RPR INSW CMPLT | TABLEMTN | ETL.6430.INSL | 2021-05-28 | 2021-05-22 | 2022-05-16 | 2022-05-22 | 2022-05-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45212638 | T2 DI COLEMN-CTTNWD 0/4 RPR INSW | ICW
LC | 121420569 | 001/051 | T2 DI HMLTN BRNCH-CHSTR 1/51 INS HRDD | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-28 | 2021-05-22 | 2022-07-23 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45213359 | T2 DI HMLTN BRNCH-CHSTR 1/51 INS HRDD | ICW
LC | 121420593 | 000/004 | T2 DI COLEMN-CTTNWD 0/4 RPLC HRDW CMPLT | TABLEMTN | ETL.6430.POLE.WOOD | 2021-05-28 | 2021-05-22 | 2022-05-16 | 2022-05-22 | 2022-05-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45212741 | T2 DI COLEMN-CTTNWD 0/4 RPLC HRDW | ICW
LC | 121420678 | 008/178 | T2 DI HAMILTN BRNCH-CHSTR 8/178 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-28 | 2021-05-22 | 2022-07-23 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213360 | T2 DI HAMILTN BRNCH-CHSTR 8/178 RPR STRW | ICW
LC | 121420855 | 007/164 | T2 DI HMLTN BRNCH-CHSTR 7/164 RPL HRDD | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-28 | 2021-05-22 | 2022-07-27 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213361 | T2 DI HMLTN BRNCH-CHSTR 7/164 RPL HRDD | ICW
LC | 121420928 | 001/037 | T2 DI COTTONWD- BNTN 1/37 RPR STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-28 | 2021-05-24 | 2022-07-23 | 2022-05-24 | 2022-05-24 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45213521 | T2 DI COTTONWD- BNTN 1/37 RPR STRW | ICW
LC | 121420945 | 004/108 | T2 DI HMLTN BRNCH-CHSTR 4/108 RPR CNDW | TABLEMTN | ETL.7000.INSL.NCER | 2021-05-28 | 2021-05-22 | 2022-07-23 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45147444 | T2 DI HMLTN BRNCH-CHSTR 4/108 RPR CNDW | ICW
LC | 121421008 | 003/033 | T2 DI PT #1-HT CRK#2-BRY 3/33 RMV BUTT | TABLEMTN | ETL.7040.POLE.WOOD | 2021-05-28 | 2021-05-22 | 2022-06-02 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45213956 | T2 DI PT #1-HT CRK#2-BRY 3/33 RMV BUTT | ICW
LC | 121421100 | 007/161 | T2 DI HMLTN BRNCH-CHSTR 7/161 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-28 | 2021-05-22 | 2022-07-27 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213362 | T2 DI HMLTN BRNCH-CHSTR 7/161 RPR STRW | ICW
LC | 121421107 | 006/144 | T2 DI HMLTN BRNCH-CHSTR 6/144 RPR INSW | TABLEMTN | ETL.7000.INSL.NCER | 2021-05-28 | 2021-05-22 | 2022-07-25 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45147445 | T2 DI HMLTN BRNCH-CHSTR 6/144 RPR INSW | ICW
LC | 121421206 | 010/039 | T2 DI TESLA-METCALS 010/039 RPR ANCS | METCALF | ETL.6110.TOWR | 2021-05-28 | 2021-05-21 | 2022-06-27 | 2022-05-21 | 2022-05-21 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair | 45233281 | T2 DI TESLA-METCALS 010/039 RPR ANCS | ICS
LC | 121421260 | 009/200 | T2 DI HMLTN BRNCH-CHSTR 9/200 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-28 | 2021-05-22 | 2022-07-27 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213364 | T2 DI HMLTN BRNCH-CHSTR 9/200 RPR STRW | ICW
LC | 121421263 | 009/200 | T2 DI HMLTN BRNCH-CHSTR 9/200 COMPLETE | TABLEMTN | ETL.7000.INSL.NCER | 2021-05-28 | 2021-05-22 | 2022-07-27 | 2022-05-22 | 2022-05-22 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542053 | T2 DI HMLTN BRNCH-CHSTR 1/40 RPL INSW | 93I
LC | 121421264 | 003/044 | T2 DI PT #1-HT CRK #2-BRNY 3/44 RPR STRW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-05-28 | 2021-05-22 | 2022-07-19 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45213952 | T2 DI PT #1-HT CRK #2-BRNY 3/44 RPR STRW | ICW
LC | 121421457 | 003/035 | T2 DI PT #1-HT CRK#2-BRY 3/35 RPL STRW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-05-28 | 2021-05-24 | 2022-07-20 | 2022-05-24 | 2022-05-24 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542259 | T2 DI PT #1-HT CRK#2-BRY 3/35 RPL STRW | 70Y
LC | 121421671 | 008/144 | T2 DI PT#1-HT CRK#2-BRY 8/144 RMV BUTT | TABLEMTN | ETL.7040.POLE.WOOD | 2021-05-28 | 2021-05-24 | 2022-05-21 | 2022-05-24 | 2022-05-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45213949 | T2 DI PT#1-HT CRK#2-BRY 8/144 RMV BUTT | ICW
LC | 121421678 | :009/004 | T2 DI BLT-RVRBNK-MLNS :9/4 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-05-28 | 2021-05-20 | 2022-05-07 | 2022-05-20 | 2022-05-20 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536314 | T2 DI BLT-RVRBNK-MLNS RPL STRW | 70Y
LC | 121421832 | 049/001 | T2 DI FORT ROSS-GUALALA 049/001 RPL HRDD | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-05-28 | 2021-05-21 | 2022-06-14 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45144215 | T2 DI FORT ROSS-GUALALA 049/001 RPL HRDD | ICW
LC | 121421835 | 049/001 | T2 DI FORT ROSS-GUALALA 49/001 RPR STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-05-28 | 2021-05-22 | 2022-06-14 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45144215 | T2 DI FORT ROSS-GUALALA 049/001 RPL HRDD | ICW
LC | 121422105 | 009/225 | T2 DI COTTONWOOD-BENTON 009/225 RPR STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-28 | 2021-05-21 | 2022-09-01 | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213522 | T2 DI COTTONWOOD-BENTON 009/225 RPR STRW | ICW
LC | 121422237 | 005/126 | T2 DI HAMLTON BRNCH-CHSTE 5/126 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-28 | 2021-05-22 | 2022-07-22 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213365 | T2 DI HAMLTON BRNCH-CHSTE 5/126 RPR STRW | ICW
LC | 121422403 | 004/101 | T2 DI HMLTN BRNCH-CHSTR 4/101 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-28 | 2021-05-22 | 2022-07-23 | 2022-05-22 | 2022-05-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31540591 | T2 EI HMLTN BRNH-CHTR 4/104 RPL STRW | 70Y
LC | 121422409 | 005/130 | T2 DI HMLTN BRNCH-CHSTR 5/130 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-28 | 2021-05-22 | 2022-07-22 | 2022-05-22 | 2022-05-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31542055 | T2 DI HMLTN BRNCH-CHSTR 5/130 RPL STRW | 70Y
LC | 121422487 | 012/002 | WV T2 DUNLAP TAP 12/2 RPL STRW | FRESNO | ETL.9061.POLE.WOOD | 2021-05-28 | 2021-05-28 | 2022-08-24 | 2022-05-28 | 2022-05-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31591155 | WV T2 DUNLAP TAP 12/2 RPL STRW | 70Y
LC | 121422492 | 003/041 | T2 DI PT #1-HT CRK #2-BRY 3/41 RMV BUTT | TABLEMTN | ETL.7040.POLE.WOOD | 2021-05-28 | 2021-05-24 | 2022-05-22 | 2022-05-24 | 2022-05-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45213946 | T2 DI PT #1-HT CRK #2-BRY 3/41 RMV BUTT | ICW
LC | 121422705 | 008/137 | T2 DI PT#1-HT CRK#2-BRY 8/137 RPR STRW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-05-28 | 2021-05-24 | 2022-07-19 | 2022-05-24 | 2022-05-24 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45213945 | T2 DI PT#1-HT CRK#2-BRY 8/137 RPR STRW | ICW
LC | 121422849 | 002/079 | T2 DI HMLTN BRNCH-CHSTR 2/79 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-28 | 2021-05-22 | 2022-07-22 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213367 | T2 DI HMLTN BRNCH-CHSTR 2/79 RPR STRW | ICW
LC | 121424631 | 010/000 | T2 WV FULTON-HOPLAND 10/000 RPL GYWW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-28 | 2021-05-28 | 2021-06-10 | 2022-05-28 | 2022-05-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 44825729 | T2 WV FULTON-HOPLAND 10/000 RPL GYWW | ICW
LC | 121425038 | 025/107 | WV T2 MS LNDING-METCALF 25/107 RMV VEG | MOSSLNDG | ETL.6050.TOWR | 2021-05-28 | 2021-05-28 | 2022-01-28 | 2022-05-28 | 2022-05-28 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Trim
LC | 121427165 | 001/043 | T2 DI HMLTN BRNCH-CHSTR 1/43 INS HRDD | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-28 | 2021-05-22 | 2022-07-25 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45213368 | T2 DI HMLTN BRNCH-CHSTR 1/43 INS HRDD | ICW
LC | 121427168 | 006/143 | T2 DI HMLTN BRNCH-CHSTR 6/143 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-28 | 2021-05-22 | 2022-07-25 | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213369 | T2 DI HMLTN BRNCH-CHSTR 6/143 RPR STRW | ICW
LC | 121427286 | 006/097 | T2 DI PIT#1-HAT CRK#2 BNY 6/97 RPR HRDD | TABLEMTN | ETL.7040.POLE.WOOD | 2021-05-28 | 2021-05-24 | 2022-07-26 | 2022-05-24 | 2022-05-24 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213941 | T2 DI PIT#1-HAT CRK#2 BNY 6/97 RPR HRDD | ICW
LC | 121427856 | 021/166 | T2 DI MIDDLE FK-GLD HLL 21/166R RPR ANCW | SACTO | ETL.5140.POLE.WDPS | 2021-05-28 | 2021-05-26 | 2021-12-13 | 2022-05-26 | 2022-05-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Anchor-Wood | Repair | 45128353 | T2 DI MIDDLE FK-GLD HLL 21/166R RPR ANCW | ICW
LC | 121427870 | 021/166 | T2 DI MIDDLE FK-GLD HLL 21/166 RPR STRW | SACTO | ETL.5140.POLE.WDPS | 2021-05-28 | 2021-05-26 | 2021-12-14 | 2022-05-26 | 2022-05-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45018506 | T2 DI MIDDLE FK-GLD HLL 21/166 RPR STRW | ICW
LC | 121427924 | 011/096A | T2 DI PRADISE-TABLE MTN 11/096A RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-05-28 | 2021-05-26 | 2022-05-12 | 2022-05-26 | 2022-05-26 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542663 | T2 DI PRADISE-TABLE MTN 11/096A RPL INSS | 93I
LC | 121428154 | 003/004 | T2 DI LAYTONVILLE-COVELO 3/4 RPR WDPKR | WILLITS | ETL.7390.POLE.WOOD | 2021-05-28 | 2021-05-27 | 2022-06-15 | 2022-05-27 | 2022-05-27 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542885 | T2 DI LAYTONVILLE-COVELO 3/4 RPR WDPKR | 70Y
LC | 121428241 | 006/010 | T2 DI LAYTONVILLE-COVELO 6/10 RPR WDPKR | WILLITS | ETL.7390.POLE.WOOD | 2021-05-28 | 2021-05-27 | 2022-06-05 | 2022-05-27 | 2022-05-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45000035 | T2 DI LAYTONVILLE-COVELO 6/10 RPR WDPKR | ICW
LC | 121428366 | 011/093 | T2 DI PARADISE-TABLE MTN 11/93 RPL SPLW | TABLEMTN | ETL.4316.INSL.CERA | 2021-05-28 | 2021-05-26 | 2022-02-23 | 2022-05-26 | 2022-05-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Replace | 45197034 | T2 DI PARADISE-TABLE MTN 11/93 RPL SPLW | ICW
LC | 121428662 | 050/000 | T2 DI FORT ROSS-GUALALA 050/000 INS HRDD | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-05-28 | 2021-05-21 | 2021-06-10 | 2022-05-21 | 2022-05-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Wood | Install | 44935440 | T2 DI FORT ROSS-GUALALA 050/000 INS HRDD | ICW
LC | 121429785 | 019/003 | T2 DI MDCN-WLLTS-FRT BRGG 19/3 RPR SPLW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-29 | 2021-05-28 | 2022-08-18 | 2022-05-28 | 2022-05-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45145776 | T2 DI MDCN-WLLTS-FRT BRGG 19/3 RPR SPLW | ICW
LC | 121429876 | 028/004 | T2 DI GRBRVL-LYTNVL 28/4 RPR SPLW | WILLITS | ETL.8365.INSL.NCER | 2021-05-29 | 2021-05-27 | 2022-04-21 | 2022-05-27 | 2022-05-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 44830258 | T2 DI GRBRVL-LYTNVL 28/4 RPR SPLW | ICW
LC | 121430079 | 032/133 | T2 DI TESLA-METCALF 32/133 RPR SHLS | METCALF | ETL.6110.TOWR | 2021-05-29 | 2021-05-28 | 2022-07-15 | 2022-05-28 | 2022-05-28 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45151630 | T2 DI TESLA-METCALF 32/133 RPR SHLS | ICS
LC | 121430276 | 020/172 | T2 DI CRAG VIEW-CASCADE 020/172 RPR OPGW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-05-29 | 2021-05-28 | 2022-08-31 | 2022-05-28 | 2022-05-28 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45309941 | T2 DI CRAG VIEW-CASCADE 020/172 RPR OPGW | ICS
LC | 121430600 | 019/009 | T2 DI MNDCN-WLTS-FRT BRG 19/9 RPR IBWW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-29 | 2021-05-28 | 2022-08-24 | 2022-05-28 | 2022-05-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45145777 | T2 EI MNDCN-WLTS-FRT BRG 19/9 RMV BUTT | ICW
LC | 121430964 | 013/055 | T2 DI TESLA-METCALF 13/55 RMV VEG | METCALF | ETL.6110.TOWR | 2021-05-29 | 2021-05-28 | 2022-04-14 | 2022-05-28 | 2022-05-28 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121430969 | 012/108 | T2 DI CRAG VIEW-CASCADE 12/108 RPL INSS | TABLEMTN | ETL.1350.INSL | 2021-05-29 | 2021-05-29 | 2022-10-20 | 2022-05-29 | 2022-05-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619905 | T2 DI CRAG VIEW-CASCADE 12/108 RPL INSS | 93K
LC | 121431160 | 030/125 | T2 DI TESLA-METCALF 030/125 RPR GYWS | METCALF | ETL.6110.TOWR | 2021-05-29 | 2021-05-27 | 2022-07-05 | 2022-05-27 | 2022-05-27 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45233285 | T2 DI TESLA-METCALF 030/125 RPR GYWS | ICS
LC | 121431168 | 008/097 | T2 DI VEDDER TAP 8/97 RPL POLE | MIDWAY | ETL.2141.POLE.WOOD | 2021-05-29 | 2021-05-28 | 2022-02-08 | 2022-05-28 | 2022-05-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543033 | T2 DI VEDDER TAP 8/97 RPL POLE | 70Y
LC | 121431227 | 012/050 | T2 DI TESLA-METCALF 012/050 UNBURY | METCALF | ETL.6110.TOWR | 2021-05-29 | 2021-05-28 | 2022-06-27 | 2022-05-28 | 2022-05-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45211589 | T2 DI TESLA-METCALF 012/050 UNBURY | ICQ
LC | 121431266 | 019/006 | T2 DI MNDCN-WLTS-FRT BRG 19/6 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-29 | 2021-05-28 | 2022-08-24 | 2022-05-28 | 2022-05-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45145822 | T2 DI MNDCN-WLTS-FRT BRG 19/6 RPR STRW | ICW
LC | 121431314 | 030/127 | T2 DI TESLA-METCALF 030/127 RPR GYWS | METCALF | ETL.6110.TOWR | 2021-05-29 | 2021-05-28 | 2022-07-05 | 2022-05-28 | 2022-05-28 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45233292 | T2 DI TESLA-METCALF 030/127 RPR GYWS | ICS
LC | 121435273 | 013/114 | T2 DI CRAG VIEW-CASCADE 013/114 RMV NEST | TABLEMTN | ETL.1350.TOWR | 2021-06-01 | 2021-05-29 | 2022-09-16 | 2022-05-29 | 2022-05-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | Debris/Nest/etc. | Structure-Steel | Remove | 45309216 | T2 DI CRAG VIEW-CASCADE 013/114 RMV NEST | ICS
LC | 121435320 | 021/171 | T2 DI MDL FRK-GLD HL 21/171 RMV NEST | SACTO | ETL.5140.POLE.WDPS | 2021-06-01 | 2021-05-29 | 2021-08-10 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 44943255 | T2 DI MDL FRK-GLD HL 21/171 RMV NEST | ICW
LC | 121435525 | 019/166 | T2 DI CRAG VIEW-CASCADE 19/166 RPR STRW | TABLEMTN | ETL.1350.POLE.STPS | 2021-06-01 | 2021-05-28 | 2022-09-09 | 2022-05-28 | 2022-05-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45309949 | T2 DI CRAG VIEW-CASCADE 19/166 RPR STRW | ICW
LC | 121435616 | 007/002 | T2 DI MENDOCN-WLLTS-FRT BRG 7/2 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2021-06-01 | 2021-05-29 | 2022-05-19 | 2022-05-29 | 2022-05-29 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31551284 | EI MNDCNO-WLLTS-FRT BRAGG :0/9 RPL INSW | 93I
LC | 121435717 | 043/005 | T2 DI FORT ROSS-GUALALA 43/5 RPR STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-06-01 | 2021-05-29 | 2022-06-14 | 2022-05-29 | 2022-05-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45144207 | T2 DI FORT ROSS-GUALALA 43/5 RPR STRW | ICW
LC | 121435828 | 023/183 | T2 DI MDL FRK-GLD HL 23/183 RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2021-06-01 | 2021-05-29 | 2021-12-16 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45018507 | T2 DI MDL FRK-GLD HL 23/183 RPR GYWW | ICW
LC | 121435922 | 023/183 | T2 DI MDL FRK-GLD HL 23/183 RPR SPLW | SACTO | ETL.5140.INSL.NCER | 2021-06-01 | 2021-05-29 | 2021-12-16 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45018509 | T2 DI MDL FRK-GLD HL 23/183 RPR SPLW | ICW
LC | 121436164 | 013/136 | T2 DI RND MTN-CTTNWD #2 13/136 RPL INSS | TABLEMTN | ETL.5640.INSL | 2021-06-01 | 2021-05-29 | 2022-07-27 | 2022-05-29 | 2022-05-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535739 | T2 EI RND MTN-CTNWD RPL INSS 11TWRS | 93K
LC | 121436231 | 022/265 | T2 EI DRUM-SUMMIT NO. 2 22/265 HOLD | SACTO | ETL.1450.POLE.WDPS | 2021-06-01 | 2021-06-01 | 2022-06-09 | 2022-06-01 | 2022-06-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45195686 | T2 EI DRUM-SUMMIT NO. 2 22/265 RPR HRDW | ICW
LC | 121436336 | 022/266 | T2 EI DRUM-SUMMIT#2 2/266L RPL PL | SACTO | ETL.1450.POLE.WDPS | 2021-06-01 | 2021-06-01 | 2022-06-12 | 2022-06-01 | 2022-06-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31521951 | T2 EI DRUM-SUMMIT #2 REPL POLES | 70Y
LC | 121436421 | 022/266 | T2 EI DRUM-SUMMIT#2 2/266R RPL PL | SACTO | ETL.1450.POLE.WDPS | 2021-06-01 | 2021-06-01 | 2022-07-16 | 2022-06-01 | 2022-06-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31521951 | T2 EI DRUM-SUMMIT #2 REPL POLES | 70Y
LC | 121437144 | 019/003 | T2 EI MNCN-WLTS-FRT BRG 19/3 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-06-01 | 2021-06-01 | 2022-08-18 | 2022-06-01 | 2022-06-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540800 | EI MNDCN-WLLTS-FRT BRGG :0/10 REFRAME | 93E
LC | 121437435 | 000/007 | T2 DI LAYTONVILLE-COVELO 0/7 REFRAME | WILLITS | ETL.7390.POLE.WOOD | 2021-06-01 | 2021-05-27 | 2022-02-03 | 2022-05-27 | 2022-05-27 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31553454 | T2 DI LAYTONVILLE-COVELO 0/7 REFRAME | 93E
LC | 121437505 | 011/099A | T2 DI PARADISE-TABLE MTN 11/99A RPL INSW | TABLEMTN | ETL.4316.INSL.NCER | 2021-06-01 | 2021-05-27 | 2022-05-12 | 2022-05-27 | 2022-05-27 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542664 | T2 DI PARADISE-TABLE MTN 11/99A RPL INSW | 93I
LC | 121437873 | 008/059 | T2 DI COTTONWOOD-LGN CRK 8/59 RPR OPGW | TABLEMTN | ETL.4570.INSL | 2021-06-01 | 2021-06-01 | 2022-03-17 | 2022-06-01 | 2022-06-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45182726 | T2 DI COTTONWOOD-LGN CRK 8/59 RPR OPGW | ICS
LC | 121438769 | 022/103 | T2 EI FULTON-PUEBLO 22/103 RPR FOND | LAKEVLLE | ETL.1600.TOWR | 2021-06-01 | 2021-06-01 | 2022-02-01 | 2022-06-01 | 2022-06-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45151407 | T2 EI FULTON-PUEBLO 22/103 RPR FOND | ICQ
LC | 121439262 | 021/101 | T2 EI FULTON-PUEBLO 21/101 RPR STRT | LAKEVLLE | ETL.1600.TOWR | 2021-06-01 | 2021-06-01 | 2022-06-14 | 2022-06-01 | 2022-06-01 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45142253 | T2 EI FULTON-PUEBLO 21/101 RPR STRT | ICQ
LC | 121443421 | 007/052 | T2 DI ROCK CREEK-POE 7/52 RPLC INSS | TABLEMTN | ETL.5630.INSL | 2021-06-02 | 2021-06-01 | 2022-08-05 | 2022-06-01 | 2022-06-01 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535387 | T2 EI ROCK CREEK-POE RPL INSS 7TWRS | 93K
LC | 121443649 | 042/007 | T2 DI FORT ROSS-GUALALA 42/7 RPR GYWW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-06-02 | 2021-05-29 | 2022-04-27 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45144205 | T2 DI FORT ROSS-GUALALA 42/7 RPR GYWW | ICW
LC | 121444196 | 013/115 | T2 DI CRAG VIEW-CASCADE 13/115 RPR STRT | TABLEMTN | ETL.1350.TOWR | 2021-06-02 | 2021-06-01 | 2022-08-26 | 2022-06-01 | 2022-06-01 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45193884 | T2 DI CRAG VIEW-CASCADE 13/115 RPR STRT | ICQ
LC | 121444198 | 013/115 | T2 DI CRAG VIEW-CASCADE 13/115 RPR SHLS | TABLEMTN | ETL.1350.TOWR | 2021-06-02 | 2021-06-01 | 2022-10-25 | 2022-06-01 | 2022-06-01 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45309219 | T2 DI CRAG VIEW-CASCADE 13/115 RPR SHLS | ICS
LC | 121444853 | 083/005 | T2 EI HUMBOLDT-TRINITY 83/5 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-06-02 | 2021-05-28 | 2022-05-24 | 2022-05-28 | 2022-05-28 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542135 | T2 EI HUMBOLDT-TRINITY 83/5 RPL INSW | 93I
LC | 121445236 | 029/007 | T2 EI MNDCN-WLLTS-FORT BRGG 29/7 RPL STR | WILLITS | ETL.7550.POLE.WOOD | 2021-06-02 | 2021-06-01 | 2022-10-02 | 2022-06-01 | 2022-06-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP OTHR FIRE COMP OH TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31542636 | T2 DI MNDCN-WLLTS-FT BRGG 16/1 RPL STRW | 70Y
LC | 121445379 | 009/045 | T2 DI FULTON-LAKEVILLE 009/045 RPL INSS | LAKEVLLE | ETL.1600.INSL.NCER | 2021-06-02 | 2021-06-01 | 2022-02-24 | 2022-06-01 | 2022-06-01 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 121445522 | 009/045 | T2 DI SILVERADO-FUTON JCT 9/45 RPL INSS | LAKEVLLE | ETL.1610.INSL.NCER | 2021-06-02 | 2021-06-01 | 2022-03-11 | 2022-06-01 | 2022-06-01 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548684 | T2 DI SILVERADO-FUTON JCT RPL INSS 6TWR | 93K
LC | 121446834 | 018/158 | T2 DI CRAG VIEW-CASCADE 18/158 RPL INSW | TABLEMTN | ETL.1350.INSL.CERA | 2021-06-02 | 2021-05-28 | 2022-09-02 | 2022-05-28 | 2022-05-28 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542858 | T2 DI CRAG VIEW-CASCADE 18/158 RPL INSW | 93I
LC | 121447200 | 084/003 | T2 EI HUMBOLDT-TRINITY 84/3 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-06-02 | 2021-05-27 | 2022-03-25 | 2022-05-27 | 2022-05-27 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542136 | T2 EI HUMBOLDT-TRINITY 84/3 RPL INSW | 93I
LC | 121447307 | 021/180 | T2 DI CRAG VIEW-CASCADE 21/180 RPL POLE | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-02 | 2021-05-28 | 2022-09-10 | 2022-05-28 | 2022-05-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31552992 | T2 EI CRAG VIEW-CASCDE 18/154R RPL STRW | 70Y
LC | 121447381 | 013/133 | T2 DI ROUND MTN-CTTNWD #2 13/133 INS HRD | TABLEMTN | ETL.5640.TOWR | 2021-06-02 | 2021-06-02 | 2022-01-31 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Tower | Install | 45109072 | T2 DI ROUND MTN-CTTNWD #2 13/133 INS HRD | ICQ
LC | 121447624 | 047/005 | T2 DI HUMBOLDT-TRINITY 47/5L MV BUTT | EUREKA | ETL.1820.POLE.WDPS | 2021-06-02 | 2021-06-01 | 2022-03-28 | 2022-06-01 | 2022-06-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 44958550 | T2 DI HUMBOLDT-TRINITY 47/5 RPR STRW | ICW
LC | 121447627 | 047/005 | T2 DI HUMBOLDT-TRINITY 47/5L RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-02 | 2021-06-01 | 2022-04-01 | 2022-06-01 | 2022-06-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 44958550 | T2 DI HUMBOLDT-TRINITY 47/5 RPR STRW | ICW
LC | 121447628 | 047/005 | T2 DI HUMBOLDT-TRINITY 47/5C RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-02 | 2021-06-01 | 2022-04-01 | 2022-06-01 | 2022-06-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 44958551 | T2 DI HUMBOLDT-TRINITY 47/5C RPR STRW | ICW
LC | 121447681 | 047/005 | T2 DI HUMBOLDT-TRINITY 47/5 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-06-02 | 2021-06-01 | 2022-04-01 | 2022-06-01 | 2022-06-01 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542132 | T2 DI HUMBOLDT-TRINITY 47/5 RPL INSW | 93I
LC | 121447970 | 025/221 | T2 WV BRIDGVILLE-COTTNWD 25/221 RPR INSW | TABLEMTN | ETL.1110.INSL.NCER | 2021-06-02 | 2021-06-02 | 2022-06-29 | 2022-06-02 | 2022-06-02 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 45213762 | T2 WV BRIDGVILLE-COTTNWD 25/221 RPR INSW | ICW
LC | 121447975 | 025/221 | T2 WV BRIDGVILLE-COTTNWD 25/221 INS DAMP | TABLEMTN | ETL.1110.INSL.NCER | 2021-06-02 | 2021-06-02 | 2022-06-29 | 2022-06-02 | 2022-06-02 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 45213761 | T2 WV BRIDGVILLE-COTTNWD 25/221 INS DAMP | ICW
LC | 121448513 | 003/056 | T2 WV COLGATE-PALERMO 3/056 RPR SPLW | SACTO | ETL.6500.INSL.NCER | 2021-06-02 | 2021-06-02 | 2022-08-30 | 2022-06-02 | 2022-06-02 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45195687 | T2 WV COLGATE-PALERMO 3/056 RPR SPLW | ICW
LC | 121450263 | 012/143A | EI T2 DRUM-SUMMIT #1 12/143A RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2021-06-03 | 2021-05-10 | 2022-06-26 | 2022-05-10 | 2022-05-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543339 | T2 EI DRUM-SUMMIT #1 9/111 RPL STRW | 70Y
LC | 121450319 | 003/036 | T2 DI CHRISTIE-WILLOW PS 3/36 RPR STRW | CONCORD | ETL.6370.POLE.WOOD | 2021-06-03 | 2021-06-01 | 2022-03-30 | 2022-06-01 | 2022-06-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45181067 | T2 DI CHRISTIE-WILLOW PS 3/36 RPR STRW | ICW
LC | 121450378 | 048/423 | T2 DI RND MTN-CTNWD #3 48/423 RPLC INSS | TABLEMTN | ETL.5650.INSL | 2021-06-03 | 2021-06-02 | 2022-08-02 | 2022-06-02 | 2022-06-02 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548264 | T2 DI ROUD-MTN CTNWD #3 RPL INSS 8TWRS | 93K
LC | 121450406 | 033/004 | T2 DI FULTON-HOPLAND 033/004 RPL SPLW | LAKEVLLE | ETL.6890.INSL.NCER | 2021-06-03 | 2021-06-02 | 2022-06-23 | 2022-06-02 | 2022-06-02 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Replace | 45143975 | T2 DI FULTON-HOPLAND 033/004 RPL SPLW | ICW
LC | 121450464 | 029/255 | T2 DI RND MTN-CTNWD #2 29/255 RPLC HRDT | TABLEMTN | ETL.5640.TOWR | 2021-06-03 | 2021-06-02 | 2022-02-09 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45110133 | T2 DI RND MTN-CTNWD #2 29/255 RPLC HRDT | ICQ
LC | 121450850 | 069/606 | T2 DI CTTNWOOD-DLEVN #2 069/606 RMV STEP | TABLEMTN | ETL.4580.TOWR | 2021-06-03 | 2021-05-28 | 2022-05-21 | 2022-05-28 | 2022-05-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45212487 | T2 DI CTTNWOOD-DLEVN #2 069/606 RMV STEP | ICS
LC | 121451282 | 013/134 | T2 DI RND MTN-CTTNWD #2 13/134 RPR OPGW | TABLEMTN | ETL.5640.TOWR | 2021-06-03 | 2021-06-02 | 2022-07-23 | 2022-06-02 | 2022-06-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215290 | T2 DI RND MTN-CTTNWD #2 13/134 RPR OPGW | ICS
LC | 121451309 | 088/450 | T2 DI MALIN-RND MTN #2 88/450 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-03 | 2021-06-02 | 2022-07-12 | 2022-06-02 | 2022-06-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215247 | T2 DI MALIN-RND MTN #2 88/450 RPR SHLS | ICS
LC | 121451364 | 088/450 | T2 DI MALIN-RND MTN #2 88/450 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-06-03 | 2021-06-02 | 2021-06-13 | 2022-06-02 | 2022-06-02 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44853707 | T2 DI MALIN-RND MTN #2 88/450 RPR INSS | ICS
LC | 121451581 | :004/029B | T2 DI ROCK CREEK-POE :4/29B RPR FOND | TABLEMTN | ETL.5630.POLE.NWOD | 2021-06-03 | 2021-06-02 | 2022-07-26 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195454 | T2 DI ROCK CREEK-POE :4/29B RPR FOND | ICQ
LC | 121451838 | :001/009 | T2 DI ROCK CREEK-POE :1/9 RPLC INSS | TABLEMTN | ETL.5630.INSL.CERA | 2021-06-03 | 2021-06-02 | 2022-11-04 | 2022-06-02 | 2022-06-02 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535387 | T2 EI ROCK CREEK-POE RPL INSS 7TWRS | 93K
LC | 121452019 | 045/354 | T2 DI RND MTN-CTTND #2 45/354 RPL INSS | TABLEMTN | ETL.5640.INSL | 2021-06-03 | 2021-06-02 | 2022-07-31 | 2022-06-02 | 2022-06-02 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535739 | T2 EI RND MTN-CTNWD RPL INSS 11TWRS | 93K
LC | 121452292 | 019/163 | T2 DI CRAG VIEW-CASCADE 19/163 RPR OPGW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-03 | 2021-05-29 | 2022-09-02 | 2022-05-29 | 2022-05-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45309933 | T2 DI CRAG VIEW-CASCADE 19/163 RPR OPGW | ICS
LC | 121452856 | 029/178 | T2 HELMS-GREGG #1 29/178 RMV DBRS | FRESNO | ETL.4870.TOWR | 2021-06-03 | 2021-06-03 | 2022-08-23 | 2022-06-03 | 2022-06-03 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove | 45509156 | T2 HELMS-GREGG #1 29/178 RMV DBRS | ICS
LC | 121453290 | 019/010 | T2 DI MDCNO-WLLTS-FRT BRG 19/10 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-06-03 | 2021-05-28 | 2022-05-23 | 2022-05-28 | 2022-05-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542636 | T2 DI MNDCN-WLLTS-FT BRGG 16/1 RPL STRW | 70Y
LC | 121453356 | 010/001 | T2 CARIBOU-PLUMAS JCT 010/001 RPL POLE | TABLEMTN | ETL.6290.POLE.WOOD | 2021-06-03 | 2021-05-29 | 2022-10-28 | 2022-05-29 | 2022-05-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31541655 | T2 CARIBOU-PLUMAS JCT-WOOD 6/18 RPL POLE | 70Y
LC | 121453489 | 009/069 | T2 DI GREEN VLLY-LLAGAS 9/69 RPL HRDW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-06-03 | 2021-05-28 | 2021-11-22 | 2022-05-28 | 2022-05-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 44981652 | T2 DI GREEN VLLY-LLAGAS 9/69 RPL HRDW | ICW
LC | 121453649 | 020/385 | WV T2 HT CREEK #1-WSTWD 020/385 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2021-06-03 | 2021-06-03 | 2022-05-05 | 2022-06-03 | 2022-06-03 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542853 | WV T2 HT CREEK #1-WSTWD 020/385 RPL POLE | 70Y
LC | 121453768 | 000/014 | T2 DI LAYTONVILLE-COVELO 0/14 RPR GYWW | WILLITS | ETL.7390.POLE.WOOD | 2021-06-03 | 2021-05-28 | 2022-06-04 | 2022-05-28 | 2022-05-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44999868 | T2 DI LAYTONVILLE-COVELO 0/14 RPR GYWW | ICW
LC | 121454020 | 005/062 | T2 DI BURNS-LONE STAR #1 005/62 RPL STRW | MOSSLNDG | ETL.6230.POLE.WOOD | 2021-06-03 | 2021-05-29 | 2022-02-09 | 2022-05-29 | 2022-05-29 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31578759 | T2 DI BURNS-LONE STAR #1 005/62 RPL STRW | 70Y
LC | 121455865 | 013/006 | T2 CARIBOU-PLUMAS JCT 013/006 RPL POLE | TABLEMTN | ETL.6290.POLE.WOOD | 2021-06-03 | 2021-05-29 | 2022-10-30 | 2022-05-29 | 2022-05-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541655 | T2 CARIBOU-PLUMAS JCT-WOOD 6/18 RPL POLE | 70Y
LC | 121466055 | 112/000 | T2 DI HUMBOLDT-TRINITY 112/000 RPL INSW | EUREKA | ETL.1820.INSL | 2021-06-04 | 2021-06-01 | 2022-06-08 | 2022-06-01 | 2022-06-01 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542850 | T2 DI HUMBOLDT-TRINITY 112/000 RPL INSW | 93I
LC | 121466210 | 018/143 | T2 DI PT #1-CTTNWD 18/143 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-04 | 2021-06-03 | 2022-07-21 | 2022-06-03 | 2022-06-03 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45149408 | T2 DI PT #1-CTTNWD 18/143 RPR FOND | ICQ
LC | 121466213 | 013/117 | T2 DI CRAG VIEW-CASCADE 13/117 RPR SHLS | TABLEMTN | ETL.1350.TOWR | 2021-06-04 | 2021-05-29 | 2022-08-20 | 2022-05-29 | 2022-05-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45309921 | T2 DI CRAG VIEW-CASCADE 13/117 RPR SHLS | ICS
LC | 121466532 | 113/001 | T2 EI HUMBOLDT-BRIDGEVLE 113/1C RPL ANCW | EUREKA | ETL.1810.POLE.WDPS | 2021-06-04 | 2021-06-03 | 2022-05-20 | 2022-06-03 | 2022-06-03 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31542852 | T2 EI HUMBOLDT-BRIDGEVLE 113/1C RPL ANCW | 93E
LC | 121466545 | 113/001 | T2 EI HUMBOLDT-BRIDGEVLE 113/1C RPR GYWW | EUREKA | ETL.1810.POLE.WDPS | 2021-06-04 | 2021-06-03 | 2022-09-12 | 2022-06-03 | 2022-06-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45155482 | T2 EI HUMBOLDT-BRIDGEVLE 113/1C RPR GYWW | ICW
LC | 121466546 | 113/001 | T2 EI HUMBOLDT-BRIDGEVLLE 113/1L RMV VEG | EUREKA | ETL.1810.POLE.WDPS | 2021-06-04 | 2021-06-03 | 2022-03-18 | 2022-06-03 | 2022-06-03 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 121466646 | 049/246 | T2 DI MALIN-ROUND MTN #2 49/246 RPL HRDT | TABLEMTN | ETL.6020.TOWR | 2021-06-04 | 2021-06-03 | 2022-07-18 | 2022-06-03 | 2022-06-03 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45215245 | T2 DI MALIN-ROUND MTN #2 49/246 RPL HRDT | ICS
LC | 121467209 | 004/021 | T2 EI SILVERADO-FULTON JCT 4/21 RPL INSS | LAKEVLLE | ETL.1610.INSL.CERA | 2021-06-04 | 2021-06-04 | 2022-03-09 | 2022-06-04 | 2022-06-04 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31542618 | EI SILVERADO-FULTON JCT RPL INSS 6TWRS | 93K
LC | 121467250 | 004/021 | T2 EI FULTON-PUEBLO 4/21 RPL INSS | LAKEVLLE | ETL.1600.INSL.CERA | 2021-06-04 | 2021-06-04 | 2022-02-22 | 2022-06-04 | 2022-06-04 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 121467716 | 087/443 | T2 DI MALIN-RND MTN #2 087/443 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-06-04 | 2021-06-02 | 2021-06-13 | 2022-06-02 | 2022-06-02 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44853708 | T2 DI MALIN-RND MTN #2 087/443 RPR INSS | ICS
LC | 121467813 | 020/170 | T2 DI CRAG VIEW-CASCADE 20/170 RPR STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-04 | 2021-05-29 | 2022-08-14 | 2022-05-29 | 2022-05-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45309932 | T2 DI CRAG VIEW-CASCADE 20/170 RPR STRW | ICW
LC | 121468016 | 080/408 | T2 DI MALIN-ROUND MTN #2 80/408 INS HRDT | TABLEMTN | ETL.6020.TOWR | 2021-06-04 | 2021-06-03 | 2022-07-18 | 2022-06-03 | 2022-06-03 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45198251 | T2 DI MALIN-ROUND MTN #2 80/408 INS HRDT | ICQ
LC | 121468104 | 009/068 | T2 DI GREEN VLLY-LLAGAS 9/68R RPL HRDW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-06-04 | 2021-05-28 | 2021-09-28 | 2022-05-28 | 2022-05-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 44981655 | T2 DI GREEN VLLY-LLAGAS 9/68R RPL HRDW | ICW
LC | 121468161 | 043/369 | T2 DI RND MTN-CTTNWD #3 43/369 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-04 | 2021-06-03 | 2022-08-06 | 2022-06-03 | 2022-06-03 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547626 | T2 DI RND MTN-CTNWD #3 RPL INSS 9TWRS | 93K
LC | 121468285 | :001/012 | T2 DI ROCK CREEK-POE :1/12 RPR FOND | TABLEMTN | ETL.5630.TOWR | 2021-06-04 | 2021-06-02 | 2022-07-19 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195455 | T2 DI ROCK CREEK-POE :1/12 RPR FOND | ICQ
LC | 121468335 | 010/077 | T2 DI ROCK CREEK-POE 10/077 RPL INSS | TABLEMTN | ETL.5630.INSL | 2021-06-04 | 2021-06-02 | 2022-08-03 | 2022-06-02 | 2022-06-02 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535387 | T2 EI ROCK CREEK-POE RPL INSS 7TWRS | 93K
LC | 121469758 | 035/295 | T2 DI RND MTN-CTTNWD #2 035/295 RPL INSS | TABLEMTN | ETL.5640.INSL | 2021-06-04 | 2021-06-03 | 2022-08-01 | 2022-06-03 | 2022-06-03 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535739 | T2 EI RND MTN-CTNWD RPL INSS 11TWRS | 93K
LC | 121469863 | 022/008 | T2 DI PHILO JCT-ELK 22/8 RPR GYWW | WILLITS | ETL.7780.POLE.WOOD | 2021-06-04 | 2021-05-29 | 2022-03-14 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45142666 | T2 DI PHILO JCT-ELK 22/8 RPR GYWW | ICW
LC | 121470294 | 010/065 | T2 DI CTTNWD-DLVN #1 10/65 RPR INSS | TABLEMTN | ETL.4550.INSL | 2021-06-04 | 2021-05-29 | 2022-05-21 | 2022-05-29 | 2022-05-29 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45147286 | T2 DI CTTNWD-DLVN #1 10/65 RPR INSS | ICS
LC | 121470297 | 010/065 | T2 DI CTTNWD-DLVN #1 10/65 RPR SHLS | TABLEMTN | ETL.4550.TOWR | 2021-06-04 | 2021-05-29 | 2022-05-21 | 2022-05-29 | 2022-05-29 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45147287 | T2 DI CTTNWD-DLVN #1 10/65 RPR SHLS | ICS
LC | 121470890 | 024/287 | T2 EI DRUM-SUMMIT#2 24/287 RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-04 | 2021-06-04 | 2022-10-08 | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121470901 | 108/005 | T2 EI HUMBOLDT-BRIDGEVLE 108/5L RPR GYWW | EUREKA | ETL.1810.POLE.STPS | 2021-06-04 | 2021-06-04 | 2022-04-07 | 2022-06-04 | 2022-06-04 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45155394 | T2 EI HUMBOLDT-BRIDGEVLE 108/5L RPR GYWW | ICW
LC | 121470931 | 024/287 | T2 EI DRUM-SUMMIT#2 24/287C RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-04 | 2021-06-04 | 2022-10-08 | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121471021 | 024/287 | T2 EI DRUM-SUMMIT#2 24/287R RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-04 | 2021-06-04 | 2022-10-08 | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121471023 | 018/011 | T2 DI MNDCN-WLTS-FRT BRG 18/11 RPR GYWW | LAKEVLLE | ETL.7550.POLE.WOOD | 2021-06-04 | 2021-05-27 | 2021-06-28 | 2022-05-27 | 2022-05-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44880566 | T2 DI MNDCN-WLTS-FRT BRG 18/11 RPR GYWW | ICW
LC | 121471128 | 026/001 | T2 DI GRBRVL-LYTNVL 26/1 RPR STRW | WILLITS | ETL.8365.POLE.WOOD | 2021-06-04 | 2021-05-27 | 2022-04-25 | 2022-05-27 | 2022-05-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44875240 | T2 DI GRBRVL-LYTNVL 26/1 RPR STRW | ICW
LC | 121471129 | 026/001 | T2 DI GRBRVL-LYTNVL 26/1 RPR GYWW | WILLITS | ETL.8365.POLE.WOOD | 2021-06-04 | 2021-05-27 | 2022-04-25 | 2022-05-27 | 2022-05-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44875240 | T2 DI GRBRVL-LYTNVL 26/1 RPR STRW | ICW
LC | 121471182 | 025/004 | T2 DI GRBRVL-LYTNVL 25/4 RPR STRW | WILLITS | ETL.8365.POLE.WOOD | 2021-06-04 | 2021-05-27 | 2022-04-19 | 2022-05-27 | 2022-05-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44875256 | T2 DI GRBRVL-LYTNVL 25/4 RPR STRW | ICW
LC | 121471189 | 018/157 | T2 DI CRAG VIEW-CASCADE 18/157 RPR SHLW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-04 | 2021-05-28 | 2022-09-14 | 2022-05-28 | 2022-05-28 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45309942 | T2 DI CRAG VIEW-CASCADE 18/157 RPR SHLW | ICS
LC | 121471321 | 026/001 | T2 DI GRBRVL-LYTNVL 26/1 RMV BUTT | EUREKA | ETL.8365.POLE.WOOD | 2021-06-04 | 2021-05-27 | 2021-12-02 | 2022-05-27 | 2022-05-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44874939 | T2 DI GRBRVL-LYTNVL 26/1 RMV BUTT | ICW
LC | 121471326 | 010/075 | T2 DI GREEN VALLEY-LLAGAS 10/75 RPL INSW | MOSSLNDG | ETL.1720.INSL.NCER | 2021-06-04 | 2021-05-28 | 2022-09-24 | 2022-05-28 | 2022-05-28 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543246 | T2 DI GREEN VALLEY-LLAGAS 10/75 RPL INSW | 93I
LC | 121471467 | 070/609 | T2 DI COTTONWD-DELEVAN #2 70/609 RMV VEG | TABLEMTN | ETL.4580.TOWR | 2021-06-04 | 2021-05-27 | 2022-08-22 | 2022-05-27 | 2022-05-27 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121471570 | 031/129 | T2 DI TESLA-METCALF 31/129 RPR SHLS | METCALF | ETL.6110.TOWR | 2021-06-04 | 2021-05-28 | 2021-09-22 | 2022-05-28 | 2022-05-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44959065 | T2 DI TESLA-METCALF 31/129 RPR SHLS | ICS
LC | 121471571 | 031/129 | T2 DI TESLA-METCALF 31/129 RPR GYWS | METCALF | ETL.6110.TOWR | 2021-06-04 | 2021-05-28 | 2022-06-29 | 2022-05-28 | 2022-05-28 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45233293 | T2 DI TESLA-METCALF 31/129 RPR GYWS | ICS
LC | 121472548 | 041/001 | T2 DI TRINITY-MAPLE CREEK 41/1 RPL HRDD | EUREKA | ETL.8170.POLE.WOOD | 2021-06-05 | 2021-06-02 | 2022-04-26 | 2022-06-02 | 2022-06-02 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44875252 | T2 DI TRINITY-MAPLE CREEK 41/1 RPL HRDD | ICW
LC | 121473511 | 013/170 | T2 EI DELTA-MTN GATE 13/170 RPR GYWS | TABLEMTN | ETL.6750.POLE.STPS | 2021-06-05 | 2021-06-05 | 2022-07-25 | 2022-06-05 | 2022-06-05 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45297923 | T2 EI DELTA-MTN GATE 13/170 RPR GYWS | ICS
LC | 121473603 | 086/003 | T2 DI HUMBOLDT-TRINITY 86/3 RPL HRDD | EUREKA | ETL.1820.INSL.CERA | 2021-06-05 | 2021-06-04 | 2021-06-10 | 2022-06-04 | 2022-06-04 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44874090 | T2 DI HUMBOLDT-TRINITY 86/3 RPL HRDD | ICW
LC | 121473815 | 054/004 | T2 DI HUMBOLDT-TRINITY 54/4C RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-05 | 2021-05-28 | 2022-03-29 | 2022-05-28 | 2022-05-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45158940 | T2 DI HUMBOLDT-TRINITY 54/4C RPR GYWW | ICW
LC | 121474187 | 012/163 | T2 EI DLT-MT GT JCT 12/163 RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-05 | 2021-06-05 | 2022-08-23 | 2022-06-05 | 2022-06-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296698 | T2 EI DELTA-CASCADE12/163 RPR GYWW | ICW
LC | 121474233 | 012/163 | T2 EI DLT-MT GT JCT 12/163 RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-05 | 2021-06-05 | 2022-08-23 | 2022-06-05 | 2022-06-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296697 | T2 EI DELTA-CASCADE 12/163 RPR GYWW | ICW
LC | 121474234 | 012/163 | T2 EI DLT-MT GT JCT 12/163 RPR STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-05 | 2021-06-05 | 2022-08-23 | 2022-06-05 | 2022-06-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45296696 | T2 EI DELTA-CASCADE 12/163 RPR STRW | ICW
LC | 121474247 | 012/163 | T2 EI DLT-MT GT JCT 12/163 RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-05 | 2021-06-05 | 2022-08-23 | 2022-06-05 | 2022-06-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296695 | T2 EI DELTA-CASCADE 12/163 RPR GYWW | ICW
LC | 121474460 | 005/003 | T2 DI LAYTONVILLE-COVELO 5/3 RPL POLE | WILLITS | ETL.7390.POLE.WDPS | 2021-06-05 | 2021-06-04 | 2022-06-09 | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31542886 | DI LAYTONVILLE-COVELO 5/3 RPL POLE | 70Y
LC | 121474461 | 005/003 | T2 DI LAYTONVILLE-COVELO 5/3 RPL POLE | WILLITS | ETL.7390.POLE.WDPS | 2021-06-05 | 2021-06-04 | 2022-06-09 | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542886 | DI LAYTONVILLE-COVELO 5/3 RPL POLE | 70Y
LC | 121474464 | 005/003 | T2 DI LAYTONVILLE-COVELO 5/3 RPL POLE | WILLITS | ETL.7390.POLE.WDPS | 2021-06-05 | 2021-06-04 | 2022-06-09 | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31542886 | DI LAYTONVILLE-COVELO 5/3 RPL POLE | 70Y
LC | 121474584 | 011/100 | T2 DI CRAG VW-CSCD 11/100L RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-05 | 2021-06-04 | 2022-11-26 | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121474610 | 012/160 | T2 EI DELTA-MTN GATE JCT 12/160 RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-05 | 2021-06-05 | 2020-08-20 | 2022-06-05 | 2022-06-05 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31546388 | T2 DI DT-M GT JC-MN GT J 12/160 RPL INSW | 70Y
LC | 121474638 | 012/160 | T2 EI DELTA-MTN GATE JCT 12/160 RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-05 | 2021-06-05 | 2022-08-22 | 2022-06-05 | 2022-06-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31546388 | T2 DI DT-M GT JC-MN GT J 12/160 RPL INSW | 70Y
LC | 121474658 | 012/160 | T2 EI DLT-MT GT JCT 12/160 RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-05 | 2021-06-05 | 2022-08-22 | 2022-06-05 | 2022-06-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296692 | T2 EI DELTA-CASCADE 12/160 RPR GYWW | ICW
LC | 121474983 | 011/153 | T2 EI DLT-MT GT JCT 11/153 RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-05 | 2021-06-05 | 2022-08-19 | 2022-06-05 | 2022-06-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296691 | T2 EI DELTA-CASCADE 11/153 RPR GYWW | ICW
LC | 121475218 | 017/011 | T2 DI MNDCN-WLTS-FRT BRG 17/11 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-05 | 2021-05-28 | 2022-05-16 | 2022-05-28 | 2022-05-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145811 | T2 DI MNDCN-WLTS-FRT BRG 17/11 RPR GYWW | ICW
LC | 121475219 | 027/002 | T2 DI GRBRVL-LYTNVL 27/2 RMV POLE BUTT | EUREKA | ETL.8365.POLE.WOOD | 2021-06-05 | 2021-05-28 | 2021-12-02 | 2022-05-28 | 2022-05-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44875251 | T2 DI GRBRVL-LYTNVL 27/2 RMV POLE BUTT | ICW
LC | 121475290 | 016/001 | T2 DI MNDCN-WLLTS-FT BRGG 16/1 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-05 | 2021-05-29 | 2022-05-17 | 2022-05-29 | 2022-05-29 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542636 | T2 DI MNDCN-WLLTS-FT BRGG 16/1 RPL STRW | 70Y
LC | 121475293 | 021/176 | T2 DI CRAG VIEW-CASCADE 21/176 RPR SHLW | TABLEMTN | ETL.1350.POLE.STPS | 2021-06-05 | 2021-05-28 | 2022-08-31 | 2022-05-28 | 2022-05-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45309947 | T2 DI CRAG VIEW-CASCADE 21/176 RPR SHLW | ICW
LC | 121475343 | 003/009 | T2 DI MNDCN-WLTS-FRT BRG 3/9 RPL HRDW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-05 | 2021-05-29 | 2022-05-18 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45145607 | T2 EI MNDCN-WLTS-FRT BRAGG 3/9 RPR WDPKR | ICW
LC | 121475349 | 033/139 | T2 DI TESLA-METCALF 33/139 GRND WASH | METCALF | ETL.6110.INSL | 2021-06-05 | 2021-05-28 | 2022-03-09 | 2022-05-28 | 2022-05-28 | On-time | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR | Contaminated | Insulator | Ground Wash | 45107140 | T2 DI TESLA-METCALF 33/139 GRND WASH | ICD
LC | 121475401 | 020/173 | T2 DI CRAG VIEW-CASCADE 20/173 RPR CRSW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-05 | 2021-05-28 | 2022-09-14 | 2022-05-28 | 2022-05-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45309944 | T2 DI CRAG VIEW-CASCADE 20/173 RPR CRSW | ICW
LC | 121475442 | 006/005 | T2 DI CHOWCHILLA-KERCKHOFF 6/5 RPL STRW | FRESNO | ETL.1250.POLE.WDPS | 2021-06-05 | 2021-05-28 | 2022-02-16 | 2022-05-28 | 2022-05-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31581055 | T2 DI CHOWCHILLA-KERCKHOFF 7/4 RPL STRW | 70Y
LC | 121475467 | 010/145 | T2 EI DLT-MT GT JCT 10/145 RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-05 | 2021-06-05 | 2022-08-22 | 2022-06-05 | 2022-06-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296687 | T2 EI DELTA-CASCADE 10/145 RPR GYWW | ICW
LC | 121475479 | 006/005 | T2 DI MNDCN-WLTS-FRT BRG 6/5 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-05 | 2021-05-29 | 2022-05-24 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45145614 | T2 DI MNDCN-WLTS-FRT BRG 6/5 RPR STRW | ICW
LC | 121475544 | 013/006 | T2 DI MNDCN-WLLTS-FT BRGG 13/6 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-05 | 2021-05-29 | 2022-05-20 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45145779 | T2 DI MNDCN-WLLTS-FT BRGG 13/6 RPR STRW | ICW
LC | 121475565 | 020/174 | T2 DI CRAG VIEW-CASCADE 20/174R RPR SHLS | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-05 | 2021-05-28 | 2022-08-31 | 2022-05-28 | 2022-05-28 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45436126 | T2 DI CRAG VIEW-CASCADE 20/174R RPR SHLS | ICS
LC | 121475714 | 062/005 | T2 DI GRBRVLLE-LYTNVLLE 062/005 RPR GYWW | WILLITS | ETL.8365.POLE.WOOD | 2021-06-05 | 2021-05-28 | 2022-05-11 | 2022-05-28 | 2022-05-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45155778 | T2 DI GRBRVLLE-LYTNVLLE 062/005 RPR GYWW | ICW
LC | 121475734 | 001/008 | T2 DI MNDCN-WLTS-FRT BRG 1/8 RPL HRDW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-05 | 2021-05-29 | 2022-05-27 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45144312 | T2 DI MNDCN-WLTS-FRT BRG 1/8 RPL HRDW | ICW
LC | 121475792 | 010/144 | T2 EI DLT-MT GT JCT 10/144 RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-05 | 2021-06-05 | 2022-08-30 | 2022-06-05 | 2022-06-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296686 | T2 EI DELTA-CASCADE 10/144 RPR GYWW | ICW
LC | 121475794 | 010/144 | T2 EI DLT-MT GT JCT 10/144R RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-05 | 2021-06-05 | 2022-08-30 | 2022-06-05 | 2022-06-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296684 | T2 EI DELTA-CASCADE 10/144R RPR GYWW | ICW
LC | 121475887 | 010/143 | T2 EI DLT-MT GT JCT 10/143R RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-05 | 2021-06-05 | 2022-08-20 | 2022-06-05 | 2022-06-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296683 | T2 EI DELTA-CASCADE 10/143R RPR GYWW | ICW
LC | 121475965 | 010/142 | T2 EI DLT-MT GT JCT 10/142 RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-05 | 2021-06-05 | 2022-08-20 | 2022-06-05 | 2022-06-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45296377 | T2 EI DELTA-CASCADE 10/142 RPR GYWW | ICW
LC | 121476085 | 086/000EA | T2 EI HUMBOLDT-BRDGVLL 86/0EA RPR GYWW | EUREKA | ETL.1810.POLE.NWOD | 2021-06-05 | 2021-06-03 | 2022-06-14 | 2022-06-03 | 2022-06-03 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45149599 | T2 EI HUMBOLDT-BRDGVLL 86/0EA RPR GYWW | ICS
LC | 121476096 | 010/141 | T2 EI DLT-MT GT JCT 10/141 RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-05 | 2021-06-05 | 2022-08-24 | 2022-06-05 | 2022-06-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296376 | T2 EI DELTA-CASCADE 10/141 RPR GYWW | ICW
LC | 121476150 | 010/141 | T2 EI DLT-MT GT JCT 10/141R RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-05 | 2021-06-05 | 2022-08-24 | 2022-06-05 | 2022-06-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296375 | T2 EI DELTA-CASCADE 10/141 RPR GYWW | ICW
LC | 121480732 | 001/008C | T2 EI LAYTONVILLE-COVELO 1/8C RPR STRW | WILLITS | ETL.7390.POLE.WOOD | 2021-06-07 | 2021-05-17 | 2022-06-04 | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44999872 | T2 EI LAYTONVILLE-COVELO 1/8C RPR STRW | ICW
LC | 121481587 | 005/002 | T2 EI HUMBOLDT-MAPLE CREEK 5/2L RMV VEG | EUREKA | ETL.7130.POLE.WDPS | 2021-06-07 | 2021-06-05 | 2021-07-14 | 2022-06-05 | 2022-06-05 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 121481730 | 007/053 | T2 DI CTNWD-DLVN #1 7/53 RPL DAMS | TABLEMTN | ETL.4550.INSL | 2021-06-07 | 2021-05-29 | 2022-05-21 | 2022-05-29 | 2022-05-29 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 45147288 | T2 DI CTNWD-DLVN #1 7/53 RPL DAMS | ICS
LC | 121481738 | 005/000 | T2 EI HUMBOLDT-MAPLE CREEK 5/0L RMV VEG | EUREKA | ETL.7130.POLE.WDPS | 2021-06-07 | 2021-06-05 | 2021-07-21 | 2022-06-05 | 2022-06-05 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 121482239 | 014/085 | WV T2 STAN-MEL SW STA-RVR 14/85 COMPLETE | VICTOR | ETL.3840.INSL.NCER | 2021-06-07 | 2021-06-07 | 2022-05-12 | 2022-06-07 | 2022-06-07 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31537188 | T2 DI STAN MEL-RVRBNK JC RPLC INSS 2TWR | 93K
LC | 121482513 | 036/159 | T2 DI FULTON-LAKEVILLE 36/159 RPLC INSS | LAKEVLLE | ETL.4950.INSL | 2021-06-07 | 2021-06-05 | 2022-07-22 | 2022-06-05 | 2022-06-05 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540227 | T3 DI FULTON-LAKEVILLE RPL INSS 4TWRS | 93K
LC | 121482853 | 004/054 | T2 DI BURNS-LONE STAR #1 4/54 RPR STRW | MOSSLNDG | ETL.6230.POLE.WOOD | 2021-06-07 | 2021-05-29 | 2021-09-11 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44932393 | T2 DI BURNS-LONE STAR #1 4/54 RPR STRW | ICW
LC | 121482990 | 023/109 | T2 EI SLVRDO-FULTON JCT 23/109 RPL INSS | LAKEVLLE | ETL.1610.INSL.CERA | 2021-06-07 | 2021-06-07 | 2022-03-17 | 2022-06-07 | 2022-06-07 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548688 | T2 DI SLVDO FLTN JCT SW RPL INSS 6TWRS | 93K
LC | 121484223 | 017/003 | T2 DI MNDCN-WLTS-FRT BRG 17/3 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-07 | 2021-05-29 | 2022-05-23 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145809 | T2 DI MNDCN-WLTS-FRT BRG 17/3 RPR GYWW | ICW
LC | 121484227 | 050/316 | T2 DI MADISON-VACA 50/316 RPL HRDS | SACTO | ETL.2170.TOWR | 2021-06-07 | 2021-05-29 | 2022-09-28 | 2022-05-29 | 2022-05-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Steel | Replace | 45233072 | T2 DI MADISON-VACA 50/316 RPL HRDS | ICS
LC | 121484596 | 021/182 | T2 DI CRAG VIEW-CASCADE 21/182 RPR SHLW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-07 | 2021-05-28 | 2022-09-14 | 2022-05-28 | 2022-05-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45500228 | T2 DI CRAG VIEW-CASCADE 21/182 RPR SHLW | ICW
LC | 121484661 | 018/001 | T2 DI MNDCN-WLTS-FRT BRG 18/1 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-07 | 2021-05-29 | 2022-05-16 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145812 | T2 DI MNDCN-WLTS-FRT BRG 18/1 RPR GYWW | ICW
LC | 121485298 | 033/138 | T2 DI TESLA-METCALF 33/138 RPR GYWS | METCALF | ETL.6110.TOWR | 2021-06-07 | 2021-05-28 | 2022-07-05 | 2022-05-28 | 2022-05-28 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45211590 | T2 DI TESLA-METCALF 33/138 RPR GYWS | ICS
LC | 121485367 | 023/006 | T2 DI GARBRVLLE-LYTNVL 23/6 INS HRDS | WILLITS | ETL.8365.POLE.NWOD | 2021-06-07 | 2021-05-29 | 2022-04-13 | 2022-05-29 | 2022-05-29 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Steel | Install | 45155499 | T2 DI GARBRVLLE-LYTNVL 23/6 INS HRDS | ICS
LC | 121485420 | 014/011 | T2 DI MNDCN-WLTS-FRT BRG 14/11 RMV BUTT | WILLITS | ETL.7550.POLE.NWOD | 2021-06-07 | 2021-05-29 | 2022-04-29 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45145802 | T2 DI MNDCN-WLTS-FRT BRG 14/11 RMV BUTT | ICW
LC | 121485496 | 052/001 | T2 DI HUMBOLDT-TRINITY 52/1C RPLC STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-07 | 2021-05-28 | 2022-06-07 | 2022-05-28 | 2022-05-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31506039 | DI HUMBOLDT-TRINITY REPL POLES(ENG) | 70Y
LC | 121485497 | 052/001 | T2 DI HUMBOLDT-TRINITY 52/1L RPLC STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-07 | 2021-05-28 | 2022-06-07 | 2022-05-28 | 2022-05-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31506039 | DI HUMBOLDT-TRINITY REPL POLES(ENG) | 70Y
LC | 121485498 | 052/001 | T2 DI HUMBOLDT-TRINITY 52/1R RPLC STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-07 | 2021-05-28 | 2022-06-07 | 2022-05-28 | 2022-05-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31506039 | DI HUMBOLDT-TRINITY REPL POLES(ENG) | 70Y
LC | 121485517 | 015/287 | T2 DI FULTON-MOLINO 15/287 REFRAME | LAKEVLLE | ETL.6910.POLE.WOOD | 2021-06-07 | 2021-05-29 | 2022-02-15 | 2022-05-29 | 2022-05-29 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31540580 | T2 DI FULTON-MOLINO 15/287 REFRAME | 93E
LC | 121485568 | 004/052 | T2 DI BURNS-LNE STAR #1 4/52 RMV PL BUTT | MOSSLNDG | ETL.6230.POLE.WOOD | 2021-06-07 | 2021-05-29 | 2021-09-11 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44932392 | T2 DI BURNS-LNE STAR #1 4/52 RMV PL BUTT | ICW
LC | 121485658 | 020/002 | T2 DI MENDO-WLTS-FORT BRAG 20/2 RPR INSW | WILLITS | ETL.7550.INSL.NCER | 2021-06-07 | 2021-05-28 | 2022-05-24 | 2022-05-28 | 2022-05-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45145823 | T2 DI MENDO-WLTS-FORT BRAG 20/2 RPR INSW | ICW
LC | 121485671 | 013/013 | T2 DI MDCN-WLLTS-FRT BRGG 13/13 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-07 | 2021-05-29 | 2022-05-20 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45145774 | T2 DI MDCN-WLLTS-FRT BRGG 13/13 RPR STRW | ICW
LC | 121485673 | 017/006 | T2 DI MENDOCINO-WILLITS-FB 17/6 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-07 | 2021-05-29 | 2022-05-23 | 2022-05-29 | 2022-05-29 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542636 | T2 DI MNDCN-WLLTS-FT BRGG 16/1 RPL STRW | 70Y
LC | 121485674 | 013/013 | T2 DI MDCN-WLLTS-FT BGG 13/13 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-07 | 2021-05-29 | 2022-05-20 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145774 | T2 DI MDCN-WLLTS-FRT BRGG 13/13 RPR STRW | ICW
LC | 121485692 | 005/010 | T2 DI MNDCN-WLTS-FRT BRG 5/10 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-07 | 2021-05-29 | 2022-05-26 | 2022-05-29 | 2022-05-29 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542636 | T2 DI MNDCN-WLLTS-FT BRGG 16/1 RPL STRW | 70Y
LC | 121485765 | 020/168 | T2 DI CRAG VIEW-CASCADE 20/168 RPR STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-07 | 2021-05-29 | 2022-09-14 | 2022-05-29 | 2022-05-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45471569 | T2 DI CRAG VIEW-CASCADE 20/168 RPR STRW | ICW
LC | 121485831 | 019/162 | T2 DI CRAG VIEW-CASCADE 19/162 RPR STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-07 | 2021-05-29 | 2022-09-02 | 2022-05-29 | 2022-05-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45449628 | T2 DI CRAG VIEW-CASCADE 19/162 RPR STRW | ICW
LC | 121485832 | 019/162 | T2 DI CRAG VIEW-CASCADE 19/162 RPL INSW | TABLEMTN | ETL.1350.INSL | 2021-06-07 | 2021-05-29 | 2022-09-02 | 2022-05-29 | 2022-05-29 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542873 | T2 DI CRAG VIEW-CASCADE 19/162 RPL INSW | 93I
LC | 121485861 | 020/168 | T2 DI CRAG VIEW-CASCADE 20/168 RPR CRSW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-07 | 2021-05-29 | 2022-09-14 | 2022-05-29 | 2022-05-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45226171 | T2 DI CRAG VIEW-CASCADE 20/168 RPR CRSW | ICW
LC | 121485864 | 013/086 | T2 DI METCALF-GRN VALLEY 13/86L RPR GYWW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-06-07 | 2021-05-29 | 2022-07-12 | 2022-05-29 | 2022-05-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45224022 | T2 DI METCALF-GRN VALLEY 13/86 RPR GYWW | ICW
LC | 121485870 | 003/048 | T2 DI BURNS-LONE STAR 3/48 RMV PL BUTT | MOSSLNDG | ETL.6230.POLE.WOOD | 2021-06-07 | 2021-05-29 | 2021-09-11 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44932396 | T2 DI BURNS-LONE STAR 3/48 RMV PL BUTT | ICW
LC | 121485947 | 021/177 | T2 DI CRAG VIEW-CASCADE 21/177 RPL HRDW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-07 | 2021-05-28 | 2022-08-31 | 2022-05-28 | 2022-05-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45453831 | T2 DI CRAG VIEW-CASCADE 21/177 RPL HRDW | ICW
LC | 121485949 | 017/007 | T2 DI MENDO-WLITS-FRT BRG 17/7 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-07 | 2021-05-29 | 2022-05-16 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45145775 | T2 DI MENDO-WLITS-FRT BRG 17/7 RPR STRW | ICW
LC | 121485978 | 067/595 | T2 DI COTTONWD-GLENN 67/595 RPL INSS | TABLEMTN | ETL.4560.INSL | 2021-06-07 | 2021-05-29 | 2022-03-30 | 2022-05-29 | 2022-05-29 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534508 | DI COTTONWOOD-GLENN RPLC INSS 7TWRS | 93K
LC | 121486011 | 010/067 | T2 DI CTTNWD-DELVN #1 010/067 RPR FOND | TABLEMTN | ETL.4550.TOWR | 2021-06-07 | 2021-05-29 | 2022-01-04 | 2022-05-29 | 2022-05-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45099103 | T2 DI CTTNWD-DELVN #1 010/067 RPR FOND | ICQ
LC | 121486020 | 017/007 | T2 DI MENDO-WLITS-FRT BRAG 17/7 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-07 | 2021-05-29 | 2022-05-16 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145775 | T2 DI MENDO-WLITS-FRT BRG 17/7 RPR STRW | ICW
LC | 121486028 | 010/084 | T2 DI PARADISE-TBLE MTN 10/84 REFRAME | TABLEMTN | ETL.4316.POLE.STPS | 2021-06-07 | 2021-05-26 | 2022-05-11 | 2022-05-26 | 2022-05-26 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31548097 | T2 DI PARADISE-TBLE MTN 10/84 REFRAME | 93E
LC | 121486064 | 023/180 | T2 DI MIDDLE FORK-GD HL 23/180 RPL STRW | SACTO | ETL.5140.POLE.WDPS | 2021-06-07 | 2021-05-29 | 2022-09-27 | 2022-05-29 | 2022-05-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31516281 | T3 DI MDDL FRK-GLD HLL 13/108 RPL POLE | 70Y
LC | 121486106 | 012/000 | T2 DI MNDCNO-WLLTS FT BG 12/0 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-07 | 2021-05-29 | 2022-05-20 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45145778 | T2 DI MNDCNO-WLLTS FT BG 12/0 RPR STRW | ICW
LC | 121487433 | 018/000 | T2 DI MNDCN-WLTS-FRT BRG 18/0 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-08 | 2021-05-29 | 2022-08-18 | 2022-05-29 | 2022-05-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31537422 | T2 EI MNDCNO-WLTS-FRT BRGG 15/5 REPL PL | 70Y
LC | 121487617 | 011/096 | T2 DI PARADISE-TABLE MTN 11/96 RPL HRDW | TABLEMTN | ETL.4316.POLE.WOOD | 2021-06-08 | 2021-05-29 | 2022-05-12 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45240513 | T2 DI PARADISE-TABLE MTN 11/96 RPL HRDW | ICW
LC | 121487619 | 011/096 | T2 DI PARADISE-TABLE MTN 11/96 REFRAME | TABLEMTN | ETL.4316.POLE.STPS | 2021-06-08 | 2021-05-29 | 2022-05-12 | 2022-05-29 | 2022-05-29 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31602048 | T2 DI PARADISE-TABLE MTN 11/96 REFRAME | 93E
LC | 121487714 | 001/007 | T2 DI MNDCN-WLTS-FRT BRG 1/7 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-08 | 2021-05-29 | 2022-05-17 | 2022-05-29 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45144311 | T2 DI MNDCN-WLTS-FRT BRG 1/7 RPR STRW | ICW
LC | 121487718 | 011/073 | T2 DI COTTONWOOD-DLVN #1 11/73 RPR SHLS | TABLEMTN | ETL.4550.TOWR | 2021-06-08 | 2021-06-01 | 2022-05-22 | 2022-06-01 | 2022-06-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45147289 | T2 DI COTTONWOOD-DLVN #1 11/73 RPR SHLS | ICS
LC | 121487846 | 000/006 | T2 DI CHRISTIE-WLLOW PASS 000/6 RPL STRW | CONCORD | ETL.6370.POLE.WOOD | 2021-06-08 | 2021-06-01 | 2021-10-13 | 2022-06-01 | 2022-06-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543392 | T2 DI CHRISTIE-WLLOW PASS 000/6 RPL STRW | 70Y
LC | 121488053 | 011/045 | T2 DI TESLA-METCALF 011/045 UNBURY | METCALF | ETL.6110.TOWR | 2021-06-08 | 2021-06-01 | 2022-06-27 | 2022-06-01 | 2022-06-01 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45211591 | T2 DI TESLA-METCALF 011/045 UNBURY | ICQ
LC | 121488423 | 015/064 | T2 DI TESLA-METCALF 015/064 UNBURY | METCALF | ETL.6110.TOWR | 2021-06-08 | 2021-06-01 | 2022-07-07 | 2022-06-01 | 2022-06-01 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45211592 | T2 DI TESLA-METCALF 015/064 UNBURY | ICQ
LC | 121488719 | 012/059 | T2 DI FULTON-PUEBLO 012/059 RPL INSS | LAKEVLLE | ETL.1600.INSL.NCER | 2021-06-08 | 2021-06-01 | 2022-02-28 | 2022-06-01 | 2022-06-01 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 121488759 | 035/292 | T2 DI RND MTN-CTTNWD #2 35/292 RPL HRDT | TABLEMTN | ETL.5640.TOWR | 2021-06-08 | 2021-06-02 | 2022-02-10 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45110226 | T2 DI RND MTN-CTTNWD #2 35/292 RPL HRDT | ICQ
LC | 121488961 | 012/059 | T2 DI SILVERADO-FULTON 12/59 RPL INSS | LAKEVLLE | ETL.1610.INSL.NCER | 2021-06-08 | 2021-06-01 | 2022-03-16 | 2022-06-01 | 2022-06-01 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536106 | T2 DI SLVRD-FLTN JCT RPL INSS 6TWRS | 93K
LC | 121489010 | 006/085 | T2 EI DIVIDE-CABRILLO #1 6/85 RPR CNDW | PISMOBCH | ETL.1380.POLE.WDPS | 2021-06-08 | 2021-06-08 | 2022-08-20 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Conductor-Wood | Repair | 45098631 | T2 EI DIVIDE-CABRILLO #1 6/85 RPR CNDW | ICW
LC | 121489030 | 004/008 | T2 DI MNCN-WLLTS-FRT BGG 4/8 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-08 | 2021-05-29 | 2022-05-26 | 2022-05-29 | 2022-05-29 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542636 | T2 DI MNDCN-WLLTS-FT BRGG 16/1 RPL STRW | 70Y
LC | 121489039 | 006/085 | T2 EI DIVIDE-CABRILLO #1 6/85 RPR CNDW | PISMOBCH | ETL.1380.POLE.WDPS | 2021-06-08 | 2021-06-08 | 2022-08-20 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Conductor-Wood | Repair | 45098633 | T2 EI DIVIDE-CABRILLO #1 6/85 RPR CNDW | ICW
LC | 121489111 | 006/085 | T2 EI DIVIDE-CABRILLO #1 6/85 RPR CNDW | PISMOBCH | ETL.1380.POLE.WDPS | 2021-06-08 | 2021-06-08 | 2022-08-20 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Conductor-Wood | Repair | 45098634 | T2 EI DIVIDE-CABRILLO #1 6/85 RPR CNDW | ICW
LC | 121489372 | 024/290 | T2 EI DRUM-SUMMIT#2 24/290L RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-08 | 2021-06-08 | 2022-10-08 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121489430 | 024/290 | T2 EI DRUM-SUMMIT#2 24/290R RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-08 | 2021-06-08 | 2022-10-08 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121489472 | 007/054 | T2 DI COTTONWD-DLVAN #1 7/54 RPR SHLS | TABLEMTN | ETL.4550.TOWR | 2021-06-08 | 2021-06-01 | 2022-05-22 | 2022-06-01 | 2022-06-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45147290 | T2 DI COTTONWD-DLVAN #1 7/54 RPR SHLS | ICS
LC | 121489485 | 047/191 | T2 DI MIDWAY-WHIRLWIND 47/191 RPR GYWS | MIDWAY | ETL.6030.TOWR | 2021-06-08 | 2021-06-07 | 2022-01-27 | 2022-06-07 | 2022-06-07 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45067991 | T2 DI MIDWAY-WHIRLWIND 47/191 RPR GYWS | ICS
LC | 121490360 | 000/009 | T2 DI CHRISTIE-WILLOW PASS 0/9 RPL DAMW | CONCORD | ETL.6370.POLE.WOOD | 2021-06-08 | 2021-06-01 | 2021-10-13 | 2022-06-01 | 2022-06-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Damper-Wood | Replace | 44959015 | T2 DI CHRISTIE-WILLOW PASS 0/9 RPL DAMW | ICW
LC | 121490695 | 044/181 | T2 DI MIDWAY-WHIRLWIND 044/181 RPL SHLS | MIDWAY | ETL.6030.TOWR | 2021-06-08 | 2021-06-08 | 2021-12-17 | 2022-06-08 | 2022-06-08 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44987470 | T2 DI MIDWAY-WHIRLWIND 044/181 RPL SHLS | ICS
LC | 121490852 | 018/593 | T2 DI SPAULNG-SUMMIT 18/593 RPL INSS | SACTO | ETL.8060.INSL.NCER | 2021-06-08 | 2021-06-08 | 2022-09-14 | 2022-06-08 | 2022-06-08 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31543809 | T2 DI SPAULNG-SUMMIT RPL INSS 2TWRS | 93K
LC | 121491064 | 001/063 | T2 DI SPALDNG-SUMMIT 1/63 RPR INSW | SACTO | ETL.8060.INSL.NCER | 2021-06-08 | 2021-06-07 | 2022-09-25 | 2022-06-07 | 2022-06-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45219537 | T2 DI SPALDNG-SUMMIT 1/63 RPR INSW | ICW
LC | 121491202 | 002/086 | T2 DI SPAULDNG-SUMMIT 002/086 COTTER | SACTO | ETL.8060.SWIT | 2021-06-08 | 2021-06-07 | 2022-09-26 | 2022-06-07 | 2022-06-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45219538 | T2 DI SPAULDNG-SUMMIT 002/086 COTTER | ICW
LC | 121491935 | 007/159 | T2 DI HMLTN BRNCH-CHSTR 7/159 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-06-08 | 2021-06-08 | 2022-07-26 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213370 | T2 DI HMLTN BRNCH-CHSTR 7/159 RPR STRW | ICW
LC | 121492097 | 007/051 | T2 EI SBRNTE-GZY-CLRMNT #2 7/51 RPR FOND | CONCORD | ETL.3750.TOWR | 2021-06-08 | 2021-06-08 | 2021-08-24 | 2022-06-08 | 2022-06-08 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAR | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44948312 | T2 EI SBRNTE-GZY-CLRMNT #2 7/51 RPR FOND | ICQ
LC | 121492266 | 012/091 | T2 DI CARIBOU-TABLE MTN 12/91 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-08 | 2021-06-01 | 2022-06-21 | 2022-06-01 | 2022-06-01 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121492325 | 086/439 | T2 DI MLN-RND MNTN #2 086/439 RPR FOND | TABLEMTN | ETL.6020.TOWR | 2021-06-08 | 2021-06-02 | 2022-07-14 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45198263 | T2 DI MLN-RND MNTN #2 086/439 RPR FOND | ICQ
LC | 121492326 | 086/439 | T2 DI MLN-RND MNTN #2 086/439 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-06-08 | 2021-06-02 | 2021-06-13 | 2022-06-02 | 2022-06-02 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44857412 | T2 DI MLN-RND MNTN #2 086/439 RPR INSS | ICS
LC | 121492362 | 008/049 | T2 WV SBRT-STD OIL SS #1 8/49 RPR JMPRS | CONCORD | ETL.3800.INSL | 2021-06-08 | 2021-06-08 | 2021-07-11 | 2022-06-08 | 2022-06-08 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31530960 | DI SBNT-STD OIL SW ST#1 RPL INSS IN 4 TW | 93K
LC | 121492516 | 018/076 | T2 DI GEYSERS #12-FLTN 018/076 INS HRDD | LAKEVLLE | ETL.4750.TOWR | 2021-06-08 | 2021-06-02 | 2022-01-28 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45150734 | T2 DI GEYSERS #12-FLTN 018/076 INS HRDD | ICQ
LC | 121492622 | 002/022 | T2 DI CHRISTIE-WILLOW PASS 2/22 RPL STRW | CONCORD | ETL.6370.POLE.WDPS | 2021-06-08 | 2021-06-01 | 2022-12-08 | 2022-06-01 | 2022-06-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31543891 | T2 DI CHRISTIE-WILLOW PASS 2/22 RPL STRW | 70Y
LC | 121492623 | 002/022 | T2 DI CHRISTIE-WILLOW PASS 2/22 RPL STRW | CONCORD | ETL.6370.POLE.WDPS | 2021-06-08 | 2021-06-01 | 2022-12-08 | 2022-06-01 | 2022-06-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31543891 | T2 DI CHRISTIE-WILLOW PASS 2/22 RPL STRW | 70Y
LC | 121492656 | 039/319 | T2 DI RND MTN-CTNWD #2 39/314 RPR INSS | TABLEMTN | ETL.5640.INSL | 2021-06-08 | 2021-05-29 | 2022-08-01 | 2022-05-29 | 2022-05-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45215289 | T2 DI RND MTN-CTNWD #2 39/314 RPR INSS | ICS
LC | 121492750 | :004/026 | T2 DI ROCK CREEK-POE :004/026 RPR FOND | TABLEMTN | ETL.5630.TOWR | 2021-06-08 | 2021-06-02 | 2022-07-12 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195457 | T2 DI ROCK CREEK-POE :004/026 RPR FOND | ICQ
LC | 121492777 | 008/055 | T2 DI MRGA-SAN LEANDRO #1 8/55 RPR FOND | CONCORD | ETL.2770.TOWR | 2021-06-08 | 2021-06-02 | 2022-02-10 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45168391 | T2 DI MRGA-SAN LEANDRO #1 8/55 RPR FOND | ICQ
LC | 121492880 | :007/057 | T2 DI ROCK CREEK-POE :007/057 RPL HRDT | TABLEMTN | ETL.5630.TOWR | 2021-06-08 | 2021-06-02 | 2022-07-19 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45159483 | T2 DI ROCK CREEK-POE :007/057 RPL HRDT | ICQ
LC | 121492892 | 014/105 | T2 DI CARIBOU-TABLE MTN 14/105 RMV STEP | TABLEMTN | ETL.4440.TOWR | 2021-06-08 | 2021-05-29 | 2022-07-07 | 2022-05-29 | 2022-05-29 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45159360 | T2 DI CARIBOU-TABLE MTN 14/105 RMV STEP | ICQ
LC | 121492925 | 053/480 | T2 DI PIT #1-COTTONWOOD 53/480 RMV DBRS | TABLEMTN | ETL.5390.TOWR | 2021-06-08 | 2021-06-02 | 2022-03-08 | 2022-06-02 | 2022-06-02 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45182733 | T2 DI PIT #1-COTTONWOOD 53/480 RMV DBRS | ICS
LC | 121492955 | 031/474 | T2 DI CLAY-MARTEL 31/474L RPR GYWW | VICTOR | ETL.8250.POLE.WDPS | 2021-06-08 | 2021-06-01 | 2022-07-26 | 2022-06-01 | 2022-06-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45067233 | T2 DI CLAY-MARTEL 31/474 RPR GYWW | ICW
LC | 121492956 | 031/474 | T2 DI CLAY-MARTEL 31/474M RPR GYWW | VICTOR | ETL.8250.POLE.WDPS | 2021-06-08 | 2021-06-01 | 2022-07-26 | 2022-06-01 | 2022-06-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45067234 | T2 DI CLAY-MARTEL 31/474 RPR GYWW | ICW
LC | 121492958 | 031/474 | T2 DI CLAY-MARTEL 31/474R RPR GYWW | VICTOR | ETL.8250.POLE.WDPS | 2021-06-08 | 2021-06-01 | 2022-07-26 | 2022-06-01 | 2022-06-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45067235 | T2 DI CLAY-MARTEL 31/474 RPR GYWW | ICW
LC | 121492967 | 108/003 | T2 DI HUMBLDT BRDGVL 108/3 RPR SWTCH | EUREKA | ETL.1810.SWIT | 2021-06-08 | 2021-06-02 | 2022-04-06 | 2022-06-02 | 2022-06-02 | On-time | 623 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR SR22 | Out of Adjustment | Switch | Repair | 45058224 | T2 DI HUMBLDT BRDGVL 108/3 RPR SWIS #267 | ICE
LC | 121492975 | 016/123 | T2DI CARIBOU-TABLE MTN X16/123 HRDT INST | TABLEMTN | ETL.4440.TOWR | 2021-06-08 | 2021-06-01 | 2022-07-19 | 2022-06-01 | 2022-06-01 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45159364 | T2DI CARIBOU-TABLE MTN X16/123 HRDT INST | ICQ
LC | 121492994 | 004/051 | T2 DI SNTH LN-PACIFICA 4/51 RMV VEG | METCALF | ETL.7575.POLE.WOOD | 2021-06-08 | 2021-06-01 | 2022-07-28 | 2022-06-01 | 2022-06-01 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121492996 | 030/001 | T2 DI FULTON-HOPLAND 30/1 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-06-08 | 2021-06-02 | 2022-06-22 | 2022-06-02 | 2022-06-02 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143963 | T2 DI FULTON-HOPLAND 30/1 RPR STRW | ICW
LC | 121493047 | 050/000 | T2 DI HUMBOLDT-TRINITY 050/000 RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-08 | 2021-06-01 | 2022-03-27 | 2022-06-01 | 2022-06-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45158838 | T2 DI HUMBOLDT-TRINITY 050/000 RPR STRW | ICW
LC | 121493054 | 050/000 | T2 DI HUMBOLDT-TRINITY 050/000 RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-08 | 2021-06-01 | 2022-03-29 | 2022-06-01 | 2022-06-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45158838 | T2 DI HUMBOLDT-TRINITY 050/000 RPR STRW | ICW
LC | 121493055 | 050/000 | T2 DI HUMBOLDT-TRINITY 050/000 RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-08 | 2021-06-01 | 2022-03-29 | 2022-06-01 | 2022-06-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45158838 | T2 DI HUMBOLDT-TRINITY 050/000 RPR STRW | ICW
LC | 121493079 | 024/008 | T2 DI MDCN-WLLT-FRT BRGG 24/8 RPL HRDW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-08 | 2021-05-28 | 2022-05-20 | 2022-05-28 | 2022-05-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45148038 | T2 DI MDCN-WLLT-FRT BRGG 24/8 RPL HRDW | ICW
LC | 121493094 | 038/013 | T2 DI FULTON-HOPLAND 38/13 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-06-08 | 2021-06-02 | 2022-06-21 | 2022-06-02 | 2022-06-02 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45144024 | T2 DI FULTON-HOPLAND 38/13 RPR STRW | ICW
LC | 121493127 | 020/141 | T2 DI CRIBU-TBL MNTN-TWR 20/141 DBRS CPT | TABLEMTN | ETL.4440.TOWR | 2021-06-08 | 2021-06-01 | 2022-06-24 | 2022-06-01 | 2022-06-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45212441 | T2 DI CRIBU-TBL MNTN-TWR 20/141 RMV STEP | ICW
LC | 121493142 | 046/355 | T2 DI RND MTN CTTNWD 046/355 RPL INSS | TABLEMTN | ETL.5640.INSL | 2021-06-08 | 2021-06-02 | 2022-07-31 | 2022-06-02 | 2022-06-02 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535739 | T2 EI RND MTN-CTNWD RPL INSS 11TWRS | 93K
LC | 121493146 | 111/006A | T2 DI HMBLT TRNTY 111/006A RPL HRDW | EUREKA | ETL.1820.POLE.NWOD | 2021-06-08 | 2021-06-01 | 2022-08-25 | 2022-06-01 | 2022-06-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45079104 | T2 DI HMBLT TRNTY 111/006A RPL HRDW | ICW
LC | 121493150 | 068/601 | T2 DI CTNWD-DLVN #2 68/601 INS HRDT | TABLEMTN | ETL.4580.TOWR | 2021-06-08 | 2021-05-29 | 2022-01-06 | 2022-05-29 | 2022-05-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45107500 | T2 DI CTNWD-DLVN #2 68/601 INS HRDT | ICQ
LC | 121493152 | 002/027 | T2 DI CHRISTIE-WILLOW PASS 2/27 RPR STRW | CONCORD | ETL.6370.POLE.WOOD | 2021-06-08 | 2021-06-01 | 2022-03-30 | 2022-06-01 | 2022-06-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45181063 | T2 DI CHRISTIE-WILLOW PASS 2/27 RPR STRW | ICW
LC | 121493230 | 007/052 | T2 DI CTTNWD-DLVN #1 7/52 RPR SHLD | TABLEMTN | ETL.4550.TOWR | 2021-06-08 | 2021-06-01 | 2022-05-22 | 2022-06-01 | 2022-06-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45147291 | T2 DI CTTNWD-DLVN #1 7/52 RPR SHLD | ICS
LC | 121493255 | 023/182 | T2 DI MDL FRK-GLD HL 23/182 RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2021-06-08 | 2021-06-01 | 2022-10-29 | 2022-06-01 | 2022-06-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45018527 | T2 DI MDL FRK-GLD HL 23/182 RPR GYWW | ICW
LC | 121493259 | 013/111 | T2 DI CRAG VIEW-CASCADE 13/111L RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-08 | 2021-06-01 | 2022-10-01 | 2022-06-01 | 2022-06-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121493268 | 092/472 | T2 DI MLN RND MTN #2 092/472 RPR FOND | TABLEMTN | ETL.6020.TOWR | 2021-06-08 | 2021-06-01 | 2022-07-13 | 2022-06-01 | 2022-06-01 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45198275 | T2 DI MLN RND MTN #2 092/472 RPR FOND | ICQ
LC | 121493281 | 009/069 | T2 DI ROCK CREEK-POE-TOWER 9/69 RMV VEG | TABLEMTN | ETL.5630.TOWR | 2021-06-08 | 2021-06-02 | 2022-10-19 | 2022-06-02 | 2022-06-02 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121493284 | 006/053 | T2 DI PIT #1-COTTONWOOD 6/53 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-06-08 | 2021-06-02 | 2022-02-18 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45180996 | T2 DI PIT #1-COTTONWOOD 6/53 RPR STRT | ICQ
LC | 121493286 | 017/125 | T2 DI CARIBOU-TBL MNTIN 17/125 INST HRDT | TABLEMTN | ETL.4440.TOWR | 2021-06-08 | 2021-06-02 | 2022-07-19 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45159365 | T2 DI CARIBOU-TBL MNTIN 17/125 INST HRDT | ICQ
LC | 121493293 | 004/007 | DI T2 BLLT-RBK-MLS SWST 4/7 RPL STRW | VICTOR | ETL.1070.POLE.WDPS | 2021-06-08 | 2021-06-01 | 2022-04-14 | 2022-06-01 | 2022-06-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543454 | DI T2 BLLT-RBK-MLS SWST 4/7 RPL STRW | 70Y
LC | 121493297 | 004/007 | DI T2 BLLT-RBK-MLS SWST 4/7 RPL STRW | VICTOR | ETL.1070.POLE.WDPS | 2021-06-08 | 2021-06-01 | 2022-04-14 | 2022-06-01 | 2022-06-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543454 | DI T2 BLLT-RBK-MLS SWST 4/7 RPL STRW | 70Y
LC | 121493303 | 012/089 | T2 DI GRN VLLY-LLAGAS 12/89 RPR GYWW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-06-08 | 2021-05-28 | 2021-09-30 | 2022-05-28 | 2022-05-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44981656 | T2 DI GRN VLLY-LLAGAS 12/89 RPR GYWW | ICW
LC | 121493326 | 015/065 | T2 DI TESLA-METCALF 015/065 RPR FOND | METCALF | ETL.6110.TOWR | 2021-06-08 | 2021-06-01 | 2022-07-07 | 2022-06-01 | 2022-06-01 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45233296 | T2 DI TESLA-METCALF 015/065 RPR FOND | ICQ
LC | 121493335 | 010/043 | T2 DI TESLA-METCALF 010/043 RPR GYWS | METCALF | ETL.6110.TOWR | 2021-06-08 | 2021-06-01 | 2022-06-27 | 2022-06-01 | 2022-06-01 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45233297 | T2 DI TESLA-METCALF 010/043 RPR GYWS | ICS
LC | 121493356 | 019/152 | T2 DI DRUM-RIO OSO #1 19/152 RPR FOND | SACTO | ETL.1420.TOWR | 2021-06-08 | 2021-05-29 | 2022-03-07 | 2022-05-29 | 2022-05-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45177730 | T2 DI DRUM-RIO OSO #1 19/152 RPR FOND | ICQ
LC | 121493433 | 005/054 | T2 DI SNEATH LANE-PACIFICA 5/54 RMV VEG | METCALF | ETL.7575.POLE.WOOD | 2021-06-08 | 2021-06-01 | 2022-07-28 | 2022-06-01 | 2022-06-01 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121493438 | 012/088 | T2 DI GREEN VALLEY-LLAGAS 12/88 RPL INSW | MOSSLNDG | ETL.1720.INSL.CERA | 2021-06-08 | 2021-05-28 | 2022-08-04 | 2022-05-28 | 2022-05-28 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548489 | T2 DI GREEN VALLEY-LLAGAS 12/88 RPL INSW | 93I
LC | 121493439 | 012/088 | T2 DI GREEN VALLEY-LLAGAS 12/88 RPR STRW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-06-08 | 2021-05-28 | 2021-09-29 | 2022-05-28 | 2022-05-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 44981658 | T2 DI GREEN VALLEY-LLAGAS 12/88 RPR STRW | ICW
LC | 121493468 | :009/066 | T2 DI ROCK CREK-POE-TWR :09/66 RPR FOND | TABLEMTN | ETL.5630.TOWR | 2021-06-08 | 2021-06-02 | 2022-08-24 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195459 | T2 DI ROCK CREK-POE-TWR :09/66 RPR FOND | ICQ
LC | 121493486 | 017/169 | T2 DI RND MTN CTTNWD 017/169 RPR OPGW | TABLEMTN | ETL.5640.TOWR | 2021-06-08 | 2021-06-02 | 2022-07-24 | 2022-06-02 | 2022-06-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215287 | T2 DI RND MTN CTTNWD 017/169 RPR OPGW | ICS
LC | 121493520 | 020/144A | T2 DI CARIBOU-TBL MTN 20/144A RPL HRDS | TABLEMTN | ETL.4440.POLE.NWOD | 2021-06-08 | 2021-06-01 | 2022-06-23 | 2022-06-01 | 2022-06-01 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45212442 | T2 DI CARIBOU-TBL MTN 20/144A RPL HRDS | ICS
LC | 121493522 | 040/321 | T2 DI RND MTN CTTNWD 040/321 RPL INSS | TABLEMTN | ETL.5640.INSL | 2021-06-08 | 2021-06-01 | 2022-07-30 | 2022-06-01 | 2022-06-01 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535739 | T2 EI RND MTN-CTNWD RPL INSS 11TWRS | 93K
LC | 121493580 | :009/066 | T2 DI ROCK CREK-POE-TWR :09/66 RPL HRDT | TABLEMTN | ETL.5630.TOWR | 2021-06-08 | 2021-06-02 | 2022-07-20 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45159484 | T2 DI ROCK CREK-POE-TWR :09/66 RPL HRDT | ICQ
LC | 121493584 | 014/061 | T2 DI TESLA-METCALF-TOWER 14/61 RPR GYWS | METCALF | ETL.6110.TOWR | 2021-06-08 | 2021-06-01 | 2022-06-28 | 2022-06-01 | 2022-06-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45233298 | T2 DI TESLA-METCALF-TOWER 14/61 RPR GYWS | ICW
LC | 121493617 | 032/482 | T2 DI CLAY-MARTEL 032/482 RPL STRW | VICTOR | ETL.8250.POLE.WDPS | 2021-06-08 | 2021-06-01 | 2022-02-11 | 2022-06-01 | 2022-06-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543355 | T2 DI CLAY-MARTEL 032/482 RPL STRW | 70Y
LC | 121493618 | 032/482 | T2 DI CLAY-MARTEL 032/482 RPL STRW | VICTOR | ETL.8250.POLE.WDPS | 2021-06-08 | 2021-06-01 | 2022-02-11 | 2022-06-01 | 2022-06-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543355 | T2 DI CLAY-MARTEL 032/482 RPL STRW | 70Y
LC | 121493660 | 032/482 | T2 DI CLAY-MARTEL 032/482 RPL STRW | VICTOR | ETL.8250.POLE.WDPS | 2021-06-08 | 2021-06-01 | 2022-02-15 | 2022-06-01 | 2022-06-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543355 | T2 DI CLAY-MARTEL 032/482 RPL STRW | 70Y
LC | 121493665 | 057/284 | T2 DI ALIN-ROUND MNT #2 57/284 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-08 | 2021-06-02 | 2022-07-14 | 2022-06-02 | 2022-06-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215244 | T2 DI ALIN-ROUND MNT #2 57/284 RPR SHLS | ICS
LC | 121493738 | 046/399 | T2 DI RND MTN CTTNWD #3 046/399 RPL HRDT | TABLEMTN | ETL.5650.TOWR | 2021-06-08 | 2021-06-02 | 2022-01-19 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45110554 | T2 DI RND MTN CTTNWD #3 046/399 RPL HRDT | ICQ
LC | 121493748 | 045/352 | T2 DI RND MNTN-CTNWD #2 45/352 RPR OPGW | TABLEMTN | ETL.5640.TOWR | 2021-06-08 | 2021-06-03 | 2022-07-30 | 2022-06-03 | 2022-06-03 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215286 | T2 DI RND MNTN-CTNWD #2 45/352 RPR OPGW | ICS
LC | 121493782 | 046/398 | T2 DI RND MTN-COTTONWD 3 46/698 RPR HRDT | TABLEMTN | ETL.5650.TOWR | 2021-06-08 | 2021-06-02 | 2022-01-18 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45110553 | T2 DI RND MTN-COTTONWD 3 46/698 RPR HRDT | ICQ
LC | 121493784 | :007/050 | T2 DI ROCK CREEK-POE :007/050 RPL INSS | TABLEMTN | ETL.5630.INSL | 2021-06-08 | 2021-06-01 | 2022-08-06 | 2022-06-01 | 2022-06-01 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535387 | T2 EI ROCK CREEK-POE RPL INSS 7TWRS | 93K
LC | 121494514 | 023/276 | T2 DI DRUM-SUMMIT #1 23/276L RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-09 | 2021-06-08 | 2022-09-02 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45193294 | T2 DI DRUM-SUMMIT #1 2/276L RPR STRW | ICW
LC | 121494637 | 007/082 | T2 DI WST PNT-VLLY SPRNGS 7/82 RPR SPLW | VICTOR | ETL.8350.INSL.CERA | 2021-06-09 | 2021-06-08 | 2022-05-10 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45156110 | T2 DI WST PNT-VLLY SPRNGS 7/82 RPR SPLW | ICW
LC | 121494638 | 009/113 | T2 DI DRUM-SUMMIT #1 9/113L RPL HRDD | SACTO | ETL.1440.POLE.WDPS | 2021-06-09 | 2021-06-08 | 2022-08-23 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45195699 | T2 DI DRUM-SUMMIT #1 9/113L RPL HRDD | ICW
LC | 121494760 | 009/113 | T2 DI DRUM-SUMMIT #1 9/113R RPL HRDD | SACTO | ETL.1440.POLE.WDPS | 2021-06-09 | 2021-06-08 | 2022-08-23 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45195700 | T2 DI DRUM-SUMMIT #1 9/113R RPL HRDD | ICW
LC | 121494982 | 032/273 | T2 DI ROUND MTN-CTNWD #2 32/273 RPL INSS | TABLEMTN | ETL.5640.INSL | 2021-06-09 | 2021-06-02 | 2022-08-01 | 2022-06-02 | 2022-06-02 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535739 | T2 EI RND MTN-CTNWD RPL INSS 11TWRS | 93K
LC | 121495047 | :005/047 | T2 DI PIT #3-PIT #1 :005/047 RPR INSS | TABLEMTN | ETL.5400.INSL | 2021-06-09 | 2021-06-02 | 2022-06-24 | 2022-06-02 | 2022-06-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213903 | T2 DI PIT #3-PIT #1 :005/047 RPR INSS | ICS
LC | 121495266 | 049/428 | T2 DI ROUND MTN-CTNWD #3 49/428 RPL HRDT | TABLEMTN | ETL.5650.TOWR | 2021-06-09 | 2021-06-02 | 2022-02-24 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45110998 | T2 DI ROUND MTN-CTNWD #3 49/428 RPL HRDT | ICQ
LC | 121495305 | 016/504 | T2 DI SPAULDING-SUMMIT 16/504 RPR INSW | SACTO | ETL.8060.INSL.CERA | 2021-06-09 | 2021-06-08 | 2021-08-18 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 121495596 | 011/073 | T2 DI COTTONWOOD-LOGAN 11/73 RPR INSS | TABLEMTN | ETL.4550.INSL | 2021-06-09 | 2021-06-01 | 2022-06-09 | 2022-06-01 | 2022-06-01 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45147292 | T2 DI COTTONWOOD-LOGAN 11/73 RPR INSS | ICS
LC | 121495635 | 008/171 | T2 DI HMLTN BRNCH-CHSTR 8/171 RPLC INSW | TABLEMTN | ETL.7000.INSL.CERA | 2021-06-09 | 2021-06-08 | 2022-07-27 | 2022-06-08 | 2022-06-08 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542053 | T2 DI HMLTN BRNCH-CHSTR 1/40 RPL INSW | 93I
LC | 121495804 | 013/062 | T2 DI PITTSBURG-TESLA #1 13/062 RMV NEST | CONCORD | ETL.5510.TOWR | 2021-06-09 | 2021-06-02 | 2021-09-28 | 2022-06-02 | 2022-06-02 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44959039 | T2 DI PITTSBURG-TESLA #1 13/062 RMV NEST | ICS
LC | 121495970 | 010/164 | T2 DI TEJON-LEBEC 10/164 RMV STUB | MIDWAY | ETL.9250.POLE.NWOD | 2021-06-09 | 2021-06-08 | 2021-08-09 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44874348 | T2 DI TEJON-LEBEC 10/164 RMV STUB | ICW
LC | 121496068 | 018/594 | T2 DI SPAULDING-SUMMIT 18/594 RPR HRDW | SACTO | ETL.8060.POLE.WOOD | 2021-06-09 | 2021-06-08 | 2022-09-14 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44883166 | T2 DI SPAULDING-SUMMIT 18/594 RPR HRDW | ICW
LC | 121496112 | 023/180 | EI T2 MIDDLE FRK-GLD HIL 23/180 RPL STRW | SACTO | ETL.5140.POLE.WDPS | 2021-06-09 | 2021-06-08 | 2022-09-27 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31516281 | T3 DI MDDL FRK-GLD HLL 13/108 RPL POLE | 70Y
LC | 121496181 | 009/107 | T2 DI DRUM-SUMMIT #1 009/107 RPL INSW | SACTO | ETL.1440.INSL | 2021-06-09 | 2021-06-08 | 2022-06-21 | 2022-06-08 | 2022-06-08 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543338 | T2 DI DRUM-SUMMIT #1 009/107 RPL INSW | 93I
LC | 121496200 | 026/309 | T2 DI DRUM-SUMMIT #1 26/309 RPLC INSS | SACTO | ETL.1440.INSL.NCER | 2021-06-09 | 2021-06-08 | 2021-08-26 | 2022-06-08 | 2022-06-08 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31543805 | T2 DI DRUM-SUMMIT #1 26/309 RPLC INSS | 93K
LC | 121496269 | 109/008 | T2 DI HUMBOLDT-BRIDGVILLE 109/8 COMPLETE | EUREKA | ETL.1810.INSL.CERA | 2021-06-09 | 2021-06-08 | 2022-05-26 | 2022-06-08 | 2022-06-08 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31511685 | HUMBOLDT-BRIDGEVILLE RPL INSL & REFRM PO | 93Z
LC | 121496301 | 012/413 | T2 DI SPAULDING-SUMMIT 12/413 RPL INSW | SACTO | ETL.8060.INSL.CERA | 2021-06-09 | 2021-06-08 | 2022-09-20 | 2022-06-08 | 2022-06-08 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545057 | T2 DI SPAULDING-SUMMIT 12/413 RPL INSW | 93I
LC | 121496459 | 017/009 | T2 EI CLEAR LAKE-KONOCTI 17/9 RPL POLE | LAKEVLLE | ETL.6852.POLE.WOOD | 2021-06-09 | 2021-06-09 | 2022-02-02 | 2022-06-09 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31588004 | T2 EI CLEAR LAKE-KONOCTI 17/9 RPL POLE | 70Y
LC | 121496472 | 034/248 | T2 DI CARIBOU-TABLE MTN 34/248 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-09 | 2021-06-08 | 2022-06-18 | 2022-06-08 | 2022-06-08 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121496512 | 018/001 | T2 EI CLEAR LAKE-KONOCTI 18/1 RPL POLE | LAKEVLLE | ETL.6852.POLE.WOOD | 2021-06-09 | 2021-06-09 | 2022-02-01 | 2022-06-09 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31588004 | T2 EI CLEAR LAKE-KONOCTI 17/9 RPL POLE | 70Y
LC | 121496556 | 018/003 | T2 EI CLEAR LAKE-KONOCTI 18/003 RMV DBRS | LAKEVLLE | ETL.6852.POLE.WOOD | 2021-06-09 | 2021-06-09 | 2022-02-01 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45138169 | T2 EI CLEAR LAKE-KONOCTI 18/003 RMV DBRS | ICW
LC | 121496578 | 011/055 | T2 DI FULTON-PUEBLO 11/55 RPLC HRDT | LAKEVLLE | ETL.1600.TOWR | 2021-06-09 | 2021-06-01 | 2022-03-15 | 2022-06-01 | 2022-06-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45142246 | T2 DI FULTON-PUEBLO 11/55 RPLC HRDT | ICQ
LC | 121496593 | 011/055 | T2 DI FULTON-PUEBLO 11/55 RPLC INSS | LAKEVLLE | ETL.1600.INSL.NCER | 2021-06-09 | 2021-06-01 | 2022-02-28 | 2022-06-01 | 2022-06-01 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 121496595 | 011/055 | T2 DI SILVERADO-FLTN JCT 11/55 RPLC INSS | LAKEVLLE | ETL.1610.INSL.NCER | 2021-06-09 | 2021-06-01 | 2022-03-15 | 2022-06-01 | 2022-06-01 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536106 | T2 DI SLVRD-FLTN JCT RPL INSS 6TWRS | 93K
LC | 121496648 | 066/586 | T2 DI COTTONWOOD-GLENN 66/586 RPL INSS | TABLEMTN | ETL.4560.INSL | 2021-06-09 | 2021-06-08 | 2022-03-30 | 2022-06-08 | 2022-06-08 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534508 | DI COTTONWOOD-GLENN RPLC INSS 7TWRS | 93K
LC | 121497008 | 033/240 | T2 DI CRBU-TBL MTN 033/240 RPR STRT | TABLEMTN | ETL.4440.TOWR | 2021-06-09 | 2021-06-08 | 2022-07-15 | 2022-06-08 | 2022-06-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45108132 | T2 DI CRBU-TBL MTN 033/240 RPR STRT | ICQ
LC | 121497235 | 008/097 | T2 DI DRUM-SUMMIT #1 008/097L RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-09 | 2021-06-08 | 2022-08-26 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544924 | T3 EI DRUM-SUMMIT #1 000/007 RPL STRW | 70Y
LC | 121497263 | 008/097 | T2 DI DRUM-SUMMIT #1 008/097R RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-09 | 2021-06-08 | 2022-08-26 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544924 | T3 EI DRUM-SUMMIT #1 000/007 RPL STRW | 70Y
LC | 121497276 | 090/457 | T2 DI MALIN-ROUND MTN #2 90/457 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-09 | 2021-06-02 | 2022-07-11 | 2022-06-02 | 2022-06-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215243 | T2 DI MALIN-ROUND MTN #2 90/457 RPR SHLS | ICS
LC | 121497328 | 000/014 | T2 WV COLGATE-SMRTVLLE #2 0/14 RPR SPLW | SACTO | ETL.6520.INSL.NCER | 2021-06-09 | 2021-06-09 | 2022-07-18 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45233073 | T2 WV COLGATE-SMRTVLLE #2 0/14 RPR SPLW | ICW
LC | 121497467 | 001/073 | T2 DI SPAULDING-SUMMIT 1/73 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-06-09 | 2021-06-08 | 2022-08-06 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45219541 | T2 DI SPAULDING-SUMMIT 1/73 RPR GYWW | ICW
LC | 121497595 | 008/075 | T2 DI CRAG VIEW-CASCADE 8/75L RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-09 | 2021-06-08 | 2022-08-31 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121497596 | 008/075 | T2 DI CRAG VIEW-CASCADE 8/75R RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-09 | 2021-06-08 | 2022-08-31 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121497597 | 013/127 | T2 DI BRIDGEVILLE-CTTNWD 13/127 RPL INSW | TABLEMTN | ETL.1110.INSL.CERA | 2021-06-09 | 2021-06-09 | 2022-06-29 | 2022-06-09 | 2022-06-09 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543328 | T2 DI BRIDGEVILLE-CTTNWD 13/127 RPL INSW | 93I
LC | 121497832 | 081/004 | T2 DI HUMBOLDT-TRINITY 81/4 RPR JUMS | EUREKA | ETL.1820.INSL | 2021-06-09 | 2021-06-08 | 2022-03-26 | 2022-06-08 | 2022-06-08 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Jumper-Steel | Repair | 44888304 | T2 DI HUMBOLDT-TRINITY 81/4 RPR JUMS | ICS
LC | 121497898 | 009/156 | T2 DI TEJON-LEBEC 9/156 INS HRDS | MIDWAY | ETL.9250.POLE.NWOD | 2021-06-09 | 2021-06-08 | 2021-08-07 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Wood | Install | 44930599 | T2 DI TEJON-LEBEC 9/156 INS HRDS | ICW
LC | 121498082 | 018/006 | T2 EI CLEAR LAKE-KONOCTI 18/6 REGRADE | WILLITS | ETL.6852.POLE.NWOD | 2021-06-09 | 2021-06-09 | 2022-02-07 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45138101 | T2 EI CLEAR LAKE-KONOCTI 18/6 REGRADE | ICW
LC | 121498228 | 011/005 | T2 DI TRINITY-MAPLE CREEK 11/5 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2021-06-09 | 2021-06-02 | 2022-11-30 | 2022-06-02 | 2022-06-02 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45158744 | T2 DI TRNTY-MPLE CRK 11/5 RPR GYWW | ICW
LC | 121498485 | 015/067 | T2 EI SN LS OBSPO-OCNO 15/67 RMV VEG | PISMOBCH | ETL.3530.POLE.WDPS | 2021-06-09 | 2021-06-09 | 2022-05-10 | 2022-06-09 | 2022-06-09 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 121498554 | 059/536 | T2 DI PIT #1-CTTNWD 59/536 INS HRDT | TABLEMTN | ETL.5390.TOWR | 2021-06-09 | 2021-06-02 | 2022-02-15 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45149571 | T2 DI PIT #1-CTTNWD 59/536 INS HRDT | ICQ
LC | 121498559 | 055/495 | T2 DI PIT #1-CTTNWD 55/495 RMV VEG | TABLEMTN | ETL.5390.TOWR | 2021-06-09 | 2021-06-02 | 2022-08-30 | 2022-06-02 | 2022-06-02 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121498792 | 055/495 | T2 DI PIT #1-CTTNWD 55/495 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-06-09 | 2021-06-02 | 2022-02-22 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45195761 | T2 DI PIT #1-CTTNWD 55/495 RPR STRT | ICQ
LC | 121498796 | :005/045 | T2 DI PIT #3-PIT #1 :005/045 RPR FOND | TABLEMTN | ETL.5400.TOWR | 2021-06-09 | 2021-06-02 | 2022-07-27 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45198319 | T2 DI PIT #3-PIT #1 :005/045 RPR FOND | ICQ
LC | 121498798 | 004/030 | T2 DI WISHON-COPPERMINE 4/30 RPR FOND | FRESNO | ETL.9330.TOWR | 2021-06-09 | 2021-06-03 | 2022-02-23 | 2022-06-03 | 2022-06-03 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45070067 | T2 DI WISHON-COPPERMINE 4/30 RPR FOND | ICQ
LC | 121498837 | 025/222 | T2 DI RND MTN-CTNWD #2 25/222 RPL HDWT | TABLEMTN | ETL.5640.TOWR | 2021-06-09 | 2021-06-02 | 2022-02-07 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45109973 | T2 DI RND MTN-CTNWD #2 25/222 RPL HDWT | ICQ
LC | 121498909 | 016/161 | T2 DI RND MTN-COTTONWD 3 16/161 RPL HRDT | TABLEMTN | ETL.5640.TOWR | 2021-06-09 | 2021-06-02 | 2022-07-23 | 2022-06-02 | 2022-06-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45215285 | T2 DI RND MTN-COTTONWD 3 16/161 RPL HRDT | ICS
LC | 121499033 | 006/049 | T2 DI ISHON-COPPERMINE 6/49 RPR FOND | FRESNO | ETL.9330.TOWR | 2021-06-09 | 2021-06-02 | 2022-04-30 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45070421 | T2 DI ISHON-COPPERMINE 6/49 RPR FOND | ICQ
LC | 121499510 | 012/059 | T2 DI MOSS LDNG-MTCLF 12/59 RPR FOND | MOSSLNDG | ETL.6050.TOWR | 2021-06-09 | 2021-06-02 | 2022-03-16 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149015 | T2 DI MOSS LDNG-MTCLF 12/59 RPR FOND | ICQ
LC | 121499586 | :006/048 | T2 DI ROCK CREEK-POE :006/048 RPL HRDT | TABLEMTN | ETL.5630.TOWR | 2021-06-09 | 2021-06-02 | 2022-07-06 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45159480 | T2 DI ROCK CREEK-POE :006/048 RPL HRDT | ICQ
LC | 121499609 | 010/077 | T2 DI CARIBOU-TABLE MTN 10/77 RPR STRT | TABLEMTN | ETL.4440.TOWR | 2021-06-09 | 2021-06-01 | 2022-07-07 | 2022-06-01 | 2022-06-01 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45158376 | T2 DI CARIBOU-TABLE MTN 10/77 RPR STRT | ICQ
LC | 121499710 | 047/414 | T2 DI RND MNTN-COTNWD #2 47/414 RMV VEG | TABLEMTN | ETL.5650.TOWR | 2021-06-09 | 2021-06-02 | 2022-08-04 | 2022-06-02 | 2022-06-02 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121499719 | 047/414 | T2 DI RND MNTN-COTNWD #2 47/414 RPL HRDT | TABLEMTN | ETL.5650.TOWR | 2021-06-09 | 2021-06-02 | 2022-02-24 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45110990 | T2 DI RND MNTN-COTNWD #2 47/414 RPL HRDT | ICQ
LC | 121499737 | 013/004 | T2 DI FULTON-HOPLAND 13/4 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-06-09 | 2021-06-02 | 2022-08-24 | 2022-06-02 | 2022-06-02 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143921 | T2 DI FULTON-HOPLAND 13/4 RPR STRW | ICW
LC | 121499748 | 019/006 | T2 EI CLEAR LAKE-KONOCTI 19/6 RPL POLE | WILLITS | ETL.6852.POLE.WOOD | 2021-06-09 | 2021-06-09 | 2022-02-02 | 2022-06-09 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541658 | EI CLEAR LAKE-KONOCTI 14/10 RPL STRW | 70Y
LC | 121499756 | 005/039 | T2 DI WISHON-COPPERMINE 5/39 RPR FOND | FRESNO | ETL.9330.TOWR | 2021-06-09 | 2021-06-03 | 2022-02-23 | 2022-06-03 | 2022-06-03 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45070422 | T2 DI WISHON-COPPERMINE 5/39 RPR FOND | ICQ
LC | 121499770 | 019/004 | T2 EI CLEAR LAKE-KONOCTI 19/4 RPL POLE | WILLITS | ETL.6852.POLE.WOOD | 2021-06-09 | 2021-06-09 | 2022-12-08 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31541658 | EI CLEAR LAKE-KONOCTI 14/10 RPL STRW | 70Y
LC | 121499782 | 088/447 | T2 DI MLN RND MTN #2 088/447 INST HRDT | TABLEMTN | ETL.6020.TOWR | 2021-06-09 | 2021-06-03 | 2022-04-19 | 2022-06-03 | 2022-06-03 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45198267 | T2 DI MLN RND MTN #2 088/447 INST HRDT | ICQ
LC | 121499785 | 001/004 | T2 DI MAPLE CREEK-HOOPA 001/004 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2021-06-09 | 2021-06-02 | 2022-08-19 | 2022-06-02 | 2022-06-02 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45158825 | T2 DI MAPLE CREEK-HOOPA 001/004 RPR GYWW | ICW
LC | 121499823 | 019/007 | T2 EI CLEAR LAKE-KONOCTI 19/7 RPL POLE | LAKEVLLE | ETL.6852.POLE.WOOD | 2021-06-09 | 2021-06-09 | 2022-02-02 | 2022-06-09 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31541658 | EI CLEAR LAKE-KONOCTI 14/10 RPL STRW | 70Y
LC | 121499843 | :009/070 | T2 DI ROCK CREEK-POE-TWR 9/70 RPR STRT | TABLEMTN | ETL.5630.TOWR | 2021-06-09 | 2021-06-02 | 2022-07-20 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45159485 | T2 DI ROCK CREEK-POE-TWR 9/70 RPR STRT | ICQ
LC | 121499844 | 027/240 | T2 DI RND MTN-COTTONWD 2 27/240 INS HRDT | TABLEMTN | ETL.5640.TOWR | 2021-06-09 | 2021-06-02 | 2022-02-08 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45109978 | T2 DI RND MTN-COTTONWD 2 27/240 INS HRDT | ICQ
LC | 121499848 | 047/412 | T2 DI RND MTN-COTTONWD 3 47/412 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-09 | 2021-06-02 | 2022-08-02 | 2022-06-02 | 2022-06-02 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548264 | T2 DI ROUD-MTN CTNWD #3 RPL INSS 8TWRS | 93K
LC | 121499849 | 047/412 | T2 DI RND MTN-COTTONWD 3 47/412 INS HRDT | TABLEMTN | ETL.5650.TOWR | 2021-06-09 | 2021-06-02 | 2022-01-26 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45110646 | T2 DI RND MTN-COTTONWD 3 47/412 INS HRDT | ICQ
LC | 121499934 | 008/069 | T2 DI PIT #1-COTTONWOOD 8/69 UNBURY | TABLEMTN | ETL.5390.TOWR | 2021-06-09 | 2021-06-02 | 2022-02-17 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45149338 | T2 DI PIT #1-COTTONWOOD 8/69 UNBURY | ICQ
LC | 121499998 | 006/051 | T2 DI PIT #3-PIT #1 6/51 RPR INSS | TABLEMTN | ETL.5400.INSL | 2021-06-09 | 2021-06-02 | 2022-06-24 | 2022-06-02 | 2022-06-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213902 | T2 DI PIT #3-PIT #1 6/51 RPR INSS | ICS
LC | 121500049 | 026/231 | T2 DI RND MTN-CTNWD #2 26/231 RPL INSS | TABLEMTN | ETL.5640.INSL | 2021-06-09 | 2021-06-02 | 2022-07-30 | 2022-06-02 | 2022-06-02 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535739 | T2 EI RND MTN-CTNWD RPL INSS 11TWRS | 93K
LC | 121500063 | 046/401 | T2 DI ROUND MTN-CTWD 46/401 RPR INSS CPT | TABLEMTN | ETL.5650.INSL | 2021-06-09 | 2021-06-02 | 2022-08-01 | 2022-06-02 | 2022-06-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45147293 | T2 DI ROUND MTN-COTTONWD 46/104 RPR INSS | ICS
LC | 121500091 | :005/035 | T2 DI ROCK CREEK-POE :005/035 RPR FOND | TABLEMTN | ETL.5630.TOWR | 2021-06-09 | 2021-06-02 | 2022-07-06 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195461 | T2 DI ROCK CREEK-POE :005/035 RPR FOND | ICQ
LC | 121500095 | 059/536 | T2 DI RND MTN CTTNWD #3 059/536 RPR INSS | TABLEMTN | ETL.5650.INSL | 2021-06-09 | 2021-06-02 | 2022-08-05 | 2022-06-02 | 2022-06-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair | 45147294 | T2 DI RND MTN CTTNWD #3 059/536 RPR INSS | ICS
LC | 121500118 | 031/131 | T2 DI TESLA-METCALF 31/131 RPR GYWS | METCALF | ETL.6110.TOWR | 2021-06-09 | 2021-06-01 | 2022-06-29 | 2022-06-01 | 2022-06-01 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45233299 | T2 DI TESLA-METCALF 31/131 RPR GYWS | ICS
LC | 121500197 | 086/437 | T2 DI MLIN-RND MNTN #2 86/437 RPR FOND | TABLEMTN | ETL.6020.TOWR | 2021-06-09 | 2021-06-02 | 2022-07-14 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45198262 | T2 DI MLIN-RND MNTN #2 86/437 RPR FOND | ICQ
LC | 121500208 | 015/155 | T2 DI RND MTN-CTTNWD #2 15/155 RPR OPGW | TABLEMTN | ETL.5640.TOWR | 2021-06-09 | 2021-06-02 | 2022-07-23 | 2022-06-02 | 2022-06-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215282 | T2 DI RND MTN-CTTNWD #2 15/155 RPR OPGW | ICS
LC | 121500211 | 046/396 | T2 DI RND MTN-CTNWD #3 46/396 RPL HRDT | TABLEMTN | ETL.5650.TOWR | 2021-06-09 | 2021-06-02 | 2022-01-18 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45110552 | T2 DI RND MTN-CTNWD #3 46/396 RPL HRDT | ICQ
LC | 121500236 | :005/048 | T2 DI PIT #3-PIT #1 :005/048 RPR INSS | TABLEMTN | ETL.5400.INSL.NCER | 2021-06-09 | 2021-06-02 | 2022-06-24 | 2022-06-02 | 2022-06-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213901 | T2 DI PIT #3-PIT #1 :005/048 RPR INSS | ICS
LC | 121500239 | 013/062 | T2 DI MOSS LANDING-METCALF 13/62 RPL HRD | MOSSLNDG | ETL.6050.TOWR | 2021-06-09 | 2021-06-03 | 2022-03-16 | 2022-06-03 | 2022-06-03 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45149016 | T2 DI MOSS LANDING-METCALF 13/62 RPL HRD | ICQ
LC | 121500245 | 007/058 | T2 DI PIT #3-PIT #1 X7/58 RPL HRDT | TABLEMTN | ETL.5400.TOWR | 2021-06-09 | 2021-06-02 | 2022-07-28 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45198322 | T2 DI PIT #3-PIT #1 X7/58 RPL HRDT | ICQ
LC | 121500247 | 025/221 | T2 DI RND MTN-CTNWD #2 25/221 RPL HDWT | TABLEMTN | ETL.5640.TOWR | 2021-06-09 | 2021-06-02 | 2022-02-07 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45109972 | T2 DI RND MTN-CTNWD #2 25/221 RPL HDWT | ICQ
LC | 121500270 | 000/004 | T2 DI SBNT GZLY CLT #2 0/4 RPL INSS | CONCORD | ETL.3750.SWIT | 2021-06-09 | 2021-06-03 | 2022-07-19 | 2022-06-03 | 2022-06-03 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546696 | T2 DI SBNT GZLY CLT #2 RPL INSS 2TWRS | 93K
LC | 121500278 | PF/3 | T2 DI PINE FLAT PH TAP PF/3 RPL HRDT | FRESNO | ETL.4821.TOWR | 2021-06-09 | 2021-06-03 | 2022-02-22 | 2022-06-03 | 2022-06-03 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45070423 | T2 DI PINE FLAT PH TAP PF/3 RPL HRDT | ICQ
LC | 121500279 | 046/398 | T2 DI PIT #1-COTTONWOOD 46/398 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-06-09 | 2021-06-02 | 2022-02-25 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45149567 | T2 DI PIT #1-COTTONWOOD 46/398 RPR STRT | ICQ
LC | 121500401 | 008/070 | T2 DI PIT #3-PIT #1 008/070 RPR CONS | TABLEMTN | ETL.5400.INSL.CERA | 2021-06-09 | 2021-06-02 | 2022-06-24 | 2022-06-02 | 2022-06-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45213900 | T2 DI PIT #3-PIT #1 008/070 RPR CONS | ICS
LC | 121500453 | 025/224 | T2 DI ROUND MOUNTAIN 25/224 HRDT INST | TABLEMTN | ETL.5640.TOWR | 2021-06-09 | 2021-06-02 | 2022-02-08 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45109974 | T2 DI ROUND MOUNTAIN 25/224 HRDT INST | ICQ
LC | 121500455 | 025/299 | T2 DI DRUM-SUMMIT #2 25/299 RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2021-06-09 | 2021-06-04 | 2022-10-02 | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121500480 | 025/301 | T2 DI DRUM-SUMMIT #2 25/301 RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2021-06-09 | 2021-06-04 | 2022-10-13 | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121500481 | 025/301 | T2 DI DRUM-SUMMIT #2 25/301 RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2021-06-09 | 2021-06-04 | 2022-10-13 | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121500495 | 003/029 | T2 DI WSHN CPPRMN 003/029 RPR STRT | FRESNO | ETL.9330.TOWR | 2021-06-09 | 2021-06-01 | 2022-02-24 | 2022-06-01 | 2022-06-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45070424 | T2 DI WSHN CPPRMN 003/029 RPR STRT | ICQ
LC | 121500611 | 025/182 | T2 DI TRINITY-CTTNWD 25/182 RPL INSS | TABLEMTN | ETL.4040.INSL.CERA | 2021-06-09 | 2021-06-04 | 2022-08-23 | 2022-06-04 | 2022-06-04 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543578 | T2 DI TRINITY-CTTNWD 25/182 RPL INSS | 93I
LC | 121510358 | 090/007 | T2 DI HUMBOLDT-TRINITY 90/7 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-06-10 | 2021-06-09 | 2022-10-10 | 2022-06-09 | 2022-06-09 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543569 | T2 DI HUMBOLDT-TRINITY 90/7 RPL INSW | 93I
LC | 121510756 | 014/118 | T2 DI CRAG VIEW-CASCADE 14/118 RPR OPGW | TABLEMTN | ETL.1350.POLE.STPS | 2021-06-10 | 2021-06-09 | 2022-09-16 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45500229 | T2 DI CRAG VIEW-CASCADE 14/118 RPR OPGW | ICW
LC | 121510798 | 008/095 | T2 DI DRUM-SUMMIT #1 8/95R RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2021-06-10 | 2021-06-08 | 2022-06-28 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544924 | T3 EI DRUM-SUMMIT #1 000/007 RPL STRW | 70Y
LC | 121510871 | 008/095 | T2 DI DRUM-SUMMIT #1 8/95L RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2021-06-10 | 2021-06-08 | 2022-06-28 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544924 | T3 EI DRUM-SUMMIT #1 000/007 RPL STRW | 70Y
LC | 121510994 | 015/128 | T2 DI CRAG VIEW-CASCADE 15/128 RPL INSW | TABLEMTN | ETL.1350.INSL.CERA | 2021-06-10 | 2021-06-09 | 2022-09-12 | 2022-06-09 | 2022-06-09 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543332 | T2 DI CRAG VIEW-CASCADE 15/128 RPL INSW | 93I
LC | 121511340 | 037/179 | T2 DI LAKEVILLE-IGNACIO #2 37/179 INS HR | LAKEVLLE | ETL.3745.TOWR | 2021-06-10 | 2021-06-08 | 2022-08-02 | 2022-06-08 | 2022-06-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45142403 | T2 DI LAKEVILLE-IGNACIO #2 37/179 INS HR | ICQ
LC | 121511342 | 037/179 | T2 DI FULTON-IGNACIO #1 37/179 RPL INSS | LAKEVLLE | ETL.4680.INSL.CERA | 2021-06-10 | 2021-06-08 | 2022-09-14 | 2022-06-08 | 2022-06-08 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31544563 | T3 DI FULTON-IGNACIO #1 2TWRS | 93K
LC | 121511425 | 024/297 | T2 EI DRUM-SUMMIT#2 24/297 RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-10 | 2021-06-10 | 2022-10-03 | 2022-06-10 | 2022-06-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121512325 | 018/155 | T2 DI CRAG VIEW-CASCADE 18/155 RPL POLE | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-10 | 2021-06-09 | 2022-09-13 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31552992 | T2 EI CRAG VIEW-CASCDE 18/154R RPL STRW | 70Y
LC | 121512326 | 018/155 | T2 DI CRAG VIEW-CASCADE 18/155 RPL POLE | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-10 | 2021-06-09 | 2022-09-13 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31552992 | T2 EI CRAG VIEW-CASCDE 18/154R RPL STRW | 70Y
LC | 121512555 | 005/121 | T2 DI HMLTN BRNCH-CHSTR 5/121 RPR GYWW | TABLEMTN | ETL.7000.POLE.WDPS | 2021-06-10 | 2021-06-09 | 2022-07-27 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213371 | T2 DI HMLTN BRNCH-CHSTR 5/121 RPR GYWW | ICW
LC | 121512556 | 005/121 | T2 DI HMLTN BRNCH-CHSTR 5/121 RPR GYWW | TABLEMTN | ETL.7000.POLE.WDPS | 2021-06-10 | 2021-06-09 | 2022-07-27 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213372 | T2 DI HMLTN BRNCH-CHSTR 5/121 RPR GYWW | ICW
LC | 121512576 | 090/006 | T2 DI HUMBOLDT-TRINITY 90/6 RPL INSW | EUREKA | ETL.1820.INSL.NCER | 2021-06-10 | 2021-06-09 | 2022-10-10 | 2022-06-09 | 2022-06-09 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543568 | T2 DI HUMBOLDT-TRINITY 90/6 RPL INSW | 93I
LC | 121512943 | 020/005 | T2 EI CLR LAKE-KONOCTI 020/005 RPR STRW | LAKEVLLE | ETL.6852.POLE.NWOD | 2021-06-10 | 2021-06-10 | 2022-02-03 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45138105 | T2 EI CLR LAKE-KONOCTI 020/005 RPR STRW | ICW
LC | 121513097 | 003/027 | T2 DI WISHON-CPPRMINE 3/27 RPR FOND | FRESNO | ETL.9330.TOWR | 2021-06-10 | 2021-06-03 | 2022-02-23 | 2022-06-03 | 2022-06-03 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45070425 | T2 DI WISHON-CPPRMINE 3/27 RPR FOND | ICQ
LC | 121513143 | 015/073 | EI T2 FULTON-PUEBLO 015/073 RPL HRDT | LAKEVLLE | ETL.1600.TOWR | 2021-06-10 | 2021-06-10 | 2022-06-14 | 2022-06-10 | 2022-06-10 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45142256 | EI T2 FULTON-PUEBLO 015/073 RPL HRDT | ICQ
LC | 121513429 | 027/327 | T2 EI DRUM-SUMMIT#2 027/327 RMV VEG | SACTO | ETL.1450.POLE.WDPS | 2021-06-10 | 2021-06-10 | 2021-12-07 | 2022-06-10 | 2022-06-10 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 121513666 | 009/075 | T2 EI ATASCADERO-CAYUCOS 9/75 RPR JMPW | PISMOBCH | ETL.8480.INSL.NCER | 2021-06-10 | 2021-06-10 | 2022-05-09 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Jumper-Wood | Repair | 45068299 | T2 EI ATASCADERO-CAYUCOS 9/75 RPR JMPW | ICW
LC | 121513841 | 027/328 | T2 EI DRUM-SUMMIT#2 027/328 RMV VEG | SACTO | ETL.1450.POLE.WDPS | 2021-06-10 | 2021-06-10 | 2021-12-07 | 2022-06-10 | 2022-06-10 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 121513861 | 004/079 | T2 DI CNTRVL-TBL MTN 4/79 RPR GYWW | TABLEMTN | ETL.6320.POLE.NWOD | 2021-06-10 | 2021-06-10 | 2022-03-02 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45197503 | T2 DI CNTRVL-TBL MTN 4/79 RPR GYWW | ICW
LC | 121513862 | 004/079 | T2 DI CNTRVL-TBL MTN 4/79 INS HRDW | TABLEMTN | ETL.6320.POLE.NWOD | 2021-06-10 | 2021-06-10 | 2022-03-02 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Wood | Install | 45197502 | T2 DI CNTRVL-TBL MTN 4/79 INS HRDW | ICW
LC | 121513864 | 003/062 | T2 DI SMARTVILLE-NCLS #1 3/62 RPR SPLW | SACTO | ETL.7990.INSL.NCER | 2021-06-10 | 2021-06-09 | 2022-08-20 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45233074 | T2 DI SMARTVILLE-NCLS #1 3/62 RPR SPLW | ICW
LC | 121513881 | 008/043 | T2 EI SILVERADO-FULTON 008/043 RPL INSS | LAKEVLLE | ETL.1610.INSL | 2021-06-10 | 2021-06-10 | 2022-02-23 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548683 | T2 DI SILVERADO-FULTON JCT RPL INSS 6TW | 93K
LC | 121513891 | 008/043 | T2 EI FULTON-PUEBLO 008/043 RPL INSS | LAKEVLLE | ETL.1600.INSL | 2021-06-10 | 2021-06-10 | 2022-03-14 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 121513966 | 093/005 | T2 DI HUMBOLDT-TRINITY 93/5L RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-10 | 2021-06-09 | 2022-06-02 | 2022-06-09 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121513967 | 093/005 | T2 DI HUMBOLDT-TRINITY 93/5R RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-10 | 2021-06-09 | 2022-06-02 | 2022-06-09 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121514016 | 008/042 | T2 EI FULTON-PUEBLO 8/42 RPL SPLS | LAKEVLLE | ETL.1600.INSL | 2021-06-10 | 2021-06-10 | 2022-02-23 | 2022-06-10 | 2022-06-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Replace | 45142242 | T2 EI FULTON-PUEBLO 8/42 RPL SPLS | ICS
LC | 121514017 | 008/042 | T2 EI FULTON-PUEBLO 8/42 RPL INSS | LAKEVLLE | ETL.1600.INSL | 2021-06-10 | 2021-06-10 | 2022-02-23 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 121514018 | 008/042 | T2 EI SILVRADO-FLTON JCT 8/42 RPL INSS | LAKEVLLE | ETL.1610.INSL | 2021-06-10 | 2021-06-10 | 2022-03-13 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548683 | T2 DI SILVERADO-FULTON JCT RPL INSS 6TW | 93K
LC | 121514193 | 001/039 | T2 DI COTTONWOOD-BNTN #1 1/39 COMPLETE | TABLEMTN | ETL.6640.POLE.WOOD | 2021-06-10 | 2021-06-09 | 2022-06-13 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45213525 | T2 DI COTTONWOOD-BNTN #1 1/39 RMV BUTT | ICW
LC | 121514204 | 025/308 | T2 EI DRUM-SUMMIT#2 25/308 RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-10 | 2021-06-10 | 2022-10-14 | 2022-06-10 | 2022-06-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544720 | EI DRUM-SUMMIT#2 26/320 RPL POLE | 70Y
LC | 121514213 | 025/308 | T2 EI DRUM-SUMMIT#2 25/308 RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-10 | 2021-06-10 | 2022-10-14 | 2022-06-10 | 2022-06-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544720 | EI DRUM-SUMMIT#2 26/320 RPL POLE | 70Y
LC | 121514214 | 008/041 | T2 EI SILVERADO-FULTON JCT 8/41 RPL INSS | LAKEVLLE | ETL.1610.INSL | 2021-06-10 | 2021-06-10 | 2022-03-13 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548683 | T2 DI SILVERADO-FULTON JCT RPL INSS 6TW | 93K
LC | 121514221 | 008/041 | T2 EI FULTON-PUEBLO 8/41 RPL INSS | LAKEVLLE | ETL.1600.INSL | 2021-06-10 | 2021-06-10 | 2022-02-23 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549865 | T2 DI FULTON-PUEBLO-INSUL RPL INSS 5TWR | 93K
LC | 121514259 | 004/007 | DI T2 BLLT-RBK-MLS SWST 4/7 RPL STRW | VICTOR | ETL.1070.POLE.WDPS | 2021-06-10 | 2021-06-01 | 2022-04-14 | 2022-06-01 | 2022-06-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543454 | DI T2 BLLT-RBK-MLS SWST 4/7 RPL STRW | 70Y
LC | 121514400 | 004/067 | T2 EI CENTERVILLE-TBLE MTN 4/67 RPL STRW | TABLEMTN | ETL.6320.POLE.WOOD | 2021-06-10 | 2021-06-10 | 2022-04-27 | 2022-06-10 | 2022-06-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31580351 | T2 EI CENTERVILLE-TBLE MTN 4/67 RPL STRW | 70Y
LC | 121514551 | 030/220 | T2 DI CARIBOU-TABLE MTN 30/220 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-10 | 2021-06-10 | 2022-06-18 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121514627 | 059/535 | T2 DI PIT #1 COTTONWOOD 059/535 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-10 | 2021-06-02 | 2022-02-16 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45149570 | T2 DI PIT #1 COTTONWOOD 059/535 RPR FOND | ICQ
LC | 121514651 | 059/535 | T2 DI PIT #1 COTTONWOOD 059/535 RMV DBRS | TABLEMTN | ETL.5390.TOWR | 2021-06-10 | 2021-06-02 | 2022-03-08 | 2022-06-02 | 2022-06-02 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45197201 | T2 DI PIT #1 COTTONWOOD 059/535 RMV DBRS | ICS
LC | 121514707 | 022/105 | T2 DI FULTON-PUEBLO 22/105 RPR INSS | LAKEVLLE | ETL.1600.INSL.CERA | 2021-06-10 | 2021-06-10 | 2022-03-02 | 2022-06-10 | 2022-06-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45142280 | T2 DI FULTON-PUEBLO 22/105 RPR INSS | ICS
LC | 121514734 | 008/040 | T2 EI SILVRADO-FLTON JCT 8/40 RPL SPLS | LAKEVLLE | ETL.1610.INSL | 2021-06-10 | 2021-06-10 | 2022-03-10 | 2022-06-10 | 2022-06-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Steel | Replace | 45142559 | T2 EI SILVRADO-FLTON JCT 8/40 RPL SPLS | ICS
LC | 121514750 | 008/040 | T2 EI FULTON-PUEBLO 8/40 RPL INSS | LAKEVLLE | ETL.1600.INSL | 2021-06-10 | 2021-06-10 | 2022-02-23 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 121514752 | 008/040 | T2 EI SILVRADO-FLTON JCT 8/40 RPL INSS | LAKEVLLE | ETL.1610.INSL | 2021-06-10 | 2021-06-10 | 2022-03-10 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548683 | T2 DI SILVERADO-FULTON JCT RPL INSS 6TW | 93K
LC | 121514756 | 079/403 | T2 DI MALIN-ROUND MTN #2 79/403 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-06-10 | 2021-06-03 | 2022-07-12 | 2022-06-03 | 2022-06-03 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215242 | T2 DI MALIN-ROUND MTN #2 79/403 RPR SHLS | ICS
LC | 121514775 | 008/072 | T2 DI PIT #3-PIT #1 008/072 RPL HRDT | TABLEMTN | ETL.5400.TOWR | 2021-06-10 | 2021-06-02 | 2022-07-26 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45198324 | T2 DI PIT #3-PIT #1 008/072 RPL HRDT | ICQ
LC | 121514815 | 009/111 | T2 EI DRUM-SUMMIT #1 9/111 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-10 | 2021-04-29 | 2022-08-23 | 2022-04-29 | 2022-04-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31543339 | T2 EI DRUM-SUMMIT #1 9/111 RPL STRW | 70Y
LC | 121514817 | 009/111 | T2 EI DRUM-SUMMIT #1 9/111 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-10 | 2021-04-29 | 2022-08-23 | 2022-04-29 | 2022-04-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31543339 | T2 EI DRUM-SUMMIT #1 9/111 RPL STRW | 70Y
LC | 121514875 | 053/479 | T2 DI PIT #1 COTTONWOOD 53/479 RMV STEP | TABLEMTN | ETL.5390.TOWR | 2021-06-10 | 2021-06-02 | 2022-03-04 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45195462 | T2 DI PIT #1 COTTONWOOD 53/479 RMV STEP | ICQ
LC | 121515949 | 018/148 | T2 DI PIT #1-COTTONWOOD 18/148 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-10 | 2021-06-02 | 2022-07-21 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45149409 | T2 DI PIT #1-COTTONWOOD 18/148 RPR FOND | ICQ
LC | 121516017 | 110/000 | T2 DI HUMBOLDT-TRINITY 110/000 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-10 | 2021-06-04 | 2022-03-30 | 2022-06-04 | 2022-06-04 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 121516018 | 110/000 | T2 DI HUMBOLDT-TRINITY 110/000 RPL STRS | EUREKA | ETL.1820.POLE.WDPS | 2021-06-10 | 2021-06-04 | 2022-03-30 | 2022-06-04 | 2022-06-04 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 121516019 | 110/000 | T2 DI HUMBOLDT-TRINITY 110/000 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-10 | 2021-06-04 | 2022-03-30 | 2022-06-04 | 2022-06-04 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 121516043 | 012/059B3 | EI T2 FULTON-PUEBLO 012/059B3 RPR GYWW | LAKEVLLE | ETL.1600.POLE.NWOD | 2021-06-10 | 2021-06-10 | 2022-02-26 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45142250 | EI T2 FULTON-PUEBLO 012/059B3 RPR GYWW | ICW
LC | 121516048 | 004/036 | T2 WV SOBRANTE G #1 4/36 INST DMPRS | CONCORD | ETL.3720.INSL.NCER | 2021-06-10 | 2021-06-10 | 2022-02-04 | 2022-06-10 | 2022-06-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Steel | Install | 45137549 | T2 WV SOBRANTE G #1 4/36 INST DMPRS | ICS
LC | 121516073 | 007/054 | T2 DI MORGA-SN LEANDRO #1 7/54 INS HRDS | CONCORD | ETL.2770.TOWR | 2021-06-10 | 2021-06-02 | 2022-02-10 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45168394 | T2 DI MORGA-SN LEANDRO #1 7/54 INS HRDS | ICQ
LC | 121516083 | 004/036 | T2 WV SOBRANTE G #2 4/36 INST DMPRS | CONCORD | ETL.3730.INSL.NCER | 2021-06-10 | 2021-06-10 | 2022-02-04 | 2022-06-10 | 2022-06-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Steel | Install | 45137552 | T2 WV SOBRANTE G #2 4/36 INST DMPRS | ICS
LC | 121516180 | 027/330 | T2 EI DRUM-SUMMIT#2 027/330 RMV VEG | SACTO | ETL.1450.POLE.WDPS | 2021-06-10 | 2021-06-10 | 2021-08-31 | 2022-06-10 | 2022-06-10 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO | Overgrown | Vegetation | Remove
LC | 121516220 | 022/442 | T2 DI COLGATE-PALERMO 022/442 COMPLETE | SACTO | ETL.6500.POLE.WOOD | 2021-06-10 | 2021-06-09 | 2022-05-02 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45195704 | T2 DI COLGATE-PALERMO 022/442 RPR STRW | ICW
LC | 121516229 | 032/002 | T2 DI GRBRVL-LYTNVL 32/2 RPR STRW | WILLITS | ETL.8365.POLE.WOOD | 2021-06-10 | 2021-06-07 | 2022-04-22 | 2022-06-07 | 2022-06-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44875248 | T2 DI GRBRVL-LYTNVL 32/2 RPR STRW | ICW
LC | 121516290 | 027/114 | T2 DI TESLA-METCALF 027/114 RPR STRT | METCALF | ETL.6110.TOWR | 2021-06-10 | 2021-05-28 | 2022-07-06 | 2022-05-28 | 2022-05-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | Anti-Climbing Guard | Structure-Tower | Repair | 45211598 | T2 DI TESLA-METCALF 027/114 RPR STRT | ICQ
LC | 121516303 | 003/028 | T2 DI WISHON-COPPERMINE 3/28 RPL INSS | FRESNO | ETL.9330.INSL | 2021-06-10 | 2021-06-03 | 2022-04-27 | 2022-06-03 | 2022-06-03 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31544849 | T2 DI WISHON-COPPERMINE RPL INSS 4TWRS | 93K
LC | 121516369 | 030/143 | T2 DI TRACY-LOS BANOS 30/143 RPL INSS | VICTOR | ETL.6130.INSL | 2021-06-10 | 2021-06-05 | 2022-04-10 | 2022-06-05 | 2022-06-05 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31543093 | DI TRACY-LOS BANOS RPL INSS 8TWRS | 93K
LC | 121516370 | 055/275 | T2 DI MLN-RND MNT#2 55/275 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-06-10 | 2021-06-03 | 2022-07-15 | 2022-06-03 | 2022-06-03 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215241 | T2 DI MLN-RND MNT#2 55/275 RPR OPGW | ICS
LC | 121516378 | 002/011 | T2 DI LAYTONVILLE-COVELO 2/11 RPR WDPKR | WILLITS | ETL.7390.POLE.WDPS | 2021-06-10 | 2021-06-04 | 2022-06-10 | 2022-06-04 | 2022-06-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 44999922 | T2 DI LAYTONVILLE-COVELO 2/11 RPR WDPKR | ICW
LC | 121516417 | :004/027 | T2 DI ROCK CREEK-POE 4/27 INST HRDT | TABLEMTN | ETL.5630.TOWR | 2021-06-10 | 2021-06-01 | 2022-07-12 | 2022-06-01 | 2022-06-01 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45159377 | T2 DI ROCK CREEK-POE 4/27 INST HRDT | ICQ
LC | 121516430 | 002/011 | T2 DI LAYTONVILLE-COVELO 2/11 RPR WDPKR | WILLITS | ETL.7390.POLE.WDPS | 2021-06-10 | 2021-06-04 | 2022-06-10 | 2022-06-04 | 2022-06-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 44999929 | T2 DI LAYTONVILLE-COVELO 2/11 RPR WDPKR | ICW
LC | 121516483 | :006/041 | T2 DI ROCK CREEK-POE 6/41 RPR INSS | TABLEMTN | ETL.5630.INSL.CERA | 2021-06-10 | 2021-06-01 | 2022-08-07 | 2022-06-01 | 2022-06-01 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213406 | T2 DI ROCK CREEK-POE 6/41 RPR INSS | ICS
LC | 121516737 | 045/185 | T2 DI MIDWAY-WHIRLWIND 45/185 RPR STRT | MIDWAY | ETL.6030.TOWR | 2021-06-10 | 2021-06-05 | 2021-12-02 | 2022-06-05 | 2022-06-05 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45067992 | T2 DI MIDWAY-WHIRLWIND 45/185 RPR STRT | ICQ
LC | 121516792 | 005/055 | T2 DI SNTH LN PCFCA 005/055 RMV VEG | METCALF | ETL.7575.POLE.WOOD | 2021-06-10 | 2021-06-01 | 2022-07-28 | 2022-06-01 | 2022-06-01 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121516806 | 006/000 | T2 DI LAYTONVILLE-COVELO 6/0 RPR WDPKR | WILLITS | ETL.7390.POLE.WDPS | 2021-06-10 | 2021-06-04 | 2022-06-16 | 2022-06-04 | 2022-06-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45000030 | T2 DI LAYTONVILLE-COVELO 6/0 RPR WDPKR | ICW
LC | 121516845 | 040/320 | T2 DI RND MTN CTTNWD 040/320 RPL INSS | TABLEMTN | ETL.5640.INSL | 2021-06-10 | 2021-06-01 | 2022-07-30 | 2022-06-01 | 2022-06-01 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535739 | T2 EI RND MTN-CTNWD RPL INSS 11TWRS | 93K
LC | 121516888 | 067/596 | T2 DI CTTNWD-DLVN#2 67/596 RPR STRS | TABLEMTN | ETL.4580.TOWR | 2021-06-10 | 2021-06-07 | 2022-05-22 | 2022-06-07 | 2022-06-07 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45212488 | T2 DI CTTNWD-DLVN#2 67/596 RPR STRS | ICS
LC | 121516963 | :002/008 | T2 DI BLTA RVK MLNS SS :002/8 BACKFIL | VICTOR | ETL.1070.POLE.NWOD | 2021-06-10 | 2021-06-05 | 2022-02-16 | 2022-06-05 | 2022-06-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45156970 | T2 DI BLTA RVK MLNS SS :002/8 BACKFIL | ICW
LC | 121518209 | 039/337 | T2 DI PIT#1 COTTNWOOD 39/337 RPL HRDT | TABLEMTN | ETL.5390.TOWR | 2021-06-11 | 2021-06-10 | 2022-03-01 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45149532 | T2 DI PIT#1 COTTNWOOD 39/337 RPL HRDT | ICQ
LC | 121518223 | 045/183 | T2 DI MIDWAY-WHIRLWIND 045/183 RPR SHLS | MIDWAY | ETL.6030.TOWR | 2021-06-11 | 2021-06-08 | 2021-12-17 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44987471 | T2 DI MIDWAY-WHIRLWIND 045/183 RPR SHLS | ICW
LC | 121518225 | 000/010 | T2 DI BCKS CRK-RCK CRK 000/10 RPR STRT | TABLEMTN | ETL.4430.TOWR | 2021-06-11 | 2021-06-08 | 2022-07-12 | 2022-06-08 | 2022-06-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45158369 | T2 DI BCKS CRK-RCK CRK 000/10 RPR STRT | ICQ
LC | 121518256 | 022/008 | T2 EI CPRMNE-TIVY VALLEY 22/8L COMPLETE | FRESNO | ETL.8590.POLE.WDPS | 2021-06-11 | 2021-06-11 | 2022-04-20 | 2022-06-11 | 2022-06-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45093338 | T2 EI CPRMNE-TIVY VALLEY 22/8 RPR GYWW | ICW
LC | 121518263 | 112/009 | T2 DI HMBLDT-BRDGVLL 112/9 RPR CNDW | EUREKA | ETL.1810.INSL.CERA | 2021-06-11 | 2021-06-04 | 2022-04-06 | 2022-06-04 | 2022-06-04 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45155481 | T2 DI HMBLDT-BRDGVLL 112/9 RPR CNDW | ICW
LC | 121518289 | 022/008 | T2 EI CPRMINE-TIVY VALLEY 22/8R COMPLETE | FRESNO | ETL.8590.POLE.WDPS | 2021-06-11 | 2021-06-11 | 2022-04-20 | 2022-06-11 | 2022-06-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45093339 | T2 EI CPRMINE-TIVY VALLEY 22/8 RPR GYWW | ICW
LC | 121518305 | 022/008 | T2 EI CPRMNE-TIVY VALLEY 22/8C COMPLETE | FRESNO | ETL.8590.POLE.WDPS | 2021-06-11 | 2021-06-11 | 2022-04-20 | 2022-06-11 | 2022-06-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45093880 | T2 EI CPRMNE-TIVY VALLEY 22/8 RPR GYWW | ICW
LC | 121518326 | 031/227 | T2 DI CARIBOU-TBL MTN 31/227 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-11 | 2021-06-10 | 2022-06-20 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121518333 | 047/405 | T2 DI RND MTN-CTTNWD X47/405 RPR FOND | TABLEMTN | ETL.5650.TOWR | 2021-06-11 | 2021-06-02 | 2022-01-27 | 2022-06-02 | 2022-06-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45110558 | T2 DI RND MTN-CTTNWD X47/405 RPR FOND | ICQ
LC | 121518581 | 024/112 | T2 DI FULTON-PUEBLO 24/112 RPR JUMP | LAKEVLLE | ETL.1600.INSL.CERA | 2021-06-11 | 2021-06-10 | 2021-08-24 | 2022-06-10 | 2022-06-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Jumper-Steel | Repair | 44858887 | T2 DI FULTON-PUEBLO 24/112 RPR JUMP | ICS
LC | 121518584 | 027/110 | T2 DI DIABLO-MIDWAY #2 27/110 RPR SHLS | PISMOBCH | ETL.5970.TOWR | 2021-06-11 | 2021-06-10 | 2022-02-16 | 2022-06-10 | 2022-06-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45068547 | T2 DI DIABLO-MIDWAY #2 27/110 RPR SHLS | ICS
LC | 121518589 | 005/063 | T2 DI BURNS-LONE STAR #1 5/63 RPL STRW | MOSSLNDG | ETL.6230.POLE.WOOD | 2021-06-11 | 2021-06-10 | 2022-02-10 | 2022-06-10 | 2022-06-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543889 | T2 DI BURNS-LONE STAR #1 5/63 RPL STRW | 70Y
LC | 121518794 | 013/161 | T2 DI WST PT VLY SPRNGS 13/161 RPL DAMW | VICTOR | ETL.8350.INSL.NCER | 2021-06-11 | 2021-06-08 | 2022-05-11 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace | 45156972 | T2 DI WST PT VLY SPRNGS 13/161 RPL DAMW | ICW
LC | 121518832 | 038/193 | T2 DI FULTON-PUEBLO 38/193 RPL INSS | LAKEVLLE | ETL.1600.INSL.NCER | 2021-06-11 | 2021-06-10 | 2022-03-21 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536501 | T3 WV FULTON-PUEBLO 29 TWRS | 93K
LC | 121518848 | 054/489 | T2 DI RND MTN-CTNWD #3 54/489 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-11 | 2021-06-10 | 2022-08-03 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548265 | T2 DI RND MTN-COTNWD #3 RPL INSS 10TWRS | 93K
LC | 121518978 | 024/215 | T2 DI RND MT-CTNWD#2 24/215 RPL INSS CMT | TABLEMTN | ETL.5640.INSL | 2021-06-11 | 2021-06-10 | 2022-07-28 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535739 | T2 EI RND MTN-CTNWD RPL INSS 11TWRS | 93K
LC | 121518988 | 109/000 | T2 DI HUMBLDT-BRIDGEVILLE 109/0 RPR HRDW | EUREKA | ETL.1810.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2022-04-07 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45155396 | T2 DI HUMBLDT-BRIDGEVILLE 109/0 RPR HRDW | ICW
LC | 121519045 | 014/124 | T2 EI COTTONWD-BENTON #2 14/124 RPL INSW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-06-11 | 2021-06-11 | 2022-06-03 | 2022-06-11 | 2022-06-11 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31544357 | T2 EI COTTONWD-BENTON #2 14/124 RPL INSW | 93I
LC | 121519116 | 008/181 | T2 DI HAMLTN BRCH-CHESTR 8/181 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2021-06-11 | 2021-06-08 | 2022-07-28 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544408 | T2 DI HAMLTN BRCH-CHESTR 8/181 RPL POLE | 70Y
LC | 121519120 | 006/042A | T2 DI CTTNWD DLVN #1 6/42A RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-06-11 | 2021-06-08 | 2022-05-21 | 2022-06-08 | 2022-06-08 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45147296 | T2 DI CTTNWD DLVN #1 6/42A RPR SHLS | ICS
LC | 121519145 | 052/469 | T2 DI RND MTN-COTNWD #3 52/469 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-11 | 2021-06-10 | 2022-08-04 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548265 | T2 DI RND MTN-COTNWD #3 RPL INSS 10TWRS | 93K
LC | 121519255 | 114/002 | T2 DI HUMBOLDT-BRIDGEVLLE 114/2 RPL INSW | EUREKA | ETL.1810.INSL.CERA | 2021-06-11 | 2021-06-04 | 2022-09-02 | 2022-06-04 | 2022-06-04 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31544412 | T2 DI HUMBOLDT-BRIDGEVLLE 114/2 RPL INSW | 93I
LC | 121519260 | 029/208 | T2 DI CARIBOU-TABLE MTN 29/208 RPL INSS | TABLEMTN | ETL.4440.INSL | 2021-06-11 | 2021-06-10 | 2022-06-21 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121519269 | 027/194 | T2 DI CARIBOU-TABLE MTN 27/194 RPR INSS | TABLEMTN | ETL.4440.INSL | 2021-06-11 | 2021-06-10 | 2022-06-22 | 2022-06-10 | 2022-06-10 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45212443 | T2 DI CARIBOU-TABLE MTN 27/194 RPR INSS | ICS
LC | 121519287 | 015/200 | T2 EI SALINAS-ANZAR JCT 15/200 RPR GYWW | MOSSLNDG | ETL.8310.POLE.WDPS | 2021-06-11 | 2021-06-11 | 2021-10-21 | 2022-06-11 | 2022-06-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44981672 | T2 EI SALINAS-ANZAR JCT 15/200 RPR GYWW | ICW
LC | 121519293 | 015/200 | T2 EI SALINAS-ANZAR JCT 15/200 RPL INSW | MOSSLNDG | ETL.8310.POLE.WDPS | 2021-06-11 | 2021-06-11 | 2021-10-30 | 2022-06-11 | 2022-06-11 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31544436 | T2 EI SALINAS-ANZAR JCT 15/200 RPL INSW | 93I
LC | 121519331 | 015/200 | T2 EI SALINAS-ANZAR JCT 15/200 RPR GYWW | MOSSLNDG | ETL.8310.POLE.WDPS | 2021-06-11 | 2021-06-11 | 2021-10-21 | 2022-06-11 | 2022-06-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44981673 | T2 EI SALINAS-ANZAR JCT 15/200 RPR GYWW | ICW
LC | 121519488 | 006/068 | T2 IGNACIO-BOLINAS #1 6/68 RPR GYWW | LAKEVLLE | ETL.7140.POLE.NWOD | 2021-06-11 | 2021-06-07 | 2022-01-13 | 2022-06-07 | 2022-06-07 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45128244 | T2 IGNACIO-BOLINAS #1 6/68 RPR GYWW | ICS
LC | 121519517 | 085/002 | T2 DI HUMBLDT- TRNITY 85/2R RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-06-11 | 2021-06-08 | 2022-06-08 | 2022-06-08 | 2022-06-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW WATR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121519611 | B025/577 | T2 DI DRUM-GRS VALY-WMR B25/577 RPR SPLW | SACTO | ETL.6760.INSL.NCER | 2021-06-11 | 2021-06-10 | 2022-04-13 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45174216 | T2 DI DRUM-GRS VALY-WMR B25/577 RPR SPLW | ICW
LC | 121519614 | 011/094 | T2 DI PIT #1-COTTONWOOD 11/94 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-11 | 2021-06-10 | 2022-07-27 | 2022-06-10 | 2022-06-10 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45180999 | T2 DI PIT #1-COTTONWOOD 11/94 RPR FOND | ICQ
LC | 121519752 | 058/526 | T2 DI RND MTN-CTNWD #3 58/526 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-11 | 2021-06-10 | 2022-08-05 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548265 | T2 DI RND MTN-COTNWD #3 RPL INSS 10TWRS | 93K
LC | 121519753 | 034/003 | T2 DI MNDO-WLTS-FRT BRG 34/03 GRND WSH | WILLITS | ETL.7550.INSL.CERA | 2021-06-11 | 2021-06-10 | 2022-05-12 | 2022-06-10 | 2022-06-10 | On-time | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Contaminated | Insulator | Ground Wash | 45193182 | T2 DI MNDO-WLTS-FRT BRG 34/03 GRND WSH | ICD
LC | 121519754 | 037/328 | T2 DI RND MTN-CTTNWD #3 37/328 COMPLETE | TABLEMTN | ETL.5650.TOWR | 2021-06-11 | 2021-06-10 | 2022-05-24 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45110450 | T2 DI RND MTN-CTTNWD #3 37/328 RPR FOND | ICQ
LC | 121519756 | 037/328 | T2 DI RND MTN-CTTNWD #3 37/328 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-11 | 2021-06-10 | 2022-08-04 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547626 | T2 DI RND MTN-CTNWD #3 RPL INSS 9TWRS | 93K
LC | 121519780 | 009/198 | T2 DI HAMLTN BRNCH-CHSTR 9/198 RPR WDPKR | TABLEMTN | ETL.7000.POLE.WOOD | 2021-06-11 | 2021-06-07 | 2022-07-27 | 2022-06-07 | 2022-06-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213373 | T2 DI HAMLTN BRNCH-CHSTR 9/198 RPR WDPKR | ICW
LC | 121519790 | 029/010 | T2 DI MENDO-WILL-FT BRAGG 29/10 RPR HRDW | WILLITS | ETL.7550.POLE.NWOD | 2021-06-11 | 2021-06-07 | 2022-05-16 | 2022-06-07 | 2022-06-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45148579 | T2 DI MENDO-WILL-FT BRAGG 29/10 RPR HRDW | ICW
LC | 121519796 | 093/015 | T2 DI HUMBOLDT-TRINITY 93/15L RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-11 | 2021-06-08 | 2022-03-26 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45260064 | T2 DI HUMBOLDT-TRINITY 93/15L RPR STRW | ICW
LC | 121519854 | 003/092 | T2 DI HAMTON BRNCH-CHESTER 3/92 RPR GYWW | TABLEMTN | ETL.7000.POLE.NWOD | 2021-06-11 | 2021-06-08 | 2022-07-22 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213374 | T2 DI HAMTON BRNCH-CHESTER 3/92 RPR GYWW | ICW
LC | 121519914 | 002/068 | T2 DI HAMTON BRNCH-CHSTR 2/68 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-06-11 | 2021-06-08 | 2022-07-23 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213375 | T2 DI HAMTON BRNCH-CHSTR 2/68 RPR STRW | ICW
LC | 121519930 | 112/003 | T2 DI HUMBLDT-BRIDGEVILLE 112/3 RPL POLE | EUREKA | ETL.1810.POLE.WDPS | 2021-06-11 | 2021-06-08 | 2022-04-08 | 2022-06-08 | 2022-06-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544729 | T2 HUMBOLDT-BRIDGEVILLE 112/3 RPL POLE | 70Y
LC | 121520015 | 019/220 | T2 DI DRUM-SUMMIT #1 19/220L RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-11 | 2021-06-08 | 2022-09-17 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31581111 | T2 DI DRUM-SUMMIT #1 19/220 RPL STRW | 70Y
LC | 121520073 | 055/494 | T2 DI RND MTN-CTNWD #3 55/494 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-11 | 2021-06-10 | 2022-08-03 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548265 | T2 DI RND MTN-COTNWD #3 RPL INSS 10TWRS | 93K
LC | 121520106 | 026/315 | EI T2 DRUM-SUMMIT#2 26/315R RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-11 | 2021-06-11 | 2022-10-18 | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544720 | EI DRUM-SUMMIT#2 26/320 RPL POLE | 70Y
LC | 121520112 | 026/315 | EI T2 DRUM-SUMMIT#2 26/315C RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-11 | 2021-06-11 | 2022-10-18 | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544720 | EI DRUM-SUMMIT#2 26/320 RPL POLE | 70Y
LC | 121520215 | 008/066 | T2 DI TRINTY-COTTNWD 8/66L RPL HRDD | TABLEMTN | ETL.4040.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2022-06-24 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45211998 | T2 DI TRINTY-COTTNWD 8/66L RPL HRDD | ICW
LC | 121520217 | 010/042 | T2 DI EGL RK-FULT-SILV 10/42 RMV NEST | LAKEVLLE | ETL.4392.TOWR | 2021-06-11 | 2021-06-08 | 2022-10-19 | 2022-06-08 | 2022-06-08 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45144221 | T2 DI EGL RK-FULT-SILV 10/42 RMV NEST | ICS
LC | 121520243 | 019/230 | T2 DI DRUM-SUMMIT #2 019/230L RPR POLE | SACTO | ETL.1450.POLE.WDPS | 2021-06-11 | 2021-06-04 | 2022-08-18 | 2022-06-04 | 2022-06-04 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45195711 | T2 DI DRUM-SUMMIT #2 019/230L RPR WDPKR | ICW
LC | 121520245 | 018/591 | T2 DI SPAULDING-SUMMIT 18/591 REFRAME | SACTO | ETL.8060.POLE.WOOD | 2021-06-11 | 2021-06-08 | 2022-09-14 | 2022-06-08 | 2022-06-08 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31545058 | T2 DI SPAULDING-SUMMIT 18/591 REFRAME | 93E
LC | 121520330 | 002/014 | T2 EI DIVIDE-VANDENBERG #2 2/14 RPL INSW | PISMOBCH | ETL.8630.INSL.CERA | 2021-06-11 | 2021-06-11 | 2021-09-07 | 2022-06-11 | 2022-06-11 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543351 | T2 EI DIVIDE-VANDENBERG #2 1/10 RPL INSW | 93I
LC | 121520398 | 039/170 | T2 DI FLTON-LAKEVLLE 39/170 COMPLETE | LAKEVLLE | ETL.4950.TOWR | 2021-06-11 | 2021-06-07 | 2022-06-23 | 2022-06-07 | 2022-06-07 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45144136 | T2 DI FLTON-LAKEVLLE 39/170 RMV NEST | ICS
LC | 121520558 | 025/305 | T2 EI DRUM-SUMMIT #1 25/305 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-11 | 2021-06-11 | 2022-09-15 | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121520571 | 012/157 | T2 DI WP VALLEY SPRNGS 12/157 COMPLETE | VICTOR | ETL.8350.POLE.NWOD | 2021-06-11 | 2021-06-08 | 2022-05-27 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45156973 | T2 DI WP VALLEY SPRNGS 12/157 RPR GYWW | ICW
LC | 121520579 | 011/101 | T2 DI CRAG VIEW-CASCADE 11/101 RPR SHLW | TABLEMTN | ETL.1350.POLE.STPS | 2021-06-11 | 2021-06-09 | 2022-09-15 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45500230 | T2 DI CRAG VIEW-CASCADE 11/101 RPR SHLW | ICW
LC | 121520713 | 026/317 | T2 EI DRUM-SUMMIT#2 26/317C RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-11 | 2021-06-11 | 2022-10-20 | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544720 | EI DRUM-SUMMIT#2 26/320 RPL POLE | 70Y
LC | 121520943 | 021/421 | T2 WV HAT CREEK #1-WSTWD 21/421 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2021-06-11 | 2021-06-11 | 2022-05-05 | 2022-06-11 | 2022-06-11 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542853 | WV T2 HT CREEK #1-WSTWD 020/385 RPL POLE | 70Y
LC | 121520980 | 012/139 | T2 DI DRUM-SUMMIT #1 12/139 RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-11 | 2021-06-08 | 2022-06-27 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45193299 | T2 DI DRUM-SUMMIT #1 12/139 RPR STRW | ICW
LC | 121520988 | 010/122 | T2 DI DRUM-SUMMIT #1 10/122 RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-11 | 2021-06-08 | 2022-08-01 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45195712 | T2 DI DRUM-SUMMIT #1 10/122 RPR STRW | ICW
LC | 121521258 | 030/214 | T2 DI CARIBOU-TBLE MTN 30/214 RPL INSS | TABLEMTN | ETL.4440.INSL | 2021-06-11 | 2021-06-10 | 2022-06-20 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121521265 | 026/320 | T2 EI DRUM-SUMMIT#2 26/320L RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2021-06-11 | 2021-06-11 | 2022-08-17 | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544720 | EI DRUM-SUMMIT#2 26/320 RPL POLE | 70Y
LC | 121521311 | 026/320 | T2 EI DRUM-SUMMIT#2 26/320C RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2021-06-11 | 2021-06-11 | 2022-08-17 | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544720 | EI DRUM-SUMMIT#2 26/320 RPL POLE | 70Y
LC | 121521358 | 026/320 | T2 EI DRUM-SUMMIT#2 26/320R RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2021-06-11 | 2021-06-11 | 2022-08-17 | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544720 | EI DRUM-SUMMIT#2 26/320 RPL POLE | 70Y
LC | 121521514 | 005/067 | T2 EI G.V.-CAMP EVERS 5/67 RPL INSW | MOSSLNDG | ETL.1710.INSL.CERA | 2021-06-11 | 2021-06-11 | 2022-04-26 | 2022-06-11 | 2022-06-11 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537552 | EI GREEN VALLEY-CAMP EVERS 3/46 RPL INSW | 93I
LC | 121521644 | 000/005 | T2 DI HAMLTN BRNCH-CHSTR 00/005 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-06-11 | 2021-06-08 | 2022-07-24 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31539905 | T2 EI HMLTN BRNCH-CHSTR 0/25 RPL STRW | 70Y
LC | 121521717 | 008/061 | T2 DI CRBU-TBLE MNTIN 8/61 INS HRDT | TABLEMTN | ETL.4440.TOWR | 2021-06-11 | 2021-06-08 | 2022-07-18 | 2022-06-08 | 2022-06-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45160935 | T2 DI CRBU-TBLE MNTIN 8/61 INS HRDT | ICQ
LC | 121521774 | 015/127 | T2 EI CRAG VIEW-CASCADE 15/127 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-11 | 2021-06-11 | 2022-11-27 | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121521778 | :001/008 | T2 DI PIT #3-PIT #1 1/8 RPL HRDT | TABLEMTN | ETL.5400.TOWR | 2021-06-11 | 2021-06-10 | 2021-06-26 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44917328 | T2 DI PIT #3-PIT #1 1/8 RPL HRDT | ICQ
LC | 121521980 | 032/006 | T2 DI MEN-WILLTS-FT BRG 32/6 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-11 | 2021-06-10 | 2022-05-16 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148584 | T2 EI MEND-WILL-FT BRAGG 32/6 RPR SPLW | ICW
LC | 121522507 | 000/001 | T2 DI STAN-MEL SS-MAN 0/1 BENT STEEL | VICTOR | ETL.3830.TOWR | 2021-06-11 | 2021-06-11 | 2022-03-03 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45123148 | T2 DI STAN-MEL SS-MAN 0/1 BENT STEEL | ICQ
LC | 121522675 | 010/117 | T2 DI DRUM-SUMMIT #1 10/117 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-11 | 2021-06-08 | 2022-06-13 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543339 | T2 EI DRUM-SUMMIT #1 9/111 RPL STRW | 70Y
LC | 121522725 | 010/117 | T2 DI DRUM-SUMMIT #1 10/117 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-11 | 2021-06-08 | 2022-06-13 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543339 | T2 EI DRUM-SUMMIT #1 9/111 RPL STRW | 70Y
LC | 121522753 | 013/098 | T2 DI CARIBOU TBLE MTN 13/98 RPR STRT | TABLEMTN | ETL.4440.TOWR | 2021-06-11 | 2021-06-08 | 2022-02-14 | 2022-06-08 | 2022-06-08 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45158378 | T2 DI CARIBOU TBLE MTN 13/98 RPR STRT | ICQ
LC | 121522870 | 096/000 | T2 WV HUMBOLDT-TRINITY 96/0 INS DAMP | EUREKA | ETL.1820.INSL.NCER | 2021-06-11 | 2021-06-11 | 2022-03-22 | 2022-06-11 | 2022-06-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 45160747 | T2 EI HUMBOLDT-TRINITY 96/000 RPR CRSW | ICW
LC | 121522895 | 045/394 | T2 DI RND MTN-COTTNWD #3 45/394 RPL HRDT | TABLEMTN | ETL.5650.TOWR | 2021-06-11 | 2021-06-11 | 2022-01-18 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45110549 | T2 DI RND MTN-COTTNWD #3 45/394 RPL HRDT | ICQ
LC | 121522899 | 045/394 | T2 DI RND MTN-COTTNWD #3 45/394 RPR SPLS | TABLEMTN | ETL.5650.INSL | 2021-06-11 | 2021-06-11 | 2022-08-04 | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45147297 | T2 DI RND MTN-COTTNWD #3 45/394 RPR SPLS | ICS
LC | 121523001 | 028/007 | T2 DI MNDCNO WLLTS FT BRG 28/7 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-11 | 2021-06-08 | 2022-08-18 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCL COMP OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148576 | T2NT DI MNDCNO WLTS FT BRG 28/7 RMV DBRS | ICW
LC | 121523003 | 028/007 | T2 DI MNDCN WLTS FT BRG 28/7 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-11 | 2021-06-08 | 2022-08-18 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCL COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45148576 | T2NT DI MNDCNO WLTS FT BRG 28/7 RMV DBRS | ICW
LC | 121523068 | 001/050 | T2 DI SPAULDING-SUMMIT 001/050 RPR GYWW | SACTO | ETL.8060.POLE.NWOD | 2021-06-11 | 2021-06-07 | 2022-08-02 | 2022-06-07 | 2022-06-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45219547 | T2 DI SPAULDING-SUMMIT 001/050 RPR GYWW | ICW
LC | 121523105 | 007/033 | T2 DI PITTSBURG-TESLA #1 7/33 RPR STRT | CONCORD | ETL.5510.TOWR | 2021-06-11 | 2021-06-11 | 2022-04-13 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45190828 | T2 DI PITTSBURG-TESLA #1 7/33 RPR STRT | ICQ
LC | 121523148 | 004/036 | T2 DI VACA-VACAVL-CORDELIA 4/36 RPL INSS | SACTO | ETL.4090.INSL.NCER | 2021-06-11 | 2021-06-11 | 2022-05-11 | 2022-06-11 | 2022-06-11 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31542279 | EI VCA-VCVILE-CORDELIATO RPL INSS 2 TWRS | 93K
LC | 121523149 | 004/036 | T2 DI VACA-VACAVL-JAMESON 4/36 INS STEP | LAKEVLLE | ETL.4100.TOWR | 2021-06-11 | 2021-06-11 | 2022-04-27 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45161084 | T2 DI VACA-VACAVL-JAMESON 4/36 INS STEP | ICQ
LC | 121523167 | 000/005 | T2 DI SMRTSVLL NCLS #2 000/005 RPR GYWW | SACTO | ETL.8000.POLE.WOOD | 2021-06-11 | 2021-06-08 | 2022-04-27 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45233077 | T2 DI SMRTSVLL NCLS #2 000/005 RPR GYWW | ICW
LC | 121523247 | 001/062 | T2 DI SPAULDING-SUMMIT 1/062 RPR GYWW | SACTO | ETL.8060.POLE.NWOD | 2021-06-11 | 2021-06-07 | 2022-08-02 | 2022-06-07 | 2022-06-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45219548 | T2 DI SPAULDING-SUMMIT 1/062 RPR GYWW | ICW
LC | 121523289 | 108/002 | T2 DI HMBLT BRDGVLL 108/2L RPR WDPKR | EUREKA | ETL.1810.POLE.WDPS | 2021-06-11 | 2021-06-08 | 2022-04-06 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45155392 | T2 DI HMBLT BRDGVLL 108/2LRPR WDPKR | ICW
LC | 121523292 | 031/210 | T2 DI POE-RIO OSO 31/210 RPR FOND | TABLEMTN | ETL.5540.TOWR | 2021-06-11 | 2021-06-11 | 2022-02-03 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45145301 | T2 DI POE-RIO OSO 31/210 RPR FOND | ICQ
LC | 121523301 | 004/036 | T2 DI VACA-VACVL-JMSN NRTH 4/36 RPL INSS | LAKEVLLE | ETL.4100.INSL.NCER | 2021-06-11 | 2021-06-11 | 2022-02-24 | 2022-06-11 | 2022-06-11 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549199 | EI VCA-VCVILE-JMESN-NRTH TO RPL INSS 7TW | 93K
LC | 121523309 | 007/059 | T2 DI PIT #3-PIT #1 7/59 RPR SPLS | TABLEMTN | ETL.5400.INSL | 2021-06-11 | 2021-06-11 | 2022-06-18 | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45213899 | T2 DI PIT #3-PIT #1 7/59 RPR SPLS | ICS
LC | 121523350 | 108/002 | T2 DI HMBLT BRDGVLL 108/2C RPR WDPKR | EUREKA | ETL.1810.POLE.WDPS | 2021-06-11 | 2021-06-08 | 2022-04-06 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45155392 | T2 DI HMBLT BRDGVLL 108/2LRPR WDPKR | ICW
LC | 121523356 | 004/115 | T2 DI HMLTN BRNCH CHSTR 004/115 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-06-11 | 2021-06-08 | 2022-07-23 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31540591 | T2 EI HMLTN BRNH-CHTR 4/104 RPL STRW | 70Y
LC | 121523445 | A000/016 | T2 DI COLGATE-CHALLENGE A0/16 RPR STRW | SACTO | ETL.6480.POLE.WOOD | 2021-06-11 | 2021-06-10 | 2022-08-24 | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 44883003 | T2 DI COLGATE-CHALLENGE A0/16 RPR STRW | ICW
LC | 121523461 | 090/001 | T2 DI HUMBOLDT-TRINITY 90/1 RMV VEG | EUREKA | ETL.1820.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2022-06-10 | 2022-06-09 | 2022-06-09 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR | Overgrown | Vegetation | Remove
LC | 121523466 | 010/093 | T2 DI CRG VW-CSCD 010/093 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2022-09-22 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121523469 | 006/049 | T2 DI TRINITY CTTNWD 6/49L RMV BUTT | TABLEMTN | ETL.4040.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2022-06-23 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45195464 | T2 DI TRINITY CTTNWD 6/49L RMV BUTT | ICW
LC | 121523500 | 006/049 | T2 DI TRINITY CTTNWD 6/49L RPR STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2022-06-24 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45212041 | T2 DI TRINITY CTTNWD 6/49L RPR STRW | ICW
LC | 121523502 | 012/104 | T2 DI CRG VW-CSCD 012/104 RMV DEBRIS | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2022-07-07 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45429223 | T2 DI CRG VW-CSCD 012/104 RMV DEBRIS | ICW
LC | 121523503 | 012/104 | T2 DI CRG VW-CSCD 012/104 RPR SHLW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2022-09-16 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45500231 | T2 DI CRG VW-CSCD 012/104 RPR SHLW | ICW
LC | 121523504 | 012/104 | T2 DI CRG VW-CSCD 012/104 RPL INSW | TABLEMTN | ETL.1350.INSL.NCER | 2021-06-11 | 2021-06-09 | 2022-09-16 | 2022-06-09 | 2022-06-09 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31549082 | T2 DI CRG VW-CSCD 012/104 RPL INSW | 93I
LC | 121523509 | 009/192 | T2 DI HMLTN BRNCH CHSTR 9/192 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2021-06-11 | 2021-06-07 | 2022-07-28 | 2022-06-07 | 2022-06-07 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544408 | T2 DI HAMLTN BRCH-CHESTR 8/181 RPL POLE | 70Y
LC | 121523631 | 003/023 | T2 DI TRINITY CTTNWD 3/23R RPR STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2022-06-22 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45212042 | T2 DI TRINITY CTTNWD 3/23R RPR STRW | ICW
LC | 121523632 | 003/023 | T2 DI TRINITY CTTNWD 3/23L RPR STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2022-06-23 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45212043 | T2 DI TRINITY CTTNWD 3/23L RPR STRW | ICW
LC | 121523644 | 071/616 | T2 DI CTTNWD-DELEVAN #2 71/616 RPL INSS | TABLEMTN | ETL.4580.INSL.CERA | 2021-06-11 | 2021-06-10 | 2022-06-06 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540712 | T2 EI CTONWD-DELEVAN #2 RPL INSS 9TWRS | 93K
LC | 121523650 | 024/293 | T2 DI DRUM-SUMMIT #2 24/293 RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2022-10-08 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121523651 | 024/293 | T2 DI DRUM-SUMMIT #2 24/293 RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2022-10-08 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121523799 | 017/140 | T2 DI CRAG VIEW-CASCADE 017/140 RPL STRW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-06-12 | 2021-06-09 | 2022-09-14 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31552992 | T2 EI CRAG VIEW-CASCDE 18/154R RPL STRW | 70Y
LC | 121523814 | 007/085 | T2 DI DRUM-SUMMIT #1 007/085 RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-06-13 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45195716 | T2 DI DRUM-SUMMIT #1 007/085 RPR STRW | ICW
LC | 121523815 | 026/191 | T2 DI CARIBOU TBL MTN 26/191 RPR FOND | TABLEMTN | ETL.4440.TOWR | 2021-06-12 | 2021-06-08 | 2022-07-20 | 2022-06-08 | 2022-06-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160949 | T2 DI CARIBOU TBL MTN 26/191 RPR FOND | ICQ
LC | 121523816 | 014/126 | T2 DI CRAG VIEW-CSAD 014/126 RMV DEBRIS | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2020-06-30 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45428530 | T2 DI CRAG VIEW-CSAD 014/126 RMV DEBRIS | ICW
LC | 121523863 | 094/011 | T2 DI HUMBOLDT-TRINITY 94/11 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-06-12 | 2021-06-09 | 2022-03-26 | 2022-06-09 | 2022-06-09 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31549299 | T2 DI HUMBOLDT-TRINITY 94/11 RPL INSW | 93I
LC | 121523911 | 029/002 | T2 DI MNDCN WLTS FT BRG 29/2 RPR INSW | WILLITS | ETL.7550.INSL.CERA | 2021-06-12 | 2021-06-08 | 2022-08-16 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45148577 | T2 DI MNDCN WLTS FT BRG 29/2 RPR INSW | ICW
LC | 121523915 | 096/007 | T2 DI HUMBOLDT-TRINITY 96/7 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-06-12 | 2021-06-09 | 2022-03-26 | 2022-06-09 | 2022-06-09 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31549299 | T2 DI HUMBOLDT-TRINITY 94/11 RPL INSW | 93I
LC | 121523925 | 011/399 | T2 DI SPAULDING-SUMMIT 011/399 RPR JUMW | SACTO | ETL.8060.POLE.WOOD | 2021-06-12 | 2021-06-08 | 2022-09-19 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Jumper-Wood | Repair | 44883010 | T2 DI SPAULDING-SUMMIT 011/399 RPR JUMW | ICW
LC | 121523944 | 018/592 | T2 DI SPAULDING-SUMMIT 18/592 RPL INSS | SACTO | ETL.8060.INSL.NCER | 2021-06-12 | 2021-06-08 | 2022-09-15 | 2022-06-08 | 2022-06-08 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31543809 | T2 DI SPAULNG-SUMMIT RPL INSS 2TWRS | 93K
LC | 121523946 | 024/288 | T2 DI DRUM-SUMMIT #1 24/288 RPL INSW | SACTO | ETL.1440.INSL | 2021-06-12 | 2021-06-08 | 2022-06-26 | 2022-06-08 | 2022-06-08 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541895 | T2 EI DRUM-SUMMIT #1 20/237 RPL INSW | 93I
LC | 121523980 | 020/541 | T2NT DI CARIBOU #2 020/541 RPL HRDW | TABLEMTN | ETL.6280.POLE.NWOD | 2021-06-12 | 2021-06-08 | 2022-07-14 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2N PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45214076 | T2NT DI CARIBOU #2 020/541 RPL HRDW | ICW
LC | 121523985 | 009/107 | T2 DI DRUM-SUMMIT #2 9/107L RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-07-26 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543771 | T3 DI DRUM-SUMMIT #2 0/5C RPL STRW | 70Y
LC | 121524020 | 005/070 | EI T2 GREN VLLEY-CMP EVRS 5/70 RPL INSW | MOSSLNDG | ETL.1710.INSL.CERA | 2021-06-12 | 2021-06-12 | 2022-04-04 | 2022-06-12 | 2022-06-12 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537552 | EI GREEN VALLEY-CAMP EVERS 3/46 RPL INSW | 93I
LC | 121524060 | 008/040 | T2 DI FULTON-PUEBLO 8/40 RPR SPLS | LAKEVLLE | ETL.1600.INSL | 2021-06-12 | 2021-06-11 | 2022-02-23 | 2022-06-11 | 2022-06-11 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45142241 | T2 DI FULTON-PUEBLO 8/40 RPR SPLS | ICS
LC | 121524071 | 020/003 | T2 DI CLR LAKE-KONOCTI 020/003 RPL STRW | WILLITS | ETL.6852.POLE.WOOD | 2021-06-12 | 2021-06-09 | 2022-02-03 | 2022-06-09 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541658 | EI CLEAR LAKE-KONOCTI 14/10 RPL STRW | 70Y
LC | 121524159 | 049/201 | T2 DI MIDWY-WHRLWND 49/201 RPL INSS | MIDWAY | ETL.6030.INSL | 2021-06-12 | 2021-06-05 | 2022-03-10 | 2022-06-05 | 2022-06-05 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31579248 | T0 DI MIDWAY-WHIRLWIND RPL INSS 2TWRS | 93K
LC | 121524196 | 005/051 | T2 DI PIT #3-PIT #1 05/51 RPR INSS | TABLEMTN | ETL.5400.INSL | 2021-06-12 | 2021-06-02 | 2022-06-24 | 2022-06-02 | 2022-06-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213898 | T2 DI PIT #3-PIT #1 05/51 RPR INSS | ICS
LC | 121524201 | :000/004 | T2 DI ROCK CREEK-POE :00/04 RPR INSS | TABLEMTN | ETL.5630.INSL | 2021-06-12 | 2021-06-02 | 2022-08-07 | 2022-06-02 | 2022-06-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213408 | T2 DI ROCK CREEK-POE :00/04 RPR INSS | ICS
LC | 121524231 | 006/052 | T2 DI PIT #1-COTTONWOOD 6/52 UNBURY | TABLEMTN | ETL.5390.TOWR | 2021-06-12 | 2021-06-02 | 2022-08-01 | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45195629 | T2 DI PIT #1-COTTONWOOD 6/52 UNBURY | ICQ
LC | 121524265 | 004/010 | T2 DI LAYTONVILLE-COVELO 4/10L RPR STRW | LAKEVLLE | ETL.7390.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2021-10-19 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45000020 | T2 DI LAYTONVILLE-COVELO 4/10L RPR STRW | ICW
LC | 121524267 | 004/010 | T2 DI LAYTONVILLE-COVELO 4/10C RPR STRW | LAKEVLLE | ETL.7390.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2021-10-19 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45000021 | T2 DI LAYTONVILLE-COVELO 4/10C RPR STRW | ICW
LC | 121524280 | 007/163 | T2 DI HMLTN BRNCH CHSTR 7/163 RPR WDPKR | TABLEMTN | ETL.7000.POLE.WOOD | 2021-06-12 | 2021-06-08 | 2021-08-19 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44951880 | T2 DI HMLTN BRNCH CHSTR 7/163 RPR WDPKR | ICW
LC | 121524300 | 015/130 | T2 DI CRG VW CSCD 015/130 RMV DEBRIS | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-06-30 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45428521 | T2 DI CRG VW CSCD 015/130 RMV DEBRIS | ICW
LC | 121524303 | 015/130 | T2 DI CRG VW CSCD 015/130 RPR SHLW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-09-19 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45500232 | T2 DI CRG VW CSCD 015/130 RPR SHLW | ICW
LC | 121524375 | 018/153 | T2 DI CRG VW CSCD 18/153 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-09-14 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31552992 | T2 EI CRAG VIEW-CASCDE 18/154R RPL STRW | 70Y
LC | 121524379 | 111/004 | T2 DI HMBLDT-BRDGVLLE 111/4 RPL ADSS | EUREKA | ETL.1810.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-06-17 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Replace | 44958552 | T2 DI HMBLDT-BRDGVLLE 111/4 RPL ADSS | ICW
LC | 121524390 | 111/004 | T2 DI HMBLDT-BRDGVLLE 111/4 RPR GYWW | EUREKA | ETL.1810.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-06-17 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44958552 | T2 DI HMBLDT-BRDGVLLE 111/4 RPL ADSS | ICW
LC | 121524391 | 099/004 | T2 DI HUMBOLDT-TRINITY 99/4R RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-03-25 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45093430 | T2 DI HUMBOLDT-TRINITY 99/4R RPR STRW | ICW
LC | 121524425 | 000/009 | T2 DI CRAG VIEW-CASCADE 000/009 RMV VEG | TABLEMTN | ETL.1350.TOWR | 2021-06-12 | 2021-06-11 | 2022-04-26 | 2022-06-11 | 2022-06-11 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121524433 | 099/004 | T2 DI HUMBOLDT-TRINITY 99/4L RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-03-25 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 44958553 | T2 DI HUMBOLDT-TRINITY 99/4L RPR STRW | ICW
LC | 121524453 | 099/004 | T2 DI HUMBOLDT-TRINITY 99/4L RMV BUTT | EUREKA | ETL.1820.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-03-25 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 44958553 | T2 DI HUMBOLDT-TRINITY 99/4L RPR STRW | ICW
LC | 121524458 | 099/004 | T2 DI HUMBOLDT-TRINITY 99/4 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-06-12 | 2021-06-08 | 2022-03-25 | 2022-06-08 | 2022-06-08 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542131 | T2 DI HUMBOLDT-TRINITY 99/4 RPL INSW | 93I
LC | 121524488 | 010/121 | T2 DI DRUM-SUMMIT #1 10/121L RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-08-20 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45195779 | T2 DI DRUM-SUMMIT #1 10/121L RPR STRW | ICW
LC | 121524525 | 004/058 | EI T2 GREEN VLLEY-CMP EVRS 4/58 RPR GYWW | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-06-12 | 2021-06-12 | 2022-03-02 | 2022-06-12 | 2022-06-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45166702 | EI T2 GREEN VLLEY-CMP EVRS 4/58 RPR GYWW | ICW
LC | 121524545 | 011/102 | T2 DI CRG VW CSCD 011/102 RPR SHLW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-09-15 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45500233 | T2 DI CRG VW CSCD 011/102 RPR SHLW | ICW
LC | 121524551 | 011/102 | T2 DI CRG VW CSCD 011/102 RMV DEBRIS | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-07-07 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45429224 | T2 DI CRG VW CSCD 011/102 RMV DEBRIS | ICW
LC | 121524561 | 003/084 | T2 DI HMLTN BRNCH-CHSTR 3/84 RPR INSW | TABLEMTN | ETL.7000.INSL.CERA | 2021-06-12 | 2021-06-08 | 2022-07-22 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45147446 | T2 DI HMLTN BRNCH-CHSTR 3/84 RPR INSW | ICW
LC | 121524562 | 004/058 | EI T2 GREEN VLLEY-CMP EVRS 4/58 RPR GYWW | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-06-12 | 2021-06-12 | 2022-03-02 | 2022-06-12 | 2022-06-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45166700 | EI T2 GREEN VLLEY-CMP EVRS 4/58 RPR GYWW | ICW
LC | 121524593 | 004/058 | EI T2 GREEN VLLEY-CMP EVRS 4/58 RPL INSW | MOSSLNDG | ETL.1710.INSL.CERA | 2021-06-12 | 2021-06-12 | 2022-04-06 | 2022-06-12 | 2022-06-12 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537552 | EI GREEN VALLEY-CAMP EVERS 3/46 RPL INSW | 93I
LC | 121524594 | 004/058 | EI T2 GREEN VLLEY-CMP EVRS 4/58 RPR GYWW | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-06-12 | 2021-06-12 | 2022-03-02 | 2022-06-12 | 2022-06-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45166707 | EI T2 GREEN VLLEY-CMP EVRS 4/58 RPR GYWW | ICW
LC | 121524613 | 000/007 | T2 EI NARROWS #2 TAP 0/7 RPL STRW | SACTO | ETL.6521.POLE.WDPS | 2021-06-12 | 2021-06-12 | 2022-06-03 | 2022-06-12 | 2022-06-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544417 | T2 EI NARROWS #2 TAP 0/7 RPL STRW | 70Y
LC | 121524614 | 050/206 | T2 DI MIDWAY-WHIRLWIND 50/206 RPL INSS | MIDWAY | ETL.6030.INSL | 2021-06-12 | 2021-06-08 | 2022-03-09 | 2022-06-08 | 2022-06-08 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536505 | MIDWAY-WHIRLWIND RPL INSS 4TWRS | 93K
LC | 121524629 | :001/008 | T2 DI BCKS CRK-RCK CRK :1/8 RPL INSS | TABLEMTN | ETL.4430.INSL | 2021-06-12 | 2021-06-08 | 2022-06-29 | 2022-06-08 | 2022-06-08 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31545126 | T2 DI BCKS CRK-RCK CRK RPL INSS 2TWRS | 93K
LC | 121524661 | 026/312 | T2 EI DRUM-SUMMIT #1 26/312R RPL PL | SACTO | ETL.1440.POLE.WDPS | 2021-06-12 | 2021-06-12 | 2021-08-22 | 2022-06-12 | 2022-06-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544594 | T2 DRUM-SUMMIT #1 26/312R RPL PL | 70Y
LC | 121524670 | 000/007 | T2 EI NARROWS #2 TAP 0/7 RPL STRW | SACTO | ETL.6521.POLE.WDPS | 2021-06-12 | 2021-06-12 | 2022-06-03 | 2022-06-12 | 2022-06-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544417 | T2 EI NARROWS #2 TAP 0/7 RPL STRW | 70Y
LC | 121524716 | 000/007 | T2 EI NARROWS #2 TAP 0/7 RPL STRW CMPLTD | SACTO | ETL.6521.POLE.WDPS | 2021-06-12 | 2021-06-12 | 2022-06-03 | 2022-06-12 | 2022-06-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31544417 | T2 EI NARROWS #2 TAP 0/7 RPL STRW | 70Y
LC | 121524827 | 109/004 | T2 DI HMBLDT-BRDGVLLE 109/4 RPL POLE | EUREKA | ETL.1810.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-04-07 | 2022-06-08 | 2022-06-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544728 | T2 DI HMBLDT-BRDGVLLE 109/4 RPL POLE | 70Y
LC | 121524828 | 109/004 | T2 DI HMBLDT-BRDGVLLE 109/4 RPL POLE | EUREKA | ETL.1810.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-04-07 | 2022-06-08 | 2022-06-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544728 | T2 DI HMBLDT-BRDGVLLE 109/4 RPL POLE | 70Y
LC | 121524845 | 012/095 | T2 DI CARIBOU-TABLE MTN 12/95 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-12 | 2021-06-11 | 2022-06-22 | 2022-06-11 | 2022-06-11 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121524855 | 009/111 | T2 DI DRUM-SUMMIT #2 9/111 INST HRDD | SACTO | ETL.1450.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-08-09 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Missing | Hardware-Wood | Install | 45195844 | T2 DI DRUM-SUMMIT #2 9/111 INST HRDD | ICW
LC | 121524863 | 009/111 | T2 DI DRUM-SUMMIT #2 9/111 RPR WDPKR | SACTO | ETL.1450.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-08-09 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45195985 | T2 DI DRUM-SUMMIT #2 9/111 RPR WDPKR | ICW
LC | 121524864 | 014/124 | T2 DI CRAG VIEW-CASCADE 14/124 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-09-22 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121524887 | 012/126 | EI T2 PIT #5-RND MTN #1 12/126 RPL HRDW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-12 | 2021-06-12 | 2022-07-17 | 2022-06-12 | 2022-06-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 44960689 | EI T2 PIT #5-RND MTN #1 12/126 RPL HRDW | ICW
LC | 121524889 | 024/195 | T2 DI PIT #1-COTTONWOOD 24/195 RPR SPLS | TABLEMTN | ETL.5390.INSL.NCER | 2021-06-12 | 2021-06-10 | 2022-10-10 | 2022-06-10 | 2022-06-10 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45197213 | T2 DI PIT #1-COTTONWOOD 24/195 RPR SPLS | ICS
LC | 121524890 | 014/124 | T2 DI CRAG VIEW-CASCADE 14/124 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-09-22 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121524894 | 014/124 | T2 DI CRAG VIEW-CASCADE 14/124 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-09-22 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121524899 | 067/001 | T2 DI HUMBOLDT-TRINITY 67/1L RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-04-01 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145528 | T2 DI HUMBOLDT-TRINITY 67/1L RPR GYWW | ICW
LC | 121524920 | 024/195 | T2 DI PIT #1-COTTONWOOD 24/195 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-06-12 | 2021-06-10 | 2022-03-08 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45149507 | T2 DI PIT #1-COTTONWOOD 24/195 RPR STRT | ICQ
LC | 121524931 | 067/001 | T2 DI HUMBOLDT-TRINITY 67/1C RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-04-01 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145528 | T2 DI HUMBOLDT-TRINITY 67/1L RPR GYWW | ICW
LC | 121524935 | 067/001 | T2 DI HUMBOLDT-TRINITY 67/1R RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-04-01 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145528 | T2 DI HUMBOLDT-TRINITY 67/1L RPR GYWW | ICW
LC | 121524946 | 027/332 | T2 EI DRUM-SUMMIT #2 27/332 RPL INSS | SACTO | ETL.1450.INSL | 2021-06-12 | 2021-06-12 | 2022-08-11 | 2022-06-12 | 2022-06-12 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31543649 | T2 EI DRUM-SUMMIT #2 27/332 RPL INSS | 93K
LC | 121524952 | 007/091 | T2 DI DRUM-SUMMIT #1 007/091 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-08-25 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544924 | T3 EI DRUM-SUMMIT #1 000/007 RPL STRW | 70Y
LC | 121524979 | 027/318 | T2 EI DRUM-SUMMIT#1 27/318 RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2021-06-12 | 2021-06-12 | 2022-09-23 | 2022-06-12 | 2022-06-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45195986 | T2 EI DRUM-SUMMIT#1 27/318 RPR GYWW | ICW
LC | 121524992 | 090/003 | T2 DI HUMBOLDT-TRINITY 90/3 SPLIT BOLT | EUREKA | ETL.1820.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-10-10 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Wood | Install | 45148698 | T2 DI HUMBOLDT-TRINITY 90/3 SPLIT BOLT | ICW
LC | 121525041 | 019/227 | T2 DI DRUM-SUMMIT #2 19/227L SPLIT BOLT | SACTO | ETL.1450.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-06-10 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Wood | Install | 45195991 | T2 DI DRUM-SUMMIT #2 19/227 SPLIT BOLT | ICW
LC | 121525184 | 001/012 | T2 EI PIT #5-ROUND MTN #1 1/12R RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-12 | 2021-06-12 | 2022-06-22 | 2022-06-12 | 2022-06-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45212835 | T2 EI PIT #5-ROUND MTN #1 1/12 RPR STRW | ICW
LC | 121525211 | 028/201 | T2 DI CARIBOU TBL MTN 28/201 RPL INSS | TABLEMTN | ETL.4440.INSL | 2021-06-12 | 2021-06-12 | 2022-06-22 | 2022-06-12 | 2022-06-12 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121525219 | 016/377 | T2 DI DRUM-GRAS VLY-WEMR 16/377 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-06-12 | 2021-06-09 | 2022-03-25 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45174217 | T2 DI DRUM-GRAS VLY-WEMR 16/377 RPR GYWW | ICW
LC | 121525296 | 063/317 | T2 DI MALIN-ROUND MTN #2 63/317 RPR OPGW | TABLEMTN | ETL.6020.INSL.NCER | 2021-06-12 | 2021-06-11 | 2022-07-14 | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215240 | T2 DI MALIN-ROUND MTN #2 63/317 RPR OPGW | ICS
LC | 121525299 | 063/317 | T2 DI MALIN-ROUND MTN #2 63/317 RPR ANCS | TABLEMTN | ETL.6020.TOWR | 2021-06-12 | 2021-06-11 | 2022-07-20 | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair | 45193989 | T2 DI MALIN-ROUND MTN #2 63/317 RPR ANCS | ICS
LC | 121525302 | 018/589 | T2 DI SPAULDING-SUMMIT 18/589 RPL INSW | SACTO | ETL.8060.INSL.NCER | 2021-06-12 | 2021-06-07 | 2022-09-14 | 2022-06-07 | 2022-06-07 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545057 | T2 DI SPAULDING-SUMMIT 12/413 RPL INSW | 93I
LC | 121525309 | 101/000 | T2 DI HUMBOLDT-TRINITY 101/000L RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-03-29 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45094207 | T2 DI HUMBOLDT-TRINITY 101/000L RPR GYWW | ICW
LC | 121525330 | 101/000 | T2 DI HUMBOLDT-TRINITY 101/000R RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-03-29 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45094341 | T2 DI HUMBOLDT-TRINITY 101/000R RPR GYWW | ICW
LC | 121525331 | 101/000 | T2 DI HUMBOLDT-TRINITY 101/000C RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-03-29 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45094352 | T2 DI HUMBOLDT-TRINITY 101/000C RPR GYWW | ICW
LC | 121525357 | 001/023 | T2 EI NARROWS #1 TAP 1/23 RPR GYWW | SACTO | ETL.6511.POLE.WDPS | 2021-06-12 | 2021-06-12 | 2022-08-29 | 2022-06-12 | 2022-06-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45219551 | T2 EI NARROWS #1 TAP 1/23 RPR GYWW | ICW
LC | 121525402 | 091/006 | T2 DI HUMBOLDT-TRINITY 91/6 RPL INSW | EUREKA | ETL.1820.INSL.NCER | 2021-06-12 | 2021-06-08 | 2022-06-07 | 2022-06-08 | 2022-06-08 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542141 | T2 EI HUMBOLDT-TRINITY 91/3 RPL INSW | 93I
LC | 121525464 | 105/004 | T2 DI HUMBOLDT-TRINITY 105/4 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-06-12 | 2021-06-09 | 2022-01-22 | 2022-06-09 | 2022-06-09 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542141 | T2 EI HUMBOLDT-TRINITY 91/3 RPL INSW | 93I
LC | 121525604 | 008/042 | T2 DI SILVERADO-FULTON JCT 8/42 RPL SPLS | LAKEVLLE | ETL.1610.INSL | 2021-06-12 | 2021-06-12 | 2022-03-13 | 2022-06-12 | 2022-06-12 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 45142580 | T2 DI SILVERADO-FULTON JCT 8/42 RPL SPLS | ICS
LC | 121525607 | 024/196 | T2 DI PIT #1-COTTONWOOD 24/196 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-12 | 2021-06-11 | 2022-03-08 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195628 | T2 DI PIT #1-COTTONWOOD 24/196 RPR FOND | ICQ
LC | 121525646 | 026/162 | T2 DI TSLA-SLDO-MNTCA 26/162 BACKFIL | VICTOR | ETL.4000.POLE.WOOD | 2021-06-12 | 2021-06-09 | 2021-09-22 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44962485 | T2 DI TSLA-SLDO-MNTCA 26/162 BACKFIL | ICW
LC | 121525676 | 082/002 | T2 DI HUMBOLDT-TRINITY 82/2L RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-03-29 | 2022-06-09 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31591946 | T2 DI HUMBOLDT-TRINITY 82/2L RPL POLE | 70Y
LC | 121525690 | 001/023 | T2 EI NARROWS #1 TAP 1/23 RPR GYWW | SACTO | ETL.6511.POLE.WDPS | 2021-06-12 | 2021-06-12 | 2022-08-29 | 2022-06-12 | 2022-06-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45219552 | T2 EI NARROWS #1 TAP 1/23 RPR GYWW | ICW
LC | 121525691 | 001/023 | T2 EI NARROWS #1 TAP 1/23 RPR GYWW | SACTO | ETL.6511.POLE.WDPS | 2021-06-12 | 2021-06-12 | 2022-08-29 | 2022-06-12 | 2022-06-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45219553 | T2 EI NARROWS #1 TAP 1/23 RPR GYWW | ICW
LC | 121525725 | 002/022 | EI T2 PIT #5 - RND MTN #1 2/22 RPR CNDW | TABLEMTN | ETL.5420.POLE.STPS | 2021-06-12 | 2021-06-12 | 2022-07-17 | 2022-06-12 | 2022-06-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Conductor-Wood | Repair | 31544420 | EI T2 PIT #5 - RND MTN #1 2/22 RPR CNDW | 93C
LC | 121525750 | 024/196 | T2 DI PIT #1-COTNWD 24/196 RPL HRDT | TABLEMTN | ETL.5390.TOWR | 2021-06-12 | 2021-06-11 | 2022-03-08 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45181122 | T2 DI PIT #1-COTNWD 24/196 RPL HRDT | ICQ
LC | 121525758 | 064/324 | T2 DI MALIN-RND MTN #2 64/324 RPR ANCS | TABLEMTN | ETL.6020.TOWR | 2021-06-12 | 2021-06-12 | 2022-08-03 | 2022-06-12 | 2022-06-12 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair | 45194351 | T2 DI MALIN-RND MTN #2 64/324 RPR ANCS | ICS
LC | 121525790 | 024/290C | T2 DI DRUM-SUMMIT #1 24/290C RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2021-06-12 | 2021-06-12 | 2022-09-18 | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581111 | T2 DI DRUM-SUMMIT #1 19/220 RPL STRW | 70Y
LC | 121525839 | 010/066 | T2 DI COTTONWD-DELEVAN #1 10/66 RPL INSS | TABLEMTN | ETL.4550.INSL | 2021-06-12 | 2021-06-11 | 2022-06-10 | 2022-06-11 | 2022-06-11 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546146 | DI COTTONWOOD-DELEVAN #1 RPLC INSS 2TWRS | 93K
LC | 121525883 | 010/066 | T2 DI CTTNWD-LGN CRK 10/66 RPL INSS | TABLEMTN | ETL.4570.INSL | 2021-06-12 | 2021-06-11 | 2022-03-16 | 2022-06-11 | 2022-06-11 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535731 | T2 EI CTTNWD-LGN CRK RPL INSS 8TWR | 93K
LC | 121525887 | 010/066 | T2 DI CTTNWD-LGN CRK 10/66 RPL DAMS | TABLEMTN | ETL.4570.INSL | 2021-06-12 | 2021-06-11 | 2022-03-16 | 2022-06-11 | 2022-06-11 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 45197215 | T2 DI CTTNWD-LGN CRK 10/66 RPL DAMS | ICS
LC | 121525889 | 010/066 | T2 DI COTTONWD-DELEVAN #1 10/66 RPL DAMS | TABLEMTN | ETL.4550.INSL | 2021-06-12 | 2021-06-11 | 2022-06-10 | 2022-06-11 | 2022-06-11 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 45147299 | T2 DI COTTONWD-DELEVAN #1 10/66 RPL DAMS | ICS
LC | 121525919 | 094/003 | T2 DI HUMBOLDT-TRINITY 094/3 RPL INSW | EUREKA | ETL.1820.INSL.NCER | 2021-06-12 | 2021-06-09 | 2022-03-23 | 2022-06-09 | 2022-06-09 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542141 | T2 EI HUMBOLDT-TRINITY 91/3 RPL INSW | 93I
LC | 121525949 | 008/066 | T2 DI CARIBOU-TBL MTN 8/66 RPR FOND | TABLEMTN | ETL.4440.POLE.STPS | 2021-06-12 | 2021-06-09 | 2022-07-07 | 2022-06-09 | 2022-06-09 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45158374 | T2 DI CARIBOU-TBL MTN 8/66 RPR FOND | ICQ
LC | 121525951 | 094/003 | T2 DI HUMBOLDT-TRINITY 94/3L RPR WDPKR | EUREKA | ETL.1820.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-03-23 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45160732 | T2 DI HUMBOLDT-TRINITY 94/3L RPR WDPKR | ICW
LC | 121525959 | 006/106 | T2 DI COLGATE-PALERMO 6/106 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2021-06-12 | 2021-06-09 | 2022-05-14 | 2022-06-09 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31599817 | T2 DI COLGATE-PALERMO 6/106 RPL STRW | 70Y
LC | 121526002 | 014/007A | T2 DI CARIBOU-PLUMAS JCT 14/7A RPL STRW | TABLEMTN | ETL.6290.POLE.WOOD | 2021-06-12 | 2021-06-10 | 2022-10-29 | 2022-06-10 | 2022-06-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541655 | T2 CARIBOU-PLUMAS JCT-WOOD 6/18 RPL POLE | 70Y
LC | 121526014 | 017/148 | T2 DI CRAG VIEW-CASCADE 017/148 RPL INSW | TABLEMTN | ETL.1350.INSL | 2021-06-12 | 2021-06-09 | 2022-09-10 | 2022-06-09 | 2022-06-09 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543332 | T2 DI CRAG VIEW-CASCADE 15/128 RPL INSW | 93I
LC | 121526017 | 017/148 | T2 DI CRG VW-CSCDE 17/148 RPR SHLW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-09-14 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45500234 | T2 DI CRG VW-CSCDE 17/148 RPR SHLW | ICW
LC | 121526204 | 040/342 | T2 DI RND MTN-CTTNWD #3 40/342 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-12 | 2021-06-11 | 2022-08-12 | 2022-06-11 | 2022-06-11 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547626 | T2 DI RND MTN-CTNWD #3 RPL INSS 9TWRS | 93K
LC | 121526301 | 001/037 | T2 DI KILARC-DESCHUTES 001/037 RPR SPLW | TABLEMTN | ETL.7300.INSL.CERA | 2021-06-12 | 2021-06-11 | 2022-04-15 | 2022-06-11 | 2022-06-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45212343 | T2 DI KILARC-DESCHUTES 001/037 RPR SPLW | ICW
LC | 121526347 | 031/224 | T2 DI CARIBOU-TABLE MTN 31/224 RPL HRDT | TABLEMTN | ETL.4440.TOWR | 2021-06-12 | 2021-06-10 | 2022-02-08 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45108129 | T2 DI CARIBOU-TABLE MTN 31/224 RPL HRDT | ICQ
LC | 121526393 | 010/072 | T2 DI GRN VLLY-LLAGAS 10/72 RPL CRSW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-09-24 | 2022-06-08 | 2022-06-08 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31544763 | T2 DI GRN VLLY-LLAGAS 10/72 RPL CRSW | 93E
LC | 121526396 | 010/072 | T2 DI GRN VLLY-LLAGAS 10/72 RPL HRDD | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2021-09-29 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 44981659 | T2 DI GRN VLLY-LLAGAS 10/72 RPL HRDD | ICW
LC | 121526518 | 041/345 | T2 DI PIT #1-COTTONWOOD 41/345 RPL HRDT | TABLEMTN | ETL.5390.TOWR | 2021-06-12 | 2021-06-10 | 2022-03-01 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45149534 | T2 DI PIT #1-COTTONWOOD 41/345 RPL HRDT | ICQ
LC | 121526573 | 094/007 | T2 DI HUMBOLDT-TRINITY 94/7R RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-03-22 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45160734 | T2 DI HUMBOLDT-TRINITY 94/7R RPR STRW | ICW
LC | 121526616 | 011/127 | T2 DI DRUM-SUMMIT #1 011/127 RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-08-25 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45195994 | T2 DI DRUM-SUMMIT #1 011/127 RPR STRW | ICW
LC | 121526671 | 011/134 | T2 DI DRUM-SUMMIT #1 011/134 RPL INSW | SACTO | ETL.1440.INSL | 2021-06-12 | 2021-06-08 | 2022-06-27 | 2022-06-08 | 2022-06-08 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31549083 | T2 DI DRUM-SUMMIT #1 011/134 RPL INSW | 93I
LC | 121526688 | 006/006 | T2 DI LAYTONVILLE-COVELO 06/06L RPL STRW | WILLITS | ETL.7390.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-06-26 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544413 | T2 DI LAYTONVILLE-COVELO 06/06C RPL STRW | 70Y
LC | 121526689 | 006/006 | T2 DI LAYTONVILLE-COVELO 06/06C RPL STRW | WILLITS | ETL.7390.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-06-28 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544413 | T2 DI LAYTONVILLE-COVELO 06/06C RPL STRW | 70Y
LC | 121526720 | 111/000 | T2 DI HUMBOLDT-BRDGVLL 111/0 RPL INSW | EUREKA | ETL.1810.INSL.NCER | 2021-06-12 | 2021-06-08 | 2022-04-05 | 2022-06-08 | 2022-06-08 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31544412 | T2 DI HUMBOLDT-BRIDGEVLLE 114/2 RPL INSW | 93I
LC | 121526722 | 013/113 | T2 DI CRAG VIEW-CASCDE 03/113 RMV DEBRIS | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-07-06 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45426622 | T2 DI CRAG VIEW-CASCDE 03/113 RMV DEBRIS | ICW
LC | 121526789 | 007/133 | T2 DI SMRTVLL-NCLS #1 7/133 RPL POLE | SACTO | ETL.7990.POLE.WOOD | 2021-06-12 | 2021-06-09 | 2022-08-24 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544424 | T2 DI SMRTVIL-NICOLUS #1 7/132 RPL STRW | 70Y
LC | 121526844 | 003/049 | T2 DI BURNS-LONE STAR #1 03/49 RPR GYWW | MOSSLNDG | ETL.6230.POLE.WOOD | 2021-06-12 | 2021-06-09 | 2022-02-09 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44932395 | T2 DI BURNS-LONE STAR #1 03/49 RPR GYWW | ICW
LC | 121526846 | 008/007 | T2 DI FULTON-HOPLAND 08/07 GRND WSH | LAKEVLLE | ETL.6890.INSL.CERA | 2021-06-12 | 2021-06-10 | 2022-08-23 | 2022-06-10 | 2022-06-10 | Late | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | Contaminated | Insulator | Ground Wash | 45194043 | T2 DI FULTON-HOPLAND 08/07 GRND WSH | ICD
LC | 121526848 | 018/004 | T2 DI CLEAR LAKE-KONOCTI 18/04 RPL INSW | WILLITS | ETL.6852.INSL.NCER | 2021-06-12 | 2021-06-10 | 2022-02-03 | 2022-06-10 | 2022-06-10 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31595521 | T2 DI CLEAR LAKE-KONOCTI 18/04 RPL INSW | 93I
LC | 121526849 | 018/004 | T2 DI CLEAR LAKE-KONOCTI 18/04 RPR STRW | LAKEVLLE | ETL.6852.POLE.WOOD | 2021-06-12 | 2021-06-10 | 2022-02-03 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45138171 | T2 DI CLEAR LAKE-KONOCTI 18/04 RPR INSW | ICW
LC | 121526923 | 015/131 | T2 DI CRAG VIEW-CSCDE 015/131 RMV DEBRIS | TABLEMTN | ETL.1350.POLE.WOOD | 2021-06-12 | 2021-06-09 | 2022-06-30 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45428529 | T2 DI CRAG VIEW-CSCDE 015/131 RMV DEBRIS | ICW
LC | 121526927 | 031/223 | T2 DI CARIBOU TBL MTN 31/223 RPL HRDT | TABLEMTN | ETL.4440.TOWR | 2021-06-12 | 2021-06-10 | 2022-02-08 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45108128 | T2 DI CARIBOU TBL MTN 31/223 RPL HRDT | ICQ
LC | 121526994 | 028/200 | T2 DI CARIBOU-TABLE MTN 28/200 RPL INSS | TABLEMTN | ETL.4440.INSL | 2021-06-12 | 2021-06-11 | 2022-06-21 | 2022-06-11 | 2022-06-11 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121527084 | 009/083 | T2 DI CRAG VIEW-CASCADE 09/83 RPR GYWW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-09-15 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45471568 | T2 DI CRAG VIEW-CASCADE 09/83 RPR GYWW | ICW
LC | 121527085 | 009/083 | T2 DI CRAG VIEW-CASCADE 09/83 RPR OPGW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-08 | 2022-09-15 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45509722 | T2 DI CRAG VIEW-CASCADE 09/83 RPR OPGW | ICW
LC | 121527090 | 066/585 | T2 DI COTTNWD-DELVN #2 66/585 RPR FOND | TABLEMTN | ETL.4580.TOWR | 2021-06-12 | 2021-06-08 | 2022-01-12 | 2022-06-08 | 2022-06-08 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45107495 | T2 DI COTTNWD-DELVN #2 66/585 RPR FOND | ICQ
LC | 121527093 | 037/178 | T2 DI LKVLLE-IGNCO #2 37/178 RPL INSS | LAKEVLLE | ETL.3745.INSL.CERA | 2021-06-12 | 2021-06-08 | 2022-07-15 | 2022-06-08 | 2022-06-08 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31531809 | DI LAKEVILLE-IGNACIO #2 RPL INSS 4 TWRS. | 93K
LC | 121527094 | 037/178 | T2 DI LKVLLE-IGNCIO #2 37/178 RPR STRT | LAKEVLLE | ETL.3745.TOWR | 2021-06-12 | 2021-06-08 | 2022-06-02 | 2022-06-08 | 2022-06-08 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45142410 | T2 DI LKVLLE-IGNCIO #2 37/178 RPR STRT | ICQ
LC | 121527098 | 024/283 | T2 DI DRUM-SUMMIT #1 24/283 RPL INSW | SACTO | ETL.1440.INSL | 2021-06-12 | 2021-06-08 | 2022-06-28 | 2022-06-08 | 2022-06-08 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541895 | T2 EI DRUM-SUMMIT #1 20/237 RPL INSW | 93I
LC | 121527140 | 015/495 | T2 DI SPAULDING-SUMMIT 15/495 RPR INSW | SACTO | ETL.8060.INSL.NCER | 2021-06-12 | 2021-06-08 | 2022-09-22 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45219556 | T2 DI SPAULDING-SUMMIT 15/495 RPR INSW | ICW
LC | 121527142 | 012/251 | T2 DI COTTONWD-RED BLUFF 12/251 RMV BUTT | TABLEMTN | ETL.6660.POLE.NWOD | 2021-06-12 | 2021-06-10 | 2022-06-06 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45197171 | T2 DI COTTONWD-RED BLUFF 12/251 RMV BUTT | ICW
LC | 121527149 | 046/395 | T2 DI RND MTN-CTTNWD #3 46/395 RMV VEG | TABLEMTN | ETL.5650.TOWR | 2021-06-12 | 2021-06-03 | 2022-08-09 | 2022-06-03 | 2022-06-03 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121527220 | 007/081 | T2 DI WST PNT-VLEY SPRINGS 7/81 RPL STRW | VICTOR | ETL.8350.POLE.WOOD | 2021-06-12 | 2021-06-08 | 2022-05-25 | 2022-06-08 | 2022-06-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31579997 | T3 DI WP-VALLEY SPRINGS 0/2 RPL STRW | 70Y
LC | 121527240 | 026/310 | T2 DI DRUM-SUMMIT #1 26/310 RPR FOND | SACTO | ETL.1440.TOWR | 2021-06-12 | 2021-06-08 | 2022-06-21 | 2022-06-08 | 2022-06-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45193939 | T2 DI DRUM-SUMMIT #1 26/310 RPR FOND | ICQ
LC | 121527528 | 012/059 | T2 EI FULTON-PUEBLO 12/59 RMV NEST | LAKEVLLE | ETL.1600.TOWR | 2021-06-13 | 2021-06-11 | 2022-02-28 | 2022-06-11 | 2022-06-11 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45142249 | T2 EI FULTON-PUEBLO 12/59 RMV NEST | ICS
LC | 121527529 | 013/062 | T2 EI FULTON-PUEBLO 13/62 RPR FOND | LAKEVLLE | ETL.1600.TOWR | 2021-06-13 | 2021-06-11 | 2022-02-01 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45151412 | T2 EI FULTON-PUEBLO 13/62 RPR FOND | ICQ
LC | 121527552 | 007/135 | T2 EI VALLEY SPRINGS#2 007/135L RPR GYWW | VICTOR | ETL.9460.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-08-18 | 2022-06-13 | 2022-06-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45167555 | T2 EI VALLEY SPRINGS#2 007/135L RPR GYWW | ICW
LC | 121527602 | 007/135 | T2 EI VALLEY SPRINGS#2 007/135R RPR GYWW | VICTOR | ETL.9460.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-08-18 | 2022-06-13 | 2022-06-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45167556 | T2 EI VALLEY SPRINGS#2 007/135R RPR GYWW | ICW
LC | 121527614 | 011/111 | EI T2 PIT #5-RND MTN #211/111 RPL STRW | TABLEMTN | ETL.5430.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-06-16 | 2022-06-13 | 2022-06-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31601295 | EI T2 PIT #5-ROUND MTN #2 7/72 RPL STRW | 70Y
LC | 121527620 | 007/135 | T2 EI VALLEY SPRINGS#2 007/135M RPR GYWW | VICTOR | ETL.9460.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-08-18 | 2022-06-13 | 2022-06-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45167558 | T2 EI VALLEY SPRINGS#2 007/135M RPR GYWW | ICW
LC | 121527661 | 011/111 | EI T2 PIT #5-RND MTN #2 11/111 RPL STRW | TABLEMTN | ETL.5430.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-06-16 | 2022-06-13 | 2022-06-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31601295 | EI T2 PIT #5-ROUND MTN #2 7/72 RPL STRW | 70Y
LC | 121527753 | 011/109 | EI T2 PIT #5-RND MTN #2 11/109 RPR STRW | TABLEMTN | ETL.5430.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-06-07 | 2022-06-13 | 2022-06-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45213820 | EI T2 PIT #5-RND MTN #2 11/109 RPR STRW | ICW
LC | 121527968 | 007/133 | T2 EI VALLEY SPRINGS#2 007/133L RPL STRW | VICTOR | ETL.9460.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-03-10 | 2022-06-13 | 2022-06-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544434 | T2 EI VALLEY SPRINGS#2 007/133M RPL STRW | 70Y
LC | 121527984 | 007/133 | T2 EI VALLEY SPRINGS#2 007/133M RPL STRW | VICTOR | ETL.9460.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-03-10 | 2022-06-13 | 2022-06-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544434 | T2 EI VALLEY SPRINGS#2 007/133M RPL STRW | 70Y
LC | 121527985 | 007/133 | T2 EI VALLEY SPRINGS#2 007/133R RPL STRW | VICTOR | ETL.9460.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-03-10 | 2022-06-13 | 2022-06-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544434 | T2 EI VALLEY SPRINGS#2 007/133M RPL STRW | 70Y
LC | 121528117 | 002/025 | EI T2 PT #5-RD MN #2 2/25 RPR SHLW CMPLT | TABLEMTN | ETL.5430.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-06-02 | 2022-06-13 | 2022-06-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45213819 | EI T2 PIT #5-ROUND MTN #2 2/25 RPR SHLW | ICW
LC | 121528145 | 002/025 | EI T2 PT #5-RD MN #2 2/25 RPR SHLW CMPLT | TABLEMTN | ETL.5430.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-06-02 | 2022-06-13 | 2022-06-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45213818 | EI T2 PIT #5-ROUND MTN #2 2/25 RPR SHLW | ICW
LC | 121528345 | 000/009 | T2 EI MELONES-CURTIS 0/009 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-06-13 | 2021-06-13 | 2021-11-19 | 2022-06-13 | 2022-06-13 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543177 | T2 EI MELONES-CURTIS 7/3 RPL INSW | 93I
LC | 121528390 | 000/008 | T2 EI MELONES-CURTIS 0/8R RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-11-29 | 2022-06-13 | 2022-06-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544432 | T2 EI MELONES-CURTIS 0/8R RPL STRW | 70Y
LC | 121528411 | 009/100 | EI T2 PIT #5-RD MT #2 9/100 RPL STRW CMT | TABLEMTN | ETL.5430.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-06-17 | 2022-06-13 | 2022-06-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31601295 | EI T2 PIT #5-ROUND MTN #2 7/72 RPL STRW | 70Y
LC | 121528415 | 000/007 | T2 EI MELONES-CURTIS 0/7L RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-11-28 | 2022-06-13 | 2022-06-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544431 | T2 EI MELONES-CURTIS 0/7L RPL STRW | 70Y
LC | 121528419 | 000/007 | T2 EI MELONES-CURTIS 0/7R RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-11-28 | 2022-06-13 | 2022-06-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544431 | T2 EI MELONES-CURTIS 0/7L RPL STRW | 70Y
LC | 121528554 | 010/105 | EI T2 PIT #5-RND MTN #1 10/105 RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2022-07-13 | 2022-06-13 | 2022-06-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121528559 | 001/000 | T2 EI MELONES-CURTIS 1/000 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-06-13 | 2021-06-13 | 2021-11-18 | 2022-06-13 | 2022-06-13 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543177 | T2 EI MELONES-CURTIS 7/3 RPL INSW | 93I
LC | 121528715 | 001/002 | T2 EI MELONES-CURTIS 1/002 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-06-13 | 2021-06-13 | 2021-11-18 | 2022-06-13 | 2022-06-13 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543177 | T2 EI MELONES-CURTIS 7/3 RPL INSW | 93I
LC | 121528842 | 001/003 | EI T2 MELONES-CURTIS 1/003 RPL HRDW | VICTOR | ETL.2390.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2021-10-02 | 2022-06-13 | 2022-06-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44977846 | EI T2 MELONES-CURTIS 1/003 RPL HRDW | ICW
LC | 121528843 | 001/003 | T2 EI MELONES-CURTIS 1/003 RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-06-13 | 2021-06-13 | 2021-10-02 | 2022-06-13 | 2022-06-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44977847 | T2 EI MELONES-CURTIS 1/003 RPR STRW | ICW
LC | 121530855 | 016/001 | T2 DI TRINITY-MAPLE CRK 16/1 GYWW COMPLT | EUREKA | ETL.8170.POLE.WOOD | 2021-06-14 | 2021-06-13 | 2022-04-16 | 2022-06-13 | 2022-06-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44874933 | T2 DI TRINITY-MAPLE CRK 16/1 RPR GYWW | ICW
LC | 121530904 | 023/283A | T2 DI DRUM-SUMMIT #2 23/283A RPL INSW | SACTO | ETL.1450.INSL | 2021-06-14 | 2021-06-12 | 2022-06-09 | 2022-06-12 | 2022-06-12 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543772 | T2 DI DRUM-SUMMIT #2 23/283A RPL INSW | 93I
LC | 121530918 | 005/052 | T2 DI BRIDGEVILLE CTTNWD 5/052L RPR SHLW | TABLEMTN | ETL.1110.POLE.WDPS | 2021-06-14 | 2021-06-08 | 2021-07-01 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44873528 | T2 DI BRIDGEVILLE CTTNWD 5/052L RPR SHLW | ICW
LC | 121530919 | 005/052 | T2 DI BRIDGEVILLE CTTNWD 5/052L RPR STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2021-06-14 | 2021-06-08 | 2021-07-01 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 44873527 | T2 DI BRIDGEVILLE CTTNWD 5/052L RPR STRW | ICW
LC | 121530939 | 009/067 | T2 DI ROCK CREEK-POE 9/67 RPL INSS | TABLEMTN | ETL.5630.INSL | 2021-06-14 | 2021-06-13 | 2022-08-03 | 2022-06-13 | 2022-06-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535387 | T2 EI ROCK CREEK-POE RPL INSS 7TWRS | 93K
LC | 121530970 | 005/052 | T2 DI BRIDGEVILLE CTTNWD 5/052R RPR STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2021-06-14 | 2021-06-08 | 2021-07-01 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 44873531 | T2 DI BRIDGEVILLE CTTNWD 5/052R RPR STRW | ICW
LC | 121530975 | 054/485 | T2 DI ROUND MTN-CTNWD #3 54/485 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-14 | 2021-06-10 | 2022-08-03 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548265 | T2 DI RND MTN-COTNWD #3 RPL INSS 10TWRS | 93K
LC | 121531031 | 093/014 | T2 DI HUMBOLDT-TRINITY 93/14R RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-06-14 | 2021-06-09 | 2022-10-08 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121531035 | 093/014 | T2 DI HUMBOLDT-TRINITY 93/14C RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-06-14 | 2021-06-09 | 2022-10-08 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121531055 | 005/041 | T2 DI ROCK CREEK-POE 5/41 RPR FOND | TABLEMTN | ETL.5630.TOWR | 2021-06-14 | 2021-06-13 | 2022-07-22 | 2022-06-13 | 2022-06-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195627 | T2 DI ROCK CREEK-POE 5/41 RPR FOND | ICQ
LC | 121531056 | 005/041 | T2 DI ROCK CREEK-POE 5/41 RPL INSS | TABLEMTN | ETL.5630.INSL | 2021-06-14 | 2021-06-13 | 2022-08-05 | 2022-06-13 | 2022-06-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535387 | T2 EI ROCK CREEK-POE RPL INSS 7TWRS | 93K
LC | 121531182 | 019/381 | T2 DI COLGATE-PALERMO 19/381 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2021-06-14 | 2021-06-12 | 2022-05-04 | 2022-06-12 | 2022-06-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31580350 | T2 DI COLGATE-PALERMO 19/381 RPL STRW | 70Y
LC | 121531452 | 002/000 | T2 EI MELONES-CURTIS 2/0 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-06-14 | 2021-06-14 | 2021-11-19 | 2022-06-14 | 2022-06-14 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543177 | T2 EI MELONES-CURTIS 7/3 RPL INSW | 93I
LC | 121531483 | 011/141 | T2 DI W POINT VLY SPNGS 011/141 RPL HRDD | VICTOR | ETL.8350.POLE.NWOD | 2021-06-14 | 2021-06-08 | 2022-05-10 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45156978 | T2 DI W POINT VLY SPNGS 011/141 RPL HRDD | ICW
LC | 121531586 | 002/001 | T2 EI MELONES-CURTIS 2/1R RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-06-14 | 2021-06-14 | 2022-11-30 | 2022-06-14 | 2022-06-14 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545144 | T2 EI MELONES-CURTIS 2/1 RPL STRW | 70Y
LC | 121531674 | 005/043 | T2 DI ROCK CREEK-POE 5/43 RPR FOND | TABLEMTN | ETL.5630.TOWR | 2021-06-14 | 2021-06-13 | 2022-07-11 | 2022-06-13 | 2022-06-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195626 | T2 DI ROCK CREEK-POE 5/43 RPR FOND | ICQ
LC | 121531746 | 054/486 | T2 DI ROUND MTN-CTNWD #3 54/486 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-14 | 2021-06-10 | 2022-08-03 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548265 | T2 DI RND MTN-COTNWD #3 RPL INSS 10TWRS | 93K
LC | 121531800 | 012/109 | T2 DI CRAG VIEW-CASCADE 12/109 RPL HRDS | TABLEMTN | ETL.1350.TOWR | 2021-06-14 | 2021-05-29 | 2022-09-21 | 2022-05-29 | 2022-05-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45436128 | T2 DI CRAG VIEW-CASCADE 12/109 RPL HRDS | ICS
LC | 121531944 | 048/001A | T2 DI HUMBOLDT-TRINITY 48/1A RMV BUTT | EUREKA | ETL.1820.POLE.NWOD | 2021-06-14 | 2021-06-12 | 2022-03-27 | 2022-06-12 | 2022-06-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45145183 | T2 DI HUMBOLDT-TRINITY 48/1A RMV BUTT | ICW
LC | 121532096 | 016/503 | T2 DI SPAULDING-SUMMIT 16/503 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2021-06-14 | 2021-06-08 | 2022-09-22 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31596203 | T2 DI SPULDNG-SMMIT 014/459 RPL POLE | 70Y
LC | 121532336 | 058/289 | T2 DI MALIN-ROUND MTN #2 58/289 RPR FOND | TABLEMTN | ETL.6020.TOWR | 2021-06-14 | 2021-06-10 | 2022-10-04 | 2022-06-10 | 2022-06-10 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45193985 | T2 DI MALIN-ROUND MTN #2 58/289 RPR FOND | ICQ
LC | 121532612 | 009/062 | T2 DI COTTONWOOD-DLVN #1 9/62 RPLC HRDT | TABLEMTN | ETL.4550.TOWR | 2021-06-14 | 2021-06-11 | 2022-01-03 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45098659 | T2 DI COTTONWOOD-DLVN #1 9/62 RPLC HRDT | ICQ
LC | 121532615 | 009/062 | T2 DI COTTONWOOD-DLVN #1 9/62 RPLC DAMS | TABLEMTN | ETL.4550.INSL | 2021-06-14 | 2021-06-11 | 2022-05-21 | 2022-06-11 | 2022-06-11 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 45147343 | T2 DI COTTONWOOD-DLVN #1 9/62 RPLC DAMS | ICS
LC | 121532696 | 009/062 | T2 DI CTNWD-DLVN #1 9/62 RPR INSS | TABLEMTN | ETL.4550.INSL | 2021-06-14 | 2021-06-11 | 2022-05-21 | 2022-06-11 | 2022-06-11 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45147344 | T2 DI CTNWD-DLVN #1 9/62 RPR INSS | ICS
LC | 121532893 | 004/116 | T2 EI COLGATE-ALLEGHANY 4/116 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2021-06-14 | 2021-06-14 | 2022-06-22 | 2022-06-14 | 2022-06-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45224559 | T2 EI COLGATE-ALLEGHANY 4/116 RPR STRW | ICW
LC | 121532952 | 010/102 | EI T2 PIT #5-RND MTN #1 10/102 RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-14 | 2021-06-14 | 2022-07-13 | 2022-06-14 | 2022-06-14 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121533210 | 016/006 | T2 DI HMBLDT BY-RIO DL JCT 16/6 RPL INSW | EUREKA | ETL.7100.INSL.NCER | 2021-06-14 | 2021-06-14 | 2022-04-24 | 2022-06-14 | 2022-06-14 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542056 | T2 DI HMBLDT BY-RIO DL JCT 18/1 RPL INSW | 93I
LC | 121533352 | 002/006 | T2 EI MELONES-CURTIS 2/006 RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-06-14 | 2021-06-14 | 2021-10-02 | 2022-06-14 | 2022-06-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44977848 | T2 EI MELONES-CURTIS 2/006 RPR STRW | ICW
LC | 121533356 | 002/007 | T2 EI MELONES-CURTIS 2/007R RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-06-14 | 2021-06-14 | 2022-12-02 | 2022-06-14 | 2022-06-14 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545145 | T2 EI MELONES-CURTIS 2/007 RPL STRW | 70Y
LC | 121533382 | 002/006 | T2 EI MELONES-CURTIS 2/6 RPL X-BRACE | VICTOR | ETL.2390.POLE.WDPS | 2021-06-14 | 2021-06-14 | 2021-10-02 | 2022-06-14 | 2022-06-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Crossarm-Wood | Repair | 44962393 | T2 EI MELONES-CURTIS 2/6 RPL X-BRACE | ICW
LC | 121533383 | 002/007 | T2 EI MELONES-CURTIS 2/007L RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-06-14 | 2021-06-14 | 2022-12-02 | 2022-06-14 | 2022-06-14 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545145 | T2 EI MELONES-CURTIS 2/007 RPL STRW | 70Y
LC | 121533385 | 002/006 | T2 EI MELONES-CURTIS 2/006 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-06-14 | 2021-06-14 | 2021-11-18 | 2022-06-14 | 2022-06-14 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543177 | T2 EI MELONES-CURTIS 7/3 RPL INSW | 93I
LC | 121533553 | 010/099 | EI T2 PIT #5-RND MTN #1 10/99 RPL HRDW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-14 | 2021-06-14 | 2021-07-27 | 2022-06-14 | 2022-06-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44931918 | EI T2 PIT #5-RND MTN #1 10/99 RPL HRDW | ICW
LC | 121533565 | 010/092 | T2 DI CRAG VIEW-CASCADE 10/92L RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-14 | 2021-06-08 | 2022-09-27 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121533665 | 000/019 | T2 DI COLGATE-CHALLENGE 000/019 RPL PL | SACTO | ETL.6480.POLE.WOOD | 2021-06-14 | 2021-06-09 | 2022-08-24 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31580347 | T2 DI COLGATE-CHALLENGE 000/019 RPL PL | 70Y
LC | 121533835 | 053/473 | T2 DI PIT #1 CTNWD 53/473 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-14 | 2021-06-10 | 2022-03-04 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45195625 | T2 DI PIT #1 CTNWD 53/473 RPR FOND | ICQ
LC | 121534003 | 093/006 | T2 DI HUMBOLDT-TRINITY 93/6 RPL INSW | EUREKA | ETL.1820.INSL.NCER | 2021-06-14 | 2021-06-09 | 2022-03-23 | 2022-06-09 | 2022-06-09 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542141 | T2 EI HUMBOLDT-TRINITY 91/3 RPL INSW | 93I
LC | 121534155 | 022/104 | T2 DI FULTON-PUEBLO 22/104 RPL HNGR | LAKEVLLE | ETL.1600.INSL.CERA | 2021-06-14 | 2021-06-10 | 2022-03-02 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 45142259 | T2 DI FULTON-PUEBLO 22/104 RPL HNGR | ICQ
LC | 121534205 | 022/104 | T2 DI FULTON-PUEBLO 22/104 RPL INSS | LAKEVLLE | ETL.1600.INSL.CERA | 2021-06-14 | 2021-06-10 | 2022-03-02 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549865 | T2 DI FULTON-PUEBLO-INSUL RPL INSS 5TWR | 93K
LC | 121534285 | 000/022 | T2 DI COLGATE-CHALLENGE 0/22 RPR STRW | SACTO | ETL.6480.POLE.WOOD | 2021-06-14 | 2021-06-09 | 2021-08-20 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44876427 | T2 DI COLGATE-CHALLENGE 0/22 RPR STRW | ICW
LC | 121534395 | 053/479 | T2 DI ROUND MTN-CTNWD #3 53/479 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-14 | 2021-06-10 | 2022-08-05 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548265 | T2 DI RND MTN-COTNWD #3 RPL INSS 10TWRS | 93K
LC | 121534692 | 047/406 | T2 DI ROND-MTN CTTNWD #3 47/406 INS STEP | TABLEMTN | ETL.5650.TOWR | 2021-06-14 | 2021-06-10 | 2022-01-26 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45110559 | T2 DI ROND-MTN CTTNWD #3 47/406 INS STEP | ICQ
LC | 121534805 | 009/109 | T2 DI DRUM-SUMMIT #2 9/109 RPR STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-14 | 2021-06-08 | 2022-07-27 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45195997 | T2 DI DRUM-SUMMIT #2 9/109 RPR STRW | ICW
LC | 121534971 | 023/111 | T2 DI SILVERADO-FULTON 23/111 RPL INSS | LAKEVLLE | ETL.1610.INSL | 2021-06-14 | 2021-06-10 | 2022-03-17 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548688 | T2 DI SLVDO FLTN JCT SW RPL INSS 6TWRS | 93K
LC | 121535129 | 004/009 | T2 EI MELONES-CURTIS 4/009 RPL INSW | VICTOR | ETL.2390.SWIT | 2021-06-14 | 2021-06-14 | 2022-08-28 | 2022-06-14 | 2022-06-14 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543178 | EI MELONES-CURTIS RPL INSW | 93I
LC | 121535183 | 016/507 | T2 DI SPAULDING-SUMMIT 16/507 RPL HRDW | SACTO | ETL.8060.POLE.WDPS | 2021-06-14 | 2021-06-09 | 2022-08-05 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45219557 | T2 DI SPAULDING-SUMMIT 16/507 RPL HRDW | ICW
LC | 121535842 | 005/068 | T2 DI BURNS-LONE STAR #1 05/68 RMV BUTT | MOSSLNDG | ETL.6230.POLE.WOOD | 2021-06-14 | 2021-06-10 | 2021-09-11 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44932389 | T2 DI BURNS-LONE STAR #1 05/68 RMV BUTT | ICW
LC | 121535846 | 034/002 | T2 DI MNDCNO WLT FT BRG 34/2 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-14 | 2021-06-10 | 2022-05-12 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148589 | T2 DI MNDCNO WLT FT BRG 34/2 RPR GYWW | ICW
LC | 121535910 | 001/027 | T2 DI CTTNWD-BNTN #1 1/27 RPR STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-06-14 | 2021-06-10 | 2022-08-30 | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45213583 | T2 DI CTTNWD-BNTN #1 1/27 RPR STRW | ICW
LC | 121535930 | 093/012 | T2 DI HUMBLDT-TRINTY 93/12 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-06-14 | 2021-06-08 | 2022-03-23 | 2022-06-08 | 2022-06-08 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542141 | T2 EI HUMBOLDT-TRINITY 91/3 RPL INSW | 93I
LC | 121535933 | 048/420 | T2 DI EI PIT#1-COTTONWD 48/420 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-14 | 2021-06-10 | 2022-07-13 | 2022-06-10 | 2022-06-10 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195624 | T2 DI EI PIT#1-COTTONWD 48/420 RPR FOND | ICQ
LC | 121536108 | 006/032 | T2 DI SILVERA FULTON INSUL 6/32 RPL INSS | LAKEVLLE | ETL.1610.INSL | 2021-06-14 | 2021-06-10 | 2022-03-09 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548682 | T2 DI SILVERADO-FULTON JCT RPL INSS 6TWR | 93K
LC | 121536109 | 022/102 | T2 DI FULTON-PUEBLO 22/102 RPR INSS | LAKEVLLE | ETL.1600.INSL.CERA | 2021-06-14 | 2021-06-09 | 2022-03-02 | 2022-06-09 | 2022-06-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45142254 | T2 DI FULTON-PUEBLO 22/102 RPR INSS | ICS
LC | 121536151 | 022/102 | T2 DI FULTON-PUEBLO 22/102 INS STEP | LAKEVLLE | ETL.1600.TOWR | 2021-06-14 | 2021-06-09 | 2022-06-14 | 2022-06-09 | 2022-06-09 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45142258 | T2 DI FULTON-PUEBLO 22/102 INS STEP | ICQ
LC | 121536152 | 022/102 | T2 DI FULTON-PUEBLO 22/102 RPR FOND | LAKEVLLE | ETL.1600.TOWR | 2021-06-14 | 2021-06-09 | 2022-01-29 | 2022-06-09 | 2022-06-09 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45151413 | T2 DI FULTON-PUEBLO 22/102 RPR FOND | ICQ
LC | 121536153 | 006/032 | T2 DI FULTON-PUEBLO-INSUL 6/32 RPL INSS | LAKEVLLE | ETL.1600.INSL | 2021-06-14 | 2021-06-10 | 2022-02-22 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549865 | T2 DI FULTON-PUEBLO-INSUL RPL INSS 5TWR | 93K
LC | 121536156 | 006/032 | T2 DI FULTON-PUEBLO TOWER 6/32 RPL HNGR | LAKEVLLE | ETL.1600.INSL | 2021-06-14 | 2021-06-10 | 2022-03-14 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 45142240 | T2 DI FULTON-PUEBLO TOWER 6/32 RPL HNGR | ICQ
LC | 121536157 | 030/218 | T2 DI CARIBOU TBL MTN 30/218 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-14 | 2021-06-10 | 2022-06-20 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121536159 | 006/032 | T2 DI FULTON-PUEBLO TOWER 6/32 RPL HNGR | LAKEVLLE | ETL.1610.INSL | 2021-06-14 | 2021-06-10 | 2022-02-25 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 45142558 | T2 DI FULTON-PUEBLO TOWER 6/32 RPL HNGR | ICQ
LC | 121536200 | 108/001 | T2 DI HUMBOLDT-TRINITY 108/1L RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-14 | 2021-06-10 | 2022-01-22 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45128332 | T2 DI HUMBOLDT-TRINITY 108/1L RPR STRW | ICW
LC | 121536271 | 024/115 | T2 DI SLVRDO-FULTON JCT 24/115 RPL HRDT | LAKEVLLE | ETL.1600.TOWR | 2021-06-14 | 2021-06-10 | 2022-04-21 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45142281 | T2 DI SLVRDO-FULTON JCT 24/115 RPL HRDT | ICQ
LC | 121536468 | 052/470 | T2 DI RND MTN CTTNWD #3 052/470 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-14 | 2021-06-10 | 2022-08-05 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548265 | T2 DI RND MTN-COTNWD #3 RPL INSS 10TWRS | 93K
LC | 121536502 | 010/115 | T2 DI DRUM-SUMMIT #1 10/115LRPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-14 | 2021-06-08 | 2022-06-16 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543339 | T2 EI DRUM-SUMMIT #1 9/111 RPL STRW | 70Y
LC | 121536530 | 006/029 | T2 DI PITTSBURG-TSLA #1 006/029 RPL HRDT | CONCORD | ETL.5510.TOWR | 2021-06-14 | 2021-06-10 | 2022-04-13 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45190829 | T2 DI PITTSBURG-TSLA #1 006/029 RPL HRDT | ICQ
LC | 121536551 | 022/156 | T2 DI CARIBOU-TABLE MTN 22/156 RPR JUMS | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-14 | 2021-06-08 | 2022-06-24 | 2022-06-08 | 2022-06-08 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Jumper-Steel | Repair | 45212444 | T2 DI CARIBOU-TABLE MTN 22/156 RPR JUMS | ICS
LC | 121536557 | 009/081 | T2 DI CRAG VIEW-CASCADE 9/81 RPR OPGW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-14 | 2021-06-09 | 2022-09-15 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45509607 | T2 DI CRAG VIEW-CASCADE 9/81 RPR OPGW | ICW
LC | 121536572 | 021/295C | T2 DI SSQC-SNT YNZ SW 21/295C RPL STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-06-14 | 2021-06-14 | 2022-05-20 | 2022-06-14 | 2022-06-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544433 | T2 DI SSQC-SNT YNZ SW 21/295C RPL STRW | 70Y
LC | 121536573 | 066/584 | T2 DI COTTNWD-DELVN #2 66/584 RPR FOND | TABLEMTN | ETL.4580.TOWR | 2021-06-14 | 2021-06-08 | 2022-01-10 | 2022-06-08 | 2022-06-08 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45107494 | T2 DI COTTNWD-DELVN #2 66/584 RPR FOND | ICQ
LC | 121536591 | 009/081 | T2 DI CRAG VIEW-CASCADE 9/81 RPL INSW | TABLEMTN | ETL.1350.INSL | 2021-06-14 | 2021-06-09 | 2022-09-15 | 2022-06-09 | 2022-06-09 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542859 | T2 DI CRAG VIEW-CASCADE 02/018 RPL INSLW | 93I
LC | 121536600 | :007/057 | T2 DI PIT #3-PIT #1 07/57 RPR FOND | TABLEMTN | ETL.5400.TOWR | 2021-06-14 | 2021-06-11 | 2022-07-27 | 2022-06-11 | 2022-06-11 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45198321 | T2 DI PIT #3-PIT #1 07/57 RPR FOND | ICQ
LC | 121536604 | :001/013 | T2 DI ULTON-PUEBLO :01/13 RMV VEG | LAKEVLLE | ETL.1600.POLE.WOOD | 2021-06-14 | 2021-06-10 | 2022-02-18 | 2022-06-10 | 2022-06-10 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121536608 | 030/221 | T2 DI CARIBOU-TABLE MTN 30/221 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-14 | 2021-06-10 | 2022-06-18 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121536610 | 014/344 | T2 DI CTTNWD BNTN 14/344 RPR GYWW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-06-14 | 2021-06-10 | 2022-08-22 | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213584 | T2 DI CTTNWD BNTN 14/344 RPR GYWW | ICW
LC | 121536612 | 054/491 | T2 DI RND MTN CTTNWD #3 054/491 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-14 | 2021-06-10 | 2022-08-03 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548265 | T2 DI RND MTN-COTNWD #3 RPL INSS 10TWRS | 93K
LC | 121536634 | 014/327 | T2 DI DRUM-GRASS VLY-WMR 14/327 RPL HRDW | SACTO | ETL.6760.POLE.NWOD | 2021-06-14 | 2021-06-10 | 2022-01-24 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45155152 | T2 DI DRUM-GRASS VLY-WMR 14/327 RPL HRDW | ICW
LC | 121536645 | 020/237 | T2 DI DRUM-SUMMIT #1 20/237 INS HRDD | SACTO | ETL.1440.POLE.WDPS | 2021-06-14 | 2021-06-08 | 2022-06-19 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45195998 | T2 DI DRUM-SUMMIT #1 20/237 INS HRDD | ICW
LC | 121536646 | 035/008 | T2 DI MNDO-WLTS-FRT BRAG 35/8 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-14 | 2021-06-11 | 2022-05-15 | 2022-06-11 | 2022-06-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45148597 | T2 DI MNDO-WLTS-FRT BRAG 35/8 RPR STRW | ICW
LC | 121536647 | 009/077 | T2NT DI CRAG VIEW-CASCADE 9/77 RMV STRW | TABLEMTN | ETL.1350.POLE.STPS | 2021-06-14 | 2021-06-08 | 2022-08-04 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2N PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45419645 | T2NT DI CRAG VIEW-CASCADE 9/77 RMV STRW | ICW
LC | 121536649 | 022/152 | T2 DI CARIBOU-TBL MTN 22/152 RPL HRDT | TABLEMTN | ETL.4440.TOWR | 2021-06-14 | 2021-06-10 | 2022-07-06 | 2022-06-10 | 2022-06-10 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45160940 | T2 DI CARIBOU-TBL MTN 22/152 RPL HRDT | ICQ
LC | 121536656 | 005/057 | EI T2 PIT #5-ROUND MTN #2 5/57 COMPLETE | TABLEMTN | ETL.5430.POLE.WOOD | 2021-06-14 | 2021-06-14 | 2022-06-14 | 2022-06-14 | 2022-06-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31547482 | T2 DI PIT #5-ROUND MTN #2 1/18R RPL STRW | 70Y
LC | 121536657 | 005/057 | EI T2 PIT #5-ROUND MTN #2 5/57 COMPLETE | TABLEMTN | ETL.5430.POLE.WOOD | 2021-06-14 | 2021-06-14 | 2022-06-14 | 2022-06-14 | 2022-06-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31547482 | T2 DI PIT #5-ROUND MTN #2 1/18R RPL STRW | 70Y
LC | 121536723 | 038/330 | T2 DI ROUND MTN-COTTONWD 38/330 RPL INSS | TABLEMTN | ETL.5650.TOWR | 2021-06-14 | 2021-06-10 | 2022-08-04 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547626 | T2 DI RND MTN-CTNWD #3 RPL INSS 9TWRS | 93K
LC | 121536738 | 004/045 | T2 EI PIT #5-ROUND MTN #2 4/45L RPL STRW | TABLEMTN | ETL.5430.POLE.WDPS | 2021-06-14 | 2021-06-14 | 2022-06-15 | 2022-06-14 | 2022-06-14 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31547482 | T2 DI PIT #5-ROUND MTN #2 1/18R RPL STRW | 70Y
LC | 121536739 | 007/072 | EI T2 PIT #5-ROUND MTN #2 7/72 RPL STRW | TABLEMTN | ETL.5430.POLE.WDPS | 2021-06-14 | 2021-06-14 | 2022-06-13 | 2022-06-14 | 2022-06-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31601295 | EI T2 PIT #5-ROUND MTN #2 7/72 RPL STRW | 70Y
LC | 121536742 | 020/009 | T2 DI MENDOCINO-WILLITS FB 20/9 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2021-06-14 | 2021-06-10 | 2022-08-23 | 2022-06-10 | 2022-06-10 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31551283 | T2 DI MNDCN-WLTS-FRT BRG 28/10 RPL INSW | 93I
LC | 121536749 | :001/011 | T2 DI FULTON-PUEBLO-WOOD 1/11 RMV STRW | LAKEVLLE | ETL.1600.POLE.WOOD | 2021-06-14 | 2021-06-10 | 2022-02-10 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45149900 | T2 DI FULTON-PUEBLO-WOOD 1/11 RMV STRW | ICW
LC | 121536762 | 100/001 | T2 DI HUMBOLDT-TRINITY 100/1L RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-14 | 2021-06-09 | 2022-03-29 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45094353 | T2 DI HUMBOLDT-TRINITY 100/1L RPR STRW | ICW
LC | 121536771 | 016/162 | T2 DI RND MTN CTTNWD #2 016/162 RPL INSS | TABLEMTN | ETL.5640.INSL | 2021-06-14 | 2021-06-10 | 2022-07-29 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548821 | T2 DI ROUND MTN-CTNWD #2 RPL INSS 5TWRS | 93K
LC | 121536774 | 027/216 | T2 DI PIT #1-CTTND 027/216 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-14 | 2021-06-11 | 2022-02-02 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149512 | T2 DI PIT #1-CTTND 027/216 RPR FOND | ICQ
LC | 121536779 | 013/006 | T2 DI TRINITY-MAPLE CRK 13/6 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2021-06-14 | 2021-06-10 | 2022-12-01 | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45158746 | T2 DI TRINITY-MAPLE CRK 13/6 RPR GYWW | ICW
LC | 121536784 | 021/003 | T2 DI CLEAR LAKE-KONOCTI 21/3 RPL STRW | LAKEVLLE | ETL.6852.POLE.WOOD | 2021-06-14 | 2021-06-09 | 2022-02-05 | 2022-06-09 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541658 | EI CLEAR LAKE-KONOCTI 14/10 RPL STRW | 70Y
LC | 121536790 | :001/011 | T2 DI FULTON-PUEBLO-WOOD 1/11 RPR STRW | LAKEVLLE | ETL.1600.POLE.WOOD | 2021-06-14 | 2021-06-10 | 2022-02-10 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Splice-Wood | Repair | 45149900 | T2 DI FULTON-PUEBLO-WOOD 1/11 RMV STRW | ICW
LC | 121536796 | 047/192 | T2 DI DIBLO-GATS #1 47/192 RMV NEST | PISMOBCH | ETL.5960.TOWR | 2021-06-14 | 2021-06-11 | 2021-09-01 | 2022-06-11 | 2022-06-11 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44960629 | T2 DI DIBLO-GATS #1 47/192 RMV NEST | ICS
LC | 121536821 | 042/362 | T2 DI PIT #1-CTTNWD 42/362 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-14 | 2021-06-11 | 2022-02-25 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149537 | T2 DI PIT #1-CTTNWD 42/362 RPR FOND | ICQ
LC | 121536826 | 034/519 | T2 DI CLAY-MARTEL 34/519 RPR CRSW | VICTOR | ETL.8250.POLE.WOOD | 2021-06-14 | 2021-06-09 | 2022-03-23 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45067237 | T2 DI CLAY-MARTEL 34/519 RPR CRSW | ICW
LC | 121536834 | 031/265 | T2 DI ROUND MTN-CTNWD #2 31/265 INS HRDT | TABLEMTN | ETL.5640.TOWR | 2021-06-14 | 2021-06-10 | 2022-02-10 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45110138 | T2 DI ROUND MTN-CTNWD #2 31/265 INS HRDT | ICQ
LC | 121536860 | 035/000 | T2 DI MNDCN WLTS FT BRG 35/0 RPL HRDD | WILLITS | ETL.7550.POLE.WOOD | 2021-06-14 | 2021-06-10 | 2022-05-12 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45148594 | T2 DI MNDCN WLTS FT BRG 35/0 RPL HRDD | ICW
LC | 121536861 | 035/000 | T2 DI MNDCN WLTS FT BRG 35/0 RPR INSW | WILLITS | ETL.7550.INSL.NCER | 2021-06-14 | 2021-06-10 | 2022-05-12 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45148594 | T2 DI MNDCN WLTS FT BRG 35/0 RPL HRDD | ICW
LC | 121536864 | 015/150 | T2 DI RND MTN CTTNWD #2 15/150 RPL INSS | TABLEMTN | ETL.5640.INSL | 2021-06-14 | 2021-06-11 | 2022-07-28 | 2022-06-11 | 2022-06-11 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548821 | T2 DI ROUND MTN-CTNWD #2 RPL INSS 5TWRS | 93K
LC | 121537885 | 042/357 | T2 DI ROUND-MTN CTNWD #3 42/357 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-15 | 2021-06-10 | 2022-08-05 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547626 | T2 DI RND MTN-CTNWD #3 RPL INSS 9TWRS | 93K
LC | 121537974 | 053/006 | T2 DI HUMBOLT-TRINITY 53/6 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-06-15 | 2021-06-10 | 2022-06-09 | 2022-06-10 | 2022-06-10 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31549298 | T2 DI HUMBOLT-TRINITY 53/6 RPL INSW | 93I
LC | 121538056 | 000/005 | T2 EI MELONES-CURTIS 0/5L RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-06-15 | 2021-06-15 | 2021-11-30 | 2022-06-15 | 2022-06-15 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31551988 | T2 EI MELONES-CURTIS 0/5L RPL STRW | 70Y
LC | 121538121 | 001/017 | T2 EI CHRISTIE-FRANKLIN #1 1/17 RPL ANCW | CONCORD | ETL.6350.POLE.WDPS | 2021-06-15 | 2021-06-15 | 2022-02-26 | 2022-06-15 | 2022-06-15 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31544429 | T2 EI CHRISTIE-FRANKLIN #1 1/17 RPR GYWW | 93E
LC | 121538204 | 037/327 | T2 DI ROUND-MTN CTNWD #3 37/327 COMPLETE | TABLEMTN | ETL.5650.TOWR | 2021-06-15 | 2021-06-11 | 2022-05-24 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45110449 | T2 DI ROUND-MTN CTNWD #3 37/327 RPR FOND | ICQ
LC | 121538289 | 001/017 | T2 EI CHRISTIE-FRANKLIN #1 1/17 RPL ANCW | CONCORD | ETL.6350.POLE.WDPS | 2021-06-15 | 2021-06-15 | 2022-02-26 | 2022-06-15 | 2022-06-15 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31544429 | T2 EI CHRISTIE-FRANKLIN #1 1/17 RPR GYWW | 93E
LC | 121538290 | 060/302 | T2 DI MLN-ROND MTN #2 060/302 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-06-15 | 2021-06-11 | 2022-08-05 | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45193987 | T2 DI MLN-ROND MTN #2 060/302 RPR GYWS | ICS
LC | 121538295 | 094/006 | T2 DI HUMBOLT-TRINITY 94/6 RMV BUTT | EUREKA | ETL.1820.POLE.WDPS | 2021-06-15 | 2021-06-12 | 2022-03-22 | 2022-06-12 | 2022-06-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45160733 | T2 DI HUMBOLT-TRINITY 94/6 RMV BUTT | ICW
LC | 121538348 | 002/021 | T2 EI DIVIDE-VANDENBERG #1 2/21 RPR IBWW | PISMOBCH | ETL.8620.INSL.CERA | 2021-06-15 | 2021-06-15 | 2022-03-15 | 2022-06-15 | 2022-06-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45098713 | T2 EI DIVIDE-VANDENBERG #1 2/21 RPR IBWW | ICW
LC | 121538535 | 002/019 | T2 EI DIVIDE-VANDENBERG #1 2/19 RPR JMPW | PISMOBCH | ETL.8620.INSL.NCER | 2021-06-15 | 2021-06-15 | 2022-03-15 | 2022-06-15 | 2022-06-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Jumper-Wood | Repair | 45098714 | T2 EI DIVIDE-VANDENBERG #1 2/19 RPR JMPW | ICW
LC | 121538699 | 002/017 | T2 EI DIVIDE-VANDENBERG #1 2/17 RPR JMPW | PISMOBCH | ETL.8620.INSL.CERA | 2021-06-15 | 2021-06-15 | 2022-03-15 | 2022-06-15 | 2022-06-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Jumper-Wood | Repair | 45098709 | T2 EI DIVIDE-VANDENBERG #1 2/17 RPR JMPW | ICW
LC | 121538923 | 009/068 | T2 WV ROCK CREEK-POE 9/68 INS JUMP | TABLEMTN | ETL.5630.INSL.NCER | 2021-06-15 | 2021-06-15 | 2022-08-04 | 2022-06-15 | 2022-06-15 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31541441 | T2 DI ROCK CREEK-POE 009/068 RPL INSS | 93K
LC | 121538962 | 045/391 | T2 DI PIT #1 COTTONWOOD 45/391 RPR GYWS | TABLEMTN | ETL.5390.TOWR | 2021-06-15 | 2021-06-11 | 2022-03-04 | 2022-06-11 | 2022-06-11 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45166848 | T2 DI PIT #1 COTTONWOOD 45/391 RPR GYWS | ICS
LC | 121538964 | 009/068 | T2 WV ROCK CREEK-POE 9/68 RPR INSS | TABLEMTN | ETL.5630.INSL.NCER | 2021-06-15 | 2021-06-15 | 2022-08-04 | 2022-06-15 | 2022-06-15 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45442612 | T2 WV ROCK CREEK-POE 9/68 RPR INSS | ICS
LC | 121538988 | 009/068 | T2 WV ROCK CREEK-POE 9/68 INS DAMP | TABLEMTN | ETL.5630.INSL.NCER | 2021-06-15 | 2021-06-15 | 2022-08-04 | 2022-06-15 | 2022-06-15 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install | 45437368 | T2 WV ROCK CREEK-POE 9/68 INS DAMP | ICS
LC | 121539235 | 070/608 | T2 DI CTTNWD-DELEVAN #2 70/608 RPL INSS | TABLEMTN | ETL.4580.INSL.CERA | 2021-06-15 | 2021-06-11 | 2022-06-07 | 2022-06-11 | 2022-06-11 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540712 | T2 EI CTONWD-DELEVAN #2 RPL INSS 9TWRS | 93K
LC | 121539243 | 005/000 | T2 EI MELONES-CURTIS 5/0C RPL POLE | VICTOR | ETL.2390.POLE.WDPS | 2021-06-15 | 2021-06-15 | 2022-11-12 | 2022-06-15 | 2022-06-15 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545148 | T2 EI MELONES-CURTIS 5/0 RPL POLE | 70Y
LC | 121539819 | 051/004 | T2 DI HUMBOLDT-TRINITY 51/4L RPR WDPKR | EUREKA | ETL.1820.POLE.WDPS | 2021-06-15 | 2021-06-10 | 2022-03-27 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45145195 | T2NT DI HUMBOLDT-TRINITY 51/4 RMV BUTT | ICW
LC | 121540000 | 019/003 | T2 DI CLEAR LAKE-KONOCTI 19/3 REFRAME | WILLITS | ETL.6852.POLE.WOOD | 2021-06-15 | 2021-06-09 | 2022-02-02 | 2022-06-09 | 2022-06-09 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31544355 | T2 DI CLEAR LAKE-KONOCTI 19/3 REFRAME | 93E
LC | 121540054 | 021/002 | T2 EI CLR LAKE-KONOCTI 021/002 RPR STRW | WILLITS | ETL.6852.POLE.NWOD | 2021-06-15 | 2021-06-15 | 2022-02-04 | 2022-06-15 | 2022-06-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45138107 | T2 EI CLR LAKE-KONOCTI 021/002 RPR STRW | ICW
LC | 121540153 | 029/211 | T2 DI CARIBOU-TBL MTN 29/211 RPR FOND | TABLEMTN | ETL.4440.TOWR | 2021-06-15 | 2021-06-11 | 2022-01-27 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45108124 | T2 DI CARIBOU-TBL MTN 29/211 RPR FOND | ICQ
LC | 121540156 | 029/211 | T2 DI CARIBOU-TBL MTN 029/21 RPL HRDT | TABLEMTN | ETL.4440.TOWR | 2021-06-15 | 2021-06-11 | 2022-01-27 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45108125 | T2 DI CARIBOU-TBL MTN 029/21 RPL HRDT | ICQ
LC | 121540257 | 014/147 | T2 DI ROUND MTN-CTNWD #2 14/147 RPL INSS | TABLEMTN | ETL.5640.INSL | 2021-06-15 | 2021-06-11 | 2022-07-28 | 2022-06-11 | 2022-06-11 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548821 | T2 DI ROUND MTN-CTNWD #2 RPL INSS 5TWRS | 93K
LC | 121540258 | 032/001 | T2 DI FULTON-HOLAND 32/1 RPR GYWW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-06-15 | 2021-06-10 | 2022-06-22 | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45143970 | T2 DI FULTON-HOLAND 32/1 RPR GYWW | ICW
LC | 121540452 | 039/336 | T2 DI RND MTN-CTNWD #3 39/336 RPR STRT | TABLEMTN | ETL.5650.TOWR | 2021-06-15 | 2021-06-11 | 2022-01-25 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45110453 | T2 DI RND MTN-CTNWD #3 39/336 RPR STRT | ICQ
LC | 121540523 | 022/206 | T2 DI ROUD-MTN CTNWD #2 22/206 RPR INSS | TABLEMTN | ETL.5640.INSL | 2021-06-15 | 2021-06-11 | 2022-07-24 | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45215280 | T2 DI ROUD-MTN CTNWD #2 22/206 RPR INSS | ICS
LC | 121540926 | 000/003 | T2 DI COLGATE-PALERMO 0/3 RPR GYWW | SACTO | ETL.6500.POLE.NWOD | 2021-06-15 | 2021-06-10 | 2022-05-15 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45200304 | T2 DI COLGATE-PALERMO 0/3 RPR GYWW | ICW
LC | 121541554 | 003/027 | T2 DI ROCK CREEK-POE 3/27 RPR FOND | TABLEMTN | ETL.5630.TOWR | 2021-06-15 | 2021-06-11 | 2022-07-22 | 2022-06-11 | 2022-06-11 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195623 | T2 DI ROCK CREEK-POE 3/27 RPR FOND | ICQ
LC | 121541584 | 014/082 | T2 PARKWAY-MORAGA 14/82 RMV VEG | CONCORD | ETL.5930.TOWR | 2021-06-15 | 2021-06-04 | 2022-05-25 | 2022-06-04 | 2022-06-04 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 121541811 | 052/467 | T2 DI PIT #1 CTNWD 52/467 RPR GYWS | TABLEMTN | ETL.5390.TOWR | 2021-06-15 | 2021-06-10 | 2022-02-16 | 2022-06-10 | 2022-06-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45166854 | T2 DI PIT #1 CTNWD 52/467 RPR GYWS | ICS
LC | 121541865 | 052/467 | T2 DI PIT #1 CTNWD 52/467 RPL HRDS | TABLEMTN | ETL.5390.TOWR | 2021-06-15 | 2021-06-10 | 2022-02-16 | 2022-06-10 | 2022-06-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Steel | Replace | 45166855 | T2 DI PIT #1 CTNWD 52/467 RPL HRDS | ICS
LC | 121541886 | 001/018 | T2 DI ROCK CREEK-POE 1/18 RPR STRT | TABLEMTN | ETL.5630.TOWR | 2021-06-15 | 2021-06-11 | 2022-02-10 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45159489 | T2 DI ROCK CREEK-POE 1/18 RPR STRT | ICQ
LC | 121541952 | 003/028 | T2 DI ROCK CREEK-POE 3/28 RPR FOND | TABLEMTN | ETL.5630.TOWR | 2021-06-15 | 2021-06-11 | 2022-07-08 | 2022-06-11 | 2022-06-11 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195622 | T2 DI ROCK CREEK-POE 3/28 RPR FOND | ICQ
LC | 121542073 | R002/020 | T2 DI RND MTN-COTTONWD #3 R2/20 RPR JUMS | TABLEMTN | ETL.5650.INSL.NCER | 2021-06-15 | 2021-06-11 | 2022-08-07 | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Jumper-Steel | Repair | 45147347 | T2 DI RND MTN-COTTONWD #3 R2/20 RPR JUMS | ICS
LC | 121542136 | 070/610 | T2 DI CTTNWD-GLENN 70/610 RPL INSS | TABLEMTN | ETL.4560.INSL | 2021-06-15 | 2021-06-12 | 2022-03-30 | 2022-06-12 | 2022-06-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534508 | DI COTTONWOOD-GLENN RPLC INSS 7TWRS | 93K
LC | 121542241 | 018/099 | T2 DI TESLA-NEWARK #1 018/099 RPR SHLS | CONCORD | ETL.5720.TOWR | 2021-06-15 | 2021-06-11 | 2021-09-30 | 2022-06-11 | 2022-06-11 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44959070 | T2 DI TESLA-NEWARK #1 018/099 RPR SHLS | ICS
LC | 121542302 | 012/105 | T2 DI CRAG VIEW-CASCADE 12/105 RPR SHLS | TABLEMTN | ETL.1350.POLE.STPS | 2021-06-15 | 2021-06-15 | 2022-09-15 | 2022-06-15 | 2022-06-15 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45436130 | T2 DI CRAG VIEW-CASCADE 12/105 RPR SHLS | ICS
LC | 121542363 | :001/006 | T2 DI FULTON-PUEBLO :001/006 RMV DEBRIS | LAKEVLLE | ETL.1600.POLE.WOOD | 2021-06-15 | 2021-06-12 | 2022-02-10 | 2022-06-12 | 2022-06-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45147866 | T2 DI FULTON-PUEBLO :001/006 RMV DEBRIS | ICW
LC | 121542406 | 003/047 | T2 DI COLGATE-PALERMO 3/47 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2021-06-15 | 2021-06-10 | 2022-05-21 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45200305 | T2 DI COLGATE-PALERMO 3/47 RPR STRW | ICW
LC | 121542521 | 040/341 | T2 DI PIT #1-COTTONWOOD 040/341 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-15 | 2021-06-10 | 2022-03-01 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149533 | T2 DI PIT #1-COTTONWOOD 040/341 RPR FOND | ICQ
LC | 121542640 | :000/011 | T2 DI BLTA-RVBK-MLN SWST :0/11 RPR GYWW | VICTOR | ETL.1070.POLE.WOOD | 2021-06-15 | 2021-06-12 | 2022-04-14 | 2022-06-12 | 2022-06-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45156982 | T2 DI BLTA-RVBK-MLN SWST :0/11 RPR GYWW | ICW
LC | 121542662 | 037/321 | T2 DI PIT #1-COTTONWOOD 37/321 COMPLETE | TABLEMTN | ETL.5390.TOWR | 2021-06-15 | 2021-06-11 | 2022-05-24 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45149529 | T2 DI PIT #1-COTTONWOOD 37/321 RPR FOND | ICQ
LC | 121542828 | 036/008 | T2DI MENDO-WLTS-FRT BRG 36/8 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-15 | 2021-06-10 | 2022-05-13 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45148605 | T2DI MENDO-WLTS-FRT BRG 36/8 RPR STRW | ICW
LC | 121542876 | :000/008 | T2 DI BLTA-RVBK-MLN SWSTA :0/8 BOND COA | VICTOR | ETL.1070.POLE.WOOD | 2021-06-15 | 2021-06-12 | 2022-04-14 | 2022-06-12 | 2022-06-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45156984 | T2 DI BLTA-RVBK-MLN SWSTA :0/8 RPR GYWW | ICW
LC | 121542999 | 034/008 | T2 DI MNDCN-WLTS-FRT BRG 34/8 RPR GYWW | WILLITS | ETL.7550.POLE.NWOD | 2021-06-15 | 2021-06-10 | 2022-05-12 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148593 | T2 DI MNDCN-WLTS-FRT BRG 34/8 RPR GYWW | ICW
LC | 121543113 | 024/290A | T2 DI DRUM-SUMMIT #1 24/290A RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2021-06-15 | 2021-06-12 | 2022-09-18 | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581111 | T2 DI DRUM-SUMMIT #1 19/220 RPL STRW | 70Y
LC | 121543142 | 026/213 | T2 DI PIT #1-COTTONWOOD 26/213 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-15 | 2021-06-11 | 2022-01-31 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149510 | T2 DI PIT #1-COTTONWOOD 26/213 RPR FOND | ICQ
LC | 121543207 | 016/139 | T2 DI CRAG VIEW-CASCADE 16/139 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-15 | 2021-06-09 | 2022-09-12 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31552992 | T2 EI CRAG VIEW-CASCDE 18/154R RPL STRW | 70Y
LC | 121543209 | 012/250 | T2 DI COTTONWD-RED BLUFF 12/250 RPR GYWW | TABLEMTN | ETL.6660.POLE.WOOD | 2021-06-15 | 2021-06-09 | 2022-09-29 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45242431 | T2 DI COTTONWD-RED BLUFF 12/250 RPR GYWW | ICW
LC | 121543214 | 002/037 | T2 DI SMARTVILLE-NICLS 2/37 RPL STRW | SACTO | ETL.7990.POLE.WOOD | 2021-06-15 | 2021-06-12 | 2022-08-20 | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548078 | T2 DI SMRTSVLLE NCLS #1 000/002 RPL STRW | 70Y
LC | 121543314 | 016/362 | T2 DI DRM-GRS VLY-WMR 16/362 RMV STUB | SACTO | ETL.6760.POLE.WOOD | 2021-06-15 | 2021-06-10 | 2022-07-16 | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44944956 | T2 DI DRM-GRS VLY-WMR 16/362 RMV STUB | ICW
LC | 121543483 | 037/319 | T2 DI PIT #1-COTTONWOOD 37/319 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-15 | 2021-06-11 | 2022-08-02 | 2022-06-11 | 2022-06-11 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45149528 | T2 DI PIT #1-COTTONWOOD 37/319 RPR FOND | ICQ
LC | 121543644 | 018/098 | T2 DI TESLA-NEWARK #1 18/98 RPL INSS | CONCORD | ETL.5720.INSL | 2021-06-15 | 2021-06-12 | 2021-09-30 | 2022-06-12 | 2022-06-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31550838 | T2 DI TESLA-NEWARK #1 RPL INSS 2TWRS | 93K
LC | 121543645 | 012/141C | T2 DI DRUM-SUMMIT #1 012/141C RPR STRW | SACTO | ETL.1440.POLE.WOOD | 2021-06-15 | 2021-06-12 | 2022-06-27 | 2022-06-12 | 2022-06-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45200312 | T2 DI DRUM-SUMMIT #1 012/141C RPR STRW | ICW
LC | 121543649 | 001/023 | T2 DI SMRTSVLL-NCLS #1 1/23 RPR STRW | SACTO | ETL.7990.POLE.WOOD | 2021-06-15 | 2021-06-12 | 2022-08-22 | 2022-06-12 | 2022-06-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45233330 | T2 DI SMRTSVLL-NCLS #1 1/23 RPR STRW | ICW
LC | 121543699 | 024/290B | T2 DI DRUM-SUMMIT #1 24/290B RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2021-06-15 | 2021-06-12 | 2022-09-18 | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581111 | T2 DI DRUM-SUMMIT #1 19/220 RPL STRW | 70Y
LC | 121543717 | 000/001 | T2 DI COLGATE-PALERMO 0/1 COMPLETE | SACTO | ETL.6500.POLE.WOOD | 2021-06-15 | 2021-06-10 | 2022-05-15 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44883224 | T2 DI COLGATE-PALERMO 0/1 RPR STRW | ICW
LC | 121543718 | 000/001 | T2 DI COLGATE-PALERMO 0/1 RPR GYWW | SACTO | ETL.6500.POLE.WOOD | 2021-06-15 | 2021-06-10 | 2022-05-15 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44883223 | T2 DI COLGATE-PALERMO 0/1 RPR GYWW | ICW
LC | 121543721 | 006/030 | T2 DI SILVERADO-FULTON JCT 6/30 RPL INSS | LAKEVLLE | ETL.1610.INSL | 2021-06-15 | 2021-06-10 | 2022-03-08 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548682 | T2 DI SILVERADO-FULTON JCT RPL INSS 6TWR | 93K
LC | 121543723 | 006/030 | T2 DI SILVERADO-FULTON JCT 6/30 RPL HNGR | LAKEVLLE | ETL.1610.INSL | 2021-06-15 | 2021-06-10 | 2022-03-08 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 45142557 | T2 DI SILVERADO-FULTON JCT 6/30 RPL HNGR | ICQ
LC | 121543727 | 009/074A | T2 DI PIT #1-COTTNWD 9/74A RMV NEST | TABLEMTN | ETL.5390.TOWR | 2021-06-15 | 2021-06-10 | 2022-03-04 | 2022-06-10 | 2022-06-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45197219 | T2 DI PIT #1-COTTNWD 9/74A RMV NEST | ICS
LC | 121543728 | 096/006 | T2 DI HUMBOLDT-TRINITY 96/6 RPR STRW | EUREKA | ETL.1820.POLE.STPS | 2021-06-15 | 2021-06-12 | 2022-03-22 | 2022-06-12 | 2022-06-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45160749 | T2 DI HUMBOLDT-TRINITY 96/6 RPR STRW | ICW
LC | 121543757 | 026/214 | T2 DI PIT #1-COTTONWOOD 26/214 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-15 | 2021-06-11 | 2022-01-31 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149511 | T2 DI PIT #1-COTTONWOOD 26/214 RPR FOND | ICQ
LC | 121543811 | 025/005 | T2 DI MNDCN WLTS FT BRG 25/5 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-06-15 | 2021-06-12 | 2022-08-13 | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31540800 | EI MNDCN-WLLTS-FRT BRGG :0/10 REFRAME | 93E
LC | 121543816 | 107/005 | T2 DI HUMBOLDT-TRINITY 107/5R RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-15 | 2021-06-10 | 2022-01-24 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45128330 | T2 DI HUMBOLDT-TRINITY 107/5R RPR STRW | ICW
LC | 121543818 | 107/005 | T2 DI HUMBOLDT-TRINITY 107/5 RPL INSW | EUREKA | ETL.1820.INSL.NCER | 2021-06-15 | 2021-06-10 | 2022-01-24 | 2022-06-10 | 2022-06-10 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542141 | T2 EI HUMBOLDT-TRINITY 91/3 RPL INSW | 93I
LC | 121543819 | 002/020 | T2 DI ROCK CREEK-POE 2/20 RPLC INSS | TABLEMTN | ETL.5630.TOWR | 2021-06-15 | 2021-06-11 | 2022-08-06 | 2022-06-11 | 2022-06-11 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551263 | T3 DI ROCK CREEK-POE RPL INSS 9TWRS | 93K
LC | 121543830 | 035/301 | T2 DI PIT #1-COTTONWOOD 35/301 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-15 | 2021-06-11 | 2022-08-02 | 2022-06-11 | 2022-06-11 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45198316 | T2 DI PIT #1-COTTONWOOD 35/301 RPR FOND | ICQ
LC | 121543833 | 009/061 | T2 DI COTTONWD-DLVN #1 9/61 RMV STEP | TABLEMTN | ETL.4550.TOWR | 2021-06-15 | 2021-06-12 | 2022-01-03 | 2022-06-12 | 2022-06-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45098658 | T2 DI COTTONWD-DLVN #1 9/61 RMV STEP | ICQ
LC | 121543835 | 009/061 | T2 DI COTTONWOOD-DLVN #1 9/61 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-06-15 | 2021-06-12 | 2022-05-22 | 2022-06-12 | 2022-06-12 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45240549 | T2 DI COTTONWOOD-DLVN #1 9/61 RPR OPGW | ICS
LC | 121543882 | 045/390 | T2 DI RND MTN-CTTNWD #3 45/390 INS HRDT | TABLEMTN | ETL.5650.TOWR | 2021-06-15 | 2021-06-11 | 2022-01-26 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45110546 | T2 DI RND MTN-CTTNWD #3 45/390 INS HRDT | ICQ
LC | 121543977 | 037/322 | T2 DI PIT #1-COTTONWOOD 37/322 COMPLETE | TABLEMTN | ETL.5390.TOWR | 2021-06-15 | 2021-06-11 | 2022-05-24 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45198318 | T2 DI PIT #1-COTTONWOOD 37/322 RPR FOND | ICQ
LC | 121543990 | 001/026 | T2 DI SMRTSVLLE-NCLS #1 1/26 RPL STRW | SACTO | ETL.7990.POLE.WOOD | 2021-06-15 | 2021-06-12 | 2022-08-15 | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548078 | T2 DI SMRTSVLLE NCLS #1 000/002 RPL STRW | 70Y
LC | 121544145 | 033/003 | T2 DI MNDCN WLTS FT BRG 33/3 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-15 | 2021-06-10 | 2022-10-02 | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45148587 | T2 DI MNDCN WLTS FT BRG 33/3 RPR STRW | ICW
LC | 121544147 | 016/126 | T2 DI PIT #1 COTTNWD 16/126 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-15 | 2021-06-10 | 2022-07-20 | 2022-06-10 | 2022-06-10 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149406 | T2 DI PIT #1 COTTNWD 16/126 RPR FOND | ICQ
LC | 121544149 | 009/078 | T2 DI PIT #1 COTTNWD 9/78 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-15 | 2021-06-10 | 2022-02-17 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149402 | T2 DI PIT #1 COTTNWD 9/78 RPR FOND | ICQ
LC | 121544178 | :000/007 | T2 DI BLTA RVK MLNS SS :000/7 RPR STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-06-15 | 2021-06-12 | 2022-04-14 | 2022-06-12 | 2022-06-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45156985 | T2 DI BLTA RVK MLNS SS :000/7 RPR STRW | ICW
LC | 121544212 | 028/204A | T2 DI CARIBU-TABLE MTN 28/204A RPL HNGR | TABLEMTN | ETL.4440.POLE.NWOD | 2021-06-15 | 2021-06-11 | 2021-09-10 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 121544213 | 028/204A | T2 DI CARIBU-TABLE MTN 28/204A RPL INSS | TABLEMTN | ETL.4440.INSL | 2021-06-15 | 2021-06-11 | 2021-09-10 | 2022-06-11 | 2022-06-11 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121544218 | 028/204C | T2 DI CARIBOU-TABL MTN 28/204C RPL HNGR | TABLEMTN | ETL.4440.INSL.NCER | 2021-06-15 | 2021-06-11 | 2021-09-10 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 45100153 | T2 DI CARIBOU-TABL MTN 28/204C RPL HNGR | ICQ
LC | 121544219 | 028/204C | T2 DI CARIBOU-TABL MTN 28/204C RPL INSS | TABLEMTN | ETL.4440.INSL.NCER | 2021-06-15 | 2021-06-11 | 2021-09-10 | 2022-06-11 | 2022-06-11 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121544221 | :001/005 | T2 DI BLTA RVK MLNS SS :001/005 RPR STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-06-15 | 2021-06-11 | 2022-04-16 | 2022-06-11 | 2022-06-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45156986 | T2 DI BLTA RVK MLNS SS :001/005 RPR STRW | ICW
LC | 121544654 | C009/037 | T2 DI MSS LNDNG-COBRN C009/037 RPL INSS | MOSSLNDG | ETL.5330.INSL | 2021-06-16 | 2021-06-15 | 2022-04-17 | 2022-06-15 | 2022-06-15 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31550478 | DI MOSS LANDING-COBURN RPL INSS 6TWR | 93K
LC | 121544718 | 002/049 | T2 DI SMRTVLLE-NCLS #1 2/49 COMPLETE | SACTO | ETL.7990.POLE.WOOD | 2021-06-16 | 2021-06-12 | 2022-05-09 | 2022-06-12 | 2022-06-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45233394 | T2 DI SMRTVLLE-NCLS #1 2/49 RPR GYWW | ICW
LC | 121544875 | 006/066 | T2 EI PT NO. 5-RND MTN #1 6/66L RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-16 | 2021-06-14 | 2022-07-17 | 2022-06-14 | 2022-06-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45212838 | T2 EI PT NO. 5-RND MTN #1 6/66L RPR STRW | ICW
LC | 121544877 | 005/060 | T2 EI PIT #5 - RND MTN #1 5/60L RPL STRW | TABLEMTN | ETL.5420.POLE.WOOD | 2021-06-16 | 2021-06-14 | 2022-07-14 | 2022-06-14 | 2022-06-14 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121544878 | 004/048 | T2 EI PIT #5 RND MN #1 4/48L RMV DEBRIS | TABLEMTN | ETL.5420.POLE.STPS | 2021-06-16 | 2021-06-13 | 2022-06-10 | 2022-06-13 | 2022-06-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45212839 | EI T2 PIT #5 - RND MTN #1 RMV DEBRIS | ICW
LC | 121544879 | 006/065 | EI T2 PIT #5 - RND MTN #1 6/65 RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-16 | 2021-06-14 | 2022-07-15 | 2022-06-14 | 2022-06-14 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121544941 | 001/015 | EI T2 PIT #6 TAP 1/15 RPR STRW | TABLEMTN | ETL.5441.POLE.WDPS | 2021-06-16 | 2021-06-15 | 2022-06-09 | 2022-06-15 | 2022-06-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45213833 | EI T2 PIT #6 TAP 1/15 RPR STRW | ICW
LC | 121544945 | 004/050 | T2 EI PIT #5 - RND MTN #1 4/50R RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-16 | 2021-06-14 | 2022-07-01 | 2022-06-14 | 2022-06-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45212904 | EI T2 PIT #5 - RND MTN #1 4/50 RPR STRW | ICW
LC | 121544947 | 004/050 | T2 EI PIT #5 - RND MTN #1 4/50L RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-16 | 2021-06-14 | 2022-07-01 | 2022-06-14 | 2022-06-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45212906 | EI T2 PIT #5 - RND MTN #1 4/50 RPR STRW | ICW
LC | 121544952 | 004/042 | EI T2 PIT #5 - RND MTN #1 4/42 RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-16 | 2021-06-13 | 2022-07-17 | 2022-06-13 | 2022-06-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45212909 | EI T2 PIT #5 - RND MTN #1 4/42 RPR STRW | ICW
LC | 121544957 | 004/046 | EI T2 PIT #5 - RND MTN #1 4/46 RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-16 | 2021-06-13 | 2022-07-01 | 2022-06-13 | 2022-06-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45212912 | EI T2 PIT #5 - RND MTN #1 4/46 RPR STRW | ICW
LC | 121545290 | 000/002 | T2 DI PIT#3-PIT#1 000/002 RMV VEG | TABLEMTN | ETL.5400.TOWR | 2021-06-16 | 2021-06-13 | 2022-09-07 | 2022-06-13 | 2022-06-13 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121545296 | 028/204B | T2 DI CARIBOU-TBL MTN 20/204B RPLC HNGR | TABLEMTN | ETL.4440.INSL.NCER | 2021-06-16 | 2021-06-11 | 2021-09-10 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44983299 | T2 DI CARIBOU-TBL MTN 20/204B RPLC HNGR | ICQ
LC | 121545299 | 028/204B | T2 DI CARIBOU-TBL MTN 20/204B RPLC INSS | TABLEMTN | ETL.4440.INSL.NCER | 2021-06-16 | 2021-06-11 | 2021-09-10 | 2022-06-11 | 2022-06-11 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121545304 | 007/050 | T2 DI CTTNWD-DLVN #1 7/50 RPR FOND | TABLEMTN | ETL.4550.TOWR | 2021-06-16 | 2021-06-11 | 2021-12-22 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45097431 | T2 DI CTTNWD-DLVN #1 7/50 RPR FOND | ICQ
LC | 121545308 | 007/050 | T2 DI CTTNWD-DLVN #1 7/50 RPL DAMS | TABLEMTN | ETL.4550.INSL | 2021-06-16 | 2021-06-11 | 2022-06-10 | 2022-06-11 | 2022-06-11 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 45147348 | T2 DI CTTNWD-DLVN #1 7/50 RPL DAMS | ICS
LC | 121545445 | 004/056 | EI T2 GREEN VLEY-CMP EVRS 4/56 RPL INSW | MOSSLNDG | ETL.1710.INSL.CERA | 2021-06-16 | 2021-06-16 | 2022-04-14 | 2022-06-16 | 2022-06-16 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537552 | EI GREEN VALLEY-CAMP EVERS 3/46 RPL INSW | 93I
LC | 121545520 | 007/050 | T2 DI CTTNWD-DLVN #1 7/50 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-06-16 | 2021-06-11 | 2022-06-10 | 2022-06-11 | 2022-06-11 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45147350 | T2 DI CTTNWD-DLVN #1 7/50 RPR SHLS | ICS
LC | 121545525 | 013/099 | T2 DI CARIBOU-TABLE MTN 13/99 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-16 | 2021-06-16 | 2022-06-22 | 2022-06-16 | 2022-06-16 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121545747 | 045/388 | T2 DI ROUD-MTN CTNWD #3 045/388 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-16 | 2021-06-13 | 2022-08-04 | 2022-06-13 | 2022-06-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548264 | T2 DI ROUD-MTN CTNWD #3 RPL INSS 8TWRS | 93K
LC | 121546071 | 029/119 | T2 DI DIABLO-MIDWAY #2 029/119 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-06-16 | 2021-06-11 | 2022-06-03 | 2022-06-11 | 2022-06-11 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068548 | T2 DI DIABLO-MIDWAY #2 029/119 RPR GYWS | ICS
LC | 121546156 | 004/039 | T2 EI DELTA-CASCADE 4/39L RPR STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-06-16 | 2021-06-16 | 2022-07-24 | 2022-06-16 | 2022-06-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44947139 | T2 EI DELTA-CASCADE 4/39 RPR STRW | ICW
LC | 121546314 | 005/070 | T2 EI HT CRK #1-PT #1 5/70L RPL HRDD | TABLEMTN | ETL.7020.POLE.WDPS | 2021-06-16 | 2021-06-16 | 2022-07-25 | 2022-06-16 | 2022-06-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45215254 | T2 EI HT CRK #1-PT #1 5/70 RPL HRDD | ICW
LC | 121546316 | 005/071 | T2 EI HT CRK #1-PT #1 5/71L RPL STRW | TABLEMTN | ETL.7020.POLE.WDPS | 2021-06-16 | 2021-06-16 | 2022-07-25 | 2022-06-16 | 2022-06-16 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544410 | T2 EI HT CRK #1-PT #1 5/71 RPL POLE | 70Y
LC | 121546522 | 011/044 | T2 DI DIABLO-MIDWAY #2 011/044 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-06-16 | 2021-06-11 | 2022-06-16 | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Replace | 45068549 | T2 DI DIABLO-MIDWAY #2 011/044 RPR GYWS | ICS
LC | 121546688 | 037/161 | T2 DI FULTON-LAKEVILLE 037/161 RMV NEST | LAKEVLLE | ETL.4950.TOWR | 2021-06-16 | 2021-06-16 | 2022-06-23 | 2022-06-16 | 2022-06-16 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45144132 | T2 DI FULTON-LAKEVILLE 037/161 RMV NEST | ICS
LC | 121546798 | 010/094 | DI T2 CRAG VIEW-CASCADE 10/94C RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-16 | 2021-06-10 | 2022-09-29 | 2022-06-10 | 2022-06-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121546799 | 010/094 | DI T2 CRAG VIEW-CASCADE 10/94L RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-16 | 2021-06-10 | 2022-09-29 | 2022-06-10 | 2022-06-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121546860 | 010/094 | DI T2 CRAG VIEW-CASCADE 10/94 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-16 | 2021-06-10 | 2022-09-29 | 2022-06-10 | 2022-06-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121547121 | 036/006 | T2 DI MDCN-WLLTS-FORT BRGG 36/6 RPR GYWW | WILLITS | ETL.7550.POLE.NWOD | 2021-06-16 | 2021-06-10 | 2022-08-18 | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148603 | T2 DI MDCN-WLLTS-FORT BRGG 36/6 RPR GYWW | ICW
LC | 121547165 | 038/251C | T2 DI TRINITY-CTNWD 38/251C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2021-06-16 | 2021-06-12 | 2022-06-24 | 2022-06-12 | 2022-06-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45212048 | T2 DI TRINITY-CTNWD 38/251C RPR GYWW | ICW
LC | 121547224 | 038/251B | T2 DI TRINITY-CTNWD 38/251B GYWW CMPLTD | TABLEMTN | ETL.4040.POLE.NWOD | 2021-06-16 | 2021-06-12 | 2022-06-24 | 2022-06-12 | 2022-06-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45212049 | T2 DI TRINITY-CTNWD 38/251B RPR GYWW | ICW
LC | 121547226 | 007/088A | T2 DI DRUM-SUMMIT #1 7/88A RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2021-06-16 | 2021-06-12 | 2022-06-25 | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581111 | T2 DI DRUM-SUMMIT #1 19/220 RPL STRW | 70Y
LC | 121547302 | 023/273 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-16 | 2021-06-16 | 2022-08-26 | 2022-06-16 | 2022-06-16 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121547315 | 023/273 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-16 | 2021-06-16 | 2022-08-31 | 2022-06-16 | 2022-06-16 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121547357 | 003/034 | T2 EI MTN GATE JCT CSCDE 3/34L RPL STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-06-16 | 2021-06-16 | 2022-08-09 | 2022-06-16 | 2022-06-16 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31547477 | T2 DI MTN GTE JCT CSCD 000/006 RPL STRW | 70Y
LC | 121547422 | 007/088B | T2 DI DRUM-SUMMIT #1 7/88B RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2021-06-16 | 2021-06-12 | 2022-06-29 | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581111 | T2 DI DRUM-SUMMIT #1 19/220 RPL STRW | 70Y
LC | 121547451 | 003/034 | T2 EI MTN GATE JCT CSCDE 3/34R RPL STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-06-16 | 2021-06-16 | 2022-08-09 | 2022-06-16 | 2022-06-16 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31547477 | T2 DI MTN GTE JCT CSCD 000/006 RPL STRW | 70Y
LC | 121547491 | 006/004 | EI T2 FORT SEWARD TAP 6/4 RPL STRW | EUREKA | ETL.6222.POLE.WDPS | 2021-06-16 | 2021-06-14 | 2022-05-26 | 2022-06-14 | 2022-06-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544934 | EI T2 FORT SEWARD TAP 6/4 RPL STRW | 70Y
LC | 121547497 | 006/004 | EI T2 FORT SEWARD TAP 6/4 RPL STRW | EUREKA | ETL.6222.POLE.WDPS | 2021-06-16 | 2021-06-14 | 2022-05-26 | 2022-06-14 | 2022-06-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544934 | EI T2 FORT SEWARD TAP 6/4 RPL STRW | 70Y
LC | 121547500 | 006/004 | EI T2 FORT SEWARD TAP 6/4 RPL STRW | EUREKA | ETL.6222.POLE.WDPS | 2021-06-16 | 2021-06-14 | 2022-05-26 | 2022-06-14 | 2022-06-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544934 | EI T2 FORT SEWARD TAP 6/4 RPL STRW | 70Y
LC | 121547767 | 004/033 | T2 DI PIT#3-PIT#1 004/033 RPL HRDT | TABLEMTN | ETL.5400.INSL | 2021-06-16 | 2021-06-13 | 2022-07-26 | 2022-06-13 | 2022-06-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 45198320 | T2 DI PIT#3-PIT#1 004/033 RPL HRDT | ICQ
LC | 121547776 | 003/033 | T2 EI MTN GATE JCT CSCD 3/33L RPL PL | TABLEMTN | ETL.7640.POLE.WDPS | 2021-06-16 | 2021-06-16 | 2022-08-09 | 2022-06-16 | 2022-06-16 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31547477 | T2 DI MTN GTE JCT CSCD 000/006 RPL STRW | 70Y
LC | 121547908 | 007/088C | T2 DI DRUM-SUMMIT #1 7/88C RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2021-06-16 | 2021-06-12 | 2022-06-25 | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581111 | T2 DI DRUM-SUMMIT #1 19/220 RPL STRW | 70Y
LC | 121547998 | 045/388 | T2 DI PIT#1-COTTONWOOD 45/388 RPL HRDT | TABLEMTN | ETL.5390.TOWR | 2021-06-16 | 2021-06-13 | 2022-03-04 | 2022-06-13 | 2022-06-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45149564 | T2 DI PIT#1-COTTONWOOD 45/388 RPL HRDT | ICQ
LC | 121548095 | 003/032 | T2 EI MTN GT JCT CSCD 3/32L RPL ANCW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-06-16 | 2021-06-16 | 2022-08-10 | 2022-06-16 | 2022-06-16 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31544736 | T2 EI MTN GT JCT CSCD 3/32R RPL ANCW | 93E
LC | 121548128 | 025/299 | T2 DI DRUM-SUMMIT #2 25/299R RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2021-06-16 | 2021-06-04 | 2022-10-02 | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121548178 | 003/032 | T2 EI MTN GT JCT CSCD 3/32R RPL ANCW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-06-16 | 2021-06-16 | 2022-08-10 | 2022-06-16 | 2022-06-16 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31544736 | T2 EI MTN GT JCT CSCD 3/32R RPL ANCW | 93E
LC | 121548265 | 038/166 | T2 DI FULTON-LAKEVILLE 38/166 RPR INSS | LAKEVLLE | ETL.4950.INSL | 2021-06-16 | 2021-06-11 | 2022-06-22 | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45144135 | T2 DI FULTON-LAKEVILLE 38/166 RPR INSS | ICS
LC | 121548380 | 012/099 | T2 DI PIT#1-COTTONWOOD 012/099 RMV NEST | TABLEMTN | ETL.5390.TOWR | 2021-06-16 | 2021-06-13 | 2022-03-10 | 2022-06-13 | 2022-06-13 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45197281 | T2 DI PIT#1-COTTONWOOD 012/099 RMV NEST | ICS
LC | 121548383 | 067/592 | T2 DI CTTNWD-DELEVAN #2 067/592 RPR FOND | TABLEMTN | ETL.4580.TOWR | 2021-06-16 | 2021-06-11 | 2022-01-10 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45107496 | T2 DI CTTNWD-DELEVAN #2 067/592 RPR FOND | ICQ
LC | 121548425 | 067/592 | T2 DI CTTNWD-GLENN 67/592 RPL INSS | TABLEMTN | ETL.4560.INSL | 2021-06-16 | 2021-06-11 | 2022-03-30 | 2022-06-11 | 2022-06-11 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Steel | Replace
LC | 121548430 | 024/005 | T2 DI MNDCN-WLLTS-FRT BRGG 24/5 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2021-06-16 | 2021-06-12 | 2022-05-21 | 2022-06-12 | 2022-06-12 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31551283 | T2 DI MNDCN-WLTS-FRT BRG 28/10 RPL INSW | 93I
LC | 121548462 | 067/592 | T2 DI CTTNWD-DELEVAN #2 067/592 RPL HRDT | TABLEMTN | ETL.4580.TOWR | 2021-06-16 | 2021-06-11 | 2022-01-10 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45107497 | T2 DI CTTNWD-DELEVAN #2 067/592 RPL HRDT | ICQ
LC | 121548562 | 009/076 | T2 DI PIT #3-PIT #1 9/76 RMV NEST | TABLEMTN | ETL.5400.TOWR | 2021-06-16 | 2021-06-11 | 2022-10-11 | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove | 45213895 | T2 DI PIT #3-PIT #1 9/76 RMV NEST | ICS
LC | 121549011 | 021/295B | T2 EI SSQC-SNT YNZ SW ST 21/295B RPL STR | PISMOBCH | ETL.3700.POLE.WOOD | 2021-06-16 | 2021-06-16 | 2022-05-20 | 2022-06-16 | 2022-06-16 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544433 | T2 DI SSQC-SNT YNZ SW 21/295C RPL STRW | 70Y
LC | 121549013 | 021/295A | T2 EI SQC-SNT NZ 21/295A RPL STRW CMPLTD | PISMOBCH | ETL.3700.POLE.WOOD | 2021-06-16 | 2021-06-16 | 2022-05-20 | 2022-06-16 | 2022-06-16 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544433 | T2 DI SSQC-SNT YNZ SW 21/295C RPL STRW | 70Y
LC | 121549421 | 009/130 | T2 EI DLTA-MTN GATE JCT 9/130 RPR GYWW | TABLEMTN | ETL.6750.POLE.WOOD | 2021-06-16 | 2021-06-16 | 2022-08-21 | 2022-06-16 | 2022-06-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296374 | T2 EI DLTA-MTN GATE JCT 9/130 RPR GYWW | ICW
LC | 121549451 | 009/130 | T2 EI DLTA-MTN GATE JCT 9/130 RPR GYWW | TABLEMTN | ETL.6750.POLE.WOOD | 2021-06-16 | 2021-06-16 | 2022-08-21 | 2022-06-16 | 2022-06-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296372 | T2 EI DLTA-MTN GATE JCT 9/130 RPR GYWW | ICW
LC | 121549597 | 009/129 | T2 EI DLTA-MTN GATE JCT 9/129 RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-16 | 2021-06-16 | 2022-08-22 | 2022-06-16 | 2022-06-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296371 | T2 EI DLTA-MTN GATE JCT 9/129 RPR GYWW | ICW
LC | 121549605 | 009/129 | T2 EI DLTA-MTN GATE JCT 9/129 RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-16 | 2021-06-16 | 2022-08-22 | 2022-06-16 | 2022-06-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296745 | T2 EI DLTA-MTN GATE JCT 9/129 RPR GYWW | ICW
LC | 121549612 | 048/001B | T2 DI HUMBOLDT-TRINITY 048/001B RMV DBRS | EUREKA | ETL.1820.POLE.NWOD | 2021-06-16 | 2021-06-12 | 2022-03-27 | 2022-06-12 | 2022-06-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45145183 | T2 DI HUMBOLDT-TRINITY 48/1A RMV BUTT | ICW
LC | 121549671 | 009/129 | T2 EI DLTA-MTN GATE JCT 9/129 RPR WDPKR | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-16 | 2021-06-16 | 2022-08-22 | 2022-06-16 | 2022-06-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45296747 | T2 EI DLTA-MTN GATE JCT 9/129 RPR WDPKR | ICW
LC | 121549768 | 064/319 | T2 DI MLN-RND MTN #2 64/319 COMPLETED | TABLEMTN | ETL.6020.TOWR | 2021-06-16 | 2021-06-12 | 2022-08-05 | 2022-06-12 | 2022-06-12 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45449539 | T2 DI MLN-RND MTN #2 64/319 COMPLETED | ICS
LC | 121549769 | 064/319 | T2 DI MALIN-ROUND MTN #2 64/319 RPR FOND | TABLEMTN | ETL.6020.TOWR | 2021-06-16 | 2021-06-12 | 2022-08-03 | 2022-06-12 | 2022-06-12 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45194349 | T2 DI MALIN-ROUND MTN #2 64/319 RPR FOND | ICQ
LC | 121549856 | 002/028 | T2 EI MTN GATE JCT-CSCDE 2/28L COMPLETE | TABLEMTN | ETL.7640.POLE.WDPS | 2021-06-16 | 2021-06-16 | 2022-04-27 | 2022-06-16 | 2022-06-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45354985 | T2 EI MTN GATE JCT-CSCDE 2/28L COMPLETE | ICW
LC | 121550072 | 006/046 | T2 DI ROCK CREEK-POE 6/46 RMV STEP | TABLEMTN | ETL.5630.TOWR | 2021-06-16 | 2021-06-13 | 2022-07-22 | 2022-06-13 | 2022-06-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45195578 | T2 DI ROCK CREEK-POE 6/46 RMV STEP | ICQ
LC | 121550128 | 004/037 | T2 DI PIT #1-CTTNWD 004/037 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-16 | 2021-06-13 | 2022-08-02 | 2022-06-13 | 2022-06-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149335 | T2 DI PIT #1-CTTNWD 004/037 RPR FOND | ICQ
LC | 121550145 | 020/239B | T2 DI DRUM-SUMMIT #2 20/239B RPL HRDD | SACTO | ETL.1450.POLE.WOOD | 2021-06-16 | 2021-06-13 | 2022-06-09 | 2022-06-13 | 2022-06-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45193589 | T2 DI DRUM-SUMMIT #2 20/239B RPL HRDD | ICW
LC | 121550190 | 020/239C | T2 DI DRUM-SUMMIT #2 20/239C RPL HRDD | SACTO | ETL.1450.POLE.WOOD | 2021-06-16 | 2021-06-13 | 2022-06-09 | 2022-06-13 | 2022-06-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45193590 | T2 DI DRUM-SUMMIT #2 20/239C RPL HRDD | ICW
LC | 121550199 | 039/334 | T2 DI ROUND MTN-CTNWD #3 39/334 HANGER | TABLEMTN | ETL.5650.TOWR | 2021-06-16 | 2021-06-13 | 2022-08-03 | 2022-06-13 | 2022-06-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45094449 | T2 DI ROUND MTN-CTNWD #3 39/334 HANGER | ICQ
LC | 121550227 | 002/028 | T2 EI MTN GATE JCT-CSCDE 2/28R COMPLETE | TABLEMTN | ETL.7640.POLE.WDPS | 2021-06-16 | 2021-06-16 | 2022-04-27 | 2022-06-16 | 2022-06-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45352184 | T2 EI MTN GATE JCT-CSCDE 2/28R COMPLETE | ICW
LC | 121550342 | 039/334 | T2 DI ROUND MTN-CTNWD #3 39/334 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-16 | 2021-06-13 | 2022-08-03 | 2022-06-13 | 2022-06-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547626 | T2 DI RND MTN-CTNWD #3 RPL INSS 9TWRS | 93K
LC | 121550347 | 006/047 | T2NT DI ROCK CREEK-POE 06/47 RPL HRDT | TABLEMTN | ETL.5630.TOWR | 2021-06-16 | 2021-06-13 | 2022-07-11 | 2022-06-13 | 2022-06-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2N PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45195577 | T2NT DI ROCK CREEK-POE 06/47 RPL HRDT | ICQ
LC | 121550348 | 006/047 | T2 DI ROCK CREEK-POE 06/47 RPL INSS | TABLEMTN | ETL.5630.INSL | 2021-06-16 | 2021-06-13 | 2022-08-05 | 2022-06-13 | 2022-06-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551263 | T3 DI ROCK CREEK-POE RPL INSS 9TWRS | 93K
LC | 121550422 | 045/387 | T2 DI RND MTN CTTNWD #3 045/387 RPR STRT | TABLEMTN | ETL.5650.TOWR | 2021-06-16 | 2021-06-13 | 2022-01-27 | 2022-06-13 | 2022-06-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45110545 | T2 DI RND MTN CTTNWD #3 045/387 RPR STRT | ICQ
LC | 121550507 | 000/015 | T2 DI SMRTSVLLE NCLS #1 0/15 RPL STRW | SACTO | ETL.7990.POLE.WOOD | 2021-06-16 | 2021-06-12 | 2022-08-23 | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548078 | T2 DI SMRTSVLLE NCLS #1 000/002 RPL STRW | 70Y
LC | 121550574 | 000/006 | T2 DI COLEMAN-SOUTH 00/06 RPL HRDW | TABLEMTN | ETL.6450.POLE.WOOD | 2021-06-16 | 2021-06-11 | 2022-05-10 | 2022-06-11 | 2022-06-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45212300 | T2 DI COLEMAN-SOUTH 00/06 RPL HRDW | ICW
LC | 121550631 | 036/145 | T2 DI DIABLO-MIDWAY #2 036/145 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-06-16 | 2021-06-15 | 2022-06-24 | 2022-06-15 | 2022-06-15 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068551 | T2 DI DIABLO-MIDWAY #2 036/145 RPR GYWS | ICS
LC | 121550636 | 001/015 | T2 DI PIT #1-COTNWD 01/15 RPL HRDT | TABLEMTN | ETL.5390.TOWR | 2021-06-16 | 2021-06-13 | 2022-08-01 | 2022-06-13 | 2022-06-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45195576 | T2 DI PIT #1-COTNWD 01/15 RPL HRDT | ICQ
LC | 121550684 | 003/031 | T2 DI PIT #3-PIT #1 003/031 RPR INSS | TABLEMTN | ETL.5400.INSL | 2021-06-16 | 2021-06-13 | 2022-06-24 | 2022-06-13 | 2022-06-13 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213894 | T2 DI PIT #3-PIT #1 003/031 RPR INSS | ICS
LC | 121550748 | 001/016 | T2 DI PIT #3-PIT #1 001/016 RPR INSS | TABLEMTN | ETL.5400.INSL | 2021-06-16 | 2021-06-13 | 2022-06-24 | 2022-06-13 | 2022-06-13 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213891 | T2 DI PIT #3-PIT #1 001/016 RPR INSS | ICS
LC | 121550788 | 017/070 | T2 DI DIABLO-MIDWAY #3 017/070 RPL HRDT | PISMOBCH | ETL.5980.TOWR | 2021-06-16 | 2021-06-16 | 2022-02-14 | 2022-06-16 | 2022-06-16 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45073737 | T2 DI DIABLO-MIDWAY #3 017/070 RPL HRDT | ICQ
LC | 121550789 | 002/035 | T2 DI SMRTVIL-NICLS #1 2/35 RPL STRW | SACTO | ETL.7990.POLE.WOOD | 2021-06-16 | 2021-06-12 | 2022-08-15 | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548078 | T2 DI SMRTSVLLE NCLS #1 000/002 RPL STRW | 70Y
LC | 121550814 | 005/045 | T2 DI ROCK CREEK-POE 5/45 RMV STEP | TABLEMTN | ETL.5630.TOWR | 2021-06-16 | 2021-06-13 | 2022-07-22 | 2022-06-13 | 2022-06-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45195575 | T2 DI ROCK CREEK-POE 5/45 RMV STEP | ICQ
LC | 121550817 | 067/004 | T2 DI HUMBOLDT-TRINITY 067/004 RPR INSW | EUREKA | ETL.1820.INSL.CERA | 2021-06-16 | 2021-06-12 | 2022-03-29 | 2022-06-12 | 2022-06-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45145529 | T2 DI HUMBOLDT-TRINITY 067/004 RPR INSW | ICW
LC | 121551028 | 019/226A | T2 DI DRUM-SUMMIT #1 19/226A RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2021-06-16 | 2021-06-12 | 2022-09-10 | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121551782 | 026/114 | T2 DI MOSS LNDG-MTCLF 26/114 RPR GYWS | MOSSLNDG | ETL.6050.TOWR | 2021-06-17 | 2021-06-16 | 2022-08-09 | 2022-06-16 | 2022-06-16 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45149709 | T2 DI MOSS LNDG-MTCLF 26/114 RPR GYWS | ICS
LC | 121552580 | 002/026 | T2 EI MTN GTE- CSCD 2/26L RPR GWRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-06-17 | 2021-06-17 | 2022-04-26 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45378769 | T2 EI MTN GTE- CSCD 2/26L RPR GWRW | ICW
LC | 121552658 | 002/026 | T2 EI MTN GTE- CSCD 2/26R RPR GYWW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-06-17 | 2021-06-17 | 2022-04-26 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45378049 | T2 EI MTN GTE- CSCD 2/26R RPR GYWW | ICW
LC | 121552704 | 093/473 | T2 DI MALIN-ROUND MTN #2 93/473 RPR FOND | TABLEMTN | ETL.6020.TOWR | 2021-06-17 | 2021-06-17 | 2022-07-13 | 2022-06-17 | 2022-06-17 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45198276 | T2 DI MALIN-ROUND MTN #2 93/473 RPR FOND | ICQ
LC | 121552706 | 048/197 | T2 DI MIDWAY-WHIRLWIND 48/197 RPR GYWS | MIDWAY | ETL.6030.TOWR | 2021-06-17 | 2021-06-16 | 2022-01-19 | 2022-06-16 | 2022-06-16 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45067995 | T2 DI MIDWAY-WHIRLWIND 48/197 RPR GYWS | ICS
LC | 121552924 | 002/025 | T2 EI MTN GATE JCT-CSCDE 2/025L RPR GYWW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-06-17 | 2021-06-17 | 2022-04-27 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45352180 | T2 EI MTN GATE JCT-CSCDE 2/025L RPR GYWW | ICW
LC | 121552961 | 002/025 | T2 EI MTN GATE JCT-CSCDE 2/025R RPR GYWW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-06-17 | 2021-06-17 | 2022-04-27 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45352181 | T2 EI MTN GATE JCT-CSCDE 2/025R RPR GYWW | ICW
LC | 121553054 | 025/103 | T2 DI TESLA-METCALF 025/103 UNBURY | METCALF | ETL.6110.TOWR | 2021-06-17 | 2021-06-16 | 2022-07-06 | 2022-06-16 | 2022-06-16 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45211595 | T2 DI TESLA-METCALF 025/103 UNBURY | ICQ
LC | 121553173 | 055/272 | T2 DI MALIN-ROUND MTN #2 55/272 RPL HRDT | TABLEMTN | ETL.6020.TOWR | 2021-06-17 | 2021-06-16 | 2022-10-04 | 2022-06-16 | 2022-06-16 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45193984 | T2 DI MALIN-ROUND MTN #2 55/272 RPL HRDT | ICQ
LC | 121553177 | 055/272 | T2 DI MALIN-ROUND MTN #2 55/272 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-17 | 2021-06-16 | 2022-07-15 | 2022-06-16 | 2022-06-16 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215239 | T2 DI MALIN-ROUND MTN #2 55/272 RPR SHLS | ICS
LC | 121553462 | 044/382 | T2 DI PIT #1-COTTONWOOD 044/382 RPR INSS | TABLEMTN | ETL.5390.INSL.NCER | 2021-06-17 | 2021-06-13 | 2022-03-08 | 2022-06-13 | 2022-06-13 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45197283 | T2 DI PIT #1-COTTONWOOD 044/382 RPR INSS | ICS
LC | 121553477 | 093/474 | T2 DI MALIN-ROUND MTN #2 93/474 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-06-17 | 2021-06-17 | 2022-06-14 | 2022-06-17 | 2022-06-17 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45198278 | T2 DI MALIN-ROUND MTN #2 93/474 RPR GYWS | ICS
LC | 121553576 | 001/010 | T2 DI PIT #3-PIT #1 001/010 RMV VEG COA | TABLEMTN | ETL.5400.TOWR | 2021-06-17 | 2021-06-13 | 2022-08-31 | 2022-06-13 | 2022-06-13 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR FRAB SR22 | Overgrown | Vegetation | Remove
LC | 121553615 | 023/097 | T2 DI TESLA-METCALF 23/97 RPR STRT | METCALF | ETL.6110.TOWR | 2021-06-17 | 2021-06-17 | 2022-07-06 | 2022-06-17 | 2022-06-17 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45233300 | T2 DI TESLA-METCALF 23/97 RPR STRT | ICQ
LC | 121554022 | 026/115 | T2 DI MSS LNDING-METCALF 26/115 RPR GYWS | MOSSLNDG | ETL.6050.TOWR | 2021-06-17 | 2021-06-16 | 2022-06-29 | 2022-06-16 | 2022-06-16 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45149710 | T2 DI MSS LNDING-METCALF 26/115 RPR GYWS | ICS
LC | 121554024 | 018/075 | T2 DI DIABLO-MIDWAY #2 018/075 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-06-17 | 2021-06-16 | 2022-06-21 | 2022-06-16 | 2022-06-16 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068555 | T2 DI DIABLO-MIDWAY #2 018/075 RPR GYWS | ICS
LC | 121554099 | 014/183 | T2 EI DELTA-MTN GT JCT 14/183 RPL INSW | TABLEMTN | ETL.6750.INSL.CERA | 2021-06-17 | 2021-06-17 | 2022-08-24 | 2022-06-17 | 2022-06-17 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31544400 | T2 EI DELTA-MTN GT JCT 15/183 RPL INSW | 93I
LC | 121554311 | 015/003 | T2 EI LAYTONVILLE-WILLITS 15/3L CNCL | WILLITS | ETL.8360.POLE.STPS | 2021-06-17 | 2021-06-17 | 2022-10-07 | 2022-06-17 | 2022-06-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP CNCL OH FMOB TR2 PRTO NTDE CNNV | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 121554417 | 015/003 | T2 EI LAYTONVILLE-WILLITS 15/3C RPR GYWW | WILLITS | ETL.8360.POLE.STPS | 2021-06-17 | 2021-06-17 | 2022-10-24 | 2022-06-17 | 2022-06-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45144666 | T2 EI LAYTONVILLE-WILLITS 15/3L RPR GYWW | ICW
LC | 121554429 | 054/267 | T2 DI MALIN-ROUND MTN #2 54/267 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-17 | 2021-06-16 | 2022-07-15 | 2022-06-16 | 2022-06-16 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215238 | T2 DI MALIN-ROUND MTN #2 54/267 RPR SHLS | ICS
LC | 121555008 | 014/178 | T2 EI DLTA-MTN GTE JCT 14/178 RPL DAMP | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-17 | 2021-06-17 | 2022-08-20 | 2022-06-17 | 2022-06-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Damper-Wood | Replace | 45296748 | T2 EI DLTA-MTN GTE JCT 14/178 RPL DAMP | ICW
LC | 121555021 | 021/091 | T2 DI TESLA-METCALF 21/91 RPR SHLS | METCALF | ETL.6110.TOWR | 2021-06-17 | 2021-06-17 | 2021-09-21 | 2022-06-17 | 2022-06-17 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44959063 | T2 DI TESLA-METCALF 21/91 RPR SHLS | ICS
LC | 121555276 | 023/099 | T2 DI TESLA-METCALF 23/99 RPR GYWS | METCALF | ETL.6110.TOWR | 2021-06-17 | 2021-06-16 | 2022-07-06 | 2022-06-16 | 2022-06-16 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45232738 | T2 DI TESLA-METCALF 23/99 RPR GYWS | ICS
LC | 121555923 | 020/082 | T2 DI DIABLO-MIDWAY #2 020/082 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-06-17 | 2021-06-17 | 2022-05-26 | 2022-06-17 | 2022-06-17 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068556 | T2 DI DIABLO-MIDWAY #2 020/082 RPR GYWS | ICS
LC | 121556119 | 006/006 | T2 DI LAYTONVILLE-COVELO 06/06R RPL STRW | WILLITS | ETL.7390.POLE.WDPS | 2021-06-17 | 2021-06-09 | 2022-06-26 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544413 | T2 DI LAYTONVILLE-COVELO 06/06C RPL STRW | 70Y
LC | 121556312 | 020/081 | T2 DI DIABLO-MIDWAY #2 020/081 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-06-17 | 2021-06-16 | 2022-05-25 | 2022-06-16 | 2022-06-16 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068558 | T2 DI DIABLO-MIDWAY #2 020/081 RPR GYWS | ICS
LC | 121556313 | 005/071 | T2 EI HT CRK #1-PT #1 5/71R RPL POLE | TABLEMTN | ETL.7020.POLE.WDPS | 2021-06-17 | 2021-06-16 | 2022-07-25 | 2022-06-16 | 2022-06-16 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544410 | T2 EI HT CRK #1-PT #1 5/71 RPL POLE | 70Y
LC | 121556314 | 005/071 | T2 EI HT CRK #1-PT #1 5/71C RPL POLE | TABLEMTN | ETL.7020.POLE.WDPS | 2021-06-17 | 2021-06-16 | 2022-07-25 | 2022-06-16 | 2022-06-16 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544410 | T2 EI HT CRK #1-PT #1 5/71 RPL POLE | 70Y
LC | 121556324 | 006/065 | EI T2 PIT #5 - RND MTN #1 6/65 RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-17 | 2021-06-14 | 2022-07-15 | 2022-06-14 | 2022-06-14 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121556390 | 001/022 | T2 PIT #1-MC ARTHUR 1/22 RPL STRW | TABLEMTN | ETL.7790.POLE.WOOD | 2021-06-17 | 2021-06-12 | 2022-06-26 | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544219 | T2 PIT #1-MC ARTHUR 1/22 RPL STRW | 70Y
LC | 121556520 | 005/060 | T2 EI PIT #5 - RND MTN #1 5/60R RPL STRW | TABLEMTN | ETL.5420.POLE.WOOD | 2021-06-17 | 2021-06-14 | 2022-07-14 | 2022-06-14 | 2022-06-14 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121556770 | 020/082 | T2 DI DIABLO-MIDWAY #2 020/082 RPL HRDT | PISMOBCH | ETL.5970.TOWR | 2021-06-17 | 2021-06-17 | 2022-02-15 | 2022-06-17 | 2022-06-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45073730 | T2 DI DIABLO-MIDWAY #2 020/082 RPL HRDT | ICQ
LC | 121556809 | 003/033 | T2 DI PIT #1-COTTONWOOD 3/33 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-17 | 2021-06-13 | 2022-08-01 | 2022-06-13 | 2022-06-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195574 | T2 DI PIT #1-COTTONWOOD 3/33 RPR FOND | ICQ
LC | 121557095 | 007/110 | T2 EI DLTA-MTN GATE JCT 7/110L RPL POLE | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-17 | 2021-06-17 | 2022-08-24 | 2022-06-17 | 2022-06-17 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544359 | T2 EI DLTA-MTN GATE JCT 7/110 RPL POLE | 70Y
LC | 121557097 | 007/110 | T2 EI DLTA-MTN GATE JCT 7/110R RPL POLE | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-17 | 2021-06-17 | 2022-08-18 | 2022-06-17 | 2022-06-17 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544359 | T2 EI DLTA-MTN GATE JCT 7/110 RPL POLE | 70Y
LC | 121557217 | 008/063A | T2 DI HELMS-GREGG #1 008/063A RPL HRDS | FRESNO | ETL.4870.TOWR | 2021-06-17 | 2021-06-16 | 2022-08-21 | 2022-06-16 | 2022-06-16 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45069493 | T2 DI HELMS-GREGG #1 008/063A RPL HRDS | ICS
LC | 121557219 | 008/063A | T2 DI HELMS-GREGG #1 008/063A RPL INSS | FRESNO | ETL.4870.INSL | 2021-06-17 | 2021-06-16 | 2022-08-21 | 2022-06-16 | 2022-06-16 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551822 | DI HELMS-GREGG #1 RPL INSS 12 TWRS | 93K
LC | 121557237 | 006/048 | T2 DI ROCK CREEK-POE 6/48 RPLC INSS | TABLEMTN | ETL.5630.INSL.CERA | 2021-06-17 | 2021-06-13 | 2022-08-05 | 2022-06-13 | 2022-06-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551263 | T3 DI ROCK CREEK-POE RPL INSS 9TWRS | 93K
LC | 121557347 | 070/613 | T2 DI CTTNWD-DLVN #2 70/613 RPR FOND | TABLEMTN | ETL.4580.TOWR | 2021-06-17 | 2021-06-11 | 2022-01-10 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45107505 | T2 DI CTTNWD-DLVN #2 70/613 RPR FOND | ICQ
LC | 121557525 | 021/004 | T2 DI MNDCN-WLTS-FRT BRG 21/4 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-17 | 2021-06-12 | 2022-08-15 | 2022-06-12 | 2022-06-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145830 | T2 DI MNDCN-WLTS-FRT BRG 21/4 RPR GYWW | ICW
LC | 121557527 | 021/004 | T2 DI MNDCN-WLTS-FRT BRG 21/4 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-17 | 2021-06-12 | 2022-09-14 | 2022-06-12 | 2022-06-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45262571 | T2 DI MNDCN-WLTS-FRT BRG 21/4 RPR STRW | ICW
LC | 121557601 | 004/039 | T2 DI ROCK CREEK-POE 4/39 RMV VEGN | TABLEMTN | ETL.5630.TOWR | 2021-06-17 | 2021-06-13 | 2022-08-09 | 2022-06-13 | 2022-06-13 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121557602 | 004/039 | T2 DI ROCK CREEK-POE 4/39 RPR STRT | TABLEMTN | ETL.5630.TOWR | 2021-06-17 | 2021-06-13 | 2022-02-10 | 2022-06-13 | 2022-06-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45159495 | T2 DI ROCK CREEK-POE 4/39 RPR STRT | ICQ
LC | 121557742 | 084/004B | T2 DI HUMBOLDT-TRINITY 84/4B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2021-06-17 | 2021-06-12 | 2022-03-25 | 2022-06-12 | 2022-06-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45149345 | T2NT DI HMBOLDT-TRINITY 84/4A RMV DEBRIS | ICW
LC | 121557793 | 009/076 | T2 DI PIT #1-CTTNWD 9/76 RMV NEST | TABLEMTN | ETL.5390.TOWR | 2021-06-17 | 2021-06-11 | 2022-03-04 | 2022-06-11 | 2022-06-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45197284 | T2 DI PIT #1-CTTNWD 9/76 RMV NEST | ICW
LC | 121557798 | 025/203 | T2 DI PIT #1-COTTONWOOD 25/203 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-17 | 2021-06-11 | 2022-02-02 | 2022-06-11 | 2022-06-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149509 | T2 DI PIT #1-COTTONWOOD 25/203 RPR FOND | ICQ
LC | 121558471 | 007/080 | T2 DI DRUM-SUMMIT #2 7/80 RPR CRSW | SACTO | ETL.1450.POLE.WDPS | 2021-06-17 | 2021-06-08 | 2022-08-08 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45200327 | T2 DI DRUM-SUMMIT #2 7/80 RPR CRSW | ICW
LC | 121558479 | ;002/016 | T2 DI CARIBOU #2 ;002/16 RPL INSW | TABLEMTN | ETL.6280.INSL.CERA | 2021-06-17 | 2021-06-08 | 2022-07-15 | 2022-06-08 | 2022-06-08 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31544339 | T2 DI CARIBOU #2 ;002/16 RPL INSW | 93I
LC | 121560055 | 109/007 | T2 DI HMBLDT-BRDGVLLE 109/007 RPL INSW | EUREKA | ETL.1810.INSL.NCER | 2021-06-18 | 2021-06-17 | 2022-04-05 | 2022-06-17 | 2022-06-17 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547434 | DI HUMBOLDT-BRIDGEVILLE RPL INSS 7TWRS | 93K
LC | 121560206 | 009/114 | T2 DI DRUM-SUMMIT #1 009/114 RPL HRDW | SACTO | ETL.1440.POLE.STPS | 2021-06-18 | 2021-06-08 | 2022-08-19 | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45200329 | T2 DI DRUM-SUMMIT #1 009/114 RPL HRDW | ICW
LC | 121560328 | 002/036 | T2 DI SMRTSVLLE NCLS #1 2/36 RPR STRW | SACTO | ETL.7990.POLE.WOOD | 2021-06-18 | 2021-06-12 | 2022-08-20 | 2022-06-12 | 2022-06-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45233398 | T2 DI SMRTSVLLE NCLS #1 2/36 RPR STRW | ICW
LC | 121560442 | 040/007 | T2 DI MNDCN-WLLTS-FRT BRGG 40/7 RPR SPLW | WILLITS | ETL.7550.INSL.NCER | 2021-06-18 | 2021-06-17 | 2022-10-24 | 2022-06-17 | 2022-06-17 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45150031 | T2 DI MNDCN-WLLTS-FRT BRGG 40/7 RPR SPLW | ICS
LC | 121560448 | 031/005 | T2 DI MNDC-WLLT-FRT BRGG 31/5 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2021-06-18 | 2021-06-17 | 2022-10-02 | 2022-06-17 | 2022-06-17 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31551283 | T2 DI MNDCN-WLTS-FRT BRG 28/10 RPL INSW | 93I
LC | 121560585 | 095/012 | T2 DI HUMBOLDT-TRINITY 95/12R RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-18 | 2021-06-08 | 2022-03-22 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45160746 | T2 DI HUMBOLDT-TRINITY 95/12R RPR STRW | ICW
LC | 121560586 | 095/012 | T2 DI HUMBOLDT-TRINITY 95/12L RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-18 | 2021-06-08 | 2022-03-22 | 2022-06-08 | 2022-06-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45160746 | T2 DI HUMBOLDT-TRINITY 95/12R RPR STRW | ICW
LC | 121560852 | 007/168 | T2 DI HMLTN BRNCH CHSTR 7/168 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-06-18 | 2021-06-08 | 2022-07-26 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544408 | T2 DI HAMLTN BRCH-CHESTR 8/181 RPL POLE | 70Y
LC | 121560861 | 022/204 | T2 EI GYSRS NO. 3-UKIAH_022/204 RPL INSW | LAKEVLLE | ETL.4050.INSL.NCER | 2021-06-18 | 2021-06-18 | 2022-01-29 | 2022-06-18 | 2022-06-18 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545619 | T2 EI UKIAH-HOPLAND 002/024 RPR INSW | 93I
LC | 121560933 | :001/004 | T2 DI BLTA-RVK-MLNS SS :1/4 RPL POLE | VICTOR | ETL.1070.POLE.WOOD | 2021-06-18 | 2021-06-12 | 2022-04-15 | 2022-06-12 | 2022-06-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31539414 | T2 DI BLLT-RVRBNK-MLS SWS :1/7 RPL STRW | 70Y
LC | 121561396 | 003/062 | T2 EI CORDELIA #2 TAP 3/62L RPL STRW | SACTO | ETL.8184.POLE.WDPS | 2021-06-18 | 2021-06-18 | 2022-08-19 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544902 | T2 EI CORDELIA #2 TAP 3/62L RPL STRW | 70Y
LC | 121561411 | 045/390 | T2 DI PIT #1-CTTNWD 045/390 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-06-18 | 2021-06-10 | 2022-03-04 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149565 | T2 DI PIT #1-CTTNWD 045/390 RPR FOND | ICQ
LC | 121561451 | 003/062 | T2 EI CORDELIA #2 TAP 3/62C RPL STRW | SACTO | ETL.8184.POLE.WDPS | 2021-06-18 | 2021-06-18 | 2022-08-19 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544902 | T2 EI CORDELIA #2 TAP 3/62L RPL STRW | 70Y
LC | 121561469 | 003/062 | T2 EI CORDELIA #2 TAP 3/62R RPL STRW | SACTO | ETL.8184.POLE.WDPS | 2021-06-18 | 2021-06-18 | 2022-08-19 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544902 | T2 EI CORDELIA #2 TAP 3/62L RPL STRW | 70Y
LC | 121561515 | 008/124 | EI T2 DELTA-MTN GATE JCT 8/124L RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-18 | 2021-06-18 | 2022-08-17 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544588 | EI T2 DELTA-MTN GATE JCT 8/124 RPL STRW | 70Y
LC | 121561533 | 030/003C | T2 EI PHILO JCT-ELK 30/3C RPL ANCW | WILLITS | ETL.7780.POLE.WOOD | 2021-06-18 | 2021-06-18 | 2022-03-17 | 2022-06-18 | 2022-06-18 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31541325 | PHILO JCT-ELK 22/000 REFRAME | 93E
LC | 121561553 | 008/124 | EI T2 DELTA-MTN GATE JCT 8/124R RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-18 | 2021-06-18 | 2022-08-17 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544588 | EI T2 DELTA-MTN GATE JCT 8/124 RPL STRW | 70Y
LC | 121561580 | 021/088 | T2 DI TESLA-METCALF 021/088 RPR SHLS | METCALF | ETL.6110.TOWR | 2021-06-18 | 2021-06-16 | 2021-09-03 | 2022-06-16 | 2022-06-16 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44959066 | T2 DI TESLA-METCALF 021/088 RPR SHLS | ICS
LC | 121561702 | 000/007 | T2 EI MNTN GT JCT-CSCD 0/7L RPR GYWW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-06-18 | 2021-06-18 | 2022-04-27 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45352130 | T2 EI MNTN GT JCT-CSCD 0/7L RPR GYWW | ICW
LC | 121561795 | 060/300 | T2 DI MALIN-ROUND MTN #2 60/300 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-18 | 2021-06-11 | 2022-07-14 | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215236 | T2 DI MALIN-ROUND MTN #2 60/300 RPR SHLS | ICS
LC | 121561809 | 012/079 | T2 DI CORTINA-VACA 12/79 RPL DAMS | SACTO | ETL.4540.INSL.CERA | 2021-06-18 | 2021-06-15 | 2022-05-09 | 2022-06-15 | 2022-06-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 45200330 | T2 DI CORTINA-VACA 12/79 RPL DAMS | ICS
LC | 121561921 | 008/120 | T2 EI DELTA-MTN GATE JCT 8/120 RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-18 | 2021-06-18 | 2022-08-22 | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296754 | T2 EI DELTA-MTN GATE JCT 8/120 RPR GYWW | ICW
LC | 121562174 | R001/017 | T2 DI RND MTN-COTTONWD #3 R1/17 RPR STRT | TABLEMTN | ETL.5650.TOWR | 2021-06-18 | 2021-06-18 | 2022-01-20 | 2022-06-18 | 2022-06-18 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45111984 | T2 DI RND MTN-COTTONWD #3 R1/17 RPR STRT | ICQ
LC | 121562334 | 022/000 | T2 DI MNDCN-WLTS-FRT BRG 22/0 RMV DEBRIS | WILLITS | ETL.7550.POLE.WOOD | 2021-06-18 | 2021-06-18 | 2022-05-22 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45148028 | T2 EI MNDCN-WLTS-FRT BRG 22/0 RPL DAMW | ICW
LC | 121562392 | 022/000 | T2 DI MNDCN-WLTS-FRT BRG 22/0 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-18 | 2021-06-18 | 2022-05-22 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148028 | T2 EI MNDCN-WLTS-FRT BRG 22/0 RPL DAMW | ICW
LC | 121562497 | 015/142 | T2 EI UKIAH-HOPLAND 015/142L RPL POLE | WILLITS | ETL.4050.POLE.WDPS | 2021-06-18 | 2021-06-18 | 2022-05-05 | 2022-06-18 | 2022-06-18 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545800 | T2 EI UKIAH-HOPLAND RPL POLE IN 6 TWRS. | 70Y
LC | 121562590 | 015/142 | T2 EI UKIAH-HOPLAND 015/142R COMPLETE | WILLITS | ETL.4050.POLE.WDPS | 2021-06-18 | 2021-06-18 | 2022-05-05 | 2022-06-18 | 2022-06-18 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545800 | T2 EI UKIAH-HOPLAND RPL POLE IN 6 TWRS. | 70Y
LC | 121562648 | 023/100 | T2 DI MSS LNDNG-MTCLF 023/100 RPR SHLS | MOSSLNDG | ETL.6050.TOWR | 2021-06-18 | 2021-06-17 | 2022-02-26 | 2022-06-17 | 2022-06-17 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45166395 | T2 DI MSS LNDNG-MTCLF 023/100 RPR SHLS | ICS
LC | 121562691 | 008/116 | T2 EI DELTA-MTN GATE JCT 8/116L RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-18 | 2021-06-18 | 2022-07-25 | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296755 | T2 EI DELTA-MTN GATE JCT 8/116L RPR GYWW | ICW
LC | 121562752 | 008/116 | T2 EI DELTA-MTN GATE JCT 8/116R RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-06-18 | 2021-06-18 | 2022-07-25 | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296756 | T2 EI DELTA-MTN GATE JCT 8/116R RPR GYWW | ICW
LC | 121563152 | 031/475 | T2 DI CLAY-MARTEL 031/475L RPR GYWW | VICTOR | ETL.8250.POLE.WDPS | 2021-06-18 | 2021-06-17 | 2022-07-26 | 2022-06-17 | 2022-06-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45067238 | T2 DI CLAY-MARTEL 031/475L RPR GYWW | ICW
LC | 121563154 | 031/475 | T2 DI CLAY-MARTEL 031/475C RPR GYWW | VICTOR | ETL.8250.POLE.WDPS | 2021-06-18 | 2021-06-17 | 2022-07-26 | 2022-06-17 | 2022-06-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45067239 | T2 DI CLAY-MARTEL 031/475C RPR GYWW | ICW
LC | 121563155 | 031/475 | T2 DI CLAY-MARTEL 031/475R RPR GYWW | VICTOR | ETL.8250.POLE.WDPS | 2021-06-18 | 2021-06-17 | 2022-07-26 | 2022-06-17 | 2022-06-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45067380 | T2 DI CLAY-MARTEL 031/475R RPR GYWW | ICW
LC | 121563156 | 031/475 | T2 DI CLAY-MARTEL 031/475R RPR STRW | VICTOR | ETL.8250.POLE.WDPS | 2021-06-18 | 2021-06-17 | 2022-07-26 | 2022-06-17 | 2022-06-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45067381 | T2 DI CLAY-MARTEL 031/475R RPR STRW | ICW
LC | 121563175 | 001/000 | T2 EI GARCIA TAP 01/000 RPL INSW | WILLITS | ETL.8411.POLE.WDPS | 2021-06-18 | 2021-06-18 | 2022-07-20 | 2022-06-18 | 2022-06-18 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31544722 | T2 EI GARCIA TAP 01/000 RPL INSW | 93I
LC | 121563228 | 008/115 | T2 EI DLT-MT GT JCT 8/115 RPL DAMW | TABLEMTN | ETL.6750.INSL.CERA | 2021-06-18 | 2021-06-18 | 2022-08-23 | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Damper-Wood | Replace | 45296758 | T2 EI DELTA-CASCADE 8/115 RPL DAMW | ICW
LC | 121563234 | 008/115 | T2 EI DLT-MT GT JCT 8/115 RPR SPLW | TABLEMTN | ETL.6750.INSL.CERA | 2021-06-18 | 2021-06-18 | 2022-08-23 | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45438761 | T2 EI DLT-MT GT JCT 8/115 RPR SPLW | ICW
LC | 121563484 | 000/004 | T2 DI STANISLAUS-MANTECA #2 0/4 RMV VEG | VICTOR | ETL.3820.TOWR | 2021-06-18 | 2021-06-18 | 2021-12-15 | 2022-06-18 | 2022-06-18 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121563628 | 003/015 | T2 DI MORRO BAY-MESA 3/15 RPL HRDT | PISMOBCH | ETL.5290.TOWR | 2021-06-18 | 2021-06-16 | 2022-06-15 | 2022-06-16 | 2022-06-16 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45073831 | T2 DI MORRO BAY-MESA 3/15 RPL HRDT | ICQ
LC | 121563736 | 003/015 | T2 DI MORRO BAY-MESA 3/15 RPL INSS | PISMOBCH | ETL.5290.INSL | 2021-06-18 | 2021-06-16 | 2022-06-23 | 2022-06-16 | 2022-06-16 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534504 | T2 EI MORRO BAY-MESA RPL INSLS 5TWRS | 93K
LC | 121563808 | 003/015 | T2 DI MRRO BAY-DIABLO 3/15 RPL INSS | PISMOBCH | ETL.5260.INSL | 2021-06-18 | 2021-06-16 | 2022-12-14 | 2022-06-16 | 2022-06-16 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548991 | T2 DI MORRO BAY-DIABLO 3/15 RPL INSS | 93K
LC | 121564076 | 034/520 | T2 DI CLAY-MARTEL 034/520 REFRAME | VICTOR | ETL.8250.POLE.WOOD | 2021-06-18 | 2021-06-17 | 2022-03-23 | 2022-06-17 | 2022-06-17 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31544761 | T2 DI CLAY-MARTEL 034/520 REFRAME | 93E
LC | 121564078 | 034/520 | T2 DI CLAY-MARTEL 034/520 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-06-18 | 2021-06-17 | 2022-03-28 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45135175 | T2 DI CLAY-MARTEL 034/520 RPR STRW | ICW
LC | 121564136 | 021/257 | T2 EI DRUM-SUMMIT #1 21/257 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-18 | 2021-06-18 | 2022-08-30 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121564143 | 022/261 | EI T2 DRUM- SUMMIT NO. 1 22/261 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-18 | 2021-06-18 | 2022-09-01 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121564272 | 027/011 | T2 DI MNDCN-WLLTS-FRT BRGG 27/11 RPL CRS | WILLITS | ETL.7550.POLE.WOOD | 2021-06-18 | 2021-06-18 | 2022-05-18 | 2022-06-18 | 2022-06-18 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31540800 | EI MNDCN-WLLTS-FRT BRGG :0/10 REFRAME | 93E
LC | 121564273 | 027/011 | T2 DI MNDCN-WLLTS-FRT BRG 27/11 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-18 | 2021-06-18 | 2022-05-18 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45148573 | T2 DI MNDCN-WLLTS-FRT BRG 27/11 RPR STRW | ICW
LC | 121564510 | 039/244 | T2 DI CZY HRS CNYN-SLNS 39/244 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2021-06-18 | 2021-06-18 | 2021-10-07 | 2022-06-18 | 2022-06-18 | On-time | 593 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 44962411 | T2 DI CZY HRS CNYN-SLNS 39/244 RPL RPTS | ICB
LC | 121564513 | 067/336 | T2 DI MALIN-ROUND MTN #2 067/336 RPR SHL | TABLEMTN | ETL.6020.TOWR | 2021-06-18 | 2021-06-18 | 2022-07-14 | 2022-06-18 | 2022-06-18 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215235 | T2 DI MALIN-ROUND MTN #2 067/336 RPR SHL | ICS
LC | 121565270 | 044/381 | T2 DI RND MTN-CTTNWD #3 44/381 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-18 | 2021-06-13 | 2022-08-04 | 2022-06-13 | 2022-06-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547626 | T2 DI RND MTN-CTNWD #3 RPL INSS 9TWRS | 93K
LC | 121565543 | 089/003 | T2 DI HUMBOLDT-TRINITY 89/3 RPR SWTC | EUREKA | ETL.1820.SWIT | 2021-06-18 | 2021-06-13 | 2022-10-12 | 2022-06-13 | 2022-06-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Switch-Wood | Repair | 44888302 | T2 DI HUMBOLDT-TRINITY 89/3 RPR SWTC | ICW
LC | 121565685 | 000/004 | T2 DI PIT #1-COTTONWOOD 0/4 RPR INSS | TABLEMTN | ETL.5390.INSL.NCER | 2021-06-18 | 2021-06-14 | 2022-03-10 | 2022-06-14 | 2022-06-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45197285 | T2 DI PIT #1-COTTONWOOD 0/4 RPR INSS | ICS
LC | 121565778 | 000/008 | T2 DI COLEMAN-SOUTH 000/008 RPL STRW | TABLEMTN | ETL.6450.POLE.WOOD | 2021-06-18 | 2021-06-14 | 2022-05-11 | 2022-06-14 | 2022-06-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544700 | T2 DI COLEMAN-SOUTH 000/008 RPL STRW | 70Y
LC | 121565932 | 004/023 | T2 DI MOSS LANDING-METCALF 4/23 RPR GYWS | MOSSLNDG | ETL.6050.TOWR | 2021-06-18 | 2021-06-18 | 2022-06-28 | 2022-06-18 | 2022-06-18 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45149711 | T2 DI MOSS LANDING-METCALF 4/23 RPR GYWS | ICS
LC | 121567902 | 051/386 | T2 DI BRDGVLLE-CTTNWD 051/386 REM VEG | TABLEMTN | ETL.1110.TOWR | 2021-06-19 | 2021-06-15 | 2022-08-29 | 2022-06-15 | 2022-06-15 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE CNCL OH TR2 PRTO AIR FRAB SR22 | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121567904 | 051/386 | T2 DI BRDGVLLE-CTTNWD 051/386 RPL INSS | TABLEMTN | ETL.1110.INSL.CERA | 2021-06-19 | 2021-06-15 | 2022-06-27 | 2022-06-15 | 2022-06-15 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31529414 | T2 DI NN BRDGVLLE-CTNWD RPL INSS 5TWRS | 93K
LC | 121568054 | 050/383 | T2 DI BRDGVLLE-CTTNWD 50/383 RPR FOND | TABLEMTN | ETL.1110.TOWR | 2021-06-19 | 2021-06-14 | 2022-07-29 | 2022-06-14 | 2022-06-14 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149334 | T2 DI BRDGVLLE-CTTNWD 50/383 RPR FOND | ICQ
LC | 121568057 | 050/383 | T2 DI BRDGVLLE-CTTNWD 50/383 RPR INSS | TABLEMTN | ETL.1110.INSL.CERA | 2021-06-19 | 2021-06-14 | 2022-06-27 | 2022-06-14 | 2022-06-14 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213328 | T2 DI BRDGVLLE-CTTNWD 50/383 RPR INSS | ICS
LC | 121568108 | 092/002 | T2 DI HUMBOLDT-TRINITY 92/2 COMPLETED | EUREKA | ETL.1820.POLE.WDPS | 2021-06-19 | 2021-06-09 | 2022-06-07 | 2022-06-09 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121568122 | 041/347 | T2 DI PIT #1-COTTONWOOD 41/347 RMV BUTT | TABLEMTN | ETL.5390.TOWR | 2021-06-19 | 2021-06-10 | 2022-03-10 | 2022-06-10 | 2022-06-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45197286 | T2 DI PIT #1-COTTONWOOD 41/347 RMV BUTT | ICW
LC | 121568201 | 006/052 | T2 DI TRINITY-CTTNWD 6/52L RMV BUTT | TABLEMTN | ETL.4040.POLE.STPS | 2021-06-19 | 2021-06-09 | 2022-06-23 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45195573 | T2 DI TRINITY-CTTNWD 6/52L RMV BUTT | ICW
LC | 121568464 | 013/112B | T2 DI CRAG VIEW-CSCD 13/112B RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-06-19 | 2021-06-12 | 2022-09-16 | 2022-06-12 | 2022-06-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45500236 | T2 DI CRAG VIEW-CSCD 13/112B RPR GYWW | ICW
LC | 121568573 | 017/142 | DI T2 CRAG VIEW-CASCADE 017/142 RMV DBRS | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-19 | 2021-06-09 | 2022-07-06 | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45426621 | DI T2 CRAG VIEW-CASCADE 017/142 RMV DBRS | ICW
LC | 121568574 | 017/142 | T2 DI CRAG VIEW-CASCADE 017/142 RPL INSW | TABLEMTN | ETL.1350.INSL.NCER | 2021-06-19 | 2021-06-09 | 2022-09-13 | 2022-06-09 | 2022-06-09 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543332 | T2 DI CRAG VIEW-CASCADE 15/128 RPL INSW | 93I
LC | 121568639 | 000/002 | T2 DI PIT #1-COTTONWOOD 0/2 RMV NEST | TABLEMTN | ETL.5390.TOWR | 2021-06-19 | 2021-06-15 | 2022-03-03 | 2022-06-15 | 2022-06-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45197287 | T2 DI PIT #1-COTTONWOOD 0/2 RMV NEST | ICS
LC | 121568752 | 012/081 | T2 DI CORTINA-VACA 012/081 INSS COA | SACTO | ETL.4540.INSL.CERA | 2021-06-19 | 2021-06-15 | 2022-06-01 | 2022-06-15 | 2022-06-15 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31545131 | T2 DI CORTINA-VACA RPL INS 8 TWRS | 93K
LC | 121568753 | 012/081 | T2 DI DELEVAN-VACA #1 012/081 RPL INSS | SACTO | ETL.5010.INSL.CERA | 2021-06-19 | 2021-06-15 | 2022-04-01 | 2022-06-15 | 2022-06-15 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31530365 | DI DELEVAN-VACA #1 RPL INSS 4TWRS | 93K
LC | 121568892 | 037/162 | T2 DI FULTON-LAKEVILLE 037/162 RMV VEG | LAKEVLLE | ETL.4950.TOWR | 2021-06-19 | 2021-06-16 | 2021-12-07 | 2022-06-16 | 2022-06-16 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121568947 | 009/078 | T2 DI CRAG VIEW-CASCADE 9/78 RPR OPGW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-19 | 2021-06-15 | 2022-09-15 | 2022-06-15 | 2022-06-15 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45509601 | T2 DI CRAG VIEW-CASCADE 9/78 RPR OPGW | ICW
LC | 121568948 | 009/078 | T2 DI CRAG VIEW-CASCADE 9/78 RMV BUTT | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-19 | 2021-06-15 | 2022-07-08 | 2022-06-15 | 2022-06-15 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45427575 | T2 DI CRAG VIEW-CASCADE 9/78 RMV BUTT | ICW
LC | 121569269 | 013/062 | T2 DI SILVERADO-FULTN JCT 13/62 RPL INSS | LAKEVLLE | ETL.1610.INSL.CERA | 2021-06-19 | 2021-06-15 | 2022-03-14 | 2022-06-15 | 2022-06-15 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548688 | T2 DI SLVDO FLTN JCT SW RPL INSS 6TWRS | 93K
LC | 121569303 | 019/446 | T2 DI DRM-GRS VLY-WMR 19/446 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-06-19 | 2021-06-14 | 2022-03-30 | 2022-06-14 | 2022-06-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31592020 | T2 DI DRM-GRS VLY-WMR 19/446 RPL STRW | 70Y
LC | 121572392 | 039/000 | T2 DI MNDCN WLLTS FRT BRGG 39/0 RPL ANCW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-21 | 2021-06-17 | 2022-05-14 | 2022-06-17 | 2022-06-17 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31540800 | EI MNDCN-WLLTS-FRT BRGG :0/10 REFRAME | 93E
LC | 121572399 | 039/000 | T2 DI MNDCN-WLTS-FRT BRGG 39/0 GRND WASH | WILLITS | ETL.7550.INSL.CERA | 2021-06-21 | 2021-06-17 | 2022-05-14 | 2022-06-17 | 2022-06-17 | On-time | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Contaminated | Insulator | Ground Wash | 45326363 | T2 DI MNDCN-WLTS-FRT BRGG 39/0 GRND WASH | ICD
LC | 121572414 | 039/000 | T2 DI MNDCN WLLTS FRT BRGG 39/0 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2021-06-21 | 2021-06-17 | 2022-10-01 | 2022-06-17 | 2022-06-17 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31606710 | T2 DI MNDCN WLLTS FRT BRGG 39/0 RPL INSW | 93I
LC | 121572530 | 023/208 | T2 DI ROUND MTN-CTNWD #2 23/208 RPR SHLS | TABLEMTN | ETL.5640.TOWR | 2021-06-21 | 2021-06-11 | 2022-07-24 | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215259 | T2 DI ROUND MTN-CTNWD #2 23/208 RPR SHLS | ICS
LC | 121572600 | 007/055 | T2 DI ROCK CREEK-POE 7/55 RPR HRDT | TABLEMTN | ETL.5630.TOWR | 2021-06-21 | 2021-06-16 | 2022-07-25 | 2022-06-16 | 2022-06-16 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45159497 | T2 DI ROCK CREEK-POE 7/55 RPR HRDT | ICQ
LC | 121572712 | 034/006 | T2 DI MDCNO-WLLTS-FRT BRG 34/6 RPR GRWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-21 | 2021-06-17 | 2022-05-22 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148591 | T2 DI MDCNO-WLLTS-FRT BRG 34/6 RPR GRWW | ICW
LC | 121572717 | 021/006 | T2 DI MDCN-WLTS-FRT BRG 21/6 STRW CMPLTD | WILLITS | ETL.7550.POLE.WOOD | 2021-06-21 | 2021-06-17 | 2022-08-21 | 2022-06-17 | 2022-06-17 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31595995 | T2 DI MDCNO-WLLTS-FRT BRG 21/6 RPL STRW | 70Y
LC | 121572925 | 012/244 | T2 DI CTTNWOOD-RED BLFF 012/244 RMV DBRS | TABLEMTN | ETL.6660.POLE.NWOD | 2021-06-21 | 2021-06-17 | 2022-06-06 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45197169 | T2 DI CTTNWOOD-RED BLFF 012/244 RMV DBRS | ICW
LC | 121573058 | 026/012 | T2 DI MNDCN WLLTS FRT BRG 26/12 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-21 | 2021-06-17 | 2022-05-19 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148566 | T2 DI MNDCN WLLTS FRT BRG 26/12 RPR GYWW | ICW
LC | 121573082 | 009/073 | T2 DI CARIBOU-TABLE MTN 9/73 INS HRDT | TABLEMTN | ETL.4440.TOWR | 2021-06-21 | 2021-06-16 | 2022-02-14 | 2022-06-16 | 2022-06-16 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45158375 | T2 DI CARIBOU-TABLE MTN 9/73 INS HRDT | ICQ
LC | 121573104 | 036/001 | T2 DI MDCNO-WLLTS-FRT BRG 36/1 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-21 | 2021-06-18 | 2022-08-20 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31595995 | T2 DI MDCNO-WLLTS-FRT BRG 21/6 RPL STRW | 70Y
LC | 121573314 | 038/005 | T2 DI MDCNO-WLLTS-FRT BRG 38/5 GRND WASH | WILLITS | ETL.7550.INSL.CERA | 2021-06-21 | 2021-06-17 | 2022-08-18 | 2022-06-17 | 2022-06-17 | Late | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | Contaminated | Insulator | Ground Wash | 45262572 | T2 DI MDCNO-WLLTS-FRT BRG 38/5 GRND WASH | ICD
LC | 121573440 | 012/080 | T2 DI CORTINA-VACA 12/80 RPLC DAMS | SACTO | ETL.4540.INSL.CERA | 2021-06-21 | 2021-06-16 | 2022-05-09 | 2022-06-16 | 2022-06-16 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 45200362 | T2 DI CORTINA-VACA 12/80 RPLC DAMS | ICS
LC | 121573463 | 009/197 | T2 DI KILARC-DESCHUTES 9/197 RPR CRSW | TABLEMTN | ETL.7300.POLE.WOOD | 2021-06-21 | 2021-06-16 | 2022-04-19 | 2022-06-16 | 2022-06-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45212344 | T2 DI KILARC-DESCHUTES 9/197 RPR CRSW | ICW
LC | 121573515 | 021/001 | T2 DI MDCNO-WLLTS-FRT BRG 21/1 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-21 | 2021-06-17 | 2022-08-20 | 2022-06-17 | 2022-06-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145829 | T2 DI MDCNO-WLLTS-FRT BRG 21/1 RPR GYWW | ICW
LC | 121573517 | 021/001 | T2 DI MDCNO-WLLTS-FRT BRG 21/1 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-21 | 2021-06-17 | 2022-08-20 | 2022-06-17 | 2022-06-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45145829 | T2 DI MDCNO-WLLTS-FRT BRG 21/1 RPR GYWW | ICW
LC | 121573570 | 003/003 | T2 DI LAYTONVILLE-COVELO 03/03 RPR GYWW | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-06-21 | 2021-06-18 | 2021-10-20 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44999931 | T2 DI LAYTONVILLE-COVELO 03/03 RPR GYWW | ICW
LC | 121573729 | 011/017 | T2 DI LWR LK-HMSTK TAP 11/17 RPL POLE | WILLITS | ETL.1481.POLE.WOOD | 2021-06-21 | 2021-06-15 | 2022-06-17 | 2022-06-15 | 2022-06-15 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31545143 | T2 DI LWR LK-HMSTK TAP 11/17 RPL POLE | 70Y
LC | 121573802 | 036/003 | T2 DI MDCNO-WLLTS-FRT BRG 36/3 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-21 | 2021-06-17 | 2022-05-15 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45148602 | T2NT DI MDNO-WLLTS-FRT BRG 36/3 RMV BUTT | ICW
LC | 121574383 | 025/011 | T2 DI MDCNO-WLLTS-FRT BRG 25/11 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-21 | 2021-06-18 | 2022-08-21 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31543104 | T2 DI MNDCN-WLTS-FRT BRG 25/0 RPL STRW | 70Y
LC | 121574958 | 019/002 | T2 DI MNDCN-WLTS-FRT BRG 19/2 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2021-06-21 | 2021-06-16 | 2022-08-24 | 2022-06-16 | 2022-06-16 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCL COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31551283 | T2 DI MNDCN-WLTS-FRT BRG 28/10 RPL INSW | 93I
LC | 121575010 | 019/002 | T2 DI MNDCN-WLTS-FRT BRG 19/2 RPL HRDW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-21 | 2021-06-16 | 2022-10-04 | 2022-06-16 | 2022-06-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45145820 | T2 DI MNDCN-WLTS-FRT BRG 19/2 RPL HRDW | ICW
LC | 121575118 | 001/013 | T2 DI TRINITY-COTTNWOOD 1/13 RPL INSS | TABLEMTN | ETL.4040.INSL.CERA | 2021-06-21 | 2021-06-18 | 2022-08-07 | 2022-06-18 | 2022-06-18 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546109 | T2 DI TRINITY-COTTNWOOD 1/13 RPL INSS | 93K
LC | 121575203 | 000/014 | T2 DI WISHON-COPPERMINE 000/014 RPR FOND | FRESNO | ETL.9330.TOWR | 2021-06-21 | 2021-06-17 | 2022-04-28 | 2022-06-17 | 2022-06-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45070445 | T2 DI WISHON-COPPERMINE 000/014 RPR FOND | ICQ
LC | 121575379 | 041/006 | T2 DI MNDCN-WLLTS-FRT BRGG 41/6 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-21 | 2021-06-17 | 2022-05-11 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45150034 | T2 DI MNDCN-WLLTS-FRT BRGG 41/6 RPR GYWW | ICW
LC | 121575608 | :000/012 | T2 DI MNDCNO-WLTS-FT BRG :0/12 RPR GYWW | WILLITS | ETL.7550.POLE.NWOD | 2021-06-21 | 2021-06-17 | 2022-10-01 | 2022-06-17 | 2022-06-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45144306 | T2 DI MNDCNO-WLTS-FT BRG :0/12 RPR GYWW | ICW
LC | 121575712 | 028/003 | T2 DI MNDO WLLTS FRT BRG 28/003 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-21 | 2021-06-18 | 2022-08-18 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31596073 | T2 EI MNDCN-WLTS-FRT BRG 21/5 RPL POLE | 70Y
LC | 121575743 | 002/015 | T2 WV STN ML SW ST-R 2/15 RPL HRDT CMPLT | VICTOR | ETL.3840.INSL.CERA | 2021-06-21 | 2021-06-21 | 2022-05-11 | 2022-06-21 | 2022-06-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair | 45122653 | T2 WV STN ML SW ST-RK JT 2/15 RPL HRDT | ICS
LC | 121576219 | 005/064 | T2 WV CLATE-SMRTVILLE #2 5/064 RPR SPLW | SACTO | ETL.6520.POLE.NWOD | 2021-06-21 | 2021-06-21 | 2022-07-18 | 2022-06-21 | 2022-06-21 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Splice-Steel | Repair | 45233400 | T2 WV CLATE-SMRTVILLE #2 5/064 RPR SPLW | ICS
LC | 121577958 | 085/002 | T2 DI HUMBLDT-TRNITY 85/2L RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-06-22 | 2021-06-08 | 2022-06-08 | 2022-06-08 | 2022-06-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW WATR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121578023 | 112/003 | T2 DI HUMBLDT-BRIDGEVILLE 112/3 RPL POLE | EUREKA | ETL.1810.POLE.WDPS | 2021-06-22 | 2021-06-08 | 2022-04-08 | 2022-06-08 | 2022-06-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544729 | T2 HUMBOLDT-BRIDGEVILLE 112/3 RPL POLE | 70Y
LC | 121578025 | 112/003 | T2 DI HUMBLDT-BRIDGEVILLE 112/3 RPL POLE | EUREKA | ETL.1810.POLE.WDPS | 2021-06-22 | 2021-06-08 | 2022-04-08 | 2022-06-08 | 2022-06-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544729 | T2 HUMBOLDT-BRIDGEVILLE 112/3 RPL POLE | 70Y
LC | 121578087 | 007/091 | T2 DI DRUM-SUMMIT #1 007/091 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-22 | 2021-06-08 | 2022-08-25 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544924 | T3 EI DRUM-SUMMIT #1 000/007 RPL STRW | 70Y
LC | 121578220 | 010/092 | T2 DI CRAG VIEW-CASCADE 10/92R RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-22 | 2021-06-08 | 2022-09-27 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121578280 | 025/000 | T2 DI MNDCN-WLTS-FRT BRG 25/0 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-22 | 2021-06-17 | 2022-05-21 | 2022-06-17 | 2022-06-17 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543104 | T2 DI MNDCN-WLTS-FRT BRG 25/0 RPL STRW | 70Y
LC | 121578286 | 002/020 | T2 DI BCKSCRK-RCKCRK CRSTA 2/20 RPR SPLS | TABLEMTN | ETL.4430.INSL | 2021-06-22 | 2021-06-18 | 2022-06-28 | 2022-06-18 | 2022-06-18 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45212512 | T2 DI BCKSCRK-RCKCRK CRSTA 2/20 RPR SPLS | ICS
LC | 121578547 | 049/001 | T2 EI HUMBOLDT-TRINITY 049/001 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-22 | 2021-06-22 | 2022-10-21 | 2022-06-22 | 2022-06-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31506039 | DI HUMBOLDT-TRINITY REPL POLES(ENG) | 70Y
LC | 121578581 | 049/001 | T2 EI HUMBOLDT-TRINITY 049/001 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-22 | 2021-06-22 | 2022-10-24 | 2022-06-22 | 2022-06-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31506039 | DI HUMBOLDT-TRINITY REPL POLES(ENG) | 70Y
LC | 121578925 | 030/002 | T2 DI MNDCNO-WLTS-FT BRG 30/002 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-22 | 2021-06-18 | 2022-05-16 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45148581 | T2 DI MNDCNO-WLTS-FT BRG 30/002 RPR STRW | ICW
LC | 121578928 | 085/430 | T2 DI MALIN-ROUND MTN #2 85/430 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-22 | 2021-06-18 | 2022-07-12 | 2022-06-18 | 2022-06-18 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215233 | T2 DI MALIN-ROUND MTN #2 85/430 RPR SHLS | ICS
LC | 121579400 | 011/226 | T2 DI COLGATE-PALERMO 011/226 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2021-06-22 | 2021-06-09 | 2021-08-14 | 2022-06-09 | 2022-06-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 44896596 | T2 DI COLGATE-PALERMO 011/226 RPR STRW | ICW
LC | 121579510 | 010/115 | T2 DI DRUM-SUMMIT #1 10/115 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-22 | 2021-06-08 | 2022-06-16 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543339 | T2 EI DRUM-SUMMIT #1 9/111 RPL STRW | 70Y
LC | 121579687 | 021/000 | T2 DI MNDCNO-WLTS-FT BRG 21/000 RPL HRDD | WILLITS | ETL.7550.POLE.WOOD | 2021-06-22 | 2021-06-17 | 2022-08-21 | 2022-06-17 | 2022-06-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45145828 | T2NT DI MNDCNO-WLTS-FT BRG 21/0 RPR GYWW | ICW
LC | 121579923 | 032/233 | T2 EI DRUM-RIO OSO #1 32/233 RPR STRT | SACTO | ETL.1420.TOWR | 2021-06-22 | 2021-06-22 | 2022-01-19 | 2022-06-22 | 2022-06-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45127785 | T2 EI DRUM-RIO OSO #1 32/233 RPR STRT | ICQ
LC | 121580093 | 013/140 | T2 DI RND MTN-CTTONWD #2 13/140 RPR OPGW | TABLEMTN | ETL.5640.TOWR | 2021-06-22 | 2021-06-17 | 2022-07-22 | 2022-06-17 | 2022-06-17 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215258 | T2 DI RND MTN-CTTONWD #2 13/140 RPR OPGW | ICS
LC | 121580186 | :019/010 | T2 EI EAGLE ROCK-REDBUD :19/10 RPR GYWW | LAKEVLLE | ETL.1480.POLE.WDPS | 2021-06-22 | 2021-06-22 | 2022-01-20 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45061765 | T2 EI EAGLE ROCK-REDBUD :19/10 RPR GYWW | ICW
LC | 121580212 | 033/134 | T2 DI DIABLO-MIDWAY #2 33/134 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-06-22 | 2021-06-22 | 2022-06-03 | 2022-06-22 | 2022-06-22 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068562 | T2 DI DIABLO-MIDWAY #2 33/134 RPR GYWS | ICS
LC | 121580225 | :019/010 | T2 EI EAGLE ROCK-REDBUD :19/10 RPR GYWW | LAKEVLLE | ETL.1480.POLE.WDPS | 2021-06-22 | 2021-06-22 | 2022-01-20 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45061764 | T2 EI EAGLE ROCK-REDBUD :19/10 RPR GYWW | ICW
LC | 121580251 | :019/010 | T2 EI EAGLE ROCK-REDBUD :19/10 RPR GYWW | LAKEVLLE | ETL.1480.POLE.WDPS | 2021-06-22 | 2021-06-22 | 2022-01-20 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45061763 | T2 EI EAGLE ROCK-REDBUD :19/10 RPR GYWW | ICW
LC | 121580389 | 085/431 | T2 DI MALIN-ROUND MTN #2 85/431 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-22 | 2021-06-22 | 2022-07-12 | 2022-06-22 | 2022-06-22 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215232 | T2 DI MALIN-ROUND MTN #2 85/431 RPR SHLS | ICS
LC | 121580687 | 006/002 | T2 EI MENDOCINO-UKIAH 6/2L RPL POLE | WILLITS | ETL.2420.POLE.WDPS | 2021-06-22 | 2021-06-22 | 2022-07-12 | 2022-06-22 | 2022-06-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544735 | T2 EI MENDOCINO-UKIAH 3/1R RPL STRW | 70Y
LC | 121580750 | 006/002 | T2 EI MENDOCINO-UKIAH 6/2R RPL POLE | WILLITS | ETL.2420.POLE.WDPS | 2021-06-22 | 2021-06-22 | 2022-07-12 | 2022-06-22 | 2022-06-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544735 | T2 EI MENDOCINO-UKIAH 3/1R RPL STRW | 70Y
LC | 121580874 | 037/005 | T2 DI MNDCN-WLLT-FRT BRGG 37/5 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-22 | 2021-06-17 | 2022-08-19 | 2022-06-17 | 2022-06-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45148608 | T2 EI MNDCN-WLLTS-FRT BRGG 37/5 RPR GYWW | ICW
LC | 121580947 | 023/277 | T2 DI DRUM-SUMMIT #2 23/277 C RPR SPLW | SACTO | ETL.1450.INSL.NCER | 2021-06-22 | 2021-06-18 | 2022-06-09 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45200368 | T2 DI DRUM-SUMMIT #2 23/277 C RPR SPLW | ICW
LC | 121580992 | 023/277 | T2 DI DRUM-SUMMIT #2 23/277 L RPR GYWW | SACTO | ETL.1450.POLE.STPS | 2021-06-22 | 2021-06-18 | 2022-06-09 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45200371 | T2 DI DRUM-SUMMIT #2 23/277 L RPR GYWW | ICW
LC | 121581169 | 032/005 | T2 DI MNDCN-WLTS-FRT BRG 32/5 RPLC DAMW | WILLITS | ETL.7550.INSL.NCER | 2021-06-22 | 2021-06-18 | 2022-05-16 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace | 45148583 | T2 DI MNDCN-WLTS-FRT BRG 32/5 RPLC DAMW | ICW
LC | 121581421 | 032/005 | T2 DI MNDCN-WLTS-FRT BRG 32/5 RPR ANCW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-22 | 2021-06-18 | 2022-05-16 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45148583 | T2 DI MNDCN-WLTS-FRT BRG 32/5 RPLC DAMW | ICW
LC | 121581509 | 032/005 | T2 DI MNDCN-WLTS-FRT BRG 32/5 RPR HRDW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-22 | 2021-06-18 | 2022-05-16 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45148583 | T2 DI MNDCN-WLTS-FRT BRG 32/5 RPLC DAMW | ICW
LC | 121581538 | 032/005 | T2 DI MNDCN-WLTS-FRT BRG 32/5 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-22 | 2021-06-18 | 2022-05-16 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148583 | T2 DI MNDCN-WLTS-FRT BRG 32/5 RPLC DAMW | ICW
LC | 121581632 | 039/157 | T2 DI DIABLO-MIDWAY #3 39/157 RPR JUMS | PISMOBCH | ETL.5980.INSL.NCER | 2021-06-22 | 2021-06-22 | 2022-01-11 | 2022-06-22 | 2022-06-22 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Jumper-Steel | Repair | 45068626 | T2 DI DIABLO-MIDWAY #3 39/157 RPR JUMS | ICS
LC | 121581683 | 026/312 | T2 EI DRUM-SUMMIT #1 26/312L RPL PL | SACTO | ETL.1440.POLE.WDPS | 2021-06-22 | 2021-06-12 | 2021-08-22 | 2022-06-12 | 2022-06-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544594 | T2 DRUM-SUMMIT #1 26/312R RPL PL | 70Y
LC | 121581686 | 019/220 | T2 DI DRUM-SUMMIT #1 19/220R RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-22 | 2021-06-08 | 2022-09-17 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31581111 | T2 DI DRUM-SUMMIT #1 19/220 RPL STRW | 70Y
LC | 121583067 | 035/258 | T2 EI CARIBOU-TABLE MTN 35/258 RMV VEG | TABLEMTN | ETL.4440.TOWR | 2021-06-22 | 2021-06-22 | 2022-08-18 | 2022-06-22 | 2022-06-22 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB SR22 | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121583083 | 019/079 | T2 DI TESLA-METCALF 19/79 RPR GYWS | METCALF | ETL.6110.TOWR | 2021-06-22 | 2021-06-16 | 2022-07-07 | 2022-06-16 | 2022-06-16 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45233301 | T2 DI TESLA-METCALF 19/79 RPR GYWS | ICS
LC | 121583088 | 029/123 | T2 DI MSS LNDING-METCALF 29/123 RPR GYWS | MOSSLNDG | ETL.6050.TOWR | 2021-06-22 | 2021-06-17 | 2022-08-09 | 2022-06-17 | 2022-06-17 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45149712 | T2 DI MSS LNDING-METCALF 29/123 RPR GYWS | ICS
LC | 121583253 | 090/460A | T2 DI MALIN-ROUND MTN #2 90/460 INS HRDT | TABLEMTN | ETL.6020.TOWR | 2021-06-22 | 2021-06-18 | 2022-07-15 | 2022-06-18 | 2022-06-18 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45198270 | T2 DI MALIN-ROUND MTN #2 90/460 INS HRDT | ICQ
LC | 121583380 | 000/007B | T2 CLGT-SMRTVLLE #2 000/007B RPL ANCW | SACTO | ETL.6520.POLE.WOOD | 2021-06-22 | 2021-06-22 | 2021-08-31 | 2022-06-22 | 2022-06-22 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31544901 | T2 CLGT-SMRTVLLE #2 000/007B RPL ANCW | 93E
LC | 121583382 | A000/016 | T2 SMRTVLL-CMP FR WST A0/16 RPL STRW | SACTO | ETL.7970.POLE.WOOD | 2021-06-22 | 2021-06-22 | 2022-07-13 | 2022-06-22 | 2022-06-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544760 | T2 SMRTVLL-CMP FR WST A0/16 RPL STRW | 70Y
LC | 121584073 | 093/014 | T2 DI HUMBOLDT-TRINITY 93/14L RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-06-23 | 2021-06-09 | 2022-10-08 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121584249 | 041/004 | T2 DI MNDCNO-WLTS-FRT BRG 41/4 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-23 | 2021-06-17 | 2022-05-13 | 2022-06-17 | 2022-06-17 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543104 | T2 DI MNDCN-WLTS-FRT BRG 25/0 RPL STRW | 70Y
LC | 121584271 | 037/006 | T2 DI MNDCN-WLTS-FRT BRG 37/6 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-23 | 2021-06-17 | 2022-05-14 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45148609 | T2 DI MNDCN-WLTS-FRT BRG 37/6 RPR STRW | ICW
LC | 121584273 | 037/006 | T2 DI MNDCN-WLTS-FRT BRG 37/6 RPR SPLW | WILLITS | ETL.7550.INSL.NCER | 2021-06-23 | 2021-06-17 | 2022-05-14 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45148609 | T2 DI MNDCN-WLTS-FRT BRG 37/6 RPR STRW | ICW
LC | 121584276 | 092/002 | T2 DI HUMBOLDT-TRINITY 92/2 RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-06-23 | 2021-06-09 | 2022-06-07 | 2022-06-09 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121584286 | 005/049 | T2 EI UKIAH-HOPLAND 005/049L RPL POLE | WILLITS | ETL.4050.POLE.WDPS | 2021-06-23 | 2021-06-22 | 2022-05-05 | 2022-06-22 | 2022-06-22 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545800 | T2 EI UKIAH-HOPLAND RPL POLE IN 6 TWRS. | 70Y
LC | 121584296 | 005/049 | T2 EI UKIAH-HOPLAND 005/049R RPL POLE | WILLITS | ETL.4050.POLE.WDPS | 2021-06-23 | 2021-06-22 | 2022-05-05 | 2022-06-22 | 2022-06-22 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545800 | T2 EI UKIAH-HOPLAND RPL POLE IN 6 TWRS. | 70Y
LC | 121584299 | 010/090 | T2 EI UKIAH-HOPLAND 010/090L RPL INSW | LAKEVLLE | ETL.4050.INSL.CERA | 2021-06-23 | 2021-06-22 | 2022-01-26 | 2022-06-22 | 2022-06-22 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545619 | T2 EI UKIAH-HOPLAND 002/024 RPR INSW | 93I
LC | 121584300 | 009/087 | T2 EI UKIAH-HOPLAND 009/087L RPL INSW | LAKEVLLE | ETL.4050.INSL.CERA | 2021-06-23 | 2021-06-22 | 2022-01-26 | 2022-06-22 | 2022-06-22 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545619 | T2 EI UKIAH-HOPLAND 002/024 RPR INSW | 93I
LC | 121584320 | 092/002 | T2 DI HUMBOLDT-TRINITY 92/2 RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-06-23 | 2021-06-09 | 2022-06-07 | 2022-06-09 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121584371 | 018/221 | T2 DI DRUM-SUMMIT #2 18/221R RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2021-06-23 | 2021-06-18 | 2022-08-17 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545492 | T2 DI DRUM-SUMMIT #2 18/221L RPL STRW | 70Y
LC | 121584373 | 020/169 | T2 DI CRAG VIEW-CASCADE 20/169 RPR CNDW | TABLEMTN | ETL.1350.INSL.NCER | 2021-06-23 | 2021-06-17 | 2022-09-14 | 2022-06-17 | 2022-06-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair | 45500237 | T2 DI CRAG VIEW-CASCADE 20/169 RPR CNDW | ICW
LC | 121584541 | 003/029 | EI T2 PIT #7 TAP 3/29 RPR SWITCH | TABLEMTN | ETL.5442.SWIT | 2021-06-23 | 2021-06-23 | 2022-09-08 | 2022-06-23 | 2022-06-23 | Late | 623 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | Out of Adjustment | Switch | Repair | 45213886 | EI T2 PIT #7 TAP 3/29 RPR SWITCH | ICE
LC | 121584621 | 024/297 | T2 EI DRUM-SUMMIT#2 24/297L RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-23 | 2021-06-10 | 2022-10-03 | 2022-06-10 | 2022-06-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121584738 | 005/005 | T2 EI MENDOCINO-UKIAH 5/5C RPL STRW | WILLITS | ETL.2420.POLE.STPS | 2021-06-23 | 2021-06-23 | 2022-07-18 | 2022-06-23 | 2022-06-23 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544814 | T2 EI MENDOCINO-UKIAH 5/5L RPL STRW | 70Y
LC | 121584778 | 005/005 | T2 EI MENDOCINO-UKIAH 5/5R RPL STRW | WILLITS | ETL.2420.POLE.STPS | 2021-06-23 | 2021-06-23 | 2022-07-18 | 2022-06-23 | 2022-06-23 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544814 | T2 EI MENDOCINO-UKIAH 5/5L RPL STRW | 70Y
LC | 121585246 | 031/002 | T2 DI GRBRVL-LYTNVL 031/002R RPR GYWW | EUREKA | ETL.8365.POLE.STPS | 2021-06-23 | 2021-06-18 | 2021-11-17 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45070126 | T2 DI GRBRVL-LYTNVL 031/002R RPR GYWW | ICW
LC | 121586230 | 015/076 | T2 EI CNTRACSTA-MRGA#1 15/76 RPR FOND | CONCORD | ETL.5452.TOWR | 2021-06-23 | 2021-04-21 | 2022-01-11 | 2022-04-21 | 2022-04-21 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45121151 | T2 EI CNTRACSTA-MRGA#1 15/76 RPR FOND | ICQ
LC | 121586418 | 018/153 | T2 DI CRG VW CSCD 18/153L RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-23 | 2021-06-09 | 2022-09-14 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31552992 | T2 EI CRAG VIEW-CASCDE 18/154R RPL STRW | 70Y
LC | 121586465 | 009/083 | T2 EI UKIAH-HOPLAND 009/083 RPL INSW | LAKEVLLE | ETL.4050.INSL.CERA | 2021-06-23 | 2021-06-23 | 2022-01-26 | 2022-06-23 | 2022-06-23 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545619 | T2 EI UKIAH-HOPLAND 002/024 RPR INSW | 93I
LC | 121586489 | 003/054 | T2 EI MANVILLE TAP 3/54L RPR GYWW | PISMOBCH | ETL.1372.POLE.STPS | 2021-06-23 | 2021-06-23 | 2022-05-17 | 2022-06-23 | 2022-06-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45098806 | T2 EI MANVILLE TAP 3/54L RPR GYWW | ICW
LC | 121586707 | 003/054 | T2 EI MANVILLE TAP 3/54C RPR GYWW | PISMOBCH | ETL.1372.POLE.STPS | 2021-06-23 | 2021-06-23 | 2022-05-17 | 2022-06-23 | 2022-06-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45098810 | T2 EI MANVILLE TAP 3/54C RPR GYWW | ICW
LC | 121586789 | 003/054 | T2 EI MANVILLE TAP 3/54R RPR GYWW | PISMOBCH | ETL.1372.POLE.STPS | 2021-06-23 | 2021-06-23 | 2022-05-17 | 2022-06-23 | 2022-06-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45098805 | T2 EI MANVILLE TAP 3/54R RPR GYWW | ICW
LC | 121586843 | 019/156 | T2 CARBERRY SS-RO MTN 19/156 RPR FOND | TABLEMTN | ETL.5410.TOWR | 2021-06-23 | 2021-04-21 | 2022-07-21 | 2022-04-21 | 2022-04-21 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160930 | T2 CARBERRY SS-RO MTN 19/156 RPR FOND | ICQ
LC | 121586877 | 017/140 | T2 DI CRAG VIEW-CASCADE 017/140 RPL STRW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-06-23 | 2021-06-09 | 2022-09-14 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31552992 | T2 EI CRAG VIEW-CASCDE 18/154R RPL STRW | 70Y
LC | 121586900 | 003/053 | T2 EI MANVILLE TAP 3/53R RPR GYWW | PISMOBCH | ETL.1372.POLE.STPS | 2021-06-23 | 2021-06-23 | 2022-05-17 | 2022-06-23 | 2022-06-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45098803 | T2 EI MANVILLE TAP 3/53R RPR GYWW | ICW
LC | 121586965 | 003/053 | T2 EI MANVILLE TAP 3/53C RPR GYWW | PISMOBCH | ETL.1372.POLE.STPS | 2021-06-23 | 2021-06-23 | 2022-05-17 | 2022-06-23 | 2022-06-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45098812 | T2 EI MANVILLE TAP 3/53C RPR GYWW | ICW
LC | 121587034 | 003/053 | T2 EI MANVILLE TAP 3/53L RPR GYWW | PISMOBCH | ETL.1372.POLE.STPS | 2021-06-23 | 2021-06-23 | 2022-05-17 | 2022-06-23 | 2022-06-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45098813 | T2 EI MANVILLE TAP 3/53L RPR GYWW | ICW
LC | 121587045 | 082/002 | T2 DI HUMBOLDT-TRINITY 82/2 RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-06-23 | 2021-06-09 | 2022-03-29 | 2022-06-09 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31591946 | T2 DI HUMBOLDT-TRINITY 82/2L RPL POLE | 70Y
LC | 121587537 | 009/059 | T2 DI MORAGA-SAN LNDR #3 9/59 RPLC INSS | CONCORD | ETL.2790.INSL | 2021-06-23 | 2021-06-22 | 2022-04-27 | 2022-06-22 | 2022-06-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549067 | T3 DI MRGA-SN LNDRO #3 RPL INSS 5TWRS | 93K
LC | 121587609 | 016/166 | T2 DI RND MTN-CTTNWD #2 16/166 RPL INSS | TABLEMTN | ETL.5640.INSL | 2021-06-23 | 2021-06-22 | 2022-07-30 | 2022-06-22 | 2022-06-22 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548821 | T2 DI ROUND MTN-CTNWD #2 RPL INSS 5TWRS | 93K
LC | 121587680 | 003/001 | T2 EI MENDOCINO-UKIAH 3/1L RPL STRW | WILLITS | ETL.2420.POLE.WDPS | 2021-06-23 | 2021-06-23 | 2022-07-14 | 2022-06-23 | 2022-06-23 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544735 | T2 EI MENDOCINO-UKIAH 3/1R RPL STRW | 70Y
LC | 121587697 | 003/001 | T2 EI MENDOCINO-UKIAH 3/1C RPL STRW | WILLITS | ETL.2420.POLE.WDPS | 2021-06-23 | 2021-06-23 | 2022-07-14 | 2022-06-23 | 2022-06-23 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544735 | T2 EI MENDOCINO-UKIAH 3/1R RPL STRW | 70Y
LC | 121587778 | 003/001 | T2 EI MENDOCINO-UKIAH 3/1R RPL STRW | WILLITS | ETL.2420.POLE.WDPS | 2021-06-23 | 2021-06-23 | 2022-07-14 | 2022-06-23 | 2022-06-23 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544735 | T2 EI MENDOCINO-UKIAH 3/1R RPL STRW | 70Y
LC | 121587791 | 016/166 | T2 DI RND MTN-CTTNWD #2 16/166 RMV VEG | TABLEMTN | ETL.5640.TOWR | 2021-06-23 | 2021-06-22 | 2022-08-31 | 2022-06-22 | 2022-06-22 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121587877 | 016/299 | T2 DI FULTON-MLN-COTATI 16/299 RPR SPLW | LAKEVLLE | ETL.6910.INSL.NCER | 2021-06-23 | 2021-06-22 | 2022-02-15 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45138288 | T2 DI FULTON-MLN-COTATI 16/299 RPR SPLW | ICW
LC | 121587934 | 029/439 | T2 DI CLAY-MARTEL 029/439 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-06-23 | 2021-06-22 | 2022-02-01 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45067386 | T2 DI CLAY-MARTEL 029/439 RPR STRW | ICW
LC | 121588310 | 009/040 | T2 DI PTTSBRG-TSL #1 9/40 RPL HANGER | CONCORD | ETL.5510.INSL.CERA | 2021-06-23 | 2021-06-22 | 2022-05-06 | 2022-06-22 | 2022-06-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44929311 | T2 DI PTTSBRG-TSL #1 9/40 RPL HRDT | ICQ
LC | 121588480 | 009/060 | T2 DI MRAGA-SAN LEANDRO #3 9/60 RPL INSS | CONCORD | ETL.2790.INSL | 2021-06-23 | 2021-06-22 | 2022-04-27 | 2022-06-22 | 2022-06-22 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549067 | T3 DI MRGA-SN LNDRO #3 RPL INSS 5TWRS | 93K
LC | 121588732 | 053/264 | T2 WV MENDOCINO-REDBUD 53/264 INS DAMS | WILLITS | ETL.2410.INSL.CERA | 2021-06-23 | 2021-06-23 | 2022-08-27 | 2022-06-23 | 2022-06-23 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install | 45142188 | T2 WV MENDOCINO-REDBUD 53/264 INS DAMS | ICS
LC | 121588980 | 032/234 | T2 EI CARIBOU-TABLE MTN 32/234 RPR FOND | TABLEMTN | ETL.4440.TOWR | 2021-06-23 | 2021-06-23 | 2022-07-08 | 2022-06-23 | 2022-06-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45108131 | T2 EI CARIBOU-TABLE MTN 32/234 RPR FOND | ICQ
LC | 121589116 | 015/348 | T2 WV DRM-GRSS VLLY-WMR 15/3 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2021-06-23 | 2021-06-23 | 2021-08-31 | 2022-06-23 | 2022-06-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44891916 | T2 WV DRM-GRSS VLLY-WMR 15/3 RPR STRW | ICW
LC | 121589228 | 008/135 | T2 DI SSQC-SNT YNZ SW ST 8/135 RPL INSW | PISMOBCH | ETL.3700.INSL.CERA | 2021-06-23 | 2021-06-22 | 2022-04-11 | 2022-06-22 | 2022-06-22 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543110 | DI SISQUOC-SANTA YNEZ 2/45 RPL INSW | 93I
LC | 121589349 | 024/000 | T2 DI PHILO JCT-ELK 24/000 RPR STRW | WILLITS | ETL.7780.POLE.WOOD | 2021-06-23 | 2021-06-17 | 2022-03-14 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45142670 | T2 DI PHILO JCT-ELK 24/000 RPR STRW | ICW
LC | 121590609 | 027/197 | T2 DI CARIBOU-TABLE MTN 27/197 RPL INSS | TABLEMTN | ETL.4440.INSL | 2021-06-24 | 2021-06-23 | 2022-07-15 | 2022-06-23 | 2022-06-23 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121590792 | B018/418 | T2 DI DRM-GRS VLY-WMR B18/418 RPL INSW | SACTO | ETL.6760.INSL.CERA | 2021-06-24 | 2021-06-22 | 2022-04-20 | 2022-06-22 | 2022-06-22 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31540566 | T2 DI DRUM-GRS VLY-WMR 16/369 RPLC INSWC | 93I
LC | 121590795 | B018/418 | T2 DI DRM-GRS VLY-WMR B18/418 RMV VEG | SACTO | ETL.6760.POLE.WOOD | 2021-06-24 | 2021-06-22 | 2022-02-22 | 2022-06-22 | 2022-06-22 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121590796 | B018/418 | T2 DI DRM-GRS VLY-WMR B18/418 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-06-24 | 2021-06-22 | 2022-04-20 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44944951 | T2 DI DRM-GRS VLY-WMR B18/418 RPR GYWW | ICW
LC | 121590844 | 012/165 | T2 DI WATSONVLLE-SALINAS 12/165 RPR SPLW | MOSSLNDG | ETL.8310.POLE.WOOD | 2021-06-24 | 2021-06-22 | 2021-10-14 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Splice-Wood | Repair | 44981674 | T2 DI WATSONVLLE-SALINAS 12/165 RPR SPLW | ICW
LC | 121590871 | R002/019 | T2 DI RND MTN-CTTNWD #3 R2/19 RPL HRDT | TABLEMTN | ETL.5650.TOWR | 2021-06-24 | 2021-06-17 | 2022-01-31 | 2022-06-17 | 2022-06-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45111986 | T2 DI RND MTN-CTTNWD #3 R2/19 RPL HRDT | ICQ
LC | 121591200 | 016/319 | T2 DI COLGATE PLM 16/319 RPL STRW CMPT | SACTO | ETL.6500.POLE.WOOD | 2021-06-24 | 2021-06-22 | 2022-05-08 | 2022-06-22 | 2022-06-22 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540562 | T2 DI COLGATE-PALERMO 7/135 RPLC STRW | 70Y
LC | 121591302 | 016/319 | T2 DI COLGATE PALERMO 16/319 RMV VEG | TABLEMTN | ETL.6500.POLE.WOOD | 2021-06-24 | 2021-06-22 | 2022-08-04 | 2022-06-22 | 2022-06-22 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121591743 | 005/002 | T2 DI LAYTONVILLE-COVELO 5/2R RPL STRW | WILLITS | ETL.7390.POLE.WDPS | 2021-06-24 | 2021-06-18 | 2022-06-07 | 2022-06-18 | 2022-06-18 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544833 | T2 DI LAYTONVILLE-COVELO 5/2L RPL STRW | 70Y
LC | 121591746 | 005/002 | T2 DI LAYTONVILLE-COVELO 5/2L RPL STRW | WILLITS | ETL.7390.POLE.WDPS | 2021-06-24 | 2021-06-18 | 2022-06-07 | 2022-06-18 | 2022-06-18 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544833 | T2 DI LAYTONVILLE-COVELO 5/2L RPL STRW | 70Y
LC | 121591800 | 005/002 | T2 DI LAYTONVILLE-COVELO 5/2C RPL STRW | WILLITS | ETL.7390.POLE.WDPS | 2021-06-24 | 2021-06-18 | 2022-06-07 | 2022-06-18 | 2022-06-18 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544833 | T2 DI LAYTONVILLE-COVELO 5/2L RPL STRW | 70Y
LC | 121591927 | 022/267 | T2 DI DRUM-SUMMIT #1 22/267L RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-24 | 2021-06-23 | 2022-06-29 | 2022-06-23 | 2022-06-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45193595 | T2 DI DRUM-SUMMIT #1 22/267L RPR STRW | ICW
LC | 121591936 | 024/342 | T2 DI CLAY-MARTEL 24/342 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-06-24 | 2021-06-22 | 2022-07-19 | 2022-06-22 | 2022-06-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45110676 | T2 DI CLAY-MARTEL 24/342 RPR GYWW | ICW
LC | 121591939 | 015/186 | T2 DI WST PNT-VLY SPRNGS 15/186 RMV DBRS | VICTOR | ETL.8350.POLE.NWOD | 2021-06-24 | 2021-06-22 | 2022-05-10 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45156990 | T2 DI WST PNT-VLY SPRNGS 15/186 RMV DBRS | ICW
LC | 121592086 | 041/005 | T2 DI MDCN-WLLTS-FRT BRGG 41/5 RPR SPLW | WILLITS | ETL.7550.INSL.NCER | 2021-06-24 | 2021-06-23 | 2022-05-11 | 2022-06-23 | 2022-06-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45150033 | T2 DI MDCN-WLLTS-FRT BRGG 41/5 RPR SPLW | ICW
LC | 121592098 | 017/002 | T2 EI CLEAR LAKE-KONOCTI 17/2 RMV BUTT | LAKEVLLE | ETL.6852.POLE.WOOD | 2021-06-24 | 2021-06-24 | 2022-02-02 | 2022-06-24 | 2022-06-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45138167 | T2 EI CLEAR LAKE-KONOCTI 17/2 RMV BUTT | ICW
LC | 121592138 | 017/002 | T2 EI CLEAR LAKE-KONOCTI 17/2 RPL HRDD | LAKEVLLE | ETL.6852.POLE.WOOD | 2021-06-24 | 2021-06-24 | 2022-02-02 | 2022-06-24 | 2022-06-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45138168 | T2 EI CLEAR LAKE-KONOCTI 17/2 RPL HRDD | ICW
LC | 121592532 | A002/053 | WV T2 VALLEY SPRINGS #1 A2/53 RPR SPLW | VICTOR | ETL.8210.POLE.WOOD | 2021-06-24 | 2021-06-24 | 2021-08-08 | 2022-06-24 | 2022-06-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Splice-Wood | Repair | 44943423 | WV T2 VALLEY SPRINGS #1 A2/53 RPR SPLW | ICW
LC | 121592622 | 037/004 | T2 DI MDCNO-WLLTS-FT BRG 37/004 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-24 | 2021-06-18 | 2022-05-14 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148607 | T2 DI MDCNO-WLLTS-FT BRG 37/004 RPR GYWW | ICW
LC | 121593404 | 000/004 | T2 WV MORRO BAY SLO #1 0/4 INS DAMS | PISMOBCH | ETL.2810.INSL.NCER | 2021-06-24 | 2021-06-24 | 2022-01-20 | 2022-06-24 | 2022-06-24 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Steel | Install | 45098847 | T2 WV MORRO BAY SLO #1 0/4 INS DAMS | ICS
LC | 121593542 | 016/137 | T2 DI CRAG VIEW-CASCADE 16/137 RPL INSW | TABLEMTN | ETL.1350.INSL.CERA | 2021-06-24 | 2021-06-18 | 2022-09-13 | 2022-06-18 | 2022-06-18 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543332 | T2 DI CRAG VIEW-CASCADE 15/128 RPL INSW | 93I
LC | 121593543 | 016/137 | T2 DI CRAG VIEW-CASCADE 16/137 RPR SHLW | TABLEMTN | ETL.1350.INSL.CERA | 2021-06-24 | 2021-06-18 | 2022-09-19 | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45500238 | T2 DI CRAG VIEW-CASCADE 16/137 RPR SHLW | ICW
LC | 121593874 | 002/006 | T2 DI RIO DELL TAP 2/6 RPR SPLW | EUREKA | ETL.7851.INSL.NCER | 2021-06-24 | 2021-06-23 | 2022-06-26 | 2022-06-23 | 2022-06-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45158750 | T2 DI RIO DELL TAP 2/6 RPR SPLW | ICW
LC | 121594444 | 029/129 | WV T2 FULTON-LAKEVILLE 29/129 RPL HRDT | LAKEVLLE | ETL.4950.TOWR | 2021-06-24 | 2021-06-24 | 2022-10-03 | 2022-06-24 | 2022-06-24 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45144130 | WV T2 FULTON-LAKEVILLE 29/129 RPL HRDT | ICQ
LC | 121595387 | 016/078 | T2 DI MOSS LDNG-LS BNS 16/78 RPR SHLS | MOSSLNDG | ETL.6040.TOWR | 2021-06-24 | 2021-06-24 | 2021-07-11 | 2022-06-24 | 2022-06-24 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44894674 | T2 DI MOSS LDNG-LS BNS 16/78 RPR SHLS | ICS
LC | 121595468 | 006/057 | T2 EI CTTNWD-BNTN #2 6/57L RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-06-24 | 2021-06-24 | 2022-07-23 | 2022-06-24 | 2022-06-24 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45213104 | T2 EI CTTNWD-BNTN #2 6/57L RPR STRW | ICW
LC | 121595514 | 006/057 | T2 EI CTTNWD-BNTN #2 6/57R RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-06-24 | 2021-06-24 | 2022-07-23 | 2022-06-24 | 2022-06-24 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45213105 | T2 EI CTTNWD-BNTN #2 6/57R RPR STRW | ICW
LC | 121595686 | 016/329 | T2 DI COLGATE-PALERMO 16/239 RPR GYWW | SACTO | ETL.6500.POLE.WOOD | 2021-06-24 | 2021-06-22 | 2022-05-06 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45200374 | T2 DI COLGATE-PALERMO 16/239 RPR GYWW | ICW
LC | 121595775 | 000/009 | T2 WV CLGT-SMARTVILLE #2 0/9 RPL SPLW | SACTO | ETL.6520.INSL.NCER | 2021-06-24 | 2021-06-24 | 2022-07-18 | 2022-06-24 | 2022-06-24 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Replace | 45233401 | T2 WV CLGT-SMARTVILLE #2 0/9 RPL SPLW | ICW
LC | 121595802 | 026/318 | T2 DI DRUM-SUMMIT #2 26/318L RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-24 | 2021-06-23 | 2022-07-15 | 2022-06-23 | 2022-06-21 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544720 | EI DRUM-SUMMIT#2 26/320 RPL POLE | 70Y
LC | 121596097 | 034/140 | T2 DI DIABLO-MIDWAY #2 034/140 RMV NEST | PISMOBCH | ETL.5970.TOWR | 2021-06-24 | 2021-06-22 | 2022-01-26 | 2022-06-22 | 2022-06-22 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45068563 | T2 DI DIABLO-MIDWAY #2 034/140 RMV NEST | ICS
LC | 121596342 | 065/326 | T2 DI MALIN-ROUND MTN #2 65/326 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-06-24 | 2021-06-24 | 2022-08-09 | 2022-06-24 | 2022-06-24 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45240553 | T2 DI MALIN-ROUND MTN #2 65/326 RPR GYWS | ICS
LC | 121596351 | 002/024 | T2 EI UKIAH-HOPLAND 002/024 RPL INSW | LAKEVLLE | ETL.4050.INSL.CERA | 2021-06-24 | 2021-06-24 | 2022-01-27 | 2022-06-24 | 2022-06-24 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545619 | T2 EI UKIAH-HOPLAND 002/024 RPR INSW | 93I
LC | 121596401 | 006/081 | T2 WV DVDE-CBRLL #2 6/81 INS DAMW | PISMOBCH | ETL.1370.POLE.WDPS | 2021-06-24 | 2021-06-24 | 2021-11-22 | 2022-06-24 | 2022-06-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 44963080 | T2 WV DVDE-CBRLL #2 6/81 INS DAMW | ICW
LC | 121596410 | :004/000 | T2 DI BLTA RVK MLNS SS :004/000 RPR ANCW | VICTOR | ETL.1070.POLE.NWOD | 2021-06-24 | 2021-06-22 | 2022-02-24 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45156991 | T2 DI BLTA RVK MLNS SS :004/000 RPR ANCW | ICW
LC | 121596748 | 025/201 | T2 DI PIT #1-COTTONWOOD 25/201 RMV VEG | TABLEMTN | ETL.5390.TOWR | 2021-06-24 | 2021-06-11 | 2022-01-12 | 2022-06-11 | 2022-06-11 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121596769 | 000/032 | T2 DI HMLTN BRNCH CHSTR 0/32 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-06-24 | 2021-06-22 | 2022-07-25 | 2022-06-22 | 2022-06-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45213377 | T2 DI HMLTN BRNCH CHSTR 0/32 RPR STRW | ICW
LC | 121596815 | 016/306 | T2 DI FLTN MLNO CTTI 16/306 RMV VEG | LAKEVLLE | ETL.6910.POLE.WOOD | 2021-06-24 | 2021-06-22 | 2022-04-05 | 2022-06-22 | 2022-06-22 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121596830 | 003/032 | T2 DI BCKS CRK/RK CRK CRS 3/32 RPR FOND | TABLEMTN | ETL.4430.TOWR | 2021-06-24 | 2021-06-18 | 2022-06-27 | 2022-06-18 | 2022-06-18 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160924 | T2 DI BCKS CRK/RK CRK CRS 3/32 RPR FOND | ICQ
LC | 121596839 | 006/031 | T2 DI DIABLO-GATES #1 006/031 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2021-06-24 | 2021-06-22 | 2022-07-11 | 2022-06-22 | 2022-06-22 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068477 | T2 DI DIABLO-GATES #1 006/031 RPR GYWS | ICS
LC | 121596914 | 014/109 | T2 EI CARIBOU-TABLE MTN 14/109 RPR JUMS | TABLEMTN | ETL.4440.TOWR | 2021-06-24 | 2021-06-24 | 2022-06-23 | 2022-06-24 | 2022-06-24 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Jumper-Steel | Repair | 45212447 | T2 EI CARIBOU-TABLE MTN 14/109 RPR JUMS | ICS
LC | 121596974 | 013/142 | T2 DI RND MTN-CTTNWD #2 13/142 RPR SHLS | TABLEMTN | ETL.5640.TOWR | 2021-06-24 | 2021-06-17 | 2022-07-23 | 2022-06-17 | 2022-06-17 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215257 | T2 DI RND MTN-CTTNWD #2 13/142 RPR SHLS | ICS
LC | 121597118 | 024/338 | T2 DI CLAY-MARTEL 24/338 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-06-24 | 2021-06-22 | 2022-07-19 | 2022-06-22 | 2022-06-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45110677 | T2 DI CLAY-MARTEL 24/338 RPR GYWW | ICW
LC | 121597160 | 016/322 | T2 DI COLGATE-PALERMO 016/322 RPL HRDW | SACTO | ETL.6500.POLE.WOOD | 2021-06-24 | 2021-06-22 | 2022-05-06 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45200401 | T2 DI COLGATE-PALERMO 016/322 RPL HRDW | ICW
LC | 121597199 | 019/137 | T2 EI CARIBOU-TABLE MTN 19/137 RPR FOND | TABLEMTN | ETL.4440.TOWR | 2021-06-24 | 2021-06-24 | 2022-07-19 | 2022-06-24 | 2022-06-24 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160938 | T2 EI CARIBOU-TABLE MTN 19/137 RPR FOND | ICQ
LC | 121598741 | 025/305 | T2 EI DRUM-SUMMIT #1 25/305 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-25 | 2021-06-11 | 2022-09-15 | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121598743 | 025/305 | T2 EI DRUM-SUMMIT #1 25/305 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-25 | 2021-06-11 | 2022-09-15 | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121598851 | 026/317 | T2 EI DRUM-SUMMIT#2 26/317R RPLC STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-25 | 2021-06-11 | 2022-10-20 | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544720 | EI DRUM-SUMMIT#2 26/320 RPL POLE | 70Y
LC | 121598856 | 026/317 | T2 EI DRUM-SUMMIT#2 26/317L RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-25 | 2021-06-11 | 2022-10-20 | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544720 | EI DRUM-SUMMIT#2 26/320 RPL POLE | 70Y
LC | 121598869 | 014/060 | T2 DI DIABLO-GATES #1 014/060 RPR SHLS | PISMOBCH | ETL.5960.TOWR | 2021-06-25 | 2021-06-24 | 2021-10-18 | 2022-06-24 | 2022-06-24 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44962376 | T2 DI DIABLO-GATES #1 014/060 RPR SHLS | ICS
LC | 121598946 | 026/315 | T2 EI DRUM-SUMMIT#2 26/315L RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-25 | 2021-06-11 | 2022-10-18 | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544720 | EI DRUM-SUMMIT#2 26/320 RPL POLE | 70Y
LC | 121599130 | 016/078 | T2 EI MSS LNDING-LOS BNOS 16/78 RPL INSS | MOSSLNDG | ETL.6040.INSL | 2021-06-25 | 2021-06-25 | 2022-08-11 | 2022-06-25 | 2022-06-25 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31544846 | T2 EI MSS LNDING-LOS BNOS RPL INSS 4TWR | 93K
LC | 121599168 | 034/005 | T2 DI MDCN-WLLT-FT BRGG 34/5 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-25 | 2021-06-17 | 2022-05-22 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148590 | T2 DI MDCN-WLLT-FT BRGG 34/5 RPR GYWW | ICW
LC | 121599484 | 018/265 | T2 DI CLAY-MARTEL 18/265 RPR SWIW | VICTOR | ETL.8250.SWIT | 2021-06-25 | 2021-06-23 | 2022-06-15 | 2022-06-23 | 2022-06-23 | On-time | 623 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Out of Adjustment | Switch | Repair | 45110678 | T2 DI CLAY-MARTEL 18/265 RPR SWIW | ICE
LC | 121599497 | 025/307 | T2 EI DRUM-SUMMIT #2 25/307 RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2021-06-25 | 2021-06-25 | 2022-10-15 | 2022-06-25 | 2022-06-25 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544720 | EI DRUM-SUMMIT#2 26/320 RPL POLE | 70Y
LC | 121599498 | 026/318 | T2 DRUM-SUMMIT #2 26/318R RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2021-06-25 | 2021-06-25 | 2022-06-15 | 2022-06-25 | 2022-06-25 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544720 | EI DRUM-SUMMIT#2 26/320 RPL POLE | 70Y
LC | 121599535 | 025/307 | T2 EI DRUM-SUMMIT #2 25/307 RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2021-06-25 | 2021-06-25 | 2022-10-15 | 2022-06-25 | 2022-06-25 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544720 | EI DRUM-SUMMIT#2 26/320 RPL POLE | 70Y
LC | 121599595 | 025/295 | T2 EI DRUM-SUMMIT #1 25/295 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-25 | 2021-06-25 | 2022-09-08 | 2022-06-25 | 2022-06-25 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121599759 | 065/329 | T2 DI MALIN-ROUND MTN #2 65/329 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2021-06-25 | 2021-06-24 | 2022-07-16 | 2022-06-24 | 2022-06-24 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45215230 | T2 DI MALIN-ROUND MTN #2 65/329 RPR INSS | ICS
LC | 121599796 | 065/329 | T2 DI MALIN-ROUND MTN #2 65/329 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-06-25 | 2021-06-24 | 2022-08-05 | 2022-06-24 | 2022-06-24 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45194356 | T2 DI MALIN-ROUND MTN #2 65/329 RPR GYWS | ICS
LC | 121599919 | 010/105 | T2 EI PIT #5-RND MTN #1 10/105 RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-25 | 2021-06-13 | 2022-07-13 | 2022-06-13 | 2022-06-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121599943 | 027/193 | T2 DI CARIBOU-TABLE MTN 27/193 RPR ANCS | TABLEMTN | ETL.4440.POLE.STPS | 2021-06-25 | 2021-06-23 | 2022-06-22 | 2022-06-23 | 2022-06-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Anchor-Steel | Repair | 45212448 | T2 DI CARIBOU-TABLE MTN 27/193 RPR ANCS | ICS
LC | 121599976 | 027/193 | T2 DI CARIBOU-TABLE MTN 27/193 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-25 | 2021-06-23 | 2022-06-22 | 2022-06-23 | 2022-06-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551234 | T2 DI CARIBOU-TBL-MTN RPL INSS 2TWRS | 93K
LC | 121600190 | 022/259 | EI T2 DRUM-SUMMIT #1 22/259 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-25 | 2021-06-25 | 2022-08-27 | 2022-06-25 | 2022-06-25 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121600421 | 021/251 | EI T2 DRUM-SUMMIT #1 21/251 RPR ANCW | SACTO | ETL.1440.POLE.WDPS | 2021-06-25 | 2021-06-25 | 2022-09-07 | 2022-06-25 | 2022-06-25 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 45200407 | EI T2 DRUM-SUMMIT #1 21/251 RPR ANCW | ICW
LC | 121600503 | 021/251 | EI T2 DRUM-SUMMIT #1 21/251R RPR ANCW | SACTO | ETL.1440.POLE.WDPS | 2021-06-25 | 2021-06-25 | 2022-09-07 | 2022-06-25 | 2022-06-25 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 45200409 | EI T2 DRUM-SUMMIT #1 21/251 RPR ANCW | ICW
LC | 121600556 | 007/004 | T2 WV LAYTONVILLE-COVELO 7/4 RPR HRDD | WILLITS | ETL.7390.POLE.NWOD | 2021-06-25 | 2021-06-25 | 2022-06-02 | 2022-06-25 | 2022-06-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45000043 | T2 WV LAYTONVILLE-COVELO 7/4 RPR HRDD | ICW
LC | 121600652 | 007/004 | T2 WV LAYTONVILLE-COVELO 7/4 RPR ARMROD | WILLITS | ETL.7390.POLE.NWOD | 2021-06-25 | 2021-06-25 | 2022-06-02 | 2022-06-25 | 2022-06-25 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45000044 | T2 WV LAYTONVILLE-COVELO 7/4 RPR ARMROD | ICS
LC | 121600768 | 004/045 | T2 EI PIT #5-ROUND MTN #2 4/45R RPL STRW | TABLEMTN | ETL.5430.POLE.WDPS | 2021-06-25 | 2021-06-14 | 2022-06-15 | 2022-06-14 | 2022-06-14 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31547482 | T2 DI PIT #5-ROUND MTN #2 1/18R RPL STRW | 70Y
LC | 121600852 | 007/072 | EI T2 PIT #5-ROUND MTN #2 7/72 RPL STRW | TABLEMTN | ETL.5430.POLE.WDPS | 2021-06-25 | 2021-06-14 | 2022-06-13 | 2022-06-14 | 2022-06-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31601295 | EI T2 PIT #5-ROUND MTN #2 7/72 RPL STRW | 70Y
LC | 121600875 | 009/100 | EI T2 PIT #5-RND MTN #2 9/100L COMPLETE | TABLEMTN | ETL.5430.POLE.WDPS | 2021-06-25 | 2021-06-13 | 2022-06-17 | 2022-06-13 | 2022-06-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31601295 | EI T2 PIT #5-ROUND MTN #2 7/72 RPL STRW | 70Y
LC | 121600957 | 031/261 | T2 WV BRDGVLE-CTNWD 31/2 RPR FOND | TABLEMTN | ETL.1110.TOWR | 2021-06-25 | 2021-06-25 | 2022-07-29 | 2022-06-25 | 2022-06-25 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149331 | T2 WV BRDGVLE-CTNWD 31/2 RPR FOND | ICQ
LC | 121601002 | 001/019 | T2 DI BUCKS CRK-RCK CRK 1/019 RPR FOND | TABLEMTN | ETL.4430.TOWR | 2021-06-25 | 2021-06-18 | 2022-07-08 | 2022-06-18 | 2022-06-18 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160921 | T2 DI BUCKS CRK-RCK CRK 1/019 RPR FOND | ICQ
LC | 121601285 | 017/080 | T2 DI MS LDNG-LS BNS 17/80 RPLC HRDT | MOSSLNDG | ETL.6040.TOWR | 2021-06-25 | 2021-06-24 | 2022-03-20 | 2022-06-24 | 2022-06-24 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45128059 | T2 DI MS LDNG-LS BNS 17/80 RPLC HRDT | ICQ
LC | 121601362 | 020/239A | T2 EI DRUM-SUMMIT #1 20/239A RRP GYWW | SACTO | ETL.1440.POLE.NWOD | 2021-06-25 | 2021-06-25 | 2022-09-06 | 2022-06-25 | 2022-06-25 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45200410 | T2 EI DRUM-SUMMIT #1 20/239A RRP GYWW | ICW
LC | 121601906 | 001/010 | T2 EI LAYTONVILLE-COVELO 1/10 RPL STRW | WILLITS | ETL.7390.POLE.WOOD | 2021-06-25 | 2021-06-25 | 2022-06-15 | 2022-06-25 | 2022-06-25 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542885 | T2 DI LAYTONVILLE-COVELO 3/4 RPR WDPKR | 70Y
LC | 121602421 | 022/157 | T2 DI CARIBOU-TBL MTN 22/157 RPL HRDT | TABLEMTN | ETL.4440.TOWR | 2021-06-25 | 2021-06-22 | 2022-07-06 | 2022-06-22 | 2022-06-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45160945 | T2 DI CARIBOU-TBL MTN 22/157 RPL HRDT | ICQ
LC | 121602719 | 003/037 | T2 DI CHRISTIE-WLLW PASS 3/37 RMV DBRS | CONCORD | ETL.6370.POLE.WOOD | 2021-06-25 | 2021-06-23 | 2022-03-30 | 2022-06-23 | 2022-06-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45181070 | T2 DI CHRISTIE-WLLW PASS 3/37 RMV DBRS | ICW
LC | 121602769 | 027/404 | T2 DI CLAY-MARTEL 27/404 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-06-25 | 2021-06-23 | 2022-01-25 | 2022-06-23 | 2022-06-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543390 | DI CLAY-MARTEL 026/367 RPL STRW | 70Y
LC | 121603133 | 007/139 | T2 DI COLGATE-PALERMO 007/139 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2021-06-25 | 2021-06-22 | 2022-05-14 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45200411 | T2 DI COLGATE-PALERMO 007/139 RPR STRW | ICW
LC | 121603217 | 087/441 | T2 DI MALIN-ROUND MTN #2 87/441 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2021-06-25 | 2021-06-24 | 2022-07-16 | 2022-06-24 | 2022-06-24 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45215229 | T2 DI MALIN-ROUND MTN #2 87/441 RPR INSS | ICS
LC | 121603218 | 087/441 | T2 DI MALIN-ROUND MTN #2 87/441 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-06-25 | 2021-06-24 | 2022-04-25 | 2022-06-24 | 2022-06-24 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45198264 | T2 DI MALIN-ROUND MTN #2 87/441 RPR GYWS | ICS
LC | 121603349 | 021/010 | T2 DI MNDCN-WLTS-FRT BRG 21/10 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-06-25 | 2021-06-17 | 2022-09-29 | 2022-06-17 | 2022-06-17 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31547473 | T2 EI MNDCN-WLTS-FRT BRG 23/6R RPL POLE | 70Y
LC | 121603511 | 027/010 | T2 DI MNDCN-WLTS-FRT BRG 27/10 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-25 | 2021-06-17 | 2022-05-18 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148572 | T2 DI MNDCN-WLTS-FRT BRG 27/10 RPR GYWW | ICW
LC | 121603647 | 008/060 | T2 DI ROCK CREEK-POE 8/60 RPL INSS | TABLEMTN | ETL.5630.INSL.CERA | 2021-06-25 | 2021-06-18 | 2022-08-04 | 2022-06-18 | 2022-06-18 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551263 | T3 DI ROCK CREEK-POE RPL INSS 9TWRS | 93K
LC | 121603812 | 032/003 | T2 DI MNDOCN-WLLTS-FRT BRGG 32/3 RPR STR | WILLITS | ETL.7550.POLE.WOOD | 2021-06-25 | 2021-06-17 | 2022-05-17 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45148582 | T2 DI MNDOCN-WLLTS-FRT BRGG 32/3 RPR STR | ICW
LC | 121604304 | 087/445 | T2 DI MALIN-RND MTN #2 87/445 RMV DBRS | TABLEMTN | ETL.6020.TOWR | 2021-06-25 | 2021-06-24 | 2022-04-20 | 2022-06-24 | 2022-06-24 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45215228 | T2 DI MALIN-RND MTN #2 87/445 RMV DBRS | ICS
LC | 121604305 | 087/445 | T2 DI MALIN-RND MTN #2 87/445 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-25 | 2021-06-24 | 2022-07-12 | 2022-06-24 | 2022-06-24 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45262061 | T2 DI MALIN-RND MTN #2 87/445 RPR SHLS | ICS
LC | 121604349 | 065/329A | T2 DI MALIN-RND MTN #2 65/329A RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-06-25 | 2021-06-24 | 2022-08-05 | 2022-06-24 | 2022-06-24 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45194357 | T2 DI MALIN-RND MTN #2 65/329A RPR GYWS | ICS
LC | 121604366 | 015/069 | T2 DI PITTSBURG-TESLA #1 15/69 RMV NEST | CONCORD | ETL.5510.TOWR | 2021-06-25 | 2021-06-15 | 2021-09-28 | 2022-06-15 | 2022-06-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44959062 | T2 DI PITTSBURG-TESLA #1 15/69 RMV NEST | ICW
LC | 121604367 | 015/069 | T2 DI PITTSBURG-TESLA #1 15/69 INS HRDT | CONCORD | ETL.5510.TOWR | 2021-06-25 | 2021-06-15 | 2022-04-11 | 2022-06-15 | 2022-06-15 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45190830 | T2 DI PITTSBURG-TESLA #1 15/69 INS HRDT | ICQ
LC | 121605289 | 013/065 | T2 DI MOSS LANDING-CBRN 013/065 INS HRDT | MOSSLNDG | ETL.5330.TOWR | 2021-06-26 | 2021-06-22 | 2022-05-17 | 2022-06-22 | 2022-06-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45121220 | T2 DI MOSS LANDING-CBRN 013/065 INS HRDT | ICQ
LC | 121605536 | 003/033 | T2 DI BUCKS CRK-RCK CRK 003/033 RPR FOND | TABLEMTN | ETL.4430.TOWR | 2021-06-26 | 2021-06-23 | 2022-06-27 | 2022-06-23 | 2022-06-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160926 | T2 DI BUCKS CRK-RCK CRK 003/033 RPR FOND | ICQ
LC | 121605787 | 021/258 | T2 DI DRUM-SUMMIT #1 021/258 RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-26 | 2021-06-23 | 2022-06-30 | 2022-06-23 | 2022-06-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45200413 | T2 DI DRUM-SUMMIT #1 021/258 RPR STRW | ICW
LC | 121605788 | 021/258 | T2 DI DRUM-SUMMIT #1 021/258 RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-26 | 2021-06-23 | 2022-06-30 | 2022-06-23 | 2022-06-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45200417 | T2 DI DRUM-SUMMIT #1 021/258 RPR STRW | ICW
LC | 121605856 | 025/002 | T2 DI GARBRVILLE-LAYTNVLLE 25/2 RPL STRW | WILLITS | ETL.8365.POLE.WOOD | 2021-06-26 | 2021-06-24 | 2022-04-18 | 2022-06-24 | 2022-06-24 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31539395 | EI GARBERVILLE-LAYTONVILLE 51/0 RPL STRW | 70Y
LC | 121605939 | 035/258 | T2 DI CARIBOU-TABLE MTN 035/258 RPL INSS | TABLEMTN | ETL.4440.INSL | 2021-06-26 | 2021-06-24 | 2022-06-18 | 2022-06-24 | 2022-06-24 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121605974 | 006/069 | T2 EI CLGTE-SMRTVLLE #1 6/69L RPR GYWW | SACTO | ETL.6510.POLE.WDPS | 2021-06-26 | 2021-06-26 | 2022-07-25 | 2022-06-26 | 2022-06-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45233403 | T2 EI CLGTE-SMRTVLLE #1 6/69L RPR GYWW | ICW
LC | 121605989 | 006/069 | T2 EI CLGTE-SMRTVLLE #1 6/69R RPR GYWW | SACTO | ETL.6510.POLE.WDPS | 2021-06-26 | 2021-06-26 | 2022-07-25 | 2022-06-26 | 2022-06-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44905437 | T2 EI CLGTE-SMRTVLLE #1 6/69R RPR GYWW | ICW
LC | 121605995 | 006/069 | T2 EI CLGTE-SMRTVLLE #1 6/69C RPR GYWW | SACTO | ETL.6510.POLE.WDPS | 2021-06-26 | 2021-06-26 | 2022-07-25 | 2022-06-26 | 2022-06-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45233405 | T2 EI CLGTE-SMRTVLLE #1 6/69C RPR GYWW | ICW
LC | 121606124 | 021/245 | T2 DI DRUM-SUMMIT #1 021/245 BACKFILL | SACTO | ETL.1440.POLE.STPS | 2021-06-26 | 2021-06-18 | 2022-09-07 | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45200418 | T2 DI DRUM-SUMMIT #1 021/245 BACKFILL | ICW
LC | 121606383 | 038/165 | T2 DI FULTON-LAKEVILLE 38/165 RPR INSS | LAKEVLLE | ETL.4950.INSL.CERA | 2021-06-26 | 2021-06-22 | 2022-06-22 | 2022-06-22 | 2022-06-22 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45144133 | T2 DI FULTON-LAKEVILLE 38/165 RPR INSS | ICS
LC | 121606407 | 007/058 | T2 EI CARIBOU-TABLE MTN 7/58 RPR FOND | TABLEMTN | ETL.4440.TOWR | 2021-06-26 | 2021-06-25 | 2022-07-25 | 2022-06-25 | 2022-06-25 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160933 | T2 EI CARIBOU-TABLE MTN 7/58 RPR FOND | ICQ
LC | 121606408 | 011/088A | T2 EI CARIBOU-TABLE MTN 11/88A RPR FOND | TABLEMTN | ETL.4440.POLE.NWOD | 2021-06-26 | 2021-06-25 | 2022-07-18 | 2022-06-25 | 2022-06-25 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160936 | T2 EI CARIBOU-TABLE MTN 11/88A RPR FOND | ICQ
LC | 121606437 | 007/057 | T2 EI CARIBOU-TABLE MTN 7/57 RPR FOND | TABLEMTN | ETL.4440.POLE.STPS | 2021-06-26 | 2021-06-25 | 2022-07-25 | 2022-06-25 | 2022-06-25 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160932 | T2 EI CARIBOU-TABLE MTN 7/57 RPR FOND | ICQ
LC | 121606442 | 006/068 | T2 EI CLGTE-SMRTVLLE #1 6/68R RPR GYWW | SACTO | ETL.6510.POLE.WDPS | 2021-06-26 | 2021-06-26 | 2022-07-25 | 2022-06-26 | 2022-06-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45233406 | T2 EI CLGTE-SMRTVLLE #1 6/68R RPR GYWW | ICW
LC | 121606443 | 006/068 | T2 EI CLGTE-SMRTVLLE #1 6/68L RPR GYWW | SACTO | ETL.6510.POLE.WDPS | 2021-06-26 | 2021-06-26 | 2022-07-25 | 2022-06-26 | 2022-06-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45233407 | T2 EI CLGTE-SMRTVLLE #1 6/68L RPR GYWW | ICW
LC | 121606453 | 006/068 | T2 EI CLGTE-SMRTVLLE #1 6/68C RPR GYWW | SACTO | ETL.6510.POLE.WDPS | 2021-06-26 | 2021-06-26 | 2022-07-25 | 2022-06-26 | 2022-06-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45233408 | T2 EI CLGTE-SMRTVLLE #1 6/68C RPR GYWW | ICW
LC | 121606454 | 006/068 | T2 EI CLGTE-SMRTVLLE #1 6/68R RPR STRW | SACTO | ETL.6510.POLE.WDPS | 2021-06-26 | 2021-06-26 | 2022-07-25 | 2022-06-26 | 2022-06-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45233409 | T2 EI CLGTE-SMRTVLLE #1 6/68R RPR STRW | ICW
LC | 121606789 | 006/014 | T2 DI VAL SPGS-MRTL#1 6/14 RMV DEBR | VICTOR | ETL.8240.INSL.NCER | 2021-06-26 | 2021-06-25 | 2022-02-26 | 2022-06-25 | 2022-06-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Conductor-Wood | Remove | 44961289 | T2 DI VAL SPGS-MRTL#1 6/14 RMV DEBR | ICW
LC | 121606812 | 025/001 | T2 DI MNDCN-WLLTS-FRT BRGG 25/1 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-26 | 2021-06-17 | 2022-05-20 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45148039 | T2 DI MNDCN-WLLTS-FRT BRGG 25/1 RPR STRW | ICW
LC | 121606889 | 017/149 | T2 DI CRAG VIEW-CASCADE 17/149 RPR SHLW | TABLEMTN | ETL.1350.POLE.STPS | 2021-06-26 | 2021-06-18 | 2022-09-14 | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45500239 | T2 DI CRAG VIEW-CASCADE 17/149 RPR SHLW | ICW
LC | 121607115 | 010/118 | T2 DI DRUM-SUMMIT #2 010/118 RPR STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-26 | 2021-06-17 | 2022-05-08 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45200420 | T2 DI DRUM-SUMMIT #2 010/118 RPR STRW | ICW
LC | 121607116 | 010/118 | T2 DI DRUM-SUMMIT #2 010/118 RPR STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-26 | 2021-06-17 | 2022-05-08 | 2022-06-17 | 2022-06-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45200424 | T2 DI DRUM-SUMMIT #2 010/118 RPR STRW | ICW
LC | 121607575 | 029/206 | T2 DI CARIBOU-TBL MTN 29/206 RPL INSS | TABLEMTN | ETL.4440.INSL | 2021-06-26 | 2021-06-10 | 2022-06-22 | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121607601 | 022/002 | T2 DI MNDCN-WLLTS-FRT BRGG 22/2 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-26 | 2021-06-18 | 2022-05-22 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45148031 | T2 DI MNDCN-WLLTS-FRT BRGG 22/2 RPR GYWW | ICW
LC | 121607603 | 022/002 | T2NT DI MNDCN-WLTS-FRT BRG 22/2 RMV DBRS | WILLITS | ETL.7550.POLE.WOOD | 2021-06-26 | 2021-06-18 | 2022-05-22 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2N PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45148031 | T2 DI MNDCN-WLLTS-FRT BRGG 22/2 RPR GYWW | ICW
LC | 121607688 | 007/137 | T2 DI SMRTVLL-NCLS #1 007/137 REFRAME | SACTO | ETL.7990.POLE.WOOD | 2021-06-26 | 2021-06-23 | 2022-08-18 | 2022-06-23 | 2022-06-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45233410 | T2 DI SMRTVLL-NCLS #1 007/137 REFRAME | ICW
LC | 121607755 | 002/007 | T2 DI RIO DELL TAP 2/7 RPLC HRDW | EUREKA | ETL.7851.POLE.WOOD | 2021-06-26 | 2021-06-23 | 2022-06-25 | 2022-06-23 | 2022-06-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44888307 | T2 DI RIO DELL TAP 2/7 RPLC HRDW | ICW
LC | 121607940 | B020/452 | T2 DI DRM-GRSS VLLY-WMR B20/452 RPL HRDD | SACTO | ETL.6760.POLE.WOOD | 2021-06-26 | 2021-06-23 | 2022-07-26 | 2022-06-23 | 2022-06-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45193823 | T2 DI DRM-GRSS VLLY-WMR B20/452 RPL HRDD | ICW
LC | 121607941 | 038/242 | T2 DI CZY HRS CYN-SLS-SD 38/242 INS ACG | MOSSLNDG | ETL.2900.TOWR | 2021-06-26 | 2021-06-18 | 2022-03-13 | 2022-06-18 | 2022-06-18 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Anti-Climbing Guard | Structure-Tower | Repair | 45241923 | T2 DI CZY HRS CYN-SLS-SD 38/242 INS ACG | ICQ
LC | 121607944 | 013/117 | T2 DI EL DRD-MSSR FLT #1 13/117 RMV STEP | SACTO | ETL.1530.TOWR | 2021-06-26 | 2021-06-23 | 2022-05-23 | 2022-06-23 | 2022-06-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45149865 | T2 DI EL DRD-MSSR FLT #1 13/117 RMV STEP | ICQ
LC | 121608015 | 006/003 | T2 DI MENDCNO-WLLTS-FT BRG 6/3 RPR INSW | WILLITS | ETL.7550.INSL.CERA | 2021-06-26 | 2021-06-17 | 2022-08-17 | 2022-06-17 | 2022-06-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45145613 | T2 DI MENDCNO-WLLTS-FT BRG 6/3 RPR INSW | ICW
LC | 121608250 | 000/003 | T2 DI MORAGA-CSTR VLLY 000/003 RPL HRDT | CONCORD | ETL.5250.TOWR | 2021-06-26 | 2021-06-23 | 2022-01-25 | 2022-06-23 | 2022-06-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45149174 | T2 DI MORAGA-CSTR VLLY 000/003 RPL HRDT | ICQ
LC | 121608251 | 000/003 | T2 DI MORAGA-CSTR VLLY 000/003 RPR SHLS | CONCORD | ETL.5250.TOWR | 2021-06-26 | 2021-06-23 | 2022-02-01 | 2022-06-23 | 2022-06-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45137553 | T2 DI MORAGA-CSTR VLLY 000/003 RPR SHLS | ICS
LC | 121608255 | :003/007 | T2 DI BLLT-RBK-MLS SWT :003/007 RPR STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-06-26 | 2021-06-22 | 2022-04-14 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45157225 | T2 DI BLLT-RBK-MLS SWT :003/007 RPR STRW | ICW
LC | 121608262 | 003/001 | T2 EI SALMON CREEK TAP 3/1 INS DAMW | LAKEVLLE | ETL.6981.POLE.WDPS | 2021-06-26 | 2021-06-26 | 2022-04-21 | 2022-06-26 | 2022-06-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Damper-Wood | Replace | 45136725 | T2 EI SALMON CREEK TAP 3/1 INS DAMW | ICW
LC | 121608543 | 024/286 | T2 DI DRUM-SUMMIT #1 024/286 RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-26 | 2021-06-23 | 2022-09-02 | 2022-06-23 | 2022-06-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45193597 | T2 DI DRUM-SUMMIT #1 024/286 RPR STRW | ICW
LC | 121609002 | 028/421 | T2 DI CLAY-MARTEL 28/421 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-06-26 | 2021-06-24 | 2022-01-27 | 2022-06-24 | 2022-06-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45067387 | T2 DI CLAY-MARTEL 28/421 RPR STRW | ICW
LC | 121609150 | 008/095 | T2 DI DRUM-SUMMIT #2 8/95 FILL HOLE | SACTO | ETL.1450.POLE.STPS | 2021-06-26 | 2021-06-15 | 2022-06-08 | 2022-06-15 | 2022-06-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45200431 | T2 DI DRUM-SUMMIT #2 8/95 FILL HOLE | ICW
LC | 121609155 | 002/028 | T2 DI COLGATE-PALERMO 002/028 RMV BUTT | SACTO | ETL.6500.POLE.NWOD | 2021-06-26 | 2021-06-22 | 2022-05-22 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45200433 | T2 DI COLGATE-PALERMO 002/028 RMV BUTT | ICW
LC | 121609162 | :002/005 | T2 DI BLT-RVRBNK-MLNS 2/5 RPR INSW | VICTOR | ETL.1070.INSL.NCER | 2021-06-26 | 2021-06-18 | 2022-03-08 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45157226 | T2 DI BLT-RVRBNK-MLNS 2/5 RPR INSW | ICW
LC | 121609274 | 035/300 | T2 DI RND MTN-CTNWD #3 35/300 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-26 | 2021-06-18 | 2022-08-04 | 2022-06-18 | 2022-06-18 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547626 | T2 DI RND MTN-CTNWD #3 RPL INSS 9TWRS | 93K
LC | 121609277 | 016/118 | T2 DI CAYUCOS-CAMBRIA 16/118 RPL HRDW | PISMOBCH | ETL.8560.POLE.WOOD | 2021-06-26 | 2021-06-23 | 2022-11-22 | 2022-06-23 | 2022-06-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45068465 | T2 DI CAYUCOS-CAMBRIA 16/118 RPL HRDW | ICW
LC | 121609308 | 000/007 | T2 DI ROLLINS TAP 0/7 RPL INSW | SACTO | ETL.6762.INSL | 2021-06-26 | 2021-06-22 | 2022-07-29 | 2022-06-22 | 2022-06-22 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545281 | T2 DI ROLLINS TAP 0/7 RPL INSW | 93I
LC | 121609444 | 000/010 | T2 DI ROLLINS TAP 0/10 RPL INSW | SACTO | ETL.6762.INSL | 2021-06-26 | 2021-06-18 | 2022-07-29 | 2022-06-18 | 2022-06-18 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31613211 | T2 DI ROLLINS TAP 0/10 RPL INSW | 93I
LC | 121609449 | 022/268 | T2 DI DRUM-SUMMIT #1 22/268 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-26 | 2021-06-23 | 2022-08-30 | 2022-06-23 | 2022-06-23 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121609457 | 083/422 | T2 DI MALIN-RND MTN #2 083/422 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-06-26 | 2021-06-26 | 2022-07-12 | 2022-06-26 | 2022-06-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215227 | T2 DI MALIN-RND MTN #2 083/422 RPR OPGW | ICS
LC | 121609552 | :009/002 | T2 DI BLT-RVRBNK-MLNS :9/2 RPL INSW | VICTOR | ETL.1070.INSL.NCER | 2021-06-26 | 2021-06-22 | 2022-05-06 | 2022-06-22 | 2022-06-22 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545223 | T2 DI BLTA RVK MLNS SS :011/004 RPL INSW | 93I
LC | 121609582 | 078/396 | T2 DI MALIN-RND MTN #2 078/396 RPR FOND | TABLEMTN | ETL.6020.TOWR | 2021-06-26 | 2021-06-26 | 2022-07-15 | 2022-06-26 | 2022-06-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45198247 | T2 DI MALIN-RND MTN #2 078/396 RPR FOND | ICQ
LC | 121609585 | 010/044 | T2 DI DIABLO-GATES #1 010/044 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2021-06-26 | 2021-06-26 | 2022-06-25 | 2022-06-26 | 2022-06-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068521 | T2 DI DIABLO-GATES #1 010/044 RPR GYWS | ICS
LC | 121609730 | 010/123 | T2 DI CLGT-SMRTVLL #2 010/123 RPR STRW | SACTO | ETL.6520.POLE.WOOD | 2021-06-26 | 2021-06-16 | 2022-07-19 | 2022-06-16 | 2022-06-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45233419 | T2 DI CLGT-SMRTVLL #2 010/123 RPR STRW | ICW
LC | 121609831 | 032/137 | T2 DI MORRO BAY-SOLAR #2 32/137 RPL INSS | PISMOBCH | ETL.5310.INSL | 2021-06-26 | 2021-06-22 | 2022-07-26 | 2022-06-22 | 2022-06-22 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31550476 | T2 EI MR BY-SLR SW STA #2 RPL INSS 5 TW | 93K
LC | 121609832 | 034/255 | T2 DI CARIBOU-TABLE MTN 34/255 RPLC HRDT | TABLEMTN | ETL.4440.TOWR | 2021-06-26 | 2021-06-23 | 2022-07-25 | 2022-06-23 | 2022-06-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45108136 | T2 DI CARIBOU-TABLE MTN 34/255 RPLC HRDT | ICQ
LC | 121609834 | 034/255 | T2 DI CARIBOU-TABLE MTN 34/255 RPR INSS | TABLEMTN | ETL.4440.INSL | 2021-06-26 | 2021-06-23 | 2022-06-20 | 2022-06-23 | 2022-06-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45212449 | T2 DI CARIBOU-TABLE MTN 34/255 RPR INSS | ICS
LC | 121610867 | 024/114 | EI T2 CONTRA COSTA-MORAGA #1 24/114 WASH | CONCORD | ETL.5452.INSL.CERA | 2021-06-27 | 2021-06-27 | 2021-11-03 | 2022-06-27 | 2022-06-27 | On-time | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | Contaminated | Insulator | Ground Wash | 44959023 | EI T2 CONTRA COSTA-MORAGA #1 24/114 WASH | ICD
LC | 121620639 | 016/136 | T2 DI CRAG VIEW-CASCADE 016/136 RPR STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-28 | 2021-06-18 | 2022-09-16 | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45460928 | T2 DI CRAG VIEW-CASCADE 016/136 RPR STRW | ICW
LC | 121620808 | 016/136 | T2 DI CRAG VIEW-CASCADE 16/136 RPR SHLW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-28 | 2021-06-18 | 2022-09-19 | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45500280 | T2 DI CRAG VIEW-CASCADE 16/136 RPR SHLW | ICW
LC | 121620965 | 026/310 | T2 DI DRUM-SUMMIT #2 26/310 RPR INSW | SACTO | ETL.1450.INSL.CERA | 2021-06-28 | 2021-06-18 | 2022-06-12 | 2022-06-18 | 2022-06-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45193599 | T2 DI DRUM-SUMMIT #2 26/310 RPR INSW | ICW
LC | 121621085 | 010/119 | T2 DI DRUM-SUMMIT #1 010/119 RPL INSW | SACTO | ETL.1440.INSL.NCER | 2021-06-28 | 2021-06-17 | 2022-06-26 | 2022-06-17 | 2022-06-17 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541895 | T2 EI DRUM-SUMMIT #1 20/237 RPL INSW | 93I
LC | 121621100 | 010/119 | DI T2 DRUM-SUMMIT #1 010/119 RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-28 | 2021-06-18 | 2022-06-26 | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45200439 | DI T2 DRUM-SUMMIT #1 010/119 RPR STRW | ICW
LC | 121621161 | 014/000 | T2 EI HUMBOLDT-MAPLE CRK 14/0R RPR GYWW | EUREKA | ETL.7130.POLE.WDPS | 2021-06-28 | 2021-06-27 | 2022-11-16 | 2022-06-27 | 2022-06-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44908267 | T2 EI HUMBOLDT-MAPLE CREK 14/0L RPR JMPW | ICW
LC | 121621222 | 014/000 | T2 EI HUMBOLDT-MAPLE CRK 14/0C RPR GYWW | EUREKA | ETL.7130.POLE.WDPS | 2021-06-28 | 2021-06-27 | 2022-11-16 | 2022-06-27 | 2022-06-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44908267 | T2 EI HUMBOLDT-MAPLE CREK 14/0L RPR JMPW | ICW
LC | 121621270 | 014/000 | T2 EI HUMBOLDT-MAPLE CRK 14/0L RPR JMPW | EUREKA | ETL.7130.POLE.WDPS | 2021-06-28 | 2021-06-27 | 2022-11-16 | 2022-06-27 | 2022-06-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Conductor-Wood | Repair | 44908267 | T2 EI HUMBOLDT-MAPLE CREK 14/0L RPR JMPW | ICW
LC | 121621655 | 027/318 | T2 DI DRUM-SUMMIT #1 27/318 RPL INSW | SACTO | ETL.1440.INSL.NCER | 2021-06-28 | 2021-06-17 | 2022-09-23 | 2022-06-17 | 2022-06-17 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31549084 | T2 DI DRUM-SUMMIT #1 27/318 RPL INSW | 93I
LC | 121621707 | 081/414 | T2 DI MLN-RND MTN #2 81/414 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-06-28 | 2021-06-26 | 2022-07-13 | 2022-06-26 | 2022-06-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215224 | T2 DI MLN-RND MTN #2 81/414 RPR OPGW | ICS
LC | 121621810 | 081/414 | T2 DI MLN-RND MTN #2 81/414 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2021-06-28 | 2021-06-26 | 2022-07-16 | 2022-06-26 | 2022-06-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45465172 | T2 DI MLN-RND MTN #2 81/414 RPR INSS | ICS
LC | 121621817 | 025/111 | T2 DI MSS LNDNG-MTCLF 25/111 RMV NEST | MOSSLNDG | ETL.6050.TOWR | 2021-06-28 | 2021-06-24 | 2022-02-26 | 2022-06-24 | 2022-06-24 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45166387 | T2 DI MSS LNDNG-MTCLF 25/111 RMV NEST | ICS
LC | 121623176 | 008/091A | T2 EI DRUM-SUMMIT #2 8/91A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2021-06-28 | 2021-06-28 | 2022-06-08 | 2022-06-28 | 2022-06-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45200483 | T2 EI DRUM-SUMMIT #2 8/91A RPR GYWW | ICS
LC | 121623201 | 008/091B | T2 EI DRUM-SUMMIT #2 8/91B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2021-06-28 | 2021-06-28 | 2022-06-08 | 2022-06-28 | 2022-06-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45200485 | T2 EI DRUM-SUMMIT #2 8/91B RPR GYWW | ICS
LC | 121623300 | 008/091C | T2 EI DRUM-SUMMIT #2 8/91C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2021-06-28 | 2021-06-28 | 2022-06-08 | 2022-06-28 | 2022-06-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45200488 | T2 EI DRUM-SUMMIT #2 8/91C RPR GYWW | ICS
LC | 121623363 | 010/075C | T2 DI CARIBOU-TBLE MTN 010/075C RPL INSS | TABLEMTN | ETL.4440.POLE.NWOD | 2021-06-28 | 2021-06-27 | 2022-06-20 | 2022-06-27 | 2022-06-27 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Repair | 45212450 | T2 DI CARIBOU-TBLE MTN 010/075C RPL INSS | ICS
LC | 121623638 | 025/151 | T2 DI STANISLAUS-MTCA 25/151 RMV NEST | VICTOR | ETL.3820.TOWR | 2021-06-28 | 2021-06-22 | 2021-09-25 | 2022-06-22 | 2022-06-22 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44962386 | T2 DI STANISLAUS-MTCA 25/151 RMV NEST | ICS
LC | 121623675 | 011/018 | T2 DI LWR LK-HMSTK TP 11/18 RPL INSW | WILLITS | ETL.1481.INSL.NCER | 2021-06-28 | 2021-06-15 | 2022-06-17 | 2022-06-15 | 2022-06-15 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31544975 | T2 DI LWR LK-HMSTK TP 11/18 RPL INSW | 93I
LC | 121624075 | 029/442 | T2 DI CLAY-MARTEL 29/442 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-06-28 | 2021-06-28 | 2022-02-03 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45067388 | T2 DI CLAY-MARTEL 29/442 RPR STRW | ICW
LC | 121624076 | 029/442 | T2 DI CLAY-MARTEL 29/442 RPLC SPLW | VICTOR | ETL.8250.INSL.CERA | 2021-06-28 | 2021-06-28 | 2022-02-03 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Replace | 45067389 | T2 DI CLAY-MARTEL 29/442 RPLC SPLW | ICW
LC | 121624280 | 029/442 | T2 DI CLAY-MARTEL 29/442 RPLC HRDW | VICTOR | ETL.8250.POLE.WOOD | 2021-06-28 | 2021-06-28 | 2022-02-03 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45067390 | T2 DI CLAY-MARTEL 29/442 RPLC HRDW | ICW
LC | 121624328 | 058/527 | T2 DI RND MTN-CTNWD #3 58/527 RPL HNGR | TABLEMTN | ETL.5650.TOWR | 2021-06-28 | 2021-06-10 | 2022-01-19 | 2022-06-10 | 2022-06-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45094450 | T2 DI RND MTN-CTNWD #3 58/527 RPL HNGR | ICQ
LC | 121624329 | 058/527 | T2 DI RND MTN-CTNWD #3 58/527 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-28 | 2021-06-10 | 2022-01-19 | 2022-06-10 | 2022-06-10 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548265 | T2 DI RND MTN-COTNWD #3 RPL INSS 10TWRS | 93K
LC | 121624652 | 000/015 | T2 JEFFERSON-STANFORD 0/015 RPL STRW | METCALF | ETL.7220.POLE.WOOD | 2021-06-28 | 2021-06-28 | 2022-09-24 | 2022-06-28 | 2022-06-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31544873 | T2 JEFFERSON-STANFORD 0/015 RPL STRW | 70Y
LC | 121624868 | 005/068 | T2 DI GREEN VLLY-CMP EVRS 5/68 RPR SPLW | MOSSLNDG | ETL.1710.INSL.CERA | 2021-06-28 | 2021-06-28 | 2022-03-03 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45122583 | T2 DI GREEN VLLY-CMP EVRS 5/68 RPR SPLW | ICW
LC | 121624921 | 005/067 | T2 DI GRN VLLY-CMP EVRS 5/67R RPR STRW | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-06-28 | 2021-06-28 | 2022-03-03 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45166717 | T2 DI GRN VLLY-CMP EVRS 5/67R RPR STRW | ICW
LC | 121625565 | 009/005 | T2 LWR LKE-HMESTAKE TAP 9/5 RPR WDPKR | LAKEVLLE | ETL.1481.POLE.WOOD | 2021-06-28 | 2021-06-28 | 2021-08-13 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44947982 | T2 LWR LKE-HMESTAKE TAP 9/5 RPR WDPKR | ICW
LC | 121627609 | 078/398 | T2 DI MALIN-RND MTN #2 78/398 RPLC SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-29 | 2021-06-28 | 2022-07-13 | 2022-06-28 | 2022-06-28 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO CLMB AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 45215223 | T2 DI MALIN-RND MTN #2 78/398 RPLC SHLS | ICS
LC | 121627683 | 000/004A | T2 EI COLGATE-PALERMO 0/004A RMV VEG | SACTO | ETL.6500.POLE.NWOD | 2021-06-29 | 2021-06-28 | 2021-11-29 | 2022-06-28 | 2022-06-28 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 121627684 | 000/004C | T2 EI COLGATE-PALERMO 0/004C RMV VEG | SACTO | ETL.6500.POLE.NWOD | 2021-06-29 | 2021-06-28 | 2021-11-29 | 2022-06-28 | 2022-06-28 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 121627701 | 000/004B | T2 EI COLGATE-PALERMO 0/004B RMV VEG | SACTO | ETL.6500.POLE.NWOD | 2021-06-29 | 2021-06-28 | 2021-11-29 | 2022-06-28 | 2022-06-28 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 121627751 | 009/069A | T2 DI HELMS-GREGG #1 009/069A RPR INSS | FRESNO | ETL.4870.INSL | 2021-06-29 | 2021-06-16 | 2022-08-26 | 2022-06-16 | 2022-06-16 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair | 45069494 | T2 DI HELMS-GREGG #1 009/069A RPR INSS | ICS
LC | 121627939 | 013/141 | T2 DI RND MTN-COTTNWD #2 13/141 RPL INSW | TABLEMTN | ETL.5640.INSL.NCER | 2021-06-29 | 2021-06-18 | 2022-07-28 | 2022-06-18 | 2022-06-18 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545617 | T2 DI RND MTN-COTTNWD #2 13/141 RPL INSW | 93I
LC | 121628015 | 013/141 | T2 DI RND MTN-CTNWD #2 13/141L RPR STRW | TABLEMTN | ETL.5640.POLE.WDPS | 2021-06-29 | 2021-06-18 | 2022-07-23 | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45215255 | T2 DI RND MTN-CTNWD #2 13/141 RPR STRW | ICW
LC | 121628310 | :006/044 | T2 DI ROCK CREEK-POE :6/44 RPL INSS | TABLEMTN | ETL.5630.INSL.CERA | 2021-06-29 | 2021-06-23 | 2022-08-07 | 2022-06-23 | 2022-06-23 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551263 | T3 DI ROCK CREEK-POE RPL INSS 9TWRS | 93K
LC | 121628395 | 006/046 | T2 DI WISHON-COPPERMINE 006/046 RPL INSS | FRESNO | ETL.9330.INSL.CERA | 2021-06-29 | 2021-06-17 | 2022-04-28 | 2022-06-17 | 2022-06-17 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549334 | T2 DI WISHON-COPPERMINE RPL INSS 48 LOC' | 93K
LC | 121628396 | 006/046 | T2 DI WSHN-CPPRMNE 6/46 RPR FOND CMPLTD | FRESNO | ETL.9330.TOWR | 2021-06-29 | 2021-06-17 | 2022-04-30 | 2022-06-17 | 2022-06-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45070448 | T2 DI WISHON-COPPERMINE 006/046 RPR FOND | ICQ
LC | 121628398 | 022/004 | T2 DI MNDCN-WLLT-FT BRGG 22/4 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-06-29 | 2021-06-17 | 2022-08-19 | 2022-06-17 | 2022-06-17 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31547473 | T2 EI MNDCN-WLTS-FRT BRG 23/6R RPL POLE | 70Y
LC | 121628419 | 005/064 | T2 EI CLGTE-SMRTVLLE #1 5/64R RPR STRW | SACTO | ETL.6510.POLE.WDPS | 2021-06-29 | 2021-06-29 | 2022-07-28 | 2022-06-29 | 2022-06-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45239501 | T2 EI CLGTE-SMRTVLLE #1 5/64R RPR STRW | ICW
LC | 121628431 | 005/000 | T2 EI MELONES-CURTIS 5/0L RPL POLE | VICTOR | ETL.2390.POLE.WDPS | 2021-06-29 | 2021-06-15 | 2022-11-12 | 2022-06-15 | 2022-06-15 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545148 | T2 EI MELONES-CURTIS 5/0 RPL POLE | 70Y
LC | 121628433 | 005/000 | T2 EI MELONES-CURTIS 5/0R RPL POLE | VICTOR | ETL.2390.POLE.WDPS | 2021-06-29 | 2021-06-15 | 2022-11-12 | 2022-06-15 | 2022-06-15 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545148 | T2 EI MELONES-CURTIS 5/0 RPL POLE | 70Y
LC | 121628602 | 041/009 | T2 DI MDCN-WLLT-FT BRG 41/9 GRND WASH | WILLITS | ETL.7550.INSL.CERA | 2021-06-29 | 2021-06-17 | 2022-05-11 | 2022-06-17 | 2022-06-17 | On-time | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Contaminated | Insulator | Ground Wash | 45262573 | T2 DI MDCN-WLLT-FT BRG 41/9 GRND WASH | ICD
LC | 121628934 | R001/014 | T2 DI RND MTN-CTTNWD #3 R1/14 RPL INSW | TABLEMTN | ETL.5650.INSL.CERA | 2021-06-29 | 2021-06-18 | 2022-08-02 | 2022-06-18 | 2022-06-18 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545282 | T2 DI RND MTN-CTTNWD #3 R1/14 RPL INSW | 93I
LC | 121628973 | 011/131 | EI T2 DRUM-SUMMIT NO. 1 11/131 RPL INSW | SACTO | ETL.1440.INSL | 2021-06-29 | 2021-06-29 | 2022-06-27 | 2022-06-29 | 2022-06-29 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541895 | T2 EI DRUM-SUMMIT #1 20/237 RPL INSW | 93I
LC | 121629104 | 011/132 | EI T2 DRUM-SUMMIT NO. 1 11/132L RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-29 | 2021-06-29 | 2022-06-24 | 2022-06-29 | 2022-06-29 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31543339 | T2 EI DRUM-SUMMIT #1 9/111 RPL STRW | 70Y
LC | 121629221 | 006/007 | T2 DI SLS-FT OD #2-FT OD #2 6/7 RMV DBRS | MOSSLNDG | ETL.8423.POLE.NWOD | 2021-06-29 | 2021-06-23 | 2022-08-06 | 2022-06-23 | 2022-06-23 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45213175 | T2 DI SLS-FT OD #2-FT OD #2 6/7 RMV DBRS | ICS
LC | 121629223 | 006/007 | T2 DI SLS-FT OD #2-FT OD #2 6/7 RPR CNDS | MOSSLNDG | ETL.8423.INSL.CERA | 2021-06-29 | 2021-06-23 | 2022-05-11 | 2022-06-23 | 2022-06-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Conductor-Steel | Repair | 45232807 | T2 DI SLS-FT OD #2-FT OD #2 6/7 RPR CNDS | ICS
LC | 121629593 | 024/339 | T2 DI CLAY-MARTEL 024/339 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-06-29 | 2021-06-22 | 2022-07-19 | 2022-06-22 | 2022-06-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45110701 | T2 DI CLAY-MARTEL 024/339 RPR GYWW | ICW
LC | 121629618 | 012/126 | T2 DI PIT #5-RND MTN #1 12/126 RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-29 | 2021-06-28 | 2021-07-28 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 121630247 | 025/184 | T2 DI CARIBOU-TABLE MTN 25/184 RPLC INSS | TABLEMTN | ETL.4440.INSL | 2021-06-29 | 2021-06-11 | 2022-06-23 | 2022-06-11 | 2022-06-11 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121630807 | 013/012 | T2 DI MNDCN-WLTS-FRT BRG 13/12 RPR INSW | WILLITS | ETL.7550.INSL.NCER | 2021-06-29 | 2021-06-16 | 2022-05-20 | 2022-06-16 | 2022-06-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45145773 | T2 DI MNDCN-WLTS-FRT BRG 13/12 RPR INSW | ICW
LC | 121630808 | 013/012 | T2 DI MNDCN-WLTS-FRT BRG 13/12 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-29 | 2021-06-16 | 2022-05-20 | 2022-06-16 | 2022-06-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145773 | T2 DI MNDCN-WLTS-FRT BRG 13/12 RPR INSW | ICW
LC | 121630906 | 001/014 | T2 PIT #6 TAP-WOOD 1/14L RPL POLE CMT | TABLEMTN | ETL.5441.POLE.WDPS | 2021-06-29 | 2021-06-19 | 2022-06-20 | 2022-06-19 | 2022-06-19 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO AIR NTDE | Rotten | Structure-Wood | Replace | 31545615 | T2 PIT #6 TAP-WOOD 1/14 RPL POLE | 70Y
LC | 121630943 | 001/055 | T2 DI HMLTN BRNCH-CHESTER 1/55 RPR GYWW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-06-29 | 2021-06-28 | 2022-07-25 | 2022-06-28 | 2022-06-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213378 | T2 DI HMLTN BRNCH-CHESTER 1/55 RPR GYWW | ICW
LC | 121632685 | 001/010 | T2 DI PIT #7 TAP 001/010 RMV BUTT | TABLEMTN | ETL.5442.POLE.WDPS | 2021-06-29 | 2021-06-28 | 2022-06-15 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45213885 | T2 DI PIT #7 TAP 001/010 RMV BUTT | ICW
LC | 121632689 | 001/010 | T2 DI PIT #7 TAP 001/010 RPR STRW | TABLEMTN | ETL.5442.POLE.WDPS | 2021-06-29 | 2021-06-28 | 2022-07-14 | 2022-06-28 | 2022-06-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213884 | T2 DI PIT #7 TAP 001/010 RPR STRW | ICW
LC | 121632772 | 001/010 | T2 DI PIT #7 TAP 001/010 RPR STRW | TABLEMTN | ETL.5442.POLE.WDPS | 2021-06-29 | 2021-06-28 | 2022-07-14 | 2022-06-28 | 2022-06-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213883 | T2 DI PIT #7 TAP 001/010 RPR STRW | ICW
LC | 121632775 | 001/010 | T2 DI PIT #7 TAP 001/010 INS HRDW | TABLEMTN | ETL.5442.POLE.WDPS | 2021-06-29 | 2021-06-28 | 2022-07-14 | 2022-06-28 | 2022-06-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Missing | Hardware-Wood | Install | 45213882 | T2 DI PIT #7 TAP 001/010 INS HRDW | ICW
LC | 121632823 | 001/010 | T2 DI PIT #7 TAP 001/010 RPR CRSW | TABLEMTN | ETL.5442.POLE.WDPS | 2021-06-29 | 2021-06-28 | 2022-07-14 | 2022-06-28 | 2022-06-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45213881 | T2 DI PIT #7 TAP 001/010 RPR CRSW | ICW
LC | 121632825 | 001/010 | T2 DI PIT #7 TAP 001/010 RPR SHLW | TABLEMTN | ETL.5442.POLE.WDPS | 2021-06-29 | 2021-06-28 | 2022-07-14 | 2022-06-28 | 2022-06-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45213880 | T2 DI PIT #7 TAP 001/010 RPR SHLW | ICW
LC | 121632974 | 029/020 | T2 DI CLAY-MARTEL 29/20 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-06-29 | 2021-06-23 | 2022-03-29 | 2022-06-23 | 2022-06-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543390 | DI CLAY-MARTEL 026/367 RPL STRW | 70Y
LC | 121633157 | 005/065 | T2 DI GRN VLLY-CMP EVRS 5/65 RPL INSW | MOSSLNDG | ETL.1710.INSL.CERA | 2021-06-29 | 2021-06-28 | 2022-04-08 | 2022-06-28 | 2022-06-28 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537552 | EI GREEN VALLEY-CAMP EVERS 3/46 RPL INSW | 93I
LC | 121633552 | 003/085 | T2 DI HAMILTON BRANCH 3/85 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-06-29 | 2021-06-24 | 2022-07-22 | 2022-06-24 | 2022-06-24 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31539905 | T2 EI HMLTN BRNCH-CHSTR 0/25 RPL STRW | 70Y
LC | 121633665 | 114/001 | T2 DI HMBLDT-BRDGVL 114/1 RPLC INSW | EUREKA | ETL.1810.INSL.CERA | 2021-06-29 | 2021-06-23 | 2021-10-16 | 2022-06-23 | 2022-06-23 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31544412 | T2 DI HUMBOLDT-BRIDGEVLLE 114/2 RPL INSW | 93I
LC | 121633744 | 010/051 | T2 DI CONTRA COSTA-DELTA S 6/32 RPL INSS | CONCORD | ETL.4490.INSL | 2021-06-29 | 2021-06-25 | 2022-02-14 | 2022-06-25 | 2022-06-25 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31552145 | DI CNTRA CSTA DLTA RPL INSS. 5TWRS | 93K
LC | 121634232 | 007/053 | T2 DI ROCK CREEK-POE 7/53 RPL INSS | TABLEMTN | ETL.5630.INSL.CERA | 2021-06-29 | 2021-06-23 | 2022-08-05 | 2022-06-23 | 2022-06-23 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551263 | T3 DI ROCK CREEK-POE RPL INSS 9TWRS | 93K
LC | 121634312 | :010/002 | T2 DI BELLOTA-RVRBNK-MELON 10/2 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-06-29 | 2021-06-24 | 2022-05-03 | 2022-06-24 | 2022-06-24 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536314 | T2 DI BLT-RVRBNK-MLNS RPL STRW | 70Y
LC | 121634377 | 015/312 | T2 DI COLGATE-PALERMO 15/312 RMV STUB | SACTO | ETL.6500.POLE.WOOD | 2021-06-29 | 2021-06-22 | 2022-05-01 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45200490 | T2 DI COLGATE-PALERMO 15/312 RMV STUB | ICW
LC | 121634379 | 015/312 | T2 DI COLGATE-PALERMO 15/312 RPL INSW | SACTO | ETL.6500.INSL.CERA | 2021-06-29 | 2021-06-22 | 2022-05-11 | 2022-06-22 | 2022-06-22 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541806 | T2 DI COLGATE-PALERMO 15/312 RPL INSW | 93I
LC | 121634443 | 006/134 | T2 DI COTTONWOOD-RED BLFF 6/134 RMV BUTT | TABLEMTN | ETL.6660.POLE.NWOD | 2021-06-29 | 2021-06-25 | 2022-02-02 | 2022-06-25 | 2022-06-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45164607 | T2 DI COTTONWOOD-RED BLFF 6/134 RMV BUTT | ICW
LC | 121634694 | 004/045 | T2 DI SNEATH LANE-PACIFICA 4/45 RPR INSW | METCALF | ETL.7575.INSL.NCER | 2021-06-29 | 2021-06-23 | 2022-05-02 | 2022-06-23 | 2022-06-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45150678 | T2 DI SNEATH LANE-PACIFICA 4/45 RPR INSW | ICW
LC | 121634978 | 016/138 | DI T2 CRAG VIEW-CASCADE 16/138 RPR OPGW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-29 | 2021-06-18 | 2022-09-19 | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45500281 | DI T2 CRAG VIEW-CASCADE 16/138 RPR OPGW | ICW
LC | 121635045 | C002/013 | T2 DI MOSS LANDING-COBURN C2/13 RPL HRDT | MOSSLNDG | ETL.5330.TOWR | 2021-06-29 | 2021-06-23 | 2022-05-18 | 2022-06-23 | 2022-06-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45121221 | T2 DI MOSS LANDING-COBURN C2/13 RPL HRDT | ICQ
LC | 121635207 | 008/056 | T2 DI MRG-SN LD #1 8/56 RPL INSS COMPLET | CONCORD | ETL.2770.INSL | 2021-06-30 | 2021-06-23 | 2022-05-09 | 2022-06-23 | 2022-06-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548202 | T2 DI MRG-SAN LEANDRO #1 RPL INSS 2 TWR | 93K
LC | 121635209 | 027/408 | T2 DI CLAY-MARTEL 27/408 RPR CRSW | VICTOR | ETL.8250.POLE.NWOD | 2021-06-30 | 2021-06-22 | 2022-01-25 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45067391 | T2 DI CLAY-MARTEL 27/408 RPR CRSW | ICW
LC | 121636050 | 017/398 | T2 DI DRM-GRSS VLLY-WMR 17/398 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2021-06-30 | 2021-06-23 | 2022-01-17 | 2022-06-23 | 2022-06-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45135971 | T2 DI DRM-GRSS VLLY-WMR 17/398 RPR STRW | ICW
LC | 121636535 | :008/006 | T2 DI BLLT-RBK-MLS SWST :8/6 RPR STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-06-30 | 2021-06-23 | 2022-05-06 | 2022-06-23 | 2022-06-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45158141 | T2 DI BLLT-RBK-MLS SWST :8/6 RPR STRW | ICW
LC | 121636957 | 002/004 | T2 DI RIO DEL TAP 002/004 RPR GYWW CPLT | EUREKA | ETL.7851.POLE.WOOD | 2021-06-30 | 2021-06-29 | 2022-06-26 | 2022-06-29 | 2022-06-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45158749 | T2 DI RIO DEL TAP 002/004 RPR GYWW | ICW
LC | 121637384 | 022/269 | T2 DI DRUM-SUMMIT #2 22/269L RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2021-06-30 | 2021-06-23 | 2022-06-13 | 2022-06-23 | 2022-06-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121637386 | 022/269 | T2 DI DRUM-SUMMIT #2 22/269R RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2021-06-30 | 2021-06-23 | 2022-06-13 | 2022-06-23 | 2022-06-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121637869 | 044/380 | T2 DI PITT #1 COTTONWOOD 44/380 RPR INSS | TABLEMTN | ETL.5390.INSL.NCER | 2021-06-30 | 2021-06-23 | 2022-03-10 | 2022-06-23 | 2022-06-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45197288 | T2 DI PITT #1 COTTONWOOD 44/380 RPR INSS | ICS
LC | 121638124 | 041/005 | T2 WV FORT ROSS-GUALALA 41/5 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-06-30 | 2021-06-30 | 2022-04-27 | 2022-06-30 | 2022-06-30 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542051 | T2 DI FORT ROSS-GUALALA 45/1 RPL STRW | 70Y
LC | 121638198 | 019/226B | T2 DI DRUM-SUMMIT #1 19/226B RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2021-06-30 | 2021-06-12 | 2022-09-10 | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121638371 | 019/226C | T2 DI DRUM-SUMMIT #1 19/226C RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2021-06-30 | 2021-06-12 | 2022-09-10 | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121638718 | 004/002 | T2 WV LAYTONVILLE-COVELO 4/2 RPL STRW | WILLITS | ETL.7390.POLE.WOOD | 2021-06-30 | 2021-06-30 | 2022-09-06 | 2022-06-30 | 2022-06-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH RTNR FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542885 | T2 DI LAYTONVILLE-COVELO 3/4 RPR WDPKR | 70Y
LC | 121640264 | 000/005 | T2 DI SBRNTE-GRZLY-CLRMNT#2 0/5 RPR GYWW | CONCORD | ETL.3750.POLE.WOOD | 2021-06-30 | 2021-06-24 | 2022-01-31 | 2022-06-24 | 2022-06-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45137555 | T2 DI SBRNTE-GRZLY-CLRMNT#2 0/5 RPR GYWW | ICW
LC | 121640424 | 003/025 | T2 WV PIT #7 TAP 03/025 INS DAMW | TABLEMTN | ETL.5442.INSL.NCER | 2021-06-30 | 2021-06-30 | 2022-07-15 | 2022-06-30 | 2022-06-30 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Steel | Install | 45213839 | T2 WV PIT #7 TAP 03/025 INS DAMW | ICS
LC | 121641040 | 011/132 | EI T2 DRUM-SUMMIT #1 1 011/132R RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-30 | 2021-06-29 | 2022-06-24 | 2022-06-29 | 2022-06-29 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31543339 | T2 EI DRUM-SUMMIT #1 9/111 RPL STRW | 70Y
LC | 121641280 | 014/064 | T2 DI MORRO BAY-MESA 14/64 RPR INSS | PISMOBCH | ETL.5290.INSL | 2021-06-30 | 2021-06-23 | 2021-09-13 | 2022-06-23 | 2022-06-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44963086 | T2 DI MORRO BAY-MESA 14/64 RPR INSS | ICS
LC | 121641285 | 045/186 | T2 DI MIDWAY-WHIRLWIND 45/186 RPL HRDWS | MIDWAY | ETL.6030.TOWR | 2021-06-30 | 2021-06-29 | 2021-12-28 | 2022-06-29 | 2022-06-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45067996 | T2 DI MIDWAY-WHIRLWIND 45/186 RPL HRDWS | ICQ
LC | 121641303 | 007/092 | T2 DI DRUM-SUMMIT #1 7/92R RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-30 | 2021-06-23 | 2022-06-23 | 2022-06-23 | 2022-06-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544924 | T3 EI DRUM-SUMMIT #1 000/007 RPL STRW | 70Y
LC | 121641532 | 025/180 | T2 DI TRINITY-COTTON 25/180 RMV STEP | TABLEMTN | ETL.4040.POLE.STPS | 2021-06-30 | 2021-06-23 | 2022-07-18 | 2022-06-23 | 2022-06-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45212053 | T2 DI TRINITY-COTTON 25/180 RMV STEP | ICW
LC | 121641603 | 015/291 | T2 DI FLTN-MOLNO-COTATI 15/291 RPL STRW | LAKEVLLE | ETL.6910.POLE.WOOD | 2021-06-30 | 2021-06-22 | 2022-02-15 | 2022-06-22 | 2022-06-22 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541603 | EI FLTN-MLIN-CTTI 5/101 RPL STRW | 70Y
LC | 121641660 | 021/008 | T2 DI MNDCN-WLLTS-FRT BRGG 21/8 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-30 | 2021-06-17 | 2022-08-25 | 2022-06-17 | 2022-06-17 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31547473 | T2 EI MNDCN-WLTS-FRT BRG 23/6R RPL POLE | 70Y
LC | 121641798 | 026/006 | T2 DI MNDCN-WILTS-FRT-BRG 26/6 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-06-30 | 2021-06-17 | 2022-09-28 | 2022-06-17 | 2022-06-17 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31543104 | T2 DI MNDCN-WLTS-FRT BRG 25/0 RPL STRW | 70Y
LC | 121641900 | 020/242 | T2 DI DRUM-SUMMIT #2 20/242 RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-30 | 2021-06-23 | 2022-10-16 | 2022-06-23 | 2022-06-23 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121642306 | 025/300 | T2 DI DRUM-SUMMIT #1 25/300 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-30 | 2021-06-18 | 2022-09-10 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31608673 | T2 DI DRUM-SUMMIT #1 25/300 RPL STRW | 70Y
LC | 121642307 | 025/300 | T2 DI DRUM-SUMMIT #1 25/300R RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2021-06-30 | 2021-06-18 | 2022-09-09 | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45193602 | T2 DI DRUM-SUMMIT #1 25/300R RPR STRW | ICW
LC | 121642405 | 014/067 | T2 DI FULTON-PUEBLO 14/67 RPL INSS | LAKEVLLE | ETL.1600.INSL | 2021-06-30 | 2021-06-11 | 2022-02-28 | 2022-06-11 | 2022-06-11 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549865 | T2 DI FULTON-PUEBLO-INSUL RPL INSS 5TWR | 93K
LC | 121642407 | 014/067 | T2 DI SILVERADO-FULTN JCT 14/67 RPL INSS | LAKEVLLE | ETL.1610.INSL | 2021-06-30 | 2021-06-11 | 2022-03-14 | 2022-06-11 | 2022-06-11 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548688 | T2 DI SLVDO FLTN JCT SW RPL INSS 6TWRS | 93K
LC | 121643425 | 021/257 | T2 EI DRUM-SUMMIT #1 21/257 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-07-01 | 2021-06-18 | 2022-08-30 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121643603 | 020/242 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-07-01 | 2021-06-23 | 2022-10-16 | 2022-06-23 | 2022-06-23 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 121643604 | 018/221 | T2 DI DRUM-SUMMIT #2 18/221L RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2021-07-01 | 2021-06-18 | 2022-08-17 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31545492 | T2 DI DRUM-SUMMIT #2 18/221L RPL STRW | 70Y
LC | 121643657 | 022/259 | EI T2 DRUM-SUMMIT #1 22/259 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-07-01 | 2021-06-25 | 2022-08-27 | 2022-06-25 | 2022-06-25 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121644056 | 022/268 | T2 DI DRUM-SUMMIT #1 22/268 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-07-01 | 2021-06-23 | 2022-08-30 | 2022-06-23 | 2022-06-23 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121644234 | 022/261 | EI T2 DRUM- SUMMIT NO. 1 22/261 RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-07-01 | 2021-06-18 | 2022-08-31 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121644292 | 078/395A | T2 DI MALIN-ROUND MTN #2 78/395 RPR FOND | TABLEMTN | ETL.6020.TOWR | 2021-07-01 | 2021-06-27 | 2022-07-15 | 2022-06-27 | 2022-06-27 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45198245 | T2 DI MALIN-ROUND MTN #2 78/395 RPR FOND | ICQ
LC | 121644458 | 001/054 | T2 DI HAMILTON-BRNCH CHSTR 1/54 RPR GYWW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-07-01 | 2021-06-28 | 2022-07-28 | 2022-06-28 | 2022-06-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213379 | T2 DI HAMILTON-BRNCH CHSTR 1/54 RPR GYWW | ICW
LC | 121644659 | 008/088 | T2 DI PARADISE-BUTTE 008/088 RPL HRDD | TABLEMTN | ETL.4396.POLE.STPS | 2021-07-01 | 2021-06-28 | 2022-07-18 | 2022-06-28 | 2022-06-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45261918 | T2 DI PARADISE-BUTTE 008/088 RPL HRDD | ICW
LC | 121644936 | 025/010 | T2 DI MDCN-WLLTS-FRT BRGG 25/10 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-07-01 | 2021-06-17 | 2022-08-13 | 2022-06-17 | 2022-06-17 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31543104 | T2 DI MNDCN-WLTS-FRT BRG 25/0 RPL STRW | 70Y
LC | 121645068 | 006/075 | T2 DI GRN VLLY-CMP EVERS 6/75L RMV BUTT | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-07-01 | 2021-06-28 | 2022-03-02 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45166751 | T2 DI GRN VLLY-CMP EVERS 6/75L RMV BUTT | ICW
LC | 121645195 | 019/086 | T2 EI PITTSBRG-TSLA #20 19/086 GRND WASH | CONCORD | ETL.5520.INSL.CERA | 2021-07-01 | 2021-07-01 | 2022-04-30 | 2022-07-01 | 2022-07-01 | On-time | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Contaminated | Insulator | Ground Wash | 45107137 | T2 EI PITTSBRG-TSLA #20 19/086 GRND WASH | ICD
LC | 121645196 | 019/086 | T2 EI PTSUG-TSL #1 19/86 RPR FOND CMPLT | CONCORD | ETL.5510.TOWR | 2021-07-01 | 2021-07-01 | 2022-04-09 | 2022-07-01 | 2022-07-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190831 | T2 EI PITTSBURG-TESLA #1 19/086 RPR FOND | ICQ
LC | 121645246 | 001/014 | T2 PIT #6 TAP-WOOD 1/14 RPL POLE | TABLEMTN | ETL.5441.POLE.WDPS | 2021-07-01 | 2021-06-19 | 2022-06-20 | 2022-06-19 | 2022-06-19 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | Rotten | Structure-Wood | Replace | 31545615 | T2 PIT #6 TAP-WOOD 1/14 RPL POLE | 70Y
LC | 121645483 | 022/154A | T2 DI CARIBOU-TABLE MTN 22/154A RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2021-07-01 | 2021-06-18 | 2022-06-24 | 2022-06-18 | 2022-06-18 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45212451 | T2 DI CARIBOU-TABLE MTN 22/154A RPR GYWS | ICS
LC | 121645830 | 080/411 | T2 DI MALIN-ROUND MTN #2 80/411 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-01 | 2021-06-30 | 2022-07-12 | 2022-06-30 | 2022-06-30 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215222 | T2 DI MALIN-ROUND MTN #2 80/411 RPR OPGW | ICS
LC | 121646847 | 010/122C | T2 DI DRUM-SUMMIT #2 10/122C RPR STRW | SACTO | ETL.1450.POLE.WOOD | 2021-07-01 | 2021-06-28 | 2022-05-07 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45200493 | T2 DI DRUM-SUMMIT #2 10/122C RPR STRW | ICW
LC | 121647019 | 011/117 | T2 DI PIT#5-RND MTN#1 11/117L RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-01 | 2021-06-28 | 2022-07-22 | 2022-06-28 | 2022-06-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213116 | T2 DI PIT#5-RND MTN#1 11/117 RPR STRW | ICW
LC | 121647104 | 004/057 | T2 DI GRN VLY-CMP EVRS 4/57 RPL HRDD | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-07-01 | 2021-07-01 | 2022-03-03 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45166758 | T2 DI GRN VLY-CMP EVRS 4/57 RPL HRDD | ICW
LC | 121647135 | 034/016 | T2 DI FULTON-HOPLAND 034/016 COMPLETE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-07-01 | 2021-06-28 | 2022-05-12 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45143981 | T2 DI FULTON-HOPLAND 034/016 RPR GYWW | ICW
LC | 121647341 | 009/053 | T2 DI VACA-BAHIA 9/53 INS HRDT | SACTO | ETL.5810.INSL | 2021-07-01 | 2021-06-30 | 2022-06-28 | 2022-06-30 | 2022-06-30 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Missing | Hardware-Tower | Install | 45149868 | T2 DI VACA-BAHIA 9/53 INS HRDT | ICQ
LC | 121647474 | 009/043 | T2 DI DIABLO-GATES #1 9/43 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2021-07-01 | 2021-06-26 | 2022-06-09 | 2022-06-26 | 2022-06-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068524 | T2 DI DIABLO-GATES #1 9/43 RPR GYWS | ICS
LC | 121647604 | 086/000B | T2 DI HMBLDT-BRDGVLL 086/000B RPR SPLW | EUREKA | ETL.1810.INSL.NCER | 2021-07-01 | 2021-06-30 | 2022-06-14 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45149598 | T2 DI HMBLDT-BRDGVLL 086/000B RPR SPLW | ICW
LC | 121647724 | 006/014 | T2 DI VLY SPRNGS-MRTLL #1 6/14 RPL HWRW | VICTOR | ETL.8240.POLE.STPS | 2021-07-01 | 2021-07-01 | 2022-02-26 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45158143 | T2 DI VLY SPRNGS-MRTLL #1 6/14 RPL HWRW | ICW
LC | 121647743 | 048/204B | T2 DI CAL FLATS GATES 48/204A RPL INSS | FRESNO | ETL.5281.INSL.CERA | 2021-07-01 | 2021-07-01 | 2022-05-31 | 2022-07-01 | 2022-07-01 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31550186 | DI CALFRNIA FLATS SW STA RPL INSS 2TWRS | 93K
LC | 121648426 | 000/007 | T2 DI SLT SPNGS TGR CRK 000/007 RPR INSS | VICTOR | ETL.3500.INSL | 2021-07-01 | 2021-06-17 | 2022-06-17 | 2022-06-17 | 2022-06-17 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45158144 | T2 DI SLT SPNGS TGR CRK 000/007 RPR INSS | ICS
LC | 121648442 | 008/098C | T2 DI DRUM-SUMMIT #2 8/98 INSTALL HRDW | SACTO | ETL.1450.POLE.NWOD | 2021-07-01 | 2021-06-28 | 2022-06-10 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR NTDE | Missing | Hardware-Wood | Install | 45200494 | T2 DI DRUM-SUMMIT #2 8/98 INSTALL HRDW | ICW
LC | 121648681 | 078/395A | T2 DI MALIN-ROUND MTN #2 78/395 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2021-07-01 | 2021-06-27 | 2022-07-12 | 2022-06-27 | 2022-06-27 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45223891 | T2 DI MALIN-ROUND MTN #2 78/395 RPR INSS | ICS
LC | 121648742 | B025/580 | T2 DI DRM-GRSS VLY WMR B25/580 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-07-01 | 2021-06-28 | 2022-04-13 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45193825 | T2 DI DRM-GRSS VLY WMR B25/580 RPR GYWW | ICW
LC | 121648812 | 022/154C | T2 DI CARIBOU-TABLE MTN 22/154C RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2021-07-01 | 2021-06-27 | 2022-06-24 | 2022-06-27 | 2022-06-27 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45212452 | T2 DI CARIBOU-TABLE MTN 22/154C RPR GYWS | ICS
LC | 121648825 | 011/061 | T2 DI TESLA-NEWARK #1 11/61 RMV NEST | CONCORD | ETL.5720.TOWR | 2021-07-01 | 2021-06-28 | 2021-09-30 | 2022-06-28 | 2022-06-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44959071 | T2 DI TESLA-NEWARK #1 11/61 RMV NEST | ICS
LC | 121648827 | B025/579 | T2 DI DRM-GRSS VLLY WMR B25/579 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-07-01 | 2021-06-28 | 2022-06-28 | 2022-06-28 | 2022-06-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31590280 | T2 DI DRM-GRSS VLLY WMR B25/579 RPL STRW | 70Y
LC | 121649019 | 017/006 | T2 DI CLEAR LAKE-KONOCTI 17/6 RPL STRW | LAKEVLLE | ETL.6852.POLE.WOOD | 2021-07-01 | 2021-07-01 | 2022-02-03 | 2022-07-01 | 2022-07-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31545484 | T2 DI CLEAR LAKE-KONOCTI 17/6 RPL STRW | 70Y
LC | 121649049 | 012/252 | T2 DI CTTNWD-RED BLUFF 12/252 RMV DEBRIS | TABLEMTN | ETL.6660.POLE.NWOD | 2021-07-01 | 2021-06-28 | 2022-06-06 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45197172 | T2 DI CTTNWD-RED BLUFF 12/252 RMV DEBRIS | ICW
LC | 121649120 | 023/274B | T2 DI DRUM-SUMMIT #1 23/274B RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2021-07-01 | 2021-06-27 | 2022-09-01 | 2022-06-27 | 2022-06-27 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121649157 | 030/010 | T2 DI FULTON-HOPLAND 30/10 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-07-01 | 2021-06-28 | 2022-06-24 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143965 | T2 DI FULTON-HOPLAND 30/10 RPR STRW | ICW
LC | 121649245 | 006/131 | T2 DI COTTONWOOD-RED BLF 6/131 RMV BUTT | TABLEMTN | ETL.6660.POLE.NWOD | 2021-07-01 | 2021-06-25 | 2022-06-06 | 2022-06-25 | 2022-06-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45197115 | T2 DI COTTONWOOD-RED BLF 6/131 RMV BUTT | ICW
LC | 121649259 | 010/060 | T2 DI TESLA-NEWARK #1 010/060 RMV NEST | CONCORD | ETL.5720.TOWR | 2021-07-01 | 2021-06-28 | 2021-09-30 | 2022-06-28 | 2022-06-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 44959069 | T2 DI TESLA-NEWARK #1 010/060 RMV NEST | ICS
LC | 121649280 | 019/435 | T2 DI DRM GRS VLY WMR 19/435 RMV BUTT | SACTO | ETL.6760.POLE.WOOD | 2021-07-01 | 2021-06-28 | 2022-01-13 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44930732 | T2 DI DRM GRS VLY WMR 19/435 RMV BUTT | ICW
LC | 121649292 | 000/016 | T2 DI LAYTONVILLE-COVELO 0/16 RPL POLE | WILLITS | ETL.7390.POLE.WOOD | 2021-07-01 | 2021-06-28 | 2022-06-14 | 2022-06-28 | 2022-06-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE SPCR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542885 | T2 DI LAYTONVILLE-COVELO 3/4 RPR WDPKR | 70Y
LC | 121649299 | 011/056 | T2 DI CNTRA CSTA-DLTA 07/037 RPL INSS | CONCORD | ETL.4490.INSL.NCER | 2021-07-01 | 2021-06-28 | 2022-06-08 | 2022-06-28 | 2022-06-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31552145 | DI CNTRA CSTA DLTA RPL INSS. 5TWRS | 93K
LC | 121649398 | 023/274C | T2 DI DRUM-SUMMIT #1 023/274C RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2021-07-01 | 2021-06-28 | 2022-09-01 | 2022-06-28 | 2022-06-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121649546 | 001/000 | T2 DI LAYTONVILLE-COVELO 1/0 RPL POLE | WILLITS | ETL.7390.POLE.WOOD | 2021-07-01 | 2021-06-28 | 2022-06-13 | 2022-06-28 | 2022-06-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542885 | T2 DI LAYTONVILLE-COVELO 3/4 RPR WDPKR | 70Y
LC | 121651688 | 011/145A | T2 DI WST PNT-VLLY SPGS 11/145A RPL HRDD | VICTOR | ETL.8350.POLE.NWOD | 2021-07-01 | 2021-06-28 | 2022-05-10 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45158145 | T2 DI WST PNT-VLLY SPGS 11/145A RPL HRDD | ICW
LC | 121651761 | 012/277 | T2 DI DRM-GRSS VLLY-WMR 12/277 INS HRDD | SACTO | ETL.6760.POLE.WOOD | 2021-07-01 | 2021-06-28 | 2022-07-15 | 2022-06-28 | 2022-06-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45193606 | T2 DI DRM-GRSS VLLY-WMR 12/277 INS HRDD | ICW
LC | 121653164 | 019/089 | T2 DI MSS LNDNG-LS BNS 019/089 RPR INSS | MOSSLNDG | ETL.6040.TOWR | 2021-07-02 | 2021-07-01 | 2022-08-15 | 2022-07-01 | 2022-07-01 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Repair | 44893009 | T2 DI MSS LNDNG-LS BNS 019/089 RPR INSS | ICS
LC | 121653173 | 082/418 | T2 DI MLN-RND MTN #2 82/418 RPL OPGW INS | TABLEMTN | ETL.6020.TOWR | 2021-07-02 | 2021-06-30 | 2022-07-12 | 2022-06-30 | 2022-06-30 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 45215220 | T2 DI MLN-RND MTN #2 82/418 RPL OPGW INS | ICS
LC | 121653176 | 082/418 | T2 DI MALIN-RND MTN #2 082/418 RPL HRDT | TABLEMTN | ETL.6020.TOWR | 2021-07-02 | 2021-06-30 | 2022-07-15 | 2022-06-30 | 2022-06-30 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45198254 | T2 DI MALIN-RND MTN #2 082/418 RPL HRDT | ICQ
LC | 121653179 | 082/418 | T2 DI MALIN-RND MTN #2 082/418 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-07-02 | 2021-06-30 | 2022-07-15 | 2022-06-30 | 2022-06-30 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45198255 | T2 DI MALIN-RND MTN #2 082/418 RPR GYWS | ICS
LC | 121653362 | 001/024 | T2 DI COTTONWD-BENTON #2 1/24L RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-02 | 2021-07-02 | 2022-06-04 | 2022-07-02 | 2022-06-30 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31511046 | DI CTTNWD BNTN #2 5/53 RPL POLE (ENG) | 70Y
LC | 121653363 | 001/024 | T2 DI COTTONWD-BENTON #2 1/24R RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-02 | 2021-07-02 | 2022-06-04 | 2022-07-02 | 2022-06-30 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31511046 | DI CTTNWD BNTN #2 5/53 RPL POLE (ENG) | 70Y
LC | 121653365 | 005/024 | T2 DI PTSBRG-TSL #2 5/24 RPL INSS | CONCORD | ETL.5520.INSL.CERA | 2021-07-02 | 2021-07-02 | 2021-12-02 | 2022-07-02 | 2022-07-02 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31461401 | DI PTSBRG-TSL #2 5/24 RPL INSS. | 93K
LC | 121653366 | 005/024 | T2 DI PTSBRG-TSL #2 5/24 RPL HRDS | CONCORD | ETL.5520.INSL.CERA | 2021-07-02 | 2021-07-02 | 2021-12-02 | 2022-07-02 | 2022-07-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44929301 | T2 DI PTSBRG-TSL #2 5/24 RPL HRDS | ICQ
LC | 121653517 | 000/015 | DI T2 COLGATE-PALERMO 000/015 RPR GYWW | SACTO | ETL.6500.POLE.STPS | 2021-07-02 | 2021-06-22 | 2022-05-20 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45200525 | DI T2 COLGATE-PALERMO 000/015 RPR GYWW | ICW
LC | 121653518 | 000/015 | DI T2 COLGATE-PALERMO 000/015 RPR GYWW | SACTO | ETL.6500.POLE.STPS | 2021-07-02 | 2021-06-22 | 2022-05-20 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45200527 | DI T2 COLGATE-PALERMO 000/015 RPR GYWW | ICW
LC | 121653519 | 000/015 | DI T2 COLGATE-PALERMO 000/015 RPR GYWW | SACTO | ETL.6500.POLE.STPS | 2021-07-02 | 2021-06-22 | 2022-05-20 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45200529 | DI T2 COLGATE-PALERMO 000/015 RPR GYWW | ICW
LC | 121653631 | 000/015 | DI T2 COLGATE-PALERMO 000/015 RMV DEBRIS | SACTO | ETL.6500.POLE.STPS | 2021-07-02 | 2021-06-22 | 2022-05-22 | 2022-06-22 | 2022-06-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45200530 | DI T2 COLGATE-PALERMO 000/015 RMV DEBRIS | ICW
LC | 121653905 | 025/195 | T2 DI MID FRK-GOLD HILL 025/195 RPL STRW | SACTO | ETL.5140.POLE.WDPS | 2021-07-02 | 2021-06-30 | 2022-11-03 | 2022-06-30 | 2022-06-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546023 | T2 DI MDD FRK-GLD HLL 026/201 RPL STRW | 70Y
LC | 121653907 | 025/195 | T2 DI MID FRK-GOLD HILL 25/195 RPL STRW | SACTO | ETL.5140.POLE.WDPS | 2021-07-02 | 2021-06-30 | 2022-11-03 | 2022-06-30 | 2022-06-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546023 | T2 DI MDD FRK-GLD HLL 026/201 RPL STRW | 70Y
LC | 121653911 | 010/158 | T2 DI SQC-SY SW ST 10/158 RPR STRW CMPLT | PISMOBCH | ETL.3700.POLE.WDPS | 2021-07-02 | 2021-06-30 | 2022-04-12 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45069347 | T2 DI SISQUOC-SY SW STA 010/158 RPR STRW | ICW
LC | 121654237 | 007/057 | NRP T2 PLACER-GOLD HILL #1 7/57 RMV VEG | SACTO | ETL.3340.TOWR | 2021-07-02 | 2021-07-02 | 2022-01-07 | 2022-07-02 | 2022-07-02 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121655277 | 015/203 | T2 DI WTSNVLLE-SLNS 015/203 RMV BUTT | MOSSLNDG | ETL.8310.POLE.WDPS | 2021-07-02 | 2021-06-28 | 2021-09-28 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 44981675 | T2 DI WTSNVLLE-SLNS 015/203 RMV BUTT | ICW
LC | 121655310 | 015/203 | T2 DI WTSNVLLE-SLNS 015/203 GRND WASH | MOSSLNDG | ETL.8310.INSL.CERA | 2021-07-02 | 2021-06-28 | 2021-09-28 | 2022-06-28 | 2022-06-28 | On-time | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Contaminated | Insulator | Ground Wash | 44981676 | T2 DI WTSNVLLE-SLNS 015/203 GRND WASH | ICD
LC | 121655619 | 016/008 | T2 DI HUMB BAY-RIO DELL 16/8 RPL INSW | EUREKA | ETL.7100.INSL.CERA | 2021-07-02 | 2021-06-29 | 2022-04-23 | 2022-06-29 | 2022-06-29 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542056 | T2 DI HMBLDT BY-RIO DL JCT 18/1 RPL INSW | 93I
LC | 121655657 | 011/113 | T2 DI PIT #5-RND MTN #2 11/113 COMPLETE | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-02 | 2021-07-01 | 2022-06-13 | 2022-07-01 | 2022-07-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31601295 | EI T2 PIT #5-ROUND MTN #2 7/72 RPL STRW | 70Y
LC | 121655658 | 011/113 | T2 DI PIT #5-RND MTN #2 11/113 COMPLETE | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-02 | 2021-07-01 | 2022-06-13 | 2022-07-01 | 2022-07-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31601295 | EI T2 PIT #5-ROUND MTN #2 7/72 RPL STRW | 70Y
LC | 121655659 | 011/113 | T2 DI PIT #5-RND MTN #2 11/113 COMPLETE | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-02 | 2021-07-01 | 2022-06-13 | 2022-07-01 | 2022-07-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31601295 | EI T2 PIT #5-ROUND MTN #2 7/72 RPL STRW | 70Y
LC | 121655933 | 020/011 | T2 DI MNDCN-PHL JCT-HPLND 20/11 RPR GYWW | WILLITS | ETL.7520.POLE.NWOD | 2021-07-02 | 2021-07-01 | 2022-03-08 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45142585 | T2 DI MNDCN-PHL JCT-HPLND 20/11 RPR GYWW | ICW
LC | 121656135 | 003/057 | T2 DI GRN VLLY-PAUL SWT 3/57 RMV DEBRIS | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-07-02 | 2021-06-30 | 2022-03-10 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45211627 | T2 DI GRN VLLY-PAUL SWT 3/57 RMV DEBRIS | ICW
LC | 121656672 | 015/489 | T2 DI SPAULDING-SUMMIT 015/489 RPL HRDD | SACTO | ETL.8060.POLE.WOOD | 2021-07-02 | 2021-06-22 | 2022-08-05 | 2022-06-22 | 2022-06-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 44930748 | T2 DI SPAULDING-SUMMIT 015/489 RPL HRDD | ICW
LC | 121656990 | 018/429 | T2 DI DRM GRSS VLY WMR 018/429 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-07-02 | 2021-06-28 | 2022-06-30 | 2022-06-28 | 2022-06-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE SPCR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31595647 | T3 DI DRM GRAS VLY WMAR 3/79 RPL STRW | 70Y
LC | 121657701 | 014/185 | EI T2 DELTA-MTN GATE JCT 14/185 RPR GYWW | TABLEMTN | ETL.6750.POLE.STPS | 2021-07-02 | 2021-07-02 | 2022-07-24 | 2022-07-02 | 2022-07-02 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296783 | EI T2 DELTA-MTN GATE JCT 14/185 RPR GYWW | ICW
LC | 121657836 | 011/118 | T2 DI PIT #5-RND MTN#1 11/118 RMV DEBRIS | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-02 | 2021-06-28 | 2022-06-13 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45213118 | T2 DI PIT #5-RND MTN#1 11/118 RMV DEBRIS | ICW
LC | 121658152 | 014/175 | EI T2 DELTA-MTN GATE JCT 14/175 RPR GYWW | TABLEMTN | ETL.6750.POLE.STPS | 2021-07-02 | 2021-07-02 | 2022-07-24 | 2022-07-02 | 2022-07-02 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45297921 | EI T2 DELTA-MTN GATE JCT 14/175 RPR GYWW | ICS
LC | 121658267 | :006/002 | T2 DI BELLOTA-RVRBNK-MELNES 6/2 BACKFILL | VICTOR | ETL.1070.POLE.NWOD | 2021-07-02 | 2021-06-28 | 2022-02-16 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45158146 | T2 DI BELLOTA-RVRBNK-MELNES 6/2 BACKFILL | ICW
LC | 121658760 | 036/002 | T2 DI MENDCNO-WLLTS-FT BRG 36/2 RPR SPLW | WILLITS | ETL.7550.POLE.WOOD | 2021-07-02 | 2021-07-01 | 2022-05-15 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45148601 | T2 DI MENDCNO-WLLTS-FT BRG 36/2 RPR SPLW | ICW
LC | 121658880 | 011/077 | DI T2 METCALF-GREEN VLLEY 11/77 COMPLETE | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-07-02 | 2021-06-30 | 2022-08-21 | 2022-06-30 | 2022-06-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545867 | DI METCALF-GREEN VALLEY 11/77 RPL STRW | 70Y
LC | 121658943 | 015/067 | T2 DI SL OBISPO-OCEANO 15/67L RPL STRW | PISMOBCH | ETL.3530.POLE.WDPS | 2021-07-02 | 2021-07-01 | 2022-07-29 | 2022-07-01 | 2022-07-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545570 | T2 DI SL OBISPO-OCEANO 15/67L RPL STRW | 70Y
LC | 121658944 | 015/067 | T2 DI SL OBISPO-OCEANO 15/67C RPL STRW | PISMOBCH | ETL.3530.POLE.WDPS | 2021-07-02 | 2021-07-01 | 2022-07-29 | 2022-07-01 | 2022-07-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545570 | T2 DI SL OBISPO-OCEANO 15/67L RPL STRW | 70Y
LC | 121659234 | 000/004 | WV T2 JEFFERSON #1 0/4 RPL INSS | METCALF | ETL.6831.INSL.CERA | 2021-07-02 | 2021-07-02 | 2022-09-12 | 2022-07-02 | 2022-07-02 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31597367 | WV T2 JEFFERSON #1 0/4 RPL INSS | 93K
LC | 121659317 | 024/188 | T2 DI MIDDLE FRK-GLD HLL 24/188 RMV DBRS | SACTO | ETL.5140.POLE.STPS | 2021-07-02 | 2021-06-30 | 2021-12-15 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45017975 | T2 DI MIDDLE FRK-GLD HLL 24/188 RMV DBRS | ICW
LC | 121659340 | 005/070 | T2 DI GRN VLY PAUL SWT 005/70 RMV DEBRIS | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-07-02 | 2021-06-30 | 2022-05-02 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45211628 | T2 DI GRN VLY PAUL SWT 005/70 RMV DEBRIS | ICW
LC | 121659343 | 005/070 | T2 DI GRN VLY PAUL SWT 005/070 RPR INSW | MOSSLNDG | ETL.1730.INSL.CERA | 2021-07-02 | 2021-06-30 | 2022-05-02 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair | 45213435 | T2 DI GRN VLY PAUL SWT 005/070 RPR INSW | ICW
LC | 121659348 | 007/078A | T2 DI GRN VLY PAUL SWT 007/078A RPR STRW | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-07-02 | 2021-06-30 | 2022-05-05 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213542 | T2 DI GRN VLY PAUL SWT 007/078A RPR STRW | ICW
LC | 121659349 | 026/201 | T2 DI MDD FRK-GLD HLL 026/201L RPL STRW | SACTO | ETL.5140.POLE.WDPS | 2021-07-02 | 2021-06-30 | 2022-10-02 | 2022-06-30 | 2022-06-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31546023 | T2 DI MDD FRK-GLD HLL 026/201 RPL STRW | 70Y
LC | 121659446 | 000/007 | T2 DI HAT CREEK #1-WESTWOOD 0/7 RPR GYWW | TABLEMTN | ETL.7030.POLE.WOOD | 2021-07-02 | 2021-06-28 | 2022-05-02 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45212256 | T2 DI HAT CREEK #1-WESTWOOD 0/7 RPR GYWW | ICW
LC | 121660510 | 005/070 | T2 DI HAT CREEK #1-PIT #1 5/70L RPL STRW | TABLEMTN | ETL.7020.POLE.WDPS | 2021-07-03 | 2021-07-01 | 2022-07-25 | 2022-07-01 | 2022-07-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545997 | T2 DI HAT CREEK #1-PIT #1 5/70 RPL STRW | 70Y
LC | 121660512 | 005/070 | T2 DI HAT CREEK #1-PIT #1 5/70C RPL STRW | TABLEMTN | ETL.7020.POLE.WDPS | 2021-07-03 | 2021-07-01 | 2022-07-25 | 2022-07-01 | 2022-07-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545997 | T2 DI HAT CREEK #1-PIT #1 5/70 RPL STRW | 70Y
LC | 121660513 | 005/070 | T2 DI HAT CREEK #1-PIT #1 5/70R RPL STRW | TABLEMTN | ETL.7020.POLE.WDPS | 2021-07-03 | 2021-07-01 | 2022-07-25 | 2022-07-01 | 2022-07-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545997 | T2 DI HAT CREEK #1-PIT #1 5/70 RPL STRW | 70Y
LC | 121660555 | 007/036 | T2 DI BRENTWOOD-KELSO 7/36 RPR FOND | CONCORD | ETL.4410.TOWR | 2021-07-03 | 2021-06-28 | 2021-12-28 | 2022-06-28 | 2022-06-28 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45106485 | T2 DI BRENTWOOD-KELSO 7/36 RPR FOND | ICQ
LC | 121660556 | 007/036 | T2 DI BRENTWOOD-KELSO 7/36 RPR INSS | CONCORD | ETL.4410.INSL.NCER | 2021-07-03 | 2021-06-28 | 2021-09-10 | 2022-06-28 | 2022-06-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44958975 | T2 DI BRENTWOOD-KELSO 7/36 RPR INSS | ICS
LC | 121660600 | 007/084 | T2 DI GRN VLLY PL SWT 007/084 RPL STRW | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-07-03 | 2021-06-30 | 2022-08-25 | 2022-06-30 | 2022-06-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545862 | T2 DI GRN VLLY PL SWT 007/084 RPL STRW | 70Y
LC | 121660602 | 007/084 | T2 DI GRN VLLY PL SWT 007/084 RPL STRW | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-07-03 | 2021-06-30 | 2022-08-25 | 2022-06-30 | 2022-06-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545862 | T2 DI GRN VLLY PL SWT 007/084 RPL STRW | 70Y
LC | 121660639 | 002/025 | T2 DI CTTNWD-BENTON #2 002/025L RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-03 | 2021-07-01 | 2022-06-04 | 2022-07-01 | 2022-07-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31511046 | DI CTTNWD BNTN #2 5/53 RPL POLE (ENG) | 70Y
LC | 121660643 | 012/060 | T2 DI CNTR CST DLT SW 12/60 RPL INSS | CONCORD | ETL.4490.INSL | 2021-07-03 | 2021-06-28 | 2022-02-15 | 2022-06-28 | 2022-06-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540225 | EI CONTRA COSTA-DELTA SWI REPL INSS 3TWR | 93K
LC | 121660644 | 008/041 | T2 DI BRENTWOOD-KELSO 8/41 RPR INSS | CONCORD | ETL.4410.INSL.NCER | 2021-07-03 | 2021-06-28 | 2021-09-10 | 2022-06-28 | 2022-06-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44958973 | T2 DI BRENTWOOD-KELSO 8/41 RPR INSS | ICS
LC | 121660645 | 012/060 | T2 DI CNTR CST DLT SW 8/41 HANGER | CONCORD | ETL.4490.INSL | 2021-07-03 | 2021-06-28 | 2022-02-15 | 2022-06-28 | 2022-06-28 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 45084080 | T2 DI CNTR CST DLT SW 8/41 HANGER | ICQ
LC | 121660670 | 002/025 | T2 DI CTTNWD-BENTON #2 002/025R RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-03 | 2021-07-01 | 2022-06-04 | 2022-07-01 | 2022-07-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31511046 | DI CTTNWD BNTN #2 5/53 RPL POLE (ENG) | 70Y
LC | 121660805 | 025/304 | T2 DI DRUM-SUMMIT #2 25/304 RPL HRDW | SACTO | ETL.1450.POLE.STPS | 2021-07-03 | 2021-06-28 | 2022-06-10 | 2022-06-28 | 2022-06-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45193608 | T2 DI DRUM-SUMMIT #2 25/304 RPL HRDW | ICW
LC | 121661464 | 004/045 | T2 DI CTTNWD-BENTON #2 004/045L RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-03 | 2021-07-01 | 2022-07-23 | 2022-07-01 | 2022-07-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213119 | T2 DI CTTNWD-BENTON #2 004/045 RPR STRW | ICW
LC | 121661466 | 004/045 | T2 DI CTTNWD-BENTON #2 004/045R RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-03 | 2021-07-01 | 2022-07-23 | 2022-07-01 | 2022-07-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213140 | T2 DI CTTNWD-BENTON #2 004/045 RPR STRW | ICW
LC | 121661522 | 028/240 | T2 DI BRDGVLLE-CTTNWD X28/240 COMPLETE | TABLEMTN | ETL.1110.INSL.CERA | 2021-07-03 | 2021-07-01 | 2022-06-22 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45213760 | T2 DI BRDGVLLE-CTTNWD X28/240 RPR INSW | ICW
LC | 121661532 | 000/002 | T2 DI HLLSDLE HLF MN BY 0/2 RPR IBWW | METCALF | ETL.7060.POLE.WOOD | 2021-07-03 | 2021-06-30 | 2021-09-29 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAR | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 44931582 | T2 DI HLLSDLE HLF MN BY 0/2 RPR IBWW | ICW
LC | 121661623 | 015/067 | T2 DI SL OBISPO-OCEANO 15/67R RPL STRW | PISMOBCH | ETL.3530.POLE.WDPS | 2021-07-03 | 2021-07-01 | 2022-07-29 | 2022-07-01 | 2022-07-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545570 | T2 DI SL OBISPO-OCEANO 15/67L RPL STRW | 70Y
LC | 121661803 | 004/043 | T2 DI COTTONWOD-BENTN 2 4/43L RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-03 | 2021-07-01 | 2022-07-23 | 2022-07-01 | 2022-07-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213141 | T2 DI COTTONWOOD-BENTON 2 4/43 RPR STRW | ICW
LC | 121662032 | 010/122A | T2 DI DRUM-SUMT #2 10/122A RPL INSW | SACTO | ETL.1450.INSL.NCER | 2021-07-03 | 2021-06-28 | 2021-10-09 | 2022-06-28 | 2022-06-28 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31522060 | T3 DI DRUM-SUMMIT #2 5/62A RPLC INSW | 93I
LC | 121662034 | 019/004 | T2 DI MENDO-WILL-FT BRAGG 19/4 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2021-07-03 | 2021-07-01 | 2022-08-24 | 2022-07-01 | 2022-07-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145821 | T2 DI MENDO-WILL-FT BRAGG 19/4 RPR GYWW | ICW
LC | 121662075 | 004/060 | T2 DI GREEN VLLY-PAUL SWT 4/60 RPL STRW | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-07-03 | 2021-06-30 | 2022-10-28 | 2022-06-30 | 2022-06-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31545860 | T2 DI GREEN VLLY-PAUL SWT 4/60L RPL STRW | 70Y
LC | 121662142 | 010/122B | T2 DI DRUM-SUMT #2 10/122B RPL INSW | SACTO | ETL.1450.INSL.NCER | 2021-07-03 | 2021-06-28 | 2021-10-09 | 2022-06-28 | 2022-06-28 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31522060 | T3 DI DRUM-SUMMIT #2 5/62A RPLC INSW | 93I
LC | 121662144 | 006/078 | T2 DI GREEN VLY-PL SWT 6/78 RPL INSW | MOSSLNDG | ETL.1730.INSL.NCER | 2021-07-03 | 2021-06-30 | 2022-05-05 | 2022-06-30 | 2022-06-30 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31591536 | T2 DI GREEN VLY-PL SWT 6/78 RPL INSW | 93I
LC | 121662148 | 006/078 | T2 DI GREEN VLY-PL SWT 6/78 RPR CRSW | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-07-03 | 2021-06-30 | 2022-05-05 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45213395 | T2 DI GREEN VLY-PL SWT 6/78 RPR CRSW | ICW
LC | 121662175 | 007/108 | T2 DI CENTERVILLE-TBL MTN 7/108 REFRAME | TABLEMTN | ETL.6320.POLE.WOOD | 2021-07-03 | 2021-06-28 | 2022-04-26 | 2022-06-28 | 2022-06-28 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31544906 | EI CNTRVLLE-TABLE MTN 016/289 REFRAME | 93E
LC | 121662254 | 028/009A | T2 DI MENDO-WILLITS-FRT 28/9A RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-07-03 | 2021-07-01 | 2022-08-17 | 2022-07-01 | 2022-07-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31546021 | T2 DI MENDO-WILL-FT BRAGG 28/9 RPL POLE | 70Y
LC | 121662524 | 016/233 | T2 DI SISQC SNTA YNZ SS 016/233 RPL INSW | PISMOBCH | ETL.3700.INSL.NCER | 2021-07-03 | 2021-06-30 | 2022-04-14 | 2022-06-30 | 2022-06-30 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543110 | DI SISQUOC-SANTA YNEZ 2/45 RPL INSW | 93I
LC | 121662526 | 016/233 | T2 DI SISQC-SNTA YNZ SS 16/233L RPR GYWW | PISMOBCH | ETL.3700.POLE.WDPS | 2021-07-03 | 2021-06-30 | 2022-04-14 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069348 | T2 DI SISQC SNTA YNZ SS 016/233 RPR GYWW | ICW
LC | 121662527 | 016/233 | T2 DI SSQC SNT YNZ SS 16/233C CMPLTD | PISMOBCH | ETL.3700.POLE.WDPS | 2021-07-03 | 2021-06-30 | 2022-04-14 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069349 | T2 DI SISQC SNTA YNZ SS 016/233 RPR GYWW | ICW
LC | 121662529 | 016/233 | T2 DI SISQC SNTA YNZ SS 16/233R RPR GYWW | PISMOBCH | ETL.3700.POLE.WDPS | 2021-07-03 | 2021-06-30 | 2022-04-14 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069350 | T2 DI SISQC SNTA YNZ SS 016/233 RPR GYWW | ICW
LC | 121662570 | 016/233 | T2 DI SISQC SNTA YNZ SS 16/233R CMPLTD | PISMOBCH | ETL.3700.POLE.WDPS | 2021-07-03 | 2021-06-30 | 2022-04-14 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45069351 | T2 DI SISQC SNTA YNZ SS 016/233 RPR STRW | ICW
LC | 121662573 | 016/233 | T2 DI SISQC SNTA YNZ SS 16/233C CMPLTD | PISMOBCH | ETL.3700.POLE.WDPS | 2021-07-03 | 2021-06-30 | 2022-04-14 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45069352 | T2 DI SISQC SNTA YNZ SS 016/233 RPR STRW | ICW
LC | 121662576 | 011/115 | T2 DI PT#5RD MN #2 11/115 RPL HRDD CMPLT | TABLEMTN | ETL.5430.POLE.WOOD | 2021-07-03 | 2021-07-01 | 2022-06-09 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213816 | T2 DI PIT #5-RND MTN #2 11/115 RPL HRDD | ICW
LC | 121662578 | 011/115 | T2 DI PIT#5-RND MTN#2 11/115 RPR STRW | TABLEMTN | ETL.5430.POLE.WOOD | 2021-07-03 | 2021-07-01 | 2022-06-09 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213814 | T2 DI PIT#5-RND MTN#2 11/115 RPR STRW | ICW
LC | 121662608 | 003/045 | T2 DI BRNS-LN STR #1 003/045 RPR SPLW | MOSSLNDG | ETL.6230.INSL | 2021-07-03 | 2021-07-01 | 2021-09-23 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 44932398 | T2 DI BRNS-LN STR #1 003/045 RPR SPLW | ICW
LC | 121662651 | 020/186 | T2 DI UKIAH-HPLND-CLVRDL 20/186 RPR STRW | LAKEVLLE | ETL.4050.POLE.WDPS | 2021-07-03 | 2021-07-01 | 2022-01-27 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45137837 | T2 DI UKIAH-HPLND-CLVRDL 20/186 RPR STRW | ICW
LC | 121662684 | 005/071 | T2 DI GRN VLY-CAMP EVR 5/71 RPL STRW COA | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-07-03 | 2021-06-28 | 2022-04-08 | 2022-06-28 | 2022-06-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545456 | T2 DI GRN VLY-CAMP EVER 5/71 RPL STRW | 70Y
LC | 121662714 | 024/186 | T2 DI PARADISE-TBL MTN 024/186 RPR INSW | TABLEMTN | ETL.4316.INSL.NCER | 2021-07-03 | 2021-06-30 | 2022-05-16 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45197380 | T2 DI PARADISE-TBL MTN 024/186 RPR INSW | ICW
LC | 121662802 | 022/155 | T2 DI CARIBOU-TABLE MTN 22/155L RPR GYWS | TABLEMTN | ETL.4440.POLE.STPS | 2021-07-03 | 2021-07-01 | 2022-06-24 | 2022-07-01 | 2022-07-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45212453 | T2 DI CARIBOU-TABLE MTN 22/155A RPR GYWS | ICS
LC | 121662882 | 028/009 | T2 DI MENDO-WILL-FT BRAGG 28/9 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-07-03 | 2021-07-02 | 2022-08-17 | 2022-07-02 | 2022-07-02 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31546021 | T2 DI MENDO-WILL-FT BRAGG 28/9 RPL POLE | 70Y
LC | 121662885 | 016/308 | T2 DI FLTN-MLNO-COTATI 016/308 RPR GYWW | LAKEVLLE | ETL.6910.POLE.WOOD | 2021-07-03 | 2021-07-01 | 2022-02-03 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45138291 | T2 DI FLTN-MLNO-COTATI 016/308 RPR GYWW | ICW
LC | 121662998 | 026/000 | T2 DI MENDO-WILL-FT BRAGG 26/0 RPR WDPKR | WILLITS | ETL.7550.POLE.WOOD | 2021-07-03 | 2021-07-01 | 2022-05-19 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45148563 | T2NT DI MEND-WILL-FT BRAGG 26/0 RMV BUTT | ICW
LC | 121664678 | 004/056 | T2 DI GRN VLY-CMP EVERS 4/56 RMV DEBRIS | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-07-05 | 2021-07-01 | 2022-03-02 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45166747 | T2 DI GRN VLY-CMP EVERS 4/56 RMV DEBRIS | ICW
LC | 121664700 | 004/065 | T2 DI GRN VLY-PL SWT 4/65 INS HRDW | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-07-05 | 2021-06-30 | 2022-03-11 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Missing | Hardware-Wood | Install | 45211626 | T2 DI GRN VLY-PL SWT 4/65 INS HRDW | ICW
LC | 121665658 | 005/040 | T3 DI GREEN VLY-LLAGAS 5/40 RPL INSW | MOSSLNDG | ETL.1720.INSL.CERA | 2021-07-06 | 2021-07-05 | 2022-08-03 | 2022-01-01 | 2022-01-05 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545993 | T3 DI GREEN VLY-LLAGAS 5/40 RPL INSW | 93I
LC | 121665945 | 023/274A | T2 DI DRUM-SUMMIT #1 023/274A RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2021-07-06 | 2021-06-28 | 2022-09-01 | 2022-06-28 | 2022-06-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544898 | T2 EI DRUM-SUMMIT #1 23/273 RPL STRW | 70Y
LC | 121666580 | 014/004 | T3 EI MONTE RIO-FULTON 14/4 REFRAME | LAKEVLLE | ETL.7630.POLE.WOOD | 2021-07-06 | 2021-07-06 | 2022-08-10 | 2022-01-02 | 2022-01-06 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31546026 | T3 EI MONTE RIO-FULTON 14/4 REFRAME | 93E
LC | 121666615 | 001/018 | T2 EI COTTONWD-BNTN #2 1/018 RPL INSW | TABLEMTN | ETL.6650.INSL.NCER | 2021-07-06 | 2021-07-06 | 2022-09-10 | 2022-07-06 | 2022-07-06 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545816 | T2 EI COTTONWD-BNTN #2 1/018 RPL INSW | 93I
LC | 121666721 | 001/018 | T2 EI COTTONWD-BNTN #2 1/18 RPL XBRACE | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-06 | 2021-07-06 | 2022-07-22 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45213142 | T2 EI COTTONWD-BNTN #2 1/18 RPL XBRACE | ICW
LC | 121666904 | 078/398A | T2 DI MLN-RND MTN #2 78/398A RPR FOND | TABLEMTN | ETL.6020.TOWR | 2021-07-06 | 2021-07-06 | 2022-07-15 | 2022-07-06 | 2022-07-06 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45198250 | T2 DI MLN-RND MTN #2 78/398A RPR FOND | ICQ
LC | 121666905 | 003/013 | T3 DI DIABLO-MIDWAY #2 3/13 RPL HRDS | PISMOBCH | ETL.5970.TOWR | 2021-07-06 | 2021-07-06 | 2022-01-25 | 2022-01-02 | 2022-01-06 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Steel | Replace | 45068567 | T3 DI DIABLO-MIDWAY #2 3/13 RPL HRDS | ICS
LC | 121667376 | 005/071 | T2 DI GRN VLY-CAMP EVER 5/71 RPL STRW | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-07-06 | 2021-06-28 | 2022-04-08 | 2022-06-28 | 2022-06-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545456 | T2 DI GRN VLY-CAMP EVER 5/71 RPL STRW | 70Y
LC | 121667423 | 001/021 | T2 EI COTTONWOOD-BENTON 1/021L RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-06 | 2021-07-06 | 2022-06-02 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45213143 | T2 EI COTTONWOOD-BENTON 1/021L RPR STRW | ICW
LC | 121667480 | 001/021 | T2 EI COTTONWOOD-BENTON 1/021R RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-06 | 2021-07-06 | 2022-06-02 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 44897024 | EI COTTONWOOD-BENTON 1/021R RPR STRW | ICW
LC | 121667769 | 001/023 | T2 EI COTTONWD-BENTON #2 1/23L RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-06 | 2021-07-06 | 2022-06-03 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31511046 | DI CTTNWD BNTN #2 5/53 RPL POLE (ENG) | 70Y
LC | 121667802 | 004/060 | T2 DI GREEN VLLY-PAUL SWT 4/60L RPL STRW | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-07-06 | 2021-06-30 | 2022-10-28 | 2022-06-30 | 2022-06-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31545860 | T2 DI GREEN VLLY-PAUL SWT 4/60L RPL STRW | 70Y
LC | 121667821 | 001/023 | T2 EI COTTONWD-BENTON #2 1/23R RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-06 | 2021-07-06 | 2022-06-03 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31511046 | DI CTTNWD BNTN #2 5/53 RPL POLE (ENG) | 70Y
LC | 121668224 | 007/077 | T3 DI DRUM-RIO OSO #1 7/77 INS HRDT | SACTO | ETL.1420.TOWR | 2021-07-06 | 2021-07-06 | 2022-05-23 | 2022-01-02 | 2022-01-06 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45181131 | T3 DI DRUM-RIO OSO #1 7/77 INS HRDT | ICQ
LC | 121668762 | 007/098 | T2 DI VALLEY SPRINGS-CLAY 7/98R RPR GYWW | VICTOR | ETL.8264.POLE.WDPS | 2021-07-06 | 2021-07-01 | 2021-11-29 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44975288 | T2 DI VALLEY SPRINGS-CLAY 7/98R RPR GYWW | ICW
LC | 121668764 | 007/098 | T2 DI VALLEY SPRINGS-CLAY 7/98L RPR GYWW | VICTOR | ETL.8264.POLE.WDPS | 2021-07-06 | 2021-07-01 | 2021-11-29 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44975289 | T2 DI VALLEY SPRINGS-CLAY 7/98L RPR GYWW | ICW
LC | 121669069 | -016/000 | T3 DI FULTON CALISTOGA 016/000 RPR INSW | LAKEVLLE | ETL.6880.INSL.CERA | 2021-07-06 | 2021-07-05 | 2022-07-12 | 2022-01-01 | 2022-01-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45142899 | T3 DI FULTON CALISTOGA 016/000 RPR INSW | ICW
LC | 121669276 | -016/008 | T3 DI FULTON CALISTOGA -16/8 BOND HRDW | LAKEVLLE | ETL.6880.POLE.WOOD | 2021-07-06 | 2021-07-05 | 2022-12-05 | 2022-01-01 | 2022-01-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45143392 | T3 DI FULTON CALISTOGA 16/8 BOND HRDW | ICW
LC | 121669474 | 011/077 | DI T2 METCALF-GREEN VLLY 11/77R COMPLETE | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-07-06 | 2021-06-30 | 2022-08-21 | 2022-06-30 | 2022-06-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545867 | DI METCALF-GREEN VALLEY 11/77 RPL STRW | 70Y
LC | 121669475 | 015/201 | T2 WTSNVLE-SLNS 15/201L RPL STRW | MOSSLNDG | ETL.8310.POLE.WDPS | 2021-07-06 | 2021-07-06 | 2022-06-13 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31546240 | T2 WTSNVLE-SLNS 15/201R RPL STRW | 70Y
LC | 121669478 | 015/201 | T2 WTSNVLE-SLNS 15/201R RPL STRW | MOSSLNDG | ETL.8310.POLE.WDPS | 2021-07-06 | 2021-07-06 | 2022-06-13 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31546240 | T2 WTSNVLE-SLNS 15/201R RPL STRW | 70Y
LC | 121669497 | 009/086 | T2 EI COTTONWOOD-BNTN #2 9/86R RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-06 | 2021-07-06 | 2022-06-04 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45213144 | T2 EI COTTONWOOD-BENTON #2 9/86 RPR STRW | ICW
LC | 121669965 | 025/198 | T2 DI MDL FORK-GOLD HILL 25/198 RPL STRW | SACTO | ETL.5140.POLE.WDPS | 2021-07-06 | 2021-07-05 | 2022-10-29 | 2022-07-05 | 2022-07-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546023 | T2 DI MDD FRK-GLD HLL 026/201 RPL STRW | 70Y
LC | 121670015 | 029/003 | T2 MNDCN-WLTS-FRT BRG 29/3 RPL CRSW | WILLITS | ETL.7550.POLE.WOOD | 2021-07-06 | 2021-07-06 | 2022-08-17 | 2022-07-06 | 2022-07-06 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31546212 | T2 MNDCN-WLTS-FRT BRG 29/3 RPL CRSW | 93E
LC | 121670344 | 006/072 | EI T2 GRN VLY-CP EV 6/72L RPL STR COMPLT | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-07-06 | 2021-07-06 | 2022-04-04 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545457 | EI GRN VLLY-CMP EVRS 6/72 RPL STRW | 70Y
LC | 121670399 | 006/072 | EI T2 GRN VLY-CP EV 6/72R RPL STR COMPLT | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-07-06 | 2021-07-06 | 2022-04-04 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545457 | EI GRN VLLY-CMP EVRS 6/72 RPL STRW | 70Y
LC | 121671482 | 022/089 | T3 DI DIABLO-GATES #1 22/89 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2021-07-06 | 2021-07-06 | 2022-06-25 | 2022-01-02 | 2022-01-06 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068525 | T3 DI DIABLO-GATES #1 22/89 RPR GYWS | ICS
LC | 121673313 | 008/006 | T3 DI MONTE RIO-FULTON 8/6 RPL HRDD | LAKEVLLE | ETL.7630.POLE.WOOD | 2021-07-07 | 2021-07-05 | 2022-06-30 | 2022-01-01 | 2022-01-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45142163 | T3 DI MONTE RIO-FULTON 8/6 RPL HRDD | ICW
LC | 121673895 | 014/177 | T2 DI DELTA-MTN GATE JCT 14/177 RPR SPLW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-07 | 2021-07-06 | 2022-08-20 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45296784 | T2 DI DELTA-MTN GATE JCT 14/177 RPR SPLW | ICW
LC | 121674058 | 002/018 | T2 DI MTN GATE JCT-CASCDE 2/18R RPL STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-07 | 2021-07-06 | 2022-04-29 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547477 | T2 DI MTN GTE JCT CSCD 000/006 RPL STRW | 70Y
LC | 121674136 | 002/018 | T2 DI MTN GATE JCT-CASCDE 2/18L RPL STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-07 | 2021-07-06 | 2022-04-29 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547477 | T2 DI MTN GTE JCT CSCD 000/006 RPL STRW | 70Y
LC | 121674139 | 007/005 | T3 DI PTER VALY-WLITS 7/5 RPL INSW CMPLT | WILLITS | ETL.7820.INSL | 2021-07-07 | 2021-07-06 | 2022-06-19 | 2022-01-02 | 2022-01-06 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546216 | T3 DI POTTER VALLEY-WILLITS 7/5 RPL INSW | 93I
LC | 121674152 | T083 | T3 EI MIDWAY-SANTA MARIA T083 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-07 | 2021-07-07 | 2021-12-13 | 2022-01-03 | 2022-01-07 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121674214 | 025/198 | T2 DI MDL FRK-GLD HILL 25/198 RPLC STRW | SACTO | ETL.5140.POLE.WDPS | 2021-07-07 | 2021-07-05 | 2022-10-29 | 2022-07-05 | 2022-07-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546023 | T2 DI MDD FRK-GLD HLL 026/201 RPL STRW | 70Y
LC | 121674423 | 025/198 | T2 DI MDL FRK-GLD HILL 25/198 RPLC STRW | SACTO | ETL.5140.POLE.WDPS | 2021-07-07 | 2021-07-05 | 2022-10-29 | 2022-07-05 | 2022-07-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546023 | T2 DI MDD FRK-GLD HLL 026/201 RPL STRW | 70Y
LC | 121674646 | 010/102 | EI T2 PIT #5-RND MTN #1 10/102 RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-07 | 2021-06-14 | 2022-08-10 | 2022-06-14 | 2022-06-14 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121674972 | 004/050 | T2 DI SNEATH LN-PACFICA 4/50B-R RPR GYWW | METCALF | ETL.7575.POLE.WDPS | 2021-07-07 | 2021-07-03 | 2021-07-16 | 2022-07-03 | 2022-07-03 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 121675043 | 000/002 | T2 WV SOBRANTE-R #1 0/2 RPL INSS | CONCORD | ETL.3770.INSL | 2021-07-07 | 2021-07-07 | 2022-06-25 | 2022-07-07 | 2022-07-07 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535095 | T3 EI SOBRANTE-R #1 RPL INSLS 6TWR | 93K
LC | 121675207 | 007/080B | T2 DI GREEN VLY-PL SWT 7/80B RPLC INSW | MOSSLNDG | ETL.1730.INSL.NCER | 2021-07-07 | 2021-06-30 | 2022-08-26 | 2022-06-30 | 2022-06-30 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535459 | T2 EI GRN VLLY-PAUL SWT-WD 6/72 RPL INSW | 93I
LC | 121675548 | T080 | T3 EI MIDWAY-SANTA MARIA T080 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-07 | 2021-07-07 | 2022-01-25 | 2022-01-03 | 2022-01-07 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121676035 | 042/808 | T2 WV HAT CRK #1-WSTWD 42/808 RPL CRSW | TABLEMTN | ETL.7030.POLE.WOOD | 2021-07-07 | 2021-07-07 | 2022-05-06 | 2022-07-07 | 2022-07-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 31471609 | T2 EI HAT CRK #1-WESTWD 042/808 REFRAME | 93E
LC | 121676076 | T079 | T3 EI MIDWAY-SANTA MARIA T079 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-07 | 2021-07-07 | 2022-01-25 | 2022-01-03 | 2022-01-07 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121676150 | 010/100 | T2 DI PIT #5-RND MTN #1 10/100 RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-07 | 2021-07-06 | 2022-07-11 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213146 | T2 DI PIT #5-RND MTN #1 10/100 RPR STRW | ICW
LC | 121676155 | 014/183 | T2 DI DELTA-MTN GATE JCT 14/183 RPR SPLW | TABLEMTN | ETL.6750.INSL.CERA | 2021-07-07 | 2021-07-06 | 2022-08-24 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45296785 | T2 DI DELTA-MTN GATE JCT 14/183 RPR SPLW | ICW
LC | 121676159 | 014/183 | T2 DI DELTA-MTN GATE JCT 14/183 RPR STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-07 | 2021-07-06 | 2022-07-24 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45296786 | T2 DI DELTA-MTN GATE JCT 14/183 RPR STRW | ICW
LC | 121676217 | 010/100 | T2 DI PIT #5-RND MTN #1 10/100 RPR GYWW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-07 | 2021-07-06 | 2022-07-11 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213147 | T2 DI PIT #5-RND MTN #1 10/100 RPR GYWW | ICW
LC | 121676218 | 010/100 | T2 DI PIT #5-RND MTN #1 10/100R RPR GYWW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-07 | 2021-07-06 | 2022-07-11 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45240548 | T2 DI PIT #5-RND MTN #1 10/100 RPR GYWW | ICW
LC | 121676401 | T071 | T3 EI MIDWAY-SANTA MARIA T071 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-07 | 2021-07-07 | 2022-01-26 | 2022-01-03 | 2022-01-07 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121676757 | 020/083 | T3 DI DIABLO-GATES #1 020/083 RPL SHLS | PISMOBCH | ETL.5960.TOWR | 2021-07-07 | 2021-07-06 | 2021-10-18 | 2022-01-02 | 2022-01-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44963015 | T3 DI DIABLO-GATES #1 020/083 RPL SHLS | ICS
LC | 121676901 | 024/189 | T2 DI MDLE FRK GLD HLL 24/189 RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2021-07-07 | 2021-06-30 | 2022-10-24 | 2022-06-30 | 2022-06-30 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45017973 | T2 DI MDLE FRK GLD HLL 24/189 RPR GYWW | ICW
LC | 121677334 | T065 | T3 EI MIDWAY-SANTA MARIA T65 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-07 | 2021-07-07 | 2022-07-14 | 2022-01-03 | 2022-01-07 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098884 | T3 EI MIDWAY-SANTA MARIA T65 RPR FOND | ICQ
LC | 121677738 | 016/234 | T2 DI SSQUC-SNTA YNZ SW 16/234 RPL INSW | PISMOBCH | ETL.3700.INSL.NCER | 2021-07-07 | 2021-06-30 | 2022-04-13 | 2022-06-30 | 2022-06-30 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543110 | DI SISQUOC-SANTA YNEZ 2/45 RPL INSW | 93I
LC | 121677989 | 067/340 | T2 DI MALIN-ROUND MTN #2 67/340 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-07 | 2021-07-06 | 2022-07-14 | 2022-07-06 | 2022-07-06 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215177 | T2 DI MALIN-ROUND MTN #2 67/340 RPR OPGW | ICS
LC | 121678734 | 075/380A | T2 DI MALIN-ROUND MT #2 75/380 INST HRDT | TABLEMTN | ETL.6020.TOWR | 2021-07-07 | 2021-07-07 | 2022-08-17 | 2022-07-07 | 2022-07-07 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45526570 | T2 DI MALIN-ROUND MT #2 75/380 INST HRDT | ICQ
LC | 121679085 | T096 | T3 EI MIDWAY-SANTA MARIA T096 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-07 | 2021-07-07 | 2022-01-24 | 2022-01-03 | 2022-01-07 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121679120 | T093 | T3 EI MIDWAY-SANTA MARIA T093 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-07 | 2021-07-07 | 2022-01-24 | 2022-01-03 | 2022-01-07 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121679152 | 017/238 | T2 DI SSQC-SNT YNZ SWSTA 17/238 RPR STRW | PISMOBCH | ETL.3700.POLE.WDPS | 2021-07-07 | 2021-06-30 | 2022-04-13 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45069353 | T2 DI SSQC-SNT YNZ SWSTA 17/238 RPR STRW | ICW
LC | 121679154 | 017/238 | T2 DI SISQC-SNT YNZ SSTA 17/238 RPL INSW | PISMOBCH | ETL.3700.INSL.NCER | 2021-07-07 | 2021-06-30 | 2022-04-13 | 2022-06-30 | 2022-06-30 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543110 | DI SISQUOC-SANTA YNEZ 2/45 RPL INSW | 93I
LC | 121679200 | -016/003 | T3 DI FULTON-CLSTGA -016/3L RPR GYWW | LAKEVLLE | ETL.6880.POLE.WDPS | 2021-07-07 | 2021-07-05 | 2022-07-12 | 2022-01-01 | 2022-01-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148358 | T3 DI FULTON-CLSTGA -016/003 RPR GYWW | ICW
LC | 121679201 | -016/003 | T3 DI FULTON-CLSTGA -016/3C RPR GYWW | LAKEVLLE | ETL.6880.POLE.WDPS | 2021-07-07 | 2021-07-05 | 2022-07-12 | 2022-01-01 | 2022-01-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148358 | T3 DI FULTON-CLSTGA -016/003 RPR GYWW | ICW
LC | 121679203 | -016/003 | T3 DI FULTON-CLSTGA -016/3R RPR GYWW | LAKEVLLE | ETL.6880.POLE.WDPS | 2021-07-07 | 2021-07-05 | 2022-07-12 | 2022-01-01 | 2022-01-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148358 | T3 DI FULTON-CLSTGA -016/003 RPR GYWW | ICW
LC | 121679309 | 009/063 | T2 DI COTTONWD-DELEVAN #1 9/63 RPR INSS | TABLEMTN | ETL.4550.INSL | 2021-07-07 | 2021-06-29 | 2022-05-21 | 2022-06-29 | 2022-06-29 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45147355 | T2 DI COTTONWD-DELEVAN #1 9/63 RPR INSS | ICS
LC | 121679351 | 003/038 | T2 DI CTNWD-BENTN #2 3/38L RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-07 | 2021-07-01 | 2022-07-23 | 2022-07-01 | 2022-07-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213148 | T2 DI CTNWD-BENTN #2 3/38 RPR STRW | ICW
LC | 121679393 | 024/192 | T2 DI MDDL FK GLN HLL 024/192 RPL STRW | SACTO | ETL.5140.POLE.WDPS | 2021-07-07 | 2021-07-05 | 2022-10-24 | 2022-07-05 | 2022-07-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546023 | T2 DI MDD FRK-GLD HLL 026/201 RPL STRW | 70Y
LC | 121679498 | T047 | T3 EI MIDWAY-SANTA MARIA T47 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-07 | 2021-07-07 | 2022-08-01 | 2022-01-03 | 2022-01-07 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP PGEA COMP OH FMOB TR3 PRTO | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121679499 | T051 | T3 EI MIDWAY-SANTA MARIA RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-07 | 2021-07-07 | 2022-01-17 | 2022-01-03 | 2022-01-07 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP PGEA COMP OH FMOB TR3 PRTO | Overgrown | Vegetation | Remove
LC | 121679509 | T049 | T3 EI MIDWAY-SANTA MARIA T49 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-07 | 2021-07-07 | 2022-07-28 | 2022-01-03 | 2022-01-07 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP PGEA COMP OH FMOB TR3 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098886 | T3 EI MIDWAY-SANTA MARIA T49 RPR FOND | ICQ
LC | 121679570 | T049 | T3 EI MIDWAY-SANTA MARIA T49 BENT STEEL | PISMOBCH | ETL.9240.TOWR | 2021-07-07 | 2021-07-07 | 2022-07-28 | 2022-01-03 | 2022-01-07 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP PGEA COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45098888 | T3 EI MIDWAY-SANTA MARIA T49 BENT STEEL | ICQ
LC | 121679573 | T050 | T3 EI MIDWAY-SANTA MARIA T050 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-07 | 2021-07-07 | 2022-01-18 | 2022-01-03 | 2022-01-07 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP PGEA COMP OH FMOB TR3 PRTO | Overgrown | Vegetation | Remove
LC | 121679575 | T052 | T3 EI MIDWAY-SANTA MARIA T052 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-07 | 2021-07-07 | 2022-01-17 | 2022-01-03 | 2022-01-07 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP PGEA COMP OH FMOB TR3 PRTO | Overgrown | Vegetation | Remove
LC | 121680589 | 021/094 | T2 DI MSS LNDNG-LOS BNS 21/94 NEST | MOSSLNDG | ETL.6040.TOWR | 2021-07-08 | 2021-07-07 | 2021-07-17 | 2022-07-07 | 2022-07-07 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Steel | Remove | 44909662 | T2 DI MSS LNDNG-LOS BNS 21/94 NEST | ICS
LC | 121681029 | 013/002A | T2 OAKHURST TAP 13/2A INST POLE | FRESNO | ETL.1252.POLE.NWOD | 2021-07-08 | 2021-07-08 | 2022-04-04 | 2022-07-08 | 2022-07-08 | On-time | 401 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31545794 | T2 OAKHURST TAP 13/2A INST POLE | 93G
LC | 121681088 | 005/115 | T3 KILARC-CEDAR CREEK 5/115 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2021-07-08 | 2021-07-08 | 2022-04-23 | 2022-01-04 | 2022-01-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31539398 | T3 EI KILARC-CDR CRK 4/114 RPL STRW | 70Y
LC | 121681650 | 010/099 | T2 DI PIT #5-ROUND MTN #1 10/99 RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-08 | 2021-07-06 | 2021-07-27 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 44929692 | T2 DI PIT #5-ROUND MTN #1 10/99 RPR STRW | ICW
LC | 121681991 | 007/035 | T2 DI BRENTWOOD-KELSO 7/35 RPL INSS | CONCORD | ETL.4410.INSL | 2021-07-08 | 2021-06-28 | 2021-11-12 | 2022-06-28 | 2022-06-28 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546144 | T2 DI BRENTWOOD-KELSO 7/35 RPL INSS | 93K
LC | 121681992 | 007/035 | T2 DI BRENTWOOD-KELSO 7/35 RPL HRDT | CONCORD | ETL.4410.INSL | 2021-07-08 | 2021-06-28 | 2021-11-11 | 2022-06-28 | 2022-06-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Steel | Replace | 44958974 | T2 DI BRENTWOOD-KELSO 7/35 RPL HRDT | ICS
LC | 121682757 | T059 | T3 EI MIDWAY-SANTA MARIA T59 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-01-20 | 2022-01-04 | 2022-01-08 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121682936 | T060 | T3 EI MIDWAY-SANTA MARIA T60 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-05-05 | 2022-01-04 | 2022-01-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098889 | T3 EI MIDWAY-SANTA MARIA T60 RPR FOND | ICQ
LC | 121683227 | 003/005 | T2 DI CHOWCHILLA-KERCKHOFF 3/5 RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-07-08 | 2021-07-07 | 2022-02-14 | 2022-07-07 | 2022-07-07 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31546284 | T2 DI CHOWCHILLA-KERCKHOFF 3/5 RPL STRW | 70Y
LC | 121683939 | T055 | T3 EI MIDWAY-SANTA MARIA T055 RPR STRT | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-08-23 | 2022-01-04 | 2022-07-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3N PRTO FRAB | Anti-Climbing Guard | Structure-Tower | Repair | 44923738 | T3 EI MIDWAY-SANTA MARIA T055 RPR STRT | ICQ
LC | 121683960 | 054/266 | T2 WV CORTNA-MENDCNO #1 54/266 RPR FOND | WILLITS | ETL.1330.TOWR | 2021-07-08 | 2021-07-08 | 2022-01-28 | 2022-07-08 | 2022-07-08 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45014638 | T2 WV CORTNA-MENDCNO #1 54/266 RPR FOND | ICQ
LC | 121683969 | T054 | T3 EI MIDWAY-SANTA MARIA_T054 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-08-23 | 2022-01-04 | 2022-01-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098890 | T3 EI MIDWAY-SANTA MARIA_T054 RPR FOND | ICQ
LC | 121683974 | T-100 | T3 EI MIDWAY-SANTA MARIA T-100 RPR STRT | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-05-03 | 2022-01-04 | 2022-01-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair | 45098891 | T3 EI MIDWAY-SANTA MARIA T-100 RPR STRT | ICQ
LC | 121683975 | T099 | T3 EI MIDWAY-SANTA MARIA T099 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-02-28 | 2022-01-04 | 2022-01-08 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121683976 | T-106 | T3 EI MIDWAY-SANTA MARIA T-106 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-05-02 | 2022-01-04 | 2022-01-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098892 | T3 EI MIDWAY-SANTA MARIA T-106 RPR FOND | ICQ
LC | 121683978 | T-102 | T3 EI MIDWAY-SANTA MARIA T-102 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-08-24 | 2022-01-04 | 2022-01-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098893 | T3 EI MIDWAY-SANTA MARIA T-102 RPR FOND | ICQ
LC | 121683981 | T055 | T3 EI MIDWAY-SANTA MARIA T055 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-08-23 | 2022-01-04 | 2022-01-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP PGEA COMP OH FMOB TR3 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098894 | T3 EI MIDWAY-SANTA MARIA T055 RPR FOND | ICQ
LC | 121683987 | T056 | T3 EI MIDWAY-SANTA MARIA_T056 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-05-06 | 2022-01-04 | 2022-01-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098895 | T3 EI MIDWAY-SANTA MARIA_T056 RPR FOND | ICQ
LC | 121683996 | T-101 | T3 EI MIDWAY-SANTA MARIA T-101 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-05-02 | 2022-01-04 | 2022-01-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098899 | T3 EI MIDWAY-SANTA MARIA T-101 RPR FOND | ICQ
LC | 121683999 | T-108 | T3 EI MIDWAY-SANTA MARIA T-108 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-05-09 | 2022-01-04 | 2022-01-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098900 | T3 EI MIDWAY-SANTA MARIA T-108 RPR FOND | ICQ
LC | 121684005 | T-108 | T3 EI MIDWAY-SANTA MARIA T-108 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-08-30 | 2022-01-04 | 2022-01-08 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548619 | T3 EI MIDWAY-SANTA MARIA RPL INSS 8TWRS | 93K
LC | 121684006 | T-107 | T3 EI MIDWAY-SANTA MARIA T-107 RPR STRT | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-05-02 | 2022-01-04 | 2022-01-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair | 45098902 | T3 EI MIDWAY-SANTA MARIA T-107 RPR STRT | ICQ
LC | 121684012 | T-107 | T3 EI MIDWAY-SANTA MARIA T-107 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-08-30 | 2022-01-04 | 2022-01-08 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31596011 | T3 DI MIDWAY-SANTA MARIA RPL INSS | 93K
LC | 121684015 | T-100 | T3 EI MIDWAY-SANTA MARIA T-100 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-05-03 | 2022-01-04 | 2022-01-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098903 | T3 EI MIDWAY-SANTA MARIA T-100 RPR FOND | ICQ
LC | 121684017 | T-107 | T3 EI MIDWAY-SANTA MARIA T-107 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 | 2022-05-02 | 2022-01-04 | 2022-01-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098904 | T3 EI MIDWAY-SANTA MARIA T-107 RPR FOND | ICQ
LC | 121684355 | 032/263 | T2 WV BRIDGEVLLE-COTTNWD 32/263 RPR FOND | TABLEMTN | ETL.1110.TOWR | 2021-07-08 | 2021-07-08 | 2022-07-29 | 2022-07-08 | 2022-07-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45149333 | T2 WV BRIDGEVLLE-COTTNWD 32/263 RPR FOND | ICQ
LC | 121684561 | 058/425B | T2 WV BRIDGEVLE-COTTNWD 58/425B RPR FOND | TABLEMTN | ETL.1110.POLE.NWOD | 2021-07-08 | 2021-07-08 | 2022-07-28 | 2022-07-08 | 2022-07-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160909 | T2 WV BRIDGEVLE-COTTNWD 58/425B RPR FOND | ICQ
LC | 121684568 | 058/425C | T2 WV BRIDGEVLE-COTTNWD 58/425C RPR FOND | TABLEMTN | ETL.1110.POLE.NWOD | 2021-07-08 | 2021-07-08 | 2022-07-28 | 2022-07-08 | 2022-07-08 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160912 | T2 WV BRIDGEVLE-COTTNWD 58/425C RPR FOND | ICQ
LC | 121684961 | 010/159 | T2 DI SISQUOC-SNTA YNEZ 10/159R RPL HRDD | PISMOBCH | ETL.3700.POLE.WDPS | 2021-07-08 | 2021-06-30 | 2022-04-12 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45069354 | T2 DI SISQUOC-SNTA YNEZ 10/159R RPL HRDD | ICW
LC | 121684962 | 010/159 | T2 DI SQC-SNT YNZ 10/159L RPR GYWW CMPLT | PISMOBCH | ETL.3700.POLE.WDPS | 2021-07-08 | 2021-06-30 | 2022-04-12 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069355 | T2 DI SISQUOC-SNTA YNEZ 10/159L RPR GYWW | ICW
LC | 121684965 | 010/159 | T2 DI SISQUOC-SANTA YNEZ 10/159 RPL INSW | PISMOBCH | ETL.3700.INSL.CERA | 2021-07-08 | 2021-06-30 | 2022-04-12 | 2022-06-30 | 2022-06-30 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579988 | T2 DI SISQUOC-SANTA YNEZ 10/159 RPL INSW | 93I
LC | 121685152 | 006/052 | T3 DI GRN VLLY-LLGS-WD 6/52L RPL STRW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-07-08 | 2021-07-05 | 2022-09-22 | 2022-01-01 | 2022-01-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579736 | T3 DI GRN VLLY-LLGS-WD 6/52L RPL STRW | 70Y
LC | 121685153 | 006/052 | T3 DI GREEN VLLY-LLGS-WD 6/52R RPL STRW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-07-08 | 2021-07-05 | 2022-09-22 | 2022-01-01 | 2022-01-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579736 | T3 DI GRN VLLY-LLGS-WD 6/52L RPL STRW | 70Y
LC | 121685245 | 003/039 | T2 DI CTTNWD-BENTON #2 3/39L RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-08 | 2021-07-01 | 2022-07-23 | 2022-07-01 | 2022-07-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213149 | T2 DI CTTNWD-BENTON #2 3/39L RPR STRW | ICW
LC | 121685246 | 003/039 | T2 DI CTTNWD-BENTON #2 3/39R RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-08 | 2021-07-01 | 2022-07-23 | 2022-07-01 | 2022-07-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213222 | T2 DI CTTNWD-BENTON #2 3/39R RPR STRW | ICW
LC | 121685488 | 000/001 | T3 DI DRM-GRS VALY-WEMR 00/01 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-07-08 | 2021-07-06 | 2022-04-23 | 2022-01-02 | 2022-01-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44949948 | T3 DI DRM-GRS VALY-WEMR 00/01 RPR GYWW | ICW
LC | 121685573 | 028/001 | T2 DI GARBRVIL-LYTNVIL 28/01 RPR GYWW | WILLITS | ETL.8365.POLE.WOOD | 2021-07-08 | 2021-07-05 | 2022-04-21 | 2022-07-05 | 2022-07-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45155527 | T2 DI GARBRVIL-LYTNVIL 28/01 RPR GYWW | ICW
LC | 121685634 | 029/015 | T2 DI FULTON-HOPLAND 029/015 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-07-08 | 2021-07-05 | 2022-06-24 | 2022-07-05 | 2022-07-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143960 | T2 DI FULTON-HOPLAND 029/015 RPR STRW | ICW
LC | 121685647 | 025/194 | T2 DI MID FRK-GLD HILL 25/194 RPR INSW | SACTO | ETL.5140.INSL.CERA | 2021-07-08 | 2021-07-05 | 2022-10-24 | 2022-07-05 | 2022-07-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair | 45017971 | T2 DI MID FRK-GLD HILL 25/194 RPR INSW | ICW
LC | 121685680 | 025/194 | T2 DI MID FRK-GLD HLL 25/194 RPR CRSW | SACTO | ETL.5140.POLE.WDPS | 2021-07-08 | 2021-07-05 | 2022-10-24 | 2022-07-05 | 2022-07-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45017970 | T2 DI MID FRK-GLD HLL 25/194 RPR CRSW | ICW
LC | 121685815 | 008/142 | T2 DI TEJON-LEBEC 08/142 RPL HRDW | MIDWAY | ETL.9250.POLE.WOOD | 2021-07-08 | 2021-07-05 | 2021-08-12 | 2022-07-05 | 2022-07-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44930760 | T2 DI TEJON-LEBEC 08/142 RPL HRDW | ICW
LC | 121685817 | 008/142 | T2 DI TEJON-LEBEC 08/142 RPL DAMW | MIDWAY | ETL.9250.INSL | 2021-07-08 | 2021-07-05 | 2021-08-31 | 2022-07-05 | 2022-07-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace | 44930761 | T2 DI TEJON-LEBEC 08/142 RPL DAMW | ICW
LC | 121685843 | 007/086A | T2 DI DRUM-SUMMIT #207/86A SPLIT BOLT | SACTO | ETL.1450.POLE.WOOD | 2021-07-08 | 2021-07-01 | 2022-06-04 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Wood | Install | 45200553 | T2 DI DRUM-SUMMIT #207/86A SPLIT BOLT | ICW
LC | 121687429 | 005/003 | T2 DI MLNS-RCTRCK-WD 5/3 RPR STRW CMPLTD | VICTOR | ETL.2400.POLE.WOOD | 2021-07-09 | 2021-07-05 | 2022-04-26 | 2022-07-05 | 2022-07-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45122704 | T2 DI MELONES-RACETRACK-WD 5/3 RPR STRW | ICW
LC | 121687471 | 005/003 | T2 DI MELONES-RACETRACK 5/3 COMPLETE | VICTOR | ETL.2400.INSL.NCER | 2021-07-09 | 2021-07-05 | 2022-04-26 | 2022-07-05 | 2022-07-05 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579815 | T2 DI MELONES-RACETRACK 5/3 RPL INSW | 93I
LC | 121687473 | 019/000 | T2 DI FULTON-HOPLAND 19/0 RMV DEBRIS | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-07-09 | 2021-07-05 | 2022-06-20 | 2022-07-05 | 2022-07-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45143936 | T2 DI FULTON-HOPLAND 19/0 RMV DEBRIS | ICW
LC | 121687477 | 085/601 | T3 DI BRDGVLLE CTTNWD 085/601 RPR ADSS | EUREKA | ETL.1110.POLE.STPS | 2021-07-09 | 2021-07-06 | 2022-05-02 | 2022-01-02 | 2022-01-06 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45010738 | T3 DI BRDGVLLE CTTNWD 085/601 RPR ADSS | ICS
LC | 121687730 | 014/179 | T2 DI DLTA-MTN GTE JCT 14/179 RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-09 | 2021-07-06 | 2022-08-19 | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546294 | T2 DI DLTA-MTN GTE JCT 14/179 RPL STRW | 70Y
LC | 121687784 | 000/002 | T2 DI SMRTSVLLE NCLS #1 000/002 RPL STRW | SACTO | ETL.7990.POLE.WOOD | 2021-07-09 | 2021-07-05 | 2022-08-23 | 2022-07-05 | 2022-07-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31548078 | T2 DI SMRTSVLLE NCLS #1 000/002 RPL STRW | 70Y
LC | 121687852 | 004/039 | T2 DI MTN GATE JCT CSCD 04/039R RPR STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-09 | 2021-07-06 | 2022-07-24 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45419438 | T2 DI MTN GATE JCT CSCD 04/039R RPR STRW | ICW
LC | 121687881 | 005/040 | T2 DI TRNTY-CTNWD 5/40 RPL POLE | TABLEMTN | ETL.4040.POLE.WDPS | 2021-07-09 | 2021-07-08 | 2022-08-21 | 2022-07-08 | 2022-07-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31549880 | T2 DI TRNTY-CTNWD 5/40 RPL POLE | 70Y
LC | 121687882 | 005/040 | T2 DI TRNTY-CTNWD 5/40 RPL POLE | TABLEMTN | ETL.4040.POLE.WDPS | 2021-07-09 | 2021-07-08 | 2022-08-21 | 2022-07-08 | 2022-07-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31549880 | T2 DI TRNTY-CTNWD 5/40 RPL POLE | 70Y
LC | 121687883 | 005/040 | T2 DI TRNTY-CTNWD 5/40 RPL POLE | TABLEMTN | ETL.4040.POLE.WDPS | 2021-07-09 | 2021-07-08 | 2022-08-21 | 2022-07-08 | 2022-07-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31549880 | T2 DI TRNTY-CTNWD 5/40 RPL POLE | 70Y
LC | 121687925 | 010/159 | EI T2 SSQC-SNT YNZ SW ST 10/159 RPR GYWW | PISMOBCH | ETL.3700.POLE.WDPS | 2021-07-09 | 2021-07-09 | 2022-04-12 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069356 | EI T2 SSQC-SNT YNZ SW ST 10/159 RPR GYWW | ICW
LC | 121687927 | 010/159 | EI T2 SC-ST YZ SW ST 10/159 RPR GYWW CMP | PISMOBCH | ETL.3700.POLE.WDPS | 2021-07-09 | 2021-07-09 | 2022-04-11 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45069357 | EI T2 SSQC-SNT YNZ SW ST 10/159 RPR GYWW | ICW
LC | 121687929 | 010/159 | EI T2 SSQC-SNT YNZ SW ST 10/159 RPL HRDD | PISMOBCH | ETL.3700.POLE.WDPS | 2021-07-09 | 2021-07-09 | 2022-04-12 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45069358 | EI T2 SSQC-SNT YNZ SW ST 10/159 RPL HRDD | ICW
LC | 121688009 | 054/001A | T2 DI HUMBOLDT-TRINITY- 54/1A RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2021-07-09 | 2021-07-01 | 2022-06-08 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145285 | T2 DI HUMBOLDT-TRINITY- 54/1A RPR GYWW | ICW
LC | 121688149 | 011/110 | T2 DI PIT #5-RD MTN #1 11/110 INS HRDW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-09 | 2021-07-06 | 2022-07-15 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR NTDE | Missing | Hardware-Wood | Install | 45213223 | T2 DI PIT #5-RD MTN #1 11/110 INS HRDW | ICW
LC | 121688280 | 009/095 | T2 DI PIT #5-ROUND MTN #2 9/95L RPL POLE | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-09 | 2021-07-06 | 2022-06-13 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31601295 | EI T2 PIT #5-ROUND MTN #2 7/72 RPL STRW | 70Y
LC | 121688679 | 007/134 | T2 DI TEJON-LEBEC 007/134 RPL HRDW | MIDWAY | ETL.9250.POLE.WOOD | 2021-07-09 | 2021-07-05 | 2021-08-05 | 2022-07-05 | 2022-07-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44930762 | T2 DI TEJON-LEBEC 007/134 RPL HRDW | ICW
LC | 121688721 | 012/166 | T2 DI DLTA MTN GTE JCT 012/166 RPL HRDW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-09 | 2021-07-06 | 2022-08-20 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45296787 | T2 DI DLTA MTN GTE JCT 012/166 RPL HRDW | ICW
LC | 121688723 | 012/061 | T2 DI CNTRA CSTA DLTA 012/061 RPL INSS | CONCORD | ETL.4490.INSL | 2021-07-09 | 2021-07-06 | 2022-02-14 | 2022-07-06 | 2022-07-06 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31552145 | DI CNTRA CSTA DLTA RPL INSS. 5TWRS | 93K
LC | 121688726 | 006/085 | T2 DI DVDE-CBRLLO #1 006/085 RMV DEBRIS | PISMOBCH | ETL.1380.POLE.WDPS | 2021-07-09 | 2021-07-01 | 2022-08-03 | 2022-07-01 | 2022-07-01 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45098630 | T2 DI DVDE-CBRLLO #1 006/085 RMV DEBRIS | ICW
LC | 121688753 | T077 | T3 EI WAY-SANTA MARIA T077 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-09 | 2021-07-09 | 2022-03-01 | 2022-01-05 | 2022-01-09 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121689013 | 011/107 | T2DI UKIHHPLND-CLVRLHPLN 11/107 RPL GYWW | LAKEVLLE | ETL.4050.POLE.STPS | 2021-07-09 | 2021-07-06 | 2022-01-27 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45136920 | T2DI UKIHHPLND-CLVRLHPLN 11/107 RPL GYWW | ICW
LC | 121689030 | 004/008A | T2 DI LYTNVILE-COVELO 4/8C RPR GYWW | LAKEVLLE | ETL.7390.POLE.NWOD | 2021-07-09 | 2021-06-27 | 2021-10-19 | 2022-06-27 | 2022-06-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44999939 | T2 DI LYTNVILE-COVELO 4/8C RPR GYWW | ICW
LC | 121689196 | 009/132 | T2 DI DELTA MTN GTE JCT 9/132 RMV DEBRIS | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-09 | 2021-07-06 | 2022-06-27 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45296788 | T2 DI DELTA MTN GTE JCT 9/132 RMV DEBRIS | ICW
LC | 121689198 | 005/009 | T3 DI POTTER VALLEY-WILLITS 5/9 RPR INSS | WILLITS | ETL.7820.INSL | 2021-07-09 | 2021-07-06 | 2022-08-10 | 2022-01-02 | 2022-01-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45136985 | T3 DI POTTER VALLEY-WILLITS 5/9 RPR INSS | ICW
LC | 121689448 | 008/115 | T2 DI DELTA MTN GTE JCT 8/115L RPR GYWW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-09 | 2021-07-06 | 2022-08-23 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296790 | T2 DI DELTA MTN GTE JCT 008/115 RPR GYWW | ICW
LC | 121689783 | 015/187 | T2 DI DELTA-MTN GT -MNT 15/187 RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-09 | 2021-07-06 | 2022-08-09 | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546296 | 30 DI DELTA-MTN GT -MNT 15/187C RPL STRW | 70Y
LC | 121689786 | 003/027 | T2 DI PIT #7 TAP 3/27 COMPLETE | TABLEMTN | ETL.5442.POLE.STPS | 2021-07-09 | 2021-07-01 | 2022-06-14 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45213836 | T2 DI PIT #7 TAP 3/27 RMV DEBRIS | ICW
LC | 121689872 | 003/031 | T2 DI MTN GATE JCT-CASCAD 3/31R RPL STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-09 | 2021-07-06 | 2022-04-28 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547477 | T2 DI MTN GTE JCT CSCD 000/006 RPL STRW | 70Y
LC | 121690054 | 009/071 | T2 DI GREEN VALLEY-LLAGAS- 9/71 RPL STRW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-07-09 | 2021-07-05 | 2022-08-04 | 2022-07-05 | 2022-07-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31579736 | T3 DI GRN VLLY-LLGS-WD 6/52L RPL STRW | 70Y
LC | 121690626 | 006/014 | WV T2 TULUCAY-NAPA #1 6/14 COMPLETE | LAKEVLLE | ETL.8180.POLE.NWOD | 2021-07-09 | 2021-07-09 | 2022-04-30 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45144267 | WV T2 TULUCAY-NAPA #1 6/14 RMV DEBRIS | ICW
LC | 121690651 | 006/014 | WV T2 TULUCAY-NAPA #1 6/014 COMPLETE | LAKEVLLE | ETL.8180.POLE.NWOD | 2021-07-09 | 2021-07-09 | 2022-04-30 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Wood | Install | 45122904 | WV T2 TULUCAY-NAPA #1 6/014 INS DAMW | ICW
LC | 121690704 | 000/006 | T2 DI MTN GTE JCT CSCD 000/006 RPL STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-09 | 2021-07-06 | 2022-06-07 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547477 | T2 DI MTN GTE JCT CSCD 000/006 RPL STRW | 70Y
LC | 121690785 | 010/143 | T2 DI DEL-MTN GT JCT 10/143L INST HRDW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-09 | 2021-07-09 | 2022-08-20 | 2022-07-09 | 2022-07-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Missing | Hardware-Wood | Install | 45296791 | T2 DI DEL-MTN GT JCT 10/143L INST HRDW | ICW
LC | 121690802 | 026/003 | T2 DI MNDCN-WT-FT BRGG 26/3 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2021-07-09 | 2021-07-01 | 2022-10-01 | 2022-07-01 | 2022-07-01 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547425 | T2 DI MNDCN-WT-FT BRGG 26/3 RPL INSW | 93I
LC | 121690943 | 008/117 | T2 DI DELTA-MTN GATE JCT 8/117 RPR STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-09 | 2021-07-06 | 2022-08-22 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45296792 | T2 DI DELTA-MTN GATE JCT 8/117 RPR STRW | ICW
LC | 121690950 | 002/025 | T2 DI MTN GTE JCT-CSCDE 2/25L RPR POLE | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-09 | 2021-07-06 | 2022-04-28 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45294985 | T2 DI MTN GTE JCT-CSCDE 2/25L RPR POLE | ICW
LC | 121691121 | 003/072 | T2 DI COLEMAN-COTTONWOOD 03/72 RMV DEBRI | TABLEMTN | ETL.6430.POLE.WOOD | 2021-07-09 | 2021-07-05 | 2022-05-14 | 2022-07-05 | 2022-07-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45212744 | T2 DI COLEMAN-COTTONWOOD 03/72 RMV DEBRI | ICW
LC | 121691224 | 014/184 | T2 DI DELTA-MTN GT JCT 014/184 RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-09 | 2021-07-06 | 2022-08-20 | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546295 | T2 DI DELTA-MTN GT JCT 014/184 RPL STRW | 70Y
LC | 121691330 | 007/086 | WV T2 DIVIDE-CABRILLO #2 7/086 INS DAMW | PISMOBCH | ETL.1370.POLE.WOOD | 2021-07-09 | 2021-07-09 | 2022-06-24 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB SR22 | Missing | Damper-Wood | Install | 45068670 | WV T2 DIVIDE-CABRILLO #2 7/086 INS DAMW | ICW
LC | 121691842 | 003/041 | T3 DI IGNCO-BOLINAS#2 3/41 RPR CNDW | LAKEVLLE | ETL.7180.INSL.NCER | 2021-07-09 | 2021-07-05 | 2022-10-05 | 2022-01-01 | 2022-01-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45143061 | T3 DI IGNCO-BOLINAS#2 3/41 RPR CNDW | ICW
LC | 121692329 | 006/057 | T2 DI COTTNWD-BENTN #2 6/57L RMV BUTT | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-09 | 2021-07-07 | 2022-06-29 | 2022-07-07 | 2022-07-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45213225 | T2 DI COTTNWD-BENTN #2 6/57L RMV PL BUTT | ICW
LC | 121692614 | 007/113 | T2 DI DELTA-MTN GT JCT 007/113R RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-09 | 2021-07-06 | 2022-08-18 | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546293 | T2 DI DELTA-MTN GT JCT 007/113 RPL STRW | 70Y
LC | 121693941 | 013/012 | T3 DI LAURELES-OTTER 13/012 RPR STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2021-07-09 | 2021-07-07 | 2021-08-17 | 2022-01-03 | 2022-01-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44923641 | T3 DI LAURELES-OTTER 13/012 RPR STRW | ICW
LC | 121694095 | 010/101 | T2 DI PIT #5-RND MTN #1 10/101 RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-09 | 2021-07-06 | 2022-07-11 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213226 | T2 DI PIT #5-RND MTN #1 10/101 RPR STRW | ICW
LC | 121694167 | 004/054C | T3 DI DRUM-SUMMIT #2 004/054C RPR STRW | SACTO | ETL.1450.POLE.WOOD | 2021-07-09 | 2021-07-07 | 2022-05-04 | 2022-01-03 | 2022-01-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45200570 | T3 DI DRUM-SUMMIT #2 004/054C RPR STRW | ICW
LC | 121694169 | 004/054C | T3 DI DRUM-SUMMIT #2 004/054C RPL INSW | SACTO | ETL.1450.INSL.NCER | 2021-07-09 | 2021-07-07 | 2022-06-05 | 2022-01-03 | 2022-01-07 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546395 | T3 DI DRUM-SUMMIT #2 004/054B RPL INSW | 93I
LC | 121694828 | 009/071 | T2 DI GREEN VALLEY-LLAGAS 9/71R RPL STRW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-07-10 | 2021-07-05 | 2022-08-04 | 2022-07-05 | 2022-07-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31579736 | T3 DI GRN VLLY-LLGS-WD 6/52L RPL STRW | 70Y
LC | 121704915 | 006/110 | T2 DI COLGATE-PALERMO 6/110 RPR JUMPW | SACTO | ETL.6500.POLE.NWOD | 2021-07-10 | 2021-07-09 | 2022-05-14 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Jumper-Wood | Repair | 45200573 | T2 DI COLGATE-PALERMO 6/110 RPR JUMPW | ICW
LC | 121704917 | 020/139C | T2 DI CARIBOU-TABL MTN 20/139C RPR STRW | TABLEMTN | ETL.4440.POLE.NWOD | 2021-07-10 | 2021-07-09 | 2022-07-19 | 2022-07-09 | 2022-07-09 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45159367 | T2 DI CARIBOU-TABL MTN 20/139C RPR STRW | ICQ
LC | 121705123 | 001/013 | T2 DI BC CRK-RCK CK-CRST 1/13 RPR SPLS | TABLEMTN | ETL.4430.TOWR | 2021-07-10 | 2021-07-09 | 2022-06-28 | 2022-07-09 | 2022-07-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45212514 | T2 DI BC CRK-RCK CK-CRST 1/13 RPR SPLS | ICS
LC | 121705124 | 001/013 | T2 DI BC CRK-RCK CK-CRST 1/13 RPL INSS | TABLEMTN | ETL.4430.INSL.NCER | 2021-07-10 | 2021-07-09 | 2022-06-28 | 2022-07-09 | 2022-07-09 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546438 | T2 DI BCKS CRK RK CRK RPL INSS 2 TWRS | 93K
LC | 121705167 | 000/011 | T3 DI DRM-GRSS VLLY-WMR 000/011 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-07-10 | 2021-07-06 | 2022-04-23 | 2022-01-02 | 2022-01-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31580703 | T3 DI DRM-GRSS VLLY-WMR 000/011 RPL STRW | 70Y
LC | 121705242 | 003/053 | T2 DI GRN VLLY-CMP EVRS 3/53L RPR STRW | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-07-10 | 2021-07-01 | 2022-03-02 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45166762 | T2 DI GRN VLLY-CMP EVRS 3/53L RPR STRW | ICW
LC | 121705243 | 003/053 | T2 DI GRN VLLY-CMP EVRS 3/53R RPR STRW | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-07-10 | 2021-07-01 | 2022-03-02 | 2022-07-01 | 2022-07-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45166755 | T2 DI GRN VLLY-CMP EVRS 3/53R RPR STRW | ICW
LC | 121705325 | 004/003A | T2 DI LYTNVLL COVELO 004/003A RPR HRDW | LAKEVLLE | ETL.7390.INSL.NCER | 2021-07-10 | 2021-07-07 | 2021-10-19 | 2022-07-07 | 2022-07-07 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44999937 | T2 DI LYTNVLL COVELO 004/003A RPR HRDW | ICS
LC | 121705541 | 026/004 | T2 DI MNDCN WLTS FT BRG 026/004 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-07-10 | 2021-07-01 | 2022-08-15 | 2022-07-01 | 2022-07-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE SPCR COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31546021 | T2 DI MENDO-WILL-FT BRAGG 28/9 RPL POLE | 70Y
LC | 121705543 | 004/054B | T3 DI DRUM-SUMMIT #2 004/054B RPL INSW | SACTO | ETL.1450.INSL.NCER | 2021-07-10 | 2021-07-07 | 2022-06-05 | 2022-01-03 | 2022-01-07 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546395 | T3 DI DRUM-SUMMIT #2 004/054B RPL INSW | 93I
LC | 121705754 | 007/086C | T2 DI DRUM-SUMMIT #2 007/086C RPR STRW | SACTO | ETL.1450.POLE.WOOD | 2021-07-10 | 2021-06-27 | 2022-06-04 | 2022-06-27 | 2022-06-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45200575 | T2 DI DRUM-SUMMIT #2 007/086C RPR STRW | ICW
LC | 121705851 | 023/181 | T2 DI PRDSE TBL MTN 023/181R RPR GYWW | TABLEMTN | ETL.4316.POLE.STPS | 2021-07-10 | 2021-07-06 | 2022-05-16 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45197346 | T2 DI PRDSE TBL MTN 023/181R RPR GYWW | ICW
LC | 121705852 | 023/181 | T2 DI PRDSE TBL MTN 023/181C RPR GYWW | TABLEMTN | ETL.4316.POLE.STPS | 2021-07-10 | 2021-07-06 | 2022-05-16 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45197356 | T2 DI PRDSE TBL MTN 023/181C RPR GYWW | ICW
LC | 121705853 | 023/181 | T2 DI PRDSE TBL MTN 023/181L RPR GYWW | TABLEMTN | ETL.4316.POLE.STPS | 2021-07-10 | 2021-07-06 | 2022-05-16 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45197354 | T2 DI PRDSE TBL MTN 023/181L RPR GYWW | ICW
LC | 121705909 | 007/113 | T2 DI DELTA-MTN GT JCT 007/113L RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-08-18 | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546293 | T2 DI DELTA-MTN GT JCT 007/113 RPL STRW | 70Y
LC | 121705989 | 048/236 | T2 DI MALIN-RND MTN#2 48/236 RPL HRDT | TABLEMTN | ETL.6020.TOWR | 2021-07-10 | 2021-07-09 | 2022-08-04 | 2022-07-09 | 2022-07-09 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45193981 | T2 DI MALIN-RND MTN#2 48/236 RPL HRDT | ICQ
LC | 121706110 | 014/179 | T2 DI DLTA-MTN GTE JCT 14/179R RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-08-19 | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546294 | T2 DI DLTA-MTN GTE JCT 14/179 RPL STRW | 70Y
LC | 121706111 | 014/184 | T2 DI DELTA-MTN GT JCT 014/184R RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-08-20 | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546295 | T2 DI DELTA-MTN GT JCT 014/184 RPL STRW | 70Y
LC | 121706116 | 003/078 | T2 DLT-MTN GT JT-MTN GT J 3/78 RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-10 | 2021-07-10 | 2022-08-23 | 2022-07-10 | 2022-07-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31546387 | T2 DI DELTA-MTN GATE JCT 3/71L RPL STRW | 70Y
LC | 121706117 | 003/078 | T2 DLT-MTN GT JT-MTN GT J 3/78 RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-10 | 2021-07-10 | 2022-08-23 | 2022-07-10 | 2022-07-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546387 | T2 DI DELTA-MTN GATE JCT 3/71L RPL STRW | 70Y
LC | 121706118 | 003/078 | T2 DLT-MTN GT JT-MTN GT J 3/78 RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-10 | 2021-07-10 | 2022-08-23 | 2022-07-10 | 2022-07-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546387 | T2 DI DELTA-MTN GATE JCT 3/71L RPL STRW | 70Y
LC | 121706230 | 015/187 | T2 DI DELTA-MTN GT -MNT 15/187R RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-08-09 | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546296 | 30 DI DELTA-MTN GT -MNT 15/187C RPL STRW | 70Y
LC | 121706231 | 015/187 | T2 DI DELTA-MTN GT -MNT 15/187C RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-08-09 | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546296 | 30 DI DELTA-MTN GT -MNT 15/187C RPL STRW | 70Y
LC | 121706524 | 020/542 | T3 DI COLGATE-ALLEGHANY 020/542 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2021-07-10 | 2021-07-07 | 2022-06-14 | 2022-01-03 | 2022-01-07 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31546285 | T3 DI COLGATE-ALLEGHANY 020/542 RPL STRW | 70Y
LC | 121706526 | 005/044 | T2 DI TRINITY-CTTNWD 005/044L RPL STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-07-10 | 2021-07-07 | 2022-08-24 | 2022-07-07 | 2022-07-07 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31548131 | T2 DI TRINITY-CTTNWD 005/044L RPL | 70Y
LC | 121706650 | 000/006 | T2 DI MTN GTE JCT CSCD 000/006L RPL STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-06-07 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547477 | T2 DI MTN GTE JCT CSCD 000/006 RPL STRW | 70Y
LC | 121706655 | 005/007 | T3 DI POTTER VALLEY-WILLITS 5/7 RPL INSW | WILLITS | ETL.7820.POLE.WOOD | 2021-07-10 | 2021-07-06 | 2022-08-09 | 2022-01-02 | 2022-01-06 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546216 | T3 DI POTTER VALLEY-WILLITS 7/5 RPL INSW | 93I
LC | 121706848 | 002/025 | T2 DI MTN GTE JCT-CSCDE 2/25R RPR POLE | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-04-28 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45294984 | T2 DI MTN GTE JCT-CSCDE 2/25R RPR POLE | ICW
LC | 121706994 | 003/031 | T2 DI MTN GT JCT-CASCAD+ 3/31L RPL STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-04-28 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547477 | T2 DI MTN GTE JCT CSCD 000/006 RPL STRW | 70Y
LC | 121707079 | 002/046 | T2 DI SMARTVILLE-NIC #1 02/046 RPL POLE | SACTO | ETL.7990.POLE.WOOD | 2021-07-10 | 2021-07-08 | 2022-08-16 | 2022-07-08 | 2022-07-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548078 | T2 DI SMRTSVLLE NCLS #1 000/002 RPL STRW | 70Y
LC | 121707184 | 043/174 | T2 DI DIABLO-MIDWAY #2 43/174 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-07-10 | 2021-07-08 | 2022-06-15 | 2022-07-08 | 2022-07-08 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068568 | T2 DI DIABLO-MIDWAY #2 43/174 RPR GYWS | ICS
LC | 121707185 | 039/159 | T2 DI DIABLO-MIDWAY #3 439/159 RPR GYWS | PISMOBCH | ETL.5980.TOWR | 2021-07-10 | 2021-07-08 | 2022-08-18 | 2022-07-08 | 2022-07-08 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068630 | T2 DI DIABLO-MIDWAY #3 439/159 RPR GYWS | ICS
LC | 121707187 | 004/006 | T3 DI POTTER VALLEY-WILLITS 4/6 RPR STRW | WILLITS | ETL.7820.POLE.WOOD | 2021-07-10 | 2021-07-06 | 2022-08-09 | 2022-01-02 | 2022-01-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45137097 | T3 DI POTTER VALLEY-WILLITS 4/6 RPR STRW | ICW
LC | 121707188 | 004/006 | T3 DI POTTER VALLEY-WILLITS 4/6 RMV VEG | LAKEVLLE | ETL.7820.POLE.WOOD | 2021-07-10 | 2021-07-06 | 2022-02-10 | 2022-01-02 | 2022-01-06 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE CNCL OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121707275 | 026/192C | T2 DI CARIBOU-TABLE MTN 26/192C RPR FOND | TABLEMTN | ETL.4440.POLE.NWOD | 2021-07-10 | 2021-06-27 | 2022-07-05 | 2022-06-27 | 2022-06-27 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160951 | T2 DI CARIBOU-TABLE MTN 26/192C RPR FOND | ICQ
LC | 121707279 | 003/036 | T2 DI MTN GATE JCT-CASCADE 3/36 RPL STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-08-25 | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31601186 | T2 DI MTN GATE JCT-CASCADE 3/36 RPL STRW | 70Y
LC | 121707387 | 003/071 | T2 DI DELTA-MTN GATE JCT 3/71L RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-08-27 | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546387 | T2 DI DELTA-MTN GATE JCT 3/71L RPL STRW | 70Y
LC | 121707511 | 003/036 | T2 DI MTN GATE JCT-CASCADE 3/36 RPL STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-08-10 | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31601186 | T2 DI MTN GATE JCT-CASCADE 3/36 RPL STRW | 70Y
LC | 121707695 | 014/178 | T2 DI DELTA-MTN GATE JCT 14/178 RPL HRDW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-08-20 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45296793 | T2 DI DELTA-MTN GATE JCT 14/178 RPL HRDW | ICW
LC | 121707696 | 014/178 | T2 DI DELTA-MTN GATE JCT 14/178 RPR STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-08-20 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45298013 | T2 DI DELTA-MTN GATE JCT 14/178 RPR STRW | ICW
LC | 121707699 | 011/149 | T2 DI DELTA-MTN GAT JCT 11/149L RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-10 | 2021-07-09 | 2022-08-22 | 2022-07-09 | 2022-07-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546294 | T2 DI DLTA-MTN GTE JCT 14/179 RPL STRW | 70Y
LC | 121707734 | 003/030 | T2 DI MTN GATE JCT-CASCDE 3/30R RPL STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-08-08 | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547477 | T2 DI MTN GTE JCT CSCD 000/006 RPL STRW | 70Y
LC | 121707735 | 003/030 | T2 DI MTN GATE JCT-CASCDE 3/30L RPL STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-08-08 | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547477 | T2 DI MTN GTE JCT CSCD 000/006 RPL STRW | 70Y
LC | 121707788 | 009/087 | T2 DI UKIAH HPLND CLVDL 009/087 RMV BUTT | LAKEVLLE | ETL.4050.POLE.WDPS | 2021-07-10 | 2021-07-06 | 2022-01-26 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45128087 | T2 DI UKIAH HPLND CLVDL 009/087 RMV BUTT | ICW
LC | 121707820 | 011/149 | T2 DI DELTA-MTN GAT JCT 11/149R RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-10 | 2021-07-09 | 2022-08-22 | 2022-07-09 | 2022-07-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546294 | T2 DI DLTA-MTN GTE JCT 14/179 RPL STRW | 70Y
LC | 121707821 | 040/265 | T2 DI TRINITY-CTTNWD 40/265 RMV BUTT | TABLEMTN | ETL.4040.POLE.WDPS | 2021-07-10 | 2021-07-07 | 2022-06-27 | 2022-07-07 | 2022-07-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45212056 | T2 DI TRINITY-CTTNWD 40/265 RMV BUTT | ICW
LC | 121708497 | 014/081 | T2 MSS LNDNG-DL MONTE #2 14/81 INS AGS | MOSSLNDG | ETL.2840.INSL | 2021-07-10 | 2021-07-10 | 2021-09-02 | 2022-07-10 | 2022-07-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | Missing | Animal Guard-Steel | Install | 44923018 | T2 MSS LNDNG-DL MONTE #1 14/81 INS AGS | ICS
LC | 121708531 | 014/081 | T2 MSS LNDNG-DL MONTE #2 14/81 RPR JMPS | MOSSLNDG | ETL.2840.INSL | 2021-07-10 | 2021-07-10 | 2021-09-02 | 2022-07-10 | 2022-07-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Jumper-Steel | Repair | 44923019 | T2 MSS LNDNG-DL MONTE #1 14/81 RPR JMPS | ICS
LC | 121711698 | 010/076 | T2 DI GREEN VALLEY-LLAGAS 10/76 RPL INSW | MOSSLNDG | ETL.1720.INSL.NCER | 2021-07-12 | 2021-07-05 | 2022-08-01 | 2022-07-05 | 2022-07-05 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579735 | DI GREEN VALLEY-LLAGAS 000/009 RPL INSW | 93I
LC | 121712732 | 001/014 | T3 DI WOODLEAF-PALERMO 001/014L RPR GYWW | TABLEMTN | ETL.4220.POLE.STPS | 2021-07-12 | 2021-07-12 | 2022-05-19 | 2022-01-08 | 2022-01-10 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45212398 | T3 DI WOODLEAF-PALERMO 001/014 RPR GYWW | ICW
LC | 121713128 | 035/676 | T2 WV HAT CRK #1-WESTWD 35/676 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2021-07-12 | 2021-07-12 | 2022-05-06 | 2022-07-12 | 2022-07-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31546937 | T2 WV HAT CRK #1-WESTWD 35/676 RPL STRW | 70Y
LC | 121713134 | 016/232 | T2 DI SSQC-SNT YNZ SW ST 16/232 RPL INSW | PISMOBCH | ETL.3700.INSL.NCER | 2021-07-12 | 2021-06-30 | 2022-04-15 | 2022-06-30 | 2022-06-30 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579988 | T2 DI SISQUOC-SANTA YNEZ 10/159 RPL INSW | 93I
LC | 121713139 | 016/232 | T2 DI SSQC-SNT YNZ SW ST 16/232 RPR STRW | PISMOBCH | ETL.3700.POLE.WDPS | 2021-07-12 | 2021-06-30 | 2022-04-15 | 2022-06-30 | 2022-06-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45069380 | T2 DI SSQC-SNT YNZ SW ST 16/232 RPR STRW | ICW
LC | 121713606 | 069/502 | T2 WV BRIDGEVL-COTTONWD 69/5 INS DMPS | EUREKA | ETL.1110.TOWR | 2021-07-12 | 2021-07-12 | 2022-09-28 | 2022-07-12 | 2022-07-12 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Damper-Steel | Install | 45158757 | T2 WV BRDGEVLLE-CTTNWD 069/5 INS DMPS | ICS
LC | 121714165 | 048/238 | T2 DI MALIN-ROUND MTN #2 48/238 RPR OPGW | TABLEMTN | ETL.6020.INSL.NCER | 2021-07-12 | 2021-07-09 | 2022-07-15 | 2022-07-09 | 2022-07-09 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215175 | T2 DI MALIN-ROUND MTN #2 48/238 RPR OPGW | ICS
LC | 121714175 | 005/124 | T2 WV WEIMAR-HALSEY 5/124 INS GYWW | SACTO | ETL.8340.POLE.WOOD | 2021-07-12 | 2021-07-12 | 2022-03-05 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO AIR | Missing | Guy Wire-Wood | Install | 45144413 | T2 WV WEIMAR-HALSEY 5/124 INS GYWW | ICW
LC | 121714643 | 042/171 | T2 DI DIABLO-MIDWAY #3 42/171 RPR GYWS | PISMOBCH | ETL.5980.TOWR | 2021-07-12 | 2021-07-08 | 2022-06-15 | 2022-07-08 | 2022-07-08 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068631 | T2 DI DIABLO-MIDWAY #3 42/171 RPR GYWS | ICS
LC | 121714644 | 042/173 | T2 DI DIABLO-MIDWAY #2 42/173 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-07-12 | 2021-07-08 | 2022-06-15 | 2022-07-08 | 2022-07-08 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068569 | T2 DI DIABLO-MIDWAY #2 42/173 RPR GYWS | ICS
LC | 121714778 | 060/435 | T2 WV BRDGVLLE-CTTNWD 060/4 RPR FOND | TABLEMTN | ETL.1110.TOWR | 2021-07-12 | 2021-07-12 | 2022-07-28 | 2022-07-12 | 2022-07-12 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160914 | T2 WV BRDGVLLE-CTTNWD 060/4 RPR FOND | ICQ
LC | 121714827 | 011/092 | T2 DI PIT #3-PIT #1 11/92 RPR INSS | TABLEMTN | ETL.5400.INSL | 2021-07-12 | 2021-07-12 | 2022-06-18 | 2022-07-12 | 2022-07-12 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213890 | T2 DI PIT #3-PIT #1 11/92 RPR INSS | ICS
LC | 121714924 | 003/020 | T2 DI STANISLAUS-MNTC #2 3/20 RPR FOND | VICTOR | ETL.3820.TOWR | 2021-07-12 | 2021-07-12 | 2022-01-13 | 2022-07-12 | 2022-07-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45119708 | T2 DI STANISLAUS-MNTC #2 3/20 RPR FOND | ICQ
LC | 121715526 | 095/008 | T2 DI HUMBOLDT-TRINITY 095/008 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-12 | 2021-07-12 | 2021-08-01 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44950054 | T2 DI HUMBOLDT-TRINITY 095/008 RPR GYWW | ICW
LC | 121715528 | 095/008 | T2 DI HUMBOLDT-TRINITY 095/008 RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2021-07-12 | 2021-07-12 | 2021-08-01 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 31546781 | T2 DI HMBLDT-TRNTY 095/001 RPL INSW | 93I
LC | 121715669 | 013/139 | T2 DI RND MTN-CTTNWD #2 13/139R RPL PL | TABLEMTN | ETL.5640.POLE.WDPS | 2021-07-12 | 2021-07-09 | 2022-07-27 | 2022-07-09 | 2022-07-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31542253 | T2 EI RND MTN-CTTNWD #2 13/139 RPL STRC | 70Y
LC | 121715678 | 000/009 | T3 DI WST PNT-VLLY SPRGS 0/9 COMPLETE | VICTOR | ETL.8350.INSL.NCER | 2021-07-12 | 2021-07-12 | 2022-05-16 | 2022-01-08 | 2022-01-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair | 45158150 | T3 DI WST PNT-VLLY SPRGS 0/9 RPR SPLW | ICW
LC | 121715777 | 054/002A | T2 DI HUMBOLDT-TRINITY 054/2A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2021-07-12 | 2021-07-12 | 2022-06-07 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145286 | T2 DI HUMBOLDT-TRINITY 054/2A RPR GYWW | ICW
LC | 121716050 | 012/160 | T2 DI DELTA-MTN GATE JCT 12/160 RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-12 | 2021-07-12 | 2022-08-20 | 2022-07-12 | 2022-07-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546388 | T2 DI DT-M GT JC-MN GT J 12/160 RPL INSW | 70Y
LC | 121716223 | 005/134 | T3 COLGATE-ALLEGHANY 5/134 RPR SWTC | SACTO | ETL.6470.SWIT | 2021-07-12 | 2021-07-12 | 2021-07-22 | 2022-01-08 | 2022-01-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Switch-Wood | Repair | 44906055 | T3 COLGATE-ALLEGHANY 5/134 RPR SWTC | ICW
LC | 121716236 | 027/013 | T3 DI FULTON-HOPLAND 027/013 RPR SPLW | LAKEVLLE | ETL.6890.INSL | 2021-07-12 | 2021-07-12 | 2021-08-04 | 2022-01-08 | 2022-01-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 44907506 | T3 DI FULTON-HOPLAND 027/013 RPR SPLW | ICW
LC | 121716515 | 009/083 | T2 DI UKH-HPLND-CLOVER 9/83 ANTI SPLIT | LAKEVLLE | ETL.4050.POLE.WDPS | 2021-07-12 | 2021-07-06 | 2022-01-26 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45128086 | T2 DI UKH-HPLND-CLOVER 9/83 ANTI SPLIT | ICW
LC | 121716963 | 009/130 | T2 DI DLT-MN GT -MN GT J 9/130 RPR STRW | TABLEMTN | ETL.6750.POLE.WOOD | 2021-07-12 | 2021-07-06 | 2022-08-21 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45298005 | T2 DI DLT-MN GT -MN GT J 9/130 RPR STRW | ICW
LC | 121717091 | 000/013 | T2 DI COLGATE-PALERMO 000/013 RPR GYWW | SACTO | ETL.6500.POLE.WOOD | 2021-07-12 | 2021-07-05 | 2022-05-19 | 2022-07-05 | 2022-07-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45218757 | T2 DI COLGATE-PALERMO 000/013 RPR GYWW | ICW
LC | 121717211 | 025/108B | T2 DI MSS LNDING-MTCALF 25/108B RMV STEP | METCALF | ETL.6050.TOWR | 2021-07-12 | 2021-07-12 | 2022-08-04 | 2022-07-12 | 2022-07-12 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45179152 | T2 DI MSS LNDING-MTCALF 25/108B RMV STEP | ICQ
LC | 121717214 | 071/359 | T2 DI MLN-RND MTN #2 71/359 RPR GYWW | TABLEMTN | ETL.6020.TOWR | 2021-07-12 | 2021-07-12 | 2022-08-08 | 2022-07-12 | 2022-07-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45385812 | T2 DI MLN-RND MTN #2 71/359 RPR GYWW | ICW
LC | 121717217 | 040/161 | T2 DI DIABLO-MIDWAY #2 40/161 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-07-12 | 2021-07-08 | 2022-08-03 | 2022-07-08 | 2022-07-08 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068570 | T2 DI DIABLO-MIDWAY #2 40/161 RPR GYWS | ICS
LC | 121717377 | 029/017 | T2 DI FULTON-HOPLAND 029/017 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-07-12 | 2021-07-08 | 2022-06-23 | 2022-07-08 | 2022-07-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143962 | T2 DI FULTON-HOPLAND 029/017 RPR STRW | ICW
LC | 121717393 | 054/002C | T2 DI HUMBLDT-TRINITY 54/02C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2021-07-12 | 2021-07-12 | 2022-06-07 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145286 | T2 DI HUMBOLDT-TRINITY 054/2A RPR GYWW | ICW
LC | 121717758 | 000/008 | T2 DI BCKS CRK RK CRK 000/008 RPR FOND | TABLEMTN | ETL.4430.TOWR | 2021-07-12 | 2021-07-07 | 2022-07-20 | 2022-07-07 | 2022-07-07 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160918 | T2 DI BCKS CRK RK CRK 000/008 RPR FOND | ICQ
LC | 121717797 | 000/008 | T2 DI BCKS CRK RK CRK 000/008 RPL INSS | TABLEMTN | ETL.4430.INSL | 2021-07-12 | 2021-07-07 | 2022-06-30 | 2022-07-07 | 2022-07-07 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546438 | T2 DI BCKS CRK RK CRK RPL INSS 2 TWRS | 93K
LC | 121717857 | 009/066 | T3 DI GREEN VALLEY-LLAGAS 9/66 RPL INSW | MOSSLNDG | ETL.1720.INSL.NCER | 2021-07-12 | 2021-07-05 | 2022-09-09 | 2022-01-01 | 2022-01-05 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579735 | DI GREEN VALLEY-LLAGAS 000/009 RPL INSW | 93I
LC | 121717859 | 009/066 | T3 DI GREEN VALLEY-LLAGAS 9/66 RPR STRW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-07-12 | 2021-07-05 | 2022-09-09 | 2022-01-01 | 2022-01-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45084402 | T3 DI GREEN VALLEY-LLAGAS 9/66 RPR STRW | ICW
LC | 121717922 | 001/017A | T3 DI WT PNT-VLLY SPRNGS 1/17A RPR STRW | VICTOR | ETL.8350.POLE.WOOD | 2021-07-12 | 2021-07-08 | 2022-05-14 | 2022-01-04 | 2022-01-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45158151 | T3 DI WT PNT-VLLY SPRNGS 1/17A RPR STRW | ICW
LC | 121717956 | 003/025 | T3 DI SOBRANTE-"R" #1 003/025 RMV VEG | CONCORD | ETL.3770.TOWR | 2021-07-12 | 2021-07-07 | 2021-11-22 | 2022-01-03 | 2022-01-07 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE CNCL OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121717967 | 012/107C | T2 DI CRAG VIEW-CASCADE 12/107C RPR SHLW | TABLEMTN | ETL.1350.POLE.NWOD | 2021-07-12 | 2021-07-08 | 2022-09-16 | 2022-07-08 | 2022-07-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45296824 | T2 DI CRAG VIEW-CASCADE 12/107C RPR SHLW | ICW
LC | 121717984 | 005/026 | T2 DI PTTSBRG-SN MTO 005/026 RPL INSS | CONCORD | ETL.5463.INSL | 2021-07-12 | 2021-07-01 | 2022-07-31 | 2022-07-01 | 2022-07-01 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548823 | T2 DI PTTSBRG-SN MTO RPL INSS 4TWRS | 93K
LC | 121717986 | 010/101 | T2 DI PIT #5-RND MTN #2 010/101 RPR STRW | TABLEMTN | ETL.5430.POLE.WOOD | 2021-07-12 | 2021-07-06 | 2022-06-17 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213812 | T2 DI PIT #5-RND MTN #2 010/101 RPR STRW | ICW
LC | 121717987 | 010/101 | T2 DI PIT #5-RND MTN #2 010/101 RPR STRW | TABLEMTN | ETL.5430.POLE.WOOD | 2021-07-12 | 2021-07-06 | 2022-06-17 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213811 | T2 DI PIT #5-RND MTN #2 010/101 RPR STRW | ICW
LC | 121717989 | 010/101 | T2 DI PIT #5-RND MTN #2 010/101 COMPLETE | TABLEMTN | ETL.5430.INSL.NCER | 2021-07-12 | 2021-07-06 | 2022-06-15 | 2022-07-06 | 2022-07-06 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547500 | T2 DI PIT #5-RND MTN #2 010/101 RPL INSW | 93I
LC | 121718066 | 007/066 | T2 DI CTTNWD-BNTN #2 7/66L RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-12 | 2021-07-08 | 2022-07-22 | 2022-07-08 | 2022-07-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213232 | T2 DI CTTNWD-BNTN #2 7/66L RPR STRW | ICW
LC | 121718067 | 007/066 | T2 DI CTTNWD-BNTN #2 7/66R RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-12 | 2021-07-08 | 2022-07-22 | 2022-07-08 | 2022-07-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213233 | T2 DI CTTNWD-BNTN #2 7/66R RPR STRW | ICW
LC | 121719411 | 013/056A | T2 DI TESLA-METCALF 13/56A RPR FOND | METCALF | ETL.6110.TOWR | 2021-07-13 | 2021-07-12 | 2022-06-28 | 2022-07-12 | 2022-07-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45211596 | T2 DI TESLA-METCALF 13/56A RPR FOND | ICQ
LC | 121719513 | 051/000A | T2 DI HMBLDT-TRNTY 051/000A RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-13 | 2021-07-12 | 2022-04-02 | 2022-07-12 | 2022-07-12 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547344 | T2 DI HMBLDT-TRNTY 051/000A RPL INSW | 93I
LC | 121719515 | 051/000A | T2 DI HMBLDT-TRNTY 051/000A RPR STRW | EUREKA | ETL.1820.POLE.WOOD | 2021-07-13 | 2021-07-12 | 2022-04-02 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45145194 | T2 DI HMBLDT-TRNTY 051/000A RPR STRW | ICW
LC | 121719522 | 005/062 | T3 DI W. PNT-VLY SPRNGS 5/62 RPR SPLS | VICTOR | ETL.8350.SWIT | 2021-07-13 | 2021-07-12 | 2022-05-18 | 2022-01-08 | 2022-01-12 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45158153 | T3 DI W. PNT-VLY SPRNGS 5/62 RPR SPLS | ICS
LC | 121719756 | 074/001A | T2 DI HMBLDT-TRNTY 074/001A ANTI SPLIT | EUREKA | ETL.1820.POLE.WDPS | 2021-07-13 | 2021-07-12 | 2022-04-01 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45147806 | T2 DI HMBLDT-TRNTY 074/001A ANTI SPLIT | ICW
LC | 121719888 | 105/002 | T2 DI HMBLDT-TRNTY 105/002 RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-13 | 2021-07-12 | 2022-01-19 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45128324 | T2 DI HMBLDT-TRNTY 105/002 RPR STRW | ICW
LC | 121720515 | 095/001 | T2 DI HMBLDT-TRNTY 095/001 RPL INSW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-13 | 2021-07-13 | 2021-07-31 | 2022-07-13 | 2022-07-13 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546781 | T2 DI HMBLDT-TRNTY 095/001 RPL INSW | 93I
LC | 121720873 | 019/136 | T3 DI METCALF-GRN VLY 19/136R RPLC STRW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-07-13 | 2021-07-13 | 2022-08-27 | 2022-01-09 | 2022-01-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543163 | T3 DI METCALF-GRN VLLY 019/136 RPL STRW | 70Y
LC | 121720998 | :004/023A | T2 DI ROCK CREEK-POE :4/23A RPR INSS | TABLEMTN | ETL.5630.INSL.NCER | 2021-07-13 | 2021-07-06 | 2022-08-07 | 2022-07-06 | 2022-07-06 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213410 | T2 DI ROCK CREEK-POE :4/23A RPR INSS | ICS
LC | 121721022 | 020/141 | T3 DI METCALF-GRN VLLY 20/141R RPL STRW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-07-13 | 2021-07-13 | 2022-07-15 | 2022-01-09 | 2022-01-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543164 | T3 DI METCALF-GRN VLLY 020/141 RPL STRW | 70Y
LC | 121721039 | 000/004 | T3 DI W POINT-VALLEY SPRNGS 0/4 RPR STRW | VICTOR | ETL.8350.POLE.WOOD | 2021-07-13 | 2021-07-13 | 2022-05-14 | 2022-01-09 | 2022-01-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45158155 | T3 DI W POINT-VALLEY SPRNGS 0/4 RPR STRW | ICW
LC | 121721211 | 012/086 | T2 DI GREEN VLY-LLAGAS 12/86 RPL INSW | MOSSLNDG | ETL.1720.INSL.NCER | 2021-07-13 | 2021-07-05 | 2022-08-04 | 2022-07-05 | 2022-07-05 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579735 | DI GREEN VALLEY-LLAGAS 000/009 RPL INSW | 93I
LC | 121721230 | 000/004 | T3 DI W POINT-VALLEY SPRNGS 0/4 RPL HRDD | VICTOR | ETL.8350.POLE.WOOD | 2021-07-13 | 2021-07-13 | 2022-05-14 | 2022-01-09 | 2022-01-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45158156 | T3 DI W POINT-VALLEY SPRNGS 0/4 RPL HRDD | ICW
LC | 121721236 | 010/113 | T3 DI IGNACIO-BOLINAS #1 10/113 RPR GYWW | LAKEVLLE | ETL.7140.POLE.WDPS | 2021-07-13 | 2021-07-13 | 2022-06-18 | 2022-01-09 | 2022-01-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45128035 | T3 DI IGNACIO-BOLINAS #1 10/113 RPR GYWW | ICW
LC | 121721239 | 010/113 | T3 DI IGNACIO-BOLINAS #1 10/113 RPR SPLW | LAKEVLLE | ETL.7140.INSL.CERA | 2021-07-13 | 2021-07-13 | 2022-06-18 | 2022-01-09 | 2022-01-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45128036 | T3 DI IGNACIO-BOLINAS #1 10/113 RPR SPLW | ICW
LC | 121721917 | 004/065 | T3 DI KESWICK-TRNTY 4/65 RPR STRW CMPLTD | TABLEMTN | ETL.7270.POLE.WOOD | 2021-07-13 | 2021-07-05 | 2022-05-30 | 2022-01-01 | 2022-01-05 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3N PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45212826 | T3 DI KESWICK-TRINITY 4/65 RPR STRW | ICW
LC | 121722149 | 001/017 | T2 DI MTN GATE-JCT CSCADE 1/17R RPR STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-13 | 2021-07-06 | 2022-04-27 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45351544 | T2 DI MTN GATE-JCT CSCADE 1/17R RPR STRW | ICW
LC | 121722176 | 040/164 | T2 DI DIABLO-MIDWAY #2 40/164 RPR SHLWS | PISMOBCH | ETL.5970.TOWR | 2021-07-13 | 2021-07-08 | 2022-01-26 | 2022-07-08 | 2022-07-08 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45068571 | T2 DI DIABLO-MIDWAY #2 40/164 RPR SHLWS | ICS
LC | 121722340 | 001/017 | T2 DI MTN GATE-JCT CSCADE 1/17L RPR STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-13 | 2021-07-06 | 2022-04-27 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45351553 | T2 DI MTN GATE-JCT CSCADE 1/17L RPR STRW | ICW
LC | 121722347 | 009/004 | T3 DI POTTER VALLEY-WILLITS 9/4 COMPLETE | WILLITS | ETL.7820.POLE.WOOD | 2021-07-13 | 2021-07-06 | 2022-06-19 | 2022-01-02 | 2022-01-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45136866 | T3 DI POTTER VALLEY-WILLITS 9/4 RPR STRW | ICW
LC | 121722502 | 000/003 | T2 DI COLGATE-SMARTVILLE #2 0/3 RPR GYWW | SACTO | ETL.6520.POLE.WOOD | 2021-07-13 | 2021-07-08 | 2022-07-19 | 2022-07-08 | 2022-07-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45253247 | T2 DI COLGATE-SMARTVILLE #2 0/3 RPR GYWW | ICW
LC | 121722666 | 006/071 | T2 DI GRN VLLY-PL SWT 6/71 RPR STRW | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-07-13 | 2021-07-05 | 2022-03-10 | 2022-07-05 | 2022-07-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213434 | T2 DI GRN VLLY-PL SWT 6/71 RPR STRW | ICW
LC | 121722668 | 006/071 | T2 DI GRN VLLY-PL SWT 6/71 RPR STRW | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-07-13 | 2021-07-05 | 2022-03-10 | 2022-07-05 | 2022-07-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45243290 | T2 DI GRN VLLY-PL SWT 6/71 RPR STRW | ICW
LC | 121723058 | 071/360 | T2 DI MALIN-RND MTN #2 71/360 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-07-13 | 2021-07-12 | 2022-08-11 | 2022-07-12 | 2022-07-12 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45240552 | T2 DI MALIN-RND MTN #2 71/360 RPR GYWS | ICS
LC | 121723230 | 072/364 | T2 DI MLN-RD MT #2 72/364 RPR OPGW | TABLEMTN | ETL.6020.INSL.NCER | 2021-07-13 | 2021-07-09 | 2022-07-13 | 2022-07-09 | 2022-07-09 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215174 | T2 DI MLN-RD MT #2 72/364 RPR OPGW | ICS
LC | 121724201 | 003/007 | T3 DI DONNELLS-MI-WUK 3/7L RPL STRW | VICTOR | ETL.1400.POLE.WDPS | 2021-07-13 | 2021-07-07 | 2022-10-08 | 2022-01-03 | 2022-01-07 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31578120 | T3 DI DONNELLS-MI-WUK 3/7L RPL STRW | 70Y
LC | 121724202 | 003/007 | T3 DI DONNELLS-MI-WUK 3/7R RPL STRW | VICTOR | ETL.1400.POLE.WDPS | 2021-07-13 | 2021-07-07 | 2022-10-08 | 2022-01-03 | 2022-01-07 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31578120 | T3 DI DONNELLS-MI-WUK 3/7L RPL STRW | 70Y
LC | 121724441 | 043/175 | T2 DI DIABLO-MDWY#2 43/175 RPR GYWW | PISMOBCH | ETL.5970.TOWR | 2021-07-13 | 2021-07-08 | 2022-06-15 | 2022-07-08 | 2022-07-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45068572 | T2 DI DIABLO-MDWY#2 43/175 RPR GYWW | ICW
LC | 121724482 | 044/183 | T2 DI DIABLO-MDWY#2-TWR 44/183 RPR GYWW | PISMOBCH | ETL.5970.TOWR | 2021-07-13 | 2021-07-13 | 2022-06-21 | 2022-07-13 | 2022-07-13 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068573 | T2 DI DIABLO-MDWY#2-TWR 44/183 RPR GYWW | ICS
LC | 121724488 | 003/024 | T3 DI SOBRANTE "R" #1+" 3/24 RMV VEG | CONCORD | ETL.3770.TOWR | 2021-07-13 | 2021-07-13 | 2021-11-22 | 2022-01-09 | 2022-01-13 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW CNCL OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121724499 | 004/022 | T2 DI MSS LANDING-METCALF 4/22 RMV NEST | MOSSLNDG | ETL.6050.TOWR | 2021-07-13 | 2021-07-13 | 2022-01-20 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45121224 | T2 DI MSS LANDING-METCALF 4/22 RMV NEST | ICW
LC | 121724569 | 002/064 | T3 DI KILARC-CEDAR CRK WP 2/64 RPL HRDD | TABLEMTN | ETL.7290.POLE.WOOD | 2021-07-13 | 2021-07-13 | 2022-04-25 | 2022-01-09 | 2022-01-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45212234 | T3 DI KILARC-CEDAR CRK WP 2/64 RPL HRDD | ICW
LC | 121724695 | 065/468 | T2 DI BRIDGEVILLE-CTTNWD 65/468 RPR FOND | TABLEMTN | ETL.1110.TOWR | 2021-07-13 | 2021-07-13 | 2022-07-28 | 2022-07-13 | 2022-07-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160916 | T2 DI BRIDGEVILLE-CTTNWD 65/468 RPR FOND | ICQ
LC | 121724698 | 019/451 | T2 DI DRM GRSS VLY-WIMR 19/451 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2021-07-13 | 2021-07-13 | 2022-03-30 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45193828 | T2 DI DRM GRSS VLY-WIMR 19/451 RPR STRW | ICW
LC | 121724738 | 095/005 | T2 DI HUMBOLDT-TRINITY 95/5 RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-13 | 2021-07-13 | 2022-03-22 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45160743 | T2NT EI HUMBOLDT-TRINITY 95/5 RMV BUTT | ICW
LC | 121724758 | 005/049 | T2 DI CTTNWD-BNTN #2 5/49L RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-13 | 2021-07-07 | 2022-07-23 | 2022-07-07 | 2022-07-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213234 | T2 DI CTTNWD-BNTN #2 5/49L RPR STRW | ICW
LC | 121724782 | 095/005 | T2 DI HUMBLDT-TRNTY-CERMIN 95/5 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-13 | 2021-07-13 | 2021-08-12 | 2022-07-13 | 2022-07-13 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548117 | T2 DI HUMBLDT-TRNTY-CERMIN 95/5 RPL INSW | 93I
LC | 121724803 | 010/050 | T2 DI PITTSBURG-TESLA #1 10/50 RPR FOND | CONCORD | ETL.5510.TOWR | 2021-07-13 | 2021-07-07 | 2022-03-28 | 2022-07-07 | 2022-07-07 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190832 | T2 DI PITTSBURG-TESLA #1 10/50 RPR FOND | ICQ
LC | 121724844 | 004/007 | T3 DI DNNELLS-MI-WUK-STEEL X4/7 RPR INSW | VICTOR | ETL.1400.INSL.CERA | 2021-07-13 | 2021-07-07 | 2022-08-18 | 2022-01-03 | 2022-01-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45122718 | T3 DI DNNELLS-MI-WUK-STEEL X4/7 RPR INSW | ICW
LC | 121724852 | 005/049 | T2 DI CTTNWD-BNTN #2 5/49R RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-13 | 2021-07-07 | 2022-07-23 | 2022-07-07 | 2022-07-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213237 | T2 DI CTTNWD-BNTN #2 5/49R RPR STRW | ICW
LC | 121724884 | 005/050 | T2 DI CTTNWD-BNTN #2 5/50 RPR INSW | TABLEMTN | ETL.6650.INSL.NCER | 2021-07-13 | 2021-07-07 | 2022-07-23 | 2022-07-07 | 2022-07-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45213238 | T2 DI CTTNWD-BNTN #2 5/50 RPR INSW | ICW
LC | 121725009 | 002/038 | T3 DI BURNS-LONE STAR #1 02/38 RPR STRW | MOSSLNDG | ETL.6230.POLE.NWOD | 2021-07-13 | 2021-07-09 | 2022-01-19 | 2022-01-05 | 2022-01-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 44932394 | T3 DI BURNS-LONE STAR #1 02/38 RPR STRW | ICW
LC | 121725010 | 003/053 | T2 DI BRIONES TAP 003/053 RPR GYWW | CONCORD | ETL.7055.POLE.WOOD | 2021-07-13 | 2021-07-07 | 2022-04-02 | 2022-07-07 | 2022-07-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45107141 | T2 DI BRIONES TAP 003/053 RPR GYWW | ICW
LC | 121725058 | 007/004 | T3 DI DONNELLS-MI-WUK 7/4 RMV BUTT | VICTOR | ETL.1400.POLE.WDPS | 2021-07-13 | 2021-07-07 | 2022-08-31 | 2022-01-03 | 2022-01-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45122740 | T3 DI DONNELLS-MI-WUK-WOOD 7/4 RMV BUTT | ICW
LC | 121725182 | 002/019 | T2 DI MTN GAT JCT-CSCD+ 02/19 RPL STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-13 | 2021-07-06 | 2022-04-29 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547477 | T2 DI MTN GTE JCT CSCD 000/006 RPL STRW | 70Y
LC | 121725195 | 002/009 | T2 DI CHOWCHILLA-KERHOFF 2/9 RPR GYWW | FRESNO | ETL.1250.POLE.WOOD | 2021-07-13 | 2021-07-07 | 2022-02-17 | 2022-07-07 | 2022-07-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45068184 | T2 DI CHOWCHILLA-KERHOFF 2/9 RPR GYWW | ICW
LC | 121725251 | 013/170 | T2 DI DLTA-MTN GTE JT 013/170R INS HRDW | TABLEMTN | ETL.6750.POLE.STPS | 2021-07-13 | 2021-07-06 | 2022-08-20 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | Missing | Hardware-Wood | Install | 45298003 | T2 DI DLTA-MTN GTE JT 013/170R INS HRDW | ICW
LC | 121725274 | 073/002B | T2 DI HUMBOLDT-TRINITY 073/002B RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-13 | 2021-06-27 | 2022-10-17 | 2022-06-27 | 2022-06-27 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547352 | T2 DI HUMBOLDT-TRINITY 073/002A RPL INSW | 93I
LC | 121725277 | 073/002A | T2 DI HUMBOLDT-TRINITY 073/002A RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-13 | 2021-07-01 | 2022-10-17 | 2022-07-01 | 2022-07-01 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547352 | T2 DI HUMBOLDT-TRINITY 073/002A RPL INSW | 93I
LC | 121725371 | 009/129 | T2 DI DLT-MTN GT JCTMT GT 9/129 RPR STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-13 | 2021-07-06 | 2022-08-22 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45298001 | T2 DI DLT-MTN GT JCTMT GT 9/129 RPR STRW | ICW
LC | 121725372 | 008/079 | T2 DI PIT #5-RND MTN #1 08/079L RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-13 | 2021-07-09 | 2022-07-14 | 2022-07-09 | 2022-07-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121725374 | 008/079 | T2 DI PIT #5-RND MTN #1 08/079R RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-13 | 2021-07-09 | 2022-07-14 | 2022-07-09 | 2022-07-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121725584 | 001/018 | T3 DI WOODLEAF-PALERMO 001/018 RPR STRW | TABLEMTN | ETL.4220.POLE.STPS | 2021-07-14 | 2021-07-07 | 2022-06-01 | 2022-01-03 | 2022-01-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45212399 | T3 DI WOODLEAF-PALERMO 001/018 RPR STRW | ICW
LC | 121725587 | 001/018 | T3 DI WOODLEAF-PALERMO 001/018 RPR STRW | TABLEMTN | ETL.4220.POLE.STPS | 2021-07-14 | 2021-07-07 | 2022-06-01 | 2022-01-03 | 2022-01-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45212480 | T3 DI WOODLEAF-PALERMO 001/018 RPR STRW | ICW
LC | 121725589 | 001/018 | T3 DI WOODLEAF-PALERMO 001/018 RMV BUTT | TABLEMTN | ETL.4220.POLE.STPS | 2021-07-14 | 2021-07-07 | 2022-06-01 | 2022-01-03 | 2022-01-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45212481 | T3 DI WOODLEAF-PALERMO 001/018 RMV BUTT | ICW
LC | 121725629 | 000/005 | T2 DI MELONES-CURTIS 000/005 RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-14 | 2021-07-13 | 2021-11-30 | 2022-07-13 | 2022-07-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31551988 | T2 EI MELONES-CURTIS 0/5L RPL STRW | 70Y
LC | 121725901 | 000/005 | T2 DI MELONES-CURTIS 000/005 RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-14 | 2021-07-13 | 2021-11-30 | 2022-07-13 | 2022-07-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | Rotten | Structure-Wood | Replace | 31551988 | T2 EI MELONES-CURTIS 0/5L RPL STRW | 70Y
LC | 121725999 | 013/118A | T3 DI GRN VLLY-PAUL SWT 13/118A RMV VEG | MOSSLNDG | ETL.1730.POLE.NWOD | 2021-07-14 | 2021-07-10 | 2021-12-08 | 2022-01-06 | 2022-01-10 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121726189 | 005/063 | T2 DI PIT #5-RND MTN #2 5/63 RPR SRW COA | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-14 | 2021-07-09 | 2022-05-07 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213810 | T2 DI PIT #5-ROUND MTN #2 5/63 RPR STRW | ICW
LC | 121726274 | 008/080 | T2 DI PIT #5-ROUND MTN #1 8/80 RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-14 | 2021-07-09 | 2022-06-30 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213260 | T2 DI PIT #5-ROUND MTN #1 8/80 RPR STRW | ICW
LC | 121727331 | 009/115 | T2 DI WT PT-VLY SGS 9/115 RPL STRW CMPLT | VICTOR | ETL.8350.POLE.WOOD | 2021-07-14 | 2021-07-13 | 2022-05-25 | 2022-07-13 | 2022-07-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31579997 | T3 DI WP-VALLEY SPRINGS 0/2 RPL STRW | 70Y
LC | 121727332 | 003/034 | T2 DI PIT #5-ROUND MTN #2 3/34 COMPLETE | TABLEMTN | ETL.5430.INSL.NCER | 2021-07-14 | 2021-07-13 | 2022-06-13 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Wood | Replace | 45213809 | T2 DI PIT #5-ROUND MTN #2 3/34 RPL DAMW | ICW
LC | 121727498 | 019/537 | T3 DI COLGATE-ALLEGHANY 19/537 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2021-07-14 | 2021-07-07 | 2022-06-14 | 2022-01-03 | 2022-01-07 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31596507 | T3 DI COLGATE-ALLEGHANY 21/567 RPL STRW | 70Y
LC | 121727774 | 017/407 | T2 DI DRM-GRSS VLLY-WMR 17/407 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2021-07-14 | 2021-07-13 | 2022-06-29 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45193829 | T2 DI DRM-GRSS VLLY-WMR 17/407 RPR STRW | ICW
LC | 121729744 | 095/002 | T2 DI HUMBOLDT-TRINITY 95/2 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-14 | 2021-07-12 | 2021-07-31 | 2022-07-12 | 2022-07-12 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546781 | T2 DI HMBLDT-TRNTY 095/001 RPL INSW | 93I
LC | 121729881 | 007/003B | T2 DI LAYTONVILLE-COVELO 7/3B RMV STEP | LAKEVLLE | ETL.7390.POLE.NWOD | 2021-07-14 | 2021-07-09 | 2021-10-21 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45000042 | T2 DI LAYTONVILLE-COVELO 7/3B RMV STEP | ICW
LC | 121729887 | 012/003 | T3 DI DONNELLS-MI-WUK 012/003 RPR STRW | VICTOR | ETL.1400.POLE.WDPS | 2021-07-14 | 2021-07-07 | 2022-06-11 | 2022-01-03 | 2022-01-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45122741 | T3 DI DONNELLS-MI-WUK 12/3 RPR STRW | ICW
LC | 121730031 | 086/000H | T2 DI HUMBOLDT-BRDGVL 86/0H RPR GYWW | EUREKA | ETL.1810.POLE.WOOD | 2021-07-14 | 2021-07-09 | 2022-06-14 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45149741 | T2 DI HUMBOLDT-BRDGVL 86/0H RPR GYWW | ICW
LC | 121730038 | 066/001 | T2 DI HUMBOLT-TRINITY 066/001C RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-14 | 2021-07-12 | 2022-06-06 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145525 | T2 EI HUMBOLDT-TRINITY 66/1R RPR ANCHW | ICW
LC | 121730345 | 003/026 | T3 DI GRN VLLY-LLAGAS 003/026 RPL HRDW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-07-14 | 2021-07-14 | 2021-07-22 | 2022-01-10 | 2022-01-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 44923408 | T3 DI GRN VLLY-LLAGAS 003/026 RPL HRDW | ICW
LC | 121730721 | 003/026 | T3 DI GRN VLLY-LLAGAS 003/026 RPR INSW | MOSSLNDG | ETL.1720.INSL.CERA | 2021-07-14 | 2021-07-14 | 2021-07-22 | 2022-01-10 | 2022-01-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44923647 | T3 DI GRN VLLY-LLAGAS 003/026 RPR INSW | ICW
LC | 121730966 | 003/091 | T2 DI HMLTN-BRNCH CHSTR 3/91 BOND GYWW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-07-14 | 2021-07-13 | 2021-07-22 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44924448 | T2 DI HMLTN-BRNCH CHSTR 3/91 BOND GYWW | ICW
LC | 121731052 | 000/016 | T2 DLT-MTN GT J-MTN GT J 0/16 RPL STR | TABLEMTN | ETL.6750.POLE.WOOD | 2021-07-14 | 2021-07-14 | 2022-08-27 | 2022-07-14 | 2022-07-14 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31549106 | T2 DLT-MTN GT J-MTN GT J 0/16 RPL STR | 70Y
LC | 121731053 | 006/004 | T3 DI DONNELLS-MI-WUK 6/4 RPR STRW | VICTOR | ETL.1400.POLE.WDPS | 2021-07-14 | 2021-07-07 | 2022-08-28 | 2022-01-03 | 2022-01-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45122742 | T3 DI DONNELLS-MI-WUK 6/4 RPR STRW | ICW
LC | 121731122 | 010/100 | T3 DI GRN VLY-PL SWT 10/100 RPR GYWW | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-07-14 | 2021-07-13 | 2022-03-10 | 2022-01-09 | 2022-01-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45211631 | T3 DI GRN VLY-PL SWT 10/100 RPR GYWW | ICW
LC | 121731124 | 044/180 | T2 DI DIABLO-MIDWAY #2 44/180 RPR SHLDWS | PISMOBCH | ETL.5970.TOWR | 2021-07-14 | 2021-07-13 | 2022-01-26 | 2022-07-13 | 2022-07-13 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45068574 | T2 DI DIABLO-MIDWAY #2 44/180 RPR SHLDWS | ICS
LC | 121731291 | 005/003 | T3 DI DONNELLS-MI-WUK 005/003L RPR STRW | VICTOR | ETL.1400.POLE.WDPS | 2021-07-14 | 2021-07-07 | 2022-08-30 | 2022-01-03 | 2022-01-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45122743 | T3 DI DONNELLS-MI-WUK 005/003L RPR STRW | ICW
LC | 121731292 | 005/003 | T3 DI DONNELLS-MI-WUK 005/003R RPR STRW | VICTOR | ETL.1400.POLE.WDPS | 2021-07-14 | 2021-07-07 | 2022-08-30 | 2022-01-03 | 2022-01-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45122744 | T3 DI DONNELLS-MI-WUK 005/003R RPR STRW | ICW
LC | 121731295 | 001/018 | T2 DI PT #5-RD MN #2 1/18 RPL STRW CMPLT | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-14 | 2021-07-09 | 2022-06-10 | 2022-07-09 | 2022-07-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547482 | T2 DI PIT #5-ROUND MTN #2 1/18R RPL STRW | 70Y
LC | 121731533 | 011/005 | T3 DI LAURELES-OTTER 011/005 RPR GYWW | MOSSLNDG | ETL.7380.POLE.WOOD | 2021-07-14 | 2021-07-07 | 2022-03-23 | 2022-01-03 | 2022-01-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45084509 | T3 DI LAURELES-OTTER 011/005 RPR GYWW | ICW
LC | 121731563 | 002/002 | T2 DI MENDOCINO-UKIAH 002/002 RPL INSW | WILLITS | ETL.2420.INSL.CERA | 2021-07-14 | 2021-07-09 | 2022-07-13 | 2022-07-09 | 2022-07-09 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545607 | EI MENDOCINO-UKIAH 3/4 RPL INSW | 93I
LC | 121731690 | 016/119 | T2 DI CAYUCOS-CAMBRIA 016/119 RPL POLE | PISMOBCH | ETL.8560.POLE.WOOD | 2021-07-14 | 2021-07-09 | 2022-08-21 | 2022-07-09 | 2022-07-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31577901 | T2 DI CAYUCOS-CAMBRIA 016/119 RPL POLE | 70Y
LC | 121731717 | 000/005 | T3 DI DRUM-SUMMIT #2 00/05 RPL ANCW | SACTO | ETL.1450.POLE.WDPS | 2021-07-14 | 2021-07-08 | 2022-05-30 | 2022-01-04 | 2022-01-08 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Anchor-Wood | Replace | 31546836 | T3 DI DRUM-SUMMIT #2 00/05 RPL ANCW | 93E
LC | 121731771 | 012/163 | T2 DI DLTA MTN GTE JCT 012/163 RPR STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-14 | 2021-07-12 | 2022-08-23 | 2022-07-12 | 2022-07-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45297967 | T2 DI DLTA MTN GTE JCT 012/163 RPR STRW | ICW
LC | 121731797 | 002/005 | T2 DI MENDO-UKIAH 02/05R RPR STRW | WILLITS | ETL.2420.POLE.WDPS | 2021-07-14 | 2021-07-09 | 2022-07-14 | 2022-07-09 | 2022-07-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45142180 | T2 DI MENDO-UKIAH 02/05R RPR STRW | ICW
LC | 121731846 | 001/010 | T2 DI PIT #6 TAP 1/10 RPR SHLW | TABLEMTN | ETL.5441.POLE.STPS | 2021-07-14 | 2021-07-14 | 2022-06-21 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45213831 | T2 DI PIT #6 TAP 1/10 RPR SHLW | ICW
LC | 121731888 | 003/026 | T3 DI SOBRANTE "R" "#2+" 3/26 RPR INSS | CONCORD | ETL.3780.INSL.NCER | 2021-07-14 | 2021-07-07 | 2022-06-07 | 2022-01-03 | 2022-01-07 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair | 45168056 | T3 DI SOBRANTE "R" "#2+" 3/26 RPR INSS | ICS
LC | 121731931 | 003/026 | T3 DI SOBRANTE ""R"" #1+" 3/26 RMV VEG | CONCORD | ETL.3770.TOWR | 2021-07-14 | 2021-07-07 | 2021-12-15 | 2022-01-03 | 2022-01-07 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121732075 | 008/075 | T2 DI CTTNWD-BENTON #2 8/75L RMV BUTT | TABLEMTN | ETL.6650.POLE.STPS | 2021-07-14 | 2021-07-08 | 2022-06-14 | 2022-07-08 | 2022-07-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45213262 | T2 DI CTTNWD-BENTON #2 8/75 RMV BUTT | ICW
LC | 121732101 | :019/010 | T2 DI EAGLE ROCK-RDBD :019/010C RPR GYWW | LAKEVLLE | ETL.1480.POLE.WDPS | 2021-07-14 | 2021-07-09 | 2022-01-20 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45061762 | T2 DI EAGLE ROCK-RDBD :019/010C RPR GYWW | ICW
LC | 121732102 | :019/010 | T2 DI EAGLE ROCK-RDBD :019/010R RPR GYWW | LAKEVLLE | ETL.1480.POLE.WDPS | 2021-07-14 | 2021-07-09 | 2022-01-20 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45061719 | T2 DI EAGLE ROCK-RDBD :019/010R RPR GYWW | ICW
LC | 121732104 | :019/010 | T2 DI EAGLE ROCK-RDBD :019/010L RPR GYWW | LAKEVLLE | ETL.1480.POLE.WDPS | 2021-07-14 | 2021-07-09 | 2022-01-20 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45061718 | T2 DI EAGLE ROCK-RDBD :019/010L RPR GYWW | ICW
LC | 121732143 | 012/102 | T2 DI PIT #3-PIT #1 012/102 RPR INSS | TABLEMTN | ETL.5400.INSL | 2021-07-14 | 2021-07-09 | 2022-06-18 | 2022-07-09 | 2022-07-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213889 | T2 DI PIT #3-PIT #1 012/102 RPR INSS | ICS
LC | 121732162 | 004/001 | T2 DI LAYTONVILLE-COVELO 4/1 RPR GYWW | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-07-14 | 2021-07-08 | 2021-10-19 | 2022-07-08 | 2022-07-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44999936 | T2 DI LAYTONVILLE-COVELO 4/1 RPR GYWW | ICW
LC | 121732190 | 004/001 | T3 DI DONNELLS-MI-WUK-WOOD 4/1 RPR STRW | VICTOR | ETL.1400.POLE.WDPS | 2021-07-14 | 2021-07-07 | 2022-08-17 | 2022-01-03 | 2022-01-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45122750 | T3 DI DONNELLS-MI-WUK-WOOD 4/1 RPR STRW | ICW
LC | 121732199 | 012/096 | T2 DI PIT #3-PIT #1 12/96 RPR FOND | TABLEMTN | ETL.5400.TOWR | 2021-07-14 | 2021-07-09 | 2022-07-26 | 2022-07-09 | 2022-07-09 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195502 | T2 DI PIT #3-PIT #1 12/96 RPR FOND | ICQ
LC | 121732269 | 093/008 | T2 DI HUMBOLDT-TRINITY 93/08L BACKFIL | EUREKA | ETL.1820.POLE.STPS | 2021-07-14 | 2021-07-06 | 2022-03-23 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45160729 | T2 DI HUMBOLDT-TRINITY 93/08L BACKFIL | ICW
LC | 121732300 | 006/046 | T2 DI TRINITY-CTTNWD 6/46 RMV BUTT | TABLEMTN | ETL.4040.POLE.STPS | 2021-07-14 | 2021-07-07 | 2022-06-23 | 2022-07-07 | 2022-07-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45195500 | T2 DI TRINITY-CTTNWD 6/46 RMV BUTT | ICW
LC | 121732307 | 006/090 | T3 DI MIDDLEFORK #1 6/90 RPR GYWW | SACTO | ETL.8405.POLE.WOOD | 2021-07-14 | 2021-07-12 | 2022-08-05 | 2022-01-08 | 2022-01-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45017967 | T3NT DI MIDDLEFORK #1 6/90 RPR GYWW | ICW
LC | 121732338 | 011/086B | T2 DI CARBU-TBL MTN 11/86B RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2021-07-14 | 2021-06-12 | 2022-06-23 | 2022-06-12 | 2022-06-12 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45212454 | T2 DI CARBU-TBL MTN 11/86B RPR GYWS | ICS
LC | 121732371 | 013/103 | T2 DI PIT #3-PIT #1 013/103 RPL HRDT | TABLEMTN | ETL.5400.TOWR | 2021-07-14 | 2021-07-09 | 2022-07-26 | 2022-07-09 | 2022-07-09 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45198325 | T2 DI PIT #3-PIT #1 013/103 RPL HRDT | ICQ
LC | 121732372 | 013/103 | T2 DI PIT #3-PIT #1 013/103 RPR JUMS | TABLEMTN | ETL.5400.TOWR | 2021-07-14 | 2021-07-09 | 2022-06-24 | 2022-07-09 | 2022-07-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Jumper-Steel | Repair | 45213888 | T2 DI PIT #3-PIT #1 013/103 RPR JUMS | ICS
LC | 121732470 | 001/012 | T2 DI LAYTONVILLE-COVELO 01/12 RPR GYWW | WILLITS | ETL.7390.POLE.WOOD | 2021-07-14 | 2021-07-08 | 2022-06-16 | 2022-07-08 | 2022-07-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44999874 | T2 DI LAYTONVILLE-COVELO 01/12 RPR GYWW | ICW
LC | 121732471 | 002/002 | T2 DI MENDOCINO-UKIAH 2/2 RPR STRW | WILLITS | ETL.2420.POLE.WDPS | 2021-07-14 | 2021-07-09 | 2022-07-13 | 2022-07-09 | 2022-07-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45142182 | T2 DI MENDOCINO-UKIAH 2/2 RPR STRW | ICW
LC | 121732474 | 001/022 | T2 DI COLGATE-PALERMO 1/22 RMV BUTT | SACTO | ETL.6500.POLE.WOOD | 2021-07-14 | 2021-07-09 | 2022-05-22 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45218803 | T2 DI COLGATE-PALERMO 1/22 RMV BUTT | ICW
LC | 121733471 | 002/035 | T2 WEIMAR #1 2/35 RPL STRW | SACTO | ETL.7560.POLE.WOOD | 2021-07-15 | 2021-07-15 | 2022-08-28 | 2022-07-15 | 2022-07-15 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31547662 | T2 WEIMAR #1 2/35 RPL STRW | 70Y
LC | 121733472 | 074/374 | T2 DI MALIN-RND MTN #2 74/374 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2021-07-15 | 2021-07-15 | 2022-07-16 | 2022-07-15 | 2022-07-15 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45215173 | T2 DI MALIN-RND MTN #2 74/374 RPR INSS | ICS
LC | 121733473 | 073/002C | T2 DI HUMBOLDT-TRINITY 073/002C RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-15 | 2021-06-27 | 2022-10-17 | 2022-06-27 | 2022-06-27 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547352 | T2 DI HUMBOLDT-TRINITY 073/002A RPL INSW | 93I
LC | 121733479 | 004/053 | T3 DI DRUM-RIO OSO #1 4/53 RPR JUMS | SACTO | ETL.1420.INSL.NCER | 2021-07-15 | 2021-07-14 | 2021-11-06 | 2022-01-10 | 2022-01-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Steel | Repair | 45017966 | T3 DI DRUM-RIO OSO #1 4/53 RPR JUMS | ICS
LC | 121733741 | 002/019 | T2 DI MTN GAT JCT-CSCD 2/19L RPL STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-15 | 2021-07-06 | 2022-04-29 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547477 | T2 DI MTN GTE JCT CSCD 000/006 RPL STRW | 70Y
LC | 121734028 | 084/001 | T2 DI HUMBOLDT-TRINITY 84/1 RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-03-26 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45149343 | T2NT EI CTTNWD-HMBLDT 84/1R RPR GYWW | ICW
LC | 121734172 | :007/007 | T2 WV BLLTA-RVRBNK-MLNS :7/7 RPL INSS | VICTOR | ETL.1070.TOWR | 2021-07-15 | 2021-07-15 | 2022-12-18 | 2022-07-15 | 2022-07-15 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549232 | T2 WV BLLTA-RVRBNK-MLNS :7/7 RPL INSS | 93K
LC | 121734348 | 003/026 | T2 EI TRINITY-CTTNWD 3/26R RPL STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-07-15 | 2021-03-19 | 2021-09-17 | 2022-03-19 | 2022-03-19 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31508137 | T3 DI TRINITY-CTTNWD 11/92 RPL STRW(ENG) | 70Y
LC | 121734419 | 022/258 | T3 DI IGNACIO-BOLINAS #2 22/258 RPR INSW | LAKEVLLE | ETL.7180.INSL.CERA | 2021-07-15 | 2021-07-12 | 2022-09-24 | 2022-01-08 | 2022-01-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45142537 | T3 DI IGNACIO-BOLINAS #2 22/258 RPR INSW | ICW
LC | 121734490 | 054/001C | T2 DI HUMBOLDT-TRINITY 054/001C RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2021-07-15 | 2021-07-12 | 2022-06-08 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145285 | T2 DI HUMBOLDT-TRINITY- 54/1A RPR GYWW | ICW
LC | 121734600 | 000/008 | T3 DI MORAGA-OAKLAND #3 0/8 INS HRDT | CONCORD | ETL.2740.TOWR | 2021-07-15 | 2021-07-12 | 2022-02-10 | 2022-01-08 | 2022-01-12 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45168398 | T3 DI MORAGA-OAKLAND #3 0/8 INS HRDT | ICQ
LC | 121734606 | 048/000 | T2 DI HUMBOLDT-TRINITY 48/0 RPR FOND | EUREKA | ETL.1820.POLE.STPS | 2021-07-15 | 2021-07-12 | 2022-03-27 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45158836 | T2 DI HUMBOLDT-TRINITY 48/0 RPR FOND | ICW
LC | 121734613 | 064/001 | T2 DI HUMBOLT-TRINTY 064/001R RPL HRDD | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-06-09 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45145457 | T2 DI HUMBOLT-TRINTY 064/001R RPL HRDD | ICW
LC | 121734783 | 013/352 | T3 DI COLGATE-ALLEGHANY 13/352 RPR INSW | SACTO | ETL.6470.INSL.NCER | 2021-07-15 | 2021-07-12 | 2022-06-17 | 2022-01-08 | 2022-01-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair | 45224627 | T3 DI COLGATE-ALLEGHANY 13/352 RPR INSW | ICW
LC | 121735025 | 001/018 | T2 DI PIT #5-ROUND MTN #2 1/18R RPL STRW | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-15 | 2021-07-09 | 2022-06-10 | 2022-07-09 | 2022-07-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547482 | T2 DI PIT #5-ROUND MTN #2 1/18R RPL STRW | 70Y
LC | 121735029 | 009/254 | T3 DI COLGATE-ALLEGHANY 009/254 RPL HRDD | SACTO | ETL.6470.POLE.WOOD | 2021-07-15 | 2021-07-12 | 2022-06-19 | 2022-01-08 | 2022-01-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45224628 | T3 DI COLGATE-ALLEGHANY 009/254 RPL HRDD | ICW
LC | 121735061 | 025/281 | T3 DI IGNCI-BLNS #2 25/281 COMPLETE | LAKEVLLE | ETL.7180.POLE.WOOD | 2021-07-15 | 2021-07-12 | 2022-06-25 | 2022-01-08 | 2022-01-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45142529 | T3 DI IGANCIO-BLNS #2 025/281 RPR STRW | ICW
LC | 121735238 | 070/004 | T2 DI HUMBOLDT-TRINITY 70/4 RPR INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-15 | 2021-07-12 | 2022-03-30 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45147637 | T2 DI HUMBOLDT-TRINITY 70/4 RPR INSW | ICW
LC | 121735330 | 006/144 | T2 WV DEL MONTE-VIEJO 6/144 RPL INSW | MOSSLNDG | ETL.6710.INSL.NCER | 2021-07-15 | 2021-07-15 | 2022-10-02 | 2022-07-15 | 2022-07-15 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31577836 | T2 WV DEL MONTE-VIEJO 6/144 RPL INSW | 93I
LC | 121735917 | 018/416 | T2 VOLTA-DESCHUTES 18/416 RPL STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2021-07-15 | 2021-07-10 | 2022-06-08 | 2022-07-10 | 2022-07-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31547666 | T2 VOLTA-DESCHUTES 16/357 RPL STRW | 70Y
LC | 121736009 | 017/384 | T2 VOLTA-DESCHUTES 17/384 RPL STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2021-07-15 | 2021-07-10 | 2022-06-08 | 2022-07-10 | 2022-07-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31547666 | T2 VOLTA-DESCHUTES 16/357 RPL STRW | 70Y
LC | 121736099 | 016/357 | T2 VOLTA-DESCHUTES 16/357 RPL STRW CMT | TABLEMTN | ETL.8290.POLE.WOOD | 2021-07-15 | 2021-07-10 | 2022-06-13 | 2022-07-10 | 2022-07-10 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31547666 | T2 VOLTA-DESCHUTES 16/357 RPL STRW | 70Y
LC | 121736239 | 091/466 | T2 WV MALIN-ROUND MTN #2 91/466 RPR OPGW | TABLEMTN | ETL.6020.INSL.NCER | 2021-07-15 | 2021-07-15 | 2022-07-11 | 2022-07-15 | 2022-07-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215172 | T2 WV MALIN-ROUND MTN #2 91/466 RPR OPGW | ICS
LC | 121736319 | 082/003C | T2 DI HUMBOLDT-TRINITY 82/3C INS HRDD | EUREKA | ETL.1820.POLE.NWOD | 2021-07-15 | 2021-07-12 | 2022-03-26 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45158949 | T2 DI HUMBOLDT-TRINITY 82/3C INS HRDD | ICW
LC | 121736442 | 077/001 | T2 DI HUMBOLDT-TRINITY 77/1 RPLC INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-15 | 2021-07-12 | 2022-06-02 | 2022-07-12 | 2022-07-12 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547351 | T2 DI HUMBOLDT-TRINITY 77/1 RPLC INSW | 93I
LC | 121736660 | 056/001 | T2 DI HUMBOLDT-TRINITY 56/1 RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-03-29 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45145095 | T2 DI HUMBOLDT-TRINITY 56/1 RPR STRW | ICW
LC | 121736734 | 054/001B | T2 DI HUMBOLDT-TRINITY 054/1B RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2021-07-15 | 2021-07-12 | 2022-06-08 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145285 | T2 DI HUMBOLDT-TRINITY- 54/1A RPR GYWW | ICW
LC | 121736739 | 005/069 | T2 DI BURNS-LONE STAR #1 5/69 RPR GYWW | MOSSLNDG | ETL.6230.POLE.WOOD | 2021-07-15 | 2021-07-12 | 2022-01-13 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44932388 | T2 DI BURNS-LONE STAR #1 5/69 RPR GYWW | ICW
LC | 121736751 | 004/024 | T2 MOSS LANDING-METCALF 4/24 RPL INSS | MOSSLNDG | ETL.6050.INSL | 2021-07-15 | 2021-07-15 | 2022-02-16 | 2022-07-15 | 2022-07-15 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549072 | T2 MOSS LANDING-METCALF RPL INSS 1 TWR | 93K
LC | 121736965 | 084/003 | T2 DI HUMBOLT-TRINITY 084/003R RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-03-25 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45149344 | T2 DI HUMBOLT-TRINITY 084/003R RPR STRW | ICW
LC | 121736967 | 084/003 | T2 DI HUMBOLT-TRINITY 084/003L RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-03-25 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45149344 | T2 DI HUMBOLT-TRINITY 084/003R RPR STRW | ICW
LC | 121737222 | 039/765 | T2 WV HAT CRK #1-WSTWD 39/765 INS GYWW | TABLEMTN | ETL.7030.POLE.NWOD | 2021-07-15 | 2021-07-15 | 2022-08-29 | 2022-07-15 | 2022-07-15 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Guy Wire-Wood | Install | 45147763 | T2 WV HAT CRK #1-WSTWD 39/765 INS GYWW | ICW
LC | 121737231 | 078/003 | T2 DI HUMBOLDT-TRINITY 078/003L RMV BUTT | EUREKA | ETL.1820.POLE.STPS | 2021-07-15 | 2021-07-12 | 2022-05-14 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45148679 | T2 DI HUMBOLDT-TRINITY 078/003L RMV BUTT | ICW
LC | 121737272 | 020/089 | T2 DI PITTSBRG-TESLA #1 20/89 RPL HANGER | CONCORD | ETL.5520.INSL.CERA | 2021-07-15 | 2021-07-12 | 2022-03-11 | 2022-07-12 | 2022-07-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 45084082 | T2 DI PITTSBRG-TESLA #1 20/89 RPL HANGER | ICQ
LC | 121737277 | 008/109 | T3 DI GOLD HILL #1 008/109 RPR HRDW | SACTO | ETL.6950.POLE.WOOD | 2021-07-15 | 2021-07-12 | 2022-04-21 | 2022-01-08 | 2022-01-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45218804 | T3 DI GOLD HILL #1 008/109 RPR HRDW | ICW
LC | 121737296 | 007/068 | T2 DI CTNWD-BNTN #2 7/68L RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-15 | 2021-07-08 | 2022-07-22 | 2022-07-08 | 2022-07-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213263 | T2 DI CTNWD-BNTN #2 7/68L RPR STRW | ICW
LC | 121737297 | 007/068 | T2 DI CTNWD-BNTN #2 7/68R RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-15 | 2021-07-08 | 2022-07-22 | 2022-07-08 | 2022-07-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213264 | T2 DI CTNWD-BNTN #2 7/68R RPR STRW | ICW
LC | 121737298 | 044/181 | T2 DI DIABLO-MIDWAY #3 44/181 RPL HRDT | PISMOBCH | ETL.5980.TOWR | 2021-07-15 | 2021-07-12 | 2022-02-24 | 2022-07-12 | 2022-07-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45073822 | T2 DI DIABLO-MIDWAY #3 44/181 RPL HRDT | ICQ
LC | 121737363 | 020/013 | T2 DI CLEAR LAKE-KONOCTI 20/13 RPR INSW | WILLITS | ETL.6852.POLE.NWOD | 2021-07-15 | 2021-07-12 | 2022-02-02 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Wood | Repair | 45138106 | T2 DI CLEAR LAKE-KONOCTI 20/13 RPR INSW | ICW
LC | 121737407 | 005/046 | T2 WV PARADISE-TABLE MTN 5/46 INS DAMT | TABLEMTN | ETL.4316.INSL.NCER | 2021-07-15 | 2021-07-15 | 2022-02-28 | 2022-07-15 | 2022-07-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install
LC | 121737483 | 005/045 | T2 WV PARADISE-TABLE MTN 5/45 INS DAMT | TABLEMTN | ETL.4316.INSL.NCER | 2021-07-15 | 2021-07-15 | 2022-02-28 | 2022-07-15 | 2022-07-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install
LC | 121737509 | 054/002B | T2 DI HUMBOLDT-TRINITY 054/2B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2021-07-15 | 2021-07-12 | 2022-06-07 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145286 | T2 DI HUMBOLDT-TRINITY 054/2A RPR GYWW | ICW
LC | 121737643 | 004/005 | T2 WV LAYTONVILLE-COVELO 4/5 INS DAMW | LAKEVLLE | ETL.7390.POLE.NWOD | 2021-07-15 | 2021-07-15 | 2021-10-19 | 2022-07-15 | 2022-07-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 44999938 | T2 WV LAYTONVILLE-COVELO 4/5 INS DAMW | ICW
LC | 121737747 | 002/020 | T2 DI PIT #7 TAP 2/20 RMV BUTT | TABLEMTN | ETL.5442.POLE.WDPS | 2021-07-15 | 2021-07-09 | 2022-06-14 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45213835 | T2 DI PIT #7 TAP 2/20 RMV BUTT | ICW
LC | 121737878 | 066/476 | T2 WV BRDGEVLLE-CTTNWD 066/4 RPR FOND | TABLEMTN | ETL.1110.TOWR | 2021-07-15 | 2021-07-15 | 2022-07-25 | 2022-07-15 | 2022-07-15 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45160917 | T2 WV BRDGEVLLE-CTTNWD 066/4 RPR FOND | ICQ
LC | 121738209 | 056/000 | T2 DI HUMBOLDT-TRINITY 56/0 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-03-29 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145094 | T2 DI HUMBOLDT-TRINITY 56/0 RPR GYWW | ICW
LC | 121738211 | 082/004 | T2 DI HUMBOLDT-TRINITY 82/4 RMV BUTT | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-03-26 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45158950 | T2 DI HUMBOLDT-TRINITY 82/4 RMV BUTT | ICW
LC | 121738243 | 080/002 | T2 DI HUMBOLDT-TRINITY 80/02 RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-03-27 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45149125 | T2NT DI HUMBOLDT-TRINITY 80/02 RMV DBRS | ICW
LC | 121738245 | 082/000 | T2 DI HUMBOLDT-TRNTY 82/00 RPR RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-03-26 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45149129 | T2NT EI HUMBOLDT-TRINITY 82/0 RPR GYWW | ICW
LC | 121738249 | 082/000 | T2 DI HUMBOLDT-TRINITY 82/00 RMV DBRS | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-03-26 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45149129 | T2NT EI HUMBOLDT-TRINITY 82/0 RPR GYWW | ICW
LC | 121738284 | 026/001 | T3DI FULTON-HOPLAND-WOOD 26/1 HRDW RPL | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-07-15 | 2021-07-09 | 2021-08-13 | 2022-01-05 | 2022-01-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44913894 | T3DI FULTON-HOPLAND-WOOD 26/1 HRDW RPL | ICW
LC | 121738291 | :007/042 | T3 WV EAGLE ROCK-CORTINA :7/42 INS DAMS | WILLITS | ETL.1470.INSL.CERA | 2021-07-15 | 2021-07-15 | 2022-03-29 | 2022-01-11 | 2022-01-15 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO NTDE | Missing | Damper-Steel | Install | 45149946 | T3 WV EAGLE ROCK-CORTINA :7/42 INS DAMS | ICS
LC | 121738350 | 093/004 | T2 DI HUMBOLDT-TRINITY 093/004 RPR INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-15 | 2021-07-12 | 2022-06-02 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45160727 | T2 DI HUMBOLDT-TRINITY 093/004 RPR INSW | ICW
LC | 121738353 | 012/262 | T2 DI CTTNWD-RED BLUFF 012/262 RPR GYWW | TABLEMTN | ETL.6660.POLE.NWOD | 2021-07-15 | 2021-07-09 | 2022-09-29 | 2022-07-09 | 2022-07-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45242432 | T2 DI CTTNWD-RED BLUFF 012/262 RPR GYWW | ICW
LC | 121738358 | 000/003 | T2 WV CHOWCHILLA-KERCKHOFF 0/3 RPR FOND | FRESNO | ETL.1250.POLE.NWOD | 2021-07-15 | 2021-07-15 | 2022-02-16 | 2022-07-15 | 2022-07-15 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45070450 | T2 WV CHOWCHILLA-KERCKHOFF 0/3 RPR FOND | ICQ
LC | 121738380 | 056/000 | T2 DI HUMBOLDT-TRINITY 56/0 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-03-29 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145094 | T2 DI HUMBOLDT-TRINITY 56/0 RPR GYWW | ICW
LC | 121738382 | 002/000 | T2 DI MENDOCINO-UKIAH 2/0L RPL STRW | WILLITS | ETL.2420.POLE.WDPS | 2021-07-15 | 2021-07-09 | 2022-07-15 | 2022-07-09 | 2022-07-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544735 | T2 EI MENDOCINO-UKIAH 3/1R RPL STRW | 70Y
LC | 121738383 | 002/000 | T2 DI MENDOCINO-UKIAH 2/0R RPL STRW | WILLITS | ETL.2420.POLE.WDPS | 2021-07-15 | 2021-07-09 | 2022-07-15 | 2022-07-09 | 2022-07-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544735 | T2 EI MENDOCINO-UKIAH 3/1R RPL STRW | 70Y
LC | 121738457 | 002/028 | T2 DI PT#5-RD MN #2 2/28L RPL STW CMPLT | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-15 | 2021-07-13 | 2022-06-13 | 2022-07-13 | 2022-07-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547482 | T2 DI PIT #5-ROUND MTN #2 1/18R RPL STRW | 70Y
LC | 121738459 | 002/028 | T2 DI PT#5-RD MN #2 2/28R RPL STW CMPLT | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-15 | 2021-07-13 | 2022-06-13 | 2022-07-13 | 2022-07-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547482 | T2 DI PIT #5-ROUND MTN #2 1/18R RPL STRW | 70Y
LC | 121738464 | 107/004 | T2 DI HMBLDT-TRNTY STEEL 107/4 RMV BUTT | EUREKA | ETL.1820.POLE.STPS | 2021-07-15 | 2021-07-12 | 2022-01-24 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45128329 | T2 DI HMBLDT-TRNTY STEEL 107/4 RMV BUTT | ICW
LC | 121738466 | 092/006 | T2 DI HUMBLDT-TRINITY-WD 92/6 RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-06-07 | 2022-07-12 | 2022-07-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544732 | T2 DI HUMBLDT-TRNITY 85/2 RPL POLE | 70Y
LC | 121738542 | 000/005 | T3 DI FORKS OF THE BUTTE TP 0/5 RPL HRDD | TABLEMTN | ETL.6722.POLE.WOOD | 2021-07-15 | 2021-07-12 | 2022-04-23 | 2022-01-08 | 2022-01-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45212317 | T3 DI FORKS OF THE BUTTE TP 0/5 RPL HRDD | ICW
LC | 121738572 | 074/002 | T2 DI HUMBOLDT-TRINITY 74/2L RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-13 | 2022-04-02 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45147809 | T2 DI HUMBOLDT-TRINITY 74/2L RPR GYWW | ICW
LC | 121738588 | 009/065 | T2 DI MRGA-SAN LNDRO #2 9/65 RPL INSS | CONCORD | ETL.2780.INSL | 2021-07-15 | 2021-07-12 | 2022-04-22 | 2022-07-12 | 2022-07-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31591454 | T2 DI MRGA-SAN LNDRO #2 9/65 RPL INSS | 93K
LC | 121738589 | 009/065 | T2 DI MRG-SN LNDR #1 9/65 RPL INSS CMPLT | CONCORD | ETL.2770.INSL | 2021-07-15 | 2021-07-12 | 2022-05-10 | 2022-07-12 | 2022-07-12 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548202 | T2 DI MRG-SAN LEANDRO #1 RPL INSS 2 TWR | 93K
LC | 121738604 | 073/005 | T2 DI HUMBOLDT-TRINITY 73/05R BACKFILL | EUREKA | ETL.1820.POLE.STPS | 2021-07-15 | 2021-07-12 | 2022-08-12 | 2022-07-12 | 2022-07-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45147801 | T2 DI HUMBOLDT-TRINITY 73/05R BACKFILL | ICW
LC | 121738686 | 106/002 | T2 DI HUMBOLDT-TRINITY SP 106/2 RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2021-07-15 | 2021-07-12 | 2022-01-22 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45128328 | T2 DI HUMBOLDT-TRINITY SP 106/2 RPR INSW | ICW
LC | 121738694 | 006/066 | T2 DI PIT #5-ROUND MTN #1 6/66 RPL HRDD | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-15 | 2021-07-09 | 2022-07-17 | 2022-07-09 | 2022-07-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213265 | T2 DI PIT #5-ROUND MTN #1 6/66 RPL HRDD | ICW
LC | 121738698 | 023/263 | T3 DI IGNACIO-BOLINAS #2 23/263 RPL HRDD | LAKEVLLE | ETL.7180.POLE.WOOD | 2021-07-15 | 2021-07-12 | 2022-09-24 | 2022-01-08 | 2022-01-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45142534 | T3 DI IGNACIO-BOLINAS #2 23/263 RPL HRDD | ICW
LC | 121738707 | 066/004 | T2 DI HUMBOLDT-TRINITY 066/004 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-10-18 | 2022-07-12 | 2022-07-12 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547346 | T2 DI HUMBOLDT-TRINITY 066/004 RPL STRW | 70Y
LC | 121738768 | 003/021 | T3 DI SOBRNTE-"G" #1""TWR X3/21 RPL INSS | CONCORD | ETL.3720.INSL.CERA | 2021-07-15 | 2021-07-13 | 2022-07-25 | 2022-01-09 | 2022-01-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546931 | T3 DI SOBRANTE-""G"" #1 RPL INSS 4TWRS | 93K
LC | 121738769 | 003/021 | T3 DI SOBRANTE G #1 TWR X3/21 RPL HRDT | CONCORD | ETL.3720.INSL.CERA | 2021-07-15 | 2021-07-13 | 2022-07-25 | 2022-01-09 | 2022-01-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 45094456 | T3 DI SOBRANTE G #1 TWR X3/21 RPL HRDT | ICQ
LC | 121738821 | 015/002 | T3 DI DONNELLS-MI-WUK 015/002 INS HRDD | VICTOR | ETL.1400.POLE.WDPS | 2021-07-15 | 2021-07-08 | 2022-04-07 | 2022-01-04 | 2022-01-08 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | Missing | Hardware-Wood | Install | 45122753 | T3 DI DONNELLS-MI-WUK 015/002 INS HRDD | ICW
LC | 121738838 | B019/436 | T2 DI DRM GRSS VLY WMR B19/436 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-07-15 | 2021-07-13 | 2022-07-25 | 2022-07-13 | 2022-07-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31595647 | T3 DI DRM GRAS VLY WMAR 3/79 RPL STRW | 70Y
LC | 121738922 | 003/022 | T3 DI SOBRANTE-"G" #1 003/022 RPL INSS | CONCORD | ETL.3720.INSL.CERA | 2021-07-15 | 2021-07-13 | 2022-07-28 | 2022-01-09 | 2022-01-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546931 | T3 DI SOBRANTE-""G"" #1 RPL INSS 4TWRS | 93K
LC | 121738923 | 008/083 | T2 DI CTTND-BENTON #2 008/083 RPL INSW | TABLEMTN | ETL.6650.INSL.NCER | 2021-07-15 | 2021-07-13 | 2022-06-04 | 2022-07-13 | 2022-07-13 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546829 | T2 DI CTTND-BENTON #2 008/083 RPL INSW | 93I
LC | 121738942 | 051/000B | T2 DI HUMBOLDT-TRINITY 51/00B RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-15 | 2021-07-12 | 2022-04-02 | 2022-07-12 | 2022-07-12 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547344 | T2 DI HMBLDT-TRNTY 051/000A RPL INSW | 93I
LC | 121738946 | 051/000C | T2 DI HUMBOLDT-TRINITY 51/00C RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-15 | 2021-07-12 | 2022-04-02 | 2022-07-12 | 2022-07-12 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547344 | T2 DI HMBLDT-TRNTY 051/000A RPL INSW | 93I
LC | 121738954 | 108/000 | T2 DI HUMBOLDT-TRINITY WP 108/0 RMV STRW | EUREKA | ETL.1820.POLE.STPS | 2021-07-15 | 2021-07-13 | 2022-01-21 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45128331 | T2 DI HUMBOLDT-TRINITY WP 108/0 RMV STRW | ICW
LC | 121738956 | 008/082 | T2 DI PIT #5-RND MT #2 8/82 BUTT CMPLTD | TABLEMTN | ETL.5430.POLE.STPS | 2021-07-15 | 2021-07-09 | 2022-06-15 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45213808 | T2 DI PIT #5-RND MTN #2 8/82 RMV DEBRIS | ICW
LC | 121738983 | 002/044 | T3 DI CNTRVL TBL MTN ORO 2/44 REGRADE CM | TABLEMTN | ETL.6330.POLE.NWOD | 2021-07-15 | 2021-07-13 | 2022-04-04 | 2022-01-09 | 2022-01-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Repair | 45212505 | T3 DI CNTRVL TBL MTN ORO 2/44 REGRADE | ICW
LC | 121739001 | 067/000 | T2 DI HUMBOLDT-TRINITY 67/00L RPL HRDD | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-03-31 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45158942 | T2 EI CTTNWD-HMBLDT 67/0C RPL GWRW | ICW
LC | 121739002 | 067/000 | T2 DI HUMBOLDT-TRINITY 67/00C RPL HRDD | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-03-31 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45158942 | T2 EI CTTNWD-HMBLDT 67/0C RPL GWRW | ICW
LC | 121739003 | 067/000 | T2 DI HUMBOLDT-TRINITY 67/00R RPL HRDD | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-12 | 2022-03-31 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45158942 | T2 EI CTTNWD-HMBLDT 67/0C RPL GWRW | ICW
LC | 121739112 | 001/016 | T2 DI PIT #5-ROUND MTN 1 1/16 RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-15 | 2021-07-09 | 2022-06-16 | 2022-07-09 | 2022-07-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121739118 | 002/000 | T2 DI MENDOCINO-PHILO 2/0 RPR GYWW | WILLITS | ETL.7520.POLE.WDPS | 2021-07-15 | 2021-07-09 | 2022-02-22 | 2022-07-09 | 2022-07-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45142541 | T2 DI MENDOCINO-PHILO 2/0 RPR GYWW | ICW
LC | 121740955 | 008/083 | T2 DI PIT #5-ROUND MTN #1 8/83 GYWW COA | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-16 | 2021-07-12 | 2022-06-21 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45354995 | T2 DI PIT #5-ROUND MTN #1 8/83 GYWW COA | ICW
LC | 121741190 | 079/003 | T2 DI HUMBOLDT-TRINITY 79/3R RPR STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-16 | 2021-07-12 | 2022-06-02 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45158945 | T2 DI HUMBOLDT-TRINITY 79/3R RPR STRW | ICW
LC | 121741223 | 073/370 | T2 DI MALIN-RD MTN #2 73/370 RMV DEBRIS | TABLEMTN | ETL.6020.INSL.NCER | 2021-07-16 | 2021-07-14 | 2022-07-16 | 2022-07-14 | 2022-07-14 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | Debris/Nest/etc. | Conductor-Steel | Remove | 45223890 | T2 DI MALIN-RD MTN #2 73/370 RMV DEBRIS | ICS
LC | 121741239 | 061/003 | T2 DI HUMBOLDT-TRINITY 61/3L RMV LADDER | EUREKA | ETL.1820.POLE.STPS | 2021-07-16 | 2021-07-12 | 2022-03-30 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45145449 | T2NT EI HUMBOLDT-TRINITY 61/3R RMV DBRS | ICW
LC | 121741260 | 061/003 | T2 DI HUMBOLDT-TRINITY 61/3 RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2021-07-16 | 2021-07-12 | 2022-03-30 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45145449 | T2NT EI HUMBOLDT-TRINITY 61/3R RMV DBRS | ICW
LC | 121741296 | 002/026 | T2 DI PIT #5-ROUND MTN #1 2/26 RPL INSS | TABLEMTN | ETL.5420.INSL.CERA | 2021-07-16 | 2021-07-13 | 2022-07-17 | 2022-07-13 | 2022-07-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31607397 | T2 DI PIT #5-ROUND MTN #1 2/25 RPL INSS | 93K
LC | 121741350 | 001/003 | T2 DI MENDOCINO-UKIAH 1/3R RPR STRW | WILLITS | ETL.2420.POLE.WDPS | 2021-07-16 | 2021-07-09 | 2022-07-13 | 2022-07-09 | 2022-07-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45142186 | T2 DI MENDOCINO-UKIAH 1/3R RPR STRW | ICW
LC | 121741356 | 008/080 | T2 DI CTTNWD-BENTON#2 8/80L RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-06-04 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213267 | T2 DI CTTNWD-BENTON#2 8/80 RPR STRW | ICW
LC | 121741357 | 008/080 | T2 DI COTTONWD-BNTN#2 8/80 ANCW RPR | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-06-04 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Anchor-Wood | Repair | 45213268 | T2DI COTTONWD-BENTON#2-WD 8/80 ANCW RPR | ICW
LC | 121741389 | 093/000 | T2 DI HUMBOLDT-TRINITY 93/0 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-16 | 2021-07-12 | 2022-06-03 | 2022-07-12 | 2022-07-12 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547354 | T2 DI HUMBOLDT-TRINITY 93/0 RPL INSW | 93I
LC | 121741430 | 010/178 | T2 DI TEJON-LEBEC 10/178 RPL HRDD | MIDWAY | ETL.9250.POLE.WOOD | 2021-07-16 | 2021-07-14 | 2021-12-17 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44992848 | T2 DI TEJON-LEBEC 10/178 RPL HRDD | ICW
LC | 121741437 | 026/290 | T3 DI IGNACIO-BOLINS #2 26/290 RPL INSW | LAKEVLLE | ETL.7180.INSL.CERA | 2021-07-16 | 2021-07-14 | 2022-06-25 | 2022-01-10 | 2022-01-14 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547356 | T3 DI IGNACIO-BOLINS #2 26/290 RPL INSW | 93I
LC | 121741443 | 073/369 | T2 DI MALIN-RD MTN #2 073/369 RPR FOND | TABLEMTN | ETL.6020.TOWR | 2021-07-16 | 2021-07-14 | 2022-07-19 | 2022-07-14 | 2022-07-14 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45197659 | T2 DI MALIN-RD MTN #2 073/369 RPR FOND | ICQ
LC | 121741501 | 000/009 | T2 DI IGNACIO-BOLINS #1 0/9 RPL HRDD | LAKEVLLE | ETL.7140.POLE.WOOD | 2021-07-16 | 2021-07-14 | 2022-01-13 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45127109 | T2 DI IGNACIO-BOLINS #1 0/9 RPL HRDD | ICW
LC | 121741503 | 000/007 | T3 DI KONOCTI-EAGLE RCK 000/007 INS HRDD | LAKEVLLE | ETL.6861.POLE.NWOD | 2021-07-16 | 2021-07-13 | 2022-02-14 | 2022-01-09 | 2022-01-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | Missing | Hardware-Wood | Install | 45128110 | T3 DI KONOCTI-EAGLE RCK 000/007 INS HRDD | ICW
LC | 121741545 | 004/049 | T2 DI HLSDL JCT-HF MN BY 4/49L RPR GYWW | METCALF | ETL.7060.POLE.WDPS | 2021-07-16 | 2021-07-14 | 2022-02-22 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45150544 | T2 DI HLSDL JCT-HF MN BY 4/49L RPR GYWW | ICW
LC | 121741588 | 010/000 | T2 DI MELONES-CURTIS 010/000R RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-11-03 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45162138 | T2 DI MELONES-CURTIS 010/000R RPR STRW | ICW
LC | 121741600 | 011/112C | T3 DI GRN VLY CMP EVRS 011/112C RPL INSW | MOSSLNDG | ETL.1710.INSL.NCER | 2021-07-16 | 2021-07-14 | 2022-04-05 | 2022-01-10 | 2022-01-14 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE ACCM COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579487 | T3 DI GRN VLY CMP EVRS 011/112C RPL INSW | 93I
LC | 121741613 | 011/112B | T3 DI GRN VLY CMP EVRS 011/112B RPL INSW | MOSSLNDG | ETL.1710.INSL.NCER | 2021-07-16 | 2021-07-14 | 2022-04-05 | 2022-01-10 | 2022-01-14 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579487 | T3 DI GRN VLY CMP EVRS 011/112C RPL INSW | 93I
LC | 121741676 | 008/005 | T2 DI MELONES-CURTIS-WP STR 8/5 RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-08-03 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163100 | T2 DI MELONES-CURTIS-WP STR 8/5 RPR STRW | ICW
LC | 121741681 | 010/000 | T2 DI MELONES-CURTIS 010/000L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-11-03 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163103 | T2 DI MELONES-CURTIS 010/000L RPR STRW | ICW
LC | 121741714 | 009/109 | T2 DI WP-VALLEY SPRINGS 09/109 RPL STRW | VICTOR | ETL.8350.POLE.WOOD | 2021-07-16 | 2021-07-14 | 2022-05-22 | 2022-07-14 | 2022-07-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31579997 | T3 DI WP-VALLEY SPRINGS 0/2 RPL STRW | 70Y
LC | 121741741 | 011/112A | T3 DI GRN VLY CMP EVRS 011/112A RPL INSW | MOSSLNDG | ETL.1710.INSL.NCER | 2021-07-16 | 2021-07-14 | 2022-04-05 | 2022-01-10 | 2022-01-14 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579487 | T3 DI GRN VLY CMP EVRS 011/112C RPL INSW | 93I
LC | 121741745 | 000/004 | T3 DI DRM GRSS VLLY WMR 000/004 RPR IBWW | SACTO | ETL.6760.INSL.NCER | 2021-07-16 | 2021-07-13 | 2022-04-23 | 2022-01-09 | 2022-01-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45194337 | T3 DI DRM GRSS VLLY WMR 000/004 RPR IBWW | ICW
LC | 121741784 | 095/000 | T2 DI HUMBOLDT-TRINITY WP 95/0L RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-16 | 2021-07-12 | 2022-06-02 | 2022-07-12 | 2022-07-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31591951 | T2 DI HUMBOLDT-TRINITY WP 95/0L RPL STRW | 70Y
LC | 121741796 | 083/000 | T2 DI HMBOLDT-TRTY STL PL X83/0 RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2021-07-16 | 2021-07-12 | 2022-03-25 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45149136 | T2 DI HMBOLDT-TRTY STL PL X83/0 RPR GYWW | ICW
LC | 121741827 | 004/069A | T3 DI SISQUOC-GAREY 4/69A RPL HRDD | PISMOBCH | ETL.3690.POLE.WOOD | 2021-07-16 | 2021-07-14 | 2022-02-08 | 2022-01-10 | 2022-01-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE ACCL COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45069433 | T3 DI SISQUOC-GAREY 4/69A RPL HRDD | ICW
LC | 121741914 | 005/052 | T2 DI HLSD JCT-HF MN BY 5/52L RPR GYWW | METCALF | ETL.7060.POLE.WDPS | 2021-07-16 | 2021-07-14 | 2022-04-08 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45150547 | T2 DI HLSD JCT-HF MN BY 5/52L RPR GYWW | ICW
LC | 121742263 | 073/004 | DI T2 HUMBOLDT-TRINITY 073/004 RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2021-07-16 | 2021-07-12 | 2022-03-31 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45147777 | DI T2 HUMBOLDT-TRINITY 073/004 RPR GYWW | ICW
LC | 121742267 | 010/093 | T2 DI CTTNWD-BENTON 2 10/93R RPR GYWW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-06-04 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213269 | T2 DI CTTNWD-BENTON 2 10/93R RPR GYWW | ICW
LC | 121742294 | 011/002 | T2 DI MELONES-CURTIS 11/2L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-08-08 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163104 | T2 DI MELONES-CURTIS 11/2L RPR STRW | ICW
LC | 121742325 | 000/009 | T2 DI MLNES-CURTIS-WD PL 0/9L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-11-29 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163105 | T2 DI MLNES-CURTIS-WD PL 0/9 RPR STRW | ICW
LC | 121742330 | 020/090 | T2 DI PITTSBURG-TESLA #1 20/90 COMPLETE | CONCORD | ETL.5510.TOWR | 2021-07-16 | 2021-07-12 | 2022-04-18 | 2022-07-12 | 2022-07-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190833 | T2 DI PITTSBURG-TESLA #1 20/90 RPR FOND | ICQ
LC | 121742336 | 004/069C | T3 DI SISQUOC-GAREY4/69C RPL HRDD | PISMOBCH | ETL.3690.POLE.WOOD | 2021-07-16 | 2021-07-14 | 2022-02-08 | 2022-01-10 | 2022-01-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45069434 | T3 DI SISQUOC-GAREY4/69C RPL HRDD | ICW
LC | 121742367 | B023/531 | T3 DI DRM GRSS VLY WMR B023/531 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2021-07-16 | 2021-07-13 | 2022-04-15 | 2022-01-09 | 2022-01-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45193830 | T3 DI DRM GRSS VLY WMR B023/531 RPR STRW | ICW
LC | 121742368 | B023/531 | T3 DI DRM GRSS VLY WMR B023/531 RPL HRDD | SACTO | ETL.6760.POLE.WOOD | 2021-07-16 | 2021-07-13 | 2022-04-15 | 2022-01-09 | 2022-01-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45193612 | T3 DI DRM GRSS VLY WMR B023/531 RPL HRDD | ICW
LC | 121742391 | 054/000 | T2 DI HUMBOLT-TRINITY 54/0 FL HL COMPLT | EUREKA | ETL.1820.POLE.STPS | 2021-07-16 | 2021-07-13 | 2022-05-11 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Repair | 45145283 | T2 DI HUMBOLT-TRINITY 54/0 FILL HOLE | ICW
LC | 121742441 | 000/010 | T3 DI KONOCTI-EAGLE RK 000/10 REPLUMB | LAKEVLLE | ETL.6861.INSL | 2021-07-16 | 2021-07-13 | 2022-02-12 | 2022-01-09 | 2022-01-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45128112 | T3 DI KONOCTI-EAGLE RK 000/10 REPLUMB | ICW
LC | 121742485 | 108/003 | T2 DI HUMBOLDT-TRINITY 108/3L RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2021-07-16 | 2021-07-12 | 2022-01-22 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45128333 | T2 DI HUMBOLDT-TRINITY RPR GYWW | ICW
LC | 121742584 | 006/144 | T2 DI DEL MONTE-VIEJO 006/144 RMV BUTT | MOSSLNDG | ETL.6710.POLE.WOOD | 2021-07-16 | 2021-07-13 | 2022-03-03 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45122535 | T2 DI DEL MONTE-VIEJO 006/144 RMV BUTT | ICW
LC | 121742588 | 003/023 | T3 DI SOBRANTE-"G" #1 003/023 RPL INSS | CONCORD | ETL.3720.INSL.CERA | 2021-07-16 | 2021-07-13 | 2022-07-28 | 2022-01-09 | 2022-01-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546931 | T3 DI SOBRANTE-""G"" #1 RPL INSS 4TWRS | 93K
LC | 121742750 | 065/002 | T2 DI HUMBOLDT-TRINITY 65/2L BRKN BOND | EUREKA | ETL.1820.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-06-05 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Wood | Install | 45145523 | T2NT EI HUMBOLDT-TRINITY 65/2R INS MRKW | ICW
LC | 121742876 | 080/001 | T2 DI HUMBLDT-TRINITY WP 80/1 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-16 | 2021-07-12 | 2022-03-27 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45158947 | T2 DI HUMBLDT-TRINITY WP 80/1 RPR GYWW | ICW
LC | 121742935 | 002/014 | T3 DI SAN RAMON-MORAGA 002/014 RPR SHLS | CONCORD | ETL.5660.INSL.CERA | 2021-07-16 | 2021-07-12 | 2022-05-12 | 2022-01-08 | 2022-01-12 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45181106 | T3 DI SAN RAMON-MORAGA 002/014 RPR SHLS | ICS
LC | 121743107 | 000/001 | T3 DI DRUM-RIO OSO #2 00/01 INST HRDT | SACTO | ETL.1430.TOWR | 2021-07-16 | 2021-07-13 | 2021-10-28 | 2022-01-09 | 2022-01-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 44945144 | T3 DI DRUM-RIO OSO #2 00/01 INST HRDT | ICQ
LC | 121743170 | 000/001 | T3 DI DRUM-RIO OSO #2 00/01 RPR FOND | SACTO | ETL.1430.TOWR | 2021-07-16 | 2021-07-13 | 2021-10-28 | 2022-01-09 | 2022-01-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44945146 | T3 DI DRUM-RIO OSO #2 00/01 RPR FOND | ICQ
LC | 121743184 | 012/000 | T2 DI MELONES-CURTIS 12/0L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-08-10 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163107 | T2 DI MELONES-CURTIS 12/0L RPR STRW | ICW
LC | 121743185 | 012/000 | T2 DI MELONES-CURTIS 12/0R RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-08-10 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163108 | T2 DI MELONES-CURTIS 12/0R RPR STRW | ICW
LC | 121743212 | 065/004 | T2 DI HUMBOLDT-TRINITY 65/4L RPR WDPKR | EUREKA | ETL.1820.POLE.WDPS | 2021-07-16 | 2021-07-12 | 2022-06-09 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45145524 | T2 DI HUMBOLDT-TRINITY 65/4L RPR WDPKR | ICW
LC | 121743313 | 013/002 | T2 DI MELONES-CURTIS 13/02L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-11-03 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163109 | T2 DI MELONES-CURTIS 13/02L RPR STRW | ICW
LC | 121743375 | 010/005 | T2 DI MELONES-CURTIS 010/005L RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-11-02 | 2022-07-13 | 2022-07-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579811 | T2 DI MELONES-CURTIS 3/7 RPL STRW | 70Y
LC | 121743394 | 001/012 | T2 DI PIT #6 TAP-WP STR 1/12L RPL STRW | TABLEMTN | ETL.5441.POLE.WDPS | 2021-07-16 | 2021-07-14 | 2022-06-21 | 2022-07-14 | 2022-07-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545615 | T2 PIT #6 TAP-WOOD 1/14 RPL POLE | 70Y
LC | 121743410 | 010/005 | T2 DI MELONES-CURTIS 010/005R RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-11-02 | 2022-07-13 | 2022-07-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579811 | T2 DI MELONES-CURTIS 3/7 RPL STRW | 70Y
LC | 121743497 | 001/027 | T3 DI MIDDLE FORK #1 1/27 RPR STRW | SACTO | ETL.8405.POLE.WOOD | 2021-07-16 | 2021-07-15 | 2021-10-20 | 2022-01-11 | 2022-01-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45017963 | T3 DI MIDDLE FORK #1 1/27 RPR STRW | ICW
LC | 121743579 | 008/081 | T2 DI COTTONWOOD-BNTN #2 8/81R RPL HRDD | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-06-04 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213270 | T2 DI COTTONWOOD-BENTON #2 8/81 RPL HRDD | ICW
LC | 121743620 | 013/103A | T2 DI CARIBOU-TBL MTN 013/103A RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2021-07-16 | 2021-07-12 | 2022-06-23 | 2022-07-12 | 2022-07-12 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45212455 | T2 DI CARIBOU-TBL MTN 013/103A RPR GYWS | ICS
LC | 121743643 | 002/023 | T2 DI PT #5-RD MN #2 2/23 RPL STRW CMPLT | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-06-11 | 2022-07-13 | 2022-07-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547482 | T2 DI PIT #5-ROUND MTN #2 1/18R RPL STRW | 70Y
LC | 121743826 | 073/002AA | T2 DI HBOLDT-TRITY 73/2AA RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-16 | 2021-07-12 | 2022-04-02 | 2022-07-12 | 2022-07-12 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547352 | T2 DI HUMBOLDT-TRINITY 073/002A RPL INSW | 93I
LC | 121743860 | 095/007 | T2 DI HUMBOLDT-TRINITY 095/007 RPL HRDW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-16 | 2021-07-12 | 2022-03-31 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45160745 | T2 DI HUMBOLDT-TRINITY 095/007 RPL HRDW | ICW
LC | 121743864 | 099/002 | T2 DI HUMBOLDT-TRINITY 99/02 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-16 | 2021-07-12 | 2022-06-06 | 2022-07-12 | 2022-07-12 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547355 | T2 DI HUMBOLDT-TRINITY 99/02 RPL INSW | 93I
LC | 121744085 | 008/096 | T3 DI GREEN VLLY-CMP EVRS 8/96 RPL INSW | MOSSLNDG | ETL.1710.INSL.CERA | 2021-07-16 | 2021-07-14 | 2022-04-24 | 2022-01-10 | 2022-01-14 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579487 | T3 DI GRN VLY CMP EVRS 011/112C RPL INSW | 93I
LC | 121744218 | 063/003C | T2 DI HUMBOLDT-TRINITY 63/3C RPL INSW | EUREKA | ETL.1820.INSL.NCER | 2021-07-16 | 2021-07-15 | 2022-10-18 | 2022-07-15 | 2022-07-15 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547345 | T2 DI HUMBOLT-TRINITY 63/3 RPL INSW | 93I
LC | 121744228 | :015/081 | T2 DI CZY HS CNYN-SLS-SD :15/81 RPR STRT | MOSSLNDG | ETL.2900.TOWR | 2021-07-16 | 2021-07-13 | 2021-11-05 | 2022-07-13 | 2022-07-13 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45000262 | T2 DI CZY HS CNYN-SLS-SD :15/81 RPR STRT | ICQ
LC | 121744271 | 063/003C | T2 DI HMBLDT-TRNTY 63/3C RPR GYWW COA | EUREKA | ETL.1820.POLE.WOOD | 2021-07-16 | 2021-07-15 | 2022-10-18 | 2022-07-15 | 2022-07-15 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145454 | T2 DI HUMBOLDT-TRINITY 63/3C RPR GYWW | ICW
LC | 121744276 | 000/002 | T2 DI MELONES-CURTIS 00/02L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-11-30 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163113 | T2 DI MELONES-CURTIS 00/02L RPR STRW | ICW
LC | 121744278 | 000/002 | T2 DI MELONES-CURTIS 0/2R RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-11-30 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163114 | T2 DI MELONES-CURTIS 0/2R RPR STRW | ICW
LC | 121744338 | :000/002 | T2 DI PIT #3-PIT #1 :0/2 RPR FOND | TABLEMTN | ETL.5400.TOWR | 2021-07-16 | 2021-07-15 | 2022-07-29 | 2022-07-15 | 2022-07-15 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195478 | T2NT DI PIT #3-PIT #1 :0/2 RPR FOND | ICQ
LC | 121744402 | 006/087 | T3 DI MIDDLE FORK #1 6/87 RPL HRDW | SACTO | ETL.8405.POLE.WOOD | 2021-07-16 | 2021-07-15 | 2022-08-04 | 2022-01-11 | 2022-01-15 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44944239 | T3 DI MIDDLE FORK #1 6/87 RPL HRDW | ICW
LC | 121744442 | 012/003 | T2 DI OAKHURST TAP NCINSUL 12/3 RPL INSW | FRESNO | ETL.1252.INSL.NCER | 2021-07-16 | 2021-07-14 | 2022-03-30 | 2022-07-14 | 2022-07-14 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579297 | T2 DI OAKHURST TAP NCINSUL 12/3 RPL INSW | 93I
LC | 121744485 | 012/003 | T2 DI OAKHURST TAP SP STR 12/3 RPR GYWW | FRESNO | ETL.1252.POLE.STPS | 2021-07-16 | 2021-07-14 | 2022-03-30 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45068098 | T2 DI OAKHURST TAP SP STR 12/3 RPR GYWW | ICW
LC | 121744497 | 013/001 | T2 DI MELONES-CURTIS 13/01R RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-11-03 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163401 | T2 DI MELONES-CURTIS 13/01R RPR STRW | ICW
LC | 121744499 | 013/001 | T2 DI MELONES-CURTIS 13/01L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-11-03 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163402 | T2 DI MELONES-CURTIS 13/01L RPR STRW | ICW
LC | 121744570 | 004/043 | T2 DI PIT #5-ROUND MTN #2 4/43L RPL STRW | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-16 | 2021-07-14 | 2022-06-14 | 2022-07-14 | 2022-07-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547482 | T2 DI PIT #5-ROUND MTN #2 1/18R RPL STRW | 70Y
LC | 121744581 | 002/058 | T3 DI BURNS-LNE STAR #2 002/058 RPL HRDD | MOSSLNDG | ETL.6240.POLE.WOOD | 2021-07-16 | 2021-07-13 | 2022-02-02 | 2022-01-09 | 2022-01-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45166610 | T3 DI BURNS-LNE STAR #2 002/058 RPL HRDD | ICW
LC | 121744589 | 005/086 | T2 DI COLGATE-PALERMO 005/086 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2021-07-16 | 2021-07-15 | 2022-05-18 | 2022-07-15 | 2022-07-15 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31546828 | T2 DI COLGATE-PALERMO 005/086 RPL STRW | 70Y
LC | 121744631 | 002/025 | T2 DI PIT #5-ROUND MTN #1 2/25 RPL INSS | TABLEMTN | ETL.5420.INSL.CERA | 2021-07-16 | 2021-07-14 | 2022-07-17 | 2022-07-14 | 2022-07-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31607397 | T2 DI PIT #5-ROUND MTN #1 2/25 RPL INSS | 93K
LC | 121744639 | 010/002 | T2 DI MELONES-CURTIS 010/002R RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-14 | 2022-08-05 | 2022-07-14 | 2022-07-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163403 | T2 DI MELONES-CURTIS 010/002R RPR STRW | ICW
LC | 121744761 | 010/002 | T2 DI MELONES-CURTIS 010/002L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-14 | 2022-08-05 | 2022-07-14 | 2022-07-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163404 | T2 DI MELONES-CURTIS 010/002L RPR STRW | ICW
LC | 121744783 | 063/003A | T2 DI HUMBOLDT-TRINITY 63/3A RPL INSW | EUREKA | ETL.1820.INSL.NCER | 2021-07-16 | 2021-07-15 | 2022-10-18 | 2022-07-15 | 2022-07-15 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547345 | T2 DI HUMBOLT-TRINITY 63/3 RPL INSW | 93I
LC | 121744912 | 005/008 | T3 DI KONOCTI-EAGLE ROCK 5/8 RPL STRW | WILLITS | ETL.6861.POLE.WOOD | 2021-07-16 | 2021-07-13 | 2022-02-11 | 2022-01-09 | 2022-01-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31547359 | T3 DI KONOCTI-EAGLE ROCK 5/8 RPL STRW | 70Y
LC | 121744921 | 011/002 | T2 DI MNDCN WLTS FT BRG 11/2 FILL HOLE | WILLITS | ETL.7550.POLE.NWOD | 2021-07-16 | 2021-07-14 | 2022-08-23 | 2022-07-14 | 2022-07-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45145768 | T2 DI MNDCN WLTS FT BRG 11/2 FILL HOLE | ICW
LC | 121744923 | 020/552 | T3 DI COLGATE-ALLEGHANY 020/552 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2021-07-16 | 2021-07-13 | 2022-06-14 | 2022-01-09 | 2022-01-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45224629 | T3 DI COLGATE-ALLEGHANY 020/552 RPR STRW | ICW
LC | 121744997 | 002/027 | T2 DI PT #5-RD MN #2 2/27 RMV DBRS CMPLT | TABLEMTN | ETL.5430.POLE.STPS | 2021-07-16 | 2021-07-13 | 2022-06-15 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45213805 | T2 DI PIT #5-RND MTN #2 2/27 RMV DEBRIS | ICW
LC | 121745012 | 092/003 | T2 DI HUMBOLDT-TRINITY SP 92/3R RE-GRADE | EUREKA | ETL.1820.POLE.STPS | 2021-07-16 | 2021-07-12 | 2022-06-03 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45160722 | T2 DI HUMBOLDT-TRINITY SP 92/3R REGRADE | ICW
LC | 121745110 | 001/023 | T3 DI CENTERVILLE-TBLE MTN 1/23 RPR HRDW | TABLEMTN | ETL.6330.POLE.WOOD | 2021-07-16 | 2021-07-15 | 2022-08-16 | 2022-01-11 | 2022-01-15 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45212506 | T3 DI CENTERVILLE-TBLE MTN 1/23 RPR HRDW | ICW
LC | 121745165 | 024/007 | T2 DI MENDCN-WLLTS-FTBG 24/7 RPR WDPKR | WILLITS | ETL.7550.POLE.WOOD | 2021-07-16 | 2021-07-14 | 2022-05-20 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45148037 | T2 DI MENDCN-WLLTS-FTBG 24/7 RPR WDPKR | ICW
LC | 121745167 | 000/009 | T3 DI KONOCTI-EAGLE RK 000/009 RPL HRDD | LAKEVLLE | ETL.6861.POLE.WOOD | 2021-07-16 | 2021-07-13 | 2022-02-12 | 2022-01-09 | 2022-01-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45128111 | T3 DI KONOCTI-EAGLE RK 000/009 RPL HRDD | ICW
LC | 121745223 | 002/014B | T3 DI KANAKA TAP 002/014B RPR STRW | TABLEMTN | ETL.4223.POLE.WOOD | 2021-07-16 | 2021-07-14 | 2022-06-03 | 2022-01-10 | 2022-01-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45212482 | T3 DI KANAKA TAP 002/014B RPR STRW | ICW
LC | 121745268 | 002/014C | T3 DI KANAKA TAP-WOOD 2/14C RPR STRW | TABLEMTN | ETL.4223.POLE.WOOD | 2021-07-16 | 2021-07-14 | 2022-06-03 | 2022-01-10 | 2022-01-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45212483 | T3 DI KANAKA TAP-WOOD 2/14C RPR STRW | ICW
LC | 121745269 | 005/012 | T3 DI KONOCTI-EAGLE ROCK 5/12 RMV VEG | WILLITS | ETL.6861.POLE.WOOD | 2021-07-16 | 2021-07-13 | 2022-02-24 | 2022-01-09 | 2022-01-13 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121745441 | 064/000C | T2 DI HUMBOLDT-TRINITY 64/0C RPR CNDW | EUREKA | ETL.1820.POLE.NWOD | 2021-07-16 | 2021-07-15 | 2022-06-05 | 2022-07-15 | 2022-07-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45145456 | T2NT DI HUMBOLT-TRINITY 064/0B INS MRKW | ICW
LC | 121745442 | 037/002 | T2 DI MENDCN-WLLTS-FTBG 37/2 INS HRDW | WILLITS | ETL.7550.POLE.NWOD | 2021-07-16 | 2021-07-14 | 2022-05-15 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45148606 | T2NT DI MENDCN-WLLTS-FTBG 37/2 RMV BUTT | ICW
LC | 121745445 | 017/403 | T2 DI DRM GRSS VLY WMR 017/403 RPL HRDD | SACTO | ETL.6760.POLE.WOOD | 2021-07-16 | 2021-07-13 | 2022-06-29 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45193831 | T2 DI DRM GRSS VLY WMR 017/403 RPL HRDD | ICW
LC | 121745503 | 003/065 | T3 DI BURNS-LONE STAR #2 3/65 REFRAME | MOSSLNDG | ETL.6240.POLE.WOOD | 2021-07-16 | 2021-07-13 | 2022-02-04 | 2022-01-09 | 2022-01-13 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31578780 | T3 DI BURNS-LONE STAR #2 3/65 REFRAME | 93E
LC | 121745535 | 012/002 | T2 DI OAKHURST TAP 12/2 RPL INSW | FRESNO | ETL.1252.INSL.NCER | 2021-07-16 | 2021-07-14 | 2022-03-27 | 2022-07-14 | 2022-07-14 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589244 | T3 DI OAKHURST TAP 017/009 RPL INSW | 93I
LC | 121745539 | 006/055BA | T2 DI PRDS-TBLE MTN 006/055BA RPR GYWW | TABLEMTN | ETL.4316.POLE.NWOD | 2021-07-16 | 2021-07-14 | 2022-02-25 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45196973 | T2 DI PRDS-TBLE MTN 006/055BA RPR GYWW | ICW
LC | 121745630 | 006/055BA | T2 DI PRDS-TBLE MTN 6/55BA RPL HRDD | TABLEMTN | ETL.4316.POLE.NWOD | 2021-07-16 | 2021-07-14 | 2022-02-25 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 121745632 | C026/102 | T2 DI MOSS LNDG-CBRN C026/102 RPR INSS | MOSSLNDG | ETL.5330.INSL | 2021-07-16 | 2021-07-14 | 2022-08-04 | 2022-07-14 | 2022-07-14 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45121222 | T2 DI MOSS LNDG-CBRN C026/102 RPR INSS | ICS
LC | 121745635 | 006/055BC | T2 DI PRDS-TBLE MTN 6/55BC RPL HRDD | TABLEMTN | ETL.4316.POLE.NWOD | 2021-07-16 | 2021-07-14 | 2022-02-25 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45199957 | T2 DI PRDS-TBLE MTN 6/55BC RPL HRDD | ICW
LC | 121745711 | 007/005 | T2 DI LYTNVLLE-COVELO 7/5 RPR GYWW | WILLITS | ETL.7390.POLE.WOOD | 2021-07-16 | 2021-07-13 | 2022-06-02 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45000045 | T2 DI LYTNVLLE-COVELO 7/5 RPR GYWW | ICW
LC | 121745712 | 007/005 | T2 DI LYTNVLLE-COVELO 7/5 RPR WDPKR | WILLITS | ETL.7390.POLE.WOOD | 2021-07-16 | 2021-07-13 | 2022-06-02 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45000046 | T2 DI LYTNVLLE-COVELO 7/5 RPR WDPKR | ICW
LC | 121745730 | 004/053 | T2 DI PIT #5-RD MTN #2 4/53 COMPLETE | TABLEMTN | ETL.5430.INSL.CERA | 2021-07-16 | 2021-07-14 | 2022-06-14 | 2022-07-14 | 2022-07-14 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547483 | T2 DI PIT #5-ROUND MTN #2 4/51 RPL INS | 93I
LC | 121745790 | 010/085 | T2 EL DRD-MSSR FLT #2 10/85 RMV BUTT | SACTO | ETL.1540.POLE.NWOD | 2021-07-16 | 2021-07-16 | 2022-05-20 | 2022-07-16 | 2022-07-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45219375 | T2 EL DRD-MSSR FLT #2 10/85 RMV BUTT | ICW
LC | 121745803 | 017/399 | T2 DI DRUM-GRSS VLLY WMR 17/399 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-07-16 | 2021-07-13 | 2022-06-29 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45193832 | T2 DI DRUM-GRSS VLLY WMR 17/399 RPR GYWW | ICW
LC | 121745804 | 017/399 | T2 DI DRUM-GRSS VLLY WMR 17/399 RMV BUTT | SACTO | ETL.6760.POLE.WOOD | 2021-07-16 | 2021-07-13 | 2022-01-17 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45128095 | T2 DI DRUM-GRSS VLLY WMR 17/399 RMV BUTT | ICW
LC | 121746176 | 004/043 | T2 DI PIT #5-RND MTN #1 004/043 RPL INSW | TABLEMTN | ETL.5420.INSL.CERA | 2021-07-16 | 2021-07-14 | 2022-07-17 | 2022-07-14 | 2022-07-14 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31601366 | T2 DI PIT #5-RND MTN #1 004/043 RPL INSW | 93I
LC | 121746309 | 008/001 | T2 DI MELONES-CURTIS 008/001(L) RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-11-15 | 2022-07-13 | 2022-07-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31599819 | T2 DI MELONES-CURTIS 008/001(R) RPL STRW | 70Y
LC | 121746326 | 019/133 | T2 DI CARIBOU-TABLE MTN 19/133 INST HRDT | TABLEMTN | ETL.4440.TOWR | 2021-07-16 | 2021-07-13 | 2022-07-19 | 2022-07-13 | 2022-07-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45159366 | T2 DI CARIBOU-TABLE MTN 19/133 INST HRDT | ICQ
LC | 121746383 | 003/020 | T3 DI SOBRANTE-""G"" #1 3/20 RPL INSS | CONCORD | ETL.3720.INSL.CERA | 2021-07-16 | 2021-07-13 | 2022-07-25 | 2022-01-09 | 2022-01-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546931 | T3 DI SOBRANTE-""G"" #1 RPL INSS 4TWRS | 93K
LC | 121746385 | 003/020 | T3 DI SOBRANTE-""G"" #1 3/20 RPL HRDT | CONCORD | ETL.3720.TOWR | 2021-07-16 | 2021-07-13 | 2022-07-25 | 2022-01-09 | 2022-01-13 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45094458 | T3 DI SOBRANTE-""G"" #1 3/20 RPL HRDT | ICQ
LC | 121746450 | 008/001 | T2 DI MELONES-CURTIS 008/001(R) RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-11-15 | 2022-07-13 | 2022-07-13 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31599819 | T2 DI MELONES-CURTIS 008/001(R) RPL STRW | 70Y
LC | 121746521 | 008/006 | T2 DI MELONES-CURTIS WP STR 8/6 RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2022-08-04 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163415 | T2 DI MELONES-CURTIS WP STR 8/6 RPR STRW | ICW
LC | 121746669 | 000/018 | T3 DI BRNS-LONE STR #2 000/018 RPL STRW | MOSSLNDG | ETL.6240.POLE.WOOD | 2021-07-16 | 2021-07-15 | 2022-02-06 | 2022-01-11 | 2022-01-15 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31578781 | T3 DI BRNS-LONE STR #2 000/018 RPL STRW | 70Y
LC | 121746683 | 022/204 | T2 DI UKHPLND-CLVRDHPLND 22/204 RMV BUTT | LAKEVLLE | ETL.4050.POLE.WDPS | 2021-07-16 | 2021-07-14 | 2022-01-29 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45137839 | T2 DI UKHPLND-CLVRDHPLND 22/204 RMV BUTT | ICW
LC | 121746697 | 006/034 | T2 DI BRENTWOOD-KELSO 6/34 RMV NEST | CONCORD | ETL.4410.TOWR | 2021-07-16 | 2021-07-15 | 2022-01-09 | 2022-07-15 | 2022-07-15 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45079055 | T2 DI BRENTWOOD-KELSO 6/34 RMV NEST | ICS
LC | 121746699 | 010/053 | T2 DI CTR CST-DLT SCG YRD 10/53 RPL INSS | CONCORD | ETL.4490.INSL | 2021-07-16 | 2021-07-15 | 2022-02-14 | 2022-07-15 | 2022-07-15 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31552145 | DI CNTRA CSTA DLTA RPL INSS. 5TWRS | 93K
LC | 121746930 | 010/053 | T2 DI CTR CST-DLT SCG YRD 10/53 RPL HRDT | CONCORD | ETL.4490.INSL | 2021-07-16 | 2021-07-15 | 2022-02-14 | 2022-07-15 | 2022-07-15 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 45084084 | T2 DI CTR CST-DLT SCG YRD 10/53 RPL HRDT | ICQ
LC | 121747006 | 004/044 | T2 DI PIT #5-RND MTN #1 004/044 RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-16 | 2021-07-14 | 2022-07-17 | 2022-07-14 | 2022-07-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213271 | T2 DI PIT #5-RND MTN #1 004/044 RPR STRW | ICW
LC | 121747007 | 004/044 | T2 DI PIT #5-RND MTN #1 004/044 RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-16 | 2021-07-14 | 2022-07-17 | 2022-07-14 | 2022-07-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213272 | T2 DI PIT #5-RND MTN #1 004/044 RPR STRW | ICW
LC | 121747037 | 049/427 | T2 DI PIT #1-CTNWD 49/427 INST HRDS | TABLEMTN | ETL.5390.POLE.STPS | 2021-07-16 | 2021-07-14 | 2022-07-23 | 2022-07-14 | 2022-07-14 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Missing | Hardware-Steel | Install | 45166851 | T2 DI PIT #1-CTNWD 49/427 INST HRDS | ICS
LC | 121747152 | 016/108A | T3 DI METCLF-GRN VLLY 16/108A RPL HRDW | MOSSLNDG | ETL.2540.POLE.NWOD | 2021-07-16 | 2021-07-14 | 2022-07-13 | 2022-01-10 | 2022-01-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213306 | T3 DI METCLF-GRN VLLY 16/108A RPL HRDW | ICW
LC | 121747163 | 095/010 | T2 DI HUMBOLDT-TRINITY 95/10L RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-07-16 | 2021-07-15 | 2022-03-25 | 2022-07-15 | 2022-07-15 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 121747165 | 095/010 | T2 DI HUMBOLDT-TRINITY 95/10C RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-07-16 | 2021-07-15 | 2022-03-25 | 2022-07-15 | 2022-07-15 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 121747197 | 012/059C | T2 DI FULTON-PUEBLO 12/59C RPR INSW | LAKEVLLE | ETL.1600.POLE.NWOD | 2021-07-16 | 2021-07-14 | 2022-02-26 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45142251 | T2 DI FULTON-PUEBLO 12/59C RPR INSW | ICW
LC | 121747246 | 001/047 | T2 DI SPAULDING-SUMMIT 1/47 RPR IBWW | SACTO | ETL.8060.POLE.WOOD | 2021-07-16 | 2021-07-16 | 2022-09-26 | 2022-07-16 | 2022-07-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45224497 | T2 DI SPAULDING-SUMMIT 1/47 RPR IBWW | ICW
LC | 121747317 | 002/025 | T2 DI CHRISTIE-WILLOW PASS 2/25 RPR STRW | CONCORD | ETL.6370.POLE.WOOD | 2021-07-16 | 2021-07-14 | 2022-06-01 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45181062 | T2 DI CHRISTIE-WILLOW PASS 2/25 RPR STRW | ICW
LC | 121747353 | 001/012 | T2 DI PIT #5-ROUND MTN #1 1/12L RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-16 | 2021-07-14 | 2022-06-22 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213273 | T2 DI PIT #5-ROUND MTN #1 1/12 RPR STRW | ICW
LC | 121747372 | 008/114 | T3 DI MIDDLEFORK #1 8/114 RPR JUMW | SACTO | ETL.8405.POLE.WOOD | 2021-07-16 | 2021-07-16 | 2022-08-07 | 2022-01-12 | 2022-01-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Jumper-Wood | Repair | 45017961 | T3 DI MIDDLEFORK #1 8/114 RPR JUMW | ICW
LC | 121747432 | 054/005A | T2 DI HUMBOLDT-TRINITY 54/5A RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2021-07-16 | 2021-07-15 | 2022-03-29 | 2022-07-15 | 2022-07-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45158941 | T2 DI HUMBOLDT-TRINITY 54/5A RPR GYWW | ICW
LC | 121747433 | 054/005C | T2 DI HUMBOLDT-TRINITY 54/5C RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2021-07-16 | 2021-07-15 | 2022-03-29 | 2022-07-15 | 2022-07-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45158941 | T2 DI HUMBOLDT-TRINITY 54/5A RPR GYWW | ICW
LC | 121747437 | 008/040A | T2 DI CNTR CST-MRG #2 8/40A RPL HRDT | CONCORD | ETL.5453.POLE.NWOD | 2021-07-16 | 2021-07-16 | 2022-01-12 | 2022-07-16 | 2022-07-16 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45121402 | T2 DI CNTR CST-MRG #2 8/40A RPL HRDT | ICQ
LC | 121747438 | 008/040A | T2 DI CNTR CST-MRG #2 8/40A RPR GYWS | CONCORD | ETL.5453.POLE.NWOD | 2021-07-16 | 2021-07-16 | 2022-01-12 | 2022-07-16 | 2022-07-16 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45079058 | T2 DI CNTR CST-MRG #2 8/40A RPR GYWS | ICS
LC | 121747958 | C010/042 | T2 DI MSS LNDNG-CBRN C010/042 RMV VEG | MOSSLNDG | ETL.5330.TOWR | 2021-07-17 | 2021-07-15 | 2022-04-20 | 2022-07-15 | 2022-07-15 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121748078 | 009/006 | T2 DI MELONES-CURTIS 9/6L RPR POLE | VICTOR | ETL.2390.POLE.WDPS | 2021-07-17 | 2021-07-13 | 2022-11-03 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163417 | T2 DI MELONES-CURTIS 9/6L RPR STRW | ICW
LC | 121748080 | 082/006B | T2 DI HUMBOLDT-TRINITY 82/6B RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-17 | 2021-07-15 | 2022-10-17 | 2022-07-15 | 2022-07-15 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548090 | T2 DI HUMB-TRIN 82/6C RPL INSW | 93I
LC | 121748089 | 073/001A | T2 DI HUMBOLDT-TRINITY 73/1A RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-17 | 2021-07-15 | 2022-10-17 | 2022-07-15 | 2022-07-15 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547352 | T2 DI HUMBOLDT-TRINITY 073/002A RPL INSW | 93I
LC | 121748124 | 073/001B | T2 DI HUMBOLDT-TRINITY 73/1B RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-17 | 2021-07-15 | 2022-10-17 | 2022-07-15 | 2022-07-15 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547352 | T2 DI HUMBOLDT-TRINITY 073/002A RPL INSW | 93I
LC | 121748127 | 073/001C | T2 DI HUMBOLDT-TRINITY 73/1C RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-17 | 2021-07-15 | 2022-10-17 | 2022-07-15 | 2022-07-15 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547352 | T2 DI HUMBOLDT-TRINITY 073/002A RPL INSW | 93I
LC | 121748146 | 008/008 | T2 DI MELONES-CURTIS 008/008R RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-17 | 2021-07-13 | 2022-11-15 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163419 | T2 DI MELONES-CURTIS 008/008R RPR STRW | ICW
LC | 121748159 | 003/082 | T3 DI BURNS-LNE STAR #2 003/082 RPL ANCW | MOSSLNDG | ETL.6240.POLE.WOOD | 2021-07-17 | 2021-07-16 | 2022-04-07 | 2022-01-12 | 2022-01-16 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31578893 | T3 DI BURNS-LNE STAR #2 003/082 RPL ANCW | 93E
LC | 121748269 | 003/041 | T2 DI CHRISTIE-WILLOW PASS 3/41 RPR GYWW | CONCORD | ETL.6370.POLE.WOOD | 2021-07-17 | 2021-07-13 | 2022-09-11 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45192975 | T2 DI CHRISTIE-WILLOW PASS 3/41 RPR GYWW | ICW
LC | 121748336 | 013/009 | T2 DI MELONES-CURTIS 13/9L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-17 | 2021-07-14 | 2022-08-26 | 2022-07-14 | 2022-07-14 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163500 | T2 DI MELONES-CURTIS 13/9L RPR STRW | ICW
LC | 121748340 | 018/460 | T2 DI CARIBOU #2 018/460 RPL HRDW | TABLEMTN | ETL.6280.POLE.NWOD | 2021-07-17 | 2021-07-14 | 2022-07-14 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45214074 | T2 DI CARIBOU #2 018/460 RPL HRDW | ICW
LC | 121748361 | 013/009 | T2 DI MELONES-CURTIS 13/9 GRND WASH | VICTOR | ETL.2390.INSL.CERA | 2021-07-17 | 2021-07-14 | 2022-08-25 | 2022-07-14 | 2022-07-14 | Late | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Contaminated | Insulator | Ground Wash | 45163501 | T2 DI MELONES-CURTIS 13/9 GRND WASH | ICD
LC | 121748368 | 008/079 | T2 DI CTTNWD-BENTON #2 8/79R RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-17 | 2021-07-13 | 2022-06-04 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213274 | T2 DI CTTNWD-BENTON #2 8/79R RPR STRW | ICW
LC | 121748455 | 008/076 | T2 DI COTTONWD-BENTON #2 8/76 RPR CRSW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-17 | 2021-07-13 | 2022-07-22 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45213275 | T2 DI COTTONWD-BENTON #2 8/76 RPR CRSW | ICW
LC | 121748477 | 003/078 | T3 DI BURNS-LONE STAR#2 003/078 RPR INSW | MOSSLNDG | ETL.6240.POLE.WOOD | 2021-07-17 | 2021-07-16 | 2022-04-05 | 2022-01-12 | 2022-01-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Wood | Repair | 45075340 | T3 DI BURNS-LONE STAR#2 003/078 RPR INSW | ICW
LC | 121748492 | 008/076 | T2 DI COTTONWOOD-BENTN #2 8/76L RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-17 | 2021-07-13 | 2022-07-22 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213276 | T2 DI COTTONWOOD-BENTN #2 8/76L RPR STRW | ICW
LC | 121748551 | 010/001 | T2 DI MELONES-CURTIS 010/001L RPR POLE | VICTOR | ETL.2390.POLE.WDPS | 2021-07-17 | 2021-07-15 | 2022-08-25 | 2022-07-15 | 2022-07-15 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163502 | T2 DI MELONES-CURTIS 010/001L RPR POLE | ICW
LC | 121748753 | 058/003B | T2 DI HUMBOLDT-TRINITY 58/3B RPL HRDD | EUREKA | ETL.1820.POLE.WOOD | 2021-07-17 | 2021-07-15 | 2022-03-30 | 2022-07-15 | 2022-07-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45010276 | T2 DI HUMBOLDT-TRINITY 58/3B RPL HRDD | ICW
LC | 121748774 | 058/003B | T2 DI HUMBOLDT-TRINITY 58/3B RPR JUMP | EUREKA | ETL.1820.INSL.CERA | 2021-07-17 | 2021-07-15 | 2022-06-10 | 2022-07-15 | 2022-07-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Jumper-Wood | Repair | 45145440 | T2 DI HUMBOLDT-TRINITY 58/3B RPR JUMP | ICW
LC | 121748834 | 013/238 | T3 DI FRNCH MDWS-MDL FRK 13/238 INS HRDD | SACTO | ETL.6870.POLE.WOOD | 2021-07-17 | 2021-07-16 | 2022-05-07 | 2022-01-12 | 2022-01-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45218805 | T3 DI FRNCH MDWS-MDL FRK 13/238 INS HRDD | ICW
LC | 121748870 | 069/350 | T2 DI MALIN-RND MTN #2 069/350 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-17 | 2021-07-16 | 2022-07-14 | 2022-07-16 | 2022-07-16 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215171 | T2 DI MALIN-RND MTN #2 069/350 RPR OPGW | ICS
LC | 121748920 | 013/238 | T3 DI FRN MDW-ML FK 13/238 GYWW CMPLTD | SACTO | ETL.6870.POLE.WOOD | 2021-07-17 | 2021-07-16 | 2022-05-07 | 2022-01-12 | 2022-01-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45218806 | T3 DI FRNCH MDWS-MDL FRK 13/238 RPR GYWW | ICW
LC | 121748933 | 020/238A | T2 DI DRUM-SUMMIT NWP #1 2/238A RPL HRDD | SACTO | ETL.1440.POLE.NWOD | 2021-07-17 | 2021-07-15 | 2022-09-02 | 2022-07-15 | 2022-07-15 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45218294 | T2 DI DRUM-SUMMIT NWP #1 2/238A RPL HRDD | ICW
LC | 121748977 | 003/041 | T2 DI PIT #5-ROUND MTN #1 3/41L RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-17 | 2021-07-14 | 2022-07-14 | 2022-07-14 | 2022-07-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121748989 | 057/001A | T2 DI HUMBOLDT-TRINITY 57/1A RPR STRW | EUREKA | ETL.1820.POLE.WOOD | 2021-07-17 | 2021-07-15 | 2022-05-31 | 2022-07-15 | 2022-07-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45145276 | T2 DI HUMBOLDT-TRINITY 57/1A RPR WDPKR | ICW
LC | 121749030 | 004/054A | T3 DI DRUM SUMMIT #2 4/54A RPL INSW | SACTO | ETL.1450.INSL.NCER | 2021-07-17 | 2021-07-07 | 2022-06-05 | 2022-01-03 | 2022-01-07 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546395 | T3 DI DRUM-SUMMIT #2 004/054B RPL INSW | 93I
LC | 121749042 | 057/001B | T2 DI HUMBOLDT-TRINITY 57/1B RPR STRW | EUREKA | ETL.1820.POLE.WOOD | 2021-07-17 | 2021-07-15 | 2022-05-30 | 2022-07-15 | 2022-07-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45145277 | T2 DI HUMBOLDT-TRINITY 57/1B RPR WDPKR | ICW
LC | 121749049 | 106/001C | T2 DI HUMBOLDT-TRINITY 106/1C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2021-07-17 | 2021-07-14 | 2022-01-22 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45128326 | T2 DI HUMBOLDT-TRINITY 106/1A RPR GYWW | ICW
LC | 121749101 | 106/001B | T2 DI HUMBOLDT-TRINITY 106/1B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2021-07-17 | 2021-07-15 | 2022-01-22 | 2022-07-15 | 2022-07-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45128326 | T2 DI HUMBOLDT-TRINITY 106/1A RPR GYWW | ICW
LC | 121749337 | 013/005 | T2 DI MELONES-CURTIS 13/5L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-17 | 2021-07-13 | 2022-08-26 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163505 | T2 DI MELONES-CURTIS 13/5L RPR STRW | ICW
LC | 121749382 | 019/535 | T3 DI COLGATE-ALLEGHANY 19/535 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2021-07-17 | 2021-07-17 | 2022-06-14 | 2022-01-13 | 2022-01-17 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31596507 | T3 DI COLGATE-ALLEGHANY 21/567 RPL STRW | 70Y
LC | 121749533 | 004/048 | T2 DI PIT #5-ROUND MTN #2 4/48L RPL STRW | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-17 | 2021-07-14 | 2022-06-15 | 2022-07-14 | 2022-07-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547482 | T2 DI PIT #5-ROUND MTN #2 1/18R RPL STRW | 70Y
LC | 121749587 | 002/030 | T2 DI PIT #5-ROUND MTN #2 2/30 RPR STRW | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-17 | 2021-07-14 | 2022-06-02 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213803 | T2 DI PIT #5-ROUND MTN #2 2/30 RPR STRW | ICW
LC | 121749614 | ?001/006 | T3 DI SNTH LN-HLF MN BY ?1/6 RMV VEG | METCALF | ETL.7212.POLE.WOOD | 2021-07-17 | 2021-07-17 | 2022-01-03 | 2022-01-13 | 2022-01-17 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121749633 | 008/002 | T3 DI PTTR VLLY WLLTS 008/002 COMPLETE | WILLITS | ETL.7820.POLE.WOOD | 2021-07-17 | 2021-07-17 | 2022-06-14 | 2022-01-13 | 2022-01-17 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31548072 | T3 DI PTTR VLLY WLLTS 008/002 RPL POLE | 93E
LC | 121749694 | 022/175 | T2 DI MDDL FRK-GLD HLL 22/175 RPR INSW | SACTO | ETL.5140.INSL.NCER | 2021-07-17 | 2021-07-16 | 2021-12-15 | 2022-07-16 | 2022-07-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45017960 | T2 DI MDDL FRK-GLD HLL 22/175 RPR INSW | ICW
LC | 121749695 | 060/001 | T2 DI HUMBOLDT-TRINITY 60/1 RPR IBWW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-17 | 2021-07-12 | 2022-03-30 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45145447 | T2NT DI HUMBOLDT-TRINITY 60/1 RMV BUTT | ICW
LC | 121749716 | 017/159 | T3 DI MNTA VSTA-BRNS 17/159C RPR GYWW | MOSSLNDG | ETL.7590.POLE.WDPS | 2021-07-17 | 2021-07-15 | 2022-03-02 | 2022-01-11 | 2022-01-15 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45082562 | T3 DI MNTA VSTA-BRNS 17/159C RPR GYWW | ICW
LC | 121749727 | 004/051 | T2 DI PIT #5-ROUND MTN #1 4/51 RPL INSS | TABLEMTN | ETL.5420.INSL.CERA | 2021-07-17 | 2021-07-14 | 2022-07-17 | 2022-07-14 | 2022-07-14 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31607397 | T2 DI PIT #5-ROUND MTN #1 2/25 RPL INSS | 93K
LC | 121749739 | 000/002 | T3 DI DRM GRSS VLY WMR 000/002 RPR SPLW | SACTO | ETL.6760.INSL.CERA | 2021-07-17 | 2021-07-17 | 2022-04-23 | 2022-01-13 | 2022-01-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45194339 | T3 DI DRM GRSS VLY WMR 000/002 RPR SPLW | ICW
LC | 121749831 | 000/002 | T3 DI DRM GRSS VLY WMR 000/002 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-07-17 | 2021-07-17 | 2022-04-23 | 2022-01-13 | 2022-01-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45194342 | T3 DI DRM GRSS VLY WMR 000/002 RPR GYWW | ICW
LC | 121749871 | 001/011 | T2 DI LAYTNVILLE-COVELO 1/11 RPL HRDD | WILLITS | ETL.7390.POLE.WOOD | 2021-07-17 | 2021-07-17 | 2022-06-04 | 2022-07-17 | 2022-07-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44999873 | T2 DI LAYTNVILLE-COVELO 1/11 RPL HRDD | ICW
LC | 121749940 | 032/221 | DI TRNTY-CTTNWD 32/221 RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-07-17 | 2021-07-14 | 2022-06-27 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45212100 | DI TRNTY-CTTNWD 32/221 RPR GYWW | ICW
LC | 121749943 | 019/442 | T2 DI DRUM-GRSS VLLY-WMR 19/442 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-07-17 | 2021-07-15 | 2022-03-29 | 2022-07-15 | 2022-07-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45193833 | T2 DI DRUM-GRSS VLLY-WMR 19/442 RPR GYWW | ICW
LC | 121750020 | 018/005 | T2 DI MNDCN-WLLTS-FRT BRG 18/5 RPL HRDD | WILLITS | ETL.7550.POLE.WOOD | 2021-07-17 | 2021-07-17 | 2022-05-16 | 2022-07-17 | 2022-07-17 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45145816 | T2 DI MNDCN-WLLTS-FRT BRG 18/5 RPL HRDD | ICW
LC | 121750027 | 072/002 | T2 DI HUMBOLDT-TRINITY 72/02L RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2021-07-17 | 2021-07-12 | 2022-03-31 | 2022-07-12 | 2022-07-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45147769 | T2 DI HUMBOLDT-TRINITY 72/02L RPR GYWW | ICW
LC | 121750033 | 002/027 | T2 DI PIT #5-ROUND MTN #1 2/27 INST HRDD | TABLEMTN | ETL.5420.POLE.STPS | 2021-07-17 | 2021-07-14 | 2022-06-22 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Missing | Hardware-Wood | Install | 45213277 | T2 DI PIT #5-ROUND MTN #1 2/27 INST HRDD | ICW
LC | 121750061 | 011/110 | T3 DI DRM-RO OSO #1 11/110 BNT STL CMPLT | SACTO | ETL.1420.TOWR | 2021-07-17 | 2021-07-17 | 2022-05-31 | 2022-01-13 | 2022-01-17 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45181134 | T3 DI DRUM-RIO OSO #1 011/110 BNT STEEL | ICQ
LC | 121750087 | 001/011 | T2 DI PIT #5-ROUND MTN #2 01/11 RPR SHLW | TABLEMTN | ETL.5430.POLE.STPS | 2021-07-17 | 2021-07-13 | 2022-06-02 | 2022-07-13 | 2022-07-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45213802 | T2 DI PIT #5-ROUND MTN #2 01/11 RPR SHLW | ICW
LC | 121750116 | 000/002 | T3NT DI DEER CREEK-DRUM 000/002 RMV BUTT | SACTO | ETL.6690.POLE.WOOD | 2021-07-17 | 2021-07-17 | 2022-05-14 | 2022-01-13 | 2022-01-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45193615 | T3NT DI DEER CREEK-DRUM 000/002 RMV BUTT | ICW
LC | 121750146 | 004/046 | T2 DI PIT #5-RND MTN #1 4/46 RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-17 | 2021-07-14 | 2022-07-01 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213278 | T2 DI PIT #5-RND MTN #1 4/46 RPR STRW | ICW
LC | 121750167 | 001/006 | T2 DI LYTNVILLE-COVELO 1/6 RPL POLE | WILLITS | ETL.7390.POLE.WOOD | 2021-07-17 | 2021-07-17 | 2022-06-04 | 2022-07-17 | 2022-07-17 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31547421 | T2 DI LYTNVILLE-COVELO 1/6 RPL POLE | 70Y
LC | 121750172 | 004/051 | PIT #5-ROUND MTN #2 COMPLETE | TABLEMTN | ETL.5430.INSL.CERA | 2021-07-17 | 2021-07-14 | 2022-06-14 | 2022-07-14 | 2022-07-14 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547483 | T2 DI PIT #5-ROUND MTN #2 4/51 RPL INS | 93I
LC | 121750287 | 058/003A | T2 DI HUMBOLDT-TRINITY 58/3A RPL HRDD | EUREKA | ETL.1820.POLE.WOOD | 2021-07-17 | 2021-07-15 | 2022-03-30 | 2022-07-15 | 2022-07-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45145279 | T2 DI HUMBOLDT-TRINITY 58/3A RPL HRDD | ICW
LC | 121750320 | 000/001 | T2 DI PIT #5-ROUND MTN #2 00/01 RPR HRDW | TABLEMTN | ETL.5430.POLE.STPS | 2021-07-17 | 2021-07-14 | 2022-06-09 | 2022-07-14 | 2022-07-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45213801 | T2 DI PIT #5-ROUND MTN #2 00/01 RPR HRDW | ICS
LC | 121750642 | 004/048 | T2 DI PIT #5-ROUND MTN #1 4/48 RPR INSW | TABLEMTN | ETL.5420.INSL.CERA | 2021-07-17 | 2021-07-14 | 2022-07-01 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45213279 | T2 DI PIT #5-ROUND MTN #1 4/48 RPR INSW | ICW
LC | 121751057 | 003/077 | T2 DI DELTA-MTNGATEJCT-3/77 RMV BUTT | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-17 | 2021-07-06 | 2022-06-23 | 2022-07-06 | 2022-07-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45297928 | T2 DI DELTA-MTNGATEJCT-3/77 RMV BUTT | ICW
LC | 121752841 | 005/022 | T2 DI PITTSBURG-TESLA #2 5/022 RPR INSS | CONCORD | ETL.5520.INSL.CERA | 2021-07-19 | 2021-07-17 | 2022-01-31 | 2022-07-17 | 2022-07-17 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45107138 | T2 DI PITTSBURG-TESLA #2 5/022 RPR INSS | ICS
LC | 121752843 | 010/075 | T2 DI ROCK CREEK-POE 010/075 RPL HRDT | TABLEMTN | ETL.5630.TOWR | 2021-07-19 | 2021-07-17 | 2022-07-21 | 2022-07-17 | 2022-07-17 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45195475 | T2 DI ROCK CREEK-POE 010/075 RPL HRDT | ICQ
LC | 121752844 | 010/075 | T2 DI ROCK CREEK-POE 010/075 RPL INSS | TABLEMTN | ETL.5630.INSL | 2021-07-19 | 2021-07-17 | 2022-08-04 | 2022-07-17 | 2022-07-17 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551263 | T3 DI ROCK CREEK-POE RPL INSS 9TWRS | 93K
LC | 121752990 | 025/200 | T2 DI MID FORK-GLD HILL 25/200L RPR ANCW | SACTO | ETL.5140.POLE.STPS | 2021-07-19 | 2021-07-14 | 2021-12-02 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Anchor-Wood | Repair | 45018592 | T2 DI MID FORK-GLD HILL 25/200L RPR ANCW | ICW
LC | 121752991 | 025/200 | T2 DI MID FORK-GLD HILL 25/200L RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2021-07-19 | 2021-07-14 | 2021-12-01 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45018590 | T2 DI MID FORK-GLD HILL 25/200L RPR GYWW | ICW
LC | 121752993 | 013/358 | T3 DI COLGATE-ALLEGHANY 13/358 RPR SPLW | SACTO | ETL.6470.INSL.CERA | 2021-07-19 | 2021-07-19 | 2022-06-20 | 2022-01-15 | 2022-01-19 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45224631 | T3 DI COLGATE-ALLEGHANY 13/358 RPR SPLW | ICW
LC | 121753091 | 014/388 | T3 DI COLGATE-ALLEGHANY 14/388 RPL SPLW | SACTO | ETL.6470.INSL.NCER | 2021-07-19 | 2021-07-19 | 2022-06-26 | 2022-01-15 | 2022-01-19 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Replace | 45224632 | T3 DI COLGATE-ALLEGHANY 14/388 RPL SPLW | ICW
LC | 121753257 | 034/140 | T2 DI DIABLO-MIDWAY #2 034/140 RPR SHLS | PISMOBCH | ETL.5980.TOWR | 2021-07-19 | 2021-07-19 | 2022-01-10 | 2022-07-19 | 2022-07-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45068634 | T2 DI DIABLO-MIDWAY #2 034/140 RPR SHLS | ICS
LC | 121753397 | ?005/000 | T3 DI SNTH LN-HF MN BY ?005/000 RPR STRW | METCALF | ETL.7212.POLE.WOOD | 2021-07-19 | 2021-07-19 | 2022-07-20 | 2022-01-15 | 2022-01-19 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45151633 | T3 DI SNTH LN-HF MN BY ?005/000 RPR STRW | ICW
LC | 121753964 | 006/114 | T3 DI COLGATE-CHALLENGE 6/114 RPL INSW | SACTO | ETL.6480.INSL.NCER | 2021-07-19 | 2021-07-15 | 2022-08-24 | 2022-01-11 | 2022-01-15 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546753 | T3 DI COLGATE-CHALLENGE 6/114 RPL INSW | 93I
LC | 121754228 | 006/073A | T2 DI GREEN VLLY-CMP EVRS 6/73A RMV BUTT | MOSSLNDG | ETL.1710.POLE.NWOD | 2021-07-19 | 2021-07-19 | 2022-03-02 | 2022-07-19 | 2022-07-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45166754 | T2 DI GREEN VLLY-CMP EVRS 6/73A RMV BUTT | ICW
LC | 121754402 | 006/073A | T2 DI GRN VLLY-CMP EVRS 6/73A RPR SPLW | MOSSLNDG | ETL.1710.INSL.NCER | 2021-07-19 | 2021-07-19 | 2022-03-02 | 2022-07-19 | 2022-07-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45166749 | T2 DI GRN VLLY-CMP EVRS 6/73A RPR SPLW | ICW
LC | 121754872 | 008/036 | T2 DI PITTSBURG-TESLA #1 8/36 RPR FOND | CONCORD | ETL.5510.TOWR | 2021-07-19 | 2021-07-19 | 2022-04-13 | 2022-07-19 | 2022-07-19 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190834 | T2 DI PITTSBURG-TESLA #1 8/36 RPR FOND | ICQ
LC | 121754960 | 067/337 | T2 DI MALIN-RND MTN #2 67/337 RPR INSLS | TABLEMTN | ETL.6020.INSL.NCER | 2021-07-19 | 2021-07-19 | 2022-07-16 | 2022-07-19 | 2022-07-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45223889 | T2 DI MALIN-RND MTN #2 67/337 RPR INSLS | ICS
LC | 121755111 | 068/344 | T2 DI MALIN-ROUND MTN #2 68/344 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-19 | 2021-07-19 | 2022-07-14 | 2022-07-19 | 2022-07-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215170 | T2 DI MALIN-ROUND MTN #2 68/344 RPR OPGW | ICS
LC | 121755936 | 025/151 | T2 DI TSLA-SLDO-MTC 25/151 RPL HRDD | VICTOR | ETL.4000.POLE.WOOD | 2021-07-19 | 2021-07-19 | 2022-01-24 | 2022-07-19 | 2022-07-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45067146 | T2 DI TSLA-SLDO-MTC 25/151 RPL HRDD | ICW
LC | 121756279 | 013/360 | T3 DI CLGTE-ALLGHNY 13/360 RPL INSW | SACTO | ETL.6470.INSL.NCER | 2021-07-19 | 2021-07-19 | 2022-06-20 | 2022-01-15 | 2022-01-19 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31609223 | T3 DI CLGTE-ALLGHNY 13/360 RPL INSW | 93I
LC | 121756756 | :001/008 | T2 DI ROCK CREEK-POE :001/008 RPR GYWS | TABLEMTN | ETL.5630.TOWR | 2021-07-19 | 2021-07-19 | 2022-08-07 | 2022-07-19 | 2022-07-19 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45404465 | T2 DI ROCK CREEK-POE :001/008 RPR GYWS | ICS
LC | 121756994 | 004/043 | T2 DI PIT #5-ROUND MTN #2 4/43R RPL STRW | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-19 | 2021-07-14 | 2022-06-14 | 2022-07-14 | 2022-07-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547482 | T2 DI PIT #5-ROUND MTN #2 1/18R RPL STRW | 70Y
LC | 121756999 | 001/016 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-19 | 2021-07-09 | 2022-07-16 | 2022-07-09 | 2022-07-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121757061 | 004/048 | T2 DI PIT #5-ROUND MTN #2 4/48R RPL STRW | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-19 | 2021-07-14 | 2022-06-15 | 2022-07-14 | 2022-07-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547482 | T2 DI PIT #5-ROUND MTN #2 1/18R RPL STRW | 70Y
LC | 121757063 | 003/041 | T2 DI PIT #5-ROUND MTN #1 3/41R RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-19 | 2021-07-14 | 2022-07-14 | 2022-07-14 | 2022-07-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121757881 | 014/074 | T2 WV BALCH-SANGER 14/74 RPR FOND | FRESNO | ETL.1050.TOWR | 2021-07-19 | 2021-07-19 | 2022-08-17 | 2022-07-19 | 2022-07-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45070453 | T2 WV BALCH-SANGER 14/74 RPR FOND | ICQ
LC | 121759702 | 066/004 | T2 EI HUMBOLDT-TRINITY 66/4 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-20 | 2021-07-19 | 2022-10-18 | 2022-07-19 | 2022-07-19 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547346 | T2 DI HUMBOLDT-TRINITY 066/004 RPL STRW | 70Y
LC | 121759919 | 020/192B | T2 DI UKH-HPLD-CLDL-HLD 20/192B COTTER | LAKEVLLE | ETL.4050.INSL.NCER | 2021-07-20 | 2021-07-19 | 2022-01-31 | 2022-07-19 | 2022-07-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45137838 | T2 DI UKH-HPLD-CLDL-HLD 20/192B COTTER | ICW
LC | 121759993 | 008/008 | T2 DI MELONES-CURTIS 008/008L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-20 | 2021-07-13 | 2022-11-15 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164442 | T2 DI MELONES-CURTIS 008/008L RPR STRW | ICW
LC | 121760316 | 006/055BC | T2 DI PRDS-TBLE MTN 6/55BC RPR STRW | TABLEMTN | ETL.4316.POLE.NWOD | 2021-07-20 | 2021-07-14 | 2022-02-25 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45196974 | T2 DI PRDS-TBLE MTN 6/55BC RPR STRW | ICW
LC | 121760815 | 007/118 | T2 DI CENTERVILLE-TBL MTN 7/118 RPL INSW | TABLEMTN | ETL.6320.INSL.NCER | 2021-07-20 | 2021-07-19 | 2022-04-27 | 2022-07-19 | 2022-07-19 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547462 | T2 DI CENTERVILLE-TBL MTN 7/118 RPL INSW | 93I
LC | 121761372 | ?005/002 | T3 DI SNEATH LN-HLF MN BY ?5/2 RPR STRW | METCALF | ETL.7212.POLE.WOOD | 2021-07-20 | 2021-07-19 | 2022-04-12 | 2022-01-15 | 2022-01-19 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45151634 | T3 DI SNEATH LN-HLF MN BY ?5/2 RPR STRW | ICW
LC | 121761837 | 007/034 | T2 DI PITTSBURG-TESLA #1 7/34 RPL HRDT | CONCORD | ETL.5510.TOWR | 2021-07-20 | 2021-07-19 | 2022-04-10 | 2022-07-19 | 2022-07-19 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45190835 | T2 DI PITTSBURG-TESLA #1 7/34 RPL HRDT | ICQ
LC | 121761949 | 002/023 | T2 DI PT #5-RD MN #2 2/23R RPL STR CMPLT | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-20 | 2021-07-13 | 2022-06-11 | 2022-07-13 | 2022-07-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547482 | T2 DI PIT #5-ROUND MTN #2 1/18R RPL STRW | 70Y
LC | 121761995 | 008/005 | T2 DI MELNES-CURTIS-WP STR 8/5R RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-20 | 2021-07-13 | 2022-08-03 | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164450 | T2 DI MELNES-CURTIS-WP STR 8/5R RPR STRW | ICW
LC | 121762216 | 002/030 | T2 DI PIT #5-ROUND MTN #2 2/30R RPR STRW | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-20 | 2021-07-14 | 2022-06-02 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213800 | T2 DI PIT #5-ROUND MTN #2 2/30R RPR STRW | ICW
LC | 121762271 | 001/012 | T2 DI PIT #6 TP-WP STR 1/12R RPL STRW CM | TABLEMTN | ETL.5441.POLE.WDPS | 2021-07-20 | 2021-07-14 | 2022-06-21 | 2022-07-14 | 2022-07-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31545615 | T2 PIT #6 TAP-WOOD 1/14 RPL POLE | 70Y
LC | 121762703 | 065/327 | T2 DI MALIN-RD MTN #2 65/327 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-20 | 2021-07-19 | 2022-07-14 | 2022-07-19 | 2022-07-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215169 | T2 DI MALIN-RD MTN #2 65/327 RPR OPGW | ICS
LC | 121762843 | T058 | T3 DI MIDWAY-SANTA MARIA T58 BENT STEEL | PISMOBCH | ETL.9240.TOWR | 2021-07-20 | 2021-07-19 | 2022-05-06 | 2022-01-15 | 2022-01-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Tower | Repair | 45098905 | T3 DI MIDWAY-SANTA MARIA T58 BENT STEEL | ICQ
LC | 121763360 | T056 | T3 DI MIDWAY-SANTA MARIA T056 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-20 | 2021-07-19 | 2022-01-20 | 2022-01-15 | 2022-01-19 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 121763467 | 002/011 | T3 DI DIABLO-MIDWAY #2 2/11 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-07-20 | 2021-07-19 | 2022-06-02 | 2022-01-15 | 2022-01-19 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068576 | T3 DI DIABLO-MIDWAY #2 2/11 RPR GYWS | ICS
LC | 121766789 | T082 | T3 DI MIDWAY-SANTA MARIA T082 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-21 | 2021-07-19 | 2022-07-27 | 2022-01-15 | 2022-01-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098907 | T3 DI MIDWAY-SANTA MARIA T082 RPR FOND | ICQ
LC | 121766921 | T082 | T3 DI MIDWAY-SANTA MARIA T82 INS STEP | PISMOBCH | ETL.9240.TOWR | 2021-07-21 | 2021-07-19 | 2022-07-27 | 2022-01-15 | 2022-01-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45098909 | T3 DI MIDWAY-SANTA MARIA T82 INS STEP | ICQ
LC | 121766924 | T042 | T3 DI MIDWAY-SANTA MARIA T042 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-21 | 2021-07-19 | 2022-05-07 | 2022-01-15 | 2022-01-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098910 | T3 DI MIDWAY-SANTA MARIA T042 RPR FOND | ICQ
LC | 121767131 | ?005/001 | T3 DI SNTH LN-HLF MN BY ?005/001 RPL DAM | METCALF | ETL.7212.POLE.NWOD | 2021-07-21 | 2021-07-19 | 2022-07-10 | 2022-01-15 | 2022-01-19 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Damper-Wood | Replace | 45151635 | T3 DI SNTH LN-HLF MN BY ?005/001 RPL DAM | ICW
LC | 121767133 | ?005/001 | T3 DI SNTH LN-HLF MN BY ?005/1 RPL HRDD | METCALF | ETL.7212.POLE.NWOD | 2021-07-21 | 2021-07-19 | 2022-07-20 | 2022-01-15 | 2022-01-19 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45181108 | T3 DI SNTH LN-HLF MN BY ?005/1 RPL HRDD | ICW
LC | 121767694 | 008/172 | T2 DI CTTNWD-RD BLFF 8/172 RMV BUTT | TABLEMTN | ETL.6660.POLE.NWOD | 2021-07-21 | 2021-07-19 | 2022-06-06 | 2022-07-19 | 2022-07-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45197162 | T2 DI CTTNWD-RD BLFF 8/172 RMV BUTT | ICW
LC | 121767808 | 013/000 | T2 DI MELONES-CURTIS 013/000L RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-21 | 2021-07-20 | 2022-11-03 | 2022-07-20 | 2022-07-20 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579809 | T2 DI MELONES-CURTIS 13/7L RPL STRW | 70Y
LC | 121767809 | 013/000 | T2 DI MELONES-CURTIS 013/000R RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-21 | 2021-07-20 | 2022-11-03 | 2022-07-20 | 2022-07-20 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579809 | T2 DI MELONES-CURTIS 13/7L RPL STRW | 70Y
LC | 121767880 | T060 | T3 DI MIDWAY-SANTA MARIA T060 INS HRDT | PISMOBCH | ETL.9240.TOWR | 2021-07-21 | 2021-07-19 | 2022-05-05 | 2022-01-15 | 2022-01-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | Missing | Hardware-Tower | Install | 45098911 | T3 DI MIDWAY-SANTA MARIA T060 INS HRDT | ICQ
LC | 121767884 | 005/023 | T2 DI PITTSBURG-TESLA #1 5/23 RPL HRDT | CONCORD | ETL.5510.TOWR | 2021-07-21 | 2021-07-19 | 2022-04-12 | 2022-07-19 | 2022-07-19 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45190836 | T2 DI PITTSBURG-TESLA #1 5/23 RPL HRDT | ICQ
LC | 121768092 | T041 | T3 DI MIDWAY-SANTA MARIA T041 RPL STEP | PISMOBCH | ETL.9240.TOWR | 2021-07-21 | 2021-07-19 | 2022-05-07 | 2022-01-15 | 2022-01-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 45098913 | T3 DI MIDWAY-SANTA MARIA T041 RPL STEP | ICQ
LC | 121768093 | T041 | T3 DI MIDWAY-SANTA MARIA T041 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-21 | 2021-07-19 | 2022-08-31 | 2022-01-15 | 2022-01-19 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548616 | T3 DI MIDWAY-SANTA MARIA RPL INSS 7TWRS | 93K
LC | 121768214 | 000/003 | T2 DI KANAKA TAP 000/003 RPR COMPLETE | TABLEMTN | ETL.4223.POLE.STPS | 2021-07-21 | 2021-07-20 | 2022-06-03 | 2022-07-20 | 2022-07-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45240547 | T2 DI KANAKA TAP 000/003 RPR GYWW | ICW
LC | 121768459 | 004/008 | T2 DI MELONES-CURTIS 004/008L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-21 | 2021-07-20 | 2022-08-29 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164454 | T2 DI MELONES-CURTIS 004/008L RPR STRW | ICW
LC | 121768963 | 004/008 | T2 DI MELONES-CURTIS 004/008R RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-21 | 2021-07-20 | 2022-08-29 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164455 | T2 DI MELONES-CURTIS 004/008R RPR STRW | ICW
LC | 121769187 | T055 | T3 MIDWAY-SANTA MARIA T055 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-21 | 2021-07-21 | 2022-01-19 | 2022-01-17 | 2022-01-21 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR FIRE COMP OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 121769442 | 022/009 | T2 DI CPPRMINE-TIVY VLLY 22/9 RPR GYWW | FRESNO | ETL.8590.POLE.WDPS | 2021-07-21 | 2021-07-20 | 2021-08-26 | 2022-07-20 | 2022-07-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44947997 | T2 DI CPPRMINE-TIVY VLLY 22/9 RPR GYWW | ICW
LC | 121769443 | T054 | T3 DI MIDWAY-SANTA MARIA T054 RPL INSW | PISMOBCH | ETL.9240.TOWR | 2021-07-21 | 2021-07-20 | 2022-08-31 | 2022-01-16 | 2022-01-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548616 | T3 DI MIDWAY-SANTA MARIA RPL INSS 7TWRS | 93K
LC | 121769920 | 010/004 | T2 DI MELONES-CURTIS 010/004L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-21 | 2021-07-20 | 2022-08-08 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164457 | T2 DI MELONES-CURTIS 010/004L RPR STRW | ICW
LC | 121770128 | 013/003 | T2 DI MELONES-CURTIS 013/003L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-21 | 2021-07-20 | 2022-08-25 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164485 | T2 DI MELONES-CURTIS 013/003L RPR STRW | ICW
LC | 121770340 | 013/003 | T2 DI MELONES-CURTIS 013/003R RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-21 | 2021-07-20 | 2022-08-25 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164520 | T2 DI MELONES-CURTIS 013/003R RPR STRW | ICW
LC | 121770343 | 005/006 | T2 DI MELONES-CURTIS 005/006L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-21 | 2021-07-20 | 2022-08-06 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164522 | T2 DI MELONES-CURTIS 005/006L RPR STRW | ICW
LC | 121770344 | 005/006 | T2 DI MELONES-CURTIS 005/006R RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-21 | 2021-07-20 | 2022-08-06 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164523 | T2 DI MELONES-CURTIS 005/006R RPR STRW | ICW
LC | 121770346 | 005/001 | T2 DI MELONES-CURTIS 005/001 RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-21 | 2021-07-20 | 2022-08-01 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164525 | T2 DI MELONES-CURTIS 005/001 RPR STRW | ICW
LC | 121770401 | 001/020 | T2 DI CLGTE-SMRTVLE #1 1/20C RPR GYWW | SACTO | ETL.6510.POLE.STPS | 2021-07-21 | 2021-07-19 | 2022-07-29 | 2022-07-19 | 2022-07-19 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45253249 | T2 DI CLGTE-SMRTVLE #1 1/20C RPR GYWW | ICW
LC | 121770402 | 001/020 | T2 DI CLGTE-SMRTVLE #1 1/20R RPR GYWW | SACTO | ETL.6510.POLE.STPS | 2021-07-21 | 2021-07-19 | 2022-07-29 | 2022-07-19 | 2022-07-19 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45253250 | T2 DI CLGTE-SMRTVLE #1 1/20R RPR GYWW | ICW
LC | 121770597 | 005/005 | T2 DI MELONES-CURTIS 005/005 RMV BUTT | VICTOR | ETL.2390.POLE.WDPS | 2021-07-21 | 2021-07-20 | 2022-08-06 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45164527 | T2 DI MELONES-CURTIS 005/005 RMV BUTT | ICW
LC | 121770598 | 013/004 | T2 DI MELONES-CURTIS 13/4L RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-21 | 2021-07-20 | 2022-11-04 | 2022-07-20 | 2022-07-20 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579809 | T2 DI MELONES-CURTIS 13/7L RPL STRW | 70Y
LC | 121770910 | 013/004 | T2 DI MELONES-CURTIS 13/4R RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-21 | 2021-07-20 | 2022-11-04 | 2022-07-20 | 2022-07-20 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579809 | T2 DI MELONES-CURTIS 13/7L RPL STRW | 70Y
LC | 121775993 | 004/068 | T2 COLGATE-PALERMO 4/68 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2021-07-21 | 2021-07-21 | 2021-08-10 | 2022-07-21 | 2022-07-21 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31423185 | T2 EI COLGATE-PALERMO-3/49 REPLACE POLE | 70Y
LC | 121776986 | 008/037 | T3 DI GEYSERS #17-FULTON 8/37 RPL INSS | LAKEVLLE | ETL.4770.INSL.CERA | 2021-07-22 | 2021-07-19 | 2022-07-12 | 2022-01-15 | 2022-01-19 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549694 | T3 DI GEYSERS #17-FULTON 8/37 RPL INSS | 93K
LC | 121777092 | 003/001 | T2 DI SALMON CREEK TAP 003/001 RPR GYWW | LAKEVLLE | ETL.6981.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-04-21 | 2022-07-20 | 2022-07-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45136720 | T2 DI SALMON CREEK TAP 003/001 RPR GYWW | ICW
LC | 121777096 | 007/008 | T2 DI MELONES-CURTIS 007/008L RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-11-14 | 2022-07-20 | 2022-07-20 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31599818 | T2 DI MELONES-CURTIS 007/008R RPL STRW | 70Y
LC | 121777097 | 007/008 | T2 DI MELONES-CURTIS 007/008R RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-11-14 | 2022-07-20 | 2022-07-20 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31599818 | T2 DI MELONES-CURTIS 007/008R RPL STRW | 70Y
LC | 121777180 | 008/037 | T3 DI GEYSERS #12-FULTON 8/37 RPL INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2021-07-22 | 2021-07-19 | 2022-06-14 | 2022-01-15 | 2022-01-19 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31604475 | DI GEYSERS #12-FULTON RPL INSS IN 2 TWRS | 93K
LC | 121777191 | ?004/005 | T3 DI SNEATH LN-HLF MN BY ?4/5L RPL STRW | METCALF | ETL.7212.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-07-19 | 2022-01-16 | 2022-01-20 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579989 | T3 DI SNEATH LN-HLF MN BY ?4/5C RPL STRW | 70Y
LC | 121777193 | ?004/005 | T3 DI SNEATH LN-HLF MN BY ?4/5R RPL STRW | METCALF | ETL.7212.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-07-19 | 2022-01-16 | 2022-01-20 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579989 | T3 DI SNEATH LN-HLF MN BY ?4/5C RPL STRW | 70Y
LC | 121777568 | T046 | T3 DI MIDWAY-SANTA MARIA T046 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-22 | 2021-07-19 | 2022-08-23 | 2022-01-15 | 2022-01-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45098914 | T3 DI MIDWAY-SANTA MARIA T046 RPR FOND | ICQ
LC | 121777629 | 001/023 | T2 DI NARROWS #1 TAP 001/23L RPR STRW | SACTO | ETL.6511.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-08-29 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45224635 | T2 DI NARROWS #1 TAP 001/23L RPR STRW | ICW
LC | 121778116 | 009/001 | T2 DI MELONES-CURTIS 009/001R RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-08-02 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164535 | T2 DI MELONES-CURTIS 009/001R RPR STRW | ICW
LC | 121778117 | 009/001 | T2 DI MELONES-CURTIS 009/001L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-08-02 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164536 | T2 DI MELONES-CURTIS 009/001L RPR STRW | ICW
LC | 121778151 | 007/001 | T2 DI MELONES-CURTIS 007/001L RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-22 | 2021-07-19 | 2022-11-13 | 2022-07-19 | 2022-07-19 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31599815 | T2 DI MELONES-CURTIS 007/001L RPL STRW | 70Y
LC | 121778922 | T084 | T3 DI MIDWAY-SANTA MARIA T084 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-22 | 2021-07-19 | 2022-05-04 | 2022-01-15 | 2022-01-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098916 | T3 DI MIDWAY-SANTA MARIA T084 RPR FOND | ICQ
LC | 121779120 | 005/052 | T2 DI HLSD JCT-HF MN BY 5/52C RPR GYWW | METCALF | ETL.7060.POLE.WDPS | 2021-07-22 | 2021-07-14 | 2022-04-08 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45150549 | T2 DI HLSD JCT-HF MN BY 5/52C RPR GYWW | ICW
LC | 121779123 | 005/052 | T2 DI HLSD JCT-HF MN BY 5/52R RPR GYWW | METCALF | ETL.7060.POLE.WDPS | 2021-07-22 | 2021-07-14 | 2022-04-08 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45150551 | T2 DI HLSD JCT-HF MN BY 5/52R RPR GYWW | ICW
LC | 121779421 | 005/064 | T2 DI COLGATE-SMRTVLLE #1 5/64L RPR STRW | SACTO | ETL.6510.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-07-28 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45253252 | T2 DI COLGATE-SMRTVLLE #1 5/64L RPR STRW | ICW
LC | 121779422 | 005/064 | T2 DI COLGATE-SMRTVLLE #1 5/64C RPR STRW | SACTO | ETL.6510.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-07-28 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 44947133 | T2 DI COLGATE-SMRTVLLE #1 5/64C RPR STRW | ICW
LC | 121780007 | 000/001 | T2 DI COLGATE-ALLEGHANY 000/001 RMV BUTT | SACTO | ETL.6470.POLE.WOOD | 2021-07-22 | 2021-07-19 | 2022-06-23 | 2022-07-19 | 2022-07-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44930735 | T2 DI COLGATE-ALLEGHANY 000/001 RMV BUTT | ICW
LC | 121780166 | 004/049 | T2 EI HLSDL JCT-HF MN BY 4/49R RPR GYWW | METCALF | ETL.7060.POLE.WDPS | 2021-07-22 | 2021-07-14 | 2022-02-22 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45150555 | T2 EI HLSDL JCT-HF MN BY 4/49R RPR GYWW | ICW
LC | 121780169 | 004/049 | T2 EI HLSDL JCT-HF MN BY 4/49C RPR GYWW | METCALF | ETL.7060.POLE.WDPS | 2021-07-22 | 2021-07-14 | 2022-02-22 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45150558 | T2 EI HLSDL JCT-HF MN BY 4/49C RPR GYWW | ICW
LC | 121780714 | 001/012B | T3 DI MIDDLE FORK-GD HILL 1/12B RPR GYWW | SACTO | ETL.5140.POLE.WOOD | 2021-07-22 | 2021-07-21 | 2021-12-15 | 2022-01-17 | 2022-01-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45018589 | T3 DI MIDDLE FORK-GD HILL 1/12B RPR GYWW | ICW
LC | 121780852 | 026/316 | T2 DI DRM-SUMMIT #1 26/316L RPL HDRW | SACTO | ETL.1440.POLE.WDPS | 2021-07-22 | 2021-07-21 | 2022-09-19 | 2022-07-21 | 2022-07-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45218298 | T2 DI DRM-SUMMIT #1 26/316L RPL HDRW | ICW
LC | 121780880 | 000/002B | T3 DI DUTCH FLT#2 TAP 0/2B RPR INSW | SACTO | ETL.1421.POLE.NWOD | 2021-07-22 | 2021-07-21 | 2022-05-21 | 2022-01-17 | 2022-01-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45193618 | T3 DI DUTCH FLT#2 TAP 0/2B RPR INSW | ICW
LC | 121780948 | T089 | T3 DI MIDWAY-SANTA MARIA T089 RPR STRT | PISMOBCH | ETL.9240.TOWR | 2021-07-22 | 2021-07-22 | 2022-05-05 | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Tower | Repair | 45098917 | T3 DI MIDWAY-SANTA MARIA T089 RPR STRT | ICQ
LC | 121781016 | T077 | T3 DI MIDWAY-SANTA MARIA T077 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-22 | 2021-07-22 | 2022-05-04 | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098918 | T3 DI MIDWAY-SANTA MARIA T077 RPR FOND | ICQ
LC | 121781034 | 009/070 | T2 DI TRINITY-CTTNWD 009/070 RPL INSW | TABLEMTN | ETL.4040.INSL.NCER | 2021-07-22 | 2021-07-21 | 2022-08-23 | 2022-07-21 | 2022-07-21 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548130 | T2 DI TRNITY-CTTONWD 4/33 RPL INSW | 93I
LC | 121781036 | 003/005C | T3 DI LAURELES-OTTER 3/5C RPR HDWW | MOSSLNDG | ETL.7380.POLE.WOOD | 2021-07-22 | 2021-07-21 | 2022-03-16 | 2022-01-17 | 2022-01-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45084511 | T3 DI LAURELES-OTTER 3/5C RPR HDWW | ICW
LC | 121781073 | T076 | T3 DI MIDWAY-SANTA MARIA T076 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-22 | 2021-07-22 | 2022-07-19 | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45098919 | T3 DI MIDWAY-SANTA MARIA T076 RPR FOND | ICQ
LC | 121781125 | 002/023 | T3 DI MIDDL FK-GLD HILL 2/23L RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2021-07-22 | 2021-07-21 | 2022-10-14 | 2022-01-17 | 2022-01-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45018588 | T3 DI MIDDL FK-GLD HILL 2/23L RPR GYWW | ICW
LC | 121781126 | 002/023 | T3 DI MIDDL FK-GLD HILL 2/23C RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2021-07-22 | 2021-07-21 | 2022-10-14 | 2022-01-17 | 2022-01-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45017283 | T3 DI MIDDL FK-GLD HILL 2/23C RPR GYWW | ICW
LC | 121781142 | 015/101 | T2 DI MTCALF-GREN VALLEY 15/101 COMPLETE | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-07-22 | 2021-07-21 | 2022-05-21 | 2022-07-21 | 2022-07-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45117830 | T2 DI MTCALF-GREN VALLEY 15/101 RPR STRW | ICW
LC | 121781144 | 009/250 | T3 DI COLGATE-ALLEGHANY 9/250 RPR GYWW | SACTO | ETL.6470.POLE.WOOD | 2021-07-22 | 2021-07-22 | 2022-06-18 | 2022-01-18 | 2022-01-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45224637 | T3 DI COLGATE-ALLEGHANY 9/250 RPR GYWW | ICW
LC | 121781147 | 006/096 | T3 DI MIDDLEFORK #1 06/96 STRW RPL | SACTO | ETL.8405.POLE.WOOD | 2021-07-22 | 2021-07-22 | 2022-08-04 | 2022-01-18 | 2022-01-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548093 | T3 DI MIDDLEFORK #1 06/96 STRW RPL | 70Y
LC | 121781330 | T069 | T3 DI MIDWAY-SANTA MARIA T069 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-22 | 2021-07-22 | 2022-07-18 | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45098920 | T3 DI MIDWAY-SANTA MARIA T069 RPR FOND | ICQ
LC | 121781332 | T069 | T3 DI MIDWAY-SANTA MARIA T069 INS HRDT | PISMOBCH | ETL.9240.TOWR | 2021-07-22 | 2021-07-22 | 2022-07-14 | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45098921 | T3 DI MIDWAY-SANTA MARIA T069 INS HRDT | ICQ
LC | 121781356 | T070 | T3 DI MIDWY-SNT MARIA T070 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-22 | 2021-07-22 | 2022-08-23 | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45098922 | T3 DI MIDWY-SNT MARIA T070 RPR FOND | ICQ
LC | 121781442 | 011/009 | T3 DI UKH-HPLAND-CLVRDL 11/9 RPL STRW | LAKEVLLE | ETL.4050.POLE.WOOD | 2021-07-22 | 2021-07-21 | 2022-01-25 | 2022-01-17 | 2022-01-21 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548225 | T3 DI UKH-HPLAND-CLVRDL 11/9 RPL STRW | 70Y
LC | 121781444 | 017/004 | T2 DI LAYTONVILLE-WILLITS 17/4 RPL INSW | WILLITS | ETL.8360.INSL.CERA | 2021-07-22 | 2021-07-20 | 2022-10-24 | 2022-07-20 | 2022-07-20 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548091 | T2 DI LAYTONVILLE-WILLITS 17/4 RPL INSW | 93I
LC | 121781542 | 000/009 | T2 DI COLGATE-SMTVLLE #1 0/9 RPR ANCW | SACTO | ETL.6510.POLE.STPS | 2021-07-22 | 2021-07-20 | 2022-07-27 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Anchor-Wood | Repair | 45253254 | T2 DI COLGATE-SMTVLLE #1 0/9 RPR ANCW | ICW
LC | 121781580 | 000/009 | T2 DI COLGATE-SMTVLLE #1 0/9 RPR GYWW | SACTO | ETL.6510.POLE.STPS | 2021-07-22 | 2021-07-20 | 2022-07-27 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45253255 | T2 DI COLGATE-SMTVLLE #1 0/9 RPR GYWW | ICW
LC | 121781585 | 022/155 | T2 DI CARIBOU-TBL MTN 22/155 RPR GYWS | TABLEMTN | ETL.4440.POLE.STPS | 2021-07-22 | 2021-07-21 | 2022-06-24 | 2022-07-21 | 2022-07-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Steel | Replace | 45212457 | T2 DI CARIBOU-TBL MTN 22/155 RPL GYWS | ICS
LC | 121781587 | 022/155 | T2 DI CARIBOU-TBL MTN 22/155R RPR GYWS | TABLEMTN | ETL.4440.POLE.STPS | 2021-07-22 | 2021-07-21 | 2022-06-24 | 2022-07-21 | 2022-07-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Steel | Replace | 45211347 | T2 DI CARIBOU-TBL MTN 22/155 RPL GYWS | ICS
LC | 121781616 | 006/069 | T2 DI COLGATE-SMTVLLE #1 6/69 RPR STRW | SACTO | ETL.6510.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-07-25 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45253256 | T2 DI COLGATE-SMTVLLE #1 6/69 RPR STRW | ICW
LC | 121781667 | 034/000 | T2 DI MENDCINO-WILLITS-FT X34/0 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-07-22 | 2021-07-19 | 2022-05-17 | 2022-07-19 | 2022-07-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45148588 | T2 DI MENDCINO-WILLITS-FT X34/0 RPR STRW | ICW
LC | 121781690 | 004/042 | T3 DI MIDDLE FORK-GD HILL 4/42 RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2021-07-22 | 2021-07-21 | 2022-10-20 | 2022-01-17 | 2022-01-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45017281 | T3 DI MIDDLE FORK-GD HILL 4/42 RPR GYWW | ICW
LC | 121781724 | 006/003 | T2 DI MELNS-CRTS 06/03L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-11-13 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164539 | T2 DI MELNS-CRTS 06/03 RPR STRW | ICW
LC | 121781749 | 012/006 | T2 DI MELONES-CURTIS 012/006 RMV DEBR | VICTOR | ETL.2390.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-03-01 | 2022-07-20 | 2022-07-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45164541 | T2 DI MELONES-CURTIS 012/006 RMV DEBR | ICW
LC | 121781766 | 004/006 | T2 DI MELONES-CURTIS 004/006 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-22 | 2021-07-20 | 2022-08-29 | 2022-07-20 | 2022-07-20 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579812 | T2 DI MELONES-CURTIS 007/004 RPL INSW | 93I
LC | 121781801 | 011/115 | T2 DI PIT#5-ROUND MTN#1 11/115 RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-07-12 | 2022-07-20 | 2022-07-20 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121781807 | 004/009 | T2 DI MELONES-CURTIS 004/009 RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-08-28 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164544 | T2 DI MELONES-CURTIS 004/009 RPR STRW | ICW
LC | 121781808 | 004/009 | T2 DI MELONES-CURTIS 004/009 RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-08-28 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164545 | T2 DI MELONES-CURTIS 004/009 RPR STRW | ICW
LC | 121783047 | T096 | T3 DI MIDWAY-SANTA MARIA T096 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 | 2022-08-25 | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098924 | T3 DI MIDWAY-SANTA MARIA T096 RPR FOND | ICQ
LC | 121783183 | 006/068 | T2 DI COLGATE-SMTVLLE #1 6/68 RPR STRW | SACTO | ETL.6510.POLE.WDPS | 2021-07-23 | 2021-07-20 | 2022-07-25 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45253257 | T2 DI COLGATE-SMTVLLE #1 6/68 RPR STRW | ICW
LC | 121783276 | 072/368 | T2 DI MALIN RND MTN #2 72/368 RPR FOND | TABLEMTN | ETL.6020.TOWR | 2021-07-23 | 2021-07-22 | 2022-07-18 | 2022-07-22 | 2022-07-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45197658 | T2 DI MALIN RND MTN #2 72/368 RPR FOND | ICQ
LC | 121783488 | 007/006A | T2 DI MELONES-CURTIS 007/006A RPR GYWW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-23 | 2021-07-20 | 2022-11-14 | 2022-07-20 | 2022-07-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45164553 | T2 DI MELONES-CURTIS 007/006A RPR GYWW | ICW
LC | 121783545 | 007/006A | T2 DI MELONES-CURTIS 007/006A RPL HRDD | VICTOR | ETL.2390.POLE.WDPS | 2021-07-23 | 2021-07-20 | 2022-11-14 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45164555 | T2 DI MELONES-CURTIS 007/006A RPL HRDD | ICW
LC | 121783547 | 007/006A | T2 DI MELONES-CURTIS 007/006A RPL HRDD | VICTOR | ETL.2390.POLE.WDPS | 2021-07-23 | 2021-07-20 | 2022-11-14 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45164556 | T2 DI MELONES-CURTIS 007/006A RPL HRDD | ICW
LC | 121783656 | ?004/005 | T3 DI SNEATH LN-HLF MN BY ?4/5C RPL STRW | METCALF | ETL.7212.POLE.WDPS | 2021-07-23 | 2021-07-20 | 2022-07-19 | 2022-01-16 | 2022-01-20 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31579989 | T3 DI SNEATH LN-HLF MN BY ?4/5C RPL STRW | 70Y
LC | 121783721 | 019/532 | T3 DI COLGATE-ALLGHNY 019/532 RPL PL | SACTO | ETL.6470.POLE.WOOD | 2021-07-23 | 2021-07-22 | 2022-06-14 | 2022-01-18 | 2022-01-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31578443 | T3 COLGATE-ALLEGHANY 15/428 RPL POLE | 70Y
LC | 121783802 | T045 | T3 DI MIDWAY-SANTA MARIA T045 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-20 | 2022-05-06 | 2022-01-16 | 2022-01-20 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098925 | T3 DI MIDWAY-SANTA MARIA T045 RPR FOND | ICQ
LC | 121783807 | T097 | T3 DI MIDWAY-SANTA MARIA T097 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 | 2022-07-27 | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45098926 | T3 DI MIDWAY-SANTA MARIA T097 RPR FOND | ICQ
LC | 121783808 | T097 | T3 DI MIDWAY-SANTA MARIA T097 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 | 2022-08-31 | 2022-01-18 | 2022-01-22 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548618 | T3 DI MIDWAY-SANTA MARIA RPL INSS 6TWRS | 93K
LC | 121783882 | T045 | T3 DI MIDWAY-SANTA MARIA T045 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-20 | 2022-08-31 | 2022-01-16 | 2022-01-20 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548616 | T3 DI MIDWAY-SANTA MARIA RPL INSS 7TWRS | 93K
LC | 121784011 | 087/001 | T2NT DI HUMBOLDT-TRINITY 87/1 RMV BUTT | EUREKA | ETL.1820.POLE.STPS | 2021-07-23 | 2021-07-20 | 2022-10-25 | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2N PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45149354 | T2NT DI HUMBOLDT-TRINITY 87/1 RMV BUTT | ICW
LC | 121784357 | T-111 | T3 DI MDWAY-SNTA MARA T-111 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-23 | 2022-08-30 | 2022-01-19 | 2022-01-23 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548619 | T3 EI MIDWAY-SANTA MARIA RPL INSS 8TWRS | 93K
LC | 121784504 | T062 | T3 DI MIDWAY-SANTA MARIA T062 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 | 2022-01-21 | 2022-01-18 | 2022-01-22 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 121784512 | B022/493 | T3 DI DRM-GRS VLY-WMR B22/493 INST IBWW | SACTO | ETL.6760.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2022-04-18 | 2022-01-19 | 2022-01-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45193834 | T3 DI DRM-GRS VLY-WMR B22/493 INST IBWW | ICW
LC | 121784820 | 006/157 | T3 DI COLGATE-ALLEGHANY 6/157 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2022-06-21 | 2022-01-19 | 2022-01-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45224638 | T3 DI COLGATE-ALLEGHANY 6/157 RPR STRW | ICW
LC | 121784963 | 010/066 | T2 EI OLEUM-G #1 010/066 RPL INSS | CONCORD | ETL.3150.INSL.CERA | 2021-07-23 | 2021-07-23 | 2022-05-12 | 2022-07-23 | 2022-07-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31595108 | T2 EI OLEUM-G #1 010/066 RPL INSS | 93K
LC | 121785063 | 019/525 | T3 DI COLGATE-ALLEGHANY 019/525 RPL INSW | SACTO | ETL.6470.INSL.CERA | 2021-07-23 | 2021-07-22 | 2022-06-13 | 2022-01-18 | 2022-01-22 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545810 | T3 DI COLGATE-ALLEGHANY 20/556 RPL INSW | 93I
LC | 121785192 | 012/065C | T2 DI KNGS RVR-SGR-RLY 012/065C RPR GYWS | FRESNO | ETL.2030.POLE.NWOD | 2021-07-23 | 2021-07-23 | 2022-03-02 | 2022-07-23 | 2022-07-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45066234 | T2 DI KNGS RVR-SGR-RLY 012/065C RPR GYWS | ICS
LC | 121785199 | 006/003 | T2 DI LYTNVLLE-COVELO 006/003 RPL STRW | WILLITS | ETL.7390.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2022-06-13 | 2022-07-23 | 2022-07-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31547421 | T2 DI LYTNVILLE-COVELO 1/6 RPL POLE | 70Y
LC | 121785216 | 010/272 | T3 WV CLGTE-ALGHNY 10/272 INST DMPW | SACTO | ETL.6470.INSL.NCER | 2021-07-23 | 2021-07-23 | 2022-06-18 | 2022-01-19 | 2022-01-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO | Missing | Damper-Wood | Install | 45224639 | T3 WV CLGTE-ALGHNY 10/272 INST DMPW | ICW
LC | 121785293 | 071/361 | T2 DI MALIN RND MTN #2 71/361 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-23 | 2021-07-23 | 2022-07-13 | 2022-07-23 | 2022-07-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215168 | T2 DI MALIN RND MTN #2 71/361 RPR OPGW | ICS
LC | 121785300 | T071 | T3 DI MIDWAY-SANTA MARIA T071 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-23 | 2022-05-04 | 2022-01-19 | 2022-01-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098928 | T3 DI MIDWAY-SANTA MARIA T071 RPR FOND | ICQ
LC | 121785338 | 000/001B | T3 DI DIABLO-MIDWAY #3 000/1B RPL HRDT | PISMOBCH | ETL.5980.TOWR | 2021-07-23 | 2021-07-23 | 2022-07-30 | 2022-01-19 | 2022-01-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45073823 | T3 DI DIABLO-MIDWAY #3 000/1B RPL HRDT | ICQ
LC | 121785665 | 016/140 | T2 EI DRUM-RIO OSO #1 16/140 RMV VEG | SACTO | ETL.1420.TOWR | 2021-07-23 | 2021-07-23 | 2022-05-24 | 2022-07-23 | 2022-07-23 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121785690 | T-108 | T3 DI MIDWAY-SANTA MARIA T-108 INS STEP | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 | 2022-05-09 | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | Missing | Hardware-Tower | Install | 45098929 | T3 DI MIDWAY-SANTA MARIA T-108 INS STEP | ICQ
LC | 121785858 | 010/105B | T3 DI GRN VLLY-CMP EVRS 10/105 RPL INSW | MOSSLNDG | ETL.1710.INSL.NCER | 2021-07-23 | 2021-07-21 | 2022-04-12 | 2022-01-17 | 2022-01-21 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579487 | T3 DI GRN VLY CMP EVRS 011/112C RPL INSW | 93I
LC | 121785859 | 010/105 | T3 DI GRN VLLY-CMP EVRS 10/105L RPR GYWW | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-07-23 | 2021-07-21 | 2022-03-07 | 2022-01-17 | 2022-01-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45166711 | T3 DI GRN VLLY-CMP EVRS 10/105L RPR GYWW | ICW
LC | 121785876 | 072/367 | T2 DI MALIN-RND MTN #2 72/367 RPR ANCS | TABLEMTN | ETL.6020.TOWR | 2021-07-23 | 2021-07-22 | 2022-07-18 | 2022-07-22 | 2022-07-22 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair | 45194113 | T2 DI MALIN-RND MTN #2 72/367 RPR ANCS | ICS
LC | 121785940 | 018/148A | T3 DI PARADISE-TBL MTN 18/148A RMV BUTT | TABLEMTN | ETL.4316.POLE.NWOD | 2021-07-23 | 2021-07-21 | 2022-07-18 | 2022-01-17 | 2022-01-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45240518 | T3 DI PARADISE-TBL MTN 18/148A RMV BUTT | ICW
LC | 121786022 | 072/367 | T2 DI MALIN-RND MTN #2 72/367 RPR FOND | TABLEMTN | ETL.6020.TOWR | 2021-07-23 | 2021-07-22 | 2022-07-18 | 2022-07-22 | 2022-07-22 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45197656 | T2 DI MALIN-RND MTN #2 72/367 RPR FOND | ICQ
LC | 121786026 | T068 | T3 DI MIDWAY-SANTA MARIA T068 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 | 2022-05-04 | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098930 | T3 DI MIDWAY-SANTA MARIA T068 RPR FOND | ICQ
LC | 121786257 | 006/008 | T2 DI LAYTONVILLE-COVELO 6/8 RPL STRW | WILLITS | ETL.7390.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2022-06-13 | 2022-07-23 | 2022-07-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544413 | T2 DI LAYTONVILLE-COVELO 06/06C RPL STRW | 70Y
LC | 121786409 | T090 | T3 DI MIDWY-SNTA MARA(12KV)T090 RPL HRDT | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-23 | 2022-08-25 | 2022-01-19 | 2022-01-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45098931 | T3 DI MIDWY-SNTA MARA(12KV)T090 RPL HRDT | ICQ
LC | 121786741 | 106/001A | T2 DI HUMBOLDT-TRINITY 106/1A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2021-07-23 | 2021-07-14 | 2022-01-22 | 2022-07-14 | 2022-07-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45128326 | T2 DI HUMBOLDT-TRINITY 106/1A RPR GYWW | ICW
LC | 121787011 | 018/148B | T3 DI PARADISE-TBL MTN 18/148B RMV BUTT | TABLEMTN | ETL.4316.POLE.NWOD | 2021-07-23 | 2021-07-21 | 2022-07-19 | 2022-01-17 | 2022-01-21 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45240541 | T3 DI PARADISE-TBL MTN 18/148B RMV BUTT | ICW
LC | 121787165 | 011/089B | T2 DI PIT#6 JCT-RND MTN 11/089B RMV DBRS | TABLEMTN | ETL.5440.POLE.NWOD | 2021-07-23 | 2021-07-20 | 2022-06-09 | 2022-07-20 | 2022-07-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45213826 | T2 DI PIT#6 JCT-RND MTN 11/089B RMV DBRS | ICW
LC | 121787299 | 029/000 | T2 DI GARBERVILLE-LYTNVLLE 29/0 RPL HRDD | WILLITS | ETL.8365.POLE.WDPS | 2021-07-23 | 2021-07-23 | 2022-04-22 | 2022-07-23 | 2022-07-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45155529 | T2 DI GARBERVILLE-LYTNVLLE 29/0 RPL HRDD | ICW
LC | 121787417 | T079 | T3 DI MIDWAY-SANTA MARIA T079 RPR STRT | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 | 2022-08-25 | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45098933 | T3 DI MIDWAY-SANTA MARIA T079 RPR STRT | ICQ
LC | 121787522 | T072 | T3 DI MIDWAY-SANTA MARIA T072 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 | 2022-01-26 | 2022-01-18 | 2022-01-22 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 121787656 | 080/405B | T2 DI MALIN-RND MTN #2 80/405B RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-23 | 2021-07-23 | 2021-07-18 | 2022-07-23 | 2022-07-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215166 | T2 DI MALIN-RND MTN #2 80/405A RPR OPGW | ICS
LC | 121789403 | T064 | T3 DI MIDWAY-SANTA MARIA T064 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-24 | 2021-07-22 | 2022-05-09 | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098934 | T3 DI MIDWAY-SANTA MARIA T064 RPR FOND | ICQ
LC | 121789963 | T-115 | T3 DI MDWY-SNTA MARA(12KV) T115 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-24 | 2021-07-23 | 2022-08-31 | 2022-01-19 | 2022-01-23 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548619 | T3 EI MIDWAY-SANTA MARIA RPL INSS 8TWRS | 93K
LC | 121790043 | T-115 | T3 DI MDWY-SNTA MARA(12KV) T115 RPR STRT | PISMOBCH | ETL.9240.TOWR | 2021-07-24 | 2021-07-23 | 2022-08-30 | 2022-01-19 | 2022-01-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45098935 | T3 DI MDWY-SNTA MARA(12KV) T115 RPR STRT | ICQ
LC | 121790561 | 009/050 | T3 DI MNT VST-CYT SW ST 9/50 RPL INSS | MOSSLNDG | ETL.5090.INSL | 2021-07-24 | 2021-07-24 | 2022-06-08 | 2022-01-20 | 2022-01-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549063 | T3 DI MNT VST-CYT SW ST 9/50 RPL INSS | 93K
LC | 121790711 | T-117 | T3 DI MIDWAY-SANTA MARIA T-117 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-24 | 2021-07-23 | 2022-08-30 | 2022-01-19 | 2022-01-23 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548619 | T3 EI MIDWAY-SANTA MARIA RPL INSS 8TWRS | 93K
LC | 121790713 | T-117 | T3 DI MIDWAY-SANTA MARIA T-117 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-24 | 2021-07-23 | 2022-08-26 | 2022-01-19 | 2022-01-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098939 | T3 DI MIDWAY-SANTA MARIA T-117 RPR FOND | ICQ
LC | 121790897 | 002/025 | T2 DI NARROWS #2 TAP 02/25 RMV DBRS | SACTO | ETL.6521.POLE.WDPS | 2021-07-24 | 2021-07-20 | 2022-06-03 | 2022-07-20 | 2022-07-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45224720 | T2 DI NARROWS #2 TAP 02/25 RMV DBRS | ICW
LC | 121791090 | T057 | T3 DI MIDWAY-SANTA MARIA T057 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-24 | 2021-07-24 | 2022-01-27 | 2022-01-20 | 2022-01-24 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 121791216 | T078 | T3 DI MDWY-SNTA MRA T078 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-24 | 2021-07-22 | 2022-05-04 | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098940 | T3 DI MDWY-SNTA MRA T078 RPR FOND | ICQ
LC | 121791435 | T092 | T3 DI MDWY-SNTA MARIA T092 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-24 | 2021-07-22 | 2022-05-19 | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098941 | T3 DI MDWY-SNTA MARIA T092 RPR FOND | ICQ
LC | 121792267 | T-110 | T3 DI MIDWAY-SANTA MARIA T-110 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-25 | 2021-07-23 | 2022-07-18 | 2022-01-19 | 2022-01-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45098942 | T3 DI MIDWAY-SANTA MARIA T-110 RPR FOND | ICQ
LC | 121792268 | 004/051 | T2 DI BURNS-LONE STR #1 004/051 RPL INSW | MOSSLNDG | ETL.6230.POLE.WDPS | 2021-07-25 | 2021-07-24 | 2022-02-09 | 2022-07-24 | 2022-07-24 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31578758 | T2 DI BURNS-LONE STR #1 004/051 RPL INSW | 93I
LC | 121792269 | 004/051 | T2 DI BURNS-LONE STR #1 004/051 RMV DEBR | MOSSLNDG | ETL.6230.POLE.WDPS | 2021-07-25 | 2021-07-24 | 2022-01-13 | 2022-07-24 | 2022-07-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45144663 | T2 DI BURNS-LONE STR #1 004/051 RMV DEBR | ICW
LC | 121792348 | T-116 | T3 DI MIDWAY-SANTA MARIA T-116 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-25 | 2021-07-23 | 2022-08-26 | 2022-01-19 | 2022-01-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45098943 | T3 DI MIDWAY-SANTA MARIA T-116 RPR FOND | ICQ
LC | 121792349 | T-116 | T3 DI MIDWAY-SANTA MARIA T-116 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-25 | 2021-07-23 | 2022-08-31 | 2022-01-19 | 2022-01-23 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548619 | T3 EI MIDWAY-SANTA MARIA RPL INSS 8TWRS | 93K
LC | 121792660 | T-116 | T3 DI MIDWAY-SANTA MARIA T-116 RPL STEP | PISMOBCH | ETL.9240.TOWR | 2021-07-25 | 2021-07-23 | 2022-08-26 | 2022-01-19 | 2022-01-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45098944 | T3 DI MIDWAY-SANTA MARIA T-116 RPL STEP | ICQ
LC | 121792767 | 070/354 | T2 DI MALIN-RND MTN #2 070/354 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-07-25 | 2021-07-22 | 2022-07-14 | 2022-07-22 | 2022-07-22 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215165 | T2 DI MALIN-RND MTN #2 070/354 RPR SHLS | ICS
LC | 121792769 | 090/460B | T2 DI MALIN-RND MTN #2 90/460A RPL HRDT | TABLEMTN | ETL.6020.TOWR | 2021-07-25 | 2021-07-23 | 2022-07-15 | 2022-07-23 | 2022-07-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45198271 | T2 DI MALIN-RND MTN #2 90/460A RPL HRDT | ICQ
LC | 121792980 | 038/179 | T2 DI LKVLLE-SBRNTE 038/179 RPR FOND | CONCORD | ETL.4920.TOWR | 2021-07-25 | 2021-07-23 | 2022-03-29 | 2022-07-23 | 2022-07-23 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190699 | T2 DI LKVLLE-SBRNTE 038/179 RPR FOND | ICQ
LC | 121792981 | 038/179 | T2 DI LKVLLE-SBRNTE #2 38/179 RPL INSS | CONCORD | ETL.4960.INSL | 2021-07-25 | 2021-07-23 | 2022-01-27 | 2022-07-23 | 2022-07-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31542274 | T2 DI LKVILLE-SBRNTE #2 RPL INSS 3 TWRS | 93K
LC | 121792982 | T-114 | T3 DI MIDWAY-SANTA MARIA T-114 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-25 | 2021-07-23 | 2022-08-26 | 2022-01-19 | 2022-01-23 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45098945 | T3 DI MIDWAY-SANTA MARIA T-114 RPR FOND | ICQ
LC | 121794559 | 012/246 | T2 DI COTTONWD-RED BLUFF 12/246 RPR STRW | TABLEMTN | ETL.6660.POLE.WOOD | 2021-07-26 | 2021-07-23 | 2022-06-22 | 2022-07-23 | 2022-07-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45242430 | T2 DI COTTONWD-RED BLUFF 12/246 RPR STRW | ICW
LC | 121794702 | 010/066 | T2 EI OLEUM-G #2 010/066 RPL INSS | CONCORD | ETL.3160.INSL.CERA | 2021-07-26 | 2021-07-23 | 2022-05-13 | 2022-07-23 | 2022-07-23 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31595110 | T2 EI OLEUM-G #2 010/066 RPL INSS | 93K
LC | 121795133 | T-103 | T3 DI MIDWAY-SANTA MARIA T-103 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2022-08-31 | 2022-01-22 | 2022-01-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548618 | T3 DI MIDWAY-SANTA MARIA RPL INSS 6TWRS | 93K
LC | 121795134 | T-103 | T3 DI MIDWAY-SANTA MARIA T-103 RPR STRT | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2022-08-31 | 2022-01-22 | 2022-01-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45098946 | T3 DI MIDWAY-SANTA MARIA T-103 RPR STRT | ICQ
LC | 121795440 | 011/091 | T2 DI PIT #3-PIT #1 011/091 RPR FOND | TABLEMTN | ETL.5400.TOWR | 2021-07-26 | 2021-07-24 | 2022-07-26 | 2022-07-24 | 2022-07-24 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45195473 | T2 DI PIT #3-PIT #1 011/091 RPR FOND | ICQ
LC | 121795442 | T-120 | T3 DI MIDWAY-SANTA MARIA T-120 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2021-12-15 | 2022-01-22 | 2022-01-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 121795883 | 022/113 | T3 DI RND MTN-TBL MTN #1 22/113 RPL INSS | TABLEMTN | ETL.6060.INSL | 2021-07-26 | 2021-07-24 | 2022-05-13 | 2022-01-20 | 2022-01-24 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548204 | T3 DI RND MTN-TBL MTN #1 RPLC INSS 8 TWR | 93K
LC | 121796309 | T-101 | T3 DI MIDWAY-SANTA MARIA T-101 RPR INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2021-10-29 | 2022-01-22 | 2022-01-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44938198 | T3 DI MIDWAY-SANTA MARIA T-101 RPR INSS | ICS
LC | 121796544 | T-102 | T3 DI MIDWAY-SANTA MARIA T-102 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2022-08-30 | 2022-01-22 | 2022-01-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548618 | T3 DI MIDWAY-SANTA MARIA RPL INSS 6TWRS | 93K
LC | 121796549 | T-102 | T3 DI MIDWAY-SANTA MARIA T-102 INST STEP | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2022-07-19 | 2022-01-22 | 2022-01-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45098948 | T3 DI MIDWAY-SANTA MARIA T-102 INST STEP | ICQ
LC | 121796730 | T-113 | T3 DI MIDWAY-SANTA MARIA T-113 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2021-12-16 | 2022-01-22 | 2022-01-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121796733 | T-113 | T3 DI MIDWAY-SANTA MARIA T-113 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2022-08-26 | 2022-01-22 | 2022-01-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098949 | T3 DI MIDWAY-SANTA MARIA T-113 RPR FOND | ICQ
LC | 121796816 | 008/071 | T3 DI MIDDLE FRK-GOLD HILL 8/71 RPR INSS | SACTO | ETL.5140.INSL.NCER | 2021-07-26 | 2021-07-24 | 2022-10-02 | 2022-01-20 | 2022-01-24 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45017217 | T3 DI MIDDLE FRK-GOLD HILL 8/71 RPR INSS | ICS
LC | 121797003 | T098 | T3 DI MIDWAY-SANTA MARIA T098 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2022-05-19 | 2022-01-22 | 2022-01-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098951 | T3 DI MIDWAY-SANTA MARIA T098 RPR FOND | ICQ
LC | 121797205 | 016/136 | T3 DI PARADISE TBL MTN 016/136 RPR INSW | TABLEMTN | ETL.4316.INSL.NCER | 2021-07-26 | 2021-07-22 | 2022-02-24 | 2022-01-18 | 2022-01-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45195730 | T3 DI PARADISE TBL MTN 016/136 RPR INSW | ICW
LC | 121797208 | 016/136 | T3 DI PARADISE TBL MTN 016/136 RPR STRW | TABLEMTN | ETL.4316.POLE.STPS | 2021-07-26 | 2021-07-22 | 2022-02-24 | 2022-01-18 | 2022-01-22 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45194514 | T3 DI PARADISE TBL MTN 016/136 RPR STRW | ICW
LC | 121797465 | T-122 | T3 DI MIDWAY-SANTA MARIA T-122 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2022-08-26 | 2022-01-22 | 2022-01-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45098954 | T3 DI MIDWAY-SANTA MARIA T-122 RPR FOND | ICQ
LC | 121797466 | T-122 | T3 DI MIDWAY-SANTA MARIA T-122 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2021-12-13 | 2022-01-22 | 2022-01-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 121797497 | T099 | T3 DI MIDWAY-SANTA MARIA T099 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2021-10-29 | 2022-01-22 | 2022-01-26 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548178 | T3DI MIDWY-SNTA MARA RPL INSS 2TWRS | 93K
LC | 121797572 | 068/347 | T2 DI MALIN-ROUND MTN#2 68/347 RPR ANCS | TABLEMTN | ETL.6020.TOWR | 2021-07-26 | 2021-07-26 | 2022-07-20 | 2022-07-26 | 2022-07-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair | 45194403 | T2 DI MALIN-ROUND MTN#2 68/347 RPR ANCS | ICS
LC | 121797717 | 003/020 | T3 DI DIABLO-GATES #1 3/20 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2021-07-26 | 2021-07-26 | 2022-07-12 | 2022-01-22 | 2022-01-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068527 | T3 DI DIABLO-GATES #1 3/20 RPR GYWS | ICS
LC | 121797797 | 031/001 | T2 DI GRBRVLL-LAYTONVILLE 31/1 RPR GYWW | WILLITS | ETL.8365.POLE.WOOD | 2021-07-26 | 2021-07-24 | 2022-04-22 | 2022-07-24 | 2022-07-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45155544 | T2 DI GRBRVLL-LAYTONVILLE 31/1 RPR GYWW | ICW
LC | 121797927 | 012/107 | T3 DI CTTNWOOD-BENTON#2 12/107 RPR CNDW | TABLEMTN | ETL.6650.INSL.CERA | 2021-07-26 | 2021-07-26 | 2022-06-03 | 2022-01-22 | 2022-01-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45213320 | T3 DI CTTNWOOD-BENTON#2 12/107 RPR CNDW | ICW
LC | 121798013 | 003/057 | T3 DI MIDDLE FORK #1 003/057 RPL HRDD | SACTO | ETL.8405.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2022-08-06 | 2022-01-22 | 2022-01-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45017215 | T3 DI MIDDLE FORK #1 003/057 RPL HRDD | ICW
LC | 121798910 | 020/475 | T2 DI DRUM-GRSS VLLY WMR 20/475 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2022-03-31 | 2022-07-26 | 2022-07-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45193835 | T2 DI DRUM-GRSS VLLY WMR 20/475 RPR STRW | ICW
LC | 121799128 | T051 | T3 DI MIDWAY-SANTA MARIA T051 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2022-08-31 | 2022-01-22 | 2022-01-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548616 | T3 DI MIDWAY-SANTA MARIA RPL INSS 7TWRS | 93K
LC | 121800378 | 004/069C | T3 DI SISQUOC-GAREY 004/069C RPR INSW | PISMOBCH | ETL.3690.INSL.CERA | 2021-07-26 | 2021-07-26 | 2022-02-08 | 2022-01-22 | 2022-01-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45069435 | T3 DI SISQUOC-GAREY 004/069C RPR INSW | ICW
LC | 121800647 | 001/009 | T2 DI PIT #5-RND MTN #1 001/009 RPL HRDW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-26 | 2021-07-24 | 2022-07-16 | 2022-07-24 | 2022-07-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213321 | T2 DI PIT #5-RND MTN #1 001/009 RPL HRDW | ICW
LC | 121800648 | 020/003 | T2 DI MNDCN WLTS FT BRG 020/003 RMV BUTT | WILLITS | ETL.7550.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2022-07-17 | 2022-07-26 | 2022-07-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45145824 | T2 DI MNDCN WLTS FT BRG 020/003 RMV BUTT | ICW
LC | 121800670 | 020/003 | T2 DI MNDCN WLTS FT BRG 020/003 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2022-08-26 | 2022-07-26 | 2022-07-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45145824 | T2 DI MNDCN WLTS FT BRG 020/003 RMV BUTT | ICW
LC | 121801638 | 002/058 | T3 DI COLGATE-CHALLENGE 2/58 RPR STRW | SACTO | ETL.6480.POLE.WOOD | 2021-07-27 | 2021-07-26 | 2022-08-25 | 2022-01-22 | 2022-01-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45253260 | T3 DI COLGATE-CHALLENGE 2/58 RPR STRW | ICW
LC | 121801728 | T-123 | T3 DI MIDWAY-SANTA MARIA T-123 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-27 | 2021-07-26 | 2022-05-02 | 2022-01-22 | 2022-01-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098957 | T3 DI MIDWAY-SANTA MARIA T-123 RPR FOND | ICQ
LC | 121802212 | 004/050 | T2 DI BURNS-LONE STAR #1 4/50R RPR STRW | MOSSLNDG | ETL.6230.POLE.WDPS | 2021-07-27 | 2021-07-26 | 2022-02-16 | 2022-07-26 | 2022-07-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45166607 | T2 DI BURNS-LONE STAR #1 4/50R RPR STRW | ICW
LC | 121802215 | 004/050 | T2 DI BURNS-LONE STAR #1 4/50R RPR GYWW | MOSSLNDG | ETL.6230.POLE.WDPS | 2021-07-27 | 2021-07-26 | 2022-01-12 | 2022-07-26 | 2022-07-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45161109 | T2 DI BURNS-LONE STAR #1 4/50R RPR GYWW | ICW
LC | 121802317 | 053/265 | T2 DI MALIN-RND MTN #2 53/265 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-07-27 | 2021-07-26 | 2022-07-15 | 2022-07-26 | 2022-07-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215164 | T2 DI MALIN-RND MTN #2 53/265 RPR SHLS | ICS
LC | 121802319 | 001/017 | T2 CHRISTIE-FRANKLIN #2 1/17 RPL STRW | CONCORD | ETL.6360.POLE.WDPS | 2021-07-27 | 2021-07-27 | 2022-02-12 | 2022-07-27 | 2022-07-27 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31549730 | T2 CHRISTIE-FRANKLIN #2 1/17 RPL STRW | 70Y
LC | 121802551 | 001/017 | T2 CHRISTIE-FRANKLIN #2 1/17 RPL STRW | CONCORD | ETL.6360.POLE.WDPS | 2021-07-27 | 2021-07-27 | 2022-02-12 | 2022-07-27 | 2022-07-27 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31549730 | T2 CHRISTIE-FRANKLIN #2 1/17 RPL STRW | 70Y
LC | 121803005 | 071/358 | T2 DI MALIN-RND MTN #2 71/358 RPL SHLS | TABLEMTN | ETL.6020.TOWR | 2021-07-27 | 2021-07-26 | 2022-07-13 | 2022-07-26 | 2022-07-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 45215163 | T2 DI MALIN-RND MTN #2 71/358 RPL SHLS | ICS
LC | 121803402 | 068/346A | T2 DI MALIN-RND MTN #2 68/346A RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-27 | 2021-07-26 | 2022-07-14 | 2022-07-26 | 2022-07-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215162 | T2 DI MALIN-RND MTN #2 68/346A RPR OPGW | ICS
LC | 121803404 | 011/100 | T3 DI CTTNWD-BENTON #2 11/100 RMV DBRS | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-27 | 2021-07-26 | 2022-06-14 | 2022-01-22 | 2022-01-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45213322 | T3NT DI CTTNWD-BENTON #2 11/100 RMV DBRS | ICW
LC | 121803708 | 010/117 | T2 DI DRUM-SUMMIT #2 010/117 RPL INSW | SACTO | ETL.1450.INSL.CERA | 2021-07-27 | 2021-07-26 | 2022-10-18 | 2022-07-26 | 2022-07-26 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31611092 | T2 DI DRUM-SUMMIT #2 010/117 RPR INSW | 93I
LC | 121803751 | ?004/000 | T3 DI SNEATH LN-HLF MN BY ?4/0 RPR STRW | METCALF | ETL.7212.POLE.WOOD | 2021-07-27 | 2021-07-26 | 2022-07-20 | 2022-01-22 | 2022-01-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45181107 | T3 DI SNEATH LN-HLF MN BY ?4/0 RPR STRW | ICW
LC | 121803870 | 002/014 | T3 DI DIABLO-GATES #1 2/14 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2021-07-27 | 2021-07-26 | 2022-06-09 | 2022-01-22 | 2022-01-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068529 | T3 DI DIABLO-GATES #1 2/14 RPR GYWS | ICS
LC | 121803874 | 000/002 | T3 DI DIABLO-MIDWAY #2 0/2 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-07-27 | 2021-07-26 | 2022-07-31 | 2022-01-22 | 2022-01-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45090044 | T3 DI DIABLO-MIDWAY #2 0/2 RPR GYWS | ICS
LC | 121803879 | 002/060 | T3 DI DRUM-SPAULDING 002/060 RPL HRDW | SACTO | ETL.6770.POLE.WOOD | 2021-07-27 | 2021-07-26 | 2022-05-21 | 2022-01-22 | 2022-01-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45218814 | T3 DI DRUM-SPAULDING 002/060 RPL HRDW | ICW
LC | 121805495 | T-122 | T3 EI MIDWAY-SANTA MARIA T-122 RPR STRT | PISMOBCH | ETL.9240.TOWR | 2021-07-27 | 2021-07-27 | 2022-08-26 | 2022-01-23 | 2022-01-27 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45098958 | T3 EI MIDWAY-SANTA MARIA T-122 RPR STRT | ICQ
LC | 121805498 | T-120 | T3 EI MIDWAY-SANTA MARIA T-120 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-27 | 2021-07-27 | 2022-08-30 | 2022-01-23 | 2022-01-27 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548619 | T3 EI MIDWAY-SANTA MARIA RPL INSS 8TWRS | 93K
LC | 121806234 | 001/012 | T2 EI KANAKA TAP 001/012L COMPLETE | TABLEMTN | ETL.4223.POLE.WDPS | 2021-07-28 | 2021-03-18 | 2022-06-03 | 2022-03-18 | 2022-03-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544831 | T2 EI KANAKA TAP 001/012B RPL STRW | 70Y
LC | 121806235 | 001/012 | T2 EI KANAKA TAP 001/012R RPL STRW | TABLEMTN | ETL.4223.POLE.WDPS | 2021-07-28 | 2021-03-18 | 2022-06-03 | 2022-03-18 | 2022-03-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544831 | T2 EI KANAKA TAP 001/012B RPL STRW | 70Y
LC | 121806251 | 004/100 | T3 DI BURNS-LONE STAR #2 4/100 RPR GYWW | MOSSLNDG | ETL.6240.POLE.WOOD | 2021-07-28 | 2021-07-26 | 2022-04-06 | 2022-01-22 | 2022-01-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45075345 | T3 DI BURNS-LONE STAR #2 4/100 RPR GYWW | ICW
LC | 121806258 | 022/113 | T3 DI RND MT-TM #2 22/113 RPL INS CMPLT | TABLEMTN | ETL.6070.INSL | 2021-07-28 | 2021-07-26 | 2022-05-18 | 2022-01-22 | 2022-01-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548820 | T3 DI RND MTN-TBL MTN #2 RPL INS 5TWR | 93K
LC | 121806353 | 002/015 | T3 DI DIABLO-GATES #1 2/15 CNCL | PISMOBCH | ETL.5960.TOWR | 2021-07-28 | 2021-07-26 | 2022-06-09 | 2022-01-22 | 2022-01-26 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068530 | T3 DI DIABLO-GATES #1 2/15 RPR GYWS | ICS
LC | 121806512 | 010/011C | T3 DI MAPLE CREEK-HOOPA 10/11C RPL STRW | EUREKA | ETL.7490.POLE.WOOD | 2021-07-28 | 2021-07-26 | 2022-08-03 | 2022-01-22 | 2022-01-26 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31548069 | T3 DI MAPLE CREEK-HOOPA 11/4A RPL STRW | 70Y
LC | 121806904 | 005/073 | T2 DI VALLEY SPRINGS-CLAY 5/73 RMV BUTT | VICTOR | ETL.8264.POLE.WOOD | 2021-07-28 | 2021-07-26 | 2021-08-26 | 2022-07-26 | 2022-07-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44959194 | T2 DI VALLEY SPRINGS-CLAY 5/73 RMV BUTT | ICW
LC | 121806907 | 005/073 | T2 DI VALLEY SPRINGS-CLAY 5/73 RPR STRW | VICTOR | ETL.8264.POLE.WOOD | 2021-07-28 | 2021-07-26 | 2021-08-26 | 2022-07-26 | 2022-07-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR FRAB | No Good/Out of Stdrd | Splice-Wood | Repair | 44959341 | T2 DI VALLEY SPRINGS-CLAY 5/73 RPR STRW | ICW
LC | 121807345 | 017/003 | T2 DI HMBLDT BY-RO DLL JT 17/3 RPL INSW | EUREKA | ETL.7100.INSL.CERA | 2021-07-28 | 2021-07-26 | 2022-04-24 | 2022-07-26 | 2022-07-26 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542056 | T2 DI HMBLDT BY-RIO DL JCT 18/1 RPL INSW | 93I
LC | 121807462 | 032/004 | T2 DI GRBRVLL-LAYTONVILLE 32/4 RMV DBRS | WILLITS | ETL.8365.POLE.NWOD | 2021-07-28 | 2021-07-26 | 2022-04-22 | 2022-07-26 | 2022-07-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45155548 | T2 DI GRBRVLL-LAYTONVILLE 32/4 RMV DBRS | ICW
LC | 121808205 | 015/003 | T3 DI DONNELLS-MI-WUK 015/3L RPR STRW | VICTOR | ETL.1400.POLE.WDPS | 2021-07-28 | 2021-07-26 | 2022-08-29 | 2022-01-22 | 2022-01-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45122759 | T3 DI DONNELLS-MI-WUK 015/3L RPR STRW | ICW
LC | 121808209 | 028/005 | T2 DI GARBERVLLE-LAYTNVLLE 28/5 RPR GYWW | WILLITS | ETL.8365.POLE.WOOD | 2021-07-28 | 2021-07-27 | 2022-04-21 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45155528 | T2 DI GARBERVLLE-LAYTNVLLE 28/5 RPR GYWW | ICW
LC | 121808350 | 073/371 | T2 DI MALIN-RND MTN #2 73/371 RPR FOND | TABLEMTN | ETL.6020.TOWR | 2021-07-28 | 2021-07-26 | 2022-07-20 | 2022-07-26 | 2022-07-26 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45198240 | T2 DI MALIN-RND MTN #2 73/371 RPR FOND | ICQ
LC | 121809216 | 030/008 | T2 DI GARBERVLLE-LAYTNVLLE 30/8 RPL INSW | WILLITS | ETL.8365.INSL.CERA | 2021-07-28 | 2021-07-26 | 2022-04-22 | 2022-07-26 | 2022-07-26 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542897 | T2 EI GRBRVLL-LYTNVILLE 31/7 RPL INSW | 93I
LC | 121809408 | 011/118 | T2 DI PT#5-RD MN#2 11/118 RPR POLE CMPLT | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-28 | 2021-07-27 | 2022-06-08 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213778 | T2 DI PIT #5-RND MTN #2 11/118 RPR STRW | ICW
LC | 121809725 | 001/009 | T2 DI DIVIDE-VNDNBRG #2 1/9 INS HRDW | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-28 | 2021-07-27 | 2022-02-14 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Wood | Install | 45090081 | T2 DI DIVIDE-VNDNBRG #2 1/9 INS HRDW | ICW
LC | 121809756 | 009/171 | T2 DI PT#1-HT CRK #2-BRNY 9/171 INS HRDW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-07-28 | 2021-07-26 | 2022-07-19 | 2022-07-26 | 2022-07-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45213913 | T2 DI PT#1-HT CRK #2-BRNY 9/171 INS HRDW | ICW
LC | 121809844 | 017/000 | T2 DI HMBLDT BY-RIO DL JCT 17/0 RMV BUTT | EUREKA | ETL.7100.POLE.WOOD | 2021-07-28 | 2021-07-27 | 2022-02-14 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45155864 | T2 DI HMBLDT BY-RIO DL JCT 17/0 RMV BUTT | ICW
LC | 121809886 | X000/002 | T3 DI MORRO BAY-DIABLO X000/002 RPL INSS | PISMOBCH | ETL.5260.INSL.CERA | 2021-07-28 | 2021-07-26 | 2022-07-31 | 2022-01-22 | 2022-01-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548991 | T2 DI MORRO BAY-DIABLO 3/15 RPL INSS | 93K
LC | 121809972 | 029/002 | T2 DI GARBERVILLE-LYTNVL 29/2 RPLC HRDW | WILLITS | ETL.8365.POLE.WOOD | 2021-07-28 | 2021-07-27 | 2022-04-22 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45155530 | T2 DI GARBERVILLE-LYTNVL 29/2 RPLC HRDW | ICW
LC | 121810019 | 017/124 | T2 DI CARIBOU-TABLE MTN 017/124 RPR GYWS | TABLEMTN | ETL.4440.POLE.STPS | 2021-07-28 | 2021-07-28 | 2022-06-24 | 2022-07-28 | 2022-07-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45195472 | T2 DI CARIBOU-TABLE MTN 017/124 RPR GYWS | ICS
LC | 121810023 | 025/374 | T3 DI GOLD HILL #1 025/374 RPR INSW | SACTO | ETL.6950.INSL.NCER | 2021-07-28 | 2021-07-28 | 2022-11-10 | 2022-01-24 | 2022-01-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45218208 | T3 DI GOLD HILL #1 025/374 RPR INSW | ICW
LC | 121810032 | 001/035 | T3 DI MIDDLEFORK #1/35 RPR GYWW | SACTO | ETL.8405.POLE.WOOD | 2021-07-28 | 2021-07-27 | 2021-10-21 | 2022-01-23 | 2022-01-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45017213 | T3 DI MIDDLEFORK #1/35 RPR GYWW | ICW
LC | 121810034 | 000/001C | T3 DI DIABLO-GATES #1 0/1C RPL HRDT CMT | PISMOBCH | ETL.5960.TOWR | 2021-07-28 | 2021-07-27 | 2022-08-04 | 2022-01-23 | 2022-01-27 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45070726 | T3 DI DIABLO-GATES #1 0/1C RPL HRDT | ICQ
LC | 121810073 | 007/038 | T2 DI FULTON-PUEBLO-TOWER 7/38 RPL INSS | LAKEVLLE | ETL.1600.INSL | 2021-07-28 | 2021-07-27 | 2021-10-19 | 2022-07-27 | 2022-07-27 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548751 | DI FULTON-PUEBLO-TOWER 7/38 RPL INSS | 93K
LC | 121810077 | 007/038 | T2 DI SILVERADO-FULTON JCT 7/38 RPL INSS | LAKEVLLE | ETL.1610.INSL | 2021-07-28 | 2021-07-27 | 2022-03-13 | 2022-07-27 | 2022-07-27 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548683 | T2 DI SILVERADO-FULTON JCT RPL INSS 6TW | 93K
LC | 121810084 | 023/002 | T2 DI GARBERVLLE-LAYTNVLLE 23/2 RPR CNDW | WILLITS | ETL.8365.POLE.WOOD | 2021-07-28 | 2021-07-26 | 2022-04-11 | 2022-07-26 | 2022-07-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Conductor-Wood | Repair | 45155498 | T2 DI GARBERVLLE-LAYTNVLLE 23/2 RPR CNDW | ICW
LC | 121810092 | 004/058 | T3 DI WST PT-VLY SPRNGS 004/058 RPR STRW | VICTOR | ETL.8350.POLE.WOOD | 2021-07-28 | 2021-07-28 | 2022-05-14 | 2022-01-24 | 2022-01-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45164568 | T3 DI WST PT-VLY SPRNGS 004/058 RPR STRW | ICW
LC | 121810115 | 014/121 | T3 DI MONTA VISTA-BURNS 14/121 RP SWTC | MOSSLNDG | ETL.7590.SWIT | 2021-07-28 | 2021-07-28 | 2022-03-02 | 2022-01-24 | 2022-01-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Switch-Wood | Repair | 45082488 | T3 DI MONTA VISTA-BURNS 14/121 RP SWTC | ICW
LC | 121810117 | 007/073 | T2 DI PIT #5-ROUND MTN #2 7/73 RMV BUTT | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-28 | 2021-07-26 | 2022-06-16 | 2022-07-26 | 2022-07-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45213776 | T2 DI PIT #5-ROUND MTN #2 7/73 RMV BUTT | ICW
LC | 121810118 | 008/039 | T2 DI FULTON-PUEBLO 08/39 RPL INSS | LAKEVLLE | ETL.1600.INSL | 2021-07-28 | 2021-07-27 | 2022-02-23 | 2022-07-27 | 2022-07-27 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549865 | T2 DI FULTON-PUEBLO-INSUL RPL INSS 5TWR | 93K
LC | 121810137 | 001/010 | T3 DI MORAGA-OAKLAND #3 1/10 RPL HRDT | CONCORD | ETL.2740.TOWR | 2021-07-28 | 2021-07-26 | 2022-08-28 | 2022-01-22 | 2022-01-26 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45094455 | T3 DI MORAGA-OAKLAND #3 1/10 RPL HRDT | ICQ
LC | 121810141 | 015/097 | T2 METCALF-GREEN VALLEY 15/097 RPL ANCW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-07-28 | 2021-07-28 | 2021-09-18 | 2022-07-28 | 2022-07-28 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31535758 | T2 EI METCALF-GRN VALLEY 15/97L RPL STRW | 70Y
LC | 121810176 | 015/097 | T2 METCALF-GREEN VALLEY 15/097 RPL ANCW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-07-28 | 2021-07-28 | 2021-09-18 | 2022-07-28 | 2022-07-28 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31535758 | T2 EI METCALF-GRN VALLEY 15/97L RPL STRW | 70Y
LC | 121810192 | 015/097 | T2 METCALF-GREEN VALLEY 15/097 RPL ANCW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-07-28 | 2021-07-28 | 2021-09-18 | 2022-07-28 | 2022-07-28 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31535758 | T2 EI METCALF-GRN VALLEY 15/97L RPL STRW | 70Y
LC | 121810200 | 032/006 | T2 DI GRBRVLLE-LYTNVLLE 032/006 RPR JUMW | WILLITS | ETL.8365.POLE.WOOD | 2021-07-28 | 2021-07-28 | 2022-04-22 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Jumper-Wood | Repair | 45155549 | T2 DI GRBRVLLE-LYTNVLLE 032/006 RPR JUMW | ICW
LC | 121810201 | 011/109 | T3 DI DRUM-HIGGINS 011/109 INS HRDD | SACTO | ETL.4393.POLE.WDPS | 2021-07-28 | 2021-07-27 | 2022-08-05 | 2022-01-23 | 2022-01-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR NTDE | Missing | Hardware-Wood | Install | 45219477 | T3 DI DRUM-HIGGINS 011/109 INS HRDD | ICW
LC | 121810212 | 012/001 | T2 DI OAKHURST TAP 12/1 RPLC INSS | FRESNO | ETL.1252.INSL.NCER | 2021-07-28 | 2021-07-27 | 2022-03-30 | 2022-07-27 | 2022-07-27 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579297 | T2 DI OAKHURST TAP NCINSUL 12/3 RPL INSW | 93I
LC | 121810214 | 025/000 | T2 DI GARBERVILLE-LYTNVL 25/0 RPR STRW | WILLITS | ETL.8365.POLE.WOOD | 2021-07-28 | 2021-07-26 | 2022-04-18 | 2022-07-26 | 2022-07-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45155521 | T2 DI GARBERVILLE-LYTNVL 25/0 RPR STRW | ICW
LC | 121810220 | 007/073 | T2 DI PIT #5-ROUND MTN #2 7/73 RPL INSW | TABLEMTN | ETL.5430.INSL.CERA | 2021-07-28 | 2021-07-26 | 2022-06-13 | 2022-07-26 | 2022-07-26 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547500 | T2 DI PIT #5-RND MTN #2 010/101 RPL INSW | 93I
LC | 121810221 | 008/039 | T2 DI SILVERADO-FULTON JCT 8/39 RPL INSS | LAKEVLLE | ETL.1610.INSL | 2021-07-28 | 2021-07-27 | 2022-03-13 | 2022-07-27 | 2022-07-27 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548683 | T2 DI SILVERADO-FULTON JCT RPL INSS 6TW | 93K
LC | 121810301 | 007/003 | T3 DI ULTON-CALISTOGA 7/3L RPR GYWW | LAKEVLLE | ETL.6880.POLE.STPS | 2021-07-28 | 2021-07-27 | 2022-09-13 | 2022-01-23 | 2022-01-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148359 | T3 DI FULTON-CALISTOGA 007/003 RPR GYWW | ICW
LC | 121810314 | 005/099 | T3 DI COLGATE-CHALLENGE 005/099 RPR SWTC | SACTO | ETL.6480.POLE.NWOD | 2021-07-28 | 2021-07-28 | 2022-08-07 | 2022-01-24 | 2022-01-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Switch-Wood | Repair | 44930513 | T3 DI COLGATE-CHALLENGE 005/099 RPR SWTC | ICW
LC | 121810316 | 028/006 | T2 DI GRBRVLLE-LYTNVLLE 028/6L RMV BUTT | EUREKA | ETL.8365.POLE.WDPS | 2021-07-28 | 2021-07-28 | 2021-12-02 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45082297 | T2 DI GRBRVLLE-LYTNVLLE 028/6L RMV BUTT | ICW
LC | 121810319 | 025/007 | T2 DI GRBRVLLE-LYTNVLLE 025/007 RPR STRW | WILLITS | ETL.8365.POLE.WOOD | 2021-07-28 | 2021-07-28 | 2022-04-25 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45155524 | T2 DI GRBRVLLE-LYTNVLLE 025/007 RPR STRW | ICW
LC | 121810352 | 089/452B | T2 DI MALIN-ROUND MTN#2 89/452A COMPLETE | TABLEMTN | ETL.6020.TOWR | 2021-07-28 | 2021-07-27 | 2022-04-19 | 2022-07-27 | 2022-07-27 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45198269 | T2 DI MALIN-ROUND MTN#2 89/452A RPR GYWS | ICS
LC | 121810382 | 003/067 | T2 DI SMRTSVLLE-NCLS #2 003/067 COMPLETE | SACTO | ETL.8000.POLE.NWOD | 2021-07-28 | 2021-07-28 | 2022-04-26 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45239504 | T2 DI SMRTSVLLE-NCLS #2 003/067 RMV BUTT | ICW
LC | 121810582 | 000/003 | T2 DI COLEMAN-CTTNWD 0/3 RPL STRW | TABLEMTN | ETL.6430.POLE.WOOD | 2021-07-28 | 2021-07-28 | 2022-05-16 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543020 | T2 DI COLEMN-CTTNWD 0/6 RPL STRW | 70Y
LC | 121810626 | :008/003 | T2 DI BLTA RVK MLNS SS :008/003 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-07-28 | 2021-07-28 | 2022-05-05 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536314 | T2 DI BLT-RVRBNK-MLNS RPL STRW | 70Y
LC | 121810631 | 004/000 | T2DI LAYTONVILLE-COVELO 04/00 RPR STRW | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-07-28 | 2021-07-27 | 2021-10-19 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44999934 | T2DI LAYTONVILLE-COVELO 04/00 RPR STRW | ICW
LC | 121810655 | 006/116 | T2 DI SMARTVIL-NICLAUS#2 6/116 RMV BUTT | SACTO | ETL.8000.POLE.NWOD | 2021-07-28 | 2021-07-27 | 2022-07-13 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45239505 | T2 DI SMARTVIL-NICLAUS#2 6/116 RMV BUTT | ICW
LC | 121810687 | 005/055B | T2 DI IGNACO-BOLNS #1 05/55B INS IBWW | LAKEVLLE | ETL.7140.INSL.CERA | 2021-07-28 | 2021-07-28 | 2022-01-14 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Replace | 45150007 | T2 DI IGNACO-BOLNS #1 05/55B INS IBWW | ICW
LC | 121810691 | 023/002 | T2 DI GRBRVLLE-LYTNVLLE 023/002 RPL DAMW | WILLITS | ETL.8365.POLE.WOOD | 2021-07-28 | 2021-07-27 | 2022-04-11 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Damper-Wood | Replace | 45155498 | T2 DI GARBERVLLE-LAYTNVLLE 23/2 RPR CNDW | ICW
LC | 121810699 | 005/062 | T2 DI PIT #5-RND MTN #1 5/62R RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-28 | 2021-07-27 | 2022-06-30 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213323 | T2 DI PIT #5-RND MTN #1 5/62R RPR STRW | ICW
LC | 121810740 | 005/062 | T2 DI PIT #5-RND MTN #1 5/62L RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-28 | 2021-07-27 | 2022-06-30 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213324 | T2 DI PIT #5-RND MTN #1 5/62L RPR STRW | ICW
LC | 121810743 | 003/000 | T2 DI LAYTONVILLE-COVELO 3/0 RPR STRW | WILLITS | ETL.7390.POLE.WOOD | 2021-07-28 | 2021-07-27 | 2022-06-10 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44999930 | T2 DI LAYTONVILLE-COVELO 3/0 RPR STRW | ICW
LC | 121810745 | 025/372 | T3 DI GOLD HILL #1 025/372 RPL STRW | SACTO | ETL.6950.POLE.WOOD | 2021-07-28 | 2021-07-28 | 2022-11-10 | 2022-01-24 | 2022-01-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548679 | T3 DI GOLD HILL #1 025/372 RPL STRW | 70Y
LC | 121810756 | 039/158 | T2 DI DIABLO-MIDWAY #2 39/158 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2021-07-28 | 2021-07-27 | 2022-06-21 | 2022-07-27 | 2022-07-27 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068579 | T2 DI DIABLO-MIDWAY #2 39/158 RPR GYWS | ICS
LC | 121810775 | 030/007 | T2 DI GARBERVL-LYTNVL 30/7 RPR STRW | WILLITS | ETL.8365.POLE.WOOD | 2021-07-28 | 2021-07-26 | 2022-04-22 | 2022-07-26 | 2022-07-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45155538 | T2 DI GARBERVL-LYTNVL 30/7 RPR STRW | ICW
LC | 121810777 | 030/007 | T2 DI GARBERVL-LYTNVL 30/7 RPR GYWW | WILLITS | ETL.8365.POLE.WOOD | 2021-07-28 | 2021-07-26 | 2022-04-22 | 2022-07-26 | 2022-07-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45155538 | T2 DI GARBERVL-LYTNVL 30/7 RPR STRW | ICW
LC | 121810800 | 003/029 | T2 DI PIT #3-PIT #1 3/29 RMV DBRI NST | TABLEMTN | ETL.5400.TOWR | 2021-07-28 | 2021-07-28 | 2022-10-12 | 2022-07-28 | 2022-07-28 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove | 45487821 | T2 DI PIT #3-PIT #1 3/29 RMV DBRI NST | ICS
LC | 121810803 | 009/074 | T2 DI TRNTY-CTTNWD 9/74 BACKFIL | TABLEMTN | ETL.4040.POLE.STPS | 2021-07-28 | 2021-07-27 | 2022-06-24 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45212058 | T2 DI TRNTY-CTTNWD 9/74 BACKFIL | ICW
LC | 121810815 | 014/185C | T3 DI WEIMAR #1 014/185C RPL HRDD | SACTO | ETL.7560.POLE.WOOD | 2021-07-28 | 2021-07-27 | 2022-08-02 | 2022-01-23 | 2022-01-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45210964 | T3 DI WEIMAR #1 014/185C RPL HRDD | ICW
LC | 121810822 | 017/000 | T2 DI HMBLDT BY-RIO DL JCT 17/0 RPL INSW | EUREKA | ETL.7100.INSL | 2021-07-28 | 2021-07-27 | 2022-04-24 | 2022-07-27 | 2022-07-27 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31592022 | T2 DI HMBLDT BY-RIO DL JCT 17/0 RPL INSW | 93I
LC | 121810826 | 007/114 | T3 DI WEIMAR #1 7/114 RPL STRW | SACTO | ETL.7560.POLE.WOOD | 2021-07-28 | 2021-07-27 | 2022-08-28 | 2022-01-23 | 2022-01-27 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31579239 | T3 DI WEIMAR #1 8/131 RPL STRW | 70Y
LC | 121810867 | 005/093 | T2 DI COLGATE-PALERMO 5/93 RPR GYWW | SACTO | ETL.6500.POLE.WOOD | 2021-07-28 | 2021-07-27 | 2022-05-18 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44930721 | T2 DI COLGATE-PALERMO 5/93 RPR GYWW | ICW
LC | 121810868 | 005/093 | T2 DI COLGATE-PALERMO 5/93 RPR SPLW | SACTO | ETL.6500.INSL.CERA | 2021-07-28 | 2021-07-27 | 2021-08-11 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 44948327 | T2 DI COLGATE-PALERMO 5/93 RPR SPLW | ICW
LC | 121810881 | 007/083 | T2 DI DRUM-SUMMIT #2 7/83 FILL HOLE | SACTO | ETL.1450.POLE.STPS | 2021-07-28 | 2021-07-27 | 2022-05-11 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Repair | 45218211 | T2 DI DRUM-SUMMIT #2 7/83 FILL HOLE | ICW
LC | 121810914 | B019/440 | 2222 | SACTO | ETL.6760.POLE.WOOD | 2021-07-28 | 2021-07-26 | 2022-07-26 | 2022-07-26 | 2022-07-26 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCM COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31595647 | T3 DI DRM GRAS VLY WMAR 3/79 RPL STRW | 70Y
LC | 121810918 | 020/109 | T2 DI TSLA-NWRD #1 20/109 COMPLETE | CONCORD | ETL.5720.TOWR | 2021-07-28 | 2021-07-26 | 2022-04-23 | 2022-07-26 | 2022-07-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45053944 | T2 DI TESLA-NEWARD #1 20/109 RPR OPGW | ICS
LC | 121810945 | 020/084 | T3 DI DIABLO-GATES #1 20/84 RPR JUMPER | PISMOBCH | ETL.5960.TOWR | 2021-07-28 | 2021-07-28 | 2022-06-24 | 2022-01-24 | 2022-01-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45068531 | T3 DI DIABLO-GATES #1 20/84 RPR JUMPER | ICW
LC | 121810946 | 019/440 | T2 DI DRM GRS VLY WMR 019/440 RPL CRSW | SACTO | ETL.6760.POLE.WOOD | 2021-07-28 | 2021-07-28 | 2022-03-29 | 2022-07-28 | 2022-07-28 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31548672 | T2 DI DRM GRS VLY WMR 019/440 RPL CRSW | 93E
LC | 121810950 | 004/004 | T2 DI LAYTONVILLE-COVELO 4/4 RPL STRW | WILLITS | ETL.7390.POLE.WOOD | 2021-07-28 | 2021-07-28 | 2022-06-06 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31547421 | T2 DI LYTNVILLE-COVELO 1/6 RPL POLE | 70Y
LC | 121810961 | 005/148 | T3 DI DEER CREEK-DRUM 5/148 RPR GYWW | SACTO | ETL.6690.POLE.NWOD | 2021-07-28 | 2021-07-27 | 2022-06-22 | 2022-01-23 | 2022-01-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45239506 | T3 DI DEER CREEK-DRUM 5/148 RPR GYWW | ICW
LC | 121810993 | 007/138 | T2 DI SMRTVLLE-NCLS #1 7/138 RMV BUTT | SACTO | ETL.7990.POLE.NWOD | 2021-07-28 | 2021-07-28 | 2022-08-18 | 2022-07-28 | 2022-07-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45253261 | T2 DI SMRTVLLE-NCLS #1 7/138 RMV BUTT | ICW
LC | 121811001 | 018/130 | T2 DI CARIBOU-TABLE MTN 18/130 RPR GYWS | TABLEMTN | ETL.4440.POLE.STPS | 2021-07-28 | 2021-07-28 | 2022-06-23 | 2022-07-28 | 2022-07-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45195471 | T2 DI CARIBOU-TABLE MTN 18/130 RPR GYWS | ICS
LC | 121811002 | 025/367 | T3 DI GOLD HILL #1 025/367 INST IBWW | SACTO | ETL.6950.POLE.NWOD | 2021-07-28 | 2021-07-28 | 2022-11-10 | 2022-01-24 | 2022-01-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45218212 | T3 DI GOLD HILL #1 025/367 INST IBWW | ICW
LC | 121811011 | 027/170 | T2 DI TESLA-SALADO-MTCA 27/170 RPR GYWW | VICTOR | ETL.4000.POLE.WOOD | 2021-07-28 | 2021-07-27 | 2021-10-12 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44995528 | T2 DI TESLA-SALADO-MTCA 27/170 RPR GYWW | ICW
LC | 121811015 | 003/082 | T2 DI COLGATE-ALLEGHANY 3/82 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2021-07-28 | 2021-07-28 | 2022-06-24 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548663 | T2 DI COLGATE-ALLEGHANY 3/82 RPL STRW | 70Y
LC | 121811021 | 006/062B | T2 DI IGNACIO-BOLINAS #1 06/62B RPR GYWW | LAKEVLLE | ETL.7140.POLE.WOOD | 2021-07-28 | 2021-07-28 | 2022-01-13 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45127363 | T2 DI IGNACIO-BOLINAS #1 06/62B RPR GYWW | ICW
LC | 121811166 | 007/075 | T2 DI PIT #5-ROUND MTN #2 7/75 RPR STRW | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-29 | 2021-07-27 | 2022-05-07 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213775 | T2 DI PIT #5-ROUND MTN #2 7/75 RPR STRW | ICW
LC | 121811334 | 007/075 | T2 DI PIT #5-RD MT #2 7/75R RPR STRW CMT | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-29 | 2021-07-27 | 2022-06-07 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213774 | T2 DI PIT #5-ROUND MTN #2 7/75R RPR STRW | ICW
LC | 121811335 | 007/075 | T2 DI PIT #5-ROUND MTN #2 7/75 RMV BUTT | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-29 | 2021-07-27 | 2022-06-16 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove | 45213772 | T2 DI PIT #5-ROUND MTN #2 7/75 RMV BUTT | ICW
LC | 121811711 | 025/373 | T3 DI GOLD HILL #1 025/373 RPL HRDD | SACTO | ETL.6950.POLE.WOOD | 2021-07-29 | 2021-07-28 | 2021-10-18 | 2022-01-24 | 2022-01-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45020029 | T3 DI GOLD HILL #1 025/373 RPL HRDD | ICW
LC | 121811853 | 003/057 | T3 DI MIDDLE FORK #1 003/057 RPL INSW | SACTO | ETL.8405.INSL.CERA | 2021-07-29 | 2021-07-27 | 2022-06-08 | 2022-01-23 | 2022-01-27 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548709 | T3 DI MIDDLE FORK #1 003/057 RPL INSW | 93I
LC | 121812377 | 072/364B | T2 DI MALIN-RND MTN #2 72/364B RPR OPGW | TABLEMTN | ETL.6020.INSL.NCER | 2021-07-29 | 2021-07-27 | 2022-07-14 | 2022-07-27 | 2022-07-27 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215161 | T2 DI MALIN-RND MTN #2 72/364B RPR OPGW | ICS
LC | 121812473 | 001/011 | T2 DI DIVIDE-VANDENBRG #2 1/11R RPR STRW | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-29 | 2021-07-28 | 2022-01-31 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45098717 | T2 DI DIVIDE-VANDENBRG #2 1/11R RPR STRW | ICW
LC | 121812475 | 001/011 | T2 DI DIVIDE-VNDNBRG #2 1/11L RPR STRW | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-29 | 2021-07-28 | 2022-01-31 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45098801 | T2 DI DIVIDE-VNDNBRG #2 1/11L RPR STRW | ICW
LC | 121812834 | 023/115 | T3 DI RND MTN-TBL MTN#2 23/115 RPR GYWS | TABLEMTN | ETL.6070.TOWR | 2021-07-29 | 2021-07-28 | 2021-09-13 | 2022-01-24 | 2022-01-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 121812927 | 004/034 | T2 DI DIVIDE-VANDENBERG#2 4/34C RPL STRW | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-29 | 2021-07-28 | 2022-04-21 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CITY COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31578117 | T2 DI DIVIDE-VNDNBRG #2 2/19L RPL STRW | 70Y
LC | 121812951 | 004/034 | T2 DI DIVIDE-VANDENBERG#2 4/34R RPL STRW | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-29 | 2021-07-28 | 2022-04-21 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CITY COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31578117 | T2 DI DIVIDE-VNDNBRG #2 2/19L RPL STRW | 70Y
LC | 121812955 | 004/034 | T2 DI DIVIDE-VANDENBERG#2 4/34L RPL STRW | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-29 | 2021-07-28 | 2022-04-21 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CITY COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31578117 | T2 DI DIVIDE-VNDNBRG #2 2/19L RPL STRW | 70Y
LC | 121813213 | 012/237 | T3 DI FRNCH MDWS-MDL FRK 12/237 RPR GYWW | SACTO | ETL.6870.POLE.NWOD | 2021-07-29 | 2021-07-27 | 2022-05-07 | 2022-01-23 | 2022-01-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45218816 | T3 DI FRNCH MDWS-MDL FRK 12/237 RPR GYWW | ICW
LC | 121813323 | 007/070 | T2 DI IGNACIO-BOLINAS #1 7/70 RPL INSW | LAKEVLLE | ETL.7140.INSL | 2021-07-29 | 2021-07-28 | 2022-01-14 | 2022-07-28 | 2022-07-28 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548705 | T2 DI IGNACIO-BOLINAS #1 7/70 RPL INSW | 93I
LC | 121813845 | 006/056 | T2 WV PARADISE-TABLE MTN 6/56 INS DAMS | TABLEMTN | ETL.4316.INSL.CERA | 2021-07-29 | 2021-07-29 | 2022-02-25 | 2022-07-29 | 2022-07-29 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install | 45201430 | T2 WV PARADISE-TABLE MTN 6/56 INS DAMS | ICS
LC | 121814228 | 015/003 | T3 DI DONNELLS-MI-WUK 015/3R RPR STRW | VICTOR | ETL.1400.POLE.WDPS | 2021-07-29 | 2021-07-26 | 2022-08-29 | 2022-01-22 | 2022-01-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45122861 | T3 DI DONNELLS-MI-WUK 015/3R RPR STRW | ICW
LC | 121814391 | 004/005 | T2 WV HUMBOLDT-MAPLE CREEK 4/5 RPL POLE | EUREKA | ETL.7130.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2022-11-17 | 2022-07-29 | 2022-07-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548703 | T2 WV HUMBOLDT-MAPLE CREEK 4/3 RPL POLE | 70Y
LC | 121814422 | 004/004 | T2 WV HUMBOLDT-MAPLE CREEK 4/4 RPL POLE | EUREKA | ETL.7130.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2022-11-18 | 2022-07-29 | 2022-07-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548703 | T2 WV HUMBOLDT-MAPLE CREEK 4/3 RPL POLE | 70Y
LC | 121814436 | 004/047A | T2 DI HLLSDL JT-HLF MN BY 4/47A RPR GYWW | METCALF | ETL.7060.POLE.WOOD | 2021-07-29 | 2021-07-28 | 2022-04-07 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45150663 | T2 DI HLLSDL JT-HLF MN BY 4/47A RPR GYWW | ICW
LC | 121814440 | :000/005 | T2 EI STNSLS-MLNS SS MNTE :0/5 RPR FOND | VICTOR | ETL.3830.TOWR | 2021-07-29 | 2021-07-29 | 2022-02-16 | 2022-07-29 | 2022-07-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45107267 | T2 EI STNSLS-MLNS SS MNTE :0/5 RPR FOND | ICQ
LC | 121814516 | 004/050 | T2 DI BURNS-LONE STAR #1 4/50C RPR GYWW | MOSSLNDG | ETL.6230.POLE.WDPS | 2021-07-29 | 2021-07-26 | 2022-01-12 | 2022-07-26 | 2022-07-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145026 | T2 DI BURNS-LONE STAR #1 4/50C RPR GYWW | ICW
LC | 121814540 | 004/050 | T2 DI BURNS-LONE STAR #1 4/50L RPR GYWW | MOSSLNDG | ETL.6230.POLE.WDPS | 2021-07-29 | 2021-07-26 | 2022-01-12 | 2022-07-26 | 2022-07-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45123087 | T2 DI BURNS-LONE STAR #1 4/50L RPR GYWW | ICW
LC | 121814596 | 017/077 | T3 SAN RAMON-MORAGA 4/21 RPL HANGER | CONCORD | ETL.5660.INSL | 2021-07-29 | 2021-07-29 | 2021-07-28 | 2022-01-25 | 2022-01-29 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 | No Good/Out of Stdrd | Hardware-Steel | Replace
LC | 121814732 | 008/074 | T2 WV PARADISE-TABLE MTN 8/74 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-07-29 | 2021-07-29 | 2022-05-11 | 2022-07-29 | 2022-07-29 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31591036 | T2 WV PARADISE-TABLE MTN RPL INSS 3 STRT | 93K
LC | 121814886 | 007/064 | T2 WV PARADISE-TABLE MTN 7/64 RPR JUMS | TABLEMTN | ETL.4316.INSL.NCER | 2021-07-29 | 2021-07-29 | 2022-05-13 | 2022-07-29 | 2022-07-29 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Jumper-Steel | Repair | 45196977 | T2 WV PARADISE-TABLE MTN 7/64 RPR JUMS | ICS
LC | 121814971 | A000/005 | T2 KM GREEN TAP A0/5 RPL INSS | VICTOR | ETL.3505.POLE.NWOD | 2021-07-29 | 2021-07-29 | 2022-10-29 | 2022-07-29 | 2022-07-29 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31611652 | T2 KM GREEN TAP A0/5 RPL INSS | 93K
LC | 121814972 | 006/053 | T2 WV PARADISE-TABLE MTN 6/53 RPR JUMS | TABLEMTN | ETL.4316.INSL.NCER | 2021-07-29 | 2021-07-29 | 2022-05-13 | 2022-07-29 | 2022-07-29 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Jumper-Steel | Repair | 45240544 | T2 WV PARADISE-TABLE MTN 6/53 RPR JUMS | ICS
LC | 121815064 | 016/430 | T3 WV COLGATE-ALLEGHANY 16/430 INS DAMS | SACTO | ETL.6470.POLE.NWOD | 2021-07-29 | 2021-07-29 | 2022-07-16 | 2022-01-25 | 2022-01-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB NTDE | Missing | Damper-Steel | Install | 45224721 | T3 WV COLGATE-ALLEGHANY 16/430 INS DAMS | ICS
LC | 121815095 | 006/057 | T2 WV PARADISE-TABLE MTN 6/57 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-07-29 | 2021-07-29 | 2022-05-11 | 2022-07-29 | 2022-07-29 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31591036 | T2 WV PARADISE-TABLE MTN RPL INSS 3 STRT | 93K
LC | 121815287 | 004/044B | T2 DI HLSDL JT-HF MN BY 4/44B RPR WDPKR | METCALF | ETL.7060.POLE.WOOD | 2021-07-29 | 2021-07-28 | 2022-02-23 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45150664 | T2 DI HLSDL JT-HF MN BY 4/44B RPR WDPKR | ICW
LC | 121815407 | 001/011 | T2 DI DIVIDE-VNDNBRG #1 001/11C RPL STRW | PISMOBCH | ETL.8620.POLE.WDPS | 2021-07-29 | 2021-07-28 | 2022-03-16 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31578011 | T2 DI DIVIDE-VNDNBRG #1 001/11R RPL STRW | 70Y
LC | 121815408 | 001/011 | T2 DI DIVIDE-VNDNBRG #1 001/11L RPL STRW | PISMOBCH | ETL.8620.POLE.WDPS | 2021-07-29 | 2021-07-28 | 2022-03-16 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31578011 | T2 DI DIVIDE-VNDNBRG #1 001/11R RPL STRW | 70Y
LC | 121815409 | 001/011 | T2 DI DIVIDE-VNDNBRG #1 001/11R RPL STRW | PISMOBCH | ETL.8620.POLE.WDPS | 2021-07-29 | 2021-07-28 | 2022-03-16 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31578011 | T2 DI DIVIDE-VNDNBRG #1 001/11R RPL STRW | 70Y
LC | 121815490 | 002/023 | T2 DI UKIAH-HPLND-CLVRDLE 2/23R COMPLETE | WILLITS | ETL.4050.POLE.WDPS | 2021-07-29 | 2021-07-24 | 2022-05-07 | 2022-07-24 | 2022-07-24 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545800 | T2 EI UKIAH-HOPLAND RPL POLE IN 6 TWRS. | 70Y
LC | 121815598 | 010/047 | T2 DI BRENTWOOD-KELSO 010/047 RPR STRT | CONCORD | ETL.4410.TOWR | 2021-07-29 | 2021-07-29 | 2022-01-06 | 2022-07-29 | 2022-07-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45107667 | T2 DI BRENTWOOD-KELSO 010/047 RPR STRT | ICQ
LC | 121815605 | 010/282 | T3 DI COLGATE-ALLEGHANY 010/282 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2022-06-18 | 2022-01-25 | 2022-01-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45224722 | T3 DI COLGATE-ALLEGHANY 010/282 RPR STRW | ICW
LC | 121815619 | 010/047 | T2 DI BRENTWOOD-KELSO 010/047 RPL INSS | CONCORD | ETL.4410.INSL | 2021-07-29 | 2021-07-29 | 2022-06-10 | 2022-07-29 | 2022-07-29 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549234 | T2 DI BRENTWOOD-KELSO 010/047 RPL INSS | 93K
LC | 121815652 | 014/066 | T2 DI CONTRA COSTA-DELT 10/047 COMPLETED | CONCORD | ETL.4490.INSL | 2021-07-29 | 2021-07-29 | 2022-02-14 | 2022-07-29 | 2022-07-29 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31552145 | DI CNTRA CSTA DLTA RPL INSS. 5TWRS | 93K
LC | 121815724 | 004/044A | T2 DI HLSDL JT-HF MN BY 4/44A RMV VEG | METCALF | ETL.7060.POLE.WOOD | 2021-07-29 | 2021-07-28 | 2022-08-08 | 2022-07-28 | 2022-07-28 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR FRAB SR22 | Overgrown | Vegetation | Remove
LC | 121815727 | 013/125 | T2 DI DRUM-HIGGINS 13/125 RPL INSW | SACTO | ETL.4393.INSL.CERA | 2021-07-29 | 2021-07-29 | 2022-08-07 | 2022-07-29 | 2022-07-29 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548674 | T2 DI DRUM-HIGGINS 13/125 RPL INSW | 93I
LC | 121815861 | 011/391 | T2 DI SPAULDING-SUMMIT 11/391 RPL HRDD | SACTO | ETL.8060.POLE.WOOD | 2021-07-29 | 2021-07-27 | 2022-09-19 | 2022-07-27 | 2022-07-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45224498 | T2 DI SPAULDING-SUMMIT 11/391 RPL HRDD | ICW
LC | 121815914 | 000/004 | T2 DI IGNACIO-BLNS #1 0/4 RPR WDPKR | LAKEVLLE | ETL.7140.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2022-01-13 | 2022-07-29 | 2022-07-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAR | No Good/Out of Stdrd | Structure-Wood | Repair | 45128242 | T2 DI IGNACIO-BLNS #1 0/4 RPR WDPKR | ICW
LC | 121815916 | 007/134 | T2 DI VLLY SPNG #2 7/134L COMPLETE | VICTOR | ETL.9460.POLE.WDPS | 2021-07-29 | 2021-07-28 | 2021-07-28 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579189 | T2 DI VALLEY SPRINGS #2 7/134 RPL STRW | 70Y
LC | 121815950 | 003/083 | T3DI DEER CREEK-DRUM 3/83 RPR STRW | SACTO | ETL.6690.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2021-09-22 | 2022-01-25 | 2022-01-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44945140 | T3DI DEER CREEK-DRUM 3/83 RPR STRW | ICW
LC | 121815953 | 003/083 | T3 DI DEER CREEK-DRUM 3/83 RPR GYWW | SACTO | ETL.6690.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2021-09-22 | 2022-01-25 | 2022-01-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44945142 | T3 DI DEER CREEK-DRUM 3/83 RPR GYWW | ICW
LC | 121815955 | 003/083 | T3 DI DEER CREEK-DRUM 3/83 RPL HRDW | SACTO | ETL.6690.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2021-09-22 | 2022-01-25 | 2022-01-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44944976 | T3 DI DEER CREEK-DRUM 3/83 RPL HRDW | ICW
LC | 121815958 | 003/083 | T3 DI DEER CREEK-DRUM 3/83 RPR SPLW | SACTO | ETL.6690.INSL.NCER | 2021-07-29 | 2021-07-29 | 2021-09-22 | 2022-01-25 | 2022-01-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Replace | 44944978 | T3 DI DEER CREEK-DRUM 3/83 RPR SPLW | ICW
LC | 121815975 | 000/009 | T3 DI DRUM-SPAULDING 00/09 RPR HDWW | SACTO | ETL.6770.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2022-05-21 | 2022-01-25 | 2022-01-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45218817 | T3 DI DRUM-SPAULDING 00/09 RPR HDWW | ICW
LC | 121816051 | 112/008 | T2 DI HMBLDT-BRIDEVIL 112/08 RPR ADSS | EUREKA | ETL.1810.POLE.WDPS | 2021-07-29 | 2021-07-28 | 2022-04-05 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45155399 | T2 DI HMBLDT-BRIDEVIL 112/08 RPR ADSS | ICW
LC | 121816064 | 023/641 | T3 DI COLGATE-ALLEGHANY 23/641 RPL HRDD | SACTO | ETL.6470.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2022-06-15 | 2022-01-25 | 2022-01-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45224724 | T3 DI COLGATE-ALLEGHANY 23/641 RPL HRDD | ICW
LC | 121816066 | 003/020 | T3 DI DIABLO-GATES #1 3/20 INS HRDT | PISMOBCH | ETL.5960.TOWR | 2021-07-29 | 2021-07-29 | 2022-05-21 | 2022-01-25 | 2022-01-29 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45070727 | T3 DI DIABLO-GATES #1 3/20 INS HRDT | ICQ
LC | 121816068 | 000/008 | T2 DI COLGATE-PALERMO 000/008 RPR GYWW | SACTO | ETL.6500.POLE.STPS | 2021-07-29 | 2021-07-28 | 2022-05-15 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45218818 | T2 DI COLGATE-PALERMO 000/008 RPR GYWW | ICW
LC | 121816111 | 003/007 | T2 DI LAYTONVILLE-COVELO 3/7 RPL STRW | WILLITS | ETL.7390.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2022-06-11 | 2022-07-29 | 2022-07-29 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31547421 | T2 DI LYTNVILLE-COVELO 1/6 RPL POLE | 70Y
LC | 121816119 | 007/032 | T2 DI PITTSBURG-SAN MATEO 7/32 RPL HRDT | CONCORD | ETL.5463.TOWR | 2021-07-29 | 2021-07-29 | 2022-04-11 | 2022-07-29 | 2022-07-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45190810 | T2 DI PITTSBURG-SAN MATEO 7/32 RPL HRDT | ICQ
LC | 121816145 | 014/095 | T2 DI METCALF-GRN VLLY 14/95 RPR WDPKR | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-07-29 | 2021-07-29 | 2022-05-19 | 2022-07-29 | 2022-07-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45117831 | T2 DI METCALF-GRN VLLY 14/95 RPR WDPKR | ICW
LC | 121816153 | 004/020 | T2 DI PITTSBURG-TESLA #1 4/20 RPR FOND | CONCORD | ETL.5510.TOWR | 2021-07-29 | 2021-07-29 | 2022-04-12 | 2022-07-29 | 2022-07-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45190837 | T2 DI PITTSBURG-TESLA #1 4/20 RPR FOND | ICQ
LC | 121816183 | 000/002 | T3 DI KILARC-DESCHUTES 00/02 RPL INSW | TABLEMTN | ETL.7300.INSL.CERA | 2021-07-29 | 2021-07-27 | 2022-04-19 | 2022-01-23 | 2022-01-27 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548707 | T3 DI KILARC-DESCHUTES 00/02 RPL INSW | 93I
LC | 121816237 | 023/651 | T3 DI COLGATE-ALLEGHANY 23/651 INS HRDD | SACTO | ETL.6470.POLE.WOOD | 2021-07-29 | 2021-07-26 | 2022-06-15 | 2022-01-22 | 2022-01-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45224725 | T3 DI COLGATE-ALLEGHANY 23/651 INS HRDD | ICW
LC | 121816256 | 000/006 | T3 DI DEER CREEK-DRUM 0/6 RPL INSW | SACTO | ETL.6690.INSL | 2021-07-29 | 2021-07-29 | 2022-06-22 | 2022-01-25 | 2022-01-29 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548670 | T3 DI DEER CREEK-DRUM 0/6 RPL INSW | 93I
LC | 121816277 | 023/640 | T3 DI COLGATE-ALLEGHANY 23/640 RPL HRDD | SACTO | ETL.6470.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2022-06-15 | 2022-01-25 | 2022-01-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44930729 | T3 DI COLGATE-ALLEGHANY 23/640 RPL HRDD | ICW
LC | 121816301 | 003/064 | T3 DI COLGATE-CHALLENGE 3/64 RPL INSW | SACTO | ETL.6480.INSL.CERA | 2021-07-29 | 2021-07-27 | 2022-08-25 | 2022-01-23 | 2022-01-27 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548666 | T3 DI COLGATE-CHALLENGE 3/64 RPL INSW | 93I
LC | 121816344 | 023/640 | T3 DI COLGATE-ALLEGHANY 23/640 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2022-06-15 | 2022-01-25 | 2022-01-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 44930730 | T3 DI COLGATE-ALLEGHANY 23/640 RPR STRW | ICW
LC | 121816431 | 000/005A | T3 DI MRAGA-CLARMONT #2 0/5A RPL INSS | CONCORD | ETL.2710.INSL.CERA | 2021-07-29 | 2021-07-28 | 2022-08-22 | 2022-01-24 | 2022-01-28 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549064 | T3 DI MRAGA-CLARMONT #2 0/5A RPL INSS | 93K
LC | 121816441 | 006/135 | T2 DI SMRTSVLLE NCLS #2 006/135 RPR INSW | SACTO | ETL.8000.INSL.NCER | 2021-07-29 | 2021-07-27 | 2022-07-13 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45239510 | T2 DI SMRTSVLLE NCLS #2 006/135 RPR INSW | ICW
LC | 121816447 | 005/038 | T2 DI DIVIDE-VNDNBRG #2 005/038 RPR INSW | PISMOBCH | ETL.8630.INSL.NCER | 2021-07-29 | 2021-07-28 | 2022-01-27 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45090085 | T2 DI DIVIDE-VNDNBRG #2 005/038 RPR INSW | ICW
LC | 121816449 | 005/038 | T2 DI DIVIDE-VNDNBRG #2 005/038 RPR STRW | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-29 | 2021-07-28 | 2022-02-14 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45090082 | T2 DI DIVIDE-VNDNBRG #2 005/038 RPR STRW | ICW
LC | 121816461 | 062/008 | T2 DI GARBRVIL-LAYTNVLE 62/08 RPR SPLW | WILLITS | ETL.8365.INSL.CERA | 2021-07-29 | 2021-07-27 | 2022-05-06 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45155779 | T2 DI GARBRVIL-LAYTNVLE 62/08 RPR SPLW | ICW
LC | 121816468 | 062/008 | T2 DI GARBRVIL-LAYTNVLE 62/08 RPL INSW | WILLITS | ETL.8365.INSL.CERA | 2021-07-29 | 2021-07-27 | 2022-05-06 | 2022-07-27 | 2022-07-27 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542897 | T2 EI GRBRVLL-LYTNVILLE 31/7 RPL INSW | 93I
LC | 121816508 | 007/107 | T3 DI MIDDLEFORK #1+ 7/107 RPR CRSW | SACTO | ETL.8405.POLE.WOOD | 2021-07-29 | 2021-07-27 | 2022-08-03 | 2022-01-23 | 2022-01-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45017210 | T3 DI MIDDLEFORK #1+ 7/107 RPR CRSW | ICW
LC | 121816516 | 007/132 | T2 DI SMRTVIL-NICOLUS #1 7/132 RPL STRW | SACTO | ETL.7990.POLE.WOOD | 2021-07-29 | 2021-07-27 | 2022-08-20 | 2022-07-27 | 2022-07-27 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544424 | T2 DI SMRTVIL-NICOLUS #1 7/132 RPL STRW | 70Y
LC | 121816521 | 015/104 | T2 DI METCALF-GRN VLLY 015/104L RPL STRW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-07-29 | 2021-07-29 | 2022-07-14 | 2022-07-29 | 2022-07-29 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31580055 | T2 DI METCALF-GRN VLLY 015/104L RPL STRW | 70Y
LC | 121816523 | 019/436 | T2 DI DRUM GRS VLY WMR 019/436 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2022-03-29 | 2022-07-29 | 2022-07-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45193836 | T2 DI DRUM GRS VLY WMR 019/436 RPR GYWW | ICW
LC | 121816524 | 019/436 | T2 DI DRUM GRS VLY WMR 019/436 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2022-03-29 | 2022-07-29 | 2022-07-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45193837 | T2 DI DRUM GRS VLY WMR 019/436 RPR STRW | ICW
LC | 121816529 | 011/251 | T3 DI KILARC-CEDAR CRK 011/251 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2022-04-21 | 2022-01-25 | 2022-01-29 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548706 | T3 DI KILARC-CEDAR CRK 011/251 RPL STRW | 70Y
LC | 121816627 | 010/078A | T2 DI HELMS-GREGG #1 10/78A RPL INSS | FRESNO | ETL.4870.INSL | 2021-07-29 | 2021-07-28 | 2022-08-25 | 2022-07-28 | 2022-07-28 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551822 | DI HELMS-GREGG #1 RPL INSS 12 TWRS | 93K
LC | 121816736 | 013/101 | T2 DI CARIBOU-TABLE MTN 13/101 RPL HRDD | TABLEMTN | ETL.4440.TOWR | 2021-07-29 | 2021-07-28 | 2022-07-18 | 2022-07-28 | 2022-07-28 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45158379 | T2 DI CARIBOU-TABLE MTN 13/101 RPL HRDD | ICQ
LC | 121816859 | 005/093 | T2 DI COLGATE-PALERMO 5/93 RPL INSW | SACTO | ETL.6500.POLE.WOOD | 2021-07-29 | 2021-07-28 | 2022-05-18 | 2022-07-28 | 2022-07-28 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31609224 | T2 DI COLGATE-PALERMO 5/93 RPL INSW | 93I
LC | 121816869 | 025/374 | T3 DI GOLD HILL #1 25/374 GRND WASH | SACTO | ETL.6950.INSL.NCER | 2021-07-29 | 2021-07-28 | 2022-04-15 | 2022-01-24 | 2022-01-28 | Late | 622 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | Contaminated | Insulator | Ground Wash | 45218213 | T3 DI GOLD HILL #1 25/374 GRND WASH | ICD
LC | 121818109 | 022/162 | T2 DI TRINITY-CTTNWD 22/162 RPL INSW | TABLEMTN | ETL.4040.INSL.CERA | 2021-07-30 | 2021-07-29 | 2022-08-24 | 2022-07-29 | 2022-07-29 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548715 | T2 DI TRINITY-CTTNWD 22/162 RPL IN | 93I
LC | 121818173 | 014/386 | T3 DI COLGATE-ALLEGHANY 14/386 REFRAME | SACTO | ETL.6470.INSL.NCER | 2021-07-30 | 2021-07-29 | 2022-06-20 | 2022-01-25 | 2022-01-29 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31548668 | T3 DI COLGATE-ALLEGHANY 14/386 REFRAME | 93E
LC | 121818174 | 003/025 | T3 DI SOBRANTE-"G" #1 003/25 RMV VEG | CONCORD | ETL.3720.TOWR | 2021-07-30 | 2021-07-29 | 2021-12-16 | 2022-01-25 | 2022-01-29 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121818179 | 000/005 | T2 DI PIT #1-COTTONWOOD 0/5 RPL HRDT | TABLEMTN | ETL.5390.TOWR | 2021-07-30 | 2021-07-29 | 2022-08-01 | 2022-07-29 | 2022-07-29 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45195469 | T2 DI PIT #1-COTTONWOOD 0/5 RPL HRDT | ICQ
LC | 121818197 | 047/405 | T2 DI PIT #1-COTTONWOOD 047/405 RPR GYWS | TABLEMTN | ETL.5390.POLE.STPS | 2021-07-30 | 2021-07-29 | 2022-02-25 | 2022-07-29 | 2022-07-29 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45166850 | T2 DI PIT #1-COTTONWOOD 047/405 RPR GYWS | ICS
LC | 121818269 | 005/004 | T2 DI LYTNVLLE-COVELO 5/4 RPR WDPKR | WILLITS | ETL.7390.POLE.WDPS | 2021-07-30 | 2021-07-29 | 2022-06-05 | 2022-07-29 | 2022-07-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45000022 | T2 DI LYTNVLLE-COVELO 5/4 RPR WDPKR | ICW
LC | 121818290 | 002/019 | T2 DI DIVIDE-VNDNBRG #2 2/19L RPL STRW | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-30 | 2021-07-28 | 2022-03-09 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31578117 | T2 DI DIVIDE-VNDNBRG #2 2/19L RPL STRW | 70Y
LC | 121818291 | 005/004 | T2 DI LYTNVLLE-COVELO 5/4 RPR WDPKR | WILLITS | ETL.7390.POLE.WDPS | 2021-07-30 | 2021-07-29 | 2022-06-05 | 2022-07-29 | 2022-07-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45000023 | T2 DI LYTNVLLE-COVELO 5/4 RPR WDPKR | ICW
LC | 121818292 | 005/004 | T2 DI LYTNVLLE-COVELO 5/4 RPR WDPKR | WILLITS | ETL.7390.POLE.WDPS | 2021-07-30 | 2021-07-29 | 2022-06-05 | 2022-07-29 | 2022-07-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45000024 | T2 DI LYTNVLLE-COVELO 5/4 RPR WDPKR | ICW
LC | 121818320 | 001/005 | T3 DI DONNELLS-MI-WUK 001/5 REPLUMB | VICTOR | ETL.1400.INSL | 2021-07-30 | 2021-07-29 | 2022-10-09 | 2022-01-25 | 2022-01-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45122862 | T3 DI DONNELLS-MI-WUK 001/5 REPLUMB | ICW
LC | 121818327 | 048/426 | T2 DI RND MTN-CTTNWD #3 48/426 COMPLETE | TABLEMTN | ETL.5650.TOWR | 2021-07-30 | 2021-07-28 | 2022-06-07 | 2022-07-28 | 2022-07-28 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45110996 | T2 DI RND MTN-CTTNWD #3 48/426 RPR FOND | ICQ
LC | 121818396 | 001/002 | T2 DI LYTNVLLE-COVELO 001/002 RPL DAMW | WILLITS | ETL.7390.POLE.WOOD | 2021-07-30 | 2021-07-29 | 2022-06-04 | 2022-07-29 | 2022-07-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Damper-Wood | Replace | 44999870 | T2 DI LYTNVLLE-COVELO 001/002 RPL DAMW | ICW
LC | 121818397 | 001/002 | T2 DI LYTNVLLE-COVELO 001/002 RPR GYWW | WILLITS | ETL.7390.POLE.WOOD | 2021-07-30 | 2021-07-29 | 2022-06-04 | 2022-07-29 | 2022-07-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44999871 | T2 DI LYTNVLLE-COVELO 001/002 RPR GYWW | ICW
LC | 121818420 | 078/395B | T2 DI MALIN-RND MTN #2 78/395A RMV VEG | TABLEMTN | ETL.6020.TOWR | 2021-07-30 | 2021-07-29 | 2022-09-01 | 2022-07-29 | 2022-07-29 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121818541 | 008/085 | T2 DI PIT #5-ROUND MTN #2 08/85 RPR FOND | TABLEMTN | ETL.5430.POLE.WDPS | 2021-07-30 | 2021-07-29 | 2022-07-14 | 2022-07-29 | 2022-07-29 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45195468 | T2 DI PIT #5-ROUND MTN #2 08/85 RPR FOND | ICQ
LC | 121818789 | 015/104 | T2 DI METCALF-GRN VLLY 015/104R RPL STRW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-07-30 | 2021-07-29 | 2022-07-14 | 2022-07-29 | 2022-07-29 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31580055 | T2 DI METCALF-GRN VLLY 015/104L RPL STRW | 70Y
LC | 121819225 | 014/325 | T2 DI DRM-GRSS VLY-WMR 14/325 RMV BUTT | SACTO | ETL.6760.POLE.WOOD | 2021-07-30 | 2021-07-29 | 2022-01-24 | 2022-07-29 | 2022-07-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44930731 | T2 DI DRM-GRSS VLY-WMR 14/325 RMV BUTT | ICW
LC | 121819333 | :016/085 | T2 WV CHC-SALINAS-SLDAD :16/85 RPR FOND | MOSSLNDG | ETL.2900.TOWR | 2021-07-30 | 2021-07-30 | 2022-07-12 | 2022-07-30 | 2022-07-30 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45075197 | T2 WV CHC-SALINAS-SLDAD :16/85 RPR FOND | ICQ
LC | 121820012 | 007/134 | T2 DI VLLY SPNG #2 7/134C RPL STR CMPLTD | VICTOR | ETL.9460.POLE.WDPS | 2021-07-30 | 2021-07-28 | 2022-03-09 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579189 | T2 DI VALLEY SPRINGS #2 7/134 RPL STRW | 70Y
LC | 121820014 | 007/134 | T2 DI VLLY SPNG #2 7/134R RPL STR CMPLTD | VICTOR | ETL.9460.POLE.WDPS | 2021-07-30 | 2021-07-28 | 2022-03-09 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579189 | T2 DI VALLEY SPRINGS #2 7/134 RPL STRW | 70Y
LC | 121820344 | 001/002 | T2 DI MELONES-CURTIS 1/2 RPL HRDD | VICTOR | ETL.2390.POLE.WDPS | 2021-07-30 | 2021-07-28 | 2022-12-02 | 2022-07-28 | 2022-07-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45164602 | T2 DI MELONES-CURTIS 1/2 RPL HRDD | ICW
LC | 121820845 | 001/035 | T3 DI DRM-GRS VY-WR 1/35 RPR ADSS CMPLTD | SACTO | ETL.6760.POLE.NWOD | 2021-07-30 | 2021-07-29 | 2022-04-06 | 2022-01-25 | 2022-01-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44930641 | T3 DI DRUM-GRASS VLLY-WEMR 1/35 RPR ADSS | ICW
LC | 121820950 | 004/035 | T2 DI TRINITY-CTTNWD 4/35 RPL INSW | TABLEMTN | ETL.4040.INSL.NCER | 2021-07-30 | 2021-07-28 | 2022-08-22 | 2022-07-28 | 2022-07-28 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548130 | T2 DI TRNITY-CTTONWD 4/33 RPL INSW | 93I
LC | 121820954 | 004/027 | T2 DI DVD-VNDBG #2 4/27L RPL STRW COMPLT | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-30 | 2021-07-28 | 2022-04-22 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31578117 | T2 DI DIVIDE-VNDNBRG #2 2/19L RPL STRW | 70Y
LC | 121821142 | 003/021 | T2 DI DIVIDE-VANDENBERG #2 3/21 RPL HRDD | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-30 | 2021-07-28 | 2022-04-23 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45090086 | T2 DI DIVIDE-VANDENBERG #2 3/21 RPL HRDD | ICW
LC | 121821145 | 003/021 | T2 DI DIVIDE-VANDENBERG #2 3/21 RPL HRDD | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-30 | 2021-07-28 | 2022-04-23 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45090087 | T2 DI DIVIDE-VANDENBERG #2 3/21 RPL HRDD | ICW
LC | 121821186 | 018/412 | T2 DI DRUM-GRSS VLLY-WMR 18/412 INS HRDD | SACTO | ETL.6760.POLE.WOOD | 2021-07-30 | 2021-07-29 | 2022-03-25 | 2022-07-29 | 2022-07-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | Missing | Hardware-Wood | Install | 45193838 | T2 DI DRUM-GRSS VLLY-WMR 18/412 INS HRDD | ICW
LC | 121821274 | 000/008B | T3 DI MORAGA-OAKLAND #4 0/8B RPL STRW | CONCORD | ETL.2750.POLE.WOOD | 2021-07-30 | 2021-07-28 | 2022-07-09 | 2022-01-24 | 2022-01-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31556333 | T3 DI MORAGA-OAKLAND #4 0/8B RPL STRW | 70Y
LC | 121822280 | 020/477 | T2 DI DRM-GRSS VLLY-WMR 20/477 PPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-07-30 | 2021-07-29 | 2022-03-31 | 2022-07-29 | 2022-07-29 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31595647 | T3 DI DRM GRAS VLY WMAR 3/79 RPL STRW | 70Y
LC | 121822281 | 020/477 | T2 DI DRM-GRSS VLLY-WMR 20/477 RMV VEG | SACTO | ETL.6760.POLE.WOOD | 2021-07-30 | 2021-07-29 | 2022-08-12 | 2022-07-29 | 2022-07-29 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE CNCL OH TR2 PRTO AIR FRAB SR22 | Overgrown | Vegetation | Remove
LC | 121822282 | 001/009 | T3 DI MORAGA-OAKLAND #2 1/9 RPL INSS | CONCORD | ETL.2730.INSL | 2021-07-30 | 2021-07-28 | 2022-12-02 | 2022-01-24 | 2022-01-28 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536103 | T3 DI MORAGA-OAKLAND #2 RPL INSS 8 TWRS | 93K
LC | 121822285 | 001/009 | T3 DI MORAGA-OAKLAND #1 1/9 RPL HRDT | CONCORD | ETL.2720.TOWR | 2021-07-30 | 2021-07-28 | 2022-02-02 | 2022-01-24 | 2022-01-28 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45161288 | T3 DI MORAGA-OAKLAND #1 1/9 RPL HRDT | ICQ
LC | 121822443 | 016/131A | T3 DI MDL FRK-GLD HLL 16/131A RPL HRDD | SACTO | ETL.5140.POLE.WOOD | 2021-07-30 | 2021-07-29 | 2022-10-27 | 2022-01-25 | 2022-01-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44930511 | T3 DI MDL FRK-GLD HLL 16/131A RPL HRDD | ICW
LC | 121822444 | -018/000 | T3 DI FULTON-CALISTOGA -18/0 RPLC HRDW | LAKEVLLE | ETL.6880.POLE.NWOD | 2021-07-30 | 2021-07-28 | 2022-06-27 | 2022-01-24 | 2022-01-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45143390 | T3 DI FULTON-CALISTOGA -18/0 RPLC HRDW | ICW
LC | 121822625 | 014/096 | T2 DI METCALF-GRN VLY 14/96 WDPK COMPLET | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-07-30 | 2021-07-29 | 2022-05-19 | 2022-07-29 | 2022-07-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45117833 | T2 DI METCALF-GRN VLY 14/96 RPR WDPKR | ICW
LC | 121822626 | 028/000 | T2 DI MDCN-WLTS-FRT BRG 028/000 RPL INSW | WILLITS | ETL.7550.INSL.NCER | 2021-07-30 | 2021-07-28 | 2022-08-17 | 2022-07-28 | 2022-07-28 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 45193180 | T2 DI MNDCN-WLTS-FRT BRG 28/0 GRND WASH | ICD
LC | 121822676 | 003/026 | T2 DI DIVIDE-VANDNBERG #2 3/26R RPL STRW | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-30 | 2021-07-28 | 2022-03-08 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31578117 | T2 DI DIVIDE-VNDNBRG #2 2/19L RPL STRW | 70Y
LC | 121822705 | 000/001 | T2 DI SPAULDING-SUMMIT 0/1 RPLC TIES | SACTO | ETL.8060.INSL.CERA | 2021-07-30 | 2021-07-29 | 2022-09-23 | 2022-07-29 | 2022-07-29 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Tie Wire-Steel | Replace | 45224499 | T2 DI SPAULDING-SUMMIT 0/1 RPLC TIES | ICS
LC | 121822866 | 008/057 | T2 DI MORAGA-SAN LNDR #1 8/57 RMV STEP | CONCORD | ETL.2770.TOWR | 2021-07-30 | 2021-07-30 | 2022-02-10 | 2022-07-30 | 2022-07-30 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45168399 | T2 DI MORAGA-SAN LNDR #1 8/57 RMV STEP | ICQ
LC | 121822893 | 039/181 | T2 DI IGNACIO-SOBRANTE 039/181 RMV NEST | LAKEVLLE | ETL.4920.TOWR | 2021-07-30 | 2021-07-30 | 2022-04-15 | 2022-07-30 | 2022-07-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45142471 | T2 DI IGNACIO-SOBRANTE 039/181 RMV NEST | ICS
LC | 121822969 | 011/093 | T3 DI MONTA VISTA-BURNS 11/93 RPL HRDD | MOSSLNDG | ETL.7590.POLE.NWOD | 2021-07-30 | 2021-07-29 | 2022-03-27 | 2022-01-25 | 2022-01-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45082563 | T3 DI MONTA VISTA-BURNS 11/93 RPL HRDD | ICW
LC | 121822984 | 000/009 | T2 DI PIT #1-COTTONWD 0/9 RMV VEG | TABLEMTN | ETL.5390.TOWR | 2021-07-30 | 2021-07-29 | 2022-10-20 | 2022-07-29 | 2022-07-29 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | Overgrown | Vegetation-Tower | Cage Clearing
LC | 121822986 | 023/266 | T3 DI IGNACIO-BOLINAS #2 23/266 RPR STRW | LAKEVLLE | ETL.7180.POLE.WOOD | 2021-07-30 | 2021-07-30 | 2022-09-27 | 2022-01-26 | 2022-01-30 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45142531 | T3 DI IGNACIO-BOLINAS #2 23/266 RPR STRW | ICW
LC | 121823109 | 010/203 | T2 DI CTNWD-RD BLFF 10/203 RPL HRDD | TABLEMTN | ETL.6660.POLE.NWOD | 2021-07-30 | 2021-07-27 | 2022-03-02 | 2022-07-27 | 2022-07-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45194418 | T2 DI CTNWD-RD BLFF 10/203 RPL HRDD | ICW
LC | 121823152 | PF/2 | T2 DI PN FLT PH TAP (CDWR) PF/2 RPL INSS | FRESNO | ETL.4821.INSL.CERA | 2021-07-30 | 2021-07-30 | 2022-02-08 | 2022-07-30 | 2022-07-30 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31590810 | T2 DI PN FLT PH TAP (CDWR) PF/2 RPL INSS | 93K
LC | 121823155 | 007/191 | T3 DI DRM-GRS VLY-WMR 7/191 RPR SPLW | SACTO | ETL.6760.INSL.NCER | 2021-07-30 | 2021-07-27 | 2022-07-20 | 2022-01-23 | 2022-01-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45193659 | T3 DI DRM-GRS VLY-WMR 7/192 RPR SPLW | ICW
LC | 121823257 | 003/090 | T3 DI DEER CREEK-DRUM 003/090 RPL INSW | SACTO | ETL.6690.INSL | 2021-07-30 | 2021-07-30 | 2022-06-22 | 2022-01-26 | 2022-01-30 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548670 | T3 DI DEER CREEK-DRUM 0/6 RPL INSW | 93I
LC | 121823826 | 017/146 | T2 DI CRAG VIEW-CASCADE 17/146 RPLC INSW | TABLEMTN | ETL.1350.INSL | 2021-07-31 | 2021-07-30 | 2022-09-10 | 2022-07-30 | 2022-07-30 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543332 | T2 DI CRAG VIEW-CASCADE 15/128 RPL INSW | 93I
LC | 121823951 | 008/067 | T2 DI SLT SPRNGS-TGR CRK 8/67 RPR INSS | VICTOR | ETL.3500.INSL | 2021-07-31 | 2021-07-30 | 2022-06-25 | 2022-07-30 | 2022-07-30 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45166965 | T2 DI SLT SPRNGS-TGR CRK 8/67 RPR INSS | ICS
LC | 121823954 | 001/031 | T3 DI MIDDLE FORK #1 1/31 RPLC HRDW | SACTO | ETL.8405.POLE.WOOD | 2021-07-31 | 2021-07-30 | 2022-08-01 | 2022-01-26 | 2022-01-30 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45017209 | T3 DI MIDDLE FORK #1 1/31 RPLC HRDW | ICW
LC | 121824217 | 001/007 | T2 DI LAYTONVILLE-COVELO 1/7 RPL STRW | WILLITS | ETL.7390.POLE.WOOD | 2021-07-31 | 2021-07-29 | 2022-06-04 | 2022-07-29 | 2022-07-29 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31547421 | T2 DI LYTNVILLE-COVELO 1/6 RPL POLE | 70Y
LC | 121824409 | 004/000 | T2 DI LAYTONVILLE-COVELO 4/0 RPL HRDD | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-07-31 | 2021-07-28 | 2021-10-19 | 2022-07-28 | 2022-07-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44999935 | T2 DI LAYTONVILLE-COVELO 4/0 RPL HRDD | ICW
LC | 121824547 | 001/022 | T2 DI IGNACIO-BLNS #1 001/022 RPL STRW | LAKEVLLE | ETL.7140.POLE.WOOD | 2021-07-31 | 2021-07-30 | 2022-06-15 | 2022-07-30 | 2022-07-30 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548704 | T2 DI IGNACIO-BLNS #1 001/022 RPL STRW | 70Y
LC | 121824671 | 004/027 | T2 DI DVD-VNDBG #2 4/27R RPL STRW COMPLT | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-31 | 2021-07-28 | 2022-04-22 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31578117 | T2 DI DIVIDE-VNDNBRG #2 2/19L RPL STRW | 70Y
LC | 121824672 | 004/027 | T2 DI DVD-VNDBG #2 4/27C RPL STRW COMPLT | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-31 | 2021-07-28 | 2022-04-22 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31578117 | T2 DI DIVIDE-VNDNBRG #2 2/19L RPL STRW | 70Y
LC | 121824673 | 003/026 | T2 DI DIVIDE-VANDNBERG #2 3/26L RPL STRW | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-31 | 2021-07-28 | 2022-03-08 | 2022-07-28 | 2022-07-28 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31578117 | T2 DI DIVIDE-VNDNBRG #2 2/19L RPL STRW | 70Y
LC | 121824677 | :003/020C | T2 DI ROCK CREEK-POE :003/020C RPR GYWS | TABLEMTN | ETL.5630.POLE.NWOD | 2021-07-31 | 2021-07-30 | 2022-08-07 | 2022-07-30 | 2022-07-30 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45213412 | T2 DI ROCK CREEK-POE :003/020C RPR GYWS | ICS
LC | 121824731 | 004/061 | T2 DI PIT #1-HAT CRK #2 004/061 RPR STRW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-07-31 | 2021-07-31 | 2022-06-11 | 2022-07-31 | 2022-07-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45213912 | T2 DI PIT #1-HAT CRK #2 004/061 RPR STRW | ICW
LC | 121825174 | 006/106 | T2 DI CNRVL-TBL MT 6/106 RPR INSW CMPLT | TABLEMTN | ETL.6320.INSL.NCER | 2021-07-31 | 2021-07-31 | 2022-04-25 | 2022-07-31 | 2022-07-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45197477 | T2 DI CNTRVLLE-TBL MTN 006/106 RPR INSW | ICW
LC | 121825176 | 005/080 | T2 DI CNTRVLLE-TBL MTN 005/080 RPR INSW | TABLEMTN | ETL.6320.INSL.NCER | 2021-07-31 | 2021-07-31 | 2022-04-26 | 2022-07-31 | 2022-07-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45197501 | T2 DI CNTRVLLE-TBL MTN 005/080 RPR INSW | ICW
LC | 121825177 | 005/080 | T2 DI CNTRVLLE-TBL MTN 005/080 RPL DAMW | TABLEMTN | ETL.6320.INSL.NCER | 2021-07-31 | 2021-07-31 | 2022-04-26 | 2022-07-31 | 2022-07-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace | 45197500 | T2 DI CNTRVLLE-TBL MTN 005/080 RPL DAMW | ICW
LC | 121829468 | 045/002 | T2 TRINITY-MAPLE CREEK 45/2 RPR IBWW | EUREKA | ETL.8170.POLE.WDPS | 2021-08-02 | 2021-07-31 | 2022-04-28 | 2022-07-31 | 2022-07-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45155497 | T2 TRINITY-MAPLE CREEK 45/2 RPR IBWW | ICW
LC | 121829483 | 058/425D | T2 EI BRIDGVL-CTNWD 58/425D RPR SWTC 239 | EUREKA | ETL.1110.SWIT | 2021-08-02 | 2021-07-31 | 2022-10-03 | 2022-07-31 | 2022-07-31 | Late | 623 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP NONR COMP OH FMOB TR2 PRTO SR22 | Out of Adjustment | Switch | Repair | 45158752 | T2 EI BRDGVLL-CTTN 58/425D RPR SWTC 239 | ICE
LC | 121832305 | 002/016 | T3 EI SOBRANTE-R #1 2/016 RPR STRT | CONCORD | ETL.3770.TOWR | 2021-08-02 | 2021-08-02 | 2022-06-01 | 2022-01-29 | 2022-02-02 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP CREW COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45211583 | T3 EI SOBRANTE-R #1 2/016 RPR STRT | ICQ
LC | 121832599 | 005/112 | T2 BURNS-LONE STAR #2 5/112 RPR SWITCH | MOSSLNDG | ETL.6240.POLE.NWOD | 2021-08-02 | 2021-08-02 | 2022-04-06 | 2022-08-02 | 2022-08-02 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Switch-Wood | Repair | 45166613 | T2 BURNS-LONE STAR #2 5/112 RPR SWITCH | ICW
LC | 121837480 | 024/346 | T2 WV CLAY-MARTEL 24/346 INS DAMW | VICTOR | ETL.8250.INSL.NCER | 2021-08-03 | 2021-08-03 | 2022-07-18 | 2022-08-03 | 2022-08-03 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Wood | Install | 45097044 | T2 WV CLAY-MARTEL 24/346 INS DAMW | ICW
LC | 121838787 | :001/013 | T2 WV BCKS CRK-RC-CRST :1/13 RPR SPLW | TABLEMTN | ETL.4430.TOWR | 2021-08-03 | 2021-08-03 | 2022-06-29 | 2022-08-03 | 2022-08-03 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45212624 | T2 WV BCKS CRK-RC-CRST :1/13 RPR SPLW | ICS
LC | 121838868 | 012/413 | T2 WV SPAULDING-SUMMIT 12/413 RPR SPLW | SACTO | ETL.8060.POLE.WOOD | 2021-08-03 | 2021-08-03 | 2022-09-20 | 2022-08-03 | 2022-08-03 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45224540 | T2 WV SPAULDING-SUMMIT 12/413 RPR SPLW | ICW
LC | 121840255 | 010/055 | T2 MRR BY-SN LS OBSPO #2 10/55 HANGER | PISMOBCH | ETL.2820.INSL.NCER | 2021-08-03 | 2021-08-03 | 2022-08-30 | 2022-08-03 | 2022-08-03 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Tower | Replace | 45098848 | T2 MRR BY-SN LS OBSPO #2 10/55 HANGER | ICQ
LC | 121841580 | 001/004 | T2 GARCIA TAP 1/4 RMV VEG | WILLITS | ETL.8411.POLE.WOOD | 2021-08-04 | 2021-07-29 | 2021-08-10 | 2022-07-29 | 2022-07-29 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO FRAB | Overgrown | Vegetation | Trim
LC | 121842133 | 003/072 | T2 WEIMAR-HALSEY 3/072 RMV VEG | SACTO | ETL.8340.POLE.NWOD | 2021-08-04 | 2021-08-04 | 2022-11-07 | 2022-08-04 | 2022-08-04 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW NONR CNCL OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 121843140 | 005/042 | T2 WV PRADISE-TABLE MTN 005/042 RPR INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-08-04 | 2021-08-04 | 2022-02-28 | 2022-08-04 | 2022-08-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213841 | T2 WV PRADISE-TABLE MTN 005/042 RPR INSS | ICS
LC | 121844255 | 005/043 | T2 WV PRADISE-TABLE MTN 005/043 RPR INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-08-04 | 2021-08-04 | 2022-02-28 | 2022-08-04 | 2022-08-04 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45213293 | T2 WV PRADISE-TABLE MTN 005/043 RPR INSS | ICS
LC | 121848661 | 013/172 | T2 WV VLLY SPRNGS-CLY 13/172 INS DAMW | VICTOR | ETL.8264.POLE.WOOD | 2021-08-05 | 2021-08-05 | 2022-03-21 | 2022-08-05 | 2022-08-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Wood | Install | 45110702 | T2 WV VLLY SPRNGS-CLY 13/172 INS DAMW | ICW
LC | 121854886 | 005/050 | WV T2 PARADISE-TABLE MTN 5/50 INS DAMS | TABLEMTN | ETL.4316.TOWR | 2021-08-06 | 2021-08-06 | 2022-02-24 | 2022-08-06 | 2022-08-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Damper-Steel | Install | 45194509 | WV T2 PARADISE-TABLE MTN 5/50 INS DAMS | ICS
LC | 121855717 | 011/115 | T2 DI PIT#5-ROUND MTN#1 11/115L RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-08-06 | 2021-07-20 | 2022-07-12 | 2022-07-20 | 2022-07-20 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31547480 | T2 DI PIT #5-ROUND MTN 1 1/16R RPL STRW | 70Y
LC | 121856898 | -018/006 | T3 WV FULTN-CLISTOG 18/6 INS ANCW | LAKEVLLE | ETL.6880.POLE.NWOD | 2021-08-06 | 2021-08-06 | 2022-05-25 | 2022-02-02 | 2022-02-06 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW CREW COMP OH FMOB TR3 PRTO FRAB | Missing | Anchor-Wood | Install | 31601822 | T3 WV FULTON-CALISTOGA -18/6 INS ANCW | 93E
LC | 121862692 | 000/001 | T3 VOLTA-DESCHUTES 0/1 RPL STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2021-08-09 | 2021-07-24 | 2021-08-26 | 2022-01-20 | 2022-01-24 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR COMP OH TR3 PRTO FRAB | Rotten | Structure-Wood | Replace | 31542832 | T3 DI VOLTA-DESCHUTES 000/001 RPL POLE | 93E
LC | 121862693 | 007/151A | T3 VOLTA-DESCHUTES 7/151A RPL STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2021-08-09 | 2021-07-24 | 2022-06-15 | 2022-01-20 | 2022-01-24 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO FRAB | Rotten | Structure-Wood | Replace | 31575554 | T3 VOLTA-DESCHUTES 7/151A RPL STRW | 70Y
LC | 121862794 | 004/031 | T2 TRINITY-COTTNWD 4/31R RPL STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-08-09 | 2021-07-31 | 2022-08-07 | 2022-07-31 | 2022-07-31 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31577970 | T2 TRINITY-COTTNWD 4/31R RPL STRW | 70Y
LC | 121864822 | 028/010 | T2 DI MNDCN-WLTS-FRT BRG 28/10 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2021-08-09 | 2021-08-09 | 2022-08-16 | 2022-08-09 | 2022-08-09 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31551283 | T2 DI MNDCN-WLTS-FRT BRG 28/10 RPL INSW | 93I
LC | 121864974 | 029/440 | T2 WV CLAY-MARTEL 29/440 INS DAMW | VICTOR | ETL.8250.POLE.WOOD | 2021-08-09 | 2021-08-09 | 2022-02-02 | 2022-08-09 | 2022-08-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Wood | Install | 45067392 | T2 WV CLAY-MARTEL 29/440 INS DAMW | ICW
LC | 121865086 | 014/387 | T3 WV COLGATE-ALLEGHANY 14/387 INS DAMW | SACTO | ETL.6470.POLE.WOOD | 2021-08-09 | 2021-08-09 | 2022-06-20 | 2022-02-05 | 2022-02-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO NTDE | Missing | Damper-Wood | Install | 45224726 | T3 WV COLGATE-ALLEGHANY 14/387 INS DAMW | ICW
LC | 121866669 | 008/000 | T3 WV LAURELES-OTTER 8/0 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2021-08-09 | 2021-08-09 | 2022-08-15 | 2022-02-05 | 2022-02-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW CREW COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31579737 | T3 WV LAURELES-OTTER 8/0 RPL STRW | 70Y
LC | 121866923 | 001/012 | T2 LAURELES-OTTER 001/012 RPL GUY STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2021-08-09 | 2021-08-09 | 2022-08-08 | 2022-08-09 | 2022-08-09 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Guy Pole-Wood | Replace | 31579738 | T2 LAURELES-OTTER 001/012 RPL GUY STRW | 93E
LC | 121879352 | 004/031 | T2 TRINITY-COTTNWD 4/31L RPL STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-08-10 | 2021-07-31 | 2022-08-07 | 2022-07-31 | 2022-07-31 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31577970 | T2 TRINITY-COTTNWD 4/31R RPL STRW | 70Y
LC | 121879630 | 008/004 | T3 WV MONTE RIO-FULTON 8/4 RPL STRW | LAKEVLLE | ETL.7630.POLE.WOOD | 2021-08-10 | 2021-08-10 | 2022-06-28 | 2022-02-06 | 2022-02-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW CREW COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541596 | T3 EI MONTE RIO-FULTON 7/018 RPL POLE | 70Y
LC | 121883934 | 009/002A | T2 MELONES-CURTIS 9/2A RPR SWTC | VICTOR | ETL.2390.POLE.NWOD | 2021-08-11 | 2021-08-11 | 2021-10-14 | 2022-08-11 | 2022-08-11 | On-time | 623 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Out of Adjustment | Switch | Repair | 44943951 | T2 MELONES-CURTIS 9/2A RPR SWTC | ICE
LC | 121887385 | 008/048 | T3 CASTRO VALLEY-NEWARK 8/048 RPL STRT | CONCORD | ETL.4450.TOWR | 2021-08-11 | 2021-08-11 | 2021-08-13 | 2022-02-07 | 2022-02-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW CREW COMP OH FMOB TR3 FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 44945530 | T3 CASTRO VALLEY-NEWARK 8/045 RPL STRT | ICQ
LC | 121887627 | 010/287 | WV T3 COLGATE-ALLEGHANY 10/287 INS DMPR | SACTO | ETL.6470.POLE.WOOD | 2021-08-11 | 2021-08-11 | 2022-06-18 | 2022-02-07 | 2022-02-11 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB NTDE | Missing | Damper-Wood | Install | 45224727 | WV T3 COLGATE-ALLEGHANY 10/287 INS DMPR | ICW
LC | 121889170 | 015/000 | T2 TRINITY-MAPLE CREEK 15/00 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-12 | 2021-08-12 | 2021-09-12 | 2022-08-12 | 2022-08-12 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549277 | T2 TRINITY-MAPLE CREEK 15/00 RPL STRW | 92F
LC | 121889715 | 003/025 | T2 EI TRINITY-COTTONWOOD 3/25 RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2021-08-12 | 2021-03-19 | 2021-09-03 | 2022-03-19 | 2022-03-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 44979846 | T2 EI TRINITY-COTTONWOOD 3/25 RPR GYWW | ICS
LC | 121890033 | 021/166 | T2 DI MIDDLE FK-GLD HLL 21/166C RPR ANCW | SACTO | ETL.5140.POLE.WDPS | 2021-08-12 | 2021-05-26 | 2021-12-13 | 2022-05-26 | 2022-05-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Anchor-Wood | Repair | 45102127 | T2 DI MIDDLE FK-GLD HLL 21/166C RPR ANCW | ICW
LC | 121890035 | 013/086 | T2 DI METCALF-GRN VALLEY 13/86R RPR GYWW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-08-12 | 2021-05-29 | 2022-07-12 | 2022-05-29 | 2022-05-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45224023 | T2 DI METCALF-GRN VALLEY 13/86R RPR GYWW | ICW
LC | 121890036 | 013/086 | T2 DI METCALF-GRN VALLEY 13/86C RPR GYWW | MOSSLNDG | ETL.2540.POLE.WDPS | 2021-08-12 | 2021-05-29 | 2022-07-12 | 2022-05-29 | 2022-05-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45224024 | T2 DI METCALF-GRN VALLEY 13/86C RPR GYWW | ICW
LC | 121890289 | 011/110 | T2 DI PIT #5-RD MTN #1 11/110R INS HRDW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-08-12 | 2021-07-06 | 2022-07-15 | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR NTDE | Missing | Hardware-Wood | Install | 45213325 | T2 DI PIT #5-RD MTN #1 11/110R INS HRDW | ICW
LC | 121890421 | 005/044 | T2 DI TRINITY-CTTNWD 005/044R RPL STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-08-12 | 2021-07-07 | 2022-08-24 | 2022-07-07 | 2022-07-07 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31548131 | T2 DI TRINITY-CTTNWD 005/044L RPL | 70Y
LC | 121890605 | 021/166 | T2 DI MIDDLE FK-GLD HLL 21/166C RPR STRW | SACTO | ETL.5140.POLE.WDPS | 2021-08-12 | 2021-05-26 | 2021-12-14 | 2022-05-26 | 2022-05-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45017208 | T2 DI MIDDLE FK-GLD HLL 21/166C RPR STRW | ICW
LC | 121890712 | 020/170 | T2 DI CRAG VIEW-CASCADE 20/170R RPR STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-08-12 | 2021-05-29 | 2022-09-14 | 2022-05-29 | 2022-05-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45296822 | T2 DI CRAG VIEW-CASCADE 20/170R RPR STRW | ICW
LC | 121890802 | 012/089 | T2 DI GRN VLLY-LLAGAS 12/89R RPR GYWW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-08-12 | 2021-05-28 | 2021-09-30 | 2022-05-28 | 2022-05-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44993533 | T2 DI GRN VLLY-LLAGAS 12/89R RPR GYWW | ICW
LC | 121890804 | 012/089 | T2 DI GRN VLLY-LLAGAS 12/89C RPR GYWW | MOSSLNDG | ETL.1720.POLE.WDPS | 2021-08-12 | 2021-05-28 | 2021-09-30 | 2022-05-28 | 2022-05-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44993534 | T2 DI GRN VLLY-LLAGAS 12/89C RPR GYWW | ICW
LC | 121892404 | 027/012 | T3 WV FULTON-HOPLAND 27/12 RPL GYWW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-08-12 | 2021-08-12 | 2021-08-17 | 2022-02-08 | 2022-02-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 44948643 | T3 WV FULTON-HOPLAND 27/12 RPL GYWW | ICW
LC | 121893529 | 013/112C | T2 WV CRAG VIEW-CSCADE 13/112C RPL ANCS | TABLEMTN | ETL.1350.POLE.NWOD | 2021-08-12 | 2021-08-12 | 2022-10-29 | 2022-08-12 | 2022-08-12 | Late | 93Z | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Anchor-Steel | Replace
LC | 121897689 | 027/119 | T2 WV DIABLO-MESA 27/119 INS MKBL | PISMOBCH | ETL.4620.INSL | 2021-08-13 | 2021-08-13 | 2022-04-24 | 2022-08-13 | 2022-08-13 | On-time | 671 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Missing | FAA Lighting-Steel | Install | 31504388 | T2 DIABLO-MESA INS MRKS BALLS | 93V
LC | 121897801 | 027/118 | T2 WV DIABLO-MESA 27/118 BALL MARKER | PISMOBCH | ETL.4620.INSL | 2021-08-13 | 2021-08-13 | 2022-04-24 | 2022-08-13 | 2022-08-13 | On-time | 671 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | FAA Lighting-Steel | Replace | 31504388 | T2 DIABLO-MESA INS MRKS BALLS | 93V
LC | 121900682 | 015/006 | T2 TRINITY-MAPLE CREEK 15/006 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-13 | 2021-08-13 | 2021-09-26 | 2022-08-13 | 2022-08-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31549277 | T2 TRINITY-MAPLE CREEK 15/00 RPL STRW | 92F
LC | 121900691 | 015/005 | T2 TRINITY-MAPLE CREEK 015/005 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-13 | 2021-08-13 | 2021-09-24 | 2022-08-13 | 2022-08-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31549277 | T2 TRINITY-MAPLE CREEK 15/00 RPL STRW | 92F
LC | 121900742 | 061/004 | T2 HUMBOLDT-TRINITY 61/004L RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-08-13 | 2021-08-13 | 2021-09-16 | 2022-08-13 | 2022-08-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31549273 | T2 WV HMBLDT-TRNITY 52/4 RPL INSW | 92F
LC | 121900744 | 061/001 | T2 HUMBOLDT-TRINITY 61/001L RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-08-13 | 2021-08-13 | 2021-09-12 | 2022-08-13 | 2022-08-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31549273 | T2 WV HMBLDT-TRNITY 52/4 RPL INSW | 92F
LC | 121904754 | 061/004 | T2 HUMBOLDT-TRINITY 61/004R RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-08-16 | 2021-08-13 | 2021-09-16 | 2022-08-13 | 2022-08-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31549273 | T2 WV HMBLDT-TRNITY 52/4 RPL INSW | 92F
LC | 121904757 | 061/001 | T2 HUMBOLDT-TRINITY 61/001R RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-08-16 | 2021-08-13 | 2021-09-12 | 2022-08-13 | 2022-08-13 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31549273 | T2 WV HMBLDT-TRNITY 52/4 RPL INSW | 92F
LC | 121908470 | 005/048 | T2 WV PARDISE-TBL MTN 5/48 INS DAMT | TABLEMTN | ETL.4316.INSL.NCER | 2021-08-16 | 2021-08-16 | 2022-02-24 | 2022-08-16 | 2022-08-16 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install | 45193887 | T2 WV PARDISE-TBL MTN 5/48 INS DAMT | ICS
LC | 121908595 | 095/006 | T2 WV HUMBOLDT-TRINITY 95/6 INS DAMT | EUREKA | ETL.1820.INSL.NCER | 2021-08-16 | 2021-08-16 | 2022-03-23 | 2022-08-16 | 2022-08-16 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 45160744 | T2 WV HUMBOLDT-TRINITY 95/6 INS DAMT | ICW
LC | 121908671 | 032/138 | T2 WV MRRO BAY-SLAR #1 32/138 RPL ARMR | PISMOBCH | ETL.5300.INSL.NCER | 2021-08-16 | 2021-08-16 | 2022-06-18 | 2022-08-16 | 2022-08-16 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair | 45068708 | T2 WV MRRO BAY-SLAR #1 32/138 RPL ARMR | ICS
LC | 121911024 | 008/005 | T3 WV MONTE RIO-FULTON 8/5 INS DMPW | LAKEVLLE | ETL.7630.POLE.NWOD | 2021-08-17 | 2021-08-17 | 2022-06-28 | 2022-02-13 | 2022-02-17 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH FMOB TR3 PRTO AIR FRAB | Missing | Damper-Wood | Install | 45142164 | T3 WV MONTE RIO-FULTON 8/5 INS DMPW | ICW
LC | 121917163 | 000/005 | WV T2 SPAULDING-SUMMIT 0/5 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-08-18 | 2021-08-18 | 2022-09-23 | 2022-08-18 | 2022-08-18 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45224541 | WV T2 SPAULDING-SUMMIT 0/5 RPR GYWW | ICW
LC | 121917457 | 004/050 | WV T2 SNEATH LN-PACIFICA 4/50B RPL STRW | METCALF | ETL.7575.POLE.WDPS | 2021-08-18 | 2021-08-18 | 2022-11-03 | 2022-08-18 | 2022-08-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31580346 | WV T2 SNEATH LN-PACIFICA 4/50R RPL STRW | 70Y
LC | 121919671 | 015/494B | T2 WV SPAULDING-SUMMIT 15/494B RPR SPLW | SACTO | ETL.8060.INSL.NCER | 2021-08-19 | 2021-08-19 | 2022-09-22 | 2022-08-19 | 2022-08-19 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45224542 | T2 WV SPAULDING-SUMMIT 15/494B RPR SPLW | ICW
LC | 121919972 | 004/050 | WV T2 SNEATH LN-PACIFICA 4/50 RPL STRW | METCALF | ETL.7575.POLE.WDPS | 2021-08-19 | 2021-08-18 | 2022-11-03 | 2022-08-18 | 2022-08-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW CREW COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31580346 | WV T2 SNEATH LN-PACIFICA 4/50R RPL STRW | 70Y
LC | 121919975 | 004/050 | WV T2 SNEATH LN-PACIFICA 4/50R RPL STRW | METCALF | ETL.7575.POLE.WDPS | 2021-08-19 | 2021-08-18 | 2022-11-03 | 2022-08-18 | 2022-08-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31580346 | WV T2 SNEATH LN-PACIFICA 4/50R RPL STRW | 70Y
LC | 121921048 | 010/348 | T2 SPAULDING-SUMMIT 010/348 RPL POLE | SACTO | ETL.8060.POLE.WOOD | 2021-08-19 | 2021-08-12 | 2021-08-12 | 2022-08-12 | 2022-08-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW CREW COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31453471 | T2 DI SPAULDING-SUMMIT 002/108 REPL POLE | 70Y
LC | 121921529 | 012/336 | T3 WV COLGATE-ALLEGHANY 12/336 INS DAM | SACTO | ETL.6470.POLE.NWOD | 2021-08-19 | 2021-08-19 | 2022-06-17 | 2022-02-15 | 2022-02-19 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB NTDE | Missing | Damper-Steel | Install | 45224728 | T3 WV COLGATE-ALLEGHANY 12/336 INS DAM | ICS
LC | 121921771 | 016/009 | T2 TRINITY-MAPLE CREEK 16/9 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-19 | 2021-08-19 | 2022-12-06 | 2022-08-19 | 2022-08-19 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31550342 | T2 TRINITY-MAPLE CREEK 16/8 RPL STRW | 70Y
LC | 121927082 | 014/095 | T2 WV CAYUCOS-CAMBRIA 14/95 INS DAMP | PISMOBCH | ETL.8560.INSL.NCER | 2021-08-20 | 2021-08-20 | 2022-06-01 | 2022-08-20 | 2022-08-20 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install | 45068466 | T2 WV CAYUCOS-CAMBRIA 14/95 INS DAMP | ICS
LC | 121927405 | 009/196 | HMLTN BRANCH-CHESTER 9/196 REPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2021-08-20 | 2021-08-20 | 2022-07-28 | 2022-08-20 | 2022-08-20 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO FRAB SR22 | Rotten | Structure-Wood | Replace | 31544408 | T2 DI HAMLTN BRCH-CHESTR 8/181 RPL POLE | 70Y
LC | 121928543 | 022/330 | T2 WV KESWICK-TRINITY 22/330 INS DAMP | TABLEMTN | ETL.7270.POLE.WOOD | 2021-08-20 | 2021-08-20 | 2022-05-31 | 2022-08-20 | 2022-08-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Wood | Install | 45212828 | T2 WV KESWICK-TRINITY 22/330 INS DAMP | ICW
LC | 121934849 | 019/007A | T2 TRINITY-MAPLE CRK 019/007A RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2021-08-22 | 2021-08-22 | 2022-02-08 | 2022-08-22 | 2022-08-22 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31557253 | T2 TRINITY-MAPLE CREEK 14/6 RPL POLE | 70Y
LC | 121942182 | 008/096 | T3 WV IGNACIO-BOLINAS #1 8/96 RPR SPLW | LAKEVLLE | ETL.7140.POLE.WOOD | 2021-08-23 | 2021-08-23 | 2022-06-17 | 2022-02-19 | 2022-02-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Splice-Wood | Replace | 45128021 | T3 WV IGNACIO-BOLINAS #1 8/96 RPR SPLW | ICW
LC | 121942699 | 013/238 | WV T2 VALLEY SPRINGS #2 13/238 RPR SPLW | VICTOR | ETL.9460.POLE.WOOD | 2021-08-23 | 2021-08-23 | 2022-06-16 | 2022-08-23 | 2022-08-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Splice-Wood | Repair | 45167627 | WV T2 VALLEY SPRINGS #2 13/238 RPR SPLW | ICW
LC | 121944786 | 006/057 | T2 WV PRADISE-TABLE MTN 006/057 RPL SPLS | TABLEMTN | ETL.4316.TOWR | 2021-08-24 | 2021-08-24 | 2022-05-11 | 2022-08-24 | 2022-08-24 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Splice-Steel | Replace | 45196976 | WV T2 PRADISE-TABLE MTN 006/057 RPL SPLS | ICS
LC | 121947435 | 001/045 | T3 KILARC-CEDAR CREEK-WOOD 1/45 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2021-08-24 | 2021-08-21 | 2022-04-22 | 2022-02-17 | 2022-02-21 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR COMP OH TR3 PRTO FRAB | Rotten | Structure-Wood | Replace | 31542889 | T3 DI KILARC-CEDAR CREEK 1/44 RPL PL | 70Y
LC | 121947439 | 008/172 | T2 VOLTA-DESCHUTES-WOOD 8/172 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2021-08-24 | 2021-08-21 | 2022-06-08 | 2022-08-21 | 2022-08-21 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31575554 | T3 VOLTA-DESCHUTES 7/151A RPL STRW | 70Y
LC | 121947699 | 010/093 | T2 WV EL DORAD-MISS FT #2 10/93 RPL INSS | SACTO | ETL.1540.SWIT | 2021-08-24 | 2021-08-24 | 2022-05-25 | 2022-08-24 | 2022-08-24 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547631 | T2 WV EL DORADO-MSR FLT #2 RPL INSS 10TW | 93K
LC | 121953131 | 003/014 | T2 MONTA VISTA-JEFFERS #1 3/14 WASH INSU | METCALF | ETL.5220.INSL | 2021-08-25 | 2021-08-25 | 2022-01-25 | 2022-08-25 | 2022-08-25 | On-time | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | Contaminated | Insulator | Ground Wash | 45145039 | T2 MONTA VISTA-JEFFERS #1 3/14 WASH INSU | ICD
LC | 121954178 | 003/016 | T2 MONTA VISTA-JEFFERS #1 3/16 WASH INSU | METCALF | ETL.5220.INSL | 2021-08-25 | 2021-08-25 | 2022-01-25 | 2022-08-25 | 2022-08-25 | On-time | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | Contaminated | Insulator | Ground Wash | 45145120 | T2 MONTA VISTA-JEFFERS #1 3/16 WASH INSU | ICD
LC | 121954184 | 001/001 | T2 EI LAYTONVILLE-COVELO 1/1 RPR INSW | WILLITS | ETL.7390.POLE.WOOD | 2021-08-25 | 2021-08-23 | 2022-06-04 | 2022-08-23 | 2022-08-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Repair | 44999869 | T2 EI LAYTONVILLE-COVELO 1/1 RPR INSW | ICW
LC | 121954204 | 040/006 | T2 EI MENDO-WILL-FT BRAGG 40/6 RPR INSW | WILLITS | ETL.7550.POLE.WOOD | 2021-08-25 | 2021-08-25 | 2022-08-16 | 2022-08-25 | 2022-08-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45150030 | T2 EI MENDO-WILL-FT BRAGG 40/6 RPR INSW | ICW
LC | 121957167 | 009/104 | T2 DRUM-SUMMIT #1 9/104L RPL ANCW | SACTO | ETL.1440.POLE.STPS | 2021-08-25 | 2021-03-24 | 2021-08-31 | 2022-03-24 | 2022-03-24 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR CUSI COMP OH TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31550787 | DRUM-SUMMIT #1 9/104L RPL ANCW | 93E
LC | 121957250 | 009/104 | T2 DRUM-SUMMIT #1 9/104R RPL ANCW | SACTO | ETL.1440.POLE.STPS | 2021-08-25 | 2021-03-24 | 2021-08-31 | 2022-03-24 | 2022-03-24 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31550787 | DRUM-SUMMIT #1 9/104L RPL ANCW | 93E
LC | 121957252 | 009/104 | T2 DRUM-SUMMIT #1 9/104R RPR GYWW | SACTO | ETL.1440.POLE.STPS | 2021-08-25 | 2021-03-24 | 2021-08-30 | 2022-03-24 | 2022-03-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44988260 | T2 DRUM-SUMMIT #1 9/104R RPR GYWW | ICW
LC | 121957254 | 009/104 | T2 DRUM-SUMMIT #1 9/104R REFRAME | SACTO | ETL.1440.POLE.STPS | 2021-08-25 | 2021-03-24 | 2021-08-31 | 2022-03-24 | 2022-03-24 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31550787 | DRUM-SUMMIT #1 9/104L RPL ANCW | 93E
LC | 121958964 | 004/044 | T3 WV IGNCIO-BOLINAS #1 004/044 RPL SPLW | LAKEVLLE | ETL.7140.POLE.WOOD | 2021-08-26 | 2021-08-26 | 2022-11-17 | 2022-02-22 | 2022-02-26 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Splice-Wood | Replace | 45127654 | T3 WV IGNCIO-BOLINAS #1 004/044 RPL SPLW | ICW
LC | 121961520 | 013/062 | T3 WV SAN RAMON-MORAGA 13/62 RPL INSS | CONCORD | ETL.5660.INSL | 2021-08-26 | 2021-08-26 | 2022-06-21 | 2022-02-22 | 2022-02-26 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31526414 | EI SAN RAMON-MORAGA RPL INS IN 7 TWRS. | 93K
LC | 121967145 | 003/049 | T2 WV WEIMAR #1 3/049 COMPLETE | SACTO | ETL.7560.POLE.NWOD | 2021-08-27 | 2021-08-27 | 2022-08-10 | 2022-08-27 | 2022-08-27 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Steel | Repair | 45210966 | T2 WV WEIMAR #1 3/049 RPR STRS | ICS
LC | 121970673 | 007/057 | T2 BUTTE VALLEY-CARIBOU 7/054D CMPLTD | TABLEMTN | ETL.1180.POLE.WOOD | 2021-08-30 | 2021-08-30 | 2022-11-01 | 2022-08-30 | 2022-08-30 | Late | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31550793 | T2 BUTTE VALLEY-CARIBOU 7/054A RPL STRW | 92F
LC | 121970786 | 007/055B | T2 BUTTE VALLEY-CARIBOU 7/054A CMPTD | TABLEMTN | ETL.1180.POLE.WOOD | 2021-08-30 | 2021-08-30 | 2022-11-01 | 2022-08-30 | 2022-08-30 | Late | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB NTDE | Fire | Emergency | Replace | 31550793 | T2 BUTTE VALLEY-CARIBOU 7/054A RPL STRW | 92F
LC | 121972364 | 003/027 | T2 PIT #1-COTTONWOOD 3/27 RPL INSS | TABLEMTN | ETL.5390.TOWR | 2021-08-30 | 2021-08-30 | 2022-03-03 | 2022-08-30 | 2022-08-30 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31541306 | T2 EI PIT #1-CTTNWD RPL INSS 3 TWR | 93K
LC | 121972568 | 009/016 | T3 BRIDGEVILLE-GARBERVILLE 9/16 RPR GYWW | EUREKA | ETL.6220.POLE.NWOD | 2021-08-30 | 2021-08-30 | 2022-02-22 | 2022-02-26 | 2022-02-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45010822 | T3 BRIDGEVILLE-GARBERVILLE 9/16 RPR GYWW | ICW
LC | 121973862 | 007/147 | T2 WV VALLEY SPRINGS #1 7/147 RPL SPLW | VICTOR | ETL.8210.INSL.CERA | 2021-08-30 | 2021-08-30 | 2022-02-17 | 2022-08-30 | 2022-08-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Replace | 45151085 | T2 WV VALLEY SPRINGS #1 7/147 RPL SPLW | ICW
LC | 121973966 | 022/349 | T2 WV KESWICK-TRINITY 22/349 RPR GYWW | TABLEMTN | ETL.7270.POLE.WOOD | 2021-08-30 | 2021-08-30 | 2022-10-24 | 2022-08-30 | 2022-08-30 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Repair | 45212484 | T2 WV KESWICK-TRINITY 22/349 RPR GYWW | ICW
LC | 121974069 | 009/133 | T2 DELTA-MTN GATE JCT 9/133L RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-08-30 | 2021-08-30 | 2022-08-29 | 2022-08-30 | 2022-08-30 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544588 | EI T2 DELTA-MTN GATE JCT 8/124 RPL STRW | 70Y
LC | 121976937 | 001/007 | T2 DI CHOWCHILLA-KERCKHOFF 1/7 RPR ANCW | FRESNO | ETL.1250.POLE.NWOD | 2021-08-31 | 2021-08-30 | 2022-02-16 | 2022-08-30 | 2022-08-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45068091 | T2 DI CHOWCHILLA-KERCKHOFF 1/7 RPR ANCW | ICW
LC | 121977218 | 009/133 | T2 DELTA-MTN GATE JCT 9/133R RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-08-31 | 2021-08-30 | 2022-08-29 | 2022-08-30 | 2022-08-30 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544588 | EI T2 DELTA-MTN GATE JCT 8/124 RPL STRW | 70Y
LC | 121977525 | 004/093 | T3 WV BURNS-LONE STAR #2 4/093 INS DAMW | MOSSLNDG | ETL.6240.POLE.WOOD | 2021-08-31 | 2021-08-31 | 2022-03-30 | 2022-02-27 | 2022-02-28 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | Missing | Damper-Wood | Install | 45075343 | T3 WV BURNS-LONE STAR #2 4/093 INS DAMW | ICW
LC | 121978543 | 004/073 | T2 WV COLGATE-PALERMO 4/073 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2021-08-31 | 2021-08-31 | 2022-08-30 | 2022-08-31 | 2022-08-31 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45218842 | T2 WV COLGATE-PALERMO 4/073 RPR STRW | ICW
LC | 121978929 | 004/049 | T3 WV IGNACIO-BOLINAS #1 4/049 INS DAMW | LAKEVLLE | ETL.7140.POLE.WOOD | 2021-08-31 | 2021-08-31 | 2022-01-14 | 2022-02-27 | 2022-02-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | Missing | Damper-Wood | Install | 45168704 | T3 WV IGNACIO-BOLINAS #1 4/049 INS DAMW | ICW
LC | 121979152 | 008/014 | T2 WV FORT BRAGG-ELK 8/014 INS DAMW | WILLITS | ETL.2060.POLE.WOOD | 2021-08-31 | 2021-08-31 | 2022-10-26 | 2022-08-31 | 2022-08-31 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAR NTDE SR22 | Missing | Damper-Wood | Install | 45144039 | T2 WV FORT BRAGG-ELK 8/014 INS DAMW | ICW
LC | 121983790 | 009/104 | T2 DRUM-SUMMIT #1 9/104L RPL GYWW | SACTO | ETL.1440.POLE.STPS | 2021-09-01 | 2021-03-24 | 2022-08-27 | 2022-03-24 | 2022-03-24 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 31550787 | DRUM-SUMMIT #1 9/104L RPL ANCW | 93E
LC | 121985436 | 016/359 | T2 WV VOLTA-DESCHUTES 16/359 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2021-09-01 | 2021-09-01 | 2022-06-13 | 2022-09-01 | 2022-09-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31426666 | T3 EI VOLTA-DESCHUTES 000/010 RPL POLE | 70Y
LC | 121985520 | 015/323 | T2 WV VOLTA-DESCHUTES 15/323 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2021-09-01 | 2021-09-01 | 2022-06-08 | 2022-09-01 | 2022-09-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31426666 | T3 EI VOLTA-DESCHUTES 000/010 RPL POLE | 70Y
LC | 121985665 | 001/032 | T3 WV VOLTA-DESCHUTES 1/032 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2021-09-01 | 2021-09-01 | 2022-06-14 | 2022-02-28 | 2022-03-01 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31426666 | T3 EI VOLTA-DESCHUTES 000/010 RPL POLE | 70Y
LC | 121986389 | 038/005 | T2 EI RIO DLL JCT-BRDGEVLL 38/5 RPL STRW | EUREKA | ETL.7850.POLE.WOOD | 2021-09-01 | 2021-09-01 | 2022-02-18 | 2022-09-01 | 2022-09-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548073 | DI RIO DELL JCT-BRDGVLL 036/006 RPL STRW | 70Y
LC | 121986476 | 007/064 | T2 EI PARADISE-TABLE MTN 7/64 RPL HRDT | TABLEMTN | ETL.4316.TOWR | 2021-09-01 | 2021-09-01 | 2022-06-28 | 2022-09-01 | 2022-09-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45195466 | T2 EI PARADISE-TABLE MTN 7/64 RPL HRDT | ICQ
LC | 121992814 | 019/137 | T2 DI CARIBOU-TBL-MTN 19/137 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-09-02 | 2021-09-02 | 2022-06-22 | 2022-09-02 | 2022-09-02 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551234 | T2 DI CARIBOU-TBL-MTN RPL INSS 2TWRS | 93K
LC | 121999449 | 024/006 | T2 WV TULE-SPRINGVILLE 24/6 INS DAMP | MIDWAY | ETL.9040.POLE.NWOD | 2021-09-03 | 2021-09-03 | 2022-07-28 | 2022-09-03 | 2022-09-03 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Steel | Install | 45098581 | T2 WV TULE-SPRINGVILLE 24/6 INS DAMP | ICS
LC | 121999580 | 006/127 | T2 WV CRB-WSTWOD 6/127 RPR SPLW | TABLEMTN | ETL.6300.POLE.NWOD | 2021-09-03 | 2021-09-03 | 2022-08-01 | 2022-09-03 | 2022-09-03 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Splice-Wood | Repair | 45212507 | T2 WV CRB-WSTWOD 6/127 RPR SPLW | ICW
LC | 122001181 | :002/014 | T2 DI ROCK CREEK-POE :2/14 RPR SHLS | TABLEMTN | ETL.5630.TOWR | 2021-09-04 | 2021-09-02 | 2022-08-07 | 2022-09-02 | 2022-09-02 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45212491 | T2 DI ROCK CREEK-POE :2/14 RPR SHLS | ICS
LC | 122001182 | :002/014 | T2 DI ROCK CREEK-POE :2/14 RPR GYWS | TABLEMTN | ETL.5630.TOWR | 2021-09-04 | 2021-09-02 | 2022-08-07 | 2022-09-02 | 2022-09-02 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45404466 | T2 DI ROCK CREEK-POE :2/14 RPR GYWS | ICS
LC | 122006157 | 004/036 | T2 DI ROCK CREEK-POE 4/36 RPL INSS | TABLEMTN | ETL.5630.INSL | 2021-09-07 | 2021-09-03 | 2022-08-05 | 2022-09-03 | 2022-09-03 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551263 | T3 DI ROCK CREEK-POE RPL INSS 9TWRS | 93K
LC | 122007196 | 023/325 | T2 WV CLAY-MARTEL 23/325 INS DAMW | VICTOR | ETL.8250.INSL.NCER | 2021-09-07 | 2021-09-07 | 2022-07-15 | 2022-09-07 | 2022-09-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 45344341 | T2 WV CLAY-MARTEL 23/325 INS DAMW | ICW
LC | 122007347 | 003/087 | WV T2 CASCADE-BNTON-DESCHTES INS DAMW | TABLEMTN | ETL.6310.POLE.WOOD | 2021-09-07 | 2021-09-07 | 2022-10-11 | 2022-09-07 | 2022-09-07 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Damper-Wood | Install | 45508513 | WV T2 CASCADE-BNTON-DESCHTES INS DAMW | ICW
LC | 122007443 | A009/185 | WV T2 CASCDE-BNTN-DSCHTS A9/185 INS DAMW | TABLEMTN | ETL.6310.POLE.NWOD | 2021-09-07 | 2021-09-07 | 2022-09-15 | 2022-09-07 | 2022-09-07 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Damper-Steel | Install | 45436320 | WV T2 CASCDE-BNTN-DSCHTS A9/185 INS DAMW | ICS
LC | 122007612 | A009/185 | WV T2 CASCDE-BNTN-DSCHTS A9/185 RPL ANCW | TABLEMTN | ETL.6310.POLE.NWOD | 2021-09-07 | 2021-09-07 | 2022-10-10 | 2022-09-07 | 2022-09-07 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31618285 | WV T2 CASCDE-BNTN-DSCHTS A9/185 RPL ANCW | 93E
LC | 122007748 | 001/044 | T2 WV CLGTE-ALLGHNY 1/44 RPL DAMW | SACTO | ETL.6470.INSL.CERA | 2021-09-07 | 2021-09-07 | 2022-06-23 | 2022-09-07 | 2022-09-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Damper-Wood | Replace | 45078069 | T2 WV CLGTE-ALLGHNY 1/44 RPL DAMW | ICW
LC | 122007807 | 001/003 | T2 WV LAURELES-OTTER 1/3 INS DAMW | MOSSLNDG | ETL.7380.INSL.NCER | 2021-09-07 | 2021-09-07 | 2022-08-08 | 2022-09-07 | 2022-09-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE SR22 | Missing | Damper-Wood | Install | 45145237 | T2 WV LAURELES-OTTER 1/3 INS DAMW | ICW
LC | 122011832 | 000/007 | T2 DI BUCKS CREEK-ROCK 000/007 RPL INSS | TABLEMTN | ETL.4430.INSL.NCER | 2021-09-08 | 2021-09-03 | 2022-06-30 | 2022-09-03 | 2022-09-03 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31590239 | T2 DI BUCKS CREEK-ROCK 000/007 RPL INSS | 93K
LC | 122012265 | :006/046 | T2 DI ROCK CREEK-POE 6/46 RPL HRDW | TABLEMTN | ETL.5630.TOWR | 2021-09-08 | 2021-09-02 | 2022-07-26 | 2022-09-02 | 2022-09-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45159379 | T2 DI ROCK CREEK-POE 6/46 RPL HRDW | ICQ
LC | 122014634 | 003/072 | WV T2 DELTA-MTN GATE JCT 3/72 RPL POLE | TABLEMTN | ETL.6750.POLE.WDPS | 2021-09-08 | 2021-09-08 | 2022-08-27 | 2022-09-08 | 2022-09-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31431541 | T2 EI DLTA-MTN GTE JCT 005/088C RPL(ENG) | 70Y
LC | 122014781 | 003/073B | WV T2 DELTA-MTN GATE JCT 3/73B RPL STRW | TABLEMTN | ETL.6750.POLE.WOOD | 2021-09-08 | 2021-09-08 | 2022-08-27 | 2022-09-08 | 2022-09-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31431541 | T2 EI DLTA-MTN GTE JCT 005/088C RPL(ENG) | 70Y
LC | 122014834 | 003/074B | T2 WV DELTA-MTN GATE JCT 3/74B RPL POLE | TABLEMTN | ETL.6750.POLE.WOOD | 2021-09-08 | 2021-09-08 | 2022-08-27 | 2022-09-08 | 2022-09-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31431541 | T2 EI DLTA-MTN GTE JCT 005/088C RPL(ENG) | 70Y
LC | 122017569 | 003/008 | T3 WV KONOCTI-EAGLE ROCK 3/8 INST DMAPE | LAKEVLLE | ETL.6861.INSL.NCER | 2021-09-09 | 2021-09-09 | 2022-02-12 | 2022-03-08 | 2022-03-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO | Missing | Damper-Wood | Install | 45128113 | T3 WV KONOCTI-EAGLE ROCK 3/8 INST DMAPE | ICW
LC | 122017656 | 011/193 | T2 WV TEJON-LEBEC 11/193 RPL PL | MIDWAY | ETL.9250.POLE.WOOD | 2021-09-09 | 2021-09-09 | 2021-12-13 | 2022-09-09 | 2022-09-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541448 | T2 EI TEJON-LEBEC 11/193 RPL STRW | 70Y
LC | 122017740 | 010/159 | WV T3 WEIMAR #1 10/159 INS DMPW | SACTO | ETL.7560.POLE.WOOD | 2021-09-09 | 2021-09-09 | 2022-08-01 | 2022-03-08 | 2022-03-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH FMOB TR3 PRTO AIR FRAB NTDE | Missing | Damper-Wood | Install | 45210967 | WV T3 WEIMAR #1 10/159 INS DMPW | ICW
LC | 122017762 | 003/073A | WV T2 DELTA-MTN GATE JCT 3/73A RPL STRW | TABLEMTN | ETL.6750.POLE.WOOD | 2021-09-09 | 2021-09-08 | 2022-08-27 | 2022-09-08 | 2022-09-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31431541 | T2 EI DLTA-MTN GTE JCT 005/088C RPL(ENG) | 70Y
LC | 122017765 | 003/073C | WV T2 DELTA-MTN GATE JCT 3/73C RPL STRW | TABLEMTN | ETL.6750.POLE.WOOD | 2021-09-09 | 2021-09-08 | 2022-08-27 | 2022-09-08 | 2022-09-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31431541 | T2 EI DLTA-MTN GTE JCT 005/088C RPL(ENG) | 70Y
LC | 122018166 | 006/117 | T2 WV CARIBOU-WESTWD 06/117 INST GYWW | TABLEMTN | ETL.6300.POLE.WOOD | 2021-09-09 | 2021-09-09 | 2021-09-16 | 2022-09-09 | 2022-09-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Guy Wire-Wood | Install | 45070515 | T2 WV CARIBOU-WESTWD 06/117 INST GYWW | ICW
LC | 122018591 | 003/010 | T3 WV KONOCTI-EAGLE ROCK 03/010 BOND WIR | LAKEVLLE | ETL.6861.POLE.WOOD | 2021-09-09 | 2021-09-09 | 2022-02-11 | 2022-03-08 | 2022-03-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | Missing | Hardware-Wood | Install | 45128115 | T3 WV KONOCTI-EAGLE ROCK 03/010 BOND WIR | ICW
LC | 122020368 | 021/146A | T2 DI CARIBOU-TABLE MTN 21/146A RPR FOND | TABLEMTN | ETL.4440.POLE.NWOD | 2021-09-09 | 2021-09-02 | 2022-07-12 | 2022-09-02 | 2022-09-02 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45160939 | T2 DI CARIBOU-TABLE MTN 21/146A RPR FOND | ICQ
LC | 122020448 | 021/146B | T2 DI CARIBOU-TABLE MTN 21/146B RPL HRDS | TABLEMTN | ETL.4440.POLE.NWOD | 2021-09-09 | 2021-09-02 | 2022-06-23 | 2022-09-02 | 2022-09-02 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Steel | Replace | 45211348 | T2 DI CARIBOU-TABLE MTN 21/146B RPL HRDS | ICS
LC | 122020582 | 021/146C | T2 DI CARIBOU-TABLE MTN 21/146C RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2021-09-09 | 2021-09-02 | 2022-06-24 | 2022-09-02 | 2022-09-02 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45211349 | T2 DI CARIBOU-TABLE MTN 21/146C RPR GYWS | ICS
LC | 122021948 | 007/054 | T2 BUTTE VALLEY-CARIBOU 007/054 CMPLTD | TABLEMTN | ETL.1180.TOWR | 2021-09-09 | 2021-09-09 | 2022-11-01 | 2022-09-09 | 2022-09-09 | Late | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31550793 | T2 BUTTE VALLEY-CARIBOU 7/054A RPL STRW | 92F
LC | 122021951 | 007/054C | T2 BUTTE VALLEY-CARIBOU 7/054C CMPLTD | TABLEMTN | ETL.1180.POLE.WOOD | 2021-09-09 | 2021-09-09 | 2022-11-02 | 2022-09-09 | 2022-09-09 | Late | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31550793 | T2 BUTTE VALLEY-CARIBOU 7/054A RPL STRW | 92F
LC | 122021952 | 007/056 | T2 BUTTE VALLEY-CARIBOU 7/054B CMPLTD | TABLEMTN | ETL.1180.POLE.WOOD | 2021-09-09 | 2021-09-09 | 2022-11-01 | 2022-09-09 | 2022-09-09 | Late | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | Fire | Emergency | Replace | 31550793 | T2 BUTTE VALLEY-CARIBOU 7/054A RPL STRW | 92F
LC | 122035643 | 018/008 | T2 WV TRNTY-MPL CK 18/8 INST DMPRW CMPLT | EUREKA | ETL.8170.POLE.WOOD | 2021-09-10 | 2021-09-10 | 2022-04-18 | 2022-09-10 | 2022-09-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO AIR FRAB NTDE | Missing | Damper-Wood | Install | 45155861 | T2 WV TRNTY-MPLE CRK 18/8 INST DMPRW | ICW
LC | 122040877 | 001/005 | T2 MENDOCINO-UKIAH 1/5 INSL WASH | WILLITS | ETL.2420.POLE.NWOD | 2021-09-12 | 2021-09-12 | 2022-07-12 | 2022-09-12 | 2022-09-12 | On-time | 622 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | Contaminated | Insulator | Ground Wash | 45142183 | T2 MENDOCINO-UKIAH 1/5 INSL WASH | ICD
LC | 122043478 | 015/115 | T3 WV SLT SPRG-TGR CK 15/115 INS JMPRS | VICTOR | ETL.3500.TOWR | 2021-09-13 | 2021-09-13 | 2022-06-27 | 2022-03-12 | 2022-03-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31580615 | T2 DI ST SPNGS TGR CK RPL INSS 4TWRS | 93K
LC | 122043572 | 005/011 | T2 WV MAPLE CREEK-HOOPA 5/11 INS DMPRW | EUREKA | ETL.7490.INSL.NCER | 2021-09-13 | 2021-09-13 | 2022-08-19 | 2022-09-13 | 2022-09-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE SR22 | Missing | Damper-Wood | Install | 45158826 | T2 WV MAPLE CREEK-HOOPA 5/11 INS DMPRW | ICW
LC | 122044120 | 000/015 | T2 DI COLGATE-ALLEGHANY 00/15 RPR GYWW | SACTO | ETL.6470.POLE.WOOD | 2021-09-13 | 2021-09-10 | 2022-06-23 | 2022-09-10 | 2022-09-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45078071 | T2 DI COLGATE-ALLEGHANY 00/15 RPR GYWW | ICW
LC | 122053271 | :000/001 | T3 GEYSERS #9-LAKEVILLE :0/1 RPL INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122053382 | :000/003 | T3 GEYSERS #9-LAKEVILLE :0/3 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122053482 | :000/004 | T3 GEYSERS #9-LAKEVILLE :0/4 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122053552 | :001/007 | T3 GEYSERS #9-LAKEVILLE :1/7 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122053607 | :002/008 | T3 GEYSERS #9-LAKEVILLE :2/8 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122053634 | :002/010 | T3 GEYSERS #9-LAKEVILLE :2/10 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122053649 | :002/009 | T3 GEYSERS #9-LAKEVILLE :2/9 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122054003 | :002/011 | T3 GEYSERS #9-LAKEVILLE :2/11 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122054044 | :003/012 | T3 GEYSERS #9-LAKEVILLE :3/12 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122054079 | :003/013 | T3 GEYSERS #9-LAKEVILLE :3/13 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122054086 | :003/014 | T3 GEYSERS #9-LAKEVILLE :3/14 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122054304 | :003/018 | T3 GEYSERS #9-LAKEVILLE :3/18 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122054346 | :003/019 | T3 GEYSERS #9-LAKEVILLE :3/19 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122054410 | :003/020 | T3 GEYSERS #9-LAKEVILLE :3/20 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122054614 | :004/016 | T3 GEYSERS #9-LAKEVILLE :4/16 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122054700 | :005/022 | T3 GEYSERS #9-LAKEVILLE :5/22 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122054741 | :006/029 | T3 GEYSERS #9-LAKEVILLE :6/29 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122054878 | 002/010 | T3 GEYSERS #9-LAKEVILE 2/10 RPL INSS COA | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122055195 | 002/012 | T3 GEYSERS #9-LAKEVILE 2/12 RPL INSS COA | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122055241 | 003/015 | T3 GEYSERS #9-LAKEVILLE 3/15 RPL INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122055271 | 003/018 | T3 GEYSERS #9-LAKEVILLE 3/18 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122055307 | 003/019 | T3 GEYSERS #9-LAKEVILLE 3/19 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122055319 | 004/017 | T3 GEYSERS #9-LAKEVILLE 4/17 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-15 | 2021-09-15 | 2021-04-22 | 2022-03-14 | 2022-03-15 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122056966 | 004/018 | T3 GEYSERS #9-LAKEVILLE 4/18 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057066 | 004/021 | T3 GEYSERS #9-LAKEVILLE 4/21 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057101 | 004/022 | T3 GEYSERS #9-LAKEVILLE 4/22 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057113 | 005/019 | T3 GEYSERS #9-LAKEVILLE 005/019 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057131 | 005/020 | T3 GEYSERS #9-LAKEVILLE 005/020 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057153 | 005/021 | T3 GEYSERS #9-LAKEVILLE 005/021 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057254 | 006/024 | T3 GEYSERS #9-LAKEVILLE 006/024 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057418 | 006/025 | T3 GEYSERS #9-LAKEVILLE 006/025 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057558 | 006/028 | T3 GEYSERS #9-LAKEVILLE 006/028 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057566 | 007/031 | T3 GEYSERS #9-LAKEVILLE 007/031 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057609 | 007/032 | T3 GEYSERS #9-LAKEVILLE 007/032 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057634 | 008/033 | T3 GEYSERS #9-LAKEVILLE 008/033 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057662 | 008/035 | T3 GEYSERS #9-LAKEVILLE 008/035 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057693 | 008/036 | T3 GEYSERS #9-LAKEVILLE 008/036 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057698 | 009/037 | T3 GEYSERS #9-LAKEVILLE 009/037 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057729 | 009/039 | T2 GEYSERS #9-LAKEVILLE 009/039 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-09-16 | 2022-09-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057765 | 009/038 | T2 GEYSERS #9-LAKEVILLE 009/038 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-09-16 | 2022-09-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057819 | 010/043 | T2 GEYSERS #9-LAKEVILLE 010/043 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-09-16 | 2022-09-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057820 | 009/040 | T2 GEYSERS #9-LAKEVILLE 009/040 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-09-16 | 2022-09-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057827 | 010/042 | T2 GEYSERS #9-LAKEVILLE 010/042 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-09-16 | 2022-09-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057832 | 009/041 | T2 GEYSERS #9-LAKEVILLE 009/041 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-09-16 | 2022-09-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057865 | 011/047 | T3 GEYSERS #9-LAKEVILLE 011/047 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057892 | 010/044 | T2 GEYSERS #9-LAKEVILLE 010/044 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-09-16 | 2022-09-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057897 | 011/045 | T3 GEYSERS #9-LAKEVILLE 011/045 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057906 | 011/046 | T3 GEYSERS #9-LAKEVILLE 011/046 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057944 | 011/048 | T3 GEYSERS #9-LAKEVILLE 011/048 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122057963 | 011/049 | T3 GEYSERS #9-LAKEVILLE 011/049 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058082 | 012/050 | T3 GEYSERS #9-LAKEVILLE 012/050 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058093 | 012/051 | T3 GEYSERS #9-LAKEVILLE 012/051 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058123 | 013/053 | T3 GEYSERS #9-LAKEVILLE 013/053 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058128 | 013/054 | T3 GEYSERS #9-LAKEVILLE 013/054 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058153 | 013/055 | T3 GEYSERS #9-LAKEVILLE 013/055 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058171 | 013/056 | T3 GEYSERS #9-LAKEVILLE 013/056 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058175 | 013/057 | T3 GEYSERS #9-LAKEVILLE 013/057 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058201 | 013/058 | T3 GEYSERS #9-LAKEVILLE 013/058 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058209 | 013/059 | T3 GEYSERS #9-LAKEVILLE 013/059 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058265 | 015/063 | T3 GEYSERS #9-LAKEVILLE 015/063 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058280 | 014/060 | T3 GEYSERS #9-LAKEVILLE 014/060 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058285 | 014/061 | T3 GEYSERS #9-LAKEVILLE 014/061 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058322 | 014/062 | T3 GEYSERS #9-LAKEVILLE 014/062 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058346 | 015/064 | T3 GEYSERS #9-LAKEVILLE 015/064 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058372 | 015/065 | T3 GEYSERS #9-LAKEVILLE 015/065 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058396 | 016/067 | T3 GEYSERS #9-LAKEVILLE 016/067 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058471 | 016/068 | T3 GEYSERS #9-LAKEVILLE 16/68 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058581 | 016/069 | T3 GEYSERS #9-LAKEVILLE 16/69 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058585 | 016/070 | T3 GEYSERS #9-LAKEVILLE 16/70 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058613 | 017/074 | T3 GEYSERS #9-LAKEVILLE 17/74 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122058621 | 017/071 | T3 GEYSERS #9-LAKEVILLE 17/71 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059137 | 018/075 | T3 GEYSERS #9-LAKEVILLE 18/75 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059232 | 018/076 | T3 GEYSERS #9-LAKEVILLE 18/76 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059234 | 018/077 | T3 GEYSERS #9-LAKEVILLE 18/77 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059261 | 018/078 | T3 GEYSERS #9-LAKEVILLE 18/78 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059263 | 018/079 | T3 GEYSERS #9-LAKEVILLE 18/79 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059275 | 019/080 | T3 GEYSERS #9-LAKEVILLE 19/80 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059352 | 019/081 | T3 GEYSERS #9-LAKEVILLE 19/81 COMPLETE | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059383 | 019/082 | T3 GEYSERS #9-LAKEVILLE 19/82 PRL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059420 | 019/083 | T3 GEYSERS #9-LAKEVILLE 19/83 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059424 | 020/084 | T3 GEYSERS #9-LAKEVILLE 20/84 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059465 | 020/085 | T3 GEYSERS #9-LAKEVILLE 20/85 RPL INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059589 | 020/086 | T3 GEYSERS #9-LAKEVILLE 20/86 RPL INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059639 | 020/087 | T3 GEYSERS #9-LAKEVILLE 20/87 RPL INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059680 | 025/111 | T3 GEYSERS #9-LAKEVILLE 25/111 RPL INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059686 | 026/114 | T3 GEYSERS #9-LAKEVILLE 26/114 RPL INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059701 | 025/112 | T3 GEYSERS #9-LAKEVILLE 25/112 RPL INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059757 | 026/113 | T3 GEYSERS #9-LAKEVILLE 26/113 RPL INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059779 | 026/115 | T3 GEYSERS #9-LAKEVILLE 26/115 RPL INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059816 | 026/117 | T3 GEYSERS #9-LAKEVILLE 26/117 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122059829 | 004/034 | T2 EI TRINITY-COTTNWD 4/034L RPL POLE | TABLEMTN | ETL.4040.POLE.WDPS | 2021-09-16 | 2021-03-22 | 2022-08-08 | 2022-03-22 | 2022-03-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31577970 | T2 TRINITY-COTTNWD 4/31R RPL STRW | 70Y
LC | 122059964 | 027/118 | T3 GEYSERS #9-LAKEVILLE 27/118 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122060017 | 028/124 | T3 GEYSERS #9-LAKEVILLE 28/124 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122060025 | 028/125 | T3 GEYSERS #9-LAKEVILLE 28/125 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122060110 | 028/126 | T3 GEYSERS #9-LAKEVILLE 28/126 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122060115 | 028/127 | T3 GEYSERS #9-LAKEVILLE 28/127 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122060141 | 029/128 | T3 GEYSERS #9-LAKEVILLE 29/128 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122060182 | 029/129 | T2 GEYSERS #9-LAKEVILLE 29/129 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-09-16 | 2022-09-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122060186 | 030/130 | T3 GEYSERS #9-LAKEVILLE 30/130 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122060422 | 030/131 | T3 GEYSERS #9-LAKEVILLE 30/131 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122060423 | 031/132 | T3 GEYSERS #9-LAKEVILLE 31/132 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-16 | 2021-09-16 | 2021-04-22 | 2022-03-15 | 2022-03-16 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122063787 | 031/134 | T3 GEYSERS #9-LAKEVILLE 031/134 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122063841 | 031/133 | T3 GEYSERS #9-LAKEVILLE 031/133 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122063937 | 031/135 | T3 GEYSERS #9-LAKEVILLE 031/135 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122063956 | 032/137 | T3 GEYSERS #9-LAKEVILLE 032/137 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122064008 | 032/138 | T3 GEYSERS #9-LAKEVILLE 032/138 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122064459 | 032/139 | T3 GEYSERS #9-LAKEVILLE 032/139 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122064551 | 032/140 | T3 GEYSERS #9-LAKEVILLE 032/140 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122064630 | 032/141 | T3 GEYSERS #9-LAKEVILLE 032/141 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122064637 | 033/142 | T3 GEYSERS #9-LAKEVILLE 033/142 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122064702 | 033/143 | T3 GEYSERS #9-LAKEVILLE 033/143 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122064708 | 033/144 | T3 GEYSERS #9-LAKEVILLE 033/144 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122064806 | 033/145 | T3 GEYSERS #9-LAKEVILLE 033/145 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122064936 | 034/147 | T3 GEYSERS #9-LAKEVILLE 034/147 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065030 | 034/148 | T3 GEYSERS #9-LAKEVILLE 034/148 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065142 | 034/149 | T3 GEYSERS #9-LAKEVILLE 034/149 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065168 | 035/150 | T3 GEYSERS #9-LAKEVILLE 035/150 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065207 | 035/152 | T3 GEYSERS #9-LAKEVILLE 035/152 RPL INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065212 | 035/151 | T3 GEYSERS #9-LAKEVILLE 035/151 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-03-16 | 2022-03-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065238 | 035/154 | T2 GEYSERS #9-LAKEVILLE 35/154 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065260 | 035/153 | T2 GEYSERS #9-LAKEVILLE 035/153 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065501 | 036/157 | T2 GEYSERS #9-LAKEVILLE 36/157 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065504 | 036/158 | T2 GEYSERS #9-LAKEVILLE 36/158 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065513 | 036/159 | T2 GEYSERS #9-LAKEVILLE 36/159 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065604 | 037/160 | T2 GEYSERS #9-LAKEVILLE 37/160 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065642 | 037/161 | T2 GEYSERS #9-LAKEVILLE 37/161 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-10-12 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065668 | 037/162 | T2 GEYSERS #9-LAKEVILLE 37/162 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065732 | 037/163 | T2 GEYSERS #9-LAKEVILLE 37/163 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065834 | 038/167 | T2 GEYSERS #9-LAKEVILLE 38/167 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065840 | 038/166 | T2 GEYSERS #9-LAKEVILLE 38/166 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065865 | 039/168 | T2 GEYSERS #9-LAKEVILLE 39/168 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065925 | 039/170 | T2 GEYSERS #9-LAKEVILLE 39/170 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-10-12 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065947 | 039/171 | T2 GEYSERS #9-LAKEVILLE 39/171 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065957 | 039/172 | T2 GEYSERS #9-LAKEVILLE 39/172 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122065977 | 040/173 | T2 GEYSERS #9-LAKEVILLE 40/173 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-10-12 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122066011 | 040/174 | T2 GEYSERS #9-LAKEVILLE 40/174 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-10-12 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122066015 | 040/175 | T2 GEYSERS #9-LAKEVILLE 40/175 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122066035 | 040/176 | T2 GEYSERS #9-LAKEVILLE 40/176 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122066092 | 041/177 | T2 GEYSERS #9-LAKEVILLE 41/177 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 | 2021-04-22 | 2022-09-17 | 2022-09-17 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122073420 | 037/151 | T2 DIABLO-MIDWAY #3 37/151 RPR INSS | PISMOBCH | ETL.5980.INSL.NCER | 2021-09-20 | 2021-09-20 | 2022-01-10 | 2022-09-20 | 2022-09-20 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45262431 | T2 DIABLO-MIDWAY #3 37/151 RPR INSS | ICS
LC | 122074510 | 045/351 | T2 EI BRIDGVIL-COTTONWD 45/351 INS HRDS | EUREKA | ETL.1110.POLE.STPS | 2021-09-20 | 2021-09-20 | 2022-10-04 | 2022-09-20 | 2022-09-20 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | Missing | Hardware-Steel | Install | 45158751 | T2 EI BRIDGEVILLE-CTTNWD 45/351 INS HRDS | ICS
LC | 122078189 | 024/005 | T2 TULE-SPRINGVILLE 24/005 INS DAMW | MIDWAY | ETL.9040.POLE.NWOD | 2021-09-21 | 2021-09-21 | 2022-07-28 | 2022-09-21 | 2022-09-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Steel | Install | 45098580 | T2 TULE-SPRINGVILLE 24/005 INS DAMW | ICS
LC | 122079183 | A001/027 | T2 WV VALLEY SPRINGS #1 A1/27 INS DAMW | VICTOR | ETL.8210.POLE.NWOD | 2021-09-21 | 2021-09-21 | 2022-04-03 | 2022-09-21 | 2022-09-21 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Damper-Steel | Replace | 45151087 | T2 WV VALLEY SPRINGS #1 A1/27 INS DAMW | ICS
LC | 122079297 | 018/588 | T2 WV SPAULDING-SUMMIT 18/588INS DAMW | SACTO | ETL.8060.INSL.NCER | 2021-09-21 | 2021-09-21 | 2022-08-05 | 2022-09-21 | 2022-09-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Wood | Install | 45219521 | T2 WV SPAULDING-SUMMIT 18/588INS DAMW | ICW
LC | 122080418 | 002/014 | T2 DIVIDE-VANDENBERG #2 2/014 RPR INSW | PISMOBCH | ETL.8630.INSL.CERA | 2021-09-21 | 2021-09-21 | 2022-04-23 | 2022-09-21 | 2022-09-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair | 45098800 | T2 DIVIDE-VANDENBERG #2 2/014 RPR INSW | ICW
LC | 122088275 | X001/007 | T3 WV MORRO BAY-DIABLO X001/007 RPR OPGW | PISMOBCH | ETL.5260.INSL.CERA | 2021-09-23 | 2021-09-23 | 2022-05-24 | 2022-03-22 | 2022-03-23 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45098842 | T3 WV MORRO BAY-DIABLO X001/007 RPR OPGW | ICS
LC | 122088530 | 010/269 | T3 WV COLGATE-ALLEGHANY 10/269 INS DAMP | SACTO | ETL.6470.POLE.WOOD | 2021-09-23 | 2021-09-23 | 2022-06-18 | 2022-03-22 | 2022-03-23 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB NTDE | Missing | Damper-Wood | Install | 45078072 | T3 WV COLGATE-ALLEGHANY 10/269 INS DAMP | ICW
LC | 122088660 | 000/018 | T2 WV WEIMAR #1 0/18 COMPLETE | SACTO | ETL.7560.POLE.NWOD | 2021-09-23 | 2021-09-23 | 2022-08-28 | 2022-09-23 | 2022-09-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB SR22 | Missing | Damper-Wood | Install | 45210968 | T2 WV WEIMAR #1 0/18 INS DAMP | ICW
LC | 122088832 | 010/078A | T2 WV TRINITY-COTTONWD 10/78A COMPLETE | TABLEMTN | ETL.4040.POLE.WOOD | 2021-09-23 | 2021-09-23 | 2022-08-08 | 2022-09-23 | 2022-09-23 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO FRAB SR22 | Rotten | Structure-Wood | Replace | 31545105 | T2 EI TRNTY-CTNWD 10/078B RPL POLE | 70Y
LC | 122095685 | 003/017 | T3 GEYSERS#9-LAKEVILLE 3/17 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-24 | 2021-09-24 | 2021-04-22 | 2022-03-23 | 2022-03-24 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace
LC | 122095813 | 038/165 | T2 GEYSERS#9-LAKEVILLE 38/165 RPL INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-24 | 2021-09-24 | 2021-04-22 | 2022-09-24 | 2022-09-24 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace
LC | 122096087 | 039/169 | T3 GEYSERS #9-LAKEVILLE 39/169 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-24 | 2021-09-24 | 2021-04-22 | 2022-03-23 | 2022-03-24 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO | Fire | Emergency | Replace
LC | 122096124 | 041/178 | T2 GEYSERS #9-LAKEVILLE 41/178 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-24 | 2021-09-24 | 2021-04-22 | 2022-09-24 | 2022-09-24 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace
LC | 122096204 | 041/179 | T2 GEYSERS #9-LAKEVILLE 41/179 RPL INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-24 | 2021-09-24 | 2021-04-22 | 2022-09-24 | 2022-09-24 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace
LC | 122096418 | 034/146 | T2 GEYSERS #9-LAKEVILLE 034/146 RPL INSS | LAKEVLLE | ETL.4780.INSL | 2021-09-24 | 2021-09-24 | 2021-04-22 | 2022-09-24 | 2022-09-24 | On-time | 437 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace
LC | 122098868 | 004/009 | T2 WV POTTER VALLEY-WILLITS 4/9 INS DAMW | WILLITS | ETL.7820.POLE.WOOD | 2021-09-24 | 2021-09-24 | 2022-08-10 | 2022-09-24 | 2022-09-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Damper-Wood | Install | 45137014 | T2 WV POTTER VALLEY-WILLITS 4/9 INS DAMW | ICW
LC | 122103924 | ;001/014 | T2 WV CARIBOU #2 ;001/014 INS DAMW | TABLEMTN | ETL.6280.POLE.STPS | 2021-09-27 | 2021-09-27 | 2022-07-15 | 2022-09-27 | 2022-09-27 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Steel | Install | 45214070 | T2 WV CARIBOU #2 ;001/014 INS DAMW | ICS
LC | 122104028 | 014/148 | T2 WV IGNACIO-BOLINAS #1 14/148 RPR STRW | LAKEVLLE | ETL.7140.POLE.WOOD | 2021-09-27 | 2021-09-27 | 2022-06-20 | 2022-09-27 | 2022-09-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45128039 | T2 WV IGNACIO-BOLINAS #1 14/148 RPR STRW | ICW
LC | 122104068 | 014/148 | T2 WV IGNACIO-BOLINAS #1 14/148 INS DAMW | LAKEVLLE | ETL.7140.POLE.WOOD | 2021-09-27 | 2021-09-27 | 2022-06-20 | 2022-09-27 | 2022-09-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Damper-Wood | Replace | 45352788 | T2 WV IGNACIO-BOLINAS #1 14/148 INS DAMW | ICW
LC | 122104360 | 003/029 | T2 SOBRANTE G #2 3/29 RPL INSS | CONCORD | ETL.3730.INSL.CERA | 2021-09-27 | 2021-09-27 | 2022-07-07 | 2022-09-27 | 2022-09-27 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31597693 | T2 SOBRANTE G #2 RPL INSS IN 2 TSPS. | 93K
LC | 122104805 | 002/024 | T2 WV SBRNT-GRZLY-CLRMT #1 2/24 INS DAMS | CONCORD | ETL.3740.POLE.NWOD | 2021-09-27 | 2021-09-27 | 2022-06-10 | 2022-09-27 | 2022-09-27 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Damper-Steel | Install | 45168058 | T2 WV SBRNT-GRZLY-CLRMT #1 2/24 INS DAMS | ICS
LC | 122104899 | 024/007 | T2 WV TULE-SPRINGVILLE 24/007 INS DAMW | MIDWAY | ETL.9040.POLE.NWOD | 2021-09-27 | 2021-09-27 | 2022-07-28 | 2022-09-27 | 2022-09-27 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Steel | Install | 45098582 | T2 WV TULE-SPRINGVILLE 24/007 INS DAMW | ICS
LC | 122105242 | ;000/033 | T2 WV CARIBOU #2 ;000/033 INS GYWW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-09-27 | 2021-09-27 | 2022-07-15 | 2022-09-27 | 2022-09-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Guy Wire-Wood | Install | 45214068 | T2 WV CARIBOU #2 ;000/033 INS GYWW | ICW
LC | 122106217 | 010/049 | T2 BRENTWOOD-KELSO 010/049 RPL INSS | CONCORD | ETL.4410.INSL | 2021-09-27 | 2021-09-27 | 2021-11-12 | 2022-09-27 | 2022-09-27 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31554666 | T2 BRENTWOOD-KELSO RPL INSS 3TWRS | 93K
LC | 122117489 | 000/025 | T3 EI SANDBAR TAP 0/025 RPR ROAD | VICTOR | ETL.1403.POLE.STPS | 2021-09-29 | 2021-09-29 | 2021-11-19 | 2022-03-28 | 2022-03-29 | On-time | 932 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Road | Repair | 31521953 | 2021 SACRAMENTO GATES | 71Y
LC | 122120713 | 006/129 | T2 DI VALLEY SPRINGS #2 6/129 RPL INSW | VICTOR | ETL.9460.INSL.CERA | 2021-09-29 | 2021-09-24 | 2022-07-08 | 2022-09-24 | 2022-09-24 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP OTHR COMP OH TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579996 | T2 DI VALLEY SPRINGS #2 6/129 RPL INSW | 93I
LC | 122121177 | 002/043C | T3 WV MDDLE FRK #1 02/043C RPR STRW | SACTO | ETL.8405.POLE.WOOD | 2021-09-29 | 2021-09-29 | 2022-08-04 | 2022-03-28 | 2022-03-29 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45017201 | T3 WV MDDLE FRK #1 02/043C RPR STRW | ICW
LC | 122122812 | 023/611 | T2 WV CARIBOU #2 23/611 INS DMPW | TABLEMTN | ETL.6280.POLE.NWOD | 2021-09-29 | 2021-09-29 | 2022-07-14 | 2022-09-29 | 2022-09-29 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Steel | Install | 45214067 | T2 WV CARIBOU #2 23/611 INS DMPW | ICS
LC | 122125579 | 023/367 | T2 EI KSWCK-TRNITY 023/367 INS DMPW | TABLEMTN | ETL.7270.INSL.NCER | 2021-09-30 | 2021-09-30 | 2022-05-31 | 2022-09-30 | 2022-09-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 45212485 | T2 EI KSWCK-TRNITY 023/367 INS DMPW | ICW
LC | 122133312 | 009/060 | T3 WV OLEUM-G #2 9/060 RPR JUMS | CONCORD | ETL.3160.INSL.NCER | 2021-10-01 | 2021-10-01 | 2022-05-13 | 2022-03-30 | 2022-04-01 | Late | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Jumper-Steel | Repair | 45107134 | T3 WV OLEUM-G #2 9/060 RPR JUMS | ICS
LC | 122134446 | 008/004 | T2 DI MELONES-RACETRACK 8/4 RPL STRW | VICTOR | ETL.2400.POLE.WOOD | 2021-10-01 | 2021-10-01 | 2022-04-27 | 2022-10-01 | 2022-10-01 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31555313 | T2 DI MELONES-RACETRACK 8/4 RPL STRW | 70Y
LC | 122136723 | ;003/003 | T2 WV CARIBOU #2 ;003/003 INS DAMW | TABLEMTN | ETL.6280.POLE.NWOD | 2021-10-01 | 2021-10-01 | 2022-07-15 | 2022-10-01 | 2022-10-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Steel | Install | 45262063 | T2 WV CARIBOU #2 ;003/003 INS DAMW | ICS
LC | 122145437 | ;004/003 | T2 WV CARIBOU #2 ;4/3 REFRAME | TABLEMTN | ETL.6280.POLE.WOOD | 2021-10-04 | 2021-10-04 | 2022-07-15 | 2022-10-04 | 2022-10-04 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 31508413 | T2 DI CARIBOU #2 ;004/3 RPLC INSW | 93I
LC | 122148896 | 005/078 | T2 WV PARDEE #1 TAP 5/78 INST DMPR | VICTOR | ETL.8231.INSL.NCER | 2021-10-05 | 2021-10-05 | 2022-04-21 | 2022-10-05 | 2022-10-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 45135202 | T2 WV VALLEY SPRINGS-CLAY 5/78 INST DMPR | ICW
LC | 122154841 | 008/074 | T2 CRESTA-RIO OSO 8/074 INS DAMS | TABLEMTN | ETL.4590.TOWR | 2021-10-06 | 2021-10-06 | 2022-05-04 | 2022-10-06 | 2022-10-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Steel | Install | 45212494 | T2 CRESTA-RIO OSO 8/074 INS DAMS | ICS
LC | 122154913 | 008/073 | T2 CRESTA-RIO OSO 8/073 INS DAMS | TABLEMTN | ETL.4590.INSL | 2021-10-06 | 2021-10-06 | 2022-05-04 | 2022-10-06 | 2022-10-06 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Steel | Install | 45212495 | T2 CRESTA-RIO OSO 8/073 INS DAMS | ICS
LC | 122157248 | 022/603 | T2 CARIBOU #2 22/603 INS GYWW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-10-06 | 2021-10-06 | 2022-07-14 | 2022-10-06 | 2022-10-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Guy Wire-Wood | Install | 45214065 | T2 CARIBOU #2 22/603 INS GYWW | ICW
LC | 122161529 | 034/172 | T3 EAGLE RK-FTN-SLVR 34/172 RPL INSS COA | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 | 2022-11-02 | 2022-04-05 | 2022-04-07 | Late | 505 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122161616 | 034/173 | T3 EAGLE RK-FTN-SLVR 34/173 RPL INSS COA | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 | 2022-11-02 | 2022-04-05 | 2022-04-07 | Late | 505 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122161897 | 036/185 | T3 EGLE RCK-FLTN-SVR 36/185 COMPLETED | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 | 2021-01-14 | 2022-04-05 | 2022-04-07 | On-time | 505 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122162126 | 000/002 | T2 DI LYTNVLE CVLO 0/2 RPL STRW | WILLITS | ETL.7390.POLE.WOOD | 2021-10-07 | 2021-10-07 | 2022-06-02 | 2022-10-07 | 2022-10-07 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544833 | T2 DI LAYTONVILLE-COVELO 5/2L RPL STRW | 70Y
LC | 122162225 | 039/198 | T3 EAGLE RCK-FTN-SLR 39/198 COMPLETED | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 | 2021-01-13 | 2022-04-05 | 2022-04-07 | On-time | 505 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122162670 | 039/201 | T3 EAGLE ROCK-FLTN-SILVR 39/201 COMPLETE | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 | 2021-01-14 | 2022-04-05 | 2022-04-07 | On-time | 505 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122162710 | 039/202 | T3 EAGLE ROCK-FLTN-SILVR 39/202 COMPLETE | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 | 2021-01-14 | 2022-04-05 | 2022-04-07 | On-time | 505 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122162746 | 040/204 | T3 EAGLE ROCK-FLTN-SILVR 40/204 COMPLETE | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 | 2021-01-14 | 2022-04-05 | 2022-04-07 | On-time | 505 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122163027 | 041/210 | T3 EAGLE ROCK-FLTN-SILVR 41/210 COMPLETE | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 | 2021-01-14 | 2022-04-05 | 2022-04-07 | On-time | 505 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122163105 | 041/211 | T3 EAGLE ROCK-FLTN-SILVR 41/211 COMPLETE | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 | 2021-01-14 | 2022-04-05 | 2022-04-07 | On-time | 505 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122164335 | 024/653 | T3 DI CLGT-ALLGHNY 024/653 RPL INSW | SACTO | ETL.6470.INSL.NCER | 2021-10-07 | 2021-10-07 | 2022-06-15 | 2022-04-05 | 2022-04-07 | Late | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31554487 | T3 DI CLGT-ALLGHNY 024/653 RPL INSW | 93I
LC | 122168885 | 011/115 | PTR T2 ARCO-CHOLAME 11/115 RMV NEST | MIDWAY | ETL.8440.POLE.NWOD | 2021-10-08 | 2021-10-08 | 2022-01-21 | 2022-10-08 | 2022-10-08 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45097659 | PTR T2 ARCO-CHOLAME 11/115 RMV NEST | ICW
LC | 122185121 | 021/155 | T3 WV TRINITY-COTTONWOOD 21/155 INS DAMW | TABLEMTN | ETL.4040.INSL.CERA | 2021-10-11 | 2021-10-11 | 2022-08-22 | 2022-04-09 | 2022-04-11 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO | Missing | Damper-Wood | Install | 45212102 | T3 WV TRINITY-COTTONWOOD 21/155 INS DAMW | ICW
LC | 122186517 | 026/314A | T2 WV DRUM-SUMMIT #2 26/314A INS DAMW | SACTO | ETL.1450.INSL.NCER | 2021-10-11 | 2021-10-11 | 2022-08-11 | 2022-10-11 | 2022-10-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Wood | Install | 45218215 | T2 WV DRUM-SUMMIT #2 26/314A INS DAMW | ICW
LC | 122186578 | 026/314C | T2 WV DRUM-SUMMIT #2 26/314C INS DAMW | SACTO | ETL.1450.INSL.NCER | 2021-10-11 | 2021-10-11 | 2022-08-11 | 2022-10-11 | 2022-10-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Wood | Install | 45218216 | T2 WV DRUM-SUMMIT #2 26/314C INS DAMW | ICW
LC | 122186581 | 026/314B | T2 WV DRUM-SUMMIT #2 26/314B INS DAMW | SACTO | ETL.1450.INSL.NCER | 2021-10-11 | 2021-10-11 | 2022-08-11 | 2022-10-11 | 2022-10-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Wood | Install | 45218217 | T2 WV DRUM-SUMMIT #2 26/314B INS DAMW | ICW
LC | 122190818 | 003/047 | T3 IGNACIO-BOLINAS #2 3/47 RPR ROAD | LAKEVLLE | ETL.7180.POLE.NWOD | 2021-10-12 | 2021-08-18 | 2022-02-15 | 2022-02-14 | 2022-02-18 | Late | 932 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Road | Repair | 45022030 | T3 IGNACIO-BOLINAS #2 3/47 RPR ROAD | CHS
LC | 122190819 | 000/005 | EI T3 GEYSERS #3-CLOVERDALE 0/5 RMV DBRS | LAKEVLLE | ETL.1650.POLE.WOOD | 2021-10-12 | 2021-09-01 | 2022-02-02 | 2022-02-28 | 2022-03-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45133546 | EI T3 GEYSERS #3-CLOVERDALE 0/5 RMV DBRS | ICW
LC | 122191829 | 011/009C | T3 EI MAPLE CREEK-HOOPA 11/9C RMV STEP | EUREKA | ETL.7490.POLE.NWOD | 2021-10-12 | 2021-10-12 | 2022-06-24 | 2022-04-10 | 2022-04-12 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH FMOB TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45079411 | T3 EI MAPLE CREEK-HOOPA 11/9C RMV STEP | ICW
LC | 122192045 | 000/011 | T3 EI KONOCTI-EAGLE ROCK 0/011 RMV STEP | LAKEVLLE | ETL.6861.POLE.NWOD | 2021-10-12 | 2021-10-12 | 2022-01-04 | 2022-04-10 | 2022-04-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45161280 | T3 EI KONOCTI-EAGLE ROCK 0/011 RMV STEP | ICW
LC | 122196781 | 014/007B | T2 CARIBOU-PLUMAS 14/7B RPL STRW | TABLEMTN | ETL.6290.POLE.WOOD | 2021-10-13 | 2021-10-02 | 2022-10-29 | 2022-10-02 | 2022-10-02 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31541655 | T2 CARIBOU-PLUMAS JCT-WOOD 6/18 RPL POLE | 70Y
LC | 122198964 | 015/109A | T2 DI HELMS GRG #1 15/109A RPL INSLS | FRESNO | ETL.4870.INSL | 2021-10-13 | 2021-10-13 | 2022-08-22 | 2022-10-13 | 2022-10-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551822 | DI HELMS-GREGG #1 RPL INSS 12 TWRS | 93K
LC | 122208822 | 034/012 | T2 WV FULTON-HOPLAND 34/12 INS DAMS | LAKEVLLE | ETL.6890.INSL.NCER | 2021-10-14 | 2021-10-14 | 2022-05-17 | 2022-10-14 | 2022-10-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Steel | Install | 45143980 | T2 WV FULTON-HOPLAND 34/12 INS DAMS | ICS
LC | 122209222 | 005/052 | T2 HILLSDALE JCT-HMB 5/52 RPR INSW | METCALF | ETL.7060.INSL.CERA | 2021-10-14 | 2021-10-01 | 2022-04-29 | 2022-10-01 | 2022-10-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 45015023 | T2 HILLSDALE JCT-HMB 5/52 RPR INSW | ICW
LC | 122209234 | 011/048 | T3 MORAGA-CASTRO VALLEY 11/48 RPL INSS | CONCORD | ETL.5250.INSL | 2021-10-14 | 2021-10-13 | 2022-03-31 | 2022-04-11 | 2022-10-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31591453 | T3 MORAGA-CASTRO VALLEY 11/48 RPL INSS | 93K
LC | 122209966 | 020/003 | T2 DI MNDCN-WLLTS-FRT BRGG 20/3 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2021-10-14 | 2021-10-13 | 2022-08-26 | 2022-10-13 | 2022-10-13 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31551283 | T2 DI MNDCN-WLTS-FRT BRG 28/10 RPL INSW | 93I
LC | 122213357 | 028/000 | T2 DI MENDO-WLLTS-FT BRGG 28/00 RPR WDPK | WILLITS | ETL.7550.POLE.WOOD | 2021-10-15 | 2021-10-14 | 2022-08-17 | 2022-10-14 | 2022-10-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45148574 | T2 DI MENDO-WLLTS-FT BRGG 28/00 RPR WDPK | ICW
LC | 122216321 | 011/050 | T3 SAN RMN-MORAGA 11/50 RPL INSS | CONCORD | ETL.5660.INSL | 2021-10-16 | 2021-10-13 | 2022-06-21 | 2022-04-11 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR COMP OH FMOB TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31588466 | T3 DI SAN RAMON-MORAGA RPLC INSS 3TWRS | 93K
LC | 122221261 | 002/043 | WV T3 CNTRVL-TBL MTN-ORVL 2/43 INS DAMW | TABLEMTN | ETL.6330.POLE.NWOD | 2021-10-18 | 2021-10-18 | 2022-04-04 | 2022-04-16 | 2022-04-18 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | Missing | Damper-Steel | Install | 45212509 | WV T3 CNTRVL-TBL MTN-ORVL 2/43 INS DAMW | ICS
LC | 122221375 | 000/009 | WV T2 CHRISTIE-WILLOW PASS 0/9 INS DAMW | CONCORD | ETL.6370.POLE.WOOD | 2021-10-18 | 2021-10-18 | 2022-02-12 | 2022-10-18 | 2022-10-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Wood | Install | 45179568 | WV T2 CHRISTIE-WILLOW PASS 0/9 INS DAMW | ICW
LC | 122222668 | 030/007 | T2 WV FULTON-HOPLAND 30/7 RPL SPLW | LAKEVLLE | ETL.6890.INSL.NCER | 2021-10-18 | 2021-10-18 | 2022-06-23 | 2022-10-18 | 2022-10-18 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Replace | 45143964 | T2 WV FULTON-HOPLAND 30/7 RPL SPLW | ICS
LC | 122226236 | 002/004 | T2 EI MELONES-CURTIS_002/004L RPL HRDD | VICTOR | ETL.2390.POLE.WDPS | 2021-10-19 | 2021-10-16 | 2022-12-02 | 2022-10-16 | 2022-10-16 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45167634 | T2 EI MELONES-CURTIS_002/004L RPL HRDD | ICW
LC | 122228070 | 003/018 | T3 SAN RAMON-MORAGA 3/018 RPR STRT | CONCORD | ETL.5660.TOWR | 2021-10-19 | 2021-10-19 | 2022-06-30 | 2022-04-17 | 2022-04-19 | Late | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW CREW COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45190907 | T3 SAN RAMON-MORAGA 3/018 RPR STRT | ICQ
LC | 122230107 | 017/005 | T2 DI MENDOCNO-WILLTS-FB 17/5 RPL IBWW | WILLITS | ETL.7550.POLE.WOOD | 2021-10-19 | 2021-10-07 | 2022-05-23 | 2022-10-07 | 2022-10-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Replace | 45145810 | T2 DI MENDOCNO-WILLTS-FB 17/5 RPL IBWW | ICW
LC | 122232018 | 015/111A | T2 DI HELMS-GREGG #1 15/111A RPL INSS | FRESNO | ETL.4870.INSL | 2021-10-20 | 2021-10-13 | 2022-08-21 | 2022-10-13 | 2022-10-13 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551822 | DI HELMS-GREGG #1 RPL INSS 12 TWRS | 93K
LC | 122232357 | 063/454 | T2 BRIDGEVILLE-COTTONWD 63/454 RPL DAMP | EUREKA | ETL.1110.INSL.CERA | 2021-10-20 | 2021-10-20 | 2022-10-05 | 2022-10-20 | 2022-10-20 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Damper-Steel | Replace | 45158753 | T2 BRIDGEVILLE-COTTONWD 63/454 RPL DAMP | ICS
LC | 122232869 | 064/463 | T2 BRIDGEVILLE-COTTONWD 64/463 INS DAMP | EUREKA | ETL.1110.TOWR | 2021-10-20 | 2021-10-20 | 2022-09-28 | 2022-10-20 | 2022-10-20 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB SR22 | Missing | Damper-Steel | Install | 45158755 | T2 BRIDGEVILLE-COTTON 64/463 INS DAMP | ICS
LC | 122232937 | 064/464 | T2 BRIDGEVILLE-COTTONWD 64/464 INS DAMP | EUREKA | ETL.1110.TOWR | 2021-10-20 | 2021-10-20 | 2022-09-28 | 2022-10-20 | 2022-10-20 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB SR22 | Missing | Damper-Steel | Install | 45158756 | T2 BRIDGEVILLE-COTTON 64/464 INS DAMP | ICS
LC | 122233132 | 082/576 | T2 BRIDGEVILLE-COTTONWD 82/576 RPL ANCW | EUREKA | ETL.1110.POLE.STPS | 2021-10-20 | 2021-10-20 | 2022-09-28 | 2022-10-20 | 2022-10-20 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31578024 | T2 BRIDGEVILLE-COTTON 82/576 RPL ANCW | 93E
LC | 122233191 | 082/581 | T2 BRIDGEVILLE-COTTON 82/581 INS DAMP | EUREKA | ETL.1110.TOWR | 2021-10-20 | 2021-10-20 | 2022-05-18 | 2022-10-20 | 2022-10-20 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Steel | Install | 45158758 | T2 BRIDGEVILLE-COTTON 82/581 INS DAMP | ICS
LC | 122233244 | 083/583 | T2 BRIDGEVILLE-COTTON 83/583 RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2021-10-20 | 2021-10-20 | 2022-05-17 | 2022-10-20 | 2022-10-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45158759 | T2 BRIDGEVILLE-COTTON 83/583 RPR GYWW | ICW
LC | 122233485 | 011/047 | T3 EI MORAGA-CASTRO VLY 11/47 RPR INSS | CONCORD | ETL.5250.INSL | 2021-10-20 | 2021-10-20 | 2022-04-01 | 2022-04-18 | 2022-04-20 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45144678 | T3 EI MORAGA-CASTRO VLY 11/47 RPR INSS | ICS
LC | 122234606 | 009/094A | T3 DI DRUM-RIO OSO #2 9/94A RPL INSS | SACTO | ETL.1430.POLE.STPS | 2021-10-20 | 2021-10-13 | 2022-08-02 | 2022-04-11 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31557440 | T3 DI DRUM-RIO OSO #2 9/94A RPL CRSW | 93K
LC | 122234671 | ?007/007 | T3 EI SNTH LANE-HALF MN BY ?7/7 RPR STRW | METCALF | ETL.7212.POLE.STPS | 2021-10-20 | 2021-10-20 | 2022-04-12 | 2022-04-18 | 2022-04-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45191625 | T3 EI SNTH LANE-HALF MN BY ?7/7 RPR STRW | ICW
LC | 122238079 | 031/481 | T2 CLAY-MARTEL 31/481 INS DAMW | VICTOR | ETL.8250.INSL.NCER | 2021-10-21 | 2021-10-21 | 2021-11-07 | 2022-10-21 | 2022-10-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 45091876 | T2 CLAY-MARTEL 31/481 INS DAMW | ICW
LC | 122238175 | 031/480 | T2 CLAY-MARTEL 31/480 RPL CRSMW | VICTOR | ETL.8250.POLE.NWOD | 2021-10-21 | 2021-10-21 | 2021-11-07 | 2022-10-21 | 2022-10-21 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31578423 | CLAY-MARTEL 31/480 RPL CRSMW | 93E
LC | 122245197 | 019/440 | T2DI DRM GRS VLY WMR 19/440 RMV BUTT | SACTO | ETL.6760.POLE.WOOD | 2021-10-22 | 2021-10-07 | 2022-01-12 | 2022-10-07 | 2022-10-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW ACCM COMP OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45078073 | T2DI DRM GRS VLY WMR 19/440 RMV BUTT | ICW
LC | 122245934 | 001/014 | WV T2 CHRISTIE-WILLOW PASS 1/14 INS DAMW | CONCORD | ETL.6370.INSL.CERA | 2021-10-22 | 2021-10-22 | 2022-09-11 | 2022-10-22 | 2022-10-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE SR22 | Missing | Damper-Wood | Install | 45195831 | WV T2 CHRISTIE-WILLOW PASS 1/14 INS DAMW | ICW
LC | 122246729 | 004/043 | DI T3 MID FORK-GOLD HILL 4/43L RPL INSS | SACTO | ETL.5140.INSL.CERA | 2021-10-22 | 2021-10-13 | 2022-10-15 | 2022-04-11 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31542676 | T3 EI MDLE FRK-GOLD HILL 32/233 RPL INSS | 93K
LC | 122246890 | 009/098 | T3 DI DRUM-RIO OSO #1 009/098L RPL INSS | SACTO | ETL.1420.POLE.STPS | 2021-10-22 | 2021-10-13 | 2022-08-30 | 2022-04-11 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31608468 | T3 DI DRUM-RIO OSO #1 009/098L RPR CRSS | 93K
LC | 122263976 | 073/371 | T2 DI MALIN-RND MTN #2 73/371 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2021-10-27 | 2021-10-26 | 2022-08-10 | 2022-10-26 | 2022-10-26 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45385813 | T2 DI MALIN-RND MTN #2 73/371 RPR GYWS | ICS
LC | 122274996 | 021/009 | T2 DI MENDO-WLLTS BRGG 21/9 RPL HRDW | WILLITS | ETL.7550.INSL | 2021-10-29 | 2021-10-14 | 2022-08-20 | 2022-10-14 | 2022-10-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45145831 | T2NT DI MNDCN WLTS FT BRG 21/9 RPR GYWW | ICW
LC | 122281173 | 000/003 | T2 WV CHRISTIE-WILLOW PASS 0/3 INS DAMP | CONCORD | ETL.6370.POLE.WOOD | 2021-11-01 | 2021-11-01 | 2022-09-11 | 2022-11-01 | 2022-11-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Damper-Wood | Install | 45179579 | T2 WV CHRISTIE-WILLOW PASS 0/3 INS DAMP | ICW
LC | 122281259 | 000/006 | T2 WV WISHON-SAN JAQUIN #3 0/6 COMPLETE | FRESNO | ETL.9340.POLE.NWOD | 2021-11-01 | 2021-11-01 | 2022-05-02 | 2022-11-01 | 2022-11-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Steel | Install | 45092454 | T2 WV WISHON-SAN JOAQUIN #3 0/6 INS DAMP | ICS
LC | 122282327 | 018/580 | T2 DI SPAULDING-SUMMIT 18/580 RPR INSW | SACTO | ETL.8060.INSL.NCER | 2021-11-01 | 2021-11-01 | 2022-09-15 | 2022-11-01 | 2022-11-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45219523 | T2 DI SPAULDING-SUMMIT 18/580 RPR INSW | ICW
LC | 122282450 | 001/012 | T2 DI DIVIDE-VANDNBRG #2 1/12 RPR INSW | PISMOBCH | ETL.8630.INSL.NCER | 2021-11-01 | 2021-11-01 | 2022-01-31 | 2022-11-01 | 2022-11-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45098716 | T2 DI DIVIDE-VANDNBRG #2 1/12 RPR INSW | ICW
LC | 122282459 | 000/005 | T2 DI PIT #3-PIT #1 0/5 RMV NEST | TABLEMTN | ETL.5400.TOWR | 2021-11-01 | 2021-11-01 | 2022-10-12 | 2022-11-01 | 2022-11-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove | 45240554 | T2 DI PIT #3-PIT #1 0/5 RMV NEST | ICS
LC | 122282527 | 002/017 | T2 DI DIVIDE-VANDNBRG #2 2/17 RPL HRDD | PISMOBCH | ETL.8630.POLE.WDPS | 2021-11-01 | 2021-11-01 | 2022-02-14 | 2022-11-01 | 2022-11-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45098719 | T2 DI DIVIDE-VANDNBRG #2 2/17 RPL HRDD | ICW
LC | 122289485 | 001/010 | T3 WV WISHN-SAN JOAQN #3 1/10 COMPLETE | FRESNO | ETL.9340.POLE.NWOD | 2021-11-02 | 2021-11-02 | 2022-04-19 | 2022-05-01 | 2022-05-02 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45092456 | T3 WV WISHON-SAN JOAQN #3 1/10 RPR FENCE | ICS
LC | 122307670 | :009/052 | T3 EAGLE ROCK-REDBUD :9/52 RPL INSS | LAKEVLLE | ETL.1480.INSL.CERA | 2021-11-03 | 2021-11-03 | 2021-11-04 | 2022-05-02 | 2022-05-03 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW NONR COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31573886 | T3 ETLI00000949_EAGLE ROCK RDBD :009/052 | 93K
LC | 122320030 | 036/240 | T2 CRESTA-RIO OSO 036/240 RPL INSS | TABLEMTN | ETL.4590.INSL.CERA | 2021-11-04 | 2021-11-04 | 2022-05-07 | 2022-11-04 | 2022-11-04 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31590446 | T2 CRESTA-RIO OSO 036/240 RPL INSS | 93K
LC | 122325860 | 037/161 | T2 WV GYSRS #9-LAKEVILE 37/161 INS DMPS | LAKEVLLE | ETL.4780.INSL | 2021-11-05 | 2021-11-05 | 2021-04-22 | 2022-11-05 | 2022-11-05 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Steel | Install | 45143071 | T2 WV GYSRS #9-LAKEVILE 37/161 INS DMPS | ICS
LC | 122326142 | 003/020 | T2 DI DIVIDE-VANDENBURG#2 3/20L INS HRDD | PISMOBCH | ETL.8630.POLE.WDPS | 2021-11-05 | 2021-11-01 | 2022-02-14 | 2022-11-01 | 2022-11-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Wood | Install | 45098718 | T2 DI DIVIDE-VANDENBURG#2 3/20L INS HRDD | ICW
LC | 122330089 | 005/005 | T2 DI LAYTONVILLE-COVELO 5/5 RPL POLE | WILLITS | ETL.7390.POLE.WOOD | 2021-11-06 | 2021-10-27 | 2022-06-13 | 2022-10-27 | 2022-10-27 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542886 | DI LAYTONVILLE-COVELO 5/3 RPL POLE | 70Y
LC | 122331551 | 006/114 | T3 FRNCH MEADOW-MIDDLE FRK 6/114 REFRAME | SACTO | ETL.6870.POLE.WOOD | 2021-11-06 | 2021-11-06 | 2022-05-12 | 2022-05-05 | 2022-05-06 | Late | 637 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW NONR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31578224 | T3 FRNCH MEADOW-MIDDLE FRK 6/114 REFRAME | 93E
LC | 122340835 | 114/001 | T2 WV HUMBOLDT-BRIDGEVILE 114/1 INS DAMP | EUREKA | ETL.1810.INSL.NCER | 2021-11-09 | 2021-11-09 | 2022-04-09 | 2022-11-09 | 2022-11-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 45155490 | T2 WV HUMBOLDT-BRIDGEVILE 114/1 INS DAMP | ICW
LC | 122341523 | 009/106 | T2 WV DRUM-SUMMIT #1 9/106 RPR INSS | SACTO | ETL.1440.INSL.NCER | 2021-11-09 | 2021-11-09 | 2022-06-21 | 2022-11-09 | 2022-11-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair | 45199098 | T2 WV DRUM-SUMMIT #1 9/106 RPR INSS | ICW
LC | 122341677 | 015/428 | T3 COLGATE-ALLEGHANY 15/428 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2021-11-09 | 2021-11-09 | 2022-06-19 | 2022-05-08 | 2022-05-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW NONR COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31578443 | T3 COLGATE-ALLEGHANY 15/428 RPL POLE | 70Y
LC | 122341696 | 014/389 | T3 COLGATE-ALLEGHANY 14/389 RPR GYWW | SACTO | ETL.6470.POLE.WOOD | 2021-11-09 | 2021-11-09 | 2022-06-20 | 2022-05-08 | 2022-05-09 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW NONR COMP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45240131 | T3 COLGATE-ALLEGHANY 14/389 RPR GYWW | ICW
LC | 122343290 | 015/193 | T2 KESWICK-TRINITY 15/193 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2021-11-09 | 2021-11-09 | 2022-05-31 | 2022-11-09 | 2022-11-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31604004 | T2 KESWICK-TRINITY 15/193 RPL POLE | 70Y
LC | 122346226 | 006/077 | T2 DI W. PNT-VALLEY SPRNG 6/77 RPR WDPKR | VICTOR | ETL.8350.POLE.WOOD | 2021-11-09 | 2021-11-05 | 2022-05-21 | 2022-11-05 | 2022-11-05 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45167638 | T2 DI W. PNT-VALLEY SPRNG 6/77 RPR WDPKR | ICW
LC | 122371405 | 010/078B | T2 EI TRNTY-CTNWD 10/078B RPL POLE CPT | TABLEMTN | ETL.4040.POLE.WOOD | 2021-11-12 | 2021-03-26 | 2022-08-30 | 2022-03-26 | 2022-03-26 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO FRAB NTDE SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31545105 | T2 EI TRNTY-CTNWD 10/078B RPL POLE | 70Y
LC | 122371678 | 021/118 | T2 WV PARKWAY-MORAGA 21/118 RPR OPGW | CONCORD | ETL.5930.TOWR | 2021-11-12 | 2021-11-12 | 2022-02-02 | 2022-11-12 | 2022-11-12 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45106383 | T2 WV PARKWAY-MORAGA 21/118 RPR OPGW | ICS
LC | 122371735 | 021/117 | T2 WV PARKWAY-MORAGA 21/117 RPR OPGW | CONCORD | ETL.5930.TOWR | 2021-11-12 | 2021-11-12 | 2022-02-02 | 2022-11-12 | 2022-11-12 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45106384 | T2 WV PARKWAY-MORAGA 21/117 RPR OPGW | ICS
LC | 122372641 | 000/001 | T3 MIDDLE FORK-GOLD HILL 0/1 RPR SHLDW | SACTO | ETL.5140.INSL.CERA | 2021-11-13 | 2021-11-13 | 2021-11-16 | 2022-05-12 | 2022-05-13 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW NONR COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45078404 | T3 MIDDLE FORK-GOLD HILL 0/1 RPR SHLDW | ICS
LC | 122375979 | 005/091 | T2 COLGATE-PALERMO 5/91 RPL STRW CMPLTD | SACTO | ETL.6500.POLE.WOOD | 2021-11-15 | 2021-11-15 | 2022-05-18 | 2022-11-15 | 2022-11-15 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31423185 | T2 EI COLGATE-PALERMO-3/49 REPLACE POLE | 70Y
LC | 122377807 | 001/041 | T2 DI COLGATE-ALLEGHANY 001/041 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2021-11-15 | 2021-11-15 | 2022-06-24 | 2022-11-15 | 2022-11-15 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31596504 | T2 DI COLGATE-ALLEGHANY 1/41 RPL STRW | 70Y
LC | 122378391 | 002/055 | T2 DI CLGTE-ALLGHNY 002/055 RPR SPLW | SACTO | ETL.6470.INSL.CERA | 2021-11-15 | 2021-11-15 | 2022-06-23 | 2022-11-15 | 2022-11-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45240133 | T2 DI CLGTE-ALLGHNY 002/055 RPR SPLW | ICW
LC | 122378392 | 002/055 | T2 DI CLGTE-ALLGHNY 002/055 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2021-11-15 | 2021-11-15 | 2022-06-27 | 2022-11-15 | 2022-11-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45240134 | T2 DI CLGTE-ALLGHNY 002/055 RPR STRW | ICW
LC | 122379414 | 003/094 | T2 DI COLGATE-ALLEGHANY 3/94 RPR INSW | SACTO | ETL.6470.INSL.NCER | 2021-11-16 | 2021-11-15 | 2022-06-22 | 2022-11-15 | 2022-11-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45240135 | T2 DI COLGATE-ALLEGHANY 3/94 RPR INSW | ICW
LC | 122381023 | 079/321 | T2 RND MTN-TABLE MTN #2 79/321 RPL ANCS | TABLEMTN | ETL.6070.TOWR | 2021-11-16 | 2021-11-16 | 2022-08-29 | 2022-11-16 | 2022-11-16 | On-time | 93Z | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Steel | Replace | 31602985 | T2 RND MTN-TABLE MTN #2 79/321 RPL ANCS | 93Z
LC | 122382734 | 002/072 | T2 DI COLGTE-ALLGHNY 2/72 RPR GYWW | SACTO | ETL.6470.POLE.WOOD | 2021-11-16 | 2021-11-15 | 2022-06-24 | 2022-11-15 | 2022-11-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45240136 | T2 DI COLGTE-ALLGHNY 2/72 RPR GYWW | ICW
LC | 122384558 | 004/040 | T2 DI PIT #1-COTTNWD 4/40 RPR INSS | TABLEMTN | ETL.5390.INSL.NCER | 2021-11-16 | 2021-11-09 | 2022-03-10 | 2022-11-09 | 2022-11-09 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45211200 | T2 DI PIT #1-COTTNWD 4/40 RPR INSS | ICS
LC | 122389325 | A009/189 | T2 DI CNR-TL MN-RVL A9/189 RPR WDP CMPLT | TABLEMTN | ETL.6330.POLE.WOOD | 2021-11-17 | 2021-11-15 | 2022-05-17 | 2022-11-15 | 2022-11-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45212510 | T2 DI CENTER-TBL MTN-ORVL A9/189 RPR WDP | ICW
LC | 122397579 | 001/016 | T2 DI BCKS CRK-RCK CRK-CRST 1/16 UNBURY | TABLEMTN | ETL.4430.TOWR | 2021-11-19 | 2021-11-15 | 2022-07-20 | 2022-11-15 | 2022-11-15 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45160920 | T2 DI BCKS CRK-RCK CRK-CRST 1/16 UNBURY | ICQ
LC | 122400202 | 007/063 | T3 EI ATSCADRO-CAYCS 7/63 RPL ANCW | PISMOBCH | ETL.8480.POLE.WOOD | 2021-11-19 | 2021-11-19 | 2022-05-09 | 2022-05-18 | 2022-05-19 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31579486 | T3 EI ATSCADRO-CAYCS 7/63 RPL ANCW | 93E
LC | 122400235 | 005/065 | T2 EI GRN VLY-CAMP EVERS 5/65L RMV VEG | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-11-19 | 2021-11-19 | 2022-06-02 | 2022-11-19 | 2022-11-19 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 122403951 | 005/065 | T2 EI GRN VLY-CAMP EVERS 5/65R RMV VEG | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-11-22 | 2021-11-19 | 2022-06-02 | 2022-11-19 | 2022-11-19 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 122403952 | 005/065 | T2 EI GRN VLY-CAMP EVERS 5/65C RMV VEG | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-11-22 | 2021-11-19 | 2022-06-02 | 2022-11-19 | 2022-11-19 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 122405115 | 017/457 | T3 WV COLGATE-ALLEGHANY 17/457 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2021-11-22 | 2021-11-22 | 2022-06-21 | 2022-05-21 | 2022-05-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31531502 | T3 DI COLGATE-ALLGHNY 14/395 RPL STRW | 70Y
LC | 122407035 | 004/056 | T3 EI DRUM-SUMMIT #2 4/56 RPLC STRW | SACTO | ETL.1450.POLE.WDPS | 2021-11-22 | 2021-11-22 | 2022-06-08 | 2022-05-21 | 2022-05-22 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP FIRE COMP OH TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31578023 | DI DRUM-SUMMIT #2 15/179R RPL STRW | 70Y
LC | 122408931 | T002/015 | WV T2 TLCY-NP #1 T2/15 INS DAMW CMPLT | LAKEVLLE | ETL.8180.POLE.NWOD | 2021-11-23 | 2021-11-23 | 2022-04-26 | 2022-11-23 | 2022-11-23 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Damper-Steel | Install | 45084845 | WV T2 TULUCAY-NAPA #1 T2/15 INS DAMW | ICS
LC | 122410197 | 001/022 | T2 VALLEY SPRINGS #1 1/22 RPL GYWW | VICTOR | ETL.8210.POLE.WOOD | 2021-11-23 | 2021-11-23 | 2022-02-17 | 2022-11-23 | 2022-11-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45074892 | T2 VALLEY SPRINGS #1 1/22 RPL GYWW | ICW
LC | 122410249 | 001/022 | T2 VALLEY SPRINGS #1 1/22 INS HRDD | VICTOR | ETL.8210.POLE.WOOD | 2021-11-23 | 2021-11-23 | 2022-02-17 | 2022-11-23 | 2022-11-23 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | Missing | Hardware-Wood | Install | 45074849 | T2 VALLEY SPRINGS #1 1/22 INS HRDD | ICW
LC | 122421794 | :015/011 | T2 WV EAGLE RCK-RDBD :15/11 RPL STRW | LAKEVLLE | ETL.1480.POLE.WOOD | 2021-11-29 | 2021-11-29 | 2022-01-18 | 2022-11-29 | 2022-11-29 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31472116 | T2 DI EAGLE ROCK-REDBD :15/11 RPL SWIW | 70Y
LC | 122422686 | 013/106 | T3 DI MONTA VSTA-BRNS 13/106 RPR GYWW | MOSSLNDG | ETL.7590.INSL.NCER | 2021-11-29 | 2021-11-29 | 2022-02-25 | 2022-05-28 | 2022-05-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45082572 | T3 DI MONTA VSTA-BRNS 13/106 RPR GYWW | ICW
LC | 122427343 | 023/357A | T2 WV KESWICK-TRINITY 023/357A RPL ANCW | TABLEMTN | ETL.7270.POLE.WOOD | 2021-11-30 | 2021-11-30 | 2022-10-28 | 2022-11-30 | 2022-11-30 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE SR22 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31579743 | T2 WV KESWICK-TRINITY 023/357A RPL ANCW | 93E
LC | 122432644 | T003/000 | T2 WV TLCY-NP #1 T3/0 INS DAMW CMPLTD | LAKEVLLE | ETL.8180.POLE.NWOD | 2021-12-01 | 2021-12-01 | 2022-04-26 | 2022-12-01 | 2022-12-01 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Steel | Install | 45262689 | T2 WV TULUCAY-NAPA #1 T3/0 INS DAMW | ICS
LC | 122435817 | 024/007 | T2 EI GRBRVL-LYTNVL 24/7 RPR STRW | WILLITS | ETL.8365.POLE.WOOD | 2021-12-02 | 2021-12-02 | 2022-04-25 | 2022-12-02 | 2022-12-02 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45155520 | T2 EI GRBRVL-LYTNVL 24/7 RPR STRW | ICW
LC | 122436499 | 026/005 | T2 EI GRBRVL-LYTNVL 26/5 RPL STRW | WILLITS | ETL.8365.POLE.WOOD | 2021-12-02 | 2021-12-02 | 2022-04-16 | 2022-12-02 | 2022-12-02 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31579755 | T2 EI GRBRVL-LYTNVL 27/0 RPL STRW | 70Y
LC | 122437207 | 027/000 | T2 EI GRBRVL-LYTNVL 27/0 RPL STRW | WILLITS | ETL.8365.POLE.WOOD | 2021-12-02 | 2021-12-02 | 2022-04-22 | 2022-12-02 | 2022-12-02 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31579755 | T2 EI GRBRVL-LYTNVL 27/0 RPL STRW | 70Y
LC | 122442011 | 002/055 | T3 WV CNTVL-TBL MTN-ORVL 2/55 INS DMPW | TABLEMTN | ETL.6330.POLE.NWOD | 2021-12-03 | 2021-12-03 | 2022-04-04 | 2022-06-01 | 2022-06-03 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Damper-Wood | Replace | 45253165 | T3 WV CNTVL-TBL MTN-ORVL 2/55 INS DMPW | ICW
LC | 122443733 | 003/030 | T2 WV HAT CREK #1-PIT #1 3/30 INS ANCHW | TABLEMTN | ETL.7020.POLE.NWOD | 2021-12-03 | 2021-12-03 | 2022-09-20 | 2022-12-03 | 2022-12-03 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Anchor-Wood | Install | 31604500 | T2 WV HAT CREK #1-PIT #1 3/30 INS ANCHW | 93E
LC | 122443843 | 009/171 | T3 FRNCH MDWS-MDDL FRK 9/171 REFRAME | SACTO | ETL.6870.POLE.WOOD | 2021-12-03 | 2021-12-03 | 2022-05-03 | 2022-06-01 | 2022-06-03 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31578224 | T3 FRNCH MEADOW-MIDDLE FRK 6/114 REFRAME | 93E
LC | 122448105 | 026/000 | T2 EI GRBRVLL-LAYTNVLL 26/0 INS DMPW | WILLITS | ETL.8365.POLE.WOOD | 2021-12-06 | 2021-12-06 | 2022-04-22 | 2022-12-06 | 2022-12-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Wood | Install | 45155525 | T2 EI GRBRVLL-LAYTNVLL 26/0 INS DMPW | ICW
LC | 122449544 | 019/076 | T2 EI DIABLO-MIDWAY #3 19/76 BENT STEEL | PISMOBCH | ETL.5980.TOWR | 2021-12-06 | 2021-12-06 | 2022-05-12 | 2022-12-06 | 2022-12-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45210875 | T2 EI DIABLO-MIDWAY #3 19/76 BENT STEEL | ICQ
LC | 122456943 | 023/282 | T2 DRUM-SUMMIT #1 23/282L RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-12-08 | 2021-12-08 | 2022-09-01 | 2022-12-08 | 2022-12-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31581111 | T2 DI DRUM-SUMMIT #1 19/220 RPL STRW | 70Y
LC | 122456974 | 023/282 | T2 DRUM-SUMMIT #1 23/282R RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2021-12-08 | 2021-12-08 | 2022-09-01 | 2022-12-08 | 2022-12-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31581111 | T2 DI DRUM-SUMMIT #1 19/220 RPL STRW | 70Y
LC | 122460116 | 000/004 | T2 EI MRO BAY-SLR SW STA #1 0/4 RPR STRT | PISMOBCH | ETL.5300.TOWR | 2021-12-09 | 2021-12-09 | 2022-06-27 | 2022-12-09 | 2022-12-09 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45210876 | T2 EI MRO BAY-SLR SW STA #1 0/4 RPR STRT | ICQ
LC | 122460818 | 007/093 | T3 DI GREEN VALLEY 007/093L COMPLETE | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-12-09 | 2021-12-09 | 2022-04-24 | 2022-06-07 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31591267 | T3 DI GREEN VALLEY 007/093L RPL STRW | 70Y
LC | 122460965 | 007/093 | T3 DI GREEN VALLEY 007/093R COMPLETE | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-12-09 | 2021-12-09 | 2022-04-24 | 2022-06-07 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31591267 | T3 DI GREEN VALLEY 007/093L RPL STRW | 70Y
LC | 122460968 | 007/093 | T3 DI GREEN VALLEY 007/093C COMPLETE | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-12-09 | 2021-12-09 | 2022-04-24 | 2022-06-07 | 2022-06-09 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31591267 | T3 DI GREEN VALLEY 007/093L RPL STRW | 70Y
LC | 122474110 | 004/040 | T3 EI SBRNTE-GRZZLY-CLR #1 4/40 INS ROAD | CONCORD | ETL.3740.TOWR | 2021-12-10 | 2021-12-10 | 2022-07-01 | 2022-06-08 | 2022-06-10 | Late | 374 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP NONR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Road | Replace | 31607281 | T3 EI SBRNTE-GRZZLY-CLR #1 4/40 INS ROAD | 71Y
LC | 122474788 | 002/021 | T3 EI DI MDDL FRK-GLD HILL 2/21 RPL STRW | SACTO | ETL.5140.POLE.WDPS | 2021-12-10 | 2021-12-10 | 2022-10-10 | 2022-06-08 | 2022-12-10 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546023 | T2 DI MDD FRK-GLD HLL 026/201 RPL STRW | 70Y
LC | 122484724 | 002/023 | T2 DI UKIAH-HPLND-CLVRDLE 2/23L COMPLETE | WILLITS | ETL.4050.POLE.WDPS | 2021-12-14 | 2021-07-24 | 2022-05-27 | 2022-07-24 | 2022-07-24 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545800 | T2 EI UKIAH-HOPLAND RPL POLE IN 6 TWRS. | 70Y
LC | 122490473 | 005/031 | T3 FULTON-IGNACIO #1 005/031 RPR ROAD | LAKEVLLE | ETL.4680.TOWR | 2021-12-15 | 2021-12-15 | 2022-03-04 | 2022-06-13 | 2022-06-15 | On-time | 932 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW NONR COMP OH FMOB TR3 PRTO FRAB | Grade Change | Road | Repair | 44953660 | EI FULTON-PUEBLO :7/6 RPR ROAD | CHS
LC | 122491982 | 007/092 | T3 DI GRN VLLY-CMP EVRS 7/92L RPL STRW | MOSSLNDG | ETL.1710.POLE.WDPS | 2021-12-15 | 2021-12-14 | 2022-04-25 | 2022-06-12 | 2022-06-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW OTHR FIRE COMP OH TR3 PRTO NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31591152 | T3 DI GRN VLLEY-CAMP EVERS 7/92 RPL STRW | 70Y
LC | 122495898 | 013/139 | T2 DI RND MNTIN-CTNWD 13/139L RPL PL | TABLEMTN | ETL.5640.POLE.WDPS | 2021-12-16 | 2021-06-09 | 2022-07-27 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542253 | T2 EI RND MTN-CTTNWD #2 13/139 RPL STRC | 70Y
LC | 122498720 | 026/125 | EI CRTNA-MNDCIN 026/125 RMV SWC/INSS RPL | WILLITS | ETL.1330.SWIT | 2021-12-17 | 2021-12-17 | 2022-06-29 | 2022-12-17 | 2022-12-17 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW INSP NONR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615449 | EI CRTNA-MNDCIN 026/125 RMV SWC/INSS RPL | 93K
LC | 122510057 | 019/498 | T2 WV CARIBOU #2 19/498 RPL INSLW | TABLEMTN | ETL.6280.INSL.NCER | 2021-12-21 | 2021-12-21 | 2022-07-14 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31580713 | T2 CARIBOU #2 - 60 KV_019/496 | 93I
LC | 122511952 | 017/400 | T2 DRM-GRS VLY-WMAR 17/400 INS DPRW | SACTO | ETL.6760.INSL.CERA | 2021-12-22 | 2021-12-22 | 2022-06-29 | 2022-12-22 | 2022-12-22 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install | 45196026 | T2 DRM-GRS VLY-WMAR 17/400 INS DPRW | ICS
LC | 122512189 | 016/097 | T2 STNSLS-MNTCA #2 16/097 RPR SPLSS | VICTOR | ETL.3820.INSL.CERA | 2021-12-22 | 2021-12-22 | 2022-03-22 | 2022-12-22 | 2022-12-22 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45194141 | T2 STNSLS-MNTCA #2 16/097 RPR SPLSS | ICS
LC | 122512441 | 001/034 | T2 EI VOLTA-SOUTH 1/34 STRW RPR | TABLEMTN | ETL.8300.POLE.WOOD | 2021-12-22 | 2021-12-22 | 2022-03-24 | 2022-12-22 | 2022-12-22 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45194112 | T2 EI VOLTA-SOUTH 1/34 STRW RPR | ICW
LC | 122514424 | 001/008 | T2 T0 OAKHURST TAP 01/08 RPL INSW | FRESNO | ETL.1252.INSL.NCER | 2021-12-23 | 2021-12-21 | 2022-03-23 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589246 | T2 OAKHURST TAP 00/10 RPL INSW | 93I
LC | 122514428 | 002/000 | T2 OAKHURST TAP 02/00 RPL INSW | FRESNO | ETL.1252.INSL.NCER | 2021-12-23 | 2021-12-21 | 2022-03-24 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589246 | T2 OAKHURST TAP 00/10 RPL INSW | 93I
LC | 122515043 | 002/002 | T2 OAKHURST TAP 02/02 RPL INSW | FRESNO | ETL.1252.INSL.NCER | 2021-12-23 | 2021-12-21 | 2022-03-24 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589246 | T2 OAKHURST TAP 00/10 RPL INSW | 93I
LC | 122515044 | 003/000 | T2 OAKHURST TAP 03/00 RPL INSW | FRESNO | ETL.1252.INSL.NCER | 2021-12-23 | 2021-12-21 | 2022-03-24 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589246 | T2 OAKHURST TAP 00/10 RPL INSW | 93I
LC | 122515045 | 003/004 | T2 OAKHURST TAP 03/04 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-24 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589246 | T2 OAKHURST TAP 00/10 RPL INSW | 93I
LC | 122515151 | 004/000 | T2 OAKHURST TAP 04/00 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-25 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589246 | T2 OAKHURST TAP 00/10 RPL INSW | 93I
LC | 122515153 | 004/002 | T2 OAKHURST TAP 04/02 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-25 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589246 | T2 OAKHURST TAP 00/10 RPL INSW | 93I
LC | 122515155 | 004/003 | T2 OAKHURST TAP 04/03 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-25 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589246 | T2 OAKHURST TAP 00/10 RPL INSW | 93I
LC | 122515191 | 004/004 | T2 OAKHURST TAP 04/04 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-24 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589246 | T2 OAKHURST TAP 00/10 RPL INSW | 93I
LC | 122515193 | 004/007 | T2 OAKHURST TAP 04/07 RPL INSW | FRESNO | ETL.1252.INSL.NCER | 2021-12-23 | 2021-12-21 | 2022-03-23 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR ACCM COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589247 | T2 OAKHURST TAP 04/07 RPL INSW | 93I
LC | 122515194 | 004/009 | T2 OAKHURST TAP 04/09 RPL INSW | FRESNO | ETL.1252.INSL.NCER | 2021-12-23 | 2021-12-21 | 2022-03-24 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589247 | T2 OAKHURST TAP 04/07 RPL INSW | 93I
LC | 122515197 | 005/004A | T2 OAKHURST TAP 05/04A RPL INSW | FRESNO | ETL.1252.INSL.NCER | 2021-12-23 | 2021-12-21 | 2022-03-24 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589247 | T2 OAKHURST TAP 04/07 RPL INSW | 93I
LC | 122515199 | 005/004B | T2 OAKHURST TAP 05/04B RPL INSW | FRESNO | ETL.1252.INSL.NCER | 2021-12-23 | 2021-12-21 | 2022-03-24 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589247 | T2 OAKHURST TAP 04/07 RPL INSW | 93I
LC | 122515260 | 005/004C | T2 OAKHURST TAP 05/04C RPL INSW | FRESNO | ETL.1252.INSL.NCER | 2021-12-23 | 2021-12-21 | 2022-03-24 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589247 | T2 OAKHURST TAP 04/07 RPL INSW | 93I
LC | 122515266 | 005/005 | T2 OAKHURST TAP 05/05 COMPLETE | FRESNO | ETL.1252.INSL.NCER | 2021-12-23 | 2021-12-21 | 2022-03-25 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589247 | T2 OAKHURST TAP 04/07 RPL INSW | 93I
LC | 122515289 | 006/006 | T2 OAKHURST TAP 06/06 RPL INSW | FRESNO | ETL.1252.INSL.NCER | 2021-12-23 | 2021-12-21 | 2022-03-23 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589247 | T2 OAKHURST TAP 04/07 RPL INSW | 93I
LC | 122515308 | 006/008 | T2 OAKHURST TAP 06/08 COMPLETE | FRESNO | ETL.1252.INSL.NCER | 2021-12-23 | 2021-12-21 | 2022-03-23 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589247 | T2 OAKHURST TAP 04/07 RPL INSW | 93I
LC | 122515309 | 006/009 | T2 OAKHURST TAP 06/09 RPL INSW | FRESNO | ETL.1252.INSL.NCER | 2021-12-23 | 2021-12-21 | 2022-03-23 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589247 | T2 OAKHURST TAP 04/07 RPL INSW | 93I
LC | 122515355 | 007/013 | T2 OAKHURST TAP 07/13 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-25 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589247 | T2 OAKHURST TAP 04/07 RPL INSW | 93I
LC | 122515393 | 007/014 | T2 OAKHURST TAP 07/14 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-25 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589248 | T2 OAKHURST TAP 07/14 RPL INSW | 93I
LC | 122515394 | 008/000 | T2 OAKHURST TAP 08/00 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-25 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589248 | T2 OAKHURST TAP 07/14 RPL INSW | 93I
LC | 122515396 | 008/004 | T2 OAKHURST TAP 08/04 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-26 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589248 | T2 OAKHURST TAP 07/14 RPL INSW | 93I
LC | 122515397 | 009/001A | T2 OAKHURST TAP 09/01A RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-24 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589248 | T2 OAKHURST TAP 07/14 RPL INSW | 93I
LC | 122515399 | 009/001B | T2 OAKHURST TAP 09/01B RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-24 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589248 | T2 OAKHURST TAP 07/14 RPL INSW | 93I
LC | 122515411 | 009/001C | T2 OAKHURST TAP 09/01C RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-24 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589248 | T2 OAKHURST TAP 07/14 RPL INSW | 93I
LC | 122515415 | 009/009 | T2 OAKHURST TAP 09/09 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-24 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589248 | T2 OAKHURST TAP 07/14 RPL INSW | 93I
LC | 122515417 | 009/011 | T2 OAKHURST TAP 09/11 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-24 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589248 | T2 OAKHURST TAP 07/14 RPL INSW | 93I
LC | 122515418 | 010/001 | T2 OAKHURST TAP 10/01 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-25 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589248 | T2 OAKHURST TAP 07/14 RPL INSW | 93I
LC | 122515474 | 010/002A | T2 OAKHURST TAP 10/02A RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-26 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589249 | T2 OAKHURST TAP 10/02A RPL INSW | 93I
LC | 122515475 | 010/002B | T2 AKHURST TAP 10/02B RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-26 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589249 | T2 OAKHURST TAP 10/02A RPL INSW | 93I
LC | 122515476 | 010/002C | T2 OAKHURST TAP 10/02C RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-26 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589249 | T2 OAKHURST TAP 10/02A RPL INSW | 93I
LC | 122515478 | 010/007 | T2 OAKHURST TAP 10/07 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-25 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589244 | T3 DI OAKHURST TAP 017/009 RPL INSW | 93I
LC | 122515531 | 010/011 | T2 OAKHURST TAP 10/11 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-26 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCL COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579297 | T2 DI OAKHURST TAP NCINSUL 12/3 RPL INSW | 93I
LC | 122515534 | 011/002 | T2 OAKHURST TAP 10/02 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-27 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589249 | T2 OAKHURST TAP 10/02A RPL INSW | 93I
LC | 122515536 | 012/000A | T2 OAKHURST TAP 12/00A RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-26 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589249 | T2 OAKHURST TAP 10/02A RPL INSW | 93I
LC | 122515537 | 012/000B | T2 T0 OAKHURST TAP 12/00B RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-26 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589249 | T2 OAKHURST TAP 10/02A RPL INSW | 93I
LC | 122515538 | 012/000C | T2 OAKHURST TAP 12/00C RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-27 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589249 | T2 OAKHURST TAP 10/02A RPL INSW | 93I
LC | 122515539 | 012/004 | T2 OAKHURST TAP 12/04 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-30 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589250 | T2 OAKHURST TAP 12/05C RPL INSW | 93I
LC | 122515590 | 012/005A | T2 OAKHURST TAP 12/05A RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-27 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589249 | T2 OAKHURST TAP 10/02A RPL INSW | 93I
LC | 122515591 | 012/005B | T2 OAKHURST TAP 12/05B RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-27 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589249 | T2 OAKHURST TAP 10/02A RPL INSW | 93I
LC | 122515593 | 012/005C | T2 OAKHURST TAP 12/05C RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-27 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589249 | T2 OAKHURST TAP 10/02A RPL INSW | 93I
LC | 122515617 | 012/006 | T2 OAKHURST TAP 12/06 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-27 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589250 | T2 OAKHURST TAP 12/05C RPL INSW | 93I
LC | 122515618 | 012/007 | T2 OAKHURST TAP 12/07 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-29 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589250 | T2 OAKHURST TAP 12/05C RPL INSW | 93I
LC | 122515619 | 012/009 | T2 OAKHURST TAP 12/09 RPL INSW | FRESNO | ETL.1252.POLE.WOOD | 2021-12-23 | 2021-12-21 | 2022-03-27 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589250 | T2 OAKHURST TAP 12/05C RPL INSW | 93I
LC | 122515660 | 013/000 | T2 OAKHURST TAP 13/00 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-27 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589250 | T2 OAKHURST TAP 12/05C RPL INSW | 93I
LC | 122515661 | 013/001 | T2 OAKHURST TAP 13/01 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-04-01 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31589250 | T2 OAKHURST TAP 12/05C RPL INSW | 93I
LC | 122515662 | 013/002A | T2 OAKHURST TAP 13/02A COMPLETE | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-04-01 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589250 | T2 OAKHURST TAP 12/05C RPL INSW | 93I
LC | 122515666 | 013/002B | T2 OAKHURST TAP 13/02B RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-04-01 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589250 | T2 OAKHURST TAP 12/05C RPL INSW | 93I
LC | 122515667 | 013/002C | T2 OAKHURST TAP 13/02C RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-04-01 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589250 | T2 OAKHURST TAP 12/05C RPL INSW | 93I
LC | 122515668 | 013/003 | T2 OAKHURST TAP 13/03 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-31 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589250 | T2 OAKHURST TAP 12/05C RPL INSW | 93I
LC | 122515669 | 013/005A | T2 OAKHURST TAP 13/05A COMPLETE | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-04-02 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR ACCM COMP OH TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589251 | T2 OAKHURST TAP 13/05A RPL INSW | 93I
LC | 122515704 | 013/005B | T2 OAKHURST TAP 13/05B COMPLETE | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-04-02 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589251 | T2 OAKHURST TAP 13/05A RPL INSW | 93I
LC | 122515705 | 013/005C | T2 OAKHURST TAP 13/05C COMPLETE | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-04-02 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589251 | T2 OAKHURST TAP 13/05A RPL INSW | 93I
LC | 122515706 | 013/006 | T2 OAKHURST TAP 13/06 COMPLETE | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-04-01 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589251 | T2 OAKHURST TAP 13/05A RPL INSW | 93I
LC | 122515707 | 013/007A | T2 OAKHURST TAP 13/07A RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-04-01 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589251 | T2 OAKHURST TAP 13/05A RPL INSW | 93I
LC | 122515708 | 013/007B | T2 OAKHURST TAP 13/07B RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-04-01 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589251 | T2 OAKHURST TAP 13/05A RPL INSW | 93I
LC | 122515709 | 013/007C | T2 OAKHURST TAP 13/07C RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-04-01 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589251 | T2 OAKHURST TAP 13/05A RPL INSW | 93I
LC | 122515761 | 013/008 | T2 OAKHURST TAP 13/08 COMPLETE | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-04-05 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589251 | T2 OAKHURST TAP 13/05A RPL INSW | 93I
LC | 122515762 | 014/000 | T2 OAKHURST TAP 14/00 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-04-04 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589251 | T2 OAKHURST TAP 13/05A RPL INSW | 93I
LC | 122515763 | 014/001 | T2 OAKHURST TAP 14/01 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-29 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589251 | T2 OAKHURST TAP 13/05A RPL INSW | 93I
LC | 122515764 | 014/004 | T2 OAKHURST TAP 14/04 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-31 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589252 | T2 OAKHURST TAP 14/04 RPL INSW | 93I
LC | 122515765 | 014/005A | T2 OAKHURST TAP 14/05A COMPLETE | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-29 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589252 | T2 OAKHURST TAP 14/04 RPL INSW | 93I
LC | 122515766 | 014/005B | T2 OAKHURST TAP 14/05B COMPLETE | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-29 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589252 | T2 OAKHURST TAP 14/04 RPL INSW | 93I
LC | 122515767 | 014/005C | T2 OAKHURST TAP 14/05C RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-29 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589252 | T2 OAKHURST TAP 14/04 RPL INSW | 93I
LC | 122515768 | 014/006 | T2 OAKHURST TAP 14/06 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-29 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589252 | T2 OAKHURST TAP 14/04 RPL INSW | 93I
LC | 122515800 | 015/001A | T2 OAKHURST TAP 15/01A RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-25 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589252 | T2 OAKHURST TAP 14/04 RPL INSW | 93I
LC | 122515801 | 015/001B | T2 OAKHURST TAP 15/01B RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-25 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589252 | T2 OAKHURST TAP 14/04 RPL INSW | 93I
LC | 122515802 | 015/001C | T2 OAKHURST TAP 15/01C RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-25 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589252 | T2 OAKHURST TAP 14/04 RPL INSW | 93I
LC | 122515803 | 015/003 | T2 OAKHURST TAP 15/03 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-31 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589252 | T2 OAKHURST TAP 14/04 RPL INSW | 93I
LC | 122515804 | 015/004 | T2 OAKHURST TAP 15/04 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-27 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589252 | T2 OAKHURST TAP 14/04 RPL INSW | 93I
LC | 122515805 | 015/006A | T2 OAKHURST TAP 15/06A RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-27 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589253 | T2 OAKHURST TAP 15/06A RPL INSW | 93I
LC | 122515806 | 015/006B | T2 OAKHURST TAP 15/06B RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-27 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589253 | T2 OAKHURST TAP 15/06A RPL INSW | 93I
LC | 122515807 | 015/006C | T2 OAKHURST TAP 15/06C RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-28 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589253 | T2 OAKHURST TAP 15/06A RPL INSW | 93I
LC | 122515808 | 015/007A | T2 OAKHURST TAP 15/07A RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-27 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589253 | T2 OAKHURST TAP 15/06A RPL INSW | 93I
LC | 122515809 | 015/007B | T2 OAKHURST TAP 15/07B RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-27 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589253 | T2 OAKHURST TAP 15/06A RPL INSW | 93I
LC | 122515970 | 015/007C | T2 OAKHURST TAP 15/07C RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-27 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589253 | T2 OAKHURST TAP 15/06A RPL INSW | 93I
LC | 122515971 | 016/000 | T2 OAKHURST TAP 16/00 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-26 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589253 | T2 OAKHURST TAP 15/06A RPL INSW | 93I
LC | 122515973 | 016/003 | T2 OAKHURST TAP 16/03 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-26 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589253 | T2 OAKHURST TAP 15/06A RPL INSW | 93I
LC | 122515974 | 016/008 | T2 OAKHURST TAP 16/08 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-31 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589253 | T2 OAKHURST TAP 15/06A RPL INSW | 93I
LC | 122515975 | 016/009 | T2 OAKHURST TAP 16/09 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-31 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589253 | T2 OAKHURST TAP 15/06A RPL INSW | 93I
LC | 122515976 | 016/010 | T2 OAKHURST TAP 16/10 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-04-02 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | RELW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589254 | T2 OAKHURST TAP 16/10 RPL INSW | 93I
LC | 122515977 | 016/011 | T2 OAKHURST TAP 16/11 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-25 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589254 | T2 OAKHURST TAP 16/10 RPL INSW | 93I
LC | 122515978 | 017/001 | T2 OAKHURST TAP 17/01 RPL INSW | FRESNO | ETL.1252.POLE.NWOD | 2021-12-23 | 2021-12-21 | 2022-03-31 | 2022-12-21 | 2022-12-21 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW PATR ACCM COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31589254 | T2 OAKHURST TAP 16/10 RPL INSW | 93I
LC | 122533739 | 020/561 | COLGATE-ALLEGHANY 20/561 RPR SWTCH | SACTO | ETL.6470.SWIT | 2021-12-31 | 2021-12-31 | 2022-06-13 | 2022-06-29 | 2022-06-30 | On-time | 623 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW NONR COMP OH FMOB TR3 PRTO | Out of Adjustment | Switch | Repair | 45105845 | COLGATE-ALLEGHANY 20/561 RPR SWTCH | ICE
LC | 122782417 | 000/002B | T3 MORAGA-LAKEWOOD 000/002B RMV VEG | CONCORD | ETL.3741.POLE.NWOD | 2022-01-21 | 2022-01-21 | 2022-07-26 | 2022-07-20 | 2022-07-21 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Trim
LC | 122885701 | 006/005 | T2 DI CHOWCHILLA-KERCKHOFF 6/5R CMPLTD | FRESNO | ETL.1250.POLE.STPS | 2022-01-26 | 2021-05-28 | 2022-06-09 | 2022-05-28 | 2022-05-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31581055 | T2 DI CHOWCHILLA-KERCKHOFF 7/4 RPL STRW | 70Y
LC | 122885705 | 006/005 | T2 DI CHOWCHILLA-KERCKHOFF 6/5C CMPLTD | FRESNO | ETL.1250.POLE.STPS | 2022-01-26 | 2021-05-28 | 2022-06-09 | 2022-05-28 | 2022-05-28 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31581055 | T2 DI CHOWCHILLA-KERCKHOFF 7/4 RPL STRW | 70Y
LC | 122890987 | 008/060 | T3 DI GRN VLLY-LLAGAS 8/60 RPR HRDD | MOSSLNDG | ETL.1720.POLE.WOOD | 2022-01-27 | 2022-01-27 | 2022-08-17 | 2022-07-26 | 2022-07-27 | Late | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCL COMP OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45376268 | T3 DI GRN VLLY-LLAGAS 8/60 RPR HRDD | ICW
LC | 122924352 | 019/108 | T3 EI PARKWAY-MORAGA 19/108 RMV VEG | CONCORD | ETL.5930.TOWR | 2022-02-04 | 2022-02-04 | 2022-07-25 | 2022-08-03 | 2022-08-04 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 122939198 | 095/000 | T2 DI HUMBOLDT-TRINITY WP 95/0R RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2022-02-07 | 2021-07-12 | 2022-06-02 | 2022-07-12 | 2022-07-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31591951 | T2 DI HUMBOLDT-TRINITY WP 95/0L RPL STRW | 70Y
LC | 122939741 | 095/000 | T2 DI HUMBOLDT-TRINITY WP 95/0C RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2022-02-07 | 2021-07-12 | 2022-06-02 | 2022-07-12 | 2022-07-12 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31591951 | T2 DI HUMBOLDT-TRINITY WP 95/0L RPL STRW | 70Y
LC | 122950571 | 021/120 | T3 DI PARKWAY-MORAGA 21/120 RMV VEG | CONCORD | ETL.5930.TOWR | 2022-02-09 | 2022-02-05 | 2022-07-25 | 2022-08-04 | 2022-08-05 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 122988382 | 022/091 | T3 EI DIABLO-MIDWAY #2 22/091 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2022-02-16 | 2022-02-16 | 2022-06-23 | 2022-08-15 | 2022-08-16 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45354327 | T3 EI DIABLO-MIDWAY #2 22/091 RPR GYWS | ICS
LC | 123053075 | 021/251 | T2 EI DRUM-SUMMIT#2 21/251R RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2022-03-04 | 2021-05-27 | 2022-07-12 | 2022-05-27 | 2022-05-27 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31545493 | T2 DI DRUM-SUMMIT #2 20/242R RPL STRWC | 70Y
LC | 123053124 | 009/107 | T2 DI DRUM-SUMMIT #2 9/107R RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2022-03-04 | 2021-06-08 | 2022-07-26 | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543771 | T3 DI DRUM-SUMMIT #2 0/5C RPL STRW | 70Y
LC | 123054368 | 020/231 | T3 IGNACIO-BLNS #2 20/231 RPL POLE | LAKEVLLE | ETL.7180.POLE.WOOD | 2022-03-04 | 2022-03-03 | 2022-06-24 | 2022-08-30 | 2022-09-03 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31597899 | T3 IGNACIO-BLNS #2 20/231 RPL POLE | 70Y
LC | 123091662 | 003/024 | T3 DI TGR CRK-VLLY SPRNGS 3/24 RPR INSS | VICTOR | ETL.5790.INSL.CERA | 2022-03-11 | 2022-03-10 | 2022-07-12 | 2022-09-06 | 2022-09-10 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45212705 | T3 DI TGR CRK-VLLY SPRNGS 3/24 RPR INSS | ICS
LC | 123149449 | 009/002 | T3 POTTER VALLEY-WILLITS 09/02 RPR GYWW | WILLITS | ETL.7820.POLE.WOOD | 2022-03-18 | 2022-03-10 | 2022-06-15 | 2022-09-06 | 2022-09-10 | On-time | ICX | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45242311 | T3 POTTER VALLEY-WILLITS 09/02 RPR GYWW | ICX
LC | 123156237 | 007/058 | T3 DI TIGR CREK-VALY SPRNGS 7/58 RMV VEG | VICTOR | ETL.5790.TOWR | 2022-03-19 | 2022-03-16 | 2022-04-13 | 2022-09-12 | 2022-09-16 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123177017 | T052 | T3 DI MIDWAY-SNT MR (12KV) T052 RPL HRDT | PISMOBCH | ETL.9240.TOWR | 2022-03-23 | 2022-03-17 | 2022-05-17 | 2022-09-13 | 2022-09-17 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45307965 | T3 DI MIDWAY-SNT MR (12KV) T052 RPL HRDT | ICQ
LC | 123178403 | 003/012 | T3 WSHON-SN JQUIN #3 3/12 REFRAME | FRESNO | ETL.9340.POLE.NWOD | 2022-03-24 | 2022-03-24 | 2022-04-30 | 2022-09-20 | 2022-09-24 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31599446 | T3 WSHON-SN JQUIN #3 3/12 REFRAME | 93E
LC | 123180794 | T049 | T3 DI MDWY-SNT MR (12KV) T049 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2022-03-24 | 2022-03-16 | 2022-08-01 | 2022-09-12 | 2022-09-16 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 123181014 | T065 | T3 EI MIDWAY-SANTA MARIA T65 BENT STEEL | PISMOBCH | ETL.9240.TOWR | 2022-03-24 | 2022-03-24 | 2022-07-14 | 2022-09-20 | 2022-09-24 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45381051 | T3 EI MIDWAY-SANTA MARIA T65 BENT STEEL | ICQ
LC | 123184135 | T042 | T3 DI MIDWY-SNT MR (12KV) T42 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2022-03-24 | 2022-03-18 | 2022-05-08 | 2022-09-14 | 2022-09-18 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 123184455 | T045 | T3 DI MDWY-SNT MR (12KV) T45 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2022-03-24 | 2022-03-17 | 2022-08-01 | 2022-09-13 | 2022-09-17 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW COMP OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 123195620 | 016/081 | T3 DI MNTA VSTA CYOTE 16/81 RPR SHLS | MOSSLNDG | ETL.5090.TOWR | 2022-03-25 | 2022-03-19 | 2022-05-14 | 2022-09-15 | 2022-09-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45388670 | T3 DI MNTA VSTA CYOTE 16/81 RPR SHLS | ICS
LC | 123196346 | :009/000 | T3 DI FULTON-CALISTOGA :09/00 RPR STRW | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-03-26 | 2022-03-21 | 2022-05-17 | 2022-09-17 | 2022-09-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45300047 | T3NT EI FULTON-CALISTOGA :8/8 RMV DBRS | ICW
LC | 123197860 | 001/008 | T3 DI MRGGA-SAN LNDRO #1 1/8 RMV VEG | CONCORD | ETL.2770.TOWR | 2022-03-26 | 2022-03-22 | 2022-07-25 | 2022-09-18 | 2022-09-22 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123210402 | 019/004 | T3 DI MONTE RIO-FORT ROSS 19/04 RPR SPLW | LAKEVLLE | ETL.6979.INSL.NCER | 2022-03-29 | 2022-03-24 | 2022-04-19 | 2022-09-20 | 2022-09-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW ACCL COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45258510 | T3 DI MNTE RIO-FRT ROSS 17/2C RPR GYWW | ICW
LC | 123210472 | 006/049 | T3 DI TIGER CREEK-ELECTRA 6/49 RMV VEG | VICTOR | ETL.5780.TOWR | 2022-03-29 | 2022-03-15 | 2022-06-23 | 2022-09-11 | 2022-09-15 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW CNCL OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123223208 | 025/107 | T3 DI EXCHQER-INDN FLT 25/107 COTR KEY | FRESNO | ETL.8650.POLE.NWOD | 2022-03-31 | 2022-03-25 | 2022-07-13 | 2022-09-21 | 2022-09-25 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45238906 | T3 DI EXCHQER-INDN FLT 25/107 COTR KEY | ICS
LC | 123226920 | 022/112 | T3 DI RND MNT-TBL MNT #2 22/112 RPL INSS | TABLEMTN | ETL.6070.INSL | 2022-04-01 | 2022-03-29 | 2022-05-18 | 2022-09-25 | 2022-09-29 | On-time | 532 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31600263 | T3 DI RND MNT-TBL MNT #2 RPL INSS | 93K
LC | 123236418 | T050 | T3 DI MDWY SNT MR T050 UNBURY | PISMOBCH | ETL.9240.TOWR | 2022-04-02 | 2022-03-30 | 2022-05-06 | 2022-09-26 | 2022-09-30 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45285307 | T3 DI MDWY SNT MR T050 UNBURY | ICQ
LC | 123236967 | 003/041 | T3 EI DRUM-SUMMIT #2 3/41L RPR POLE | SACTO | ETL.1450.POLE.WDPS | 2022-04-02 | 2022-04-02 | 2022-05-31 | 2022-09-29 | 2022-10-02 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45388780 | T3 EI DRUM-SUMMIT #2 3/41L RPR POLE | ICW
LC | 123237023 | 003/034 | T3 EI DRUM-SUMMIT #2 3/34L RPR POLE | SACTO | ETL.1450.POLE.WDPS | 2022-04-02 | 2022-04-02 | 2022-06-12 | 2022-09-29 | 2022-10-02 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45401879 | T3 EI DRUM-SUMMIT #2 3/34L RPR POLE | ICW
LC | 123238648 | T090 | T3 DI MDWY SNT MRA T090 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2022-04-04 | 2022-03-31 | 2022-07-13 | 2022-09-27 | 2022-09-30 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123239603 | 005/061 | T3 EI SNTH LN PCFC 5/61 RPL STRW | METCALF | ETL.7575.POLE.WOOD | 2022-04-04 | 2022-04-04 | 2022-11-04 | 2022-10-01 | 2022-10-04 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31602590 | T3 EI SNTH LN PCFC 5/61 RPL STRW | 70Y
LC | 123245539 | 021/005 | T3 DI MNTE RIO-FRT RSS 21/5 RPR POLE | LAKEVLLE | ETL.6979.POLE.WDPS | 2022-04-05 | 2022-03-25 | 2022-04-19 | 2022-09-21 | 2022-09-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45258510 | T3 DI MNTE RIO-FRT ROSS 17/2C RPR GYWW | ICW
LC | 123249304 | 001/005 | T3 EI DIABLO-MIDWAY #2 1/5 RMV VEG | PISMOBCH | ETL.5970.TOWR | 2022-04-05 | 2022-04-05 | 2022-09-15 | 2022-10-02 | 2022-10-05 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123252183 | 021/003 | T3 DI MONTE RIO-FORT ROSS 21/3 RPR POLE | LAKEVLLE | ETL.6979.POLE.WOOD | 2022-04-05 | 2022-03-25 | 2022-04-19 | 2022-09-21 | 2022-09-25 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW COMP OH TR3 AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45258510 | T3 DI MNTE RIO-FRT ROSS 17/2C RPR GYWW | ICW
LC | 123279407 | 005/126 | T3 EI DRM-GRS VLY-WMR 5/126 RMV VEG | SACTO | ETL.6760.POLE.WOOD | 2022-04-09 | 2022-04-09 | 2022-10-28 | 2022-10-06 | 2022-10-09 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Trim
LC | 123297709 | 002/017 | T3 MRGA-SN LNDRO #3 2/17 RPL HRDT | CONCORD | ETL.2790.INSL | 2022-04-11 | 2022-04-11 | 2022-04-28 | 2022-10-08 | 2022-10-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW OTHR REMT NOAC CLR COMP OH TR3 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair | 45261503 | T3 MRGA-SN LNDRO #3 2/17 RPL HRDT | ICQ
LC | 123303674 | 007/032 | T3 EI MORRO BAY-TEMPLETON 7/032 MASTIC | PISMOBCH | ETL.5933.TOWR | 2022-04-12 | 2022-04-12 | 2022-05-19 | 2022-10-09 | 2022-10-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45302346 | T3 EI MORRO BAY-TEMPLETON 7/032 MASTIC | ICQ
LC | 123308004 | 001/021 | T3 DI ORO FNO TAP 1/021 RPR INSW | TABLEMTN | ETL.6721.INSL | 2022-04-12 | 2022-04-06 | 2022-04-18 | 2022-10-03 | 2022-10-06 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123310993 | X001/006 | T3 EI DIABLO-MESA X0/6 CLEAR ROAD | PISMOBCH | ETL.4620.TOWR | 2022-04-12 | 2022-04-12 | 2022-07-05 | 2022-10-09 | 2022-10-12 | On-time | 932 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | Brush Fuel | Road | Remove | 45321700 | T3 EI DIABLO-MESA X0/6 CLEAR ROAD | CHS
LC | 123312072 | X001/009 | T3 EI DIABLO-MESA X0/9 RPR ROAD | PISMOBCH | ETL.4620.TOWR | 2022-04-12 | 2022-04-12 | 2022-07-05 | 2022-10-09 | 2022-10-12 | On-time | 932 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Road | Repair | 45321700 | T3 EI DIABLO-MESA X0/6 CLEAR ROAD | CHS
LC | 123313253 | 000/005 | T3 DI CNTRVLLE-TBL MTN 0/5 RPR STRW | TABLEMTN | ETL.6320.POLE.NWOD | 2022-04-12 | 2022-04-04 | 2022-04-25 | 2022-10-01 | 2022-10-04 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45349169 | T3 DI CNTRVLLE-TBL MTN 0/5 RPR STRW | ICW
LC | 123313611 | T-114 | T3 DI MIDWAY-SANTA MARIA T-114 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2022-04-12 | 2022-04-07 | 2022-07-21 | 2022-10-04 | 2022-10-07 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 123318355 | X002/014 | T3 EI DIABLO-MESA X002/014 RPR ROAD | PISMOBCH | ETL.4620.TOWR | 2022-04-13 | 2022-04-13 | 2022-06-23 | 2022-10-10 | 2022-10-13 | On-time | 932 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Road | Repair | 45321700 | T3 EI DIABLO-MESA X0/6 CLEAR ROAD | CHS
LC | 123319007 | 001/020 | T3 DI DRUM-HIGGINS 1/20L RPL HRDW | SACTO | ETL.4393.POLE.WDPS | 2022-04-13 | 2022-04-02 | 2022-06-28 | 2022-09-29 | 2022-10-02 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45415764 | T3 DI DRUM-HIGGINS 1/20L RPL HRDW | ICW
LC | 123319482 | X003/018 | T3 EI DIABLO-MESA X003/018 RPR ROAD | PISMOBCH | ETL.4620.TOWR | 2022-04-13 | 2022-04-13 | 2022-06-24 | 2022-10-10 | 2022-10-13 | On-time | 932 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Road | Repair | 45321700 | T3 EI DIABLO-MESA X0/6 CLEAR ROAD | CHS
LC | 123320935 | 002/013 | T3 DI SOBRANTE-G #2 002/013 HANGER | CONCORD | ETL.3730.INSL.CERA | 2022-04-13 | 2022-03-31 | 2022-07-07 | 2022-09-27 | 2022-09-30 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 45269077 | T3 DI SOBRANTE-G #2 002/013 HANGER | ICQ
LC | 123325531 | 020/001 | T3 DI MNT RIO-FRT RSS 20/1 RPR INSW | LAKEVLLE | ETL.6979.INSL.NCER | 2022-04-13 | 2022-04-07 | 2022-04-19 | 2022-10-04 | 2022-10-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45260209 | T3 DI MNT RIO-FRT RSS 20/1 RPR INSW | ICW
LC | 123330315 | X005/023 | T3 EI MORRO BAY-DIABLO X5/23 COTTER | PISMOBCH | ETL.5260.INSL.NCER | 2022-04-14 | 2022-04-14 | 2022-07-08 | 2022-10-11 | 2022-10-14 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45370362 | T3 EI MORRO BAY-DIABLO X5/23 COTTER | ICS
LC | 123338195 | B024/540 | T3 EI DRM-GRS VLY-WMR B24/540 RMV VEG | SACTO | ETL.6760.POLE.NWOD | 2022-04-15 | 2022-04-15 | 2022-08-03 | 2022-10-12 | 2022-10-15 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123354676 | 008/074 | T3 EI MIDDLE FORK-GLD HILL 8/74 RPR INSW | SACTO | ETL.5140.INSL.NCER | 2022-04-18 | 2022-04-18 | 2022-10-13 | 2022-10-15 | 2022-10-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 45593291 | T3 EI MIDDLE FORK-GLD HILL 8/74 RPR INSW | ICW
LC | 123359839 | 006/081 | T3 DI GRN VLLY-CAMP EVERS 6/81L RPL POLE | MOSSLNDG | ETL.1710.POLE.STPS | 2022-04-18 | 2022-04-14 | 2022-04-26 | 2022-10-11 | 2022-10-14 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31510657 | GREEN VALLEY-CAMP EVERS 6/81 RPL POLE | 70Y
LC | 123359923 | 001/017 | T3 DI SBRNT-GRZLY CLRMNT #2 1/17 RMV VEG | CONCORD | ETL.3750.POLE.NWOD | 2022-04-18 | 2022-04-04 | 2022-07-22 | 2022-10-01 | 2022-10-04 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW CNCL OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Trim
LC | 123368030 | 002/028 | T3 EI GYSRS #3-CLVRDLE 2/28 COTTER | LAKEVLLE | ETL.1650.INSL.NCER | 2022-04-19 | 2022-04-19 | 2022-10-11 | 2022-10-16 | 2022-10-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP PGEA COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 45449991 | T3 EI GYSRS #3-CLVRDLE 2/28 COTTER | ICW
LC | 123371284 | 006/078 | T3 DI GRN VLLY-CMP EVRS 6/78L RMV VEG | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-04-19 | 2022-04-14 | 2022-10-24 | 2022-10-11 | 2022-10-14 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 123375554 | 003/038 | T3 EI GEYSERS #3-CLOVRDALE 3/38 RPL STRW | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-04-20 | 2022-04-20 | 2022-10-11 | 2022-10-17 | 2022-10-20 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31614662 | T3 EI GEYSERS #3-CLOVRDALE 3/38 RPL STRW | 70Y
LC | 123394310 | 014/002 | T3 DI MONTE RIO FLTN 14/2 RPR INSW | LAKEVLLE | ETL.7630.INSL.NCER | 2022-04-22 | 2022-04-07 | 2022-06-29 | 2022-10-04 | 2022-10-07 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45137270 | T3NT DI MONTE RIO-FULTON 14/02 RMV BUTT | ICW
LC | 123399121 | 004/031 | T3 DI TGR CRK VLY SPRNGS 4/31 RMV VEGN | VICTOR | ETL.5790.TOWR | 2022-04-23 | 2022-04-08 | 2022-08-17 | 2022-10-05 | 2022-10-08 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123414119 | 009/095 | T2 DI PIT #5-ROUND MTN #2 9/95R RPL POLE | TABLEMTN | ETL.5430.POLE.WDPS | 2022-04-25 | 2021-07-06 | 2022-06-13 | 2022-07-06 | 2022-07-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | REGW COMP OH FMOB TR2 AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31601295 | EI T2 PIT #5-ROUND MTN #2 7/72 RPL STRW | 70Y
LC | 123430393 | 007/060 | T3 EI ATASCADERO-CAYUCOS 7/60 RPR CNDW | PISMOBCH | ETL.8480.INSL.NCER | 2022-04-26 | 2022-04-26 | 2022-05-11 | 2022-10-23 | 2022-10-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Conductor-Wood | Repair | 45291319 | T3 EI ATASCADERO-CAYUCOS 7/60 RPR CNDW | ICW
LC | 123436180 | 023/005 | T3 EI MPLE CRK-HPA 23/5 RMV BRSH | EUREKA | ETL.7490.POLE.NWOD | 2022-04-27 | 2022-04-27 | 2022-07-15 | 2022-10-24 | 2022-10-27 | On-time | 932 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | Brush Fuel | Road | Remove | 45191000 | MAPLE CREEK-HOOPA 24/0 RPR RD | CHS
LC | 123439132 | 010/041 | T3 DI MRRO BY-TMPLTN 10/41 RPR INSS | PISMOBCH | ETL.5933.INSL | 2022-04-27 | 2022-04-27 | 2022-06-24 | 2022-10-24 | 2022-10-27 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45333297 | T3 DI MRRO BY-TMPLTN 10/41 RPR INSS | ICS
LC | 123451582 | 013/008 | T3 EI LAURELES-OTTER 13/008 RMV VEG | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-04-28 | 2022-04-28 | 2022-10-20 | 2022-10-25 | 2022-10-28 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123455624 | 009/093 | T3 DI DRM RIO OSO #1 9/93 INS STEP | SACTO | ETL.1420.TOWR | 2022-04-29 | 2022-04-12 | 2022-05-25 | 2022-10-09 | 2022-10-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45315536 | T3 DI DRM RIO OSO #1 9/93 INS STEP | ICQ
LC | 123468345 | 002/035 | T3 DI GEYSERS #3-CLOVERDLE 2/35 RPL HRDW | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-04-30 | 2022-04-18 | 2022-10-11 | 2022-10-15 | 2022-10-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45449992 | T3 DI GEYSERS #3-CLOVERDLE 2/35 RPL HRDW | ICW
LC | 123468346 | 002/035 | T3 DI GEYSERS #3-CLOVERDLE 2/35 RPL ANCW | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-04-30 | 2022-04-18 | 2022-10-11 | 2022-10-15 | 2022-10-18 | On-time | 637 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31615346 | T3 DI GEYSERS #3-CLOVERDLE 2/35 RPL ANCW | 93E
LC | 123473040 | 011/007 | T3 DI MONTE RIO-FULTON 11/7 RPR INSW | LAKEVLLE | ETL.7630.INSL.CERA | 2022-05-02 | 2022-04-11 | 2022-07-27 | 2022-10-08 | 2022-10-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45137511 | T3 DI MONTE RIO-FULTON 11/7 RPR ANCW | ICW
LC | 123474815 | 003/037 | T3 DI GEYSERS #3-CLVRDL 3/37 RPR GYWW | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-05-02 | 2022-04-18 | 2022-10-11 | 2022-10-15 | 2022-10-18 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45449993 | T3 DI GEYSERS #3-CLVRDL 3/37 RPR GYWW | ICW
LC | 123475324 | 001/022 | T3 DI GYSR #3-CLVRDLE 1/22 RPR STRW | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-05-02 | 2022-04-19 | 2022-10-06 | 2022-10-16 | 2022-10-19 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45449990 | T3 DI GYSR #3-CLVRDLE 1/22 RPR STRW | ICW
LC | 123480349 | 009/090 | T3 DI GREEN VALLEY-PL SWT 9/90 RPR GYWW | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-05-02 | 2022-04-14 | 2022-08-24 | 2022-10-11 | 2022-10-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45376277 | T3 DI GREEN VALLEY-PL SWT 9/90 RPR GYWW | ICW
LC | 123480403 | 009/090 | T3 DI GREEN VALLEY-PL SWT 9/90 RPR GYWW | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-05-02 | 2022-04-14 | 2022-08-24 | 2022-10-11 | 2022-10-14 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45376278 | T3 DI GREEN VALLEY-PL SWT 9/90 RPR GYWW | ICW
LC | 123485620 | 027/132 | T3 DI XCHQR-INDN FLT 27/132 COTR KEY | FRESNO | ETL.8650.INSL.CERA | 2022-05-03 | 2022-04-27 | 2022-07-13 | 2022-10-24 | 2022-10-27 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45279391 | T3 DI XCHQR-INDN FLT 27/132 COTR KEY | ICS
LC | 123489332 | 005/064 | T3 DI DRUM-SUMMIT #2 #2 5/64R RPR STRW | SACTO | ETL.1450.POLE.WDPS | 2022-05-03 | 2022-04-28 | 2022-06-11 | 2022-10-25 | 2022-10-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45349702 | T3 DI DRUM-SUMMIT #2 #2 5/64R RPR STRW | ICW
LC | 123496580 | 009/097 | T3 EI GRN VLLY-CAMP EVERS 9/97 RPL HRDW | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-05-04 | 2022-05-04 | 2022-09-14 | 2022-10-31 | 2022-11-04 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45414195 | T3 EI GRN VLLY-CAMP EVERS 9/97 RPL HRDW | ICW
LC | 123519142 | B009/087 | T3 DRUM-HIGGINS B9/87 RMV CONS | SACTO | ETL.4393.TOWR | 2022-05-05 | 2022-05-05 | 2022-05-29 | 2022-11-01 | 2022-11-05 | On-time | 673 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO FRAB NTDE | Idle | Structure-Steel | Remove | 31603719 | T2 DRUM-HIGGINS 13/127 RMV CONS | 93J
LC | 123526234 | 004/098 | T3 DI CLGT-CHLLNG 4/098 RPL INSW | SACTO | ETL.6480.INSL.CERA | 2022-05-06 | 2022-05-02 | 2022-08-25 | 2022-10-29 | 2022-11-02 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31614167 | T3 DI CLGT-CHLLNG 4/098 RPL INSW | 93I
LC | 123526332 | 002/024 | T3 EI GREEN VALLEY-LLAGAS 2/24R RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-05-06 | 2022-05-06 | 2022-09-22 | 2022-11-02 | 2022-11-06 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545458 | T3 DI GREEN VALLEY-LLAGAS 2/24 RPL STRW | 70Y
LC | 123535486 | T-115 | T3 DI IDWAY-SANTA MARIA T-115 UNBURY | PISMOBCH | ETL.9240.TOWR | 2022-05-07 | 2022-05-03 | 2022-08-29 | 2022-10-30 | 2022-11-03 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45432527 | T3 DI IDWAY-SANTA MARIA T-115 UNBURY | ICQ
LC | 123546421 | 003/020 | T3 DI SBRNTE G #1 3/020 RMV VEG | CONCORD | ETL.3720.TOWR | 2022-05-09 | 2022-04-19 | 2022-07-22 | 2022-10-16 | 2022-10-19 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW CNCL OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123547113 | 002/011 | T3 DI DIABLO-MDWY #2 2/11 INS STEP | PISMOBCH | ETL.5970.TOWR | 2022-05-09 | 2022-05-06 | 2022-06-03 | 2022-11-02 | 2022-11-06 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45364257 | T3 DI DIABLO-MDWY #2 2/11 INS STEP | ICQ
LC | 123564309 | 019/514 | T3 DI COLGATE-ALLEGHANY 19/514 RPR POLE | SACTO | ETL.6470.POLE.WOOD | 2022-05-10 | 2022-04-29 | 2022-06-15 | 2022-10-26 | 2022-10-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45405772 | T3 DI COLGATE-ALLEGHANY 19/514 RPR POLE | ICW
LC | 123564445 | 019/514 | T3 DI COLGATE-ALLEGHANY 19/514 RPL HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-05-10 | 2022-04-29 | 2022-06-13 | 2022-10-26 | 2022-10-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45428907 | T3 DI COLGATE-ALLEGHANY 19/514 RPL HRDW | ICW
LC | 123566872 | 005/060 | T3 EI GEYSERS #3-CLOVERDL 5/60R RPR STRW | LAKEVLLE | ETL.1650.POLE.WDPS | 2022-05-11 | 2022-05-11 | 2022-10-16 | 2022-11-07 | 2022-11-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45449999 | T3 EI GEYSERS #3-CLOVERDL 5/60R RPR STRW | ICW
LC | 123568146 | 009/066 | T3 DI GREEN VALLEY-LLAGAS 9/66 RMV VEG | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-05-11 | 2022-04-21 | 2022-08-30 | 2022-10-18 | 2022-10-21 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | Overgrown | Vegetation | Trim
LC | 123568287 | 026/201 | T2 DI MDDE FRK-GLD HLL 026/201R RPL STRW | SACTO | ETL.5140.POLE.WDPS | 2022-05-11 | 2021-06-30 | 2022-10-02 | 2022-06-30 | 2022-06-30 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31546023 | T2 DI MDD FRK-GLD HLL 026/201 RPL STRW | 70Y
LC | 123568512 | 024/192 | T2 DI MDDLE FK GLN HLL 24/192R RPL STRW | SACTO | ETL.5140.POLE.WDPS | 2022-05-11 | 2021-07-05 | 2022-10-24 | 2022-07-05 | 2022-07-05 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546023 | T2 DI MDD FRK-GLD HLL 026/201 RPL STRW | 70Y
LC | 123568933 | 006/074 | T3 EI GEYSERS #3-CLOVERDAL 6/74 RPR POLE | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-05-11 | 2022-05-11 | 2022-10-17 | 2022-11-07 | 2022-11-11 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45450244 | T3 EI GEYSERS #3-CLOVERDAL 6/74 RPR POLE | ICW
LC | 123568981 | 006/073 | T3 EI GEYSERS #3-CLOVERDAL 6/73 RPL POLE | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-05-11 | 2022-05-11 | 2022-10-17 | 2022-11-07 | 2022-11-11 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31614662 | T3 EI GEYSERS #3-CLOVRDALE 3/38 RPL STRW | 70Y
LC | 123572149 | T072 | T3 EI MIDWAY-SANTA MARIA T072 UNBURY | PISMOBCH | ETL.9240.TOWR | 2022-05-11 | 2022-05-11 | 2022-08-25 | 2022-11-07 | 2022-11-11 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45428840 | T3 EI MIDWAY-SANTA MARIA T072 UNBURY | ICQ
LC | 123572176 | T046 | T3 EI MIDWAY-SANTA MARIA_T046 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2022-05-11 | 2022-05-11 | 2022-08-01 | 2022-11-07 | 2022-11-11 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123572184 | T096 | T3 EI MIDWAY-SANTA MARIA T096 BENT STEEL | PISMOBCH | ETL.9240.TOWR | 2022-05-11 | 2022-05-10 | 2022-08-25 | 2022-11-06 | 2022-11-10 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45429513 | T3 EI MIDWAY-SANTA MARIA T096 BENT STEEL | ICQ
LC | 123573268 | 004/109 | T3 DI DEER CREEK-DRUM 4/109 RMV STEP | SACTO | ETL.6690.POLE.NWOD | 2022-05-11 | 2022-04-29 | 2022-06-18 | 2022-10-26 | 2022-10-29 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45350868 | T3 DI DEER CREEK-DRUM 4/109 RMV STEP | ICW
LC | 123573317 | 001/016B | T3 DI DRUM-SUMMIT #2 001/016B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2022-05-11 | 2022-04-28 | 2022-06-10 | 2022-10-25 | 2022-10-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45411279 | T3 DI DRUM-SUMMIT #2 001/016B RPR GYWW | ICW
LC | 123573342 | 001/016C | T3 DI DRUM-SUMMIT #2 001/016C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2022-05-11 | 2022-04-28 | 2022-06-11 | 2022-10-25 | 2022-10-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45411461 | T3 DI DRUM-SUMMIT #2 001/016C RPR GYWW | ICW
LC | 123573392 | 014/126 | T3 DI GREEN VLY-PL SWT 14/126 RMV VEG | MOSSLNDG | ETL.1730.POLE.WOOD | 2022-05-11 | 2022-04-21 | 2022-08-12 | 2022-10-18 | 2022-10-21 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE ACCL CNCL OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123573637 | 000/006B | T3 DI DRUM-SUMMIT #2 000/006B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2022-05-11 | 2022-04-28 | 2022-06-09 | 2022-10-25 | 2022-10-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45411465 | T3 DI DRUM-SUMMIT #2 000/006B RPR GYWW | ICW
LC | 123582295 | 021/155 | T3 DI TRNTY CTNWD 21/155R RMV STEP | TABLEMTN | ETL.4040.POLE.STPS | 2022-05-12 | 2022-04-28 | 2022-08-22 | 2022-10-25 | 2022-10-28 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45437533 | T3 DI TRNTY CTNWD 21/155R RMV STEP | ICW
LC | 123582360 | 021/155 | T3 DI TRNTY CTNWD 21/155 RPR CNDW | TABLEMTN | ETL.4040.INSL.CERA | 2022-05-12 | 2022-04-28 | 2022-08-24 | 2022-10-25 | 2022-10-28 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Steel | Repair | 45503665 | T3 DI TRNTY CTNWD 21/155 RPR CNDW | ICS
LC | 123586649 | 008/007 | T3 DI LAURELES-OTTER 8/7 RPL HRDW | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-13 | 2022-04-21 | 2022-08-12 | 2022-10-18 | 2022-10-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45376643 | T3 DI LAURELES-OTTER 8/7 RPL HRDW | ICW
LC | 123595017 | 011/103 | T3 DI GRN VALEY-PAUL SWT 11/103 RMV VEG | MOSSLNDG | ETL.1730.POLE.WOOD | 2022-05-14 | 2022-04-22 | 2022-10-12 | 2022-10-19 | 2022-10-22 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123600045 | 005/092 | T3 EI DLT-MTN GT JCT-MTN 5/92L RPR GYWW | TABLEMTN | ETL.6750.POLE.STPS | 2022-05-15 | 2022-05-15 | 2022-07-24 | 2022-11-11 | 2022-11-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45419659 | T3 EI DLT-MTN GT JCT-MTN 5/92L RPR GYWW | ICW
LC | 123601446 | 002/027 | T3 EI MIDDLE FRK-GLD HILL 2/27L RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2022-05-15 | 2022-05-15 | 2022-11-01 | 2022-11-11 | 2022-11-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP CPUA COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45582079 | T3 EI MIDDLE FRK-GLD HILL 2/27L RPR GYWW | ICW
LC | 123601461 | 002/027 | T3 EI MIDDLE FRK-GLD HILL 2/27R RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2022-05-15 | 2022-05-15 | 2022-11-01 | 2022-11-11 | 2022-11-15 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP CPUA COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45582078 | T3 EI MIDDLE FRK-GLD HILL 2/27R RPR GYWW | ICW
LC | 123604423 | T054 | T3 DI MIDWAY-SANTA MARIA T054 RMV VEG | PISMOBCH | ETL.9240.TOWR | 2022-05-16 | 2022-05-12 | 2022-08-01 | 2022-11-08 | 2022-11-12 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 123618887 | T079 | T3 DI MIDWAY-SANTA MARIA T079 UNBURY | PISMOBCH | ETL.9240.TOWR | 2022-05-17 | 2022-05-12 | 2022-08-25 | 2022-11-08 | 2022-11-12 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45429512 | T3 DI MIDWAY-SANTA MARIA T079 UNBURY | ICQ
LC | 123624993 | 001/017A | T3 DI MID FRK-GLD HILL 1/17A RPR GYWW | SACTO | ETL.5140.POLE.NWOD | 2022-05-18 | 2022-05-12 | 2022-10-13 | 2022-11-08 | 2022-11-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45502065 | T3 DI MID FRK-GLD HILL 1/17A RPR GYWW | ICW
LC | 123633248 | 000/004 | T3 DI BURNS-LONE STAR #1 0/4 RMV VEG | MOSSLNDG | ETL.6230.POLE.NWOD | 2022-05-18 | 2022-05-13 | 2022-08-26 | 2022-11-09 | 2022-11-13 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE ACCL CNCL OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123636734 | X001/007 | T3 DI DBL MS X1/7 RPR SHLS | PISMOBCH | ETL.4620.INSL.CERA | 2022-05-19 | 2022-05-18 | 2022-05-24 | 2022-11-14 | 2022-11-18 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45312967 | T3 DI DBL MS X1/7 RPR SHLS | ICS
LC | 123642067 | 002/019 | T3 DI MIDDLE FORK-GOLD HIL 2/19 RPR GRWW | SACTO | ETL.5140.POLE.WDPS | 2022-05-19 | 2022-05-12 | 2022-10-13 | 2022-11-08 | 2022-11-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 45502068 | T3 DI MIDDLE FORK-GOLD HIL 2/19 RPR GRWW | ICW
LC | 123653134 | 014/008 | T3 EI MONTE RIO-FULTON 14/8 WASH INSU | LAKEVLLE | ETL.7630.INSL.CERA | 2022-05-20 | 2022-05-20 | 2022-08-09 | 2022-11-16 | 2022-11-20 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 45137265 | T3 DI MONTE RIO-FULTN-FLTN 14/8 RPR SPLW | ICW
LC | 123680896 | 013/064 | T3 DI MOSS LDNG-MTCALF 013/064 RMV VEG | MOSSLNDG | ETL.6050.TOWR | 2022-05-24 | 2022-05-23 | 2022-10-21 | 2022-11-19 | 2022-11-23 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE ACCM COMP OH TR3 PRTO AIR FRAB NTDE | Overgrown | Vegetation | Trim
LC | 123683452 | 006/066 | T3 DI DRUM-RIO OSO #2 006/066 RPL SPLS | SACTO | ETL.1430.INSL.NCER | 2022-05-24 | 2022-05-19 | 2022-08-02 | 2022-11-15 | 2022-11-19 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Replace | 45317471 | T3 DI DRUM-RIO OSO #2 006/066 RPL SPLS | ICS
LC | 123691053 | 010/283 | T3 EI CLG-ALLGHNY 10/283 RPR FENCE | SACTO | ETL.6470.POLE.WOOD | 2022-05-25 | 2022-05-25 | 2022-11-30 | 2022-11-21 | 2022-11-25 | Late | 932 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Fence / Gate | Repair
LC | 123692628 | 006/054 | T3 DI MONTA VISTA-BURNS 6/54 RMV VEG | MOSSLNDG | ETL.7590.POLE.WOOD | 2022-05-25 | 2022-05-20 | 2022-10-11 | 2022-11-16 | 2022-11-20 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123712812 | 003/069 | T3 DI BURNS-LONE STAR #2 3/69 RMV VEG | MOSSLNDG | ETL.6240.POLE.NWOD | 2022-05-27 | 2022-05-04 | 2022-10-21 | 2022-10-31 | 2022-11-04 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123714143 | 001/040 | T3 DI BURNS-LONE STAR #2 1/40 TRIM VEG | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-05-28 | 2022-05-09 | 2022-10-21 | 2022-11-05 | 2022-11-09 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW ACCH COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Trim
LC | 123715060 | 006/070 | T3 DI GEYSERS #3-CLVRDL 6/70 RPR GYWW | LAKEVLLE | ETL.1650.POLE.NWOD | 2022-05-28 | 2022-05-27 | 2022-10-13 | 2022-11-23 | 2022-11-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45450243 | T3 DI GEYSERS #3-CLVRDL 6/70 RPR GYWW | ICW
LC | 123715122 | 001/013 | T3 DI MDLE FORK-GOLD HILL 1/13L RPR SHLD | SACTO | ETL.5140.POLE.WDPS | 2022-05-28 | 2022-05-12 | 2022-10-24 | 2022-11-08 | 2022-11-12 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45508791 | T3 DI MDLE FORK-GOLD HILL 1/13L RPR SHLD | ICW
LC | 123715225 | 018/000A | T3 DI OAKHURST TAP 018/000A RMV VEG | FRESNO | ETL.1252.POLE.NWOD | 2022-05-28 | 2022-05-11 | 2022-10-31 | 2022-11-07 | 2022-11-11 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123715408 | 005/058 | T3 DI GEYSERS #3-CLVRDL 5/58 RPR INSW | LAKEVLLE | ETL.1650.INSL.CERA | 2022-05-28 | 2022-05-27 | 2022-10-16 | 2022-11-23 | 2022-11-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45449997 | T3 DI GEYSERS #3-CLVRDL 5/58 RPR INSW | ICW
LC | 123715430 | 005/058 | T3 DI GEYSERS #3-CLVRDL 5/58L RPR GYWW | LAKEVLLE | ETL.1650.POLE.WDPS | 2022-05-28 | 2022-05-27 | 2022-10-16 | 2022-11-23 | 2022-11-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45449998 | T3 DI GEYSERS #3-CLVRDL 5/58L RPR GYWW | ICW
LC | 123734734 | 028/135 | T3 DI EXCHQER-INDN FLT 28/135 RMV VEG | FRESNO | ETL.8650.POLE.NWOD | 2022-06-01 | 2022-05-19 | 2022-09-01 | 2022-11-15 | 2022-11-19 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE CNCL OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123737721 | 005/061 | T3 DI GEYSERS #3-CLVRDLE 5/61L RPL HRDW | LAKEVLLE | ETL.1650.POLE.WDPS | 2022-06-02 | 2022-05-27 | 2022-10-13 | 2022-11-23 | 2022-11-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45450240 | T3 DI GEYSERS #3-CLVRDLE 5/61L RPL HRDW | ICW
LC | 123744483 | 005/065 | T3 DI GEYSRS #3-CLOVRDL 005/065 BACKFIL | LAKEVLLE | ETL.1650.POLE.NWOD | 2022-06-02 | 2022-05-26 | 2022-10-16 | 2022-11-22 | 2022-11-26 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Repair | 45450242 | T3 DI GEYSRS #3-CLOVRDL 005/065 BACKFIL | ICW
LC | 123745132 | 001/002 | T3 DI MISSION POWER TAP-01/02 RPR GYWW | LAKEVLLE | ETL.1651.POLE.NWOD | 2022-06-02 | 2022-06-02 | 2022-10-08 | 2022-11-29 | 2022-12-02 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45450246 | T3 DI MISSION POWER TAP-01/02 RPR GYWW | ICW
LC | 123747863 | 004/055 | T3 DI GEYSERS #3-CLOVERDAL 4/55 RPR POLE | LAKEVLLE | ETL.1650.POLE.WDPS | 2022-06-03 | 2022-05-27 | 2022-10-16 | 2022-11-23 | 2022-11-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45449996 | T3 DI GEYSERS #3-CLOVERDAL 4/55 RPR POLE | ICW
LC | 123748001 | 005/063 | T3 DI GEYSRS #3-CLERDALE 5/63 RMV NEST | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-06-03 | 2022-05-27 | 2022-10-14 | 2022-11-23 | 2022-11-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 45450241 | T3 DI GEYSRS #3-CLERDALE 5/63 RMV NEST | ICW
LC | 123748003 | 005/063 | T3 DI GEYSRS #3-CLERDALE 5/63 RPL INSW | LAKEVLLE | ETL.1650.INSL.CERA | 2022-06-03 | 2022-05-27 | 2022-10-14 | 2022-11-23 | 2022-11-27 | On-time | 508 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31615347 | T3 DI GEYSRS #3-CLERDALE 5/63 RPL INSW | 93I
LC | 123751931 | 002/019 | T3 DI MORAGA-CLAREMONT #1 2/19 RPR STRT | CONCORD | ETL.2700.TOWR | 2022-06-03 | 2022-06-01 | 2022-07-19 | 2022-11-28 | 2022-12-01 | On-time | 543 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45384418 | T3 DI MORAGA-CLAREMONT #1 2/19 RPR STRT | ICQ
LC | 123758106 | 000/016 | T3 DI BURNS-LONE STAR #2 0/16 RMV VEG | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-06-03 | 2022-06-01 | 2022-10-24 | 2022-11-28 | 2022-12-01 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE ACCM COMP OH XMPT TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123759352 | 000/001 | T3 DI ROLLINS TAP 0/1 RMV VEG | SACTO | ETL.6762.POLE.NWOD | 2022-06-03 | 2022-05-20 | 2022-10-20 | 2022-11-16 | 2022-11-20 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Trim
LC | 123762292 | 000/001C | T3 EI DRUM-HIGGINS 000/001C RPR GYWW | SACTO | ETL.4393.POLE.WOOD | 2022-06-04 | 2022-06-04 | 2022-06-26 | 2022-12-01 | 2022-12-04 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45415762 | T3 EI DRUM-HIGGINS 000/001C RPR GYWW | ICW
LC | 123762293 | 000/001A | T3 EI DRUM-HIGGINS 000/001A RPR GYWW | SACTO | ETL.4393.POLE.WOOD | 2022-06-04 | 2022-06-04 | 2022-06-27 | 2022-12-01 | 2022-12-04 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45415763 | T3 EI DRUM-HIGGINS 000/001A RPR GYWW | ICW
LC | 123777135 | 018/149C | T3 DI PARADISE-TBL MTN 018/149C RPL HRDW | TABLEMTN | ETL.4316.POLE.NWOD | 2022-06-07 | 2022-05-24 | 2022-10-15 | 2022-11-20 | 2022-11-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45515961 | T3 DI PARADISE-TBL MTN 018/149C RPL HRDW | ICW
LC | 123777139 | 018/149B | T3 DI PARADISE-TBL MTN 018/149B RPL HRDW | TABLEMTN | ETL.4316.POLE.NWOD | 2022-06-07 | 2022-05-24 | 2022-10-15 | 2022-11-20 | 2022-11-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45515962 | T3 DI PARADISE-TBL MTN 018/149B RPL HRDW | ICW
LC | 123778352 | ?010/007 | T3 DI SNTH LN-HLF MOON BY ?10/7 RMV VEG | METCALF | ETL.7212.POLE.NWOD | 2022-06-07 | 2022-06-02 | 2022-10-18 | 2022-11-29 | 2022-12-02 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123779666 | 018/149A | T3 DI PARADISE-TBL MTN 018/149A RPL HRDW | TABLEMTN | ETL.4316.POLE.NWOD | 2022-06-07 | 2022-05-24 | 2022-10-15 | 2022-11-20 | 2022-11-24 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45563627 | T3 DI PARADISE-TBL MTN 018/149A RPL HRDW | ICW
LC | 123788156 | 004/034 | T3 EI TGR CRK-VLLY SPRNGS 4/34 RMV VEG | VICTOR | ETL.5790.TOWR | 2022-06-08 | 2022-06-08 | 2022-07-18 | 2022-12-05 | 2022-12-08 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP CNCL OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123788678 | 005/059 | T3 EI DRUM-RIO OSO #2 005/059 RMV VEG | SACTO | ETL.1430.TOWR | 2022-06-08 | 2022-06-08 | 2022-10-28 | 2022-12-05 | 2022-12-08 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP CNCL OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Trim
LC | 123793092 | Z015/001 | T3 DI FULTON-CALISTOGA 15/001 RMV VEG | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-06-08 | 2022-05-23 | 2022-12-01 | 2022-11-19 | 2022-11-23 | Late | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE ACCH CNCL OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Trim
LC | 123793410 | 004/038 | T3 DI MIDDLE FRK-GLD HILL 4/38R RPR STRW | SACTO | ETL.5140.POLE.WDPS | 2022-06-08 | 2022-06-04 | 2022-10-20 | 2022-12-01 | 2022-12-04 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45502073 | T3 DI MIDDLE FRK-GLD HILL 4/38R RPR STRW | ICW
LC | 123797489 | 006/051 | T3 EI TIGER CRK-VALY SPNGS 6/51 RMV VEG | VICTOR | ETL.5790.TOWR | 2022-06-09 | 2022-06-09 | 2022-07-18 | 2022-12-06 | 2022-12-09 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP CNCL OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123815058 | 004/033 | T3 EI BRUNSWICK #1 TAP 4/033 RMV VEG | SACTO | ETL.1422.TOWR | 2022-06-10 | 2022-06-10 | 2022-11-07 | 2022-12-07 | 2022-12-10 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP CNCL OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123821024 | 000/001A | T3 DI ROSSMOOR #1 TAP 000/001A RMV VEG | CONCORD | ETL.5451.TOWR | 2022-06-10 | 2022-05-25 | 2022-08-19 | 2022-11-21 | 2022-11-25 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW COMP OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123827495 | ?009/010 | T3 EI SNEATH LANE-HMB ?9/10 RMV VEG | METCALF | ETL.7212.POLE.WOOD | 2022-06-12 | 2022-06-12 | 2022-10-18 | 2022-12-09 | 2022-12-12 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123827697 | 017/009 | T3 EI OAKHURST TAP 017/009 RMV VEG | FRESNO | ETL.1252.POLE.NWOD | 2022-06-12 | 2022-06-12 | 2022-10-31 | 2022-12-09 | 2022-12-12 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Trim
LC | 123844248 | 002/026 | T3 DI MDDL FRK-GLD HILL 2/026 REPULL | SACTO | ETL.5140.POLE.STPS | 2022-06-14 | 2022-06-09 | 2022-10-14 | 2022-12-06 | 2022-12-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45502066 | T3 DI MDDL FRK-GLD HILL 2/026 REPULL | ICW
LC | 123852893 | 033/166 | T3 DI FULTON-PUEBLO 033/166 CMPL | LAKEVLLE | ETL.1600.INSL.NCER | 2022-06-15 | 2022-06-08 | 2022-07-05 | 2022-12-05 | 2022-12-08 | On-time | 628 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCL COMP OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45362336 | T3 DI FULTON-PUEBLO 033/166 RPR INSS | ICS
LC | 123853529 | 014/008 | T3 DI MNTE RIO-FLTN (NF) 14/008 RPR STRW | LAKEVLLE | ETL.7630.POLE.WOOD | 2022-06-16 | 2022-05-27 | 2022-08-09 | 2022-11-23 | 2022-11-27 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE ACCM COMP OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45137265 | T3 DI MONTE RIO-FULTN-FLTN 14/8 RPR SPLW | ICW
LC | 123866235 | 004/032 | T3 EI TIGER CREEK-ELECTRA 4/32 RMV VEG | VICTOR | ETL.5780.TOWR | 2022-06-17 | 2022-06-17 | 2022-09-07 | 2022-12-14 | 2022-12-17 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123866247 | 004/033 | T3 EI TIGER CREEK-ELECTRA 4/33 RMV VEG | VICTOR | ETL.5780.TOWR | 2022-06-17 | 2022-06-17 | 2022-09-07 | 2022-12-14 | 2022-12-17 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123872648 | :000/008 | T3 DI FULTON-CALISTOGA :0/8 RPL DMPW | LAKEVLLE | ETL.6880.INSL.NCER | 2022-06-18 | 2022-06-09 | 2022-07-24 | 2022-12-06 | 2022-12-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace | 45387660 | T3 DI FULTON-CALISTOGA :0/8R RPR GYWW | ICW
LC | 123872728 | :000/008 | T3 DI FULTON-CALISTOGA :0/8R RPR GYWW | LAKEVLLE | ETL.6880.POLE.STPS | 2022-06-18 | 2022-06-09 | 2022-07-24 | 2022-12-06 | 2022-12-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45387660 | T3 DI FULTON-CALISTOGA :0/8R RPR GYWW | ICW
LC | 123872858 | 017/135 | T3 DI MDL FRK GLD HL 17/135 RPR INSW | SACTO | ETL.5140.INSL | 2022-06-18 | 2022-06-09 | 2022-10-14 | 2022-12-06 | 2022-12-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45580799 | T3 DI MDL FRK GLD HL 17/135 RPR INSW | ICW
LC | 123882614 | 000/001 | T3 EI SLY CREEK TAP 0/1L RPR GYWW | TABLEMTN | ETL.4221.POLE.STPS | 2022-06-20 | 2022-06-20 | 2022-07-22 | 2022-12-17 | 2022-12-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45419650 | T3 EI SLY CREEK TAP 0/1L RPR GYWW | ICW
LC | 123882616 | 000/001 | T3 EI SLY CREEK TAP 0/1R RPR GYWW | TABLEMTN | ETL.4221.POLE.STPS | 2022-06-20 | 2022-06-20 | 2022-07-22 | 2022-12-17 | 2022-12-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45419651 | T3 EI SLY CREEK TAP 0/1R RPR GYWW | ICW
LC | 123882620 | 000/001 | T3 EI SLY CREEK TAP 0/1C RPR GYWW | TABLEMTN | ETL.4221.POLE.STPS | 2022-06-20 | 2022-06-20 | 2022-07-22 | 2022-12-17 | 2022-12-20 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45419640 | T3 EI SLY CREEK TAP 0/1C RPR GYWW | ICW
LC | 123891629 | 004/041 | T3 DI MDDL FRK-GLD HILL 4/41L RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2022-06-21 | 2022-06-13 | 2022-10-20 | 2022-12-10 | 2022-12-13 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45502076 | T3 DI MDDL FRK-GLD HILL 4/41 RPR GYWW | ICW
LC | 123902115 | 016/139 | T2 DI CRAG VIEW-CASCADE 16/139L RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2022-06-23 | 2021-06-09 | 2022-09-12 | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31552992 | T2 EI CRAG VIEW-CASCDE 18/154R RPL STRW | 70Y
LC | 123911997 | 002/036 | T3 DI BURNS-LONE STAR #1 002/036 RMV VEG | MOSSLNDG | ETL.6230.POLE.NWOD | 2022-06-24 | 2022-06-01 | 2022-10-21 | 2022-11-28 | 2022-12-01 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE ACCL COMP OH XMPT TR3 PRTO AIR | Overgrown | Vegetation | Trim
LC | 123916073 | 006/056 | T3 DI MIDDLE FRK-GLD HIL 6/56L RPR GYWW | SACTO | ETL.5140.POLE.WDPS | 2022-06-24 | 2022-06-01 | 2022-10-13 | 2022-11-28 | 2022-12-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45502063 | T3 DI MIDDLE FRK-GLD HIL 6/56L RPR GYWW | ICW
LC | 123916077 | 006/056 | T3 DI MIDDLE FRK-GLD HIL 6/56R RPR GRWW | SACTO | ETL.5140.POLE.WDPS | 2022-06-24 | 2022-06-01 | 2022-10-13 | 2022-11-28 | 2022-12-01 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 45502069 | T3 DI MIDDLE FRK-GLD HIL 6/56R RPR GRWW | ICW
LC | 123919213 | 002/000 | T3 DI BEARDSLEY TAP 2/0 RMV VEG | VICTOR | ETL.1401.POLE.STPS | 2022-06-24 | 2022-06-06 | 2022-07-08 | 2022-12-03 | 2022-12-06 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW FIRE CNCL OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123924902 | 003/007 | T3 DI FULTON-CALISTOGA 3/7 RPR GYWW | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-06-25 | 2022-05-31 | 2022-10-19 | 2022-11-27 | 2022-11-30 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45456818 | T3 DI FULTON-CALISTOGA 3/7 RPR GYWW | ICW
LC | 123929621 | 013/011 | T3 EI LAURELES-OTTER 013/011 RMV VEG | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-06-26 | 2022-06-26 | 2022-10-20 | 2022-12-23 | 2022-12-26 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123934991 | 003/034 | T3 DI MID FRK-GLD HILL 3/34L RPL HRDD | SACTO | ETL.5140.POLE.STPS | 2022-06-27 | 2022-06-10 | 2022-10-20 | 2022-12-07 | 2022-12-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45502077 | T3 DI MID FRK-GLD HILL 3/34L RPL HRDD | ICW
LC | 123934992 | 003/034 | T3 DI MID FRK-GLD HILL 3/34L RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2022-06-27 | 2022-06-10 | 2022-10-20 | 2022-12-07 | 2022-12-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45502078 | T3 DI MID FRK-GLD HILL 3/34L RPR GYWW | ICW
LC | 123934998 | 003/031 | T3 DI MDDLE FRK-GLD HILL 3/31R RPR CRSW | SACTO | ETL.5140.POLE.STPS | 2022-06-27 | 2022-06-10 | 2022-10-20 | 2022-12-07 | 2022-12-10 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45502079 | T3 DI MDDLE FRK-GLD HILL 3/31R RPR CRSW | ICW
LC | 123967209 | 000/001 | T3 DI TIGR CREEK-VALY SPRNGS 0/1 RMV VEG | VICTOR | ETL.5790.TOWR | 2022-06-30 | 2022-06-06 | 2022-07-20 | 2022-12-03 | 2022-12-06 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW CNCL OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 124053904 | 000/005 | T3 DI MDDL FORK-GLD HLL 0/5R RPR POLE | SACTO | ETL.5140.POLE.WDPS | 2022-07-11 | 2022-06-21 | 2022-10-22 | 2022-12-18 | 2022-12-21 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45542108 | T3 DI MDDL FORK-GLD HLL 0/5R RPR POLE | ICW
LC | 124072640 | 025/300 | T2 DI DRUM-SUMMIT #1 25/300R RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2022-07-13 | 2021-06-18 | 2022-09-10 | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31608673 | T2 DI DRUM-SUMMIT #1 25/300 RPL STRW | 70Y
LC | 124113614 | 001/018 | T3 DI MIDDLE FORK-GOLD HIL 1/18 RPR WDPK | SACTO | ETL.5140.POLE.WDPS | 2022-07-19 | 2022-06-09 | 2022-10-13 | 2022-12-06 | 2022-12-09 | On-time | 630 | E - Schd Compl Yr 0 | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45502064 | T3 DI MIDDLE FORK-GOLD HIL 1/18 RPR WDPK | ICW
LC | 124130108 | 005/004 | T3 DI DONNELLS-MI-WUK 5/4 RMV VEG | VICTOR | ETL.1400.TOWR | 2022-07-20 | 2022-06-25 | 2022-07-22 | 2022-12-22 | 2022-12-25 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW COMP OH TR3 AIR FRAB | Overgrown | Vegetation | Remove
LC | 124173442 | 008/066 | T2 EI TRINITY-COTTONWD 8/66 RPL POLE | TABLEMTN | ETL.4040.POLE.WDPS | 2022-07-27 | 2021-03-25 | 2022-08-08 | 2022-03-25 | 2022-03-25 | Late | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31577970 | T2 TRINITY-COTTNWD 4/31R RPL STRW | 70Y
LC | 124187905 | 021/154 | T3 DI METCALF-GREEN VALLY 21/154 RMV VEG | MOSSLNDG | ETL.2540.POLE.WDPS | 2022-07-28 | 2022-06-28 | 2022-10-25 | 2022-12-25 | 2022-12-28 | On-time | 564 | E - Schd Compl Yr 0 | Closed | HFTD 3 | POHW COMP OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 124336712 | 003/072 | WV T2 DELTA-MTN GATE JCT 3/72 RPL POLE | TABLEMTN | ETL.6750.POLE.WDPS | 2022-08-22 | 2021-09-08 | 2022-08-27 | 2022-09-08 | 2022-09-08 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31431541 | T2 EI DLTA-MTN GTE JCT 005/088C RPL(ENG) | 70Y
LC | 124384079 | 009/133 | T2 DELTA-MTN GATE JCT 9/133C RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2022-08-28 | 2021-08-30 | 2022-08-29 | 2022-08-30 | 2022-08-30 | On-time | 372 | E - Schd Compl Yr 0 | Closed | HFTD 2 | POHW OTHR COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31544588 | EI T2 DELTA-MTN GATE JCT 8/124 RPL STRW | 70Y
LC | 120259723 | 017/124 | T2 CAYUCOS-CAMBRIA 17/124 REPL INSW | PISMOBCH | ETL.8560.POLE.NWOD | 2021-01-05 | 2021-01-05 | 2021-03-08 | 2022-01-05 | 2021-04-05 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31527288 | T2 CAYUCOS-CAMBRIA 17/124 REPL INSW | 93I
LC | 120446065 | 004/053 | T2 EI SNEATH LNE-PCIFIC 4/053 RPL INSW | METCALF | ETL.7575.INSL.NCER | 2021-01-19 | 2021-01-19 | 2022-05-05 | 2022-01-19 | 2022-01-19 | Late | 508 | Upgraded | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31597207 | T2 EI SNEATH LNE-PCIFIC 4/053 RPL INSW | 93I
LC | 120475392 | 006/147 | WV T2 DEL MONTE-VIEJO 6/147 INST DAMW | MOSSLNDG | ETL.6710.POLE.NWOD | 2021-01-28 | 2021-01-28 | 2021-04-12 | 2022-01-28 | 2021-04-28 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 44638255 | WV T2 DEL MONTE-VIEJO 6/147 INST DAMW | ICW
LC | 120485050 | 019/087 | EI T2 DIABLO-MESA 019/087 RPL INSS | PISMOBCH | ETL.4620.INSL | 2021-02-01 | 2021-02-01 | 2021-02-10 | 2022-02-01 | 2021-05-01 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31529413 | EI T2 DIABLO-MESA 019/087 RPL INSS | 93K
LC | 120504000 | 024/289A | T2 EI DRUM-SUMMIT #2 24/289A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2021-02-05 | 2021-02-05 | 2021-02-26 | 2022-02-05 | 2021-05-05 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44644147 | T2 EI DRUM-SUMMIT #2 24/289A RPR GYWW | ICW
LC | 120589910 | 008/055 | T2 DI METCALF-MORGAN HILL RPR INSS | MOSSLNDG | ETL.2570.INSL.CERA | 2021-03-02 | 2021-03-01 | 2021-05-09 | 2022-03-01 | 2021-06-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44670082 | T2 DI METCALF-MORGAN HILL RPR INSS | ICS
LC | 120594244 | 027/002 | T2 COALINGA #1-SAN MIGUEL 27/2 RMV BALLN | PISMOBCH | ETL.8580.TOWR | 2021-03-03 | 2021-03-02 | 2021-03-02 | 2022-03-02 | 2021-06-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 | Debris/Nest/etc. | Conductor-Steel | Remove | 44670025 | T2 COALINGA #1-SAN MIGUEL 27/2 RMV BALLN | ICS
LC | 120604304 | 014/091 | T2 JEFFERSON-MARTIN 14/091 RPR SWITCH | METCALF | ETL.5710.POLE.NWOD | 2021-03-04 | 2021-03-04 | 2021-05-25 | 2022-03-04 | 2021-06-04 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | Out of Adjustment | Switch | Repair | 44673155 | T2 JEFFERSON-MARTIN 14/091 RPR SWITCH | ICE
LC | 120612185 | 009/004 | T2 MELONES-CURTIS 9/4C REPL POLE | VICTOR | ETL.2390.POLE.WDPS | 2021-03-08 | 2021-03-08 | 2021-05-20 | 2022-03-08 | 2021-06-08 | On-time | 372 | Upgraded | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31532553 | MELONES-CURTIS 9/4R REPL POLE | 70Y
LC | 120612195 | 009/004 | T2 MELONES-CURTIS 9/4R REPL POLE | VICTOR | ETL.2390.POLE.WDPS | 2021-03-08 | 2021-03-08 | 2021-05-20 | 2022-03-08 | 2021-06-08 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31532553 | MELONES-CURTIS 9/4R REPL POLE | 70Y
LC | 120612206 | 014/067 | T2 CORTINA-MENDOCINO #1 14/67 RPR CONS | LAKEVLLE | ETL.1330.TOWR | 2021-03-08 | 2021-03-08 | 2021-04-21 | 2022-03-08 | 2021-06-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Conductor-Steel | Repair | 44698546 | T2 CORTINA-MENDOCINO #1 14/67 RPR CONS | ICS
LC | 120614493 | 001/010 | T2 BALCH-SANGER 1/010 INST COTR KEY | FRESNO | ETL.1050.INSL.CERA | 2021-03-09 | 2021-03-08 | 2021-04-13 | 2022-03-08 | 2021-06-08 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44688405 | T2 BALCH-SANGER 1/010 INST COTR KEY | ICS
LC | 120634258 | 007/000 | EI T2 OAKHURST TAP 7/000 REPL INSW | FRESNO | ETL.1252.INSL.NCER | 2021-03-11 | 2021-03-11 | 2021-05-27 | 2022-03-11 | 2021-06-11 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31533001 | EI T2 OAKHURST TAP 7/000 REPL INSW | 93I
LC | 120634393 | 008/038 | T2 DI DIABLO-MESA 008/038 INS COT KEY | PISMOBCH | ETL.4620.INSL.NCER | 2021-03-11 | 2021-03-11 | 2021-03-23 | 2022-03-11 | 2021-06-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44700353 | T2 DI DIABLO-MESA 008/038 INS COT KEY | ICS
LC | 120634940 | 004/037 | EI T2 CRAG VIEW-CASCADE 4/037 RMV NEST | TABLEMTN | ETL.1350.TOWR | 2021-03-11 | 2021-03-11 | 2021-04-02 | 2022-03-11 | 2021-06-11 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Structure-Steel | Remove | 44685355 | EI T2 CRAG VIEW-CASCADE 4/037 RMV NEST | ICS
LC | 120635637 | 033/505 | T2 CLAY-MARTEL 33/505 REPL HRDW | VICTOR | ETL.8250.POLE.NWOD | 2021-03-11 | 2021-03-11 | 2021-04-19 | 2022-03-11 | 2021-06-11 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44687718 | T2 CLAY-MARTEL 33/505 REPL HRDW | ICW
LC | 120642697 | 015/069 | T2 DI DIABLO-MESA 015/069 COTR KEY | PISMOBCH | ETL.4620.INSL.NCER | 2021-03-15 | 2021-03-12 | 2021-03-23 | 2022-03-12 | 2021-06-10 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 44700352 | T2 DI DIABLO-MESA 015/069 COTR KEY | ICS
LC | 120645204 | 004/096 | WV T2 KILARC-DESCHUTES 4/096 INST DAMP | TABLEMTN | ETL.7300.POLE.WOOD | 2021-03-15 | 2021-03-15 | 2021-03-22 | 2022-03-15 | 2021-06-15 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 | Missing | Damper-Wood | Install | 44699716 | WV T2 KILARC-DESCHUTES 4/096 INST DAMP | ICW
LC | 120647202 | 034/154 | T2 DI DIABLO-MESA 34/154 RPR INSS | PISMOBCH | ETL.4620.INSL | 2021-03-16 | 2021-03-11 | 2021-05-10 | 2022-03-11 | 2021-06-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44721254 | T2 DI DIABLO-MESA 34/154 RPR INSS | ICS
LC | 120648071 | 026/165 | T2 DI HELMS-GREGG #2 026/165 RPR INSS | FRESNO | ETL.4880.INSL | 2021-03-16 | 2021-03-16 | 2021-04-28 | 2022-03-16 | 2021-06-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44689398 | T2 DI HELMS-GREGG #2 026/165 RPR INSS | ICS
LC | 120652198 | 022/099 | T2 DI DIABLO-MESA 22/99 RPR INSS | PISMOBCH | ETL.4620.INSL.CERA | 2021-03-17 | 2021-03-12 | 2021-05-10 | 2022-03-12 | 2021-06-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44721253 | T2 DI DIABLO-MESA 22/99 RPR INSS | ICS
LC | 120653884 | 020/164 | T2 DI PARADISE-TABLE MTN 20/164 RPL STRW | TABLEMTN | ETL.4316.POLE.WOOD | 2021-03-17 | 2021-03-16 | 2021-04-23 | 2022-03-16 | 2021-06-16 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31533723 | T2 DI PARADISE-TABLE MTN 20/164 RPL STRW | 70Y
LC | 120657945 | 003/002 | EI T2 FULTON-HOPLAND 3/002 COTR KEY | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-03-18 | 2021-03-18 | 2021-03-29 | 2022-03-18 | 2021-06-18 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44698545 | EI T2 FULTON-HOPLAND 3/002 COTR KEY | ICW
LC | 120659851 | 019/086 | T2 EI MOSS LNDING-MTCLF 019/086 RPR STRS | MOSSLNDG | ETL.6050.TOWR | 2021-03-18 | 2021-03-18 | 2021-04-02 | 2022-03-18 | 2021-06-18 | On-time | 543 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO CLMB | No Good/Out of Stdrd | Structure-Tower | Repair | 44709079 | T2 MOSS LANDING-METCALF 019/086 RPR STRS | ICQ
LC | 120663452 | 018/158 | T2 EI CRAG VIEW-CASCADE 18/158 COTR KEY | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-19 | 2021-03-19 | 2021-04-02 | 2022-03-19 | 2021-06-19 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44698322 | EI CRAG VIEW-CASCADE 18/158 COTR KEY | ICW
LC | 120663625 | 029/177 | T2 DI HELMS-GREGG #1 029/177 COTR KEY | FRESNO | ETL.4870.INSL | 2021-03-19 | 2021-03-19 | 2021-04-28 | 2022-03-19 | 2021-06-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44700567 | T2 DI HELMS-GREGG #1 029/177 COTR KEY | ICS
LC | 120670230 | 001/013 | T2 NARROWS #2 TAP 001/013 RPL STRW | SACTO | ETL.6521.POLE.WOOD | 2021-03-21 | 2021-03-19 | 2021-05-02 | 2022-03-19 | 2021-06-19 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31534280 | T2 NARROWS #2 TAP 001/013 RPL STRW | 70Y
LC | 120671678 | 004/033 | T2 EI TRNTY-CTTNWD 4/033 INS DMPW | TABLEMTN | ETL.4040.INSL.CERA | 2021-03-22 | 2021-03-22 | 2021-03-31 | 2022-03-22 | 2021-06-22 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 44706915 | T2 EI TRNTY-CTTNWD 4/033 INS DMPW | ICW
LC | 120673582 | 014/126 | T2 EI DELTA-COTTONWD 14/126 RPR OPGW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-22 | 2021-03-22 | 2021-04-02 | 2022-03-22 | 2021-06-22 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44702074 | T2 EI DELTA-COTTONWD 14/126 RPR OPGW | ICW
LC | 120677270 | 006/110 | T2 DI SISQUOC-SANTA YNEZ 6/110 RPR INSW | PISMOBCH | ETL.3700.INSL.CERA | 2021-03-23 | 2021-03-22 | 2021-05-27 | 2022-03-22 | 2021-06-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44721255 | T2 DI SISQUOC-SANTA YNEZ 6/110 RPR INSW | ICW
LC | 120678064 | 028/214 | T2 EI MDL FRK-GLD HLL 28/214 RPR INSW | SACTO | ETL.5140.INSL.NCER | 2021-03-23 | 2021-03-23 | 2021-03-30 | 2022-03-23 | 2021-06-23 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44711464 | T2 EI MDL FRK-GLD HLL 28/214 RPR INSW | ICW
LC | 120680338 | 007/060 | EI TRINITY-COTTONWOOD 7/060 INS CTR KEY | TABLEMTN | ETL.4040.INSL.CERA | 2021-03-23 | 2021-03-23 | 2021-03-31 | 2022-03-23 | 2021-06-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44706918 | EI TRINITY-COTTONWOOD 7/060 INS CTR KEY | ICW
LC | 120681748 | 007/007 | T2 MAPLE CREEK-HOOPA 7/7 RPR CONW | EUREKA | ETL.7490.POLE.NWOD | 2021-03-23 | 2021-03-23 | 2021-04-13 | 2022-03-23 | 2021-06-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair | 44704427 | T2 MAPLE CREEK-HOOPA 7/7 RPR CONW | ICW
LC | 120682833 | 003/025 | T2 EI BALCH-SANGER 3/025 INST DAMPS | FRESNO | ETL.1050.INSL.CERA | 2021-03-24 | 2021-03-22 | 2021-04-12 | 2022-03-22 | 2021-06-22 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Steel | Install | 44715863 | T2 EI BALCH-SANGER 3/025 INST DAMPS | ICS
LC | 120683267 | 056/312 | T2 DI TMBLR-SN LS OBISPO 56/312 RPR INSS | PISMOBCH | ETL.3960.INSL | 2021-03-24 | 2021-03-23 | 2021-04-29 | 2022-03-23 | 2021-06-23 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44721256 | T2 DI TMBLR-SN LS OBISPO 56/312 RPR INSS | ICS
LC | 120683310 | 004/041 | T2 DI BRIDGEVILLE-CTTNWD 4/41 RPR ADSS | TABLEMTN | ETL.1110.POLE.STPS | 2021-03-24 | 2021-03-17 | 2021-05-12 | 2022-03-17 | 2021-06-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44706912 | T2 DI BRIDGEVILLE-CTTNWD 4/41 RPR ADSS | ICW
LC | 120683311 | 005/050 | T2 DI BRIDGEVLL-CTTNWD 5/50 RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2021-03-24 | 2021-03-17 | 2021-05-12 | 2022-03-17 | 2021-06-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44706917 | T2 DI BRIDGEVLL-CTTNWD 5/50 RPR ADSS | ICW
LC | 120683313 | 005/054 | T2 DI BRIDGEVL-CTTNWD 5/54 RPR ADSS | TABLEMTN | ETL.1110.POLE.STPS | 2021-03-24 | 2021-03-17 | 2021-05-12 | 2022-03-17 | 2021-06-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44706911 | T2 DI BRIDGEVL-CTTNWD 5/54 RPR ADSS | ICW
LC | 120683813 | 014/134 | T2 DI BRDGVLL-COTTONWOOD 14/134 RPR ADSS | TABLEMTN | ETL.1110.POLE.STPS | 2021-03-24 | 2021-03-17 | 2021-05-12 | 2022-03-17 | 2021-06-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44706919 | T2 DI BRDGVLL-COTTONWOOD 14/134 RPR ADSS | ICW
LC | 120683814 | 027/231 | T2 DI BRDGEVLL-CTTNWD 27/231 RPR ADSS | TABLEMTN | ETL.1110.POLE.STPS | 2021-03-24 | 2021-03-17 | 2021-05-12 | 2022-03-17 | 2021-06-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44706914 | DI BRDGEVLL-CTTNWD 27/231 RPR ADSS | ICW
LC | 120683817 | 039/314 | T2 DI BRDGEVLL-CTTNWD 39/314 RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2021-03-24 | 2021-03-17 | 2021-05-12 | 2022-03-17 | 2021-06-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44706913 | DI BRDGEVLL-CTTNWD 39/314 RPR ADSS | ICW
LC | 120684122 | 007/054 | T2 EI TRNTY-CTTNWD 7/54L RPL STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-03-24 | 2021-03-24 | 2021-04-30 | 2022-03-24 | 2021-06-24 | On-time | 372 | Upgraded | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535072 | T2 EI TRNTY-CTTNWD 7/54R RPL STRW | 70Y
LC | 120685673 | 021/082 | T2 DI PITTSBURG-SAN MATEO 21/82 COTR KEY | CONCORD | ETL.5463.INSL | 2021-03-24 | 2021-03-23 | 2021-04-05 | 2022-03-23 | 2021-06-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44709078 | T2 DI PITTSBURG-SAN MATEO 21/82 COTR KEY | ICS
LC | 120685674 | 021/082 | T2 DI PITTSBURG-EASTSHORE 21/82 COTR KEY | CONCORD | ETL.5462.INSL | 2021-03-24 | 2021-03-23 | 2021-04-05 | 2022-03-23 | 2021-06-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44709077 | T2 DI PITTSBURG-EASTSHORE 21/82 COTR KEY | ICS
LC | 120686135 | 006/139 | T2 CLMN-STH 006/139 RPR GWRW | TABLEMTN | ETL.6450.POLE.WOOD | 2021-03-24 | 2021-03-24 | 2021-04-23 | 2022-03-24 | 2021-06-24 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44722574 | T2 CLMN-STH 006/139 RPR GWRW | ICW
LC | 120686242 | :019/005 | T2 WV EAGLE RCK-CRTINA :019/005 INS DAMW | LAKEVLLE | ETL.1470.INSL.NCER | 2021-03-24 | 2021-03-24 | 2021-04-02 | 2022-03-24 | 2021-06-24 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 44711104 | T2 WV EAGLE RCK-CRTINA :019/005 INS DAMW | ICW
LC | 120689396 | 013/114 | T2 EI CRAG VIEW-CSCDE 13/114 RPR INSS | TABLEMTN | ETL.1350.INSL | 2021-03-25 | 2021-03-24 | 2021-03-31 | 2022-03-24 | 2021-06-24 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44715140 | T2 EI CRAG VIEW-CSCDE 13/114 RPR INSS | ICS
LC | 120689627 | 007/054 | T2 EI TRNTY-CTTNWD 7/54R RPL STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-03-25 | 2021-03-24 | 2021-05-03 | 2022-03-24 | 2021-06-24 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535072 | T2 EI TRNTY-CTTNWD 7/54R RPL STRW | 70Y
LC | 120691523 | 032/189 | T2 DI HELMS-GREGG #2 32/189 COTR KEY | FRESNO | ETL.4880.INSL | 2021-03-25 | 2021-03-25 | 2021-04-26 | 2022-03-25 | 2021-06-23 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44715872 | T2 DI HELMS-GREGG #2 32/189 COTR KEY | ICS
LC | 120692024 | 008/133 | T2 DI SISQUOC-SANTA YNEZ 8/133 COTR KEY | PISMOBCH | ETL.3700.INSL.CERA | 2021-03-25 | 2021-03-25 | 2021-04-09 | 2022-03-25 | 2021-06-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44721257 | T2 DI SISQUOC-SANTA YNEZ 8/133 COTR KEY | ICW
LC | 120694889 | 035/199 | T2 EXCHEQUER-INDIN FLT 35/199 RMV DEBRIS | FRESNO | ETL.8650.POLE.NWOD | 2021-03-26 | 2021-03-26 | 2021-04-15 | 2022-03-26 | 2021-06-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Conductor-Steel | Remove | 44715875 | T2 EXCHEQUER-INDIN FLT 35/199 RMV DEBRIS | ICS
LC | 120694981 | 017/101 | T2 DI STN ML SW STA-RVBN 17/101 INS HRDS | VICTOR | ETL.3840.INSL.CERA | 2021-03-26 | 2021-03-25 | 2021-05-20 | 2022-03-25 | 2021-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44723012 | T2 DI STN ML SW STA-RVBN 17/101 INS HRDS | ICS
LC | 120694982 | 017/108 | T2 DI STLS-MLS SS-MTC #1 17/108 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-03-26 | 2021-03-25 | 2021-05-26 | 2022-03-25 | 2021-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44723013 | T2 DI STLS-MLS SS-MTC #1 17/108 INS HRDS | ICS
LC | 120694985 | 025/158 | T2 DI STLS-MLS SS-MTC #1 25/158 INS HRDS | VICTOR | ETL.3830.INSL | 2021-03-26 | 2021-03-25 | 2021-05-28 | 2022-03-25 | 2021-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44723014 | T2 DI STLS-MLS SS-MTC #1 25/158 INS HRDS | ICS
LC | 120695161 | 024/152 | T2 DI STS-MLNS SS-MTC #1 24/152 INS HRDS | VICTOR | ETL.3830.INSL | 2021-03-26 | 2021-03-25 | 2021-05-28 | 2022-03-25 | 2021-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44723016 | T2 DI STS-MLNS SS-MTC #1 24/152 INS HRDS | ICS
LC | 120695211 | 009/052 | T2 DI STAN MEL SW -RVRBNK 9/52 RPL DAMS | VICTOR | ETL.3840.INSL.CERA | 2021-03-26 | 2021-03-25 | 2021-05-18 | 2022-03-25 | 2021-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 44723017 | T2 DI STAN MEL SW -RVRBNK 9/52 RPL DAMS | ICS
LC | 120695217 | 009/059 | T2 DI STLS-MLNS SS-MTC #1 9/59 INS HRDS | VICTOR | ETL.3830.INSL | 2021-03-26 | 2021-03-25 | 2021-05-25 | 2022-03-25 | 2021-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44723018 | T2 DI STLS-MLNS SS-MTC #1 9/59 INS HRDS | ICS
LC | 120695342 | 009/054 | T2 DI STANSLS-MLNS-MNTC 9/54 INS HRDS | VICTOR | ETL.3830.INSL | 2021-03-26 | 2021-03-25 | 2021-05-25 | 2022-03-25 | 2021-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44723019 | T2 DI STANSLS-MLNS-MNTC 9/54 INS HRDS | ICS
LC | 120695542 | 024/153 | T2 DI STANSLS-MLNS-MNTC 24/153 INS HRDS | VICTOR | ETL.3830.INSL | 2021-03-26 | 2021-03-25 | 2021-05-28 | 2022-03-25 | 2021-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724200 | T2 DI STANSLS-MLNS-MNTC 24/153 INS HRDS | ICS
LC | 120695692 | 024/140 | T2 DI STAN MEL SW-RVRBK 24/140 INS HRDS | VICTOR | ETL.3840.INSL.CERA | 2021-03-26 | 2021-03-25 | 2021-05-20 | 2022-03-25 | 2021-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724201 | T2 DI STAN MEL SW-RVRBK 24/140 INS HRDS | ICS
LC | 120696294 | 008/068 | T2 EI ELDORDO-MSSRI FLT #1 8/0 RPL INSW | SACTO | ETL.1530.POLE.NWOD | 2021-03-26 | 2021-03-26 | 2021-04-23 | 2022-03-26 | 2021-06-26 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31534886 | T2 EI ELDORDO-MSSRI FLT #1 8/68 RPL INSW | 93I
LC | 120696573 | 023/136 | T2 DI SN ML SW ST-RK J SW 23/136 INS HRD | VICTOR | ETL.3840.INSL.NCER | 2021-03-26 | 2021-03-25 | 2021-05-20 | 2022-03-25 | 2021-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724203 | T2 DI SN ML SW ST-RK J SW 23/136 INS HRD | ICS
LC | 120696574 | 023/144 | T2 DI STLS-MLS SS-MTC #1 23/144 INS HRDS | VICTOR | ETL.3830.INSL | 2021-03-26 | 2021-03-26 | 2021-05-28 | 2022-03-26 | 2021-06-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724204 | T2 DI STLS-MLS SS-MTC #1 23/144 INS HRDS | ICS
LC | 120696579 | 025/159 | T2 DI STLS-MLS SS-MTC #1 25/159 INS HRDS | VICTOR | ETL.3830.INSL | 2021-03-26 | 2021-03-26 | 2021-05-28 | 2022-03-26 | 2021-06-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724205 | T2 DI STLS-MLS SS-MTC #1 25/159 INS HRDS | ICS
LC | 120696625 | 017/247 | T2 EI SSC-SNT YNZ SW ST 17/247 RPR GYWW | PISMOBCH | ETL.3700.POLE.NWOD | 2021-03-26 | 2021-03-26 | 2021-06-07 | 2022-03-26 | 2021-06-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44721259 | T2 EI SSC-SNT YNZ SW ST 17/247 RPR GYWW | ICW
LC | 120696797 | 024/150 | T2 DI STANSLS-MLNS-MNTC 24/150 INS HRDS | VICTOR | ETL.3830.INSL | 2021-03-26 | 2021-03-25 | 2021-05-25 | 2022-03-25 | 2021-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724206 | T2 DI STANSLS-MLNS-MNTC 24/150 INS HRDS | ICS
LC | 120696799 | 024/149 | T2 DI STANIS-MLNS-MNTC#1 24/149 INS HRDS | VICTOR | ETL.3830.INSL | 2021-03-26 | 2021-03-26 | 2021-05-28 | 2022-03-26 | 2021-06-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724207 | T2 DI STANIS-MLNS-MNTC#1 24/149 INS HRDS | ICS
LC | 120697686 | 000/002 | T2 EI FLINT TAP 0/2 RPR SWITCH | SACTO | ETL.3341.SWIT | 2021-03-26 | 2021-03-26 | 2021-06-24 | 2022-03-26 | 2021-06-26 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | Out of Adjustment | Switch | Repair | 44725284 | T2 EI FLINT TAP 0/2 RPR SWITCH | ICE
LC | 120697902 | 002/017 | T2 WISHON-COPPERMINE 2/017 REPL DAMS | FRESNO | ETL.9330.TOWR | 2021-03-26 | 2021-03-26 | 2021-06-11 | 2022-03-26 | 2021-06-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Damper-Steel | Replace | 44715878 | T2 WISHON-COPPERMINE 2/017 REPL DAMS | ICS
LC | 120698545 | 025/156 | T2 DI STLS-MLNS SS-MTC #1 25/156 INS HRD | VICTOR | ETL.3830.INSL | 2021-03-26 | 2021-03-26 | 2021-05-28 | 2022-03-26 | 2021-06-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724208 | T2 DI STLS-MLNS SS-MTC #1 25/156 INS HRD | ICS
LC | 120698602 | 009/054 | T2 DI STANMEL-RVRBNK JCT 9/54 RPLC DAMS | VICTOR | ETL.3840.INSL.CERA | 2021-03-26 | 2021-03-26 | 2021-05-18 | 2022-03-26 | 2021-06-24 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 44724209 | T2 DI STANMEL-RVRBNK JCT 9/54 RPLC DAMS | ICS
LC | 120698715 | 034/216 | T2 EI CRZY HRS CYN-HLSTR 34/216 RMV DBR | MOSSLNDG | ETL.2153.INSL.CERA | 2021-03-26 | 2021-03-26 | 2021-05-21 | 2022-03-26 | 2021-06-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Conductor-Steel | Remove | 44715198 | T2 EI CRZY HRS CYN-HLSTR 34/216 RMV DBR | ICS
LC | 120704982 | 018/111 | T2 DI STNSLS-MLNS-MANTCA 18/111 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-03-29 | 2021-03-26 | 2021-05-26 | 2022-03-26 | 2021-06-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724210 | T2 DI STNSLS-MLNS-MANTCA 18/111 INS HRDS | ICS
LC | 120705059 | 023/148 | T2 DI STNSLS-MLNS-MNTCA 23/148 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-03-29 | 2021-03-26 | 2021-05-28 | 2022-03-26 | 2021-06-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724211 | T2 DI STNSLS-MLNS-MNTCA 23/148 INS HRDS | ICS
LC | 120707042 | 008/075 | T2 EI DELTA-COTTONWOOD 8/75 RPR SPLW | TABLEMTN | ETL.1350.INSL.CERA | 2021-03-29 | 2021-03-29 | 2021-05-18 | 2022-03-29 | 2021-06-29 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Repair | 44715146 | EI DELTA-COTTONWOOD 8/75 RPR SPLW | ICW
LC | 120708712 | 024/154 | T2 DI STLS-MLS SS-MTC #1 24/154 INS HRDS | VICTOR | ETL.3830.INSL | 2021-03-29 | 2021-03-25 | 2021-05-28 | 2022-03-25 | 2021-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724212 | T2 DI STLS-MLS SS-MTC #1 24/154 INS HRDS | ICS
LC | 120708814 | 016/102 | T2 DI STNSLS-MLS SS-MTC #1 16/102 INS HR | VICTOR | ETL.3830.INSL | 2021-03-29 | 2021-03-26 | 2021-05-26 | 2022-03-26 | 2021-06-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724213 | T2 DI STNSLS-MLS SS-MTC #1 16/102 INS HR | ICS
LC | 120708868 | 016/103 | T2 DI STNSLS-MLS SS-MTC #1 16/103 INS HR | VICTOR | ETL.3830.INSL | 2021-03-29 | 2021-03-26 | 2021-05-26 | 2022-03-26 | 2021-06-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724214 | T2 DI STNSLS-MLS SS-MTC #1 16/103 INS HR | ICS
LC | 120711054 | 015/097 | T2 DI STNLS-MLS SS-MTC #1 15/97 INS HRDS | VICTOR | ETL.3830.INSL | 2021-03-30 | 2021-03-26 | 2021-05-26 | 2022-03-26 | 2021-06-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724215 | T2 DI STNLS-MLS SS-MTC #1 15/97 INS HRDS | ICS
LC | 120711311 | 002/016 | T2 DI KRKHF-CLS-SNGR #2 2/16 INS CTR KEY | FRESNO | ETL.1900.INSL.CERA | 2021-03-30 | 2021-03-29 | 2021-04-29 | 2022-03-29 | 2021-06-29 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44720706 | T2 DI KRKHF-CLS-SNGR #2 2/16 INS CTR KEY | ICS
LC | 120711526 | 005/030 | T2 DI KRCKFF-CLVS-SANGR #1 5/30 RPR INSS | FRESNO | ETL.1890.INSL.CERA | 2021-03-30 | 2021-03-29 | 2021-04-29 | 2022-03-29 | 2021-06-29 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44720707 | T2 DI KRCKFF-CLVS-SANGR #1 5/30 RPR INSS | ICS
LC | 120711978 | 016/372 | T2 EI DRUM-GV-WEIMAR 16/372 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-03-30 | 2021-03-30 | 2021-06-30 | 2022-03-30 | 2021-06-30 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44725258 | T2 EI DRUM-GV-WEIMAR 16/372 RPR GYWW | ICW
LC | 120714410 | :005/038 | T2 EI RCK CRK-POE :5/38 RPR HRDT | TABLEMTN | ETL.5630.INSL.CERA | 2021-03-30 | 2021-03-30 | 2021-06-29 | 2022-03-30 | 2021-06-30 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44722572 | T2 EI RCK CRK-POE :5/38 RPR HRDT | ICS
LC | 120714510 | :005/035 | T2 EI ROCK CREEK-POE :5/035 RPR MEMBER | TABLEMTN | ETL.5630.TOWR | 2021-03-30 | 2021-03-30 | 2021-04-08 | 2022-03-30 | 2021-06-30 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair | 44720154 | T2 EI ROCK CREEK-POE :5/035 RPR MEMBER | ICQ
LC | 120715091 | 008/053 | T2 DI STNSLS-MLNS-MNTC 8/53 INS HRDS | VICTOR | ETL.3830.INSL | 2021-03-30 | 2021-03-25 | 2021-05-25 | 2022-03-25 | 2021-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724217 | T2 DI STNSLS-MLNS-MNTC 8/53 INS HRDS | ICS
LC | 120717474 | 026/161 | T2 DI TSL-SLD-MNTC 26/161 INS COTR KEY | VICTOR | ETL.4000.INSL.CERA | 2021-03-31 | 2021-03-31 | 2021-05-13 | 2022-03-31 | 2021-06-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44724218 | T2 DI TSL-SLD-MNTC 26/161 INS COTR KEY | ICW
LC | 120718087 | 053/477 | T2 EI PIT #1-COTTONWD 53/477 COTR KEY | TABLEMTN | ETL.5390.TOWR | 2021-03-31 | 2021-03-31 | 2021-04-26 | 2022-03-31 | 2021-06-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44722569 | T2 EI PIT #1-COTTONWD 53/477 COTR KEY | ICS
LC | 120718199 | 058/531 | T2 EI ROUND MTN-CTNWD#3 58/531 COTR | TABLEMTN | ETL.5650.TOWR | 2021-03-31 | 2021-03-31 | 2021-04-13 | 2022-03-31 | 2021-06-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44737030 | T2 EI ROUND MTN-CTNWD#3 58/531 COTR | ICS
LC | 120723798 | 024/155 | T2 DI STNSLS-MLNS-MNTC 24/155 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-01 | 2021-03-26 | 2021-05-28 | 2022-03-26 | 2021-06-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724241 | T2 DI STNSLS-MLNS-MNTC 24/155 INS HRDS | ICS
LC | 120723837 | 008/052 | T2 DI STNSLS-MLNS-MNTC 8/52 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-01 | 2021-03-31 | 2021-05-25 | 2022-03-31 | 2021-06-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724242 | T2 DI STNSLS-MLNS-MNTC 8/52 INS HRDS | ICS
LC | 120723851 | 020/131 | T2 DI SNSLS-MS SS-MTC #1 20/131 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-01 | 2021-03-31 | 2021-05-28 | 2022-03-31 | 2021-06-29 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724243 | T2 DI SNSLS-MS SS-MTC #1 20/131 INS HRDS | ICS
LC | 120725044 | 009/167 | T2 EI PT #1-HT CRK #2-BRY 9/167 RPR INSW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-04-01 | 2021-04-01 | 2021-05-08 | 2022-04-01 | 2021-07-01 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44722578 | T2 PIT #1-HT CRK #2-BRNY 9/167 RPR INSW | ICW
LC | 120725393 | 007/096 | T2 IGNACIO-BOLINAS #2 7/96 REPL POLE | LAKEVLLE | ETL.7180.POLE.WOOD | 2021-04-01 | 2021-03-31 | 2021-04-14 | 2022-03-31 | 2021-06-30 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | POHW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535104 | T2 IGNACIO-BOLINAS #2 7/96 REPL POLE | 70Y
LC | 120725853 | 018/133 | T2 EI CAYUCOS-CAMBRIA 18/133 INS DAMW | PISMOBCH | ETL.8560.INSL.CERA | 2021-04-01 | 2021-04-01 | 2021-06-23 | 2022-04-01 | 2021-06-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | Missing | Damper-Wood | Install | 44772563 | T2 EI CAYUCOS-CAMBRIA 18/133 INS DAMW | ICW
LC | 120726520 | 020/285 | T2 DI SQC-SNT YNZ SW 20/285 INS COTR KEY | PISMOBCH | ETL.3700.INSL.CERA | 2021-04-01 | 2021-04-01 | 2021-05-11 | 2022-04-01 | 2021-06-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44772564 | T2 DI SQC-SNT YNZ SW 20/285 INS COTR KEY | ICW
LC | 120726525 | 020/130 | T2 DI STSLS-MLS S-MTC #1 20/130 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-01 | 2021-03-31 | 2021-05-28 | 2022-03-31 | 2021-06-29 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724244 | T2 DI STSLS-MLS S-MTC #1 20/130 INS HRDS | ICS
LC | 120726528 | 008/050 | T2 DI STN ML SW ST-RVR JCT 8/50 INS HRDS | VICTOR | ETL.3840.INSL.CERA | 2021-04-01 | 2021-03-31 | 2021-05-18 | 2022-03-31 | 2021-06-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724246 | T2 DI STN ML SW ST-RVR JCT 8/50 INS HRDS | ICS
LC | 120726685 | 006/055AB | T2 EI PARADISE-TABLE MTN 6/055AB REPL PL | TABLEMTN | ETL.4316.POLE.WDPS | 2021-04-01 | 2021-04-01 | 2021-07-24 | 2022-04-01 | 2022-04-01 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31543429 | T2 DI PRDS-TBL MTN 006/055AB RPL STRW | 70Y
LC | 120726758 | 024/139 | T2 DI SN ML SW ST-RK JT 24/139 RPR INSS | VICTOR | ETL.3840.INSL.CERA | 2021-04-01 | 2021-03-25 | 2021-05-20 | 2022-03-25 | 2021-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44724247 | T2 DI SN ML SW ST-RK JT 24/139 RPR INSS | ICS
LC | 120726914 | 005/039 | T2 DI VAC-VCVL-JMSN-N. TWR 5/39 COTR KEY | SACTO | ETL.4090.INSL.CERA | 2021-04-01 | 2021-04-01 | 2021-04-06 | 2022-04-01 | 2021-06-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 44721531 | T2 DI VAC-VCVL-JMSN-N. TWR 5/39 COTR KEY | ICS
LC | 120734116 | 024/134 | T2 DI TESLA-SALADO-MNTC 24/134 COTR KEY | VICTOR | ETL.4000.INSL.CERA | 2021-04-02 | 2021-03-31 | 2021-05-13 | 2022-03-31 | 2021-06-29 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44724248 | T2 DI TESLA-SALADO-MNTC 24/134 COTR KEY | ICW
LC | 120734181 | 006/039 | T2 DI KRKF-CLVS-SNR #1 6/39 INS COTR KEY | FRESNO | ETL.1890.INSL.CERA | 2021-04-02 | 2021-04-01 | 2021-04-29 | 2022-04-01 | 2021-07-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44720767 | T2 DI KRKF-CLVS-SNR #1 6/39 INS COTR KEY | ICS
LC | 120734189 | 022/137 | T2 DI STANSLS-MLNS-MNTC 22/137 INS WASHR | VICTOR | ETL.3830.INSL | 2021-04-02 | 2021-04-01 | 2021-05-28 | 2022-04-01 | 2021-06-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724249 | T2 DI STANSLS-MLNS-MNTC 22/137 INS WASHR | ICS
LC | 120734775 | 005/035 | T2 DI KRKF-CLVS-SNGR #1 5/35 INS CTR KEY | FRESNO | ETL.1900.INSL.CERA | 2021-04-02 | 2021-04-01 | 2021-04-29 | 2022-04-01 | 2021-07-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44720768 | T2 DI KRKF-CLVS-SNGR #1 5/35 INS CTR KEY | ICS
LC | 120734898 | 022/128 | T2 DI SN ML SW ST-RK JT 22/128 COTR KEY | VICTOR | ETL.3840.INSL.CERA | 2021-04-02 | 2021-03-31 | 2021-05-20 | 2022-03-31 | 2021-06-29 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44724251 | T2 DI SN ML SW ST-RK JT 22/128 COTR KEY | ICS
LC | 120735527 | 022/140 | T2 DI STNSLS-MLS SS-MTC #1 22/140 RPR ST | VICTOR | ETL.3830.TOWR | 2021-04-02 | 2021-04-01 | 2021-04-16 | 2022-04-01 | 2021-06-30 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair | 44724252 | T2 DI STNSLS-MLS SS-MTC #1 22/140 RPR ST | ICQ
LC | 120735559 | 022/140 | T2 DI STNSLS-MLS SS-MTC #1 22/140 INS HR | VICTOR | ETL.3830.INSL | 2021-04-02 | 2021-04-01 | 2021-05-28 | 2022-04-01 | 2021-06-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724253 | T2 DI STNSLS-MLS SS-MTC #1 22/140 INS HR | ICS
LC | 120736390 | :015/082 | T2 CAZY HRSE CNYN-SLINS-SL:15/82 RPR FND | MOSSLNDG | ETL.2900.TOWR | 2021-04-02 | 2021-04-02 | 2021-04-20 | 2022-04-02 | 2021-07-02 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44722333 | T2 CAZY HRSE CNYN-SLINS-SL:15/82 RPR FND | ICQ
LC | 120736692 | 017/241 | T2 DI SSQC-SNT YNZ SW ST 17/241 RPR GYWW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-02 | 2021-04-01 | 2021-06-06 | 2022-04-01 | 2021-06-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44772562 | T2 DI SSQC-SNT YNZ SW ST 17/241 RPR GYWW | ICW
LC | 120736708 | 008/138 | T2 EI IPIT #1HT CRK #2-BNY 8/138 COTTER | TABLEMTN | ETL.7040.INSL.NCER | 2021-04-02 | 2021-04-02 | 2021-05-19 | 2022-04-02 | 2021-07-02 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44739880 | T2 EI IPIT #1HT CRK #2-BNY 8/138 INSW | ICW
LC | 120736802 | 022/139 | T2 DI STNSLS-MLS SS-MTC #1 22/139 INS HR | VICTOR | ETL.3830.TOWR | 2021-04-02 | 2021-04-01 | 2021-05-28 | 2022-04-01 | 2021-06-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44724254 | T2 DI STNSLS-MLS SS-MTC #1 22/139 INS HR | ICS
LC | 120737571 | :016/087 | T2 EI CRZY HRS CNYN-SLNS-SL:16/87 RPR FO | MOSSLNDG | ETL.2900.TOWR | 2021-04-02 | 2021-04-02 | 2021-04-19 | 2022-04-02 | 2021-07-02 | On-time | 543 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44722334 | T2 EI CRZY HRS CNYN-SLNS-SL:16/87 RPR FO | ICQ
LC | 120743589 | 012/004 | T2 WV TRINITY-MPLE CRK 12/4 INST GYWW | EUREKA | ETL.8170.POLE.WOOD | 2021-04-05 | 2021-04-05 | 2021-06-11 | 2022-04-05 | 2021-07-05 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Guy Wire-Wood | Install | 44736830 | T2 WV TRINITY-MPLE CRK 12/4 INST GYWW | ICW
LC | 120743802 | 017/107 | T2 DI STS-MLS SS-MTC #1 017/107 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-05 | 2021-03-25 | 2021-05-26 | 2022-03-25 | 2021-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752032 | T2 DI STS-MLS SS-MTC #1 017/107 INS HRDS | ICS
LC | 120743844 | 022/138 | T2 DI STNSLS-MLNS-MNTC#1 22/138 INS HDRS | VICTOR | ETL.3830.TOWR | 2021-04-05 | 2021-03-31 | 2021-05-28 | 2022-03-31 | 2021-06-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44764684 | T2 DI STNSLS-MLNS-MNTC#1 22/138 INS HDRS | ICS
LC | 120745014 | :007/006 | T2 BLT-RVRBK-MLNS SWSTA :7/6 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-04-05 | 2021-04-05 | 2021-06-03 | 2022-04-05 | 2021-07-04 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31535255 | T2 BLT-RVRBK-MLNS SWSTA :7/6 RPL STRW | 70Y
LC | 120745364 | 005/066 | T2 EI GREEN VALLEY-PAUL 05/66L RPL PL | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-04-05 | 2021-04-05 | 2022-10-28 | 2022-04-05 | 2022-04-05 | Late | 372 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31537554 | T2 EI GREEN VALLEY-PAUL 05/066 RPL PL | 70Y
LC | 120745900 | 006/104 | T2 EI PT #1-HT CK #2-BNY 6/101 GY COTTET | TABLEMTN | ETL.7040.POLE.WOOD | 2021-04-05 | 2021-04-05 | 2021-05-19 | 2022-04-05 | 2021-07-05 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44738655 | T2 EI PT #1-HT CK #2-BNY 6/101 GY COTTET | ICW
LC | 120747457 | 012/075 | T2 DI STN ML SW ST-RBK JT 12/75 INS HRDS | VICTOR | ETL.3840.INSL.CERA | 2021-04-06 | 2021-04-05 | 2021-05-18 | 2022-04-05 | 2021-07-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752034 | T2 DI STN ML SW ST-RBK JT 12/75 INS HRDS | ICS
LC | 120747617 | 019/119 | T2 DI STNSLS-MLNS-MNTC 19/119 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-04-06 | 2021-05-27 | 2022-04-06 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752037 | T2 DI STNSLS-MLNS-MNTC 19/119 INS HRDS | ICS
LC | 120747618 | 008/048 | T2 DI STNSLS-MLS SS-MTC #1 8/48 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752101 | T2 DI STNSLS-MLS SS-MTC #1 8/48 INS HRDS | ICS
LC | 120747726 | 007/046 | T2 DI STNSLS-MLNS-MNTC 7/46 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-04-05 | 2021-05-25 | 2022-04-05 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752102 | T2 DI STNSLS-MLNS-MNTC 7/46 INS HRDS | ICS
LC | 120747851 | 008/051 | T2 DI STNSLS-MLS SS-MTC #1 8/51 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-04-05 | 2021-05-25 | 2022-04-05 | 2021-07-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752103 | T2 DI STNSLS-MLS SS-MTC #1 8/51 INS HRDS | ICS
LC | 120748316 | 008/049 | T2 DI STN MEL-RVRBNK JCT 8/49 RPLC HRDS | VICTOR | ETL.3840.INSL.CERA | 2021-04-06 | 2021-04-06 | 2021-05-18 | 2022-04-06 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Steel | Replace | 44752106 | T2 DI STN MEL-RVRBNK JCT 8/49 RPLC HRDS | ICS
LC | 120748977 | 021/494 | T2 EI DRUM-GV-WEIMAR 21/494 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2021-04-06 | 2021-04-06 | 2021-06-03 | 2022-04-06 | 2021-07-06 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535913 | T2 EI DRUM-GV-WEIMAR 21/494 RPL POLE | 70Y
LC | 120749870 | 019/120 | T2 DI STNSLS-MLNS-MNTC 19/120 INST HRDS | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-04-06 | 2021-05-27 | 2022-04-06 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752108 | T2 DI STNSLS-MLNS-MNTC 19/120 INST HRDS | ICS
LC | 120749872 | 007/043 | T2 DI STNSLS-MLNS-MNTC 7/43 INST HRDS | VICTOR | ETL.3830.INSL.CERA | 2021-04-06 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752112 | T2 DI STNSLS-MLNS-MNTC 7/43 INST HRDS | ICS
LC | 120750189 | 003/024 | T2 DI STNLS-MLNS SS-MTC #1 3/24 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-06 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752114 | T2 DI STNLS-MLNS SS-MTC #1 3/24 INS HRDS | ICS
LC | 120750249 | 007/047 | T2 DI STNLS-MLNS SS-MTC #1 7/47 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-06 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752117 | T2 DI STNLS-MLNS SS-MTC #1 7/47 INS HRDS | ICS
LC | 120750328 | 024/151 | T2 DI STNSLS-MLNS-MTC#1 24/151 INST HRDS | VICTOR | ETL.3830.INSL | 2021-04-06 | 2021-03-25 | 2021-05-28 | 2022-03-25 | 2021-06-23 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44764685 | T2 DI STNSLS-MLNS-MTC#1 24/151 INST HRDS | ICS
LC | 120750472 | 019/118 | T2 DI STNSLS-MLNS-MNTC 19/118 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-04-06 | 2021-05-27 | 2022-04-06 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752121 | T2 DI STNSLS-MLNS-MNTC 19/118 INS HRDS | ICS
LC | 120750523 | 000/005 | T2 DI STNSLS-MLNS-MNTC#1 0/5 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-06 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752126 | T2 DI STNSLS-MLNS-MNTC#1 0/5 INS HRDS | ICS
LC | 120750534 | 015/343 | T2 EI DRUM-GV-WEIMAR 15/343 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-04-06 | 2021-04-06 | 2021-07-01 | 2022-04-06 | 2021-07-06 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44752904 | T2 EI DRUM-GV-WEIMAR 15/343 RPR GYWW | ICW
LC | 120750793 | 001/009 | T2 DI STNSLS-MLNS-MNTC#1 1/9 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-06 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752161 | T2 DI STNSLS-MLNS-MNTC#1 1/9 INS HRDS | ICS
LC | 120751924 | 003/018 | T2 DI STNSLS-MANTCA #2 3/18 INS HRDS | VICTOR | ETL.3820.TOWR | 2021-04-06 | 2021-04-06 | 2021-05-18 | 2022-04-06 | 2021-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752165 | T2 DI STNSLS-MANTCA #2 3/18 INS HRDS | ICS
LC | 120752064 | 007/044 | T2 DI STSLS-MLS SS-MTC #1 7/44 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-06 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752172 | T2 DI STSLS-MLS SS-MTC #1 7/44 INS HRDS | ICS
LC | 120752086 | 012/075 | T2 DI STSLS-MLS SS-MTC #1 12/75 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-04-06 | 2021-05-26 | 2022-04-06 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752173 | T2 DI STSLS-MLS SS-MTC #1 12/75 INS HRDS | ICS
LC | 120752131 | 000/004 | T2 DI STSLS-MLS SS-MTC #1 0/4 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-06 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752174 | T2 DI STSLS-MLS SS-MTC #1 0/4 INS HRDS | ICS
LC | 120752306 | 008/048 | T2 DI STANISLAUS-MANTEC #2 8/48 INS HRDS | VICTOR | ETL.3820.TOWR | 2021-04-06 | 2021-04-06 | 2021-05-18 | 2022-04-06 | 2021-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752175 | T2 DI STANISLAUS-MANTEC #2 8/48 INS HRDS | ICS
LC | 120753031 | 012/076 | T2 DI STAN MEL -RVRBNK 12/76 INS WASHR | VICTOR | ETL.3840.INSL.CERA | 2021-04-06 | 2021-04-06 | 2021-05-18 | 2022-04-06 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44752176 | T2 DI STAN MEL -RVRBNK 12/76 INS WASHR | ICS
LC | 120753033 | 001/010 | T2 DI STNSLS-MLNS-MNTC 1/10 RPLC DAMS | VICTOR | ETL.3830.TOWR | 2021-04-06 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 44752177 | T2 DI STNSLS-MLNS-MNTC 1/10 RPLC DAMS | ICS
LC | 120753077 | 015/094 | T2 DI STNSLS-MLNS-MNTC 15/94 COTR KEY | VICTOR | ETL.3830.INSL | 2021-04-06 | 2021-03-26 | 2021-05-26 | 2022-03-26 | 2021-06-24 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752178 | T2 DI STNSLS-MLNS-MNTC 15/94 COTR KEY | ICS
LC | 120754511 | 008/049 | T2 DI STNSLS-MLNS-MNTC 8/49 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-07 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752179 | T2 DI STNSLS-MLNS-MNTC 8/49 INS HRDS | ICS
LC | 120754514 | 019/123 | T2 DI STNSLS-MLNS-MNTC 19/123 INST HRDS | VICTOR | ETL.3830.INSL | 2021-04-07 | 2021-04-06 | 2021-05-28 | 2022-04-06 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752240 | T2 DI STNSLS-MLNS-MNTC 19/123 INST HRDS | ICS
LC | 120754655 | 004/025 | T2 DI STSLS-MLS SS-MTC #1 4/25 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-07 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752241 | T2 DI STSLS-MLS SS-MTC #1 4/25 INS HRDS | ICS
LC | 120756053 | 008/050 | T2 DI STNSLS-MLNS-MNTC 8/50 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-07 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752242 | T2 DI STNSLS-MLNS-MNTC 8/50 INS HRDS | ICS
LC | 120757244 | 010/128 | T2 EI WST PT-VALY SPRNGS 10/128 RPR GYWW | VICTOR | ETL.8350.POLE.NWOD | 2021-04-07 | 2021-04-07 | 2021-06-10 | 2022-04-07 | 2021-07-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44752243 | T2 EI WST PT-VALY SPRNGS 10/128 RPR GYWW | ICW
LC | 120757554 | 002/022 | T2 EI CRG VW-CSCDE 2/22 HRDS COTR KEY | TABLEMTN | ETL.1350.POLE.STPS | 2021-04-07 | 2021-04-07 | 2021-05-18 | 2022-04-07 | 2021-07-07 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Steel | Replace | 44738659 | T2 EI CRG VW-CSCDE 2/22 HRDS COTR KEY | ICS
LC | 120758357 | 004/064 | T2 EI PIT #1-HT CK #2-BNY 4/64 COTER KEY | TABLEMTN | ETL.7040.INSL.NCER | 2021-04-07 | 2021-04-07 | 2021-05-19 | 2022-04-07 | 2021-07-07 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44739881 | T2 EI PIT #1-HT CK #2-BNY 4/64 COTER KEY | ICW
LC | 120758375 | 028/005 | T2 EI GARBERVLE-LYTNVLE 28/5 COTR KEY | EUREKA | ETL.8365.POLE.WOOD | 2021-04-07 | 2021-04-07 | 2021-04-16 | 2022-04-07 | 2021-07-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44737829 | T2 EI GARBERVLE-LYTNVLE 28/5 COTR KEY | ICW
LC | 120758766 | 007/030 | T2 EI MORRO BAY-SLR SS#1 7/30 REPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-07 | 2021-04-07 | 2021-06-28 | 2022-04-07 | 2021-07-07 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535790 | T2 MORRO BAY-SLR SS#1 7/30 REPL INSS | 93K
LC | 120759062 | 021/136 | T2 DI STNLS-MLS S-MTC #1 21/136 RPR INSS | VICTOR | ETL.3830.INSL | 2021-04-07 | 2021-03-31 | 2021-05-28 | 2022-03-31 | 2021-06-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44752244 | T2 DI STNLS-MLS S-MTC #1 21/136 RPR INSS | ICS
LC | 120759764 | 001/008 | T2 DI STNSLS-MLNS-MNTC 1/8 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-07 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752245 | T2 DI STNSLS-MLNS-MNTC 1/8 INS HRDS | ICS
LC | 120759786 | 080/408 | T2 DI MALIN-RND MTN #2 80/408 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-04-07 | 2021-04-05 | 2021-06-25 | 2022-04-05 | 2021-07-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44739883 | T2 DI MALIN-RND MTN #2 80/408 RPR OPGW | ICS
LC | 120760282 | 010/124 | T2 EI WST PT-VALY SPRGS 10/124 RPR CONW | VICTOR | ETL.8350.POLE.WOOD | 2021-04-07 | 2021-04-07 | 2021-06-24 | 2022-04-07 | 2021-07-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Conductor-Wood | Repair | 44752246 | T2 EI WST PT-VALY SPRGS 10/124 RPR CONW | ICW
LC | 120761603 | 089/453A | T2 DI MALIN-RND MTN #2 89/453A RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-04-08 | 2021-04-05 | 2021-06-10 | 2022-04-05 | 2021-07-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44739882 | T2 DI MALIN-RND MTN #2 89/453A RPR OPGW | ICS
LC | 120762403 | 004/063 | T2 EI PIT #1HT CRK #2BNY 4/63 INSW CTR K | TABLEMTN | ETL.7040.INSL.NCER | 2021-04-08 | 2021-04-08 | 2021-05-04 | 2022-04-08 | 2021-07-08 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44739886 | T2 PIT #1-HT CRK #2-BRNY 4/63 INSW CTR K | ICW
LC | 120762979 | 013/134 | T2 EI RND MTN-CTTNWD #3 13/134 RPR INSS | TABLEMTN | ETL.5640.TOWR | 2021-04-08 | 2021-04-08 | 2021-06-12 | 2022-04-08 | 2021-07-08 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44795199 | T2 EI RND MTN-CTTNWD #3 13/134 RPR INSS | ICS
LC | 120763451 | 006/070 | T2 EI WST PNT-VALY SPRGS 6/70 FILL HOLE | VICTOR | ETL.8350.POLE.NWOD | 2021-04-08 | 2021-04-08 | 2021-06-10 | 2022-04-08 | 2021-07-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove | 44752247 | T2 EI WST PNT-VALY SPRGS 6/70 FILL HOLE | ICW
LC | 120764290 | 004/052 | T2 EI PIT #1-HT CRK #2-BRY 4/52 RPR INSW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-04-08 | 2021-04-08 | 2021-05-28 | 2022-04-08 | 2021-07-08 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44739890 | T2 PIT #1-HT CRK #2-BRNY 4/52 RPR INSW | ICW
LC | 120767106 | 000/003 | T2 DI STNSLS-MLS SS-MTC #1 0/3 INS WASHR | VICTOR | ETL.3830.TOWR | 2021-04-08 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-07 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752251 | T2 DI STNSLS-MLS SS-MTC #1 0/3 INS WASHR | ICS
LC | 120771596 | 003/034 | T2 EI PIT 1-HAT CRK 2-BRNY 3/34 RPR INSW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-04-09 | 2021-04-09 | 2021-05-18 | 2022-04-09 | 2021-07-09 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44752424 | T2 EI PIT 1-HAT CRK 2-BRNY 3/34 RPR INSW | ICW
LC | 120772783 | 007/043 | T2 DI STAN MEL #2 7/43 RPL DAMPS | VICTOR | ETL.3820.INSL.CERA | 2021-04-09 | 2021-04-06 | 2021-05-18 | 2022-04-06 | 2021-07-06 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 44752252 | T2 DI STAN MEL #2 7/43 RPL DAMPS | ICS
LC | 120785592 | 032/004 | T2 EI GRBRVLE-LYTNVL 32/4 COTR KEY | EUREKA | ETL.8365.POLE.NWOD | 2021-04-10 | 2021-04-08 | 2021-04-16 | 2022-04-08 | 2021-07-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44737832 | T2 EI GRBRVLE-LYTNVL 32/4 COTR KEY | ICW
LC | 120786606 | 021/290 | T2 EI CLAY-MARTEL 021/290 INS DAMW | VICTOR | ETL.8250.INSL.NCER | 2021-04-10 | 2021-04-10 | 2021-06-11 | 2022-04-10 | 2021-07-10 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 44752258 | T2 EI CLAY-MARTEL 021/290 INS DAMW | ICW
LC | 120787940 | 030/467 | T2 EI CLAY-MARTEL 030/467 INS DMPW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-05-28 | 2022-04-10 | 2021-07-10 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Wood | Install | 44752259 | T2 EI CLAY-MARTEL 030/467 INS DMPW | ICW
LC | 120787970 | 030/466 | T2 EI CLAY-MARTEL 030/466 INS DMPW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-05-28 | 2022-04-10 | 2021-07-10 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Missing | Damper-Wood | Install | 44752280 | T2 EI CLAY-MARTEL 030/466 INS DMPW | ICW
LC | 120787977 | 030/465 | T2 EI CLAY-MARTEL 030/465 INS DMPW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-10 | 2021-04-10 | 2021-05-28 | 2022-04-10 | 2021-07-10 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 44752281 | T2 EI CLAY-MARTEL 030/465 INS DMPW | ICW
LC | 120792914 | 013/078 | T2 DI STSLS-MLS S-MTC #1 13/78 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-09 | 2021-05-26 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752282 | T2 DI STSLS-MLS S-MTC #1 13/78 INS HRDS | ICS
LC | 120792974 | 016/101 | T2 DI SS-MLS SS-MTC #1 16/101 INS WASHR | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-09 | 2021-05-26 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752286 | T2 DI SS-MLS SS-MTC #1 16/101 INS WASHR | ICS
LC | 120792975 | 002/013 | T2 DI STSLS-MLS SS-MTC #1 2/13 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-12 | 2021-04-09 | 2021-05-25 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752287 | T2 DI STSLS-MLS SS-MTC #1 2/13 INS HRDS | ICS
LC | 120792977 | 005/034 | T2 DI STSLS-MLS SS-MTC #1 5/34 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-12 | 2021-04-09 | 2021-05-25 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752288 | T2 DI STSLS-MLS SS-MTC #1 5/34 INS HRDS | ICS
LC | 120793024 | 014/083 | T2 DI STAN MEL-RVRBNK JCT 14/83 RPR SPLS | VICTOR | ETL.3840.INSL | 2021-04-12 | 2021-04-09 | 2021-05-20 | 2022-04-09 | 2021-07-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 44752289 | T2 DI STAN MEL-RVRBNK JCT 14/83 RPR SPLS | ICS
LC | 120793161 | 016/095 | T2 DI STN ML SW ST-RVRBNK 16/95 RPR SPL | VICTOR | ETL.3840.INSL.CERA | 2021-04-12 | 2021-04-09 | 2021-05-20 | 2022-04-09 | 2021-07-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 44752290 | T2 DI STN ML SW ST-RVRBNK 16/95 RPR SPL | ICS
LC | 120793162 | 016/095 | T2 DI STN ML SW ST-RVRBNK 16/95 INS HWRS | VICTOR | ETL.3840.INSL.CERA | 2021-04-12 | 2021-04-09 | 2021-05-20 | 2022-04-09 | 2021-07-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752292 | T2 DI STN ML SW ST-RVRBNK 16/95 INS HWRS | ICS
LC | 120793164 | 016/099 | T2 DI STSLS-MLS SS-MTC #1 16/99 INS WASH | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-09 | 2021-05-26 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752293 | T2 DI STSLS-MLS SS-MTC #1 16/99 INS WASH | ICS
LC | 120793269 | 007/043 | T2 DI STAN MEL RVRBNK JCT 7/43 RPL DAMPS | VICTOR | ETL.3840.INSL.CERA | 2021-04-12 | 2021-04-06 | 2021-05-18 | 2022-04-06 | 2021-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 44752294 | T2 DI STAN MEL RVRBNK JCT 7/43 RPL DAMPS | ICS
LC | 120794216 | 030/461 | T2 EI CLAY-MARTEL 30/461 INS DMPW | VICTOR | ETL.8250.POLE.NWOD | 2021-04-12 | 2021-04-12 | 2021-05-28 | 2022-04-12 | 2021-07-12 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 44752296 | T2 EI CLAY-MARTEL 30/461 INS DMPW | ICW
LC | 120794312 | 013/077 | T2 DI STSLS-MLS SS-MTC #1 13/77 INS WASH | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-09 | 2021-05-26 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752297 | T2 DI STSLS-MLS SS-MTC #1 13/77 INS WASH | ICS
LC | 120794315 | 006/037 | T2 DI STSLS-MLS SS-MTC #1 6/37 INS WASH | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752298 | T2 DI STSLS-MLS SS-MTC #1 6/37 INS WASH | ICS
LC | 120794507 | 015/098 | T2 DI STSLS-MLS SS-MTC #1 15/98 INS WASH | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-09 | 2021-05-26 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752299 | T2 DI STSLS-MLS SS-MTC #1 15/98 INS WASH | ICS
LC | 120794508 | 015/098 | T2 DI STSLS-MLS SS-MTC #1 15/98 RPR INSS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-09 | 2021-05-26 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44752360 | T2 DI STSLS-MLS SS-MTC #1 15/98 RPR INSS | ICS
LC | 120794704 | 031/474 | T2 EI CLAY-MARTEL 31/474 INS DMPW | VICTOR | ETL.8250.INSL.NCER | 2021-04-12 | 2021-04-12 | 2021-05-29 | 2022-04-12 | 2021-07-12 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 44752361 | T2 EI CLAY-MARTEL 31/474 INS DMPW | ICW
LC | 120795145 | 015/090 | T2 DI STAN MEL-RVRBNK JCT 15/90 RPR INSS | VICTOR | ETL.3840.INSL.CERA | 2021-04-12 | 2021-04-09 | 2021-05-18 | 2022-04-09 | 2021-07-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44752363 | T2 DI STAN MEL-RVRBNK JCT 15/90 RPR INSS | ICS
LC | 120795299 | 005/032 | T2 DI STNLS-MLNS-MNTC 5/32 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-12 | 2021-04-09 | 2021-05-25 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752364 | T2 DI STNLS-MLNS-MNTC 5/32 INS HRDS | ICS
LC | 120795416 | 004/027 | T2 DI SLS-MLS SS-MTC #1 4/27 INS HRDS | VICTOR | ETL.3830.INSL.NCER | 2021-04-12 | 2021-04-06 | 2021-05-21 | 2022-04-06 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752365 | T2 DI SLS-MLS SS-MTC #1 4/27 INS HRDS | ICS
LC | 120795448 | 009/080 | T2 DI PARADISE-TABLE MTN 9/80 RPR INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-12 | 2021-04-09 | 2021-04-26 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44743860 | T2 DI PARADISE-TABLE MTN 9/80 RPR INSS | ICS
LC | 120795588 | 007/042 | T2 DI STANISLAUS-MTC #2 7/42 RPR SPLS | VICTOR | ETL.3820.INSL.NCER | 2021-04-12 | 2021-04-06 | 2021-05-18 | 2022-04-06 | 2021-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 44752366 | T2 DI STANISLAUS-MTC #2 7/42 RPR SPLS | ICS
LC | 120795690 | 007/042 | T2 DI STN MEL SW ST-RBNK 7/42 RPR SPLS | VICTOR | ETL.3840.INSL.NCER | 2021-04-12 | 2021-04-06 | 2021-05-18 | 2022-04-06 | 2021-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 44752367 | T2 DI STN MEL SW ST-RBNK 7/42 RPR SPLS | ICS
LC | 120795694 | 003/018 | T2 DI SLS-MLS SS-MTC #1 3/18 INS HRDT | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752368 | T2 DI SLS-MLS SS-MTC #1 3/18 INS HRDT | ICS
LC | 120795768 | 005/033 | T2 DI STANISLAUS-MANTC #2 5/33 INS HRDS | VICTOR | ETL.3820.TOWR | 2021-04-12 | 2021-04-09 | 2021-05-18 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752369 | T2 DI STANISLAUS-MANTC #2 5/33 INS HRDS | ICS
LC | 120795832 | 029/431 | T2 EI CLAY-MARTEL 29/431 RPLC STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-12 | 2021-04-12 | 2021-08-29 | 2022-04-12 | 2021-10-21 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548113 | T2 EI CLAY-MARTEL 29/431 RPLC STRW | 70Y
LC | 120796204 | 001/007 | T2 DI STNSLS-MLNS-MNTC#1 1/7 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-12 | 2021-04-09 | 2021-05-25 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752370 | T2 DI STNSLS-MLNS-MNTC#1 1/7 INS HRDS | ICS
LC | 120796709 | 014/084 | T2 DI STAN MEL-RVRBNK 14/84 RPR SPLS | VICTOR | ETL.3840.INSL.NCER | 2021-04-12 | 2021-04-09 | 2021-05-18 | 2022-04-09 | 2021-07-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 44752441 | T2 DI STAN MEL-RVRBNK 14/84 RPR SPLS | ICS
LC | 120796824 | 008/047 | T2 DI STANISLAUS-MANTEC #2 8/47 INS HRDT | VICTOR | ETL.3840.INSL.NCER | 2021-04-12 | 2021-04-06 | 2021-05-18 | 2022-04-06 | 2021-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752443 | T2 DI STANISLAUS-MANTEC #2 8/47 INS HRDT | ICS
LC | 120797278 | 031/475 | T2 EI CLAY-MARTEL 31/475 INS DMPW | VICTOR | ETL.8250.INSL.NCER | 2021-04-12 | 2021-04-12 | 2021-05-29 | 2022-04-12 | 2021-07-12 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 44752444 | T2 EI CLAY-MARTEL 31/475 INS DMPW | ICW
LC | 120798119 | 015/095 | T2 DI SLS-MLS SS-MTC #1 15/95 INS WASHER | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-09 | 2021-05-26 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752446 | T2 DI SLS-MLS SS-MTC #1 15/95 INS WASHER | ICS
LC | 120798433 | 014/085 | T2 DI SLS-MLS SS-MTC #1 14/85 INS WASHR | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-09 | 2021-05-26 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752447 | T2 DI SLS-MLS SS-MTC #1 14/85 INS WASHR | ICS
LC | 120799051 | 005/033 | T2 DI STNSLS-MLNS-MNTC 5/33 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-12 | 2021-04-09 | 2021-05-25 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752449 | T2 DI STNSLS-MLNS-MNTC 5/33 INS HRDS | ICS
LC | 120799372 | 033/500 | T2 EI CLAY-MARTEL 33/500 RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2021-04-12 | 2021-04-12 | 2021-04-19 | 2022-04-12 | 2021-07-12 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44752450 | T2 EI CLAY-MARTEL 33/500 RPR GYWW | ICW
LC | 120799530 | 021/122 | T2 STAN MEL SS-RVERBK J 21/122 REPL INSS | VICTOR | ETL.3840.INSL.NCER | 2021-04-12 | 2021-04-12 | 2021-05-20 | 2022-04-12 | 2021-07-12 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | REGW PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31535845 | T2 STANISLAUS-MANTECA #2 RPL INS 021/122 | 93K
LC | 120799867 | 011/080 | T2 DI VAC-VACVLL-JMSN-NTH 11/80 RPR INSS | LAKEVLLE | ETL.4100.INSL.NCER | 2021-04-12 | 2021-04-12 | 2021-04-27 | 2022-04-12 | 2021-07-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44744139 | T2 DI VAC-VCVL-JMSN-N. TWR 11/83 COTR KY | ICS
LC | 120800186 | :005/003 | T2 DI BLLT-RVRBNK-MLNS :5/3 RPR INSW | VICTOR | ETL.1070.INSL.NCER | 2021-04-12 | 2021-04-12 | 2021-06-16 | 2022-04-12 | 2021-07-11 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44752451 | T2 DI BLLT-RVRBNK-MLNS :5/3 RPR INSW | ICW
LC | 120800419 | 001/010 | T2 DI STAN MEL-RVBNK 1/10 RPR SPLS | VICTOR | ETL.3840.INSL.CERA | 2021-04-12 | 2021-04-12 | 2021-05-18 | 2022-04-12 | 2021-07-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 44752452 | T2 DI STAN MEL-RVBNK 1/10 RPR SPLS | ICS
LC | 120800637 | 015/091 | T2 DI STANISLAUS-MANTC #2 15/91 INS HRDS | VICTOR | ETL.3820.TOWR | 2021-04-12 | 2021-04-09 | 2021-05-18 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752453 | T2 DI STANISLAUS-MANTC #2 15/91 INS HRDS | ICS
LC | 120801308 | 005/031 | T2 DI STNSLS-MLNS-MNTC 5/31 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-12 | 2021-04-12 | 2021-05-25 | 2022-04-12 | 2021-07-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752454 | T2 DI STNSLS-MLNS-MNTC 5/31 INS HRDS | ICS
LC | 120801460 | 003/020 | T2 DI SLS-MLS SS-MTC #1 3/20 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-12 | 2021-04-12 | 2021-05-25 | 2022-04-12 | 2021-07-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752455 | T2 DI SLS-MLS SS-MTC #1 3/20 INS HRDS | ICS
LC | 120801462 | 020/126 | T2 DI SLS-MLS SS-MTC #1 20/126 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-12 | 2021-05-28 | 2022-04-12 | 2021-07-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752456 | T2 DI SLS-MLS SS-MTC #1 20/126 INS HRDS | ICS
LC | 120801582 | 011/083 | T2 DI VAC-VCVL-JMSN-N. TWR 11/83 COTR KY | LAKEVLLE | ETL.4100.INSL.NCER | 2021-04-12 | 2021-04-12 | 2021-04-27 | 2022-04-12 | 2021-07-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44744139 | T2 DI VAC-VCVL-JMSN-N. TWR 11/83 COTR KY | ICS
LC | 120801589 | 006/036 | T2 DI STNSLS-MLNS-MNTC 6/36 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-12 | 2021-05-25 | 2022-04-12 | 2021-07-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752458 | T2 DI STNSLS-MLNS-MNTC 6/36 INS HRDS | ICS
LC | 120801658 | 003/022 | T2 DI SLS-MLS SS-MTC #1 3/22 RPR SPLS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-12 | 2021-05-25 | 2022-04-12 | 2021-07-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 44764687 | T2 DI SLS-MLS SS-MTC #1 3/22 RPR SPLS | ICS
LC | 120801740 | 003/022 | T2 DI SLS-MLS SS-MTC #1 3/22 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-12 | 2021-05-25 | 2022-04-12 | 2021-07-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752459 | T2 DI SLS-MLS SS-MTC #1 3/22 INS HRDS | ICS
LC | 120801780 | 006/036 | T2 DI STNSLS-MLNS-MNTC 6/36 INS HRDT | VICTOR | ETL.3830.TOWR | 2021-04-12 | 2021-04-12 | 2021-04-21 | 2022-04-12 | 2021-07-12 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | Missing | Hardware-Tower | Install | 44752460 | T2 DI STNSLS-MLNS-MNTC 6/36 INS HRDT | ICQ
LC | 120801782 | 002/014 | T2 DI STNSLS-MLNS-MNTC 2/14 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-12 | 2021-04-12 | 2021-05-25 | 2022-04-12 | 2021-07-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752461 | T2 DI STNSLS-MLNS-MNTC 2/14 INS HRDS | ICS
LC | 120802088 | 031/476 | T2 EI CLAY-MARTEL 31/476 INS DMPW | VICTOR | ETL.8250.INSL.NCER | 2021-04-12 | 2021-04-12 | 2021-05-29 | 2022-04-12 | 2021-07-12 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Missing | Damper-Wood | Install | 44752462 | T2 EI CLAY-MARTEL 31/476 INS DMPW | ICW
LC | 120803493 | C025/101 | T2 DI MOSS LNDNG-AGUILA C25/101 COTR KEY | MOSSLNDG | ETL.4460.INSL | 2021-04-13 | 2021-04-12 | 2021-04-29 | 2022-04-12 | 2021-07-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44760646 | T2 DI MOSS LNDNG-AGUILA C25/101 COTR KEY | ICS
LC | 120803574 | 006/012 | T2 DI BRCBRG JCT-MARPSA TP 6/12 COTR KEY | FRESNO | ETL.8651.INSL.CERA | 2021-04-13 | 2021-04-12 | 2021-05-19 | 2022-04-12 | 2021-07-11 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44752574 | T2 DI BRCBRG JCT-MARPSA TP 6/12 COTR KEY | ICW
LC | 120803951 | 003/023 | T2 DI STNSLS-MLS SS-MTC #1 3/23 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-13 | 2021-04-12 | 2021-05-25 | 2022-04-12 | 2021-07-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752463 | T2 DI STNSLS-MLS SS-MTC #1 3/23 INS HRDS | ICS
LC | 120804616 | 020/128 | T2 DI STNSLS-MLNS-MNTC#1 20/128 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-13 | 2021-04-12 | 2021-05-25 | 2022-04-12 | 2021-07-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752464 | T2 DI STNSLS-MLNS-MNTC#1 20/128 INS HRDS | ICS
LC | 120806900 | :004/004 | T2 DI BLT-RVRBNK-MLNS :4/4 RPLC INSW | VICTOR | ETL.1070.INSL.CERA | 2021-04-13 | 2021-04-12 | 2021-06-16 | 2022-04-12 | 2021-07-12 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31536100 | T2 DI BLT-RVRBNK-MLNS :4/4 RPLC INSW | 93I
LC | 120807115 | C019/077 | T2 DI MOSS LANDING-CBRN C19/77 COTR KEY | MOSSLNDG | ETL.5330.INSL | 2021-04-13 | 2021-04-13 | 2021-06-30 | 2022-04-13 | 2021-07-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44744689 | T2 DI MOSS LANDING-CBRN C19/77 COTR KEY | ICS
LC | 120807544 | 002/015 | T2 DI STNSLS-MLNS-MNTC 2/15 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-13 | 2021-04-12 | 2021-05-25 | 2022-04-12 | 2021-07-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752465 | T2 DI STNSLS-MLNS-MNTC 2/15 INS HRDS | ICS
LC | 120807684 | 014/087 | T2 DI STNLS-MLS SS-MTC #1 14/87 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-13 | 2021-04-12 | 2021-05-26 | 2022-04-12 | 2021-07-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752467 | T2 DI STNLS-MLS SS-MTC #1 14/87 INS HRDS | ICS
LC | 120807808 | 000/002 | T2 DI STNSLS-MLS SS-MTC #1 0/2 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-13 | 2021-04-13 | 2021-05-25 | 2022-04-13 | 2021-07-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752468 | T2 DI STNSLS-MLS SS-MTC #1 0/2 INS HRDS | ICS
LC | 120807976 | 036/168 | T2 DI IGNACIO-SOBRANTE 036/168 COTR KEY | LAKEVLLE | ETL.4920.INSL.CERA | 2021-04-13 | 2021-04-13 | 2021-05-22 | 2022-04-13 | 2021-07-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44744136 | T2 DI IGNACIO-SOBRANTE 036/168 COTR KEY | ICS
LC | 120808028 | 022/014B | T2 HARTLEY-CLEARLAKE 22/014B RPR SWITCH | LAKEVLLE | ETL.7515.SWIT | 2021-04-13 | 2021-04-13 | 2021-07-10 | 2022-04-13 | 2021-07-13 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Out of Adjustment | Switch | Repair | 44744329 | T2 HARTLEY-CLEARLAKE 22/014B RPR SWITCH | ICE
LC | 120810632 | 040/344 | T2 EI RND MTN-CTTNWD #3 40/344 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-04-14 | 2021-04-13 | 2021-07-06 | 2022-04-13 | 2021-07-13 | On-time | 532 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31537449 | T2 EI RND MTN-CTTNWD #3 40/344 RPL INSS. | 93K
LC | 120810635 | 040/342 | T2 EI ROUND MT-CTTNWD#3 40/342 RPR TWR | TABLEMTN | ETL.5650.TOWR | 2021-04-14 | 2021-04-13 | 2021-06-07 | 2022-04-13 | 2021-07-13 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair | 44765004 | T2 EI ROUND MT-CTTNWD#3 40/342 RPR TWR | ICQ
LC | 120810637 | 041/352 | T2 EI RND MTN-CTTNWD #3 41/352 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-04-14 | 2021-04-13 | 2021-07-06 | 2022-04-13 | 2021-07-13 | On-time | 532 | Upgraded | Closed | HFTD 2 | REGW INSP PATR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31537449 | T2 EI RND MTN-CTTNWD #3 40/344 RPL INSS. | 93K
LC | 120810657 | 001/012 | T2 DI STNSLS-MLS SS-MTC #1 1/12 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-14 | 2021-04-13 | 2021-05-25 | 2022-04-13 | 2021-07-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752469 | T2 DI STNSLS-MLS SS-MTC #1 1/12 INS HRDS | ICS
LC | 120810833 | 031/004 | T2 EI GARBERVILLE-LAYTONVL 31/4 COTR KEY | EUREKA | ETL.8365.POLE.WOOD | 2021-04-14 | 2021-04-12 | 2021-04-27 | 2022-04-12 | 2021-07-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44754885 | T2 EI GARBERVILLE-LAYTONVL 31/4 COTR KEY | ICW
LC | 120811017 | 005/028 | T2 DI FULTON-PUEBLO 5/28 INST COTR KEY | LAKEVLLE | ETL.1600.INSL.CERA | 2021-04-14 | 2021-04-13 | 2021-05-04 | 2022-04-13 | 2021-07-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44747345 | T2 DI FULTON-PUEBLO 5/28 INST COTR KEY | ICS
LC | 120811082 | 007/059 | T2 DI EL DRDO-MSSR FLT #1 7/59 COTR RKEY | SACTO | ETL.1530.INSL | 2021-04-14 | 2021-04-13 | 2021-04-23 | 2022-04-13 | 2021-07-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44752890 | T2 DI EL DRDO-MSSR FLT #1 7/59 COTR RKEY | ICS
LC | 120811166 | 018/022 | T2 EI TULE-SPRINGVILL 18/22 REPL POLE | MIDWAY | ETL.9040.POLE.WOOD | 2021-04-14 | 2021-04-12 | 2022-07-25 | 2022-04-12 | 2022-04-12 | Late | 372 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536427 | T2 EI TULE-SPRINGVILL 18/22 REPL POLE | 70Y
LC | 120811798 | 003/028 | T2 EI MORAGA-OAKLAND #1 3/28 INST ACG | CONCORD | ETL.2720.TOWR | 2021-04-14 | 2021-04-14 | 2021-04-21 | 2022-04-14 | 2021-07-14 | On-time | 988 | Upgraded | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Anti-Climbing Guard | Structure-Tower | Repair | 31536657 | EI MORAGA-OAKLAND #1 3/28 INST ACG | 93A
LC | 120813257 | :023/122 | T2 DI CRZY HS CYN-SLS-SLD :23/122 RP INS | MOSSLNDG | ETL.2910.INSL.CERA | 2021-04-14 | 2021-04-13 | 2021-05-05 | 2022-04-13 | 2021-07-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44752279 | T2 DI CRZY HS CYN-SLS-SLD :23/122 RP INS | ICS
LC | 120815796 | 008/074 | T2 EI PARADISE-TABLE MTN 8/74 INS CTR KY | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-14 | 2021-04-14 | 2021-04-26 | 2022-04-14 | 2021-07-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44761484 | T2 EI PARADISE-TABLE MTN 8/74 INS CTR KY | ICS
LC | 120818961 | 019/448 | T2 EI DRM-GRSS VLY-WMR 19/448 GO95 CLRNC | SACTO | ETL.6760.POLE.WOOD | 2021-04-15 | 2021-04-15 | 2021-06-03 | 2022-04-15 | 2021-07-14 | On-time | 401 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE CLR COMP OH TR2 PRTO | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31536122 | T2 DRM-GRSS VLY-WEIMAR-19/448 GO95 CLRNC | 93G
LC | 120819130 | 002/015 | T2 DI IONE TAP 002/015 RPL STRW | VICTOR | ETL.8253.POLE.WOOD | 2021-04-15 | 2021-04-13 | 2021-04-30 | 2022-04-13 | 2021-07-12 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31536285 | T2 DI IONE TAP 002/015 RPL STRW | 70Y
LC | 120820591 | 000/002 | T2 EI COLGATE-ALLEGHANY 000/002 RPR JMPW | SACTO | ETL.6470.INSL.NCER | 2021-04-15 | 2021-04-15 | 2021-07-08 | 2022-04-15 | 2021-07-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Jumper-Wood | Repair | 44752899 | T2 EI COLGATE-ALLEGHANY 000/002 RPR JMPW | ICW
LC | 120820592 | 000/003C | T2 EI COLGATE-ALLEGHANY 0/3C RPR INSW | SACTO | ETL.6470.POLE.WOOD | 2021-04-15 | 2021-04-15 | 2021-07-08 | 2022-04-15 | 2021-07-15 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44755287 | T2 EI COLGATE-ALLEGHANY 0/3C RPR INSW | ICW
LC | 120824145 | 015/177 | T2 IGNACIO-BOLINAS 15/177 RPR SWTC | LAKEVLLE | ETL.7180.SWIT | 2021-04-15 | 2021-04-15 | 2021-05-04 | 2022-04-15 | 2021-07-15 | On-time | 623 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Out of Adjustment | Switch | Repair | 44758494 | IGNACIO-BOLINAS 15/177 RPR SWTC | ICE
LC | 120824235 | 029/213 | T2 EI DRUM-RIO OSO #1 29/213 COTTER KEY | SACTO | ETL.1420.INSL.CERA | 2021-04-15 | 2021-04-15 | 2021-07-07 | 2022-04-15 | 2021-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44752880 | T2 EI DRUM-RIO OSO #1 29/213 COTTER KEY | ICS
LC | 120824357 | 007/134 | T2 EI TEJON-LEBEC 7/134 RMV NEST | MIDWAY | ETL.9250.POLE.WOOD | 2021-04-15 | 2021-04-15 | 2021-08-05 | 2022-04-15 | 2021-07-15 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Structure-Wood | Remove | 44817947 | T2 EI TEJON-LEBEC 7/134 RMV NEST | ICW
LC | 120825089 | 036/211 | T2 DI TMBLR-SN LS OBISPO 36/211 RPR INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-16 | 2021-04-15 | 2021-05-10 | 2022-04-15 | 2021-07-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44766876 | T2 DI TMBLR-SN LS OBISPO 36/211 RPR INSS | ICS
LC | 120826140 | B015/354 | T2 EI DRUM-GRSS VALY-WMR B15/354 COTR KY | SACTO | ETL.6760.POLE.NWOD | 2021-04-16 | 2021-04-15 | 2021-05-13 | 2022-04-15 | 2021-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44752902 | T2 EI DRUM-GRSS VALY-WMR B15/354 COTR KY | ICS
LC | 120827201 | 011/097 | T2 DI PARADISE-TABLE MTN 11/97 RPR INSS | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-16 | 2021-04-15 | 2021-04-26 | 2022-04-15 | 2021-07-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44751981 | T2 DI PARADISE-TABLE MTN 11/97 RPR INSS | ICS
LC | 120827677 | :024/124 | T2 DI CZY HRS CYN-SLS :24/124 RPR INSS | MOSSLNDG | ETL.2910.INSL.CERA | 2021-04-16 | 2021-04-13 | 2021-05-05 | 2022-04-13 | 2021-07-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44753109 | T2 DI CZY HRS CYN-SLS :24/124 RPR INSS | ICS
LC | 120828354 | 012/073 | T2 DI STANISLAUS-MNTC #2 12/73 RPR STRT | VICTOR | ETL.3820.TOWR | 2021-04-16 | 2021-04-16 | 2021-04-21 | 2022-04-16 | 2021-07-15 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair | 44752567 | T2 DI STANISLAUS-MNTC #2 12/73 RPR STRT | ICQ
LC | 120828495 | A013/262 | T2 DI COLGATE-PALERMO A13/262 COTR KEY | TABLEMTN | ETL.6500.INSL.NCER | 2021-04-16 | 2021-04-15 | 2021-05-27 | 2022-04-15 | 2021-07-14 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44752900 | T2 DI COLGATE-PALERMO A13/262 COTR KEY | ICW
LC | 120828539 | 020/006 | T2 TULE-SPRINGVILLE 20/6 REPL POLE | MIDWAY | ETL.9040.POLE.WOOD | 2021-04-16 | 2021-04-16 | 2021-08-20 | 2022-04-16 | 2021-07-16 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536286 | T2 TULE-SPRINGVILLE 20/6 REPL POLE | 70Y
LC | 120829347 | 013/080 | T2 DI STNISLS-MLNS-MNTC 13/80 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-16 | 2021-04-16 | 2021-05-26 | 2022-04-16 | 2021-07-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44752570 | T2 DI STNISLS-MLNS-MNTC 13/80 INS HRDS | ICS
LC | 120830263 | 000/009 | T2 EI SALT SPRINGS-TIGER CRK 0/9 RPR TWR | VICTOR | ETL.3500.TOWR | 2021-04-16 | 2021-04-16 | 2021-04-20 | 2022-04-16 | 2021-07-16 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 44750219 | T2 EI SALT SPRINGS-TIGER CRK 0/9 RPR TWR | ICQ
LC | 120831735 | 013/080 | T2 DI STN ML SW ST-RVRBNK 13/80 INS HRDS | VICTOR | ETL.3840.INSL.CERA | 2021-04-16 | 2021-04-16 | 2021-05-18 | 2022-04-16 | 2021-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44764688 | T2 DI STN ML SW ST-RVRBNK 13/80 INS HRDS | ICS
LC | 120831864 | 032/211 | T2 DI POE-RIO OSO 032/211 RPL INSS | TABLEMTN | ETL.5540.INSL.CERA | 2021-04-16 | 2021-04-15 | 2021-06-11 | 2022-04-15 | 2021-07-14 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536365 | T2 DI POE-RIO OSO RPL INSS 2TWR | 93K
LC | 120833012 | 003/033 | T2 DI SLT SPRNGS-TGR CRK 3/33 COTR KEY | VICTOR | ETL.3500.INSL | 2021-04-17 | 2021-04-16 | 2021-07-07 | 2022-04-16 | 2021-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44764689 | T2 DI SLT SPRNGS-TGR CRK 3/33 COTR KEY | ICS
LC | 120833016 | 014/083 | T2 DI STNSLS-MLNS-MNTC 14/83 RPLC HRDS | VICTOR | ETL.3830.INSL | 2021-04-17 | 2021-04-16 | 2021-05-26 | 2022-04-16 | 2021-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Steel | Replace | 44764690 | T2 DI STNSLS-MLNS-MNTC 14/83 RPLC HRDS | ICS
LC | 120833071 | 007/004 | T2 DI OAKHURST TAP 7/4 INST COTR KEY | FRESNO | ETL.1252.INSL.NCER | 2021-04-17 | 2021-04-16 | 2021-05-27 | 2022-04-16 | 2021-07-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44772598 | T2 DI OAKHURST TAP 7/4 INST COTR KEY | ICW
LC | 120833077 | 006/048 | T2 DI ELDORADO-MSR FLT #2 6/48 COTR KEY | SACTO | ETL.1540.INSL.CERA | 2021-04-17 | 2021-04-16 | 2021-07-06 | 2022-04-16 | 2021-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44752896 | T2 DI ELDORADO-MSR FLT #2 6/48 COTR KEY | ICS
LC | 120833079 | 006/048 | T2 DI ELDORADO-MSR FLT #1 6/48 COTR KEY | SACTO | ETL.1530.INSL.CERA | 2021-04-17 | 2021-04-16 | 2021-07-06 | 2022-04-16 | 2021-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44752891 | T2 DI ELDORADO-MSR FLT #1 6/48 COTR KEY | ICS
LC | 120833126 | 014/082 | T2 DI STNLS-MLS SS-MTC #1 14/82 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-17 | 2021-04-16 | 2021-05-26 | 2022-04-16 | 2021-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44764692 | T2 DI STNLS-MLS SS-MTC #1 14/82 INS HRDS | ICS
LC | 120833127 | 024/162 | T2 DI POE-RIO OSO 024/162 RPR INSS | TABLEMTN | ETL.5540.INSL.CERA | 2021-04-17 | 2021-04-15 | 2021-06-12 | 2022-04-15 | 2021-07-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44795224 | T2 DI POE-RIO OSO 024/162 RPR INSS | ICS
LC | 120833210 | 027/117A | T2 DI MR BY-SLR SW ST #1 27/117A COTR KY | PISMOBCH | ETL.5300.INSL.NCER | 2021-04-17 | 2021-04-16 | 2021-05-10 | 2022-04-16 | 2021-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44766877 | T2 DI MR BY-SLR SW ST #1 27/117A COTR KY | ICS
LC | 120834554 | 012/098 | T2 EI PIT #3-PIT #1 12/098 RPR SPLS | TABLEMTN | ETL.5400.TOWR | 2021-04-17 | 2021-04-17 | 2021-05-25 | 2022-04-17 | 2021-07-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Repair | 44795197 | T2 EI PIT #3-PIT #1 12/098 RPR SPLS | ICS
LC | 120834963 | 080/411 | T2 EI MALIN-ROUND MTN #2 80/411 COTR KEY | TABLEMTN | ETL.6020.TOWR | 2021-04-17 | 2021-04-17 | 2021-06-04 | 2022-04-17 | 2021-07-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44774835 | T2 EI MALIN-ROUND MTN #2 80/411 COTR KEY | ICS
LC | 120835116 | 011/094 | T2 EI PIT #3-PIT #1 11/094 COTR KEY | TABLEMTN | ETL.5400.TOWR | 2021-04-17 | 2021-04-17 | 2021-05-25 | 2022-04-17 | 2021-07-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44795192 | T2 EI PIT #3-PIT #1 11/094 COTR KEY | ICS
LC | 120839730 | 012/090 | T2 DI WISHON-COPPERMINE 012/090 COTR KEY | FRESNO | ETL.9330.INSL.NCER | 2021-04-19 | 2021-04-16 | 2021-06-14 | 2022-04-16 | 2021-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772599 | T2 DI WISHON-COPPERMINE 012/090 COTR KEY | ICS
LC | 120839802 | 030/183 | T2 DI HELMS-GREGG #2 030/183 COTR KEY | FRESNO | ETL.4880.INSL | 2021-04-19 | 2021-04-16 | 2021-04-28 | 2022-04-16 | 2021-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44764315 | T2 DI HELMS-GREGG #2 030/183 COTR KEY | ICS
LC | 120840874 | 066/331 | T2 EI MALIN-ROUND MTN #2 66/331 COTR KEY | TABLEMTN | ETL.6020.TOWR | 2021-04-19 | 2021-04-19 | 2021-05-11 | 2022-04-19 | 2021-07-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44774834 | T2 EI MALIN-ROUND MTN #2 66/331 COTR KEY | ICS
LC | 120841130 | 005/035 | T2 DI STNSLS-MLNS-MNTC 5/35 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-19 | 2021-04-09 | 2021-05-25 | 2022-04-09 | 2021-07-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44764694 | T2 DI STNSLS-MLNS-MNTC 5/35 INS HRDS | ICS
LC | 120841930 | 012/095 | T2 EI PIT #1-COTTONWOOD 12/095 COTR KEY | TABLEMTN | ETL.5390.TOWR | 2021-04-19 | 2021-04-19 | 2021-05-25 | 2022-04-19 | 2021-07-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44795195 | T2 EI PIT #1-COTTONWOOD 12/095 COTR KEY | ICS
LC | 120842454 | 031/184 | T2 DI HELMS-GREGG #1 31/184 RPR SHLS | FRESNO | ETL.4870.TOWR | 2021-04-19 | 2021-04-19 | 2021-04-27 | 2022-04-19 | 2021-07-18 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44764316 | T2 DI HELMS-GREGG #1 31/184 RPR SHLS | ICS
LC | 120842947 | 002/015 | T2 DI STN ML SW ST-RK JT 2/15 RPL INSS | VICTOR | ETL.3840.INSL.CERA | 2021-04-19 | 2021-04-12 | 2021-05-18 | 2022-04-12 | 2021-07-12 | On-time | 532 | Upgraded | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31537188 | T2 DI STAN MEL-RVRBNK JC RPLC INSS 2TWR | 93K
LC | 120843370 | 007/055 | T2 DI EL DRD-MSSR FLT #2 7/55 RPR INSS | SACTO | ETL.1540.INSL | 2021-04-19 | 2021-04-16 | 2021-04-23 | 2022-04-16 | 2021-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44756748 | T2 DI EL DRD-MSSR FLT #2 7/55 RPR INSS | ICS
LC | 120843374 | 007/055 | T2 DI EL DRD-MSSR FLT #1 7/55 RPR INSS | SACTO | ETL.1530.INSL | 2021-04-19 | 2021-04-16 | 2021-04-23 | 2022-04-16 | 2021-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44756747 | T2 DI EL DRD-MSSR FLT #1 7/55 RPR INSS | ICS
LC | 120844779 | 022/148 | T2 DI HELMS-GREGG #2 22/148 CANCEL | FRESNO | ETL.4880.INSL | 2021-04-19 | 2021-04-19 | 2021-06-01 | 2022-04-19 | 2021-07-18 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44764317 | T2 DI HELMS-GREGG #2 22/148 RPR INSS | ICS
LC | 120844842 | 022/148 | T2 DI HELMS-GREGG #1 22/148 RPR INSS | FRESNO | ETL.4870.INSL | 2021-04-19 | 2021-04-19 | 2021-06-01 | 2022-04-19 | 2021-07-18 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44764318 | T2 DI HELMS-GREGG #1 22/148 RPR INSS | ICS
LC | 120845276 | 014/085 | T2 DI STAN MEL-RVRBNK JC 14/85 RPLC INSS | VICTOR | ETL.3840.INSL.NCER | 2021-04-19 | 2021-04-09 | 2021-05-18 | 2022-04-09 | 2021-07-09 | On-time | 532 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31537188 | T2 DI STAN MEL-RVRBNK JC RPLC INSS 2TWR | 93K
LC | 120847143 | 009/006 | T2 EI EXCHQUR-MARIPS 9/6 RPR INSW | FRESNO | ETL.8640.POLE.NWOD | 2021-04-19 | 2021-04-19 | 2021-07-15 | 2022-04-19 | 2021-07-19 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44772680 | T2 EI EXCHQUR-MARIPS 9/6 RPR INSW | ICW
LC | 120849392 | 014/084 | T2 DI STSLS-MLS SS-MTC #1 14/84 INS HRDS | VICTOR | ETL.3830.TOWR | 2021-04-20 | 2021-04-16 | 2021-05-26 | 2022-04-16 | 2021-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44764697 | T2 DI STSLS-MLS SS-MTC #1 14/84 INS HRDS | ICS
LC | 120849705 | 009/009 | T2 DI TRINITY-MAPLE CREEK 9/9 COTR KEY | EUREKA | ETL.8170.POLE.WOOD | 2021-04-20 | 2021-04-19 | 2021-06-07 | 2022-04-19 | 2021-07-18 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44763331 | T2 DI TRINITY-MAPLE CREEK 9/9 COTR KEY | ICW
LC | 120850641 | 038/331 | T2 EI ROUND MT-CTNWD#3 38/331 RPR TWR | TABLEMTN | ETL.5650.TOWR | 2021-04-20 | 2021-04-20 | 2021-07-08 | 2022-04-20 | 2021-07-20 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair | 44765008 | T2 EI ROUND MT-CTNWD#3 38/331 RPR TWR | ICQ
LC | 120854494 | 001/017 | T2 EI SLT SPRINGS-TGR CREK 1/17 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-20 | 2021-04-20 | 2022-06-21 | 2022-04-20 | 2022-04-20 | Late | 532 | Upgraded | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31580615 | T2 DI ST SPNGS TGR CK RPL INSS 4TWRS | 93K
LC | 120854495 | 001/018 | T2 EI SALT SPGS-TIGER CRK 1/18 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-20 | 2021-04-20 | 2021-07-07 | 2022-04-20 | 2021-07-20 | On-time | 532 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31537145 | T2 EI SALT SPGS-TIGER CRK 1/18 RPL INSS | 93K
LC | 120854571 | 002/020 | T2 EI SALT SPRNGS-TGR CREK 2/20 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-20 | 2021-04-20 | 2022-06-21 | 2022-04-20 | 2022-04-20 | Late | 532 | Upgraded | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540431 | T2 EI SALT SPRNGS-TGR CREK RPL INSS 18TW | 93K
LC | 120857292 | C020/082 | T2 DI MSS LANDING-COBURN C20/82 RPL INSS | MOSSLNDG | ETL.5330.INSL | 2021-04-21 | 2021-04-20 | 2021-06-30 | 2022-04-20 | 2021-07-19 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536806 | T2 DI MSS LANDING-COBURN C20/82 RPL INSS | 93K
LC | 120857536 | 017/119 | T2 DI HELMS-GREGG #1 017/119 RPR INSS | FRESNO | ETL.4870.INSL | 2021-04-21 | 2021-04-20 | 2021-06-11 | 2022-04-20 | 2021-07-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44764319 | T2 DI HELMS-GREGG #1 017/119 RPR INSS | ICS
LC | 120857730 | 019/112 | T2 EI STN ML SW ST-RV JT 19/112 INS WSHR | VICTOR | ETL.3840.INSL.NCER | 2021-04-21 | 2021-04-21 | 2021-05-20 | 2022-04-21 | 2021-07-21 | On-time | 543 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Missing | Hardware-Tower | Install | 44764763 | T2 EI STN ML SW ST-RV JT 19/112 INS WSHR | ICQ
LC | 120857762 | :016/084 | T2 DI CHC-SAL-SOL :16/84 COTR KEY | MOSSLNDG | ETL.2910.INSL.CERA | 2021-04-21 | 2021-04-20 | 2021-05-05 | 2022-04-20 | 2021-07-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44760651 | T2 DI CHC-SAL-SOL :16/84 COTR KEY | ICS
LC | 120858196 | 009/072 | T2 DI SLT SPRNGS-TGR CRK 9/72 RPR SPLS | VICTOR | ETL.3500.INSL | 2021-04-21 | 2021-04-20 | 2021-07-07 | 2022-04-20 | 2021-07-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Repair | 44764764 | T2 DI SLT SPRNGS-TGR CRK 9/72 RPR SPLS | ICS
LC | 120858669 | 004/033 | T2 DI ELDORADO-MSR FLT #2 4/33 RPR INSS | SACTO | ETL.1540.INSL | 2021-04-21 | 2021-04-20 | 2021-04-23 | 2022-04-20 | 2021-07-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44764386 | T2 DI ELDORADO-MSR FLT #2 4/33 RPR INSS | ICS
LC | 120858720 | 004/033 | T2 DI ELDORADO-MSR FLT #1 4/33 RPR INSS | SACTO | ETL.1530.INSL | 2021-04-21 | 2021-04-20 | 2021-04-23 | 2022-04-20 | 2021-07-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44764916 | T2 DI ELDORADO-MSR FLT #1 4/33 RPR INSS | ICS
LC | 120859129 | 005/040 | T2 DI EL DRD-MSSR FLT #2 5/40 RPR INSS | SACTO | ETL.1540.INSL | 2021-04-21 | 2021-04-20 | 2021-04-23 | 2022-04-20 | 2021-07-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44764385 | T2 DI EL DRD-MSSR FLT #2 5/40 RPR INSS | ICS
LC | 120860997 | 016/118 | T2 DI HELMS-GREGG #1 16/118 RPR SHLS | FRESNO | ETL.4870.TOWR | 2021-04-21 | 2021-04-20 | 2021-06-11 | 2022-04-20 | 2021-07-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44764680 | T2 DI HELMS-GREGG #1 16/118 RPR SHLS | ICS
LC | 120860998 | 016/118 | T2 DI HELMS-GREGG #2 16/118 RPR INSS | FRESNO | ETL.4880.INSL | 2021-04-21 | 2021-04-20 | 2021-06-11 | 2022-04-20 | 2021-07-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44764681 | T2 DI HELMS-GREGG #2 16/118 RPR INSS | ICS
LC | 120860999 | 005/051 | T2 DI PARADISE-TABLE MTN 005/051 COTR KY | TABLEMTN | ETL.4316.INSL.CERA | 2021-04-21 | 2021-04-21 | 2021-05-03 | 2022-04-21 | 2021-07-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44761483 | T2 DI PARADISE-TABLE MTN 005/051 COTR KY | ICS
LC | 120861176 | :021/112 | T2 DI CHC-SAL-SOL :21/112 BENT STEEL | MOSSLNDG | ETL.2900.INSL.CERA | 2021-04-21 | 2021-04-20 | 2021-07-18 | 2022-04-20 | 2021-07-19 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Tower | Repair | 44763186 | T2 DI CHC-SAL-SOL :21/112 BENT STEEL | ICQ
LC | 120861324 | 018/125 | T2 DI HELMS-GREGG #1 018/125 RPR INSS | FRESNO | ETL.4870.INSL | 2021-04-21 | 2021-04-21 | 2021-06-11 | 2022-04-21 | 2021-07-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44764682 | T2 DI HELMS-GREGG #1 018/125 RPR INSS | ICS
LC | 120861541 | 003/028 | T2 DI MORAGA-OAKLAND #3 3/28 RPR INSS | CONCORD | ETL.2740.INSL.NCER | 2021-04-21 | 2021-04-21 | 2021-05-31 | 2022-04-21 | 2021-07-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44764514 | T2 DI MORAGA-OAKLAND #3 3/28 RPR INSS | ICS
LC | 120861597 | 008/070 | T2 DI SLT SPRNGS-TGR CREEK 8/70 RPR INSS | VICTOR | ETL.3500.INSL | 2021-04-21 | 2021-04-20 | 2021-07-06 | 2022-04-20 | 2021-07-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44764765 | T2 DI SLT SPRNGS-TGR CREEK 8/70 RPR INSS | ICS
LC | 120862374 | 004/035 | T2 EI SALT SPRNGS-TGR CREK 4/35 RPL INSS | VICTOR | ETL.3500.INSL | 2021-04-21 | 2021-04-21 | 2022-06-18 | 2022-04-21 | 2022-04-21 | Late | 532 | Upgraded | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540431 | T2 EI SALT SPRNGS-TGR CREK RPL INSS 18TW | 93K
LC | 120863603 | 039/223 | T2 DI TMBLR-SN LS OBISPO 39/223 RPR INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-22 | 2021-04-21 | 2021-05-10 | 2022-04-21 | 2021-07-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44766875 | T2 DI TMBLR-SN LS OBISPO 39/223 RPR INSS | ICS
LC | 120863891 | 008/010 | T2 DI SALINAS-FORT ORD #1 8/10 RPL INSS | MOSSLNDG | ETL.7890.INSL.NCER | 2021-04-22 | 2021-04-21 | 2021-06-04 | 2022-04-21 | 2021-07-20 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31537148 | T2 DI SALINAS-FORT ORD #2 8/10 RPL INSS | 93K
LC | 120864073 | 001/011 | T2 DI MENDOCINO-WILLITS 1/11 RPR JUMP | LAKEVLLE | ETL.7540.POLE.NWOD | 2021-04-22 | 2021-04-21 | 2021-04-28 | 2022-04-21 | 2021-07-20 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Jumper-Wood | Repair | 44763986 | T2 DI MENDOCINO-WILLITS 1/11 RPR JUMP | ICW
LC | 120864572 | 017/095 | T2 DI BALCH-MCCALL 17/95 RPL INSS | FRESNO | ETL.4350.INSL | 2021-04-22 | 2021-04-21 | 2021-05-24 | 2022-04-21 | 2021-07-20 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31537142 | T2 DI BALCH-MCCALL 17/95 RPL INSS | 93K
LC | 120864579 | 037/248 | T2 DI CRESTA-RIO OSO 037/248 RPR INSS | TABLEMTN | ETL.4590.INSL.CERA | 2021-04-22 | 2021-04-21 | 2021-07-08 | 2022-04-21 | 2021-07-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44795233 | T2 DI CRESTA-RIO OSO 037/248 RPR INSS | ICS
LC | 120864704 | 037/244 | T2 DI CRESTA-RIO OSO 37/244 RPL INSS | TABLEMTN | ETL.4590.INSL.CERA | 2021-04-22 | 2021-04-21 | 2021-07-16 | 2022-04-21 | 2021-07-20 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31537150 | T2 DI CRESTA-RIO OSO RPL INSS 2TWR | 93K
LC | 120864708 | 035/262 | T2 DI CARIBOU-TABLE MTN 35/262 RPR INSS | TABLEMTN | ETL.4440.INSL | 2021-04-22 | 2021-04-21 | 2021-04-30 | 2022-04-21 | 2021-07-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44770602 | T2 DI CARIBOU-TABLE MTN 35/262 RPR INSS | ICS
LC | 120864709 | 009/000 | T2 DI SALINAS-FORT ORD #1 9/0 RPL INSS | MOSSLNDG | ETL.7890.INSL.CERA | 2021-04-22 | 2021-04-21 | 2021-06-04 | 2022-04-21 | 2021-07-21 | On-time | 532 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31537147 | T2 DI SALINAS-FORT ORD #1 9/0 RPL INSS | 93K
LC | 120864749 | 037/248 | T2 DI CRESTA-RIO OSO 037/248 RPL INSS | TABLEMTN | ETL.4590.INSL.CERA | 2021-04-22 | 2021-04-21 | 2021-07-08 | 2022-04-21 | 2021-07-21 | On-time | 532 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546556 | T2 DI CRESTA-RIO OSO 037/248 RPL INSS | 93K
LC | 120865070 | 107/000 | T2 EI HUMBOLDT-TRINITY 107/000 RPL SPLW | EUREKA | ETL.1820.POLE.STPS | 2021-04-22 | 2021-04-22 | 2021-05-17 | 2022-04-22 | 2021-07-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Replace | 44764756 | T2 EI HUMBOLDT-TRINITY 107/000 RPL SPLW | ICW
LC | 120865543 | 008/053 | T2 DI HAAS-MC CALL 8/53 RPL INSS | FRESNO | ETL.4850.INSL | 2021-04-22 | 2021-04-21 | 2021-06-26 | 2022-04-21 | 2021-07-20 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31537144 | T2 DI HAAS-MC CALL 8/53 RPL INSS | 93K
LC | 120865637 | 015/493 | T2 EI SPAULDING-SUMMIT 15/493 REFRAME | SACTO | ETL.8060.POLE.WOOD | 2021-04-22 | 2021-04-22 | 2021-07-20 | 2022-04-22 | 2021-07-22 | On-time | 637 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31540168 | T2 EI SPAULDING-SUMMIT 15/493 REFRAME | 93E
LC | 120865925 | 038/254 | T2 DI POE-RIO OSO 38/254 RPL INSS | TABLEMTN | ETL.5540.INSL.CERA | 2021-04-22 | 2021-04-20 | 2021-06-19 | 2022-04-20 | 2021-07-19 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536365 | T2 DI POE-RIO OSO RPL INSS 2TWR | 93K
LC | 120866699 | 004/028 | T2 DI STSLS-MLS SS-MTC #1 4/28 INS HRDS | VICTOR | ETL.3830.INSL.NCER | 2021-04-22 | 2021-04-06 | 2021-05-25 | 2022-04-06 | 2021-07-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Steel | Install | 44764767 | T2 DI STSLS-MLS SS-MTC #1 4/28 INS HRDS | ICS
LC | 120871995 | 007/008 | T2 DI CHOWCHILLA-KERCKHOFF 7/8 RPR INSW | FRESNO | ETL.1250.INSL.NCER | 2021-04-23 | 2021-04-22 | 2021-05-20 | 2022-04-22 | 2021-07-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44772685 | T2 DI CHOWCHILLA-KERCKHOFF 7/8 RPR INSW | ICW
LC | 120872203 | 000/007 | T2 DI CHOWCHILLA-KERCKHOFF 0/7 RPR INSS | FRESNO | ETL.1250.INSL | 2021-04-23 | 2021-04-22 | 2021-05-20 | 2022-04-22 | 2021-07-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772687 | T2 DI CHOWCHILLA-KERCKHOFF 0/7 RPR INSS | ICS
LC | 120872287 | 002/011 | T2 DI CHOWCHILLA-KERCKHOFF 2/11 RPR INSW | FRESNO | ETL.1250.INSL.NCER | 2021-04-23 | 2021-04-22 | 2021-05-20 | 2022-04-22 | 2021-07-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44772689 | T2 DI CHOWCHILLA-KERCKHOFF 2/11 RPR INSW | ICW
LC | 120872588 | 013/099A | T2 DI HELMS-GREGG #1 013/099A COTTER KEY | FRESNO | ETL.4870.INSL | 2021-04-23 | 2021-04-21 | 2021-06-11 | 2022-04-21 | 2021-07-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772690 | T2 DI HELMS-GREGG #1 013/099A COTTER KEY | ICS
LC | 120872616 | 000/009 | T2 EI MNDCN-WLLTS-FRT BRGG RPL GUY POLE | LAKEVLLE | ETL.7550.POLE.WOOD | 2021-04-23 | 2021-04-22 | 2021-06-07 | 2022-04-22 | 2021-07-22 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Guy Pole-Wood | Replace | 31537420 | T2 EI MNDCN-WLLTS-FRT BRGG RPL GUY POLE | 93E
LC | 120872778 | 031/183 | T2 DI TMBLR-SN LS OBSPO 31/183 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-23 | 2021-04-22 | 2021-05-21 | 2022-04-22 | 2021-07-21 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31537187 | T2 DI TMBLR-SN LS OBSPO RPL INSS 2TWR | 93K
LC | 120873091 | 007/086 | T2 EI DRUM-SUMMIT #1 7/86 RPL DMPW | SACTO | ETL.1440.POLE.WDPS | 2021-04-23 | 2021-04-23 | 2021-06-04 | 2022-04-23 | 2021-07-23 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Damper-Wood | Replace | 44811847 | T2 EI DRUM-SUMMIT #1 7/86 RPL DMPW | ICW
LC | 120873131 | 009/158 | T2 TEJON-LEBEC 9/158 RPR INSW | MIDWAY | ETL.9250.POLE.NWOD | 2021-04-23 | 2021-04-23 | 2021-04-27 | 2022-04-23 | 2021-07-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44761087 | T2 TEJON-LEBEC 9/158 RPR INSW | ICW
LC | 120873183 | 018/128 | T2 DI HELMS-GREGG #2 18/128 COTTER KEY | FRESNO | ETL.4880.INSL | 2021-04-23 | 2021-04-20 | 2021-06-11 | 2022-04-20 | 2021-07-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772693 | T2 DI HELMS-GREGG #2 18/128 COTTER KEY | ICS
LC | 120873245 | 108/002 | T2 EI HUMBOLDT-TRINITY 108/2 RPL INSS | EUREKA | ETL.1820.INSL.NCER | 2021-04-23 | 2021-04-23 | 2021-05-17 | 2022-04-23 | 2021-07-23 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537421 | T2 EI HUMBOLDT-TRINITY 108/2 RPL INSS | 93I
LC | 120873382 | 020/139 | T2 DI HELMS-GREGG #1 20/139 COTTER KEY | FRESNO | ETL.4870.INSL | 2021-04-23 | 2021-04-22 | 2021-06-17 | 2022-04-22 | 2021-07-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772694 | T2 DI HELMS-GREGG #1 20/139 COTTER KEY | ICS
LC | 120873772 | 021/141 | T2 DI HELMS-GREGG #2 021/141 COTTER KEY | FRESNO | ETL.4880.INSL | 2021-04-23 | 2021-04-21 | 2021-06-17 | 2022-04-21 | 2021-07-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772696 | T2 DI HELMS-GREGG #2 021/141 COTTER KEY | ICS
LC | 120873894 | 019/132 | T2 DI HELMS-GREGG #1 19/132 COTTER KEY | FRESNO | ETL.4880.INSL | 2021-04-23 | 2021-04-21 | 2021-06-17 | 2022-04-21 | 2021-07-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772697 | T2 DI HELMS-GREGG #1 19/132 COTTER KEY | ICS
LC | 120873899 | 003/025 | T2 DI MORAGA-OAKLAND #1 3/25 RPR INSS | CONCORD | ETL.2720.INSL | 2021-04-23 | 2021-04-21 | 2021-05-31 | 2022-04-21 | 2021-07-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44764518 | T2 DI MORAGA-OAKLAND #1 3/25 RPR INSS | ICS
LC | 120874049 | 004/028 | T2 DI EL DRD-MSSR FLT #1 4/28 RPR INSS | SACTO | ETL.1530.INSL.CERA | 2021-04-23 | 2021-04-21 | 2021-07-06 | 2022-04-21 | 2021-07-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44764384 | T2 DI EL DRD-MSSR FLT #1 4/28 RPR INSS | ICS
LC | 120874054 | 003/013 | T2 DI CHOWCHILLA-KERCKHOFF 3/13 RPR INSW | FRESNO | ETL.1250.INSL.NCER | 2021-04-23 | 2021-04-22 | 2021-05-20 | 2022-04-22 | 2021-07-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44772698 | T2 DI CHOWCHILLA-KERCKHOFF 3/13 RPR INSW | ICW
LC | 120874057 | 007/007 | T2 DI SALINAS-FORT ORD #2 7/7 RPLC SPLS | MOSSLNDG | ETL.8423.INSL.CERA | 2021-04-23 | 2021-04-22 | 2021-06-03 | 2022-04-22 | 2021-07-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Replace | 44765417 | T2 DI SALINAS-FORT ORD #2 7/7 RPLC SPLS | ICS
LC | 120874313 | 004/008A | T2 DI CHWCHLLA-KRCKHFF 004/008A RPL STRW | FRESNO | ETL.1250.POLE.WOOD | 2021-04-23 | 2021-04-22 | 2021-05-21 | 2022-04-22 | 2021-07-21 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31536973 | T2 DI CHWCHLLA-KRCKHFF 004/008A RPL STRW | 70Y
LC | 120874505 | :014/077 | T2 DI CZY HRS CNYN-SLS-S :14/77 RPR INSS | MOSSLNDG | ETL.2900.INSL.NCER | 2021-04-23 | 2021-04-21 | 2021-05-05 | 2022-04-21 | 2021-07-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 44765418 | T2 DI CZY HRS CNYN-SLS-S :14/77 RPR INSS | ICS
LC | 120874891 | 001/008 | T2 DI CHWCHLLA-KERCKHOFF 001/008 RPR INS | FRESNO | ETL.1250.INSL.NCER | 2021-04-23 | 2021-04-22 | 2021-05-20 | 2022-04-22 | 2021-07-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44772720 | T2 DI CHWCHLLA-KERCKHOFF 001/008 RPR INS | ICW
LC | 120875051 | 026/156 | T2 DI TMBLR-SN LS OBSPO 26/156 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2021-04-23 | 2021-04-22 | 2021-05-21 | 2022-04-22 | 2021-07-22 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31537187 | T2 DI TMBLR-SN LS OBSPO RPL INSS 2TWR | 93K
LC | 120875358 | 016/000 | T2 EI FULTON-HOPLAND 016/000 RMV IDLE | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-04-23 | 2021-04-23 | 2021-05-20 | 2022-04-23 | 2021-07-23 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Structure-Wood | Remove | 44579280 | DI FULTON-HOPLAND :10/0 INST MRKW | ICW
LC | 120875643 | 013/452 | T2 EI SPAULDING-SUMMIT 13/452 RPR CNDW | SACTO | ETL.8060.INSL.NCER | 2021-04-23 | 2021-04-23 | 2021-07-20 | 2022-04-23 | 2021-07-23 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair | 44771036 | T2 EI SPAULDING-SUMMIT 13/452 RPR CNDW | ICW
LC | 120875884 | 006/004 | T2 DI SALINAS-FORT ORD #1 6/4 RPLC SPLS | MOSSLNDG | ETL.7890.INSL.CERA | 2021-04-23 | 2021-04-22 | 2021-06-04 | 2022-04-22 | 2021-07-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Replace | 44765419 | T2 DI SALINAS-FORT ORD #2 6/4 RPLC SPLS | ICS
LC | 120878339 | 000/005 | T2 DI CHOWCHILLA-KERCKHOFF 0/5 RPR INSS | FRESNO | ETL.1250.INSL | 2021-04-24 | 2021-04-22 | 2021-05-20 | 2022-04-22 | 2021-07-22 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772722 | T2 DI CHOWCHILLA-KERCKHOFF 0/5 RPR INSS | ICS
LC | 120878552 | 013/078 | EI T2 STNISLS-MLNS SS-MNT 13/78 RPR INSS | VICTOR | ETL.3830.INSL | 2021-04-24 | 2021-04-24 | 2021-05-26 | 2022-04-24 | 2021-07-24 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44809492 | EI T2 STNISLS-MLNS SS-MNT 13/78 RPR INSS | ICS
LC | 120878650 | 013/077 | EI T2 STNISLS-MLNS SS-MNT 13/77 RPR INSS | VICTOR | ETL.3830.INSL | 2021-04-24 | 2021-04-24 | 2021-05-26 | 2022-04-24 | 2021-07-24 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44809493 | EI T2 STNISLS-MLNS SS-MNT 13/77 RPR INSS | ICS
LC | 120879020 | 014/082 | EI T2 STNISLS-MLNS SS-MNT 14/82 RPR INSS | VICTOR | ETL.3830.INSL | 2021-04-24 | 2021-04-24 | 2021-05-26 | 2022-04-24 | 2021-07-24 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44809494 | EI T2 STNISLS-MLNS SS-MNT 14/82 RPR INSS | ICS
LC | 120879128 | 014/083 | EI T2 STNLUS-MLNS SS-MNT 14/83 RPR INSS | VICTOR | ETL.3830.INSL | 2021-04-24 | 2021-04-24 | 2021-05-26 | 2022-04-24 | 2021-07-24 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44809495 | EI T2 STNLUS-MLNS SS-MNT 14/83 RPR INSS | ICS
LC | 120879411 | 014/085 | T2 EI STNISLS-MLNS SS MNT 14/85 RPR INSS | VICTOR | ETL.3830.INSL | 2021-04-24 | 2021-04-24 | 2021-05-26 | 2022-04-24 | 2021-07-24 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44809496 | T2 STANISLAUS-MLNS SS MNT 14/85 RPR INSS | ICS
LC | 120879433 | 022/096A | T2 EI PITTSBURG-TESLA #1 22/96A RPR STRT | CONCORD | ETL.5510.TOWR | 2021-04-24 | 2021-04-24 | 2022-04-19 | 2022-04-24 | 2022-04-24 | On-time | 543 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45190818 | T2 EI PITTSBURG-TESLA #1 22/96A RPR STRT | ICQ
LC | 120879921 | 012/074 | T2 EI STAN-MEL-MANTECA 12/74 INS HRDS | VICTOR | ETL.3830.INSL | 2021-04-24 | 2021-04-24 | 2021-05-26 | 2022-04-24 | 2021-07-24 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44809617 | T2 EI STAN-MEL-MANTECA 12/74 INS HRDS | ICS
LC | 120880154 | 012/073 | T2 EI STAN-MEL-MANTECA 12/73 RPR INSS | VICTOR | ETL.3830.INSL | 2021-04-24 | 2021-04-24 | 2021-05-26 | 2022-04-24 | 2021-07-24 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44809619 | T2 EI STAN-MEL-MANTECA 12/73 RPR INSS | ICS
LC | 120880736 | 030/209 | T2 EI TRINITY-COTTONWD 30/209 COTTER KEY | TABLEMTN | ETL.4040.INSL.CERA | 2021-04-24 | 2021-04-24 | 2021-05-11 | 2022-04-24 | 2021-07-24 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44795228 | T2 EI TRINITY-COTTONWD 30/209 COTTER KEY | ICW
LC | 120882230 | 010/004A | T2 DI WINDSOR-FITCH MTN 010/04A RPR INSW | LAKEVLLE | ETL.6900.POLE.NWOD | 2021-04-26 | 2021-04-24 | 2021-05-04 | 2022-04-24 | 2021-07-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 44766588 | T2 DI WINDSOR-FITCH MTN 010/04A RPR INSW | ICW
LC | 120882273 | 010/085 | T2 DI SLT SPRNG-TGR CRK 10/85 COTTER KEY | VICTOR | ETL.3500.INSL | 2021-04-26 | 2021-04-22 | 2021-07-06 | 2022-04-22 | 2021-07-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44773926 | T2 DI SLT SPRNG-TGR CRK 10/85 COTTER KEY | ICS
LC | 120882388 | 026/157 | T2 DI TMBLR-SN LS OBSP 26/157 WASH INSS | PISMOBCH | ETL.3960.TOWR | 2021-04-26 | 2021-04-22 | 2021-05-21 | 2022-04-22 | 2021-07-21 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31542613 | T2 DI TMBLR-SN LS OBSP 26/157 WASH INSS | 93K
LC | 120889278 | 001/015 | T2 DI CHRISTIE-WILLOW PASS 1/15 COTR KEY | CONCORD | ETL.6370.INSL.CERA | 2021-04-27 | 2021-04-26 | 2021-05-21 | 2022-04-26 | 2021-07-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44766973 | T2 DI CHRISTIE-WILLOW PASS 1/15 COTR KEY | ICW
LC | 120889562 | 035/153 | T2 DI MRR BY-SLR SW ST #2 35/153 COTR KY | PISMOBCH | ETL.5310.INSL | 2021-04-27 | 2021-04-26 | 2021-05-22 | 2022-04-26 | 2021-07-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772570 | T2 DI MRR BY-SLR SW ST #2 35/153 COTR KY | ICS
LC | 120889794 | 016/131 | T2 EI PIT #1-CTTNWD 16/131 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2021-04-27 | 2021-04-27 | 2021-05-19 | 2022-04-27 | 2021-07-27 | On-time | 543 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44795223 | T2 EI PIT #1-CTTNWD 16/131 RPR FOND | ICQ
LC | 120890113 | C011/047 | T2 DI CBRN-LS AGLS S S-PN C11/47 RPL INS | MOSSLNDG | ETL.4460.INSL | 2021-04-27 | 2021-04-26 | 2021-04-30 | 2022-04-26 | 2021-07-25 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31537492 | T2 DI CBRN-LS AGLS S S-PN C11/47 RPL INS | 93K
LC | 120890623 | 032/138 | T2 DI MRR BY-SLR SW ST #1 32/138 RPL INS | PISMOBCH | ETL.5300.INSL | 2021-04-27 | 2021-04-26 | 2021-08-12 | 2022-04-26 | 2021-07-25 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31537419 | T2 DI MRR BY-SLR SW ST #1 32/138 RPL INS | 93K
LC | 120890937 | 036/240 | T2 DI CRESTA-RIO OSO 036/240 COTR KEY | TABLEMTN | ETL.4590.INSL.CERA | 2021-04-27 | 2021-04-26 | 2021-07-16 | 2022-04-26 | 2021-07-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44795230 | T2 DI CRESTA-RIO OSO 036/240 COTR KEY | ICS
LC | 120891023 | 036/157 | T2 DI MR BY-SLR SW ST #1 36/157 COTR KEY | PISMOBCH | ETL.5300.INSL | 2021-04-27 | 2021-04-26 | 2021-05-22 | 2022-04-26 | 2021-07-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772571 | T2 DI MR BY-SLR SW ST #1 36/157 COTR KEY | ICS
LC | 120891378 | 009/105 | T2 EI DRUM-SUMMIT#2 9/105C COTR KEY | SACTO | ETL.1450.POLE.WDPS | 2021-04-27 | 2021-04-27 | 2021-05-08 | 2022-04-27 | 2021-07-27 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44774085 | T2 EI DRUM-SUMMIT#2 9/105C COTR KEY | ICW
LC | 120892583 | 005/005 | T2 DI CHOWCHILLA-KERCKHOFF 5/5 RPR INSW | FRESNO | ETL.1250.INSL.NCER | 2021-04-27 | 2021-04-22 | 2021-05-20 | 2022-04-22 | 2021-07-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44772726 | T2 DI CHOWCHILLA-KERCKHOFF 5/5 RPR INSW | ICW
LC | 120892762 | 034/148 | T2 DI MRR BY-SLR SW STA #2 34/148 RPL IN | PISMOBCH | ETL.5310.INSL | 2021-04-27 | 2021-04-26 | 2021-06-30 | 2022-04-26 | 2021-07-25 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31539125 | T2 DI MRR BY-SLR SW STA #2 34/148 RPL IN | 93K
LC | 120892798 | 021/147 | T2 DI HELMS-GREGG #1 21/147 INS COTR KEY | FRESNO | ETL.4870.INSL | 2021-04-27 | 2021-04-16 | 2021-06-01 | 2022-04-16 | 2021-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772728 | T2 DI HELMS-GREGG #1 21/147 INS COTR KEY | ICS
LC | 120893359 | 019/004 | T2 DI TULE-SPRINGVILLE 019/004 REFRAME | MIDWAY | ETL.9040.POLE.WOOD | 2021-04-28 | 2021-04-27 | 2021-07-15 | 2022-04-27 | 2021-07-26 | On-time | 637 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31537557 | T2 DI TULE-SPRINGVILLE 019/004 REFRAME | 93E
LC | 120893791 | 020/159 | T2 EI PARADISE-TABLE MTN 20/159 COTR KEY | TABLEMTN | ETL.4316.POLE.WDPS | 2021-04-28 | 2021-04-28 | 2021-04-26 | 2022-04-28 | 2021-07-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44795222 | T2 EI PARADISE-TABLE MTN 20/159 COTR KEY | ICW
LC | 120893986 | 031/187 | T2 DI HELMS-GREGG #2 31/187 RPR INSS | FRESNO | ETL.4880.INSL | 2021-04-28 | 2021-04-27 | 2021-06-17 | 2022-04-27 | 2021-07-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772729 | T2 DI HELMS-GREGG #2 31/187 RPR INSS | ICS
LC | 120894047 | 042/203 | T2 DI LKVLL-SBRANTE #2 42/203 COTR KEY | CONCORD | ETL.4960.INSL.CERA | 2021-04-28 | 2021-04-28 | 2021-05-26 | 2022-04-28 | 2021-07-27 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44770576 | T2 DI LKVLL-SBRANTE #2 42/203 COTR KEY | ICS
LC | 120896768 | :014/088 | T2 DI MRGN HLL-LLGS :14/88 RPR INSS | MOSSLNDG | ETL.2800.INSL.CERA | 2021-04-28 | 2021-04-28 | 2021-05-07 | 2022-04-28 | 2021-07-27 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44768202 | T2 DI MRGN HLL-LLGS :14/88 RPR INSS | ICS
LC | 120897396 | 037/161 | T2 EI MORRO BAY-SOLR SS#1 37/161 COTR KY | PISMOBCH | ETL.5300.INSL | 2021-04-28 | 2021-04-28 | 2021-05-24 | 2022-04-28 | 2021-07-28 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772579 | T2 EI MORRO BAY-SOLR SS#1 37/161 COTR KY | ICS
LC | 120897397 | 037/161 | T2 EI MORRO BAY-SOLR SS#2 37/161 COTR KY | PISMOBCH | ETL.5310.INSL | 2021-04-28 | 2021-04-28 | 2021-05-22 | 2022-04-28 | 2021-07-28 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772609 | T2 EI MORRO BAY-SOLR SS#2 37/161 COTR KY | ICS
LC | 120897841 | 000/024 | EI T2 COLGATE-ALLEGHANY 0/24 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2021-04-28 | 2021-04-28 | 2021-07-08 | 2022-04-28 | 2021-07-28 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31539577 | EI T2 COLGATE-ALLEGHANY 0/24 RPL STRW | 70Y
LC | 120898014 | 042/205 | T2 DI LKEVLL-SBRANT #2 42/205 COTR KEY | CONCORD | ETL.4960.INSL | 2021-04-28 | 2021-04-28 | 2021-05-26 | 2022-04-28 | 2021-07-27 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44770575 | T2 DI LKEVLL-SBRANT #2 42/205 COTR KEY | ICS
LC | 120899849 | 026/118 | T2 DI TESLA-LOS BANOS #1 26/118 RPR OGPW | VICTOR | ETL.6100.TOWR | 2021-04-29 | 2021-04-28 | 2021-06-12 | 2022-04-28 | 2021-07-27 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44774042 | T2 DI TESLA-LOS BANOS #1 26/118 RPR OGPW | ICS
LC | 120903838 | X006/029 | T2 DI DIABLO-MESA X6/29 RPR OPGW | PISMOBCH | ETL.4620.TOWR | 2021-04-29 | 2021-04-29 | 2021-05-21 | 2022-04-29 | 2021-07-28 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44772611 | T2 DI DIABLO-MESA X6/29 RPR OPGW | ICS
LC | 120903879 | 019/078 | T2 DI DIABLO-MIDWAY #2 19/78 COTR KEY | PISMOBCH | ETL.5970.INSL.CERA | 2021-04-29 | 2021-04-29 | 2021-05-10 | 2022-04-29 | 2021-07-28 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772578 | T2 DI DIABLO-MIDWAY #2 19/78 COTR KEY | ICS
LC | 120904022 | X009/039 | T2 DI DIABLO-MESA X9/39 COTR KEY | PISMOBCH | ETL.4620.INSL | 2021-04-29 | 2021-04-28 | 2021-06-08 | 2022-04-28 | 2021-07-27 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772573 | T2 DI DIABLO-MESA X9/39 COTR KEY | ICS
LC | 120904024 | 017/120 | T2 DI HELMS-GREGG #2 17/120 COTR KEY | FRESNO | ETL.4880.INSL | 2021-04-29 | 2021-04-27 | 2021-06-11 | 2022-04-27 | 2021-07-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772730 | T2 DI HELMS-GREGG #2 17/120 COTR KEY | ICS
LC | 120904191 | 006/003 | T2 DI FULTON-HOPLAND 006/003 GRD WAS INS | LAKEVLLE | ETL.6890.INSL.CERA | 2021-04-29 | 2021-04-28 | 2021-05-18 | 2022-04-28 | 2021-07-27 | On-time | 622 | B - Urgt Compliance | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | Contaminated | Insulator | Ground Wash | 44766589 | T3 DI FULTON-HOPLAND 2/1 GRD WSH INSW | ICD
LC | 120906580 | 013/055 | T2 DI MORRO BAY-TEMPLETON 13/55 RPR OPGW | PISMOBCH | ETL.5933.TOWR | 2021-04-30 | 2021-04-29 | 2021-05-21 | 2022-04-29 | 2021-07-28 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44772610 | T2 DI MORRO BAY-TEMPLETON 13/55 RPR OPGW | ICS
LC | 120906881 | 003/014 | T2 DI MORRO BAY-DIABLO 3/14 COTR KEY | PISMOBCH | ETL.5260.INSL.NCER | 2021-04-30 | 2021-04-29 | 2021-05-10 | 2022-04-29 | 2021-07-28 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772615 | T2 DI MORRO BAY-MESA 3/14 COTR KEY | ICS
LC | 120907478 | 002/025 | T2 EI PIT #3-PIT #1 2/025 COTR KEY | TABLEMTN | ETL.5400.TOWR | 2021-04-30 | 2021-04-30 | 2021-05-26 | 2022-04-30 | 2021-07-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44795183 | T2 EI PIT #3-PIT #1 2/025 COTR KEY | ICS
LC | 120909451 | 033/140 | T2 DI TESLA-METCALF 33/140 GRND WASH | METCALF | ETL.6110.INSL | 2021-04-30 | 2021-04-30 | 2021-05-28 | 2022-04-30 | 2021-07-30 | On-time | 622 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Contaminated | Insulator | Ground Wash | 44772453 | T2 DI TESLA-METCALF 33/140 GRND WASH | ICD
LC | 120910984 | 014/053 | T2 DI DIABLO-MIDWAY #2 014/053 COTR KEY | PISMOBCH | ETL.5970.INSL | 2021-04-30 | 2021-04-30 | 2021-05-11 | 2022-04-30 | 2021-07-29 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44772601 | T2 DI DIABLO-MIDWAY #2 014/053 COTR KEY | ICS
LC | 120912258 | 028/214 | T2 DI MIDDLE FORK-GOLD HILL 28/214 COTR | SACTO | ETL.5140.INSL.NCER | 2021-05-01 | 2021-04-30 | 2021-06-26 | 2022-04-30 | 2021-07-29 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44775435 | T2 DI MIDDLE FORK-GOLD HILL 28/214 COTR | ICS
LC | 120912426 | 005/066 | T2 EI GREEN VALLEY-PAUL 05/066R RPL PL | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-05-01 | 2021-05-01 | 2022-10-28 | 2022-05-01 | 2022-05-01 | Late | 372 | Upgraded | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31537554 | T2 EI GREEN VALLEY-PAUL 05/066 RPL PL | 70Y
LC | 120913777 | 002/067 | T2 EI HMLTN BRNCH-CHSTR 2/67 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2021-05-01 | 2021-05-01 | 2021-05-21 | 2022-05-01 | 2021-08-01 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31539579 | T2 EI HMLTN BRNCH-CHSTR 2/67 RPL STRW | 70Y
LC | 120919790 | 003/017 | T2 DI MORRO BAY-MESA 003/017 COTR KEY | PISMOBCH | ETL.5290.INSL.NCER | 2021-05-03 | 2021-04-29 | 2021-05-18 | 2022-04-29 | 2021-07-28 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44808449 | T2 DI MORRO BAY-MESA 003/017 COTR KEY | ICS
LC | 120919852 | 005/025 | T2 DI MORRO BAY-MESA 5/25 RPR OPGW | PISMOBCH | ETL.5290.TOWR | 2021-05-03 | 2021-04-29 | 2021-05-21 | 2022-04-29 | 2021-07-28 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44815664 | T2 DI MORRO BAY-MESA 5/25 RPR OPGW | ICS
LC | 120920513 | 013/051 | T2 DI DIABLO-MIDWAY #3 13/51 RPR INSS | PISMOBCH | ETL.5980.INSL | 2021-05-03 | 2021-05-03 | 2021-05-10 | 2022-05-03 | 2021-08-03 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44779290 | T2 DI DIABLO-MIDWAY #3 13/51 RPR INSS | ICS
LC | 120921107 | 008/034 | EI T2 TESLA-METCALF 8/34 RPL SPLICE | METCALF | ETL.6110.INSL.NCER | 2021-05-03 | 2021-05-03 | 2021-05-28 | 2022-05-03 | 2021-08-03 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Replace | 44792210 | EI T2 TESLA-METCALF 8/34 RPL SPLICE | ICS
LC | 120922332 | 002/014 | T2 EI STNISLUS-MLNS SS-MNT 2/14 RPR INSS | VICTOR | ETL.3830.TOWR | 2021-05-03 | 2021-05-03 | 2021-05-25 | 2022-05-03 | 2021-08-03 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44809664 | T2 EI STNISLUS-MLNS SS-MNT 2/14 RPR INSS | ICS
LC | 120924097 | 005/037 | T2 OLEUM-G #2 5/037 REPL INSS | CONCORD | ETL.3160.INSL | 2021-05-03 | 2021-05-03 | 2021-05-14 | 2022-05-03 | 2021-08-03 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31539594 | T2 OLEUM-G #2 5/037 REPL INSS | 93K
LC | 120927027 | 003/018 | T2 EI STANISLAUS-MLNS MNTE 3/18 RPR INSS | VICTOR | ETL.3830.TOWR | 2021-05-04 | 2021-05-04 | 2021-05-25 | 2022-05-04 | 2021-08-04 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44819857 | T2 EI STANISLAUS-MLNS MNTE 3/18 RPR INSS | ICS
LC | 120929316 | 030/131 | T2 EI MRR BY-SLR SW ST#2 30/131 COTTER | PISMOBCH | ETL.5300.TOWR | 2021-05-04 | 2021-05-04 | 2021-06-04 | 2022-05-04 | 2021-08-04 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44815671 | T2 EI MRR BY-SLR SW ST#2 30/131 COTTER | ICS
LC | 120929662 | 002/020 | T2 DI COTTONWOOD-DELVN #1 2/20 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-05-04 | 2021-05-04 | 2021-06-12 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44795180 | T2 DI COTTONWOOD-DELVN #1 2/20 RPR OPGW | ICS
LC | 120929668 | 008/058 | T2 DI COTTONWOOD-DELVN #1 8/58 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-05-04 | 2021-05-04 | 2021-06-15 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44795196 | T2 DI COTTONWOOD-DELVN #1 8/58 RPR OPGW | ICS
LC | 120929764 | 065/580 | T2 DI CTTNWD-DELEVAN #1 65/580 COTR KEY | TABLEMTN | ETL.4560.INSL | 2021-05-04 | 2021-05-04 | 2021-07-13 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44795234 | T2 DI CTTNWD-DELEVAN #1 65/580 COTR KEY | ICS
LC | 120929781 | 005/033 | T2 DI COTTONWOOD-DELVN #1 5/33 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-05-04 | 2021-05-04 | 2021-06-12 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44795137 | T2 DI COTTONWOOD-DELVN #1 5/33 RPR OPGW | ICS
LC | 120929902 | 000/003B | T2 DI MRR BY-SLR #1 0/3B RPR OPGW | PISMOBCH | ETL.5300.POLE.NWOD | 2021-05-04 | 2021-05-04 | 2021-05-20 | 2022-05-04 | 2021-08-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44811101 | T2 DI MRR BY-SLR #1 0/3B RPR OPGW | ICS
LC | 120929906 | 005/038 | T2 DI CTTNWD-DELEVAN #1 5/38 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-05-04 | 2021-05-04 | 2021-06-12 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44795189 | T2 DI CTTNWD-DELEVAN #1 5/38 RPR OPGW | ICS
LC | 120930170 | 004/029 | T2 DI CTTNWD-DELEVAN #1 4/29 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-05-04 | 2021-05-04 | 2021-06-12 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44795135 | T2 DI CTTNWD-DELEVAN #1 4/29 RPR OPGW | ICS
LC | 120930296 | 025/114 | T2 DI QUINTO SS-WESTY 25/114 RPR OPGW | VICTOR | ETL.5070.TOWR | 2021-05-04 | 2021-05-04 | 2021-06-10 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44809662 | T2 DI QUINTO SS-WESTY 25/114 RPR OPGW | ICS
LC | 120930456 | 002/018 | T2 DI COTTONWOOD-DELVN #1 2/18 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-05-04 | 2021-05-04 | 2021-06-12 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44795138 | T2 DI COTTONWOOD-DELVN #1 2/18 RPR OPGW | ICS
LC | 120930816 | 011/077 | T2 DI COTTONWOOD-DELVN #1 11/77 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-05-04 | 2021-05-04 | 2021-06-15 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44795221 | T2 DI COTTONWOOD-DELVN #1 11/77 RPR OPGW | ICS
LC | 120930849 | 000/005 | T2 EI STANISLAUS-MLNS MNTE 0/5 RPR INSS | VICTOR | ETL.3830.TOWR | 2021-05-04 | 2021-05-04 | 2021-05-25 | 2022-05-04 | 2021-08-04 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44809663 | T2 EI STANISLAUS-MLNS MNTE 0/5 RPR INSS | ICS
LC | 120930906 | 038/160 | T2 DI TEMPLETON-GATES 38/160 RPLC DAMS | PISMOBCH | ETL.5934.INSL.CERA | 2021-05-04 | 2021-05-04 | 2021-06-22 | 2022-05-04 | 2021-08-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 44815663 | T2 DI TEMPLETON-GATES 38/160 RPLC DAMS | ICS
LC | 120930945 | 003/023 | T2 DI COTTONWOOD-DELVN #1 3/23 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-05-04 | 2021-05-04 | 2021-06-12 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44795133 | T2 DI COTTONWOOD-DELVN #1 3/23 RPR OPGW | ICS
LC | 120931381 | 027/001 | T2 EI MNDCNO-WLLTS-FRT BRG 27/1 RPL HRDW | LAKEVLLE | ETL.7550.POLE.NWOD | 2021-05-04 | 2021-05-04 | 2021-05-27 | 2022-05-04 | 2021-08-04 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44804371 | T2 EI MNDCNO-WLLTS-FRT BRG 27/1 RPL HRDW | ICW
LC | 120931441 | 005/034 | T2 DI CTTNWD-DELEVAN #1 5/34 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-05-04 | 2021-05-04 | 2021-06-12 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44795139 | T2 DI CTTNWD-DELEVAN #1 5/34 RPR OPGW | ICS
LC | 120931477 | 005/034 | T2 DI CTTNWD-LOGAN CREEK 5/34 RPL DAMS | TABLEMTN | ETL.4570.INSL | 2021-05-04 | 2021-05-04 | 2021-06-16 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 44795182 | T2 DI CTTNWD-LOGAN CREEK 5/34 RPL DAMS | ICS
LC | 120931676 | 005/034 | T2 DI CTTNWD-DELEVAN #1 5/34 RPL DAMS | TABLEMTN | ETL.4550.INSL | 2021-05-04 | 2021-05-04 | 2021-07-21 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 44795184 | T2 DI CTTNWD-DELEVAN #1 5/34 RPL DAMS | ICS
LC | 120932151 | 040/168 | T2 DI TEMPLETON-GATES 40/168 RPR OPGW | PISMOBCH | ETL.5934.TOWR | 2021-05-04 | 2021-05-04 | 2021-06-22 | 2022-05-04 | 2021-08-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44815666 | T2 DI TEMPLETON-GATES 40/168 RPR OPGW | ICS
LC | 120932231 | 012/053 | T2 DI MORAGA-CASTRO VLY 12/53 RPR OPGW | CONCORD | ETL.5250.TOWR | 2021-05-04 | 2021-05-04 | 2021-05-31 | 2022-05-04 | 2021-08-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44792214 | T2 DI MORAGA-CASTRO VLY 12/53 RPR OPGW | ICS
LC | 120932311 | 005/010 | T2 DI OAKHURST TAP 5/010 RPR INSS | FRESNO | ETL.1252.INSL.NCER | 2021-05-04 | 2021-04-16 | 2021-05-27 | 2022-04-16 | 2021-07-16 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44811220 | T2 DI OAKHURST TAP 5/010 RPR INSS | ICS
LC | 120934595 | 065/581 | T2 DI COTTONWD-DELVN #2 65/581 RPLC INSS | TABLEMTN | ETL.4580.INSL.CERA | 2021-05-05 | 2021-05-04 | 2021-07-16 | 2022-05-04 | 2021-08-04 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540063 | T2 DI COTTONWD-DELVN #2 65/581 RPLC INSS | 93K
LC | 120935344 | 032/017 | T2 EI FULTON-HOPLAND 32/17 RPL STRW | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-05-05 | 2021-05-04 | 2022-06-24 | 2022-05-04 | 2022-05-04 | Late | 372 | Upgraded | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31536640 | T2 EI FULTON-HOPLAND 033/003 RPL STRW | 70Y
LC | 120936566 | 028/118 | T2 EI TESLA-METCALF 28/118 REPULL GUY | METCALF | ETL.6110.TOWR | 2021-05-05 | 2021-05-05 | 2021-06-12 | 2022-05-05 | 2021-08-05 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 44857079 | T2 EI TESLA-METCALF 28/118 REPULL GUY | ICS
LC | 120937141 | 063/565 | T2 DI COTTONWOOD-DLVN #2 63/565 RPR INSS | TABLEMTN | ETL.4580.INSL.CERA | 2021-05-05 | 2021-05-04 | 2021-07-16 | 2022-05-04 | 2021-08-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44795232 | T2 DI COTTONWOOD-DLVN #2 63/565 RPR INSS | ICS
LC | 120937501 | 002/016 | T2 DI COTTONWOOD-DLVN #1 2/16 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-05-05 | 2021-05-04 | 2021-06-12 | 2022-05-04 | 2021-08-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44795128 | T2 DI COTTONWOOD-DLVN #1 2/16 RPR OPGW | ICS
LC | 120941058 | 024/139 | T2 DI TESLA-SLD-MTC 24/139 COTR KEY | VICTOR | ETL.4000.INSL.CERA | 2021-05-06 | 2021-05-04 | 2021-05-13 | 2022-05-04 | 2021-08-02 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44796386 | T2 DI TESLA-SLD-MTC 24/139 COTR KEY | ICW
LC | 120941200 | 005/041 | T2 DI COTTONWOOD-DLEVN #1 5/41 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-05-06 | 2021-05-04 | 2021-06-12 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44795191 | T2 DI COTTONWOOD-DLEVN #1 5/41 RPR OPGW | ICS
LC | 120941865 | 009/074A | T2 EI PIT #1-COTTONWOOD 9/074A RPR CONS | TABLEMTN | ETL.5390.TOWR | 2021-05-06 | 2021-05-06 | 2021-05-31 | 2022-05-06 | 2021-08-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Conductor-Steel | Repair | 44791696 | T2 PIT #1-COTTONWOOD 9/074A RPR CONS | ICS
LC | 120941890 | 002/022 | T2 DI COTTONWOOD-DLVN #1 2/22 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-05-06 | 2021-05-04 | 2021-06-12 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44795130 | T2 DI COTTONWOOD-DLVN #1 2/22 RPR OPGW | ICS
LC | 120941896 | 005/037 | T2 DI COTTONWOOD-DLVN #1 5/37 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-05-06 | 2021-05-04 | 2021-06-12 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44795186 | T2 DI COTTONWOOD-DLVN #1 5/37 RPR OPGW | ICS
LC | 120942250 | 036/152 | T2 DI TEMPLETON-GATES 36/152 RPR OPGW | PISMOBCH | ETL.5934.TOWR | 2021-05-06 | 2021-05-04 | 2021-06-22 | 2022-05-04 | 2021-08-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44815667 | T2 DI TEMPLETON-GATES 36/152 RPR OPGW | ICS
LC | 120943672 | 026/202B | T2 DI MDL FRK-GLD HL 26/202B COTR KY | SACTO | ETL.5140.POLE.NWOD | 2021-05-06 | 2021-05-06 | 2021-06-26 | 2022-05-06 | 2021-08-04 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44811777 | T2 DI MDL FRK-GLD HL 26/202B COTR KY | ICW
LC | 120947252 | 013/122 | T2 DI DRUM-RIO OSO #1 013/122 RPR INSS | SACTO | ETL.1420.INSL.NCER | 2021-05-07 | 2021-05-06 | 2021-07-24 | 2022-05-06 | 2021-08-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44811779 | T2 DI DRUM-RIO OSO #1 013/122 RPR INSS | ICS
LC | 120947469 | 019/155 | T2 DI DRUM-RIO OSO #1 019/155 RPR INSS | SACTO | ETL.1420.INSL.NCER | 2021-05-07 | 2021-05-06 | 2021-07-24 | 2022-05-06 | 2021-08-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44811778 | T2 DI DRUM-RIO OSO #1 019/155 RPR INSS | ICS
LC | 120947548 | 040/192 | T2 DI LKVLLE-SBRNTE #2 040/192 COTR KEY | CONCORD | ETL.4960.INSL | 2021-05-07 | 2021-05-06 | 2021-06-14 | 2022-05-06 | 2021-08-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44792781 | T2 DI LKVLLE-SBRNTE #2 040/192 COTR KEY | ICS
LC | 120947668 | 039/185 | T2 DI IGNACIO-SOBRANTE 039/185 COTR KEY | CONCORD | ETL.4920.INSL.CERA | 2021-05-07 | 2021-05-06 | 2021-07-16 | 2022-05-06 | 2021-08-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44791970 | T2 DI IGNACIO-SOBRANTE 039/185 COTR KEY | ICS
LC | 120948357 | 031/131 | T2 DI MOSS LNDNG-MTCLF 31/131 COTR KEY | MOSSLNDG | ETL.6050.INSL | 2021-05-07 | 2021-05-06 | 2021-05-20 | 2022-05-06 | 2021-08-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44792203 | T2 DI MOSS LNDNG-MTCLF 31/131 COTR KEY | ICS
LC | 120948928 | 039/188 | T2 DI LKVL-SOBRANTE #2 39/188 COTR KEY | CONCORD | ETL.4960.INSL.CERA | 2021-05-07 | 2021-05-06 | 2021-08-01 | 2022-05-06 | 2021-08-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44792218 | T2 DI LKVL-SOBRANTE #2 39/188 COTR KEY | ICS
LC | 120949019 | 039/187 | T2 DI IGNACIO-SOBRANTE 39/187 COTR KEY | CONCORD | ETL.4920.INSL.CERA | 2021-05-07 | 2021-05-06 | 2021-08-02 | 2022-05-06 | 2021-08-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44788851 | T2 DI IGNACIO-SOBRANTE 39/187 COTR KEY | ICS
LC | 120949262 | 039/187 | T2 DI LAKEVL-SBRNTE#2 39/187 COTR KEY | CONCORD | ETL.4960.INSL | 2021-05-07 | 2021-05-06 | 2021-08-01 | 2022-05-06 | 2021-08-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44792780 | T2 DI LAKEVL-SBRNTE#2 39/187 COTR KEY | ICS
LC | 120949370 | 041/196 | T2 DI IGNACIO-SOBRANTE 41/196 COTR KEY | CONCORD | ETL.4960.INSL | 2021-05-07 | 2021-05-07 | 2021-06-14 | 2022-05-07 | 2021-08-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44792219 | T2 DI IGNACIO-SOBRANTE 41/196 COTR KEY | ICS
LC | 120952755 | :002/016 | T2 EI SLS-MLNS SW ST-MNT :2/16 RPR SPLS | VICTOR | ETL.3840.INSL.NCER | 2021-05-08 | 2021-05-08 | 2021-08-04 | 2022-05-08 | 2021-08-08 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Steel | Repair | 44840714 | T2 EI SLS-MLNS SW ST-MNT :2/16 RPR SPLS | ICS
LC | 120953273 | 009/169 | T2 PT #1-HT CRK #2-BRNY 9/169 RMV JMPR | TABLEMTN | ETL.7040.POLE.WOOD | 2021-05-08 | 2021-05-08 | 2021-05-10 | 2022-05-08 | 2021-08-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | Debris/Nest/etc. | Conductor-Wood | Remove | 44784313 | T2 PT #1-HT CRK #2-BRNY 9/169 RMV JMPR | ICW
LC | 121030928 | 017/252 | T2 DI CLAY-MARTEL 017/252 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-10 | 2021-05-08 | 2021-06-18 | 2022-05-08 | 2021-08-08 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540307 | T2 DI CLAY-MARTEL 017/252 RPL STRW | 70Y
LC | 121032396 | 016/305 | T2 DI WASHOE TAP 16/305 RPR INSW | LAKEVLLE | ETL.6911.INSL.CERA | 2021-05-10 | 2021-05-08 | 2021-05-28 | 2022-05-08 | 2021-08-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44796134 | T2 DI WASHOE TAP 16/305 RPR INSW | ICW
LC | 121038974 | 017/229 | T2 DI WST PNT-VLY SPGS 17/229 RPR INSS | VICTOR | ETL.8350.INSL.NCER | 2021-05-10 | 2021-05-08 | 2021-06-21 | 2022-05-08 | 2021-08-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44809814 | T2 DI WST PNT-VLY SPGS 17/229 RPR INSS | ICS
LC | 121041745 | 016/217 | T2 DI W. PNT-VLY SPRNGS 16/217 RPR INSW | VICTOR | ETL.8350.INSL.NCER | 2021-05-10 | 2021-05-08 | 2021-06-21 | 2022-05-08 | 2021-08-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44809816 | T2 DI W. PNT-VLY SPRNGS 16/217 RPR INSW | ICW
LC | 121130220 | 033/004 | T2 EI MEND-WILL-FT BRAGG 33/4 RPR INSW | LAKEVLLE | ETL.7550.POLE.WOOD | 2021-05-10 | 2021-05-08 | 2021-05-27 | 2022-05-08 | 2021-08-08 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44808647 | T2 EI MEND-WILL-FT BRAGG 33/4 RPR INSW | ICW
LC | 121130239 | 032/005 | T2 EI MNDOCNO-WILTS-FRT BRG 32/5 COTR KY | LAKEVLLE | ETL.7550.POLE.WOOD | 2021-05-10 | 2021-05-08 | 2021-05-27 | 2022-05-08 | 2021-08-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44801216 | T2 EI MNDOCNO-WILTS-FRT BRG 32/5 COTR KY | ICW
LC | 121186827 | 016/304 | T2 DI FULTON-MLN-COTATI 16/304 COTR KEY | LAKEVLLE | ETL.6910.INSL.NCER | 2021-05-11 | 2021-05-08 | 2021-05-28 | 2022-05-08 | 2021-08-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44801214 | T2 DI FULTON-MLN-COTATI 16/304 COTR KEY | ICW
LC | 121189199 | 004/106 | T2 DI COLGATE-ALLEGHANY 004/106 RPR CNDW | SACTO | ETL.6470.INSL.CERA | 2021-05-11 | 2021-05-11 | 2021-07-23 | 2022-05-11 | 2021-08-09 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 44811770 | T2 DI COLGATE-ALLEGHANY 004/106 RPR CNDW | ICW
LC | 121189357 | 017/250 | T2 DI CLAY-MARTEL 17/250 RPR INSS | VICTOR | ETL.8250.INSL.NCER | 2021-05-11 | 2021-05-08 | 2021-05-12 | 2022-05-08 | 2021-08-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44796481 | T2 DI CLAY-MARTEL 17/250 RPR INSS | ICS
LC | 121191539 | 020/289 | T2 DI CLAY-MARTEL 020/289 RPR ADSS | VICTOR | ETL.8250.POLE.WOOD | 2021-05-11 | 2021-05-11 | 2021-07-29 | 2022-05-11 | 2021-08-11 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44809647 | T2 DI CLAY-MARTEL 020/289 RPR ADSS | ICW
LC | 121191887 | 008/099 | T2 DI VEDDER TAP 008/099 RPR GYWW | MIDWAY | ETL.2141.POLE.WOOD | 2021-05-11 | 2021-04-21 | 2021-06-01 | 2022-04-21 | 2021-07-21 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44815746 | T2 DI VEDDER TAP 008/099 RPR GYWW | ICW
LC | 121317844 | 016/007 | T2 EI MEND-WILL-FT BRAG 16/7 RPL POLE | LAKEVLLE | ETL.7550.POLE.WOOD | 2021-05-12 | 2021-05-12 | 2021-08-27 | 2022-05-12 | 2021-08-12 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH RTNR FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31540946 | T2 EI MEND-WILL-FT BRAG 16/7 RPL POLE | 70Y
LC | 121318439 | :015/094 | T2 DI MORGAN HILL-LLAGAS 15/94 RPR COTER | MOSSLNDG | ETL.2800.INSL.CERA | 2021-05-12 | 2021-04-28 | 2021-06-09 | 2022-04-28 | 2021-07-27 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44805774 | T2 DI MORGAN HILL-LLAGAS 15/94 RPR COTER | ICS
LC | 121319888 | 006/054 | T2 WV BCKS CK-RCK CRK-CRTA 6/54 INS DAMS | TABLEMTN | ETL.4430.TOWR | 2021-05-12 | 2021-05-12 | 2021-06-25 | 2022-05-12 | 2021-08-12 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Missing | Damper-Steel | Install | 44821788 | T2 WV BCKS CK-RCK CRK-CRTA 6/54 INS DAMS | ICS
LC | 121320207 | 018/145 | T2 EI PIT #1-COTTONWOOD 18/145 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-05-12 | 2021-05-12 | 2021-07-07 | 2022-05-12 | 2021-08-12 | On-time | 543 | Upgraded | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB | No Good/Out of Stdrd | Structure-Tower | Repair | 44856571 | T2 EI PIT #1-COTTONWOOD 18/145 RPR STRT | ICQ
LC | 121321384 | 113/004 | T2 EI HMBLDT-BRDGVLLE 113/4 RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-05-12 | 2021-05-12 | 2021-07-15 | 2022-05-12 | 2021-08-12 | On-time | 372 | Upgraded | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31540941 | T2 EI HMBLDT-BRDGVLLE 113/4 RPL STRW | 70Y
LC | 121321474 | 113/004 | T2 EI HMBLDT-BRDGVLLE 113/4 RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-05-12 | 2021-05-12 | 2021-07-15 | 2022-05-12 | 2021-08-12 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31540941 | T2 EI HMBLDT-BRDGVLLE 113/4 RPL STRW | 70Y
LC | 121321532 | 113/004 | T2 EI HMBLDT-BRDGVLLE 113/4 RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-05-12 | 2021-05-12 | 2021-07-15 | 2022-05-12 | 2021-08-12 | On-time | 372 | Upgraded | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31540941 | T2 EI HMBLDT-BRDGVLLE 113/4 RPL STRW | 70Y
LC | 121326018 | 024/180 | T2 DI DRUM-RIO OSO #1 24/180 RPR INSS | SACTO | ETL.1420.INSL.NCER | 2021-05-13 | 2021-05-12 | 2021-07-08 | 2022-05-12 | 2021-08-10 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44811769 | T2 DI DRUM-RIO OSO #1 24/180 RPR INSS | ICS
LC | 121328937 | 018/123 | T2 EI HELMS-GREGG #1 18/123 COTR KEY | FRESNO | ETL.4870.INSL | 2021-05-13 | 2021-05-12 | 2021-08-05 | 2022-05-12 | 2021-08-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44811233 | T2 EI HELMS-GREGG #1 18/123 COTR KEY | ICS
LC | 121329150 | 018/124 | T2 EI HELMS-GREGG #2 18/124 COTR KEY | FRESNO | ETL.4880.INSL | 2021-05-13 | 2021-05-12 | 2021-08-05 | 2022-05-12 | 2021-08-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44811234 | T2 EI HELMS-GREGG #2 18/124 COTR KEY | ICS
LC | 121329151 | 018/124 | T2 EI HELMS-GREGG #1 18/124 COTR KEY | FRESNO | ETL.4870.INSL | 2021-05-13 | 2021-05-12 | 2021-08-05 | 2022-05-12 | 2021-08-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44811235 | T2 EI HELMS-GREGG #1 18/124 COTR KEY | ICS
LC | 121331289 | 003/039 | T2 DI HLSDL JCT-HLF MN BY 3/39 RPLC INSW | METCALF | ETL.7060.INSL.CERA | 2021-05-14 | 2021-05-12 | 2021-08-01 | 2022-05-12 | 2021-08-12 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31540705 | T2 DI HLSDL JCT-HLF MN BY 3/39 RPLC INSW | 93I
LC | 121333664 | 020/136 | T2 EI HELMS-GREGG #1 20/136 INS COTR KEY | FRESNO | ETL.4870.INSL | 2021-05-14 | 2021-05-14 | 2021-06-01 | 2022-05-14 | 2021-08-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44811236 | T2 EI HELMS-GREGG #1 20/136 INS COTR KEY | ICS
LC | 121333854 | 020/135 | T2 EI HELMS-GREGG #2 20/135 INS COTR KEY | FRESNO | ETL.4880.INSL | 2021-05-14 | 2021-05-14 | 2021-06-01 | 2022-05-14 | 2021-08-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44811237 | T2 EI HELMS-GREGG #2 20/135 INS COTR KEY | ICS
LC | 121334100 | 019/134 | T2 EI HELMS-GREGG #2 19/134 INS COTR KEY | FRESNO | ETL.4880.INSL | 2021-05-14 | 2021-05-14 | 2021-06-01 | 2022-05-14 | 2021-08-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44811238 | T2 EI HELMS-GREGG #2 19/134 INS COTR KEY | ICS
LC | 121335009 | 005/037 | T2 OLEUM-G #2 5/037 HANGR PLATE | CONCORD | ETL.3160.INSL | 2021-05-14 | 2021-05-14 | 2021-05-18 | 2022-05-14 | 2021-08-14 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 44808899 | T2 OLEUM-G #2 5/037 HANGR PLATE | ICQ
LC | 121340558 | 027/199 | T2 EI CARIBOU-TABLE MTN 027/199 RPR HRDT | TABLEMTN | ETL.4440.TOWR | 2021-05-15 | 2021-05-15 | 2021-05-25 | 2022-05-15 | 2021-08-15 | On-time | 543 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | Missing | Hardware-Tower | Install | 44816164 | T2 EI CARIBOU-TABLE MTN 027/199 RPR HRDT | ICQ
LC | 121343353 | 000/002 | T2 DI CHOWCHILLA-KERCKHOFF 0/2 RPR INSS | FRESNO | ETL.1250.INSL | 2021-05-17 | 2021-05-15 | 2021-05-20 | 2022-05-15 | 2021-08-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44809653 | T2 DI CHOWCHILLA-KERCKHOFF 0/2 RPR INSS | ICS
LC | 121344438 | 015/010 | T2 DI FULTON-HOPLAND 15/10 RPR GYWW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-17 | 2021-05-13 | 2021-05-20 | 2022-05-13 | 2021-08-11 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44810459 | T2 DI FULTON-HOPLAND 15/10 RPR GYWW | ICW
LC | 121344621 | 002/024 | T2 DI CHRISTIE-WILLOW PASS 2/24 RPR SWTC | CONCORD | ETL.6370.SWIT | 2021-05-17 | 2021-05-17 | 2021-08-02 | 2022-05-17 | 2021-08-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Switch-Wood | Repair | 44816214 | T2 DI CHRISTIE-WILLOW PASS 2/24 RPR SWTC | ICW
LC | 121345189 | X010/042 | T2 DI MORRO BAY-DIABLO X010/042 RPL INSS | PISMOBCH | ETL.5260.INSL | 2021-05-17 | 2021-04-28 | 2021-08-15 | 2022-04-28 | 2021-07-28 | On-time | 532 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31540872 | T2 DI MORRO BAY-DIABLO X010/042 RPL INSS | 93K
LC | 121345327 | 037/003 | T2 DI FORT ROSS-GUALALA 037/003 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2021-05-17 | 2021-05-17 | 2021-05-24 | 2022-05-17 | 2021-08-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44589099 | T2 DI FORT ROSS-GUALALA 030/008 RPR SPLW | ICW
LC | 121346215 | 042/011 | T2 DI FORT ROSS-GUALALA 42/11 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2021-05-17 | 2021-05-17 | 2021-05-24 | 2022-05-17 | 2021-08-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44589099 | T2 DI FORT ROSS-GUALALA 030/008 RPR SPLW | ICW
LC | 121348352 | 013/100A | T2 EI HLMS-GRG #1 13/100A COTR KEY | FRESNO | ETL.4870.TOWR | 2021-05-17 | 2021-05-17 | 2021-07-07 | 2022-05-17 | 2021-08-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44811240 | T2 EI HLMS-GRG #1 13/100A RPR INSS | ICS
LC | 121350194 | 011/247 | T2 DI SALINAS-LAURELES 11/247 RPR INSW | MOSSLNDG | ETL.7930.INSL.NCER | 2021-05-18 | 2021-05-17 | 2021-06-29 | 2022-05-17 | 2021-08-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44811286 | T2 DI SALINAS-LAURELES 11/247 RPR INSW | ICW
LC | 121350199 | 025/191 | T2 DI DRUM-RIO OSO #1 25/191 REPL HRDT | SACTO | ETL.1420.INSL.CERA | 2021-05-18 | 2021-05-17 | 2021-05-25 | 2022-05-17 | 2021-08-15 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44811763 | T2 DI DRUM-RIO OSO #1 25/191 REPL HRDT | ICQ
LC | 121352433 | A011/250 | T2 DI SALINAS-LAURELES A11/250 RPR INSW | MOSSLNDG | ETL.7930.INSL.NCER | 2021-05-18 | 2021-05-17 | 2021-07-15 | 2022-05-17 | 2021-08-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44811298 | T2 DI SALINAS-LAURELES A11/250 RPR INSW | ICW
LC | 121353056 | 071/358A | T2 EI MLIN-RND MTN #2 71/358A RPR COND | TABLEMTN | ETL.6020.TOWR | 2021-05-18 | 2021-05-18 | 2021-06-04 | 2022-05-18 | 2021-08-18 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Conductor-Steel | Repair | 44821792 | T2 EI MLIN-RND MTN #2 71/358A RPR COND | ICS
LC | 121354532 | 010/338 | T2 DI SPAULDING-SUMMIT 10/338 RPR INSW | SACTO | ETL.8060.INSL.NCER | 2021-05-18 | 2021-05-18 | 2021-07-20 | 2022-05-18 | 2021-08-18 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44811761 | T2 DI SPAULDING-SUMMIT 10/338 RPR INSW | ICW
LC | 121358786 | 034/002 | T2 DI FULTON-HOPLAND 34/2 COTR KY | LAKEVLLE | ETL.6890.INSL.NCER | 2021-05-19 | 2021-05-18 | 2021-06-10 | 2022-05-18 | 2021-08-16 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44815957 | T2 DI FULTON-HOPLAND 34/2 COTR KY | ICW
LC | 121359912 | 025/107 | T2 DI MSS LNDNG-MTCLF 25/107 RPR INSS | MOSSLNDG | ETL.6050.INSL.NCER | 2021-05-19 | 2021-05-19 | 2021-05-26 | 2022-05-19 | 2021-08-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44813258 | T2 DI MSS LNDNG-MTCLF 25/107 RPR INSS | ICS
LC | 121362647 | 015/314 | T2 DI COLGATE-PALERMO 15/314 RPR INSW | TABLEMTN | ETL.6500.INSL.CERA | 2021-05-19 | 2021-05-10 | 2021-08-07 | 2022-05-10 | 2021-08-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44821794 | T2 DI COLGATE-PALERMO 15/314 RPR INSW | ICW
LC | 121363639 | 009/064 | T2 DI DELEVAN-VACA #1 9/64 COMPLETE | SACTO | ETL.5010.INSL.CERA | 2021-05-19 | 2021-05-18 | 2022-04-13 | 2022-05-18 | 2022-05-18 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44896667 | T2 DI DELEVAN-VACA #1 9/64 RPR OPGW | ICS
LC | 121363740 | 009/064 | T2 DI CORTINA-VACA 9/64 RPR OPGW | SACTO | ETL.4540.INSL.CERA | 2021-05-19 | 2021-05-18 | 2022-05-10 | 2022-05-18 | 2022-05-18 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44896668 | T2 DI CORTINA-VACA 9/64 RPR OPGW | ICS
LC | 121367076 | 021/183 | T2 DI CRAG VIEW-CASCADE 21/183 RPR INSW | TABLEMTN | ETL.1350.INSL | 2021-05-20 | 2021-05-18 | 2021-05-25 | 2022-05-18 | 2021-08-16 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44817052 | T2 DI CRAG VIEW-CASCADE 21/183 RPR INSW | ICW
LC | 121367574 | A011/250 | T2 WV SALINAS-LAURELES A11/250 RPR SWTCH | MOSSLNDG | ETL.7930.POLE.NWOD | 2021-05-20 | 2021-05-20 | 2021-05-21 | 2022-05-20 | 2021-08-19 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 | Out of Adjustment | Switch | Repair | 44813259 | T2 WV SALINAS-LAURELES A11/250 RPR SWTCH | ICE
LC | 121369774 | 011/248 | T2 SALINAS-LAURELES 11/248 RPR SWITCH | MOSSLNDG | ETL.7930.SWIT | 2021-05-20 | 2021-05-20 | 2021-05-21 | 2022-05-20 | 2021-08-20 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | Out of Adjustment | Switch | Repair | 44813441 | T2 SALINAS-LAURELES 11/248 RPR SWITCH | ICE
LC | 121369786 | 011/250 | T2 SALINAS-LAURELES 11/250 RPR SWITCH | MOSSLNDG | ETL.7930.SWIT | 2021-05-20 | 2021-05-20 | 2021-05-21 | 2022-05-20 | 2021-08-20 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO | Out of Adjustment | Switch | Repair | 44813440 | T2 SALINAS-LAURELES 11/250 RPR SWITCH | ICE
LC | 121370260 | 011/045 | T2 DI MORRO BAY-TEMPLETON 11/45 RPR OPGW | PISMOBCH | ETL.5933.TOWR | 2021-05-20 | 2021-04-29 | 2021-06-04 | 2022-04-29 | 2021-07-29 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44837782 | T2 DI MORRO BAY-TEMPLETON 11/45 RPR OPGW | ICS
LC | 121371078 | 000/001 | T2 EI SALT SPRINGS-TIGER CRK 0/1 CTR KEY | VICTOR | ETL.3500.INSL | 2021-05-20 | 2021-05-20 | 2021-07-06 | 2022-05-20 | 2021-08-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44841521 | T2 EI SALT SPRINGS-TIGER CRK 0/1 CTR KEY | ICS
LC | 121372762 | :008/005 | T2 DI BLTA RVK MLNS SS :8/5 RPR INSW | VICTOR | ETL.1070.INSL.NCER | 2021-05-21 | 2021-05-20 | 2021-06-26 | 2022-05-20 | 2021-08-18 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44841523 | T2 DI BLTA RVK MLNS SS :8/5 RPR INSW | ICW
LC | 121375563 | 014/093 | T2 MILLBRAE-SNTH LN 14/93 SWITCH CMPLTD | METCALF | ETL.7570.SWIT | 2021-05-21 | 2021-05-21 | 2021-07-29 | 2022-05-21 | 2021-08-21 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Out of Adjustment | Switch | Repair | 44817606 | T2 MILLBRAE-SNEATH LANE 14/93 RPR SWITCH | ICE
LC | 121375959 | 009/071A | T2 EI HELMS-GREGG #1 9/071A RPR INSS | FRESNO | ETL.4870.TOWR | 2021-05-21 | 2021-05-21 | 2021-07-22 | 2022-05-21 | 2021-08-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44844064 | T2 EI HELMS-GREGG #1 9/071A RPR INSS | ICS
LC | 121376317 | 012/087A | T2 EI HELMS-GREGG #1 12/087A RPR INSS | FRESNO | ETL.4870.INSL | 2021-05-21 | 2021-05-21 | 2021-07-07 | 2022-05-21 | 2021-08-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44844065 | T2 EI HELMS-GREGG #1 12/087A RPR INSS | ICS
LC | 121376393 | 034/152 | T2 DI MOSS LDNG-LOS BANS 34/152 RPR SHLS | MOSSLNDG | ETL.6040.TOWR | 2021-05-21 | 2021-05-21 | 2021-06-02 | 2022-05-21 | 2021-08-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44817373 | T2 DI MOSS LDNG-LOS BANS 34/152 RPR SHLS | ICS
LC | 121376499 | 030/004 | T2 DI CLAY-MARTEL 30/4 RPL POLE | VICTOR | ETL.8250.POLE.WOOD | 2021-05-21 | 2021-05-21 | 2021-07-30 | 2022-05-21 | 2021-08-21 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541165 | T2 DI CLAY-MARTEL 30/4 RPL POLE | 70Y
LC | 121378056 | 086/003 | T2 EI HUMBOLDT-TRINITY 86/003 RPR INSW | EUREKA | ETL.1820.INSL.CERA | 2021-05-21 | 2021-05-21 | 2021-06-10 | 2022-05-21 | 2021-08-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44815958 | EI HUMBOLDT-TRINITY 86/003 RPR INSW | ICW
LC | 121378930 | 034/152 | T2 MOSS LANDING-LS BNS 34/152 INS DAMS | MOSSLNDG | ETL.6040.TOWR | 2021-05-21 | 2021-05-21 | 2021-06-02 | 2022-05-21 | 2021-08-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | Missing | Damper-Steel | Install | 44817374 | T2 MOSS LANDING-LS BNS 34/152 INS DAMS | ICS
LC | 121379443 | :011/003 | T2 DI BLTA-RBK-MS SS :011/003 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-05-22 | 2021-05-21 | 2021-07-03 | 2022-05-21 | 2021-08-19 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541172 | T2 DI BLTA-RBK-MS SS :011/003 RPL STRW | 70Y
LC | 121379586 | :003/022 | T2 DI STSLS-MLS SS-MTC #1 :3/22 CKT KEY | VICTOR | ETL.3830.INSL.NCER | 2021-05-22 | 2021-05-21 | 2021-08-04 | 2022-05-21 | 2021-08-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44947109 | T2 DI STSLS-MLS SS-MTC #1 :3/22 CKT KEY | ICS
LC | 121380289 | :007/043 | T2 DI STN ML SW ST-RBK JT :7/43 RPR SWTC | VICTOR | ETL.3840.SWIT | 2021-05-22 | 2021-05-21 | 2021-05-24 | 2022-05-21 | 2021-08-19 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Out of Adjustment | Switch | Repair | 44816586 | T2 DI STN ML SW ST-RBK JT :7/43 RPR SWTC | ICE
LC | 121380567 | 035/154 | T2 DI MOSS LANDNG-LS BNS 35/154 RPR INSS | MOSSLNDG | ETL.6040.INSL | 2021-05-22 | 2021-05-21 | 2021-06-02 | 2022-05-21 | 2021-08-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44817376 | T2 DI MOSS LANDNG-LS BNS 35/154 RPR INSS | ICS
LC | 121380636 | :004/028 | T2 DI STNSLS-MLNS-MNTC :4/28 RPLC INSS | VICTOR | ETL.3840.INSL.NCER | 2021-05-22 | 2021-05-21 | 2021-08-09 | 2022-05-21 | 2021-08-19 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31541213 | T2 DI STNSLS-MLNS-MNTC :4/28 RPLC INSS | 93K
LC | 121380874 | 036/156 | T2 DI MOSS LANDNG-LOS BNS 36/156 RPR INS | MOSSLNDG | ETL.6040.INSL | 2021-05-22 | 2021-05-21 | 2021-05-22 | 2022-05-21 | 2021-08-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44813545 | T2 DI MOSS LANDNG-LOS BNS 36/156 RPR INS | ICS
LC | 121380876 | 010/041 | T2 DI TESLA-METCALF 010/041 RPR SHLS | METCALF | ETL.6110.TOWR | 2021-05-22 | 2021-05-21 | 2021-06-18 | 2022-05-21 | 2021-08-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44817609 | T2 DI TESLA-METCALF 010/041 RPR SHLS | ICS
LC | 121380973 | :007/007 | T2 DI BELLOTA-RVRBNK-MLNS :7/7 RPR INSS | VICTOR | ETL.1070.SWIT | 2021-05-22 | 2021-05-21 | 2021-06-26 | 2022-05-21 | 2021-08-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44938150 | T2 DI BELLOTA-RVRBNK-MLNS :7/7 RPR INSS | ICS
LC | 121384178 | 012/073 | T2 DI STAN-MEL-MANTECA 12/73 RPR STRT | VICTOR | ETL.3830.TOWR | 2021-05-23 | 2021-05-21 | 2021-05-26 | 2022-05-21 | 2021-08-21 | On-time | 543 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair | 44816802 | T2 DI STAN-MEL-MANTECA 12/73 RPR STRT | ICQ
LC | 121384271 | 012/073 | T2 DI STAN-MEL-MANTECA 12/73 COTTER | VICTOR | ETL.3830.INSL | 2021-05-23 | 2021-05-21 | 2021-08-04 | 2022-05-21 | 2021-08-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44841525 | T2 DI STAN-MEL-MANTECA 12/73 COTTER | ICS
LC | 121384284 | 013/003 | T2 DI MNDCNO-WLLTS-FT BRGG 13/3 RPR INSW | LAKEVLLE | ETL.7550.INSL.NCER | 2021-05-23 | 2021-05-21 | 2021-06-07 | 2022-05-21 | 2021-08-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44816513 | T2 DI MNDCNO-WLLTS-FT BRGG 13/3 RPR INSW | ICW
LC | 121384401 | 059/243 | T2 DI DIABLO-GATES #1 059/243 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2021-05-23 | 2021-05-21 | 2021-06-24 | 2022-05-21 | 2021-08-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 44875585 | T2 DI DIABLO-GATES #1 059/243 RPR GYWS | ICS
LC | 121384402 | 010/093 | T2 DI EL DRD-MSRI FT #1 10/93 INS CTR KY | SACTO | ETL.1530.INSL | 2021-05-23 | 2021-05-21 | 2021-08-15 | 2022-05-21 | 2021-08-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44876363 | T2 DI EL DRD-MSRI FT #1 10/93 INS CTR KY | ICS
LC | 121384404 | 010/093 | T2 DI EL DRD-MSRI FT #2 10/93 INS CTR KY | SACTO | ETL.1540.SWIT | 2021-05-23 | 2021-05-21 | 2021-08-15 | 2022-05-21 | 2021-08-19 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Out of Adjustment | Switch | Repair | 44876367 | T2 DI EL DRD-MSRI FT #2 10/93 INS CTR KY | ICE
LC | 121386412 | 000/009 | T2 MUSTANG TAP 000/009 RPR SWITCH | PISMOBCH | ETL.9091.INSL.NCER | 2021-05-24 | 2021-05-24 | 2021-06-03 | 2022-05-24 | 2021-08-24 | On-time | 925 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Request | WRO | Switching | 44815813 | T2 MUSTANG TAP 000/009 RPR SWITCH | CHD
LC | 121387178 | 012/071 | T2 DI STNSLUS-MLONS 012/071 RPR INSS | VICTOR | ETL.3830.INSL | 2021-05-24 | 2021-05-21 | 2021-08-01 | 2022-05-21 | 2021-08-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44841527 | T2 DI STNSLUS-MLONS 012/071 RPR INSS | ICS
LC | 121387345 | 012/071 | T2 DI STNSLUS-MLONS 012/071 RPR STRT | VICTOR | ETL.3830.TOWR | 2021-05-24 | 2021-05-21 | 2021-08-02 | 2022-05-21 | 2021-08-19 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 44817605 | T2 DI STNSLUS-MLONS 012/071 RPR STRT | ICQ
LC | 121387486 | 008/033 | T2 DI TESLA-METCALF 008/033 RPR SHLD | METCALF | ETL.6110.TOWR | 2021-05-24 | 2021-05-21 | 2021-06-18 | 2022-05-21 | 2021-08-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44817612 | T2 DI TESLA-METCALF 008/033 RPR SHLD | ICS
LC | 121387849 | 010/018 | T2 DI TRNTY-MAPLE CRK 010/018 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2021-05-24 | 2021-05-21 | 2021-06-11 | 2022-05-21 | 2021-08-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44817234 | T2 DI TRNTY-MAPLE CRK 010/018 RPR GYWW | ICW
LC | 121390969 | 009/068 | T2 DI ROCK CREEK-POE 009/068 RPL INSS | TABLEMTN | ETL.5630.INSL | 2021-05-24 | 2021-05-24 | 2021-05-27 | 2022-05-24 | 2021-08-22 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31541441 | T2 DI ROCK CREEK-POE 009/068 RPL INSS | 93K
LC | 121394676 | 010/066 | T2 OLEUM-G #1 10/66 RPL HRDT | CONCORD | ETL.3150.TOWR | 2021-05-25 | 2021-05-24 | 2021-07-01 | 2022-05-24 | 2021-08-24 | On-time | 543 | Upgraded | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair | 44856735 | T2 OLEUM-G #1 10/66 RPL HRDT | ICQ
LC | 121404431 | 018/115 | T2 EI STNILS-MLN SW ST-MNT 18/115 RPR SW | VICTOR | ETL.3830.SWIT | 2021-05-26 | 2021-05-26 | 2021-05-27 | 2022-05-26 | 2021-08-26 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO AIR | Out of Adjustment | Switch | Repair | 44825556 | T2 EI STNILS-MLN SW ST-MNT 18/115 RPR SW | ICE
LC | 121406674 | 003/031 | T2 DI PT #1-HT CRK #2-BRNY 3/31 RPR ADSS | TABLEMTN | ETL.7040.POLE.WOOD | 2021-05-27 | 2021-05-22 | 2021-06-12 | 2022-05-22 | 2021-08-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44828262 | T2 DI PT #1-HT CRK #2-BRNY 3/31 RPR ADSS | ICW
LC | 121417437 | 020/160 | T2 DI PARADISE-TBLE MTN 20/160 RPR GYWW | TABLEMTN | ETL.4316.POLE.STPS | 2021-05-27 | 2021-05-26 | 2021-06-01 | 2022-05-26 | 2021-08-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44826220 | T2 DI PARADISE-TBLE MTN 20/160 RPR GYWW | ICW
LC | 121417480 | 020/160 | T2 DI PARADISE-TBLE MTN 20/160 RPR GYWW | TABLEMTN | ETL.4316.POLE.STPS | 2021-05-27 | 2021-05-26 | 2021-06-01 | 2022-05-26 | 2021-08-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44825739 | T2 DI PARADISE-TBLE MTN 20/160 RPR GYWW | ICW
LC | 121422084 | 093/476 | T2 DI MALIN-RND MTN #2 93/476 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-05-28 | 2021-05-28 | 2021-06-02 | 2022-05-28 | 2021-08-28 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44828266 | T2 DI MALIN-RND MTN #2 93/476 RPR OPGW | ICS
LC | 121429783 | 014/058 | T2 DI TESLA-METCALF 014/058 INS CTR KEY | METCALF | ETL.6110.INSL.CERA | 2021-05-29 | 2021-05-28 | 2021-07-12 | 2022-05-28 | 2021-08-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44828316 | T2 DI TESLA-METCALF 014/058 INS CTR KEY | ICS
LC | 121429885 | 010/078 | T2 DI GREEN VALLEY-LLAGAS 10/78 RPR INSW | MOSSLNDG | ETL.1720.INSL.NCER | 2021-05-29 | 2021-05-28 | 2021-06-24 | 2022-05-28 | 2021-08-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44857424 | T2 DI GREEN VALLEY-LLAGAS 10/78 RPR INSW | ICW
LC | 121430072 | 015/063 | T2 DI TESLA-METCALF 15/63 COTR KEY | METCALF | ETL.6110.INSL.CERA | 2021-05-29 | 2021-05-28 | 2021-07-12 | 2022-05-28 | 2021-08-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44828317 | T2 DI TESLA-METCALF 15/63 COTR KEY | ICS
LC | 121430077 | 020/004 | T2 DI MNDCN-WLTS-FRT BRG 2/4 RPR INSW | LAKEVLLE | ETL.7550.INSL.NCER | 2021-05-29 | 2021-05-28 | 2021-06-11 | 2022-05-28 | 2021-08-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44829753 | T2 DI MNDCN-WLTS-FRT BRG 2/4 RPR INSW | ICW
LC | 121430197 | 013/056 | T2 DI TESLA-METCALF 13/56 RPR OPGW | METCALF | ETL.6110.TOWR | 2021-05-29 | 2021-05-28 | 2021-07-12 | 2022-05-28 | 2021-08-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44828343 | T2 DI TESLA-METCALF 13/56 RPR OPGW | ICS
LC | 121431223 | 051/003 | T2 DI HUMBOLDT-TRINITY 51/3 RPLC INSW | EUREKA | ETL.1820.INSL.CERA | 2021-05-29 | 2021-05-28 | 2021-07-31 | 2022-05-28 | 2021-08-28 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541923 | T2 DI HUMBOLDT-TRINITY 51/3 RPLC INSW | 93I
LC | 121434916 | 019/224 | T2 EI DRUM-SUMMIT#2 019/224 CNDW CMPTLD | SACTO | ETL.1450.INSL.CERA | 2021-05-31 | 2021-05-25 | 2021-08-28 | 2022-05-25 | 2021-08-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair | 44876370 | T2 EI DRUM-SUMMIT#2 019/224 RPR CNDW | ICW
LC | 121435027 | 023/177 | T2 DI PARADISE-TABLE MTN 23/177 COTTER | TABLEMTN | ETL.4316.INSL.CERA | 2021-06-01 | 2021-05-28 | 2021-06-08 | 2022-05-28 | 2021-08-28 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44829942 | T2 DI PARADISE-TABLE MTN 23/177 COTTER | ICS
LC | 121435323 | 021/171 | T2 DI MDL FRK-GLD HL 21/171 RPR INSW | SACTO | ETL.5140.INSL.CERA | 2021-06-01 | 2021-05-29 | 2021-08-10 | 2022-05-29 | 2021-08-27 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876356 | T2 DI MDL FRK-GLD HL 21/171 RPR INSW | ICW
LC | 121435340 | 069/607 | T2 DI COTTONWOOD-GLENN 69/607 RPR INSS | TABLEMTN | ETL.4560.INSL | 2021-06-01 | 2021-05-29 | 2021-07-13 | 2022-05-29 | 2021-08-27 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44829943 | T2 DI COTTONWOOD-GLENN 69/607 RPR INSS | ICS
LC | 121435349 | 032/001 | T2 DI PHILO JCT-ELK 032/001 RPR GYWW | LAKEVLLE | ETL.7780.POLE.WOOD | 2021-06-01 | 2021-05-29 | 2021-07-07 | 2022-05-29 | 2021-08-29 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44830272 | T2 DI PHILO JCT-ELK 032/001 RPR GYWW | ICW
LC | 121435351 | 008/095 | T2 DI VEDDER TAP 8/95 COTTER | MIDWAY | ETL.2141.INSL.NCER | 2021-06-01 | 2021-05-28 | 2021-07-01 | 2022-05-28 | 2021-08-28 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44826571 | T2 DI VEDDER TAP 8/95 COTTER | ICW
LC | 121435454 | 039/000 | T2 DI FORT ROSS-GUALALA 039/000 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2021-06-01 | 2021-05-29 | 2021-06-14 | 2022-05-29 | 2021-08-29 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44830270 | T2 DI FORT ROSS-GUALALA 039/000 RPR INSW | ICW
LC | 121435456 | 039/011 | T2 DI FORT ROSS-GUALALA 039/011 RPR GYWW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-06-01 | 2021-05-29 | 2021-06-10 | 2022-05-29 | 2021-08-29 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44830269 | T2 DI FORT ROSS-GUALALA 039/011 RPR INSW | ICW
LC | 121435459 | 039/011 | T2 DI FORT ROSS-GUALALA 039/011 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2021-06-01 | 2021-05-29 | 2021-06-10 | 2022-05-29 | 2021-08-29 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44830269 | T2 DI FORT ROSS-GUALALA 039/011 RPR INSW | ICW
LC | 121435719 | 043/005 | T2 DI FORT ROSS-GUALALA 43/5 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2021-06-01 | 2021-05-29 | 2021-06-10 | 2022-05-29 | 2021-08-29 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44830271 | T2 DI FORT ROSS-GUALALA 43/5 RPR INSW | ICW
LC | 121436109 | 013/136 | T2 DI RND MTN-CTTNWD #2 13/136 RPR OPGW | TABLEMTN | ETL.5640.TOWR | 2021-06-01 | 2021-05-29 | 2021-06-16 | 2022-05-29 | 2021-08-27 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44829944 | T2 DI RND MTN-CTTNWD #2 13/136 RPR OPGW | ICS
LC | 121436856 | 012/096 | T2 DI CARIBOU-TABLE MTN 012/096 RPR INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-01 | 2021-05-29 | 2021-06-28 | 2022-05-29 | 2021-08-27 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44829945 | T2 DI CARIBOU-TABLE MTN 012/096 RPR INSS | ICS
LC | 121437016 | 023/002 | T2 DI PHILO JCT-ELK 023/002 RPR INSW | LAKEVLLE | ETL.7780.INSL | 2021-06-01 | 2021-05-29 | 2021-07-07 | 2022-05-29 | 2021-08-29 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44830274 | T2 DI PHILO JCT-ELK 023/002 RPR INSW | ICW
LC | 121437647 | 014/059 | T2 DI TESLA-METCALF 14/59 RPR INSS | METCALF | ETL.6110.INSL.CERA | 2021-06-01 | 2021-05-29 | 2021-07-12 | 2022-05-29 | 2021-08-27 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44839369 | T2 DI TESLA-METCALF 14/59 RPR INSS | ICS
LC | 121437798 | 027/112 | T2 DI TESLA-METCALF 027/112 RPR INSS | METCALF | ETL.6110.INSL | 2021-06-01 | 2021-05-28 | 2021-06-22 | 2022-05-28 | 2021-08-28 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44839367 | T2 DI TESLA-METCALF 027/112 RPR INSS | ICS
LC | 121438147 | 072/368 | T2 EI MLIN-RND MTN #2 72/368 RPR CONDS | TABLEMTN | ETL.6020.INSL | 2021-06-01 | 2021-06-01 | 2021-06-07 | 2022-06-01 | 2021-09-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Conductor-Steel | Repair | 44829947 | T2 EI MLIN-RND MTN #2 72/368 RPR CONDS | ICS
LC | 121443734 | 042/007 | T2 DI FORT ROSS-GUALALA 42/7 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2021-06-02 | 2021-05-29 | 2021-06-10 | 2022-05-29 | 2021-08-29 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44837945 | T2 DI FORT ROSS-GUALALA 42/7 RPR INSW | ICW
LC | 121446067 | 026/108 | T2 DI TESLA-METCALF 26/108 RPR INSS | METCALF | ETL.6110.INSL | 2021-06-02 | 2021-06-02 | 2021-06-22 | 2022-06-02 | 2021-09-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44839376 | T2 DI TESLA-METCALF 26/108 RPR INSS | ICS
LC | 121446068 | :001/010 | T2 DI ROCK CREEK-POE :001/010 RPR INSS | TABLEMTN | ETL.5630.INSL | 2021-06-02 | 2021-06-01 | 2021-08-04 | 2022-06-01 | 2021-09-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44856984 | T2 DI ROCK CREEK-POE :001/010 RPR INSS | ICS
LC | 121446271 | 020/140 | T2 DI CARIBOU-TABLE MTN 20/140 RPR INSS | TABLEMTN | ETL.4440.INSL | 2021-06-02 | 2021-06-02 | 2021-08-04 | 2022-06-02 | 2021-09-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44856983 | T2 DI CARIBOU-TABLE MTN 20/140 RPR INSS | ICS
LC | 121446865 | 022/002 | T2 EI CLEAR LAKE-KONOCTI 22/002 COTTER | LAKEVLLE | ETL.6852.INSL.CERA | 2021-06-02 | 2021-06-02 | 2021-06-24 | 2022-06-02 | 2021-09-02 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876074 | T2 EI CLEAR LAKE-KONOCTI 22/002 COTTER | ICW
LC | 121447105 | 084/001 | T2 EI HUMBPLDT-TRINITY 84/1 INS COTR KEY | EUREKA | ETL.1820.INSL | 2021-06-02 | 2021-05-27 | 2021-06-10 | 2022-05-27 | 2021-08-27 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44838566 | T2 EI CTTNWD-HUMBLDT 84/1 INS COTR KEY | ICW
LC | 121447210 | 087/444B | T2 DI MLN-RND MTN #2 087/444A RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-02 | 2021-06-02 | 2021-06-04 | 2022-06-02 | 2021-09-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44829948 | T2 DI MLN-RND MTN #2 087/444A RPR SHLS | ICS
LC | 121447308 | 013/133 | T2 DI RND MTN-CTTNWD #2 13/133 RPR OPGW | TABLEMTN | ETL.5640.TOWR | 2021-06-02 | 2021-06-02 | 2021-06-28 | 2022-06-02 | 2021-09-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44856985 | T2 DI RND MTN-CTTNWD #2 13/133 RPR OPGW | ICS
LC | 121447470 | 027/109 | T2 DI DIABLO-MIDWAY #3 27/109 RPR INSS | PISMOBCH | ETL.5980.INSL | 2021-06-02 | 2021-06-02 | 2021-06-23 | 2022-06-02 | 2021-09-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44875295 | T2 DI DIABLO-MIDWAY #3 27/109 RPR INSS | ICS
LC | 121447494 | 003/017 | T2 EI FULTON-PUEBLO 3/17 COTTER | LAKEVLLE | ETL.1600.TOWR | 2021-06-02 | 2021-06-02 | 2021-06-07 | 2022-06-02 | 2021-09-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44836855 | T2 EI FULTON-PUEBLO 3/17 COTTER | ICS
LC | 121450307 | 046/404 | T2 DI RND MTN-CTNWD #3 46/404 RPR STRT | TABLEMTN | ETL.5650.TOWR | 2021-06-03 | 2021-06-02 | 2021-07-22 | 2022-06-02 | 2021-08-31 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Tower | Repair | 44856573 | T2 DI RND MTN-CTNWD #3 46/404 RPR STRT | ICQ
LC | 121450313 | 029/255 | T2 DI RND MTN-CTNWD #2 29/255 RPR STRT | TABLEMTN | ETL.5640.TOWR | 2021-06-03 | 2021-06-02 | 2021-07-22 | 2022-06-02 | 2021-08-31 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Tower | Repair | 44856572 | T2 DI RND MTN-CTNWD #2 29/255 RPR STRT | ICQ
LC | 121450372 | 046/404 | T2 DI RND MTN-CTNWD #3 46/404 COTTER KEY | TABLEMTN | ETL.5650.INSL | 2021-06-03 | 2021-06-02 | 2021-06-26 | 2022-06-02 | 2021-08-31 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44856989 | T2 DI RND MTN-CTNWD #3 46/404 COTTER KEY | ICS
LC | 121450376 | 092/471C | T2 DI MALIN-RND MTN #2 92/471B RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-03 | 2021-06-01 | 2021-06-08 | 2022-06-01 | 2021-08-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44845595 | T2 DI MALIN-RND MTN #2 92/471B RPR SHLS | ICS
LC | 121450379 | 048/423 | T2 DI RND MTN-CTNWD #3 48/423 COTTER KEY | TABLEMTN | ETL.5650.INSL | 2021-06-03 | 2021-06-02 | 2021-06-29 | 2022-06-02 | 2021-08-31 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44856992 | T2 DI RND MTN-CTNWD #3 48/423 COTTER KEY | ICS
LC | 121450766 | 035/291 | T2 DI KILARC-VOLTA 35/291 COTTER KEY | TABLEMTN | ETL.7310.INSL | 2021-06-03 | 2021-06-02 | 2021-08-07 | 2022-06-02 | 2021-08-31 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44856993 | T2 DI KILARC-VOLTA 35/291 COTTER KEY | ICS
LC | 121450896 | 055/494 | T2 DI PIT #1-COTTONWD 55/494 COTTER KEY | TABLEMTN | ETL.5390.INSL.CERA | 2021-06-03 | 2021-06-02 | 2021-06-12 | 2022-06-02 | 2021-08-31 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44856348 | T2 DI PIT #1-COTTONWD 55/494 COTTER KEY | ICS
LC | 121450950 | 013/135 | T2 DI RND MTN-CTNWD #2 13/135 RPR OPGW | TABLEMTN | ETL.5640.TOWR | 2021-06-03 | 2021-06-02 | 2021-06-17 | 2022-06-02 | 2021-08-31 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44856986 | T2 DI RND MTN-CTNWD #2 13/135 RPR OPGW | ICS
LC | 121451643 | 012/048 | T2 DI TESLA-METCALF 12/48 COTTER | METCALF | ETL.6110.INSL.NCER | 2021-06-03 | 2021-06-02 | 2021-07-12 | 2022-06-02 | 2021-09-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44839377 | T2 DI TESLA-METCALF 12/48 COTTER | ICS
LC | 121452012 | 061/304 | T2 DI MALIN-ROUND MTN #2 61/304 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-06-03 | 2021-06-02 | 2021-06-08 | 2022-06-02 | 2021-08-31 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44845594 | T2 DI MALIN-ROUND MTN #2 61/304 RPR INSS | ICS
LC | 121452139 | 047/413 | T2 DI RND MTN-CTNWD #3 47/413 COTTER KEY | TABLEMTN | ETL.5650.INSL | 2021-06-03 | 2021-06-03 | 2021-07-01 | 2022-06-03 | 2021-09-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44856991 | T2 DI RND MTN-CTNWD #3 47/413 COTTER KEY | ICS
LC | 121452400 | 009/038 | T2 DI EGL RCK-FLTN-SLVRD 9/38 COTTER KEY | LAKEVLLE | ETL.4392.INSL.CERA | 2021-06-03 | 2021-06-02 | 2021-07-09 | 2022-06-02 | 2021-09-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44838153 | T2 DI EGL RCK-FLTN-SLVRD 9/38 COTTER KEY | ICS
LC | 121452402 | 009/038 | T2 DI GEYSERS #9-LAKVILL 9/38 COTTER KEY | LAKEVLLE | ETL.4780.INSL.CERA | 2021-06-03 | 2021-06-02 | 2021-07-09 | 2022-06-02 | 2021-09-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44838154 | T2 DI GEYSERS #9-LAKVILL 9/38 COTTER KEY | ICS
LC | 121466217 | 036/296 | T2 DI RND MTN-CTTND #2 36/296 RPR SHLS | TABLEMTN | ETL.5640.TOWR | 2021-06-04 | 2021-06-03 | 2021-07-25 | 2022-06-03 | 2021-09-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44856988 | T2 DI RND MTN-CTTND #2 36/296 RPR SHLS | ICS
LC | 121466478 | 018/008 | T2 DI TRINITY-MAPLE CREEK 18/8 RPR INSW | EUREKA | ETL.8170.INSL | 2021-06-04 | 2021-06-03 | 2021-06-11 | 2022-06-03 | 2021-09-01 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44841566 | T2 DI TRINITY-MAPLE CREEK 18/8 RPR INSW | ICW
LC | 121466645 | 049/246 | T2 DI MALIN-ROUND MTN #2 49/246 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-04 | 2021-06-03 | 2021-06-09 | 2022-06-03 | 2021-09-03 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44850334 | T2 DI MALIN-ROUND MTN #2 49/246 RPR SHLS | ICS
LC | 121466782 | 022/090 | T2 DI DIABLO-MIDWAY #2 022/090 RPL HRDT | PISMOBCH | ETL.5970.TOWR | 2021-06-04 | 2021-06-01 | 2021-06-14 | 2022-06-01 | 2021-08-30 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Tower | Install | 44844662 | T2 DI DIABLO-MIDWAY #2 022/090 RPL HRDT | ICQ
LC | 121466833 | 069/348A | T2 DI MALIN-RND MTN #2 69/348A RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-04 | 2021-06-03 | 2021-06-09 | 2022-06-03 | 2021-09-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44850330 | T2 DI MALIN-RND MTN #2 69/348A RPR SHLS | ICS
LC | 121467284 | 006/048 | T2 DI WISHON-COPPERMINE 6/48 COTTER | FRESNO | ETL.9330.INSL.NCER | 2021-06-04 | 2021-06-03 | 2021-06-14 | 2022-06-03 | 2021-09-03 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44844074 | T2 DI WISHON-COPPERMINE 6/48 COTTER | ICS
LC | 121467650 | 063/318 | T2 DI MALIN-RND MTN #2 063/318 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-04 | 2021-06-03 | 2021-06-09 | 2022-06-03 | 2021-09-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44850333 | T2 DI MALIN-RND MTN #2 063/318 RPR SHLS | ICS
LC | 121468226 | 011/076 | T2 DI CTTNWOOD-DELEVAN #1 11/76 RPR SHW | TABLEMTN | ETL.4550.TOWR | 2021-06-04 | 2021-06-02 | 2021-07-24 | 2022-06-02 | 2021-09-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44856995 | T2 DI CTTNWOOD-DELEVAN #1 11/76 RPR SHW | ICS
LC | 121468339 | 073/373 | T2 DI MALIN-RND MTN #2 073/373 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-06-04 | 2021-06-03 | 2021-06-09 | 2022-06-03 | 2021-09-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44850331 | T2 DI MALIN-RND MTN #2 073/373 RPR INSS | ICS
LC | 121468640 | :001/012 | T2 DI ROCK CREEK-POE :1/12 RPR INSS | TABLEMTN | ETL.5630.INSL | 2021-06-04 | 2021-06-02 | 2021-06-10 | 2022-06-02 | 2021-08-31 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44851816 | T2 DI ROCK CREEK-POE :1/12 RPR INSS | ICS
LC | 121469650 | 047/411 | T2 DI RND MTN-CTTNWD #3 47/411 RPR INSS | TABLEMTN | ETL.5650.INSL | 2021-06-04 | 2021-06-03 | 2021-07-01 | 2022-06-03 | 2021-09-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44856990 | T2 DI RND MTN-CTTNWD #3 47/411 RPR INSS | ICS
LC | 121469754 | 035/295 | T2 DI RND MTN-CTTNWD #2 035/295 RPR SHLS | TABLEMTN | ETL.5640.TOWR | 2021-06-04 | 2021-06-03 | 2021-06-19 | 2022-06-03 | 2021-09-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44856987 | T2 DI RND MTN-CTTNWD #2 035/295 RPR SHLS | ICS
LC | 121471042 | 018/011 | T2 DI MNDCN-WLTS-FRT BRG 18/11 RPR INSW | LAKEVLLE | ETL.7550.INSL.NCER | 2021-06-04 | 2021-05-27 | 2021-06-24 | 2022-05-27 | 2021-08-27 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44842153 | T2 DI MNDCN-WLTS-FRT BRG 18/11 RPR INSW | ICW
LC | 121473224 | 003/021 | T2 DI MOSS LDNG-MTCLF 3/21 SHLS CMPLTD | MOSSLNDG | ETL.6050.TOWR | 2021-06-05 | 2021-06-03 | 2021-06-14 | 2022-06-03 | 2021-09-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44858871 | T2 DI MOSS LANDING-METCALF 3/21 RPR SHLS | ICS
LC | 121474266 | 088/001 | T2 DI HUMBOLDT-TRINITY 088/001 RPR INSW | EUREKA | ETL.1820.INSL.CERA | 2021-06-05 | 2021-06-04 | 2021-07-31 | 2022-06-04 | 2021-09-02 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44842935 | T2 DI HUMBOLDT-TRINITY 088/001 RPR INSW | ICW
LC | 121474380 | 088/001 | T2 DI HUMBOLDT-TRINITY 088/001 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-05 | 2021-06-04 | 2021-07-31 | 2022-06-04 | 2021-09-04 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 44856345 | T2 DI HUMBOLDT-TRINITY 088/001 RPR GYWW | ICW
LC | 121475732 | 011/100 | T2 DI CRAG VIEW-CASCADE 11/100 RPR INSW | TABLEMTN | ETL.1350.INSL.CERA | 2021-06-05 | 2021-06-04 | 2021-06-16 | 2022-06-04 | 2021-09-04 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 44856994 | T2 DI CRAG VIEW-CASCADE 11/100 RPR INSW | ICW
LC | 121480996 | 062/310 | T2 DI MALIN-ROUND MTN #2 62/310 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-06-07 | 2021-06-03 | 2021-06-10 | 2022-06-03 | 2021-09-03 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44850754 | T2 DI MALIN-ROUND MTN #2 62/310 RPR OPGW | ICS
LC | 121481058 | 013/120 | T2 DI DRUM-RIO OSO #1 13/120 RPR INSS | SACTO | ETL.1420.INSL.CERA | 2021-06-07 | 2021-06-01 | 2021-08-25 | 2022-06-01 | 2021-08-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44876354 | T2 DI DRUM-RIO OSO #1 13/120 RPR INSS | ICS
LC | 121481739 | 007/053 | T2 DI CTNWD-DLVN #1 7/53 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-06-07 | 2021-05-29 | 2021-06-19 | 2022-05-29 | 2021-08-29 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44857001 | T2 DI CTNWD-DLVN #1 7/53 RPR OPGW | ICS
LC | 121482409 | 019/105 | T2 DI BALCH-MCCALL 19/105 RPR INSS | FRESNO | ETL.4350.INSL | 2021-06-07 | 2021-06-05 | 2021-08-05 | 2022-06-05 | 2021-09-03 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44844075 | T2 DI BALCH-MCCALL 19/105 RPR INSS | ICS
LC | 121483111 | 031/146 | T2 DI TRACY-LOS BANOS 31/146 RPR INSS | VICTOR | ETL.6130.INSL | 2021-06-07 | 2021-06-05 | 2021-10-05 | 2022-06-05 | 2021-09-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44858247 | T2 DI TRACY-LOS BANOS 31/146 RPR INSS | ICS
LC | 121483321 | 020/106 | T2 DI HAAS-MC CALL 020/106 RPR STRT | FRESNO | ETL.4850.INSL | 2021-06-07 | 2021-06-07 | 2021-06-09 | 2022-06-07 | 2021-09-05 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Structure-Tower | Repair | 44843394 | T2 DI HAAS-MC CALL 020/106 RPR STRT | ICQ
LC | 121485049 | 002/020 | T2 DI CRAG VIEW-CASCADE 002/020 RPR INSW | TABLEMTN | ETL.1350.INSL.CERA | 2021-06-07 | 2021-06-04 | 2021-06-17 | 2022-06-04 | 2021-09-02 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44857003 | T2 DI CRAG VIEW-CASCADE 002/020 RPR INSW | ICW
LC | 121488032 | 029/002 | T2 CLAY-MARTEL 29/2 RPR CNDW | VICTOR | ETL.8250.POLE.WOOD | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2022-06-08 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 44841794 | T2 CLAY-MARTEL 29/2 RPR CNDW | ICW
LC | 121489488 | 047/191 | T2 DI MIDWAY-WHIRLWIND 47/191 RPR INSS | MIDWAY | ETL.6030.INSL | 2021-06-08 | 2021-06-07 | 2021-07-09 | 2022-06-07 | 2021-09-07 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44875594 | T2 DI MIDWAY-WHIRLWIND 47/191 RPR INSS | ICS
LC | 121489803 | 017/526 | T2 DI SPAULDING-SUMMIT 17/526 COTTER | SACTO | ETL.8060.INSL.CERA | 2021-06-08 | 2021-06-07 | 2021-08-26 | 2022-06-07 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876347 | T2 DI SPAULDING-SUMMIT 17/526 COTTER | ICW
LC | 121490691 | 004/114 | T2 DI HAMILTON BRAN-CHSTR 4/114 RPR INSW | TABLEMTN | ETL.7000.INSL.CERA | 2021-06-08 | 2021-06-08 | 2021-06-24 | 2022-06-08 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44857006 | T2 DI HAMILTON BRAN-CHSTR 4/114 RPR INSW | ICW
LC | 121490699 | 013/169 | T2 DI WST PNT-VLLY SPNGS 13/169 COTTER | VICTOR | ETL.8350.POLE.NWOD | 2021-06-08 | 2021-06-08 | 2021-07-06 | 2022-06-08 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44858249 | T2 DI WST PNT-VLLY SPNGS 13/169 COTTER | ICW
LC | 121491005 | 006/103 | T2 DI PT #1-HT CRK #2-BRY 6/103 RPR GYWW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-06-08 | 2021-06-08 | 2021-06-25 | 2022-06-08 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44857010 | T2 DI PT #1-HT CRK #2-BRY 6/103 RPR GYWW | ICW
LC | 121491062 | 018/593 | T2 DI SPAULNG-SUMMIT 18/593 COTTER | SACTO | ETL.8060.INSL.NCER | 2021-06-08 | 2021-06-08 | 2021-08-26 | 2022-06-08 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44876346 | T2 DI SPAULNG-SUMMIT 18/593 COTTER | ICS
LC | 121491068 | 001/063 | T2 DI SPALDNG-SUMMIT 1/063 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-06-08 | 2021-06-07 | 2021-08-26 | 2022-06-07 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44876345 | T2 DI SPALDNG-SUMMIT 1/063 RPR GYWW | ICW
LC | 121491206 | 010/122 | T2 DI W POINT VLLY SPRGS 10/122 COTTER | VICTOR | ETL.8350.INSL.NCER | 2021-06-08 | 2021-06-08 | 2021-07-06 | 2022-06-08 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44858250 | T2 DI W POINT VLLY SPRGS 10/122 COTTER | ICW
LC | 121491389 | 010/126 | T2 DI W POINT VLLY SPRGS 10/126 RPR SWTC | VICTOR | ETL.8350.SWIT | 2021-06-08 | 2021-06-08 | 2021-08-30 | 2022-06-08 | 2021-09-08 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Out of Adjustment | Switch | Repair | 44858251 | T2 DI W POINT VLLY SPRGS 10/126 RPR SWTC | ICE
LC | 121491737 | 001/015 | T2 DI CARIBOU #2 001/015 RPR INSW | TABLEMTN | ETL.6280.INSL.NCER | 2021-06-08 | 2021-06-08 | 2021-06-10 | 2022-06-08 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44857008 | T2 DI CARIBOU #2 001/015 RPR INSW | ICW
LC | 121491789 | 000/006 | T2 DI SPAULDING-SUMMIT 0/6 RPR INSW | SACTO | ETL.8060.INSL.NCER | 2021-06-08 | 2021-06-08 | 2021-08-26 | 2022-06-08 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876344 | T2 DI SPAULDING-SUMMIT 0/6 RPR INSW | ICW
LC | 121491913 | 016/513 | T2 DI SPAULDNG-SUMMIT 016/513 COTTER | SACTO | ETL.8060.INSL.NCER | 2021-06-08 | 2021-06-08 | 2021-08-26 | 2022-06-08 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876343 | T2 DI SPAULDNG-SUMMIT 016/513 COTTER | ICW
LC | 121491993 | 010/119 | T2 DI W POINT VLLY SPRGS 10/119 RPR GYWW | VICTOR | ETL.8350.POLE.WOOD | 2021-06-08 | 2021-06-08 | 2021-08-31 | 2022-06-08 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44858252 | T2 DI W POINT VLLY SPRGS 10/119 RPR GYWW | ICW
LC | 121492023 | 010/337 | T2 DI SPAULDING-SUMMIT 10/337 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-06-08 | 2021-06-08 | 2021-07-21 | 2022-06-08 | 2021-09-08 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44876216 | T2 DI SPAULDING-SUMMIT 10/337 RPR GYWW | ICW
LC | 121492162 | 053/007 | T2 DI HUMBOLDT-TRINITY 53/7 RPR COTTER | EUREKA | ETL.1820.INSL.NCER | 2021-06-08 | 2021-06-08 | 2021-12-07 | 2022-06-08 | 2021-09-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44850461 | T2 DI HUMBOLDT-TRINITY 53/7 RPR INSS | ICS
LC | 121492327 | 086/439 | T2 DI MLN-RND MNTN #2 086/439 RPR SHIELD | TABLEMTN | ETL.6020.TOWR | 2021-06-08 | 2021-06-02 | 2021-06-14 | 2022-06-02 | 2021-09-02 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44858383 | T2 DI MLN-RND MNTN #2 086/439 RPR SHIELD | ICS
LC | 121492331 | 006/036 | T2 SBRNT-STNDRD OIL SW #2 6/36 RMV DBRS | CONCORD | ETL.3790.INSL | 2021-06-08 | 2021-06-08 | 2021-07-02 | 2022-06-08 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 | Debris/Nest/etc. | Conductor-Steel | Remove | 44856429 | T2 SBRNT-STNDRD OIL SW #2 6/36 RMV DBRS | ICS
LC | 121492882 | 010/125 | T2DI WEST POINT-VLY SPGS 10/125 RPR SWTC | VICTOR | ETL.8350.POLE.NWOD | 2021-06-08 | 2021-06-08 | 2021-08-30 | 2022-06-08 | 2021-09-06 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | Out of Adjustment | Switch | Repair | 44858254 | T2DI WEST POINT-VLY SPGS 10/125 RPR SWTC | ICE
LC | 121492921 | 051/208 | T2 DI MIDWAY-WHIRLWIND 51/208 RPR OPGW | MIDWAY | ETL.6030.TOWR | 2021-06-08 | 2021-06-08 | 2021-07-09 | 2022-06-08 | 2021-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44858346 | T2 DI MIDWAY-WHIRLWIND 51/208 RPR OPGW | ICW
LC | 121493141 | 046/355 | T2 DI RND MTN CTTNWD 046/355 RPR SHLW | TABLEMTN | ETL.5640.TOWR | 2021-06-08 | 2021-06-02 | 2021-06-23 | 2022-06-02 | 2021-09-02 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44857030 | T2 DI RND MTN CTTNWD 046/355 RPR SHLW | ICW
LC | 121493336 | 010/043 | T2 DI TESLA-METCALF 010/043 RPR SHLS | METCALF | ETL.6110.TOWR | 2021-06-08 | 2021-06-01 | 2021-06-18 | 2022-06-01 | 2021-09-01 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44873535 | T2 DI TESLA-METCALF 010/043 RPR SHLS | ICS
LC | 121493392 | 006/055AB | T2 DI PRDS-TBL MTN 006/055AB RPL STRW | TABLEMTN | ETL.4316.POLE.WDPS | 2021-06-08 | 2021-06-01 | 2021-07-24 | 2022-06-01 | 2021-09-01 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543429 | T2 DI PRDS-TBL MTN 006/055AB RPL STRW | 70Y
LC | 121493763 | 026/229 | T2 DI RND MTN-CTTNWOOD#2 26/229 RPR SHLS | TABLEMTN | ETL.5640.TOWR | 2021-06-08 | 2021-06-02 | 2021-06-19 | 2022-06-02 | 2021-09-02 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44857029 | T2 DI RND MTN-CTTNWOOD#2 26/229 RPR SHLS | ICS
LC | 121494519 | 010/129 | T2 DI W. PNT-VLY SPRNGS 10/129 COTTER | VICTOR | ETL.8350.INSL.NCER | 2021-06-09 | 2021-06-08 | 2021-08-31 | 2022-06-08 | 2021-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44858256 | T2 DI W. PNT-VLY SPRNGS 10/129 COTTER | ICW
LC | 121494543 | 010/360 | T2 DI SPAULDING-SUMMIT 10/360 RPR INSW | SACTO | ETL.8060.INSL.CERA | 2021-06-09 | 2021-06-08 | 2021-08-14 | 2022-06-08 | 2021-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876215 | T2 DI SPAULDING-SUMMIT 10/360 RPR INSW | ICW
LC | 121494546 | 009/103 | T2 DI DRUM-SUMMIT #2 9/103 RPR INSS | SACTO | ETL.1450.INSL | 2021-06-09 | 2021-06-08 | 2021-08-27 | 2022-06-08 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44876342 | T2 DI DRUM-SUMMIT #2 9/103 RPR INSS | ICS
LC | 121494893 | 006/047 | T2 DI COTTONWOOD-DELEVN #1 6/47 RPR SHLS | TABLEMTN | ETL.4550.TOWR | 2021-06-09 | 2021-06-08 | 2021-07-18 | 2022-06-08 | 2021-09-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44857011 | T2 DI COTTONWOOD-DELEVN #1 6/47 RPR SHLS | ICS
LC | 121494955 | 029/006 | T2 DI MNDCN-WLTS-FRT BRG 29/6 RPR GYWW | LAKEVLLE | ETL.7550.POLE.WOOD | 2021-06-09 | 2021-06-07 | 2021-08-27 | 2022-06-07 | 2021-09-05 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44856530 | T2 DI MNDCN-WLTS-FRT BRG 29/6 RPR GYWW | ICW
LC | 121495301 | 006/106 | T2 DI PT #1-HT CRK #2-BRNY 6/106 RPR INS | TABLEMTN | ETL.7040.INSL.NCER | 2021-06-09 | 2021-06-08 | 2021-06-24 | 2022-06-08 | 2021-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44857015 | T2 DI PT #1-HT CRK #2-BRNY 6/106 RPR INS | ICW
LC | 121495416 | 033/237 | T2 DI CARIBOU-TABLE MTN 33/237 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-09 | 2021-06-08 | 2022-06-20 | 2022-06-08 | 2022-06-08 | Late | 532 | Upgraded | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121495719 | 003/131 | T2 DI SPAULDING-SUMMIT 3/131 RPR INSS | SACTO | ETL.8060.INSL.NCER | 2021-06-09 | 2021-06-08 | 2021-08-01 | 2022-06-08 | 2021-09-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44876214 | T2 DI SPAULDING-SUMMIT 3/131 RPR INSS | ICS
LC | 121495762 | 013/162 | T2 DI WST PNT-VLLY SPRNGS 13/162 RPR GYW | VICTOR | ETL.8350.POLE.NWOD | 2021-06-09 | 2021-06-08 | 2021-07-06 | 2022-06-08 | 2021-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44858257 | T2 DI WST PNT-VLLY SPRNGS 13/162 RPR GYW | ICW
LC | 121495766 | 024/285 | T2 DI DRUM-SUMMIT #1 24/285 RPR INSW | SACTO | ETL.1440.INSL | 2021-06-09 | 2021-06-08 | 2021-06-22 | 2022-06-08 | 2021-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876341 | T2 DI DRUM-SUMMIT #1 24/285 RPR INSW | ICW
LC | 121495877 | 015/478 | T2 DI SPAULDING-SUMMIT 15/478 REFRAME | SACTO | ETL.8060.INSL.CERA | 2021-06-09 | 2021-06-08 | 2021-07-28 | 2022-06-08 | 2021-09-06 | On-time | 637 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31543640 | T2 DI SPAULDING-SUMMIT 15/478 REFRAME | 93E
LC | 121495978 | 010/164 | T2 DI TEJON-LEBEC 10/164 COTTER | MIDWAY | ETL.9250.INSL.NCER | 2021-06-09 | 2021-06-08 | 2021-08-09 | 2022-06-08 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44874098 | T2 DI TEJON-LEBEC 10/164 COTTER | ICW
LC | 121496054 | 024/289 | T2 DI DRUM-SUMMIT #1 024/289 RPR INSW | SACTO | ETL.1440.INSL | 2021-06-09 | 2021-06-08 | 2021-06-22 | 2022-06-08 | 2021-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876340 | T2 DI DRUM-SUMMIT #1 024/289 RPR INSW | ICW
LC | 121496058 | 000/005 | T2 DI SPAULDING-SUMMIT 000/005 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-06-09 | 2021-06-08 | 2021-08-13 | 2022-06-08 | 2021-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44876213 | T2 DI SPAULDING-SUMMIT 000/005 RPR GYWW | ICW
LC | 121496260 | 099/005 | T2 DI HUMBOLDT-TRINITY 99/5 RPR INSW | EUREKA | ETL.1820.INSL.CERA | 2021-06-09 | 2021-06-08 | 2021-06-14 | 2022-06-08 | 2021-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44856347 | T2 DI HUMBOLDT-TRINITY 99/5 RPR INSW | ICW
LC | 121496265 | 110/003 | T2 DI HUMBLDT-BRIDGVILLE 110/3 RPR ADSS | EUREKA | ETL.1810.POLE.STPS | 2021-06-09 | 2021-06-08 | 2021-06-14 | 2022-06-08 | 2021-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44854457 | T2 DI HUMBLDT-BRIDGVILLE 110/3 RPR ADSS | ICW
LC | 121496268 | 109/008 | T2 DI HUMBLDT-BRIDGVILLE 109/8 RPR SHLW | EUREKA | ETL.1810.POLE.STPS | 2021-06-09 | 2021-06-08 | 2021-07-06 | 2022-06-08 | 2021-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44854459 | T2 DI HUMBLDT-BRIDGVILLE 109/8 RPR SHLW | ICW
LC | 121496446 | 021/247 | T2 DI DRUM-SUMMIT #1 021/247 RPR INSW | SACTO | ETL.1440.INSL.CERA | 2021-06-09 | 2021-06-08 | 2021-06-23 | 2022-06-08 | 2021-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876212 | T2 DI DRUM-SUMMIT #1 021/247 RPR INSW | ICW
LC | 121496453 | 023/275 | T2 DI DRUM-SUMMIT #1 23/275 RPR INSW | SACTO | ETL.1440.INSL | 2021-06-09 | 2021-06-08 | 2021-06-22 | 2022-06-08 | 2021-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876298 | T2 DI DRUM-SUMMIT #1 23/275 RPR INSW | ICW
LC | 121496568 | 018/003 | T2 CLEAR LAKE-KONOCTI 18/003 COTTER | LAKEVLLE | ETL.6852.INSL.NCER | 2021-06-09 | 2021-06-09 | 2021-06-24 | 2022-06-09 | 2021-09-09 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 44871744 | T2 CLEAR LAKE-KONOCTI 18/003 COTTER | ICW
LC | 121497070 | 010/044 | T2 DI EGL RK-FLTN-SLVRDO 10/044 RPR INSS | LAKEVLLE | ETL.4392.INSL.CERA | 2021-06-09 | 2021-06-08 | 2021-08-17 | 2022-06-08 | 2021-09-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44856525 | T2 DI EGL RK-FLTN-SLVRDO 10/044 RPR INSS | ICS
LC | 121497199 | 008/097 | T2 DI DRUM-SUMMIT #1 008/097 RPL INSW | SACTO | ETL.1440.INSL | 2021-06-09 | 2021-06-08 | 2021-06-23 | 2022-06-08 | 2021-09-06 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545067 | T2 DI DRUM-SUMMIT #1 008/097 RPL INSW | 93I
LC | 121497270 | 013/100 | T2 DI CRBU-TBL MTN 013/100 RPR INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-09 | 2021-06-08 | 2021-06-28 | 2022-06-08 | 2021-09-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44857013 | T2 DI CRBU-TBL MTN 013/100 RPR INSS | ICS
LC | 121497339 | 110/008 | T2 DI HUMBOLDT-BRDGVLLE 110/008 RPR INSW | EUREKA | ETL.1810.INSL.CERA | 2021-06-09 | 2021-06-09 | 2021-06-15 | 2022-06-09 | 2021-09-09 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44856342 | T2 DI HUMBOLDT-BRDGVLLE 110/008 RPR INSW | ICW
LC | 121497466 | 001/073 | T2 DI SPAULDING-SUMMIT 1/73 RPR INSW | SACTO | ETL.8060.INSL.NCER | 2021-06-09 | 2021-06-08 | 2021-08-19 | 2022-06-08 | 2021-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876209 | T2 DI SPAULDING-SUMMIT 1/73 RPR INSW | ICW
LC | 121497508 | 023/171 | T2 DI CARIBOU-TABLE MTN 023/171 RPR INSS | TABLEMTN | ETL.4440.INSL | 2021-06-09 | 2021-06-08 | 2021-08-04 | 2022-06-08 | 2021-09-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44857014 | T2 DI CARIBOU-TABLE MTN 023/171 RPR INSS | ICS
LC | 121497768 | 034/249 | T2 DI CARIBOU-TABLE MTN 034/249 RPR INSS | TABLEMTN | ETL.4440.INSL | 2021-06-09 | 2021-06-08 | 2021-07-06 | 2022-06-08 | 2021-09-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44857012 | T2 DI CARIBOU-TABLE MTN 034/249 RPR INSS | ICS
LC | 121498133 | 088/003 | T2 DI HUMBOLDT-TRINITY 88/3 GYWW COTTER | EUREKA | ETL.1820.POLE.WDPS | 2021-06-09 | 2021-06-09 | 2021-07-31 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44856346 | T2 DI HUMBOLDT-TRINITY 88/3 RPR GYWW | ICW
LC | 121498221 | 028/333 | T2 DI DRUM-SUMMIT #2 028/333 COTTER | SACTO | ETL.1450.INSL.NCER | 2021-06-09 | 2021-06-08 | 2021-08-04 | 2022-06-08 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876208 | T2 DI DRUM-SUMMIT #2 028/333 COTTER | ICW
LC | 121498223 | 012/143 | T2 DI DRUM-SUMMIT #2 12/143L RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-09 | 2021-06-09 | 2022-07-30 | 2022-06-09 | 2022-06-09 | Late | 372 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Rotten | Structure-Wood | Replace | 31543771 | T3 DI DRUM-SUMMIT #2 0/5C RPL STRW | 70Y
LC | 121498226 | 012/143 | T2 DI DRUM-SUMMIT #2 12/143R RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-06-09 | 2021-06-09 | 2022-07-30 | 2022-06-09 | 2022-06-09 | Late | 372 | Upgraded | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | Rotten | Structure-Wood | Replace | 31543771 | T3 DI DRUM-SUMMIT #2 0/5C RPL STRW | 70Y
LC | 121498227 | 028/333 | T2 DI DRUM-SUMMIT #2 028/333 RPL GYWW | SACTO | ETL.1450.POLE.WDPS | 2021-06-09 | 2021-06-08 | 2021-08-04 | 2022-06-08 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 44876207 | T2 DI DRUM-SUMMIT #2 028/333 RPL GYWW | ICW
LC | 121500297 | 003/020 | T2 DI MOSS LNDNG-MTCLF 3/20 RPL HRDT | MOSSLNDG | ETL.6050.TOWR | 2021-06-09 | 2021-06-02 | 2022-07-13 | 2022-06-02 | 2022-06-02 | Late | 543 | Upgraded | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45149017 | T2 DI MOSS LNDNG-MTCLF 3/20 RPL HRDT | ICQ
LC | 121510612 | 041/269 | T2 DI TRINITY-COTTONWD 41/269 RPR GYWW | TABLEMTN | ETL.4040.POLE.WDPS | 2021-06-10 | 2021-06-09 | 2021-07-20 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44857027 | T2 DI TRINITY-COTTONWD 41/269 RPR GYWW | ICW
LC | 121510766 | 001/000 | T2 DI CARIBOU #2 001/000 GYWW COTTER | TABLEMTN | ETL.6280.POLE.WOOD | 2021-06-10 | 2021-06-08 | 2021-06-28 | 2022-06-08 | 2021-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44857019 | T2 DI CARIBOU #2 001/000 GYWW COTTER | ICW
LC | 121510992 | 015/128 | T2 DI CRAG VIEW-CASCADE 15/128 RPR OPGW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-10 | 2021-06-09 | 2021-07-30 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44857023 | T2 DI CRAG VIEW-CASCADE 15/128 RPR OPGW | ICW
LC | 121511221 | 009/084 | T2 DI CRAG VIEW-CASCADE 9/84 RPR OPGW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-10 | 2021-06-09 | 2021-06-16 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44857020 | T2 DI CRAG VIEW-CASCADE 9/84 RPR OPGW | ICW
LC | 121511504 | 006/055AB | T2 EI PARADISE-TABLE MTN 6/55AB RPL STRW | TABLEMTN | ETL.4316.POLE.WDPS | 2021-06-10 | 2021-06-10 | 2021-07-24 | 2022-06-10 | 2021-09-08 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31543429 | T2 DI PRDS-TBL MTN 006/055AB RPL STRW | 70Y
LC | 121511541 | 010/090 | T2 DI CRAG VIEW-CASCADE 10/90 RPR SHLW | TABLEMTN | ETL.1350.POLE.STPS | 2021-06-10 | 2021-06-09 | 2021-06-16 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44857021 | T2 DI CRAG VIEW-CASCADE 10/90 RPR SHLW | ICW
LC | 121512028 | 110/001 | T2 DI HUMBOLDT-BRIDGEVL 110/1 RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-06-10 | 2021-06-09 | 2022-09-08 | 2022-06-09 | 2022-06-09 | Late | 372 | Upgraded | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31541449 | EI HUMBOLDT-BRIDGEVLLE 107/003 RPLC STRW | 70Y
LC | 121512029 | 110/001 | T2 DI HUMBOLDT-BRIDGEVILL 110/1 RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-06-10 | 2021-06-09 | 2022-09-08 | 2022-06-09 | 2022-06-09 | Late | 372 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31541449 | EI HUMBOLDT-BRIDGEVLLE 107/003 RPLC STRW | 70Y
LC | 121512073 | 110/001 | T2 DI HUMBOLDT-BRIDGEVILL 110/1 RPR INSW | EUREKA | ETL.1810.INSL.NCER | 2021-06-10 | 2021-06-09 | 2021-07-06 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44857250 | T2 DI HUMBOLDT-BRIDGEVILL 110/1 RPR INSW | ICW
LC | 121512080 | 008/074 | T2 DI CRAG VIEW-CASCADE 8/74R RPL POLE | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-10 | 2021-06-09 | 2021-07-29 | 2022-06-09 | 2021-09-07 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543356 | T2 DI CRAG VIEW-CASCADE 8/74L RPL POLE | 70Y
LC | 121512083 | 008/074 | T2 DI CRAG VIEW-CASCADE 8/74L RPL POLE | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-10 | 2021-06-09 | 2021-07-29 | 2022-06-09 | 2021-09-07 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543356 | T2 DI CRAG VIEW-CASCADE 8/74L RPL POLE | 70Y
LC | 121512428 | 018/154 | T2 DI CRAG VIEW-CASCADE 18/154 RPR OPGW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-10 | 2021-06-09 | 2021-07-30 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44857024 | T2 DI CRAG VIEW-CASCADE 18/154 RPR OPGW | ICW
LC | 121512552 | 005/121 | T2 DI HMLTN BRNCH-CHSTR 5/121 RPR JUMW | TABLEMTN | ETL.7000.INSL.NCER | 2021-06-10 | 2021-06-09 | 2021-06-23 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Jumper-Wood | Repair | 44857018 | T2 DI HMLTN BRNCH-CHSTR 5/121 RPR JUMW | ICW
LC | 121512652 | 090/006 | T2 DI HUMBOLDT-TRINITY 90/6 RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2021-06-10 | 2021-06-09 | 2021-07-31 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44857253 | T2 DI HUMBOLDT-TRINITY 90/6 RPR INSW | ICW
LC | 121512992 | 006/012 | T2 DI CARIBOU-PLUMAS JCT 6/12 RPR INSW | TABLEMTN | ETL.6290.INSL.CERA | 2021-06-10 | 2021-06-09 | 2021-06-25 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44857016 | T2 DI CARIBOU-PLUMAS JCT 6/12 RPR INSW | ICW
LC | 121513292 | 007/060 | T2 DI TRINITY-COTTONWOOD 7/60 RPL DAMW | TABLEMTN | ETL.4040.INSL.CERA | 2021-06-10 | 2021-06-09 | 2021-06-24 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Damper-Wood | Replace | 44857026 | T2 DI TRINITY-COTTONWOOD 7/60 RPL DAMW | ICW
LC | 121513520 | 015/127 | T2 DI CRAG VIEW-CASCADE 015/127 RPR INSW | TABLEMTN | ETL.1350.INSL.CERA | 2021-06-10 | 2021-06-09 | 2021-08-04 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44857022 | T2 DI CRAG VIEW-CASCADE 015/127 RPR INSW | ICW
LC | 121513592 | 018/413 | T2 DI DRUM-GRSS VLLY-WMR 18/413 RPR INSW | SACTO | ETL.6760.INSL.NCER | 2021-06-10 | 2021-06-09 | 2021-08-06 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876297 | T2 DI DRUM-GRSS VLLY-WMR 18/413 RPR INSW | ICW
LC | 121513746 | 009/044 | T2 EI SILVERADO-FULTON JCT 9/44 RPR INSS | LAKEVLLE | ETL.1610.INSL | 2021-06-10 | 2021-06-10 | 2021-08-19 | 2022-06-10 | 2021-09-10 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44856722 | T2 EI SILVERADO-FULTON JCT 9/44 RPR INSS | ICS
LC | 121513918 | 013/252 | T2 DI COLGATE-PALERMO 013/252 RPR GYWW | TABLEMTN | ETL.6500.POLE.NWOD | 2021-06-10 | 2021-06-09 | 2021-08-14 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44898453 | T2 DI COLGATE-PALERMO 013/252 RPR GYWW | ICW
LC | 121514190 | 001/039 | T2 DI COTTONWD-BNTN #1 1/39 RPL INSW | TABLEMTN | ETL.6640.INSL | 2021-06-10 | 2021-06-09 | 2021-07-22 | 2022-06-09 | 2021-09-07 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543641 | T2 DI COTTONWD-BNTN #1 1/39 RPL INSW | 93I
LC | 121514250 | 010/004 | T2 DI FULTON-HOPLAND 10/4 RPR INSW | LAKEVLLE | ETL.6890.INSL.NCER | 2021-06-10 | 2021-06-09 | 2021-07-27 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44856528 | T2 DI FULTON-HOPLAND 10/4 RPR INSW | ICW
LC | 121514476 | 065/003 | T2 DI HUMBOLDT-TRINITY 65/3 RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2021-06-10 | 2021-06-10 | 2021-06-28 | 2022-06-10 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44857254 | T2 DI HUMBOLDT-TRINITY 65/3 RPR INSW | ICW
LC | 121514567 | 008/096 | T2 DI DRUM-SUMMIT #1 8/96 RPR INSW | SACTO | ETL.1440.INSL | 2021-06-10 | 2021-06-09 | 2021-06-23 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876205 | T2 DI DRUM-SUMMIT #1 8/96 RPR INSW | ICW
LC | 121514623 | 105/002 | T2 DI HUMBOLDT-TRINITY 105/002 RPR INSW | EUREKA | ETL.1820.INSL.CERA | 2021-06-10 | 2021-06-10 | 2021-06-21 | 2022-06-10 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44857252 | T2 DI HUMBOLDT-TRINITY 105/002 RPR INSW | ICW
LC | 121514704 | 022/105 | T2 DI SILVERADO-FULTON 022/105 RPL INSS | LAKEVLLE | ETL.1610.INSL.CERA | 2021-06-10 | 2021-06-10 | 2021-12-03 | 2022-06-10 | 2021-09-08 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551235 | T2 DI SILVERADO-FULTON 022/105 RPL INSS | 93K
LC | 121514821 | 024/216 | T2 DI RND MTN-CTTNWD #2 024/216 RPR OPGW | TABLEMTN | ETL.5640.TOWR | 2021-06-10 | 2021-06-02 | 2021-06-19 | 2022-06-02 | 2021-09-02 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44873521 | T2 DI RND MTN-CTTNWD #2 024/216 RPR OPGW | ICS
LC | 121516117 | :001/003 | T2 DI FULTON-PUEBLO :1/3 RPR INSW | LAKEVLLE | ETL.1600.INSL.NCER | 2021-06-10 | 2021-06-10 | 2021-08-31 | 2022-06-10 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44856538 | T2 DI FULTON-PUEBLO :1/3 RPR INSW | ICW
LC | 121516203 | 066/001X | T2 DI HMBLDT-TRNTY 66/1X RPR INSW | EUREKA | ETL.1820.INSL.CERA | 2021-06-10 | 2021-06-10 | 2021-06-28 | 2022-06-10 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44857251 | T2 DI HMBLDT-TRNTY 66/1X RPR INSW | ICW
LC | 121516205 | 056/000 | T2 DI HMBLDT-TRNTY 056/000 RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2021-06-10 | 2021-06-10 | 2021-07-31 | 2022-06-10 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44857255 | T2 DI HMBLDT-TRNTY 056/000 RPR INSW | ICW
LC | 121516207 | 022/442 | T2 DI COLGATE-PALERMO 022/442 RPR INSW | TABLEMTN | ETL.6500.INSL.CERA | 2021-06-10 | 2021-06-09 | 2021-07-06 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44893146 | T2 DI COLGATE-PALERMO 022/442 RPR INSW | ICW
LC | 121517142 | 008/067 | T2 DI CRAG VIEW-CASCADE 8/67R RPR OPGW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-10 | 2021-06-04 | 2021-07-21 | 2022-06-04 | 2021-09-04 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44873808 | T2 DI CRAG VIEW-CASCADE 8/67R RPR OPGW | ICW
LC | 121518232 | 002/025 | T2 DI BRIDGEVILLE-COTTONWD 2/25 RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2021-06-29 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44873805 | T2 DI BRIDGEVILLE-COTTONWD 2/25 RPR ADSS | ICW
LC | 121518234 | 031/010 | T2 DI FULTON-HOPLAND 031/010 INS COTR KY | LAKEVLLE | ETL.6890.INSL | 2021-06-11 | 2021-06-09 | 2021-06-29 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44858886 | T2 DI FULTON-HOPLAND 031/010 INS COTR KY | ICW
LC | 121518323 | 027/195 | T2 DI CARIBOU-TBL MTN 27/195 RPL DAMS | TABLEMTN | ETL.4440.INSL | 2021-06-11 | 2021-06-10 | 2021-08-03 | 2022-06-10 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 44860057 | T2 DI CARIBOU-TBL MTN 27/195 RPL DAMS | ICS
LC | 121518374 | 000/001 | T2 DI LAYTONVILLE-COVELO 00/01 COTR KEY | LAKEVLLE | ETL.7390.INSL.NCER | 2021-06-11 | 2021-06-10 | 2021-06-18 | 2022-06-10 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44858893 | T2 DI LAYTONVILLE-COVELO 00/01 COTR KEY | ICS
LC | 121518378 | 042/354 | T2 DI PIT #1-COTNWD 42/354 RPR INSS | TABLEMTN | ETL.5390.TOWR | 2021-06-11 | 2021-06-10 | 2021-08-27 | 2022-06-10 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Repair | 44874008 | T2 DI PIT #1-COTNWD 42/354 RPR INSS | ICS
LC | 121518580 | 024/112 | T2 DI SILVERADO-FULTON 24/112 RPR JUMP | LAKEVLLE | ETL.1610.INSL.CERA | 2021-06-11 | 2021-06-10 | 2021-08-27 | 2022-06-10 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Jumper-Steel | Repair | 44858889 | T2 DI SILVERADO-FULTON 24/112 RPR JUMP | ICS
LC | 121518582 | 020/010 | T2 DI MENDO-WILTS-FRT BRG 20/10 RPR INSW | LAKEVLLE | ETL.7550.INSL.CERA | 2021-06-11 | 2021-06-10 | 2021-07-21 | 2022-06-10 | 2021-09-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44858894 | T2 DI MENDO-WILTS-FRT BRG 20/10 RPR INSW | ICW
LC | 121518985 | 011/074 | T2 DI COTTNWD-DELVN #1 11/74 RPR SHLS | TABLEMTN | ETL.4550.TOWR | 2021-06-11 | 2021-06-10 | 2021-07-24 | 2022-06-10 | 2021-09-10 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44897784 | T2 DI COTTNWD-DELVN #1 11/74 RPR SHLS | ICS
LC | 121518986 | 109/000 | T2 DI HUMBOLDT-BRIDGEVILLE 109/0 RPR GYW | EUREKA | ETL.1810.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2021-07-07 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44858730 | T2 DI HUMBOLDT-BRIDGEVILLE 109/0 RPR GYW | ICW
LC | 121518989 | 011/074 | T2 DI COTNWD-LGAN CRK 11/74 COTTER | TABLEMTN | ETL.4570.INSL | 2021-06-11 | 2021-06-10 | 2021-08-07 | 2022-06-10 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44872169 | T2 DI COTNWD-LGAN CRK 11/74 COTTER | ICS
LC | 121519113 | 024/215 | T2 DI RND MTN-COTTNWD#2 24/215 RPR SHLS | TABLEMTN | ETL.5640.TOWR | 2021-06-11 | 2021-06-10 | 2021-06-23 | 2022-06-10 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44871876 | T2 DI RND MTN-COTTNWD#2 24/215 RPR SHLS | ICW
LC | 121519141 | 109/000 | T2 DI HMBOLDT-BRIDGEVILLE 109/0 RPR ADSS | EUREKA | ETL.1810.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2021-07-07 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44858731 | T2 DI HMBOLDT-BRIDGEVILLE 109/0 RPR ADSS | ICW
LC | 121519401 | 027/194 | T2 DI CARIBOU-TBL MTN 27/194 BRKN STEEL | TABLEMTN | ETL.4440.TOWR | 2021-06-11 | 2021-06-10 | 2021-06-22 | 2022-06-10 | 2021-09-08 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Structure-Tower | Repair | 44860058 | T2 DI CARIBOU-TBL MTN 27/194 BRKN STEEL | ICQ
LC | 121519408 | 040/344 | T2 DI RND MTN-CTTNWD #3 40/344 RPR INSS | TABLEMTN | ETL.5650.INSL | 2021-06-11 | 2021-06-10 | 2021-06-30 | 2022-06-10 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44874015 | T2 DI PIT #1-COTTNWD 40/344 RPR INSS | ICS
LC | 121519616 | 041/353 | T2 DI PIT #1-COTTNWOOD 41/353 RPR COTTER | TABLEMTN | ETL.5390.INSL.NCER | 2021-06-11 | 2021-06-10 | 2021-08-27 | 2022-06-10 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 44873998 | T2 DI PIT #1-COTTNWOOD 41/353 RPR COTTER | ICS
LC | 121519619 | 058/526 | T2 DI RND MTN-CTNWD #3 58/526 COTTER | TABLEMTN | ETL.5650.INSL | 2021-06-11 | 2021-06-10 | 2021-06-30 | 2022-06-10 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44872163 | T2 DI RND MTN-CTNWD #3 58/526 COTTER | ICS
LC | 121519758 | 034/003 | T2 DI MNDO-WLTS-FRT BRG 34/03 COTTER KEY | LAKEVLLE | ETL.7550.INSL.CERA | 2021-06-11 | 2021-06-10 | 2021-08-27 | 2022-06-10 | 2021-09-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44858888 | T2 DI MNDO-WLTS-FRT BRG 34/03 COTTER KEY | ICW
LC | 121519971 | 047/407 | T2 DI RND MTN-CTNWD #3 47/407 RPL INSS | TABLEMTN | ETL.5650.INSL | 2021-06-11 | 2021-06-10 | 2021-07-06 | 2022-06-10 | 2021-09-08 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31543652 | T2 DI RND MTN-CTNWD #3 47/407 RPL INSS | 93K
LC | 121520172 | 002/015 | T2 EI DVIDE-VANDENBERG #2 2/15R RPL INSW | PISMOBCH | ETL.8630.INSL.CERA | 2021-06-11 | 2021-06-11 | 2021-09-07 | 2022-06-11 | 2021-09-11 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543909 | T2 EI DVIDE-VANDENBERG #2 2/15R RPL INSW | 93I
LC | 121520395 | 008/154 | T2 DI COLGATE-PALERMO 8/154 RPR GYWW | SACTO | ETL.6500.POLE.NWOD | 2021-06-11 | 2021-06-09 | 2021-08-12 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44876296 | T2 DI COLGATE-PALERMO 8/154 RPR GYWW | ICW
LC | 121520706 | 027/332 | T2 DI DRUM-SUMMIT #2 27/332 SWTC RPR | SACTO | ETL.1450.TOWR | 2021-06-11 | 2021-06-10 | 2021-07-03 | 2022-06-10 | 2021-09-08 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | Out of Adjustment | Switch | Repair | 44876426 | T2 DI DRUM-SUMMIT #2 27/332 SWTC RPR | ICE
LC | 121520866 | 025/160 | T2 DI HELMS-GREGG #1 25/160 COTTER KEY | FRESNO | ETL.4870.INSL | 2021-06-11 | 2021-06-10 | 2021-06-17 | 2022-06-10 | 2021-09-10 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 44860868 | T2 DI HELMS-GREGG #1 25/160 COTTER KEY | ICS
LC | 121520876 | 025/160 | T2 DI HELMS-GREGG #2 25/160 COTTER KEY | FRESNO | ETL.4880.INSL | 2021-06-11 | 2021-06-10 | 2021-06-17 | 2022-06-10 | 2021-09-10 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44860869 | T2 DI HELMS-GREGG #2 25/160 COTTER KEY | ICS
LC | 121521251 | 026/314 | T2 DI DRUM-SUMMIT#1 26/314 RPL INSS | SACTO | ETL.1440.TOWR | 2021-06-11 | 2021-06-10 | 2021-08-01 | 2022-06-10 | 2021-09-08 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31543742 | T2 DI DRUM-SUMMIT#1 26/314 RPL INSS | 93K
LC | 121521430 | 071/002A | T2 DI HUMBOLDT-TRINITY 71/2A RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2021-06-16 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44858732 | DI HUMBOLDT-TRINITY 71/2A RPR GYWW | ICW
LC | 121521431 | 011/086A | T2 DI HELMS-GREGG #1 011/086A COTTER | FRESNO | ETL.4870.INSL | 2021-06-11 | 2021-06-10 | 2021-07-07 | 2022-06-10 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44875601 | T2 DI HELMS-GREGG #1 011/086A COTTER | ICS
LC | 121521770 | 053/475 | T2 DI RND MTN-CTTNWD #3 53/475 RPR STRT | TABLEMTN | ETL.5650.TOWR | 2021-06-11 | 2021-06-10 | 2021-07-06 | 2022-06-10 | 2021-09-08 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Structure-Tower | Repair | 44874017 | T2 DI RND MTN-CTTNWD #3 53/475 RPR STRT | ICQ
LC | 121521775 | 018/096 | T2 DI TESLA-NEWARK #1 018/096 RPR FOND | CONCORD | ETL.5720.TOWR | 2021-06-11 | 2021-06-11 | 2021-07-02 | 2022-06-11 | 2021-09-09 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 44875602 | T2 DI TESLA-NEWARK #1 018/096 RPR FOND | ICQ
LC | 121522120 | 001/008 | T2 DI PIT #3-PIT #1 1/8 RPR INSS | TABLEMTN | ETL.5400.INSL.NCER | 2021-06-11 | 2021-06-10 | 2021-06-26 | 2022-06-10 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44874010 | T2 DI PIT #3-PIT #1 1/8 RPR INSS | ICS
LC | 121522126 | R002/021 | T2 DI RND MTN-CTTNWD #3 R002/021 COTTER | TABLEMTN | ETL.5650.INSL | 2021-06-11 | 2021-06-11 | 2021-07-01 | 2022-06-11 | 2021-09-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44873524 | T2 DI RND MTN-CTTNWD #3 R002/021 COTTER | ICS
LC | 121522631 | 000/001 | T2 DI STAN-MEL SS-MAN 0/1 RPR INSS | VICTOR | ETL.3830.INSL | 2021-06-11 | 2021-06-11 | 2021-09-01 | 2022-06-11 | 2021-09-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44858919 | T2 DI STAN-MEL SS-MAN 0/1 RPR INSS | ICS
LC | 121522865 | 014/337 | T2 DI COTTONWD-BENTN #1 14/337 RPR INSW | TABLEMTN | ETL.6640.INSL | 2021-06-11 | 2021-06-09 | 2021-07-28 | 2022-06-09 | 2021-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44872162 | T2 DI COTTONWD-BENTN #1 14/337 RPR INSW | ICW
LC | 121522867 | 013/143 | T2 DI RND MTN-CTTNWD #2 013/143 RPR SHLS | TABLEMTN | ETL.5640.TOWR | 2021-06-11 | 2021-06-11 | 2021-06-17 | 2022-06-11 | 2021-09-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44871634 | T2 DI RND MTN-CTTNWD #2 013/143 RPR SHLS | ICS
LC | 121522893 | 030/004 | T2 DI TRNTY-MPL CRK 30/4 CTR KY | EUREKA | ETL.8170.INSL | 2021-06-11 | 2021-06-11 | 2021-08-23 | 2022-06-11 | 2021-09-11 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44858733 | T2 DI TRNTY-MPL CRK 30/4 CTR KY | ICW
LC | 121522985 | 046/357 | T2 DI RND MTN-COTNWD #2 46/357 RPR INSS | TABLEMTN | ETL.5640.INSL | 2021-06-11 | 2021-06-11 | 2021-06-30 | 2022-06-11 | 2021-09-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44872170 | T2 DI RND MTN-COTNWD #2 46/357 RPR INSS | ICS
LC | 121522988 | 029/209A | T2 DI CARIBOU-TBL MTN 29/209A RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2021-06-11 | 2021-06-11 | 2021-07-07 | 2022-06-11 | 2021-09-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Ground Wire-Steel | Repair | 44860059 | T2 DI CARIBOU-TBL MTN 29/209A RPR GYWS | ICS
LC | 121523104 | 007/033 | T2 DI PITTSBURG-TESLA #2 7/33 RPR INSS | CONCORD | ETL.5520.INSL.CERA | 2021-06-11 | 2021-06-11 | 2021-07-05 | 2022-06-11 | 2021-09-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44873538 | T2 DI PITTSBURG-TESLA #2 7/33 RPR INSS | ICS
LC | 121523142 | 030/261 | T2 DI ROUND MTN-CTNWD #2 30/261 RPR SHLS | TABLEMTN | ETL.5640.TOWR | 2021-06-11 | 2021-06-10 | 2021-06-30 | 2022-06-10 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44872173 | T2 DI ROUND MTN-CTNWD #2 30/261 RPR SHLS | ICS
LC | 121523146 | 041/268 | T2 DI TRINITY-COTTONWD 41/268 RPR SWTC | TABLEMTN | ETL.4040.SWIT | 2021-06-11 | 2021-06-11 | 2021-07-21 | 2022-06-11 | 2021-09-09 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Out of Adjustment | Switch | Repair | 44897756 | T2 DI TRINITY-COTTONWD 41/268 RPR SWTC | ICE
LC | 121523291 | 031/266 | T2 DI RND MTN-CTTNWD #2 031/266 RPR INSS | TABLEMTN | ETL.5640.INSL | 2021-06-11 | 2021-06-10 | 2021-06-23 | 2022-06-10 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44873525 | T2 DI RND MTN-CTTNWD #2 031/266 RPR INSS | ICS
LC | 121523293 | 031/210 | T2 DI POE-RIO OSO 31/210 RPL INSS | TABLEMTN | ETL.5540.INSL.CERA | 2021-06-11 | 2021-06-11 | 2021-06-19 | 2022-06-11 | 2021-09-09 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31543743 | T2 DI POE-RIO OSO RPL INSS IN 2 TWRS. | 93K
LC | 121523308 | 000/002 | T2 DI COLGATE-PALERMO 00/02 RPR INSW | SACTO | ETL.6500.POLE.NWOD | 2021-06-11 | 2021-06-10 | 2021-08-09 | 2022-06-10 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876293 | T2 DI COLGATE-PALERMO 00/02 RPR INSW | ICW
LC | 121523383 | 022/014 | T2 DI GRBRVIL-LAYTNVIL 22/14 RPR INSS | EUREKA | ETL.8365.INSL.NCER | 2021-06-11 | 2021-06-10 | 2021-06-18 | 2022-06-10 | 2021-09-10 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44858892 | T2 DI GRBRVIL-LAYTNVIL 22/14 RPR INSS | ICS
LC | 121523448 | 064/323 | T2 DI MALIN-ROUND MTN #2 64/323 COTTER | TABLEMTN | ETL.6020.TOWR | 2021-06-11 | 2021-06-11 | 2021-06-18 | 2022-06-11 | 2021-09-09 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44868889 | T2 DI MALIN-ROUND MTN #2 64/323 COTTER | ICW
LC | 121523468 | 010/093 | T2 DI CRG VW-CSCD 010/093 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-11 | 2021-06-09 | 2022-09-26 | 2022-06-09 | 2022-06-09 | Late | 372 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121523495 | 014/008 | T2 DI TRINITY-MAPLE CREEK 14/08 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-06-11 | 2021-06-11 | 2022-12-07 | 2022-06-11 | 2022-06-11 | Late | 372 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31619822 | T2 DI TRINITY-MAPLE CREEK 14/08 RPL STRW | 70Y
LC | 121523630 | 013/138 | T2 DI RND MTN CTTND #2 013/138 RPR OPGW | TABLEMTN | ETL.5640.POLE.STPS | 2021-06-11 | 2021-06-09 | 2021-07-01 | 2022-06-09 | 2021-09-09 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44896364 | T2 DI RND MTN CTTND #2 013/138 RPR OPGW | ICW
LC | 121523877 | 008/066 | T2 DI CRAG VIEW-CSAD 008/066L RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2021-07-29 | 2022-06-09 | 2021-09-09 | On-time | 372 | Upgraded | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543356 | T2 DI CRAG VIEW-CASCADE 8/74L RPL POLE | 70Y
LC | 121523878 | 008/066 | T2 DI CRAG VIEW-CSAD 008/066R RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2021-07-29 | 2022-06-09 | 2021-09-09 | On-time | 372 | Upgraded | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543356 | T2 DI CRAG VIEW-CASCADE 8/74L RPL POLE | 70Y
LC | 121523879 | 008/066 | T2 DI CRAG VIEW-CSAD 008/066C RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2021-07-29 | 2022-06-09 | 2021-09-09 | On-time | 372 | Upgraded | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543356 | T2 DI CRAG VIEW-CASCADE 8/74L RPL POLE | 70Y
LC | 121524013 | 014/006 | T2 DI TRINITY-MAPLE CREEK 14/6 RPR INSW | EUREKA | ETL.8170.INSL | 2021-06-12 | 2021-06-11 | 2021-08-24 | 2022-06-11 | 2021-09-11 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44858734 | T2 DI TRINITY-MAPLE CREEK 14/6 RPR INSW | ICW
LC | 121524022 | 041/345 | T2 DI RND MTN-CTTNWD #3 41/345 RPR INSS | TABLEMTN | ETL.5650.INSL.NCER | 2021-06-12 | 2021-06-11 | 2021-06-26 | 2022-06-11 | 2021-09-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44871879 | T2 DI RND MTN-CTTNWD #3 41/345 RPR INSS | ICS
LC | 121524041 | 002/021 | T2 DI COTTONWD-DELEVAN #1 2/21 RPR SHLS | TABLEMTN | ETL.4550.TOWR | 2021-06-12 | 2021-05-04 | 2021-07-18 | 2022-05-04 | 2021-08-04 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44873995 | T2 DI COTTONWD-DELEVAN #1 2/21 RPR SHLS | ICS
LC | 121524260 | 004/010 | T2 DI LAYTONVILLE-COVELO 4/10L RPR GYWW | LAKEVLLE | ETL.7390.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2021-06-18 | 2022-06-09 | 2021-09-09 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44858891 | T2 DI LAYTONVILLE-COVELO 4/10L RPR GYWW | ICW
LC | 121524511 | 025/181 | T2 DI CARIBOU-TABLE MTN 25/181 RPL INSS | TABLEMTN | ETL.4440.INSL | 2021-06-12 | 2021-06-11 | 2022-06-23 | 2022-06-11 | 2022-06-11 | Late | 532 | Upgraded | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121524741 | 017/145 | T2 DI CRAG VIEW-CASCADE 17/145 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-09-10 | 2022-06-09 | 2022-06-09 | Late | 372 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31552992 | T2 EI CRAG VIEW-CASCDE 18/154R RPL STRW | 70Y
LC | 121524743 | 017/145 | T2 DI CRAG VIEW-CASCADE 17/145 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 | 2022-09-10 | 2022-06-09 | 2022-06-09 | Late | 372 | Upgraded | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31552992 | T2 EI CRAG VIEW-CASCDE 18/154R RPL STRW | 70Y
LC | 121525028 | 060/301 | T2 DI MALIN-ROUND MTN #2 60/301 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-06-12 | 2021-06-11 | 2021-06-28 | 2022-06-11 | 2021-09-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44874019 | T2 DI MALIN-ROUND MTN #2 60/301 RPR OPGW | ICS
LC | 121525033 | 018/174 | T2 DI RND MTN-CTTONWD #2 18/174 RPR SHLS | TABLEMTN | ETL.5640.TOWR | 2021-06-12 | 2021-06-10 | 2021-07-01 | 2022-06-10 | 2021-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44871874 | T2 DI RND MTN-CTTONWD #2 18/174 RPR SHLS | ICS
LC | 121525166 | 063/314 | T2 DI MLN RND MTN #2 063/314 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-06-12 | 2021-06-11 | 2021-06-28 | 2022-06-11 | 2021-09-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44874060 | T2 DI MLN RND MTN #2 063/314 RPR OPGW | ICS
LC | 121525186 | 001/012 | EI T2 PIT #5 - RND MTN #1 1/12 RPL DAMW | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-12 | 2021-06-12 | 2021-06-19 | 2022-06-12 | 2021-09-12 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 44874011 | EI T2 PIT #5 - RND MTN #1 1/12 RPL DAMW | ICW
LC | 121525240 | 000/002 | T2 DI COLGATE-ALLEGHANY 0/2 INS COTR KEY | SACTO | ETL.6470.INSL.NCER | 2021-06-12 | 2021-06-10 | 2021-07-08 | 2022-06-10 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876204 | T2 DI COLGATE-ALLEGHANY 0/2 INS COTR KEY | ICW
LC | 121525264 | 010/070 | T2 DI CTTNWD DLVN #1 10/70 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-06-12 | 2021-06-11 | 2021-07-24 | 2022-06-11 | 2021-09-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44872167 | T2 DI CTTNWD DLVN #1 10/70 RPR OPGW | ICS
LC | 121525281 | 012/141A | T2 DI DRUM-SUMMIT #1 12/141A RPR GYWW | SACTO | ETL.1440.POLE.WOOD | 2021-06-12 | 2021-06-12 | 2021-08-22 | 2022-06-12 | 2021-09-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44876202 | T2 DI DRUM-SUMMIT #1 12/141A RPR GYWW | ICW
LC | 121525352 | 010/071 | T2 DI CTTNWD-DLVN #1 10/71 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-06-12 | 2021-06-11 | 2021-07-20 | 2022-06-11 | 2021-09-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44872174 | T2 DI CTTNWD-DLVN #1 10/71 RPR OPGW | ICS
LC | 121525538 | 001/018 | T2 DI BCK CRK-RCK CRK-CRST 1/18 RPR INSS | TABLEMTN | ETL.4430.INSL | 2021-06-12 | 2021-06-11 | 2021-06-30 | 2022-06-11 | 2021-09-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44859178 | T2 DI BCK CRK-RCK CRK-CRST 1/18 RPR INSS | ICS
LC | 121525605 | 009/102A | T2 DI DRUM-SUMMIT #2 9/102A COTR KEY | SACTO | ETL.1450.INSL.CERA | 2021-06-12 | 2021-06-12 | 2021-08-27 | 2022-06-12 | 2021-09-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44876292 | T2 DI DRUM-SUMMIT #2 0/12A COTR KEY | ICW
LC | 121525704 | 062/309 | T2 DI MALIN-ROUND MTN #2 62/309 COTTER | TABLEMTN | ETL.6020.INSL | 2021-06-12 | 2021-06-11 | 2021-07-15 | 2022-06-11 | 2021-09-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44874018 | T2 DI MALIN-ROUND MTN #2 62/309 COTTER | ICS
LC | 121525753 | 085/005 | T2 DI HUMBOLDT-TRINITY 85/5 COTR KEY | EUREKA | ETL.1820.INSL.NCER | 2021-06-12 | 2021-06-12 | 2021-07-31 | 2022-06-12 | 2021-09-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44858735 | T2 DI HUMBOLDT-TRINITY 85/5 COTR KEY | ICW
LC | 121525838 | 010/066 | T2 DI COTTONWD-DELEVAN #1 10/66 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-06-12 | 2021-06-11 | 2021-06-17 | 2022-06-11 | 2021-09-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44864325 | T2 DI COTTONWD-DELEVAN #1 10/66 RPR OPGW | ICS
LC | 121525941 | 007/081B | T2 DI DRUM-SUMMIT #2 7/81B RPR GYWW | SACTO | ETL.1450.POLE.WOOD | 2021-06-12 | 2021-06-12 | 2021-08-27 | 2022-06-12 | 2021-09-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44876291 | T2 DI DRUM-SUMMIT #2 7/81B RPR GYWW | ICW
LC | 121526004 | 014/007A | T2 DI CARIBOU-PLUMAS JCT 14/7A COTTER | TABLEMTN | ETL.6290.INSL.NCER | 2021-06-12 | 2021-06-10 | 2021-06-30 | 2022-06-10 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44860056 | T2 DI CARIBOU-PLUMAS JCT 14/7A COTTER | ICW
LC | 121526275 | 063/315 | T2 DI MALIN-ROUND MTN #2 63/315 COTTER | TABLEMTN | ETL.6020.TOWR | 2021-06-12 | 2021-06-11 | 2021-06-18 | 2022-06-11 | 2021-09-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 44868888 | T2 DI MALIN-ROUND MTN #2 63/315 COTTER | ICS
LC | 121526517 | 041/345 | T2 DI PIT #1-COTTONWOOD 41/345 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-06-12 | 2021-06-10 | 2021-08-27 | 2022-06-10 | 2021-09-08 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 44874009 | T2 DI PIT #1-COTTONWOOD 41/345 RPR STRT | ICQ
LC | 121526814 | 085/003 | T2 DI HUMBOLDT-TRINITY 85/3 COTR KEY | EUREKA | ETL.1820.INSL.NCER | 2021-06-12 | 2021-06-12 | 2021-07-31 | 2022-06-12 | 2021-09-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44858736 | T2 DI HUMBOLDT-TRINITY 85/3 COTR KEY | ICW
LC | 121527046 | 008/041 | T2 DI SILVERADO-FULTON JCT 8/41 RPR INSS | LAKEVLLE | ETL.1610.INSL | 2021-06-12 | 2021-06-12 | 2021-09-08 | 2022-06-12 | 2021-09-10 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Jumper-Steel | Repair | 44858890 | T2 DI SILVERADO-FULTON JCT 8/41 RPR INSS | ICS
LC | 121527143 | 012/251 | T2 DI CTTNWD-RED BLFF 12/251 RPR GYWW | TABLEMTN | ETL.6660.POLE.NWOD | 2021-06-12 | 2021-06-10 | 2021-07-23 | 2022-06-10 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44907369 | T2 DI CTTNWD-RED BLFF 12/251 RPR GYWW | ICW
LC | 121527846 | 010/130 | T2 DIVIDE-CABRILLO #1 10/130 RPL INSW | PISMOBCH | ETL.1380.POLE.WOOD | 2021-06-13 | 2021-06-13 | 2021-06-14 | 2022-06-13 | 2021-09-13 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 FRAR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543414 | T2 DIVIDE-CABRILLO #1 10/130 RPL INSW | 93I
LC | 121530618 | 037/246C | T2 DI TRINITY-COTTONWOOD 37/246C COTTER | TABLEMTN | ETL.4040.INSL.NCER | 2021-06-14 | 2021-06-12 | 2021-07-21 | 2022-06-12 | 2021-09-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44871871 | T2 DI TRINITY-COTTONWOOD 37/246C COTTER | ICW
LC | 121530854 | 016/001 | T2 DI TRINITY-MAPLE CRK 16/1 RPL INSW | EUREKA | ETL.8170.INSL | 2021-06-14 | 2021-06-13 | 2021-09-12 | 2022-06-13 | 2021-09-13 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31549711 | T2 TRINITY-MAPLE CREEK 16/0 RPL INSW | 93I
LC | 121530857 | 039/255A | T2 DI TRINITY-COTTONWOOD 039/255A COTTER | TABLEMTN | ETL.4040.POLE.NWOD | 2021-06-14 | 2021-06-13 | 2021-07-20 | 2022-06-13 | 2021-09-13 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44872161 | T2 DI TRINITY-COTTONWOOD 039/255A COTTER | ICW
LC | 121530984 | 036/240A | T2 DI TRINITY-COTTONWOOD 036/240A COTTER | TABLEMTN | ETL.4040.INSL.NCER | 2021-06-14 | 2021-06-12 | 2021-07-29 | 2022-06-12 | 2021-09-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44871872 | T2 DI TRINITY-COTTONWOOD 036/240A COTTER | ICW
LC | 121531087 | 021/005 | T2 DI KONOCTI-MIDDLETOWN 21/5 RPL INSW | LAKEVLLE | ETL.6380.INSL.NCER | 2021-06-14 | 2021-06-12 | 2021-07-06 | 2022-06-12 | 2021-09-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44877400 | T2 DI KONOCTI-MIDDLETOWN 21/5 RPL INSW | ICW
LC | 121531184 | 024/291B | T2 DI DRUM-SUMMIT #2 24/291B GYWW COTTER | SACTO | ETL.1450.POLE.WOOD | 2021-06-14 | 2021-06-12 | 2021-08-27 | 2022-06-12 | 2021-09-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44876290 | T2 DI DRUM-SUMMIT #2 24/291B GYWW COTTER | ICW
LC | 121531186 | 023/170C | T2 DI TRINITY-CTNWD 23/170C COTTER | TABLEMTN | ETL.4040.INSL.CERA | 2021-06-14 | 2021-06-12 | 2021-06-24 | 2022-06-12 | 2021-09-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44872171 | T2 DI TRINITY-CTNWD 23/170C COTTER | ICW
LC | 121531302 | 051/001A | T2 DI HUMBOLDT-TRINITY 51/1A COTTER | EUREKA | ETL.1820.INSL.CERA | 2021-06-14 | 2021-06-12 | 2021-07-31 | 2022-06-12 | 2021-09-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44859998 | T2 DI HUMBOLDT-TRINITY 51/1A COTTER | ICW
LC | 121531384 | 050/003 | T2 DI HUMBOLDT-TRINITY 50/3 COTTER | EUREKA | ETL.1820.INSL.NCER | 2021-06-14 | 2021-06-12 | 2021-07-31 | 2022-06-12 | 2021-09-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44859996 | T2 DI HUMBOLDT-TRINITY 50/3 COTTER | ICW
LC | 121531511 | 001/011C | T2 DI KANAKA TAP 001/011C COTTER | TABLEMTN | ETL.4223.POLE.WOOD | 2021-06-14 | 2021-06-13 | 2021-07-01 | 2022-06-13 | 2021-09-13 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44860184 | DI KANAKA TAP 001/011C COTTER | ICW
LC | 121531535 | 085/004 | T2 DI HUMBOLDT-TRINITY 85/4B COTTER | EUREKA | ETL.1820.INSL.NCER | 2021-06-14 | 2021-06-12 | 2021-07-31 | 2022-06-12 | 2021-09-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44859994 | T2 DI HUMBOLDT-TRINITY 85/4B COTTER | ICW
LC | 121531670 | 005/043 | T2 DI ROCK CREEK-POE 5/43 RPL INSS | TABLEMTN | ETL.5630.INSL | 2021-06-14 | 2021-06-13 | 2021-08-10 | 2022-06-13 | 2021-09-13 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31543651 | T2 DI ROCK CREEK-POE 5/43 RPL INSS | 93K
LC | 121532465 | 010/068 | T2 DI CTNWD-DLVN #1 10/68 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-06-14 | 2021-06-11 | 2021-07-20 | 2022-06-11 | 2021-09-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44864326 | T2 DI CTNWD-DLVN #1 10/68 RPR OPGW | ICS
LC | 121532793 | 009/062 | T2 DI CTNWD-DLVN #1 9/62 RPR OPGW | TABLEMTN | ETL.4550.TOWR | 2021-06-14 | 2021-06-11 | 2021-07-25 | 2022-06-11 | 2021-09-11 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44864324 | T2 DI CTNWD-DLVN #1 9/62 RPR OPGW | ICS
LC | 121533511 | 000/005 | T2 JEFFERSON-HILLSDALE JCT 0/5 DUP CNCL | METCALF | ETL.7190.TOWR | 2021-06-14 | 2021-06-14 | 2021-06-15 | 2022-06-14 | 2021-09-14 | On-time | 543 | Upgraded | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 121536164 | 041/352 | T2 DI PIT#1-COTTNWOOD 41/352 RPR GYWS | TABLEMTN | ETL.5390.TOWR | 2021-06-14 | 2021-06-10 | 2021-08-27 | 2022-06-10 | 2021-09-10 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 44897800 | T2 DI PIT#1-COTTNWOOD 41/352 RPR GYWS | ICS
LC | 121536455 | 013/258 | T2 DI COLGTE-PALERMO 13/258 RPR SWTC | TABLEMTN | ETL.6500.POLE.NWOD | 2021-06-14 | 2021-06-09 | 2021-06-30 | 2022-06-09 | 2021-09-09 | On-time | 623 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | Out of Adjustment | Switch | Repair | 44886425 | T2 DI COLGTE-PALERMO 13/258 RPR SWTC | ICE
LC | 121536941 | 045/350 | T2 DI RND MTN-CTNWD #2 45/350 RPR OPGW | TABLEMTN | ETL.5640.TOWR | 2021-06-14 | 2021-06-10 | 2021-06-30 | 2022-06-10 | 2021-09-10 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44871873 | T2 DI RND MTN-CTNWD #2 45/350 RPR OPGW | ICW
LC | 121537808 | 016/001 | T2 DI CARIBOU #2 16/1 COTTER | TABLEMTN | ETL.6280.INSL.NCER | 2021-06-15 | 2021-06-11 | 2021-06-28 | 2022-06-11 | 2021-09-11 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44874061 | T2 DI CARIBOU #2 16/1 COTTER | ICW
LC | 121538088 | 008/043 | T2 DI SILVERADO-FULTON JCT 8/43 COTTER | LAKEVLLE | ETL.1610.INSL | 2021-06-15 | 2021-06-14 | 2021-08-19 | 2022-06-14 | 2021-09-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44861453 | T2 DI SILVERADO-FULTON JCT 8/43 COTTER | ICS
LC | 121538346 | 009/127 | T2 EI VLLY SPRNGS-CLY 09/127 RPR SWITCH | VICTOR | ETL.8264.POLE.WOOD | 2021-06-15 | 2021-06-15 | 2021-08-21 | 2022-06-15 | 2021-09-15 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW COMP OH FMOB TR2 PRTO AIR FRAB | Out of Adjustment | Switch | Repair | 44874839 | T2 EI VLLY SPRNGS-CLY 09/127 RPR SWITCH | ICE
LC | 121539339 | 011/099 | T2 DI CRAG VIEW-CASCADE 11/099 RPL SPLS | TABLEMTN | ETL.6750.INSL | 2021-06-15 | 2021-06-15 | 2021-08-31 | 2022-06-15 | 2021-09-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Replace | 44897785 | T2 DI CRAG VIEW-CASCADE 11/099 RPL SPLS | ICS
LC | 121539521 | 015/346 | T2 DRUM-GRSS VLLY-WEIMAR 15/385 RPR SWTC | SACTO | ETL.6760.SWIT | 2021-06-15 | 2021-06-15 | 2021-06-19 | 2022-06-15 | 2021-09-15 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 | Out of Adjustment | Switch | Repair | 44858174 | T2 DRUM-GRSS VLLY-WEIMAR 15/385 RPR SWTC | ICE
LC | 121539982 | 004/002 | T2 EI MELONES-CURTIS 4/2 RPR X-ARM | VICTOR | ETL.2390.POLE.WDPS | 2021-06-15 | 2021-06-15 | 2021-09-01 | 2022-06-15 | 2021-09-15 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 44888053 | T2 EI MELONES-CURTIS 4/2 RPR X-ARM | ICW
LC | 121540463 | 003/081 | T2 EI PLACER-DEL MAR 3/81 RPL GUY POLE | SACTO | ETL.7800.POLE.WOOD | 2021-06-15 | 2021-06-15 | 2022-12-08 | 2022-06-15 | 2022-06-15 | Late | 372 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | Rotten | Guy Pole-Wood | Replace | 31544428 | T2 EI PLACER-DEL MAR 3/81GUY RPL STRW | 70Y
LC | 121542905 | 009/090 | T2 EI PIT NO. 5-ROUND MTN #2 9/90 COTTER | TABLEMTN | ETL.5430.INSL.NCER | 2021-06-15 | 2021-06-15 | 2021-06-21 | 2022-06-15 | 2021-09-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 44874013 | T2 EI PIT NO. 5-ROUND MTN #2 9/90 COTTER | ICW
LC | 121543206 | 016/139 | T2 DI CRAG VIEW-CASCADE 16/139 RPR SHLW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-15 | 2021-06-09 | 2021-07-21 | 2022-06-09 | 2021-09-09 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44897746 | T2 DI CRAG VIEW-CASCADE 16/139 RPR SHLW | ICW
LC | 121544711 | 062/447 | T2 DI BRIDGVL-CTNWD 62/447 RPR SHLS | EUREKA | ETL.1110.TOWR | 2021-06-16 | 2021-06-15 | 2021-07-02 | 2022-06-15 | 2021-09-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44871502 | T2 DI BRIDGVL-CTNWD 62/447 RPR SHLS | ICS
LC | 121544716 | 018/075 | T2 DI DIABLO-MIDWAY #3 18/75 RPR INSS | PISMOBCH | ETL.5980.INSL | 2021-06-16 | 2021-06-15 | 2021-06-23 | 2022-06-15 | 2021-09-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44875605 | T2 DI DIABLO-MIDWAY #3 18/75 RPR INSS | ICS
LC | 121544717 | 003/028 | T2 DI SOBRANTE-""G"" #1" 3/28 COTTER | CONCORD | ETL.3720.INSL.CERA | 2021-06-16 | 2021-06-15 | 2021-07-02 | 2022-06-15 | 2021-09-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44873882 | T2 DI SOBRANTE-""G"" #1" 3/28 COTTER | ICS
LC | 121545738 | 021/147 | T2 DI CARIBOU-TABLE MTN 021/147 COTTER | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-16 | 2021-06-16 | 2021-08-04 | 2022-06-16 | 2021-09-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44873994 | T2 DI CARIBOU-TABLE MTN 021/147 COTTER | ICS
LC | 121545759 | :020/002 | T2 DI EAGLE ROCK-CORTINA :20/2 RPR SHLD | LAKEVLLE | ETL.1470.POLE.NWOD | 2021-06-16 | 2021-06-15 | 2021-07-22 | 2022-06-15 | 2021-09-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44871746 | T2 DI EAGLE ROCK-CORTINA :20/2 RPR SHLD | ICS
LC | 121546588 | 037/161 | T2 DI GEYSERS #9-LAKEVILL 037/161 COTTER | LAKEVLLE | ETL.4780.INSL | 2021-06-16 | 2021-06-16 | 2021-08-18 | 2022-06-16 | 2021-09-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44871929 | T2 DI FULTON-LAKEVILLE 037/161 COTTER | ICS
LC | 121551720 | 024/098 | T2 DI DIABLO-GATES #1 24/98 COTTER | PISMOBCH | ETL.5960.INSL | 2021-06-17 | 2021-06-16 | 2021-07-22 | 2022-06-16 | 2021-09-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44875607 | T2 DI DIABLO-GATES #1 24/98 COTTER | ICS
LC | 121551885 | 018/074 | T2 DI DIABLO-MIDWAY #3 018/074 COTTER | PISMOBCH | ETL.5980.INSL | 2021-06-17 | 2021-06-15 | 2021-07-01 | 2022-06-15 | 2021-09-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44875608 | T2 DI DIABLO-MIDWAY #3 018/074 COTTER | ICS
LC | 121552703 | 093/473 | T2 DI MALIN-ROUND MTN #2 93/473 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-06-17 | 2021-06-17 | 2021-07-01 | 2022-06-17 | 2021-09-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44872168 | T2 DI MALIN-ROUND MTN #2 93/473 RPR OPGW | ICS
LC | 121552905 | 024/101 | T2 DI TESLA-METCALF 24/101 COTTER | METCALF | ETL.6110.INSL | 2021-06-17 | 2021-06-16 | 2021-07-11 | 2022-06-16 | 2021-09-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44873889 | T2 DI TESLA-METCALF 24/101 COTTER | ICS
LC | 121553277 | 027/118 | T2 DI MSS LNDNG-METCALF 27/118 COTTER | MOSSLNDG | ETL.6050.INSL | 2021-06-17 | 2021-06-17 | 2021-07-07 | 2022-06-17 | 2021-09-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44874265 | T2 DI MSS LNDNG-METCALF 27/118 COTTER | ICS
LC | 121553425 | 012/078 | T2 DI CORTINA-VACA 12/78 RPR SHLS | SACTO | ETL.4540.TOWR | 2021-06-17 | 2021-06-16 | 2021-08-12 | 2022-06-16 | 2021-09-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44876239 | T2 DI CORTINA-VACA 12/78 RPR SHLS | ICS
LC | 121553815 | 017/003 | T2 EI LAYTONVILLE-WILLITS 17/3 COTR KEY | LAKEVLLE | ETL.8360.INSL.CERA | 2021-06-17 | 2021-06-17 | 2021-07-28 | 2022-06-17 | 2021-09-17 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44871745 | T2 EI LAYTONVILLE-WILLITS 17/3 COTR KEY | ICW
LC | 121554480 | 019/081 | T2 DI TESLA-METCALF 19/81 COTTER | METCALF | ETL.6110.INSL | 2021-06-17 | 2021-06-16 | 2021-07-11 | 2022-06-16 | 2021-09-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44873884 | T2 DI TESLA-METCALF 19/81 COTTER | ICS
LC | 121554488 | 019/076 | T2 DI DIABLO-MIDWAY #3 19/76 RPR INSS | PISMOBCH | ETL.5980.INSL | 2021-06-17 | 2021-06-17 | 2021-07-01 | 2022-06-17 | 2021-09-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44875612 | T2 DI DIABLO-MIDWAY #3 19/76 RPR INSS | ICS
LC | 121555895 | 009/072A | T2 DI HELMS-GREGG #1 9/72A RPR INSS | FRESNO | ETL.4870.INSL | 2021-06-17 | 2021-06-16 | 2021-07-22 | 2022-06-16 | 2021-09-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44875622 | T2 DI HELMS-GREGG #1 9/72A RPR INSS | ICS
LC | 121555976 | 043/208 | T2 DI LAKEVILLE-SBRNT#2 43/208 RPR INSS | CONCORD | ETL.4960.INSL | 2021-06-17 | 2021-06-15 | 2021-07-02 | 2022-06-15 | 2021-09-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44873888 | T2 DI LAKEVILLE-SBRNT#2 43/208 RPR INSS | ICS
LC | 121556827 | 008/086 | T2 PIT #5-ROUND MTN #1 008/086B RPL STRW | TABLEMTN | ETL.5420.POLE.WOOD | 2021-06-17 | 2021-06-12 | 2021-09-28 | 2022-06-12 | 2021-09-12 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO | Rotten | Structure-Wood | Replace | 31545613 | T2 PIT #5-ROUND MTN #1 11/112R RPL POLE | 70Y
LC | 121557028 | 044/212 | T2 DI LAKEVILLE-SBRNT #2 44/212 RPR INSS | CONCORD | ETL.4960.INSL | 2021-06-17 | 2021-06-16 | 2021-07-02 | 2022-06-16 | 2021-09-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44873886 | T2 DI LAKEVILLE-SBRNT #2 44/212 RPR INSS | ICS
LC | 121557212 | 006/001 | T2 DI DUNLAP TAP 006/001 RPR INSW | FRESNO | ETL.9061.INSL | 2021-06-17 | 2021-06-16 | 2021-08-23 | 2022-06-16 | 2021-09-16 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44875137 | T2 DI DUNLAP TAP 006/001 RPR INSW | ICW
LC | 121557489 | 051/388 | T2 DI BRDGVLL-CTTNWD 51/388 RPR SHLS | TABLEMTN | ETL.1110.TOWR | 2021-06-17 | 2021-06-15 | 2021-07-01 | 2022-06-15 | 2021-09-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44892931 | T2 DI BRDGVLL-CTTNWD 51/388 RPR SHLS | ICS
LC | 121557892 | 000/002 | T2 DI COLGATE-CHALLENGE 000/002 RPR GYWW | SACTO | ETL.6480.POLE.NWOD | 2021-06-17 | 2021-06-10 | 2021-08-09 | 2022-06-10 | 2021-09-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44876425 | T2 DI COLGATE-CHALLENGE 000/002 RPR GYWW | ICW
LC | 121558475 | 021/453 | T2 DI KILARC-DESCHUTES 021/453 RPL DAMW | TABLEMTN | ETL.7300.INSL.NCER | 2021-06-17 | 2021-06-11 | 2021-08-27 | 2022-06-11 | 2021-09-11 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace | 44903371 | T2 DI KILARC-DESCHUTES 021/453 RPL DAMW | ICW
LC | 121560025 | 022/099 | T2 DI MSS LNDNG-MTCLF 22/99 RPR INSS | MOSSLNDG | ETL.6050.INSL | 2021-06-18 | 2021-06-17 | 2021-07-06 | 2022-06-17 | 2021-09-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44875466 | T2 DI MSS LNDNG-MTCLF 22/99 RPR INSS | ICS
LC | 121560054 | 109/007 | T2 DI HMBLDT-BRDGVLLE 109/007 COTTER | EUREKA | ETL.1810.INSL.NCER | 2021-06-18 | 2021-06-17 | 2021-07-06 | 2022-06-17 | 2021-09-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44874355 | T2 DI HMBLDT-BRDGVLLE 109/007 COTTER | ICW
LC | 121560058 | 053/003 | T2 DI FRT RSS-GUALALA 053/003 COTTER | LAKEVLLE | ETL.6980.INSL.NCER | 2021-06-18 | 2021-06-17 | 2021-09-15 | 2022-06-17 | 2021-09-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44875029 | T2 DI FRT RSS-GUALALA 053/003 COTTER | ICW
LC | 121560085 | 004/009 | T2 DI LYTNVLLE-COVELO 4/9 RPR INSW | LAKEVLLE | ETL.7390.INSL.CERA | 2021-06-18 | 2021-06-17 | 2021-07-23 | 2022-06-17 | 2021-09-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44875027 | T2 DI LYTNVLLE-COVELO 4/9 RPR INSW | ICW
LC | 121560526 | 029/004 | T2 DI GRBRVL-LYTNVL 29/4 RPR GYWW | EUREKA | ETL.8365.POLE.STPS | 2021-06-18 | 2021-06-17 | 2021-07-23 | 2022-06-17 | 2021-09-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44874356 | T2 DI GRBRVL-LYTNVL 29/4 RPR GYWW | ICW
LC | 121560730 | 022/006 | T2 DI MNDC-WLLT-FRT BRGG 22/6 RPR INSW | LAKEVLLE | ETL.7550.INSL.NCER | 2021-06-18 | 2021-06-17 | 2021-07-21 | 2022-06-17 | 2021-09-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44875033 | T2 DI MNDC-WLLT-FRT BRGG 22/6 RPR INSW | ICW
LC | 121561802 | 012/079 | T2 DI CORTINA-VACA 12/79 RPR SHLS | SACTO | ETL.4540.TOWR | 2021-06-18 | 2021-06-15 | 2021-08-12 | 2022-06-15 | 2021-09-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44876424 | T2 DI CORTINA-VACA 12/79 RPR SHLS | ICS
LC | 121562213 | 053/007 | T2 DI FORT ROSS-GUALALA 53/7 COTTER | LAKEVLLE | ETL.6980.INSL.NCER | 2021-06-18 | 2021-06-17 | 2021-08-09 | 2022-06-17 | 2021-09-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44875031 | T2 DI FORT ROSS-GUALALA 53/7 COTTER | ICW
LC | 121562329 | 012/091A | T2 DI HELMS-GREGG #1 012/091A RPR INSS | FRESNO | ETL.4870.INSL | 2021-06-18 | 2021-06-16 | 2021-07-21 | 2022-06-16 | 2021-09-14 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31544499 | T2 DI HELMS-GREGG #1 012/091A RPL INSS | 93K
LC | 121562331 | 023/007 | T2 DI MNDCN-WLTS-FRT BRG 23/7 RPR INSW | LAKEVLLE | ETL.7550.INSL.NCER | 2021-06-18 | 2021-06-17 | 2021-07-21 | 2022-06-17 | 2021-09-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44875032 | T2 DI MNDCN-WLTS-FRT BRG 23/7 RPR INSW | ICW
LC | 121562733 | 024/100 | T2 DI TESLA-METCALF 24/100 RPR INSS | METCALF | ETL.6110.INSL | 2021-06-18 | 2021-06-17 | 2021-07-11 | 2022-06-17 | 2021-09-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44875613 | T2 DI TESLA-METCALF 24/100 RPR INSS | ICS
LC | 121562908 | 022/005 | T2 DI MNDCN-WLTTS-FRT BRG 22/5 RPR INSW | LAKEVLLE | ETL.7550.INSL.NCER | 2021-06-18 | 2021-06-17 | 2021-08-27 | 2022-06-17 | 2021-09-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44875035 | T2 DI MNDCN-WLTTS-FRT BRG 22/5 RPR INSW | ICW
LC | 121562948 | 032/002 | T2 DI MNDCN WLTS FT BRG 032/002 RPR GYWW | LAKEVLLE | ETL.7550.POLE.WOOD | 2021-06-18 | 2021-06-18 | 2021-07-21 | 2022-06-18 | 2021-09-18 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44875034 | T2 DI MNDCN WLTS FT BRG 032/002 RPR GYWW | ICW
LC | 121563061 | 014/105A | T2 DI HELMS-GREGG #1 14/105A COTTER | FRESNO | ETL.4870.INSL | 2021-06-18 | 2021-06-16 | 2021-07-22 | 2022-06-16 | 2021-09-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44875440 | T2 DI HELMS-GREGG #1 14/105A COTTER | ICS
LC | 121563150 | 031/475 | T2 DI CLAY-MARTEL 031/475 RPR INSW-COTR | VICTOR | ETL.8250.INSL.NCER | 2021-06-18 | 2021-06-17 | 2021-07-09 | 2022-06-17 | 2021-09-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44875325 | T2 DI CLAY-MARTEL 031/475 RPR INSW | ICW
LC | 121563272 | 002/022 | T2 DI CRAG VIEW-CASCADE 2/22 COTTER | TABLEMTN | ETL.1350.INSL.NCER | 2021-06-18 | 2021-06-18 | 2021-07-20 | 2022-06-18 | 2021-09-16 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44897741 | T2 DI CRAG VIEW-CASCADE 2/22 COTTER | ICW
LC | 121563290 | 001/017B | T2 DI CHRISTIE-WILLOW PASS 1/17 COTTER | CONCORD | ETL.6370.INSL.NCER | 2021-06-18 | 2021-06-18 | 2021-08-03 | 2022-06-18 | 2021-09-16 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44875614 | T2 DI CHRISTIE-WILLOW PASS 1/17 COTTER | ICW
LC | 121563336 | 090/456 | T2 DI MLN-RND MTN #2 90/456 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-06-18 | 2021-06-18 | 2021-07-01 | 2022-06-18 | 2021-09-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44887888 | T2 DI MLN-RND MTN #2 90/456 OPGW SPACERB | ICS
LC | 121564142 | 021/258 | T2 EI DRUM-SUMMIT NO. 1 21/258 RPR CNDW | SACTO | ETL.1440.INSL.CERA | 2021-06-18 | 2021-06-18 | 2021-06-25 | 2022-06-18 | 2021-09-18 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 44876422 | T2 EI DRUM-SUMMIT NO. 1 21/258 RPR CNDW | ICW
LC | 121564277 | 039/244 | T2 DI CZY HRS CNYN-SLNS-SL 39/244 COTTER | MOSSLNDG | ETL.2900.INSL.CERA | 2021-06-18 | 2021-06-18 | 2021-07-19 | 2022-06-18 | 2021-09-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44875467 | T2 DI CZY HRS CNYN-SLNS-SL 39/244 COTTER | ICS
LC | 121573289 | 003/025 | T2 PIT #7 TAP - 230 kV 3/025L RPL STRW | TABLEMTN | ETL.5442.POLE.WDPS | 2021-06-21 | 2021-06-21 | 2021-06-26 | 2022-06-21 | 2021-09-21 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544216 | T2 PIT #7 TAP - 230 KV 3/025L RPL STRW | 70Y
LC | 121578505 | 003/025 | T2 PIT #7 TAP - 230 kV 3/025R RPL STRW | TABLEMTN | ETL.5442.POLE.WDPS | 2021-06-22 | 2021-06-21 | 2021-06-26 | 2022-06-21 | 2021-09-21 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | POHW CREW COMP OH FMOB TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544216 | T2 PIT #7 TAP - 230 KV 3/025L RPL STRW | 70Y
LC | 121578508 | 003/025 | T2 PIT #7 TAP - 230 kV 3/025C RPL STRW | TABLEMTN | ETL.5442.POLE.WDPS | 2021-06-22 | 2021-06-21 | 2021-06-26 | 2022-06-21 | 2021-09-21 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | POHW CREW COMP OH FMOB TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544216 | T2 PIT #7 TAP - 230 KV 3/025L RPL STRW | 70Y
LC | 121579166 | 090/461 | T2 DI MALIN-ROUND MTN #2 90/461 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-06-22 | 2021-06-18 | 2021-07-01 | 2022-06-18 | 2021-09-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44892976 | T2 DI MALIN-ROUND MTN #2 90/461 RPR INSS | ICS
LC | 121579929 | 020/135 | T2 DI HELMS-GREGG #1 20/135 RPR INSS | FRESNO | ETL.4870.INSL | 2021-06-22 | 2021-06-17 | 2021-08-05 | 2022-06-17 | 2021-09-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44876392 | T2 DI HELMS-GREGG #1 20/135 RPR INSS | ICS
LC | 121580872 | 037/005 | T2 DI MNDCN-WLLT-FRT BRGG 37/5 RPR INSW | LAKEVLLE | ETL.7550.INSL.NCER | 2021-06-22 | 2021-06-17 | 2021-07-21 | 2022-06-17 | 2021-09-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44875036 | T2 DI MNDCN-WLLT-FRT BRGG 37/5 RPR INSW | ICW
LC | 121580996 | 010/132 | T2 DI IGNACIO-BLINAS #2 010/132 RPR INSS | LAKEVLLE | ETL.7180.INSL.NCER | 2021-06-22 | 2021-06-18 | 2021-08-02 | 2022-06-18 | 2021-09-18 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44875716 | T2 DI IGNACIO-BLINAS #2 010/132 RPR INSS | ICW
LC | 121581092 | 033/136 | T2 DI DIABLO-MIDWAY #2 033/136 RPR INSS | PISMOBCH | ETL.5970.INSL | 2021-06-22 | 2021-06-22 | 2021-07-08 | 2022-06-22 | 2021-09-22 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44896739 | T2 DI DIABLO-MIDWAY #2 033/136 RPR INSS | ICS
LC | 121581543 | 010/126 | T2 DI DRUM-SUMMIT #2 10/126 RPR INSS | SACTO | ETL.1450.INSL.CERA | 2021-06-22 | 2021-06-18 | 2021-08-27 | 2022-06-18 | 2021-09-18 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44896540 | T2 DI DRUM-SUMMIT #2 10/126 RPR INSS | ICS
LC | 121582817 | :016/015 | T2 EI EAGLE RCK-CRTNA :016/015 RPL HWRW | LAKEVLLE | ETL.1470.POLE.NWOD | 2021-06-22 | 2021-06-22 | 2021-06-23 | 2022-06-22 | 2021-09-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 44875940 | T2 EI EAGLE RCK-CRTNA :016/015 RPL HWRW | ICW
LC | 121583080 | 066/334 | T2 DI MALIN-ROUND MTN #2 66/334 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-06-22 | 2021-06-18 | 2021-06-29 | 2022-06-18 | 2021-09-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44887894 | T2 DI MALIN-ROUND MTN #2 66/334 RPR INSS | ICS
LC | 121584695 | 005/005 | T2 EI MENDOCINO-UKIAH 5/5L RPL STRW | LAKEVLLE | ETL.2420.POLE.WDPS | 2021-06-23 | 2021-06-23 | 2021-09-16 | 2022-06-23 | 2021-09-23 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544814 | T2 EI MENDOCINO-UKIAH 5/5L RPL STRW | 70Y
LC | 121585311 | 020/001 | T2 DI TRINITY-MAPLE CREEK 20/1INS CTR KY | EUREKA | ETL.8170.INSL.NCER | 2021-06-23 | 2021-06-22 | 2021-08-23 | 2022-06-22 | 2021-09-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44882272 | T2 DI TRINITY-MAPLE CREEK 20/1INS CTR KY | ICW
LC | 121586226 | 027/001 | T2 DI TRINITY-MAPLE CREEK 27/1 COTR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2021-06-23 | 2021-06-22 | 2021-08-23 | 2022-06-22 | 2021-09-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44882271 | T2 DI TRINITY-MAPLE CREEK 27/1 COTR GYWW | ICW
LC | 121586289 | 093/473 | T2 DI MALIN-RND MTN #2 93/473 RPR INSLS | TABLEMTN | ETL.6020.INSL | 2021-06-23 | 2021-06-18 | 2021-07-02 | 2022-06-18 | 2021-09-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44889840 | T2 DI MALIN-RND MTN #2 93/473 RPR INSLS | ICS
LC | 121586673 | :004/001 | T2 DI BLT-RVRBNK-MLNS :4/1 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-06-23 | 2021-06-22 | 2021-09-13 | 2022-06-22 | 2021-09-20 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544815 | T2 DI BLT-RVRBNK-MLNS :4/1 RPL STRW | 70Y
LC | 121586753 | 027/007 | T2 DI MNDCN-WLLTS-FRT BRGG 27/7 RPR INSW | LAKEVLLE | ETL.7550.INSL.NCER | 2021-06-23 | 2021-06-17 | 2021-07-21 | 2022-06-17 | 2021-09-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44882268 | T2 DI MNDCN-WLLTS-FRT BRGG 27/7 RPR INSW | ICW
LC | 121586876 | 011/083A | T2 DI HELMS-GREGG #1 11/893A COTTER | FRESNO | ETL.4870.INSL | 2021-06-23 | 2021-06-17 | 2021-07-22 | 2022-06-17 | 2021-09-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44876393 | T2 DI HELMS-GREGG #1 11/893A COTTER | ICS
LC | 121587381 | 025/181 | T2 DI TRINITY-CTNWD 25/181 COTTER | TABLEMTN | ETL.4040.INSL.CERA | 2021-06-23 | 2021-06-18 | 2021-08-07 | 2022-06-18 | 2021-09-16 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44904188 | T2 DI TRINITY-CTNWD 25/181 COTTER | ICW
LC | 121587574 | 009/059 | T2 DI MORAGA-OAKLAND "J" 9/59 RPLC INSS | CONCORD | ETL.2760.INSL.CERA | 2021-06-23 | 2021-06-22 | 2021-09-04 | 2022-06-22 | 2021-09-20 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31544645 | T2 DI MORAGA-OAKLAND "J" 9/59 RPLC INSS | 93K
LC | 121587616 | 001/012B | T2 PIT #7 TAP 1/012B RPL STRW | TABLEMTN | ETL.5442.POLE.WOOD | 2021-06-23 | 2021-06-23 | 2021-06-27 | 2022-06-23 | 2021-09-23 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544216 | T2 PIT #7 TAP - 230 KV 3/025L RPL STRW | 70Y
LC | 121587617 | 001/012A | T2 PIT #7 TAP 1/012A RPL STRW | TABLEMTN | ETL.5442.POLE.WOOD | 2021-06-23 | 2021-06-23 | 2021-06-29 | 2022-06-23 | 2021-09-23 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544216 | T2 PIT #7 TAP - 230 KV 3/025L RPL STRW | 70Y
LC | 121587618 | 001/012C | T2 PIT #7 TAP 1/012C RPL STRW | TABLEMTN | ETL.5442.POLE.WOOD | 2021-06-23 | 2021-06-23 | 2021-06-27 | 2022-06-23 | 2021-09-23 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544216 | T2 PIT #7 TAP - 230 KV 3/025L RPL STRW | 70Y
LC | 121587663 | 008/058 | T2 DI MORAGA-OAKLAND "J" 8/58 RPR INSS | CONCORD | ETL.2760.INSL.CERA | 2021-06-23 | 2021-06-22 | 2021-07-21 | 2022-06-22 | 2021-09-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44882464 | T2 DI MORAGA-OAKLAND "J" 8/58 RPR INSS | ICS
LC | 121587936 | 029/439 | T2 DI CLAY-MARTEL 029/439 INS COTTER KEY | VICTOR | ETL.8250.INSL.CERA | 2021-06-23 | 2021-06-22 | 2021-07-09 | 2022-06-22 | 2021-09-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44886220 | T2 DI CLAY-MARTEL 029/439 INS COTTER KEY | ICW
LC | 121587937 | 033/239 | T2 DI DRUM-RIO OSO #1 033/239 COTTER | SACTO | ETL.1430.INSL.CERA | 2021-06-23 | 2021-06-22 | 2021-08-28 | 2022-06-22 | 2021-09-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44896551 | T2 DI DRUM-RIO OSO #1 033/239 COTTER | ICS
LC | 121588016 | 003/039 | T2 DI CHRISTIE-WILLOW PASS 3/39 RPR INSW | CONCORD | ETL.6370.INSL.CERA | 2021-06-23 | 2021-06-22 | 2021-08-02 | 2022-06-22 | 2021-09-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44882466 | T2 DI CHRISTIE-WILLOW PASS 3/39 RPR INSW | ICW
LC | 121588212 | 015/204 | T2 DI W PNT-VLY SPRNGS 15/204 RPR INSW | VICTOR | ETL.8350.INSL.NCER | 2021-06-23 | 2021-06-22 | 2021-08-31 | 2022-06-22 | 2021-09-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44886221 | T2 DI W PNT-VLY SPRNGS 15/204 RPR INSW | ICW
LC | 121588219 | 033/500 | T2 DI CLAY-MARTEL 33/500 INS COTR KEY | VICTOR | ETL.8250.INSL.CERA | 2021-06-23 | 2021-06-22 | 2021-07-05 | 2022-06-22 | 2021-09-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44886222 | T2 DI CLAY-MARTEL 33/500 INS COTR KEY | ICW
LC | 121588981 | 008/158 | T2 DI MNT VST-LS GTS 8/158 INS COTR KEY | METCALF | ETL.7610.INSL | 2021-06-23 | 2021-06-22 | 2021-07-20 | 2022-06-22 | 2021-09-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44882469 | T2 DI MNT VST-LS GTS 8/158 INS COTR KEY | ICW
LC | 121588986 | 031/478 | T2 DI CLAY-MARTEL 031/478 RPL INSW | VICTOR | ETL.8250.INSL.NCER | 2021-06-23 | 2021-06-22 | 2021-09-20 | 2022-06-22 | 2021-09-22 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31544797 | T2 DI CLAY-MARTEL 031/478 RPL INSW | 93I
LC | 121589227 | B016/361 | T2 DI DRM-GRSS VLLY-WMR B16/361 RPR INSW | SACTO | ETL.6760.INSL.NCER | 2021-06-23 | 2021-06-22 | 2021-06-25 | 2022-06-22 | 2021-09-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44883002 | T2 DI DRM-GRSS VLLY-WMR B16/361 RPR INSW | ICW
LC | 121589343 | 020/306 | T2 DI KESWICK-TRINITY 020/306 INS CTR KY | TABLEMTN | ETL.7270.INSL.NCER | 2021-06-23 | 2021-06-22 | 2021-07-14 | 2022-06-22 | 2021-09-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44906102 | T2 DI KESWICK-TRINITY 020/306 INS CTR KY | ICW
LC | 121590608 | 000/021 | T2 DI KILARC-DESCHUTES 000/021 COTTER | TABLEMTN | ETL.7300.INSL.NCER | 2021-06-24 | 2021-06-18 | 2021-07-02 | 2022-06-18 | 2021-09-16 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44890368 | T2 DI KILARC-DESCHUTES 000/021 COTTER | ICW
LC | 121590732 | 015/009 | T2 DI TRINITY-MAPLE CRK 15/9 CTR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2021-06-24 | 2021-06-23 | 2021-09-03 | 2022-06-23 | 2021-09-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44882965 | T2 DI TRINITY-MAPLE CRK 15/9 CTR GYWW | ICW
LC | 121590735 | 027/196 | T2 DI CARIBOU-TABLE MTN 27/196 RPL INSS | TABLEMTN | ETL.4440.INSL | 2021-06-24 | 2021-06-23 | 2021-08-04 | 2022-06-23 | 2021-09-21 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31544843 | T2 DI CARIBOU-TABLE MTN 27/196 RPL INSS | 93K
LC | 121590737 | 087/444A | T2 DI MLN-RND MTN #2 87/444 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-06-24 | 2021-06-18 | 2021-06-29 | 2022-06-18 | 2021-09-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44887890 | T2 DI MLN-RND MTN #2 87/444 RPR OPGW | ICS
LC | 121590739 | 002/025 | T2 DI CRAG VIEW-CASCADE 2/25 RPR INSW | TABLEMTN | ETL.1350.INSL.NCER | 2021-06-24 | 2021-06-18 | 2021-07-20 | 2022-06-18 | 2021-09-18 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44897742 | T2 DI CRAG VIEW-CASCADE 2/25 RPR INSW | ICW
LC | 121590798 | 044/378 | T2 DI PIT #1-COTTONWOOD 44/378 COTTER | TABLEMTN | ETL.5390.INSL.NCER | 2021-06-24 | 2021-06-23 | 2021-09-20 | 2022-06-23 | 2021-09-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44897802 | T2 DI PIT #1-COTTONWOOD 44/378 COTTER | ICS
LC | 121590880 | 018/241 | T2 DI KESWICK-TRINITY 18/241 COTTER | TABLEMTN | ETL.7270.INSL.NCER | 2021-06-24 | 2021-06-23 | 2021-07-14 | 2022-06-23 | 2021-09-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44906101 | T2 DI KESWICK-TRINITY 18/241 COTTER | ICW
LC | 121590914 | 014/149 | T2 DI RND MTN-CTTNWD #2 14/149 RPR SHLS | TABLEMTN | ETL.5640.TOWR | 2021-06-24 | 2021-06-22 | 2021-07-01 | 2022-06-22 | 2021-09-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44894551 | T2 DI RND MTN-CTTNWD #2 14/149 RPR SHLS | ICS
LC | 121590986 | 027/007 | T2 DI TRINITY-MAPLE CRK 27/27 RPR INSW | EUREKA | ETL.8170.INSL | 2021-06-24 | 2021-06-22 | 2021-08-23 | 2022-06-22 | 2021-09-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44882967 | T2 DI TRINITY-MAPLE CRK 27/27 RPR INSW | ICW
LC | 121591459 | 017/229 | T2 DI KESWICK-TRINITY 017/229 COTTER | TABLEMTN | ETL.7270.POLE.WOOD | 2021-06-24 | 2021-06-22 | 2021-07-14 | 2022-06-22 | 2021-09-20 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44906100 | T2 DI KESWICK-TRINITY 017/229 COTTER | ICW
LC | 121591825 | 041/000 | T2 DI TRINITY MAPLE CREEK 41/00 RPR INSW | EUREKA | ETL.8170.POLE.WOOD | 2021-06-24 | 2021-06-23 | 2021-08-25 | 2022-06-23 | 2021-09-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Wood | Repair | 44882966 | T2 DI TRINITY MAPLE CREEK 41/00 RPR INSW | ICW
LC | 121591888 | 022/267 | T2 DI DRUM-SUMMIT #1 22/267 RPR INSW | SACTO | ETL.1440.INSL | 2021-06-24 | 2021-06-23 | 2021-06-30 | 2022-06-23 | 2021-09-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44882835 | T2 DI DRUM-SUMMIT #1 22/267 RPR INSW | ICW
LC | 121591975 | 021/252 | T2 DI DRUM-SUMMIT #1 21/252 RPR INSW | SACTO | ETL.1440.INSL.CERA | 2021-06-24 | 2021-06-23 | 2021-06-29 | 2022-06-23 | 2021-09-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44882838 | T2 DI DRUM-SUMMIT #1 21/252 RPR INSW | ICW
LC | 121592139 | 017/002 | T2 EI CLEAR LAKE-KONOCTI 17/2 RPR INSW | LAKEVLLE | ETL.6852.INSL.NCER | 2021-06-24 | 2021-06-24 | 2021-07-21 | 2022-06-24 | 2021-09-24 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44882964 | T2 EI CLEAR LAKE-KONOCTI 17/2 RPR INSW | ICW
LC | 121592193 | 011/095 | T2 DI CRAG VIEW-CASCADE 11/95R RPR OPGW | TABLEMTN | ETL.1350.POLE.STPS | 2021-06-24 | 2021-06-17 | 2022-09-15 | 2022-06-17 | 2022-06-17 | Late | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45365034 | T2 DI CRAG VIEW-CASCADE 11/95R RPR OPGW | ICW
LC | 121592320 | 015/492 | T2 DI SPAULDING-SUMMIT 15/492 RPLC GYWW | SACTO | ETL.8060.POLE.WOOD | 2021-06-24 | 2021-06-23 | 2021-06-30 | 2022-06-23 | 2021-09-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 44882834 | T2 DI SPAULDING-SUMMIT 15/492 RPLC GYWW | ICW
LC | 121592686 | 000/004A | T2 DI HMLTN BRNCH-CH/STR 0/4A COTTER | TABLEMTN | ETL.7000.POLE.WOOD | 2021-06-24 | 2021-06-23 | 2021-06-29 | 2022-06-23 | 2021-09-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | POHW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 121593567 | 022/262 | T2 DI DRUM-SUMMIT #1 22/262 RPR INSW | SACTO | ETL.1440.INSL | 2021-06-24 | 2021-06-23 | 2021-06-30 | 2022-06-23 | 2021-09-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44882830 | T2 DI DRUM-SUMMIT #1 22/262 RPR INSW | ICW
LC | 121593870 | 002/006 | T2 DI RIO DELL TAP 2/6 INS COTR KEY | EUREKA | ETL.7851.INSL.NCER | 2021-06-24 | 2021-06-23 | 2021-12-14 | 2022-06-23 | 2021-09-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44882969 | T2 DI RIO DELL TAP 2/6 INS COTR KEY | ICW
LC | 121595389 | 016/078 | T2 DI MOSS LDNG-LS BNS 16/78 RPR INSS | MOSSLNDG | ETL.6040.INSL | 2021-06-24 | 2021-06-24 | 2021-07-11 | 2022-06-24 | 2021-09-22 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44884091 | T2 DI MOSS LDNG-LS BNS 16/78 RPR INSS | ICS
LC | 121596223 | 015/005 | T2 DI TRNITY-MPL CRK 15/5 INS COTR KEY | EUREKA | ETL.8170.INSL | 2021-06-24 | 2021-06-23 | 2021-09-23 | 2022-06-23 | 2021-09-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44882968 | T2 DI TRNITY-MPL CRK 15/5 INS COTR KEY | ICW
LC | 121596224 | 030/211 | T2 DI TRINITY-CTNWD 30/211 RPR INSW | TABLEMTN | ETL.4040.INSL.CERA | 2021-06-24 | 2021-06-23 | 2021-09-21 | 2022-06-23 | 2021-09-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44904189 | T2 DI TRINITY-CTNWD 30/211 RPR INSW | ICW
LC | 121596228 | 000/004 | T2 DI MORAGA-CASTRO VLY 0/4 RPR SHLS | CONCORD | ETL.5250.TOWR | 2021-06-24 | 2021-06-23 | 2021-08-12 | 2022-06-23 | 2021-09-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44885296 | T2 DI MORAGA-CASTRO VLY 0/4 RPR SHLS | ICS
LC | 121598696 | 014/069 | T2 DI MS LDNG-LS BNS 14/69 RPR INSS | MOSSLNDG | ETL.6040.INSL | 2021-06-25 | 2021-06-24 | 2021-07-11 | 2022-06-24 | 2021-09-22 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44884092 | T2 DI MS LDNG-LS BNS 14/69 RPR INSS | ICS
LC | 121599356 | 094/479 | T2 DI MALIN-ROUND MTN #2 94/479 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-06-25 | 2021-06-24 | 2021-07-15 | 2022-06-24 | 2021-09-22 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44889841 | T2 DI MALIN-ROUND MTN #2 94/479 RPR INSS | ICS
LC | 121599971 | 027/193 | T2 DI CARIBOU-TABLE MTN 27/193 RPR INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-25 | 2021-06-23 | 2021-08-02 | 2022-06-23 | 2021-09-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44897780 | T2 DI CARIBOU-TABLE MTN 27/193 RPR INSS | ICS
LC | 121601128 | 091/464 | T2 DI MALIN-ROUND MTN #2 91/464 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-06-25 | 2021-06-24 | 2021-06-29 | 2022-06-24 | 2021-09-22 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44892972 | T2 DI MALIN-ROUND MTN #2 91/464 RPR OPGW | ICS
LC | 121601470 | 065/328 | T2 DI MALIN-RND MTN #2 65/328 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-25 | 2021-06-24 | 2021-06-29 | 2022-06-24 | 2021-09-24 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44887893 | T2 DI MALIN-RND MTN #2 65/328 RPR SHLS | ICS
LC | 121603725 | 003/000 | T2 DI RIO DELL TAP 3/0 RPR GYWW | EUREKA | ETL.7851.POLE.WDPS | 2021-06-25 | 2021-06-24 | 2021-08-16 | 2022-06-24 | 2021-09-24 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44884678 | T2 DI RIO DELL TAP 3/0 RPR GYWW | ICW
LC | 121603728 | 012/061 | T2 DI MS LDNG-MTCLF 12/61 RPR INSS | MOSSLNDG | ETL.6050.INSL | 2021-06-25 | 2021-06-25 | 2021-07-06 | 2022-06-25 | 2021-09-23 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44884098 | T2 DI MS LDNG-MTCLF 12/61 RPR INSS | ICS
LC | 121604186 | 023/009 | T2 DI GRBRVLL-LYTNVLL 23/9 INS COTR KEY | EUREKA | ETL.8365.INSL.NCER | 2021-06-25 | 2021-06-22 | 2021-07-23 | 2022-06-22 | 2021-09-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44884673 | T2 DI GRBRVLL-LYTNVLL 23/9 INS COTR KEY | ICW
LC | 121604340 | 065/329A | T2 DI MALIN-RND MTN #2 65/329A RPR INSS | TABLEMTN | ETL.6020.INSL.CERA | 2021-06-25 | 2021-06-24 | 2021-07-15 | 2022-06-24 | 2021-09-24 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44897786 | T2 DI MALIN-RND MTN #2 65/329A RPR INSS | ICS
LC | 121604374 | 094/480 | T2 DI MALIN-RND MTN #2 094/480 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-06-25 | 2021-06-24 | 2021-07-15 | 2022-06-24 | 2021-09-24 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44897795 | T2 DI MALIN-RND MTN #2 094/480 RPR INSS | ICS
LC | 121605680 | 009/070 | T2 DI CARIBOU-TABLE MTN 9/70 RPR COTR | TABLEMTN | ETL.4440.INSL.CERA | 2021-06-26 | 2021-06-25 | 2021-08-03 | 2022-06-25 | 2021-09-23 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44897758 | T2 DI CARIBOU-TABLE MTN 9/70 RPR COTR | ICS
LC | 121606542 | 043/209 | T2 DI IGNACIO-SOBRANTE 43/209 COTTER | CONCORD | ETL.4960.INSL | 2021-06-26 | 2021-06-16 | 2021-07-29 | 2022-06-16 | 2021-09-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44886140 | T2 DI IGNACIO-SOBRANTE 43/209 COTTER | ICS
LC | 121606788 | 006/014 | T2 DI VAL SPRGS-MARTELL #1 6/14 COTR KEY | VICTOR | ETL.8240.INSL.NCER | 2021-06-26 | 2021-06-25 | 2021-07-09 | 2022-06-25 | 2021-09-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44886238 | T2 DI VAL SPRGS-MARTELL #1 6/14 COTR KEY | ICW
LC | 121608016 | 006/003 | T2 DI MENDCNO-WLLTS-FT BRG 6/3 RPR GYWW | LAKEVLLE | ETL.7550.POLE.WOOD | 2021-06-26 | 2021-06-17 | 2021-07-21 | 2022-06-17 | 2021-09-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44884675 | T2 DI MENDCNO-WLLTS-FT BRG 6/3 RPR GYWW | ICW
LC | 121608156 | 080/405 | T2 DI MALIN-ROUND MTN#2 80/405 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-06-26 | 2021-06-26 | 2021-06-29 | 2022-06-26 | 2021-09-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44887891 | T2 DI MALIN-ROUND MTN#2 80/405 RPR INSS | ICS
LC | 121608259 | 017/083 | T2 DI MSS LNDNG-LS BANOS 17/83 RPR SHLS | MOSSLNDG | ETL.6040.TOWR | 2021-06-26 | 2021-06-24 | 2021-07-16 | 2022-06-24 | 2021-09-24 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44893008 | T2 DI MSS LNDNG-LS BANOS 17/83 RPR SHLS | ICS
LC | 121608688 | 079/404 | T2 DI MALIN-ROUND MTN #2 79/404 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-06-26 | 2021-06-26 | 2021-07-01 | 2022-06-26 | 2021-09-26 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44887892 | T2 DI MALIN-ROUND MTN #2 79/404 RPR SHLS | ICS
LC | 121608871 | 080/409 | T2 DI MALIN-RND MTN #2 080/409 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-06-26 | 2021-06-26 | 2021-07-15 | 2022-06-26 | 2021-09-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44897790 | T2 DI MALIN-RND MTN #2 080/409 RPR INSS | ICS
LC | 121608875 | 078/397 | T2 DI MALIN-ROUND MTN #2 78/397 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-06-26 | 2021-06-26 | 2021-07-01 | 2022-06-26 | 2021-09-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44887897 | T2 DI MALIN-ROUND MTN #2 78/397 RPR SHLS | ICS
LC | 121609263 | 009/040 | T2 DI DIABLO-GATES #1 009/040 RPR INSS | PISMOBCH | ETL.5960.INSL.CERA | 2021-06-26 | 2021-06-26 | 2021-07-13 | 2022-06-26 | 2021-09-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44905274 | T2 DI DIABLO-GATES #1 009/040 RPR INSS | ICS
LC | 121609456 | 083/422 | T2 DI MALIN-RND MTN #2 083/422 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-06-26 | 2021-06-26 | 2021-08-25 | 2022-06-26 | 2021-09-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44897792 | T2 DI MALIN-RND MTN #2 083/422 RPR INSS | ICS
LC | 121620498 | 015/134 | T2 DI CRAG VIEW-CASCADE 15/134 RPR OPGW | TABLEMTN | ETL.1350.POLE.STPS | 2021-06-28 | 2021-06-18 | 2021-07-22 | 2022-06-18 | 2021-09-18 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44897745 | T2 DI CRAG VIEW-CASCADE 15/134 RPR OPGW | ICW
LC | 121622859 | 023/167A | T2 DI TRNTY-CTTNWD 23/167A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2021-06-28 | 2021-06-27 | 2021-07-14 | 2022-06-27 | 2021-09-27 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44904187 | T2 DI TRNTY-CTTNWD 23/167A RPR GYWW | ICW
LC | 121623562 | 022/005 | T2 DI MNDCN-WLTTS-FRT BRG 22/5 RPR GYWW | LAKEVLLE | ETL.7550.POLE.WOOD | 2021-06-28 | 2021-06-17 | 2021-08-27 | 2022-06-17 | 2021-09-17 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44884676 | T2 DI MNDCN-WLTTS-FRT BRG 22/5 RPR GYWW | ICW
LC | 121624004 | 080/410 | T2 DI MLN-RND MTN #2 80/410 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-06-28 | 2021-06-26 | 2021-07-15 | 2022-06-26 | 2021-09-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44897791 | T2 DI MLN-RND MTN #2 80/410 RPR OPGW | ICS
LC | 121624071 | 004/053 | T2 DI SNEATH LANE-PACIFICA 4/53 RPL DAMW | METCALF | ETL.7575.INSL.NCER | 2021-06-28 | 2021-06-28 | 2021-09-20 | 2022-06-28 | 2021-09-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace | 44892408 | T2 DI SNEATH LANE-PACIFICA 4/53 RPL DAMW | ICW
LC | 121624073 | 021/490 | T2 DI DRM-GRS VLY-WMR 21/490 COTER KEY | SACTO | ETL.6760.INSL.NCER | 2021-06-28 | 2021-06-28 | 2021-06-30 | 2022-06-28 | 2021-09-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44891912 | T2 DI DRM-GRS VLY-WMR 21/490 COTER KEY | ICW
LC | 121624366 | 017/151B | T2 DI CRAG VIEW-CASCADE 17/151B RPR INSW | TABLEMTN | ETL.1350.INSL.CERA | 2021-06-28 | 2021-06-27 | 2021-07-21 | 2022-06-27 | 2021-09-27 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44897747 | T2 DI CRAG VIEW-CASCADE 17/151B RPR INSW | ICW
LC | 121624452 | 001/033B | T2 DI CARIBOU-WESTWOOD 001/033B RPR INSW | TABLEMTN | ETL.6300.INSL.CERA | 2021-06-28 | 2021-06-27 | 2021-07-02 | 2022-06-27 | 2021-09-27 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44892837 | T2 DI CARIBOU-WESTWOOD 001/033B RPR INSW | ICW
LC | 121624667 | 004/067 | T2 DI CETERVILLE-TABLE MTN 4/67 RPR INSW | TABLEMTN | ETL.6320.INSL.NCER | 2021-06-28 | 2021-06-28 | 2021-07-07 | 2022-06-28 | 2021-09-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 44895247 | T2 DI CETERVILLE-TABLE MTN 4/67 RPR INSW | ICW
LC | 121624745 | 016/374 | T2 DI DRUM-GRSS VLLY-WMR 16/374 RPR INSW | SACTO | ETL.6760.INSL.CERA | 2021-06-28 | 2021-06-28 | 2021-06-30 | 2022-06-28 | 2021-09-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44891911 | T2 DI DRUM-GRSS VLLY-WMR 16/374 RPR INSW | ICW
LC | 121624879 | 005/067 | 2 DI GRN VLLY-CMP EVRS 5/67 RPR INSW | MOSSLNDG | ETL.1710.INSL.CERA | 2021-06-28 | 2021-06-28 | 2021-07-06 | 2022-06-28 | 2021-09-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44885933 | T2 DI GRN VLLY-CMP EVRS 5/67 RPR INSW | ICW
LC | 121625230 | 001/019 | T2 DI CARIBOU #2 001/019 RPR GYWW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-06-28 | 2021-06-28 | 2021-07-01 | 2022-06-28 | 2021-09-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44886313 | T2 DI CARIBOU #2 001/019 RPR GYWW | ICW
LC | 121625315 | 018/422 | T2 DI DRM GRS VLY WEMAR 18/422 COTR KEY | SACTO | ETL.6760.INSL.NCER | 2021-06-28 | 2021-06-28 | 2021-07-30 | 2022-06-28 | 2021-09-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44896543 | T2 DI DRM GRS VLY WEMAR 18/422 COTR KEY | ICW
LC | 121625483 | A041/332A | T2 DI BRDGVILLE CTNWD A41/332A RPR GYWW | TABLEMTN | ETL.1110.POLE.WOOD | 2021-06-28 | 2021-06-28 | 2021-09-13 | 2022-06-28 | 2021-09-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44897752 | T2 DI BRDGVILLE CTNWD A41/3324 RPR GYWW | ICW
LC | 121627896 | A041/332C | T2 DI BRDGVLLE-CTTNWD A041/332C COTTER | TABLEMTN | ETL.1110.INSL.NCER | 2021-06-29 | 2021-06-28 | 2021-09-14 | 2022-06-28 | 2021-09-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44906070 | T2 DI BRDGVLLE-CTTNWD A041/332C COTTER | ICW
LC | 121628242 | 021/254 | T2 DI DRUM-SUMMIT #2 021/254 COTTER | SACTO | ETL.1450.INSL.CERA | 2021-06-29 | 2021-06-23 | 2021-08-27 | 2022-06-23 | 2021-09-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44896545 | T2 DI DRUM-SUMMIT #2 021/254 COTTER | ICW
LC | 121629616 | 012/126 | T2 DI PIT #5-RND MTN #1 12/126 RPR INSW | TABLEMTN | ETL.5420.INSL.CERA | 2021-06-29 | 2021-06-28 | 2021-07-28 | 2022-06-28 | 2021-09-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44907366 | T2 DI PIT #5-RND MTN #1 12/126 RPR INSW | ICW
LC | 121630941 | 001/055 | T2 DI HMLTN BRNCH-CHESTER 1/55 RPR INSS | TABLEMTN | ETL.7000.INSL | 2021-06-29 | 2021-06-28 | 2021-07-01 | 2022-06-28 | 2021-09-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44889842 | T2 DI HMLTN BRNCH-CHESTER 1/55 RPR INSS | ICW
LC | 121631340 | 011/112 | T2 PIT #5-ROUND MTN #1 11/112B RPL POLE | TABLEMTN | ETL.5420.POLE.WDPS | 2021-06-29 | 2021-06-26 | 2021-09-21 | 2022-06-26 | 2021-09-26 | On-time | 372 | Upgraded | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO | Rotten | Structure-Wood | Replace | 31545613 | T2 PIT #5-ROUND MTN #1 11/112R RPL POLE | 70Y
LC | 121632963 | 086/000C | T2 DI HMBLDT-BRDGVLL 086/000C COTTER | EUREKA | ETL.1810.INSL.NCER | 2021-06-29 | 2021-06-28 | 2021-08-06 | 2022-06-28 | 2021-09-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44887776 | T2 DI HMBLDT-BRDGVLL 086/000C COTTER | ICW
LC | 121633158 | 005/065 | T2 DI GRN VLLY-CMP EVRS 5/65 COTTER | MOSSLNDG | ETL.1710.INSL.CERA | 2021-06-29 | 2021-06-28 | 2021-07-06 | 2022-06-28 | 2021-09-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44887941 | T2 DI GRN VLLY-CMP EVRS 5/65 COTTER | ICW
LC | 121636956 | 002/004 | T2 DI RIO DEL TAP 002/004 INS COTR KEY | EUREKA | ETL.7851.INSL | 2021-06-30 | 2021-06-29 | 2021-08-16 | 2022-06-29 | 2021-09-29 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44890441 | T2 DI RIO DEL TAP 002/004 INS COTR KEY | ICW
LC | 121637246 | 024/184 | T2 DI PARADISE-TBL MTN 024/184 COTTER | TABLEMTN | ETL.4316.INSL.CERA | 2021-06-30 | 2021-06-30 | 2021-07-22 | 2022-06-30 | 2021-09-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44905935 | T2 DI PARADISE-TBL MTN 024/184 COTTER | ICW
LC | 121639813 | 024/005 | T2 EI TULE-SPRINGVILLE 24/005 RPL STRW | MIDWAY | ETL.9040.POLE.WOOD | 2021-06-30 | 2021-06-30 | 2021-08-30 | 2022-06-30 | 2021-09-30 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31545409 | T2 EI TULE-SPRINGVILLE 24/005 RPL STRW | 70Y
LC | 121639817 | 024/006 | T2 TULE-SPRINGVILLE 24/6 RPL STRW | MIDWAY | ETL.9040.POLE.WOOD | 2021-06-30 | 2021-06-30 | 2021-08-30 | 2022-06-30 | 2021-09-30 | On-time | 372 | Upgraded | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31545409 | T2 EI TULE-SPRINGVILLE 24/005 RPL STRW | 70Y
LC | 121641652 | 010/131 | T2 DIVIDE-CABRILLO #1 10/131 RPL INSW | PISMOBCH | ETL.1380.INSL.CERA | 2021-06-30 | 2021-06-30 | 2021-08-26 | 2022-06-30 | 2021-09-30 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545408 | T2 DIVIDE-CABRILLO #1 10/127 RPL INSW | 93I
LC | 121643026 | 044/211 | T2 DI LKVL-SBRNT #2 44/211 COTTER | CONCORD | ETL.4960.INSL.NCER | 2021-07-01 | 2021-06-30 | 2021-08-01 | 2022-06-30 | 2021-09-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44892184 | T2 DI LKVL-SBRNT #2 44/211 COTTER | ICS
LC | 121643497 | 079/404 | T2 DI MLIN-ROUND MTN #2 79/404 RPR INSLS | TABLEMTN | ETL.6020.INSL.CERA | 2021-07-01 | 2021-06-30 | 2021-07-15 | 2022-06-30 | 2021-09-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44915725 | T2 DI MLIN-ROUND MTN #2 79/404 RPR INSLS | ICS
LC | 121644351 | 032/008 | T2 FULTON-HOPLAND 32/008 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-07-01 | 2021-07-01 | 2022-06-23 | 2022-07-01 | 2022-07-01 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31545497 | T2 FULTON-HOPLAND 32/008 RPL STRW | 70Y
LC | 121645244 | 011/112 | T2 PIT #5-ROUND MTN #1 11/112R RPL POLE | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-01 | 2021-06-26 | 2021-09-21 | 2022-06-26 | 2021-09-26 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | Rotten | Structure-Wood | Replace | 31545613 | T2 PIT #5-ROUND MTN #1 11/112R RPL POLE | 70Y
LC | 121645245 | 011/112 | T2 PIT #5-ROUND MTN #1 11/112C RPL POLE | TABLEMTN | ETL.5420.POLE.WDPS | 2021-07-01 | 2021-06-26 | 2021-09-21 | 2022-06-26 | 2021-09-26 | On-time | 372 | Upgraded | Closed | HFTD 2 | POHW OTHR COMP OH TR2 PRTO | Rotten | Structure-Wood | Replace | 31545613 | T2 PIT #5-ROUND MTN #1 11/112R RPL POLE | 70Y
LC | 121646845 | 010/122C | T2 DI DRUM-SUMMIT #2 10/122C COTTER | SACTO | ETL.1450.INSL.NCER | 2021-07-01 | 2021-06-28 | 2021-08-27 | 2022-06-28 | 2021-09-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44896556 | T2 DI DRUM-SUMMIT #2 10/122C COTTER | ICW
LC | 121647606 | 078/395A | T2 DI MALIN-ROUND MTN #2 78/395 RPL OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-01 | 2021-06-30 | 2022-07-12 | 2022-06-30 | 2022-06-30 | Late | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 45215221 | T2 DI MALIN-ROUND MTN #2 78/395 RPL OPGW | ICS
LC | 121647748 | 048/204A | T2 DI TEMPLETON-GATES 48/204A RPR OPGW | PISMOBCH | ETL.5934.TOWR | 2021-07-01 | 2021-07-01 | 2021-07-20 | 2022-07-01 | 2021-09-29 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44907214 | T2 DI TEMPLETON-GATES 48/204A RPR OPGW | ICS
LC | 121647989 | 014/119 | T2 DI CRAG VIEW CSCD 14/119 RPR OPGW | TABLEMTN | ETL.1350.POLE.STPS | 2021-07-01 | 2021-06-18 | 2021-08-04 | 2022-06-18 | 2021-09-18 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44897744 | T2 DI CRAG VIEW CSCD 14/119 RPR OPGW | ICW
LC | 121649147 | 010/054 | T2 DI CONTRA COSTA-DELTA 10/54 RPL INSS | CONCORD | ETL.4490.INSL | 2021-07-01 | 2021-06-28 | 2021-09-17 | 2022-06-28 | 2022-06-28 | On-time | 532 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31545707 | T2 DI CONTRA COSTA-DELTA SWITCHING YARD+ | 93K
LC | 121649148 | 010/054 | T2 DI CC DELTA SWITCHING 10/54 RPL HRDT | CONCORD | ETL.4490.INSL | 2021-07-01 | 2021-06-28 | 2021-09-17 | 2022-06-28 | 2022-06-28 | On-time | 543 | Upgraded | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44955071 | T2 DI CC DELTA SWITCHING 10/54 RPL HRDT | ICQ
LC | 121653464 | 013/104 | T2 DI TIGER CRK-ELECTRA 13/104 RPR INSS | VICTOR | ETL.5780.INSL | 2021-07-02 | 2021-07-01 | 2021-09-17 | 2022-07-01 | 2021-10-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44893001 | T2 DI TIGER CRK-ELECTRA 13/104 RPR INSS | ICS
LC | 121653700 | 005/071 | T2 DI HAT CREEK#1-PIT#1 05/071 RPR ADSS | TABLEMTN | ETL.7020.POLE.WDPS | 2021-07-02 | 2021-07-01 | 2021-07-22 | 2022-07-01 | 2021-10-01 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44903363 | T2 DI HAT CREEK#1-PIT#1 05/071 RPR ADSS | ICW
LC | 121653915 | 010/158B | T2 DI SISQUOC-SY SW STA 010/158 RPR INSW | PISMOBCH | ETL.3700.INSL.NCER | 2021-07-02 | 2021-06-30 | 2021-07-15 | 2022-06-30 | 2021-09-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44907213 | T2 DI SISQUOC-SY SW STA 010/158 RPR INSW | ICW
LC | 121654000 | 032/131 | T2 DI DIABLO-MIDWAY#2 032/131 RPR INSS | PISMOBCH | ETL.5970.TOWR | 2021-07-02 | 2021-07-02 | 2021-07-14 | 2022-07-02 | 2021-10-03 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44907212 | T2 DI DIABLO-MIDWAY#2 032/131 RPR INSS | ICS
LC | 121659012 | 015/067 | T2 DI SL OBISPO-OCEANO 15/67R RPR GYWW | PISMOBCH | ETL.3530.POLE.WDPS | 2021-07-02 | 2021-07-01 | 2021-07-19 | 2022-07-01 | 2021-10-01 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 44907211 | T2 DI SL OBISPO-OCEANO 15/67R RPR GYWW | ICW
LC | 121659051 | 015/067 | T2 DI SL OBISPO-OCEANO 15/67 RPR INSW | PISMOBCH | ETL.3530.INSL.CERA | 2021-07-02 | 2021-07-01 | 2021-07-19 | 2022-07-01 | 2021-10-01 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44907210 | T2 DI SL OBISPO-OCEANO 15/67 RPR INSW | ICW
LC | 121659365 | 005/077 | T2 DI VLLY SPRNGS-CLY 5/77L GYWW COTTER | VICTOR | ETL.8264.POLE.WDPS | 2021-07-02 | 2021-07-02 | 2021-08-26 | 2022-07-02 | 2021-10-02 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44896734 | T2 DI VLLY SPRNGS-CLY 5/77L GYWW COTTER | ICW
LC | 121660515 | 005/070 | T2 DI HAT CREEK #1-PIT #1 5/70 COTTER | TABLEMTN | ETL.7020.INSL.CERA | 2021-07-03 | 2021-07-01 | 2021-07-22 | 2022-07-01 | 2021-09-29 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44903362 | T2 DI HAT CREEK #1-PIT #1 5/70 COTTER | ICW
LC | 121660642 | 001/011 | T2 DI PIT #7 TAP 1/11 RPR SHLW | TABLEMTN | ETL.5442.POLE.STPS | 2021-07-03 | 2021-06-28 | 2022-07-14 | 2022-06-28 | 2022-06-28 | Late | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45213838 | T2 DI PIT #7 TAP 1/11 RPR SHLW | ICW
LC | 121662426 | 010/060 | T2 DI TESLA-RAVENSWD 10/60 GRD WAS INSU | CONCORD | ETL.5730.INSL | 2021-07-03 | 2021-07-02 | 2021-08-17 | 2022-07-02 | 2021-10-02 | On-time | 622 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Contaminated | Insulator | Ground Wash | 44905114 | T2 DI TESLA-RAVENSWD 10/60 GRD WAS INSU | ICD
LC | 121664418 | 028/190 | T2 DI POE-RIO OSO 028/190 INS COTR KEY | TABLEMTN | ETL.5540.INSL | 2021-07-05 | 2021-07-05 | 2021-07-27 | 2022-07-05 | 2021-10-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44897803 | T2 DI POE-RIO OSO 028/190 INS COTR KEY | ICS
LC | 121664565 | -018/004 | T3 DI FULTON-CALISTOGA -018/004 COTTER | LAKEVLLE | ETL.6880.INSL.NCER | 2021-07-05 | 2021-07-05 | 2021-07-27 | 2022-01-01 | 2021-10-05 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44896487 | T3 DI FULTON-CALISTOGA -018/004 COTTER | ICW
LC | 121667062 | 075/384 | T2 DI MLN-RND MTN #2 75/384 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-07-06 | 2021-07-06 | 2021-07-10 | 2022-07-06 | 2021-10-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44904184 | T2 DI MLN-RND MTN #2 75/384 RPR INSS | ICS
LC | 121667096 | 005/146A | T3 DI DRUM-SPAULDING 5/146A COTTER | SACTO | ETL.6770.INSL.CERA | 2021-07-06 | 2021-07-06 | 2021-09-02 | 2022-01-02 | 2021-10-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44896559 | T3 DI DRUM-SPAULDING 5/146A COTTER | ICW
LC | 121667800 | 008/074 | T2 DI PARADISE-TABLE MTN 8/74 COTTER | TABLEMTN | ETL.4316.INSL.CERA | 2021-07-06 | 2021-07-05 | 2021-08-11 | 2022-07-05 | 2021-10-03 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44897798 | T2 DI PARADISE-TABLE MTN 8/74 COTTER | ICS
LC | 121668169 | 007/077 | T3 DI DRUM-RIO OSO #1 7/77 HANGER | SACTO | ETL.1420.TOWR | 2021-07-06 | 2021-07-06 | 2021-08-03 | 2022-01-02 | 2021-10-04 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44905399 | T3 DI DRUM-RIO OSO #1 7/77 HANGER | ICQ
LC | 121668175 | 007/077 | T3 DI DRUM-RIO OSO #1 7/77 RPL INSS | SACTO | ETL.1420.INSL.CERA | 2021-07-06 | 2021-07-06 | 2021-08-03 | 2022-01-02 | 2021-10-04 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31545900 | T3 DI DRUM-RIO OSO #1 7/77 RPL INSS | 93K
LC | 121668347 | 012/001 | T3 DI MAPLE CREEK-HOOPA 12/1 COTTER | EUREKA | ETL.7490.INSL.CERA | 2021-07-06 | 2021-07-06 | 2021-07-27 | 2022-01-02 | 2021-10-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44896483 | T3 DI MAPLE CREEK-HOOPA 12/1 COTTER | ICW
LC | 121669960 | 025/198 | T2 DI MDL FRK-GLD HILL 25/198 ANTI SPLIT | SACTO | ETL.5140.POLE.WDPS | 2021-07-06 | 2021-07-05 | 2021-08-10 | 2022-07-05 | 2021-10-03 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | Missing | Hardware-Wood | Install | 44896580 | DI MIDDLE FRK-GLD HILL 25/198 ANTI SPLIT | ICW
LC | 121671131 | 076/389 | T2 DI MLN-RD MNTN #2 76/389 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-06 | 2021-07-06 | 2021-07-15 | 2022-07-06 | 2021-10-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44897788 | T2 MLN-RD MNTN #2 76/389 RPR OPGW | ICS
LC | 121671601 | 010/046 | T2 DI BRENTWOOD-KELSO 010/046 RPL INSS | CONCORD | ETL.4410.INSL | 2021-07-06 | 2021-07-06 | 2021-09-16 | 2022-07-06 | 2021-10-04 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31545858 | T2 DI BRENTWOOD-KELSO 010/046 RPL INSS | 93K
LC | 121671604 | 010/046 | T2 DI BRENTWOOD-KELSO 010/046 HANGER | CONCORD | ETL.4410.INSL | 2021-07-06 | 2021-07-06 | 2021-09-16 | 2022-07-06 | 2021-10-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Steel | Repair | 44907065 | T2 DI BRENTWOOD-KELSO 010/046 HANGER | ICS
LC | 121671607 | 013/065 | T2 DI CONTRA CST-DLT SWG 13/65 RPL INSS | CONCORD | ETL.4490.INSL | 2021-07-06 | 2021-07-06 | 2021-09-17 | 2022-07-06 | 2021-10-04 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31545859 | T2 DI CONTRA CST-DLT SWG 13/65 RPL INSS | 93K
LC | 121671609 | 013/065 | T2 DI CONTRA CST-DLT SWG 13/65 HANGER | CONCORD | ETL.4490.INSL | 2021-07-06 | 2021-07-06 | 2021-09-17 | 2022-07-06 | 2021-10-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Steel | Repair | 44907064 | T2 DI CONTRA CST-DLT SWG 13/65 HANGER | ICS
LC | 121673307 | 078/399 | T2 DI MALIN-ROUND MTN #2 78/399 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-07-07 | 2021-07-06 | 2021-07-11 | 2022-07-06 | 2021-10-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 44904185 | T2 DI MALIN-ROUND MTN #2 78/399 RPR INSS | ICS
LC | 121673745 | 076/387 | T2 DI MALIN-ROUND MTN #2 76/387 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-07 | 2021-07-06 | 2022-07-12 | 2022-07-06 | 2022-07-06 | Late | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45215178 | T2 DI MALIN-ROUND MTN #2 76/387 RPR OPGW | ICS
LC | 121674056 | 002/018 | T2 DI MTN GATE JCT-CASCADE 2/18 RPR INSW | TABLEMTN | ETL.7640.INSL.CERA | 2021-07-07 | 2021-07-06 | 2021-07-29 | 2022-07-06 | 2021-10-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44907363 | T2 DI MTN GATE JCT-CASCADE 2/18 RPR INSW | ICW
LC | 121674857 | 009/098 | T2 DI PIT #5-ROUND MTN #2 9/98 COTR KEY | TABLEMTN | ETL.5430.INSL.NCER | 2021-07-07 | 2021-07-06 | 2021-07-22 | 2022-07-06 | 2021-10-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44907361 | T2 DI PIT #5-ROUND MTN #2 9/98 COTR KEY | ICW
LC | 121675328 | 000/005 | T2 DI MTN GT JCT-CSCD 0/5 COTTER | TABLEMTN | ETL.7640.INSL.CERA | 2021-07-07 | 2021-07-06 | 2021-07-29 | 2022-07-06 | 2021-10-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44907360 | T2 DI MTN GT JCT-CSCD 0/5 COTTER | ICW
LC | 121676925 | -017/006 | T3 DI FULTON-CALISTOGA -017/006 COTTER | LAKEVLLE | ETL.6880.INSL.NCER | 2021-07-07 | 2021-07-05 | 2021-07-27 | 2022-01-01 | 2021-10-03 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44826070 | T3 DI FULTON-CALISTOGA -015/001 RPR INSW | ICW
LC | 121677813 | 008/102 | T2 EI DRUM-SUMMIT #1 8/102 RPR SWITCH | SACTO | ETL.1440.TOWR | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2022-07-07 | 2021-10-07 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP OTHR COMP OH FMOB TR2 PRTO | Out of Adjustment | Switch | Repair | 44895230 | T2 EI DRUM-SUMMIT #1 8/102 RPR SWITCH | ICE
LC | 121678378 | 074/378 | T2 DI MALIN-ROUND MTN #2 74/378 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-07-07 | 2021-07-06 | 2021-07-10 | 2022-07-06 | 2021-10-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44904182 | T2 DI MALIN-ROUND MTN #2 74/378 RPR INSS | ICS
LC | 121678577 | 075/380C | T2 DI MALIN-RND MTN #2 75/380B RPR INSS | TABLEMTN | ETL.6020.TOWR | 2021-07-07 | 2021-07-07 | 2021-07-10 | 2022-07-07 | 2021-10-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44904183 | T2 DI MALIN-RND MTN #2 75/380B RPR INSS | ICS
LC | 121679370 | 009/063 | T2 DI COTTONWD-DELEVAN #1 9/63 RPR SHLS | TABLEMTN | ETL.4550.TOWR | 2021-07-07 | 2021-06-29 | 2021-07-20 | 2022-06-29 | 2021-09-29 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44907353 | T2 DI COTTONWD-DELEVAN #1 9/63 RPR SHLS | ICS
LC | 121679562 | T052 | T3 EI MIDWAY-SANTA MARIA T052 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2021-07-07 | 2021-07-07 | 2022-07-13 | 2022-01-03 | 2022-01-07 | Late | 543 | Upgraded | Closed | HFTD 3 | RELW INSP PGEA COMP OH FMOB TR3 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45098887 | T3 EI MIDWAY-SANTA MARIA T052 RPR FOND | ICQ
LC | 121680588 | 021/094 | T2 DI MSS LNDNG-LOS BNS 21/94 RPR INSS | MOSSLNDG | ETL.6040.INSL.CERA | 2021-07-08 | 2021-07-07 | 2021-07-17 | 2022-07-07 | 2021-10-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44905634 | T2 DI MSS LNDNG-LOS BNS 21/94 RPR INSS | ICS
LC | 121681288 | 014/175 | T2 DI DT-M GT JT-MN GT J 14/175 RPR INSW | TABLEMTN | ETL.6750.INSL.CERA | 2021-07-08 | 2021-07-06 | 2021-07-28 | 2022-07-06 | 2021-10-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44907346 | T2 DI DT-M GT JT-MN GT J 14/175 RPR INSW | ICW
LC | 121681657 | 010/099 | T2 DI PIT #5-ROUND MTN #1 10/99 COTR KEY | TABLEMTN | ETL.5420.INSL.CERA | 2021-07-08 | 2021-07-06 | 2021-07-27 | 2022-07-06 | 2021-10-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44907341 | T2 DI PIT #5-ROUND MTN #1 10/99 COTR KEY | ICW
LC | 121682594 | 037/151 | T2 DI DIABLO-MIDWAY #3 037/151 RPR SHLS | PISMOBCH | ETL.5980.TOWR | 2021-07-08 | 2021-07-07 | 2021-07-20 | 2022-07-07 | 2021-10-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44907203 | T2 DI DIABLO-MIDWAY #3 037/151 RPR SHLS | ICS
LC | 121684230 | 004/033 | T2 DI TRNITY-CTTONWD 4/33 RPL INSW | TABLEMTN | ETL.4040.INSL.CERA | 2021-07-08 | 2021-07-07 | 2022-08-08 | 2022-07-07 | 2022-07-07 | Late | 508 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548130 | T2 DI TRNITY-CTTONWD 4/33 RPL INSW | 93I
LC | 121684498 | 004/008 | T3 DI DONNELLS-MI-WUK 4/8 COTTER | VICTOR | ETL.1400.INSL | 2021-07-08 | 2021-07-08 | 2021-10-05 | 2022-01-04 | 2021-10-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44905714 | T3 DI DONNELLS-MI-WUK 4/8 COTTER | ICW
LC | 121687206 | 017/069 | T3 DI DIABLO-GTS #1 17/69 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2021-07-09 | 2021-07-06 | 2021-07-23 | 2022-01-02 | 2021-10-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 44907201 | T3 DI DIABLO-GTS #1 17/69 RPR GYWS | ICS
LC | 121687209 | 017/069 | T3 DI DIABLO-GATES #1 17/69 COTR KEY | PISMOBCH | ETL.5960.INSL | 2021-07-09 | 2021-07-06 | 2021-07-19 | 2022-01-02 | 2021-10-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44907200 | T3 DI DIABLO-GATES #1 17/69 COTR KEY | ICS
LC | 121687392 | 006/062 | T2 DI COTTONWD-BNTN #2 6/62 COTTER | TABLEMTN | ETL.6650.INSL.CERA | 2021-07-09 | 2021-07-07 | 2021-08-27 | 2022-07-07 | 2021-10-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44907258 | T2 DI COTTONWD-BNTN #2 6/62 COTTER | ICW
LC | 121687508 | 049/244 | T2 DI MALIN-RND MTN #2 49/244 RPR INSS | TABLEMTN | ETL.6020.INSL.CERA | 2021-07-09 | 2021-07-09 | 2021-07-15 | 2022-07-09 | 2021-10-07 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44907257 | T2 DI MALIN-RND MTN #2 49/244 RPR INSS | ICS
LC | 121687974 | 018/000 | T3 DI DONNELLS-MI-WUK 18/0 COTR KEY | VICTOR | ETL.1400.INSL | 2021-07-09 | 2021-07-08 | 2021-10-05 | 2022-01-04 | 2021-10-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44905717 | T3 DI DONNELLS-MI-WUK 18/0 COTR KEY | ICW
LC | 121688030 | 041/167 | T2 DI DIABLO-MIDWAY #3 41/167 RPR INSS | PISMOBCH | ETL.5980.TOWR | 2021-07-09 | 2021-07-08 | 2021-08-24 | 2022-07-08 | 2021-10-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Repair | 44907119 | T2 DI DIABLO-MIDWAY #3 41/167 RPR INSS | ICS
LC | 121690307 | 002/012 | T3 DI KONOCTI-EAGLE ROCK 2/12 COTTER | LAKEVLLE | ETL.6861.INSL.NCER | 2021-07-09 | 2021-07-09 | 2021-07-21 | 2022-01-05 | 2021-10-09 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44905204 | T3 DI KONOCTI-EAGLE ROCK 2/12 COTTER | ICW
LC | 121690645 | 010/143 | T2 DI DEL-MTN GT JCT 10/143 RPR INSW | TABLEMTN | ETL.6750.INSL.CERA | 2021-07-09 | 2021-07-09 | 2021-08-07 | 2022-07-09 | 2021-10-09 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44907254 | T2 DI DEL-MTN GT JCT 10/143 RPR INSW | ICW
LC | 121691500 | 034/232A | T2 DI TRINITY-COTTNWD B34/232A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2021-07-09 | 2021-07-08 | 2021-08-07 | 2022-07-08 | 2021-10-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44907253 | T2 DI TRINITY-COTTNWD B34/232A RPR GYWW | ICW
LC | 121692253 | 091/465 | T2 DI MLN-RND MTN #2 91/465 RPR SHLD WR | TABLEMTN | ETL.6020.TOWR | 2021-07-09 | 2021-07-09 | 2021-07-10 | 2022-07-09 | 2021-10-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44898452 | T2 DI MLN-RND MTN #2 91/465 RPR SHLD WR | ICS
LC | 121705027 | 086/000F | T2 DI HUMBOLDT-BRIDGEVLL 86/0F RPR INSW | EUREKA | ETL.1810.POLE.WOOD | 2021-07-10 | 2021-07-09 | 2021-08-04 | 2022-07-09 | 2021-10-09 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Wood | Repair | 44905917 | T2 DI HUMBOLDT-BRIDGEVLL 86/0F RPR INSW | ICW
LC | 121705029 | 086/000G | T2 DI HMBLDT-BRDGVLLE 086/000G RPR INSW | EUREKA | ETL.1810.POLE.WOOD | 2021-07-10 | 2021-07-09 | 2021-08-04 | 2022-07-09 | 2021-10-09 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Wood | Repair | 44906088 | T2 DI HMBLDT-BRDGVLLE 086/000G RPR INSW | ICW
LC | 121705389 | 077/392 | T2 DI MALIN-ROUND MTN #2 77/392 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-07-10 | 2021-07-09 | 2021-07-15 | 2022-07-09 | 2021-10-09 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44907403 | T2 DI MALIN-ROUND MTN #2 77/392 RPR SHLS | ICS
LC | 121705980 | 053/262 | T2 DI MALIN-ROUND MTN#2 53/262 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-07-10 | 2021-07-09 | 2021-07-15 | 2022-07-09 | 2021-10-07 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44907417 | T2 DI MALIN-ROUND MTN#2 53/262 RPR SHLS | ICS
LC | 121706398 | 006/144 | T2 DI DEL MONTE-VIEJO 6/144 RPL INSW | MOSSLNDG | ETL.6710.INSL | 2021-07-10 | 2021-07-10 | 2021-07-11 | 2022-07-10 | 2021-10-10 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545939 | T2 DI DEL MONTE-VIEJO 6/144 RPL INSW | 93I
LC | 121706498 | 005/054 | T2 DI COTTONWD-BENTON#2 5/2 CTR KEY | TABLEMTN | ETL.6650.INSL.NCER | 2021-07-10 | 2021-07-07 | 2021-07-29 | 2022-07-07 | 2021-10-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44907402 | T2 DI COTTONWD-BENTON#2 5/2 CTR KEY | ICW
LC | 121706523 | 005/044 | T2 DI TRINITY-CTTNWD 005/044 RPR INSW | TABLEMTN | ETL.4040.INSL.CERA | 2021-07-10 | 2021-07-07 | 2021-07-27 | 2022-07-07 | 2021-10-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44907412 | T2 DI TRINITY-CTTNWD 005/044 RPR INSW | ICW
LC | 121706527 | 004/104 | T3 DI DRUM-SPAULDING 004/104 RPR INSW | SACTO | ETL.6770.INSL.NCER | 2021-07-10 | 2021-07-09 | 2022-05-19 | 2022-01-05 | 2022-01-09 | Late | 630 | Upgraded | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45200576 | T3 DI DRUM-SPAULDING 004/104 RPR INSW | ICW
LC | 121706671 | 031/000 | T2 DI MNDCN-WLLTS-FRT BRG 031/0 COTR KEY | LAKEVLLE | ETL.7550.POLE.NWOD | 2021-07-10 | 2021-07-07 | 2021-07-21 | 2022-07-07 | 2021-10-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44906086 | T2 DI MNDCN-WLLTS-FRT BRG 031/0 COTR KEY | ICW
LC | 121707020 | 007/087B | T2 DI DRUM-SUMMIT#2 007/087B RPR INSW | SACTO | ETL.1450.POLE.NWOD | 2021-07-10 | 2021-07-08 | 2021-09-17 | 2022-07-08 | 2021-10-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44905210 | T2 DI DRUM-SUMMIT#2 007/087B RPR INSW | ICW
LC | 121713998 | 002/030 | T3 DI IGNACIO-BOLINAS #1 2/30 RPL HRDD | LAKEVLLE | ETL.7140.POLE.NWOD | 2021-07-12 | 2021-07-12 | 2021-07-14 | 2022-01-08 | 2021-10-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 44906087 | T3 DI IGNACIO-BOLINAS #1 2/30 RPL HRDD | ICW
LC | 121714926 | 078/003B | T2 DI HUMBOLDT-TRINITY 78/3B RPR INSW | EUREKA | ETL.1820.POLE.NWOD | 2021-07-12 | 2021-07-12 | 2021-09-13 | 2022-07-12 | 2021-10-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44907586 | T2 DI HUMBOLDT-TRINITY 78/3B RPR INSW | ICW
LC | 121715160 | 009/044 | T2 DI BRENTWOOD-KELSO 008/044 HANGER | CONCORD | ETL.4410.INSL | 2021-07-12 | 2021-07-12 | 2021-09-16 | 2022-07-12 | 2021-10-12 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44955070 | T2 DI BRENTWOOD-KELSO 008/044 HANGER | ICQ
LC | 121715443 | 014/322 | T2 DI DRM-GRS VLY-WMR 14/322 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-07-12 | 2021-07-12 | 2021-09-18 | 2022-07-12 | 2021-10-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44921918 | T2 DI DRM-GRS VLY-WMR 14/322 RPR GYWW | ICW
LC | 121715497 | 009/044 | T2 DI BRENTWOOD-KELSO 009/044 RPL INSS | CONCORD | ETL.4410.INSL | 2021-07-12 | 2021-07-12 | 2021-09-16 | 2022-07-12 | 2021-10-12 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546019 | T2 DI BRENTWOOD-KELSO 008/044 RPL INSS | 93K
LC | 121715503 | 012/194 | T3 DI GOLD HILL #1 012/194 COTER KEY | SACTO | ETL.6950.INSL.NCER | 2021-07-12 | 2021-07-12 | 2021-10-09 | 2022-01-08 | 2021-10-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44921919 | T3 DI GOLD HILL #1 012/194 COTER KEY | ICW
LC | 121715524 | 095/008 | T2 DI HUMBOLDT-TRINITY 095/008 RPL HRDD | EUREKA | ETL.1820.INSL.NCER | 2021-07-12 | 2021-07-12 | 2021-08-01 | 2022-07-12 | 2021-10-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 44907507 | T2 DI HUMBOLDT-TRINITY 095/008 RPL HRDD | ICW
LC | 121715674 | 000/009 | T3 DI WST PNT-VLLY SPRGS 0/9 GYW COTR | VICTOR | ETL.8350.POLE.WOOD | 2021-07-12 | 2021-07-12 | 2021-10-09 | 2022-01-08 | 2021-10-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44921273 | T3 DI WST PNT-VLLY SPRGS 0/9 GYW COTR | ICW
LC | 121715874 | 097/001C | T2 DI HUMBOLDT-TRINITY 97/1C COTTER | EUREKA | ETL.1820.INSL.NCER | 2021-07-12 | 2021-07-12 | 2021-08-01 | 2022-07-12 | 2021-10-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44907510 | T2 DI HUMBOLDT-TRINITY 97/1C COTTER | ICW
LC | 121715913 | 052/004 | T2 DI HUMBOLDT-TRINITY 052/004 RPR INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-12 | 2021-07-12 | 2021-07-31 | 2022-07-12 | 2021-10-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44907509 | T2 DI HUMBOLDT-TRINITY 052/004 RPR INSW | ICW
LC | 121716109 | 005/007B | T3 DI DBL UNIT #2 TIE 5/7B RPR INSLS | PISMOBCH | ETL.5950.INSL | 2021-07-12 | 2021-07-12 | 2021-07-20 | 2022-01-08 | 2021-10-10 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44915660 | T3 DI DBL UNIT #2 TIE 5/7B RPR INSLS | ICS
LC | 121717722 | 071/002B | T2 DI HUMBOLDT-TRINITY 71/2B RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-12 | 2021-07-12 | 2021-07-16 | 2022-07-12 | 2021-10-10 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546550 | T2 DI HUMBOLDT-TRINITY 71/2B RPL INSW | 93I
LC | 121719116 | 061/006 | T2 DI HUMBOLDT-TRINITY 61/6 COTTER | EUREKA | ETL.1820.INSL.NCER | 2021-07-13 | 2021-07-12 | 2021-07-12 | 2022-07-12 | 2021-10-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44908485 | T2 DI HUMBOLDT-TRINITY 61/6 COTTER | ICW
LC | 121719413 | 005/066 | T2 DI WST PNT-VLY SPRNGS 5/66 RPR SWTC | VICTOR | ETL.8350.SWIT | 2021-07-13 | 2021-07-12 | 2021-10-08 | 2022-07-12 | 2021-10-12 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | Out of Adjustment | Switch | Repair | 44921274 | T2 DI WST PNT-VLY SPRNGS 5/66 RPR SWTC | ICE
LC | 121719432 | 095/002 | T2 DI HUMBOLDT-TRINITY 95/2 RPL HRDW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-13 | 2021-07-12 | 2021-07-31 | 2022-07-12 | 2021-10-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 44908491 | DI HUMBOLDT-TRINITY 95/2 RPL HRDW | ICW
LC | 121719529 | 097/001A | T2 DI HUMBOLDT-TRINITY 97/1A RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2021-07-13 | 2021-07-12 | 2021-08-01 | 2022-07-12 | 2021-10-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44908490 | T2 DI HUMBOLDT-TRINITY 97/1A RPR INSW | ICW
LC | 121719752 | 074/001A | T2 DI HMBLDT-TRNTY 074/001A RPR INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-13 | 2021-07-12 | 2021-08-01 | 2022-07-12 | 2021-10-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44908488 | T2 DI HMBLDT-TRNTY 074/001A RPR INSW | ICW
LC | 121720402 | 000/002 | T2 DI PIT #6 TAP 0/2 RPR SHLS COTTER | TABLEMTN | ETL.5441.POLE.STPS | 2021-07-13 | 2021-07-12 | 2021-07-26 | 2022-07-12 | 2021-10-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44908433 | T2 DI PIT #6 TAP 0/2 RPR SHLS COTTER | ICW
LC | 121720573 | 095/001 | T2 DI HMBLDT-TRNTY 095/001 RPL HRDD | EUREKA | ETL.1820.POLE.WDPS | 2021-07-13 | 2021-07-13 | 2021-07-31 | 2022-07-13 | 2021-10-13 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 44908484 | DI HMBLDT-TRNTY 095/001 RPL HRDD | ICW
LC | 121720593 | 029/239 | T3 DI RND MTN-CTNWD #3 29/239 COTTER | TABLEMTN | ETL.5650.INSL | 2021-07-13 | 2021-07-13 | 2021-07-25 | 2022-01-09 | 2021-10-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44908297 | T3 DI RND MTN-CTNWD #3 29/239 COTTER | ICS
LC | 121720621 | 003/004 | EI T2 LAURELES-OTTER 3/4 RPR ROAD | MOSSLNDG | ETL.7380.POLE.WDPS | 2021-07-13 | 2021-07-13 | 2021-07-16 | 2022-07-13 | 2021-10-13 | On-time | 932 | B - Urgt Compliance | Closed | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | Brush Fuel | Road | Remove | 44627165 | EI T2NT LAURELES-OTTER 3/001 RPR ROAD | CHS
LC | 121720651 | 066/000 | T2 DI HUMBOLDT-TRINITY 66/0 COTTER | EUREKA | ETL.1820.INSL.CERA | 2021-07-13 | 2021-07-12 | 2021-08-01 | 2022-07-12 | 2021-10-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44908489 | T2 DI HUMBOLDT-TRINITY 66/0 COTTER | ICW
LC | 121721300 | 065/003 | T2 DI HUMBOLDT-TRINITY 65/3 COTTER | EUREKA | ETL.1820.INSL.NCER | 2021-07-13 | 2021-07-12 | 2021-08-01 | 2022-07-12 | 2021-10-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44908487 | T2 DI HUMBOLDT-TRINITY 65/3 COTTER | ICW
LC | 121721481 | 001/024 | T2 DI IGNACIO-LAS GALLINAS 1/24 COTTER | LAKEVLLE | ETL.1860.INSL | 2021-07-13 | 2021-07-12 | 2021-08-20 | 2022-07-12 | 2021-10-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44908481 | T2 DI IGNACIO-LAS GALLINAS 1/24 COTTER | ICW
LC | 121721562 | 001/009 | T3 DI MORAGA-OAKLAND #3 1/9 COTTER | CONCORD | ETL.2740.INSL.NCER | 2021-07-13 | 2021-07-12 | 2021-08-13 | 2022-01-08 | 2021-10-10 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44908196 | T3 DI MORAGA-OAKLAND #3 1/9 COTTER | ICS
LC | 121721672 | 008/003 | T3 DI POTTER VALLEY-WILLITS 8/3 COTR KEY | LAKEVLLE | ETL.7820.INSL | 2021-07-13 | 2021-07-13 | 2021-07-16 | 2022-01-09 | 2021-10-13 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44908480 | T3 DI POTTER VALLEY-WILLITS 8/3 COTR KEY | ICW
LC | 121721678 | 078/000 | T2 DI HUMBOLDT-TRINITY 78/000 COTTER | EUREKA | ETL.1820.INSL.CERA | 2021-07-13 | 2021-07-13 | 2021-08-14 | 2022-07-13 | 2021-10-13 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44908483 | T2 DI HUMBOLDT-TRINITY 78/000 COTTER | ICW
LC | 121721892 | 089/009 | T2 DI HUMBOLDT-TRINITY 089/009 COTTER | EUREKA | ETL.1820.INSL.CERA | 2021-07-13 | 2021-07-13 | 2021-07-31 | 2022-07-13 | 2021-10-11 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44908494 | T2 DI HUMBOLDT-TRINITY 089/009 COTTER | ICW
LC | 121721900 | 085/006 | T2 DI HUMBOLDT-TRINITY 85/006 COTTER | EUREKA | ETL.1820.INSL.NCER | 2021-07-13 | 2021-07-13 | 2021-07-31 | 2022-07-13 | 2021-10-11 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44908493 | T2 DI HUMBOLDT-TRINITY 85/006 COTTER | ICW
LC | 121722803 | 057/006 | T2 DI HUMBOLDT-TRNTY 57/6 RPR GYWW CTTR | EUREKA | ETL.1820.POLE.WDPS | 2021-07-13 | 2021-07-12 | 2021-08-01 | 2022-07-12 | 2021-10-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44908482 | T2 DI HUMBOLDT-TRNTY 57/6 RPR GYWW CTTR | ICW
LC | 121723056 | 071/360 | T2 DI MALIN-RND MTN #2 71/360 RPR INSLS | TABLEMTN | ETL.6020.INSL | 2021-07-13 | 2021-07-12 | 2021-07-15 | 2022-07-12 | 2021-10-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44908281 | T2 DI MALIN-RND MTN #2 71/360 RPR INSLS | ICS
LC | 121723415 | 000/008 | T3 DI WST PNT-VLLY SPRGS 0/8 GYW COTR | VICTOR | ETL.8350.POLE.WOOD | 2021-07-13 | 2021-07-12 | 2021-08-31 | 2022-01-08 | 2021-10-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44921278 | T3 DI WST PNT-VLLY SPRGS 0/8 GYW COTR | ICW
LC | 121724306 | 020/102 | T3 DI RND MNT-TBLE MT#2 20/102 RPR INSLS | TABLEMTN | ETL.6070.INSL | 2021-07-13 | 2021-07-09 | 2021-09-13 | 2022-01-05 | 2021-10-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44908360 | T3 DI RND MNT-TBLE MT#2 20/102 RPR INSLS | ICS
LC | 121724494 | 004/022 | T2 DI MSS LNDNG-MTCLF 4/22 RPR SHLDWS | MOSSLNDG | ETL.6050.TOWR | 2021-07-13 | 2021-07-13 | 2021-07-19 | 2022-07-13 | 2021-10-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44908925 | T2 DI MSS LNDNG-MTCLF 4/22 RPR SHLDWS | ICS
LC | 121724541 | 003/024 | T3 DI SOBRANTE "R" "#1+" 3/24 COTTER | CONCORD | ETL.3770.INSL | 2021-07-13 | 2021-07-13 | 2021-08-13 | 2022-01-09 | 2021-10-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44908195 | T3 DI SOBRANTE "R" "#1+" 3/24 COTTER | ICS
LC | 121724689 | 095/006 | T2 HUMBOLDT-TRITY-WD POLE 95/6 INSW RPL | EUREKA | ETL.1820.INSL.CERA | 2021-07-13 | 2021-07-13 | 2021-08-01 | 2022-07-13 | 2021-10-13 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31549074 | T2 HUMBOLDT-TRITY-WD POLE 95/6 INSW RPL | 93I
LC | 121724731 | 019/451 | T2 DI DRM GRSS VLY-WIMR 19/451 RPR INSW | SACTO | ETL.6760.INSL.CERA | 2021-07-13 | 2021-07-13 | 2021-09-22 | 2022-07-13 | 2021-10-13 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44921920 | T2 DI DRM GRSS VLY-WIMR 19/451 RPR INSW | ICW
LC | 121724761 | 095/006 | T2 HUMBOLDT-TRITY-WD POLE 95/6 HRDW RPL | EUREKA | ETL.1820.POLE.WDPS | 2021-07-13 | 2021-07-13 | 2021-08-01 | 2022-07-13 | 2021-10-13 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 44907260 | T2 HUMBOLDT-TRITY-WD POLE X95/6 HRDW RPL | IBE
LC | 121724763 | 009/090 | T2 DI COTTONWOOD-BENTON #2 9/90 RPR INSW | TABLEMTN | ETL.6650.INSL.NCER | 2021-07-13 | 2021-07-13 | 2021-07-29 | 2022-07-13 | 2021-10-13 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44908361 | T2 DI COTTONWOOD-BENTON #2 9/90 RPR INSW | ICW
LC | 121725121 | 008/086 | T2 DI PIT #5-RND MTN #1 8/086R RPL STRW | TABLEMTN | ETL.5420.POLE.WOOD | 2021-07-13 | 2021-07-09 | 2021-09-28 | 2022-07-09 | 2021-10-09 | On-time | 372 | Upgraded | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545613 | T2 PIT #5-ROUND MTN #1 11/112R RPL POLE | 70Y
LC | 121725921 | 187 | T2 MI-WUK-CURTIS-SWITCH 26/4 RPR SWTC | VICTOR | ETL.1073.SWIT | 2021-07-14 | 2021-07-14 | 2021-07-14 | 2022-07-14 | 2021-10-14 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | Out of Adjustment | Switch | Repair | 44907493 | MI-WUK-CURTIS-SWITCH 26/4 RPR SWTC | ICE
LC | 121725933 | 071/002B | T2 HUMBOLDT-TRINITY 71/002B RPL IBWW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-14 | 2021-07-14 | 2021-07-16 | 2022-07-14 | 2021-10-14 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Replace | 44908492 | T2 HUMBOLDT-TRINITY 71/002B RPL IBWW | ICW
LC | 121725964 | 057/006 | T2 HUMBOLDT-TRINITY 57/6C RPR IBWW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-14 | 2021-07-14 | 2021-08-01 | 2022-07-14 | 2021-10-14 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 44911942 | T2 HUMBOLDT-TRINITY 57/6C RPR IBWW | ICW
LC | 121725981 | 057/006 | T2 HUMBOLDT-TRINITY 57/6L RPR IBWW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-14 | 2021-07-14 | 2021-08-01 | 2022-07-14 | 2021-10-14 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 44911685 | T2 HUMBOLDT-TRINITY 57/6L RPR IBWW | ICW
LC | 121725995 | 001/013 | T2 DI PIT #5-ROUND MTN #1 1/13 COTTER | TABLEMTN | ETL.5420.INSL.NCER | 2021-07-14 | 2021-07-13 | 2021-07-23 | 2022-07-13 | 2021-10-11 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44910601 | T2 DI PIT #5-ROUND MTN #1 1/13 COTTER | ICW
LC | 121726527 | 005/063 | T2 DI PIT #5-ROUND MTN #2 5/63 RPR INSW | TABLEMTN | ETL.5430.INSL.NCER | 2021-07-14 | 2021-07-09 | 2021-07-26 | 2022-07-09 | 2021-10-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44910602 | T2 DI PIT #5-ROUND MTN #2 5/63 RPR INSW | ICW
LC | 121726529 | 014/123 | T2 DI COTTONWD-BENTON #2 14/123 COTTER | TABLEMTN | ETL.6650.INSL.NCER | 2021-07-14 | 2021-07-13 | 2021-08-27 | 2022-07-13 | 2021-10-11 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44909677 | T2 DI COTTONWD-BENTON #2 14/123 COTTER | ICW
LC | 121726974 | 074/001B | T2 DI HUMBOLDT-TRINITY 074/001B RPR INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-14 | 2021-07-12 | 2021-08-01 | 2022-07-12 | 2021-10-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44911684 | T2 DI HUMBOLDT-TRINITY 074/001B RPR INSW | ICW
LC | 121727337 | 002/022 | T2 DI PIT #5-ROUND MTN #2 2/22 RPL DAMW | TABLEMTN | ETL.5430.POLE.STPS | 2021-07-14 | 2021-07-13 | 2021-07-26 | 2022-07-13 | 2021-10-11 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace | 44910603 | T2 DI PIT #5-ROUND MTN #2 2/22 RPL DAMW | ICW
LC | 121728401 | 008/147 | T2 EI TEJON-LEBEC 8/147 RPR CNDW | MIDWAY | ETL.9250.INSL.CERA | 2021-07-14 | 2021-07-14 | 2021-08-12 | 2022-07-14 | 2021-10-14 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair | 44912001 | T2 EI TEJON-LEBEC 8/148 RPR CNDW | ICW
LC | 121729536 | 002/025 | T2 NARROWS #1 TAP 002/025 RPR GYWW | SACTO | ETL.6511.POLE.WDPS | 2021-07-14 | 2021-07-14 | 2021-07-21 | 2022-07-14 | 2021-10-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44915996 | T2 NARROWS #1 TAP 002/025 RPR GYWW | ICW
LC | 121729563 | 015/116A | T2 DI CARIBOU-TABLE MTN 15/116A RPR SWTC | TABLEMTN | ETL.4440.TOWR | 2021-07-14 | 2021-07-13 | 2021-08-28 | 2022-07-13 | 2021-10-13 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR FRAB | Out of Adjustment | Switch | Repair | 44947702 | T2 DI CARIBOU-TABLE MTN 15/116A RPR SWTC | ICE
LC | 121730037 | 003/024 | T3 DI SOBRANTE-"G"#1" 003/024 RPR INSS | CONCORD | ETL.3730.INSL.CERA | 2021-07-14 | 2021-07-13 | 2021-08-13 | 2022-01-09 | 2021-10-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44923493 | T3 DI SOBRANTE-"G"#1" 003/024 RPR INSS | ICS
LC | 121730342 | 009/094 | T3 DI GRN VLLY-PAUL SWT 9/94 GUY COTTER | MOSSLNDG | ETL.1730.POLE.WDPS | 2021-07-14 | 2021-07-14 | 2021-07-22 | 2022-01-10 | 2021-10-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44911956 | T3 DI GRN VLLY-PAUL SWT 9/94 GUY COTTER | ICW
LC | 121730348 | 003/026 | T3 DI GRN VLLY-LLAGAS 003/026 COTTER | MOSSLNDG | ETL.1720.INSL.CERA | 2021-07-14 | 2021-07-14 | 2021-07-22 | 2022-01-10 | 2021-10-14 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44911958 | T3 DI GRN VLLY-LLAGAS 003/026 COTTER | ICW
LC | 121730967 | 003/091 | T2 DI HAMLTN-BRNCH CHESTER 3/91 COTR KEY | TABLEMTN | ETL.7000.INSL.CERA | 2021-07-14 | 2021-07-13 | 2021-07-22 | 2022-07-13 | 2021-10-13 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44910600 | T2 DI HAMLTN-BRNCH CHESTER 3/91 COTR KEY | ICW
LC | 121731491 | 074/374 | T2 DI MALIN-ROUND MTN #2 74/374 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-14 | 2021-07-13 | 2021-08-03 | 2022-07-13 | 2021-10-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44909679 | T2 DI MALIN-ROUND MTN #2 74/374 RPR OPGW | ICS
LC | 121731565 | 075/002A | T2 DI HUMBOLT-TRINITY 075/002A RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2021-07-14 | 2021-07-12 | 2021-08-01 | 2022-07-12 | 2021-10-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44911940 | T2 DI HUMBOLT-TRINITY 075/002A RPR INSW | ICW
LC | 121731641 | 070/353 | T2 DI MALIN-RND MTN #2 70/353 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-14 | 2021-07-14 | 2021-08-30 | 2022-07-14 | 2021-10-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44909678 | T2 DI MALIN-RND MTN #2 70/353 RPR OPGW | ICS
LC | 121731697 | 008/151 | T2 DI TEJON-LEBEC 8/151 INS COTR KEY | MIDWAY | ETL.9250.INSL | 2021-07-14 | 2021-07-14 | 2021-08-12 | 2022-07-14 | 2021-10-14 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44923306 | T2 DI TEJON-LEBEC 8/151 INS COTR KEY | ICW
LC | 121731806 | 009/161 | T2 DI TEJON-LEBEC 009/161 RPR INSW | MIDWAY | ETL.9250.INSL | 2021-07-14 | 2021-07-14 | 2021-08-25 | 2022-07-14 | 2021-10-14 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44923421 | T2 DI TEJON-LEBEC 009/161 RPR INSW | ICW
LC | 121731982 | 015/011 | T2 DI CARIBOU #12 015/011 RPR SPLW | TABLEMTN | ETL.6280.INSL | 2021-07-14 | 2021-07-14 | 2021-10-08 | 2022-07-14 | 2021-10-14 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 44915821 | T2 DI CARIBOU #12 015/011 RPR SPLW | ICW
LC | 121733224 | 000/008 | T2 DI PIT #5-ROUND MTN #1 0/8 COTTER | TABLEMTN | ETL.5420.POLE.STPS | 2021-07-15 | 2021-07-14 | 2021-07-27 | 2022-07-14 | 2021-10-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44915736 | T2 DI PIT #5-ROUND MTN #1 0/8 COTTER | ICS
LC | 121733475 | 004/053 | T3 DI DRUM-RIO OSO #1 4/53 RPR STRT | SACTO | ETL.1420.TOWR | 2021-07-15 | 2021-07-14 | 2021-07-27 | 2022-01-10 | 2021-10-12 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Tower | Repair | 44921922 | T3 DI DRUM-RIO OSO #1 4/53 RPR STRT | ICQ
LC | 121733931 | 011/075 | T2 DI CTTNWD-DELEVAN #1 11/75 COTTER | TABLEMTN | ETL.4550.INSL | 2021-07-15 | 2021-07-14 | 2021-09-11 | 2022-07-14 | 2021-10-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44915733 | T2 DI CTTNWD-DELEVAN #1 11/75 COTTER | ICS
LC | 121734029 | 084/001 | T2 DI HUMBOLDT-TRINITY 84/1 COTTER | EUREKA | ETL.1820.INSL | 2021-07-15 | 2021-07-12 | 2021-07-31 | 2022-07-12 | 2021-10-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44912175 | T2 DI HUMBOLDT-TRINITY 84/1 COTTER | ICW
LC | 121734218 | 009/157 | T2 DI TEJON-LEBEC 9/157 RPR INSW | MIDWAY | ETL.9250.INSL.NCER | 2021-07-15 | 2021-07-14 | 2021-08-12 | 2022-07-14 | 2021-10-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44923422 | T2 DI TEJON-LEBEC 9/157 RPR INSW | ICS
LC | 121734340 | 079/001 | T2 DI HUMBOLDT-TRINITY 079/001 COTTER | EUREKA | ETL.1820.INSL | 2021-07-15 | 2021-07-14 | 2021-08-14 | 2022-07-14 | 2021-10-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44912174 | T2 DI HUMBOLDT-TRINITY 079/001 COTTER | ICS
LC | 121734443 | 109/003 | T2 DI HUMBOLT-TRINITY 109/3 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-15 | 2021-07-12 | 2021-07-31 | 2022-07-12 | 2021-10-12 | On-time | 508 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546782 | T2 DI HUMBOLT-TRINITY 109/3 RPL INSW | 93I
LC | 121735020 | 095/005 | T2 DI HUMBOLDT-TRINITY 095/005 RPL HRDW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-15 | 2021-07-13 | 2021-08-01 | 2022-07-13 | 2021-10-13 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 44911941 | DI HUMBOLDT-TRINITY 095/005 RPL HRDW | ICW
LC | 121735024 | 008/086 | T2 DI PIT #5-RND MTN #1 8/086C RPL STRW | TABLEMTN | ETL.5420.POLE.WOOD | 2021-07-15 | 2021-07-09 | 2021-09-28 | 2022-07-09 | 2021-10-09 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545613 | T2 PIT #5-ROUND MTN #1 11/112R RPL POLE | 70Y
LC | 121736142 | 010/040 | T3 DI PITTSBURG-SAN RAMON 10/40 RPR INSS | CONCORD | ETL.5470.INSL | 2021-07-15 | 2021-07-14 | 2021-08-13 | 2022-01-10 | 2021-10-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44923375 | T3 DI PITTSBURG-SAN RAMON 10/40 RPR INSS | ICS
LC | 121741221 | 072/365A | T2 DI MALIN-RUND MTN #2 72/365A RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-07-16 | 2021-07-14 | 2021-08-03 | 2022-07-14 | 2021-10-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44915729 | T2 DI MALIN-RUND MTN #2 72/365A RPR INSS | ICS
LC | 121741318 | 073/372 | T2 DI MALIN-RD MTN #2 073/372 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-07-16 | 2021-07-14 | 2021-08-30 | 2022-07-14 | 2021-10-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44916650 | T2 DI MALIN-RD MTN #2 073/372 RPR INSS | ICS
LC | 121741896 | 007/133 | T2 DI VALLEY SPRINGS #2 7/133L RPL HDWW | VICTOR | ETL.9460.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2021-10-01 | 2022-07-13 | 2021-10-13 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 44921279 | T2 DI VALLEY SPRINGS #2 7/133L RPL HDWW | ICW
LC | 121742023 | 000/006 | T2 FULTON-CALISTOGA -00/006 RPL CRSMW | LAKEVLLE | ETL.6880.POLE.WOOD | 2021-07-16 | 2021-07-16 | 2021-07-22 | 2022-07-16 | 2021-10-16 | On-time | 637 | B - Urgt Compliance | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31546523 | T2 FULTON-CALISTOGA -00/006 RPL CRSMW | 93E
LC | 121744076 | 000/010 | T2 DI MELONES-CURTIS 0/10 RPL INSW | VICTOR | ETL.2390.INSL.CERA | 2021-07-16 | 2021-07-13 | 2021-10-13 | 2022-07-13 | 2021-11-04 | On-time | 508 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31548887 | T2 DI MELONES-CURTIS 0/10 RPL INSW | 93I
LC | 121744078 | 000/010 | T2 DI MELONES-CURTIS 0/10 RPL HRDW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 | 2021-10-13 | 2022-07-13 | 2021-11-04 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 44934755 | T2 DI MELONES-CURTIS 0/10 RPL HRDW | ICW
LC | 121745187 | 004/055 | T3 DI WP-VLY SPRGS 4/55L RPL STRW | VICTOR | ETL.8350.POLE.WDPS | 2021-07-16 | 2021-07-14 | 2022-05-22 | 2022-01-10 | 2022-01-14 | Late | 372 | Upgraded | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579997 | T3 DI WP-VALLEY SPRINGS 0/2 RPL STRW | 70Y
LC | 121745232 | 004/055 | T3 DI WP-VLY SPRGS 4/55C RPL STRW | VICTOR | ETL.8350.POLE.WDPS | 2021-07-16 | 2021-07-14 | 2022-05-22 | 2022-01-10 | 2022-01-14 | Late | 372 | Upgraded | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579997 | T3 DI WP-VALLEY SPRINGS 0/2 RPL STRW | 70Y
LC | 121745234 | 004/055 | T3 DI WP-VLY SPRGS 4/55R RPL STRW | VICTOR | ETL.8350.POLE.WDPS | 2021-07-16 | 2021-07-14 | 2022-05-22 | 2022-01-10 | 2022-01-14 | Late | 372 | Upgraded | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579997 | T3 DI WP-VALLEY SPRINGS 0/2 RPL STRW | 70Y
LC | 121745636 | 106/001A | T2 DI HUMBLT-TRINITY 106/001A COTTER | EUREKA | ETL.1820.POLE.NWOD | 2021-07-16 | 2021-07-15 | 2021-07-31 | 2022-07-15 | 2021-10-13 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44914081 | T2 DI HUMBLT-TRINITY 106/001A COTTER | ICW
LC | 121745704 | 001/009A | T3DI GRZLY TAP-SNTCLRA 01/09A COTR KEY | TABLEMTN | ETL.2395.INSL.CERA | 2021-07-16 | 2021-07-15 | 2021-10-06 | 2022-01-11 | 2021-10-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44915735 | T3DI GRZLY TAP-SNTCLRA 01/09A COTR KEY | ICW
LC | 121745802 | 002/031 | T2 DI PIT#5-ROUND MTN#2 002/031 COTR KEY | TABLEMTN | ETL.5430.POLE.STPS | 2021-07-16 | 2021-07-14 | 2021-07-23 | 2022-07-14 | 2021-10-14 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44915823 | T2 DI PIT#5-ROUND MTN#2 002/031 COTR KEY | ICW
LC | 121746219 | 070/355A | T2 DI MALIN-ROUND MTN#2 70/355A RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-07-16 | 2021-07-16 | 2021-08-05 | 2022-07-16 | 2021-10-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44915730 | T2 DI MALIN-ROUND MTN#2 70/355A RPR SHLS | ICS
LC | 121746268 | 001/009B | T3DI GRIZLYTAP-SNTACLRA)1/9B COTR KEY | TABLEMTN | ETL.2395.INSL.CERA | 2021-07-16 | 2021-07-15 | 2021-10-06 | 2022-01-11 | 2021-10-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44915732 | T3DI GRIZLYTAP-SNTACLRA)1/9B COTR KEY | ICW
LC | 121746871 | 001/011C | T3 DI GEYSERS #3-CLOVRDL 1/11C COTTER | LAKEVLLE | ETL.1650.POLE.NWOD | 2021-07-16 | 2021-07-15 | 2021-10-13 | 2022-01-11 | 2021-10-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44914084 | T3 DI GEYSERS #3-CLOVRDL 1/11C COTTER | ICS
LC | 121746913 | 002/022 | T2 DI PIT #5-ROUND MTN #1 02/22 RPR SHLW | TABLEMTN | ETL.5420.POLE.STPS | 2021-07-16 | 2021-07-13 | 2021-07-26 | 2022-07-13 | 2021-10-13 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44915825 | T2 DI PIT #5-ROUND MTN #1 02/22 RPR SHLW | ICW
LC | 121746936 | 003/010 | T3 DI WISHN-SN JOAQUIN #3 3/10A RPR INSW | FRESNO | ETL.9340.SWIT | 2021-07-16 | 2021-07-15 | 2021-08-18 | 2022-01-11 | 2021-10-13 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44923386 | T3 DI WISHN-SN JOAQUIN #3 3/10A RPR INSW | ICW
LC | 121746980 | 009/162 | T2 DI TEJON-LEBEC 009/162 COTTER | MIDWAY | ETL.9250.INSL.NCER | 2021-07-16 | 2021-07-14 | 2021-08-25 | 2022-07-14 | 2021-10-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44923307 | T2 DI TEJON-LEBEC 009/162 COTTER | ICW
LC | 121748236 | 068/347A | T2 DI MALIN-ROUND MTN#2 68/347A RPR INSS | TABLEMTN | ETL.6020.TOWR | 2021-07-17 | 2021-07-16 | 2021-08-30 | 2022-07-16 | 2021-10-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Repair | 44915829 | T2 DI MALIN-ROUND MTN#2 68/347A RPR INSS | ICS
LC | 121748472 | 070/356 | T2 DI MALIN-RND MTN #2 070/356 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-07-17 | 2021-07-16 | 2021-08-05 | 2022-07-16 | 2021-10-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44915734 | T2 DI MALIN-RND MTN #2 070/356 RPR INSS | ICS
LC | 121748473 | 070/356 | T2 DI MALIN-RND MTN #2 070/356 RPR SHLDS | TABLEMTN | ETL.6020.TOWR | 2021-07-17 | 2021-07-16 | 2021-08-05 | 2022-07-16 | 2021-10-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44915824 | T2 DI MALIN-RND MTN #2 070/356 RPR SHLDS | ICS
LC | 121748818 | 069/350 | T2 DI MALIN-RND MTN #2 069/350 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-07-17 | 2021-07-16 | 2021-08-30 | 2022-07-16 | 2021-10-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44915731 | T2 DI MALIN-RND MTN #2 069/350 RPR INSS | ICS
LC | 121748868 | 000/002 | T3 DI MIDDLE FORK #1 000/002 RPL SPLW | SACTO | ETL.8405.INSL.NCER | 2021-07-17 | 2021-07-17 | 2021-09-13 | 2022-01-13 | 2021-10-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Replace | 44921926 | T3 DI MIDDLE FORK #1 000/002 RPL SPLW | ICW
LC | 121749132 | 069/000B | T2 DI HUMBLT-TRINTY 069/000B COTTER | EUREKA | ETL.1820.POLE.NWOD | 2021-07-17 | 2021-07-15 | 2021-08-01 | 2022-07-15 | 2021-10-13 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44914082 | T2 DI HUMBLT-TRINTY 069/000B COTTER | ICW
LC | 121749230 | ?003/002 | T3 DI SNEATH LN-HLFMN BY ?3/2 COTTER | METCALF | ETL.7212.INSL.NCER | 2021-07-17 | 2021-07-17 | 2021-08-09 | 2022-01-13 | 2021-10-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44921565 | T3 DI SNEATH LN-HLFMN BY ?3/2 COTTER | ICW
LC | 121749449 | 071/358B | T2 DI MALIN-RD MTN #2 071/358B RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-17 | 2021-07-17 | 2021-08-05 | 2022-07-17 | 2021-10-17 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE ACCM COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44922549 | T2 DI MALIN-RD MTN #2 071/358B RPR OPGW | ICS
LC | 121749526 | 066/331 | T2 DI MALIN-ROUND MTN #2 66/331 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-07-17 | 2021-07-17 | 2021-08-25 | 2022-07-17 | 2021-10-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44915820 | T2 DI MALIN-ROUND MTN #2 66/331 RPR INSS | ICS
LC | 121749732 | ?003/009 | T3 DI SNTH LN-HF MN BY ?003/009 COTTER | METCALF | ETL.7212.INSL.NCER | 2021-07-17 | 2021-07-17 | 2021-08-09 | 2022-01-13 | 2021-10-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44921566 | T3 DI SNTH LN-HF MN BY ?003/009 COTTER | ICW
LC | 121749878 | 045/184 | T2 DI DIABLO-MIDWAY #2 45/184 RPR INSS | PISMOBCH | ETL.5970.INSL | 2021-07-17 | 2021-07-17 | 2021-08-24 | 2022-07-17 | 2021-10-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44923733 | T2 DI DIABLO-MIDWAY #2 45/184 RPR INSS | ICS
LC | 121750054 | ?003/003 | T3 DI SNEATH LN-HLF ?003/003 COTTER | METCALF | ETL.7212.INSL.CERA | 2021-07-17 | 2021-07-17 | 2021-08-09 | 2022-01-13 | 2021-10-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44921563 | T3 DI SNEATH LN-HLF ?003/003 COTTER | ICW
LC | 121752791 | 000/001 | T2 DI HMLTN BRNCH-CHSTR 0/1 RPR INSS | TABLEMTN | ETL.7000.INSL.CERA | 2021-07-19 | 2021-07-17 | 2021-07-22 | 2022-07-17 | 2021-10-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44915728 | T2 DI HMLTN BRNCH-CHSTR 0/1 RPR INSS | ICW
LC | 121752973 | 020/002 | T3 DI MAPLE CREEK-HOOPA 020/002 COTTER | EUREKA | ETL.7490.INSL | 2021-07-19 | 2021-07-19 | 2021-08-28 | 2022-01-15 | 2021-10-19 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44915672 | T3 DI MAPLE CREEK-HOOPA 020/002 COTTER | ICW
LC | 121754585 | B041/332R | T2 DI BRIDGVLLE-CTTNWD B41/332R COTTER | TABLEMTN | ETL.1110.INSL.CERA | 2021-07-19 | 2021-07-19 | 2021-09-02 | 2022-07-19 | 2021-10-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44915830 | T2 DI BRIDGVLLE-CTTNWD B41/332R COTTER | ICW
LC | 121758786 | 007/016 | T2 CARIBOU #2 7/016 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-19 | 2021-07-19 | 2021-08-28 | 2022-07-19 | 2021-10-19 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31546788 | T2 CARIBOU #2 - 60 KV_007/004 | 92F
LC | 121759544 | 014/014 | EI T3 ETLI00001023 14/014 RPR SWITCH | LAKEVLLE | ETL.7630.SWIT | 2021-07-19 | 2021-07-19 | 2021-08-13 | 2022-01-15 | 2021-10-19 | On-time | 630 | Upgraded | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 | No Good/Out of Stdrd | Switch-Wood | Repair | 44916942 | EI T3 ETLI00001023 14/014 RPR SWITCH | ICW
LC | 121760022 | 023/272 | T2 DI DRUM-SUMMIT #1 023/272 COTTER | SACTO | ETL.1440.INSL | 2021-07-20 | 2021-07-19 | 2021-09-10 | 2022-07-19 | 2021-10-19 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44921924 | T2 DI DRUM-SUMMIT #1 023/272 COTTER | ICW
LC | 121760133 | 022/259 | T2 DI DRUM-SUMMIT #1 022/259 COTTER | SACTO | ETL.1440.INSL | 2021-07-20 | 2021-07-19 | 2021-09-10 | 2022-07-19 | 2021-10-19 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44921923 | T2 DI DRUM-SUMMIT #1 022/259 COTTER | ICW
LC | 121760926 | 070/354A | T2 DI MALIN-RND MTN #2 70/354A RPR SHLWS | TABLEMTN | ETL.6020.TOWR | 2021-07-20 | 2021-07-16 | 2021-08-05 | 2022-07-16 | 2021-10-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44916649 | T2 DI MALIN-RND MTN #2 70/354A RPR SHLWS | ICS
LC | 121761831 | 007/034 | T2 DI PITTSBURG-TESLA #1 7/34 COTTER | CONCORD | ETL.5510.INSL.CERA | 2021-07-20 | 2021-07-19 | 2021-08-10 | 2022-07-19 | 2021-10-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44923377 | T2 DI PITTSBURG-TESLA #1 7/34 COTTER | ICS
LC | 121762188 | 089/006 | T2 DI HUMBOLDT-TRINITY 89/6 COTTER | EUREKA | ETL.1820.INSL.CERA | 2021-07-20 | 2021-07-19 | 2021-07-31 | 2022-07-19 | 2021-10-19 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44916940 | T2 DI HUMBOLDT-TRINITY 89/6 COTTER | ICW
LC | 121762635 | 001/009 | T3 DI DIABLO-MIDWAY #2 1/9 RPR INSLS | PISMOBCH | ETL.5970.INSL.NCER | 2021-07-20 | 2021-07-19 | 2021-07-22 | 2022-01-15 | 2021-10-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44917283 | T3 DI DIABLO-MIDWAY #2 1/9 RPR INSLS | ICS
LC | 121763006 | 009/103 | T2 DRUM-SUMMIT #2 9/103 RPR SWTC | SACTO | ETL.1450.TOWR | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2022-07-20 | 2021-10-20 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 | Out of Adjustment | Switch | Repair | 44913895 | T2 DRUM-SUMMIT #2 9/103 RPR SWTC | ICE
LC | 121763227 | T056 | T3 DI MIDWAY-SANTA MARIA T056 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-20 | 2021-07-19 | 2022-01-18 | 2022-01-15 | 2021-10-19 | Late | 532 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31547428 | T3 DI MIDWAY-SANTA MARIA T056 RPL INSS | 93K
LC | 121764001 | 003/037B | T3 DI IGNACIO-BOLINAS #1 3/37 COTTER | LAKEVLLE | ETL.7140.INSL.NCER | 2021-07-20 | 2021-07-19 | 2021-08-17 | 2022-01-15 | 2021-10-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44916941 | T3 DI IGNACIO-BOLINAS #1 3/37 COTTER | ICW
LC | 121766651 | 016/226 | T2 VALLEY SPRINGS-CLAY 16/226 GUY COTTER | VICTOR | ETL.8264.POLE.WOOD | 2021-07-21 | 2021-06-12 | 2021-08-21 | 2022-06-12 | 2021-09-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44921360 | T2 VALLEY SPRINGS-CLAY 16/226 GUY COTTER | ICW
LC | 121766659 | T-104 | T3 DI MIDWAY-SANTA MARIA T-104 COTTER | PISMOBCH | ETL.9240.POLE.WOOD | 2021-07-21 | 2021-07-19 | 2021-07-22 | 2022-01-15 | 2021-10-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44915990 | T3 DI MIDWAY-SANTA MARIA T-104 COTTER | ICW
LC | 121766785 | T082 | T3 DI MIDWAY-SANTA MARIA T082 BENT STEEL | PISMOBCH | ETL.9240.TOWR | 2021-07-21 | 2021-07-19 | 2021-09-21 | 2022-01-15 | 2021-10-17 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Tower | Repair | 44923736 | T3 DI MIDWAY-SANTA MARIA T082 BENT STEEL | ICQ
LC | 121769052 | 068/346 | T2 DI MALIN-ROUND MTN #2 68/346 RPR INSS | TABLEMTN | ETL.6020.INSL | 2021-07-21 | 2021-07-19 | 2021-08-30 | 2022-07-19 | 2021-10-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44918681 | T2 DI MALIN-ROUND MTN #2 68/346 RPR INSS | ICS
LC | 121769441 | 022/009 | T2 DI CPPRMINE-TIVY VLLY 22/9 COTTER | FRESNO | ETL.8590.INSL.NCER | 2021-07-21 | 2021-07-20 | 2021-08-26 | 2022-07-20 | 2021-10-18 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44923390 | T2 DI CPPRMINE-TIVY VLLY 22/9 COTTER | ICW
LC | 121769898 | 018/074 | T2 DI GEYSRS #17-FLTN 018/074 COTR KEY | LAKEVLLE | ETL.4770.INSL.CERA | 2021-07-21 | 2021-07-14 | 2021-08-19 | 2022-07-14 | 2021-10-14 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44918566 | T2 DI GEYSRS #17-FLTN 018/074 COTR KEY | ICW
LC | 121770349 | 005/001 | T2 DI MELONES-CURTIS 005/001 COTR KEY | VICTOR | ETL.2390.INSL.CERA | 2021-07-21 | 2021-07-20 | 2021-09-01 | 2022-07-20 | 2021-10-20 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44921361 | T2 DI MELONES-CURTIS 005/001 COTR KEY | ICW
LC | 121770514 | 017/003 | T2 DI LAYTONVLL-WILLITS 17/3 GUY COTTER | LAKEVLLE | ETL.8360.POLE.WDPS | 2021-07-21 | 2021-07-20 | 2021-07-28 | 2022-07-20 | 2021-10-18 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44918565 | T2 DI LAYTONVLL-WILLITS 17/3 GUY COTTER | ICW
LC | 121771968 | 012/146 | T2 DI DRUM-SUMMIT #1 012/146L GUY COTR | SACTO | ETL.1440.POLE.STPS | 2021-07-21 | 2021-07-19 | 2021-09-10 | 2022-07-19 | 2021-10-19 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44921925 | T2 DI DRUM-SUMMIT #1 012/146L GUY COTR | ICW
LC | 121772111 | 007/085 | T2 DI VEDDAR TAP 007/085 COTR KEY | MIDWAY | ETL.2141.INSL.CERA | 2021-07-21 | 2021-07-20 | 2021-08-12 | 2022-07-20 | 2021-10-20 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44922646 | T2 DI VEDDAR TAP 007/085 COTR KEY | ICW
LC | 121772119 | 004/049 | T2 DI HLLDL JCT HLF MN BY 4/49 RPR INSW | METCALF | ETL.7060.INSL.CERA | 2021-07-21 | 2021-07-21 | 2021-10-05 | 2022-07-21 | 2021-10-19 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44923378 | T2 DI HLLDL JCT HLF MN BY 4/49 RPR INSW | ICW
LC | 121777196 | 015/003 | T2 DI LAYTONVILLE-WILLITS 15/3R RPR GYWW | LAKEVLLE | ETL.8360.POLE.STPS | 2021-07-22 | 2021-07-20 | 2021-07-28 | 2022-07-20 | 2021-10-20 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44921373 | T2 DI LAYTONVILLE-WILLITS 15/3R RPR GYWW | ICW
LC | 121777622 | 007/007A | T2 DI MELONES-CURTIS 007/007AR RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2021-10-14 | 2022-07-20 | 2021-10-20 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31548238 | T2 DI MELONES-CURTIS 007/007AR RPL STRW | 70Y
LC | 121778926 | T084 | T3 DI MIDWAY-SANTA MARIA T084 RPL SPLS | PISMOBCH | ETL.9240.TOWR | 2021-07-22 | 2021-07-19 | 2021-09-21 | 2022-01-15 | 2021-10-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Replace | 44923737 | T3 DI MIDWAY-SANTA MARIA T084 RPL SPLS | ICS
LC | 121778929 | 012/009 | T2 DI MELONES-CURTIS 012/009 RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-11-02 | 2022-07-20 | 2022-07-20 | Late | 372 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31596146 | T2 DI MELONES-CURTIS 012/009 RPL STRW | 70Y
LC | 121779240 | 012/009 | T2 DI MELONES-CURTIS 012/009 RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-22 | 2021-07-20 | 2022-11-02 | 2022-07-20 | 2022-07-20 | Late | 372 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31596146 | T2 DI MELONES-CURTIS 012/009 RPL STRW | 70Y
LC | 121779244 | 012/009 | T2 DI MELONES-CURTIS 012/009 COTR KEY | VICTOR | ETL.2390.INSL.CERA | 2021-07-22 | 2021-07-20 | 2021-08-14 | 2022-07-20 | 2021-10-20 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44923319 | T2 DI MELONES-CURTIS 012/009 COTR KEY | ICW
LC | 121780888 | 025/295 | T2 DI DRUM-SUMMIT #1 025/295 RPR INSW | SACTO | ETL.1440.INSL | 2021-07-22 | 2021-07-21 | 2021-09-28 | 2022-07-21 | 2021-10-19 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44923996 | T2 DI DRUM-SUMMIT #1 025/295 RPR INSW | ICW
LC | 121781019 | 047/233 | T2 DI MALIN-ROUND MTN #2 47/233 RPR INSS | TABLEMTN | ETL.6020.INSL.CERA | 2021-07-22 | 2021-07-20 | 2021-08-25 | 2022-07-20 | 2021-10-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44922551 | T2 DI MALIN-ROUND MTN #2 47/233 RPR INSS | ICS
LC | 121781038 | 074/375A | T2 DI MALIN-RND MTN #2 74/375 COTTER | TABLEMTN | ETL.6020.TOWR | 2021-07-22 | 2021-07-21 | 2021-08-03 | 2022-07-21 | 2021-10-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44922555 | T2 DI MALIN-RND MTN #2 74/375 COTTER | ICS
LC | 121781075 | T076 | T3 DI MIDWY-SNTA MARA T076 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-22 | 2021-07-22 | 2021-10-29 | 2022-01-18 | 2021-10-22 | On-time | 532 | Upgraded | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548178 | T3DI MIDWY-SNTA MARA RPL INSS 2TWRS | 93K
LC | 121781077 | T076 | T3 DI MIDWY-SNTA MARA T076 RPL HNGR | PISMOBCH | ETL.9240.TOWR | 2021-07-22 | 2021-07-22 | 2021-10-29 | 2022-01-18 | 2021-10-22 | On-time | 543 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44938267 | T3 DI MIDWY-SNTA MARA T076 RPL HNGR | ICQ
LC | 121781121 | 067/338 | T2 DI MALIN-RND MTN #2 067/338 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-22 | 2021-07-20 | 2021-08-30 | 2022-07-20 | 2021-10-20 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH TR2 AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44922552 | T2 DI MALIN-RND MTN #2 067/338 RPR OPGW | ICS
LC | 121781210 | 047/233 | T2 DI MALIN-ROUND MTN #2 47/233 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-22 | 2021-07-20 | 2021-09-10 | 2022-07-20 | 2021-10-20 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44922550 | T2 DI MALIN-ROUND MTN #2 47/233 RPR OPGW | ICS
LC | 121781215 | 071/360A | T2 DI MALIN-ROUND MTN #2 71/360A RPR DAM | TABLEMTN | ETL.6020.TOWR | 2021-07-22 | 2021-07-20 | 2021-08-05 | 2022-07-20 | 2021-10-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44922554 | T2 DI MALIN-ROUND MTN #2 71/360A RPR DAM | ICS
LC | 121781476 | 012/008 | T2 DI MELONES-CURTIS 012/008 COTTER | VICTOR | ETL.2390.INSL.CERA | 2021-07-22 | 2021-07-20 | 2021-08-14 | 2022-07-20 | 2021-10-20 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44923660 | T2 DI MELONES-CURTIS 012/008 COTTER | ICW
LC | 121781527 | 000/002C | T3 DI SPRING GAP TAP 000/002C COTTER | VICTOR | ETL.1402.INSL.NCER | 2021-07-22 | 2021-07-21 | 2021-09-16 | 2022-01-17 | 2021-10-19 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44923661 | T3 DI SPRING GAP TAP 000/002C COTTER | ICW
LC | 121781529 | 000/002C | T3 DI SPRING GAP TAP 0/2C RPR GYWW CTTR | VICTOR | ETL.1402.POLE.NWOD | 2021-07-22 | 2021-07-21 | 2021-09-16 | 2022-01-17 | 2021-10-19 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44923662 | T3 DI SPRING GAP TAP 0/2C RPR GYWW CTTR | ICW
LC | 121781723 | 006/003 | T2 DI MELNS-CRTS 06/03 COTTER | VICTOR | ETL.2390.INSL.NCER | 2021-07-22 | 2021-07-20 | 2021-09-01 | 2022-07-20 | 2021-10-18 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44923663 | T2 DI MELNS-CRTS 06/03 COTTER | ICW
LC | 121783051 | 003/061B | T2DI CORDELIA #2 TAP-STEEL 3/61 INSW RPR | SACTO | ETL.8184.INSL.NCER | 2021-07-23 | 2021-07-21 | 2021-09-23 | 2022-07-21 | 2021-10-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44923993 | T2DI CORDELIA #2 TAP-STEEL 3/61 INSW RPR | ICW
LC | 121783540 | 007/006A | T2 DI MELONES-CURTIS 7/6A RPR GYWW CTTR | VICTOR | ETL.2390.POLE.WDPS | 2021-07-23 | 2021-07-20 | 2021-08-26 | 2022-07-20 | 2021-10-18 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44923664 | T2 DI MELONES-CURTIS 7/6A RPR GYWW CTTR | ICW
LC | 121783805 | T097 | T3 DI MIDWAY-SANTA MARIA T097 RPR INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 | 2021-10-05 | 2022-01-18 | 2021-10-22 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44938266 | T3 DI MIDWAY-SANTA MARIA T097 RPR INSS | ICS
LC | 121784301 | 080/405C | T2 DI MALIN-RND MTN #2 80/405B RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2021-07-23 | 2021-07-23 | 2021-08-03 | 2022-07-23 | 2021-10-23 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44922556 | T2 DI MALIN-RND MTN #2 80/405B RPR SHLS | ICS
LC | 121784657 | T073 | T3 DI MDWAY-SNTA MARA T073 RPL HANGER | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-23 | 2021-10-29 | 2022-01-19 | 2021-10-23 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 44938261 | T3 DI MDWAY-SNTA MARA T073 RPL HANGER | ICQ
LC | 121784691 | T073 | T3 DI MDWAY-SNTA MARA T073 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-23 | 2021-10-29 | 2022-01-19 | 2021-10-23 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548199 | T3 DI MDWAY-SNTA MARA T073 RPL INSS | 93K
LC | 121785129 | 005/063C | T3 DI WST PNT-VLLY SPRNGS 5/63C RPR SPL | VICTOR | ETL.8350.INSL.CERA | 2021-07-23 | 2021-07-21 | 2021-10-09 | 2022-01-17 | 2021-10-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Replace | 44923665 | T3 DI WST PNT-VLLY SPRNGS 5/63C RPR SPL | ICW
LC | 121785745 | 005/003B | T3 DI LAURELES-OTTER 005/003B RPR INSW | MOSSLNDG | ETL.7380.INSL.NCER | 2021-07-23 | 2021-07-21 | 2021-08-07 | 2022-01-17 | 2021-10-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44923265 | T3 DI LAURELES-OTTER 005/003B RPR INSW | ICW
LC | 121785872 | 071/359A | T2 DI MALIN-RND MTN #2 71/359A RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-23 | 2021-07-22 | 2021-08-03 | 2022-07-22 | 2021-10-22 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44922553 | T2 DI MALIN-RND MTN #2 71/359A RPR OPGW | ICS
LC | 121786028 | T068 | T3 DI MIDWAY-SANTA MARIA T068 RPL HRDT | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 | 2021-09-23 | 2022-01-18 | 2021-10-20 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 44938260 | T3 DI MIDWAY-SANTA MARIA T068 RPL HRDT | ICQ
LC | 121786591 | 007/007A | T2 DI MELONES-CURTIS 007/007AC RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-23 | 2021-07-20 | 2021-10-14 | 2022-07-20 | 2021-10-20 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31548238 | T2 DI MELONES-CURTIS 007/007AR RPL STRW | 70Y
LC | 121786593 | 007/007A | T2 DI MELONES-CURTIS 007/007AL RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-23 | 2021-07-20 | 2021-10-14 | 2022-07-20 | 2021-10-20 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31548238 | T2 DI MELONES-CURTIS 007/007AR RPL STRW | 70Y
LC | 121787208 | 008/113 | T3 DI MIDDLEFORK #1 008/113 COTR KEY | SACTO | ETL.8405.POLE.WOOD | 2021-07-23 | 2021-07-22 | 2021-10-15 | 2022-01-18 | 2021-10-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44923994 | T3 DI MIDDLEFORK #1 008/113 COTR KEY | ICW
LC | 121787558 | 002/042 | T3 DI MIDDLEFORK #1 002/042 RPL DAMW | SACTO | ETL.8405.INSL.CERA | 2021-07-23 | 2021-07-22 | 2021-10-14 | 2022-01-18 | 2021-10-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace | 44923990 | T3 DI MIDDLEFORK #1 002/042 RPL DAMW | ICW
LC | 121788074 | ;001/022 | EI T2 CARIBOU #2 ;001/022 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-06 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788077 | ;001/015 | EI T2 CARIBOU #2 ;1/015 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-01 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788079 | ;001/013 | EI T2 CARIBOU #2 ;001/013 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-01 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788082 | ;001/021 | EI T2 CARIBOU #2 ;1/021 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-06 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788083 | ;001/020 | EI T2 CARIBOU #2 ;001/020 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-06 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788085 | ;001/018 | EI T2 CARIBOU #2 ;001/018 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-06 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788086 | ;001/017 | EI T2 CARIBOU #2 ;001/017 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-06 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788147 | ;001/016 | EI T2 CARIBOU #2 ;001/016 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-01 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788156 | ;001/005 | EI T2 CARIBOU #2 ;001/005 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-01 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788161 | ;001/014 | EI T2 CARIBOU #2 ;001/014 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-01 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788162 | ;001/012 | EI T2 CARIBOU #2 ;001/012 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-01 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788163 | ;001/010 | EI T2 CARIBOU #2 ;001/010 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-01 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788164 | ;001/008 | EI T2 CARIBOU #2 ;001/008 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-04 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788166 | ;001/007 | EI T2 CARIBOU #2 ;001/007 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-04 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788167 | ;001/006 | EI T2 CARIBOU #2 ;001/006 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-01 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788168 | ;001/004 | EI T2 CARIBOU #2 ;001/004 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-01 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788169 | ;001/003 | EI T2 CARIBOU #2 ;001/003 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-01 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788192 | ;001/001 | EI T2 CARIBOU #2 ;001/001 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-06 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121788211 | ;001/002 | EI T2 CARIBOU #2 ;001/002 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-23 | 2021-07-23 | 2021-09-01 | 2022-07-23 | 2021-10-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121790177 | 080/407 | T2 DI MALIN-ROUND MTN #2 80/407 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-24 | 2021-07-24 | 2021-08-03 | 2022-07-24 | 2021-10-24 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44922557 | T2 DI MALIN-ROUND MTN #2 80/407 RPR OPGW | ICS
LC | 121790562 | 009/050 | T3 DI MTCLF-MONTA VISTA #3 9/50 RPR INSS | MOSSLNDG | ETL.5091.INSL | 2021-07-24 | 2021-07-24 | 2021-08-22 | 2022-01-20 | 2021-10-22 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44923266 | T3 DI MTCLF-MONTA VISTA #3 9/50 RPR INSS | ICS
LC | 121790802 | 010/004A | T2 EI WINDSOR-FITCH MTN 10/4A RPR SWTC | LAKEVLLE | ETL.6900.SWIT | 2021-07-24 | 2021-07-24 | 2021-09-10 | 2022-07-24 | 2021-10-24 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Switch-Wood | Repair | 44922041 | T2 EI WINDSOR-FITCH MTN 10/4A RPR SWTC | ICW
LC | 121791247 | 005/102 | T3 DI COLGATE-CHALLENGE 005/102 RPL SPLW | SACTO | ETL.6480.INSL.NCER | 2021-07-24 | 2021-07-22 | 2021-08-01 | 2022-01-18 | 2021-10-20 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Splice-Wood | Replace | 44923995 | T3 DI COLGATE-CHALLENGE 005/102 RPL SPLW | ICW
LC | 121793926 | T074 | T3 MIDWAY-SANTA MARIA T074 RPR SPLS | PISMOBCH | ETL.9240.TOWR | 2021-07-25 | 2021-07-25 | 2021-10-29 | 2022-01-21 | 2021-10-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW CREW COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Splice-Steel | Repair | 44938264 | T3 MIDWAY-SANTA MARIA T074 RPR SPLS | ICS
LC | 121793951 | T074 | T3 MIDWAY-SANTA MARIA T074 RPL HANGER | PISMOBCH | ETL.9240.TOWR | 2021-07-25 | 2021-07-25 | 2021-10-29 | 2022-01-21 | 2021-10-25 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW CREW COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Tower | Replace | 44945185 | T3 MIDWAY-SANTA MARIA T074 RPL HANGER | ICQ
LC | 121794216 | 022/598 | T2 CARIBOU #2 22/598 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-25 | 2021-07-25 | 2021-09-09 | 2022-07-25 | 2021-10-25 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547679 | T2 CARIBOU #2 22/593 RPL STRW | 92F
LC | 121794217 | 022/593 | T2 CARIBOU #2 22/593 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-25 | 2021-07-25 | 2021-09-11 | 2022-07-25 | 2021-10-25 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547679 | T2 CARIBOU #2 22/593 RPL STRW | 92F
LC | 121794218 | 022/603 | T2 CARIBOU #2 22/603 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-25 | 2021-07-25 | 2021-09-09 | 2022-07-25 | 2021-10-25 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547679 | T2 CARIBOU #2 22/593 RPL STRW | 92F
LC | 121794243 | 023/604 | T2 CARIBOU #2 23/604 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-25 | 2021-07-25 | 2021-09-11 | 2022-07-25 | 2021-10-25 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548080 | T2 CARIBOU #2 23/604 RPL STRW | 92F
LC | 121794252 | 022/601 | T2 CARIBOU #2 22/601 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-25 | 2021-07-25 | 2021-09-09 | 2022-07-25 | 2021-10-25 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547679 | T2 CARIBOU #2 22/593 RPL STRW | 92F
LC | 121794552 | 007/134 | EI SMARTVILLE-NICOLAUS #1 7/134 RPR SWTC | SACTO | ETL.7990.SWIT | 2021-07-26 | 2021-07-24 | 2021-07-24 | 2022-07-24 | 2021-10-24 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 | Out of Adjustment | Switch | Repair | 44921298 | EI SMARTVILLE-NICOLAUS #1 7/134 RPR SWTC | ICE
LC | 121794561 | 007/136 | EI SMARTVILLE-NICOLAUS #2 7/136 RPR SWTC | SACTO | ETL.8000.SWIT | 2021-07-26 | 2021-07-24 | 2021-07-24 | 2022-07-24 | 2021-10-24 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 | Out of Adjustment | Switch | Repair | 44921296 | EI SMARTVILLE-NICOLAUS #2 7/136 RPR SWTC | ICE
LC | 121796263 | 001/011 | T2 DI PIT #5-ROUND MTN #1 1/11 RPR SHLW | TABLEMTN | ETL.5420.POLE.STPS | 2021-07-26 | 2021-07-26 | 2021-09-11 | 2022-07-26 | 2021-10-26 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44953981 | T2 DI PIT #5-ROUND MTN #1 1/11 RPR SHLW | ICW
LC | 121796522 | 046/224 | T2 DI IGNACIO-SOBRANTE 46/224 RPR INSS | CONCORD | ETL.4920.INSL.CERA | 2021-07-26 | 2021-07-26 | 2021-08-31 | 2022-07-26 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44923049 | T2 DI IGNACIO-SOBRANTE 46/224 RPR INSS | ICS
LC | 121796776 | 008/071 | T3 DI MIDDLE FRK-GLD HILL 8/71 RPR SHWR | SACTO | ETL.5140.TOWR | 2021-07-26 | 2021-07-24 | 2021-11-16 | 2022-01-20 | 2021-10-24 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44923991 | T3 DI MIDDLE FRK-GLD HILL 8/71 RPR SHWR | ICS
LC | 121796922 | T-124 | T3 DI MIDWAY-SANTA MARIA T-124 RPR INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2021-09-20 | 2022-01-22 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44938199 | T3 DI MIDWAY-SANTA MARIA T-124 RPR INSS | ICS
LC | 121797001 | T098 | T3 DI MIDWAY-SANTA MARIA T098 RPR INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2021-10-05 | 2022-01-22 | 2021-10-24 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44938265 | T3 DI MIDWAY-SANTA MARIA T098 RPR INSS | ICS
LC | 121797719 | 071/360B | T2 DI MALIN-ROUND MTN#2 71/360B COTTER | TABLEMTN | ETL.6020.INSL | 2021-07-26 | 2021-07-26 | 2021-08-30 | 2022-07-26 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44930392 | T2 DI MALIN-ROUND MTN#2 71/360B COTTER | ICS
LC | 121797923 | 071/360B | T2 DI MALIN-ROUND MTN#2 71/360B RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-26 | 2021-07-26 | 2021-08-05 | 2022-07-26 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCM COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44930391 | T2 DI MALIN-ROUND MTN#2 71/360B RPR OPGW | ICS
LC | 121799401 | 046/225 | T2 DI IGNACIO-SOBRANTE 46/225 RPR INSS | CONCORD | ETL.4960.INSL | 2021-07-26 | 2021-07-24 | 2021-10-16 | 2022-07-24 | 2021-10-24 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44923050 | T2 DI IGNACIO-SOBRANTE 46/225 RPR INSS | ICS
LC | 121799733 | 046/225 | T2 DI IGNACIO-SOBRANTE 46/225 RPR INSS | CONCORD | ETL.4920.INSL.CERA | 2021-07-26 | 2021-07-24 | 2021-08-31 | 2022-07-24 | 2021-10-24 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44923048 | T2 DI IGNACIO-SOBRANTE 46/225 RPR INSS | ICS
LC | 121800253 | T-109 | T3 DI MIDWAY-SNTA MARIA T-109 INS COTTER | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2021-09-20 | 2022-01-22 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44938197 | T3 DI MIDWAY-SNTA MARIA T-109 INS COTTER | ICS
LC | 121800279 | T-125 | T3 DI MIDWAY-SANTA MARIA T-125 RPR INSW | PISMOBCH | ETL.9240.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2021-09-20 | 2022-01-22 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44947613 | T3 DI MIDWAY-SANTA MARIA T-125 RPR INSW | ICW
LC | 121800441 | T074 | T3 DI MIDWAY-SANTA MARIA T074 RPL DAMS | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 | 2021-10-29 | 2022-01-22 | 2021-10-24 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 44938263 | T3 DI MIDWAY-SANTA MARIA T074 RPL DAMS | ICS
LC | 121800500 | 023/003 | T2 DI GRBRVLLE-LYTNVLLE 023/003 RPR GYWW | EUREKA | ETL.8365.POLE.NWOD | 2021-07-26 | 2021-07-26 | 2021-08-17 | 2022-07-26 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH TR2 AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44923051 | T2 DI GRBRVLLE-LYTNVLLE 023/003 RPR GYWW | ICW
LC | 121800502 | 001/005 | T3 DI DIABLO-MIDWAY #3 001/5 RPR INSS | PISMOBCH | ETL.5980.INSL | 2021-07-26 | 2021-07-26 | 2021-09-08 | 2022-01-22 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44938190 | T3 DI DIABLO-MIDWAY #3 001/5 RPR INSS | ICS
LC | 121800503 | 012/001 | T2 DI MELONES-CURTIS 012/001 INSW COTR | VICTOR | ETL.2390.INSL.NCER | 2021-07-26 | 2021-07-26 | 2021-08-26 | 2022-07-26 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44923667 | T2 DI MELONES-CURTIS 012/001 INSW COTR | ICW
LC | 121800673 | 032/006 | T2 DI GRBRVLLE-LYTNVLLE 032/006 RPR GYWW | EUREKA | ETL.8365.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2021-08-17 | 2022-07-26 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH TR2 AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44923052 | T2 DI GRBRVLLE-LYTNVLLE 032/006 RPR GYWW | ICW
LC | 121800774 | 023/607 | T2 EI CARIBOU #2 23/607 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2021-09-12 | 2022-07-26 | 2021-10-26 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548080 | T2 CARIBOU #2 23/604 RPL STRW | 92F
LC | 121800777 | 023/609 | T2 EI CARIBOU #2 23/609 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2021-09-12 | 2022-07-26 | 2021-10-26 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548080 | T2 CARIBOU #2 23/604 RPL STRW | 92F
LC | 121800778 | 023/612 | T2 EI CARIBOU #2 23/612 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2021-09-11 | 2022-07-26 | 2021-10-26 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548080 | T2 CARIBOU #2 23/604 RPL STRW | 92F
LC | 121800779 | 023/613 | T2 EI CARIBOU #2 23/613 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2021-09-11 | 2022-07-26 | 2021-10-26 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548080 | T2 CARIBOU #2 23/604 RPL STRW | 92F
LC | 121800794 | 023/605 | T2 EI CARIBOU #2 23/605 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2021-09-11 | 2022-07-26 | 2021-10-26 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548080 | T2 CARIBOU #2 23/604 RPL STRW | 92F
LC | 121800795 | 023/608 | T2 EI CARIBOU #2 23/608 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2021-09-11 | 2022-07-26 | 2021-10-26 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548080 | T2 CARIBOU #2 23/604 RPL STRW | 92F
LC | 121800805 | 023/611 | T2 EI CARIBOU #2 023/611 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2021-09-11 | 2022-07-26 | 2021-10-26 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548080 | T2 CARIBOU #2 23/604 RPL STRW | 92F
LC | 121800806 | 023/614 | T2 EI CARIBOU #2 23/614 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2021-09-11 | 2022-07-26 | 2021-10-26 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548080 | T2 CARIBOU #2 23/604 RPL STRW | 92F
LC | 121800808 | 023/617 | T2 EI CARIBOU #2 23/617 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2021-09-11 | 2022-07-26 | 2021-10-26 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548080 | T2 CARIBOU #2 23/604 RPL STRW | 92F
LC | 121800820 | 023/615 | T2 EI CARIBOU #2 023/615 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2021-09-11 | 2022-07-26 | 2021-10-26 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548080 | T2 CARIBOU #2 23/604 RPL STRW | 92F
LC | 121800821 | 023/616 | T2 EI CARIBOU #2 23/616 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2021-09-11 | 2022-07-26 | 2021-10-26 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548080 | T2 CARIBOU #2 23/604 RPL STRW | 92F
LC | 121800822 | 023/618 | T2 EI CARIBOU #2 23/618 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2021-09-12 | 2022-07-26 | 2021-10-26 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548080 | T2 CARIBOU #2 23/604 RPL STRW | 92F
LC | 121800823 | 023/620 | T2 EI CARIBOU #2 23/620 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-26 | 2021-07-26 | 2021-09-11 | 2022-07-26 | 2021-10-26 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548080 | T2 CARIBOU #2 23/604 RPL STRW | 92F
LC | 121801434 | 083/421 | T2 DI MALIN-ROUND MTN#2 83/421 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-27 | 2021-07-26 | 2021-08-03 | 2022-07-26 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44930395 | T2 DI MALIN-ROUND MTN#2 83/421 RPR OPGW | ICS
LC | 121801487 | 083/421 | T2 DI MALIN-ROUND MTN#2 83/421 COTTER | TABLEMTN | ETL.6020.INSL | 2021-07-27 | 2021-07-26 | 2021-08-03 | 2022-07-26 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44930394 | T2 DI MALIN-ROUND MTN#2 83/421 COTTER | ICS
LC | 121803000 | 001/012 | T3 DI DIABLO-GATES #1 1/12 COTTER | PISMOBCH | ETL.5960.INSL.NCER | 2021-07-27 | 2021-07-26 | 2021-09-08 | 2022-01-22 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44938186 | T3 DI DIABLO-GATES #1 1/12 COTTER | ICS
LC | 121803618 | 022/001 | T2 DI MNDCNO-WLLTS-FT BRG 22/1 RPR SPLW | LAKEVLLE | ETL.7550.INSL.NCER | 2021-07-27 | 2021-07-26 | 2021-08-25 | 2022-07-26 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 44924185 | T2 DI MNDCNO-WLLTS-FT BRG 22/1 RPR SPLW | ICW
LC | 121803757 | X001/007 | T3 DI DIABLO-MESA X001/007 RPR INSS | PISMOBCH | ETL.4620.INSL.CERA | 2021-07-27 | 2021-07-26 | 2021-09-08 | 2022-01-22 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44938187 | T3 DI DIABLO-MESA X001/007 RPR INSS | ICS
LC | 121803809 | X001/007 | T3 DI DIABLO-MESA X001/007 RPR OPGW | PISMOBCH | ETL.5260.INSL.CERA | 2021-07-27 | 2021-07-26 | 2021-09-08 | 2022-01-22 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44938195 | T3 DI DIABLO-MESA X001/007 RPR OPGW | ICS
LC | 121803873 | 000/002 | T3 DI DIABLO-MIDWAY #2 0/2 COTTER | PISMOBCH | ETL.5970.INSL | 2021-07-27 | 2021-07-26 | 2021-09-08 | 2022-01-22 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44938189 | T3 DI DIABLO-MIDWAY #2 0/2 COTTER | ICS
LC | 121804008 | 003/027 | T2 DI PIT#1-HAT CRK#2 BRNY 3/27 RPR OPGW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-07-27 | 2021-07-26 | 2021-08-07 | 2022-07-26 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44945014 | T2 DI PIT#1-HAT CRK#2 BRNY 3/27 RPR OPGW | ICW
LC | 121806184 | 061/306 | T2 DI MALIN-ROUND MTN #2 61/306 COTTER | TABLEMTN | ETL.6020.INSL | 2021-07-28 | 2021-07-26 | 2021-08-25 | 2022-07-26 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44930390 | T2 DI MALIN-ROUND MTN #2 61/306 COTTER | ICS
LC | 121806255 | 026/008 | T2 DI GRBRVLL-LAYTONVILLE 26/8 RPR GYWW | EUREKA | ETL.8365.POLE.WOOD | 2021-07-28 | 2021-07-26 | 2021-08-17 | 2022-07-26 | 2021-10-27 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44928739 | T2 DI GRBRVLL-LAYTONVILLE 26/8 RPR GYWW | ICW
LC | 121806350 | 022/113 | T3 DI RND MTN-TBLE MTN #2 22/113 COTTER | TABLEMTN | ETL.6070.INSL | 2021-07-28 | 2021-07-26 | 2021-10-03 | 2022-01-22 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44979077 | T3 DI RND MTN-TBLE MTN #2 22/113 COTTER | ICS
LC | 121806630 | 007/136 | T2 DI SMRTVLL-NICOLUAS#2 7/136 RPR SWTC | SACTO | ETL.8000.SWIT | 2021-07-28 | 2021-07-28 | 2021-08-25 | 2022-07-28 | 2021-10-28 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | Out of Adjustment | Switch | Repair | 44943253 | T2 DI SMRTVLL-NICOLUAS#2 7/136 RPR SWTC | ICE
LC | 121807461 | 032/004 | T2 DI GRBRVLL-LAYTONVILLE 32/4 RPR GYWW | EUREKA | ETL.8365.POLE.NWOD | 2021-07-28 | 2021-07-26 | 2021-08-17 | 2022-07-26 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44928985 | T2 DI GRBRVLL-LAYTONVILLE 32/4 RPR GYWW | ICW
LC | 121807901 | 015/006 | T2 DI MNDCN-WLLTS-FRT BRGG 15/6 RPR INSW | LAKEVLLE | ETL.7550.INSL.NCER | 2021-07-28 | 2021-07-26 | 2021-08-27 | 2022-07-26 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44928730 | T2 DI MNDCN-WLLTS-FRT BRGG 15/6 RPR INSW | ICW
LC | 121808094 | X001/007 | T3 DI DIABLO-MESA 001/007 RPR OPGW | PISMOBCH | ETL.4620.INSL.CERA | 2021-07-28 | 2021-07-26 | 2021-09-08 | 2022-01-22 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44938188 | T3 DI DIABLO-MESA 001/007 RPR OPGW | ICS
LC | 121808351 | 073/372 | T2 DI MALIN-RND MTN #2 73/371 CANCEL | TABLEMTN | ETL.6020.INSL | 2021-07-28 | 2021-07-26 | 2021-08-30 | 2022-07-26 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44930393 | T2 DI MALIN-RND MTN #2 73/371 COTTER | ICS
LC | 121809280 | 007/135 | T2 DI SMRTVLL-NICOLS #1 7/135 REFRAME | SACTO | ETL.7990.INSL.NCER | 2021-07-28 | 2021-07-27 | 2021-10-05 | 2022-07-27 | 2021-10-27 | On-time | 637 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31548665 | T2 DI SMRTVLL-NICOLS #1 7/135 REFRAME | 93E
LC | 121809437 | 105/002 | EI T2 HUMBOLDT-TRINITY 105/2 COTTER | EUREKA | ETL.1820.POLE.WDPS | 2021-07-28 | 2021-07-28 | 2021-07-31 | 2022-07-28 | 2021-10-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 44926384 | EI T2 HUMBOLDT-TRINITY 105/2 COTTER | ICW
LC | 121809722 | 010/065 | T2 DI CORTINA-VACA 10/65 RPR OPGW | SACTO | ETL.4540.TOWR | 2021-07-28 | 2021-07-27 | 2021-09-23 | 2022-07-27 | 2021-10-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44930547 | T2 DI CORTINA-VACA 10/65 RPR OPGW | ICW
LC | 121809840 | 000/009 | T3 DI DRUM-SPAULDING 000/009 COTTER | SACTO | ETL.6770.INSL.NCER | 2021-07-28 | 2021-07-27 | 2021-09-28 | 2022-01-23 | 2021-10-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44930557 | T3 DI DRUM-SPAULDING 000/009 COTTER | ICW
LC | 121809842 | 030/008 | T2 DI GRBRVLLE-LYTNVLLE 030/008 RPR INSW | EUREKA | ETL.8365.INSL.CERA | 2021-07-28 | 2021-07-28 | 2021-08-17 | 2022-07-28 | 2021-10-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44928986 | T2 DI GRBRVLLE-LYTNVLLE 030/008 RPR INSW | ICW
LC | 121809843 | 000/003 | T2 DI LYTNVLLE COVELO 000/003 RPR GYWW | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-07-28 | 2021-07-28 | 2021-08-05 | 2022-07-28 | 2021-10-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44928736 | T2 DI LYTNVLLE COVELO 000/003 RPR GYWW | ICW
LC | 121810029 | 023/001 | T2 DI GRBRVLL-LYTNVLL 23/1 RPR INSW | EUREKA | ETL.8365.INSL.CERA | 2021-07-28 | 2021-07-26 | 2021-08-17 | 2022-07-26 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44929247 | T2 DI GRBRVLL-LYTNVLL 23/1 RPR INSW | ICW
LC | 121810041 | 009/168 | T2 DI PT #1-HT CRK#2-BRNY 9/168 COTTER | TABLEMTN | ETL.7040.POLE.NWOD | 2021-07-28 | 2021-07-27 | 2021-08-07 | 2022-07-27 | 2021-10-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR FRAB | No Good/Out of Stdrd | Insulator-Wood | Repair | 44945016 | T2 DI PT #1-HT CRK#2-BRNY 9/168 COTTER | ICW
LC | 121810131 | 006/002 | T2 DI MENDOCINO-UKIAH 6/2 COTTER | LAKEVLLE | ETL.2420.INSL.CERA | 2021-07-28 | 2021-07-27 | 2021-08-09 | 2022-07-27 | 2021-10-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44928734 | T2 DI MENDOCINO-UKIAH 6/2 COTTER | ICW
LC | 121810197 | 024/104 | T2 DI MOSS LANDNG-METCLF 24/104 RPR SHLW | MOSSLNDG | ETL.6050.TOWR | 2021-07-28 | 2021-07-27 | 2021-08-03 | 2022-07-27 | 2021-10-27 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44932752 | T2 DI MOSS LANDNG-METCLF 24/104 RPR SHLW | ICS
LC | 121810216 | 025/000 | T2 DI GARBERVILLE-LYTNVL 25/0 RPR GYWW | EUREKA | ETL.8365.POLE.WOOD | 2021-07-28 | 2021-07-26 | 2021-08-17 | 2022-07-26 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44928980 | T2 DI GARBERVILLE-LYTNVL 25/0 RPR GYWW | ICW
LC | 121810304 | 003/001 | T2 DI MENDOCINO-UKIAH 3/1R GUY COTTER | LAKEVLLE | ETL.2420.POLE.WDPS | 2021-07-28 | 2021-07-27 | 2021-08-09 | 2022-07-27 | 2021-10-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44928732 | DI MENDOCINO-UKIAH 3/1 GUY COTTER | ICW
LC | 121810306 | 003/001 | T2 DI MENDOCINO-UKIAH 3/1L GUY COTTER | LAKEVLLE | ETL.2420.POLE.WDPS | 2021-07-28 | 2021-07-27 | 2021-08-09 | 2022-07-27 | 2021-10-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44928733 | DI MENDOCINO-UKIAH 3/1 GUY COTTER | ICW
LC | 121810351 | 089/452B | T2 DI MALIN-ROUND MTN#2 89/452A RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-07-28 | 2021-07-27 | 2021-08-03 | 2022-07-27 | 2021-10-27 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44930396 | T2 DI MALIN-ROUND MTN#2 89/452A RPR OPGW | ICS
LC | 121810530 | 014/323 | T2 DI DRUM-GRASS VLY-WEI 14/373 COTTER | SACTO | ETL.6760.INSL.CERA | 2021-07-28 | 2021-07-27 | 2021-09-24 | 2022-07-27 | 2021-10-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44945042 | T2 DI DRUM-GRASS VLY-WEI 14/373 COTTER | ICS
LC | 121810557 | 016/002 | T2 DI MNDO-WLTS-FRTBRG 16/2 RPR INSW CTR | LAKEVLLE | ETL.7550.INSL | 2021-07-28 | 2021-07-28 | 2021-08-27 | 2022-07-28 | 2021-10-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44928731 | T2DI MNDO-WLTS-FRTBRG 16/02 RPR INSW CTR | ICW
LC | 121810604 | 003/012 | T2 DI LAYTONVILLE-COVELO 3/12 RPL CRSW | LAKEVLLE | ETL.7390.POLE.WOOD | 2021-07-28 | 2021-07-27 | 2021-10-19 | 2022-07-27 | 2021-10-27 | On-time | 637 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31548664 | T2 DI LAYTONVILLE-COVELO 3/12 RPL CRSW | 93E
LC | 121810876 | 015/001 | T2 DI LAYTONVILLE-WILLITS 15/1 RPR INSW | LAKEVLLE | ETL.8360.INSL.NCER | 2021-07-28 | 2021-07-27 | 2021-08-06 | 2022-07-27 | 2021-10-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44938321 | T2 DI LAYTONVILLE-WILLITS 15/1 RPR INSW | ICW
LC | 121810877 | 015/001 | T2 DI LAYTONVILLE-WILLITS 15/1 RPR GYWW | LAKEVLLE | ETL.8360.POLE.STPS | 2021-07-28 | 2021-07-27 | 2021-08-06 | 2022-07-27 | 2021-10-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44938324 | T2 DI LAYTONVILLE-WILLITS 15/1 RPR GYWW | ICW
LC | 121810942 | 009/131 | T3 DI MIDDLEFORK #1 009/131 COTTER | SACTO | ETL.8405.INSL.NCER | 2021-07-28 | 2021-07-28 | 2021-10-17 | 2022-01-24 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44930555 | T3 DI MIDDLEFORK #1 009/131 COTTER | ICW
LC | 121811020 | 004/037 | T2 DI CRAG VIEW-CASCADE 004/037 COTTER | TABLEMTN | ETL.1350.INSL | 2021-07-28 | 2021-07-28 | 2021-08-03 | 2022-07-28 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44935673 | T2 DI CRAG VIEW-CASCADE 004/037 COTTER | ICS
LC | 121812526 | B022/497 | T3 DI DRM-GRSS VLLY-WMR B22/497 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-07-29 | 2021-07-28 | 2021-09-24 | 2022-01-24 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44930558 | T3 DI DRM-GRSS VLLY-WMR B22/497 RPR GYWW | ICW
LC | 121812780 | 004/046A | T2 DI HILLSDLE JCT-HF MN 4/46A RPR GYWW | METCALF | ETL.7060.POLE.WOOD | 2021-07-29 | 2021-07-28 | 2021-10-05 | 2022-07-28 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44929306 | T2 DI HILLSDLE JCT-HF MN 4/46A RPR GYWW | ICW
LC | 121812837 | 023/115 | T3 DI RND MTN-TBL MTN#2 23/115 COTTER | TABLEMTN | ETL.6070.TOWR | 2021-07-29 | 2021-07-28 | 2021-09-13 | 2022-01-24 | 2021-10-28 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44979079 | T3 DI RND MTN-TBL MTN#2 23/115 COTTER | ICS
LC | 121813019 | ;000/024 | T2 CARIBOU #2 ;000/024 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2021-09-05 | 2022-07-29 | 2021-10-29 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547729 | T2 CARIBOU #2 ;000/013 RPL POLE | 92F
LC | 121813050 | 014/093 | T2 MILLBRAE-SNEATH 14/93 RPR SWTC | METCALF | ETL.7570.SWIT | 2021-07-29 | 2021-07-29 | 2021-10-11 | 2022-07-29 | 2021-10-29 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | Out of Adjustment | Switch | Repair | 44929315 | T2 JEFFERSON-MARTIN 14/093 RPR SWTC | ICE
LC | 121813061 | ;000/013 | T2 CARIBOU #2 ;000/013 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2021-09-11 | 2022-07-29 | 2021-10-29 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547729 | T2 CARIBOU #2 ;000/013 RPL POLE | 92F
LC | 121813062 | ;000/016 | T2 CARIBOU #2 ;000/016 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2021-09-11 | 2022-07-29 | 2021-10-29 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547729 | T2 CARIBOU #2 ;000/013 RPL POLE | 92F
LC | 121813064 | ;000/019 | T2 CARIBOU #2 ;000/019 RPL POLE | TABLEMTN | ETL.6280.POLE.NWOD | 2021-07-29 | 2021-07-29 | 2021-09-11 | 2022-07-29 | 2021-10-29 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547729 | T2 CARIBOU #2 ;000/013 RPL POLE | 92F
LC | 121813127 | ;000/034 | T2 CARIBOU #2 ;0/34 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2021-09-01 | 2022-07-29 | 2021-10-29 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121813129 | ;001/000 | T2 CARIBOU #2 ;001/000 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2021-09-01 | 2022-07-29 | 2021-10-29 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121813134 | ;002/000 | T2 CARIBOU #2 ;2/0 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2021-09-02 | 2022-07-29 | 2021-10-29 | On-time | 500 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Other | Emergency-Wood | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121813135 | ;001/009 | T2 CARIBOU #2 ;001/009 RPL STRW | TABLEMTN | ETL.6280.POLE.NWOD | 2021-07-29 | 2021-07-29 | 2021-09-01 | 2022-07-29 | 2021-10-29 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121813137 | ;001/011 | T2 CARIBOU #2 ;001/011 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2021-09-04 | 2022-07-29 | 2021-10-29 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121813197 | ;002/000A | T2 CARIBOU #2 ;2/0 RPL STRW | TABLEMTN | ETL.6280.POLE.NWOD | 2021-07-29 | 2021-07-29 | 2021-09-06 | 2022-07-29 | 2021-10-29 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121813247 | ;001/019 | T2 CARIBOU #2 ;001/019 RPL STRW | TABLEMTN | ETL.6280.POLE.NWOD | 2021-07-29 | 2021-07-29 | 2021-09-06 | 2022-07-29 | 2021-10-29 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121813287 | 007/005 | NPR T2 CARIBOU-PLUMAS JCT 7/5 RPL STRW | TABLEMTN | ETL.6290.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2021-09-07 | 2022-07-29 | 2021-10-29 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548550 | NPR T2 CARIBOU-PLUMAS JCT 7/5 RPL STRW | 92F
LC | 121813325 | 023/115 | T3 DI RND MTN-TBL MTN#2 23/115 COTTER | TABLEMTN | ETL.6070.INSL | 2021-07-29 | 2021-07-28 | 2021-09-13 | 2022-01-24 | 2021-10-28 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44979101 | T3 DI RND MTN-TBL MTN#2 23/115 COTTER | ICS
LC | 121814221 | 046/224 | T2 DI LKVLL-SBRNT #2 46/224 COTTER | CONCORD | ETL.4960.INSL | 2021-07-29 | 2021-07-28 | 2021-08-24 | 2022-07-28 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44929312 | T2 DI LKVLL-SBRNT #2 46/224 COTTER | ICS
LC | 121814543 | 007/076 | T2 DI IGNACIO-BOLINAS #1 7/76 RPR INSW | LAKEVLLE | ETL.7140.INSL | 2021-07-29 | 2021-07-28 | 2021-08-17 | 2022-07-28 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44929805 | T2 DI IGNACIO-BOLINAS #1 7/76 RPR INSW | ICW
LC | 121815131 | 064/464 | NRP T2 BRIDGVILLE-CTTNWD 64/464 RPR CNDW | EUREKA | ETL.1110.TOWR | 2021-07-29 | 2021-07-29 | 2021-07-30 | 2022-07-29 | 2021-10-29 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 44924531 | NRP T2 BRIDGVILLE-CTTNWD 64/464 RPR CNDW | ICS
LC | 121815405 | 001/004 | T2 DI MELONES-CURTIS 001/004 COTTER | VICTOR | ETL.2390.INSL.NCER | 2021-07-29 | 2021-07-28 | 2021-09-01 | 2022-07-28 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44930387 | T2 DI MELONES-CURTIS 001/004 COTTER | ICW
LC | 121815411 | 013/107C | T3 DI MIDLE FRK-GLD HIL 13/107C RPL INSS | SACTO | ETL.5140.INSL | 2021-07-29 | 2021-07-29 | 2022-10-02 | 2022-01-25 | 2022-01-29 | Late | 532 | Upgraded | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31543650 | T3 DI MDDL FRK-GLD HLL RPL INSS 4TWR | 93K
LC | 121815746 | 014/379 | T3 DI COLGATE-ALLEGHANY 14/379 RPL HRDD | SACTO | ETL.6470.POLE.WOOD | 2021-07-29 | 2021-07-29 | 2021-09-22 | 2022-01-25 | 2021-10-29 | On-time | 630 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 44930553 | T3 DI COLGATE-ALLEGHANY 14/379 RPL HRDD | ICW
LC | 121816444 | 005/057 | T2 DI IGNACIO-BLNS #1 005/057 RPR INSW | LAKEVLLE | ETL.7140.INSL.CERA | 2021-07-29 | 2021-07-28 | 2021-08-17 | 2022-07-28 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | POHW COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44929805 | T2 DI IGNACIO-BOLINAS #1 7/76 RPR INSW | ICW
LC | 121816465 | 062/008 | T2 DI GARBRVIL-LAYTNVLE 62/08 RPR INSW | EUREKA | ETL.8365.INSL.CERA | 2021-07-29 | 2021-07-27 | 2021-08-16 | 2022-07-27 | 2021-10-27 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44931524 | T2 DI GARBRVIL-LAYTNVLE 62/08 RPR INSW | ICW
LC | 121816520 | 015/104 | T2 DI METCALF-GRN VLLY 015/104 COTTER | MOSSLNDG | ETL.2540.INSL.CERA | 2021-07-29 | 2021-07-29 | 2021-08-20 | 2022-07-29 | 2021-10-27 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44930407 | T2 DI METCALF-GRN VLLY 015/104 COTTER | ICW
LC | 121816602 | 000/007 | T2 DI COLGATE-PALERMO 0/7 RPR INSW | SACTO | ETL.6500.INSL.NCER | 2021-07-29 | 2021-07-28 | 2021-09-22 | 2022-07-28 | 2021-10-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44930559 | T2 DI COLGATE-PALERMO 0/7 RPR INSW | ICW
LC | 121816624 | 010/078A | T2 DI HELMS-GREGG #1 10/78A RPR SHLS | FRESNO | ETL.4870.TOWR | 2021-07-29 | 2021-07-28 | 2021-08-06 | 2022-07-28 | 2021-10-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44929114 | T2 DI HELMS-GREGG #1 10/78A RPR SHLS | ICS
LC | 121816694 | 002/014 | T2 DI DIVIDE-VNDNBRG #2 2/14L RPL HRDD | PISMOBCH | ETL.8630.POLE.WDPS | 2021-07-29 | 2021-07-28 | 2021-09-07 | 2022-07-28 | 2021-10-28 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 44938193 | T2 DI DIVIDE-VNDNBRG #2 2/14L RPL HRDD | ICW
LC | 121816832 | 008/112 | T3 DI MIDDLEFORK #1 08/112 RPR INSW | SACTO | ETL.8405.INSL.NCER | 2021-07-29 | 2021-07-28 | 2021-10-14 | 2022-01-24 | 2021-10-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44930549 | T3 DI MIDDLEFORK #1 08/112 RPR INSW | ICW
LC | 121818106 | 008/197 | T3 DI KILARC-CEDAR CRK 8/197 RPL SPLW | TABLEMTN | ETL.7290.INSL.NCER | 2021-07-30 | 2021-07-29 | 2021-08-28 | 2022-01-25 | 2021-10-27 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Splice-Wood | Replace | 44953982 | T3 DI KILARC-CEDAR CRK 8/197 RPL SPLW | ICW
LC | 121818325 | 048/426 | T2 DI RND MTN-CTTNWD #3 48/426 COTTER | TABLEMTN | ETL.5650.INSL.CERA | 2021-07-30 | 2021-07-28 | 2021-08-07 | 2022-07-28 | 2021-10-28 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44949123 | T2 DI RND MTN-CTTNWD #3 48/426 COTTER | ICS
LC | 121819422 | 010/279 | T3 DI COLGATE-ALLEGHANY 10/279 RPR SPLW | SACTO | ETL.6470.INSL.NCER | 2021-07-30 | 2021-07-29 | 2022-06-18 | 2022-01-25 | 2022-01-29 | Late | 630 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45225472 | T3 DI COLGATE-ALLEGHANY 10/279 RPR SPLW | ICW
LC | 121820343 | 012/237 | T3 DI FRNH MDWS-MIDL FRK 12/237 COTTER | SACTO | ETL.6870.INSL.NCER | 2021-07-30 | 2021-07-28 | 2021-09-03 | 2022-01-24 | 2021-10-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44930640 | T3 DI FRNH MDWS-MIDL FRK 12/237 COTTER | ICW
LC | 121820788 | 022/592 | T2 CARIBOU #2 22/592 RPL INSS | TABLEMTN | ETL.6280.POLE.NWOD | 2021-07-30 | 2021-07-30 | 2021-09-11 | 2022-07-30 | 2021-10-30 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31547679 | T2 CARIBOU #2 22/593 RPL STRW | 92F
LC | 121820872 | 008/012 | T2 CARIBOU-PLUMAS JCT 8/12 RPL POLE | TABLEMTN | ETL.6290.POLE.WOOD | 2021-07-30 | 2021-07-30 | 2021-09-01 | 2022-07-30 | 2021-10-30 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547734 | T2 CARIBOU-PLUMAS JCT - 60 KV_008/008 | 92F
LC | 121820876 | 008/013 | T2 CARIBOU-PLUMAS JCT 8/13 RPL POLE | TABLEMTN | ETL.6290.POLE.WOOD | 2021-07-30 | 2021-07-30 | 2021-09-03 | 2022-07-30 | 2021-10-30 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547734 | T2 CARIBOU-PLUMAS JCT - 60 KV_008/008 | 92F
LC | 121820881 | 008/008 | T2 CARIBOU-PLUMAS JCT 8/8 RPL POLE | TABLEMTN | ETL.6290.POLE.WOOD | 2021-07-30 | 2021-07-30 | 2021-09-01 | 2022-07-30 | 2021-10-30 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547734 | T2 CARIBOU-PLUMAS JCT - 60 KV_008/008 | 92F
LC | 121820889 | 008/015 | T2 CARIBOU-PLUMAS JCT 8/015 RPL POLE | TABLEMTN | ETL.6290.POLE.WOOD | 2021-07-30 | 2021-07-30 | 2021-09-03 | 2022-07-30 | 2021-10-30 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547734 | T2 CARIBOU-PLUMAS JCT - 60 KV_008/008 | 92F
LC | 121820983 | 008/017 | T2 CARIBOU-PLUMAS JCT 8/017 RPL POLE | TABLEMTN | ETL.6290.POLE.WOOD | 2021-07-30 | 2021-07-30 | 2021-09-02 | 2022-07-30 | 2021-10-30 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547734 | T2 CARIBOU-PLUMAS JCT - 60 KV_008/008 | 92F
LC | 121821001 | 008/019 | T2 CARIBOU-PLUMAS JCT 8/019 RPL POLE | TABLEMTN | ETL.6290.POLE.WOOD | 2021-07-30 | 2021-07-30 | 2021-09-02 | 2022-07-30 | 2021-10-30 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547734 | T2 CARIBOU-PLUMAS JCT - 60 KV_008/008 | 92F
LC | 121821006 | 009/003 | T2 CARIBOU-PLUMAS JCT 9/003 RPL POLE | TABLEMTN | ETL.6290.POLE.WOOD | 2021-07-30 | 2021-07-30 | 2021-08-31 | 2022-07-30 | 2021-10-30 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547735 | T2 CARIBOU-PLUMAS JCT - 60 KV_009/003 | 92F
LC | 121822702 | 000/001 | T2 DI SPAULDING-SUMMIT 0/1 RPR INSS | SACTO | ETL.8060.INSL.CERA | 2021-07-30 | 2021-07-29 | 2021-09-28 | 2022-07-29 | 2021-10-27 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44945045 | T2 DI SPAULDING-SUMMIT 0/1 RPR INSS | ICS
LC | 121822796 | 001/017B | T3 DI WST PNT-VLLY SPRNGS 1/17B COTTER | VICTOR | ETL.8350.INSL.NCER | 2021-07-30 | 2021-07-29 | 2021-08-30 | 2022-01-25 | 2021-10-27 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44930388 | T3 DI WST PNT-VLLY SPRNGS 1/17B COTTER | ICW
LC | 121823108 | 007/183 | T3 DI DRM-GRSS VLY-WMR 7/183 COTTTER | SACTO | ETL.6760.INSL.NCER | 2021-07-30 | 2021-07-30 | 2021-09-24 | 2022-01-26 | 2021-10-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44930551 | T3 DI DRM-GRSS VLY-WMR 7/183 COTTTER | ICW
LC | 121823824 | 017/146 | T2 DI CRAG VIEW-CASCADE 17/146 RPR DAMW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-07-31 | 2021-07-30 | 2021-08-03 | 2022-07-30 | 2021-10-30 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 44929404 | T2 DI CRAG VIEW-CASCADE 17/146 RPR DAMW | ICW
LC | 121823856 | 010/291 | T3 DI COLGATE-ALLEGHANY 10/291 RPLC TIE | SACTO | ETL.6470.INSL.CERA | 2021-07-31 | 2021-07-30 | 2021-09-22 | 2022-01-26 | 2021-10-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 44930554 | T3 DI COLGATE-ALLEGHANY 10/291 RPLC TIE | ICW
LC | 121824003 | 084/425 | T2 DI MALIN-ROUND MTN #2 84/425 COTTER | TABLEMTN | ETL.6020.INSL | 2021-07-31 | 2021-07-30 | 2021-08-07 | 2022-07-30 | 2021-10-28 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44929402 | T2 DI MALIN-ROUND MTN #2 84/425 COTTER | ICS
LC | 121824013 | 015/359 | T2 DI DRM-GRS VLY-WR 15/359 GYWW COTTER | SACTO | ETL.6760.POLE.WOOD | 2021-07-31 | 2021-07-30 | 2021-09-24 | 2022-07-30 | 2021-10-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44930550 | T2 DI DRM-GRS VLY-WR 15/359 GYWW COTTER | ICW
LC | 121824563 | 000/004C | T2 DI COLGATE-PALERMO 000/004C RPR GYWW | SACTO | ETL.6500.POLE.NWOD | 2021-07-31 | 2021-07-30 | 2021-09-26 | 2022-07-30 | 2021-10-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44930556 | T2 DI COLGATE-PALERMO 000/004C RPR GYWW | ICW
LC | 121824922 | 020/104 | T3 DI RND MTN-TBL MN #2 020/104 RPL INSS | TABLEMTN | ETL.6070.INSL | 2021-07-31 | 2021-07-31 | 2021-10-03 | 2022-01-27 | 2021-10-30 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548680 | T3 DI RND MTN-TBL MN #2 020/104 RPL INSS | 93K
LC | 121825087 | 007/135 | T2 SMRTVLE-CMP FR WST 7/135 RPR SWITCH | SACTO | ETL.7970.SWIT | 2021-07-31 | 2021-07-31 | 2021-07-31 | 2022-07-31 | 2021-10-31 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 | Out of Adjustment | Switch | Repair | 44928426 | T2 SMRTVLE-CMP FR WST 7/135 RPR SWITCH | ICE
LC | 121825558 | 006/134 | T2 SMARTVILLE-NICOLAUS #2 6/134 RPR SWTC | SACTO | ETL.8000.SWIT | 2021-07-31 | 2021-07-31 | 2021-07-31 | 2022-07-31 | 2021-10-31 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 | Out of Adjustment | Switch | Repair | 44928427 | T2 SMARTVILLE-NICOLAUS #2 6/134 RPR SWTC | ICE
LC | 121825730 | 007/132 | T2 SMARTVILLE-NICOLAUS #1 7/132 RPR CNDW | SACTO | ETL.7990.POLE.WOOD | 2021-07-31 | 2021-07-31 | 2021-10-05 | 2022-07-31 | 2021-10-31 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Conductor-Wood | Repair | 44945044 | T2 SMARTVILLE-NICOLAUS #1 7/132 RPR CNDW | ICW
LC | 121826356 | 000/001 | T3 DI CENTERVILLE-TBL MTN 000/001 COTTER | TABLEMTN | ETL.6320.INSL.NCER | 2021-07-31 | 2021-07-31 | 2021-08-05 | 2022-01-27 | 2021-10-31 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44936245 | T3 DI CENTERVILLE-TBL MTN 000/001 COTTER | ICW
LC | 121829442 | 010/065 | T2 STNSLS-MLNS SS-MNTE 10/65 RPR SWITCH | VICTOR | ETL.3830.TOWR | 2021-08-02 | 2021-08-02 | 2021-10-20 | 2022-08-02 | 2021-11-02 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Out of Adjustment | Switch | Repair | 44930755 | T2 STNSLS-MLNS SS-MNTE 10/65 RPR SWITCH | ICE
LC | 121830674 | 004/033 | T2 ROCK CREEK-POE 4/33 RPL INSLS | TABLEMTN | ETL.5630.INSL | 2021-08-02 | 2021-08-02 | 2021-08-06 | 2022-08-02 | 2021-11-02 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548981 | T2 ROCK CREEK-POE 4/33 RPL INSLS | 93K
LC | 121830675 | 017/124 | T2 CARIBOU-TABLE MTN 17/124 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2021-08-02 | 2021-08-02 | 2021-08-21 | 2022-08-02 | 2021-11-02 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549227 | T2 CARIBOU-TABLE MTN 17/124 RPL INSLS | 93K
LC | 121831185 | 014/058 | T3 EI MNTA VSTA-JFFRSN #1 14/58 RPR INSS | METCALF | ETL.5220.INSL.NCER | 2021-08-02 | 2021-08-02 | 2021-08-16 | 2022-01-29 | 2021-11-02 | On-time | 628 | Upgraded | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 | No Good/Out of Stdrd | Insulator-Steel | Repair | 44943364 | T3 EI MNTA VSTA-JFFRSN #1 14/58 RPR INSS | ICS
LC | 121831769 | :000/010 | T2 CARIBOU #2 :0/10 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-08-02 | 2021-08-02 | 2021-09-06 | 2022-08-02 | 2021-11-02 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548740 | T2 CARIBOU #2 - 60 KV_:000/010 | 92F
LC | 121831774 | :000/014 | T2 CARIBOU #2 :0/14 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-08-02 | 2021-08-02 | 2021-09-07 | 2022-08-02 | 2021-11-02 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31548740 | T2 CARIBOU #2 - 60 KV_:000/010 | 92F
LC | 121832567 | 002/024 | T2 CHRISTIE-WILLOW PASS 2/24 RPR SWITCH | CONCORD | ETL.6370.SWIT | 2021-08-02 | 2021-08-02 | 2021-10-14 | 2022-08-02 | 2021-11-02 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Switch-Wood | Repair | 44943365 | T2 CHRISTIE-WILLOW PASS 2/24 RPR SWITCH | ICW
LC | 121836072 | 007/006 | T3 KONOCTI-EAGLE ROCK 7/6 RPR CONW | LAKEVLLE | ETL.6861.POLE.WOOD | 2021-08-03 | 2021-08-03 | 2021-08-30 | 2022-01-30 | 2021-11-03 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW CREW COMP OH FMOB TR3 FRAB | No Good/Out of Stdrd | Conductor-Wood | Repair | 44933522 | T3 KONOCTI-EAGLE ROCK 7/6 RPR CONW | ICW
LC | 121860077 | 002/047 | T2 CARIBOU-WESTWOOD 2/047 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-03 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549091 | T2 CARIBOU-WESTWOOD - 60 KV_002/046 | 92F
LC | 121860119 | 002/046 | T2 CARIBOU-WESTWOOD 2/046 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-07 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549091 | T2 CARIBOU-WESTWOOD - 60 KV_002/046 | 92F
LC | 121860121 | 002/048 | T2 CARIBOU-WESTWOOD 2/048 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-07 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549091 | T2 CARIBOU-WESTWOOD - 60 KV_002/046 | 92F
LC | 121860123 | 002/049 | T2 CARIBOU-WESTWOOD 2/049 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-07 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549091 | T2 CARIBOU-WESTWOOD - 60 KV_002/046 | 92F
LC | 121860125 | 002/050 | T2 CARIBOU-WESTWOOD 2/050 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-05 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549091 | T2 CARIBOU-WESTWOOD - 60 KV_002/046 | 92F
LC | 121860126 | 002/053 | T2 CARIBOU-WESTWOOD 2/053 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-08 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549091 | T2 CARIBOU-WESTWOOD - 60 KV_002/046 | 92F
LC | 121860127 | 002/054 | T2 CARIBOU-WESTWOOD 2/054 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-03 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549091 | T2 CARIBOU-WESTWOOD - 60 KV_002/046 | 92F
LC | 121860128 | 002/055 | T2 CARIBOU-WESTWOOD 2/055 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-01 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549091 | T2 CARIBOU-WESTWOOD - 60 KV_002/046 | 92F
LC | 121860129 | 003/059 | T2 CARIBOU-WESTWOOD 03/059 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-06 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549092 | T2 CARIBOU-WESTWOOD - 60 KV_003/058 | 92F
LC | 121860133 | 002/051 | T2 CARIBOU-WESTWOOD 2/051 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-07 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549091 | T2 CARIBOU-WESTWOOD - 60 KV_002/046 | 92F
LC | 121860134 | 002/056 | T2 CARIBOU-WESTWOOD 2/056 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-01 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549091 | T2 CARIBOU-WESTWOOD - 60 KV_002/046 | 92F
LC | 121860135 | 002/057 | T2 CARIBOU-WESTWOOD 2/057 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-07 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549091 | T2 CARIBOU-WESTWOOD - 60 KV_002/046 | 92F
LC | 121860136 | 003/058 | T2 CARIBOU-WESTWOOD 3/058 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-06 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549092 | T2 CARIBOU-WESTWOOD - 60 KV_003/058 | 92F
LC | 121860161 | 003/061 | T2 CARIBOU-WESTWOOD 3/061 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-07 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549092 | T2 CARIBOU-WESTWOOD - 60 KV_003/058 | 92F
LC | 121860163 | 005/110 | T2 CARIBOU-WESTWOOD 5/110R RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-07 | 2021-08-07 | 2021-08-27 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549093 | CARIBOU-WESTWOOD_005/110 | 92F
LC | 121860164 | 005/110 | T2 CARIBOU-WESTWOOD 5/110C RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-07 | 2021-08-07 | 2021-08-27 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549093 | CARIBOU-WESTWOOD_005/110 | 92F
LC | 121860171 | 003/060 | T2 CARIBOU-WESTWOOD 03/060 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-01 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549092 | T2 CARIBOU-WESTWOOD - 60 KV_003/058 | 92F
LC | 121860174 | 003/063 | T2 CARIBOU-WESTWOOD 3/063 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-02 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549092 | T2 CARIBOU-WESTWOOD - 60 KV_003/058 | 92F
LC | 121860175 | 003/066 | T2 CARIBOU-WESTWOOD 3/066 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-05 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549092 | T2 CARIBOU-WESTWOOD - 60 KV_003/058 | 92F
LC | 121860176 | 003/068 | T2 CARIBOU-WESTWOOD 3/068 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-09-02 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549092 | T2 CARIBOU-WESTWOOD - 60 KV_003/058 | 92F
LC | 121860183 | 006/127 | T2 CARIBOU-WESTWOOD 6/127 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-08-30 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549094 | T2 CARIBOU-WESTWOOD - 60 KV_006/127 | 92F
LC | 121860186 | 005/110 | T2 CARIBOU-WESTWOOD 5/110L RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-07 | 2021-08-07 | 2021-08-27 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549093 | CARIBOU-WESTWOOD_005/110 | 92F
LC | 121860188 | 007/140 | T2 CARIBOU-WESTWOOD 7/140R RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-07 | 2021-08-07 | 2021-08-17 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 | Fire | Emergency | Replace | 31549095 | CARIBOU-WESTWOOD_007/140 | 92F
LC | 121860343 | 007/145 | T2 CARIBOU-WESTWOOD 7/145 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-07 | 2021-08-07 | 2021-08-22 | 2022-08-07 | 2021-11-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549095 | CARIBOU-WESTWOOD_007/140 | 92F
LC | 121864063 | 023/101 | T2 MORRO BAY-MESA 023/101 INSW GRWSH | PISMOBCH | ETL.5290.TOWR | 2021-08-09 | 2021-08-09 | 2021-08-11 | 2022-08-09 | 2021-11-09 | On-time | 622 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 FRAB | Contaminated | Insulator | Ground Wash | 44944854 | T2 MORRO BAY-MESA 023/101 INSW GRWSH | ICD
LC | 121881989 | 007/147 | T2 CARIBOU-WESTWOOD 7/147 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-10 | 2021-08-10 | 2021-08-14 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549095 | CARIBOU-WESTWOOD_007/140 | 92F
LC | 121882473 | 018/003A | NPR T2 TRINITY-MAPLE CRK 18/3A RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-10 | 2021-08-10 | 2021-08-21 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549278 | NPR T2 TRINITY-MAPLE CRK 18/3A RPL STRW | 92F
LC | 121882474 | 063/004 | T2 EI HUMBOLDT-TRINITY 63/4 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-08-27 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31549273 | T2 WV HMBLDT-TRNITY 52/4 RPL INSW | 92F
LC | 121882475 | 017/003 | NPR T2 TRINITY-MAPLE CREEK 17/3 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-10 | 2021-08-10 | 2021-08-17 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31549275 | NPR T2 TRINITY-MAPLE CREEK 17/3 RPL STRW | 92F
LC | 121882476 | 017/006 | NPR T2 TRINITY-MAPLE CREEK 17/6 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-10 | 2021-08-10 | 2021-08-18 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31549275 | NPR T2 TRINITY-MAPLE CREEK 17/3 RPL STRW | 92F
LC | 121882479 | 004/081 | T2 CARIBOU-WESTWOOD 4/081 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-10 | 2021-08-10 | 2021-08-31 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549326 | T2 CARIBOU-WESTWOOD - 60 KV_004/081 | 92F
LC | 121882481 | 004/085 | T2 CARIBOU-WESTWOOD 4/085R RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-09-02 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549326 | T2 CARIBOU-WESTWOOD - 60 KV_004/081 | 92F
LC | 121882482 | 004/085 | T2 CARIBOU-WESTWOOD 4/85C RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-09-02 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549326 | T2 CARIBOU-WESTWOOD - 60 KV_004/081 | 92F
LC | 121882484 | 004/085 | T2 CARIBOU-WESTWOOD 04/085L RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-09-02 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549326 | T2 CARIBOU-WESTWOOD - 60 KV_004/081 | 92F
LC | 121882643 | 005/105 | T2 CARIBOU-WESTWOOD 5/105L RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-09-03 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 | Fire | Emergency | Replace | 31549093 | CARIBOU-WESTWOOD_005/110 | 92F
LC | 121882646 | 004/093 | T2 CARIBOU-WESTWOOD 4/093R RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-09-05 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549326 | T2 CARIBOU-WESTWOOD - 60 KV_004/081 | 92F
LC | 121882661 | 005/105 | T2 CARIBOU-WESTWOOD 5/105R RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-09-03 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 | Fire | Emergency | Replace | 31549093 | CARIBOU-WESTWOOD_005/110 | 92F
LC | 121882662 | 005/105 | T2 CARIBOU-WESTWOOD 005/105C RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-09-03 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 | Fire | Emergency | Replace | 31549093 | CARIBOU-WESTWOOD_005/110 | 92F
LC | 121882663 | 005/103 | T2 CARIBOU-WESTWOOD 5/103 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-10 | 2021-08-10 | 2021-09-03 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549093 | CARIBOU-WESTWOOD_005/110 | 92F
LC | 121882665 | 005/097 | T2 CARIBOU-WESTWOOD 5/097 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-10 | 2021-08-10 | 2021-09-04 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549093 | CARIBOU-WESTWOOD_005/110 | 92F
LC | 121882666 | 005/096 | T2 CARIBOU-WESTWOOD 5/096 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-10 | 2021-08-10 | 2021-08-27 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549093 | CARIBOU-WESTWOOD_005/110 | 92F
LC | 121882667 | 005/095 | T2 CARIBOU-WESTWOOD 5/095L RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-08-28 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 | Fire | Emergency | Replace | 31549093 | CARIBOU-WESTWOOD_005/110 | 92F
LC | 121882668 | 005/095 | T2 CARIBOU-WESTWOOD 05/095C RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-08-28 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 | Fire | Emergency | Replace | 31549093 | CARIBOU-WESTWOOD_005/110 | 92F
LC | 121882669 | 005/095 | T2 CARIBOU-WESTWOOD 5/095R RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-08-28 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 | Fire | Emergency | Replace | 31549093 | CARIBOU-WESTWOOD_005/110 | 92F
LC | 121882680 | 005/104 | T2 CARIBOU-WESTWOOD 5/104 COMPLETE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-10 | 2021-08-10 | 2021-08-26 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549093 | CARIBOU-WESTWOOD_005/110 | 92F
LC | 121882682 | 005/098 | T2 CARIBOU-WESTWOOD_005/098L RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-09-03 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 | Fire | Emergency | Replace | 31549093 | CARIBOU-WESTWOOD_005/110 | 92F
LC | 121882691 | 004/094 | T2 CARIBOU-WESTWOOD 4/094 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-10 | 2021-08-10 | 2021-09-02 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549326 | T2 CARIBOU-WESTWOOD - 60 KV_004/081 | 92F
LC | 121882695 | 004/093 | T2 CARIBOU-WESTWOOD 4/93C RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-09-06 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549326 | T2 CARIBOU-WESTWOOD - 60 KV_004/081 | 92F
LC | 121882696 | 004/093 | T2 CARIBOU-WESTWOOD 4/093L RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-09-06 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549326 | T2 CARIBOU-WESTWOOD - 60 KV_004/081 | 92F
LC | 121882759 | 004/092 | T2 CARIBOU-WESTWOOD 4/092C RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-09-04 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549326 | T2 CARIBOU-WESTWOOD - 60 KV_004/081 | 92F
LC | 121882777 | 004/089 | T2 CARIBOU-WESTWOOD 4/089 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-10 | 2021-08-10 | 2021-09-05 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549326 | T2 CARIBOU-WESTWOOD - 60 KV_004/081 | 92F
LC | 121882779 | 004/088 | T2 EI CARIBOU-WESTWOOD 4/88 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-10 | 2021-08-10 | 2021-09-06 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549326 | T2 CARIBOU-WESTWOOD - 60 KV_004/081 | 92F
LC | 121882790 | 004/092 | T2 CARIBOU-WESTWOOD 4/092R RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-09-04 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549326 | T2 CARIBOU-WESTWOOD - 60 KV_004/081 | 92F
LC | 121882791 | 004/092 | T2 CARIBOU-WESTWOOD 4/092L RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-10 | 2021-08-10 | 2021-09-04 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549326 | T2 CARIBOU-WESTWOOD - 60 KV_004/081 | 92F
LC | 121882792 | 004/091 | T2 CARIBOU-WESTWOOD 4/091 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-10 | 2021-08-10 | 2021-09-05 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549326 | T2 CARIBOU-WESTWOOD - 60 KV_004/081 | 92F
LC | 121883141 | 065/001 | T2 HUMBOLDT-TRINITY 65/1L RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-08-11 | 2021-08-11 | 2021-08-20 | 2022-08-11 | 2021-11-11 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549273 | T2 WV HMBLDT-TRNITY 52/4 RPL INSW | 92F
LC | 121883143 | 020/007 | T2 TRINTY-MPLE CRK 20/7L RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-11 | 2021-08-11 | 2021-08-25 | 2022-08-11 | 2021-11-11 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31549274 | T2 TRINTY-MPLE CRK 20/7 RPL STRW | 92F
LC | 121883163 | 020/008 | T2 TRINTY-MPLE CRK 20/8L RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2021-08-11 | 2021-08-11 | 2021-08-26 | 2022-08-11 | 2021-11-11 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549274 | T2 TRINTY-MPLE CRK 20/7 RPL STRW | 92F
LC | 121883328 | 063/004 | T2 EI HUMBOLDT-TRINITY 63/4L RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-08-11 | 2021-08-10 | 2021-08-27 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | POHW NONR COMP OH FMOB TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31549273 | T2 WV HMBLDT-TRNITY 52/4 RPL INSW | 92F
LC | 121883913 | 018/003 | NPR T2 TRINITY-MAPLE CRK 18/3B | EUREKA | ETL.8170.POLE.NWOD | 2021-08-11 | 2021-08-10 | 2021-08-21 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | POHW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549278 | NPR T2 TRINITY-MAPLE CRK 18/3A RPL STRW | 92F
LC | 121883914 | 018/003C | NPR T2 TRINITY-MAPLE CRK 18/3C | EUREKA | ETL.8170.POLE.WOOD | 2021-08-11 | 2021-08-10 | 2021-08-21 | 2022-08-10 | 2021-11-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | POHW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549278 | NPR T2 TRINITY-MAPLE CRK 18/3A RPL STRW | 92F
LC | 121889184 | 065/001 | T2 HUMBOLDT-TRINITY 65/1R RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-08-12 | 2021-08-11 | 2021-08-20 | 2022-08-11 | 2021-11-11 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | POHW NONR COMP OH FMOB TR2 PRTO AIR | Fire | Emergency | Replace | 31549273 | T2 WV HMBLDT-TRNITY 52/4 RPL INSW | 92F
LC | 121889185 | 065/001 | T2 HUMBOLDT-TRINITY 65/1C RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-08-12 | 2021-08-11 | 2021-08-20 | 2022-08-11 | 2021-11-11 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | POHW NONR COMP OH FMOB TR2 PRTO AIR | Fire | Emergency | Replace | 31549273 | T2 WV HMBLDT-TRNITY 52/4 RPL INSW | 92F
LC | 121894212 | 000/005 | T3 WV CENTERVILLE-TABLE MTN 0/5 RPR INSW | TABLEMTN | ETL.6320.INSL.NCER | 2021-08-12 | 2021-08-12 | 2021-08-28 | 2022-02-08 | 2021-11-12 | On-time | 630 | Upgraded | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 121896288 | 013/005 | T2 TRINITY-MAPLE CREEK 013/005 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2021-08-13 | 2021-08-13 | 2021-09-09 | 2022-08-13 | 2021-11-13 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549487 | T2 TRINITY-MAPLE CREEK 013/005 RPL POLE | 92F
LC | 121897212 | 020/008 | T2 TRINTY-MPLE CRK 20/8R RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2021-08-13 | 2021-08-11 | 2021-08-26 | 2022-08-11 | 2021-11-11 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | POHW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31549274 | T2 TRINTY-MPLE CRK 20/7 RPL STRW | 92F
LC | 121897258 | 020/008 | T2 TRINTY-MPLE CRK 20/8C RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2021-08-13 | 2021-08-11 | 2021-08-26 | 2022-08-11 | 2021-11-11 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | POHW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31549274 | T2 TRINTY-MPLE CRK 20/7 RPL STRW | 92F
LC | 121897317 | 020/007 | T2 TRINTY-MPLE CRK 20/7R RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-13 | 2021-08-11 | 2021-08-25 | 2022-08-11 | 2021-11-11 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | POHW NONR COMP OH FMOB TR2 FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31549274 | T2 TRINTY-MPLE CRK 20/7 RPL STRW | 92F
LC | 121897340 | 020/007 | T2 TRINTY-MPLE CRK 20/7C RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-13 | 2021-08-11 | 2021-08-25 | 2022-08-11 | 2021-11-11 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | POHW NONR COMP OH FMOB TR2 FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31549274 | T2 TRINTY-MPLE CRK 20/7 RPL STRW | 92F
LC | 121900619 | 061/005 | T2 HUMBOLDT-TRINITY 61/005 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-08-13 | 2021-08-13 | 2021-09-07 | 2022-08-13 | 2021-11-13 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31549273 | T2 WV HMBLDT-TRNITY 52/4 RPL INSW | 92F
LC | 121900639 | 015/007 | T2 TRINITY-MAPLE CREEK 15/7 RPL INSW | EUREKA | ETL.8170.INSL.CERA | 2021-08-13 | 2021-08-13 | 2021-09-03 | 2022-08-13 | 2021-11-13 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31549277 | T2 TRINITY-MAPLE CREEK 15/00 RPL STRW | 92F
LC | 121900658 | 016/000 | T2 TRINITY-MAPLE CREEK 16/0 RPL INSW | EUREKA | ETL.8170.INSL.NCER | 2021-08-13 | 2021-08-13 | 2021-09-08 | 2022-08-13 | 2021-11-13 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31549711 | T2 TRINITY-MAPLE CREEK 16/0 RPL INSW | 93I
LC | 121900686 | 015/008 | T2 TRINITY-MAPLE CREEK 15/8 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-13 | 2021-08-13 | 2021-09-12 | 2022-08-13 | 2021-11-13 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549277 | T2 TRINITY-MAPLE CREEK 15/00 RPL STRW | 92F
LC | 121900729 | 016/004 | T2 TRINITY-MAPLE CREEK 16/4L RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-13 | 2021-08-13 | 2021-09-01 | 2022-08-13 | 2021-11-13 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31549711 | T2 TRINITY-MAPLE CREEK 16/0 RPL INSW | 93I
LC | 121902603 | 094/001 | T2 HUMBOLDT-TRINITY 94/1 COTR KEY | EUREKA | ETL.1820.POLE.WDPS | 2021-08-14 | 2021-08-14 | 2021-08-25 | 2022-08-14 | 2021-11-14 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 44949333 | T2 HUMBOLDT-TRINITY 94/1 COTR KEY | ICW
LC | 121903470 | 001/026 | T2 CARIBOU-WESTWOOD 001/026 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-14 | 2021-08-14 | 2021-09-13 | 2022-08-14 | 2021-11-14 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549710 | T2 CARIBOU-WESTWOOD 001/026 RPL POLE | 92F
LC | 121908332 | ;000/032 | T2 CARIBOU #2 ;000/032 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-08-16 | 2021-08-16 | 2021-09-01 | 2022-08-16 | 2021-11-16 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121908336 | ;000/033 | T2 CARIBOU #2 ;000/033 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-08-16 | 2021-08-16 | 2021-09-04 | 2022-08-16 | 2021-11-16 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F
LC | 121910394 | 009/041 | T3 GEYSERS #12-FULTON 9/41 COTTER KEY | LAKEVLLE | ETL.4750.INSL.CERA | 2021-08-17 | 2021-08-17 | 2021-11-02 | 2022-02-13 | 2021-11-17 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 44856539 | T3 DI GEYSERS #12-FULTON 1/7 RPR INSS | ICS
LC | 121913757 | -017/007 | T3 FULTON-CALISTOGA -017/007 RPL INSS | LAKEVLLE | ETL.6880.INSL.NCER | 2021-08-17 | 2021-08-17 | 2021-08-18 | 2022-02-13 | 2022-08-17 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31550994 | T3 FULTON-CALISTOGA -017/007 RPL INSS | 93I
LC | 121914250 | 003/016 | T2 HUMBLDT BY-HUMBLDT #2 3/16 RPR CONDS | EUREKA | ETL.7090.INSL | 2021-08-17 | 2021-08-17 | 2021-08-19 | 2022-08-17 | 2021-11-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 44950900 | T2 HUMBLDT BY-HUMBLDT #2 3/16 RPR CONDS | ICS
LC | 121918467 | 017/071 | T2 TESLA-METCALF 17/071 COTTER | METCALF | ETL.6110.INSL | 2021-08-18 | 2021-08-18 | 2021-09-03 | 2022-08-18 | 2021-11-18 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 44953816 | T2 TESLA-METCALF 17/071 COTTER | ICS
LC | 121920527 | 016/004 | T2 TRINITY-MAPLE CREEK 16/4C RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-19 | 2021-08-13 | 2021-09-01 | 2022-08-13 | 2021-11-13 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | POHW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549711 | T2 TRINITY-MAPLE CREEK 16/0 RPL INSW | 93I
LC | 121920528 | 016/004 | T2 TRINITY-MAPLE CREEK 16/4R RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-19 | 2021-08-13 | 2021-09-01 | 2022-08-13 | 2021-11-13 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | POHW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549711 | T2 TRINITY-MAPLE CREEK 16/0 RPL INSW | 93I
LC | 121921635 | 016/005 | T2 TRINITY-MAPLE CREEK 16/5 GRWSH INSLW | EUREKA | ETL.8170.POLE.STPS | 2021-08-19 | 2021-08-19 | 2021-08-21 | 2022-08-19 | 2021-11-19 | On-time | 622 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 FRAB | Contaminated | Insulator | Ground Wash | 44970421 | T2 TRINITY-MAPLE CREEK 16/5 GRWSH INSLW | ICD
LC | 121921670 | 016/007 | T2 TRINITY-MAPLE CREEK 16/7 RPL INSLW | EUREKA | ETL.8170.INSL.CERA | 2021-08-19 | 2021-08-19 | 2021-08-20 | 2022-08-19 | 2021-11-19 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31549777 | T2 TRINITY-MAPLE CREEK 18/8 RPL INSLW | 92F
LC | 121921673 | 016/010 | T2 TRINITY-MAPLE CREEK 16/010 RPL INSLW | EUREKA | ETL.8170.INSL.NCER | 2021-08-19 | 2021-08-19 | 2021-08-21 | 2022-08-19 | 2021-11-19 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31549777 | T2 TRINITY-MAPLE CREEK 18/8 RPL INSLW | 92F
LC | 121921679 | 018/008 | T2 TRINITY-MAPLE CREEK 18/8 RPL INSLW | EUREKA | ETL.8170.INSL | 2021-08-19 | 2021-08-19 | 2021-08-20 | 2022-08-19 | 2021-11-19 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31549777 | T2 TRINITY-MAPLE CREEK 18/8 RPL INSLW | 92F
LC | 121921809 | 016/008 | T2 TRINITY-MAPLE CREEK 16/8 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-19 | 2021-08-19 | 2021-12-15 | 2022-08-19 | 2021-11-19 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31550342 | T2 TRINITY-MAPLE CREEK 16/8 RPL STRW | 70Y
LC | 121940323 | 001/033A | T2 CARIBOU-WESTWOOD 1/033A RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-23 | 2021-08-23 | 2021-09-15 | 2022-08-23 | 2021-11-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549710 | T2 CARIBOU-WESTWOOD 001/026 RPL POLE | 92F
LC | 121940352 | 001/033C | T2 CARIBOU-WESTWOOD 1/033C RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-23 | 2021-08-23 | 2021-09-15 | 2022-08-23 | 2021-11-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549710 | T2 CARIBOU-WESTWOOD 001/026 RPL POLE | 92F
LC | 121940356 | 001/031 | T2 CARIBOU-WESTWOOD 01/031R RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-23 | 2021-08-23 | 2021-09-16 | 2022-08-23 | 2021-11-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549710 | T2 CARIBOU-WESTWOOD 001/026 RPL POLE | 92F
LC | 121940363 | 001/033B | T2 CARIBOU-WESTWOOD 01/033B RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-23 | 2021-08-23 | 2021-09-15 | 2022-08-23 | 2021-11-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549710 | T2 CARIBOU-WESTWOOD 001/026 RPL POLE | 92F
LC | 121940382 | 001/032 | T2 CARIBOU-WESTWOOD 1/032 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-23 | 2021-08-23 | 2021-09-15 | 2022-08-23 | 2021-11-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549710 | T2 CARIBOU-WESTWOOD 001/026 RPL POLE | 92F
LC | 121940431 | 001/031 | T2 CARIBOU-WESTWOOD 1/031C RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-23 | 2021-08-23 | 2021-09-15 | 2022-08-23 | 2021-11-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549710 | T2 CARIBOU-WESTWOOD 001/026 RPL POLE | 92F
LC | 121940435 | 001/031 | T2 CARIBOU-WESTWOOD 1/031L RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-23 | 2021-08-23 | 2021-09-15 | 2022-08-23 | 2021-11-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549710 | T2 CARIBOU-WESTWOOD 001/026 RPL POLE | 92F
LC | 121940474 | 001/028 | T2 CARIBOU-WESTWOOD 1/28L RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-23 | 2021-08-23 | 2021-09-15 | 2022-08-23 | 2021-11-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549710 | T2 CARIBOU-WESTWOOD 001/026 RPL POLE | 92F
LC | 121940478 | 001/028 | T2 CARIBOU-WESTWOOD 1/28R RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-23 | 2021-08-23 | 2021-09-15 | 2022-08-23 | 2021-11-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549710 | T2 CARIBOU-WESTWOOD 001/026 RPL POLE | 92F
LC | 121940483 | 001/030 | T2 CARIBOU-WESTWOOD 1/030 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-23 | 2021-08-23 | 2021-09-15 | 2022-08-23 | 2021-11-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549710 | T2 CARIBOU-WESTWOOD 001/026 RPL POLE | 92F
LC | 121940484 | 001/029 | T2 CARIBOU-WESTWOOD 1/029 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2021-08-23 | 2021-08-23 | 2021-09-15 | 2022-08-23 | 2021-11-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31549710 | T2 CARIBOU-WESTWOOD 001/026 RPL POLE | 92F
LC | 121940508 | 001/028 | T2 CARIBOU-WESTWOOD 1/028 RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2021-08-23 | 2021-08-23 | 2021-09-15 | 2022-08-23 | 2021-11-23 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31549710 | T2 CARIBOU-WESTWOOD 001/026 RPL POLE | 92F
LC | 121946908 | 006/050 | T2 DI TRINITY-COTTONWOOD 6/50A RPL POLE | TABLEMTN | ETL.4040.POLE.WDPS | 2021-08-24 | 2021-08-14 | 2021-09-18 | 2022-08-14 | 2021-11-14 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31550521 | T2 DI TRINITY-COTTONWOOD 6/50A RPL POLE | 70Y
LC | 121947055 | 008/077 | T2 COTTONWOOD-BENTON 8/77L RPL POLE | TABLEMTN | ETL.6650.POLE.WDPS | 2021-08-24 | 2021-08-14 | 2021-11-08 | 2022-08-14 | 2021-11-14 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31550520 | T2 COTTONWOOD-BENTON 8/77 RPL POLE | 70Y
LC | 121948669 | 022/255 | WV T3 IGNACIO-BOLINAS #2 22/255 RPL DMW | LAKEVLLE | ETL.7180.POLE.WDPS | 2021-08-24 | 2021-08-24 | 2021-11-19 | 2022-02-20 | 2021-11-24 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Damper-Wood | Replace | 44955289 | T3 IGNACIO-BOLINAS #2 - 60 KV_022/255 | ICW
LC | 121955881 | 008/077 | T2 CTTNWD-BENTN #2 8/77R RPL POLE | TABLEMTN | ETL.6650.POLE.WDPS | 2021-08-25 | 2021-08-14 | 2021-11-08 | 2022-08-14 | 2021-11-14 | On-time | 372 | Upgraded | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR FRAB | Rotten | Structure-Wood | Replace | 31550520 | T2 COTTONWOOD-BENTON 8/77 RPL POLE | 70Y
LC | 121955883 | 006/050 | T2 DI TRINITY-COTTONWOOD 6/50R RPL POLE | TABLEMTN | ETL.4040.POLE.WDPS | 2021-08-25 | 2021-08-14 | 2021-09-18 | 2022-08-14 | 2021-11-14 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 2 | POHW COMP OH TR2 PRTO AIR FRAB | Rotten | Structure-Wood | Replace | 31550521 | T2 DI TRINITY-COTTONWOOD 6/50A RPL POLE | 70Y
LC | 121957235 | 008/070 | T2 SALT SPRINGS-TIGER CREEK 8/70 RMV VEG | VICTOR | ETL.3500.TOWR | 2021-08-25 | 2021-08-25 | 2021-11-04 | 2022-08-25 | 2021-11-25 | On-time | 564 | B - Urgt Compliance | Closed | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 121959112 | -013/004 | T3 WV FULTON-CALISTOGA -013/004 RMV ENCR | LAKEVLLE | ETL.6880.POLE.NWOD | 2021-08-26 | 2021-08-26 | 2021-11-18 | 2022-02-22 | 2021-11-26 | On-time | 931 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | Encroachment | Right of Way | Remove | 45078427 | T3 WV FULTON-CALISTOGA -013/004 RMV ENCR | CHR
LC | 121966544 | 002/000 | T2 RACETRACK TP 2/0 RPL PL WASH FIRE | VICTOR | ETL.2393.POLE.WOOD | 2021-08-27 | 2021-08-27 | 2021-09-01 | 2022-08-27 | 2021-11-27 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31550494 | T2 RACETRACK TP 2/1 RPL PL WASH FIRE | 92F
LC | 121966558 | 002/001 | T2 RACETRACK TP 2/1 RPL PL WASH FIRE | VICTOR | ETL.2393.POLE.WOOD | 2021-08-27 | 2021-08-27 | 2021-09-01 | 2022-08-27 | 2021-11-27 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31550494 | T2 RACETRACK TP 2/1 RPL PL WASH FIRE | 92F
LC | 121983049 | 033/137 | T2 TESLA-METCALF 33/137 COTTER | METCALF | ETL.6110.INSL.CERA | 2021-09-01 | 2021-09-01 | 2021-09-22 | 2022-09-01 | 2021-12-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44970482 | T2 TESLA-METCALF 33/137 COTTER | ICS
LC | 121983949 | 000/008B | T2 COLGATE-SMARTVILLE #1 0/8B RPR CNDW | SACTO | ETL.6510.POLE.WOOD | 2021-09-01 | 2021-09-01 | 2021-11-16 | 2022-09-01 | 2021-12-01 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Conductor-Wood | Repair | 44982112 | T2 COLGATE-SMARTVILLE #1 0/8B RPR CNDW | ICW
LC | 121985890 | 004/090 | T2 CARIBOU-WESTWOOD 4/90 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2021-09-01 | 2021-09-01 | 2021-09-05 | 2022-09-01 | 2021-12-01 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31550868 | T2 CARIBOU-WESTWOOD 4/90 RPL STRW | 92F
LC | 121986683 | 009/002A | T2 MELONES-CURTIS 009/002A RPR SWITCH | VICTOR | ETL.2390.SWIT | 2021-09-01 | 2021-09-01 | 2021-10-14 | 2022-09-01 | 2021-12-01 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Out of Adjustment | Switch | Repair | 44962495 | T2 MELONES-CURTIS 009/002A RPR SWITCH | ICE
LC | 121989035 | :023/194 | T2 DI CARBOU-PALRMO :23/194 RPR INSS | TABLEMTN | ETL.3190.INSL.CERA | 2021-09-02 | 2021-09-02 | 2021-10-09 | 2022-09-02 | 2021-12-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44979145 | T2 DI CARBOU-PALRMO :23/194 RPR INSS | ICS
LC | 121989858 | 004/084 | T2 CARIBOU-WESTWOOD 04/084 REFRAME | TABLEMTN | ETL.6300.POLE.WOOD | 2021-09-02 | 2021-09-02 | 2021-09-03 | 2022-09-02 | 2021-12-02 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31551142 | T2 CARIBOU-WESTWOOD 04/084 REFRAME | 92F
LC | 122001300 | 000/006 | T2 DI BKS CRK-RK CK-CRA 0/6 COTTER | TABLEMTN | ETL.4430.INSL.NCER | 2021-09-04 | 2021-09-03 | 2021-11-29 | 2022-09-03 | 2021-12-03 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 44979331 | T2 DI BKS CRK-RK CK-CRA 0/6 COTTER | ICS
LC | 122003182 | 008/010 | T2 CARIBOU-PLUMAS JCT 008/010 RPL POLE | TABLEMTN | ETL.6290.POLE.WOOD | 2021-09-04 | 2021-09-04 | 2021-11-09 | 2022-09-04 | 2021-12-04 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31551415 | T2 CARIBOU-PLUMAS JCT 008/010 RPL POLE | 92F
LC | 122006657 | :002/001 | T2 CARIBOU #2 :002/001 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-09-07 | 2021-09-07 | 2021-11-03 | 2022-09-07 | 2021-12-07 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31551140 | T2 DI CARIBOU #2 :6/5 RPLC STRW | 92F
LC | 122015716 | 023/096B | T2 TESLA-METCALF 23/096B COTTER | METCALF | ETL.6110.INSL | 2021-09-08 | 2021-09-08 | 2021-09-21 | 2022-09-08 | 2021-12-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 44980243 | T2 TESLA-METCALF 23/096B COTTER | ICS
LC | 122016403 | 075/002 | T2 EI HUMBOLDT-TRINITY 75/2 RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2021-09-08 | 2021-08-26 | 2021-11-18 | 2022-08-26 | 2021-11-24 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 44980270 | T2 EI HUMBOLDT-TRINITY 75/2 RPR INSW | ICW
LC | 122019645 | 008/070 | T3 IR MIDDLE FORK-GLD HILL 8/70 RPR CONS | SACTO | ETL.5140.TOWR | 2021-09-09 | 2021-09-09 | 2021-11-16 | 2022-03-08 | 2021-12-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Conductor-Steel | Repair | 44988272 | T3 IR MIDDLE FORK-GLD HILL 8/70 RPR CONS | ICS
LC | 122019663 | 008/068 | T3 IR MIDDLE FRK GLD HILL 8/68 RPR CONS | SACTO | ETL.5140.TOWR | 2021-09-09 | 2021-09-09 | 2021-11-10 | 2022-03-08 | 2021-12-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Conductor-Steel | Repair | 44988271 | T3 IR MIDDLE FRK GLD HILL 8/68 RPR CONS | ICS
LC | 122021528 | 009/067 | T2 GREEN VALLEY-LLAGAS 9/67 INS MKBL | MOSSLNDG | ETL.1720.INSL.NCER | 2021-09-09 | 2021-09-09 | 2021-11-22 | 2022-09-09 | 2021-12-09 | On-time | 671 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | Missing | FAA Lighting-Wood | Install | 31551644 | T2 GREEN VALLEY-LLAGAS 9/67 INS MKBL | 93P
LC | 122035897 | 016/317 | T2 HAT CRK #1-WESTWD 16/317 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2021-09-10 | 2021-09-10 | 2021-09-11 | 2022-09-10 | 2021-12-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31551525 | T2 HAT CRK #1-WESTWD 16/317 RPL STRW | 92F
LC | 122036503 | 016/325 | T2 HAT CREEK #1-WESTWOOD 16/325 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2021-09-10 | 2021-09-10 | 2021-09-11 | 2022-09-10 | 2021-12-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31551525 | T2 HAT CRK #1-WESTWD 16/317 RPL STRW | 92F
LC | 122036506 | 016/326 | T2 HAT CREEK #1-WESTWOOD 16/326 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2021-09-10 | 2021-09-10 | 2021-09-11 | 2022-09-10 | 2021-12-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31551525 | T2 HAT CRK #1-WESTWD 16/317 RPL STRW | 92F
LC | 122036507 | 017/328 | T2 HAT CREEK #1-WESTWOOD 17/328 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2021-09-10 | 2021-09-10 | 2021-09-11 | 2022-09-10 | 2021-12-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31551525 | T2 HAT CRK #1-WESTWD 16/317 RPL STRW | 92F
LC | 122036509 | 017/329 | T2 HAT CREEK #1-WESTWOOD 17/329 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2021-09-10 | 2021-09-10 | 2021-09-11 | 2022-09-10 | 2021-12-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31551525 | T2 HAT CRK #1-WESTWD 16/317 RPL STRW | 92F
LC | 122036571 | 017/338 | T2 HAT CREEK #1-WESTWOOD 17/338 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2021-09-10 | 2021-09-10 | 2021-09-11 | 2022-09-10 | 2021-12-10 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW OTHR COMP OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31551525 | T2 HAT CRK #1-WESTWD 16/317 RPL STRW | 92F
LC | 122040809 | 001/034 | T2 CARIBOU-WSTWD 1/34 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2021-09-12 | 2021-09-12 | 2021-09-15 | 2022-09-12 | 2021-12-12 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31551921 | T2 CARIBOU-WSTWD 1/34 RPL STRW | 70Y
LC | 122040848 | 001/035 | T2 CARIBOU-WESTWOOD 1/035 RPL INSW | TABLEMTN | ETL.6300.POLE.WDPS | 2021-09-12 | 2021-09-12 | 2021-09-15 | 2022-09-12 | 2021-12-12 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO | Fire | Emergency | Replace | 31552132 | T2 CARIBOU-WESTWOOD 1/035 RPL INSW | 92F
LC | 122063628 | 001/020 | T3 MIDDLEFORK #1 1/020 RPR SWITCH | SACTO | ETL.8405.SWIT | 2021-09-17 | 2021-09-17 | 2021-10-17 | 2022-03-16 | 2021-12-17 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO | Out of Adjustment | Switch | Repair | 45011107 | T3 MIDDLEFORK #1 1/020 RPR SWITCH | ICE
LC | 122068658 | 015/132 | T3 DRUM-RIO OSO #2 15/132 RPR SWITCH | SACTO | ETL.1430.SWIT | 2021-09-18 | 2021-09-17 | 2021-09-17 | 2022-03-16 | 2021-12-17 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 | Out of Adjustment | Switch | Repair | 44986515 | T3 DRUM-RIO OSO #2 15/132 RPR SWITCH | ICE
LC | 122068720 | 015/132 | T3 DRUM-RIO OSO #1 015/132 RPR SWITCH | SACTO | ETL.1420.SWIT | 2021-09-18 | 2021-09-17 | 2021-09-17 | 2022-03-16 | 2021-12-17 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 | Out of Adjustment | Switch | Repair | 44986570 | T3 DRUM-RIO OSO #1 015/132 RPR SWITCH | ICE
LC | 122069417 | 000/002 | T3 BRUNSWICK #1 TAP 000/002 RPR SWTC | SACTO | ETL.1422.SWIT | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2022-03-17 | 2021-12-18 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH FMOB TR3 | Out of Adjustment | Switch | Repair | 44986656 | T3 BRUNSWICK #1 TAP 000/002 RPR SWTC | ICE
LC | 122069423 | 000/002 | T3 RUNSWICK #2 TAP 000/002 RPR SWTC | SACTO | ETL.1431.SWIT | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2022-03-17 | 2021-12-18 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 | Out of Adjustment | Switch | Repair | 44986657 | T3 RUNSWICK #2 TAP 000/002 RPR SWTC | ICE
LC | 122099471 | 001/016 | T2 MTN GATE JCT-CASCADE 1/16L RPL POLE | TABLEMTN | ETL.7640.POLE.WDPS | 2021-09-24 | 2021-09-24 | 2021-09-28 | 2022-09-24 | 2021-12-24 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31552724 | MOUNTAIN GATE JCT-CASCADE 1/16R RPL POLE | 92F
LC | 122099480 | 001/015 | T2 MTN GATE JCT-CASCADE 1/15R RPL POLE | TABLEMTN | ETL.7640.POLE.WDPS | 2021-09-24 | 2021-09-24 | 2021-09-28 | 2022-09-24 | 2021-12-24 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 2 | REGW NONR COMP OH FMOB TR2 FRAB | Fire | Emergency | Replace | 31552724 | MOUNTAIN GATE JCT-CASCADE 1/16R RPL POLE | 92F
LC | 122107256 | 036/005 | T2 FORT ROSS-GUALALA 36/5C RPR GYWS | LAKEVLLE | ETL.6980.POLE.STPS | 2021-09-27 | 2021-07-30 | 2021-10-28 | 2022-07-30 | 2021-10-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 44993921 | T2 FORT ROSS-GUALALA 36/5C RPR GYWS | ICS
LC | 122142643 | 009/151 | ATSCDRO-SN LS OBISPO 9/151 GRND WSH | PISMOBCH | ETL.8490.TOWR | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2022-04-02 | 2022-01-04 | On-time | 622 | B - Urgt Compliance | Closed | HFTD 3 | RELW NONR COMP OH FMOB TR3 FRAB | Contaminated | Insulator | Ground Wash | 44999333 | ATSCDRO-SN LS OBISPO 9/151 GRND WSH | ICD
LC | 122170872 | 012/176 | T3 DI WEIMAR #1 012/176 INS COTTER | SACTO | ETL.7560.INSL.NCER | 2021-10-09 | 2021-10-08 | 2022-02-04 | 2022-04-06 | 2022-01-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45011998 | T3 DI WEIMAR #1 012/176 INS COTTER | ICW
LC | 122171899 | 011/169 | T3 DI WEIMAR #1 11/169 INS COTTER | SACTO | ETL.7560.INSL.NCER | 2021-10-09 | 2021-10-08 | 2022-02-04 | 2022-04-06 | 2022-01-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45012025 | T3 DI WEIMAR #1 11/169 INS COTTER | ICW
LC | 122198963 | 015/109A | T2 DI HELMS GRG #1 15/109A INS COTTER | FRESNO | ETL.4870.INSL | 2021-10-13 | 2021-10-13 | 2021-12-17 | 2022-10-13 | 2022-01-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45014567 | T2 DI HELMS GRG #1 15/109A INS COTTER | ICS
LC | 122213359 | 028/000 | T2 DI MENDO-WLLTS-FT BRGG 28/00 COTR KEY | LAKEVLLE | ETL.7550.INSL.NCER | 2021-10-15 | 2021-10-14 | 2021-11-17 | 2022-10-14 | 2022-01-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45014660 | T2 DI MENDO-WLLTS-FT BRGG 28/00 COTR KEY | ICW
LC | 122216426 | 004/051A | T3 DI DRM-RIO OSO #2 4/51A RPR INSS CTTR | SACTO | ETL.1430.INSL.CERA | 2021-10-16 | 2021-10-13 | 2021-12-09 | 2022-04-11 | 2022-01-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45016591 | T3 DI DRM-RIO OSO #2 4/51A RPR INSS CTTR | ICS
LC | 122216743 | 114/001 | T2 HUMBOLDT-BRIDGEVILLE 114/001 RPL HNGR | EUREKA | ETL.1810.INSL.NCER | 2021-10-16 | 2021-10-16 | 2022-04-07 | 2022-10-16 | 2022-01-16 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45015435 | T2 HUMBOLDT-BRIDGEVILLE 114/001 RPL HNGR | ICW
LC | 122229144 | 007/007 | T3 DI DONNELLS-MI-WUK 7/7 RPR SWITCH | VICTOR | ETL.1400.POLE.STPS | 2021-10-19 | 2021-10-13 | 2021-11-05 | 2022-04-11 | 2022-01-11 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | Out of Adjustment | Switch | Repair | 45018220 | T3 DI DONNELLS-MI-WUK 7/7 RPR SWITCH | ICE
LC | 122233538 | 000/001 | NRP T2 NARROWS #1 TAP 0/1 RPR SWTW | SACTO | ETL.6511.POLE.WOOD | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2022-10-20 | 2022-01-20 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | Out of Adjustment | Switch | Repair | 45018290 | NRP T2 NARROWS #1 TAP 0/1 RPR SWTW | ICE
LC | 122246640 | 009/239 | T2 DRUM-SPAULDING 9/239 RPR SWITCH | SACTO | ETL.6770.SWIT | 2021-10-22 | 2021-10-22 | 2022-05-04 | 2022-10-22 | 2022-01-22 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Out of Adjustment | Switch | Repair | 45061979 | T2 DRUM-SPAULDING 9/239 RPR SWITCH | ICE
LC | 122261636 | 110/003B | T2 EI HUMBOLDT-TRINITY 110/3B ANTI SPLIT | EUREKA | ETL.1820.POLE.WOOD | 2021-10-27 | 2021-10-26 | 2022-01-19 | 2022-10-26 | 2022-01-24 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45029029 | T2 EI HUMBOLDT-TRINITY 110/3C ANTI SPLIT | ICW
LC | 122261751 | 110/003C | T2 EI HUMBOLDT-TRINITY 110/3C ANTI SPLIT | EUREKA | ETL.1820.POLE.WOOD | 2021-10-27 | 2021-10-26 | 2022-01-19 | 2022-10-26 | 2022-01-24 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45029029 | T2 EI HUMBOLDT-TRINITY 110/3C ANTI SPLIT | ICW
LC | 122263317 | 073/371 | T2 DI MALIN-RND MTN #2 73/371 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2021-10-27 | 2021-10-26 | 2021-12-09 | 2022-10-26 | 2022-01-26 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45054564 | T2 DI MALIN-RND MTN #2 73/371 RPR OPGW | ICS
LC | 122266533 | 037/191A | T3 EI FULTON-PUEBLO 037/191A RPR SWTC | LAKEVLLE | ETL.1600.SWIT | 2021-10-27 | 2021-10-26 | 2021-11-02 | 2022-04-24 | 2022-01-24 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR | Out of Adjustment | Switch | Repair | 45029601 | T3 EI FULTON-PUEBLO 037/191A RPR SWTC | ICE
LC | 122266534 | 037/191A | T3 EAGLE RK-FTN-SLVRDO 37/191A RPR SWCH | LAKEVLLE | ETL.4392.SWIT | 2021-10-27 | 2021-10-26 | 2021-11-02 | 2022-04-24 | 2022-01-24 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO | Out of Adjustment | Switch | Repair | 45029600 | T3 EAGLE RK-FTN-SLVRDO 37/191A RPR SWCH | ICE
LC | 122267855 | ;002/000 | T2 DI CARIBOU #2 ;2/00 RPR INSLW | TABLEMTN | ETL.6280.POLE.WOOD | 2021-10-28 | 2021-10-28 | 2021-11-18 | 2022-10-28 | 2022-01-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Wood | Repair | 45054566 | T2 DI CARIBOU #2 ;2/00 RPR INSLW | ICW
LC | 122269229 | 001/044 | T3 DI DEER CREEK-DRUM 1/44 REFRAME | SACTO | ETL.6690.POLE.WOOD | 2021-10-28 | 2021-10-28 | 2022-06-22 | 2022-04-26 | 2022-01-28 | Late | 637 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31591467 | T3 DI DEER CREEK-DRUM 1/44 REFRAME | 93E
LC | 122270145 | 014/185C | T3 DI WEIMAR #1 14/185C COTR KEY | SACTO | ETL.7560.POLE.WOOD | 2021-10-28 | 2021-10-28 | 2022-02-04 | 2022-04-26 | 2022-01-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45031065 | T3 DI WEIMAR #1 14/185C COTR KEY | ICW
LC | 122307607 | 187 | T2 MI-WUK-CURTIS 026/004 RPR SWITCH | VICTOR | ETL.1073.SWIT | 2021-11-03 | 2021-11-03 | 2021-11-09 | 2022-11-03 | 2022-02-03 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | Out of Adjustment | Switch | Repair | 45053543 | MI-WUK-CURTIS 026/004 RPR SWITCH | ICE
LC | 122392814 | 021/013 | T2 TULE-SPRINGVILLE 21/13 RPL STRW | MIDWAY | ETL.9040.POLE.WOOD | 2021-11-18 | 2021-11-06 | 2022-07-26 | 2022-11-06 | 2022-11-06 | On-time | 372 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31579993 | T2 TULE-SPRINGVILLE 21/13 RPL STRW | 70Y
LC | 122411674 | 019/086 | T2 DI MOSS LNDING-MTCLF 19/86 COTR KEY | MOSSLNDG | ETL.6050.TOWR | 2021-11-23 | 2021-11-23 | 2022-01-21 | 2022-11-23 | 2022-02-23 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Repair | 45082264 | T2 DI MOSS LNDING-MTCLF 19/86 COTR KEY | ICS
LC | 122426239 | 015/003 | T3 MAPLE CREEK-HOOPA 15/003 RPR CONDW | EUREKA | ETL.7490.POLE.WOOD | 2021-11-30 | 2021-11-30 | 2022-01-06 | 2022-05-29 | 2022-03-02 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW NONR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Conductor-Wood | Repair | 45082009 | T3 MAPLE CREEK-HOOPA 15/003 RPR CONDW | ICW
LC | 122446786 | 009/131 | T3 MIDDLE FORK #1 009/131 RPR GWRW | SACTO | ETL.8405.POLE.WOOD | 2021-12-06 | 2021-12-02 | 2021-12-08 | 2022-05-31 | 2022-03-02 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW NONR COMP OH FMOB TR3 FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45082865 | T3 MIDDLE FORK #1 009/131 RPR GWRW | ICW
LC | 122489637 | A002/031 | T2 NARROWS #2 TAP A002/031 RPR SWTCHW | SACTO | ETL.6521.POLE.WOOD | 2021-12-15 | 2021-12-15 | 2022-03-15 | 2022-12-15 | 2022-03-15 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 2 | RELW NONR COMP OH FMOB TR2 PRTO FRAB | Out of Adjustment | Switch | Repair | 45106506 | T2 NARROWS #2 TAP A002/031 RPR SWTCHW | ICE
LC | 122493784 | 148/O | T2 DI BRIGHTON-OLEUM JT 148/O COTR KEY | CONCORD | ETL.1162.POLE.WOOD | 2021-12-16 | 2021-12-15 | 2022-01-28 | 2022-12-15 | 2022-03-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Wood | Repair | 45097155 | T2 DI BRIGHTON-OLEUM JT 148/O COTR KEY | ICW
LC | 122499256 | 148/H | T2 DI BRIGHTON-OLEUM JT 148/H RPR CNDW | CONCORD | ETL.1162.INSL.NCER | 2021-12-17 | 2021-12-16 | 2022-02-24 | 2022-12-16 | 2022-03-16 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45101992 | T2 DI BRIGHTON-OLEUM JT 148/H RPR CNDW | ICW
LC | 122499258 | 148/H | T2 DI BRIGHTON-OLEUM 148/H RPL/RMV CRSW | CONCORD | ETL.1162.POLE.WDPS | 2021-12-17 | 2021-12-16 | 2022-02-24 | 2022-12-16 | 2022-03-16 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45101989 | T2 DI BRIGHTON-OLEUM 148/H RPL/RMV CRSW | ICW
LC | 122499327 | 148/H | T2 DI BRIGHTON-OLEUM JT 148/H RPL INSW | CONCORD | ETL.1162.INSL.NCER | 2021-12-17 | 2021-12-16 | 2022-02-24 | 2022-12-16 | 2022-03-16 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31596475 | T2 DI BRIGHTON-OLEUM JT 148/H RPL INSW | 93I
LC | 122507061 | 016/125 | T3 PARADISE-TABLE MTN 16/125 RPR STRT | TABLEMTN | ETL.4316.TOWR | 2021-12-21 | 2021-12-21 | 2022-02-02 | 2022-06-19 | 2022-03-21 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45106495 | T3 PARADISE-TABLE MTN 16/125 RPR STRT | ICQ
LC | 122511850 | C010/044 | WV CBRN-AGLS SW ST-PNCH C10/44 INS DMPS | MOSSLNDG | ETL.4460.INSL | 2021-12-22 | 2021-12-22 | 2022-02-18 | 2022-12-22 | 2022-03-22 | On-time | 628 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO NTDE | Missing | Damper-Steel | Install | 45102422 | WV CBRN-AGLS SW ST-PNCH C10/44 INS DMPS | ICS
LC | 122514108 | 053/1034 | T2 HAT CREEK #1-WESTWD 53/1034 RPR TIE | TABLEMTN | ETL.7030.INSL | 2021-12-23 | 2021-12-23 | 2022-03-25 | 2022-12-23 | 2022-03-23 | On-time | 630 | Upgraded | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair | 45123694 | T2 HAT CREEK #1-WESTWD 53/1034 RPR TIE | ICW
LC | 122525061 | 020/007 | T3 MI-WUK-CURTIS 20/07 RPR CNDW | VICTOR | ETL.1073.POLE.WDPS | 2021-12-29 | 2021-12-29 | 2021-12-26 | 2022-06-27 | 2022-03-29 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW CREW COMP OH FMOB TR3 PRTO FRAB | Debris/Nest/etc. | Conductor-Wood | Remove | 45102715 | T3 MI-WUK-CURTIS 20/07 RPR CNDW | ICW
LC | 122527507 | 002/062 | T2 JEFFERSON-STANFORD 2/62 RPR ADSS | METCALF | ETL.7220.POLE.WOOD | 2021-12-29 | 2021-12-29 | 2022-01-24 | 2022-12-29 | 2022-03-29 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45106730 | T2 JEFFERSON-STANFORD 2/62 RPR ADSS | ICW
LC | 122533646 | 001/013 | T2 FLINT TAP 1/13 RPR ADSS | SACTO | ETL.3341.POLE.WOOD | 2021-12-31 | 2021-12-30 | 2022-03-02 | 2022-12-30 | 2022-03-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45106500 | T2 FLINT TAP 1/13 RPR ADSS | ICW
LC | 122533685 | 001/014 | T2 FLINT TAP 1/14 RPR ADSS | SACTO | ETL.3341.POLE.NWOD | 2021-12-31 | 2021-12-30 | 2022-03-02 | 2022-12-30 | 2022-03-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45106501 | T2 FLINT TAP 1/14 RPR ADSS | ICS
LC | 122611440 | 018/092A | T3 CORTINA-MENDOCINO #1 18/92A RPR SWTCH | LAKEVLLE | ETL.1330.SWIT | 2022-01-13 | 2022-01-13 | 2022-01-26 | 2022-07-12 | 2022-04-13 | On-time | 623 | Upgraded | Closed | HFTD 3 | RELW NONR COMP OH FMOB TR3 | Out of Adjustment | Switch | Repair | 45150603 | T3 CORTINA-MENDOCINO #1 18/92A CANCEL | ICE
LC | 122949972 | 020/112 | T3 DI PARKWAY-MORAGA 20/112 RPR OPGW | CONCORD | ETL.5930.TOWR | 2022-02-09 | 2022-02-05 | 2022-04-15 | 2022-08-04 | 2022-05-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45175074 | T3 DI PARKWAY-MORAGA 20/112 RPR OPGW | ICS
LC | 122951517 | 022/122 | T3 DI PRKWY-MORAGA 22/122 RPR OPGW | CONCORD | ETL.5930.TOWR | 2022-02-09 | 2022-02-07 | 2022-03-25 | 2022-08-06 | 2022-05-07 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45175076 | T3 DI PRKWY-MORAGA 22/122 RPR OPGW | ICS
LC | 122952371 | 019/106 | T3 DI PARKWAY-MORAGA 19/106 RPR OPGW | CONCORD | ETL.5930.TOWR | 2022-02-09 | 2022-02-05 | 2022-03-04 | 2022-08-04 | 2022-05-05 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45175101 | T3 DI PARKWAY-MORAGA 19/106 RPR OPGW | ICS
LC | 122952568 | 022/255 | T3 DI IGNACIO-BLNS #2 022/255 RPR CONW | LAKEVLLE | ETL.7180.INSL.CERA | 2022-02-09 | 2022-02-04 | 2022-06-25 | 2022-08-03 | 2022-08-04 | On-time | 630 | Upgraded | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45341206 | T3 DI IGNACIO-BLNS #2 022/255 RPR CONW | ICW
LC | 123031341 | 279 | T3 LN TR-CYTN-SW279 14/93B RPR SW | CONCORD | ETL.6160.SWIT | 2022-02-27 | 2022-02-26 | 2022-05-11 | 2022-08-25 | 2022-05-26 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO | Out of Adjustment | Switch | Repair | 45193965 | T3 LN TR-CYTN-SW279 14/93B RPR SW | ICE
LC | 123042089 | 001/006 | T3 SPRING GAP TAP 1/6 RPR SW | VICTOR | ETL.1402.SWIT | 2022-03-02 | 2022-03-02 | 2022-03-02 | 2022-08-29 | 2022-06-02 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 3 | RELW PATR COMP OH FMOB TR3 PRTO | Out of Adjustment | Switch | Repair | 45195733 | T3 SPRING GAP TAP 1/6 RPR SW | ICE
LC | 123042144 | 143 | T3 DONNELLS-MI-WUK-SW 007/007 RPR SW | VICTOR | ETL.1400.SWIT | 2022-03-02 | 2022-03-02 | 2022-03-02 | 2022-08-29 | 2022-06-02 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 3 | RELW PATR COMP OH FMOB TR3 | Out of Adjustment | Switch | Repair | 45195734 | T3 DONNELLS-MI-WUK-SW 007/007 RPR SW | ICE
LC | 123044614 | 012/096A | T3 DI TRNTY-COTTONWOOD 12/96A COTTER | TABLEMTN | ETL.4040.INSL.CERA | 2022-03-02 | 2022-03-02 | 2022-03-21 | 2022-08-29 | 2022-06-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45200931 | T3 DI TRNTY-COTTONWOOD 12/96A COTTER | ICS
LC | 123054638 | 027/108 | T3 DI PTTSBRG-SAN MATEO 27/108 RPR SHLS | CONCORD | ETL.5463.TOWR | 2022-03-04 | 2022-03-02 | 2022-04-12 | 2022-08-29 | 2022-06-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45201139 | T3 DI PTTSBRG-SAN MATEO 27/108 RPR SHLS | ICS
LC | 123055819 | 013/118B | T3 DI CTTNWD-BNTN #2 13/118B RPL INSW | TABLEMTN | ETL.6650.INSL.CERA | 2022-03-05 | 2022-03-04 | 2022-06-02 | 2022-08-31 | 2022-06-04 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31596728 | T3 DI CTTNWD-BNTN #2 13/118B RPL INSW | 93I
LC | 123059598 | 015/406 | T3 EI COLGATE-ALLEGHANY 15/406 RPL CRMW | SACTO | ETL.6470.POLE.WOOD | 2022-03-07 | 2022-03-07 | 2022-06-16 | 2022-09-03 | 2022-06-07 | On-time | 637 | Upgraded | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31609078 | T3 EI COLGATE-ALLEGHANY 15/406 RPL CRMW | 93E
LC | 123073907 | 004/098 | T3 DRM-GRSS VLLEY-WMAR 4/98 RPR ADSS | SACTO | ETL.6760.POLE.NWOD | 2022-03-09 | 2022-03-09 | 2022-03-18 | 2022-09-05 | 2022-06-09 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45223516 | T3 DRM-GRSS VLLEY-WMAR 4/98 RPR ADSS | ICW
LC | 123084221 | B009/089 | T3 DI DRUM-HIGGINS B9/89 RPL INSS | SACTO | ETL.4393.TOWR | 2022-03-10 | 2022-03-09 | 2022-03-09 | 2022-09-05 | 2022-06-09 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31596878 | T3 DI DRUM-HIGGINS B9/89 RPL INSS | 93K
LC | 123088453 | 006/050 | T3 DI GRN VLLY-LLAGAS 6/050 RPR INSW | MOSSLNDG | ETL.1720.INSL.CERA | 2022-03-10 | 2022-03-10 | 2022-03-24 | 2022-09-06 | 2022-06-08 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45212976 | T3 DI GRN VLLY-LLAGAS 6/050 RPR INSW | ICW
LC | 123090477 | 000/007 | T3 IR RND MTN-TABLE MTN #2 0/7 RPR SPLS | TABLEMTN | ETL.6070.INSL | 2022-03-11 | 2022-03-08 | 2022-05-25 | 2022-09-04 | 2022-06-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW PATR COMP OH TR3 PRTO | No Good/Out of Stdrd | Splice-Steel | Repair | 45211558 | T3 IR RND MTN-TABLE MTN #2 0/7 RPR SPLS | ICS
LC | 123090479 | 004/024 | T3 IR RND MTN-TABLE MTN #2 4/24 RPR SPLS | TABLEMTN | ETL.6070.INSL.NCER | 2022-03-11 | 2022-03-09 | 2022-05-23 | 2022-09-05 | 2022-06-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW PATR COMP OH TR3 PRTO | No Good/Out of Stdrd | Splice-Steel | Repair | 45211557 | T3 IR RND MTN-TABLE MTN #2 4/24 RPR SPLS | ICS
LC | 123099147 | 012/056 | T3 DI SN LUIS OBSPO-SN MRA 12/56 COTTER | PISMOBCH | ETL.3540.INSL.CERA | 2022-03-14 | 2022-03-11 | 2022-03-21 | 2022-09-07 | 2022-06-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45219259 | T3 DI SN LUIS OBSPO-SN MRA 12/56 COTTER | ICS
LC | 123099705 | 012/135 | T3 DI IGNACIO-BOLINAS #1 12/135 RPR GYWW | LAKEVLLE | ETL.7140.POLE.WOOD | 2022-03-14 | 2022-03-11 | 2022-05-19 | 2022-09-07 | 2022-06-11 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW ACCL COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213285 | T3 DI IGNACIO-BOLINAS #1 12/135 RPR GYWW | ICW
LC | 123099755 | 002/018 | T3 DI MORAGA-OAKLAND #1 2/18 COTTER | CONCORD | ETL.2720.INSL | 2022-03-14 | 2022-03-11 | 2022-03-28 | 2022-09-07 | 2022-06-11 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45214205 | T3 DI MORAGA-OAKLAND #1 2/18 COTTER | ICS
LC | 123144727 | 002/014 | T3 EI RND MTN-TABLE MTN#2 2/14 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2022-03-17 | 2022-03-17 | 2022-06-01 | 2022-09-13 | 2022-06-15 | On-time | 543 | Upgraded | Closed | HFTD 3 | RELW COMP OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45232788 | T3 EI RND MTN-TABLE MTN#2 2/14 RPR STRT | ICQ
LC | 123145492 | 002/015 | T3 EI RND MTN-TABLE MTN#2 2/15 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2022-03-17 | 2022-03-17 | 2022-06-01 | 2022-09-13 | 2022-06-15 | On-time | 543 | Upgraded | Closed | HFTD 3 | RELW COMP OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45232789 | T3 EI RND MTN-TABLE MTN#2 2/15 RPR STRT | ICQ
LC | 123148997 | 004/038 | T3 DI ATSCDRO-CAYUCOS 4/38 RPL SPLW | PISMOBCH | ETL.8480.INSL.NCER | 2022-03-18 | 2022-03-14 | 2022-03-25 | 2022-09-10 | 2022-06-14 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW ACCL COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Replace | 45226350 | T3 DI ATSCDRO-CAYUCOS 4/38 RPL SPLW | ICW
LC | 123150670 | 000/003 | T3 DI MRGA-OAKLAND #3 000/003 RPR INSS | CONCORD | ETL.2740.INSL.CERA | 2022-03-18 | 2022-03-14 | 2022-04-06 | 2022-09-10 | 2022-06-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45224037 | T3 DI MRGA-OAKLAND #3 000/003 RPR INSS | ICS
LC | 123150682 | 020/550 | T3 EI COLGATE-ALLEGHANY 20/550 RPL SPLW | SACTO | ETL.6470.INSL.NCER | 2022-03-18 | 2022-03-18 | 2022-06-14 | 2022-09-14 | 2022-06-18 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Splice-Wood | Replace | 45225537 | T3 EI COLGATE-ALLEGHANY 20/550 RPL SPLW | ICW
LC | 123152546 | 013/106 | T3 DI TRINITY CTTNWD 13/106 RPR INSS | TABLEMTN | ETL.4040.INSL.CERA | 2022-03-18 | 2022-03-14 | 2022-04-14 | 2022-09-10 | 2022-06-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45232787 | T3 DI TRINITY CTTNWD 13/106 RPR INSS | ICW
LC | 123154901 | 016/122 | T3 DI TRINITY-CTTONWOOD 16/122(L) COTTER | TABLEMTN | ETL.4040.POLE.STPS | 2022-03-19 | 2022-03-15 | 2022-04-14 | 2022-09-11 | 2022-06-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45232863 | T3 DI TRINITY-CTTONWOOD 16/122(L) COTTER | ICW
LC | 123154974 | 000/001 | T3 DI MSORI FLT-GOLD HLL #2 0/1 RPR INSS | SACTO | ETL.2670.INSL.NCER | 2022-03-19 | 2022-03-15 | 2022-03-26 | 2022-09-11 | 2022-06-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45225538 | T3 DI MSORI FLT-GOLD HLL #2 0/1 RPR INSS | ICS
LC | 123155377 | 000/020 | T3 DI PINE GROVE TAP 0/20 COTTER | VICTOR | ETL.8351.INSL.CERA | 2022-03-19 | 2022-03-15 | 2022-04-06 | 2022-09-11 | 2022-06-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45226068 | T3 DI PINE GROVE TAP 0/20 COTTER | ICW
LC | 123166164 | 022/598 | T3 EI COLGATE-ALLEGHANY 22/598 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-22 | 2022-03-22 | 2022-06-13 | 2022-09-18 | 2022-09-22 | On-time | 372 | Upgraded | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31604501 | T3 EI COLGATE-ALLEGHANY 22/598 RPL POLE | 70Y
LC | 123173004 | 020/007 | T3 DI MI-WUK-CURTIS 20/7 RPR INSW | VICTOR | ETL.1073.INSL.CERA | 2022-03-23 | 2022-03-23 | 2022-05-05 | 2022-09-19 | 2022-06-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45232929 | T3 DI MI-WUK-CURTIS 20/7 RPR INSW | ICW
LC | 123177084 | 019/006 | T3 DI MI-WUK-CURTIS 019/006 COTTER | VICTOR | ETL.1073.POLE.WDPS | 2022-03-23 | 2022-03-16 | 2022-05-05 | 2022-09-12 | 2022-06-16 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45233024 | T3 DI MI-WUK-CURTIS 019/006 COTTER | ICW
LC | 123178206 | T057 | T3 DI MIDWAY-SANTA MARIA T057 COTR KEY | PISMOBCH | ETL.9240.TOWR | 2022-03-24 | 2022-03-17 | 2022-08-31 | 2022-09-13 | 2022-06-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Repair | 45251262 | T3 DI MIDWAY-SANTA MARIA T057 COTR KEY | ICS
LC | 123183860 | 002/016 | T3 DI MORAGA-OAKLAND #3 2/16 COTTER | CONCORD | ETL.2740.INSL.NCER | 2022-03-24 | 2022-03-15 | 2022-04-09 | 2022-09-11 | 2022-06-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45233284 | T3 DI MORAGA-OAKLAND #3 2/16 COTTER | ICS
LC | 123195621 | 016/081 | T3 DI MNTA VSTA CYOTE 16/81 COTTER | MOSSLNDG | ETL.5090.INSL | 2022-03-25 | 2022-03-19 | 2022-05-21 | 2022-09-15 | 2022-06-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45234329 | T3 DI MNTA VSTA CYOTE 16/81 COTTER | ICS
LC | 123195622 | 016/081 | T3 DI MTCALF MNTA VISTA #3 16/81 COTTER | MOSSLNDG | ETL.5091.INSL | 2022-03-25 | 2022-03-19 | 2022-05-21 | 2022-09-15 | 2022-06-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45234330 | T3 DI MTCALF MNTA VISTA #3 16/81 COTTER | ICS
LC | 123197507 | 019/005A | T3 DI MI-WUK-CURTIS 019/005A COTTER | VICTOR | ETL.1073.INSL.NCER | 2022-03-26 | 2022-03-21 | 2022-04-05 | 2022-09-17 | 2022-06-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45233887 | T3 DI MI-WUK-CURTIS 019/005A COTTER | ICW
LC | 123204420 | 032/236 | T3 DI MDL FRK-GLD HL 32/236 RPR INSW | SACTO | ETL.5140.INSL.NCER | 2022-03-28 | 2022-03-23 | 2022-04-08 | 2022-09-19 | 2022-06-23 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45239514 | T3 DI MDL FRK-GLD HL 32/236 RPR INSW | ICS
LC | 123204442 | 001/016 | T3 DI WST PNT VLY SPRNGS 1/16 COTR CMPLT | VICTOR | ETL.8350.INSL.NCER | 2022-03-28 | 2022-03-23 | 2022-05-14 | 2022-09-19 | 2022-06-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45234900 | T3 DI WST PNT VLY SPRNGS 1/16 COTR KEY | ICW
LC | 123206498 | 021/001 | T3 DI MI-WUK-CURTIS 021/001 COTTER | VICTOR | ETL.1073.INSL.CERA | 2022-03-29 | 2022-03-23 | 2022-06-07 | 2022-09-19 | 2022-06-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45235961 | T3 DI MI-WUK-CURTIS 021/001 COTTER | ICW
LC | 123209099 | 023/621 | T3 EI COLGATE-ALLEGHANY 23/621 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-29 | 2022-03-29 | 2022-06-14 | 2022-09-25 | 2022-09-29 | On-time | 372 | Upgraded | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31603173 | T3 EI COLGATE-ALLEGHANY 23/621 RPL POLE | 70Y
LC | 123209766 | 001/018 | T3 DI WST PT-VLLY SPRNGS 1/18 COTTR CMPL | VICTOR | ETL.8350.INSL.NCER | 2022-03-29 | 2022-03-21 | 2022-05-14 | 2022-09-17 | 2022-06-21 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair | 45235859 | T3 DI WST PT-VLLY SPRNGS 1/18 RPR INSW | ICW
LC | 123210139 | 020/010 | T3 DI MI-WUK-CURTIS 020/010 COTTER | VICTOR | ETL.1073.INSL.CERA | 2022-03-29 | 2022-03-23 | 2022-06-07 | 2022-09-19 | 2022-06-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45235962 | T3 DI MI-WUK-CURTIS 020/010 COTTER | ICW
LC | 123210568 | 021/325 | T3 DI GOLD HILL #1 21/325 RPR GYWW | SACTO | ETL.6950.POLE.WOOD | 2022-03-29 | 2022-03-25 | 2022-04-12 | 2022-09-21 | 2022-06-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45240138 | T3 DI GOLD HILL #1 21/325 RPR GYWW | ICW
LC | 123210625 | 021/325 | T3 DI GOLD HILL #1 21/325 RPR INSW | SACTO | ETL.6950.INSL.NCER | 2022-03-29 | 2022-03-25 | 2022-04-12 | 2022-09-21 | 2022-06-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45240139 | T3 DI GOLD HILL #1 21/325 RPR INSW | ICW
LC | 123210641 | 018/277 | T3 DI GOLD HILL #1 18/277 RPR INSW | SACTO | ETL.6950.INSL.CERA | 2022-03-29 | 2022-03-25 | 2022-04-15 | 2022-09-21 | 2022-06-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45240160 | T3 DI GOLD HILL #1 18/277 RPR INSW | ICW
LC | 123211452 | 005/050 | T3 DI SBRNTE-GRZ-CLRMT#1 5/50 RPR INSS | CONCORD | ETL.3740.TOWR | 2022-03-30 | 2022-03-25 | 2022-04-29 | 2022-09-21 | 2022-06-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Repair | 45238692 | T3 DI SBRNTE-GRZ-CLRMT#1 5/50 RPR INSS | ICS
LC | 123215762 | 020/103 | T3 EI RD MTN-TB MTN #1 20/103 RPR SHIELD | TABLEMTN | ETL.6060.TOWR | 2022-03-30 | 2022-03-30 | 2022-05-17 | 2022-09-26 | 2022-06-30 | On-time | 628 | Upgraded | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45240167 | T3 EI RD MTN-TB MTN #1 20/103 RPR SHIELD | ICS
LC | 123217004 | 013/070 | T3 DI MTCLF-MNTA VISTA #3 13/70 INSS RPR | MOSSLNDG | ETL.5091.INSL | 2022-03-30 | 2022-03-24 | 2022-04-28 | 2022-09-20 | 2022-06-24 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45242379 | T3 DI MTCLF-MNTA VISTA #3 13/70 INSS RPR | ICS
LC | 123222951 | 004/108 | T3 DI DRM-GRS VALY-WEMAR 04/108 COMPLETE | SACTO | ETL.6760.POLE.NWOD | 2022-03-31 | 2022-03-30 | 2022-04-08 | 2022-09-26 | 2022-06-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW ACCM COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45239561 | T3 DI DRM-GRS VALY-WEMAR 04/108 RPR ADSS | ICW
LC | 123223209 | 008/006 | T3 DI MENDOCINO-WILLITS-WD 8/6 RPL STRW | WILLITS | ETL.7540.POLE.WOOD | 2022-03-31 | 2022-03-28 | 2022-06-28 | 2022-09-24 | 2022-06-28 | On-time | 372 | Upgraded | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31599913 | T2 DI MENDOCINO-WILLITS 7/6 RPL STRW | 70Y
LC | 123226135 | 004/053 | T3 DI WST PONT-VLLY SP 4/53L COMPLETE | VICTOR | ETL.8350.POLE.STPS | 2022-04-01 | 2022-03-28 | 2022-05-13 | 2022-09-24 | 2022-06-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45240732 | T3 DI WST PONT-VLLY SP 4/53L RPR GYWW | ICW
LC | 123227190 | 020/191 | T3 DI RND MTN-CTNWD#2 20/191 RPR OPGW | TABLEMTN | ETL.5640.TOWR | 2022-04-01 | 2022-03-29 | 2022-04-26 | 2022-09-25 | 2022-06-29 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45240163 | T3 DI RND MTN-CTNWD#2 20/191 RPR OPGW | ICS
LC | 123229468 | 019/186 | T3 DI RND MTN-CTWD#2 19/186 RPR INSS | TABLEMTN | ETL.5640.INSL | 2022-04-01 | 2022-03-29 | 2022-04-26 | 2022-09-25 | 2022-06-29 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45240257 | T3 DI RND MTN-CTWD#2 19/186 RPR INSS | ICS
LC | 123231461 | T081 | T3 DI MDWY SNT MR T081 COTTER | PISMOBCH | ETL.9240.TOWR | 2022-04-01 | 2022-03-29 | 2022-06-08 | 2022-09-25 | 2022-06-29 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45240737 | T3 DI MDWY SNT MR T081 COTTER | ICS
LC | 123235154 | 002/052 | T3 DI DRM-GRSS VLY-WMR 2/52 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2022-04-02 | 2022-03-30 | 2022-04-14 | 2022-09-26 | 2022-06-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45253119 | T3 DI DRM-GRSS VLY-WMR 2/52 RPR GYWW | ICW
LC | 123235223 | 017/081 | T3 DI CRTNA-MNDCNO #1 17/81 RPR OPGW | WILLITS | ETL.1330.TOWR | 2022-04-02 | 2022-03-30 | 2022-04-28 | 2022-09-26 | 2022-06-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45251971 | T3 DI CRTNA-MNDCNO #1 17/81 RPR OPGW | ICS
LC | 123235478 | 009/221 | T3 DI DRM-GRSS VLLY-WMAR 9/221 RPR INSS | SACTO | ETL.6760.INSL.NCER | 2022-04-02 | 2022-03-30 | 2022-04-15 | 2022-09-26 | 2022-06-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW ACCH COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45253111 | T3 DI DRM-GRSS VLLY-WMAR 9/221 RPR INSS | ICW
LC | 123235711 | 001/010 | T3 DI TGR CK-VLLY SPRNGS 1/10 RPL INSS | VICTOR | ETL.5790.INSL.CERA | 2022-04-02 | 2022-03-31 | 2022-08-30 | 2022-09-27 | 2022-06-29 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31600258 | T3 DI TGR CK-VLLY SPRNGS 1/10 RPL INSS | 93K
LC | 123236256 | 001/011 | T3 DI TGR CRK ELCTR 1/11 COTR KEY | VICTOR | ETL.5780.INSL | 2022-04-02 | 2022-03-31 | 2022-07-19 | 2022-09-27 | 2022-06-29 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45242376 | T3 DI TGR CRK ELCTR 1/11 COTR KEY | ICS
LC | 123236709 | 026/387 | T3 DI GOLD HILL #1 26/387 RPL SPLW | SACTO | ETL.6950.INSL.NCER | 2022-04-02 | 2022-03-30 | 2022-04-17 | 2022-09-26 | 2022-06-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Splice-Wood | Replace | 45253112 | T3 DI GOLD HILL #1 26/387 RPL SPLW | ICW
LC | 123238378 | 017/083 | T3 DI CRTNA-MNDCINO 17/83 RPR OPGW | WILLITS | ETL.1330.TOWR | 2022-04-04 | 2022-03-30 | 2022-04-28 | 2022-09-26 | 2022-06-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45251970 | T3 DI CRTNA-MNDCINO 17/83 RPR OPGW | ICS
LC | 123241292 | 000/017 | T3 DI KILARC-CEDAR CREEK 0/17 RPR INSW | TABLEMTN | ETL.7290.INSL.CERA | 2022-04-04 | 2022-03-31 | 2022-04-24 | 2022-09-27 | 2022-06-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45241464 | T3 DI KILARC-CEDAR CREEK 0/17 RPR INSW | ICW
LC | 123260534 | 010/006 | T3 DI POTTER VALLEY-WLLTS 10/6 RPR INSW | WILLITS | ETL.7820.INSL.NCER | 2022-04-06 | 2022-03-30 | 2022-06-15 | 2022-09-26 | 2022-06-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45262609 | T3 DI POTTER VALLEY-WLLTS 10/6 RPR INSW | ICW
LC | 123264157 | 002/050 | T3 EI DEER CREEK-DRUM 2/50 RPL POLE | SACTO | ETL.6690.POLE.WOOD | 2022-04-07 | 2022-04-07 | 2022-06-15 | 2022-10-04 | 2022-07-07 | On-time | 372 | Upgraded | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600740 | T3 EI DEER CREEK-DRUM 2/50 RPL POLE | 70Y
LC | 123275883 | 004/042 | T3 EI WOODLEAF-PALERMO 4/42 COMPLETE | TABLEMTN | ETL.4220.POLE.STPS | 2022-04-08 | 2022-04-08 | 2022-04-18 | 2022-10-05 | 2022-07-08 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | REGW INSP CGI COMP OH FMOB TR3 NTDE | Land/Enviro Issue | Other | Access Issue
LC | 123279643 | 003/083 | T3 DI DRM GRS VLY WMR 3/83 COTR KEY | SACTO | ETL.6760.INSL.NCER | 2022-04-09 | 2022-04-04 | 2022-04-14 | 2022-10-01 | 2022-07-04 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45253181 | T3 DI DRM GRS VLY WMR 3/83 COTR KEY | ICW
LC | 123296006 | 009/051 | T3 DI RND MTN TBL MTN #2 9/51 COMPLETE | TABLEMTN | ETL.6070.INSL | 2022-04-11 | 2022-04-04 | 2022-05-24 | 2022-10-01 | 2022-07-03 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45254811 | T3 DI RND MTN TBL MTN #2 9/51 INS COTTER | ICS
LC | 123299980 | 010/054 | T3 DI MNT VST CYT SS 10/54 SHLS COMPLETE | MOSSLNDG | ETL.5090.TOWR | 2022-04-11 | 2022-04-05 | 2022-05-15 | 2022-10-02 | 2022-07-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45259679 | T3 DI MNT VST CYT SS 10/54 RPR SHLS | ICS
LC | 123300679 | 011/056 | T3 DI MNT VST CYT SS 11/56 COMPLETE | MOSSLNDG | ETL.5090.INSL | 2022-04-11 | 2022-04-05 | 2022-05-16 | 2022-10-02 | 2022-07-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | Missing | Damper-Steel | Install | 45259740 | T3 DI MNT VST CYT SS 11/56 INS DAMS | ICS
LC | 123301010 | 002/003 | T3 DI BRIDGEVL-GARBERVL 2/3 RPR CRSMW | EUREKA | ETL.6220.INSL.CERA | 2022-04-11 | 2022-04-05 | 2022-09-19 | 2022-10-02 | 2022-07-05 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45260282 | T3 DI BRDGVIL-GRBRVIL 02/03 RPR CRSMW | ICW
LC | 123312290 | 003/061 | T3 CNTRVLL-TBL MTN 3/061 RESAG | TABLEMTN | ETL.6320.POLE.NWOD | 2022-04-12 | 2022-04-12 | 2022-04-25 | 2022-10-09 | 2022-07-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW NONR COMP OH FMOB TR3 FRAB | No Good/Out of Stdrd | Conductor-Wood | Repair | 45255967 | T3 CNTRVLL-TBL MTN 3/061 RESAG | ICW
LC | 123313431 | 000/009 | T3 DI DESABL-CNTRVILE 0/9 RPLC SPLW | TABLEMTN | ETL.6720.INSL | 2022-04-12 | 2022-04-07 | 2022-04-22 | 2022-10-04 | 2022-07-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Splice-Wood | Replace | 45255694 | T3 DI DESABL-CNTRVILE 0/9 RPLC SPLW | ICW
LC | 123313742 | 015/006 | T3 DI MONTE RIO-FORT ROSS 15/6 RPR INSW | LAKEVLLE | ETL.6979.INSL.CERA | 2022-04-12 | 2022-04-07 | 2022-04-19 | 2022-10-04 | 2022-07-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45258507 | T3 DI MONTE RIO-FORT ROSS 15/6 RPR INSW | ICW
LC | 123313828 | 020/099 | T3 DI MONTA VISTA-COYTE 20/99 COMPLETE | MOSSLNDG | ETL.5090.INSL | 2022-04-12 | 2022-04-07 | 2022-05-21 | 2022-10-04 | 2022-07-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45259743 | T3 DI MONTA VISTA-COYTE 20/99 RPR COTTER | ICS
LC | 123317387 | 006/116 | T3 EI BRIONES TAP 6/116 RPR SWITCH | CONCORD | ETL.7055.SWIT | 2022-04-13 | 2022-04-02 | 2022-06-28 | 2022-09-29 | 2022-07-02 | On-time | 623 | Upgraded | Closed | HFTD 3 | RELW INSP SUBS COMP OH FMOB TR3 PRTO | Out of Adjustment | Switch | Repair | 45262000 | T3 EI BRIONES TAP 6/116 RPR SWITCH | ICE
LC | 123321030 | 002/013 | T3 DI SOBRANTE-G #2 002/013 RPL INSS | CONCORD | ETL.3730.INSL.CERA | 2022-04-13 | 2022-03-31 | 2022-07-06 | 2022-09-27 | 2022-06-30 | On-time | 532 | Upgraded | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31597693 | T2 SOBRANTE G #2 RPL INSS IN 2 TSPS. | 93K
LC | 123325449 | 004/104 | T3 DI KILARC-CEDAR CREEK 4/104 RPL INSW | TABLEMTN | ETL.7290.INSL | 2022-04-13 | 2022-03-31 | 2022-04-25 | 2022-09-27 | 2022-07-01 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31601181 | T3 DI KILARC-CEDAR CREEK 4/104 RPL INSW | 93I
LC | 123325819 | 009/000 | T3 DI MONTE RIO-FULTON 9/0 RPR INSW | LAKEVLLE | ETL.7630.INSL.CERA | 2022-04-13 | 2022-04-09 | 2022-05-27 | 2022-10-06 | 2022-07-09 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45260114 | T3 DI MONTE RIO-FULTON 9/0 RPR INSW | ICW
LC | 123325851 | 019/092 | T3 DI METCALF-MNT VST#3 19/92 COTR KEY | MOSSLNDG | ETL.5091.INSL | 2022-04-13 | 2022-04-09 | 2022-04-28 | 2022-10-06 | 2022-07-09 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45259747 | T3 DI METCALF-MNT VST#3 19/92 COTR KEY | ICS
LC | 123332891 | B010/108 | T3 DI DRUM-HIGGINS+ B10/108 COMPLETE | SACTO | ETL.4393.INSL.CERA | 2022-04-14 | 2022-04-11 | 2022-04-30 | 2022-10-08 | 2022-07-10 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45260845 | T3 DI DRUM-HIGGINS+ B10/108 RPR COTTER | ICS
LC | 123334245 | 016/067 | T3 DI EGL RCK-FLTN-SLVRDO 16/67 COMPLETE | LAKEVLLE | ETL.4392.INSL.CERA | 2022-04-15 | 2022-04-12 | 2022-05-18 | 2022-10-09 | 2022-07-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45260211 | T3 DI EGL RCK-FLTN-SLVRDO 16/67 COTTER | ICS
LC | 123367988 | 006/083 | T3 DI GRN VLLY-CMP EVRS 6/83 RPR JMPW | MOSSLNDG | ETL.1710.INSL.NCER | 2022-04-19 | 2022-04-14 | 2022-07-19 | 2022-10-11 | 2022-07-14 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Wood | Repair | 45263181 | T3 DI GRN VLLY-CMP EVRS 6/83 RPR JMPW | ICW
LC | 123369700 | 006/040 | T3 DI SBRNT GRLY CLRMNT #2 6/40 RPR STRT | CONCORD | ETL.3750.TOWR | 2022-04-19 | 2022-04-15 | 2022-06-26 | 2022-10-12 | 2022-07-14 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45286103 | T3 DI SBRNT GRLY CLRMNT #2 6/40 RPR STRT | ICQ
LC | 123375941 | :004/027 | T3 DI EAGLE ROCK-CORTINA :4/27 COTTER | WILLITS | ETL.1470.INSL.NCER | 2022-04-20 | 2022-04-15 | 2022-07-25 | 2022-10-12 | 2022-07-15 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45265190 | T3 DI EAGLE ROCK-CORTINA :4/27 COTTER | ICS
LC | 123388289 | 000/016 | T3 DI DESABLA-CENTERVILLE 0/16 RPL STRW | TABLEMTN | ETL.6720.POLE.WOOD | 2022-04-21 | 2022-04-18 | 2022-12-06 | 2022-10-15 | 2022-10-18 | Late | 372 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31607506 | T3 DI DESABLA-CENTERVILLE 0/16 RPL STRW | 70Y
LC | 123397103 | 043/190 | T3 DI MTCLF-MSS LNDNG #1 43/190 COTTER | MOSSLNDG | ETL.5100.INSL | 2022-04-22 | 2022-04-20 | 2022-06-16 | 2022-10-17 | 2022-07-20 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45274762 | T3 DI MTCLF-MSS LNDNG #1 43/190 COTTER | ICS
LC | 123397316 | 019/091 | T3 DI CORTINA-MNDCN 19/91 RPR OPGW | WILLITS | ETL.1330.TOWR | 2022-04-22 | 2022-04-14 | 2022-05-10 | 2022-10-11 | 2022-07-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45278965 | T3 DI CORTINA-MNDCN 19/91 RPR OPGW | ICS
LC | 123399125 | :008/006 | T3 DI FULTON-CALISTOGA :8/6 RPR INSW | LAKEVLLE | ETL.6880.INSL.CERA | 2022-04-23 | 2022-04-20 | 2022-05-16 | 2022-10-17 | 2022-07-20 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCH COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45267212 | T3 DI FULTON-CALISTOGA :8/6 RPR INSW | ICW
LC | 123401035 | 003/005A | T3 DI LAURELES-OTTER 3/5A RPR GYWW | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-04-23 | 2022-04-20 | 2022-07-15 | 2022-10-17 | 2022-07-20 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45274763 | T3 DI LAURELES-OTTER 3/5A RPR GYWW | ICW
LC | 123401649 | 004/005 | T3 DI LAURELES-OTTER 4/5 RPR INSW | MOSSLNDG | ETL.7380.INSL.NCER | 2022-04-23 | 2022-04-20 | 2022-07-15 | 2022-10-17 | 2022-07-20 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45274764 | T3 DI LAURELES-OTTER 4/5 RPR INSW | ICW
LC | 123420852 | 011/043 | T3 DI DIABLO-MIDWAY #3 11/43 RPR INSS | PISMOBCH | ETL.5980.INSL | 2022-04-25 | 2022-04-25 | 2022-05-24 | 2022-10-22 | 2022-07-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45268095 | T3 DI DIABLO-MIDWAY #3 11/43 RPR INSS | ICS
LC | 123432518 | 011/100 | T3 EI COTTNWD-BENTN #2 11/100 COTTER | TABLEMTN | ETL.6650.INSL.CERA | 2022-04-26 | 2022-04-26 | 2022-06-01 | 2022-10-23 | 2022-07-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Structure-Wood | Repair | 45274883 | T3 EI COTTNWD-BENTN #2 11/100 COTTER | ICW
LC | 123447153 | 003/082 | T3 DI DRUM-SPLDNG 3/082 INS COTTER | SACTO | ETL.6770.INSL | 2022-04-28 | 2022-04-21 | 2022-07-07 | 2022-10-18 | 2022-07-20 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45274922 | T3 DI DRUM-SPLDNG 3/082 INS COTTER | ICW
LC | 123452228 | 002/038 | T3 DI KSWCK-TRNTY 002/038 COMPLETE | TABLEMTN | ETL.7270.INSL.CERA | 2022-04-28 | 2022-04-11 | 2022-06-02 | 2022-10-08 | 2022-07-10 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45274893 | T3 DI KSWCK-TRNTY 002/038 RPL TIE WIRE | ICW
LC | 123454234 | 028/127 | T3 DI FULTON-LAKEVILLE 28/127 CTTR CMPLT | LAKEVLLE | ETL.4950.INSL | 2022-04-29 | 2022-04-22 | 2022-05-20 | 2022-10-19 | 2022-07-22 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45278276 | T3 DI FULTON-LAKEVILLE 28/127 INS COTTER | ICS
LC | 123454477 | 017/071 | T3 DI GYSRS #17-FLTN 17/71 INS COTTER | LAKEVLLE | ETL.4770.INSL.CERA | 2022-04-29 | 2022-04-22 | 2022-06-07 | 2022-10-19 | 2022-07-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45278277 | T3 DI GYSRS #17-FLTN 17/71 INS COTTER | ICS
LC | 123454694 | 006/161 | T3 DI CLGT-ALLGHNY 006/161 RPL INSW | SACTO | ETL.6470.INSL.NCER | 2022-04-29 | 2022-04-15 | 2022-06-21 | 2022-10-12 | 2022-07-15 | On-time | 508 | Upgraded | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31602334 | T3 DI CLGT-ALLGHNY 006/161 RPL INSW | 93I
LC | 123456299 | 008/036 | T3 DI EGL RCK FLTN SLVRD 8/36 COMPLETE | LAKEVLLE | ETL.4392.INSL.CERA | 2022-04-29 | 2022-04-22 | 2022-06-07 | 2022-10-19 | 2022-07-22 | On-time | 628 | Upgraded | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45278279 | T3 DI EGL RCK FLTN SLVRD 8/36 RPR INSS | ICS
LC | 123457443 | 003/035 | T3 EI DRUM-SUMMIT #1 3/35 COTTER | SACTO | ETL.1440.INSL.NCER | 2022-04-29 | 2022-04-29 | 2022-07-14 | 2022-10-26 | 2022-07-29 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair | 45276985 | T3 EI DRUM-SUMMIT #1 3/35 COTTER | ICW
LC | 123457989 | 027/120 | T3 DI FLTN LKVL 27/120 INS COTTER | LAKEVLLE | ETL.4950.INSL.CERA | 2022-04-29 | 2022-04-22 | 2022-05-20 | 2022-10-19 | 2022-07-21 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45278960 | T3 DI FLTN LKVL 27/120 INS COTTER | ICS
LC | 123463332 | 008/036 | T3 DI GEYSERS #9-LKVLL 8/36 COMPLETE | LAKEVLLE | ETL.4780.INSL.NCER | 2022-04-30 | 2022-04-22 | 2022-06-07 | 2022-10-19 | 2022-07-22 | On-time | 628 | Upgraded | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45278961 | T3 DI GEYSERS #9-LKVLL 8/36 RPR INSS | ICS
LC | 123466940 | 003/047 | T3 EI DRUM-SUMMIT #1 3/47 COTTER | SACTO | ETL.1440.INSL.NCER | 2022-04-30 | 2022-04-30 | 2022-07-14 | 2022-10-27 | 2022-07-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair | 45276987 | T3 EI DRUM-SUMMIT #1 3/47 COTTER | ICW
LC | 123474440 | B021/465 | T3 EI RM-GRSS VLLY-WR B21/465 COMPLETE | SACTO | ETL.6760.INSL.NCER | 2022-05-02 | 2022-05-02 | 2022-07-25 | 2022-10-29 | 2022-08-02 | On-time | 630 | Upgraded | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45296450 | T3 EI RM-GRSS VLLY-WR B21/465 RPL HRDD | ICW
LC | 123477328 | 006/118 | T3 DI FRCH MDWS-MDDLE FRK 6/118 REFRAME | SACTO | ETL.6870.POLE.WOOD | 2022-05-02 | 2022-05-02 | 2022-05-10 | 2022-10-29 | 2022-08-02 | On-time | 637 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31602502 | T3 DI FRCH MDWS-MDDLE FRK 6/118 REFRAME | 93E
LC | 123480252 | 005/073 | T3 DI KESWICK-TRINITY 5/73 GUY COTR | TABLEMTN | ETL.7270.POLE.WOOD | 2022-05-02 | 2022-04-28 | 2022-05-30 | 2022-10-25 | 2022-07-27 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45278836 | T3 DI KESWICK-TRINITY 5/73 GUY COTR | ICW
LC | 123480292 | 008/034 | T3 DI GEYSERS #9-LAKEVILLE 8/34 COTTER | LAKEVLLE | ETL.4780.INSL.CERA | 2022-05-02 | 2022-04-22 | 2022-07-01 | 2022-10-19 | 2022-07-22 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45278968 | T3 DI GEYSERS #9-LAKEVILLE 8/34 COTTER | ICS
LC | 123481955 | 006/039 | T3 DI SBRNT-GRZLY-CLRMNT#2 6/39 RPL HRDS | CONCORD | ETL.3750.TOWR | 2022-05-02 | 2022-04-14 | 2022-06-21 | 2022-10-11 | 2022-07-14 | On-time | 543 | Upgraded | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45350150 | T3 DI SBRNT-GRZLY-CLRMNT#2 6/39 RPL HRDS | ICQ
LC | 123482010 | 004/057 | T3 DI DRUM-SUMMIT #2 04/57C COTTER | SACTO | ETL.1450.POLE.WDPS | 2022-05-02 | 2022-04-28 | 2022-06-10 | 2022-10-25 | 2022-07-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45296451 | T3 DI DRUM-SUMMIT #2 04/57C COTTER | ICW
LC | 123482013 | 004/057B | T3 DI DRUM-SUMMIT #2 4/57B COTTER | SACTO | ETL.1450.INSL.NCER | 2022-05-02 | 2022-04-28 | 2022-07-14 | 2022-10-25 | 2022-07-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45296452 | T3 DI DRUM-SUMMIT #2 4/57B COTTER | ICW
LC | 123485483 | 029/240 | T3 DI PIT #1-COTTNWD 29/240 BENT STEEL | TABLEMTN | ETL.5390.TOWR | 2022-05-03 | 2022-04-28 | 2022-08-18 | 2022-10-25 | 2022-07-28 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45285619 | T3 DI PIT #1-COTTNWD 29/240 BENT STEEL | ICQ
LC | 123485615 | 000/008 | T3 DI GEYSERS #5-GEYSERS #3 0/8 RPR INSW | LAKEVLLE | ETL.1670.INSL | 2022-05-03 | 2022-04-22 | 2022-06-05 | 2022-10-19 | 2022-07-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45292432 | T3 DI GEYSERS #5-GEYSERS #3 0/8 RPR INSW | ICW
LC | 123485996 | 014/191 | T3 MIDDLEFORK #1 14/191 RPR SWITCH | SACTO | ETL.8405.SWIT | 2022-05-03 | 2022-05-03 | 2022-05-07 | 2022-10-30 | 2022-08-03 | On-time | 623 | B - Urgt Compliance | Closed | HFTD 3 | RELW CREW COMP OH FMOB TR3 PRTO NTDE | Out of Adjustment | Switch | Repair | 45277624 | T3 MIDDLEFORK #1 14/191 RPR SWITCH | ICE
LC | 123487348 | 001/028 | T3 DI DEER CREEK-DRUM 1/28 RPL TIE | SACTO | ETL.6690.INSL.CERA | 2022-05-03 | 2022-04-29 | 2022-06-14 | 2022-10-26 | 2022-07-29 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45296453 | T3 DI DEER CREEK-DRUM 1/28 RPL TIE | ICW
LC | 123490056 | 010/081 | T3 EI MONTA VISTA-BURNS 10/081 COTR KEY | MOSSLNDG | ETL.7590.INSL.NCER | 2022-05-03 | 2022-05-03 | 2022-09-02 | 2022-10-30 | 2022-08-03 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 45292186 | T3 EI MONTA VISTA-BURNS 10/081 COTR KEY | ICW
LC | 123490668 | 001/000 | T3 DI KNCTI EGLE RCK 1/0 RPR INSW | WILLITS | ETL.6861.INSL.CERA | 2022-05-03 | 2022-04-29 | 2022-09-13 | 2022-10-26 | 2022-10-29 | On-time | 630 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45389375 | T3 DI KNCTI EGLE RCK 1/0 RPR INSW | ICW
LC | 123490955 | 004/107 | T3 DI DEER CRK-DRM 4/107 REFRAME | SACTO | ETL.6690.POLE.WOOD | 2022-05-03 | 2022-04-29 | 2022-06-22 | 2022-10-26 | 2022-07-29 | On-time | 637 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31602624 | T3 DI DEER CRK-DRM 4/107 REFRAME | 93E
LC | 123494056 | 020/147 | T3 EI TRINITY-CTTNWD 20/147 RPL INSW | TABLEMTN | ETL.4040.INSL.CERA | 2022-05-04 | 2022-05-04 | 2022-08-23 | 2022-10-31 | 2022-08-04 | On-time | 508 | Upgraded | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31615012 | T3 EI TRINITY-CTTNWD 20/147 RPL INSW | 93I
LC | 123496322 | 002/071 | T3 DI DR CRK DRM 2/71 RPL TIED | SACTO | ETL.6690.INSL.CERA | 2022-05-04 | 2022-04-29 | 2022-06-22 | 2022-10-26 | 2022-07-29 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45296456 | T3 DI DR CRK DRM 2/71 RPL TIED | ICW
LC | 123500859 | 008/008 | T3 DI LAURELES-OTTER 08/08 RPL HRDW | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-04 | 2022-04-20 | 2022-08-08 | 2022-10-17 | 2022-07-20 | On-time | 630 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45292154 | T3 DI LAURELES-OTTER 08/08 RPL HRDW | ICW
LC | 123526231 | 004/098 | T3 DI CLGT-CHLLNG 4/098 COTTER | SACTO | ETL.6480.INSL.CERA | 2022-05-06 | 2022-05-02 | 2022-08-24 | 2022-10-29 | 2022-08-02 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45312729 | T3 DI CLGT-CHLLNG 4/098 COTTER | ICW
LC | 123529850 | 009/001 | T3 EI LAURELES-OTTER 9/1 RPR INSW | MOSSLNDG | ETL.7380.INSL | 2022-05-06 | 2022-05-06 | 2022-07-22 | 2022-11-02 | 2022-08-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 45292156 | T3 EI LAURELES-OTTER 9/1 RPR INSW | ICW
LC | 123546398 | 003/020 | T3 DI SBRNTE G #2 3/020 RPL INSS | CONCORD | ETL.3730.INSL.CERA | 2022-05-09 | 2022-04-19 | 2022-07-06 | 2022-10-16 | 2022-07-19 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 3 | POHW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31603152 | T3 DI SBRNTE G #2 3/020 RPL INSS | 93K
LC | 123546673 | 018/489 | T3 DI COLGATE-ALLEGHANY 18/489 RPR CNDW | SACTO | ETL.6470.INSL.NCER | 2022-05-09 | 2022-04-21 | 2022-06-17 | 2022-10-18 | 2022-07-20 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45296458 | T3 DI COLGATE-ALLEGHANY 18/489 RPR CNDW | ICW
LC | 123557082 | T-121 | T3 DI MIDWAY-SANTA MARIA T-121 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2022-05-10 | 2022-05-03 | 2022-08-30 | 2022-10-30 | 2022-08-03 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31604353 | T3 DI MIDWAY-SANTA MARIA T-121 RPL INSS | 93K
LC | 123559281 | :007/058 | T3 EI CARIBOU-PALERMO :7/58 COMPLETE | TABLEMTN | ETL.3190.TOWR | 2022-05-10 | 2022-05-10 | 2022-06-02 | 2022-11-06 | 2022-08-10 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Land/Enviro Issue | Other | Access Issue
LC | 123559397 | :007/059 | T3 EI CARIBOU-PALERMO :7/59 COMPLETE | TABLEMTN | ETL.3190.TOWR | 2022-05-10 | 2022-05-10 | 2022-06-02 | 2022-11-06 | 2022-08-10 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Land/Enviro Issue | Other | Access Issue
LC | 123559510 | :007/060 | T3 EI CARIBOU-PALERMO :7/60 COMPLETE | TABLEMTN | ETL.3190.TOWR | 2022-05-10 | 2022-05-10 | 2022-06-02 | 2022-11-06 | 2022-08-10 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Land/Enviro Issue | Other | Access Issue
LC | 123560053 | :008/064 | T3 EI CARIBOU-PALERMO :8/64 COMPLETE | TABLEMTN | ETL.3190.TOWR | 2022-05-10 | 2022-05-10 | 2022-06-02 | 2022-11-06 | 2022-08-10 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Land/Enviro Issue | Other | Access Issue
LC | 123564396 | :009/073 | T3 EI CARIBOU-PALERMO :9/73 COMPLETE | TABLEMTN | ETL.3190.TOWR | 2022-05-10 | 2022-05-10 | 2022-06-02 | 2022-11-06 | 2022-08-10 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Land/Enviro Issue | Other | Access Issue
LC | 123566390 | :009/074 | T3 EI CARIBOU-PALERMO :9/74 COMPLETE | TABLEMTN | ETL.3190.TOWR | 2022-05-11 | 2022-05-11 | 2022-06-02 | 2022-11-07 | 2022-08-11 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Land/Enviro Issue | Other | Access Issue
LC | 123566471 | :009/075 | T3 EI CARIBOU-PALERMO :9/75 COMPLETE | TABLEMTN | ETL.3190.TOWR | 2022-05-11 | 2022-05-11 | 2022-06-02 | 2022-11-07 | 2022-08-11 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Land/Enviro Issue | Other | Access Issue
LC | 123566525 | :009/076 | T3 EI CARIBOU-PALERMO :009/76 COMPLETE | TABLEMTN | ETL.3190.TOWR | 2022-05-11 | 2022-05-11 | 2022-06-02 | 2022-11-07 | 2022-08-11 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Land/Enviro Issue | Other | Access Issue
LC | 123566619 | :009/077 | T3 EI CARIBOU-PALERMO :009/77 COMPLETE | TABLEMTN | ETL.3190.TOWR | 2022-05-11 | 2022-05-11 | 2022-06-02 | 2022-11-07 | 2022-08-11 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Land/Enviro Issue | Other | Access Issue
LC | 123566692 | :010/078 | T3 EI CARIBOU-PALERMO :010/78 COMPLETE | TABLEMTN | ETL.3190.TOWR | 2022-05-11 | 2022-05-11 | 2022-06-25 | 2022-11-07 | 2022-08-11 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Land/Enviro Issue | Other | Access Issue
LC | 123566772 | :010/079 | T3 EI CARIBOU-PALERMO :010/79 COMPLETE | TABLEMTN | ETL.3190.TOWR | 2022-05-11 | 2022-05-11 | 2022-06-25 | 2022-11-07 | 2022-08-11 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO | Land/Enviro Issue | Other | Access Issue
LC | 123571186 | 000/008 | T3 DI DRUM-GRASS VLLY-WMR 0/8 COMPLETE | SACTO | ETL.6760.POLE.WOOD | 2022-05-11 | 2022-04-22 | 2022-07-18 | 2022-10-19 | 2022-07-22 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45312737 | T3 DI DRUM-GRASS VLLY-WMR 0/8 RPR ADSS | ICW
LC | 123572172 | T072 | T3 EI MIDWAY-SANTA MARIA_T072 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2022-05-11 | 2022-05-11 | 2022-08-31 | 2022-11-07 | 2022-08-11 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 3 | REGW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31604353 | T3 DI MIDWAY-SANTA MARIA T-121 RPL INSS | 93K
LC | 123577176 | 011/209 | T3 DI FRNCH MDWS-MDL FRK 11/209 COMPLETE | SACTO | ETL.6870.POLE.WOOD | 2022-05-12 | 2022-05-09 | 2022-05-22 | 2022-11-05 | 2022-08-09 | On-time | 637 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31604560 | T3 DI FRNCH MDWS-MDL FRK 11/209 REFRAME | 93E
LC | 123593527 | T072 | T3 DI MDWAY-SNTA MARIA T072 HNGR PLATE | PISMOBCH | ETL.9240.TOWR | 2022-05-14 | 2022-05-11 | 2022-08-31 | 2022-11-07 | 2022-08-11 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45298124 | T3 DI MDWAY-SNTA MARIA T072 HNGR PLATE | ICQ
LC | 123595659 | T082 | T3 DI MDWY-SANTA MARIA T082 BENT STEEL | PISMOBCH | ETL.9240.TOWR | 2022-05-14 | 2022-05-11 | 2022-08-31 | 2022-11-07 | 2022-08-11 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45298127 | T3 DI MDWY-SANTA MARIA T082 BENT STEEL | ICQ
LC | 123597406 | 005/135 | T3 EI DRM-SPLDING 5/135 RPR CONDW | SACTO | ETL.6770.INSL | 2022-05-14 | 2022-05-14 | 2022-05-21 | 2022-11-10 | 2022-08-14 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair | 45302447 | T3 EI DRM-SPLDING 5/135 RPR CONDW | ICW
LC | 123597522 | 001/028 | T3 DI FRNCH MDWS-MDLE FRK 1/28 COMPLETE | SACTO | ETL.6870.INSL.NCER | 2022-05-14 | 2022-05-06 | 2022-05-21 | 2022-11-02 | 2022-08-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45312826 | T3 FRNCH MEDWS-MIDLE FORK 1/28 COMPLETE | ICW
LC | 123604208 | -013/004 | T3 DI FULTON-CALISTOGA -13/4 RPR INSW | LAKEVLLE | ETL.6880.INSL.NCER | 2022-05-16 | 2022-05-13 | 2022-05-20 | 2022-11-09 | 2022-08-11 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45302181 | T3 DI FULTON-CALISTOGA -13/4 RPR INSW | ICW
LC | 123604343 | T054 | T3 DI MIDWAY-SANTA MARIA T054 BENT STEEL | PISMOBCH | ETL.9240.TOWR | 2022-05-16 | 2022-05-12 | 2022-08-31 | 2022-11-08 | 2022-08-12 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Tower | Repair | 45310133 | T3 DI MIDWAY-SANTA MARIA T054 BENT STEEL | ICQ
LC | 123604674 | 001/030 | T3 DI FRNCH MDWS-MID FRK 1/30 RPL TIED | SACTO | ETL.6870.INSL | 2022-05-16 | 2022-05-07 | 2022-08-26 | 2022-11-03 | 2022-08-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45312827 | T3 DI FRNCH MDWS-MID FRK 1/30 RPL TIED | ICW
LC | 123621763 | 013/181 | T3 DI WEIMAR #1 13/181 EMERG RPL | SACTO | ETL.7560.POLE.WOOD | 2022-05-17 | 2022-04-28 | 2022-11-06 | 2022-10-25 | 2022-07-28 | Late | 437 | B - Urgt Compliance | Closed | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | Fire | Emergency | Replace | 74050021 | WEIMAR #1 EMERGENCY REBUILD | 92F
LC | 123622070 | 021/109 | T3 DI RND MTN-TBL MTN #2 21/109 RPR INSS | TABLEMTN | ETL.6070.INSL | 2022-05-17 | 2022-05-13 | 2022-09-27 | 2022-11-09 | 2022-11-13 | On-time | 628 | Upgraded | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45333722 | T3 DI RND MTN-TBL MTN #2 21/109 RPR INSS | ICS
LC | 123628058 | 005/136 | T3 COLGATE-GRASS VALLEY 5/136 REFRAME | SACTO | ETL.6490.POLE.WOOD | 2022-05-18 | 2022-05-15 | 2022-08-12 | 2022-11-11 | 2022-08-15 | On-time | 637 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31604008 | T3 COLGATE-GRASS VALLEY 5/136 REFRAME | 93E
LC | 123635650 | 004/018 | T3 DI DIABLO-MIDWAY #3 004/018 COTTER | PISMOBCH | ETL.5980.INSL | 2022-05-19 | 2022-05-17 | 2022-07-01 | 2022-11-13 | 2022-08-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45312416 | T3 DI DIABLO-MIDWAY #3 004/018 COTTER | ICS
LC | 123636735 | X001/007 | T3 DI DBL MS X1/7 RPL HRDT | PISMOBCH | ETL.4620.INSL.CERA | 2022-05-19 | 2022-05-18 | 2022-07-25 | 2022-11-14 | 2022-08-18 | On-time | 543 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 45311422 | T3 DI DBL MS X1/7 RPL HRDT | ICQ
LC | 123639972 | 000/001A | T3 DI DBL PP STNBY SPL 0/1A RPR SHLS | PISMOBCH | ETL.4610.POLE.NWOD | 2022-05-19 | 2022-05-18 | 2022-09-14 | 2022-11-14 | 2022-08-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45314661 | T3 DI DBL PP STNBY SPL 0/1A RPR SHLS | ICS
LC | 123648499 | 000/007 | T3 DI RND MTN-TBLE MTN #2 0/7 INS DMPS | TABLEMTN | ETL.6070.INSL | 2022-05-20 | 2022-05-19 | 2022-05-25 | 2022-11-15 | 2022-08-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | Missing | Damper-Steel | Install | 45313699 | T3 DI RND MTN-TBLE MTN #2 0/7 INS DMPS | ICS
LC | 123651865 | 001/011 | T3 DI RND MTN-TBLE MTN #1 1/11 COTTER | TABLEMTN | ETL.6060.TOWR | 2022-05-20 | 2022-05-16 | 2022-08-11 | 2022-11-12 | 2022-08-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45315463 | T3 DI RND MTN-TBLE MTN #1 1/11 COTTER | ICS
LC | 123651999 | 009/040 | T3 DI MRGA-CSTRO VALLY 009/040 RPR OPGW | CONCORD | ETL.5250.TOWR | 2022-05-20 | 2022-05-14 | 2022-06-13 | 2022-11-10 | 2022-08-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW PATR FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45312619 | T3 DI MRGA-CSTRO VALLY 009/040 RPR OPGW | ICS
LC | 123654562 | 032/137 | T3 DI FLTN-LKILE-IGNCO+ 032/137 COTTER | LAKEVLLE | ETL.4950.INSL.CERA | 2022-05-20 | 2022-05-16 | 2022-07-01 | 2022-11-12 | 2022-11-16 | On-time | 628 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45341209 | T3 DI FLTN-LKILE-IGNCO+ 032/137 COTTER | ICS
LC | 123656461 | 022/005 | T3 DI MAPLE CREEK-HOOPA 22/5 RPR CNDW | EUREKA | ETL.7490.INSL.NCER | 2022-05-21 | 2022-05-05 | 2022-10-24 | 2022-11-01 | 2022-08-05 | On-time | 630 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45312961 | T3 DI MAPLE CREEK-HOOPA 022/005 RPR CNDW | ICW
LC | 123669800 | X002/013 | T3 DI DIABLO-MESA X2/13 RPR OPGW | PISMOBCH | ETL.4620.TOWR | 2022-05-23 | 2022-05-18 | 2022-06-02 | 2022-11-14 | 2022-08-18 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45314446 | T3 DI DIABLO-MESA X2/13 RPR OPGW | ICS
LC | 123672916 | 008/066 | T3 EI MIDDLE FORK-GLD HILL 8/69 COMPLETE | SACTO | ETL.5140.TOWR | 2022-05-23 | 2022-05-23 | 2022-06-25 | 2022-11-19 | 2022-08-23 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB NTDE | Land/Enviro Issue | Other | Access Issue
LC | 123673954 | 032/138 | T3 DI FULTN-LAKEVL-IGNCO 32/138 RPR INSS | LAKEVLLE | ETL.4950.INSL.CERA | 2022-05-23 | 2022-05-17 | 2022-07-01 | 2022-11-13 | 2022-11-17 | On-time | 628 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45342045 | T3 DI FULTN-LAKEVL-IGNCO 32/138 RPR INSS | ICS
LC | 123674084 | 014/094 | T3 DI CNTR CSTA-LS PSTAS 14/094 RPR OPGW | CONCORD | ETL.4510.TOWR | 2022-05-23 | 2022-05-17 | 2022-07-30 | 2022-11-13 | 2022-08-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45322717 | T3 DI CNTR CSTA-LS PSTAS 14/094 RPR OPGW | ICS
LC | 123674086 | 014/094 | T3 DI CNTR CSTA-LS PSTAS 14/94 RPR CNDS | CONCORD | ETL.4510.INSL | 2022-05-23 | 2022-05-17 | 2022-07-30 | 2022-11-13 | 2022-08-17 | On-time | 628 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Steel | Repair | 45323620 | T3 DI CNTR CSTA-LS PSTAS 14/94 RPR CNDS | ICS
LC | 123683666 | 005/047 | T3 DI MNT VST BRNS 5/47 RPR INSW | MOSSLNDG | ETL.7590.INSL.NCER | 2022-05-24 | 2022-05-19 | 2022-06-27 | 2022-11-15 | 2022-08-19 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45333987 | T3 DI MNT VST BRNS 5/47 RPR INSW | ICW
LC | 123685170 | 001/035 | T3 DI MIDDLEFORK #1 01/35 GUY COTR | SACTO | ETL.8405.POLE.WOOD | 2022-05-24 | 2022-05-12 | 2022-08-28 | 2022-11-08 | 2022-08-12 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45317473 | T3 DI MIDDLEFORK #1+ 01/35 GUY COTR | ICW
LC | 123686299 | 011/170 | T3 DI GOLD HILL #1 11/170 COTR KEY | SACTO | ETL.6950.INSL.NCER | 2022-05-25 | 2022-05-20 | 2022-07-11 | 2022-11-16 | 2022-08-20 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45343673 | T3 DI GOLD HILL #1 11/170 COTR KEY | ICW
LC | 123693195 | 011/000 | T3 EI MNDCN-WLLTS 11/0 RPR INSW | WILLITS | ETL.7540.INSL.NCER | 2022-05-25 | 2022-05-25 | 2022-06-29 | 2022-11-21 | 2022-08-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 45326378 | T3 EI MNDCN-WLLTS 11/0 RPR INSW | ICW
LC | 123707414 | 021/167 | T3 DI PARADISE-TABLE MTN 21/167R COTTER | TABLEMTN | ETL.4316.INSL.NCER | 2022-05-27 | 2022-05-25 | 2022-06-13 | 2022-11-21 | 2022-08-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45324075 | T3 DI PARADISE-TABLE MTN 21/167R COTTER | ICW
LC | 123707453 | 021/167 | T3 DI PARADISE-TABL MTN 21/167L COTTER | TABLEMTN | ETL.4316.POLE.STPS | 2022-05-27 | 2022-05-25 | 2022-06-13 | 2022-11-21 | 2022-08-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45324076 | T3 DI PARADISE-TABL MTN 21/167L COTTER | ICW
LC | 123707581 | 002/057 | T3 DI DRM-GRSS VLLY-WMR 2/57 COMPLETE | SACTO | ETL.6760.POLE.WOOD | 2022-05-27 | 2022-05-18 | 2022-07-22 | 2022-11-14 | 2022-08-18 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45343678 | T3 DI DRM-GRSS VLLY-WMR 2/57 RPR ADSS | ICW
LC | 123707614 | 045/329A | T3 DI CARIBU-TBL MONTIN 45/329A COTTER | TABLEMTN | ETL.4440.INSL.NCER | 2022-05-27 | 2022-05-24 | 2022-06-17 | 2022-11-20 | 2022-08-24 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45324077 | T3 DI CARIBU-TBL MONTIN 45/329A COTTER | ICS
LC | 123707648 | 022/178 | T3 DI MSRI FLT-GLD HLL#1 22/178 COTTER | SACTO | ETL.2660.INSL.NCER | 2022-05-27 | 2022-05-24 | 2022-07-08 | 2022-11-20 | 2022-08-24 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45343679 | T3 DI MSRI FLT-GLD HLL#1 22/178 COTTER | ICS
LC | 123709827 | 009/051 | T3 DI METCALF-MNTA VSTA #3 9/51 COTTER | MOSSLNDG | ETL.5091.INSL | 2022-05-27 | 2022-05-16 | 2022-09-27 | 2022-11-12 | 2022-08-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45333990 | T3 DI METCALF-MNTA VSTA #3 9/51 COTTER | ICS
LC | 123712457 | 002/047 | T3 DI DRM-GRSS VLY-WMR 2/47 COMPLETE | SACTO | ETL.6760.POLE.WOOD | 2022-05-27 | 2022-05-18 | 2022-07-22 | 2022-11-14 | 2022-08-18 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45343864 | T3 DI DRM-GRSS VLY-WMR 2/47 RPR ADSS | ICW
LC | 123712595 | 003/068 | T3 DI DRM-GRS VLY-WMAR 3/68 RPR ADSS | SACTO | ETL.6760.POLE.WOOD | 2022-05-27 | 2022-05-23 | 2022-07-22 | 2022-11-19 | 2022-08-23 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45343865 | T3 DI DRM-GRS VLY-WMAR 3/68 RPR ADSS | ICW
LC | 123712637 | 006/035 | T3 DI ROUND MTN-TBL MTN #1 6/35 RPR JMPS | TABLEMTN | ETL.6060.INSL | 2022-05-27 | 2022-05-26 | 2022-09-27 | 2022-11-22 | 2022-08-26 | On-time | 628 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Steel | Repair | 45324067 | T3 DI ROUND MTN-TBL MTN #1 6/35 RPR JMPS | ICS
LC | 123712791 | 006/035 | T3 DI ROUND MNTN-TBL MNTN #1 6/35 COTTER | TABLEMTN | ETL.6060.TOWR | 2022-05-27 | 2022-05-26 | 2022-09-21 | 2022-11-22 | 2022-08-26 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45324063 | T3 DI ROUND MNTN-TBL MNTN #1 6/35 COTTER | ICS
LC | 123714110 | 005/066 | T3 DI GEYSERS#3-CLVRDL 5/66 RPR INSW | LAKEVLLE | ETL.1650.INSL.NCER | 2022-05-28 | 2022-05-26 | 2022-06-03 | 2022-11-22 | 2022-08-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45325996 | T3 DI GEYSERS#3-CLVRDL 5/66 RPR INSW | ICW
LC | 123714327 | 005/105 | T3 DI COLGATE-CHALLENGE 5/105 RPR GYWW | SACTO | ETL.6480.POLE.NWOD | 2022-05-28 | 2022-05-27 | 2022-07-29 | 2022-11-23 | 2022-08-25 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45343867 | T3 DI COLGATE-CHALLENGE 5/105 RPR GYWW | ICW
LC | 123715038 | 037/191A | T3 DI FULTON-PUEBLO 37/191A RPR SWTC | LAKEVLLE | ETL.1600.SWIT | 2022-05-28 | 2022-05-09 | 2022-12-19 | 2022-11-05 | 2022-08-09 | Late | 623 | Upgraded | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR | Out of Adjustment | Switch | Repair | 45326137 | T3 DI FULTON-PUEBLO 37/191A RPR SWTC | ICE
LC | 123715401 | 007/003 | T3 DI DONNELLS-MI-WUK 7/3 COTTER | VICTOR | ETL.1400.INSL | 2022-05-28 | 2022-05-27 | 2022-08-24 | 2022-11-23 | 2022-08-27 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45326061 | T3 DI DONNELLS-MI-WUK 7/3 COTTER | ICW
LC | 123715474 | 010/044 | T3 DI GEYSERS #17-FULTON 10/44 COTTER | LAKEVLLE | ETL.4770.INSL.CERA | 2022-05-28 | 2022-05-24 | 2022-06-05 | 2022-11-20 | 2022-08-24 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45325997 | T3 DI GEYSERS #17-FULTON 10/44 COTTER | ICS
LC | 123715495 | 006/074 | T3 DI GEYSERS #3-CLVRDL 6/74 RPR INSW | LAKEVLLE | ETL.1650.INSL.CERA | 2022-05-28 | 2022-05-26 | 2022-06-03 | 2022-11-22 | 2022-08-26 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | POHW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45325996 | T3 DI GEYSERS#3-CLVRDL 5/66 RPR INSW | ICW
LC | 123725038 | 014/054 | T3 EI PITTSBURG-SAN MATEO 14/54 COTTER | CONCORD | ETL.5463.INSL | 2022-05-31 | 2022-05-31 | 2022-07-25 | 2022-11-27 | 2022-08-31 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45329191 | T3 EI PITTSBURG-SAN MATEO 14/54 COTTER | ICS
LC | 123742674 | 008/069 | T3 DI MIDDLE FRK-GLD HLL 8/69 RPR SHIELD | SACTO | ETL.5140.TOWR | 2022-06-02 | 2022-05-25 | 2022-08-07 | 2022-11-21 | 2022-11-25 | On-time | 628 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45355776 | T3 DI MIDDLE FRK-GLD HLL 8/69 RPR SHIELD | ICS
LC | 123744407 | 001/011B | T3 DI GYSRS #3 CLVRDL 001/011B RPR JUMW | LAKEVLLE | ETL.1650.INSL.NCER | 2022-06-02 | 2022-06-02 | 2022-10-11 | 2022-11-29 | 2022-09-02 | On-time | 630 | Upgraded | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Wood | Repair | 45352787 | T3 DI GYSRS #3 CLVRDL 001/011B RPR JUMW | ICW
LC | 123745045 | 002/017 | T3 DI RND MTN-TBL MTN #2 002/017 COTTER | TABLEMTN | ETL.6070.TOWR | 2022-06-02 | 2022-05-31 | 2022-09-27 | 2022-11-27 | 2022-08-31 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45330435 | T3 DI RND MTN-TBL MTN #2 002/017 COTTER | ICS
LC | 123745046 | 002/017 | T3 DI RD MTN-TBL MTN #2 002/017 RPL HRDT | TABLEMTN | ETL.6070.TOWR | 2022-06-02 | 2022-05-31 | 2022-06-08 | 2022-11-27 | 2022-08-31 | On-time | 543 | Upgraded | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45331110 | T3 DI RD MTN-TBL MTN #2 002/017 RPL HRDT | ICQ
LC | 123746092 | 000/007 | T3 DI BURNS-LONE STR #2 000/007 RPR JUMW | MOSSLNDG | ETL.6240.INSL.NCER | 2022-06-02 | 2022-05-11 | 2022-07-06 | 2022-11-07 | 2022-08-11 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Wood | Repair | 45333991 | T3 DI BURNS-LONE STR #2 000/007 RPR JUMW | ICW
LC | 123747782 | 000/001A | T3 DI DIABLO-GATES #1 000/001A COTTER | PISMOBCH | ETL.5960.INSL | 2022-06-03 | 2022-06-02 | 2022-07-01 | 2022-11-29 | 2022-09-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45330482 | T3 DI DIABLO-GATES #1 000/001A COTTER | ICS
LC | 123747835 | 003/039 | T3 DI DRUM-RIO OSO #1 003/039 RPL HRDT | SACTO | ETL.1420.TOWR | 2022-06-03 | 2022-05-19 | 2022-06-21 | 2022-11-15 | 2022-08-19 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45341210 | T3 DI DRUM-SUMMIT #1 003/039 RPL HRDT | ICQ
LC | 123748388 | 002/016 | T3 DI MRGA-SN LENDRO#3 2/16 COTTER | CONCORD | ETL.2790.INSL | 2022-06-03 | 2022-06-01 | 2022-07-09 | 2022-11-28 | 2022-09-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45341929 | T3 DI MRGA-SN LENDRO#3 2/16 COTTER | ICS
LC | 123748648 | 006/033 | T3 DI RND MTN-TBL MNT #2 6/33 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2022-06-03 | 2022-05-31 | 2022-06-08 | 2022-11-27 | 2022-08-31 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45331111 | T3 DI RND MTN-TBL MNT #2 6/33 RPR STRT | ICQ
LC | 123750545 | 000/011 | T3 DI MORAGA-OAKLAND "J" 0/11 HANGER | CONCORD | ETL.2760.INSL | 2022-06-03 | 2022-06-01 | 2022-11-03 | 2022-11-28 | 2022-09-01 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace | 45341936 | T3 DI MORGA-SN LENDRO#3 0/11 HANGER | ICQ
LC | 123750546 | 000/011 | T3 DI MORAGA-OAKLAND "J" 0/11 RPL INSS | CONCORD | ETL.2760.INSL | 2022-06-03 | 2022-06-01 | 2022-11-03 | 2022-11-28 | 2022-09-01 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 3 | POHW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31605764 | DI MORGA-OAKLAND "J" 0/11 RPL INSS | 93K
LC | 123751579 | 002/019 | T3 DI MORAGA-CLAREMONT #1 2/19 RPL HRDT | CONCORD | ETL.2700.TOWR | 2022-06-03 | 2022-06-01 | 2022-07-19 | 2022-11-28 | 2022-09-01 | On-time | 543 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45381054 | T3 DI MORAGA-CLAREMONT #1 2/19 RPL HRDT | ICQ
LC | 123752037 | 001/009 | T3 DI MORAGA-OAKLAND #3 1/9 RPR INSS | CONCORD | ETL.2750.INSL.NCER | 2022-06-03 | 2022-06-01 | 2022-07-03 | 2022-11-28 | 2022-09-01 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45341932 | T3 DI MORAGA-OAKLAND #3 1/9 RPR INSS | ICS
LC | 123758426 | 000/010A | T3 DI DRUM-SUMMIT #1 0/10A GUY COTR | SACTO | ETL.1440.POLE.NWOD | 2022-06-03 | 2022-06-01 | 2022-08-01 | 2022-11-28 | 2022-09-01 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45343973 | T3 DI DRUM-SUMMIT #1 0/10A GUY COTR | ICW
LC | 123759179 | 006/048 | T3 DI MORAGA-SAN LENDRO #2 6/48 COTR KEY | CONCORD | ETL.2780.INSL.NCER | 2022-06-03 | 2022-06-02 | 2022-07-03 | 2022-11-29 | 2022-09-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45341933 | T3 DI MORAGA-SAN LENDRO #2 6/48 COTR KEY | ICS
LC | 123759338 | 017/068 | T3 DI DIABLO-GATES #1 17/68 COTTER | PISMOBCH | ETL.5960.INSL | 2022-06-03 | 2022-06-02 | 2022-08-25 | 2022-11-29 | 2022-09-02 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45330489 | T3 DI DIABLO-GATES #1 17/68 COTTER | ICS
LC | 123762291 | 000/001B | T3 EI DRUM-HIGGINS 000/001B RRL STRW | SACTO | ETL.4393.POLE.WOOD | 2022-06-04 | 2022-06-04 | 2022-06-26 | 2022-12-01 | 2022-09-04 | On-time | 372 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605285 | T3 EI DRUM-HIGGINS 000/001B RRL STRW | 70Y
LC | 123771047 | 003/075 | T3 DI DRM-GRS VLLY- WEIMR 3/075 RPR OPGW | SACTO | ETL.6760.POLE.WOOD | 2022-06-06 | 2022-06-06 | 2022-07-18 | 2022-12-03 | 2022-09-06 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45344018 | T3 DI DRM-GRS VLLY- WEIMR 3/075 RPR OPGW | ICW
LC | 123778279 | ?010/007 | T3 DI SNTH LN-HLF MOON BY ?10/7 RPL STRW | METCALF | ETL.7212.POLE.WOOD | 2022-06-07 | 2022-06-02 | 2022-07-20 | 2022-11-29 | 2022-09-02 | On-time | 372 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606172 | T3 DI SNTH LN-HLF MOON BY ?10/7 RPL INSW | 70Y
LC | 123784345 | 025/199 | T3 DI CRBRRY SS-RND MTN 25/199 COMPLETE | TABLEMTN | ETL.5410.INSL | 2022-06-07 | 2022-05-25 | 2022-08-22 | 2022-11-21 | 2022-08-25 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45333725 | T3 DI CRBRRY SS-RND MTN 25/199 RPR INSS | ICS
LC | 123785910 | 010/045 | T3 DI GEYSERS #12-FULTON 10/45 RPR STRT | LAKEVLLE | ETL.4750.TOWR | 2022-06-08 | 2022-05-24 | 2022-08-09 | 2022-11-20 | 2022-08-24 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45341218 | T3 DI GEYSERS #12-FULTON 10/45 RPR STRT | ICQ
LC | 123791219 | 008/068 | T3 EI MIDDLE FORK-GLD HILL 8/68 COMPLETE | SACTO | ETL.5140.TOWR | 2022-06-08 | 2022-06-08 | 2022-06-25 | 2022-12-05 | 2022-09-08 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB NTDE | Land/Enviro Issue | Other | Access Issue
LC | 123791275 | 008/067 | T3 EI MIDDLE FORK-GLD HILL 8/67 COMPLETE | SACTO | ETL.5140.TOWR | 2022-06-08 | 2022-06-08 | 2022-06-25 | 2022-12-05 | 2022-09-08 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB NTDE | Land/Enviro Issue | Other | Access Issue
LC | 123793416 | ?009/008 | T3 DI SNEATH LANE-HLF MN BAY ?9/8 HANGER | METCALF | ETL.7212.INSL.CERA | 2022-06-08 | 2022-05-27 | 2022-07-20 | 2022-11-23 | 2022-08-27 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45345069 | T3 DI SNEATH LANE-HLF MN BAY ?9/8 HANGER | ICW
LC | 123793656 | 000/011 | T3 DI SALMON CREEK TAP 0/11 INS COTTER | LAKEVLLE | ETL.6981.INSL | 2022-06-08 | 2022-06-03 | 2022-10-27 | 2022-11-30 | 2022-12-03 | On-time | 630 | Upgraded | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45353025 | T3 DI SALMON CREEK TAP 0/11 INS COTTER | ICW
LC | 123793691 | 009/005 | T3 DI MNTE RIO-FLTN-FLTN 9/5 RPR INSW | LAKEVLLE | ETL.7630.INSL.CERA | 2022-06-08 | 2022-06-04 | 2022-06-29 | 2022-12-01 | 2022-09-04 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45341205 | T3 DI MNTE RIO-FLTN-FLTN 9/5 RPR INSW | ICW
LC | 123793831 | 003/081 | T3 DI DRUM-G.V.-WEIMAR 3/81 RPR ADSS | SACTO | ETL.6760.POLE.WOOD | 2022-06-08 | 2022-06-06 | 2022-10-31 | 2022-12-03 | 2022-09-04 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Repair | 45344043 | T3 DI DRUM-G.V.-WEIMAR 3/81 RPR ADSS | ICW
LC | 123799426 | 002/018 | T3 DI MORAGA-SAN LEANDRO #1 2/18 COTTER | CONCORD | ETL.2770.INSL | 2022-06-09 | 2022-05-31 | 2022-07-08 | 2022-11-27 | 2022-08-31 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45342053 | T3 DI MORAGA-SAN LEANDRO #1 2/18 COTTER | ICS
LC | 123802279 | ?009/000 | T3 DI SNTH LN HLF MN BY ?9/0 COTR KEY | METCALF | ETL.7212.INSL.NCER | 2022-06-09 | 2022-05-31 | 2022-07-21 | 2022-11-27 | 2022-08-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45342050 | T3 DI SNTH LN HLF MN BY ?9/0 COTR KEY | ICW
LC | 123813684 | 006/051 | T3 DI MIDDLE FRK-GLD HILL 6/51L RPR STRW | SACTO | ETL.5140.POLE.WDPS | 2022-06-10 | 2022-06-09 | 2022-06-11 | 2022-12-06 | 2022-09-09 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45342236 | T3 DI MIDDLE FRK-GLD HILL 6/51L RPR STRW | ICW
LC | 123815903 | 000/002 | T3 DI TIGER CREEK-VLLY SPRNGS 0/2 COTTER | VICTOR | ETL.5790.INSL | 2022-06-10 | 2022-06-06 | 2022-08-02 | 2022-12-03 | 2022-09-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45342288 | T3 DI TIGER CREEK-VLLY SPRNGS 0/2 COTTER | ICS
LC | 123816800 | 009/042 | T3 DI TASSAJARA-NEWARK 009/042 COTTER | CONCORD | ETL.5920.INSL | 2022-06-10 | 2022-06-06 | 2022-07-14 | 2022-12-03 | 2022-09-06 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45345063 | T3 DI TASSAJARA-NEWARK 009/042 COTTER | ICS
LC | 123817876 | X000/002 | T3 DI DIABLO-MESA X0/2 RPR OPGW | PISMOBCH | ETL.4620.TOWR | 2022-06-10 | 2022-06-03 | 2022-06-03 | 2022-11-30 | 2022-09-03 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45342031 | T3 DI DIABLO-MESA X0/2 RPR OPGW | ICS
LC | 123819363 | 006/029 | T3 DI MORAGA-CASTRO VALLEY 6/29 RPR OPGW | CONCORD | ETL.5250.TOWR | 2022-06-10 | 2022-06-07 | 2022-07-08 | 2022-12-04 | 2022-09-07 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45342056 | T3 DI MORAGA-CASTRO VALLEY 6/29 RPR OPGW | ICS
LC | 123820225 | 011/051 | T3 DI SAN RAMON-MORAGA 011/051 COTTER | CONCORD | ETL.5660.INSL | 2022-06-10 | 2022-06-08 | 2022-07-08 | 2022-12-05 | 2022-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45342054 | T3 DI SAN RAMON-MORAGA 011/051 COTTER | ICS
LC | 123820607 | 005/039 | T3 DI MORGA-SN LEANDRO #1 5/39 BNT STEEL | CONCORD | ETL.2770.TOWR | 2022-06-10 | 2022-06-07 | 2022-11-28 | 2022-12-04 | 2022-12-07 | On-time | 543 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45351946 | T3 DI MORGA-SN LEANDRO #1 5/39 BNT STEEL | ICQ
LC | 123821894 | 004/025 | T3 DI RND MTN-TBL MTN #1 4/025 COTTER | TABLEMTN | ETL.6060.INSL | 2022-06-11 | 2022-06-08 | 2022-10-04 | 2022-12-05 | 2022-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45342466 | T3 DI RND MTN-TBL MTN #1 4/025 COTTER | ICS
LC | 123827496 | ?009/004 | T3 EI SNTH LNE-HLF MN BY ?9/4 COTTER | METCALF | ETL.7212.INSL.CERA | 2022-06-12 | 2022-06-12 | 2022-07-20 | 2022-12-09 | 2022-09-12 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45345071 | T3 EI SNTH LNE-HLF MN BY ?9/4 COTTER | ICS
LC | 123832269 | :001/002 | T3 DI FLTN CLSTG :1/2 COTTER | LAKEVLLE | ETL.6880.INSL.NCER | 2022-06-13 | 2022-06-09 | 2022-07-19 | 2022-12-06 | 2022-09-09 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45343707 | T3 DI FLTN CLSTG :1/2 COTTER | ICW
LC | 123842589 | 004/036 | T3 DI MORAGA-OAKLAND "J" 4/36 RPR INSS | CONCORD | ETL.2760.INSL | 2022-06-14 | 2022-06-04 | 2022-07-08 | 2022-12-01 | 2022-09-04 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45345067 | T3 DI MORAGA-OAKLAND "J" 4/36 RPR INSS | ICS
LC | 123842908 | 006/001 | T3 DI BRDGVLL-GRBRVLL 6/001 RPL INSW | EUREKA | ETL.6220.INSL.NCER | 2022-06-14 | 2022-06-09 | 2022-09-21 | 2022-12-06 | 2022-09-09 | On-time | 508 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31606366 | T3 DI BRDGVLL-GRBRVLL 6/001 RPL INSW | 93I
LC | 123844743 | :002/015 | T3 DI ROCK CREEK-POE 2/15 RPR SHLS | TABLEMTN | ETL.5630.TOWR | 2022-06-14 | 2022-06-01 | 2022-06-24 | 2022-11-28 | 2022-08-30 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45343557 | T3 DI ROCK CREEK-POE 2/15 RPR SHLS | ICS
LC | 123852890 | 033/166 | T3 DI EAGLE RCK-FLTN SV 033/166 RPR INSS | LAKEVLLE | ETL.4392.INSL.NCER | 2022-06-15 | 2022-06-08 | 2022-07-01 | 2022-12-05 | 2022-09-08 | On-time | 628 | Upgraded | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45352784 | T3 DI EAGLE RCK-FLTN SV 033/166 RPR INSS | ICS
LC | 123862042 | 008/112 | T3 EI MIDDLE FORK #1 08/112 COMPLETE | SACTO | ETL.8405.POLE.WOOD | 2022-06-17 | 2022-06-17 | 2022-06-25 | 2022-12-14 | 2022-09-17 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 FRAB | Land/Enviro Issue | Other | Access Issue
LC | 123862043 | 008/113 | T3 EI MIDDLE FORK #1 8/113 COMPLETE | SACTO | ETL.8405.POLE.WOOD | 2022-06-17 | 2022-06-17 | 2022-06-25 | 2022-12-14 | 2022-09-17 | On-time | 625 | B - Urgt Compliance | Closed | HFTD 3 | RELW INSP COMP OH FMOB TR3 FRAB | Land/Enviro Issue | Other | Access Issue
LC | 123862537 | 007/001 | T3 DI DNLS MI WK 7/1 COTTER | VICTOR | ETL.1400.INSL.NCER | 2022-06-17 | 2022-06-13 | 2022-08-24 | 2022-12-10 | 2022-09-13 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45351135 | T3 DI DNLS MI WK 7/1 COTTER | ICS
LC | 123863083 | 002/018 | T3 DI EL DOR-MISS FT #2 2/18 RPR INSS | SACTO | ETL.1540.INSL.CERA | 2022-06-17 | 2022-06-14 | 2022-07-08 | 2022-12-11 | 2022-09-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45350143 | T3 DI EL DOR-MISS FT #2 2/18 RPR INSS | ICS
LC | 123867365 | :010/005 | T3 DI FLTON-CLSTOGA :010/005 RPL TIED | LAKEVLLE | ETL.6880.INSL.CERA | 2022-06-17 | 2022-06-14 | 2022-11-02 | 2022-12-11 | 2022-09-14 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45353021 | T3 DI FLTON-CLSTOGA :010/005 RPL TIED | ICW
LC | 123868322 | 002/020 | T3 DI MORAGA-CLAREMONT #1 2/20 RPR STRT | CONCORD | ETL.2700.INSL | 2022-06-17 | 2022-06-01 | 2022-11-14 | 2022-11-28 | 2022-12-01 | On-time | 543 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Tower | Repair | 45384267 | T3 DI MORAGA-CLAREMONT #1 2/20 RPR STRT | ICQ
LC | 123870672 | 008/045 | T3 DI CASTRO VALLEY-NEWARK 8/45 RPR OPGW | CONCORD | ETL.4450.TOWR | 2022-06-18 | 2022-06-10 | 2022-07-23 | 2022-12-07 | 2022-09-10 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45351274 | T3 DI CASTRO VALLEY-NEWARK 8/45 RPR OPGW | ICS
LC | 123871039 | 006/120 | T3 DI COLGATE-CHALLENGE 6/120 RPR CNDW | SACTO | ETL.6480.INSL.NCER | 2022-06-18 | 2022-06-15 | 2022-08-25 | 2022-12-12 | 2022-09-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45350146 | T3 DI COLGATE-CHALLENGE 6/120 RPR CNDW | ICW
LC | 123874028 | 007/187 | T3 DI DRUM-GRSS VLLY-WMR 7/187 COTTER | SACTO | ETL.6760.INSL.NCER | 2022-06-18 | 2022-06-15 | 2022-09-01 | 2022-12-12 | 2022-09-15 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45350149 | T3 DI DRUM-GRSS VLLY-WMR 7/187 COTTER | ICW
LC | 123891609 | 004/027 | T3 DI CSTRO VLY-NWRK 4/27 RPR SHLS | CONCORD | ETL.4450.TOWR | 2022-06-21 | 2022-06-16 | 2022-08-19 | 2022-12-13 | 2022-09-16 | On-time | 628 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45364307 | T3 DI CSTRO VLY-NWRK 4/27 RPR SHLS | ICS
LC | 123892306 | 010/042 | T3 DI PITTSBURG-SAN RAMON 10/42 COTR KEY | CONCORD | ETL.5490.INSL | 2022-06-21 | 2022-06-16 | 2022-07-14 | 2022-12-13 | 2022-09-14 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45351571 | T3 DI PITTSBURG-SAN RAMON 10/42 COTR KEY | ICS
LC | 123892349 | 012/220 | T3 DI COLGATE-CHALLENGE 12/220 RPR JUMW | SACTO | ETL.6480.INSL.NCER | 2022-06-21 | 2022-06-16 | 2022-08-24 | 2022-12-13 | 2022-09-16 | On-time | 630 | Upgraded | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Wood | Repair | 45378077 | T3 DI COLGATE-CHALLENGE 12/220 RPR JUMW | ICW
LC | 123892378 | :001/011 | T3 DI EAGLE RCK-CRTNA :001/011 RPL INSS | WILLITS | ETL.1470.INSL.NCER | 2022-06-21 | 2022-06-16 | 2022-07-25 | 2022-12-13 | 2022-09-16 | On-time | 532 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31608890 | DI EAGLE RCK-CRTNA RPL INSS IN 3 TWRS. | 93K
LC | 123892431 | 005/032 | T3 DI CASTRO VLLY-NWRK 5/32 RPR OPGW | CONCORD | ETL.4450.TOWR | 2022-06-21 | 2022-06-10 | 2022-07-14 | 2022-12-07 | 2022-09-08 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCH COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45351570 | T3 DI CASTRO VLLY-NWRK 5/32 RPR OPGW | ICS
LC | 123892437 | 013/072 | T3 DI FULTON-IGNACIO #1 13/072 RPR INSS | LAKEVLLE | ETL.4680.INSL | 2022-06-21 | 2022-06-16 | 2022-07-01 | 2022-12-13 | 2022-09-16 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45353020 | T3 DI FULTON-IGNACIO #1 13/072 RPR INSS | ICS
LC | 123894219 | 006/065 | T3 DI SNTH LN PCFC 6/65 RPL INSW | METCALF | ETL.7575.INSL.NCER | 2022-06-22 | 2022-06-17 | 2022-11-04 | 2022-12-14 | 2022-09-17 | On-time | 508 | Upgraded | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31608532 | T3 DI SNTH LN PCFC 6/65 RPL INSW | 93I
LC | 123894454 | 005/051 | T3 DI DRM HGNS 5/51 COTR KEY | SACTO | ETL.4393.SWIT | 2022-06-22 | 2022-06-17 | 2022-07-15 | 2022-12-14 | 2022-09-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45355769 | T3 DI DRM HGNS 5/51 COTR KEY | ICS
LC | 123900813 | 012/051 | T3 DI PTTSBRG-EASTSHORE 12/51 RPR INSS | CONCORD | ETL.5462.INSL | 2022-06-22 | 2022-06-17 | 2022-07-14 | 2022-12-14 | 2022-09-17 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45354802 | T3 DI PTTSBRG-EASTSHORE 12/51 RPR INSS | ICS
LC | 123901591 | 000/002 | T3 DI FRKS OF THE BTTE TAP 0/2 RPR INSW | TABLEMTN | ETL.6722.INSL.NCER | 2022-06-22 | 2022-06-20 | 2022-06-30 | 2022-12-17 | 2022-09-20 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45354312 | T3 DI FRKS OF THE BTTE TAP 0/2 RPR INSW | ICW
LC | 123903405 | 006/057 | T3 DI MONTA VISTA-BURNS 6/57 RPR JUMW | MOSSLNDG | ETL.7590.INSL.NCER | 2022-06-23 | 2022-06-20 | 2022-08-29 | 2022-12-17 | 2022-09-20 | On-time | 630 | Upgraded | Closed | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Wood | Repair | 45388703 | T3 DI MONTA VISTA-BURNS 6/57 RPR JUMW | ICW
LC | 123905774 | 003/023 | T3 SOBRANTE-R #1 003/023 HANGER | CONCORD | ETL.3770.INSL | 2022-06-23 | 2022-06-23 | 2022-07-26 | 2022-12-20 | 2022-09-23 | On-time | 543 | B - Urgt Compliance | Closed | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Tower | Replace | 45354249 | T3 SOBRANTE-R #1 003/023 HANGER | ICQ
LC | 123907481 | 021/168 | T3 DI CRESTA-RIO OSO 21/168 COTR KEY | TABLEMTN | ETL.4590.INSL | 2022-06-23 | 2022-06-21 | 2022-07-11 | 2022-12-18 | 2022-09-19 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45354317 | T3 DI CRESTA-RIO OSO 21/168 COTR KEY | ICS
LC | 123911766 | 002/026 | T3 DI DRUM-SUMMIT #1 2/26 RPR CNDW | SACTO | ETL.1440.INSL.NCER | 2022-06-24 | 2022-06-01 | 2022-07-14 | 2022-11-28 | 2022-08-30 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45355773 | T3 DI DRUM-SUMMIT #1 2/26 RPR CNDW | ICW
LC | 123914932 | ?001/003 | T3 DI SNEATH LN-HMB ?1/3 RPL INSW | METCALF | ETL.7212.INSL.CERA | 2022-06-24 | 2022-06-10 | 2022-07-19 | 2022-12-07 | 2022-09-10 | On-time | 508 | Upgraded | Closed | HFTD 3 | RELW FIRE ACCH COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31607386 | T3 DI SNEATH LN-HMB ?1/3 RPL INSW | 93I
LC | 123915111 | 023/092 | T3 DI PITTSBURG-SAN MATEO 23/92 RPR OPGW | CONCORD | ETL.5463.TOWR | 2022-06-24 | 2022-06-23 | 2022-07-08 | 2022-12-20 | 2022-09-23 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45354937 | T3 DI PITTSBURG-SAN MATEO 23/92 RPR OPGW | ICS
LC | 123916113 | 011/162 | T3 DI WEIMAR #1 11/162 EMRG RPL | SACTO | ETL.7560.POLE.WOOD | 2022-06-24 | 2022-06-22 | 2022-10-21 | 2022-12-19 | 2022-09-22 | On-time | 437 | B - Urgt Compliance | Closed | HFTD 3 | POHW COMP OH TR3 PRTO AIR FRAB | Fire | Emergency | Replace | 74050021 | WEIMAR #1 EMERGENCY REBUILD | 92F
LC | 123931965 | 003/041B | T3 DI IGNCIO BLNS #1 3/41B COTTER | LAKEVLLE | ETL.7140.INSL.NCER | 2022-06-27 | 2022-06-09 | 2022-09-27 | 2022-12-06 | 2022-09-07 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45363396 | T3 DI IGNCIO BLNS #1 3/41B COTTER | ICW
LC | 123941395 | 011/010 | T3 DI DONNELLS-MI-WUK 11/10 COTTER CMT | VICTOR | ETL.1400.INSL.CERA | 2022-06-28 | 2022-06-02 | 2022-08-24 | 2022-11-29 | 2022-09-02 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45363087 | T3 DI DONNELLS-MI-WUK 14/002 COTTER | ICW
LC | 123945685 | 000/002 | T3 DI DONNELLS-MI-WUK 0/2 RPR CONN | VICTOR | ETL.1400.INSL.NCER | 2022-06-28 | 2022-06-24 | 2022-10-09 | 2022-12-21 | 2022-09-24 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45363092 | T3 DI DONNELLS-MI-WUK 0/2 RPR CONN | ICW
LC | 123960956 | 008/149 | T3 DI FNCH MDWS MDDL FRK 8/149 RPR JMPW | SACTO | ETL.6870.INSL.NCER | 2022-06-30 | 2022-06-27 | 2022-08-26 | 2022-12-24 | 2022-09-27 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Wood | Repair | 45362982 | T3 DI FNCH MDWS MDDL FRK 8/149 RPR JMPW | ICW
LC | 123971539 | 000/002 | T3 DI SLY CREEK TAP 0/2 COTTER | TABLEMTN | ETL.4221.INSL.CERA | 2022-07-01 | 2022-06-28 | 2022-07-22 | 2022-12-25 | 2022-09-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45362857 | T3 DI SLY CREEK TAP 0/2 COTTER | ICW
LC | 123973519 | 000/001 | T3 DI SLY CREEK TAP 0/1L COTTER | TABLEMTN | ETL.4221.POLE.STPS | 2022-07-01 | 2022-06-28 | 2022-07-22 | 2022-12-25 | 2022-09-28 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45362858 | T3 DI SLY CREEK TAP 0/1L COTTER | ICW
LC | 124162167 | 023/106 | T3 DI CONTR CSTA MRAGA#1 23/106 RPL HRDT | CONCORD | ETL.5452.TOWR | 2022-07-25 | 2022-06-25 | 2022-10-04 | 2022-12-22 | 2022-09-25 | On-time | 543 | Upgraded | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45414703 | T3 DI CONTR CSTA MRAGA#1 23/106 RPL HRDT | ICQ
LC | 124194068 | 025/100 | T3 DI PTTSBRG-ESTSHRE 25/100 RPR COTTER | CONCORD | ETL.5462.INSL | 2022-07-29 | 2022-06-27 | 2022-08-22 | 2022-12-24 | 2022-09-27 | On-time | 628 | B - Urgt Compliance | Closed | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45400558 | T3 DI PTTSBRG-ESTSHRE 25/100 RPR COTTER | ICS
LC | 124212893 | 009/097 | T3 DI GRN VLY CMP EVRS 9/097 RPR INSW | MOSSLNDG | ETL.1710.INSL.CERA | 2022-08-02 | 2022-06-29 | 2022-09-14 | 2022-12-26 | 2022-09-27 | On-time | 630 | B - Urgt Compliance | Closed | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45414193 | T3 DI GRN VLY CMP EVRS 9/097 RPR INSW | ICW
LC | 121391866 | B016/365 | T2 DI DRM-GASS VLY-WMR-B16/365 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-05-24 | 2021-05-17 |  | 2022-05-17 | 2022-05-17 | Late | 372 | B - Urgt Compliance | Open | HFTD 2 | POHW OTHR FIRE ACCM OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541884 | T2 DI DRM-GRS VLY-WMR 15/351 RPL STRW | 70Y
LC | 121797006 | T098 | T3 DI MIDWAY-SANTA MARIA T098 RPR STRT | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 |  | 2022-01-22 | 2022-01-26 | Late | 543 | B - Urgt Compliance | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45098953 | T3 DI MIDWAY-SANTA MARIA T098 RPR STRT | ICQ
LC | 123156289 | 002/017 | T3 DI MORAGA-OAKLAND #1 02/17 BNT STEEL | CONCORD | ETL.2720.TOWR | 2022-03-19 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 543 | B - Urgt Compliance | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45617016 | T3 DI MORAGA-OAKLAND #1 02/17 BNT STEEL | ICQ
LC | 123598493 | -017/008 | T3 EI FULTON-CALISTOGA -17/8 RPL POLE | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-15 | 2022-05-15 |  | 2022-11-11 | 2022-08-15 | Late | 372 | B - Urgt Compliance | Open | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31609129 | T3 EI FULTON-CALISTOGA -17/8 RPL POLE | 70Y
LC | 123673403 | 001/011 | T3 DI GEYSERS #13 TAP 1/11 RPL SWTC | LAKEVLLE | ETL.4781.INSL | 2022-05-23 | 2022-05-18 |  | 2022-11-14 | 2022-08-16 | Late | 435 | B - Urgt Compliance | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Switch-Steel | Replace | 31605538 | DI GEYSERS #13 TAP 1/11 RPL SWTC | 93S
LC | 123706772 | 006/030 | T3 DI EAGLE RCK-FLTN-SLVRDO 6/30 COTTER | LAKEVLLE | ETL.4392.INSL.CERA | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-08-24 | Late | 628 | B - Urgt Compliance | Open | HFTD 3 | RELW ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45325994 | T3 DI EAGLE RCK-FLTN-SLVRDO 6/30 COTTER | ICS
LC | 123713822 | 001/007 | T3 DI GEYSERS#11-EAGLE RCK 1/7 RPL INSS | LAKEVLLE | ETL.4391.INSL.CERA | 2022-05-28 | 2022-05-24 |  | 2022-11-20 | 2022-08-24 | Late | 532 | B - Urgt Compliance | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31604965 | T3 DI GEYSERS#11-EAGLE RCK 1/7 RPL INSS | 93K
LC | 123714804 | 016/003 | T3 DI DONNELLS-MI-WUK 16/3 RPL INSW | VICTOR | ETL.1400.INSL.CERA | 2022-05-28 | 2022-05-27 |  | 2022-11-23 | 2022-08-27 | Late | 508 | B - Urgt Compliance | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31605105 | T3 DI DONNELLS-MI-WUK 16/3 RPL INSW | 93I
LC | 123715068 | 002/011 | T3 DI GEYSERS #17-FULTON 02/11 COMPLETE | LAKEVLLE | ETL.4770.INSL.CERA | 2022-05-28 | 2022-05-05 |  | 2022-11-01 | 2022-08-05 | Late | 628 | B - Urgt Compliance | Open | HFTD 3 | POHW ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 31604476 | T3 EI GYSRS #17-FLTN RPL INSS IN 2 TWRS | 93K
LC | 123775893 | 004/081 | T3 EI FRNCH MDWS-MDDLE FRK 4/81 RMV VEG | SACTO | ETL.6870.POLE.NWOD | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-09-06 | Late | 564 | B - Urgt Compliance | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123775894 | 004/085 | T3 EI FRNCH MDWS-MDLE FRK 4/85 RMV VEG | SACTO | ETL.6870.POLE.NWOD | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-09-06 | Late | 564 | B - Urgt Compliance | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123781556 | 012/006 | T3 DI LAURELES-OTTER 12/6 RPR INSW | MOSSLNDG | ETL.7380.INSL | 2022-06-07 | 2022-05-20 |  | 2022-11-16 | 2022-08-20 | Late | 630 | B - Urgt Compliance | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45333992 | T3 DI LAURELES-OTTER 12/6 RPR INSW | ICW
LC | 123790452 | 007/131 | T3 EI FRNCH MEADW-MID FRK 7/131 RMV VEG | SACTO | ETL.6870.POLE.WOOD | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-09-08 | Late | 564 | B - Urgt Compliance | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123911823 | 000/008 | T3 DI MORAGA-OAKLAND #3 0/8 RPR STRT | CONCORD | ETL.2740.TOWR | 2022-06-24 | 2022-06-01 |  | 2022-11-28 | 2022-08-30 | Late | 543 | B - Urgt Compliance | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45375864 | T3 DI MORAGA-OAKLAND #3 0/8 RPR STRT | ICQ
LC | 120423250 | 005/038 | T2 SOBRANTE-MORAGA 0/005A CANCEL | CONCORD | ETL.3742.POLE.NWOD | 2021-01-12 | 2021-01-12 |  | 2022-01-12 | 2022-01-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | Missing | Guy Wire-Steel | Install | 45168048 | T2 SOBRANTE-MORAGA 0/005A INS GYWS | ICS
LC | 120425161 | 023/004 | T2 TRINITY-MAPLE CREEK 23/4 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-01-13 | 2021-01-13 |  | 2022-01-13 | 2022-01-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31514142 | T2 DI TRINITY-MAPLE CRK 23/003 RPLC STRW | 70Y
LC | 120425496 | 023/002 | T2 NN TRINITY-MAPLE CREEK 23/2 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2021-01-13 | 2021-01-13 |  | 2022-01-13 | 2022-01-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31514142 | T2 DI TRINITY-MAPLE CRK 23/003 RPLC STRW | 70Y
LC | 120502985 | 015/307 | T2 WV COLGATE-PALERMO 15/307 RPR FENCE | TABLEMTN | ETL.6500.POLE.NWOD | 2021-02-05 | 2021-02-05 |  | 2022-02-05 | 2022-02-05 | Late | 931 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW OTHR OH FMOB TR2 PRTO | Encroachment | Road | Remove
LC | 120534971 | 004/024 | WV T2 TULACAY-VACA 17/083 RPR INSS | LAKEVLLE | ETL.5800.INSL.NCER | 2021-02-15 | 2021-02-15 |  | 2022-02-15 | 2022-02-15 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45136663 | WV T2 TULACAY-VACA 17/083 RPR INSS | ICS
LC | 120651589 | 009/170 | T2 DI MNTA VSTA-LOS GATOS 9/170 RPR GYWW | METCALF | ETL.7610.POLE.WOOD | 2021-03-17 | 2021-03-16 |  | 2022-03-16 | 2022-03-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45183633 | T2 DI MNTA VSTA-LOS GATOS 9/170 RPR GYWW | ICW
LC | 120658282 | 001/010C | T2 EI KANAKA TAP 1/010C RPL GYWW | TABLEMTN | ETL.4223.POLE.WOOD | 2021-03-18 | 2021-03-18 |  | 2022-03-18 | 2022-03-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45212389 | T2 EI KANAKA TAP 1/010C RPL GYWW | ICW
LC | 120667199 | 018/154 | T2 EI CRAG VIEW-CASCDE 18/154R RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-20 | 2021-03-20 |  | 2022-03-20 | 2022-03-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31552992 | T2 EI CRAG VIEW-CASCDE 18/154R RPL STRW | 70Y
LC | 120667311 | 018/154 | T2 EI CRAG VIEW-CASCD 18/154L RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-20 | 2021-03-20 |  | 2022-03-20 | 2022-03-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31552992 | T2 EI CRAG VIEW-CASCDE 18/154R RPL STRW | 70Y
LC | 120674485 | 009/175 | T2 DI MNT VISTA-LOS GATOS 9/175 RPL INSW | METCALF | ETL.7610.INSL | 2021-03-22 | 2021-03-16 |  | 2022-03-16 | 2022-03-16 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31534651 | T2 DI MNT VISTA-LOS GATOS 9/175 RPL INSW | 93I
LC | 120691623 | 011/100 | T2 EI CRAG VW-CSCDE 11/100R RPR ANCW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-25 | 2021-03-25 |  | 2022-03-25 | 2022-03-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH RTNR FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 45267708 | T2 EI CRAG VW-CSCDE 11/100R RPR ANCW | ICW
LC | 120696458 | 008/070 | T2 EI ELDRDO-MSSRI FLAT #1 8/70 RMV HRDW | SACTO | ETL.1530.POLE.NWOD | 2021-03-26 | 2021-03-26 |  | 2022-03-26 | 2022-03-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 44737830 | T2 EI ELDRDO-MSSRI FLAT #1 8/70 RMV HRDW | ICW
LC | 120706089 | B016/364 | T2 EI DRUM-GV-WEIMAR B16/364 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2021-03-29 | 2021-03-29 |  | 2022-03-29 | 2022-03-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535167 | T2 EI DRUM-GV-WEIMAR B16/364 RPL POLE | 70Y
LC | 120708017 | 015/359 | T2 EI DRM-GRS VLY-WMR 015/359 RPR GWRW | SACTO | ETL.6760.POLE.WOOD | 2021-03-29 | 2021-03-29 |  | 2022-03-29 | 2022-03-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44737717 | T2 EI DRM-GRS VLY-WMR 015/359 RPR GWRW | ICW
LC | 120708357 | 010/091 | T2 DI ELDORADO-MSR FLT #1 10/91 INS HRDS | SACTO | ETL.1530.POLE.NWOD | 2021-03-29 | 2021-03-29 |  | 2022-03-29 | 2022-03-29 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Steel | Install | 44737651 | T2 DI ELDORADO-MSR FLT #1 10/91 INS HRDS | ICS
LC | 120712285 | 016/374 | T2 EI DRUM-GV-WEIMAR 16/374 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2021-03-30 | 2021-03-30 |  | 2022-03-30 | 2022-03-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31535167 | T2 EI DRUM-GV-WEIMAR B16/364 RPL POLE | 70Y
LC | 120714003 | 007/064 | T2 EI CRAG VIEW-CASCADE 7/64R CANCEL | TABLEMTN | ETL.1350.POLE.WDPS | 2021-03-30 | 2021-03-30 |  | 2022-03-30 | 2022-03-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544910 | T2 DI CRAG VIEW-CASCADE 1/15 RPL STRW | 70Y
LC | 120734802 | :006/008 | T2 EI BLT-RVBNK-MLNS SW ST :6/8 RPL INSS | VICTOR | ETL.1070.INSL.NCER | 2021-04-02 | 2021-04-02 |  | 2022-04-02 | 2022-04-02 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31535290 | T2 BLLT-RBK-MLNS SW :005/001 RPL INSW | 93I
LC | 120737558 | 018/075 | T2NT EI GEYSERS #12-FTN 18/75 RMV DEBRIS | LAKEVLLE | ETL.4750.TOWR | 2021-04-02 | 2021-04-02 |  | 2022-04-02 | 2022-04-02 | Late | 931 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAB NTDE | Encroachment | Right of Way | Remove
LC | 120744331 | 050/203 | T2 EI DIABLO-GATES #1 050/203 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2021-04-05 | 2021-04-05 |  | 2022-04-05 | 2022-04-05 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068474 | T2 EI DIABLO-GATES #1 050/203 RPR GYWS | ICS
LC | 120745819 | 006/101 | T2 EI PIT #1-HT CK #2-BNY 6/101 RPL PL | TABLEMTN | ETL.7040.POLE.WOOD | 2021-04-05 | 2021-04-05 |  | 2022-04-05 | 2022-04-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31535961 | T2 EI PIT #1-HT CK #2-BNY 6/101 RPL PL | 70Y
LC | 120751317 | 010/089 | T2 DI ELDORADO-MSR FLT #1 10/89 INS HRDS | SACTO | ETL.1530.POLE.NWOD | 2021-04-06 | 2021-03-29 |  | 2022-03-29 | 2022-03-29 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Steel | Install | 44737747 | T2 DI ELDORADO-MSR FLT #1 10/89 INS HRDS | ICS
LC | 120755323 | 005/082 | T2 EI PIT #1-HT CK #2-BNY 5/82 RPL HRDW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-04-07 | 2021-04-07 |  | 2022-04-07 | 2022-04-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213848 | T2 EI PIT #1-HT CK #2-BNY 5/82 RPL HRDW | ICW
LC | 120757110 | 014/328 | T2 EI DRM-GRSS VLLY-WMR 014/328 STRW RPL | SACTO | ETL.6760.POLE.WOOD | 2021-04-07 | 2021-04-07 |  | 2022-04-07 | 2022-04-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544907 | T2 EI DRM-GRSS VLLY-WMR 014/328 STRW RPL | 70Y
LC | 120760982 | 003/021 | T2 EI MS LANDING-METCALF 3/21 RPL ANCHS | MOSSLNDG | ETL.6050.TOWR | 2021-04-07 | 2021-04-07 |  | 2022-04-07 | 2022-04-07 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Anchor-Steel | Replace | 31596828 | T2 EI MS LANDING-METCALF 3/21 RPL ANCHS | 93Z
LC | 120762988 | 013/307 | T2 EI DRM-GRSS VLLY-WMR 013/307 REFRAME | SACTO | ETL.6760.POLE.WOOD | 2021-04-08 | 2021-04-08 |  | 2022-04-08 | 2022-04-08 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31537166 | T2 EI DRM-GRSS VLLY-WMR 013/307 RPL INSW | 93I
LC | 120763863 | 010/088 | T2 DI ELDRD-MSR FLT #1 10/88 INS HRDS | SACTO | ETL.1530.POLE.NWOD | 2021-04-08 | 2021-03-29 |  | 2022-03-29 | 2022-03-29 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Steel | Install | 44737748 | T2 DI ELDRD-MSR FLT #1 10/88 INS HRDS | ICS
LC | 120764505 | 045/391 | T2 EI RND MTN-CTNWD 45/391 RMV VEG | TABLEMTN | ETL.5650.TOWR | 2021-04-08 | 2021-04-08 |  | 2022-04-08 | 2022-04-08 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 120772283 | 003/030 | T2 EI PT 1-HAT CRK 2-BURN 3/30 RPR HRDW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-04-09 | 2021-04-09 |  | 2022-04-09 | 2022-04-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213843 | T2 EI PT 1-HAT CRK 2-BURN 3/30 RPR HRDW | ICW
LC | 120773491 | 009/046 | T2 EI TULUCAY-VACA-VACA+ 9/046 RPR OPGW | SACTO | ETL.5800.INSL | 2021-04-09 | 2021-04-09 |  | 2022-04-09 | 2022-04-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW PATR COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 44777051 | T2 EI TULUCAY-VACA_009/046 RPR OPGW | ICS
LC | 120786765 | 044/373 | T2 EI RND MT-CTONWD #3 44/373 INST BOLT | TABLEMTN | ETL.5650.TOWR | 2021-04-10 | 2021-04-10 |  | 2022-04-10 | 2022-04-10 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE | Missing | Hardware-Tower | Install | 45110543 | T2 EI RND MT-CTONWD #3 44/373 INST BOLT | ICQ
LC | 120788074 | C013/053 | T2 EI MSS LNDNG-CBRN C013/053 ROW ENCR | MOSSLNDG | ETL.5330.TOWR | 2021-04-10 | 2021-04-10 |  | 2022-04-10 | 2022-04-10 | Late | 931 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB NTDE | Encroachment | Right of Way | Remove | 44811294 | T2 EI MSS LNDNG-CBRN C013/053 ROW ENCR | CHR
LC | 120802275 | 000/001 | T2 KERCKHOFF #1-KERCKHFF #2 0/1 INS HRDT | FRESNO | ETL.1880.TOWR | 2021-04-12 | 2021-04-12 |  | 2022-04-12 | 2022-04-12 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW CREW OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45109311 | T2 KERCKHOFF #1-KERCKHFF #2 0/1 INS HRDT | ICQ
LC | 120804239 | 015/343 | T2 DRM-GRS VLY-WMR 15/343 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2021-04-13 | 2021-04-13 |  | 2022-04-13 | 2022-04-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31609442 | T2 DRM-GRS VLY-WMR 15/343 RPL POLE | 70Y
LC | 120805080 | 041/347 | T2 EI PIT #1-CTTNWD 041/347 RPL SPLS | TABLEMTN | ETL.5390.INSL.NCER | 2021-04-13 | 2021-04-13 |  | 2022-04-13 | 2022-04-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Steel | Replace | 45182629 | T2 EI PIT #1-CTTNWD 041/347 RPL SPLS | ICS
LC | 120808727 | 012/050A | T2 EI MR BY-SLR SW STA #112/50A RPL INSS | PISMOBCH | ETL.5300.INSL | 2021-04-13 | 2021-04-13 |  | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528621 | EI MORRO BAY-SOLAR SS #1 RPLC INNS 18TW | 93K
LC | 120808821 | 012/050B | T2 EI MRR BY-SLR SW #2 12/50B RPL INSS | PISMOBCH | ETL.5310.TOWR | 2021-04-13 | 2021-04-13 |  | 2022-04-13 | 2022-04-13 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528622 | EI MORRO BAY-SOLAR SS#2 RPL INS 8WR | 93K
LC | 120833196 | 002/022 | T2 EI SBRNT-GRZLY-CLMNT #2 2/22 RPL INSS | CONCORD | ETL.3750.INSL | 2021-04-17 | 2021-04-17 |  | 2022-04-17 | 2022-04-17 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31541090 | DI SBRNT-GRZLY-CLRMT #2 RPL EMRS IN 2 TW | 92S
LC | 120842138 | 001/009 | T2 DI SILVERADO-FULTON JCT 1/9 COMPLETE | LAKEVLLE | ETL.1610.INSL.CERA | 2021-04-19 | 2021-04-12 |  | 2022-04-12 | 2022-04-12 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31542618 | EI SILVERADO-FULTON JCT RPL INSS 6TWRS | 93K
LC | 120860042 | 009/071 | T2 DI ELDORADO-MSR FLT #1 9/71 RPL HRDD | SACTO | ETL.1530.POLE.WOOD | 2021-04-21 | 2021-04-13 |  | 2022-04-13 | 2022-04-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44776415 | T2 DI ELDORADO-MSR FLT #1 9/71 RPL HRDD | ICW
LC | 120872605 | 020/286 | T2 DI SISQUOC-SANTA YNEZ 20/286 RPL STRW | PISMOBCH | ETL.3700.POLE.WOOD | 2021-04-23 | 2021-04-20 |  | 2022-04-20 | 2022-04-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31596782 | T2 DI SISQUOC-SANTA YNEZ 20/286 RPL STRW | 70Y
LC | 120873432 | C009/039 | T2 EI MOSS LANDING-COBURN C9/39 RPL INSS | MOSSLNDG | ETL.5330.INSL | 2021-04-23 | 2021-04-23 |  | 2022-04-23 | 2022-04-23 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31536364 | DI MOSS LANDING-COBURN RPL INSS 15TWR | 93K
LC | 120874048 | 004/028 | T2 DI EL DRD-MSSR FLT #1 4/28 RPL HRDT | SACTO | ETL.1530.TOWR | 2021-04-23 | 2021-04-21 |  | 2022-04-21 | 2022-04-21 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 44764485 | T2 DI EL DRD-MSSR FLT #1 4/28 RPL HRDT | ICQ
LC | 120879352 | 086/001A | T2 EI HUMBOLDT-BRIDGEVILLE 86/1A REGRADE | EUREKA | ETL.1810.POLE.NWOD | 2021-04-24 | 2021-04-23 |  | 2022-04-23 | 2022-04-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45079948 | T2 EI HMBLDT-BRIDGEVILLE 86/1A REGRADE | ICW
LC | 120885542 | 036/148 | T2 EI DIABLO-MIDWAY #2 036/148 COMPLETED | PISMOBCH | ETL.5970.TOWR | 2021-04-26 | 2021-04-26 |  | 2022-04-26 | 2022-04-26 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068542 | T2 EI DIABLO-MIDWAY #2 036/148 RPR GYWS | ICS
LC | 120886809 | 004/003 | T2 EI MNDCN-WILITS-FORT BRAGG 4/3 RPL PL | WILLITS | ETL.7550.POLE.WOOD | 2021-04-26 | 2021-04-26 |  | 2022-04-26 | 2022-04-26 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31540801 | T2 DI MENDO-WILL-FT BRAGG 1/6 RPL POLE | 70Y
LC | 120890686 | 021/176 | T2 EI PIT #1-CTTNWD 021/176 RPR CNDS | TABLEMTN | ETL.5390.TOWR | 2021-04-27 | 2021-04-27 |  | 2022-04-27 | 2022-04-27 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45182635 | T2 EI PIT #1-CTTNWD 021/176 RPR CNDS | ICS
LC | 120892360 | 030/005 | T2 FLTN-HPLND 30/5 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-04-27 | 2021-04-27 |  | 2022-04-27 | 2022-04-27 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540574 | EI FULTON-HOPLAND :026/4 RPL STRW | 70Y
LC | 120893444 | 006/040 | T2 DI STN MEL SW STA-RVRBK 6/40 RPL INSS | VICTOR | ETL.3840.INSL.NCER | 2021-04-28 | 2021-04-27 |  | 2022-04-27 | 2022-04-27 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31551877 | T2 DI STN MEL SW STA-RVRBK RPL INSS 3TW | 93K
LC | 120894654 | 017/142 | T2 EI PIT #1-COTTONWOOD 17/142 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-04-28 | 2021-04-28 |  | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45149407 | T2 EI PIT #1-COTTONWOOD 17/142 RPR STRT | ICQ
LC | 120895443 | 022/178 | T2 EI PIT #1-COTNWD 022/178 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-04-28 | 2021-04-28 |  | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45527073 | T2 EI PIT #1-COTNWD 022/178 RPR STRT | ICQ
LC | 120895878 | 026/171 | T2 DI POE-RIO OSO 26/171 RPL HRDT | TABLEMTN | ETL.5540.TOWR | 2021-04-28 | 2021-04-14 |  | 2022-04-14 | 2022-04-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45198335 | T2 DI POE-RIO OSO 26/171 RPL HRDT | ICQ
LC | 120896090 | 004/030 | T2 EI MORAGA-OAKLAND #2 4/30 RPL INSLS | CONCORD | ETL.2730.INSL | 2021-04-28 | 2021-04-28 |  | 2022-04-28 | 2022-04-28 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31595363 | EI MORAGA-OAKLAND #2 4/30 RPL INSS | 93K
LC | 120898260 | 044/181 | T2 EI DIABLO-MIDWAY #3 44/181 RPR STRT | PISMOBCH | ETL.5980.TOWR | 2021-04-28 | 2021-04-28 |  | 2022-04-28 | 2022-04-28 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45073735 | T2 EI DIABLO-MIDWAY #3 44/181 RPR STRT | ICQ
LC | 120904186 | 038/000 | T2 EI FLTN-HOPLAND 38/0 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-04-29 | 2021-04-29 |  | 2022-04-29 | 2022-04-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31631442 | T2 EI FLTN-HOPLAND 38/0 RPL POLE | 70Y
LC | 120913003 | 005/011 | EI T2 CHWCHLLA-KRCKHFF 5/11 RPL INSW | FRESNO | ETL.1250.INSL.NCER | 2021-05-01 | 2021-05-01 |  | 2022-05-01 | 2022-05-01 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31591317 | EI T2 CHWCHLLA-KRCKHFF 5/11 RPL INSW | 93I
LC | 120914241 | 017/003 | T2 EI FULTON-HOPLAND 17/3 RPR GYWW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-01 | 2021-05-01 |  | 2022-05-01 | 2022-05-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45143933 | T2 EI FULTON-HOPLAND 17/3 RPR GYWW | ICW
LC | 120914607 | 021/002 | T2 EI MNDCN-WLTS-FRT BRG 21/2 RPL INSW | WILLITS | ETL.7550.INSL.NCER | 2021-05-01 | 2021-05-01 |  | 2022-05-01 | 2022-05-01 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542846 | T2 EI MNDCN-WLTS-FRT BRG 21/2 RPL INSW | 93I
LC | 120920727 | 009/007 | T2 EI FLTN-HPLND 9/7 RPR GWRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-03 | 2021-05-03 |  | 2022-05-03 | 2022-05-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45143569 | T2 EI FLTN-HPLND 9/7 RPR GWRW | ICW
LC | 120921741 | 017/006 | T2 EI FULTON-HOPLAND 17/6 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-03 | 2021-05-03 |  | 2022-05-03 | 2022-05-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143934 | T2 EI FULTON-HOPLAND 17/6 RPR STRW | ICW
LC | 120933005 | 062/002 | T2NT EI HUMBOLDT-TRINITY 062/2 INST MRKW | EUREKA | ETL.1820.POLE.STPS | 2021-05-04 | 2021-05-04 |  | 2022-05-04 | 2022-05-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2N PRTO NTDE | No Good/Out of Stdrd | Marker (i.e. signs)-Wood | Install | 45166571 | T2NT EI HUMBOLDT-TRINITY 062/2 INST MRKW | ICW
LC | 120935035 | 019/005 | T2 EI FULTON-HOPLAND 019/005 RPL ANCW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-05 | 2021-05-05 |  | 2022-05-05 | 2022-05-05 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31541674 | T2 EI FULTON-HOPLAND 019/005 RPL ANCW | 93E
LC | 120936135 | 012/005 | T2 EI FULTON-HOPLAND 012/005 RPR GYWW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-05 | 2021-05-05 |  | 2022-05-05 | 2022-05-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45143577 | T2 EI FULTON-HOPLAND 012/005 RPR GYWW | ICW
LC | 120938568 | 024/000 | T2 EI MNDCNO-WLLTS-FRT BRG 24/0 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-05 | 2021-05-04 |  | 2022-05-04 | 2022-05-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31543104 | T2 DI MNDCN-WLTS-FRT BRG 25/0 RPL STRW | 70Y
LC | 120938705 | 032/004 | T2 EI FULTON-HOPLAND 32/4 RPL POLE | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-05-05 | 2021-05-05 |  | 2022-05-05 | 2022-05-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541677 | T2 EI FULTON-HOPLAND 019/006 RPL POLE | 70Y
LC | 120942120 | 015/357 | T2 DI DRM-GRSS VLLY-WMAR 15/357 RPR SPLW | SACTO | ETL.6760.INSL.CERA | 2021-05-06 | 2021-05-05 |  | 2022-05-05 | 2022-05-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 44812229 | T2 DI DRM-GRSS VLLY-WMAR 15/357 RPR SPLW | ICW
LC | 120942242 | 018/001 | T2 EI HMBLDT BY-RIO DL JCT 18/1 RPL INSW | EUREKA | ETL.7100.POLE.WOOD | 2021-05-06 | 2021-05-06 |  | 2022-05-06 | 2022-05-06 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542056 | T2 DI HMBLDT BY-RIO DL JCT 18/1 RPL INSW | 93I
LC | 120945659 | 067/005 | T2 EI HUMBOLDT-TRINITY 67/5C RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-06 | 2021-05-06 |  | 2022-05-06 | 2022-05-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145444 | T2 EI HUMBOLDT-TRINITY 67/5C RPR GYWW | ICW
LC | 120945680 | 067/005 | T2 EI HUMBOLDT-TRINITY 67/5R RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-06 | 2021-05-06 |  | 2022-05-06 | 2022-05-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145444 | T2 EI HUMBOLDT-TRINITY 67/5C RPR GYWW | ICW
LC | 120945681 | 067/005 | T2 EI HUMBOLDT-TRINITY 67/5L RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-06 | 2021-05-06 |  | 2022-05-06 | 2022-05-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145444 | T2 EI HUMBOLDT-TRINITY 67/5C RPR GYWW | ICW
LC | 120948601 | 024/004 | T2 EI FULTON-HOPLAND 24/4 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-07 | 2021-05-07 |  | 2022-05-07 | 2022-05-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31541677 | T2 EI FULTON-HOPLAND 019/006 RPL POLE | 70Y
LC | 120949003 | 024/000 | T2 EI FULTON-HOPLAND 24/0 RPR GYWW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-07 | 2021-05-07 |  | 2022-05-07 | 2022-05-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45143944 | T2 EI FULTON-HOPLAND 24/0 RPR GYWW | ICW
LC | 120951636 | 028/015 | T2 EI FULTON-HOPLAND 28/15 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-07 | 2021-05-07 |  | 2022-05-07 | 2022-05-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541677 | T2 EI FULTON-HOPLAND 019/006 RPL POLE | 70Y
LC | 120952993 | 009/179 | T2 EI MNTA VISTA-LOS GATS 9/179 RPL STRW | METCALF | ETL.7610.POLE.WOOD | 2021-05-08 | 2021-05-08 |  | 2022-05-08 | 2022-05-08 | Late | 401 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAR SR22 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31616003 | DI MONTA VISTA-LOS GATOS 1/36 REFRAME | 93G
LC | 120953590 | 051/003 | T2 EI HUMBOLDT-TRINITY 51/3 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-08 | 2021-05-08 |  | 2022-05-08 | 2022-05-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31506039 | DI HUMBOLDT-TRINITY REPL POLES(ENG) | 70Y
LC | 120953591 | 051/003 | T2 EI HUMBOLDT-TRINITY 51/3 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-08 | 2021-05-08 |  | 2022-05-08 | 2022-05-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31506039 | DI HUMBOLDT-TRINITY REPL POLES(ENG) | 70Y
LC | 120995327 | 009/186 | T2 EI MNTA VSTA-LS GTS 9/186 RPL STRW | METCALF | ETL.7610.POLE.WOOD | 2021-05-10 | 2021-05-08 |  | 2022-05-08 | 2022-05-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAR SR22 | Rotten | Structure-Wood | Replace | 31543124 | EI MONTA VISTA-LOS GATOS 5/101 RPL STRW | 70Y
LC | 121002069 | 009/174 | T2 EI MNTA VISTA-LOS GATOS 9/174 RMV VEG | METCALF | ETL.7610.POLE.WOOD | 2021-05-10 | 2021-05-10 |  | 2022-05-10 | 2022-05-10 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAR SR22 | Overgrown | Vegetation | Trim
LC | 121037957 | 013/125 | T2 ARCO-CHOLAME 013/125 REFRAME | MIDWAY | ETL.8440.POLE.WOOD | 2021-05-10 | 2021-05-10 |  | 2022-05-10 | 2022-05-10 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31543280 | T2 ARCO-CHOLAME 013/125 REFRAME | 93E
LC | 121041761 | 008/163 | T2 EI MNTA VSTA-LS GTOS 8/163 RPL STRW | METCALF | ETL.7610.POLE.WOOD | 2021-05-10 | 2021-05-10 |  | 2022-05-10 | 2022-05-10 | Late | 401 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAB SR22 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31616003 | DI MONTA VISTA-LOS GATOS 1/36 REFRAME | 93G
LC | 121062410 | 043/370 | T2 EI PIT #1-COTTONWOOD 043/370 RPL GYWS | TABLEMTN | ETL.5390.TOWR | 2021-05-10 | 2021-05-10 |  | 2022-05-10 | 2022-05-10 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Replace | 45166846 | T2 EI PIT #1-COTTONWOOD 043/370 RPL GYWS | ICS
LC | 121186766 | 037/008 | T2 EI MNDCN-WLLTS-FRT BRGG 37/8 INS MRKS | WILLITS | ETL.7550.POLE.NWOD | 2021-05-11 | 2021-05-11 |  | 2022-05-11 | 2022-05-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAB REJC NTDE | No Good/Out of Stdrd | Marker (i.e. signs)-Steel | Install
LC | 121187108 | 008/162 | T2 EI MONTA VISTA-LS GTS 8/162 RPR GYWW | METCALF | ETL.7610.POLE.WOOD | 2021-05-11 | 2021-05-11 |  | 2022-05-11 | 2022-05-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45183638 | T2 EI MONTA VISTA-LS GTS 8/162 RPR GYWW | ICW
LC | 121187593 | 008/159 | T2 EI MNTA VSTA-LS GTOS 8/159 RPR HRDW | METCALF | ETL.7610.POLE.WOOD | 2021-05-11 | 2021-05-11 |  | 2022-05-11 | 2022-05-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAR SR22 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45600603 | T2 EI MNTA VSTA-LS GTOS 8/159 RPR HRDW | ICW
LC | 121188979 | 036/000 | T2 EI MNDCN-WLLTS-FRT BRGG 36/0 RPL INSW | WILLITS | ETL.7550.POLE.WOOD | 2021-05-11 | 2021-05-11 |  | 2022-05-11 | 2022-05-11 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31600242 | T2 EI MNDCN-WLLTS-FRT BRGG 35/9 RPL INSW | 93I
LC | 121191361 | 020/125 | T2 DI STNSLS-MLNS MNTC 20/125 RPL INSS | VICTOR | ETL.3830.INSL | 2021-05-11 | 2021-04-12 |  | 2022-04-12 | 2022-04-12 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528967 | NN STANISLAUS-MLNS-MNTC RPLC INSS 11TWR | 93K
LC | 121320137 | 057/001 | T2 EI HUMBOLDT-TRINITY 57/1C REFRAME | EUREKA | ETL.1820.POLE.WDPS | 2021-05-12 | 2021-05-12 |  | 2022-05-12 | 2022-05-12 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31625199 | T2 EI HUMBOLDT-TRINITY 57/1C REFRAME | 93E
LC | 121322340 | 056/004 | T2 EI HUMBOLDT-TRINITY 56/4R RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-12 | 2021-05-12 |  | 2022-05-12 | 2022-05-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145096 | T2 EI HUMBOLDT-TRINITY 056/004R RPR GYWW | ICW
LC | 121322342 | 056/004 | T2 EI HUMBOLDT-TRINITY 56/4 RPL ANCHOR | EUREKA | ETL.1820.POLE.WDPS | 2021-05-12 | 2021-05-12 |  | 2022-05-12 | 2022-05-12 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31549297 | T2 EI HUMBOLDT-TRINITY 056/4 RPL ANCHOR | 93E
LC | 121322343 | 056/004 | T2 EI HUMBOLDT-TRINITY 56/4C RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-12 | 2021-05-12 |  | 2022-05-12 | 2022-05-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45145096 | T2 EI HUMBOLDT-TRINITY 056/004R RPR GYWW | ICW
LC | 121322756 | 008/068 | WV T2 EL DRDO-MSSRI FLT #1 8/68 INS DAMW | SACTO | ETL.1530.POLE.NWOD | 2021-05-12 | 2021-05-12 |  | 2022-05-12 | 2022-05-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO FRAB NTDE | Missing | Damper-Wood | Install | 44812180 | WV T2 EL DRDO-MSSRI FLT #1 8/68 INS DAMW | ICW
LC | 121328521 | 012/210 | T2 DI TEJON-LEBEC 12/210 RPLC STRW | MIDWAY | ETL.9250.POLE.WOOD | 2021-05-13 | 2021-04-22 |  | 2022-04-22 | 2022-04-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE ACCM OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543041 | T2 DI TEJON-LEBEC 12/210 RPLC STRW | 70Y
LC | 121328873 | 010/180 | T2 DI TEJON-LEBEC 10/180 RPLC STRW | MIDWAY | ETL.9250.POLE.WOOD | 2021-05-13 | 2021-04-22 |  | 2022-04-22 | 2022-04-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31537284 | T2 EI TEJON-LEBEC 10/180 RPLC STRW | 70Y
LC | 121329380 | 011/188 | T2 DI 70085 TEJON-LEBEC-11/088 RPR STRW | MIDWAY | ETL.9250.POLE.WOOD | 2021-05-13 | 2021-04-22 |  | 2022-04-22 | 2022-04-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45068008 | T2 DI 70085 TEJON-LEBEC-11/088 RPR STRW | ICW
LC | 121335002 | 002/028 | T2 WV LAKEVILLE-SONOMA #2 2/28 RPL INSS | LAKEVLLE | ETL.2070.INSL.NCER | 2021-05-14 | 2021-05-14 |  | 2022-05-14 | 2022-05-14 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW CREW OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31599961 | T2 WV LAKEVILLE-SONOMA #2 2/28 RPL INSS | 93K
LC | 121336056 | 089/008 | T2 EI HUMBOLDT-TRINITY 89/8L RPR HRDW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-14 | 2021-05-14 |  | 2022-05-14 | 2022-05-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45160706 | T2 EI HUMBOLDT-TRINITY 89/8L RPR HRDW | ICW
LC | 121336717 | 009/010 | T2 DI FULTON-HOPLAND 9/10 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-14 | 2021-04-24 |  | 2022-04-24 | 2022-04-24 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31614889 | T2 DI FULTON-HOPLAND 9/10 RPL STRW | 70Y
LC | 121336880 | 089/009 | T2 EI HUMBOLDT-TRINITY 89/9 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-05-14 | 2021-05-14 |  | 2022-05-14 | 2022-05-14 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542140 | T2 EI HUMBOLDT-TRINITY 89/9 RPL INSW | 93I
LC | 121338285 | 010/177 | T2 DI TEJON-LEBEC 10/177 RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-05-15 | 2021-04-22 |  | 2022-04-22 | 2022-04-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45068009 | T2 DI TEJON-LEBEC 10/177 RPR GYWW | ICW
LC | 121340572 | 089/007A | T2 EI HUMBOLDT-TRINITY 89/7A RPR WDPKR | EUREKA | ETL.1820.POLE.WOOD | 2021-05-15 | 2021-05-15 |  | 2022-05-15 | 2022-05-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45160705 | T2 DI HUMBOLDT-TRINITY 89/7C RPR STRW | ICW
LC | 121345212 | :001/010 | T2 EI FULTON-PUEBLO :1/10 RPL STRW | LAKEVLLE | ETL.1600.POLE.WOOD | 2021-05-17 | 2021-05-17 |  | 2022-05-17 | 2022-05-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31590689 | T2 EI FULTON-PUEBLO :1/10 RPL STRW | 70Y
LC | 121348901 | 013/200 | T2 DI SISQUC-SNT YNEZ SW 13/200 RPL POLE | PISMOBCH | ETL.3700.INSL.CERA | 2021-05-17 | 2021-04-27 |  | 2022-04-27 | 2022-04-27 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31613106 | T2 DI SISQUC-SNT YNEZ SW 13/200 RPL POLE | 70Y
LC | 121350610 | 008/141 | T2 DI TEJON-LEBEC 8/141 RPLC HRDW | MIDWAY | ETL.9250.POLE.WOOD | 2021-05-18 | 2021-04-22 |  | 2022-04-22 | 2022-04-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 44874347 | T2 DI TEJON-LEBEC 8/141 RPLC HRDW | ICW
LC | 121352435 | A011/250 | T2 DI SALINAS-LAURELES A11/250 INS HRDW | MOSSLNDG | ETL.7930.POLE.NWOD | 2021-05-18 | 2021-05-17 |  | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45213173 | T2 DI SALINAS-LAURELES A11/250 INS HRDW | ICW
LC | 121353552 | 006/043 | T2 EI BUTTE VALLEY-CARIBOU 6/43 RPR GYWS | TABLEMTN | ETL.1180.TOWR | 2021-05-18 | 2021-05-18 |  | 2022-05-18 | 2022-05-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45212383 | T2 EI BUTTE VALLEY-CARIBOU 6/43 RPR GYWS | ICS
LC | 121357635 | 007/151 | T2 EI VALLEY SPRINGS #1 7/151 RPLC STRW | VICTOR | ETL.8210.POLE.WOOD | 2021-05-19 | 2021-05-19 |  | 2022-05-19 | 2022-05-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543037 | DI VALLEY SPRINGS #1 2/45 RPLC STRW | 70Y
LC | 121361140 | 016/101 | T2 WV NEWARK-LIVERMORE 16/101 RPR FENCE | CONCORD | ETL.7660.POLE.NWOD | 2021-05-19 | 2021-05-19 |  | 2022-05-19 | 2022-05-19 | Late | 931 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW OTHR OH FMOB TR2 PRTO FRAB NTDE | Encroachment | Right of Way | Remove
LC | 121361257 | 004/018 | T2 DI MORRO BAY-DIABLE 4/18 RPR INSS | PISMOBCH | ETL.5260.INSL.CERA | 2021-05-19 | 2021-04-29 |  | 2022-04-29 | 2022-04-29 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45098819 | T2 DI MORRO BAY-MESA 4/18 RPR INSS | ICS
LC | 121362623 | 008/149 | T2 DI COLGATE-PALERMO 8/149 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2021-05-19 | 2021-05-10 |  | 2022-05-10 | 2022-05-10 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617003 | T2 DI COLGATE-PALERMO 8/149 RPL POLE | 70Y
LC | 121363854 | 005/047 | T2NT DI SLT SPRNGS-TGR CRK 5/47 RPR STRT | VICTOR | ETL.3500.TOWR | 2021-05-19 | 2021-04-20 |  | 2022-04-20 | 2022-04-20 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45150490 | T2NT DI SLT SPRNGS-TGR CRK 5/47 RPR STRT | ICQ
LC | 121365123 | 090/009 | T2 EI HUMBOLDT-TRINITY 90/9 RPL INSW | EUREKA | ETL.1820.INSL.NCER | 2021-05-20 | 2021-05-19 |  | 2022-05-19 | 2022-05-19 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542148 | T2 EI CTTONWOOD-HUMBOLDT 90/009 RPL INSW | 93I
LC | 121368665 | 089/004 | T2 EI HUMBOLDT-TRINITY 89/4 RPR CRSW | EUREKA | ETL.1820.POLE.WDPS | 2021-05-20 | 2021-05-15 |  | 2022-05-15 | 2022-05-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45160704 | T2 EI HUMBOLDT-TRINITY 89/004 RPR CRSW | ICW
LC | 121372147 | 012/060 | T2 DI FULTON-PUEBLO SW 12/60 RPL SWITCH | LAKEVLLE | ETL.1600.SWIT | 2021-05-21 | 2021-05-17 |  | 2022-05-17 | 2022-05-17 | Late | 435 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Switch-Steel | Replace | 74019484 | CENTRAL BUNDLE C-28 | 94A
LC | 121374310 | 036/154 | T2 DI TEMPLETON-GATES 036/154 RPR FOND | PISMOBCH | ETL.5934.TOWR | 2021-05-21 | 2021-05-04 |  | 2022-05-04 | 2022-05-04 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45077928 | T2 DI TEMPLETON-GATES 036/154 RPR FOND | ICQ
LC | 121376404 | :007/000 | T2 DI BLTA-RVK-MLNS SS :007/000 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-05-21 | 2021-05-05 |  | 2022-05-05 | 2022-05-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536314 | T2 DI BLT-RVRBNK-MLNS RPL STRW | 70Y
LC | 121376796 | 011/065 | T2 DI TESLA-RVNSWD 011/065 RPL INSS | CONCORD | ETL.5730.INSL | 2021-05-21 | 2021-05-04 |  | 2022-05-04 | 2022-05-04 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549337 | T2 DI TESLA-RVNSWD RPL INSS 5TWRS | 93K
LC | 121381526 | 029/005 | T2 DI CLAY-MARTEL 29/5 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-10 |  | 2022-05-10 | 2022-05-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45135063 | T2 DI CLAY-MARTEL 29/5 RPR STRW | ICW
LC | 121381950 | 023/329 | T2 DI CLAY-MARTEL 023/329 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-11 |  | 2022-05-11 | 2022-05-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540452 | DI CLAY-MARTEL 26/371 RPLC STRW | 70Y
LC | 121382044 | 021/296 | T2 DI CLAY-MARTEL 021/296 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-22 | 2021-05-08 |  | 2022-05-08 | 2022-05-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540452 | DI CLAY-MARTEL 26/371 RPLC STRW | 70Y
LC | 121382844 | 028/427 | T2NT DI CLAY-MARTEL 28/427 RMV BUTT | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 |  | 2022-05-11 | 2022-05-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45513994 | T2NT DI CLAY-MARTEL 28/427 RMV BUTT | ICW
LC | 121382869 | 024/344 | T2 DI CLAY-MARTEL 024/344 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 |  | 2022-05-11 | 2022-05-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540452 | DI CLAY-MARTEL 26/371 RPLC STRW | 70Y
LC | 121383511 | 041/194 | T2 DI LKVILLE-SBRNTE #2 41/194 RPL INSS | CONCORD | ETL.4960.INSL.CERA | 2021-05-23 | 2021-05-06 |  | 2022-05-06 | 2022-05-06 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31542274 | T2 DI LKVILLE-SBRNTE #2 RPL INSS 3 TWRS | 93K
LC | 121383548 | 015/361 | T2 DI DRUM-GRS VLY-WEIMR 15/361 RPL INSW | SACTO | ETL.6760.INSL.CERA | 2021-05-23 | 2021-05-05 |  | 2022-05-05 | 2022-05-05 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541885 | T2 DI DRUM-GRS VLY-WEIMR 15/361 RPL INSW | 93I
LC | 121383855 | 021/004 | T2 DI FULTON-HOPLAND 21/04 RPL ANCW | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-05-23 | 2021-05-13 |  | 2022-05-13 | 2022-05-13 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31541674 | T2 EI FULTON-HOPLAND 019/005 RPL ANCW | 93E
LC | 121384107 | 024/345 | T2 DI CLAY-MARTEL 24/345 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-05-23 | 2021-05-11 |  | 2022-05-11 | 2022-05-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540452 | DI CLAY-MARTEL 26/371 RPLC STRW | 70Y
LC | 121384128 | 008/214 | T2 DI COTTONWD- BENTN #1 8/214 RPL POLE | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-23 | 2021-05-21 |  | 2022-05-21 | 2022-05-21 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31545485 | DI COTTONWOOD-BENTN#1 006/152 RPL STRW | 70Y
LC | 121384285 | 045/005 | T2 DI FT RSS GLA GLA 045/005 RPR SPLW | LAKEVLLE | ETL.6980.INSL.NCER | 2021-05-23 | 2021-05-21 |  | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCM OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45144208 | T2 DI FT RSS GLA GLA 045/005 RPR SPLW | ICW
LC | 121391748 | 012/274 | T2 DI DRM-GRSS VLLY X12/274 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-05-24 | 2021-05-17 |  | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45075010 | T2 DI DRM-GRSS VLLY X12/274 RPR GYWW | ICW
LC | 121391856 | 014/316 | T2 DI DRM-GRS VLY-WMR 014/316 RPR INSW | SACTO | ETL.6760.INSL.CERA | 2021-05-24 | 2021-05-17 |  | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCM OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45075015 | T2 DI DRM-GRS VLY-WMR 014/316 RPR INSW | ICW
LC | 121392163 | 013/295 | T2 DI DRUM-GRSS VLLY-WMR 13/295 RPL INSW | SACTO | ETL.6760.INSL.NCER | 2021-05-24 | 2021-05-17 |  | 2022-05-17 | 2022-05-17 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE ACCM OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31540566 | T2 DI DRUM-GRS VLY-WMR 16/369 RPLC INSWC | 93I
LC | 121392300 | 029/013 | T2 DI FULTON-HOPLAND 29/13 RPL HDRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-05-24 | 2021-05-17 |  | 2022-05-17 | 2022-05-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCM OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45143959 | T2 DI FULTON-HOPLAND 29/13 RPL HDRW | ICW
LC | 121395248 | 015/350 | T2NT DI DRM-GRS VLY-WMR 15/350 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2021-05-25 | 2021-05-17 |  | 2022-05-17 | 2022-05-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31598429 | T2NT DI DRM-GRS VLY-WMR 15/350 RPL POLE | 70Y
LC | 121395581 | 019/224 | T2 EI DRUM-SUMMIT #2 19/224L RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2021-05-25 | 2021-05-25 |  | 2022-05-25 | 2022-05-25 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31618280 | T2 EI DRUM-SUMMIT #2 19/226 RPL PL | 70Y
LC | 121395904 | B016/367 | T2 DI DRM-GRS VLY-WMR B16/367 RPLC INSW | SACTO | ETL.6760.INSL.NCER | 2021-05-25 | 2021-05-17 |  | 2022-05-17 | 2022-05-17 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541885 | T2 DI DRUM-GRS VLY-WEIMR 15/361 RPL INSW | 93I
LC | 121395983 | 015/351 | T2 DI DRM-GRS VLY-WMR 15/351 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-05-25 | 2021-05-17 |  | 2022-05-17 | 2022-05-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31541884 | T2 DI DRM-GRS VLY-WMR 15/351 RPL STRW | 70Y
LC | 121397153 | 014/337 | T2 DI DRUM-GRSS VLLY-WMR 14/337 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-05-25 | 2021-05-17 |  | 2022-05-17 | 2022-05-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31592020 | T2 DI DRM-GRS VLY-WMR 19/446 RPL STRW | 70Y
LC | 121400171 | 044/007 | T2 DI FORT ROSS-GUALALA 44/7 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-05-26 | 2021-05-17 |  | 2022-05-17 | 2022-05-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31542050 | T2 DI FORT ROSS-GUALALA 44/7 REFRAME | 93E
LC | 121402043 | 024/116 | T2 EI FULTON-PUEBLO 24/116 RMV FENCE | LAKEVLLE | ETL.1600.TOWR | 2021-05-26 | 2021-05-26 |  | 2022-05-26 | 2022-05-26 | Late | 931 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO FRAB NTDE | Encroachment | Right of Way | Remove
LC | 121404665 | 007/177 | T2 DI CTTNWD-BNTN #1 7/177 RPL INSW | TABLEMTN | ETL.6640.INSL.NCER | 2021-05-26 | 2021-05-21 |  | 2022-05-21 | 2022-05-21 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31541809 | DI COTTONWOOD-BENTON #1 13/331 RPL INSW | 93I
LC | 121405002 | 051/209 | T2 DI DIABLO-GATES #1 51/209 RPR HRDD | PISMOBCH | ETL.5960.TOWR | 2021-05-26 | 2021-05-21 |  | 2022-05-21 | 2022-05-21 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45070722 | T2 DI DIABLO-GATES #1 51/209 RPL HRDT | ICQ
LC | 121405126 | 003/074 | T2 DI COLEMAN-COTTONWOOD 3/74 RPR STRW | TABLEMTN | ETL.6430.POLE.WOOD | 2021-05-26 | 2021-05-22 |  | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45212629 | T2 DI COLEMAN-COTTONWOOD 3/74 RPR STRW | ICW
LC | 121405159 | :006/008 | T2 DI BELLOTA-RVRBNK :006/008 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-05-26 | 2021-05-21 |  | 2022-05-21 | 2022-05-21 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE ACCH OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536314 | T2 DI BLT-RVRBNK-MLNS RPL STRW | 70Y
LC | 121405258 | 003/065 | T2 DI CORDELIA #1 TAP 003/065 RPR CNDW | SACTO | ETL.8182.INSL | 2021-05-26 | 2021-05-21 |  | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45567097 | T2 DI CORDELIA #1 TAP 003/065 RPR CNDW | ICW
LC | 121405532 | 002/058 | T2 DI COTTNWD-BENTON #1 002/058 RPR STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-26 | 2021-05-22 |  | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45213475 | T2 DI COTTNWD-BENTON #1 002/058 RPR STRW | ICW
LC | 121405539 | 045/001 | T2 DI FORT ROSS-GUALALA 45/1 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-05-26 | 2021-05-21 |  | 2022-05-21 | 2022-05-21 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31542051 | T2 DI FORT ROSS-GUALALA 45/1 RPL STRW | 70Y
LC | 121405586 | 002/062 | T2 DI CTTNWD-BENTN #1 002/062 RPL STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-26 | 2021-05-22 |  | 2022-05-22 | 2022-05-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31541808 | T2 DI CTTNWD-BENTN #1 002/062 RPL STRW | 70Y
LC | 121405601 | :000/010 | T2 DI BLOTA-RVRBNK-MLNS :0/10 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-05-26 | 2021-05-21 |  | 2022-05-21 | 2022-05-21 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31536314 | T2 DI BLT-RVRBNK-MLNS RPL STRW | 70Y
LC | 121405615 | 000/006 | T2 DI COLEMN-CTTNWD 0/6 RPL STRW | TABLEMTN | ETL.6430.POLE.WOOD | 2021-05-26 | 2021-05-21 |  | 2022-05-21 | 2022-05-21 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543020 | T2 DI COLEMN-CTTNWD 0/6 RPL STRW | 70Y
LC | 121409218 | 003/067 | T2 DI CTTNWD-BENTN #1 3/67 RPL STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-27 | 2021-05-21 |  | 2022-05-21 | 2022-05-21 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR FRAR | No Good/Out of Stdrd | Structure-Wood | Replace | 31541808 | T2 DI CTTNWD-BENTN #1 002/062 RPL STRW | 70Y
LC | 121418162 | :009/006 | T2 DI BLTA RVBK MLNS SS :9/6 RPL POLE | VICTOR | ETL.1070.POLE.WOOD | 2021-05-27 | 2021-05-20 |  | 2022-05-20 | 2022-05-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31602715 | T2 DI BLTA RVBK MLNS SS :9/6 RPL STRW | 70Y
LC | 121418178 | 003/071 | T2NT DI COLEMAN-COTTONWOOD 3/71 RMV BUTT | TABLEMTN | ETL.6430.POLE.WOOD | 2021-05-27 | 2021-05-22 |  | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45456340 | T2NT DI COLEMAN-COTTONWOOD 3/71 RMV BUTT | ICW
LC | 121418287 | 007/186 | T2 DI COTTNWOOD-BENTN #1 7/186 RPR STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-27 | 2021-05-22 |  | 2022-05-22 | 2022-05-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAR | No Good/Out of Stdrd | Structure-Wood | Repair | 45213488 | T2 DI COTTNWOOD-BENTN #1 7/186 RPR STRW | ICW
LC | 121420385 | 001/045 | T2 DI COTTONWOOD-BENTON #1 1/45 RPR STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-05-28 | 2021-05-21 |  | 2022-05-21 | 2022-05-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45213494 | T2 DI COTTONWOOD-BENTON #1 1/45 RPR STRW | ICW
LC | 121421155 | 008/149 | T2 DI PT#1-HT CRK#2-BRY 8/149 REFRAME | TABLEMTN | ETL.7040.POLE.WOOD | 2021-05-28 | 2021-05-24 |  | 2022-05-24 | 2022-05-24 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31609440 | T2 DI PT#1-HT CRK#2-BRY 8/149 REFRAME | 93E
LC | 121421266 | 015/140 | T2 DI UKH-HPLND-CLVRDL 15/140 RPL POLE | WILLITS | ETL.4050.POLE.WOOD | 2021-05-28 | 2021-05-21 |  | 2022-05-21 | 2022-05-21 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE ACCL OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31595994 | T2 DI UKH-HPLND-CLVRDL 15/140 RPL POLE | 70Y
LC | 121430148 | 012/049 | T2 DI TESLA-METCALF 012/049 INS HRDT | METCALF | ETL.6110.TOWR | 2021-05-29 | 2021-05-28 |  | 2022-05-28 | 2022-05-28 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45211588 | T2 DI TESLA-METCALF 012/049 INS HRDT | ICQ
LC | 121430257 | 011/097 | T2 DI CRAG VIEW-CASCADE 11/97 INS HRDT | TABLEMTN | ETL.1350.TOWR | 2021-05-29 | 2021-05-28 |  | 2022-05-28 | 2022-05-28 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45160958 | T2 DI CRAG VIEW-CASCADE 11/97 INS HRDT | ICQ
LC | 121430876 | 031/132 | T2 DI TESLA-METCALF 31/132 RPR GYWS | METCALF | ETL.6110.TOWR | 2021-05-29 | 2021-05-28 |  | 2022-05-28 | 2022-05-28 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45233282 | T2 DI TESLA-METCALF 31/132 RPR GYWS | ICS
LC | 121430963 | 013/055 | T2 DI TESLA-METCALF 13/55 RPL ANCS | METCALF | ETL.6110.TOWR | 2021-05-29 | 2021-05-28 |  | 2022-05-28 | 2022-05-28 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCH OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Replace | 31601396 | DI TESLA-METCALF 13/55 RPL ANCS | 93Z
LC | 121435346 | 017/002 | T2 DI MNDCN-WLLTS-FRT BRGG 17/2 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2021-06-01 | 2021-05-29 |  | 2022-05-29 | 2022-05-29 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31551283 | T2 DI MNDCN-WLTS-FRT BRG 28/10 RPL INSW | 93I
LC | 121436337 | 005/082 | T2 DI PT #1-HT CRK #2-BRNY 5/82 REFRAME | TABLEMTN | ETL.7040.INSL.NCER | 2021-06-01 | 2021-05-24 |  | 2022-05-24 | 2022-05-24 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31542660 | T2 DI PT #1-HC #2-BRNY 7/128 RPL INSW | 93I
LC | 121443732 | 042/007 | T2 DI FORT ROSS-GUALALA 42/7 RPL DAMW | LAKEVLLE | ETL.6980.INSL.NCER | 2021-06-02 | 2021-05-29 |  | 2022-05-29 | 2022-05-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR NTDE SR22 | No Good/Out of Stdrd | Damper-Wood | Replace | 45144205 | T2 DI FORT ROSS-GUALALA 42/7 RPR GYWW | ICW
LC | 121444459 | 017/073 | T2 DI GEYSERS #12-FULTON 17/73 RPLC INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2021-06-02 | 2021-06-01 |  | 2022-06-01 | 2022-06-01 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE ACCL COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31539352 | 02 EI GEYSERS #12-FULTON 7 TWRS | 93K
LC | 121447387 | 043/372 | T2 DI PIT #1-COTTONWOOD 43/372 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2021-06-02 | 2021-06-02 |  | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45149562 | T2 DI PIT #1-COTTONWOOD 43/372 RPR STRT | ICQ
LC | 121452386 | 004/008A | T2 WV CHOWCHILLA-KERCKHOFF 4/8 INS ANCW | FRESNO | ETL.1250.POLE.NWOD | 2021-06-03 | 2021-06-03 |  | 2022-06-03 | 2022-06-03 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO NTDE | Missing | Anchor-Wood | Install | 31620335 | T2 WV CHOWCHILLA-KERCKHOFF 4/8 INS ANCW | 93E
LC | 121455707 | 008/006 | T2 CARIBOU-PLUMAS JCT85 008/006 RPL POLE | TABLEMTN | ETL.6290.POLE.WOOD | 2021-06-03 | 2021-05-29 |  | 2022-05-29 | 2022-05-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR COMP OH TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31541655 | T2 CARIBOU-PLUMAS JCT-WOOD 6/18 RPL POLE | 70Y
LC | 121474585 | 011/100 | T2 DI CRAG VW-CSCD 11/100R RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-05 | 2021-06-04 |  | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121481690 | 005/000 | T2 EI HUMBOLDT-MAPLE CREEK 5/0R RPL ANCW | EUREKA | ETL.7130.POLE.WDPS | 2021-06-07 | 2021-06-05 |  | 2022-06-05 | 2022-06-05 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31542851 | T2 HUMBOLDT-MAPLE CREEK 5/000R RPL ANCW | 93E
LC | 121481737 | 005/000 | T2 EI HUMBOLDT-MAPLE CREEK 5/0L RPL ANCW | EUREKA | ETL.7130.POLE.WDPS | 2021-06-07 | 2021-06-05 |  | 2022-06-05 | 2022-06-05 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31542851 | T2 HUMBOLDT-MAPLE CREEK 5/000R RPL ANCW | 93E
LC | 121484122 | 054/004 | T2 DI FORT ROSS-GUALALA 54/4 RPL HRDW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-06-07 | 2021-05-29 |  | 2022-05-29 | 2022-05-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCM OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45144261 | T2 DI FORT ROSS-GUALALA 54/4 RPL HRDW | ICW
LC | 121484123 | 054/004 | T2 DI FORT ROSS-GUALALA 54/4 RPR GYWW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-06-07 | 2021-05-29 |  | 2022-05-29 | 2022-05-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45144261 | T2 DI FORT ROSS-GUALALA 54/4 RPL HRDW | ICW
LC | 121484125 | 054/004 | T2 DI FORT ROSS-GUALALA 54/4 RPR STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-06-07 | 2021-05-29 |  | 2022-05-29 | 2022-05-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45144261 | T2 DI FORT ROSS-GUALALA 54/4 RPL HRDW | ICW
LC | 121484666 | 031/001 | T2 DI FORT ROSS-GUALALA 31/1 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-06-07 | 2021-05-29 |  | 2022-05-29 | 2022-05-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE ACCM OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31542051 | T2 DI FORT ROSS-GUALALA 45/1 RPL STRW | 70Y
LC | 121484891 | 055/005 | T2 DI FORT ROSS-GUALALA 55/5 RPLC INSS | LAKEVLLE | ETL.6980.INSL.NCER | 2021-06-07 | 2021-05-29 |  | 2022-05-29 | 2022-05-29 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE ACCM OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542052 | T2 DI FORT ROSS-GUALALA 45/08 RPL INSW | 93I
LC | 121484892 | 055/005 | T2 DI FORT ROSS-GUALALA 55/5 INS HRDW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-06-07 | 2021-05-29 |  | 2022-05-29 | 2022-05-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCM OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45144264 | T2 DI FORT ROSS-GUALALA 55/5 INS HRDW | ICW
LC | 121485452 | 016/068 | T2 DI TESLA-METCALF 016/068 RPR ANCS | METCALF | ETL.6110.TOWR | 2021-06-07 | 2021-05-28 |  | 2022-05-28 | 2022-05-28 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair | 45233294 | T2 DI TESLA-METCALF 016/068 RPR ANCS | ICS
LC | 121485716 | 030/126 | T2 DI TESLA-METCALF-TWR 30/126 RPR GYWS | METCALF | ETL.6110.TOWR | 2021-06-07 | 2021-05-28 |  | 2022-05-28 | 2022-05-28 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45233295 | T2 DI TESLA-METCALF-TWR 30/126 RPR GYWS | ICS
LC | 121485768 | 054/007 | T2 DI FORT RSS-GLLA 54/7 RPR GYWW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-06-07 | 2021-05-29 |  | 2022-05-29 | 2022-05-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45144263 | T2 DI FORT RSS-GLLA 54/7 RPR GYWW | ICW
LC | 121485839 | 043/003 | T2 DI FRT RS-GULALA-GULALA 43/3 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-06-07 | 2021-06-01 |  | 2022-06-01 | 2022-06-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE ACCM OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31542051 | T2 DI FORT ROSS-GUALALA 45/1 RPL STRW | 70Y
LC | 121487435 | 012/106 | T2 DI CRAG VIEW-CASCADE 12/106 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-08 | 2021-05-29 |  | 2022-05-29 | 2022-05-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121487610 | 012/106 | T2 DI CRAG VIEW-CASCADE 12/106 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-08 | 2021-05-29 |  | 2022-05-29 | 2022-05-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121489335 | 025/106 | T2 DI TESLA-METCALF 025/106 UNBURY | METCALF | ETL.6110.TOWR | 2021-06-08 | 2021-06-01 |  | 2022-06-01 | 2022-06-01 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCL COMP OH TR2 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45211594 | T2 DI TESLA-METCALF 025/106 UNBURY | ICQ
LC | 121490084 | 008/159 | T2 DI MNTA VSTA-LOS GATOS 8/159 RPR STRW | METCALF | ETL.7610.POLE.WOOD | 2021-06-08 | 2021-06-01 |  | 2022-06-01 | 2022-06-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCH COMP OH TR2 PRTO AIR FRAR SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45195798 | T2 DI MNTA VSTA-LOS GATOS 8/159 RPR STRW | ICW
LC | 121491689 | 000/002 | T2 DI CARIBOU #2 000/002 REFRAME | TABLEMTN | ETL.6280.POLE.WOOD | 2021-06-08 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31542831 | T2 DI CARIBOU #2 000/002 REFRAME | 93E
LC | 121492130 | 053/007 | T2 DI HUMBOLDT-TRINITY 53/7 RPL INSS | EUREKA | ETL.1820.INSL.NCER | 2021-06-08 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31546221 | T2 DI HUMBOLDT-TRINITY RPL INSS 2TWRS | 93K
LC | 121492578 | 001/004 | T2 WV VLLEY SPRNGS-CLVRS CMNT 1/4 RPL PL | VICTOR | ETL.8220.POLE.WOOD | 2021-06-08 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW CREW OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543645 | T2 WV VLLEY SPRNGS-CLVRS CMNT 1/4 RPL PL | 70Y
LC | 121492608 | 015/312 | T2 DI SLNS-LRLS-LRLS 15/312 RPR JUMW | MOSSLNDG | ETL.7930.POLE.WOOD | 2021-06-08 | 2021-06-01 |  | 2022-06-01 | 2022-06-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45213391 | T2 DI SLNS-LRLS-LRLS 15/312 RPR JUMW | ICW
LC | 121492624 | 018/150 | T2 DI PIT #1-COTTONWOOD 18/150 INST HRDT | TABLEMTN | ETL.5390.TOWR | 2021-06-08 | 2021-06-02 |  | 2022-06-02 | 2022-06-02 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45149419 | T2 DI PIT #1-COTTONWOOD 18/150 INST HRDT | ICQ
LC | 121493086 | 025/009 | T2 DI MAPLE CREEK-HOOPA 25/9 RPL INSW | EUREKA | ETL.7490.INSL.NCER | 2021-06-08 | 2021-05-29 |  | 2022-05-29 | 2022-05-29 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31544835 | T2 DI MAPLE CREEK-HOOPA 25/9 RPL INSW | 93I
LC | 121493350 | 013/111 | T2 DI CRAG VIEW-CASCADE 13/111R RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-08 | 2021-06-01 |  | 2022-06-01 | 2022-06-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121496065 | 008/138 | T2 DI PIT#1-HAT CRK#2-BRNY8/138 RPL STRW | TABLEMTN | ETL.7040.INSL.NCER | 2021-06-09 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31543575 | T2 DI PIT#1-HAT CRK#2-BRNY8/138 RPL STRW | 70Y
LC | 121496168 | 001/010 | T2 EI DIVIDE-VANDENBERG #2 1/10 RPL INSW | PISMOBCH | ETL.8630.INSL.CERA | 2021-06-09 | 2021-06-09 |  | 2022-06-09 | 2022-06-09 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543351 | T2 EI DIVIDE-VANDENBERG #2 1/10 RPL INSW | 93I
LC | 121498834 | 010/164 | T2 DI TEJON-LEBEC 10/164 RPL INSW | MIDWAY | ETL.9250.INSL.NCER | 2021-06-09 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543644 | T2 DI TEJON-LEBEC 10/164 RPL INSW | 93I
LC | 121499055 | 018/009 | T2 EI CLEAR LAKE-KONOCTI 18/9 RPR ANCW | WILLITS | ETL.6852.POLE.WOOD | 2021-06-09 | 2021-06-09 |  | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45138102 | T2 EI CLEAR LAKE-KONOCTI 18/9 RPR ANCW | ICW
LC | 121500213 | 028/002 | T2 DI FULTON-HOPLAND 28/2 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-06-09 | 2021-06-02 |  | 2022-06-02 | 2022-06-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE ACCM OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143953 | T2 DI FULTON-HOPLAND 28/2 RPR STRW | ICW
LC | 121510795 | 000/006 | T2 DI CRAG VW-CCCDE 000/006L COMPLETE | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-10 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544910 | T2 DI CRAG VIEW-CASCADE 1/15 RPL STRW | 70Y
LC | 121511245 | 007/064 | T2 DI CRAG VIEW-CASCADE 7/64L CANCEL | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-10 | 2021-06-04 |  | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544910 | T2 DI CRAG VIEW-CASCADE 1/15 RPL STRW | 70Y
LC | 121516552 | 009/172 | T2 DI MNTA VSTA-LS GTS 009/172 RPR GYWW | METCALF | ETL.7610.POLE.WOOD | 2021-06-10 | 2021-06-01 |  | 2022-06-01 | 2022-06-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR FRAR SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45183639 | T2 DI MNTA VSTA-LS GTS 009/172 RPR GYWW | ICW
LC | 121517141 | 008/067 | T2 DI CRAG VIEW-CASCADE 8/67L CANCEL | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-10 | 2021-06-04 |  | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31516883 | T2 CRAG VIEW-CASCADE 17/151A RPL POLE | 70Y
LC | 121518237 | 024/007 | T2 DI FULTON-HOPLAND 024/007 RPL INSW | LAKEVLLE | ETL.6890.INSL | 2021-06-11 | 2021-06-10 |  | 2022-06-10 | 2022-06-10 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543773 | T2 DI FULTON-HOPLAND 024/007 RPL INSW | 93I
LC | 121518238 | 024/007 | T2 DI FULTON-HOPLAND 024/007 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-06-11 | 2021-06-10 |  | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143945 | T2NT DI FULTON-HOPLAND 024/007 RMV BUTT | ICW
LC | 121518324 | 027/195 | T2 DI CARIBOU-TBL MTN 27/195 RPL INSS | TABLEMTN | ETL.4440.INSL | 2021-06-11 | 2021-06-10 |  | 2022-06-10 | 2022-06-10 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31534944 | T3 DI CARBOU-TBL MNTAIN RPL INSS 10TWR | 93K
LC | 121518825 | 014/126 | T2 EI COTTONWD-BENTON #2 14/126 RPL POLE | TABLEMTN | ETL.6650.POLE.WDPS | 2021-06-11 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31546287 | DI CTTNWD-BNTN#2 6/58L RPL POLE | 70Y
LC | 121518876 | 014/126 | T2 EI COTTONWD-BENTON #2 14/126 RPL POLE | TABLEMTN | ETL.6650.POLE.WDPS | 2021-06-11 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31546287 | DI CTTNWD-BNTN#2 6/58L RPL POLE | 70Y
LC | 121518940 | 014/126 | T2 EI COTTONWD-BENTON #2 14/126 RPL POLE | TABLEMTN | ETL.6650.POLE.WDPS | 2021-06-11 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31546287 | DI CTTNWD-BNTN#2 6/58L RPL POLE | 70Y
LC | 121519514 | 008/070 | T2 DI CRAG VIEW-CASCADE 8/70R CANCEL | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-11 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544913 | T2 DI CRAG VIEW-CASCADE 8/70R RPL STRW | 70Y
LC | 121519516 | 008/070 | T2 DI CRAG VIEW-CASCADE 8/70L CANCEL | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-11 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544913 | T2 DI CRAG VIEW-CASCADE 8/70R RPL STRW | 70Y
LC | 121519792 | 008/184 | T2 DI HMLTN BRNCH CHSTR 8/184 COMPLETE | TABLEMTN | ETL.7000.POLE.WOOD | 2021-06-11 | 2021-06-07 |  | 2022-06-07 | 2022-06-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31439198 | T2 EI HMLTN BRNCH-CHSTR 008/185 RPL STRW | 70Y
LC | 121519960 | 002/023 | T2 DI CRAG VIEW-CASCADE 2/23R RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-11 | 2021-06-09 |  | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544910 | T2 DI CRAG VIEW-CASCADE 1/15 RPL STRW | 70Y
LC | 121519962 | 002/023 | T2 DI CRAG VIEW-CASCADE 2/23L COMPLETE | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-11 | 2021-06-09 |  | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544910 | T2 DI CRAG VIEW-CASCADE 1/15 RPL STRW | 70Y
LC | 121521772 | 015/127 | T2 EI CRAG VIEW-CASCADE 15/127 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-11 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544917 | DI T2 CRAG VIEW-CASCADE 10/94R RPL STRW | 70Y
LC | 121522128 | 037/325 | T2 DI PIT #1-COTTNWOOD 37/325 RPR CNDS | TABLEMTN | ETL.5390.INSL.NCER | 2021-06-11 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45197212 | T2 DI PIT #1-COTTNWOOD 37/325 RPR CNDS | ICS
LC | 121522250 | 008/068 | T2 DI CRAG VIEW-CASCADE 8/68 CANCEL | TABLEMTN | ETL.1350.INSL.CERA | 2021-06-11 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542859 | T2 DI CRAG VIEW-CASCADE 02/018 RPL INSLW | 93I
LC | 121522652 | 002/024 | T2 DI CRAG VIEW-CASCADE 2/24 COMPLETE | TABLEMTN | ETL.1350.INSL.CERA | 2021-06-11 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542859 | T2 DI CRAG VIEW-CASCADE 02/018 RPL INSLW | 93I
LC | 121522692 | 002/024 | T2 DI CRAG VIEW-CASCADE 2/24L COMPLETE | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-11 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 121522894 | 030/004 | T2 DI TRINITY-MAPLE CRK 30/4 RPR HRDD | EUREKA | ETL.8170.POLE.WOOD | 2021-06-11 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45135650 | T2 DI TRNTY-MPL CRK 30/4 RPR HRDD | ICW
LC | 121523245 | 008/150 | T2 DI CARIBOU-WESTWOOD 8/150 RPR GYWW | TABLEMTN | ETL.6300.POLE.WOOD | 2021-06-11 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45212497 | T2 DI CARIBOU-WESTWOOD 8/150 RPR GYWW | ICW
LC | 121523381 | 007/056 | T2 DI MA CARIBOU-TABLE MTN 7/56 RMV NEST | TABLEMTN | ETL.4440.TOWR | 2021-06-11 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR MBSF FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45195463 | T2 DI MA CARIBOU-TABLE MTN 7/56 RMV NEST | ICS
LC | 121524157 | 001/014 | T2 DI CRG VW CSCDE 001/014 COMPLETE | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 121524158 | 001/014 | T2 DI CRG VW CSCD 001/014 COMPLETE | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 121524191 | 007/003 | T2 DI MELONES-CURTIS 7/3 RPL XBRACE | VICTOR | ETL.2390.POLE.WDPS | 2021-06-12 | 2021-06-09 |  | 2022-06-09 | 2022-06-09 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31544765 | T2 DI MELONES-CURTIS 7/3 RPL XBRACE | 93E
LC | 121524308 | 003/030 | T2 DI CRAG VIEW-CASCADE 3/30 CANCEL | TABLEMTN | ETL.1350.INSL.CERA | 2021-06-12 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542859 | T2 DI CRAG VIEW-CASCADE 02/018 RPL INSLW | 93I
LC | 121524484 | 001/015 | T2 DI CRAG VIEW-CSCDE 001/015L COMPLETE | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544910 | T2 DI CRAG VIEW-CASCADE 1/15 RPL STRW | 70Y
LC | 121524505 | 001/015 | T2 DI CRAG VIEW-CASCADE 1/15R COMPLETE | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544910 | T2 DI CRAG VIEW-CASCADE 1/15 RPL STRW | 70Y
LC | 121524955 | 109/003 | T2 DI HUMBOLDT-BRIDGEVLE 109/3C RPL POLE | EUREKA | ETL.1810.POLE.WDPS | 2021-06-12 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544727 | T2 DI HMBLDT-BRDGVLLE 109/3 RPL POLE | 70Y
LC | 121525146 | 000/023 | T2 DI CTTNWD BNTN #1 0/23 RPR STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-06-12 | 2021-06-09 |  | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45213526 | T2 DI CTTNWD BNTN #1 0/23 RPR STRW | ICW
LC | 121525439 | 012/007 | T2 EI MELONES-CURTIS 12/007 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-06-12 | 2021-06-12 |  | 2022-06-12 | 2022-06-12 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543178 | EI MELONES-CURTIS RPL INSW | 93I
LC | 121525852 | 007/065 | T2 DI CRAG VIEW-CASCADE 7/65L CANCEL | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-04 |  | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31516883 | T2 CRAG VIEW-CASCADE 17/151A RPL POLE | 70Y
LC | 121525894 | 001/013 | T2 DI CRAG VIEW-CSCADE 001/013L COMPLETE | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-12 | 2021-06-09 |  | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 121525972 | 090/009 | T2 DI HUMBOLDT-TRINITY 90/9R RPR HRDW | EUREKA | ETL.1820.POLE.WDPS | 2021-06-12 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45160436 | T2 DI HUMBOLDT-TRINITY 90/9 RPR HRDW | ICW
LC | 121526448 | 008/001 | T2 DI FULTON-HOPLAND 08/01 RPR STRW | LAKEVLLE | ETL.6890.POLE.NWOD | 2021-06-12 | 2021-06-10 |  | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCM OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45143566 | T2 DI FULTON-HOPLAND 08/01 RPR STRW | ICW
LC | 121526661 | 018/097 | T2 DI TESLA-RAVENSWOOD 18/97 RPL INSS | CONCORD | ETL.5730.INSL | 2021-06-12 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31599822 | DI TESLA-RAVENSWOOD RPL INSS IN 2 TWRS. | 93K
LC | 121528063 | 000/002 | T2 EI MELONES-CURTIS 0/2 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-06-13 | 2021-06-13 |  | 2022-06-13 | 2022-06-13 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543177 | T2 EI MELONES-CURTIS 7/3 RPL INSW | 93I
LC | 121531166 | 010/003 | T2 DI FULTON-CALISTOGA 010/003 RPR GYWW | LAKEVLLE | ETL.6880.POLE.NWOD | 2021-06-14 | 2021-06-10 |  | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45144043 | T2 DI FULTON-CALISTOGA 010/003 RPR GYWW | ICW
LC | 121532027 | 004/042 | T2 DI CRAG VIEW-CASCADE 4/42L CANCEL | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-14 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544912 | T2 DI CRAG VIEW-CASCADE 4/42 RPL STRW | 70Y
LC | 121532029 | 004/042 | T2 DI CRAG VIEW-CASCADE 4/42R CANCEL | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-14 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544912 | T2 DI CRAG VIEW-CASCADE 4/42 RPL STRW | 70Y
LC | 121533134 | 091/004B | T2 WV HUMBOLDT-TRINITY 91/4 RPR SPLW | EUREKA | ETL.1820.INSL.NCER | 2021-06-14 | 2021-06-14 |  | 2022-06-14 | 2022-06-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45160720 | T2 WV HUMBOLDT-TRINITY 91/4 RPR SPLW | ICW
LC | 121533355 | 003/000 | T2 EI MELONES-CURTIS 3/000 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-06-14 | 2021-06-14 |  | 2022-06-14 | 2022-06-14 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543177 | T2 EI MELONES-CURTIS 7/3 RPL INSW | 93I
LC | 121534076 | 014/326 | T2 DI DRUM-GRASS VLY-WMR 14/326 RPR JUMW | SACTO | ETL.6760.INSL.CERA | 2021-06-14 | 2021-06-10 |  | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45195995 | T2 DI DRUM-GRASS VLY-WMBR 93/6 RPR JUMW | ICW
LC | 121534106 | 009/231 | T2 DI CTTNWD BNTN 9/231 RPR GYWW | TABLEMTN | ETL.6640.POLE.WOOD | 2021-06-14 | 2021-06-09 |  | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45213582 | T2 DI CTTNWD BNTN 9/231 RPR GYWW | ICW
LC | 121535919 | 015/352 | T2 DI DRM GRS VLY WMR 015/352 RPL HRDD | SACTO | ETL.6760.POLE.WOOD | 2021-06-14 | 2021-06-10 |  | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45174218 | T2 DI DRM GRS VLY WMR 015/352 RPL HRDD | ICW
LC | 121536058 | 018/002 | T2 DI CLEAR LAKE-KONOCTI 18/2 REFRAME | WILLITS | ETL.6852.POLE.WOOD | 2021-06-14 | 2021-06-09 |  | 2022-06-09 | 2022-06-09 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31613219 | T2 DI CLEAR LAKE-KONOCTI 18/2 REFRAME | 93E
LC | 121536558 | :003/006 | T2NT DI BELLOTA-RVRBNK-MLNS 3/6 RMV BUTT | VICTOR | ETL.1070.POLE.NWOD | 2021-06-14 | 2021-06-09 |  | 2022-06-09 | 2022-06-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45513478 | T2NT DI BELLOTA-RVRBNK-MLNS 3/6 RMV BUTT | ICW
LC | 121536809 | 113/008 | T2 DI HUMBOLDT-BRIDGEVIL 113/8 RPR ADSS | EUREKA | ETL.1810.POLE.STPS | 2021-06-14 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45155484 | T2 DI HUMBLDT-BRIDGEVILLE 113/8 RPR ADSS | ICW
LC | 121536850 | 018/360 | T2 DI COLGATE-PALERMO 18/360 RPL STRW | TABLEMTN | ETL.6500.POLE.WOOD | 2021-06-14 | 2021-06-09 |  | 2022-06-09 | 2022-06-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31604323 | T2 EI CLGTE-PLRMO 017/353 RPL STRW | 70Y
LC | 121538026 | 000/004 | T2 EI MELONES-CURTIS 0/4 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-06-15 | 2021-06-15 |  | 2022-06-15 | 2022-06-15 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543177 | T2 EI MELONES-CURTIS 7/3 RPL INSW | 93I
LC | 121539185 | 029/003 | T2 DI TRINITY-MAPLE CRK 29/3 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2021-06-15 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45128376 | T2 DI TRINITY-MAPLE CRK 29/3 RPR GYWW | ICW
LC | 121539531 | 011/099 | T2 DI CRAG VIEW-CASCADE 11/099 INS DAMS | TABLEMTN | ETL.1350.INSL | 2021-06-15 | 2021-06-15 |  | 2022-06-15 | 2022-06-15 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR NTDE | Missing | Damper-Steel | Install | 45436129 | T2 DI CRAG VIEW-CASCADE 11/099 INS DAMS | ICS
LC | 121540065 | 004/001 | T2 EI MELONES-CURTIS 4/1 RPL POLE | VICTOR | ETL.2390.POLE.WDPS | 2021-06-15 | 2021-06-15 |  | 2022-06-15 | 2022-06-15 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545147 | T2 EI MELONES-CURTIS 4/1 RPL POLE | 70Y
LC | 121540109 | 029/211 | T2 DI CARIBOU-TBL MTN 029/211 RMV NEST | TABLEMTN | ETL.4440.TOWR | 2021-06-15 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45212445 | T2 DI CARIBOU-TBL MTN 029/211 RMV NEST | ICS
LC | 121540115 | 003/008 | T2 EI MELONES-CURTIS 3/8 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-06-15 | 2021-06-15 |  | 2022-06-15 | 2022-06-15 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543178 | EI MELONES-CURTIS RPL INSW | 93I
LC | 121540154 | 011/091 | T2 DI PIT #1-COTTNWD 11/91 RPR CNDS | TABLEMTN | ETL.5390.INSL.NCER | 2021-06-15 | 2021-06-10 |  | 2022-06-10 | 2022-06-10 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Conductor-Steel | Repair | 45197218 | T2 DI PIT #1-COTTNWD 11/91 RPR CNDS | ICS
LC | 121540450 | 003/005 | T2 EI MELONES-CURTIS 3/5R RPL POLE | VICTOR | ETL.2390.POLE.WDPS | 2021-06-15 | 2021-06-15 |  | 2022-06-15 | 2022-06-15 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545146 | T2 EI MELONES-CURTIS 3/5 RPL POLE | 70Y
LC | 121540663 | 003/002 | T2 EI MELONES-CURTIS 3/2 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-06-15 | 2021-06-15 |  | 2022-06-15 | 2022-06-15 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543178 | EI MELONES-CURTIS RPL INSW | 93I
LC | 121541504 | 053/001 | T2 DI HUMBOLDT-TRINITY 53/1 RPR WDPKR | EUREKA | ETL.1820.POLE.WDPS | 2021-06-15 | 2021-06-10 |  | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45145280 | T2 DI HUMBOLT-TRINITY 53/1 RPR WDPKR | ICW
LC | 121542000 | 014/298 | T2 DI CARIBOU-WESTWOOD 014/298 RPR GYWW | TABLEMTN | ETL.6300.POLE.WOOD | 2021-06-15 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE ACCL COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45212498 | T2 DI CARIBOU-WESTWOOD 014/298 RPR GYWW | ICW
LC | 121542040 | 015/339 | T2 DI DRUM-GRS VLLY WMR 015/339 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-06-15 | 2021-06-10 |  | 2022-06-10 | 2022-06-10 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE ACCM OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31541884 | T2 DI DRM-GRS VLY-WMR 15/351 RPL STRW | 70Y
LC | 121542289 | 018/099 | T2 DI TESLA-RAVENSWOOD 18/99 RPL INSS | CONCORD | ETL.5730.INSL | 2021-06-15 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549337 | T2 DI TESLA-RVNSWD RPL INSS 5TWRS | 93K
LC | 121543755 | 016/009 | T2 DI HMBLDT BY-RIO DL JCT 16/9 RPL ANCW | EUREKA | ETL.7100.POLE.WOOD | 2021-06-15 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31589213 | T2 DI HMBLDT BY-RIO DL JCT 16/9 RPL ANCW | 93E
LC | 121543836 | 029/004 | T2 DI TRINITY-MAPLE CREEK 29/4 RPR INSW | EUREKA | ETL.8170.INSL | 2021-06-15 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45135648 | T2 DI TRINITY-MAPLE CREEK 29/4 RPR INSW | ICW
LC | 121548266 | 038/166 | T2 DI FULTON-LAKEVILLE 38/166 RPR INSS | LAKEVLLE | ETL.4780.INSL | 2021-06-16 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45143070 | T2 DI FULTON-LAKEVILLE 38/166 RPR INSS | ICS
LC | 121548682 | 000/005 | T2 EI TOCALOMA TAP 0/5L RPL STRW | LAKEVLLE | ETL.7721.POLE.WDPS | 2021-06-16 | 2021-06-16 |  | 2022-06-16 | 2022-06-16 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31544425 | T2 EI TOCALOMA TAP 0/5L RPL STRW | 70Y
LC | 121549346 | 000/004 | T2 EI TOCALOMA TAP 0/4R RPR STRW | LAKEVLLE | ETL.7721.POLE.WDPS | 2021-06-16 | 2021-06-16 |  | 2022-06-16 | 2022-06-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45136675 | T2 EI TOCALOMA TAP 0/4R RPR STRW | ICW
LC | 121550197 | 002/016 | T2 DI TRINITY-MAPLE CREEK 2/16 RPR WDPKR | EUREKA | ETL.8170.POLE.WOOD | 2021-06-16 | 2021-06-13 |  | 2022-06-13 | 2022-06-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45158740 | T2 DI TRINITY-MAPLE CREEK 2/16 RPR WDPKR | ICW
LC | 121550701 | 036/158 | T2 DI GEYSERS #9-LAKEVIL 36/158 RPR INSS | LAKEVLLE | ETL.4780.INSL | 2021-06-16 | 2021-06-11 |  | 2022-06-11 | 2022-06-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Hardware-Steel | Replace | 45143072 | T2 DI GEYSERS #9-LAKEVIL 36/158 RPR INSS | ICS
LC | 121550810 | 113/003 | T2 DI HUMBOLDT-BRIDGEVL 113/3L RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-06-16 | 2021-06-04 |  | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544411 | T2 DI HUMBOLDT-BRDGVLL 113/3R RPL STRW | 70Y
LC | 121550811 | 113/003 | T2 DI HUMBOLDT-BRIDGEVLL 113/3R RPL STRW | EUREKA | ETL.1810.POLE.WDPS | 2021-06-16 | 2021-06-04 |  | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544411 | T2 DI HUMBOLDT-BRDGVLL 113/3R RPL STRW | 70Y
LC | 121550891 | 044/381 | T2 DI PIT #1-CTTNWD 044/381 RPR GYWS | TABLEMTN | ETL.5390.TOWR | 2021-06-16 | 2021-06-12 |  | 2022-06-12 | 2022-06-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45166847 | T2 DI PIT #1-CTTNWD 044/381 RPR GYWS | ICS
LC | 121554725 | 017/006 | T2 EI UKIAH-HOPLAND 017/006R RPL POLE | WILLITS | ETL.4050.POLE.WDPS | 2021-06-17 | 2021-06-17 |  | 2022-06-17 | 2022-06-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545800 | T2 EI UKIAH-HOPLAND RPL POLE IN 6 TWRS. | 70Y
LC | 121554838 | 017/006 | T2 EI UKIAH-HOPLAND 017/006L RPL POLE | WILLITS | ETL.4050.POLE.WDPS | 2021-06-17 | 2021-06-17 |  | 2022-06-17 | 2022-06-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545800 | T2 EI UKIAH-HOPLAND RPL POLE IN 6 TWRS. | 70Y
LC | 121556040 | 002/018 | T2 DI CRAG VIEW-CASCADE 2/18 COMPLETE | TABLEMTN | ETL.1350.INSL.CERA | 2021-06-17 | 2021-06-04 |  | 2022-06-04 | 2022-06-04 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE ACCM OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542859 | T2 DI CRAG VIEW-CASCADE 02/018 RPL INSLW | 93I
LC | 121556441 | 002/032 | T2 PIT #1-MC ARTHUR 2/32 RPL STRW | TABLEMTN | ETL.7790.POLE.WOOD | 2021-06-17 | 2021-06-12 |  | 2022-06-12 | 2022-06-12 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR COMP OH TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544219 | T2 PIT #1-MC ARTHUR 1/22 RPL STRW | 70Y
LC | 121560943 | 034/001 | T2 DI MNDC-WLLT-FRT BRGG 34/1 RPL INSS | WILLITS | ETL.7550.INSL.CERA | 2021-06-18 | 2021-06-17 |  | 2022-06-17 | 2022-06-17 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31551283 | T2 DI MNDCN-WLTS-FRT BRG 28/10 RPL INSW | 93I
LC | 121561563 | 008/067 | T2 DI CRAG VIEW-CASCADE 8/67R CANCEL | TABLEMTN | ETL.1350.POLE.WDPS | 2021-06-18 | 2021-06-04 |  | 2022-06-04 | 2022-06-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31516883 | T2 CRAG VIEW-CASCADE 17/151A RPL POLE | 70Y
LC | 121565392 | 000/008 | T2 EI MELONES-CURTIS 0/8L RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-06-18 | 2021-06-13 |  | 2022-06-13 | 2022-06-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544432 | T2 EI MELONES-CURTIS 0/8R RPL STRW | 70Y
LC | 121573466 | 018/009 | T2 DI CLEAR LAKE-KONOCTI 18/9 RPR GYWW | WILLITS | ETL.6852.POLE.WOOD | 2021-06-21 | 2021-06-10 |  | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45138102 | T2 EI CLEAR LAKE-KONOCTI 18/9 RPR ANCW | ICW
LC | 121573469 | 018/009 | T2 DI CLEAR LAKE-KONOCTI 18/9 RPLC HRDW | WILLITS | ETL.6852.POLE.WOOD | 2021-06-21 | 2021-06-10 |  | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45138102 | T2 EI CLEAR LAKE-KONOCTI 18/9 RPR ANCW | ICW
LC | 121573576 | :000/001 | T2 DI BLTA-RVBK-MLNS-SWSTA :0/1 RPL POLE | VICTOR | ETL.1070.POLE.WOOD | 2021-06-21 | 2021-06-17 |  | 2022-06-17 | 2022-06-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31539414 | T2 DI BLLT-RVRBNK-MLS SWS :1/7 RPL STRW | 70Y
LC | 121574819 | 018/374 | T2 WV COLGATE-PALERMO 18/374 RPR FENCE | SACTO | ETL.6500.POLE.NWOD | 2021-06-21 | 2021-06-21 |  | 2022-06-21 | 2022-06-21 | Late | 931 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW OTHR OH FMOB TR2 PRTO NTDE | Encroachment | Right of Way | Remove
LC | 121574821 | 057/004 | T2 DI FORT ROSS-GUALALA 57/4 RPR GYWW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-06-21 | 2021-06-17 |  | 2022-06-17 | 2022-06-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45144265 | T2 DI FORT ROSS-GUALALA 57/4 RPR GYWW | ICW
LC | 121575460 | 000/005 | T2 EI TOCALOMA TAP 000/005 RPL STRW | LAKEVLLE | ETL.7721.POLE.WDPS | 2021-06-21 | 2021-06-18 |  | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31544425 | T2 EI TOCALOMA TAP 0/5L RPL STRW | 70Y
LC | 121578929 | 003/076 | T2 DI COLEMAN-CTTNWD 003/076L RPR STRW | TABLEMTN | ETL.6430.POLE.WDPS | 2021-06-22 | 2021-06-18 |  | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45212742 | T2 DI COLEMAN-CTTNWD 003/076L RPR STRW | ICW
LC | 121579031 | 003/076 | T2 DI COLEMAN-CTTNWD 003/076R RPR STRW | TABLEMTN | ETL.6430.POLE.WDPS | 2021-06-22 | 2021-06-18 |  | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45212743 | T2 DI COLEMAN-CTTNWD 003/076R RPR STRW | ICW
LC | 121580519 | 109/003 | T2 DI HMBLDT-BRDGVLLE 109/3L RPL POLE | EUREKA | ETL.1810.POLE.WDPS | 2021-06-22 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544727 | T2 DI HMBLDT-BRDGVLLE 109/3 RPL POLE | 70Y
LC | 121580641 | 109/003 | T2 DI HMBLDT-BRDGVLLE 109/3R RPL POLE | EUREKA | ETL.1810.POLE.WDPS | 2021-06-22 | 2021-06-08 |  | 2022-06-08 | 2022-06-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31544727 | T2 DI HMBLDT-BRDGVLLE 109/3 RPL POLE | 70Y
LC | 121581539 | 012/072 | T2 DI STNSLS-MLNS-MNTC 12/72 RPLC INSS | VICTOR | ETL.3830.INSL | 2021-06-22 | 2021-06-17 |  | 2022-06-17 | 2022-06-17 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31528967 | NN STANISLAUS-MLNS-MNTC RPLC INSS 11TWR | 93K
LC | 121585723 | 031/004 | T2 DI MNDCNO-WLTS-FRT BRG 31/4 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2021-06-23 | 2021-06-17 |  | 2022-06-17 | 2022-06-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE ACCH OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31543104 | T2 DI MNDCN-WLTS-FRT BRG 25/0 RPL STRW | 70Y
LC | 121586857 | 004/058 | T2 EI MANVILLE TAP 4/058 RPR JUMW | PISMOBCH | ETL.1372.INSL.CERA | 2021-06-23 | 2021-06-23 |  | 2022-06-23 | 2022-06-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Jumper-Wood | Repair | 45098804 | T2 EI MANVILLE TAP 4/058 RPR JUMW | ICW
LC | 121586867 | 004/058 | T2 EI MANVILLE TAP 4/058 RPR SPLW | PISMOBCH | ETL.1372.POLE.WDPS | 2021-06-23 | 2021-06-23 |  | 2022-06-23 | 2022-06-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Splice-Wood | Repair | 45098809 | T2 EI MANVILLE TAP 4/058 RPR SPLW | ICW
LC | 121587271 | 003/052 | T2 EI MANVILLE TAP 3/52 RPL ANCW | PISMOBCH | ETL.1372.POLE.WDPS | 2021-06-23 | 2021-06-23 |  | 2022-06-23 | 2022-06-23 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31545290 | T2 EI MANVILLE TAP 3/52 RPL ANCW | 93E
LC | 121587399 | 003/052 | T2 EI MANVILLE TAP 3/52 RPL ANCW | PISMOBCH | ETL.1372.POLE.WDPS | 2021-06-23 | 2021-06-23 |  | 2022-06-23 | 2022-06-23 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31545290 | T2 EI MANVILLE TAP 3/52 RPL ANCW | 93E
LC | 121587412 | 003/052 | T2 EI MANVILLE TAP 3/52 RPL INSW | PISMOBCH | ETL.1372.INSL.NCER | 2021-06-23 | 2021-06-23 |  | 2022-06-23 | 2022-06-23 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545289 | T2 EI MANVILLE TAP 3/52 RPL INSW | 93I
LC | 121587476 | 053/001 | T2 DI HUMBOLDT-TRINITY 53/1 RPR WDPKR | EUREKA | ETL.1820.POLE.WDPS | 2021-06-23 | 2021-06-10 |  | 2022-06-10 | 2022-06-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45145280 | T2 DI HUMBOLT-TRINITY 53/1 RPR WDPKR | ICW
LC | 121591859 | 027/007 | T2 DI TRINITY-MAPLE CRK 27/7 REFRAME | EUREKA | ETL.8170.POLE.WOOD | 2021-06-24 | 2021-06-22 |  | 2022-06-22 | 2022-06-22 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31545108 | T2 DI TRINITY-MAPLE CRK 27/7 REFRAME | 93E
LC | 121593905 | 004/046 | T2 EI CTTNWD-BNTN #2 4/46R RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-06-24 | 2021-06-24 |  | 2022-06-24 | 2022-06-24 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31511046 | DI CTTNWD BNTN #2 5/53 RPL POLE (ENG) | 70Y
LC | 121593952 | 004/046 | T2 EI CTTNWD-BNTN #2 4/46L RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-06-24 | 2021-06-24 |  | 2022-06-24 | 2022-06-24 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31511046 | DI CTTNWD BNTN #2 5/53 RPL POLE (ENG) | 70Y
LC | 121596567 | 003/025 | T2 EI UKIAH-HOPLAND 003/025 RPL INSW COA | WILLITS | ETL.4050.INSL.CERA | 2021-06-24 | 2021-06-24 |  | 2022-06-24 | 2022-06-24 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31549882 | T2 EI UKIAH-HOPLAND 003/025 RPL INSW | 93I
LC | 121596810 | 008/169 | T2 DI MNTA VSTA LS GTS 8/169 RPL HRDD | METCALF | ETL.7610.POLE.WOOD | 2021-06-24 | 2021-06-22 |  | 2022-06-22 | 2022-06-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45151592 | T2 DI MNTA VSTA LS GTS 8/169 RPL HRDD | ICW
LC | 121597200 | 021/300 | T2 DI CLAY-MARTEL 021/300 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2021-06-24 | 2021-06-22 |  | 2022-06-22 | 2022-06-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31540452 | DI CLAY-MARTEL 26/371 RPLC STRW | 70Y
LC | 121601442 | 029/002 | T2 DI TRINITY-MAPLE CREEK 29/2 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2021-06-25 | 2021-06-23 |  | 2022-06-23 | 2022-06-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45128375 | T2 DI TRINITY-MAPLE CRK 029/002 RPR GYWW | ICW
LC | 121602548 | 007/056 | T2 EI CARIBOU-TABLE MTN 7/56 COTTER | TABLEMTN | ETL.4440.INSL | 2021-06-25 | 2021-06-25 |  | 2022-06-25 | 2022-06-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45195569 | T2 EI CARIBOU-TABLE MTN 7/56 COTTER | ICS
LC | 121605417 | 016/366 | T2 DI DRM GRSS VLY WMR 16/366 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2021-06-26 | 2021-06-23 |  | 2022-06-23 | 2022-06-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE ACCM OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45193821 | T2 DI DRM GRSS VLY WMR 16/366 RPR GYWW | ICW
LC | 121605419 | 008/156 | T2 DI MNTA VSTA-LS GTS 008/156 RPL INSW | METCALF | ETL.7610.INSL | 2021-06-26 | 2021-06-22 |  | 2022-06-22 | 2022-06-22 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31545157 | T2 DI MNTA VSTA-LS GTS 008/156 RPL INSW | 93I
LC | 121606885 | B016/371 | T2 DI DRM GRS VLY WMR B016/371 RPL INSW | SACTO | ETL.6760.INSL.NCER | 2021-06-26 | 2021-06-23 |  | 2022-06-23 | 2022-06-23 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31613843 | T2 DI DRM GRS VLY WMR B016/371 RPL INSW | 93I
LC | 121609001 | 009/173 | T2 DI MNTA VSTA LS GTS 009/173 RPR INSW | METCALF | ETL.7610.INSL | 2021-06-26 | 2021-06-22 |  | 2022-06-22 | 2022-06-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE ACCH COMP OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45183880 | T2 DI MNTA VSTA LS GTS 009/173 RPR INSW | ICW
LC | 121609276 | 009/153 | T2 DI TEJON-LEBEC 009/153 RPL STRW | MIDWAY | ETL.9250.POLE.WOOD | 2021-06-26 | 2021-06-23 |  | 2022-06-23 | 2022-06-23 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31543041 | T2 DI TEJON-LEBEC 12/210 RPLC STRW | 70Y
LC | 121609301 | 012/247 | T2 DI COLGATE-PALERMO 012/247 RPL STRW | TABLEMTN | ETL.6500.POLE.WOOD | 2021-06-26 | 2021-06-22 |  | 2022-06-22 | 2022-06-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31612267 | T2 EI COLGATE-PALERMO 15/299 RPL PL | 70Y
LC | 121609375 | :004/002 | T2 DI BLT-RVRBNK-MLNS :4/2 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-06-26 | 2021-06-22 |  | 2022-06-22 | 2022-06-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31596141 | T2 DI BLT-RVRBNK-MLNS :4/2 RPL STRW | 70Y
LC | 121620574 | 008/001 | T2 EI HUMBOLDT-MAPLE CREEK 8/1R RPL STRW | EUREKA | ETL.7130.POLE.WDPS | 2021-06-28 | 2021-06-27 |  | 2022-06-27 | 2022-06-27 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545255 | T2 EI HUMBOLDT-MAPLE CREEK 8/1R RPL STRW | 70Y
LC | 121620649 | 008/001 | T2 EI HUMBOLDT-MAPLE CREEK 8/1C RPL STRW | EUREKA | ETL.7130.POLE.WDPS | 2021-06-28 | 2021-06-27 |  | 2022-06-27 | 2022-06-27 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545255 | T2 EI HUMBOLDT-MAPLE CREEK 8/1R RPL STRW | 70Y
LC | 121620678 | 008/001 | T2 EI HUMBOLDT-MAPLE CREEK 8/1L RPL STRW | EUREKA | ETL.7130.POLE.WDPS | 2021-06-28 | 2021-06-27 |  | 2022-06-27 | 2022-06-27 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545255 | T2 EI HUMBOLDT-MAPLE CREEK 8/1R RPL STRW | 70Y
LC | 121621031 | 038/009 | T2 DI FORT ROSS-GUALALA 038/009 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-06-28 | 2021-06-18 |  | 2022-06-18 | 2022-06-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31607660 | T2 DI FORT ROSS-GUALALA 038/009 RPL STRW | 70Y
LC | 121621037 | 038/009 | T2 DI FORT ROSS-GUALALA 038/009 RPR STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-06-28 | 2021-06-18 |  | 2022-06-18 | 2022-06-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45144169 | T2 DI FORT ROSS-GUALALA 038/009 RPR STRW | ICW
LC | 121623779 | 012/286 | T2 DI DRM-GRS VLY-WMR 12/286 RPR SPLW | SACTO | ETL.6760.INSL.NCER | 2021-06-28 | 2021-06-28 |  | 2022-06-28 | 2022-06-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCM OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45200489 | T2 DI DRM-GRS VLY-WMR 12/286 RPR SPLW | ICW
LC | 121624533 | B015/356 | T2 DI DRM GRS VLY WEMAR B15/356 RPR SPLW | SACTO | ETL.6760.POLE.WOOD | 2021-06-28 | 2021-06-28 |  | 2022-06-28 | 2022-06-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCM OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45193824 | T2 DI DRM GRS VLY WEMAR B15/356 RPR SPLW | ICW
LC | 121624661 | 002/001 | T2 EI MELONES-CURTIS 2/1 RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-06-28 | 2021-06-14 |  | 2022-06-14 | 2022-06-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31545144 | T2 EI MELONES-CURTIS 2/1 RPL STRW | 70Y
LC | 121628313 | 008/149 | T2 DI TEJON-LEBEC 008/149 RPL INSW | MIDWAY | ETL.9250.INSL.NCER | 2021-06-29 | 2021-06-23 |  | 2022-06-23 | 2022-06-23 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31543644 | T2 DI TEJON-LEBEC 10/164 RPL INSW | 93I
LC | 121629115 | 014/319 | T2 DI DRUM-GRSS VLLY-WMR 14/319 RPL INSW | SACTO | ETL.6760.INSL.NCER | 2021-06-29 | 2021-06-24 |  | 2022-06-24 | 2022-06-24 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE ACCH OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31540566 | T2 DI DRUM-GRS VLY-WMR 16/369 RPLC INSWC | 93I
LC | 121629117 | 022/092 | T2 DI DIABLO-GATES #1 22/092 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2021-06-29 | 2021-06-24 |  | 2022-06-24 | 2022-06-24 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCM COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45068523 | T2 DI DIABLO-GATES #1 22/092 RPR GYWS | ICS
LC | 121629367 | 004/001 | T2 EI MELONES-CURTIS 4/1 RPL POLE | VICTOR | ETL.2390.POLE.WDPS | 2021-06-29 | 2021-06-15 |  | 2022-06-15 | 2022-06-15 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW INSP OH FMOB TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545147 | T2 EI MELONES-CURTIS 4/1 RPL POLE | 70Y
LC | 121631262 | 003/005 | T2 EI MELONES-CURTIS 3/5L RPL POLE | VICTOR | ETL.2390.POLE.WDPS | 2021-06-29 | 2021-06-15 |  | 2022-06-15 | 2022-06-15 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW INSP OH FMOB TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31545146 | T2 EI MELONES-CURTIS 3/5 RPL POLE | 70Y
LC | 121631671 | 024/000 | T2 DI FULTON-HOPLAND 024/000 RPR CRSW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-06-29 | 2021-06-28 |  | 2022-06-28 | 2022-06-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45143944 | T2 EI FULTON-HOPLAND 24/0 RPR GYWW | ICW
LC | 121638985 | 031/011 | T2 WV FORT ROSS-GUALALA 31/11 INS DAMW | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-06-30 | 2021-06-30 |  | 2022-06-30 | 2022-06-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO FRAB | Missing | Damper-Wood | Install | 45144165 | T2 WV FORT ROSS-GUALALA 31/11 INS DAMW | ICW
LC | 121640372 | 042/359 | T2NT DI PIT#1-CTONWOOD 042/359 RMV BUTT | TABLEMTN | ETL.5390.TOWR | 2021-06-30 | 2021-06-10 |  | 2022-06-10 | 2022-06-10 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove
LC | 121647003 | 016/376 | T2 DI DRUM-GRS VLY WEMR 16/376 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-07-01 | 2021-06-28 |  | 2022-06-28 | 2022-06-28 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE ACCM OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541884 | T2 DI DRM-GRS VLY-WMR 15/351 RPL STRW | 70Y
LC | 121656562 | 004/041 | T2 DI COTTONWOOD-BNTN #2 4/41L RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-02 | 2021-07-01 |  | 2022-07-01 | 2022-07-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31511046 | DI CTTNWD BNTN #2 5/53 RPL POLE (ENG) | 70Y
LC | 121656563 | 004/041 | T2 DI COTTONWOOD-BNTN #2 4/41R RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-02 | 2021-07-01 |  | 2022-07-01 | 2022-07-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31511046 | DI CTTNWD BNTN #2 5/53 RPL POLE (ENG) | 70Y
LC | 121659150 | 017/001C | T2 WV TRINITY-MAPLE CREEK 17/1C RPR SPLW | EUREKA | ETL.8170.POLE.NWOD | 2021-07-02 | 2021-07-02 |  | 2022-07-02 | 2022-07-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 44892192 | T2 WV TRINITY-MAPLE CREEK 17/1C RPR SPLW | ICW
LC | 121669029 | 009/087 | T2 EI CTTNWD BNTN#2 9/87L RPL POLE | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-06 | 2021-07-06 |  | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31546287 | DI CTTNWD-BNTN#2 6/58L RPL POLE | 70Y
LC | 121669285 | 002/031 | T2 EI COTTONWD-BNTN #2 2/031L RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-06 | 2021-07-06 |  | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31511046 | DI CTTNWD BNTN #2 5/53 RPL POLE (ENG) | 70Y
LC | 121669333 | 002/031 | T2 EI COTTONWOOD-BNTN #2 2/31R RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-06 | 2021-07-06 |  | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31511046 | DI CTTNWD BNTN #2 5/53 RPL POLE (ENG) | 70Y
LC | 121670093 | 003/035 | T2 EI COTTONWD-BNTN #2 3/35L RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-06 | 2021-07-06 |  | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31511046 | DI CTTNWD BNTN #2 5/53 RPL POLE (ENG) | 70Y
LC | 121670117 | 003/035 | T2 EI COTTONWD-BNTN #2 3/035R RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-06 | 2021-07-06 |  | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31511046 | DI CTTNWD BNTN #2 5/53 RPL POLE (ENG) | 70Y
LC | 121671388 | 003/037 | T2 EI COTTONWOOD-BENTON 3/37L RPL POLE | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-06 | 2021-07-06 |  | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31511046 | DI CTTNWD BNTN #2 5/53 RPL POLE (ENG) | 70Y
LC | 121673602 | 003/052 | T2 DI MANVILLE TAP 003/052C RPR GYWW | PISMOBCH | ETL.1372.POLE.WDPS | 2021-07-07 | 2021-07-06 |  | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45090089 | T2 DI MANVILLE TAP 003/052C RPR GYWW | ICW
LC | 121675657 | 003/055 | T2 DI MANVILLE TAP 003/055C RPL STRW | PISMOBCH | ETL.1372.POLE.WDPS | 2021-07-07 | 2021-07-06 |  | 2022-07-06 | 2022-07-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546211 | T2 DI MANVILLE TAP 003/055R RPL STRW | 70Y
LC | 121675658 | 003/055 | T2 DI MANVILLE TAP 003/055L RPL STRW | PISMOBCH | ETL.1372.POLE.WDPS | 2021-07-07 | 2021-07-06 |  | 2022-07-06 | 2022-07-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546211 | T2 DI MANVILLE TAP 003/055R RPL STRW | 70Y
LC | 121675697 | 007/065 | T2 CRAG VIEW-CASCADE 007/065R CANCEL | TABLEMTN | ETL.1350.POLE.WDPS | 2021-07-07 | 2021-07-07 |  | 2022-07-07 | 2022-07-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR OH FMOB TR2 PRTO SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31516883 | T2 CRAG VIEW-CASCADE 17/151A RPL POLE | 70Y
LC | 121676005 | 003/055 | T2 DI MANVILLE TAP 003/055R RPL STRW | PISMOBCH | ETL.1372.POLE.WDPS | 2021-07-07 | 2021-07-06 |  | 2022-07-06 | 2022-07-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546211 | T2 DI MANVILLE TAP 003/055R RPL STRW | 70Y
LC | 121677340 | T065 | T3 EI MIDWAY-SANTA MARIA T65 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-07 | 2021-07-07 |  | 2022-01-03 | 2022-01-07 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31596011 | T3 DI MIDWAY-SANTA MARIA RPL INSS | 93K
LC | 121679075 | 019/002 | T2 DI FULTON-HOPLAND 19/2 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2021-07-07 | 2021-07-05 |  | 2022-07-05 | 2022-07-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE ACCM OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600084 | T2 DI FULTON-HOPLAND 018/002 RPL POLE | 70Y
LC | 121683977 | T-105 | T3 EI MIDWAY-SANTA MARIA T-105 RPL STRW | PISMOBCH | ETL.9240.POLE.WOOD | 2021-07-08 | 2021-07-08 |  | 2022-01-04 | 2022-01-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31596154 | T3 EI CMIDWAY-SANTA MARIA T-105 RPL STRW | 70Y
LC | 121684001 | T-106 | T3 EI MIDWAY-SANTA MARIA T-106 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-08 | 2021-07-08 |  | 2022-01-04 | 2022-01-08 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548618 | T3 DI MIDWAY-SANTA MARIA RPL INSS 6TWRS | 93K
LC | 121684425 | 004/002 | T3 DI DONNELLS-MI-WUK 4/2 RPL INSW | VICTOR | ETL.1400.INSL.NCER | 2021-07-08 | 2021-07-07 |  | 2022-01-03 | 2022-01-07 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546198 | T3 DI DONNELLS-MI-WUK 5/000 RPL INSW | 93I
LC | 121685829 | 020/087A | T3 DI EGL RK-FTN-SLVRD 020/087A RPL INSS | LAKEVLLE | ETL.4392.INSL.NCER | 2021-07-08 | 2021-07-06 |  | 2022-01-02 | 2022-01-06 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549863 | T3 DI EGL RCK-FLTN-SLVRD RPL INSS 2TWRS | 93K
LC | 121687760 | 003/029 | T2 DI PIT#1 HAT CRK#2 BRNY 3/29 RPL HRDW | TABLEMTN | ETL.7040.POLE.WOOD | 2021-07-09 | 2021-07-06 |  | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45213916 | T2 DI PIT#1 HAT CRK#2 BRNY 3/29 RPL HRDW | ICW
LC | 121687920 | 003/000 | T3 DI DONNELLS-MI-WUK 3/0 RPL INSW | VICTOR | ETL.1400.INSL.NCER | 2021-07-09 | 2021-07-07 |  | 2022-01-03 | 2022-01-07 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546198 | T3 DI DONNELLS-MI-WUK 5/000 RPL INSW | 93I
LC | 121688776 | 012/012 | T3 DI MAPLE CREEK-HOOPA 12/12 CNCL | EUREKA | ETL.7490.POLE.WOOD | 2021-07-09 | 2021-07-05 |  | 2022-01-01 | 2022-01-05 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31547424 | T3 DI MAPLE CREEK-HOOPA 12/12 REFRAME | 93E
LC | 121691819 | 001/011 | T2 DI MTN GTE JCT CSCD 001/011 RPR GYWW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-09 | 2021-07-06 |  | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 121705653 | 006/058 | T2 DI CTTNWD-BENTON#2 006/058R RPL POLE | TABLEMTN | ETL.6650.POLE.WOOD | 2021-07-10 | 2021-07-07 |  | 2022-07-07 | 2022-07-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546287 | DI CTTNWD-BNTN#2 6/58L RPL POLE | 70Y
LC | 121705654 | 006/058 | T2 DI CTTNWD-BNTN#2 6/58L RPL POLE | TABLEMTN | ETL.6650.POLE.WOOD | 2021-07-10 | 2021-07-07 |  | 2022-07-07 | 2022-07-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546287 | DI CTTNWD-BNTN#2 6/58L RPL POLE | 70Y
LC | 121705711 | 025/003 | T2 DI GARB-LAYTONVILLE 025/003 RPR GYWW | WILLITS | ETL.8365.POLE.WOOD | 2021-07-10 | 2021-07-08 |  | 2022-07-08 | 2022-07-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCM OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45155522 | T2 DI GARB-LAYTONVILLE 028/003 RPR GYWW | ICW
LC | 121706494 | 006/060 | T2 DI CTTNWD-BENTON #2 6/060L RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-10 | 2021-07-07 |  | 2022-07-07 | 2022-07-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | Rotten | Structure-Wood | Replace | 31546287 | DI CTTNWD-BNTN#2 6/58L RPL POLE | 70Y
LC | 121706520 | 005/054 | T2 DI CTTNWD-BNTN #2 5/54 RPR CONDW | TABLEMTN | ETL.6650.INSL.NCER | 2021-07-10 | 2021-07-07 |  | 2022-07-07 | 2022-07-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45213229 | T2 DI CTTNWD-BNTN #2 2/54 RPR CONDW | ICW
LC | 121707381 | R000/007 | T2 DI CRBRY SW ST-RND MT R0/7 RPR INSW | TABLEMTN | ETL.5410.INSL.CERA | 2021-07-10 | 2021-07-06 |  | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45213662 | T2 DI CRBRY SW ST-RND MT R0/7 RPR INSW | ICW
LC | 121707385 | 003/071 | T2 DI DELTA-MTN GATE JCT 3/71L RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-10 | 2021-07-06 |  | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546387 | T2 DI DELTA-MTN GATE JCT 3/71L RPL STRW | 70Y
LC | 121707386 | 003/071 | T2 DI DELTA-MTN GATE JCT 3/71 RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2021-07-10 | 2021-07-06 |  | 2022-07-06 | 2022-07-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546387 | T2 DI DELTA-MTN GATE JCT 3/71L RPL STRW | 70Y
LC | 121707687 | 004/058 | T2 DI MANVILLE TAP 004/058 RPR STRW | PISMOBCH | ETL.1372.POLE.WDPS | 2021-07-10 | 2021-07-06 |  | 2022-07-06 | 2022-07-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45098802 | T2 DI MANVILLE TAP 004/058 RPR STRW | ICW
LC | 121712517 | 020/087 | T3 DI EGL RCK-FLTN-SLVRD 20/87 RPL INSS | LAKEVLLE | ETL.4392.INSL.CERA | 2021-07-12 | 2021-07-06 |  | 2022-01-02 | 2022-01-06 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31549863 | T3 DI EGL RCK-FLTN-SLVRD RPL INSS 2TWRS | 93K
LC | 121716654 | 050/001 | T2 EI FORT ROSS-GUALALA 50/1 RPLC POLE | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-07-12 | 2021-07-12 |  | 2022-07-12 | 2022-07-12 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE ACCM OH TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31542051 | T2 DI FORT ROSS-GUALALA 45/1 RPL STRW | 70Y
LC | 121717631 | 006/000 | T3 DI DNNELLS-MI-WUK-WOOD 06/00 RPL INSW | VICTOR | ETL.1400.INSL.NCER | 2021-07-12 | 2021-07-08 |  | 2022-01-04 | 2022-01-08 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546198 | T3 DI DONNELLS-MI-WUK 5/000 RPL INSW | 93I
LC | 121717668 | 002/008 | T3 DI DONNELLS-MI-WUK 2/8 RPL INSW | VICTOR | ETL.1400.INSL.NCER | 2021-07-12 | 2021-07-08 |  | 2022-01-04 | 2022-01-08 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31577860 | T3 DI DONNELLS-MI-WUK 2/8 RPL INSW | 93I
LC | 121717703 | 004/005 | T3 DI DONNELLS-MI-WUK 4/5 RPL INSW | VICTOR | ETL.1400.INSL.NCER | 2021-07-12 | 2021-07-07 |  | 2022-01-03 | 2022-01-07 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31577860 | T3 DI DONNELLS-MI-WUK 2/8 RPL INSW | 93I
LC | 121718064 | 007/066 | T2 DI CTTNWD-BNTN #2 7/66 RPR INSW | TABLEMTN | ETL.6650.INSL.NCER | 2021-07-12 | 2021-07-08 |  | 2022-07-08 | 2022-07-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45213231 | T2 DI CTTNWD-BNTN #2 7/66 RPR INSW | ICW
LC | 121720885 | 013/002A | T3 DI DONNELLS-MI-WUK 013/002A RPL INSW | VICTOR | ETL.1400.INSL.CERA | 2021-07-13 | 2021-07-05 |  | 2022-01-01 | 2022-01-05 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546391 | T3 DI DONNELLS-MI-WUK 013/002A RPL INSW | 93I
LC | 121724900 | 006/002 | T3 DI DONNELLS-MI-WUK-WOOD 6/2 RPL INSW | VICTOR | ETL.1400.INSL.NCER | 2021-07-13 | 2021-07-07 |  | 2022-01-03 | 2022-01-07 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31577860 | T3 DI DONNELLS-MI-WUK 2/8 RPL INSW | 93I
LC | 121724957 | 007/004 | T3 DI DONNELLS-MI-WUK-WOOD 7/4 RPL INSW | VICTOR | ETL.1400.INSL.NCER | 2021-07-13 | 2021-07-07 |  | 2022-01-03 | 2022-01-07 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31577860 | T3 DI DONNELLS-MI-WUK 2/8 RPL INSW | 93I
LC | 121726185 | 006/060 | T2 DI CTTNWD-BENTON #2 6/60R RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-14 | 2021-07-07 |  | 2022-07-07 | 2022-07-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | Rotten | Structure-Wood | Replace | 31546287 | DI CTTNWD-BNTN#2 6/58L RPL POLE | 70Y
LC | 121729569 | 005/135 | T3 DI DRUM-GRASS VLLY-WMR 5/135 RPR SPLW | SACTO | ETL.6760.INSL.NCER | 2021-07-14 | 2021-07-14 |  | 2022-01-10 | 2022-01-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45218801 | T3 DI DRUM-GRASS VLLY-WMR 5/135 RPR SPLW | ICW
LC | 121730118 | 003/032 | T2 DI MTN GATE JCT-CASCADE 3/32 RPL STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2021-07-14 | 2021-07-09 |  | 2022-07-09 | 2022-07-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31629783 | T2 DI MTN GATE JCT-CASCADE 3/32 RPL STRW | 70Y
LC | 121731238 | 010/214 | T2 SALINAS-LAURELES 010/214 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2021-07-14 | 2021-07-14 |  | 2022-07-14 | 2022-07-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31546416 | T2 SALINAS-LAURELES 010/214 RPL POLE | 70Y
LC | 121731742 | 006/005 | T3 DI DONNELLS-MI-WUK 006/005 RPL INSW | VICTOR | ETL.1400.INSL.NCER | 2021-07-14 | 2021-07-07 |  | 2022-01-03 | 2022-01-07 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31577860 | T3 DI DONNELLS-MI-WUK 2/8 RPL INSW | 93I
LC | 121731749 | 016/115 | T3 DI ROCK CK-POE 16/115 RPR JMPR | TABLEMTN | ETL.5630.POLE.STPS | 2021-07-14 | 2021-07-07 |  | 2022-01-03 | 2022-01-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Wood | Repair | 45277450 | T3 DI ROCK CK-POE 16/1 RPR JMPR | ICW
LC | 121731999 | 016/001 | T3 DI DONNELLS-MI-WUK WP 16/1R RPR GYWW | VICTOR | ETL.1400.POLE.WDPS | 2021-07-14 | 2021-07-07 |  | 2022-01-03 | 2022-01-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45122746 | T3 DI DONNELLS-MI-WUK WP 16/1R RPR GYWW | ICW
LC | 121732139 | 002/004 | T2 DI MENDOCINO-UKIAH 02/04L BACKFIL | WILLITS | ETL.2420.POLE.STPS | 2021-07-14 | 2021-07-09 |  | 2022-07-09 | 2022-07-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45142181 | T2 DI MENDOCINO-UKIAH 02/04L BACKFIL | ICW
LC | 121732177 | 004/001 | T3 DI DONNELLS-MI-WUK 4/1 RPL INSW | VICTOR | ETL.1400.INSL.NCER | 2021-07-14 | 2021-07-07 |  | 2022-01-03 | 2022-01-07 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31577860 | T3 DI DONNELLS-MI-WUK 2/8 RPL INSW | 93I
LC | 121732373 | 013/103 | T2 DI PIT #3-PIT #1 013/103 RPL SWS | TABLEMTN | ETL.5400.TOWR | 2021-07-14 | 2021-07-09 |  | 2022-07-09 | 2022-07-09 | Late | 435 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Switch-Steel | Replace | 31549176 | T2 DI PIT #3-PIT #1 013/103 RPL SWS | 93S
LC | 121734412 | 009/157 | T2 DI TEJON-LEBEC 9/157 RPLC INSW | MIDWAY | ETL.9250.INSL.NCER | 2021-07-15 | 2021-07-14 |  | 2022-07-14 | 2022-07-14 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579991 | T2 DI TEJON-LEBEC 9/157 RPLC INSW | 93I
LC | 121738178 | 015/080 | T2 WV KINGS RVR-SNGR-RDLY 15/80 RPL HRDT | FRESNO | ETL.2030.INSL.NCER | 2021-07-15 | 2021-07-15 |  | 2022-07-15 | 2022-07-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45070449 | T2 WV KINGS RVR-SNGR-RDLY 15/80 RPL HRDT | ICQ
LC | 121738767 | 003/021 | T3 DI SBRANTE"G"#1"-TOWER 3/21 VEG RMV | CONCORD | ETL.3720.TOWR | 2021-07-15 | 2021-07-13 |  | 2022-01-09 | 2022-01-13 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 121738961 | 013/007 | T2 DI MELONES-CURTIS 13/7L RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-15 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579809 | T2 DI MELONES-CURTIS 13/7L RPL STRW | 70Y
LC | 121739006 | 003/004 | T2 DI MELONES-CURTIS 3/4L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-15 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45158157 | T2 DI MELONES-CURTIS 3/4 RPR STRW | ICW
LC | 121739060 | 012/004 | T2 DI MELONES-CURTIS 12/04 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-15 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579810 | T2 DI MELONES-CURTIS 12/04 RPL INSW | 93I
LC | 121741268 | 019/002 | T2 DI CLEAR LAKE-KONOCTI 19/02 RPL POLE | WILLITS | ETL.6852.POLE.WOOD | 2021-07-16 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31545484 | T2 DI CLEAR LAKE-KONOCTI 17/6 RPL STRW | 70Y
LC | 121741541 | 000/002 | T3 DI WP-VALLEY SPRINGS 0/2 RPL STRW | VICTOR | ETL.8350.POLE.WOOD | 2021-07-16 | 2021-07-13 |  | 2022-01-09 | 2022-01-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31579997 | T3 DI WP-VALLEY SPRINGS 0/2 RPL STRW | 70Y
LC | 121741582 | 010/000 | T2 DI MELONES-CURTIS 010/000 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-16 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579810 | T2 DI MELONES-CURTIS 12/04 RPL INSW | 93I
LC | 121741596 | 011/003 | T2 DI MELONES-CURTIS 11/3L RPR GYWW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45162139 | T2 DI MELONES-CURTIS 11/3L RPR GYWW | ICW
LC | 121741944 | 072/004 | T2 DI HUMBOLDT-TRINITY 72/4 RPR POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-07-16 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 45158944 | T2NT EI HUMBOLDT-TRINITY 72/4 RMV BUTT | ICW
LC | 121741999 | 072/004 | T2 DI HUMBOLDT-TRINITY 72/4 RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-07-16 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31547347 | T2 DI HUMBOLDT-TRINITY 72/4 RPL POLE | 70Y
LC | 121742641 | 012/000 | T2 DI MELONES-CURTIS 12/0 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-16 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579810 | T2 DI MELONES-CURTIS 12/04 RPL INSW | 93I
LC | 121743019 | 089/004 | T2 DI HUMBOLDT-TRINITY 89/4 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-16 | 2021-07-12 |  | 2022-07-12 | 2022-07-12 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542140 | T2 EI HUMBOLDT-TRINITY 89/9 RPL INSW | 93I
LC | 121743340 | 013/002 | T2 DI MELONES-CURTIS 13/02 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-16 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579810 | T2 DI MELONES-CURTIS 12/04 RPL INSW | 93I
LC | 121743659 | 073/006 | T2 DI HUMBOLDT-TRINITY 73/6L RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2021-07-16 | 2021-07-12 |  | 2022-07-12 | 2022-07-12 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31615000 | T2 DI HUMBOLDT-TRINITY 73/06 RPL STRW | 70Y
LC | 121743824 | 089/008 | T2 DI HUMBOLDT-TRINITY 89/8 RPL INSW | EUREKA | ETL.1820.INSL.NCER | 2021-07-16 | 2021-07-12 |  | 2022-07-12 | 2022-07-12 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542140 | T2 EI HUMBOLDT-TRINITY 89/9 RPL INSW | 93I
LC | 121743965 | 090/010C | T2 DI HUMBOLDT-TRINITY 90/10C RPR INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-16 | 2021-07-12 |  | 2022-07-12 | 2022-07-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45160437 | T2 DI HUMBOLDT-TRINITY 90/10C RPR INSW | ICW
LC | 121744087 | 003/007 | T2 DI MELONES-CURTIS 3/7L RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579811 | T2 DI MELONES-CURTIS 3/7 RPL STRW | 70Y
LC | 121744134 | 003/001 | T2 DI MELONES-CURTIS 3/1 RPL DAMW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace | 45163112 | T2 DI MELONES-CURTIS 3/1 RPL DAMW | ICW
LC | 121744314 | 013/008 | T2 DI MELONES-CURTIS 13/8 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-16 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579810 | T2 DI MELONES-CURTIS 12/04 RPL INSW | 93I
LC | 121744365 | 001/000 | T2 DI MELONES-CURTIS 1/0 RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45163119 | T2 DI MELONES-CURTIS 1/0 RPR STRW | ICW
LC | 121744409 | 013/001 | T2 DI MELONES-CURTIS 13/01 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-16 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579810 | T2 DI MELONES-CURTIS 12/04 RPL INSW | 93I
LC | 121744782 | 012/206 | T2 DI TEJON-LEBEC-NONWD 12/206 RPL INSS | MIDWAY | ETL.9250.INSL.NCER | 2021-07-16 | 2021-07-15 |  | 2022-07-15 | 2022-07-15 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31596660 | T2 DI TEJON-LEBEC-NONWD 12/206 RPL INSS | 93K
LC | 121745036 | 011/185 | T2 DI TEJON-LEBEC 011/185 RPR GYWW | MIDWAY | ETL.9250.POLE.WOOD | 2021-07-16 | 2021-07-14 |  | 2022-07-14 | 2022-07-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45068013 | T2 DI TEJON-LEBEC 011/185 RPR GYWW | ICW
LC | 121745483 | 011/001 | T2 DI MELONES-CURTIS 11/01 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-16 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579810 | T2 DI MELONES-CURTIS 12/04 RPL INSW | 93I
LC | 121745754 | 002/006 | T2 DI MELONES-CURTIS 2/6 RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-16 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE COMP OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45163407 | T2 DI MELONES-CURTIS 2/6 RPR STRW | ICW
LC | 121746189 | 009/162 | T2 DI TEJON-LEBEC 009/162 RPR SPLW | MIDWAY | ETL.9250.POLE.NWOD | 2021-07-16 | 2021-07-14 |  | 2022-07-14 | 2022-07-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45068014 | T2 DI TEJON-LEBEC 009/162 RPR SPLW | ICW
LC | 121746981 | 009/162 | T2 DI TEJON-LEBEC 009/162 RMV COND | MIDWAY | ETL.9250.POLE.NWOD | 2021-07-16 | 2021-07-14 |  | 2022-07-14 | 2022-07-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Conductor-Wood | Remove | 45068015 | T2 DI TEJON-LEBEC 009/162 RMV DBRS | ICW
LC | 121748111 | 009/006 | T2 DI MELONES-CURTIS 9/6L RPR GUYWW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-17 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45163418 | T2 DI MELONES-CURTIS 9/6L RPR GYWW | ICW
LC | 121748148 | 008/008 | T2 DI MELONES-CURTIS 008/008 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-17 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579810 | T2 DI MELONES-CURTIS 12/04 RPL INSW | 93I
LC | 121748444 | 009/087 | T2 DI CTTNWD-BENTON #2 009/087 RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2021-07-17 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31546287 | DI CTTNWD-BNTN#2 6/58L RPL POLE | 70Y
LC | 121749211 | 076/000A | T2 DI HUMBOLDT-TRINITY 076/000A RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2021-07-17 | 2021-07-15 |  | 2022-07-15 | 2022-07-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148455 | T2NT DI HUMBOLDT-TRINITY 076/0A RMV DBRS | ICW
LC | 121749262 | 076/000B | T2 DI HUMBOLDT-TRINITY 076/000B RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2021-07-17 | 2021-07-15 |  | 2022-07-15 | 2022-07-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148455 | T2NT DI HUMBOLDT-TRINITY 076/0A RMV DBRS | ICW
LC | 121749305 | 076/000C | T2 DI HUMBOLDT-TRINITY 076/000C RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2021-07-17 | 2021-07-15 |  | 2022-07-15 | 2022-07-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45148455 | T2NT DI HUMBOLDT-TRINITY 076/0A RMV DBRS | ICW
LC | 121750221 | 011/256 | T3 DI DRUM-GRS VALY-WMAR 11/256 RPR INSW | SACTO | ETL.6760.INSL.NCER | 2021-07-17 | 2021-07-17 |  | 2022-01-13 | 2022-01-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45218808 | T3 DI DRUM-GRS VALY-WMAR 11/256 RPR INSW | ICW
LC | 121750284 | 089/007C | T2 DI HUMBOLDT-TRINITY 89/7C RPR STRW | EUREKA | ETL.1820.POLE.WOOD | 2021-07-17 | 2021-07-15 |  | 2022-07-15 | 2022-07-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45160705 | T2 DI HUMBOLDT-TRINITY 89/7C RPR STRW | ICW
LC | 121760318 | 009/006 | T2 EI MELONES-CURTIS 9/6R RPR GUYWW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-20 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45164447 | T2 EI MELONES-CURTIS 9/6R RPR GYWW | ICW
LC | 121760514 | 011/004B | T3 DI MAPLE CREEK-HOOPA 11/4B CNCL | EUREKA | ETL.7490.POLE.WOOD | 2021-07-20 | 2021-07-19 |  | 2022-01-15 | 2022-01-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548069 | T3 DI MAPLE CREEK-HOOPA 11/4A RPL STRW | 70Y
LC | 121760619 | 011/004A | T3 DI MAPLE CREEK-HOOPA 11/4A CNCL | EUREKA | ETL.7490.POLE.WOOD | 2021-07-20 | 2021-07-19 |  | 2022-01-15 | 2022-01-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548069 | T3 DI MAPLE CREEK-HOOPA 11/4A RPL STRW | 70Y
LC | 121762097 | 089/006 | T2 DI HUMBOLDT-TRINITY 89/6 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-07-20 | 2021-07-19 |  | 2022-07-19 | 2022-07-19 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31542140 | T2 EI HUMBOLDT-TRINITY 89/9 RPL INSW | 93I
LC | 121762994 | 004/050A | T2 DI PT #1-HT CRK #2-BRY 4/50A REFRAME | TABLEMTN | ETL.7040.INSL.NCER | 2021-07-20 | 2021-07-19 |  | 2022-07-19 | 2022-07-19 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31548070 | T2 DI PT #1-HT CRK #2-BRY 4/50A REFRAME | 93E
LC | 121763077 | 013/124 | T3 DI DRUM-HIGGINS 013/124 GRD WAS INSU | SACTO | ETL.4393.INSL.CERA | 2021-07-20 | 2021-07-19 |  | 2022-01-15 | 2022-01-19 | Late | 622 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | Contaminated | Insulator | Ground Wash | 45219474 | T3 DI DRUM-HIGGINS 013/124 GRD WAS INSU | ICD
LC | 121763132 | 011/003 | T2 DI MELONES-CURTIS 11/3C RPR GYWW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-20 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45164451 | T2 DI MELONES-CURTIS 11/3C RPR GYWW | ICW
LC | 121763135 | 011/003 | T2 DI MELONES-CURTIS 11/3R RPR GYWW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-20 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OH TR2 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45164452 | T2 DI MELONES-CURTIS 11/3R RPR GYWW | ICW
LC | 121763370 | 011/003 | T2 CARIBOU #2 11/003 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2021-07-20 | 2021-07-20 |  | 2022-07-20 | 2022-07-20 | Late | 437 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW NONR OH FMOB TR2 PRTO FRAB | Fire | Emergency | Replace | 31546790 | T2 CARIBOU #2 11/003 RPL POLE | 92F
LC | 121763664 | T049 | T3 DI MIDWAY-SANTA MARIA T49 RPL SPLS | PISMOBCH | ETL.9240.TOWR | 2021-07-20 | 2021-07-19 |  | 2022-01-15 | 2022-01-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Replace | 45193626 | T3 DI MIDWAY-SANTA MARIA T49 RPL SPLS | ICS
LC | 121763694 | T050 | T3 DI MIDWAY-SANTA MARIA T50 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-20 | 2021-07-19 |  | 2022-01-15 | 2022-01-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31629631 | T3 DI MIDWAY-SANTA MARIA T50 RPR SPLS | 93K
LC | 121763733 | T050 | T3 DI MIDWAY-SANTA MARIA T50 BENT STEEL | PISMOBCH | ETL.9240.TOWR | 2021-07-20 | 2021-07-19 |  | 2022-01-15 | 2022-01-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45098906 | T3 DI MIDWAY-SANTA MARIA T50 BENT STEEL | ICQ
LC | 121764616 | 013/007 | T2 DI MELONES-CURTIS 13/7R RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-20 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579809 | T2 DI MELONES-CURTIS 13/7L RPL STRW | 70Y
LC | 121766658 | T-104 | T3 DI MIDWAY-SANTA MARIA T-104 RPR STRW | PISMOBCH | ETL.9240.POLE.WOOD | 2021-07-21 | 2021-07-19 |  | 2022-01-15 | 2022-01-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 44938271 | T3 DI MIDWAY-SANTA MARIA T-104 RPR STRW | ICW
LC | 121767138 | T052 | T3 DI MIDWAY-SANTA MARIA T052 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-21 | 2021-07-19 |  | 2022-01-15 | 2022-01-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548616 | T3 DI MIDWAY-SANTA MARIA RPL INSS 7TWRS | 93K
LC | 121768114 | 006/004 | T2 DI MELONES-CURTIS 6/4L RPL POLE | VICTOR | ETL.2390.POLE.WDPS | 2021-07-21 | 2021-07-20 |  | 2022-07-20 | 2022-07-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31602711 | T2 DI MELONES-CURTIS 6/4R RPL POLE | 70Y
LC | 121768116 | 006/004 | T2 DI MELONES-CURTIS 6/4R RPL POLE | VICTOR | ETL.2390.POLE.WDPS | 2021-07-21 | 2021-07-20 |  | 2022-07-20 | 2022-07-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31602711 | T2 DI MELONES-CURTIS 6/4R RPL POLE | 70Y
LC | 121768968 | 006/002 | T2 DI MELONES-CURTIS 006/002 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-21 | 2021-07-20 |  | 2022-07-20 | 2022-07-20 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579812 | T2 DI MELONES-CURTIS 007/004 RPL INSW | 93I
LC | 121770086 | 007/004 | T2 DI MELONES-CURTIS 007/004 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-21 | 2021-07-19 |  | 2022-07-19 | 2022-07-19 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579812 | T2 DI MELONES-CURTIS 007/004 RPL INSW | 93I
LC | 121770596 | 005/005 | T2 DI MELONES-CURTIS 005/005 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-21 | 2021-07-20 |  | 2022-07-20 | 2022-07-20 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579812 | T2 DI MELONES-CURTIS 007/004 RPL INSW | 93I
LC | 121771023 | 011/005 | T2 DI MELONES-CURTIS 011/005 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-21 | 2021-07-20 |  | 2022-07-20 | 2022-07-20 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579810 | T2 DI MELONES-CURTIS 12/04 RPL INSW | 93I
LC | 121776648 | 011/004C | T3 DI MAPLE CREEK-HOOPA 11/4C CNCL | EUREKA | ETL.7490.POLE.WOOD | 2021-07-22 | 2021-07-19 |  | 2022-01-15 | 2022-01-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548069 | T3 DI MAPLE CREEK-HOOPA 11/4A RPL STRW | 70Y
LC | 121777875 | 001/023 | T2 DI NARROWS #1 TAP 001/023 RMV VEG | SACTO | ETL.6511.POLE.WDPS | 2021-07-22 | 2021-07-20 |  | 2022-07-20 | 2022-07-20 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | Overgrown | Vegetation | Remove
LC | 121780348 | 007/002 | T2 DI MELONES-CURTIS 007/002 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-22 | 2021-07-20 |  | 2022-07-20 | 2022-07-20 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579812 | T2 DI MELONES-CURTIS 007/004 RPL INSW | 93I
LC | 121780966 | T080 | T3 DI MIDWAY-SANTA MARIA T080 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-22 | 2021-07-22 |  | 2022-01-18 | 2022-01-22 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548618 | T3 DI MIDWAY-SANTA MARIA RPL INSS 6TWRS | 93K
LC | 121780968 | T063 | T3 DI MIDWAY-SANTA MARIA T063 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-22 | 2021-07-22 |  | 2022-01-18 | 2022-01-22 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548616 | T3 DI MIDWAY-SANTA MARIA RPL INSS 7TWRS | 93K
LC | 121781334 | T069 | T3 DI MIDWAY-SANTA MARIA T069 RPR INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-22 | 2021-07-22 |  | 2022-01-18 | 2022-01-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45193625 | T3 DI MIDWAY-SANTA MARIA T069 RPR INSS | ICS
LC | 121781448 | T044 | T3 DI MIDWAY-SANTA MARIA T44 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-19 |  | 2022-01-15 | 2022-01-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31596011 | T3 DI MIDWAY-SANTA MARIA RPL INSS | 93K
LC | 121781660 | 006/069 | T2 DI COLGATE-SMTVLLE #1 6/69 RMV VEG | SACTO | ETL.6510.POLE.WDPS | 2021-07-22 | 2021-07-20 |  | 2022-07-20 | 2022-07-20 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | Overgrown | Vegetation | Remove
LC | 121781661 | 004/000 | T3 DI DONNELLS-MI-WUK-WD 4/0 RPL INSW | VICTOR | ETL.1400.INSL.NCER | 2021-07-22 | 2021-07-21 |  | 2022-01-17 | 2022-01-21 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31577860 | T3 DI DONNELLS-MI-WUK 2/8 RPL INSW | 93I
LC | 121781725 | 006/003 | T2 DI MELNS-CRTS 6/03 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-22 | 2021-07-20 |  | 2022-07-20 | 2022-07-20 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579812 | T2 DI MELONES-CURTIS 007/004 RPL INSW | 93I
LC | 121781745 | 012/006 | T2 DI MELONES-CURTIS 012/006 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-07-22 | 2021-07-20 |  | 2022-07-20 | 2022-07-20 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31579810 | T2 DI MELONES-CURTIS 12/04 RPL INSW | 93I
LC | 121781809 | 004/003 | T2 DI MELONES-CURTIS 004/003 RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-22 | 2021-07-20 |  | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164546 | T2 DI MELONES-CURTIS 004/003 RPR STRW | ICW
LC | 121781810 | 004/003 | T2 DI MELONES-CURTIS 004/003 RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-22 | 2021-07-20 |  | 2022-07-20 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45164547 | T2 DI MELONES-CURTIS 004/003 RPR STRW | ICW
LC | 121782967 | T067 | T3 DI MIDWAY-SANTA MARIA T067 RPL HRDT | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 |  | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45098923 | T3 DI MIDWAY-SANTA MARIA T067 RPL HRDT | ICQ
LC | 121783045 | T096 | T3 DI MIDWAY-SANTA MARIA T096 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 |  | 2022-01-18 | 2022-01-22 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31596011 | T3 DI MIDWAY-SANTA MARIA RPL INSS | 93K
LC | 121783410 | 010/003 | T2 DI MELONES-CURTIS 010/003 RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-23 | 2021-07-20 |  | 2022-07-20 | 2022-07-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579811 | T2 DI MELONES-CURTIS 3/7 RPL STRW | 70Y
LC | 121783546 | 010/003 | T2 DI MELONES-CURTIS 010/003 RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-23 | 2021-07-20 |  | 2022-07-20 | 2022-07-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579811 | T2 DI MELONES-CURTIS 3/7 RPL STRW | 70Y
LC | 121785168 | T065 | T3 DI MIDWAY-SANTA MARIA INST HRDT | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 |  | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | Missing | Hardware-Tower | Install | 45098927 | T3 DI MIDWAY-SANTA MARIA INST HRDT | ICQ
LC | 121786403 | T094 | T3 DI MIDWY-SNTA MARA(12KV)T094 RPR INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 |  | 2022-01-18 | 2022-01-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45193623 | T3 DI MIDWY-SNTA MARA(12KV)T094 RPR INSS | ICS
LC | 121786408 | T090 | T3 DI MIDWY-SNTA MARA(12KV)T090 RPR CONS | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-23 |  | 2022-01-19 | 2022-01-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45193620 | T3 DI MIDWY-SNTA MARA(12KV)T090 RPR CONS | ICS
LC | 121786873 | T088 | T3 DI MIDWAY-SANTA MARIA T088 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 |  | 2022-01-18 | 2022-01-22 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548618 | T3 DI MIDWAY-SANTA MARIA RPL INSS 6TWRS | 93K
LC | 121787066 | T066 | T3 DI MIDWAY-SNTA MRIA T66 RPR STRT | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 |  | 2022-01-18 | 2022-01-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45098932 | T3 DI MIDWAY-SANTA MARIA T066 RPR STRT | ICQ
LC | 121787201 | T066 | T3 DI MIDWAY-SANTA MARIA T066 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-23 | 2021-07-22 |  | 2022-01-18 | 2022-01-22 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548616 | T3 DI MIDWAY-SANTA MARIA RPL INSS 7TWRS | 93K
LC | 121789710 | 003/008 | T3 DI DONNELLS-MI-WUK 3/8 RPL INSW | VICTOR | ETL.1400.INSL.NCER | 2021-07-24 | 2021-07-19 |  | 2022-01-15 | 2022-01-19 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31577860 | T3 DI DONNELLS-MI-WUK 2/8 RPL INSW | 93I
LC | 121790220 | T-119 | T3 DI MDWY-SNTA MARIA T-119 RPL INS | PISMOBCH | ETL.9240.TOWR | 2021-07-24 | 2021-07-24 |  | 2022-01-20 | 2022-01-24 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31599759 | T3 DI MDWY-SNTA MARIA T-119 RPL INS | 93K
LC | 121790221 | T-119 | T3 DI MIDWAY-SANTA MARIA T-119 INS STEP | PISMOBCH | ETL.9240.TOWR | 2021-07-24 | 2021-07-24 |  | 2022-01-20 | 2022-01-24 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | Missing | Hardware-Tower | Install | 45098936 | T3 DI MIDWAY-SANTA MARIA T-119 INS STEP | ICQ
LC | 121791093 | 063/000 | T2 DI GRBRVIL-LAYTONVILLE 63/0 RPR INSW | WILLITS | ETL.8365.INSL.NCER | 2021-07-24 | 2021-07-24 |  | 2022-07-24 | 2022-07-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45429599 | T2 DI GRBRVIL-LAYTONVILLE 63/0 RPR INSW | ICW
LC | 121792771 | 008/208 | T3 DI DRM GRSS VLLY WMR 8/208 RPL HRDD | SACTO | ETL.6760.POLE.WOOD | 2021-07-25 | 2021-07-23 |  | 2022-01-19 | 2022-01-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR ACCH OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45193643 | T3 DI DRM GRSS VLLY WMR 8/208 RPL HRDD | ICW
LC | 121796771 | T-113 | T3 DI MIDWAY-SANTA MARIA T-113 INS STEP | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 |  | 2022-01-22 | 2022-01-26 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | Missing | Hardware-Tower | Install | 45098950 | T3 DI MIDWAY-SANTA MARIA T-113 INS STEP | ICQ
LC | 121797380 | T-122 | T3 DI MIDWAY-SANTA MARIA T-122 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 |  | 2022-01-22 | 2022-01-26 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31548619 | T3 EI MIDWAY-SANTA MARIA RPL INSS 8TWRS | 93K
LC | 121798219 | T-121 | T3 DI MIDWAY-SANTA MARIA T-121 INS HRDT | PISMOBCH | ETL.9240.TOWR | 2021-07-26 | 2021-07-26 |  | 2022-01-22 | 2022-01-26 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | Missing | Hardware-Tower | Install | 45098956 | T3 DI MIDWAY-SANTA MARIA T-121 INS HRDT | ICQ
LC | 121800504 | 014/000 | T2 DI HMBLDT BY-RIO DEL JT 14/0 RPR GYWW | EUREKA | ETL.7100.POLE.WOOD | 2021-07-26 | 2021-07-26 |  | 2022-07-26 | 2022-07-26 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OH TR2 PRTO AIR FRAB NTDE SR22 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45128374 | T2 DI HMBLDT BY RIO DLL JT 14/0 RPR GYWW | ICS
LC | 121800591 | 006/005 | T3 DI FULTON-CALISTOGA 006/5L RPL HRDD | LAKEVLLE | ETL.6880.POLE.STPS | 2021-07-26 | 2021-07-26 |  | 2022-01-22 | 2022-07-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45149821 | T3 DI FULTON-CALISTOGA 006/5L RPL HRDD | ICW
LC | 121802836 | 010/011A | T3 DI MAPLE CREEK-HOOPA 10/11A RPL STRW | EUREKA | ETL.7490.POLE.WOOD | 2021-07-27 | 2021-07-26 |  | 2022-01-22 | 2022-01-26 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31548069 | T3 DI MAPLE CREEK-HOOPA 11/4A RPL STRW | 70Y
LC | 121803407 | 019/080 | T3 DI MNT VST-JFFRSN #2 19/80 RPL INSS | METCALF | ETL.5230.INSL | 2021-07-27 | 2021-07-26 |  | 2022-01-22 | 2022-01-26 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31542277 | T3 EI MONT VIST-JEFRSN #2 RPL INSS 2TWR | 93K
LC | 121805020 | 007/003 | T2 EI PHILO JCT-ELK 7/3 RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2021-07-27 | 2021-07-27 |  | 2022-07-27 | 2022-07-27 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW CREW OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31541324 | T2 PHILO JCT-ELK 05/000 RPL PL | 70Y
LC | 121806511 | 010/011B | T3 DI MAPLE CREEK-HOOPA 10/11B RPL STRW | EUREKA | ETL.7490.POLE.WOOD | 2021-07-28 | 2021-07-26 |  | 2022-01-22 | 2022-01-26 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31548069 | T3 DI MAPLE CREEK-HOOPA 11/4A RPL STRW | 70Y
LC | 121806560 | 003/007 | T2 DI MELONES-CURTIS 3/7R RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-28 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579811 | T2 DI MELONES-CURTIS 3/7 RPL STRW | 70Y
LC | 121806581 | 003/007 | T2 DI MELONES-CURTIS 3/7C RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-28 | 2021-07-13 |  | 2022-07-13 | 2022-07-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31579811 | T2 DI MELONES-CURTIS 3/7 RPL STRW | 70Y
LC | 121808164 | 003/002 | T2 DI MELONES-CURTIS 003/2L RPR GYWW | VICTOR | ETL.2390.POLE.WDPS | 2021-07-28 | 2021-07-26 |  | 2022-07-26 | 2022-07-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45164567 | T2 DI MELONES-CURTIS 003/2L RPR GYWW | ICW
LC | 121809947 | 025/117 | T3 DI FULTON-PUEBLO 25/117 RMV FENCE | LAKEVLLE | ETL.1600.TOWR | 2021-07-28 | 2021-07-27 |  | 2022-01-23 | 2022-01-27 | Late | 931 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Encroachment | Right of Way | Remove
LC | 121810317 | 013/008 | T2 DI HMBLDT BY-RIO DL JT 017/3 RPR STRW | EUREKA | ETL.7100.POLE.WOOD | 2021-07-28 | 2021-07-28 |  | 2022-07-28 | 2022-07-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Repair | 45128373 | T2 DI HMBLDT BY RIO DL JT 017/3 RPR STRW | ICW
LC | 121810498 | 003/010 | T2 DI LAYTONVILLE-COVELO 3/10 RPL STRW | WILLITS | ETL.7390.POLE.WOOD | 2021-07-28 | 2021-07-27 |  | 2022-07-27 | 2022-07-27 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31544833 | T2 DI LAYTONVILLE-COVELO 5/2L RPL STRW | 70Y
LC | 121810588 | 025/369 | T3 DI GOLD HILL #1 025/369 INS IBWW | SACTO | ETL.6950.INSL.CERA | 2021-07-28 | 2021-07-28 |  | 2022-01-24 | 2022-01-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Replace | 45218209 | T3 DI GOLD HILL #1 025/369 INS IBWW | ICW
LC | 121812010 | 015/347 | T2 DI DRM-GRSS VLLY-WMR 15/347 RPR SPLW | SACTO | ETL.6760.INSL.NCER | 2021-07-29 | 2021-07-26 |  | 2022-07-26 | 2022-07-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45218815 | T2 DI DRM-GRSS VLLY-WMR 15/347 RPR SPLW | ICW
LC | 121813105 | 025/008 | T3NT DI MAPLE CREEK-HOOPA 25/8 RPR GWRW | EUREKA | ETL.7490.POLE.STPS | 2021-07-29 | 2021-07-27 |  | 2022-01-23 | 2022-01-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3N PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 44958431 | T3NT DI MAPLE CREEK-HOOPA 25/8 RPR GWRW | ICW
LC | 121813210 | 025/008 | T3 DI MAPLE CREEK-HOOPA 25/8 RPL SPLW | EUREKA | ETL.7490.INSL.NCER | 2021-07-29 | 2021-07-27 |  | 2022-01-23 | 2022-01-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Replace | 45010820 | T3 DI MAPLE CREEK-HOOPA 25/8 RPL SPLW | ICW
LC | 121813727 | 025/204 | T2 WV CRBRY SW ST-RND MTN 25/204 RPL ARM | TABLEMTN | ETL.5410.TOWR | 2021-07-29 | 2021-07-29 |  | 2022-07-29 | 2022-07-29 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45213665 | T2 WV CRBRY SW ST-RND MTN 25/204 RPL ARM | ICS
LC | 121814425 | 004/003 | T2 WV HUMBOLDT-MAPLE CREEK 4/3 RPL POLE | EUREKA | ETL.7130.POLE.WOOD | 2021-07-29 | 2021-07-29 |  | 2022-07-29 | 2022-07-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548703 | T2 WV HUMBOLDT-MAPLE CREEK 4/3 RPL POLE | 70Y
LC | 121815346 | 000/006 | T2 WV FULTON-CALISTOGA 0/6 REFRAME | LAKEVLLE | ETL.6880.POLE.WOOD | 2021-07-29 | 2021-07-29 |  | 2022-07-29 | 2022-07-29 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW OTHR OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31546523 | T2 FULTON-CALISTOGA -00/006 RPL CRSMW | 93E
LC | 121815413 | 013/107C | T3 DI MIDLE FRK-GLD HIL 13/107C RPR GYWS | SACTO | ETL.5140.POLE.NWOD | 2021-07-29 | 2021-07-29 |  | 2022-01-25 | 2022-01-29 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45568277 | T3 DI MIDLE FRK-GLD HIL 13/107C RPR GYWS | ICS
LC | 121816147 | 001/003 | T2 DI MELONES-CURTIS 1/3 RPL X-BRACE | VICTOR | ETL.2390.POLE.WDPS | 2021-07-29 | 2021-07-28 |  | 2022-07-28 | 2022-07-28 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OH TR2 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31579813 | T2 DI MELONES-CURTIS 012/009 RPL CRSW | 93E
LC | 121816429 | 013/107B | T3 DI MID FORK-GLD HILL 13/107B INS GYWS | SACTO | ETL.5140.POLE.NWOD | 2021-07-29 | 2021-07-29 |  | 2022-01-25 | 2022-01-29 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | Missing | Guy Wire-Steel | Install | 45568286 | T3 DI MID FORK-GLD HILL 13/107B INS GYWS | ICS
LC | 121818692 | 015/347 | T2 DI DRUM-GRAS VLY-WEMR 15/347 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-07-30 | 2021-07-28 |  | 2022-07-28 | 2022-07-28 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE ACCM OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31591950 | T2 DI DRUM-GRAS VLY-WEMR 15/347 RPL STRW | 70Y
LC | 121819466 | 020/084 | T3 DIABLO-GATES #1 020/084 RPL SHLS INSS | PISMOBCH | ETL.5960.TOWR | 2021-07-30 | 2021-07-30 |  | 2022-01-26 | 2022-01-30 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 45193192 | T3 DIABLO-GATES #1 020/084 RPL SHLS | ICS
LC | 121821868 | 003/010 | T3 GRIZZLY TAP 003/010L RPL POLE | TABLEMTN | ETL.2395.POLE.WDPS | 2021-07-30 | 2021-07-30 |  | 2022-01-26 | 2022-01-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO | Fire | Emergency | Replace
LC | 121822003 | 003/016A | T3 GRIZZLY TAP 003/016A RPL POLE | TABLEMTN | ETL.2395.POLE.WOOD | 2021-07-30 | 2021-07-30 |  | 2022-01-26 | 2022-01-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO FRAB | Fire | Emergency | Replace
LC | 121822010 | 003/016B | T3 GRIZZLY TAP 003/016B RPL POLE | TABLEMTN | ETL.2395.POLE.WOOD | 2021-07-30 | 2021-07-30 |  | 2022-01-26 | 2022-01-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO FRAB | Fire | Emergency | Replace
LC | 121822011 | 003/016C | T3 GRIZZLY TAP 003/016C RPL POLE | TABLEMTN | ETL.2395.POLE.WOOD | 2021-07-30 | 2021-07-30 |  | 2022-01-26 | 2022-01-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO FRAB | Fire | Emergency | Replace
LC | 121822543 | 000/003 | T2 DI PIT #3-PIT #1 000/003 RPL HRDS | TABLEMTN | ETL.5400.POLE.STPS | 2021-07-30 | 2021-07-29 |  | 2022-07-29 | 2022-07-29 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45213887 | T2 DI PIT #3-PIT #1 000/003 RPL HRDS | ICS
LC | 121824405 | 003/010 | T3 GRIZZLY TAP 003/010R RPL POLE | TABLEMTN | ETL.2395.POLE.WDPS | 2021-07-31 | 2021-07-30 |  | 2022-01-26 | 2022-01-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR OH FMOB TR3 PRTO | Fire | Emergency | Replace
LC | 121824407 | 003/010 | T3 GRIZZLY TAP 003/010C RPL POLE | TABLEMTN | ETL.2395.POLE.WDPS | 2021-07-31 | 2021-07-30 |  | 2022-01-26 | 2022-01-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 121824800 | B016/381 | T3 DI DRM GRSS VLY WMR B016/381 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2021-07-31 | 2021-07-31 |  | 2022-01-27 | 2022-01-31 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548673 | T3 DI DRM GRSS VLY WMR B016/381 RPL STRW | 70Y
LC | 121829484 | 045/005 | T2 EI TRINITY-MAPLE CREEK 45/5 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2021-08-02 | 2021-07-31 |  | 2022-07-31 | 2022-07-31 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP NONR OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31548880 | T2 EI TRINITY-MAPLE CREEK 45/5 RPL POLE | 70Y
LC | 121838465 | 003/081 | T2 PLACER-DEL MAR 3/081 RPL STW | SACTO | ETL.7800.POLE.WOOD | 2021-08-03 | 2021-08-03 |  | 2022-08-03 | 2022-08-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW NONR OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31548884 | T2 PLACER-DEL MAR 3/081 RPL STRW | 70Y
LC | 121841063 | 033/004 | T2 DI TRINITY-MAPLE CREEK 33/4L RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2021-08-04 | 2021-08-04 |  | 2022-08-04 | 2022-08-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31471998 | TRINITY-MAPLE CREEK | 70Y
LC | 121841068 | 033/004 | T2 DI TRINITY-MAPLE CREEK 33/4R RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2021-08-04 | 2021-08-04 |  | 2022-08-04 | 2022-08-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31471998 | TRINITY-MAPLE CREEK | 70Y
LC | 121841112 | 033/004 | T2 DI TRINITY-MAPLE CREEK 33/4C RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2021-08-04 | 2021-08-04 |  | 2022-08-04 | 2022-08-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW OTHR FIRE OH TR2 PRTO AIR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31471998 | TRINITY-MAPLE CREEK | 70Y
LC | 121841430 | 004/085 | T2 WEIMAR-HALSEY 4/085 RMV VEG | SACTO | ETL.8340.POLE.NWOD | 2021-08-04 | 2021-08-04 |  | 2022-08-04 | 2022-08-04 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW NONR OH FMOB TR2 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 121862694 | 002/069 | T2 VOLTA-SOUTH 2/69 RPL STRW CMPLT | TABLEMTN | ETL.8300.POLE.WOOD | 2021-08-09 | 2021-07-24 |  | 2022-07-24 | 2022-07-24 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR COMP OH TR2 PRTO FRAB NTDE | Rotten | Structure-Wood | Replace | 31575747 | T2 VOLTA-SOUTH 2/69 RPL STRW | 70Y
LC | 121863981 | 052/004 | T2 WV HUMBOLDT-TRINITY 52/4 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2021-08-09 | 2021-08-09 |  | 2022-08-09 | 2022-08-09 | Late | 437 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO NTDE | Fire | Emergency | Replace | 31549273 | T2 WV HMBLDT-TRNITY 52/4 RPL INSW | 92F
LC | 121864608 | 003/057 | T3 WV CNTRVLL-TBL MTN 3/57 RPL CNDS | TABLEMTN | ETL.6320.POLE.NWOD | 2021-08-09 | 2021-08-09 |  | 2022-02-05 | 2022-02-09 | Late | 531 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW CREW OH RTNR FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Conductor-Steel | Replace | 31550824 | T3 WV CNTRVLL-TBL MTN 3/57 RPL CNDS | 93C
LC | 121864718 | 026/211 | T2 WV CRBRY RND MTN 26/211 INS ARMR | TABLEMTN | ETL.5410.INSL.NCER | 2021-08-09 | 2021-08-09 |  | 2022-08-09 | 2022-08-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45213663 | T2 WV CRBRY RND MTN 26/211 INS ARMR | ICS
LC | 121879692 | 001/019 | T2 EI IGNACIO-BOLINAS #1 1/19 RPL STRW | LAKEVLLE | ETL.7140.POLE.WOOD | 2021-08-10 | 2021-08-10 |  | 2022-08-10 | 2022-08-10 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW INSP OTHR FIRE COMP OH TR2 PRTO AIR FRAR SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31548704 | T2 DI IGNACIO-BLNS #1 001/022 RPL STRW | 70Y
LC | 121916901 | 000/005 | T2 EI TOCALOMA TAP 0/5R RPL STRW | LAKEVLLE | ETL.7721.POLE.WDPS | 2021-08-18 | 2021-06-16 |  | 2022-06-16 | 2022-06-16 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW INSP OH FMOB TR2 PRTO | Rotten | Structure-Wood | Replace | 31544425 | T2 EI TOCALOMA TAP 0/5L RPL STRW | 70Y
LC | 121921863 | 016/007 | T2 TRINITY-MAPLE CREEK 16/7 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-19 | 2021-08-19 |  | 2022-08-19 | 2022-08-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW NONR OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31557253 | T2 TRINITY-MAPLE CREEK 14/6 RPL POLE | 70Y
LC | 121921904 | 017/008 | T2 TRINITY-MAPLE CREEK 17/8 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-19 | 2021-08-19 |  | 2022-08-19 | 2022-08-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW NONR OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31557253 | T2 TRINITY-MAPLE CREEK 14/6 RPL POLE | 70Y
LC | 121921955 | 018/000 | T2 TRINITY-MAPLE CREEK 18/0 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-19 | 2021-08-19 |  | 2022-08-19 | 2022-08-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW NONR OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31557253 | T2 TRINITY-MAPLE CREEK 14/6 RPL POLE | 70Y
LC | 121929046 | 014/298 | T2 SALINAS-LAURELES 014/298 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2021-08-20 | 2021-08-20 |  | 2022-08-20 | 2022-08-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW CREW OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31505565 | T2 DI SALINAS-LAURELES 14/298 RPLC POLE | 70Y
LC | 121934473 | 019/004 | T2 TRINITY-MAPLE CREEK 19/4 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2021-08-22 | 2021-08-22 |  | 2022-08-22 | 2022-08-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW NONR OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31557253 | T2 TRINITY-MAPLE CREEK 14/6 RPL POLE | 70Y
LC | 121934474 | 021/003 | T2 TRINITY-MAPLE CREEK 21/3 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2021-08-22 | 2021-08-22 |  | 2022-08-22 | 2022-08-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW NONR OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31557255 | T2 TRINITY-MAPLE CRK 20/3C RPL POLE | 70Y
LC | 121934475 | 024/002 | T2 TRINITY-MAPLE CREEK 24/2 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2021-08-22 | 2021-08-22 |  | 2022-08-22 | 2022-08-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW NONR OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31557255 | T2 TRINITY-MAPLE CRK 20/3C RPL POLE | 70Y
LC | 121934477 | 067/002 | T2 HUMBOLDT-TRINITY 67/2L RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-08-22 | 2021-08-22 |  | 2022-08-22 | 2022-08-22 | Late | 437 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW NONR OH FMOB TR2 PRTO NTDE | Fire | Emergency | Replace | 31578175 | T2 HMBLDT-TRINITY 67/2L RPL POLE | 92F
LC | 121934553 | 020/003 | T2 TRINITY-MAPLE CRK 20/3 RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2021-08-22 | 2021-08-22 |  | 2022-08-22 | 2022-08-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW NONR OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31557255 | T2 TRINITY-MAPLE CRK 20/3C RPL POLE | 70Y
LC | 121938697 | 000/009 | T2 EI VIEJO-MONTEREY 000/009 RPR GYWW | MOSSLNDG | ETL.8270.POLE.WOOD | 2021-08-23 | 2021-08-23 |  | 2022-08-23 | 2022-08-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB SR22 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45225165 | T2 EI VIEJO-MONTEREY 000/009 RPR GYWW | ICW
LC | 121939324 | 066/001 | T2 EI HUMBOLDT-TRINITY 66/1 RPL SPLW | EUREKA | ETL.1820.INSL.CERA | 2021-08-23 | 2021-08-23 |  | 2022-08-23 | 2022-08-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Replace | 44957753 | T2 EI HUMBOLDT-TRINITY 066/001 RPL SPLW | ICW
LC | 121940286 | 020/003 | T2 TRINITY-MAPLE CREEK 20/3R RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2021-08-23 | 2021-08-22 |  | 2022-08-22 | 2022-08-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW NONR OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31557255 | T2 TRINITY-MAPLE CRK 20/3C RPL POLE | 70Y
LC | 121940289 | 020/003 | T2 TRINITY-MAPLE CREEK 20/3C RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2021-08-23 | 2021-08-22 |  | 2022-08-22 | 2022-08-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW NONR OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31557255 | T2 TRINITY-MAPLE CRK 20/3C RPL POLE | 70Y
LC | 121940334 | 067/002 | T2 HUMBOLDT-TRINITY 67/2R RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2021-08-23 | 2021-08-22 |  | 2022-08-22 | 2022-08-22 | Late | 437 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW NONR OH FMOB TR2 PRTO NTDE | Fire | Emergency | Replace | 31578175 | T2 HMBLDT-TRINITY 67/2L RPL POLE | 92F
LC | 121949870 | 014/006 | T2 TRINITY-MAPLE CREEK 14/6 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2021-08-24 | 2021-08-24 |  | 2022-08-24 | 2022-08-24 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW CREW COMP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31557253 | T2 TRINITY-MAPLE CREEK 14/6 RPL POLE | 70Y
LC | 121957077 | A008/162 | T2 EI CASCADE-BENT-DESC A8/162 RPL POLE | TABLEMTN | ETL.6310.POLE.WOOD | 2021-08-25 | 2021-08-25 |  | 2022-08-25 | 2022-08-25 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW CREW OH FMOB TR2 PRTO FRAB | Rotten | Structure-Wood | Replace | 31427802 | T2 EI CSCDE-BNTN-DSCHTS A006/125 RPL PL | 70Y
LC | 121966943 | 002/037 | T3 WV KSWCK-TRNTY 2/37 RPL POLE CMLT | TABLEMTN | ETL.7270.POLE.WOOD | 2021-08-27 | 2021-08-27 |  | 2022-02-23 | 2022-02-27 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW CREW COMP OH FMOB TR3 PRTO FRAB NTDE | Rotten | Structure-Wood | Replace | 31547341 | T3 WV KSWCK-TRNTY 2/37 RPL POLE | 70Y
LC | 121972583 | 018/000 | T2 HMBLDT BAY-RIO DELL JCT 18/0 RPL ANCW | EUREKA | ETL.7100.POLE.WOOD | 2021-08-30 | 2021-08-30 |  | 2022-08-30 | 2022-08-30 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW OTHR OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31589213 | T2 DI HMBLDT BY-RIO DL JCT 16/9 RPL ANCW | 93E
LC | 121978973 | 012/001 | T2 MELONES-CURTIS 12/001 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2021-08-31 | 2021-08-31 |  | 2022-08-31 | 2022-08-31 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31578767 | T2 MELONES-CURTIS 12/001 RPL INSW | 93I
LC | 121982790 | :004/004 | T2 WV BLT-RVBK-MLNS SW ST :4/4 RPL STRW | VICTOR | ETL.1070.POLE.WOOD | 2021-09-01 | 2021-09-01 |  | 2022-09-01 | 2022-09-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31597946 | T2 WV BLT-RVBK-MLNS SW ST :4/4 RPL STRW | 70Y
LC | 122018042 | 036/004 | T2 WV TRINITY-MAPLE CREEK 36/4 RPR COND | EUREKA | ETL.8170.INSL | 2021-09-09 | 2021-09-09 |  | 2022-09-09 | 2022-09-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR COMP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair | 45155494 | T2 WV TRINITY-MAPLE CREEK 36/4 RPR COND | ICW
LC | 122018646 | 012/005 | T2 WV TRINITY-MAPLE CREEK 12/5 RPR PL | EUREKA | ETL.8170.POLE.WOOD | 2021-09-09 | 2021-09-09 |  | 2022-09-09 | 2022-09-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW OTHR OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 31471998 | TRINITY-MAPLE CREEK | 70Y
LC | 122019101 | 054/007 | T2 WV FORT ROSS-GUALALA 54/7 INST DMPER | LAKEVLLE | ETL.6980.POLE.WOOD | 2021-09-09 | 2021-09-09 |  | 2022-09-09 | 2022-09-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO FRAB NTDE | Missing | Damper-Wood | Install | 45143068 | T2 WV FORT ROSS-GUALALA 54/7 INST DMPER | ICW
LC | 122044952 | 019/008 | T2 TULE-SPRINGVILLE 019/008 RPR FENCE | MIDWAY | ETL.9040.POLE.NWOD | 2021-09-13 | 2021-09-13 |  | 2022-09-13 | 2022-09-13 | Late | 931 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW CREW OH FMOB TR2 PRTO FRAB NTDE | Encroachment | Right of Way | Remove
LC | 122055207 | 003/013 | T3 GEYSERS #9-LAKEVILE 3/13 RPL INSS COA | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-15 | 2021-09-15 |  | 2022-03-14 | 2022-03-15 | Late | 437 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122063985 | 031/136 | T3 GEYSERS #9-LAKEVILLE 031/136 COMPLETE | LAKEVLLE | ETL.4780.INSL | 2021-09-17 | 2021-09-17 |  | 2022-03-16 | 2022-03-17 | Late | 437 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO NTDE | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122095313 | 012/052 | T3 GEYSERS #9-LAKEVILLE 12/52 COMPLETE | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-24 | 2021-09-24 |  | 2022-03-23 | 2022-03-24 | Late | 437 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122095365 | 017/073 | T3 GEYSERS #9-LAKEVILLE 17/73 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2021-09-24 | 2021-09-24 |  | 2022-03-23 | 2022-03-24 | Late | 437 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122095465 | 002/011 | T3 GEYSERS #9-LAKEVILLE 2/11 RPL INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2021-09-24 | 2021-09-24 |  | 2022-03-23 | 2022-03-24 | Late | 437 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO | Fire | Emergency | Replace | 31515180 | 10/03/20 GLASS FIRE-SONOMA CO. (POST) | 92F
LC | 122113342 | 019/011 | T2 WV TRINITY-MAPLE CRK 19/11 INS GYWW | EUREKA | ETL.8170.POLE.NWOD | 2021-09-28 | 2021-09-28 |  | 2022-09-28 | 2022-09-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OTHR OH FMOB TR2 PRTO FRAB NTDE SR22 | Missing | Guy Wire-Wood | Install | 45160751 | T2 EI TRINITY-MPLE CRK 19/011 INS GYWW | ICW
LC | 122145521 | :008/000 | T3 WV FLTN-CLISTOGA :8/0 INS DMPRW | LAKEVLLE | ETL.6880.INSL.NCER | 2021-10-04 | 2021-10-04 |  | 2022-04-02 | 2022-04-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO | Missing | Damper-Wood | Install | 45144059 | T3 WV FLTN-CLISTOGA :8/0 INS DMPRW | ICW
LC | 122161690 | 035/176 | T3 EAGLE RK-FLT-SV 35/176 RPL INSS CMPLT | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 |  | 2022-04-05 | 2022-04-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO NTDE | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122161726 | 035/177 | T3 EGL RCK-FLTN-SLV 35/177 RPL INS CMPLT | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 |  | 2022-04-05 | 2022-04-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO NTDE | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122161752 | 036/180 | T3 EAGLE ROCK-FLTN-SILVR 36/180 COMPLETE | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 |  | 2022-04-05 | 2022-04-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO NTDE | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122161792 | 036/183 | T3 EGLE RCK-FLN-SLVR 36/183 RPL INSS COA | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 |  | 2022-04-05 | 2022-04-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122161827 | 036/184 | T3 EAGLE RK-FLTN-SLR 36/184 RPL INSS COA | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 |  | 2022-04-05 | 2022-04-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122161949 | 037/190 | T3 EAGLE ROCK-FLTN-SILVR 37/190 COMPLETE | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 |  | 2022-04-05 | 2022-04-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122162001 | 037/191 | T2 EAGLE ROCK-FLTN-SILVR 37/191 RPL INSS | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 |  | 2022-10-07 | 2022-10-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW OTHR OH FMOB TR2 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122162074 | 037/191A | T3 EAGLE RCK-FLTN-SILVR 37/191A RPL INSS | LAKEVLLE | ETL.4392.SWIT | 2021-10-07 | 2021-10-07 |  | 2022-04-05 | 2022-04-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122162106 | 038/193 | T2 EAGLE ROCK-FLTN-SILVR 38/193 RPL INSS | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 |  | 2022-10-07 | 2022-10-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW OTHR OH FMOB TR2 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122162173 | 038/195 | T2 EAGLE ROCK-FLTN-SILVR 38/195 COMPLETE | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 |  | 2022-10-07 | 2022-10-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW OTHR OH FMOB TR2 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122162235 | 039/199 | T3 EAGL RCK-FTN-SLVR 39/199 RPL INSS COA | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 |  | 2022-04-05 | 2022-04-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122162615 | 039/200 | T3 EAGLE ROCK-FLTN-SILVR 39/200 COMPLETE | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 |  | 2022-04-05 | 2022-04-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122162814 | 040/206 | T3 EAGLE ROCK-FLTN-SILVR 40/206 RPL INSS | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 |  | 2022-04-05 | 2022-04-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122163234 | 041/212 | T3 EAGLE ROCK-FLTN-SILVR 41/212 COMPLETE | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 |  | 2022-04-05 | 2022-04-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR COMP OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122163273 | 041/213 | T3 EGLE RCK-FLTN-SLVR 41/213 RPL INS COA | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 |  | 2022-04-05 | 2022-04-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122163307 | 041/214 | T3 EGLE RCK-FLTN-SLVR 41/214 RPL INS COA | LAKEVLLE | ETL.4392.INSL.NCER | 2021-10-07 | 2021-10-07 |  | 2022-04-05 | 2022-04-07 | Late | 505 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO | Storm Related | Emergency | Replace | 31515212 | DI EGL RCK-FLTN-SLVRD RPLC INS IN 15 TWR | 92E
LC | 122186113 | 010/012 | T3 EI MAPLE CREEK-HOOPA 10/12R CNCL | EUREKA | ETL.7490.POLE.WDPS | 2021-10-11 | 2021-10-11 |  | 2022-04-09 | 2022-10-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31554570 | T3 EI MAPLE CREEK-HPA 11/3 RPL STRW | 70Y
LC | 122186114 | 011/003 | T3 EI MAPLE CREEK-HOOPA 11/3R RPL STRW | EUREKA | ETL.7490.POLE.WDPS | 2021-10-11 | 2021-10-11 |  | 2022-04-09 | 2022-04-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31554570 | T3 EI MAPLE CREEK-HPA 11/3 RPL STRW | 70Y
LC | 122192399 | 001/010 | T2 EI KANAKA TAP 001/010L RPL STRW CMPLT | TABLEMTN | ETL.4223.POLE.WDPS | 2021-10-12 | 2021-06-03 |  | 2022-06-03 | 2022-06-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31544831 | T2 EI KANAKA TAP 001/012B RPL STRW | 70Y
LC | 122193423 | 001/010 | T2 EI KANAKA TAP 001/010C RPL STRW CPLT | TABLEMTN | ETL.4223.POLE.WDPS | 2021-10-13 | 2021-06-03 |  | 2022-06-03 | 2022-06-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31544831 | T2 EI KANAKA TAP 001/012B RPL STRW | 70Y
LC | 122193424 | 001/010 | T2 EI KANAKA TAP 001/010R RPL STRW CMPT | TABLEMTN | ETL.4223.POLE.WDPS | 2021-10-13 | 2021-06-03 |  | 2022-06-03 | 2022-06-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW FIRE COMP OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31544831 | T2 EI KANAKA TAP 001/012B RPL STRW | 70Y
LC | 122227179 | 009/181 | T2 MONTA VISTA-LOS GATOS 9/181 RPR ANCR | METCALF | ETL.7610.POLE.WOOD | 2021-10-19 | 2021-10-19 |  | 2022-10-19 | 2022-10-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP COMP OH FMOB TR2 PRTO FRAR SR22 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45183881 | T2 MONTA VISTA-LOS GATOS 9/181 RPR ANCR | ICW
LC | 122229097 | Z013/006 | T3 DI FULTON-CALISTOGA :13/6 RPR GYWW | LAKEVLLE | ETL.6880.POLE.NWOD | 2021-10-19 | 2021-10-13 |  | 2022-04-11 | 2022-04-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45326373 | T3 DI FULTON-CALISTOGA :13/6 RPR GYWW | ICW
LC | 122233784 | 008/165 | T2 EI MONTA VISTA-LOS GTS 8/165 RPL HRDW | METCALF | ETL.7610.POLE.WOOD | 2021-10-20 | 2021-10-20 |  | 2022-10-20 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45183882 | T2 EI MONTA VISTA-LOS GTS 8/165 RPL HRDW | ICW
LC | 122241584 | :007/006 | T3 WV FULTON-CALSTGA :7/6 INS DAMW | LAKEVLLE | ETL.6880.POLE.NWOD | 2021-10-21 | 2021-10-21 |  | 2022-04-19 | 2022-04-21 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO FRAB NTDE | Missing | Damper-Steel | Install | 45262687 | T3 WV FULTON-CALSTGA :7/6 INS DAMW | ICS
LC | 122257695 | :008/002 | WV T3 FULTON-CALISTOGA :8/2 RPL DAMW | LAKEVLLE | ETL.6880.POLE.NWOD | 2021-10-26 | 2021-10-26 |  | 2022-04-24 | 2022-04-26 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO FRAB NTDE | Missing | Damper-Steel | Install | 45262688 | WV T3 FULTON-CALISTOGA :8/2 RPL DAMW | ICS
LC | 122277075 | 018/004 | T2 WV TRINITY-MAPLE CRK 18/4 INS GYWW | EUREKA | ETL.8170.POLE.NWOD | 2021-10-29 | 2021-10-29 |  | 2022-10-29 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO FRAB NTDE | Missing | Guy Wire-Wood | Install | 45155868 | T2 WV TRINITY-MAPLE CRK 18/4 INS GYWW | ICW
LC | 122279717 | 003/001 | T2 EI MELONES-CURTIS 3/1 RPR GYWW | VICTOR | ETL.2390.POLE.WDPS | 2021-10-31 | 2021-10-31 |  | 2022-10-31 | 2022-10-31 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW INSP OH FMOB TR2 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45167636 | T2 EI MELONES-CURTIS 3/1 RPR GYWW | ICW
LC | 122320225 | 013/107 | T3 CRESTA-RIO OSO 13/107 RPL INSS | TABLEMTN | ETL.4590.INSL.CERA | 2021-11-04 | 2021-11-04 |  | 2022-05-03 | 2022-05-04 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615914 | T2 EI CRESTA-RIO RPL INSS 10 STRTS | 93K
LC | 122320262 | 016/136 | T3 CRESTA-RIO OSO 16/136 RPL INSS | TABLEMTN | ETL.4590.INSL | 2021-11-04 | 2021-11-04 |  | 2022-05-03 | 2022-05-04 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615915 | T3 EI CRESTA-RIO OSO RPL INSS 10 STRTS | 93K
LC | 122320267 | 011/092 | T2 CRESTA-RIO OSO 11/092 RPL INSS | TABLEMTN | ETL.4590.INSL | 2021-11-04 | 2021-11-04 |  | 2022-11-04 | 2022-11-04 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW OTHR OH FMOB TR2 NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615914 | T2 EI CRESTA-RIO RPL INSS 10 STRTS | 93K
LC | 122343113 |  | T2 DI PIT #1-COTTONWOOD 12/97 RPR CNDS | TABLEMTN | ETL.5390.CDIF | 2021-11-09 | 2021-11-09 |  | 2022-11-09 | 2022-11-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW FIRE OH TR2 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45210819 | T2 DI PIT #1-COTTONWOOD 12/97 RPR CNDS | ICS
LC | 122408876 | T099 | WV T3 MIDWAY-SANTA MARIA T099 RPL HRDS | PISMOBCH | ETL.9240.TOWR | 2021-11-23 | 2021-11-23 |  | 2022-05-22 | 2022-05-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Hardware-Steel | Replace | 45193632 | WV T3 MIDWAY-SANTA MARIA T099 RPL HRDS | ICS
LC | 122427024 | 010/078C | T2 WV TRNTY-CTTNWD 010/078C COMPLETE | TABLEMTN | ETL.4040.POLE.WOOD | 2021-11-30 | 2021-11-30 |  | 2022-11-30 | 2022-11-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | REGW CREW COMP OH FMOB TR2 PRTO FRAB SR22 | No Good/Out of Stdrd | Structure-Wood | Replace | 31545105 | T2 EI TRNTY-CTNWD 10/078B RPL POLE | 70Y
LC | 122453989 | 026/216 | T2 CRESTA-RIO OSO 26/216 RPR INSS | TABLEMTN | ETL.4590.TOWR | 2021-12-07 | 2021-12-07 |  | 2022-12-07 | 2022-12-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR OH FMOB TR2 PRTO FRAB NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair | 45599145 | T2 CRESTA-RIO OSO 26/216 RPR INSS | ICS
LC | 122603881 | 005/135 | T3 DRUM-GRASS VALLEY-WMR 5/135 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2022-01-11 | 2022-01-11 |  | 2022-07-10 | 2022-07-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31590539 | T3 WV DRM-GRSS VLLY-WMR 5/134 RPL POLE | 70Y
LC | 122607288 | 005/134 | T3 WV DRM-GRSS VLLY-WMR 5/134 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2022-01-12 | 2022-01-12 |  | 2022-07-11 | 2022-07-12 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31590539 | T3 WV DRM-GRSS VLLY-WMR 5/134 RPL POLE | 70Y
LC | 122607348 | 009/228 | T3 WV DRM-GRS VLY-WMR 9/228 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2022-01-12 | 2022-01-12 |  | 2022-07-11 | 2022-07-12 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31590539 | T3 WV DRM-GRSS VLLY-WMR 5/134 RPL POLE | 70Y
LC | 122627340 | T077 | T3 WV MIDWAY-SANTA MARIA T077 RPR INSS | PISMOBCH | ETL.9240.INSL.NCER | 2022-01-19 | 2022-01-19 |  | 2022-07-18 | 2022-07-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB XMPT TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair | 45194108 | WV T3 MIDWAY-SANTA MARIA T077 RPR INSS | ICS
LC | 122773498 | 002/021 | T3 MORAGA-CLAREMONT #1 2/21 RPL INSS | CONCORD | ETL.2700.INSL.CERA | 2022-01-20 | 2022-01-19 |  | 2022-07-18 | 2022-07-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW NONR OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31600949 | T3 MORAGA-CLAREMONT #1 2/21 RPL INSS | 93K
LC | 122773593 | 002/021 | T3 MORAGA-CLAREMONT #2 2/021 RPL INSS | CONCORD | ETL.2710.INSL.CERA | 2022-01-20 | 2022-01-19 |  | 2022-07-18 | 2022-07-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW NONR OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31600950 | T3 MORAGA-CLAREMONT #2 RPL INSS IN 3 STR | 93K
LC | 122775674 | 005/148 | T3 WV DEER CREEK-DRUM 5/148 RPR SPLW | SACTO | ETL.6690.INSL.NCER | 2022-01-20 | 2022-01-20 |  | 2022-07-19 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB XMPT TR3 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45568296 | T3 WV DEER CREEK-DRUM 5/148 RPR SPLW | ICW
LC | 122785234 | 000/002B | T3 MORAGA-LAKEWOOD 000/002B RPR GYWS | CONCORD | ETL.3741.POLE.NWOD | 2022-01-21 | 2022-01-21 |  | 2022-07-20 | 2022-07-21 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45503486 | T3 MORAGA-LAKEWOOD 000/002B RPR GYWS | ICS
LC | 122900778 | 007/054 | T3 DI GRN VLLY-LLAGAS 7/54 INS RPTW | MOSSLNDG | ETL.1720.POLE.STPS | 2022-01-31 | 2022-01-27 |  | 2022-07-26 | 2022-07-27 | Late | 672 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR NTDE | Missing | Raptor Guard-Wood | Install
LC | 122901581 | 006/053 | T3 DI GRN VLLY-LLAGAS 6/53 INS RPTW | MOSSLNDG | ETL.1720.POLE.STPS | 2022-01-31 | 2022-01-27 |  | 2022-07-26 | 2022-07-27 | Late | 672 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR NTDE | Missing | Raptor Guard-Wood | Install
LC | 122902980 | 016/002 | T3 UKIAH-HPLND-CLVRDL 016/002 RPR STRW | WILLITS | ETL.4050.POLE.NWOD | 2022-01-31 | 2022-01-31 |  | 2022-07-30 | 2022-07-31 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW NONR OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45487502 | T3 UKIAH-HPLND-CLVRDL 016/002 RPR STRW | ICW
LC | 122916759 | 010/239 | T3 EI KILARC-CEDAR CREEK 10/239 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-02 | 2022-02-02 |  | 2022-08-01 | 2022-08-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606234 | T3 EI KILARC-CEDAR CREEK 10/229 RPL POLE | 70Y
LC | 122916787 | 013/280 | T3 EI KILARC-CEDAR CREEK 13/280 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-02 | 2022-02-02 |  | 2022-08-01 | 2022-08-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606234 | T3 EI KILARC-CEDAR CREEK 10/229 RPL POLE | 70Y
LC | 122919818 | 025/277 | T3 DI IGNACIO-BOLINAS#2 25/277 RPL INSW | LAKEVLLE | ETL.7180.INSL.CERA | 2022-02-03 | 2022-02-02 |  | 2022-08-01 | 2022-08-02 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617012 | T3 EI IGNACIO-BOLINAS #2 24/276 RPL INSW | 93I
LC | 122919940 | 020/111 | T3 EI PRKWY-MRAGA 20/111 RPL INSS | CONCORD | ETL.5930.INSL | 2022-02-03 | 2022-02-03 |  | 2022-08-02 | 2022-08-03 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31595635 | T2 PARKWAY-MORAGA RPL INSS 3 TWRS | 93K
LC | 122920914 | 010/114 | T3 WV IGNACIO-BOLINAS #1 10/114 INS DAMW | LAKEVLLE | ETL.7140.INSL.NCER | 2022-02-03 | 2022-02-03 |  | 2022-08-02 | 2022-08-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO NTDE | Missing | Damper-Wood | Install | 45486124 | T3 WV IGNACIO-BOLINAS #1 10/114 INS DAMW | ICW
LC | 122921001 | 004/124 | T3 EI COLGATE-ALLEGHANY 4/124 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-02-03 | 2022-02-03 |  | 2022-08-02 | 2022-08-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600082 | T3 EI COLGATE-ALLEGHANY 4/124 RPL STRW | 70Y
LC | 122924354 | 019/108 | T3 EI PRKWY-MORAGA 19/108 RPR INSS | CONCORD | ETL.5930.INSL | 2022-02-04 | 2022-02-04 |  | 2022-08-03 | 2022-08-04 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45514923 | T3 EI PRKWY-MORAGA 19/108 RPR INSS | ICS
LC | 122924601 | 005/134 | T3 EI COLGATE-ALLGHNY 5/134 RPR SWTCH 17 | SACTO | ETL.6470.SWIT | 2022-02-04 | 2022-02-04 |  | 2022-08-03 | 2022-08-04 | Late | 623 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | Out of Adjustment | Switch | Repair | 45526724 | T3 EI COLGATE-ALLGHNY 5/134 RPR SWTCH 17 | ICE
LC | 122924878 | 005/141 | T3 EI COLGATE-ALLEGHANY 005/141 RPR POLE | SACTO | ETL.6470.POLE.WOOD | 2022-02-04 | 2022-02-04 |  | 2022-08-03 | 2022-08-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45568838 | T3 EI COLGATE-ALLEGHANY 005/141 RPR POLE | ICW
LC | 122926767 | 005/154 | T3 EI COLGATE-ALLEGHANY 005/154 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-02-04 | 2022-02-04 |  | 2022-08-03 | 2022-08-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31600082 | T3 EI COLGATE-ALLEGHANY 4/124 RPL STRW | 70Y
LC | 122927797 | 012/337 | T3 EI CLGT-ALLGHNY-NNCRM 12/337 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-02-05 | 2022-02-05 |  | 2022-08-04 | 2022-08-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600082 | T3 EI COLGATE-ALLEGHANY 4/124 RPL STRW | 70Y
LC | 122927856 | 013/345 | T3 EI COLGATE-ALLEGHANY 13/345 RPR POLE | SACTO | ETL.6470.POLE.WOOD | 2022-02-05 | 2022-02-05 |  | 2022-08-04 | 2022-08-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45568844 | T3 EI COLGATE-ALLEGHANY 13/345 RPR POLE | ICW
LC | 122927857 | 013/341 | T3 EI COLGATE-ALLEGHANY 013/341 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-02-05 | 2022-02-05 |  | 2022-08-04 | 2022-08-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600082 | T3 EI COLGATE-ALLEGHANY 4/124 RPL STRW | 70Y
LC | 122927868 | 013/343 | T3 EI COLGATE-ALLEGHANY 013/343 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-02-05 | 2022-02-05 |  | 2022-08-04 | 2022-08-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600082 | T3 EI COLGATE-ALLEGHANY 4/124 RPL STRW | 70Y
LC | 122928175 | 013/354 | T3 EI COLGATE-ALLEGHANY 13/354 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-02-05 | 2022-02-05 |  | 2022-08-04 | 2022-08-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600082 | T3 EI COLGATE-ALLEGHANY 4/124 RPL STRW | 70Y
LC | 122929351 | 013/062 | T3 DI TASSAJARA-NEWARK 13/62 RPR INSS | CONCORD | ETL.5920.INSL | 2022-02-07 | 2022-01-28 |  | 2022-07-27 | 2022-07-28 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45513092 | T3 DI TASSAJARA-NEWARK 13/62 RPR INSS | ICS
LC | 122941932 | 001/005 | T3 EI DIABLO-MIDWAY #3 1/5 RPR GYWS | PISMOBCH | ETL.5980.TOWR | 2022-02-07 | 2022-02-07 |  | 2022-08-06 | 2022-08-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45616539 | T3 EI DIABLO-MIDWAY #3 1/5 RPR GYWS | ICS
LC | 122942750 | 000/005 | T3 EI DIABLO-GATES #1 000/005 RPR STRS | PISMOBCH | ETL.5960.TOWR | 2022-02-07 | 2022-02-07 |  | 2022-08-06 | 2022-08-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45616660 | T3 EI DIABLO-GATES #1 000/005 RPR STRS | ICS
LC | 122942751 | 000/005 | T3 EI DIABLO-GATES #1 000/005 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2022-02-07 | 2022-02-07 |  | 2022-08-06 | 2022-08-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW TR3 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45616661 | T3 EI DIABLO-GATES #1 000/005 RPR GYWS | ICS
LC | 122945534 | 011/261 | T3 EI KILARC-CEDAR CREEK 11/261 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-08 | 2022-02-08 |  | 2022-08-07 | 2022-08-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606234 | T3 EI KILARC-CEDAR CREEK 10/229 RPL POLE | 70Y
LC | 122946490 | 003/038B | T3 DRUM-SUMMIT #1 003/038B RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2022-02-08 | 2022-02-08 |  | 2022-08-07 | 2022-08-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31633891 | T3 DRUM-SUMMIT #1 003/038A RPL STRW | 70Y
LC | 122946623 | 010/229 | T3 EI KILARC-CEDAR CREEK 10/229 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-08 | 2022-02-08 |  | 2022-08-07 | 2022-08-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606234 | T3 EI KILARC-CEDAR CREEK 10/229 RPL POLE | 70Y
LC | 122946624 | 010/224 | T3 EI KILARC-CEDAR CREEK 10/224 RPL STRW | TABLEMTN | ETL.7290.INSL.CERA | 2022-02-08 | 2022-02-08 |  | 2022-08-07 | 2022-08-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31617628 | T3 DI KILARC-CEDAR CRK 4/96 RPL STRW | 70Y
LC | 122947002 | 012/129 | T3 DI IGNACIO-BOLINAS #1 12/129 RMV BUTT | LAKEVLLE | ETL.7140.POLE.WOOD | 2022-02-08 | 2022-02-01 |  | 2022-07-31 | 2022-08-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45486135 | T3 DI IGNACIO-BOLINAS #1 12/129 RMV BUTT | ICW
LC | 122947098 | 019/226 | T3 DI IGNACIO-BOLINAS #2 19/226 RPR HRDD | LAKEVLLE | ETL.7180.POLE.WOOD | 2022-02-08 | 2022-02-03 |  | 2022-08-02 | 2022-08-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45486088 | T3 DI IGNACIO-BOLINAS #2 19/226 RPR HRDD | ICW
LC | 122947276 | 012/128 | T3 DI IGNACIO-BOLINAS #1 12/128 RPL INSW | LAKEVLLE | ETL.7140.INSL | 2022-02-08 | 2022-02-01 |  | 2022-07-31 | 2022-08-01 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617009 | T2 DI IGNACIO-BOLINAS #1 7/071 RPL INSW | 93I
LC | 122947399 | 002/016 | T3 EI DIABLO-GATES #1 2/16 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2022-02-08 | 2022-02-08 |  | 2022-08-07 | 2022-08-08 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45616662 | T3 EI DIABLO-GATES #1 2/16 RPR GYWS | ICS
LC | 122947443 | 012/128 | T3 DI IGNACIO-BOLINAS #1 12/128 RMV STEP | LAKEVLLE | ETL.7140.POLE.WOOD | 2022-02-08 | 2022-02-01 |  | 2022-07-31 | 2022-08-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45486133 | T3 DI IGNACIO-BOLINAS #1 12/128 RMV STEP | ICW
LC | 122947524 | 020/229 | T3 DI IGNACIO-BLNS #2 20/229 RPL INSW | LAKEVLLE | ETL.7180.INSL.NCER | 2022-02-08 | 2022-02-03 |  | 2022-08-02 | 2022-08-03 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617019 | T3 DI IGNACIO-BLNS #2 20/229 RPL INSW | 93I
LC | 122947600 | 003/015 | T3 EI DIABLO-MIDWAY #3 3/15 RPR GYWS | PISMOBCH | ETL.5980.TOWR | 2022-02-08 | 2022-02-08 |  | 2022-08-07 | 2022-08-08 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45616663 | T3 EI DIABLO-MIDWAY #3 3/15 RPR GYWS | ICS
LC | 122947606 | 003/038A | T3 DRUM-SUMMIT #1 003/038A RPL STRW | SACTO | ETL.1440.POLE.WOOD | 2022-02-08 | 2022-02-08 |  | 2022-08-07 | 2022-08-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31633891 | T3 DRUM-SUMMIT #1 003/038A RPL STRW | 70Y
LC | 122947697 | 026/289 | T3 DI IGNACIO-BLNS #2 26/289 RPL INSW | LAKEVLLE | ETL.7180.INSL.CERA | 2022-02-08 | 2022-02-01 |  | 2022-07-31 | 2022-08-01 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617019 | T3 DI IGNACIO-BLNS #2 20/229 RPL INSW | 93I
LC | 122947788 | 024/273 | T3 DI IGNACIO-BOLINAS #2 24/273 RMV BUTT | LAKEVLLE | ETL.7180.POLE.WOOD | 2022-02-08 | 2022-02-02 |  | 2022-08-01 | 2022-08-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45486097 | T3 DI IGNACIO-BOLINAS #2 24/273 RMV BUTT | ICW
LC | 122948195 | 003/019 | T3 EI DIABLO-GATES #1 3/19 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2022-02-08 | 2022-02-08 |  | 2022-08-07 | 2022-08-08 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45616664 | T3 EI DIABLO-GATES #1 3/19 RPR GYWS | ICS
LC | 122950011 | 022/123 | T3 DI PARKWAY-MORAGA 22/123 RPR OPGW | CONCORD | ETL.5930.TOWR | 2022-02-09 | 2022-02-05 |  | 2022-08-04 | 2022-08-05 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45514927 | T3 DI PARKWAY-MORAGA 22/123 RPR OPGW | ICS
LC | 122950514 | 024/136 | T3 DI BAHIA-MORAGA 024/136 RPR INSS | CONCORD | ETL.4340.INSL.NCER | 2022-02-09 | 2022-02-05 |  | 2022-08-04 | 2022-08-05 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45514928 | T3 DI BAHIA-MORAGA 024/136 RPR INSS | ICS
LC | 122950761 | 019/108 | T3 DI PARKWAY-MORAGA 19/108 RPR OPGW | CONCORD | ETL.5930.TOWR | 2022-02-09 | 2022-02-05 |  | 2022-08-04 | 2022-08-05 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45514929 | T3 DI PARKWAY-MORAGA 19/108 RPR OPGW | ICS
LC | 122950797 | 007/167 | T3 EI KILARC-CEDAR CREEK 7/167 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-09 | 2022-02-09 |  | 2022-08-08 | 2022-08-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606232 | T3 EI KILARC-CEDAR CREEK 6/139 RPL POLE | 70Y
LC | 122950847 | 007/171 | T3 EI KILARC-CEDAR CREEK 7/171 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-09 | 2022-02-09 |  | 2022-08-08 | 2022-08-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606232 | T3 EI KILARC-CEDAR CREEK 6/139 RPL POLE | 70Y
LC | 122952218 | 008/199 | T3 EI KILARC-CEDAR CREEK 08/199 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-09 | 2022-02-09 |  | 2022-08-08 | 2022-08-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606232 | T3 EI KILARC-CEDAR CREEK 6/139 RPL POLE | 70Y
LC | 122952285 | 008/195 | T3 EI KILARC-CEDAR CREEK 8/195 RPR SPLW | TABLEMTN | ETL.7290.INSL | 2022-02-09 | 2022-02-09 |  | 2022-08-08 | 2022-08-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45459234 | T3 EI KILARC-CEDAR CREEK 8/195 RPR SPLW | ICW
LC | 122952286 | 009/210 | T3 EI KILARC-CEDAR 9/210 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-09 | 2022-02-09 |  | 2022-08-08 | 2022-08-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606233 | CREEK 09/202 RPL POLE | 70Y
LC | 122952288 | 008/181 | T3 EI KILARC-CEDAR CREEK 8/181 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-09 | 2022-02-09 |  | 2022-08-08 | 2022-08-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606232 | T3 EI KILARC-CEDAR CREEK 6/139 RPL POLE | 70Y
LC | 122952289 | 009/202 | T3 EI KILARC-CEDAR CREEK 09/202 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-09 | 2022-02-09 |  | 2022-08-08 | 2022-08-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606233 | CREEK 09/202 RPL POLE | 70Y
LC | 122952301 | 008/190 | T3 EI KILARC-CEDAR CREEK 8/190 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-09 | 2022-02-09 |  | 2022-08-08 | 2022-08-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606232 | T3 EI KILARC-CEDAR CREEK 6/139 RPL POLE | 70Y
LC | 122952364 | 022/124 | T3 DI PARKWAY-MORAGA 22/124 RPR FOND | CONCORD | ETL.5930.TOWR | 2022-02-09 | 2022-02-05 |  | 2022-08-04 | 2022-08-05 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 122952365 | 022/124 | T3 DI PRKWY-MORAGA 22/124 RMV STEP | CONCORD | ETL.5930.TOWR | 2022-02-09 | 2022-02-05 |  | 2022-08-04 | 2022-08-05 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 122952370 | 019/106 | T3 DI PARKWAY-MORAGA 19/106 INS HRDT | CONCORD | ETL.5930.TOWR | 2022-02-09 | 2022-02-05 |  | 2022-08-04 | 2022-08-05 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install
LC | 122952569 | 022/255 | T3 DI IGNACIO-BLNS #2 022/255 RPR SPLW | LAKEVLLE | ETL.7180.INSL.CERA | 2022-02-09 | 2022-02-04 |  | 2022-08-03 | 2022-08-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45457376 | T3 DI IGNACIO-BLNS #2 022/255 RPR SPLW | ICW
LC | 122952584 | 022/255 | T3 DI IGNACIO-BLNS #2 022/255L RMV VEG | LAKEVLLE | ETL.7180.POLE.WDPS | 2022-02-09 | 2022-02-04 |  | 2022-08-03 | 2022-08-04 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 122965177 | 009/221 | T3 EI KILARC-CEDAR CREEK 9/221 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-10 | 2022-02-10 |  | 2022-08-09 | 2022-08-10 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606233 | CREEK 09/202 RPL POLE | 70Y
LC | 122965200 | 009/220 | T3 EI KILARC-CEDAR CREEK 9/220 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-10 | 2022-02-10 |  | 2022-08-09 | 2022-08-10 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606233 | CREEK 09/202 RPL POLE | 70Y
LC | 122965201 | 009/215 | T3 EI KILARC-CEDAR 9/215 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-10 | 2022-02-10 |  | 2022-08-09 | 2022-08-10 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606233 | CREEK 09/202 RPL POLE | 70Y
LC | 122965737 | 021/244 | T3 DI IGNACIO-BLNS #2 21/244 INS HRDD | LAKEVLLE | ETL.7180.POLE.NWOD | 2022-02-10 | 2022-02-02 |  | 2022-08-01 | 2022-08-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45486093 | T3 DI IGNACIO-BLNS #2 21/244 INS HRDD | ICW
LC | 122966184 | 006/142 | T3 EI KILARC-CEDAR CREEK 6/142 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-10 | 2022-02-10 |  | 2022-08-09 | 2022-08-10 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606232 | T3 EI KILARC-CEDAR CREEK 6/139 RPL POLE | 70Y
LC | 122966195 | 006/139 | T3 EI KILARC-CEDAR CREEK 6/139 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-10 | 2022-02-10 |  | 2022-08-09 | 2022-08-10 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606232 | T3 EI KILARC-CEDAR CREEK 6/139 RPL POLE | 70Y
LC | 122970473 | 010/040 | T3 EI DIABLO-MIDWAY #3 10/040 RPR STRT | PISMOBCH | ETL.5980.TOWR | 2022-02-11 | 2022-02-11 |  | 2022-08-10 | 2022-08-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Structure-Tower | Repair | 45616665 | T3 EI DIABLO-MIDWAY #3 10/040 RPR STRT | ICQ
LC | 122971239 | 005/132 | EI T3 KILARC-CEDAR CRK 5/132 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-11 | 2022-02-11 |  | 2022-08-10 | 2022-08-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617628 | T3 DI KILARC-CEDAR CRK 4/96 RPL STRW | 70Y
LC | 122971283 | 005/130 | EI T3 KILARC-CEDAR CRK 5/130 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-11 | 2022-02-11 |  | 2022-08-10 | 2022-08-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617628 | T3 DI KILARC-CEDAR CRK 4/96 RPL STRW | 70Y
LC | 122971290 | 007/163 | T3 EI KILARC-CEDAR CRK 7/163 RPR CNDW | TABLEMTN | ETL.7290.INSL.NCER | 2022-02-11 | 2022-02-11 |  | 2022-08-10 | 2022-08-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Conductor-Wood | Repair | 45599892 | T3 EI KILARC-CEDAR CRK 7/163 RPR CNDW | ICW
LC | 122977201 | 000/017 | T3 EI KILARC-CEDAR CRK 0/017 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-12 | 2022-02-12 |  | 2022-08-11 | 2022-08-12 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606230 | T3 EI KILARC-CEDAR CREEK 00/005 RPL POLE | 70Y
LC | 122977347 | 001/024 | EI T3 KILARC-CEDAR CRK 1/024 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-12 | 2022-02-12 |  | 2022-08-11 | 2022-08-12 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31631564 | T3 EI KILARC-CEDAR CREEK 0/002 RPL STRW | 70Y
LC | 122977348 | 000/021 | T3 EI KILARC-CEDAR CRK 0/21 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-12 | 2022-02-12 |  | 2022-08-11 | 2022-08-12 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31631564 | T3 EI KILARC-CEDAR CREEK 0/002 RPL STRW | 70Y
LC | 122977349 | 001/028 | EI T3 KILARC-CEDAR CRK 1/028 RPL GYWW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-12 | 2022-02-12 |  | 2022-08-11 | 2022-08-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45459233 | EI T3 KILARC-CEDAR CRK 1/028 RPL GYWW | ICW
LC | 122977380 | 000/020 | T3 EI KILARC-CEDAR CRK 0/020 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-12 | 2022-02-12 |  | 2022-08-11 | 2022-08-12 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606230 | T3 EI KILARC-CEDAR CREEK 00/005 RPL POLE | 70Y
LC | 122980855 | 001/028 | T3 EI KILARC-CDR CRK 001/028 RPL ANCW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-14 | 2022-02-12 |  | 2022-08-11 | 2022-08-12 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Anchor-Wood | Replace | 31617627 | T3 EI KILARC-CEDAR CRK 0/21 REFRAME | 93E
LC | 122981714 | 002/022 | T3 EI ATASCADERO-CAYUCOS 2/022 RPR JUMW | PISMOBCH | ETL.8480.INSL.NCER | 2022-02-14 | 2022-02-14 |  | 2022-08-13 | 2022-08-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Jumper-Wood | Repair | 45600488 | T3 EI ATASCADERO-CAYUCOS 2/022 RPR JUMW | ICW
LC | 122981825 | 005/005 | T3 EI DIABLO UNIT #2 5/5 RPR GYWS | PISMOBCH | ETL.5950.TOWR | 2022-02-14 | 2022-02-14 |  | 2022-08-13 | 2022-08-14 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 122982878 | 002/064 | T3 EI KILARC-CEDAR CREEK 002/064 RPL STR | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-15 | 2022-02-14 |  | 2022-08-13 | 2022-08-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31631564 | T3 EI KILARC-CEDAR CREEK 0/002 RPL STRW | 70Y
LC | 122982879 | 002/062 | T3 EI KILARC-CEDAR CREEK 02/062 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-15 | 2022-02-14 |  | 2022-08-13 | 2022-08-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606230 | T3 EI KILARC-CEDAR CREEK 00/005 RPL POLE | 70Y
LC | 122983040 | 002/058 | T3 EI KILARC-CEDAR CREEK 02/058 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-15 | 2022-02-14 |  | 2022-08-13 | 2022-08-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606230 | T3 EI KILARC-CEDAR CREEK 00/005 RPL POLE | 70Y
LC | 122983041 | 002/063 | T3 EI KILARC-CEDAR CREEK 02/063 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-15 | 2022-02-14 |  | 2022-08-13 | 2022-08-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606230 | T3 EI KILARC-CEDAR CREEK 00/005 RPL POLE | 70Y
LC | 122983042 | 002/058 | T3 EI KILARC-CEDAR CREEK 2/58 RPR SPLW | TABLEMTN | ETL.7290.INSL.CERA | 2022-02-15 | 2022-02-14 |  | 2022-08-13 | 2022-08-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 122983849 | 013/060 | T3 DI MORAGA-CSTRO VLLY-13/60 RPL INSS | CONCORD | ETL.5250.INSL | 2022-02-15 | 2022-02-08 |  | 2022-08-07 | 2022-08-08 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31596647 | T3 DI MORAGA-CSTRO VLLY-13/60 RPL INSS | 93K
LC | 122984865 | 008/092 | T3 WV IGNACIO-BOLINAS #1 8/92 RPR INSW | LAKEVLLE | ETL.7140.INSL.NCER | 2022-02-15 | 2022-02-15 |  | 2022-08-14 | 2022-08-15 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair | 45486125 | T3 WV IGNACIO-BOLINAS #1 8/92 RPR INSW | ICS
LC | 122988153 | 022/092 | T3 EI DIABLO-MIDWAY #3 22/092 RPR FOND | PISMOBCH | ETL.5980.TOWR | 2022-02-16 | 2022-02-16 |  | 2022-08-15 | 2022-08-16 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45616721 | T3 EI DIABLO-MIDWAY #3 22/092 RPR FOND | ICQ
LC | 122988179 | 003/032 | T3 EI ATASCADERO-CAYUCOS 3/032 RPR STRW | PISMOBCH | ETL.8480.POLE.NWOD | 2022-02-16 | 2022-02-16 |  | 2022-08-15 | 2022-08-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45600491 | T3 EI ATASCADERO-CAYUCOS 3/032 RPR STRW | ICW
LC | 122989655 | 003/035 | T3 EI ATASCADERO-CAYUCOS 3/035 RPR GYWW | PISMOBCH | ETL.8480.POLE.NWOD | 2022-02-16 | 2022-02-16 |  | 2022-08-15 | 2022-08-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45600492 | T3 EI ATASCADERO-CAYUCOS 3/035 RPR GYWW | ICW
LC | 122989656 | 003/035 | T3 EI ATASCADERO-CAYUCOS 3/035 REGRADE | PISMOBCH | ETL.8480.POLE.NWOD | 2022-02-16 | 2022-02-16 |  | 2022-08-15 | 2022-08-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45600493 | T3 EI ATASCADERO-CAYUCOS 3/035 REGRADE | ICW
LC | 122989657 | 003/034 | T3 EI ATASCADERO-CAYUCOS 03/34 RPR GYWW | PISMOBCH | ETL.8480.POLE.NWOD | 2022-02-16 | 2022-02-16 |  | 2022-08-15 | 2022-08-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45600494 | T3 EI ATASCADERO-CAYUCOS 03/34 RPR GYWW | ICW
LC | 122989658 | 003/034 | T3NT EI ATASCDERO-CAYUCOS 03/34 REGRADE | PISMOBCH | ETL.8480.POLE.NWOD | 2022-02-16 | 2022-02-16 |  | 2022-08-15 | 2022-08-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3N PRTO NTDE | No Good/Out of Stdrd | Structure-Wood | Repair | 45600496 | T3NT EI ATASCDERO-CAYUCOS 03/34 REGRADE | ICW
LC | 122993358 | 005/004 | T3 EI DIABLO UNIT #2 5/004 RPR GYWS | PISMOBCH | ETL.5950.TOWR | 2022-02-17 | 2022-02-17 |  | 2022-08-16 | 2022-08-17 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 122994025 | 005/002 | T3 EI DIABLO UNIT #1 5/002 RPR GYWS | PISMOBCH | ETL.5940.TOWR | 2022-02-17 | 2022-02-17 |  | 2022-08-16 | 2022-08-17 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 122994154 | 005/044 | T3 EI ADERO-CAYUCOS 5/044 RPL POLE | PISMOBCH | ETL.8480.POLE.WOOD | 2022-02-17 | 2022-02-17 |  | 2022-08-16 | 2022-08-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31609301 | T3 DI ATSCDRO-CYUCOS 2/22L RPL POLE | 70Y
LC | 122994761 | 014/383 | T3 EI COLGATE-ALLEGHANY 14/383 RMV VEG | SACTO | ETL.6470.POLE.WOOD | 2022-02-17 | 2022-02-17 |  | 2022-08-16 | 2022-08-17 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | Overgrown | Vegetation | Remove
LC | 122998132 | 022/256 | T3 DI IGNACIO-BLNS #2 22/256 RMV BUTT | LAKEVLLE | ETL.7180.POLE.WOOD | 2022-02-18 | 2022-02-07 |  | 2022-08-06 | 2022-08-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45486091 | T3 DI IGNACIO-BLNS #2 22/256 RMV BUTT | ICW
LC | 122999358 | 005/138 | T3 EI COLGATE-ALLEGHANY 5/138 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-02-18 | 2022-02-18 |  | 2022-08-17 | 2022-08-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31600082 | T3 EI COLGATE-ALLEGHANY 4/124 RPL STRW | 70Y
LC | 122999420 | 014/377 | T3 EI COLGATE-ALLEGHANY 14/377 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-02-18 | 2022-02-18 |  | 2022-08-17 | 2022-08-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31600082 | T3 EI COLGATE-ALLEGHANY 4/124 RPL STRW | 70Y
LC | 123000125 | 003/087 | T3 EI KILARC-CEDAR CREEK 3/087 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-19 | 2022-02-18 |  | 2022-08-17 | 2022-08-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606231 | T3 EI KILARC-CEDAR CREEK 3/076 RPL POLE | 70Y
LC | 123000126 | 003/071 | T3 EI KILARC-CEDAR CREEK 3/71 RPL CNDW | TABLEMTN | ETL.7290.INSL | 2022-02-19 | 2022-02-18 |  | 2022-08-17 | 2022-08-18 | Late | 638 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Conductor-Wood | Replace | 31617624 | T3 EI KILARC-CEDAR CREEK 3/71 RPL CNDW | 93C
LC | 123000178 | 003/076 | T3 EI KILARC-CEDAR CREEK 3/076 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-19 | 2022-02-18 |  | 2022-08-17 | 2022-08-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606231 | T3 EI KILARC-CEDAR CREEK 3/076 RPL POLE | 70Y
LC | 123000299 | 004/095 | T3 EI KILARC-CEDAR CREEK 4/095 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-19 | 2022-02-19 |  | 2022-08-18 | 2022-08-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606231 | T3 EI KILARC-CEDAR CREEK 3/076 RPL POLE | 70Y
LC | 123000321 | 003/078 | T3 EI KILARC-CEDAR CREEK 3/078 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-02-19 | 2022-02-19 |  | 2022-08-18 | 2022-08-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31631564 | T3 EI KILARC-CEDAR CREEK 0/002 RPL STRW | 70Y
LC | 123000326 | 016/453 | T3 EI COLGATE-ALLEGHANY 016/453 RPR GYWW | SACTO | ETL.6470.POLE.NWOD | 2022-02-19 | 2022-02-19 |  | 2022-08-18 | 2022-08-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 45568899 | T3 EI COLGATE-ALLEGHANY 016/453 RPR GYWW | ICW
LC | 123000327 | 017/459 | T3 EI COLGATE-ALLEGHANY 17/459 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-02-19 | 2022-02-19 |  | 2022-08-18 | 2022-08-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600083 | T3NT EI COLGTE-ALLEGHNY 15/413 RPL POLE | 70Y
LC | 123000475 | 016/447 | T3 EI COLGATE-ALLEGHANY 16/447 RPR GYWW | SACTO | ETL.6470.POLE.NWOD | 2022-02-19 | 2022-02-19 |  | 2022-08-18 | 2022-08-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45568905 | T3 EI COLGATE-ALLEGHANY 16/447 RPR GYWW | ICW
LC | 123000655 | 009/243 | T3 EI COLGATE-ALLEGHANY RPL SPLW | SACTO | ETL.6470.INSL.NCER | 2022-02-19 | 2022-02-19 |  | 2022-08-18 | 2022-08-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Replace | 45568910 | T3 EI COLGATE-ALLEGHANY RPL SPLW | ICW
LC | 123000656 | 009/249 | T3 EI COLGATE-ALLEGHANY 9/249 RPL SPLW | SACTO | ETL.6470.INSL.NCER | 2022-02-19 | 2022-02-19 |  | 2022-08-18 | 2022-08-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Replace | 45568926 | T3 EI COLGATE-ALLEGHANY 9/249 RPL SPLW | ICW
LC | 123000858 | 016/433 | T3 EI COLGATE-ALLEGHANY 16/433 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-02-20 | 2022-02-20 |  | 2022-08-19 | 2022-08-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31600083 | T3NT EI COLGTE-ALLEGHNY 15/413 RPL POLE | 70Y
LC | 123000859 | 016/438 | T3 EI COLGATE-ALLEGHANY 16/438 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-02-20 | 2022-02-20 |  | 2022-08-19 | 2022-08-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31605566 | HANY 15/402 RPL POLE | 70Y
LC | 123000894 | 015/423 | T3 EI COLGATE-ALLEGHANY 15/423 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-02-20 | 2022-02-20 |  | 2022-08-19 | 2022-08-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31600083 | T3NT EI COLGTE-ALLEGHNY 15/413 RPL POLE | 70Y
LC | 123000895 | 015/424 | T3 EI COLGATE-ALLEGHANY 15/424 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-02-20 | 2022-02-20 |  | 2022-08-19 | 2022-08-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31600083 | T3NT EI COLGTE-ALLEGHNY 15/413 RPL POLE | 70Y
LC | 123006805 | 025/279 | T3 DI IGNACIO-BOLINAS #2 25/279 RPR POLE | LAKEVLLE | ETL.7180.POLE.WDPS | 2022-02-23 | 2022-02-02 |  | 2022-08-01 | 2022-08-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45486092 | T3 DI IGNACIO-BOLINAS #2 25/279 RPR POLE | ICW
LC | 123007232 | 020/237 | T3 DI IGNACIO-BLNS #2 020/237 RPR POLE | LAKEVLLE | ETL.7180.POLE.WOOD | 2022-02-23 | 2022-02-04 |  | 2022-08-03 | 2022-08-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45486089 | T3 DI IGNACIO-BLNS #2 020/237 RPR POLE | ICW
LC | 123007336 | 019/223 | T3 DI IGNACIO-BOLINAS #2 19/223 RPR IBWW | LAKEVLLE | ETL.7180.POLE.WOOD | 2022-02-23 | 2022-02-02 |  | 2022-08-01 | 2022-08-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45486086 | T3 DI IGNACIO-BOLINAS #2 19/223 RPR IBWW | ICW
LC | 123007536 | 018/214 | T3 DI IGNACIO-BOLINAS #2 18/214 RPR IBWW | LAKEVLLE | ETL.7180.POLE.WOOD | 2022-02-23 | 2022-02-02 |  | 2022-08-01 | 2022-08-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45486087 | T3 DI IGNACIO-BOLINAS #2 18/214 RPR IBWW | ICW
LC | 123007780 | 020/232 | T3 DI IGNACIO-BOLINAS #2 020/232 REFRAME | LAKEVLLE | ETL.7180.POLE.WOOD | 2022-02-23 | 2022-02-03 |  | 2022-08-02 | 2022-08-03 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31617017 | T3 DI IGNACIO-BOLINAS #2 020/232 REFRAME | 93E
LC | 123007788 | 020/234 | T3 DI IGNACIO-BLNS #2 020/234 REFRAME | LAKEVLLE | ETL.7180.POLE.WOOD | 2022-02-23 | 2022-02-04 |  | 2022-08-03 | 2022-08-04 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31617017 | T3 DI IGNACIO-BOLINAS #2 020/232 REFRAME | 93E
LC | 123008070 | 016/188 | T3 DI IGNACIO-BOLINAS #2 16/188 RMV BUTT | LAKEVLLE | ETL.7180.POLE.WOOD | 2022-02-23 | 2022-02-07 |  | 2022-08-06 | 2022-08-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45486016 | T3 DI IGNACIO-BOLINAS #2 16/188 RMV BUTT | ICW
LC | 123009820 | 023/266 | T3 DI IGNACIO-BLNS #2 023/266 RPL POLE | LAKEVLLE | ETL.7180.POLE.WOOD | 2022-02-23 | 2022-02-07 |  | 2022-08-06 | 2022-08-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617014 | T3 DI IGNACIO-BLNS #2 023/266 RPL POLE | 70Y
LC | 123009924 | 023/261 | T3 DI IGNACIO-BLNS #2 023/261L RPL HRDW | LAKEVLLE | ETL.7180.POLE.WDPS | 2022-02-23 | 2022-02-07 |  | 2022-08-06 | 2022-08-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45486098 | T3 DI IGNACIO-BLNS #2 023/261L RPL HRDW | ICW
LC | 123009952 | 023/261 | T3 DI IGNACIO-BLNS #2 023/261R RPL HRDW | LAKEVLLE | ETL.7180.POLE.WDPS | 2022-02-23 | 2022-02-07 |  | 2022-08-06 | 2022-08-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45486096 | T3 DI IGNACIO-BLNS #2 023/261R RPL HRDW | ICW
LC | 123028498 | 004/020 | T3 DI SAN RAMON-MORAGA RPR OPGS | CONCORD | ETL.5660.TOWR | 2022-02-25 | 2022-02-09 |  | 2022-08-08 | 2022-08-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45513094 | T3 DI SAN RAMON-MORAGA RPR OPGS | ICS
LC | 123037908 | 000/005 | T3 EI KILARC-CEDAR CREEK 00/005 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-03-01 | 2022-03-01 |  | 2022-08-28 | 2022-09-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606230 | T3 EI KILARC-CEDAR CREEK 00/005 RPL POLE | 70Y
LC | 123037961 | 000/006 | T3 EI KILARC-CEDAR CRK 000/006 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-03-01 | 2022-03-01 |  | 2022-08-28 | 2022-09-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606230 | T3 EI KILARC-CEDAR CREEK 00/005 RPL POLE | 70Y
LC | 123041624 | 039/001 | T2 RIO DELL JCT-BRIDGEVILL 39/1 RPL POLE | EUREKA | ETL.7850.POLE.WOOD | 2022-03-02 | 2021-04-24 |  | 2022-04-24 | 2022-04-24 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | RELW OTHR FIRE OH TR2 FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31613218 | T2 RIO DELL JCT-BRIDGEVILL 39/1 RPL POLE | 70Y
LC | 123042721 | 000/003 | T3 WV KONOCTI-EAGLE RCK 000/003 INS DAMW | WILLITS | ETL.6861.INSL.NCER | 2022-03-02 | 2022-03-02 |  | 2022-08-29 | 2022-09-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO NTDE | Missing | Damper-Wood | Install | 45128107 | T3 EI KONOCTI-EAGLE ROCK 0/003 INST DAMP | ICW
LC | 123044571 | 033/242 | T3 DI MDDLE FRK-GLD HLL 33/242 REFRAME | SACTO | ETL.5140.POLE.STPS | 2022-03-02 | 2022-03-02 |  | 2022-08-29 | 2022-09-02 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace
LC | 123047421 | 004/112 | T3 EI KILLARC-CEDAR CREEK 4/112 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-03-03 | 2022-03-03 |  | 2022-08-30 | 2022-09-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606231 | T3 EI KILARC-CEDAR CREEK 3/076 RPL POLE | 70Y
LC | 123048119 | 019/080 | T3 EI DIABLO-GATES 19/80 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2022-03-03 | 2022-03-03 |  | 2022-08-30 | 2022-09-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Ground Wire-Steel | Repair | 45619007 | T3 EI DIABLO-GATES 19/80 RPR GYWS | ICS
LC | 123049020 | 008/237 | T3 EI COLEGATE-ALLEGHANY 008/237 REFRAME | SACTO | ETL.6470.POLE.WOOD | 2022-03-03 | 2022-03-03 |  | 2022-08-30 | 2022-09-03 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OTHR OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31600080 | T2 EI COLGATE-ALLEGHANY 001/048 REFRAME | 93E
LC | 123050654 | 018/486 | T3 EI COLGATE-ALLEGHANY 18/486 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-04 | 2022-03-03 |  | 2022-08-30 | 2022-09-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600083 | T3NT EI COLGTE-ALLEGHNY 15/413 RPL POLE | 70Y
LC | 123051655 | 017/469 | T3 EI COLGATE-ALLEGHANY 17/469 RPL INSW | SACTO | ETL.6470.INSL.CERA | 2022-03-04 | 2022-03-03 |  | 2022-08-30 | 2022-09-03 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31600081 | T3 EI COLGATE-ALLEGHANY 17/469 RPL INSW | 93I
LC | 123051656 | 017/478 | T3 EI COLGATE-ALLEGHANY 17/478 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-04 | 2022-03-03 |  | 2022-08-30 | 2022-09-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600083 | T3NT EI COLGTE-ALLEGHNY 15/413 RPL POLE | 70Y
LC | 123051996 | 027/109 | T3 DI PITTSBURG-SAN MATE 27/109 RPR INSS | CONCORD | ETL.5463.INSL | 2022-03-04 | 2022-02-28 |  | 2022-08-27 | 2022-08-28 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45514931 | T3 DI PITTSBURG-SAN MATE 27/109 RPR INSS | ICS
LC | 123053096 | 020/564 | T3 EI COLGATE-ALLEGHANY 20/564 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-04 | 2022-03-04 |  | 2022-08-31 | 2022-09-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600086 | T3 EI COLGATE-ALLEGHANY 19/533 RPL STRW | 70Y
LC | 123053099 | 020/565 | T3 EI COLGATE-ALLEGHANY 20/565 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-04 | 2022-03-04 |  | 2022-08-31 | 2022-09-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600086 | T3 EI COLGATE-ALLEGHANY 19/533 RPL STRW | 70Y
LC | 123053186 | 025/295 | T2 EI DRUM-SUMMIT #1 25/295R RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2022-03-04 | 2021-06-25 |  | 2022-06-25 | 2022-06-25 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW INSP OH FMOB TR2 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31597209 | T2 EI DRUM-SUMMIT #1 25/295R RPL STRW | 70Y
LC | 123053558 | 021/568 | T3 EI COLGATE-ALLEGHANY 21/568 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-04 | 2022-03-04 |  | 2022-08-31 | 2022-09-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31600087 | T3 EI COLGATE-ALLEGHANY 21/568 RPL POLE | 70Y
LC | 123054077 | 010/157 | T3 DI ATASCADERO-SLO 10/157 RPR JUMPER | PISMOBCH | ETL.8490.INSL.NCER | 2022-03-04 | 2022-03-03 |  | 2022-08-30 | 2022-09-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Steel | Repair | 45597406 | T3 DI ATASCADERO-SLO 10/157 RPR JUMPER | ICS
LC | 123054662 | 027/108 | T3 DI PTTSBRG-SAN MATEO 27/108 RPR INSS | CONCORD | ETL.5463.INSL | 2022-03-04 | 2022-03-02 |  | 2022-08-29 | 2022-09-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45514934 | T3 DI PTTSBRG-SAN MATEO 27/108 RPR INSS | ICS
LC | 123055739 | 021/590 | T3 EI COLGATE-ALLEGHANY 21/590 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-05 | 2022-03-05 |  | 2022-09-01 | 2022-09-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600087 | T3 EI COLGATE-ALLEGHANY 21/568 RPL POLE | 70Y
LC | 123055840 | 013/118B | T3 DI CTTNWD-BNTN #2 13/118B L UNBURY | TABLEMTN | ETL.6650.POLE.WDPS | 2022-03-05 | 2022-03-04 |  | 2022-08-31 | 2022-09-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123055841 | 013/118B | T3 DI CTTNWD-BNTN #2 13/118B C UNBURY | TABLEMTN | ETL.6650.POLE.WDPS | 2022-03-05 | 2022-03-04 |  | 2022-08-31 | 2022-09-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123055842 | 013/118B | T3 DI CTTNWD-BNTN #2 13/118B R UNBURY | TABLEMTN | ETL.6650.POLE.WDPS | 2022-03-05 | 2022-03-04 |  | 2022-08-31 | 2022-09-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123056065 | 008/221 | T3 EI COLGATE-ALLEGHANY 008/221 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-03-05 | 2022-03-05 |  | 2022-09-01 | 2022-09-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31633457 | T3 DI COLGATE-ALLEGHANY 008/222 RPL STRW | 70Y
LC | 123057945 | 034/248 | T3 DI MDDL FRK-GLD HLL 34/248L RPL CRSW | SACTO | ETL.5140.POLE.STPS | 2022-03-07 | 2022-03-02 |  | 2022-08-29 | 2022-09-02 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace
LC | 123059595 | 003/065 | T3 WV BURNS-LONE STAR #2 3/065 RPL POLE | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-03-07 | 2022-03-07 |  | 2022-09-03 | 2022-09-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31629518 | T3 DI BRNS LN STR #2 2/49 RPL POLE | 70Y
LC | 123059597 | 015/402 | T3 EI CLGATE-ALLEGHANY 15/402 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-07 | 2022-03-07 |  | 2022-09-03 | 2022-09-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605566 | HANY 15/402 RPL POLE | 70Y
LC | 123059688 | 015/418 | T3 EI COLGATE-ALLEGHANY 15/418 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-07 | 2022-03-07 |  | 2022-09-03 | 2022-09-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31600083 | T3NT EI COLGTE-ALLEGHNY 15/413 RPL POLE | 70Y
LC | 123059689 | 015/413 | T3NT EI COLGTE-ALLEGHNY 15/413 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-07 | 2022-03-07 |  | 2022-09-03 | 2022-09-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600083 | T3NT EI COLGTE-ALLEGHNY 15/413 RPL POLE | 70Y
LC | 123059787 | 001/025 | T3 CTRVLE-TBL MTN-ORVLE 1/25 RPL INSW | TABLEMTN | ETL.6330.INSL | 2022-03-07 | 2022-03-07 |  | 2022-09-03 | 2022-09-07 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW NONR OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31600041 | T3 CTRVLE-TBL MTN-ORVLE 1/25 RPL INSW | 93I
LC | 123059886 | 001/026 | T3 CTRVL-TBL MTN-ORVL 1/26 RPL INSS | TABLEMTN | ETL.6330.INSL.NCER | 2022-03-07 | 2022-03-07 |  | 2022-09-03 | 2022-09-07 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW NONR OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31618796 | T3 CTRVL-TBL MTN-ORVL 1/26 RPL INSS | 93K
LC | 123060105 | B017/385 | T3 DRM-GRSS VLLEY-WEMR B017/385 RPR SPLS | SACTO | ETL.6760.SWIT | 2022-03-07 | 2022-03-07 |  | 2022-09-03 | 2022-09-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Conductor-Wood | Repair | 45568936 | T3 DRM-GRSS VLLEY-WEMR B017/385 RPR SPLS | ICW
LC | 123063118 | 017/118 | T3 EI ROCK CREEK-POE 017/118 RPR STRT | TABLEMTN | ETL.5630.TOWR | 2022-03-08 | 2022-03-08 |  | 2022-09-04 | 2022-09-08 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123063315 | 017/119 | T3 EI POE-RIO OSO-RIO 017/119 RPR ANCT | TABLEMTN | ETL.5540.TOWR | 2022-03-08 | 2022-03-08 |  | 2022-09-04 | 2022-09-08 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair
LC | 123085206 | 008/141 | T3 DI ATSCDRO-LUIS OBSPO 8/141 RPL DMPS | PISMOBCH | ETL.8490.INSL.CERA | 2022-03-10 | 2022-03-09 |  | 2022-09-05 | 2022-09-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 45597405 | T3 DI ATSCDRO-LUIS OBSPO 8/141 RPL DMPS | ICS
LC | 123086049 | 018/487 | T3 EI COLGATE-ALLEGHANY 018/487 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-10 | 2022-03-10 |  | 2022-09-06 | 2022-09-10 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600083 | T3NT EI COLGTE-ALLEGHNY 15/413 RPL POLE | 70Y
LC | 123086074 | :001/007 | T3 WV EAGLE ROCK-RDBD :001/007 INS DMPS | WILLITS | ETL.1480.INSL.NCER | 2022-03-10 | 2022-03-10 |  | 2022-09-06 | 2022-09-10 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO NTDE | Missing | Damper-Steel | Install | 31540875 | T3 DI EAGLE ROCK-REDBUD REPL INSS 6TWRS | 93K
LC | 123086255 | :001/006 | T3 WV EAGLE ROCK-RDBD :001/006 INS DMPS | WILLITS | ETL.1480.INSL.NCER | 2022-03-10 | 2022-03-10 |  | 2022-09-06 | 2022-09-10 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO NTDE | Missing | Damper-Steel | Install | 31540875 | T3 DI EAGLE ROCK-REDBUD REPL INSS 6TWRS | 93K
LC | 123086277 | 013/114 | T3 DI COTTONWD-BNTON #2 13/114 RPL INSLW | TABLEMTN | ETL.6650.INSL.NCER | 2022-03-10 | 2022-03-09 |  | 2022-09-05 | 2022-09-09 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617828 | T2 DI CTTNWOOD-BNTN #2 6/057 RPL INSW | 93I
LC | 123088059 | 009/149 | T3 DI ATASCDRO-LUIS OBSPO 9/149 INS STEP | PISMOBCH | ETL.8490.TOWR | 2022-03-10 | 2022-03-03 |  | 2022-08-30 | 2022-09-03 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45634778 | T3 DI ATASCDRO-LUIS OBSPO 9/149 INS STEP | ICQ
LC | 123090092 | 015/065 | T3 DI MONTA VST-JFFRSN #1 15/65 BNT STEE | METCALF | ETL.5220.TOWR | 2022-03-11 | 2022-03-10 |  | 2022-09-06 | 2022-09-10 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123092136 | 005/062 | T3 EI SNEATH LANE-PACIFICA 5/62 RPL ANCW | METCALF | ETL.7575.POLE.WOOD | 2022-03-11 | 2022-03-11 |  | 2022-09-07 | 2022-09-11 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31629677 | T2 EI SNEATH LANE-PACIFICA 5/54 RPL ANCW | 93E
LC | 123092925 | 018/082 | T3 EI MOSS LANDING-MTCLF 18/82 BNT STEEL | MOSSLNDG | ETL.6050.TOWR | 2022-03-11 | 2022-03-11 |  | 2022-09-07 | 2022-09-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW CREW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123095321 | 010/271 | T3 EI COLGATE-ALLEGHANY 10/271 REFRAME | SACTO | ETL.6470.POLE.WOOD | 2022-03-13 | 2022-03-12 |  | 2022-09-08 | 2022-09-12 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31600080 | T2 EI COLGATE-ALLEGHANY 001/048 REFRAME | 93E
LC | 123097168 | 004/069A | T3 DI SSQC GRY 4/69A RPL INSW | PISMOBCH | ETL.3690.INSL | 2022-03-14 | 2022-03-12 |  | 2022-09-08 | 2022-09-12 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31629721 | T3 DI SSQC GRY 4/69A RPL INSW | 93I
LC | 123098031 | 018/507 | T3 EI COLGATE-ALLEGHANY 018/507 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-03-14 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600083 | T3NT EI COLGTE-ALLEGHNY 15/413 RPL POLE | 70Y
LC | 123098304 | 011/101 | T3 DI CTTNWD-BENTON #2 11/101R INS HRDD | TABLEMTN | ETL.6650.POLE.STPS | 2022-03-14 | 2022-03-10 |  | 2022-09-06 | 2022-09-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | Missing | Hardware-Wood | Install
LC | 123098309 | 003/026 | T3 DI TIGER CRK-ELECTRA 3/26 RPR STRS | VICTOR | ETL.5780.TOWR | 2022-03-14 | 2022-03-10 |  | 2022-09-06 | 2022-09-10 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45519428 | T3 DI TIGER CRK-ELECTRA 3/26 RPR STRS | ICS
LC | 123098385 | 002/033 | T3 DI WST PNT-VLLY SPRNG 2/33 RPL HRDD | VICTOR | ETL.8350.POLE.WOOD | 2022-03-14 | 2022-03-10 |  | 2022-09-06 | 2022-09-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45519429 | T3 DI WST PNT-VLLY SPRNG 2/33 RPL HRDD | ICW
LC | 123099835 | 054/302 | T3 DI TEMBLOR-SLO 54/302 RPR INSS | PISMOBCH | ETL.3960.INSL.NCER | 2022-03-14 | 2022-03-11 |  | 2022-09-07 | 2022-09-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123099836 | 054/302 | T3 DI TEMBLOR-SLO 54/302 RPL HRDT | PISMOBCH | ETL.3960.TOWR | 2022-03-14 | 2022-03-11 |  | 2022-09-07 | 2022-09-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45634823 | T3 DI TEMBLOR-SLO 54/302 RPL HRDT | ICQ
LC | 123107520 | 001/009 | T3 EI RND MTN-TBLE MTN #1 1/9 BNT STEEL | TABLEMTN | ETL.6060.TOWR | 2022-03-16 | 2022-03-16 |  | 2022-09-12 | 2022-09-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45458620 | T3 EI RND MTN-TBLE MTN #1 1/9 BNT STEEL | ICS
LC | 123108449 | 001/010 | T3 EI RND MTN-TBLE MTN #1 1/10 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2022-03-16 | 2022-03-16 |  | 2022-09-12 | 2022-09-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45458621 | T3 EI RND MTN-TBLE MTN #1 1/10 RPR GYWS | ICS
LC | 123108458 | 054/301 | T3 DI TMBOR-SN LS OBISPO 54/301 RPL HRDT | PISMOBCH | ETL.3960.TOWR | 2022-03-16 | 2022-03-11 |  | 2022-09-07 | 2022-09-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45634826 | T3 DI TMBOR-SN LS OBISPO 54/301 RPL HRDT | ICQ
LC | 123108926 | 001/010 | T3 EI RND MTN-TALE MTN #2 1/10 BNT STEEL | TABLEMTN | ETL.6070.TOWR | 2022-03-16 | 2022-03-16 |  | 2022-09-12 | 2022-09-16 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123109029 | 001/010 | T3 EI RND MTN-TABLE MTN #2 1/10 RMV VEG | TABLEMTN | ETL.6070.TOWR | 2022-03-16 | 2022-03-16 |  | 2022-09-12 | 2022-09-16 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123109592 | 021/010 | T3 WV MAPLE CREEK-HOOPA 21/10 RPR SPLW | EUREKA | ETL.7490.INSL.NCER | 2022-03-16 | 2022-03-16 |  | 2022-09-12 | 2022-09-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO | No Good/Out of Stdrd | Splice-Wood | Replace | 45416604 | T3 WV MAPLE CREEK-HOOPA 21/10 RPR SPLW | ICW
LC | 123110182 | 002/029 | T3 WV DRUM-RIO OSO #1 002/029 RPR FOND | SACTO | ETL.1420.TOWR | 2022-03-16 | 2022-03-16 |  | 2022-09-12 | 2022-09-16 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45582123 | T3 WV DRUM-RIO OSO #1 002/029 RPR FOND | ICQ
LC | 123110885 | 000/005B | T3 EI GEYSERS #7-EAGLE RCK 0/5B RMV BUTT | LAKEVLLE | ETL.1680.POLE.WOOD | 2022-03-16 | 2022-03-16 |  | 2022-09-12 | 2022-09-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123110886 | 000/005C | T3 EI GEYSERS #7-EAGLE RCK 0/5C RMV BUTT | LAKEVLLE | ETL.1680.POLE.WOOD | 2022-03-16 | 2022-03-16 |  | 2022-09-12 | 2022-09-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45575657 | T3 EI GEYSERS #7-EAGLE RCK 0/5C RMV BUTT | ICW
LC | 123110972 | 001/012 | T3 EI RND MTN-TBLE MTN #1 1/12 BNT STEEL | TABLEMTN | ETL.6060.TOWR | 2022-03-16 | 2022-03-16 |  | 2022-09-12 | 2022-09-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45458622 | T3 EI RND MTN-TBLE MTN #1 1/12 BNT STEEL | ICS
LC | 123111014 | 007/065 | T3 MONTA VISTA-BURNS 7/65 INST HRDD | MOSSLNDG | ETL.7590.POLE.STPS | 2022-03-16 | 2022-02-02 |  | 2022-08-01 | 2022-08-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO NTDE | Missing | Hardware-Wood | Install | 45459133 | T3 MONTA VISTA-BURNS 7/65 INST HRDD | ICW
LC | 123112326 | 013/058 | T3 DI SN LS BSPO-OCNO 13/58 RPR INSS | PISMOBCH | ETL.3530.INSL.CERA | 2022-03-17 | 2022-03-12 |  | 2022-09-08 | 2022-09-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45604937 | T3 DI SN LS BSPO-OCNO 13/58 RPR INSS | ICS
LC | 123119442 | 002/013 | T3 EI ROUND MTN-TABLE MTN#1 REGRADE | TABLEMTN | ETL.6060.TOWR | 2022-03-17 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45458623 | T3 EI ROUND MTN-TABLE MTN#1 REGRADE | ICS
LC | 123119443 | 002/013 | T3 EI ROUND MTN-TABLE MTN#1 2/13 RMV VEG | TABLEMTN | ETL.6060.TOWR | 2022-03-17 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123143806 | 002/014 | T3 EI RND MTN-TABLE MTN#1 2/14 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2022-03-17 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45644373 | T3 EI RND MTN-TABLE MTN#1 2/14 RPR STRT | ICQ
LC | 123143881 | 002/014 | T3 EI ROUND MTN-TABLE MTN#1 RPL ANCW | TABLEMTN | ETL.6060.TOWR | 2022-03-17 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Anchor-Steel | Replace
LC | 123144288 | 019/533 | T3 EI COLGATE-ALLEGHANY 19/533 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-03-17 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600086 | T3 EI COLGATE-ALLEGHANY 19/533 RPL STRW | 70Y
LC | 123144330 | 019/534 | T3 EI COLGATE-ALLEGHANY 19/534 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-03-17 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600086 | T3 EI COLGATE-ALLEGHANY 19/533 RPL STRW | 70Y
LC | 123144423 | 019/007 | T3 WV MAPLE CREEK-HOOPA INS DAMW | EUREKA | ETL.7490.INSL.NCER | 2022-03-17 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO NTDE | Missing | Damper-Wood | Install
LC | 123144707 | 002/014 | T3 EI RND MTN-TABLE MTN#2 2/14 RPL ANCS | TABLEMTN | ETL.6070.TOWR | 2022-03-17 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Anchor-Steel | Replace
LC | 123144708 | 002/014 | T3 EI RND MTN-TABLE MTN#2 2/14 RMV VEG | TABLEMTN | ETL.6070.TOWR | 2022-03-17 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123145327 | 020/544 | T3 EI COLGATE-ALLEGHANY 20/544 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-03-17 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600086 | T3 EI COLGATE-ALLEGHANY 19/533 RPL STRW | 70Y
LC | 123145328 | 020/545 | T3 EI COLGATE-ALLEGHANY 20/545 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-03-17 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600086 | T3 EI COLGATE-ALLEGHANY 19/533 RPL STRW | 70Y
LC | 123145351 | 019/539 | T3 EI COLGATE-ALLEGHANY 19/539 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-03-17 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600086 | T3 EI COLGATE-ALLEGHANY 19/533 RPL STRW | 70Y
LC | 123145700 | 014/119 | WV T3 MONTA VISTA-BURNS RPR SWITCH | MOSSLNDG | ETL.7590.POLE.NWOD | 2022-03-17 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Switch-Wood | Repair | 45605906 | WV T3 MONTA VISTA-BURNS RPR SWITCH | ICW
LC | 123145866 | 002/016 | T3 EI RND MTN-TABLE MTN#1 2/16 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2022-03-17 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45644376 | T3 EI RND MTN-TABLE MTN#1 2/16 RPR STRT | ICQ
LC | 123146131 | 002/016 | EI T3 RND MTN-TABLE MTN#2 20/16 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2022-03-17 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123149766 | 010/002 | T3 PTTR VLLY-WILLITS 10/2 ARC FAULT CNCL | WILLITS | ETL.7820.POLE.WOOD | 2022-03-18 | 2022-03-10 |  | 2022-09-06 | 2022-09-10 | Late | ICX | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR OH TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Replace
LC | 123150135 | 003/025 | T3 DI TGR CRK VLLY SPRNGS 3/25 RMV STEP | VICTOR | ETL.5790.TOWR | 2022-03-18 | 2022-03-10 |  | 2022-09-06 | 2022-09-10 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45590782 | T3 DI TGR CRK VLLY SPRNGS 3/25 RMV STEP | ICQ
LC | 123150611 | 002/017 | T3 EI ROUND MTN-TBLE MTN #2 2/17 BNT STL | TABLEMTN | ETL.6070.TOWR | 2022-03-18 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123150672 | 000/003 | T3 DI MRGA-OAKLAND #4 000/003 RPR INSS | CONCORD | ETL.2750.INSL.CERA | 2022-03-18 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45507984 | T3 DI MRGA-OAKLAND #4 000/003 RPR INSS | ICS
LC | 123150681 | 020/548 | T3 EI COLGATE-ALLEGHANY20/548 RPL PL | SACTO | ETL.6470.POLE.WOOD | 2022-03-18 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600086 | T3 EI COLGATE-ALLEGHANY 19/533 RPL STRW | 70Y
LC | 123150683 | 020/549 | T3 EI COLGATE-ALLEGHANY 020/549 RPL PL | SACTO | ETL.6470.POLE.WOOD | 2022-03-18 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600086 | T3 EI COLGATE-ALLEGHANY 19/533 RPL STRW | 70Y
LC | 123150684 | 020/554 | T3 EI COLGATE-ALLEGHANY 20/554 RPL PL | SACTO | ETL.6470.POLE.WOOD | 2022-03-18 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600086 | T3 EI COLGATE-ALLEGHANY 19/533 RPL STRW | 70Y
LC | 123150694 | 020/553 | T3 EI COLGATE-ALLEGHANY 20/553 RPL PL | SACTO | ETL.6470.POLE.WOOD | 2022-03-18 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31600086 | T3 EI COLGATE-ALLEGHANY 19/533 RPL STRW | 70Y
LC | 123151056 | 002/018 | T3 EI ROUND MTN-TBLE MTN #1 2/18 RMV VE | TABLEMTN | ETL.6060.TOWR | 2022-03-18 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123151513 | 003/027 | T3 DI TGR CRK-ELECTRA 3/27 WASH INSW | VICTOR | ETL.5780.INSL.CERA | 2022-03-18 | 2022-03-10 |  | 2022-09-06 | 2022-09-10 | Late | 622 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | Contaminated | Insulator | Ground Wash | 45519430 | T3 DI TGR CRK-ELECTRA 3/27 WASH INSW | ICD
LC | 123151565 | 002/018 | T3 EI ROUND MTN-TBLE MTN #2 2/18 BNT STL | TABLEMTN | ETL.6070.TOWR | 2022-03-18 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123151566 | 002/018 | T3 EI ROUND MTN-TBLE MTN #2 2/18 RMV VEG | TABLEMTN | ETL.6070.TOWR | 2022-03-18 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123151942 | 002/020 | T3 DI ATSCDR CYCS 2/20 LF WD PL RPL STRW | PISMOBCH | ETL.8480.POLE.WDPS | 2022-03-18 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31609238 | T2 EI ATASCADERO-CAYUCOS 1/17 RPL POLE | 70Y
LC | 123152052 | 002/020 | T3 DI ATSCDR CYCS 2/20 WD PL RPL STRW | PISMOBCH | ETL.8480.POLE.WDPS | 2022-03-18 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31609238 | T2 EI ATASCADERO-CAYUCOS 1/17 RPL POLE | 70Y
LC | 123152054 | 002/020 | T3 DI ATSCDR CYCS 2/20 CTR WD P RPL STRW | PISMOBCH | ETL.8480.POLE.WDPS | 2022-03-18 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31609238 | T2 EI ATASCADERO-CAYUCOS 1/17 RPL POLE | 70Y
LC | 123152304 | 003/019 | T3 EI ROUND MTN-TBLE MTN #2 3/19 BNT STL | TABLEMTN | ETL.6070.TOWR | 2022-03-18 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123152333 | 002/025 | T3 DI ATSCDRO-CAYUCOS 002/025 INS HRDD | PISMOBCH | ETL.8480.POLE.WOOD | 2022-03-18 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW ACCM OH TR3 PRTO AIR FRAB | Missing | Hardware-Wood | Install | 45600497 | T3 DI ATSCDRO-CAYUCOS 002/025 INS HRDD | ICW
LC | 123152681 | 022/006 | T3 DI MI-WUK-CURTIS 022/006L RPL POLE | VICTOR | ETL.1073.POLE.WDPS | 2022-03-18 | 2022-03-11 |  | 2022-09-07 | 2022-09-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Rotten | Structure-Wood | Replace | 31629711 | T3 DI MI-WUK-CURTIS 020/004L RPL POLE | 70Y
LC | 123152738 | 003/020 | T3 EI ROUND MTN-TBLE MTN #2 3/20 BNT STL | TABLEMTN | ETL.6070.TOWR | 2022-03-18 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123153126 | 003/020 | T3 EI ROUND MTN-TBLE MTN #1 3/20 BNT STL | TABLEMTN | ETL.6060.TOWR | 2022-03-18 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45644400 | T3 EI ROUND MTN-TBLE MTN #1 3/20 BNT STL | ICQ
LC | 123154902 | 001/010 | T3 DI MORAGA-OAKLAND #1 001/010 RPR FOND | CONCORD | ETL.2720.TOWR | 2022-03-19 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123154903 | 001/010 | T3 DI MORAGA-OAKLAND #1 001/010 INS HRDD | CONCORD | ETL.2720.TOWR | 2022-03-19 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install
LC | 123154908 | 026/101 | T3 DI PITSBURG-SAN MATEO 26/101 RPR INSS | CONCORD | ETL.5463.INSL | 2022-03-19 | 2022-03-10 |  | 2022-09-06 | 2022-09-10 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45514935 | T3 DI PITSBURG-SAN MATEO 26/101 RPR INSS | ICS
LC | 123154913 | 052/291 | T3 DI TEMBLOR-SLO 52/291 INS STEP | PISMOBCH | ETL.3960.TOWR | 2022-03-19 | 2022-03-11 |  | 2022-09-07 | 2022-09-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45634831 | T3 DI TEMBLOR-SLO 52/291 INS STEP | ICQ
LC | 123155124 | 003/023 | T3 DI TGR CRK ELCT 3/23 CRM INSL RPL INS | VICTOR | ETL.5780.INSL | 2022-03-19 | 2022-03-15 |  | 2022-09-11 | 2022-09-15 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31600869 | T3 DI TGR CRK ELCT RPL INSS 5TWR | 93K
LC | 123155125 | 002/014 | T3 DI MORAGA-OAKLAND #1 2/14 INS HRDT | CONCORD | ETL.2720.TOWR | 2022-03-19 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Missing | Hardware-Tower | Install
LC | 123155127 | 002/014 | T3 DI MORAGA-OAKLAND #1 2/14 RPR STRT | CONCORD | ETL.2720.TOWR | 2022-03-19 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123155238 | 008/142 | T3 DI ATASCADERO-SLO 008/142 RPR STRS | PISMOBCH | ETL.8490.TOWR | 2022-03-19 | 2022-03-09 |  | 2022-09-05 | 2022-09-09 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45634832 | T3 DI ATASCADERO-SLO 008/142 RPR STRS | ICQ
LC | 123155259 | 014/107 | T3 DI TRINITY-CTTNWD 014/107 INS RPTS | TABLEMTN | ETL.4040.POLE.STPS | 2022-03-19 | 2022-03-15 |  | 2022-09-11 | 2022-09-15 | Late | 672 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | Missing | Raptor Guard-Wood | Install
LC | 123155469 | 008/063 | T3 DI TGR CRK-ELECTRA 008/063 RPR STRT | VICTOR | ETL.5780.TOWR | 2022-03-19 | 2022-03-15 |  | 2022-09-11 | 2022-09-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45590785 | T3 DI TGR CRK-ELECTRA 008/063 RPR STRT | ICQ
LC | 123155554 | 020/004 | T3 DI MI-WUK-CURTIS 20/4 RPL POLE | VICTOR | ETL.1073.POLE.WDPS | 2022-03-19 | 2022-03-15 |  | 2022-09-11 | 2022-09-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45519204 | T3 DI MI-WUK-CURTIS 20/4 RPL POLE | ICW
LC | 123155600 | 022/000 | T3 DI MI-WUK-CURTIS 022/000L RPR CRSW | VICTOR | ETL.1073.POLE.STPS | 2022-03-19 | 2022-03-11 |  | 2022-09-07 | 2022-09-11 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31603495 | T3 DI MI-WUK-CURTIS 022/000L RPR CRSW | 93E
LC | 123155780 | 003/023 | T3 DI TGR CRK-VLLY SPRNGS 3/23 RPL HRDT | VICTOR | ETL.5790.TOWR | 2022-03-19 | 2022-03-10 |  | 2022-09-06 | 2022-09-10 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45590786 | T3 DI TGR CRK-VLLY SPRNGS 3/23 RPL HRDT | ICQ
LC | 123156018 | 001/028 | T3 DI PINEGROVE TAP 01/28 RPL STRW | VICTOR | ETL.8351.POLE.WOOD | 2022-03-19 | 2022-03-16 |  | 2022-09-12 | 2022-09-16 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31603297 | T2 DI PINE GROVE TAP 002/061 RPL STRW | 70Y
LC | 123156324 | 002/017 | T3 DI MORAGA-OAKLAND #1 02/17 RPL HRDT | CONCORD | ETL.2720.TOWR | 2022-03-19 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123156486 | 008/064 | T3 DI TIGR CRK-VALY SPRNGS 8/64 RPL INSS | VICTOR | ETL.5790.INSL.CERA | 2022-03-19 | 2022-03-15 |  | 2022-09-11 | 2022-09-15 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31599750 | T3 DI TIGER CREK-VLLY SPRG RPL INSS 2TW | 93K
LC | 123156523 | 020/003A | T3 DI MI-WUK-CURTIS 020/003A RPR GYWW | VICTOR | ETL.1073.POLE.NWOD | 2022-03-19 | 2022-03-16 |  | 2022-09-12 | 2022-09-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45519209 | T3 DI MI-WUK-CURTIS 020/003A RPR GYWW | ICW
LC | 123159651 | 004/070 | T3 DI SISQUOC-GAREY 4/70 RPR IBWW | PISMOBCH | ETL.3690.POLE.WOOD | 2022-03-21 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45604904 | T3 DI SISQUOC-GAREY 4/70 RPR IBWW | ICW
LC | 123159659 | 005/041 | T3 DI SOBRANTE-MORAGA 5/41 RPR SPLS | CONCORD | ETL.3742.INSL.CERA | 2022-03-21 | 2022-03-16 |  | 2022-09-12 | 2022-09-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45513106 | T3 DI SOBRANTE-MORAGA 5/41 RPR SPLS | ICS
LC | 123160679 | 001/029 | T3 DI IGNCIO BLNAS #1 1/29 RPL POLE | LAKEVLLE | ETL.7140.POLE.WOOD | 2022-03-21 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606078 | T3 DI IGNCIO BLNAS #1 1/29 RPL POLE | 70Y
LC | 123161138 | 004/023 | T3 EI RND MTN-TBLE MTN #2 4/23 BNT STEEL | TABLEMTN | ETL.6070.TOWR | 2022-03-21 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123161221 | 022/006 | T3 DI MI-WUK-CURTIS 022/006R RPL POLE | VICTOR | ETL.1073.POLE.WDPS | 2022-03-21 | 2022-03-11 |  | 2022-09-07 | 2022-09-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Rotten | Structure-Wood | Replace | 31629711 | T3 DI MI-WUK-CURTIS 020/004L RPL POLE | 70Y
LC | 123162228 | 004/023 | T3 EI RND MTN-TBLE MTN #1 4/23 BNT STEEL | TABLEMTN | ETL.6060.POLE.NWOD | 2022-03-21 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45644378 | T3 EI RND MTN-TBLE MTN #1 4/23 BNT STEEL | ICQ
LC | 123162451 | 004/024 | T3 EI ROND MTN-TBL MTN #1 4/24 BNT STEEL | TABLEMTN | ETL.6060.TOWR | 2022-03-21 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45644402 | T3 EI ROND MTN-TBL MTN #1 4/24 BNT STEEL | ICQ
LC | 123162824 | 004/025 | T3 EI ROUND MTN-TBLE MTN #2 4/25 RMV VEG | TABLEMTN | ETL.6070.TOWR | 2022-03-21 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | Overgrown | Vegetation | Remove
LC | 123164557 | 004/026 | T3 EI RND MTN-TBLE MTN #1 4/26 BNT STEEL | TABLEMTN | ETL.6060.TOWR | 2022-03-22 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45644404 | T3 EI RND MTN-TBLE MTN #1 4/26 BNT STEEL | ICQ
LC | 123164580 | 004/026 | T3 EI ROUND MTN-TBLE MTN #1 4/26 RMV VEG | TABLEMTN | ETL.6060.TOWR | 2022-03-22 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | Overgrown | Vegetation | Remove
LC | 123164610 | 004/026 | T3 EI RND MTN-TABLE MTN #2 4/26 RPL INSS | TABLEMTN | ETL.6070.INSL | 2022-03-22 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617251 | T3 DI RND MTN TBL MTN#2 2/015 RPL INSS | 93K
LC | 123164784 | 004/025 | T3 EI ROUND MTN-TBLE MTN #1 4/25 RMV VEG | TABLEMTN | ETL.6060.TOWR | 2022-03-22 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | Overgrown | Vegetation | Remove
LC | 123165142 | 002/022 | T3 DI ATSCDRO-CYUCOS 2/22R RPL POLE | PISMOBCH | ETL.8480.POLE.WDPS | 2022-03-22 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31609301 | T3 DI ATSCDRO-CYUCOS 2/22L RPL POLE | 70Y
LC | 123165192 | 002/022 | T3 DI ATSCDRO-CYUCOS 2/22L RPL POLE | PISMOBCH | ETL.8480.POLE.WDPS | 2022-03-22 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31609301 | T3 DI ATSCDRO-CYUCOS 2/22L RPL POLE | 70Y
LC | 123165251 | 002/022 | T3 DI ATSCDRO-CYUCOS 2/22C RPL POLE | PISMOBCH | ETL.8480.POLE.WDPS | 2022-03-22 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31609301 | T3 DI ATSCDRO-CYUCOS 2/22L RPL POLE | 70Y
LC | 123165478 | 004/027 | T3 EI ROUND MTN-TBLE MTN #1 4/27 RMV VEG | TABLEMTN | ETL.6060.TOWR | 2022-03-22 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | Overgrown | Vegetation | Remove
LC | 123165517 | 004/027 | T3 EI RND MTN-TBLE MTN #2 4/27 RMV VEG | TABLEMTN | ETL.6070.TOWR | 2022-03-22 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123165542 | 004/027 | T3 EI RND MTN-TBLE MTN #2 4/27 BNT STEEL | TABLEMTN | ETL.6070.TOWR | 2022-03-22 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123166138 | 022/599 | T3 EI COLGATE-ALLEGHANY 22/599 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-22 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31600087 | T3 EI COLGATE-ALLEGHANY 21/568 RPL POLE | 70Y
LC | 123166793 | 020/004 | T3 DI MI-WUK-CURTIS 020/004L RPL POLE | VICTOR | ETL.1073.POLE.WDPS | 2022-03-22 | 2022-03-15 |  | 2022-09-11 | 2022-09-15 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31629711 | T3 DI MI-WUK-CURTIS 020/004L RPL POLE | 70Y
LC | 123166905 | 005/029 | T3 EI RND MTN-TBLE MTN #2 5/29 REGRADE | TABLEMTN | ETL.6070.TOWR | 2022-03-22 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45456821 | T3 EI RND MTN-TBLE MTN #2 5/29 REGRADE | ICS
LC | 123167369 | 005/029 | T3 EI ROUND MTN-TBLE MTN #1 5/29 RMV VEG | TABLEMTN | ETL.6060.TOWR | 2022-03-22 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | Overgrown | Vegetation | Remove
LC | 123167656 | T-124 | T3 EI MDWY-SNT MR (12KV) T-124 RPR CNDS | PISMOBCH | ETL.9240.TOWR | 2022-03-22 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair | 45605025 | T3 EI MDWY-SNT MR (12KV) T-124 RPR CNDS | ICS
LC | 123167782 | 005/030 | T3 EI RND MTN-TBLE MTN #2 5/30 RPR GYWS | TABLEMTN | ETL.6070.TOWR | 2022-03-22 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45456822 | T3 EI RND MTN-TBLE MTN #2 5/30 RPR GYWS | ICS
LC | 123171610 | 005/032 | T3 EI RND MTN-TBLE MTN #2 5/32 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2022-03-23 | 2022-03-23 |  | 2022-09-19 | 2022-09-23 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123173001 | 004/057 | T3 DI WST PT-VLLY SPRNGS 4/57 RPR STRW | VICTOR | ETL.8350.POLE.WOOD | 2022-03-23 | 2022-03-15 |  | 2022-09-11 | 2022-09-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45519435 | T3 DI WST PT-VLLY SPRNGS 4/57 RPR STRW | ICW
LC | 123173975 | 006/035 | T3 EI RND MTN-TBLE MTN #2 06/35 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2022-03-23 | 2022-03-23 |  | 2022-09-19 | 2022-09-23 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123176569 | 006/036 | T3 EI RND MTN-TBLE MTN #2 06/36 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2022-03-23 | 2022-03-23 |  | 2022-09-19 | 2022-09-23 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123176918 | 013/104 | T3 DI TRINITY-COTNWD-WD 13/104L RPL STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2022-03-23 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31618699 | T2 DI TRINITY-COTTONWOOD 9/72A RPL POLE | 70Y
LC | 123176961 | 013/104 | T3 DI TRINITY-COTNWD-WD 13/104R RPL STRW | TABLEMTN | ETL.4040.POLE.WDPS | 2022-03-23 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31618699 | T2 DI TRINITY-COTTONWOOD 9/72A RPL POLE | 70Y
LC | 123178164 | T057 | T3 DI MIDWAY-SANTA MARIA T057 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2022-03-24 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45634861 | T3 DI MIDWAY-SANTA MARIA T057 RPR FOND | ICQ
LC | 123181499 | 006/038 | T3 EI RND MTN-TABLE MTN #1 6/38 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2022-03-24 | 2022-03-24 |  | 2022-09-20 | 2022-09-24 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45458627 | T3 EI RND MTN-TABLE MTN #1 6/38 RPR GYWS | ICS
LC | 123181650 | 007/039 | T3 EI RND MTN-TBLE MTN #1 7/39 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2022-03-24 | 2022-03-24 |  | 2022-09-20 | 2022-09-24 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45302529 | T3 EI RND MTN-TBLE MTN #1 7/39 RPR STRT | ICS
LC | 123181653 | 007/040 | T3 EI RND MTN-TABLE MTN #2 7/40 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2022-03-24 | 2022-03-24 |  | 2022-09-20 | 2022-09-24 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123182759 | 007/042 | T3 EI RND MTN-TABLE MTN #2 7/42 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2022-03-24 | 2022-03-24 |  | 2022-09-20 | 2022-09-24 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123183822 | 002/016 | T3 DI MORAGA-OAKLAND #3 2/16 BENT STEEL | CONCORD | ETL.2740.TOWR | 2022-03-24 | 2022-03-15 |  | 2022-09-11 | 2022-09-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123184162 | T042 | T3 DI MIDWY-SNT MR (12KV) T42 BNT STEEL | PISMOBCH | ETL.9240.TOWR | 2022-03-24 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45634864 | T3 DI MIDWY-SNT MR (12KV) T42 BNT STEEL | ICQ
LC | 123184702 | 019/159 | T3 DI MISURI FT-OLD HL#1 19/159 RPR STRT | SACTO | ETL.2660.TOWR | 2022-03-24 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45582136 | T3 DI MISURI FT-OLD HL#1 19/159 RPR STRT | ICQ
LC | 123187120 | 006/052 | T3 DI TIGER CREEK-ELECTRA 6/52 REGRADE | VICTOR | ETL.5780.TOWR | 2022-03-25 | 2022-03-15 |  | 2022-09-11 | 2022-09-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45590790 | T3 DI TIGER CREEK-ELECTRA 6/52 REGRADE | ICQ
LC | 123187369 | 016/109 | T3 DI MTCLF-GRN VLLY 16/109R RPL POLE | MOSSLNDG | ETL.2540.POLE.WDPS | 2022-03-25 | 2022-03-16 |  | 2022-09-12 | 2022-09-16 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31611517 | T3 DI METCALF-GRN VLLY 17/118 RPL STRW | 70Y
LC | 123187440 | 016/109 | T3 DI MTCLF-GRN VLLY 16/109L RPL POLE | MOSSLNDG | ETL.2540.POLE.WDPS | 2022-03-25 | 2022-03-16 |  | 2022-09-12 | 2022-09-16 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31611517 | T3 DI METCALF-GRN VLLY 17/118 RPL STRW | 70Y
LC | 123187968 | 015/118 | T3 DI TRINITY-COTTONWD-STL 15/18 REGRADE | TABLEMTN | ETL.4040.POLE.STPS | 2022-03-25 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123188106 | 041/183 | T3 DI MTCF-MOS LNDNG #1 41/183 RPR FOND | MOSSLNDG | ETL.5100.TOWR | 2022-03-25 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123188159 | 008/044 | T3 EI RND MTN-TBLE MTN #1 08/44 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2022-03-25 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45644410 | T3 EI RND MTN-TBLE MTN #1 08/44 RPR STRT | ICQ
LC | 123188591 | 008/045 | T3 EI RND MTN-TBLE MTN #1 08/45 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2022-03-25 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45644411 | T3 EI RND MTN-TBLE MTN #1 08/45 RPR STRT | ICQ
LC | 123189081 | -014/002 | T3 DI FULTON-CALISTOGA -014/002 RMV BUTT | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-03-25 | 2022-03-19 |  | 2022-09-15 | 2022-09-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45485893 | T3 DI FULTON-CALISTOGA -014/002 RMV BUTT | ICW
LC | 123189130 | 007/057 | T3 DI TGER CREK-VALLEY SGS 7/57 RPL HRDT | VICTOR | ETL.5790.TOWR | 2022-03-25 | 2022-03-15 |  | 2022-09-11 | 2022-09-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45590791 | T3 DI TGER CREK-VALLEY SGS 7/57 RPL HRDT | ICQ
LC | 123189135 | 014/000 | T3 DI MNTE RIO-FLTON-FLTON 14/0 RPL STRW | LAKEVLLE | ETL.7630.POLE.WOOD | 2022-03-25 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31624227 | T0 EI MONTE RIO-FULTON 007/002 RPL STRW | 70Y
LC | 123189865 | 008/046 | T3 EI RND MTN-TBLE MTN #2 08/46 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2022-03-25 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123189986 | 005/070 | T3 DI WEIMAR #1 5/70 RPR INSW | SACTO | ETL.7560.INSL.NCER | 2022-03-25 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair | 45568994 | T3 DI WEIMAR #1 5/70 RPR INSW | ICW
LC | 123190492 | 005/059 | T3 DI WST PT-VLLY SPRNG 5/59 RPL HRDD | VICTOR | ETL.8350.POLE.NWOD | 2022-03-25 | 2022-03-15 |  | 2022-09-11 | 2022-09-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45519438 | T3 DI WST PT-VLLY SPRNG 5/59 RPL HRDD | ICW
LC | 123191116 | 002/016 | T3 DI TIGER CREK-VLLY SPRG 2/16 RPL INSS | VICTOR | ETL.5790.INSL.CERA | 2022-03-25 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31599750 | T3 DI TIGER CREK-VLLY SPRG RPL INSS 2TW | 93K
LC | 123192363 | 008/047 | T3 EI RND MTN-TBL MTN #2 08/47 RPR GYWS | TABLEMTN | ETL.6070.TOWR | 2022-03-25 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45302530 | T3 EI RND MTN-TBL MTN #2 08/47 RPR GYWS | ICS
LC | 123192364 | 008/047 | T3 EI RND MTN-TBLE MTN #2 08/47 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2022-03-25 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123193028 | 008/048 | T3 EI RND MTN-TBLE MTN #1 08/48 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2022-03-25 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45458628 | T3 EI RND MTN-TBLE MTN #1 08/48 RPR GYWS | ICS
LC | 123193215 | 008/048 | T3 EI RND MTN-TBLE MTN #2 08/48 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2022-03-25 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123195453 | 014/114 | T3 DI TRNTY CTNWD 14/114L INS HRDD | TABLEMTN | ETL.4040.POLE.STPS | 2022-03-25 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | Missing | Hardware-Wood | Install
LC | 123196335 | :005/006 | T3 DI FULTON-CALISTOGA :005/006 REGRADE | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-03-26 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123196337 | 005/004 | T3 DI FULTON-CALISTOGA 005/004 REGRADE | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-03-26 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAR | No Good/Out of Stdrd | Structure-Wood | Repair | 45485550 | T3 DI FULTON-CALISTOGA 005/004 REGRADE | ICW
LC | 123196519 | 000/009 | T3 DI GYSRS #3-CLVRDLE 0/9 RPR HRDW | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-03-26 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45575593 | T3 DI GYSRS #3-CLVRDLE 0/9 RPR HRDW | ICW
LC | 123196575 | 008/096 | T3 DI GYSRS #3-CLVRDLE 8/96 RPL HRDD | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-03-26 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45575594 | T3 DI GYSRS #3-CLVRDLE 8/96 RPL HRDD | ICW
LC | 123196609 | 022/007 | T3 DI MI-WUK-CURTIS 22/7 RMV DEBRIS | VICTOR | ETL.1073.POLE.STPS | 2022-03-26 | 2022-03-11 |  | 2022-09-07 | 2022-09-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45519240 | T3 DI MI-WUK-CURTIS 22/7 RMV DEBRIS | ICW
LC | 123196632 | 000/005 | T3 DI MORAGA-SN LNDRO #1 0/5 BENT STEEL | CONCORD | ETL.2770.TOWR | 2022-03-26 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123196638 | 000/005 | T3 DI MORAGA-SN LNDRO #1 0/5 RPL HRDT | CONCORD | ETL.2770.INSL | 2022-03-26 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123196646 | 009/110 | T3 DI GYSRS #3-CLVRDLE 9/110 RPR INSW | LAKEVLLE | ETL.1650.INSL.NCER | 2022-03-26 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45575596 | T3 DI GYSRS #3-CLVRDLE 9/110 RPR INSW | ICW
LC | 123196647 | 009/110 | T3 DI GYSRS #3-CLVRDLE 9/110 RMV BUTT | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-03-26 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45575595 | T3 DI GYSRS #3-CLVRDLE 9/110 RMV BUTT | ICW
LC | 123196671 | 000/005 | T3 DI MORAGA-SN LNDRO #1 0/5 INS HRDT | CONCORD | ETL.2770.TOWR | 2022-03-26 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install
LC | 123196695 | 017/118 | T3 DI METCALF-GRN VLLY 17/118 RPL STRW | MOSSLNDG | ETL.2540.POLE.WDPS | 2022-03-26 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611517 | T3 DI METCALF-GRN VLLY 17/118 RPL STRW | 70Y
LC | 123196699 | 017/118 | T3 DI METCALF-GRN VLLY 17/118 RPL STRW | MOSSLNDG | ETL.2540.POLE.WDPS | 2022-03-26 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611517 | T3 DI METCALF-GRN VLLY 17/118 RPL STRW | 70Y
LC | 123196716 | :004/013 | T3 DI FULTON-CALISTOGA :04/13 INS IBWW | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-03-26 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45571426 | T3 DI FULTON-CALISTOGA :04/13 INS IBWW | ICW
LC | 123196784 | T053 | T3 DI MDWY-SNT MR (12KV) T53 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2022-03-26 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace
LC | 123196829 | T044 | T3 DI MDWY-SNT MR (12KV) T44 UNBURY | PISMOBCH | ETL.9240.TOWR | 2022-03-26 | 2022-03-17 |  | 2022-09-13 | 2022-09-17 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45638426 | T3 DI MDWY-SNT MR (12KV) T44 UNBURY | ICQ
LC | 123196983 | 001/011 | T3 DI MORAGA-OAKLAND #1 1/11 RMV DEBRIS | CONCORD | ETL.2720.INSL | 2022-03-26 | 2022-03-14 |  | 2022-09-10 | 2022-09-14 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Steel | Remove | 45502974 | T3 DI MORAGA-OAKLAND #1 1/11 RMV DEBRIS | ICS
LC | 123196987 | 007/047 | T3 DI SBRT-GRZLY-CLRMT #2 7/47 BNT STEEL | CONCORD | ETL.3750.TOWR | 2022-03-26 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123197150 | :004/002 | T3 DI FULTON-CLSTGA :004/002 RPL HRDW | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-03-26 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45571447 | T3 DI FULTON-CLSTGA :004/002 RPL HRDW | ICW
LC | 123197515 | 043/245 | T3 DI TMBLR SN LS OBSP 43/245 BENT STEEL | PISMOBCH | ETL.3960.TOWR | 2022-03-26 | 2022-03-15 |  | 2022-09-11 | 2022-09-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45638430 | T3 DI TMBLR SN LS OBSP 43/245 BENT STEEL | ICQ
LC | 123197563 | 005/001 | T3 DI FLTN CLSTG 5/1 RPR STRW | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-03-26 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE ACCL OH TR3 PRTO AIR FRAR NTDE | No Good/Out of Stdrd | Structure-Wood | Repair | 45575464 | T3 DI FLTN CLSTG 5/1 RPR STRW | ICW
LC | 123197869 | T066 | T3 DI MDWY-SNT MR (12KV) T66 RPR JMPS | PISMOBCH | ETL.9240.TOWR | 2022-03-26 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Jumper-Steel | Repair | 45605026 | T3 DI MDWY-SNT MR (12KV) T66 RPR JMPS | ICS
LC | 123197983 | :002/004 | T3 DI FULTON CALISTOGA :002/004 RPL STRW | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-03-26 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606073 | T3 DI FULTON CALISTOGA :002/004 RPL STRW | 70Y
LC | 123201004 | 009/049 | T3 EI RND MTN-TBLE MTN #1 9/49 BNT STEEL | TABLEMTN | ETL.6060.TOWR | 2022-03-28 | 2022-03-28 |  | 2022-09-24 | 2022-09-28 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45644412 | T3 EI RND MTN-TBLE MTN #1 9/49 BNT STEEL | ICQ
LC | 123201005 | 009/049 | T3 EI RND MTN-TBLE MTN #1 9/49 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2022-03-28 | 2022-03-28 |  | 2022-09-24 | 2022-09-28 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB NTDE | No Good/Out of Stdrd | Ground Wire-Steel | Repair | 45458631 | T3 EI RND MTN-TBLE MTN #1 9/49 RPR GYWS | ICS
LC | 123203419 | T068 | T3 DI MDWY-SNT MR (12KV) T68 BNT STEEL | PISMOBCH | ETL.9240.TOWR | 2022-03-28 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45638431 | T3 DI MDWY-SNT MR (12KV) T68 BNT STEEL | ICQ
LC | 123204312 | 022/005 | T3 DI FULTON-HOPLAND 022/005 RPR CRSW | LAKEVLLE | ETL.6890.POLE.WOOD | 2022-03-28 | 2022-03-23 |  | 2022-09-19 | 2022-09-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45571448 | T3 DI FULTON-HOPLAND 022/005 RPR CRSW | ICW
LC | 123204588 | 020/006B | T3 DI MI-WUK-CURTIS 20/6B RPR STRW | VICTOR | ETL.1073.POLE.WOOD | 2022-03-28 | 2022-03-23 |  | 2022-09-19 | 2022-09-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45519248 | T3 DI MI-WUK-CURTIS 20/6B RPR STRW | ICW
LC | 123207071 | 021/011 | T3 WV MAPLE CREEK-HOOPA 21/011 RPR SPLW | EUREKA | ETL.7490.INSL | 2022-03-29 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 123209103 | 022/613 | T3 EI COLGATE-ALLEGHANY 22/613 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-29 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31600087 | T3 EI COLGATE-ALLEGHANY 21/568 RPL POLE | 70Y
LC | 123209104 | 022/617 | T3 EI COLGATE-ALLEGHANY 22/617 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-29 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31600087 | T3 EI COLGATE-ALLEGHANY 21/568 RPL POLE | 70Y
LC | 123210317 | 007/115 | T3 DI WEIMAR #1 007/115 RPR INSW | SACTO | ETL.7560.INSL.CERA | 2022-03-29 | 2022-03-24 |  | 2022-09-20 | 2022-09-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123210345 | 022/336 | T3 DI GOLD HILL #1 022/336 RPR GYWW | SACTO | ETL.6950.POLE.NWOD | 2022-03-29 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123210637 | 001/024 | T3 DI IGNACIO-BOLINAS #2 001/24 RPL HRDW | LAKEVLLE | ETL.7180.POLE.WOOD | 2022-03-29 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45575601 | T3 DI IGNACIO-BOLINAS #2 001/24 RPL HRDW | ICW
LC | 123210644 | 018/277 | T3 DI GOLD HILL #1 18/277 RPR GYWW | SACTO | ETL.6950.POLE.WOOD | 2022-03-29 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123210704 | 019/158 | T3 DI MIDDLE FK-GLD HILL 19/158 RPR INSW | SACTO | ETL.5140.INSL.NCER | 2022-03-29 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123211302 | 000/009 | T3 DI KONOCTI-EAGLE ROCK 0/9 RPR INSW | WILLITS | ETL.6861.INSL.CERA | 2022-03-30 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123213974 | 027/009 | T3 DI FULTON-HOPLAND 27/9 RPR INSW | LAKEVLLE | ETL.6890.INSL | 2022-03-30 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45571438 | T3 DI FULTON-HOPLAND 27/9 RPR INSW | ICW
LC | 123214152 | 011/042 | T3 EI DIABLO-MIDWAY #2 011/042 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2022-03-30 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45638434 | T3 EI DIABLO-MIDWAY #2 011/042 RPR GYWS | ICS
LC | 123216099 | 000/006 | T3 DI MORAGA-SN LNDRO #1 0/6 RPR JMPS | CONCORD | ETL.2770.INSL | 2022-03-30 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Steel | Repair | 45514937 | T3 DI MORAGA-SN LNDRO #1 0/6 RPR JMPS | ICS
LC | 123216495 | 013/060 | T3 WV SAN LS OBSP-OCN 13/60 RPL INSS | PISMOBCH | ETL.3530.INSL.CERA | 2022-03-30 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619482 | T2 WV SN LUS OBSPO-OCANO 9/41 RPL INSS | 93K
LC | 123216533 | 013/057 | T3 WV SAN LUIS OBSP-OCN 13/57 RPL INSS | PISMOBCH | ETL.3530.INSL.CERA | 2022-03-30 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619482 | T2 WV SN LUS OBSPO-OCANO 9/41 RPL INSS | 93K
LC | 123216592 | 013/006 | T3 DI UKIAH-HOPLAND-CLOVRDL 13/6 REGRADE | WILLITS | ETL.4050.POLE.NWOD | 2022-03-30 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45487315 | T3 DI UKIAH-HOPLAND-CLOVRDL 13/6 REGRADE | ICW
LC | 123216634 | :005/011 | T3 DI FULTON-CALISTOGA :5/11 INS HRDD | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-03-30 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR NTDE | Missing | Hardware-Wood | Install
LC | 123216663 | 024/353 | T3 DI GOLD HILL #1 24/353 RPL POLE | SACTO | ETL.6950.POLE.WOOD | 2022-03-30 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606076 | T3 DI GLD HL #1 24/352 RPL STRW | 70Y
LC | 123216720 | T075 | T3 DI MDWY-SNT MR (12KV) T75 UNBURY | PISMOBCH | ETL.9240.TOWR | 2022-03-30 | 2022-03-26 |  | 2022-09-22 | 2022-09-26 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45638436 | T3 DI MDWY-SNT MR (12KV) T75 UNBURY | ICQ
LC | 123216745 | 011/163 | T3 DI GOLD HILL #1 11/163 RPR JUMW | SACTO | ETL.6950.INSL.NCER | 2022-03-30 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Wood | Repair
LC | 123216748 | 007/046 | T3 DI SBRNT-GRZLY-CLRNT #2 7/46 RPL HRDT | CONCORD | ETL.3750.TOWR | 2022-03-30 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123216762 | 007/113 | T3 DI WEIMAR #1 7/113 RPL IBWW | SACTO | ETL.7560.POLE.WOOD | 2022-03-30 | 2022-03-23 |  | 2022-09-19 | 2022-09-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123219448 | 023/342 | T3 DI GOLD HILL #1 23/342 RPR SPLW | SACTO | ETL.6950.INSL.CERA | 2022-03-31 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 123219449 | 023/342 | T3 DI GOLD HILL #1 23/342 RPL HRDD | SACTO | ETL.6950.POLE.NWOD | 2022-03-31 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123220316 | 003/035 | T3 DI ATASCDERO-CYUCOS 3/035 RPL INSW | PISMOBCH | ETL.8480.INSL.NCER | 2022-03-31 | 2022-03-18 |  | 2022-09-14 | 2022-09-18 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31633740 | T3 DI ATASCDERO-CYUCOS 3/035 RPL INSW | 93I
LC | 123221067 | 009/035 | T3 EI DIABLO-MIDWAY #2 9/35 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2022-03-31 | 2022-03-31 |  | 2022-09-27 | 2022-10-01 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45638564 | T3 EI DIABLO-MIDWAY #2 9/35 RPR GYWS | ICS
LC | 123221109 | 016/079 | T3 DI MNT VST CYT SS 16/79 RPR SHLW | MOSSLNDG | ETL.5090.TOWR | 2022-03-31 | 2022-03-19 |  | 2022-09-15 | 2022-09-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45381038 | T3 DI MNT VST CYT SS 16/79 RPR SHLW | ICS
LC | 123221309 | 010/278 | T3 CLGTE-ALLEGHENY 10/278 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-03-31 | 2022-03-31 |  | 2022-09-27 | 2022-09-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606404 | T3 COLGATE-ALLEGHANY 7/188 RPL POLE | 70Y
LC | 123222174 | 000/012 | T3 EI DRM-GRSS VLLEY-WEIMR 0/12 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2022-03-31 | 2022-03-31 |  | 2022-09-27 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123222983 | T061 | T3 MIDWAY-SANTA MARIA T061 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2022-03-31 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace
LC | 123223071 | :003/000 | T3 DI FLTN CLSTG 3/0 REFILL HOLE | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-03-31 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45575461 | T3 DI FLTN CLSTG 3/0 REFILL HOLE | ICW
LC | 123223113 | 041/237 | T3 DI TBLOR-SN LS OBSPO 41/237 BNT STEEL | PISMOBCH | ETL.3960.TOWR | 2022-03-31 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45638566 | T3 DI TBLOR-SN LS OBSPO 41/237 BNT STEEL | ICQ
LC | 123223399 | 005/005 | T3 DI FULTON-CALISTOGA 5/5 CANCEL | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-03-31 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO AIR FRAR | No Good/Out of Stdrd | Structure-Wood | Repair | 45571446 | T3 DI FULTON-CALISTOGA 5/5 RPR POLE | ICW
LC | 123225700 | 007/059 | T3 DI TGR CRK-ELCTRA 7/59 REFRAME | VICTOR | ETL.5780.POLE.STPS | 2022-04-01 | 2022-03-23 |  | 2022-09-19 | 2022-09-23 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Steel | Replace
LC | 123225785 | 021/002C | T3 DI MI-WUK-CURTIS 21/2C RPR POLE | VICTOR | ETL.1073.POLE.WOOD | 2022-04-01 | 2022-03-23 |  | 2022-09-19 | 2022-09-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45519250 | T3 DI MI-WUK-CURTIS 21/2C RPR POLE | ICW
LC | 123226134 | 004/053 | T3 WST PNT-VALLEY SPRINGS 4/53 RPR INSW | VICTOR | ETL.8350.INSL.NCER | 2022-04-01 | 2022-03-28 |  | 2022-09-24 | 2022-09-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair | 45519450 | T3 WST PNT-VALLEY SPRINGS 4/53 RPR INSW | ICW
LC | 123226498 | T078 | T3 DI MIDWAY-SANTA MARIA T078 BNT STEEL | PISMOBCH | ETL.9240.TOWR | 2022-04-01 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Tower | Repair | 45638571 | T3 DI MIDWAY-SANTA MARIA T078 BNT STEEL | ICQ
LC | 123226842 | 002/014 | T3 EI RND MTN-TABLE MTN #1 2/14 RMV VEG | TABLEMTN | ETL.6060.TOWR | 2022-04-01 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123226923 | 022/112 | T3 DI RND MNT-TBL MNT #2 22/112 RPR SHLS | TABLEMTN | ETL.6070.TOWR | 2022-04-01 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45456840 | T3 DI RND MNT-TBL MNT #2 22/112 RPR SHLS | ICS
LC | 123227163 | 005/036 | T3 EI SBRNT-GRZLY-CLRMT #2 5/36 RPL INSS | CONCORD | ETL.3750.INSL.CERA | 2022-04-01 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31604889 | T2 DI SBRNT-GRZLY-CLRMNT#2 RPL INSS 3TW | 93K
LC | 123227318 | 002/015 | T3 EI RND MTN-TBL MTN #1 2/15 RPR ANCHS | TABLEMTN | ETL.6060.TOWR | 2022-04-01 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Anchor-Steel | Repair | 45458638 | T3 EI RND MTN-TBL MTN #1 2/15 RPR ANCHS | ICS
LC | 123228056 | 000/017 | T3 EI DRM-GRSS VLEY-WEIMAR 0/17 RPL INSW | SACTO | ETL.6760.INSL.NCER | 2022-04-01 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617792 | T3 EI DRM-GRSS VLEY-WEIMAR 0/17 RPL INSW | 93I
LC | 123228069 | 007/029 | T3 EI DIABLO-MIDWAY #2 7/29 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2022-04-01 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45638578 | T3 EI DIABLO-MIDWAY #2 7/29 RPR GYWS | ICS
LC | 123228502 | T-119 | T3 DI MIDWAY-SANTA MARIA T-119 UNBURY | PISMOBCH | ETL.9240.TOWR | 2022-04-01 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45638579 | T3 DI MIDWAY-SANTA MARIA T-119 UNBURY | ICQ
LC | 123228652 | 008/046 | T3 EI RND MTN-TBL MTN #1 008/046 RMV VEG | TABLEMTN | ETL.6060.TOWR | 2022-04-01 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | Overgrown | Vegetation | Remove
LC | 123229933 | 016/008 | T3 DI UKH-HPLD-CLVRL-HPLND 16/8 RPL HRDD | WILLITS | ETL.4050.POLE.NWOD | 2022-04-01 | 2022-03-26 |  | 2022-09-22 | 2022-09-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45487837 | T3 DI UKH-HPLD-CLVRL-HPLND 16/8 RPL HRDD | ICW
LC | 123230214 | 005/061 | T3 DI WST PNT-VLLY SPNGS 5/61 RPR WDPKR | VICTOR | ETL.8350.POLE.WOOD | 2022-04-01 | 2022-03-22 |  | 2022-09-18 | 2022-09-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45519451 | T3 DI WST PNT-VLLY SPNGS 5/61 RPR WDPKR | ICW
LC | 123230699 | 010/001 | T3 DI POTTER VALLEY-WILLIT 10/1 RPL POLE | WILLITS | ETL.7820.POLE.WOOD | 2022-04-01 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31615506 | T2 WV POTTER VALLEY-WILLITS 5/0 RPL POLE | 70Y
LC | 123230850 | 007/062 | T3 DI ATASCADERO-CYUCS 7/62 INS IBWW | PISMOBCH | ETL.8480.POLE.WOOD | 2022-04-01 | 2022-03-26 |  | 2022-09-22 | 2022-09-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45600520 | T3 DI ATASCADERO-CYUCS 7/62 INS IBWW | ICW
LC | 123231038 | 001/024 | T3 EI DRUM-GRS VLEY-WEMR 1/24 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2022-04-01 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123231155 | 001/024 | T3 EI DRM-GRS VLEY-WMAR 1/24 RPL HRDW | SACTO | ETL.6760.POLE.WOOD | 2022-04-01 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123231231 | 001/026 | T3 EI VOLTA-DESCHUTES 1/26 REFRAME | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-01 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31617272 | T3 EI VOLTA-DESCHUTES 1/26 REFRAME | 93E
LC | 123231239 | 007/040 | T3 EI RND MTN-TBL MTN #1 07/040 RPR ANCS | TABLEMTN | ETL.6060.TOWR | 2022-04-01 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Anchor-Steel | Repair | 45458642 | T3 EI RND MTN-TBL MTN #1 07/040 RPR ANCS | ICS
LC | 123231271 | 004/038B | T3 DI SBNT-GRZLY-CLRMNT#1 4/38B RPR FOND | CONCORD | ETL.3740.TOWR | 2022-04-01 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123231280 | 007/041 | T3 EI RND MTN-TBL MTN #1 007/041 RMV VEG | TABLEMTN | ETL.6060.TOWR | 2022-04-01 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | Overgrown | Vegetation | Remove
LC | 123235027 | 000/004 | T3 EI ORO FINO TAP 0/4 RPR GYWW | TABLEMTN | ETL.6721.POLE.WOOD | 2022-04-02 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123235080 | 012/328 | T3 EI COLGATE-ALLEGHANY 12/328 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-04-02 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606404 | T3 COLGATE-ALLEGHANY 7/188 RPL POLE | 70Y
LC | 123235082 | 012/312 | T3 EI COLGATE-ALLEGHANY 12/312 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-04-02 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31633458 | T3 DI COLGATE-ALLGHNY 011/293 RPL STRW | 70Y
LC | 123235087 | 022/616 | T3 COLGATE-ALLEGHANY 22/616 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-04-02 | 2022-03-31 |  | 2022-09-27 | 2022-10-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR OH TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31605566 | HANY 15/402 RPL POLE | 70Y
LC | 123235177 | 017/002 | T3 DI MNTE RIO-FRT ROSS 17/2L RPR INSW | LAKEVLLE | ETL.6979.INSL.NCER | 2022-04-02 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair | 45575618 | T3 DI MNTE RIO-FRT ROSS 17/2L RPR INSW | ICW
LC | 123235179 | 017/002 | T3 DI MNTE RIO-FRT ROSS 17/2R RPR GYWW | LAKEVLLE | ETL.6979.POLE.WDPS | 2022-04-02 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45258510 | T3 DI MNTE RIO-FRT ROSS 17/2C RPR GYWW | ICW
LC | 123235220 | 017/002 | T3 DI MNTE RIO-FRT ROSS 17/2C RPR GYWW | LAKEVLLE | ETL.6979.POLE.WDPS | 2022-04-02 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45258510 | T3 DI MNTE RIO-FRT ROSS 17/2C RPR GYWW | ICW
LC | 123235221 | 017/002 | T3 DI MNTE RIO-FRT ROSS 17/2L RPR GYWW | LAKEVLLE | ETL.6979.POLE.WDPS | 2022-04-02 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45258510 | T3 DI MNTE RIO-FRT ROSS 17/2C RPR GYWW | ICW
LC | 123235224 | 017/081 | T3 DI CRTNA-MNDCNO #1 17/81 INS STEP | WILLITS | ETL.1330.TOWR | 2022-04-02 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45644070 | T3 DI CRTNA-MNDCNO #1 17/81 INS STEP | ICQ
LC | 123235368 | 000/006 | T3 EI KILARC-DESCHUTES 0/6 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617636 | T3 EI KILARC-DESCHUTES 0/6 RPL POLE | 70Y
LC | 123235751 | 011/292 | T3 EI COLGATE-ALLEGHANY 11/292 RPR POLE | SACTO | ETL.6470.POLE.WDPS | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123235785 | 001/036 | T3 EI VOLTA-DESCHUTES 1/36 RPR INSW | TABLEMTN | ETL.8290.INSL.NCER | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 45458386 | T3 EI VOLTA-DESCHUTES 1/36 RPR INSW | ICW
LC | 123235982 | 002/015 | T3 DI TGR CRK ELCT 2/15 RPL INSS | VICTOR | ETL.5780.INSL | 2022-04-02 | 2022-03-31 |  | 2022-09-27 | 2022-09-30 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31600869 | T3 DI TGR CRK ELCT RPL INSS 5TWR | 93K
LC | 123236291 | 004/028 | T3 EI RND MTN-TBLE MTN #1 4/28 RMV VEG | TABLEMTN | ETL.6060.TOWR | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123236364 | 000/013 | T3 EI KILARC-DESCHUTES 0/13 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606220 | T3 DI KILARC-DESCHUTES 000/005 RPL POLE | 70Y
LC | 123236390 | 001/041 | T3 EI VOLTA-DESCHUTES 1/41 REFRAME | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31617272 | T3 EI VOLTA-DESCHUTES 1/26 REFRAME | 93E
LC | 123236491 | 009/230 | T3 EI DRUM-G.V.-WEIMAR 9/230 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605825 | T3 DI DRM GRS VLY WMR 0/14 RPL STRW | 70Y
LC | 123236578 | 001/031 | T3 EI DRUM-GRS VLY-WMR 001/031 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617788 | T3 DI DRM-GRSS VLLY-WMR 6/154 RPL POLE | 70Y
LC | 123236649 | 011/297 | T3 EI COLGATE-ALLEGHANY 11/297 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606404 | T3 COLGATE-ALLEGHANY 7/188 RPL POLE | 70Y
LC | 123236680 | 011/296 | T3 EI COLGATE-ALLEGHANY 11/296 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606404 | T3 COLGATE-ALLEGHANY 7/188 RPL POLE | 70Y
LC | 123236681 | 011/298 | T3 EI COLGATE-ALLEGHANY 11/298 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606404 | T3 COLGATE-ALLEGHANY 7/188 RPL POLE | 70Y
LC | 123236702 | 001/033 | T3 DI DRM-GRS VLY-WMR 1/33 RPR ADSS | SACTO | ETL.6760.POLE.NWOD | 2022-04-02 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45253116 | T3 DI DRM-GRS VLY-WMR 1/33 RPR ADSS | ICW
LC | 123236966 | 002/033 | T3 EI DRUM-SUMMIT #2 2/33L RPR POLE | SACTO | ETL.1450.POLE.WDPS | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123237102 | 009/225 | T3 EI DRUM-GRS VALLEY-WEIMR 9/2 RPR GYWW | SACTO | ETL.6760.POLE.NWOD | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123237107 | 005/041 | T3 EI SOBRANTE-MORAGA 005/041 RPR GYWS | CONCORD | ETL.3742.POLE.NWOD | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45513115 | T3 EI SOBRANTE-MORAGA 005/041 RPR GYWS | ICS
LC | 123237184 | 000/002 | T3 DI ORO FINO TAP 0/2 RPL HRDW | TABLEMTN | ETL.6721.POLE.WOOD | 2022-04-02 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123237217 | 001/029 | T3 EI VOLTA-DESCHUTES 1/29 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45458391 | T3 EI VOLTA-DESCHUTES 1/29 RPL POLE | ICW
LC | 123237259 | 007/003 | T3 DI POTTER VALLEY-WILLI 7/3 ANTI SPLIT | WILLITS | ETL.7820.POLE.WOOD | 2022-04-02 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR FRAB | Missing | Hardware-Wood | Install
LC | 123237294 | 023/630 | T3 EI COLGATE-ALLEGHANY 23/630 RPR POLE | SACTO | ETL.6470.POLE.WOOD | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123237295 | 023/638 | T3 EI COLGATE-ALLEGHANY 23/638 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-04-02 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605566 | HANY 15/402 RPL POLE | 70Y
LC | 123239358 | 016/002 | T3 DI MNTE RIO-FRT RSS 16/002 RPR STRW | LAKEVLLE | ETL.6979.POLE.WDPS | 2022-04-04 | 2022-03-31 |  | 2022-09-27 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45575640 | T3 DI MNTE RIO-FRT RSS 16/002 RPR STRW | ICW
LC | 123239554 | 000/014 | T3 DI DRM GRS VLY WMR 0/14 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-04 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605825 | T3 DI DRM GRS VLY WMR 0/14 RPL STRW | 70Y
LC | 123241247 | 001/043 | T3 EI DRM-GRSS VLLY-WEIMR 1/43 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-04 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605825 | T3 DI DRM GRS VLY WMR 0/14 RPL STRW | 70Y
LC | 123242673 | T-111 | T3 DI MDWY SNT MR T-111 UNBURY | PISMOBCH | ETL.9240.TOWR | 2022-04-04 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45639034 | T3 DI MDWY SNT MR T-111 UNBURY | ICQ
LC | 123243243 | 002/048 | T3 EI DRM-GRSS VLLY-WEIMR 2/48 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-04 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605825 | T3 DI DRM GRS VLY WMR 0/14 RPL STRW | 70Y
LC | 123243771 | 016/007 | T3 DI UKIH-HPLND-CLVRDLE 16/7 RPL POLE | WILLITS | ETL.4050.POLE.WOOD | 2022-04-04 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31619395 | T2 EI UKH-HPLND-CLVRDLE 010/089 RPL STRW | 70Y
LC | 123243777 | 031/232 | T3 DI MDDL FRK-GLD HLL 31/232C RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2022-04-04 | 2022-03-23 |  | 2022-09-19 | 2022-09-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123245295 | 008/207 | T3 EI DRM-GRSS VLLY-WMR 8/207 RPR CRSW | SACTO | ETL.6760.POLE.WOOD | 2022-04-05 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair
LC | 123247670 | 002/056 | T3 EI VOLTA-DESCHUTES 2/56 RPR WDPKR | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-05 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45458393 | T3 EI VOLTA-DESCHUTES 2/56 RPR WDPKR | ICW
LC | 123248022 | :026/009 | T3 DI FLTN HPLND 26/9 INS HRDW | LAKEVLLE | ETL.6890.POLE.WOOD | 2022-04-05 | 2022-03-23 |  | 2022-09-19 | 2022-09-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | Missing | Hardware-Wood | Install | 45575465 | T3 DI FLTN HPLND 26/9 INS HRDW | ICW
LC | 123248448 | 002/041 | T3 DI CENTER-TABLE MTN 2/041 RPL POLE | TABLEMTN | ETL.6320.POLE.WOOD | 2022-04-05 | 2022-03-31 |  | 2022-09-27 | 2022-09-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31622215 | T3 DI CENTER-TABLE MTN 2/041 RPL POLE | 70Y
LC | 123248477 | 016/001B | T3 DI MNT RIO FRT-ROSS 16/1B RPL DAMW | LAKEVLLE | ETL.6979.INSL.NCER | 2022-04-05 | 2022-03-31 |  | 2022-09-27 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Wood | Replace | 45575611 | T3 DI MNT RIO FRT-ROSS 16/1B RPL DAMW | ICW
LC | 123248565 | 002/057 | T3 EI DRM-GRS VLEY-WMR 2/57 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2022-04-05 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123248980 | 002/062 | T3 EI VOLTA-DESCHUTES 2/62 REFRAME | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-05 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31617272 | T3 EI VOLTA-DESCHUTES 1/26 REFRAME | 93E
LC | 123249205 | 002/059 | T3 EI DRM-GRS VLEY-WMAR 2/59 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2022-04-05 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123250194 | 002/061 | T3 EI DRM-GRSS VLLY-WMR 2/61 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-05 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605825 | T3 DI DRM GRS VLY WMR 0/14 RPL STRW | 70Y
LC | 123250384 | 000/012 | T3 EI ORO FINO TAP 0/12 RPL POLE | TABLEMTN | ETL.6721.POLE.WOOD | 2022-04-05 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | Rotten | Structure-Wood | Replace | 31606412 | T3 EI ORO FINO TAP 0/12 RPL POLE | 70Y
LC | 123251158 | 000/004 | T3NT EI WOODLEAF-PALERMO 0/4 RPR GYWW | TABLEMTN | ETL.4220.POLE.STPS | 2022-04-05 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123251816 | 000/001 | T3 DI KESWICK-TRINITY 0/1 SPLIT BOLT | TABLEMTN | ETL.7270.POLE.WOOD | 2022-04-05 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Missing | Hardware-Wood | Install
LC | 123251966 | 009/049 | T3 DI RND MTN-TBL MTN #2 09/49 RPR SHLD | TABLEMTN | ETL.6070.TOWR | 2022-04-05 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45456858 | T3 DI RND MTN-TBL MTN #2 09/49 RPR SHLD | ICS
LC | 123252284 | 007/041 | T3 DI RND MTN-TBLE MTN #1 7/41 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2022-04-05 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45458650 | T3 DI RND MTN-TBLE MTN #1 7/41 RPR GYWS | ICS
LC | 123254120 | 008/210 | T3 EI DRM-GRSS VLLY-WMR 8/210 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2022-04-06 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31631448 | T3 EI DRM-GRS VLY-WMR 006/162 RPL STRW | 70Y
LC | 123255193 | 001/012 | T3 EI WOODLEAF-PALERMO 001/012 RPR INSW | TABLEMTN | ETL.4220.INSL.CERA | 2022-04-06 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123255194 | 001/013 | T3 EI WOODLEAF-PALERMO 001/013L RPL POLE | TABLEMTN | ETL.4220.POLE.WDPS | 2022-04-06 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31626016 | T3 EI WOODLEAF-PALERMO 001/013R RPL POLE | 70Y
LC | 123257138 | 084/596 | T3 BRIDGEVL-COTTONWD 84/596 RPR CONDW | EUREKA | ETL.1110.INSL.NCER | 2022-04-06 | 2022-01-14 |  | 2022-07-13 | 2022-07-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair | 45451870 | T3 BRDGVLLE-CTTNWD 84/596 RPR CONDW | ICW
LC | 123257281 | 003/077 | T3 EI VOLTA-DESCHUTES 3/077 RPR STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-06 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45458396 | T3 EI VOLTA-DESCHUTES 3/077 RPR STRW | ICW
LC | 123257900 | 011/269 | T3 EI DRM-GRS VLLY-WMAR 11/269 RPR ANCW | SACTO | ETL.6760.POLE.NWOD | 2022-04-06 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123258123 | 004/045C | T3 EI DRUM-HIGGINS 004/045C RPL HRDW | SACTO | ETL.4393.POLE.NWOD | 2022-04-06 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123259417 | 023/650 | T3 EI COLGATE-ALLEGHANY 23/650 RPR POLE | SACTO | ETL.6470.POLE.WOOD | 2022-04-06 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123259419 | 024/654 | T3 EI COLGATE-ALLEGHANY 24/654 RPR POLE | SACTO | ETL.6470.POLE.WOOD | 2022-04-06 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123259479 | 023/649 | T3 EI CLGATE-ALLEGHANY 023/649 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-04-06 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31633603 | T3 DI COLGATE-ALLEGHANY 18/488 RPL POLE | 70Y
LC | 123259949 | 005/000 | T3 DI KNCTI-EGLE RCK 5/0 RPL STRW | WILLITS | ETL.6861.POLE.WOOD | 2022-04-06 | 2022-03-24 |  | 2022-09-20 | 2022-09-24 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606237 | T3 DI KNCTI-EGLE RCK 1/5 RPL STRW | 70Y
LC | 123260064 | 008/048 | T3 DI RND MTN TBL MTN 1 8/48 RPR SHLDWS | TABLEMTN | ETL.6060.TOWR | 2022-04-06 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45458654 | T3 DI RND MTN TBL MTN 1 8/48 RPR SHLDWS | ICS
LC | 123260139 | 002/039 | T3 DI KESWICK-TRINITY 2/039 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2022-04-06 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123260261 | 003/036 | T3 DI SBNT-GRZZ-CLMNT #1 3/36 RPL INSS | CONCORD | ETL.3740.INSL.NCER | 2022-04-06 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31606159 | T2 EI SBTE-GRZLY-CLRMT #1 RPL INSS 3TWR | 93K
LC | 123261537 | 011/264 | T3 DI DRM-GRS VLY-WMR 11/264 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2022-04-07 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123261539 | 011/264 | T3 DI DRM-GRS VLY-WMR 11/264 RPR JUMW | SACTO | ETL.6760.INSL.CERA | 2022-04-07 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Jumper-Wood | Repair
LC | 123261617 | 009/088 | T3 DI DRUM-HIGGINS 009/088R RPL POLE | SACTO | ETL.4393.POLE.WDPS | 2022-04-07 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31617831 | T3 DI DRUM-HIGGINS 009/088L RPL POLE | 70Y
LC | 123263710 | 012/000 | T3 DI UKIAH-HOPLAND-CLOVRDL 12/0 REGRADE | WILLITS | ETL.4050.POLE.NWOD | 2022-04-07 | 2022-03-25 |  | 2022-09-21 | 2022-09-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45593160 | T3 DI UKIAH-HOPLAND-CLOVRDL 12/0 REGRADE | ICW
LC | 123264399 | 002/025A | T3 EI WOODLEAF-PALERMO 002/025A REGRADE | TABLEMTN | ETL.4220.POLE.NWOD | 2022-04-07 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123264450 | 002/025C | T3 EI WOODLEAF-PALERMO 002/025C REGRADE | TABLEMTN | ETL.4220.POLE.NWOD | 2022-04-07 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123264862 | 006/055 | T3 DI CRG VW-CSCD 6/55L RPL ANCW | TABLEMTN | ETL.1350.POLE.WDPS | 2022-04-07 | 2022-03-31 |  | 2022-09-27 | 2022-10-01 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Anchor-Wood | Replace | 31618172 | T3 DI CRG VW-CSCD 6/55L RPL ANCW | 93E
LC | 123264866 | 006/055 | T3 DI CRG VW CSCD 6/55R RPL ANCW | TABLEMTN | ETL.1350.POLE.WDPS | 2022-04-07 | 2022-03-31 |  | 2022-09-27 | 2022-10-01 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Anchor-Wood | Replace | 31618172 | T3 DI CRG VW-CSCD 6/55L RPL ANCW | 93E
LC | 123265308 | 003/083 | T3 EI DRM-GRSS VLLY-WMR 3/83 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2022-04-07 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31605825 | T3 DI DRM GRS VLY WMR 0/14 RPL STRW | 70Y
LC | 123266503 | 004/095 | T3 EI VOLTA-DESCHUTES 4/95 RMV BUTT | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-07 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45458440 | T3 EI VOLTA-DESCHUTES 4/95 RMV BUTT | ICW
LC | 123267628 | 003/090 | T3 EI DRM-GRSS VLLY-WMR 3/90 RPR GYWW | SACTO | ETL.6760.POLE.NWOD | 2022-04-07 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123268572 | 003/031 | T3 EI WOODLEAF-PALERMO 003/031L RPL HRDW | TABLEMTN | ETL.4220.POLE.STPS | 2022-04-07 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123268642 | 003/031 | T3 EI WOODLEAF-PALERMO 003/031C RPL HRDW | TABLEMTN | ETL.4220.POLE.STPS | 2022-04-07 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123268643 | 003/031 | T3 EI WOODLEAF-PALERMO 003/031L RPR GYWW | TABLEMTN | ETL.4220.POLE.STPS | 2022-04-07 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123268855 | 001/009 | T3 EI DIABLO-GATES #1 001/009 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2022-04-07 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45639052 | T3 EI DIABLO-GATES #1 001/009 RPR GYWS | ICS
LC | 123269054 | 007/042 | T3 DI RND MTN-TBL MTN #1 7/42 INS DAMS | TABLEMTN | ETL.6060.INSL | 2022-04-07 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR NTDE | Missing | Damper-Steel | Install | 45458659 | T3 DI RND MTN-TBL MTN #1 7/42 INS DAMS | ICS
LC | 123269056 | 007/042 | T3 DI RND MTN-TBL MTN #1 7/42 RPL INSS | TABLEMTN | ETL.6060.INSL | 2022-04-07 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617248 | T3 DI RND MTN-TBL MTN #1 2/17 RPL INSS | 93K
LC | 123269084 | 004/090 | T3 DI VOLTA-DESCHUTES 4/90 REFRAME | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-07 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31617272 | T3 EI VOLTA-DESCHUTES 1/26 REFRAME | 93E
LC | 123269627 | 003/074 | T3 DI VOLTA-DESCHUTES 3/074 RPL INSW | TABLEMTN | ETL.8290.INSL | 2022-04-07 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617271 | T3 DI VLT DSCHTS 3/69 RPL INSW | 93I
LC | 123269870 | 019/101 | T3 DI RND MTN-TBL MTN #2 19/101 GY COTR | TABLEMTN | ETL.6070.TOWR | 2022-04-07 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45457126 | T3 DI RND MTN-TBL MTN #2 19/101 GY COTR | ICS
LC | 123271279 | 004/088 | T3 EI VOLTA-DESCHUTES 04/88 RPL STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-08 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606238 | T3 DI VOLTA-DESCHUTES 002/061 RPL POLE | 70Y
LC | 123272203 | 001/013 | T3 EI WOODLEAF-PALERMO 001/013R RPL POLE | TABLEMTN | ETL.4220.POLE.WDPS | 2022-04-08 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31626016 | T3 EI WOODLEAF-PALERMO 001/013R RPL POLE | 70Y
LC | 123272417 | 004/103 | T3 EI VOLTA-DESCHUTES 004/103 REFRAME | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-08 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31617272 | T3 EI VOLTA-DESCHUTES 1/26 REFRAME | 93E
LC | 123273090 | 004/105 | T3 EI VOLTA-DESCHUTES 004/105 RPL STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-08 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606238 | T3 DI VOLTA-DESCHUTES 002/061 RPL POLE | 70Y
LC | 123273286 | 006/065 | T3 EI SNATH LNE-PACIFICA 06/65L RPL ANCW | METCALF | ETL.7575.POLE.WDPS | 2022-04-08 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31612564 | T3 EI SNATH LNE-PACIFICA 06/65R RPL ANCW | 93E
LC | 123273299 | 004/106 | T3 EI VOLTA-DESCHUTES 004/106 REFRAME | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-08 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31617272 | T3 EI VOLTA-DESCHUTES 1/26 REFRAME | 93E
LC | 123273387 | 006/065 | T3 EI SNATH LNE-PACIFICA 06/65C RPL ANCW | METCALF | ETL.7575.POLE.WDPS | 2022-04-08 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31612564 | T3 EI SNATH LNE-PACIFICA 06/65R RPL ANCW | 93E
LC | 123273436 | 006/065 | T3 EI SNATH LNE-PACIFICA 06/65R RPL ANCW | METCALF | ETL.7575.POLE.WDPS | 2022-04-08 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31612564 | T3 EI SNATH LNE-PACIFICA 06/65R RPL ANCW | 93E
LC | 123273454 | 005/110 | T3 DI VOLTA-DESCHUTES 5/110 RPL INSW | TABLEMTN | ETL.8290.INSL | 2022-04-08 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617271 | T3 DI VLT DSCHTS 3/69 RPL INSW | 93I
LC | 123273771 | 000/005 | T3 EI DRUM-GRASS VALLEY 0/5 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2022-04-08 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123273969 | 004/106 | T3 EI DRM-GRS VLY-WMR 4/106 RPR HRDW | SACTO | ETL.6760.INSL.NCER | 2022-04-08 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123274004 | 006/064 | T3 EI SNATH LANE-PACIFICA 06/64 RPR GYWW | METCALF | ETL.7575.POLE.NWOD | 2022-04-08 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45600655 | T3 EI SNATH LANE-PACIFICA 06/64 RPR GYWW | ICW
LC | 123274218 | 000/003 | T3 EI DIABLO-MIDWAY #2 0/3 RPR INSS | PISMOBCH | ETL.5970.INSL.CERA | 2022-04-08 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123274540 | 000/002 | T3 EI DIABLO-MIDWAY #2 0/2 RPL INSS | PISMOBCH | ETL.5970.INSL.NCER | 2022-04-08 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31628915 | 53 EI DIABLO-MIDWAY #2 0/2 RPL INSS | 93K
LC | 123275266 | 005/042 | T3 DI GREEN VALLEY-LLAGAS 5/42 RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-04-08 | 2022-03-28 |  | 2022-09-24 | 2022-09-28 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31610973 | T3 DI GREEN VALLEY-LLAGAS 5/42R RPL POLE | 70Y
LC | 123275441 | 005/040 | T3 DI GREEN VALLEY-LLAGAS 5/40 RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-04-08 | 2022-03-28 |  | 2022-09-24 | 2022-09-28 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31610972 | T3 EI GREEN VALLEY-LLAGAS 5/37R RPL POLE | 70Y
LC | 123275445 | 005/040 | T3 DI GREEN VALLEY-LLAGAS 5/40 RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-04-08 | 2022-03-28 |  | 2022-09-24 | 2022-09-28 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31610972 | T3 EI GREEN VALLEY-LLAGAS 5/37R RPL POLE | 70Y
LC | 123275446 | 005/040 | T3 DI GREEN VALLEY-LLAGAS 5/40 RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-04-08 | 2022-03-28 |  | 2022-09-24 | 2022-09-28 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31610972 | T3 EI GREEN VALLEY-LLAGAS 5/37R RPL POLE | 70Y
LC | 123276899 | 009/088 | T3 DI DRUM-HIGGINS 009/088L RPL POLE | SACTO | ETL.4393.POLE.WDPS | 2022-04-08 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31617831 | T3 DI DRUM-HIGGINS 009/088L RPL POLE | 70Y
LC | 123277709 | 000/007 | T3 EI FORKS OF THE BUTTE 0/7 RPR ANCW | TABLEMTN | ETL.6722.POLE.NWOD | 2022-04-08 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123277743 | 000/006 | T3 EI FORKS OF THE BUTTE 0/6 RPR ANCW | TABLEMTN | ETL.6722.POLE.NWOD | 2022-04-08 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123277744 | 000/001 | T3 EI FORKS OF THE BUTTE 0/1 RPL POLE | TABLEMTN | ETL.6722.POLE.WOOD | 2022-04-08 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31613972 | T3 EI FORKS OF THE BUTTE 0/1 RPL POLE | 70Y
LC | 123279092 | 015/064 | T3 DI MNT VST JFRSN #2 15/64 RPL INSS | METCALF | ETL.5230.INSL | 2022-04-09 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31602541 | T2 DI MNT VST-JFRSN #2 RPL INSS 5 TWRS. | 93K
LC | 123279124 | 005/042 | T3 DI GREEN VALLEY-LLAGAS 5/42R RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-04-09 | 2022-03-28 |  | 2022-09-24 | 2022-09-28 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31610973 | T3 DI GREEN VALLEY-LLAGAS 5/42R RPL POLE | 70Y
LC | 123279187 | 004/115 | T3 EI DRM-GRS VLY-WMR 4/115 RMV BUTT | SACTO | ETL.6760.POLE.NWOD | 2022-04-09 | 2022-04-09 |  | 2022-10-06 | 2022-10-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123279366 | 004/114 | T3 EI DRUM-GRAS VLLY-WMR 4/114 RPR INSW | SACTO | ETL.6760.INSL.NCER | 2022-04-09 | 2022-04-09 |  | 2022-10-06 | 2022-10-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123279703 | 004/072 | T3 EI SISQUOC-GAREY 4/072 RPL ANCW | PISMOBCH | ETL.3690.POLE.WOOD | 2022-04-09 | 2022-04-09 |  | 2022-10-06 | 2022-10-09 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31605589 | T3 EI SISQUOC-GAREY 4/072 RPL ANCW | 93E
LC | 123279858 | 003/059 | T3 DI CNTRVL TBL MTN ORVL 3/59 RPR INSW | TABLEMTN | ETL.6330.INSL.NCER | 2022-04-09 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123280226 | 014/068 | T3 DI CRTN MNDCN #1 14/68 RPR FOND | WILLITS | ETL.1330.TOWR | 2022-04-09 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45644569 | T3 DI CRTN MNDCN #1 14/68 RPR FOND | ICQ
LC | 123280278 | 006/132 | T3 EI VOLTA-DESCHUTES 006/132 RPR STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-09 | 2022-04-09 |  | 2022-10-06 | 2022-10-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45458441 | T3 EI VOLTA-DESCHUTES 006/132 RPR STRW | ICW
LC | 123280879 | 006/063 | T3 EI DRUM-HIGGINS 6/63 INS DAMS | SACTO | ETL.4393.INSL.CERA | 2022-04-09 | 2022-04-09 |  | 2022-10-06 | 2022-10-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | Missing | Damper-Steel | Install | 45644100 | T3 EI DRUM-HIGGINS 6/63 INS DAMS | ICS
LC | 123280914 | 005/061 | T3 EI DRUM-HIGGINS 5/61 RPL INSS | SACTO | ETL.4393.INSL.CERA | 2022-04-09 | 2022-04-09 |  | 2022-10-06 | 2022-10-09 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31618894 | T3 EI DRUM-HIGGINS RPL INSS 6 TWRS | 93K
LC | 123281475 | 005/138 | T3 EI DRUM-GRASS VALLEY 005/138 RPL HRDW | SACTO | ETL.6760.INSL.NCER | 2022-04-09 | 2022-04-09 |  | 2022-10-06 | 2022-10-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123281802 | 008/007 | T3 DI MENDOCINO-WILLITS 008/007 RPL HRDW | WILLITS | ETL.7540.POLE.WOOD | 2022-04-09 | 2022-03-28 |  | 2022-09-24 | 2022-09-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123294512 | 007/014 | T3 DI MENDOCINO-WILLITS 007/014 RPR STRW | WILLITS | ETL.7540.POLE.WOOD | 2022-04-11 | 2022-03-28 |  | 2022-09-24 | 2022-09-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123294663 | 003/069 | T3 DI VLT DSCHTS 3/69 RPL INSW | TABLEMTN | ETL.8290.INSL | 2022-04-11 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617271 | T3 DI VLT DSCHTS 3/69 RPL INSW | 93I
LC | 123295798 | T083 | T3 DI MIDWAY-SANTA MARIA T083 UNBURY | PISMOBCH | ETL.9240.TOWR | 2022-04-11 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45639148 | T3 DI MIDWAY-SANTA MARIA T083 UNBURY | ICQ
LC | 123295966 | 019/184 | T3 DI RND MTN CTNWD #2 19/184 RPL INSS | TABLEMTN | ETL.5640.INSL | 2022-04-11 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31625580 | T3 DI RND MTN CTNWD #2 RPL INSS 6 TWRS | 93K
LC | 123296003 | 020/102 | T3 EI RND MTN-TBL MTN #2 20/102 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2022-04-11 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123296371 | 006/144 | T3 EI VOLTA-DESCHUTES 006/144 RPL STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-11 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Rotten | Structure-Wood | Replace | 31606239 | T3 VOLTA-DESCHUTES 006/137 RPL POLE | 70Y
LC | 123296702 | 002/045 | T3 DI VLTA-DSCHTS 2/045 RPR HWRW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-11 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45458449 | T3 DI VLTA-DSCHTS 2/045 RPR HWRW | ICW
LC | 123297441 | 019/101 | T3 EI RND MTN-TBL MTN #1 19/101 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2022-04-11 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45644441 | T3 EI RND MTN-TBL MTN #1 19/101 RPR STRT | ICQ
LC | 123297761 | 029/001 | T3 DI FULT0N-HOPLAND 29/1 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2022-04-11 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45575477 | T3 DI FULT0N-HOPLAND 29/1 RPR STRW | ICW
LC | 123297798 | 006/029 | T3 EI MORRO BAY-TEMPLETON 6/29 RPR FOND | PISMOBCH | ETL.5933.TOWR | 2022-04-11 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45639149 | T3 EI MORRO BAY-TEMPLETON 6/29 RPR FOND | ICQ
LC | 123298784 | 007/153 | T3 EI VOLTA-DESCHUTES 007/153 RPL STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-11 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Rotten | Structure-Wood | Replace | 31606239 | T3 VOLTA-DESCHUTES 006/137 RPL POLE | 70Y
LC | 123299449 | 024/099 | T3 DI EXCHQER-INDAN FLT 24/099 RPR INSS | FRESNO | ETL.8650.INSL.CERA | 2022-04-11 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair | 45489051 | T3 DI EXCHQER-INDAN FLT 24/099 RPR INSS | ICS
LC | 123299617 | 015/132 | T3 DI DRM RIO OSO#1 15/132 RPR SWTCH 319 | SACTO | ETL.1420.SWIT | 2022-04-11 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 623 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | Out of Adjustment | Switch | Repair | 45526722 | T3 DI DRM RIO OSO#1 15/132 RPR SWTCH 319 | ICE
LC | 123299660 | 015/132 | T3 DI DRM RIO OSO#2 15/132 RPR SWTCH 327 | SACTO | ETL.1430.SWIT | 2022-04-11 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 623 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | Out of Adjustment | Switch | Repair | 45526723 | T3 DI DRM RIO OSO#2 15/132 RPR SWTCH 327 | ICE
LC | 123300323 | 006/145 | T3 DI KILARC-CEDAR CREEK 6/145 INS HRDW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-04-11 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45459232 | T3 DI KILARC-CEDAR CREEK 6/145 INS HRDW | ICW
LC | 123300326 | 001/027 | T3 DI MIDDLE FORK #1+ 001/027 RPR INSW | SACTO | ETL.8405.INSL.NCER | 2022-04-11 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123300424 | T-112 | T3 DI MIDWAY-SANTA MARIA T-112 RPR STRT | PISMOBCH | ETL.9240.TOWR | 2022-04-11 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45639159 | T3 DI MIDWAY-SANTA MARIA T-112 RPR STRT | ICQ
LC | 123300426 | T-112 | T3 DI MIDWAY-SANTA MARIA T-112 UNBURY | PISMOBCH | ETL.9240.TOWR | 2022-04-11 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45639180 | T3 DI MIDWAY-SANTA MARIA T-112 UNBURY | ICQ
LC | 123300638 | 005/002 | T3 DI BRIDGEVILL-GARBERVL 05/02 RPL INSW | EUREKA | ETL.6220.INSL.CERA | 2022-04-11 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617171 | T3 EI BRIDGEVILLE-GRBRVLL 3/0 RPL INSW | 93I
LC | 123300725 | 009/231 | T3 DI DRM-GRS VLY WMR 9/231 RPR CRSW | SACTO | ETL.6760.POLE.WOOD | 2022-04-11 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Crossarm-Wood | Repair
LC | 123300783 | 005/013 | T3 DI BRIDGEVL-GARBERVLE 5/13 RPL STRW | EUREKA | ETL.6220.POLE.WOOD | 2022-04-11 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31604325 | T2 EI BRIDGEVILLE-GARBERVILLE 0/4 RPL PL | 70Y
LC | 123300820 | 012/262 | T3 DI KILARC-CEDAR CREEK 12/262 INS HRDW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-04-11 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45459231 | T3 DI KILARC-CEDAR CREEK 12/262 INS HRDW | ICW
LC | 123300932 | 003/035 | T3 DI SBRNT-GRZLY-CLRMNT#1 3/35 RPR FOND | CONCORD | ETL.3740.TOWR | 2022-04-11 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123301284 | 001/011 | T3 EI GEYSERS#7-EAGLE ROCK 1/11 INS DAMS | LAKEVLLE | ETL.1680.INSL.CERA | 2022-04-12 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | Missing | Damper-Steel | Install
LC | 123301285 | 001/012 | T3 EI GEYSERS#7-EAGLE ROCK 1/12 RPR FOND | LAKEVLLE | ETL.1680.POLE.NWOD | 2022-04-12 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123301286 | 001/011 | T3 EI GEYSERS#3-EAGLE ROCK 1/11 INS DAMS | LAKEVLLE | ETL.1660.INSL.CERA | 2022-04-12 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | Missing | Damper-Steel | Install | 45576006 | T3 EI GEYSERS#3-EAGLE ROCK 1/11 INS DAMS | ICS
LC | 123302256 | 007/158 | T3 EI VOLTA-DESCHUTES 007/158 RPL STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Rotten | Structure-Wood | Replace | 31606239 | T3 VOLTA-DESCHUTES 006/137 RPL POLE | 70Y
LC | 123302461 | 006/156 | T3 EI DRM-GRS VLLY-WMR 6/156 RPR SPLW | SACTO | ETL.6760.INSL.NCER | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 123302530 | 006/150 | T3 EI DRM-GRS VLLY-WMR 6/150 RPLM INSW | SACTO | ETL.6760.INSL.NCER | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123302645 | X000/002 | T3 EI DIABLO-MESA X0/2 UNBURY | PISMOBCH | ETL.4620.TOWR | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45639186 | T3 EI DIABLO-MESA X0/2 UNBURY | ICQ
LC | 123302942 | 006/157 | T3 EI DRM-GRSS VLLY -WEIMR 6/157 BACKFIL | SACTO | ETL.6760.POLE.WOOD | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Structure-Wood | Repair | 45349033 | T3 EI DRM-GRSS VLLY -WEIMR 6/157 BACKFIL | ICW
LC | 123303046 | 011/112 | T3 EI DRUM-RIO OSO #2 11/112 RMV NEST | SACTO | ETL.1430.TOWR | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove
LC | 123303258 | T080 | T3 DI MIDWAY-SANTA MARIA T080 UNBURY | PISMOBCH | ETL.9240.TOWR | 2022-04-12 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45639187 | T3 DI MIDWAY-SANTA MARIA T080 UNBURY | ICQ
LC | 123303369 | 006/158 | T3 EI DRM-GRS VLLY -WMRT 006/158 REFRAME | SACTO | ETL.6760.INSL.NCER | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 627 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Crossarm-Wood | Replace
LC | 123303721 | 021/107 | T3 EI RND MTN-TBL MTN #2 21/107 BNT STEL | TABLEMTN | ETL.6070.TOWR | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123304458 | 017/138 | T3 EI PARADISE-TABLE MTN 17/138 RMV BUTT | TABLEMTN | ETL.4316.POLE.STPS | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123304691 | 023/115 | T3 DI RND MTN-TBL MTN#2 23/115 RPR SHLWS | TABLEMTN | ETL.6070.TOWR | 2022-04-12 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45644275 | T3 DI RND MTN-TBL MTN#2 23/115 RPR SHLWS | ICS
LC | 123304735 | 018/085 | T3 DI CORTINA-MNDCNO #1 18/85 RPR FOND | WILLITS | ETL.1330.TOWR | 2022-04-12 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45644573 | T3 DI CORTINA-MNDCNO #1 18/85 RPR FOND | ICQ
LC | 123304796 | 006/153 | T3 EI DRM -GRS VLLY-WMR 6/153 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123306187 | 021/109 | T3 EI RND MTN-TBL MTN #1 21/109 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45458666 | T3 EI RND MTN-TBL MTN #1 21/109 RPR GYWS | ICS
LC | 123306531 | 021/109 | T3 EI RND MTN-TBL MTN #1 21/109 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3N PRTO CLMB FRAB | Anti-Climbing Guard | Structure-Tower | Repair | 45314415 | T3 EI RND MTN-TBL MTN #1 21/109 RPR STRT | ICQ
LC | 123307529 | 000/006 | T3 DI SOBRANTE-G #1 0/6 RPL INSS | CONCORD | ETL.3720.INSL.CERA | 2022-04-12 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31627444 | T2 DI SOBRANTE-G #1 RPL INSS IN 2 TWRS. | 93K
LC | 123307641 | 005/140 | T3 EI DRM -GRSS-VLY-WMR 5/140 RPLM INSW | SACTO | ETL.6760.INSL.NCER | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123307703 | 000/006 | T3 DI SOBRANTE-G #1 0/6 BNT STEEL | CONCORD | ETL.3720.TOWR | 2022-04-12 | 2022-03-29 |  | 2022-09-25 | 2022-09-29 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45513118 | T3 DI SOBRANTE-G #1 0/6 BNT STEEL | ICS
LC | 123308889 | 016/136 | T3 EI CARIBOU-SYCMRE CRK 16/136 RMV BUTT | TABLEMTN | ETL.4316.POLE.STPS | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123309091 | 006/155 | T3 EI DRM-GRS VLLY-WMR 6/155 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31616445 | T3 EI DRM-GRS VLLY-WMR 6/155 RPL STRW | 70Y
LC | 123309117 | 021/110 | T3 EI RND MTN-TBL MTN #1 21/110 BNT STEL | TABLEMTN | ETL.6060.TOWR | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45644444 | T3 EI RND MTN-TBL MTN #1 21/110 BNT STEL | ICQ
LC | 123309601 | 021/110 | T3 EI RND MTN-TBL MTN #2 21/110 RPR GYWS | TABLEMTN | ETL.6070.TOWR | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45457131 | T3 EI RND MTN-TBL MTN #2 21/110 RPR GYWS | ICS
LC | 123309691 | 004/013 | T3 BRIDGEVLLE-GARBERVLLE 4/13 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31604325 | T2 EI BRIDGEVILLE-GARBERVILLE 0/4 RPL PL | 70Y
LC | 123310996 | X001/007 | T3 EI DIABLO-MESA X0/7 RPR STRT | PISMOBCH | ETL.4620.TOWR | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45639189 | T3 EI DIABLO-MESA X0/7 RPR STRT | ICQ
LC | 123311128 | 007/171 | T3 EI DRM-GRSS VLLY-WMR 007/171 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605825 | T3 DI DRM GRS VLY WMR 0/14 RPL STRW | 70Y
LC | 123311541 | 022/112 | T3 EI RND MTN-TBL MTN #2 22/112 RPR GYWS | TABLEMTN | ETL.6070.TOWR | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45457132 | T3 EI RND MTN-TBL MTN #2 22/112 RPR GYWS | ICS
LC | 123311569 | 009/049 | T3 DI RND MTN-TBL MTN#1 9/049 RPL INSS | TABLEMTN | ETL.6060.INSL | 2022-04-12 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617248 | T3 DI RND MTN-TBL MTN #1 2/17 RPL INSS | 93K
LC | 123311607 | 011/166 | T3 EI GOLD HILL #1 011/166 RPL HRDW | SACTO | ETL.6950.POLE.WOOD | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123311915 | 011/057 | T3 DI MNTA VSTA-CYTE 11/57 RPR SHLS | MOSSLNDG | ETL.5090.TOWR | 2022-04-12 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45581098 | T3 DI MNTA VSTA-CYTE 11/57 RPR SHLS | ICS
LC | 123312142 | 007/183 | T3 DI DRM-GRS VLY-WMR 7/183 RPL INSW | SACTO | ETL.6760.INSL.NCER | 2022-04-12 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617792 | T3 EI DRM-GRSS VLEY-WEIMAR 0/17 RPL INSW | 93I
LC | 123312877 | 022/113 | T3 EI RND MTN-TBL MTN #2 22/113 RPR GYWS | TABLEMTN | ETL.6070.TOWR | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45457133 | T3 EI RND MTN-TBL MTN #2 22/113 RPR GYWS | ICS
LC | 123313146 | 022/114 | T3 EI RND MTN-TBL MT #1 22/114 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2022-04-12 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45458668 | T3 EI RND MTN-TBL MT #1 22/114 RPR GYWS | ICS
LC | 123313380 | 020/102 | T3 DI RND MTN-TBL MTN#1 20/102 COTER KEY | TABLEMTN | ETL.6060.INSL | 2022-04-12 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair | 45458669 | T3 DI RND MTN-TBL MTN#1 20/102 COTER KEY | ICS
LC | 123313404 | 019/101 | T3 DI RND MTN TBL MTN #1 19/101 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2022-04-12 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45458670 | T3 DI RND MTN TBL MTN #1 19/101 RPR GYWS | ICS
LC | 123313407 | 010/120 | T3 DI GYSR#3-CLVRDLE 10/120 RPR SWTC | LAKEVLLE | ETL.1650.SWIT | 2022-04-12 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 623 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR NTDE | Out of Adjustment | Switch | Repair | 45575588 | T3 DI GYSR#3-CLVRDLE 10/120 RPR SWTC | ICE
LC | 123313488 | 010/124 | T3 DI GYSRS #3-CLVRDAL 10/124 RPL HRDD | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-04-12 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW ACCM OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45575592 | T3 DI GYSRS #3-CLVRDAL 10/124 RPL HRDD | ICW
LC | 123313532 | 001/010 | T3 DI FULTON-IGNACIO #1 1/10 RPL INSS | LAKEVLLE | ETL.4680.INSL | 2022-04-12 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31634587 | T3 DI FULTON-IGNACIO #1 1/10 RPL INSS | 93K
LC | 123313581 | 019/001 | T3 DI MONTE RIO-FORT ROS 19/01R RPR HRDW | LAKEVLLE | ETL.6979.POLE.WDPS | 2022-04-12 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45575642 | T3 DI MONTE RIO-FORT ROS 19/01R RPR HRDW | ICW
LC | 123313633 | 019/001 | T3 DI MONTE RIO-FORT ROSS 19/1R RPL INSW | LAKEVLLE | ETL.6979.INSL.NCER | 2022-04-12 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31619384 | T3 DI MONTE RIO-FORT ROSS 19/1R RPL INSW | 93I
LC | 123313637 | 018/004 | T3 DI MONTE-RIO-FORT ROSS 18/04 REFRAME | LAKEVLLE | ETL.6979.POLE.WOOD | 2022-04-12 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31619385 | T3 DI MONTE-RIO-FORT ROSS 18/04 REFRAME | 93E
LC | 123313800 | 017/082 | T3 DI EAGLE ROCK-CORTINA 17/82 RPR INSS | WILLITS | ETL.1470.INSL.NCER | 2022-04-12 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45593176 | T3 DI EAGLE ROCK-CORTINA 17/82 RPR INSS | ICS
LC | 123314019 | 020/098 | T3 DI MNT VST-CYTE SW ST 20/98 RPL DMPS | MOSSLNDG | ETL.5090.INSL | 2022-04-12 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 45605934 | T3 DI MNT VST-CYTE SW ST 20/98 RPL DMPS | ICS
LC | 123315481 | 006/137 | T3 VOLTA-DESCHUTES 006/137 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-13 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606239 | T3 VOLTA-DESCHUTES 006/137 RPL POLE | 70Y
LC | 123315628 | 006/060 | T3 DI CRAG VIEW-CASCADE 6/60R RPR POLE | TABLEMTN | ETL.1350.POLE.WDPS | 2022-04-13 | 2022-03-31 |  | 2022-09-27 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45461075 | T3 DI CRAG VIEW-CASCADE 6/60R RPR POLE | ICW
LC | 123316180 | 013/067 | T3 DI MNT VST CYT SS 13/67 RPR SHLS | MOSSLNDG | ETL.5090.TOWR | 2022-04-13 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45581099 | T3 DI MNT VST CYT SS 13/67 RPR SHLS | ICS
LC | 123316843 | 007/169 | T3 EI DRM GRSS VLL -WMR 7/169 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-13 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123318652 | 013/068 | T3 DI METCALF-MONTA VT #3 13/68 RPL INSS | MOSSLNDG | ETL.5091.INSL | 2022-04-13 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617199 | DI METCALF-MONTA VISTA #3 RPL INSS 3 TWR | 93K
LC | 123319541 | 018/087 | T3 DI CRTN MNDCN #1 18/87 RPR FOND | WILLITS | ETL.1330.TOWR | 2022-04-13 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123320248 | 014/073 | T3 DI MTCLF-MNT VST#3 14/73 COTR KEY | MOSSLNDG | ETL.5091.INSL | 2022-04-13 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45605940 | T3 DI MTCLF-MNT VST#3 14/73 COTR KEY | ICS
LC | 123320480 | 005/046 | T3 DI CRAG VIEW-CASCADE 5/46L RPL POLE | TABLEMTN | ETL.1350.POLE.WDPS | 2022-04-13 | 2022-03-31 |  | 2022-09-27 | 2022-09-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31618170 | T3 DI CRAG VIEW-CASCADE 5/46L RPL POLE | 70Y
LC | 123320482 | 005/046 | T3 DI CRAG VIEW-CASCADE 5/46R RPL POLE | TABLEMTN | ETL.1350.POLE.WDPS | 2022-04-13 | 2022-03-31 |  | 2022-09-27 | 2022-09-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31618170 | T3 DI CRAG VIEW-CASCADE 5/46L RPL POLE | 70Y
LC | 123320651 | 010/040 | T3 EI PITTSBURG-SAN RAMON 10/40 RPR JMPS | CONCORD | ETL.5490.INSL.NCER | 2022-04-13 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Jumper-Steel | Repair | 45513119 | T3 EI PITTSBURG-SAN RAMON 10/40 RPR JMPS | ICS
LC | 123322362 | 009/216 | T3 DI DRM-GRS VLLY-WMAR 9/216 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2022-04-13 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123323774 | 011/244 | T3 DI KILARC-CEDAR CREEK 11/244 RPR GRWW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-04-13 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 45459230 | T3 DI KILARC-CEDAR CREEK 11/244 RPR GRWW | ICW
LC | 123324157 | 001/034 | T3 DI VOLTA-DESCHUTES 001/034 RPR GRWW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-13 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 45458605 | T3 DI VOLTA-DESCHUTES 001/034 RPR GRWW | ICW
LC | 123324264 | 001/035 | T3 DI KILARC-CEDAR CREEK 01/35 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-04-13 | 2022-03-31 |  | 2022-09-27 | 2022-09-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31631564 | T3 EI KILARC-CEDAR CREEK 0/002 RPL STRW | 70Y
LC | 123324340 | 021/102 | T3 DI MNT VST-CYTE SS 21/102 COTER KEY | MOSSLNDG | ETL.5090.INSL | 2022-04-13 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45605941 | T3 DI MNT VST-CYTE SS 21/102 COTER KEY | ICS
LC | 123324888 | 009/004 | T3 DI BRIDGEVILLE-GARBERVIL 9/4 INS HRDW | EUREKA | ETL.6220.POLE.WOOD | 2022-04-13 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45416593 | T3 DI BRIDGEVILLE-GARBERVIL 9/4 INS HRDW | ICW
LC | 123325530 | 025/105 | T3 DI EXCHQR INDN FLT 25/105 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2022-04-13 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123325540 | 000/005 | T3 DI KILARC-DESCHUTES 000/005 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2022-04-13 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606220 | T3 DI KILARC-DESCHUTES 000/005 RPL POLE | 70Y
LC | 123325645 | 016/066 | T3 DI MNTA VST-JFFRSN #2 16/66 RPL DAMS | METCALF | ETL.5230.INSL | 2022-04-13 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 45258561 | T3 DI MNTA VST-JFFRSN #2 16/66 RPL DAMS | ICS
LC | 123325649 | 014/071 | T3 DI MNTA VST-CYTE SW ST 14/71 RPR SHLS | MOSSLNDG | ETL.5090.TOWR | 2022-04-13 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45605946 | T3 DI MNTA VST-CYTE SW ST 14/71 RPR SHLS | ICS
LC | 123325662 | 014/069 | T3 DI CRTNA-MNDCNO #1 14/69 RPR FOND | WILLITS | ETL.1330.TOWR | 2022-04-13 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123325729 | 007/039 | T3 DI RND MNTN-TBL MNTN #1 7/39 RPL OPGW | TABLEMTN | ETL.6060.TOWR | 2022-04-13 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 45458672 | T3 DI RND MNTN-TBL MNTN #1 7/39 RPL OPGW | ICS
LC | 123325742 | 014/071 | T3 DI MTCLF-MNT VST#3 14/71 COTR KEY | MOSSLNDG | ETL.5091.INSL | 2022-04-13 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45605947 | T3 DI MTCLF-MNT VST#3 14/71 COTR KEY | ICS
LC | 123325761 | 020/096 | T3 DI METCALF-MNT VISTA#3 20/96 RPR INSS | MOSSLNDG | ETL.5091.INSL | 2022-04-13 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45605949 | T3 DI METCALF-MNT VISTA#3 20/96 RPR INSS | ICS
LC | 123325801 | 011/246 | T3 DI KILARC-CEDAR CREEK 11/246 RPR POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-04-13 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45459228 | T3 DI KILARC-CEDAR CREEK 11/246 RPR POLE | ICW
LC | 123325857 | 007/014 | T3 DI BRIDGEVL-GARBERVL 7/14 RPL INSW | EUREKA | ETL.6220.INSL.CERA | 2022-04-13 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617171 | T3 EI BRIDGEVILLE-GRBRVLL 3/0 RPL INSW | 93I
LC | 123325878 | 008/191 | T3 DI KILARC-CEDAR CREEK 8/191 RPL HRDW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-04-13 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45459227 | T3 DI KILARC-CEDAR CREEK 8/191 RPL HRDW | ICW
LC | 123325886 | 008/049 | T3 DI MTCLF-MNTA VST #3 08/49 COTTER | MOSSLNDG | ETL.5091.INSL | 2022-04-13 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45605952 | T3 DI MTCLF-MNTA VST #3 08/49 COTTER | ICS
LC | 123325945 | 017/085 | T3 DI MNT VST-CYTESS 17/85 RPR COTTER | MOSSLNDG | ETL.5090.INSL | 2022-04-13 | 2022-04-09 |  | 2022-10-06 | 2022-10-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45605953 | T3 DI MNT VST-CYTESS 17/85 RPR COTTER | ICS
LC | 123325957 | 003/039 | T3 DI DRUM-HIGGINS 03/39 RPR INSW | SACTO | ETL.4393.INSL.NCER | 2022-04-13 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123326017 | 018/091 | T3 DI MNT VIT-CYTE SS 18/91 COTTER KEY | MOSSLNDG | ETL.5090.INSL | 2022-04-13 | 2022-04-09 |  | 2022-10-06 | 2022-10-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45605955 | T3 DI MNT VIT-CYTE SS 18/91 COTTER KEY | ICS
LC | 123326084 | 012/278 | T3 DI KILARC-CEDAR CREEK 12/278 RPR INSW | TABLEMTN | ETL.7290.INSL | 2022-04-13 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45459226 | T3 DI KILARC-CEDAR CREEK 12/278 RPR INSW | ICW
LC | 123326387 | 010/006 | T3 DI BRIDGEVL-GARBERVL 10/006 RPR STRW | EUREKA | ETL.6220.POLE.WOOD | 2022-04-14 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45451430 | T3 DI BRDGVLL-GRBRVLLE 10/006 RPR STRW | ICW
LC | 123327459 | 019/093 | T3 DI MNT VST CYT SS 19/93 COTTER | MOSSLNDG | ETL.5091.INSL | 2022-04-14 | 2022-04-09 |  | 2022-10-06 | 2022-10-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45605956 | T3 DI MNT VST CYT SS 19/93 COTTER | ICS
LC | 123328419 | 014/108 | T3 DI TRNTY CTNWD 14/108 INS RPTS | TABLEMTN | ETL.4040.POLE.STPS | 2022-04-14 | 2022-03-15 |  | 2022-09-11 | 2022-09-15 | Late | 530 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Missing | Raptor Guard-Steel | Install
LC | 123330399 | 007/163 | T3 DI KILARC-CEDAR CRK 7/163 INS COTTER | TABLEMTN | ETL.7290.INSL.NCER | 2022-04-14 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45459225 | T3 DI KILARC-CEDAR CRK 7/163 INS COTTER | ICW
LC | 123330783 | 026/103 | T3 DI PTTSBRG-SN MATEO 26/103 RPR SPLS | CONCORD | ETL.5463.INSL | 2022-04-14 | 2022-04-13 |  | 2022-10-10 | 2022-07-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Steel | Replace | 45260143 | T3 DI PTTSBRG-SN MATEO 26/103 RPR SPLS | ICS
LC | 123332497 | 000/012 | T3 DI CNTRVL-TBL MTN ORVLE 0/12 RPL POLE | TABLEMTN | ETL.6330.POLE.WOOD | 2022-04-14 | 2022-03-31 |  | 2022-09-27 | 2022-09-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611490 | T3 EI CNTRVLL-TBL MTN-ORLL 0/2 RPL POLE | 70Y
LC | 123332639 | 006/156 | T3 DI KILARC-CEDAR CRK-WD PL 6/156 HRDD | TABLEMTN | ETL.7290.POLE.WOOD | 2022-04-14 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | Missing | Hardware-Wood | Install | 45459224 | T3 DI KILARC-CEDAR CRK-WD PL 6/156 HRDD | ICW
LC | 123332705 | 003/071 | T3 DI KILARC-CEDAR CREEK 3/71 INS HRDW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-04-14 | 2022-03-31 |  | 2022-09-27 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45459223 | T3 DI KILARC-CEDAR CREEK 3/71 INS HRDW | ICW
LC | 123332707 | 007/062 | T3 DI CRAG VIEW-CASCADE 7/62L RPL HRDW | TABLEMTN | ETL.1350.POLE.WDPS | 2022-04-14 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45461076 | T3 DI CRAG VIEW-CASCADE 7/62L RPL HRDW | ICW
LC | 123332860 | 001/011 | T3 DI SOBRANTE-"G" #1 1/11 RPR INSS | CONCORD | ETL.3720.INSL.NCER | 2022-04-14 | 2022-03-31 |  | 2022-09-27 | 2022-09-30 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45513124 | T3 DI SOBRANTE-"G" #1 1/11 RPR INSS | ICS
LC | 123332897 | 012/276 | T3 DI KILARC-CEDAR CREEK 12/276 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-04-14 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606234 | T3 EI KILARC-CEDAR CREEK 10/229 RPL POLE | 70Y
LC | 123332899 | 008/014 | T3 DI BRIDGEVL-GARBERVL 08/14 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-04-14 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31604325 | T2 EI BRIDGEVILLE-GARBERVILLE 0/4 RPL PL | 70Y
LC | 123332900 | 002/061 | T3 DI VOLTA-DESCHUTES 002/061 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-14 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606238 | T3 DI VOLTA-DESCHUTES 002/061 RPL POLE | 70Y
LC | 123332903 | 000/004 | T3 DI W PNT-VLLY SPRINGS 0/4 RPL SPLW | VICTOR | ETL.8350.INSL.CERA | 2022-04-14 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Replace | 45519457 | T3 DI W PNT-VLLY SPRINGS 0/4 RPL SPLW | ICW
LC | 123332932 | 008/046 | T3 DI FULTON-IGNACIO #1 8/46 RPR INSS | LAKEVLLE | ETL.4680.INSL | 2022-04-14 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571456 | T3 DI FULTON-IGNACIO #1 8/46 RPR INSS | ICS
LC | 123332974 | 010/106 | T3 DI DRM-RIO OSO #2 10/106 WASH INSS | SACTO | ETL.1430.INSL | 2022-04-14 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 622 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | Contaminated | Insulator | Ground Wash
LC | 123332976 | 010/106 | T3 DI DRM-RIO OSO #2 10/106 RPR FOND | SACTO | ETL.1430.TOWR | 2022-04-14 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45582128 | T3 DI DRM-RIO OSO #2 10/106 RPR FOND | ICQ
LC | 123333003 | 004/099 | T3 DI DRM-GRSS VLY-WMAR 4/99 RPL HRDW | SACTO | ETL.6760.POLE.NWOD | 2022-04-14 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123334504 | 009/213 | T3 DI KILARC-CEDAR CRK 9/213 RMV DEBRIS | TABLEMTN | ETL.7290.POLE.WOOD | 2022-04-15 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45459221 | T3 DI KILARC-CEDAR CRK 9/213 RMV DEBRIS | ICW
LC | 123334538 | 000/008 | T3 DI VOLTA-SOUTH 0/8 REFRAME | TABLEMTN | ETL.8300.POLE.WOOD | 2022-04-15 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31616690 | T3 DI VOLTA-SOUTH 0/8 REFRAME | 93E
LC | 123334900 | 003/057 | T3 DI CNTRVIL-TABLE MTN 3/57 RPR GYWW | TABLEMTN | ETL.6320.POLE.NWOD | 2022-04-15 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123334978 | 007/177 | T3 DI KLRC-CDR CRK 7/177 RPL HRDD | TABLEMTN | ETL.7290.POLE.WOOD | 2022-04-15 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45459220 | T3 DI KLRC-CDR CRK 7/177 RPL HRDD | ICW
LC | 123335071 | 007/177 | T3 DI KLRC-CDR CRK 7/177 RPR INSW | TABLEMTN | ETL.7290.INSL.CERA | 2022-04-15 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45459158 | T3 DI KLRC-CDR CRK 7/177 RPR INSW | ICW
LC | 123335132 | 008/187 | T3 DI KILARC-CEDAR CRK 8/187 RPR INSW | TABLEMTN | ETL.7290.INSL | 2022-04-15 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45459157 | T3 DI KILARC-CEDAR CRK 8/187 RPR INSW | ICW
LC | 123335144 | 000/007 | T3 DI CNTRVL-TBL MTN-ORVL 0/7 RPL HRDW | TABLEMTN | ETL.6330.POLE.WOOD | 2022-04-15 | 2022-03-31 |  | 2022-09-27 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123335150 | 021/109 | T3 DI RND MTN TBL MTN #1 21/109 RPL ANCS | TABLEMTN | ETL.6060.TOWR | 2022-04-15 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Replace
LC | 123335312 | 006/146 | T3 DI VLT DSCHTS 6/146 RMV BUTT | TABLEMTN | ETL.8290.POLE.NWOD | 2022-04-15 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45458608 | T3 DI VLT DSCHTS 6/146 RMV BUTT | ICW
LC | 123335527 | 010/097 | T3 DI DRUM-HIGGINS 10/97L RPL STRW | SACTO | ETL.4393.POLE.WDPS | 2022-04-15 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31617831 | T3 DI DRUM-HIGGINS 009/088L RPL POLE | 70Y
LC | 123335604 | 010/097 | T3 DI DRUM-HIGGINS 10/97C RPL STRW | SACTO | ETL.4393.POLE.WDPS | 2022-04-15 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31617831 | T3 DI DRUM-HIGGINS 009/088L RPL POLE | 70Y
LC | 123335652 | 010/097 | T3 DI DRUM-HIGGINS 10/97R RPL STRW | SACTO | ETL.4393.POLE.WDPS | 2022-04-15 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31617831 | T3 DI DRUM-HIGGINS 009/088L RPL POLE | 70Y
LC | 123336807 | 009/209 | T3 DI KLRC-CDR CRK 9/209 RPL HRDW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-04-15 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | Missing | Hardware-Wood | Install | 45459155 | T3 DI KLRC-CDR CRK 9/209 RPL HRDW | ICW
LC | 123337366 | 008/186 | T3 DI KILARC-CEDAR CRK 8/186 RPL HRDD | TABLEMTN | ETL.7290.POLE.WOOD | 2022-04-15 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45459153 | T3 DI KILARC-CEDAR CRK 8/186 RPL HRDD | ICW
LC | 123337461 | 000/008 | T3 DI VOLTA-DESCHUTES 0/8 RPL HRDW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-15 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | Missing | Hardware-Wood | Install | 45458612 | T3 DI VOLTA-DESCHUTES 0/8 RPL HRDW | ICW
LC | 123337497 | 014/127 | T3 DI DRUM-RIO OSO #1 14/127 RPR STRT | SACTO | ETL.1420.TOWR | 2022-04-15 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Tower | Repair | 45582126 | T3 DI DRUM-RIO OSO #1 14/127 RPR STRT | ICQ
LC | 123337854 | 003/085 | T3 DI VOLTA-DESCHUTES 3/85 RPL STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-15 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31606238 | T3 DI VOLTA-DESCHUTES 002/061 RPL POLE | 70Y
LC | 123338502 | 006/138 | T3 DI KLRC CDR CRK 6/138 RPL SPLW | TABLEMTN | ETL.7290.INSL.CERA | 2022-04-15 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45459152 | T3 DI KLRC CDR CRK 6/138 RPL SPLW | ICW
LC | 123338618 | 007/178 | T3 DI KILARC-CEDAR CRK 7/178 RPR INSW | TABLEMTN | ETL.7290.INSL | 2022-04-15 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45459150 | T3 DI KILARC-CEDAR CRK 7/178 RPR INSW | ICW
LC | 123339159 | B023/529 | T3 EI DRM-GRSS VLLY-WMR B23/529 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2022-04-15 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123339452 | 000/004 | T3 DI SOBRANTE-"R" #1+ 00/04 RPR STRT | CONCORD | ETL.3770.TOWR | 2022-04-15 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123339537 | B023/518 | T3 EI DRM-GRSS VLLY-WMR B23/518 RPL HRDW | SACTO | ETL.6760.POLE.WOOD | 2022-04-15 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123340224 | 007/068 | T3 DI WOODLEAF-PALERMO 7/68L RPL HRDW | TABLEMTN | ETL.4220.POLE.STPS | 2022-04-15 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123341274 | 003/073 | T3 DI VOLTA-DESCHUTES 3/73 RPL HRDW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-15 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | Missing | Hardware-Wood | Install | 45458613 | T3 DI VOLTA-DESCHUTES 3/73 RPL HRDW | ICW
LC | 123341672 | 023/128 | T3 BAHIA-MORAGA 023/128 RPL INSS | CONCORD | ETL.4340.INSL.NCER | 2022-04-15 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW CREW OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31626482 | T3 BAHIA-MORAGA 023/128 RPL INSS | 93K
LC | 123343259 | 032/235 | T3 EI MDDL FRK-GLD HLL 32/235C RPUL GYWW | SACTO | ETL.5140.POLE.STPS | 2022-04-16 | 2022-04-16 |  | 2022-10-13 | 2022-10-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP CPUA OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123343271 | 032/235 | T3 EI MDL FRK-GLD HL 32/235L RPUL GYWW | SACTO | ETL.5140.POLE.STPS | 2022-04-16 | 2022-04-16 |  | 2022-10-13 | 2022-10-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP CPUA OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123343669 | 009/002 | T3 DI BRIDGEVL-GARBERVL 9/2 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-04-16 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31604325 | T2 EI BRIDGEVILLE-GARBERVILLE 0/4 RPL PL | 70Y
LC | 123343745 | 000/001 | T3 EI GEYSERS #3-CLVERDLE 0/1 RPR INSW | LAKEVLLE | ETL.1650.INSL.CERA | 2022-04-16 | 2022-04-16 |  | 2022-10-13 | 2022-10-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 45575656 | T3 EI GEYSERS #3-CLVERDLE 0/1 RPR INSW | ICW
LC | 123344781 | 001/007 | T3 EI GEYSERS #12-FULTON 1/7 RMV NEST | LAKEVLLE | ETL.4750.TOWR | 2022-04-16 | 2022-04-16 |  | 2022-10-13 | 2022-10-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove | 45571472 | T3 EI GEYSERS #12-FULTON 1/7 RMV NEST | ICS
LC | 123346820 | 010/053 | T3 DI MNT VST-CYT SS 10/53 RPL HRDT | MOSSLNDG | ETL.5090.TOWR | 2022-04-18 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123346822 | 010/053 | T3 DI MNT VST-CYT SS 10/53 RPR SHIELD | MOSSLNDG | ETL.5090.TOWR | 2022-04-18 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45581160 | T3 DI MNT VST-CYT SS 10/53 RPR SHIELD | ICS
LC | 123346964 | 006/052 | T3 DI ATASCADERO-CAYUCOS 6/52 RPR JMPW | PISMOBCH | ETL.8480.INSL.NCER | 2022-04-18 | 2022-03-30 |  | 2022-09-26 | 2022-09-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Wood | Repair | 45600529 | T3 DI ATASCADERO-CAYUCOS 6/52 RPR JMPW | ICW
LC | 123348067 | B024/532 | T3 EI DRM-GRS VLY-WMR B024/532 RPL HRDW | SACTO | ETL.6760.INSL.NCER | 2022-04-18 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Steel | Replace
LC | 123349547 | 009/051 | T3 DI RND MTN TBL MTN #1 9/51 RPL INSS | TABLEMTN | ETL.6060.INSL | 2022-04-18 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617248 | T3 DI RND MTN-TBL MTN #1 2/17 RPL INSS | 93K
LC | 123350504 | 034/286 | T3 DI PIT #1-CTTNWD 34/286 MASTIC | TABLEMTN | ETL.5390.TOWR | 2022-04-18 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45639714 | T3 DI PIT #1-CTTNWD 34/286 MASTIC | ICQ
LC | 123350789 | 003/009 | T3 DI BRIDGEVL-GARBERVL 3/9 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-04-18 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31604325 | T2 EI BRIDGEVILLE-GARBERVILLE 0/4 RPL PL | 70Y
LC | 123351211 | B023/517 | T3 EI DRM-GRS VLY-WMR B023/517 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-18 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606069 | T3 EI DRM-GRS VLY-WMR B017/401 RPL STRW | 70Y
LC | 123352305 | B023/516 | T3 EI DRM-GRS VLY-WMR B23/516 RPL HRDW | SACTO | ETL.6760.INSL.CERA | 2022-04-18 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123352467 | 011/001 | T3 EI MAPLE CREEK-HOOPA 11/001 RPR CNDW | EUREKA | ETL.7490.INSL | 2022-04-18 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair
LC | 123353610 | B018/404 | T3 EI DRM-GRS VLY-WMR B018/404 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-18 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606069 | T3 EI DRM-GRS VLY-WMR B017/401 RPL STRW | 70Y
LC | 123353705 | 009/050 | T3 DI RND MTN-TBL MTN #2 9/50 RPR GYWS | TABLEMTN | ETL.6070.TOWR | 2022-04-18 | 2022-04-02 |  | 2022-09-29 | 2022-10-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45457145 | T3 DI RND MTN-TBL MTN #2 9/50 RPR GYWS | ICS
LC | 123354525 | 012/277 | T3 DI KILARC-CEDAR CREEK 12/277 RPR INSW | TABLEMTN | ETL.7290.INSL | 2022-04-18 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45459148 | T3 DI KILARC-CEDAR CREEK 12/277 RPR INSW | ICW
LC | 123356254 | B023/513 | T3 EI DRM-GRS VLY-WMR B23/513 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-18 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606069 | T3 EI DRM-GRS VLY-WMR B017/401 RPL STRW | 70Y
LC | 123356255 | B023/511 | T3 EI DRM-GRS VLY-WMR B023/511 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-18 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606069 | T3 EI DRM-GRS VLY-WMR B017/401 RPL STRW | 70Y
LC | 123356289 | B023/512 | T3 EI DRM-GRS VLY-WMR B23/512 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-18 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606069 | T3 EI DRM-GRS VLY-WMR B017/401 RPL STRW | 70Y
LC | 123356819 | B017/399 | T3 EI DRM-GRSS VLLY-WMR B17/399 RPR ANCW | SACTO | ETL.6760.POLE.NWOD | 2022-04-18 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123357461 | B017/401 | T3 EI DRM-GRS VLY-WMR B017/401 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-18 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606069 | T3 EI DRM-GRS VLY-WMR B017/401 RPL STRW | 70Y
LC | 123357787 | :005/031 | T3 DI EAGLE ROCK-REDBUD :5/31 BNT STEEL | WILLITS | ETL.1480.TOWR | 2022-04-18 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123357986 | 000/017 | T3 DI VOLTA-DESCHUTES 0/17 RPL HRDW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-18 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45458683 | T3 DI VOLTA-DESCHUTES 0/17 RPL HRDW | ICW
LC | 123358087 | 011/104 | T3 DI DRUM-HIGGINS 11/104 RPL INSW | SACTO | ETL.4393.INSL.CERA | 2022-04-18 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617830 | T3 DI DRUM-HIGGINS 11/104 RPL INSW | 93I
LC | 123358683 | 010/235 | T3 DI KILARC-CEDAR CREK 010/235 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-04-18 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606234 | T3 EI KILARC-CEDAR CREEK 10/229 RPL POLE | 70Y
LC | 123359065 | 009/039 | T3 EI MRR BY-SLR SW ST #2 9/39 RPL INSS | PISMOBCH | ETL.5310.INSL.NCER | 2022-04-18 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619689 | MORRO BAY-SOLAR SW STA #2-REP INS 8 LSTS | 93K
LC | 123359105 | 009/039 | T3 EI MRR BY-SLR SW ST #1 9/39 RPL INSS | PISMOBCH | ETL.5300.INSL.NCER | 2022-04-18 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617859 | T3 EI MRR BY-SLR SW ST #1 RPL INSS 7WTR | 93K
LC | 123359486 | 000/009 | T3 DI MISSION POWER TAP 00/09 COTTER | LAKEVLLE | ETL.1651.INSL.NCER | 2022-04-18 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45575604 | T3 DI MISSION POWER TAP 00/09 COTTER | ICW
LC | 123359587 | 022/011 | T3 DI MAPLE CREEK-HOOPA 22/11 INS HRDD | EUREKA | ETL.7490.POLE.WOOD | 2022-04-18 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123359620 | A003/016 | T3 DI SBRNT-GRZLY-CLRMT#1 3/16 BNT STL | CONCORD | ETL.3740.TOWR | 2022-04-18 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123359754 | 018/077 | T3 DI EGL RCK-FLTN-SLVRD 18/77 RMV NEST | LAKEVLLE | ETL.4392.TOWR | 2022-04-18 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45571495 | T3 DI EGL RCK-FLTN-SLVDO 18/77 RPR INSS | ICS
LC | 123359757 | 018/077 | T3 DI EGL RCK-FLTN-SLVDO 18/77 RPR INSS | LAKEVLLE | ETL.4392.INSL.CERA | 2022-04-18 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571495 | T3 DI EGL RCK-FLTN-SLVDO 18/77 RPR INSS | ICS
LC | 123359783 | 010/234 | T3 DI DRM-GRAS VLLY-WMR 10/234 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2022-04-18 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123359880 | 023/005 | T3 DI MAPLE CREEK-HOOPA 23/5 RPR STRW | EUREKA | ETL.7490.POLE.NWOD | 2022-04-18 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123359969 | 001/029 | T3 DI KESWICK-TRINITY 01/29 RPR HRDW | TABLEMTN | ETL.7270.POLE.WOOD | 2022-04-18 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123360048 | 005/044 | T3 DI SBRNTE-GRZZLY-CLAREMT 05/44 COTTER | CONCORD | ETL.3740.INSL.CERA | 2022-04-18 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45513127 | T3 DI SBRNTE-GRZZLY-CLAREMT 05/44 COTTER | ICS
LC | 123360120 | 005/044 | T3 DI SBRNTE-GRZZLY-CLRMT 05/44 RPR STRT | CONCORD | ETL.3740.TOWR | 2022-04-18 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45513128 | T3 DI SBRNTE-GRZZLY-CLRMT 05/44 RPR STRT | ICS
LC | 123361244 | 003/067 | T3 DI VOLTA-DESCHUTES 3/67 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-19 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606238 | T3 DI VOLTA-DESCHUTES 002/061 RPL POLE | 70Y
LC | 123362121 | 001/024 | T3 DI VOLTA-SOUTH 1/24 RPL SPLW | TABLEMTN | ETL.8300.INSL | 2022-04-19 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Replace | 45456224 | T3 DI VOLTA-SOUTH 1/24 RPL SPLW | ICW
LC | 123362300 | 010/109 | T3 DI DRN RIO OSO #2 010/109L REFRAME | SACTO | ETL.1430.POLE.STPS | 2022-04-19 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31619067 | T3 EI DRUM-RIO OSO #2 7/82 RPL CRSW | 93E
LC | 123364226 | 001/029 | T3 DI CNTRVL TBL MTN ORVL 1/29 RMV BUTT | TABLEMTN | ETL.6330.POLE.NWOD | 2022-04-19 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove
LC | 123364842 | 007/011 | T3 EI MNDCNO-WLITS-FRT BRG 7/11 RPR IBWW | WILLITS | ETL.7550.INSL.NCER | 2022-04-19 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45640354 | T3 EI MNDCNO-WLITS-FRT BRG 7/11 RPR IBWW | ICW
LC | 123365133 | 006/041 | T3 DI SBRNT GRZLY CLRMNT 2 6/41 RPL HRDT | CONCORD | ETL.3750.TOWR | 2022-04-19 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123365322 | 006/041 | T3 DI SBRNT GRZLY CLRMNT 2 6/41 COTTER | CONCORD | ETL.3750.INSL | 2022-04-19 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45513129 | T3 DI SBRNT GRZLY CLRMNT 2 6/41 COTTER | ICS
LC | 123365402 | 011/006 | T3 EI MAPLE CREEK-HOOPA 11/6 RPR CNDW | EUREKA | ETL.7490.INSL.NCER | 2022-04-19 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair
LC | 123365603 | 007/010 | T3 EI MNDCNO-WLITS-FRT BRG 7/10 RPR IBWW | WILLITS | ETL.7550.INSL.NCER | 2022-04-19 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45640355 | T3 EI MNDCNO-WLITS-FRT BRG 7/10 RPR IBWW | ICW
LC | 123365642 | 007/010 | T3 EI MNDCNO-WLTS-FRT BRG 7/10 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2022-04-19 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45640356 | T3 EI MNDCNO-WLTS-FRT BRG 7/10 RPR STRW | ICW
LC | 123365683 | 014/059 | T3 EI MR BAY-SLR SW STA #114/59 RPL INSS | PISMOBCH | ETL.5300.INSL | 2022-04-19 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617859 | T3 EI MRR BY-SLR SW ST #1 RPL INSS 7WTR | 93K
LC | 123366424 | B021/482 | T3 EI DRUM-GRASS VALLEY B21/482 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-19 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31631449 | T2 EI DRUM-GRSS VLLY-WMR 18/427 RPL POLE | 70Y
LC | 123367762 | 014/061 | T3 EI MRRO BY-SOLAR SS#2 14/61 RPL INSS | PISMOBCH | ETL.5310.INSL | 2022-04-19 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619689 | MORRO BAY-SOLAR SW STA #2-REP INS 8 LSTS | 93K
LC | 123367763 | 014/061 | T3 EI MRO BAY-SLR SW ST #114/61 RPL INSS | PISMOBCH | ETL.5300.INSL | 2022-04-19 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617859 | T3 EI MRR BY-SLR SW ST #1 RPL INSS 7WTR | 93K
LC | 123367965 | 002/030 | T3 EI GEYSERS #3-CLOVRDALE 2/30 RMV VEG | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-04-19 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP PGEA OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123369583 | 004/089 | T3 DI VOLTA-DESCHUTES 4/89 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-19 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606238 | T3 DI VOLTA-DESCHUTES 002/061 RPL POLE | 70Y
LC | 123370014 | 006/139 | T3 DI VOLTA-DESCHUTES 6/139 RPL HRDW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-19 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45458696 | T3 DI VOLTA-DESCHUTES 6/139 RPL HRDW | ICW
LC | 123370187 | 022/001A | T3 DI MNTE RIO-FRT ROSS 22/001A RPR HRDS | LAKEVLLE | ETL.6979.SWIT | 2022-04-19 | 2022-04-04 |  | 2022-10-01 | 2022-10-04 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Steel | Replace | 45575619 | T3 DI MNTE RIO-FRT ROSS 22/001A RPR HRDS | ICS
LC | 123370535 | 003/002 | T3 DI BRIDGEVL-GARBERVLL 3/002 REPULL | EUREKA | ETL.6220.POLE.NWOD | 2022-04-19 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45416596 | T3 DI BRDGVLL-GRBRVLL 3/002 REPULL | ICW
LC | 123370826 | 027/013 | T3 DI FULTON-HOPLAND 027/013 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2022-04-19 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606074 | T3 DI FULTON-HOPLAND 027/013 RPL POLE | 70Y
LC | 123370880 | 025/103 | T3 DI XCHQR-IDN FLT-YSMT 25/103 RPL HRDT | FRESNO | ETL.8650.POLE.NWOD | 2022-04-19 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123370887 | 025/103 | T3 DI XCHQR-IDN FLT-YSMT 25/103 RPR SHLD | FRESNO | ETL.8650.POLE.NWOD | 2022-04-19 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45489062 | T3 DI XCHQR-IDN FLT-YSMT 25/103 RPR SHLD | ICS
LC | 123371140 | 006/014 | T3 DI BRIDGEVLLE-GARBERVL 6/14 REPULL | EUREKA | ETL.6220.POLE.NWOD | 2022-04-19 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45416597 | T3 DI BRIDGEVLLE-GRBRVLLE 6/14 REPULL | ICW
LC | 123371315 | 028/008 | T3 DI FULTON-HOPLAND 028/008 RPL INSW | LAKEVLLE | ETL.6890.INSL | 2022-04-19 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31619390 | T3 DI FULTON-HOPLAND 028/008 RPL INSW | 93I
LC | 123371331 | 006/078 | T3 DI GREEN VLLY-CMP EVRS 6/78L RPL HRDW | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-04-19 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45606021 | T3 DI GREEN VLLY-CMP EVRS 6/78L RPL HRDW | ICW
LC | 123371339 | 006/078 | T3 DI GREEN VLLY-CMP EVRS 6/78R RPL HRDW | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-04-19 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45606022 | T3 DI GREEN VLLY-CMP EVRS 6/78R RPL HRDW | ICW
LC | 123371355 | 006/078 | T3 DI GREEN VLLY-CMP EVRS 6/78C RPL HRDW | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-04-19 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45606023 | T3 DI GREEN VLLY-CMP EVRS 6/78C RPL HRDW | ICW
LC | 123371417 | 008/001 | T3 DI BRIDGEVILLE-GARBERVL 8/01 REPULL | EUREKA | ETL.6220.POLE.NWOD | 2022-04-19 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45416598 | T3 DI BRIDGVLLE-GRBRVILLE 8/01 REPULL | ICW
LC | 123371614 | 030/248 | T3 DI RND MTN-CTNWD #3 30/248 RPR INSS | TABLEMTN | ETL.5650.INSL | 2022-04-19 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123371615 | 034/295 | T3 DI PIT #1-COTTONWOOD 34/295 RPR ANCS | TABLEMTN | ETL.5390.TOWR | 2022-04-19 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair
LC | 123371934 | 009/092 | T3 DI DRUM-HIGGINS 9/92L RPR GYWW | SACTO | ETL.4393.POLE.STPS | 2022-04-19 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123372814 | 029/006 | T3 DI FULTON-HOPLAND 29/6 RPL HRDW | LAKEVLLE | ETL.6890.POLE.WOOD | 2022-04-20 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45571453 | T3 DI FULTON-HOPLAND 29/6 RPL HRDW | ICW
LC | 123372817 | 029/006 | T3 DI FULTON-HOPLAND 29/6 RPR INSW | LAKEVLLE | ETL.6890.INSL.NCER | 2022-04-20 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45571439 | T3 DI FULTON-HOPLAND 29/6 RPR INSW | ICW
LC | 123372875 | 012/010 | T3 EI MAPLE CREEK-HOOPA 12/10 REFRAME | EUREKA | ETL.7490.POLE.WOOD | 2022-04-20 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace
LC | 123373259 | B017/389 | T3 EI DRM-GRSS VLY-WMAR B17/389 RPR INSW | SACTO | ETL.6760.INSL.CERA | 2022-04-20 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123373319 | 009/250 | T3 DI COLGATE-ALLEGHANY 9/250 RPL HRDD | SACTO | ETL.6470.POLE.WOOD | 2022-04-20 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123373682 | B022/505 | T3 EI DRM-GRS VLY-WMR B022/505 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-20 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123373927 | B017/392 | T3 EI DRM-GRS VLY-WMR B17/392 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-20 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123374605 | B022/502 | T3 EI DRM-GRS VLY-WMR B022/502 RPL HRDW | SACTO | ETL.6760.INSL.NCER | 2022-04-20 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123374678 | 000/007 | T3 DI KILARC-CEDAR CREEK 0/7 RPR SWTC | TABLEMTN | ETL.7290.SWIT | 2022-04-20 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Switch-Wood | Repair | 45459147 | T3 DI KILARC-CEDAR CREEK 0/7 RPR SWTC | ICW
LC | 123374710 | :005/030 | T3 DI EAGLE ROCK-CORTINA :5/030 RPR INSS | WILLITS | ETL.1470.INSL.NCER | 2022-04-20 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45440923 | T3 DI EAGLE ROCK-CORTINA :5/030 RPR INSS | ICS
LC | 123375330 | 008/006 | T3 WV POTTER VALLEY-WILLITS 8/6 INS INSW | WILLITS | ETL.7820.INSL.NCER | 2022-04-20 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31604795 | T2 DI PTTR VLLEY-WILLITS 02/03 RPL INSW | 93I
LC | 123375332 | B022/500 | T3 EI DRM-GRS VLY-WMR B022/500 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-20 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123375341 | 029/002 | T3 DI FULTON-HOPLAND 29/2 RPR ANCW | LAKEVLLE | ETL.6890.POLE.NWOD | 2022-04-20 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45571452 | T3 DI FULTON-HOPLAND 29/2 RPR ANCW | ICW
LC | 123375568 | 012/047 | T3 EI PITTSBURG-SAN RMN 12/047 RPR INSS | CONCORD | ETL.5490.INSL | 2022-04-20 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair | 45513130 | T3 EI PITTSBURG-SAN RMN 12/047 RPR INSS | ICS
LC | 123375769 | 031/232 | T3 EI MDLE FRK-GOLD HIL 31/232R RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2022-04-20 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123375805 | B020/454 | T3 EI DRM-GRS VLY-WMR B20/454 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2022-04-20 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31608820 | T3 EI DRM-GRS VLY-WMR B20/454 RPL POLE | 70Y
LC | 123375879 | B022/498 | T3 EI DRM-GRS VLY-WMR B022/498 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-20 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31631449 | T2 EI DRUM-GRSS VLLY-WMR 18/427 RPL POLE | 70Y
LC | 123376584 | 018/276 | T3 DI GOLD HILL #1 18/276 RPL HRDW | SACTO | ETL.6950.POLE.WOOD | 2022-04-20 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123377210 | 016/142 | T3 DI DRUM-HIGGINS 16/142 RPR INSS | SACTO | ETL.4393.INSL.CERA | 2022-04-20 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45644102 | T3 DI DRUM-HIGGINS 16/142 RPR INSS | ICS
LC | 123379606 | 009/050 | T3 DI METCALF-MNT VST #3 9/50 RPL INSS | MOSSLNDG | ETL.5091.INSL | 2022-04-20 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617199 | DI METCALF-MONTA VISTA #3 RPL INSS 3 TWR | 93K
LC | 123379979 | 006/012 | T3 DI BRIDGEVL-GARBERVL 6/12 RPL INSW | EUREKA | ETL.6220.INSL.CERA | 2022-04-20 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617171 | T3 EI BRIDGEVILLE-GRBRVLL 3/0 RPL INSW | 93I
LC | 123380472 | 003/040 | T3 DI DESABLA-CNTRVL 3/40L RPR GYWW | TABLEMTN | ETL.6720.POLE.WDPS | 2022-04-20 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123380475 | 003/040 | T3 DI DESABLA-CNTRVL 3/40R RPR STRW | TABLEMTN | ETL.6720.POLE.WDPS | 2022-04-20 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123380477 | 003/040 | T3 DI DESABLA-CNTRVL 3/40R RPR HRDW | TABLEMTN | ETL.6720.POLE.WDPS | 2022-04-20 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123380521 | 003/040 | T3 DI DESABLA-CNTRVL 3/40C RPL HRDW | TABLEMTN | ETL.6720.POLE.WDPS | 2022-04-20 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123380524 | 003/040 | T3 DI DESABLA-CNTRVLL 3/40 RPL SPLW | TABLEMTN | ETL.6720.INSL.CERA | 2022-04-20 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Replace
LC | 123380566 | 001/016 | T3 DI SBRT-GRZLY-CLRMNT #2 1/16 INS HRDT | CONCORD | ETL.3750.TOWR | 2022-04-20 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install
LC | 123380692 | 003/041 | T3 DI DSBLA-CNTRVLLE 3/41C RPR GYWW | TABLEMTN | ETL.6720.POLE.STPS | 2022-04-20 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123380693 | 003/041 | T3 DI DSBLA-CNTRVLLE 3/41R RPR GYWW | TABLEMTN | ETL.6720.POLE.STPS | 2022-04-20 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123380828 | 047/206 | T3 DI MTCLF-MSS LNDNG #1 47/206 RPL INSS | MOSSLNDG | ETL.5100.INSL | 2022-04-20 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31613618 | T2 DI MTCLF-MSS LNDG #1 RPL INSS 5TWR | 93K
LC | 123380829 | 047/206 | T3 DI MTCLF-MSS LNDNG #2 47/206 RPL INSS | MOSSLNDG | ETL.5110.INSL.NCER | 2022-04-20 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31608011 | T3 DI MTCLF-MSS LNDNG #2 RPL INSS 5 TWR | 93K
LC | 123380903 | 011/101A | T3 DI DRUM-HIGGINS 11/101A RPR ANCW | SACTO | ETL.4393.POLE.NWOD | 2022-04-20 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123380913 | 000/005 | T3 DI KNCTI-EAGLE RCK 0/5 RPR GYWW | WILLITS | ETL.6861.POLE.NWOD | 2022-04-20 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123380940 | 016/135 | T3 DI DRUM-RIO OSO #1 016/135 UNBURY | SACTO | ETL.1420.TOWR | 2022-04-20 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45582127 | T3 DI DRUM-RIO OSO #1 016/135 UNBURY | ICQ
LC | 123380948 | 000/008 | T3 DI WEST PNT-VALLY SPRNGS 0/8 RPR GYWW | VICTOR | ETL.8350.POLE.WOOD | 2022-04-20 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45531527 | T3 DI WEST PNT-VALLY SPRNGS 0/8 RPR GYWW | ICW
LC | 123380949 | 005/053 | T3 DI DRUM-HIGGINS 5/53 RPL CRSS | SACTO | ETL.4393.POLE.STPS | 2022-04-20 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Steel | Replace
LC | 123380963 | :003/019 | T3 DI EAGLE ROCK-CORTINA :3/19 WASH INSS | WILLITS | ETL.1470.INSL.NCER | 2022-04-20 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 622 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | Contaminated | Insulator | Ground Wash | 45593458 | T3 DI EAGLE ROCK-CORTINA :3/19 WASH INSS | ICD
LC | 123381015 | 000/011 | T3 DI ORO FINO TAP 0/11 RPL HRDW | TABLEMTN | ETL.6721.POLE.WOOD | 2022-04-20 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123382155 | 022/000 | T3 DI MNT RIO FRT RS 22/0 COTTER | LAKEVLLE | ETL.6979.INSL.NCER | 2022-04-21 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45575610 | T3 DI MNT RIO FRT RS 22/0 COTTER | ICW
LC | 123382279 | 034/294 | T3 DI PT #1 CTNWD 34/294 RPR GYWS | TABLEMTN | ETL.5390.TOWR | 2022-04-21 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123382800 | 002/010 | T3 DI BRIDGEVL-GARBERVL 2/10 RPR HRDW | EUREKA | ETL.6220.POLE.WOOD | 2022-04-21 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45416599 | T3 DI BRDGVLLE-GRBRVLLE 2/10 RPR HRDW | ICW
LC | 123382841 | 009/007 | T3 EI MAPLE CREEK-HOOPA 9/7 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2022-04-21 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123385833 | 006/008 | T3 DI BRIDGEVL-GARBERVL 06/008 RPR CNDW | EUREKA | ETL.6220.INSL.CERA | 2022-04-21 | 2022-04-05 |  | 2022-10-02 | 2022-10-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45416600 | T3 DI BRDGVLL-GRBRVILLE 06/008 RPR CNDW | ICW
LC | 123386536 | 013/002 | T3 EI MAPLE CREEK-HOOPA 13/2 RPL ANCW | EUREKA | ETL.7490.POLE.WOOD | 2022-04-21 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace
LC | 123386537 | 013/002 | T3 EI MAPLE CREEK-HOOPA 13/2 RPR GYWW | EUREKA | ETL.7490.POLE.WOOD | 2022-04-21 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123387257 | 013/005 | T3 EI MAPLE CREEK-HOOPA 13/5 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2022-04-21 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123387810 | 000/003 | T3 DI KONOCTI-EAGLE ROCK 0/3 RPR STRW | WILLITS | ETL.6861.POLE.WOOD | 2022-04-21 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123388213 | 002/040 | T3 DI CNTRVLLE-TBL MTN 2/40 BACKFILL | TABLEMTN | ETL.6320.POLE.NWOD | 2022-04-21 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123388361 | 022/005A | T3 DI MI-WUK-CURTIS 22/5A RPR ANCW | VICTOR | ETL.1073.POLE.NWOD | 2022-04-21 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45519251 | T3 DI MI-WUK-CURTIS 22/5A RPR ANCW | ICW
LC | 123388455 | 009/092 | T3 DI DRUM-RIO OSO #2 009/092 RPR FOND | SACTO | ETL.1430.TOWR | 2022-04-21 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45600069 | T3 DI DRUM-RIO OSO #2 009/092 RPR FOND | ICQ
LC | 123388474 | 001/011 | T3 DI SOBRANTE-R #1 1/11 RMV VEGETATION | CONCORD | ETL.3770.TOWR | 2022-04-21 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123388515 | 010/281 | T3 DI COLGATE-ALLEGHANY 10/281 RPR SPLW | SACTO | ETL.6470.INSL.NCER | 2022-04-21 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 123388532 | 020/140 | T3 DI MTCLF-GRN VLY 20/140L RPL HRDW | MOSSLNDG | ETL.2540.POLE.WDPS | 2022-04-21 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45274954 | T3 DI MTCLF-GRN VLY 20/140L RPL HRDW | ICW
LC | 123388539 | 014/076 | T3 DI MNTA VSTA-CYTE SS 14/76 RPR SHLS | MOSSLNDG | ETL.5090.TOWR | 2022-04-21 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45606037 | T3 DI MNTA VSTA-CYTE SS 14/76 RPR SHLS | ICS
LC | 123388561 | 020/097 | T3 DI MONTA VISTA-CYTE SS 20/97 RPR INSS | MOSSLNDG | ETL.5090.INSL | 2022-04-21 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45606038 | T3 DI MONTA VISTA-CYTE SS 20/97 RPR INSS | ICS
LC | 123388582 | 014/076 | T3 DI MNTA VSTA-CYTE SS 14/76 RPL INSS | MOSSLNDG | ETL.5090.INSL | 2022-04-21 | 2022-04-07 |  | 2022-10-04 | 2022-10-07 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31602349 | T2 DI MNT VST CYT SS RPL INSS 3TWR | 93K
LC | 123388602 | 016/448 | T3 DI COLGATE-ALLEGHANY 16/448 RMV STEP | SACTO | ETL.6470.POLE.NWOD | 2022-04-21 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123388665 | 013/059 | T3 DI EGL RCK-FLTN-SLVRD 13/59 RPR INSS | LAKEVLLE | ETL.4392.INSL.CERA | 2022-04-21 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123388841 | 009/113 | T3 DI GEYSERS #3-CLOVRDLE 9/113 RPL POLE | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-04-21 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31601685 | T3 DI GEYSERS #3-CLOVRDLE 9/113 RPL POLE | 70Y
LC | 123388912 | 010/107 | T3 DI DRUM-RIO OSO #1 010/107 RPL HRDT | SACTO | ETL.1420.TOWR | 2022-04-21 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45582124 | T3 DI DRUM-RIO OSO #1 010/107 RPL HRDT | ICQ
LC | 123388916 | 001/020 | T3 DI DESABLA-CENTERVILLE 1/20R RPR GYWW | TABLEMTN | ETL.6720.POLE.WDPS | 2022-04-21 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123388948 | 010/108 | T3 DI DRUM-RIO OSO#2 010/108 REFRAME | SACTO | ETL.1430.POLE.STPS | 2022-04-21 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31619067 | T3 EI DRUM-RIO OSO #2 7/82 RPL CRSW | 93E
LC | 123388981 | 011/106 | T3 DI DRUM-HIGGINS 11/106L RPL XBRACE | SACTO | ETL.4393.POLE.WDPS | 2022-04-21 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair
LC | 123388991 | 022/005B | T3 DI MI-WUK-CURTIS 22/55B RPR ANCW | VICTOR | ETL.1073.POLE.NWOD | 2022-04-21 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45519252 | T3 DI MI-WUK-CURTIS 22/55B RPR ANCW | ICW
LC | 123389019 | 009/261 | T3 DI CLGTE-ALLGHNY 009/261 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-04-21 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31633457 | T3 DI COLGATE-ALLEGHANY 008/222 RPL STRW | 70Y
LC | 123389027 | 033/282 | T3 DI PIT #1-CTTNWD 033/282 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2022-04-21 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45639712 | T3 DI PIT #1-CTTNWD 033/282 RPR FOND | ICQ
LC | 123389045 | 002/013 | T3 DI SOBRANTE-R #1 2/13 RPL HRDT | CONCORD | ETL.3770.TOWR | 2022-04-21 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123389052 | 000/018 | T3 DI KESWICK-TRINITY 0/18 RMV BUTT | TABLEMTN | ETL.7270.POLE.WOOD | 2022-04-21 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123390604 | 003/001 | T3 DI BRIDGEVILLE-GARBERVL 3/1 RPL INSW | EUREKA | ETL.6220.INSL.CERA | 2022-04-22 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617171 | T3 EI BRIDGEVILLE-GRBRVLL 3/0 RPL INSW | 93I
LC | 123390658 | 006/005 | T3 DI LRLS-OTTER 006/005R RPR STRW | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-04-22 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123390777 | :027/003 | T3 DI FULTON-HOPLAND :027/003 RPL HRDW | LAKEVLLE | ETL.6890.POLE.WOOD | 2022-04-22 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45571434 | T3 DI FULTON-HOPLAND :027/003 RPL HRDW | ICW
LC | 123391026 | 019/004 | T3 MNTE RIO-FRT ROSS 019/004 RPL STRW | LAKEVLLE | ETL.6979.POLE.WOOD | 2022-04-22 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW CREW OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606070 | T3 MNTE RIO-FRT ROSS 019/004 RPL STRW | 70Y
LC | 123391180 | 007/089 | T3 DI GYSRS #3-CLVRDLE 07/89 RPL STRW | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-04-22 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Rotten | Structure-Wood | Replace | 31614662 | T3 EI GEYSERS #3-CLOVRDALE 3/38 RPL STRW | 70Y
LC | 123391188 | 000/006 | T3 DI SOBRANTE-"R" #1 0/6 BNT STEEL | CONCORD | ETL.3770.TOWR | 2022-04-22 | 2022-04-06 |  | 2022-10-03 | 2022-10-06 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123391296 | 018/179 | T3 EI RND MTN-CTONWD #2 18/179 RPR FOND | TABLEMTN | ETL.5640.TOWR | 2022-04-22 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123391565 | 019/094 | T3 DI METCALF-MONTA VSTA #3 19/94 COTTER | MOSSLNDG | ETL.5091.INSL | 2022-04-22 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45606040 | T3 DI METCALF-MONTA VSTA #3 19/94 COTTER | ICS
LC | 123391566 | 019/094 | T3 DI MNTA VSTA-CYTE SS 19/94 RPR SHIELD | MOSSLNDG | ETL.5090.TOWR | 2022-04-22 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45606041 | T3 DI MNTA VSTA-CYTE SS 19/94 RPR SHIELD | ICS
LC | 123391788 | 013/059 | T3 DI GEYSERS #9-LAKEVLLE 13/59 RPR INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2022-04-22 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575584 | T3 DI GEYSERS #9-LAKEVLLE 13/59 RPR INSS | ICS
LC | 123391842 | 013/009 | T3 EI MAPLE CREEK-HOOPA 13/9 REPUL GYWW | EUREKA | ETL.7490.POLE.NWOD | 2022-04-22 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123391943 | 016/001 | T3 EI MAPLE CREEK-HOOPA 16/1 RPR STRW | EUREKA | ETL.7490.POLE.WOOD | 2022-04-22 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123392349 | 013/010 | T3 EI MAPLE CREEK-HOOPA 13/10 RPR GWRS | EUREKA | ETL.7490.POLE.NWOD | 2022-04-22 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45474400 | T3 EI MAPLE CREEK-HOOPA 13/10 RPR GWRS | ICS
LC | 123392412 | 013/010 | T3 EI MAPLE CREEK-HOOPA 13/10 INS AMGS | EUREKA | ETL.7490.POLE.NWOD | 2022-04-22 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Missing | Animal Guard-Steel | Install | 45474400 | T3 EI MAPLE CREEK-HOOPA 13/10 RPR GWRS | ICS
LC | 123392942 | 001/006 | T3 DI KNCT EGL RCK 001/006 RPL HRDD | WILLITS | ETL.6861.POLE.WOOD | 2022-04-22 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123393060 | 011/048 | T3 DI GYSRS #9-LAKEVILLE 11/048 RPR INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2022-04-22 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575599 | T3 DI GYSRS #9-LAKEVILLE 11/048 RPR INSS | ICS
LC | 123393100 | 007/064 | T3 DI WOODLEAF-PALERMO 7/64L RPR POLE | TABLEMTN | ETL.4220.POLE.WDPS | 2022-04-22 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123393635 | 000/012 | T3 DI VLTA-SOUTH 1/012 RPR INSW | TABLEMTN | ETL.8300.INSL | 2022-04-22 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45456230 | T3 DI VLTA-SOUTH 1/012 RPR INSW | ICW
LC | 123393990 | 015/006 | T3 EI MAPLE CREEK-HOOPA 15/6R RPR GWRW | EUREKA | ETL.7490.POLE.WDPS | 2022-04-22 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123394458 | 014/072 | T3 DI METCALF-MONTA VSTA #3 14/72 COTTER | MOSSLNDG | ETL.5091.INSL | 2022-04-22 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45606045 | T3 DI METCALF-MONTA VSTA #3 14/72 COTTER | ICS
LC | 123394667 | 003/022 | T3 DI SOBRANTE-R #1 3/22 RMV VEG | CONCORD | ETL.3770.TOWR | 2022-04-22 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123394811 | 003/022 | T3 DI SOBRANTE-R #2 3/22 RPL INSS | CONCORD | ETL.3780.INSL | 2022-04-22 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31609260 | T3 DI SOBRANTE-R #2 3/22 RPL INSS | 93K
LC | 123394812 | 003/022 | T3 DI SOBRANTE-R #1 3/22 RPL INSS | CONCORD | ETL.3770.INSL | 2022-04-22 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31609199 | T3 DI SOBRANTE-R #1 RPL INSS 2TWR | 93K
LC | 123395206 | 004/095 | T3 DI VOLTA-DESCHUTES 4/95 RPL HRDD | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-22 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45458821 | T3 DI VOLTA-DESCHUTES 4/95 RPL HRDD | ICW
LC | 123395490 | 015/002 | T3 EI MAPLE CREEK-HOOPA 5/2 RPR GWRS | EUREKA | ETL.7490.POLE.NWOD | 2022-04-22 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45593187 | T3 EI MAPLE CREEK-HOOPA 5/2 RPR GWRS | ICS
LC | 123395596 | 020/000 | T3 DI FULTON-HOPLAND 020/000 RPR GYWW | LAKEVLLE | ETL.6890.POLE.NWOD | 2022-04-22 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45571435 | T3 DI FULTON-HOPLAND 020/000 RPR GYWW | ICW
LC | 123395954 | 033/279 | T3 DI PT #1 CTNWD 33/279 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2022-04-22 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45639710 | T3 DI PT #1 CTNWD 33/279 RPR STRT | ICQ
LC | 123395959 | 033/279 | T3 DI RND MTN CTNWD #3 33/279 RPR STRT | TABLEMTN | ETL.5650.TOWR | 2022-04-22 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123397310 | 014/397 | T3 DI COLGATE-ALLEGHANY 14/397 RPL SPLW | SACTO | ETL.6470.INSL.NCER | 2022-04-22 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Replace
LC | 123397802 | 008/101 | T3 EI GYSERS #3-CLVRDLE 008/101 RPR STRW | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-04-22 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP PGEA OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45576007 | T3 EI GYSERS #3-CLVRDLE 008/101 RPR STRW | ICW
LC | 123399282 | 010/238 | T3 EI DRM-GRSS VLLY-WMR 10/238 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2022-04-23 | 2022-04-23 |  | 2022-10-20 | 2022-10-23 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617788 | T3 DI DRM-GRSS VLLY-WMR 6/154 RPL POLE | 70Y
LC | 123399601 | 014/006 | T3 EI MAPLE CREEK-HOOPA 14/6 RPR GWRW | EUREKA | ETL.7490.POLE.NWOD | 2022-04-23 | 2022-04-23 |  | 2022-10-20 | 2022-10-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123400668 | 014/008 | T3 EI MAPLE CREEK-HOOPA 14/8 RPR GWRW | EUREKA | ETL.7490.POLE.NWOD | 2022-04-23 | 2022-04-23 |  | 2022-10-20 | 2022-10-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123400733 | 033/277 | T3 DI PT #1 CTNWD 33/277 RPR STRS | TABLEMTN | ETL.5390.TOWR | 2022-04-23 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45639708 | T3 DI PT #1 CTNWD 33/277 RPR STRS | ICQ
LC | 123401057 | 018/002 | T3 EI MAPLE CREEK-HOOPA 8/2 RPL DMPS | EUREKA | ETL.7490.INSL.NCER | 2022-04-23 | 2022-04-23 |  | 2022-10-20 | 2022-10-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 45593191 | T3 EI MAPLE CREEK-HOOPA 8/2 RPL DMPS | ICS
LC | 123401325 | 020/083 | T3 EI GEYSERS #12-FULTON 020/083 RMV VEG | LAKEVLLE | ETL.4750.TOWR | 2022-04-23 | 2022-04-23 |  | 2022-10-20 | 2022-10-23 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123402071 | 000/016 | T3 DI KSWCK TRNTY 0/16 RMV DBRW | TABLEMTN | ETL.7270.POLE.WOOD | 2022-04-23 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123402479 | 020/005 | T3 EI MAPLE CREEK-HOOPA 20/5 INS COTTER | EUREKA | ETL.7490.INSL.NCER | 2022-04-23 | 2022-04-23 |  | 2022-10-20 | 2022-10-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123402789 | 019/002 | T3 EI MAPLE CREEK-HOOPA 19/2 RPLS INSW | EUREKA | ETL.7490.INSL.NCER | 2022-04-23 | 2022-04-23 |  | 2022-10-20 | 2022-10-23 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace
LC | 123403024 | 020/000 | T3 EI MAPLE CREEK-HOOPA 20/0 RMV DBRS | EUREKA | ETL.7490.POLE.NWOD | 2022-04-23 | 2022-04-23 |  | 2022-10-20 | 2022-10-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123403102 | 019/003 | T3 EI MAPLE CREEK-HOOPA 19/3 RPR GWRW | EUREKA | ETL.7490.POLE.NWOD | 2022-04-23 | 2022-04-23 |  | 2022-10-20 | 2022-10-23 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Pole-Steel | Replace
LC | 123403272 | 019/011 | T3 EI MAPLE CREEK-HOOPA 19/11 RPR GWRW | EUREKA | ETL.7490.POLE.WOOD | 2022-04-23 | 2022-04-23 |  | 2022-10-20 | 2022-10-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123403279 | 019/004 | T3 EI MAPLE CREEK-HOOPA 19/4 RPL STRW | EUREKA | ETL.7490.POLE.WOOD | 2022-04-23 | 2022-04-23 |  | 2022-10-20 | 2022-10-23 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Rotten | Structure-Wood | Replace
LC | 123403441 | 019/005 | T3 EI MAPLE CREEK-HOOPA 19/5 RPR GWRW | EUREKA | ETL.7490.POLE.WOOD | 2022-04-23 | 2022-04-23 |  | 2022-10-20 | 2022-10-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Ground Wire-Wood | Repair
LC | 123403562 | 032/275 | T3 DI PIT #1-COTTONWOOD 32/275 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2022-04-23 | 2022-04-08 |  | 2022-10-05 | 2022-10-08 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45639706 | T3 DI PIT #1-COTTONWOOD 32/275 RPR STRT | ICQ
LC | 123405243 | 034/293 | T3 DI RND MTN-CTN WD #3 34/293 BNT STEEL | TABLEMTN | ETL.5650.TOWR | 2022-04-25 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123405615 | 001/007 | T3 DI TGR CK-ELECTRA 1/7 RPR STRS | VICTOR | ETL.5780.TOWR | 2022-04-25 | 2022-04-09 |  | 2022-10-06 | 2022-10-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45531529 | T3 DI TGR CK-ELECTRA 1/7 RPR STRS | ICS
LC | 123405762 | 019/006 | T3 EI MAPLE CREEK-HOOPA 19/6 REFRAME | EUREKA | ETL.7490.POLE.NWOD | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace
LC | 123406009 | 019/007 | T3 EI MAPLE CREEK-HOOPA 19/7 RPR GYWW | EUREKA | ETL.7490.POLE.WOOD | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123406539 | 019/008 | T3 EI MAPLE CREEK-HOOPA 19/8 RPR GYWW | EUREKA | ETL.7490.POLE.WOOD | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123406544 | 013/107A | T3 EI MDDLE FORK-GLD HILL 13/10 RPR ANCS | SACTO | ETL.5140.POLE.NWOD | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair
LC | 123406881 | 017/465 | T3 DI CLGT-ALLGHNY 17/465 RPR INSW | SACTO | ETL.6470.INSL.NCER | 2022-04-25 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123406884 | 017/465 | T3 DI CLGT-ALLGHNY 17/465 RPR CNDW | SACTO | ETL.6470.INSL.NCER | 2022-04-25 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair
LC | 123407153 | 008/113 | T3 EI GOLD HILL #1 008/113 RPR STRW | SACTO | ETL.6950.POLE.WOOD | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123407545 | 017/088 | T3 DI MNT VST CYT SS 17/88 RPR FOND | MOSSLNDG | ETL.5090.TOWR | 2022-04-25 | 2022-04-09 |  | 2022-10-06 | 2022-10-09 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123407665 | 022/009 | T3 DI FULTON-HOPLAND 22/9 RPR INSW | LAKEVLLE | ETL.6890.INSL.NCER | 2022-04-25 | 2022-04-09 |  | 2022-10-06 | 2022-10-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45571449 | T3 DI FULTON-HOPLAND 22/9 RPR INSW | ICW
LC | 123407840 | 004/096 | T3 EI DRM-GRS VLY-WMR 004/096 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605825 | T3 DI DRM GRS VLY WMR 0/14 RPL STRW | 70Y
LC | 123408122 | 007/012 | T3 EI MENDOCINO-WILLITS 007/012 RPR STRW | WILLITS | ETL.7540.POLE.WOOD | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123408716 | 006/162 | T3 EI DRM-GRS VLY-WMR 006/162 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31631448 | T3 EI DRM-GRS VLY-WMR 006/162 RPL STRW | 70Y
LC | 123408856 | 007/011 | T3 EI MENDOCINO-WILLITS 007/011 RPR STRW | WILLITS | ETL.7540.POLE.WOOD | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123408919 | 007/007 | T3 EI MDCO-WLTS-FRT BRG 007/007 RPR IBWW | WILLITS | ETL.7550.POLE.WOOD | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45640372 | T3 EI MDCO-WLTS-FRT BRG 007/007 RPR IBWW | ICW
LC | 123409730 | 023/011 | T3 EI MAPLE CREEK-HOOPA 23/11 RPR GYWW | EUREKA | ETL.7490.POLE.WOOD | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123410337 | 008/115 | T3 EI GOLD HILL #1 008/115 RPR GYWW | SACTO | ETL.6950.POLE.NWOD | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123411429 | 000/002 | T3 EI GEYSERS #13 TAP 00/02 RMV NEST | LAKEVLLE | ETL.4781.TOWR | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP PGEA OH FMOB TR3 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45575654 | T3 EI GEYSERS #13 TAP 00/02 RMV NEST | ICS
LC | 123411620 | 009/117 | T3 EI GOLD HILL #1 009/117 RPR STRW | SACTO | ETL.6950.POLE.WOOD | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123411662 | 022/001 | T3 EI MAPLE CREEK-HOOPA 022/001 RPR SPLW | EUREKA | ETL.7490.INSL.NCER | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 123411804 | 025/099 | T3 DI DIABLO-MIDWAY #3 25/99 RPR INSS | PISMOBCH | ETL.5980.INSL.NCER | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123412440 | 014/385 | T3 EI COLGATE-ALLEGHANY 14/385 RPR INSW | SACTO | ETL.6470.INSL.NCER | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123413019 | 023/095 | T3 DI DIABLO-MIDWAY #3 23/95 RPR GYWS | PISMOBCH | ETL.5980.TOWR | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123420434 | 025/099 | T3 DI DIABLO-MIDWAY #2 25/99 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123420590 | 002/039 | T3 DI CNTRVLL-TBL MTN 2/39 RPR POLE | TABLEMTN | ETL.6320.POLE.WOOD | 2022-04-25 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123420711 | 024/097 | T3 DI DIABLO-MIDWY #3 24/97 RPR INSS | PISMOBCH | ETL.5980.INSL.NCER | 2022-04-25 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123421632 | 000/003 | T3 DI DIABLO-MIDWAY #2 00/03 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2022-04-26 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123421875 | 026/103 | T3 EI PTSRG-SN MO-SN MO 026/103 RPL INSS | CONCORD | ETL.5463.INSL | 2022-04-26 | 2022-04-26 |  | 2022-10-23 | 2022-10-26 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31618666 | T2 DI PITTSBURG-SAN MATEO RPL INSS 4TWR | 93K
LC | 123422092 | 005/128 | T3 EI KILARC-CEDAR CREEK 5/128 RPR SWTC | TABLEMTN | ETL.7290.SWIT | 2022-04-26 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP NONR OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Switch-Wood | Repair | 45459146 | T3 EI KILARC-CEDAR CREEK 5/128 RPR SWTC | ICW
LC | 123422801 | 005/030 | T3 EI CASTRO VALLEY-NEWARK 5/30 RPR FOND | CONCORD | ETL.4450.TOWR | 2022-04-26 | 2022-04-26 |  | 2022-10-23 | 2022-10-26 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123423216 | 010/041 | T3 DI DIABLO-MIDWAY #2 10/41 RPR INSS | PISMOBCH | ETL.5970.INSL.NCER | 2022-04-26 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123423716 | 005/022 | T3 DI DIABLO-MIDWAY #3 5/22 RPR SHLS | PISMOBCH | ETL.5980.TOWR | 2022-04-26 | 2022-04-26 |  | 2022-10-23 | 2022-10-26 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair
LC | 123425261 | 022/005 | T3 EI MAPLE CREEK-HOOPA 22/5 RPR GYWW | EUREKA | ETL.7490.POLE.WOOD | 2022-04-26 | 2022-04-26 |  | 2022-10-23 | 2022-10-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123426830 | 000/006 | T3 EI GEYSERS #16 0/6 RMV NEST | LAKEVLLE | ETL.4781.TOWR | 2022-04-26 | 2022-04-26 |  | 2022-10-23 | 2022-10-26 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP PGEA OH FMOB TR3 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45575655 | T3 EI GEYSERS #16 0/6 RMV NEST | ICS
LC | 123427939 | 025/000 | T3 EI MAPLE CREEK-HOOPA 25/0 RPR SPLW | EUREKA | ETL.7490.INSL.NCER | 2022-04-26 | 2022-04-26 |  | 2022-10-23 | 2022-10-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 123429631 | 009/036 | T3 DI DIABLO-MIDWAY #2 9/36 RPR INSS | PISMOBCH | ETL.5970.INSL.NCER | 2022-04-26 | 2022-04-26 |  | 2022-10-23 | 2022-10-26 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123430406 | 006/059 | T3 EI ATASCADERO-CAYUCOS 6/59 RPL ANCW | PISMOBCH | ETL.8480.POLE.WOOD | 2022-04-26 | 2022-04-26 |  | 2022-10-23 | 2022-10-26 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31633499 | T3 EI ATASCADERO-CAYUCOS 6/59 RPL ANCW | 93E
LC | 123432012 | 015/135 | T3 EI MONTA VISTA-BURNS 15/135R RPL HRDW | MOSSLNDG | ETL.7590.POLE.STPS | 2022-04-26 | 2022-04-26 |  | 2022-10-23 | 2022-10-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45606049 | T3 EI MONTA VISTA-BURNS 15/135R RPL HRDW | ICW
LC | 123432768 | 026/114 | T3 DI DIABLO-MESA 26/114 RPR INSS | PISMOBCH | ETL.4620.INSL.NCER | 2022-04-26 | 2022-04-26 |  | 2022-10-23 | 2022-10-26 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123432928 | 008/034 | T3 DI MRR BY-SLR SS #1 8/34 RPR FOND | PISMOBCH | ETL.5300.TOWR | 2022-04-26 | 2022-04-26 |  | 2022-10-23 | 2022-10-26 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123433112 | 023/094 | T3 DI DIABLO-MIDWAY #3 23/94 REGRADE | PISMOBCH | ETL.5980.TOWR | 2022-04-26 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123433361 | 026/105 | T3 DI DIABLO-MIDWAY #2 26/105 RPR INSS | PISMOBCH | ETL.5970.INSL.NCER | 2022-04-26 | 2022-04-26 |  | 2022-10-23 | 2022-10-26 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123435659 | 013/008 | T3 EI MAPLE CREEK-HOOPA 13/8L RPR GYWW | EUREKA | ETL.7490.POLE.STPS | 2022-04-27 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123435699 | 013/008 | T3 EI MAPLE CREEK-HOOPA 13/8R RPR GYWW | EUREKA | ETL.7490.POLE.STPS | 2022-04-27 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123436948 | 009/063 | T3 EI OLEUM-G #1 009/063 UNBURY | CONCORD | ETL.3150.TOWR | 2022-04-27 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123437279 | 012/091 | T3 EI MORAGA-LAKWOD 012/091 RPL DROUND | CONCORD | ETL.3741.TOWR | 2022-04-27 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Ground Wire-Tower | Replace
LC | 123438806 | 009/265 | T3 EI COLGATE-ALLGHANY 009/265 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-04-27 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OTHR OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31633457 | T3 DI COLGATE-ALLEGHANY 008/222 RPL STRW | 70Y
LC | 123439133 | 021/091 | T3 DI MORR BAY-SL SS #1 021/091 RPR STRT | PISMOBCH | ETL.5300.TOWR | 2022-04-27 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123439135 | 010/041 | T3 DI MRRO BY-CLIF FLT ST 10/41 RPR INSS | PISMOBCH | ETL.5280.INSL | 2022-04-27 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123439686 | 014/003 | T3 EI LAURELES-OTTER 014/003 RPL POLE | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-04-27 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611560 | T3 EI LAURELES-OTTER 014/003 RPL POLE | 70Y
LC | 123439782 | 020/087 | T3 DI MRRO BY-SLR SS #1 020/087 RPR FOND | PISMOBCH | ETL.5300.TOWR | 2022-04-27 | 2022-04-26 |  | 2022-10-23 | 2022-10-26 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123440098 | 000/013 | T3 DI KESWICK-TRINITY 0/13 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2022-04-27 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606079 | T3 DI KESWICK-TRINITY 0/13 RPL POLE | 70Y
LC | 123440319 | 014/128 | T3 DI DRM RIO OSO #1 14/128 RPL SPLS | SACTO | ETL.1420.INSL.NCER | 2022-04-27 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Replace
LC | 123440341 | 014/128 | T3 DI DRM RIO OSO #1 14/128 RPR SPLS | SACTO | ETL.1430.INSL.NCER | 2022-04-27 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair
LC | 123440425 | 006/030 | T3 DI MORRO BAY-TEMPLETON 06/30 RPR OPGW | PISMOBCH | ETL.5933.TOWR | 2022-04-27 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair
LC | 123440553 | :009/051 | T3 DI EAGLE RCK-RDBD :009/051 RPR STRT | WILLITS | ETL.1480.TOWR | 2022-04-27 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123441144 | :008/050 | T3 DI EAGLE ROCK-REDBUD :8/50 RPL INSS | WILLITS | ETL.1480.INSL.NCER | 2022-04-28 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31601768 | T2 DI EAGLE RCK-RDBD RPL INSS 5TWR | 93K
LC | 123441342 | 009/040 | T3 DI MRR BAY-TMPLTN 9/40 RPR INSS | PISMOBCH | ETL.5933.INSL.CERA | 2022-04-28 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123441343 | 009/040 | T3 DI MRR BY-CALIF. FLTS 9/40 RPR INSS | PISMOBCH | ETL.5280.INSL.CERA | 2022-04-28 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123441926 | 008/048 | T3 EI CASTRO VALLEY-NEWARK 8/48 RPR FOND | CONCORD | ETL.4450.TOWR | 2022-04-28 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123442453 | 020/004 | T3 DI FULTON-HPLND 20/4 RPR GYWW | LAKEVLLE | ETL.6890.POLE.NWOD | 2022-04-28 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45571454 | T3 DI FULTON-HPLND 20/4 RPR GYWW | ICW
LC | 123442702 | 010/064 | T3 EI OLEUM-G #1 010/064 REGRADE | CONCORD | ETL.3150.TOWR | 2022-04-28 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123445890 | 015/063 | T3 EI MRO BY-SLR SW ST #2 15/63 RPL INSS | PISMOBCH | ETL.5310.INSL | 2022-04-28 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619689 | MORRO BAY-SOLAR SW STA #2-REP INS 8 LSTS | 93K
LC | 123445891 | 015/063 | T3 EI MORRO BAY-SOLAR #1 15/63 RPL INSS | PISMOBCH | ETL.5300.INSL | 2022-04-28 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617859 | T3 EI MRR BY-SLR SW ST #1 RPL INSS 7WTR | 93K
LC | 123447499 | 031/258 | T3 DI PIT #1-COTTONWOOD 31/258 UNBURY | TABLEMTN | ETL.5390.TOWR | 2022-04-28 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45639701 | T3 DI PIT #1-COTTONWOOD 31/258 UNBURY | ICQ
LC | 123447579 | 003/082 | T3 DI DRUM-SPLDNG 3/082 RPL PL | SACTO | ETL.6770.POLE.WOOD | 2022-04-28 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31629061 | T3 EI DRUM-SPAULDING 2/052 RPL PL | 70Y
LC | 123447882 | 024/100 | T3 DI GEYSERS #17-FLTN 24/100 RPL INSS | LAKEVLLE | ETL.4770.INSL.CERA | 2022-04-28 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31627766 | T3 DI GEYSERS #17-FULTON 13/55 RPL INSS | 93K
LC | 123449350 | 005/065B | T3 DI DRUM-SUMMIT #1 5/65B RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2022-04-28 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123449351 | 020/143 | T3 DI METCLF-GRN VLLY 20/143(L) RPL HRDW | MOSSLNDG | ETL.2540.POLE.WDPS | 2022-04-28 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45606054 | T3 DI METCLF-GRN VLLY 20/143(L) RPL HRDW | ICW
LC | 123450810 | 000/018 | T3 DI DRM SPLDNG 0/18 RPR INSW | SACTO | ETL.6770.INSL.CERA | 2022-04-28 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123450816 | 017/172 | T3 DI RND MTN CTNWD #2 17/172 RPL HRDT | TABLEMTN | ETL.5640.TOWR | 2022-04-28 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123450856 | 012/114 | T3 DI DRUM-HIGGINS 12/114L RPL HRDW | SACTO | ETL.4393.POLE.WDPS | 2022-04-28 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123451673 | 018/128 | T3 DI METCALF-GRN VLLY 18/128R RPL POLE | MOSSLNDG | ETL.2540.POLE.WDPS | 2022-04-28 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31611515 | T3 DI METCALF-GRN VLLY 18/128R RPL POLE | 70Y
LC | 123451686 | 018/128 | T3 DI METCALF-GRN VLLY 18/128L RPL POLE | MOSSLNDG | ETL.2540.POLE.WDPS | 2022-04-28 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31611515 | T3 DI METCALF-GRN VLLY 18/128R RPL POLE | 70Y
LC | 123451958 | 032/269 | T3 DI PIT #1-COTTONWOOD 032/269 REGRADE | TABLEMTN | ETL.5390.TOWR | 2022-04-28 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45639705 | T3 DI PIT #1-COTTONWOOD 032/269 REGRADE | ICQ
LC | 123451994 | 003/058 | T3 DI CNTRVL TBL MTN ORVL 3/58L INS HRDD | TABLEMTN | ETL.6330.POLE.STPS | 2022-04-28 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR NTDE | Missing | Hardware-Wood | Install
LC | 123451998 | 003/058 | T3 DI CNTRVL TBL MTN ORVL 3/58C INS HRDD | TABLEMTN | ETL.6330.POLE.STPS | 2022-04-28 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR NTDE | Missing | Hardware-Wood | Install
LC | 123452002 | 003/058 | T3 DI CNTRVL TBL MTN ORVL 3/58R INS HRDD | TABLEMTN | ETL.6330.POLE.STPS | 2022-04-28 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR NTDE | Missing | Hardware-Wood | Install
LC | 123452062 | :008/048 | T3 DI EAGLE ROCK-REDBUD :08/48 RPR INSS | WILLITS | ETL.1480.INSL.NCER | 2022-04-28 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45487766 | T3 DI EAGLE ROCK-REDBUD :08/48 RPR INSS | ICS
LC | 123452187 | 000/011 | T3 DI VLTA-DSCHTS 000/011 INS HRDD | TABLEMTN | ETL.8290.POLE.WOOD | 2022-04-28 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45458834 | T3 DI VLTA-DSCHTS 000/011 INS HRDD | ICW
LC | 123452222 | 000/002 | T3 DI VLTA-SOUTH 000/002 RPR INSW | TABLEMTN | ETL.8300.INSL | 2022-04-28 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45456454 | T3 DI VLTA-SOUTH 000/002 RPR INSW | ICW
LC | 123452229 | 019/133 | T3 DI METCALF-GREEN VLLY 19/133 BACKFILL | MOSSLNDG | ETL.2540.POLE.NWOD | 2022-04-28 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Repair | 45606057 | T3 DI METCALF-GREEN VLLY 19/133 BACKFILL | ICW
LC | 123453865 | 023/007 | T3 DI MAPLE CREEK-HOOPA 23/7 RPL INSW | EUREKA | ETL.7490.INSL | 2022-04-29 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31622209 | T3 DI MAPLE CREEK-HOOPA 23/7 RPL INSW | 93I
LC | 123454097 | 009/050 | T3 EI CASTRO VALLEY-NEWARK 9/50 RPR FOND | CONCORD | ETL.4450.TOWR | 2022-04-29 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123454230 | 020/139 | T3 DI MTCLF-GRN VLLY 20/139 RPR ANCW | MOSSLNDG | ETL.2540.POLE.WOOD | 2022-04-29 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Anchor-Wood | Repair | 45606080 | T3 DI MTCLF-GRN VLLY 20/139 RPR ANCW | ICW
LC | 123454587 | 009/051 | T3 EI CASTRO VALLEY-NEWARK 9/51 RPR FOND | CONCORD | ETL.4450.TOWR | 2022-04-29 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123455277 | 009/093 | T3NT DI DRUM-RIO OSO#2 9/93 BNT STEEL | SACTO | ETL.1430.TOWR | 2022-04-29 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3N PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45600070 | T3NT DI DRUM-RIO OSO#2 9/93 BNT STEEL | ICQ
LC | 123456337 | 002/032 | T3 DI IGNACIO-BLNS #1 2/32 RPL STRW | LAKEVLLE | ETL.7140.POLE.WOOD | 2022-04-29 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606078 | T3 DI IGNCIO BLNAS #1 1/29 RPL POLE | 70Y
LC | 123456944 | 000/003 | T3 DI WST PNT-VLLY SPRNGS 0/3 RPL POLE | VICTOR | ETL.8350.POLE.WOOD | 2022-04-29 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31618915 | T3 DI WST PNT VLY SPRNGS 0/1 RPL STRW | 70Y
LC | 123457403 | 001/015 | T3 DI WST PNT VLY SPRNGS 1/15 RPR CNDW | VICTOR | ETL.8350.INSL.NCER | 2022-04-29 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45531531 | T3 DI WST PNT VLY SPRNGS 1/15 RPR CNDW | ICW
LC | 123458290 | 020/161 | T3 EI MIDDLE FK-GOLD HILL 20/161 RPR WDP | SACTO | ETL.5140.POLE.WDPS | 2022-04-29 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123459414 | 005/047 | T3 EI MTA VST-BRNS 5/47R RPR GYWW | MOSSLNDG | ETL.7590.POLE.WDPS | 2022-04-29 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45606082 | T3 EI MTA VST-BRNS 5/47R RPR GYWW | ICW
LC | 123460109 | 013/108 | T3 EI MONTA VISTA-BURNS 13/108 RPR ROAD | MOSSLNDG | ETL.7590.POLE.NWOD | 2022-04-29 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 932 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Road | Repair | 45579940 | T3 EI MONTA VISTA-BURNS 13/108 RPR ROAD | CHS
LC | 123460466 | 001/032 | T3 DI DRUM-SPLDNG 1/32 RPR GYWW | SACTO | ETL.6770.POLE.NWOD | 2022-04-29 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123460796 | 004/006 | T3 EI LAURELES-OTTER 4/6 RPR INSW | MOSSLNDG | ETL.7380.INSL | 2022-04-29 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123462404 | :010/056 | T3 DI EAGLE ROCK-CORTINA :10/56 RPR INSS | WILLITS | ETL.1470.INSL.CERA | 2022-04-30 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45593455 | T3 DI EAGLE ROCK-CORTINA :10/56 RPR INSS | ICS
LC | 123462542 | 010/103 | T3 DI DRUM-RIO OSO #1 010/103 REFRAME | SACTO | ETL.1420.POLE.STPS | 2022-04-30 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Steel | Replace
LC | 123463170 | 002/043 | T3 DI CNTRVLL-TBL MTN 2/43 RPR INSW | TABLEMTN | ETL.6320.INSL | 2022-04-30 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123463172 | 000/013 | T3 DI KNCTI-EGLE RCK 0/13 RPR GYWW | WILLITS | ETL.6861.POLE.NWOD | 2022-04-30 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123463190 | 034/293 | T3 DI PIT #1-COTTONWOOD 034/293 RPR GYWS | TABLEMTN | ETL.5390.TOWR | 2022-04-30 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123463410 | 002/044 | T3 DI CNTRVL-TBL MTN-ORVLL 2/44 RPL INSW | TABLEMTN | ETL.6330.INSL.NCER | 2022-04-30 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31618453 | T3 DI CNTRVL-TBL MTN-ORVLL 2/44 RPL INSW | 93I
LC | 123463419 | 008/033 | T3 DI EGL RCK-FLTN-SLVRDO 8/33 BNT STEEL | LAKEVLLE | ETL.4392.TOWR | 2022-04-30 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123463510 | 018/136 | T3 DI TRINITY-COTTONWD 18/136L INS HRDW | TABLEMTN | ETL.4040.POLE.STPS | 2022-04-30 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123463542 | 008/159 | T3 DI KESWICK-CASCADE 8/159L RPL ANCW | TABLEMTN | ETL.7260.POLE.WDPS | 2022-04-30 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31616694 | T3 DI KESWICK-CASCADE 8/159L RPL ANCW | 93E
LC | 123463548 | 008/159 | T3 DI KESWICK-CASCADE 8/159R RPR GYWW | TABLEMTN | ETL.7260.POLE.WDPS | 2022-04-30 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45456671 | T3 DI KESWICK-CASCADE 8/159R RPR GYWW | ICW
LC | 123463625 | 005/002 | T3 DI LAURELES-OTTER 5/2 RMV BUTT | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-04-30 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123463900 | 005/002 | T3 DI LAURELES-OTTER 5/2 RPR ANCW | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-04-30 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123463936 | 003/039 | T3 EI DRUM-SUMMIT #1 3/39L RPR POLE | SACTO | ETL.1440.POLE.WDPS | 2022-04-30 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123464055 | 017/001 | T3 DI MNT RIO-FRT RSS 17/1L RPL HRDW | LAKEVLLE | ETL.6979.POLE.WDPS | 2022-04-30 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45575614 | T3 DI MNT RIO-FRT RSS 17/1L RPL HRDW | ICW
LC | 123464056 | 017/001 | T3 DI MNT RIO-FRT RSS 17/1C RPL HRDW | LAKEVLLE | ETL.6979.POLE.WDPS | 2022-04-30 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45575613 | T3 DI MNT RIO-FRT RSS 17/1C RPL HRDW | ICW
LC | 123464058 | 017/001 | T3 DI MNT RIO-FRT RSS 17/1R RPL HRDW | LAKEVLLE | ETL.6979.POLE.WDPS | 2022-04-30 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45575615 | T3 DI MNT RIO-FRT RSS 17/1R RPL HRDW | ICW
LC | 123464591 | 047/205 | T3 DI MTCLF-MSS LNDG #1 47/205 RPR FOND | MOSSLNDG | ETL.5100.TOWR | 2022-04-30 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123465372 | 007/085 | T3 DI GEYSERS #3-CLOVERDLE 7/85 RPR INSW | LAKEVLLE | ETL.1650.INSL.CERA | 2022-04-30 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45575549 | T3 DI GEYSERS #3-CLOVERDLE 7/85 RPR INSW | ICW
LC | 123465707 | :007/044 | T3 DI EAGLE ROCK-REDBUD :007/44 RPR INSS | WILLITS | ETL.1480.INSL.NCER | 2022-04-30 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45582049 | T3 DI EAGLE ROCK-REDBUD :007/44 RPR INSS | ICS
LC | 123466255 | 005/051 | T3 EI MONTA VISTA-BURNS 5/51 RPL HRDW | MOSSLNDG | ETL.7590.POLE.WOOD | 2022-04-30 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45606086 | T3 EI MONTA VISTA-BURNS 5/51 RPL HRDW | ICW
LC | 123466427 | 005/049 | T3 EI MTA VST-BRNS 5/49 RPR GYWW | MOSSLNDG | ETL.7590.POLE.WOOD | 2022-04-30 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45606088 | T3 EI MTA VST-BRNS 5/49 RPR GYWW | ICW
LC | 123466449 | 009/107 | T3 DI GYSRS #3 CLVRDL 9/107L RPR GYWW | LAKEVLLE | ETL.1650.POLE.STPS | 2022-04-30 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45575591 | T3 DI GYSRS #3 CLVRDL 9/107L RPR GYWW | ICW
LC | 123466834 | 009/254 | T3 DI COLGATE-ALLEGHANY 009/254 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-04-30 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31633457 | T3 DI COLGATE-ALLEGHANY 008/222 RPL STRW | 70Y
LC | 123466887 | 001/005 | T3 DI KNCTI-EGLE RCK 1/5 RPL STRW | WILLITS | ETL.6861.POLE.WOOD | 2022-04-30 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606237 | T3 DI KNCTI-EGLE RCK 1/5 RPL STRW | 70Y
LC | 123466889 | 046/204 | T3 DI MTCLF-MSS LNDG #1 46/204 RPR INSS | MOSSLNDG | ETL.5100.INSL | 2022-04-30 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45606090 | T3 DI MTCLF-MSS LNDG #1 46/204 RPR INSS | ICS
LC | 123467307 | 005/069 | T3 DI DSBL-CNTRVLL 5/69 RPL HRDW | TABLEMTN | ETL.6720.POLE.WOOD | 2022-04-30 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123467730 | 026/103 | T3 EI PITTSBRG-EASTSHORE 26/103 RPL INSS | CONCORD | ETL.5462.INSL | 2022-04-30 | 2022-04-26 |  | 2022-10-23 | 2022-10-26 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31625570 | DI PITTSBURG-EASTSHORE RPL INSS IN 9 TWR | 93K
LC | 123467736 | 020/195 | T3 DI RND MTN-CTONWD #2 20/195 RPR INSS | TABLEMTN | ETL.5640.INSL.NCER | 2022-04-30 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123467941 | 010/100 | T3 EI GREEN VLLY-PL SWT 10/100R RPR POLE | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-04-30 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45606091 | T3 EI GREEN VLLY-PL SWT 10/100R RPR POLE | ICW
LC | 123468052 | 009/014 | T3 DI LURLES-OTTER 9/014 RPR GYWW | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-04-30 | 2022-04-21 |  | 2022-10-18 | 2022-07-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45277903 | T3 DI LURLES-OTTER 9/014 RPR GYWW | ICW
LC | 123468057 | 027/223 | T3 DI PIT #1-COTTONWOOD 27/223 UNBURY | TABLEMTN | ETL.5390.TOWR | 2022-04-30 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45639676 | T3 DI PIT #1-COTTONWOOD 27/223 UNBURY | ICQ
LC | 123468062 | 011/044 | T3 DI MORRO BAY-TMPLTN 11/44 RPR FOND | PISMOBCH | ETL.5933.TOWR | 2022-04-30 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123468248 | 000/004 | T3 DI MISSION POWER TAP 000/004 RPR INSW | LAKEVLLE | ETL.1651.INSL.NCER | 2022-04-30 | 2022-04-13 |  | 2022-10-10 | 2022-10-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45575605 | T3 DI MISSION POWER TAP 000/004 RPR INSW | ICW
LC | 123468933 | 008/099 | T3 DI GEYSERS #3-CLOVERDLE 8/99 RPR JMPW | LAKEVLLE | ETL.1650.INSL.NCER | 2022-04-30 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Jumper-Wood | Repair | 45575550 | T3 DI GEYSERS #3-CLOVERDLE 8/99 RPR JMPW | ICW
LC | 123468939 | 002/035 | T3 DI CENTERVILLE-TBL MTN 2/35 RPR STRW | TABLEMTN | ETL.6320.POLE.NWOD | 2022-04-30 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123468992 | 002/046 | T3 DI CNTRVL-TBL MTN-ORVL 2/46 RPR POLE | TABLEMTN | ETL.6330.POLE.NWOD | 2022-04-30 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123472682 | 006/001 | T3 DI LAURALES-OTTER 6/001 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-02 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31629347 | T3 DI LAURALES-OTTER 6/001 RPL STRW | 70Y
LC | 123472739 | 008/159 | T3 DI KESWICK-CASCADE 8/159C RPR GYWW | TABLEMTN | ETL.7260.POLE.WDPS | 2022-05-02 | 2022-04-11 |  | 2022-10-08 | 2022-10-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45456670 | T3 DI KESWICK-CASCADE 8/159C RPR GYWW | ICW
LC | 123473042 | 016/069 | T3 DI GEYSERS #9-LAKEVILL 16/69 RPR INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2022-05-02 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575557 | T3 DI GEYSERS #9-LAKEVILL 16/69 RPR INSS | ICS
LC | 123473043 | 016/069 | T3 DI EGL RK-FLTN SLVRD 16/69 RPR INSS | LAKEVLLE | ETL.4392.INSL.CERA | 2022-05-02 | 2022-04-12 |  | 2022-10-09 | 2022-10-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123473190 | 000/005 | T3 DI CNTRVL-TBL MTN-ORVL 0/5 RMV VEG | TABLEMTN | ETL.6330.POLE.WOOD | 2022-05-02 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123473201 | 012/100 | T3 EI TRINITY-COTTONWOD 12/100L RPL POLE | TABLEMTN | ETL.4040.POLE.WDPS | 2022-05-02 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31618699 | T2 DI TRINITY-COTTONWOOD 9/72A RPL POLE | 70Y
LC | 123473202 | 012/100 | T3 EI TRINITY-COTTONWOD 12/100R RPL POLE | TABLEMTN | ETL.4040.POLE.WDPS | 2022-05-02 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31618699 | T2 DI TRINITY-COTTONWOOD 9/72A RPL POLE | 70Y
LC | 123473650 | 000/006 | T3 DI GEYSERS #3-CLVRDL 0/6 RPR STRW | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-05-02 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45575551 | T3 DI GEYSERS #3-CLVRDL 0/6 RPR STRW | ICW
LC | 123473981 | 017/126 | T3 DI GRN VLY CAMP EVRS 17/126 COTTER | MOSSLNDG | ETL.1710.INSL.NCER | 2022-05-02 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45606096 | T3 DI GRN VLY CAMP EVRS 17/126 COTTER | ICS
LC | 123474182 | 010/099 | T3 DI GRN VLY PL SWT 10/99 RPR INSW | MOSSLNDG | ETL.1730.INSL.CERA | 2022-05-02 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair | 45606097 | T3 DI GRN VLY PL SWT 10/99 RPR INSW | ICW
LC | 123474570 | 012/050 | T3 DI EGL RK-FLTN SLVRD 12/50 COTTER | LAKEVLLE | ETL.4392.INSL.CERA | 2022-05-02 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575436 | T3 DI EGL RK-FLTN SLVRD 12/50 COTTER | ICS
LC | 123474853 | 004/101 | T3 DI KLRC-CEDAR CREEK 4/101 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-05-02 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606231 | T3 EI KILARC-CEDAR CREEK 3/076 RPL POLE | 70Y
LC | 123476379 | 006/054 | T3 EI MONTA VISTA-BURNS 6/54 RPR GYWW | MOSSLNDG | ETL.7590.POLE.WOOD | 2022-05-02 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45606099 | T3 EI MONTA VISTA-BURNS 6/54 RPR GYWW | ICW
LC | 123477308 | 000/004 | T3 DI DESABALA-CENTERVLLE 0/4 RPR INSW | TABLEMTN | ETL.6720.INSL | 2022-05-02 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123478658 | 011/113 | T3 EI GRN VLLY-CMP EVER 11/113 RPL POLE | MOSSLNDG | ETL.1710.POLE.WOOD | 2022-05-02 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31628900 | T3 DI GRN VLLY-CMP EVRS 11/108L RPL POLE | 70Y
LC | 123478686 | 009/092 | T3 DI GREEN VALLEY-PAUL SW 9/92 RPL INSS | MOSSLNDG | ETL.1730.INSL.NCER | 2022-05-02 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31629563 | T3 DI GREEN VALLEY-PAUL SW 9/92 RPL INSS | 93I
LC | 123480037 | 000/012 | T3 EI FRNCH MDWS-MDDLE FRK 0/12 RPR INSW | SACTO | ETL.6870.INSL | 2022-05-02 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123480038 | 000/002 | T3 EI FRNCH MDWS-MDDLE FRK 0/2 RPL POLE | SACTO | ETL.6870.POLE.WOOD | 2022-05-02 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606072 | T3 EI FRNCH MDWS-MDDLE FRK 0/2 RPL POLE | 70Y
LC | 123480039 | 000/011 | T3 EI FRNCH MDWS-MDDLE FRK 0/11 RPL HRDW | SACTO | ETL.6870.POLE.WOOD | 2022-05-02 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123480124 | 000/010 | T3 EI FRNCH MDWS-MDDLE FRK 0/10 RPL HRDW | SACTO | ETL.6870.POLE.WOOD | 2022-05-02 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123480236 | 000/001 | T3 DI MISSION POWER TAP 0/1 RPR WDPKR | LAKEVLLE | ETL.1651.POLE.WOOD | 2022-05-02 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45575603 | T3 DI MISSION POWER TAP 0/1 RPR WDPKR | ICW
LC | 123480306 | 030/255 | T3 DI ROUND MTN-CTTNWD #3 30/255 BNT STL | TABLEMTN | ETL.5650.TOWR | 2022-05-02 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123480475 | 009/100 | T3 EI GRN VLLY-CMP EVERS 9/100L RPL POLE | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-05-02 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31628899 | T3 EI GRN VLLY-CMP EVERS 9/100L RPL POLE | 70Y
LC | 123480492 | 009/100 | T3 EI GRN VLLY-CMP EVERS 9/100R RPL POLE | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-05-02 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31628899 | T3 EI GRN VLLY-CMP EVERS 9/100L RPL POLE | 70Y
LC | 123480500 | 009/100 | T3 EI GRN VLLY-CMP EVERS 9/100C RPL POLE | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-05-02 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31628899 | T3 EI GRN VLLY-CMP EVERS 9/100L RPL POLE | 70Y
LC | 123481947 | :001/006 | T3 DI EAGLE ROCK-CORTINA :1/6 RPL INSS | WILLITS | ETL.1470.INSL.NCER | 2022-05-02 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615829 | T3 DI EAGLE ROCK-CORTINA RPL INSS 3TWR | 93K
LC | 123481957 | 006/039 | T3 DI SRNT-GRZLY-CLMNT#2 6/39 RPR STRT | CONCORD | ETL.3750.TOWR | 2022-05-02 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45350151 | T3 DI SRNT-GRZLY-CLMNT#2 6/39 RPR STRT | ICQ
LC | 123481975 | 009/148 | T3 DI WEIMAR #1 9/148 RPR INSW | SACTO | ETL.7560.INSL.NCER | 2022-05-02 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123482025 | 006/038 | T3 DI SBRANTE-GRIZLY-CLR#2 6/38 RPL HRDT | CONCORD | ETL.3750.TOWR | 2022-05-02 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123482117 | 018/125 | T3 DI METCLF-GRN VLY 18/125R RPL POLE | MOSSLNDG | ETL.2540.POLE.WDPS | 2022-05-02 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611515 | T3 DI METCALF-GRN VLLY 18/128R RPL POLE | 70Y
LC | 123482118 | 018/125 | T3 DI METCLF-GRN VLY 18/125L RPL POLE | MOSSLNDG | ETL.2540.POLE.WDPS | 2022-05-02 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31611515 | T3 DI METCALF-GRN VLLY 18/128R RPL POLE | 70Y
LC | 123482928 | 000/001 | T3 DI DRUM-SUMMIT#1 0/1L RPR SWTC | SACTO | ETL.1440.POLE.STPS | 2022-05-03 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Switch-Wood | Repair
LC | 123482970 | 000/001 | T3 DI DRUM-SUMMIT#1 0/1L RPR GYWW | SACTO | ETL.1440.POLE.STPS | 2022-05-03 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123482975 | 000/001 | T3 DI DRUM-SUMMIT#1 0/1L RPR INSW | SACTO | ETL.1440.POLE.STPS | 2022-05-03 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123483164 | 013/123 | T3 DI DRUM-HIGGINS 13/123 BENT STEEL | SACTO | ETL.4393.TOWR | 2022-05-03 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45599183 | T3 DI DRUM-HIGGINS 13/123 BENT STEEL | ICQ
LC | 123483611 | 012/172 | T3 DI WMR #1 12/172L GYWW COTR | SACTO | ETL.7560.POLE.WDPS | 2022-05-03 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123484326 | 031/262 | T3 DI RND MTN-CTTNWD #3 31/262 BNT STEEL | TABLEMTN | ETL.5650.TOWR | 2022-05-03 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123484521 | 031/262 | T3 DI RND MTN-CTTNWD #3 31/262 RPR INSS | TABLEMTN | ETL.5650.INSL | 2022-05-03 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123485207 | 010/085 | T3 EI MONTA VISTA-BURNS 10/085 RPL HRDD | MOSSLNDG | ETL.7590.INSL.NCER | 2022-05-03 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45606129 | T3 EI MONTA VISTA-BURNS 10/085 RPL HRDD | ICW
LC | 123485701 | -012/004 | T3 DI FLTN-CLSTOGA -12/004 RPL HRDD | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-03 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45485895 | T3 DI FLTN-CLSTOGA -12/004 RPL HRDD | ICW
LC | 123486103 | 011/000 | T3 EI LAURELES-OTTER 11/0 RPR ANCW | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-05-03 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123488062 | 017/079 | T3 DI MSS LNDG-MTCLF 17/079 RPR GYWS | MOSSLNDG | ETL.6050.TOWR | 2022-05-03 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123488747 | 007/005 | T3 DI LAURELES-OTTER 007/005 RPL HRDD | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-03 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123490239 | 014/112 | T3 EI TRINITY-COTTONWOOD 14/112 RPR CNDW | TABLEMTN | ETL.4040.INSL.CERA | 2022-05-03 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair
LC | 123490667 | 001/000 | T3 DI KNCTI EGLE RCK 1/0C GYWW COTTER | WILLITS | ETL.6861.POLE.STPS | 2022-05-03 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45449388 | T3 DI KNCTI EGLE RCK 1/0C GYWW COTTER | ICW
LC | 123490824 | 003/023 | T3 DI SOBRANTE-R #1 003/023 UNBURY | CONCORD | ETL.3770.TOWR | 2022-05-03 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123490881 | 003/023 | T3 DI SOBRANTE-R #2 003/023 RPR INSS | CONCORD | ETL.3780.INSL | 2022-05-03 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45513137 | T3 DI SOBRANTE-R #2 003/023 RPR INSS | ICS
LC | 123490888 | 031/263 | T3 DI RND MTN-CTTNWD#3 31/263 INS COTTER | TABLEMTN | ETL.5650.INSL | 2022-05-03 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123490913 | 000/019 | T3 DI CNTRVL-TBL MTN-ORVL 0/19 RPR POLE | TABLEMTN | ETL.6330.POLE.NWOD | 2022-05-03 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123490939 | 008/230 | T3 DI COLGATE-ALLEGHANY 8/230 RPL HRDD | SACTO | ETL.6470.POLE.WOOD | 2022-05-03 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123491063 | 000/015 | T3 DI DEER CREEK-DRUM 0/15 RPL STW | SACTO | ETL.6690.POLE.WOOD | 2022-05-03 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605821 | T3 DI DEER CREEK-DRUM 0/15 RPL STW | 70Y
LC | 123491150 | 012/113 | T3 DI DRUM-RIO OSO#1 12/113 BENT STEEL | SACTO | ETL.1420.TOWR | 2022-05-03 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45599996 | T3 DI DRUM-RIO OSO#1 12/113 BENT STEEL | ICQ
LC | 123491264 | 030/250 | T3 DI RND MTN-CTTNWD #3 30/250 BNT STEEL | TABLEMTN | ETL.5650.TOWR | 2022-05-03 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123491286 | 030/246 | T3 DI PIT #1-CTTNWD 30/246 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2022-05-03 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45639700 | T3 DI PIT #1-CTTNWD 30/246 RPR FOND | ICQ
LC | 123491287 | 030/246 | T3 DI PIT #1-CTTNWD 30/246 RMV VEG | TABLEMTN | ETL.5390.TOWR | 2022-05-03 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123491409 | 010/243 | T3 DI DRM-GRSS VLLY-WMR 10/243 RPL TIES | SACTO | ETL.6760.INSL.CERA | 2022-05-03 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45296454 | T3 DI DRM-GRSS VLLY-WMR 10/243 RPL TIES | ICW
LC | 123491449 | 010/104 | T3 DI DRUM-RIO OSO #2 10/104 INS HRDT | SACTO | ETL.1430.TOWR | 2022-05-03 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45600072 | T3 DI DRUM-RIO OSO #2 10/104 INS HRDT | ICQ
LC | 123491505 | 014/388 | T3 DI COLGATE-ALLEGHANY 14/388 RPR GYWW | SACTO | ETL.6470.POLE.WOOD | 2022-05-03 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123491509 | 014/388 | T3 DI COLGATE-ALLEGHANY 14/388 REFRAME | SACTO | ETL.6470.POLE.WOOD | 2022-05-03 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31633459 | T3 DI COLGATE-ALLEGHANY 013/369 REFRAME | 93E
LC | 123491594 | 023/630 | T3 DI COLGATE-ALLEGHANY 23/630 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-05-03 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605566 | HANY 15/402 RPL POLE | 70Y
LC | 123492506 | 005/072 | T3 DI KESWICK-TRINITY 5/72 RPR INSW | TABLEMTN | ETL.7270.INSL.NCER | 2022-05-04 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123493044 | 011/311 | T3 DI COLGATE-ALLGHNY 11/311 RMV BUTT | SACTO | ETL.6470.POLE.WOOD | 2022-05-04 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123493428 | 000/008 | T3 DI DRUM-SUMMIT #1 0/8R RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2022-05-04 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123494189 | 012/117 | T3 EI GRN VLLY-CMP EVRS 12/117R RPL POLE | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-05-04 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | Rotten | Structure-Wood | Replace | 31628900 | T3 DI GRN VLLY-CMP EVRS 11/108L RPL POLE | 70Y
LC | 123494344 | 012/117 | T3 EI GRN VLLY-CMP EVRS 12/117L RPL POLE | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-05-04 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | Rotten | Structure-Wood | Replace | 31628900 | T3 DI GRN VLLY-CMP EVRS 11/108L RPL POLE | 70Y
LC | 123494482 | 012/113 | T3 DI DRUM-HIGGINS 12/113L RPR STRW | SACTO | ETL.4393.POLE.WDPS | 2022-05-04 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123495245 | 002/044 | T3 DI CNTRVLLE-TBL MTN 2/44 RPR STRW | TABLEMTN | ETL.6320.POLE.WOOD | 2022-05-04 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123496053 | 000/011 | T3 EI MORAGA-SN LEANDRO #2 1/11 RPL INSS | CONCORD | ETL.2780.INSL | 2022-05-04 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31604431 | T3 EI MORAGA-SN LEANDRO #2 RPL INSS 2TW | 93K
LC | 123496054 | 001/011 | T3 EI MORAGA-SN LEANDRO #1 1/11 RPL INSS | CONCORD | ETL.2770.INSL | 2022-05-04 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617656 | T3 DI MORAGA-SAN LEANDRO #1 RPL INSS 6T | 93K
LC | 123496490 | 001/012 | T3 EI MORAGA-SN LEANDRO #1 1/12 RPR FOND | CONCORD | ETL.2770.TOWR | 2022-05-04 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123496591 | 008/236 | T3 DI COLGATE-ALLGHNY 8/236 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2022-05-04 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123498072 | 000/018 | T3 DI CNTRVL-TBL MTN-ORVL 0/18 RPR SPLW | TABLEMTN | ETL.6330.INSL.NCER | 2022-05-04 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 123498225 | 002/016 | T3 EI MRGA-SN LEANDRO #1 2/16 RPL INSS | CONCORD | ETL.2770.INSL.CERA | 2022-05-04 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617656 | T3 DI MORAGA-SAN LEANDRO #1 RPL INSS 6T | 93K
LC | 123498554 | 000/004 | T3 EI GEYSERS #11-EAGLE ROCK 0/4 REGRADE | LAKEVLLE | ETL.4391.POLE.NWOD | 2022-05-04 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123499147 | 011/111 | T3 DI GRN VLYY CMP EVRS 11/111 RPR INSW | MOSSLNDG | ETL.1710.INSL.CERA | 2022-05-04 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45606131 | T3 DI GRN VLYY CMP EVRS 11/111 RPR INSW | ICW
LC | 123499149 | 011/111 | T3 DI GRN VLYY CMP EVRS 11/111L RMV BUTT | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-05-04 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCH OH TR3 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45606132 | T3 DI GRN VLYY CMP EVRS 11/111L RMV BUTT | ICW
LC | 123499515 | 013/352 | T3 DI COLGATE-ALLEGHANY 13/352 RPL HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-05-04 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123500136 | 014/380 | T3 DI CLGT ALGHNY 14/380 RPL SPLW | SACTO | ETL.6470.INSL.NCER | 2022-05-04 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Replace
LC | 123500233 | 006/118 | T3 DI CLGT CHLNG 6/118 RPL STRW | SACTO | ETL.6480.POLE.WOOD | 2022-05-04 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617797 | T3 EI COLGATE-CHALLENGE 2/056 RPL STW | 70Y
LC | 123500293 | 007/087 | T3 EI GRN VLLY-CAMP EVERS 7/87L RPL POLE | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-05-04 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31618524 | T3 EI GRN VLLY-CMP EVRS 12/117L RPL POLE | 70Y
LC | 123500409 | 007/088 | T3 EI GRN VLLY-CAMP EVERS 7/88L RPL POLE | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-05-04 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31618524 | T3 EI GRN VLLY-CMP EVRS 12/117L RPL POLE | 70Y
LC | 123500491 | 007/088 | T3 EI GRN VLLY-CAMP EVERS 7/88R RPL POLE | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-05-04 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31618524 | T3 EI GRN VLLY-CMP EVRS 12/117L RPL POLE | 70Y
LC | 123500546 | 017/463 | T3 DI COLGATE-ALLEGNY 17/463 RPR SPLW | SACTO | ETL.6470.SWIT | 2022-05-04 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 123500641 | 007/088 | T3 EI GRN VLLY-CAMP EVERS 7/88C RPL POLE | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-05-04 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31618524 | T3 EI GRN VLLY-CMP EVRS 12/117L RPL POLE | 70Y
LC | 123500798 | 005/078 | T3 DI DSBLA-CNTRVLLE 5/78 RPR INSW | TABLEMTN | ETL.6720.INSL | 2022-05-04 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123500867 | 012/271 | T3 DI KLRC CDR CRK 12/271 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-05-04 | 2022-04-15 |  | 2022-10-12 | 2022-10-15 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617628 | T3 DI KILARC-CEDAR CRK 4/96 RPL STRW | 70Y
LC | 123500939 | 003/005B | T3 DI LAURELES-OTTER 3/5B RPL HRDD | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-04 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123500951 | 020/000 | T3 DI MONTE RIO-FORT ROSS 20/0L RPR GYWW | LAKEVLLE | ETL.6979.POLE.STPS | 2022-05-04 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45575643 | T3 DI MONTE RIO-FORT ROSS 20/0L RPR GYWW | ICW
LC | 123500972 | 014/398 | T3 DI COLGATE-ALLEGHANY 14/398 RPL DAMW | SACTO | ETL.6470.INSL.CERA | 2022-05-04 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace
LC | 123501024 | 009/146 | T3 DI WEIMAR #1 009/146 GYWW COTTER | SACTO | ETL.7560.POLE.WOOD | 2022-05-04 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123501055 | 017/479 | T3 DI COLGATE-ALLEGHANY 17/479 RPL HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-05-04 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123501085 | 000/011 | T3 DI CENTERVLLE-TBL MTN 0/11 INS HRDD | TABLEMTN | ETL.6320.POLE.NWOD | 2022-05-04 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123501101 | 028/229 | T3 DI RND MT-COTNWD #3 28/229L RPR STRW | TABLEMTN | ETL.5650.POLE.STPS | 2022-05-04 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123501103 | 028/229 | T3 DI RND MT-COTNWD #3 28/229C RPR STRW | TABLEMTN | ETL.5650.POLE.STPS | 2022-05-04 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123501107 | 028/229 | T3 DI RND MT-COTNWD #3 28/229R RPR STRW | TABLEMTN | ETL.5650.POLE.STPS | 2022-05-04 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123513950 | 003/022 | T3 EI MORAGA-SAN LEANDRO #1 3/22 REGRADE | CONCORD | ETL.2770.TOWR | 2022-05-05 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123515741 | 007/007 | T3 EI LAURELES-OTTER 007/007 RPL ANCW | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-05-05 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31620680 | T3 EI LAURELES-OTTER 007/007 RPL ANCW | 93E
LC | 123515771 | 001/019 | T3 DI CNTRVL-TBL MTN 001/019 RPL STRW | TABLEMTN | ETL.6320.POLE.WOOD | 2022-05-05 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605299 | T3 DI CNTRVL-TBL MTN 001/019 RPL STRW | 70Y
LC | 123516051 | 007/007 | T3 EI LAURELES-OTTER 007/007R RPL ANCW | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-05-05 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Anchor-Wood | Replace | 31620680 | T3 EI LAURELES-OTTER 007/007 RPL ANCW | 93E
LC | 123517298 | 003/026 | T3 EI MORAGA-SAN LEANDRO #1 3/26 UNBURY | CONCORD | ETL.2770.TOWR | 2022-05-05 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123517325 | 003/026 | T3 EI MORAGA-SAN LENDRO #2 3/26 RPL INSS | CONCORD | ETL.2780.INSL | 2022-05-05 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31604431 | T3 EI MORAGA-SN LEANDRO #2 RPL INSS 2TW | 93K
LC | 123517326 | 003/029 | T3 EI MORGA-SAN LANDRO #1 3/29 BNT STEEL | CONCORD | ETL.2770.TOWR | 2022-05-05 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123517391 | 003/063 | T3 DI CENTER-TABLE MTN 3/63 RPL PL | TABLEMTN | ETL.6330.POLE.WOOD | 2022-05-05 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31634715 | T3 DI CENTER-TABLE MTN 3/63 RPL PL | 70Y
LC | 123517891 | 001/026 | T3 DI IGNACIO-BLNAS #1 1/26 RPR INSW | LAKEVLLE | ETL.7140.INSL.NCER | 2022-05-05 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45486012 | T3 DI IGNACIO-BLNAS #1 1/26 RPR INSW | ICW
LC | 123519865 | :000/005 | T3 DI EAGLE ROCK-REDBUD 000/005 RPR FOND | WILLITS | ETL.1480.TOWR | 2022-05-05 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45616211 | T3 DI EAGLE ROCK-REDBUD 000/005 RPR FOND | ICQ
LC | 123519916 | 013/001A | T3 DI UKH-HPLND-CLVDLE 013/001A RPL INSW | WILLITS | ETL.4050.INSL.NCER | 2022-05-05 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31616733 | T3 DI UKH-HPLND-CLVDLE 013/001A RPL INSW | 93I
LC | 123520100 | 000/007 | T3 DI DSBLA CNTRVLLE 0/7 RPR SPLW | TABLEMTN | ETL.6720.INSL | 2022-05-05 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 123520106 | 007/083 | T3 DI GYSRS #3 CLVRDL 007/083 RPL HRDD | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-05-05 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45575590 | T3 DI GYSRS #3 CLVRDL 007/083 RPL HRDD | ICW
LC | 123520436 | 007/170 | T3 DI DRM-GRSS VLLY-WMR 7/170 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-05-05 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605825 | T3 DI DRM GRS VLY WMR 0/14 RPL STRW | 70Y
LC | 123522428 | :011/005 | T3 DI FULTON-CALISTOGA :11/5 RPR GYWW | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-06 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45571441 | T3 DI FULTON-CALISTOGA :11/5 RPR GYWW | ICW
LC | 123522545 | 014/062 | T3 DI EGLE RK-FLN-SLVDO 014/062 RMV NEST | LAKEVLLE | ETL.4392.INSL.CERA | 2022-05-06 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Steel | Remove
LC | 123522659 | 007/136 | T3 DI CLGT-CHLLNG 7/136 RPL STRW | SACTO | ETL.6480.POLE.WOOD | 2022-05-06 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605567 | T3 DI CLGT-CHLLNG 7/136 RPL STRW | 70Y
LC | 123522952 | 004/121 | T3 DI DR CRK-DRM 004/121 RPL HRDW | SACTO | ETL.6690.POLE.WOOD | 2022-05-06 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123522954 | 005/141 | T3 DI DR CRK-DRM 5/141 REGRADE | SACTO | ETL.6690.POLE.NWOD | 2022-05-06 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123523299 | 006/023 | T3 DI EGL RCK FTN SLVRD 006/023 RPR INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2022-05-06 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123523511 | 006/023 | T3 DI EGL RCK FLTN SLVRD 6/23 RPR INSS | LAKEVLLE | ETL.4392.INSL.NCER | 2022-05-06 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575435 | T3 DI EGL RCK FLTN SLVRD 6/23 RPR INSS | ICS
LC | 123523633 | 011/293 | T3 DI COLGATE-ALLGHNY 011/293 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-05-06 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31633458 | T3 DI COLGATE-ALLGHNY 011/293 RPL STRW | 70Y
LC | 123523725 | 003/036 | T3 DI DESABLA-CENTERVILLE 3/36 RPL STRW | TABLEMTN | ETL.6720.POLE.WOOD | 2022-05-06 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31612428 | T3 DI DESABLA-CENTERVILLE 3/36 RPL STRW | 70Y
LC | 123523741 | 003/053 | T3 DI KESWICK-TRINITY 3/053 RPR POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2022-05-06 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123525171 | 005/074 | T3 DI DSBLA-CNTRVLL 5/074 INST HRDD | TABLEMTN | ETL.6720.POLE.WOOD | 2022-05-06 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123525444 | 018/492 | T3 DI COLGATE-ALLGHNY 18/492 RPL HRDW | SACTO | ETL.6470.POLE.NWOD | 2022-05-06 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123526062 | 003/044 | T3 DI IGNACIO-BOLINAS #2 3/44 RPL POLE | LAKEVLLE | ETL.7180.POLE.WOOD | 2022-05-06 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31620250 | T3 DI IGNACIO-BOLINAS #2 3/44 RPL POLE | 70Y
LC | 123526258 | 003/026 | T3 DI SOBRANTE-R#1 3/26 RPR INSS | CONCORD | ETL.3770.INSL.NCER | 2022-05-06 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45513138 | T3 DI SOBRANTE-R#1 3/26 RPR INSS | ICS
LC | 123527012 | 010/286 | T3 DI COLGATE-ALLGHNY 10/286 REFRAME | SACTO | ETL.6470.POLE.WOOD | 2022-05-06 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31618163 | T2 DI COLGATE-ALLEGHANY 3/81 REFRAME | 93E
LC | 123527072 | 028/126 | T3 DI GEYSERS #9-LKVLLE 28/126 RPR INSS | LAKEVLLE | ETL.4780.INSL | 2022-05-06 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575585 | T3 DI GEYSERS #9-LKVLLE 28/126 RPR INSS | ICS
LC | 123527154 | 010/009 | T3 DI UKIAH-HPLND CLVRDL 10/9 RPL POLE | WILLITS | ETL.4050.POLE.WOOD | 2022-05-06 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31619397 | T2 EI UKIAH-HPLND-CLVRDALE 9/80 RPL PL | 70Y
LC | 123527219 | 006/161 | T3 DI COLGATE-GRAS VALLEY 6/161 RPL STRW | SACTO | ETL.6490.POLE.WOOD | 2022-05-06 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605822 | T3 DI COLGATE-GRAS VALLEY 6/161 RPL STRW | 70Y
LC | 123527319 | 009/142 | T3 DI WEIMAR #1 009/142 RPL HRDW | SACTO | ETL.7560.POLE.WOOD | 2022-05-06 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123527435 | 020/090 | T3 DI MSS LANDING-METCALF 20/90 INS HRDT | MOSSLNDG | ETL.6050.TOWR | 2022-05-06 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install
LC | 123529040 | 001/005 | T3 DI DIABLO-MIDWAY #3 1/5 RPL DMPS | PISMOBCH | ETL.5980.INSL.NCER | 2022-05-06 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Damper-Steel | Replace | 45290556 | T3 DI DIABLO-MIDWAY #3 1/5 RPL DMPS | ICS
LC | 123529045 | 001/014 | T3 DI DRUMS-HIGGINS 1/14 RPL STRW | SACTO | ETL.4393.POLE.WDPS | 2022-05-06 | 2022-03-31 |  | 2022-09-27 | 2022-09-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31617831 | T3 DI DRUM-HIGGINS 009/088L RPL POLE | 70Y
LC | 123529600 | 002/037 | T3 DI CENTERVLLE-TBL MTN 2/37 RPR POLE | TABLEMTN | ETL.6320.POLE.WOOD | 2022-05-06 | 2022-04-18 |  | 2022-10-15 | 2022-10-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123530164 | 023/093 | T3 DI DIABLO-MDWY #3 23/93 RPR GYWS | PISMOBCH | ETL.5980.TOWR | 2022-05-06 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123530180 | 004/035 | T3 EI GREEN VALLEY-LLAGAS 4/035 RPL HRDW | MOSSLNDG | ETL.1720.INSL.NCER | 2022-05-06 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31612321 | T3 EI GREEN VALLEY-LLAGAS 4/035 RPL HRDW | 93I
LC | 123530741 | 005/037 | T3 EI GREEN VALLEY-LLAGAS 5/37L RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-05-06 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31610972 | T3 EI GREEN VALLEY-LLAGAS 5/37R RPL POLE | 70Y
LC | 123530754 | 005/037 | T3 EI GREEN VALLEY-LLAGAS 5/37R RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-05-06 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31610972 | T3 EI GREEN VALLEY-LLAGAS 5/37R RPL POLE | 70Y
LC | 123530950 | 000/003 | T3 DI DIABLO-MDWY #3 0/3 RPR ANCS | PISMOBCH | ETL.5980.TOWR | 2022-05-06 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair
LC | 123530951 | 000/003 | T3 DI DIABLO-MDWY #3 0/3 RPR FOND | PISMOBCH | ETL.5980.TOWR | 2022-05-06 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123530959 | 013/369 | T3 DI COLGATE-ALLEGHANY 013/369 REFRAME | SACTO | ETL.6470.POLE.WOOD | 2022-05-06 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31633459 | T3 DI COLGATE-ALLEGHANY 013/369 REFRAME | 93E
LC | 123531291 | 012/114 | T3 DI GRN VLLY-PAUL SWT 12/114 RPR POLE | MOSSLNDG | ETL.1730.POLE.WOOD | 2022-05-06 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45606200 | T3 DI GRN VLLY-PAUL SWT 12/114 RPR POLE | ICW
LC | 123531292 | 012/114 | T3 DI GRN VLLY-PAUL SWT 12/114 REFRAME | MOSSLNDG | ETL.1730.POLE.WOOD | 2022-05-06 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31618251 | T3 DI GRN VLLY-PAUL SWT 12/114 REFRAME | 93E
LC | 123532349 | 003/013 | T3 DI DIABLO-MIDWAY #2 3/13 RPR INSS | PISMOBCH | ETL.5970.INSL.NCER | 2022-05-07 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123532363 | 009/263 | T3 DI CLGT-ALLGHNY 009/263 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-05-07 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31633457 | T3 DI COLGATE-ALLEGHANY 008/222 RPL STRW | 70Y
LC | 123532438 | 017/080 | T3 DI MSS LANDING-METCALF 17/80 RPL INSS | MOSSLNDG | ETL.6050.INSL | 2022-05-07 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31606171 | T2 EI MOSS LANDING-METCALF RPL INSS 2TW | 93K
LC | 123532456 | 016/122 | T3 DI GRN VLY- CMP EVERS 16/122 RPL INSS | MOSSLNDG | ETL.1710.INSL | 2022-05-07 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31616433 | T3 DI GRN VLY- CMP EVERS 16/122 RPL INSS | 93K
LC | 123532707 | 030/251 | T3 DI RND MTN-CTTNWD #3 30/251 RPR INSS | TABLEMTN | ETL.5650.INSL | 2022-05-07 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123532784 | 011/267 | T3 DI DRM GRS VLY WMR 11/267 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-05-07 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE ACCH OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617788 | T3 DI DRM-GRSS VLLY-WMR 6/154 RPL POLE | 70Y
LC | 123532787 | 009/006 | T3 DI LAURELES-OTTER 9/6 RPR INSW | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-07 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45376644 | T3 DI LAURELES-OTTER 9/6 RPR INSW | ICW
LC | 123533237 | 013/017 | T3 DI LAURELES-OTTER 13/17 RPR POLE | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-07 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123533238 | 005/005 | T3 DI LAURELES-OTTER 5/5 RPL INSW | MOSSLNDG | ETL.7380.INSL | 2022-05-07 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31612299 | T3 DI LAURELES-OTTER 5/5 RPL INSW | 93I
LC | 123533280 | 003/026 | T3 DI GRN VLY LGS 3/26L RPR STRW | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-05-07 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45606203 | T3 DI GRN VLY LGS 3/26L RPR STRW | ICW
LC | 123533282 | 003/026 | T3 DI GRN VLY LGS 3/26R RPR STRW | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-05-07 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45606204 | T3 DI GRN VLY LGS 3/26R RPR STRW | ICW
LC | 123533521 | 014/114 | T3 DI GRN VLLY-CMP EVERS 14/114 RPL HRDT | MOSSLNDG | ETL.1710.TOWR | 2022-05-07 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45590643 | T3 DI GRN VLLY-CMP EVERS 14/114 RPL HRDT | ICQ
LC | 123533703 | 001/023 | T3 DI CYSRS #3 CLVRDL 001/023 RMV VEG | LAKEVLLE | ETL.1650.POLE.NWOD | 2022-05-07 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR NTDE | Overgrown | Vegetation | Remove
LC | 123533893 | 005/041 | T3 EI MORAGA-SN LEANDRO #1 5/41 RPL INSS | CONCORD | ETL.2770.INSL.NCER | 2022-05-07 | 2022-05-07 |  | 2022-11-03 | 2022-11-07 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617656 | T3 DI MORAGA-SAN LEANDRO #1 RPL INSS 6T | 93K
LC | 123533905 | 013/283 | T3 DI KLRC CDR CRK 13/283 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-05-07 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606234 | T3 EI KILARC-CEDAR CREEK 10/229 RPL POLE | 70Y
LC | 123534114 | 021/570 | T3 DI COLGATE-ALLEGHANY 21/570 RPR INSW | SACTO | ETL.6470.INSL.NCER | 2022-05-07 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123534150 | 021/094 | T3 DI MOSS LANDNG-METCALF 21/94 RPR GYWS | MOSSLNDG | ETL.6050.TOWR | 2022-05-07 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123534151 | 021/094 | T3 DI MSS LNDNG-METCALF 21/94 RPR SHIELD | MOSSLNDG | ETL.6050.TOWR | 2022-05-07 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45579846 | T3 DI MSS LNDNG-METCALF 21/94 RPR SHIELD | ICS
LC | 123534200 | 013/054 | T3 DI GYSR #17-FULTN 13/54 RPR INSS | LAKEVLLE | ETL.4770.INSL.NCER | 2022-05-07 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45290348 | T3 DI GYSR#12-FULTN 13/054 RPR INSS | ICS
LC | 123534250 | 020/540 | T3 DI COLGATE-ALLEGHANY 20/540 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-05-07 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31633603 | T3 DI COLGATE-ALLEGHANY 18/488 RPL POLE | 70Y
LC | 123534258 | 020/540 | T3 DI COLGATE-ALLEGHANY 20/540 RPL HRDD | SACTO | ETL.6470.POLE.WOOD | 2022-05-07 | 2022-04-19 |  | 2022-10-16 | 2022-10-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123534615 | 000/009C | T3 DI GYSRS #3 EGL RCK 0/9C RPR GYWW | LAKEVLLE | ETL.1660.POLE.NWOD | 2022-05-07 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123534653 | 002/052 | T3 EI DRUM-SPAULDING 2/052 RPL PL | SACTO | ETL.6770.POLE.WOOD | 2022-05-07 | 2022-05-07 |  | 2022-11-03 | 2022-11-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31629061 | T3 EI DRUM-SPAULDING 2/052 RPL PL | 70Y
LC | 123534941 | 004/012 | T3 DI KONOCTI-EAGLE ROCK 4/12 RPR GYWW | WILLITS | ETL.6861.POLE.NWOD | 2022-05-07 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123535501 | 011/048 | T3 DI GYSRS #17-FLTN 11/48 RPR INSS | LAKEVLLE | ETL.4770.INSL.CERA | 2022-05-07 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123535505 | 011/048 | T3 DI GYSRS #12-FLTN 11/48 BACKFILL | LAKEVLLE | ETL.4750.TOWR | 2022-05-07 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123535848 | 013/056 | T3 DI GEYSERS #17-FULTON 13/56 COTR KEY | LAKEVLLE | ETL.4770.INSL.NCER | 2022-05-07 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45290353 | T3 DI GEYSERS #17-FULTON 13/56 COTR KEY | ICS
LC | 123536026 | 006/048 | T3 EI MORAGA-SN LENDRO #2 6/48 RPR HRDWT | CONCORD | ETL.2780.INSL.NCER | 2022-05-07 | 2022-05-07 |  | 2022-11-03 | 2022-11-07 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | Missing | Hardware-Tower | Install
LC | 123536645 | 015/116 | T3 DI CMP EVERS-PL SWT 15/116 RPR CNDS | MOSSLNDG | ETL.1220.INSL.NCER | 2022-05-07 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Steel | Repair | 45606213 | T3 DI CMP EVERS-PL SWT 15/116 RPR CNDS | ICS
LC | 123536646 | 015/116 | T3 DI GRN VLY-CMP EVRS 15/116 RMV BUTT | MOSSLNDG | ETL.1710.TOWR | 2022-05-07 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove | 45606214 | T3 DI GRN VLY-CMP EVRS 15/116 RMV BUTT | ICS
LC | 123537238 | 012/057 | T3 EI SAN RAMON-MORAGA 12/57 RPL INSS | CONCORD | ETL.5660.INSL | 2022-05-07 | 2022-05-07 |  | 2022-11-03 | 2022-11-07 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31627446 | T0 DI SAN RMN-MRGA RPL INSLS IN 2 TWRS. | 93K
LC | 123537577 | 000/002 | T3 DI GYSRS #5-GYSRS #3 0/002 RPL HRDD | LAKEVLLE | ETL.1670.POLE.WOOD | 2022-05-07 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45575597 | T3 DI GYSRS #5-GYSRS #3 0/002 RPL HRDD | ICW
LC | 123537596 | 008/064 | T3 EI GREEN VALLEY-LLAGAS 8/64L RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-05-07 | 2022-05-07 |  | 2022-11-03 | 2022-11-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31611564 | T3 EI GREEN VALLEY-LLAGAS 8/64L RPL POLE | 70Y
LC | 123537728 | 005/124 | T3 DI DRM-SPLDNG 5/124 RPR INSW | SACTO | ETL.6770.INSL.NCER | 2022-05-07 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123538612 | 013/015 | T3 DI LAURELES-OTTER 13/15 RPR GYWW | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-09 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123538813 | 011/112A | T3 DI GRN VLY-CMP EVRS 011/112A RPL HRDD | MOSSLNDG | ETL.1710.POLE.WOOD | 2022-05-09 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45606220 | T3 DI GRN VLY-CMP EVRS 011/112A RPL HRDD | ICW
LC | 123539028 | 003/020 | T3 DI SBRNT-R #1 3/20 RPR STRT | CONCORD | ETL.3770.TOWR | 2022-05-09 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123539071 | 011/112B | T3 DI GRN VLY-CMP EVRS 011/112B RPL HRDD | MOSSLNDG | ETL.1710.POLE.WOOD | 2022-05-09 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45606222 | T3 DI GRN VLY-CMP EVRS 011/112B RPL HRDD | ICW
LC | 123539697 | 011/112C | T3 DI GRN VLLY-CMP EVRS 11/112C RPL HRDD | MOSSLNDG | ETL.1710.POLE.WOOD | 2022-05-09 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45606224 | T3 DI GRN VLLY-CMP EVRS 11/112C RPL HRDD | ICW
LC | 123540593 | 015/409 | T3 DI COLGATE-ALLEGHANY 15/409 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-05-09 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31633458 | T3 DI COLGATE-ALLGHNY 011/293 RPL STRW | 70Y
LC | 123541083 | 006/050 | T3 EI GREEN VALLEY-LLAGAS 6/50L RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-05-09 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31610973 | T3 DI GREEN VALLEY-LLAGAS 5/42R RPL POLE | 70Y
LC | 123541307 | 006/051 | T3 EI GREEN VALLEY-LLAGAS 6/51L RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-05-09 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31610973 | T3 DI GREEN VALLEY-LLAGAS 5/42R RPL POLE | 70Y
LC | 123541350 | 001/008 | T3 DI EGL RCK FLTN SLVRD 1/8 COTTER | LAKEVLLE | ETL.4392.INSL.CERA | 2022-05-09 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575434 | T3 DI EGL RCK FLTN SLVRD 1/8 COTTER | ICS
LC | 123542725 | T075 | T3 EI MIDWAY-SANTA MARIA T75 RPL STRT | PISMOBCH | ETL.9240.TOWR | 2022-05-09 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 426 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Tower | Replace
LC | 123543061 | 004/111 | T3 DI DR CRK DRM 4/111 RPL HRDW | SACTO | ETL.6690.POLE.WOOD | 2022-05-09 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123543225 | 000/009 | T3 DI GEYSERS #7-EAGLE ROCK 0/9 RPR FOND | LAKEVLLE | ETL.1680.TOWR | 2022-05-09 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123544010 | 007/055 | T3 EI GREEN VALLEY-LLAGAS 7/055 RPL STRW | MOSSLNDG | ETL.1720.POLE.WOOD | 2022-05-09 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611564 | T3 EI GREEN VALLEY-LLAGAS 8/64L RPL POLE | 70Y
LC | 123544103 | 001/006 | T3 SPRING GAP TAP 1/6 RPR JMPRS | VICTOR | ETL.1402.SWIT | 2022-05-09 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW PATR OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Jumper-Steel | Repair | 45293713 | T3 SPRING GAP TAP 1/6 RPR JMPRS | ICS
LC | 123544288 | 143 | T3 DNNELLS-MI-WUK 007/007 RPR JMPS | VICTOR | ETL.1400.SWIT | 2022-05-09 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW PATR OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Jumper-Steel | Repair | 45293714 | T3 DNNELLS-MI-WUK 007/007 RPR JMPS | ICS
LC | 123544313 | 147 | T3 DONNELLS-MI-WUK 7/5 RPR JMPRS | VICTOR | ETL.1400.SWIT | 2022-05-09 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW PATR OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Jumper-Steel | Repair | 45293712 | T3 DONNELLS-MI-WUK 7/5 RPR JMPRS | ICS
LC | 123544580 | 003/068 | T3 EI DRUM-SPAULDING 3/068 RPL STRW | SACTO | ETL.6770.POLE.WOOD | 2022-05-09 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31629061 | T3 EI DRUM-SPAULDING 2/052 RPL PL | 70Y
LC | 123545127 | :001/005 | T3 DI GEYSERS #9-LAKEVILLE 1/5 COTTER | LAKEVLLE | ETL.4780.INSL.CERA | 2022-05-09 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123546541 | 001/006 | T3 DI DIABLO-MDWY #3 1/6 RPR GYWS | PISMOBCH | ETL.5980.TOWR | 2022-05-09 | 2022-05-07 |  | 2022-11-03 | 2022-11-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123546547 | 006/160 | T3 DI COLGATE-GRASS VLLY 6/160 RPL INSW | SACTO | ETL.6490.INSL.NCER | 2022-05-09 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617974 | T3 EI COLGATE-GRASS VALEY 5/131 RPL INSW | 93I
LC | 123546652 | 001/007 | T3 DI DIABLO-MDWY #3 1/7 RPR FOND | PISMOBCH | ETL.5980.TOWR | 2022-05-09 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123546688 | 003/002 | T3 DI KONOCTI-EAGLE ROCK 03/02 RPR GYWW | WILLITS | ETL.6861.POLE.WOOD | 2022-05-09 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123546752 | 028/231 | T3 DI PIT #1-COTTONWOOD 28/231L COTTER | TABLEMTN | ETL.5390.POLE.STPS | 2022-05-09 | 2022-05-03 |  | 2022-10-30 | 2022-08-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45294994 | T3 DI PIT #1-COTTONWOOD 28/231L COTTER | ICW
LC | 123546824 | 003/039B | T3 DI DRUM SUMMIT #2 3/39B RPR GYWW | SACTO | ETL.1450.POLE.WOOD | 2022-05-09 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123547033 | 008/013 | T3 DI LAURELES-OTTER 8/13 RPR WDPKR | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-09 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123547281 | 019/087 | T3 DI MOSS LANDING-METCLF 19/87 INS HRDT | MOSSLNDG | ETL.6050.TOWR | 2022-05-09 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install
LC | 123547309 | 002/012 | T3 DI DIABLO-MDWY #2 2/012 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2022-05-09 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123547346 | 018/090A | T3 EI CRTNA-MNDCNO #1 18/90A RMV NEST | WILLITS | ETL.1330.POLE.NWOD | 2022-05-09 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove
LC | 123547380 | 003/039C | T3 DI DRUM-SUMMIT #2 3/39C RPR GYWW | SACTO | ETL.1450.POLE.WOOD | 2022-05-09 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123547417 | 012/323 | T3 DI COLGATE-ALLEGHANY 12/323 RPL HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-05-09 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123547430 | 026/007 | T3 EI FULTON-HOPLAND 026/007 RPR POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2022-05-09 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45571488 | T3 EI FULTON-HOPLAND 026/007 RPR POLE | ICW
LC | 123547466 | 005/131 | T3 DI CLGATE-GRSS VLLEY 005/131 RPR STRW | SACTO | ETL.6490.POLE.WOOD | 2022-05-09 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123547474 | 016/435 | T3 DI COLGATE-ALLEGHANY 16/435 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-05-09 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31605566 | HANY 15/402 RPL POLE | 70Y
LC | 123557978 | 016/080 | T3 EI CORTNA-MENDOCNO #1 16/80 INS STEP | WILLITS | ETL.1330.TOWR | 2022-05-10 | 2022-05-10 |  | 2022-11-06 | 2022-11-10 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123558023 | 015/132 | T3 DI CAMP EVERS-PAUL SW 15/132 RPL INSS | MOSSLNDG | ETL.1220.INSL.CERA | 2022-05-10 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615442 | T3 DI CAMP EVERS-PL SWT RPL INSS 2TWR | 93K
LC | 123558451 | 022/094 | T3 DI GYSERS #17-FULTN 22/94 RPR INSS | LAKEVLLE | ETL.4770.INSL.CERA | 2022-05-10 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575587 | T3 DI GYSERS #17-FULTN 22/94 RPR INSS | ICS
LC | 123558493 | 000/021 | T3 DI DEER CREEK-DRUM 0/21 RPL HRDW | SACTO | ETL.6690.POLE.WOOD | 2022-05-10 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123558681 | 020/150 | T3 DI TRNTY CTNWD 20/150 RPR INSW | TABLEMTN | ETL.4040.INSL.CERA | 2022-05-10 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45644607 | T3 DI TRNTY CTNWD 20/150 RPR INSW | ICW
LC | 123559247 | 013/349 | T3 DI COLGATE-ALLGHNY 13/349 RPL SPLW | SACTO | ETL.6470.INSL.NCER | 2022-05-10 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Replace
LC | 123559249 | 013/349 | T3 DI COLGATE-ALLEGHANY 13/349 RPL HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-05-10 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123560946 | 024/099 | T3 DI GYSRS #12 FLTN 24/99 RPR FOND | LAKEVLLE | ETL.4750.TOWR | 2022-05-10 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123562360 | 003/039A | T3 DI DRUM-SUMMIT #2 3/39 RPL HRDD | SACTO | ETL.1450.POLE.WOOD | 2022-05-10 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123562362 | 003/039A | T3 DI DRUM-SUMMIT #2 3/39A RPR GYWW | SACTO | ETL.1450.POLE.WOOD | 2022-05-10 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123562977 | 012/324 | T3 DI COLGATE-ALLGHNY 12/324 RPL HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-05-10 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123563248 | 005/144 | T3 DI DRUM-SPAULING 5/144 RPR HRDW | SACTO | ETL.6770.POLE.WOOD | 2022-05-10 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123563910 | 014/384 | T3 DI COLGATE-ALLEGHANY 14/384 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-05-10 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31633458 | T3 DI COLGATE-ALLGHNY 011/293 RPL STRW | 70Y
LC | 123563978 | 019/530 | T3 DI COLGATE-ALLGHNY 19/530 RPL HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-05-10 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123564172 | 022/597 | T3 DI COLGATE-ALLGHNY 22/597 RPL HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-05-10 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | Missing | Hardware-Wood | Install
LC | 123564787 | 010/002A | T3 DI LRLS OTR 10/2AL RPR GYWW | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-05-10 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123564788 | 010/002A | T3 DI LRLS OTR 10/2AL RPL HRDD | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-05-10 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123564872 | 010/002A | T3 DI LRLS OTR 10/2AL RPR ANCW | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-05-10 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123564875 | 010/002A | T3 DI LRLS OTR 10/2AR RPR GYWW | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-05-10 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123564879 | 010/002A | T3 DI LRLS OTR 10/2AC RPR GYWW | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-05-10 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123565011 | 010/002A | T3 DI LRLS OTR 10/2AC RPL HRDD | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-05-10 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123565013 | 010/002A | T3 DI LRLS OTR 10/2A RPR INSW | MOSSLNDG | ETL.7380.INSL.CERA | 2022-05-10 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123565171 | 010/000 | T3 DI LRLS OTR 10/0R RPR GYWW | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-05-10 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123566082 | 000/002 | T3 DI DEER CREEK-DRUM 0/2 RPR INSW | SACTO | ETL.6690.INSL.NCER | 2022-05-11 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123566537 | 012/116 | T3 DI GRN VLLY-CMP EVRS 12/116 RPL STRW | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-05-11 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31628900 | T3 DI GRN VLLY-CMP EVRS 11/108L RPL POLE | 70Y
LC | 123566580 | 012/116 | T3 DI GRN VLLY-CMP EVRS 12/116R RPL POLE | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-05-11 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31628900 | T3 DI GRN VLLY-CMP EVRS 11/108L RPL POLE | 70Y
LC | 123566759 | 001/007 | T3 DI KNCT EGL RCK 1/7 RPR INSW | WILLITS | ETL.6861.INSL.NCER | 2022-05-11 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123567122 | 005/147 | T3 DI DRM SPLDNG 5/147 RPR INSW | SACTO | ETL.6770.INSL.NCER | 2022-05-11 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123569465 | 008/005 | T3 EI MNDOCNO-WLLTS-FRT-BR 8/5 RPR HRDW | WILLITS | ETL.7550.INSL.CERA | 2022-05-11 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45640387 | T3 EI MNDOCNO-WLLTS-FRT-BR 8/5 RPR HRDW | ICW
LC | 123569484 | 010/236 | T3 DI KLRC CDR CRK 10/236 INS HRDD | TABLEMTN | ETL.7290.POLE.NWOD | 2022-05-11 | 2022-04-01 |  | 2022-09-28 | 2022-10-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45459143 | T3 DI KLRC CDR CRK 10/236 INS HRDD | ICW
LC | 123570967 | 016/068 | T3 DI GEYSERS #12-FULTON 16/68 RPL INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2022-05-11 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615952 | T3 DI GEYSERS #12-FULTON RPL INSS 4TWR | 93K
LC | 123571045 | T043 | T3 EI MIDWAY-SANTA MARIA_T043 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2022-05-11 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace
LC | 123572093 | 008/010 | T3 EI MNDOCNO-WLLTS-FRT-BR 8/10 INS BOND | WILLITS | ETL.7550.INSL.NCER | 2022-05-11 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45640386 | T3 EI MNDOCNO-WLLTS-FRT-BR 8/10 INS BOND | ICW
LC | 123572148 | T046 | T3 EI MIDWAY-SANTA MARIA_T046 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2022-05-11 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace
LC | 123572170 | T-101 | T3 EI MIDWAY-SANTA MARIA T-101 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2022-05-11 | 2022-05-10 |  | 2022-11-06 | 2022-11-10 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace
LC | 123572171 | T045 | T3 EI MIDWAY-SANTA MARIA T045 BENT STEEL | PISMOBCH | ETL.9240.TOWR | 2022-05-11 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123572314 | 010/054 | T3 DI FULTON-IGNACIO #1 10/54 RMV VEG | LAKEVLLE | ETL.4680.TOWR | 2022-05-11 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123572374 | Z011/008 | T3 FULTON-CALISTOGA Z011/008 RPL INSS | LAKEVLLE | ETL.6880.INSL.NCER | 2022-05-11 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW NONR OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617412 | T3 FULTON-CALISTOGA Z011/008 RPL INSS | 93K
LC | 123572578 | 015/066 | T3 DI GEYSERS #12-FULTON 15/66 INS HRDT | LAKEVLLE | ETL.4750.TOWR | 2022-05-11 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | Missing | Hardware-Tower | Install
LC | 123572702 | 031/263 | T3 EI PIT #1-COTTONWD 31/263 RPR GYWS | TABLEMTN | ETL.5390.TOWR | 2022-05-11 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123572703 | 034/293 | T3 EI PIT #1-CTTNWD 34/293 BENT STEEL | TABLEMTN | ETL.5390.TOWR | 2022-05-11 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45639716 | T3 EI PIT #1-CTTNWD 34/293 BENT STEEL | ICQ
LC | 123572704 | 031/262 | T3 EI PIT #1-COTTONWD 31/262 BENT STEEL | TABLEMTN | ETL.5390.TOWR | 2022-05-11 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO CLMB FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45639703 | T3 EI PIT #1-COTTONWD 31/262 BENT STEEL | ICQ
LC | 123572769 | 008/004 | T3 DI LAURLES-OTTER 8/004 REFRAME | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-11 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31617672 | T3 DI LAURLES-OTTER 8/004 REFRAME | 93E
LC | 123572852 | 013/008 | T3 DI LAURELES-OTTER 13/8 RPL HRDD | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-11 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123573092 | 000/011 | T3 DI FRNCH MDWS-MDDL FRK 0/11 RPL INSW | SACTO | ETL.6870.INSL | 2022-05-11 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31614939 | T3 DI FRNCH MDWS-MDDL FRK 0/11 RPL INSW | 93I
LC | 123573097 | 010/040 | T3 DI DIABLO-MIDWAY #2 10/40 COTTER | PISMOBCH | ETL.5970.INSL.NCER | 2022-05-11 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123573098 | 013/118B | T3 DI GRN VLY PL SWT 13/118B RPR ANCW | MOSSLNDG | ETL.1730.POLE.NWOD | 2022-05-11 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45606232 | T3 DI GRN VLY PL SWT 13/118B RPR ANCW | ICW
LC | 123573274 | 009/094 | T3 DI GREEN VALLY-PL SWT 9/94R INS HRDW | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-05-11 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45606235 | T3 DI GREEN VALLY-PL SWT 9/94R INS HRDW | ICW
LC | 123573275 | 009/094 | T3 DI GREEN VALLEY-PL SWT 9/94 RPL INSW | MOSSLNDG | ETL.1730.INSL.CERA | 2022-05-11 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31629563 | T3 DI GREEN VALLEY-PAUL SW 9/92 RPL INSS | 93I
LC | 123573416 | 004/095 | T3 DI CLGT-CHLLNG 4/95 RPR GYWW | SACTO | ETL.6480.POLE.WOOD | 2022-05-11 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123573439 | 000/006A | T3 DI DRUM-SUMMIT #2 000/006A REGRADE | SACTO | ETL.1450.POLE.NWOD | 2022-05-11 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123573445 | 000/009 | T3 DI GYSRS #5-GYSRS #3 0/9 RPL HRDW | LAKEVLLE | ETL.1670.POLE.WOOD | 2022-05-11 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45575598 | T3 DI GYSRS #5-GYSRS #3 0/9 RPL HRDW | ICW
LC | 123573458 | 008/211 | T3 DI COLGATE-ALLEGHANY 8/211 RPR WDPKR | SACTO | ETL.6470.POLE.WOOD | 2022-05-11 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123573534 | 005/104 | T3 DI FRNCH MDWS-MDL FK 5/104 RPR GYWW | SACTO | ETL.6870.POLE.WOOD | 2022-05-11 | 2022-05-07 |  | 2022-11-03 | 2022-11-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123573551 | 000/007 | T3 DI GEYSERS #7-EAGLE ROCK 0/7 RPR INSS | LAKEVLLE | ETL.1680.INSL.CERA | 2022-05-11 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575555 | T3 DI GEYSERS #7-EAGLE ROCK 0/7 RPR INSS | ICS
LC | 123573611 | 014/129 | T3 DI CAMP EVERS-PAUL SWE14/129 RPL INSS | MOSSLNDG | ETL.1220.INSL.CERA | 2022-05-11 | 2022-04-25 |  | 2022-10-22 | 2022-10-25 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31605677 | T3 DI CAMP EVERS-PAUL SWE14/129 RPL INSS | 93K
LC | 123573645 | 012/112 | T3 DI GRN VALY-PAUL SWT 12/112R RPR HRDW | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-05-11 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45606236 | T3 DI GRN VALY-PAUL SWT 12/112R RPR HRDW | ICW
LC | 123573646 | 012/112 | T3 DI GRN VALY-PAUL SWT 12/112 RPL HRDW | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-05-11 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45606237 | T3 DI GRN VALY-PAUL SWT 12/112 RPL HRDW | ICW
LC | 123573707 | 006/027 | T3 DI EGL ROCK-FLTN-SLVRDO 6/27 RMV NEST | LAKEVLLE | ETL.4392.TOWR | 2022-05-11 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45575460 | T3 DI EGL ROCK-FLTN-SLVRDO 6/27 RMV NEST | ICS
LC | 123574093 | T041 | T3 EI MIDWAY-SANTA MARIA T041 BENT STEEL | PISMOBCH | ETL.9240.TOWR | 2022-05-12 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123574094 | T042 | T3 EI MIDWAY-SANTA MARIA T042 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2022-05-12 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace
LC | 123574333 | 021/313 | T3 DI GOLD HILL#1 21/313 INS IBWW | SACTO | ETL.6950.POLE.NWOD | 2022-05-12 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Replace
LC | 123574389 | :008/001 | T3 DI FULTON-CALISTOGA :8/1 RPL HRDD | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-12 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123574431 | :008/001 | T3 DI FULTON-CALISTOGA :8/1 RPR INSW | LAKEVLLE | ETL.6880.INSL.CERA | 2022-05-12 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45571429 | T3 DI FULTON-CALISTOGA :8/1 RPR INSW | ICW
LC | 123574447 | 022/614 | T3 DI COLGATE-ALLGHNY 22/614 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-05-12 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31605566 | HANY 15/402 RPL POLE | 70Y
LC | 123574623 | 013/284 | T3 DI KILARC-CDAR CRK 13/284 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-05-12 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617628 | T3 DI KILARC-CEDAR CRK 4/96 RPL STRW | 70Y
LC | 123575072 | 000/009 | T3 DI DRM-GRS-VLLY WIMR 0/009 RPR INSW | SACTO | ETL.6760.INSL.NCER | 2022-05-12 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123575974 | 002/011 | T3 DI DIABLO-MIDWAY #3 2/11 INS COTTER | PISMOBCH | ETL.5980.INSL | 2022-05-12 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123576700 | 011/058 | T3 DI FULTON-IGNACIO #1 11/58 RPR INSS | LAKEVLLE | ETL.4680.INSL | 2022-05-12 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571460 | T3 DI FULTON-IGNACIO #1 11/58 RPR INSS | ICS
LC | 123577041 | 000/007 | T3 DI DRM GRS VLY WMR 0/7 RPR STRW | SACTO | ETL.6760.POLE.NWOD | 2022-05-12 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123577045 | 000/007 | T3 DI DRM GRS VLY WMR 0/7 RPR GYWW | SACTO | ETL.6760.POLE.NWOD | 2022-05-12 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123577179 | 000/001 | T3 DI DRUM-HIGGINS 0/1 RPR SWTCh 337 | SACTO | ETL.4393.TOWR | 2022-05-12 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 623 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | Out of Adjustment | Switch | Repair | 45526721 | T3 DI DRUM-HIGGINS 0/1 RPR SWTCH 337 | ICE
LC | 123577289 | 014/130 | T3 DI GRN VLLY-PAUL SWT 14/130 BNT STEEL | MOSSLNDG | ETL.1730.TOWR | 2022-05-12 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123577676 | 008/193 | T3 DI DRM-GRSS VLLY-WMR 8/193 RPL INSW | SACTO | ETL.6760.INSL.NCER | 2022-05-12 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31603862 | T3 DI DRM-GRSS VLLY-WMR 8/193 RPL INSW | 93I
LC | 123577750 | 020/084 | T3 DI GEYSERS #12-FULTON 20/084 RPR INSS | LAKEVLLE | ETL.4750.INSL | 2022-05-12 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571484 | T3 DI GEYSERS #12-FULTON 20/084 RPR INSS | ICS
LC | 123578191 | 000/001 | T3 DI DRUM-HIGGINS 000/001 UNBURY | SACTO | ETL.4393.TOWR | 2022-05-12 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45599180 | T3 DI DRUM-HIGGINS 000/001 UNBURY | ICQ
LC | 123578192 | 000/001 | T3 DI DRUM-HIGGINS 000/001 RPP STRT | SACTO | ETL.4393.TOWR | 2022-05-12 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45599181 | T3 DI DRUM-HIGGINS 000/001 RPP STRT | ICQ
LC | 123578629 | 026/116 | T3 DI EGL RCK-FLTN-SLVRD 26/116 RPL INSS | LAKEVLLE | ETL.4392.INSL.NCER | 2022-05-12 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31613370 | T3 EI EAGL RCK-FLTN-SLVRD RPL INSS 3TWR | 93K
LC | 123578677 | 014/006 | T3 DI LAURELES-OTTER 014/006R RPR GYWW | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-05-12 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123578866 | :008/000 | T3 DI FLTN-CLISTGA 8/000 RPR STRW | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-05-12 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45575470 | T3 DI FLTN-CLISTGA 8/000 RPR STRW | ICW
LC | 123579035 | 014/006 | T3 DI LAURELES-OTTER 014/006C RPR GYWW | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-05-12 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123579128 | 010/002 | T3 DI LAURELES-OTTER 10/2R INS HRDD | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-05-12 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | Missing | Hardware-Wood | Install
LC | 123579129 | 010/002 | T3 DI LAURELES-OTTER 10/2C INS HRDD | MOSSLNDG | ETL.7380.POLE.WDPS | 2022-05-12 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | Missing | Hardware-Wood | Install
LC | 123579226 | 011/102 | T3 DI GRN VLY PL SWT 11/102R RPR HRDW | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-05-12 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45606381 | T3 DI GRN VLY PL SWT 11/102R RPR HRDW | ICW
LC | 123579524 | 007/086 | T3 DI GRN VLLY-CAMP EVRS 7/86 RPL INSW | MOSSLNDG | ETL.1710.INSL.NCER | 2022-05-12 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31618525 | T2 DI GREEN VALLY-CMP EVRS 3/51 RPL INSW | 93I
LC | 123580060 | 024/013 | T3 DI MAPLE-CREEK-HOOPA 24/13 RMV STEP | EUREKA | ETL.7490.POLE.NWOD | 2022-05-12 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123580715 | 013/056 | T3 DI GEYSERS #17-FLTN 13/56 DUP CNCL | LAKEVLLE | ETL.4770.INSL.NCER | 2022-05-12 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575545 | T3 DI GEYSERS #17-FLTN 13/56 RPR INSS | ICS
LC | 123580971 | 000/012 | T3 EI DRUM-SUMMIT #1 000/012 RPR CNDW | SACTO | ETL.1440.INSL.CERA | 2022-05-12 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Conductor-Wood | Repair
LC | 123581566 | 042/308 | T3 EI CARIBOU-TBL MTN 42/308 INS ZENA | TABLEMTN | ETL.4440.TOWR | 2022-05-12 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 593 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Raptor Guard-Steel | Replace
LC | 123581782 | 028/232 | T3 DI RND MTN-CTNWD #3 28/232 BNT STEEL | TABLEMTN | ETL.5650.TOWR | 2022-05-12 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123581786 | 025/002 | T3 DI MAPLE CREEK-HOOPA 25/2 RPR INSW | EUREKA | ETL.7490.INSL.NCER | 2022-05-12 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123581911 | 007/079 | T3 DI DRM RIO OSO #1 007/079 BNT STEEL | SACTO | ETL.1420.TOWR | 2022-05-12 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45599990 | T3 DI DRM RIO OSO #1 007/079 BNT STEEL | ICQ
LC | 123582276 | 005/134 | T3 DI CLGTE GRSS VLLY 005/134 REFRAME | SACTO | ETL.6490.POLE.WOOD | 2022-05-12 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31617973 | T2 DI COLGATE-GRASS VALLEY 4/107 REFRAME | 93E
LC | 123582293 | 002/046 | T3 DI BURNS-LN STR #2 2/46 INS DAMW | MOSSLNDG | ETL.6240.INSL.NCER | 2022-05-12 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | Missing | Damper-Wood | Install | 45606385 | T3 DI BURNS-LN STR #2 2/46 INS DAMW | ICW
LC | 123582294 | 002/046 | T3 DI BURNS-LN STR #2 2/46 RPR CNDW | MOSSLNDG | ETL.6240.INSL.NCER | 2022-05-12 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45606386 | T3 DI BURNS-LN STR #2 2/46 RPR CNDW | ICW
LC | 123582504 | 017/081 | T3 DI MSS LNDG-METCLF 17/081 RPR GYWS | MOSSLNDG | ETL.6050.TOWR | 2022-05-12 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123582505 | 005/144 | T3 DI COLGATE-GRSS VLLY 005/144 RPR INSW | SACTO | ETL.6490.INSL | 2022-05-12 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123582506 | 017/081 | T3 DI MSS LNDG-METCLF 17/081 RPR SHLS | MOSSLNDG | ETL.6050.TOWR | 2022-05-12 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45581080 | T3 DI MSS LNDG-METCLF 17/081 RPR SHLS | ICS
LC | 123582533 | 017/081 | T3 DI MSS LNDG-METCLF 17/081 RPL HRDWT | MOSSLNDG | ETL.6050.TOWR | 2022-05-12 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install
LC | 123583639 | 009/095 | T3 DI GREEN VLY-PAUL SWT 9/95L RPL HDWW | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-05-13 | 2022-04-21 |  | 2022-10-18 | 2022-10-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45606387 | T3 DI GREEN VLY-PAUL SWT 9/95L RPL HDWW | ICW
LC | 123584001 | 028/125 | T3 DI FULTON-LAKEVILLE 28/125 RPL INSS | LAKEVLLE | ETL.4950.INSL | 2022-05-13 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31606170 | T2 DI FULTON-LAKEVILLE+ RPL INSS 3TWR | 93K
LC | 123584006 | 008/161 | T3 DI FRNCH MDWS-MDLE FK 8/161 RPR GYWW | SACTO | ETL.6870.POLE.WOOD | 2022-05-13 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123584065 | 006/080B | T3 DI GRN VLY CMP EVRS 6/80B RPR GYWW | MOSSLNDG | ETL.1710.POLE.NWOD | 2022-05-13 | 2022-04-14 |  | 2022-10-11 | 2022-10-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45606388 | T3 DI GRN VLY CMP EVRS 6/80B RPR GYWW | ICW
LC | 123584358 | 000/002 | T3 DI DRUM-SPAULDING 00/02 RPR INSW | SACTO | ETL.6770.INSL.NCER | 2022-05-13 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123584359 | 000/002 | T3 DI DRUM-SPAULDING 00/02 RPL HRDD | SACTO | ETL.6770.POLE.WOOD | 2022-05-13 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123584583 | 008/142 | T3 DI COLGATE-CHALLENGE 8/142 RPL SPLW | SACTO | ETL.6480.INSL.NCER | 2022-05-13 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Replace
LC | 123584985 | -013/006 | T3 DI FLTN-CALISTOG -13/006 RPL INSW | LAKEVLLE | ETL.6880.INSL.CERA | 2022-05-13 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31616688 | T3 DI FLTN-CALISTOG -13/006 RPL INSW | 93I
LC | 123585496 | 008/088 | T3 DI IGNACIO-BOLINAS #1 08/88 RPR GYWW | LAKEVLLE | ETL.7140.POLE.WOOD | 2022-05-13 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45486136 | T3 DI IGNACIO-BOLINAS #1 08/88 RPR GYWW | ICW
LC | 123585710 | 000/013 | T3 DI WEST PNT-VLLY SPRNGS 0/13 RPL INSW | VICTOR | ETL.8350.INSL.CERA | 2022-05-13 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31604914 | T3 DI WEST PNT-VLLY SPRNGS 0/13 RPL INSW | 93I
LC | 123586074 | 001/014C | T3 DI DRUM-SUMMIT #1 1/14C RPR POLE | SACTO | ETL.1440.POLE.NWOD | 2022-05-13 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123586276 | 014/002 | T3 DI LAURELES-OTTER 14/02 RPR POLE | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-13 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123586367 | 001/009 | T3 DI RND MTN-TBL MTN #2 1/009 COTTER | TABLEMTN | ETL.6070.INSL | 2022-05-13 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45457154 | T3 DI RND MTN-TBL MTN #2 1/009 COTTER | ICS
LC | 123586474 | 001/015C | T3 DI DRUM-SUMMIT #1 01/15C RMV BUTT | SACTO | ETL.1440.POLE.NWOD | 2022-05-13 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123586589 | 005/020 | T3 DI EGL RCK-FLTN SLVRDO 5/20 RPR INSS | LAKEVLLE | ETL.4392.INSL.CERA | 2022-05-13 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123586786 | 009/147 | T3 DI WEIMAR #1 9/147 INST HDWW | SACTO | ETL.7560.POLE.WOOD | 2022-05-13 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123586924 | 011/104 | T3 DI GRN VALY-PAUL SWET 11/104 RPR STRW | MOSSLNDG | ETL.1730.POLE.WOOD | 2022-05-13 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45606391 | T3 DI GRN VALY-PAUL SWET 11/104 RPR STRW | ICW
LC | 123587042 | 001/001 | T3 EI MISSION POWER TAP 1/1 RMV STEPS | LAKEVLLE | ETL.1651.POLE.NWOD | 2022-05-13 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123587043 | 001/001 | T3 EI MISSION POWER TAP 1/1 RPR INSW | LAKEVLLE | ETL.1651.INSL.NCER | 2022-05-13 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 45450245 | T3 EI MISSION POWER TAP 1/1 RPR INSW | ICW
LC | 123587186 | 000/005 | T3 DI BURNS-LONE STAR #2 0/5 RPL HRDW | MOSSLNDG | ETL.6240.INSL.NCER | 2022-05-13 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45606392 | T3 DI BURNS-LONE STAR #2 0/5 RPL HRDW | ICW
LC | 123587270 | 024/660 | T3 DI COLGATE-ALLEGHANY 24/660 INS HRDD | SACTO | ETL.6470.POLE.WOOD | 2022-05-13 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Missing | Hardware-Wood | Install
LC | 123587529 | 021/107 | T3 DI RND MTN-TBL MTN #2 21/107 RPL INSS | TABLEMTN | ETL.6070.INSL | 2022-05-13 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617251 | T3 DI RND MTN TBL MTN#2 2/015 RPL INSS | 93K
LC | 123588084 | 012/014 | T3 DI MAPLE CREEK-HOOPA 12/14 RPR INSW | EUREKA | ETL.7490.INSL | 2022-05-13 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123588516 | 012/000 | T3 DI LAURELES-OTTER 12/000 RPR GYWW | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-13 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123588641 | 011/107 | T3 DI GRN VLY PAUL SWEET 11/107 RPL HRDW | MOSSLNDG | ETL.1730.POLE.WOOD | 2022-05-13 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45606393 | T3 DI GRN VLY PAUL SWEET 11/107 RPL HRDW | ICW
LC | 123588643 | 011/107 | T3 DI GRN VLY PAUL SWEET 11/107 RPR INSW | MOSSLNDG | ETL.1730.INSL.CERA | 2022-05-13 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45606394 | T3 DI GRN VLY PAUL SWEET 11/107 RPR INSW | ICW
LC | 123588648 | 003/009 | T3 DI WSHN SN JQN #3 3/9 RPR STRW | FRESNO | ETL.9340.POLE.NWOD | 2022-05-13 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45598612 | T3 DI WSHN SN JQN #3 3/9 RPR STRW | ICW
LC | 123589005 | 006/024 | T3 DI EGL RCK FLTN SLVRD 6/24 RPL HRDT | LAKEVLLE | ETL.4392.TOWR | 2022-05-13 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123589100 | 004/058 | T3 EI DRUM-SUMMIT #1 4/58 RPR POLE | SACTO | ETL.1440.POLE.WDPS | 2022-05-13 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123589210 | 006/026 | T3 DI GEYSERS #9-LAKEVILLE 6/26 RPR INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2022-05-13 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575580 | T3 DI GEYSERS #9-LAKEVILLE 6/26 RPR INSS | ICS
LC | 123589402 | 009/041 | T3 DI GEYSERS #12-FULTON 9/41 RPR INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2022-05-13 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571467 | T3 DI GEYSERS #12-FULTON 9/41 RPR INSS | ICS
LC | 123589447 | 009/041 | T3 DI GEYSERS #17-FULTON 9/41 RPR INSS | LAKEVLLE | ETL.4770.INSL.CERA | 2022-05-13 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123589473 | 011/105 | T3 DI GRN VLLY-PAUL SWT 11/105 RPL INSW | MOSSLNDG | ETL.1730.INSL | 2022-05-13 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31629563 | T3 DI GREEN VALLEY-PAUL SW 9/92 RPL INSS | 93I
LC | 123589478 | B023/526 | T3 DI DRM-GRASS VLY-WMR B23/526 RPR GYWW | SACTO | ETL.6760.POLE.NWOD | 2022-05-13 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123590515 | 000/004 | T3 EI DRUM-SUMMIT #1 000/004R RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2022-05-13 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31618287 | T3 EI DRUM-SUMMIT #1 000/004L RPL POLE | 70Y
LC | 123590936 | 017/083 | T3 EI TIDEWATER-SOBRANTE 17/083 RPL INSS | CONCORD | ETL.5770.INSL | 2022-05-13 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619354 | T3 EI TIDEWATER-SOBRANTE RPL INSS 4TWRS | 93K
LC | 123591063 | 004/050 | T3 EI DRUM-SUMMIT #1 004/050L RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2022-05-13 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31618287 | T3 EI DRUM-SUMMIT #1 000/004L RPL POLE | 70Y
LC | 123592852 | 002/052 | T3 DI BRNS-LONE STAR #2 2/52 RPR INSW | MOSSLNDG | ETL.6240.INSL.NCER | 2022-05-14 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45606395 | T3 DI BRNS-LONE STAR #2 2/52 RPR INSW | ICW
LC | 123592857 | 025/005 | T3 DI MAPLE CREEK-HOOPA 25/5 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2022-05-14 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123592864 | -015/006 | T3 DI FULTON-CALISTOGA -015/6 RPR GYWW | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-05-14 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45485894 | T3 DI FULTON-CALISTOGA -015/6 RPR GYWW | ICW
LC | 123593121 | 000/020 | T3 DI DRUM-GRSS VLY-WEIMAR 0/20 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2022-05-14 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123593242 | 029/238 | T3 DI PIT #1-COTTONWOOD 029/238 UNBURY | TABLEMTN | ETL.5390.TOWR | 2022-05-14 | 2022-04-27 |  | 2022-10-24 | 2022-10-27 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45639678 | T3 DI PIT #1-COTTONWOOD 029/238 UNBURY | ICQ
LC | 123593251 | 004/091 | T3 DI FRNCH MDWS-MID FRK 4/91 REFRAME | SACTO | ETL.6870.POLE.WOOD | 2022-05-14 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31633954 | T3 DI FRNCH MDWS-MID FRK 4/91 REFRAME | 93E
LC | 123593492 | 000/004 | T3 EI MISSION POWER TAP 000/004 RPR ANCW | LAKEVLLE | ETL.1651.POLE.NWOD | 2022-05-14 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP PGEA OH FMOB TR3 PRTO | No Good/Out of Stdrd | Anchor-Wood | Repair | 45576011 | T3 EI MISSION POWER TAP 000/004 RPR ANCW | ICW
LC | 123593517 | 002/030 | T3 EI DRUM-SUMMIT #1 2/30R RPR POLE | SACTO | ETL.1440.POLE.WDPS | 2022-05-14 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123593608 | -018/008 | T3 EI FULTON-CALISTOGA -018/008 RPL HRDW | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-14 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45485880 | T3 EI FULTON-CALISTOGA -018/008 RPL HRDW | ICW
LC | 123593826 | 003/016B | T3 DI EGL RK-FLTN-SLVRDO 3/16B RPL HDWT | LAKEVLLE | ETL.4392.TOWR | 2022-05-14 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123593988 | -018/007 | T3 EI FULTON-CALISTOGA -018/007 RPL ANCW | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-14 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31616689 | T3 EI FULTON-CALISTOGA -018/007 RPL ANCW | 93E
LC | 123594026 | 019/088 | T3 DI MOSS LANDNG-METCALF 19/88 RPR GYWS | MOSSLNDG | ETL.6050.TOWR | 2022-05-14 | 2022-05-10 |  | 2022-11-06 | 2022-11-10 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123594066 | 005/132 | T3 DI DEER CREEK-DRUM 5/132 RPL HRDW | SACTO | ETL.6690.POLE.WOOD | 2022-05-14 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123594361 | 003/078 | T3 DI DEER CREEK-DRUM 003/078 RPR POLE | SACTO | ETL.6690.POLE.NWOD | 2022-05-14 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123594515 | 006/014 | T3 DI WISHON-SAN JQUIN #3 6/14 RMV STEP | FRESNO | ETL.9340.POLE.NWOD | 2022-05-14 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45489590 | T3 DI WISHON-SAN JQUIN #3 6/14 RMV STEP | ICW
LC | 123594516 | 006/014 | T3 DI WISHON-SAN JQUIN #3 6/14 RPR JMPW | FRESNO | ETL.9340.INSL.NCER | 2022-05-14 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Wood | Repair | 45489556 | T3 DI WISHON-SAN JQUIN #3 6/14 RPR JMPW | ICW
LC | 123594597 | 013/009 | T3 DI LAURELES-OTTER 13/9 RPL POLE | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-14 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31629347 | T3 DI LAURALES-OTTER 6/001 RPL STRW | 70Y
LC | 123594604 | T088 | T3 DI MIDWAY-SANTA MARIA T088 INS HRDT | PISMOBCH | ETL.9240.TOWR | 2022-05-14 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Missing | Hardware-Tower | Install
LC | 123595102 | T089 | T3 DI MIDWAY-SANTA MARIA T089 UNBURY | PISMOBCH | ETL.9240.TOWR | 2022-05-14 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123595220 | 014/115 | T3 DI CAMP EVERS-PL SWT 014/115 RPL INSS | MOSSLNDG | ETL.1220.INSL | 2022-05-14 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615442 | T3 DI CAMP EVERS-PL SWT RPL INSS 2TWR | 93K
LC | 123595338 | 014/379 | T3 DI CLGTE-ALLGHNY 14/379 INST HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-05-14 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | Missing | Hardware-Wood | Install
LC | 123595486 | 004/059 | T3 DI DRUM-SUMMIT #1 4/59C RPL ANCHW | SACTO | ETL.1440.POLE.WDPS | 2022-05-14 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Anchor-Wood | Replace | 31618289 | T3 DI DRUM-SUMMIT #1 4/59C RPL ANCHW | 93E
LC | 123595546 | 018/512 | T3 DI CLGTE-ALLGHAN 18/512 RPL HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-05-14 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123595548 | 004/121 | T3 DI COLGATE-ALLEGHANY 4/121 INS HRDW | SACTO | ETL.6470.POLE.NWOD | 2022-05-14 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123595743 | 004/067 | T3 DI KESWICK-TRINITY 4/67 RPR INSW | TABLEMTN | ETL.7270.INSL.NCER | 2022-05-14 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123595782 | 000/010 | T3 DI DRUM-SPAULDING 000/010 RPR POLE | SACTO | ETL.6770.POLE.NWOD | 2022-05-14 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123595858 | 017/468 | T3 DI COLGATE-ALLEGHNY 17/468 RPL HDWW | SACTO | ETL.6470.POLE.WOOD | 2022-05-14 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123596017 | 014/376 | T3 DI COLGATE-ALLEGHANY 14/376 RPR SPLW | SACTO | ETL.6470.INSL.NCER | 2022-05-14 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 123596096 | 006/160 | T3 DI DRUM-GRAS VALY-WEMR 6/160 RPR INSW | SACTO | ETL.6760.INSL.NCER | 2022-05-14 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCM OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123596117 | 011/218 | T3 DI FRNCH MDWS-MDL FRK 11/218 RPL STRW | SACTO | ETL.6870.POLE.WOOD | 2022-05-14 | 2022-05-07 |  | 2022-11-03 | 2022-11-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606072 | T3 EI FRNCH MDWS-MDDLE FRK 0/2 RPL POLE | 70Y
LC | 123596161 | 007/009 | T3 DI POTTER VALLEY-WILLITS 7/9 RMV STEP | WILLITS | ETL.7820.POLE.NWOD | 2022-05-14 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123596162 | 007/009 | T3 DI POTTER VALLEY-WILLITS 7/9 RPR INSW | WILLITS | ETL.7820.INSL.NCER | 2022-05-14 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123596207 | 001/026 | T3 DI FRNCH MDWS-MDL FRK 1/26 REFRAME | SACTO | ETL.6870.POLE.WOOD | 2022-05-14 | 2022-05-07 |  | 2022-11-03 | 2022-11-07 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31633859 | T3 EI FRNCH MDOWS-MDLE FRK 0/16 REFRAME | 93E
LC | 123596270 | 021/587 | T3 DI COLGATE-ALLEGHNY 21/587 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2022-05-14 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123596344 | 009/229 | T3 DI DRUM-GRSS VLLY-WMR 9/229 RPR IBWW | SACTO | ETL.6760.POLE.WOOD | 2022-05-14 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair
LC | 123596375 | 003/089 | T3 DI DRM-SPLDNG 003/089 RPR STRW | SACTO | ETL.6770.POLE.NWOD | 2022-05-14 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123596517 | T071 | T3 DI MIDWAY-SANTA MARIA T071 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2022-05-14 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Insulator-Steel | Replace
LC | 123596651 | 001/035 | T3 DI FRNCH MDWS-MID FRK 1/35 INS HRDD | SACTO | ETL.6870.POLE.WOOD | 2022-05-14 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Missing | Hardware-Wood | Install
LC | 123596728 | 021/010 | T3 DI MAPLE CREEK-HOOPA 21/10 RPL HRDD | EUREKA | ETL.7490.POLE.NWOD | 2022-05-14 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCH OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45416606 | T3 DI MAPLE CK-HOOPA 21/010 RPL HRDD | ICW
LC | 123596870 | 021/010 | T3 DI MAPLE CREEK-HOOPA 21/10 INS RPR | EUREKA | ETL.7490.INSL.NCER | 2022-05-14 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45416602 | T3 DI MAPLE CK-HOOPA 21/010 INS RPR | ICW
LC | 123596871 | 021/010 | T3 DI MAPLE CREEK-HOOPA 21/10 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2022-05-14 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCH OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45416605 | T3 DI MAPLE CK-HOOPA 21/010 RPR GYWW | ICW
LC | 123597214 | 012/317 | T3 DI CLGTE-ALLGHNY 12/317 RPR INSW | SACTO | ETL.6470.INSL.NCER | 2022-05-14 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123597565 | 032/161 | T3 DI FULTON-PUEBLO 32/161 RPR FOND | LAKEVLLE | ETL.1600.TOWR | 2022-05-14 | 2022-05-10 |  | 2022-11-06 | 2022-11-10 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123597750 | 004/072 | T3 DI SISQUOC-GAREY-04/72 RPL INSW | PISMOBCH | ETL.3690.INSL | 2022-05-14 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31629721 | T3 DI SSQC GRY 4/69A RPL INSW | 93I
LC | 123600191 | 002/015 | T3 EI SAN RAMON-MORAGA 02/015 RPL INSS | CONCORD | ETL.5660.INSL | 2022-05-15 | 2022-05-15 |  | 2022-11-11 | 2022-11-15 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615181 | T3 DI SN RAMON-MORAGA RPL INSS 3TWR | 93K
LC | 123600360 | 012/001 | T3 EI UKH-HPLND-CLVRDLE 012/001 RPR GYWW | WILLITS | ETL.4050.POLE.STPS | 2022-05-15 | 2022-05-15 |  | 2022-11-11 | 2022-11-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45593082 | T3 EI UKH-HPLND-CLVRDLE 012/001 RPR GYWW | ICW
LC | 123600367 | -017/001 | T3 EI FULTON-CALISTOGA -017/001 RPL HRDW | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-15 | 2022-05-15 |  | 2022-11-11 | 2022-11-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45485886 | T3 EI FULTON-CALISTOGA -017/001 RPL HRDW | ICW
LC | 123601774 | 000/001 | T3 EI BURNS-LONE STAR #2 0/1 RPL GYWW | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-05-15 | 2022-05-15 |  | 2022-11-11 | 2022-11-15 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Pole-Steel | Replace
LC | 123603195 | 000/000 | T3 DI WSHN CPRMN 0/0 RPR JUMPS | FRESNO | ETL.9330.INSL.NCER | 2022-05-16 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Jumper-Steel | Repair | 45489213 | T3 DI WSHN CPRMN 0/0 RPR JUMPS | ICS
LC | 123603196 | 000/000 | T3 DI WSHN CPRMN 0/0 RPR GYWS | FRESNO | ETL.9330.TOWR | 2022-05-16 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45489214 | T3 DI WSHN CPRMN 0/0 RPR GYWS | ICS
LC | 123603736 | -017/004 | T3 DI FLTN CLSTG -17/4 RPR STRW | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-16 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45485887 | T3 DI FLTN CLSTG -17/4 RPR STRW | ICW
LC | 123604509 | 022/111 | T3 DI RND MTN TBL MTN #2 22/111 COTR KEY | TABLEMTN | ETL.6070.INSL | 2022-05-16 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45457349 | T3 DI RND MTN TBL MTN #2 22/111 COTR KEY | ICS
LC | 123604797 | 025/367 | T3 DI GOLD HILL #1 25/367 RPL HRDD | SACTO | ETL.6950.POLE.NWOD | 2022-05-16 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123604995 | -016/004 | T3 DI FLTN CLSTG -16/4 RPL HRDD | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-16 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE ACCH OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45485891 | T3 DI FLTN CLSTG -16/4 RPL HRDD | ICW
LC | 123605163 | 011/001 | T3 DI MAPLE CREEK-HOOPA 11/1R RPR STRW | EUREKA | ETL.7490.POLE.WDPS | 2022-05-16 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123607403 | 015/006 | T3 DI MAPLE CREEK-HOOPA 15/6L RPL STRW | EUREKA | ETL.7490.POLE.WDPS | 2022-05-16 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace
LC | 123607451 | 017/005 | T3 EI UKH-HPLND-CLVRDL 017/005 RPR STRW | WILLITS | ETL.4050.POLE.WOOD | 2022-05-16 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45593091 | T3 EI UKH-HPLND-CLVRDL 017/005 RPR STRW | ICW
LC | 123607495 | 015/006 | T3 DI MAPLE CREEK-HOOPA 15/6R RPL STRW | EUREKA | ETL.7490.POLE.WDPS | 2022-05-16 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace
LC | 123607498 | 002/049 | T3 DI BRNS LN STR #2 2/49 RPL POLE | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-05-16 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31629518 | T3 DI BRNS LN STR #2 2/49 RPL POLE | 70Y
LC | 123607499 | 015/006 | T3 DI MAPLE CREEK-HOOPA 15/6C RPL STRW | EUREKA | ETL.7490.POLE.WDPS | 2022-05-16 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace
LC | 123607937 | -015/001 | T3 DI FULTON-CALISTOGA -15/1 RPR INSW | LAKEVLLE | ETL.6880.INSL.NCER | 2022-05-16 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45485897 | T3 DI FULTON-CALISTOGA -15/1 RPR INSW | ICW
LC | 123609889 | 002/040 | T3 DI KESWICK-TRINITY 2/40 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2022-05-16 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606079 | T3 DI KESWICK-TRINITY 0/13 RPL POLE | 70Y
LC | 123610174 | 003/004 | T3 DI BRIDGEVILLE-GARBERVL 3/4 RPL HRDD | EUREKA | ETL.6220.POLE.WOOD | 2022-05-16 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45451435 | T3 DI BRDGVLLE-GRBRVILLE 3/4 RPL HRDD | ICW
LC | 123611163 | 006/157 | T3 EI DRUM-SPAULDING 006/157 RPR INSW | SACTO | ETL.6770.INSL.NCER | 2022-05-16 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123613513 | 002/043 | T3 DI BURNS-LONE STAR #2 2/43 REFRAME | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-05-17 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31629519 | T2 DI BURNS-LONE STAR #2 5/114 REFRAME | 93E
LC | 123613951 | 025/112 | T3 DI EXCHQR INDN FLT 25/112 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2022-05-17 | 2022-04-22 |  | 2022-10-19 | 2022-10-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123614527 | 004/096 | T3 DI KILARC-CEDAR CRK 4/96 RPL STRW | TABLEMTN | ETL.7290.POLE.WOOD | 2022-05-17 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31617628 | T3 DI KILARC-CEDAR CRK 4/96 RPL STRW | 70Y
LC | 123614857 | 004/116 | T3 DI DEER CREEK-DRUM 4/116 INS IBWW | SACTO | ETL.6690.POLE.WOOD | 2022-05-17 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Replace
LC | 123615318 | 012/007C | T3 DI MAPLE CREEK-HOOPA 12/7C RPR CNDW | EUREKA | ETL.7490.INSL.CERA | 2022-05-17 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair
LC | 123616440 | 006/119 | T3 DI FRNCH MDWS MDL FRK 6/119 RPL PL | SACTO | ETL.6870.POLE.WOOD | 2022-05-17 | 2022-05-07 |  | 2022-11-03 | 2022-11-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606072 | T3 EI FRNCH MDWS-MDDLE FRK 0/2 RPL POLE | 70Y
LC | 123618141 | 016/170 | T3 EI IGNACIO-ALTO 16/170 RPL HRDW | LAKEVLLE | ETL.7150.INSL.NCER | 2022-05-17 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45576008 | T3 EI IGNACIO-ALTO 16/170 RPL HRDW | ICW
LC | 123618520 | 000/020 | T3 DI DEER CREEK-DRUM 0/20 RPL POLE | SACTO | ETL.6690.POLE.WOOD | 2022-05-17 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31627627 | T3 DI DEER CREEK-DRUM 0/20 RPL POLE | 70Y
LC | 123618646 | 016/240 | T3 DI GOLD HILL #1 16/240 RPL POLE | SACTO | ETL.6950.POLE.WOOD | 2022-05-17 | 2022-04-20 |  | 2022-10-17 | 2022-10-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCH OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31604014 | T3 DI GOLD HILL #1 16/240 RPL POLE | 70Y
LC | 123619042 | 011/001 | T3 EI MAPLE CREEK-HOOPA 11/001 COTR KEY | EUREKA | ETL.7490.INSL | 2022-05-17 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OH FMOB TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123619585 | 016/165 | T3 EI IGNACIO-ALTO 16/165 RMV VEG | LAKEVLLE | ETL.7150.POLE.WOOD | 2022-05-17 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Trim
LC | 123619953 | A001/007 | T3 DI SBRNT GRZY CLRNT #1 A1/7 RPR INSS | CONCORD | ETL.3740.INSL.CERA | 2022-05-17 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45513309 | T3 DI SBRNT GRZY CLRNT #1 A1/7 RPR INSS | ICS
LC | 123621836 | 016/082 | T3 DI MNT VIST-COYOTE SS 16/82 RPR SHLS | MOSSLNDG | ETL.5090.TOWR | 2022-05-17 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45606396 | T3 DI MNT VIST-COYOTE SS 16/82 RPR SHLS | ICS
LC | 123621844 | 012/316 | T3 DI COLGATE-ALLEGHANY 12/316 RPR POLE | SACTO | ETL.6470.POLE.WOOD | 2022-05-17 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123621940 | 021/108 | T3 DI RND MTN-TBL MTN #2 21/108 RMV VEG | TABLEMTN | ETL.6070.TOWR | 2022-05-17 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123621969 | 006/011 | T3 DI WSHN SN JQN #3 6/11 RMV BUTT | FRESNO | ETL.9340.POLE.NWOD | 2022-05-17 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCH OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove | 45489592 | T3 DI WSHN SN JQN #3 6/11 RMV BUTT | ICW
LC | 123622094 | 021/100 | T3 DI METCLF-MNT VIST #3 21/100 RPR INSS | MOSSLNDG | ETL.5091.INSL | 2022-05-17 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45606397 | T3 DI METCLF-MNT VIST #3 21/100 RPR INSS | ICS
LC | 123622177 | 021/108 | T3 DI RND MTN-TBL MTN#1 21/108 RMV NEST | TABLEMTN | ETL.6060.TOWR | 2022-05-17 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45458748 | T3 DI RND MTN-TBL MTN#1 21/108 RMV NEST | ICS
LC | 123622284 | 001/027 | T3 DI WST PNT-VLY SPRGS 001/027 RPR INSW | VICTOR | ETL.8350.INSL.CERA | 2022-05-17 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45532220 | T3 DI WST PNT-VLY SPRGS 001/027 RPR INSW | ICW
LC | 123622535 | 022/111 | T3 DI RD MTN-TBL MTN #1 22/111 RPR SHIED | TABLEMTN | ETL.6060.TOWR | 2022-05-17 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45458751 | T3 DI RD MTN-TBL MTN #1 22/111 RPR SHIED | ICS
LC | 123622622 | 021/110 | T3 DI RND MTN-TBL MTN #1 21/110 RPL ANCS | TABLEMTN | ETL.6060.TOWR | 2022-05-17 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Replace
LC | 123624049 | 006/003 | T3 DI WISHON-SAN JOAQUIN #3 6/3 COTTER | FRESNO | ETL.9340.INSL.CERA | 2022-05-18 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45489552 | T3 DI WISHON-SAN JOAQUIN #3 6/3 COTTER | ICW
LC | 123624409 | 005/020 | T3 DI DIABLO MIDWAY #3 5/20 RPR GYWS | PISMOBCH | ETL.5980.TOWR | 2022-05-18 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123624866 | 035/152 | T3 DI FULTON-LAKEVILLE 35/152 RPL INSS | LAKEVLLE | ETL.4950.INSL.CERA | 2022-05-18 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615951 | T2 DI FLTN-IGNCIO RPL INSS 6TWR | 93K
LC | 123625341 | 001/042 | T3 DI BRNS LN STR #2 1/42 RPL POLE | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-05-18 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31629518 | T3 DI BRNS LN STR #2 2/49 RPL POLE | 70Y
LC | 123625466 | 013/063 | T3 EI MSS LNDNG-MTCLF 13/63 RPR FOND | MOSSLNDG | ETL.6050.TOWR | 2022-05-18 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123625554 | 002/027 | T3 DI DRUM-SUMMIT #2 2/27 RPR WDPKR | SACTO | ETL.1450.POLE.WDPS | 2022-05-18 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123625782 | X004/022 | T3 DI DIABLO-MESA X004/22 RPR SHLS | PISMOBCH | ETL.4620.TOWR | 2022-05-18 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair
LC | 123626944 | 007/087 | T3 EI GRN VLLY-CAMP EVERS 7/87R RPL POLE | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-05-18 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31618524 | T3 EI GRN VLLY-CMP EVRS 12/117L RPL POLE | 70Y
LC | 123626969 | X004/020 | T3 DI MORRO BAY-DIABLO X4/20 RPR INSS | PISMOBCH | ETL.5260.INSL.CERA | 2022-05-18 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123627748 | 015/230 | T3 EI GOLD HILL #1 15/230 RPR SPLW | SACTO | ETL.6950.INSL.CERA | 2022-05-18 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 123628163 | 015/229 | T3 EI GOLD HILL #1 015/229 RPR INSW | SACTO | ETL.6950.INSL.CERA | 2022-05-18 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123628895 | 014/225 | T3 EI GOLD HILL #1 014/225 RPL STRW | SACTO | ETL.6950.POLE.WOOD | 2022-05-18 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606075 | T3 EI GOLD HILL #1 014/225 RPL STRW | 70Y
LC | 123629187 | 014/129 | T3 EI GRN VLLY-PAUL SWT 14/129 MASTIC | MOSSLNDG | ETL.1730.TOWR | 2022-05-18 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123629264 | 016/123 | T3 DI SLT SPRNGS TGR CRK 16/123 RPR STRT | VICTOR | ETL.3500.TOWR | 2022-05-18 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45591229 | T3 DI SLT SPRNGS TGR CRK 16/123 RPR STRT | ICQ
LC | 123629595 | B017/391 | T3 DI DRUM-GRASS VALLE B17/391 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2022-05-18 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31631449 | T2 EI DRUM-GRSS VLLY-WMR 18/427 RPL POLE | 70Y
LC | 123631520 | 007/082 | T3 DI DRM RIO OSO #1 007/082 RPR HRDT | SACTO | ETL.1420.TOWR | 2022-05-18 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | Missing | Hardware-Tower | Install | 45599993 | T3 DI DRM RIO OSO #1 007/082 RPR HRDT | ICQ
LC | 123631826 | 046/262 | T3 EI TEMBLR-SN LS OBISPO 046/262 UNBURY | PISMOBCH | ETL.3960.TOWR | 2022-05-18 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123631948 | 021/089 | T3 EI MORRO BY-SLR #1 21/89 RPL INSS | PISMOBCH | ETL.5300.INSL | 2022-05-18 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31618211 | T2 EI MRO BAY-SOLAR SS #1 RPL INSS 7TWR | 93K
LC | 123631949 | 021/089 | T3 EI MORO BY-SOLR SS #2 21/89 RPL INSS | PISMOBCH | ETL.5310.INSL | 2022-05-18 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619689 | MORRO BAY-SOLAR SW STA #2-REP INS 8 LSTS | 93K
LC | 123634358 | 025/100 | T3 DI DBL MDWY #3 25/100 RPR GYWS | PISMOBCH | ETL.5980.TOWR | 2022-05-19 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123635422 | 006/056 | T3 DI ATASCADERO-CAYUCOS 6/56 RPL HRDW | PISMOBCH | ETL.8480.POLE.WOOD | 2022-05-19 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45600534 | T3 DI ATASCADERO-CAYUCOS 6/56 RPL HRDW | ICW
LC | 123635425 | 006/056 | T3 DI ATASCADERO-CAYUCOS 6/56 RPR INSW | PISMOBCH | ETL.8480.INSL.NCER | 2022-05-19 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45600535 | T3 DI ATASCADERO-CAYUCOS 6/56 RPR INSW | ICW
LC | 123636953 | 006/031 | T3 MRRO BY-TMPLETON 006/031 RPR STRT | PISMOBCH | ETL.5933.TOWR | 2022-05-19 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW CREW OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Steel | Repair
LC | 123638372 | 005/104 | T3 EI BURNS-LONE STAR #2 5/104C RPR GYWW | MOSSLNDG | ETL.6240.POLE.STPS | 2022-05-19 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123638485 | 018/000 | T3 EI DONNELLS-MI-WUK 18/0 RPR POLE | VICTOR | ETL.1400.POLE.WDPS | 2022-05-19 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45519259 | T3 EI DONNELLS-MI-WUK 18/0 RPR POLE | ICW
LC | 123638811 | 005/007C | T3 EI DBLO UNT #2 TIE 005/007C RPL INSS | PISMOBCH | ETL.5950.INSL | 2022-05-19 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31629144 | T3 DI DIABLO UNIT#2 NF RPL INSS | 93K
LC | 123638861 | -014/004 | T3 EI FULTON-CALISTOGA -014/004 RPR GYWW | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-05-19 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45485881 | T3 EI FULTON-CALISTOGA -014/004 RPR GYWW | ICW
LC | 123638862 | -015/002 | T3 EI FULTON-CALISTOGA -015/002 RPR GYWW | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-19 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45485889 | T3 EI FULTON-CALISTOGA -015/002 RPR GYWW | ICW
LC | 123638863 | -015/000 | T3 EI FULTON-CALISTOGA 015/000 RPR INSW | LAKEVLLE | ETL.6880.INSL.CERA | 2022-05-19 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 45485883 | T3 EI FULTON-CALISTOGA 015/000 RPR INSW | ICW
LC | 123638961 | 005/007B | T3 EI DIABLO UNIT #2 5/7B RPL INSS | PISMOBCH | ETL.5950.INSL | 2022-05-19 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31629144 | T3 DI DIABLO UNIT#2 NF RPL INSS | 93K
LC | 123639369 | 010/249 | T3 DI DRUM-GRASS VALLEY 10/249 RPR WDPKR | SACTO | ETL.6760.POLE.WOOD | 2022-05-19 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123639472 | -016/000 | T3 DI FULTON-CALISTOGA -16/0 INS HRDD | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-19 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | Missing | Hardware-Wood | Install | 45485898 | T3 DI FULTON-CALISTOGA -16/0 INS HRDD | ICW
LC | 123639540 | B017/398 | T3 DI DRUM-GRASS VALLEY B17/398 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-05-19 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31631449 | T2 EI DRUM-GRSS VLLY-WMR 18/427 RPL POLE | 70Y
LC | 123639604 | 004/025 | T3 EI RND MTN-TBL MTN #2 4/25 BENT STEEL | TABLEMTN | ETL.6070.TOWR | 2022-05-19 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45457352 | T3 EI RND MTN-TBL MTN #2 4/25 BENT STEEL | ICS
LC | 123639975 | 000/001A | T3 DI DBL PP STNBY SPL 0/1A RPR FOND | PISMOBCH | ETL.4610.POLE.NWOD | 2022-05-19 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123640170 | 000/001A | T3 DI DBL PP STNBY SPL 0/1A RPR GYWS | PISMOBCH | ETL.4610.POLE.NWOD | 2022-05-19 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123640174 | 000/001A | T3 DI DBL PP STNBY SPL 0/1A RPL ANCS | PISMOBCH | ETL.4610.POLE.NWOD | 2022-05-19 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Replace
LC | 123640426 | 017/072 | T3 DI DIABLO-GATES #1 17/72 RPR SHLS | PISMOBCH | ETL.5960.TOWR | 2022-05-19 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45583567 | T3 DI DIABLO-GATES #1 17/72 RPR SHLS | ICS
LC | 123640775 | 005/007A | T3 EI DIABLO UNIT #2 5/7A RPL INSS | PISMOBCH | ETL.5950.INSL | 2022-05-19 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31629144 | T3 DI DIABLO UNIT#2 NF RPL INSS | 93K
LC | 123641230 | 014/374 | T3 DI COLGATE-ALLEGHANY 14/374 RPR INSW | SACTO | ETL.6470.INSL.NCER | 2022-05-19 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123641565 | 012/111 | T3 EI GRN VLLY-PL SWT 12/111L RPL POLE | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-05-19 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31629564 | T3 DI GRN VLY-PAUL SWT 10/100 RPL STRW | 70Y
LC | 123641575 | 012/111 | T3 EI GRN VLLY-PL SWT 12/111R RPL POLE | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-05-19 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31629564 | T3 DI GRN VLY-PAUL SWT 10/100 RPL STRW | 70Y
LC | 123641676 | 012/111 | T3 EI GRN VLLY-PL SWT 12/111C RPL POLE | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-05-19 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31629564 | T3 DI GRN VLY-PAUL SWT 10/100 RPL STRW | 70Y
LC | 123641743 | 010/153 | T3 WEIMAR #1 10/153 RPL HRDD | SACTO | ETL.7560.POLE.WOOD | 2022-05-19 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW PATR OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123642415 | 012/001 | T3 DI MAPLE CREEK-HOOPA 12/1 RPL HRDW | EUREKA | ETL.7490.POLE.WOOD | 2022-05-19 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123642451 | B021/465 | T3 DI DRUM-GRASS VALLEY B21/465 RPR INSW | SACTO | ETL.6760.INSL.NCER | 2022-05-19 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123643936 | 005/133 | T3 DI COLGATE-GRSS VALLEY 5/133 RPR STRW | SACTO | ETL.6490.POLE.WOOD | 2022-05-19 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123643979 | 018/488 | T3 DI COLGATE-ALLEGHANY 18/488 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-05-19 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31633603 | T3 DI COLGATE-ALLEGHANY 18/488 RPL POLE | 70Y
LC | 123644194 | 018/000B | T3 DI OAKHURST TAP 018/000B RPR ANCW | FRESNO | ETL.1252.POLE.NWOD | 2022-05-19 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45489330 | T3 DI OAKHURST TAP 018/000B RPR ANCW | ICW
LC | 123644196 | 018/000 | T3 DI OAKHURST TAP 018/000 RPR ANCW | FRESNO | ETL.1252.POLE.NWOD | 2022-05-19 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45489332 | T3 DI OAKHURST TAP 018/000 RPR ANCW | ICW
LC | 123644384 | 023/625 | T3 DI COLGATE-ALLEGHANY 23/625 RPR POLE | SACTO | ETL.6470.POLE.WOOD | 2022-05-19 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123646407 | :006/029 | T3 DI GEYSERS #9-LAKEVILL :6/29 RPR INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2022-05-20 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575556 | T3 DI GEYSERS #9-LAKEVILL :6/29 RPR INSS | ICS
LC | 123646484 | 013/053 | T3 DI GEYSERS #12-FULTON 13/53 RMV VEG | LAKEVLLE | ETL.4750.TOWR | 2022-05-20 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE ACCM OH TR3 PRTO AIR FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123646485 | 013/053 | T3 DI GEYSERS #12-FULTON 13/53 RPR INSS | LAKEVLLE | ETL.4750.INSL.NCER | 2022-05-20 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123646543 | 027/002 | T3 EI FULTON-HOPLAND 027/002 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2022-05-20 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45571471 | T3 EI FULTON-HOPLAND 027/002 RPR STRW | ICW
LC | 123646557 | 007/188 | T3 COLGATE-ALLEGHANY 7/188 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-05-20 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW PATR OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31606404 | T3 COLGATE-ALLEGHANY 7/188 RPL POLE | 70Y
LC | 123646683 | 015/415 | T3 DI CLGT-ALLGHNY 15/415 INST HRDD | SACTO | ETL.6470.POLE.WOOD | 2022-05-20 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | Missing | Hardware-Wood | Install
LC | 123646823 | 016/127 | T3 DI SLT-SPRNGS-TGR CRK 16/127 COTTER | VICTOR | ETL.3500.INSL.NCER | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45519301 | T3 DI SLT-SPRNGS-TGR CRK 16/127 COTTER | ICS
LC | 123646936 | 002/030 | T3 DI DRUM-SUMMIT #1 2/30 RPL HRDW | SACTO | ETL.1440.POLE.WDPS | 2022-05-20 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123647019 | 003/018 | T3 DI GEYSERS #12-FULTON 3/18 RPL INSS | LAKEVLLE | ETL.4750.INSL.NCER | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615952 | T3 DI GEYSERS #12-FULTON RPL INSS 4TWR | 93K
LC | 123647101 | 003/018 | T3 DI GEYSERS #12-FULTON 3/18 RPR STRT | LAKEVLLE | ETL.4750.TOWR | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123647190 | 013/342 | T3 DI CLGTE-ALLEGHNY 13/342 RPR POLE | SACTO | ETL.6470.POLE.WOOD | 2022-05-20 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123647194 | 016/126 | T3 DI SLT SPRINGS-TIGER CRK 16/12 COTTER | VICTOR | ETL.3500.INSL.NCER | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45519302 | T3 DI SLT SPRINGS-TIGER CRK 16/12 COTTER | ICS
LC | 123647308 | 012/003 | T3 DI MAPLE CREEK-HOOPA 12/3 RPR CRSW | EUREKA | ETL.7490.POLE.WOOD | 2022-05-20 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair
LC | 123647400 | 003/016 | T3 DI GEYSERS #9-LAKEVILLE 3/16 RPR INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575558 | T3 DI GEYSERS #9-LAKEVILLE 3/16 RPR INSS | ICS
LC | 123647467 | 005/029 | T3 EI RND MTN-TABL MTN #2 5/29 BNT STEEL | TABLEMTN | ETL.6070.TOWR | 2022-05-20 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123647569 | 000/000 | T3 DI WISHON-COPPERMINE 0/0 UNBURY | FRESNO | ETL.9330.TOWR | 2022-05-20 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45616732 | T3 DI WISHON-COPPERMINE 0/0 UNBURY | ICQ
LC | 123647731 | Z012/005 | T3 DI FULTON-CALISTOGA Z12/5 RPL HRDT | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-05-20 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123647741 | :003/015 | T3 DI EAGLE ROCK-FULTON :3/15 RPR INSS | LAKEVLLE | ETL.4392.INSL.NCER | 2022-05-20 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123648334 | B021/466 | T3 DI DRM-GRS VLY-WMR B21/466 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31617789 | T2 EI DRM GRS VALEY WMR B20/450 RPL STRW | 70Y
LC | 123648337 | 003/070 | T3 DI BURNS-LONE STAR #2 3/70 RPL HRDW | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-05-20 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45616379 | T3 DI BURNS-LONE STAR #2 3/70 RPL HRDW | ICW
LC | 123648541 | 019/516 | T3 DI CLGT-ALLGHNY 19/516 RMV DEBRIS | SACTO | ETL.6470.POLE.NWOD | 2022-05-20 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123648568 | 000/012 | T3 DI FRNCH MDWS-MID FRK 0/12 REGRADE | SACTO | ETL.6870.POLE.NWOD | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123648569 | 000/012 | T3 DI FRNCH MDWS-MID FRK 0/12 RPL HRDW | SACTO | ETL.6870.POLE.NWOD | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123648652 | 000/007 | T3 DI RND MTN-TBLE MTN #2 0/7 COTTER | TABLEMTN | ETL.6070.INSL | 2022-05-20 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45457354 | T3 DI RND MTN-TBLE MTN #2 0/7 COTTER | ICS
LC | 123648674 | 006/012 | T3 DI WISHN-SN JOAQN #3 6/12 RPR INSW | FRESNO | ETL.9340.INSL.NCER | 2022-05-20 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45489580 | T3 DI WISHN-SN JOAQN #3 6/12 RPR INSW | ICW
LC | 123648678 | 006/012 | T3 DI WISHN-SN JOAQN #3 6/12 RPL HRDD | FRESNO | ETL.9340.POLE.NWOD | 2022-05-20 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45489599 | T3 DI WISHN-SN JOAQN #3 6/12 RPL HRDD | ICW
LC | 123648745 | 005/030 | T3 EI RND MTN-TBLE MTN #2 5/30 RPR STRS | TABLEMTN | ETL.6070.TOWR | 2022-05-20 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP PATR OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45457356 | T3 EI RND MTN-TBLE MTN #2 5/30 RPR STRS | ICS
LC | 123649125 | 003/017 | T3 DI GEYSERS #12-FULTON 3/17 RPR INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123649220 | 003/017 | T3 DI GEYSERS #12-FULTON 3/17 RPR INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123649313 | 013/117B | T3 DI GRN VLLY-PL SWT 13/117B RPR ANCW | MOSSLNDG | ETL.1730.POLE.NWOD | 2022-05-20 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair | 45616645 | T3 DI GRN VLLY-PL SWT 13/117B RPR ANCW | ICW
LC | 123649319 | 001/010 | T3 DI EGL RCK-FLTN-SLVRDO 1/10 RPR STRW | LAKEVLLE | ETL.4392.TOWR | 2022-05-20 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123649412 | 001/010 | T3 DI GEYSERS #17-FULTON 1/10 RPR INSS | LAKEVLLE | ETL.4770.INSL.CERA | 2022-05-20 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571487 | T3 DI GEYSERS #17-FULTON 1/10 RPR INSS | ICS
LC | 123649418 | 001/010 | T3 DI GEYSERS #17-FULTON 1/10 RPL DMPS | LAKEVLLE | ETL.4770.INSL.CERA | 2022-05-20 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace
LC | 123649590 | 004/048 | T3 DI DRUM-RIO OSO #1 4/48 INS STEP | SACTO | ETL.1420.TOWR | 2022-05-20 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45599418 | T3 DI DRUM-RIO OSO #1 4/48 INS STEP | ICQ
LC | 123649716 | 014/375 | T3 DI COLGATE-ALLGHNY 014/375 REFRAME | SACTO | ETL.6470.INSL.NCER | 2022-05-20 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31618165 | T3 DI COLGATE-ALLGHNY 13/361 REFRAME | 93I
LC | 123649832 | B022/495 | T3 DI DRM-GRS VLY-WMR B22/495 RPL INSW | SACTO | ETL.6760.INSL.NCER | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617793 | T2 DI DRM-GRS VLLY-WIMR B18/418 RPL INSW | 93I
LC | 123649835 | B022/495 | T3 DI DRM-GRS VLY-WMR B22/495 RPL HRDD | SACTO | ETL.6760.POLE.WOOD | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123649954 | 009/166 | T3 DI COLGATE-CHALLENGE 9/166 RPR INSW | SACTO | ETL.6480.INSL.NCER | 2022-05-20 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123650259 | 001/029 | T3 DI BURNS-LONE STAR #2 1/29 INS HRDW | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-05-20 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45616647 | T3 DI BURNS-LONE STAR #2 1/29 INS HRDW | ICW
LC | 123650311 | 001/029 | T3 DI BURNS-LONE STAR #2 1/29 RPR SPLW | MOSSLNDG | ETL.6240.INSL.NCER | 2022-05-20 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45616648 | T3 DI BURNS-LONE STAR #2 1/29 RPR SPLW | ICW
LC | 123650440 | 004/049 | T3 DI DRUM-RIO OSO #2 004/049 RPR INSS | SACTO | ETL.1430.INSL.NCER | 2022-05-20 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123650594 | 009/041 | T3 DI MRG CSTR VLY 9/41 RPR OPGW | CONCORD | ETL.5250.TOWR | 2022-05-20 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45502876 | T3 DI MRG CSTR VLY 9/41 RPR OPGW | ICS
LC | 123650679 | 005/025 | T3 DI MRGA-CASTRO VLY 005/025 RPL HRDT | CONCORD | ETL.5250.TOWR | 2022-05-20 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123650751 | -013/006 | T3 EI FLTN-CALITG -13/006 REPUL GYWW | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-20 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45450251 | T3 EI FLTN-CALITG -13/006 REPUL GYWW | ICW
LC | 123650873 | 031/134 | T3 DI FULTON-IGNACIO #1 14/75 RPR INSS | LAKEVLLE | ETL.4780.INSL | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571455 | T3 DI FULTON-IGNACIO #1 14/75 RPR INSS | ICS
LC | 123650874 | 031/134 | T3 DI FLTN-LKVLL-IGNCO 31/134 RPR INSS | LAKEVLLE | ETL.4950.INSL.CERA | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575476 | T3 DI FLTN-LKVLL-IGNCO 31/134 RPR INSS | ICS
LC | 123651253 | 017/484 | T3 DI COLGATE-ALLGHNY 17/484 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-05-20 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31605566 | HANY 15/402 RPL POLE | 70Y
LC | 123651743 | 018/506 | T3 DI COLGATE-ALLGHNY 18/506 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-05-20 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31633603 | T3 DI COLGATE-ALLEGHANY 18/488 RPL POLE | 70Y
LC | 123651868 | 001/011 | T3 DI RND MTN-TBLE MTN #1 1/11 INS DMPS | TABLEMTN | ETL.6060.INSL | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | Missing | Damper-Steel | Install | 45315465 | T3 DI RND MTN-TBLE MTN #1 1/11 INS DMPS | ICS
LC | 123652408 | B022/487 | T3 DI DRM-GRS VLY-WEMR B22/487 RPL INSW | SACTO | ETL.6760.INSL.NCER | 2022-05-20 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617793 | T2 DI DRM-GRS VLLY-WIMR B18/418 RPL INSW | 93I
LC | 123652582 | 004/085 | T3 DI CLGT-CHLLNG 4/085 RPL HRDW | SACTO | ETL.6480.POLE.WOOD | 2022-05-20 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123652809 | 017/117 | T3 EI ROCK CREEK-PO 17/117 RPR FOND | TABLEMTN | ETL.5630.TOWR | 2022-05-20 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123652821 | 016/112 | T3 EI ROCK CREEK-POE 16/112 REFRAME | TABLEMTN | ETL.5630.POLE.STPS | 2022-05-20 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Crossarm-Steel | Replace
LC | 123652825 | 016/111 | T3 EI ROCK CREEK-POE 16/111 REFRAME | TABLEMTN | ETL.5630.POLE.STPS | 2022-05-20 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Crossarm-Steel | Replace
LC | 123653086 | 031/136 | T3 DI FLTN LKVL-IGNC-LKVL 031/136 COTTER | LAKEVLLE | ETL.2823.INSL.CERA | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575468 | T3 DI FLTN LKVL-IGNC-LKVL 031/136 COTTER | ICS
LC | 123653089 | 031/136 | T3 DI FLTN-LKVL-IGNC+ 031/136 RPL INSS | LAKEVLLE | ETL.4950.INSL.CERA | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615951 | T2 DI FLTN-IGNCIO RPL INSS 6TWR | 93K
LC | 123653183 | 031/136 | T3 DI GEYSERS #9-LAKEVILLE 31/136 COTTER | LAKEVLLE | ETL.4780.INSL | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575559 | T3 DI GEYSERS #9-LAKEVILLE 31/136 COTTER | ICS
LC | 123653613 | 012/113 | T3 EI GRN VLLY-PL SWT 12/113 WASH INSW | MOSSLNDG | ETL.1730.INSL.CERA | 2022-05-20 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 622 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | Contaminated | Insulator | Ground Wash | 45616655 | T3 EI GRN VLLY-PL SWT 12/113 WASH INSW | ICD
LC | 123653801 | 002/023 | T3 DI DRUM-SUMMIT #1 002/023 RPL HRDW | SACTO | ETL.1440.POLE.STPS | 2022-05-20 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123654239 | 011/008 | T3 DI LAURELES-OTTER 11/8 RPL HRDD | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-20 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123654300 | 024/661 | T3 DI CLGT ALGHNY 24/661 INS HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-05-20 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123654533 | 024/654 | T3 DI CLGT ALGHNY 24/654 INS HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-05-20 | 2022-04-29 |  | 2022-10-26 | 2022-10-29 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123654690 | 005/048 | T3 DI MONTA VST-BRNS 5/48 RPL HRDW | MOSSLNDG | ETL.7590.POLE.WOOD | 2022-05-20 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45616656 | T3 DI MONTA VST-BRNS 5/48 RPL HRDW | ICW
LC | 123654691 | 005/048 | T3 DI MONTA VSTA-BRNS 5/48 RPR INSW | MOSSLNDG | ETL.7590.INSL | 2022-05-20 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45616657 | T3 DI MONTA VSTA-BRNS 5/48 RPR INSW | ICW
LC | 123654698 | 000/001 | T3 DI MORAGA-SAN LEANDRO #1 0/1 RPL INSS | CONCORD | ETL.2770.INSL | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617656 | T3 DI MORAGA-SAN LEANDRO #1 RPL INSS 6T | 93K
LC | 123654730 | 000/001 | T3 DI MORGA-SAN LEANDRO #1 0/1 BNT STEEL | CONCORD | ETL.2770.TOWR | 2022-05-20 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123654787 | 006/037 | T3 EI RD MTN-TBL MTN #2 006/037 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2022-05-20 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123656874 | 013/120 | T3 EI GRN VLLY-PAUL SWT 13/120L RPL POLE | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-05-21 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31629564 | T3 DI GRN VLY-PAUL SWT 10/100 RPL STRW | 70Y
LC | 123656967 | 013/120 | T3 EI GRN VLLY-PAUL SWT 13/120R RPL POLE | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-05-21 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31629564 | T3 DI GRN VLY-PAUL SWT 10/100 RPL STRW | 70Y
LC | 123657078 | 016/000 | T3 EI DONNELLS-MI-WUK 16/0L RPR STRW | VICTOR | ETL.1400.POLE.WDPS | 2022-05-21 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45519304 | T3 EI DONNELLS-MI-WUK 16/0L RPR STRW | ICW
LC | 123657109 | 016/000 | T3 EI DONNELLS-MI-WUK 16/0R RPR STRW | VICTOR | ETL.1400.POLE.WDPS | 2022-05-21 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45519305 | T3 EI DONNELLS-MI-WUK 16/0R RPR STRW | ICW
LC | 123657795 | 004/049 | T3 DI IGNACIO BOLINAS #1 4/49 RPL HRDD | LAKEVLLE | ETL.7140.POLE.WOOD | 2022-05-21 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45486001 | T3 DI IGNACIO BOLINAS #1 4/49 RPL HRDD | ICW
LC | 123658019 | 010/052 | T3 DI MONTA VIST-COYOT SS 10/52 RPR SHLS | MOSSLNDG | ETL.5090.TOWR | 2022-05-21 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45581164 | T3 DI MONTA VIST-COYOT SS 10/52 RPR SHLS | ICS
LC | 123658401 | 010/052 | T3 DI MONT VSTA-CYT SS 10/52 RPR INSS | MOSSLNDG | ETL.5090.INSL | 2022-05-21 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45581165 | T3 DI MONT VSTA-CYT SS 10/52 RPR INSS | ICS
LC | 123658532 | 000/016 | T3 EI FRNCH MDOWS-MDLE FRK 0/16 REFRAME | SACTO | ETL.6870.POLE.WOOD | 2022-05-21 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31633859 | T3 EI FRNCH MDOWS-MDLE FRK 0/16 REFRAME | 93E
LC | 123658551 | 010/094 | T3 DI DRUM HIGGINS 10/94 RPR STRS | SACTO | ETL.4393.TOWR | 2022-05-21 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45599182 | T3 DI DRUM HIGGINS 10/94 RPR STRS | ICQ
LC | 123658865 | 000/001 | T3 DI MORAGA-OAKLAND #4 0/1 RPL INSS | CONCORD | ETL.2750.INSL.CERA | 2022-05-21 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31625441 | T3 DI MORAGA-OAKLAND #4 0/1 RPL INSS | 93K
LC | 123658867 | 000/001 | T3 DI MORAGA-OAKLAND #3 0/1 RPL INSS | CONCORD | ETL.2740.INSL.CERA | 2022-05-21 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31625440 | T3 DI MORAGA-OAKLAND #3 0/1 RPL INSS | 93K
LC | 123658930 | 000/001 | T3 DI MORAGA-OAKLAND #3 0/1 RPR STRT | CONCORD | ETL.2740.TOWR | 2022-05-21 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123659166 | 004/005 | T3 EI DONNELLS-MI-WUK 4/5 RPR WDPKR | VICTOR | ETL.1400.POLE.WDPS | 2022-05-21 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45519306 | T3 EI DONNELLS-MI-WUK 4/5 RPR WDPKR | ICW
LC | 123659230 | 001/031 | T3 EI FRNCH MDOWS-MDLE FRK 1/31 RPR STRW | SACTO | ETL.6870.POLE.WOOD | 2022-05-21 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123659231 | 001/030 | T3 EI FRNCH MDOS-MDLE FORK 1/30 REFRAME | SACTO | ETL.6870.POLE.WOOD | 2022-05-21 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31617970 | T3 EI FRNCH MDOS-MDLE FORK 1/30 REFRAME | 93E
LC | 123659261 | 009/040 | T3 DI GEYSERS #17-FULTN 9/40 RPR INSS | LAKEVLLE | ETL.4770.INSL.CERA | 2022-05-21 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575546 | T3 DI GEYSERS #17-FULTN 9/40 RPR INSS | ICS
LC | 123659269 | 002/061 | T3 DI DEER CREEK-DRUM 002/061 RPL STRW | SACTO | ETL.6690.POLE.WOOD | 2022-05-21 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31612271 | T3 EI DEER CREEK-DRUM 2/56 RPL POLE | 70Y
LC | 123660161 | 011/057 | T3 EI MNTA VSTA-CYTE SS 11/57 RPR FOND | MOSSLNDG | ETL.5090.TOWR | 2022-05-21 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123660251 | 017/118 | T3 EI ROCK CREEK-POE 17/118 RMV NEST | TABLEMTN | ETL.5630.TOWR | 2022-05-21 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove
LC | 123660262 | 001/010 | T3 DI GEYSERS #13 TAP 1/10 RPR INSS | LAKEVLLE | ETL.4781.INSL | 2022-05-21 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575541 | T3 DI GEYSERS #13 TAP 1/10 RPR INSS | ICS
LC | 123660424 | 010/184 | T3 EI COLGATE-CHALLENGE 10/184 RPR INSW | SACTO | ETL.6480.INSL.NCER | 2022-05-21 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123660442 | 010/172 | T3 EI CLGTE-CHLLNG 10/172 RPR INSW | SACTO | ETL.6480.INSL.NCER | 2022-05-21 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123660443 | 010/174 | T3 EI CLGTE-CHLLNGE 10/174 RPUL GYWW | SACTO | ETL.6480.POLE.NWOD | 2022-05-21 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123661768 | :010/001 | T3 EI FULTON-CALISTOGA :010/001 RPR GYWW | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-05-22 | 2022-05-22 |  | 2022-11-18 | 2022-11-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP PGEA OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123662874 | 014/000 | T3 EI DONNELLS-MI-WUK 14/0L RPR POLE | VICTOR | ETL.1400.POLE.WDPS | 2022-05-22 | 2022-05-22 |  | 2022-11-18 | 2022-11-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45519307 | T3 EI DONNELLS-MI-WUK 14/0L RPR POLE | ICW
LC | 123663340 | 002/007 | T3 EI FULTON-CALISTOGA 002/007 RPR GYWW | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-05-22 | 2022-05-22 |  | 2022-11-18 | 2022-11-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123663882 | :007/007 | T3 EI FULTON-CALISTOGA :007/007 RPL INSW | LAKEVLLE | ETL.6880.INSL.NCER | 2022-05-22 | 2022-05-22 |  | 2022-11-18 | 2022-11-22 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP PGEA OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31620118 | T3 DI FLTN-CLSTGA :001/001 RPL INSW | 93I
LC | 123666594 | 006/005 | T3 EI DONNELLS-MI-WUK 6/5 RPR WDPKR | VICTOR | ETL.1400.POLE.WDPS | 2022-05-23 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45519308 | T3 EI DONNELLS-MI-WUK 6/5 RPR WDPKR | ICW
LC | 123666683 | 012/007 | T3 EI MONTE RIO-FULTON 12/7 RPR STRW | LAKEVLLE | ETL.7630.POLE.WOOD | 2022-05-23 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45571473 | T3 EI MONTE RIO-FULTON 12/7 RPR STRW | ICW
LC | 123666714 | 003/020 | T3 DI GEYSERS #9-LAKEVILLE 3/20 COTTER | LAKEVLLE | ETL.4780.INSL.NCER | 2022-05-23 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45467297 | T3 DI GEYSERS #9-LAKEVILLE 3/20 COTTER | ICS
LC | 123666718 | 003/020 | T3 DI GYSRS # 12-FULTON 3/20 RPR INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2022-05-23 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45467298 | T3 DI GYSRS # 12-FULTON 3/20 RPR INSS | ICS
LC | 123667073 | 008/064 | T3 EI GREEN VALLEY-LLAGAS 8/64R RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-05-23 | 2022-05-07 |  | 2022-11-03 | 2022-11-07 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31611564 | T3 EI GREEN VALLEY-LLAGAS 8/64L RPL POLE | 70Y
LC | 123667208 | 006/051 | T3 EI GREEN VALLEY-LLAGAS 6/51R RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-05-23 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31610973 | T3 DI GREEN VALLEY-LLAGAS 5/42R RPL POLE | 70Y
LC | 123667271 | 006/051 | T3 EI GREEN VALLEY-LLAGAS 6/51C RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-05-23 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31610973 | T3 DI GREEN VALLEY-LLAGAS 5/42R RPL POLE | 70Y
LC | 123667321 | 006/050 | T3 EI GREEN VALLEY-LLAGAS 6/50R RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2022-05-23 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31610973 | T3 DI GREEN VALLEY-LLAGAS 5/42R RPL POLE | 70Y
LC | 123667555 | 037/191B | T3 DI RINCON #1 TAP 37/191B RPL HRDT | LAKEVLLE | ETL.1601.TOWR | 2022-05-23 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL COMP OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45617364 | T3 DI RINCON #1 TAP 37/191B RPL HRDT | ICQ
LC | 123668961 | :007/001 | T3 EI FLTN-CLSTGA :007/003 RMV VEG | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-23 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP PGEA OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123669834 | 007/004 | T3 EI DONNELLS-MI-WUK 7/4L RPR POLE | VICTOR | ETL.1400.POLE.WDPS | 2022-05-23 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45519309 | T3 EI DONNELLS-MI-WUK 7/4L RPR POLE | ICW
LC | 123669838 | 007/004 | T3 EI DONNELLS-MI-WUK 7/4R RPR POLE | VICTOR | ETL.1400.POLE.WDPS | 2022-05-23 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45519310 | T3 EI DONNELLS-MI-WUK 7/4R RPR POLE | ICW
LC | 123669992 | X002/014 | T3 DI DIABLO-MESA X2/14 COTTER | PISMOBCH | ETL.4620.INSL.CERA | 2022-05-23 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123670142 | X000/001 | T3 DI DIABLO-MESA X0/1 RPL INSS | PISMOBCH | ETL.4620.INSL.CERA | 2022-05-23 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31601767 | T2 EI DIABLO-MESA RPL INSS 3TWR | 93K
LC | 123670390 | 000/003 | T3 DI FRNCH MDWS-MDL FRK 0/3 RPR GYWW | SACTO | ETL.6870.POLE.WOOD | 2022-05-23 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123670721 | 002/034 | T3 DI WST PNT VLY SPRNGS 2/34 RPR INSW | VICTOR | ETL.8350.INSL.CERA | 2022-05-23 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45531614 | T3 DI WST PNT VLY SPRNGS 2/34 RPR INSW | ICW
LC | 123671470 | X003/016 | T3 DI DIABLO-MESA X3/16 RPR INSS | PISMOBCH | ETL.4620.INSL.CERA | 2022-05-23 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123671574 | X001/008 | T3 DI DIABLO-MESA X1/8 RPR INSS | PISMOBCH | ETL.4620.INSL.CERA | 2022-05-23 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123672358 | 010/000 | T3 EI MENDOCINO-WLITS-FRT 10/0 RPR STRW | WILLITS | ETL.7550.POLE.WDPS | 2022-05-23 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45640365 | T3 EI MENDOCINO-WLITS-FRT 10/0 RPR STRW | ICW
LC | 123672376 | 005/000 | T3 EI FULTON-CALISTOGA 5/0 RMV STEP | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-05-23 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAR NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123672394 | 012/003 | T3 EI DONNELLS-MI-WUK 12/3L RPL HRDW | VICTOR | ETL.1400.POLE.WDPS | 2022-05-23 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45519311 | T3 EI DONNELLS-MI-WUK 12/3L RPL HRDW | ICW
LC | 123672412 | 012/005 | T3 EI DONNELLS-MI-WUK 12/5L RPR POLE | VICTOR | ETL.1400.POLE.WDPS | 2022-05-23 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair | 45519312 | T3 EI DONNELLS-MI-WUK 12/5L RPR POLE | ICW
LC | 123672651 | 005/123 | T3 DI DRUM-SPAULDING 5/123 RPR INSW | SACTO | ETL.6770.INSL.NCER | 2022-05-23 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123672706 | 005/117 | T3 DI DRUM-SPAULDING 5/117 RPR INSW | SACTO | ETL.6770.INSL.NCER | 2022-05-23 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123673224 | 000/014 | T3 DI FRNCH MDOWS-MDDL FRK 0/14 RPR POLE | SACTO | ETL.6870.POLE.NWOD | 2022-05-23 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123673445 | 005/139 | T3 DI DRUM-SPAULDING 5/139 BACKFILL | SACTO | ETL.6770.POLE.NWOD | 2022-05-23 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123673565 | 004/053 | T3 DI DRUM-RIO OSO #2 4/53 RPR STRT | SACTO | ETL.1430.TOWR | 2022-05-23 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45600064 | T3 DI DRUM-RIO OSO #2 4/53 RPR STRT | ICQ
LC | 123673596 | 021/316 | T3 DI GOLD HILL #1 021/316 INS HRDD | SACTO | ETL.6950.POLE.NWOD | 2022-05-23 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123673650 | 022/335 | T3 DI GOLD HILL #1 22/335 RMV BUTT | SACTO | ETL.6950.POLE.NWOD | 2022-05-23 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3N PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123673781 | B023/509 | T3 DI DRM-GRS VLY-WMR B23/509 RPL HRDD | SACTO | ETL.6760.POLE.WOOD | 2022-05-23 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123673889 | 006/003 | T3 DI LAURELES-OTTER-WD PL6/3 HRDW RPL | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-23 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45376641 | T3 DI LAURELES-OTTER-WD PL6/3 HRDW RPL | ICW
LC | 123673959 | 015/079 | T3 DI FULTON-IGNACIO #1 32/138 RPL INSS | LAKEVLLE | ETL.4680.INSL | 2022-05-23 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615951 | T2 DI FLTN-IGNCIO RPL INSS 6TWR | 93K
LC | 123674022 | 002/062 | T3 DI DRUM-SPAULDING 2/62 RPR POLE | SACTO | ETL.6770.POLE.NWOD | 2022-05-23 | 2022-04-30 |  | 2022-10-27 | 2022-10-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123674030 | B022/488 | T3 DI DRM-GRS VLY-WMR B022/488 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2022-05-23 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606069 | T3 EI DRM-GRS VLY-WMR B017/401 RPL STRW | 70Y
LC | 123674052 | 000/019 | T3 DI FRNCH MDOWS-MDDL FK 0/019 RPL HRDD | SACTO | ETL.6870.POLE.WOOD | 2022-05-23 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123674059 | 000/019 | T3 DI FRNCH MDOWS-MDDL FK 0/019 RPR INSW | SACTO | ETL.6870.INSL | 2022-05-23 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123674080 | 029/241 | T3 DI PIT #1-COTTONWOOD 29/241 RPR GYWS | TABLEMTN | ETL.5390.TOWR | 2022-05-23 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123674081 | 029/241 | T3 DI PIT #1-COTTONWOOD 29/241 RPR ANCS | TABLEMTN | ETL.5390.TOWR | 2022-05-23 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair
LC | 123674102 | 004/029 | T3 DI BRUNSWICK #1 TAP 4/29 RPL HRDT | SACTO | ETL.1422.TOWR | 2022-05-23 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCH OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45582379 | T3 DI BRUNSWICK #1 TAP 4/29 RPL HRDT | ICQ
LC | 123674158 | 005/061 | T3 DI DRUM-RIO OSO #1 05/61 COTTER | SACTO | ETL.1420.INSL.CERA | 2022-05-23 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123674234 | -014/001 | T3 DI FULTON-CALISTOGA -014/001 RPL HRDW | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-23 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45485892 | T3 DI FULTON-CALISTOGA -014/001 RPL HRDW | ICW
LC | 123674274 | 018/272 | T3 DI GOLD HILL #1 18/272 RPR STRW | SACTO | ETL.6950.POLE.NWOD | 2022-05-23 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123674277 | 005/144 | T3 DI DRUM-GRASS VALLEY 5/144 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2022-05-23 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123674278 | 003/007 | T3 DI BRIDGEVILLE-GARBERVL 3/7 RPR HRDW | EUREKA | ETL.6220.POLE.WOOD | 2022-05-23 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45451436 | T3 DI BRIDGEVLLE-GARBERVLLE 3/7 RPR HRDW | ICW
LC | 123674538 | 003/041 | T3 DI WP-VALLEY SPRINGS 03/41 INS HRDD | VICTOR | ETL.8350.POLE.WOOD | 2022-05-23 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45531616 | T3 DI WP-VALLEY SPRINGS 03/41 INS HRDD | ICW
LC | 123674794 | 000/004 | T3 DI ROLLINS TAP 0/4 RPL HRDW | SACTO | ETL.6762.POLE.WOOD | 2022-05-23 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123674976 | 005/060 | T3 DI DRUM-RIO OSO #2 5/60 RPR JMPS | SACTO | ETL.1430.INSL | 2022-05-23 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Steel | Repair
LC | 123674980 | 003/086 | T3 DI BURNS-LONE STAR #2 3/86 RPR SPLW | MOSSLNDG | ETL.6240.INSL.NCER | 2022-05-23 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45616745 | T3 DI BURNS-LONE STAR #2 3/86 RPR SPLW | ICW
LC | 123674981 | 005/125 | T3 DI DRUM-SPAULDING 5/125 RPR INSW | SACTO | ETL.6770.INSL.NCER | 2022-05-23 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123676541 | B022/496 | T3 DI DRM-GRS VLY-WMR B22/496 RPR SPLW | SACTO | ETL.6760.INSL.NCER | 2022-05-24 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 123676544 | 004/047 | T3 DI IGNACIO-BOLINAS #1 4/47 RPR INSW | LAKEVLLE | ETL.7140.INSL.NCER | 2022-05-24 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45486010 | T3 DI IGNACIO-BOLINAS #1 4/47 RPR INSW | ICW
LC | 123676617 | 006/180 | T3 DI COLGTE ALLEGHNY 006/180 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-05-24 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31618163 | T2 DI COLGATE-ALLEGHANY 3/81 REFRAME | 93E
LC | 123676969 | 005/144 | T3 DI DRM-GRSS VLLY-WMR 5/144 RPR SPLW | SACTO | ETL.6760.INSL.NCER | 2022-05-24 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Replace
LC | 123677435 | :009/005 | T3 EI FULTON-CALISTOGA :9/5 RPL STRW | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-24 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606073 | T3 DI FULTON CALISTOGA :002/004 RPL STRW | 70Y
LC | 123677589 | 005/049 | T3 DI MNT VST BRNS 5/49 RPL INSW | MOSSLNDG | ETL.7590.INSL | 2022-05-24 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31612296 | T3 DI MNT VST BRNS 5/49 RPL INSW | 93I
LC | 123678866 | 032/141 | T3 DI FLTN-LAKEVILL-IGNC 32/141 RPR INSS | LAKEVLLE | ETL.4950.INSL.CERA | 2022-05-24 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575474 | T3 DI FLTN-LAKEVILL-IGNC 32/141 RPR INSS | ICS
LC | 123678930 | 032/141 | T3 DI GEYSERS #9-LAKEVLE 32/141 RPR INSS | LAKEVLLE | ETL.4780.INSL | 2022-05-24 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575582 | T3 DI GEYSERS #9-LAKEVLE 32/141 RPR INSS | ICS
LC | 123679350 | 002/050 | T3 DI BURNS-LNE STR#2 2/050 RPL HRDW | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-05-24 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45616754 | T3 DI BURNS-LNE STR#2 2/050 RPL HRDW | ICW
LC | 123679355 | 002/050 | T3 DI BURNS-LNE STR#2 2/050 REFRAME | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-05-24 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31633924 | T3 DI BURNS-LNE STR#2 2/050 REFRAME | 93E
LC | 123680078 | 010/005 | T3 EI MONTE RIO-FULTON 10/5 RMV VEG | LAKEVLLE | ETL.7630.POLE.WOOD | 2022-05-24 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 932 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | Brush Fuel | Road | Remove | 45465931 | T3 EI MONTE RIO-FULTON 10/5 RMV VEG | CHS
LC | 123680081 | 010/005 | T3 EI MONTE RIO-FULTON 10/5 RPL HRDD | LAKEVLLE | ETL.7630.POLE.WOOD | 2022-05-24 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45571489 | T3 EI MONTE RIO-FULTON 10/5 RPL HRDD | ICW
LC | 123680677 | 007/039 | T3 EI RND MTN-TBL MTN #2 7/39 RMV VEG | TABLEMTN | ETL.6070.TOWR | 2022-05-24 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | Overgrown | Vegetation | Trim
LC | 123680712 | 007/039 | T3 EI RND MTN-TBL MTN #2 7/39 BENT STEEL | TABLEMTN | ETL.6070.TOWR | 2022-05-24 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123681640 | 004/001B | T3 DI GRZLY TP CTY SNT CLR 4/1B RPR GYWW | TABLEMTN | ETL.2395.POLE.WOOD | 2022-05-24 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123681750 | 002/054 | T3 DI COLGATE-CHALLENGE 2/54 RPR GYWW | SACTO | ETL.6480.POLE.NWOD | 2022-05-24 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123681878 | 016/148 | T3 DI MONTA VISTA-BURNS 16/148 RPL HRDD | MOSSLNDG | ETL.7590.POLE.NWOD | 2022-05-24 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45617064 | T3 DI MONTA VISTA-BURNS 16/148 RPL HRDD | ICW
LC | 123682434 | 002/054 | T3 DI BURNS-LNE STR#2 2/054 RPL INSW | MOSSLNDG | ETL.6240.INSL.NCER | 2022-05-24 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31612424 | T3 DI BURNS-LNE STR#2 2/054 RPL INSW | 93I
LC | 123682781 | 005/065 | T3 DI DRUM-SUMMIT #2 5/65 RPL HRDW | SACTO | ETL.1450.POLE.WDPS | 2022-05-24 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123682899 | 008/066 | T3 DI MNT VST BRNS 8/66 INS COTTER | MOSSLNDG | ETL.7590.INSL.NCER | 2022-05-24 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45617065 | T3 DI MNT VST BRNS 8/66 INS COTTER | ICW
LC | 123682906 | 008/044 | T3 EI RND MTN-TBL MTN #2 8/44 BENT STEEL | TABLEMTN | ETL.6070.TOWR | 2022-05-24 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123683001 | 010/078 | T3 DI MONTA VISTA BURNS 10/78 INS HRDD | MOSSLNDG | ETL.7590.POLE.NWOD | 2022-05-24 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | Missing | Hardware-Wood | Install | 45617381 | T3 DI MONTA VISTA BURNS 10/78 INS HRDD | ICW
LC | 123683295 | 011/000 | T3 DI MAPLE CREEK-HOOPA 11/0 RPR INSW | EUREKA | ETL.7490.INSL.NCER | 2022-05-24 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123683520 | 008/045 | T3 EI RND MTN-TBL MTN #2 8/45 BENT STEEL | TABLEMTN | ETL.6070.TOWR | 2022-05-24 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123683540 | 006/066 | T3 DI DRUM-RIO OSO #2 006/066 RPR CNDS | SACTO | ETL.1430.INSL.NCER | 2022-05-24 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair
LC | 123683668 | 005/047 | T3 DI MNT VST BRNS 5/47C RPR STRW | MOSSLNDG | ETL.7590.POLE.WDPS | 2022-05-24 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45617383 | T3 DI MNT VST BRNS 5/47C RPR STRW | ICW
LC | 123683731 | -014/003 | T3 DI FULTON-CALISTOGA -14/3 RPL INSW | LAKEVLLE | ETL.6880.INSL.NCER | 2022-05-24 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31616688 | T3 DI FLTN-CALISTOG -13/006 RPL INSW | 93I
LC | 123683834 | 006/116 | T3 EI COLGATE-CHALLENGE 6/116 ANTI-SPLT | SACTO | ETL.6480.POLE.WOOD | 2022-05-24 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123683835 | 005/110 | T3 EI COLGATE-CHALLENGE 5/110 RPR CNDW | SACTO | ETL.6480.INSL.NCER | 2022-05-24 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair
LC | 123683879 | T-120 | T3 DI MIDWAY-SANTA MARIA T-120 UNBURY | PISMOBCH | ETL.9240.TOWR | 2022-05-24 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123684139 | 005/121 | T3 DI DRUM-SPAULDING 5/121 RPR INSW | SACTO | ETL.6770.INSL.NCER | 2022-05-24 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123684189 | 005/051 | T3 DI MONTA-VSTA-BURNS 5/051 RPR CRSW | MOSSLNDG | ETL.7590.POLE.WOOD | 2022-05-24 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45617385 | T3 DI MONTA-VSTA-BURNS 5/051 RPR CRSW | ICW
LC | 123684230 | 085/598 | T3 DI BRDGVLLE-CTTNWD 085/598L RPR SHLW | EUREKA | ETL.1110.POLE.WDPS | 2022-05-24 | 2022-05-19 |  | 2022-11-15 | 2022-11-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45576068 | T3 DI BRDGVLLE-CTTNWD 085/598L RPR SHLW | ICW
LC | 123684258 | 016/075 | T3 DI MSS LNDG-MTCLF 16/75 COTTER | MOSSLNDG | ETL.6050.INSL | 2022-05-24 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45581083 | T3 DI MSS LNDG-MTCLF 16/75 COTTER | ICS
LC | 123684390 | 026/118 | T3 DI XCHQR-INDN FL 026/118 RPR FOND | FRESNO | ETL.8650.POLE.NWOD | 2022-05-24 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123684401 | 016/124 | T3 DI GRN VALLY-CMP EVRS 16/124 RPR INSS | MOSSLNDG | ETL.1710.INSL | 2022-05-24 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45617387 | T3 DI GRN VALLY-CMP EVRS 16/124 RPR INSS | ICS
LC | 123684403 | 016/124 | T3 DI GRN VALLY-CMP EVRS 16/124 RPL HDWT | MOSSLNDG | ETL.1710.TOWR | 2022-05-24 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45590652 | T3 DI GRN VALLY-CMP EVRS 16/124 RPL HDWT | ICQ
LC | 123684577 | 010/000 | T3 DI MENDOCINO-WILLITS 010/000 RPL STRW | WILLITS | ETL.7540.POLE.WOOD | 2022-05-24 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31615124 | T2 EI MENDOCINO-WILLITS 7/0 RPL POLE | 70Y
LC | 123684687 | 007/078 | T3 DI DRUM RIO OSO #1 007/078 INS HRDT | SACTO | ETL.1420.TOWR | 2022-05-24 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45599989 | T3 DI DRUM RIO OSO #1 007/078 INS HRDT | ICQ
LC | 123684710 | -013/001 | T3 DI FULTON-CALISTOGA -13/1 RPL HRDD | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-24 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45485899 | T3 DI FULTON-CALISTOGA -13/1 RPL HRDD | ICW
LC | 123684715 | B023/519 | T3 DI DRM-GRSS VLLY-WEI B23/519 RPL HRDD | SACTO | ETL.6760.POLE.WOOD | 2022-05-24 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123684749 | 009/264 | T3 DI COLGATE-ALLEGHANY 009/264 RPL HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-05-24 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123684750 | 007/078 | T3 DI DRUM RIO OSO #1 007/078 RPL INSS | SACTO | ETL.1420.INSL.CERA | 2022-05-24 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31618898 | T3 DI DRUM-RIO OSO #1 RPL INSS 2 TWRS | 93K
LC | 123684875 | 019/008 | T3 DI MAPLE CREEK-HOOPA 19/8 RPL HRDD | EUREKA | ETL.7490.POLE.WOOD | 2022-05-24 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123684906 | 005/057 | T3 DI DRUM-RIO OSO #1-TWR 5/57 HRDT RPL | SACTO | ETL.1420.TOWR | 2022-05-24 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45599982 | T3 DI DRUM-RIO OSO #1-TWR 5/57 HRDT RPL | ICQ
LC | 123684966 | 010/000 | T3 DI MAPLE CREEK-HOOPA 10/0 RPR INSS | EUREKA | ETL.7490.INSL.NCER | 2022-05-24 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123685107 | 001/010 | T3 DI RND MTN-TB MTN #2 1/10 INS HRDT | TABLEMTN | ETL.6070.TOWR | 2022-05-24 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Missing | Hardware-Tower | Install
LC | 123685146 | 010/285 | T3 DI COLGATE-ALLEGHANY 10/285 RPL HRDW | SACTO | ETL.6470.INSL.NCER | 2022-05-24 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123685157 | 022/176 | T3 DI PARADISE-TABLE MTN 22/176 RPR INSW | TABLEMTN | ETL.4316.INSL.NCER | 2022-05-24 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123685246 | 000/001C | T3 DI DRUM PH #2 TAP 0/1C RPL HRDW | SACTO | ETL.6375.POLE.WOOD | 2022-05-24 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123685413 | 000/006 | T3 DI GEYSERS #7-EAGLE ROCK 0/6 RPR INSW | LAKEVLLE | ETL.1680.INSL.CERA | 2022-05-24 | 2022-05-02 |  | 2022-10-29 | 2022-11-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45575554 | T3 DI GEYSERS #7-EAGLE ROCK 0/6 RPR INSW | ICW
LC | 123685983 | 026/116 | T3 DI GEYSERS #9-LAKEVIL 26/116 RPL INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2022-05-25 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31616434 | T3 DI GEYSERS #9-LAKEVIL 26/116 RPL INSS | 93K
LC | 123685984 | 026/116 | T3 DI EGL RK-FLTN-SLVR 26/116 RPR INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2022-05-25 | 2022-04-28 |  | 2022-10-25 | 2022-10-28 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575439 | T3 DI EGL RK-FLTN-SLVR 26/116 RPR INSS | ICS
LC | 123686103 | :004/016 | T3 DI GEYSERS #9-LAKVLL :4/16 INS DAMS | LAKEVLLE | ETL.4780.INSL.NCER | 2022-05-25 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR NTDE | Missing | Damper-Steel | Install | 45324324 | T3 DI GEYSERS #9-LAKVLL :4/16 INS DAMS | ICS
LC | 123686522 | :000/010 | T3 DI FULTON-PUEBLO :0/10 RPR STRW | LAKEVLLE | ETL.1600.POLE.NWOD | 2022-05-25 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAR | No Good/Out of Stdrd | Structure-Wood | Repair | 45571458 | T3 DI FULTON-PUEBLO :0/10 RPR STRW | ICW
LC | 123686740 | 005/009 | T3 DI PTTR VLLY-WLLTS 5/9 RPR STRW | WILLITS | ETL.7820.POLE.WOOD | 2022-05-25 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123687274 | 045/255 | T3 EI TEMBLOR-SLO 44/255 RPR RPTS | PISMOBCH | ETL.3960.INSL.NCER | 2022-05-25 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 593 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Raptor Guard-Steel | Replace
LC | 123687314 | 007/002 | T3 DI WISHON SN JQUIN #3 7/2 RPR GYWW | FRESNO | ETL.9340.POLE.NWOD | 2022-05-25 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45489621 | T3 DI WISHON SN JQUIN #3 7/2 RPR GYWW | ICW
LC | 123687617 | Z009/003 | T3 DI FULTON-CLSTGA 9/003 RPR STRS | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-05-25 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45450252 | T3 DI FULTON-CLSTGA 9/003 RPR STRS | ICS
LC | 123687634 | 031/264 | T3 EI PIT #1-COTTONWOOD 31/264 RPR GWRS | TABLEMTN | ETL.5390.TOWR | 2022-05-25 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123688801 | 023/100 | T3 EI MOR BY-SR SW ST #2 23/100 RPL INSS | PISMOBCH | ETL.5310.INSL | 2022-05-25 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619690 | T2 EI MRRO BY-SLR SS #2 034/147 RPL INSS | 93K
LC | 123688802 | 044/253 | T3 EI TEMBLOR-SLO 44/253 COTR KEY | PISMOBCH | ETL.3960.INSL.CERA | 2022-05-25 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123688803 | 023/100 | T3 EI MRRO BY-SOLR ST #1 23/100 RPL INSS | PISMOBCH | ETL.5300.INSL | 2022-05-25 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31618211 | T2 EI MRO BAY-SOLAR SS #1 RPL INSS 7TWR | 93K
LC | 123689598 | 044/250 | T3 EI TEMBLOR-SLO 44/250 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2022-05-25 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31611745 | T3 EI TEMBLOR-SLO RPL INSS 7TWR | 93K
LC | 123689814 | 023/101 | T3 EI MOR BY-SR SW ST #2 23/101 RPL INSS | PISMOBCH | ETL.5310.INSL | 2022-05-25 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619690 | T2 EI MRRO BY-SLR SS #2 034/147 RPL INSS | 93K
LC | 123691086 | 007/189 | T3 DI COLGATE-ALLGHNY 7/189 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-05-25 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31606404 | T3 COLGATE-ALLEGHANY 7/188 RPL POLE | 70Y
LC | 123691172 | 006/004 | T3 DI PTTR VLLY-WLLTS 6/4 REFRAME | WILLITS | ETL.7820.POLE.NWOD | 2022-05-25 | 2022-05-03 |  | 2022-10-30 | 2022-11-03 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31627442 | T3 DI PTTR VLLY-WLLTS 6/4 REFRAME | 93E
LC | 123691260 | 006/172 | T3 DI COLGATE-ALLGHNY 6/172 RPL INSW | SACTO | ETL.6470.INSL.CERA | 2022-05-25 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31615823 | T3 DI COLGATE-ALLGHNY 6/172 RPL INSW | 93I
LC | 123691468 | 030/254 | T3 EI PIT #1-COTTONWD 30/254 RPR GYWS | TABLEMTN | ETL.5390.TOWR | 2022-05-25 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123692154 | 021/007 | T3 DI MAPLE CREEK-HOOPA 21/7 RPR INSW | EUREKA | ETL.7490.INSL.NCER | 2022-05-25 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123692288 | 044/252 | T3 EI TEMBLOR-SLO 44/252 RPR RPTS | PISMOBCH | ETL.3960.INSL.CERA | 2022-05-25 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 593 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Raptor Guard-Steel | Replace
LC | 123693196 | 011/000 | T3 EI MNDCN-WLLTS 11/0 REPUL GYWW | WILLITS | ETL.7540.POLE.NWOD | 2022-05-25 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP COMP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45590445 | T3 EI MNDCN-WLLTS 11/0 REPUL GYWW | ICW
LC | 123693252 | 007/009 | T3 LAURELES-OTTER 7/9 COTR KEY | MOSSLNDG | ETL.7380.INSL | 2022-05-25 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123693722 | 002/038 | T3 DI BURNS-LONE STAR #1 2/38 INS ARMS | MOSSLNDG | ETL.6230.INSL.NCER | 2022-05-25 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Conductor-Wood | Repair | 45617392 | T3 DI BURNS-LONE STAR #1 2/38 INS ARMS | ICW
LC | 123694470 | 005/145 | T3 DI COLGATE-ALLEGHANY 5/145 RMV BUTT | SACTO | ETL.6470.POLE.WOOD | 2022-05-25 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123694584 | 002/040 | T3 DI MIDDLEFORK #1 2/40 RPL INSW | SACTO | ETL.8405.INSL.NCER | 2022-05-25 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31619025 | T3 DI MIDDLEFORK #1 2/40 RPL INSW | 93I
LC | 123694634 | 003/006 | T3 BRIDGEVILLE-GARBERVILLE 3/6 RPL CONDW | EUREKA | ETL.6220.POLE.NWOD | 2022-05-25 | 2022-03-21 |  | 2022-09-17 | 2022-09-21 | Late | 638 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW CREW OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Conductor-Wood | Replace | 31604373 | T3 BRIDGEVILLE-GARBERVILLE 3/6 RPL CONDW | 93C
LC | 123694762 | 037/191A | T3 DI EGL RK-FLTN-SLVRD 37/191A RPR SWTC | LAKEVLLE | ETL.4392.SWIT | 2022-05-25 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 623 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | Out of Adjustment | Switch | Repair
LC | 123694767 | 003/011 | T3 DI WISHON-SN JQUIN #3 3/11 RPL HRDD | FRESNO | ETL.9340.POLE.NWOD | 2022-05-25 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45598608 | T3 DI WISHON-SN JQUIN #3 3/11 RPL HRDD | ICW
LC | 123694873 | 024/352 | T3 DI GLD HL #1 24/352 RPL STRW | SACTO | ETL.6950.POLE.WOOD | 2022-05-25 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606076 | T3 DI GLD HL #1 24/352 RPL STRW | 70Y
LC | 123694922 | 003/044 | T3 DI BURNS-LONE STAR #1 3/44 RPR STRW | MOSSLNDG | ETL.6230.POLE.NWOD | 2022-05-25 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Repair | 45617397 | T3 DI BURNS-LONE STAR #1 3/44 RPR STRW | ICW
LC | 123694924 | 015/119 | T3 DI SLT SPRNG-TGR CR 15/119 RPR STRT | VICTOR | ETL.3500.TOWR | 2022-05-25 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45591272 | T3 DI SLT SPRNG-TGR CR 15/119 RPR STRT | ICQ
LC | 123694965 | 002/020 | T3 DI MIDDLE FORK #1 2/20 RPR INSS | SACTO | ETL.5140.INSL | 2022-05-25 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123695029 | 009/003 | T3 DI POTTER VLLY-WILLITS 9/3 RPL HRDW | WILLITS | ETL.7820.POLE.WOOD | 2022-05-25 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123695074 | 005/095 | T3 EI FLTN-CLSTGA 005/095 REFRAME | SACTO | ETL.6870.POLE.WOOD | 2022-05-25 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31633954 | T3 DI FRNCH MDWS-MID FRK 4/91 REFRAME | 93E
LC | 123695075 | 005/106 | T3 EI COLGATE-CHALLENGE 5/106 RPL HRDW | SACTO | ETL.6480.POLE.NWOD | 2022-05-25 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123695783 | 002/058 | T3 DI BURNS-LONE STR#2 2/058 RMV VEG | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-05-26 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123695928 | 004/052 | T3 DI WST PNT VLY SPRNGS 4/52 RPL HRDD | VICTOR | ETL.8350.POLE.WOOD | 2022-05-26 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45532625 | T3 DI WST PNT VLY SPRNGS 4/52 RPL HRDD | ICW
LC | 123697136 | T062 | T3 DI MIDWY-SNTA MARIA T062 UNBURY | PISMOBCH | ETL.9240.TOWR | 2022-05-26 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123697502 | 009/050 | T3 EI RND MTN-TBL MTN #2 9/50 RPR STEEL | TABLEMTN | ETL.6070.TOWR | 2022-05-26 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123697775 | 009/049 | T3 EI RND MTN-TBL MTN #2 9/49 RPR STEEL | TABLEMTN | ETL.6070.TOWR | 2022-05-26 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123697950 | 007/003 | T3 EI FULTON-CALISTOGA 007/003 RPR GYWW | LAKEVLLE | ETL.6880.POLE.STPS | 2022-05-26 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45485772 | T3 EI FULTON-CALISTOGA 007/003 RPR GYWW | ICW
LC | 123697957 | 006/002 | T3 DI LAURELES-OTTER 6/2 RPL HRDD | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-26 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123698025 | 007/074 | T3 DI DRUM-RIO OSO #2 7/74 RPR STRT | SACTO | ETL.1430.TOWR | 2022-05-26 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45456859 | T3 DI DRUM-RIO OSO #2 7/74 RPR STRT | ICQ
LC | 123698833 | 010/187 | T3 DI FRNCH MDWS MDL FRK 10/187 RPL STRW | SACTO | ETL.6870.POLE.WOOD | 2022-05-26 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606072 | T3 EI FRNCH MDWS-MDDLE FRK 0/2 RPL POLE | 70Y
LC | 123698990 | 006/124 | T3 DI FRNCH MDWS MDL FRK 6/124 REFRAME | SACTO | ETL.6870.POLE.WOOD | 2022-05-26 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31633954 | T3 DI FRNCH MDWS-MID FRK 4/91 REFRAME | 93E
LC | 123699681 | 004/048 | T3 DI DRUM-RIO OSO #2 004/048 RPR INSS | SACTO | ETL.1430.INSL.NCER | 2022-05-26 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123699728 | 004/048 | T3 DI DRUM-RIO OSO #2 004/048 RPR SPLS | SACTO | ETL.1430.INSL.NCER | 2022-05-26 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair
LC | 123699772 | 004/048 | T3 DI DRUM-RIO OSO #2 4/48 BNT STEEL | SACTO | ETL.1430.TOWR | 2022-05-26 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45600060 | T3 DI DRUM-RIO OSO #2 4/48 BNT STEEL | ICQ
LC | 123699819 | 002/044 | T3 DI COLGATE-CHALLENGE 2/44 RPL SPLW | SACTO | ETL.6480.INSL.NCER | 2022-05-26 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Replace
LC | 123700188 | 002/029 | T3 DI DRUM-RIO OSO #1 2/29 RPL INSS | SACTO | ETL.1420.INSL.CERA | 2022-05-26 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31618898 | T3 DI DRUM-RIO OSO #1 RPL INSS 2 TWRS | 93K
LC | 123700293 | 004/091 | T3 EI COLGATE-CHALLENGE 004/091 RPR HRDW | SACTO | ETL.6480.POLE.WOOD | 2022-05-26 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123700478 | 000/002 | T3 DI BURNS-LONE STAR #2 0/2 RPL STRW | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-05-26 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31629518 | T3 DI BRNS LN STR #2 2/49 RPL POLE | 70Y
LC | 123700541 | 005/128 | T3 EI COLGATE-GRASS VALEY 5/128 RPR GYWW | SACTO | ETL.6490.POLE.NWOD | 2022-05-26 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123700543 | 005/131 | T3 EI COLGATE-GRASS VALEY 5/131 RPL INSW | SACTO | ETL.6490.INSL | 2022-05-26 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617974 | T3 EI COLGATE-GRASS VALEY 5/131 RPL INSW | 93I
LC | 123700550 | 000/002 | T3 DI BURNS-LONE STAR #2 0/2 RPR XARM | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-05-26 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45333989 | T3 DI BURNS-LONE STAR #2 0/2 RPR XARM | ICW
LC | 123700561 | 006/149 | T3 EI CLGTE-GRS VLY 6/149 RPR SPLCW | SACTO | ETL.6490.INSL.NCER | 2022-05-26 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 123700563 | 006/149 | T3 EI CLGTE-GRS VLY 6/149 RPR STRW | SACTO | ETL.6490.POLE.WOOD | 2022-05-26 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123701770 | 017/117 | T3 DI MTCLF-GRN VLLY 17/117 RPR SPLW | MOSSLNDG | ETL.2540.INSL.NCER | 2022-05-26 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Repair | 45617437 | T3 DI MTCLF-GRN VLLY 17/117 RPR SPLW | ICW
LC | 123703369 | 002/047 | T3 DI BURNS-LONE STAR #2 2/47 RPL HRDD | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-05-26 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45617438 | T3 DI BURNS-LONE STAR #2 2/47 RPL HRDD | ICW
LC | 123706740 | 006/064 | T3 DI DRUM-RIO OSO #2 6/64 BNT STEEL | SACTO | ETL.1430.TOWR | 2022-05-27 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45600068 | T3 DI DRUM-RIO OSO #2 6/64 BNT STEEL | ICQ
LC | 123706744 | 017/148 | T3 DI MRI FLT-GLD HL#1 17/148 RMV VEG | SACTO | ETL.2660.TOWR | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123706775 | 006/030 | T3 DI GEYSERS #17-FULTON 06/30 RPR INSS | LAKEVLLE | ETL.4770.INSL.CERA | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571486 | T3 DI GEYSERS #17-FULTON 06/30 RPR INSS | ICS
LC | 123706779 | 017/148 | T3 DI MRI FLT-GLD HL#1 17/148 RPR INSS | SACTO | ETL.2660.INSL.NCER | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123706824 | 018/146 | T3 DI PARADISE-TBL MTN 18/146 RPR XARMS | TABLEMTN | ETL.4316.POLE.STPS | 2022-05-27 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Steel | Replace
LC | 123706950 | 018/150A | T3 DI PARADSE-TABLE MTN 18/150A RPR HRDD | TABLEMTN | ETL.4316.POLE.NWOD | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123706954 | 018/150A | T3 DI PARADSE-TABLE MTN 18/150A RPR GYWW | TABLEMTN | ETL.4316.POLE.NWOD | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123707035 | :006/039 | T3 DI EAGLE ROCK-REDBUD :6/39 RPR INSS | WILLITS | ETL.1480.INSL.NCER | 2022-05-27 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45590073 | T3 DI EAGLE ROCK-REDBUD :6/39 RPR INSS | ICS
LC | 123707203 | 015/071 | T3 DI MSS LANDING-MTCLF 015/071 RPR INSS | MOSSLNDG | ETL.6050.INSL.CERA | 2022-05-27 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45581084 | T3 DI MSS LANDING-MTCLF 015/071 RPR INSS | ICS
LC | 123707303 | 000/001 | T3 DI GEYSERS #12-FULTON 0/1 RPL INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2022-05-27 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615952 | T3 DI GEYSERS #12-FULTON RPL INSS 4TWR | 93K
LC | 123707677 | 009/006 | T3 DI BRIDGEVILLE-GARBERVLL 9/6 RPR INSW | EUREKA | ETL.6220.INSL.CERA | 2022-05-27 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45451438 | T3 DI BRIDGEVILLE-GARBERVLL 9/6 RPR INSW | ICW
LC | 123707781 | 009/043 | T3 DI GEYSERS #12-FULTON 9/43 RPR INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571485 | T3 DI GEYSERS #12-FULTON 9/43 RPR INSS | ICS
LC | 123707932 | :002/008 | T3 DI EGL RCK-FLTN-SLVRDO :2/8 COTTER | LAKEVLLE | ETL.4392.INSL.CERA | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45467299 | T3 DI EGL RCK-FLTN-SLVRDO :2/8 COTTER | ICS
LC | 123707936 | 005/153 | T3 DI CLGTE-ALLGHNY 5/153 RPL HRDD | SACTO | ETL.6470.POLE.WOOD | 2022-05-27 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123708095 | B021/475 | T3 DI DRM-GRSS VLY-WMR B021/475 RPL HRDD | SACTO | ETL.6760.POLE.WOOD | 2022-05-27 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123708320 | 011/093 | T3 DI MONTA VISTA-BURNS 11/93 RPR INSW | MOSSLNDG | ETL.7590.INSL.NCER | 2022-05-27 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45617524 | T3 DI MONTA VISTA-BURNS 11/93 RPR INSW | ICW
LC | 123708347 | 003/082 | T3 DI DRM-GRSS VLLY-WMR 3/82 REFRAME | SACTO | ETL.6760.POLE.WOOD | 2022-05-27 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31612262 | T3 DI DRM-GRSS VLLY-WMR 3/82 REFRAME | 93E
LC | 123708516 | 010/013 | T3 DI MAPLE CREEK-HOOPA 10/13L RPL ANCW | EUREKA | ETL.7490.POLE.WDPS | 2022-05-27 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Anchor-Steel | Replace
LC | 123708517 | 010/013 | T3 DI MAPLE CREEK-HOOPA 10/13L RPR GYWW | EUREKA | ETL.7490.POLE.WDPS | 2022-05-27 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123708518 | 008/007 | T3 DI BRIDGEVILLE-GARBERVL 8/7 RPR INSW | EUREKA | ETL.6220.INSL.CERA | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45640231 | T3 DI BRIDGEVILLE-GARBERVL 8/7 RPR INSW | ICW
LC | 123708615 | 002/043 | T3 EI FRCH MDWS-MDL FK 2/43 RPR GYWW | SACTO | ETL.6870.POLE.NWOD | 2022-05-27 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123708669 | -016/006 | T3 DI FULTON-CALISTOGA -16/6 REFRAME | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-05-27 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31634722 | T3 DI FULTON-CALISTOGA -16/6 REFRAME | 93E
LC | 123708809 | 027/006 | T3 DI MAPLE CREEK-HOOPA 27/6 RPR GYWW | EUREKA | ETL.7490.POLE.WOOD | 2022-05-27 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123708857 | B022/490 | T3 DI DRM-GRS VLLY-WMR B22/490 RPL HRDW | SACTO | ETL.6760.POLE.NWOD | 2022-05-27 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123708958 | 004/119 | T3 DI DRM GRS VLY WMR 4/119 RPL DAMS | SACTO | ETL.6760.POLE.NWOD | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Damper-Steel | Replace
LC | 123708964 | 004/119 | T3 DI DRM GRS VLY WMR 4/119 RPL HRDS | SACTO | ETL.6760.POLE.NWOD | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Steel | Replace
LC | 123708968 | 004/119 | T3 DI DRM GRS VLY WMR 4/119 RPR JUMW | SACTO | ETL.6760.POLE.NWOD | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Jumper-Wood | Repair
LC | 123709264 | 017/003 | T3 DI OAKHURST TAP 017/003 RPR GYWW | FRESNO | ETL.1252.POLE.NWOD | 2022-05-27 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45489412 | T3 DI OAKHURST TAP 017/003 RPR GYWW | ICW
LC | 123709411 | 024/106 | T3 DI MORRO BY-SLR SS #2 24/106 RPR INSS | PISMOBCH | ETL.5310.INSL | 2022-05-27 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45605023 | T3 DI MORRO BY-SLR SS #2 24/106 RPR INSS | ICS
LC | 123709605 | 011/047 | T3 DI GEYSERS #17-FULTON 11/47 RPR INSS | LAKEVLLE | ETL.4770.INSL.CERA | 2022-05-27 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571468 | T3 DI GEYSERS #17-FULTON 11/47 RPR INSS | ICS
LC | 123709606 | 011/047 | T3 DI GEYSERS #12-FULTON 11/47 RPR INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2022-05-27 | 2022-05-04 |  | 2022-10-31 | 2022-11-04 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571466 | T3 DI GEYSERS #12-FULTON 11/47 RPR INSS | ICS
LC | 123709707 | 016/074 | T3 DI MSS LNDNG-MTCLF 016/074 RPR INSS | MOSSLNDG | ETL.6050.INSL | 2022-05-27 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45581088 | T3 DI MSS LNDNG-MTCLF 016/074 RPR INSS | ICS
LC | 123709872 | 018/142 | T3 DI PARADISE-TBL MTN 18//142 COTR KEY | TABLEMTN | ETL.4316.INSL.NCER | 2022-05-27 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123709928 | 009/051 | T3 DI MNTA VSTA-CYTE SW ST 9/51 RPL HRDT | MOSSLNDG | ETL.5090.TOWR | 2022-05-27 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45507798 | T3 DI MNTA VSTA-CYTE SW ST 9/51 RPL HRDT | ICQ
LC | 123709972 | 009/051 | T3 DI MTCLF-MNTA VSTA #3 9/51 RPR SHLD | MOSSLNDG | ETL.5091.INSL | 2022-05-27 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45381026 | T3 DI MTCLF-MNTA VSTA #3 9/51 RPR SHLD | ICS
LC | 123710189 | 008/037 | T3 DI GEYSERS #12-FULTON 8/37 INS HRDT | LAKEVLLE | ETL.4750.TOWR | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install
LC | 123710621 | 001/007 | T3 DI GYSRS #12-FLTN 1/7 RPR INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2022-05-27 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575589 | T3 DI GYSRS #12-FLTN 1/7 RPR INSS | ICS
LC | 123710624 | 001/005 | T3 DI GEYSERS #12-FULTON 1/5 RPR SHLS | LAKEVLLE | ETL.4750.TOWR | 2022-05-27 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45571483 | T3 DI GEYSERS #12-FULTON 1/5 RPR SHLS | ICS
LC | 123710665 | :003/019 | T3 DI GEYSERS #12-FULTON :3/19 RPR INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571481 | T3 DI GEYSERS #12-FULTON :3/19 RPR INSS | ICS
LC | 123710692 | :003/019 | T3 DI GEYSERS #9-LAKEVLLE :3/19 RPR INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575583 | T3 DI GEYSERS #9-LAKEVLLE :3/19 RPR INSS | ICS
LC | 123710939 | B017/388 | T3 DI DRM-GRSS VLLY-WMR B17/388 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2022-05-27 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123711069 | 036/182 | T3 EI FULTON-PUEBLO 36/182 RPR FOND | LAKEVLLE | ETL.1600.TOWR | 2022-05-27 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP PGEA OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123711122 | 000/005 | T3 DI BRUNSWICK #1 TAP 0/5 RPR JMPS | SACTO | ETL.1422.INSL.CERA | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Steel | Repair | 45456604 | T3 DI BRUNSWICK #1 TAP 0/5 RPR JMPS | ICS
LC | 123711165 | 028/134 | T3 DI EXCHQR INDN FLT 28/134 RPL HRDT | FRESNO | ETL.8650.POLE.NWOD | 2022-05-27 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123711169 | 028/134 | T3 DI EXCHQR INDN FLT 28/134 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2022-05-27 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123711225 | 028/134 | T3 DI EXCHQR INDN FLT 28/134 RPR SHLS | FRESNO | ETL.8650.POLE.NWOD | 2022-05-27 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair
LC | 123711227 | 028/134 | T3 DI EXCHQR INDN FLT 28/134 RPR INSS | FRESNO | ETL.8650.INSL.CERA | 2022-05-27 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45489444 | T3 DI EXCHQR INDN FLT 28/134 RPR INSS | ICS
LC | 123711269 | B020/456 | T3 DI DRM-GRSS VLLY-WMR B20/456 RPL HRDW | SACTO | ETL.6760.POLE.WOOD | 2022-05-27 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123711351 | B020/456 | T3 DI DRM-GRSS VLLY-WMR B20/456 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2022-05-27 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31631449 | T2 EI DRUM-GRSS VLLY-WMR 18/427 RPL POLE | 70Y
LC | 123711823 | 003/024 | T3 DI MORAGA-CLARMNT #1 3/24 RMV VEG | CONCORD | ETL.2700.TOWR | 2022-05-27 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123711825 | 000/004 | T3 EI DRUM-SUMMIT #1 000/004L RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2022-05-27 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Replace | 31618287 | T3 EI DRUM-SUMMIT #1 000/004L RPL POLE | 70Y
LC | 123712216 | 018/078 | T3 DI MNTA VSTA-JFFRSN #1 18/78 INS HRDT | METCALF | ETL.5220.TOWR | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install
LC | 123712683 | :000/001 | T3 DI EAGL RCK-FLTN-SLVRDO :0/1 RPR INSS | LAKEVLLE | ETL.4392.INSL.CERA | 2022-05-27 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123712778 | 006/034 | T3 DI RND MTN-TBL MTN #2 6/34 RPR SHIELD | TABLEMTN | ETL.6070.TOWR | 2022-05-28 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45457518 | T3 DI RND MTN-TBL MTN #2 6/34 RPR SHIELD | ICS
LC | 123712790 | 006/035 | T3 DI ROUND MTN-TBL MTN #1 6/35 RPL ANCS | TABLEMTN | ETL.6060.TOWR | 2022-05-27 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Replace
LC | 123712792 | 006/035 | T3 DI ROUND MTN-TBL MTN #1 6/35 RMV VEG | TABLEMTN | ETL.6060.TOWR | 2022-05-27 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123713510 | 006/034 | T3 DI RND MTN-TBLE MTN #2 6/34 RPL HRDT | TABLEMTN | ETL.6070.TOWR | 2022-05-28 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123713512 | 006/034 | T3 DI RND MTN-TBLE MTN #2 6/34 RPR ANCS | TABLEMTN | ETL.6070.TOWR | 2022-05-28 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair | 45457519 | T3 DI RND MTN-TBLE MTN #2 6/34 RPR ANCS | ICS
LC | 123713516 | 006/034 | T3 DI RND MTN-TABLE MTN #1 6/34 RPL ANCS | TABLEMTN | ETL.6060.TOWR | 2022-05-28 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Replace
LC | 123713592 | 018/148A | T3 DI PARADISE-TABLE MTN 018/148A MASTIC | TABLEMTN | ETL.4316.POLE.NWOD | 2022-05-28 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123713613 | 004/116 | T3 DI DRM-GRS VLY WMAR 4/116 RPR ADSS | SACTO | ETL.6760.POLE.WOOD | 2022-05-28 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair
LC | 123713640 | 032/140 | T3 DI FULTON-LAKEVILLE 32/140 COTTER | LAKEVLLE | ETL.4950.INSL.CERA | 2022-05-28 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571462 | T3 DI FULTON-LAKEVILLE 32/140 COTTER | ICS
LC | 123713751 | 003/042A | T3 DI DRUM-RIO OSO #1 3/42AR RPR STRW | SACTO | ETL.1420.POLE.STPS | 2022-05-28 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW REMT FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123713827 | 001/007 | T3 DI EGL RCK-FLTN-SLVRDO 1/7 BNT STEEL | LAKEVLLE | ETL.4392.TOWR | 2022-05-28 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123713828 | 001/007 | T3 DI GEYSERS#17-FULTON 1/7 RPL INSS | LAKEVLLE | ETL.4770.INSL.CERA | 2022-05-28 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace
LC | 123713836 | 008/070 | T3 DI MDDL FRK-GLD HLL 8/70 BNT STEEL | SACTO | ETL.5140.TOWR | 2022-05-28 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45600185 | T3 DI MDDL FRK-GLD HLL 8/70 BNT STEEL | ICQ
LC | 123713855 | 008/237 | T3 DI COLEGATE-ALLEGHANY 8/237 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2022-05-28 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123713887 | 013/006 | T3 DI MAPLE CREEK-HOOPA 13/6 RPR ANCW | EUREKA | ETL.7490.POLE.NWOD | 2022-05-28 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123713894 | B017/386 | T3 DI DRM-GRS VLY-WEMR B17/386 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2022-05-28 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123713932 | 006/120 | T3 DI FRNCH MDWS-MDL FRK 6/120 RPL HRDW | SACTO | ETL.6870.POLE.WOOD | 2022-05-28 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123714045 | 014/121 | T3 DI MNTA VSTA-BURNS 14/121 RPR INSW | MOSSLNDG | ETL.7590.SWIT | 2022-05-28 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45617525 | T3 DI MNTA VSTA-BURNS 14/121 RPR INSW | ICW
LC | 123714073 | 015/125 | T3 DI MIDDLE FRK-GLD HLL 15/125 RPR INSS | SACTO | ETL.5140.INSL.NCER | 2022-05-28 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123714091 | 006/156 | T3 DI CLGTE-GRSS VLLY 6/156 INS HRDW | SACTO | ETL.6490.POLE.WOOD | 2022-05-28 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123714309 | 024/097 | T3 DI EXCHQR-INDN FLT-YSMT 24/97 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2022-05-28 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123714411 | 011/010 | T3 DI MAPLE CREEK-HOOPA 11/10 RPR CONDW | EUREKA | ETL.7490.INSL.NCER | 2022-05-28 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair
LC | 123714427 | 001/037 | T3 DI BRNS-LNE STR #2 1/37 RPR INSW | MOSSLNDG | ETL.6240.INSL.NCER | 2022-05-28 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45617526 | T3 DI BRNS-LNE STR #2 1/37 RPR INSW | ICW
LC | 123714485 | 012/096 | T3 DI MIDDLE FORK-GOLD HILL 12/96 COTTER | SACTO | ETL.5140.INSL.CERA | 2022-05-28 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123714539 | 014/012 | T3 DI MONTE RIO-FULTON 14/12 COTTER | LAKEVLLE | ETL.7630.INSL | 2022-05-28 | 2022-05-28 |  | 2022-11-24 | 2022-11-28 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45571470 | T3 DI MONTE RIO-FULTON 14/12 COTTER | ICW
LC | 123714587 | 018/006 | T3 DI MI-WUK-CURTIS 18/06L RPL POLE | VICTOR | ETL.1073.POLE.WDPS | 2022-05-28 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31629711 | T3 DI MI-WUK-CURTIS 020/004L RPL POLE | 70Y
LC | 123714588 | 018/006 | T3 DI MI-WUK-CURTIS 18/06R RPL POLE | VICTOR | ETL.1073.POLE.WDPS | 2022-05-28 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31629711 | T3 DI MI-WUK-CURTIS 020/004L RPL POLE | 70Y
LC | 123714589 | 018/006 | T3 DI MI-WUK-CURTIS 18/06C RPL POLE | VICTOR | ETL.1073.POLE.WDPS | 2022-05-28 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31629711 | T3 DI MI-WUK-CURTIS 020/004L RPL POLE | 70Y
LC | 123714703 | 017/161 | T3 DI MONTA VISTA-BURNS 17/161 RPR INSW | MOSSLNDG | ETL.7590.INSL.NCER | 2022-05-28 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45617527 | T3 DI MONTA VISTA-BURNS 17/161 RPR INSW | ICW
LC | 123714771 | 005/056 | T3 DI DRUM-RIO OSO#1 5/056 RPR FOND | SACTO | ETL.1420.TOWR | 2022-05-28 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45599981 | T3 DI DRUM-RIO OSO#1 5/056 RPR FOND | ICQ
LC | 123714882 | 015/097 | T3 DI CNTRA CSTA-LS PSTS 15/97 RPR STRT | CONCORD | ETL.4510.TOWR | 2022-05-28 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123714905 | 005/061A | T3 DI DRUM-RIO OSO #1 5/61A RPR INSW | SACTO | ETL.1420.INSL.CERA | 2022-05-28 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123714907 | 005/061A | T3 DI DRUM-RIO OSO #1 5/61AL RPL HDWW | SACTO | ETL.1420.POLE.STPS | 2022-05-28 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123714923 | 018/076 | T3 DI MNTA VSTA-JFRSN #1 18/76 RPL HRDT | METCALF | ETL.5220.TOWR | 2022-05-28 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123714945 | 001/036 | T3 DI FRNCH-MDWS-MDDLE FRK 1/36 REFRAME | SACTO | ETL.6870.POLE.WOOD | 2022-05-28 | 2022-05-07 |  | 2022-11-03 | 2022-11-07 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31633859 | T3 EI FRNCH MDOWS-MDLE FRK 0/16 REFRAME | 93E
LC | 123715063 | 002/011 | T3 DI GEYSERS #17-FULTON 02/011 RPL INSS | LAKEVLLE | ETL.4770.INSL.CERA | 2022-05-28 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace
LC | 123715067 | 006/011 | T3 DI BRIDGEVILLE-GARBERVL 6/11 RPL INSW | EUREKA | ETL.6220.INSL.CERA | 2022-05-28 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617171 | T3 EI BRIDGEVILLE-GRBRVLL 3/0 RPL INSW | 93I
LC | 123715080 | 006/011 | T3 DI BRIDGEVILLE-GARBERVILL 6/11 COTTER | EUREKA | ETL.6220.POLE.WOOD | 2022-05-28 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45640232 | T3 DI BRIDGEVILLE-GARBERVILL 6/11 COTTER | ICW
LC | 123715082 | 002/011 | T3 DI EAGL RCK-FLTN-SILVRD 2/11 RMV DBRS | LAKEVLLE | ETL.4392.TOWR | 2022-05-28 | 2022-05-05 |  | 2022-11-01 | 2022-11-05 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCM OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove
LC | 123715090 | 015/120B | T3 DI MDDL FRK-GLD HLL 15/120B RPR STRW | SACTO | ETL.5140.POLE.NWOD | 2022-05-28 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123715125 | 001/013 | T3 DI MDLE FORK-GOLD HILL 1/13L RPR GRWW | SACTO | ETL.5140.POLE.WDPS | 2022-05-28 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Ground Wire-Wood | Repair
LC | 123715166 | 005/139 | T3 DI DEER CREEK-DRUM 5/129 RPL INSW | SACTO | ETL.6690.INSL.CERA | 2022-05-28 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123715182 | 001/009 | T3 DI GEYSERS #13 TAP 1/9 INS HRDT | LAKEVLLE | ETL.4781.TOWR | 2022-05-28 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install
LC | 123715229 | 008/151 | T3 DI FRNCH MDWS-MDL FRK 8/151 RPL HRDD | SACTO | ETL.6870.POLE.WOOD | 2022-05-28 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123715251 | 005/059A | T3 DI DRUM-RIO OSO #1 5/59A MASTIC | SACTO | ETL.1420.POLE.STPS | 2022-05-28 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45599983 | T3 DI DRUM-RIO OSO #1 5/59A MASTIC | ICQ
LC | 123715253 | 016/141 | T3 DI MONTA-VISTA BURNS 16/141 RPL HRDD | MOSSLNDG | ETL.7590.POLE.NWOD | 2022-05-28 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45617529 | T3 DI MONTA-VISTA BURNS 16/141 RPL HRDD | ICW
LC | 123715258 | 004/047 | T3 DI DRUM-RIO OSO #2 4/47 RPL HRDT | SACTO | ETL.1430.TOWR | 2022-05-28 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45600037 | T3 DI DRUM-RIO OSO #2 4/47 RPL HRDT | ICQ
LC | 123715290 | 004/047 | T3 DI DRUM-RIO OSO #2 4/47 RPR FOND | SACTO | ETL.1430.TOWR | 2022-05-28 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45600038 | T3 DI DRUM-RIO OSO #2 4/47 RPR FOND | ICQ
LC | 123715291 | 004/047 | T3 DI DRUM-RIO OSO #2 4/47 RPR STRT | SACTO | ETL.1430.TOWR | 2022-05-28 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45600039 | T3 DI DRUM-RIO OSO #2 4/47 RPR STRT | ICQ
LC | 123715344 | 009/015 | T3 DI BRIDGEVILLE-GARBERVL 9/15 RPR INSW | EUREKA | ETL.6220.INSL.NCER | 2022-05-28 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45451439 | T3 DI BRDGVLLE-GRBRVLL 009/015 RPR INSW | ICW
LC | 123715353 | 016/129 | T3 DI MDLE FRK-GLD HLL 16/129R INS HRDW | SACTO | ETL.5140.POLE.STPS | 2022-05-28 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | Missing | Hardware-Wood | Install
LC | 123715370 | 006/008 | T3 DI LAURELES-OTTER 6/008 RPL HRDD | MOSSLNDG | ETL.7380.POLE.NWOD | 2022-05-28 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123715414 | 008/228 | T3 DI COLGATE-ALLEGHANY 008/228 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-05-28 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31606404 | T3 COLGATE-ALLEGHANY 7/188 RPL POLE | 70Y
LC | 123715436 | 000/002 | T3 DI GEYSERS #17-FLTN 0/2 RMV VEG | LAKEVLLE | ETL.4770.TOWR | 2022-05-28 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123715498 | 017/134 | T3 DI MIDDLE FRK-GLD HLL 17/134 RPL HRDW | SACTO | ETL.5140.POLE.STPS | 2022-05-28 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | Missing | Hardware-Wood | Install
LC | 123717732 | 005/063 | T3 DI DRUM-RIO OSO #1 5/63 BACKFILL | SACTO | ETL.1420.TOWR | 2022-05-30 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair
LC | 123717791 | 006/067 | T3 DI DRUM-RIO OSO #1 006/067 BNT STEEL | SACTO | ETL.1420.TOWR | 2022-05-30 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45599986 | T3 DI DRUM-RIO OSO #1 006/067 BNT STEEL | ICQ
LC | 123717792 | 006/067 | T3 DI DRUM-RIO OSO #1 006/067 RPR INSS | SACTO | ETL.1420.INSL.CERA | 2022-05-30 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123718063 | 002/042 | T3 DI MIDDLEFORK #1 2/42 HRDW RPL | SACTO | ETL.8405.POLE.WOOD | 2022-05-30 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123718067 | 002/053 | T3 DI FRNCH MADWS-MDDL FRK 2/53 RPR POLE | SACTO | ETL.6870.POLE.NWOD | 2022-05-30 | 2022-05-07 |  | 2022-11-03 | 2022-11-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123719448 | 001/008 | T3 DI GEYSERS #13 TAP 1/8 RPR SHLS | LAKEVLLE | ETL.4781.TOWR | 2022-05-31 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45575543 | T3 DI GEYSERS #13 TAP 1/8 RPR SHLS | ICS
LC | 123719489 | 005/138 | T3 EI COLGT-GRSS VLLY 5/138 RPR POLE | SACTO | ETL.6490.POLE.WOOD | 2022-05-31 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123719652 | 009/002 | T3 EI FULTON-CALISTOG 9/2 REPULL GYWW | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-05-31 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45485768 | T3 EI FULTON-CALISTOG 9/2 REPULL GYWW | ICW
LC | 123719740 | 010/006 | T3 DI MDCNO-WLLTS-FT-BRG 10/6 RPR INSW | WILLITS | ETL.7550.INSL.CERA | 2022-05-31 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45640337 | T3 DI MDCNO-WLLTS-FT-BRG 10/6 RPR INSW | ICW
LC | 123719788 | !000/004 | T3 DI GEYSER #12-FULTON !0/4 RPR STRT | LAKEVLLE | ETL.4750.TOWR | 2022-05-31 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123719890 | !000/004 | T3 DI GEYSER #12-FULTON !0/4 RPR GYWS | LAKEVLLE | ETL.4750.TOWR | 2022-05-31 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45571480 | T3 DI GEYSER #12-FULTON !0/4 RPR GYWS | ICS
LC | 123720925 | 013/001 | T3 DI MONTE RIO-FULTON 13/1 RPR STRW | LAKEVLLE | ETL.7630.POLE.STPS | 2022-05-31 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45571469 | T3 DI MONTE RIO-FULTON 13/1 RPR STRW | ICW
LC | 123721182 | 000/010 | T3 DI MDDL FRK-GLD HILL 0/010 RPR SHLW | SACTO | ETL.5140.POLE.WDPS | 2022-05-31 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair
LC | 123721185 | 000/010 | T3 DI MDDL FRK-GLD HILL 0/010 RPR GRDW | SACTO | ETL.5140.POLE.WDPS | 2022-05-31 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Ground Wire-Wood | Repair
LC | 123721189 | 000/010 | T3 DI MDDL FRK-GLD HILL 0/010 INS HRDW | SACTO | ETL.5140.POLE.WDPS | 2022-05-31 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | Missing | Hardware-Wood | Install
LC | 123721278 | 004/096 | T3 DI COLGATE-CHALLNG 4/96 RPR POLE | SACTO | ETL.6480.POLE.STPS | 2022-05-31 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123721583 | 011/009 | T3 DI LAURELES-OTTER 11/9 RMV DBRS | MOSSLNDG | ETL.7380.POLE.WOOD | 2022-05-31 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123722927 | 003/068 | T3 EI COLGATE-CHALLENGE 3/68 RPL STRW | SACTO | ETL.6480.POLE.WOOD | 2022-05-31 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617797 | T3 EI COLGATE-CHALLENGE 2/056 RPL STW | 70Y
LC | 123722933 | 003/066 | T3 EI CLGT-CHLLNG 3/66 RPR INSW | SACTO | ETL.6480.INSL.NCER | 2022-05-31 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123723215 | 012/221 | T3 EI FRNCH MDWS-MDL FRK 12/221 RPL POLE | SACTO | ETL.6870.POLE.WOOD | 2022-05-31 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31614153 | T3 EI FRNCH MDWS-MDLE FRK 8/149 RPL STRW | 70Y
LC | 123723220 | 016/131C | T3 DI MDLE FRK-GLD HLL 16/131C RPR GYWW | SACTO | ETL.5140.POLE.WOOD | 2022-05-31 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123723342 | 025/199 | T3 DI PT #1 COTTNWD 25/199 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2022-05-31 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45639674 | T3 DI PT #1 COTTNWD 25/199 RPR FOND | ICQ
LC | 123723442 | 016/131C | T3 DI MDLE FRK-GLD HLL 16/131C RPR POLE | SACTO | ETL.5140.POLE.WOOD | 2022-05-31 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123724247 | 010/245 | T3 DI DRM-GRSS VLLY-WMR 10/245 RPL INSW | SACTO | ETL.6760.INSL.NCER | 2022-05-31 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617792 | T3 EI DRM-GRSS VLEY-WEIMAR 0/17 RPL INSW | 93I
LC | 123724298 | 067/002 | T2 HUMBOLDT-TRINITY 67/2 RPL STRW COA | EUREKA | ETL.1820.POLE.WDPS | 2022-05-31 | 2021-08-22 |  | 2022-08-22 | 2022-08-22 | Late | 437 | E - Schd Compl Yr 0 | Open | HFTD 2 | POHW NONR OH FMOB TR2 PRTO SR22 | Fire | Emergency | Replace | 31578175 | T2 HMBLDT-TRINITY 67/2L RPL POLE | 92F
LC | 123724411 | 007/009 | T3 DI BRIDGEVL-GARBERVL 7/9 RPL STRW | EUREKA | ETL.6220.POLE.WOOD | 2022-05-31 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617167 | T3 EI BRIDGEVILLE-GRBRVLL 2/4 RPL POLE | 70Y
LC | 123724850 | 005/139 | T3 EI COLGATE-GRS VLY 005/139 RPL INSW | SACTO | ETL.6490.INSL | 2022-05-31 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617974 | T3 EI COLGATE-GRASS VALEY 5/131 RPL INSW | 93I
LC | 123725221 | 011/255 | T3 DI DRM GRS VLY-WMR 11/255 INS HRDD | SACTO | ETL.6760.POLE.WOOD | 2022-05-31 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | Missing | Hardware-Wood | Install
LC | 123727684 | 042/308 | T3 DI CARIBOU-TABL MONTN 42/308 RMV NEST | TABLEMTN | ETL.4440.TOWR | 2022-06-01 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE COMP OH XMPT TR3 PRTO AIR FRAB | Debris/Nest/etc. | Structure-Steel | Remove
LC | 123728530 | 005/032 | T3 DI RND MTN TBL MN #1 5/32 SHLS COTTER | TABLEMTN | ETL.6060.TOWR | 2022-06-01 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45458791 | T3 DI RND MTN TBL MN #1 5/32 SHLS COTTER | ICS
LC | 123728549 | 004/031 | T3 DI BRUNSWICK #2TAP 004/031 RPL INSS | SACTO | ETL.1431.INSL | 2022-06-01 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31605337 | T3 DI BRUNSWICK #2 TAP RPL INSS 2TWR | 93K
LC | 123728868 | 022/177 | T3 DI MSRI FL-GLD HLL #1 22/177 REFRAME | SACTO | ETL.2660.POLE.NWOD | 2022-06-01 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Steel | Replace
LC | 123729326 | 022/000 | T3 DI MAPLE CREEK-HOOPA 22/0 RPR STRW | EUREKA | ETL.7490.POLE.WOOD | 2022-06-01 | 2022-05-10 |  | 2022-11-06 | 2022-11-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123730206 | 043/249 | T3 EI TEMBLR-SAN LS BISP 43/249 BNT STEL | PISMOBCH | ETL.3960.TOWR | 2022-06-01 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123730562 | 043/247 | T3 EI TEMBLR-SAN LS OBSP 43/247 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2022-06-01 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31611746 | T2 EI TMBLR-SN LS OBPO RPL INSS 8TWR | 93K
LC | 123731343 | 007/168 | T3 EI CLGTE-GRSS VLLY 7/168 RPR GYWW | SACTO | ETL.6490.POLE.NWOD | 2022-06-01 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123731710 | 026/382 | T3 DI GOLD HILL #1 26/382 RPL POLE | SACTO | ETL.6950.POLE.WOOD | 2022-06-01 | 2022-05-06 |  | 2022-11-02 | 2022-11-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606076 | T3 DI GLD HL #1 24/352 RPL STRW | 70Y
LC | 123731866 | 026/378 | T3 EI GLD HL #1 26/378 RPL STRW | SACTO | ETL.6950.POLE.WOOD | 2022-06-01 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31614770 | T3 WV GOLD HILL #1 12/192 RPL POLE | 70Y
LC | 123732388 | 024/105 | T3 EI MRRO BY-SLR SS #1 24/105 RPL INSS | PISMOBCH | ETL.5300.INSL | 2022-06-01 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31618211 | T2 EI MRO BAY-SOLAR SS #1 RPL INSS 7TWR | 93K
LC | 123732389 | 024/103 | T3 EI MRRO BY-SLR SS #2 24/103 RPL INSS | PISMOBCH | ETL.5310.INSL | 2022-06-01 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619692 | T3 EI MRRO BY-SLR SS #2 24/103 RPL INSS | 93K
LC | 123732413 | 024/103 | T3 EI MRRO BY-SLR SS #1 24/103 RPL INSS | PISMOBCH | ETL.5300.INSL | 2022-06-01 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31618211 | T2 EI MRO BAY-SOLAR SS #1 RPL INSS 7TWR | 93K
LC | 123732414 | 043/244 | T3 EI TEMBLR-SN LUIS BSP 43/244 RPL RPTS | PISMOBCH | ETL.3960.INSL.CERA | 2022-06-01 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 593 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Raptor Guard-Steel | Replace
LC | 123732415 | 043/245 | T3 EI TEMBLR-SAN LS OBSP 43/245 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2022-06-01 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31611746 | T2 EI TMBLR-SN LS OBPO RPL INSS 8TWR | 93K
LC | 123732416 | 043/245 | T3 EI TEMBLR-SN LUIS BSP 43/245 RPL RPTS | PISMOBCH | ETL.3960.INSL.CERA | 2022-06-01 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 593 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO | No Good/Out of Stdrd | Raptor Guard-Steel | Replace
LC | 123732430 | 024/105 | T3 EI MRRO BY-SLR SS #2 24/105 RPL INSS | PISMOBCH | ETL.5310.INSL | 2022-06-01 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619692 | T3 EI MRRO BY-SLR SS #2 24/103 RPL INSS | 93K
LC | 123734039 | 013/008 | T3 DI UKH HPLND CLVRDL 13/8 RPR GYWW | WILLITS | ETL.4050.POLE.NWOD | 2022-06-01 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45487398 | T3 DI UKH HPLND CLVRDL 13/8 RPR GYWW | ICW
LC | 123734092 | 008/222 | T3 DI COLGATE-ALLEGHANY 008/222 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-06-01 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31633457 | T3 DI COLGATE-ALLEGHANY 008/222 RPL STRW | 70Y
LC | 123734141 | 013/008 | T3 DI UKH HPLND CLVRDL 13/8 RPR STRW | WILLITS | ETL.4050.POLE.NWOD | 2022-06-01 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45487397 | T3 DI UKH HPLND CLVRDL 13/8 RPR STRW | ICW
LC | 123734145 | 013/008 | T3 DI UKH HPLND CLVRDL 13/8 RPR INSW | WILLITS | ETL.4050.INSL.NCER | 2022-06-01 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45487388 | T3 DI UKH HPLND CLVRDL 13/8 RPR INSW | ICW
LC | 123734173 | 007/198 | T3 DI COLGATE-ALLEGHANY 007/198 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-06-01 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31606404 | T3 COLGATE-ALLEGHANY 7/188 RPL POLE | 70Y
LC | 123734367 | 014/125 | T3 DI GRN VLLY-PAUL SWT 14/125 RPL HRDW | MOSSLNDG | ETL.1730.POLE.WOOD | 2022-06-01 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45617581 | T3 DI GRN VLLY-PAUL SWT 14/125 RPL HRDW | ICW
LC | 123734369 | 000/001 | T3 DI RINCON #2 TAP 0/1 RPL INSS | LAKEVLLE | ETL.1611.INSL.CERA | 2022-06-01 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace
LC | 123734654 | 018/002 | T3 DI MAPLE CREEK-HOOPA 18/2 RPL HRDD | EUREKA | ETL.7490.POLE.NWOD | 2022-06-01 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123734731 | 028/135 | T3 DI EXCHQER-INDN FLT 28/135 RPR INSS | FRESNO | ETL.8650.INSL.CERA | 2022-06-01 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45489454 | T3 DI EXCHQER-INDN FLT 28/135 RPR INSS | ICS
LC | 123734861 | 010/200 | T3 EI FRH MDWS-MDDL FRK 10/200 RPL INSW | SACTO | ETL.6870.INSL | 2022-06-01 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617969 | T3 DI FNCH MDWS MDDL FRK 6/117 RPL INSW | 93I
LC | 123737272 | 008/225 | T3 DI COLGATE-ALLEGHANY 008/225 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-06-02 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31633457 | T3 DI COLGATE-ALLEGHANY 008/222 RPL STRW | 70Y
LC | 123737437 | 010/186 | T3 DI FRNCH MDWS MDL FRK 10/186 REFRAME | SACTO | ETL.6870.POLE.WOOD | 2022-06-02 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31633954 | T3 DI FRNCH MDWS-MID FRK 4/91 REFRAME | 93E
LC | 123737952 | -017/007 | T3 DI FULTON-CALISTOGA -17/7 INS HRDW | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-06-02 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45485960 | T3 DI FULTON-CALISTOGA -17/7 INS HRDW | ICW
LC | 123738242 | 013/001 | T3 DI MAPLE CREEK-HOOPA 13/1 RPR INSW | EUREKA | ETL.7490.INSL.CERA | 2022-06-02 | 2022-05-10 |  | 2022-11-06 | 2022-11-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123738389 | 002/016 | T3 DI RND MTN-TBL MTN #2 2/16 RMV VEG | TABLEMTN | ETL.6070.TOWR | 2022-06-02 | 2022-05-30 |  | 2022-11-26 | 2022-11-30 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123738707 | 031/135 | T3 DI FLTN-LAKVLE-IGNCIO 31/135 RPR INSS | LAKEVLLE | ETL.4950.INSL.CERA | 2022-06-02 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575475 | T3 DI FLTN-LAKVLE-IGNCIO 31/135 RPR INSS | ICS
LC | 123738714 | 012/105 | T3 DI MDLE FRK-GLD HLL 12/105 RPL HRDW | SACTO | ETL.5140.POLE.STPS | 2022-06-02 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123738796 | 013/063 | T3 DI CNTRA-CSTA-MRGA#1 13/63 BNT STEEL | CONCORD | ETL.5452.TOWR | 2022-06-02 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123739460 | 004/024 | T3 DI EAGLE RK-FLTN-SLVRD 4/24 RPL HRDT | LAKEVLLE | ETL.4392.TOWR | 2022-06-02 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123740575 | 002/045 | T3 DI BURNS-LN STR #2 2/45 RPR SPLW | MOSSLNDG | ETL.6240.INSL.NCER | 2022-06-02 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45617582 | T3 DI BURNS-LN STR #2 2/45 RPR SPLW | ICW
LC | 123740830 | 042/242 | T3 EI TMBLR-SAN LUS OBIS 42/242 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2022-06-02 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31611746 | T2 EI TMBLR-SN LS OBPO RPL INSS 8TWR | 93K
LC | 123741181 | 003/012 | T3 DI BRIDGEVILLE-GARBERVL 3/12 RPR CRSW | EUREKA | ETL.6220.POLE.WOOD | 2022-06-02 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45640234 | T3 DI BRIDGEVILLE-GARBERVL 3/12 RPR CRSW | ICW
LC | 123741182 | 003/012 | T3 DI BRIDGEVILLE-GARBERVL 3/12 INS HRDD | EUREKA | ETL.6220.POLE.WOOD | 2022-06-02 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45640235 | T3 DI BRIDGEVILLE-GARBERVL 3/12 INS HRDD | ICW
LC | 123741534 | 001/011C | T3 DI GEYSERS #3-CLVRDL 001/11C RMV NEST | LAKEVLLE | ETL.1650.POLE.NWOD | 2022-06-02 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | Debris/Nest/etc. | Structure-Steel | Remove | 45575552 | T3 DI GEYSERS #3-CLVRDL 001/11C RMV NEST | ICS
LC | 123742514 | 004/052 | T3 DI DRUM-RIO OSO #2 4/52 RPR INSS | SACTO | ETL.1430.INSL.NCER | 2022-06-02 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123742670 | 008/069 | T3 DI MIDDLE FRK-GLD HLL 8/69 BNT STEEL | SACTO | ETL.5140.TOWR | 2022-06-02 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45600184 | T3 DI MIDDLE FRK-GLD HLL 8/69 BNT STEEL | ICQ
LC | 123743293 | 004/050 | T3 EI DRUM-SUMMIT #1 4/50C RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2022-06-02 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31618287 | T3 EI DRUM-SUMMIT #1 000/004L RPL POLE | 70Y
LC | 123743297 | 004/050 | T3 EI DRUM-SUMMIT #1 4/50R RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2022-06-02 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31618287 | T3 EI DRUM-SUMMIT #1 000/004L RPL POLE | 70Y
LC | 123743318 | 002/038 | T3 DI WEST PNT-VLLY SPRNGS 2/38 INS HRDW | VICTOR | ETL.8350.POLE.WOOD | 2022-06-02 | 2022-05-09 |  | 2022-11-05 | 2022-11-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45540264 | T3 DI WEST PNT-VLLY SPRNGS 2/38 INS HRDW | ICW
LC | 123744698 | 023/115 | T3 EI RND MTN-TBL MN #2 23/115 RPR ANCW | TABLEMTN | ETL.6070.TOWR | 2022-06-02 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Anchor-Steel | Repair | 45457611 | T3 EI RND MTN-TBL MN #2 23/115 RPR ANCW | ICS
LC | 123744699 | 001/008 | T3 DI DIABLO-GATES #1 1/008 RPR STRT | PISMOBCH | ETL.5960.TOWR | 2022-06-02 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123745151 | 013/007 | T3 DI MAPLE CREEK-HOOPA 13/7 RPL STRW | EUREKA | ETL.7490.POLE.WOOD | 2022-06-02 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace
LC | 123745329 | B022/491 | T3 DI DRM-GRSS VLLY-WMR B22/491 RPR GYWW | SACTO | ETL.6760.POLE.NWOD | 2022-06-02 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123745653 | 009/259 | T3 DI COLGATE-ALLEGHANY 9/259 INS HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-06-02 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123745654 | 003/002 | T3 DI WISHON-SAN JOAQUIN #3 3/2 INS RPTS | FRESNO | ETL.9340.POLE.NWOD | 2022-06-02 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 672 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3N PRTO AIR FRAB NTDE | Missing | Raptor Guard-Wood | Install
LC | 123745727 | 002/017 | T3 DI RND MTN-TBL MTN #1 2/17 RPR SHLS | TABLEMTN | ETL.6060.TOWR | 2022-06-02 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45458797 | T3 DI RND MTN-TBL MTN #1 2/17 RPR SHLS | ICS
LC | 123745728 | 002/017 | T3 DI RND MTN-TBL MTN #1 2/17 RPL INSS | TABLEMTN | ETL.6060.INSL | 2022-06-02 | 2022-05-31 |  | 2022-11-27 | 2022-12-01 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617248 | T3 DI RND MTN-TBL MTN #1 2/17 RPL INSS | 93K
LC | 123745760 | 002/017 | T3 DI RND MTN-TBL MTN #1 2/17 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2022-06-02 | 2022-05-31 |  | 2022-11-27 | 2022-12-01 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45458798 | T3 DI RND MTN-TBL MTN #1 2/17 RPR GYWS | ICS
LC | 123745776 | 013/002 | T3 DI MAPLE CREEK-HOOPA 13/2 RPL INSS | EUREKA | ETL.7490.INSL | 2022-06-02 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace
LC | 123746151 | 000/006C | T3 DI GEYSERS #3-EAGL RCK 0/6C RPR SHILD | LAKEVLLE | ETL.1660.POLE.NWOD | 2022-06-02 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45575553 | T3 DI GEYSERS #3-EAGL RCK 0/6C RPR SHILD | ICW
LC | 123747788 | 000/012 | T3 DI DRUM-SUMMIT #1 0/12L RPR POLE | SACTO | ETL.1440.POLE.STPS | 2022-06-03 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123747789 | 000/012 | T3 DI DRUM-SUMMIT #1 0/12R RPR POLE | SACTO | ETL.1440.POLE.STPS | 2022-06-03 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123747810 | -017/006 | T3 DI FULTON-CALISTOGA -017/006 RPR GYWW | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-06-03 | 2022-05-11 |  | 2022-11-07 | 2022-11-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45485888 | T3 DI FULTON-CALISTOGA -017/006 RPR GYWW | ICW
LC | 123747816 | 001/010 | T3 DI BRNSWCK #1 TAP 1/010 RPL DAMS | SACTO | ETL.1422.INSL | 2022-06-03 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 45456605 | T3 DI BRNSWCK #1 TAP 1/010 RPL DAMS | ICS
LC | 123747854 | 004/108 | T3 DI DEER CREEK-DRUM 4/108 RPR GYWW | SACTO | ETL.6690.POLE.NWOD | 2022-06-03 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123747878 | 005/005 | T3 DI DIABLO UNIT#2 NF 5/5 RPL INSS | PISMOBCH | ETL.5950.INSL | 2022-06-03 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31629144 | T3 DI DIABLO UNIT#2 NF RPL INSS | 93K
LC | 123747879 | 005/005 | T3 DI DIABLO UNIT#2 NF 5/5 RPR SHLS | PISMOBCH | ETL.5950.TOWR | 2022-06-03 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair
LC | 123747923 | :000/011 | T3 DI FULTON-PUEBLO :0/11 RPR POLE | LAKEVLLE | ETL.1600.POLE.NWOD | 2022-06-03 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAR | No Good/Out of Stdrd | Structure-Wood | Repair | 45571463 | T3 DI FULTON-PUEBLO :0/11 RPR POLE | ICW
LC | 123747938 | 005/031 | T3 DI RND MNT TBL MTN #2 5/31 RPL ANCS | TABLEMTN | ETL.6070.TOWR | 2022-06-03 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Steel | Replace
LC | 123747948 | 005/063 | T3 DI GEYSRS #3-CLVERDALE 5/63 RMV VEG | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-06-03 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123748092 | 011/250 | T3 DI DRM-GRSS VLLY-WMR 11/250 RPL HRDW | SACTO | ETL.6760.POLE.NWOD | 2022-06-03 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123748217 | 037/187 | T3 DI FULTON-PUEBLO 37/187 RPR STRT | LAKEVLLE | ETL.1600.TOWR | 2022-06-03 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123748378 | 000/020 | T3 DI PLUMAS SIERRA TAP 0/20 RPL HRDD | TABLEMTN | ETL.6291.POLE.WOOD | 2022-06-03 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123748389 | 002/016 | T3 DI MRGA-SN LENDRO#3 2/16 RUSTED STL | CONCORD | ETL.2790.TOWR | 2022-06-03 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123748443 | B024/533 | T3 DI DRM-GRS VLLY-WMR B24/533 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2022-06-03 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123748546 | 027/128 | T3 DI EXCHQR-IDN FT-YSMT 27/128 RPR INSS | FRESNO | ETL.8650.INSL.CERA | 2022-06-03 | 2022-05-12 |  | 2022-11-08 | 2022-11-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45489456 | T3 DI EXCHQR-IDN FT-YSMT 27/128 RPR INSS | ICS
LC | 123748605 | 003/004 | T3 DI FLTN-CLSTGA 003/004 RPL HRDD | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-06-03 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45575466 | T3 DI FLTN-CLSTGA 003/004 RPL HRDD | ICW
LC | 123748645 | 006/033 | T3 DI RND MTN-TBL MNT #2 6/33 RPR INSS | TABLEMTN | ETL.6070.INSL.CERA | 2022-06-03 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45457618 | T3 DI RND MTN-TBL MNT #2 6/33 RPR INSS | ICS
LC | 123748777 | 020/103 | T3 EI RND MTN-TBL MTN#2 20/103 RPR GYWS | TABLEMTN | ETL.6070.TOWR | 2022-06-03 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45457640 | T3 EI RND MTN-TBL MTN#2 20/103 RPR GYWS | ICS
LC | 123748804 | 010/203 | T3 DI FRNCH MDWS-MDDL FK 10/203 RPR GYWW | SACTO | ETL.6870.POLE.WOOD | 2022-06-03 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123748836 | 006/031 | T3 DI EAGLE RK-FLTN-SLVRDO 6/31 RPR STRT | LAKEVLLE | ETL.4392.TOWR | 2022-06-03 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123748838 | 006/031 | T3 DI EAGLE RK-FLTN-SLVRDO 6/31 RMV VEG | LAKEVLLE | ETL.4392.TOWR | 2022-06-03 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123748990 | 006/031 | T3 DI EAGLE RK-FLTN-SLVRDO 6/31 RPR INSS | LAKEVLLE | ETL.4392.INSL.CERA | 2022-06-03 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575433 | T3 DI EAGLE RK-FLTN-SLVRDO 6/31 RPR INSS | ICS
LC | 123749161 | 023/004 | T3 DI MAPLE CREEK-HOOPA 23/4 RPL HRDW | EUREKA | ETL.7490.POLE.WOOD | 2022-06-03 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123749251 | 023/004 | T3 DI MAPLE CREEK-HOOPA 23/4 RPR SPLW | EUREKA | ETL.7490.INSL | 2022-06-03 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 123749264 | ?010/005 | T3 DI SNEATH LANE-HMB ?10/4 COTR KEY | METCALF | ETL.7212.INSL.NCER | 2022-06-03 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace | 45600657 | T3 DI SNEATH LANE-HMB ?10/4 COTR KEY | ICW
LC | 123749462 | 001/011 | T3 DI DIABLO-GATES #1 1/11 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2022-06-03 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123749498 | 004/048 | T3 DI GYSRS #3-CLVRDL 004/048 RPR HRDW | LAKEVLLE | ETL.1650.POLE.STPS | 2022-06-03 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | Missing | Hardware-Wood | Install | 45449995 | T3 DI GYSRS #3-CLVRDL 004/048 RPR HRDW | ICW
LC | 123749988 | 015/002 | T3 WV LAURELES-OTTER 15/2 INS DMPW | MOSSLNDG | ETL.7380.INSL.NCER | 2022-06-03 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH FMOB XMPT TR3 PRTO NTDE | Missing | Damper-Wood | Install
LC | 123750086 | ?006/000 | T3 DI SNTH LN HLF MN BY 6/0 RPR POLE | METCALF | ETL.7212.POLE.WOOD | 2022-06-03 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45600658 | T3 DI SNTH LN HLF MN BY 6/0 RPR POLE | ICW
LC | 123750089 | ?006/000 | T3 DI SNTH LN HLF MN BY ?6/0 RPR GYWW | METCALF | ETL.7212.POLE.WOOD | 2022-06-03 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45600659 | T3 DI SNTH LN HLF MN BY ?6/0 RPR GYWW | ICW
LC | 123750116 | 006/033 | T3 DI RND MTN-TBL MNT #1 6/33 RPR SHIELD | TABLEMTN | ETL.6060.INSL | 2022-06-03 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45458884 | T3 DI RND MTN-TBL MNT #1 6/33 RPR SHIELD | ICS
LC | 123750119 | 006/033 | T3 DI RND MTN-TBL MNT #1 6/33 RPL INSS | TABLEMTN | ETL.6060.INSL | 2022-06-03 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617248 | T3 DI RND MTN-TBL MTN #1 2/17 RPL INSS | 93K
LC | 123750162 | 006/033 | T3 DI RND MTN-TBL MNT #1 6/33 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2022-06-03 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45458885 | T3 DI RND MTN-TBL MNT #1 6/33 RPR GYWS | ICS
LC | 123750390 | 011/006 | T3 EI BRIDGEVILLE-GARBERVL 11/6 RPR GYWW | EUREKA | ETL.6220.POLE.WOOD | 2022-06-03 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45640236 | T3 EI BRIDGEVILLE-GARBERVL 11/6 RPR GYWW | ICW
LC | 123750412 | 004/008 | T3 DI DONNELLS-MI-WUK 004/008L RPL STRW | VICTOR | ETL.1400.POLE.WDPS | 2022-06-03 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31610969 | T3 DI DONNELLS-MI-WUK 004/008R RPL STRW | 70Y
LC | 123750416 | 004/008 | T3 DI DONNELLS-MI-WUK 004/008R RPL STRW | VICTOR | ETL.1400.POLE.WDPS | 2022-06-03 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31610969 | T3 DI DONNELLS-MI-WUK 004/008R RPL STRW | 70Y
LC | 123750549 | 000/011 | T3 DI MORGA-SN LENDRO #3 0/11 RUSTED STL | CONCORD | ETL.2790.TOWR | 2022-06-03 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123750962 | 000/007 | T3 DI MORAGA-OAKLAND #1 0/7 INS HRDT | CONCORD | ETL.2720.TOWR | 2022-06-03 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install
LC | 123750978 | 022/111 | T3 EI RND MTN-TBL MTN#2 21/111 RPR GYWS | TABLEMTN | ETL.6070.TOWR | 2022-06-03 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45457648 | T3 EI RND MTN-TBL MTN#2 21/111 RPR GYWS | ICS
LC | 123751279 | ?007/007 | T3 DI SNEATH LANE-HMB ?7/7 COTR KEY | METCALF | ETL.7212.INSL.NCER | 2022-06-03 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45600680 | T3 DI SNEATH LANE-HMB ?7/7 COTR KEY | ICW
LC | 123751696 | 002/019 | T3 DI MORAGA-CLAREMONT #2 2/19 RPR INSS | CONCORD | ETL.2710.INSL.NCER | 2022-06-03 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45503489 | T3 DI MORAGA-CLAREMONT #2 2/19 RPR INSS | ICS
LC | 123751749 | B017/397 | T3 DI DRM-GRSS VLLY-WMR B17/397 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2022-06-03 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31631449 | T2 EI DRUM-GRSS VLLY-WMR 18/427 RPL POLE | 70Y
LC | 123751941 | B017/397 | T3 DI DRM-GRSS VLLY-WMR B17/397 RPL HRDW | SACTO | ETL.6760.POLE.WOOD | 2022-06-03 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123752101 | 002/014 | T3 DI SAN RMN-MRGA 002/014 RPL INSS | CONCORD | ETL.5660.INSL.CERA | 2022-06-03 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615181 | T3 DI SN RAMON-MORAGA RPL INSS 3TWR | 93K
LC | 123752229 | 002/010 | T3 DI GEYSERS #12-FULTON 02/010 RPR INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2022-06-03 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571465 | T3 DI GEYSERS #12-FULTON 02/010 RPR INSS | ICS
LC | 123752350 | 002/010 | T3 DI GEYSERS #9-LAKEVILLE 2/10 RPR INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2022-06-03 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123752445 | 010/109 | T3 DI DRM RIO OSO #1 10/109L RMV FOND | SACTO | ETL.1420.POLE.STPS | 2022-06-03 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45599994 | T3 DI DRM RIO OSO #1 10/109L RMV FOND | ICQ
LC | 123752763 | 002/014C | T3 DI KANAKA TAP 2/14C RPR STRW | TABLEMTN | ETL.4223.POLE.WOOD | 2022-06-03 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123753030 | 002/014B | T3 DI KANAKA TAP 2/14B RPL HRDW | TABLEMTN | ETL.4223.POLE.WOOD | 2022-06-03 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123753144 | 147 | T3 DI DONNELLS-MI-WUK 7/5 RPR SWTC | VICTOR | ETL.1400.SWIT | 2022-06-03 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 623 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | Out of Adjustment | Switch | Repair | 45519321 | T3 DI DONNELLS-MI-WUK 7/5 RPR SWTC | ICE
LC | 123753259 | 009/005 | T3 DI POTTER VALLEY-WILLITS 9/5 RPR SPLW | WILLITS | ETL.7820.INSL.NCER | 2022-06-03 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair
LC | 123753374 | 009/005 | T3 DI POTTER VALLEY-WILLITS 9/5 RPL HRDW | WILLITS | ETL.7820.POLE.WOOD | 2022-06-03 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123758044 | 003/023 | T3 DI MRGA SAN LNDRO #3 3/23 RMV VEG | CONCORD | ETL.2790.TOWR | 2022-06-03 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123758266 | 007/006C | T3 DI DNNLLS-MI-WUK 7/006C RPR ANCW | VICTOR | ETL.1400.POLE.WOOD | 2022-06-03 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Anchor-Wood | Repair | 45519322 | T3 DI DNNLLS-MI-WUK 7/006C RPR ANCW | ICW
LC | 123758640 | :001/007A | T3 DI EAGLE ROCK-REDBUD :1/7A RPL HRDW | WILLITS | ETL.1480.POLE.NWOD | 2022-06-03 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Steel | Install | 45582050 | T3 DI EAGLE ROCK-REDBUD :1/7A RPL HRDW | ICS
LC | 123758732 | 013/107 | T3 DI MNT VST BRNS 13/107 RPL HRDD | MOSSLNDG | ETL.7590.POLE.WOOD | 2022-06-03 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45617585 | T3 DI MNT VST BRNS 13/107 RPL HRDD | ICW
LC | 123758765 | 002/016 | T3 DI RND MTN-TABLE MTN#1 2/16 RPR OPGW | TABLEMTN | ETL.6060.INSL | 2022-06-03 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45458888 | T3 DI RND MTN-TABLE MTN#1 2/16 RPR OPGW | ICS
LC | 123759128 | 009/011 | T3 EI BRIDGEVILLE-GARBERVL 9/11 RPR POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-06-03 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45640237 | T3 EI BRIDGEVILLE-GARBERVL 9/11 RPR POLE | ICW
LC | 123759259 | 009/008 | T3 EI BRIDGVLLE-GARBERVLLE 9/8 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-06-03 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611487 | T3 EI BRIDGVLLE-GARBERVLLE 9/8 RPL POLE | 70Y
LC | 123759260 | 009/010 | T3 EI BRIDGVLLE-GARBERVLLE 9/10 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-06-03 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611487 | T3 EI BRIDGVLLE-GARBERVLLE 9/8 RPL POLE | 70Y
LC | 123759271 | 011/000 | T3 EI BRIDGVLLE-GARBERVLLE 11/0 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-06-03 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606888 | T2 DI BRDGVLLE-GRBRVLLE 11/7 RPL STRW | 70Y
LC | 123759272 | 009/013 | T3 EI BRIDGVLLE-GARBERVLLE 9/13 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-06-03 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611487 | T3 EI BRIDGVLLE-GARBERVLLE 9/8 RPL POLE | 70Y
LC | 123761843 | 003/068 | T3 EI FRCH MDWS-MDL FRK 3/68 RPR STRW | SACTO | ETL.6870.POLE.WOOD | 2022-06-04 | 2022-06-04 |  | 2022-12-01 | 2022-12-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123763001 | 012/220 | T3 EI COLGTE-CHALLNGE 12/220 RPR GYWW | SACTO | ETL.6480.POLE.NWOD | 2022-06-04 | 2022-06-04 |  | 2022-12-01 | 2022-12-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123765596 | 000/014 | T3 DI DRUM-SPAULDING 0/14 RPL POLE | SACTO | ETL.6770.POLE.WOOD | 2022-06-05 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31618852 | T3 DI DRUM-SPAULDING 0/14 RPL POLE | 70Y
LC | 123765699 | 003/041 | T3 DI DRUM-RIO OSO #1 3/41 RPL HRDT | SACTO | ETL.1420.TOWR | 2022-06-05 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45599416 | T3 DI DRUM-RIO OSO #1 3/41 RPL HRDT | ICQ
LC | 123766363 | 035/175 | T3 DI FULTON-PUEBLO 35/175 RPR FND | LAKEVLLE | ETL.1600.TOWR | 2022-06-05 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123766459 | 020/164 | T3 DI MDLE FRK-GLD HIL 20/164 RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2022-06-05 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123767732 | A014/121 | T3 MNTA VSTA-BURNS A14/121 RPL STRW | MOSSLNDG | ETL.7590.POLE.WOOD | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611514 | T3 MNTA VSTA-BURNS A14/121 RPL STRW | 70Y
LC | 123769077 | 000/004 | T3 DI DIABLO-GATES#1 0/004 RPR FOND | PISMOBCH | ETL.5960.TOWR | 2022-06-06 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123769140 | 002/016 | T3 DI DIABLO-GATES #1 2/016 RPR SHLS | PISMOBCH | ETL.5960.TOWR | 2022-06-06 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45592093 | T3 DI DIABLO-GATES #1 2/016 RPR SHLS | ICS
LC | 123769661 | 017/071 | T3 DI DIABLO-GATES#1 17/071 RPR GYWS | PISMOBCH | ETL.5960.TOWR | 2022-06-06 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123769949 | 005/007B | T3 DI DIABLO UNIT #2 5/7B INS HRDT | PISMOBCH | ETL.5950.TOWR | 2022-06-06 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install | 45542010 | T3 DI DIABLO UNIT #2 5/7B INS HRDT | ICQ
LC | 123769950 | 013/147 | T3 EI IGNACIO-BOLINAS #1 13/147 RPR CNDW | LAKEVLLE | ETL.7140.INSL | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Conductor-Wood | Repair | 45486131 | T3 EI IGNACIO-BOLINAS #1 13/147 RPR CNDW | ICW
LC | 123770052 | 004/051 | T3 DI DRUM-RIO OSO #1 4/51 RPL HRDT | SACTO | ETL.1420.TOWR | 2022-06-06 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45599419 | T3 DI DRUM-RIO OSO #1 4/51 RPL HRDT | ICQ
LC | 123770198 | 026/286 | T3 EI IGNACIO-BLINAS #2 26/286 WASH INSW | LAKEVLLE | ETL.7180.INSL.CERA | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 622 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | Contaminated | Insulator | Ground Wash | 45486094 | T3 EI IGNACIO-BLINAS #2 26/286 WASH INSW | ICD
LC | 123770229 | 026/286 | T3 EI IGNACIO-BOLINAS #2 26/286 RMV VEG | LAKEVLLE | ETL.7180.POLE.WDPS | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO | Overgrown | Vegetation | Remove
LC | 123770353 | 005/007A | T3 DI DIABLO UNIT #2 5/7A RPR SHLS | PISMOBCH | ETL.5950.TOWR | 2022-06-06 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE COMP OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair
LC | 123770799 | 002/015 | T3 DI DIABLO-GATES#1 2/015 RPL INSS | PISMOBCH | ETL.5960.INSL | 2022-06-06 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31618032 | T3 DI DIABLO-GATES#1 2/015 RPL INSS | 93K
LC | 123770863 | 001/012 | T3 EI IGNACIO-SN RFL #1 1/12 RPL INSS | LAKEVLLE | ETL.1850.INSL | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31634460 | T3 EI IGNACIO-SN RFL #1 1/12 RPL INSS | 93K
LC | 123771138 | 026/285 | T3 EI IGNACIO-BOLINAS #2 26/285 RPR GYWW | LAKEVLLE | ETL.7180.POLE.STPS | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45486099 | T3 EI IGNACIO-BOLINAS #2 26/285 RPR GYWW | ICW
LC | 123771166 | 026/285 | T3 EI IGNACIO-BOLINAS #2 026/285 RMV VEG | LAKEVLLE | ETL.7180.POLE.STPS | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | Overgrown | Vegetation | Trim
LC | 123771614 | 001/011 | T3 EI IGNACIO-SAN RFL #1 1/11 RPL INSS | LAKEVLLE | ETL.1850.INSL | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31607836 | T3 EI IGNACIO-SAN RFL #1 RPL INSS 4TWR | 93K
LC | 123771896 | 013/142 | T3 EI IGNCIO-BLNAS #1 13/142L RPR GYWW | LAKEVLLE | ETL.7140.POLE.STPS | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45486127 | T3 EI IGNCIO-BLNAS #1 13/142L RPR GYWW | ICW
LC | 123772045 | 013/142 | T3 EI IGNCIO-BLNAS #1 13/142C RPR GYWW | LAKEVLLE | ETL.7140.POLE.STPS | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45486128 | T3 EI IGNCIO-BLNAS #1 13/142C RPR GYWW | ICW
LC | 123772178 | 013/142 | T3 EI IGNCIO-BLNAS #1 13/142R RPR GYWW | LAKEVLLE | ETL.7140.POLE.STPS | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45486126 | T3 EI IGNCIO-BLNAS #1 13/142R RPR GYWW | ICW
LC | 123772597 | 005/059 | T3 DI DRUM-RIO OSO #1 5/59 RPR JMPW | SACTO | ETL.1420.INSL.CERA | 2022-06-06 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Steel | Repair
LC | 123772719 | 028/231 | T3 EI RND MTN-CTNWOOD #3 28/231 RPR ANCS | TABLEMTN | ETL.5650.POLE.STPS | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO | No Good/Out of Stdrd | Anchor-Steel | Repair
LC | 123772797 | 010/045 | T3 DI MRG CSTR VLY 10/45 RPL INSS | CONCORD | ETL.5250.INSL | 2022-06-06 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617072 | T3 DI MRAGA-CSTRO VLLY RPL INSS 2TWR | 93K
LC | 123772980 | A005/052C | T3 DI DRM HGNS A5/52C RPR STRW | SACTO | ETL.4393.POLE.WOOD | 2022-06-06 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123773109 | 004/024 | T3 DI EAGLE RK-FLTN-SLVRD 4/24 RPR INSS | LAKEVLLE | ETL.4392.INSL.CERA | 2022-06-06 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575432 | T3 DI EAGLE RK-FLTN-SLVRD 4/24 RPR INSS | ICS
LC | 123773166 | 025/284 | T3 EI IGNACIO-BOLINAS #2 25/284 RMV VEG | LAKEVLLE | ETL.7180.POLE.WDPS | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO | Overgrown | Vegetation | Remove
LC | 123773382 | 013/141 | T3 EI IGNACIO-BOLINAS #1 13/141 RMV VEG | LAKEVLLE | ETL.7140.POLE.STPS | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | Overgrown | Vegetation | Trim
LC | 123773660 | 004/047 | T3 EI DRUM-RIO OSO #2 4/47 ARMOR ROD | SACTO | ETL.1430.INSL | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair
LC | 123773893 | 008/232 | T3 DI COLGATE-ALLEGHANY 008/232 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-06-06 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31633457 | T3 DI COLGATE-ALLEGHANY 008/222 RPL STRW | 70Y
LC | 123773898 | A005/052A | T3 DI DRUM-HIGGINS A5/52A RPL HRDD | SACTO | ETL.4393.POLE.WOOD | 2022-06-06 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123773932 | 003/039 | T3 EI IGNACIO-BOLINAS #1 3/39 COTTER | LAKEVLLE | ETL.7140.INSL.NCER | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45486004 | T3 EI IGNACIO-BOLINAS #1 3/39 COTTER | ICS
LC | 123773933 | 003/038 | T3 EI IGNACIO-BOLINAS #1 3/38 RPR CRSW | LAKEVLLE | ETL.7140.POLE.WOOD | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45486000 | T3 EI IGNACIO-BOLINAS #1 3/38 RPR CRSW | ICW
LC | 123774356 | 012/096 | T3 DI MNT VST BRNS 12/96 RPR INSW | MOSSLNDG | ETL.7590.INSL.NCER | 2022-06-06 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45617587 | T3 DI MNT VST BRNS 12/96 RPR INSW | ICW
LC | 123775146 | 004/051A | T3 EI DRUM-RIO OSO #1 4/51A RPL HRDS | SACTO | ETL.1420.POLE.STPS | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP CPUA OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Steel | Replace
LC | 123775149 | 025/282 | T3 EI IGNACIO-BOLINAS #2 25/282 RPL INSW | LAKEVLLE | ETL.7180.INSL.CERA | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617019 | T3 DI IGNACIO-BLNS #2 20/229 RPL INSW | 93I
LC | 123775589 | 025/281 | T3 EI IGNACIO-BOLINAS #2 25/281 RPL INSW | LAKEVLLE | ETL.7180.INSL.CERA | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617019 | T3 DI IGNACIO-BLNS #2 20/229 RPL INSW | 93I
LC | 123775883 | 004/079 | T3 EI FRCH MDWS-MDL FRK 4/79 RPR STRW | SACTO | ETL.6870.POLE.WOOD | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123775884 | 004/083 | T3 EI FRCH MDWS-MDL FRK 4/83 RPR INSW | SACTO | ETL.6870.INSL.NCER | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123775885 | 004/080 | T3 EI FRCH MDWS-MDL FRK 4/80 RPL POLE | SACTO | ETL.6870.POLE.WOOD | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31614152 | T3 EI FRCH MDWS-MDL FRK 4/80 RPL POLE | 70Y
LC | 123776454 | 008/124 | T3 EI MIDDLE FORK #1 8/124 RPR ANCW | SACTO | ETL.8405.POLE.WOOD | 2022-06-06 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123777125 | 005/002 | T3 DI DIABLO UNIT#1 TIE 5/2 RPL HRDT | PISMOBCH | ETL.5940.TOWR | 2022-06-07 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123777179 | 003/022 | T3 DI BRUNSWICK #2 TAP 003/022 RPR JMPS | SACTO | ETL.1431.INSL | 2022-06-07 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Steel | Repair | 45456608 | T3 DI BRUNSWICK #2 TAP 003/022 RPR JMPS | ICS
LC | 123777295 | ?006/009 | T3 DI SNTH LN-HALF MON BAY ?6/9 RPL INSW | METCALF | ETL.7212.INSL.NCER | 2022-06-07 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31612284 | T3 DI SNTH LN-HALF MON BAY ?6/9 RPL INSW | 93I
LC | 123777480 | 003/022 | T3 DI BRUNSWCK #1 TAP 3/22 RPL HRDT | SACTO | ETL.1422.TOWR | 2022-06-07 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45582378 | T3 DI BRUNSWCK #1 TAP 3/22 RPL HRDT | ICQ
LC | 123777704 | 004/050 | T3 EI DRUM-RIO OSO #2 4/50 RPR COND | SACTO | ETL.1430.INSL | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair
LC | 123777957 | X000/002 | T3 DI DIABLO-MESA X000/002 RPL INSS | PISMOBCH | ETL.4620.INSL.CERA | 2022-06-07 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31601767 | T2 EI DIABLO-MESA RPL INSS 3TWR | 93K
LC | 123777971 | 013/137 | T3 EI IGNACIO-BOLINAS #1 13/137 RPL ANCW | LAKEVLLE | ETL.7140.POLE.WOOD | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31617010 | T3 EI IGNACIO-BOLINAS #1 13/137 RPL ANCW | 93E
LC | 123778171 | 012/004 | T3 DI MONTE RIO-FULTON 12/4 RPL INSW | LAKEVLLE | ETL.7630.INSL | 2022-06-07 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31624226 | T3 DI MONTE RIO-FULTON 12/4 RPL INSW | 93I
LC | 123778380 | 006/044 | T3 DI MRG SN LNDR #3 6/44 INS HRDT | CONCORD | ETL.2790.TOWR | 2022-06-07 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR FRAB | Missing | Hardware-Tower | Install
LC | 123778384 | 006/044 | T3 DI MRG SN LNDR #3 6/44 RPR INSS | CONCORD | ETL.2760.INSL | 2022-06-07 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45502971 | T3 DI MRG SN LNDR #3 6/44 RPR INSS | ICS
LC | 123778463 | ?009/002 | T3 DI SNTH LN-HLF MN BY ?9/2 RPL HRDD | METCALF | ETL.7212.POLE.WOOD | 2022-06-07 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCH OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45600684 | T3 DI SNTH LN-HLF MN BY ?9/2 RPL HRDD | ICW
LC | 123778658 | 017/149 | T3 DI MSSURI FLT-GLD HIL#1 17/149 RPR ST | SACTO | ETL.2660.TOWR | 2022-06-07 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45341212 | T3 DI MSSURI FLT-GLD HIL#1 17/149 | ICQ
LC | 123778825 | 003/076 | T3 DI DRM SPLDNG 3/76 RPR GYWW | SACTO | ETL.6770.POLE.NWOD | 2022-06-07 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123778832 | 004/051A | T3 EI DRUM-RIO OSO #2 4/51A COTTER | SACTO | ETL.1430.INSL.NCER | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123779890 | 002/015 | T3 DI RND MTN-TBL MTN #1 2/15 RPL SHLS | TABLEMTN | ETL.6060.TOWR | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 45458895 | T3 DI RND MTN-TBL MTN #1 2/15 RPL SHLS | ICS
LC | 123780175 | 005/003C | T3 DI DIABLO UNT #1 5/3C RPR SHLS | PISMOBCH | ETL.5940.TOWR | 2022-06-07 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair
LC | 123780237 | 005/109 | T3 EI FNCH MDWS-MDL FRK 5/109 RMV TREE | SACTO | ETL.6870.POLE.WOOD | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123780372 | 025/278 | T3 EI IGNACIO-BOLINAS #2 25/278 RPL INSW | LAKEVLLE | ETL.7180.INSL.CERA | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617019 | T3 DI IGNACIO-BLNS #2 20/229 RPL INSW | 93I
LC | 123780906 | 025/277 | T3 EI IGNACIO-BOLINAS #2 025/277 RMV VEG | LAKEVLLE | ETL.7180.POLE.WDPS | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO | Overgrown | Vegetation | Remove
LC | 123780977 | 005/003 | T3 DI DONNELLS-MI-WUK 005/003 RPL HRDD | VICTOR | ETL.1400.POLE.WDPS | 2022-06-07 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45519323 | T3 DI DONNELLS-MI-WUK 005/003 RPL HRDD | ICW
LC | 123781102 | 001/013 | T3 DI MRGA SAN LNDRO #1 1/13 BENT STEEL | CONCORD | ETL.2770.TOWR | 2022-06-07 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123781268 | 000/019 | T3 EI PINE GROVE TAP 0/19 RPR STRW | VICTOR | ETL.8351.POLE.WOOD | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45519324 | T3 EI PINE GROVE TAP 0/19 RPR STRW | ICW
LC | 123781401 | X001/009 | T3 DI DIABLO-MESA X001/009 RPR SHIELD | PISMOBCH | ETL.4620.TOWR | 2022-06-07 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair
LC | 123781404 | X001/009 | T3 DI MORRO BAY-DIABLO X001/009 RPR INSS | PISMOBCH | ETL.5260.INSL.NCER | 2022-06-07 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123781691 | 024/276 | T3 EI IGNACO-BOLNAS #2 24/276 ANTI SPLIT | LAKEVLLE | ETL.7180.POLE.WDPS | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45486120 | T3 EI IGNACO-BOLNAS #2 24/276 ANTI SPLIT | ICW
LC | 123781729 | 024/276 | T3 EI IGNACO-BOLNS #2 24/276R ANTI SPLIT | LAKEVLLE | ETL.7180.POLE.WDPS | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45486095 | T3 EI IGNACO-BOLNS #2 24/276R ANTI SPLIT | ICW
LC | 123781760 | 024/276 | T3 EI IGNACIO-BOLINAS #2 24/276 RPL INSW | LAKEVLLE | ETL.7180.INSL.CERA | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617012 | T3 EI IGNACIO-BOLINAS #2 24/276 RPL INSW | 93I
LC | 123781774 | 000/008 | T3 DI DRUM-SUMMIT #2 0/8L RPR ANCW | SACTO | ETL.1450.POLE.STPS | 2022-06-07 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123781958 | 005/059A | T3 DI DRUM-RIO OSO #1 005/059A MASTIC | SACTO | ETL.1420.POLE.STPS | 2022-06-07 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45599984 | T3 DI DRUM-RIO OSO #1 005/059A MASTIC | ICQ
LC | 123782377 | 005/003B | T3 DI DIABLO-UNIT #1 5/3B RPR SHLS | PISMOBCH | ETL.5940.TOWR | 2022-06-07 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair
LC | 123782425 | 008/118 | T3 EI MIDDLE FORK #1+ 008/118 RPR STRW | SACTO | ETL.8405.POLE.WOOD | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45616122 | T3 EI MIDDLE FORK #1+ 008/118 RPR STRW | ICW
LC | 123782838 | 006/177 | T3 DI COLGATE-ALLEGHANY 6/177 RPR GYWW | SACTO | ETL.6470.POLE.NWOD | 2022-06-07 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123783147 | 022/097 | T3 EI MRO BY-SLR SW ST #1 22/97 RPL INSS | PISMOBCH | ETL.5300.INSL | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31618211 | T2 EI MRO BAY-SOLAR SS #1 RPL INSS 7TWR | 93K
LC | 123783148 | 022/096 | T3 EI MRO BAY-SOLAR SS #2 22/96 RPL INSS | PISMOBCH | ETL.5310.INSL | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619692 | T3 EI MRRO BY-SLR SS #2 24/103 RPL INSS | 93K
LC | 123783149 | 022/096 | T3 EI MRO BY-SLR SW ST #1 22/96 RPL INSS | PISMOBCH | ETL.5300.INSL | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31618211 | T2 EI MRO BAY-SOLAR SS #1 RPL INSS 7TWR | 93K
LC | 123783150 | 022/097 | T3 EI MRO BAY-SOLAR SS #2 22/97 RPL INSS | PISMOBCH | ETL.5310.INSL | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619692 | T3 EI MRRO BY-SLR SS #2 24/103 RPL INSS | 93K
LC | 123783153 | 022/095 | T3 EI MRO BAY-SOLAR SS #2 22/95 RPL INSS | PISMOBCH | ETL.5310.INSL | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619692 | T3 EI MRRO BY-SLR SS #2 24/103 RPL INSS | 93K
LC | 123783215 | 000/005 | T3 DI SNTA FE GEOTHRML TAP 0/5 RPR SHLD | LAKEVLLE | ETL.4782.TOWR | 2022-06-07 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45575645 | T3 DI SNTA FE GEOTHRML TAP 0/5 RPR SHLD | ICS
LC | 123783734 | 006/123 | T3 EI FRCH MDWS-MDL FRK 6/123 RPR INSW | SACTO | ETL.6870.INSL.NCER | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123784164 | 005/030 | T3 DI RND MTN-TABLE MTN#2 05/30 RPR INSS | TABLEMTN | ETL.6070.INSL.CERA | 2022-06-07 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45457654 | T3 DI RND MTN-TABLE MTN#2 05/30 RPR INSS | ICS
LC | 123784198 | 005/122 | T3 DI DRM-GRSS VLLY WMR 5/122 RMV BUTT | SACTO | ETL.6760.POLE.WOOD | 2022-06-07 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Wood | Remove
LC | 123784334 | 014/006 | T3 DI DONNELLS-MI-WUK 14/6R RPR POLE | VICTOR | ETL.1400.POLE.STPS | 2022-06-07 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Structure-Wood | Repair | 45519327 | T3 DI DONNELLS-MI-WUK 14/6R RPR POLE | ICW
LC | 123784392 | 025/199 | T3 DI CRBRRY SS-RND MTN 25/199 RPL HRDT | TABLEMTN | ETL.5410.TOWR | 2022-06-07 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45582690 | T3 DI CRBRRY SS-RND MTN 25/199 RPL HRDT | ICQ
LC | 123784398 | 025/199 | T3 DI CRBRRY SS-RND MTN 25/199 RPR STRT | TABLEMTN | ETL.5410.TOWR | 2022-06-07 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45582691 | T3 DI CRBRRY SS-RND MTN 25/199 RPR STRT | ICQ
LC | 123784492 | 010/272 | T3 DI CLGT-ALLGHNY 10/272 RPR INSW | SACTO | ETL.6470.INSL.NCER | 2022-06-07 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123784527 | 006/028 | T3 DI GEYSERS #9-LAKEVILLE 6/28 COTR KEY | LAKEVLLE | ETL.4780.INSL.NCER | 2022-06-07 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Steel | Replace | 45575581 | T3 DI GEYSERS #9-LAKEVILLE 6/28 COTR KEY | ICS
LC | 123784529 | 006/028 | T3 DI EAGLE RCK-FLTN-SILVR 6/28 COTR KEY | LAKEVLLE | ETL.4392.INSL.CERA | 2022-06-07 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW ACCL OH TR3 PRTO AIR | Missing | Hardware-Steel | Install | 45575431 | T3 DI EAGLE RCK-FLTN-SILVR 6/28 COTR KEY | ICS
LC | 123784730 | 021/110 | T3 DI RND MTN-TBL MTN #2 21/110 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2022-06-07 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123784754 | 026/002 | T3 DI FLTN-HPLND 026/002 RPR INSW | LAKEVLLE | ETL.6890.INSL | 2022-06-07 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45575473 | T3 DI FLTN-HPLND 026/002 RPR INSW | ICW
LC | 123784755 | 026/002 | T3 DI FLTN-HPLND 026/002 RPR GYWW | LAKEVLLE | ETL.6890.POLE.WOOD | 2022-06-07 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45575472 | T3 DI FLTN-HPLND 026/002 RPR GYWW | ICW
LC | 123784760 | 000/017 | T3 DI BURNS-LONE STAR #2 0/17 RPL SPLW | MOSSLNDG | ETL.6240.INSL.NCER | 2022-06-07 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Replace | 45617588 | T3 DI BURNS-LONE STAR #2 0/17 RPL SPLW | ICW
LC | 123785832 | 012/099 | T3 MIDDLE FRK-GLD HLL 12/99 RPL XARM | SACTO | ETL.5140.POLE.STPS | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH XMPT TR3 PRTO | No Good/Out of Stdrd | Crossarm-Wood | Replace
LC | 123785866 | 000/003 | T3 DI GEYSERS #12-FULTON 0/3 RPR INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2022-06-08 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571464 | T3 DI GEYSERS #12-FULTON 0/3 RPR INSS | ICS
LC | 123786104 | 004/023 | T3 DI EGL RK-FLTN SLVDO 004/023 RPL HRDT | LAKEVLLE | ETL.4392.TOWR | 2022-06-08 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123786370 | 008/127 | T3 EI WEIMAR #1 008/127 RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31629060 | T2 DI WEIMAR #1 004/059 RPL POLE | 70Y
LC | 123786422 | 001/027 | T3 DI KESWICK-TRINITY 1/27 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2022-06-08 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123786424 | 001/027 | T3 DI KESWICK-TRINITY 1/27 RPR CNDW | TABLEMTN | ETL.7270.INSL.NCER | 2022-06-08 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair
LC | 123786425 | 001/027 | T3 DI KESWICK-TRINITY 1/27 RPL DAMW | TABLEMTN | ETL.7270.INSL.NCER | 2022-06-08 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace
LC | 123786528 | 004/094 | T3 DI BURNS-LONE STAR #2 004/94 RPL HRDW | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-06-08 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45617591 | T3 DI BURNS-LONE STAR #2 004/94 RPL HRDW | ICW
LC | 123786828 | 001/024 | T3 DI DRUM-SPAULDING 1/24 RPR GYWW | SACTO | ETL.6770.POLE.NWOD | 2022-06-08 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123786875 | 003/030 | T3 EI TIGR CRK-VLEY SPRIN 3/30 RPL INSS | VICTOR | ETL.5790.INSL.CERA | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31607317 | T3 DI TGR CRK VLY SPRNGS RPL INSS 4TWR | 93K
LC | 123787031 | 009/060 | T3 DI OLEUM-G #1 9/060 BENT STEEL | CONCORD | ETL.3150.TOWR | 2022-06-08 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123787039 | 009/060 | T3 DI OLEUM-G #1 9/060 RPR INSS | CONCORD | ETL.3160.INSL.NCER | 2022-06-08 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45513505 | T3 DI OLEUM-G #1 9/060 RPR INSS | ICS
LC | 123787116 | 005/057 | T3 EI DRUM-RIO OSO #2 05/57 RPR STEEL | SACTO | ETL.1430.TOWR | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Structure-Tower | Repair | 45600065 | T3 EI DRUM-RIO OSO #2 05/57 RPR STEEL | ICQ
LC | 123787677 | 014/216 | T3 EI GOLD HILL #1 014/216 RPR POLE | SACTO | ETL.6950.POLE.WOOD | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123787777 | 011/212 | T3 DI FRCH MDWS-MID FRK 11/212 RPR STRW | SACTO | ETL.6870.POLE.WOOD | 2022-06-08 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123787893 | 011/212 | T3 DI FRCH MDWS-MID FRK 11/212 INS HRDD | SACTO | ETL.6870.POLE.WOOD | 2022-06-08 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install
LC | 123788195 | 011/118 | T3 EI IGNACIO-BOLINAS #1 11/118 RPR CNDW | LAKEVLLE | ETL.7140.INSL.NCER | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair | 45576010 | T3 EI IGNACIO-BOLINAS #1 11/118 RPR CNDW | ICW
LC | 123788701 | 005/059 | T3 EI DRUM-RIO OSO #2 005/059 REGRADE | SACTO | ETL.1430.TOWR | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45600066 | T3 EI DRUM-RIO OSO #2 005/059 REGRADE | ICQ
LC | 123788719 | T081 | T3 EI MIDWAY-SANTA MARIA T81 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace
LC | 123788723 | T047 | T3 EI MIDWAY-SANTA MARIA T47 RPR FOND | PISMOBCH | ETL.9240.TOWR | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Steel | Repair | 45605033 | T3 EI MIDWAY-SANTA MARIA T47 RPR FOND | ICS
LC | 123788725 | T047 | T3 EI MIDWAY-SANTA MARIA T47 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace
LC | 123788970 | 008/132 | T3 EI WEIMAR #1 008/132 RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31629060 | T2 DI WEIMAR #1 004/059 RPL POLE | 70Y
LC | 123789162 | 014/220 | T3 EI GOLD HILL #1 014/220 RPL POLE | SACTO | ETL.6950.POLE.WOOD | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31614770 | T3 WV GOLD HILL #1 12/192 RPL POLE | 70Y
LC | 123789258 | 005/059 | T3 EI DRUM-RIO OSO #1 05/59 COTTER | SACTO | ETL.1420.INSL.CERA | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123789505 | 004/036 | T3 EI TGR CRK-VLLY SPRNGS 4/36 RPL INSS | VICTOR | ETL.5790.INSL.CERA | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31609395 | T2 DI TIGR CREEK-VLLY SPRNGS RPL INSS 6T | 93K
LC | 123790701 | 017/071 | T3 DI MONTA VISTA-JFRSO #1 17/71 RMV VEG | METCALF | ETL.5220.TOWR | 2022-06-08 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123790762 | 017/071 | T3 DI MONT VIST JFRSON #1 17/71 RPR INSS | METCALF | ETL.5220.INSL | 2022-06-08 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45598736 | T3 DI MONT VIST JFRSON #1 17/71 RPR INSS | ICS
LC | 123790966 | 026/002 | T3 DI FULTON-HOPLAND 026/002 RMV VEG | LAKEVLLE | ETL.6890.POLE.WOOD | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123791120 | 008/037 | T3 DI MRG CSTR VLY 8/37 RPR OPGW | CONCORD | ETL.5250.TOWR | 2022-06-08 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45502877 | T3 DI MRG CSTR VLY 8/37 RPR OPGW | ICS
LC | 123791167 | 005/040 | T3 EI TGR CRK-VLLY SPRNGS 5/40 RPL INSS | VICTOR | ETL.5790.INSL.CERA | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31609395 | T2 DI TIGR CREEK-VLLY SPRNGS RPL INSS 6T | 93K
LC | 123791597 | 000/006 | T3 DI TGR CRK VLY SPRNGS 0/6 RPR STRT | VICTOR | ETL.5790.TOWR | 2022-06-08 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45591318 | T3 DI TGR CRK VLY SPRNGS 0/6 RPR STRT | ICQ
LC | 123791790 | 000/006 | T3 DI TGR CRK VLY SPRNGS 0/6 RPL INSS | VICTOR | ETL.5790.INSL | 2022-06-08 | 2022-05-21 |  | 2022-11-17 | 2022-11-21 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31607317 | T3 DI TGR CRK VLY SPRNGS RPL INSS 4TWR | 93K
LC | 123792613 | 001/028 | T3 EI MIDDLEFORK #1 1/28 RPR STRW | SACTO | ETL.8405.POLE.WOOD | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123792696 | 005/031 | T3 ROUND MTN-TABLE MTN #1 5/31 UNBURY | TABLEMTN | ETL.6060.TOWR | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB XMPT TR3 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45644407 | T3 ROUND MTN-TABLE MTN #1 5/31 UNBURY | ICQ
LC | 123792747 | A004/120 | T3 DI DRM-GRS VLLY WIMAR 4/120 RPL HRDD | SACTO | ETL.6760.POLE.WOOD | 2022-06-08 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123792748 | A004/120 | T3 DI DRM-GRS VLLY WIMAR 4/120 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2022-06-08 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123792765 | T079 | T3 EI MIDWAY-SANTA MARIA T079 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace
LC | 123792766 | T048 | T3 EI MIDWAY-SANTA MARIA T048 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace
LC | 123793292 | 002/025 | T3 DI DRUM-SUMMIT #1 2/025 RPR INSW | SACTO | ETL.1440.INSL.NCER | 2022-06-08 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123793350 | 006/119 | T3 DI COLGATE-CHALLENGE 6/119 RPL HRDD | SACTO | ETL.6480.POLE.NWOD | 2022-06-08 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123793394 | 002/064 | T3 DI BURNS-LONE STAR #2 02/064 INS HRDW | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-06-08 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45618341 | T3 DI BURNS-LONE STAR #2 02/064 INS HRDW | ICW
LC | 123793433 | 018/000A | T3 WV OAKHURST TAP 18/0A INS DAMS | FRESNO | ETL.1252.INSL.NCER | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO NTDE | Missing | Damper-Steel | Install | 45489434 | T3 WV OAKHURST TAP 18/0A INS DAMS | ICS
LC | 123793484 | 001/038 | T3 DI DRM-GRS VLY-WMR 1/38 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2022-06-08 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123793489 | 004/097 | T3 DI DRM-GRS VLY-WMR 4/97 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2022-06-08 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH XMPT TR3 PRTO AIR FRAB | Rotten | Structure-Wood | Replace | 31612546 | T3 EI DRUM GRASS VLY WIMAR 3/75 RPL STRW | 70Y
LC | 123793572 | 004/024 | T3 DI RND MTN-TBL MTN #1 004/024 RMV VEG | TABLEMTN | ETL.6060.TOWR | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123793655 | 000/011 | T3 DI SALMON CREEK TAP 0/11 RPL HRDD | LAKEVLLE | ETL.6981.POLE.WOOD | 2022-06-08 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45571358 | T3 DI SALMON CREEK TAP 0/11 RPL HRDD | ICW
LC | 123793778 | 001/023 | T3 DI CNTRVL-TBL MTN-OROVL 1/23 RPL POLE | TABLEMTN | ETL.6330.POLE.WOOD | 2022-06-08 | 2022-05-30 |  | 2022-11-26 | 2022-11-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611490 | T3 EI CNTRVLL-TBL MTN-ORLL 0/2 RPL POLE | 70Y
LC | 123793907 | 015/064 | T3 EI EGLE RK-FLTN-SLVRDO 15/64 RPL INSS | LAKEVLLE | ETL.4392.INSL.CERA | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31613370 | T3 EI EAGL RCK-FLTN-SLVRD RPL INSS 3TWR | 93K
LC | 123793908 | 013/059 | T3 EI EAGL RCK-FLTN-SLVRD 13/59 REGRADE | LAKEVLLE | ETL.4392.TOWR | 2022-06-08 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123794325 | 015/061 | T3 DI MNTA VSTA-JFFRSN #1 15/61 INS HRDT | METCALF | ETL.5220.TOWR | 2022-06-09 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install
LC | 123795007 | 007/079 | T3NT EI DRUM-RIO OSO #1 7/079 RMV DEBRIS | SACTO | ETL.1420.TOWR | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP CPUA OH FMOB TR3 PRTO FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove
LC | 123795259 | 008/094 | T3 DI GRN VALLY-CAMP EVRS 8/94C RPL HRDW | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-06-09 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45618342 | T3 DI GRN VALLY-CAMP EVRS 8/94C RPL HRDW | ICW
LC | 123795572 | 008/094 | T3 DI GRN VALLY-CAMP EVRS 8/94R RPL HRDW | MOSSLNDG | ETL.1710.POLE.WDPS | 2022-06-09 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45618343 | T3 DI GRN VALLY-CAMP EVRS 8/94R RPL HRDW | ICW
LC | 123795828 | 008/094 | T3 DI GRN VALLEY-CAMP EVRS 8/94 RPR INSW | MOSSLNDG | ETL.1710.INSL.CERA | 2022-06-09 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45618346 | T3 DI GRN VALLEY-CAMP EVRS 8/94 RPR INSW | ICW
LC | 123795960 | 054/301 | T3 EI TMBLR-SN LS OBSPO 54/301 REGRADE | PISMOBCH | ETL.3960.TOWR | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123796107 | 001/008 | T3 EI BRIDGEVILLE-GARBERVL 1/8 RPR GYWW | EUREKA | ETL.6220.POLE.NWOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45575273 | T2 DI BRIDGEVILLE-GARBERVL 1/4 RPR ANCW | ICW
LC | 123796235 | 054/300 | T3 EI TEMBLOR-SLO 54/300 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31611745 | T3 EI TEMBLOR-SLO RPL INSS 7TWR | 93K
LC | 123796601 | 030/255 | T3 EI RND MTN-CTTNWD #3 30/255 RPR INSS | TABLEMTN | ETL.5650.INSL | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123796602 | 030/256 | T3 EI RND MTN-CTTNWD #3 30/256 BNT STEEL | TABLEMTN | ETL.5650.TOWR | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123796610 | 007/075 | T3 EI DRUM-RIO OSO #1 7/075 RPR FOND | SACTO | ETL.1420.TOWR | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP CPUA OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45599987 | T3 EI DRUM-RIO OSO #1 7/075 RPR FOND | ICQ
LC | 123796638 | 002/027 | T3 EI IGNACIO-BOLINAS #2 2/27 RPR POLE | LAKEVLLE | ETL.7180.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45575650 | T3 EI IGNACIO-BOLINAS #2 2/27 RPR POLE | ICW
LC | 123796697 | 001/005 | T3 EI BRIDGEVILLE-GARBERVL 1/5 RPR POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45575273 | T2 DI BRIDGEVILLE-GARBERVL 1/4 RPR ANCW | ICW
LC | 123797213 | 023/261 | T3 EI IGNCO-BLINAS #2 23/261 WASH INSS | LAKEVLLE | ETL.7180.INSL.CERA | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 622 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | Contaminated | Insulator | Ground Wash | 45486090 | T3 EI IGNCO-BLINAS #2 23/261 WASH INSS | ICD
LC | 123797372 | 005/062 | T3 EI DRUM-RIO OSO #1 5/062 RMV STEP | SACTO | ETL.1420.TOWR | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45599985 | T3 EI DRUM-RIO OSO #1 5/062 RMV STEP | ICQ
LC | 123797654 | 010/008 | T3 DI DONNELLS-MI-WUK 010/008 COTTER | VICTOR | ETL.1400.INSL.CERA | 2022-06-09 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45519331 | T3 DI DONNELLS-MI-WUK 010/008 COTTER | ICW
LC | 123797699 | 007/145 | T3 EI FRNCH MDWS-MDLE FRK 7/145 RPL STRW | SACTO | ETL.6870.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617971 | T3 EI FRNCH MDWS-MDDL FRK 7/143 RPL POLE | 70Y
LC | 123797733 | 007/141 | T3 EI FRNCH MDWS-MDDL FRK 7/141 RPL POLE | SACTO | ETL.6870.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31614152 | T3 EI FRCH MDWS-MDL FRK 4/80 RPL POLE | 70Y
LC | 123797734 | 007/140 | T3 EI FRNCH MDWS-MDDL FRK 7/140 RPL STRW | SACTO | ETL.6870.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31614152 | T3 EI FRCH MDWS-MDL FRK 4/80 RPL POLE | 70Y
LC | 123797735 | 007/143 | T3 EI FRNCH MDWS-MDDL FRK 7/143 RPL POLE | SACTO | ETL.6870.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617971 | T3 EI FRNCH MDWS-MDDL FRK 7/143 RPL POLE | 70Y
LC | 123797750 | 007/144 | T3 EI FRNCH MDWS-MDDL FRK 7/144 RPL POLE | SACTO | ETL.6870.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617971 | T3 EI FRNCH MDWS-MDDL FRK 7/143 RPL POLE | 70Y
LC | 123797751 | 007/142 | T3 EI FRNCH MDWS-MDDL FRK 7/142 RPL STRW | SACTO | ETL.6870.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617971 | T3 EI FRNCH MDWS-MDDL FRK 7/143 RPL POLE | 70Y
LC | 123797834 | 006/071 | T3 EI DRUM-RIO OSO #1 6/071 RPL CRSW | SACTO | ETL.1420.POLE.STPS | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP CPUA OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Steel | Replace
LC | 123798015 | 052/294 | T3 EI TEMBLOR-SLO 52/294 RPL INSS | PISMOBCH | ETL.3960.INSL | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31611745 | T3 EI TEMBLOR-SLO RPL INSS 7TWR | 93K
LC | 123798024 | 051/290 | T3 EI TEMBLOR-SLO 51/290 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31611745 | T3 EI TEMBLOR-SLO RPL INSS 7TWR | 93K
LC | 123798627 | 002/002 | T3 EI BRIDGEVLE-GARBERVLE 2/2 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606887 | T3 EI BRDGVLL-GRBRVLL 003/014 RPL STRW | 70Y
LC | 123798781 | 007/057 | T3 EI TGR CRK VLLY SPRNGS 7/57 REPLUMB | VICTOR | ETL.5790.INSL.CERA | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45503726 | T3 EI TGR CRK VLLY SPRNGS 7/57 REPLUMB | ICS
LC | 123798802 | 001/022 | T3 WV HLSDL JCT-HLF MN BY 1/22 RPL ANCW | METCALF | ETL.7060.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW CREW OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31629661 | T3 WV HLSDL JCT-HLF MN BY 1/22 RPL ANCW | 93E
LC | 123798956 | 007/056 | T3 EI TGR CRK VLLY SPRNGS 7/56 REPLUMB | VICTOR | ETL.5790.INSL.CERA | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45503727 | T3 EI TGR CRK VLLY SPRNGS 7/56 REPLUMB | ICS
LC | 123799722 | 025/004 | T3 DI MAPLE CREEK-HOOPA 25/4 RPR STRW | EUREKA | ETL.7490.POLE.NWOD | 2022-06-09 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123799751 | 048/273 | T3 EI TEMBLOR-SLO 48/273 RPL INSS | PISMOBCH | ETL.3960.INSL | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31611745 | T3 EI TEMBLOR-SLO RPL INSS 7TWR | 93K
LC | 123800079 | 008/149 | T3 EI FRNCH MDWS-MDLE FRK 8/149 RPL STRW | SACTO | ETL.6870.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31614153 | T3 EI FRNCH MDWS-MDLE FRK 8/149 RPL STRW | 70Y
LC | 123800138 | 010/111B | T3 EI IGNACIO-BOLNS #1 10/111B INST DMPR | LAKEVLLE | ETL.7140.INSL.CERA | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | Missing | Damper-Wood | Install | 45486129 | T3 EI IGNACIO-BOLNS #1 10/111B INST DMPR | ICW
LC | 123800217 | 006/152 | T3 WV KILARC-CEDAR CREEK 06/152 RPL POLE | TABLEMTN | ETL.7290.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW CREW OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617623 | T3 WV KILARC-CEDAR CREEK 06/152 RPL POLE | 70Y
LC | 123800244 | 011/107 | T3 DI DRM HGNS 11/107L RPR STRW | SACTO | ETL.4393.POLE.STPS | 2022-06-09 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123800418 | 001/034 | T3 EI MIDDLEFORK #1 1/34 RPR CRSW | SACTO | ETL.8405.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair
LC | 123800451 | 001/032 | T3 EI MIDDLEFORK #1 1/32 RPR CRSW | SACTO | ETL.8405.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair
LC | 123800764 | 032/271 | T3 EI RUND MTN-CTTNWD #3 32/271 BNT STEL | TABLEMTN | ETL.5650.TOWR | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123801364 | B021/483 | T3 DRUM GRAS VALY WMAR B21/483 RPR WDPKR | SACTO | ETL.6760.POLE.WOOD | 2022-06-09 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR OH TR3 PRTO | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123801620 | 000/007 | T3 DI SNTA FE GTHRML TAP 0/007 INS STEP | LAKEVLLE | ETL.4782.TOWR | 2022-06-09 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123801722 | 023/000 | T3 DI MAPLE CREEK-HOOPA 23/0 RMV VEGN | EUREKA | ETL.7490.POLE.NWOD | 2022-06-09 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE ACCL OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123801739 | 023/342 | T3 EI GOLD HILL #1 23/342 RPR STRW | SACTO | ETL.6950.POLE.NWOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123802047 | 005/038 | T3 DI MRAGA-SN LENDRO#1 5/038 RPL INSS | CONCORD | ETL.2770.INSL | 2022-06-09 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617656 | T3 DI MORAGA-SAN LEANDRO #1 RPL INSS 6T | 93K
LC | 123802063 | 003/021 | T3 DI RND MTN-TBL MTN #2 3/21 RPR FOND | TABLEMTN | ETL.6070.TOWR | 2022-06-09 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123802117 | 002/006 | T3 EI BRIDGEVILE-GARBERVL 2/6 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611484 | T3 EI BRIDGEVILLE-GRBRVLL 2/6 RPL POLE | 70Y
LC | 123802150 | 003/000 | T3 EI BRIDGEVILLE-GARBERVL 3/0 RPL INSW | EUREKA | ETL.6220.INSL.CERA | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617171 | T3 EI BRIDGEVILLE-GRBRVLL 3/0 RPL INSW | 93I
LC | 123802160 | 002/004 | T3 EI BRIDGEVILE-GARBERVL 2/4 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-06-09 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617167 | T3 EI BRIDGEVILLE-GRBRVLL 2/4 RPL POLE | 70Y
LC | 123802255 | ?003/006 | T3 DI SNETH LN-HLF MN BY ?3/6 RPL INSW | METCALF | ETL.7212.INSL.CERA | 2022-06-09 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31612284 | T3 DI SNTH LN-HALF MON BAY ?6/9 RPL INSW | 93I
LC | 123802298 | 004/023 | T3 DI RND MTN-TBL MTN #2 4/23 RPL INSS | TABLEMTN | ETL.6070.INSL | 2022-06-09 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617251 | T3 DI RND MTN TBL MTN#2 2/015 RPL INSS | 93K
LC | 123802299 | 020/001 | T3 DI MNT RIO FRT RS 20/1 COTR KEY | LAKEVLLE | ETL.6979.INSL.NCER | 2022-06-09 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45575609 | T3 DI MNT RIO FRT RS 20/1 COTR KEY | ICW
LC | 123802309 | 004/023 | T3 DI RND MTN-TBL MTN #2 4/23 RPR FOND | TABLEMTN | ETL.6070.TOWR | 2022-06-09 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123802575 | 022/159 | T3 DI TRINITY-COTTONWOOD 22/159 RMV VEG | TABLEMTN | ETL.4040.POLE.STPS | 2022-06-09 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 123802786 | 001/027 | T3 DI DRUM-SPAULDING 1/27 RPR GYWW | SACTO | ETL.6770.POLE.NWOD | 2022-06-09 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123813647 | :003/018 | T3 DI GYSRS#12-FULTON 3/018 RPR INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2022-06-10 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45467440 | T3 DI GYSRS#12-FULTON 3/018 RPR INSS | ICS
LC | 123813649 | :003/018 | T3 DI GEYSERS #9-LAKEVILL :3/18 RPR INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2022-06-10 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45467441 | T3 DI GEYSERS #9-LAKEVILL :3/18 RPR INSS | ICS
LC | 123813765 | 002/002 | T3 DI FLTN-CLSTGA 002/002 RPL HRDD | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-06-10 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45575471 | T3 DI FLTN-CLSTGA 002/002 RPL HRDD | ICW
LC | 123813815 | 009/128 | T3 DI MIDDLEFORK#1 009/128 RPL STRW | SACTO | ETL.8405.POLE.WOOD | 2022-06-10 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31614824 | T3 DI MIDDLEFORK#1 009/128 RPL STRW | 70Y
LC | 123814029 | B020/462 | T3 DI DRUM-G.V.-WEMAR B20/462 RPL INSW | SACTO | ETL.6760.INSL.CERA | 2022-06-10 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617793 | T2 DI DRM-GRS VLLY-WIMR B18/418 RPL INSW | 93I
LC | 123814050 | 002/004 | T3 DI FULTON-CALISTOGA 2/4 RPR INSW | LAKEVLLE | ETL.6880.INSL.NCER | 2022-06-10 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45571444 | T3 DI FULTON-CALISTOGA 2/4 RPR INSW | ICW
LC | 123814160 | 016/003 | T3 DI MNTE RIO-FORT ROSS 16/003 RPR INSW | LAKEVLLE | ETL.6979.INSL.NCER | 2022-06-10 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45575617 | T3 DI MNTE RIO-FORT ROSS 16/003 RPR INSW | ICW
LC | 123814169 | 000/002 | T3 DI MORAGA-SN LENDRO#2 0/002 RPL INSS | CONCORD | ETL.2780.INSL | 2022-06-10 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617657 | 3 DI MORAGA-SN LENDRO#2 0/002 RPL INSS | 93K
LC | 123814314 | 005/145 | T3 DI CLGATE-GRS VLLY 5/145 RPR INSW | SACTO | ETL.6490.INSL.NCER | 2022-06-10 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123814608 | 016/079 | T3 DI CORTINA-MENDCN #1 16/79 RPR OPGW | WILLITS | ETL.1330.TOWR | 2022-06-10 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair
LC | 123814753 | 005/029 | T3 DI RND MTN-TBL MTN#2 5/029 RPR HRDT | TABLEMTN | ETL.6070.TOWR | 2022-06-10 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123814776 | 033/277 | T3 EI RND MTN-CTTNWD #3 33/277 BNT STEEL | TABLEMTN | ETL.5650.TOWR | 2022-06-10 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123815052 | 000/002 | T3 DI BREADSLEY TAP 000/002R RPR STRW | VICTOR | ETL.1401.POLE.WDPS | 2022-06-10 | 2022-06-04 |  | 2022-12-01 | 2022-12-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45519334 | T3 DI BREADSLEY TAP 000/002R RPR STRW | ICW
LC | 123815080 | 001/019 | T3 DI ATASCADERO-CAYUCOS-WD 1/19 RPL PL | PISMOBCH | ETL.8480.POLE.WOOD | 2022-06-10 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31609238 | T2 EI ATASCADERO-CAYUCOS 1/17 RPL POLE | 70Y
LC | 123815170 | 001/007 | T3 DI GEYSERS #13 TAP 1/7 RPR SHLS | LAKEVLLE | ETL.4781.TOWR | 2022-06-10 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45575542 | T3 DI GEYSERS #13 TAP 1/7 RPR SHLS | ICS
LC | 123815199 | 000/001 | T3 DI TGR CREEK-ELECTRA 0/001 RPR FOND | VICTOR | ETL.5780.TOWR | 2022-06-10 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45591429 | T3 DI TGR CREEK-ELECTRA 0/001 RPR FOND | ICQ
LC | 123815414 | 010/108 | T3 EI IGNACIO-BOLINAS #1 10/108 RPL POLE | LAKEVLLE | ETL.7140.POLE.WOOD | 2022-06-10 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617008 | T2 DI IGNACIO-BOLINAS #1 6/66C RPL POLE | 70Y
LC | 123815592 | 003/036 | T3 DI WOODLEAF-PALERMO 3/36 REFRAME | TABLEMTN | ETL.4220.POLE.STPS | 2022-06-10 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31626015 | T3 DI WOODLEAF-PALERMO 3/36 REFRAME | 93E
LC | 123815752 | 019/009 | T3 DI MAPLE CREEK-HOOPA 19/9 RPR JUMW | EUREKA | ETL.7490.INSL.NCER | 2022-06-10 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Wood | Repair
LC | 123815755 | 019/009 | T3 DI MAPLE CREEK-HOOPA 19/9 RMV VEG | EUREKA | ETL.7490.POLE.NWOD | 2022-06-10 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123815902 | 017/087 | T3 DI MNTA VSTA-CYTE SS 17/87 RPR INSS | MOSSLNDG | ETL.5090.INSL | 2022-06-10 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45618352 | T3 DI MNTA VSTA-CYTE SS 17/87 RPR INSS | ICS
LC | 123815947 | 017/087 | T3 DI MNTA VSTA-CYTE SS 17/87 RPR SHLS | MOSSLNDG | ETL.5090.TOWR | 2022-06-10 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45618353 | T3 DI MNTA VSTA-CYTE SS 17/87 RPR SHLS | ICS
LC | 123816188 | 005/038 | T3 EI BRUNSWICK #1 TAP 5/038 RPR FOND | SACTO | ETL.1422.TOWR | 2022-06-10 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45582460 | T3 EI BRUNSWICK #1 TAP 5/038 RPR FOND | ICQ
LC | 123816221 | 000/003 | T3 DI SANTA FE GTHRML TAP 0/3 RPR SHIELD | LAKEVLLE | ETL.4782.TOWR | 2022-06-10 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45575644 | T3 DI SANTA FE GTHRML TAP 0/3 RPR SHIELD | ICW
LC | 123816323 | 003/037 | T3 DI DRUM-SUMMIT #2 3/37R RPL PL | SACTO | ETL.1450.POLE.WDPS | 2022-06-10 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31634269 | T3 DI DRUM-SUMMIT #2 001/013R RPL STRW | 70Y
LC | 123816326 | 003/037 | T3 DI DRUM-SUMMIT #2 3/37L RPL PL | SACTO | ETL.1450.POLE.WDPS | 2022-06-10 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Replace | 31634269 | T3 DI DRUM-SUMMIT #2 001/013R RPL STRW | 70Y
LC | 123816353 | 005/001 | T3 DI WISHON-SAN JOAQUIN #3 5/1 INS IBWW | FRESNO | ETL.9340.POLE.NWOD | 2022-06-10 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45489623 | T3 DI WISHON-SAN JOAQUIN #3 5/1 INS IBWW | ICW
LC | 123816477 | 008/033 | T3 EI GEYSERS #9-LAKEVILLE 8/33 RMV NEST | LAKEVLLE | ETL.4392.TOWR | 2022-06-10 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45575658 | T3 EI GEYSERS #9-LAKEVILLE 8/33 RMV NEST | ICS
LC | 123816498 | 005/077 | T3 DI MIDDLEFORK #1 005/077 RPR GYWW | SACTO | ETL.8405.POLE.NWOD | 2022-06-10 | 2022-06-05 |  | 2022-12-02 | 2022-12-05 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123816730 | 005/037 | T3 EI BRUNSWICK #1 TAP 5/37 RMV VEG | SACTO | ETL.1422.TOWR | 2022-06-10 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123816802 | 009/042 | T3 DI TASSAJARA-NEWARK 9/42 RPL INSS | CONCORD | ETL.5920.INSL | 2022-06-10 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31606226 | DI TASSAJARA-NEWARK 9/42 RPL INSS | 93K
LC | 123817474 | 014/116 | T3 DI CRESTA-RIO OSO 14/116 UNBURY | TABLEMTN | ETL.4590.TOWR | 2022-06-10 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45597805 | T3 DI CRESTA-RIO OSO 14/116 UNBURY | ICQ
LC | 123817604 | 006/006 | T3 DI WISHON-SAN JOAQUIN #3 6/6 HRDW | FRESNO | ETL.9340.POLE.NWOD | 2022-06-10 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45489625 | T3 DI WISHON-SAN JOAQUIN #3 6/6 HRDW | ICW
LC | 123817702 | 012/192 | T3 WV GOLD HILL #1 12/192 RPL POLE | SACTO | ETL.6950.POLE.WOOD | 2022-06-10 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW CREW OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31614770 | T3 WV GOLD HILL #1 12/192 RPL POLE | 70Y
LC | 123817802 | ?005/001 | T3 DI SNTH LN HLF MN BY 5/1 RPR INSW | METCALF | ETL.7212.INSL.NCER | 2022-06-10 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45600689 | T3 DI SNTH LN HLF MN BY 5/1 RPR INSW | ICW
LC | 123817862 | 005/041 | T3 EI BRUNSWICK #1 TAP 005/041 RMV VEG | SACTO | ETL.1422.TOWR | 2022-06-10 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123817935 | 004/121 | T3 EI DEER CREEK-DRUM 004/121 RPR INSW | SACTO | ETL.6690.INSL.NCER | 2022-06-10 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123818066 | X000/002 | T3 DI DIABLO-MESA X0/2 RPL HRDT | PISMOBCH | ETL.4620.TOWR | 2022-06-10 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123818385 | 016/008 | T3 DI MNT RIO FRT RS 16/8 RPL HRDD | LAKEVLLE | ETL.6979.POLE.WOOD | 2022-06-10 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45575607 | T3 DI MNT RIO FRT RS 16/8 RPL HRDD | ICW
LC | 123818392 | 007/064 | T3 DI TASCADERO-CAYUCOS 7/64 RPR HRDW | PISMOBCH | ETL.8480.POLE.WOOD | 2022-06-10 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45600537 | T3 DI TASCADERO-CAYUCOS 7/64 RPR HRDW | ICW
LC | 123818419 | 001/006B | T3 DI BEARDSLEY TAP 1/6B RPL POLE | VICTOR | ETL.1401.POLE.WOOD | 2022-06-10 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31619561 | T3 DI BRDSLY TP 1/6A RPL POLE | 70Y
LC | 123818454 | 016/008 | T3 DI MNT RIO FRT RS 16/8 RPR SPLW | LAKEVLLE | ETL.6979.INSL.NCER | 2022-06-10 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45575608 | T3 DI MNT RIO FRT RS 16/8 RPR SPLW | ICW
LC | 123818458 | 020/160B | T3 DI MDL FRK-GLD HLL 20/160B RPR GYWW | SACTO | ETL.5140.POLE.NWOD | 2022-06-10 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123818493 | 020/160B | T3 DI MDL FRK-GLD HLL 20/160B RPR ANCW | SACTO | ETL.5140.POLE.NWOD | 2022-06-10 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123818503 | 009/105 | T3 EI IGNACIO-BOLINAS #1 9/105 RESAG | LAKEVLLE | ETL.7140.INSL.NCER | 2022-06-10 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Conductor-Wood | Repair | 45486130 | T3 EI IGNACIO-BOLINAS #1 9/105 RESAG | ICW
LC | 123818517 | 009/104 | T3 EI GNACIO-BOLINAS #109/104L RPL PL | LAKEVLLE | ETL.7140.POLE.WDPS | 2022-06-10 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617015 | T3 EI GNACIO-BOLINAS #1 09/104L RPL PL | 70Y
LC | 123818853 | 020/160C | T3 DI MDL FRK-GLD HLl 20/160C RPR GYWW | SACTO | ETL.5140.POLE.NWOD | 2022-06-10 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123818924 | 014/007 | T3 DI MAPLE CREEK-HOOPA 14/7 RPL SPLW | EUREKA | ETL.7490.INSL.NCER | 2022-06-10 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Replace
LC | 123818926 | 014/007 | T3 DI MAPLE CREEK-HOOPA 14/7 RPL RPTW | EUREKA | ETL.7490.POLE.NWOD | 2022-06-10 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 593 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Raptor Guard-Wood | Replace
LC | 123819210 | 001/006A | T3 DI BRDSLY TP 1/6A RPL POLE | VICTOR | ETL.1401.POLE.WOOD | 2022-06-10 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31619561 | T3 DI BRDSLY TP 1/6A RPL POLE | 70Y
LC | 123819351 | 027/119 | T3 EI FULTON-LAKEVILLE 27/119 RPL INSS | LAKEVLLE | ETL.4950.INSL | 2022-06-10 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP PGEA OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31606170 | T2 DI FULTON-LAKEVILLE+ RPL INSS 3TWR | 93K
LC | 123819407 | 001/006C | T3 DI BEARDSLEY TAP 1/6C RPL POLE | VICTOR | ETL.1401.POLE.WOOD | 2022-06-10 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31619561 | T3 DI BRDSLY TP 1/6A RPL POLE | 70Y
LC | 123819741 | 012/173 | T3 EI WEIMAR #1 12/173L RPR GYWW | SACTO | ETL.7560.POLE.STPS | 2022-06-10 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123819742 | 012/173 | T3 EI WEIMAR #1 12/173R RPR GYWW | SACTO | ETL.7560.POLE.STPS | 2022-06-10 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123820405 | 000/004 | T3 WV KILARC-DESCHUTES 0/4 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2022-06-10 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617633 | T3 WV KILARC-DESCHUTES 0/4 RPL POLE | 70Y
LC | 123820489 | 012/007 | T3 DI DONNELLS-MI-WUK 12/007 RPL HRDW | VICTOR | ETL.1400.POLE.STPS | 2022-06-10 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45519338 | T3 DI DONNELLS-MI-WUK 12/007 RPL HRDW | ICW
LC | 123820738 | 013/239 | T3 EI FRNCH MDWS MDL FRK 13/239 RPR INSW | SACTO | ETL.6870.INSL.NCER | 2022-06-10 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123821189 | 010/100 | T3 DI GRN VLY-PAUL SWT 10/100 RPL STRW | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-06-10 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31629564 | T3 DI GRN VLY-PAUL SWT 10/100 RPL STRW | 70Y
LC | 123821221 | 010/100 | T3 DI GRN VLY-PAUL SWT 10/100 RPL STRW | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-06-10 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31629564 | T3 DI GRN VLY-PAUL SWT 10/100 RPL STRW | 70Y
LC | 123821223 | 010/100 | T3 DI GRN VLY-PAUL SWT 10/100 RPL STRW | MOSSLNDG | ETL.1730.POLE.WDPS | 2022-06-10 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31629564 | T3 DI GRN VLY-PAUL SWT 10/100 RPL STRW | 70Y
LC | 123821786 | 004/042 | T3 DI ATASCADERO-CYCS 4/042 RPL HRDD | PISMOBCH | ETL.8480.POLE.WOOD | 2022-06-11 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45600538 | T3 DI ATASCADERO-CYCS 4/042 RPL HRDD | ICW
LC | 123821801 | 003/063 | T3 DI COLGATE-CHLLNGE 3/063 RPL HRDD | SACTO | ETL.6480.POLE.WOOD | 2022-06-11 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123821829 | 016/130 | T3 DI PARADISE-TBL MTN 16/130 RPL HRDS | TABLEMTN | ETL.4316.POLE.NWOD | 2022-06-11 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Steel | Replace
LC | 123821848 | 005/143 | T3 DI DRM-GRSS VLLY-WMR 5/143 RPL HRDW | SACTO | ETL.6760.POLE.WOOD | 2022-06-11 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123822097 | 010/099 | T3 EI DRUM-RIO OSO #2 10/99 BNT STEEL | SACTO | ETL.1430.TOWR | 2022-06-11 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45600071 | T3 EI DRUM-RIO OSO #2 10/99 BNT STEEL | ICQ
LC | 123822141 | 003/024 | T3 EI BRUNSWICK #1 TAP 3/24 RPR INSS | SACTO | ETL.1422.INSL | 2022-06-11 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair | 45456609 | T3 EI BRUNSWICK #1 TAP 3/24 RPR INSS | ICS
LC | 123822155 | 002/011 | T3 DI BRIDGEVILLE-GARBERVIL 2/11 REFRAME | EUREKA | ETL.6220.POLE.WOOD | 2022-06-11 | 2022-05-13 |  | 2022-11-09 | 2022-11-13 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31617168 | T3 DI BRDGVLLE-GARBERVILLE 2/11 REFRAME | 93E
LC | 123822522 | 009/101 | T3 EI IGNACIO-BOLINAS #1 9/101 RPR GYWW | LAKEVLLE | ETL.7140.POLE.WOOD | 2022-06-11 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45486134 | T3 EI IGNACIO-BOLINAS #1 9/101 RPR GYWW | ICW
LC | 123822569 | 008/155 | T3 EI FRNCH MDWS MDL FRK 8/155 RPL POLE | SACTO | ETL.6870.POLE.WOOD | 2022-06-11 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31614153 | T3 EI FRNCH MDWS-MDLE FRK 8/149 RPL STRW | 70Y
LC | 123822904 | 002/016 | T3 EI BRUNSWICK #1 TAP 2/16 RMV VEG | SACTO | ETL.1422.TOWR | 2022-06-11 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation-Tower | Cage Clearing
LC | 123823950 | 003/008 | T3 EI WSHN-SN JOQN #3 3/8 REPULL GYWW | FRESNO | ETL.9340.POLE.NWOD | 2022-06-11 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45489629 | T3 EI WSHN-SN JOQN #3 3/8 REPULL GYWW | ICW
LC | 123824011 | 003/005 | T3 EI BRIDGVILE-GARBERVL 3/5 RPL STRW | EUREKA | ETL.6220.POLE.WOOD | 2022-06-11 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611484 | T3 EI BRIDGEVILLE-GRBRVLL 2/6 RPL POLE | 70Y
LC | 123824012 | 003/007 | T3 EI BRIDGEVILLE-GARBERVL 3/7 RPR GYWW | EUREKA | ETL.6220.POLE.WOOD | 2022-06-11 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45640239 | T3 EI BRIDGEVILLE-GARBERVL 3/7 RPR GYWW | ICW
LC | 123824541 | 000/007 | T3 EI MIDDLEFORK #1 0/7 RMV VEG | SACTO | ETL.8405.POLE.WOOD | 2022-06-11 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123824635 | 008/164 | T3 EI FRCH MDWS-MDL FRK 8/164 RPL POLE | SACTO | ETL.6870.POLE.WOOD | 2022-06-11 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31614153 | T3 EI FRNCH MDWS-MDLE FRK 8/149 RPL STRW | 70Y
LC | 123825268 | 008/087 | T3 EI IGNACIO-BOLINAS #1 8/87 RMV VEG | LAKEVLLE | ETL.7140.POLE.WOOD | 2022-06-11 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123825336 | 003/014 | T3 EI BRIDGEVL-GARBERVL 3/14 RPL STRW | EUREKA | ETL.6220.POLE.WOOD | 2022-06-11 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606887 | T3 EI BRDGVLL-GRBRVLL 003/014 RPL STRW | 70Y
LC | 123825342 | 003/012 | T3 EI WISHN-SN JQN #3 3/012 REPULL GYWW | FRESNO | ETL.9340.POLE.NWOD | 2022-06-11 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45489631 | T3 EI WISHN-SN JQN #3 3/012 REPULL GYWW | ICW
LC | 123825343 | 003/011 | T3 EI BRIDGEVILLE-GARBERVL 3/11 RPR GYWW | EUREKA | ETL.6220.POLE.WOOD | 2022-06-11 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45640240 | T3 EI BRIDGEVILLE-GARBERVL 3/11 RPR GYWW | ICW
LC | 123825368 | 004/000 | T3 EI BRIDGEVILLE-GARBERVL 4/0 RPR GYWW | EUREKA | ETL.6220.POLE.WOOD | 2022-06-11 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45640241 | T3 EI BRIDGEVILLE-GARBERVL 4/0 RPR GYWW | ICW
LC | 123826126 | 001/008 | T3 EI EAGL RCK-FLTN-SLVRD 1/8 RPL HRDT | LAKEVLLE | ETL.4392.TOWR | 2022-06-12 | 2022-06-12 |  | 2022-12-09 | 2022-12-12 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | Missing | Hardware-Tower | Install
LC | 123826208 | 006/068 | T3 EI DRUM-RIO OSO #2 6/68 ARMOR ROD | SACTO | ETL.1430.INSL | 2022-06-12 | 2022-06-12 |  | 2022-12-09 | 2022-12-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair
LC | 123826223 | ?010/006 | T3 EI SNTH LNE-HLF MN BY-HLF ?10/6 VEG | METCALF | ETL.7212.POLE.WDPS | 2022-06-12 | 2022-06-12 |  | 2022-12-09 | 2022-12-12 | Late | 932 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | Brush Fuel | Road | Remove | 44306463 | SNEATH LANE-HMB :001/010 FIX ROAD | CHS
LC | 123826467 | 004/006 | T3NT EI WISHON-SAN JQN #3 4/6 RPR INSW | FRESNO | ETL.9340.INSL.NCER | 2022-06-12 | 2022-06-12 |  | 2022-12-09 | 2022-12-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3N PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 45489584 | T3NT EI WISHON-SAN JQN #3 4/6 RPR INSW | ICW
LC | 123826568 | 004/007 | T3 EI WISHON-SAN JOAQUIN #3 4/7 RPR INSW | FRESNO | ETL.9340.INSL.NCER | 2022-06-12 | 2022-06-12 |  | 2022-12-09 | 2022-12-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 45489586 | T3 EI WISHON-SAN JOAQUIN #3 4/7 RPR INSW | ICW
LC | 123827376 | 006/071 | T3 EI DRUM-RIO OSO #2 6/71 ARMOR ROD | SACTO | ETL.1430.INSL | 2022-06-12 | 2022-06-12 |  | 2022-12-09 | 2022-12-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair
LC | 123827573 | 006/072 | T3 EI DRUM-RIO OSO #2 006/072 RPR CNDS | SACTO | ETL.1430.INSL | 2022-06-12 | 2022-06-12 |  | 2022-12-09 | 2022-12-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair
LC | 123827850 | 000/002 | T3 EI SALMON CREEK TAP 0/2 RPR INSW | LAKEVLLE | ETL.6981.INSL | 2022-06-12 | 2022-06-12 |  | 2022-12-09 | 2022-12-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace | 45571384 | T3 EI SALMON CREEK TAP 0/2 RPR INSW | ICW
LC | 123827851 | 000/004 | T3 EI SALMON CREEK TAP 0/4 RPR CNDW | LAKEVLLE | ETL.6981.INSL | 2022-06-12 | 2022-06-12 |  | 2022-12-09 | 2022-12-12 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair | 45571359 | T3 EI SALMON CREEK TAP 0/4 RPR CNDW | ICW
LC | 123827879 | 007/073 | T3 EI DRUM-RIO OSO #2 7/73 ARMOR ROD | SACTO | ETL.1430.INSL | 2022-06-12 | 2022-06-12 |  | 2022-12-09 | 2022-12-12 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Conductor-Steel | Repair
LC | 123829355 | 000/003 | T3 DI BRUNSWICK #1 TAP 0/3 REGRADE | SACTO | ETL.1422.TOWR | 2022-06-13 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45582377 | T3 DI BRUNSWICK #1 TAP 0/3 REGRADE | ICQ
LC | 123829783 | 007/080 | T3 EI DRUM-RIO OSO #2 7/82 RPL CRSW | SACTO | ETL.1430.POLE.STPS | 2022-06-13 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31619067 | T3 EI DRUM-RIO OSO #2 7/82 RPL CRSW | 93E
LC | 123829835 | 000/001 | T3 DI FRCH MDWS-MID FRK 000/001 RPR INSS | SACTO | ETL.6870.INSL.NCER | 2022-06-13 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123830547 | 005/029 | T3 DI RND MTN-TB MTN#2 5/029 RPR FOND | TABLEMTN | ETL.6070.TOWR | 2022-06-13 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123831654 | 007/052 | T3 DI MORAGA-SAN LEANDRO #3 7/52 RMV VEG | CONCORD | ETL.2790.TOWR | 2022-06-13 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123832096 | 005/026 | T3 EI EAGLE RCK-FLTN-SLVRD 5/26 RPR FOND | LAKEVLLE | ETL.4392.TOWR | 2022-06-13 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123832579 | 008/005 | T3 DI FULTON-CALISTOGA 8/5 COTTER | LAKEVLLE | ETL.6880.INSL.NCER | 2022-06-13 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45485770 | T3 DI FULTON-CALISTOGA 8/5 COTTER | ICW
LC | 123833263 | Z013/006 | T3 EI FULTON-CALISTOGA Z13/6 RPR STRW | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-06-13 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45485963 | T3 EI FULTON-CALISTOGA Z13/6 RPR STRW | ICW
LC | 123833448 | 004/024 | T3 DI RND MTN-TBL MTN #2 4/24 RPR GYWS | TABLEMTN | ETL.6070.TOWR | 2022-06-13 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45457725 | T3 DI RND MTN-TBL MTN #2 4/24 RPR GYWS | ICS
LC | 123833464 | 014/186 | T3 DI WEIMAR #1 14/186R RPR GYWW | SACTO | ETL.7560.POLE.WDPS | 2022-06-13 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123835208 | 003/018 | T3 EI EAGL RCK-FLTN-SLVRD 3/18 RPL INSS | LAKEVLLE | ETL.4392.INSL.CERA | 2022-06-13 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31613370 | T3 EI EAGL RCK-FLTN-SLVRD RPL INSS 3TWR | 93K
LC | 123835477 | 001/022 | T3 EI MIDDLEFORK #1 1/22 RPL POLE | SACTO | ETL.8405.POLE.WOOD | 2022-06-13 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123835797 | 010/015 | T3 EI BRIDGEVL-GARBERVL 10/15 RPL STRW | EUREKA | ETL.6220.POLE.WOOD | 2022-06-13 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611487 | T3 EI BRIDGVLLE-GARBERVLLE 9/8 RPL POLE | 70Y
LC | 123835798 | 005/001 | T3 EI BRIDGEVL-GARBERVL 5/1 RPL STRW | EUREKA | ETL.6220.POLE.WOOD | 2022-06-13 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611484 | T3 EI BRIDGEVILLE-GRBRVLL 2/6 RPL POLE | 70Y
LC | 123835810 | 010/014 | T3 EI BRIDGEVILLE-GARBERVL 10/14 RMV VEG | EUREKA | ETL.6220.POLE.WOOD | 2022-06-13 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123835903 | 001/021 | T3 WV CENTERVIL-TABL MTN 1/021 RPL POLE | TABLEMTN | ETL.6320.POLE.WOOD | 2022-06-13 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW CREW OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31626017 | T3 WV CENTERVIL-TABL MTN 1/021 RPL POLE | 70Y
LC | 123836076 | 014/000 | T3 DI DONNELLS-MI-WUK 14/00R RPR POLE | VICTOR | ETL.1400.POLE.WDPS | 2022-06-13 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45519339 | T3 DI DONNELLS-MI-WUK 14/00R RPR POLE | ICW
LC | 123837463 | 009/094 | T3 DI DRUM-RIO OSO #1 009/094 RPR INSS | SACTO | ETL.1420.INSL.CERA | 2022-06-14 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123837468 | 004/037 | T3 DI MRAGA SN LEANDRO #1 4/37 RPR STRT | CONCORD | ETL.2770.TOWR | 2022-06-14 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123837658 | 003/064 | T3 DI FRNCH MDWS-MDL FRK 3/64 RPR GYWW | SACTO | ETL.6870.POLE.NWOD | 2022-06-14 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123837954 | 010/006 | T3 DI LRLS OTR 10/6 COTTER | MOSSLNDG | ETL.7380.INSL | 2022-06-14 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123838043 | 011/167 | T3 EI WEIMAR #1 011/167 RPR STRW | SACTO | ETL.7560.POLE.WOOD | 2022-06-14 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123838459 | 017/159 | T3 DI MNTA VSTA-BURNS 17/159L RPR GYWW | MOSSLNDG | ETL.7590.POLE.WDPS | 2022-06-14 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45618356 | T3 DI MNTA VSTA-BURNS 17/159L RPR GYWW | ICW
LC | 123838722 | 001/021 | T3 DI DRUM-SUMMIT #1 001/021 RPR INSW | SACTO | ETL.1440.INSL.NCER | 2022-06-14 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123838954 | 004/026 | T3 DI RND MTN-TBL MTN #1 4/26 RPR INSS | TABLEMTN | ETL.6060.INSL | 2022-06-14 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45459022 | T3 DI RND MTN-TBL MTN #1 4/26 RPR INSS | ICS
LC | 123839353 | 019/155 | T3 DI CRESTA-RIO OSO 19/155 UNBURY | TABLEMTN | ETL.4590.TOWR | 2022-06-14 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45597882 | T3 DI CRESTA-RIO OSO 19/155 UNBURY | ICQ
LC | 123839658 | 001/027 | T3 EI KESWICK-TRINITY 001/027 RPL ANCW | TABLEMTN | ETL.7270.POLE.NWOD | 2022-06-14 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31620420 | T3 EI KESWICK-TRINITY 001/027 RPL ANCW | 93E
LC | 123839930 | 007/004 | T3 DI PTTR VLLY-WILLITS 7/4 RPL INSW | WILLITS | ETL.7820.INSL.NCER | 2022-06-14 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31627443 | T3 DI PTTR VLLY-WILLITS 7/4 RPL INSW | 93I
LC | 123839991 | 005/009 | T3 EI WISHN-SN JOAQUIN #3 5/9 RMV VEG | FRESNO | ETL.9340.POLE.NWOD | 2022-06-14 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 932 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Road | Repair | 45503361 | T3 EI WISHN-SN JOAQUIN #3 5/9 RMV VEG | CHS
LC | 123840498 | 003/092 | T3 EI DEER CREEK-DRUM 3/92 RPR INSW | SACTO | ETL.6690.INSL.NCER | 2022-06-14 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123840528 | 000/017 | T3 DI DSBL CNTRVL 0/17R RPR STRW | TABLEMTN | ETL.6720.POLE.WDPS | 2022-06-14 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123841308 | 002/056 | T3 EI DEER CREEK-DRUM 2/56 RPL POLE | SACTO | ETL.6690.POLE.WOOD | 2022-06-14 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP CPUA OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31612271 | T3 EI DEER CREEK-DRUM 2/56 RPL POLE | 70Y
LC | 123841545 | ?001/004 | T3 DI SNTH LN-HLF MN BY ?1/4 RPL INSW | METCALF | ETL.7212.INSL.CERA | 2022-06-14 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31612284 | T3 DI SNTH LN-HALF MON BAY ?6/9 RPL INSW | 93I
LC | 123841557 | 002/015 | T3 EI EGL RCK-FLTN-SLVRDO 2/15 RPL HRDT | LAKEVLLE | ETL.4392.TOWR | 2022-06-14 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123841644 | 002/015 | T3 EI EGL RCK-FLTN-SLVRDO 2/15 RPR FOND | LAKEVLLE | ETL.4392.TOWR | 2022-06-14 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123842834 | 003/097 | T3 EI DEER CREEK-DRUM 3/97 RPL POLE | SACTO | ETL.6690.POLE.WOOD | 2022-06-14 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31627627 | T3 DI DEER CREEK-DRUM 0/20 RPL POLE | 70Y
LC | 123843289 | 007/082 | T3 DI GYSRS#3-CLVRDLE 007/082 RPR SPLW | LAKEVLLE | ETL.1650.INSL.NCER | 2022-06-14 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Splice-Wood | Repair | 45575600 | T3 DI GYSRS#3-CLVRDLE 007/082 RPR SPLW | ICW
LC | 123843333 | ?005/003 | T3 EI SNTH LN-HLF MN BY ?5/3 RPR GYWW | METCALF | ETL.7212.POLE.WOOD | 2022-06-14 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45600690 | T3 EI SNTH LN-HLF MN BY ?5/3 RPR GYWW | ICW
LC | 123843424 | 000/013 | T3 DI BRNS LN STR #1 0/13 RPR STRW | MOSSLNDG | ETL.6230.POLE.WOOD | 2022-06-14 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45618800 | T3 DI BRNS LN STR #1 0/13 RPR STRW | ICW
LC | 123844573 | 010/044 | T3 DI MRAGA-CSTRO VLLY 10/44 RPL INSS | CONCORD | ETL.5250.INSL | 2022-06-14 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617072 | T3 DI MRAGA-CSTRO VLLY RPL INSS 2TWR | 93K
LC | 123844574 | 010/044 | T3 DI MRAGA-CSTRO VLLY 10/44 RPR FOND | CONCORD | ETL.5250.TOWR | 2022-06-14 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123844576 | Z013/004 | T3 DI FLTN-CLSTGA ;13/004 RPR INSW | LAKEVLLE | ETL.6880.INSL.NCER | 2022-06-14 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45485961 | T3 DI FLTN-CLSTGA ;13/004 RPR INSW | ICS
LC | 123844723 | 006/006 | T3 EI BRIDGEVILLE-GARBERVLL 6/6 RPR GYWW | EUREKA | ETL.6220.POLE.WOOD | 2022-06-14 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45640242 | T3 EI BRIDGEVILLE-GARBERVLL 6/6 RPR GYWW | ICW
LC | 123844724 | 006/003 | T3 EI BRIDGEVILLE-GARBERVL 6/3 RPR GYWW | EUREKA | ETL.6220.POLE.NWOD | 2022-06-14 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45640243 | T3 EI BRIDGEVILLE-GARBERVL 6/3 RPR GYWW | ICW
LC | 123844750 | 005/147 | T3 DI DEER CREEK-DRUM 5/147 RPR INSW | SACTO | ETL.6690.INSL.CERA | 2022-06-14 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123844755 | ?008/005 | T3 DI SNTH LN-HLF MN BY ?8/5L RPR STRW | METCALF | ETL.7212.POLE.WDPS | 2022-06-14 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45600691 | T3 DI SNTH LN-HLF MN BY ?8/5L RPR STRW | ICW
LC | 123844757 | ?008/005 | T3 DI SNTH LN-HLF MN BAY ?8/5R RPR STRW | METCALF | ETL.7212.POLE.WDPS | 2022-06-14 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45600692 | T3 DI SNTH LN-HLF MN BAY ?8/5R RPR STRW | ICW
LC | 123844779 | 006/151 | T3 DI DRUM-GRSS VLLY-WMR 6/151 RPL ANCW | SACTO | ETL.6760.POLE.WOOD | 2022-06-14 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Anchor-Wood | Replace | 31612262 | T3 DI DRM-GRSS VLLY-WMR 3/82 REFRAME | 93E
LC | 123844790 | 006/151 | T3 DI DRUM-GRSS VLLY-WMR 6/151 RPL HRDW | SACTO | ETL.6760.INSL.NCER | 2022-06-14 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123846467 | 008/037 | T3 GEYSERS #12-FULTON 8/37 RPR CNDW | LAKEVLLE | ETL.4750.INSL.NCER | 2022-06-15 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW OTHR OH RTNR FMOB TR3 PRTO | No Good/Out of Stdrd | Conductor-Steel | Repair
LC | 123846945 | 017/000 | T3 EI MONTE RIO-FORT ROSS 17/0 RPR JMPW | LAKEVLLE | ETL.6979.INSL.NCER | 2022-06-15 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Jumper-Wood | Repair | 45576012 | T3 EI MONTE RIO-FORT ROSS 17/0 RPR JMPW | ICW
LC | 123846988 | 010/006 | T3 DI MENDOCINO-WILLITS 10/006 REFRAME | WILLITS | ETL.7540.POLE.WOOD | 2022-06-15 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31617361 | T3 DI MENDOCINO-WILLITS 10/006 REFRAME | 93E
LC | 123847765 | 003/042 | T3 EI WT PNT-VEY SPRGS 3/42 RPR POLE | VICTOR | ETL.8350.POLE.WOOD | 2022-06-15 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45541936 | T3 EI WT PNT-VEY SPRGS 3/42 RPR POLE | ICW
LC | 123848412 | 003/040 | T3 EI WST PNT-VLLY SPRNGS 3/40 RPL STRW | VICTOR | ETL.8350.POLE.WOOD | 2022-06-15 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace
LC | 123848710 | 017/001 | T3 EI MONTE RIO-FORT ROSS 17/1 RPR JMPW | LAKEVLLE | ETL.6979.INSL.NCER | 2022-06-15 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Jumper-Wood | Repair | 45576013 | T3 EI MONTE RIO-FORT ROSS 17/1 RPR JMPW | ICW
LC | 123849455 | 002/044 | T3 EI KESWICK-TRINITY 002/044 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2022-06-15 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31620253 | T3 EI KESWICK-TRINITY 002/044 RPL POLE | 70Y
LC | 123849501 | 015/128 | T3 EI CRESTA-RIO OSO 015/128 UNBURY | TABLEMTN | ETL.4590.TOWR | 2022-06-15 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45597810 | T3 EI CRESTA-RIO OSO 015/128 UNBURY | ICQ
LC | 123850944 | 000/009 | T3 EI WT PNT-VEY SPRGS 0/9 RPR GYWW | VICTOR | ETL.8350.POLE.WOOD | 2022-06-15 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45541937 | T3 EI WT PNT-VEY SPRGS 0/9 RPR GYWW | ICW
LC | 123851510 | 016/183 | T3 EI IGNCIO-BLNS #2 16/183 INS CTL GRD | LAKEVLLE | ETL.7180.POLE.WOOD | 2022-06-15 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | Missing | Animal Guard-Wood | Install | 45457374 | T3 EI IGNCIO-BLNS #2 16/183 INS CTL GRD | ICW
LC | 123851704 | 006/149 | T3 EI DER CREEK-DRUM 006/149 RPR FOUND | SACTO | ETL.6690.POLE.STPS | 2022-06-15 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45593314 | T3 EI DER CREEK-DRUM 006/149 RPR FOUND | ICQ
LC | 123851705 | 006/149 | T3 EI DER CREEK-DRUM_006/149 RPR GYWW | SACTO | ETL.6690.POLE.STPS | 2022-06-15 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123851844 | 004/068 | T3 EI MIDDLEFORK #1 4/68 RPR INSW | SACTO | ETL.8405.INSL.NCER | 2022-06-15 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123852230 | 000/001 | T3 DI MORAGA-OAKLAND #1 00/01 RPR INSS | CONCORD | ETL.2720.INSL | 2022-06-15 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45502972 | T3 DI MORAGA-OAKLAND #1 00/01 RPR INSS | ICS
LC | 123852452 | 020/161 | T3 DI MIDDLE FRK-GLD HLL 20/161 RPR INSW | SACTO | ETL.5140.INSL.CERA | 2022-06-15 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123852570 | 007/053 | T3 DI MRAGA-SAN LEANDRO#1 07/53 RPR STRT | CONCORD | ETL.2770.TOWR | 2022-06-15 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123852649 | 000/004 | T3 DI GEYSERS #13 TAP 000/004 RPL HRDT | LAKEVLLE | ETL.4781.TOWR | 2022-06-15 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123852671 | 000/004 | T3 DI GEYSERS #13 TAP 00/004 RPR INSS | LAKEVLLE | ETL.4781.INSL | 2022-06-15 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575540 | T3 DI GEYSERS #13 TAP 00/004 RPR INSS | ICS
LC | 123852682 | 005/025 | T3 DI EGLE RCK-FLTN-SLVRDO 5/25 RPR FOND | LAKEVLLE | ETL.4392.TOWR | 2022-06-15 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123852834 | 000/001B | T3 DI MORAGA-LAKEWOOD 00/01B RPL INSS | CONCORD | ETL.3741.INSL | 2022-06-15 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31608730 | T3 DI MORAGA-LAKEWOOD RPL INSS 3TWR | 93K
LC | 123852840 | 010/009 | T3 EI BRIDGEVL-GARBERVL 10/9 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-06-15 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611487 | T3 EI BRIDGVLLE-GARBERVLLE 9/8 RPL POLE | 70Y
LC | 123853024 | ?003/010 | T3 DI SNEATH LNE-HLF MN BY ?3/10 COTTER | METCALF | ETL.7212.INSL.NCER | 2022-06-15 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45600696 | T3 DI SNEATH LNE-HLF MN BY ?3/10 COTTER | ICW
LC | 123853042 | B023/510 | T3 DI DRM-GRSS VLLY-WMR B23/510 RPR INSW | SACTO | ETL.6760.INSL.CERA | 2022-06-15 | 2022-05-16 |  | 2022-11-12 | 2022-11-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCM OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123853053 | 001/013 | T3 DI MORAGA-OAKLAND #1 1/13 RPL INSS | CONCORD | ETL.2720.INSL.CERA | 2022-06-15 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31620104 | DI MORAGA-OAKLAND #1 1/13 RPL INSS | 93K
LC | 123853056 | 001/013 | T3 DI MORAGA-OAKLAND #1 1/13 BNT STEEL | CONCORD | ETL.2720.TOWR | 2022-06-15 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123853070 | 032/139 | T3 DI FULTON-LAKEVILLE 032/139 RMV NEST | LAKEVLLE | ETL.4950.TOWR | 2022-06-15 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | Debris/Nest/etc. | Structure-Steel | Remove | 45571457 | T3 DI FULTON-LAKEVILLE 032/139 RMV NEST | ICS
LC | 123853153 | 002/007 | T3 DI FULTON-CALISTOGA 2/7 RPR INSW | LAKEVLLE | ETL.6880.INSL.NCER | 2022-06-15 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123853186 | 014/186 | T3 EI WEIMAR #1 14/186C RPR GYWW | SACTO | ETL.7560.POLE.WDPS | 2022-06-15 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123853255 | 006/047 | T3 DI MRGA-SAN LNDRO #1 006/047 UNBURY | CONCORD | ETL.2770.TOWR | 2022-06-15 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123853575 | 006/032 | T3 DI EGL RCK FLTN SLVRD 6/32 INS STEP | LAKEVLLE | ETL.4392.TOWR | 2022-06-16 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH XMPT TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Tower | Install
LC | 123853614 | 008/009 | T3 DI POTTER VALLEY-WLTS 8/9 RPR WDPKR | WILLITS | ETL.7820.POLE.WOOD | 2022-06-16 | 2022-05-14 |  | 2022-11-10 | 2022-11-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123853733 | 002/019 | T3 DI MRGA-SAN LNDRO #1 2/19 RMV VEG | CONCORD | ETL.2770.TOWR | 2022-06-16 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123853805 | :000/004 | T3 DI EGL RCK-FLTN SLVRDO 0/4 RPR INSS | LAKEVLLE | ETL.4392.INSL.CERA | 2022-06-16 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123853868 | 003/021 | T3 DI MORAGA-OAKLAND "J" 3/021 RPL INSS | CONCORD | ETL.2760.INSL | 2022-06-16 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31620102 | T2 DI MORAGA-OAKLAND "J" RPL INSS IN 4 T | 93K
LC | 123853990 | 003/021 | T3 DI MRGA-SAN LNDRO #3 3/21 RMV VEG | CONCORD | ETL.2790.TOWR | 2022-06-16 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123854028 | 000/011 | T3 EI WEST PNT-VALY SPRNGS 0/11 RPR POLE | VICTOR | ETL.8350.POLE.WOOD | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45541982 | T3 EI WEST PNT-VALY SPRNGS 0/11 RPR POLE | ICW
LC | 123855190 | 000/014 | T3 EI WST PNT-VEY SPNGS 0/14 RPL POLE | VICTOR | ETL.8350.POLE.WOOD | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31616032 | T3 EI WST PNT-VEY SPNGS 0/14 RPL POLE | 70Y
LC | 123855483 | 002/046 | T3 EI MIDDLEFORK #1 2/46 RPR INSW | SACTO | ETL.8405.INSL.NCER | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123855570 | 017/156 | T3 DI MNTA VISTA-BRNS 17/156 RPR HRDW | MOSSLNDG | ETL.7590.POLE.NWOD | 2022-06-16 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH XMPT TR3 PRTO AIR FRAB | Missing | Hardware-Wood | Install | 45618803 | T3 DI MNTA VISTA-BRNS 17/156 RPR HRDW | ICW
LC | 123855574 | 010/065 | T3 DI C5K9 OLEUM-G#1 10/065 RPR STRT | CONCORD | ETL.3150.TOWR | 2022-06-16 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAR | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123855576 | 010/065 | T3 DI C5K9 OLEUM-G#1 10/065 RPL HRDS | CONCORD | ETL.3150.TOWR | 2022-06-16 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR FRAR | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123855689 | Z005/004 | T3 DI FULTON-CALISTG Z5/4 BNT STEEL | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-06-16 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123855819 | ?007/008 | T3 DI SNTH LN-HLF MN BAY ?7/8 RPL HRDD | METCALF | ETL.7212.POLE.NWOD | 2022-06-16 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH XMPT TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45600697 | T3 DI SNTH LN-HLF MN BAY ?7/8 RPL HRDD | ICW
LC | 123855902 | 021/319 | T3 EI GOLD HILL #1 021/319 RPR GYWW | SACTO | ETL.6950.POLE.NWOD | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123855923 | ?004/003 | T3 EI SNEATH LANE-HMB ?4/3 RPR GYWW | METCALF | ETL.7212.POLE.WOOD | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45600698 | T3 EI SNEATH LANE-HMB ?4/3 RPR GYWW | ICW
LC | 123855987 | 017/138 | T3 DI PRDISE-TBL MTN 17/138 RPR INSW | TABLEMTN | ETL.4316.INSL.NCER | 2022-06-16 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123856162 | 007/006 | T3 EI KNCTI-EAGLE RCK 7/6 RPL STRW | WILLITS | ETL.6861.POLE.WOOD | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB XMPT TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606237 | T3 DI KNCTI-EGLE RCK 1/5 RPL STRW | 70Y
LC | 123856201 | 001/000 | T3 EI KONOCTI-EAGLE ROCK 01/00R RPR GYWW | WILLITS | ETL.6861.POLE.STPS | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45449391 | T3 EI KONOCTI-EAGLE ROCK 01/00R RPR GYWW | ICW
LC | 123856524 | 001/017A | T3 EI WT PNT-VLEY SPRGS 1/17A RPL HRDW | VICTOR | ETL.8350.POLE.WOOD | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45541983 | T3 EI WT PNT-VLEY SPRGS 1/17A RPL HRDW | ICW
LC | 123856630 | 001/017B | T3 EI WT POINT-VLEY SPGS 1/17B RPL HRDW | VICTOR | ETL.8350.POLE.WOOD | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45541984 | T3 EI WT POINT-VLEY SPGS 1/17B RPL HRDW | ICW
LC | 123856633 | 021/314 | T3 EI GOLD HILL #1 021/314 RPL POLE | SACTO | ETL.6950.POLE.WOOD | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31614770 | T3 WV GOLD HILL #1 12/192 RPL POLE | 70Y
LC | 123856691 | 001/000 | T3 EI KONOCTI-EAGLE ROCK 01/00L RPR GYWW | WILLITS | ETL.6861.POLE.STPS | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45449390 | T3 EI KONOCTI-EAGLE ROCK 01/00L RPR GYWW | ICW
LC | 123856693 | 021/317 | T3 EI GOLD HILL #1 021/317 INS IBWW | SACTO | ETL.6950.POLE.NWOD | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Replace
LC | 123856729 | 001/017C | T3 EI WT PNT-VEY SPRGS 1/17C RPL HRDW | VICTOR | ETL.8350.POLE.WOOD | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45541985 | T3 EI WT PNT-VEY SPRGS 1/17C RPL HRDW | ICW
LC | 123857729 | 007/004 | T3 EI KONOCTI-EAGLE ROCK 7/4 RPR GYWW | WILLITS | ETL.6861.POLE.WOOD | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | Missing | Guy Wire-Wood | Install
LC | 123858803 | 003/057 | T3 EI MIDDLEFORK #1 3/57 RPL POLE | SACTO | ETL.8405.POLE.WOOD | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31619027 | T3 DI MIDDLEFORK #1 0/5 RPL POLE | 70Y
LC | 123858812 | 003/055 | T3 EI MDDLFRK #1 3/55 RPR INSW | SACTO | ETL.8405.INSL.CERA | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123858825 | 005/061A | T3 DI DRM RIO OSO #2 5/61A RPL HRDD | SACTO | ETL.1430.POLE.STPS | 2022-06-16 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123859480 | 000/001 | T3 MORGA OAKLND #2 0/1 RPR CNDW | CONCORD | ETL.2730.INSL | 2022-06-16 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO NTDE | No Good/Out of Stdrd | Jumper-Steel | Repair | 45502975 | T3 MORGA OAKLND #2 0/1 RPR CNDW | ICS
LC | 123859652 | 003/022 | T3 DI MRGA SAN LNDRO #3 3/22 RMV VEG | CONCORD | ETL.2790.TOWR | 2022-06-16 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123859917 | 008/124 | T3 DI MDLFRK #1 8/124 RPL GYWW | SACTO | ETL.8405.POLE.WOOD | 2022-06-16 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Replace
LC | 123859963 | 034/169 | T3 DI FLTN PBL 34/169 RPL DAMS | LAKEVLLE | ETL.4392.INSL.NCER | 2022-06-16 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Damper-Steel | Replace | 45575469 | T3 DI FLTN PBL 34/169 RPL DAMS | ICS
LC | 123860160 | 024/198 | T3 DI CRBRY SWST-RND MTN 24/198 RPR SPLS | TABLEMTN | ETL.5410.INSL | 2022-06-16 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Steel | Repair
LC | 123860285 | 012/212 | T3 DI CLGT-CHLLNG 12/212 RPR INSW | SACTO | ETL.6480.INSL.NCER | 2022-06-16 | 2022-05-27 |  | 2022-11-23 | 2022-11-27 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123860359 | 006/065 | T3 DI DRM RIO OSO #2 6/65 RPR INSS | SACTO | ETL.1430.INSL.NCER | 2022-06-16 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123860444 | 013/000 | T3 DI DONNELLS-MI-WUK 13/000 RPL HRDW | VICTOR | ETL.1400.POLE.STPS | 2022-06-16 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45519341 | T3 DI DONNELLS-MI-WUK 13/000 RPL HRDW | ICW
LC | 123860537 | 003/002 | T3 DI DNLS MI WK 3/2 RPR STRW | VICTOR | ETL.1400.POLE.WDPS | 2022-06-16 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45519342 | T3 DI DNLS MI WK 3/2 RPR STRW | ICW
LC | 123860538 | 003/002 | T3 DI DNLS MI WK 3/2 INST HRDD | VICTOR | ETL.1400.POLE.WDPS | 2022-06-16 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45519343 | T3 DI DNLS MI WK 3/2 INST HRDD | ICW
LC | 123860560 | 003/002 | T3 DI DNLS MI WK 3/2 RPL INSW | VICTOR | ETL.1400.INSL.NCER | 2022-06-16 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Wood | Replace | 31612353 | T3 DI DONNELLS-MI-WUK 010/002L RPL INSW | 93I
LC | 123862138 | 000/014 | T3 DI VOLTA-SOUTH 000/014 RPR INSW | TABLEMTN | ETL.8300.INSL.NCER | 2022-06-17 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45456487 | T3 DI VOLTA-SOUTH 000/014 RPR INSW | ICW
LC | 123862159 | 004/044 | T3 DI DRUM-RIO OSO #2 4/044 RPL HRDT | SACTO | ETL.1430.TOWR | 2022-06-17 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45600036 | T3 DI DRUM-RIO OSO #2 4/044 RPL HRDT | ICQ
LC | 123862160 | 005/145 | T3 DI DEER CREEK-DRUM 5/145 RPL INSW | SACTO | ETL.6690.INSL.NCER | 2022-06-17 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31618457 | T3 DI DEER CREEK-DRUM 3/96 RPL INSW | 93I
LC | 123862218 | 004/022 | T3 DI EGL RCK-FLTN-SLVRD 4/22 RPL HRDT | LAKEVLLE | ETL.4392.TOWR | 2022-06-17 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123862359 | 009/000 | T3 DI FLTN CLSTG 9/0R RPR GYWW | LAKEVLLE | ETL.6880.POLE.STPS | 2022-06-17 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45467442 | T3 DI FLTN CLSTG 9/0R RPR GYWW | ICW
LC | 123862412 | 006/042 | T3 DI MRGA-SAN LNDRO #1 006/042 RPR STRT | CONCORD | ETL.2770.TOWR | 2022-06-17 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123862710 | 004/007 | T3 DI FULTON-CALISTOGA 004/007 MASTIC | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-06-17 | 2022-06-08 |  | 2022-12-05 | 2022-12-08 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45485769 | T3 DI FULTON-CALISTOGA 004/007 MASTIC | ICW
LC | 123862919 | 014/068 | T3 DI TASSAJARA-NWRK 14/68 RPL INSS | CONCORD | ETL.5920.INSL | 2022-06-17 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31625571 | DI TSJRA NWRK RPL INSS IN 7 TWRS | 93K
LC | 123862980 | 010/001 | T3 DI BRIDGVILLE-GARBERVL 10/1 RPL TIE W | EUREKA | ETL.6220.INSL.CERA | 2022-06-17 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM COMP OH TR3 PRTO AIR | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45640244 | T3 DI BRIDGVILLE-GARBERVL 10/1 RPL TIE W | ICW
LC | 123863006 | 002/018 | T3 DI EL DOR-MISS FT #1 2/18 RPR INSS | SACTO | ETL.1530.INSL.CERA | 2022-06-17 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123863063 | 005/029 | T3 DI CASTRO VLLY-NWRK 5/29 BNT STEEL | CONCORD | ETL.4450.TOWR | 2022-06-17 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123863641 | 010/105B | T3 DI GRN VLLY-CAMP EVRS 10/105 RPR INSW | MOSSLNDG | ETL.1710.INSL.NCER | 2022-06-17 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45618805 | T3 DI GRN VLLY-CAMP EVRS 10/105 RPR INSW | ICW
LC | 123864281 | 018/279 | T3 EI GOLD HILL #1 18/279 RPR STRW | SACTO | ETL.6950.POLE.WOOD | 2022-06-17 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123864360 | 019/000 | T3 DI MAPLE CREEK-HOOPA 19/0L RPR GYWW | EUREKA | ETL.7490.POLE.WDPS | 2022-06-17 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123864414 | 003/002 | T3 DI FULTON-CALISTOGA 3/2 RPR GYWW | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-06-17 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45571445 | T3 DI FULTON-CALISTOGA 3/2 RPR GYWW | ICW
LC | 123864468 | 001/010 | T3 EI KONOCTI-EAGLE ROCK 1/10 RPR STRW | WILLITS | ETL.6861.POLE.WOOD | 2022-06-17 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123864469 | 001/010 | T3 EI KONOCTI-EAGLE ROCK 1/10 RPL HRDD | WILLITS | ETL.6861.POLE.WOOD | 2022-06-17 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123864642 | 003/015 | T3 DI GEYSERS #9-LAKEVILLE 3/15 RPR INSS | LAKEVLLE | ETL.4780.INSL.CERA | 2022-06-17 | 2022-06-11 |  | 2022-12-08 | 2022-12-11 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123864660 | 009/008 | T3 EI POTTER VALLEY-WILLITS 9/8 RPR CRSW | WILLITS | ETL.7820.POLE.WOOD | 2022-06-17 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair
LC | 123864704 | 017/005 | T3 DI DONNELLS-MI-WUK 17/5L RPL HRDW | VICTOR | ETL.1400.POLE.WDPS | 2022-06-17 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45519344 | T3 DI DONNELLS-MI-WUK 17/5L RPL HRDW | ICW
LC | 123864723 | ?006/002 | T3 DI SNTH LN-HLF MN BY ?006/2 RPL INSW | METCALF | ETL.7212.INSL.NCER | 2022-06-17 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31612284 | T3 DI SNTH LN-HALF MON BAY ?6/9 RPL INSW | 93I
LC | 123864782 | 017/005 | T3 DI DONNELLS-MI-WUK 17/5R RPL HRDW | VICTOR | ETL.1400.POLE.WDPS | 2022-06-17 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace | 45519345 | T3 DI DONNELLS-MI-WUK 17/5R RPL HRDW | ICW
LC | 123864789 | 017/005 | T3 DI DONNELLS-MI-WUK 17/5R RPR GYWW | VICTOR | ETL.1400.POLE.WDPS | 2022-06-17 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45519346 | T3 DI DONNELLS-MI-WUK 17/5R RPR GYWW | ICW
LC | 123864865 | 017/005 | T3 DI DONNELLS-MI-WUK 017/005 RPR JMPW | VICTOR | ETL.1400.INSL | 2022-06-17 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Wood | Repair | 45519347 | T3 DI DONNELLS-MI-WUK 017/005 RPR JMPW | ICW
LC | 123864976 | 031/151 | T3 DI FULTON-PUEBLO 31/151 RPR FOND | LAKEVLLE | ETL.1600.TOWR | 2022-06-17 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair
LC | 123865205 | 019/002 | T3 EI MI-WUK-CURTIS 19/2 RPL INSW | VICTOR | ETL.1073.INSL.CERA | 2022-06-17 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Replace | 31629710 | T3 EI MI-WUK-CURTIS 19/2 RPL INSW | 93I
LC | 123865481 | 005/063 | T3 DI DRUM-RIO OSO #2 5/63 RPL HRDT | SACTO | ETL.1430.TOWR | 2022-06-17 | 2022-05-17 |  | 2022-11-13 | 2022-11-17 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45600067 | T3 DI DRUM-RIO OSO #2 5/63 RPL HRDT | ICQ
LC | 123865571 | 009/006 | T3 EI POTTR VLLY-WILLITS 9/6 RPR POLE | WILLITS | ETL.7820.POLE.WOOD | 2022-06-17 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123865638 | 008/065 | T3 EI TIGER CREEK-ELECTRA 8/65 BNT STEEL | VICTOR | ETL.5780.TOWR | 2022-06-17 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3N PRTO FRAB | Anti-Climbing Guard | Structure-Tower | Repair | 45591546 | T3 EI TIGER CREEK-ELECTRA 8/65 BNT STEEL | ICQ
LC | 123865671 | 018/278 | T3 EI GOLD HILL #1 18/278 RPL POLE | SACTO | ETL.6950.POLE.WOOD | 2022-06-17 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace
LC | 123865672 | 008/065 | T3 EI TIGER CREEK-ELECTRA 8/65 RPR SPLS | VICTOR | ETL.5780.INSL | 2022-06-17 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | No Good/Out of Stdrd | Splice-Steel | Repair | 45541987 | T3 EI TIGER CREEK-ELECTRA 8/65 RPR SPLS | ICS
LC | 123866252 | 004/070 | T3 DI KESWICK-TRINITY 004/070 RMV VEG | TABLEMTN | ETL.7270.POLE.STPS | 2022-06-17 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR | Overgrown | Vegetation | Remove
LC | 123866334 | 009/004 | T3 EI POTTER VALLEY-WLITS 9/4 RPR ARMR | WILLITS | ETL.7820.INSL.CERA | 2022-06-17 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Conductor-Wood | Repair
LC | 123866335 | 009/004 | T3 EI POTTER VALLEY-WILLITS 9/4 RPR CRSW | WILLITS | ETL.7820.POLE.WOOD | 2022-06-17 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Repair
LC | 123866754 | 022/006 | T3 DI MAPLE CREEK-HOOPA 22/6 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2022-06-17 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123866778 | 001/025 | T3 VOLTA-DESCHUTES 1/025 RPR BOND | TABLEMTN | ETL.8290.POLE.WOOD | 2022-06-17 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45458835 | T3 VOLTA-DESCHUTES 1/025 RPR BOND | ICW
LC | 123867323 | 022/181 | T3 EI MSSR FLT-GLD HLL #1 22/181 REFRAME | SACTO | ETL.2660.POLE.NWOD | 2022-06-17 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP CPUA OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Steel | Replace
LC | 123867871 | 012/102 | T3 EI CRESTA-RIO OSO 12/102 RPL INSS | TABLEMTN | ETL.4590.INSL | 2022-06-17 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615914 | T2 EI CRESTA-RIO RPL INSS 10 STRTS | 93K
LC | 123869873 | 018/000 | T3 DI DONNLLS-MI-WUK 018/000 RPR GYWW | VICTOR | ETL.1400.POLE.WDPS | 2022-06-18 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45519348 | T3 DI DONNLLS-MI-WUK 018/000 RPR GYWW | ICW
LC | 123869890 | 001/014 | T3 DI EL DORADO-MS FL#1 001/014 RPL HRDT | SACTO | ETL.1530.TOWR | 2022-06-18 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace | 45600077 | T3 DI EL DORADO-MS FL#1 001/014 RPL HRDT | ICQ
LC | 123869920 | 003/040 | T3 DI DRUM-RIO OSO #1 3/40 RPR INSS | SACTO | ETL.1420.INSL.NCER | 2022-06-18 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123869968 | ;001/017 | T3 DI SNTH LN-HLF MN BY ;1/17 RPR IBWW | METCALF | ETL.7212.POLE.WOOD | 2022-06-18 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45600699 | T3 DI SNTH LN-HLF MN BY ;1/17 RPR IBWW | ICW
LC | 123870073 | 006/117 | T3 DI BRIONES TAP 006/117 INS COTTER | CONCORD | ETL.7055.INSL.NCER | 2022-06-18 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45515100 | T3 DI BRIONES TAP 006/117 INS COTTER | ICW
LC | 123870096 | 022/178 | T3 EI MSSR FLT-GLD HLL #1 22/178 REFRAME | SACTO | ETL.2660.POLE.NWOD | 2022-06-18 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP CPUA OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Steel | Replace
LC | 123870182 | 022/004 | T3 EI TMI-WUK-CURTIS 22/004 RPR INSS | VICTOR | ETL.1073.INSL.CERA | 2022-06-18 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45519349 | T3 EI TMI-WUK-CURTIS 22/004 RPR INSS | ICS
LC | 123870197 | 008/038 | T3 DI GEYSERS #12-FLTN 8/038 RPR INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2022-06-18 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575479 | T3 DI GEYSERS #12-FLTN 8/038 RPR INSS | ICS
LC | 123870199 | 008/038 | T3 DI GEYSERS #17-FLTN 8/038 RPR INSS | LAKEVLLE | ETL.4770.INSL.CERA | 2022-06-18 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123870246 | 008/038 | T3 DI GEYSERS #12-FLTN 8/038 RPL HRDT | LAKEVLLE | ETL.4750.TOWR | 2022-06-18 | 2022-05-19 |  | 2022-11-15 | 2022-11-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123870291 | 001/025 | T3 DI BRNS-LONE STR #2 001/025 RPR GRWW | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-06-18 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 45618806 | T3 DI BRNS-LONE STR #2 001/025 RPR GRWW | ICW
LC | 123870295 | 001/025 | T3 DI BRNS-LONE STR #2 001/025 RPR CNDW | MOSSLNDG | ETL.6240.INSL.NCER | 2022-06-18 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Wood | Repair | 45618807 | T3 DI BRNS-LONE STR #2 001/025 RPR CNDW | ICW
LC | 123870300 | 014/109 | T3 DI MNTA VSTA-BRNS 14/109 RPR GYWW | MOSSLNDG | ETL.7590.POLE.WOOD | 2022-06-18 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45618808 | T3 DI MNTA VSTA-BRNS 14/109 RPR GYWW | ICW
LC | 123870332 | :005/008 | T3 DI FULTON-CALISTOGA :5/8 INS COTTER | LAKEVLLE | ETL.6880.INSL.NCER | 2022-06-18 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45571443 | T3 DI FULTON-CALISTOGA :5/8 INS COTTER | ICW
LC | 123870333 | :005/008 | T3 DI FULTON-CALISTOGA :005/008 RPL ANCW | LAKEVLLE | ETL.6880.POLE.WOOD | 2022-06-18 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31620119 | T3 DI FULTON-CALISTOGA :005/008 RPL ANCW | 93E
LC | 123870477 | 008/215 | T3 DI COLGATE-ALLEGHANY 8/215 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2022-06-18 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31612265 | T3 DI COLGATE-ALLEGHANY 8/215 RPL POLE | 70Y
LC | 123870671 | 018/084 | T3 DI TASSAJARA-NEWARK 18/84 RPL INSS | CONCORD | ETL.5920.INSL.CERA | 2022-06-18 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31625571 | DI TSJRA NWRK RPL INSS IN 7 TWRS | 93K
LC | 123870684 | 022/180 | T3 EI MSSR FLT-GLD HLL #1 22/180 REFRAME | SACTO | ETL.2660.POLE.NWOD | 2022-06-18 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 93Z | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP CPUA OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Steel | Replace
LC | 123871116 | 041/301 | T3 DI CARIBOU TBL MTN 41/301 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2022-06-18 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31629130 | T2 DI CARIBOU-TBL MTN RPL INSS 10 TWRS | 93K
LC | 123871170 | 014/119 | T3 EI CRESTA-RIO OSO 14/119 RPL INSS | TABLEMTN | ETL.4590.INSL | 2022-06-18 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615914 | T2 EI CRESTA-RIO RPL INSS 10 STRTS | 93K
LC | 123871201 | 015/001 | T3 DI MAPLE CREEK-HOOPA 15/1 RPR STRW | EUREKA | ETL.7490.POLE.WOOD | 2022-06-18 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123871204 | 003/039 | T3 DI DRUM-SUMMIT #1 003/039R RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2022-06-18 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123871272 | 014/120 | T3 EI CRESTA-RIO OSO 14/120 RPL INSS | TABLEMTN | ETL.4590.INSL | 2022-06-18 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615915 | T3 EI CRESTA-RIO OSO RPL INSS 10 STRTS | 93K
LC | 123871623 | 012/000 | T3 DI DONNELLS-MI-WUK 12/000 RMV STEP | VICTOR | ETL.1400.POLE.STPS | 2022-06-18 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45519351 | T3 DI DONNELLS-MI-WUK 12/000 RMV STEP | ICW
LC | 123871858 | 000/005 | T3 EI VOLTA-DESCHUTES 0/5 RPL HRDW | TABLEMTN | ETL.8290.POLE.NWOD | 2022-06-18 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45458836 | T3 EI VOLTA-DESCHUTES 0/5 RPL HRDW | ICW
LC | 123871902 | ?001/010 | T3 EI SNTH LN-HALF MN BY ?1/10L RPR GYWW | METCALF | ETL.7212.POLE.WDPS | 2022-06-18 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO ZNE1 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45600702 | T3 EI SNTH LN-HALF MN BY ?1/10L RPR GYWW | ICW
LC | 123872001 | 041/302 | T3 DI CARIBOU-TBL MT 41/302 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2022-06-18 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31629130 | T2 DI CARIBOU-TBL MTN RPL INSS 10 TWRS | 93K
LC | 123872003 | 041/302 | T3 DI CARIBOU-TBL MT 41/302 RPL HRDT | TABLEMTN | ETL.4440.TOWR | 2022-06-18 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace | 45593302 | T3 DI CARIBOU-TBL MT 41/302 RPL HRDT | ICQ
LC | 123872824 | 005/070 | T3 DI DRUM-SMMIT#1 5/70R RPL HRDD | SACTO | ETL.1440.POLE.STPS | 2022-06-18 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123872892 | 000/002 | T3 DI GEYSERS #18 TAP 0/2 RPR INSS | LAKEVLLE | ETL.4784.INSL.CERA | 2022-06-18 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45575547 | T3 DI GEYSERS #18 TAP 0/2 RPR INSS | ICS
LC | 123872990 | 014/112 | T3 EI CRESTA-RIO OSO 14/112 RPL INSS | TABLEMTN | ETL.4590.INSL | 2022-06-18 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615914 | T2 EI CRESTA-RIO RPL INSS 10 STRTS | 93K
LC | 123873269 | 006/003 | T3 EI KONOCTI-EAGLE ROCK 6/3 RPR POLE | WILLITS | ETL.6861.POLE.WOOD | 2022-06-18 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123873339 | 003/004 | T3 EI KONOCTI-EAGLE ROCK 3/004 RPR POLE | WILLITS | ETL.6861.POLE.WOOD | 2022-06-18 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123873885 | 006/050 | T3 EI TIGER CREEK-ELECTRA 6/50 BNT STEEL | VICTOR | ETL.5780.TOWR | 2022-06-18 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair | 45591547 | T3 EI TIGER CREEK-ELECTRA 6/50 BNT STEEL | ICQ
LC | 123874384 | 001/034 | T3 DI DEER CREEK-DRUM 0/34 RPL HRDW | SACTO | ETL.6690.POLE.WOOD | 2022-06-18 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123874490 | 026/010 | T3 DI FULTON-HOPLAND 26/10 RPR INSW | LAKEVLLE | ETL.6890.INSL.NCER | 2022-06-18 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45571450 | T3 DI FULTON-HOPLAND 26/10 RPR INSW | ICW
LC | 123874564 | 001/001B | T3 EI BEARDSLEY TAP 01/001B RPR POLE | VICTOR | ETL.1401.POLE.WOOD | 2022-06-18 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45519352 | T3 EI BEARDSLEY TAP 01/001B RPR POLE | ICW
LC | 123874571 | 001/001A | T3 EI BEARDSLEY TAP 01/001A RPR POLE | VICTOR | ETL.1401.POLE.WOOD | 2022-06-18 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45519353 | T3 EI BEARDSLEY TAP 01/001A RPR POLE | ICW
LC | 123874572 | 000/009 | T3 EI BEARDSLEY TAP 00/009 RPR INSW | VICTOR | ETL.1401.INSL.CERA | 2022-06-18 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Wood | Repair | 45519354 | T3 EI BEARDSLEY TAP 00/009 RPR INSW | ICW
LC | 123875271 | 019/156 | T3 EI CRESTA-RIO OSO 19/156 RMV STEP | TABLEMTN | ETL.4590.TOWR | 2022-06-19 | 2022-06-19 |  | 2022-12-16 | 2022-12-19 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | Missing | Hardware-Tower | Install | 45597883 | T3 EI CRESTA-RIO OSO 19/156 RMV STEP | ICQ
LC | 123875603 | 007/002 | T3 EI POTTER VALLEY-WILLITS 7/2 RMV VEG | WILLITS | ETL.7820.POLE.NWOD | 2022-06-19 | 2022-06-19 |  | 2022-12-16 | 2022-12-19 | Late | 932 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Road | Repair | 45590574 | T3 EI POTTER VALLEY-WILLITS 6/3 RMV VEG | CHS
LC | 123875854 | 003/009 | T3 EI KONOCTI-EAGLE ROCK 3/9 RPR GYWW | WILLITS | ETL.6861.POLE.WOOD | 2022-06-19 | 2022-06-19 |  | 2022-12-16 | 2022-12-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123876475 | 020/006C | T3 EI MI-WUK-CURTIS 20/006C RPR WDPKR | VICTOR | ETL.1073.POLE.WOOD | 2022-06-19 | 2022-06-19 |  | 2022-12-16 | 2022-12-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45519355 | T3 EI MI-WUK-CURTIS 20/006C RPR WDPKR | ICW
LC | 123876756 | 020/167 | T3 EI CRESTA-RIO OSO 20/167 RMV NEST | TABLEMTN | ETL.4590.TOWR | 2022-06-19 | 2022-06-19 |  | 2022-12-16 | 2022-12-19 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | Debris/Nest/etc. | Structure-Steel | Remove | 45462390 | T3 EI CRESTA-RIO OSO 20/167 RMV NEST | ICS
LC | 123877210 | 005/001 | T3 EI KONOCTI-EAGLE ROCK 5/1 RPL HRDW | WILLITS | ETL.6861.INSL.NCER | 2022-06-19 | 2022-06-19 |  | 2022-12-16 | 2022-12-19 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123877714 | 020/161 | T3 EI CRESTA-RIO OSO 20/161 RPL INSLS | TABLEMTN | ETL.4590.INSL | 2022-06-19 | 2022-06-19 |  | 2022-12-16 | 2022-12-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615915 | T3 EI CRESTA-RIO OSO RPL INSS 10 STRTS | 93K
LC | 123877715 | 021/168 | T3 EI CRESTA-RIO OSO 21/168 RPL INSS | TABLEMTN | ETL.4590.INSL | 2022-06-19 | 2022-06-19 |  | 2022-12-16 | 2022-12-19 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615915 | T3 EI CRESTA-RIO OSO RPL INSS 10 STRTS | 93K
LC | 123881320 | 000/001B | T3 EI GEYSRS #3-CLOVRDLE 0/1B RPR GYWW | LAKEVLLE | ETL.1650.POLE.WOOD | 2022-06-20 | 2022-06-20 |  | 2022-12-17 | 2022-12-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45501404 | T3 EI GEYSRS #3-CLOVRDLE 0/1B RPR GYWW | ICW
LC | 123882501 | 010/017 | T3 WV BRIDGEVILL-GARBERVL 10/17 RPL POLE | EUREKA | ETL.6220.POLE.NWOD | 2022-06-20 | 2022-06-20 |  | 2022-12-17 | 2022-12-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31606713 | T3 WV BRDGVLL-GRBRVLL 10/17 RPL POLE | 70Y
LC | 123883384 | A000/007C | T3 EI SLY CREEK TAP A000/007C RPR GYWW | TABLEMTN | ETL.4221.POLE.NWOD | 2022-06-20 | 2022-06-20 |  | 2022-12-17 | 2022-12-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45462519 | T3 EI SLY CREEK TAP A000/007C RPR GYWW | ICW
LC | 123883413 | 001/009 | T3 EI SLY CREEK TAP 001/009L RPL POLE | TABLEMTN | ETL.4221.POLE.WDPS | 2022-06-20 | 2022-06-20 |  | 2022-12-17 | 2022-12-20 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617925 | T3 EI SLY CREEK TAP 001/009L RPL POLE | 70Y
LC | 123883721 | ?001/010 | T3 EI SNTH LN-HALF MN BY ?1/10R RPR GYWW | METCALF | ETL.7212.POLE.WDPS | 2022-06-21 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO ZNE1 NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45600703 | T3 EI SNTH LN-HALF MN BY ?1/10R RPR GYWW | ICW
LC | 123883722 | ?001/010 | T3 EI SNTH LN-HALF MN BY ?1/10C RPR GYWW | METCALF | ETL.7212.POLE.WDPS | 2022-06-21 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB XMPT TR3 PRTO ZNE1 NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45600704 | T3 EI SNTH LN-HALF MN BY ?1/10C RPR GYWW | ICW
LC | 123884298 | 018/276 | T3 EI GOLD HILL #1 18/276 RPR GYWW | SACTO | ETL.6950.POLE.WOOD | 2022-06-21 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123884930 | 000/005 | T3 EI EL DRDO-MSSRI FLT #1 0/5 RPR FOND | SACTO | ETL.1530.TOWR | 2022-06-21 | 2022-06-21 |  | 2022-12-18 | 2022-12-21 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP CPUA OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45600076 | T3 EI EL DRDO-MSSRI FLT #1 0/5 RPR FOND | ICQ
LC | 123885123 | 001/034 | T3 DI BURNS-LONE STAR #2 1/34 INS HRDW | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-06-21 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45618809 | T3 DI BURNS-LONE STAR #2 1/34 INS HRDW | ICW
LC | 123886139 | 006/045 | T3 DI MORAGA-SN LNDRO #3 6/45 RPR STRT | CONCORD | ETL.2790.TOWR | 2022-06-21 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123886272 | 006/045 | T3 DI MORAGA-SN LNDRO #3 6/45 RPR INSS | CONCORD | ETL.2790.INSL | 2022-06-21 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45507989 | T3 DI MORAGA-SN LNDRO #3 6/45 RPR INSS | ICS
LC | 123886274 | 006/045 | T3 DI MORAGA-SN LNDRO #3 6/45 RPL HRDT | CONCORD | ETL.2790.TOWR | 2022-06-21 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123886367 | 012/005 | T3 DI DONNELLS-MI WUK 12/5R RPR STRW | VICTOR | ETL.1400.POLE.WDPS | 2022-06-21 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45519356 | T3 DI DONNELLS-MI WUK 12/5R RPR STRW | ICW
LC | 123888161 | 000/007 | T3 DI DRUM-SPAULDING 0/7 RPR INSW | SACTO | ETL.6770.INSL.NCER | 2022-06-21 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123888309 | 000/015 | T3 DI DRM-GRSS VLLY-WMR 0/15 RPR INSW | SACTO | ETL.6760.INSL.NCER | 2022-06-21 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123888560 | 001/010 | T3 DI MORAGA-OAKLAND #3 01/010 BNT STEEL | CONCORD | ETL.2740.TOWR | 2022-06-21 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123888761 | 001/013 | T3 DI MORAGA-SN LNDR #3 1/13 RPR STRT | CONCORD | ETL.2790.TOWR | 2022-06-21 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123888966 | 008/212 | T3 DI COLGATE-ALLEGHANY 8/212 RPR HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-06-21 | 2022-05-18 |  | 2022-11-14 | 2022-11-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123889239 | 005/058A | T3 DI DRUM-RIO OSO #2 005/058A(L) MASTIC | SACTO | ETL.1430.POLE.STPS | 2022-06-21 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123889330 | 004/005 | T3 DI FULTON-CALISTOGA 4/5 RPR POLE | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-06-21 | 2022-05-31 |  | 2022-11-27 | 2022-11-30 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45571430 | T3 DI FULTON-CALISTOGA 4/5 RPR POLE | ICW
LC | 123889378 | 005/058A | T3 DI DRUM-RIO OSO #2 005/058A(R) MASTIC | SACTO | ETL.1430.POLE.STPS | 2022-06-21 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123889719 | 002/015 | T3 DI MRAGA-SN LNDRO #3 002/015 RPR STRT | CONCORD | ETL.2790.TOWR | 2022-06-21 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123889799 | 000/013 | T3 EI CNTRVLL-TBL MTN-ORLL 0/13 RPL POLE | TABLEMTN | ETL.6330.POLE.WOOD | 2022-06-21 | 2022-06-21 |  | 2022-12-18 | 2022-12-21 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611490 | T3 EI CNTRVLL-TBL MTN-ORLL 0/2 RPL POLE | 70Y
LC | 123889803 | 000/002 | T3 EI CNTRVLL-TBL MTN-ORLL 0/2 RPL POLE | TABLEMTN | ETL.6330.POLE.WOOD | 2022-06-21 | 2022-06-21 |  | 2022-12-18 | 2022-12-21 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31611490 | T3 EI CNTRVLL-TBL MTN-ORLL 0/2 RPL POLE | 70Y
LC | 123890107 | 000/012 | T3 DI BURNS-LONE STAR #2 0/12 INS HRDW | MOSSLNDG | ETL.6240.POLE.WOOD | 2022-06-21 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45618810 | T3 DI BURNS-LONE STAR #2 0/12 INS HRDW | ICW
LC | 123891292 | 016/167 | T3 DI IGNACIO-ALTO 16/167 RPL INSW | LAKEVLLE | ETL.7150.INSL.CERA | 2022-06-21 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31619835 | T3 DI IGNACIO-ALTO 16/167 RPL INSW | 93I
LC | 123891677 | 009/005 | T3 DI MENDOCN-WLLTS-FRT 9/5 RPR GYWS | WILLITS | ETL.7550.POLE.WDPS | 2022-06-21 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45640332 | T3 DI MENDOCN-WLLTS-FRT 9/5 RPR GYWS | ICW
LC | 123891705 | ?001/009 | T3 DI SNTH LN-HALF MOON BY ?1/9 RPR INSW | METCALF | ETL.7212.INSL.NCER | 2022-06-21 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45600705 | T3 DI SNTH LN-HALF MOON BY ?1/9 RPR INSW | ICW
LC | 123891865 | 003/030 | T3 DI WOODLEAF-PALERMO 3/30 RMV VEG | TABLEMTN | ETL.4220.POLE.STPS | 2022-06-21 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123891976 | 001/024 | T3 DI BURNS-LONE STAR #1 1/24 RPR GYWW | MOSSLNDG | ETL.6230.POLE.STPS | 2022-06-21 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45618811 | T3 DI BURNS-LONE STAR #1 1/24 RPR GYWW | ICW
LC | 123891977 | 001/008 | T3 DI MORAGA-CLREMNT #2 001/008 RPL INSS | CONCORD | ETL.2710.INSL.CERA | 2022-06-21 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31611421 | T3 DI MORAGA-CLREMNT #2 RPL INSS 2TWR | 93K
LC | 123891989 | 001/006 | T3 DI GEYSERS #12-FULTON 001/06 RPL HRDT | LAKEVLLE | ETL.4750.TOWR | 2022-06-21 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123892095 | 002/024 | T3 DI DRUM-SUMMIT#1 2/24 RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2022-06-21 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123892234 | 007/063 | T3 DI ATASCADERO-CAYUCOS 7/63 RPR INSW | PISMOBCH | ETL.8480.INSL.NCER | 2022-06-21 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45600560 | T3 DI ATASCADERO-CAYUCOS 7/63 RPR INSW | ICW
LC | 123892301 | 020/002 | T3 DI MAPLE CREEK-HOOPA 20/2 RPR INSW | EUREKA | ETL.7490.INSL | 2022-06-21 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123892302 | 020/002 | T3 DI MAPLE CREEK-HOOPA 20/2 RPR STRW | EUREKA | ETL.7490.POLE.WOOD | 2022-06-21 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE ACCH OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123892382 | 008/013 | T3 DI BRIDGEVILLE-GARBERVL 8/13 RPL HRDW | EUREKA | ETL.6220.POLE.WOOD | 2022-06-21 | 2022-05-20 |  | 2022-11-16 | 2022-11-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45451437 | T3 DI BRDGVLL-GRBRVLL 8/13 RPL HRDW | ICW
LC | 123892389 | 007/159 | T3 DI VOLTA-DESCHUTES 7/159 RPL HRDW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-06-21 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB NTDE | Missing | Hardware-Wood | Install | 45458837 | T3 DI VOLTA-DESCHUTES 7/159 RPL HRDW | ICW
LC | 123892407 | 001/013 | T3 DI WISHN-SN JOAQUIN #3 1/13 RPL POLE | FRESNO | ETL.9340.POLE.WOOD | 2022-06-21 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31610814 | T2 EI WISON-SN JOAQUIN 2/9 RPL STRW | 70Y
LC | 123892432 | 015/071 | T3 DI TASSAJARA-NWRK 5/32 RPL INSS | CONCORD | ETL.5920.INSL | 2022-06-21 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31625571 | DI TSJRA NWRK RPL INSS IN 7 TWRS | 93K
LC | 123892433 | 015/071 | T3 DI TASSAJARA-NWRK 5/32 HANGER | CONCORD | ETL.5920.INSL | 2022-06-21 | 2022-06-10 |  | 2022-12-07 | 2022-12-10 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123892435 | 030/131 | T3 DI FULTON-LKVLL-IGNCO 30/131 RPR INSS | LAKEVLLE | ETL.4950.INSL.CERA | 2022-06-21 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571400 | T3 DI FULTON-LKVLL-IGNCO 30/131 RPR INSS | ICS
LC | 123892436 | 030/131 | T3 DI FULTON-LKVLL-IGNCO 30/131 RPR INSS | LAKEVLLE | ETL.2823.INSL.CERA | 2022-06-21 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571400 | T3 DI FULTON-LKVLL-IGNCO 30/131 RPR INSS | ICS
LC | 123892479 | 000/002 | T3 DI DRUM-SUMMIT #1-WD PL 0/2 HRDW RPL | SACTO | ETL.1440.POLE.WDPS | 2022-06-21 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123892530 | 000/002 | T3 DI DRUM-SUMMIT #1-WD PL 0/2 HRDW RPL | SACTO | ETL.1440.POLE.WDPS | 2022-06-21 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123892544 | 015/123B | T3 DI MDLE FORK-GLD HIL 15/123B RPR GYWW | SACTO | ETL.5140.POLE.NWOD | 2022-06-21 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123892546 | 015/123B | T3 DI MDLE FRK-GLD HILL 15/123B RPR INSW | SACTO | ETL.5140.INSL.NCER | 2022-06-21 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123892555 | A005/051A | T3 DI DRUM-HIGGINS A5/51A RPL HRDW | SACTO | ETL.4393.POLE.WOOD | 2022-06-21 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123892556 | A005/051A | T3 DI DRUM-HIGGINS A5/51A RPR POLE | SACTO | ETL.4393.POLE.WOOD | 2022-06-21 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123892607 | 015/123C | T3 DI MDLE FRK-GOLD HIL 15/123C RPR INSW | SACTO | ETL.5140.INSL.NCER | 2022-06-21 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 123892622 | ;002/021 | T3 DI SNEAT LN-HLF MN BAY ;2/21 RPL HRDW | METCALF | ETL.7212.POLE.WOOD | 2022-06-21 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45600708 | T3 DI SNEAT LN-HLF MN BAY ;2/21 RPL HRDW | ICW
LC | 123892625 | ;002/021 | T3 DI SNEAT LN-HLF MN BAY ;2/21 RPR DAMW | METCALF | ETL.7212.INSL.NCER | 2022-06-21 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Damper-Wood | Replace | 45600709 | T3 DI SNEAT LN-HLF MN BAY ;2/21 RPR DAMW | ICW
LC | 123893363 | 003/036A | T3 EI SLY CREEK TAP -03/036A RPR GYWW | TABLEMTN | ETL.4221.POLE.NWOD | 2022-06-22 | 2022-06-22 |  | 2022-12-19 | 2022-12-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123893448 | 006/069A | T3 DI DRM RIO OSO #2 6/69A RPR CRSW | SACTO | ETL.1430.POLE.WDPS | 2022-06-22 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Crossarm-Wood | Repair
LC | 123893618 | 003/036B | T3 EI SLY CREEK TAP 3/36B RPR GYWW | TABLEMTN | ETL.4221.POLE.NWOD | 2022-06-22 | 2022-06-22 |  | 2022-12-19 | 2022-12-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123893619 | 003/036C | T3 EI SLY CREEK TAP 03/036C RPR GYWW | TABLEMTN | ETL.4221.POLE.NWOD | 2022-06-22 | 2022-06-22 |  | 2022-12-19 | 2022-12-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123893832 | 003/005B | T3 DI DONNELLS-MI-WUK 3/5B RPR STRW | VICTOR | ETL.1400.POLE.WOOD | 2022-06-22 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45519357 | T3 DI DONNELLS-MI-WUK 3/5B RPR STRW | ICW
LC | 123893880 | 009/008 | T3 DI MAPLE CREEK-HOOPA 9/8 RPR JMPW | EUREKA | ETL.7490.INSL.NCER | 2022-06-22 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Jumper-Wood | Repair
LC | 123894453 | 000/006 | T3 DI GEYSERS #13 TAP 0/6 RPR INSS | LAKEVLLE | ETL.4781.INSL | 2022-06-22 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCM OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571496 | T3 DI GEYSERS #13 TAP 0/6 RPR INSS | ICS
LC | 123894457 | 000/006 | T3 DI GEYSERS #13 TAP 0/6 RPR SHIELD | LAKEVLLE | ETL.4781.TOWR | 2022-06-22 | 2022-05-23 |  | 2022-11-19 | 2022-11-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45571496 | T3 DI GEYSERS #13 TAP 0/6 RPR INSS | ICS
LC | 123895243 | 000/012 | T3 DI DEER CREEK-DRUM 000/012 RPL INSW | SACTO | ETL.6690.INSL.NCER | 2022-06-22 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31614561 | T3 DI DEER CREEK-DRUM 000/012 RPL INSW | 93I
LC | 123896267 | 026/112 | T3 MORRO BAY-MESA 26/112 BNT STEEL | PISMOBCH | ETL.5290.TOWR | 2022-06-22 | 2022-06-22 |  | 2022-12-19 | 2022-12-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW CREW OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123896526 | 011/092B | T3 DI MDDL FRK-GLD HLL 11/92B RPR GYWW | SACTO | ETL.5140.POLE.NWOD | 2022-06-22 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 123897218 | 000/012 | T3 EI VOLTA-SOUTH 0/12 RPR GYWW | TABLEMTN | ETL.8300.POLE.NWOD | 2022-06-22 | 2022-06-22 |  | 2022-12-19 | 2022-12-22 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45456489 | T3 EI VOLTA-SOUTH 0/12 RPR GYWW | ICW
LC | 123897253 | 001/012 | T3 DI BRUNSWICK #1 TAP 001/012 RMV VEG | SACTO | ETL.1422.TOWR | 2022-06-22 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR FRAB | Overgrown | Vegetation | Remove
LC | 123897524 | 009/043 | T3 DI TASSAJARA-NEWARK 009/043 RPL INSS | CONCORD | ETL.5920.INSL | 2022-06-22 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31625571 | DI TSJRA NWRK RPL INSS IN 7 TWRS | 93K
LC | 123897532 | 018/151B | T3 DI PRDISE-TBL MTN 18/151B RPL ANCW | TABLEMTN | ETL.4316.POLE.NWOD | 2022-06-22 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Replace | 31626011 | T2 DI PARADISE-TABLE MTN 012/101 REFRAME | 93E
LC | 123898617 | 000/001 | T3 EI ELDORADO-MISOUR FLT#1 0/1 COTTER | SACTO | ETL.1530.INSL | 2022-06-22 | 2022-06-22 |  | 2022-12-19 | 2022-12-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123899892 | 013/106B | T3 DI MDDL FRK-GLD HLL 13/106B RPR GYWS | SACTO | ETL.5140.POLE.NWOD | 2022-06-22 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Steel | Repair
LC | 123900939 | 005/040 | T3 DI MORAGA-SN LNDR #3 5/40 BNT STEEL | CONCORD | ETL.2790.TOWR | 2022-06-22 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123901230 | 009/044 | T3 DI TASSAJARA-NEWARK- 09/44 RPL INSS | CONCORD | ETL.5920.INSL | 2022-06-22 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCH OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Replace | 31625571 | DI TSJRA NWRK RPL INSS IN 7 TWRS | 93K
LC | 123901316 | 010/001 | T3 DI MNT RIO-FLTN-FLTN 10/1 RPR GYWW | LAKEVLLE | ETL.7630.POLE.NWOD | 2022-06-22 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45575612 | T3 DI MNT RIO-FLTN-FLTN 10/1 RPR GYWW | ICW
LC | 123901372 | 004/035 | T3 DI MORAGA-SN LNDR #3 4/35 RPR INSS | CONCORD | ETL.2790.INSL.NCER | 2022-06-22 | 2022-06-02 |  | 2022-11-29 | 2022-12-02 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45507988 | T3 DI MORAGA-SN LNDR #3 4/35 RPR INSS | ICS
LC | 123901391 | 004/043 | T3 DI DESABLA-CENTERVILLE 4/43R RPR STRW | TABLEMTN | ETL.6720.POLE.WDPS | 2022-06-22 | 2022-06-20 |  | 2022-12-17 | 2022-12-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123901396 | 009/006 | T3 DI MNDCINO-WLLITS 009/006 RPL HRDW | WILLITS | ETL.7540.POLE.NWOD | 2022-06-22 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW COMP OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45486205 | T3 DI MNDCINO-WLLITS 009/006 RPL HRDW | ICW
LC | 123901448 | 005/002 | T3 DI DONNELLS-MI-WUK 5/2 RPR GYWW | VICTOR | ETL.1400.POLE.STPS | 2022-06-22 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO AIR | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45519358 | T3 DI DONNELLS-MI-WUK 5/2 RPR GYWW | ICW
LC | 123901513 | 006/058 | T3 DI MONTA VISTA-BURNS 6/58 RMV STEP | MOSSLNDG | ETL.7590.POLE.NWOD | 2022-06-22 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45618812 | T3 DI MONTA VISTA-BURNS 6/58 RMV STEP | ICW
LC | 123902112 | 008/055 | T3 DI OLEUM-G #1 008/055 UNBURY | CONCORD | ETL.3150.TOWR | 2022-06-23 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair
LC | 123902199 | 085/597 | T3 DI BRDGVLL-CTTNWD 85/597 RPR STRW | EUREKA | ETL.1110.POLE.WDPS | 2022-06-23 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45640246 | T3 DI BRDGVLL-CTTNWD 85/597 RPR STRW | ICW
LC | 123903261 | 014/059 | T3 DI MNT VST-JFFRSN #1 14/59 RPL HRDT | METCALF | ETL.5220.TOWR | 2022-06-23 | 2022-06-20 |  | 2022-12-17 | 2022-12-20 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123904082 | 004/039 | T3 DI WOODLEAF-PALERMO 4/039 RPR SWTC | TABLEMTN | ETL.4220.SWIT | 2022-06-23 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 623 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | Out of Adjustment | Switch | Repair
LC | 123904241 | 005/051 | T3 EI CRAG VIEW-CASCADE 5/51 RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2022-06-23 | 2022-06-23 |  | 2022-12-20 | 2022-12-23 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45461091 | T3 EI CRAG VIEW-CASCADE 5/51 RPR GYWW | ICW
LC | 123905401 | 014/058 | T3 EI MONTA VSTA-JFFSN #2 14/58 COTR KEY | METCALF | ETL.5230.INSL.NCER | 2022-06-23 | 2022-06-23 |  | 2022-12-20 | 2022-12-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Repair | 45600356 | T3 EI MONTA VSTA-JFFSN #2 14/58 COTR KEY | ICS
LC | 123905735 | 002/039 | T3 WV CNTRVLL-TBL MTN 002/039 RPL POLE | TABLEMTN | ETL.6320.POLE.WOOD | 2022-06-23 | 2022-06-23 |  | 2022-12-20 | 2022-12-23 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW CREW OH RTNR FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31550824 | T3 WV CNTRVLL-TBL MTN 3/57 RPL CNDS | 93C
LC | 123905861 | 003/056 | T3 WV CNTRVLL-TBL MTN 003/056 RPL POLE | TABLEMTN | ETL.6320.POLE.NWOD | 2022-06-23 | 2022-06-23 |  | 2022-12-20 | 2022-12-23 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW CREW OH RTNR FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31550824 | T3 WV CNTRVLL-TBL MTN 3/57 RPL CNDS | 93C
LC | 123906260 | 016/079 | T3 DI MNT VST CYT SS 16/79 RPR INSS | MOSSLNDG | ETL.5091.INSL | 2022-06-23 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45618813 | T3 DI MNT VST CYT SS 16/79 RPR INSS | ICS
LC | 123906881 | 019/128 | T3 EI POE-RIO OSO 019/128 RPL HRDT | TABLEMTN | ETL.5540.TOWR | 2022-06-23 | 2022-06-23 |  | 2022-12-20 | 2022-12-23 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123907048 | ;001/019 | T3 DI SNTH LN-HLF MN BY ;1/19 RPR INSW | METCALF | ETL.7212.INSL.NCER | 2022-06-23 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCH OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45600710 | T3 DI SNTH LN-HLF MN BY ;1/19 RPR INSW | ICW
LC | 123907089 | 006/002 | T3 DI BRIDGEVILLE-GARBERVL 6/2 RPL HRDW | EUREKA | ETL.6220.POLE.WOOD | 2022-06-23 | 2022-05-24 |  | 2022-11-20 | 2022-11-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace | 45640247 | T3 DI BRIDGEVILLE-GARBERVL 6/2 RPL HRDW | ICW
LC | 123908113 | 018/123 | T3 EI POE-RIO OSO-RO OS 018/123 REFRAME | TABLEMTN | ETL.5540.POLE.STPS | 2022-06-23 | 2022-06-23 |  | 2022-12-20 | 2022-12-23 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace
LC | 123908115 | 017/122 | T3 EI POE-RIO OSO-RO OS 017/122 REFRAME | TABLEMTN | ETL.5540.POLE.STPS | 2022-06-23 | 2022-06-23 |  | 2022-12-20 | 2022-12-23 | Late | 637 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | No Good/Out of Stdrd | Crossarm-Wood | Replace
LC | 123908350 | 017/119 | T3 EI POE-RIO OSO -17/119 RMV VEG | TABLEMTN | ETL.5540.TOWR | 2022-06-23 | 2022-06-23 |  | 2022-12-20 | 2022-12-23 | Late | 564 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO FRAB | Overgrown | Vegetation | Remove
LC | 123908859 | 008/002 | T3 DI BRIDGEVILLE-GARBERVL 8/2 RPR POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-06-23 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45640248 | T3 DI BRIDGEVILLE-GARBERVL 8/2 RPR POLE | ICW
LC | 123909070 | 015/125 | T3 EI CRESTA-RIO OSO 015/125 RPL INSS | TABLEMTN | ETL.4590.INSL | 2022-06-23 | 2022-06-23 |  | 2022-12-20 | 2022-12-23 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615915 | T3 EI CRESTA-RIO OSO RPL INSS 10 STRTS | 93K
LC | 123909071 | 015/124 | T3 EI CRESTA-RIO OSO 015/124 RPL INSS | TABLEMTN | ETL.4590.INSL | 2022-06-23 | 2022-06-23 |  | 2022-12-20 | 2022-12-23 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | REGW INSP OH FMOB TR3 PRTO | No Good/Out of Stdrd | Insulator-Steel | Replace | 31615915 | T3 EI CRESTA-RIO OSO RPL INSS 10 STRTS | 93K
LC | 123909313 | 014/093B | T3 DI LNE TRE-CYTNO 14/93 RPR OPGW | CONCORD | ETL.6160.POLE.NWOD | 2022-06-23 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45502920 | T3 DI LNE TRE-CYTNO 14/93 RPR OPGW | ICS
LC | 123909345 | 004/000 | T3 DI BRIDGEVILLE-GARBERVL 4/0 RPR POLE | EUREKA | ETL.6220.POLE.WOOD | 2022-06-23 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123909535 | 009/217 | T3 DI DRUM-GRS VLY-WEIMAR 9/217 RPL HRDW | SACTO | ETL.6760.POLE.WOOD | 2022-06-23 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW ACCH OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123909716 | 020/165 | T3 DI CRESTA-RIO OSO 20/165 UNBURY | TABLEMTN | ETL.4590.TOWR | 2022-06-23 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45598964 | T3 DI CRESTA-RIO OSO 20/165 UNBURY | ICQ
LC | 123909723 | 002/062 | T3 DI DEER CREEK-DRM 2/62 INS HRDW | SACTO | ETL.6690.POLE.WOOD | 2022-06-23 | 2022-06-21 |  | 2022-12-18 | 2022-12-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | Missing | Hardware-Wood | Install
LC | 123909749 | 020/166 | T3 DI CRESTA-RIO OSO 20/166 UNBURY | TABLEMTN | ETL.4590.TOWR | 2022-06-23 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45598965 | T3 DI CRESTA-RIO OSO 20/166 UNBURY | ICQ
LC | 123909779 | 013/108 | T3 DI MONTA VISTA-BURNS 13/108 RPR INSW | MOSSLNDG | ETL.7590.INSL.NCER | 2022-06-23 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Repair | 45618814 | T3 DI MONTA VISTA-BURNS 13/108 RPR INSW | ICW
LC | 123909821 | 007/152 | T3 DI VOLTA-DESCHUTES 7/152 RPL INSW | TABLEMTN | ETL.8290.INSL | 2022-06-23 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617271 | T3 DI VLT DSCHTS 3/69 RPL INSW | 93I
LC | 123909891 | 014/001 | T3 DI DONNELLS-MI-WUK 14/001 RPR STRW | VICTOR | ETL.1400.POLE.STPS | 2022-06-23 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Structure-Wood | Repair | 45519359 | T3 DI DONNELLS-MI-WUK 14/001 RPR STRW | ICW
LC | 123909912 | 005/065 | T3 DI DESABLA-CENTERVILLE 05/65 RPL HRDD | TABLEMTN | ETL.6720.POLE.NWOD | 2022-06-23 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123909936 | 006/067 | T3 DI SNEATH LN-PACIFICA 6/67 RPR GYWW | METCALF | ETL.7575.POLE.WOOD | 2022-06-23 | 2022-06-04 |  | 2022-12-01 | 2022-12-04 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR FRAR NTDE | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45600719 | T3 DI SNEATH LN-PACIFICA 6/67 RPR GYWW | ICW
LC | 123910006 | 030/145 | T3 DI FULTON-PUEBLO 30/145 RPR CNDS | LAKEVLLE | ETL.1600.INSL.NCER | 2022-06-23 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OH TR3 PRTO AIR | No Good/Out of Stdrd | Conductor-Steel | Repair | 45571459 | T3 DI FULTON-PUEBLO 30/145 RPR CNDS | ICS
LC | 123910007 | 030/145 | T3 DI FULTON-PUEBLO 30/145 RPL HRDT | LAKEVLLE | ETL.1600.TOWR | 2022-06-23 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Tower | Replace
LC | 123910057 | 001/027A | T3 DI DRM-GRAS VLY-WMR 1/27A RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2022-06-23 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCM OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 123910095 | 001/007 | T3 DI GEYSERS #16 TAP 1/7 SWTC REPAI | LAKEVLLE | ETL.4760.TOWR | 2022-06-23 | 2022-06-13 |  | 2022-12-10 | 2022-12-13 | Late | 623 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW OTHR OH TR3 PRTO FRAB | Out of Adjustment | Switch | Repair | 45575544 | T3 DI GEYSERS #16 TAP 1/7 SWTC REPAI | ICE
LC | 123910096 | 008/056 | T3 DI OLEUM-G #1 008/056 BNT STEEL | CONCORD | ETL.3150.POLE.NWOD | 2022-06-23 | 2022-06-03 |  | 2022-11-30 | 2022-12-03 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123910201 | 004/039 | T3 DI WDLEAF-PLRMO 004/039 RPL INSS | TABLEMTN | ETL.4220.SWIT | 2022-06-23 | 2022-06-18 |  | 2022-12-15 | 2022-12-18 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31619355 | T3 DI WDLEAF-PLRMO 004/039 RPL INSS | 93K
LC | 123910316 | 043/315 | T3 DI CARIBOU-TBL MTN 43/315 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2022-06-23 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 532 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Replace | 31622345 | T2 DI CARIBOU-TBL MT RPL INSS 6 TWRS | 93K
LC | 123910365 | 006/152 | T3 DI DRUM-GRSS VLLY-WMR 6/152 RPL HRDW | SACTO | ETL.6760.POLE.NWOD | 2022-06-23 | 2022-05-25 |  | 2022-11-21 | 2022-11-25 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123911834 | ?003/003 | T3 DI SNEATH LN-HALF MB ?3/3 RPL INSW | METCALF | ETL.7212.INSL.CERA | 2022-06-24 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 508 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Wood | Replace | 31612284 | T3 DI SNTH LN-HALF MON BAY ?6/9 RPL INSW | 93I
LC | 123911965 | 001/001C | T3 DI BEARDSLEY TAP 1/1C RPR POLE | VICTOR | ETL.1401.POLE.WOOD | 2022-06-24 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45519360 | T3 DI BEARDSLEY TAP 1/1C RPR POLE | ICW
LC | 123911993 | 005/142 | T3 DI DEER CRK-DRUM 5/142 RPR ANCW | SACTO | ETL.6690.POLE.WOOD | 2022-06-24 | 2022-05-26 |  | 2022-11-22 | 2022-11-26 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Anchor-Wood | Repair
LC | 123912017 | 002/036 | T3 DI BURNS-LONE STAR #1 02/036 RPL SPLW | MOSSLNDG | ETL.6230.INSL.NCER | 2022-06-24 | 2022-06-01 |  | 2022-11-28 | 2022-12-01 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Splice-Wood | Replace | 45618816 | T3 DI BURNS-LONE STAR #1 02/036 RPL SPLW | ICW
LC | 123912090 | 007/151 | T3 DI VOLTA-DESCHUTES 71/151 RPL HRDW | TABLEMTN | ETL.8290.POLE.WOOD | 2022-06-24 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Hardware-Wood | Replace | 45458850 | T3 DI VOLTA-DESCHUTES 71/151 RPL HRDW | ICW
LC | 123912096 | 004/006 | T3 DI FULTON-CALISTOGA 4/6 RPR STRW | LAKEVLLE | ETL.6880.POLE.NWOD | 2022-06-24 | 2022-06-16 |  | 2022-12-13 | 2022-12-16 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45571431 | T3 DI FULTON-CALISTOGA 4/6 RPR STRW | ICW
LC | 123912196 | 013/358 | T3 DI COLGATE-ALLEGHANY 13/358 RPL HRDW | SACTO | ETL.6470.POLE.WOOD | 2022-06-24 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123912303 | 013/358 | T3 DI COLGATE-ALLEGHANY 013/358 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2022-06-24 | 2022-06-14 |  | 2022-12-11 | 2022-12-14 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB NTDE | No Good/Out of Stdrd | Structure-Wood | Replace | 31633458 | T3 DI COLGATE-ALLGHNY 011/293 RPL STRW | 70Y
LC | 123912304 | 001/023 | T3 DI MIDDLEFORK #1 1/23 RPL POLE | SACTO | ETL.8405.POLE.WOOD | 2022-06-24 | 2022-06-21 |  | 2022-12-18 | 2022-12-21 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31619027 | T3 DI MIDDLEFORK #1 0/5 RPL POLE | 70Y
LC | 123912309 | 012/050 | T3 DI PTTSBURG-SN RMN 12/050 RPR INSS | CONCORD | ETL.5490.INSL | 2022-06-24 | 2022-06-07 |  | 2022-12-04 | 2022-12-07 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH XMPT TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45513701 | T3 DI PTTSBURG-SN RMN 12/050 RPR INSS | ICS
LC | 123912326 | 003/080 | T3 DI DEER CREEK-DRUM 3/80 RPL HRDD | SACTO | ETL.6690.POLE.WOOD | 2022-06-24 | 2022-06-21 |  | 2022-12-18 | 2022-12-21 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123912328 | 000/006 | T3 DI BEARDSLEY TAP 0/6 RPR GYWW | VICTOR | ETL.1401.POLE.STPS | 2022-06-24 | 2022-06-06 |  | 2022-12-03 | 2022-12-06 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45519361 | T3 DI BEARDSLEY TAP 0/6 RPR GYWW | ICW
LC | 123912445 | 017/084 | T3 DI TESORO-SOBRANTE 17/84 RPR INSS | CONCORD | ETL.5670.INSL | 2022-06-24 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45513702 | T3 DI TESORO-SOBRANTE 17/84 RPR INSS | ICS
LC | 123912447 | 017/084 | T3 DI TIDEWTR-SOBRNATE 17/84 RPR INSS | CONCORD | ETL.5770.INSL | 2022-06-24 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45513703 | T3 DI TIDEWTR-SOBRNATE 17/84 RPR INSS | ICS
LC | 123912459 | 037/186 | T3 DI FULTON-PUEBLO 37/186 RPR INSS | LAKEVLLE | ETL.4392.INSL.NCER | 2022-06-24 | 2022-06-21 |  | 2022-12-18 | 2022-12-21 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR | No Good/Out of Stdrd | Insulator-Steel | Repair | 45571482 | T3 DI FULTON-PUEBLO 37/186 RPR INSS | ICS
LC | 123912518 | 008/048 | T3 DI CASTRO VLLY-NWRK 8/48 RPR OPGW | CONCORD | ETL.4450.TOWR | 2022-06-24 | 2022-06-22 |  | 2022-12-19 | 2022-12-22 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45502929 | T3 DI CASTRO VLLY-NWRK 8/48 RPR OPGW | ICS
LC | 123912532 | 008/048 | T3 DI CASTRO VLLY-NWRK 8/48 RPL HRDT | CONCORD | ETL.4450.TOWR | 2022-06-24 | 2022-06-22 |  | 2022-12-19 | 2022-12-22 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE ACCL OH TR3 PRTO AIR FRAB | Missing | Hardware-Tower | Install
LC | 123913029 | 002/018 | T3 DI MORAGA-CLRMNT #1 2/18 RPR STRT | CONCORD | ETL.2700.TOWR | 2022-06-24 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Tower | Repair
LC | 123913249 | 007/099 | T3 DI WEIMAR #1 007/099 RPL STRW | SACTO | ETL.7560.POLE.WOOD | 2022-06-24 | 2022-06-22 |  | 2022-12-19 | 2022-12-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617798 | T2 WEIMAR #1 1/19 RPL POLE | 70Y
LC | 123913287 | 010/005 | T3 DI MNTE RIO-FLTN (NF) 10/005 RPR STRW | LAKEVLLE | ETL.7630.POLE.WOOD | 2022-06-24 | 2022-06-17 |  | 2022-12-14 | 2022-12-17 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCL OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45575616 | T3 DI MNTE RIO-FLTN (NF) 10/005 RPR STRW | ICW
LC | 123914062 | 006/162 | T3 DI DRM-GRS VLY-WMR 6/162 RPL HRDD | SACTO | ETL.6760.POLE.WOOD | 2022-06-24 | 2022-06-20 |  | 2022-12-17 | 2022-12-20 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR | No Good/Out of Stdrd | Hardware-Wood | Replace
LC | 123914150 | 001/011 | T3 DI EL DRDO-MSR FLT #1 1/11 INS COTTER | SACTO | ETL.1530.INSL | 2022-06-24 | 2022-06-21 |  | 2022-12-18 | 2022-12-21 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW OTHR OH XMPT TR3 PRTO AIR NTDE | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 123914225 | 006/090 | T3 DI WEIMAR #1 6/90 RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2022-06-24 | 2022-06-22 |  | 2022-12-19 | 2022-12-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31629060 | T2 DI WEIMAR #1 004/059 RPL POLE | 70Y
LC | 123914356 | 006/096 | T3 DI WEIMAR #1 6/96 RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2022-06-24 | 2022-06-22 |  | 2022-12-19 | 2022-12-22 | Late | 372 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH XMPT TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Replace | 31617798 | T2 WEIMAR #1 1/19 RPL POLE | 70Y
LC | 123914396 | 010/007 | T3 DI MDCNO-WLTS-FT BRG 10/7C RPR STRW | WILLITS | ETL.7550.POLE.WDPS | 2022-06-24 | 2022-06-09 |  | 2022-12-06 | 2022-12-09 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Structure-Wood | Repair | 45640338 | T3 DI MDCNO-WLTS-FT BRG 10/7C RPR STRW | ICW
LC | 123914446 | 001/010 | T3 DI SAN RAMON-MORAGA 001/010 COTTER | CONCORD | ETL.5660.TOWR | 2022-06-24 | 2022-06-23 |  | 2022-12-20 | 2022-12-23 | Late | 628 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE ACCH OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45513706 | T3 DI SAN RAMON-MORAGA 001/010 COTTER | ICS
LC | 123914487 | 016/132 | T3 DI CRESTA-RIO OSO 16/132 UNBURY | TABLEMTN | ETL.4590.TOWR | 2022-06-24 | 2022-06-20 |  | 2022-12-17 | 2022-12-20 | Late | 543 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW FIRE OH TR3 PRTO AIR FRAB | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45597813 | T3 DI CRESTA-RIO OSO 16/132 UNBURY | ICQ
LC | 123914628 | 006/055 | T3 EI CRAG VIEW-CASCADE 6/55 INS DMPW | TABLEMTN | ETL.1350.INSL.CERA | 2022-06-24 | 2022-06-24 |  | 2022-12-21 | 2022-12-24 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | RELW INSP OH FMOB TR3 PRTO NTDE | Missing | Damper-Wood | Install | 45461092 | T3 EI CRAG VIEW-CASCADE 6/55 INS DMPW | ICW
LC | 123914695 | 000/011 | T3 DI DEER CREEK-DRUM 0/11 RPR GYWW | SACTO | ETL.6690.POLE.WOOD | 2022-06-24 | 2022-06-15 |  | 2022-12-12 | 2022-12-15 | Late | 630 | E - Schd Compl Yr 0 | Open | HFTD 3 | POHW FIRE OH TR3 PRTO AIR FRAB | No Good/Out of Stdrd | Guy Wire-Wood | Repair