## Sheet3
Count of Notification No | Column Labels
| Jan | Feb | Mar | Apr | May | Jun | Grand Total
Row Labels
Late | 16 | 239 | 375 | 677 | 1178 | 890 | 3375
On-time | 104 | 541 | 519 | 994 | 1084 | 993 | 4235
Grand Total | 120 | 780 | 894 | 1671 | 2262 | 1883 | 7610
| 86.67% | 69.36% | 58.05% | 59.49% | 47.92% | 52.73% | 55.65%

## Sheet1
Notification type | Notification No | Technical identification no. | Description | Main work center | Functional Location | Created On | Notification date | Reference date | Late | SOMs Due Date | Check | Required End | Work Type Code | Planner group | Status | Priority text | Notification Sytem Status | Notification User Status | Damage Code text | Object Code text | Activity Code text | Order | Order Number Description | MaintActivityType
LC | 126492317 | 012/107 | T3 COTTONWOOD-BENTON #2 12/107 GO95 | TABLEMTN | ETL.6650.POLE.STPS | 2023-07-01 | 2023-07-01 | 2023-12-27 | On-time | 2024-01-01 | 5 | 2024-01-01 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654673 | T3 COTTONWOOD-BENTON #2 12/107 GO95 | 93G
LC | 126492341 | 006/123 | T3 FRENCH MDWS-MDDL FRK 6/123 GO95 | SACTO | ETL.6870.POLE.WOOD | 2023-07-01 | 2023-07-01 | 2023-09-10 | On-time | 2024-01-01 | 113 | 2024-01-01 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654679 | T3 FRENCH MDWS-MDDL FRK 6/123 GO95 | 93G
LC | 126521173 | 011/005 | T3 DI LAURELES-OTTER 011/005 RMV VEG | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-07-07 | 2023-07-03 | 2023-09-08 | On-time | 2024-01-03 | 117 | 2024-01-03 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR3 | Overgrown | Vegetation | Remove
LC | 126521176 | 011/005 | T3 DI LAURELES-OTT 11/5 RPL HRDD | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-07-07 | 2023-07-03 | 2023-10-08 | On-time | 2024-01-03 | 87 | 2024-01-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45890562 | T3 DI LAURELES-OTT 11/5 RPL HRDD | ICW
LC | 126521260 | 011/005 | T3 DI LAURELES-OTTER 011/005 RPR GYWW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-07-07 | 2023-07-03 | 2023-10-08 | On-time | 2024-01-03 | 87 | 2024-01-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45890563 | T3 DI LAURELES-OTTER 011/005 RPR GYWW | ICW
LC | 126503410 | 000/007 | T3 FRKS OF THE BUTTE TAP 0/7 GO95 | TABLEMTN | ETL.6722.POLE.NWOD | 2023-07-05 | 2023-07-05 | 2023-10-23 | On-time | 2024-01-05 | 74 | 2024-01-05 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656327 | T3 FRKS OF THE BUTTE TAP 0/7 GO95 | 93G
LC | 126503844 | 008/125 | T3 MIDDLE FORK #1 08/125 GO95 | SACTO | ETL.8405.POLE.WOOD | 2023-07-05 | 2023-07-05 | 2023-08-27 | On-time | 2024-01-05 | 131 | 2024-01-05 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654787 | T3 MIDDLE FORK #1 08/125 GO95 | 93G
LC | 126503854 | 009/126 | T3 MIDDLE FORK #1 9/126 GO95 | SACTO | ETL.8405.POLE.WOOD | 2023-07-05 | 2023-07-05 | 2023-08-27 | On-time | 2024-01-05 | 131 | 2024-01-05 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654787 | T3 MIDDLE FORK #1 08/125 GO95 | 93G
LC | 126506893 | 003/096 | T3 DEER CREEK-DRUM 3/096 GO95 | SACTO | ETL.6690.POLE.WOOD | 2023-07-05 | 2023-07-05 | 2023-10-28 | On-time | 2024-01-05 | 69 | 2024-01-05 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656402 | T3 DEER CREEK-DRUM 2/062 GO95 | 93G
LC | 126506910 | 004/112 | T3 DEER CREEK-DRUM 4/112 GO95 | SACTO | ETL.6690.POLE.WOOD | 2023-07-05 | 2023-07-05 | 2023-10-30 | On-time | 2024-01-05 | 67 | 2024-01-05 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656402 | T3 DEER CREEK-DRUM 2/062 GO95 | 93G
LC | 126507039 | 003/095 | T3 DEER CREEK-DRUM 3/095 GO95 | SACTO | ETL.6690.POLE.WOOD | 2023-07-05 | 2023-07-05 | 2023-10-24 | On-time | 2024-01-05 | 73 | 2024-01-05 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656402 | T3 DEER CREEK-DRUM 2/062 GO95 | 93G
LC | 126507131 | 003/079 | T3 DEER CREEK-DRUM 3/079 GO95 | SACTO | ETL.6690.POLE.WOOD | 2023-07-05 | 2023-07-05 | 2023-10-30 | On-time | 2024-01-05 | 67 | 2024-01-05 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656402 | T3 DEER CREEK-DRUM 2/062 GO95 | 93G
LC | 126507155 | 002/071 | T3 DEER CREEK-DRUM 2/071 GO95 | SACTO | ETL.6690.POLE.WOOD | 2023-07-05 | 2023-07-05 | 2023-10-30 | On-time | 2024-01-05 | 67 | 2024-01-05 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656402 | T3 DEER CREEK-DRUM 2/062 GO95 | 93G
LC | 126507310 | 002/062 | T3 DEER CREEK-DRUM 2/62 COMPLETE | SACTO | ETL.6690.POLE.WOOD | 2023-07-05 | 2023-07-05 | 2023-10-26 | On-time | 2024-01-05 | 71 | 2024-01-05 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656402 | T3 DEER CREEK-DRUM 2/062 GO95 | 93G
LC | 126591418 | 024/010 | T3 DI MAPLE CREEK-HOOPA 24/10 RPL HRDW | EUREKA | ETL.7490.POLE.WOOD | 2023-07-14 | 2023-07-05 | 2023-09-15 | On-time | 2024-01-05 | 112 | 2024-01-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45900459 | T3 DI MAPLE CREEK-HOOPA 24/10 RPL HRDW | ICW
LC | 126510999 | 000/010 | T3 ORO FINO TAP 0/10 RPR INSW | TABLEMTN | ETL.6721.INSL | 2023-07-06 | 2023-07-06 | 2023-10-17 | On-time | 2024-01-06 | 81 | 2024-01-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45895473 | T3 ORO FINO TAP 000/010 RPR INSW | ICW
LC | 126525574 | 014/185 | T3 DI WEIMAR #1 014/185 RPR ANCW | SACTO | ETL.7560.POLE.STPS | 2023-07-07 | 2023-07-06 | 2023-08-14 | On-time | 2024-01-06 | 145 | 2024-01-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45895444 | T3 DI WEIMAR #1 014/185 RPR ANCW | ICW
LC | 126525576 | 014/185 | T3 DI WEIMAR #1 014/185 RPR ANCW | SACTO | ETL.7560.POLE.STPS | 2023-07-07 | 2023-07-06 | 2023-08-14 | On-time | 2024-01-06 | 145 | 2024-01-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45895446 | T3 DI WEIMAR #1 014/185 RPR ANCW | ICW
LC | 126536366 | 011/001 | T3 DI LAURELES-OTTER 11/01C RMV VEG | MOSSLNDG | ETL.7380.POLE.WDPS | 2023-07-09 | 2023-07-06 | 2023-09-19 | On-time | 2024-01-06 | 109 | 2024-01-06 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR3 | Overgrown | Vegetation | Remove
LC | 126536367 | 011/001 | T3 DI LAURELES-OTTER 11/01L RMV VEG | MOSSLNDG | ETL.7380.POLE.WDPS | 2023-07-09 | 2023-07-06 | 2023-09-20 | On-time | 2024-01-06 | 108 | 2024-01-06 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR3 | Overgrown | Vegetation | Remove
LC | 126536368 | 011/001 | T3 DI LAURELES-OTTER 11/01R RMV VEG | MOSSLNDG | ETL.7380.POLE.WDPS | 2023-07-09 | 2023-07-06 | 2023-09-20 | On-time | 2024-01-06 | 108 | 2024-01-06 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR3 | Overgrown | Vegetation | Remove
LC | 126536422 | 011/001 | T3 DI LAURELES-OTTER 11/01L RPL ANCW | MOSSLNDG | ETL.7380.POLE.WDPS | 2023-07-09 | 2023-07-06 | 2023-10-08 | On-time | 2024-01-06 | 90 | 2024-01-06 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31662095 | T3 DI LAURELES-OTTER 004/003L RPL ANCW | 93E
LC | 126523819 | 009/093 | T3 DRUM-HIGGINS 009/093L RPL POLE | SACTO | ETL.4393.POLE.WDPS | 2023-07-07 | 2023-07-07 | 2023-12-08 | On-time | 2024-01-07 | 30 | 2024-01-07 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31629580 | T3 EI DRUM-HIGGINS 10/94 RPL SWTCH | 93S
LC | 126523873 | 009/093 | T3 DRUM-HIGGINS 009/093C RPL POLE | SACTO | ETL.4393.POLE.WDPS | 2023-07-07 | 2023-07-07 | 2023-12-08 | On-time | 2024-01-07 | 30 | 2024-01-07 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31629580 | T3 EI DRUM-HIGGINS 10/94 RPL SWTCH | 93S
LC | 126523876 | 010/095B | T3 DRUM-HIGGINS 010/095B RPL POLE | SACTO | ETL.4393.POLE.WOOD | 2023-07-07 | 2023-07-07 | 2023-12-08 | On-time | 2024-01-07 | 30 | 2024-01-07 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31629580 | T3 EI DRUM-HIGGINS 10/94 RPL SWTCH | 93S
LC | 126523884 | 009/093 | T3 DRUM-HIGGINS 009/093R RPL POLE | SACTO | ETL.4393.POLE.WDPS | 2023-07-07 | 2023-07-07 | 2023-12-08 | On-time | 2024-01-07 | 30 | 2024-01-07 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31629580 | T3 EI DRUM-HIGGINS 10/94 RPL SWTCH | 93S
LC | 126523886 | 010/095A | T3 DRUM-HIGGINS 010/095A RPL POLE | SACTO | ETL.4393.POLE.WOOD | 2023-07-07 | 2023-07-07 | 2023-12-08 | On-time | 2024-01-07 | 30 | 2024-01-07 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31629580 | T3 EI DRUM-HIGGINS 10/94 RPL SWTCH | 93S
LC | 126523925 | 010/095C | T3 DRUM-HIGGINS 010/095C RPL POLE | SACTO | ETL.4393.POLE.WOOD | 2023-07-07 | 2023-07-07 | 2023-12-08 | On-time | 2024-01-07 | 30 | 2024-01-07 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31629580 | T3 EI DRUM-HIGGINS 10/94 RPL SWTCH | 93S
LC | 126524048 | A005/052A | T3 DRUM-HIGGINS A005/052A RPL POLE | SACTO | ETL.4393.POLE.WOOD | 2023-07-07 | 2023-07-07 | 2024-06-03 | Late | 2024-01-07 | -148 | 2024-01-07 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31637757 | T3 DUTCH FLAT #2 TAP 0/1 RPL SWTCH 127 & | 93S
LC | 126524082 | A005/052C | T3 DRUM-HIGGINS A005/052C RPL POLE | SACTO | ETL.4393.POLE.WOOD | 2023-07-07 | 2023-07-07 | 2024-06-03 | Late | 2024-01-07 | -148 | 2024-01-07 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31637757 | T3 DUTCH FLAT #2 TAP 0/1 RPL SWTCH 127 & | 93S
LC | 126524090 | A005/052B | T3 DRUM-HIGGINS A005/052B RPL POLE | SACTO | ETL.4393.POLE.WOOD | 2023-07-07 | 2023-07-07 | 2024-06-03 | Late | 2024-01-07 | -148 | 2024-01-07 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31637757 | T3 DUTCH FLAT #2 TAP 0/1 RPL SWTCH 127 & | 93S
LC | 126528851 | 019/001 | T3 DI MAPLE CREEK-HOOPA 19/1 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-07-08 | 2023-07-07 | 2023-09-21 | On-time | 2024-01-07 | 108 | 2024-01-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45890184 | T3 DI MPL CRK-HOOPA 019/001 RPR GYWW | ICW
LC | 126530308 | 019/010 | T3 DI MAPLE CREEK-HOOPA 019/010 RPR JMPW | EUREKA | ETL.7490.INSL.NCER | 2023-07-08 | 2023-07-07 |  | Late | 2024-01-07 |  | 2024-01-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45885332 | T3 DI MAPLE CREEK-HOOPA 019/010 RPR JMPW | ICW
LC | 126530390 | 019/010 | T3 DI MAPEL CREEK-HOOPA 19/10 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-07-08 | 2023-07-07 |  | Late | 2024-01-07 |  | 2024-01-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45885332 | T3 DI MAPLE CREEK-HOOPA 019/010 RPR JMPW | ICW
LC | 126585511 | 010/001 | T3 DI MAPLE CREEK-HOOPA-10/01 RPR DMPW | EUREKA | ETL.7490.INSL.NCER | 2023-07-14 | 2023-07-07 | 2023-09-14 | On-time | 2024-01-07 | 115 | 2024-01-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Damper-Wood | Replace | 45902120 | T3 DI MAPLE CREEK-HOOPA-10/01 RPR DMPW | ICW
LC | 126588661 | 019/008 | T3 DI MAPLE CREEK-HOOPA 19/008 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-07-14 | 2023-07-07 | 2023-09-20 | On-time | 2024-01-07 | 109 | 2024-01-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45902121 | T3 DI MAPLE CREEK-HOOPA 19/008 RPR GYWW | ICW
LC | 126589334 | 012/002 | T3 DI MAPLE CREEK-HOOPA 12/2 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-07-14 | 2023-07-07 | 2023-09-06 | On-time | 2024-01-07 | 123 | 2024-01-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45898056 | T3 DI MAPLE CREEK-HOOPA 12/2 RPR GYWW | ICW
LC | 126589339 | 012/002 | T3 DI MAPLE CREEK-HOOPA 12/2 COTTER | EUREKA | ETL.7490.INSL.NCER | 2023-07-14 | 2023-07-07 | 2023-09-06 | On-time | 2024-01-07 | 123 | 2024-01-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45898057 | T3 DI MAPLE CREEK-HOOPA 12/2 COTTER | ICW
LC | 126589605 | 013/001 | T3 DI MAPLE CREEK-HOOPA 13/01 RMV VEG | EUREKA | ETL.7490.POLE.NWOD | 2023-07-14 | 2023-07-07 | 2023-08-03 | On-time | 2024-01-07 | 157 | 2024-01-07 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR3 | Overgrown | Vegetation | Remove
LC | 126593045 | 013/002 | T3 DI MPL CRK-HOOPA 013/002 RPL HRDD | EUREKA | ETL.7490.POLE.NWOD | 2023-07-14 | 2023-07-07 | 2023-09-13 | On-time | 2024-01-07 | 116 | 2024-01-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45892219 | T3 DI MPL CRK-HOOPA 013/002 RPL HRDD | ICW
LC | 126593047 | 013/002 | T3 DI MPL CRK-HOOPA 013/002 RPR INSW | EUREKA | ETL.7490.INSL.NCER | 2023-07-14 | 2023-07-07 | 2023-09-13 | On-time | 2024-01-07 | 116 | 2024-01-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45892801 | T3 DI MPL CRK-HOOPA 013/002 RPR INSW | ICW
LC | 126587136 | 012/175 | T3 DI WEIMAR #1 012/175L RPR GYWW | SACTO | ETL.7560.POLE.STPS | 2023-07-14 | 2023-07-10 | 2023-08-15 | On-time | 2024-01-10 | 148 | 2024-01-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45895447 | T3 DI WEIMAR #1 012/175L RPR GYWW | ICW
LC | 126587137 | 012/175 | T3 DI WEIMAR #1 012/175C RPR GYWW | SACTO | ETL.7560.POLE.STPS | 2023-07-14 | 2023-07-10 | 2023-08-15 | On-time | 2024-01-10 | 148 | 2024-01-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45895448 | T3 DI WEIMAR #1 012/175C RPR GYWW | ICW
LC | 126587138 | 012/175 | T3 DI WEIMAR #1 012/175R RPR GYWW | SACTO | ETL.7560.POLE.STPS | 2023-07-14 | 2023-07-10 | 2023-08-15 | On-time | 2024-01-10 | 148 | 2024-01-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45895449 | T3 DI WEIMAR #1 012/175R RPR GYWW | ICW
LC | 126629381 | 013/182 | T3 DI WEIMAR #1 013/182 RPR ANCW | SACTO | ETL.7560.POLE.NWOD | 2023-07-19 | 2023-07-11 | 2023-07-30 | On-time | 2024-01-11 | 165 | 2024-01-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45903993 | T3 DI WEIMAR #1 013/182 RPR ANCW | ICW
LC | 126636318 | 013/179 | T3 DI WEIMAR #1 13/179 RPR GYWW | SACTO | ETL.7560.POLE.NWOD | 2023-07-20 | 2023-07-11 | 2023-08-15 | On-time | 2024-01-11 | 149 | 2024-01-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45903992 | T3 DI WEIMAR #1 13/179 RPR GYWW | ICW
LC | 126589101 | 012/013 | T3 DI MPL CRK-HOOPA 012/013 RPR INSW | EUREKA | ETL.7490.INSL.NCER | 2023-07-14 | 2023-07-12 |  | Late | 2024-01-12 |  | 2023-10-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45892820 | T3 DI MPL CRK-HOOPA 012/013 RPR INSW | ICW
LC | 126589426 | 013/007 | T3 DI LAURELES-OTTER 13/7 COTTER | MOSSLNDG | ETL.7380.INSL.NCER | 2023-07-14 | 2023-07-12 | 2023-08-08 | On-time | 2024-01-12 | 157 | 2023-10-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45892437 | T3 DI LAURELES-OTTER 13/7 COTTER | ICW
LC | 126590360 | 013/006 | T3 DI LAURELES-OTTER 13/6 RPR GYWW | MOSSLNDG | ETL.7380.POLE.NWOD | 2023-07-14 | 2023-07-12 | 2023-09-13 | On-time | 2024-01-12 | 121 | 2024-01-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45900102 | T3 DI LAURELES-OTTER 13/6 RPR GYWW | ICW
LC | 126593311 | 013/006 | T3 DI MAPLE CREEK-HOOPA 13/6 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-07-14 | 2023-07-12 | 2023-08-29 | On-time | 2024-01-12 | 136 | 2024-01-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45898058 | T3 DI MAPLE CREEK-HOOPA 13/6 RPR GYWW | ICW
LC | 126593312 | 013/006 | T3 DI MAPLE CREEK-HOOPA 13/6 RPR ANCW | EUREKA | ETL.7490.POLE.NWOD | 2023-07-14 | 2023-07-12 | 2023-09-23 | On-time | 2024-01-12 | 111 | 2024-01-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45898059 | T3 DI MAPLE CREEK-HOOPA 13/6 RPR ANCW | ICW
LC | 126628814 | 000/017 | T3 DI KILARC-CEDAR CREEK 00/17 RPR SPLW | TABLEMTN | ETL.7290.INSL.NCER | 2023-07-19 | 2023-07-12 | 2023-09-27 | On-time | 2024-01-12 | 107 | 2024-01-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Splice-Wood | Repair | 45904660 | T3 DI KILARC-CEDAR CREEK 00/17 RPR SPLW | ICW
LC | 126629145 | 018/005 | T3 DI MAPLE CREEK-HOOPA 18/05 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-07-19 | 2023-07-12 | 2023-10-04 | On-time | 2024-01-12 | 100 | 2024-01-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45902127 | T3 DI MAPLE CREEK-HOOPA 18/05 RPR GYWW | ICW
LC | 126629147 | 018/005 | T3 DI MAPLE CREEK-HOOPA 18/05 RPL HRDD | EUREKA | ETL.7490.POLE.NWOD | 2023-07-19 | 2023-07-12 | 2023-10-04 | On-time | 2024-01-12 | 100 | 2024-01-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45902128 | T3 DI MAPLE CREEK-HOOPA 18/05 RPL HRDD | ICW
LC | 126579368 | 028/110 | T3 WV PTTSBRG-SN MTEO 28/110 INS DMPS | CONCORD | ETL.5462.INSL.NCER | 2023-07-13 | 2023-07-13 | 2023-08-19 | On-time | 2024-01-13 | 147 | 2024-01-13 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Steel | Install | 45895396 | T3 WV PTTSBRG-SN MTEO 28/110 INS DMPS | ICS
LC | 126595253 | 014/186 | T3 DI WEIMAR #1 014/186 RPR GYWW | SACTO | ETL.7560.POLE.STPS | 2023-07-15 | 2023-07-13 | 2023-08-14 | On-time | 2024-01-13 | 152 | 2024-01-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45895450 | T3 DI WEIMAR #1 014/186 RPR GYWW | ICW
LC | 126595254 | 014/186 | T3 DI WEIMAR #1 014/186 RPR JMPR | SACTO | ETL.7560.INSL.NCER | 2023-07-15 | 2023-07-13 | 2023-08-15 | On-time | 2024-01-13 | 151 | 2024-01-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45895451 | T3 DI WEIMAR #1 014/186 RPR JMPR | ICW
LC | 126590344 | 001/041 | T3 EI BRNS LN START#2 001/041 RPR GYWW | MOSSLNDG | ETL.6240.POLE.WOOD | 2023-07-14 | 2023-07-14 | 2023-08-05 | On-time | 2024-01-14 | 162 | 2024-01-14 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45902342 | T3 EI BRNS LN START#2 001/041 RPR GYWW | ICW
LC | 126592776 | 004/079 | T3 FRNCH MDWS-MDDLE FRK 4/79 RPR INSW | SACTO | ETL.6870.INSL.NCER | 2023-07-14 | 2023-07-14 | 2023-09-14 | On-time | 2024-01-14 | 122 | 2024-01-14 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45895452 | T3 FRNCH MDWS-MDDLE FRK 4/79 RPR INSW | ICW
LC | 126593013 | 002/058 | T3 EI KILARC-CEDAR CREEK 2/058 RPR INSW | TABLEMTN | ETL.7290.INSL.NCER | 2023-07-14 | 2023-07-14 | 2023-09-26 | On-time | 2024-01-14 | 110 | 2024-01-14 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45904496 | T3 EI KILARC-CEDAR CREEK 2/058 RPR INSW | ICW
LC | 126605453 | 000/003 | T3 EI BEARDSLEY TAP 000/003R RPL STRW | VICTOR | ETL.1401.POLE.WDPS | 2023-07-17 | 2023-07-17 | 2023-10-16 | On-time | 2024-01-17 | 93 | 2024-01-17 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR3 | Rotten | Structure-Wood | Replace | 31663708 | T3 BEARDSLEY TAP 000/003R RPL STRW 3POLE | 70Y
LC | 126608103 | 003/075 | T3 EI DEER CREEK-DRUM 3/75 SHUNT | SACTO | ETL.6690.INSL.NCER | 2023-07-17 | 2023-07-17 | 2023-07-27 | On-time | 2024-01-17 | 174 | 2024-01-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Splice-Wood | Repair | 74049785 | DEER CREEK-DRUM SHUNT SPLICE RPL | 93C
LC | 126608673 | 005/128 | T3 EI DEER CREEK-DRUM 5/128 SHUNT | SACTO | ETL.6690.INSL.CERA | 2023-07-17 | 2023-07-17 | 2023-07-29 | On-time | 2024-01-17 | 172 | 2024-01-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Splice-Wood | Repair | 74049785 | DEER CREEK-DRUM SHUNT SPLICE RPL | 93C
LC | 126608713 | 005/135 | T3 EI DEER CREEK-DRUM 5/135 SHUNT | SACTO | ETL.6690.INSL.NCER | 2023-07-17 | 2023-07-17 | 2023-07-29 | On-time | 2024-01-17 | 172 | 2024-01-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Splice-Wood | Repair | 74049785 | DEER CREEK-DRUM SHUNT SPLICE RPL | 93C
LC | 126608749 | 005/140 | T3 EI DEER CREEK-DRUM 5/140 SHUNT | SACTO | ETL.6690.INSL.NCER | 2023-07-17 | 2023-07-17 | 2023-07-29 | On-time | 2024-01-17 | 172 | 2024-01-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Splice-Wood | Repair | 74049785 | DEER CREEK-DRUM SHUNT SPLICE RPL | 93C
LC | 126608821 | 005/142 | T3 EI DEER CREEK-DRUM 5/142 SHUNT | SACTO | ETL.6690.INSL.NCER | 2023-07-17 | 2023-07-17 | 2023-07-27 | On-time | 2024-01-17 | 174 | 2024-01-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Splice-Wood | Repair | 74049785 | DEER CREEK-DRUM SHUNT SPLICE RPL | 93C
LC | 126610732 | 014/392 | T3 WV COLGATE-ALLEGHANY 014/392 INS DMPW | SACTO | ETL.6470.INSL.NCER | 2023-07-17 | 2023-07-17 | 2023-10-26 | On-time | 2024-01-17 | 83 | 2024-01-17 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 45907747 | T3 WV COLGATE-ALLEGHANY 014/392 INS DMPW | ICW
LC | 126799669 | 000/003 | T3 EI BEARDSLEY TAP 000/003L RPL STRW | VICTOR | ETL.1401.POLE.WDPS | 2023-08-10 | 2023-07-17 | 2023-10-16 | On-time | 2024-01-17 | 93 | 2024-01-17 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR3 | Rotten | Structure-Wood | Replace | 31663708 | T3 BEARDSLEY TAP 000/003R RPL STRW 3POLE | 70Y
LC | 126799772 | 000/003 | T3 EI BEARDSLEY TAP 000/003C RPL STRW | VICTOR | ETL.1401.POLE.WDPS | 2023-08-10 | 2023-07-17 | 2023-10-16 | On-time | 2024-01-17 | 93 | 2024-01-17 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR3 | Rotten | Structure-Wood | Replace | 31663708 | T3 BEARDSLEY TAP 000/003R RPL STRW 3POLE | 70Y
LC | 126633303 | 003/017 | T3 DIABLO-GATES #1 3/17 RPR GYWT | PISMOBCH | ETL.5960.TOWR | 2023-07-20 | 2023-07-20 | 2024-01-18 | On-time | 2024-01-20 | 2 | 2024-01-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46031622 | T3 DIABLO-GATES #1 3/17 RPR GYWT | ICQ
LC | 126633952 | 004/022 | T3 DIABLO-GATES #1 4/22 RPR GYWT | PISMOBCH | ETL.5960.TOWR | 2023-07-20 | 2023-07-20 | 2024-01-18 | On-time | 2024-01-20 | 2 | 2024-01-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46031623 | T3 DIABLO-GATES #1 4/22 RPR GYWT | ICQ
LC | 126643791 | 031/229B | T3 EI MDL FRK-GLD HIL 31/229B RPR GYWW | SACTO | ETL.5140.POLE.NWOD | 2023-07-21 | 2023-07-21 | 2023-07-30 | On-time | 2024-01-21 | 175 | 2024-01-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45903989 | T3 EI MDL FRK-GLD HIL 31/229B RPR GYWW | ICW
LC | 126643912 | 031/229A | T3 EI MDL FRK-GLD HIL 031/229A RPR GYWW | SACTO | ETL.5140.POLE.NWOD | 2023-07-21 | 2023-07-21 | 2023-07-30 | On-time | 2024-01-21 | 175 | 2024-01-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45903988 | T3 EI MDL FRK-GLD HIL 031/229A RPR GYWW | ICW
LC | 126657262 | 001/023 | T3 DESABLE-CNTRVLLE 01/23 GO95 | TABLEMTN | ETL.6720.POLE.WOOD | 2023-07-24 | 2023-07-24 | 2023-10-24 | On-time | 2024-01-24 | 92 | 2024-01-24 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31657754 | T3 DESABLE-CNTRVLLE 01/23 GO95 | 93G
LC | 126661739 | 010/100 | T3 WV GREEN VALY-PL SWT 10/100L INS GYWW | MOSSLNDG | ETL.1730.POLE.WDPS | 2023-07-24 | 2023-07-24 | 2023-10-25 | On-time | 2024-01-24 | 91 | 2024-01-24 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Guy Wire-Wood | Install | 45982196 | T3 WV GREEN VALY-PL SWT 10/100L INS GYWW | ICW
LC | 126668498 | B008/001 | T3 EI FULTON-CALISTOGA B008/001 RPR GYWW | LAKEVLLE | ETL.6880.POLE.WOOD | 2023-07-25 | 2023-07-25 | 2023-08-21 | On-time | 2024-01-25 | 157 | 2024-01-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45917955 | T3 EI FULTON-CALISTOGA B008/001 RPR GYWW | ICW
LC | 126671512 | 000/014A | T3 WV DRUM-SPAULDING 000/014A INS DMPW | SACTO | ETL.6770.INSL.NCER | 2023-07-25 | 2023-07-25 | 2023-09-05 | On-time | 2024-01-25 | 142 | 2024-01-25 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 45926250 | T3 WV DRUM-SPAULDING 000/014A INS DMPW | ICW
LC | 126684655 | 019/007 | T3 WV FULTON-HOPLAND 019/007 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-07-27 | 2023-07-27 | 2023-09-27 | On-time | 2024-01-27 | 122 | 2024-01-27 | 372 | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31662472 | T3 WV FULTON-HOPLAND 019/007 RPL POLE | 70Y
LC | 126694234 | 009/132 | T3 WV MIDDLE FORK #1 009/132 INS DMPW | SACTO | ETL.8405.INSL.NCER | 2023-07-28 | 2023-07-28 | 2023-08-31 | On-time | 2024-01-28 | 150 | 2024-01-28 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 45926251 | T3 WV MIDDLE FORK #1 009/132 INS DMPW | ICW
LC | 126709198 | 005/143 | T3 EI DEER CREEK-DRUM 005/143 SHUNT | SACTO | ETL.6690.INSL.CERA | 2023-07-31 | 2023-07-31 | 2023-08-14 | On-time | 2024-01-31 | 170 | 2024-01-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Splice-Wood | Repair | 45926253 | T3 EI DEER CREEK-DRUM 005/143 SHUNT | ICW
LC | 126717797 | 010/001 | T3 EI MNDCNO-WLTS-FRT BRG 10/1L RPL POLE | WILLITS | ETL.7550.POLE.WDPS | 2023-08-01 | 2023-08-01 |  | Late | 2024-02-01 |  | 2024-02-01 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31662471 | T3 EI MNDCNO-WLTS-FRT BRG 10/1L RPL POLE | 70Y
LC | 126718967 | 003/017C | T3 GRIZZLY TAP 003/017C RPR HRDW | TABLEMTN | ETL.2395.POLE.WOOD | 2023-08-01 | 2023-08-01 | 2023-09-16 | On-time | 2024-02-01 | 138 | 2024-02-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45916258 | T3 GRIZZLY TAP 003/017C RPR HRDW | ICW
LC | 126719562 | 022/338 | T3 WV GOLD HILL #1 22/338 INS DMPW | SACTO | ETL.6950.INSL.NCER | 2023-08-01 | 2023-08-01 | 2023-08-30 | On-time | 2024-02-01 | 155 | 2024-02-01 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Damper-Wood | Replace | 45953421 | T3 WV GOLD HILL #1 22/338 INS DMPW | ICW
LC | 126763008 | 010/001 | T3 EI MNDCNO-WLTS-FRT BRG 10/1R RPL POLE | WILLITS | ETL.7550.POLE.WDPS | 2023-08-07 | 2023-08-01 |  | Late | 2024-02-01 |  | 2024-02-01 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31662471 | T3 EI MNDCNO-WLTS-FRT BRG 10/1L RPL POLE | 70Y
LC | 126723942 | 022/333 | T3 WV GOLD HILL #1 22/333 INS DMPW | SACTO | ETL.6950.INSL.NCER | 2023-08-02 | 2023-08-02 | 2023-08-30 | On-time | 2024-02-02 | 156 | 2024-02-02 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 45953689 | T3 WV GOLD HILL #1 22/333 INS DMPW | ICW
LC | 126735533 | 149 | T3 EI SPRING GAP TAP 1/6 RPR SWTC | VICTOR | ETL.1402.SWIT | 2023-08-03 | 2023-08-03 | 2023-11-08 | On-time | 2024-02-03 | 87 | 2024-02-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Switch-Wood | Repair | 45937535 | T3 EI SPRING GAP TAP 1/6 RPR SWTC | ICW
LC | 126748969 | 005/138 | T3 WV COLGATE-ALLEGHANY 5/138 INS DMPW | SACTO | ETL.6470.INSL.NCER | 2023-08-04 | 2023-08-04 | 2023-09-26 | On-time | 2024-02-04 | 131 | 2024-02-04 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 45953429 | T3 WV COLGATE-ALLEGHANY 5/138 INS DMPW | ICW
LC | 126782699 | 008/215 | T3 WV COLGATE-ALLEGHANY 008/215 INS DMPW | SACTO | ETL.6470.INSL.NCER | 2023-08-09 | 2023-08-09 | 2023-09-04 | On-time | 2024-02-09 | 158 | 2024-02-09 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 45940141 | T3 WV COLGATE-ALLEGHANY 008/215 INS DMPW | ICW
LC | 126802652 | 007/099 | T3 WV WEIMAR #1 007/099 INS DMPW | SACTO | ETL.7560.INSL.NCER | 2023-08-10 | 2023-08-10 | 2023-08-28 | On-time | 2024-02-10 | 166 | 2024-02-10 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 45928218 | T3 WV WEIMAR #1 007/099 INS DMPW | ICW
LC | 126820041 | 012/111B | T0 T3 WV GREN VLEY-PAUL SWT 12/111 INS D | MOSSLNDG | ETL.1730.INSL.NCER | 2023-08-14 | 2023-08-14 | 2023-12-12 | On-time | 2024-02-14 | 64 | 2024-02-14 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Damper-Wood | Replace | 46081687 | T0 T3 WV GREN VLEY-PAUL SWT 12/111 INS D | ICW
LC | 126826610 | B020/462 | T3 DRUM-GRSS VLLY-WEIMR B20/462 RPL PL | SACTO | ETL.6760.POLE.WOOD | 2023-08-15 | 2023-08-14 | 2023-12-05 | On-time | 2024-02-14 | 71 | 2024-02-14 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 35482862 | T3 DRUM-GRSS VLLY-WEIMR B20/462 RPL PL | 70Y
LC | 126837233 | 37 | T3 MONTA VISTA-BURNS 014/119 RPR SW | METCALF | ETL.7590.SWIT | 2023-08-16 | 2023-08-16 | 2023-12-01 | On-time | 2024-02-16 | 77 | 2024-02-16 | 630 | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Switch-Wood | Repair | 45960483 | T3 MONTA VISTA-BURNS 014/119 RPR SW | ICW
LC | 127257579 | :002/010 | T3 EAGLE RCK-FLTN-SLVRDO :2/10 RPL INSS | LAKEVLLE | ETL.4392.INSL.CERA | 2023-10-12 | 2023-10-12 |  | Late | 2024-01-12 |  | 2024-01-12 | 532 | TLN | CREW | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31677489 | EAGLE RCK-FLTN-SLVRDO :2/10 RPL INSS | 93K
LC | 125339563 | 015/127B | T2 CRAG VIEW-CASCADE 15/127B INS DAMW | TABLEMTN | ETL.1350.INSL.NCER | 2023-01-12 | 2023-01-12 | 2023-09-15 | On-time | 2024-01-12 | 119 | 2024-01-12 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 45698571 | T2 DELTA-COTTONWOOD 15/127 INS DAMW | ICW
LC | 126859916 | 002/012 | T3 RND MTN-TBL MTN #1 01/12 RPR INSS | TABLEMTN | ETL.6060.INSL | 2023-08-18 | 2023-08-18 | 2024-04-15 | Late | 2024-02-18 | -57 | 2024-02-18 | 628 | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45939932 | T3 RND MTN-TBL MTN #1 02/12 RPR INSS | ICS
LC | 126877275 | 005/038 | T3 MORAGA-SN LNDRO #1 05/38 RPL HRDT | CONCORD | ETL.2770.INSL | 2023-08-21 | 2023-08-18 | 2023-10-18 | On-time | 2024-02-18 | 123 | 2024-02-18 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45993307 | T3 MORAGA-SN LNDRO #1 05/38 RPL HRDT | ICQ
LC | 126876906 | 001/024 | T3 BURNS-LONE STAR #2 001/024 GO95 CLRNC | MOSSLNDG | ETL.6240.POLE.WOOD | 2023-08-21 | 2023-08-21 | 2023-12-13 | On-time | 2024-02-21 | 70 | 2024-02-21 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31664700 | T3 BURNS-LONE STAR #2 001/024 GO95 CLRNC | 93G
LC | 126884417 | 023/094 | T3 DIABLO-MIDWAY #3 23/94 RPR INSS | PISMOBCH | ETL.5980.INSL.NCER | 2023-08-22 | 2023-08-22 | 2023-11-28 | On-time | 2024-02-22 | 86 | 2024-02-22 | 628 | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45994607 | T3 DIABLO-MIDWAY #3 23/94 RPR INSS | ICS
LC | 126892017 | 000/001 | T3 DRUM-GRSS VLLY-WMR 0/1 CNDW RPR | SACTO | ETL.6760.INSL.NCER | 2023-08-23 | 2023-08-23 | 2023-09-13 | On-time | 2024-02-23 | 163 | 2024-02-23 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46215809 | T3 DRUM-GRSS VLLY-WMR 0/1 CNDW RPR | ICW
LC | 126898326 | 009/127 | T3 MIDDLE FORK #1 9/127 GO95 | SACTO | ETL.8405.POLE.WOOD | 2023-08-23 | 2023-08-23 | 2023-08-26 | On-time | 2024-02-23 | 181 | 2024-02-23 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654787 | T3 MIDDLE FORK #1 08/125 GO95 | 93G
LC | 126898334 | 002/063 | T3 DEER CREEK-DRUM 2/63 GO95 | SACTO | ETL.6690.POLE.WOOD | 2023-08-23 | 2023-08-23 | 2023-10-24 | On-time | 2024-02-23 | 122 | 2024-02-23 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656402 | T3 DEER CREEK-DRUM 2/062 GO95 | 93G
LC | 126898335 | 003/080 | T3 DEER CREEK-DRUM 3/80 GO95 | SACTO | ETL.6690.POLE.WOOD | 2023-08-23 | 2023-08-23 | 2023-10-31 | On-time | 2024-02-23 | 115 | 2024-02-23 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656402 | T3 DEER CREEK-DRUM 2/062 GO95 | 93G
LC | 126853139 | 006/096 | T3 MIDDLEFORK #1 006/096 INS ANCW | SACTO | ETL.8405.POLE.NWOD | 2023-08-17 | 2023-08-17 | 2023-08-27 | On-time | 2024-02-17 | 174 | 2023-11-17 | 637 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Anchor-Wood | Install | 31663776 | T3 MIDDLEFORK #1 006/096 INS ANCW | 93E
LC | 128213174 | 006/038 | T3 SBRNT-GRIZLY-CLARMNT #2 6/38 RPR STRT | CONCORD | ETL.3750.TOWR | 2024-02-26 | 2023-08-17 |  | Late | 2024-02-17 |  | 2023-11-17 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Tower | Repair | 46203952 | T3 SBRNT-GRIZLY-CLARMNT #2 6/38 RPR STRT | ICQ
LC | 126935734 | 013/358 | T3 WV COLGATE-ALLEGHANY 13/358 IND DMPW | SACTO | ETL.6470.INSL.NCER | 2023-08-28 | 2023-08-28 | 2023-10-02 | On-time | 2024-02-28 | 149 | 2024-02-28 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 45993684 | T3 WV COLGATE-ALLEGHANY 13/358 IND DMPW | ICW
LC | 126981331 | 008/207 | T3 DRUM-GRSS VALLY-WEIMAR 8/207 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2023-09-05 | 2023-08-28 |  | Late | 2024-02-28 |  | 2024-02-28 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 35489675 | T3 DRUM-GRSS VALLY-WEIMAR 8/207 RPL POLE | 70Y
LC | 126953454 | A002/014 | T3 WV SBRTE-GRZLY-CLMT #1 A2/14 INS DAMS | CONCORD | ETL.3740.INSL.NCER | 2023-08-30 | 2023-08-30 | 2024-04-09 | Late | 2024-02-29 | -40 | 2024-02-29 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Steel | Install | 46000795 | T3 WV SBRTE-GRZLY-CLMT #1 A2/14 INS DAMS | ICS
LC | 127144254 | A002/014 | T3 WV SBRTE-GRZLY-CLMT #2 A2/14 INS DAMS | CONCORD | ETL.3750.INSL.NCER | 2023-09-27 | 2023-08-30 |  | Late | 2024-02-29 |  | 2024-02-29 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Missing | Damper-Steel | Install | 46000794 | T3 WV SBRTE-GRZLY-CLMT #1 A2/14 INS DAMS | ICS
LC | 126959018 | 003/051 | T3 EI KESWICK-TRINITY 003/051 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-08-31 | 2023-08-31 | 2023-12-16 | On-time | 2024-02-29 | 75 | 2024-02-29 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487718 | T3 EI KESWICK-TRINITY 003/051 RPL POLE | 70Y
LC | 126960893 | T-106 | T3 WV MIDWAY-SANTA MARIA (12KV) T-106 | PISMOBCH | ETL.9240.INSL.NCER | 2023-08-31 | 2023-08-31 | 2023-11-30 | On-time | 2024-02-29 | 91 | 2024-02-29 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Steel | Install | 46045668 | T3 WV MIDWAY-SANTA MARIA (12KV) T-106 | ICS
LC | 126992081 | 013/001 | T3 MAPLE CREEK-HOOPA 013/001 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-09-06 | 2023-09-06 | 2023-09-13 | On-time | 2024-03-06 | 175 | 2024-03-06 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45977436 | T3 MAPLE CREEK-HOOPA 013/001 RPR GYWW | ICW
LC | 127000186 | 004/049 | T3 DRUM-HIGGINS 4/049 GO95 | SACTO | ETL.4393.TOWR | 2023-09-07 | 2023-09-07 | 2023-12-18 | On-time | 2024-03-07 | 80 | 2024-03-07 | 400 | TLQ | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Tower | To Be Corrected | 31671235 | T3 DRUM-HIGGINS 4/049 GO95 | 93T
LC | 127003899 | 000/002 | T3 DESABLA-CENTERVILLE 000/002 GO95 | TABLEMTN | ETL.6720.POLE.NWOD | 2023-09-08 | 2023-09-08 | 2023-10-23 | On-time | 2024-03-08 | 137 | 2024-03-08 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656327 | T3 FRKS OF THE BUTTE TAP 0/7 GO95 | 93G
LC | 127004471 | 009/002 | T3 DONNELLS-MI-WUK 009/002 RMV VEG | VICTOR | ETL.1400.POLE.WDPS | 2023-09-08 | 2023-09-08 | 2023-10-09 | On-time | 2024-03-08 | 151 | 2024-03-08 | 374 | TLR | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Road | Replace | 31669480 | T3 DONNELLS-MI-WUK 009/002 RMV VEG | 71Y
LC | 127014234 | 005/002 | T3 WV LAURELES-OTTER 005/002R RPL ANCW | MOSSLNDG | ETL.7380.POLE.WDPS | 2023-09-09 | 2023-09-09 | 2024-03-04 | On-time | 2024-03-09 | 5 | 2024-03-09 | 637T | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35506185 | T3 WV LAURELES-OTTER 005/002R RPL ANCW | 93E
LC | 127988188 | 005/002 | T3 WV LAURELES-OTTER 005/002C RPL ANCW | MOSSLNDG | ETL.7380.POLE.WDPS | 2023-12-29 | 2023-09-09 | 2024-03-04 | On-time | 2024-03-09 | 5 | 2024-03-09 | 637 | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35506185 | T3 WV LAURELES-OTTER 005/002R RPL ANCW | 93E
LC | 127988189 | 005/002 | T3 WV LAURELES-OTTER 005/002L RPL ANCW | MOSSLNDG | ETL.7380.POLE.WDPS | 2023-12-29 | 2023-09-09 | 2024-03-04 | On-time | 2024-03-09 | 5 | 2024-03-09 | 637 | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35506185 | T3 WV LAURELES-OTTER 005/002R RPL ANCW | 93E
LC | 127031392 | ?002/007 | T3 WV SNTH LNE-HLF MN BY ?2/7 INS DAMW | METCALF | ETL.7212.INSL.NCER | 2023-09-11 | 2023-09-11 | 2023-11-30 | On-time | 2024-03-11 | 102 | 2024-03-11 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 45995121 | T3 WV SNTH LNE-HLF MN BY ?2/7 INS DAMW | ICW
LC | 127033936 | 003/083 | T3 DEER CREEK-DRUM 003/083 INS DMPW | SACTO | ETL.6690.INSL.NCER | 2023-09-11 | 2023-09-11 |  | Late | 2024-03-11 |  | 2024-03-11 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Missing | Damper-Wood | Install | 46003454 | T3 DEER CREEK-DRUM 003/083 INS DMPW | ICW
LC | 127039006 | 002/056 | T3 COLGATE-CHALLENGE 2/056 INS DMPW | SACTO | ETL.6480.INSL.NCER | 2023-09-12 | 2023-09-12 | 2024-04-10 | Late | 2024-03-12 | -29 | 2024-03-12 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 46011725 | T3 COLGATE-CHALLENGE 2/056 INS DMPW | ICW
LC | 127041851 | 011/005 | T3 DI MAPLE CRK-HOOPA 11/5 RPL POLE | EUREKA | ETL.7490.POLE.WOOD | 2023-09-12 | 2023-09-12 |  | Late | 2024-03-12 |  | 2024-03-12 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491108 | T3 DI MAPLE CRK-HOOPA 11/5 RPL POLE | 70Y
LC | 127047256 | T098 | T3 MIDWAY-SANTA MARIA T098 RPL INSS | PISMOBCH | ETL.9240.TOWR | 2023-09-13 | 2023-09-13 | 2023-12-02 | On-time | 2024-03-13 | 102 | 2024-03-13 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671260 | T3 MIDWAY-SANTA MARIA T098 RPL INSS | 93K
LC | 127050645 | 047/269 | T3 EI TMBLOR-SN LIS OBISPO 47/269 COTTER | PISMOBCH | ETL.3960.INSL.NCER | 2023-09-13 | 2023-09-13 | 2024-01-16 | On-time | 2024-03-13 | 57 | 2024-03-13 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46073694 | T3 EI TMBLOR-SN LIS OBISPO 47/269 COTTER | ICS
LC | 127061156 | 005/047 | T3 DI SLY CREEK TAP 05/47L RPL POLE | TABLEMTN | ETL.4221.POLE.STPS | 2023-09-15 | 2023-09-15 |  | Late | 2024-03-15 |  | 2024-03-15 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31618005 | T3 DI SLY CREEK TAP 5/48L RPL POLE | 70Y
LC | 127061159 | 005/047 | T3 DI SLY CREEK TAP 05/47R RPL POLE | TABLEMTN | ETL.4221.POLE.STPS | 2023-09-15 | 2023-09-15 |  | Late | 2024-03-15 |  | 2024-03-15 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31618005 | T3 DI SLY CREEK TAP 5/48L RPL POLE | 70Y
LC | 127061223 | 005/048 | T3 DI SLY CREEK TAP 05/48R RPL POLE | TABLEMTN | ETL.4221.POLE.STPS | 2023-09-15 | 2023-09-15 |  | Late | 2024-03-15 |  | 2024-03-15 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31618005 | T3 DI SLY CREEK TAP 5/48L RPL POLE | 70Y
LC | 127065385 | C016/006 | T3 WV FULTON-CALISTOGA C16/6 RPR INSW | LAKEVLLE | ETL.6880.INSL.NCER | 2023-09-15 | 2023-09-15 | 2023-10-11 | On-time | 2024-03-15 | 156 | 2024-03-15 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46008923 | T3 WV FULTON-CALISTOGA C16/6 RPR INSW | ICW
LC | 125524686 | 009/001 | T2 EI PHILO JCT-ELK 09/01 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-02-17 | 2023-02-17 | 2024-05-03 | Late | 2024-02-17 | -76 | 2024-02-17 | 372T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35481043 | T2 EI PHILO JCT-ELK 09/01 RPL POLE | 70Y
LC | 125520998 | 016/331 | T2 EI CLGTE-PLRMO 16/331 RMV ENCROACH | TABLEMTN | ETL.6500.POLE.NWOD | 2023-02-17 | 2023-02-17 | 2023-07-18 | On-time | 2024-02-17 | 214 | 2024-02-17 | 931 | TLS | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Encroachment | Right of Way | Remove | 45847719 | T2 EI CLGTE-PLRMO 16/331 RMV ENCROACH | CHR
LC | 125521608 | 010/176 | T2 EI TEJON-LEBEC 010/176 RPL POLE | MIDWAY | ETL.9250.POLE.WOOD | 2023-02-17 | 2023-02-17 | 2023-10-15 | On-time | 2024-02-17 | 125 | 2024-02-17 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663426 | T2 EI TEJON-LEBEC 010/176 RPL POLE | 70Y
LC | 125532207 | 024/289A | T2 DRUM-SUMMIT #2 24/289A RPL ANCW | SACTO | ETL.1450.POLE.NWOD | 2023-02-21 | 2023-02-17 | 2023-08-25 | On-time | 2024-02-17 | 176 | 2024-02-17 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31639227 | T2 DRUM-SUMMIT #2 24/289A RPL ANCW | 92T
LC | 125566711 | 004/008 | T2 DI LAYTONVILLE-WILLITS 4/8 RPR GYWW | WILLITS | ETL.8360.POLE.NWOD | 2023-02-28 | 2023-02-17 | 2023-09-08 | On-time | 2024-02-17 | 162 | 2024-02-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45927612 | T2 DI LAYTONVILLE-WILLITS 4/8 RPR GYWW | ICW
LC | 125569902 | 000/001 | T2 DI UNION CHEMICAL 0/1 RPR GYWW | CONCORD | ETL.6351.POLE.NWOD | 2023-02-28 | 2023-02-17 | 2023-10-23 | On-time | 2024-02-17 | 117 | 2024-02-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45926514 | T2 DI UNION CHEMICAL 0/1 RPR GYWW | ICW
LC | 125570483 | 002/000 | T2 DI MNDCNO HRTLY 2/000 RMV VEG | WILLITS | ETL.7510.POLE.WOOD | 2023-02-28 | 2023-02-17 | 2023-08-22 | On-time | 2024-02-17 | 179 | 2024-02-17 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 127089809 | 003/035 | T3 ATASCADERO-CAYUCOS 3/35 RPR GYWW | PISMOBCH | ETL.8480.POLE.NWOD | 2023-09-19 | 2023-09-19 | 2024-03-18 | On-time | 2024-03-19 | 1 | 2024-03-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091331 | T3 ATASCADERO-CAYUCOS 3/35 RPR GYWW | ICW
LC | 127092703 | 003/034 | T3 ATASCADERO-CAYUCOS 3/34 RPR GYWW | PISMOBCH | ETL.8480.POLE.NWOD | 2023-09-20 | 2023-09-19 | 2024-03-18 | On-time | 2024-03-19 | 1 | 2024-03-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091332 | T3 ATASCADERO-CAYUCOS 3/34 RPR GYWW | ICW
LC | 127098858 | 027/131 | T3 EXCHEQUER-INDIAN FLAT_027/131 GO95 | FRESNO | ETL.8650.POLE.NWOD | 2023-09-21 | 2023-09-21 | 2023-12-14 | On-time | 2024-03-21 | 98 | 2024-03-21 | 400T | TLQ | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Tower | To Be Corrected | 35511998 | T3 EXCHEQUER-INDIAN FLAT_027/131 GO95 | 93T
LC | 127103549 | 013/195 | T3 WV GOLD HILL #1 13/195 INS DMPW | SACTO | ETL.6950.INSL.CERA | 2023-09-21 | 2023-09-21 | 2024-04-06 | Late | 2024-03-21 | -16 | 2024-03-21 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 46079382 | T3 WV GOLD HILL #1 13/195 INS DMPW | ICW
LC | 127108033 | ?001/009 | T3 WV SNEATH LNE-HLF MN BY ?1/9 RPL DMPW | METCALF | ETL.7212.INSL.NCER | 2023-09-21 | 2023-09-21 | 2024-05-16 | Late | 2024-03-21 | -56 | 2024-03-21 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Damper-Wood | Replace | 46025359 | T3 WV SNEATH LNE-HLF MN BY ?1/9 RPL DMPW | ICW
LC | 127111479 | 004/037 | T3 MORAGA-SAN LEANDRO #1 4/37 RPR CRST | CONCORD | ETL.2770.TOWR | 2023-09-22 | 2023-09-21 |  | Late | 2024-03-21 |  | 2024-03-21 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Crossarm-Tower | Repair | 46063640 | T3 MORAGA-SAN LEANDRO #1 4/37 RPR XARM | ICQ
LC | 127114595 | 005/146A | T3 DRUM-SPAULDING 5/146A RPR SPLW | SACTO | ETL.6770.INSL.CERA | 2023-09-22 | 2023-09-22 | 2024-01-09 | On-time | 2024-03-22 | 73 | 2024-03-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Splice-Wood | Repair | 46171496 | T3 DRUM-SPAULDING 5/146A RPR SPLW | ICW
LC | 127127317 | 003/007 | T3 WV GRIZZLY TAP 3/7 RPR GYWW | TABLEMTN | ETL.2395.POLE.WDPS | 2023-09-25 | 2023-09-25 | 2023-10-15 | On-time | 2024-03-25 | 162 | 2024-03-25 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011653 | T3 WV GRIZZLY TAP 3/7 RPR GYWW | ICW
LC | 127127345 | 004/001A | T3 WV GRIZZLY TAP 4/1A RPR CNDW | TABLEMTN | ETL.2395.INSL.CERA | 2023-09-25 | 2023-09-25 | 2023-10-25 | On-time | 2024-03-25 | 152 | 2024-03-25 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46011651 | T3 WV GRIZZLY TAP 4/1A RPR CNDW | ICW
LC | 127127356 | 003/015 | T3 WV GRIZZLY TAP 3/15 RPR CRSW | TABLEMTN | ETL.2395.POLE.WDPS | 2023-09-25 | 2023-09-25 | 2023-09-16 | On-time | 2024-03-25 | 191 | 2024-03-25 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46011652 | T3 WV GRIZZLY TAP 3/15 RPR CRSW | ICW
LC | 127130962 | 008/005B | T3 WV DONNELLS-MI-WUK 8/5B RPL STRW | VICTOR | ETL.1400.POLE.NWOD | 2023-09-25 | 2023-09-25 |  | Late | 2024-03-25 |  | 2024-03-25 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 35561400 | T3 WV DONNELLS-MI-WUK 8/5A RPL STRW | 70Y
LC | 127550474 | 008/005A | T3 WV DONNELLS-MI-WUK 8/5A RPL STRW | VICTOR | ETL.1400.POLE.NWOD | 2023-12-07 | 2023-09-25 |  | Late | 2024-03-25 |  | 2024-03-25 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 35561400 | T3 WV DONNELLS-MI-WUK 8/5A RPL STRW | 70Y
LC | 127550572 | 008/005C | T3 WV DONNELLS-MI-WUK 8/5C RPL STRW | VICTOR | ETL.1400.POLE.NWOD | 2023-12-07 | 2023-09-25 |  | Late | 2024-03-25 |  | 2024-03-25 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 35561400 | T3 WV DONNELLS-MI-WUK 8/5A RPL STRW | 70Y
LC | 127136867 | 25 | T3 CLOVER CREEK TAP A5/128 RPR SWTC | TABLEMTN | ETL.7291.SWIT | 2023-09-26 | 2023-09-26 | 2024-03-09 | On-time | 2024-03-26 | 17 | 2024-03-26 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Switch-Wood | Repair | 46011776 | T3 CLOVER CREEK TAP A5/128 RPR SWTC | ICW
LC | 127145840 | 012/113 | T3 GRN VALLEY-PAUL SWT 12/113 RPR INSLW | MOSSLNDG | ETL.1730.INSL.CERA | 2023-09-27 | 2023-09-27 | 2023-11-07 | On-time | 2024-03-27 | 141 | 2024-03-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999027 | T3 GRN VALLEY-PAUL SWT 12/113 RPR INSLW | ICW
LC | 127145878 | 012/113 | T3 GRN VLLY-PAUL SWT 12/113 REPLUMB | MOSSLNDG | ETL.1730.POLE.WOOD | 2023-09-27 | 2023-09-27 | 2023-11-07 | On-time | 2024-03-27 | 141 | 2024-03-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999028 | T3 GRN VLLY-PAUL SWT 12/113 REPLUMB | ICW
LC | 127152793 | 002/020 | T3 WV ATASCADERO-CAYUCOS 2/20 RPL DMPW | PISMOBCH | ETL.8480.INSL.NCER | 2023-09-28 | 2023-09-28 | 2024-03-13 | On-time | 2024-03-28 | 15 | 2024-03-28 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Damper-Wood | Replace | 46091334 | T3 WV ATASCADERO-CAYUCOS 2/20 RPL DMPW | ICW
LC | 127183368 | A002/011 | T3 SBRNTE-GRZLY-CLRMNT #1 A2/11 RPL INSS | CONCORD | ETL.3740.INSL.CERA | 2023-10-03 | 2023-09-28 | 2024-04-09 | Late | 2024-03-28 | -12 | 2024-03-28 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671954 | T3 SBRNTE-GRZLY-CLRMNT #1 A2/11 RPL INSS | 93K
LC | 127182442 | 004/106 | T3 DI DRUM GRSS-VLLY-WMR 4/106 RPR SHLW | SACTO | ETL.6760.POLE.WOOD | 2023-10-02 | 2023-10-02 | 2023-10-04 | On-time | 2024-01-02 | 90 | 2024-01-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45998115 | T3 DI DRUM GRSS-VLLY-WMR 4/106 RPR SHLW | ICW
LC | 127184843 | 117 | T3 WV DRUM-HIGGINS 004/049 RPR SWTC | SACTO | ETL.4393.SWIT | 2023-10-03 | 2023-10-03 | 2023-12-18 | On-time | 2024-04-03 | 107 | 2024-04-03 | 623 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Out of Adjustment | Switch | Repair | 46046405 | T3 WV DRUM-HIGGINS 004/049 RPR SWTC | ICE
LC | 127192831 | 035/258 | T3 MIDDLE FORK-GOLD HILL 35/258 RPR STRT | SACTO | ETL.5140.TOWR | 2023-10-04 | 2023-10-04 | 2023-10-04 | On-time | 2024-04-04 | 183 | 2024-04-04 | 628 | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Steel | Repair | 46001112 | T3 MIDDLE FORK-GOLD HILL 35/258 RPR STRT | ICS
LC | 127194438 | 006/078 | T3 GREEN VALLEY-CAMP EVERS 6/78L GO95 | MOSSLNDG | ETL.1710.POLE.WDPS | 2023-10-04 | 2023-10-04 | 2024-03-30 | On-time | 2024-04-04 | 5 | 2024-04-04 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35492213 | T3 GREEN VALLEY-CAMP EVERS 6/78L GO95 | 93G
LC | 127194494 | 006/078 | T3 GREEN VALLEY-CAMP EVERS 006/078R GO95 | MOSSLNDG | ETL.1710.POLE.WDPS | 2023-10-04 | 2023-10-04 | 2024-03-30 | On-time | 2024-04-04 | 5 | 2024-04-04 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35492213 | T3 GREEN VALLEY-CAMP EVERS 6/78L GO95 | 93G
LC | 127194496 | 006/078 | T3 GREEN VALLEY-CAMP EVERS 6/078C GO95 | MOSSLNDG | ETL.1710.POLE.WDPS | 2023-10-04 | 2023-10-04 | 2024-03-30 | On-time | 2024-04-04 | 5 | 2024-04-04 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35492213 | T3 GREEN VALLEY-CAMP EVERS 6/78L GO95 | 93G
LC | 127195121 | B022/495 | T3 DRM-GRSS VLLY-WMR B22/495 RPL INS | SACTO | ETL.6760.INSL.NCER | 2023-10-04 | 2023-10-04 | 2024-04-04 | Late | 2024-04-04 | 0 | 2024-04-04 | 508T | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35546285 | T3 DRM-GRSS VLLY-WMR B22/495 RPL INS | 93I
LC | 127202073 | 021/010 | T3 WV MAPLE CREEK-HOOPA 21/010 REFRAME | EUREKA | ETL.7490.POLE.NWOD | 2023-10-05 | 2023-10-05 |  | Late | 2024-04-05 |  | 2024-04-05 | 637T | TLN | CREW | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35507616 | T3 MAPLE CREEK-HOOPA 21/010 REFRAME | 93E
LC | 127204686 | ?007/003 | T3 WV SNTH LNE-HLF MN BY ?7/3 RPL DMPW | METCALF | ETL.7212.INSL.CERA | 2023-10-05 | 2023-10-05 | 2024-02-01 | On-time | 2024-04-05 | 64 | 2024-04-05 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Damper-Wood | Replace | 46041251 | T3 WV SNTH LNE-HLF MN BY ?7/3 RPL DMPW | ICW
LC | 127205722 | 017/139 | T3 WV CRESTA-RIO OSO 017/139 RPR CNDS | TABLEMTN | ETL.4590.INSL.NCER | 2023-10-05 | 2023-10-05 | 2024-02-22 | On-time | 2024-04-05 | 43 | 2024-04-05 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46045948 | T3 WV CRESTA-RIO OSO 017/139 RPR CNDS | ICS
LC | 127206337 | 021/094 | T3 WV MSS LNDNG-METCALF 21/94 BNT STEEL | MOSSLNDG | ETL.6050.TOWR | 2023-10-05 | 2023-10-05 | 2024-03-06 | On-time | 2024-04-05 | 30 | 2024-04-05 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Tower | Repair | 46073318 | T3 WV MSS LNDNG-METCALF 21/94 BNT STEEL | ICQ
LC | 127206788 | 027/004 | T3 WV FULTON-HOPLAND 27/4 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-10-05 | 2023-10-05 |  | Late | 2024-04-05 |  | 2024-04-05 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521330 | T3 WV FULTON-HOPLAND 27/4 RPL POLE | 70Y
LC | 127206986 | 001/016 | T3 WV SLY CREEK TAP 001/016L RPL POLE | TABLEMTN | ETL.4221.POLE.WDPS | 2023-10-05 | 2023-10-05 |  | Late | 2024-04-05 |  | 2024-04-05 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Open | TR3 | Rotten | Structure-Wood | Replace | 35525811 | T3 WV SLY CREEK TAP 001/016L RPL POLE | 70Y
LC | 127390353 | 001/016 | T3 WV SLY CREEK TAP 001/016R RPL POLE | TABLEMTN | ETL.4221.POLE.WDPS | 2023-11-01 | 2023-10-05 |  | Late | 2024-04-05 |  | 2024-04-05 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Open | TR3 | Rotten | Structure-Wood | Replace | 35525811 | T3 WV SLY CREEK TAP 001/016L RPL POLE | 70Y
LC | 127212924 | 017/193 | T3 IGNACIO-BOLINAS #2 17/193 GO95 | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-10-06 | 2023-10-06 |  | Late | 2024-04-06 |  | 2024-04-06 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35492509 | T3 IGNACIO-BOLINAS #2 16/192 GO95 CLRNCE | 93G
LC | 127226099 | 011/001 | T3 LAURELES-OTTER 11/01C COMPLETE | MOSSLNDG | ETL.7380.POLE.WDPS | 2023-10-09 | 2023-10-09 | 2023-10-10 | On-time | 2024-04-09 | 182 | 2024-04-09 | 637 | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31662095 | T3 DI LAURELES-OTTER 004/003L RPL ANCW | 93E
LC | 127226101 | 011/001 | T3 LAURELES-OTTER 11/01LR COMPLETE | MOSSLNDG | ETL.7380.POLE.WDPS | 2023-10-09 | 2023-10-09 | 2023-10-10 | On-time | 2024-04-09 | 182 | 2024-04-09 | 637 | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31662095 | T3 DI LAURELES-OTTER 004/003L RPL ANCW | 93E
LC | 127228950 | 000/007 | T3 DRUM-GRASS VALLEY-WEIMAR 0/7 INS DMPW | SACTO | ETL.6760.INSL.NCER | 2023-10-09 | 2023-10-09 | 2024-02-26 | On-time | 2024-04-09 | 43 | 2024-04-09 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 46032463 | T3 DRUM-GRASS VALLEY-WEIMAR 0/7 INS DMPW | ICW
LC | 127253215 | 003/008A | T3 WV GRIZZLY TAP 3/8A INS DAMW | TABLEMTN | ETL.2395.INSL.CERA | 2023-10-11 | 2023-10-11 |  | Late | 2024-04-11 |  | 2024-04-11 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Missing | Damper-Wood | Install | 46046150 | T3 WV GRIZZLY TAP 3/8A INS DAMW | ICW
LC | 127253302 | 003/008B | T3 WV GRIZZLY TAP 3/8B INS DAMW | TABLEMTN | ETL.2395.INSL.CERA | 2023-10-11 | 2023-10-11 |  | Late | 2024-04-11 |  | 2024-04-11 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Missing | Damper-Wood | Install | 46046148 | T3 WV GRIZZLY TAP 3/8B INS DAMW | ICW
LC | 127253538 | 003/008C | T3 WV GRIZZLY TAP 3/008C INS DAMW | TABLEMTN | ETL.2395.INSL.CERA | 2023-10-11 | 2023-10-11 |  | Late | 2024-04-11 |  | 2024-04-11 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Missing | Damper-Wood | Install | 46046147 | T3 WV GRIZZLY TAP 3/008C INS DAMW | ICW
LC | 125577967 | 005/000 | T2 DI LYTNVIL WILLTS 5/000 RPR GYWW | WILLITS | ETL.8360.POLE.NWOD | 2023-03-02 | 2023-02-17 | 2023-09-11 | On-time | 2024-02-17 | 159 | 2024-02-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45927611 | T2 DI LYTNVIL WILLTS 5/000 RPR GYWW | ICW
LC | 127258262 | 025/006 | T3 MAPLE CREEK-HOOPA 25/006 RPL SPLW | EUREKA | ETL.7490.INSL.NCER | 2023-10-12 | 2023-10-12 |  | Late | 2024-04-12 |  | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Splice-Wood | Replace | 46049047 | T3 MAPLE CREEK-HOOPA 25/006 RPL SPLW | ICW
LC | 127258421 | 025/006 | T3 MAPLE CREEK-HOOPA 25/006 INS RPTW | EUREKA | ETL.7490.POLE.NWOD | 2023-10-12 | 2023-10-12 |  | Late | 2024-04-12 |  | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR3 | Missing | Animal Guard-Wood | Install | 46049048 | T3 MAPLE CREEK-HOOPA 25/006 INS RPTW | ICW
LC | 127262904 | 019/006 | T3 MAPLE CREEK-HOOPA 19/006 RPL CRSW | EUREKA | ETL.7490.POLE.NWOD | 2023-10-12 | 2023-10-12 |  | Late | 2024-04-12 |  | 2024-04-12 | 637T | TLN | CREW | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35531276 | T3 MAPLE CREEK-HOOPA 19/006 RPL CRSW | 93E
LC | 127262996 | 010/109 | T3 IGNACIO-BOLINAS #1 10/109 RPL STRW | LAKEVLLE | ETL.7140.POLE.WOOD | 2023-10-12 | 2023-10-12 |  | Late | 2024-04-12 |  | 2024-04-12 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518697 | T3 IGNACIO-BOLINAS #1 10/109 RPL STRW | 70Y
LC | 127274722 | 003/003 | T3 WV TP(CTY OF SNTA CLR) 3/3 INS DMPW | TABLEMTN | ETL.2395.INSL.NCER | 2023-10-14 | 2023-10-14 |  | Late | 2024-04-14 |  | 2024-04-14 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Damper-Wood | Replace | 46076619 | T3 WV TP(CTY OF SNTA CLR) 3/3 INS DMPW | ICW
LC | 127275549 | 006/122 | T3 WV FRNCH MDWS-MDL FRK 6/122 RPL POLE | SACTO | ETL.6870.POLE.WOOD | 2023-10-14 | 2023-10-14 | 2024-04-22 | Late | 2024-04-14 | -8 | 2024-04-14 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 35524095 | T3 WV FRNCH MDWS-MDL FRK 6/122 RPL POLE | 70Y
LC | 127279928 | 003/002 | T3 WV GRIZZLY TAP 003/002 INST DAMPER | TABLEMTN | ETL.2395.INSL.NCER | 2023-10-16 | 2023-10-16 |  | Late | 2024-04-16 |  | 2024-04-16 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Missing | Damper-Wood | Install | 46054034 | T3 WV GRIZZLY TAP 003/002 INST DAMPER | ICW
LC | 127293603 | 013/107A | T3 WV MDDL FRK-GLD HLL 13/107A RPR ANCHT | SACTO | ETL.5140.POLE.NWOD | 2023-10-17 | 2023-10-17 | 2024-04-11 | On-time | 2024-04-17 | 6 | 2024-04-17 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Anchor-Tower | Repair | 46095412 | T3 WV MDDL FRK-GLD HLL 13/107A RPR ANCHT | ICQ
LC | 127294182 | 001/028 | T3 WV IGNACIO-BOLINAS #1 1/28 RPL POLE | LAKEVLLE | ETL.7140.POLE.WOOD | 2023-10-17 | 2023-10-17 |  | Late | 2024-04-17 |  | 2024-04-17 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518696 | T3 WV IGNACIO-BOLINAS #1 1/28 RPL POLE | 70Y
LC | 127308568 | 022/254 | T3 IGNACIO-BLNS #2 22/254 RPL STRW | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-10-19 | 2023-10-17 |  | Late | 2024-04-17 |  | 2024-04-17 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31617012 | T3 EI IGNACIO-BOLINAS #2 24/276 RPL STRW | 70Y
LC | 128188553 | 002/019 | T3 MORAGA-OAKLAND #3 002/019 RPR STRT | CONCORD | ETL.2740.TOWR | 2024-02-16 | 2023-10-19 |  | Late | 2024-04-19 |  | 2024-04-19 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Tower | Repair | 46209826 | T3 MORAGA-OAKLAND #3 002/019 RPR STRT | ICQ
LC | 128188621 | 002/017 | T3 MORAGA-OAKLAND #3 2/17 RPL HRDT | CONCORD | ETL.2740.TOWR | 2024-02-16 | 2023-10-19 | 2024-06-12 | Late | 2024-04-19 | -54 | 2024-04-19 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46203846 | T3 MORAGA-OAKLAND #3 002/017 RPL HRDT | ICQ
LC | 127313243 | 003/005 | T3 WV GRIZZLY TAP 003/005 RPR JMPW | TABLEMTN | ETL.2395.INSL.CERA | 2023-10-20 | 2023-10-20 |  | Late | 2024-04-20 |  | 2024-04-20 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46054035 | T3 WV GRIZZLY TAP 003/005 RPR JMPW | ICW
LC | 127317760 | 021/167 | T3 WV PARADISE-TBLE MTN 21/167C RPL ANCW | TABLEMTN | ETL.4316.POLE.STPS | 2023-10-20 | 2023-10-20 |  | Late | 2024-04-20 |  | 2024-04-20 | 637T | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35519985 | T3 WV PARADISE-TBLE MTN 21/167C RPL ANCW | 93E
LC | 127323245 | 009/128 | T3NT WV MIDDLE FORK #1 09/128 INS DMPW | SACTO | ETL.8405.INSL.NCER | 2023-10-22 | 2023-10-22 | 2024-05-21 | Late | 2024-04-22 | -29 | 2024-04-22 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 46053870 | T3NT WV MIDDLE FORK #1 09/128 INS DMPW | ICW
LC | 127323748 | 007/001 | T3 WV LAURELES-OTTER 007/001 INS DAMW | MOSSLNDG | ETL.7380.INSL.NCER | 2023-10-22 | 2023-10-22 |  | Late | 2024-04-22 |  | 2024-04-22 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Missing | Damper-Wood | Install | 46081689 | T3 WV LAURELES-OTTER 007/001 INS DAMW | ICW
LC | 127346517 | 000/002 | T3NT WV FRNCH MDWS-MDLE FRK 0/2 RPL GYWW | SACTO | ETL.6870.POLE.NWOD | 2023-10-25 | 2023-10-25 | 2024-04-18 | On-time | 2024-04-25 | 7 | 2024-04-25 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 46097340 | T3NT WV FRNCH MDWS-MDLE FRK 0/2 RPL GYWW | ICW
LC | 127474948 | 010/004 | T3 POTTER VALEY-WILITS 10/4 RPR GYWW | WILLITS | ETL.7820.POLE.WOOD | 2023-11-13 | 2023-10-25 | 2024-03-28 | On-time | 2024-04-25 | 28 | 2024-04-25 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46210323 | T3 POTTER VALEY-WILITS 10/4 RPR GYWW | ICW
LC | 127478464 | 010/002 | T3 POTTER VALEY-WILITS 10/2 RPR STRW | WILLITS | ETL.7820.POLE.WOOD | 2023-11-14 | 2023-10-26 | 2024-04-02 | On-time | 2024-04-26 | 24 | 2024-04-26 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Repair | 46210324 | T3 POTTER VALEY-WILITS 10/2 RPR STRW | ICW
LC | 127404900 | 003/073 | T3 KILARC-CEDAR CREEK 3/073 GO95 | TABLEMTN | ETL.7290.POLE.WOOD | 2023-11-02 | 2023-11-02 | 2024-05-08 | Late | 2024-05-02 | -6 | 2024-05-02 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35514315 | T3 KILARC-CEDAR CREEK 3/073 GO95 | 93G
LC | 127404912 | 041/236 | T3 TEMBLOR-SAN LUIS OBISPO 41/236 GO95 | PISMOBCH | ETL.3960.TOWR | 2023-11-02 | 2023-11-02 |  | Late | 2024-05-02 |  | 2024-05-02 | 400T | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Clearance | GO95 Clear Infract-Tower | To Be Corrected | 35526084 | T3 TEMBLOR-SAN LUIS OBISPO 41/236 GO95 | 93T
LC | 127420884 | 008/086 | T3 WV IGNACIO-BOLINAS #1 8/86 CNCL | LAKEVLLE | ETL.7140.INSL.NCER | 2023-11-06 | 2023-11-06 |  | Late | 2024-05-06 |  | 2024-05-06 | 508 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617009 | T2 DI IGNACIO-BOLINAS #1 7/071 RPL INSW | 93I
LC | 127430872 | 015/227 | WV T3 GOLD HILL #1 015/227 INS DMPW | SACTO | ETL.6950.INSL.NCER | 2023-11-07 | 2023-11-07 | 2024-04-04 | On-time | 2024-05-07 | 33 | 2024-05-07 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 46127319 | WV T3 GOLD HILL #1 015/227 INS DMPW | ICW
LC | 127432611 | 027/000 | WV T3 FULTON-HOPLAND 27/000 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-11-07 | 2023-11-07 |  | Late | 2024-05-07 |  | 2024-05-07 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 35523382 | T3 FULTON-HOPLAND 27/000 RPL STRW | 70Y
LC | 127435393 | 002/017 | T3 EI RND MTN-TBL MTN #2 2/17 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2023-11-08 | 2023-11-08 | 2024-04-03 | On-time | 2024-05-08 | 35 | 2024-05-08 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Tower | Repair | 46062542 | T3 EI RND MTN-TBL MTN #2 2/17 RPR STRT | ICQ
LC | 127553299 | 013/143 | T3 IGNACIO-BOLINAS #1 13/143 RPL POLE | LAKEVLLE | ETL.7140.POLE.WOOD | 2023-12-08 | 2023-11-08 |  | Late | 2024-05-08 |  | 2024-05-08 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Rotten | Structure-Wood | Replace | 35525868 | T3 IGNACIO-BOLINAS #1 13/143 RPL POLE | 70Y
LC | 127446887 | 117 | T3 DRUM-HIGGINS 04/049 RPL INSW | SACTO | ETL.4393.SWIT | 2023-11-09 | 2023-11-09 | 2023-12-18 | On-time | 2024-05-09 | 143 | 2024-05-09 | 532 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671235 | T3 DRUM-HIGGINS 4/049 GO95 | 93T
LC | 127447154 | 026/102 | T3 PITTSBURG-SAN MATEO RPR FOND | CONCORD | ETL.5463.TOWR | 2023-11-09 | 2023-11-09 |  | Late | 2024-05-09 |  | 2024-05-09 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46057915 | T3 PITTSBURG-SAN MATEO RPR FOND | ICQ
LC | 127466957 | 014/392 | T3 WV COLGATE-ALLGHNY 14/392 RPR INSLW | SACTO | ETL.6470.INSL.NCER | 2023-11-11 | 2023-11-11 |  | Late | 2024-05-11 |  | 2024-05-11 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46102142 | T3 WV COLGATE-ALLGHNY 14/392 RPR INSLW | ICW
LC | 127473568 | 018/127A | T3 EI MTCLF-GRN VALLEY 18/127A COMPLETE | MOSSLNDG | ETL.2540.POLE.NWOD | 2023-11-13 | 2023-11-13 | 2024-04-09 | On-time | 2024-05-13 | 34 | 2024-05-13 | 637T | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35521498 | T3 EI MTCLF-GRN VALLEY 18/127B RPL ANCW | 93E
LC | 127473644 | 018/127B | T3 EI MTCLF-GRN VALLEY 18/127B COMPLETE | MOSSLNDG | ETL.2540.POLE.NWOD | 2023-11-13 | 2023-11-13 | 2024-04-09 | On-time | 2024-05-13 | 34 | 2024-05-13 | 637T | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35521498 | T3 EI MTCLF-GRN VALLEY 18/127B RPL ANCW | 93E
LC | 127478644 | 002/048 | T3 CENTERVILLE-TABLE MTN 2/048 INS DMPW | TABLEMTN | ETL.6320.INSL.NCER | 2023-11-14 | 2023-11-14 | 2024-06-10 | Late | 2024-05-14 | -27 | 2024-05-14 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 46076174 | T3 CENTERVILLE-TABLE MTN 2/048 INS DMPW | ICW
LC | 127488200 | 000/003 | T3 DIABLO-MIDWAY #2 000/003 RPR GYWT | PISMOBCH | ETL.5970.TOWR | 2023-11-16 | 2023-11-16 | 2024-05-22 | Late | 2024-05-16 | -6 | 2024-05-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46175354 | T3 DIABLO-MIDWAY #2 000/003 RPR GYWT | ICQ
LC | 127488212 | 002/016 | T3 DIABLO-GATES #1 2/16 RPR GYWT | PISMOBCH | ETL.5960.TOWR | 2023-11-16 | 2023-11-16 | 2024-05-07 | On-time | 2024-05-16 | 9 | 2024-05-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46095416 | T3 DIABLO-GATES #1 002/016 RPR GYWT | ICQ
LC | 127488340 | 011/042 | T3 DIABLO-MIDWAY #2 011/042 COMPLETED | PISMOBCH | ETL.5970.TOWR | 2023-11-16 | 2023-11-16 | 2024-02-26 | On-time | 2024-05-16 | 80 | 2024-05-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46095417 | T3 DIABLO-MIDWAY #2 011/042 RPR GYWT | ICQ
LC | 127491523 | 010/065 | T3 WV OLEUM-G #2 10/065 BENT STEEL | CONCORD | ETL.3160.INSL.CERA | 2023-11-16 | 2023-11-16 |  | Late | 2024-05-16 |  | 2024-05-16 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Tower | Repair | 46088121 | T3 WV OLEUM-G #1 10/065 BNT STEEL | ICQ
LC | 127505216 | 001/021 | T3 WV CENTERVILLE-TBLE MTN 1/21 INS DMPW | TABLEMTN | ETL.6320.INSL.NCER | 2023-11-21 | 2023-11-21 | 2024-06-10 | Late | 2024-05-21 | -20 | 2024-05-21 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 46129630 | T3 WV CENTERVILLE-TBLE MTN 1/21 INS DMPW | ICW
LC | 127506708 | 015/231 | T3 GOLD HILL #1 015/231 RPL STRW | SACTO | ETL.6950.POLE.WOOD | 2023-11-21 | 2023-11-21 | 2024-04-06 | On-time | 2024-05-21 | 45 | 2024-05-21 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 35513715 | T3 GOLD HILL #1 015/231 RPL STRW | 70Y
LC | 127512977 | B008/003 | T3 FULTON-CALISTOGA B8/3 RPR INSW | LAKEVLLE | ETL.6880.INSL.NCER | 2023-11-27 | 2023-11-27 | 2024-04-07 | On-time | 2024-05-27 | 50 | 2024-05-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079559 | T3 FULTON-CALISTOGA B8/3 RPR INSW | ICW
LC | 127516972 | 013/002 | T3 EI DONNELLS-MI-WUK 013/002 RPL INSW | VICTOR | ETL.1400.INSL.CERA | 2023-11-27 | 2023-11-27 |  | Late | 2024-05-27 |  | 2024-05-27 | 508 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31546391 | T3 DI DONNELLS-MI-WUK 013/002A RPL INSW | 93I
LC | 127539568 | 014/062 | T3 GEYSER #9-LAKEVILLE 14/062 RPR INSS | LAKEVLLE | ETL.4780.INSL.NCER | 2023-12-04 | 2023-12-04 |  | Late | 2024-06-04 |  | 2024-06-04 | 628 | TLN | CREW | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46102401 | T3 GEYSER #9-LAKEVILLE 14/062 RPR INSS | ICS
LC | 127542656 | 000/001 | T3 WV RINCON #2 TAP 0/1 RPR FENCE | LAKEVLLE | ETL.1601.POLE.NWOD | 2023-12-05 | 2023-12-05 |  | Late | 2024-06-05 |  | 2024-06-05 | 931 | TLS | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Encroachment | Right of Way | Remove
LC | 127567216 | 006/014 | T3 BRDGEVLLE-GRBRVLLE 6/14 RPR SPLW | EUREKA | ETL.6220.INSL.NCER | 2023-12-11 | 2023-12-11 |  | Late | 2024-06-11 |  | 2024-06-11 | 630 | TLN | CREW | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Splice-Wood | Repair | 46203441 | T3 BRDGEVLLE-GRBRVLLE 6/14 RPR SPLW | ICW
LC | 127568470 | 007/001 | T3 WISHON-SAN JOAQUIN #3 007/001 GO95 | FRESNO | ETL.9340.POLE.NWOD | 2023-12-12 | 2023-12-12 | 2024-04-25 | On-time | 2024-06-12 | 48 | 2024-06-12 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35518934 | T3 WISHON-SAN JOAQUIN #3 007/001 GO95 | 93G
LC | 127569146 | 006/044 | T3 MRAGA-SN LEANDRO #1 6/44 GO95 CLEAR | CONCORD | ETL.2770.INSL.NCER | 2023-12-12 | 2023-12-12 |  | Late | 2024-06-12 |  | 2024-06-12 | 400T | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Clearance | GO95 Clear Infract-Tower | To Be Corrected | 35523644 | T2 MORAGA-SAN LEANDRO #1 GO95 IN 4 STRS | 93T
LC | 128011783 | 006/044 | T3 MRAGA-SN LEANDRO #2 6/44 GO95 CLEAR | CONCORD | ETL.2780.INSL.NCER | 2024-01-08 | 2023-12-12 |  | Late | 2024-06-12 |  | 2024-06-12 | 400 | TLQ | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Clearance | GO95 Clear Infract-Tower | To Be Corrected | 35523645 | T2 MORAGA-SAN LEANDRO #2 8/57 GO95 CLR | 93T
LC | 127577618 | 011/110 | T3 GRN VLLY-CMP EVRS 11/110R RPR GYWW | MOSSLNDG | ETL.1710.POLE.STPS | 2023-12-13 | 2023-12-13 | 2024-04-26 | On-time | 2024-06-13 | 48 | 2024-06-13 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46125098 | T3 GRN VLLY-CMP EVRS 11/110R RPR GYWW | ICW
LC | 127579017 | 022/091 | T3 WV DIABLO-MIDWAY #3 22/091 RPR INSS | PISMOBCH | ETL.5980.INSL.NCER | 2023-12-14 | 2023-12-14 | 2024-05-22 | On-time | 2024-06-14 | 23 | 2024-06-14 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46156782 | T3 WV DIABLO-MIDWAY #3 22/091 RPL INSS | ICS
LC | 127579798 | 026/007 | T3 WV FULTON-HOPLAND 26/7 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-12-14 | 2023-12-14 |  | Late | 2024-06-14 |  | 2024-06-14 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521883 | T3 WV FULTON-HOPLAND 26/7 RPL POLE | 70Y
LC | 127600485 | 65 | T3 WV FORKS OF THE BTTE TAP 0/3 INS DMPW | TABLEMTN | ETL.6722.SWIT | 2023-12-18 | 2023-12-18 |  | Late | 2024-06-18 |  | 2024-06-18 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Missing | Damper-Wood | Install | 46129631 | T3 WV FORKS OF THE BTTE TAP 0/3 INS DMPW | ICW
LC | 127619633 | 003/074 | T3 KILARC-CEDAR CREEK 003/074 GO95 RPR | TABLEMTN | ETL.7290.POLE.WOOD | 2023-12-18 | 2023-12-18 | 2024-05-07 | On-time | 2024-06-18 | 42 | 2024-06-18 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35523053 | T3 KILARC-CEDAR CREEK 03/071 GO95 CLEAR | 93G
LC | 127619636 | 004/095 | T3 VOLTA-DESCHUTES 04/095 GO95 CLEAR | TABLEMTN | ETL.8290.POLE.WOOD | 2023-12-18 | 2023-12-18 | 2024-04-22 | On-time | 2024-06-18 | 57 | 2024-06-18 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35523431 | T3 VOLTA-DESCHUTES 04/095 GO95 CLEAR | 93G
LC | 127620430 | 003/071 | T3 KILARC-CEDAR CREEK 03/071 GO95 CLEAR | TABLEMTN | ETL.7290.POLE.WOOD | 2023-12-18 | 2023-12-18 | 2024-05-07 | On-time | 2024-06-18 | 42 | 2024-06-18 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35523053 | T3 KILARC-CEDAR CREEK 03/071 GO95 CLEAR | 93G
LC | 127625990 | 047/270 | T3 TMBLR-SN LUIS OBSPO 47/270 GO95 CLEAR | PISMOBCH | ETL.3960.TOWR | 2023-12-18 | 2023-12-18 |  | Late | 2024-06-18 |  | 2024-06-18 | 400T | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Clearance | GO95 Clear Infract-Tower | To Be Corrected | 35526355 | T3 TMBLR-SN LUIS OBSPO 47/270 GO95 CLEAR | 93T
LC | 128003340 | 002/016 | T3 MORAGA-OAKLAND #2 2/16 GO95 CLEAR | CONCORD | ETL.2730.INSL.NCER | 2024-01-04 | 2023-12-18 |  | Late | 2024-06-18 |  | 2024-06-18 | 400 | TLQ | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Clearance | GO95 Clear Infract-Tower | To Be Corrected | 35528629 | T3 MORAGA-OAKLAND #2 GO95 CLEAR IN 3 STR | 93T
LC | 127655684 | 005/001 | T3 WV BRDGEVLLE-GRBRVLLE 5/1 INS DMPW | EUREKA | ETL.6220.INSL.CERA | 2023-12-19 | 2023-12-19 | 2024-03-08 | On-time | 2024-06-19 | 103 | 2024-06-19 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 46132159 | T3 WV BRDGEVLLE-GRBRVLLE 5/1 INS DMPW | ICW
LC | 127693070 | 012/111B | T3 WV GRN VLLY-PL SWT 12/111B INS DMPW | MOSSLNDG | ETL.1730.INSL.NCER | 2023-12-19 | 2023-12-19 | 2024-04-04 | On-time | 2024-06-19 | 76 | 2024-06-19 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | Missing | Damper-Wood | Install | 46125146 | T3 WV GRN VLLY-PL SWT 12/111B INS DMPW | ICW
LC | 127693078 | 000/005 | T3 MORAGA-OAKLAND #1 000/005 GO95 | CONCORD | ETL.2720.TOWR | 2023-12-19 | 2023-12-19 |  | Late | 2024-06-19 |  | 2024-06-19 | 400 | TLQ | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Clearance | GO95 Clear Infract-Tower | To Be Corrected | 31681559 | T3 MORAGA-OAKLAND #1 GO95 IN 6 TWRS. | 93T
LC | 127728178 | T-123 | T3 WV MWY-STA MRIA (12KV) T-123 INS DMPS | PISMOBCH | ETL.9240.INSL.NCER | 2023-12-20 | 2023-12-20 |  | Late | 2024-06-20 |  | 2024-06-20 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | Missing | Damper-Steel | Install | 46219755 | T3 WV MWY-STA MRIA (12KV) T-123 INS DMPS | ICS
LC | 127729907 | 013/059 | T3 WV EGLE RK-FN-SLVRDO 13/59 RPR STRT | LAKEVLLE | ETL.4392.TOWR | 2023-12-21 | 2023-12-21 | 2024-06-12 | On-time | 2024-06-21 | 9 | 2024-06-21 | 543 | TLQ | CREW | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Structure-Tower | Repair | 46204154 | T3 WV EGLE RK-FN-SLVRDO 13/59 RPR STRT | ICQ
LC | 127731155 | 010/094 | T3 WV DRUM-HIGGINS 10/94 RPL INSS | SACTO | ETL.4393.SWIT | 2023-12-21 | 2023-12-21 |  | Late | 2024-06-21 |  | 2024-06-21 | 532 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31629580 | T3 EI DRUM-HIGGINS 10/94 RPL SWTCH | 93S
LC | 127832282 | :026/008 | T3 FULTON-HOPLAND :26/8 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-12-28 | 2023-12-28 |  | Late | 2024-06-28 |  | 2024-06-28 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521884 | T3 FULTON-HOPLAND :026/008 RPL POLE | 70Y
LC | 127928631 | 000/001 | T3 EI FORKS OF THE BUTT TAP 0/1 RPR INSW | TABLEMTN | ETL.6722.INSL.NCER | 2023-12-28 | 2023-12-28 |  | Late | 2024-06-28 |  | 2024-06-28 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46149499 | T3 FORKS OF THE BUTTE TAP 0/001 RPR INSW | ICW
LC | 125273691 | 000/014 | T2 COLGATE-PALERMO 000/014 RPL INSW | SACTO | ETL.6500.INSL.NCER | 2023-01-03 | 2023-01-02 | 2023-08-28 | On-time | 2024-01-02 | 127 | 2024-01-02 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31655175 | T2 COLGATE-PALERMO 000/014 RPL INSW | 93I
LC | 125276058 | 048/010 | T2 TRINITY-MAPLE CREEK 48/10 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-01-03 | 2023-01-03 | 2023-06-22 | On-time | 2024-01-03 | 195 | 2023-07-03 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31634623 | T2 TRINITY-MAPLE CREEK 48/10 RPL STRW | 70Y
LC | 125276076 | 048/009 | T2 TRINITY-MAPLE CREEK 48/9 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-01-03 | 2023-01-03 | 2023-11-03 | On-time | 2024-01-03 | 61 | 2024-01-03 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31655172 | T2 TRINITY-MAPLE CREEK 48/9 RPL STRW | 70Y
LC | 125278535 | 016/161 | T2 EI ARCO-CHOLAME 16/161 RPR GYWW | MIDWAY | ETL.8440.POLE.NWOD | 2023-01-04 | 2023-01-04 | 2023-08-29 | On-time | 2024-01-04 | 128 | 2024-01-04 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45917894 | T2 EI ARCO-CHOLAME 16/161 RPR GYWW | ICW
LC | 125308818 | 003/071B | T2NT WV DELTA-MTN GATE JCT 3/71 RPR SPLW | TABLEMTN | ETL.6750.INSL.NCER | 2023-01-09 | 2023-01-09 | 2023-10-12 | On-time | 2024-01-09 | 89 | 2024-01-09 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45894595 | T2NT WV DELTA-MTN GATE JCT 3/71 RPR SPLW | ICW
LC | 125584293 | 008/041B | T2 DI CNTR CSTA-MRGA #2 8/41B RPL HRDT | CONCORD | ETL.5453.TOWR | 2023-03-03 | 2023-02-17 | 2023-10-31 | On-time | 2024-02-17 | 109 | 2024-02-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45937201 | T2 DI CNTR CSTA-MRGA #2 8/41B RPL HRDT | ICQ
LC | 125344254 | 023/204 | T2 BRDGVLLE-CTTNWD 023/204 COTTER | TABLEMTN | ETL.1110.INSL.NCER | 2023-01-13 | 2023-01-13 | 2023-08-20 | On-time | 2024-01-13 | 146 | 2023-07-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45698334 | T2 BRIDGEVILLE-CTTNWD 23/204 RPR INSW | ICW
LC | 125349304 | 065/004 | T2 HUMBOLDT-TRINITY 65/4 RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2023-01-16 | 2023-01-16 |  | Late | 2024-01-16 |  | 2024-01-16 | 372 | TLX | CREW | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31655640 | T2 HUMBOLDT-TRINITY 65/4 RPL STRW | 70Y
LC | 125352082 | 023/128 | T2 PARKWAY-MORAGA 23/128 RPR OPGW | CONCORD | ETL.5930.TOWR | 2023-01-17 | 2023-01-17 | 2023-04-12 | On-time | 2024-01-17 | 280 | 2023-04-17 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45711238 | T2 PARKWAY-MORAGA 23/128 RPR OPGW | ICS
LC | 125353114 | 012/102 | T2 CABRILLO-SNT YNZ SS 12/102 RPL ANCW | PISMOBCH | ETL.1200.POLE.WOOD | 2023-01-17 | 2023-01-17 | 2023-08-31 | On-time | 2024-01-17 | 139 | 2024-01-17 | 637 | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31645491 | T2NT CABRILLO-SNT YNZ SS 12/102 RPL ANCW | 93E
LC | 125365136 | 003/059 | T2 BRIONES TAP 3/59 RPL POLE | CONCORD | ETL.7055.POLE.WOOD | 2023-01-20 | 2023-01-20 | 2023-11-28 | On-time | 2024-01-20 | 53 | 2024-01-20 | 372 | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31656781 | T2 BRIONES TAP 3/59 RPL POLE | 70Y
LC | 125373588 | 058/006 | T2NT WV FORT ROSS-GUALALA5 58/6 INS DAMP | LAKEVLLE | ETL.6980.INSL.NCER | 2023-01-23 | 2023-01-23 | 2023-08-15 | On-time | 2024-01-23 | 161 | 2024-01-23 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 45902132 | T2NT WV FORT ROSS-GUALALA5 58/6 INS DAMP | ICW
LC | 125374301 | 024/010 | T2 MENDO-WILLITS-FT BRAGG 24/10 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2023-01-23 | 2023-01-23 |  | Late | 2024-01-23 |  | 2023-07-23 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31656736 | T2 MENDO-WILLITS-FT BRAGG 24/10 RPL POLE | 70Y
LC | 125375430 | 020/016 | T2 WV FORT BRAGG-ELK 20/16 INS DAMP | WILLITS | ETL.2060.INSL.CERA | 2023-01-23 | 2023-01-23 | 2024-03-13 | Late | 2024-01-23 | -50 | 2024-01-23 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 45902135 | T2 WV FORT BRAGG-ELK 20/16 INS DAMP | ICW
LC | 125381820 | 014/053 | T2 EI DIABLO-MIDWAY #2 14/53 RPR GYWS | PISMOBCH | ETL.5970.TOWR | 2023-01-24 | 2023-01-24 | 2023-08-03 | On-time | 2024-01-24 | 174 | 2024-01-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45908259 | T2 EI DIABLO-MIDWAY #2 14/53 RPR GYWS | ICS
LC | 125395458 | 003/024 | T2 DIVIDE-VANDENBERG #2 3/24 RPL ANCW | PISMOBCH | ETL.8630.POLE.WOOD | 2023-01-26 | 2023-01-26 | 2023-10-11 | On-time | 2024-01-26 | 107 | 2024-01-26 | 637 | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31658033 | T2 DIVIDE-VANDENBERG #2 3/24 RPL ANCW | 93E
LC | 125396148 | 007/114 | T2 EI DELTA-MTN GATE JCT 7/114 RPR GYWW | TABLEMTN | ETL.6750.POLE.WOOD | 2023-01-26 | 2023-01-26 | 2023-10-10 | On-time | 2024-01-26 | 108 | 2024-01-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698570 | T2 EI DELTA-MTN GATE JCT 7/114 RPR GYWW | ICW
LC | 125410297 | 021/084 | T2 EI DIABLO-MIDWAY #2 21/84 RPR GYWT | PISMOBCH | ETL.5970.TOWR | 2023-01-30 | 2023-01-30 | 2023-09-11 | On-time | 2024-01-30 | 141 | 2024-01-30 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 45926697 | T2 EI DIABLO-MIDWAY #2 21/84 RPR GYWT | ICQ
LC | 125414405 | 67 | T2 MENDOCINO-HARTLEY 22/14B RPR SWTC | WILLITS | ETL.7510.SWIT | 2023-01-31 | 2023-01-31 |  | Late | 2024-01-31 |  | 2024-01-31 | 623 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Out of Adjustment | Switch | Repair | 45907208 | T2 MENDOCINO-HARTLEY 22/14B RPR SWTC | ICE
LC | 125431640 | 007/051 | T2 DI SLO-CYCS 7/51 COTTER | PISMOBCH | ETL.9090.INSL.NCER | 2023-02-03 | 2023-01-30 | 2024-01-11 | On-time | 2024-01-30 | 19 | 2024-01-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46088098 | T2 DI SLO-CYCS 7/51 COTTER | ICW
LC | 125424808 | 145 | T2 DI GOLDTREE 0/1A RPR SWTC | PISMOBCH | ETL.2821.SWIT | 2023-02-02 | 2023-02-02 |  | Late | 2024-02-02 |  | 2024-02-02 | 623 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Out of Adjustment | Switch | Repair | 46078607 | T2 DI GOLDTREE 0/1A RPR SWTC | ICE
LC | 125425015 | 007/088 | T2 IGNACIO-BOLINAS #2 7/88 RPR IBWW | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-02 | 2023-02-02 |  | Late | 2024-02-02 |  | 2024-02-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Replace | 45907203 | T2 IGNACIO-BOLINAS #2 7/88 RPR IBWW | ICW
LC | 125514035 | 008/058 | T2 DI SL BSP-CAYUCOS 8/58 RPR INSW | PISMOBCH | ETL.9090.INSL | 2023-02-16 | 2023-01-30 | 2024-01-12 | On-time | 2024-01-30 | 18 | 2024-01-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46088306 | T2 DI SL BSP-CAYUCOS 8/58 RPR INSW | ICW
LC | 125427149 | 000/002 | T2 DI GOLDTREE TAP 0/002 RPL INSW | PISMOBCH | ETL.2821.INSL.NCER | 2023-02-02 | 2023-01-31 |  | Late | 2024-01-31 |  | 2024-01-31 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35485823 | T2 DI GOLDTREE TAP 0/002 RPL INSW | 93I
LC | 125432916 | 006/073 | T2 DI IGNACIO-BLNS #2 6/73 RPR INSW | LAKEVLLE | ETL.7180.INSL.NCER | 2023-02-03 | 2023-01-31 | 2023-09-30 | On-time | 2024-01-31 | 123 | 2024-01-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45907152 | T2 DI IGNACIO-BLNS #2 6/73 RPR INSW | ICW
LC | 125428171 | 135 | T2 DI GOLDTREE TAP 0/1 RPR SWTC | PISMOBCH | ETL.2821.SWIT | 2023-02-02 | 2023-01-31 |  | Late | 2024-01-31 |  | 2024-01-31 | 623 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Out of Adjustment | Switch | Repair | 46078605 | T2 DI GOLDTREE TAP 0/1 RPR SWTC | ICE
LC | 125433421 | 006/074 | T2 DI IGNACIO-BOLINAS #2 6/74 RPR GYWW | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-03 | 2023-01-31 | 2023-09-30 | On-time | 2024-01-31 | 123 | 2024-01-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45907153 | T2 DI IGNACIO-BOLINAS #2 6/74 RPR GYWW | ICW
LC | 125433552 | 006/074 | T2 DI IGNACIO-BOLINAS #2 6/74 COTTER | LAKEVLLE | ETL.7180.INSL.NCER | 2023-02-03 | 2023-01-31 | 2023-09-30 | On-time | 2024-01-31 | 123 | 2024-01-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45907154 | T2 DI IGNACIO-BOLINAS #2 6/74 COTTER | ICW
LC | 125433714 | 006/072 | T2 DI IGNACIO-BLNS #2 6/72 RPL GYWW | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-03 | 2023-01-31 | 2023-09-29 | On-time | 2024-01-31 | 124 | 2024-01-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45907151 | T2 DI IGNACIO-BLNS #2 6/72 RPL GYWW | ICW
LC | 125434152 | 010/125 | T2 DI IGNACIO-BOLINAS #2 10/125 RPR INSW | LAKEVLLE | ETL.7180.INSL.NCER | 2023-02-03 | 2023-01-31 | 2023-10-25 | On-time | 2024-01-31 | 98 | 2024-01-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45907157 | T2 DI IGNACIO-BOLINAS #2 10/125 RPR INSW | ICW
LC | 125437746 | 009/114 | T2 DI GNACIO-BOLINAS #2 009/114 COTTER | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-06 | 2023-01-31 | 2023-04-28 | On-time | 2024-01-31 | 278 | 2023-04-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45690383 | T2 DI GNACIO-BOLINAS #2 009/114 COTTER | ICW
LC | 125437851 | 009/114 | T2 DI IGNACIO-BOLINAS#2 9/114 RPL POLE | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-06 | 2023-01-31 | 2023-10-04 | On-time | 2024-01-31 | 119 | 2024-01-31 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31657800 | T2 DI IGNACIO-BOLINAS#2 9/114 RPL POLE | 70Y
LC | 125439194 | 007/093 | T2 DI IGNACIO-BOLINAS#2 007/093 RPL POLE | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-06 | 2023-01-31 | 2023-10-03 | On-time | 2024-01-31 | 120 | 2024-01-31 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31657699 | T2 DI IGNACIO-BOLINAS #2 07/092 RPL POLE | 70Y
LC | 125439498 | 007/092 | T2 DI IGNACIO-BOLINAS #2 07/092 RPL POLE | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-06 | 2023-01-31 | 2023-10-03 | On-time | 2024-01-31 | 120 | 2024-01-31 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31657699 | T2 DI IGNACIO-BOLINAS #2 07/092 RPL POLE | 70Y
LC | 125514232 | 008/044 | T2 DI MRR BY-SL BSP #1 8/44 RPR SHLT | PISMOBCH | ETL.2810.TOWR | 2023-02-16 | 2023-01-31 | 2023-12-28 | On-time | 2024-01-31 | 34 | 2024-01-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45945139 | T2 DI MRR BY-SL BSP #1 8/44 RPR SHLT | ICS
LC | 125557258 | 002/029 | T2 DI IGNACIO-BOLINAS #2 2/29 RPL HRDD | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-25 | 2023-01-31 | 2023-09-28 | On-time | 2024-01-31 | 125 | 2024-01-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45907149 | T2 DI IGNACIO-BOLINAS #2 2/29 RPL HRDD | ICW
LC | 125557342 | 002/029 | T2 DI IGNACIO-BOLINAS #2 2/29 RPR POLE | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-25 | 2023-01-31 | 2023-09-28 | On-time | 2024-01-31 | 125 | 2024-01-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45907150 | T2 DI IGNACIO-BOLINAS #2 2/29 RPR POLE | ICW
LC | 125421735 | 059/244 | T2 EI DIABLO-GATES #1 59/244 RPR GYWT | PISMOBCH | ETL.5960.TOWR | 2023-02-01 | 2023-02-01 | 2023-09-05 | On-time | 2024-02-01 | 149 | 2024-02-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 45926696 | T2 EI DIABLO-GATES #1 59/244 RPR GYWT | ICQ
LC | 125431013 | 007/090 | T2 DI IGNACIO-BOLINAS #2 7/90 COTTER | LAKEVLLE | ETL.7180.INSL.CERA | 2023-02-03 | 2023-01-31 |  | Late | 2024-01-31 |  | 2024-01-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45907155 | T2 DI IGNACIO-BOLINAS #2 7/90 COTTER | ICW
LC | 125427330 | 010/122 | T2 DI IGNCO BLNAS#2 10/122 RPR INSW | LAKEVLLE | ETL.7180.INSL.CERA | 2023-02-02 | 2023-02-01 | 2023-10-25 | On-time | 2024-02-01 | 99 | 2024-02-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45907158 | T2 DI IGNCO BLNAS#2 10/122 RPR INSW | ICW
LC | 125428510 | 010/057 | T2 DI MORRO BY-SLO #1 1/57 COMPLETE | PISMOBCH | ETL.2810.TOWR | 2023-02-02 | 2023-02-01 | 2024-01-26 | On-time | 2024-02-01 | 6 | 2024-02-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45915270 | T2 DI MORRO BY SLO #1 1/57 RPR STRT | ICQ
LC | 125432694 | 001/004 | T2 EI MENDOCINO-HARTLEY 1/004 RPL POLE | WILLITS | ETL.7510.POLE.WOOD | 2023-02-03 | 2023-02-03 | 2024-02-13 | Late | 2024-02-03 | -10 | 2024-02-03 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31658936 | T2 EI MENDOCINO-HARTLEY 1/004 RPL POLE | 70Y
LC | 125431161 | 010/059 | T2 DI MRR BY-SNLS BSP #1 10/59 RPR OPGW | PISMOBCH | ETL.2810.INSL.NCER | 2023-02-03 | 2023-02-01 | 2023-03-30 | On-time | 2024-02-01 | 308 | 2023-05-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45706703 | T2 DI MRR BY-SNLS BSP #1 10/59 RPR OPGW | ICS
LC | 125438741 | 010/058A | T2 DI MRR BY-SNL BSP #1 10/58A COMPLETE | PISMOBCH | ETL.2810.TOWR | 2023-02-06 | 2023-02-01 | 2024-01-26 | On-time | 2024-02-01 | 6 | 2024-02-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45915271 | T2 DI MRR BY-SNL BSP#1 10/58A BNT STEEL | ICQ
LC | 125444067 | 000/004 | T2 DI BUELLTON 0/4 RPR INSW | PISMOBCH | ETL.1201.INSL | 2023-02-07 | 2023-02-01 | 2024-01-17 | On-time | 2024-02-01 | 15 | 2024-02-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46078506 | T2 DI BUELLTON 0/4 RPR INSW | ICW
LC | 125446017 | 011/139 | T2 DI IGNACIO-BOLINAS #2 11/139 RPR GYWW | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-07 | 2023-02-01 | 2023-10-25 | On-time | 2024-02-01 | 99 | 2024-02-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45907159 | T2 DI IGNACIO-BOLINAS #2 11/139 RPR GYWW | ICW
LC | 125434020 | 010/123 | T2 EI COLGATE-SMRTVLE #2 10/123 RPR POLE | SACTO | ETL.6520.POLE.WOOD | 2023-02-03 | 2023-02-03 | 2024-05-02 | Late | 2024-02-03 | -89 | 2024-02-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45909865 | T2 EI COLGATE-SMRTVLE #2 10/123 RPR POLE | ICW
LC | 125446977 | 000/014 | T2 DI BUELLTON TAP 0/014 RPR INSW | PISMOBCH | ETL.1201.INSL.NCER | 2023-02-07 | 2023-02-01 | 2024-01-17 | On-time | 2024-02-01 | 15 | 2024-02-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46078507 | T2 DI BUELLTON TAP 0/014 RPR INSW | ICW
LC | 125447229 | 007/087 | T2 DI IGNACIO-BOLINAS #2 007/087 RMV VEG | LAKEVLLE | ETL.7180.POLE.NWOD | 2023-02-07 | 2023-02-01 | 2023-09-20 | On-time | 2024-02-01 | 134 | 2024-02-01 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125434042 | 004/034 | T2 DI OLEUM-NORTH 004/034 RPL INSS | CONCORD | ETL.3180.INSL.NCER | 2023-02-03 | 2023-02-02 | 2024-03-20 | Late | 2024-02-02 | -47 | 2024-02-02 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31657826 | T2 DI OLEUM-NORTH 004/034 RPL INSS | 93K
LC | 125426015 | 058/239 | T2 EI DIABLO-GATES #1 58/239 RPR GYWT | PISMOBCH | ETL.5960.TOWR | 2023-02-02 | 2023-02-02 | 2023-08-14 | On-time | 2024-02-02 | 172 | 2024-02-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 45926695 | T2 EI DIABLO-GATES #1 58/239 RPR GYWT | ICQ
LC | 125434395 | 010/126 | T2 DI IGNACIO-BOLINAS #2 10/126 RPL ANCW | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-03 | 2023-01-31 |  | Late | 2024-01-31 |  | 2023-07-31 | 637 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31656320 | T2 DI IGNACIO-BOLINAS #2 10/126 RPL ANCW | 93E
LC | 125428487 | 000/006 | T2 EI MENDOCINO-HARTLEY 0/6 RPL INSW | WILLITS | ETL.7510.INSL.NCER | 2023-02-02 | 2023-02-02 | 2023-09-22 | On-time | 2024-02-02 | 133 | 2023-08-02 | 508 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31638896 | T2 EI MENDOCINO-HARTLEY 0/006 RPL INSW | 93I
LC | 125428563 | 015/110 | T2 WV IGN-ALT-SSALITO #1 15/110 RPL POLE | LAKEVLLE | ETL.7160.POLE.WOOD | 2023-02-02 | 2023-02-02 | 2023-10-26 | On-time | 2024-02-02 | 99 | 2024-02-02 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31657698 | T2 WV IGN-ALT-SSALITO #1 15/110 RPL POLE | 70Y
LC | 125428705 | 031/125A | T2 DIABLO-MIDWAY #3 31/125A RPL ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-02 | 2023-02-02 | 2023-09-05 | On-time | 2024-02-02 | 150 | 2024-02-02 | 374 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Road | Install | 31643850 | T2 DIABLO-MIDWAY #3 30/123 RPL ROAD | 71Y
LC | 125428706 | 030/124 | T2 DIABLO-MIDWAY #3 30/124 RPL ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-02 | 2023-02-02 | 2023-07-25 | On-time | 2024-02-02 | 192 | 2024-02-02 | 374 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Road | Install | 31643850 | T2 DIABLO-MIDWAY #3 30/123 RPL ROAD | 71Y
LC | 125428707 | 030/121 | T2 DIABLO-MIDWAY #3 30/121 RPR ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-02 | 2023-02-02 | 2023-09-05 | On-time | 2024-02-02 | 150 | 2024-02-02 | 932 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Repair | 45192143 | T3NT DIABLO-MIDWAY #3 006/023 RPR ROAD | CHS
LC | 125428708 | 032/130 | T2 DIABLO-MIDWAY #3 32/130 RPL ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-02 | 2023-02-02 | 2023-10-04 | On-time | 2024-02-02 | 121 | 2024-02-02 | 374 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Replace | 31643850 | T2 DIABLO-MIDWAY #3 30/123 RPL ROAD | 71Y
LC | 125428709 | 032/129 | T2NT DIABLO-MIDWAY #3 32/129 RPR ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-02 | 2023-02-02 | 2023-09-06 | On-time | 2024-02-02 | 149 | 2024-02-02 | 932 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Repair | 45192143 | T3NT DIABLO-MIDWAY #3 006/023 RPR ROAD | CHS
LC | 125428748 | 031/126 | T2NT DIABLO-MIDWAY #3 31/126 RPL ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-02 | 2023-02-02 | 2023-09-05 | On-time | 2024-02-02 | 150 | 2024-02-02 | 374 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Replace | 31643850 | T2 DIABLO-MIDWAY #3 30/123 RPL ROAD | 71Y
LC | 125428749 | 032/131 | T2NT DIABLO-MIDWAY #3 32/131 RPL ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-02 | 2023-02-02 | 2023-10-04 | On-time | 2024-02-02 | 121 | 2024-02-02 | 374 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Replace | 31643850 | T2 DIABLO-MIDWAY #3 30/123 RPL ROAD | 71Y
LC | 125436180 | 036/146 | T2 DIABLO-MIDWAY #3 36/146 COA | PISMOBCH | ETL.5980.TOWR | 2023-02-04 | 2023-02-04 |  | Late | 2024-02-04 |  | 2024-02-04 | 374 | TLR | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Road | Replace | 31643850 | T2 DIABLO-MIDWAY #3 30/123 RPL ROAD | 71Y
LC | 125428820 | 030/123 | T2 DIABLO-MIDWAY #3 30/123 RPL ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-02 | 2023-02-02 | 2023-07-25 | On-time | 2024-02-02 | 192 | 2024-02-02 | 374 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Replace | 31643850 | T2 DIABLO-MIDWAY #3 30/123 RPL ROAD | 71Y
LC | 125428856 | 028/113 | T2 DIABLO-MIDWAY #2 28/113 RPR ROAD | PISMOBCH | ETL.5970.TOWR | 2023-02-02 | 2023-02-02 | 2023-08-23 | On-time | 2024-02-02 | 163 | 2024-02-02 | 932 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Repair | 45192142 | T0 DIABLO-MIDWAY #2 61/247 RPR ROAD | CHS
LC | 125438155 | 015/111 | T2 DI IGNC-ALTO-SSLT #1 15/111 RPL STRW | LAKEVLLE | ETL.7160.POLE.WOOD | 2023-02-06 | 2023-02-06 |  | Late | 2024-02-06 |  | 2024-02-06 | 372T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35475606 | T2 DI IGNC-ALTO-SSLT #1 15/111 RPL STRW | 70Y
LC | 125434040 | :031/198 | T2 DI NO TWR-MRTNZ #1 :31/198 RPR SHLS | CONCORD | ETL.3130.INSL.CERA | 2023-02-03 | 2023-02-02 | 2023-05-10 | On-time | 2024-02-02 | 268 | 2023-05-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45690258 | T2 DI NO TWR-MRTNZ #1 :31/198 RPR SHLS | ICS
LC | 125434041 | :031/198 | T2 DI NO TWR-MRTNZ #1 :31/198 COTTER | CONCORD | ETL.3130.INSL.CERA | 2023-02-03 | 2023-02-02 | 2023-08-19 | On-time | 2024-02-02 | 167 | 2024-02-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45907659 | T2 DI NO TWR-MRTNZ #1 :31/198 COTTER | ICS
LC | 125445032 | 008/043 | T2 DI MRO BY-SLO #1 008/043 RPR OPGW | PISMOBCH | ETL.2810.TOWR | 2023-02-07 | 2023-02-02 | 2023-04-11 | On-time | 2024-02-02 | 297 | 2023-05-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45706705 | T2 DI MRO BY-SLO #1 008/043 RPR OPGW | ICS
LC | 125445858 | 25 | T2 DI SN LS BSP-CYCS 3/17A RPR SWTC | PISMOBCH | ETL.9090.SWIT | 2023-02-07 | 2023-02-02 | 2024-01-19 | On-time | 2024-02-02 | 14 | 2024-02-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 46088300 | T2 DI SN LS BSP-CYCS 3/17A RPR SWTC | ICW
LC | 125446386 | 008/045 | T2 DI MRO BY-SLO #1 008/045 RPR OPGW | PISMOBCH | ETL.2810.TOWR | 2023-02-07 | 2023-02-02 | 2023-04-11 | On-time | 2024-02-02 | 297 | 2023-05-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45706706 | T2 DI MRO BY-SLO #1 008/045 RPR OPGW | ICS
LC | 125446581 | 016/160 | T2 DI IGNACIO-ALTO 16/160 RPL POLE | LAKEVLLE | ETL.7150.POLE.WOOD | 2023-02-07 | 2023-02-02 | 2023-10-31 | On-time | 2024-02-02 | 94 | 2024-02-02 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31657697 | T2 DI IGNACIO-ALTO 16/160 RPL POLE | 70Y
LC | 125441661 | 021/000 | T2 RIO DELL JCT-BRIDGEVILL 21/0 RPL STRW | EUREKA | ETL.7850.POLE.WOOD | 2023-02-06 | 2023-02-06 |  | Late | 2024-02-06 |  | 2024-02-06 | 372 | TLX | CREW | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31662187 | T2 RIO DELL JCT-BRIDGEVILL 21/0 RPL STRW | 70Y
LC | 125441754 | 037/151A | T2NT DIABLO-MIDWAY #3 37/151A RPL ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-06 | 2023-02-06 |  | Late | 2024-02-06 |  | 2024-02-06 | 374 | TLR | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Road | Replace | 31643850 | T2 DIABLO-MIDWAY #3 30/123 RPL ROAD | 71Y
LC | 125450015 | 014/169 | T2 DI IGNACIO-BLNS #2 14/169L COMPLETE | LAKEVLLE | ETL.7180.POLE.WDPS | 2023-02-08 | 2023-02-02 | 2023-10-25 | On-time | 2024-02-02 | 100 | 2024-02-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45907205 | T2 DI IGNACIO-BLNS #2 14/169L RPR GYWW | ICW
LC | 125451631 | 003/018 | T2 DI SAN LUIS OBISP CAYCS 3/18 RPL DMPW | PISMOBCH | ETL.9090.INSL.NCER | 2023-02-08 | 2023-02-02 | 2024-01-13 | On-time | 2024-02-02 | 20 | 2024-02-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46088301 | T2 DI SAN LUIS OBISP CAYCS 3/18 RPL DMPW | ICW
LC | 125452793 | 004/076 | T2 DI CLNDR SW STA MESA 4/076 RPR SPLW | PISMOBCH | ETL.1210.INSL.NCER | 2023-02-08 | 2023-02-02 | 2024-01-13 | On-time | 2024-02-02 | 20 | 2024-02-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46078504 | T2 DI CLNDR SW STA MESA 4/076 RPR SPLW | ICW
LC | 125454318 | 002/056 | T2 DI CSCD-BNTN-DSCHTS 2/56 RPL POLE | TABLEMTN | ETL.6310.POLE.WOOD | 2023-02-09 | 2023-02-02 | 2023-11-06 | On-time | 2024-02-02 | 88 | 2024-02-02 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31657557 | T2 DI CSCD-BNTN-DSCHTS 2/56 RPL POLE | 70Y
LC | 125455770 | 006/031 | T2 DI SN LUS OBSP OCENO 6/031 COTTER | PISMOBCH | ETL.3540.INSL.CERA | 2023-02-09 | 2023-02-02 | 2024-01-09 | On-time | 2024-02-02 | 24 | 2024-02-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45945122 | T2 DI SN LUS OBSP OCENO 6/031 COTTER | ICS
LC | 125491407 | 015/108A | T2 DI IGIO ALTO SUSLTO#1 15/108A RPR GYW | LAKEVLLE | ETL.7160.POLE.WOOD | 2023-02-13 | 2023-02-02 | 2023-08-18 | On-time | 2024-02-02 | 168 | 2024-02-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45907206 | T2 DI IGIO ALTO SUSLTO#1 15/108A RPR GYW | ICW
LC | 125515830 | 000/003 | T2 DI GNACIO-BOLINAS #1 0/3 COTTER | LAKEVLLE | ETL.7140.INSL.NCER | 2023-02-16 | 2023-02-02 | 2023-09-12 | On-time | 2024-02-02 | 143 | 2024-02-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45907202 | T2 DI GNACIO-BOLINAS #1 0/3 COTTER | ICW
LC | 125515903 | 004/023 | T2 DI SL BSP-OCEANO 4/23 RPR STRT | PISMOBCH | ETL.3530.TOWR | 2023-02-16 | 2023-02-02 | 2023-09-05 | On-time | 2024-02-02 | 150 | 2024-02-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45915273 | T2 DI SL BSP-OCEANO 4/23 RPR STRT | ICQ
LC | 125434758 | 033/135 | T2NT DIABLO-MIDWAY #3 33/135 RPR ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-03 | 2023-02-03 | 2023-10-04 | On-time | 2024-02-03 | 122 | 2024-02-03 | 932 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Repair | 45192143 | T3NT DIABLO-MIDWAY #3 006/023 RPR ROAD | CHS
LC | 125434759 | 034/137 | T2NT DIABLO-MIDWAY #3 34/137 RPR ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-03 | 2023-02-03 | 2023-10-06 | On-time | 2024-02-03 | 120 | 2024-02-03 | 932 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Repair | 45192143 | T3NT DIABLO-MIDWAY #3 006/023 RPR ROAD | CHS
LC | 125445457 | 011/079 | T2 DI IGNC-ALTO-SLTO #1 11/79 RPR OPGW | LAKEVLLE | ETL.7160.TOWR | 2023-02-07 | 2023-02-01 |  | Late | 2024-02-01 |  | 2024-02-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45690388 | T2 DI IGNC-ALTO-SLTO #1 11/79 RPR SHLS | ICS
LC | 125435050 | 035/142 | T2 DIABLO-MIDWAY #3 35/142 RPR ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-03 | 2023-02-03 | 2023-10-06 | On-time | 2024-02-03 | 120 | 2024-02-03 | 932 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Repair | 45192143 | T3NT DIABLO-MIDWAY #3 006/023 RPR ROAD | CHS
LC | 125435051 | 035/141 | T2 DIABLO-MIDWAY #3 35/141 RPL ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-03 | 2023-02-03 | 2023-10-06 | On-time | 2024-02-03 | 120 | 2024-02-03 | 374 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Replace | 31643850 | T2 DIABLO-MIDWAY #3 30/123 RPL ROAD | 71Y
LC | 125435052 | 035/143 | T2 DIABLO-MIDWAY #3 35/143 RPL ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-03 | 2023-02-03 | 2023-10-06 | On-time | 2024-02-03 | 120 | 2024-02-03 | 374 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Replace | 31643850 | T2 DIABLO-MIDWAY #3 30/123 RPL ROAD | 71Y
LC | 125435053 | 035/144 | T2 DIABLO-MIDWAY #3 35/144 RPR ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-03 | 2023-02-03 | 2023-10-09 | On-time | 2024-02-03 | 117 | 2024-02-03 | 932 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Repair | 45192143 | T3NT DIABLO-MIDWAY #3 006/023 RPR ROAD | CHS
LC | 125446910 | 027/004 | T2 RIO DEL JCT-BRDGE 27/4 GO95 CLEARANCE | EUREKA | ETL.7850.POLE.WOOD | 2023-02-07 | 2023-02-07 |  | Late | 2024-02-07 |  | 2024-02-07 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31636426 | T2 RIO DEL JCT-BRDGE 27/4 RPL POLE | 93G
LC | 125435057 | 032/132 | T2 EI DIABLO-MIDWAY #2 32/132 RPR GYWT | PISMOBCH | ETL.5970.TOWR | 2023-02-03 | 2023-02-03 | 2023-09-07 | On-time | 2024-02-03 | 149 | 2024-02-03 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 45926698 | T2 EI DIABLO-MIDWAY #2 32/132 RPR GYWT | ICQ
LC | 125451123 | 005/111 | T2 DI KESWICK-CASCADE 5/111 RPL HRDD | TABLEMTN | ETL.7260.POLE.WOOD | 2023-02-08 | 2023-02-03 | 2023-10-15 | On-time | 2024-02-03 | 111 | 2024-02-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45698586 | T2 DI KESWICK-CASCADE 5/111 RPL HRDD | ICW
LC | 125451787 | 005/105 | T2 DI KESWICK-CASCADE 5/105 RPL INSW | TABLEMTN | ETL.7260.INSL.CERA | 2023-02-08 | 2023-02-03 | 2023-10-15 | On-time | 2024-02-03 | 111 | 2024-02-03 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35474533 | T2 DI KESWICK-CASCADE 5/105 RPL INSW | 93I
LC | 125454656 | 011/244 | T2 DI CSCD-BNTN-DSCHTS 11/244 RPL POLE | TABLEMTN | ETL.6310.POLE.WOOD | 2023-02-09 | 2023-02-03 | 2023-11-04 | On-time | 2024-02-03 | 91 | 2024-02-03 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31658934 | T2 DI CSCD-BNTN-DSCHTS 11/244 RPL POLE | 70Y
LC | 125469031 | 013/158 | T2 DI IGNACIO-BLNS #2 13/158 COTTER | LAKEVLLE | ETL.7180.INSL.NCER | 2023-02-09 | 2023-02-03 | 2023-11-13 | On-time | 2024-02-03 | 82 | 2024-02-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45910128 | T2 DI IGNACIO-BLNS #2 13/158 COTTER | ICW
LC | 125469631 | 002/052 | T2 DI KESWICK-CASCADE 002/052 RPL HRDW | TABLEMTN | ETL.7260.POLE.WOOD | 2023-02-09 | 2023-02-03 | 2023-10-15 | On-time | 2024-02-03 | 111 | 2024-02-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45698567 | T2 DI KESWICK-CASCADE 002/052 RPL HRDW | ICW
LC | 125470053 | 004/049C | T2 DI IGNACIO-BLNS #2 4/49C RPR GYWW | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-09 | 2023-02-03 | 2023-09-25 | On-time | 2024-02-03 | 131 | 2024-02-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45910130 | T2 DI IGNACIO-BLNS #2 4/49C RPR GYWW | ICW
LC | 125484430 | 037/326 | T2 DI CASCADE-CTTNWD 37/326R RPR GYWW | TABLEMTN | ETL.1240.POLE.STPS | 2023-02-10 | 2023-02-03 | 2023-11-10 | On-time | 2024-02-03 | 85 | 2024-02-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698627 | T2 DI CASCADE-CTTNWD 37/326R RPR GYWW | ICW
LC | 125485261 | 000/007C | T2 DI CTTNWD-BNTN #2 0/7C RPR GYWW | TABLEMTN | ETL.6650.POLE.NWOD | 2023-02-10 | 2023-02-03 | 2023-11-09 | On-time | 2024-02-03 | 86 | 2024-02-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698588 | T2 DI CTTNWD-BNTN #2 0/7C RPR GYWW | ICW
LC | 125516093 | 024/209 | T2 DI CASCDE CTTNWD 024/209L RPL STRW | TABLEMTN | ETL.1240.POLE.WDPS | 2023-02-16 | 2023-02-03 | 2023-12-02 | On-time | 2024-02-03 | 63 | 2024-02-03 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31658935 | T2 DI CASCDE CTTNWD 024/209L RPL STRW | 70Y
LC | 125516096 | 024/209 | T2 DI CASCDE CTTNWD 024/209R RPL STRW | TABLEMTN | ETL.1240.POLE.WDPS | 2023-02-16 | 2023-02-03 | 2023-12-02 | On-time | 2024-02-03 | 63 | 2024-02-03 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31658935 | T2 DI CASCDE CTTNWD 024/209L RPL STRW | 70Y
LC | 125516449 | 008/078 | T2 DI COTTONWD-BNTON #2 8/78R RPR STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2023-02-16 | 2023-02-03 | 2023-11-09 | On-time | 2024-02-03 | 86 | 2024-02-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45698590 | T2 DI COTTONWD-BNTON #2 8/78R RPR STRW | ICW
LC | 125516534 | 004/091 | T2 DI KESWICK-CASCADE 4/91 RPL ANCW | TABLEMTN | ETL.7260.POLE.WOOD | 2023-02-16 | 2023-02-03 | 2023-08-25 | On-time | 2024-02-03 | 162 | 2024-02-03 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35474532 | T2 DI KESWICK-CASCADE 4/91 RPL ANCW | 93E
LC | 125516651 | 037/321 | T2 DI CASCADE-CTTNWD 37/321 RPR INSW | TABLEMTN | ETL.1240.INSL.CERA | 2023-02-16 | 2023-02-03 | 2023-03-20 | On-time | 2024-02-03 | 320 | 2023-08-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45686651 | T2 DI CASCADE-CTTNWD 37/321 RPR INSW | ICW
LC | 125516652 | 037/321 | T2 DI CASCADE-CTTNWD 37/321R RPR OPGW | TABLEMTN | ETL.1240.POLE.WDPS | 2023-02-16 | 2023-02-03 | 2023-11-16 | On-time | 2024-02-03 | 79 | 2024-02-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45698592 | T2 DI CASCADE-CTTNWD 37/321R RPR OPGW | ICW
LC | 125451730 | 003/018 | T2 DI SAN LUIS OBISPO CYCS 3/18 RPR INSW | PISMOBCH | ETL.9090.INSL.NCER | 2023-02-08 | 2023-02-02 | 2024-05-12 | Late | 2024-02-02 | -100 | 2024-02-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46088302 | T2 DI SAN LUIS OBISPO CYCS 3/18 RPR INSW | ICW
LC | 125516654 | 037/321 | T2 DI CASCADE-CTTNWD 37/321L RPR STRW | TABLEMTN | ETL.1240.POLE.WDPS | 2023-02-16 | 2023-02-03 | 2023-03-20 | On-time | 2024-02-03 | 320 | 2024-02-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45698591 | T2 DI CASCADE-CTTNWD 37/321L RPR STRW | ICW
LC | 125436154 | 033/136 | T2 EI DIABLO-MIDWAY #2 33/136 RPR GYWT | PISMOBCH | ETL.5970.TOWR | 2023-02-04 | 2023-02-04 | 2023-09-06 | On-time | 2024-02-04 | 151 | 2024-02-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 45926699 | T2 EI DIABLO-MIDWAY #2 33/136 RPR GYWT | ICQ
LC | 125439492 | 001/021 | T2 DI IGNACIO-BOLINAS #1 01/021 RPL TIED | LAKEVLLE | ETL.7140.INSL.NCER | 2023-02-06 | 2023-02-06 | 2023-05-04 | On-time | 2024-02-06 | 278 | 2024-02-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45690386 | T2 DI IGNACIO-BOLINAS #1 01/021 RPL TIED | ICW
LC | 125452641 | 000/007 | T2 DI ATASCADERO-CAYUCOS 0/007 RPL POLE | PISMOBCH | ETL.8480.POLE.WOOD | 2023-02-08 | 2023-02-02 | 2024-03-14 | Late | 2024-02-02 | -41 | 2024-02-02 | 372T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483503 | T2 DI ATASCADERO CAYUCOS 0/007 RPL POLE | 70Y
LC | 125440108 | 000/010 | T2 EI PALERMO-OROVILLE #1 0/010 RPL POLE | TABLEMTN | ETL.7730.POLE.WOOD | 2023-02-06 | 2023-02-06 | 2023-10-23 | On-time | 2024-02-06 | 106 | 2024-02-06 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31662186 | T2 EI PALERMO-OROVILLE #1 0/010 RPL POLE | 70Y
LC | 125453199 | 008/039B | T2 DI SN LUS-SNTA MARIA 8/039B RPL INSS | PISMOBCH | ETL.3540.INSL.CERA | 2023-02-08 | 2023-02-02 | 2024-03-29 | Late | 2024-02-02 | -56 | 2024-02-02 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31663734 | T2 DI SLO-SANTA MARIA 21/100 RPL INSS | 93K
LC | 125453628 | 039/157 | T2 DIABLO-MIDWAY #3 39/157 RPL ROAD | PISMOBCH | ETL.5980.TOWR | 2023-02-08 | 2023-02-08 |  | Late | 2024-02-08 |  | 2024-02-08 | 374 | TLR | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Road | Replace | 31643850 | T2 DIABLO-MIDWAY #3 30/123 RPL ROAD | 71Y
LC | 125440827 | 129 | T2 EI DIVIDE-CABRILLO #2 8/106 COTTER | PISMOBCH | ETL.1370.SWIT | 2023-02-06 | 2023-02-06 | 2024-01-03 | On-time | 2024-02-06 | 34 | 2024-02-06 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45945120 | T2 EI DIVIDE-CABRILLO #2 8/106 COTTER | ICS
LC | 125441891 | 050/205 | T2 EI DIABLO-GATES #1 50/205 RPR GYWT | PISMOBCH | ETL.5960.TOWR | 2023-02-06 | 2023-02-06 | 2023-08-15 | On-time | 2024-02-06 | 175 | 2024-02-06 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 45926694 | T2 EI DIABLO-GATES #1 50/205 RPR GYWT | ICQ
LC | 125443131 | 015/109 | T2 DI IGNC-ALTO SUSLTO#2 15/109 COMPLETE | LAKEVLLE | ETL.7170.INSL.NCER | 2023-02-07 | 2023-02-06 | 2023-06-09 | On-time | 2024-02-06 | 242 | 2023-08-06 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31639234 | T2 DI IGNC-ALTO SUSLTO#2 15/109 RPL INSS | 93K
LC | 125443139 | 015/109 | T2 DI IGNC-ALTO SUSLTO#1 15/109 RPL INSS | LAKEVLLE | ETL.7160.INSL.NCER | 2023-02-07 | 2023-02-06 | 2023-10-25 | On-time | 2024-02-06 | 104 | 2023-08-06 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31639233 | T2 DI IGNC-ALTO SUSLTO#1 15/109 RPL INSS | 93K
LC | 125443289 | 57 | T2 DI IGNACIO-BLNS #2 15/175 RPR SWTC | LAKEVLLE | ETL.7180.SWIT | 2023-02-07 | 2023-02-06 | 2023-05-02 | On-time | 2024-02-06 | 280 | 2023-05-06 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 45690387 | T2 DI IGNACIO-BLNS #2 15/175 RPR SWTC | ICE
LC | 125486946 | 004/074 | T2 DI CALLENDER SS-MESA 4/74 COTTER | PISMOBCH | ETL.1210.INSL.NCER | 2023-02-10 | 2023-02-06 | 2024-01-13 | On-time | 2024-02-06 | 24 | 2024-02-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46078505 | T2 DI CALLENDER SS-MESA 4/74 COTTER | ICW
LC | 125491487 | 001/015 | T2 DI IGNACIO-BLNS #2 1/15 RPL INSW | LAKEVLLE | ETL.7180.INSL.CERA | 2023-02-13 | 2023-02-06 | 2023-10-27 | On-time | 2024-02-06 | 102 | 2024-02-06 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31662270 | T2 DI IGNACIO-BLNS #2 1/15 RPL INSW | 93I
LC | 125470108 | 37 | T2 DI IGNACIO-BOLINAS #2 26/293 RPL SWTC | LAKEVLLE | ETL.7180.SWIT | 2023-02-09 | 2023-02-03 |  | Late | 2024-02-03 |  | 2024-02-03 | 427 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Switch-Wood | Replace | 31658937 | T2 DI IGNACIO-BOLINAS #2 26/293 RPL SWTC | 93H
LC | 125492564 | 015/170 | T2 DI IGNCIO BLNAS#2 15/170 RPR GYWW | LAKEVLLE | ETL.7180.POLE.STPS | 2023-02-13 | 2023-02-06 | 2023-10-25 | On-time | 2024-02-06 | 104 | 2024-02-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45914906 | T2 DI IGNCIO BLNAS#2 15/170 RPR GYWW | ICW
LC | 125492845 | 017/088 | T2 DI SL BSP-OCEANO 17/88 RPL INSW | PISMOBCH | ETL.3530.INSL.CERA | 2023-02-13 | 2023-02-06 | 2023-05-20 | On-time | 2024-02-06 | 262 | 2024-02-06 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35535535 | T2 DI SL BSP-OCEANO 17/88 RPL INSW | 93I
LC | 125485435 | 001/008 | T2 EI MENDOCINO-HARTLEY 1/8 RPL POLE | WILLITS | ETL.7510.POLE.WOOD | 2023-02-10 | 2023-02-10 |  | Late | 2024-02-10 |  | 2024-02-10 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31658936 | T2 EI MENDOCINO-HARTLEY 1/004 RPL POLE | 70Y
LC | 125485688 | 014/165 | T2 DI IGNACIO-BLNS #2 14/165 RPL INSW | LAKEVLLE | ETL.7180.INSL.NCER | 2023-02-10 | 2023-02-03 |  | Late | 2024-02-03 |  | 2024-02-03 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35474529 | T2 DI IGNACIO-BLNS #2 14/165 RPL INSW | 93I
LC | 125493693 | 001/023 | T2 DI IGNACIO-BLNS #1 1/23 RPR GYWW | LAKEVLLE | ETL.7140.POLE.NWOD | 2023-02-13 | 2023-02-06 | 2023-09-12 | On-time | 2024-02-06 | 147 | 2024-02-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45914907 | T2 DI IGNACIO-BLNS #1 1/23 RPR GYWW | ICW
LC | 125494101 | :031/202 | T2 DI NRTH TOWR-MARTZ#1 :31/202 RPR OPGW | CONCORD | ETL.3130.TOWR | 2023-02-13 | 2023-02-06 | 2023-08-19 | On-time | 2024-02-06 | 171 | 2024-02-06 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45914374 | T2 DI NRTH TOWR-MARTZ#1 :31/202 RPR OPGW | ICS
LC | 125494490 | 000/010 | T2 DI IGNACIO-BLNS #2 0/10 RPL INSW | LAKEVLLE | ETL.7180.INSL.NCER | 2023-02-13 | 2023-02-06 | 2023-09-30 | On-time | 2024-02-06 | 129 | 2024-02-06 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31662183 | T2 DI IGNACIO-BLNS #2 0/10 RPL INSW | 93I
LC | 125487549 | 039/158 | T2 DIABLO-MIDWAY #2 39/158 RPL ROAD | PISMOBCH | ETL.5970.TOWR | 2023-02-10 | 2023-02-10 |  | Late | 2024-02-10 |  | 2024-02-10 | 374 | TLR | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Road | Replace | 31643849 | T2 DIABLO-MIDWAY #2 39/158 RPL ROAD | 71Y
LC | 125505283 | 037/325 | T2 DI CSCDE CTTNWD 37/325 RPR GYWW | TABLEMTN | ETL.1240.POLE.STPS | 2023-02-15 | 2023-02-06 | 2023-11-10 | On-time | 2024-02-06 | 88 | 2024-02-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698626 | T2 DI CSCDE CTTNWD 37/325 RPR GYWW | ICW
LC | 125487904 | 014/081 | T2 HAAS-MCCALL 14/81 RPL ROAD | FRESNO | ETL.4850.TOWR | 2023-02-10 | 2023-02-10 |  | Late | 2024-02-10 |  | 2024-02-10 | 374 | TLR | CREW | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Road | Replace | 31675925 | T2 HAAS-MCCALL 14/81 RPL ROAD | 71Y
LC | 125516636 | 001/016 | T2 DI IGNCO BLNAS#2 1/16 RPL STRW | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-16 | 2023-02-06 | 2023-10-27 | On-time | 2024-02-06 | 102 | 2024-02-06 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31662184 | T2 DI IGNCO BLNAS#2 1/16 RPL STRW | 70Y
LC | 125516823 | A006/097 | T2 DI IGNACIO-BLNS #2 A006/097 RPL HRDW | LAKEVLLE | ETL.7180.POLE.NWOD | 2023-02-16 | 2023-02-06 | 2023-10-06 | On-time | 2024-02-06 | 123 | 2024-02-06 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45914905 | T2 DI IGNACIO-BLNS #2 A006/097 RPL HRDW | ICS
LC | 125516850 | 036/315 | T2 DI CASCADE-CTTNWD 036/315R RPR OPGW | TABLEMTN | ETL.1240.POLE.STPS | 2023-02-16 | 2023-02-06 | 2023-11-10 | On-time | 2024-02-06 | 88 | 2024-02-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45698625 | T2 DI CASCADE-CTTNWD 036/315R RPR OPGW | ICW
LC | 125520169 | 000/005 | T2 DI MUSTANG TAP 0/005 RPR GYWW | PISMOBCH | ETL.9091.POLE.WOOD | 2023-02-17 | 2023-02-06 | 2023-09-09 | On-time | 2024-02-06 | 150 | 2024-02-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45971792 | T2 DI MUSTANG TAP 0/005 RPR GYWW | ICW
LC | 125491757 | 004/050 | T2 DI IGNACIO-BLNS #1 4/50 RPL STRW | LAKEVLLE | ETL.7140.POLE.WOOD | 2023-02-13 | 2023-02-06 |  | Late | 2024-02-06 |  | 2024-02-06 | 372 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31662182 | T2 DI IGNACIO-BLNS #1 4/50 RPL POLE | 70Y
LC | 125442705 | 052/004 | T2 EI HUMBOLDT-TRINITY 52/4 COMPLETE | EUREKA | ETL.1820.POLE.WDPS | 2023-02-07 | 2023-02-07 | 2023-08-05 | On-time | 2024-02-07 | 186 | 2024-02-07 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31619828 | T2 EI HUMBOLDT-TRINITY 52/4R RPL STRW | 70Y
LC | 125492213 | A005/108 | T2 EI LAKEVILLE #2 5/108 RPR GYWW | LAKEVLLE | ETL.7340.POLE.WOOD | 2023-02-13 | 2023-02-13 | 2024-05-06 | Late | 2024-02-13 | -83 | 2023-08-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45926559 | T2 EI LAKEVILLE #2 5/108 RPR GYWW | ICW
LC | 125444862 | 005/070 | T2 EI DIVIDE-CABRILLO #2 5/70 RPL INSW | PISMOBCH | ETL.1370.INSL.NCER | 2023-02-07 | 2023-02-07 | 2024-01-05 | On-time | 2024-02-07 | 33 | 2024-02-07 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35495093 | T2 EI DIVIDE-CABRILLO #2 5/70 RPL INSW | 93I
LC | 125445256 | 008/095 | T2 EI DIVIDE-CABRILLO #2 8/95 COMPLETE | PISMOBCH | ETL.1370.INSL.CERA | 2023-02-07 | 2023-02-07 | 2023-07-06 | On-time | 2024-02-07 | 216 | 2024-02-07 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35529931 | T2 EI DIVIDE-CABRILLO #2 8/95 COMPLETE | 93I
LC | 125492849 | 005/072 | T2 DI DIVIDE-CBRLLO #1 5/72 RPL STRW | PISMOBCH | ETL.1380.POLE.WOOD | 2023-02-13 | 2023-02-06 | 2024-06-20 | Late | 2024-02-06 | -135 | 2024-02-06 | 372T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483504 | T2 DI DIVIDE-CBRLLO #1 5/72 RPL STRW | 70Y
LC | 125445312 | 008/103 | T2 EI DIVIDE-CABRILLO #2 8/103 RPL INSW | PISMOBCH | ETL.1370.INSL.CERA | 2023-02-07 | 2023-02-07 | 2023-12-28 | On-time | 2024-02-07 | 41 | 2024-02-07 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35503057 | T2 EI DIVIDE-CABRILLO #2 8/103 RPL INSW | 93I
LC | 125493076 | 007/086 | T2 EI COLGATE-SMARTVILLE #2 7/86 REFRAME | SACTO | ETL.6520.POLE.WOOD | 2023-02-13 | 2023-02-13 | 2024-05-01 | Late | 2024-02-13 | -78 | 2024-02-13 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35481576 | T2 EI COLGATE-SMARTVILLE #2 7/86 REFRAME | 93E
LC | 125493485 | 003/027 | T2 DI OLEUM-NT-CHRIST 3/27 RPL INSS | CONCORD | ETL.3180.INSL | 2023-02-13 | 2023-02-06 | 2024-03-20 | Late | 2024-02-06 | -43 | 2024-02-06 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31663382 | T2 DI OLEUM-NT-CHRIST 3/27 RPL INSS | 93K
LC | 125447146 | 021/436 | T2 EI COLGATE-PALERMO 021/436 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-02-07 | 2023-02-07 | 2023-11-02 | On-time | 2024-02-07 | 97 | 2024-02-07 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31662269 | T2 EI COLGATE-PALERMO 021/436 RPL POLE | 70Y
LC | 125494042 | 000/009 | T2 DI MUSTANG 0/9 RPR INSW | PISMOBCH | ETL.9091.INSL.NCER | 2023-02-13 | 2023-02-07 | 2023-09-13 | On-time | 2024-02-07 | 147 | 2024-02-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45978383 | T2 DI MUSTANG 0/9 RPR INSW | ICW
LC | 125494043 | 005/073 | T2 DI DIVIDE-CBRLLO #2 5/73 RMV VEG | PISMOBCH | ETL.1370.POLE.NWOD | 2023-02-13 | 2023-02-07 | 2023-07-05 | On-time | 2024-02-07 | 217 | 2024-02-07 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125494046 | 005/073 | T2 DI DIVIDE-CBRLLO #2 5/73 RPR SPLW | PISMOBCH | ETL.1370.INSL.NCER | 2023-02-13 | 2023-02-07 | 2023-07-05 | On-time | 2024-02-07 | 217 | 2024-02-07 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Steel | Repair | 45923464 | T2 DI DIVIDE-CBRLLO #2 5/73 RPR SPLW | ICS
LC | 125495539 | 005/071 | DI T2 DIVIDE CBRILO#2 5/71 RMV VEG | PISMOBCH | ETL.1370.POLE.WOOD | 2023-02-13 | 2023-02-07 | 2023-07-05 | On-time | 2024-02-07 | 217 | 2024-02-07 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Trim
LC | 125495599 | 005/071 | DI T2 DIVIDE CBRILO#2 5/071 RPR CRSW | PISMOBCH | ETL.1370.POLE.WOOD | 2023-02-13 | 2023-02-07 | 2023-07-05 | On-time | 2024-02-07 | 217 | 2024-02-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45947693 | DI T2 DIVIDE CBRILO#2 5/071 RPR CRSW | ICW
LC | 125497539 | 007/089 | T2 DI DIVIDE-CABRILLO #2 7/89 COMPLETE | PISMOBCH | ETL.1370.POLE.WOOD | 2023-02-14 | 2023-02-07 | 2023-07-06 | On-time | 2024-02-07 | 216 | 2024-02-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45917267 | T2 DI DIVIDE-CABRILLO #2 7/89 COMPLETE | ICW
LC | 125497766 | 018/210 | T2 DI IGNACIO-BLNS #2 018/210 COTTER | LAKEVLLE | ETL.7180.INSL.NCER | 2023-02-14 | 2023-02-07 | 2023-10-17 | On-time | 2024-02-07 | 113 | 2024-02-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45916364 | T2 DI IGNACIO-BLNS #2 018/210 COTTER | ICW
LC | 125494511 | 000/011 | T2 DI IGNCIO BLNAS#2 0/11 RPR IBWW | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-13 | 2023-02-06 |  | Late | 2024-02-06 |  | 2024-02-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Missing | Hardware-Wood | Install | 45914908 | T2 DI IGNCIO BLNAS#2 0/11 RPR IBWW | ICW
LC | 125497767 | 018/210 | T2 DI IGNACIO-BLNS #2 018/210 RPR JUMW | LAKEVLLE | ETL.7180.INSL.NCER | 2023-02-14 | 2023-02-07 | 2023-10-17 | On-time | 2024-02-07 | 113 | 2024-02-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45916364 | T2 DI IGNACIO-BLNS #2 018/210 COTTER | ICW
LC | 125497825 | 006/069 | T2 DI IGNACIO-BLNS #2 6/69 RPL INSW | LAKEVLLE | ETL.7180.INSL.CERA | 2023-02-14 | 2023-02-07 | 2023-09-30 | On-time | 2024-02-07 | 130 | 2024-02-07 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31662183 | T2 DI IGNACIO-BLNS #2 0/10 RPL INSW | 93I
LC | 125498796 | 019/091 | T2 DI TIDEWATER-SOBRANT 19/091 RPR SPLS | CONCORD | ETL.5770.INSL | 2023-02-14 | 2023-02-07 | 2023-08-29 | On-time | 2024-02-07 | 162 | 2024-02-07 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Steel | Repair | 45916231 | T2 DI TIDEWATER-SOBRANT 19/091 RPR SPLS | ICS
LC | 125499205 | 003/025 | T2 DI CBRLL-SNT YNZ SW STA 3/25 RPR GYWW | PISMOBCH | ETL.1200.POLE.NWOD | 2023-02-14 | 2023-02-07 | 2024-01-12 | On-time | 2024-02-07 | 26 | 2024-02-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46078509 | T2 DI CBRLL-SNT YNZ SW STA 3/25 RPR GYWW | ICW
LC | 125502779 | 011/135 | T2NT DI IGNACIO-BLNS #2 11/135 RPL DMPW | LAKEVLLE | ETL.7180.INSL.NCER | 2023-02-14 | 2023-02-07 | 2023-10-04 | On-time | 2024-02-07 | 126 | 2024-02-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 45916362 | T2NT DI IGNACIO-BLNS #2 11/135 RPL DMPW | ICW
LC | 125502838 | 001/012 | T2 DI IGNACIO-BLNS #2 1/12 RPR POLE | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-14 | 2023-02-07 | 2023-09-30 | On-time | 2024-02-07 | 130 | 2024-02-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45916361 | T2 DI IGNACIO-BLNS #2 1/12 RPR POLE | ICW
LC | 125505009 | 001/016 | T2 DI IGNACIO-BLNS #1 1/16 RPR INSW | LAKEVLLE | ETL.7140.INSL.NCER | 2023-02-15 | 2023-02-07 | 2023-05-04 | On-time | 2024-02-07 | 279 | 2024-02-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45825431 | T2 DI IGNACIO-BLNS #1 1/16 RPR INSW | ICW
LC | 125505027 | 002/018 | T2 DI CBRLO SNTA YNZ SWSTA 2/18 RPR GYWW | PISMOBCH | ETL.1200.POLE.NWOD | 2023-02-15 | 2023-02-07 | 2024-01-12 | On-time | 2024-02-07 | 26 | 2024-02-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46078508 | T2 DI CBRLO SNTA YNZ SWSTA 2/18 RPR GYWW | ICW
LC | 125505100 | 001/016 | T2 DI IGNACIO-BLNS #1 1/16 RPR CONN CMT | LAKEVLLE | ETL.7140.INSL.NCER | 2023-02-15 | 2023-02-07 | 2023-05-04 | On-time | 2024-02-07 | 279 | 2023-05-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45690393 | T2 DI IGNACIO-BLNS #1 1/16 RPR CONN | ICM
LC | 125516908 | 007/089 | T2 DI DIVIDE-CABRILL #2 7/89 COMPLETE | PISMOBCH | ETL.1370.POLE.WOOD | 2023-02-16 | 2023-02-07 | 2023-07-06 | On-time | 2024-02-07 | 216 | 2024-02-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45923461 | T2 DI DIVIDE-CABRILL #2 7/89 COMPLETE | ICW
LC | 125449295 | 001/033 | T2 EI PALERMO-OROVILLE #1 01/33 CLR VEG | TABLEMTN | ETL.7730.POLE.WOOD | 2023-02-08 | 2023-02-08 | 2023-08-16 | On-time | 2024-02-08 | 176 | 2024-02-08 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125449304 | 001/033 | T2 EI PALERMO-ORVLLE #1 1/33 RPR INSW | TABLEMTN | ETL.7730.INSL | 2023-02-08 | 2023-02-08 | 2023-10-24 | On-time | 2024-02-08 | 107 | 2024-02-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45698330 | T2 EI PALERMO-ORVLLE #1 1/33 RPR INSW | ICW
LC | 125449764 | 002/048-GUY | T2 EI VOLTA-SOUTH 002/048 RPL GYPL | TABLEMTN | ETL.8300.POLE.WOOD | 2023-02-08 | 2023-02-08 | 2023-12-11 | On-time | 2024-02-08 | 59 | 2024-02-08 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Guy Pole-Wood | Replace | 31662273 | T2 EI VOLTA-SOUTH 002/048 RPL GYPL | 70Y
LC | 125498267 | 006/072 | T2 EI COLGATE-SMARTVILLE #2 6/72 RPL STR | SACTO | ETL.6520.POLE.WOOD | 2023-02-14 | 2023-02-14 | 2024-04-30 | Late | 2024-02-14 | -76 | 2024-02-14 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481575 | T2 EI COLGATE-SMARTVILLE #2 6/72 RPL STR | 70Y
LC | 125450045 | 004/100 | T2 EI VOLTA-SOUTH 004/100 RPL POLE | TABLEMTN | ETL.8300.POLE.WOOD | 2023-02-08 | 2023-02-08 | 2023-12-10 | On-time | 2024-02-08 | 60 | 2024-02-08 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31662274 | T2 EI VOLTA-SOUTH 004/100 RPL POLE | 70Y
LC | 125450302 | 029/007 | T2 EI RIO DELL JCT-BRIDGEV 29/7 RPL POLE | EUREKA | ETL.7850.POLE.WOOD | 2023-02-08 | 2023-02-08 | 2023-12-12 | On-time | 2024-02-08 | 58 | 2024-02-08 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31662272 | T2 EI RIO DELL JCT-BRIDGEV 29/7 RPL POLE | 70Y
LC | 125499808 | 018/205 | T2 DI IGNACIO-BLNS #2 18/205 RPR GYWW | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-14 | 2023-02-07 |  | Late | 2024-02-07 |  | 2024-02-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45916363 | T2 DI IGNACIO-BLNS #2 18/205 RPR GYWW | ICW
LC | 125499930 | 005/005 | T2 EI MENDOCINO-HARTLEY 5/5 COMPLETE | WILLITS | ETL.7510.POLE.WOOD | 2023-02-14 | 2023-02-14 | 2024-02-15 | Late | 2024-02-14 | -1 | 2024-02-14 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663438 | T2 EI MENDOCINO-HARTLEY 5/5 RPL POLE | 70Y
LC | 125500043 | 018/205 | T2 DI IGNACIO-BLNS #2 18/205 COTTER | LAKEVLLE | ETL.7180.INSL.NCER | 2023-02-14 | 2023-02-07 |  | Late | 2024-02-07 |  | 2023-08-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45916363 | T2 DI IGNACIO-BLNS #2 18/205 RPR GYWW | ICW
LC | 125451007 | 021/431 | T2 EI COLGATE-PALERMO 21/431 RPR GYWW | SACTO | ETL.6500.POLE.WOOD | 2023-02-08 | 2023-02-08 | 2023-08-25 | On-time | 2024-02-08 | 167 | 2024-02-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45916356 | T2 EI COLGATE-PALERMO 21/431 RPR GYWW | ICW
LC | 125501476 | 003/035 | T2 EI PIT #3-PIT #1 3/35 RPL INSS | TABLEMTN | ETL.5400.INSL.NCER | 2023-02-14 | 2023-02-14 |  | Late | 2024-02-14 |  | 2024-02-14 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31664293 | T2 EI PIT #3-PIT #1 3/35 RPL INSS | 93K
LC | 125501778 | 019/120 | T2 DI SL BSP-OCEANO 19/120 RMV VEG | PISMOBCH | ETL.3530.POLE.WOOD | 2023-02-14 | 2023-02-07 | 2024-02-12 | Late | 2024-02-07 | -5 | 2024-02-07 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125451236 | 004/005 | T2 EI MENDOCINO-HARTLEY 4/5 RPL POLE | WILLITS | ETL.7510.POLE.WOOD | 2023-02-08 | 2023-02-08 | 2023-09-20 | On-time | 2024-02-08 | 141 | 2024-02-08 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31662271 | T2 EI MENDOCINO-HARTLEY 4/5 RPL POLE | 70Y
LC | 125502723 | 019/378 | T2 EI COLGATE-PALERMO 19/378 RMV ENCRCH | TABLEMTN | ETL.6500.POLE.NWOD | 2023-02-14 | 2023-02-14 |  | Late | 2024-02-14 |  | 2024-02-14 | 931 | TLS | INSP | E - Schd Compl Yr 0 | Open | TR2 | Encroachment | Right of Way | Remove
LC | 125451474 | 004/006 | T2 EI MENDOCINO-HARTLY-WOOD 4/6 RPL POLE | WILLITS | ETL.7510.POLE.WDPS | 2023-02-08 | 2023-02-08 | 2023-09-21 | On-time | 2024-02-08 | 140 | 2024-02-08 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31662271 | T2 EI MENDOCINO-HARTLEY 4/5 RPL POLE | 70Y
LC | 125451615 | 112/003 | T2 EI HUMBOLDT-BRIDGEVLL 112/3R RPR GYWW | EUREKA | ETL.1810.POLE.STPS | 2023-02-08 | 2023-02-08 | 2023-11-03 | On-time | 2024-02-08 | 97 | 2024-02-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45916565 | T2 EI HUMBOLDT-BRIDGEVLL 112/3R RPR GYWW | ICW
LC | 125451705 | 112/003 | T2 EI HUMBOLDT-BRIDGEVIL 112/3C RPR GYWW | EUREKA | ETL.1810.POLE.STPS | 2023-02-08 | 2023-02-08 | 2023-11-03 | On-time | 2024-02-08 | 97 | 2024-02-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45916565 | T2 EI HUMBOLDT-BRIDGEVLL 112/3R RPR GYWW | ICW
LC | 125504891 | 019/126 | T2 DI OCNO CLNDR SW STA 19/126 RPL INSW | PISMOBCH | ETL.2394.INSL.CERA | 2023-02-15 | 2023-02-07 |  | Late | 2024-02-07 |  | 2024-02-07 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35489957 | T2 DI OCEANO-CLLNDR 019/123A RPL INSW | 93I
LC | 125452124 | 112/003 | T2 EI HUMBOLDT-BRDGVILL 112/3L RMV VEG | EUREKA | ETL.1810.POLE.STPS | 2023-02-08 | 2023-02-08 | 2023-06-21 | On-time | 2024-02-08 | 232 | 2024-02-08 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125452131 | 112/003 | T2 EI HUMBOLDT-BRIDGEVIL 112/3L RPR GYWW | EUREKA | ETL.1810.POLE.STPS | 2023-02-08 | 2023-02-08 | 2023-11-03 | On-time | 2024-02-08 | 97 | 2024-02-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45916565 | T2 EI HUMBOLDT-BRIDGEVLL 112/3R RPR GYWW | ICW
LC | 125505405 | 020/006 | T2 DI CLR LAKE-KONOCTI 20/6 RPR INSW | WILLITS | ETL.6852.INSL.NCER | 2023-02-15 | 2023-02-08 | 2023-09-26 | On-time | 2024-02-08 | 135 | 2024-02-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45916566 | T2 DI CLR LAKE-KONOCTI 20/6 RPR INSW | ICW
LC | 125505104 | 031/260 | T2 DI BRDGVLLE-CTTNWD 31/260L RPL ANCRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-02-15 | 2023-02-08 |  | Late | 2024-02-08 |  | 2024-02-08 | 637 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35506980 | T2 DI BRDGVLLE-CTTNWD 31/260L RPL ANCRW | 93E
LC | 125505985 | 033/268 | T2 DI BRIDGEVILLE COTTONWD 33/268 COTTER | TABLEMTN | ETL.1110.INSL.CERA | 2023-02-15 | 2023-02-08 | 2023-08-25 | On-time | 2024-02-08 | 167 | 2024-02-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45698328 | T2 DI BRIDGEVILLE COTTONWD 33/268 COTTER | ICW
LC | 125506494 | 010/083 | T2 DI CABRILLO-SANTA YNEZ 10/83 RPR GYWW | PISMOBCH | ETL.1200.POLE.NWOD | 2023-02-15 | 2023-02-08 | 2024-01-30 | On-time | 2024-02-08 | 9 | 2024-02-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46078511 | T2 DI CABRILLO-SANTA YNEZ 10/83 RPR GYWW | ICW
LC | 125505884 | 019/123A | T2 DI OCEANO-CLLNDR SS 019/123A RPL INSW | PISMOBCH | ETL.2394.INSL.NCER | 2023-02-15 | 2023-02-07 |  | Late | 2024-02-07 |  | 2024-02-07 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35489957 | T2 DI OCEANO-CLLNDR 019/123A RPL INSW | 93I
LC | 125507906 | 003/045 | T2 DI DIVIDW CBRILO#1 3/045 RPR GYWW | PISMOBCH | ETL.1380.POLE.WOOD | 2023-02-15 | 2023-02-08 | 2024-01-12 | On-time | 2024-02-08 | 27 | 2024-02-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088403 | T2 DI DIVIDW CBRILO#1 3/045 RPR GYWW | ICW
LC | 125508103 | 021/098 | T2 DI SN LS OBPO-SNTA MRA 21/98 RPL DMPS | PISMOBCH | ETL.3540.INSL.CERA | 2023-02-15 | 2023-02-08 | 2024-01-08 | On-time | 2024-02-08 | 31 | 2024-02-08 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 46078398 | T2 DI SN LS OBPO-SNTA MRA 21/98 RPL DMPS | ICS
LC | 125506218 | 030/257 | T2 DI BRDGVLLE-CTTNWD 30/257L RPL HRDW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-02-15 | 2023-02-08 |  | Late | 2024-02-08 |  | 2024-02-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46246506 | T2 DI BRDGVLLE-CTTNWD 30/257L RPL HRDW | ICW
LC | 125508749 | 010/090 | T2 DI CBRLO STA YNZ SS 010/090 INF ENG | PISMOBCH | ETL.1200.POLE.NWOD | 2023-02-15 | 2023-02-08 | 2023-04-27 | On-time | 2024-02-08 | 287 | 2023-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45691719 | T2 DI CBRLO STA YNZ SS 010/090 INF ENG | ICW
LC | 125511848 | 000/016 | T2 DI JEFRSN STNFRD 0/16 RPR ADSS | METCALF | ETL.7220.POLE.WOOD | 2023-02-16 | 2023-02-08 | 2023-10-24 | On-time | 2024-02-08 | 107 | 2024-02-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45916570 | T2 DI JEFRSN STNFRD 0/16 RPR ADSS | ICW
LC | 125511984 | 017/076 | T2 DI CLNDR SWSTA MESA 17/076 RMV NEST | PISMOBCH | ETL.1210.TOWR | 2023-02-16 | 2023-02-08 | 2024-01-11 | On-time | 2024-02-08 | 28 | 2024-02-08 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 45945126 | T2 DI CLNDR SWSTA MESA 17/076 RMV NEST | ICS
LC | 125512541 | 002/035 | T2 DI GOLDTREE TAP 002/035 RPL INSLW | PISMOBCH | ETL.2821.INSL | 2023-02-16 | 2023-02-08 | 2023-06-13 | On-time | 2024-02-08 | 240 | 2024-02-08 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31618255 | T2 DI GOLDTREE TAP 0/2 RPL INSW | 93I
LC | 125513680 | 011/063 | T2 DI MRO BY-SL OBSPO #2 11/63 RPR INSS | PISMOBCH | ETL.2820.INSL | 2023-02-16 | 2023-02-08 | 2024-01-12 | On-time | 2024-02-08 | 27 | 2024-02-08 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46078502 | T2 DI MRO BY-SL OBSPO #2 11/63 RPR INSS | ICS
LC | 125520524 | 020/097 | T2 DI SN LS OBPO-SNTA MRA 20/97 RPL INSS | PISMOBCH | ETL.3540.INSL.CERA | 2023-02-17 | 2023-02-08 | 2024-01-08 | On-time | 2024-02-08 | 31 | 2024-02-08 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31663734 | T2 DI SLO-SANTA MARIA 21/100 RPL INSS | 93K
LC | 125520604 | 019/006 | T2 DI CLR LK KNOCTI 19/006 RPR STRW | WILLITS | ETL.6852.POLE.NWOD | 2023-02-17 | 2023-02-08 | 2023-09-25 | On-time | 2024-02-08 | 136 | 2024-02-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45916567 | T2 DI CLR LK KNOCTI 19/006 RPR STRW | ICW
LC | 125508008 | 000/004 | T2 EI MORRO BAY-SOLAR SS #2 0/4 RPR INSS | PISMOBCH | ETL.5310.INSL.NCER | 2023-02-15 | 2023-02-15 | 2024-05-10 | Late | 2024-02-15 | -85 | 2024-02-15 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45945138 | T2 EI MORRO BAY-SOLAR SS #2 0/4 RPR INSS | ICS
LC | 125521056 | 003/046 | T2 DI DIVIDE-CBRLLO #1 3/46 RPR STRW | PISMOBCH | ETL.1380.POLE.WOOD | 2023-02-17 | 2023-02-08 | 2024-01-12 | On-time | 2024-02-08 | 27 | 2024-02-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088404 | T2 DI DIVIDE-CBRLLO #1 3/46 RPR STRW | ICW
LC | 125508253 | 022/171 | T2 DI OCNO-CLNDR SW STA 22/171 RPL INSW | PISMOBCH | ETL.2394.INSL.CERA | 2023-02-15 | 2023-02-07 |  | Late | 2024-02-07 |  | 2024-02-07 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35489957 | T2 DI OCEANO-CLLNDR 019/123A RPL INSW | 93I
LC | 125508288 | 004/012 | T2 TRINITY-MAPLE CREEK 4/012 CLEARANCE | EUREKA | ETL.8170.POLE.WOOD | 2023-02-15 | 2023-02-15 |  | Late | 2024-02-15 |  | 2024-02-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31639069 | T2 TRINITY-MAPLE CREEK 4/012 CLEARANCE | 93G
LC | 125522127 | 002/050 | T2 DI JFRSN STNFRD 2/50 RPR ADSS | METCALF | ETL.7220.POLE.WOOD | 2023-02-17 | 2023-02-08 | 2023-09-14 | On-time | 2024-02-08 | 147 | 2024-02-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45916572 | T2 DI JFRSN STNFRD 2/50 RPR ADSS | ICW
LC | 125508471 | 018/376 | T2 EI COLGATE-PALERMO 18/376 RMV ENCRCH | TABLEMTN | ETL.6500.POLE.NWOD | 2023-02-15 | 2023-02-15 |  | Late | 2024-02-15 |  | 2024-02-15 | 931 | TLS | INSP | E - Schd Compl Yr 0 | Open | TR2 | Encroachment | Right of Way | Remove
LC | 125522712 | 002/019 | T2 DI CBRLLO-SNT YNZ 2/19 RPR STRW | PISMOBCH | ETL.1200.POLE.NWOD | 2023-02-17 | 2023-02-08 | 2024-01-12 | On-time | 2024-02-08 | 27 | 2024-02-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46078510 | T2 DI CBRLLO-SNT YNZ 2/19 RPR STRW | ICW
LC | 125524042 | 020/094 | T2 DI SN LS OBPO-SNTA MRA 20/94 RPL DMPS | PISMOBCH | ETL.3540.INSL.CERA | 2023-02-17 | 2023-02-08 | 2024-01-08 | On-time | 2024-02-08 | 31 | 2024-02-08 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 45945160 | T2 DI SN LS OBPO-SNTA MRA 20/94 RPL DMPS | ICS
LC | 125508767 | 003/008 | T2 CLEAR LAKE-HOPLAND 3/8 GO95 CLEAR | WILLITS | ETL.6390.POLE.NWOD | 2023-02-15 | 2023-02-15 |  | Late | 2024-02-15 |  | 2023-08-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640195 | T2 CLEAR LAKE-HOPLAND 3/8 GO95 CLEAR | 93G
LC | 125524732 | 002/051 | T2 DI JFFRSN-STNFRD 2/51 INS HRDD | METCALF | ETL.7220.POLE.WOOD | 2023-02-17 | 2023-02-08 | 2023-11-06 | On-time | 2024-02-08 | 94 | 2024-02-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45916573 | T2 DI JFFRSN-STNFRD 2/51 INS HRDD | ICW
LC | 125524768 | 004/023 | T2 DI MRR-BY-SL BSP #1 4/23 INS HRDT | PISMOBCH | ETL.2810.TOWR | 2023-02-17 | 2023-02-08 | 2024-01-26 | On-time | 2024-02-08 | 13 | 2024-02-08 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Tower | Install | 45943353 | T2 DI MRR-BY-SL BSP #1 4/23 INS HRDT | ICQ
LC | 125524823 | 002/053 | T2 DI JFFRSN-STNFRD 2/53 ANTI-SPLIT | METCALF | ETL.7220.POLE.WOOD | 2023-02-17 | 2023-02-08 | 2023-11-11 | On-time | 2024-02-08 | 89 | 2024-02-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45916574 | T2 DI JFFRSN-STNFRD 2/53 ANTI-SPLIT | ICW
LC | 125508900 | 005/004 | T2 MENDOCINO-WILLITS 5/4 GO95 CLEARANCE | WILLITS | ETL.7540.POLE.NWOD | 2023-02-15 | 2023-02-15 |  | Late | 2024-02-15 |  | 2024-02-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640261 | MENDOCINO-WILLITS 1/005 CLEARANCE | 93G
LC | 125525608 | 002/061 | T2 DI JEFFERSON-STNFRD 2/61 RPR STRW | METCALF | ETL.7220.POLE.WOOD | 2023-02-18 | 2023-02-08 | 2023-11-11 | On-time | 2024-02-08 | 89 | 2024-02-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45916575 | T2 DI JEFFERSON-STNFRD 2/61 RPR STRW | ICW
LC | 125525732 | 002/058 | T2 DI JEFFERSON-STNFRD 2/58 COMPLETED | METCALF | ETL.7220.POLE.WOOD | 2023-02-18 | 2023-02-08 | 2023-11-08 | On-time | 2024-02-08 | 92 | 2024-02-08 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663837 | T2 DI JEFFERSON-STNFRD 2/58 RPL POLE | 70Y
LC | 125509425 | 004/063 | T2 DI DIVIDE-CABRILLO #1 04/063 RPL POLE | PISMOBCH | ETL.1380.POLE.WOOD | 2023-02-15 | 2023-02-07 | 2024-06-20 | Late | 2024-02-07 | -134 | 2024-02-07 | 372T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483504 | T2 DI DIVIDE-CBRLLO #1 5/72 RPL STRW | 70Y
LC | 125509567 | 013/113 | T2 DI CBRLO STA YNZ SWSTA 13/113 RMV VEG | PISMOBCH | ETL.1200.POLE.NWOD | 2023-02-15 | 2023-02-08 | 2024-02-29 | Late | 2024-02-08 | -21 | 2024-02-08 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125469132 | 002/065 | T2 EI COTTONWOOD-BENTON #1 2/65 RPL POLE | TABLEMTN | ETL.6640.POLE.WOOD | 2023-02-09 | 2023-02-09 | 2023-12-15 | On-time | 2024-02-09 | 56 | 2024-02-09 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31655547 | T2 DI COTTON-BENTON #1 7/182 RPL POLE | 70Y
LC | 125469493 | 002/064 | T2 EI COTTONWOOD-BENTON #1 2/64 RPL POLE | TABLEMTN | ETL.6640.POLE.WOOD | 2023-02-09 | 2023-02-09 | 2023-12-15 | On-time | 2024-02-09 | 56 | 2024-02-09 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31655547 | T2 DI COTTON-BENTON #1 7/182 RPL POLE | 70Y
LC | 125522240 | 024/211 | T2 DI CSCDE CTTNWD 024/211 RPR SHLW | TABLEMTN | ETL.1240.POLE.STPS | 2023-02-17 | 2023-02-09 | 2023-12-03 | On-time | 2024-02-09 | 68 | 2024-02-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45698623 | T2 DI CSCDE CTTNWD 024/211 RPR SHLW | ICW
LC | 125522244 | 024/211 | T2 DI CSCDE CTTNWD 24/211 RPR INSW | TABLEMTN | ETL.1240.INSL.CERA | 2023-02-17 | 2023-02-09 | 2023-12-03 | On-time | 2024-02-09 | 68 | 2024-02-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45698597 | T2 DI CSCDE CTTNWD 24/211 RPR INSW | ICW
LC | 125524125 | 014/065 | T2 DI SLO-SANTA MARIA 014/065 COTTER | PISMOBCH | ETL.3540.INSL.CERA | 2023-02-17 | 2023-02-09 | 2024-01-10 | On-time | 2024-02-09 | 30 | 2024-02-09 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45945127 | T2 DI SLO-SANTA MARIA 014/065 COTTER | ICS
LC | 125524710 | 000/014 | T2 DI JFFRSN-STNFRD 0/14 COTTER | METCALF | ETL.7220.INSL.CERA | 2023-02-17 | 2023-02-09 | 2023-11-06 | On-time | 2024-02-09 | 95 | 2024-02-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45916576 | T2 DI JFFRSN-STNFRD 0/14 COTTER | ICW
LC | 125524890 | 007/035 | T2 DI SLO-SANTA MARIA 007/035 RPL DMPS | PISMOBCH | ETL.3540.INSL.CERA | 2023-02-17 | 2023-02-09 | 2024-01-10 | On-time | 2024-02-09 | 30 | 2024-02-09 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 45945161 | T2 DI SLO-SANTA MARIA 007/035 RPL DMPS | ICS
LC | 125524891 | 001/001 | T2 DI MNDCNO-HRTLY 1/1 RPR GYWW | WILLITS | ETL.7510.POLE.NWOD | 2023-02-17 | 2023-02-09 | 2023-08-23 | On-time | 2024-02-09 | 170 | 2024-02-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45917350 | T2 DI MNDCNO-HRTLY 1/1 RPR GYWW | ICW
LC | 125525449 | 014/135 | T2 DI SNLUS OBPO CYUCS 14/135 ANTI SPLIT | PISMOBCH | ETL.9090.POLE.WOOD | 2023-02-18 | 2023-02-09 | 2024-01-10 | On-time | 2024-02-09 | 30 | 2024-02-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088307 | T2 DI SNLUS OBPO CYUCS 14/135 ANTI SPLIT | ICW
LC | 125515196 | 001/010 | T2 EI PIT #3-PIT #1 1/10 RPR INSS | TABLEMTN | ETL.5400.INSL.NCER | 2023-02-16 | 2023-02-16 |  | Late | 2024-02-16 |  | 2024-02-16 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45698632 | T2 EI PIT #3-PIT #1 1/10 RPR INSS | ICS
LC | 125525495 | 001/024 | T2 DI ATSCDR-SL BSP 1/24 RPR GYWW | PISMOBCH | ETL.8490.POLE.NWOD | 2023-02-18 | 2023-02-09 | 2024-01-27 | On-time | 2024-02-09 | 13 | 2024-02-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088406 | T2 DI ATSCDR-SL BSP 1/24 RPR GYWW | ICW
LC | 125525569 | 000/005 | T2 DI MRO BY SNLUS OBSPO#1 0/5 RPR OPGW | PISMOBCH | ETL.2810.TOWR | 2023-02-18 | 2023-02-09 | 2023-12-28 | On-time | 2024-02-09 | 43 | 2024-02-09 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45945162 | T2 DI MRO BY SNLUS OBSPO#1 0/5 RPR OPGW | ICS
LC | 125525764 | 000/011 | T2 DI MESA SISQUOC 0/011 RPL INSW | PISMOBCH | ETL.2460.INSL | 2023-02-18 | 2023-02-09 | 2024-01-26 | On-time | 2024-02-09 | 14 | 2024-02-09 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35486637 | T2 DI MESA SISQUOC 0/011 RPL INSW | 93I
LC | 125525781 | 033/271 | T2 DI BRDGVLLE-CTTNWD 33/271 RPR INSW | TABLEMTN | ETL.1110.INSL.NCER | 2023-02-18 | 2023-02-09 | 2023-08-30 | On-time | 2024-02-09 | 163 | 2024-02-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45698629 | T2 DI BRDGVLLE-CTTNWD 33/271 RPR INSW | ICW
LC | 125525788 | 002/048 | T2 DI JEFFERSON-STANFORD 02/48 RPR ADSS | METCALF | ETL.7220.POLE.WOOD | 2023-02-18 | 2023-02-09 | 2023-09-16 | On-time | 2024-02-09 | 146 | 2024-02-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45916577 | T2 DI JEFFERSON-STANFORD 02/48 RPR ADSS | ICW
LC | 125525963 | 004/028 | T2 DI MOR BY SNLUS OBSPO#2 4/028 RPL INS | PISMOBCH | ETL.2820.INSL | 2023-02-18 | 2023-02-09 | 2024-01-12 | On-time | 2024-02-09 | 28 | 2024-02-09 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31662930 | T2 DI MOR BY SNLUS OBSPO#2 4/028 RPL INS | 93K
LC | 125526011 | 037/320 | T2 DI CASCADE-CTTNWD 37/320R RPR OPGW | TABLEMTN | ETL.1240.POLE.WDPS | 2023-02-18 | 2023-02-09 | 2023-03-20 | On-time | 2024-02-09 | 326 | 2023-08-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45686649 | T2 DI CASCADE-CTTNWD 37/320R RPR OPGW | ICW
LC | 125526034 | 000/019 | T2 DI JFFRSN-STNFRD 0/19 RPR ADSS | METCALF | ETL.7220.POLE.WOOD | 2023-02-18 | 2023-02-09 | 2023-03-06 | On-time | 2024-02-09 | 340 | 2023-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45686552 | T2 DI JFFRSN-STNFRD 0/19 RPR ADSS | ICW
LC | 125526037 | 033/272 | T2 DI BRDGVLLE-CTTNWD 33/272R RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-02-18 | 2023-02-09 | 2023-03-24 | On-time | 2024-02-09 | 322 | 2023-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698583 | T2 DI BRDGVLLE-CTTNWD 33/272R RPR GYWW | ICW
LC | 125532111 | 018/109 | T2 DI SNLUS OSPO OCNO 18/109 RPL INSW | PISMOBCH | ETL.3530.INSL.CERA | 2023-02-21 | 2023-02-09 | 2023-05-22 | On-time | 2024-02-09 | 263 | 2024-02-09 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35542716 | T2 DI SNLUS OSPO OCNO 18/109 RPL INSW | 93I
LC | 125516781 | 013/160 | T2 DI IGNACIO-BLNS #2 13/160R RPR INSW | LAKEVLLE | ETL.7180.INSL.NCER | 2023-02-16 | 2023-02-03 |  | Late | 2024-02-03 |  | 2024-02-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45910129 | T2 DI IGNACIO-BLNS #2 13/160R RPR INSW | ICW
LC | 125516784 | 013/160 | T2 DI IGNACIO-BLNS #2 13/160C RPR JMPW | LAKEVLLE | ETL.7180.INSL.NCER | 2023-02-16 | 2023-02-03 |  | Late | 2024-02-03 |  | 2024-02-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45910129 | T2 DI IGNACIO-BLNS #2 13/160R RPR INSW | ICW
LC | 125516813 | 021/153 | T2 DI OCNO-CLNDR SW STA 21/153 RPR GYWW | PISMOBCH | ETL.2394.POLE.WOOD | 2023-02-16 | 2023-02-07 |  | Late | 2024-02-07 |  | 2024-02-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46078602 | T2 DI OCNO CLNDR SWSTA 21/153 RPR GYWW | ICW
LC | 125532304 | 000/009 | T2 DI MENDOCINO-HRTLY 0/9 RMV VEG | WILLITS | ETL.7510.POLE.NWOD | 2023-02-21 | 2023-02-09 | 2023-08-28 | On-time | 2024-02-09 | 165 | 2024-02-09 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125532500 | 036/316 | T2 DI CSCDE CTTNWD 36/316L RPL STRW | TABLEMTN | ETL.1240.POLE.WDPS | 2023-02-21 | 2023-02-09 | 2023-11-15 | On-time | 2024-02-09 | 86 | 2024-02-09 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31658935 | T2 DI CASCDE CTTNWD 024/209L RPL STRW | 70Y
LC | 125516858 | 001/009 | T2 DI SANTA YNEZ TAP 001/009 RPL DAMW | PISMOBCH | ETL.3701.INSL.CERA | 2023-02-16 | 2023-02-07 | 2024-03-06 | Late | 2024-02-07 | -28 | 2024-02-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46078973 | T2 DI SANTA YNEZ 001/009 RPL DAMW | ICW
LC | 125532502 | 036/316 | T2 DI CSCDE CTTNWD 36/316R RPL STRW | TABLEMTN | ETL.1240.POLE.WDPS | 2023-02-21 | 2023-02-09 | 2023-11-17 | On-time | 2024-02-09 | 84 | 2024-02-09 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31658935 | T2 DI CASCDE CTTNWD 024/209L RPL STRW | 70Y
LC | 125519996 | 019/119 | T2 DI SN LS OBPO OCNO 019/119 RMV VEG | PISMOBCH | ETL.3530.POLE.WOOD | 2023-02-17 | 2023-02-07 | 2024-02-12 | Late | 2024-02-07 | -5 | 2024-02-07 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125532637 | 021/100 | T2 DI SLO-SANTA MARIA 21/100 RPL INSS | PISMOBCH | ETL.3540.INSL.CERA | 2023-02-21 | 2023-02-09 | 2024-01-09 | On-time | 2024-02-09 | 31 | 2024-02-09 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31663734 | T2 DI SLO-SANTA MARIA 21/100 RPL INSS | 93K
LC | 125533022 | A006/081 | T2 DI IGNACIO-BLNS #2 A6/81 RPR IBWW | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-21 | 2023-02-09 | 2023-10-06 | On-time | 2024-02-09 | 126 | 2024-02-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45916365 | T2 DI IGNACIO-BLNS #2 A6/81 RPR IBWW | ICW
LC | 125533683 | 009/044 | T2 DI SLO-SANTA MARIA 009/044 RPL DAMS | PISMOBCH | ETL.3540.INSL.CERA | 2023-02-21 | 2023-02-09 | 2024-01-09 | On-time | 2024-02-09 | 31 | 2024-02-09 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 45945163 | T2 DI SLO-SANTA MARIA 009/044 RPL DAMS | ICS
LC | 125533936 | 034/275 | T2 DI BRDVIL CTTNWD 34/275 RPR SHLS | TABLEMTN | ETL.1110.TOWR | 2023-02-21 | 2023-02-09 | 2023-11-06 | On-time | 2024-02-09 | 95 | 2024-02-09 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45698326 | T2 DI BRDVIL CTTNWD 34/275 RPR SHLS | ICS
LC | 125534069 | 009/067 | T2 DI SN LS BSP-CAYUCOS 9/67 RPR JUMW | PISMOBCH | ETL.9090.INSL | 2023-02-21 | 2023-02-09 | 2024-01-11 | On-time | 2024-02-09 | 29 | 2024-02-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46088309 | T2 DI SN LS BSP-CAYUCOS 9/67 RPR JUMW | ICW
LC | 125535444 | 014/099 | T2 DI CAYUCOS-CAMBRIA 14/99 RPL HRDD | PISMOBCH | ETL.8560.INSL.NCER | 2023-02-21 | 2023-02-09 | 2024-01-14 | On-time | 2024-02-09 | 26 | 2024-02-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46088462 | T2 DI CAYUCOS-CAMBRIA 14/99 RPL HRDD | ICW
LC | 125485904 | 015/109 | T2 ELECTRA-BELLOTA 15/109 INS ACG | VICTOR | ETL.4670.TOWR | 2023-02-10 | 2023-02-10 | 2023-08-22 | On-time | 2024-02-10 | 172 | 2024-02-10 | 988 | TLQ | CREW | E - Schd Compl Yr 0 | Closed | TR2 | Anti-Climbing Guard | Structure-Tower | Install | 31662376 | T2 ELECTRA-BELLOTA 15/109 INS ACG | 93A
LC | 125486015 | 010/165 | T2 EI TEJON-LEBEC 10/165 RPL HRDW | MIDWAY | ETL.9250.POLE.WOOD | 2023-02-10 | 2023-02-10 | 2023-10-22 | On-time | 2024-02-10 | 111 | 2024-02-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45996697 | T2 EI TEJON-LEBEC 10/165 RPL HRDW | ICW
LC | 125487781 | 037/220 | T2NT EI INDAN FLAT-YOSMTE 37/220 BNT STL | FRESNO | ETL.1112.POLE.NWOD | 2023-02-10 | 2023-02-10 | 2023-12-11 | On-time | 2024-02-10 | 61 | 2024-02-10 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45928044 | T2NT EI INDAN FLAT-YOSMTE 37/220 BNT STL | ICQ
LC | 125528647 |  | T2 CRAG VW-CASCADE 115KV 0011/100 INS RD | TABLEMTN | ETL.1350 | 2023-02-19 | 2023-02-10 | 2023-09-08 | On-time | 2024-02-10 | 155 | 2024-02-10 | 374 | TLR | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Road | Install | 31644615 | T2 CRAG VW-CASCADE 115KV 0011/100 INS RD | 71Y
LC | 125522246 | 024/211 | T2 DI CSCDE CTTNWD 24/211 RPR STRW | TABLEMTN | ETL.1240.POLE.STPS | 2023-02-17 | 2023-02-09 |  | Late | 2024-02-09 |  | 2024-02-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46269258 | T2 DI CSCDE CTTNWD 24/211 RPR STRW | ICW
LC | 125522247 | 000/002 | T2 DI LWR LK HMSTKE 0/002 RPR GYWW | WILLITS | ETL.1481.POLE.WOOD | 2023-02-17 | 2023-02-08 |  | Late | 2024-02-08 |  | 2024-02-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45916568 | T2 DI LWR LK HMSTKE 0/002 RPR GYWW | ICW
LC | 125532961 | 012/108 | T2 DI SL BSP-CAYUCOS 12/108 RPL HRDD | PISMOBCH | ETL.9090.POLE.WOOD | 2023-02-21 | 2023-02-10 | 2024-01-10 | On-time | 2024-02-10 | 31 | 2024-02-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46088308 | T2 DI SL BSP-CAYUCOS 12/108 RPL HRDD | ICW
LC | 125523608 | 007/063 | T2 DI CBRLLO-SNT YNZ 007/063 CNCL | PISMOBCH | ETL.1200.POLE.NWOD | 2023-02-17 | 2023-02-08 | 2024-02-29 | Late | 2024-02-08 | -21 | 2024-02-08 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125523683 | 006/086 | T2 DI DIVIDE-CBRLO #1 6/86 RPL POLE | PISMOBCH | ETL.1380.POLE.WOOD | 2023-02-17 | 2023-02-09 | 2024-06-19 | Late | 2024-02-09 | -131 | 2024-02-09 | 372T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483504 | T2 DI DIVIDE-CBRLLO #1 5/72 RPL STRW | 70Y
LC | 125523687 | 006/075 | T2 DI GRN VLLY-CMP EVRS 6/75L RPL STRW | MOSSLNDG | ETL.1710.POLE.WDPS | 2023-02-17 | 2023-02-15 | 2024-03-30 | Late | 2024-02-15 | -44 | 2024-02-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35524020 | T2 DI GRN VLLY-CMP EVRS 6/75L RPL STRW | 70Y
LC | 125523688 | 006/075 | T2 DI GRN VLLY-CMP EVRS 6/75C RPL STRW | MOSSLNDG | ETL.1710.POLE.WDPS | 2023-02-17 | 2023-02-15 | 2024-03-30 | Late | 2024-02-15 | -44 | 2024-02-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35524020 | T2 DI GRN VLLY-CMP EVRS 6/75L RPL STRW | 70Y
LC | 125523797 | 006/075 | T2 DI GRN VLLY-CMP EVRS 6/75R RPL STRW | MOSSLNDG | ETL.1710.POLE.WDPS | 2023-02-17 | 2023-02-15 | 2024-03-30 | Late | 2024-02-15 | -44 | 2024-02-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35524020 | T2 DI GRN VLLY-CMP EVRS 6/75L RPL STRW | 70Y
LC | 125533003 | 015/108 | T2 DI CAYUCOS CMBRA 15/108 COTTER | PISMOBCH | ETL.8560.INSL.NCER | 2023-02-21 | 2023-02-10 | 2024-01-14 | On-time | 2024-02-10 | 27 | 2024-02-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46088419 | T2 DI CAYUCOS CMBRA 15/108 COTTER | ICW
LC | 125533995 | 016/120 | T2 DI CAYUCOS CMBRA 16/120 RPL INSW | PISMOBCH | ETL.8560.INSL.NCER | 2023-02-21 | 2023-02-10 | 2024-01-14 | On-time | 2024-02-10 | 27 | 2024-02-10 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35513605 | T2 DI CAYUCOS CMBRA 16/120 RPL INSW | 93I
LC | 125534370 | 017/128 | T2 DI CAYUCOS-CAMBRIA 17/128 RPR SPLW | PISMOBCH | ETL.8560.INSL.NCER | 2023-02-21 | 2023-02-10 | 2024-01-14 | On-time | 2024-02-10 | 27 | 2024-02-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46088461 | T2 DI CAYUCOS-CAMBRIA 17/128 RPR SPLW | ICW
LC | 125524249 | 015/066A | T2 DI SL BSP-OCEANO 015/066A RPR INSW | PISMOBCH | ETL.3530.INSL.NCER | 2023-02-17 | 2023-02-09 | 2024-03-20 | Late | 2024-02-09 | -40 | 2024-02-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46078500 | T2 DI SL BSP-OCEANO 015/066A RPR INSW | ICW
LC | 125524676 | 010/047 | T2 DI SLO-SANTA MARIA 10/47 RPL INSS | PISMOBCH | ETL.3540.INSL.CERA | 2023-02-17 | 2023-02-08 | 2024-03-29 | Late | 2024-02-08 | -50 | 2024-02-08 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31663734 | T2 DI SLO-SANTA MARIA 21/100 RPL INSS | 93K
LC | 125524677 | 010/047 | T2 DI SL BSP-OCEANO 010/047 RPL INSS | PISMOBCH | ETL.3530.INSL.CERA | 2023-02-17 | 2023-02-08 | 2024-03-24 | Late | 2024-02-08 | -45 | 2024-02-08 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31663733 | T2 DI SL BSP-OCEANO 010/047 RPL INSS | 93K
LC | 125584295 | 002/010 | T2 DI WSHN-SN JOAQUIN #3 2/10 RPR STRW | FRESNO | ETL.9340.POLE.WOOD | 2023-03-03 | 2023-02-17 | 2023-04-26 | On-time | 2024-02-17 | 297 | 2024-02-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45753534 | T2 DI WSHN-SN JOAQUIN #3 2/10 RPR STRW | ICW
LC | 125494884 | 002/051 | T2 SMARTVILLE-MARYSVILLE 02/51 RPL POLE | SACTO | ETL.7980.POLE.WOOD | 2023-02-13 | 2023-02-11 | 2023-05-03 | On-time | 2024-02-11 | 284 | 2024-02-11 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31633694 | T2 DI SMARTVLE-MARYSVLE 01/24 RPL STRW | 70Y
LC | 125491703 | 021/420 | T2 EI COLGATE-PALERMO 021/420 RPL POLE | TABLEMTN | ETL.6500.POLE.WOOD | 2023-02-13 | 2023-02-13 | 2023-11-01 | On-time | 2024-02-13 | 104 | 2024-02-13 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31663433 | T2 EI COLGATE-PALERMO 18/359 RPL POLE | 70Y
LC | 125491849 | 021/418 | T2 EI COLGATE-PALERMO 021/418 RPL POLE | TABLEMTN | ETL.6500.POLE.WOOD | 2023-02-13 | 2023-02-13 | 2023-11-01 | On-time | 2024-02-13 | 104 | 2024-02-13 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663433 | T2 EI COLGATE-PALERMO 18/359 RPL POLE | 70Y
LC | 125492894 | A005/107 | T2 EI LAKEVILLE #2 5/107 RMV VEG | LAKEVLLE | ETL.7340.POLE.WOOD | 2023-02-13 | 2023-02-13 | 2023-09-20 | On-time | 2024-02-13 | 146 | 2024-02-13 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Trim
LC | 125524874 | 000/021 | T2 DI JEFFERSON-STANFORD 0/21 RMV VEG | METCALF | ETL.7220.POLE.WOOD | 2023-02-17 | 2023-02-08 | 2024-02-21 | Late | 2024-02-08 | -13 | 2024-02-08 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125493665 | A015/239 | T2 EI COLEMAN-RED BLUFF A15/239 RPL POLE | TABLEMTN | ETL.6440.POLE.WOOD | 2023-02-13 | 2023-02-13 | 2023-10-30 | On-time | 2024-02-13 | 106 | 2024-02-13 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663432 | T2 EI COLEMAN-RED BLUFF A15/239 RPL POLE | 70Y
LC | 125494463 | A014/233 | T2 EI COLEMAN-RED BLUFF A14/233 RPL POLE | TABLEMTN | ETL.6440.POLE.WOOD | 2023-02-13 | 2023-02-13 | 2023-11-13 | On-time | 2024-02-13 | 92 | 2024-02-13 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31663431 | T2 EI COLEMAN-RED BLUFF A14/233 RPL POLE | 70Y
LC | 125494924 | A014/231 | T2 EI CLEMAN-RED BLUFF A014/231 RPR POLE | TABLEMTN | ETL.6440.POLE.NWOD | 2023-02-13 | 2023-02-13 | 2023-10-13 | On-time | 2024-02-13 | 123 | 2024-02-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45698562 | T2 EI CLEMAN-RED BLUFF A014/231 RPR POLE | ICW
LC | 125495070 | 015/137 | T2 DI SL BSP-CAYUCOS 15/137L RPR GYWW | PISMOBCH | ETL.9090.POLE.WDPS | 2023-02-13 | 2023-02-13 | 2024-01-10 | On-time | 2024-02-13 | 34 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088303 | T2 DI SL BSP-CAYUCOS 15/137L RPR GYWW | ICW
LC | 125525503 | 010/045 | DI T2 SNLUS OBPO OCNO 10/045 COA | PISMOBCH | ETL.3530.TOWR | 2023-02-18 | 2023-02-08 | 2024-02-29 | Late | 2024-02-08 | -21 | 2024-02-08 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125495072 | 015/137 | T2 DI SL BSP-CAYUCOS 15/137L RPR STRW | PISMOBCH | ETL.9090.POLE.WDPS | 2023-02-13 | 2023-02-13 | 2024-01-10 | On-time | 2024-02-13 | 34 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088304 | T2 DI SL BSP-CAYUCOS 15/137L RPR STRW | ICW
LC | 125495074 | 015/137 | T2 DI SL BSP-CAYUCOS 15/137L RPR CRSW | PISMOBCH | ETL.9090.POLE.WDPS | 2023-02-13 | 2023-02-13 | 2024-01-10 | On-time | 2024-02-13 | 34 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46088305 | T2 DI SL BSP-CAYUCOS 15/137L RPR CRSW | ICW
LC | 125495679 | A015/235 | T2 EI COLEMAN-RED BLUFF A15/235 RPR POLE | TABLEMTN | ETL.6440.POLE.WOOD | 2023-02-13 | 2023-02-13 | 2023-10-13 | On-time | 2024-02-13 | 123 | 2024-02-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45698327 | T2 EI COLEMAN-RED BLUFF A15/235 RPR POLE | ICW
LC | 125497613 | 007/087 | T2 EI COLGTE-SMARTVILLE #2 7/87 RPR INSW | SACTO | ETL.6520.POLE.NWOD | 2023-02-14 | 2023-02-13 | 2023-04-07 | On-time | 2024-02-13 | 312 | 2023-08-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45684905 | T2 EI COLGTE-SMARTVILLE #2 7/87 RPR INSW | ICW
LC | 125536516 | 025/217 | T2 DI BRDVIL CTTNWD 25/217 RPL ANCW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-02-21 | 2023-02-13 | 2023-12-01 | On-time | 2024-02-13 | 74 | 2024-02-13 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31663429 | T2 DI BRDVIL CTTNWD 25/217 RPL ANCW | 93E
LC | 125538367 | 024/211 | T2 DI BRDGVIL CTTNWD 24/211 RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-02-22 | 2023-02-13 | 2023-09-01 | On-time | 2024-02-13 | 165 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698631 | T2 DI BRDGVIL CTTNWD 24/211 RPR GYWW | ICW
LC | 125538445 | 013/125 | T2 DI SN LS OBSPO CYCS 13/125 RPR POLE | PISMOBCH | ETL.9090.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2024-01-10 | On-time | 2024-02-13 | 34 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088310 | T2 DI SN LS OBSPO CYCS 13/125 RPR POLE | ICW
LC | 125538446 | 013/125 | T2 DI SN LS OBSPO CYCOS 13/125 RPR GYW | PISMOBCH | ETL.9090.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2024-01-10 | On-time | 2024-02-13 | 34 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088312 | T2 DI SN LS OBSPO CYCOS 13/125 RPR GYW | ICW
LC | 125538589 | 000/003 | T2 DI PTTSBRG-TESLA #2 0/3 COTTER | CONCORD | ETL.5520.INSL.CERA | 2023-02-22 | 2023-02-13 | 2023-08-29 | On-time | 2024-02-13 | 168 | 2024-02-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45926513 | T2 DI PTTSBRG-TESLA #2 0/3 COTTER | ICS
LC | 125538697 | 012/113 | T2 DI SN LS OBSPO CYCOS 12/113 RPL HRDW | PISMOBCH | ETL.9090.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2024-01-10 | On-time | 2024-02-13 | 34 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46088313 | T2 DI SN LS OBSPO CYCOS 12/113 RPL HRDW | ICW
LC | 125525833 | 004/084 | T2 EI BRIONES TAP 4/84 RPL POLE | CONCORD | ETL.7055.POLE.WOOD | 2023-02-18 | 2023-02-18 | 2024-02-26 | Late | 2024-02-18 | -8 | 2024-02-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505756 | T2 EI BRIONES TAP 4/84 RPL POLE | 70Y
LC | 125538720 | 013/117 | T2 DI SL BSP-CAYUCOS 13/117 RPL POLE | PISMOBCH | ETL.9090.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2024-01-11 | On-time | 2024-02-13 | 33 | 2024-02-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495499 | T2 DI SL BSP-CAYUCOS 13/117 RPL POLE | 70Y
LC | 125525877 | 000/002 | T2 EI COLGATE-SMARTVILLE #1 0/2 RMV VEG | SACTO | ETL.6510.POLE.NWOD | 2023-02-18 | 2023-02-18 |  | Late | 2024-02-18 |  | 2024-02-18 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 125538930 | 024/213 | T2 DI BRDGVLL-CTTNWD 24/213 RPR SHLW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-02-22 | 2023-02-13 | 2023-09-28 | On-time | 2024-02-13 | 138 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45698596 | T2 DI BRDGVLL-CTTNWD 24/213 RPR SHLW | ICW
LC | 125539517 | 001/021 | T2 DI COTTONWD-BENTON #2 1/21L RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2023-02-22 | 2023-02-13 | 2023-12-28 | On-time | 2024-02-13 | 47 | 2024-02-13 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663434 | T2 DI COTTONWD-BENTON #2 1/21L RPL STRW | 70Y
LC | 125539554 | 007/088 | T2 DI JOLON 7/88 COTTER | MOSSLNDG | ETL.7321.INSL | 2023-02-22 | 2023-02-13 | 2023-12-11 | On-time | 2024-02-13 | 64 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946628 | T2 DI JOLON 7/88 COTTER | ICW
LC | 125525981 | 016/008 | T2 EI PHILO JCT-ELK 16/08 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-02-18 | 2023-02-18 | 2024-05-07 | Late | 2024-02-18 | -79 | 2024-02-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35481540 | T2 EI PHILO JCT-ELK 16/08 RPL POLE | 70Y
LC | 125539558 | 007/088 | T2 DI JOLON TAP 7/88 RMV VEG | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2024-02-09 | On-time | 2024-02-13 | 4 | 2024-02-13 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125526033 | 000/019 | T2 DI JFFRSN-STNFRD 0/19 RMV VEG | METCALF | ETL.7220.POLE.WOOD | 2023-02-18 | 2023-02-09 | 2024-02-21 | Late | 2024-02-09 | -12 | 2024-02-09 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125539590 | 001/021 | T2 DI COTTONWD-BENTON #2 1/21R RPL STRW | TABLEMTN | ETL.6650.POLE.WDPS | 2023-02-22 | 2023-02-13 | 2023-12-28 | On-time | 2024-02-13 | 47 | 2024-02-13 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663434 | T2 DI COTTONWD-BENTON #2 1/21L RPL STRW | 70Y
LC | 125539686 | 006/079 | T2 DI JOLON TAP 6/79 RPR INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-22 | 2023-02-13 | 2024-01-26 | On-time | 2024-02-13 | 18 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946626 | T2 DI JOLON TAP 6/79 RPR INSW | ICW
LC | 125526095 | 002/006 | T2 EI FORT BRAGG-ELK 2/6 GO95 CLEAR | WILLITS | ETL.2060.POLE.WOOD | 2023-02-18 | 2023-02-18 | 2024-04-09 | Late | 2024-02-18 | -51 | 2024-02-18 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35481399 | T2 EI FORT BRAGG-ELK 002/006 GO95 CLRNCE | 93G
LC | 125539806 | 007/091 | T2 DI JOLON 7/91 RPL HRDD | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2023-12-17 | On-time | 2024-02-13 | 58 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946629 | T2 DI JOLON 7/91 RPL HRDD | ICW
LC | 125529615 | 011/187 | T2 EI TEJON-LEBEC 011/187 RPL POLE | MIDWAY | ETL.9250.POLE.WOOD | 2023-02-20 | 2023-02-20 |  | Late | 2024-02-20 |  | 2024-02-20 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663426 | T2 EI TEJON-LEBEC 010/176 RPL POLE | 70Y
LC | 125529758 | 011/189 | T2 EI TEJON-LEBEC 011/189 RPL POLE | MIDWAY | ETL.9250.POLE.WOOD | 2023-02-20 | 2023-02-20 |  | Late | 2024-02-20 |  | 2024-02-20 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663426 | T2 EI TEJON-LEBEC 010/176 RPL POLE | 70Y
LC | 125539835 | 000/008 | T2 DI JOLON TAP 0/8 RPR INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-22 | 2023-02-13 | 2023-09-01 | On-time | 2024-02-13 | 165 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946547 | T2 DI JOLON TAP 0/8 RPR INSW | ICW
LC | 125540650 | 009/115 | T2 DI JOLON 9/115 RPL HRDW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2024-01-29 | On-time | 2024-02-13 | 15 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946635 | T2 DI JOLON 9/115 RPL HRDW | ICW
LC | 125540654 | 009/115 | T2 DI JOLON 9/115 RPL INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-22 | 2023-02-13 | 2024-01-29 | On-time | 2024-02-13 | 15 | 2024-02-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35494106 | T2 DI JOLON 9/115 RPL INSW | 93I
LC | 125530240 | 005/100 | 2 EI BRIONES TAP 5/100 RPL INSW | CONCORD | ETL.7055.INSL | 2023-02-20 | 2023-02-20 | 2024-02-22 | Late | 2024-02-20 | -2 | 2024-02-20 | 508 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31664057 | T2 EI BRIONES TAP 5/100 RPL INSW | 93I
LC | 125530529 | 022/007 | T2 EI PHILO JCT-ELK 22/07 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-02-20 | 2023-02-20 | 2024-06-17 | Late | 2024-02-20 | -118 | 2024-02-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483087 | T2 EI PHILO JCT-ELK 22/07 RPL POLE | 70Y
LC | 125540774 | 013/086 | T2 DI CAYUCOS-CAMBRIA 013/086 RPR GYWW | PISMOBCH | ETL.8560.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2024-01-14 | On-time | 2024-02-13 | 30 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088463 | T2 DI CAYUCOS-CAMBRIA 013/086 RPR GYWW | ICW
LC | 125541022 | 002/027 | T2 DI JOLON TAP 2/27 RPR STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2023-09-01 | On-time | 2024-02-13 | 165 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45946551 | T2 DI JOLON TAP 2/27 RPR STRW | ICW
LC | 125530992 | 006/112 | T2 EI BRIONES TAP 6/112 RPL POLE | CONCORD | ETL.7055.POLE.WOOD | 2023-02-20 | 2023-02-20 |  | Late | 2024-02-20 |  | 2024-02-20 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31664059 | T2 EI BRIONES TAP 6/106 RPL POLE | 70Y
LC | 125531048 | 021/010 | T2 EI FORT BRAGG-ELK 021/010 RMV VEG | WILLITS | ETL.2060.POLE.WOOD | 2023-02-20 | 2023-02-20 | 2024-03-11 | Late | 2024-02-20 | -20 | 2024-02-20 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125541024 | 002/027 | T2 DI JOLON TAP 2/27 RPR ANCW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2023-09-01 | On-time | 2024-02-13 | 165 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45946552 | T2 DI JOLON TAP 2/27 RPR ANCW | ICW
LC | 125541183 | 006/078 | T2 DI JOLON TAP 6/78 RPL HRDD | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2024-01-27 | On-time | 2024-02-13 | 17 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946625 | T2 DI JOLON TAP 6/78 RPL HRDD | ICW
LC | 125532251 | :019/003 | T2 EAGLE ROCK-REDBUD :019/003 RPL POLE | WILLITS | ETL.1480.POLE.WOOD | 2023-02-21 | 2023-02-21 |  | Late | 2024-02-21 |  | 2024-02-21 | 372T | TLN | CREW | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35482893 | T2 EAGLE ROCK-REDBUD :019/003 RPL POLE | 70Y
LC | 125541399 | 004/047 | T2 DI JOLON TAP 4/47 RPL HRDD | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2023-09-06 | On-time | 2024-02-13 | 160 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946557 | T2 DI JOLON TAP 4/47 RPL HRDD | ICW
LC | 125541461 | 004/047 | T2 DI JOLON TAP 4/47 RPR STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2023-09-06 | On-time | 2024-02-13 | 160 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45946559 | T2 DI JOLON TAP 4/47 RPR STRW | ICW
LC | 125532499 | 014/005 | T2 EI PHILO JCT-ELK 14/005 RPL INSW | WILLITS | ETL.7780.INSL.NCER | 2023-02-21 | 2023-02-21 | 2024-05-06 | Late | 2024-02-21 | -75 | 2024-02-21 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35483028 | T2 EI PHILO JCT-ELK 14/005 RPL INSW | 93I
LC | 125541504 | 004/051 | T2 DI JOLON TAP 4/51 RPR STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2023-09-13 | On-time | 2024-02-13 | 153 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45946620 | T2 DI JOLON TAP 4/51 RPR STRW | ICW
LC | 125541766 | 013/088 | T2 DI CAYUCOS-CAMBRIA 013/088 RPL POLE | PISMOBCH | ETL.8560.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2024-01-14 | On-time | 2024-02-13 | 30 | 2024-02-13 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31653108 | T2 DI CAYUCOS-CAMBRIA 13/088 RPL POLE | 70Y
LC | 125541793 | 002/030 | T2 DI JOLON TAP 2/30 RPR STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2023-12-14 | On-time | 2024-02-13 | 61 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45946554 | T2 DI JOLON TAP 2/30 RPR STRW | ICW
LC | 125541849 | 003/044 | T2 DI JOLON TAP 3/44 RPL HRDD | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2023-12-14 | On-time | 2024-02-13 | 61 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946556 | T2 DI JOLON TAP 3/44 RPL HRDD | ICW
LC | 125532965 | 021/006 | T2 EI FORT BRAGG-ELK 021/006 RPL INSW | WILLITS | ETL.2060.INSL.CERA | 2023-02-21 | 2023-02-21 |  | Late | 2024-02-21 |  | 2024-02-21 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35483020 | T2 EI FORT BRAGG-ELK 020/003 RPL INSW | 93I
LC | 125542130 | 010/128 | T2 DI JOLON 10/128 INS IBWW | MOSSLNDG | ETL.7321.POLE.NWOD | 2023-02-22 | 2023-02-13 | 2024-01-22 | On-time | 2024-02-13 | 22 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45946639 | T2 DI JOLON 10/128 INS IBWW | ICW
LC | 125542262 | 003/076 | T2 DI DELTA-MTN GATE JCT 3/76 RPL STRW | TABLEMTN | ETL.6750.POLE.WOOD | 2023-02-22 | 2023-02-13 | 2023-10-09 | On-time | 2024-02-13 | 127 | 2024-02-13 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663436 | T2 DI DELTA-MTN GATE JCT 3/76 RPL STRW | 70Y
LC | 125544172 | 002/051 | T2 DI KSWCK CSCDE 2/51 RPR CRSW | TABLEMTN | ETL.7260.POLE.WOOD | 2023-02-23 | 2023-02-13 | 2023-10-15 | On-time | 2024-02-13 | 121 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45698568 | T2 DI KSWCK CSCDE 2/51 RPR CRSW | ICW
LC | 125544186 | 006/085 | T2 DI JOLON TAP 6/85 RPL POLE | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-13 | 2024-01-18 | On-time | 2024-02-13 | 26 | 2024-02-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494025 | T2 DI JOLON 5/74 RPL STRW | 70Y
LC | 125533494 | 015/007 | T2 EI PHILO JCT-ELK 15/007 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-02-21 | 2023-02-21 | 2024-05-08 | Late | 2024-02-21 | -77 | 2024-02-21 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483086 | T2 EI PHILO JCT-ELK 15/007 RPL POLE | 70Y
LC | 125533571 | 020/138 | T2 DI OCNO CLNDR SWSTA 20/138 RPL IBWW | PISMOBCH | ETL.2394.INSL.NCER | 2023-02-21 | 2023-02-09 |  | Late | 2024-02-09 |  | 2024-02-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46078603 | T2 DI OCNO CLNDR SWSTA 20/138 RPL IBWW | ICW
LC | 125544280 | 004/048 | T2 DI JOLON TAP 4/48 RPR STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-13 | 2023-12-09 | On-time | 2024-02-13 | 66 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45946558 | T2 DI JOLON TAP 4/48 RPR STRW | ICW
LC | 125544314 | 007/097 | T2 DI JOLON TAP 7/97 RPR INSW | MOSSLNDG | ETL.7321.INSL.NCER | 2023-02-23 | 2023-02-13 | 2024-01-26 | On-time | 2024-02-13 | 18 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946632 | T2 DI JOLON TAP 7/97 RPR INSW | ICW
LC | 125533786 | 021/002 | T2 EI FORT BRAGG-ELK 021/002 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-02-21 | 2023-02-21 |  | Late | 2024-02-21 |  | 2024-02-21 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483021 | T2 EI FORT BRAGG-ELK 021/002 RPL STRW | 70Y
LC | 125533820 | 019/092 | T2 DI CLLNDR-MESA 019/092 COA | PISMOBCH | ETL.1210.TOWR | 2023-02-21 | 2023-02-09 | 2024-02-27 | Late | 2024-02-09 | -18 | 2024-02-09 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125544315 | 007/097 | T2 DI JOLON TAP 7/97 RPL HRDD | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-13 | 2024-01-26 | On-time | 2024-02-13 | 18 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946633 | T2 DI JOLON TAP 7/97 RPL HRDD | ICW
LC | 125544418 | 009/120 | T2 DI JOLON TAP 9/120 RPR INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-23 | 2023-02-13 | 2024-01-17 | On-time | 2024-02-13 | 27 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946636 | T2 DI JOLON TAP 9/120 RPR INSW | ICW
LC | 125533991 | 016/120 | T2 DI CAYUCOS CMBRA 16/120 RPR GYWW | PISMOBCH | ETL.8560.POLE.NWOD | 2023-02-21 | 2023-02-10 | 2024-02-21 | Late | 2024-02-10 | -11 | 2024-02-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088460 | T2 DI CAYUCOS CMBRA 16/120 RPR GYWW | ICW
LC | 125544469 | 009/120 | T2 DI JOLON TAP 9/120 RPR CNDW | MOSSLNDG | ETL.7321.INSL | 2023-02-23 | 2023-02-13 | 2024-01-17 | On-time | 2024-02-13 | 27 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45946637 | T2 DI JOLON TAP 9/120 RPR CNDW | ICW
LC | 125534043 | 003/027 | T2 EI TRINITY-CTTNWD 3/27 RPR INSS | TABLEMTN | ETL.4040.INSL.NCER | 2023-02-21 | 2023-02-21 |  | Late | 2024-02-21 |  | 2024-02-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45698624 | T2 EI TRINITY-CTTNWD 3/27 RPR INSS | ICW
LC | 125544538 | 000/011 | T2 DI JOLON TAP 0/11 ANTI SPLIT | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-13 | 2023-12-17 | On-time | 2024-02-13 | 58 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946548 | T2 DI JOLON TAP 0/11 ANTI SPLIT | ICW
LC | 125545380 | 007/095 | T2 DI JOLON TAP 7/95 RPR STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-13 | 2024-01-26 | On-time | 2024-02-13 | 18 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45946630 | T2 DI JOLON TAP 7/95 RPR STRW | ICW
LC | 125545382 | 007/095 | T2 DI JOLON TAP 7/95 RPL HRDD | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-13 | 2024-01-26 | On-time | 2024-02-13 | 18 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946631 | T2 DI JOLON TAP 7/95 RPL HRDD | ICW
LC | 125534298 | 023/000 | T2 EI PHILO JCT-ELK 23/0 RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-02-21 | 2023-02-21 | 2024-06-06 | Late | 2024-02-21 | -106 | 2024-02-21 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483034 | T2 EI PHILO JCT-ELK 23/0 RPL STRW | 70Y
LC | 125534363 | 004/000 | T2 EI CLEAR LAKE-HOPLAND 4/0 RPL POLE | WILLITS | ETL.6390.POLE.WOOD | 2023-02-21 | 2023-02-21 |  | Late | 2024-02-21 |  | 2024-02-21 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35482892 | T2 EI CLEAR LAKE-HOPLAND 4/0 RPL POLE | 70Y
LC | 125545456 | 009/125 | T2 DI JOLON TAP 9/125 UNBURY | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-13 | 2023-12-08 | On-time | 2024-02-13 | 67 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45746643 | T2 DI JOLON TAP 9/125 UNBURY | ICW
LC | 125545608 | 012/161 | T2 DI JOLON TAP 12/161 RMV VEG | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-13 | 2024-02-09 | On-time | 2024-02-13 | 4 | 2024-02-13 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125534609 | 018/133 | T2 DI CYUCOS-CMBRIA 18/133C RPL POLE | PISMOBCH | ETL.8560.POLE.WDPS | 2023-02-21 | 2023-02-10 | 2024-03-12 | Late | 2024-02-10 | -31 | 2024-02-10 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31653107 | T2 DI CYUCOS-CMBRIA 18/133C RPL POLE | 70Y
LC | 125534696 | 023/001 | T2 EI PHILO JCT-ELK 23/001 RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-02-21 | 2023-02-21 | 2024-05-23 | Late | 2024-02-21 | -92 | 2024-02-21 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483035 | T2 EI PHILO JCT-ELK 23/001 RPL STRW | 70Y
LC | 125534711 | 018/133 | T2 DI CYUCOS-CMBRIA 18/133R RPL POLE | PISMOBCH | ETL.8560.POLE.WDPS | 2023-02-21 | 2023-02-10 | 2024-03-12 | Late | 2024-02-10 | -31 | 2024-02-10 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31653107 | T2 DI CYUCOS-CMBRIA 18/133C RPL POLE | 70Y
LC | 125535307 | 018/133 | T2 DI CYUCOS-CMBRIA 18/133L RPL POLE | PISMOBCH | ETL.8560.POLE.WDPS | 2023-02-21 | 2023-02-10 | 2024-03-12 | Late | 2024-02-10 | -31 | 2024-02-10 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31653107 | T2 DI CYUCOS-CMBRIA 18/133C RPL POLE | 70Y
LC | 125547789 | 005/067 | T2 DI JOLON TAP 5/67 ANTI SPLIT | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-13 | 2024-01-10 | On-time | 2024-02-13 | 34 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946622 | T2 DI JOLON TAP 5/67 ANTI SPLIT | ICW
LC | 125550502 | 002/028 | T2 DI JOLON 2/28 RPR INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-24 | 2023-02-13 | 2023-12-17 | On-time | 2024-02-13 | 58 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946553 | T2 DI JOLON 2/28 RPR INSW | ICW
LC | 125550503 | 002/028 | T2 DI JOLON TAP 2/28 RPR INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-24 | 2023-02-13 | 2024-01-25 | On-time | 2024-02-13 | 19 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46122541 | T2 DI JOLON TAP 2/28 RPR INSW | ICW
LC | 125536410 | 025/219 | T2 DI BRDVIL CTTNWD 25/219 RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-02-21 | 2023-02-13 |  | Late | 2024-02-13 |  | 2024-02-13 | 372 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663430 | DI T2 BRDVIL CTTNWD 25/219 RPL STRW | 70Y
LC | 125536415 | 025/219 | T2 DI BRDVIL CTTNWD 25/219 RPL PL | TABLEMTN | ETL.1110.POLE.WDPS | 2023-02-21 | 2023-02-13 |  | Late | 2024-02-13 |  | 2024-02-13 | 372 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663430 | DI T2 BRDVIL CTTNWD 25/219 RPL STRW | 70Y
LC | 125550642 | 004/055 | T2 DI JOLON 4/55 RPL INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-24 | 2023-02-13 | 2024-01-16 | On-time | 2024-02-13 | 28 | 2024-02-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35494024 | T2 DI JOLON TAP 3/38 RPL INSW | 93I
LC | 125550886 | 008/111 | T2 DI JOLON TAP 008/111 RPL INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-24 | 2023-02-13 | 2024-01-17 | On-time | 2024-02-13 | 27 | 2024-02-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35502311 | T2 DI JOLON TAP 008/110 RPL INSW | 93I
LC | 125551175 | 008/105 | T2 DI JOLON 008/105 RPR INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-24 | 2023-02-13 | 2024-01-03 | On-time | 2024-02-13 | 41 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946634 | T2 DI JOLON 008/105 RPR INSW | ICW
LC | 125552008 | 013/174 | T2 DI JOLON TAP 13/174 RPR HRDW | MOSSLNDG | ETL.7321.POLE.NWOD | 2023-02-24 | 2023-02-13 | 2023-12-02 | On-time | 2024-02-13 | 73 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946641 | T2 DI JOLON TAP 13/174 RPR HRDW | ICW
LC | 125552888 | 001/015 | T2 DI JOLON 1/15 RPL HRDD | MOSSLNDG | ETL.7321.INSL.NCER | 2023-02-24 | 2023-02-13 | 2023-12-09 | On-time | 2024-02-13 | 66 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45946550 | T2 DI JOLON 1/15 RPL HRDD | ICW
LC | 125552944 | 000/013 | T2 DI JOLON 0/13 RPL INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-24 | 2023-02-13 | 2024-01-19 | On-time | 2024-02-13 | 25 | 2024-02-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35494023 | T2 DI JOLON 0/13 RPL INSW | 93I
LC | 125553565 | 005/071 | T2 DI JOLON 5/71 RPL HRDD | MOSSLNDG | ETL.7321.INSL | 2023-02-24 | 2023-02-13 | 2024-01-26 | On-time | 2024-02-13 | 18 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946623 | T2 DI JOLON 5/71 RPL HRDD | ICW
LC | 125553613 | 005/071 | T2 DI JOLON 5/71 RPR STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-24 | 2023-02-13 | 2024-01-26 | On-time | 2024-02-13 | 18 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45946624 | T2 DI JOLON 5/71 RPR STRW | ICW
LC | 125553678 | 004/059 | T2 DI JOLON TAP 4/59 RPR INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-24 | 2023-02-13 | 2023-09-06 | On-time | 2024-02-13 | 160 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946621 | T2 DI JOLON TAP 4/59 RPR INSW | ICW
LC | 125554242 | 002/029 | T2 DI JOLON 2/29 RPR INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-24 | 2023-02-13 | 2023-12-14 | On-time | 2024-02-13 | 61 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946555 | T2 DI JOLON 2/29 RPR INSW | ICW
LC | 125554602 | 000/012 | T2 DI JOLON 0/12 RPL INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-24 | 2023-02-13 | 2024-01-19 | On-time | 2024-02-13 | 25 | 2024-02-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35516913 | T2 DI JOLON 0/12 RPL INSW | 93I
LC | 125554816 | 007/099 | 2 DI JOLON 007/099 RPL POLE | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-24 | 2023-02-13 | 2024-01-26 | On-time | 2024-02-13 | 18 | 2024-02-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494030 | T2 DI JOLON 007/099 RPL POLE | 70Y
LC | 125556816 | 012/173 | T2 DI JOLON 12/173 RPR STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-25 | 2023-02-13 | 2023-12-02 | On-time | 2024-02-13 | 73 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45946640 | T2 DI JOLON 12/173 RPR STRW | ICW
LC | 125556866 | 008/100 | T2 DI JOLON TAP 008/100 RPL POLE | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-25 | 2023-02-13 | 2024-01-27 | On-time | 2024-02-13 | 17 | 2024-02-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494030 | T2 DI JOLON 007/099 RPL POLE | 70Y
LC | 125556952 | 006/084 | T2 DI JOLON TAP 6/84 RPR INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-25 | 2023-02-13 | 2024-01-26 | On-time | 2024-02-13 | 18 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946627 | T2 DI JOLON TAP 6/84 RPR INSW | ICW
LC | 125539369 | 020/006 | T2 EI FORT BRAGG-ELK 020/006 COMPLETED | WILLITS | ETL.2060.INSL.NCER | 2023-02-22 | 2023-02-22 | 2024-03-11 | Late | 2024-02-22 | -18 | 2024-02-22 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35483020 | T2 EI FORT BRAGG-ELK 020/003 RPL INSW | 93I
LC | 125539423 | 020/006 | T2 EI FORT BRAGG-ELK 020/006 COA | WILLITS | ETL.2060.POLE.WOOD | 2023-02-22 | 2023-02-22 | 2024-03-13 | Late | 2024-02-22 | -20 | 2024-02-22 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125539471 | 007/134 | T2 EI COLGATE-PALERMO 7/134 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-02-22 | 2023-02-22 | 2024-04-18 | Late | 2024-02-22 | -56 | 2024-02-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35482861 | T2 EI COLGATE-PALERMO 7/134 RPL POLE | 70Y
LC | 125557206 | 008/107 | T2 DI JOLON 008/107 RPL POLE | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-25 | 2023-02-13 | 2024-01-26 | On-time | 2024-02-13 | 18 | 2024-02-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494103 | T2 DI JOLON 008/107 RPL POLE | 70Y
LC | 125557448 | 013/176 | T2 DI JOLON 13/176 RPR STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-25 | 2023-02-13 | 2023-12-02 | On-time | 2024-02-13 | 73 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45946642 | T2 DI JOLON 13/176 RPR STRW | ICW
LC | 125557621 | 015/220 | T2 DI JOLON 15/220 RPR INSW | MOSSLNDG | ETL.7321.INSL.NCER | 2023-02-25 | 2023-02-13 | 2023-09-06 | On-time | 2024-02-13 | 160 | 2024-02-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946643 | T2 DI JOLON 15/220 RPR INSW | ICW
LC | 125561618 | 008/110 | T2 DI JOLON TAP 008/110 RPL INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-27 | 2023-02-13 | 2024-01-17 | On-time | 2024-02-13 | 27 | 2024-02-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35502311 | T2 DI JOLON TAP 008/110 RPL INSW | 93I
LC | 125501339 | 018/266A | T2 WV-CMRTL 18/266A INS POLE GO95 USAGE | VICTOR | ETL.8250.POLE.NWOD | 2023-02-14 | 2023-02-14 | 2023-05-05 | On-time | 2024-02-14 | 285 | 2024-02-14 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31543443 | T2 DI CLAY-MARTEL 18/266 RPL STRW | 70Y
LC | 125539705 | 020/005 | T2 EI FORT BRAGG-ELK 020/005 COMPLETE | WILLITS | ETL.2060.INSL.NCER | 2023-02-22 | 2023-02-22 | 2024-03-11 | Late | 2024-02-22 | -18 | 2024-02-22 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35483020 | T2 EI FORT BRAGG-ELK 020/003 RPL INSW | 93I
LC | 125502562 | 019/379 | T2 EI COLGATE-PALERMO 19/379 RMV VEG | TABLEMTN | ETL.6500.POLE.NWOD | 2023-02-14 | 2023-02-14 | 2024-02-14 | On-time | 2024-02-14 | 0 | 2024-02-14 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125503018 | 019/377 | T2 EI COLGATE-PALERMO 19/377 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-02-14 | 2023-02-14 | 2023-10-31 | On-time | 2024-02-14 | 106 | 2024-02-14 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663433 | T2 EI COLGATE-PALERMO 18/359 RPL POLE | 70Y
LC | 125539777 | 002/012 | T2 EI PHILO JCT-ELK 2/012 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-02-22 | 2023-02-22 | 2024-05-01 | Late | 2024-02-22 | -69 | 2024-02-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483032 | T2 EI PHILO JCT-ELK 2/011 RPL POLE | 70Y
LC | 125541339 | 009/122 | T2 DI JOLON TAP 9/122 RMV VEG | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-22 | 2023-02-14 | 2024-02-13 | On-time | 2024-02-14 | 1 | 2024-02-14 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125544176 | 001/017 | T2 DI JOLON TAP 1/17 ANTI SPLIT | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-14 | 2023-12-08 | On-time | 2024-02-14 | 68 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946644 | T2 DI JOLON TAP 1/17 ANTI SPLIT | ICW
LC | 125539965 | 020/004 | T2 EI FORT BRAGG-ELK 020/004 COMPLETE | WILLITS | ETL.2060.INSL.NCER | 2023-02-22 | 2023-02-22 | 2024-03-11 | Late | 2024-02-22 | -18 | 2024-02-22 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35483020 | T2 EI FORT BRAGG-ELK 020/003 RPL INSW | 93I
LC | 125540034 | 002/011 | T2 EI PHILO JCT-ELK 2/011 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-02-22 | 2023-02-22 | 2024-04-30 | Late | 2024-02-22 | -68 | 2024-02-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483032 | T2 EI PHILO JCT-ELK 2/011 RPL POLE | 70Y
LC | 125544215 | 010/141 | T2 DI JOLON TAP 10/141 RPR STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-14 | 2023-09-13 | On-time | 2024-02-14 | 154 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45946649 | T2 DI JOLON TAP 10/141 RPR STRW | ICW
LC | 125544298 | 010/143 | T2 DI JOLON 10/143 RPR STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-14 | 2024-01-31 | On-time | 2024-02-14 | 14 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45946650 | T2 DI JOLON 10/143 RPR STRW | ICW
LC | 125540350 | 020/003 | T2 EI FORT BRAGG-ELK 020/003 COMPLETE | WILLITS | ETL.2060.INSL.NCER | 2023-02-22 | 2023-02-22 | 2024-03-11 | Late | 2024-02-22 | -18 | 2024-02-22 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35483020 | T2 EI FORT BRAGG-ELK 020/003 RPL INSW | 93I
LC | 125544318 | 011/153 | T2 DI JOLON TAP 11/153 RPL POLE | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-14 | 2024-01-18 | On-time | 2024-02-14 | 27 | 2024-02-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494109 | T2 DI JOLON TAP 11/153 RPL POLE | 70Y
LC | 125544350 | 010/143 | T2 DI JOLON 10/143 RPL HRDD | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-14 | 2024-01-31 | On-time | 2024-02-14 | 14 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946651 | T2 DI JOLON 10/143 RPL HRDD | ICW
LC | 125544354 | 003/038 | T2 DI JOLON TAP 3/38 RPL INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-23 | 2023-02-14 | 2024-01-20 | On-time | 2024-02-14 | 25 | 2024-02-14 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35494024 | T2 DI JOLON TAP 3/38 RPL INSW | 93I
LC | 125544411 | 012/158 | T2 DI JOLON TAP 12/158 RPR GYWW | MOSSLNDG | ETL.7321.POLE.NWOD | 2023-02-23 | 2023-02-14 | 2023-12-02 | On-time | 2024-02-14 | 74 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45946658 | T2 DI JOLON TAP 12/158 RPR GYWW | ICW
LC | 125544687 | 010/129 | T2 DI JOLON TAP 10/129 RPR INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-23 | 2023-02-14 | 2024-01-17 | On-time | 2024-02-14 | 28 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946648 | T2 DI JOLON TAP 10/129 RPR INSW | ICW
LC | 125544858 | 013/087 | T2 DI CAYUCOS-CAMBRIA 013/087 RPR GYWW | PISMOBCH | ETL.8560.POLE.WOOD | 2023-02-23 | 2023-02-14 | 2024-01-14 | On-time | 2024-02-14 | 31 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088464 | T2 DI CAYUCOS-CAMBRIA 013/087 RPR GYWW | ICW
LC | 125544916 | 010/136 | T2 DI JOLON TAP 10/136 RPL INS IBWW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-14 | 2024-01-10 | On-time | 2024-02-14 | 35 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46015915 | T2 DI JOLON TAP 10/136 RPL INS IBWW | ICW
LC | 125541098 | 006/123 | T2 EI CNRVL-TBL MTN-ORV 6/123 RPR GYWW | TABLEMTN | ETL.6330.POLE.NWOD | 2023-02-22 | 2023-02-22 | 2024-03-04 | Late | 2024-02-22 | -11 | 2024-02-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698337 | T2 EI CNRVL-TBL MTN-ORV 6/123 RPR GYWW | ICW
LC | 125544951 | 010/136 | T2 DI JOLON TAP 10/136 RPR STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-14 | 2024-01-10 | On-time | 2024-02-14 | 35 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46015917 | T2 DI JOLON TAP 10/136 RPR STRW | ICW
LC | 125545003 | 012/156 | T2 DI JOLON TAP 12/156 ANTI SPLIT | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-14 | 2023-12-17 | On-time | 2024-02-14 | 59 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946657 | T2 DI JOLON TAP 12/156 ANTI SPLIT | ICW
LC | 125545387 | 010/139 | T2 DI JOLON TAP 10/139 INS IBWW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-14 | 2024-01-31 | On-time | 2024-02-14 | 14 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46016582 | T2 DI JOLON TAP 10/139 INS IBWW | ICW
LC | 125545570 | 010/138 | T2 DI JOLON TAP 10/138 INS IBWW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-14 | 2024-01-27 | On-time | 2024-02-14 | 18 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46015919 | T2 DI JOLON TAP 10/138 INS IBWW | ICW
LC | 125545572 | 010/138 | T2 DI JOLON TAP 10/138 RPR STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-14 | 2024-01-27 | On-time | 2024-02-14 | 18 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46016581 | T2 DI JOLON TAP 10/138 RPR STRW | ICW
LC | 125541477 | 009/004 | T2 EI PHILO JCT-ELK 9/004 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-02-22 | 2023-02-22 | 2024-05-05 | Late | 2024-02-22 | -73 | 2024-02-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483033 | T2 EI PHILO JCT-ELK 9/004 RPL POLE | 70Y
LC | 125545600 | 011/148 | T2 DI JOLON TAP 11/148 RPR INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-23 | 2023-02-14 | 2023-09-06 | On-time | 2024-02-14 | 161 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946653 | T2 DI JOLON TAP 11/148 RPR INSW | ICW
LC | 125546518 | 001/007 | T2 DI MENDOCINO-HARTLEY 01/07 RPR GYWW | WILLITS | ETL.7510.POLE.NWOD | 2023-02-23 | 2023-02-14 | 2023-09-11 | On-time | 2024-02-14 | 156 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45927606 | T2 DI MENDOCINO-HARTLEY 01/07 RPR GYWW | ICW
LC | 125546627 | 011/150A | T2 DI JOLON TAP 11/150A RPL POLE | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-14 | 2024-01-29 | On-time | 2024-02-14 | 16 | 2024-02-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494107 | T2 DI JOLON TAP 11/150A RPL POLE | 70Y
LC | 125546712 | 014/194 | T2 DI JOLON 14/194 INS IBWW | MOSSLNDG | ETL.7321.POLE.NWOD | 2023-02-23 | 2023-02-14 | 2024-01-21 | On-time | 2024-02-14 | 24 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45946662 | T2 DI JOLON 14/194 INS IBWW | ICW
LC | 125546731 | 011/150B | T2 DI JOLON TAP 11/150B RPL POLE | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-14 | 2024-01-29 | On-time | 2024-02-14 | 16 | 2024-02-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494107 | T2 DI JOLON TAP 11/150A RPL POLE | 70Y
LC | 125546990 | 011/150C | T2 DI JOLON TAP 11/150C RPL POLE | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-23 | 2023-02-14 | 2024-01-29 | On-time | 2024-02-14 | 16 | 2024-02-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494107 | T2 DI JOLON TAP 11/150A RPL POLE | 70Y
LC | 125547663 | 015/068 | T2 DI CLNDR SWSTA MESA 15/068 RMV VEG | PISMOBCH | ETL.1210.TOWR | 2023-02-23 | 2023-02-14 | 2023-07-11 | On-time | 2024-02-14 | 218 | 2024-02-14 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125550449 | 009/123 | T2 DI JOLON 9/123 RPR STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-24 | 2023-02-14 | 2023-08-08 | On-time | 2024-02-14 | 190 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45924043 | T2 DI JOLON 9/123 RPR STRW | ICW
LC | 125542625 | 006/106 | T2 EI BRIONES TAP 6/106 RPL POLE | CONCORD | ETL.7055.POLE.WOOD | 2023-02-22 | 2023-02-22 |  | Late | 2024-02-22 |  | 2024-02-22 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31664059 | T2 EI BRIONES TAP 6/106 RPL POLE | 70Y
LC | 125550483 | 009/123 | T2 DI JOLON 9/123 RPL HRDD | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-24 | 2023-02-14 | 2023-08-08 | On-time | 2024-02-14 | 190 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45924044 | T2 DI JOLON 9/123 RPL HRDD | ICW
LC | 125550564 | 010/130 | T2 DI JOLON 10/130 RMV VEG | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-24 | 2023-02-14 | 2024-01-10 | On-time | 2024-02-14 | 35 | 2024-02-14 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125550696 | 014/092 | T2 DI CAYUCOS-CAMBRIA 14/92 COTTER | PISMOBCH | ETL.8560.INSL.NCER | 2023-02-24 | 2023-02-14 | 2023-04-12 | On-time | 2024-02-14 | 308 | 2023-08-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45706783 | T2 DI CAYUCOS-CAMBRIA 14/92 COTTER | ICW
LC | 125550883 | 010/137 | T2 DI JOLON 10/137 RPR SPLW | MOSSLNDG | ETL.7321.INSL | 2023-02-24 | 2023-02-14 | 2024-01-10 | On-time | 2024-02-14 | 35 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46015918 | T2 DI JOLON 10/137 RPR SPLW | ICW
LC | 125551449 | 005/074 | T2 DI JOLON 5/74 RPL STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-24 | 2023-02-14 | 2024-01-25 | On-time | 2024-02-14 | 20 | 2024-02-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494025 | T2 DI JOLON 5/74 RPL STRW | 70Y
LC | 125552318 | 012/169 | T2 DI JOLON TAP 12/169 INS IBWW | MOSSLNDG | ETL.7321.POLE.NWOD | 2023-02-24 | 2023-02-14 | 2024-01-22 | On-time | 2024-02-14 | 23 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946660 | T2 DI JOLON TAP 12/169 INS IBWW | ICW
LC | 125554361 | 005/046 | T2 DI CBRLLO-ST YNZ 5/46 RPL INSW | PISMOBCH | ETL.1200.INSL.NCER | 2023-02-24 | 2023-02-14 | 2024-01-29 | On-time | 2024-02-14 | 16 | 2024-02-14 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31645483 | T2 DI CBRLL-SNT YNZ SW 2/12 RPL INSW | 93I
LC | 125555151 | 011/154 | T2 DI JOLON 11/154 RPL HRDD | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-24 | 2023-02-14 | 2023-12-08 | On-time | 2024-02-14 | 68 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45946655 | T2 DI JOLON 11/154 RPL HRDD | ICW
LC | 125555152 | 011/154 | T2 DI JOLON 11/154 RPR INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-24 | 2023-02-14 | 2023-12-08 | On-time | 2024-02-14 | 68 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946656 | T2 DI JOLON 11/154 RPR INSW | ICW
LC | 125555158 | 015/214 | T2 DI JOLON 15/214 RPR STRW | MOSSLNDG | ETL.7321.POLE.NWOD | 2023-02-24 | 2023-02-14 | 2023-09-06 | On-time | 2024-02-14 | 161 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45946664 | T2 DI JOLON 15/214 RPR STRW | ICW
LC | 125555189 | 011/149 | T2 DI JOLON 11/149 RPR INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-24 | 2023-02-14 | 2024-01-03 | On-time | 2024-02-14 | 42 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946654 | T2 DI JOLON 11/149 RPR INSW | ICW
LC | 125555386 | 013/185 | T2 DI JOLON 13/185 RPL STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-24 | 2023-02-14 | 2024-01-31 | On-time | 2024-02-14 | 14 | 2024-02-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494109 | T2 DI JOLON TAP 11/153 RPL POLE | 70Y
LC | 125556541 | 005/066 | T2 DI GRN VLY CMP EVRS 5/066 RPR STRW | MOSSLNDG | ETL.1710.POLE.WDPS | 2023-02-25 | 2023-02-14 | 2023-12-19 | On-time | 2024-02-14 | 57 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46082031 | T2 DI GRN VLY CMP EVRS 5/066 RPR STRW | ICW
LC | 125556547 | 001/018 | T2 DI JOLON TAP 1/18 RPL INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-25 | 2023-02-14 | 2024-01-19 | On-time | 2024-02-14 | 26 | 2024-02-14 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35516913 | T2 DI JOLON 0/12 RPL INSW | 93I
LC | 125556549 | 010/048 | T2 DI BRNTWD KLSO 10/048 RPL DAMS | CONCORD | ETL.4410.INSL | 2023-02-25 | 2023-02-14 | 2023-09-23 | On-time | 2024-02-14 | 144 | 2024-02-14 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 45690259 | T2 DI BRNTWD KLSO 10/048 RPL DAMS | ICS
LC | 125557684 | 015/215 | T2 DI JOLON 15/215 RPL STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-25 | 2023-02-14 | 2024-01-28 | On-time | 2024-02-14 | 17 | 2024-02-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494109 | T2 DI JOLON TAP 11/153 RPL POLE | 70Y
LC | 125558235 | 004/032 | T2 DI CBRL-ST YNZ SS 4/32 RPL INSW | PISMOBCH | ETL.1200.INSL.NCER | 2023-02-25 | 2023-02-14 | 2024-01-29 | On-time | 2024-02-14 | 16 | 2024-02-14 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31645483 | T2 DI CBRLL-SNT YNZ SW 2/12 RPL INSW | 93I
LC | 125563055 | 012/167 | T2 DI JOLON 12/167 INS IBWW | MOSSLNDG | ETL.7321.POLE.NWOD | 2023-02-27 | 2023-02-14 | 2024-01-22 | On-time | 2024-02-14 | 23 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45946659 | T2 DI JOLON 12/167 INS IBWW | ICW
LC | 125564164 | 012/170 | T2 DI JOLON 12/170 INS IBWW | MOSSLNDG | ETL.7321.POLE.NWOD | 2023-02-27 | 2023-02-14 | 2024-01-22 | On-time | 2024-02-14 | 23 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45946661 | T2 DI JOLON 12/170 INS IBWW | ICW
LC | 125564359 | 003/036 | T2 DI JOLON TAP 003/036 RPR INSW | MOSSLNDG | ETL.7321.INSL | 2023-02-27 | 2023-02-14 | 2023-09-01 | On-time | 2024-02-14 | 166 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946646 | T2 DI JOLON TAP 003/036 RPR INSW | ICW
LC | 125569673 | 005/041 | T2 DI CABRILLO-SANTA YNEZ 5/41 RPL HRDW | PISMOBCH | ETL.1200.POLE.NWOD | 2023-02-28 | 2023-02-14 | 2024-01-29 | On-time | 2024-02-14 | 16 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46078512 | T2 DI CABRILLO-SANTA YNEZ 5/41 RPL HRDW | ICW
LC | 125606746 | 014/209 | T2 DI JOLON TAP 014/209 RPR STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-03-08 | 2023-02-14 | 2023-12-08 | On-time | 2024-02-14 | 68 | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45946663 | T2 DI JOLON TAP 014/209 RPR STRW | ICW
LC | 125505895 | 015/079 | T2 VACA-PARKWAY 15/79 RPL INSS | SACTO | ETL.5850.INSL | 2023-02-15 | 2023-02-15 | 2023-11-22 | On-time | 2024-02-15 | 85 | 2024-02-15 | 532 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667697 | T2 VACA-PARKWAY 15/79 RPL INSS | 93K
LC | 125506603 | 007/142 | T2 CNTRVILLE-TBL MTN-RVILLE 7/142 GO95 | TABLEMTN | ETL.6330.POLE.WOOD | 2023-02-15 | 2023-02-15 | 2023-07-24 | On-time | 2024-02-15 | 206 | 2024-02-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31639070 | T2 CNTRVILLE-TBL MTN-RVILLE 7/142 GO 95 | 93G
LC | 125507318 | 014/098 | T2 EI MLLBRAE-SNTH LNE 14/98 RPL INSS | METCALF | ETL.7570.INSL.CERA | 2023-02-15 | 2023-02-15 | 2023-12-12 | On-time | 2024-02-15 | 65 | 2024-02-15 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667794 | T2 EI MLLBRAE-SNTH LNE 14/98 RPL INSS | 93K
LC | 125507940 | 009/046 | T2 FULTON-PUEBLO 9/46 RPR SPLW | LAKEVLLE | ETL.1600.INSL.NCER | 2023-02-15 | 2023-02-15 | 2023-10-14 | On-time | 2024-02-15 | 124 | 2024-02-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45735762 | T2 FULTON-PUEBLO 9/46 RPR SPLW | ICW
LC | 125507946 | 009/045 | T2 SILVERADO-FULTON 9/45 RPR SPLW | LAKEVLLE | ETL.1610.INSL.NCER | 2023-02-15 | 2023-02-15 | 2023-10-15 | On-time | 2024-02-15 | 123 | 2024-02-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45735760 | T2 SILVERADO-FULTON 9/45 RPR SPLW | ICW
LC | 125508003 | 009/045 | T2 SILVERADO-FULTON 9/45 RPR SPLW | LAKEVLLE | ETL.1610.INSL.NCER | 2023-02-15 | 2023-02-15 | 2023-10-15 | On-time | 2024-02-15 | 123 | 2024-02-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45735519 | T2 SILVERADO-FULTON 9/45 RPR SPLW | ICW
LC | 125508032 | 009/045 | T2 FULTON-PUEBLO 9/45 RPR SPLW | LAKEVLLE | ETL.1600.INSL.NCER | 2023-02-15 | 2023-02-15 | 2023-10-14 | On-time | 2024-02-15 | 124 | 2024-02-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45735518 | T2 FULTON-PUEBLO 9/45 RPR SPLW | ICW
LC | 125508426 | 004/057 | T2 JOLON TAP 4/57 GO95 CLEARANC | MOSSLNDG | ETL.7321.POLE.NWOD | 2023-02-15 | 2023-02-15 | 2024-01-23 | On-time | 2024-02-15 | 23 | 2024-02-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640151 | T2 JOLON TAP 4/56 GO95 | 93G
LC | 125508531 | 014/208 | T2 JOLON TAP 14/208 GO95 | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-15 | 2023-02-15 | 2024-01-28 | On-time | 2024-02-15 | 18 | 2024-02-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640151 | T2 JOLON TAP 4/56 GO95 | 93G
LC | 125508553 | 010/144 | T2 JOLON TAP 10/144 GO95 CLEARNCE | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-15 | 2023-02-15 | 2024-01-31 | On-time | 2024-02-15 | 15 | 2024-02-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640151 | T2 JOLON TAP 4/56 GO95 | 93G
LC | 125508789 | 018/374 | T2 EI COLGATE-PALERMO 18/374 RMV VEG | TABLEMTN | ETL.6500.POLE.NWOD | 2023-02-15 | 2023-02-15 | 2024-02-08 | On-time | 2024-02-15 | 7 | 2024-02-15 | 564 | TLV | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125508825 | 001/005 | T2 MENDOCINO-WILLITS 1/005 CLEARANCE | WILLITS | ETL.7540.POLE.WOOD | 2023-02-15 | 2023-02-15 | 2023-11-02 | On-time | 2024-02-15 | 105 | 2024-02-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640261 | MENDOCINO-WILLITS 1/005 CLEARANCE | 93G
LC | 125508828 | 000/016 | T2 CARIBOU-WESTWOOD 0/16 GO95 | TABLEMTN | ETL.6300.POLE.WOOD | 2023-02-15 | 2023-02-15 | 2023-11-28 | On-time | 2024-02-15 | 79 | 2024-02-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640155 | T2 CARIBOU-WESTWOOD 0/16 GO95 | 93G
LC | 125508903 | 005/009 | T2 MENDOCINO-WILLITS 5/009 CLEARANCE | WILLITS | ETL.7540.POLE.NWOD | 2023-02-15 | 2023-02-15 | 2023-11-04 | On-time | 2024-02-15 | 103 | 2024-02-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640261 | MENDOCINO-WILLITS 1/005 CLEARANCE | 93G
LC | 125509067 | 007/007 | T2 TULUCAY-NAPA #1 7/007 RPR GYWW | LAKEVLLE | ETL.8180.POLE.NWOD | 2023-02-15 | 2023-02-15 | 2024-01-16 | On-time | 2024-02-15 | 30 | 2024-02-15 | 630 | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 45927600 | T2 TULUCAY-NAPA #1 7/007 RPR GYWW | ICW
LC | 125550352 | 005/067 | T2 DI DIVIDE-CBRLLO #2 5/67 RPL HRDD | PISMOBCH | ETL.1370.POLE.WOOD | 2023-02-24 | 2023-02-15 | 2024-01-04 | On-time | 2024-02-15 | 42 | 2024-02-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46037138 | T2 DI DIVIDE-CBRLLO #2 5/67 RPL HRDD | ICW
LC | 125547169 | 009/042 | T2 DIABLO-MESA 9/42 RPL INSS | PISMOBCH | ETL.4620.INSL.NCER | 2023-02-23 | 2023-02-23 | 2024-05-16 | Late | 2024-02-23 | -83 | 2024-02-23 | 532 | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31664764 | T2 DIABLO-MESA 9/42 RPL INSS | 93K
LC | 125551775 | 004/021 | T2 DI SL BSP-CAYUCOS 4/21 RPL POLE | PISMOBCH | ETL.9090.POLE.WOOD | 2023-02-24 | 2023-02-15 | 2024-01-13 | On-time | 2024-02-15 | 33 | 2024-02-15 | 372T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481622 | T2 DI SL BSP-CAYUCOS 4/21 RPL POLE | 70Y
LC | 125552926 | 004/024 | T2 DI SNLUS OBPO CYCOS 4/024R RPL POLE | PISMOBCH | ETL.9090.POLE.WDPS | 2023-02-24 | 2023-02-15 | 2023-08-11 | On-time | 2024-02-15 | 188 | 2023-08-15 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31639350 | T2 DI SNLUS OBPO CYCOS 4/024 RPL POLE | 70Y
LC | 125547922 | 005/031 | T2 DI SNLUS OBPO CYCOS 5/031 RPR GYWS | PISMOBCH | ETL.9090.POLE.NWOD | 2023-02-23 | 2023-02-14 | 2024-05-12 | Late | 2024-02-14 | -88 | 2024-02-14 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45945131 | T2 DI SNLUS OBPO CYCOS 5/031 RPR GYWS | ICS
LC | 125552956 | 004/024 | T2 DI SNLUS OBPO CYCOS 4/024 RPL POLE | PISMOBCH | ETL.9090.POLE.WDPS | 2023-02-24 | 2023-02-15 | 2023-08-11 | On-time | 2024-02-15 | 188 | 2023-08-15 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31639350 | T2 DI SNLUS OBPO CYCOS 4/024 RPL POLE | 70Y
LC | 125553561 | 009/043 | T2 DI SL BSP-OCEANO 9/43 RPR STRT | PISMOBCH | ETL.3530.TOWR | 2023-02-24 | 2023-02-15 | 2023-09-05 | On-time | 2024-02-15 | 163 | 2024-02-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45943354 | T2 DI SL BSP-OCEANO 9/43 RPR STRT | ICQ
LC | 125556619 | 013/120 | T2 DI BRIDGEVILLE CTTNWD 13/120 RPR INSW | TABLEMTN | ETL.1110.INSL.NCER | 2023-02-25 | 2023-02-15 | 2024-01-15 | On-time | 2024-02-15 | 31 | 2024-02-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45698329 | T2 DI BRIDGEVILLE CTTNWD 13/120 RPR INSW | ICW
LC | 125557934 | 004/025 | T2 DI SL BSP-CAUYCOS 4/25 G095 USAGE | PISMOBCH | ETL.9090.POLE.WOOD | 2023-02-25 | 2023-02-15 | 2024-01-13 | On-time | 2024-02-15 | 33 | 2024-02-15 | 401 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654420 | T2 DI SL BSP-CAUYCOS 4/25 G095 USAGE | 93G
LC | 125563237 | 010/091B | T2 DI CTTNWD BNTON#2 10/091B RPL HRDW | TABLEMTN | ETL.6650.POLE.WOOD | 2023-02-27 | 2023-02-15 | 2023-11-09 | On-time | 2024-02-15 | 98 | 2024-02-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45698579 | T2 DI CTTNWD BNTON#2 10/091B RPL HRDW | ICW
LC | 125564086 | 004/084 | T2 DI DELTA-MTN GATE 4/84 RPR SPLW | TABLEMTN | ETL.6750.INSL.NCER | 2023-02-27 | 2023-02-15 | 2023-09-16 | On-time | 2024-02-15 | 152 | 2024-02-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45698628 | T2 DI DELTA-MTN GATE 4/84 RPR SPLW | ICW
LC | 125574048 | 007/143 | T2 CNTRVL-TB-MT-ORVL 7/143 GO95 CLEAR | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-01 | 2023-02-15 | 2023-07-22 | On-time | 2024-02-15 | 208 | 2024-02-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31639070 | T2 CNTRVILLE-TBL MTN-RVILLE 7/142 GO 95 | 93G
LC | 125513637 | A002/031 | T2 NARROWS #2 TAP A002/031 RPL SWTC | SACTO | ETL.6521.POLE.WOOD | 2023-02-16 | 2023-02-16 | 2023-12-13 | On-time | 2024-02-16 | 65 | 2024-02-16 | 427 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Wood | Replace | 31654423 | T2 NARROWS #2 TAP A002/031 RPL SWTC | 93H
LC | 125514252 | 018/359 | T2 EI COLGATE-PALERMO 18/359 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-02-16 | 2023-02-16 | 2023-10-31 | On-time | 2024-02-16 | 108 | 2024-02-16 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31663433 | T2 EI COLGATE-PALERMO 18/359 RPL POLE | 70Y
LC | 125515005 | 007/097 | T2 DI IGNCO BLNAS#2 7/097 RPR INSW | LAKEVLLE | ETL.7180.INSL.CERA | 2023-02-16 | 2023-02-16 | 2023-10-03 | On-time | 2024-02-16 | 136 | 2024-02-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45927603 | T2 DI IGNCO BLNAS#2 7/097 RPR INSW | ICW
LC | 125554776 | 007/050 | T2 DI IGNACI-ALTO-SAUSLTO #1 7/50 COTTER | LAKEVLLE | ETL.7170.INSL.CERA | 2023-02-24 | 2023-02-16 | 2023-10-25 | On-time | 2024-02-16 | 114 | 2024-02-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45927602 | T2 DI IGNACI-ALTO-SAUSLTO #1 7/50 COTTER | ICS
LC | 125558303 | 007/097-GUY | T2 DI IGNACIO-BOLINAS #2 7/97-GY RMV VEG | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-25 | 2023-02-16 | 2023-09-20 | On-time | 2024-02-16 | 149 | 2024-02-16 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125572354 | 009/078 | T2 DI CBRLL-SNT YNZ 9/78 RPL INSW | PISMOBCH | ETL.1200.INSL.NCER | 2023-03-01 | 2023-02-16 | 2024-01-30 | On-time | 2024-02-16 | 17 | 2024-02-16 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31645483 | T2 DI CBRLL-SNT YNZ SW 2/12 RPL INSW | 93I
LC | 125552077 | 002/016 | T2 DI LWER LAKE HMESTAKE 2/16 RPR GYWW | WILLITS | ETL.1481.POLE.WOOD | 2023-02-24 | 2023-02-14 |  | Late | 2024-02-14 |  | 2024-02-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45927607 | T2 DI LWER LAKE HMESTAKE 2/16 RPR GYWW | ICW
LC | 125574270 | 000/012 | T2 DI WSHN-SN JOAQUIN #3 0/12 RPL HRDD | FRESNO | ETL.9340.POLE.WOOD | 2023-03-01 | 2023-02-16 | 2023-11-30 | On-time | 2024-02-16 | 78 | 2024-02-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45954701 | T2 DI WSHN-SN JOAQUIN #3 0/12 RPL HRDD | ICW
LC | 125577274 | 000/013 | T2 DI WSHN-SN JOAQUIN #3 0/13 RMV DBRS | FRESNO | ETL.9340.POLE.NWOD | 2023-03-02 | 2023-02-16 | 2023-11-30 | On-time | 2024-02-16 | 78 | 2024-02-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 45954702 | T2 DI WSHN-SN JOAQUIN #3 0/13 RMV DBRS | ICW
LC | 125552920 | 005/069 | T2 DI DIVIDE CABRILLO #1 05/069 RPL POLE | PISMOBCH | ETL.1380.POLE.WOOD | 2023-02-24 | 2023-02-15 | 2024-06-20 | Late | 2024-02-15 | -126 | 2024-02-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507490 | T2 DI DIVIDE CABRILLO #1 05/069 RPL POLE | 70Y
LC | 125577642 | 002/005 | T2 DI LAURELES OTTER 2/5 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-03-02 | 2023-02-16 | 2024-01-27 | On-time | 2024-02-16 | 20 | 2024-02-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486636 | T2 DI LAURELES-OTTER 2/2 RPL POLE | 70Y
LC | 125577872 | 000/009 | T2NT DI LAURELES OTTER 0/9 RMV VEG | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-03-02 | 2023-02-16 | 2023-10-12 | On-time | 2024-02-16 | 127 | 2024-02-16 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125577972 | 010/010 | T2 DI LWR LK-HMSTK 10/10 RMV VEG | WILLITS | ETL.1481.POLE.WOOD | 2023-03-02 | 2023-02-16 | 2023-09-27 | On-time | 2024-02-16 | 142 | 2024-02-16 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125553395 | 005/072 | T2 DI JOLON 5/72 RPL POLE | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-24 | 2023-02-14 |  | Late | 2024-02-14 |  | 2024-02-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35563939 | T2 DI JOLON 5/72 RPL POLE | 70Y
LC | 125584677 | 000/008 | T2 DI WSHN SN JOQUIN#3 0/008 RPR STRW | FRESNO | ETL.9340.POLE.WOOD | 2023-03-03 | 2023-02-16 | 2023-11-30 | On-time | 2024-02-16 | 78 | 2024-02-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45954703 | T2 DI WSHN SN JOQUIN#3 0/008 RPR STRW | ICW
LC | 125641641 | 019/121 | T2 DI SN LS OBISPO-OCEANO 19/121 RNV VEG | PISMOBCH | ETL.3530.POLE.WOOD | 2023-03-12 | 2023-02-16 | 2024-02-12 | On-time | 2024-02-16 | 4 | 2024-02-16 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125642137 | 006/044 | T2 DI IGNCIO-ALTO-SASALTO#1 06/44 RPR ST | LAKEVLLE | ETL.7160.TOWR | 2023-03-12 | 2023-02-16 | 2023-10-02 | On-time | 2024-02-16 | 137 | 2024-02-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46004103 | T2 DI IGNCIO-ALTO-SASALTO#1 06/44 RPR ST | ICQ
LC | 125584421 | 016/080 | T2 DI TIDEWTR-SBRNT 16/80 RPL HRDW | CONCORD | ETL.5770.TOWR | 2023-03-03 | 2023-02-17 | 2023-10-31 | On-time | 2024-02-17 | 109 | 2024-02-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45937203 | T2 DI TIDEWTR-SBRNT 16/80 RPL HRDW | ICQ
LC | 125584423 | 016/080 | T2 DI TIDEWTR-SBRNT 16/80 RPR SHIELD | CONCORD | ETL.5770.TOWR | 2023-03-03 | 2023-02-17 | 2023-09-01 | On-time | 2024-02-17 | 169 | 2024-02-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45927741 | T2 DI TIDEWTR-SBRNT 16/80 RPR SHIELD | ICS
LC | 125554241 | 005/073 | T2 DI JOLON TAP 5/73 RPL STRW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-02-24 | 2023-02-14 |  | Late | 2024-02-14 |  | 2024-02-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35561408 | T2 DI JOLON TAP 5/73 RPL STRW | 70Y
LC | 125584433 | 019/093 | T2 DI TIDEWTR-SBRNT 19/93 RPR SHIELD | CONCORD | ETL.5770.TOWR | 2023-03-03 | 2023-02-17 | 2023-09-01 | On-time | 2024-02-17 | 169 | 2024-02-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45927743 | T2 DI TIDEWTR-SBRNT 19/93 RPR SHIELD | ICS
LC | 125642446 | 001/010 | T2 DI MENDOCINO-HARTLEY 001/10 RPR INSW | WILLITS | ETL.7510.INSL.NCER | 2023-03-12 | 2023-02-17 | 2023-09-20 | On-time | 2024-02-17 | 150 | 2024-02-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45927613 | T2 DI MENDOCINO-HARTLEY 001/10 RPR INSW | ICW
LC | 125642589 | 001/017 | T2 DI SBRNT-GRZLY-CLMT#1 1/17 RPR STRT | CONCORD | ETL.3740.TOWR | 2023-03-12 | 2023-02-17 | 2023-12-21 | On-time | 2024-02-17 | 58 | 2024-02-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45937159 | T2 DI SBRNT-GRZLY-CLMT#1 1/17 RPR STRT | ICQ
LC | 125557702 | 005/043 | T2 DI IGNCO ALTO SUSLTO#1 5/43 COMPLETE | LAKEVLLE | ETL.7160.TOWR | 2023-02-25 | 2023-02-17 | 2024-03-26 | Late | 2024-02-17 | -38 | 2024-02-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45978227 | T2 DI IGNCO ALTO SUSLTO#1 5/043 RPR STRT | ICQ
LC | 125557705 | 005/043 | T2 DI IGNCO ALTO SUSLTO#1 5/43 RPL HRDT | LAKEVLLE | ETL.7160.INSL | 2023-02-25 | 2023-02-17 | 2024-03-14 | Late | 2024-02-17 | -26 | 2023-05-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45895008 | T2 DI IGNCO ALTO SUSLTO#2 5/043 RPL HRDT | ICQ
LC | 125557706 | 005/043 | T2 DI IGNCO ALTO SUSLTO#1 5/43 RPL INSS | LAKEVLLE | ETL.7160.INSL | 2023-02-25 | 2023-02-17 | 2024-03-14 | Late | 2024-02-17 | -26 | 2023-05-17 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31668656 | DI IGNCO ALTO SUSLTO#1 5/043 RPL INSS | 93K
LC | 125577322 | 000/007 | T2 DI LAURELES-OTTER 0/7 RMV VEG | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-03-02 | 2023-02-17 | 2024-02-23 | Late | 2024-02-17 | -6 | 2024-02-17 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125612356 | 002/000 | T2 DI MNDCN-PHL JT-HPLND 2/0(L) RPL ANCW | WILLITS | ETL.7520.POLE.WDPS | 2023-03-08 | 2023-02-17 | 2024-03-19 | Late | 2024-02-17 | -31 | 2024-02-17 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35480879 | T2 DI MNDCN-PHL JT-HPLND 2/0(L) RPL ANCW | 93E
LC | 125642577 | 006/045 | T2 DI IGNACIO-ALTO-SLITO#1 6/45 RPR STRT | LAKEVLLE | ETL.7160.TOWR | 2023-03-12 | 2023-02-17 |  | Late | 2024-02-17 |  | 2024-02-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45978228 | T2 DI IGNACIO-ALTO-SLITO#1 6/45 RPR STRT | ICQ
LC | 125555245 | 004/014 | T2 DI LOWER LAKE-HOMESTAKE 4/14 COTTER | WILLITS | ETL.1481.INSL.NCER | 2023-02-24 | 2023-02-16 |  | Late | 2024-02-16 |  | 2024-02-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45927617 | T2 DI LOWER LAKE-HOMESTAKE 04/014 COTTER | ICW
LC | 126911793 | 005/048 | T3 DI SLY CREEK TAP 5/48C RPL POLE | TABLEMTN | ETL.4221.POLE.STPS | 2023-08-25 | 2023-08-24 |  | Late | 2024-02-24 |  | 2024-02-24 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Structure-Wood | Replace | 31618005 | T3 DI SLY CREEK TAP 5/48L RPL POLE | 70Y
LC | 126913185 | 016/134 | T3 DI PARADISE-TBL MTN 16/134R RPR GYWW | TABLEMTN | ETL.4316.POLE.STPS | 2023-08-25 | 2023-08-24 | 2023-10-17 | On-time | 2024-02-24 | 130 | 2023-11-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45974105 | T3 DI PARADISE-TBL MTN 16/134 RPR GYWW | ICW
LC | 125570477 | 007/004 | T2 DI MNDCNO #1 7/4 COTTER | WILLITS | ETL.7530.INSL.NCER | 2023-02-28 | 2023-02-24 |  | Late | 2024-02-24 |  | 2024-02-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45956917 | T2 DI MNDCNO-PHL-HPLND 7/4 COTTER | ICS
LC | 125525545 | 001/021 | T2 WEIMAR #1 01/21 RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2023-02-18 | 2023-02-18 | 2023-11-05 | On-time | 2024-02-18 | 105 | 2024-02-18 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481579 | T2 WEIMAR #1 01/21 RPL POLE | 70Y
LC | 125525546 | 000/021 | T2 EI COLGATE-CHALLENGE 0/21 RPL POLE | SACTO | ETL.6480.POLE.WOOD | 2023-02-18 | 2023-02-18 | 2023-12-01 | On-time | 2024-02-18 | 79 | 2024-02-18 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481563 | T2 EI COLGATE-CHALLENGE 0/21 RPL POLE | 70Y
LC | 125525702 | 001/021A | T2 EI WEIMAR #1 01/21A RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2023-02-18 | 2023-02-18 | 2023-11-05 | On-time | 2024-02-18 | 105 | 2024-02-18 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481600 | T2 EI WEIMAR #1 01/21A RPL POLE | 70Y
LC | 125525722 | 004/021 | T2 EI PITTSBURG-SAN RAMON 4/21 RPR FOND | CONCORD | ETL.5490.TOWR | 2023-02-18 | 2023-02-18 | 2024-02-05 | On-time | 2024-02-18 | 13 | 2024-02-18 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45937208 | T2 EI PITTSBURG-SAN RAMON 4/21 RPR FOND | ICQ
LC | 125525876 | 001/023 | T2 EI COLGATE-CHALLENGE 1/23 RPL POLE | SACTO | ETL.6480.POLE.WOOD | 2023-02-18 | 2023-02-18 | 2023-11-18 | On-time | 2024-02-18 | 92 | 2024-02-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481564 | T2 EI COLGATE-CHALLENGE 1/23 RPL POLE | 70Y
LC | 125525878 | 000/001 | T2 EI COLGATE-SMARTVILLE #2 0/1 RPR GYWW | SACTO | ETL.6520.POLE.WOOD | 2023-02-18 | 2023-02-18 | 2023-08-17 | On-time | 2024-02-18 | 185 | 2024-02-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45929125 | T2 EI COLGATE-SMARTVILLE #2 0/1 RPR GYWW | ICW
LC | 125525879 | 000/001 | T2 EI COLGATE-SMARTVILLE #2 0/1 COTTER | SACTO | ETL.6520.INSL.CERA | 2023-02-18 | 2023-02-18 | 2023-08-17 | On-time | 2024-02-18 | 185 | 2024-02-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45929126 | T2 EI COLGATE-SMARTVILLE #2 0/1 COTTER | ICW
LC | 125529801 | 022/004 | T2 EI PHILO JCT-ELK 22/04 RPR STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-02-20 | 2023-02-20 | 2023-09-12 | On-time | 2024-02-20 | 161 | 2024-02-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45935108 | T2 EI PHILO JCT-ELK 22/04 RPR STRW | ICW
LC | 125529867 | 059/534 | T2 EI PIT #1-CTTNWD 59/534 RPR GYWS | TABLEMTN | ETL.5390.TOWR | 2023-02-20 | 2023-02-20 | 2023-09-30 | On-time | 2024-02-20 | 143 | 2024-02-20 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45935262 | T2 EI PIT #1-CTTNWD 59/534 RPR GYWS | ICS
LC | 125530204 | 011/192 | T2 EI TEJON-LEBEC 011/192 RPL POLE | MIDWAY | ETL.9250.POLE.WOOD | 2023-02-20 | 2023-02-20 | 2023-10-14 | On-time | 2024-02-20 | 129 | 2024-02-20 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663426 | T2 EI TEJON-LEBEC 010/176 RPL POLE | 70Y
LC | 125530698 | 007/143 | T2 EI CTRVL-TBL MTN-RVI 007/143 INST DMW | TABLEMTN | ETL.6330.INSL.NCER | 2023-02-20 | 2023-02-20 | 2023-12-01 | On-time | 2024-02-20 | 81 | 2024-02-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 45698338 | T2 EI CNTRVIL-TBL MTN-RVI 7/143 INST DMW | ICW
LC | 125530882 | 020/011 | T2 EI PHILO JCT-ELK 20/11 COTTER | WILLITS | ETL.7780.INSL.NCER | 2023-02-20 | 2023-02-20 | 2023-09-13 | On-time | 2024-02-20 | 160 | 2024-02-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45935104 | T2 EI PHILO JCT-ELK 20/11 COTTER | ICW
LC | 125574058 | 005/003 | T2 DI MENDOCINO #1 5/3 RPL INSS | WILLITS | ETL.7530.INSL.CERA | 2023-03-01 | 2023-02-24 |  | Late | 2024-02-24 |  | 2024-02-24 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667792 | T2 DI MENDOCINO #1 5/3 RPL INSS | 93K
LC | 125576184 | 005/005 | T2 DI MNDCNO-PHLO JT HPLND 5/5 RPR CNDS | WILLITS | ETL.7520.INSL.CERA | 2023-03-01 | 2023-02-24 |  | Late | 2024-02-24 |  | 2024-02-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 45956916 | T2 DI MNDCNO PHLO JT HPLND 5/5 RPR CNDS | ICS
LC | 125551928 | 020/399 | T2 EI COLGATE-PALERMO 020/399 RPL INSW | SACTO | ETL.6500.INSL.NCER | 2023-02-24 | 2023-02-24 | 2023-11-01 | On-time | 2024-02-24 | 115 | 2024-02-24 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35483185 | T2 EI COLGATE-PALERMO 020/399 RPL INSW | 93I
LC | 125532256 | 024/289B | T2 DRUM-SUMMIT #2 24/289B RPL GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-02-21 | 2023-02-21 | 2023-08-25 | On-time | 2024-02-21 | 180 | 2024-02-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45935750 | T2 DRUM-SUMMIT #2 24/289B RPL GYWW | ICW
LC | 125557951 | 005/070 | T2 DI DIVIDE-CABRILLO #1 05/070 RPL POLE | PISMOBCH | ETL.1380.POLE.WOOD | 2023-02-25 | 2023-02-15 | 2024-06-20 | Late | 2024-02-15 | -126 | 2024-02-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507490 | T2 DI DIVIDE CABRILLO #1 05/069 RPL POLE | 70Y
LC | 125533197 | 001/041 | T2 EI COLGATE-ALLEGHANY 1/41 RPR GYWW | SACTO | ETL.6470.POLE.NWOD | 2023-02-21 | 2023-02-21 | 2023-11-10 | On-time | 2024-02-21 | 103 | 2024-02-21 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45935745 | T2 EI COLGATE-ALLEGHANY 1/41 RPR GYWW | ICS
LC | 125533268 | 005/069B | T2 DIVIDE-CABRILLO #2 5/69B COTTER | PISMOBCH | ETL.1370.POLE.NWOD | 2023-02-21 | 2023-02-21 | 2024-01-04 | On-time | 2024-02-21 | 48 | 2024-02-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45945128 | T2 DIVIDE-CABRILLO #2 5/69B COTTER | ICS
LC | 125558200 | 011/013 | T2 DI MNDCN-PHL-HPLND 11/13 RPL STRW | WILLITS | ETL.7520.POLE.WOOD | 2023-02-25 | 2023-02-14 |  | Late | 2024-02-14 |  | 2024-02-14 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663439 | T2 DI MNDCN-PHL-HPLND 11/13 RPL STRW | 70Y
LC | 125533765 | 001/043 | T2 EI COLGATE-ALLEGHANY 1/43 RPR INSW | SACTO | ETL.6470.INSL.CERA | 2023-02-21 | 2023-02-21 | 2023-11-10 | On-time | 2024-02-21 | 103 | 2024-02-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45935746 | T2 EI COLGATE-ALLEGHANY 1/43 RPR INSW | ICW
LC | 125558257 | 014/011 | T2 DI MNDCN-PHL-HPLND 14/11 RPL HRDD | WILLITS | ETL.7520.POLE.WOOD | 2023-02-25 | 2023-02-21 | 2024-03-20 | Late | 2024-02-21 | -28 | 2024-02-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45935103 | T2 DI MNDCN-PHL-HPLND 14/11 RPL HRDD | ICW
LC | 125533915 | 002/003 | T2 EI FULTON-HOPLAND 002/003 RPR GYWW | LAKEVLLE | ETL.6890.POLE.NWOD | 2023-02-21 | 2023-02-21 | 2023-09-20 | On-time | 2024-02-21 | 154 | 2024-02-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45937370 | T2 EI FULTON-HOPLAND 002/003 RPR GYWW | ICW
LC | 125561201 | 012/048 | T2 EI DIABLO-MIDWAY #2 12/48 RMV ENCRCH | PISMOBCH | ETL.5970.TOWR | 2023-02-27 | 2023-02-27 |  | Late | 2024-02-27 |  | 2024-02-27 | 931 | TLS | INSP | E - Schd Compl Yr 0 | Open | TR2 | Encroachment | Right of Way | Remove
LC | 125534049 | 159/1214 | T2 EI DELEVAN-VACA #2 159/1214 RPL INSS | SACTO | ETL.4231.INSL.CERA | 2023-02-21 | 2023-02-21 | 2023-10-09 | On-time | 2024-02-21 | 135 | 2024-02-21 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667696 | T2 EI DELEVAN-VACA #2 159/1214 RPL INSS | 93K
LC | 125534242 | 012/247 | T2 EI LAKEVILLE #2 12/247 RPR POLE | LAKEVLLE | ETL.7340.POLE.WOOD | 2023-02-21 | 2023-02-21 | 2023-11-30 | On-time | 2024-02-21 | 83 | 2024-02-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45934897 | T2 EI LAKEVILLE #2 12/247 RPR POLE | ICW
LC | 125534445 | 000/010 | T2 EI ROLLINS TAP 00/10 RPR GYWW | SACTO | ETL.6762.POLE.WOOD | 2023-02-21 | 2023-02-21 | 2023-09-04 | On-time | 2024-02-21 | 170 | 2024-02-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45935747 | T2 EI ROLLINS TAP 00/10 RPR GYWW | ICW
LC | 125535801 | 002/066 | T2 EI COLGATE-ALLEGHANY 2/66 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2023-02-21 | 2023-02-21 | 2023-11-09 | On-time | 2024-02-21 | 104 | 2024-02-21 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35482860 | T2 EI COLGATE-ALLEGHANY 1/52 RPL POLE | 70Y
LC | 125535835 | 023/006B | T2 EI PHILO JCT-ELK 23/006B RPL INSW | WILLITS | ETL.7780.INSL.NCER | 2023-02-21 | 2023-02-21 | 2023-09-12 | On-time | 2024-02-21 | 162 | 2024-02-21 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35483030 | PHILO JCT-ELK 23/006B RPL INSW-POST EST | 93I
LC | 125561954 | 005/068 | T2 DI GRN VLY CMP EVRS 5/68L RPL STRW | MOSSLNDG | ETL.1710.POLE.WDPS | 2023-02-27 | 2023-02-14 | 2024-03-29 | Late | 2024-02-14 | -44 | 2024-02-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35523959 | T2 DI GRN VLY CMP EVRS 5/68L RPL STRW | 70Y
LC | 125561955 | 005/068 | T2 DI GRN VLY CMP EVRS 5/68R RPL STRW | MOSSLNDG | ETL.1710.POLE.WDPS | 2023-02-27 | 2023-02-14 | 2024-03-29 | Late | 2024-02-14 | -44 | 2024-02-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35523959 | T2 DI GRN VLY CMP EVRS 5/68L RPL STRW | 70Y
LC | 125536613 | 004/031C | T2 EI TRNTY-CTTNWD 4/31C RPR INSW | TABLEMTN | ETL.4040.INSL.NCER | 2023-02-21 | 2023-02-21 | 2023-08-28 | On-time | 2024-02-21 | 177 | 2024-02-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45698639 | T2 EI TRNTY-CTTNWD 4/31C RPR INSW | ICW
LC | 125536937 | 001/010 | T2 EI KANAKA TAP 1/10R RPR GYWW | TABLEMTN | ETL.4223.POLE.STPS | 2023-02-21 | 2023-02-21 | 2023-10-11 | On-time | 2024-02-21 | 133 | 2024-02-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698634 | T2 EI KANAKA TAP 1/10R RPR GYWW | ICW
LC | 125536939 | 001/012 | T2 EI KANAKA TAP 1/12C RPR GYWW | TABLEMTN | ETL.4223.POLE.STPS | 2023-02-21 | 2023-02-21 | 2023-10-11 | On-time | 2024-02-21 | 133 | 2024-02-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698635 | T2 EI KANAKA TAP 1/12C RPR GYWW | ICW
LC | 125536993 | 001/012 | T2 EI KANAKA TAP 1/12L RPR GYWW | TABLEMTN | ETL.4223.POLE.STPS | 2023-02-21 | 2023-02-21 | 2023-10-11 | On-time | 2024-02-21 | 133 | 2024-02-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698636 | T2 EI KANAKA TAP 1/12L RPR GYWW | ICW
LC | 125563486 | 017/073 | T2 WV GEYSERS #12-FULTON 17/73 RPL INSS | LAKEVLLE | ETL.4750.INSL.CERA | 2023-02-27 | 2023-02-27 |  | Late | 2024-02-27 |  | 2024-02-27 | 532 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31539352 | 02 EI GEYSERS #12-FULTON 7 TWRS | 93K
LC | 125536994 | 001/012 | T2 EI KANAKA TAP 1/12R RPR GYWW | TABLEMTN | ETL.4223.POLE.STPS | 2023-02-21 | 2023-02-21 | 2023-10-11 | On-time | 2024-02-21 | 133 | 2024-02-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698637 | T2 EI KANAKA TAP 1/12R RPR GYWW | ICW
LC | 125563816 | 002/027 | T2 DI SANTA YNEZ TP 2/27 RPL STRW | PISMOBCH | ETL.3701.INSL.CERA | 2023-02-27 | 2023-02-23 |  | Late | 2024-02-23 |  | 2024-02-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493012 | T2 DI SANTA YNEZ TP 2/27 RPL STRW | 70Y
LC | 125536995 | 001/010 | T2 EI KANAKA TAP 1/10C RPR GYWW | TABLEMTN | ETL.4223.POLE.STPS | 2023-02-21 | 2023-02-21 | 2023-10-11 | On-time | 2024-02-21 | 133 | 2024-02-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698633 | T2 EI KANAKA TAP 1/10C RPR GYWW | ICW
LC | 125557993 | 003/020 | T2 DI PTSBRG-KRK-CLMB STL 3/20 RPL INSS | CONCORD | ETL.3310.INSL | 2023-02-25 | 2023-02-21 | 2023-12-11 | On-time | 2024-02-21 | 72 | 2024-02-21 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31664439 | T2 DI PTSBRG-KRK-CLMB STL 3/20 RPL INSS | 93K
LC | 125557995 | 003/020 | T2 DI PTSBRG-KRK-CLMB STL 3/20 RPL HRDT | CONCORD | ETL.3310.INSL | 2023-02-25 | 2023-02-21 | 2023-12-11 | On-time | 2024-02-21 | 72 | 2024-02-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45933834 | T2 DI PTSBRG-KRK-CLMB STL 3/20 RPL HRDT | ICQ
LC | 125561216 | 047/230B | T2 DI IGNCIO SBRNTE 47/230B RPR INSS | LAKEVLLE | ETL.4960.INSL.CERA | 2023-02-27 | 2023-02-21 | 2023-09-01 | On-time | 2024-02-21 | 173 | 2024-02-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45933837 | T2 DI IGNCIO SBRNTE 47/230B RPR INSS | ICS
LC | 125561247 | 003/019B | T2 DI PTSBURG CLYTN#4 3/019B RPL HRDT | CONCORD | ETL.3291.TOWR | 2023-02-27 | 2023-02-21 | 2023-10-31 | On-time | 2024-02-21 | 113 | 2024-02-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45934980 | T2 DI PTSBURG CLYTN#4 3/019B RPL HRDT | ICQ
LC | 125561754 | 003/017 | T2 DI PTSBURG CLYTN#3 3/17 BNT STEEL | CONCORD | ETL.3290.TOWR | 2023-02-27 | 2023-02-21 | 2024-01-09 | On-time | 2024-02-21 | 43 | 2024-02-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45937215 | T2 DI PTSBURG CLYTN#3 3/17 BNT STEEL | ICQ
LC | 125562005 | 039/188 | T2 DI IGNCIO SBRNTE 39/188 RPR INSS | CONCORD | ETL.4960.INSL.NCER | 2023-02-27 | 2023-02-21 | 2023-10-12 | On-time | 2024-02-21 | 132 | 2024-02-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45934898 | T2 DI IGNCIO SBRNTE 39/188 RPR INSS | ICS
LC | 125566669 | 006/081 | T2 DI IGNACIO-BLNS #2 6/81 RPL POLE | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-02-28 | 2023-02-16 |  | Late | 2024-02-16 |  | 2024-02-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485465 | T2 DI IGNACIO-BLNS #2 6/81 RPL POLE | 70Y
LC | 125562837 | 003/018 | T2 DI PTTSBRG-CLYTN #4 3/18 RPR INSS | CONCORD | ETL.3291.INSL | 2023-02-27 | 2023-02-21 | 2023-10-20 | On-time | 2024-02-21 | 124 | 2024-02-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45933839 | T2 DI PTTSBRG-CLYTN #3 3/18 RPR INSS | ICS
LC | 125572895 | 010/114 | T2 DI VEDDER TAP 10/114 RPL POLE | MIDWAY | ETL.2141.POLE.WOOD | 2023-03-01 | 2023-02-21 | 2024-01-31 | On-time | 2024-02-21 | 21 | 2024-02-21 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663498 | T2 DI VEDDER 10/114 RPL POLE | 70Y
LC | 125584349 | 008/004 | T2 DI TULUCAY-NAPA #1 8/4 RPR INSW | LAKEVLLE | ETL.8180.INSL.NCER | 2023-03-03 | 2023-02-21 | 2024-01-16 | On-time | 2024-02-21 | 36 | 2024-02-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45934057 | T2 DI TULUCAY-NAPA #1 8/4 RPR INSW | ICW
LC | 125584420 | 008/004 | T2 DI TULUCAY-NAPA #1 8/4 RPL HRDD | LAKEVLLE | ETL.8180.POLE.WOOD | 2023-03-03 | 2023-02-21 | 2024-01-16 | On-time | 2024-02-21 | 36 | 2024-02-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45934896 | T2 DI TULUCAY-NAPA #1 8/4 RPL HRDD | ICW
LC | 125584458 | 008/043 | T2 DI CONTRA COSTA-MRGA #1 8/43 RPR INSS | CONCORD | ETL.5452.INSL.CERA | 2023-03-03 | 2023-02-21 | 2023-08-29 | On-time | 2024-02-21 | 176 | 2024-02-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45933835 | T2 DI CONTRA COSTA-MRGA #1 8/43 RPR INSS | ICS
LC | 125569395 | 015/013 | T2 DI MNDCNO-PHL-HPLND 15/13 COMPLETE | WILLITS | ETL.7520.POLE.NWOD | 2023-02-28 | 2023-02-23 | 2024-03-20 | Late | 2024-02-23 | -26 | 2023-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45935017 | T2 DI MNDCNO-PHL-HPLND 15/13 RPR GYWW | ICW
LC | 125584471 | 008/043 | T2 DI CONTRA COSTA-MRGA #1 8/43 RPL HRDT | CONCORD | ETL.5452.TOWR | 2023-03-03 | 2023-02-21 | 2023-08-29 | On-time | 2024-02-21 | 176 | 2024-02-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45933836 | T2 DI CONTRA COSTA-MRGA #1 8/43 RPL HRDT | ICQ
LC | 125585829 | :000/006 | T2 DI LKWD MDOW LN CLYTN 0/6 BENT STEEL | CONCORD | ETL.2080.TOWR | 2023-03-03 | 2023-02-21 | 2024-01-04 | On-time | 2024-02-21 | 48 | 2024-02-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45937212 | T2 DI LKWD MDOW LN CLYTN 0/6 BENT STEEL | ICQ
LC | 125642684 | 003/019 | T2 DI PITTSBRG-MARTINZ#1 3/19 RPR STRT | CONCORD | ETL.3320.TOWR | 2023-03-12 | 2023-02-21 | 2024-01-31 | On-time | 2024-02-21 | 21 | 2024-02-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45937216 | T2 DI PITTSBRG-MARTINZ#1 3/19 RPR STRT | ICQ
LC | 125570426 | 055/003 | T2 DI FRT ROSS GUALALA 55/003 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-02-28 | 2023-02-23 |  | Late | 2024-02-23 |  | 2024-02-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483022 | T2 DI FRT ROSS GUALALA 55/003 RPL STRW | 70Y
LC | 125570196 | 008/001 | T2 DI MNDCNO-PHL-HPLND 8/1 RPL HRDT | WILLITS | ETL.7520.POLE.NWOD | 2023-02-28 | 2023-02-24 | 2023-04-12 | On-time | 2024-02-24 | 318 | 2024-02-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Steel | Replace | 45716134 | T2 DI MNDCNO-PHL-HPLND 8/1 RPL HRDT | ICS
LC | 125538613 | 000/002 | T2 EI PHILO JCT-ELK 0/002 RPR POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-02-22 | 2023-02-22 | 2023-09-04 | On-time | 2024-02-22 | 171 | 2024-02-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45935100 | T2 EI PHILO JCT-ELK 0/002 RPR POLE | ICW
LC | 125538718 | 004/032 | T2 EI TRNTY-CTTNWD 4/32L RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-02-22 | 2023-02-22 | 2023-03-21 | On-time | 2024-02-22 | 338 | 2023-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698582 | T2 EI TRNTY-CTTNWD 4/32L RPR GYWW | ICW
LC | 125571719 | :000/003 | T2 BLOTA-RVRBNK-MLONS SS :00/03 RPL POLE | VICTOR | ETL.1070.POLE.WOOD | 2023-03-01 | 2023-02-28 |  | Late | 2024-02-28 |  | 2024-02-28 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31639236 | T2 BLOTA-RVRBNK-MLONS SS :00/03 REFRAME | 93E
LC | 125571750 | 091/464 | T2NT MALIN-RND MTN #2 91/464 COMPLETE | TABLEMTN | ETL.6020.TOWR | 2023-03-01 | 2023-03-01 | 2024-03-26 | Late | 2024-02-29 | -26 | 2024-03-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46090910 | T2NT MALIN-ROUND MNTAN #2 91/464 BNT STL | ICQ
LC | 125539146 | 001/052 | T2 EI COLGATE-ALLEGHANY 1/52 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2023-02-22 | 2023-02-22 | 2023-11-09 | On-time | 2024-02-22 | 105 | 2024-02-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35482860 | T2 EI COLGATE-ALLEGHANY 1/52 RPL POLE | 70Y
LC | 125539733 | 056/003 | T2 HUMBOLDT-TRINITY 56/3L RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2023-02-22 | 2023-02-22 | 2023-08-10 | On-time | 2024-02-22 | 196 | 2024-02-22 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31639420 | T2 HUMBOLDT-TRINITY 56/3L RPL POLE | 70Y
LC | 125539736 | 056/003 | T2 HUMBOLDT-TRINITY 56/3R RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2023-02-22 | 2023-02-22 | 2023-08-10 | On-time | 2024-02-22 | 196 | 2024-02-22 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31639420 | T2 HUMBOLDT-TRINITY 56/3L RPL POLE | 70Y
LC | 125540101 | ;001/015 | T2 SNETH LNE-HF MN BAY ;1/15 INS WEIGHTS | METCALF | ETL.7212.INSL.NCER | 2023-02-22 | 2023-02-22 | 2023-02-22 | On-time | 2024-02-22 | 365 | 2024-02-22 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45946665 | T2 SNETH LNE-HF MN BAY ;1/15 INS WEIGHTS | ICW
LC | 125573681 | A012/272 | T2 DI SALINAS-LAURELES 12/272 RPR SPLW | MOSSLNDG | ETL.7930.INSL | 2023-03-01 | 2023-02-27 | 2024-04-18 | Late | 2024-02-27 | -51 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46080984 | T2 DI SALINAS-LAURELES 12/272 RPR SPLW | ICW
LC | 125540172 | C011/009 | T2 EI FULTON-CALISTOGA 11/9 RPL POLE | LAKEVLLE | ETL.6880.POLE.WOOD | 2023-02-22 | 2023-02-22 | 2023-10-13 | On-time | 2024-02-22 | 132 | 2024-02-22 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31639982 | T2 EI FULTON-CALISTOGA 11/9 RPL POLE | 70Y
LC | 125540351 | 007/088 | T2 DI VEDDER TAP 7/088 COMPLETED | MIDWAY | ETL.2141.INSL.CERA | 2023-02-22 | 2023-02-22 | 2023-08-17 | On-time | 2024-02-22 | 189 | 2023-08-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45706680 | T2 DI VEDDER TAP 7/088 RPR CONDW | ICW
LC | 125599018 | 017/001 | T2 DI MNDCNO-PHL-HPLND 17/1 RPR GYWW | WILLITS | ETL.7520.POLE.NWOD | 2023-03-06 | 2023-02-24 | 2023-04-11 | On-time | 2024-02-24 | 319 | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45726361 | T2 DI MNDCNO-PHL-HPLND 17/1 RPR GYWW | ICW
LC | 125574243 | 005/066 | T2 DI CLGTE SMRTVL#2 5/66C RPL ANCW | SACTO | ETL.6520.POLE.STPS | 2023-03-01 | 2023-02-27 | 2024-05-01 | Late | 2024-02-27 | -64 | 2024-02-27 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35487481 | T2 COLGATE-SMRTVL #2 05/66R RPL ANCW | 93E
LC | 125574246 | 005/066 | T2 DI CLGTE SMRTVL#2 5/66L RPL ANCW | SACTO | ETL.6520.POLE.STPS | 2023-03-01 | 2023-02-27 | 2024-05-01 | Late | 2024-02-27 | -64 | 2024-02-27 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35487481 | T2 COLGATE-SMRTVL #2 05/66R RPL ANCW | 93E
LC | 125540803 | 012/285 | T2 EI DRUM-GRSS VLLY-WMR 12/285 RPR INSW | SACTO | ETL.6760.INSL.CERA | 2023-02-22 | 2023-02-22 | 2023-09-20 | On-time | 2024-02-22 | 155 | 2024-02-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45935748 | T2 EI DRUM-GRSS VLLY-WMR 12/285 RPR INSW | ICW
LC | 125574350 | 000/013 | T2 DI LAURELES OTTER 0/13 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-03-01 | 2023-02-16 |  | Late | 2024-02-16 |  | 2024-02-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35486635 | T2 DI LAURELES OTTER 0/13 RPL STRW | 70Y
LC | 125574353 | 009/008 | T2 DI PHILO-ELK 9/8 RPL HRDD | WILLITS | ETL.7780.POLE.WOOD | 2023-03-01 | 2023-02-27 | 2024-05-07 | Late | 2024-02-27 | -70 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46213092 | T2 DI PHILO-ELK 9/8 RPL HRDD | ICW
LC | 125574354 | 009/008 | T2 DI PHILO-ELK 9/8 RPR INSW | WILLITS | ETL.7780.INSL.CERA | 2023-03-01 | 2023-02-27 | 2024-05-07 | Late | 2024-02-27 | -70 | 2023-08-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46210429 | T2 DI PHILO-ELK 9/8 RPR INSW | ICW
LC | 125574515 | 002/002 | T2 DI LAURELES-OTTER 2/2 RPL POLE | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-03-01 | 2023-02-16 | 2024-03-12 | Late | 2024-02-16 | -25 | 2024-02-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486636 | T2 DI LAURELES-OTTER 2/2 RPL POLE | 70Y
LC | 125574857 | 109/003 | T2 HUMBOLDT-TRINITY 109/3C RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2023-03-01 | 2023-03-01 |  | Late | 2024-02-29 |  | 2024-03-01 | 372 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31539397 | T2 EI HUMBOLDT TRINITY 112/001 RPL STRW | 70Y
LC | 125541245 | 004/037C | T2 EI TRNTY-COTTONWD 4/37C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-02-22 | 2023-02-22 | 2023-08-28 | On-time | 2024-02-22 | 178 | 2024-02-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698630 | T2 EI TRNTY-COTTONWD 4/37C RPR GYWW | ICW
LC | 125575189 | A016/351 | T2 DI SALINAS-LAURELES A16/351 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-03-01 | 2023-02-27 |  | Late | 2024-02-27 |  | 2024-02-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486638 | T2 DI SALINAS-LAURELES A16/351 RPL POLE | 70Y
LC | 125541651 | 004/006 | T2 EI FULTON-HOPLAND 004/006 RPL SPLW | LAKEVLLE | ETL.6890.INSL.CERA | 2023-02-22 | 2023-02-22 | 2023-09-25 | On-time | 2024-02-22 | 150 | 2024-02-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Replace | 45937372 | T2 EI FULTON-HOPLAND 004/006 RPL SPLW | ICW
LC | 125542162 | 005/000 | T2 EI FULTON-HOPLAND 005/000 RPR GYWW | LAKEVLLE | ETL.6890.POLE.NWOD | 2023-02-22 | 2023-02-22 | 2023-09-20 | On-time | 2024-02-22 | 155 | 2024-02-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45937373 | T2 EI FULTON-HOPLAND 005/000 RPR GYWW | ICW
LC | 125600358 | 014/177 | T2 DI ATSCDR SNLUS OBPO 14/177 RPR STRT | PISMOBCH | ETL.8490.TOWR | 2023-03-07 | 2023-02-24 | 2023-09-06 | On-time | 2024-02-24 | 171 | 2024-02-24 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45943349 | T2 DI ATSCDR SNLUS OBPO 14/177 RPR STRT | ICQ
LC | 125542745 | 006/057 | T2 EI BUCKS CREEK-ROCK 6/57 RPR FOND | TABLEMTN | ETL.4430.TOWR | 2023-02-22 | 2023-02-22 | 2023-10-30 | On-time | 2024-02-22 | 115 | 2024-02-22 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45945129 | T2 EI BUCKS CREEK-ROCK 6/57 RPR FOND | ICQ
LC | 125576356 | 003/007 | T2 DI PHILO JCT ELK 3/007 COTTER | WILLITS | ETL.7780.INSL.NCER | 2023-03-01 | 2023-02-28 | 2024-04-30 | Late | 2024-02-28 | -62 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45975337 | T2 DI PHILO JCT ELK 3/007 COTTER | ICW
LC | 125542790 | 006/052 | T2 EI BUCKS CREEK-ROCK CC 6/52 RPR FOND | TABLEMTN | ETL.4430.TOWR | 2023-02-22 | 2023-02-22 | 2023-10-26 | On-time | 2024-02-22 | 119 | 2024-02-22 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45945130 | T2 EI BUCKS CREEK-ROCK CC 6/52 RPR FOND | ICQ
LC | 125542791 | 006/053 | T2 EI BUCKS CREEK-ROCK CC 6/53 RPR FOND | TABLEMTN | ETL.4430.TOWR | 2023-02-22 | 2023-02-22 | 2023-10-30 | On-time | 2024-02-22 | 115 | 2024-02-22 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45945165 | T2 EI BUCKS CREEK-ROCK CC 6/53 RPR FOND | ICQ
LC | 125542858 | 005/002 | T2 MENDOCINO-HARTLEY-STELL 5/2 COTTER | WILLITS | ETL.7510.INSL.NCER | 2023-02-22 | 2023-02-22 | 2023-09-22 | On-time | 2024-02-22 | 153 | 2024-02-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45935019 | T2 MENDOCINO-HARTLEY-STELL 5/2 COTTER | ICW
LC | 125563937 | 007/088 | T2 DI VEDDER 7/88 INS HRDD | MIDWAY | ETL.2141.INSL.CERA | 2023-02-27 | 2023-02-22 | 2023-08-17 | On-time | 2024-02-22 | 189 | 2024-02-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45927414 | T2 DI VEDDER 7/88 INS HRDD | ICW
LC | 125601076 | 003/042 | T2 DI LAKEVILLE #1 3/42 ANCW RPR | LAKEVLLE | ETL.7360.POLE.WOOD | 2023-03-07 | 2023-02-24 | 2023-11-02 | On-time | 2024-02-24 | 114 | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46161567 | T2 DI LAKEVILLE #1 3/42 COMPLETE | ICW
LC | 125577267 | 006/076 | T2 DI VEDDER TAO 6/76 RPL HRDD | MIDWAY | ETL.2141.POLE.WOOD | 2023-03-02 | 2023-02-22 | 2023-08-17 | On-time | 2024-02-22 | 189 | 2024-02-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45927411 | T2 DI VEDDER TAO 6/76 RPL HRDD | ICW
LC | 125591614 | 002/020 | T2 DI SANTA YNEZ 2/20 RPL DMPW | PISMOBCH | ETL.3701.INSL.NCER | 2023-03-04 | 2023-02-22 | 2023-05-02 | On-time | 2024-02-22 | 296 | 2023-08-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 45706791 | T2 DI SANTA YNEZ 2/20 RPL DMPW | ICW
LC | 125613645 | 004/032 | T2 EI TRNTY-CTTNWD 4/32R RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-03-09 | 2023-02-22 | 2023-03-20 | On-time | 2024-02-22 | 339 | 2023-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698584 | T2 EI TRNTY-CTTNWD 4/32R RPR GYWW | ICW
LC | 125546291 | 000/002 | T2 EI BEALE AFB (WAPA) #2 0/2 RMV NEST | SACTO | ETL.7971.POLE.NWOD | 2023-02-23 | 2023-02-23 | 2023-08-09 | On-time | 2024-02-23 | 198 | 2023-08-23 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 45907246 | T2 EI BEALE AFB (WAPA) #2 0/2 RMV NEST | ICS
LC | 125561506 | 044/183 | T2 EI DIABLO-MIDWAY #2 044/183 RPR GYWT | PISMOBCH | ETL.5970.TOWR | 2023-02-27 | 2023-02-23 | 2024-01-29 | On-time | 2024-02-23 | 25 | 2024-02-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 45943352 | T2 EI DIABLO-MIDWAY #2 044/183 RPR GYWT | ICQ
LC | 125567932 | 001/005 | T2 DI SLO-CAYUCOS 001/005 RPR WEIGHT | PISMOBCH | ETL.9090.INSL.CERA | 2023-02-28 | 2023-02-23 | 2023-05-02 | On-time | 2024-02-23 | 297 | 2024-02-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 45706786 | DI T2 SLO-CAYUCOS 1/5 RPR WEIGHT | ICS
LC | 125567933 | 001/005 | T2 DI ATSCRO SNLS OBSPO 14/178 COTTER | PISMOBCH | ETL.9090.INSL.CERA | 2023-02-28 | 2023-02-23 | 2023-05-02 | On-time | 2024-02-23 | 297 | 2024-02-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45746688 | T2 DI ATSCRO SNLS OBSPO 14/178 COTTER | ICS
LC | 125568920 | 000/006 | T2 DI PIT#4 TAP 0/6 RPL INST | TABLEMTN | ETL.5432.INSL.CERA | 2023-02-28 | 2023-02-23 | 2023-10-02 | On-time | 2024-02-23 | 144 | 2024-02-23 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31664430 | T2 DI PIT#4 TAP 0/6 RPL INST | 93K
LC | 125568961 | 000/006 | T2 DI PIT#4 TAP 0/6 HANGER | TABLEMTN | ETL.5432.TOWR | 2023-02-28 | 2023-02-23 | 2023-10-02 | On-time | 2024-02-23 | 144 | 2024-02-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45936898 | T2 DI PIT#4 TAP 0/6 HANGER | ICQ
LC | 125570481 | 000/004 | T2 DI PIT#4 TAP 0/4 RPR STRT | TABLEMTN | ETL.5432.TOWR | 2023-02-28 | 2023-02-23 | 2023-10-03 | On-time | 2024-02-23 | 143 | 2024-02-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45945166 | T2 DI PIT#4 TAP 0/4 RPR STRT | ICQ
LC | 125592211 | 013/269 | T2 DI LAKEVILLE #2 13/269 RPR IBWW | LAKEVLLE | ETL.7340.POLE.WOOD | 2023-03-04 | 2023-02-23 | 2024-02-15 | On-time | 2024-02-23 | 8 | 2024-02-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45935060 | T2 DI LAKEVILLE #2 13/269 RPR IBWW | ICW
LC | 125592212 | 013/269 | T2 DI LAKEVILLE #2 13/269 RPL INSW | LAKEVLLE | ETL.7340.INSL.NCER | 2023-03-04 | 2023-02-23 | 2024-02-15 | On-time | 2024-02-23 | 8 | 2024-02-23 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35483025 | T2 DI LAKEVILLE #2 13/269 RPL INSW | 93I
LC | 125597091 | 055/008 | T2 DI FORT ROSS-GUALALA 55/8 RPR CRSW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-03-06 | 2023-02-23 | 2023-11-01 | On-time | 2024-02-23 | 114 | 2024-02-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45956914 | T2 DI FORT ROSS-GUALALA 55/8 RPR CRSW | ICW
LC | 125597249 | 000/005 | T2 DI ATSCDRO CYCUOS 0/005 INS IBWW | PISMOBCH | ETL.8480.POLE.NWOD | 2023-03-06 | 2023-02-23 | 2024-01-19 | On-time | 2024-02-23 | 35 | 2024-02-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088467 | T2 DI ATSCDRO CYCUOS 0/005 INS IBWW | ICW
LC | 125597546 | 011/078 | T2 DI IGCIO ALTO SUSLTO#1 11/078 BNT STL | LAKEVLLE | ETL.7160.TOWR | 2023-03-06 | 2023-02-23 | 2023-10-23 | On-time | 2024-02-23 | 123 | 2024-02-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46028431 | T2 DI IGCIO ALTO SUSLTO#1 11/078 BNT STL | ICQ
LC | 125578019 | 008/007 | T2 DI MNDCNO-HARTLEY 8/7 RPL ANCW | WILLITS | ETL.7510.POLE.WOOD | 2023-03-02 | 2023-02-28 |  | Late | 2024-02-28 |  | 2023-08-28 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35484589 | T2 DI MNDCNO-HARTLEY 8/7 RPL ANCW | 93E
LC | 125597667 | 023/117 | T2 DI FULTON IGNACIO #1 023/117 RPL INST | LAKEVLLE | ETL.4680.INSL | 2023-03-06 | 2023-02-23 | 2023-11-27 | On-time | 2024-02-23 | 88 | 2024-02-23 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31667716 | DI FULTON IGNACIO #1 023/117 RPL INST | 93I
LC | 125578286 | 013/005B | T2 HMBLDT-MPLE CRK 13/5B RPL CONDW | EUREKA | ETL.7130.INSL.NCER | 2023-03-02 | 2023-03-02 |  | Late | 2024-03-01 |  | 2024-03-02 | 638T | TLN | CREW | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 35484830 | T2 HMBLDT-MPLE CRK 13/5B RPL CONDW | 93C
LC | 125578626 | Z004/001 | T2 DI FLTN CLISTOGA Z004/001 CNCL | LAKEVLLE | ETL.6880.INSL.NCER | 2023-03-02 | 2023-03-01 |  | Late | 2024-02-29 |  | 2024-03-01 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667796 | T2 DI FLTN CLISTOGA Z004/001 RPL INSW | 93K
LC | 125579149 | 008/158 | T2 DI VALLEY SPRNGS #1 8/158 RPR INSW | VICTOR | ETL.8210.INSL.NCER | 2023-03-02 | 2023-03-01 | 2024-03-21 | Late | 2024-02-29 | -21 | 2024-03-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946240 | T2 DI VALLEY SPRNGS #1 8/158 RPR INSW | ICW
LC | 125597817 | 054/009 | T2 DI FORT ROSS-GUALALA 54/9 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-03-06 | 2023-02-23 | 2023-11-13 | On-time | 2024-02-23 | 102 | 2024-02-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45954917 | T2 DI FORT ROSS-GUALALA 54/9 RPR INSW | ICW
LC | 125598268 | 014/132 | T2 DI SLO-CAYUCOS 14/132 RPL STRW | PISMOBCH | ETL.9090.POLE.WOOD | 2023-03-06 | 2023-02-23 | 2024-01-11 | On-time | 2024-02-23 | 43 | 2024-02-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495581 | T2 DI SLO-CAYUCOS 14/132 RPL STRW | 70Y
LC | 125598329 | 014/131 | T2 DI SNLUS CYUCOS 14/131 ANTI SPLIT | PISMOBCH | ETL.9090.POLE.WOOD | 2023-03-06 | 2023-02-23 | 2024-01-10 | On-time | 2024-02-23 | 44 | 2024-02-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088314 | T2 DI SNLUS CYUCOS 14/131 ANTI SPLIT | ICW
LC | 125598516 | 011/070 | T2 DI CAYUCOS-CAMBRIA 11/70 RPR GYWW | PISMOBCH | ETL.8560.POLE.WOOD | 2023-03-06 | 2023-02-23 | 2024-01-15 | On-time | 2024-02-23 | 39 | 2024-02-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088468 | T2 DI CAYUCOS-CAMBRIA 11/70 RPR GYWW | ICW
LC | 125579670 | 001/037 | T2 EI CTTNWD-BNTN #1 001/037 RPL POLE | TABLEMTN | ETL.6640.POLE.WOOD | 2023-03-02 | 2023-03-02 |  | Late | 2024-03-01 |  | 2024-03-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35557729 | T2 EI CTTNWD-BNTN #1 001/037 RPL POLE | 70Y
LC | 125580146 | 006/100 | T2 EI SN MATEO-HILSDLE JCT 6/100 RMV VEG | METCALF | ETL.7950.POLE.STPS | 2023-03-02 | 2023-03-02 |  | Late | 2024-03-01 |  | 2024-03-02 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Trim
LC | 125598558 | 056/000 | T2 DI FORT ROSS GUALALA 56/000 RPL HRDD | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-03-06 | 2023-02-23 | 2023-11-01 | On-time | 2024-02-23 | 114 | 2024-02-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45956913 | T2 DI FORT ROSS GUALALA 56/000 RPL HRDD | ICW
LC | 125598615 | 011/071 | T2 DI CYUCOS CMBRIA 11/71 RPR GYWW | PISMOBCH | ETL.8560.POLE.NWOD | 2023-03-06 | 2023-02-23 | 2024-01-15 | On-time | 2024-02-23 | 39 | 2024-02-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088469 | T2 DI CYUCOS CMBRIA 11/71 RPR GYWW | ICW
LC | 125598714 | 008/063 | T2 DI VACA-SUISUN 008/063 RPR STRT | SACTO | ETL.4070.TOWR | 2023-03-06 | 2023-02-23 | 2023-10-10 | On-time | 2024-02-23 | 136 | 2024-02-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45945167 | T2 DI VACA-SUISUN 008/063 RPR STRT | ICQ
LC | 125598754 | 014/176 | T2 DI ATSCDR SNLUS OBPO 14/176 RPR STRT | PISMOBCH | ETL.8490.TOWR | 2023-03-06 | 2023-02-23 | 2023-09-06 | On-time | 2024-02-23 | 170 | 2024-02-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45943348 | T2 DI ATSCDR SNLUS OBPO 14/176 RPR STRT | ICQ
LC | 125598946 | 011/080 | T2 DI IGCIO ALTO SUSLTO#1 11/080 RMV VEG | LAKEVLLE | ETL.7160.TOWR | 2023-03-06 | 2023-02-23 | 2023-09-20 | On-time | 2024-02-23 | 156 | 2024-02-23 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125599869 | 010/217 | T2 DI SLNAS LURLES 10/217 RMV VEG | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-03-07 | 2023-02-23 | 2024-02-23 | On-time | 2024-02-23 | 0 | 2024-02-23 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125599884 | 008/065 | T2 DI VACA SUISUN 8/065 RMV VEG | SACTO | ETL.4070.TOWR | 2023-03-07 | 2023-02-23 | 2024-02-20 | On-time | 2024-02-23 | 3 | 2024-02-23 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125615973 | 012/011 | T2 DI LOWER LAKE-HOMESTKE 12/11 RPL HRDW | WILLITS | ETL.1481.POLE.WOOD | 2023-03-09 | 2023-02-23 | 2023-03-10 | On-time | 2024-02-23 | 350 | 2024-02-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45763185 | T2 DI LOWER LAKE-HOMESTKE 12/11 RPL HRDW | ICW
LC | 125604104 | 007/168 | T2 DI SALINAS-LAURELES 7/168 RMV VEG | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-03-07 | 2023-02-24 | 2024-02-22 | On-time | 2024-02-24 | 2 | 2024-02-24 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125605316 | A015/326 | T2 DI SLNS-LAURELES A015/326 RMV VEG | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-03-07 | 2023-02-24 | 2024-02-23 | On-time | 2024-02-24 | 1 | 2024-02-24 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125605449 | 007/078 | T2 DI COLGATE-SMARTVLLE #1 7/78 RPR POLE | SACTO | ETL.6510.POLE.WOOD | 2023-03-07 | 2023-02-24 | 2023-12-14 | On-time | 2024-02-24 | 72 | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45939758 | T2 DI COLGATE-SMARTVLLE #1 7/78 RPR POLE | ICW
LC | 125605477 | A015/324 | T2 DI SLNS-LAURELES A015/324 RMV VEG | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-03-07 | 2023-02-24 | 2024-02-23 | On-time | 2024-02-24 | 1 | 2024-02-24 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125584906 | 002/009 | T2 DI MNDCO PHLO JT HPLND 2/009 RPR GYWW | WILLITS | ETL.7520.POLE.NWOD | 2023-03-03 | 2023-02-16 |  | Late | 2024-02-16 |  | 2024-02-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45927618 | T2 DI MNDCO PHLO JT HPLND 2/009 RPR GYWW | ICW
LC | 125605478 | 011/201 | T2 DI VALLEY SPRINGS #2 11/201 INS IBWW | VICTOR | ETL.9460.POLE.WOOD | 2023-03-07 | 2023-02-24 | 2023-09-02 | On-time | 2024-02-24 | 175 | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45937536 | T2 DI VALLEY SPRINGS #2 11/201 INS IBWW | ICW
LC | 125605494 | 014/175 | T2 DI ATASCDR-SN LS OBSP 14/175 RPL HRD | PISMOBCH | ETL.8490.TOWR | 2023-03-07 | 2023-02-24 | 2023-09-06 | On-time | 2024-02-24 | 171 | 2024-02-24 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45943347 | T2 DI ATASCDR-SN LS OBSP 14/175 RPL HRD | ICQ
LC | 125606425 | 008/106 | T2 DI COLGATE SMARTVILL#1 8/106 RPR STRW | SACTO | ETL.6510.POLE.WOOD | 2023-03-08 | 2023-02-24 | 2023-12-12 | On-time | 2024-02-24 | 74 | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45939759 | T2 DI COLGATE SMARTVILL#1 8/106 RPR STRW | ICW
LC | 125589461 | 001/011 | T2 DI MELONES-RACETRACK 01/011 RPL POLE | VICTOR | ETL.2400.POLE.WOOD | 2023-03-03 | 2023-03-01 | 2024-05-11 | Late | 2024-02-29 | -72 | 2024-03-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493015 | T2 DI MELONES RACETRACK 01/011 RPL POLE | 70Y
LC | 125589462 | 036/009 | T2 DI PHILO JCT ELK 36/9 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-03-03 | 2023-03-01 | 2024-06-14 | Late | 2024-02-29 | -106 | 2024-03-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484594 | T2 DI PHILO JCT ELK 36/9 RPL POLE | 70Y
LC | 125589466 | 036/009 | T2 DI PHILO JCT ELK 36/009 RPR CNDW | WILLITS | ETL.7780.INSL.NCER | 2023-03-03 | 2023-03-01 | 2024-06-14 | Late | 2024-02-29 | -106 | 2024-03-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45976356 | T2 DI PHILO JCT ELK 36/009 RPR CNDW | ICW
LC | 125589681 | :031/199 | T2 DI NRTH TWR MZ JT#1 =31/199 RPR STRT | CONCORD | ETL.3130.TOWR | 2023-03-03 | 2023-03-01 |  | Late | 2024-02-29 |  | 2024-03-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45989475 | T2 DI NRTH TWR MZ JT#1 :31/199 RPR HRDT | ICQ
LC | 125607468 | 011/203 | T2 DI VALLEY SPRINGS#2 11/203 COMPLETE | VICTOR | ETL.9460.POLE.WOOD | 2023-03-08 | 2023-02-24 | 2024-02-14 | On-time | 2024-02-24 | 10 | 2024-02-24 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31665665 | T2 DI VALLEY SPRINGS#2 11/203 RPL POLE | 70Y
LC | 125591067 | 008/103 | T2 DI DIVIDE CBRILO#1 8/103 RPL INSW | PISMOBCH | ETL.1380.INSL.CERA | 2023-03-04 | 2023-03-01 | 2024-06-20 | Late | 2024-02-29 | -112 | 2024-03-01 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35507493 | T2 DI DIVIDE CBRILO#1 8/103 RPL INSW | 93I
LC | 125591153 | :009/067 | T2 DI ROCK CRK POE :009/067 RPL HRDT | TABLEMTN | ETL.5630.TOWR | 2023-03-04 | 2023-03-02 |  | Late | 2024-03-01 |  | 2024-03-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46257548 | T2 DI ROCK CRK POE :009/067 RPL HRDT | ICQ
LC | 125591158 | 017/005 | T2 DI MENDCNO HARTLY 17/005 RPL INSW | WILLITS | ETL.7510.INSL.NCER | 2023-03-04 | 2023-03-01 |  | Late | 2024-02-29 |  | 2024-03-01 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35484588 | T2 DI MENDCNO HARTLY 17/005 RPL INSW | 93I
LC | 125600159 | 018/013 | T2 DI MNDCO PHLO JT HPLD18/13 RPL HRDW | WILLITS | ETL.7520.POLE.WOOD | 2023-03-07 | 2023-02-24 |  | Late | 2024-02-24 |  | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45958101 | T2 DI MNDCO PHLO JT HPLD18/13 RPL HRDW | ICW
LC | 125591496 | 009/068 | T2 DI VAC-VLL-JMSN-NTWR 9/68 COMPLETE | SACTO | ETL.4090.INSL.NCER | 2023-03-04 | 2023-03-02 | 2024-03-07 | Late | 2024-03-01 | -6 | 2024-03-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45954900 | T2 DI VAC-VLL-JMSN-NTWR 9/68 RPR INSS | ICS
LC | 125601079 | 006/003 | T2 DI MENDOCINO #1 6/3 RPL INST | WILLITS | ETL.7530.INSL.CERA | 2023-03-07 | 2023-02-24 |  | Late | 2024-02-24 |  | 2024-02-24 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667792 | T2 DI MENDOCINO #1 5/3 RPL INSS | 93K
LC | 125601898 | 008/181 | T2 DI SLNAS LURLES 008/181 RPR SPLW | MOSSLNDG | ETL.7930.INSL | 2023-03-07 | 2023-02-24 | 2024-03-26 | Late | 2024-02-24 | -31 | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46080987 | T2 DI SLNAS LURLES 008/181 RPR SPLW | ICW
LC | 125602817 | 008/186 | T2 DI SLNS-LAURELES 8/186 INS IBWW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-03-07 | 2023-02-24 | 2024-03-27 | Late | 2024-02-24 | -32 | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 46080989 | T2 DI SLNS-LAURELES 8/186 INS IBWW | ICW
LC | 125603023 | 019/001 | T2 DI MDCNO PHLO JT HPLND 19/1 RPR STRW | WILLITS | ETL.7520.POLE.NWOD | 2023-03-07 | 2023-02-24 |  | Late | 2024-02-24 |  | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45958102 | T2 DI MDCNO PHLO JT HPLND 19/1 RPR STRW | ICW
LC | 125563640 | 008/149 | T2 WV PIT #1-HT CRK #2-BRNY 8/1 INS DMPW | TABLEMTN | ETL.7040.POLE.WOOD | 2023-02-27 | 2023-02-27 | 2023-03-28 | On-time | 2024-02-27 | 336 | 2024-02-27 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 45698566 | T2 WV PIT #1-HT CRK #2-BRNY 8/1 INS DMPW | ICW
LC | 125573026 | 008/105 | T2 DI DIVIDE-CBRLLO #2 8/105 RPL INSW | PISMOBCH | ETL.1370.INSL.NCER | 2023-03-01 | 2023-02-27 | 2024-01-03 | On-time | 2024-02-27 | 55 | 2024-02-27 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35495592 | T2 DI DIVIDE-CBRLLO #2 8/105 RPL INSW | 93I
LC | 125573994 | 001/010 | T2 DI LAKEWD-MDW LN-CLYTN :1/10 COTTER | CONCORD | ETL.2082.INSL.NCER | 2023-03-01 | 2023-02-27 | 2023-09-23 | On-time | 2024-02-27 | 157 | 2024-02-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45954239 | T2 DI LAKEWD-MDW LN-CLYTN :1/10 COTTER | ICS
LC | 125591753 | 009/067 | T2 DI VACA VCVL JMSN NR TR 9/67 COMPLETE | SACTO | ETL.4100.TOWR | 2023-03-04 | 2023-03-02 | 2024-05-03 | Late | 2024-03-01 | -63 | 2024-03-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46063597 | T2 DI VACA VCVL JMSN NR TR 9/67 RPR STRT | ICQ
LC | 125574896 | 010/049 | T2 DI BRNTWD-KELSO 10/49 COTTER | CONCORD | ETL.4410.INSL.NCER | 2023-03-01 | 2023-02-27 | 2023-10-06 | On-time | 2024-02-27 | 144 | 2024-02-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45954894 | T2 DI BRNTWD-KELSO 10/49 COTTER | ICS
LC | 125576185 | 005/021 | T2 DI PITSBURG TESLA#1 5/021 RPL HRDW | CONCORD | ETL.5510.TOWR | 2023-03-01 | 2023-02-27 | 2024-01-16 | On-time | 2024-02-27 | 42 | 2024-02-27 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45989467 | T2 DI PITSBURG TESLA#1 5/021 RPL HRDW | ICQ
LC | 125577419 | 039/185 | T2 DI IGNCO-SOBRANTE 39/185 COTTER | CONCORD | ETL.4920.INSL.CERA | 2023-03-02 | 2023-02-27 | 2023-09-23 | On-time | 2024-02-27 | 157 | 2024-02-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45943081 | T2 DI IGNCO-SOBRANTE 39/185 COTTER | ICS
LC | 125577470 | 039/185 | T2 DI IGNCO-SOBRANTE 39/185 RPL HRDT | LAKEVLLE | ETL.4920.TOWR | 2023-03-02 | 2023-02-27 | 2023-11-02 | On-time | 2024-02-27 | 117 | 2024-02-27 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45989469 | T2 DI IGNCO-SOBRANTE 39/185 RPL HRDT | ICQ
LC | 125591983 | 67 | T2 DI MNDCNO-PHL-HPLND 11/12 RPR SWTC | WILLITS | ETL.7520.SWIT | 2023-03-04 | 2023-03-03 |  | Late | 2024-03-02 |  | 2024-03-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 45977498 | T2 DI MNDCNO-PHL-HPLND 11/12 RPR SWTC | ICW
LC | 125592036 | 017/008 | T2 DI MENDOCINO-HARTLEY 17/8 RPL INSW | WILLITS | ETL.7510.INSL.NCER | 2023-03-04 | 2023-03-03 |  | Late | 2024-03-02 |  | 2024-03-03 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35485470 | T2 DI MENDOCINO-HARTLEY 17/8 RPL INSW | 93I
LC | 125592061 | 006/000 | T2 DI LAKEVILLE #1 6/0 RPL INSW | LAKEVLLE | ETL.7360.INSL.CERA | 2023-03-04 | 2023-03-03 | 2024-05-20 | Late | 2024-03-02 | -79 | 2024-03-03 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35483855 | T2 DI LAKEVILLE #1 6/0 RPL INSW | 93I
LC | 125610955 | 006/120 | T2 DI VALLEY SPRINGS#2 6/120 RPL INSW | VICTOR | ETL.9460.INSL.CERA | 2023-03-08 | 2023-02-27 | 2024-02-15 | On-time | 2024-02-27 | 12 | 2024-02-27 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35495595 | T2 DI VALLEY SPRINGS#2 6/120 RPL INSW | 93I
LC | 125611567 | 004/007 | T2 DI MELONES RCETRCK 004/007 RMV VEG | VICTOR | ETL.2400.POLE.NWOD | 2023-03-08 | 2023-02-27 | 2023-10-12 | On-time | 2024-02-27 | 138 | 2024-02-27 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125611982 | 006/069 | T2 DI COLGATE-SMRTVLLE #1 6/69R RPL POLE | SACTO | ETL.6510.POLE.WDPS | 2023-03-08 | 2023-02-27 | 2023-12-14 | On-time | 2024-02-27 | 75 | 2024-02-27 | 372T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481556 | T2 DI COLGATE-SMRTVLLE #1 6/69R RPL POLE | 70Y
LC | 125611983 | 006/069 | T2 DI COLGATE-SMRTVLLE #1 6/69L RPL POLE | SACTO | ETL.6510.POLE.WDPS | 2023-03-08 | 2023-02-27 | 2023-12-14 | On-time | 2024-02-27 | 75 | 2024-02-27 | 372 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481556 | T2 DI COLGATE-SMRTVLLE #1 6/69R RPL POLE | 70Y
LC | 125592250 | 005/006 | T2 DI MDCNO PHLO JT HPLND 5/006 COTTER | WILLITS | ETL.7520.INSL.NCER | 2023-03-04 | 2023-03-03 |  | Late | 2024-03-02 |  | 2024-03-03 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45977495 | T2 DI MDCNO PHLO JT HPLND 5/006 COTTER | ICS
LC | 125592253 | 014/300 | T2 DI LAKEVILLE #2 014/300 GO95 POLE | LAKEVLLE | ETL.7340.POLE.WOOD | 2023-03-04 | 2023-02-22 |  | Late | 2024-02-22 |  | 2024-02-22 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35516952 | T2 DI LAKEVILLE #2 014/300 GO95 POLE | 93G
LC | 125611986 | 006/069 | T2 DI COLGATE-SMRTVLLE #1 6/69C RPL POLE | SACTO | ETL.6510.POLE.WDPS | 2023-03-08 | 2023-02-27 | 2023-12-14 | On-time | 2024-02-27 | 75 | 2024-02-27 | 372 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481556 | T2 DI COLGATE-SMRTVLLE #1 6/69R RPL POLE | 70Y
LC | 125592421 | 002/024 | T2 DI SANTA YNZ TP 2/24 RPL INSW | PISMOBCH | ETL.3701.INSL.CERA | 2023-03-04 | 2023-02-23 | 2024-03-06 | Late | 2024-02-23 | -12 | 2024-02-23 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493011 | T2 DI SANTA YNZ TP 2/24 RPL INSW | 93I
LC | 125612010 | 003/041 | T2 DI LAKEVILLE #1 003/041 RPR GYWW | LAKEVLLE | ETL.7360.POLE.WOOD | 2023-03-08 | 2023-02-27 | 2023-11-02 | On-time | 2024-02-27 | 117 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45954914 | T2 DI LAKEVILLE #1 003/041 RPR GYWW | ICW
LC | 125594787 | 002/026 | T2 DI SANTA YNZ TP 2/026 RPR STRW | PISMOBCH | ETL.3701.POLE.NWOD | 2023-03-06 | 2023-02-23 | 2024-03-07 | Late | 2024-02-23 | -13 | 2024-02-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46078977 | T2 DI SANTA YNZ TP 2/026 RPR STRW | ICW
LC | 125594838 | 010/014 | T2 TRINITY-MAPLE CRK 10/14 GO95 | EUREKA | ETL.8170.POLE.NWOD | 2023-03-06 | 2023-03-06 |  | Late | 2024-03-05 |  | 2024-03-06 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31629292 | T2 TRINITY-MAPLE CRK 10/12 RPL STRW G095 | 93G
LC | 125612015 | 009/168 | T2 DI VALLEY SPRINGS#2 9/168 RPR SPLW | VICTOR | ETL.9460.INSL.CERA | 2023-03-08 | 2023-02-27 | 2023-09-07 | On-time | 2024-02-27 | 173 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45907431 | T2 DI VALLEY SPRINGS#2 9/168 RPR SPLW | ICW
LC | 125594910 | 002/029 | T2 DI LKVIL SONOMA#1 2/29 RPL INSS | LAKEVLLE | ETL.2063.INSL.NCER | 2023-03-06 | 2023-02-23 |  | Late | 2024-02-23 |  | 2024-02-23 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31664418 | T2 DI LKVIL SONOMA#1 2/29 RPL INSS | 93K
LC | 125612074 | 007/078 | T2 DI COLGATE-SMRTVIL#2 7/78 RPR GYWW | SACTO | ETL.6520.POLE.NWOD | 2023-03-08 | 2023-02-27 | 2023-09-01 | On-time | 2024-02-27 | 179 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45953420 | T2 DI COLGATE-SMRTVIL#2 7/78 RPR GYWW | ICW
LC | 125612197 | 010/198 | T2 DI VALLEY SPRNGS #2 10/198 INS IBWW | VICTOR | ETL.9460.POLE.WOOD | 2023-03-08 | 2023-02-27 | 2023-08-18 | On-time | 2024-02-27 | 193 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45907512 | T2 DI VALLEY SPRNGS #2 10/198 INS IBWW | ICW
LC | 125595890 | 033/003 | T2 TRINITY-MAPLE CREEK 33/003C CLEARANCE | EUREKA | ETL.8170.POLE.WDPS | 2023-03-06 | 2023-03-06 |  | Late | 2024-03-05 |  | 2023-09-06 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35511910 | T2 TRINITY-MAPLE CREEK 33/003 CLEARANCE | 93G
LC | 125595894 | 033/003 | T2 TRINITY-MAPLE CREEK 33/003R CLEARANCE | EUREKA | ETL.8170.POLE.WDPS | 2023-03-06 | 2023-03-06 |  | Late | 2024-03-05 |  | 2024-03-06 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35511910 | T2 TRINITY-MAPLE CREEK 33/003 CLEARANCE | 93G
LC | 125612199 | 064/003 | T2 DI ELK-GUALALA 64/3 ANTI SPLIT | WILLITS | ETL.8410.POLE.WOOD | 2023-03-08 | 2023-02-27 | 2024-01-30 | On-time | 2024-02-27 | 28 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45975334 | T2 DI ELK-GUALALA 64/3 ANTI SPLIT | ICW
LC | 125612262 | 062/011 | T2 DI ELK-GULALA 62/11 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-03-08 | 2023-02-27 | 2024-01-25 | On-time | 2024-02-27 | 33 | 2024-02-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483854 | T2 DI ELK-GUALALA 62/7 RPL POLE | 70Y
LC | 125612274 | 009/163 | T2 DI VLY SPRNGS-#2 09/163 RPR SPLW | VICTOR | ETL.9460.INSL.NCER | 2023-03-08 | 2023-02-27 | 2023-09-01 | On-time | 2024-02-27 | 179 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45907428 | T2 DI VLY SPRNGS-#2 09/163 RPR SPLW | ICW
LC | 125612302 | 010/189 | T2 DI VALLEY SPRINGS #2 10/189 RPR INSW | VICTOR | ETL.9460.INSL.CERA | 2023-03-08 | 2023-02-27 | 2023-09-02 | On-time | 2024-02-27 | 178 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45907432 | T2 DI VALLEY SPRINGS #2 10/189 RPR INSW | ICW
LC | 125597570 | 017/121 | T2 EI HELMS-GREGG #1 017/121 RPR ROAD | FRESNO | ETL.4870.TOWR | 2023-03-06 | 2023-03-06 |  | Late | 2024-03-05 |  | 2024-03-06 | 374 | TLR | INSP | E - Schd Compl Yr 0 | Open | TR2 | Missing | Road | Install | 31677103 | T2NT EI HELMS-GREGG #1 017/120 RPL ROAD | 71Y
LC | 125612334 | 008/151 | T2 DI LAKEVILLE #2 8/151 RPR STRW | VICTOR | ETL.9460.POLE.WOOD | 2023-03-08 | 2023-02-27 | 2023-08-26 | On-time | 2024-02-27 | 185 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45907427 | T2 DI LAKEVILLE #2 8/151 RPR STRW | ICW
LC | 125612394 | 001/007 | T2 DI LKWD-CLAYTON 001/007 COMPLETE | CONCORD | ETL.2082.INSL.NCER | 2023-03-08 | 2023-02-27 | 2024-02-26 | On-time | 2024-02-27 | 1 | 2024-02-27 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667527 | T2 DI LKWD-CLAYTON 001/007 COMPLETE | 93K
LC | 125612519 | 009/164 | T2 DI VALLEY SPRINGS #2 9/164 INS IBWW | VICTOR | ETL.9460.POLE.WOOD | 2023-03-08 | 2023-02-27 | 2023-09-05 | On-time | 2024-02-27 | 175 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45907429 | T2 DI VALLEY SPRINGS #2 9/164 INS IBWW | ICW
LC | 125612548 | 008/062 | T2 DI VACA-SUISUN 8/62 RPL HRDT | SACTO | ETL.4070.TOWR | 2023-03-08 | 2023-02-27 | 2023-08-02 | On-time | 2024-02-27 | 209 | 2024-02-27 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45908186 | T2 DI VACA-SUISUN 8/62 RPL HRDT | ICQ
LC | 125612595 | 063/000 | T2 DI ELK-GUALALA 63/0 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-03-08 | 2023-02-27 | 2024-01-25 | On-time | 2024-02-27 | 33 | 2024-02-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483854 | T2 DI ELK-GUALALA 62/7 RPL POLE | 70Y
LC | 125612609 | 064/004 | T2 DI ELK-GUALALA 64/4 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-03-08 | 2023-02-27 | 2024-01-26 | On-time | 2024-02-27 | 32 | 2024-02-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483854 | T2 DI ELK-GUALALA 62/7 RPL POLE | 70Y
LC | 125612665 | 004/011 | T2 DI SONOMA-PUEBLO- 04/11 RPR POLE | LAKEVLLE | ETL.3810.POLE.WOOD | 2023-03-08 | 2023-02-27 | 2024-01-30 | On-time | 2024-02-27 | 28 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45954912 | T2 DI SONOMA-PUEBLO- 04/11 RPR POLE | ICW
LC | 125598712 | 002/037 | T2 DI LAKEVILLE #1 002/037 RPL POLE | LAKEVLLE | ETL.7360.POLE.WOOD | 2023-03-06 | 2023-02-23 |  | Late | 2024-02-23 |  | 2024-02-23 | 372T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483024 | T2 DI LAKEVILLE #1 002/037 RPL POLE | 70Y
LC | 125612683 | 004/001 | T2 DI SONOMA-PUEBLO 4/1 INS HRDD | LAKEVLLE | ETL.3810.INSL.CERA | 2023-03-08 | 2023-02-27 | 2024-01-30 | On-time | 2024-02-27 | 28 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45954913 | T2 DI SONOMA-PUEBLO 4/1 INS HRDD | ICW
LC | 125566191 | 007/066 | T2 EI BUKS CRK-RK CRK-CRST 7/66 COMPLETE | TABLEMTN | ETL.4430.INSL.CERA | 2023-02-28 | 2023-02-28 | 2023-08-25 | On-time | 2024-02-28 | 187 | 2023-08-28 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45698572 | T2 EI BUKS CRK-RK CRK-CRST 7/66 COTTER | ICS
LC | 125598872 | 002/021 | T2 DI LKEVIL SNOMA#2 2/21 RPL INSS | LAKEVLLE | ETL.2070.INSL.NCER | 2023-03-06 | 2023-02-23 |  | Late | 2024-02-23 |  | 2024-02-23 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31677664 | DI LKEVIL SNOMA#2 RPL INSS IN 2 TWRS. | 93K
LC | 125598940 | 011/080 | T2 DI IGCIO ALT SUSLTO#2 11/80 RPL INSS | LAKEVLLE | ETL.7170.INSL.NCER | 2023-03-06 | 2023-02-23 |  | Late | 2024-02-23 |  | 2024-02-23 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667793 | T2 DI IGNCO ALTO SUSLTO#2 RPL INSS IN 2 | 93K
LC | 125566200 | 007/064 | T2 BKS CRK-RK CRK-CRST 7/64 RPR INST | TABLEMTN | ETL.4430.INSL.CERA | 2023-02-28 | 2023-02-28 | 2024-01-16 | On-time | 2024-02-28 | 43 | 2024-02-28 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45698564 | T2 BKS CRK-RK CRK-CRST 7/64 RPR INST | ICS
LC | 125572286 | 000/003C | T2 MELONES-RACETRACK 00/03C REFRAME | VICTOR | ETL.2400.POLE.WOOD | 2023-03-01 | 2023-02-28 | 2023-11-12 | On-time | 2024-02-28 | 108 | 2024-02-28 | 637 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31639237 | T2 MELONES-RACETRACK 00/03C REFRAME | 93E
LC | 125577279 | 006/034 | T2 DI IGNCO-SN RAFAEL #1 6/34 INS HRDT | LAKEVLLE | ETL.1850.TOWR | 2023-03-02 | 2023-02-28 | 2023-10-11 | On-time | 2024-02-28 | 140 | 2024-02-28 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Tower | Install | 45989468 | T2 DI IGNCO-SN RAFAEL #1 6/34 INS HRDT | ICQ
LC | 125577305 | 065/001 | T2 DI ELK-GUALALA 65/1 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-03-02 | 2023-02-28 | 2024-01-29 | On-time | 2024-02-28 | 30 | 2024-02-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35484565 | T2 DI ELK-GUALALA 65/1 RPL POLE | 70Y
LC | 125577334 | 012/004 | T2 DI VLY SPRNGS-MRTL #1 12/4 RPR INSW | VICTOR | ETL.8240.INSL.NCER | 2023-03-02 | 2023-02-28 | 2023-05-11 | On-time | 2024-02-28 | 293 | 2023-05-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45698764 | T2 DI VLY SPRNGS-MRTL #1 12/4 RPR INSW | ICW
LC | 125599955 | 025/009 | T2 DI MI WUK CURTIS 25/9C RPL STRW | VICTOR | ETL.1073.POLE.WDPS | 2023-03-07 | 2023-03-01 |  | Late | 2024-02-29 |  | 2023-09-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495524 | T2 DI MI WUK CURTIS 25/9C RPL STRW | 70Y
LC | 125599957 | 025/009 | T2 DI MI WUK CURTIS 25/9L RPL STRW | VICTOR | ETL.1073.POLE.WDPS | 2023-03-07 | 2023-03-01 |  | Late | 2024-02-29 |  | 2023-09-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495524 | T2 DI MI WUK CURTIS 25/9C RPL STRW | 70Y
LC | 125603757 | 008/187 | T2 DI SLNS-LAURELES 8/187 INS IBWW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-03-07 | 2023-02-24 | 2024-03-27 | Late | 2024-02-24 | -32 | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 46080991 | T2 DI SLNS-LAURELES 8/187 INS IBWW | ICW
LC | 125577350 | 003/042 | T2 DI PARADISE-TBL MTN 3/42 RPR INSS | TABLEMTN | ETL.4316.INSL.NCER | 2023-03-02 | 2023-02-28 | 2023-10-18 | On-time | 2024-02-28 | 133 | 2024-02-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45698578 | T2 DI PARADISE-BUTTE 3/42 RPR INSS | ICS
LC | 125577448 | 064/009 | T2 DI ELK GUALALA 64/009 RPL HRDD | WILLITS | ETL.8410.POLE.WOOD | 2023-03-02 | 2023-02-28 | 2024-01-30 | On-time | 2024-02-28 | 29 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45976354 | T2 DI ELK GUALALA 64/009 RPL HRDD | ICW
LC | 125604073 | 009/197 | T2 DI SLNS-LAURELES 9/197 INS IBWW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-03-07 | 2023-02-24 | 2024-03-28 | Late | 2024-02-24 | -33 | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46080995 | T2 DI SLNS-LAURELES 9/197 INS IBWW | ICW
LC | 125601579 | 008/062 | T2 EI SAN LUS OBSPO-CYCS 8/62 RPL INSW | PISMOBCH | ETL.9090.INSL | 2023-03-07 | 2023-03-07 | 2024-05-12 | Late | 2024-03-06 | -67 | 2024-03-07 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35495496 | T2 EI SAN LUS OBSPO-CAYUCOS 8/62 RPL INS | 93I
LC | 125601710 | 007/147 | T2 CNTRVLL-TBL MTN-RVILL 7/147 RPL POLE | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-07 | 2023-03-07 | 2024-05-22 | Late | 2024-03-06 | -77 | 2024-03-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486529 | T2 DI CNTRVL-TB MT-ORO 6/126 RPL STRW | 70Y
LC | 125601783 | A007/146 | T2 EI LAKEVILLE #2 A007/146 RPR JUMW | LAKEVLLE | ETL.7340.INSL.NCER | 2023-03-07 | 2023-03-07 | 2024-04-19 | Late | 2024-03-06 | -44 | 2024-03-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45954415 | T2 EI LAKEVILLE #2 A007/146 RPR JUMW | ICW
LC | 125605024 | 011/234 | T2 DI SLNS-LAURELES 11/234 RPR SPLW | MOSSLNDG | ETL.7930.INSL | 2023-03-07 | 2023-02-24 |  | Late | 2024-02-24 |  | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46080996 | T2 DI SLNS-LAURELES 11/234 RPR SPLW | ICW
LC | 125605028 | 010/231 | T2 DI SLNS-LAURELES 10/231 INS IBWW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-03-07 | 2023-02-24 |  | Late | 2024-02-24 |  | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46080997 | T2 DI SLNS-LAURELES 10/231 INS IBWW | ICW
LC | 125605197 | A013/279 | T2 DI SALINAS-LAURELES A013/279 RPR SPLW | MOSSLNDG | ETL.7930.INSL | 2023-03-07 | 2023-02-24 | 2024-04-18 | Late | 2024-02-24 | -54 | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46080998 | T2 DI SALINAS-LAURELES A013/279 RPR SPLW | ICW
LC | 125577683 | 005/000 | T2 DI MNDCNO-HARTLEY 5/0L RPR GYWW | WILLITS | ETL.7510.POLE.STPS | 2023-03-02 | 2023-02-28 | 2024-02-13 | On-time | 2024-02-28 | 15 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45975338 | T2 DI MNDCNO-HARTLEY 5/0L RPR GYWW | ICW
LC | 125605304 | 004/002 | T2 DI MNDCNO-PHILO JCT-HPLND 4/2 COTTER | WILLITS | ETL.7520.INSL.NCER | 2023-03-07 | 2023-02-24 |  | Late | 2024-02-24 |  | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45956915 | T2 DI MNDCNO-PHILO JCT-HPLND 4/2 COTTER | ICW
LC | 125605454 | 012/068 | T2 DI CC-LAS POSITAS 10/69 RPL HRDT | CONCORD | ETL.6160.INSL.CERA | 2023-03-07 | 2023-02-24 |  | Late | 2024-02-24 |  | 2024-02-24 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45937217 | T2 DI CC-LAS POSITAS 10/69 RPL HRDT | ICQ
LC | 125577684 | 005/000 | T2 DI MNDCNO-HARTLEY 5/0C RPR GYWW | WILLITS | ETL.7510.POLE.STPS | 2023-03-02 | 2023-02-28 | 2024-02-13 | On-time | 2024-02-28 | 15 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45975339 | T2 DI MNDCNO-HARTLEY 5/0C RPR GYWW | ICW
LC | 125577685 | 005/000 | T2 DI MNDCNO-HARTLEY 5/0R RPR GYWW | WILLITS | ETL.7510.POLE.STPS | 2023-03-02 | 2023-02-28 | 2024-02-13 | On-time | 2024-02-28 | 15 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45976340 | T2 DI MNDCNO-HARTLEY 5/0R RPR GYWW | ICW
LC | 125605455 | 012/068 | T2 DI LNE TRE-CAYETANO 12/68 RPL INSS | CONCORD | ETL.6160.INSL.CERA | 2023-03-07 | 2023-02-24 |  | Late | 2024-02-24 |  | 2024-02-24 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31677781 | DI LNETRE-CAYENANO 12/68 RPL INSS | 93K
LC | 125605479 | 020/008 | T2 DI MNDCNO-PHL JCT HPLND 20/8 RPL INSW | WILLITS | ETL.7520.INSL.NCER | 2023-03-07 | 2023-02-24 | 2024-03-23 | Late | 2024-02-24 | -28 | 2024-02-24 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35483189 | T2 DI MNDCNO-PHL JCT HPLND 20/8 RPL INSW | 93I
LC | 125577780 | 006/005 | T2 DI MNDCNO-HARTLEY 6/5 RMV VEG | WILLITS | ETL.7510.POLE.WDPS | 2023-03-02 | 2023-02-28 | 2023-09-11 | On-time | 2024-02-28 | 170 | 2024-02-28 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125605544 | 020/002 | T2 DI MENDCN-PHL JCT-HPLND 20/2 RPL POLE | WILLITS | ETL.7520.POLE.WOOD | 2023-03-07 | 2023-02-24 | 2024-03-21 | Late | 2024-02-24 | -26 | 2024-02-24 | 372T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483188 | T2 DI MENDCN-PHL JCT-HPLND 20/2 RPL POLE | 70Y
LC | 125606488 | A013/285 | T2 DI SLNAS LURLES A13/285 RPL INSW | MOSSLNDG | ETL.7930.INSL | 2023-03-08 | 2023-02-24 | 2024-04-25 | Late | 2024-02-24 | -61 | 2024-02-24 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35507043 | T2 DI SLNAS LURLES A13/285 RPL INSW | 93I
LC | 125577783 | 009/107 | T2 DI DIVIDE-CBRLLO #2 9/107 RPL INSW | PISMOBCH | ETL.1370.INSL.NCER | 2023-03-02 | 2023-02-28 | 2023-12-28 | On-time | 2024-02-28 | 62 | 2024-02-28 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35495094 | T2 DI DIVIDE-CBRLLO #2 9/107 RPL INSW | 93I
LC | 125578017 | 008/007 | T2 DI MNDCNO-HARTLEY 8/7 RPL INSW | WILLITS | ETL.7510.INSL.CERA | 2023-03-02 | 2023-02-28 | 2024-02-16 | On-time | 2024-02-28 | 12 | 2024-02-28 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35484591 | T2 DI MNDCNO-HARTLEY 8/7 RPL INSW | 93I
LC | 125607279 | 008/194 | T2 DI SLNAS LURLES 8/194 RPR INSW | MOSSLNDG | ETL.7930.INSL | 2023-03-08 | 2023-02-24 | 2024-03-27 | Late | 2024-02-24 | -32 | 2024-02-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081060 | T2 DI SLNAS LURLES 8/194 RPR INSW | ICW
LC | 125609040 | 017/005 | T2 DI KONOCTI MIDDLETOWN 17/5 RPL STRW | WILLITS | ETL.6380.POLE.WOOD | 2023-03-08 | 2023-02-24 |  | Late | 2024-02-24 |  | 2024-02-24 | 630 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace
LC | 125578062 | 012/007 | T2 DI PHILO-ELK 12/7 RPR GYWW | WILLITS | ETL.7780.POLE.NWOD | 2023-03-02 | 2023-02-28 | 2023-09-25 | On-time | 2024-02-28 | 156 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45976352 | T2 DI PHILO-ELK 12/7 RPR GYWW | ICW
LC | 125580487 | 005/002 | T2 DI MNDCNO HRTLY 5/2C RPR GYWW | WILLITS | ETL.7510.POLE.STPS | 2023-03-02 | 2023-02-28 | 2024-02-13 | On-time | 2024-02-28 | 15 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45976341 | T2 DI MNDCNO HRTLY 5/2C RPR GYWW | ICW
LC | 125609610 | 008/002 | T2 DI PHILO JCT ELK 8/2 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-03-08 | 2023-02-24 | 2024-05-05 | Late | 2024-02-24 | -71 | 2024-02-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481043 | T2 EI PHILO JCT-ELK 09/01 RPL POLE | 70Y
LC | 125619746 | 044/180 | T2 DI MDWY-WHRLWND 44/180 RPR SHIELD | MIDWAY | ETL.6030.TOWR | 2023-03-09 | 2023-02-28 | 2024-01-09 | On-time | 2024-02-28 | 50 | 2024-02-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46024374 | T2 DI MDWY-WHRLWND 44/180 RPR SHIELD | ICS
LC | 125641753 | 020/012 | T2 DI MNDCNO-PHLO JT-HPND 20/12 RPL INSW | WILLITS | ETL.7520.INSL.NCER | 2023-03-12 | 2023-02-24 | 2024-03-23 | Late | 2024-02-24 | -28 | 2024-02-24 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35483189 | T2 DI MNDCNO-PHL JCT HPLND 20/8 RPL INSW | 93I
LC | 127077297 | 008/006 | T3 WV MONTE RIO-FULTON 8/6 RPL POLE | LAKEVLLE | ETL.7630.POLE.WOOD | 2023-09-18 | 2023-09-18 |  | Late | 2024-03-18 |  | 2024-03-18 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Open | TR3 | Rotten | Structure-Wood | Replace | 35493841 | T3 WV MONTE RIO-FULTON 8/6 RPL POLE | 70Y
LC | 125606609 | 011/080 | T2 DI IGCO ALTO SSLTO#1 11/080 RPR OPGW | LAKEVLLE | ETL.7160.TOWR | 2023-03-08 | 2023-03-07 |  | Late | 2024-03-06 |  | 2024-03-07 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45954416 | T2 DI IGCO ALTO SSLTO#1 11/080 RPR OPGW | ICS
LC | 125619849 | 010/186 | T2 DI VLY SPRNGS#2 10/186 RPL HRDD | VICTOR | ETL.9460.POLE.WOOD | 2023-03-09 | 2023-02-28 | 2023-08-29 | On-time | 2024-02-28 | 183 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45907516 | T2 DI VLY SPRNGS#2 10/186 RPL HRDD | ICW
LC | 125620002 | 003/000 | T2 DI PHILO JCT-ELK-ELK 03/00 RPR GYWW | WILLITS | ETL.7780.POLE.WOOD | 2023-03-09 | 2023-02-28 | 2023-09-25 | On-time | 2024-02-28 | 156 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45975335 | T2 DI PHILO JCT-ELK-ELK 03/00 RPR GYWW | ICW
LC | 125606955 | 036/170 | T2 DI LAKVILLE SBRNTE #2 36/170 RPL INSS | CONCORD | ETL.4960.INSL | 2023-03-08 | 2023-03-07 |  | Late | 2024-03-06 |  | 2024-03-07 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31677273 | T2 DI LAKVILLE SBRNTE #2 36/170 RPL INSS | 93K
LC | 127077837 | 000/002 | T3 DONNELLS-MI WUK 000/002L RPR GYWW | VICTOR | ETL.1400.POLE.STPS | 2023-09-18 | 2023-09-18 |  | Late | 2024-03-18 |  | 2024-03-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR3 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46269308 | T3 DONNELLS-MI WUK 000/002L RPR GYWW | ICS
LC | 125620046 | 008/155 | T2 DI VALLEY SPRINGS #2 8/155 RPR SPLW | VICTOR | ETL.9460.INSL.NCER | 2023-03-09 | 2023-02-28 | 2023-08-26 | On-time | 2024-02-28 | 186 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45907513 | T2 DI VALLEY SPRINGS #2 8/155 RPR SPLW | ICW
LC | 125620048 | 008/155 | T2 DI VALLEY SPRINGS #2 8/155 INS IBWW | VICTOR | ETL.9460.INSL.NCER | 2023-03-09 | 2023-02-28 | 2023-08-26 | On-time | 2024-02-28 | 186 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45907515 | T2 DI VALLEY SPRINGS #2 8/155 INS IBWW | ICW
LC | 125608696 | 002/027 | T2 DI SBRNT-GRZLY-CLRMT #1 2/27 RPR INSS | CONCORD | ETL.3740.INSL.CERA | 2023-03-08 | 2023-03-07 | 2024-04-09 | Late | 2024-03-06 | -34 | 2024-03-07 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45954896 | T2 DI SBRNT GRZZLY CLRMT#1 2/27 RPR INST | ICW
LC | 125608778 | A014/310 | T2 DI SLNAS LURLES 14/310A RPR SPLW | MOSSLNDG | ETL.7930.INSL | 2023-03-08 | 2023-02-27 | 2024-05-01 | Late | 2024-02-27 | -64 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46081061 | T2 DI SLNAS LURLES 14/310A RPR SPLW | ICW
LC | 125620138 | 011/004 | T2 DI MENDO-HARTLEY 11/04 RPR CNDW | WILLITS | ETL.7510.INSL.NCER | 2023-03-09 | 2023-02-28 | 2024-02-15 | On-time | 2024-02-28 | 13 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45976345 | T2 DI MENDO-HARTLEY 11/04 RPR CNDW | ICW
LC | 127078204 | 018/127C | T3 MTCLF-GRN VLY 18/127C RPR GRWW | MOSSLNDG | ETL.2540.POLE.NWOD | 2023-09-18 | 2023-09-18 | 2023-11-10 | On-time | 2024-03-18 | 129 | 2024-03-18 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 46008787 | T3 MTCLF-GRN VLY 18/127C RPR GRWW | ICW
LC | 125620250 | 009/004 | T2 DI MENDO-HARTLEY 09/04 RPR CRSW | WILLITS | ETL.7510.POLE.WOOD | 2023-03-09 | 2023-02-28 | 2024-02-15 | On-time | 2024-02-28 | 13 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45976344 | T2 DI MENDO-HARTLEY 09/04 RPR CRSW | ICW
LC | 125609500 | 013/251 | T2 EI COLGATE-PALERMO 013/251 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-08 | 2023-03-08 |  | Late | 2024-03-07 |  | 2024-03-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486530 | T2 EI COLGATE-PALERMO 013/251 RPL POLE | 70Y
LC | 125684685 | 001/023 | T2 EI PIT #1-MC ARTHUR 001/023 RPR ANCW | TABLEMTN | ETL.7790.POLE.WOOD | 2023-03-19 | 2023-03-19 | 2024-05-14 | Late | 2024-03-18 | -57 | 2024-03-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45989275 | T2 EI PIT #1-MC ARTHUR 001/023 RPR ANCW | ICW
LC | 125609686 | 062/007 | T2 DI ELK-GUALALA 62/7 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-03-08 | 2023-02-27 |  | Late | 2024-02-27 |  | 2024-02-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483854 | T2 DI ELK-GUALALA 62/7 RPL POLE | 70Y
LC | 125610111 | A015/323 | T2 DI SLNAS LURLES 15/323 RPR SPLW | MOSSLNDG | ETL.7930.INSL | 2023-03-08 | 2023-02-27 | 2024-04-25 | Late | 2024-02-27 | -58 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46081062 | T2 DI SLNAS LURLES 15/323 RPR SPLW | ICW
LC | 125620341 | 012/230 | T2 DI VALLEY SPRINGS #2 12/230 RPL INSW | VICTOR | ETL.9460.INSL.CERA | 2023-03-09 | 2023-02-28 | 2024-02-15 | On-time | 2024-02-28 | 13 | 2024-02-28 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35495596 | T2 DI VALLEY SPRINGS #2 12/230 INS RPL | 93I
LC | 125610502 | 004/007 | T2 DI PHILO JCT ELK 4/7 RPR INSW | WILLITS | ETL.7780.INSL.NCER | 2023-03-08 | 2023-02-27 | 2024-05-02 | Late | 2024-02-27 | -65 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45975332 | T2 DI PHILO JCT ELK 4/7 RPR INSW | ICW
LC | 125633362 | 002/010 | T2 DI ORVLLE-TBLE MTN 2/10 RPR INSS | TABLEMTN | ETL.6623.INSL.CERA | 2023-03-10 | 2023-02-28 | 2024-02-28 | On-time | 2024-02-28 | 0 | 2024-02-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45979824 | T2 DI ORVLLE-TBLE MTN 2/10 RPR INSS | ICS
LC | 125611355 | A016/355 | T2NT DI SLINAS-LAURELES A16/355 RMV DBRS | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-03-08 | 2023-02-27 | 2024-04-23 | Late | 2024-02-27 | -56 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 46081064 | T2NT DI SLINAS-LAURELES A16/355 RMV DBRS | ICW
LC | 125633861 | A008/106 | T2 DI DIVIDE-CBRLO #2 A08/106 RPL INSW | PISMOBCH | ETL.1370.INSL.CERA | 2023-03-10 | 2023-02-28 | 2024-01-03 | On-time | 2024-02-28 | 56 | 2024-02-28 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35503057 | T2 EI DIVIDE-CABRILLO #2 8/103 RPL INSW | 93I
LC | 125635160 | 005/051 | T2 DI BCKS CRK-RCK CRK-CTA 5/51 RPL INSS | TABLEMTN | ETL.4430.INSL.CERA | 2023-03-10 | 2023-02-28 | 2024-01-18 | On-time | 2024-02-28 | 41 | 2024-02-28 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667698 | T2 DI BCKS CRK-RCK CRK-CTA RPL INSS 5 ST | 93K
LC | 125611700 | 004/002 | T2 DI PHILO JCT ELK 4/2 RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-03-08 | 2023-02-27 |  | Late | 2024-02-27 |  | 2024-02-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35551282 | T2 DI PHILO JCT ELK 4/2 RPL STRW | 70Y
LC | 125611791 | A017/359 | T2 DI SALINAS-LAURELES A17/359 RPR SPLW | MOSSLNDG | ETL.7930.INSL | 2023-03-08 | 2023-02-27 | 2024-04-23 | Late | 2024-02-27 | -56 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46081065 | T2 DI SALINAS-LAURELES A17/359 RPR SPLW | ICW
LC | 125611881 | A016/354 | T2 DI SLNAS LURLES 16/354 RPR IBWW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-03-08 | 2023-02-27 | 2024-04-24 | Late | 2024-02-27 | -57 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46081066 | T2 DI SLNAS LURLES 16/354 RPR IBWW | ICW
LC | 125611956 | 005/006 | T2 DI LAKEVILLE #1 005/006 RPR SPLW | LAKEVLLE | ETL.7360.INSL | 2023-03-08 | 2023-02-27 | 2024-05-18 | Late | 2024-02-27 | -81 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45954911 | T2 DI LAKEVILLE #1 005/006 RPR SPLW | ICW
LC | 125640990 | 047/190 | T2 DI MIDWAY-WHIRLWIND 47/190 RPR SHIELD | MIDWAY | ETL.6030.TOWR | 2023-03-11 | 2023-02-28 | 2024-01-09 | On-time | 2024-02-28 | 50 | 2024-02-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46043009 | T2 DI MIDWAY-WHIRLWIND 47/190 RPR SHIELD | ICS
LC | 125640998 | 046/189 | T2 DI MIDWAY-WHIRLWIND 46/189 RPR SHIELD | MIDWAY | ETL.6030.TOWR | 2023-03-11 | 2023-02-28 | 2024-01-09 | On-time | 2024-02-28 | 50 | 2024-02-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46043008 | T2 DI MIDWAY-WHIRLWIND 46/189 RPR SHIELD | ICS
LC | 125641751 | 011/006 | T2 DI MNDCNO-HRTLY 011/006 RPR INSW | WILLITS | ETL.7510.INSL.NCER | 2023-03-12 | 2023-02-28 | 2024-02-13 | On-time | 2024-02-28 | 15 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45976351 | T2 DI MNDCNO-HRTLY 011/006 RPR INSW | ICW
LC | 125677705 | 006/003 | T2 DI MENDOCINO-HARTLEY 006/003 RPR GYWW | WILLITS | ETL.7510.POLE.NWOD | 2023-03-17 | 2023-02-28 | 2024-01-17 | On-time | 2024-02-28 | 42 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45976342 | T2 DI MENDOCINO-HARTLEY 006/003 RPR GYWW | ICW
LC | 125677780 | 006/003 | T2 DI MENDOCINO-HARTLEY 006/003 RPR STRW | WILLITS | ETL.7510.POLE.NWOD | 2023-03-17 | 2023-02-28 | 2024-01-17 | On-time | 2024-02-28 | 42 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45976343 | T2 DI MENDOCINO-HARTLEY 006/003 RPR STRW | ICW
LC | 125612088 | 005/026B | T2 DI PITTSBURG-E. SHR 5/26B RPL INSS | CONCORD | ETL.5462.INSL | 2023-03-08 | 2023-03-07 | 2024-05-05 | Late | 2024-03-06 | -60 | 2024-03-07 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667526 | DI PITTSBURG-E. SHORE RPL INSS IN 3 TWRS | 93K
LC | 125575776 | 093/015 | T2 HUMBOLDT-TRINITY 93/15L RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2023-03-01 | 2023-03-01 | 2023-08-08 | On-time | 2024-02-29 | 205 | 2024-03-01 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31595697 | T2 DI HUMBOLDT-TRINITY 86/3L RPL STRW | 70Y
LC | 125579304 | 007/111 | T2 DI DLTA MTN GT JCT 7/111 RPR ANCW | TABLEMTN | ETL.6750.POLE.WOOD | 2023-03-02 | 2023-03-01 | 2023-10-09 | On-time | 2024-02-29 | 143 | 2024-03-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45989270 | T2 DI DLTA MTN GT JCT 7/111 RPR ANCW | ICW
LC | 125612216 | 003/010 | T2 DI SONOMA-PUEBLO 3/10 RPR SPLW | LAKEVLLE | ETL.3810.INSL.NCER | 2023-03-08 | 2023-02-27 |  | Late | 2024-02-27 |  | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45954915 | T2 DI SONOMA-PUEBLO 3/10 RPR SPLW | ICW
LC | 125579351 | 007/111 | T2 DI DLTA MTN GT JCT 7/111 RPR CRSW | TABLEMTN | ETL.6750.POLE.WOOD | 2023-03-02 | 2023-03-01 | 2023-10-09 | On-time | 2024-02-29 | 143 | 2024-03-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45698324 | T2 DI DLTA MTN GT JCT 7/111 RPR CRSW | ICW
LC | 125586154 | 010/119 | T2 DI CLGTE SMRTVIL#2 10/119 COTTER | SACTO | ETL.6520.INSL.CERA | 2023-03-03 | 2023-03-01 | 2023-08-31 | On-time | 2024-02-29 | 182 | 2024-03-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45953219 | T2 DI CLGTE SMRTVIL#2 10/119 COTTER | ICW
LC | 125589684 | :031/199 | T2 DI NTH TWR MTZ JT #1 :31/199 RPR OPGW | CONCORD | ETL.3130.TOWR | 2023-03-03 | 2023-03-01 | 2023-10-02 | On-time | 2024-02-29 | 150 | 2024-03-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45954895 | T2 DI NTH TWR MTZ JT #1 :31/199 RPR OPGW | ICS
LC | 125612303 | 005/026C | T2 DI PITTSBURG-E. SHORE 5/26C RPL INSS | CONCORD | ETL.5462.INSL | 2023-03-08 | 2023-03-07 | 2024-05-05 | Late | 2024-03-06 | -60 | 2024-03-07 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667526 | DI PITTSBURG-E. SHORE RPL INSS IN 3 TWRS | 93K
LC | 125612307 | 005/026D | T2 DI PITTSBURG-EASTSHORE 5/26D RPL INSS | CONCORD | ETL.5462.INSL | 2023-03-08 | 2023-03-07 | 2024-05-05 | Late | 2024-03-06 | -60 | 2024-03-07 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667526 | DI PITTSBURG-E. SHORE RPL INSS IN 3 TWRS | 93K
LC | 125591281 | :006/041 | T2 DI RCK CRK POE :6/041 RPL INSS | TABLEMTN | ETL.5630.INSL.CERA | 2023-03-04 | 2023-03-01 | 2024-02-27 | On-time | 2024-02-29 | 2 | 2024-03-01 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671289 | T2 DI ROCK CREEK-POE 3 TWRS RPL INSS | 93K
LC | 125684686 | 001/023 | T2 EI PIT #1-MC ARTHUR 001/023 RPR GYWW | TABLEMTN | ETL.7790.POLE.WOOD | 2023-03-19 | 2023-03-19 | 2024-05-14 | Late | 2024-03-18 | -57 | 2024-03-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45989274 | T2 EI PIT #1-MC ARTHUR 001/023 RPR GYWW | ICW
LC | 125633384 | C011/008 | T2 DI FLTN-CLSTGA -011/008 RPR GYWW | LAKEVLLE | ETL.6880.POLE.WOOD | 2023-03-10 | 2023-03-01 | 2023-10-06 | On-time | 2024-02-29 | 146 | 2024-03-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45954902 | T2 DI FLTN-CLSTGA -011/008 RPR GYWW | ICW
LC | 125612405 | 009/011 | T2 DI MELONES-RACETRACK 009/011 RPL STRW | VICTOR | ETL.2400.POLE.WOOD | 2023-03-08 | 2023-02-27 | 2024-05-12 | Late | 2024-02-27 | -75 | 2024-02-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35513229 | T2 DI MELONES-RACETRACK 009/011 RPL STRW | 70Y
LC | 125612468 | 005/014 | T2 DI VLY SPRNGS-MARTL#1 05/14 RPR SPLW | VICTOR | ETL.8240.INSL.NCER | 2023-03-08 | 2023-02-27 | 2024-05-22 | Late | 2024-02-27 | -85 | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45946244 | T2 DI VLY SPRNGS-MARTL#1 05/14 RPR SPLW | ICW
LC | 125638843 | :001/013A | T2 DI BUCKS CREEK-ROCK :01/13A RPL INSS | TABLEMTN | ETL.4430.INSL.CERA | 2023-03-11 | 2023-03-01 | 2024-01-19 | On-time | 2024-02-29 | 41 | 2024-03-01 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667698 | T2 DI BCKS CRK-RCK CRK-CTA RPL INSS 5 ST | 93K
LC | 125638929 | 011/008 | T2 DI WINDSOR-FITCH MNT 11/8 RPR STRW | LAKEVLLE | ETL.6900.POLE.WOOD | 2023-03-11 | 2023-03-01 | 2023-04-11 | On-time | 2024-02-29 | 324 | 2024-03-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 43749442 | EI WNDSR-FTCH MNTN WSIP TAGS | ICW
LC | 125640126 | 008/111C | T2 DI DVD-CBRILO #1 08/111C RPR GYWW | PISMOBCH | ETL.1380.POLE.NWOD | 2023-03-11 | 2023-03-01 | 2024-01-12 | On-time | 2024-02-29 | 48 | 2024-03-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088470 | T2 DI DVD-CBRILO #1 08/111C RPR GYWW | ICW
LC | 125612573 | 007/005 | T2 DI VLY SPGS-MARTELL #1 7/5 RPL POLE | VICTOR | ETL.8240.POLE.WOOD | 2023-03-08 | 2023-02-27 | 2024-05-22 | Late | 2024-02-27 | -85 | 2024-02-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495588 | T2 DI VLY SPGS-MARTELL #1 7/5 RPL POLE | 70Y
LC | 125612591 | 003/081 | T2 DI CNTRVL-TBL MTN-ORVL 3/81 RPL POLE | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-08 | 2023-03-08 | 2024-05-24 | Late | 2024-03-07 | -78 | 2024-03-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486528 | T2 DI CNTRVL-TBL MTN-ORVL 3/81 RPL POLE | 70Y
LC | 125640243 | 007/112 | T2 DI DELTA-MTN GATE JCT 07/112 RPL POLE | TABLEMTN | ETL.6750.POLE.WOOD | 2023-03-11 | 2023-03-01 | 2023-10-09 | On-time | 2024-02-29 | 143 | 2024-03-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484564 | T2 DI DELTA-MTN GATE JCT 07/112 RPL POLE | 70Y
LC | 125640500 | :003/020B | T2 DI ROCK CREEK-POE- :03/20B RPR GYWS | TABLEMTN | ETL.5630.POLE.NWOD | 2023-03-11 | 2023-03-01 | 2023-12-04 | On-time | 2024-02-29 | 87 | 2024-03-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45698589 | T2 DI ROCK CREEK-POE- :03/20B RPR GYWS | ICS
LC | 125612626 | A012/257 | T2 DI SLNS-LARLS-LRLS A012/257 RPR INSW | MOSSLNDG | ETL.7930.INSL | 2023-03-08 | 2023-02-27 | 2024-04-18 | Late | 2024-02-27 | -51 | 2023-08-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081067 | T2 DI SLNS-LARLS-LRLS A012/257 RPR INSW | ICW
LC | 125640539 | :003/020A | T2 DI ROCK CREEK-POE :03/20A RPR GYWT | TABLEMTN | ETL.5630.POLE.NWOD | 2023-03-11 | 2023-03-01 | 2023-08-05 | On-time | 2024-02-29 | 208 | 2024-03-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 45945169 | T2 DI ROCK CREEK-POE :03/20A RPR GYWT | ICQ
LC | 125612681 | A014/314 | T2 DI SLNS-LARLS-LRLS A014/314 RMV VEG | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-03-08 | 2023-02-27 |  | Late | 2024-02-27 |  | 2024-02-27 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Trim
LC | 125640866 | 008/008 | T2 DI MENDOCINO-HARTLEY 008/008 RPL HRDW | WILLITS | ETL.7510.POLE.WOOD | 2023-03-11 | 2023-03-01 | 2024-02-15 | On-time | 2024-02-29 | 14 | 2024-03-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45976355 | T2 DI MENDOCINO-HARTLEY 008/008 RPL HRDW | ICW
LC | 125579462 | 000/003 | T2 EI MRR BY-TMPLTN 000/003 COTTER | PISMOBCH | ETL.5933.INSL.NCER | 2023-03-02 | 2023-03-02 | 2023-11-01 | On-time | 2024-03-01 | 121 | 2024-03-02 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45989474 | T2 EI MRR BY-TMPLTN 000/003 COTTER | ICS
LC | 125579579 | 006/079 | T2 EI DIVIDE-CABRILLO #2 06/079 RPR GYWW | PISMOBCH | ETL.1370.POLE.NWOD | 2023-03-02 | 2023-03-02 | 2023-05-24 | On-time | 2024-03-01 | 282 | 2023-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45706789 | T2 EI DIVIDE-CABRILLO #2 06/079 RPR GYWW | ICW
LC | 125613772 | 014/098 | T2 DI IGNCO ALTO SUSTO #2 14/98 RPL INSS | LAKEVLLE | ETL.7170.INSL.CERA | 2023-03-09 | 2023-03-06 |  | Late | 2024-03-05 |  | 2024-03-06 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667793 | T2 DI IGNCO ALTO SUSLTO#2 RPL INSS IN 2 | 93K
LC | 125580375 | 007/085 | T2 EI DIVIDE-CABRILLO #2 07/085 INS INSW | PISMOBCH | ETL.1370.INSL.CERA | 2023-03-02 | 2023-03-02 | 2024-01-04 | On-time | 2024-03-01 | 57 | 2024-03-02 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35495560 | T2 EI DIVIDE-CABRILLO #2 07/085 INS INSW | 93I
LC | 125615715 | 005/004 | T2 DI PHILO JCT ELK 5/004 CANCEL | WILLITS | ETL.7780.POLE.WOOD | 2023-03-09 | 2023-02-27 |  | Late | 2024-02-27 |  | 2024-02-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45975333 | T2 DI PHILO JCT ELK 5/004 RPR GYWW | ICW
LC | 125591501 | 014/127 | T2 DI SNLS OBSPO CYCOS 14/127 RPL STRW | PISMOBCH | ETL.9090.POLE.WOOD | 2023-03-04 | 2023-03-02 | 2024-01-11 | On-time | 2024-03-01 | 50 | 2024-03-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495580 | T2 DI SNLS OBSPO CYCOS 14/127 RPL STRW | 70Y
LC | 125591569 | 066/003 | T2 DI ELK GUALALA 66/003 RPR STRW | WILLITS | ETL.8410.POLE.WOOD | 2023-03-04 | 2023-03-02 | 2024-01-30 | On-time | 2024-03-01 | 31 | 2024-03-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45977491 | T2 DI ELK GUALALA 66/003 RPR STRW | ICW
LC | 125617386 | A007/142 | T2 DI LAKEVILLE#2 7/142 RPL HRDD | LAKEVLLE | ETL.7340.POLE.WOOD | 2023-03-09 | 2023-02-28 | 2024-05-06 | Late | 2024-02-28 | -68 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45954908 | T2 DI LAKEVILLE#2 7/142 RPL HRDD | ICW
LC | 125617456 | A007/142 | T2 DI LAKEVILLE#2 7/142 RPR INSW | LAKEVLLE | ETL.7340.INSL.NCER | 2023-03-09 | 2023-02-28 | 2024-05-06 | Late | 2024-02-28 | -68 | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45954907 | T2 DI LAKEVILLE#2 7/142 RPR INSW | ICW
LC | 125617571 | 003/060 | T2 DEL MONTE-VIEJO-VIEJO 3/060 RPL POLE | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-03-09 | 2023-03-09 | 2024-04-01 | Late | 2024-03-08 | -24 | 2024-03-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507488 | T2 DEL MONTE-VIEJO-VIEJO 3/060 RPL POLE | 70Y
LC | 125591690 | 008/066 | T2 DI CBRNO STA YNZ SWSTA 8/66 RPR GYWW | PISMOBCH | ETL.1200.POLE.NWOD | 2023-03-04 | 2023-03-02 | 2024-01-29 | On-time | 2024-03-01 | 32 | 2024-03-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46078513 | T2 DI CBRNO STA YNZ SWSTA 8/66 RPR GYWW | ICW
LC | 125591691 | 008/066 | T2 DI CBRNO STA YNZ SWSTA 8/66 COTTER | PISMOBCH | ETL.1200.INSL.NCER | 2023-03-04 | 2023-03-02 | 2024-01-29 | On-time | 2024-03-01 | 32 | 2024-03-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46078514 | T2 DI CBRNO STA YNZ SWSTA 8/66 COTTER | ICW
LC | 125619343 | 008/157 | T2 DI CNTRVL-TBL MTN-ORVL 8/157 RPL POLE | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-09 | 2023-03-08 | 2024-05-20 | Late | 2024-03-07 | -74 | 2024-03-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486529 | T2 DI CNTRVL-TB MT-ORO 6/126 RPL STRW | 70Y
LC | 125619691 | 005/002 | T2 DI VLY SPGS-MARTELL #1 5/2 RPL POLE | VICTOR | ETL.8240.POLE.WOOD | 2023-03-09 | 2023-02-28 | 2024-05-20 | Late | 2024-02-28 | -82 | 2024-02-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495585 | T2 DI VLY SPGS-MARTELL #1 5/2 RPL POLE | 70Y
LC | 125591751 | 038/180 | T2 DI IGNACIO-SOBRANTE 038/180 WASH INST | CONCORD | ETL.4920.INSL.CERA | 2023-03-04 | 2023-03-02 | 2023-11-01 | On-time | 2024-03-01 | 121 | 2024-03-02 | 622 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Contaminated | Insulator | Ground Wash | 45946507 | T2 DI IGNACIO-SOBRANTE 038/180 WASH INST | ICD
LC | 125591759 |  | T2 DI VACA VCVLL JMSN 9/67 COTTER CMT | SACTO | ETL.4100.INSL.NCER | 2023-03-04 | 2023-03-02 | 2023-03-22 | On-time | 2024-03-01 | 345 | 2023-09-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45691534 | T2 DI VACA VCVLL JMSN NR TWR 9/67 COTTER | ICS
LC | 125619795 | 065/006 | T2 DI ELK-GUALALA 65/6 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-03-09 | 2023-02-28 |  | Late | 2024-02-28 |  | 2024-02-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484567 | T2 DI ELK-GUALALA 65/6 RPL POLE | 70Y
LC | 125619801 | 009/016 | T2 DI VLLY SPRNGS-MRTL #1 9/16 RPL STRW | VICTOR | ETL.8240.POLE.WOOD | 2023-03-09 | 2023-02-28 | 2024-05-23 | Late | 2024-02-28 | -85 | 2024-02-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495589 | T2 DI VLLY SPRNGS-MRTL #1 9/16 RPL STRW | 70Y
LC | 125591844 | 016/119 | T2 DI CYCOS CMBRA 16/119 COTTER | PISMOBCH | ETL.8560.INSL.NCER | 2023-03-04 | 2023-03-02 | 2023-08-03 | On-time | 2024-03-01 | 211 | 2023-09-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45706792 | T2 DI CYCOS CMBRA 16/119 COTTER | ICW
LC | 125591898 | :032/207 | T2 DI NTH TWR MRTN JCT#1 32/207 RPR HRDT | CONCORD | ETL.3130.TOWR | 2023-03-04 | 2023-03-02 | 2023-11-07 | On-time | 2024-03-01 | 115 | 2024-03-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008504 | T2 DI NTH TWR MRTN JCT#1 32/207 RPR HRDT | ICQ
LC | 125591961 | :032/207 | T2 DI NTH TWR MRTN JT#1 :32/207 RPR OPGW | CONCORD | ETL.3130.TOWR | 2023-03-04 | 2023-03-02 | 2023-05-09 | On-time | 2024-03-01 | 297 | 2023-09-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45690777 | T2 DI NTH TWR MRTN JCT#1 32/207 RPR OPGW | ICS
LC | 125594863 | 004/026 | T2 DI MRR BY-SL BSP #2 4/26 RPR JMPS | PISMOBCH | ETL.2820.INSL.NCER | 2023-03-06 | 2023-03-02 | 2024-01-12 | On-time | 2024-03-01 | 49 | 2024-03-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45706793 | T2 DI MRR BY-SL BSP #2 4/26 RPR JMPS | ICS
LC | 125620110 | 006/003 | T2 DI VLLY SPRNGS-MRTL #1 6/3 RPL POLE | VICTOR | ETL.8240.POLE.WOOD | 2023-03-09 | 2023-02-28 | 2024-05-23 | Late | 2024-02-28 | -85 | 2024-02-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495586 | T2 DI VLLY SPRNGS-MRTL #1 6/3 RPL POLE | 70Y
LC | 125640891 | 008/098 | T2 DI DIVIDE-CABRILLO#2 08/98 COA | PISMOBCH | ETL.1370.POLE.WOOD | 2023-03-11 | 2023-03-02 | 2024-03-01 | On-time | 2024-03-01 | 0 | 2024-03-02 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125620152 | 003/018 | T2 DI VALLY SPRNGS-MRTL #1 3/18 RPL STRW | VICTOR | ETL.8240.POLE.WOOD | 2023-03-09 | 2023-02-28 | 2024-05-20 | Late | 2024-02-28 | -82 | 2024-02-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495584 | T2 DI VALLY SPRNGS-MRTL #1 3/18 RPL STRW | 70Y
LC | 125641027 | 000/016 | T2 DI LAURELES-OTTER 0/16 RPL POLE | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-03-11 | 2023-03-02 | 2024-01-16 | On-time | 2024-03-01 | 45 | 2024-03-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486635 | T2 DI LAURELES OTTER 0/13 RPL STRW | 70Y
LC | 125620262 | 011/000 | T2 DI PHILO JCT-ELK-ELK 11/0 RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-03-09 | 2023-02-28 | 2024-05-06 | Late | 2024-02-28 | -68 | 2024-02-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484596 | T2 DI PHILO JCT-ELK-ELK 11/0 RPL STRW | 70Y
LC | 125620264 | A005/116 | T2 DI LAKEVILLE #2 A5/116 RPL POLE | LAKEVLLE | ETL.7340.POLE.WOOD | 2023-03-09 | 2023-02-28 |  | Late | 2024-02-28 |  | 2024-02-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31639984 | T2 DI LAKEVILLE #2 A5/116 RPL POLE | 70Y
LC | 125620305 | 010/011 | T2 DI VLLY SPRNGS-MRTL #1 10/11 RPR SPLW | VICTOR | ETL.8240.INSL.NCER | 2023-03-09 | 2023-02-28 | 2024-02-29 | Late | 2024-02-28 | -1 | 2024-02-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Steel | Repair | 45946245 | T2 DI VLLY SPRNGS-MRTL #1 10/11 RPR SPLW | ICS
LC | 125620309 | 013/240 | T2 DI VALLEY SPRINGS #2 13/240 RPR INSW | VICTOR | ETL.9460.INSL.CERA | 2023-03-09 | 2023-02-28 |  | Late | 2024-02-28 |  | 2024-02-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946242 | T2 DI VALLEY SPRINGS #2 13/240 RPR INSW | ICW
LC | 125620329 | 065/009 | T2 DI ELK-GUALALA 065/009 RPL STRW | WILLITS | ETL.8410.POLE.WOOD | 2023-03-09 | 2023-02-28 |  | Late | 2024-02-28 |  | 2024-02-28 | 372 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484567 | T2 DI ELK-GUALALA 65/6 RPL POLE | 70Y
LC | 125641080 | 008/069 | T2 DI CBRLLO-SNT YNZ SW ST 8/69 RMV VEG | PISMOBCH | ETL.1200.POLE.NWOD | 2023-03-11 | 2023-03-02 | 2024-03-01 | On-time | 2024-03-01 | 0 | 2024-03-02 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125620407 | 002/006 | T2 DI MLNS-RCTRCK 002/006 RPL STRW | VICTOR | ETL.2400.POLE.WOOD | 2023-03-09 | 2023-02-28 | 2024-05-13 | Late | 2024-02-28 | -75 | 2024-02-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493016 | T2 DI MLNS-RCTRCK 002/006 RPL STRW | 70Y
LC | 125633255 | 003/001 | T2 DI MENDO-HARTLEY 003/001 RPL POLE | WILLITS | ETL.7510.POLE.WOOD | 2023-03-10 | 2023-02-28 |  | Late | 2024-02-28 |  | 2024-02-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508559 | T2 DI MENDO-HARTLEY 003/001 RPL POLE | 70Y
LC | 125641130 | 002/059 | T2 DI DLT-MTN GT JCT 2/59 RPR INSW | TABLEMTN | ETL.6750.INSL.NCER | 2023-03-11 | 2023-03-02 | 2023-10-12 | On-time | 2024-03-01 | 141 | 2024-03-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45698638 | T2 DI DLT-MTN GT JCT 2/59 RPR INSW | ICW
LC | 125641497 | 015/003 | T2 DI MENDO-HARTLY 15/3 RPR CRSW | WILLITS | ETL.7510.POLE.NWOD | 2023-03-12 | 2023-03-02 | 2024-02-16 | On-time | 2024-03-01 | 14 | 2024-03-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45977492 | T2 DI MENDO-HARTLY 15/3 RPR CRSW | ICW
LC | 125644992 | 000/015 | T2 DI JEFFERSON-STANFORD 0/15 RPR GYWW | METCALF | ETL.7220.POLE.WOOD | 2023-03-13 | 2023-03-02 | 2023-03-02 | On-time | 2024-03-01 | 365 | 2024-03-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45946666 | T2 DI JEFFERSON-STANFORD 0/15 RPR GYWW | ICW
LC | 125633524 | 006/032 | T2 DI IGNCIO-ALTO 6/32 RPL INSS | LAKEVLLE | ETL.7150.INSL.CERA | 2023-03-10 | 2023-02-28 |  | Late | 2024-02-28 |  | 2024-02-28 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667795 | T2 DI IGNCIO-ALTO 6/32 RPL INSS | 93K
LC | 125633601 | 005/098 | T2 DI BRIONES TAP 5/98 CANCEL | CONCORD | ETL.7055.INSL | 2023-03-10 | 2023-03-01 |  | Late | 2024-02-29 |  | 2024-03-01 | 508 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31664057 | T2 EI BRIONES TAP 5/100 RPL INSW | 93I
LC | 125647113 | 039/005A | T2 DI ELK-GUALALA 039/005A RPL HRDW | WILLITS | ETL.8410.POLE.WOOD | 2023-03-13 | 2023-03-02 | 2023-08-29 | On-time | 2024-03-01 | 185 | 2023-09-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45890202 | T2 DI ELK-GUALALA 039/005A RPL HRDW | ICW
LC | 125647162 | 015/067 | T2 DI SN LS OBISPO-OCEANO 15/67L COA | PISMOBCH | ETL.3530.POLE.STPS | 2023-03-13 | 2023-03-02 | 2024-03-01 | On-time | 2024-03-01 | 0 | 2024-03-02 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125634680 | 015/062 | T2 PITTSBURG-SAN MATEO 015/062 RPL INSW | CONCORD | ETL.5463.INSL | 2023-03-10 | 2023-03-10 |  | Late | 2024-03-09 |  | 2024-03-10 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671783 | PITTSBURG-SAN MATEO RPL INSS IN 2 TWRS. | 93K
LC | 125634970 | 016/158 | T2 DI IGNACIO-ALTO 16/158 RPL STRW | LAKEVLLE | ETL.7150.POLE.WOOD | 2023-03-10 | 2023-02-28 |  | Late | 2024-02-28 |  | 2024-02-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483023 | T0 DI IGNACIO-ALTO 013/099 RPL STRW | 70Y
LC | 125647192 | 000/002 | T2 DI UNION CHEMICAL TAP 0/2 RPR INSW | CONCORD | ETL.6351.INSL.NCER | 2023-03-13 | 2023-03-02 | 2023-10-23 | On-time | 2024-03-01 | 130 | 2024-03-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45978088 | T2 DI UNION CHEMICAL TAP 0/2 RPR INSW | ICW
LC | 125648227 | 009/165 | T2 DI VALLEY SPRINGS #2 09/165 RPR STRW | VICTOR | ETL.9460.POLE.NWOD | 2023-03-13 | 2023-03-02 | 2023-09-29 | On-time | 2024-03-01 | 154 | 2024-03-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45907573 | T2 DI VALLEY SPRINGS #2 09/165 RPR STRW | ICW
LC | 125637735 | 026/007 | T2 HARTLY CLEARLAKE 26/7 GO95 | WILLITS | ETL.7515.POLE.WOOD | 2023-03-10 | 2023-03-09 |  | Late | 2024-03-08 |  | 2024-03-09 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31639897 | T2 HARTLY CLEARLAKE 26/7 CLEARANCE | 93G
LC | 125637870 | A004/098 | T2 DI LAKEVILLE #2 A4/98 RPL INSS | LAKEVLLE | ETL.7340.INSL.CERA | 2023-03-10 | 2023-02-28 |  | Late | 2024-02-28 |  | 2024-02-28 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35484587 | T2 DI LAKEVILLE #2 A4/98 RPL INSS | 93I
LC | 125649514 | 008/065 | T2 DI VAC-VCVLL-JMSN-NRTH 8/65 RPR STRT | LAKEVLLE | ETL.4100.TOWR | 2023-03-14 | 2023-03-02 | 2023-10-10 | On-time | 2024-03-01 | 143 | 2024-03-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46009100 | T2 DI VAC-VCVLL-JMSN-NRTH 8/65 RPR STRT | ICQ
LC | 125638280 | 000/002 | T2 DI LUCERNE #2 TAP 0/2 RPL INSW | WILLITS | ETL.2411.INSL.NCER | 2023-03-10 | 2023-03-10 |  | Late | 2024-03-09 |  | 2024-03-10 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35486863 | T2 DI LUCERNE #2 TAP 0/2 RPL INSW | 93I
LC | 125679244 | 008/069 | T2 DI CABRILLO-SANTA YNEZ 8/69 RPR JUMW | PISMOBCH | ETL.1200.INSL.NCER | 2023-03-17 | 2023-03-02 | 2024-01-30 | On-time | 2024-03-01 | 31 | 2024-03-02 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46078515 | T2 DI CABRILLO-SANTA YNEZ 8/69 RPR JUMW | ICW
LC | 125589311 | 006/056 | T2 BUCKS CRK-RCK CRK-CRSTA 6/56 RPL INSW | TABLEMTN | ETL.4430.INSL.CERA | 2023-03-03 | 2023-03-03 | 2024-01-18 | On-time | 2024-03-02 | 44 | 2024-03-03 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667698 | T2 DI BCKS CRK-RCK CRK-CTA RPL INSS 5 ST | 93K
LC | 125592093 | 011/008 | T2 DI MENDOCINO-HARTLEY 11/8R RPR GYWW | WILLITS | ETL.7510.POLE.WDPS | 2023-03-04 | 2023-03-03 | 2024-02-13 | On-time | 2024-03-02 | 18 | 2024-03-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45977493 | T2 DI MENDOCINO-HARTLEY 11/8R RPR GYWW | ICW
LC | 125638989 | 012/007 | T2 DI WINDSR-FITCH MTN 12/7 RPL POLE | LAKEVLLE | ETL.6900.POLE.WOOD | 2023-03-11 | 2023-03-01 |  | Late | 2024-02-29 |  | 2024-03-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484586 | T2 DI WINDSR-FITCH MTN 12/7 RPL POLE | 70Y
LC | 125592098 | 011/008 | T2 DI MENDOCINO-HARTLEY 11/8 RPL INSW | WILLITS | ETL.7510.INSL.NCER | 2023-03-04 | 2023-03-03 | 2024-02-13 | On-time | 2024-03-02 | 18 | 2024-03-03 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35484591 | T2 DI MNDCNO-HARTLEY 8/7 RPL INSW | 93I
LC | 125592255 | 003/073B | T2 DI DLTA MTN GT JCT 3/073B RPR GYWW | TABLEMTN | ETL.6750.POLE.NWOD | 2023-03-04 | 2023-03-03 | 2023-05-04 | On-time | 2024-03-02 | 303 | 2024-03-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698660 | T2 DI DLTA MTN GT JCT 3/073B RPR GYWW | ICW
LC | 125594738 | 003/074A | T2 DI DLTN MTN GT JT 3/074A RPR GYWW | TABLEMTN | ETL.6750.POLE.NWOD | 2023-03-06 | 2023-03-03 | 2023-11-07 | On-time | 2024-03-02 | 116 | 2024-03-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698663 | T2 DI DLTN MTN GT JT 3/074A RPR GYWW | ICW
LC | 125595407 | 011/100 | T2 CRAG VIEW-CASCD 11/100L COMPLETE | TABLEMTN | ETL.1350.POLE.STPS | 2023-03-06 | 2023-03-03 | 2023-11-20 | On-time | 2024-03-02 | 103 | 2023-06-03 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45698581 | T2 CRAG VIEW-CASCD 11/100 RPR FOND | ICW
LC | 125639232 | 001/002A | T2 DI WINDSOR-FITCH MNTN 1/2A RPL STRW | LAKEVLLE | ETL.6900.POLE.WOOD | 2023-03-11 | 2023-03-01 |  | Late | 2024-02-29 |  | 2024-03-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484568 | T2 DI WINDSOR-FITCH MNTN 1/2A RPL STRW | 70Y
LC | 125639238 | 004/004 | T2 DI MELONES-RCTRCK 004/004 RPL INSW | VICTOR | ETL.2400.INSL.NCER | 2023-03-11 | 2023-03-01 | 2024-05-10 | Late | 2024-02-29 | -71 | 2024-03-01 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493019 | T2 DI MELONES-RCTRCK 004/004 RPL INSW | 93I
LC | 125639245 | 007/143 | T2 DI VALLEY SPRINGS #1 007/143 RPL STRW | VICTOR | ETL.8210.POLE.WOOD | 2023-03-11 | 2023-03-01 |  | Late | 2024-02-29 |  | 2024-03-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495527 | T2 DI VALLEY SPRINGS #1 007/143 RPL STRW | 70Y
LC | 125654338 | 009/102 | T2 DI VEDDER TAP 009/102 RPR GYWS | MIDWAY | ETL.2141.POLE.WOOD | 2023-03-14 | 2023-03-03 | 2023-08-17 | On-time | 2024-03-02 | 198 | 2024-03-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45927417 | T2 DI VEDDER TAP 009/102 RPR GYWS | ICW
LC | 125639324 | 007/144 | T2 DI VLLY SPRNGS #1 7/144 GO95 USAGE | VICTOR | ETL.8210.POLE.WOOD | 2023-03-11 | 2023-03-01 |  | Late | 2024-02-29 |  | 2024-03-01 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35529645 | T2 DI VALLEY SPRINGS #1 7/144 GO95 | 93G
LC | 125639327 | 009/186 | T2 DI VALLEY SPRINGS #1 009/186 RPR INSW | VICTOR | ETL.8210.INSL.NCER | 2023-03-11 | 2023-03-01 | 2024-03-27 | Late | 2024-02-29 | -27 | 2024-03-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45946241 | T2 DI VALLEY SPRINGS #1 009/186 RPR INSW | ICW
LC | 125639382 | 003/013 | T2 DI MELONES-RACETRACK 03/13 RPL HRDD | VICTOR | ETL.2400.POLE.WOOD | 2023-03-11 | 2023-03-01 | 2024-05-09 | Late | 2024-02-29 | -70 | 2024-03-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45945338 | T2 DI MELONES-RACETRACK 03/13 RPL HRDD | ICW
LC | 125639486 | 000/003 | T2 DI CLGAT-SMRTVL #2 00/03 RPL STRW | SACTO | ETL.6520.POLE.WOOD | 2023-03-11 | 2023-03-10 |  | Late | 2024-03-09 |  | 2024-03-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481568 | T2 DI CLGAT-SMRTVL#2 00/03 RPL STRW | 70Y
LC | 125639556 | 007/149 | T2 DI VALLEY SPRINGS #1 007/149 RPL POLE | VICTOR | ETL.8210.POLE.WOOD | 2023-03-11 | 2023-03-01 |  | Late | 2024-02-29 |  | 2024-03-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495527 | T2 DI VALLEY SPRINGS #1 007/143 RPL STRW | 70Y
LC | 125654706 | 018/085 | T2 DI VACA-LAKEVILLE #1 018/085 RPL HRDT | LAKEVLLE | ETL.5840.TOWR | 2023-03-14 | 2023-03-03 | 2023-10-16 | On-time | 2024-03-02 | 138 | 2024-03-03 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45989476 | T2 DI VACA-LAKEVILLE #1 018/085 RPL HRDT | ICQ
LC | 125655287 | 003/073C | T2 DI DELTA-MTN GATE JCT 3/73C RPR GYWW | TABLEMTN | ETL.6750.POLE.NWOD | 2023-03-14 | 2023-03-03 | 2023-05-04 | On-time | 2024-03-02 | 303 | 2023-09-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45710513 | T2 DI DELTA-MTN GATE JCT 3/73C RPR GYWW | ICW
LC | 125639747 | 004/025 | T2 DI FULTON-LAKEVILLE 4/25 RPR INSS | LAKEVLLE | ETL.4950.INSL | 2023-03-11 | 2023-03-10 |  | Late | 2024-03-09 |  | 2024-03-10 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45954414 | T2 DI FULTON-LAKEVILLE+ 4/25 RPL HRDT | ICS
LC | 125639827 | 55 | T2 DI ELK CREEK TAP A20/221 RPL SWTC | TABLEMTN | ETL.6921.SWIT | 2023-03-11 | 2023-03-10 |  | Late | 2024-03-09 |  | 2024-03-10 | 427 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Switch-Wood | Replace | 35489962 | T2 EI ELK CREEK TAP A20/221 RPL SWTC | 93H
LC | 125639898 | 008/006 | T2 DI MENDOCINO-HARTLEY 08/06 UNBURY | WILLITS | ETL.7510.POLE.NWOD | 2023-03-11 | 2023-03-01 |  | Late | 2024-02-29 |  | 2023-09-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45763984 | T2 DI MENDOCINO-HARTLEY 08/06 UNBURY | ICW
LC | 125639985 | 010/003 | T2 DI MNDCNO-HRTLY 10/3 RPL ANCW | WILLITS | ETL.7510.POLE.WOOD | 2023-03-11 | 2023-03-01 |  | Late | 2024-02-29 |  | 2024-03-01 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35484589 | T2 DI MNDCNO-HARTLEY 8/7 RPL ANCW | 93E
LC | 125640026 | A001/033 | T2 DI VALLEY SPRNGS #1 A001/033 RPL POLE | VICTOR | ETL.8210.POLE.WOOD | 2023-03-11 | 2023-03-01 | 2024-03-14 | Late | 2024-02-29 | -14 | 2024-03-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495528 | T2 DI VALLEY SPRNGS #1 A001/033 RPL POLE | 70Y
LC | 125655515 | 003/073A | T2 DI DELTA-MOTN GATE JCT 3/73A RPR GYWW | TABLEMTN | ETL.6750.POLE.NWOD | 2023-03-14 | 2023-03-03 | 2023-05-04 | On-time | 2024-03-02 | 303 | 2023-09-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45710512 | T2 DI DELTA-MOTN GATE JCT 3/73A RPR GYWW | ICW
LC | 125663553 | 003/004 | T2 DI MNDCNO-HRTLY 003/004 (R) RPR GYWW | WILLITS | ETL.7510.POLE.STPS | 2023-03-15 | 2023-03-03 | 2024-01-26 | On-time | 2024-03-02 | 36 | 2024-03-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45977494 | T2 DI MNDCNO-HRTLY 003/004 (R) RPR GYWW | ICW
LC | 125640351 | A002/050 | T2 DI VALLEY SPRINGS #1 A02/050 RPL STRW | VICTOR | ETL.8210.POLE.WOOD | 2023-03-11 | 2023-03-01 | 2024-03-16 | Late | 2024-02-29 | -16 | 2024-03-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495528 | T2 DI VALLEY SPRNGS #1 A001/033 RPL POLE | 70Y
LC | 125663711 | 011/125 | T2 DI VEDDER TAP 011/125 RPL HRDD | MIDWAY | ETL.2141.POLE.WOOD | 2023-03-15 | 2023-03-03 | 2023-07-25 | On-time | 2024-03-02 | 221 | 2024-03-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45927419 | T2 DI VEDDER TAP 011/125 RPL HRDD | ICW
LC | 125640507 | 007/002 | T2 DI MENDOCINO-HARTLY 7/2 GO95 RPL STRW | WILLITS | ETL.7510.POLE.WOOD | 2023-03-11 | 2023-03-10 |  | Late | 2024-03-09 |  | 2024-03-10 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35486939 | T2 DI MENDOCINO-HARTLY 7/2 GO95 RPL STRW | 93G
LC | 125792546 | 013/172 | T2 DI VLY SPRNGS-CLAY 13/172 RPR STRW | VICTOR | ETL.8264.POLE.WOOD | 2023-04-04 | 2023-03-03 | 2024-02-07 | On-time | 2024-03-02 | 24 | 2024-03-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45954278 | T2 DI VLY SPRNGS-CLAY 13/172 RPR STRW | ICW
LC | 125640551 | 065/012 | T2 DI ELK-GUALALA 65/12 RPL STRW | WILLITS | ETL.8410.POLE.WOOD | 2023-03-11 | 2023-03-01 |  | Late | 2024-02-29 |  | 2024-03-01 | 372 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484567 | T2 DI ELK-GUALALA 65/6 RPL POLE | 70Y
LC | 125640663 | 019/010 | T2 DI FORT BRAGG-ELK 19/10L COA | WILLITS | ETL.2060.POLE.STPS | 2023-03-11 | 2023-03-10 | 2024-03-22 | Late | 2024-03-09 | -13 | 2023-06-10 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125595485 | 011/221 | T2 EI COLGATE-PALERMO 11/221 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2023-03-06 | 2023-03-06 | 2023-11-11 | On-time | 2024-03-05 | 115 | 2024-03-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45979803 | T2 EI COLGATE-PALERMO 11/221 RPR STRW | ICW
LC | 125596967 | 011/223 | T2 EI COLGATE-PALERMO 011/223 RPR POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-06 | 2023-03-06 | 2023-11-11 | On-time | 2024-03-05 | 115 | 2024-03-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45979805 | T2 EI COLGATE-PALERMO 011/223 RPR POLE | ICW
LC | 125599767 | 006/127 | T2 CENTRVLL-TBL MTN-ORVLL 6/127 RPR INSW | TABLEMTN | ETL.6330.INSL | 2023-03-07 | 2023-03-06 | 2023-04-11 | On-time | 2024-03-05 | 329 | 2024-03-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45698577 | T2 CENTRVLL-TBL MTN-ORVLL 6/127 RPR INSW | ICW
LC | 125604848 | 003/074C | T2 DI DLTA MTN GT JCT 3/074C RPR GYWW | TABLEMTN | ETL.6750.POLE.NWOD | 2023-03-07 | 2023-03-06 | 2023-11-07 | On-time | 2024-03-05 | 119 | 2024-03-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698662 | T2 DI DLTA MTN GT JCT 3/074C RPR GYWW | ICW
LC | 125605033 | 003/074B | T2 DI DLT-MTN GT JCT- 03/74B RPR GYWW | TABLEMTN | ETL.6750.POLE.NWOD | 2023-03-07 | 2023-03-06 | 2023-11-07 | On-time | 2024-03-05 | 119 | 2024-03-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45698661 | T2 DI DLT-MTN GT JCT- 03/74B RPR GYWW | ICW
LC | 125613648 | 014/098 | T2 DI IGNC ALT SSLTO#1 14/098 RMV SHIELD | LAKEVLLE | ETL.7160.TOWR | 2023-03-09 | 2023-03-06 | 2023-10-04 | On-time | 2024-03-05 | 153 | 2024-03-06 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45999883 | T2 DI IGNC ALT SSLTO#1 14/098 RMV SHIELD | ICQ
LC | 125641085 | 006/080 | T2 DI DIVIDE-CABRILLO #1 6/80 RPL STRW | PISMOBCH | ETL.1380.POLE.WOOD | 2023-03-11 | 2023-03-02 |  | Late | 2024-03-01 |  | 2024-03-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507492 | T2 DI DIVIDE-CABRILLO #1 6/80 RPL STRW | 70Y
LC | 125615713 | 000/005 | T2 MORRO BAY - SLO 0/5 RPR STRT | PISMOBCH | ETL.2810.TOWR | 2023-03-09 | 2023-03-06 | 2024-02-22 | On-time | 2024-03-05 | 12 | 2024-03-06 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45977862 | T2 MORRO BAY - SLO 0/5 RPR STRT | ICQ
LC | 125647892 | 049/201 | T2 DI MIDWAY-WHIRLWIND 49/201 RPR SHIELD | MIDWAY | ETL.6030.TOWR | 2023-03-13 | 2023-03-06 | 2024-01-09 | On-time | 2024-03-05 | 56 | 2024-03-06 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46043010 | T2 DI MIDWAY-WHIRLWIND 49/201 RPR SHIELD | ICS
LC | 125663334 | 020/100 | T2 DI FLTN-IGNACIO #1 20/100 RPR STRT | LAKEVLLE | ETL.4680.TOWR | 2023-03-15 | 2023-03-06 | 2023-09-28 | On-time | 2024-03-05 | 159 | 2024-03-06 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45993777 | T2 DI FLTN-IGNACIO #1 20/100 RPR STRT | ICQ
LC | 125603417 | 006/161 | T2 DEL MONTE-VIEJO-VIEJO 6/161 WASH INSW | MOSSLNDG | ETL.6710.INSL.CERA | 2023-03-07 | 2023-03-07 | 2024-02-15 | On-time | 2024-03-06 | 20 | 2024-03-07 | 622 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Contaminated | Insulator | Ground Wash | 46174087 | T2 DEL MONTE-VIEJO-VIEJO 6/161 WASH INSW | ICD
LC | 125684700 | 001/020 | T2 EI PIT #1-MCARTHUR 001/020 RPL POLE | TABLEMTN | ETL.7790.POLE.WOOD | 2023-03-19 | 2023-03-19 |  | Late | 2024-03-18 |  | 2024-03-19 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485425 | T2 EI PIT #1-MCARTHUR -_001/020 RPL PL | 70Y
LC | 125606926 | 036/170 | T2 DI IGNCIO SBRNTE 36/170 COTTER | CONCORD | ETL.4920.INSL.CERA | 2023-03-08 | 2023-03-07 | 2023-11-24 | On-time | 2024-03-06 | 103 | 2024-03-07 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45978090 | T2 DI IGNCIO SBRNTE 36/170 COTTER | ICS
LC | 125608899 | 005/025 | T2 DI PTSBRG ESTSHR 5/25 COTTER | CONCORD | ETL.5462.INSL | 2023-03-08 | 2023-03-07 | 2023-08-15 | On-time | 2024-03-06 | 204 | 2023-09-07 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45844285 | T2 DI PTSBRG ESTSHR 5/25 COTTER | ICS
LC | 125642434 | 003/039 | T2 DI PARADISE-TABLE MTN 03/039 RPL INSS | TABLEMTN | ETL.4316.INSL.NCER | 2023-03-12 | 2023-02-28 |  | Late | 2024-02-28 |  | 2023-08-28 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31670165 | T2 DI PARADISE-TABLE MTN 03/039 RPL INSS | 93K
LC | 125609231 | 036/169 | T2 DI IGNCIO SBRNTE 36/169 RPR INSS | CONCORD | ETL.4960.INSL | 2023-03-08 | 2023-03-07 | 2023-10-12 | On-time | 2024-03-06 | 146 | 2024-03-07 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45954898 | T2 DI IGNCIO SBRNTE 36/169 RPR INSS | ICS
LC | 127080475 | 024/095 | T3 EXCHEQUER-INDN FLT 24/95 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-09-18 | 2023-09-18 | 2023-12-12 | On-time | 2024-03-18 | 97 | 2023-12-18 | 628 | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45995870 | T3 EXCHEQUER-INDN FLT 24/95 RPR JMPS | ICS
LC | 125611525 | 003/028 | T2 DI SBRNT GRZZLY CLRMNT #1 3/28 COTTER | CONCORD | ETL.3740.INSL.CERA | 2023-03-08 | 2023-03-07 | 2023-10-02 | On-time | 2024-03-06 | 156 | 2024-03-07 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45954897 | T2 DI SBRNT GRZZLY CLRMNT #1 3/28 COTTER | ICS
LC | 125678023 | 004/020 | T2 DI SLO-CAYUCOS 004/020 RPR ANCW | PISMOBCH | ETL.9090.POLE.WDPS | 2023-03-17 | 2023-03-07 | 2024-01-13 | On-time | 2024-03-06 | 53 | 2024-03-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46088315 | T2 DI SLO-CAYUCOS 004/020 RPR ANCW | ICW
LC | 125678024 | 004/020 | T2 DI SLO-CAYUCOS 004/020 RPR ANCW | PISMOBCH | ETL.9090.POLE.WDPS | 2023-03-17 | 2023-03-07 | 2024-01-13 | On-time | 2024-03-06 | 53 | 2024-03-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46088316 | T2 DI SLO-CAYUCOS 004/020 RPR ANCW | ICW
LC | 125644381 | 058/000 | T2 DI FRT ROSS-GUALALA 58/0 RMV VEG | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-03-13 | 2023-03-02 | 2024-03-13 | Late | 2024-03-01 | -12 | 2024-03-02 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125644553 | 010/005 | T2 WV EXCHEQUER-MARIPOSA 10/5 RPR SPLW | FRESNO | ETL.8640.INSL.NCER | 2023-03-13 | 2023-03-13 |  | Late | 2024-03-12 |  | 2024-03-13 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45977656 | T2 WV EXCHEQUER-MARIPOSA 10/5 RPR SPLW | ICW
LC | 125678028 | 004/020 | T2 DI SLO-CAYUCOS 004/020 RPR GYWW | PISMOBCH | ETL.9090.POLE.WDPS | 2023-03-17 | 2023-03-07 | 2024-01-13 | On-time | 2024-03-06 | 53 | 2024-03-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088317 | T2 DI SLO-CAYUCOS 004/020 RPR GYWW | ICW
LC | 125645531 | 014/000 | T2 WV HMBLDT-MPLE CRK 14/0 MARKER BALLS | EUREKA | ETL.7130.POLE.STPS | 2023-03-13 | 2023-03-13 |  | Late | 2024-03-12 |  | 2024-03-13 | 671T | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | FAA Lighting-Wood | Install | 35490840 | T2 WV HMBLDT-MPLE CRK 14/0 MARKER BALLS | 93P
LC | 125678120 | 004/020 | T2 DI SLO-CAYUCOS 004/020 RPR GYWW | PISMOBCH | ETL.9090.POLE.WDPS | 2023-03-17 | 2023-03-07 | 2024-01-13 | On-time | 2024-03-06 | 53 | 2024-03-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088318 | T2 DI SLO-CAYUCOS 004/020 RPR GYWW | ICW
LC | 125678122 | 004/020 | T2 DI SLO-CAYUCOS 004/020 RPR GYWW | PISMOBCH | ETL.9090.POLE.WDPS | 2023-03-17 | 2023-03-07 | 2024-01-13 | On-time | 2024-03-06 | 53 | 2024-03-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088340 | T2 DI SLO-CAYUCOS 004/020 RPR GYWW | ICW
LC | 125608011 | 012/237 | T2 EI COLGATE-PALERMO 012/237 RPR POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-08 | 2023-03-08 | 2023-11-11 | On-time | 2024-03-07 | 117 | 2024-03-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45979757 | T2 EI COLGATE-PALERMO 012/237 RPR POLE | ICW
LC | 125647213 | 006/035A | T2 DI JEFFERSON #1 6/35A RPL INSS | METCALF | ETL.6831.INSL.CERA | 2023-03-13 | 2023-03-02 | 2024-04-09 | Late | 2024-03-01 | -39 | 2024-03-02 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510601 | T2 DI JEFFERSON #1 6/35A RPL INSS | 93K
LC | 125647328 | X010/044 | T2 EI DIABLO-MESA X010/044 RPL INSS | PISMOBCH | ETL.4620.INSL | 2023-03-13 | 2023-03-13 | 2024-05-16 | Late | 2024-03-12 | -65 | 2024-03-13 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671707 | T0 DIABLO-MESA RPL INSS 7 LSTS | 93K
LC | 125610218 | 009/178 | T2 EI MNTA VSTA-LOS GATOS 9/178 RPR IBWW | METCALF | ETL.7610.POLE.WOOD | 2023-03-08 | 2023-03-08 | 2024-02-14 | On-time | 2024-03-07 | 22 | 2024-03-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45997627 | T2 EI MNTA VSTA-LOS GATOS 9/178 RPR IBWW | ICW
LC | 125647716 | 006/083 | T2 DI DIVIDE-CBRILO #1- 06/83 RPL STRW | PISMOBCH | ETL.1380.POLE.WOOD | 2023-03-13 | 2023-03-02 | 2024-06-19 | Late | 2024-03-01 | -110 | 2024-03-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507492 | T2 DI DIVIDE-CABRILLO #1 6/80 RPL STRW | 70Y
LC | 125647800 | 007/096 | T2 DI IGNACIO-BOLINAS#2 07/96 RPR INSW | LAKEVLLE | ETL.7180.INSL.NCER | 2023-03-13 | 2023-03-02 |  | Late | 2024-03-01 |  | 2024-03-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45954901 | T2 DI IGNACIO-BOLINAS#2 07/96 RPR INSW | ICW
LC | 125647887 | 45 | T2 DI IONE TAP 0/1 RPR SWTC | VICTOR | ETL.8253.SWIT | 2023-03-13 | 2023-03-13 | 2024-04-19 | Late | 2024-03-12 | -38 | 2024-03-13 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 45977983 | T2 DI IONE 0/1 RPR SWTC | ICE
LC | 125612477 | 009/043 | T2 EI DIABLO-GATES #1 9/43 RPR GYWT | PISMOBCH | ETL.5960.TOWR | 2023-03-08 | 2023-03-08 | 2024-02-23 | On-time | 2024-03-07 | 13 | 2024-03-08 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 45977475 | T2 EI DIABLO-GATES #1 9/43 RPR GYWT | ICQ
LC | 125618277 | 005/111 | T2 DI CNTVIL TBL MT ORVIL 5/111 COTTER | TABLEMTN | ETL.6330.INSL.NCER | 2023-03-09 | 2023-03-08 | 2023-11-30 | On-time | 2024-03-07 | 98 | 2024-03-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45979783 | T2 DI CNTVIL TBL MT ORVIL 5/111 COTTER | ICW
LC | 125618467 | 011/009 | T2 DI WNDSOR FTCH MTN 11/009 COTTER | LAKEVLLE | ETL.6900.INSL.NCER | 2023-03-09 | 2023-03-08 | 2023-04-13 | On-time | 2024-03-07 | 329 | 2024-03-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 43749442 | EI WNDSR-FTCH MNTN WSIP TAGS | ICW
LC | 125662957 | 041/004 | T2 DI ELK-GUALALA 041/004 RPL INSW | WILLITS | ETL.8410.INSL.NCER | 2023-03-15 | 2023-03-08 | 2024-01-11 | On-time | 2024-03-07 | 56 | 2024-03-08 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35486535 | T2 DI ELK-GUALALA 041/004 RPL INSW | 93I
LC | 125648221 | 018/006 | T2 DI FORT BRAGG-ELK 018/006 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-13 | 2023-03-13 | 2024-04-20 | Late | 2024-03-12 | -39 | 2024-03-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487325 | T2 EI FORT BRAGG-ELK 18/04 RPL STRW | 70Y
LC | 125663531 | 041/000 | T2 DI ELK-GUALA 41/0 RPR CNDW | WILLITS | ETL.8410.INSL.NCER | 2023-03-15 | 2023-03-08 | 2024-01-11 | On-time | 2024-03-07 | 56 | 2024-03-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45988984 | T2 DI ELK-GUALA 41/0 RPR CNDW | ICW
LC | 125682998 | 051/210 | T2 DI MDWY-WHRLWND 51/210 RPR SHIELD | MIDWAY | ETL.6030.TOWR | 2023-03-18 | 2023-03-08 | 2024-01-05 | On-time | 2024-03-07 | 62 | 2024-03-08 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46024378 | T2 DI MDWY-WHRLWND 51/210 RPR SHIELD | ICS
LC | 125705652 | 003/076 | T2 DI CNTRVIL-TBL MTN-ORVL 3/76 RPL SPLW | TABLEMTN | ETL.6330.INSL.NCER | 2023-03-21 | 2023-03-08 | 2023-11-30 | On-time | 2024-03-07 | 98 | 2024-03-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Replace | 45979699 | T2 DI CNTRVIL-TBL MTN-ORVL 3/76 RPL SPLW | ICW
LC | 125649699 | 005/002 | T2 DI LAKEVILLE #1 5/2 RPR CRSW | LAKEVLLE | ETL.7360.POLE.NWOD | 2023-03-14 | 2023-03-03 | 2024-05-09 | Late | 2024-03-02 | -68 | 2024-03-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45954418 | T2 DI LAKEVILLE #1 5/2 RPR CRSW | ICW
LC | 125650001 | 017/006 | T2 DI MNDCNO-HARTLEY 17/6 RPR GYWW | WILLITS | ETL.7510.POLE.WOOD | 2023-03-14 | 2023-03-03 |  | Late | 2024-03-02 |  | 2024-03-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45977499 | T2 DI MNDCNO-HARTLEY 17/6 RPR GYWW | ICW
LC | 125705709 | 006/120 | T2 DI CNTRVL-TBL MTN-ORVL 6/120 RPR STRW | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-21 | 2023-03-08 | 2024-03-04 | On-time | 2024-03-07 | 3 | 2024-03-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45979784 | T2 DI CNTRVL-TBL MTN-ORVL 6/120 RPR STRW | ICW
LC | 125705919 | 004/085 | T2 DI CNTRVL-TBL MTN-ORVL 4/85 RPR INSW | TABLEMTN | ETL.6330.INSL | 2023-03-21 | 2023-03-08 | 2023-11-30 | On-time | 2024-03-07 | 98 | 2024-03-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45979780 | T2 DI CNTRVL-TBL MTN-ORVL 4/85 RPR INSW | ICW
LC | 125706363 | 67 | T2 DI CNTRVL-TBLMTN-OROVL 03/70 RPR SWTC | TABLEMTN | ETL.6330.SWIT | 2023-03-21 | 2023-03-08 | 2024-03-07 | On-time | 2024-03-07 | 0 | 2024-03-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 45979698 | T2 DI CNTRVL-TBLMTN-OROVL 03/70 RPR SWTC | ICW
LC | 125706603 | 009/184 | T2 DI CNTRVL-TBLMTN-ORVLL 9/184 RPR POLE | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-21 | 2023-03-08 | 2023-11-30 | On-time | 2024-03-07 | 98 | 2024-03-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45989481 | T2 DI CNTRVL-TBLMTN-ORVLL 9/184 RPR POLE | ICW
LC | 125706758 | 004/089 | T2 DI CTRVL-TBLMTN-ORVL 004/089 RPR STRW | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-21 | 2023-03-08 | 2023-11-30 | On-time | 2024-03-07 | 98 | 2024-03-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45979781 | T2 DI CTRVL-TBLMTN-ORVL 004/089 RPR STRW | ICW
LC | 125652210 | 037/006 | T2 DI ELK-GUALALA 037/006 COTTER | WILLITS | ETL.8410.INSL.NCER | 2023-03-14 | 2023-03-13 |  | Late | 2024-03-12 |  | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45977980 | T2 DI ELK-GUALALA 037/006 COTTER | ICW
LC | 125709334 | 012/001 | T2 DI MNDCINO-HARTLEY 12/1 RPL ANCW | WILLITS | ETL.7510.POLE.STPS | 2023-03-22 | 2023-03-08 | 2024-02-15 | On-time | 2024-03-07 | 21 | 2024-03-08 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35484589 | T2 DI MNDCNO-HARTLEY 8/7 RPL ANCW | 93E
LC | 125709858 | 052/211 | T2 DI MIDWAY-WHIRLWIND 52/211 COMPELTE | MIDWAY | ETL.6030.TOWR | 2023-03-22 | 2023-03-08 | 2023-06-14 | On-time | 2024-03-07 | 267 | 2024-03-08 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Tower | Install | 45848800 | T2 DI MIDWAY-WHIRLWIND 52/211 INS HRDT | ICQ
LC | 125653111 | 17 | T2 DI IGNACI-BLNS #1 14/149 RPR SWTC | LAKEVLLE | ETL.7140.SWIT | 2023-03-14 | 2023-03-02 |  | Late | 2024-03-01 |  | 2023-09-02 | 623 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Out of Adjustment | Switch | Repair | 45954419 | T2 DI IGNACI-BLNS #1 14/149 RPR SWTC | ICE
LC | 125654119 | 017/003 | T2 LAYTONVILLE-WILLITS 017/003 INS DMPW | WILLITS | ETL.8360.INSL.NCER | 2023-03-14 | 2023-03-14 |  | Late | 2024-03-13 |  | 2024-03-14 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 45977991 | T2 LAYTONVILLE-WILLITS 017/003 INS DMPW | ICW
LC | 125654281 | A006/126 | T2 DI LAKEVILLE #2 A6/126 RPR CRSW | LAKEVLLE | ETL.7340.POLE.WOOD | 2023-03-14 | 2023-03-03 | 2024-05-03 | Late | 2024-03-02 | -62 | 2024-03-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45954417 | T2 DI LAKEVILLE #2 A6/126 RPR CRSW | ICW
LC | 125616854 | 000/011 | T2 EI PIT #1-MCARTHUR 000/011 RMV VEG | TABLEMTN | ETL.7790.POLE.WOOD | 2023-03-09 | 2023-03-09 | 2024-01-22 | On-time | 2024-03-08 | 46 | 2024-03-09 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125617190 | 000/004 | T2 MRRO BAY-TMPLTN 0/4 RPR INST | PISMOBCH | ETL.5933.INSL.CERA | 2023-03-09 | 2023-03-09 | 2023-11-01 | On-time | 2024-03-08 | 128 | 2024-03-09 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46056197 | T2 MRRO BAY-TMPLTN 0/4 RPR INST | ICS
LC | 125706303 | 009/186 | T2 DI CNTRVL-TB MNT-ORVLL 9/186 RPR STRW | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-21 | 2023-03-09 | 2023-11-30 | On-time | 2024-03-08 | 99 | 2024-03-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45979789 | T2 DI CNTRVL-TB MNT-ORVLL 9/186 RPR STRW | ICW
LC | 125706449 | 008/172 | T2 DI CNTRVL-TB MT-ORO 8/172 RPR STRW | TABLEMTN | ETL.6330.POLE.NWOD | 2023-03-21 | 2023-03-09 | 2024-02-02 | On-time | 2024-03-08 | 35 | 2024-03-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45979788 | T2 DI CNTRVL-TB MT-ORO 8/172 RPR STRW | ICW
LC | 125633316 | 006/057 | T2 BUCKS CREEK-ROCK CRESTA 6/57 RPL INS | TABLEMTN | ETL.4430.INSL.CERA | 2023-03-10 | 2023-03-10 | 2024-01-16 | On-time | 2024-03-09 | 53 | 2024-03-10 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667698 | T2 DI BCKS CRK-RCK CRK-CTA RPL INSS 5 ST | 93K
LC | 125654952 | 17 | T2 DI MNDCNO-HRTLY 017/007 RPR SWITCH | WILLITS | ETL.7510.SWIT | 2023-03-14 | 2023-03-03 |  | Late | 2024-03-02 |  | 2024-03-03 | 623 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Out of Adjustment | Switch | Repair | 45977800 | T2 DI MNDCNO-HRTLY 017/007 RPR SWITCH | ICE
LC | 125655006 | 017/246 | T2 DI VLY SPRNGS-CLY 17/246 RPR GYWW | VICTOR | ETL.8264.POLE.NWOD | 2023-03-14 | 2023-03-03 |  | Late | 2024-03-02 |  | 2024-03-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45954279 | T2 DI VLY SPRNGS-CLY 17/246 RPR GYWW | ICW
LC | 125633928 | 006/101 | T2 EI SAN MATEO-HILLSDALE JCT 6/1 CANCEL | METCALF | ETL.7950.POLE.WOOD | 2023-03-10 | 2023-03-10 | 2023-06-14 | On-time | 2024-03-09 | 269 | 2023-06-10 | 625 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Customer Issue | Other | Access Issue | 45706650 | T2 EI SAN MATEO-HILLSDALE JCT 6/1 CGI | ICH
LC | 125635445 | 002/032 | T2 EI PARADISE-BUTTE 002/032 RPR INSW | TABLEMTN | ETL.4396.INSL.NCER | 2023-03-10 | 2023-03-10 | 2024-01-23 | On-time | 2024-03-09 | 46 | 2024-03-10 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45979798 | T2 EI PARADISE-BUTTE 002/032 RPR INSW | ICS
LC | 125638054 | 000/001 | T2 DI LUCERNE #2 TAP 00/01 COTTER | WILLITS | ETL.2411.INSL.CERA | 2023-03-10 | 2023-03-10 | 2023-09-05 | On-time | 2024-03-09 | 186 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45704503 | T2 DI LUCERNE #2 TAP 00/01 COTTER | ICW
LC | 125638914 | 021/094 | T2 DI PITTSBURG-TESLA#2 21/94 RPL INSS | CONCORD | ETL.5520.INSL.CERA | 2023-03-11 | 2023-03-10 | 2024-02-04 | On-time | 2024-03-09 | 34 | 2024-03-10 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31679040 | T2 DI PITTSBURG-TESLA#2 21/94 RPL INSS | 93K
LC | 125639117 | 021/006 | T2 DI FORT BRAGG-ELK 021/006 RPR GYWW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-11 | 2023-03-10 | 2023-11-10 | On-time | 2024-03-09 | 120 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45977804 | T2 DI FORT BRAGG-ELK 021/006 RPR GYWW | ICW
LC | 125639122 | 000/002 | T2 DI LUCERNE # 1 TAP 00/02 RPR INSW | WILLITS | ETL.1331.INSL.NCER | 2023-03-11 | 2023-03-10 | 2023-11-30 | On-time | 2024-03-09 | 100 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45977488 | T2 DI LUCERNE # 1 TAP 00/02 RPR INSW | ICW
LC | 125657681 | 002/005 | T2 FORT BRAGG-ELK 2/5 GO95 CLEARNCE | WILLITS | ETL.2060.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2024-04-10 | Late | 2024-03-14 | -27 | 2024-03-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31642140 | T2 FORT BRAGG-ELK - 9/010 GO95 | 93G
LC | 125639179 | 004/003 | T2 DI MENDOCINO HARTLEY 004/003 RPL POLE | WILLITS | ETL.7510.POLE.WOOD | 2023-03-11 | 2023-03-10 | 2024-02-13 | On-time | 2024-03-09 | 25 | 2024-03-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486938 | T2 DI MENDOCINO HARTLEY 004/003 RPL POLE | 70Y
LC | 125639223 | 17 | T2 DI PARDEE #1 TAP 000/000 RPR SWTCH | VICTOR | ETL.8231.SWIT | 2023-03-11 | 2023-03-10 | 2024-02-09 | On-time | 2024-03-09 | 29 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 45954321 | T2 DI PARDEE #1 TAP 000/000 RPR SWTCH | ICW
LC | 125639268 | 061/009 | T2 DI ELK-GUALALA 61/9 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-03-11 | 2023-03-10 | 2024-01-29 | On-time | 2024-03-09 | 40 | 2024-03-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486936 | T2 DI ELK-GUALALA 61/9 RPL POLE | 70Y
LC | 125639594 | 001/024C | T2 DI JOLON TAP 1/24C COTTER | MOSSLNDG | ETL.7321.INSL.CERA | 2023-03-11 | 2023-03-10 | 2023-12-08 | On-time | 2024-03-09 | 92 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46016584 | T2 DI JOLON TAP 1/24C COTTER | ICW
LC | 125639659 | 004/025 | T2 DI FULTON-IGNACIO #1 4/25 RMV VEG | LAKEVLLE | ETL.4680.TOWR | 2023-03-11 | 2023-03-10 | 2023-09-11 | On-time | 2024-03-09 | 180 | 2024-03-10 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125658475 | 001/003 | T2 POTTER VALLEY-WILLITS 1/3 REFRAME | WILLITS | ETL.7820.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2024-05-10 | Late | 2024-03-14 | -57 | 2024-03-15 | 637 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31639794 | T2 POTTER VALLEY-WILLITS 1/3 REFRAME | 93E
LC | 125662880 | 046/001 | T2 DI ELK-GUALALA 46/01 RPR STRW | WILLITS | ETL.8410.POLE.WOOD | 2023-03-15 | 2023-03-10 | 2024-01-08 | On-time | 2024-03-09 | 61 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45977811 | T2 DI ELK-GUALALA 46/01 RPR STRW | ICW
LC | 125662950 | 063/011 | T2 DI ELK-GUALALA 63/11 RPR INSW | WILLITS | ETL.8410.INSL.NCER | 2023-03-15 | 2023-03-10 | 2024-01-30 | On-time | 2024-03-09 | 39 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45988983 | T2 DI ELK-GUALALA 63/11 RPR INSW | ICW
LC | 125662951 | 063/011 | T2 DI ELK-GUALALA 63/11 RPR STRW | WILLITS | ETL.8410.POLE.WOOD | 2023-03-15 | 2023-03-10 | 2024-01-30 | On-time | 2024-03-09 | 39 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45977490 | T2 DI ELK-GUALALA 63/11 RPR STRW | ICW
LC | 125663163 | 045/009 | T2 DI ELK-GUALALA 045/009 ANTI SPLIT | WILLITS | ETL.8410.POLE.WOOD | 2023-03-15 | 2023-03-10 | 2024-01-10 | On-time | 2024-03-09 | 59 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45977809 | T2 DI ELK-GUALALA 045/009 ANTI SPLIT | ICW
LC | 125663207 | 061/001 | T2 DI ELK-GUALA 61/1 REFRAME | WILLITS | ETL.8410.POLE.WOOD | 2023-03-15 | 2023-03-10 | 2024-01-30 | On-time | 2024-03-09 | 39 | 2024-03-10 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35486951 | T2 DI ELK-GUALA 61/1 REFRAME | 93E
LC | 125663536 | 045/005 | T2 DI ELK-GUALALA 045/005 RPR GYWW | WILLITS | ETL.8410.POLE.WOOD | 2023-03-15 | 2023-03-10 | 2024-01-10 | On-time | 2024-03-09 | 59 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45977807 | T2 DI ELK-GUALALA 045/005 RPR GYWW | ICW
LC | 125663639 | 061/007 | T2 DI ELK-GUALA 61/7 ANTI SPLIT | WILLITS | ETL.8410.POLE.WOOD | 2023-03-15 | 2023-03-10 | 2024-01-30 | On-time | 2024-03-09 | 39 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45988985 | T2 DI ELK-GUALA 61/7 ANTI SPLIT | ICW
LC | 125721566 | 009/178 | T2 DI CENTVLL-TBLMTN-ORO 9/178 RPR POLE | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-23 | 2023-03-10 | 2023-12-01 | On-time | 2024-03-09 | 99 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45989480 | T2 DI CENTVLL-TBLMTN-ORO 9/178 RPR POLE | ICW
LC | 125721607 | 000/009 | T2 DI CHINESE CAMP 000/009 RPR POLE | VICTOR | ETL.2392.POLE.WOOD | 2023-03-23 | 2023-03-10 | 2023-03-31 | On-time | 2024-03-09 | 344 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45736279 | T2 DI CHINESE CAMP 000/009 RPR POLE | ICW
LC | 125721690 | 008/002 | T2 DI MNDCNO-HRTLY 008/002 RPL POLE | WILLITS | ETL.7510.POLE.WOOD | 2023-03-23 | 2023-03-10 | 2024-02-16 | On-time | 2024-03-09 | 22 | 2024-03-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486938 | T2 DI MENDOCINO HARTLEY 004/003 RPL POLE | 70Y
LC | 125722139 | 020/220 | T2 DI ELK CREEK TAP 020/220 RPL SPLW | TABLEMTN | ETL.6921.INSL.NCER | 2023-03-23 | 2023-03-10 | 2023-12-15 | On-time | 2024-03-09 | 85 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Replace | 45979790 | T2 DI ELK CREEK TAP 020/220 RPL SPLW | ICW
LC | 125722197 | 001/023B | T2 DI JOLON TP 1/23B RPL HRDW | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-03-23 | 2023-03-10 | 2023-12-17 | On-time | 2024-03-09 | 83 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46016583 | T2 DI JOLON TP 1/23B RPL HRDW | ICW
LC | 125660987 | 013/265 | T2 EI COLGATE-PALERMO 013/265 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2024-04-24 | Late | 2024-03-14 | -41 | 2024-03-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490107 | T2 EI COLGATE-PALERMO 013/265 RPL POLE | 70Y
LC | 125661053 | 010/016 | T2 VALLEY SPRINGS-MARTELL #1 10/16 GO95 | VICTOR | ETL.8240.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2024-05-22 | Late | 2024-03-14 | -69 | 2024-03-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31646109 | T2 VALLEY SPRINGS-MARTELL #1 10/16 GO95 | 93G
LC | 125724135 | 000/014 | T2 DI BNA VSTA BMS PW 0/14 RPR GYWW | VICTOR | ETL.8252.POLE.NWOD | 2023-03-24 | 2023-03-10 | 2023-10-14 | On-time | 2024-03-09 | 147 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45954327 | T2 DI BNA VSTA BMS PW 0/14 RPR GYWW | ICW
LC | 125662036 | 000/014 | T2 PINE GROVE TAP 0/14 GO95 | VICTOR | ETL.8351.POLE.WOOD | 2023-03-15 | 2023-03-15 |  | Late | 2024-03-14 |  | 2023-09-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640262 | T2 PINE GROVE TAP _0/014 GO95 | 93G
LC | 125724223 | 008/005 | T2 DI MENDOCINO-HARTLEY 8/5 RPR GYWW | WILLITS | ETL.7510.POLE.STPS | 2023-03-24 | 2023-03-10 | 2024-02-16 | On-time | 2024-03-09 | 22 | 2023-09-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45954904 | T2 DI MENDOCINO-HARTLEY 8/5 RPR GYWW | ICW
LC | 125662800 | 016/015 | T2 DI KONOCTI-MIDDLETOWN 16/15 RPR STRW | WILLITS | ETL.6380.POLE.WOOD | 2023-03-15 | 2023-03-06 | 2024-04-07 | Late | 2024-03-05 | -33 | 2024-03-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45988989 | T2 DI KONOCTI-MIDDLETOWN 16/15 RPR STRW | ICW
LC | 125724224 | 008/005 | T2 DI MENDOCINO-HARTLEY 8/5 RPR GYWW | WILLITS | ETL.7510.POLE.STPS | 2023-03-24 | 2023-03-10 | 2024-02-16 | On-time | 2024-03-09 | 22 | 2023-09-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45954905 | T2 DI MENDOCINO-HARTLEY 8/5 RPR GYWW | ICW
LC | 125725522 | 000/011 | T2 DI BUENA VSTA BMS PW 0/11 RPR POLE | VICTOR | ETL.8252.POLE.WOOD | 2023-03-24 | 2023-03-10 | 2024-01-17 | On-time | 2024-03-09 | 52 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45954323 | T2 DI BUENA VSTA BMS PW 0/11 RPR POLE | ICW
LC | 125725575 | 011/106 | T2 DI BRGVIL-CTNWD 11/106L RPR GYWW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-03-24 | 2023-03-10 | 2023-10-25 | On-time | 2024-03-09 | 136 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45979820 | T2 DI BRGVIL-CTNWD 11/106L RPR GYWW | ICW
LC | 125726774 | 010/046 | T2 DI BRENTWOOD-KELSO 10/46 RPL HRDT | CONCORD | ETL.4410.TOWR | 2023-03-24 | 2023-03-10 | 2024-01-03 | On-time | 2024-03-09 | 66 | 2024-03-10 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45997296 | T2 DI BRENTWOOD-KELSO 10/46 RPL HRDT | ICQ
LC | 125726847 | 000/011A | T2 DI BNA VSTA BMS PW 0/11A RPR POLE | VICTOR | ETL.8252.POLE.WOOD | 2023-03-24 | 2023-03-10 | 2023-10-14 | On-time | 2024-03-09 | 147 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45954324 | T2 DI BNA VSTA BMS PW 0/11A RPR POLE | ICW
LC | 125726848 | 000/011A | T2 DI BNA VSTA BMS PW 0/11A RPL HRDW | VICTOR | ETL.8252.POLE.WOOD | 2023-03-24 | 2023-03-10 | 2023-10-14 | On-time | 2024-03-09 | 147 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45954326 | T2 DI BNA VSTA BMS PW 0/11A RPL HRDW | ICW
LC | 125663157 | 006/053 | T2 DIVIDE-VANDENBERG #1 6/053 RPL ANCW | PISMOBCH | ETL.8620.POLE.WOOD | 2023-03-15 | 2023-03-15 |  | Late | 2024-03-14 |  | 2023-09-15 | 637T | TLN | CREW | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35490504 | T2 DIVIDE-VANDENBERG #1 _5/049 RPL ANCW | 93E
LC | 125728751 | 020/010 | T2 DI FRT BRG-ELK 20/10 COMPLETE | WILLITS | ETL.2060.POLE.WOOD | 2023-03-24 | 2023-03-10 | 2024-03-07 | On-time | 2024-03-09 | 2 | 2024-03-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514951 | T2 DI FRT BRG-ELK 20/10 RPL POLE | 70Y
LC | 125663173 | 005/049 | T2 DIVIDE-VANDENBERG #1 5/49 RPL ANCW | PISMOBCH | ETL.8620.POLE.WOOD | 2023-03-15 | 2023-03-15 |  | Late | 2024-03-14 |  | 2024-03-15 | 637T | TLN | CREW | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35490504 | T2 DIVIDE-VANDENBERG #1 _5/049 RPL ANCW | 93E
LC | 125728757 | 009/089 | T2 DI BRDGVLLE-CTTNWD 009/089R RPR STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-03-24 | 2023-03-10 | 2023-10-07 | On-time | 2024-03-09 | 154 | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45979799 | T2 DI BRDGVLLE-CTTNWD 009/089R RPR STRW | ICW
LC | 125730180 | 25 | T2 DI PARDEE #2 TAP 0/1 RPR SWTC | VICTOR | ETL.8251.SWIT | 2023-03-24 | 2023-03-10 | 2024-01-31 | On-time | 2024-03-09 | 38 | 2024-03-10 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 45954322 | T2 DI PARDEE #2 TAP 0/1 RPR SWTC | ICE
LC | 125730766 | 008/000 | T2 DI MENDO-HARTLEY- 08/00 RPL POLE | WILLITS | ETL.7510.POLE.WOOD | 2023-03-25 | 2023-03-10 | 2024-02-16 | On-time | 2024-03-09 | 22 | 2024-03-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486938 | T2 DI MENDOCINO HARTLEY 004/003 RPL POLE | 70Y
LC | 125663236 | 040/000 | T2 DI ELK-GUALALA 040/000R RMV VEG | WILLITS | ETL.8410.POLE.WDPS | 2023-03-15 | 2023-03-15 | 2024-04-15 | Late | 2024-03-14 | -32 | 2024-03-15 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125686073 | 008/069 | T2 DI CABRILLO-SANTA YNEZ 8/69 RPL HRDD | PISMOBCH | ETL.1200.POLE.NWOD | 2023-03-20 | 2023-03-11 | 2024-01-30 | On-time | 2024-03-10 | 40 | 2024-03-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46078517 | T2 DI CABRILLO-SANTA YNEZ 8/69 RPL HRDD | ICW
LC | 125663337 | 020/100 | T2 DI FLTN-IGNACIO #1 20/100 RPL INSS | LAKEVLLE | ETL.4680.INSL | 2023-03-15 | 2023-03-06 |  | Late | 2024-03-05 |  | 2024-03-06 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667836 | DI FLTN-IGNACIO #1 20/100 RPL INSS | 93K
LC | 125663370 | 060/009 | T2 DI ELK-GUALALA 60/09 RPL STRW | WILLITS | ETL.8410.POLE.WOOD | 2023-03-15 | 2023-03-10 |  | Late | 2024-03-09 |  | 2024-03-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486830 | T2 DI ELK-GUALALA 60/09 RPL STRW | 70Y
LC | 125644155 | 025/415 | T2 Keswick-Trinity 025/415 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-03-13 | 2023-03-13 | 2023-11-11 | On-time | 2024-03-12 | 122 | 2024-03-13 | 372 | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31639790 | T2 KESWICK-TRINITY 025/415 RPL POLE | 70Y
LC | 125647483 | 046/005 | T2 DI ELK-GUALALA 46/5 COTTER | WILLITS | ETL.8410.INSL.NCER | 2023-03-13 | 2023-03-13 | 2024-01-08 | On-time | 2024-03-12 | 64 | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45977982 | T2 DI ELK-GUALALA 46/5 COTTER | ICW
LC | 125648007 | 057/002 | T2 DI ELK-GUALALA 57/2 RPR STRW | WILLITS | ETL.8410.POLE.WOOD | 2023-03-13 | 2023-03-13 | 2024-01-19 | On-time | 2024-03-12 | 53 | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45977818 | T2 DI ELK-GUALALA 57/2 RPR STRW | ICW
LC | 125648009 | 057/002 | T2 DI ELK-GUALALA 57/2 COTTER | WILLITS | ETL.8410.INSL.CERA | 2023-03-13 | 2023-03-13 | 2024-01-19 | On-time | 2024-03-12 | 53 | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45977819 | T2 DI ELK-GUALALA 57/2 COTTER | ICW
LC | 125663545 | 011/139 | T2 DI W PT-VLY SPRNGS 11/139 COTTER | VICTOR | ETL.8350.INSL.NCER | 2023-03-15 | 2023-03-15 |  | Late | 2024-03-14 |  | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45977996 | T2 DI W PT-VLY SPRNGS 11/139 COTTER | ICW
LC | 125648090 | 015/182 | T2 DI ELK CREEK TAP 015/182 RPR ANCW | TABLEMTN | ETL.6921.POLE.WOOD | 2023-03-13 | 2023-03-13 | 2023-11-05 | On-time | 2024-03-12 | 128 | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45996408 | T2 DI ELK CREEK TAP 015/182 RPR ANCW | ICW
LC | 125648393 | 015/001 | T2 DI FORT BRAGG-ELK 15/01 RPR INSW | WILLITS | ETL.2060.INSL.CERA | 2023-03-13 | 2023-03-13 | 2024-03-04 | On-time | 2024-03-12 | 8 | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45977812 | T2 DI FORT BRAGG-ELK 15/01 RPR INSW | ICW
LC | 125650519 | 014/000 | T2 DI FORT BRAGG-ELK 14/0 RPR STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-14 | 2023-03-13 | 2024-02-26 | On-time | 2024-03-12 | 15 | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45977816 | T2 DI FORT BRAGG-ELK 14/0 RPR STRW | ICW
LC | 125651613 | 013/006 | T2 DI FORT BRAGG-ELK 13/6 RPR HRDW | WILLITS | ETL.2060.POLE.WDPS | 2023-03-14 | 2023-03-13 | 2024-02-20 | On-time | 2024-03-12 | 21 | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46200277 | T2 DI FORT BRAGG-ELK 13/6 RPR HRDW | ICW
LC | 125651616 | 013/006 | T2 DI FORT BRAGG-ELK 13/6 RPL INSW | WILLITS | ETL.2060.INSL.CERA | 2023-03-14 | 2023-03-13 | 2024-02-27 | On-time | 2024-03-12 | 14 | 2024-03-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35487935 | T2 DI FORT BRAGG-ELK 13/6 RPL INSW | 93I
LC | 125652903 | 018/001 | T2 DI FRT BRAGG-ELK 018/001 RPL INSW | WILLITS | ETL.2060.INSL.CERA | 2023-03-14 | 2023-03-13 | 2024-03-05 | On-time | 2024-03-12 | 7 | 2024-03-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35487707 | T2 DI FRT BRAGG-ELK 018/001 RPL INSW | 93I
LC | 125653020 | 057/001 | T2 DI ELK-GUALALA 57/1 COTTER | WILLITS | ETL.8410.INSL.NCER | 2023-03-14 | 2023-03-13 | 2024-01-18 | On-time | 2024-03-12 | 54 | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45977817 | T2 DI ELK-GUALALA 57/1 COTTER | ICW
LC | 125654645 | 018/005 | T2 DI FORT BRAGG-ELK 018/005 RPL POLE | WILLITS | ETL.2060.POLE.WOOD | 2023-03-14 | 2023-03-13 | 2024-03-07 | On-time | 2024-03-12 | 5 | 2024-03-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487325 | T2 EI FORT BRAGG-ELK 18/04 RPL STRW | 70Y
LC | 125663730 | 057/000 | T2 DI ELK-GUALALA-057/00 RMV VEG | WILLITS | ETL.8410.POLE.WOOD | 2023-03-15 | 2023-03-13 | 2024-03-13 | Late | 2024-03-12 | -1 | 2024-03-13 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125655852 | 000/002C | T2 DI PTTSBRG-TESLA #2 00/002C RPL INSS | CONCORD | ETL.5520.INSL.CERA | 2023-03-14 | 2023-03-13 | 2024-02-04 | On-time | 2024-03-12 | 37 | 2024-03-13 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31652131 | T2 DI PTTSBRG-TESLA #2 00/002C RPL INSS | 93K
LC | 125663764 | 011/147 | T2 DI VLLY SPRNGS-CLAY 11/147 RPL INSW | VICTOR | ETL.8264.INSL.NCER | 2023-03-15 | 2023-03-14 |  | Late | 2024-03-13 |  | 2024-03-14 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35495593 | T2 DI VLLY SPRNGS-CLAY 11/147 RPL INSW | 93I
LC | 125663137 | 057/006 | T2 DI ELK-GUALALA 057/006 RPL STRW | WILLITS | ETL.8410.POLE.WOOD | 2023-03-15 | 2023-03-13 | 2024-01-23 | On-time | 2024-03-12 | 49 | 2024-03-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487383 | T2 DI ELK-GUALALA 057/006 RPL STRW | 70Y
LC | 125663622 | 046/008 | T2 DI ELK-GUALALA 46/08 RPR IBWW | WILLITS | ETL.8410.POLE.WOOD | 2023-03-15 | 2023-03-13 | 2024-01-08 | On-time | 2024-03-12 | 64 | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45977984 | T2 DI ELK-GUALALA 46/08 RPR IBWW | ICW
LC | 125663845 | 008/000 | T2 DI PHILO JCT-ELK 8/000 (C) RPR GYWW | WILLITS | ETL.7780.POLE.STPS | 2023-03-15 | 2023-03-03 | 2024-05-09 | Late | 2024-03-02 | -68 | 2024-03-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45704502 | T2 DI PHILO JCT-ELK 8/000 (C) RPR GYWW | ICW
LC | 125663698 | 057/000 | T2 DI ELK-GUALALA-057/00 RPL STRW | WILLITS | ETL.8410.POLE.WOOD | 2023-03-15 | 2023-03-13 | 2024-01-17 | On-time | 2024-03-12 | 55 | 2024-03-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487383 | T2 DI ELK-GUALALA 057/006 RPL STRW | 70Y
LC | 125663775 | 047/001 | T2 DI ELK-GUALALA 47/01 RPL INSW | WILLITS | ETL.8410.INSL.NCER | 2023-03-15 | 2023-03-13 | 2024-01-08 | On-time | 2024-03-12 | 64 | 2024-03-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35487276 | T2 DI ELK-GUALALA 47/01 RPL INSW | 93I
LC | 125663864 | 056/006 | T2 DI ELK-GUALALA 56/06 GO95 | WILLITS | ETL.8410.POLE.WOOD | 2023-03-15 | 2023-03-13 | 2024-01-22 | On-time | 2024-03-12 | 50 | 2024-03-13 | 401T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35509317 | T2 DI ELK-GUALALA 56/06 GO95 | 93G
LC | 125721518 | 013/005 | T2 DI FORT BRAGG-ELK 13/005 RPL HRDD | WILLITS | ETL.2060.POLE.NWOD | 2023-03-23 | 2023-03-13 | 2024-02-28 | On-time | 2024-03-12 | 13 | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45977981 | T2 DI FORT BRAGG-ELK 13/005 RPL HRDD | ICW
LC | 125667437 | 013/270-GUY | T2 EI COLGATE-PALERMO 013/270 RPR POLE | TABLEMTN | ETL.6500.POLE.WOOD | 2023-03-16 | 2023-03-16 |  | Late | 2024-03-15 |  | 2024-03-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Pole-Wood | Repair | 46265687 | T2 EI COLGATE-PALERMO 013/270 RPR POLE | ICW
LC | 125667552 | 013/271 | T2 EI COLGATE-PALERMO 013/271 RPR POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-16 | 2023-03-16 | 2024-03-27 | Late | 2024-03-15 | -12 | 2024-03-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45979751 | T2 EI COLGATE-PALERMO 013/271 RPR POLE | ICW
LC | 125668231 | 014/274 | T2 EI COLGATE-PALERMO 014/274 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-16 | 2023-03-16 | 2024-04-23 | Late | 2024-03-15 | -39 | 2024-03-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490110 | T2 EI COLGATE-PALERMO 014/274 RPL POLE | 70Y
LC | 125668366 | 003/064 | T2 DI VALLEY SPRINGS#1 003/064 RPL POLE | VICTOR | ETL.8210.POLE.WOOD | 2023-03-16 | 2023-03-15 | 2024-03-20 | Late | 2024-03-14 | -6 | 2024-03-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35511452 | T2 DI VALLEY SPRINGS#1 003/064 RPL POLE | 70Y
LC | 125725839 | 013/008 | T2 DI FORT BRAGG-ELK 13/8 RPR STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-24 | 2023-03-13 | 2024-02-23 | On-time | 2024-03-12 | 18 | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45977815 | T2 DI FORT BRAGG-ELK 13/8 RPR STRW | ICW
LC | 125726530 | 014/011 | T2 DI FORT BRAGG-ELK 14/11 RPL INSW | WILLITS | ETL.2060.INSL.NCER | 2023-03-24 | 2023-03-13 | 2024-03-07 | On-time | 2024-03-12 | 5 | 2024-03-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35487809 | T2 DI FORT BRAGG-ELK 14/11 RPL INSW | 93I
LC | 125727647 | 004/013 | T2 DI SONOMA-PUEBLO 4/13 RPR GYWW | LAKEVLLE | ETL.3810.POLE.NWOD | 2023-03-24 | 2023-03-13 | 2024-01-30 | On-time | 2024-03-12 | 42 | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45977496 | T2 DI SONOMA-PUEBLO 4/13 RPR GYWW | ICW
LC | 125728234 | 014/007 | T2 DI FORT BRAGG-ELK 14/07 RPL INSW | WILLITS | ETL.2060.INSL.NCER | 2023-03-24 | 2023-03-13 | 2024-02-26 | On-time | 2024-03-12 | 15 | 2024-03-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35487923 | T2 DI FORT BRAGG-ELK 14/07 RPL INSW | 93I
LC | 125650572 | 013/111 | T2 WV CRAG VIEW-CASCADE 13/111 RPR SPLW | TABLEMTN | ETL.1350.INSL | 2023-03-14 | 2023-03-14 | 2023-09-19 | On-time | 2024-03-13 | 176 | 2024-03-14 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46008213 | T2 WV CRAG VIEW-CASCADE 13/111 RPR SPLW | ICW
LC | 125670294 | 003/018 | T2 DI METCALF-EL PATIO #1 03/018 RMV VEG | METCALF | ETL.2500.TOWR | 2023-03-16 | 2023-03-16 |  | Late | 2024-03-15 |  | 2024-03-16 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 125670295 | 003/018 | T2 DI METCALF-EL PATIO#1 03/18 BNT STEEL | METCALF | ETL.2500.TOWR | 2023-03-16 | 2023-03-16 | 2024-05-07 | Late | 2024-03-15 | -53 | 2024-03-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008506 | T2 DI METCALF-EL PATIO#1 03/18 BNT STEEL | ICQ
LC | 125651589 | 000/010 | T2 ROLLINS TAP 000/010 RPR POLE | SACTO | ETL.6762.POLE.WOOD | 2023-03-14 | 2023-03-14 | 2023-09-04 | On-time | 2024-03-13 | 191 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45946895 | T2 ROLLINS TAP 000/010 RPR POLE | ICW
LC | 125654730 | 010/175 | T2 DI TEJON-LEBEC 010/175 RPR INSW | MIDWAY | ETL.9250.INSL.NCER | 2023-03-14 | 2023-03-14 | 2023-10-15 | On-time | 2024-03-13 | 150 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45996698 | T2 DI TEJON-LEBEC 010/175 RPR INSW | ICW
LC | 125654794 | 010/175 | T2 DI TEJON-LEBEC 010/175 RPR STRW | MIDWAY | ETL.9250.POLE.WOOD | 2023-03-14 | 2023-03-14 | 2023-10-14 | On-time | 2024-03-13 | 151 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45996699 | T2 DI TEJON-LEBEC 010/175 RPR STRW | ICW
LC | 125673157 | 009/011 | T2 DI FORT BRAGG-ELK 009/011 RPL POLE | WILLITS | ETL.2060.POLE.WOOD | 2023-03-17 | 2023-03-15 | 2024-04-09 | Late | 2024-03-14 | -26 | 2024-03-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487732 | T2 DI FORT BRAGG-ELK 009/011 RPL POLE | 70Y
LC | 125673243 | 001/002 | T2 DI LAURELES-OTTER 001/002 RMV VEG | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-03-17 | 2023-02-16 | 2024-02-23 | Late | 2024-02-16 | -7 | 2024-02-16 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125673253 | 025/009 | T2 DI MI WUK CURTIS 25/9R RPL STRW | VICTOR | ETL.1073.POLE.WDPS | 2023-03-17 | 2023-03-01 |  | Late | 2024-02-29 |  | 2023-09-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495524 | T2 DI MI WUK CURTIS 25/9C RPL STRW | 70Y
LC | 125655176 | 004/022 | T2 DI MTCLF-EL PTO #1 4/22 RPR STRT | METCALF | ETL.2500.TOWR | 2023-03-14 | 2023-03-14 | 2023-07-17 | On-time | 2024-03-13 | 240 | 2023-06-14 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45716448 | T2 DI MTCLF-EL PTO #1 4/22 RPR STRT | ICQ
LC | 125673734 | 002/025 | T2 DI SBRNT-GZLY-CLRMNT #1 2/25 RPL INSS | CONCORD | ETL.3740.INSL.CERA | 2023-03-17 | 2023-03-07 |  | Late | 2024-03-06 |  | 2024-03-07 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671784 | DI SBRNT-GZLY-CLRMNT #1 2/25 RPL INSS | 93K
LC | 125673996 | 008/011 | T2 DI FORT BRAGG-ELK 8/11 RPL INSW | WILLITS | ETL.2060.INSL.CERA | 2023-03-17 | 2023-03-15 |  | Late | 2024-03-14 |  | 2024-03-15 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35491106 | T2 DI FORT BRAGG-ELK 8/11 RPL INSW | 93I
LC | 125655752 | 009/126 | T2 DI VALLEY SPRINGS-CLAY 9/126 RPR GYWW | VICTOR | ETL.8264.POLE.WOOD | 2023-03-14 | 2023-03-14 | 2024-02-04 | On-time | 2024-03-13 | 38 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45977986 | T2 DI VALLEY SPRINGS-CLAY 9/126 RPR GYWW | ICW
LC | 125655755 | 012/009 | T2 DI VLLY SPRNGS-MRTL #1 12/9 RPR STRW | VICTOR | ETL.8240.POLE.WOOD | 2023-03-14 | 2023-03-14 | 2024-01-09 | On-time | 2024-03-13 | 64 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45977989 | T2 DI VLLY SPRNGS-MRTL #1 12/9 RPR STRW | ICW
LC | 125658851 | 011/007 | T2 DI VLY SPRNGS-MRTEL#1 11/7 RPR INSW | VICTOR | ETL.8240.INSL.NCER | 2023-03-15 | 2023-03-14 | 2023-09-20 | On-time | 2024-03-13 | 175 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45977990 | T2 DI VLY SPRNGS-MRTEL#1 11/7 RPR INSW | ICW
LC | 125658853 | 011/007 | T2 DI VLY SPRNGS-MRTEL#1 11/7 RPR STRW | VICTOR | ETL.8240.POLE.WOOD | 2023-03-15 | 2023-03-14 | 2023-09-20 | On-time | 2024-03-13 | 175 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45977992 | T2 DI VLY SPRNGS-MRTEL#1 11/7 RPR STRW | ICW
LC | 125676623 | 000/001B | T2 EI PIT #1-MC ARTHUR 000/001B COTTER | TABLEMTN | ETL.7790.INSL.NCER | 2023-03-17 | 2023-03-17 | 2024-05-14 | Late | 2024-03-16 | -59 | 2024-03-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45979794 | T2 EI PIT #1-MC ARTHUR 000/001B COTTER | ICW
LC | 125676625 | 000/001B | T2 EI PIT #1-MC ARTHUR 000/001B RMV STEP | TABLEMTN | ETL.7790.POLE.NWOD | 2023-03-17 | 2023-03-17 | 2024-05-14 | Late | 2024-03-16 | -59 | 2024-03-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45979795 | T2 EI PIT #1-MC ARTHUR 000/001B RMV STEP | ICW
LC | 125658854 | 011/007 | T2 DI VLY SPRNGS-MRTEL#1 11/7 RPL HRDD | VICTOR | ETL.8240.POLE.WOOD | 2023-03-15 | 2023-03-14 | 2023-09-20 | On-time | 2024-03-13 | 175 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45977993 | T2 DI VLY SPRNGS-MRTEL#1 11/7 RPL HRDD | ICW
LC | 125662902 | 29 | T2 DI VLY SPGS-CLAY 9/129 RPR SWTC | VICTOR | ETL.8264.SWIT | 2023-03-15 | 2023-03-14 | 2023-05-13 | On-time | 2024-03-13 | 305 | 2023-06-14 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 45705114 | T2 DI VLY SPGS-CLAY 9/129 RPR SWTC | ICE
LC | 125663407 | 042/008 | T2 DI ELK-GUALALA 042/008 RPL HRDD | WILLITS | ETL.8410.POLE.WOOD | 2023-03-15 | 2023-03-14 | 2023-08-29 | On-time | 2024-03-13 | 197 | 2023-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45890201 | T2 DI ELK-GUALALA 042/008 RPL HRDD | ICW
LC | 125663738 | 042/005 | T2 DI ELK-GUALALA 42/05C ANTI SPLIT | WILLITS | ETL.8410.POLE.WDPS | 2023-03-15 | 2023-03-14 | 2024-01-10 | On-time | 2024-03-13 | 63 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45977988 | T2 DI ELK-GUALALA 42/05C ANTI SPLIT | ICW
LC | 125663787 | 042/007 | T2 DI ELK-GUALALA 042/007 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-03-15 | 2023-03-14 | 2024-01-12 | On-time | 2024-03-13 | 61 | 2024-03-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487274 | T2 DI ELK-GUALALA 042/007 RPL POLE | 70Y
LC | 125723860 | 008/113 | T2 DI VLLY SPRNGS-CLAY 8/113 RPL ANCW | VICTOR | ETL.8264.POLE.WOOD | 2023-03-24 | 2023-03-14 | 2024-02-03 | On-time | 2024-03-13 | 39 | 2024-03-14 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35493062 | T2 DI VLLY SPRNGS-CLAY 8/113 RPL ANCW | 93E
LC | 125723992 | 005/111 | T2 DI VALLEY SPRINGS#2 5/111 RPR STRW | VICTOR | ETL.9460.POLE.WOOD | 2023-03-24 | 2023-03-14 | 2023-09-26 | On-time | 2024-03-13 | 169 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45978040 | T2 DI VALLEY SPRINGS#2 5/111 RPR STRW | ICW
LC | 125678322 | 014/277 | T2 EI COLGATE-PALERMO 014/277 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-17 | 2023-03-17 | 2024-04-27 | Late | 2024-03-16 | -42 | 2024-03-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490110 | T2 EI COLGATE-PALERMO 014/274 RPL POLE | 70Y
LC | 125678512 | 000/002 | T2 EI PIT #1-MCARTHUR 000/002 RPR GYWW | TABLEMTN | ETL.7790.POLE.WOOD | 2023-03-17 | 2023-03-17 | 2024-05-17 | Late | 2024-03-16 | -62 | 2024-03-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45989273 | T2 EI PIT #1-MCARTHUR 000/002 RPR GYWW | ICW
LC | 125724063 | 009/125 | T2 DI VLY SPGS-CLY 9/125 RPR GYWW | VICTOR | ETL.8264.POLE.WOOD | 2023-03-24 | 2023-03-14 | 2024-02-04 | On-time | 2024-03-13 | 38 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45978041 | T2 DI VLY SPGS-CLY 9/125 RPR GYWW | ICW
LC | 125726662 | 011/198 | T2 DI TEJON-LEBEC 11/198 RPR GYWW | MIDWAY | ETL.9250.POLE.NWOD | 2023-03-24 | 2023-03-14 | 2023-11-06 | On-time | 2024-03-13 | 128 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45996740 | T2 DI TEJON-LEBEC 11/198 RPR GYWW | ICW
LC | 125679372 | 000/004 | T2 EI PIT #1-MCARTHUR 000/004 RPR INSW | TABLEMTN | ETL.7790.INSL.NCER | 2023-03-17 | 2023-03-17 |  | Late | 2024-03-16 |  | 2024-03-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45979796 | T2 EI PIT #1-MCARTHUR 000/004 RPR INSW | ICW
LC | 125727009 | 011/107 | T2 DI BRDGVL-CTNWD 11/107L RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2023-03-24 | 2023-03-14 | 2023-10-25 | On-time | 2024-03-13 | 140 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45979823 | T2 DI BRDGVL-CTNWD 11/107L RPR ADSS | ICW
LC | 125729053 | 008/079 | T2 DI BRDGVLE-CTNWD 008/079L RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2023-03-24 | 2023-03-14 | 2023-10-25 | On-time | 2024-03-13 | 140 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45979821 | T2 DI BRDGVLE-CTNWD 008/079L RPR ADSS | ICW
LC | 125729233 | 008/081 | T2 DI BRIDGEVILLE-CTTNWD 8/81L RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2023-03-24 | 2023-03-14 | 2023-12-04 | On-time | 2024-03-13 | 100 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45979822 | T2 DI BRIDGEVILLE-CTTNWD 8/81L RPR ADSS | ICW
LC | 125732061 | 007/086 | T2 DI VEDDER TAP 7/86C RPL GYWW | MIDWAY | ETL.2141.POLE.WDPS | 2023-03-25 | 2023-03-14 | 2023-08-17 | On-time | 2024-03-13 | 209 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45927413 | T2 DI VEDDER TAP 7/86C RPL GYWW | ICW
LC | 125742229 | 011/090 | T2 DI TGR CK VLY SPGS 11/090 RPL HRDT | VICTOR | ETL.5790.TOWR | 2023-03-28 | 2023-03-14 | 2024-02-21 | On-time | 2024-03-13 | 21 | 2024-03-14 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45984657 | T2 DI TGR CK VLY SPGS 11/090 RPL HRDT | ICQ
LC | 125682734 | 023/002 | T2 DI MI WUK CURTIS 23/2L RPL STRW | VICTOR | ETL.1073.POLE.WDPS | 2023-03-18 | 2023-03-08 |  | Late | 2024-03-07 |  | 2024-03-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495522 | T2 DI MI WUK CURTIS 023/002L RPL POLE | 70Y
LC | 125682739 | 023/002 | T2 DI MI WUK CURTIS 23/2R RPL STRW | VICTOR | ETL.1073.POLE.WDPS | 2023-03-18 | 2023-03-08 |  | Late | 2024-03-07 |  | 2024-03-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495522 | T2 DI MI WUK CURTIS 023/002L RPL POLE | 70Y
LC | 125682783 | 025/005 | T2 DI MI WUK CURTIS 025/005R RPR STRW | VICTOR | ETL.1073.POLE.STPS | 2023-03-18 | 2023-03-07 |  | Late | 2024-03-06 |  | 2024-03-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45954320 | T2 DI MI WUK CURTIS 025/005R RPR STRW | ICW
LC | 125682996 | 022/009 | T2 DI FORT BRAGG-ELK 022/009 RPL POLE | WILLITS | ETL.2060.POLE.WOOD | 2023-03-18 | 2023-03-08 | 2024-03-12 | Late | 2024-03-07 | -5 | 2024-03-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486801 | T2 DI FORT BRAGG-ELK 022/009 RPL POLE | 70Y
LC | 125777030 | 010/015 | T2 DI VLY SPGS-MRT#1 10/15 RPL HRDD | VICTOR | ETL.8240.POLE.WOOD | 2023-04-01 | 2023-03-14 | 2023-09-20 | On-time | 2024-03-13 | 175 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45978052 | T2 DI VLY SPGS-MRT#1 10/15 RPL HRDD | ICW
LC | 125683580 | 004/091 | T2 DI CNVIL-TBL MTN-ORVL 4/091 RPL STRW | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-18 | 2023-03-08 | 2024-05-21 | Late | 2024-03-07 | -75 | 2024-03-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486528 | T2 DI CNTRVL-TBL MTN-ORVL 3/81 RPL POLE | 70Y
LC | 127080535 | 024/097 | T3 EXCHEQUER-INDN FLT 24/97 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-09-18 | 2023-09-18 | 2023-12-12 | On-time | 2024-03-18 | 97 | 2023-12-18 | 628 | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45995871 | T3 EXCHEQUER-INDN FLT 24/97 RPR JMPS | ICS
LC | 127080635 | 025/105 | T3 EXCHEQUER-INDN FLT 25/105 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-09-18 | 2023-09-18 | 2023-12-12 | On-time | 2024-03-18 | 97 | 2023-12-18 | 628 | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45995872 | T3 EXCHEQUER-INDN FLT 25/105 RPR JMPS | ICS
LC | 127080730 | 026/119 | T3 EXCHEQUER-INDN FLT 26/119 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-09-18 | 2023-09-18 | 2023-12-13 | On-time | 2024-03-18 | 96 | 2023-12-18 | 628 | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR3 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45995873 | T3 EXCHEQUER-INDN FLT 26/119 RPR JMPS | ICS
LC | 125685954 | :011/005 | T2 BLTA-RVRBNK-MLNS SW ST_:11/5 GO95 CLR | VICTOR | ETL.1070.POLE.WOOD | 2023-03-20 | 2023-03-20 | 2024-05-28 | Late | 2024-03-19 | -70 | 2024-03-20 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640617 | T2 BLTA-RVRBNK-MLNS SW ST_:11/5 GO95 CLR | 93G
LC | 125657782 | 009/010 | T2 FORT BRAGG-ELK - 9/010 GO95 | WILLITS | ETL.2060.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2024-02-26 | On-time | 2024-03-14 | 17 | 2024-03-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31642140 | T2 FORT BRAGG-ELK - 9/010 GO95 | 93G
LC | 125657823 | 010/007 | T2 FORT BRAGG-ELK 10/07 GO95 | WILLITS | ETL.2060.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2023-08-07 | On-time | 2024-03-14 | 220 | 2023-06-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640254 | T2 FORT BRAGG-ELK 10/07 GO95 | 93G
LC | 125686160 | :011/007 | T2 BLTA-RVRBNK-MLNS SW ST_:11/7 GO95 CLR | VICTOR | ETL.1070.POLE.WOOD | 2023-03-20 | 2023-03-20 | 2024-05-28 | Late | 2024-03-19 | -70 | 2024-03-20 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640617 | T2 BLTA-RVRBNK-MLNS SW ST_:11/5 GO95 CLR | 93G
LC | 125686376 | 001/000 | T2 VLY SPRNGS-CLVS CMNT_001/0 GO95 CLEAR | VICTOR | ETL.8220.POLE.WOOD | 2023-03-20 | 2023-03-20 | 2024-04-23 | Late | 2024-03-19 | -35 | 2024-03-20 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31641879 | T2 VLY SPRNGS-CLVS CMNT_001/0 GO95 CLEAR | 93G
LC | 125687624 | X008/037 | T2 EI DIABLO-MESA X008/037 RPL INSW | PISMOBCH | ETL.4620.INSL | 2023-03-20 | 2023-03-20 | 2024-05-16 | Late | 2024-03-19 | -58 | 2024-03-20 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671707 | T0 DIABLO-MESA RPL INSS 7 LSTS | 93K
LC | 125657829 | 010/008 | T2 FORT BRAGG-ELK 10/08 GO95 | WILLITS | ETL.2060.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2023-08-08 | On-time | 2024-03-14 | 219 | 2023-06-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640254 | T2 FORT BRAGG-ELK 10/07 GO95 | 93G
LC | 125689939 | :000/001 | T2 BLTA-RVERBNK-MLNS SW ST_:0/1 RPL INSW | VICTOR | ETL.1070.INSL.NCER | 2023-03-20 | 2023-03-20 |  | Late | 2024-03-19 |  | 2024-03-20 | 508T | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35495378 | T2 BLTA-RVERBNK-MLNS SW ST_:0/1 RPL INSW | 93I
LC | 125657906 | 020/002 | T2 FORT BRAGG-ELK 20/02 GO 95 CLEARNC | WILLITS | ETL.2060.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2023-08-10 | On-time | 2024-03-14 | 217 | 2023-09-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640254 | T2 FORT BRAGG-ELK 10/07 GO95 | 93G
LC | 125658011 | 020/011 | T2 FORT BRAGG-ELK 20/11 GO 95 | WILLITS | ETL.2060.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2023-08-10 | On-time | 2024-03-14 | 217 | 2023-09-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640254 | T2 FORT BRAGG-ELK 10/07 GO95 | 93G
LC | 125658914 | 005/121 | T2 DEL MONTE-VIEJO 5/121 GO95 | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2024-02-16 | On-time | 2024-03-14 | 27 | 2024-03-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31646104 | T2 DEL MONTE-VIEJO 5/121 GO95 | 93G
LC | 125658977 | 005/122 | T2 DEL MONTE-VIEJO 5/122 GO95 | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2023-08-26 | On-time | 2024-03-14 | 201 | 2024-03-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31646105 | T2 DEL MONTE-VIEJO 5/122 GO95 | 93G
LC | 125659019 | 004/118 | T2 EI DEL MONTE-VIEJO 004/118 RPR SPLW | MOSSLNDG | ETL.6710.INSL.CERA | 2023-03-15 | 2023-03-15 | 2023-12-02 | On-time | 2024-03-14 | 103 | 2024-03-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46016589 | T2 EI DEL MONTE-VIEJO 004/118 RPR SPLW | ICW
LC | 125659024 | 006/145 | T2 DEL MONTE-VIEJO 6/145 GO95 | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2023-08-26 | On-time | 2024-03-14 | 201 | 2023-09-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31646106 | T2 DEL MONTE-VIEJO 6/145 GO95 | 93G
LC | 125659132 | 006/151 | T2 DEL MONTE-VIEJO 006/151 GO95 CLEAR | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2023-08-28 | On-time | 2024-03-14 | 199 | 2024-03-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31653598 | T2 DEL MONTE-VIEJO 006/151 GO95 CLEAR | 93G
LC | 125659482 | 013/200 | T2 GOLD HILL #1 13/200 GO95 | SACTO | ETL.6950.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2023-04-30 | On-time | 2024-03-14 | 319 | 2023-06-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640198 | T2 GOLD HILL #1 13/200 GO95 | 93G
LC | 125659817 | 004/056 | T2 JOLON TAP 4/56 GO95 | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2024-01-23 | On-time | 2024-03-14 | 51 | 2024-03-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640151 | T2 JOLON TAP 4/56 GO95 | 93G
LC | 125659875 | 009/123 | T2 JOLON TAP 9/123 GO95 | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2023-08-08 | On-time | 2024-03-14 | 219 | 2023-09-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31642141 | T2 JOLON TAP 9/123 GO95 | 93G
LC | 125660303 | 004/050 | T2 EI SNEATH LANE-PACIFICA 4/50 RPL DMPW | METCALF | ETL.7575.INSL.NCER | 2023-03-15 | 2023-03-15 | 2023-10-25 | On-time | 2024-03-14 | 141 | 2024-03-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 45999080 | T2 EI SNEATH LANE-PACIFICA 4/50 RPL DMPW | ICW
LC | 125661973 | 017/266 | T2 GOLD HILL #1 17/266 GO95 | SACTO | ETL.6950.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2023-04-21 | On-time | 2024-03-14 | 328 | 2023-09-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640198 | T2 GOLD HILL #1 13/200 GO95 | 93G
LC | 125662187 | 011/074 | T2 CAYUCOS-CAMBRIA 11/074L CLEARANCE | PISMOBCH | ETL.8560.POLE.WDPS | 2023-03-15 | 2023-03-15 | 2024-01-16 | On-time | 2024-03-14 | 58 | 2024-03-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640157 | T2 CAYUCOS-CAMBRIA 11/074 CLEARANCE | 93G
LC | 125700701 | 014/287 | T2 EI COLGATE-PALERMO 14/287 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-21 | 2023-03-21 | 2024-04-27 | Late | 2024-03-20 | -38 | 2024-03-21 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35517991 | T2 EI COLGATE-PALERMO 14/287 RPL STRW | 70Y
LC | 125701973 | 014/292 | T2 EI COLGATE-PALERMO 14/292 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-21 | 2023-03-21 | 2024-04-24 | Late | 2024-03-20 | -35 | 2024-03-21 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490110 | T2 EI COLGATE-PALERMO 014/274 RPL POLE | 70Y
LC | 125702343 | 014/337 | T2 COTTONWOOD-BENTON #1 14/337 RPR INSW | TABLEMTN | ETL.6640.INSL | 2023-03-21 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45989492 | T2 COTTONWOOD-BENTON #1 14/337 RPR INSW | ICW
LC | 125663181 | 003/029B | T2NT DVDE-VNDENBERG #1 _3/29B RPR ROAD | PISMOBCH | ETL.8620.POLE.WOOD | 2023-03-15 | 2023-03-15 | 2023-03-30 | On-time | 2024-03-14 | 350 | 2023-09-15 | 932 | TLR | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Repair | 45713305 | T2NT DVDE-VNDENBERG #1 _3/29B RPR ROAD | CHS
LC | 125705657 | 007/151 | T2 DI CNTRVL-TBL MTN-ORVL 7/151 RPL HRDW | TABLEMTN | ETL.6330.POLE.NWOD | 2023-03-21 | 2023-03-08 | 2024-05-22 | Late | 2024-03-07 | -76 | 2024-03-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45979786 | T2 DI CNTRVL-TBL MTN-ORVL 7/151 RPL HRDW | ICW
LC | 125705694 | 012/007 | T2 DI LAYTONVILLE-WILLITS 12/7 RPL STRW | WILLITS | ETL.8360.POLE.WOOD | 2023-03-21 | 2023-03-20 |  | Late | 2024-03-19 |  | 2024-03-20 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35489670 | T2 DI LAYTONVILLE-WILLITS 12/7 RPL STRW | 70Y
LC | 125663232 | 040/000 | T2 DI ELK-GUALALA 040/000 (L) RPL HRDD | WILLITS | ETL.8410.INSL.NCER | 2023-03-15 | 2023-03-15 | 2024-01-12 | On-time | 2024-03-14 | 62 | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45977997 | T2 DI ELK-GUALALA 040/000 (L) RPL HRDD | ICW
LC | 125663629 | 040/001 | T2 DI ELK-GUALALA-040/01 RPL STRW | WILLITS | ETL.8410.POLE.WDPS | 2023-03-15 | 2023-03-15 | 2023-08-30 | On-time | 2024-03-14 | 197 | 2023-06-15 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31640149 | T2 DI ELK-GUALALA-040/01 RPL STRW | 70Y
LC | 125663652 | 040/001 | T2 DI ELK-GUALALA-040/01C RPL STRW | WILLITS | ETL.8410.POLE.WDPS | 2023-03-15 | 2023-03-15 | 2023-08-30 | On-time | 2024-03-14 | 197 | 2023-06-15 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31640149 | T2 DI ELK-GUALALA-040/01 RPL STRW | 70Y
LC | 125705969 | 012/000 | T2 DI LYTNVLL-WLLTS 12/0 GO95 USAGE | WILLITS | ETL.8360.POLE.WOOD | 2023-03-21 | 2023-03-20 |  | Late | 2024-03-19 |  | 2024-03-20 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35489669 | T2 DI LAYTONVILLE-WILLITS 12/00 GO95 | 93G
LC | 125706004 | 006/136 | T2 DI CNTRVL-TBL MTN-ORVL 6/136 RPL STRW | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-21 | 2023-03-09 | 2024-05-22 | Late | 2024-03-08 | -75 | 2024-03-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35535636 | T2 DI CNTRVL-TBL MTN-ORVL 6/136 RPL STRW | 70Y
LC | 125706033 | 006/133 | T2 DI CTRVL-TBLMTN-OROVL 06/133 RPL POLE | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-21 | 2023-03-08 | 2024-05-20 | Late | 2024-03-07 | -74 | 2024-03-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486529 | T2 DI CNTRVL-TB MT-ORO 6/126 RPL STRW | 70Y
LC | 125706157 | 006/126 | T2 DI CNTRVL-TB MT-ORO 6/126 RPL STRW | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-21 | 2023-03-08 | 2024-05-22 | Late | 2024-03-07 | -76 | 2024-03-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486529 | T2 DI CNTRVL-TB MT-ORO 6/126 RPL STRW | 70Y
LC | 125663655 | 040/001 | T2 DI ELK-GUALALA-040/01 RPL STRW | WILLITS | ETL.8410.POLE.WDPS | 2023-03-15 | 2023-03-15 | 2023-08-30 | On-time | 2024-03-14 | 197 | 2023-06-15 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31640149 | T2 DI ELK-GUALALA-040/01 RPL STRW | 70Y
LC | 125663809 | 039/008 | T2 DI ELK-GUALALA 039/008L ANTI SPLIT | WILLITS | ETL.8410.POLE.WDPS | 2023-03-15 | 2023-03-15 | 2024-01-12 | On-time | 2024-03-14 | 62 | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45977995 | T2 DI ELK-GUALALA 039/008L ANTI SPLIT | ICW
LC | 125706394 | 004/099 | T2 DI CTRVL-TBL MTN-OVL 004/099 RPL STRW | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-21 | 2023-03-08 | 2024-05-21 | Late | 2024-03-07 | -75 | 2024-03-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486528 | T2 DI CNTRVL-TBL MTN-ORVL 3/81 RPL POLE | 70Y
LC | 125706398 | A009/189 | T2 DI CENTVLL-TBLMTN-ORO A9/189 RPL STRW | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-21 | 2023-03-08 |  | Late | 2024-03-07 |  | 2024-03-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486527 | T2 DI CENTVLL-TBLMTN-ORO A9/189 RPL POLE | 70Y
LC | 125667217 | 011/009 | T2 DI FRT BRG ELK 11/009 RPR INSW | WILLITS | ETL.2060.INSL.CERA | 2023-03-16 | 2023-03-15 | 2023-08-09 | On-time | 2024-03-14 | 218 | 2023-09-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45704529 | T2 DI FRT BRG ELK 11/009 RPR INSW | ICW
LC | 125706536 | 005/109 | T2 DI CNTRVL-TB MT-ORO 5/109 RPR INSW | TABLEMTN | ETL.6330.INSL.NCER | 2023-03-21 | 2023-03-08 | 2024-05-21 | Late | 2024-03-07 | -75 | 2024-03-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45979782 | T2 DI CNTRVL-TB MT-ORO 5/109 RPR INSW | ICW
LC | 125667831 | 042/009 | T2 DI ELK-GUALALA 42/9 COTTER | WILLITS | ETL.8410.INSL.CERA | 2023-03-16 | 2023-03-15 | 2023-08-29 | On-time | 2024-03-14 | 198 | 2023-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45704505 | T2 DI ELK-GUALALA 042/009 COTTER | ICW
LC | 125706621 | 010/145 | T2 DI DLTA-MT GT JCT 10/145 RPL POLE | TABLEMTN | ETL.6750.POLE.WDPS | 2023-03-21 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491299 | T2 DI DLTA-MTN GATE 10/142 RPL POLE | 70Y
LC | 125706656 | 003/071 | T2 DI CNTRVL-TBL MTN-ORVL 03/71 RPL INSW | TABLEMTN | ETL.6330.INSL.NCER | 2023-03-21 | 2023-03-09 | 2024-05-24 | Late | 2024-03-08 | -77 | 2024-03-09 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35483130 | T2 DI CNTRVL-TBL MTN-ORVL 03/71 RPL INSW | 93I
LC | 125706659 | 008/173 | T2 DI CNTVLL-TBLMTN-ORVLL 8/173 RPL POLE | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-21 | 2023-03-09 | 2024-05-23 | Late | 2024-03-08 | -76 | 2023-09-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486529 | T2 DI CNTRVL-TB MT-ORO 6/126 RPL STRW | 70Y
LC | 125706752 | 005/116 | T2 DI CTRVL-TBL MTN-ORVL 5/116 RPL STRW | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-21 | 2023-03-09 | 2024-05-21 | Late | 2024-03-08 | -74 | 2024-03-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35532910 | T2 DI CTRVL-TBL MTN-ORVL 5/116 RPL STRW | 70Y
LC | 125669849 | 005/077 | T2 DI VLY SPRNGS-CLAY 05/77L RPR GYWW | VICTOR | ETL.8264.POLE.STPS | 2023-03-16 | 2023-03-15 | 2024-02-01 | On-time | 2024-03-14 | 42 | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45977998 | T2 DI VLY SPRNGS-CLAY 05/44L RPR GYWW | ICW
LC | 125669882 | 005/077 | T2 DI VLY SPRNGS-CLAY 05/77R RPR GYWW | VICTOR | ETL.8264.POLE.STPS | 2023-03-16 | 2023-03-15 | 2024-02-01 | On-time | 2024-03-14 | 42 | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45977999 | T2 DI VLY SPRNGS-CLAY 05/44R RPR GYWW | ICW
LC | 125708451 | 015/294 | T2 EI COLGATE-PALERMO 015/294 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-22 | 2023-03-22 | 2024-04-24 | Late | 2024-03-21 | -34 | 2024-03-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490111 | T2 EI COLGATE-PALERMO 015/294 RPL POLE | 70Y
LC | 125669929 | 009/075 | T2 DI CBRILO-SNTA YNZ SS 09/75 RPR GYWW | PISMOBCH | ETL.1200.POLE.NWOD | 2023-03-16 | 2023-03-15 | 2024-01-30 | On-time | 2024-03-14 | 44 | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46078518 | T2 DI CBRILO-SNTA YNZ SS 09/75 RPR GYWW | ICW
LC | 125708607 | 015/295 | T2 EI COLGATE-PALERMO 15/295 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2023-03-22 | 2023-03-22 | 2024-04-24 | Late | 2024-03-21 | -34 | 2024-03-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490111 | T2 EI COLGATE-PALERMO 015/294 RPL POLE | 70Y
LC | 125669970 | 009/075 | T2 DI CBRILO-SNTA YNZ SS 09/75 COTTER | PISMOBCH | ETL.1200.INSL.NCER | 2023-03-16 | 2023-03-15 | 2024-01-30 | On-time | 2024-03-14 | 44 | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46078519 | T2 DI CBRILO-SNTA YNZ SS 09/75 COTTER | ICW
LC | 125709192 | 015/298 | T2 EI COLGATE-PALERMO 015/298 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-22 | 2023-03-22 | 2024-04-27 | Late | 2024-03-21 | -37 | 2024-03-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490112 | T2 EI COLGATE-PALERMO 015/298 RPL POLE | 70Y
LC | 125672884 | 005/100 | T2 DI VLLY SPRNGS #2 05/100 COTTER | VICTOR | ETL.9460.INSL.NCER | 2023-03-17 | 2023-03-15 | 2023-12-01 | On-time | 2024-03-14 | 104 | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46049343 | T2 DI VLLY SPRNGS #2 05/100 COTTER | ICW
LC | 125673400 | 007/133 | T2 DI VALLEY SPRNGS #2 007/133 COTTER | VICTOR | ETL.9460.INSL.NCER | 2023-03-17 | 2023-03-15 | 2023-08-25 | On-time | 2024-03-14 | 202 | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45907574 | T2 DI VALLEY SPRNGS #2 007/133 COTTER | ICW
LC | 125724217 | 014/121 | T2 DI TGR CRK-VLY SPNG 14/121 RPL INSS | VICTOR | ETL.5790.INSL.CERA | 2023-03-24 | 2023-03-15 | 2024-01-22 | On-time | 2024-03-14 | 52 | 2024-03-15 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671712 | T2 DI TGR CRK-VLY SPRNGS RPL INSS 2 LSTS | 93K
LC | 125710243 | 006/123 | T2 DI CNTRVL-TBL MTN-RVL 6/123 RPL INSW | TABLEMTN | ETL.6330.INSL.NCER | 2023-03-22 | 2023-03-08 | 2024-05-23 | Late | 2024-03-07 | -77 | 2024-03-08 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35483133 | T2 DI CNTRVL-TBL MTN-RVL 6/123 RPL INSW | 93I
LC | 125711287 | 012/009 | T2 DI LYTNVLL-WLLTS 12/9 RPL HRDW | WILLITS | ETL.8360.POLE.WOOD | 2023-03-22 | 2023-03-20 |  | Late | 2024-03-19 |  | 2024-03-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45988992 | T2 DI LYTNVLL-WLLTS 12/9 RPL HRDW | ICW
LC | 125711605 | 004/088 | T2 DI CTRVL-TBL MT-ORVL 004/088 RPL STRW | TABLEMTN | ETL.6330.POLE.WOOD | 2023-03-22 | 2023-03-08 |  | Late | 2024-03-07 |  | 2024-03-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486528 | T2 DI CNTRVL-TBL MTN-ORVL 3/81 RPL POLE | 70Y
LC | 125711651 | 001/050 | T2 EI CSCDE-BNTN-DSCHTS 01/050 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-03-22 | 2023-03-22 | 2024-05-19 | Late | 2024-03-21 | -59 | 2024-03-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490754 | T2 EI CSCDE-BNTN-DSCHTS 01/050 RPL STRW | 70Y
LC | 125713381 | 010/142 | T2 DI DLTA-MTN GATE 10/142 RPL POLE | TABLEMTN | ETL.6750.POLE.WDPS | 2023-03-22 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491299 | T2 DI DLTA-MTN GATE 10/142 RPL POLE | 70Y
LC | 125726044 | 005/004 | T2 DI VLY SPRNGS-MARTL#1 05/04 RPR GUY | VICTOR | ETL.8240.POLE.NWOD | 2023-03-24 | 2023-03-15 | 2024-01-09 | On-time | 2024-03-14 | 65 | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45978042 | T2 DI VLY SPRNGS-MARTL#1 05/04 RPR GUY | ICW
LC | 125716834 | 012/003 | T2 DI LAYTONVILLE-WILLITS 12/3 RPR INSW | WILLITS | ETL.8360.INSL.NCER | 2023-03-23 | 2023-03-20 |  | Late | 2024-03-19 |  | 2023-09-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45988993 | T2 DI LAYTONVILLE-WILLITS 12/3 RPR INSW | ICW
LC | 125717011 | 015/302 | T2 EI COLGATE-PALERMO 015/302 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-23 | 2023-03-23 | 2024-04-27 | Late | 2024-03-22 | -36 | 2024-03-23 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490112 | T2 EI COLGATE-PALERMO 015/298 RPL POLE | 70Y
LC | 125717331 | 006/003 | T2 DI FORT BRAGG-ELK 6/3 RPL HRDW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-23 | 2023-03-22 | 2024-04-11 | Late | 2024-03-21 | -21 | 2024-03-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46089631 | T2 DI FORT BRAGG-ELK 6/3 RPL HRDW | ICW
LC | 125717679 | 015/305 | T2 EI COLGATE-PALERMO 15/305 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2023-03-23 | 2023-03-23 | 2024-04-27 | Late | 2024-03-22 | -36 | 2024-03-23 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490114 | T2 EI COLGATE-PALERMO 015/305 RPL POLE | 70Y
LC | 125729933 | 011/157 | T2 DI VLLY SPNGS-CLAY 11/157 RPR INSW | VICTOR | ETL.8264.INSL.NCER | 2023-03-24 | 2023-03-15 | 2024-02-07 | On-time | 2024-03-14 | 36 | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45978046 | T2 DI VLLY SPNGS-CLAY 11/157 RPR INSW | ICW
LC | 125718671 | 015/310 | T2 EI COLGATE-PALERMO 015/310 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-23 | 2023-03-23 | 2024-04-27 | Late | 2024-03-22 | -36 | 2024-03-23 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490115 | T2 EI COLGATE-PALERMO 015/310 RPL POLE | 70Y
LC | 125719402 | 015/312 | T2 EI COLGATE-PALERMO 15/312 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2023-03-23 | 2023-03-23 | 2024-04-25 | Late | 2024-03-22 | -34 | 2024-03-23 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490116 | T2 EI COLGATE-PALERMO 015/312 RPL POLE | 70Y
LC | 125730350 | 012/167 | T2 DI DELTA-MTN GAT JCT 12/167R BACKFILL | TABLEMTN | ETL.6750.POLE.STPS | 2023-03-24 | 2023-03-15 | 2023-10-12 | On-time | 2024-03-14 | 154 | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45979793 | T2 DI DELTA-MTN GAT JCT 12/167R BACKFILL | ICW
LC | 125719656 | 016/311 | T2 EI FLTN-MLN-CTT 016/311 RPL INSW | LAKEVLLE | ETL.6910.INSL.NCER | 2023-03-23 | 2023-03-23 |  | Late | 2024-03-22 |  | 2024-03-23 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674168 | T2 EI FLTN-MLN-CTT 016/311 RPL INSW | 93K
LC | 125720292 | 039/180 | T2 EI RD MTN-TAL MTN #2 039/180 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2023-03-23 | 2023-03-23 |  | Late | 2024-03-22 |  | 2024-03-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45742329 | T2 EI RD MTN-TAL MTN #2 039/180 RPR STRT | ICQ
LC | 125720558 | 024/001 | T2 DI MI-WUK-CURTIS 24/1 RPL POLE | VICTOR | ETL.1073.POLE.WDPS | 2023-03-23 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35551320 | T2 DI MI-WUK-CURTIS 24/1 RPL POLE | 70Y
LC | 125731062 | 004/082 | T2 DI VALLEY SPRINGS #2 4/82 RPLC HRDW | VICTOR | ETL.9460.POLE.WOOD | 2023-03-25 | 2023-03-15 | 2023-10-04 | On-time | 2024-03-14 | 162 | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45976980 | T2 DI VALLEY SPRINGS #2 4/82 RPLC HRDW | ICW
LC | 125720601 | 024/001 | T2 DI MI-WUK-CURTIS 24/1 COTTER | VICTOR | ETL.1073.INSL.CERA | 2023-03-23 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45984771 | T2 DI MI-WUK-CURTIS 24/1 COTTER | ICW
LC | 125721333 | 014/003 | T2 DI FORT BRAGG-ELK 14/3 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-23 | 2023-03-13 |  | Late | 2024-03-12 |  | 2024-03-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487925 | T2 DI FORT BRAGG-ELK 14/3 RPL STRW | 70Y
LC | 125721335 | 014/003 | T2 DI FORT BRAGG-ELK 14/3 COA | WILLITS | ETL.2060.POLE.WOOD | 2023-03-23 | 2023-03-13 | 2024-03-13 | Late | 2024-03-12 | -1 | 2024-03-13 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125731068 | 004/082 | T2 DI VALLEY SPRINGS #2 4/82 COMPLETE | VICTOR | ETL.9460.POLE.WOOD | 2023-03-25 | 2023-03-15 | 2023-10-04 | On-time | 2024-03-14 | 162 | 2023-09-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45989866 | T2 DI VALLEY SPRINGS #2 4/82 RPR GYWW | ICW
LC | 125742722 | 006/117 | T2 DI VLY SPGS#2 006/117L RPR HRDW | VICTOR | ETL.9460.POLE.WDPS | 2023-03-28 | 2023-03-15 | 2023-09-26 | On-time | 2024-03-14 | 170 | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45978049 | T2 DI VLY SPGS#2 006/117L RPR HRDW | ICW
LC | 125742726 | 022/008 | T2 DI FORT BRAGG-ELK 22/8 RPL INSW | WILLITS | ETL.2060.INSL.CERA | 2023-03-28 | 2023-03-15 | 2024-03-12 | On-time | 2024-03-14 | 2 | 2024-03-15 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35487238 | T2 EI FORT BRAGG-ELK 022/010 RPL INSW | 93I
LC | 125742901 | 006/117 | T2 DI VLY SPGS#2 006/117L RPR STRW | VICTOR | ETL.9460.POLE.WDPS | 2023-03-28 | 2023-03-15 | 2023-09-26 | On-time | 2024-03-14 | 170 | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45978050 | T2 DI VLY SPGS#2 006/117L RPR STRW | ICW
LC | 125742906 | 006/117 | T2 DI VLY SPGS#2 006/117R RPL ANCW | VICTOR | ETL.9460.POLE.WDPS | 2023-03-28 | 2023-03-15 | 2024-02-15 | On-time | 2024-03-14 | 28 | 2024-03-15 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35495371 | T2 DI VLY SPGS#2 006/117R RP ANCW | 93E
LC | 125721665 | 022/108 | T2 DI FULTN-IGNCO#1 12/67 RPL INSS | LAKEVLLE | ETL.4680.INSL.CERA | 2023-03-23 | 2023-03-13 |  | Late | 2024-03-12 |  | 2024-03-13 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31678225 | T2 DI FULTON-IGNCIO #1 RPL INSS IN 5 TWR | 93K
LC | 125742907 | 006/117 | T2 DI VLY SPGS#2 006/117C RPL ANCW | VICTOR | ETL.9460.POLE.WDPS | 2023-03-28 | 2023-03-15 | 2024-02-15 | On-time | 2024-03-14 | 28 | 2024-03-15 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35495371 | T2 DI VLY SPGS#2 006/117R RP ANCW | 93E
LC | 125721737 | 024/002 | T2 DI MI-WUK-CURTIS 24/2L RPL POLE | VICTOR | ETL.1073.POLE.WDPS | 2023-03-23 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495523 | T2 DI MI-WUK-CURTIS 24/2 RPL POLE | 70Y
LC | 125721739 | 024/002 | T2 DI MI-WUK-CURTIS 024/002R RPL POLE | VICTOR | ETL.1073.POLE.WDPS | 2023-03-23 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495523 | T2 DI MI-WUK-CURTIS 24/2 RPL POLE | 70Y
LC | 125721754 | 001/010 | T2 DI DINOSAUR POINT TAP 01/10 RPR JMPW | FRESNO | ETL.8961.INSL.CERA | 2023-03-23 | 2023-03-10 |  | Late | 2024-03-09 |  | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45954705 | T2 DI DINOSAUR POINT TAP 01/10 RPR JMPW | ICW
LC | 125721798 | 012/009 | T2 DI FORT BRAGG-ELK 12/9 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-23 | 2023-03-21 | 2024-04-12 | Late | 2024-03-20 | -23 | 2024-03-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35488001 | T2 DI FORT BRAGG-ELK 12/9 RPL STRW | 70Y
LC | 125721860 | 049/005 | T2 DI FRT RSS-GUALA 49/5 RPR SPLW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-03-23 | 2023-03-10 |  | Late | 2024-03-09 |  | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45977801 | T2 DI FRT RSS-GUALA 49/5 RPR SPLW | ICW
LC | 125721911 | 015/007 | T2 DI FORT BRAGG-ELK 015/007 RMV VEG | WILLITS | ETL.2060.POLE.WOOD | 2023-03-23 | 2023-03-13 | 2024-03-18 | Late | 2024-03-12 | -6 | 2024-03-13 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125742908 | 006/117 | T2 DI VLY SPGS#2 006/117L RPL ANCW | VICTOR | ETL.9460.POLE.WDPS | 2023-03-28 | 2023-03-15 | 2024-02-15 | On-time | 2024-03-14 | 28 | 2024-03-15 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35495371 | T2 DI VLY SPGS#2 006/117R RP ANCW | 93E
LC | 125722172 | 020/009 | T2 DI FORT BRAGG-ELK 020/009 RPL INSW | WILLITS | ETL.2060.INSL.NCER | 2023-03-23 | 2023-03-10 | 2024-03-11 | Late | 2024-03-09 | -2 | 2024-03-10 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35486932 | T2 DI FORT BRAGG-ELK 020/009 RPL INSW | 93I
LC | 125742953 | 006/117 | T2 DI VLY SPGS#2 006/117C RPR GYWW | VICTOR | ETL.9460.POLE.WDPS | 2023-03-28 | 2023-03-15 | 2023-09-26 | On-time | 2024-03-14 | 170 | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45978051 | T2 DI VLY SPGS#2 006/117C RPR GYWW | ICW
LC | 125722211 | IG001/007 | T2 DI LKVL-IGNACIO #1 IG1/7 RPL INSS | LAKEVLLE | ETL.4940.INSL | 2023-03-23 | 2023-03-10 |  | Late | 2024-03-09 |  | 2024-03-10 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667972 | DI LKVL-IGNACIO #1 IG1/7 RPL INSS | 93K
LC | 125666808 | 017/349 | T2 COLGATE-PALERMO 017/349 RPR INSW | SACTO | ETL.6500.INSL.CERA | 2023-03-16 | 2023-03-16 | 2023-11-01 | On-time | 2024-03-15 | 135 | 2024-03-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45979749 | T2 COLGATE-PALERMO 017/349 RPR INSW | ICW
LC | 125667436 | 013/270 | T2 EI COLGATE-PALERMO 013/270 RPR POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-16 | 2023-03-16 | 2023-10-30 | On-time | 2024-03-15 | 137 | 2024-03-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45979750 | T2 EI COLGATE-PALERMO 013/270 RPR POLE | ICW
LC | 125670055 | 009/042 | T2 DI DIABLO-GATES #1- 09/42 RPR GYWT | PISMOBCH | ETL.5960.TOWR | 2023-03-16 | 2023-03-16 | 2024-02-23 | On-time | 2024-03-15 | 21 | 2024-03-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 45977474 | T2 DI DIABLO-GATES #1- 09/42 RPR GYWT | ICQ
LC | 125670299 | 003/018 | T2 DI IBM HARRY RD#1 TAP 003/018 COTTER | METCALF | ETL.2501.INSL | 2023-03-16 | 2023-03-16 | 2023-11-16 | On-time | 2024-03-15 | 120 | 2024-03-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45999081 | T2 DI IBM HARRY RD#1 TAP 003/018 COTTER | ICS
LC | 125723966 | 015/002 | T2 DI FT BRGG-ELK 15/2 COMPLETE | WILLITS | ETL.2060.POLE.WOOD | 2023-03-24 | 2023-03-13 | 2024-03-19 | Late | 2024-03-12 | -7 | 2024-03-13 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125670382 | 007/043 | T2 DI MNTA VSTA-CYT SS 7/43 RPL INSS | MOSSLNDG | ETL.5090.INSL | 2023-03-16 | 2023-03-16 | 2024-03-12 | On-time | 2024-03-15 | 3 | 2024-03-16 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671708 | T2 DI MNTA VSTA-CYT SS 7/43 RPL INSS | 93K
LC | 125678560 | 009/043 | T2 DI DIABLO GTS#1 9/43 RPR SHIELD | PISMOBCH | ETL.5960.TOWR | 2023-03-17 | 2023-03-16 | 2024-03-04 | On-time | 2024-03-15 | 11 | 2024-03-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46078901 | T2 DI DIABLO GTS#1 9/43 RPR SHIELD | ICS
LC | 125680149 | 023/096 | T2 DI DIABLO-GATES #1 23/96 RPR SHIELD | PISMOBCH | ETL.5960.TOWR | 2023-03-17 | 2023-03-16 | 2024-01-31 | On-time | 2024-03-15 | 44 | 2024-03-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46078902 | T2 DI DIABLO-GATES #1 23/96 RPR SHIELD | ICS
LC | 125724400 | 002/025 | +2 DI MONTA VISTA-BURNS 2/25 GO95 RPL | MOSSLNDG | ETL.7590.POLE.WOOD | 2023-03-24 | 2023-03-16 | 2024-03-10 | On-time | 2024-03-15 | 5 | 2024-03-16 | 401 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35505601 | T2 DI MONTA VISTA-BURNS 2/25 GO95 | 93G
LC | 125732258 | 006/076 | T2 DI DIVIDE-CABRILLO #2 06/76C RPL STRW | PISMOBCH | ETL.1370.POLE.WDPS | 2023-03-25 | 2023-03-16 | 2024-01-02 | On-time | 2024-03-15 | 73 | 2024-03-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35489952 | T2 DI DIVIDE-CABRILLO #2 06/76C RPL STRW | 70Y
LC | 125724122 | 016/000 | T2 DI FORT BRAGG-ELK 16/0 RPL INSW | WILLITS | ETL.2060.INSL.NCER | 2023-03-24 | 2023-03-13 |  | Late | 2024-03-12 |  | 2024-03-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35487717 | T2 DI FORT BRAGG-ELK 16/00 RPL INSW | 93I
LC | 125732311 | 006/076 | T2 DI DIVIDE-CABRILLO #2 06/76L RPL STRW | PISMOBCH | ETL.1370.POLE.WDPS | 2023-03-25 | 2023-03-16 | 2024-01-02 | On-time | 2024-03-15 | 73 | 2024-03-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35489952 | T2 DI DIVIDE-CABRILLO #2 06/76C RPL STRW | 70Y
LC | 125735617 | 006/076 | T2 DI DIVIDE-CABRILLO #2 06/76R RPL STRW | PISMOBCH | ETL.1370.POLE.WDPS | 2023-03-27 | 2023-03-16 | 2024-01-02 | On-time | 2024-03-15 | 73 | 2024-03-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35489952 | T2 DI DIVIDE-CABRILLO #2 06/76C RPL STRW | 70Y
LC | 125748460 | 010/123 | T2 DI CLGT-SMTVLL #1 10/123 RPR SPLW | SACTO | ETL.6510.INSL.NCER | 2023-03-28 | 2023-03-16 | 2023-07-20 | On-time | 2024-03-15 | 239 | 2024-03-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45927906 | T2 DI CLGT-SMTVLL #1 10/123 RPR SPLW | ICW
LC | 125748583 | 010/131 | T2 DI DIVIDE-CABRILLO #1 10/131 RPR GYWW | PISMOBCH | ETL.1380.POLE.WOOD | 2023-03-28 | 2023-03-16 | 2024-01-12 | On-time | 2024-03-15 | 63 | 2024-03-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088475 | T2 DI DIVIDE-CABRILLO #1 10/131 RPR GYWW | ICW
LC | 125748700 | 010/131 | T2 DI DIVIDE-CABRILLO #1 10/131 RMV VEGN | PISMOBCH | ETL.1380.POLE.WOOD | 2023-03-28 | 2023-03-16 | 2024-03-01 | On-time | 2024-03-15 | 14 | 2024-03-16 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125724316 | 022/014A | T2 DI MENDO-HARTLEY 22/14A RPR JUMW | WILLITS | ETL.7510.INSL.NCER | 2023-03-24 | 2023-03-10 |  | Late | 2024-03-09 |  | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45977805 | T2 DI MENDO-HARTLEY 22/14A RPR JUMW | ICW
LC | 125724351 | 002/050A | T2 DI MANVILLE TAP 002/050A RPR GYWW | PISMOBCH | ETL.1372.POLE.WOOD | 2023-03-24 | 2023-03-21 | 2024-03-25 | Late | 2024-03-20 | -5 | 2024-03-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088471 | T2 DI MANVILLE TAP 002/050A RPR GYWW | ICW
LC | 125674676 | 000/015 | T2 SPLDNG #3-SPLDNG #1 000/015 RMV IDLE | SACTO | ETL.8050.POLE.WOOD | 2023-03-17 | 2023-03-17 | 2023-11-16 | On-time | 2024-03-16 | 121 | 2024-03-17 | 673 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Idle | Structure-Wood | Remove | 31671477 | T2 SPLDNG #3-SPLDNG #1 000/015 RMV IDLE | 93J
LC | 125674734 | 000/019 | T2 SPLDNG #3-SPLDNG #1 00/019 RMV IDLE | SACTO | ETL.8050.POLE.WOOD | 2023-03-17 | 2023-03-17 | 2023-11-16 | On-time | 2024-03-16 | 121 | 2024-03-17 | 673 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Idle | Structure-Wood | Remove | 31671477 | T2 SPLDNG #3-SPLDNG #1 000/015 RMV IDLE | 93J
LC | 125724436 | 023/002 | T2 DI FORT BRAGG-ELK 23/2 RPR CNDW | WILLITS | ETL.2060.INSL.NCER | 2023-03-24 | 2023-03-10 |  | Late | 2024-03-09 |  | 2024-03-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45977806 | T2 DI FORT BRAGG-ELK 23/2 RPR CNDW | ICW
LC | 125724437 | 054/010 | T2 DI FT RSS-GUALA 54/10 RPL DAMW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-03-24 | 2023-03-23 |  | Late | 2024-03-22 |  | 2024-03-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46042593 | T2 DI FT RSS-GUALA 54/10 RPL DAMW | ICW
LC | 125724455 | 021/003 | T2 DI FORT BRAGG-ELK 021/003 RPL INSW | WILLITS | ETL.2060.INSL.CERA | 2023-03-24 | 2023-03-10 |  | Late | 2024-03-09 |  | 2024-03-10 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35486932 | T2 DI FORT BRAGG-ELK 020/009 RPL INSW | 93I
LC | 125724472 | 023/002 | T2 DI FORT BRAGG-ELK 23/2 RPL POLE | WILLITS | ETL.2060.POLE.WOOD | 2023-03-24 | 2023-03-10 |  | Late | 2024-03-09 |  | 2024-03-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486931 | T2 DI FORT BRAGG-ELK 019/012 RPL POLE | 70Y
LC | 125674736 | 000/020 | T2 SPLDNG #3-SPLDNG #1 000/020 RMV IDLE | SACTO | ETL.8050.POLE.WOOD | 2023-03-17 | 2023-03-17 | 2023-11-16 | On-time | 2024-03-16 | 121 | 2024-03-17 | 673 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Idle | Structure-Wood | Remove | 31671477 | T2 SPLDNG #3-SPLDNG #1 000/015 RMV IDLE | 93J
LC | 125724775 | 006/080-GUY | T2 DI IGNACIO-BOLINAS #2 6/80 RPR ANCW | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-03-24 | 2023-03-13 |  | Late | 2024-03-12 |  | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45977497 | T2 DI IGNACIO-BOLINAS #2 6/80 RPR ANCW | ICW
LC | 125676211 | 024/393 | T2 DI KESWICK-TRINITY 024/393 RPL INSW | TABLEMTN | ETL.7270.INSL | 2023-03-17 | 2023-03-17 | 2023-07-21 | On-time | 2024-03-16 | 239 | 2023-06-17 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31640177 | T2 DI KESWICK-TRINITY 024/393 RPL INSW | 93I
LC | 125725163 | 013/002 | T2 DI FT BRGG-ELK 13/2 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-24 | 2023-03-13 | 2024-04-11 | Late | 2024-03-12 | -30 | 2024-03-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487937 | T2 DI FT BRGG-ELK 13/2 RPL STRW | 70Y
LC | 125725253 | 013/272 | T2 DI LAKEVILLE#2 13/272 RPL INSW | LAKEVLLE | ETL.7340.INSL.NCER | 2023-03-24 | 2023-03-13 | 2024-04-20 | Late | 2024-03-12 | -39 | 2024-03-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35490744 | T2 DI LAKEVILLE#2 13/272 RPL INSW | 93I
LC | 125725332 | 011/007 | T2 DI FORT BRAGG ELK 11/007 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-24 | 2023-03-15 |  | Late | 2024-03-14 |  | 2024-03-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35488002 | T2 DI FORT BRAGG ELK 11/007 RPL STRW | 70Y
LC | 125680661 | 013/050 | T2 DI DIABLO-GATES #3 013/050 COTTER | PISMOBCH | ETL.5980.INSL | 2023-03-17 | 2023-03-17 | 2024-02-22 | On-time | 2024-03-16 | 23 | 2024-03-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46007577 | T2 DI DIABLO-GATES #3 013/050 COTTER | ICS
LC | 125681037 | 021/084 | T2 DI DIABLO-MIDWAY #3 21/84 RPR GYWT | PISMOBCH | ETL.5980.TOWR | 2023-03-17 | 2023-03-17 | 2024-02-23 | On-time | 2024-03-16 | 22 | 2024-03-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 45977478 | T2 DI DIABLO-MIDWAY #3 21/84 RPR GYWT | ICQ
LC | 125682254 | 010/126 | T2 DI DIVIDE CABRILLO #2 10/126 RPR GYWW | PISMOBCH | ETL.1370.POLE.WOOD | 2023-03-18 | 2023-03-17 | 2024-02-13 | On-time | 2024-03-16 | 32 | 2024-03-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46078386 | T2 DI DIVIDE CABRILLO #2 10/126 RPR GYWW | ICW
LC | 125682584 | 012/006 | T2 DI LAYTONVILLE-WILLITS 12/6 RPR GYWW | WILLITS | ETL.8360.POLE.WOOD | 2023-03-18 | 2023-03-17 | 2023-11-30 | On-time | 2024-03-16 | 107 | 2024-03-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45988990 | T2 DI LAYTONVILLE-WILLITS 12/6 RPR GYWW | ICW
LC | 125694976 | 059/242 | T2 DI DIABLO-GATES #1 059/242 COTTER | PISMOBCH | ETL.5960.INSL.NCER | 2023-03-20 | 2023-03-17 | 2024-01-31 | On-time | 2024-03-16 | 45 | 2024-03-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46007579 | T2 DI DIABLO-GATES #1 059/242 COTTER | ICS
LC | 125697624 | 002/023C | T2 DI MONTA VISTA-BURNS 2/023C COMPLETE | MOSSLNDG | ETL.7590.POLE.WOOD | 2023-03-20 | 2023-03-17 | 2024-03-13 | On-time | 2024-03-16 | 3 | 2024-03-17 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125697627 | 002/023C | T2 DI MONTA VISTA-BURNS 2/023C RPL POLE | MOSSLNDG | ETL.7590.POLE.WOOD | 2023-03-20 | 2023-03-17 | 2024-03-09 | On-time | 2024-03-16 | 7 | 2024-03-17 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505600 | T2 DI MONTA VISTA-BURNS 2/23A RPL POLE | 70Y
LC | 125697739 | 002/023B | T2 DI MONTA VISTA-BURNS 2/23B RPL POLE | MOSSLNDG | ETL.7590.POLE.WOOD | 2023-03-20 | 2023-03-17 | 2024-03-09 | On-time | 2024-03-16 | 7 | 2024-03-17 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505600 | T2 DI MONTA VISTA-BURNS 2/23A RPL POLE | 70Y
LC | 125726643 | 014/002 | T2 DI FORT BRAGG-ELK 14/2 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-24 | 2023-03-13 |  | Late | 2024-03-12 |  | 2023-09-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487925 | T2 DI FORT BRAGG-ELK 14/3 RPL STRW | 70Y
LC | 125726649 | 023/116 | T2 DI FULTON-IGNCIO #1 23/116 RPL INSS | LAKEVLLE | ETL.4680.INSL | 2023-03-24 | 2023-03-13 |  | Late | 2024-03-12 |  | 2024-03-13 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31678225 | T2 DI FULTON-IGNCIO #1 RPL INSS IN 5 TWR | 93K
LC | 125697761 | 002/023B | T2 DI MONTA VISTA-BURNS 2/23B COMPLETE | MOSSLNDG | ETL.7590.POLE.WOOD | 2023-03-20 | 2023-03-17 | 2024-03-13 | On-time | 2024-03-16 | 3 | 2024-03-17 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125697806 | 011/093 | T2 DI CBRLLO-SNTA YNZ SS 11/93 RPL INSW | PISMOBCH | ETL.1200.INSL.NCER | 2023-03-20 | 2023-03-17 | 2024-01-30 | On-time | 2024-03-16 | 46 | 2024-03-17 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31645483 | T2 DI CBRLL-SNT YNZ SW 2/12 RPL INSW | 93I
LC | 125697819 | 013/049 | T2 DI DIABLO-MIDWAY #2 13/49 RPL HRDT | PISMOBCH | ETL.5970.TOWR | 2023-03-20 | 2023-03-17 | 2024-02-22 | On-time | 2024-03-16 | 23 | 2024-03-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45977476 | T2 DI DIABLO-MIDWAY #2 13/49 RPL HRDT | ICQ
LC | 125726744 | 011/141 | T2 DI WST PNT-VLY SPRNGS 11/141 RPR GYWW | VICTOR | ETL.8350.POLE.NWOD | 2023-03-24 | 2023-03-15 |  | Late | 2024-03-14 |  | 2024-03-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45978043 | T2 DI WST PNT-VLY SPRNGS 11/141 RPR GYWW | ICW
LC | 125698056 | 002/023A | T2 DI MONTA VISTA-BURNS 2/23A RPL POLE | MOSSLNDG | ETL.7590.POLE.WOOD | 2023-03-20 | 2023-03-17 | 2024-03-09 | On-time | 2024-03-16 | 7 | 2024-03-17 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505600 | T2 DI MONTA VISTA-BURNS 2/23A RPL POLE | 70Y
LC | 125726842 | 000/002 | T2 DI IONE TAP 0/2 RPR GYWW | VICTOR | ETL.8253.POLE.WOOD | 2023-03-24 | 2023-03-13 | 2024-04-02 | Late | 2024-03-12 | -21 | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45978044 | T2 DI IONE TAP 0/2 RPR GYWW | ICW
LC | 125698105 | 012/049 | T2 DI DIABLO-MIDWAY#3 12/49 INS GYWT | PISMOBCH | ETL.5980.TOWR | 2023-03-20 | 2023-03-17 | 2024-03-04 | On-time | 2024-03-16 | 12 | 2024-03-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 45977477 | T2 DI DIABLO-MIDWAY#3 12/49 INS GYWT | ICQ
LC | 125723868 | 008/070 | T2 DI CBRLL0-SNTA YNEZ 8/70 RPL INSW | PISMOBCH | ETL.1200.INSL.NCER | 2023-03-24 | 2023-03-17 | 2024-01-30 | On-time | 2024-03-16 | 46 | 2024-03-17 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31645483 | T2 DI CBRLL-SNT YNZ SW 2/12 RPL INSW | 93I
LC | 125748486 | 012/096 | T2 DI TGR CRK-VLY SPRNGS 12/96 RPR STRT | VICTOR | ETL.5790.TOWR | 2023-03-28 | 2023-03-17 | 2023-12-04 | On-time | 2024-03-16 | 103 | 2024-03-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45984658 | T2 DI TGR CRK-VLY SPRNGS 12/96 RPR STRT | ICQ
LC | 125727298 | 014/012 | T2 DI FORT BRAGG-ELK 14/12 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-24 | 2023-03-13 |  | Late | 2024-03-12 |  | 2024-03-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487719 | T2 DI FORT BRAGG-ELK 14/12 RPL STRW | 70Y
LC | 125727490 | 000/011 | T2 DI IONE TAP 0/11 RPR POLE | VICTOR | ETL.8253.POLE.WOOD | 2023-03-24 | 2023-03-13 | 2024-04-16 | Late | 2024-03-12 | -35 | 2024-03-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45978045 | T2 DI IONE TAP 0/11 RPR POLE | ICW
LC | 125748796 | 002/012 | T2 DI CBRLL-SNT YNZ SW 2/12 RPL INSW | PISMOBCH | ETL.1200.INSL.NCER | 2023-03-28 | 2023-03-17 | 2024-01-29 | On-time | 2024-03-16 | 47 | 2024-03-17 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31645483 | T2 DI CBRLL-SNT YNZ SW 2/12 RPL INSW | 93I
LC | 125727698 | 004/000 | T2 DI LYTNVL-COVLO 4/0 RPL STRW | WILLITS | ETL.7390.POLE.WOOD | 2023-03-24 | 2023-03-23 |  | Late | 2024-03-22 |  | 2024-03-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35489660 | T0 DI LYTNVL-CVLO 02/08 RPL STRW | 70Y
LC | 125727793 | 013/277 | T2 DI LAKEVILLE #2 13/277 RPL INSW | LAKEVLLE | ETL.7340.INSL.NCER | 2023-03-24 | 2023-03-13 | 2024-04-19 | Late | 2024-03-12 | -38 | 2024-03-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35490746 | T2 DI LAKEVILLE #2 13/277 RPL INSW | 93I
LC | 125727912 | 015/013 | T2 DI FORT BRAGG-ELK 15/13 RPL INSW | WILLITS | ETL.2060.INSL.CERA | 2023-03-24 | 2023-03-13 |  | Late | 2024-03-12 |  | 2024-03-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35488314 | T2 DI FORT BRAGG-ELK 15/13 RPL INSW | 93I
LC | 125748801 | 008/074 | T2 DI CAB-STA YZ SW STA 8/74 RPR GYWW | PISMOBCH | ETL.1200.POLE.NWOD | 2023-03-28 | 2023-03-17 | 2024-01-30 | On-time | 2024-03-16 | 46 | 2024-03-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46078600 | T2 DI CAB-STA YZ SW STA 8/74 RPR GYWW | ICW
LC | 125728305 | 008/014 | T2 DI MELONES-RACETRACK 8/14 RPL IBWW | VICTOR | ETL.2400.POLE.WOOD | 2023-03-24 | 2023-03-20 | 2024-05-08 | Late | 2024-03-19 | -50 | 2024-03-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45984774 | T2 DI MELONES-RACETRACK 8/14 RPL IBWW | ICW
LC | 125728340 | 019/214 | T2 DI ELK CREEK TAP 19/214 RMV VEG | TABLEMTN | ETL.6921.POLE.NWOD | 2023-03-24 | 2023-03-10 |  | Late | 2024-03-09 |  | 2024-03-10 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 125748822 | 008/072 | T2 DI CBRLL-SNT YNZ SW 8/72 RPL INSW | PISMOBCH | ETL.1200.INSL.NCER | 2023-03-28 | 2023-03-17 | 2024-01-30 | On-time | 2024-03-16 | 46 | 2024-03-17 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31645483 | T2 DI CBRLL-SNT YNZ SW 2/12 RPL INSW | 93I
LC | 125748865 | 008/071 | T2 DI CABRILLO-SANTA YNEZ 8/71 RPL INSW | PISMOBCH | ETL.1200.INSL.NCER | 2023-03-28 | 2023-03-17 | 2024-01-29 | On-time | 2024-03-16 | 47 | 2024-03-17 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31645483 | T2 DI CBRLL-SNT YNZ SW 2/12 RPL INSW | 93I
LC | 125728876 | 020/101 | T2 DI FULTON-IGNACIO#1 20/101 RPL INSS | LAKEVLLE | ETL.4680.INSL | 2023-03-24 | 2023-03-13 |  | Late | 2024-03-12 |  | 2024-03-13 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31678225 | T2 DI FULTON-IGNCIO #1 RPL INSS IN 5 TWR | 93K
LC | 125751789 | 010/127 | T2 DI DIVIDE-CBRLLO #2 10/127 RPR STRW | PISMOBCH | ETL.1370.POLE.WOOD | 2023-03-29 | 2023-03-17 | 2024-01-04 | On-time | 2024-03-16 | 72 | 2024-03-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46078387 | T2 DI DIVIDE-CBRLLO #2 10/127 RPR STRW | ICW
LC | 125751917 | 006/081 | T2 DI DIVIDE-CABRILLO #2 06/81L RPR GYWW | PISMOBCH | ETL.1370.POLE.WDPS | 2023-03-29 | 2023-03-17 | 2024-01-06 | On-time | 2024-03-16 | 70 | 2024-03-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46078384 | T2 DI DIVIDE-CABRILLO #2 06/81L RPR GYWW | ICW
LC | 125751918 | 006/081 | T2 DI DIVIDE-CABRILLO #2 06/81R RPR GYWW | PISMOBCH | ETL.1370.POLE.WDPS | 2023-03-29 | 2023-03-17 | 2024-01-06 | On-time | 2024-03-16 | 70 | 2024-03-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46078385 | T2 DI DIVIDE-CABRILLO #2 06/81R RPR GYWW | ICW
LC | 125752112 | 006/080 | T2 DI DIVIDE-CBRLLO #2 6/80 RPL POLE | PISMOBCH | ETL.1370.POLE.WOOD | 2023-03-29 | 2023-03-17 | 2024-01-05 | On-time | 2024-03-16 | 71 | 2024-03-17 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491216 | T2 DI DIVIDE-CBRLLO #2 6/80 RPL POLE | 70Y
LC | 125752281 | 010/130 | T2 DI DIVIDE-CBRLLO #2 10/130 RPR INSS | PISMOBCH | ETL.1370.INSL.CERA | 2023-03-29 | 2023-03-17 | 2024-01-04 | On-time | 2024-03-16 | 72 | 2024-03-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46078388 | T2 DI DIVIDE-CBRLLO #2 10/130 RPR INSS | ICW
LC | 125682536 | 049/201 | T2 EI MIDWAY-WHIRLWIND 049/201 COTTER | MIDWAY | ETL.6030.INSL.NCER | 2023-03-18 | 2023-03-18 | 2024-01-09 | On-time | 2024-03-17 | 68 | 2024-03-18 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46007578 | T2 EI MIDWAY-WHIRLWIND 049/201 COTTER | ICS
LC | 125686083 | :011/006 | T2 BLTA-RVRBNK-MLNS SW ST_:11/6 GO95 CLR | VICTOR | ETL.1070.POLE.WOOD | 2023-03-20 | 2023-03-20 | 2023-05-25 | On-time | 2024-03-19 | 299 | 2023-09-20 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640618 | T2 BLTA-RVRBNK-MLNS SW ST_:11/6 GO95 CLR | 93G
LC | 125730667 | 007/015 | T2 DI VLY SPRNGS-MRTL #1 7/15 RPR SPLW | VICTOR | ETL.8240.INSL.NCER | 2023-03-25 | 2023-03-14 | 2024-05-22 | Late | 2024-03-13 | -70 | 2024-03-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45978047 | T2 DI VLY SPRNGS-MRTL #1 7/15 RPR SPLW | ICW
LC | 125688457 | 035/167 | T2 EI RND MTN-TBL MTN #1 35/167 BNT STL | TABLEMTN | ETL.6060.TOWR | 2023-03-20 | 2023-03-20 | 2024-02-26 | On-time | 2024-03-19 | 22 | 2024-03-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008764 | T2 EI RND MTN-TBL MTN #1-_35/167 BNT STL | ICQ
LC | 125730809 | 005/026 | T2 DI MTCLF-EL PTIO #1 5/26 RPR STRT | METCALF | ETL.2500.TOWR | 2023-03-25 | 2023-03-14 | 2024-05-07 | Late | 2024-03-13 | -55 | 2024-03-14 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008505 | T2 DI MTCLF-EL PTIO #1 005/026 RPR STRT | ICQ
LC | 125730972 | 000/002 | T2 EI SOBRANTE-R #1 000/002 BNT STEEL | CONCORD | ETL.3770.TOWR | 2023-03-25 | 2023-03-25 | 2024-05-02 | Late | 2024-03-24 | -39 | 2024-03-25 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008507 | T2 EI SOBRANTE-R #1 000/002 BNT STEEL | ICQ
LC | 125731047 | 013/298A | T2 EI DRM-GRSS VLLY-WMR 13/298A REGRADE | SACTO | ETL.6760.POLE.WOOD | 2023-03-25 | 2023-03-25 |  | Late | 2024-03-24 |  | 2023-09-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Regrade | 45993519 | T2 EI DRM-GRASS VLLY-WMR 13/298A REGRADE | ICW
LC | 125690080 | 036/171 | T2 EI RND MTN-TBL MTN #2 -36/171 BNT STL | TABLEMTN | ETL.6070.TOWR | 2023-03-20 | 2023-03-20 | 2023-11-13 | On-time | 2024-03-19 | 127 | 2024-03-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008765 | T2 EI RND MTN-TBL MTN #2 -36/171 BNT STL | ICQ
LC | 125690453 | 037/172 | T2 EI RND MTN-TBL MTN #2 -37/172 BNT STL | TABLEMTN | ETL.6070.TOWR | 2023-03-20 | 2023-03-20 | 2023-11-13 | On-time | 2024-03-19 | 127 | 2024-03-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008766 | T2 EI RND MTN-TBL MTN #2 -37/172 BNT STL | ICQ
LC | 125697407 | 058/239A | T2 DI DIABLO-GATES #1 058/239A RPR SHLS | PISMOBCH | ETL.5960.TOWR | 2023-03-20 | 2023-03-20 | 2024-01-31 | On-time | 2024-03-19 | 48 | 2024-03-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46078915 | T2 DI DIABLO-GATES #1 058/239A RPR SHLS | ICS
LC | 125731130 | 023/003B | T2 EI FORT BRAGG-ELK 23/03B RPL POLE | WILLITS | ETL.2060.POLE.WOOD | 2023-03-25 | 2023-03-25 | 2024-04-17 | Late | 2024-03-24 | -24 | 2024-03-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487232 | T2 EI FORT BRAGG-ELK 23/03A RPL POLE | 70Y
LC | 125705965 | 012/000 | T2 DI LAYTONVILLE-WILLITS 12/00 COTTER | WILLITS | ETL.8360.POLE.WOOD | 2023-03-21 | 2023-03-20 | 2023-10-25 | On-time | 2024-03-19 | 146 | 2024-03-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45988991 | T2 DI LAYTONVILLE-WILLITS 12/00 COTTER | ICW
LC | 125731195 | 024/000 | T2 EI PHILO JCT-ELK 024/000 RPR GYWW | WILLITS | ETL.7780.POLE.WOOD | 2023-03-25 | 2023-03-25 | 2024-05-23 | Late | 2024-03-24 | -60 | 2024-03-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46214050 | T2 EI PHILO JCT-ELK 024/000 RPR GYWW | ICW
LC | 125731229 | 024/000 | T2 EI PHILO JCT-ELK 024/000 RPL DMPW | WILLITS | ETL.7780.INSL.CERA | 2023-03-25 | 2023-03-25 | 2024-05-23 | Late | 2024-03-24 | -60 | 2024-03-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46214051 | T2 EI PHILO JCT-ELK 024/000 RPL DMPW | ICW
LC | 125708570 | 000/017 | T2 DI HALSEY-PLACER 0/17 RPR ADSS | SACTO | ETL.6990.POLE.WOOD | 2023-03-22 | 2023-03-20 | 2023-04-21 | On-time | 2024-03-19 | 333 | 2023-06-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45719877 | T2 DI HALSEY-PLACER 0/17 RPR ADSS | ICW
LC | 125724389 | 000/015 | T2 DI HALSEY PLACER 0/015 RPR FIBER | SACTO | ETL.6990.POLE.WOOD | 2023-03-24 | 2023-03-20 | 2023-04-25 | On-time | 2024-03-19 | 329 | 2023-06-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45719879 | T2 DI HALSEY PLACER 0/015 RPR FIBER | ICW
LC | 125731468 | 024/003 | T2 EI PHILO JCT-ELK 024/003 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-03-25 | 2023-03-25 |  | Late | 2024-03-24 |  | 2024-03-25 | 372T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35556613 | T2 EI PHILO JCT-ELK 024/003 RPL POLE | 70Y
LC | 125731486 | 006/099 | T2 EI CNTRVLLE-TABLE MTN 6/99 COMPLETE | TABLEMTN | ETL.6320.POLE.WOOD | 2023-03-25 | 2023-03-25 | 2024-06-10 | Late | 2024-03-24 | -78 | 2024-03-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490755 | T2 EI CNTRVLLE-TABLE MTN 6/99 RPL STRW | 70Y
LC | 125731627 | 006/101 | T2 EI CNTRVLLE-TABLE MTN 6/101 RPL STRW | TABLEMTN | ETL.6320.POLE.WOOD | 2023-03-25 | 2023-03-25 | 2024-06-10 | Late | 2024-03-24 | -78 | 2024-03-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490755 | T2 EI CNTRVLLE-TABLE MTN 6/99 RPL STRW | 70Y
LC | 125731675 | 006/101 | T2 EI CNTRVLLE-TABLE MTN 6/101 RPR SLPW | TABLEMTN | ETL.6320.INSL.NCER | 2023-03-25 | 2023-03-25 | 2024-06-10 | Late | 2024-03-24 | -78 | 2024-03-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45989279 | T2 EI CNTRVLLE-TABLE MTN 6/101 RPR SLPW | ICW
LC | 125748120 | 000/007 | T2 DI HALSY-PLCR 0/7 COMPLETE | SACTO | ETL.6990.POLE.WOOD | 2023-03-28 | 2023-03-20 | 2023-06-13 | On-time | 2024-03-19 | 280 | 2023-06-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45724360 | T2 DI HALSY-PLCR 0/7 RPR NON-ADSS | ICW
LC | 125748780 | 000/003 | T2NT DI HALSEY-PLACER 00/03 RPR NON-ADSS | SACTO | ETL.6990.POLE.NWOD | 2023-03-28 | 2023-03-20 | 2023-04-23 | On-time | 2024-03-19 | 331 | 2023-06-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45724363 | T2NT DI HALSEY-PLACER 00/03 RPR NON-ADSS | ICW
LC | 125731852 | 024/004 | T2 EI PHILO JCT-ELK 024/004 RPL INSW | WILLITS | ETL.7780.INSL.CERA | 2023-03-25 | 2023-03-25 | 2024-05-30 | Late | 2024-03-24 | -67 | 2024-03-25 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35490742 | T2 EI PHILO JCT-ELK 024/004 RPL INSW | 93I
LC | 125756150 | 008/111 | T2 DI VALLEY SPRINGS-CLAY 8/11 RPL HRDW | VICTOR | ETL.8264.POLE.WOOD | 2023-03-29 | 2023-03-20 | 2023-05-11 | On-time | 2024-03-19 | 313 | 2024-03-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45727407 | T2 DI VALLEY SPRINGS-CLAY 8/11 RPL HRDW | ICW
LC | 125731919 | 023/005 | T2 EI PHILO JCT-ELK 023/005 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-03-25 | 2023-03-25 | 2024-06-03 | Late | 2024-03-24 | -71 | 2024-03-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490740 | T2 EI PHILO JCT-ELK 023/005 RPL POLE | 70Y
LC | 125756424 | 014/008 | T2 DI FORT BRAGG-ELK 14/8 RPR STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-29 | 2023-03-20 | 2024-02-26 | On-time | 2024-03-19 | 22 | 2024-03-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45988987 | T2 DI FORT BRAGG-ELK 14/8 RPR STRW | ICW
LC | 125761012 | 015/059 | T2 DI DIABLO MIDWAY#2 15/059 RPR SHLS | PISMOBCH | ETL.5970.TOWR | 2023-03-30 | 2023-03-20 | 2024-02-20 | On-time | 2024-03-19 | 28 | 2024-03-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46078958 | T2 DI DIABLO MIDWAY#2 15/059 RPR SHLS | ICS
LC | 125761738 | 022/089 | T2 DI DIABLO-MIDWAY #2 22/89 RPR SHLS | PISMOBCH | ETL.5970.TOWR | 2023-03-30 | 2023-03-20 | 2024-03-11 | On-time | 2024-03-19 | 8 | 2024-03-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46078962 | T2 DI DIABLO-MIDWAY #2 22/89 RPR SHIELD | ICS
LC | 125766415 | 015/060 | T2 DI DIABLO-MDWY#2 15/60 RPR OPGW | PISMOBCH | ETL.5970.TOWR | 2023-03-30 | 2023-03-20 | 2024-02-20 | On-time | 2024-03-19 | 28 | 2024-03-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46078960 | T2 DI DIABLO-MDWY#2 15/60 RPR OPGW | ICS
LC | 125768125 | 014/054A | T2 DI DBLO MDWY#3 14/54A RMV DBRS CNDS | PISMOBCH | ETL.5980.INSL.NCER | 2023-03-31 | 2023-03-20 | 2024-02-22 | On-time | 2024-03-19 | 26 | 2024-03-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Conductor-Steel | Remove | 45998016 | T2 DI DBLO MDWY#3 14/54A RMV DBRS CNDT | ICS
LC | 125732388 | 022/007 | T2 EI FORT BRAGG-ELK 22/7 RPL INSW | WILLITS | ETL.2060.INSL.CERA | 2023-03-25 | 2023-03-25 | 2024-04-19 | Late | 2024-03-24 | -26 | 2024-03-25 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35487238 | T2 EI FORT BRAGG-ELK 022/010 RPL INSW | 93I
LC | 125771709 | 044/179 | T2 DI DIABLO MIDWAY #3 44/179 RPR SHLS | PISMOBCH | ETL.5980.TOWR | 2023-03-31 | 2023-03-20 | 2024-03-11 | On-time | 2024-03-19 | 8 | 2024-03-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46088476 | T2 DI DIABLO MIDWAY #3 44/179 RPR SHLS | ICS
LC | 125732485 | B025/571 | T2 EI DRM-GRS VALY-WIMR B25/571 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2023-03-25 | 2023-03-25 | 2024-06-23 | Late | 2024-03-24 | -91 | 2024-03-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46217622 | T2 EI DRM-GRS VALY-WIMR B25/571 RPR GYWW | ICW
LC | 125732533 | 023/002 | T2 EI PHILO JCT-ELK 023/002 RPL DMPW | WILLITS | ETL.7780.INSL.CERA | 2023-03-25 | 2023-03-25 | 2024-05-22 | Late | 2024-03-24 | -59 | 2024-03-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46216628 | T2 EI PHILO JCT-ELK 023/002 RPL DMPW | ICW
LC | 125732667 | 012/277 | T2 EI DRM-GRSS VLLEY-WMR 12/277 RPR JMPW | SACTO | ETL.6760.INSL.CERA | 2023-03-25 | 2023-03-25 |  | Late | 2024-03-24 |  | 2024-03-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45993620 | T2 EI DRM-GRSS VLLEY-WMR 12/277 RPR JMPW | ICW
LC | 125700430 | 012/288 | T2 EI DRM-GRSS VLLY-WMR 012/2 RPL HRDW | SACTO | ETL.6760.POLE.WOOD | 2023-03-21 | 2023-03-21 | 2024-01-12 | On-time | 2024-03-20 | 68 | 2024-03-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45984332 | T2 EI DRM-GRSS VLLY-WMR 012/2 RPL HRDW | ICW
LC | 125721482 | 011/215 | T2 DI VALLEY SPRINGS #2 11/215 RPR CRSW | VICTOR | ETL.9460.POLE.WOOD | 2023-03-23 | 2023-03-21 | 2024-02-14 | On-time | 2024-03-20 | 35 | 2024-03-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45984772 | T2 DI VALLEY SPRINGS #2 11/215 RPR CRSW | ICW
LC | 125721485 | 011/215 | T2 DI VALLEY SPRINGS #2 11/215 RPL HRDW | VICTOR | ETL.9460.POLE.WOOD | 2023-03-23 | 2023-03-21 | 2024-02-14 | On-time | 2024-03-20 | 35 | 2024-03-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45984773 | T2 DI VALLEY SPRINGS #2 11/215 RPL HRDW | ICW
LC | 125733091 | 012/004 | T2 DI LAYTONVLE-WLLTS 12/4 RPR STRW | WILLITS | ETL.8360.POLE.WOOD | 2023-03-25 | 2023-03-20 |  | Late | 2024-03-19 |  | 2024-03-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45988994 | T2 DI LAYTONVLE-WLLTS 12/4 RPR STRW | ICW
LC | 125733117 | 008/112 | T2 DI VLY SPRNGS-CLY 8/112 RPL INSW | VICTOR | ETL.8264.INSL.NCER | 2023-03-25 | 2023-03-24 |  | Late | 2024-03-23 |  | 2024-03-24 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35514990 | T2 DI VLY SPRNGS-CLY 8/112 RPL INSW | 93I
LC | 125723976 | 010/147 | T2 DI DELTA-MTN GATE JCT 10/147 RPR GYWW | TABLEMTN | ETL.6750.POLE.STPS | 2023-03-24 | 2023-03-21 | 2023-05-04 | On-time | 2024-03-20 | 321 | 2023-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45711286 | T2 DI DELTA-MTN GATE JCT 10/147 RPR GYWW | ICW
LC | 125723979 | 010/147 | T2 DI DELTA-MTN GATE JCT 10/147 RPR GYWW | TABLEMTN | ETL.6750.POLE.STPS | 2023-03-24 | 2023-03-21 | 2023-05-04 | On-time | 2024-03-20 | 321 | 2023-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45711287 | T2 DI DELTA-MTN GATE JCT 10/147 RPR GYWW | ICW
LC | 125733143 | 008/112 | T2 DI VLY SPRNGS-CLY 8/112 RPR XARM | VICTOR | ETL.8264.POLE.WOOD | 2023-03-25 | 2023-03-24 |  | Late | 2024-03-23 |  | 2024-03-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45990635 | T2 DI VLY SPRNGS-CLY 8/112 RPR XARM | ICW
LC | 125723987 | 010/147 | T2 DI DELTA-MTN GATE JCT 10/147 RPR GYWW | TABLEMTN | ETL.6750.POLE.STPS | 2023-03-24 | 2023-03-21 | 2023-05-04 | On-time | 2024-03-20 | 321 | 2023-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45711288 | T2 DI DELTA-MTN GATE JCT 10/147 RPR GYWW | ICW
LC | 125733876 | 003/070 | T2 EI KESWICK-CASCADE 3/70 RPL STRW | TABLEMTN | ETL.7260.POLE.WOOD | 2023-03-26 | 2023-03-26 | 2024-06-11 | Late | 2024-03-25 | -78 | 2024-03-26 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490900 | T2 EI KESWICK-CASCADE 003/070 RPL POLE | 70Y
LC | 125724243 | 002/053 | T2 DI DELTA-MONTN GATE JCT 2/53 RPR IBWW | TABLEMTN | ETL.6750.POLE.WOOD | 2023-03-24 | 2023-03-21 | 2023-10-12 | On-time | 2024-03-20 | 160 | 2024-03-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45989493 | T2 DI DELTA-MONTN GATE JCT 2/53 RPR IBWW | ICW
LC | 125806964 | 010/141 | T2 DI DELTA MTN GT JT 10/141R RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2023-04-05 | 2023-03-21 | 2023-10-11 | On-time | 2024-03-20 | 161 | 2024-03-21 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31618690 | T2 EI DLT-MTN GT JCT-MTN 9/129R RPL STRW | 70Y
LC | 125823922 | 002/024 | T2 DI NARROWS #2 TAP 2/24L RPR GYWW | SACTO | ETL.6521.POLE.STPS | 2023-04-07 | 2023-03-21 | 2024-02-20 | On-time | 2024-03-20 | 29 | 2024-03-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45984330 | T2 DI NARROWS #2 TAP 2/24L RPR GYWW | ICW
LC | 125733974 | 004/078 | T2 EI CNTRVLLE-TABLE MTN 4/78 COMPLETED | TABLEMTN | ETL.6320.INSL | 2023-03-26 | 2023-03-26 | 2024-06-11 | Late | 2024-03-25 | -78 | 2023-09-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45990006 | T2 EI CNTRVLLE-TABLE MTN 4/78 RPR INSW | ICW
LC | 125734090 | 008/162 | T2 EI COLGATE-PALERMO 008/162 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-26 | 2023-03-26 | 2024-04-24 | Late | 2024-03-25 | -30 | 2024-03-26 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490859 | T2 EI COLGATE-PALERMO 008/162 RPL POLE | 70Y
LC | 125734101 | 016/003 | T2 EI PHILO JCT-ELK 016/003 RPR GYWW | WILLITS | ETL.7780.POLE.WOOD | 2023-03-26 | 2023-03-26 | 2024-05-02 | Late | 2024-03-25 | -38 | 2024-03-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46089633 | T2 EI PHILO JCT-ELK 016/003 RPR GYWW | ICW
LC | 125708217 | 014/007 | T2 MENDOCINO-HARTLEY 14/7 RPL POLE | WILLITS | ETL.7510.POLE.NWOD | 2023-03-22 | 2023-03-22 | 2023-08-19 | On-time | 2024-03-21 | 215 | 2023-06-22 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31640583 | T2 EI MENDOCINO-HARTLEY 14/05 RPL STRW | 70Y
LC | 125708859 | 015/297 | T2 EI COLGATE-PALERMO 015/297 RPR POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-22 | 2023-03-22 | 2023-10-27 | On-time | 2024-03-21 | 146 | 2024-03-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45985043 | T2 EI COLGATE-PALERMO 015/297 RPR POLE | ICW
LC | 125710236 | 038/176A | T2 EI RND MTN-TBL #1 38/176A BENT STEEL | TABLEMTN | ETL.6060.TOWR | 2023-03-22 | 2023-03-22 | 2024-03-18 | On-time | 2024-03-21 | 3 | 2024-03-22 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46204708 | T2 EI RND MTN-TBL #1 38/176A BNT STEEL | ICQ
LC | 125734239 | 019/007 | T2 EI FORT BRAGG-ELK 19/7 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-26 | 2023-03-26 |  | Late | 2024-03-25 |  | 2024-03-26 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487323 | T2 EI FORT BRAGG-ELK 19/07 RPL STRW | 70Y
LC | 125734360 | 013/006 | T2 EI PHILO JCT-ELK 13/6 RPR HRDW | WILLITS | ETL.7780.POLE.WOOD | 2023-03-26 | 2023-03-26 | 2024-04-30 | Late | 2024-03-25 | -36 | 2024-03-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46089634 | T2 EI PHILO JCT-ELK 13/6 RPR HRDW | ICW
LC | 125722236 | 001/011 | T2 DI LYTNVL-CVLO 1/11 COMPLETE | WILLITS | ETL.7390.INSL.CERA | 2023-03-23 | 2023-03-22 | 2023-05-22 | On-time | 2024-03-21 | 304 | 2023-09-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45709786 | T2 DI LYTNVL-CVLO 01/11 COTTER | ICW
LC | 125740190 | 055/010 | T2 DI ELK-GUALALA 55/10 RMV VEG | WILLITS | ETL.8410.POLE.WOOD | 2023-03-27 | 2023-03-22 | 2024-03-18 | On-time | 2024-03-21 | 3 | 2024-03-22 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125734456 | 009/169 | T2 EI COLGATE-PALERMO 009/169 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-26 | 2023-03-26 | 2024-04-23 | Late | 2024-03-25 | -29 | 2024-03-26 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490859 | T2 EI COLGATE-PALERMO 008/162 RPL POLE | 70Y
LC | 125734459 | 009/174 | T2 EI COLGATE-PALERMO 009/174 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-26 | 2023-03-26 | 2024-04-23 | Late | 2024-03-25 | -29 | 2024-03-26 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490859 | T2 EI COLGATE-PALERMO 008/162 RPL POLE | 70Y
LC | 125734467 | 009/173 | T2 EI COLGATE-PALERMO 009/173 RPL POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-26 | 2023-03-26 | 2024-04-23 | Late | 2024-03-25 | -29 | 2024-03-26 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490859 | T2 EI COLGATE-PALERMO 008/162 RPL POLE | 70Y
LC | 125734497 | 004/070 | T2 EI CNTRVLLE-TABLE MTN 4/70 COMPLETED | TABLEMTN | ETL.6320.POLE.WOOD | 2023-03-26 | 2023-03-26 | 2024-06-11 | Late | 2024-03-25 | -78 | 2024-03-26 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490856 | T2 EI CNTRVLLE-TABLE MTN 4/70 RPL STRW | 70Y
LC | 125734498 | 014/000 | T2 EI PHILO JCT-ELK 014/000 RPR GYWW | WILLITS | ETL.7780.POLE.NWOD | 2023-03-26 | 2023-03-26 | 2024-04-30 | Late | 2024-03-25 | -36 | 2023-09-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46089635 | T2 EI PHILO JCT-ELK 014/000 RPR GYWW | ICW
LC | 125734526 | 019/002 | T2 EI FORT BRAGG-ELK 19/02 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-26 | 2023-03-26 |  | Late | 2024-03-25 |  | 2024-03-26 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487323 | T2 EI FORT BRAGG-ELK 19/07 RPL STRW | 70Y
LC | 125742377 | 005/006 | T2 DI FORT BRAGG-ELK 005/006 RPL GYWW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-28 | 2023-03-22 | 2024-02-22 | On-time | 2024-03-21 | 28 | 2024-03-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45906981 | T2 DI FORT BRAGG-ELK 005/006 RPL GYWW | ICW
LC | 125798564 | 055/005 | T2 DI ELK-GUALALA 55/5 RPR INSW | WILLITS | ETL.8410.INSL.CERA | 2023-04-05 | 2023-03-22 | 2024-01-18 | On-time | 2024-03-21 | 63 | 2024-03-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079892 | T2 DI ELK-GUALALA 55/5 RPR INSW | ICW
LC | 125807672 | 002/022 | T2 DI SANTA YNEZ TAP 2/022 RPR SPLW | PISMOBCH | ETL.3701.INSL.NCER | 2023-04-05 | 2023-03-22 | 2023-04-21 | On-time | 2024-03-21 | 335 | 2024-03-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45765022 | T2 DI SANTA YNEZ TAP 2/022 RPR SPLW | ICW
LC | 125735631 | 011/159 | T2 DI VLLY SPRNGS-CLY 11/159 RPL STRW | VICTOR | ETL.8264.POLE.WOOD | 2023-03-27 | 2023-03-14 |  | Late | 2024-03-13 |  | 2024-03-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495594 | T2 DI VLLY SPRNGS-CLY 11/159 RPL STRW | 70Y
LC | 125735885 | 005/100 | T2 EI KESWICK-CASCADE 005/100 RPL POLE | TABLEMTN | ETL.7260.POLE.WOOD | 2023-03-27 | 2023-03-27 | 2024-06-12 | Late | 2024-03-26 | -78 | 2024-03-27 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492084 | T2 EI KESWICK-CASCADE 005/100 RPL POLE | 70Y
LC | 125736107 | 009/006 | T2 DI FORT BRAGG-ELK 9/6 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-27 | 2023-03-20 |  | Late | 2024-03-19 |  | 2023-09-20 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487732 | T2 DI FORT BRAGG-ELK 009/011 RPL POLE | 70Y
LC | 125807674 | 002/022 | T2 DI SANTA YNEZ TAP 2/022 RPL INSW | PISMOBCH | ETL.3701.INSL.NCER | 2023-04-05 | 2023-03-22 | 2024-03-06 | On-time | 2024-03-21 | 15 | 2024-03-22 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493010 | T2 DI SANTA YNEZ TAP 2/022 RPL INSW | 93I
LC | 125809589 | 001/010B | T2 DI RACETRACK TAP 01/010B RPR GYWW | VICTOR | ETL.2393.POLE.NWOD | 2023-04-06 | 2023-03-22 | 2023-10-30 | On-time | 2024-03-21 | 143 | 2024-03-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45984801 | T2 DI RACETRACK TAP 01/010B RPR GYWW | ICW
LC | 125736457 | 011/202 | T2 DI VALLEY SPRNGS #2 11/202 RPL POLE | VICTOR | ETL.9460.POLE.WOOD | 2023-03-27 | 2023-03-14 |  | Late | 2024-03-13 |  | 2024-03-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495376 | T2 DI VALLEY SPRNGS #2 11/202 RPL POLE | 70Y
LC | 125715708 | 013/272 | T2 COLGATE-PALERMO 013/272 RPL HRDW | SACTO | ETL.6500.INSL.NCER | 2023-03-23 | 2023-03-23 | 2023-10-30 | On-time | 2024-03-22 | 144 | 2024-03-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45985358 | T2 COLGATE-PALERMO 013/272 RPL HRDW | ICW
LC | 125736641 | 005/098 | T2 EI KESWICK-CASCADE 005/098 RPL POLE | TABLEMTN | ETL.7260.POLE.WOOD | 2023-03-27 | 2023-03-27 | 2024-06-12 | Late | 2024-03-26 | -78 | 2024-03-27 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492085 | T2 EI KESWICK-CASCADE 005/098 RPL POLE | 70Y
LC | 125736669 | 012/256 | T2 EI LAKEVILLE #2 012/256 RPL HRDW | LAKEVLLE | ETL.7340.INSL.NCER | 2023-03-27 | 2023-03-27 |  | Late | 2024-03-26 |  | 2024-03-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46096437 | T2 EI LAKEVILLE #2 012/256 RPL HRDW | ICW
LC | 125718571 | 015/308 | T2 EI COLGATE-PALERMO 015/308 RPR POLE | SACTO | ETL.6500.POLE.WOOD | 2023-03-23 | 2023-03-23 | 2023-10-27 | On-time | 2024-03-22 | 147 | 2024-03-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45985359 | T2 EI COLGATE-PALERMO 015/308 RPR POLE | ICW
LC | 125736951 | 012/257-GUY | T2 EI LAKEVILLE #2 012/257-GUY UNBURY | LAKEVLLE | ETL.7340.POLE.WOOD | 2023-03-27 | 2023-03-27 |  | Late | 2024-03-26 |  | 2024-03-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46096438 | T2 EI LAKEVILLE #2 012/257-GUY UNBURY | ICW
LC | 125719448 | 039/178 | T2 EI RND MTN-TBL MTN #1 39/178 INS HRDS | TABLEMTN | ETL.6060.TOWR | 2023-03-23 | 2023-03-23 | 2024-02-26 | On-time | 2024-03-22 | 25 | 2024-03-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Tower | Install | 46007982 | T2 EI RND MTN-TBL MTN #1 39/178 INS HRDS | ICQ
LC | 125737353 | 005/108 | T2 EI KESWICK-CASCADE 005/108 RPL POLE | TABLEMTN | ETL.7260.POLE.WOOD | 2023-03-27 | 2023-03-27 | 2024-06-19 | Late | 2024-03-26 | -85 | 2024-03-27 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492086 | T2 EI KESWICK-CASCADE 005/108 RPL POLE | 70Y
LC | 125737377 | 002/010 | T2 DI IONE TAP 2/10 RPR INSW | VICTOR | ETL.8253.INSL.NCER | 2023-03-27 | 2023-03-14 | 2024-04-20 | Late | 2024-03-13 | -38 | 2023-09-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45978048 | T2 DI IONE 2/10 RPR INSW | ICW
LC | 125737412 | 003/004 | T2 FULTON-HOPLAND 003/004 RPR CNDW | LAKEVLLE | ETL.6890.INSL.NCER | 2023-03-27 | 2023-03-27 |  | Late | 2024-03-26 |  | 2024-03-27 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46048921 | T2 FULTON-HOPLAND 003/004 RPR CNDW | ICW
LC | 125720586 | 039/181 | T2 EI RND MTN-TBL MTN #1 39/181 RPR GYWT | TABLEMTN | ETL.6060.TOWR | 2023-03-23 | 2023-03-23 | 2024-03-06 | On-time | 2024-03-22 | 16 | 2024-03-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46204709 | T2 EI RND MTN-TBL MTN #1 39/181 RPR GYWT | ICQ
LC | 125723887 | 039/008 | T2 DI FORT ROSS-GUALALA 39/8 RMV VEG | WILLITS | ETL.6980.POLE.WOOD | 2023-03-24 | 2023-03-23 | 2024-03-14 | On-time | 2024-03-22 | 8 | 2024-03-23 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125748285 | 041/001 | T2 DI FORT ROSS GULALA 041/001 RPR GYWW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-03-28 | 2023-03-23 | 2023-11-01 | On-time | 2024-03-22 | 142 | 2024-03-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46042591 | T2 DI FORT ROSS GULALA 041/001 RPR GYWW | ICW
LC | 126875579 | 029/176 | T2NT TMBLR-SN LIS OBISP 29/176 RPL SPLS | PISMOBCH | ETL.3960.INSL.CERA | 2023-08-21 | 2023-03-23 | 2023-10-16 | On-time | 2024-03-22 | 158 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 125737686 | 003/010 | T2 EI FULTON-HOPLAND 003/010 INS ANCW | LAKEVLLE | ETL.6890.POLE.NWOD | 2023-03-27 | 2023-03-27 |  | Late | 2024-03-26 |  | 2024-03-27 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Missing | Anchor-Wood | Install
LC | 126875937 | 032/187 | T2NT TMBLR-SN LIS OBISP 32/187 RPL SPLS | PISMOBCH | ETL.3960.INSL.NCER | 2023-08-21 | 2023-03-23 | 2024-03-12 | On-time | 2024-03-22 | 10 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 125737705 | 004/001 | T2 EI FULTON-HOPLAND 004/001 INS ANCW | LAKEVLLE | ETL.6890.POLE.NWOD | 2023-03-27 | 2023-03-27 |  | Late | 2024-03-26 |  | 2024-03-27 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Missing | Anchor-Wood | Install
LC | 125737750 | 005/109 | T2 EI KESWICK-CASCADE 005/109 RPL ANCW | TABLEMTN | ETL.7260.POLE.WOOD | 2023-03-27 | 2023-03-27 | 2024-06-19 | Late | 2024-03-26 | -85 | 2024-03-27 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35492087 | T2 EI KESWICK-CASCADE 005/109 RPL ANCW | 93E
LC | 125737758 | 004/004 | T2 EI FULTON-HOPLAND 004/004 INS ANCW | LAKEVLLE | ETL.6890.POLE.NWOD | 2023-03-27 | 2023-03-27 |  | Late | 2024-03-26 |  | 2024-03-27 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Missing | Anchor-Wood | Install
LC | 126875938 | 032/190 | T2NT TMBLR-SN LIS OBISP 32/190 RPL SPLS | PISMOBCH | ETL.3960.INSL.CERA | 2023-08-21 | 2023-03-23 | 2024-03-12 | On-time | 2024-03-22 | 10 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 126875939 | 035/203 | T2NT TMBLR-SN LIS OBISP 35/203 RPL SPLS | PISMOBCH | ETL.3960.INSL.NCER | 2023-08-21 | 2023-03-23 | 2024-03-14 | On-time | 2024-03-22 | 8 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Steel | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 125737907 | 005/006 | T2 FULTON-HOPLAND 005/006 RPL GYWW | LAKEVLLE | ETL.6890.POLE.NWOD | 2023-03-27 | 2023-03-27 |  | Late | 2024-03-26 |  | 2024-03-27 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 46048921 | T2 FULTON-HOPLAND 003/004 RPR CNDW | ICW
LC | 125737952 | 022/096B | T2 EI PTTSBRG-TSLA #2 022/096B RPR FOND | CONCORD | ETL.5520.TOWR | 2023-03-27 | 2023-03-27 | 2024-04-12 | Late | 2024-03-26 | -17 | 2024-03-27 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46008509 | T2 EI PTTSBRG-TSLA #2 022/096B RPR FOND | ICQ
LC | 126875990 | 031/184 | T2NT TMBLR-SN LIS OBISP 31/184 RPL SPLS | PISMOBCH | ETL.3960.INSL.NCER | 2023-08-21 | 2023-03-23 | 2023-10-16 | On-time | 2024-03-22 | 158 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 125738481 | 008/116 | T2 DI VLLY SPRNGS-CLY 8/116L RPL STRW | VICTOR | ETL.8264.POLE.WDPS | 2023-03-27 | 2023-03-14 |  | Late | 2024-03-13 |  | 2024-03-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493064 | T2 DI VLLY SPRNGS-CLY 8/116L RPL STRW | 70Y
LC | 125738482 | 008/116 | T2 DI VLLY SPRNGS-CLY 8/116R RPL STRW | VICTOR | ETL.8264.POLE.WDPS | 2023-03-27 | 2023-03-14 |  | Late | 2024-03-13 |  | 2024-03-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493064 | T2 DI VLLY SPRNGS-CLY 8/116L RPL STRW | 70Y
LC | 126875993 | 035/206 | T2NT TMBLR-SN LIS OBISP 35/206 RPL SPLS | PISMOBCH | ETL.3960.INSL.CERA | 2023-08-21 | 2023-03-23 | 2023-10-17 | On-time | 2024-03-22 | 157 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 125739407 | 004/091 | T2 EI CTTNWD-RD BLFF 004/091 RPL POLE | TABLEMTN | ETL.6660.POLE.WOOD | 2023-03-27 | 2023-03-27 | 2024-04-10 | Late | 2024-03-26 | -15 | 2024-03-27 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35484836 | T2 EI CTTNWD-RD BLFF 004/091 RPL POLE | 70Y
LC | 126875997 | 034/197 | T2NT TMBLR-SN LIS OBISP 034/197 RPL SPLS | PISMOBCH | ETL.3960.INSL.NCER | 2023-08-21 | 2023-03-23 | 2023-10-17 | On-time | 2024-03-22 | 157 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 126876000 | 036/208 | T2NT TMBLR-SN LIS OBISP 36/208 RPL SPLS | PISMOBCH | ETL.3960.INSL.NCER | 2023-08-21 | 2023-03-23 | 2024-03-14 | On-time | 2024-03-22 | 8 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 126876003 | 036/209 | T2NT TMBLR-SN LIS OBISP 036/209 RPL SPLS | PISMOBCH | ETL.3960.INSL.NCER | 2023-08-21 | 2023-03-23 | 2023-10-17 | On-time | 2024-03-22 | 157 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 126876062 | 036/212 | T2NT TMBLR-SN LIS OBISP 036/212 RPL SPLS | PISMOBCH | ETL.3960.INSL.CERA | 2023-08-21 | 2023-03-23 | 2023-10-17 | On-time | 2024-03-22 | 157 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 126876128 | 038/219 | T2NT TMBLR-SN LIS OBISP 38/219 RPL SPLS | PISMOBCH | ETL.3960.INSL.CERA | 2023-08-21 | 2023-03-23 | 2023-10-17 | On-time | 2024-03-22 | 157 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 126876183 | 037/218 | T2NT TMBLR-SN LIS OBISP 37/218 RPL SPLS | PISMOBCH | ETL.3960.INSL.NCER | 2023-08-21 | 2023-03-23 | 2023-10-17 | On-time | 2024-03-22 | 157 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 125740337 | 034/008 | T2 EI PHILO JCT-ELK 34/8 RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-03-27 | 2023-03-27 | 2024-05-23 | Late | 2024-03-26 | -58 | 2024-03-27 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506660 | T2 EI PHILO JCT-ELK 34/8 RPL STRW | 70Y
LC | 125740463 | 015/011 | T2 EI FORT BRAGG-ELK 015/011 RPL POLE | WILLITS | ETL.2060.POLE.WOOD | 2023-03-27 | 2023-03-27 | 2024-04-16 | Late | 2024-03-26 | -21 | 2024-03-27 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487719 | T2 DI FORT BRAGG-ELK 14/12 RPL STRW | 70Y
LC | 125740735 | 005/001 | T2 DI FORT BRAGG-ELK 5/1L RPL STRW | WILLITS | ETL.2060.POLE.WDPS | 2023-03-27 | 2023-03-27 |  | Late | 2024-03-26 |  | 2024-03-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487304 | T2 DI FORT BRAGG-ELK 5/1L RPL STRW | 70Y
LC | 125740737 | 005/001 | T2 DI FORT BRAGG-ELK 5/1C RPL STRW | WILLITS | ETL.2060.POLE.WDPS | 2023-03-27 | 2023-03-27 |  | Late | 2024-03-26 |  | 2024-03-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487304 | T2 DI FORT BRAGG-ELK 5/1L RPL STRW | 70Y
LC | 125740739 | 005/001 | T2 DI FORT BRAGG-ELK 5/1R RPL STRW | WILLITS | ETL.2060.POLE.WDPS | 2023-03-27 | 2023-03-27 |  | Late | 2024-03-26 |  | 2024-03-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487304 | T2 DI FORT BRAGG-ELK 5/1L RPL STRW | 70Y
LC | 125741049 | 010/087 | T2 EI EL DDO -MISRI FL #1 10/87 RPL INSW | SACTO | ETL.1530.INSL | 2023-03-27 | 2023-03-27 | 2024-05-01 | Late | 2024-03-26 | -36 | 2024-03-27 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35483353 | T2 EI EL DDO -MISRI FL #1 10/87 RPL INSW | 93I
LC | 125741088 | 005/083 | T2 EI CNTRVILLE-TABLE MTN 5/83 RPR INSW | TABLEMTN | ETL.6320.INSL.NCER | 2023-03-27 | 2023-03-27 | 2024-06-10 | Late | 2024-03-26 | -76 | 2024-03-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45990007 | T2 EI CNTRVILLE-TABLE MTN 5/83 RPR INSW | ICW
LC | 125742434 | 006/004 | T2 DI FORT BRAGG-ELK 006/004 RPL POLE | WILLITS | ETL.2060.POLE.WOOD | 2023-03-28 | 2023-03-22 | 2024-04-10 | Late | 2024-03-21 | -20 | 2024-03-22 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35487307 | T2 DI FORT BRAGG-ELK 006/004 RPL POLE | 70Y
LC | 126880583 | 057/315 | T2NT TMBLR-SN LIS OBISP 057/315 RPL SPLS | PISMOBCH | ETL.3960.INSL.NCER | 2023-08-22 | 2023-03-23 | 2024-03-14 | On-time | 2024-03-22 | 8 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 126880587 | 055/307 | T2NT TMBLR-SN LIS OBISP 55/307 RPL SPLS | PISMOBCH | ETL.3960.INSL.NCER | 2023-08-22 | 2023-03-23 | 2024-03-13 | On-time | 2024-03-22 | 9 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 126880600 | 055/306 | T2NT TMBLR-SN LIS OBISP 55/06 RPL SPLW | PISMOBCH | ETL.3960.INSL.NCER | 2023-08-22 | 2023-03-23 | 2024-03-13 | On-time | 2024-03-22 | 9 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 126880602 | 050/282 | T2NT TMBLR-SN LIS OBISP 50/282 RPL SPLS | PISMOBCH | ETL.3960.INSL.NCER | 2023-08-22 | 2023-03-23 | 2024-03-12 | On-time | 2024-03-22 | 10 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 126880611 | 057/313 | T2NT TMBLOR-SN LIS OBSPO 57/313 RPL SPLW | PISMOBCH | ETL.3960.INSL.CERA | 2023-08-22 | 2023-03-23 | 2024-03-14 | On-time | 2024-03-22 | 8 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 126880614 | 056/311 | T2NT TMBLR-SN LIS OBISP 56/311 RPL SPLS | PISMOBCH | ETL.3960.INSL | 2023-08-22 | 2023-03-23 | 2024-03-15 | On-time | 2024-03-22 | 7 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 126880616 | 049/280 | T2NT TMBLR-SN LIS OBISP 49/280 RPL SPLS | PISMOBCH | ETL.3960.INSL.NCER | 2023-08-22 | 2023-03-23 | 2024-03-12 | On-time | 2024-03-22 | 10 | 2024-03-23 | 638 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 74049810 | TEMBLOR-SAN LUIS OBISPO SHUNT SPLICE RPL | 93C
LC | 125743460 | 050/359 | T2 DI CARIBOU TABLE MTN 50/359 RPL SPLS | TABLEMTN | ETL.4440.INSL.CERA | 2023-03-28 | 2023-03-28 | 2024-06-08 | Late | 2024-03-27 | -73 | 2023-09-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Replace | 45895050 | T2 DI CARIBOU TABLE MTN 50/359 RPL SPLS | ICW
LC | 125724729 | 003/045 | T2 EI WEIMAR #1 3/45 RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2023-03-24 | 2023-03-24 | 2023-11-06 | On-time | 2024-03-23 | 138 | 2024-03-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481553 | T2 EI WEIMAR #1 3/45 RPL POLE | 70Y
LC | 125724925 | 003/046 | T2 EI WEIMAR #1 003/046 RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2023-03-24 | 2023-03-24 | 2023-11-05 | On-time | 2024-03-23 | 139 | 2024-03-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481557 | T2 EI WEIMAR #1 003/046 RPL POLE | 70Y
LC | 125726417 | 009/174 | T2 EI MNTA VISTA-LS GATOS 9/174 RPR IBWW | METCALF | ETL.7610.POLE.WOOD | 2023-03-24 | 2023-03-24 | 2024-02-14 | On-time | 2024-03-23 | 38 | 2024-03-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45999084 | T2 EI MNTA VISTA-LS GATOS 9/174 RPR IBWW | ICW
LC | 125726475 | 002/041 | T2 EI WEIMAR #1 2/041 RPR JMPW | SACTO | ETL.7560.INSL.NCER | 2023-03-24 | 2023-03-24 | 2023-04-23 | On-time | 2024-03-23 | 335 | 2023-09-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45734983 | T2 EI WEIMAR #1 -_002/041 RPR JMPW | ICW
LC | 125746306 | 001/000 | T2 DI FORT BRAGG-ELK 001/000 RPL INSW | WILLITS | ETL.2060.INSL.CERA | 2023-03-28 | 2023-03-27 | 2024-04-08 | Late | 2024-03-26 | -13 | 2024-03-27 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35487137 | T2 DI FORT BRAGG-ELK 001/000 RPL INSW | 93I
LC | 125726674 | 031/152 | T2 EI RD MTN-TBL MTN #2 031/152 RPR GYWS | TABLEMTN | ETL.6070.TOWR | 2023-03-24 | 2023-03-24 | 2023-10-26 | On-time | 2024-03-23 | 149 | 2024-03-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45989497 | T2 EI RD MTN-TBL MTN #2 031/152 RPR GYWS | ICS
LC | 125746850 | 007/000 | T2 DI FORT BRAGG-ELK 7/0L CANCEL | WILLITS | ETL.2060.POLE.STPS | 2023-03-28 | 2023-03-23 |  | Late | 2024-03-22 |  | 2024-03-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46089636 | T2 DI FORT BRAGG-ELK 7/0L RPR ANCW | ICW
LC | 125747234 | 003/007 | T2 DI FORT BRAGG-ELK 003/007 COTTER | WILLITS | ETL.2060.INSL.NCER | 2023-03-28 | 2023-03-27 |  | Late | 2024-03-26 |  | 2024-03-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46089637 | T2 DI FORT BRAGG-ELK 003/007 COTTER | ICW
LC | 125747331 | 001/006 | T2 DI LYTNVL COVELO 01/006 COA | WILLITS | ETL.7390.POLE.NWOD | 2023-03-28 | 2023-03-22 |  | Late | 2024-03-21 |  | 2024-03-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46219492 | T2 DI LYTNVL COVELO 01/006 REGRADE | ICW
LC | 125748043 | 011/006 | T2 DI FORT BRAGG-ELK-11/06 RPR INSW | WILLITS | ETL.2060.INSL.CERA | 2023-03-28 | 2023-03-27 | 2024-04-12 | Late | 2024-03-26 | -17 | 2024-03-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46089638 | T2 DI FORT BRAGG-ELK-11/06 RPR INSW | ICW
LC | 125726682 | 001/013 | T2 BALCH-SANGER 01/13 RPL INSS | FRESNO | ETL.1050.INSL.CERA | 2023-03-24 | 2023-03-24 | 2023-10-18 | On-time | 2024-03-23 | 157 | 2024-03-24 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671078 | T2 BALCH-SANGER 01/13 RPL INSS | 93K
LC | 125728528 | 002/040 | T2 EI WEIMAR #1 -_002/040 COTTER | SACTO | ETL.7560.INSL.NCER | 2023-03-24 | 2023-03-24 | 2023-09-26 | On-time | 2024-03-23 | 179 | 2024-03-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45985045 | T2 EI WEIMAR #1 -_002/040 COTTER | ICW
LC | 125748124 | 000/007 | T2 DI HALSY-PLCR 0/7 RPR INSW | SACTO | ETL.6990.INSL.NCER | 2023-03-28 | 2023-03-20 | 2024-04-30 | Late | 2024-03-19 | -42 | 2024-03-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45984329 | T2 DI HALSY-PLCR 0/7 RPR INSW | ICW
LC | 125728978 | 000/013 | T2 EI WEIMAR #1 000/013 RPL ANCW | SACTO | ETL.7560.POLE.NWOD | 2023-03-24 | 2023-03-24 | 2023-04-23 | On-time | 2024-03-23 | 335 | 2024-03-24 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35505894 | T2 EI WEIMAR#1 000/013 RPL ANCW-POST EST | 93E
LC | 125748211 | 008/006 | T2 DI LAKEVILLE #1 008/006 RPR INSW | LAKEVLLE | ETL.7360.INSL.NCER | 2023-03-28 | 2023-03-24 | 2024-05-13 | Late | 2024-03-23 | -51 | 2024-03-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46043054 | T2 DI LAKEVILLE #1 008/006 RPR INSW | ICW
LC | 125729520 | 000/015 | T2 EI WEIMAR #1 -_000/015 RPR JMPW | SACTO | ETL.7560.INSL.NCER | 2023-03-24 | 2023-03-24 | 2023-11-05 | On-time | 2024-03-23 | 139 | 2024-03-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45985046 | T2 EI WEIMAR #1 -_000/015 RPR JMPW | ICW
LC | 125730354 | 052/004 | T2 DI ELK-GUALALA 52/4 RPR IBWW | WILLITS | ETL.8410.POLE.WOOD | 2023-03-24 | 2023-03-24 | 2024-01-10 | On-time | 2024-03-23 | 73 | 2024-03-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45711302 | T2 DI ELK-GUALALA 52/4 RPR IBWW | ICW
LC | 125748400 | 003/002 | T2 DI FORT BRAGG-ELK 008/010 RPR GYWW | WILLITS | ETL.2060.POLE.NWOD | 2023-03-28 | 2023-03-27 |  | Late | 2024-03-26 |  | 2023-09-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46089639 | T2 DI FORT BRAGG-ELK 008/010 RPR GYWW | ICW
LC | 125731272 | 002/026 | T2 DI MONTA VISTA-BURNS 2/26 RPL PL | MOSSLNDG | ETL.7590.POLE.WOOD | 2023-03-25 | 2023-03-24 | 2024-03-10 | On-time | 2024-03-23 | 13 | 2024-03-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505602 | T2 DI MONTA VISTA-BURNS 2/26 RPL PL | 70Y
LC | 125731687 | 002/028 | T2 DI MONTA VISTA-BURNS 2/28 COTTER | MOSSLNDG | ETL.7590.INSL.NCER | 2023-03-25 | 2023-03-24 | 2023-04-18 | On-time | 2024-03-23 | 340 | 2023-06-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45713819 | T2 DI MONTA VISTA-BURNS 2/28 COTTER | ICW
LC | 125731840 | 002/028 | T2 DI MONTA VISTA-BURNS 2/28 RPR GYWW | MOSSLNDG | ETL.7590.POLE.WOOD | 2023-03-25 | 2023-03-24 | 2023-04-18 | On-time | 2024-03-23 | 340 | 2024-03-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45735620 | T2 DI MONTA VISTA-BURNS 2/28 RPR GYWW | ICW
LC | 125733119 | 008/112 | T2 DI VLY SPRNGS-CLY 8/112 COTTER | VICTOR | ETL.8264.INSL.NCER | 2023-03-25 | 2023-03-24 | 2023-05-08 | On-time | 2024-03-23 | 320 | 2023-09-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45727410 | T2 DI VLY SPRNGS-CLY 8/112 COTTER | ICW
LC | 125740240 | 052/006 | T2 DI ELK-GUALALA 52/6 CANCEL | WILLITS | ETL.8410.POLE.WOOD | 2023-03-27 | 2023-03-24 | 2024-03-14 | On-time | 2024-03-23 | 9 | 2024-03-24 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125748509 | 005/021 | T2 DI MONTA VISTA-JEFF #2 5/21 RPL INSS | METCALF | ETL.5230.INSL | 2023-03-28 | 2023-03-24 | 2024-03-18 | On-time | 2024-03-23 | 5 | 2024-03-24 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674006 | T2 DI MONTA VISTA-JEFF #2 RPL INSS IN 7 | 93K
LC | 125756852 | 002/027 | T2 DI MONTA VISTA-BURNS 2/27 RPR GYWW | MOSSLNDG | ETL.7590.POLE.NWOD | 2023-03-29 | 2023-03-24 | 2024-02-29 | On-time | 2024-03-23 | 23 | 2024-03-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46016590 | T2 DI MONTA VISTA-BURNS 2/27 RPR GYWW | ICW
LC | 125820199 | 007/114 | T2 DI DELTA-MTN GT 7/114 RPR ANCW | TABLEMTN | ETL.6750.POLE.WOOD | 2023-04-07 | 2023-03-24 | 2023-10-11 | On-time | 2024-03-23 | 164 | 2024-03-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45989488 | T2 DI DELTA-MTN GT 7/114 RPR ANCW | ICW
LC | 125867021 | 012/159 | T2 DI DELTA-MTN GATE JCT 12/159 RPR CRSW | TABLEMTN | ETL.6750.POLE.WOOD | 2023-04-11 | 2023-03-24 | 2023-10-10 | On-time | 2024-03-23 | 165 | 2024-03-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45989490 | T2 DI DELTA-MTN GATE JCT 12/159 RPR CRSW | ICW
LC | 125731085 | 005/040B | T2 EI TRINITY-COTTONWD 5/40B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-03-25 | 2023-03-25 | 2024-02-20 | On-time | 2024-03-24 | 33 | 2023-09-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46191130 | T2 EI TRINITY-COTTONWD 5/40B RPR GYWW | ICW
LC | 125731190 | 005/040C | T2 EI TRINITY-COTTONWD 5/40C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-03-25 | 2023-03-25 | 2024-02-20 | On-time | 2024-03-24 | 33 | 2023-09-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46191131 | T2 EI TRINITY-COTTONWD 5/40C RPR GYWW | ICW
LC | 125748830 | 007/040 | T2 DI IGNACIO-ALTO--07/40 RPL INSS | LAKEVLLE | ETL.7150.INSL.CERA | 2023-03-28 | 2023-03-20 |  | Late | 2024-03-19 |  | 2024-03-20 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31677490 | DI IGNACIO-ALTO- RPL INSS IN 2 TWRS. | 93K
LC | 125748831 | 007/040 | T2 DI IGNACIO-SAN RAFAL#1-07/40 RPL INSS | LAKEVLLE | ETL.1850.INSL | 2023-03-28 | 2023-03-20 |  | Late | 2024-03-19 |  | 2024-03-20 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31677641 | DI IGNACIO-SAN RAFAL#1-07/40 RPL INSS | 93K
LC | 125731464 | 005/041 | T2 EI TRINITY-COTTONWOOD 5/41L RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-03-25 | 2023-03-25 | 2024-02-20 | On-time | 2024-03-24 | 33 | 2023-09-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45989278 | T2 EI TRINITY-COTTONWOOD 5/41L RPR GYWW | ICW
LC | 125748895 | 002/005 | T2 DI FORT BRGG-ELK 2/5 ANTI SPLIT | WILLITS | ETL.2060.POLE.WOOD | 2023-03-28 | 2023-03-23 | 2024-04-10 | Late | 2024-03-22 | -19 | 2024-03-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46089491 | T2 DI FORT BRGG-ELK 2/5 ANTI SPLIT | ICW
LC | 125748960 | 012/096 | T2 DI TIGER CRK-ELCTRA 12/96 RPL INSS | VICTOR | ETL.5780.INSL | 2023-03-28 | 2023-03-27 |  | Late | 2024-03-26 |  | 2024-03-27 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671227 | T2 DI TIGER CRK-ELCTRA 12/96 RPL INSS | 93K
LC | 125731870 | 012/301 | T2 EI COLGATE-GRSS VALLEY 12/301 RMV VEG | SACTO | ETL.6490.POLE.NWOD | 2023-03-25 | 2023-03-25 | 2024-03-18 | On-time | 2024-03-24 | 6 | 2024-03-25 | 564 | TLV | CREW | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125749623 | 006/102 | T2 CNTRVLLE-TABLE MTN 6/102 RPL STRW | TABLEMTN | ETL.6320.POLE.WOOD | 2023-03-29 | 2023-03-29 | 2024-06-10 | Late | 2024-03-28 | -74 | 2024-03-29 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491469 | T2 CNTRVLLE-TABLE MTN 6/102 RPL STRW | 70Y
LC | 125732338 | 012/109 | T2 EI EL DRD-MSSR FLT #1 12/109 INS DMPS | SACTO | ETL.1530.INSL | 2023-03-25 | 2023-03-25 | 2023-09-25 | On-time | 2024-03-24 | 181 | 2024-03-25 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 45989393 | T2 EI EL DRD-MSSR FLT #1 12/109 INS DMPS | ICS
LC | 125750573 | 005/054 | T2 EI GOLD HILL #1 -_005/054 RPR STRW | SACTO | ETL.6950.POLE.WOOD | 2023-03-29 | 2023-03-29 | 2024-04-03 | Late | 2024-03-28 | -6 | 2024-03-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45993623 | T2 EI GOLD HILL #1 -_005/054 RPR STRW | ICW
LC | 125750708 | 008/150 | T2 COLGATE-PALERMO-8/150 RPR INSW | SACTO | ETL.6500.INSL.NCER | 2023-03-29 | 2023-03-29 | 2024-04-17 | Late | 2024-03-28 | -20 | 2024-03-29 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45993515 | T2 COLGATE-PALERMO-8/150 RPR INSW | ICS
LC | 125732381 | 012/281 | T2 EI DRM-GRSS VLLY-WIMR 12/281 RPR GYWW | SACTO | ETL.6760.POLE.STPS | 2023-03-25 | 2023-03-25 | 2024-01-10 | On-time | 2024-03-24 | 74 | 2024-03-25 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45993514 | T2 EI DRM-GRSS VLLY-WIMR 12/281 RPR GYWW | ICS
LC | 125750927 | 009/117 | T2 DI DVDE-CBRLL #1 9/117 RPL POLE | PISMOBCH | ETL.1380.POLE.WOOD | 2023-03-29 | 2023-03-16 | 2024-06-21 | Late | 2024-03-15 | -98 | 2024-03-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507494 | T2 DI DVDE-CBRLL #1 9/117 RPL POLE | 70Y
LC | 125751004 | 024/005B | T2 EI PHILO JCT-ELK 24/5B RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-03-29 | 2023-03-29 |  | Late | 2024-03-28 |  | 2024-03-29 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491330 | T2 EI PHILO JCT-ELK 24/5A RPL STRW | 70Y
LC | 125732442 | 012/300 | T2 EI COLGAT-GRASS VALLY 12/300 INS DMPW | SACTO | ETL.6490.INSL | 2023-03-25 | 2023-03-25 | 2023-09-26 | On-time | 2024-03-24 | 180 | 2024-03-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 45990062 | T2 EI COLGAT-GRASS VALLY 12/300 INS DMPW | ICW
LC | 125732780 | 003/023A | T2 EI OLEUM N TWR-CHRSTIE 3/23A RPL POLE | CONCORD | ETL.3180.POLE.WOOD | 2023-03-25 | 2023-03-25 | 2024-03-19 | On-time | 2024-03-24 | 5 | 2024-03-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491217 | T2 EI OLEUM N TWR-CHRSTIE 3/23A RPL POLE | 70Y
LC | 125732907 | 009/065 | T2 EI MORAGA-SAN LEANDRO #1 9/65 BNT STL | CONCORD | ETL.2770.TOWR | 2023-03-25 | 2023-03-25 | 2024-01-22 | On-time | 2024-03-24 | 62 | 2024-03-25 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008508 | T2 EI MORAGA-SAN LEANDRO #1 9/65 BNT STL | ICQ
LC | 125732908 | 009/065 | T2 EI MORAGA-SAN LEANDRO #1 9/65 RMV VEG | CONCORD | ETL.2770.TOWR | 2023-03-25 | 2023-03-25 | 2024-02-23 | On-time | 2024-03-24 | 30 | 2024-03-25 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation-Tower | Cage Clearing
LC | 125733137 | 011/105 | T2 EI L DRDO MSRI FLT #2 11/105 INS DMPS | SACTO | ETL.1540.INSL.NCER | 2023-03-25 | 2023-03-25 | 2023-09-25 | On-time | 2024-03-24 | 181 | 2024-03-25 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 45989391 | T2 EI L DRDO MSRI FLT #2 11/105 INS DMPS | ICS
LC | 125733220 | 011/105 | T2 EI EL DRDO-MSRI FL #1 11/105 INS DMPS | SACTO | ETL.1530.INSL | 2023-03-25 | 2023-03-25 | 2023-09-25 | On-time | 2024-03-24 | 181 | 2024-03-25 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 45989392 | T2 EI EL DRDO-MSRI FL #1 11/105 INS DMPS | ICS
LC | 126488396 | 003/023B | T2 EI OLEUM N TWR-CHRSTIE 3/23B RPL POLE | CONCORD | ETL.3180.POLE.WOOD | 2023-06-30 | 2023-03-25 | 2024-03-19 | On-time | 2024-03-24 | 5 | 2024-03-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491217 | T2 EI OLEUM N TWR-CHRSTIE 3/23A RPL POLE | 70Y
LC | 125733899 | 020/000 | T2 EI FRT BRG-ELK 20/0 COTTER | WILLITS | ETL.2060.INSL.NCER | 2023-03-26 | 2023-03-26 | 2024-03-11 | On-time | 2024-03-25 | 14 | 2024-03-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46089632 | T2 EI FRT BRG-ELK 20/0 COTTER | ICW
LC | 125733925 | 012/106 | T2 EI SN LS OBSPO-CYUCS 12/106 RPL ANCW | PISMOBCH | ETL.9090.POLE.WOOD | 2023-03-26 | 2023-03-26 | 2024-01-10 | On-time | 2024-03-25 | 75 | 2024-03-26 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35495497 | T2 EI SN LS OBSPO-CYUCS 12/106 RPL ANCW | 93E
LC | 125733950 | 012/106 | T2 EI SN LS OBISPO-CYUCS 12/106 INS DMPW | PISMOBCH | ETL.9090.INSL.CERA | 2023-03-26 | 2023-03-26 | 2024-01-10 | On-time | 2024-03-25 | 75 | 2024-03-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46088341 | T2 EI SN LS OBISPO-CYUCS 12/106 INS DMPW | ICW
LC | 125734183 | 009/001 | T2 EI FULTON-HOPLAND 009/001 RPR GYWS | LAKEVLLE | ETL.6890.POLE.NWOD | 2023-03-26 | 2023-03-26 | 2023-11-09 | On-time | 2024-03-25 | 137 | 2024-03-26 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46007983 | T2 EI FULTON-HOPLAND 009/001 RPR GYWS | ICS
LC | 125752316 | 004/070 | T2 EI COLGATE-PALERMO 4/70 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2023-03-29 | 2023-03-29 | 2024-04-23 | Late | 2024-03-28 | -26 | 2024-03-29 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491466 | T2 EI COLGATE-PALERMO 4/70 RPL STRW | 70Y
LC | 125752320 | 004/071 | T2 EI COLGATE-PALERMO 4/71 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2023-03-29 | 2023-03-29 | 2024-04-23 | Late | 2024-03-28 | -26 | 2024-03-29 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491468 | T2 EI COLGATE-PALERMO 4/71 RPL STRW | 70Y
LC | 125752932 | 005/116 | T2 EI KESWICK-CASCADE 05/116 RPL POLE | TABLEMTN | ETL.7260.POLE.WOOD | 2023-03-29 | 2023-03-29 |  | Late | 2024-03-28 |  | 2024-03-29 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35492088 | T2 EI KESWICK-CASCADE 05/116 RPL POLE | 70Y
LC | 125734201 | 004/044 | T2 EI MONTA VISTA-BURNS 4/44 RPR GYWW | MOSSLNDG | ETL.7590.POLE.WOOD | 2023-03-26 | 2023-03-26 | 2024-02-28 | On-time | 2024-03-25 | 26 | 2024-03-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46016591 | T2 EI MONTA VISTA-BURNS 4/44 RPR GYWW | ICW
LC | 125734238 | 019/008 | T2 EI FORT BRAGG-ELK 19/8 RMV VEG | WILLITS | ETL.2060.POLE.WOOD | 2023-03-26 | 2023-03-26 | 2024-03-22 | On-time | 2024-03-25 | 3 | 2024-03-26 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125734394 | 008/057 | T2 EI SN LS OBISPO-CAYUCOS 8/57 INS DMPW | PISMOBCH | ETL.9090.INSL | 2023-03-26 | 2023-03-26 | 2024-01-12 | On-time | 2024-03-25 | 73 | 2024-03-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46088342 | T2 EI SN LS OBISPO-CAYUCOS 8/57 INS DMPW | ICW
LC | 125734398 | 008/055 | T2 EI SN LS OBISPO-CAYUCOS 8/55 INS DMPW | PISMOBCH | ETL.9090.INSL.NCER | 2023-03-26 | 2023-03-26 | 2024-01-11 | On-time | 2024-03-25 | 74 | 2024-03-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46088407 | T2 EI SN LS OBISPO-CAYUCOS 8/55 INS DMPW | ICW
LC | 125754393 | 005/004 | T2 DI LAYTONVILLE-COVELO 5/4R RPL POLE | WILLITS | ETL.7390.POLE.WDPS | 2023-03-29 | 2023-03-27 |  | Late | 2024-03-26 |  | 2024-03-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491306 | T2 DI LAYTONVILLE-COVELO 5/4R RPL POLE | 70Y
LC | 125754626 | 019/012 | T2 DI FORT BRAGG-ELK 019/012 RPL POLE | WILLITS | ETL.2060.POLE.WOOD | 2023-03-29 | 2023-03-10 | 2024-03-11 | Late | 2024-03-09 | -2 | 2024-03-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486931 | T2 DI FORT BRAGG-ELK 019/012 RPL POLE | 70Y
LC | 125754684 | 005/004 | T2 DI LAYTONVILLE-COVELO 005/004 COTTER | WILLITS | ETL.7390.INSL.NCER | 2023-03-29 | 2023-03-27 |  | Late | 2024-03-26 |  | 2024-03-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46219491 | T2 DI LAYTONVILLE-COVELO 005/004 COTTER | ICW
LC | 125734614 | 014/316 | T2 EI DRUM-GRSS VLLY-WMR 14/316 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2023-03-26 | 2023-03-26 | 2023-09-07 | On-time | 2024-03-25 | 200 | 2024-03-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45982666 | T2 EI DRUM-GRSS VLLY-WMR 14/316 RPR POLE | ICW
LC | 125734663 | 018/004 | T2 EI FORT BRAGG-ELK 18/04 COMPLETE | WILLITS | ETL.2060.POLE.WOOD | 2023-03-26 | 2023-03-26 | 2024-03-07 | On-time | 2024-03-25 | 18 | 2024-03-26 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487325 | T2 EI FORT BRAGG-ELK 18/04 RPL STRW | 70Y
LC | 125736296 | 010/094 | T2 EI ELDRDO-MSRI FLT #1 10/94 INS DMPS | SACTO | ETL.1530.INSL | 2023-03-27 | 2023-03-27 | 2023-09-28 | On-time | 2024-03-26 | 180 | 2024-03-27 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 45990060 | T2 EI ELDRDO-MSRI FLT #1 10/94 INS DMPS | ICS
LC | 125736312 | 010/094 | T2 EI ELDRDO-MSRI FLT #2 10/94 INS DMPS | SACTO | ETL.1540.INSL | 2023-03-27 | 2023-03-27 | 2023-09-28 | On-time | 2024-03-26 | 180 | 2024-03-27 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 45990061 | T2 EI ELDRDO-MSRI FLT #2 10/94 INS DMPS | ICS
LC | 125736583 | 053/474 | T2 EI RND MTN-CTNWD #3 053/474 RPR GATE | TABLEMTN | ETL.5650.TOWR | 2023-03-27 | 2023-03-27 | 2023-12-28 | On-time | 2024-03-26 | 89 | 2024-03-27 | 932 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Fence / Gate | Repair
LC | 125736773 | 013/116 | T2 EI SN LS OBSPO-CYCS -_13/116 RPL ANCW | PISMOBCH | ETL.9090.POLE.WOOD | 2023-03-27 | 2023-03-27 | 2024-01-10 | On-time | 2024-03-26 | 76 | 2024-03-27 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35495498 | T2 EI SN LS OBSPO-CYCS -_13/116 RPL ANCW | 93E
LC | 125756533 | 008/012 | T2 DI FORT BRAGG-ELK 8/12 RPL POLE | WILLITS | ETL.2060.POLE.WOOD | 2023-03-29 | 2023-03-20 |  | Late | 2024-03-19 |  | 2024-03-20 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35537185 | T2 DI FORT BRAGG-ELK 8/12 RPL POLE | 70Y
LC | 125756535 | 013/000 | T2 DI LAYTONVILLE-WLLTS 13/0 RPR STRW | WILLITS | ETL.8360.POLE.WOOD | 2023-03-29 | 2023-03-20 |  | Late | 2024-03-19 |  | 2024-03-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45988995 | T2 DI LAYTONVILLE-WLLTS 13/0 RPR STRW | ICW
LC | 125737335 | 000/016 | T2 EI WEIMAR #1 - _000/016 RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2023-03-27 | 2023-03-27 | 2023-11-05 | On-time | 2024-03-26 | 142 | 2024-03-27 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481546 | T2 EI WEIMAR #1 - _000/016 RPL POLE | 70Y
LC | 125756639 | 021/012 | T2 DI LTNVL- WILLTS 21/12 RPL POLE | WILLITS | ETL.8360.POLE.WOOD | 2023-03-29 | 2023-03-29 |  | Late | 2024-03-28 |  | 2024-03-29 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35537186 | T2 DI LTNVL- WILLTS 21/12 RPL POLE | 70Y
LC | 125737532 | 017/127 | T2 EI CAYUCOS-CAMBRIA -_17/127 RPL INS | PISMOBCH | ETL.8560.INSL.NCER | 2023-03-27 | 2023-03-27 | 2024-03-11 | On-time | 2024-03-26 | 15 | 2024-03-27 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35513605 | T2 DI CAYUCOS CMBRA 16/120 RPL INSW | 93I
LC | 125756751 | 012/004 | T2 DI FORT BRAGG-ELK 12/4 COTTER | WILLITS | ETL.2060.INSL.CERA | 2023-03-29 | 2023-03-29 |  | Late | 2024-03-28 |  | 2024-03-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46089741 | T2 DI FORT BRAGG-ELK 12/4 COTTER | ICW
LC | 125737551 | 009/070A | T2 EI TRINITY-COTTONWOOD 9/70A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-03-27 | 2023-03-27 | 2024-02-20 | On-time | 2024-03-26 | 35 | 2023-09-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45996407 | T2 EI TRINITY-COTTONWOOD 9/70A RPR GYWW | ICW
LC | 125737616 | 040/183 | T2 EI RD MTN-TBL MTN #1 040/183 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2023-03-27 | 2023-03-27 | 2024-03-08 | On-time | 2024-03-26 | 18 | 2024-03-27 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Ground Wire-Tower | Replace | 46007986 | T2 EI RD MTN-TBL MTN #1 040/183 RPR GYWS | ICS
LC | 125737621 | 017/126 | T2 EI CAYUCOS-CAMBRIA -_017/126 RPL INSW | PISMOBCH | ETL.8560.INSL.NCER | 2023-03-27 | 2023-03-27 | 2024-03-11 | On-time | 2024-03-26 | 15 | 2024-03-27 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35513605 | T2 DI CAYUCOS CMBRA 16/120 RPL INSW | 93I
LC | 125737688 | 004/066 | T2 EI WEIMAR #1 004/066 RPL INSW | SACTO | ETL.7560.INSL.NCER | 2023-03-27 | 2023-03-27 | 2023-11-06 | On-time | 2024-03-26 | 141 | 2024-03-27 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35481562 | T2 EI WEIMAR #1 004/066 RPL INSW | 93I
LC | 125758002 | 024/008 | T2 EI PHILO JCT-ELK 024/008 RPL INSW | WILLITS | ETL.7780.INSL.CERA | 2023-03-30 | 2023-03-30 | 2024-06-21 | Late | 2024-03-29 | -84 | 2024-03-30 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35491966 | T2 EI PHILO JCT-ELK 024/008 RPL INS | 93I
LC | 125758099 | 001/022 | T2 EI KESWICK-CASCADE 01/22 RPL POLE | TABLEMTN | ETL.7260.POLE.WOOD | 2023-03-30 | 2023-03-30 | 2024-06-05 | Late | 2024-03-29 | -68 | 2024-03-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35492089 | T2 EI KESWICK-CASCADE 01/22 RPL POLE | 70Y
LC | 125737809 | 010/245 | T2 EI COLGATE-GRASS VLLY 10/245 RPL POLE | SACTO | ETL.6490.POLE.WOOD | 2023-03-27 | 2023-03-27 | 2024-03-19 | On-time | 2024-03-26 | 7 | 2024-03-27 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491968 | T2 EI COLGATE-GRASS VLLY 10/245 RPL POLE | 70Y
LC | 125737811 | 017/125 | T2 EI CAYUCOS-CAMBRIA -_017/125 MASTIC | PISMOBCH | ETL.8560.POLE.NWOD | 2023-03-27 | 2023-03-27 | 2024-01-14 | On-time | 2024-03-26 | 72 | 2024-03-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088474 | T2 EI CAYUCOS-CAMBRIA -_017/125 MASTIC | ICW
LC | 125738075 | 009/070C | T2 EI TRINITY-COTTONWOOD 9/70C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-03-27 | 2023-03-27 | 2024-02-20 | On-time | 2024-03-26 | 35 | 2023-09-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46191126 | T2 EI TRINITY-COTTONWOOD 9/70C RPR GYWW | ICW
LC | 125739184 | 004/090 | T2 EI CTTNWD-RD BLFF 004/090 RPL INSW | TABLEMTN | ETL.6660.INSL.NCER | 2023-03-27 | 2023-03-27 | 2023-06-05 | On-time | 2024-03-26 | 295 | 2024-03-27 | 508 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31641021 | T2 EI CTTNWD-RD BLFF 004/090 RPL INSW | 93I
LC | 125739243 | 040/185 | T2 EI RD MTN-TBL MTN #1 040/185 RPL GUYT | TABLEMTN | ETL.6060.TOWR | 2023-03-27 | 2023-03-27 | 2023-05-23 | On-time | 2024-03-26 | 308 | 2023-06-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Replace | 45717915 | T2 EI RD MTN-TBL MTN #1 040/185 RPL GUYT | ICS
LC | 125759553 | 014/006 | T2 EI FORT BRAGG-ELK - 014/006 RPL POLE | WILLITS | ETL.2060.POLE.WOOD | 2023-03-30 | 2023-03-30 | 2024-04-10 | Late | 2024-03-29 | -12 | 2024-03-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487925 | T2 DI FORT BRAGG-ELK 14/3 RPL STRW | 70Y
LC | 125759727 | 022/092 | T2 DI DIABLO GATES#1 22/92 RPR SHIELD | PISMOBCH | ETL.5960.TOWR | 2023-03-30 | 2023-03-20 | 2024-04-08 | Late | 2024-03-19 | -20 | 2024-03-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46078914 | T2 DI DIABLO GATES#1 22/92 RPR SHIELD | ICS
LC | 125739568 | 004/092 | T2 EI CTTNWD-RD BLFF 004/092 RPL INSW | TABLEMTN | ETL.6660.INSL.NCER | 2023-03-27 | 2023-03-27 | 2023-06-05 | On-time | 2024-03-26 | 295 | 2024-03-27 | 508 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31641021 | T2 EI CTTNWD-RD BLFF 004/090 RPL INSW | 93I
LC | 125739893 | 000/012 | T2 DI FORT BRAGG-ELK 000/012 RPL INSW | WILLITS | ETL.2060.INSL.CERA | 2023-03-27 | 2023-03-27 | 2023-08-09 | On-time | 2024-03-26 | 230 | 2023-09-27 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31641020 | T2 DI FORT BRAGG-ELK 000/012 RPL INSW | 93I
LC | 125739979 | 015/137 | T2 EI SN LUIS OBSP-CYCS_015/137 RPL ANCW | PISMOBCH | ETL.9090.POLE.WDPS | 2023-03-27 | 2023-03-27 | 2024-01-10 | On-time | 2024-03-26 | 76 | 2024-03-27 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35495583 | T2 EI SN LUIS OBSP-CYCS_015/137 RPL ANCW | 93E
LC | 125759972 | A015/328 | T2 EI SALINAS-LAURELES A015/328 RPR POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-03-30 | 2023-03-30 | 2024-04-25 | Late | 2024-03-29 | -27 | 2024-03-30 | 630 | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081070 | T2 EI SALINAS-LAURELES A015/328 RPR POLE | ICW
LC | 125760145 | 024/009 | T2 EI PHILO JCT-ELK 024/009 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-03-30 | 2023-03-30 | 2024-05-20 | Late | 2024-03-29 | -52 | 2024-03-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35491964 | T2 EI PHILO JCT-ELK 024/009 RPL POLE | 70Y
LC | 125739984 | 028/004 | T2 EI GOLD HILL #1 028/004 RPR POLE | VICTOR | ETL.6950.POLE.WOOD | 2023-03-27 | 2023-03-27 | 2024-03-20 | On-time | 2024-03-26 | 6 | 2024-03-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45990636 | T2 EI GOLD HILL #1 028/004 RPR POLE | ICW
LC | 125746702 | 001/000 | T2 DI MDCNO-PHLO JT-HPLND 1/0 RPL INSWT2 | WILLITS | ETL.7520.INSL.NCER | 2023-03-28 | 2023-03-27 | 2023-06-22 | On-time | 2024-03-26 | 278 | 2023-06-27 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31641243 | T2 DI MDCNO-PHLO JT-HPLND 1/0 RPL INSW | 93I
LC | 125760475 | 016/301 | T2 EI FULTON-MMOLINO-COT 16/301 RPL HRDW | LAKEVLLE | ETL.6910.POLE.WOOD | 2023-03-30 | 2023-03-30 |  | Late | 2024-03-29 |  | 2024-03-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46044394 | T2 EI FULTON-MMOLINO-COT 16/301 RPL HRDW | ICW
LC | 125748045 | 011/006 | T2 DI FORT BRAGG-ELK-11/06 RMV VEG | WILLITS | ETL.2060.POLE.WOOD | 2023-03-28 | 2023-03-27 | 2024-03-19 | On-time | 2024-03-26 | 7 | 2024-03-27 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125748177 | 009/072 | T2 DI TGR CRK-VLY SPRNGS 09/72 RPL INSS | VICTOR | ETL.5790.INSL.CERA | 2023-03-28 | 2023-03-27 | 2024-01-24 | On-time | 2024-03-26 | 62 | 2024-03-27 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671712 | T2 DI TGR CRK-VLY SPRNGS RPL INSS 2 LSTS | 93K
LC | 125760682 | 016/300 | T2 EI FULTON-MOLINO-COTT 16/300 RPR IBWW | LAKEVLLE | ETL.6910.POLE.WOOD | 2023-03-30 | 2023-03-30 |  | Late | 2024-03-29 |  | 2024-03-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 46044393 | T2 EI FULTON-MOLINO-COTT 16/300 RPR IBWW | ICW
LC | 125760684 | 010/002 | T2 EI FULTON-HOPLAND 010/002 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-03-30 | 2023-03-30 |  | Late | 2024-03-29 |  | 2024-03-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace
LC | 125748470 | 010/004 | T2 DI LAKEVILLE #1 10/04 RPR GYWW | LAKEVLLE | ETL.7360.POLE.WOOD | 2023-03-28 | 2023-03-27 | 2023-11-02 | On-time | 2024-03-26 | 145 | 2024-03-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46043057 | T2 DI LAKEVILLE #1 10/04 RPR GYWW | ICW
LC | 125756472 | 004/001 | T2 DI FORT BRAGG-ELK 4/1 RPR IBWW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-29 | 2023-03-27 | 2023-08-09 | On-time | 2024-03-26 | 230 | 2023-09-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45714422 | T2 DI FORT BRAGG-ELK 4/1 RPR IBWW | ICW
LC | 125761340 | 003/009A | T2 EI CLEAR LAKE-HOPLAND 3/9A RPL STRW | WILLITS | ETL.6390.POLE.WOOD | 2023-03-30 | 2023-03-30 |  | Late | 2024-03-29 |  | 2023-09-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487153 | T2 EI CLEAR LAKE-HOPLAND 3/9A RPL STRW | 70Y
LC | 125761373 | 008/152 | T2 COLGATE-PALERMO 8/152 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2023-03-30 | 2023-03-30 | 2024-04-17 | Late | 2024-03-29 | -19 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45993633 | T2 COLGATE-PALERMO 8/152 RPR STRW | ICW
LC | 125761379 | 003/009B | T2 EI CLEAR LAKE-HOPLAND 3/9B RPL STRW | WILLITS | ETL.6390.POLE.WOOD | 2023-03-30 | 2023-03-30 |  | Late | 2024-03-29 |  | 2024-03-30 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487153 | T2 EI CLEAR LAKE-HOPLAND 3/9A RPL STRW | 70Y
LC | 125761580 | 003/009C | T2 EI CLEAR LAKE-HOPLAND 3/9C RPL STRW | WILLITS | ETL.6390.POLE.WOOD | 2023-03-30 | 2023-03-30 |  | Late | 2024-03-29 |  | 2024-03-30 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487153 | T2 EI CLEAR LAKE-HOPLAND 3/9A RPL STRW | 70Y
LC | 125770083 | 009/070 | T2 DI TIGER CREEK-ELECTRA 009/070 COTTER | VICTOR | ETL.5780.INSL | 2023-03-31 | 2023-03-27 | 2023-05-04 | On-time | 2024-03-26 | 327 | 2023-06-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45743507 | T2 DI TIGER CREEK-ELECTRA 009/070 COTTER | ICS
LC | 125865635 | 004/007 | T2 DI FORT BRAGG-ELK 4/7 RMV VEG | WILLITS | ETL.2060.POLE.WOOD | 2023-04-11 | 2023-03-27 | 2024-03-22 | On-time | 2024-03-26 | 4 | 2024-03-27 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125865868 | 009/074 | T2NT DI TGR CRK-ELCTRA 9/74 RMV NEST | VICTOR | ETL.5780.TOWR | 2023-04-11 | 2023-03-27 | 2023-09-29 | On-time | 2024-03-26 | 179 | 2024-03-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 45989147 | T2NT DI TGR CRK-ELCTRA 9/74 RMV NEST | ICS
LC | 125762977 | 026/004 | T2 EI PHILO JCT-ELK 026/004 COTTER | WILLITS | ETL.7780.INSL.NCER | 2023-03-30 | 2023-03-30 | 2024-05-22 | Late | 2024-03-29 | -54 | 2023-09-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46214296 | T2 EI PHILO JCT-ELK 026/004 COTTER | ICW
LC | 125866679 | 004/063 | T2 DI JOLON TAP 004/063 RPL POLE | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-04-11 | 2023-03-27 | 2024-01-27 | On-time | 2024-03-26 | 59 | 2024-03-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35502310 | T2 DI JOLON TAP 004/063 RPL POLE | 70Y
LC | 125763526 | 007/116 | T2 EI CENTERVLL-TABLE MTN 7/116 RPL STRW | TABLEMTN | ETL.6320.POLE.WOOD | 2023-03-30 | 2023-03-30 | 2024-06-10 | Late | 2024-03-29 | -73 | 2024-03-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491961 | T2 EI CNTRVLLE-TABLE MTN 7/109 RPL STRW | 70Y
LC | 125742710 | 014/334 | T2 EI DRUM-GRS VALY-WMR 14/334 RPR INSW | SACTO | ETL.6760.INSL.NCER | 2023-03-28 | 2023-03-28 | 2024-01-11 | On-time | 2024-03-27 | 76 | 2024-03-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45993621 | T2 EI DRUM-GRS VALY-WMR 14/334 RPR INSW | ICW
LC | 125743461 | 028/202B | T2 DI CARIBOU TABLE MTN 28/202B COMPLETE | TABLEMTN | ETL.4440.INSL.NCER | 2023-03-28 | 2023-03-28 | 2023-06-15 | On-time | 2024-03-27 | 286 | 2023-06-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Steel | Replace | 45729406 | T2 DI CARIBOU TABLE MTN 28/202B RPL SPLS | ICS
LC | 125743462 | 026/191 | T2 DI CARIBOU TABLE MTN 26/191 RPL SPLC | TABLEMTN | ETL.4440.INSL.CERA | 2023-03-28 | 2023-03-28 | 2023-06-15 | On-time | 2024-03-27 | 286 | 2023-06-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Steel | Replace | 45729407 | T2 DI CARIBOU TABLE MTN 26/191 RPL SPLC | ICS
LC | 125763874 | 007/109 | T2 EI CNTRVLLE-TABLE MTN 7/109 RPL STRW | TABLEMTN | ETL.6320.POLE.WOOD | 2023-03-30 | 2023-03-30 | 2024-06-10 | Late | 2024-03-29 | -73 | 2024-03-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35491961 | T2 EI CNTRVLLE-TABLE MTN 7/109 RPL STRW | 70Y
LC | 125743561 | 013/099 | T2 DI CARIBOU TABLE MTN 13/99 COMPLETE | TABLEMTN | ETL.4440.INSL.CERA | 2023-03-28 | 2023-03-28 | 2023-06-17 | On-time | 2024-03-27 | 284 | 2023-06-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Steel | Replace | 45729408 | T2 DI CARIBOU TABLE MTN 13/099 RPL SPCR | ICS
LC | 125764497 | 010/005 | T2 EI FULTON-HOPLAND 010/005 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-03-30 | 2023-03-30 |  | Late | 2024-03-29 |  | 2024-03-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace
LC | 125744632 | 011/094 | T2 EI SAN LUS OBSPO-CYCS 11/94 INS DMPW | PISMOBCH | ETL.9090.INSL | 2023-03-28 | 2023-03-28 | 2024-01-11 | On-time | 2024-03-27 | 76 | 2024-03-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46088408 | T2 EI SAN LUS OBSPO-CYCS 11/94 INS DMPW | ICW
LC | 125766049 | 006/028 | T2 DI MNTA VSTA-JFSN #2 6/28 RPL INSS | METCALF | ETL.5230.INSL | 2023-03-30 | 2023-03-29 |  | Late | 2024-03-28 |  | 2024-03-29 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35537071 | T2 DI MNTA VSTA-JFSN #2 6/28 RPL INSS | 93K
LC | 125756596 | 005/004 | T2 DI MENDOCINO-HARTLEY 5/4 RPL POLE | WILLITS | ETL.7510.POLE.WOOD | 2023-03-29 | 2023-03-28 | 2024-02-13 | On-time | 2024-03-27 | 43 | 2024-03-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494506 | T2 DI MENDOCINO-HARTLEY 5/4 RPL POLE | 70Y
LC | 125756745 | 009/066 | T2 DI SN LS BSPO-CYCS 9/66 RPR GYWW | PISMOBCH | ETL.9090.POLE.WOOD | 2023-03-29 | 2023-03-28 | 2024-01-11 | On-time | 2024-03-27 | 76 | 2024-03-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088409 | T2 DI SN LS BSPO-CYCS 9/66 RPR GYWW | ICW
LC | 125866853 | 000/001 | T2 DI NARROWS #1 TAP 00/01 RPL HRDD | SACTO | ETL.6511.POLE.WOOD | 2023-04-11 | 2023-03-28 | 2023-12-14 | On-time | 2024-03-27 | 104 | 2024-03-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 45990063 | T2 DI COLGATE-SMARTVIL #1 00/01 RPR SWTC | ICW
LC | 125867014 | 004/001 | T2 DI MENDOCINO-HARTLEY 004/001 RPR INSW | WILLITS | ETL.7510.INSL.NCER | 2023-04-11 | 2023-03-28 | 2024-02-20 | On-time | 2024-03-27 | 36 | 2024-03-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46089303 | T2 DI MENDOCINO-HARTLEY 004/001 RPR INSW | ICW
LC | 125749549 | 009/064 | T2 MORAGA-SAN LEANDRO #2 09/064 RPL INST | CONCORD | ETL.2780.INSL | 2023-03-29 | 2023-03-29 | 2024-03-25 | On-time | 2024-03-28 | 3 | 2024-03-29 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671230 | T2 MORAGA-SAN LEANDRO #2 09/064 RPL INST | 93K
LC | 125750442 | 005/053A | T2 EI GOLD HILL #1 -_005/053A RPR STRW | SACTO | ETL.6950.POLE.WOOD | 2023-03-29 | 2023-03-29 | 2023-10-10 | On-time | 2024-03-28 | 170 | 2024-03-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45993622 | T2 EI GOLD HILL #1 -_005/053A RPR STRW | ICW
LC | 125769587 | 010/008 | T2 EI FULTON-HOPLAND 010/008 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-03-31 | 2023-03-31 |  | Late | 2024-03-30 |  | 2024-03-31 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521254 | T2 EI FULTON-HOPLAND 010/008 RPL POLE | 70Y
LC | 125769800 | 018/001 | T2 EI HMBLDT BY-R DL JCT 18/0 RPR SPLW | EUREKA | ETL.7100.INSL.CERA | 2023-03-31 | 2023-03-31 |  | Late | 2024-03-30 |  | 2024-03-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46070687 | T2 EI HMBLDT BY-R DL JCT 18/0 RPR SPLW | ICW
LC | 125750788 | 017/081 | T2 EI MSS LNDNG-LS BNS -_017/081 COTTER | MOSSLNDG | ETL.6040.INSL.NCER | 2023-03-29 | 2023-03-29 | 2024-01-12 | On-time | 2024-03-28 | 76 | 2024-03-29 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46016593 | T2 EI MSS LNDNG-LS BNS -_017/081 COTTER | ICS
LC | 125751110 | 014/007 | T2 EI FORT BRAGG-ELK 014/007 RPR CRSW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-29 | 2023-03-29 | 2024-02-27 | On-time | 2024-03-28 | 30 | 2024-03-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46089740 | T2 EI FORT BRAGG-ELK 014/007 RPR CRSW | ICW
LC | 125751884 | 011/074 | T2 CAYUCOS-CAMBRIA 11/074R CLEARANCE | PISMOBCH | ETL.8560.POLE.WDPS | 2023-03-29 | 2023-03-29 | 2024-01-16 | On-time | 2024-03-28 | 72 | 2024-03-29 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640157 | T2 CAYUCOS-CAMBRIA 11/074 CLEARANCE | 93G
LC | 125751925 | 011/074 | T2 CAYUCOS-CAMBRIA 11/074C CLEARANCE | PISMOBCH | ETL.8560.POLE.WDPS | 2023-03-29 | 2023-03-29 | 2024-01-16 | On-time | 2024-03-28 | 72 | 2024-03-29 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31640157 | T2 CAYUCOS-CAMBRIA 11/074 CLEARANCE | 93G
LC | 125751940 | 002/036 | T2 WEIMAR #1 02/36 RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2023-03-29 | 2023-03-29 | 2023-11-05 | On-time | 2024-03-28 | 144 | 2024-03-29 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481550 | T2 WEIMAR #1 02/36 RPL POLE | 70Y
LC | 125751949 | 007/172 | T2 EI COLGATE-GRSS VLLY 7/172 RPL STRW | SACTO | ETL.6490.POLE.WOOD | 2023-03-29 | 2023-03-29 | 2024-03-20 | On-time | 2024-03-28 | 8 | 2024-03-29 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491970 | T2 EI COLGATE-GRSS VLLY 7/172 RPL STRW | 70Y
LC | 125753087 | 009/078 | T2NT EI EL DRDO-MSRI FLT #1 9/78 RMV DEB | SACTO | ETL.1530.POLE.WOOD | 2023-03-29 | 2023-03-29 | 2023-09-28 | On-time | 2024-03-28 | 182 | 2024-03-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 45992665 | T2NT EI EL DRDO-MSRI FLT #1 9/78 RMV DEB | ICW
LC | 125753088 | 009/078 | T2 EI ELDRDO-MSRI FLT #1 9/78 RPR INSW | SACTO | ETL.1530.INSL | 2023-03-29 | 2023-03-29 | 2023-09-28 | On-time | 2024-03-28 | 182 | 2024-03-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45992666 | T2 EI ELDRDO-MSRI FLT #1 9/78 RPR INSW | ICW
LC | 125753447 | 046/395 | T2NT EI RD MTN-CTNWD #3 046/395 RPR STRT | TABLEMTN | ETL.5650.TOWR | 2023-03-29 | 2023-03-29 | 2023-10-25 | On-time | 2024-03-28 | 155 | 2024-03-29 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008769 | T2NT EI RD MTN-CTNWD #3 046/395 RPR STRT | ICQ
LC | 125754060 | 006/122 | T2 EI KESWICK-CASCADE 6/122 RPL POLE | TABLEMTN | ETL.7260.POLE.WOOD | 2023-03-29 | 2023-03-29 | 2023-07-28 | On-time | 2024-03-28 | 244 | 2023-09-29 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31646469 | T2 EI KESWICK-CASCADE 6/122 RPL POLE | 70Y
LC | 125772864 | 014/068 | T2 EI MSS LNDNG-LS BNOS 14/68 RMV VEG | MOSSLNDG | ETL.6040.TOWR | 2023-03-31 | 2023-03-31 | 2024-04-11 | Late | 2024-03-30 | -12 | 2024-03-31 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125754972 | 007/080 | T2 EI GRN VLLY-PAUL SWT 7/80 RPR POLE | MOSSLNDG | ETL.1730.POLE.WOOD | 2023-03-29 | 2023-03-29 | 2023-12-12 | On-time | 2024-03-28 | 107 | 2024-03-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46016592 | T2 EI GRN VLLY-PAUL SWT 7/80 RPR POLE | ICW
LC | 125772987 | 011/003 | T2 EI FULTON-HOPLAND 11/03 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-03-31 | 2023-03-31 |  | Late | 2024-03-30 |  | 2024-03-31 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521255 | T2 EI FULTON-HOPLAND 11/03 RPL POLE | 70Y
LC | 125756365 | 010/123 | T2 DI COLGATE-SMRTVILE#2 10/123 RPR GYWW | SACTO | ETL.6520.POLE.WOOD | 2023-03-29 | 2023-03-29 | 2023-10-02 | On-time | 2024-03-28 | 178 | 2024-03-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45993627 | T2 DI COLGATE-SMRTVILE#2 10/123 RPR GYWW | ICW
LC | 125773310 | 019/082 | T2 EI SAN RAMON-MORAGA 19/82 RPL INSS | CONCORD | ETL.5660.INSL | 2023-03-31 | 2023-03-31 | 2024-05-22 | Late | 2024-03-30 | -53 | 2024-03-31 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671231 | EI SAN RAMON-MORAGA RPL INSS IN 2 TWRS | 93K
LC | 125756447 | 007/074C | T2 DI PARADISE-BUTTE 7/74C RPR GYWW | TABLEMTN | ETL.4396.POLE.NWOD | 2023-03-29 | 2023-03-29 | 2024-01-23 | On-time | 2024-03-28 | 65 | 2024-03-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45996404 | T2 DI PARADISE-BUTTE 7/74C RPR GYWW | ICW
LC | 125756902 | 27 | T2 DI NARROWS #2 A10/128 RPR SWTCH | SACTO | ETL.6521.SWIT | 2023-03-29 | 2023-03-29 | 2024-03-25 | On-time | 2024-03-28 | 3 | 2024-03-29 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 45993513 | T2 DI NARROWS #2 A10/128 RPR SWITCH | ICE
LC | 125774785 | 011/005 | T2 EI FULTON-HOPLAND 11/05 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-03-31 | 2023-03-31 |  | Late | 2024-03-30 |  | 2024-03-31 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521257 | T2 EI FULTON-HOPLAND 11/05 RPL POLE | 70Y
LC | 125775144 | X010/042 | T2 DI DIABLO-MESA X10/42 RPR OPGW | PISMOBCH | ETL.4620.TOWR | 2023-03-31 | 2023-03-31 |  | Late | 2024-03-30 |  | 2024-03-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46078608 | T2 DI DIABLO-MESA X10/42 RPR OPGW | ICS
LC | 125775648 | 014/215 | T2 EI GOLD HILL #1 014/215 RPR POLE | SACTO | ETL.6950.POLE.WOOD | 2023-03-31 | 2023-03-31 | 2024-04-06 | Late | 2024-03-30 | -7 | 2024-03-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45993669 | T2 EI GOLD HILL #1 014/215 RPR POLE | ICW
LC | 125756912 | 008/085 | T2 DI PARADISE-BUTTE 8/85 RPLC ANCW | TABLEMTN | ETL.4396.POLE.NWOD | 2023-03-29 | 2023-03-29 | 2024-02-01 | On-time | 2024-03-28 | 56 | 2024-03-29 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35484832 | T2 DI PARADISE-BUTTE 8/85 RPLC ANCW | 93E
LC | 125756975 | 008/085 | T2 DI PARADISE-BUTTE 8/85 RPR GYWW | TABLEMTN | ETL.4396.POLE.NWOD | 2023-03-29 | 2023-03-29 | 2023-04-17 | On-time | 2024-03-28 | 346 | 2024-03-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45743480 | T2 DI PARADISE-BUTTE 8/85 RPR GYWW | ICW
LC | 125765311 | 054/000 | T2 DI ELK-GUALALA 054/000 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-03-30 | 2023-03-29 | 2024-01-23 | On-time | 2024-03-28 | 65 | 2024-03-29 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487316 | T2 DI ELK-GUALALA 054/008 RPL POLE | 70Y
LC | 125777176 | A004/099 | T2 DI IGNACIO-STAFFORD A4/99 RPL STRW | LAKEVLLE | ETL.1042.POLE.WOOD | 2023-04-01 | 2023-03-08 |  | Late | 2024-03-07 |  | 2024-03-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35486538 | T2 DI IGNACIO-STAFFORD A4/99 RPL STRW | 70Y
LC | 125766106 | 006/028 | T2 DI MNTA VSTA-JFSN #1 6/28 RPL INSS | METCALF | ETL.5220.INSL | 2023-03-30 | 2023-03-29 | 2024-01-09 | On-time | 2024-03-28 | 79 | 2024-03-29 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672909 | DI MNTA VSTA-JFSN #1 RPL INSS IN 4 TWRS. | 93K
LC | 125766283 | 004/017 | T2 DI MONTA VSTA-JFERSN #2 4/17 COMPLETE | METCALF | ETL.5230.INSL | 2023-03-30 | 2023-03-29 | 2024-03-18 | On-time | 2024-03-28 | 10 | 2024-03-29 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674006 | T2 DI MONTA VISTA-JEFF #2 RPL INSS IN 7 | 93K
LC | 125766289 | 004/017 | T2 DI MONTA VSTA-JEFERSON #1 4/17 COTTER | METCALF | ETL.5220.INSL | 2023-03-30 | 2023-03-29 | 2023-10-27 | On-time | 2024-03-28 | 153 | 2024-03-29 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45999085 | T2 DI MONTA VSTA-JEFERSON #1 4/17 COTTER | ICS
LC | 125778052 | 018/008 | T2 EI PHILO JCT-ELK 18/8 RPL HRDW | WILLITS | ETL.7780.POLE.NWOD | 2023-04-01 | 2023-04-01 | 2024-05-08 | Late | 2024-03-31 | -38 | 2024-04-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46089742 | T2 EI PHILO JCT-ELK 18/8 RPL HRDW | ICW
LC | 125778053 | 018/007 | T2 EI PHILO JCT-ELK 18/7 RPL INSW | WILLITS | ETL.7780.INSL.NCER | 2023-04-01 | 2023-04-01 | 2024-05-08 | Late | 2024-03-31 | -38 | 2024-04-01 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35492404 | T2 EI PHILO JCT-ELK 018/007 RPL INS | 93I
LC | 125778060 | 018/006 | T2 EI PHILO JCT-ELK 18/6 RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-01 | 2023-04-01 |  | Late | 2024-03-31 |  | 2024-04-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492405 | T2 EI PHILO JCT-ELK 18/6 RPL POLE | 70Y
LC | 125812901 | 037/008 | T2 DI ELK GUALALA 37/008 RPR INSW | WILLITS | ETL.8410.INSL.NCER | 2023-04-06 | 2023-03-29 | 2024-01-12 | On-time | 2024-03-28 | 76 | 2024-03-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079718 | T2 DI ELK GUALALA 37/008 RPR INSW | ICW
LC | 125825247 | 012/012 | T2 DI WINDSOR-FTCH MTN 12/12 RPL POLE | LAKEVLLE | ETL.6900.POLE.WOOD | 2023-04-07 | 2023-03-29 | 2023-06-16 | On-time | 2024-03-28 | 286 | 2023-06-29 | 372 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31642027 | T2 DI WINDSOR-FTCH MTN 12/12 RPL POLE | 70Y
LC | 125846076 | 011/010 | T2 DI WINDSOR-FITCH MTN 11/10 RPR SPLW | LAKEVLLE | ETL.6900.INSL.NCER | 2023-04-10 | 2023-03-29 | 2023-04-13 | On-time | 2024-03-28 | 350 | 2024-03-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 43749442 | EI WNDSR-FTCH MNTN WSIP TAGS | ICW
LC | 125778423 | 018/002 | T2NT EI PHILO JCT-ELK 18/2 RPR STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-01 | 2023-04-01 | 2024-05-01 | Late | 2024-03-31 | -31 | 2024-04-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46089745 | T2NT EI PHILO JCT-ELK 18/2 RPR WDPKR | ICW
LC | 125778481 | 006/094 | T2 EI CENTERVILLE-TBL MTN 06/94 RPL POLE | TABLEMTN | ETL.6320.POLE.WOOD | 2023-04-01 | 2023-04-01 | 2024-06-11 | Late | 2024-03-31 | -72 | 2024-04-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492462 | T2 EI CENTERVILLE-TBL MTN 06/94 RPL POLE | 70Y
LC | 125778490 | 006/092 | T2 EI CENTERVILLE-TBL MTN 06/92 RPL POLE | TABLEMTN | ETL.6320.POLE.WOOD | 2023-04-01 | 2023-04-01 | 2024-06-11 | Late | 2024-03-31 | -72 | 2024-04-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492461 | T2 EI CENTERVILLE-TBL MTN 06/92 RPL POLE | 70Y
LC | 125778512 | 002/007 | T2 EI PHILO JCT-ELK 2/7 RPR WDPKR | WILLITS | ETL.7780.POLE.WOOD | 2023-04-01 | 2023-04-01 |  | Late | 2024-03-31 |  | 2024-04-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46089746 | T2 EI PHILO JCT-ELK 2/7 RPR WDPKR | ICW
LC | 125883053 | 007/077A | T2 DI PARADISE-BUTTE 07/77A RPL HRDD | TABLEMTN | ETL.4396.INSL.CERA | 2023-04-12 | 2023-03-29 | 2024-01-23 | On-time | 2024-03-28 | 65 | 2024-03-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45996403 | T2 DI PARADISE-BUTTE 07/77A RPL HRDD | ICW
LC | 125884245 | 038/011 | T2 DI ELK-GUALALA 038/011 REFRAME | WILLITS | ETL.8410.POLE.WOOD | 2023-04-12 | 2023-03-29 | 2024-01-12 | On-time | 2024-03-28 | 76 | 2024-03-29 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35487272 | T2 DI ELK-GUALALA 038/011 REFRAME | 93E
LC | 125886193 | 042/007 | T2 DI FORT ROSS-GUALALA 42/7 RPR ANCW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-04-12 | 2023-03-29 | 2024-03-26 | On-time | 2024-03-28 | 2 | 2024-03-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46050709 | T2 DI FORT ROSS-GUALALA 42/7 RPR ANCW | ICW
LC | 125903877 | 010/120 | T2 DI CLGTE-SMRTVLE #2 10/120L RPR GYWW | SACTO | ETL.6520.POLE.STPS | 2023-04-13 | 2023-03-29 | 2023-10-02 | On-time | 2024-03-28 | 178 | 2024-03-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45993679 | T2 DI CLGTE-SMRTVLE #2 10/120L RPR GYWW | ICW
LC | 125778914 | 011/009 | T2 EI FULTON-HOPLAND 11/09 REFRAME | LAKEVLLE | ETL.6890.POLE.NWOD | 2023-04-01 | 2023-04-01 |  | Late | 2024-03-31 |  | 2024-04-01 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35521317 | T2 EI FULTON-HOPLAND 11/09 REFRAME | 93E
LC | 125903898 | 010/120 | T2 DI COLGATE-SMRTVL #2 10/120L RPR ANCW | SACTO | ETL.6520.POLE.STPS | 2023-04-13 | 2023-03-29 | 2023-07-10 | On-time | 2024-03-28 | 262 | 2023-09-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45740509 | T2 DI COLGATE-SMRTVL #2 10/120L RPR ANCW | ICW
LC | 125778933 | 003/033 | T2 EI MONTA VISTA-BURNS 3/33R RPL STRW | MOSSLNDG | ETL.7590.POLE.WDPS | 2023-04-01 | 2023-04-01 |  | Late | 2024-03-31 |  | 2024-04-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505603 | T2 EI MONTA VISTA-BURNS 3/33R RPL STRW | 70Y
LC | 125778934 | 003/033 | T2 EI MONTA VISTA-BURNS 3/33L RPL STRW | MOSSLNDG | ETL.7590.POLE.WDPS | 2023-04-01 | 2023-04-01 |  | Late | 2024-03-31 |  | 2024-04-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505603 | T2 EI MONTA VISTA-BURNS 3/33R RPL STRW | 70Y
LC | 125778936 | 003/033 | T2 EI MONTA VISTA-BURNS 3/33C RPL STRW | MOSSLNDG | ETL.7590.POLE.WDPS | 2023-04-01 | 2023-04-01 |  | Late | 2024-03-31 |  | 2024-04-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505603 | T2 EI MONTA VISTA-BURNS 3/33R RPL STRW | 70Y
LC | 125779985 | 000/002 | T2 EI CHRISTIE-WLLOW PSS 00/02 RPL POLE | CONCORD | ETL.6370.POLE.WOOD | 2023-04-02 | 2023-04-02 |  | Late | 2024-04-01 |  | 2024-04-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35529777 | T2 EI CHRISTIE-WLLOW PSS 00/02 RPL POLE | 70Y
LC | 125780017 | 017/004 | T2 EI PHILO JCT-ELK 17/4 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-04-02 | 2023-04-02 | 2024-05-07 | Late | 2024-04-01 | -36 | 2024-04-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35492763 | T2 EI PHILO JCT-ELK 17/4 RPL POLE | 70Y
LC | 125904662 | 007/031 | T2 DI MNTAVSTA-JFRSN#1 7/31 RPL INSS | METCALF | ETL.5220.INSL | 2023-04-13 | 2023-03-29 | 2024-01-07 | On-time | 2024-03-28 | 81 | 2024-03-29 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672909 | DI MNTA VSTA-JFSN #1 RPL INSS IN 4 TWRS. | 93K
LC | 125935159 | 011/006 | T2 DI WNDSR-FTCH MNTN-11/06 RPR ANCW | LAKEVLLE | ETL.6900.POLE.WOOD | 2023-04-17 | 2023-03-29 | 2023-05-02 | On-time | 2024-03-28 | 331 | 2023-09-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45745575 | T2 DI WNDSR-FTCH MNTN-11/06 RPR ANCW | ICW
LC | 126104341 | 053/009 | T2 DI ELK GUALALA 53/009 UNBURY | WILLITS | ETL.8410.POLE.WOOD | 2023-05-11 | 2023-03-29 | 2024-01-16 | On-time | 2024-03-28 | 72 | 2024-03-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46079891 | T2 DI ELK GUALALA 53/009 UNBURY | ICW
LC | 125758874 | 020/474 | T2 EI DRM-GRSS VLY-WMR 020/474 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2023-03-30 | 2023-03-30 | 2024-03-28 | On-time | 2024-03-29 | 1 | 2024-03-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491979 | T2 EI DRM-GRSS VLY-WMR 020/474 RPL STRW | 70Y
LC | 125780100 | 017/006 | T2 EI PHILO JCT-ELK 17/6 RPR GYWW | WILLITS | ETL.7780.POLE.NWOD | 2023-04-02 | 2023-04-02 | 2024-05-01 | Late | 2024-04-01 | -30 | 2024-04-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45998348 | T2 EI PHILO JCT-ELK 17/6 RPR GYWW | ICS
LC | 125759374 | 010/080 | T2 EI TRINITY-CTTNWD 010/080 RPL GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-03-30 | 2023-03-30 | 2024-02-24 | On-time | 2024-03-29 | 34 | 2024-03-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45996252 | T2 EI TRINITY-CTTNWD 010/080 RPL GYWW | ICW
LC | 125759375 | 010/080 | T2 EI TRINITY-CTTNWD 010/080 RPL GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-03-30 | 2023-03-30 | 2024-02-24 | On-time | 2024-03-29 | 34 | 2024-03-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45996250 | T2 EI TRINITY-CTTNWD 010/080 RPL GYWW | ICW
LC | 125759377 | 010/080 | T2 EI TRINITY-CTTNWD 010/080 RPL GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-03-30 | 2023-03-30 | 2024-02-24 | On-time | 2024-03-29 | 34 | 2024-03-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45996249 | T2 EI TRINITY-CTTNWD 010/080 RPL GYWW | ICW
LC | 125780347 | 004/038 | T2 EI MONTA VISTA-BURNS 4/38 RPL POLE | MOSSLNDG | ETL.7590.POLE.WOOD | 2023-04-02 | 2023-04-02 |  | Late | 2024-04-01 |  | 2023-10-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505604 | T2 EI MONTA VISTA-BURNS 4/38 RPL POLE | 70Y
LC | 125759401 | 009/122 | T2 EI GOLD HILL #1 09/122 RPR STRW | SACTO | ETL.6950.POLE.WOOD | 2023-03-30 | 2023-03-30 | 2023-10-10 | On-time | 2024-03-29 | 171 | 2024-03-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45993629 | T2 EI GOLD HILL #1 09/122 RPR STRW | ICW
LC | 125759792 | 009/072A | T2 EI TRINITY-CTTNWD 09/72A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-03-30 | 2023-03-30 | 2024-02-24 | On-time | 2024-03-29 | 34 | 2024-03-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46191127 | T2 EI TRINITY-CTTNWD 09/72A RPR GYWW | ICW
LC | 125759842 | 009/072A | T2 EI TRINITY-CTTNWD 09/72A RPR ANCW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-03-30 | 2023-03-30 | 2024-02-24 | On-time | 2024-03-29 | 34 | 2024-03-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46191128 | T2 EI TRINITY-CTTNWD 09/72A RPR ANCW | ICW
LC | 125759850 | 010/001 | T2 EI FULTON-HOPLAND 010/001 RPR GYWW | LAKEVLLE | ETL.6890.POLE.NWOD | 2023-03-30 | 2023-03-30 | 2023-11-09 | On-time | 2024-03-29 | 141 | 2024-03-30 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46007987 | T2 EI FULTON-HOPLAND 010/001 RPR GYWW | ICS
LC | 125780668 | 036/004 | T2 EI PHILO JCT-ELK 36/4 RPR INSW | WILLITS | ETL.7780.INSL.CERA | 2023-04-02 | 2023-04-02 | 2024-06-11 | Late | 2024-04-01 | -71 | 2024-04-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46213898 | T2 EI PHILO JCT-ELK 36/4 RPR INSW | ICW
LC | 125760146 | 009/072C | T2 EI TRINITY-COTTONWOOD 09/72C RPR ANCS | TABLEMTN | ETL.4040.POLE.NWOD | 2023-03-30 | 2023-03-30 | 2024-02-24 | On-time | 2024-03-29 | 34 | 2024-03-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45996255 | T2 EI TRINITY-COTTONWOOD 09/72C RPR ANCS | ICW
LC | 125780697 | 018/418 | T2 EI DRM-GRSS VLLY-WMR 018/418 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2023-04-02 | 2023-04-02 |  | Late | 2024-04-01 |  | 2023-07-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493099 | T2 EI DRM-GRSS VLLY-WMR 018/418 RPL POLE | 70Y
LC | 125760148 | 009/072C | T2 EI TRINITY-CTTNWD 9/72C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-03-30 | 2023-03-30 | 2024-02-24 | On-time | 2024-03-29 | 34 | 2024-03-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46191129 | T2 EI TRINITY-CTTNWD 9/72C RPR GYWW | ICW
LC | 125780736 | 034/007 | T2 EI PHILO JCT-ELK 34/007C RPL STRW | WILLITS | ETL.7780.POLE.WDPS | 2023-04-02 | 2023-04-02 |  | Late | 2024-04-01 |  | 2024-04-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35492687 | T2 EI PHILO JCT-ELK 34/007C RPL STRW | 70Y
LC | 125760528 | 009/125 | T2 EI GOLD HILL #109/125 RPR STRW | SACTO | ETL.6950.POLE.WOOD | 2023-03-30 | 2023-03-30 | 2023-10-11 | On-time | 2024-03-29 | 170 | 2024-03-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45993631 | T2 EI GOLD HILL #109/125 RPR STRW | ICW
LC | 125760659 | 007/145 | T2 EI KESWICK-CASCADE 7/145 RPL POLE | TABLEMTN | ETL.7260.POLE.WOOD | 2023-03-30 | 2023-03-30 | 2023-07-29 | On-time | 2024-03-29 | 244 | 2023-06-30 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31641550 | T2 EI KESWICK-CASCADE 7/145 RPL POLE | 70Y
LC | 125761048 | 035/165 | T2 EI RD MTN-TBL MTN #1 35/165 RPR FOND | TABLEMTN | ETL.6060.TOWR | 2023-03-30 | 2023-03-30 | 2024-03-19 | On-time | 2024-03-29 | 10 | 2024-03-30 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46008770 | T2 EI RD MTN-TBL MTN #1 35/165 RPR FOND | ICQ
LC | 125761101 | 035/165 | T2 EI RD MTN-TBL MTN #1 35/165 RPR GYWT | TABLEMTN | ETL.6060.TOWR | 2023-03-30 | 2023-03-30 | 2024-03-19 | On-time | 2024-03-29 | 10 | 2024-03-30 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46204710 | T2 EI RD MTN-TBL MTN #1 35/165 RPR GYWT | ICQ
LC | 125781529 | 004/076 | T2 EI CNTRVLE-TBL MTN 004/076 RPR INSW | TABLEMTN | ETL.6320.INSL.NCER | 2023-04-03 | 2023-04-03 | 2024-06-11 | Late | 2024-04-02 | -70 | 2024-04-03 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999464 | T2 EI CNTRVLE-TBL MTN 004/076 | ICW
LC | 125762877 | 012/109 | T2 SAN LUIS OBISP-CYCS 012/109C RPL HRDW | PISMOBCH | ETL.9090.POLE.WDPS | 2023-03-30 | 2023-03-30 | 2024-01-10 | On-time | 2024-03-29 | 79 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46088410 | T2 SAN LUIS OBISP-CYCS 012/109C RPL HRDW | ICW
LC | 125762916 | 066/277 | T2 EI RD MTN-TBL MTN #1 66/277 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2023-03-30 | 2023-03-30 | 2023-11-06 | On-time | 2024-03-29 | 144 | 2024-03-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46007989 | T2 EI RD MTN-TBL MTN #1 66/277 RPR GYWS | ICS
LC | 125763481 | 019/162 | T2 EI CRG VW-CSCDE-WD 19/162 RPL POLE | TABLEMTN | ETL.1350.POLE.WDPS | 2023-03-30 | 2023-03-30 | 2024-02-26 | On-time | 2024-03-29 | 32 | 2024-03-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 125763543 | 007/117 | T2 EI CENTERVLL-TABLE MTN 7/117 RPR GYWW | TABLEMTN | ETL.6320.POLE.NWOD | 2023-03-30 | 2023-03-30 | 2024-02-01 | On-time | 2024-03-29 | 57 | 2023-09-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45996258 | T2 EI CENTERVLL-TABLE MTN 7/117 RPR GYWW | ICW
LC | 125782259 | 037/011 | T2 DI ELK-GUALALA 37/11 RPR GYWW | WILLITS | ETL.8410.POLE.NWOD | 2023-04-03 | 2023-03-31 | 2024-04-23 | Late | 2024-03-30 | -24 | 2024-03-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079719 | T2 DI ELK-GUALALA 037/11 RPR GYWW | ICW
LC | 125763652 | 019/162 | T2 EI CRG VW-CSCDE-WD 19/162 RPL POLE | TABLEMTN | ETL.1350.POLE.WDPS | 2023-03-30 | 2023-03-30 | 2024-02-26 | On-time | 2024-03-29 | 32 | 2024-03-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 125763858 | 004/115 | T2 EI CLGT-GRSS VLLY 004/115 RPL POLE | SACTO | ETL.6490.POLE.WOOD | 2023-03-30 | 2023-03-30 | 2024-03-20 | On-time | 2024-03-29 | 9 | 2024-03-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518747 | T2 EI CLGT-GRSS VLLY 004/115 RPL POLE | 70Y
LC | 125782663 | 027/016 | T2 EI GOLD HILL #1 027/016 RPR POLE | VICTOR | ETL.6950.POLE.WOOD | 2023-04-03 | 2023-04-03 |  | Late | 2024-04-02 |  | 2024-04-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081366 | T2 EI GOLD HILL #1_027/016 RPR POLE | ICW
LC | 125782763 | 001/020 | T2 EI MONTA VISTA-BURNS 1/20 RPL STRW | MOSSLNDG | ETL.7590.POLE.NWOD | 2023-04-03 | 2023-04-03 |  | Late | 2024-04-02 |  | 2024-04-03 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35517394 | T2 EI MONTA VISTA-BURNS 1/20 RPL STRW | 70Y
LC | 125764469 | 019/163 | T2 EI CRG VW-CSCDE-WD 19/163 RPL INSW | TABLEMTN | ETL.1350.INSL.CERA | 2023-03-30 | 2023-03-30 | 2024-02-26 | On-time | 2024-03-29 | 32 | 2024-03-30 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35491975 | T2 EI CRG VW-CSCDE-WD 19/163 RPL INSW | 93I
LC | 125782871 | A014/295 | T2 EI SALINAS-LAURELES A14/295 RPR SPLW | MOSSLNDG | ETL.7930.INSL | 2023-04-03 | 2023-04-03 | 2024-04-24 | Late | 2024-04-02 | -22 | 2024-04-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46081071 | T2 EI SALINAS-LAURELES A14/295 RPR SPLW | ICW
LC | 125783322 | 011/004 | T2 EI FORT BRAGG-ELK 011/004 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-04-03 | 2023-04-03 |  | Late | 2024-04-02 |  | 2024-04-03 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35488003 | T2 EI FORT BRAGG-ELK 011/004 RPL STRW | 70Y
LC | 125778806 | 003/056 | T2 DI SMARTVL-MARYSVL 3/56 RPR INSW | SACTO | ETL.7980.INSL.NCER | 2023-04-01 | 2023-03-30 | 2023-10-02 | On-time | 2024-03-29 | 179 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45993674 | T2 DI SMARTVL-MARYSVL 3/56 RPR INSW | ICW
LC | 125782254 | 005/026 | T2 DI DIABLO-GATES #1 5/26 RPR GYWT | PISMOBCH | ETL.5960.TOWR | 2023-04-03 | 2023-03-30 | 2024-03-04 | On-time | 2024-03-29 | 25 | 2024-03-30 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 45998013 | T2 DI DIABLO-GATES #1 5/26 RPR GYWT | ICQ
LC | 125782645 | ?011/003 | T2 DI SNEATH LN-HALF MON BY ?11/3 COTTER | METCALF | ETL.7212.INSL.NCER | 2023-04-03 | 2023-03-30 | 2023-11-30 | On-time | 2024-03-29 | 120 | 2024-03-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45997331 | T2 DI SNEATH LN-HALF MON BY ?11/3 COTTER | ICS
LC | 125807730 | 003/024 | T2 DI STNSLS-MLNS-MNTC 3/24 BNT STEEL | VICTOR | ETL.3830.TOWR | 2023-04-05 | 2023-03-30 | 2024-01-26 | On-time | 2024-03-29 | 63 | 2024-03-30 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45996880 | T2 DI STNSLS-MLNS-MNTC 3/24 BNT STEEL | ICQ
LC | 125810610 | 000/013 | T2 DI CARIBOU-WESTWOOD 000/013L RPR GYWW | TABLEMTN | ETL.6300.POLE.STPS | 2023-04-06 | 2023-03-30 | 2023-11-28 | On-time | 2024-03-29 | 122 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45996402 | T2 DI CARIBOU-WESTWOOD 000/013L RPR GYWW | ICW
LC | 125784265 | 016/298 | T2 EI FULTON-MLIN-CTATI 16/298 RPL INSW | LAKEVLLE | ETL.6910.INSL.CERA | 2023-04-03 | 2023-04-03 |  | Late | 2024-04-02 |  | 2024-04-03 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35509400 | T2 EI FULTON-MLIN-CTATI 16/298 RPL INSW | 93I
LC | 125810615 | 000/013 | T2 DI CARIBOU-WESTWOOD 000/013C RPR GYWW | TABLEMTN | ETL.6300.POLE.STPS | 2023-04-06 | 2023-03-30 | 2023-11-28 | On-time | 2024-03-29 | 122 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45996401 | T2 DI CARIBOU-WESTWOOD 000/013C RPR GYWW | ICW
LC | 125810618 | 000/013 | T2 DI CARIBOU-WESTWOOD 000/013R RPR GYWW | TABLEMTN | ETL.6300.POLE.STPS | 2023-04-06 | 2023-03-30 | 2023-11-28 | On-time | 2024-03-29 | 122 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45996400 | T2 DI CARIBOU-WESTWOOD 000/013R RPR GYWW | ICW
LC | 125822893 | 003/021 | T2 DI STNSLS-MNTCA 3/21 RPL HRDT | VICTOR | ETL.3820.TOWR | 2023-04-07 | 2023-03-30 | 2023-10-11 | On-time | 2024-03-29 | 170 | 2024-03-30 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45996618 | T2 DI STNSLS-MNTCA 3/21 RPL HRDT | ICQ
LC | 125784775 | 086/602 | T2 EI HMBLT-BRDGVLLE 86/602 RPL INSS | EUREKA | ETL.1810.INSL.NCER | 2023-04-03 | 2023-04-03 |  | Late | 2024-04-02 |  | 2024-04-03 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672316 | T2 EI HMBLT-BRDGVLLE 86/602 RPL INSS | 93K
LC | 125784897 | 013/002 | T2 EI FULTON-HOPLAND 13/02 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-04-03 | 2023-04-03 |  | Late | 2024-04-02 |  | 2024-04-03 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521319 | T2 EI FULTON-HOPLAND 13/02 RPL POLE | 70Y
LC | 125823678 | 003/023 | T2 DI SNLS-MLNS SS-MNTCA#1 3/23 RPL HRDT | VICTOR | ETL.3830.TOWR | 2023-04-07 | 2023-03-30 | 2023-11-29 | On-time | 2024-03-29 | 121 | 2024-03-30 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45996619 | T2 DI SNLS-MLNS SS-MNTCA#1 3/23 RPL HRDT | ICQ
LC | 125846187 | 001/023 | T2 DI NARROWS #1 TAP 001/023 RPR GYWW | SACTO | ETL.6511.POLE.WDPS | 2023-04-10 | 2023-03-30 | 2023-10-03 | On-time | 2024-03-29 | 178 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45993675 | T2 DI NARROWS #1 TAP 001/023 RPR GYWW | ICW
LC | 125853962 | 002/036A | T2 DI NARROWS#2 2/36A RPR GYWW | SACTO | ETL.6521.POLE.WOOD | 2023-04-10 | 2023-03-30 | 2023-10-04 | On-time | 2024-03-29 | 177 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45993677 | T2 DI NARROWS#2 2/36A RPR GYWW | ICW
LC | 125904921 | 003/020 | T2 DI STAN-MLNS SS-RVRBNK 03/20 RPL DAMS | VICTOR | ETL.3840.INSL.CERA | 2023-04-13 | 2023-03-30 | 2023-12-02 | On-time | 2024-03-29 | 118 | 2024-03-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 45996534 | T2 DI STAN-MLNS SS-RVRBNK 03/20 RPL DAMS | ICS
LC | 125785703 | 086/000F | T2 EI HUMBLDT-BRIDGVLE 86/00F RPL ANCW | EUREKA | ETL.1810.POLE.WOOD | 2023-04-03 | 2023-04-03 |  | Late | 2024-04-02 |  | 2024-04-03 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35493313 | T2 EI HUMBLDT-BRIDGVLE 86/00F RPL ANCW | 93E
LC | 125786487 | 015/014 | T2 EI FORT BRAGG-ELK 015/014 RPL POLE | WILLITS | ETL.2060.POLE.WOOD | 2023-04-03 | 2023-04-03 |  | Late | 2024-04-02 |  | 2024-04-03 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487802 | T2 EI FORT BRAGG-ELK 015/014 RPL POLE | 70Y
LC | 125905144 | 000/018 | T2 DI CRBU-WSTWD 00/18 RPR ANCW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-04-13 | 2023-03-30 | 2023-11-28 | On-time | 2024-03-29 | 122 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45996259 | T2 DI CRBU-WSTWD 00/18 RPR ANCW | ICW
LC | 125905483 | 000/002 | T2 DI CARIBOU-PLUMAS JCT 00/02 RPR ANCW | TABLEMTN | ETL.6290.POLE.NWOD | 2023-04-13 | 2023-03-30 | 2023-05-17 | On-time | 2024-03-29 | 317 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45774620 | T2 DI CARIBOU-PLUMAS JCT 00/02 RPR ANCW | ICW
LC | 125905567 | 003/017 | T2 DI STANSLS-MANTECA #2 3/17 RPR FOND | VICTOR | ETL.3820.TOWR | 2023-04-13 | 2023-03-30 | 2023-10-11 | On-time | 2024-03-29 | 170 | 2024-03-30 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45996617 | T2 DI STANSLS-MANTECA #2 3/17 RPR FOND | ICQ
LC | 125909136 | 002/037 | T2 DI NARROWS #2 TAP 2/37 RPR ANCW | SACTO | ETL.6521.POLE.WOOD | 2023-04-14 | 2023-03-30 | 2023-11-07 | On-time | 2024-03-29 | 143 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45740517 | T2 DI NARROWS #2 TAP 2/37 RPR ANCW | ICW
LC | 125787972 | 025/009 | T2 EI PHILO JCT-ELK 25/9 RPR ANCW | WILLITS | ETL.7780.POLE.WDPS | 2023-04-03 | 2023-04-03 | 2024-05-21 | Late | 2024-04-02 | -49 | 2024-04-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46213890 | T2 EI PHILO JCT-ELK 025/009 RPR ANCW | ICW
LC | 125788011 | 027/004 | T2 EI PHILO JCT-ELK 027/004L RPR GYWW | WILLITS | ETL.7780.POLE.STPS | 2023-04-03 | 2023-04-03 | 2024-06-05 | Late | 2024-04-02 | -64 | 2024-04-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213889 | T2 EI PHILO JCT-ELK 027/004L RPR GYWW | ICW
LC | 125769388 | 007/057 | T2 EI EL DORDO-MSRI FLT #2 7/57 RPR INSS | SACTO | ETL.1540.INSL.NCER | 2023-03-31 | 2023-03-31 | 2023-10-04 | On-time | 2024-03-30 | 178 | 2024-03-31 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45993516 | T2 EI EL DORDO-MSRI FLT #2 7/57 RPR INSS | ICS
LC | 125790242 | 006/028 | T2 DI DIABLO-MESA 6/28 COMPLETE | PISMOBCH | ETL.4620.INSL.NCER | 2023-04-04 | 2023-03-31 | 2024-05-16 | Late | 2024-03-30 | -47 | 2024-03-31 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671707 | T0 DIABLO-MESA RPL INSS 7 LSTS | 93K
LC | 125770709 | 007/059 | T2 EI EL DORDO-MSRI FLT #1 7/59 RPR FOND | SACTO | ETL.1530.TOWR | 2023-03-31 | 2023-03-31 | 2023-07-14 | On-time | 2024-03-30 | 260 | 2024-03-31 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45881987 | T2 EI EL DORDO-MSRI FLT #1 7/59 RPR FOND | ICQ
LC | 125771100 | 003/052 | T2 EI WEIMAR #1 3/52 RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2023-03-31 | 2023-03-31 | 2023-11-05 | On-time | 2024-03-30 | 146 | 2024-03-31 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481559 | T2 EI WEIMAR #1 3/52 RPL POLE | 70Y
LC | 125771431 | 015/005 | T2 EI FORT BRAGG-ELK 015/005 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-03-31 | 2023-03-31 | 2024-03-06 | On-time | 2024-03-30 | 24 | 2024-03-31 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507484 | T2 EI FORT BRAGG-ELK 015/005 RPL STRW | 70Y
LC | 125771516 | 018/157 | T2 EI CRAG VIEW-CASCADE 018/157 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2023-03-31 | 2023-03-31 | 2024-02-29 | On-time | 2024-03-30 | 30 | 2024-03-31 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 125771694 | 003/050 | T2 EI WEIMAR #1 3/50 RPR CNDW | SACTO | ETL.7560.INSL.CERA | 2023-03-31 | 2023-03-31 | 2023-11-04 | On-time | 2024-03-30 | 147 | 2024-03-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45993639 | T2 EI WEIMAR #1 3/50 RPR CNDW | ICW
LC | 125791366 | B020/449 | T2 EI DRM-GRSS VLY-WMR B20/449 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2023-04-04 | 2023-04-04 |  | Late | 2024-04-03 |  | 2024-04-04 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999306 | T2 EI DRM-GRSS VLY-WMR B20/449 RPR POLE | ICW
LC | 125771917 | 020/461 | T2 EI DRM-GRSS VLY-WMR 020/461 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2023-03-31 | 2023-03-31 | 2024-03-28 | On-time | 2024-03-30 | 2 | 2023-09-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492478 | T2 EI DRM-GRSS VLY-WMR 020/461 RPL STRW | 70Y
LC | 125772708 | 003/083 | T2 EI CLGT-GRSS VLLY 003/083 RPR INSW | SACTO | ETL.6490.INSL.NCER | 2023-03-31 | 2023-03-31 | 2024-01-26 | On-time | 2024-03-30 | 64 | 2024-03-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45993667 | T2 EI CLGT-GRSS VLLY 003/083 RPR INSW | ICW
LC | 125772709 | 003/083 | T2 EI CLGT-GRSS VLLY 003/083 RPR POLE | SACTO | ETL.6490.POLE.WOOD | 2023-03-31 | 2023-03-31 | 2024-01-26 | On-time | 2024-03-30 | 64 | 2024-03-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45993668 | T2 EI CLGT-GRSS VLLY 003/083 RPR POLE | ICW
LC | 125772902 | 024/120 | T2 EI RND MTN-TBL MTN #2 24/120 RPL HRDT | TABLEMTN | ETL.6070.TOWR | 2023-03-31 | 2023-03-31 | 2023-10-26 | On-time | 2024-03-30 | 156 | 2024-03-31 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46008771 | T2 EI RND MTN-TBL MTN #2 24/120 RPL HRDT | ICQ
LC | 125772991 | 004/022 | T2 SAN LUS OBISP-CAYUCS 4/22 RPR INSW | PISMOBCH | ETL.9090.INSL.CERA | 2023-03-31 | 2023-03-31 | 2024-01-13 | On-time | 2024-03-30 | 77 | 2024-03-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46088411 | T2 SAN LUS OBISP-CAYUCS 4/22 RPR INSW | ICW
LC | 125792201 | 012/053 | T2 EI MORAGA-CASTRO VLLEY 12/53 RPL INSS | CONCORD | ETL.5250.INSL | 2023-04-04 | 2023-04-02 | 2024-04-30 | Late | 2024-04-01 | -29 | 2024-04-02 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671781 | EI MORAGA-CASTRO VLLEY 12/53 RPL INSS | 93K
LC | 125792493 | 000/012 | T2 WV LONE STAR TAP -_000/012 INS DMP | MOSSLNDG | ETL.6231.INSL.NCER | 2023-04-04 | 2023-04-04 |  | Late | 2024-04-03 |  | 2024-04-04 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 46016596 | T2 WV LONE STAR TAP -_000/012 INS DMP | ICW
LC | 125773380 | X006/029 | T2 DI DIABLO-MESA X006/029 RPR OPGW | PISMOBCH | ETL.4620.TOWR | 2023-03-31 | 2023-03-31 | 2023-08-30 | On-time | 2024-03-30 | 213 | 2023-06-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45907949 | T2 DI DIABLO-MESA X006/029 RPR OPGW | ICS
LC | 125792672 | 023/103 | T2 DI MORRO BAY-MESA 23/103 COTTER | PISMOBCH | ETL.4620.INSL.NCER | 2023-04-04 | 2023-03-31 | 2024-06-04 | Late | 2024-03-30 | -66 | 2024-03-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46007998 | T2 DI MORRO BAY-MESA 023/103 RPR INSS | ICS
LC | 125774501 | 006/049 | T2 EI ELDRDO-MSRI FLT #1 6/49 RPR INSS | SACTO | ETL.1530.INSL | 2023-03-31 | 2023-03-31 | 2024-03-14 | On-time | 2024-03-30 | 16 | 2024-03-31 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46007990 | T2 EI ELDRDO-MSRI FLT #1 6/49 RPR INSS | ICQ
LC | 125776260 | 005/026A | T2 DI DIABLO-MESA-TOWER 005/26A RPL HRDT | PISMOBCH | ETL.4620.TOWR | 2023-04-01 | 2023-03-31 | 2023-09-30 | On-time | 2024-03-30 | 182 | 2024-03-31 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45998014 | T2 DI DIABLO-MESA-TOWER 005/26A RPL HRDT | ICQ
LC | 125777976 | X009/040 | T2 DI MORRO BAY-DIABLO X9/40 COMPLETE | PISMOBCH | ETL.4620.TOWR | 2023-04-01 | 2023-03-31 | 2024-03-22 | On-time | 2024-03-30 | 8 | 2024-03-31 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46216827 | T2 DI MORRO BAY-DIABLO X9/40 COMPLETE | ICQ
LC | 125795616 | 034/154 | T2 DI MORRO BAY-MESA 034/154 RPR STRT | PISMOBCH | ETL.5290.TOWR | 2023-04-04 | 2023-03-31 | 2024-02-21 | On-time | 2024-03-30 | 38 | 2024-03-31 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45998018 | T2 DI MORRO BAY-MESA 034/154 RPR STRT | ICQ
LC | 125795768 | 004/018 | T2 DI MORRO BAY MESA 04/018 RPL INSS | PISMOBCH | ETL.5290.INSL.CERA | 2023-04-04 | 2023-03-31 | 2024-03-04 | On-time | 2024-03-30 | 26 | 2024-03-31 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31670479 | T2 DI MORRO BAY MESA 19/085 RPL INSS | 93K
LC | 125797432 | 015/069 | T2 DI MORRO BAY MESA 015/069 RPL INST | PISMOBCH | ETL.5290.INSL | 2023-04-04 | 2023-03-31 | 2024-03-05 | On-time | 2024-03-30 | 25 | 2024-03-31 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31670479 | T2 DI MORRO BAY MESA 19/085 RPL INSS | 93K
LC | 125797544 | 015/067 | T2 DI MORRO BAY MESA 015/067 RPL INST | PISMOBCH | ETL.5290.INSL | 2023-04-04 | 2023-03-31 | 2024-02-14 | On-time | 2024-03-30 | 45 | 2024-03-31 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31670479 | T2 DI MORRO BAY MESA 19/085 RPL INSS | 93K
LC | 125798692 | 005/027 | T2 DI MORRO BAY MESA 5/27 RPR INSS | PISMOBCH | ETL.5290.INSL.NCER | 2023-04-05 | 2023-03-31 | 2024-02-23 | On-time | 2024-03-30 | 36 | 2024-03-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46078952 | T2 DI MORRO BAY MESA 5/27 RPR INSS | ICS
LC | 125800887 | 027/118 | T2 DI MORRO BAY MESA 27/118 RPL INSS | PISMOBCH | ETL.5290.INSL | 2023-04-05 | 2023-03-31 | 2024-03-07 | On-time | 2024-03-30 | 23 | 2024-03-31 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31670479 | T2 DI MORRO BAY MESA 19/085 RPL INSS | 93K
LC | 125895841 | 010/048 | T2 DI MORRO BY-MESA 10/48 RPL INSS | PISMOBCH | ETL.5290.INSL | 2023-04-13 | 2023-03-31 | 2024-03-04 | On-time | 2024-03-30 | 26 | 2024-03-31 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31670479 | T2 DI MORRO BAY MESA 19/085 RPL INSS | 93K
LC | 125895844 | 010/048 | T2 DI MORRO BY-MESA 10/48 RPR STRT | PISMOBCH | ETL.5290.TOWR | 2023-04-13 | 2023-03-31 | 2024-02-21 | On-time | 2024-03-30 | 38 | 2024-03-31 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45998015 | T2 DI MORRO BY-MESA 10/48 RPR STRT | ICQ
LC | 125910128 | 063/003 | T2 DI ELK-GUALALA- 63/03 RPL STRW | WILLITS | ETL.8410.POLE.WOOD | 2023-04-14 | 2023-03-31 | 2024-01-26 | On-time | 2024-03-30 | 64 | 2024-03-31 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487367 | T2 DI ELK-GUALALA- 63/03 RPL STRW | 70Y
LC | 125915426 | 056/008 | T2 DI ELK-GUALALA 056/008 RPR ANCW | WILLITS | ETL.8410.POLE.WOOD | 2023-04-14 | 2023-03-31 | 2024-01-24 | On-time | 2024-03-30 | 66 | 2024-03-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46079893 | T2 DI ELK-GUALALA 056/008 RPR ANCW | ICW
LC | 125794781 | 028/122 | T2 DI MORRO BAY-MESA 28/122 RMV ENCR | PISMOBCH | ETL.5290.TOWR | 2023-04-04 | 2023-04-03 |  | Late | 2024-04-02 |  | 2023-10-03 | 931 | TLS |  | E - Schd Compl Yr 0 | Open | TR2 | Encroachment | Right of Way | Remove
LC | 125777041 | 002/068 | T2 EI CLGT-GRSS VLLY 002/068 REFRAME | SACTO | ETL.6490.POLE.WOOD | 2023-04-01 | 2023-04-01 | 2024-03-06 | On-time | 2024-03-31 | 25 | 2024-04-01 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35492472 | T2 EI CLGT-GRSS VLLY 002/068 REFRAME | 93E
LC | 125794952 | 029/008B | T2 EI PHILO JCT-ELK 29/8 WASH INSW | WILLITS | ETL.7780.INSL.CERA | 2023-04-04 | 2023-04-04 | 2024-06-10 | Late | 2024-04-03 | -68 | 2024-04-04 | 622 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Contaminated | Insulator | Ground Wash | 46213886 | T2 EI PHILO JCT-ELK 29/8 WASH INSW | ICD
LC | 125795093 | 023/102 | T2 DI MORRO BAY-MESA 23/102 RPL INSS | PISMOBCH | ETL.5290.INSL.CERA | 2023-04-04 | 2023-04-03 | 2024-06-24 | Late | 2024-04-02 | -83 | 2024-04-03 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31670479 | T2 DI MORRO BAY MESA 19/085 RPL INSS | 93K
LC | 125777284 | 019/444 | T2 EI DRM-GRSS VLLY-WMR 019/444 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2023-04-01 | 2023-04-01 | 2024-03-27 | On-time | 2024-03-31 | 4 | 2024-04-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45993670 | T2 EI DRM-GRSS VLLY-WMR 019/444 RPR POLE | ICW
LC | 125795262 | 028/000 | T2 EI PHILO JCT-ELK 28/0 RPR STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-04 | 2023-04-04 | 2024-06-08 | Late | 2024-04-03 | -66 | 2024-04-04 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46213887 | T2 EI PHILO JCT-ELK 28/0 RPR STRW | ICW
LC | 125777357 | 002/066 | T2 EI CLGT-GRSS VLLY 002/066 RPL POLE | SACTO | ETL.6490.POLE.WOOD | 2023-04-01 | 2023-04-01 | 2024-03-22 | On-time | 2024-03-31 | 9 | 2024-04-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492473 | T2 EI CLGT-GRSS VLLY 002/066 RPL POLE | 70Y
LC | 125795619 | 021/094 | T2 DI DIABLO-MESA 21/94 RPL INSS | PISMOBCH | ETL.4620.INSL | 2023-04-04 | 2023-04-03 |  | Late | 2024-04-02 |  | 2024-04-03 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671707 | T0 DIABLO-MESA RPL INSS 7 LSTS | 93K
LC | 125795641 | 017/389 | T2 EI DRM-GRSS VLY-WMR 17/389 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2023-04-04 | 2023-04-04 |  | Late | 2024-04-03 |  | 2024-04-04 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35537184 | T2 EI DRM-GRSS VLY-WMR 17/389 RPL POLE | 70Y
LC | 125778135 | A002/054 | T2 EI VALLEY SPRINGS #1 A2/54 RPL POLE | VICTOR | ETL.8210.POLE.WOOD | 2023-04-01 | 2023-04-01 | 2024-03-17 | On-time | 2024-03-31 | 14 | 2024-04-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35511450 | T2 EI VLLY SPRNGS #1 A002/052 RPL STRW | 70Y
LC | 125795679 | 026/001 | T2 MI-WUK-CURTIS 26/1 RPR COTTER KEY | VICTOR | ETL.1073.INSL.CERA | 2023-04-04 | 2023-04-04 |  | Late | 2024-04-03 |  | 2024-04-04 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46058675 | T2 MI-WUK-CURTIS 26/1 RPR COTTER KEY | ICW
LC | 125778204 | 018/152 | T2 EI CRAG VIEW-CSCDE 018/152L RPR PL | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-01 | 2023-04-01 | 2023-11-30 | On-time | 2024-03-31 | 122 | 2024-04-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45996248 | T2 EI CRAG VIEW-CSCDE 018/152L RPR PL | ICW
LC | 125778208 | 002/058 | T2 EI CLGT-GRSS VLLY 002/058 RPL HRDW | SACTO | ETL.6490.POLE.WOOD | 2023-04-01 | 2023-04-01 | 2024-01-26 | On-time | 2024-03-31 | 65 | 2024-04-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45993673 | T2 EI CLGT-GRSS VLLY 002/058 RPL HRDW | ICW
LC | 125778620 | 012/054 | T2 EI MORAGA-CASTRO VLLY 12/54 RMV VEG | CONCORD | ETL.5250.TOWR | 2023-04-01 | 2023-04-01 | 2024-02-23 | On-time | 2024-03-31 | 37 | 2024-04-01 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125795834 | 000/003 | T2 DI MORRO BAY-DIABLO 000/003 RPL INSS | PISMOBCH | ETL.5260.INSL | 2023-04-04 | 2023-04-03 | 2024-05-02 | Late | 2024-04-02 | -30 | 2024-04-03 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31658032 | T2 DI MORRO BAY-DIABLO 000/003 RPL INSS | 93K
LC | 125778886 | 002/027 | T2NT EI CHRST-WLLW PASS 002/027 RPR INSW | CONCORD | ETL.6370.INSL.CERA | 2023-04-01 | 2023-04-01 | 2024-02-23 | On-time | 2024-03-31 | 37 | 2024-04-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45997037 | T2NT EI CHRST-WLLW PASS 002/027 RPR INSW | ICW
LC | 125778913 | 003/036 | T2 EI CHRST-WLLW PSS 003/036 RPL POLE | CONCORD | ETL.6370.POLE.WOOD | 2023-04-01 | 2023-04-01 | 2024-02-20 | On-time | 2024-03-31 | 40 | 2024-04-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35513226 | T2 EI CHRSTE-WLW PS 001/016 RPL STRW | 70Y
LC | 125778920 | 002/030 | T2 EI CHRST-WLLW PSS 002/030 RPL POLE | CONCORD | ETL.6370.POLE.WOOD | 2023-04-01 | 2023-04-01 | 2024-02-21 | On-time | 2024-03-31 | 39 | 2024-04-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35513226 | T2 EI CHRSTE-WLW PS 001/016 RPL STRW | 70Y
LC | 125780056 | 030/220 | T2 EI DRUM-RIO OSO #1 30/220 RPL INSS | SACTO | ETL.1420.INSL.CERA | 2023-04-02 | 2023-04-02 | 2023-11-04 | On-time | 2024-04-01 | 149 | 2024-04-02 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671112 | T2 EI DRUM-RIO OSO #1 30/220 RPL INSS | 93K
LC | 125780061 | 000/016 | T2 EI VALLEY SPRINGS #1 0/16 RPL POLE | VICTOR | ETL.8210.POLE.WOOD | 2023-04-02 | 2023-04-02 | 2024-03-22 | On-time | 2024-04-01 | 10 | 2024-04-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505018 | T2 EI VALLEY SPRINGS #1 0/16 RPL POLE | 70Y
LC | 125797548 | 015/067 | T2 DI DIABLO-MESA 015/067 RPL INSS | PISMOBCH | ETL.4620.INSL | 2023-04-04 | 2023-03-31 |  | Late | 2024-03-30 |  | 2024-03-31 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671707 | T0 DIABLO-MESA RPL INSS 7 LSTS | 93K
LC | 125780064 | 030/220 | T2 EI DRUM-RIO OSO #2 30/220 RPL INSS | SACTO | ETL.1430.INSL.CERA | 2023-04-02 | 2023-04-02 | 2024-01-24 | On-time | 2024-04-01 | 68 | 2024-04-02 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671114 | T2 EI DRUM-RIO OSO #2 RPL INSS | 93K
LC | 125780099 | 018/428 | T2 EI DRM-GRSS VLLY-WMR 018/428 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2023-04-02 | 2023-04-02 | 2024-01-23 | On-time | 2024-04-01 | 69 | 2024-04-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45998958 | T2 EI DRM-GRSS VLLY-WMR 018/428 RPR POLE | ICW
LC | 125780161 | 012/053 | T2 EI MORAGA-CASTRO VLLEY 12/53 RPL HRDT | CONCORD | ETL.5250.TOWR | 2023-04-02 | 2023-04-02 | 2023-07-11 | On-time | 2024-04-01 | 265 | 2023-10-02 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45716717 | T2 EI MORAGA-CASTRO VLLEY 12/53 RPL HRDT | ICQ
LC | 125798696 | 019/085 | T2 DI DIABLO-MESA 19/85 RPL INSS | PISMOBCH | ETL.4620.INSL | 2023-04-05 | 2023-03-31 |  | Late | 2024-03-30 |  | 2024-03-31 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671707 | T0 DIABLO-MESA RPL INSS 7 LSTS | 93K
LC | 125798720 | 019/085 | T2 DI MORRO BAY MESA 19/85 RPL INSS | PISMOBCH | ETL.5290.INSL | 2023-04-05 | 2023-03-31 |  | Late | 2024-03-30 |  | 2024-03-31 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31670479 | T2 DI MORRO BAY MESA 19/085 RPL INSS | 93K
LC | 125780169 | 017/146 | T2 EI CRAG VIEW-CASCADE 17/146 RPL POLE | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-02 | 2023-04-02 | 2024-02-29 | On-time | 2024-04-01 | 32 | 2024-04-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 125780342 | 016/005 | T2 EI FORT BRAGG-ELK 016/005 RPL POLE | WILLITS | ETL.2060.POLE.WOOD | 2023-04-02 | 2023-04-02 | 2024-03-14 | On-time | 2024-04-01 | 18 | 2024-04-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487710 | T2 EI FORT BRAGG-ELK 016/005 RPL POLE | 70Y
LC | 125780348 | 001/025 | T2 EI VALLEY SPRINGS #1 1/25 RPR INSW | VICTOR | ETL.8210.INSL.NCER | 2023-04-02 | 2023-04-02 | 2023-10-28 | On-time | 2024-04-01 | 156 | 2024-04-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46048851 | T2 EI VALLEY SPRINGS #1 1/25 RPR INSW | ICW
LC | 125799353 | 006/077 | T2 EI KESWICK-TRINITY 006/077 RMV VEG | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-05 | 2023-04-05 |  | Late | 2024-04-04 |  | 2024-04-05 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 125799374 | 012/010 | T2 EI FORT BRAGG-ELK 012/010 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-04-05 | 2023-04-05 |  | Late | 2024-04-04 |  | 2024-04-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487939 | T2 EI FORT BRAGG-ELK 012/010 RPL STRW | 70Y
LC | 125780514 | 018/422 | T2 EI DRM-GRSS VLLY-WMR 018/4 RPR INSW | SACTO | ETL.6760.INSL.NCER | 2023-04-02 | 2023-04-02 | 2024-03-28 | On-time | 2024-04-01 | 4 | 2024-04-02 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45998957 | T2 EI DRM-GRSS VLLY-WMR 018/4 RPR INSW | ICS
LC | 125780516 | 010/005 | T2 EI FORT BRAGG-ELK 010/005 RPL GYWW | WILLITS | ETL.2060.POLE.WOOD | 2023-04-02 | 2023-04-02 | 2024-02-26 | On-time | 2024-04-01 | 35 | 2024-04-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 46089747 | T2 EI FORT BRAGG-ELK 010/005 RPL GYWW | ICW
LC | 125780601 | 004/042 | T2 EI MONTA VST-BRNS 4/42 RPR GWYY | MOSSLNDG | ETL.7590.POLE.STPS | 2023-04-02 | 2023-04-02 | 2024-02-28 | On-time | 2024-04-01 | 33 | 2024-04-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46016594 | T2 EI MONTA VST-BRNS 4/42 RPR GWYY | ICW
LC | 125799893 | 034/003 | T2 EI PHILO JCT-ELK 34/3 RPL INSW | WILLITS | ETL.7780.INSL.CERA | 2023-04-05 | 2023-04-05 | 2024-05-21 | Late | 2024-04-04 | -47 | 2024-04-05 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493077 | T2 EI PHILO JCT-ELK 34/3 RPL INSW | 93I
LC | 125780695 | 017/143 | T2 EI CRG VIEW-CASCADE 17/143 RPR XARM | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-02 | 2023-04-02 | 2023-11-29 | On-time | 2024-04-01 | 124 | 2024-04-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45999466 | T2 EI CRG VIEW-CASCADE 17/143 RPR XARM | ICW
LC | 125800068 | 034/002 | T2 EI PHILO JCT-ELK 34/2 RPR INSW | WILLITS | ETL.7780.INSL.CERA | 2023-04-05 | 2023-04-05 | 2024-05-21 | Late | 2024-04-04 | -47 | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46213883 | T2 EI PHILO JCT-ELK 34/2 RPR INSW | ICW
LC | 125780698 | 012/084 | T2 EI GREEN VALLEY-LLAGAS 12/84 RPR WDPK | MOSSLNDG | ETL.1720.POLE.WDPS | 2023-04-02 | 2023-04-02 | 2024-01-23 | On-time | 2024-04-01 | 69 | 2024-04-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Animal Guard-Wood | Install | 46016585 | T2 EI GREEN VALLEY-LLAGAS 12/84 RPR WDPK | ICW
LC | 125800584 | 012/008 | T2 EI FORT BRAGG-ELK 012/008 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-04-05 | 2023-04-05 | 2024-04-12 | Late | 2024-04-04 | -8 | 2024-04-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487939 | T2 EI FORT BRAGG-ELK 012/010 RPL STRW | 70Y
LC | 125780849 | 029/215 | T2 EI DRUM-RIO OSO #2 29/215 RPL INSS | SACTO | ETL.1430.INSL | 2023-04-02 | 2023-04-02 | 2024-01-17 | On-time | 2024-04-01 | 75 | 2024-04-02 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671114 | T2 EI DRUM-RIO OSO #2 RPL INSS | 93K
LC | 125780870 | 029/217 | T2 EI DRUM-RIO OSO #2 29/217 RPL INSS | SACTO | ETL.1430.INSL | 2023-04-02 | 2023-04-02 | 2024-01-17 | On-time | 2024-04-01 | 75 | 2024-04-02 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671114 | T2 EI DRUM-RIO OSO #2 RPL INSS | 93K
LC | 125780871 | 029/216 | T2 EI DRUM-RIO OSO #2 29/216 RPL INSS | SACTO | ETL.1430.INSL | 2023-04-02 | 2023-04-02 | 2024-01-17 | On-time | 2024-04-01 | 75 | 2024-04-02 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671114 | T2 EI DRUM-RIO OSO #2 RPL INSS | 93K
LC | 125780883 | 029/214 | T2 EI DRUM-RIO OSO #2 29/214 RPL INSS | SACTO | ETL.1430.INSL | 2023-04-02 | 2023-04-02 | 2024-01-17 | On-time | 2024-04-01 | 75 | 2024-04-02 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671114 | T2 EI DRUM-RIO OSO #2 RPL INSS | 93K
LC | 125801032 | 033/010 | T2 EI PHILO JCT-ELK 33/10 RPL INSW | WILLITS | ETL.7780.INSL.NCER | 2023-04-05 | 2023-04-05 | 2024-06-21 | Late | 2024-04-04 | -78 | 2024-04-05 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493077 | T2 EI PHILO JCT-ELK 34/3 RPL INSW | 93I
LC | 125993216 | 017/146 | T2 EI CRAG VIEW-CASCADE 17/146 RPL POLE | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-26 | 2023-04-02 | 2024-02-29 | On-time | 2024-04-01 | 32 | 2024-04-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 125781825 | 017/074 | T2 DI DIABLO-MESA 017/74 RPR INSS | PISMOBCH | ETL.4620.INSL.NCER | 2023-04-03 | 2023-04-03 | 2024-03-05 | On-time | 2024-04-02 | 28 | 2024-04-03 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46007991 | T2 DI DIABLO-MESA 017/74 RPR INSS | ICS
LC | 125781982 | 017/074 | T2 DI MORRO BAY-MESA 017/74 COTTER | PISMOBCH | ETL.5290.INSL.NCER | 2023-04-03 | 2023-04-03 | 2024-02-14 | On-time | 2024-04-02 | 48 | 2024-04-03 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46007992 | T2 DI MORRO BAY-MESA 017/74 COTTER | ICS
LC | 125781987 | 001/016 | T2 EI CHRSTE-WLW PS 001/016 RPL STRW | CONCORD | ETL.6370.POLE.WOOD | 2023-04-03 | 2023-04-03 | 2024-02-20 | On-time | 2024-04-02 | 42 | 2024-04-03 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35513226 | T2 EI CHRSTE-WLW PS 001/016 RPL STRW | 70Y
LC | 125782569 | 028/170 | T2 EI TEMBLR-SN LUS OBSP 28/170 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2023-04-03 | 2023-04-03 | 2024-04-01 | On-time | 2024-04-02 | 1 | 2024-04-03 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674043 | T2 EI TEMBLR-SN LUS OBSP 29/175 RPL INST | 93K
LC | 125782837 | 011/006 | T2 EI FORT BRAGG-ELK 011/006 UNBURY | WILLITS | ETL.2060.POLE.WOOD | 2023-04-03 | 2023-04-03 | 2024-02-28 | On-time | 2024-04-02 | 34 | 2024-04-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46089748 | T2 EI FORT BRAGG-ELK 011/006 UNBURY | ICW
LC | 125801958 | 015/294 | T2 EI FULTON-MOLINO-CTT-_15/294 RPR IBWW | LAKEVLLE | ETL.6910.INSL.NCER | 2023-04-05 | 2023-04-05 |  | Late | 2024-04-04 |  | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 46044395 | T2 EI FULTON-MOLINO-CTT-_15/294 RPR IBWW | ICW
LC | 125801978 | 015/294 | T2 EI FULTON-MOLINO-CTT 15/294 RPR GYWW | LAKEVLLE | ETL.6910.POLE.WOOD | 2023-04-05 | 2023-04-05 | 2024-04-12 | Late | 2024-04-04 | -8 | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46044395 | T2 EI FULTON-MOLINO-CTT-_15/294 RPR IBWW | ICW
LC | 125783327 | 018/412 | T2 EI DRM-GRSS VLY-WMR 018/412 RPL INSW | SACTO | ETL.6760.INSL.CERA | 2023-04-03 | 2023-04-03 | 2024-03-28 | On-time | 2024-04-02 | 5 | 2024-04-03 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493240 | T2 EI DRM-GRSS VLY-WMR 018/412 RPL INSW | 93I
LC | 125802147 | 014/097 | T2NT EI MLLBRAE-SNTH LN 14/97 RPR ATCG | METCALF | ETL.7570.POLE.NWOD | 2023-04-05 | 2023-04-05 | 2024-04-29 | Late | 2024-04-04 | -25 | 2024-04-05 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Anti-Climbing Guard | Structure-Tower | Repair | 46008511 | T2NT EI MLLBRAE-SNTH LN 14/97 RPR ATCG | ICQ
LC | 125783331 | 018/412 | T2 EI DRM-GRSS VLY-WMR 018/412 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2023-04-03 | 2023-04-03 | 2024-03-26 | On-time | 2024-04-02 | 7 | 2024-04-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999254 | T2 EI DRM-GRSS VLY-WMR 018/412 RPR STRW | ICW
LC | 125783864 | 018/411 | T2 EI DRM-GRSS VLY-WMR 018/411 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2023-04-03 | 2023-04-03 | 2024-03-27 | On-time | 2024-04-02 | 6 | 2024-04-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999255 | T2 EI DRM-GRSS VLY-WMR 018/411 RPR STRW | ICW
LC | 125783865 | 018/411 | T2 EI DRM-GRSS VLY-WMR 018/411 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2023-04-03 | 2023-04-03 | 2024-01-12 | On-time | 2024-04-02 | 81 | 2024-04-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999256 | T2 EI DRM-GRSS VLY-WMR 018/411 RPR GYWW | ICW
LC | 125802811 | 026/009 | T2 EI PHILO JCT-ELK 26/9 RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-05 | 2023-04-05 | 2024-06-04 | Late | 2024-04-04 | -61 | 2024-04-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493079 | T2 EI PHILO JCT-ELK 26/9 RPL POLE | 70Y
LC | 125803065 | 027/001 | T2 EI PHILO JCT-ELK 27/1 RPR INSW | WILLITS | ETL.7780.INSL.NCER | 2023-04-05 | 2023-04-05 | 2024-06-03 | Late | 2024-04-04 | -60 | 2023-10-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46213885 | T2 EI PHILO JCT-ELK 27/1 RPR INSW | ICW
LC | 125784218 | 028/167 | T2 EI TEMBLR-SN LUS OBSP 28/167 RPL INST | PISMOBCH | ETL.3960.INSL.CERA | 2023-04-03 | 2023-04-03 | 2024-04-01 | On-time | 2024-04-02 | 1 | 2024-04-03 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674043 | T2 EI TEMBLR-SN LUS OBSP 29/175 RPL INST | 93K
LC | 125784344 | 016/004 | T2 EI FORT BRAGG-ELK 016/004 COTTER | WILLITS | ETL.2060.INSL.CERA | 2023-04-03 | 2023-04-03 | 2024-03-14 | On-time | 2024-04-02 | 19 | 2024-04-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46089749 | T2 EI FORT BRAGG-ELK 016/004 COTTER | ICW
LC | 125803414 | 014/096 | T2NT EI MLLBRAE-SNTH LN -_14/96 RPR CLMB | METCALF | ETL.7570.POLE.NWOD | 2023-04-05 | 2023-04-05 | 2024-04-29 | Late | 2024-04-04 | -25 | 2024-04-05 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46008510 | T2NT EI MLLBRAE-SNTH LN -_14/96 RPR CLMB | ICQ
LC | 125784669 | 028/166 | T2 EI TEMBLR-SN LUS OBSP 28/166 RPL INST | PISMOBCH | ETL.3960.INSL.CERA | 2023-04-03 | 2023-04-03 | 2024-04-01 | On-time | 2024-04-02 | 1 | 2024-04-03 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674043 | T2 EI TEMBLR-SN LUS OBSP 29/175 RPL INST | 93K
LC | 125803420 | 023/096 | T2 EI DIABLO-GATES #1 23/96 COMPLETE | PISMOBCH | ETL.5960.TOWR | 2023-04-05 | 2023-04-05 | 2024-04-15 | Late | 2024-04-04 | -11 | 2024-04-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46175236 | T2 EI DIABLO-GATES #1 23/96 RPR GYWT | ICQ
LC | 125804064 | 018/087 | T2 MSS LNDNG-LS BNOS 18/87 RPL INSS | MOSSLNDG | ETL.6040.INSL | 2023-04-05 | 2023-04-05 | 2024-06-08 | Late | 2024-04-04 | -65 | 2024-04-05 | 532 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671709 | T2 MSS LNDNG-LS BNOS 18/87 RPL INST | 93K
LC | 125784726 | 042/189 | T2 EI RND MTN-TBL MTN#1 42/189 BNT STEEL | TABLEMTN | ETL.6060.TOWR | 2023-04-03 | 2023-04-03 | 2024-03-14 | On-time | 2024-04-02 | 19 | 2024-04-03 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008772 | T2 EI RND MTN-TBL MTN#1 42/189 BNT STEEL | ICQ
LC | 125785190 | 002/019 | T2 EI CHSTE-WLW PS 002/019 RPL STRW | CONCORD | ETL.6370.POLE.WOOD | 2023-04-03 | 2023-04-03 | 2024-02-21 | On-time | 2024-04-02 | 41 | 2024-04-03 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35513226 | T2 EI CHRSTE-WLW PS 001/016 RPL STRW | 70Y
LC | 125785597 | 016/003 | T2 EI FORT BRAGG-ELK 016/003 WASH INSW | WILLITS | ETL.2060.INSL.CERA | 2023-04-03 | 2023-04-03 | 2024-03-14 | On-time | 2024-04-02 | 19 | 2024-04-03 | 622 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Contaminated | Insulator | Ground Wash | 46089753 | T2 EI FORT BRAGG-ELK 016/003 WASH INSW | ICD
LC | 125785670 | 042/190 | T2 EI RND MTN-TBL MTN#1 42/190 BNT STEEL | TABLEMTN | ETL.6060.TOWR | 2023-04-03 | 2023-04-03 | 2024-03-11 | On-time | 2024-04-02 | 22 | 2024-04-03 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008773 | T2 EI RND MTN-TBL MTN#1 42/190 BNT STEEL | ICQ
LC | 125785671 | 042/190 | T2 EI RND MTN-TBL MTN#1 42/190 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2023-04-03 | 2023-04-03 | 2024-03-11 | On-time | 2024-04-02 | 22 | 2024-04-03 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46007993 | T2 EI RND MTN-TBL MTN#1 42/190 RPR GYWS | ICS
LC | 125786587 | 005/050 | T2 EI HLSDLE JT-HLF MN BY 5/50L RPL POLE | METCALF | ETL.7060.POLE.WDPS | 2023-04-03 | 2023-04-03 | 2023-06-28 | On-time | 2024-04-02 | 279 | 2024-04-03 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31649134 | T2 EI HLSDLE JT-HLF MN BY 5/50L RPL POLE | 70Y
LC | 125805653 | 015/283 | T2 EI FULTON-MOLINO-CTT 015/283 RPL GYWW | LAKEVLLE | ETL.6910.POLE.WOOD | 2023-04-05 | 2023-04-05 |  | Late | 2024-04-04 |  | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 46044397 | T2 EI FULTON-MOLINO-CTT-_015/283 RPR GYW | ICW
LC | 125806073 | 023/005 | T2 DI MI WUK CURTIS 23/005 RPR GYWW | VICTOR | ETL.1073.POLE.WDPS | 2023-04-05 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45984775 | T2 DI MI WUK CURTIS 23/005 RPR GYWW | ICW
LC | 125786820 | 005/050 | T2 EI HLSDLE JT-HLF MN BY 5/50C RPL POLE | METCALF | ETL.7060.POLE.WDPS | 2023-04-03 | 2023-04-03 | 2023-06-28 | On-time | 2024-04-02 | 279 | 2024-04-03 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31649134 | T2 EI HLSDLE JT-HLF MN BY 5/50L RPL POLE | 70Y
LC | 125806206 | 023/005 | T2 DI MI WUK CURTIS 23/005R RPR STRW | VICTOR | ETL.1073.POLE.WDPS | 2023-04-05 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45984776 | T2 DI MI WUK CURTIS 23/005 RPR STRW | ICW
LC | 125806208 | 023/005 | T2 DI MI WUK CURTIS 23/005L RPR STRW | VICTOR | ETL.1073.POLE.WDPS | 2023-04-05 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45984777 | T2 DI MI WUK CURTIS 23/005 RPR STRW | ICW
LC | 125806262 | 023/005 | T2 DI MI WUK CURTIS 23/005C RPR STRW | VICTOR | ETL.1073.POLE.WDPS | 2023-04-05 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45984778 | T2 DI MI WUK CURTIS 23/005 RPR STRW | ICW
LC | 125786976 | 042/192 | T2 EI RND MTN-TBL MTN #1 42/192 INS HRDT | TABLEMTN | ETL.6060.TOWR | 2023-04-03 | 2023-04-03 | 2024-03-07 | On-time | 2024-04-02 | 26 | 2024-04-03 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Tower | Install | 46007994 | T2 EI RND MTN-TBL MTN #1 42/192 INS HRDT | ICQ
LC | 125787059 | 063/004 | T2 DI ELK GUALALA 063/004 COTTER | WILLITS | ETL.8410.INSL.NCER | 2023-04-03 | 2023-04-03 | 2024-01-27 | On-time | 2024-04-02 | 66 | 2024-04-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079894 | T2 DI ELK GUALALA 063/004 COTTER | ICW
LC | 125807071 | 023/004 | T2 DI MI-WUK-CURTIS 23/004 (L) RPR GYWW | VICTOR | ETL.1073.POLE.WDPS | 2023-04-05 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45984779 | T2 DI MI-WUK-CURTIS 23/004 (L) RPR GYWW | ICW
LC | 125807074 | 023/004 | T2 DI MI-WUK-CURTIS 23/004 (R) RPR GYWW | VICTOR | ETL.1073.POLE.WDPS | 2023-04-05 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45984800 | T2 DI MI-WUK-CURTIS 23/004 (R) RPR GYWW | ICW
LC | 125790176 | 034/153 | T2 DI MORRO BAY MESA 034/153 RMV VEG | PISMOBCH | ETL.5290.TOWR | 2023-04-04 | 2023-04-03 | 2024-02-27 | On-time | 2024-04-02 | 35 | 2024-04-03 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125791163 | 015/066 | T2 DI DIABLO-MESA 015/066 COTTER | PISMOBCH | ETL.4620.INSL.NCER | 2023-04-04 | 2023-04-03 | 2024-02-24 | On-time | 2024-04-02 | 38 | 2024-04-03 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46007995 | T2 DI DIABLO-MESA 015/066 COTTER | ICS
LC | 125807455 | 001/006 | T2 DI RACETRACK TAP 1/006 RPL STRW | VICTOR | ETL.2393.POLE.WOOD | 2023-04-05 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493014 | T2 DI RACETRACK TAP 1/006 RPL STRW | 70Y
LC | 125807463 | 029/014 | T2 DI FULTON-HOPLAND 029/14 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-04-05 | 2023-04-03 |  | Late | 2024-04-02 |  | 2024-04-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521333 | T2 DI FULTON-HOPLAND 029/14 RPL POLE | 70Y
LC | 125791262 | 015/066 | T2 DI MORRO BAY MESA 015/066 COTTER | PISMOBCH | ETL.5290.INSL | 2023-04-04 | 2023-04-03 | 2024-02-14 | On-time | 2024-04-02 | 48 | 2024-04-03 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46007996 | T2 DI MORRO BAY MESA 015/066 COTTER | ICS
LC | 125795724 | 000/003 | T2 DI MORRO BAY-MESA 000/003 RPR STRT | PISMOBCH | ETL.5290.TOWR | 2023-04-04 | 2023-04-03 | 2024-02-22 | On-time | 2024-04-02 | 40 | 2024-04-03 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46031627 | T2 DI MORRO BAY-MESA 000/003 RPR STRT | ICQ
LC | 125795783 | 000/003 | T2 DI MORRO BAY-MESA 000/003 COTTER | PISMOBCH | ETL.5290.INSL.NCER | 2023-04-04 | 2023-04-03 | 2024-02-23 | On-time | 2024-04-02 | 39 | 2024-04-03 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46008080 | T2 DI MORRO BAY-MESA 000/003 COTTER | ICS
LC | 125798501 | 006/029 | T2 DI MORRO BAY-MESA 6/29 RPR INSS | PISMOBCH | ETL.5290.INSL.CERA | 2023-04-05 | 2023-04-03 | 2024-03-04 | On-time | 2024-04-02 | 29 | 2024-04-03 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46008081 | T2 DI MORRO BAY-MESA 6/29 RPR INSS | ICS
LC | 125808555 | 014/336 | T2 DI DRM GRS VLY WMR 14/336 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2023-04-06 | 2023-04-03 |  | Late | 2024-04-02 |  | 2024-04-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999258 | T2 DI DRM GRS VLY WMR 14/336 RPR POLE | ICW
LC | 125806940 | 009/223 | T2 DI COLGATE-GRASS VALEY 9/223 RPL POLE | SACTO | ETL.6490.POLE.WOOD | 2023-04-05 | 2023-04-03 | 2024-03-11 | On-time | 2024-04-02 | 22 | 2024-04-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493427 | T2 DI COLGATE-GRASS VALEY 9/223 RPL POLE | 70Y
LC | 125807083 | 011/265 | T2 DI COLGATE-GRAS VALLY 11/265 RPL POLE | SACTO | ETL.6490.POLE.WOOD | 2023-04-05 | 2023-04-03 | 2024-03-17 | On-time | 2024-04-02 | 16 | 2024-04-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493435 | T2 DI COLGATE-GRAS VALLY 11/265 RPL POLE | 70Y
LC | 125807334 | 006/147 | T2 DI COLGATE-GRASS VALLY 6/147 RPR CRSW | SACTO | ETL.6490.POLE.WOOD | 2023-04-05 | 2023-04-03 | 2024-03-05 | On-time | 2024-04-02 | 28 | 2024-04-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45998959 | T2 DI COLGATE-GRASS VALLY 6/147 RPR CRSW | ICW
LC | 125809581 | 000/001 | T2 DI DLTA-MTN GT JCT 00/001 RPR STRW | TABLEMTN | ETL.6750.POLE.WOOD | 2023-04-06 | 2023-03-30 |  | Late | 2024-03-29 |  | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45762015 | T2 DI DLTA-MTN GT JCT 00/001 RPR STRW | ICW
LC | 125807662 | 029/007 | T2NT DI FULTON-HOPLAND 29/007 RMV BUTT | LAKEVLLE | ETL.6890.POLE.NWOD | 2023-04-05 | 2023-04-03 | 2023-11-09 | On-time | 2024-04-02 | 145 | 2024-04-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 46045908 | T2NT DI FULTON-HOPLAND 29/007 RMV BUTT | ICW
LC | 125808594 | 012/302 | T2 DI COLGATE-GRASS VLLY 12/302 RPL STRW | SACTO | ETL.6490.POLE.WOOD | 2023-04-06 | 2023-04-03 | 2024-03-13 | On-time | 2024-04-02 | 20 | 2024-04-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506668 | T2 DI COLGATE-GRASS VLLY 12/302 RPL STRW | 70Y
LC | 125808906 | 006/027 | T2 DI PTSBRG SN MTO 06/027 COTTER | CONCORD | ETL.5462.INSL | 2023-04-06 | 2023-04-03 | 2023-12-14 | On-time | 2024-04-02 | 110 | 2024-04-03 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45997062 | T2 DI PTSBRG SN MTO 06/027 COTTER | ICS
LC | 125810436 | 016/371 | T2 EI DRM-GRSS VLLY-WIMR 16/371 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2023-04-06 | 2023-04-06 |  | Late | 2024-04-05 |  | 2024-04-06 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493701 | T2 EI DRM-GRSS VLLY-WIMR 16/371 RPL POLE | 70Y
LC | 125811186 | 008/202 | T2 DI CLGTE GRS VLY 08/202 REFRAME | SACTO | ETL.6490.POLE.WOOD | 2023-04-06 | 2023-04-03 | 2024-03-05 | On-time | 2024-04-02 | 28 | 2024-04-03 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35493425 | T2 DI CLGTE GRS VLY 08/202 REFRAME | 93E
LC | 125813626 | 019/436 | T2 DI DRM GRS VLY WMR 19/436 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2023-04-06 | 2023-04-03 | 2024-01-22 | On-time | 2024-04-02 | 71 | 2024-04-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999261 | T2 DI DRM GRS VLY WMR 19/436 RPR GYWW | ICW
LC | 125813753 | 019/436 | T2 DI DRM GRS VLY WMR 19/436 REFRAME | SACTO | ETL.6760.POLE.WOOD | 2023-04-06 | 2023-04-03 | 2024-03-28 | On-time | 2024-04-02 | 5 | 2024-04-03 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35493242 | T2 DI DRM GRS VLY WMR 19/436 REFRAME | 93E
LC | 125823252 | 004/123 | T2 DI CLGT-GRSS VLLY 4/123 COMPLETED | SACTO | ETL.6490.POLE.WOOD | 2023-04-07 | 2023-04-03 | 2024-03-08 | On-time | 2024-04-02 | 25 | 2024-04-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493422 | T2 DI CLGT-GRSS VLLY 4/123 RPL STRW | 70Y
LC | 125810870 | A014/303 | T2 EI SALINAS-LAURELES A14/303 RPR INSW | MOSSLNDG | ETL.7930.INSL | 2023-04-06 | 2023-04-06 | 2024-04-25 | Late | 2024-04-05 | -20 | 2024-04-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081073 | T2 EI SALINAS-LAURELES A14/303 RPR INSW | ICW
LC | 125824286 | 011/266 | T2 DI COLGATE-GRSS VLLY 11/266 RPL INSW | SACTO | ETL.6490.INSL | 2023-04-07 | 2023-04-03 | 2024-03-16 | On-time | 2024-04-02 | 17 | 2024-04-05 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493436 | T2 DI COLGATE-GRSS VLLY 11/266 RPL INSW | 93I
LC | 125853645 | 011/262 | T2 DI CLGTE GRS VLY 11/262 RPL STRW | SACTO | ETL.6490.POLE.WOOD | 2023-04-10 | 2023-04-03 | 2024-03-16 | On-time | 2024-04-02 | 17 | 2024-04-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493433 | T2 DI CLGTE GRS VLY 11/262 RPL STRW | 70Y
LC | 125811259 | 002/025 | T2 DI NARROWS #1 TAP 002/025 RMV VEG | SACTO | ETL.6511.POLE.WDPS | 2023-04-06 | 2023-03-21 |  | Late | 2024-03-20 |  | 2023-09-21 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 125866998 | 010/231 | T2 DI COLGATE-GRAS VALY-10/231R RPR STRW | SACTO | ETL.6490.POLE.WDPS | 2023-04-11 | 2023-04-03 | 2024-01-29 | On-time | 2024-04-02 | 64 | 2024-04-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999241 | T2 DI COLGATE-GRAS VALY-10/231R RPR STRW | ICW
LC | 125904905 | 004/124 | T2 DI COLGATE-GRAS VALLEY 4/124 RPR GYWW | SACTO | ETL.6490.POLE.WOOD | 2023-04-13 | 2023-04-03 | 2023-12-20 | On-time | 2024-04-02 | 104 | 2024-04-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999242 | T2 DI COLGATE-GRAS VALLEY 4/124 RPR GYWW | ICW
LC | 125904907 | 004/124 | T2 DI COLGATE-GRAS VALLEY 4/124 REFRAME | SACTO | ETL.6490.POLE.WOOD | 2023-04-13 | 2023-04-03 | 2024-03-08 | On-time | 2024-04-02 | 25 | 2024-04-03 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35495860 | T2 DI COLGATE-GRSS VLY 4/116 REFRAME | 93E
LC | 125908059 | 011/267 | T2 DI CLGT-GRSS VLLY 11/267 RPR ANCW | SACTO | ETL.6490.POLE.WOOD | 2023-04-14 | 2023-04-03 | 2024-01-30 | On-time | 2024-04-02 | 63 | 2024-04-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45999244 | T2 DI CLGT-GRSS VLLY 11/267 RPR ANCW | ICW
LC | 125812626 | 008/048 | T2 EI VACA-BAHIA 008/048 RPL DMPS | SACTO | ETL.5810.INSL | 2023-04-06 | 2023-04-06 |  | Late | 2024-04-05 |  | 2024-04-06 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 45985055 | T2 EI VACA-BAHIA 008/048 RPL DMPS | ICS
LC | 125812689 | 000/006 | T2 DI MONTICELLO PH TAP 0/6 RPL STRW | LAKEVLLE | ETL.1602.POLE.WOOD | 2023-04-06 | 2023-03-29 |  | Late | 2024-03-28 |  | 2024-03-29 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35548369 | T2 DI MONTICELLO PH TAP 0/6 RPL STRW | 70Y
LC | 125812730 | 029/000 | T2 EI PHILO JCT-ELK 29/0 RPL INSW | WILLITS | ETL.7780.INSL.NCER | 2023-04-06 | 2023-04-06 | 2024-06-18 | Late | 2024-04-05 | -74 | 2024-04-06 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493707 | T2 EI PHILO JCT-ELK 29/0 RPL INSW | 93I
LC | 125908138 | 018/409 | T2 DI DRM-GRSS VLLY-WMR 18/409 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2023-04-14 | 2023-04-03 | 2024-03-26 | On-time | 2024-04-02 | 7 | 2024-04-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493246 | T2 DI DRM-GRSS VLLY-WMR 18/409 RPL STRW | 70Y
LC | 125813119 | 023/003A | T2 EI FORT BRAGG-ELK 23/03A RPL POLE | WILLITS | ETL.2060.POLE.WOOD | 2023-04-06 | 2023-03-25 | 2024-04-17 | Late | 2024-03-24 | -24 | 2024-03-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487232 | T2 EI FORT BRAGG-ELK 23/03A RPL POLE | 70Y
LC | 125813177 | 023/003C | T2 EI FORT BRAGG-ELK 23/03C RPL POLE | WILLITS | ETL.2060.POLE.WOOD | 2023-04-06 | 2023-03-25 | 2024-04-17 | Late | 2024-03-24 | -24 | 2024-03-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487232 | T2 EI FORT BRAGG-ELK 23/03A RPL POLE | 70Y
LC | 125916911 | 005/146 | T2 DI COLGATE-GRSS VLY 5/146 RPR SPLW | SACTO | ETL.6490.INSL | 2023-04-14 | 2023-04-03 | 2023-12-20 | On-time | 2024-04-02 | 104 | 2024-04-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45999245 | T2 DI COLGATE-GRSS VLY 5/146 RPR SPLW | ICW
LC | 125813451 | 028/004 | T2 EI PHILO JCT-ELK 28/4 RPL DMPW | WILLITS | ETL.7780.INSL.NCER | 2023-04-06 | 2023-04-06 | 2024-06-06 | Late | 2024-04-05 | -62 | 2024-04-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46213881 | T2 EI PHILO JCT-ELK 28/4 RPL DMPW | ICW
LC | 125813503 | 001/000 | T2 DI MELONES-CURTIS 001/000C INS HRDD | VICTOR | ETL.2390.POLE.WDPS | 2023-04-06 | 2023-03-30 | 2024-05-17 | Late | 2024-03-29 | -49 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45990639 | T2 DI MELONES-CURTIS 001/000 INS HRDD | ICW
LC | 125813505 | 001/000 | T2 DI MELONES-CURTIS 001/000R INS HRDD | VICTOR | ETL.2390.POLE.WDPS | 2023-04-06 | 2023-03-30 | 2024-05-17 | Late | 2024-03-29 | -49 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45991340 | T2 DI MELONES-CURTIS 001/000 INS HRDD | ICW
LC | 125813507 | 001/000 | T2 DI MELONES-CURTIS 001/000R RPR GYWW | VICTOR | ETL.2390.POLE.WDPS | 2023-04-06 | 2023-03-30 | 2024-05-17 | Late | 2024-03-29 | -49 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45991341 | T2 DI MELONES-CURTIS 001/000 RPR GYWW | ICW
LC | 125813590 | 001/000 | T2 DI MELONES-CURTIS 001/000C RPR GYWW | VICTOR | ETL.2390.POLE.WDPS | 2023-04-06 | 2023-03-30 | 2024-05-17 | Late | 2024-03-29 | -49 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45991342 | T2 DI MELONES-CURTIS 001/000 RPR GYWW | ICW
LC | 125813593 | 001/000 | T2 DI MELONES-CURTIS 001/000L RPR GYWW | VICTOR | ETL.2390.POLE.WDPS | 2023-04-06 | 2023-03-30 | 2024-05-17 | Late | 2024-03-29 | -49 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45991343 | T2 DI MELONES-CURTIS 001/000 RPR GYWW | ICW
LC | 125920446 | 011/261 | T2 DI CLGAT-GRS VLY 11/261 RPL CRSW | SACTO | ETL.6490.POLE.WOOD | 2023-04-14 | 2023-04-03 | 2024-03-16 | On-time | 2024-04-02 | 17 | 2024-04-03 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35493430 | T2 DI CLGAT-GRS VLY 11/261 RPL CRSW | 93E
LC | 125921261 | 004/116 | T2 DI COLGATE-GRSS VLY 4/116 COMPLETED | SACTO | ETL.6490.POLE.WOOD | 2023-04-14 | 2023-04-03 | 2024-03-08 | On-time | 2024-04-02 | 25 | 2024-04-03 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35495860 | T2 DI COLGATE-GRSS VLY 4/116 REFRAME | 93E
LC | 125923528 | 010/243 | T2 DI CLGAT-GRS VLY 10/243 RPL POLE | SACTO | ETL.6490.POLE.WOOD | 2023-04-14 | 2023-04-03 | 2024-03-19 | On-time | 2024-04-02 | 14 | 2024-04-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493428 | T2 DI CLGAT-GRS VLY 10/243 RPL POLE | 70Y
LC | 125816321 | 029/015 | T2 DI FULTON HOPLAND 029/015 RPR POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-04-06 | 2023-04-03 |  | Late | 2024-04-02 |  | 2024-04-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46045910 | T2 DI FULTON HOPLAND 029/015 RPR POLE | ICW
LC | 125816528 | 015/010 | T2 EI FULTON-HOPLAND 15/10 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-04-06 | 2023-04-06 |  | Late | 2024-04-05 |  | 2024-04-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46045914 | T2 EI FULTON-HOPLAND 015/010 RPR POLE | ICW
LC | 125816933 | 027/389 | T2 DI GOLD HILL#1 027/389 RPL POLE | SACTO | ETL.6950.POLE.WOOD | 2023-04-06 | 2023-04-04 | 2024-04-07 | Late | 2024-04-03 | -4 | 2024-04-04 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493225 | T2 DI GOLD HILL#1 027/389 RPL POLE | 70Y
LC | 125923764 | 001/033 | T2 DI COLGATE-GRSS VLY 1/33 RPR WDPK | SACTO | ETL.6490.POLE.WOOD | 2023-04-14 | 2023-04-03 | 2024-01-29 | On-time | 2024-04-02 | 64 | 2024-04-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999247 | T2 DI COLGATE-GRSS VLY 1/33 RPR WDPK | ICW
LC | 125926842 | 012/303 | T2 DI CLGAT-GRS VLY 12/303 RPL STRW | SACTO | ETL.6490.POLE.WOOD | 2023-04-15 | 2023-04-03 | 2024-03-14 | On-time | 2024-04-02 | 19 | 2024-04-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493318 | T2 DI CLGAT-GRS VLY 12/303 RPL STRW | 70Y
LC | 125926895 | 011/263 | T2 DI CLGAT-GRS VLY 11/263 RPL POLE | SACTO | ETL.6490.POLE.WOOD | 2023-04-15 | 2023-04-03 | 2024-03-16 | On-time | 2024-04-02 | 17 | 2024-04-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493434 | T2 DI CLGAT-GRS VLY 11/263 RPL POLE | 70Y
LC | 125820227 | 002/066 | T2 DI DLTA-MTN GT JCT 2/66 RPL INSW | TABLEMTN | ETL.6750.INSL | 2023-04-07 | 2023-03-30 |  | Late | 2024-03-29 |  | 2024-03-30 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35491976 | T2 DI DLTA-MTN GT JCT 2/66 RPL INSW | 93I
LC | 125820272 | 003/011 | T2 DI LAYTONVILLE-COVELO 03/011 RPL POLE | WILLITS | ETL.7390.POLE.WOOD | 2023-04-07 | 2023-03-23 |  | Late | 2024-03-22 |  | 2024-03-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35489716 | T2 DI LAYTONVILLE-COVELO 03/011 RPL POLE | 70Y
LC | 125820791 | 045/009 | T2 DI FT RSS-GUALALA 45/9 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-04-07 | 2023-03-29 |  | Late | 2024-03-28 |  | 2024-03-29 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487982 | T2 DI FT RSS-GUALALA 45/9 RPL STRW | 70Y
LC | 125926936 | 004/120 | T2 DI CLGAT-GRS VLY 4/120 CANCEL | SACTO | ETL.6490.POLE.WOOD | 2023-04-15 | 2023-04-03 | 2024-03-08 | On-time | 2024-04-02 | 25 | 2024-04-03 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35495860 | T2 DI COLGATE-GRSS VLY 4/116 REFRAME | 93E
LC | 125821138 | A013/289 | T2 EI SALINAS-LAURELES A013/289 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-04-07 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35507041 | T2 EI SALINAS-LAURELES A013/289 RPL POLE | 70Y
LC | 125926945 | 008/206 | T2 DI CLGAT-GRS VLY 08/206 REFRAME | SACTO | ETL.6490.POLE.WOOD | 2023-04-15 | 2023-04-03 | 2024-03-14 | On-time | 2024-04-02 | 19 | 2024-04-03 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35495862 | T2 DI COLGATE-GRS VLLY 8/198 REFRAME | 93E
LC | 125821291 | 052/005 | T2 DI ELK-GUALALA 052/005 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-04-07 | 2023-03-24 | 2024-04-24 | Late | 2024-03-23 | -32 | 2024-03-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487316 | T2 DI ELK-GUALALA 054/008 RPL POLE | 70Y
LC | 125927276 | 012/301 | T2 DI CLGAT-GRS VLY 12/301 RPR GYWW | SACTO | ETL.6490.POLE.NWOD | 2023-04-15 | 2023-04-03 | 2024-01-30 | On-time | 2024-04-02 | 63 | 2024-04-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999301 | T2 DI CLGAT-GRS VLY 12/301 RPR GYWW | ICW
LC | 125927327 | 011/260 | T2 DI CLGAT-GRS VLY 11/260 RPL POLE | SACTO | ETL.6490.POLE.WOOD | 2023-04-15 | 2023-04-03 | 2024-03-16 | On-time | 2024-04-02 | 17 | 2024-04-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493429 | T2 DI CLGAT-GRS VLY 11/260 RPL POLE | 70Y
LC | 125821879 | 042/005 | T2 DI FORT ROSS-GUALALA 42/5 RPR STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-04-07 | 2023-03-23 |  | Late | 2024-03-22 |  | 2024-03-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46044515 | T2 DI FORT ROSS-GUALALA 42/5 RPR STRW | ICW
LC | 125927370 | 008/205 | T2 DI CLGAT-GRS VLY 8/205 RPR INSW | SACTO | ETL.6490.INSL.NCER | 2023-04-15 | 2023-04-03 | 2023-12-20 | On-time | 2024-04-02 | 104 | 2024-04-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999250 | T2 DI CLGAT-GRS VLY 8/205 RPR INSW | ICW
LC | 125927378 | 004/102 | T2 DI CLGAT-GRS VLY 04/102 RPL SPLW | SACTO | ETL.6490.INSL | 2023-04-15 | 2023-04-03 | 2024-03-09 | On-time | 2024-04-02 | 24 | 2024-04-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Replace | 45999251 | T2 DI CLGAT-GRS VLY 04/102 RPL SPLW | ICW
LC | 125997665 | 005/050 | T2 EI HLSDLE JT-HLF MN BY 5/50R RPL POLE | METCALF | ETL.7060.POLE.WDPS | 2023-04-26 | 2023-04-03 | 2023-06-28 | On-time | 2024-04-02 | 279 | 2024-04-03 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31649134 | T2 EI HLSDLE JT-HLF MN BY 5/50L RPL POLE | 70Y
LC | 125822112 | A013/287 | T2 EI SALINAS-LAURELES A013/287 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-04-07 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507040 | T2 DI SALINAS-LAUR A12/268-GUY RPL STRW | 70Y
LC | 127423202 | 042/189 | T2 EI ROUND MT-TBLE MT#2 42/189 RPR GYWT | TABLEMTN | ETL.6070.TOWR | 2023-11-06 | 2023-04-03 | 2024-03-12 | On-time | 2024-04-02 | 21 | 2024-04-03 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46073695 | T2 EI ROUND MT-TBLE MT#2 42/189 RPR GYWT | ICQ
LC | 125822451 | 045/006 | T2 DI FORT ROSS-GUALALA 45/6 RPL HRDW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-04-07 | 2023-03-23 | 2024-06-24 | Late | 2024-03-22 | -94 | 2024-03-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46044516 | T2 DI FORT ROSS-GUALALA 45/6 RPL HRDW | ICW
LC | 125822488 | 014/335 | T2 DI DRM-GSS VLL-WMR 14/335 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2023-04-07 | 2023-04-03 |  | Late | 2024-04-02 |  | 2024-04-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493245 | T2 DI DRM-GSS VLL-WMR 14/335 RPL POLE | 70Y
LC | 125822500 | 000/008 | T2 DI FORT BRAGG-ELK 0/8 RPL INSW | WILLITS | ETL.2060.INSL.NCER | 2023-04-07 | 2023-03-24 | 2024-04-08 | Late | 2024-03-23 | -16 | 2024-03-24 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35487135 | T2 DI FORT BRAGG-ELK 0/8 RPLC INSW | 93I
LC | 125822560 | 000/008 | T2 DI FORT BRAGG-ELK 0/8 RPL HRDW | WILLITS | ETL.2060.POLE.WOOD | 2023-04-07 | 2023-03-24 | 2024-04-08 | Late | 2024-03-23 | -16 | 2024-03-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46089319 | T2 DI FORT BRAGG-ELK 0/8 RPLC HRDW | ICW
LC | 125790528 | 005/076 | T2 EI KESWICK-TRINITY 005/076R RPL STRW | TABLEMTN | ETL.7270.POLE.WDPS | 2023-04-04 | 2023-04-04 | 2024-03-24 | On-time | 2024-04-03 | 10 | 2024-04-04 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493249 | T2 EI KESWICK-TRINITY 005/076R RPL STRW | 70Y
LC | 125822881 | 046/005 | T2 DI FORT ROSS-GUALALA 46/5 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-04-07 | 2023-03-23 |  | Late | 2024-03-22 |  | 2024-03-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487983 | T2 DI FORT ROSS-GUALALA 46/5 RPL STRW | 70Y
LC | 125790567 | 005/076 | T2 EI KESWICK-TRINITY 005/076C RPL STRW | TABLEMTN | ETL.7270.POLE.WDPS | 2023-04-04 | 2023-04-04 | 2024-03-24 | On-time | 2024-04-03 | 10 | 2024-04-04 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493249 | T2 EI KESWICK-TRINITY 005/076R RPL STRW | 70Y
LC | 125790865 | 018/157 | T2 EI CRAG VIEW-CASCADE 018/157 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-04 | 2023-04-04 | 2024-02-29 | On-time | 2024-04-03 | 34 | 2024-04-04 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 125791462 | 094/479 | T2 MALIN-ROUND MTN #2 94/479 COMPLETE | TABLEMTN | ETL.6020.TOWR | 2023-04-04 | 2023-04-04 | 2023-06-26 | On-time | 2024-04-03 | 282 | 2024-04-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45716079 | T2 MALIN-ROUND MTN #2 -_94/479 RPR FOUND | ICQ
LC | 125823035 | 005/000 | T2 DI LAYTONVILLE-COVELO 5/0 RPL STRW | WILLITS | ETL.7390.POLE.WOOD | 2023-04-07 | 2023-03-23 |  | Late | 2024-03-22 |  | 2024-03-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35489716 | T2 DI LAYTONVILLE-COVELO 03/011 RPL POLE | 70Y
LC | 125791470 | 014/001 | T2 EI FORT BRAGG-ELK 14/1 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-04-04 | 2023-04-04 | 2024-02-28 | On-time | 2024-04-03 | 35 | 2024-04-04 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487928 | T2 EI FORT BRAGG-ELK 14/1 RPL STRW | 70Y
LC | 125791810 | 008/004A | T2 CLEAR LAKE-HOPLAND 008/004A COTTER | WILLITS | ETL.6390.INSL.NCER | 2023-04-04 | 2023-04-04 | 2023-10-20 | On-time | 2024-04-03 | 166 | 2024-04-04 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46007997 | T2 CLEAR LAKE-HOPLAND 008/004A COTTER | ICS
LC | 125823364 | 000/002 | T2 DI SMARTVILL-CMP FAR WST 0/2 RPR POLE | SACTO | ETL.7970.POLE.WOOD | 2023-04-07 | 2023-04-05 |  | Late | 2024-04-04 |  | 2023-10-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999315 | T2 DI SMARTVILL-CMP FAR WST 0/2 RPR POLE | ICW
LC | 125791958 | 006/146 | T2 DEL MNTE-VJO-VJO 6/146 RPR INSW | MOSSLNDG | ETL.6710.INSL.CERA | 2023-04-04 | 2023-04-04 | 2024-02-14 | On-time | 2024-04-03 | 49 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46174863 | T2 DEL MNTE-VJO-VJO 6/146 RPR INSW | ICW
LC | 125792005 | 016/138 | T2 EI CRAG VIEW-CSCD 016/138 RPL INSW | TABLEMTN | ETL.1350.INSL.CERA | 2023-04-04 | 2023-04-04 | 2024-02-26 | On-time | 2024-04-03 | 37 | 2024-04-04 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35494032 | T2 EI CRAG VIEW-CSCD 016/138 RPL INSW | 93I
LC | 125823691 | 009/127 | T2 DI JOLON TAP 009/027 RMV VEG | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-04-07 | 2023-03-27 |  | Late | 2024-03-26 |  | 2024-03-27 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 125823822 | 029/005 | T2 EI PHILO JCT-ELK 029/005 RPR INSW | WILLITS | ETL.7780.INSL.CERA | 2023-04-07 | 2023-04-07 | 2024-06-10 | Late | 2024-04-06 | -65 | 2024-04-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46213876 | T2 EI PHILO JCT-ELK 029/005 RPR INSW | ICW
LC | 125792878 | 000/009 | T2 WV MENDOCINO-UKIAH 000/009 RPR GYWS | WILLITS | ETL.2420.POLE.WOOD | 2023-04-04 | 2023-04-04 | 2023-10-23 | On-time | 2024-04-03 | 163 | 2024-04-04 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45740034 | T2 WV MENDOCINO-UKIAH 000/009 RPR GYWS | ICW
LC | 125824056 | 000/011 | T2 DI MELONES-CURTIS 0/11 RPL DAMW | VICTOR | ETL.2390.INSL.CERA | 2023-04-07 | 2023-03-30 | 2024-05-15 | Late | 2024-03-29 | -47 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 45991344 | T2 DI MELONES-CURTIS 0/11 RPL DAMW | ICW
LC | 125792991 | 007/090 | T2 EI GOLD HILL #1 7/90 COTR KEY | SACTO | ETL.6950.INSL.NCER | 2023-04-04 | 2023-04-04 | 2024-01-26 | On-time | 2024-04-03 | 68 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46030909 | T2 EI GOLD HILL #1 7/90 COTR KEY | ICW
LC | 125793042 | 008/169 | T2 EI MONTA VISTA-LS GTS 8/169 RPR POLE | METCALF | ETL.7610.POLE.WOOD | 2023-04-04 | 2023-04-04 | 2023-12-08 | On-time | 2024-04-03 | 117 | 2024-04-04 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45997150 | T2 EI MONTA VISTA-LS GTS 8/169 RPR POLE | ICW
LC | 125793348 | 065/273 | T2NT EI RND MT-TBL MTN #1-_65/273 RPL HD | TABLEMTN | ETL.6060.TOWR | 2023-04-04 | 2023-04-04 | 2023-11-06 | On-time | 2024-04-03 | 149 | 2024-04-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46008775 | T2NT EI RND MT-TBL MTN #1-_65/273 RPL HD | ICQ
LC | 125824323 | 036/001 | T2 DI PHLO JT ELK 36/1 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-04-07 | 2023-04-06 | 2024-05-24 | Late | 2024-04-05 | -49 | 2024-04-06 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31644225 | T2 DI PHLO JT ELK 36/1 RPL POLE | 70Y
LC | 125825001 | 024/003 | T2 DI MI-WUK-CURTIS 24/3L RPL STRW | VICTOR | ETL.1073.POLE.WDPS | 2023-04-07 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35551320 | T2 DI MI-WUK-CURTIS 24/1 RPL POLE | 70Y
LC | 125825009 | 024/003 | T2 DI MI-WUK-CURTIS 24/3R RPL STRW | VICTOR | ETL.1073.POLE.WDPS | 2023-04-07 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35551320 | T2 DI MI-WUK-CURTIS 24/1 RPL POLE | 70Y
LC | 125793350 | 008/167 | T2 EI MONTA VIST-LS GTS -_8/167 RPL POLE | METCALF | ETL.7610.POLE.WOOD | 2023-04-04 | 2023-04-04 | 2024-02-13 | On-time | 2024-04-03 | 50 | 2024-04-04 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507609 | T2 EI MONTA VIST-LS GTS -_8/167 RPL POLE | 70Y
LC | 125793389 | 008/166 | T2 EI MONTA VISTA-LS GTS -_8/166 RPR INS | METCALF | ETL.7610.INSL.NCER | 2023-04-04 | 2023-04-04 | 2024-02-12 | On-time | 2024-04-03 | 51 | 2024-04-04 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999086 | T2 EI MONTA VISTA-LS GTS -_8/166 RPR INS | ICW
LC | 125827110 | 031/000 | T2 EI PHILO JCT-ELK 31/0 COMPLETE | WILLITS | ETL.7780.POLE.WOOD | 2023-04-07 | 2023-04-07 | 2024-06-15 | Late | 2024-04-06 | -70 | 2024-04-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35493858 | T2 EI PHILO JCT-ELK 31/0 RPL POLE | 70Y
LC | 125793824 | 006/137 | T2 COLEMAN-SOUTH 006/137 RPL DMPW | TABLEMTN | ETL.6450.INSL.CERA | 2023-04-04 | 2023-04-04 | 2024-01-08 | On-time | 2024-04-03 | 86 | 2024-04-04 | 630 | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 45999462 | T2 COLEMAN-SOUTH 006/137 RPL DMPW | ICW
LC | 125829195 | 030/007 | T2 EI PHILO JCT-ELK 30/7 CNCL | WILLITS | ETL.7780.POLE.WDPS | 2023-04-08 | 2023-04-08 |  | Late | 2024-04-07 |  | 2024-04-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46213875 | T2 EI PHILO JCT-ELK 30/7 RPR HRDW | ICW
LC | 125829285 | 016/375 | T2 EI DRM-GRSS VLLY-WIMR 16/375 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2023-04-08 | 2023-04-08 |  | Late | 2024-04-07 |  | 2024-04-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46011661 | T2 EI DRM-GRSS VLLY-WIMR 16/375 RPR POLE | ICW
LC | 125829411 | 031/002 | T2 EI PHILO JCT-ELK 31/2 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-04-08 | 2023-04-08 | 2024-06-13 | Late | 2024-04-07 | -67 | 2024-04-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494212 | T2 EI PHILO JCT-ELK 31/2 RPL POLE | 70Y
LC | 125829645 | 016/001 | T2 EI FULTON-HOPLAND 016/001 RPL HRDW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-04-08 | 2023-04-08 |  | Late | 2024-04-07 |  | 2024-04-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46045915 | T2 EI FULTON-HOPLAND 016/001 RPL HRDW | ICW
LC | 125793862 | 029/175 | T2 EI TEMBLR-SN LUS OBSP 29/175 RPL INST | PISMOBCH | ETL.3960.INSL.CERA | 2023-04-04 | 2023-04-04 | 2024-04-01 | On-time | 2024-04-03 | 2 | 2024-04-04 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674043 | T2 EI TEMBLR-SN LUS OBSP 29/175 RPL INST | 93K
LC | 125794279 | 044/196 | T2 EI RND MTN-TBL MTN #1 -_44/196 RPL GY | TABLEMTN | ETL.6060.TOWR | 2023-04-04 | 2023-04-04 | 2023-05-24 | On-time | 2024-04-03 | 315 | 2023-07-04 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Replace | 45726323 | T2 EI RND MTN-TBL MTN #1 -_44/196 RPL GY | ICS
LC | 125794334 | 017/388 | T2 EI DRM-GRSS VLY-WMR 17/388 RPR GYWW | SACTO | ETL.6760.POLE.WOOD | 2023-04-04 | 2023-04-04 | 2023-04-25 | On-time | 2024-04-03 | 344 | 2023-07-04 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45739536 | T2 EI DRM-GRSS VLY-WMR 17/388 RPR GYWW | ICW
LC | 125829828 | B000/019 | T2 EI COLGATE-CHALLENGE B0/19 RPL POLE | SACTO | ETL.6480.POLE.WOOD | 2023-04-08 | 2023-04-08 |  | Late | 2024-04-07 |  | 2023-10-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35545654 | T2 EI COLGATE-CHALLENGE B0/19 RPL POLE | 70Y
LC | 125830087 | 016/002 | T2 EI FULTON-HOPLAND 16/2 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-04-08 | 2023-04-08 | 2024-05-17 | Late | 2024-04-07 | -40 | 2024-04-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46045917 | T2 EI FULTON-HOPLAND 016/002 RPR POLE | ICW
LC | 125794372 | 015/134 | T2 EI CRAG VIEW-CASCADE 015/134 RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-04 | 2023-04-04 | 2024-02-01 | On-time | 2024-04-03 | 62 | 2024-04-04 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45999460 | T2 EI CRAG VIEW-CASCADE 015/134 RPR GYWW | ICS
LC | 125794449 | 015/134 | T2 EI CRAG VIEW-CASCADE 015/134 RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-04 | 2023-04-04 | 2024-02-01 | On-time | 2024-04-03 | 62 | 2024-04-04 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999439 | T2 EI CRAG VIEW-CASCADE 015/134 RPR GYWW | ICW
LC | 125794658 | 015/134 | T2 EI CRAG VIEW-CASCADE 015/134 RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-04 | 2023-04-04 | 2024-02-01 | On-time | 2024-04-03 | 62 | 2024-04-04 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999438 | T2 EI CRAG VIEW-CASCADE 015/134 RPR GYWW | ICW
LC | 125794886 | 029/174 | T2 EI TEMBLR-SN LUS OBSP 29/174 RPL INST | PISMOBCH | ETL.3960.INSL.CERA | 2023-04-04 | 2023-04-04 | 2024-04-02 | On-time | 2024-04-03 | 1 | 2024-04-04 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674043 | T2 EI TEMBLR-SN LUS OBSP 29/175 RPL INST | 93K
LC | 125795253 | 015/288 | T2 EI FULTON-MOLINO-CTATI 15/288 RMV VEG | LAKEVLLE | ETL.6910.POLE.WOOD | 2023-04-04 | 2023-04-04 | 2023-10-11 | On-time | 2024-04-03 | 175 | 2024-04-04 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Trim
LC | 125795655 | 014/009 | T2 EI FORT BRAGG-ELK 014/009 COTTER | WILLITS | ETL.2060.INSL.CERA | 2023-04-04 | 2023-04-04 | 2024-03-04 | On-time | 2024-04-03 | 30 | 2024-04-04 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46089757 | T2 EI FORT BRAGG-ELK 014/009 COTTER | ICW
LC | 125831396 | 010/009 | T2 EI FORT BRAGG-ELK 10/9 GO95 RPL | WILLITS | ETL.2060.POLE.WOOD | 2023-04-08 | 2023-04-08 |  | Late | 2024-04-07 |  | 2024-04-08 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35488004 | T2 EI FORT BRAGG-ELK 10/9 GO95 | 93G
LC | 125831436 | 032/001 | T2 EI PHILO JCT-ELK 032/001 RPR POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-04-08 | 2023-04-08 | 2024-06-17 | Late | 2024-04-07 | -71 | 2024-04-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46213874 | T2 EI PHILO JCT-ELK 032/001 RPR POLE | ICW
LC | 125795955 | 005/076 | T2 EI KESWICK-TRINITY 005/076L RPL STRW | TABLEMTN | ETL.7270.POLE.WDPS | 2023-04-04 | 2023-04-04 | 2024-03-24 | On-time | 2024-04-03 | 10 | 2024-04-04 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493249 | T2 EI KESWICK-TRINITY 005/076R RPL STRW | 70Y
LC | 125795957 | 006/088A | T2 EI KESWICK-TRINITY 6/88A COTR KEY | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-04 | 2023-04-04 | 2024-03-26 | On-time | 2024-04-03 | 8 | 2024-04-04 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45999463 | T2 EI KESWICK-TRINITY 6/88A COTR KEY | ICS
LC | 125844483 | 002/006 | 2 DI MNDCN-PHL JCT -HPLND 2/6 RPL STRW | WILLITS | ETL.7520.POLE.WOOD | 2023-04-10 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493829 | T2 DI MNDCN-PHL JCT -HPLND 2/6 RPL STRW | 70Y
LC | 125844838 | 015/356 | T2 EI DRM-GRSS VLY-WMR 15/356 RPR INSW | SACTO | ETL.6760.INSL.CERA | 2023-04-10 | 2023-04-10 |  | Late | 2024-04-09 |  | 2024-04-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011665 | T2 EI DRM-GRSS VLY-WMR 15/356 RPR INSW | ICW
LC | 125844983 | 030/520 | T2 EI KESWICK-TRINITY 030/520 REM VEG | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-10 | 2023-04-10 |  | Late | 2024-04-09 |  | 2024-04-10 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 125844984 | 030/520 | T2 EI KESWICK-TRINITY 030/520 RPR CNDW | TABLEMTN | ETL.7270.INSL.CERA | 2023-04-10 | 2023-04-10 | 2024-04-30 | Late | 2024-04-09 | -21 | 2024-04-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46011762 | T2 EI KESWICK-TRINITY 030/520 RPR CNDW | ICW
LC | 125796234 | 157 | T2 EI MELONES-CURTIS 9/2A RPR SWITCH | VICTOR | ETL.2390.SWIT | 2023-04-04 | 2023-04-04 | 2023-10-02 | On-time | 2024-04-03 | 184 | 2024-04-04 | 623 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 45952212 | T2 EI MELONES-CURTIS 9/2A RPR SWITCH | ICE
LC | 125802273 | 044/197 | T2 EI RND MTN-TBLE MTN #2 44/197 BNT STL | TABLEMTN | ETL.6070.TOWR | 2023-04-05 | 2023-04-04 | 2024-03-20 | On-time | 2024-04-03 | 14 | 2024-04-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008774 | T2 EI RND MTN-TBLE MTN #2 44/197 BNT STL | ICQ
LC | 125822140 | 006/061 | T2 DI GOLD HILL #1 6/61 COTTER | SACTO | ETL.6950.INSL.NCER | 2023-04-07 | 2023-04-04 | 2024-04-03 | On-time | 2024-04-03 | 0 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999262 | T2 DI GOLD HILL #1 6/61 COTTER | ICW
LC | 125846135 | 017/003 | T2 EI FULTON-HOPLAND -_017/003 RPL POLE | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-04-10 | 2023-04-10 |  | Late | 2024-04-09 |  | 2024-04-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521322 | T2 EI FULTON-HOPLAND -_017/003 RPL POLE | 70Y
LC | 125824120 | 008/190 | T2 DI CLGT-GRS VLY 8/190 RPL HRDW | SACTO | ETL.6490.POLE.WOOD | 2023-04-07 | 2023-04-04 | 2023-12-20 | On-time | 2024-04-03 | 105 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45999263 | T2 DI CLGT-GRS VLY 8/190 RPL HRDW | ICW
LC | 125846235 | 003/004 | T2 EI PHILO JCT-ELK 003/004 RPR POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-04-10 | 2023-04-10 | 2024-04-30 | Late | 2024-04-09 | -21 | 2024-04-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46089835 | T2 EI PHILO JCT-ELK 003/004 RPR POLE | ICW
LC | 125846366 | 013/101 | T2 DI TIGER CRK-ELECTRA 13/101 RPL INSS | VICTOR | ETL.5780.INSL | 2023-04-10 | 2023-04-06 |  | Late | 2024-04-05 |  | 2024-04-06 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674176 | T2 DI TIGER CRK-ELECTRA 13/101 RPL INSS | 93K
LC | 125844278 | 044/198 | T2 EI ROND MTN-TBL MT #1 44/198 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2023-04-10 | 2023-04-04 | 2024-03-07 | On-time | 2024-04-03 | 27 | 2024-04-04 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46008082 | T2 EI ROND MTN-TBL MT #1 44/198 RPR GYWS | ICS
LC | 125846463 | 015/360 | T2 EI DRM-GRSS VLY-WMR 15/360 RPL TIED | SACTO | ETL.6760.INSL.CERA | 2023-04-10 | 2023-04-10 |  | Late | 2024-04-09 |  | 2023-07-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46227670 | T2 EI DRM-GRSS VLY-WMR 15/360 RPL TIED | ICW
LC | 125846465 | 015/360 | T2 EI DRM-GRSS VLY-WMR 15/360 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2023-04-10 | 2023-04-10 |  | Late | 2024-04-09 |  | 2024-04-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495125 | T2 EI DRM-GRSS VLY-WMR 15/360 RPL STRW | 70Y
LC | 125845416 | 023/348 | T2 DI GOLD HILL #1 023/348 RPL INSW | SACTO | ETL.6950.INSL.CERA | 2023-04-10 | 2023-04-04 | 2023-10-16 | On-time | 2024-04-03 | 170 | 2024-04-04 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493226 | T2 DI GOLD HILL #1 023/348 RPL INSW | 93I
LC | 125850451 | 008/108 | T2 DI GOLD HILL #1 008/108 RPR GYWW | SACTO | ETL.6950.POLE.WOOD | 2023-04-10 | 2023-04-04 | 2024-04-01 | On-time | 2024-04-03 | 2 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999265 | T2 DI GOLD HILL #1 008/108 RPR GYWW | ICW
LC | 125850583 | 008/108 | T2 DI GOLD HILL #1 008/108 RPL INSW | SACTO | ETL.6950.INSL.NCER | 2023-04-10 | 2023-04-04 | 2024-04-01 | On-time | 2024-04-03 | 2 | 2024-04-04 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493228 | T2 DI GOLD HILL #1 008/108 RPL INSW | 93I
LC | 125846725 | 000/004 | T2 DI MELONES-CURTIS 0/004 RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2023-04-10 | 2023-04-06 | 2024-05-15 | Late | 2024-04-05 | -40 | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507607 | T2 DI MELONES-CURTIS 0/004 RPL STRW | 70Y
LC | 125846813 | 000/004 | T2 DI MELONES-CURTIS 0/004 RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2023-04-10 | 2023-04-06 | 2024-05-15 | Late | 2024-04-05 | -40 | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507607 | T2 DI MELONES-CURTIS 0/004 RPL STRW | 70Y
LC | 125846868 | 018/086 | T2 WV VACA-LAKEVILLE #1 018/086 INS DMPS | LAKEVLLE | ETL.5840.INSL.NCER | 2023-04-10 | 2023-04-10 | 2024-04-16 | Late | 2024-04-09 | -7 | 2024-04-10 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 46190762 | T2 WV VACA-LAKEVILLE #1 018/086 INS DMPS | ICS
LC | 125847693 | 029/510 | T2 EI KESWICK-TRINITY 029/510 RPR INSW | TABLEMTN | ETL.7270.INSL.CERA | 2023-04-10 | 2023-04-10 | 2024-04-28 | Late | 2024-04-09 | -19 | 2024-04-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011763 | T2 EI KESWICK-TRINITY 029/510 RPR INSW | ICW
LC | 125847784 | 046/205 | T2 EI ROND MTN-TB MT #2 46/205 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2023-04-10 | 2023-04-10 |  | Late | 2024-04-09 |  | 2023-10-10 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45745395 | T2 EI ROND MTN-TB MT #2 46/205 RPR STRT | ICQ
LC | 125859153 | 001/027 | T2 DI CLGTE GRS VLY 01/027 RPL HRDD | SACTO | ETL.6490.POLE.WOOD | 2023-04-11 | 2023-04-04 | 2024-01-29 | On-time | 2024-04-03 | 65 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45999266 | T2 DI CLGTE GRS VLY 01/027 RPL HRDD | ICW
LC | 125861216 | 007/173 | T2 DI CLGTE GRS VLY 07/173 REFRAME | SACTO | ETL.6490.POLE.WOOD | 2023-04-11 | 2023-04-04 | 2024-03-05 | On-time | 2024-04-03 | 29 | 2024-04-04 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35493423 | T2 DI CLGTE GRS VLY 07/173 REFRAME | 93E
LC | 125866458 | 008/201 | T2 DI COLGATE-GRAS VALY- 08/201 RPR STRW | SACTO | ETL.6490.POLE.WOOD | 2023-04-11 | 2023-04-04 | 2023-12-20 | On-time | 2024-04-03 | 105 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999267 | T2 DI COLGATE-GRAS VALY- 08/201 RPR STRW | ICW
LC | 125849874 | 047/207 | T2 EI ROND MTN-TBL MT#1 47/207 BNT STEEL | TABLEMTN | ETL.6060.TOWR | 2023-04-10 | 2023-04-10 |  | Late | 2024-04-09 |  | 2024-04-10 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46009041 | T2 EI ROND MTN-TBL MT#1 47/207 BNT STEEL | ICQ
LC | 125850231 | 042/004 | T2 DI FRT RS GUALALA 42/004 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-04-10 | 2023-03-23 |  | Late | 2024-03-22 |  | 2024-03-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490757 | T2 DI FRT RS GUALALA 42/002 RPL STRW | 70Y
LC | 125850242 | 017/007 | T2 EI FULTON-HOPLAND -_017/007 RPL HRDW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-04-10 | 2023-04-10 |  | Late | 2024-04-09 |  | 2024-04-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46045918 | T2 EI FULTON-HOPLAND -_017/007 RPL HRDW | ICW
LC | 125850243 | 017/007 | T2 EI FULTON-HOPLAND -_017/007 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-04-10 | 2023-04-10 |  | Late | 2024-04-09 |  | 2024-04-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46045918 | T2 EI FULTON-HOPLAND -_017/007 RPL HRDW | ICW
LC | 125850345 | 013/199 | T2 DI GOLD HILL#1 13/199 RPR GYWW | SACTO | ETL.6950.POLE.WOOD | 2023-04-10 | 2023-04-04 | 2024-04-06 | Late | 2024-04-03 | -3 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999264 | T2 DI GOLD HILL#1 13/199 RPR GYWW | ICW
LC | 125884439 | 023/343 | T2 DI GOLD HILL #1 23/343 RPR STRW | SACTO | ETL.6950.POLE.WOOD | 2023-04-12 | 2023-04-04 | 2024-01-26 | On-time | 2024-04-03 | 68 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999319 | T2 DI GOLD HILL #1 23/343 RPR STRW | ICW
LC | 125905053 | 007/177 | T2 DI COLGT-GRS VLY 7/177 REFRAME | SACTO | ETL.6490.POLE.WOOD | 2023-04-13 | 2023-04-04 | 2024-03-06 | On-time | 2024-04-03 | 28 | 2024-04-04 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35495861 | T2 DI COLGT-GRS VLY 7/177 REFRAME | 93E
LC | 125908176 | 003/084 | T2 DI CLGT-GRSS VLLY 3/84 RPR INSW | SACTO | ETL.6490.INSL.NCER | 2023-04-14 | 2023-04-04 | 2024-01-26 | On-time | 2024-04-03 | 68 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999269 | T2 DI CLGT-GRSS VLLY 3/84 RPR INSW | ICW
LC | 125908217 | 008/107 | T2 DI GOLD HILL #1 08/107 RMV BUTT | SACTO | ETL.6950.POLE.WOOD | 2023-04-14 | 2023-04-04 | 2024-01-25 | On-time | 2024-04-03 | 69 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 45999270 | T2 DI GOLD HILL #1 08/107 RMV BUTT | ICW
LC | 125909966 | 003/086 | T2 DI CLGT-GRSS VLY 3/86 RPL PL | SACTO | ETL.6490.POLE.WOOD | 2023-04-14 | 2023-04-04 | 2024-03-07 | On-time | 2024-04-03 | 27 | 2024-04-04 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495659 | T2 DI CLGT-GRSS VLY 3/86 RPL PL | 70Y
LC | 125851592 | 047/208 | T2 EI RND MT-TB MT #2 47/208 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2023-04-10 | 2023-04-10 | 2024-05-10 | Late | 2024-04-09 | -31 | 2024-04-10 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46009042 | T2 EI RND MT-TB MT #2 47/208 RPR STRT | ICQ
LC | 125911980 | 006/069 | T2 DI GOLD HILL #1 6/69 RPR STRW | SACTO | ETL.6950.POLE.WOOD | 2023-04-14 | 2023-04-04 | 2024-04-03 | On-time | 2024-04-03 | 0 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999272 | T2 DI GOLD HILL #1 6/69 RPR STRW | ICW
LC | 125851643 | 042/002 | T2 DI FRT RS GUALALA 42/002 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-04-10 | 2023-03-23 |  | Late | 2024-03-22 |  | 2024-03-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35490757 | T2 DI FRT RS GUALALA 42/002 RPL STRW | 70Y
LC | 125915884 | 005/057 | T2 DI GOLD HILL #1 05/57 RPR STRW | SACTO | ETL.6950.POLE.WOOD | 2023-04-14 | 2023-04-04 | 2024-04-03 | On-time | 2024-04-03 | 0 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999273 | T2 DI GOLD HILL #1 05/57 RPR STRW | ICW
LC | 125917682 | 010/137 | T2 DI GOLD HILL #1 010/137 RPR INSW | SACTO | ETL.6950.INSL.NCER | 2023-04-14 | 2023-04-04 | 2023-10-11 | On-time | 2024-04-03 | 175 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45749551 | T2 DI GOLD HILL #1 010/137 RPL HRDW | ICW
LC | 125919133 | 007/182 | T2 DI CLGT-GRSS VLY 7/182 RPR STRW | SACTO | ETL.6490.POLE.WOOD | 2023-04-14 | 2023-04-04 | 2023-12-20 | On-time | 2024-04-03 | 105 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999274 | T2 DI CLGT-GRSS VLY 7/182 RPR STRW | ICW
LC | 125919501 | 015/238 | T2 DI GOLD HILL #1 015/238 RPL POLE | SACTO | ETL.6950.POLE.WOOD | 2023-04-14 | 2023-04-04 | 2024-04-03 | On-time | 2024-04-03 | 0 | 2024-04-04 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493229 | T2 DI GOLD HILL #1 015/238 RPL POLE | 70Y
LC | 125852931 | 002/014 | T2 DI STNSLS-MLNS SS-MNT#1 2/14 RPR CNDS | VICTOR | ETL.3830.INSL | 2023-04-10 | 2023-04-06 |  | Late | 2024-04-05 |  | 2024-04-06 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46080873 | T2 DI STNSLS-MLNS SS-MNT#1 2/14 RPR CNDS | ICS
LC | 125920052 | 009/133 | T2 DI GOLD HILL #1 9/133 RPL POLE | SACTO | ETL.6950.POLE.WOOD | 2023-04-14 | 2023-04-04 | 2024-04-02 | On-time | 2024-04-03 | 1 | 2024-04-04 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493230 | T2 DI GOLD HILL #1 9/133 RPL POLE | 70Y
LC | 125853777 | 053/006 | T2 DI FRT RS GLL GLL 53/06 RPR HRDW | WILLITS | ETL.6980.POLE.WOOD | 2023-04-10 | 2023-03-23 |  | Late | 2024-03-22 |  | 2024-03-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46232918 | T2 DI FRT RS GUALALA 53/06 RPR ANTI | ICW
LC | 125923455 | 007/183 | T2 DI CLGT-GRSS VLY 7/183 RPR STRW | SACTO | ETL.6490.POLE.WOOD | 2023-04-14 | 2023-04-04 | 2023-12-20 | On-time | 2024-04-03 | 105 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999276 | T2 DI CLGT-GRSS VLY 7/183 RPR STRW | ICW
LC | 125855217 | 005/086 | T2 COLGATE-PALERMO 05/86 RPR INSW | SACTO | ETL.6500.INSL.NCER | 2023-04-11 | 2023-04-11 | 2024-04-20 | Late | 2024-04-10 | -10 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011666 | T2 COLGATE-PALERMO 05/86 RPR INSW | ICW
LC | 125855443 | 005/039 | T2 EL DRDO-MSSURI FLT #1 5/39 RPL INSS | SACTO | ETL.1530.INSL | 2023-04-11 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35550931 | T2 EL DRDO-MSSURI FLT #1 5/39 RPL INSS | 93K
LC | 125855445 | 005/039 | T2 EL DRDO-MSSURI FLT #2 5/39 RPL INSS | SACTO | ETL.1540.INSL | 2023-04-11 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35550932 | T2 EL DRDO-MSSURI FLT #2 5/39 RPL INSS | 93K
LC | 125857144 | A012/266-GUY | T2 EI SLNS-LRLS A012/266-GUY GO95 CLEAR | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-04-11 | 2023-04-11 | 2024-04-29 | Late | 2024-04-10 | -19 | 2024-04-11 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35508863 | T2 EI SLNS-LRLS A012/266-GUY GO95 CLEAR | 93G
LC | 125857619 | 048/210 | T2 EI RND MTN-TBL MTN #2 48/210 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2023-04-11 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45758968 | T2 EI RND MTN-TBL MTN #2 48/210 RPR STRT | ICQ
LC | 125926825 | 008/198 | T2 DI COLGATE-GRS VLLY 8/198 RPR SPLW | SACTO | ETL.6490.INSL | 2023-04-15 | 2023-04-04 | 2023-12-20 | On-time | 2024-04-03 | 105 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45999277 | T2 DI COLGATE-GRS VLLY 8/198 RPR SPLW | ICW
LC | 125926826 | 008/198 | T2 DI COLGATE-GRS VLLY 8/198 REFRAME | SACTO | ETL.6490.POLE.WOOD | 2023-04-15 | 2023-04-04 | 2024-03-04 | On-time | 2024-04-03 | 30 | 2024-04-04 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35495862 | T2 DI COLGATE-GRS VLLY 8/198 REFRAME | 93E
LC | 125858128 | 032/007 | T2 EI PHILO JCT-ELK -_032/007 RPR GYW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-11 | 2023-04-11 | 2024-06-21 | Late | 2024-04-10 | -72 | 2024-04-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213867 | T2 EI PHILO JCT-ELK -_032/007 RPR GYW | ICW
LC | 125926886 | 007/170 | T2 DI COLGATE-GRS VLLY 7/170 RPL HRDD | SACTO | ETL.6490.POLE.WOOD | 2023-04-15 | 2023-04-04 | 2023-12-20 | On-time | 2024-04-03 | 105 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45999300 | T2 DI COLGATE-GRS VLLY 7/170 RPL HRDD | ICW
LC | 125858505 | A012/266 | T2 EI SALINAS-LAURELS A12/266 RPR SPLW | MOSSLNDG | ETL.7930.INSL.CERA | 2023-04-11 | 2023-04-11 | 2024-04-29 | Late | 2024-04-10 | -19 | 2024-04-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46081063 | T2 EI SALINAS-LAURELS A12/266 RPR SPLW | ICW
LC | 125927920 | 007/178 | T2 DI CLGAT-GRS VLY 07/178 REFRAME | SACTO | ETL.6490.POLE.WOOD | 2023-04-15 | 2023-04-04 | 2024-03-06 | On-time | 2024-04-03 | 28 | 2024-04-04 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35495861 | T2 DI COLGT-GRS VLY 7/177 REFRAME | 93E
LC | 125859228 | 033/000B | T2 EI PHILO JCT-ELK 033/000B RPR POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-04-11 | 2023-04-11 | 2024-06-11 | Late | 2024-04-10 | -62 | 2024-04-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46213866 | T2 EI PHILO JCT-ELK -_033/000 RPR POLE | ICW
LC | 125859356 | 018/004 | T2 EI FULTON-HOPLAND 018/004 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-04-11 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521325 | T2 EI FULTON-HOPLAND 018/004 RPL STRW | 70Y
LC | 125947173 | 002/061 | T2 DI CLGT-GRSS VLLY 002/061 RPR STRW | SACTO | ETL.6490.POLE.WOOD | 2023-04-18 | 2023-04-04 | 2024-03-06 | On-time | 2024-04-03 | 28 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999303 | T2 DI CLGT-GRSS VLLY 002/061 RPR STRW | ICW
LC | 125947703 | 023/349 | T2 DI GOLD HILL #1 23/349C RPR GYWW | SACTO | ETL.6950.POLE.WDPS | 2023-04-18 | 2023-04-04 | 2023-10-17 | On-time | 2024-04-03 | 169 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999352 | T2 DI GOLD HILL #1 23/349C RPR GYWW | ICW
LC | 125947705 | 023/349 | T2 DI GOLD HILL #1 023/349 RPL HRDW | SACTO | ETL.6950.POLE.WDPS | 2023-04-18 | 2023-04-04 | 2023-10-17 | On-time | 2024-04-03 | 169 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45999353 | T2 DI GOLD HILL #1 023/349 RPL HRDW | ICW
LC | 125954107 | 009/212 | T2 DI CLGTE GRS VLY 9/212 RPR GYWW | SACTO | ETL.6490.POLE.WOOD | 2023-04-19 | 2023-04-04 | 2023-12-20 | On-time | 2024-04-03 | 105 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999304 | T2 DI CLGTE GRS VLY 9/212 RPR GYWW | ICW
LC | 125954897 | 003/083 | T2 DI CLGTE GRS VLY 3/83 RPR SPLW | SACTO | ETL.6490.INSL.NCER | 2023-04-19 | 2023-04-04 | 2024-03-07 | On-time | 2024-04-03 | 27 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45999305 | T2 DI CLGTE GRS VLY 3/83 RPR SPLW | ICW
LC | 125799329 | 006/077 | T2 EI KESWICK-TRINITY 006/077 RPR JMPW | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-05 | 2023-04-05 | 2024-03-27 | On-time | 2024-04-04 | 8 | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45999435 | T2 EI KESWICK-TRINITY 006/077 RPR JMPW | ICW
LC | 125860802 | 033/002 | T2 EI PHILO JCT-ELK 33/2 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-04-11 | 2023-04-11 | 2024-06-14 | Late | 2024-04-10 | -65 | 2024-04-11 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35495059 | T2 EI PHILO JCT-ELK 33/2 RPL POLE | 70Y
LC | 125799351 | 006/077 | T2 EI KESWICK-TRINITY 006/077 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-05 | 2023-04-05 | 2024-02-13 | On-time | 2024-04-04 | 51 | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999434 | T2 EI KESWICK-TRINITY 006/077 RPR GYWW | ICW
LC | 125861263 | 029/494 | T2 EI KESWICK-TRINITY 29/494 RPL INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-11 | 2023-04-11 | 2024-04-27 | Late | 2024-04-10 | -17 | 2024-04-11 | 508 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35503042 | T2 EI KESWICK-TRINITY 29/494 RPL INSW | 93I
LC | 125861264 | 029/501 | T2 EI KESWICK-TRINITY 29/501 RPL INSW | TABLEMTN | ETL.7270.INSL.CERA | 2023-04-11 | 2023-04-11 | 2024-04-24 | Late | 2024-04-10 | -14 | 2024-04-11 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35495136 | T2 EI KESWICK-TRINITY 29/501 RPL INSW | 93I
LC | 125861269 | 029/501 | T2 EI KESWICK-TRINITY 29/501 RPR COND | TABLEMTN | ETL.7270.INSL.CERA | 2023-04-11 | 2023-04-11 | 2024-04-24 | Late | 2024-04-10 | -14 | 2024-04-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46011745 | T2 EI KESWICK-TRINITY 29/501 RPR COND | ICW
LC | 125861281 | 029/506 | T2 EI KESWICK-TRINITY 29/506 COTTER | TABLEMTN | ETL.7270.INSL.CERA | 2023-04-11 | 2023-04-11 | 2024-04-25 | Late | 2024-04-10 | -15 | 2023-07-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011744 | T2 EI KESWICK-TRINITY 29/506 COTTER | ICW
LC | 125861427 | 033/001 | T2 EI PHILO JCT-ELK -_033/001 RPR GYW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-11 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213865 | T2 EI PHILO JCT-ELK -_033/001 RPR GYW | ICW
LC | 125799352 | 006/077 | T2 EI KESWICK-TRINITY 006/077 RPR INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-05 | 2023-04-05 | 2024-03-27 | On-time | 2024-04-04 | 8 | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999433 | T2 EI KESWICK-TRINITY 006/077 RPR INSW | ICW
LC | 125861965 | 025/003 | T2 HARTLEY-CLEARLAKE 25/3 RPL STRW | WILLITS | ETL.7515.POLE.WOOD | 2023-04-11 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 372 | TLX | CREW | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31633606 | T0 HARTLEY CLEARLAKE 24/12 RPL POLE | 70Y
LC | 125799561 | 001/017 | T2NT EI CHRISTIE-WLLW PASS 1/17 RMV DBRS | CONCORD | ETL.6370.POLE.STPS | 2023-04-05 | 2023-04-05 | 2024-01-23 | On-time | 2024-04-04 | 72 | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 45997038 | T2NT EI CHRISTIE-WLLW PASS 1/17 RMV DBRS | ICW
LC | 125799625 | 006/080 | T2 EI KESWICK-TRINITY 006/080 COTTER | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-05 | 2023-04-05 | 2024-03-24 | On-time | 2024-04-04 | 11 | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999431 | T2 EI KESWICK-TRINITY 006/080 COTTER | ICW
LC | 125799667 | 006/080 | T2 EI KESWICK-TRINITY 006/080 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-05 | 2023-04-05 | 2024-02-13 | On-time | 2024-04-04 | 51 | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999430 | T2 EI KESWICK-TRINITY 006/080 RPR GYWW | ICW
LC | 125863156 | 035/005 | T2 DI PHILO JCT-ELK 35/5 RPR GYWW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-11 | 2023-04-06 | 2024-05-22 | Late | 2024-04-05 | -47 | 2024-04-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213879 | T2 DI PHILO JCT-ELK 035/005 RPR GYWW | ICW
LC | 125799983 | 006/079 | T2 EI KESWICK-TRINITY 006/079 RPR INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-05 | 2023-04-05 | 2024-03-24 | On-time | 2024-04-04 | 11 | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999432 | T2 EI KESWICK-TRINITY 006/079 RPR INSW | ICW
LC | 125863640 | 033/005 | T2 EI PHILO JCT-ELK 33/5 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-04-11 | 2023-04-11 | 2024-05-23 | Late | 2024-04-10 | -43 | 2024-04-11 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495059 | T2 EI PHILO JCT-ELK 33/2 RPL POLE | 70Y
LC | 125800511 | 004/073 | T2 COLGATE-PALERMO 004/073 RPR IBWW | SACTO | ETL.6500.INSL.NCER | 2023-04-05 | 2023-04-05 | 2024-03-26 | On-time | 2024-04-04 | 9 | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 45999307 | T2 COLGATE-PALERMO 004/073 RPR IBWW | ICW
LC | 125863882 | 049/215 | T2 EI RND MTN-TBL MTN #1 49/215 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2023-04-11 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46009047 | T2 EI RND MTN-TBL MTN #1 49/215 RPR STRT | ICQ
LC | 125864374 | 016/214 | T2 EI KESWICK-TRINITY 16/214 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-11 | 2023-04-11 | 2024-04-15 | Late | 2024-04-10 | -5 | 2024-04-11 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495131 | T2 EI KESWICK-TRINITY 16/214 RPL POLE | 70Y
LC | 125800610 | 006/081 | T2 EI KESWICK-TRINITY 006/081 COTTER | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-05 | 2023-04-05 | 2024-03-24 | On-time | 2024-04-04 | 11 | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999428 | T2 EI KESWICK-TRINITY 006/081 COTTER | ICW
LC | 125865393 | 048/005 | T2 EI HUMBOLDT-TRINITY 48/5L RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2023-04-11 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35542069 | T2 EI HUMBOLDT-TRINITY 48/5L RPL POLE | 70Y
LC | 125800898 | 064/270 | T2 EI RND MTN-TBLE MTN #164/270 BNT STL | TABLEMTN | ETL.6060.TOWR | 2023-04-05 | 2023-04-05 | 2023-11-06 | On-time | 2024-04-04 | 150 | 2024-04-05 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008777 | T2 EI RND MTN-TBLE MTN #2 64/270 BNT STL | ICQ
LC | 125800940 | 018/154 | T2 EI CRAG VIEW-CASCADE 018/154 RPR STRW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-05 | 2023-04-05 | 2023-08-08 | On-time | 2024-04-04 | 240 | 2023-10-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45749914 | T2 EI CRAG VIEW-CASCADE 018/154 RPR STRW | ICW
LC | 125865678 | 010/000 | T2 DI LAKEVILLE #1 010/000 RPR SPLS | LAKEVLLE | ETL.7360.INSL.NCER | 2023-04-11 | 2023-03-30 | 2024-05-13 | Late | 2024-03-29 | -45 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46043056 | T2 DI LAKEVILLE #1 010/000 RPR SPLS | ICW
LC | 125801227 | 015/293 | T2 EI FULTON-MOLINO-CTT-_15/293 RMV VEG | LAKEVLLE | ETL.6910.POLE.WOOD | 2023-04-05 | 2023-04-05 | 2023-10-11 | On-time | 2024-04-04 | 176 | 2024-04-05 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125866085 | 052/012 | T2 DI FORT ROSS-GUALALA 52/12 RPR CNDW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-04-11 | 2023-03-23 |  | Late | 2024-03-22 |  | 2024-03-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46044517 | T2 DI FORT ROSS-GUALALA 52/12 RPR CNDW | ICW
LC | 125801320 | 064/270 | T2 EI RND MTN-TBLE MTN #2 64/270 BNT STL | TABLEMTN | ETL.6070.TOWR | 2023-04-05 | 2023-04-05 | 2023-11-06 | On-time | 2024-04-04 | 150 | 2024-04-05 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008778 | T2 EI RND MTN-TBLE MTN #2 64/270 BNT STL | ICQ
LC | 125866168 | 013/125 | T2 DI BRDGVLL-CTTNWD 13/125 RPL INSW | TABLEMTN | ETL.1110.INSL.CERA | 2023-04-11 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493779 | T2 DI BRDGVLL-CTTNWD 13/125 RPL INSW | 93I
LC | 125801530 | 005/054 | T2 EI SNTH LANE-PACIFICA -_5/54 RPL DMP | METCALF | ETL.7575.INSL.NCER | 2023-04-05 | 2023-04-05 | 2023-10-19 | On-time | 2024-04-04 | 168 | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 45997151 | T2 EI SNTH LANE-PACIFICA -_5/54 RPL DMP | ICW
LC | 125801606 | 017/149 | T2 EI DELTA-COTTONWOOD 017/149 RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-05 | 2023-04-05 | 2023-11-15 | On-time | 2024-04-04 | 141 | 2024-04-05 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45999421 | T2 EI DELTA-COTTONWOOD 017/149 RPR GYWW | ICS
LC | 125866393 | 012/014 | T2 DI LWR LK-HMSTKE 12/014 RPR INSW | WILLITS | ETL.1481.INSL.CERA | 2023-04-11 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46219476 | T2 DI LWR LK-HMSTKE 12/014 RPR INSW | ICW
LC | 125801692 | 006/083 | T2 EI KESWICK-TRINITY 006/083 RPR JMPW | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-05 | 2023-04-05 | 2024-03-28 | On-time | 2024-04-04 | 7 | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45999427 | T2 EI KESWICK-TRINITY 006/083 RPR JMPW | ICW
LC | 125801834 | 010/127 | T2 EI KESWICK-TRINITY 010/127 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-05 | 2023-04-05 | 2024-03-28 | On-time | 2024-04-04 | 7 | 2024-04-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493250 | T2 EI KESWICK-TRINITY 010/127 RPL POLE | 70Y
LC | 125802052 | 017/147 | T2 EI CRAG VIEW-CASCADE 017/147 RPL INSW | TABLEMTN | ETL.1350.INSL | 2023-04-05 | 2023-04-05 | 2024-02-29 | On-time | 2024-04-04 | 35 | 2024-04-05 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493540 | T2 EI CRAG VIEW-CASCADE 017/147 RPL INSW | 93I
LC | 125866646 | 013/132 | T2 DI PIT #5-RND MTN #1 13/132 COTTER | TABLEMTN | ETL.5420.INSL | 2023-04-11 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46129636 | T2 DI PIT #5-RND MTN 14/129 COTTER | ICS
LC | 125802455 | 006/090 | T2 EI KESWICK-TRINITY 006/090 RPR JMPW | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-05 | 2023-04-05 | 2024-03-24 | On-time | 2024-04-04 | 11 | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45999426 | T2 EI KESWICK-TRINITY 006/090 RPR JMPW | ICW
LC | 125802675 | 002/028 | T2 CHRISTIE-WILLOW PASS 002/028 RPR GYWW | CONCORD | ETL.6370.POLE.WOOD | 2023-04-05 | 2023-04-05 | 2024-01-23 | On-time | 2024-04-04 | 72 | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45997060 | T2 CHRISTIE-WILLOW PASS 002/028 RPR GYWW | ICW
LC | 125866749 | 021/003 | T2 DI PHILO JCT-ELK 021/003 RPL INSW | WILLITS | ETL.7780.INSL.NCER | 2023-04-11 | 2023-04-07 | 2024-05-30 | Late | 2024-04-06 | -54 | 2024-04-07 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493856 | T2 DI PHILO JCT-ELK 021/003 RPL INSW | 93I
LC | 125803195 | 010/129 | T2 EI KESWICK-TRINITY -_010/129 RPR STRW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-05 | 2023-04-05 | 2024-03-06 | On-time | 2024-04-04 | 29 | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999422 | T2 EI KESWICK-TRINITY -_010/129 RPR STRW | ICW
LC | 125803207 | 010/130 | T2 EI KESWICK-TRINITY -_010/130 RMV VEG | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-05 | 2023-04-05 | 2024-03-06 | On-time | 2024-04-04 | 29 | 2024-04-05 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125803419 | 015/130 | T2 EI CRAG VIEW-CASCADE 15/130 RPL INSW | TABLEMTN | ETL.1350.INSL.CERA | 2023-04-05 | 2023-04-05 | 2024-02-28 | On-time | 2024-04-04 | 36 | 2024-04-05 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493438 | T2 EI CRAG VIEW-CASCADE 15/130 RPL INSW | 93I
LC | 125804181 | 053/007 | T2 HUMBOLDT-TRINITY 053/007 COMPLETE | EUREKA | ETL.1820.TOWR | 2023-04-05 | 2023-04-05 | 2023-04-13 | On-time | 2024-04-04 | 357 | 2024-04-05 | 532 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31641491 | T2 HUMBOLDT-TRINITY 053/007 RPL INSS | 93K
LC | 125804227 | 064/268 | T2 EI RND MTN-TBLE MTN #2 64/268 BNT STL | TABLEMTN | ETL.6060.TOWR | 2023-04-05 | 2023-04-05 | 2023-11-21 | On-time | 2024-04-04 | 135 | 2024-04-05 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008776 | T2 EI RND MTN-TBLE MTN #2 64/268 BNT STL | ICQ
LC | 125804296 | 007/093 | T2 EI KESWICK-TRINITY 007/093 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-05 | 2023-04-05 | 2024-03-27 | On-time | 2024-04-04 | 8 | 2024-04-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493252 | T2 EI KESWICK-TRINITY 007/093 RPL POLE | 70Y
LC | 125804301 | 007/092 | T2 EI KESWICK-TRINITY 007/092 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-05 | 2023-04-05 | 2024-03-25 | On-time | 2024-04-04 | 10 | 2024-04-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493253 | T2 EI KESWICK-TRINITY 007/092 RPL POLE | 70Y
LC | 125867022 | 017/003 | T2 DI LAYTONVILLE-WILLITS 17/3L RPR GYWW | WILLITS | ETL.8360.POLE.STPS | 2023-04-11 | 2023-04-06 | 2024-06-06 | Late | 2024-04-05 | -62 | 2024-04-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45732177 | DI LAYTONVILLE-WILLITS 17/03L RPR GYWW | ICW
LC | 125804481 | 015/129 | T2 EI CRAG VIEW-CASCADE 15/129R RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-05 | 2023-04-05 | 2023-08-08 | On-time | 2024-04-04 | 240 | 2023-07-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45771880 | T2 EI CRAG VIEW-CASCADE 15/129R RPR GYWW | ICS
LC | 125867033 | 012/163 | T2 DI DELTA-MTN GATE JT 12/163C RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2023-04-11 | 2023-03-24 |  | Late | 2024-03-23 |  | 2023-09-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490617 | T2 DI DELTA-MTN GATE JT 12/163C RPL STRW | 70Y
LC | 125867034 | 012/163 | T2 DI DELTA-MTN GATE JT 12/163R RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2023-04-11 | 2023-03-24 |  | Late | 2024-03-23 |  | 2023-09-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490617 | T2 DI DELTA-MTN GATE JT 12/163C RPL STRW | 70Y
LC | 125867038 | 012/163 | T2 DI DELTA-MTN GATE JT 12/163L RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2023-04-11 | 2023-03-24 |  | Late | 2024-03-23 |  | 2023-09-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35490617 | T2 DI DELTA-MTN GATE JT 12/163C RPL STRW | 70Y
LC | 125869740 | 012/053 | T2 MORAGA-CASTRO VALLEY 12/53 RPR OPGW | CONCORD | ETL.5250.TOWR | 2023-04-12 | 2023-04-12 | 2024-04-30 | Late | 2024-04-11 | -19 | 2024-04-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45997103 | T2 MORAGA-CASTRO VALLEY 12/53 RPR OPGW | ICS
LC | 125869755 | 011/003 | T2 FULTON-HOPLAND 11/3 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-04-12 | 2023-04-12 |  | Late | 2024-04-11 |  | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46045920 | T2 FULTON-HOPLAND 11/3 RPR STRW | ICW
LC | 125804927 | 014/095 | T2 EI MILLBRAE-SNEATH LN 14/95 RPL INSS | METCALF | ETL.7570.INSL.NCER | 2023-04-05 | 2023-04-05 | 2023-09-30 | On-time | 2024-04-04 | 187 | 2023-07-05 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31655808 | T2 EI MILLBRAE-SNEATH LN 14/95 RPL INSS. | 93K
LC | 125806131 | 012/002 | T2 EI FORT BRAGG-ELK 012/002 UNBURY | WILLITS | ETL.2060.POLE.WOOD | 2023-04-05 | 2023-04-05 | 2024-02-26 | On-time | 2024-04-04 | 38 | 2024-04-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46089832 | T2 EI FORT BRAGG-ELK 012/002 UNBURY | ICW
LC | 125871609 | 016/216 | T2 EI KESWICK-TRINITY 016/216 RPL INSW | TABLEMTN | ETL.7270.INSL | 2023-04-12 | 2023-04-12 | 2024-04-15 | Late | 2024-04-11 | -4 | 2024-04-12 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35495132 | T2 EI KESWICK-TRINITY 016/216 RPL INSW | 93I
LC | 125871655 | 016/216 | T2 EI KESWICK-TRINITY 016/216 RPR POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-12 | 2023-04-12 | 2024-04-15 | Late | 2024-04-11 | -4 | 2024-04-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46011742 | T2 EI KESWICK-TRINITY 016/216 RPR POLE | ICW
LC | 125871703 | 006/034 | T2 EI CNTR CSTA-MRG #1 6/34 RPL INSS | CONCORD | ETL.5452.INSL.CERA | 2023-04-12 | 2023-04-12 |  | Late | 2024-04-11 |  | 2024-04-12 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671637 | EI CNTR CSTA-MRG #1 6/34 RPL INSS | 93K
LC | 125871741 | 006/034 | T2 EI CNTR CSTA-MRG #2 6/34 RPL INSS | CONCORD | ETL.5453.INSL.CERA | 2023-04-12 | 2023-04-12 | 2024-04-30 | Late | 2024-04-11 | -19 | 2024-04-12 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671782 | EI CNTR CSTA-MRG #2 RPL INSS IN TWR 6/34 | 93K
LC | 125820022 | 004/066 | T2 DI WEIMAR #1 004/066L RPR ANCW | SACTO | ETL.7560.POLE.WDPS | 2023-04-07 | 2023-04-05 | 2023-11-06 | On-time | 2024-04-04 | 150 | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45733890 | T2 DI WEIMAR #1 004/066L RPR ANCW | ICW
LC | 125820023 | 004/066 | T2 DI WEIMAR #1 004/066R RPR ANCW | SACTO | ETL.7560.POLE.WDPS | 2023-04-07 | 2023-04-05 | 2023-04-17 | On-time | 2024-04-04 | 353 | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45733891 | T2 DI WEIMAR #1 004/066R RPR ANCW | ICW
LC | 125872774 | 027/456 | T2 EI KESWICK-TRINITY 027/456 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-12 | 2023-04-12 | 2024-04-22 | Late | 2024-04-11 | -11 | 2024-04-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495135 | T2 EI KESWICK-TRINITY 027/456 RPL POLE | 70Y
LC | 125872775 | 027/454 | T2 EI KESWICK-TRINITY 027/454 COTTER | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-12 | 2023-04-12 | 2024-04-22 | Late | 2024-04-11 | -11 | 2023-07-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011741 | T2 EI KESWICK-TRINITY 027/454 COTTER | ICW
LC | 125820844 | 000/008 | T2 DI WEIMAR #1 0/8 RPR INSW | SACTO | ETL.7560.INSL.NCER | 2023-04-07 | 2023-04-05 | 2023-11-06 | On-time | 2024-04-04 | 150 | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999312 | T2 DI WEIMAR #1 0/8 RPR INSW | ICW
LC | 125872780 | 027/005 | T2 DI PHILO JCT-ELK 027/005 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-04-12 | 2023-04-06 | 2024-06-06 | Late | 2024-04-05 | -62 | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493706 | T2 DI PHILO JCT-ELK 027/005 RPL POLE | 70Y
LC | 125821243 | 39 | T2 DI JEFFSN-STNFRD 0/12 SW 39 RPR SWTC | METCALF | ETL.7220.SWIT | 2023-04-07 | 2023-04-05 | 2024-04-01 | On-time | 2024-04-04 | 3 | 2024-04-05 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 45999087 | T2 DI JEFFSN-STNFRD 0/12 SW 39 RPR SWTC | ICE
LC | 125821792 | 006/122 | T2 DI KESWICK-CSCD 6/122 COMPLETE | TABLEMTN | ETL.7260.INSL.CERA | 2023-04-07 | 2023-04-05 | 2023-06-27 | On-time | 2024-04-04 | 282 | 2023-07-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45728998 | T2 DI KESWICK-CSCD 6/122 RPL TIED | ICW
LC | 125821949 | 005/060 | T2 DI GOLD HILL #1 5/60 COTTER | SACTO | ETL.6950.INSL.NCER | 2023-04-07 | 2023-04-05 | 2024-04-03 | On-time | 2024-04-04 | 1 | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999313 | T2 DI GOLD HILL #1 5/60 COTTER | ICW
LC | 125822036 | 004/065 | T2 DI WEIMAR #1 4/65 RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2023-04-07 | 2023-04-05 | 2023-11-04 | On-time | 2024-04-04 | 152 | 2024-04-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481561 | T2 DI WEIMAR #1 4/65 RPL POLE | 70Y
LC | 125874539 | 027/447 | T2 EI KESWICK-TRINITY 027/447 RPL STRW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-12 | 2023-04-12 | 2024-04-22 | Late | 2024-04-11 | -11 | 2024-04-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495134 | T2 EI KESWICK-TRINITY 027/447 RPL POLE | 70Y
LC | 125875054 | 050/219 | T2 EI RND MTN-TBL MTN #1 50/219 RPR CNDW | TABLEMTN | ETL.6060.INSL | 2023-04-12 | 2023-04-12 | 2024-04-18 | Late | 2024-04-11 | -7 | 2023-10-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46011621 | T2 EI RND MTN-TBL MTN #1 50/219 RPR CNDW | ICS
LC | 125822665 | 002/033 | T2 DI WEIMAR #1 002/033 COTTER | SACTO | ETL.7560.INSL.CERA | 2023-04-07 | 2023-04-05 | 2023-11-05 | On-time | 2024-04-04 | 151 | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999314 | T2 DI WEIMAR #1 002/033 COTTER | ICW
LC | 125875254 | 050/219 | T2 EI RND MTN-TBL MTN #2 -_50/219 RPL JM | TABLEMTN | ETL.6070.INSL | 2023-04-12 | 2023-04-12 | 2024-04-29 | Late | 2024-04-11 | -18 | 2024-04-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46011620 | T2 EI RND MTN-TBL MTN #2 -_50/219 RPL JM | ICS
LC | 125822957 | 003/056 | T2 DI WEIMAR #1 3/56 RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2023-04-07 | 2023-04-05 | 2023-11-05 | On-time | 2024-04-04 | 151 | 2024-04-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481560 | T2 DI WEIMAR #1 3/56 RPL POLE | 70Y
LC | 125882421 | 000/004 | T2 DI WEIMAR #1 0/4 RPR JUMW | SACTO | ETL.7560.INSL.NCER | 2023-04-12 | 2023-04-05 | 2023-04-21 | On-time | 2024-04-04 | 349 | 2023-07-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45734832 | T2 DI WEIMAR #1 0/4 RPR JUMW | ICW
LC | 125908533 | 003/052 | T2 DI WEIMAR #1 003/052 RPR CNDW | SACTO | ETL.7560.INSL.NCER | 2023-04-14 | 2023-04-05 | 2023-04-21 | On-time | 2024-04-04 | 349 | 2023-10-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45734835 | T2 DI WEIMAR #1 003/052 RPR CNDW | ICW
LC | 125909155 | 000/010 | T2 DI WEIMAR #1 000/010 RPR POLE | SACTO | ETL.7560.POLE.WOOD | 2023-04-14 | 2023-04-05 | 2023-11-06 | On-time | 2024-04-04 | 150 | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999340 | T2 DI WEIMAR #1 000/010 RPR POLE | ICW
LC | 125876831 | 017/227 | T2 EI KESWICK-TRINITY 017/227 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-12 | 2023-04-12 | 2024-04-15 | Late | 2024-04-11 | -4 | 2024-04-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495133 | T2 EI KESWICK-TRINITY 017/227 RPL POLE | 70Y
LC | 125909738 | 001/025 | T2 DI WEIMAR#1 01/025 RPL STRW | SACTO | ETL.7560.POLE.WOOD | 2023-04-14 | 2023-04-05 | 2023-11-05 | On-time | 2024-04-04 | 151 | 2024-04-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481547 | T2 DI WEIMAR#1 01/025 RPL STRW | 70Y
LC | 125910560 | 019/082 | T2 DI TESLA-METCALF- 019/082 UNBURY | METCALF | ETL.6110.TOWR | 2023-04-14 | 2023-04-05 | 2024-04-04 | On-time | 2024-04-04 | 0 | 2024-04-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46220551 | T2 DI TESLA-METCALF- 019/082 UNBURY | ICQ
LC | 125912525 | 002/042 | T2 DI WEIMAR #1 2/42 RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2023-04-14 | 2023-04-05 | 2023-11-06 | On-time | 2024-04-04 | 150 | 2024-04-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481551 | T2 DI WEIMAR #1 2/42 RPL POLE | 70Y
LC | 125913198 | 002/034 | T2 DI NARROWS #2 TAP-02/34 RPR GYWW | SACTO | ETL.6521.POLE.WOOD | 2023-04-14 | 2023-04-05 | 2023-10-11 | On-time | 2024-04-04 | 176 | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999342 | T2 DI NARROWS #2 TAP-02/34 RPR GYWW | ICW
LC | 125913610 | 002/031 | T2 DI WEIMAR #1 RPL STRW | SACTO | ETL.7560.POLE.WOOD | 2023-04-14 | 2023-04-05 | 2023-11-05 | On-time | 2024-04-04 | 151 | 2024-04-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481549 | T2 DI WEIMAR #1 2/31 RPL POLE | 70Y
LC | 125882559 | 011/015 | T2 DI LOWER LAKE-HMSTK 11/15 RPL POLE | WILLITS | ETL.1481.POLE.WOOD | 2023-04-12 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35488187 | T2 DI LOWER LAKE-HMSTK 11/15 RPL POLE | 70Y
LC | 125882575 | 020/002 | T2 DI MENDOCINO-HARTLEY 020/002 RPL POLE | WILLITS | ETL.7510.POLE.WOOD | 2023-04-12 | 2023-03-29 |  | Late | 2024-03-28 |  | 2024-03-29 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494503 | T2 DI MENDOCINO-HARTLEY 020/002 RPL POLE | 70Y
LC | 125914730 | 004/064 | T2 DI WEIMAR #1 4/64 RPR SPLW | SACTO | ETL.7560.INSL.NCER | 2023-04-14 | 2023-04-05 | 2023-11-04 | On-time | 2024-04-04 | 152 | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45999343 | T2 DI WEIMAR #1 4/64 RPR SPLW | ICW
LC | 125882864 | 006/126 | T2 DI KESWICK-CASCADE 006/126 RPL POLE | TABLEMTN | ETL.7260.POLE.WOOD | 2023-04-12 | 2023-04-05 |  | Late | 2024-04-04 |  | 2024-04-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35532904 | T2 DI KESWICK-CASCADE 006/126 RPL POLE | 70Y
LC | 125914792 | 002/034 | T2 DI WEIMAR#1 02/034 RPR STRW | SACTO | ETL.7560.POLE.WOOD | 2023-04-14 | 2023-04-05 | 2023-11-05 | On-time | 2024-04-04 | 151 | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999344 | T2 DI WEIMAR#1 02/034 RPR STRW | ICW
LC | 125917057 | 001/021B | T2 DI WEIMAR #1 001/021B REFRAME | SACTO | ETL.7560.POLE.WOOD | 2023-04-14 | 2023-04-05 | 2023-11-05 | On-time | 2024-04-04 | 151 | 2024-04-05 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35514116 | T2 DI WEIMAR #1 1/21B REFRAME-POST EST | 93E
LC | 125883415 | 009/098 | T2 DI PIT#5-RND MT#2 9/98 RPR INSW | TABLEMTN | ETL.5430.INSL.NCER | 2023-04-12 | 2023-04-10 | 2024-06-25 | Late | 2024-04-09 | -77 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011624 | T2 DI PIT#5-RND MT#2 9/98 RPR INSW | ICW
LC | 125917196 | 002/044 | T2 DI WEIMAR #1 2/44 RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2023-04-14 | 2023-04-05 | 2023-11-06 | On-time | 2024-04-04 | 150 | 2024-04-05 | 372T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481552 | T2 DI WEIMAR #1 2/44 RPL POLE | 70Y
LC | 125927169 | 004/044 | T2 DI MONTA VISTA-BURNS 004/044 RPR JMPW | MOSSLNDG | ETL.7590.INSL.NCER | 2023-04-15 | 2023-04-05 | 2024-03-06 | On-time | 2024-04-04 | 29 | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46016640 | T2 DI MONTA VISTA-BURNS 004/044 RPR JMPW | ICW
LC | 125884160 | 024/001B | T2 DI PHILO JCT-ELK 24/1B RPR GYWW | WILLITS | ETL.7780.POLE.NWOD | 2023-04-12 | 2023-04-10 | 2024-05-22 | Late | 2024-04-09 | -43 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213871 | T2 DI PHILO JCT-ELK 24/1B RPR GYWW | ICW
LC | 125884192 | 015/003 | T2 DI LAYTONVILLE-WILLITS 15/03 RPL INSW | WILLITS | ETL.8360.INSL.NCER | 2023-04-12 | 2023-04-10 |  | Late | 2024-04-09 |  | 2024-04-10 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35495227 | T2 DI LAYTONVILLE-WILLITS 15/03 RPL INSW | 93I
LC | 125928137 | 002/032 | T2 DI NARROWS #2 TAP 2/32 RPR INSW | SACTO | ETL.6521.INSL.NCER | 2023-04-15 | 2023-04-05 | 2024-03-25 | On-time | 2024-04-04 | 10 | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999351 | T2 DI NARROWS #2 TAP 2/32 RPR INSW | ICW
LC | 125933544 | 001/029 | T2 DI WEIMAR #1 001/029 RPL POLE | SACTO | ETL.7560.POLE.WOOD | 2023-04-17 | 2023-04-05 | 2023-11-05 | On-time | 2024-04-04 | 151 | 2024-04-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481548 | T2 DI WEIMAR #1 001/029 RPL POLE | 70Y
LC | 125956266 | 000/003 | T2 DI BKS CK RK CK CSTA 00/003 RPR FOND | TABLEMTN | ETL.4430.TOWR | 2023-04-20 | 2023-04-05 | 2023-11-02 | On-time | 2024-04-04 | 154 | 2024-04-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46008083 | T2 DI BKS CK RK CK CSTA 00/003 RPR FOND | ICQ
LC | 125956269 | 000/003 | T2 DI BKS CK RK CK CSTA 00/003 RPL INSS | TABLEMTN | ETL.4430.INSL | 2023-04-20 | 2023-04-05 | 2024-01-18 | On-time | 2024-04-04 | 77 | 2024-04-05 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31667698 | T2 DI BCKS CRK-RCK CRK-CTA RPL INSS 5 ST | 93K
LC | 125978072 | 021/089 | T2 DI TESLA-METCALF 21/89 COTTER | METCALF | ETL.6110.INSL | 2023-04-24 | 2023-04-05 | 2023-10-23 | On-time | 2024-04-04 | 164 | 2024-04-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45996535 | T2 DI TESLA-METCALF 21/89 COTTER | ICS
LC | 126114624 | 056/240B | T2 DI RND MTN TBL 56/204B RPR GYWS | TABLEMTN | ETL.6070.POLE.NWOD | 2023-05-12 | 2023-04-05 | 2023-12-06 | On-time | 2024-04-04 | 120 | 2024-04-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46008084 | T2 DI RND MTN TBL 56/204B RPR GYWS | ICS
LC | 125893904 | 023/170A | T2 EI TRINITY-COTNWD 023/170A RPR ANCW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-04-13 | 2023-04-13 |  | Late | 2024-04-12 |  | 2024-04-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46217066 | T2 EI TRINITY-COTNWD 023/170A RPR ANCW | ICW
LC | 125894281 | 026/436 | T2 EI KESWICK-TRINITY 026/436 RPL PL | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-13 | 2023-04-13 | 2024-04-20 | Late | 2024-04-12 | -8 | 2024-04-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495648 | T2 EI KESWICK-TRINITY 026/436 RPL PL | 70Y
LC | 125809499 | 000/002 | T2 EI CASCADE-BENTN-DSCHUTS 0/2 RPR GYWW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-04-06 | 2023-04-06 | 2023-10-06 | On-time | 2024-04-05 | 182 | 2024-04-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999299 | T2 EI CASCADE-BENTN-DSCHUTS 0/2 RPR GYWW | ICW
LC | 125809947 | 007/056 | T2 EL DORAD-MSSR FLAT #1 -_7/56 RPL HRDT | SACTO | ETL.1530.TOWR | 2023-04-06 | 2023-04-06 | 2023-10-04 | On-time | 2024-04-05 | 184 | 2024-04-06 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46000900 | T2 EL DORAD-MSSR FLAT #1 -_7/56 RPL HRDT | ICQ
LC | 125895845 | 010/048 | T2 DI DIABLO-MESA 10/48 COMPLETE | PISMOBCH | ETL.4620.INSL | 2023-04-13 | 2023-03-31 | 2024-05-15 | Late | 2024-03-30 | -46 | 2024-03-31 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671707 | T0 DIABLO-MESA RPL INSS 7 LSTS | 93K
LC | 125810129 | 000/003 | T2 EI CASCADE-BENTN-DSCHUTS 0/3 RPR POLE | TABLEMTN | ETL.6310.POLE.WOOD | 2023-04-06 | 2023-04-06 | 2023-10-06 | On-time | 2024-04-05 | 182 | 2024-04-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999298 | T2 EI CASCADE-BENTN-DSCHUTS 0/3 RPR POLE | ICW
LC | 125897049 | 015/344 | T2 EI DRM-GRS VLY-WMR 15/344 RPL POLE | SACTO | ETL.6760.POLE.WOOD | 2023-04-13 | 2023-04-13 |  | Late | 2024-04-12 |  | 2024-04-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495495 | T2 EI DRM-GRS VLY-WMR 15/344 RPL POLE | 70Y
LC | 125810519 | 007/102 | T2 EI KESWICK-TRINITY_007/102 COTTER | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-06 | 2023-04-06 | 2024-03-25 | On-time | 2024-04-05 | 11 | 2024-04-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999296 | T2 EI KESWICK-TRINITY_007/102 COTTER | ICW
LC | 125811191 | 004/117 | T2 COLGATE-GRASS VALLEY 4/117 RPL POLE | SACTO | ETL.6490.POLE.WOOD | 2023-04-06 | 2023-04-06 | 2024-03-20 | On-time | 2024-04-05 | 16 | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518954 | T2 COLGATE-GRASS VALLEY 4/117 RPL POLE | 70Y
LC | 125899121 | :015/092 | T2 EI GREEN VALLEY-LLAGAS :15/92 RPL INS | MOSSLNDG | ETL.1720.INSL.CERA | 2023-04-13 | 2023-04-13 | 2024-06-21 | Late | 2024-04-12 | -70 | 2024-04-13 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672311 | T2 EI GREEN VALLEY-LLAGAS :15/92 RPL INS | 93K
LC | 125899178 | 015/075 | T2 EI VACA-LAKEVILLE #1 15/75 RMV VEG | LAKEVLLE | ETL.5840.TOWR | 2023-04-13 | 2023-04-13 |  | Late | 2024-04-12 |  | 2024-04-13 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation-Tower | Cage Clearing
LC | 125811803 | 017/009 | T2 EI FORT BRAGG-ELK 17/9 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-04-06 | 2023-04-06 | 2024-03-15 | On-time | 2024-04-05 | 21 | 2024-04-06 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487710 | T2 EI FORT BRAGG-ELK 016/005 RPL POLE | 70Y
LC | 125900702 | 015/190 | T2 EI KESWICK-TRINITY 015/190 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-13 | 2023-04-13 | 2024-04-29 | Late | 2024-04-12 | -17 | 2024-04-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495647 | T2 EI KESWICK-TRINITY 015/190 RPL POLE | 70Y
LC | 125901602 | 015/191 | T2 EI KESWICK-TRINITY 015/191 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-13 | 2023-04-13 | 2024-04-29 | Late | 2024-04-12 | -17 | 2024-04-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495647 | T2 EI KESWICK-TRINITY 015/190 RPL POLE | 70Y
LC | 125901773 | 015/192 | goT2 EI KESWICK-TRINITY 015/192 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-13 | 2023-04-13 | 2024-04-29 | Late | 2024-04-12 | -17 | 2024-04-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495647 | T2 EI KESWICK-TRINITY 015/190 RPL POLE | 70Y
LC | 125901788 | 026/438 | T2 EI KESWICK-TRINITY 026/438 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-13 | 2023-04-13 | 2024-04-22 | Late | 2024-04-12 | -10 | 2024-04-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35495648 | T2 EI KESWICK-TRINITY 026/436 RPL PL | 70Y
LC | 125812069 | 007/055 | T2 EL DORADO-MISSRI FLAT #2 7/055 COTTER | SACTO | ETL.1540.INSL | 2023-04-06 | 2023-04-06 | 2023-10-06 | On-time | 2024-04-05 | 182 | 2024-04-06 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45999311 | T2 EL DORADO-MISSRI FLAT #2 7/055 COTTER | ICS
LC | 125812524 | 086/605B | T2 EI BRIDGVLL-CTTNWD 86/605B RMV VEG | EUREKA | ETL.1110.POLE.WOOD | 2023-04-06 | 2023-04-06 | 2024-04-05 | On-time | 2024-04-05 | 0 | 2024-04-06 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125902798 | 017/250 | T2 EI CLAY-MARTEL 017/250 COTTER | VICTOR | ETL.8250.INSL.NCER | 2023-04-13 | 2023-04-13 | 2024-04-16 | Late | 2024-04-12 | -4 | 2024-04-13 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46004170 | T2 EI CLAY-MARTEL 017/250 COTTER | ICS
LC | 125812581 | 086/605C | T2 EI BRIDGVLL-CTTNWD 86/605C RMV VEG | EUREKA | ETL.1110.POLE.WOOD | 2023-04-06 | 2023-04-06 | 2024-04-05 | On-time | 2024-04-05 | 0 | 2024-04-06 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125903171 | 024/005C | T2 EI PHILO JCT-ELK 24/5C RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-13 | 2023-04-13 |  | Late | 2024-04-12 |  | 2024-04-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35491330 | T2 EI PHILO JCT-ELK 24/5A RPL STRW | 70Y
LC | 125903177 | 024/005A | T2 EI PHILO JCT-ELK 24/5A RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-13 | 2023-04-13 | 2024-06-19 | Late | 2024-04-12 | -68 | 2024-04-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491330 | T2 EI PHILO JCT-ELK 24/5A RPL STRW | 70Y
LC | 125813282 | 011/139 | T2 EI KESWICK-TRINITY 011/139 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-06 | 2023-04-06 | 2023-12-18 | On-time | 2024-04-05 | 109 | 2024-04-06 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31656921 | T2 EI KESWICK-TRINITY 011/139 RPL POLE | 70Y
LC | 125813602 | 007/097 | T2 EI KESWICK-TRINITY 007/097 COTTER | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-06 | 2023-04-06 | 2023-05-23 | On-time | 2024-04-05 | 318 | 2024-04-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45748323 | T2 EI KESWICK-TRINITY 007/097 COTTER | ICW
LC | 125814401 | A004/105 | T2 EI CSCD-BNTON-DSCHUTS A4/105 RPL HRDW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-04-06 | 2023-04-06 | 2023-10-05 | On-time | 2024-04-05 | 183 | 2024-04-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45999293 | T2 EI CSCD-BNTON-DSCHUTS A4/105 RPL HRDW | ICW
LC | 125904009 | 029/016 | T2 DI FLTN-HPLND 29/16 RPL INSW | LAKEVLLE | ETL.6890.INSL | 2023-04-13 | 2023-04-03 |  | Late | 2024-04-02 |  | 2024-04-03 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35558796 | T2 DI FLTN-HPLND 29/16 RPL INSW | 93I
LC | 125904222 | 038/016 | T2 DI FLTN-HPLND 38/16 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-04-13 | 2023-04-03 |  | Late | 2024-04-02 |  | 2024-04-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35562834 | T2 DI FLTN-HPLND 38/16 RPL STRW | 70Y
LC | 125904254 | 017/008 | T2 DI LAYTONVILLE-WILLITS 17/08 RPL STRW | WILLITS | ETL.8360.POLE.WOOD | 2023-04-13 | 2023-04-06 |  | Late | 2024-04-05 |  | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493704 | T2 DI LAYTONVILLE-WILLITS 17/08 RPL STRW | 70Y
LC | 125904259 | 003/020 | T2 DI STSL-MLNS SW MNTC#1 3/20 INS DMPS | VICTOR | ETL.3830.INSL | 2023-04-13 | 2023-03-30 |  | Late | 2024-03-29 |  | 2024-03-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 46219946 | T2 DI STSL-MLNS SW MNTC#1 3/20 INS DMPS | ICS
LC | 125823390 | 016/002 | T2 DI LYTNVL WLITS 16/002 RPR GYWS | WILLITS | ETL.8360.POLE.NWOD | 2023-04-07 | 2023-04-06 | 2024-03-28 | On-time | 2024-04-05 | 8 | 2024-04-06 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45998349 | T2 DI LYTNVL WLITS 16/002 RPR GYWS | ICS
LC | 125846552 | 024/214 | T2 DI CASCADE-CTTNWD 24/214L RPL STRW | TABLEMTN | ETL.1240.POLE.WDPS | 2023-04-10 | 2023-04-06 | 2023-12-03 | On-time | 2024-04-05 | 124 | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493539 | T2 DI CASCADE-CTTNWD 24/214L RPL STRW | 70Y
LC | 125904451 | 000/010 | T2 DI MELONES-CURTIS 0/10L RPL POLE | VICTOR | ETL.2390.POLE.WDPS | 2023-04-13 | 2023-03-30 | 2024-05-15 | Late | 2024-03-29 | -47 | 2024-03-30 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507608 | T2 DI MELONES-CURTIS 0/10L RPL POLE | 70Y
LC | 125904508 | 008/005 | T2 DI FORT BRAGG-ELK 08/05 RPL POLE | WILLITS | ETL.2060.POLE.WOOD | 2023-04-13 | 2023-03-29 |  | Late | 2024-03-28 |  | 2024-03-29 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487729 | T2 DI FORT BRAGG-ELK 08/05 RPL POLE | 70Y
LC | 125904660 | 007/031 | T2 DI MNTAVSTA-JFRSN #2 7/31 RPL INSS | METCALF | ETL.5230.INSL | 2023-04-13 | 2023-03-29 |  | Late | 2024-03-28 |  | 2024-03-29 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674006 | T2 DI MONTA VISTA-JEFF #2 RPL INSS IN 7 | 93K
LC | 125846553 | 024/214 | T2 DI CASCADE-CTTNWD 24/214R RPL STRW | TABLEMTN | ETL.1240.POLE.WDPS | 2023-04-10 | 2023-04-06 | 2023-12-04 | On-time | 2024-04-05 | 123 | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493539 | T2 DI CASCADE-CTTNWD 24/214L RPL STRW | 70Y
LC | 125904680 | 006/001 | T2 DI FORT BRAGG-ELK 06/01R RPR STRW | WILLITS | ETL.2060.POLE.WDPS | 2023-04-13 | 2023-04-11 | 2024-04-11 | Late | 2024-04-10 | -1 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46089839 | T2 DI FORT BRAGG-ELK 06/01R RPR STRW | ICW
LC | 125904708 | 006/001 | T2 DI FORT BRAGG-ELK 06/01L RPR GYWW | WILLITS | ETL.2060.POLE.WDPS | 2023-04-13 | 2023-04-11 | 2024-04-11 | Late | 2024-04-10 | -1 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46089891 | T2 DI FORT BRAGG-ELK 06/01L RPR GYWW | ICW
LC | 125904791 | 006/001 | T2 DI FORT BRAGG-ELK 06/01R RPR GYWW | WILLITS | ETL.2060.POLE.WDPS | 2023-04-13 | 2023-04-11 | 2024-04-11 | Late | 2024-04-10 | -1 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46089893 | T2 DI FORT BRAGG-ELK 06/01R RPR GYWW | ICW
LC | 125904795 | 006/001 | T2 DI FORT BRAGG-ELK 06/01C RPR GYWW | WILLITS | ETL.2060.POLE.WDPS | 2023-04-13 | 2023-04-11 | 2024-04-11 | Late | 2024-04-10 | -1 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46089894 | T2 DI FORT BRAGG-ELK 06/01C RPR GYWW | ICW
LC | 125904883 | 022/011 | T2 DI PHILO JCT-ELK 22/11 RPR INSW | WILLITS | ETL.7780.INSL.NCER | 2023-04-13 | 2023-04-10 | 2024-05-22 | Late | 2024-04-09 | -43 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46213872 | T2 DI PHILO JCT-ELK 22/11 RPR INSW | ICW
LC | 125852280 | 024/213 | T2 DI CASCADE-COTTONWOOD 24/213 RPL STRW | TABLEMTN | ETL.1240.POLE.WDPS | 2023-04-10 | 2023-04-06 | 2023-12-04 | On-time | 2024-04-05 | 123 | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493539 | T2 DI CASCADE-CTTNWD 24/214L RPL STRW | 70Y
LC | 125863770 | 001/006 | T2 DI STNLS MELONS SS 01/006 COTTER | VICTOR | ETL.3840.INSL.CERA | 2023-04-11 | 2023-04-06 | 2023-06-06 | On-time | 2024-04-05 | 304 | 2023-10-06 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45745596 | T2 DI STNLS MNTCA#2 01/006 COTTER | ICS
LC | 125866840 | 011/133 | T2 DI CLGTE-SMRTVLLE #1 11/133 COTTER | SACTO | ETL.6510.POLE.WOOD | 2023-04-11 | 2023-04-06 | 2023-10-10 | On-time | 2024-04-05 | 178 | 2024-04-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999316 | T2 DI CLGTE-SMRTVLLE #1 11/133 COTTER | ICW
LC | 125866846 | 019/174 | T2 DI BRIDGE-CTTNWD 19/174L RPR GYWW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-04-11 | 2023-04-06 | 2023-09-10 | On-time | 2024-04-05 | 208 | 2024-04-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45982582 | T2 DI BRIDGE-CTTNWD 19/174L RPR GYWW | ICW
LC | 125905104 | 001/006 | T2 DI FORT BRAGG-ELK 1/6 RPR ANCW | WILLITS | ETL.2060.POLE.WOOD | 2023-04-13 | 2023-04-05 |  | Late | 2024-04-04 |  | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46089480 | T2 DI FORT BRAGG-ELK 1/6 RPR ANCW | ICW
LC | 125905109 | 021/008 | T2 DI MENDO-HARTLY 021/008 RPR INSW | WILLITS | ETL.7510.INSL.NCER | 2023-04-13 | 2023-03-29 |  | Late | 2024-03-28 |  | 2024-03-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46089481 | T2 DI MENDO-HARTLY 021/008 RPR INSW | ICW
LC | 125866848 | 019/174 | T2 DI BRIDGE-COTTONWOOD 19/174L RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2023-04-11 | 2023-04-06 | 2023-11-29 | On-time | 2024-04-05 | 128 | 2024-04-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45999295 | T2 DI BRIDGE-COTTONWOOD 19/174L RPR ADSS | ICW
LC | 125905237 | 002/004 | T2 DI MELONES-CURTIS-02/04L RPL HRDD | VICTOR | ETL.2390.POLE.WDPS | 2023-04-13 | 2023-03-30 | 2024-05-17 | Late | 2024-03-29 | -49 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45991346 | T2 DI MELONES-CURTIS-02/04L RPL HRDD | ICW
LC | 125905241 | 007/001 | T2 DI FORT BRAGG-ELK 07/01 CANCEL | WILLITS | ETL.2060.POLE.WDPS | 2023-04-13 | 2023-04-05 |  | Late | 2024-04-04 |  | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46089896 | T2 DI FORT BRAGG-ELK 07/01 RPR ANCW | ICW
LC | 125905280 | 002/004 | T2 DI MELONES-CURTIS 02/04R RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2023-04-13 | 2023-03-30 | 2024-05-17 | Late | 2024-03-29 | -49 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45991347 | T2 DI MELONES-CURTIS-02/04R RPR STRW | ICW
LC | 125905286 | 001/002 | T2 DI MELONES-CURTIS 01/02 RPL HRDD | VICTOR | ETL.2390.POLE.WDPS | 2023-04-13 | 2023-03-30 | 2024-05-17 | Late | 2024-03-29 | -49 | 2024-03-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45991348 | T2 DI MELONES-CURTIS 01/02 RPL HRDD | ICW
LC | 125867025 | 027/007 | T2 DI PHILO JCT-ELK 027/007 RPR GYWW | WILLITS | ETL.7780.POLE.NWOD | 2023-04-11 | 2023-04-06 | 2023-08-17 | On-time | 2024-04-05 | 232 | 2023-07-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45732179 | T2 DI PHILO JCT-ELK 027/007 RPR GYWW | ICW
LC | 125870159 | 002/035B | T2 DI NARROWS#2 02/035B RPR GYWW | SACTO | ETL.6521.POLE.WOOD | 2023-04-12 | 2023-04-06 | 2023-11-08 | On-time | 2024-04-05 | 149 | 2024-04-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999317 | T2 DI NARROWS#2 02/035B RPR GYWW | ICW
LC | 125922535 | 019/078 | T2 DI TESLA-METCALF 019/078 RPR SHIELD | METCALF | ETL.6110.TOWR | 2023-04-14 | 2023-04-06 | 2023-10-23 | On-time | 2024-04-05 | 165 | 2024-04-06 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45997910 | T2 DI TESLA-METCALF 019/078 RPR SHIELD | ICS
LC | 125905426 | 004/085 | T2 DI KESWICK-CASCADE 004/085 RPL POLE | TABLEMTN | ETL.7260.POLE.WOOD | 2023-04-13 | 2023-03-30 | 2024-06-11 | Late | 2024-03-29 | -74 | 2024-03-30 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492090 | T2 DI KESWICK-CASCADE 004/085 RPL POLE | 70Y
LC | 125905449 | 000/011 | T2 DI DELTA-MTN GATE JCT 0/11 REFRAME | TABLEMTN | ETL.6750.POLE.WOOD | 2023-04-13 | 2023-03-30 |  | Late | 2024-03-29 |  | 2024-03-30 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35491978 | T2 DI DELTA-MTN GATE JCT 0/11 REFRAME | 93E
LC | 125923828 | 018/205 | T2 DI ELK CREEK TAP 18/205 RPL ANCW | TABLEMTN | ETL.6921.POLE.WOOD | 2023-04-14 | 2023-04-06 | 2023-12-08 | On-time | 2024-04-05 | 119 | 2024-04-06 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35489961 | T2 DI ELK CREEK TAP 18/205 RPL ANCW | 93E
LC | 125905560 | 001/014 | T2 DI NARROWS #1 TAP 1/14 RPL POLE | SACTO | ETL.6511.POLE.WOOD | 2023-04-13 | 2023-03-30 | 2024-05-08 | Late | 2024-03-29 | -40 | 2024-03-30 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35524410 | T2 DI NARROWS #1 TAP 1/14 RPL POLE | 70Y
LC | 125926765 | 010/132 | T2 DI CLGT-SMRTVLL #1 10/132 RPR STRW | SACTO | ETL.6510.POLE.WOOD | 2023-04-15 | 2023-04-06 | 2023-12-12 | On-time | 2024-04-05 | 115 | 2024-04-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999348 | T2 DI CLGT-SMRTVLL #1 10/132 RPR STRW | ICW
LC | 125905620 | 018/086 | T2 DI MONTA VISTA-SARTGA 18/86 RPL INSS | METCALF | ETL.5240.INSL | 2023-04-13 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674170 | DI MNTA VSTA-SARATG RPL INSS IN 2 TWRS. | 93K
LC | 125905653 | 020/000 | T2 DI MENDO-HARTLY 20/0 RPL POLE | WILLITS | ETL.7510.POLE.WOOD | 2023-04-13 | 2023-03-29 |  | Late | 2024-03-28 |  | 2024-03-29 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35542070 | T2 DI MENDO-HARTLY 20/0 RPL POLE | 70Y
LC | 125905770 | 000/013 | T2 DI KESWICK-CASCADE 0/13 RPL STRW | TABLEMTN | ETL.7260.POLE.WOOD | 2023-04-13 | 2023-03-30 | 2024-06-04 | Late | 2024-03-29 | -67 | 2024-03-30 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492091 | T2 DI KESWICK-CASCADE 0/13 RPL STRW | 70Y
LC | 125905867 | 012/002 | T2 DI FORT BRAGG-ELK 12/2 RPR CNDW | WILLITS | ETL.2060.INSL.CERA | 2023-04-13 | 2023-03-29 |  | Late | 2024-03-28 |  | 2024-03-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46089897 | T2 DI FORT BRAGG-ELK 12/2 RPR CNDW | ICW
LC | 125905868 | 012/002 | T2 DI FORT BRAGG-ELK 12/2 RPR SPLW | WILLITS | ETL.2060.INSL.CERA | 2023-04-13 | 2023-03-29 |  | Late | 2024-03-28 |  | 2024-03-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46089898 | T2 DI FORT BRAGG-ELK 12/2 RPR SPLW | ICW
LC | 125927020 | 019/081 | T2 DI TESLA-METCALF 019/081 COTTER | METCALF | ETL.6110.INSL | 2023-04-15 | 2023-04-06 | 2023-10-04 | On-time | 2024-04-05 | 184 | 2023-07-06 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45984805 | T2 DI TESLA-METCALF 019/081 COTTER | ICS
LC | 125927072 | 018/076 | T2 DI TESLA-METCALF 18/76 UNBURY | VICTOR | ETL.6110.TOWR | 2023-04-15 | 2023-04-06 | 2023-10-17 | On-time | 2024-04-05 | 171 | 2024-04-06 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46003902 | T2 DI TESLA-METCALF 18/76 UNBURY | ICQ
LC | 125927093 | 043/000 | T2 DI ELK GUALALA 043/000 RPR HRDW | WILLITS | ETL.8410.POLE.WDPS | 2023-04-15 | 2023-04-06 | 2024-01-09 | On-time | 2024-04-05 | 87 | 2024-04-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46079882 | T2 DI ELK GUALALA 043/000 RPR HRDW | ICW
LC | 125927096 | 043/000 | T2 DI ELK GUALALA 043/000 COTTER | WILLITS | ETL.8410.INSL.CERA | 2023-04-15 | 2023-04-06 | 2024-01-09 | On-time | 2024-04-05 | 87 | 2024-04-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079883 | T2 DI ELK GUALALA 043/000 COTTER | ICW
LC | 125908149 | 027/002 | T2 DI PHILO JCT-ELK 27/2 RPR GYWW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-14 | 2023-04-12 | 2024-06-21 | Late | 2024-04-11 | -71 | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213860 | T2 DI PHILO JCT-ELK 27/2 RPR GYWW | ICW
LC | 125927273 | 001/012 | T2 DI S-ML SW S-MT#1 1/12 RPR FOND | VICTOR | ETL.3830.TOWR | 2023-04-15 | 2023-04-06 | 2023-10-11 | On-time | 2024-04-05 | 177 | 2024-04-06 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46003858 | T2 DI S-ML SW S-MT#1 1/12 RPR FOND | ICQ
LC | 125908177 | 027/002 | T2 DI PHILO-ELK 27/2 RPL ANCW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-14 | 2023-04-12 | 2024-06-21 | Late | 2024-04-11 | -71 | 2024-04-12 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35495057 | T2 DI PHILO-ELK 27/2 RPL ANCW | 93E
LC | 125927850 | ?001/001 | T2 DI STH LN - H M B ?1/1 RPL INSS | METCALF | ETL.7212.INSL.CERA | 2023-04-15 | 2023-04-06 | 2024-03-04 | On-time | 2024-04-05 | 32 | 2024-04-06 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510602 | T2 DI STH LN - H M B ?1/1 RPL INSS | 93K
LC | 125928115 | 002/024 | T2 DI ROCK CREEK-POE 02/024 RPL INSS | TABLEMTN | ETL.5630.INSL.CERA | 2023-04-15 | 2023-04-06 | 2024-02-26 | On-time | 2024-04-05 | 39 | 2024-04-06 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671289 | T2 DI ROCK CREEK-POE 3 TWRS RPL INSS | 93K
LC | 125908300 | 030/008A | T2 DI PHILO JCT-ELK 030/008A COTTER | WILLITS | ETL.7780.INSL.NCER | 2023-04-14 | 2023-04-10 | 2024-06-12 | Late | 2024-04-09 | -64 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46213870 | T2 DI PHILO JCT-ELK 030/008A COTTER | ICW
LC | 125928504 | 000/003C | T2 DI ROCK CREEK-POE 0/3C RPR GYWS | TABLEMTN | ETL.5630.POLE.NWOD | 2023-04-15 | 2023-04-06 | 2023-11-21 | On-time | 2024-04-05 | 136 | 2024-04-06 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46008779 | T2 DI ROCK CREEK-POE 0/3C RPR GYWS | ICS
LC | 125908647 | 009/007 | T2 DI LAYTONVILLE-WILLITS 9/7 RPR JMPW | WILLITS | ETL.8360.INSL.CERA | 2023-04-14 | 2023-04-12 | 2024-04-28 | Late | 2024-04-11 | -17 | 2023-07-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46232917 | T2 DI LAYTONVILLE-WILLITS 9/7 RPR JMPW | ICW
LC | 125908789 | 035/008 | T2 DI PHILO JT ELK 35/008 RPR GYWW | WILLITS | ETL.7780.POLE.NWOD | 2023-04-14 | 2023-04-10 | 2024-05-22 | Late | 2024-04-09 | -43 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213869 | T2 DI PHILO JT ELK 35/008 RPR GYWW | ICW
LC | 125947700 | 042/003 | T2 DI ELK-GUALALA 42/3 UNBURY | WILLITS | ETL.8410.POLE.WDPS | 2023-04-18 | 2023-04-06 | 2023-08-28 | On-time | 2024-04-05 | 221 | 2023-10-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45739342 | T2 DI ELK-GUALALA 042/003 UNBURY | ICW
LC | 125947702 | 042/003 | T2 DI ELK-GUALALA 42/3 RPL HRDW | WILLITS | ETL.8410.POLE.WDPS | 2023-04-18 | 2023-04-06 | 2024-01-12 | On-time | 2024-04-05 | 84 | 2024-04-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46079881 | T2 DI ELK-GUALALA 42/3 RPL HRDW | ICW
LC | 125955300 | 025/003A | T2 DI PHILO JCT-ELK 25/3A RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-19 | 2023-04-06 | 2023-09-11 | On-time | 2024-04-05 | 207 | 2024-04-06 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31654374 | T2 DI PHILO JCT-ELK 25/3A RPL STRW | 70Y
LC | 125955306 | 025/003B | T2 DI PHILO JCT-ELK 25/3B RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-19 | 2023-04-06 | 2023-09-11 | On-time | 2024-04-05 | 207 | 2024-04-06 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31654374 | T2 DI PHILO JCT-ELK 25/3A RPL STRW | 70Y
LC | 125955395 | 044/005 | T2 DI ELK-GUALALA 044/005 UNBURY | WILLITS | ETL.8410.POLE.WDPS | 2023-04-19 | 2023-04-06 | 2023-05-03 | On-time | 2024-04-05 | 338 | 2023-10-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45739343 | T2 DI ELK-GUALALA 044/005 UNBURY | ICW
LC | 125955790 | 013/101 | T2 DI TGR CK VLY SPGS 13/101 BNT STEEL | VICTOR | ETL.5790.TOWR | 2023-04-19 | 2023-04-06 | 2024-04-04 | On-time | 2024-04-05 | 1 | 2024-04-06 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46003901 | T2 DI TGR CK VLY SPGS 13/101 BNT STEEL | ICQ
LC | 127211121 | 024/213 | T2 DI CASCADE-COTTONWD 24/213 RPL POLE | TABLEMTN | ETL.1240.POLE.WDPS | 2023-10-06 | 2023-04-06 | 2023-12-04 | On-time | 2024-04-05 | 123 | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493539 | T2 DI CASCADE-CTTNWD 24/214L RPL STRW | 70Y
LC | 125821810 | 011/145 | T2 EI KESWICK-TRINITY 011/145 RPL PL | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-07 | 2023-04-07 | 2023-12-18 | On-time | 2024-04-06 | 110 | 2024-04-07 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31656922 | T2 EI KESWICK-TRINITY 011/145 RPL PL | 70Y
LC | 125821901 | 000/002 | T2 EI HLLSDLE JCT-HLF MN BY 0/2 RPR GYWW | METCALF | ETL.7060.POLE.WOOD | 2023-04-07 | 2023-04-07 | 2023-07-01 | On-time | 2024-04-06 | 280 | 2023-07-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45727627 | T2 EI HLLSDLE JCT-HLF MN BY 0/2 RPR GYWW | ICW
LC | 125822924 | 008/104 | T2 EI KESWICK-TRINITY 8/104 COTTER | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-07 | 2023-04-07 | 2024-03-24 | On-time | 2024-04-06 | 13 | 2024-04-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999289 | T2 EI KESWICK-TRINITY 8/104 COTTER | ICW
LC | 125823089 | 011/009 | T2 EI FORT BRAGG-ELK 11/9 RPR ANCW | WILLITS | ETL.2060.POLE.WOOD | 2023-04-07 | 2023-04-07 | 2023-05-03 | On-time | 2024-04-06 | 339 | 2023-10-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45739346 | T2 EI FORT BRAGG-ELK 11/9 RPR ANCW | ICW
LC | 125911200 | 004/039 | T2 DI MNTA VSTA BRNS 04/39 RPL POLE | MOSSLNDG | ETL.7590.POLE.WOOD | 2023-04-14 | 2023-04-05 |  | Late | 2024-04-04 |  | 2024-04-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505604 | T2 EI MONTA VISTA-BURNS 4/38 RPL POLE | 70Y
LC | 125911444 | 003/050 | T2 DI WEIMAR #1 3/50 RPL ANCW | SACTO | ETL.7560.POLE.WOOD | 2023-04-14 | 2023-04-05 |  | Late | 2024-04-04 |  | 2024-04-05 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35481558 | T2 DI WEIMAR #1 3/50 RPL ANCW | 93E
LC | 125824159 | 005/089 | T2 CENTERVILE-TBLE MTN 5/89 RPL HRDD | TABLEMTN | ETL.6320.POLE.NWOD | 2023-04-07 | 2023-04-07 | 2024-02-02 | On-time | 2024-04-06 | 64 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46009040 | T2 CENTERVILE TBLE MTN 5/89 RPL HRDW | ICW
LC | 125825444 | 008/108 | T2 EI KESWICK-TRINITY 8/108 COTTER | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-07 | 2023-04-07 | 2024-03-25 | On-time | 2024-04-06 | 12 | 2024-04-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999287 | T2 EI KESWICK-TRINITY 8/108 COTTER | ICW
LC | 125911731 | 053/001 | T2 DI ELK-GUALALA 053/001 RPR JUMW | WILLITS | ETL.8410.INSL.NCER | 2023-04-14 | 2023-04-03 | 2024-05-18 | Late | 2024-04-02 | -46 | 2024-04-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46079889 | T2 DI ELK-GUALALA 053/001 RPR JUMW | ICW
LC | 125866292 | 023/002 | T2 DI PHILO JCT-ELK 023/002 COTTER | WILLITS | ETL.7780.INSL.CERA | 2023-04-11 | 2023-04-07 | 2023-09-12 | On-time | 2024-04-06 | 207 | 2023-07-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45732263 | T2 DI PHILO JCT-ELK 023/002 COTTER | ICW
LC | 125912134 | 025/002 | T2 DI PHILO JCT-ELK 025/002 RPL HRDD | WILLITS | ETL.7780.POLE.WOOD | 2023-04-14 | 2023-04-07 | 2024-05-20 | Late | 2024-04-06 | -44 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46213877 | T2 DI PHILO JCT-ELK 025/002 RPL HRDD | ICW
LC | 125866400 | 000/005 | T2 DI BKS CK-RK CK-CTA 0/5 RPR INSS | TABLEMTN | ETL.4430.INSL.NCER | 2023-04-11 | 2023-04-07 | 2024-01-19 | On-time | 2024-04-06 | 78 | 2024-04-07 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45999292 | T2 DI BKS CK-RK CK-CTA 0/5 RPR INSS | ICS
LC | 125866648 | 014/129 | T2 DI PIT#6-RND MTN 14/129 COTTER | TABLEMTN | ETL.5440.INSL.NCER | 2023-04-11 | 2023-04-07 | 2023-11-15 | On-time | 2024-04-06 | 143 | 2024-04-07 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45999282 | T2 DI PIT#6-RND MTN 14/129 COTTER | ICS
LC | 125913216 | 025/006 | T2 DI PHILO JCT-ELK 25/6 RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-14 | 2023-04-12 | 2024-05-22 | Late | 2024-04-11 | -41 | 2024-04-12 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35541712 | T2 DI PHILO JCT-ELK 25/6 RPL STRW | 70Y
LC | 125882658 | 017/161 | T2 DI BRDGVL-COTTONWD 17/161L ANTI SPLIT | TABLEMTN | ETL.1110.POLE.WDPS | 2023-04-12 | 2023-04-07 | 2023-09-04 | On-time | 2024-04-06 | 215 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45976511 | T2 DI BRDGVL-COTTONWD 17/161L ANTI SPLIT | ICW
LC | 125882941 | 017/161 | T2 DI BRDGVL-COTTONWD 17/161R ANTI SPLIT | TABLEMTN | ETL.1110.POLE.WDPS | 2023-04-12 | 2023-04-07 | 2023-09-04 | On-time | 2024-04-06 | 215 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair
LC | 125883422 | 39 | T2 DI NARROWS #2 TAP 2/29 COTTER | SACTO | ETL.6521.SWIT | 2023-04-12 | 2023-04-07 | 2023-10-11 | On-time | 2024-04-06 | 178 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 45999318 | T2 DI NARROWS #2 TAP 2/29 COTTER | ICW
LC | 125904377 | ;001/015 | T2 DI STH LN-HF MN BY ;1/15 RPR GYWW | METCALF | ETL.7212.POLE.WOOD | 2023-04-13 | 2023-04-07 | 2024-03-07 | On-time | 2024-04-06 | 30 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999088 | T2 DI STH LN-HF MN BY ;1/15 RPR GYWW | ICW
LC | 125904433 | ;001/015 | T2 DI STH LN-HF MN BY ;1/15 RPL HRDD | METCALF | ETL.7212.POLE.WOOD | 2023-04-13 | 2023-04-07 | 2024-03-07 | On-time | 2024-04-06 | 30 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45999089 | T2 DI STH LN-HF MN BY ;1/15 RPL HRDD | ICW
LC | 125908225 | 039/008 | T2 DI ELK GUALALA 39/008R RPR STRW | WILLITS | ETL.8410.POLE.WDPS | 2023-04-14 | 2023-04-07 | 2024-01-12 | On-time | 2024-04-06 | 85 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46079880 | T2 DI ELK GUALALA 39/008R RPR STRW | ICW
LC | 125909986 | 001/012 | T2 DI ELEC-BELOTA 1/12 RPL INSS | VICTOR | ETL.4670.INSL | 2023-04-14 | 2023-04-07 | 2024-04-04 | On-time | 2024-04-06 | 2 | 2024-04-07 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35503040 | T2 DI ELEC-BELOTA 1/12 RPL INSS | 93K
LC | 125923256 | 012/111 | T2 DI BRDGVLL-CTTNWD 012/111R ANTI SPLIT | TABLEMTN | ETL.1110.POLE.WDPS | 2023-04-14 | 2023-04-07 | 2023-09-02 | On-time | 2024-04-06 | 217 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45976512 | T2 DI BRDGVLL-CTTNWD 012/111R ANTI SPLIT | ICW
LC | 125963355 | 010/124 | T2 DI CLGTE-SMRTVIL#2 10/24 RPR GYWW | SACTO | ETL.6520.POLE.WOOD | 2023-04-20 | 2023-04-07 | 2023-10-10 | On-time | 2024-04-06 | 179 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46001395 | T2 DI CLGTE-SMRTVIL#2 10/24 RPR GYWW | ICW
LC | 125916304 | A007/091 | T2 DI PALERMO-OROVILLE #2 A7/91 RPL POLE | TABLEMTN | ETL.7740.POLE.WOOD | 2023-04-14 | 2023-04-10 |  | Late | 2024-04-09 |  | 2024-04-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494939 | T2 DI PALERMO-OROVILLE #2 A7/91 RPL POLE | 70Y
LC | 125963457 | 013/126 | T2 DI BRIDGEVILLE-CTTNWD 13/126 COTTER | TABLEMTN | ETL.1110.INSL.NCER | 2023-04-20 | 2023-04-07 | 2024-01-15 | On-time | 2024-04-06 | 82 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999286 | T2 DI BRIDGEVILLE-CTTNWD 13/126 COTTER | ICW
LC | 125963467 | 014/126 | T2 DI PIT#6 JCT-RND MTN-14/126C RPR GYWW | TABLEMTN | ETL.5440.POLE.WDPS | 2023-04-20 | 2023-04-07 | 2023-11-19 | On-time | 2024-04-06 | 139 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999285 | T2 DI PIT#6 JCT-RND MTN-14/126C RPR GYWW | ICW
LC | 125917066 | 027/392 | T2 DI GOLD HILL #1 27/392 RPR GYWW | SACTO | ETL.6950.POLE.WOOD | 2023-04-14 | 2023-04-04 | 2024-04-06 | Late | 2024-04-03 | -3 | 2024-04-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999346 | T2 DI GOLD HILL #1 27/392 RPR GYWW | ICW
LC | 125963468 | 014/126 | T2 DI PIT#6 JCT-RND MTN-14/126L RPR GYWW | TABLEMTN | ETL.5440.POLE.WDPS | 2023-04-20 | 2023-04-07 | 2023-11-19 | On-time | 2024-04-06 | 139 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999284 | T2 DI PIT#6 JCT-RND MTN-14/126L RPR GYWW | ICW
LC | 125963469 | 014/126 | T2 DI PIT#6 JCT-RND MTN-14/126R RPR GYWW | TABLEMTN | ETL.5440.POLE.WDPS | 2023-04-20 | 2023-04-07 | 2023-11-19 | On-time | 2024-04-06 | 139 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999283 | T2 DI PIT#6 JCT-RND MTN-14/126R RPR GYWW | ICW
LC | 125963754 | 020/003 | T2 DI MNDO-PHILO-JCT-HPLND 20/03 RPR GYW | WILLITS | ETL.7520.POLE.NWOD | 2023-04-20 | 2023-04-07 | 2024-03-04 | On-time | 2024-04-06 | 33 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46089959 | T2 DI MNDO-PHILO-JCT-HPLND 20/03 RPR GYW | ICW
LC | 125917950 | 009/003 | T2 DI FORT BRAGG-ELK 9/3 CNCL | WILLITS | ETL.2060.POLE.WOOD | 2023-04-14 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46232915 | T2 DI FORT BRAGG-ELK 9/3 CNCL | ICW
LC | 125918009 | 023/006A | T2 EI PHILO JCT-ELK 023/006A RPL INSW | WILLITS | ETL.7780.INSL.NCER | 2023-04-14 | 2023-04-14 | 2024-05-28 | Late | 2024-04-13 | -45 | 2024-04-14 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35522271 | T2 EI PHILO JCT-ELK 023/006A RPL INSW | 93I
LC | 125918385 | 042/002 | T2 DI ELK GUALALA 42/2 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-04-14 | 2023-04-06 |  | Late | 2024-04-05 |  | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487273 | T2 DI ELK GUALALA 42/2 RPL POLE | 70Y
LC | 125829121 | 008/007 | T2 EI FORT BRAGG-ELK 008/007 REFRAME | WILLITS | ETL.2060.POLE.WOOD | 2023-04-08 | 2023-04-08 | 2024-02-23 | On-time | 2024-04-07 | 44 | 2024-04-08 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35487731 | T2 EI FORT BRAGG-ELK 008/007 REFRAME | 93E
LC | 125919152 | 018/007 | T2 DI MNDCNO-PHLO JT-HPLND 18/7 CANCEL | WILLITS | ETL.7520.POLE.WOOD | 2023-04-14 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46089954 | T2 DI MNDCNO-PHLO JT-HPLND 18/7 UNBURY | ICW
LC | 125919213 | 025/408 | T2 EI KESWICK-TRINITY-_025/408 RPL TIEW | TABLEMTN | ETL.7270.INSL.CERA | 2023-04-14 | 2023-04-14 | 2024-04-27 | Late | 2024-04-13 | -14 | 2024-04-14 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46011684 | T2 EI KESWICK-TRINITY-_025/408 RPL TIEW | ICW
LC | 125829704 | 008/114 | T2 EI KESWICK-TRINITY 8/114 RPR INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-08 | 2023-04-08 | 2024-03-24 | On-time | 2024-04-07 | 14 | 2024-04-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011775 | T2 EI KESWICK-TRINITY 8/114 RPR INSW | ICW
LC | 125829754 | 009/116 | T2 EI KESWICK-TRINITY 9/116 RPR GYW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-08 | 2023-04-08 | 2024-02-24 | On-time | 2024-04-07 | 43 | 2024-04-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011773 | T2 EI KESWICK-TRINITY 9/116 RPR GYW | ICW
LC | 125919607 | 023/006C | T2 EI PHILO JCT-ELK 023/006C RPL INSW | WILLITS | ETL.7780.INSL.NCER | 2023-04-14 | 2023-04-14 | 2024-05-28 | Late | 2024-04-13 | -45 | 2024-04-14 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35559926 | T2 EI PHILO JCT-ELK 023/006C RPL INSW | 93I
LC | 125829756 | 008/115 | T2 EI KESWICK-TRINITY 8/115 RPR GYW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-08 | 2023-04-08 | 2024-02-24 | On-time | 2024-04-07 | 43 | 2024-04-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011774 | T2 EI KESWICK-TRINITY 8/115 RPR GYW | ICW
LC | 125830104 | 013/114 | T2 EI CRAG VIEW-CASCADE 013/114 RPR INSS | TABLEMTN | ETL.1350.INSL | 2023-04-08 | 2023-04-08 | 2024-02-27 | On-time | 2024-04-07 | 40 | 2024-04-08 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46011657 | T2 EI CRAG VIEW-CASCADE 013/114 RPR INSS | ICS
LC | 125830655 | 019/434 | T2 EI DRM-GRSS VLLY-WIMR 19/434 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2023-04-08 | 2023-04-08 | 2024-01-23 | On-time | 2024-04-07 | 75 | 2024-04-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46011664 | T2 EI DRM-GRSS VLLY-WIMR 19/434 RPR POLE | ICW
LC | 125920475 | 011/118 | T2 DI PT#5-RD MT#1 11/118L RPL POLE | TABLEMTN | ETL.5420.POLE.WDPS | 2023-04-14 | 2023-04-10 |  | Late | 2024-04-09 |  | 2024-04-10 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526327 | T2 DI PIT#5-RND MT#1 RPL 4 STRW | 70Y
LC | 125920536 | 025/412 | T2 EI KESWICK-TRINITY 025/412 COTTER | TABLEMTN | ETL.7270.INSL.CERA | 2023-04-14 | 2023-04-14 | 2024-04-27 | Late | 2024-04-13 | -14 | 2024-04-14 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011683 | T2 EI KESWICK-TRINITY 025/412 COTTER | ICW
LC | 125920621 | 011/118 | T2 DI PT#5-RD MT#1 11/118R RPL POLE | TABLEMTN | ETL.5420.POLE.WDPS | 2023-04-14 | 2023-04-10 |  | Late | 2024-04-09 |  | 2024-04-10 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526327 | T2 DI PIT#5-RND MT#1 RPL 4 STRW | 70Y
LC | 125921071 | 004/040 | T2 DI MNTA VISTA-BRNS 4/40 RPR INSW | MOSSLNDG | ETL.7590.INSL | 2023-04-14 | 2023-04-05 |  | Late | 2024-04-04 |  | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46179571 | T2 DI MNTA VISTA-BRNS 4/40 RPR INSW | ICW
LC | 125830783 | 010/122 | T2 EI KESWICK-TRINITY 10/122 COTTER | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-08 | 2023-04-08 | 2024-03-24 | On-time | 2024-04-07 | 14 | 2024-04-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011771 | T2 EI KESWICK-TRINITY 10/122 COTTER | ICW
LC | 125830785 | 009/119 | T2 EI KESWICK-TRINITY 9/119 RPR ANCW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-08 | 2023-04-08 | 2024-02-12 | On-time | 2024-04-07 | 55 | 2024-04-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46129635 | T2 EI KESWICK-TRINITY 9/119 RPR ANCW | ICW
LC | 125830786 | 009/117 | T2 EI KESWICK-TRINITY 9/117 RPR GYW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-08 | 2023-04-08 | 2024-02-24 | On-time | 2024-04-07 | 43 | 2024-04-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011772 | T2 EI KESWICK-TRINITY 9/117 RPR GYW | ICW
LC | 125831150 | 012/109 | T2 EI CRAG VIEW-CASCADE 012/109 COTTER | TABLEMTN | ETL.1350.INSL | 2023-04-08 | 2023-04-08 | 2024-02-24 | On-time | 2024-04-07 | 43 | 2024-04-08 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46011659 | T2 EI CRAG VIEW-CASCADE 012/109 COTTER | ICS
LC | 125831588 | 011/098 | a | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-08 | 2023-04-08 | 2024-02-27 | On-time | 2024-04-07 | 40 | 2024-04-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Wood | Repair | 46011650 | T2 EI CRAG VIEW-CASCADE 11/98R RPR OPGW | ICW
LC | 125844985 | 030/519 | T2 EI KESWICK-TRINITY 030/519 RMV VEG | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-10 | 2023-04-10 | 2024-03-20 | On-time | 2024-04-09 | 20 | 2024-04-10 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125846421 | 015/128 | T2 EI CARG VIEW-CASCADE 15/128 RPR GYWW | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-10 | 2023-04-10 | 2023-11-17 | On-time | 2024-04-09 | 144 | 2024-04-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011646 | T2 EI CARG VIEW-CASCADE 15/128 RPR GYWW | ICW
LC | 125846515 | 006/036 | T2 CASTRO VALLEY-NEWARK 6/36 HANGER | CONCORD | ETL.4450.TOWR | 2023-04-10 | 2023-04-10 | 2024-03-10 | On-time | 2024-04-09 | 30 | 2024-04-10 | 543 | TLQ | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46008512 | T2 CASTRO VALLEY-NEWARK 6/36 HANGER | ICQ
LC | 125923071 | 002/020 | T2 DI PIT #7 TAP 002/020L RPL HRDD | TABLEMTN | ETL.5442.POLE.WDPS | 2023-04-14 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45999291 | T2 DI PIT #7 TAP 002/020L RPL HRDD | ICW
LC | 125848070 | 014/126 | T2 EI CRAG VIEW-CASCADE 14/126R RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-10 | 2023-04-10 | 2024-02-29 | On-time | 2024-04-09 | 40 | 2024-04-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 125848071 | 014/126 | T2 EI CRAG VIEW-CASCADE 14/126L RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-10 | 2023-04-10 | 2024-02-29 | On-time | 2024-04-09 | 40 | 2024-04-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 125923390 | 027/390 | T2 DI GOLD HILL #1 27/390 RPR INSW | SACTO | ETL.6950.INSL.CERA | 2023-04-14 | 2023-04-04 | 2024-04-06 | Late | 2024-04-03 | -3 | 2023-10-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45999347 | T2 DI GOLD HILL #1 27/390 RPR INSW | ICW
LC | 125923393 | 026/004 | T2 DI PHILO JCT-ELK 026/004L COA | WILLITS | ETL.7780.POLE.WDPS | 2023-04-14 | 2023-04-12 |  | Late | 2024-04-11 |  | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213864 | T2 DI PHILO JCT-ELK 026/004L RPR GYWW | ICW
LC | 125923396 | 026/004 | T2 DI PHILO JCT-ELK 026/004C COA | WILLITS | ETL.7780.POLE.WDPS | 2023-04-14 | 2023-04-12 |  | Late | 2024-04-11 |  | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213863 | T2 DI PHILO JCT-ELK 026/004C RPR GYWW | ICW
LC | 125923398 | 026/004 | T2 DI PHILO JCT-ELK 026/004R COA | WILLITS | ETL.7780.POLE.WDPS | 2023-04-14 | 2023-04-12 |  | Late | 2024-04-11 |  | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213862 | T2 DI PHILO JCT-ELK 026/004R RPR GYWW | ICW
LC | 125849462 | 014/091 | T2 EI JEFFERSON-MARTIN 14/91 COTTER | METCALF | ETL.5710.INSL.NCER | 2023-04-10 | 2023-04-10 | 2023-10-10 | On-time | 2024-04-09 | 182 | 2024-04-10 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46012973 | T2 EI JEFFERSON-MARTIN 14/91 COTTER | ICS
LC | 125851169 | 19 | T2 EI MILLBRAE-SNTH LN 14/93 GUEST COTR | METCALF | ETL.7570.SWIT | 2023-04-10 | 2023-04-10 | 2023-09-13 | On-time | 2024-04-09 | 209 | 2024-04-10 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45978510 | T2 EI MILLBRAE-SNTH LN 14/93 GUEST COTR | ICS
LC | 125923544 | 026/004 | T2 DI PHILO JCT-ELK 026/004R RPR POLE | WILLITS | ETL.7780.POLE.WDPS | 2023-04-14 | 2023-04-12 | 2024-05-23 | Late | 2024-04-11 | -42 | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46213861 | T2 DI PHILO JCT-ELK 026/004R RPR POLE | ICW
LC | 125851260 | 19 | T2 EI MILLBRAE-SNTH LN 014/093 RPL PT | METCALF | ETL.7570.SWIT | 2023-04-10 | 2023-04-10 | 2023-12-12 | On-time | 2024-04-09 | 119 | 2024-04-10 | 435 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Steel | Replace | 31662570 | T0 MILLBRAE-SNEATH LANE RPL PT | 93H
LC | 125851333 | 002/024A | T2 MONTA VISTA-BURNS 002/024A RPR GYWW | MOSSLNDG | ETL.7590.POLE.WOOD | 2023-04-10 | 2023-04-10 | 2024-02-29 | On-time | 2024-04-09 | 40 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46013271 | T2 MONTA VISTA-BURNS 002/024A RPR GYWW | ICW
LC | 125923923 | 000/007 | T2 DI JEFFERSON-STANFORD 000/007 COTTER | METCALF | ETL.7220.INSL.NCER | 2023-04-14 | 2023-04-12 | 2024-04-19 | Late | 2024-04-11 | -8 | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46012979 | T2 DI JEFFERSON-STANFORD 000/007 COTTER | ICW
LC | 125923926 | 018/003 | T2 DI PHILO JCT-ELK 018/003 RPR CRSW | WILLITS | ETL.7780.POLE.NWOD | 2023-04-14 | 2023-04-12 | 2024-04-30 | Late | 2024-04-11 | -19 | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46089957 | T2 DI PHILO JCT-ELK 018/003 RPR CRSW | ICW
LC | 125851601 | 047/208 | T2 EI RND MTN-TBL MT #2 47/208 RPL HRDWT | TABLEMTN | ETL.6070.TOWR | 2023-04-10 | 2023-04-10 | 2024-02-23 | On-time | 2024-04-09 | 46 | 2024-04-10 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Tower | Install | 46009043 | T2 EI RND MTN-TBL MT #2 47/208 RPL HRDWT | ICQ
LC | 125851685 | 001/042 | T2 EI COLGATE-GRASS VALLEY 1/42 RPL POLE | SACTO | ETL.6490.POLE.WOOD | 2023-04-10 | 2023-04-10 | 2024-03-11 | On-time | 2024-04-09 | 29 | 2024-04-10 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495083 | T2 EI COLGATE-GRASS VALLEY 1/42 RPL POLE | 70Y
LC | 125926721 | 023/003 | T2 DI PHILO JCT-ELK 023/003 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-04-15 | 2023-04-06 | 2024-06-05 | Late | 2024-04-05 | -61 | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493705 | T2 DI PHILO JCT-ELK 023/003 RPL POLE | 70Y
LC | 125852099 | 015/088 | T2 MSS LNDNG-DL MNT #1 015/088 INS DMPW | MOSSLNDG | ETL.2830.INSL.NCER | 2023-04-10 | 2023-04-10 | 2023-12-18 | On-time | 2024-04-09 | 113 | 2024-04-10 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 46016598 | T2 MSS LNDNG-DL MNT #1 015/088 INS DMPW | ICS
LC | 125852200 | 047/209 | T2 EI ROND MTN-TBL MT#1 47/209 BNT STEEL | TABLEMTN | ETL.6060.TOWR | 2023-04-10 | 2023-04-10 | 2024-02-23 | On-time | 2024-04-09 | 46 | 2024-04-10 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46009044 | T2 EI ROND MTN-TBL MT#1 47/209 BNT STEEL | ICQ
LC | 125926788 | 018/172 | T2 DI BRIDGVLL-CTTNWD 18/172 RPL INSW | TABLEMTN | ETL.1110.INSL.NCER | 2023-04-15 | 2023-04-06 |  | Late | 2024-04-05 |  | 2024-04-06 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493537 | T2 DI BRIDGVLL-CTTNWD 18/172 RPL INSW | 93I
LC | 125876021 | 000/004 | T2 DI SMARTVILLE-CMP FR WST 0/4 REFRAME | SACTO | ETL.7970.POLE.WOOD | 2023-04-12 | 2023-04-10 | 2023-04-13 | On-time | 2024-04-09 | 362 | 2024-04-10 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31642237 | T2 DI SMARTVILLE-CMP FR WST 0/4 REFRAME | 93E
LC | 125884054 | 000/008 | T2 DI SMARTVILLE-MRYSVL 0/8 RPR GYWW | SACTO | ETL.7980.POLE.WOOD | 2023-04-12 | 2023-04-10 | 2023-12-27 | On-time | 2024-04-09 | 104 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011670 | T2 DI SMARTVILLE-MRYSVL 0/8 RPR GYWW | ICW
LC | 125885170 | 022/010 | T2 DI FORT BRAGG-ELK 22/010 RPR GYWW | WILLITS | ETL.2060.POLE.WOOD | 2023-04-12 | 2023-04-10 | 2024-03-12 | On-time | 2024-04-09 | 28 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46089837 | T2 DI FORT BRAGG-ELK 22/010 RPR GYWW | ICW
LC | 125885620 | 001/037 | T2 DI JFFSON-STNFORD 1/37 RPL STRW | METCALF | ETL.7220.POLE.WOOD | 2023-04-12 | 2023-04-10 | 2024-04-02 | On-time | 2024-04-09 | 7 | 2024-04-10 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507603 | T2 DI JFFSON-STNFORD 1/37 RPL INSW | 70Y
LC | 125905287 | 012/049 | T2 DI MNT VSTA-JFFRSN #1 12/49 RPR MEMB | METCALF | ETL.5220.TOWR | 2023-04-13 | 2023-04-10 | 2024-03-14 | On-time | 2024-04-09 | 26 | 2024-04-10 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46008513 | T2 DI MNT VSTA-JFFRSN #1 12/49 RPR MEMB | ICQ
LC | 125905383 | 012/049 | T2 DI MNT VSTA-JFFRSN #2 12/49 RPL INSS | METCALF | ETL.5230.INSL | 2023-04-13 | 2023-04-10 | 2024-03-20 | On-time | 2024-04-09 | 20 | 2024-04-10 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674006 | T2 DI MONTA VISTA-JEFF #2 RPL INSS IN 7 | 93K
LC | 125905415 | 012/049 | T2 DI MNT VSTA-JFFRSN #1 12/49 RPL INSS | METCALF | ETL.5220.INSL | 2023-04-13 | 2023-04-10 | 2024-01-07 | On-time | 2024-04-09 | 93 | 2024-04-10 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672909 | DI MNTA VSTA-JFSN #1 RPL INSS IN 4 TWRS. | 93K
LC | 125911528 | A007/085 | T2 DI PLRMO-ORO #2 A7/85 UNBURY | TABLEMTN | ETL.7740.POLE.WOOD | 2023-04-14 | 2023-04-10 | 2024-02-14 | On-time | 2024-04-09 | 55 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46011761 | T2 DI PLRMO-ORO #2 A7/85 UNBURY | ICW
LC | 125926734 | 002/014 | T2 DI CABRILLO-SNTA YNZ SS 2/14 RMV VEG | PISMOBCH | ETL.1200.POLE.NWOD | 2023-04-15 | 2023-04-10 | 2024-03-01 | On-time | 2024-04-09 | 39 | 2024-04-10 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125927922 | 003/064 | T2 DI KSWCK-CSCD 3/64 RPR SPLW | TABLEMTN | ETL.7260.INSL.CERA | 2023-04-15 | 2023-04-10 | 2024-04-08 | On-time | 2024-04-09 | 1 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46011768 | T2 DI KSWCK-CSCD 3/64 RPR SPLW | ICW
LC | 125965861 | 002/038 | T2 DI COLGATE-SMRTVL#1 2/38 RPR ANCW | SACTO | ETL.6510.POLE.WOOD | 2023-04-21 | 2023-04-10 | 2023-12-14 | On-time | 2024-04-09 | 117 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46011678 | T2 DI COLGATE-SMRTVL#1 2/38 RPR ANCW | ICW
LC | 125926981 | 000/010 | T2 DI NARROWS #1 TAP 0/10 RPL INSW | SACTO | ETL.6511.INSL.NCER | 2023-04-15 | 2023-04-05 | 2024-05-08 | Late | 2024-04-04 | -34 | 2024-04-05 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35481577 | T2 DI NARROWS #1 TAP 0/10 RPL INSW | 93I
LC | 125966580 | 014/121A | T2 DI PIT #6 JT-RND MTN 14/121A RPR GYWW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-04-21 | 2023-04-10 | 2023-05-12 | On-time | 2024-04-09 | 333 | 2023-07-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45749901 | T2 DI PIT #6 JT-RND MTN 14/121A RPR GYWW | ICW
LC | 125968352 | 011/048 | T2 DI MNTA VSTA-JFFRSN #1 11/48 RPL INSS | METCALF | ETL.5220.INSL | 2023-04-21 | 2023-04-10 | 2024-01-05 | On-time | 2024-04-09 | 95 | 2024-04-10 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672909 | DI MNTA VSTA-JFSN #1 RPL INSS IN 4 TWRS. | 93K
LC | 125968354 | 011/048 | T2 DI MNTA VSTA-JFFRSN #2 11/48 RPL INSS | METCALF | ETL.5230.INSL | 2023-04-21 | 2023-04-10 | 2024-03-20 | On-time | 2024-04-09 | 20 | 2024-04-10 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674006 | T2 DI MONTA VISTA-JEFF #2 RPL INSS IN 7 | 93K
LC | 125927036 | 005/005 | T2 DI LOWER LAKE-HOMESTAKE 5/5 RPL STRW | WILLITS | ETL.1481.POLE.WOOD | 2023-04-15 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35488180 | T2 DI LOWER LAKE-HOMESTAKE 5/5 RPL POLE | 70Y
LC | 125927063 | 026/424 | T2 EI KESWICK-TRINITY 026/424 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-15 | 2023-04-15 | 2024-04-20 | Late | 2024-04-14 | -6 | 2024-04-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508974 | T2 EI KESWICK-TRINITY 026/424 RPL POLE | 70Y
LC | 125970039 | 000/001B | T2 DI ELECTRA-BELLOTA 0/1B RPR ANCS | VICTOR | ETL.4670.POLE.NWOD | 2023-04-21 | 2023-04-10 | 2023-11-10 | On-time | 2024-04-09 | 151 | 2024-04-10 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 46004168 | T2 DI ELECTRA-BELLOTA 0/1B RPR ANCS | ICS
LC | 125970109 | 014/121B | T2 DI PT #6 JCT-RD MTN 14/121B COMPLETED | TABLEMTN | ETL.5440.POLE.NWOD | 2023-04-21 | 2023-04-10 | 2023-05-12 | On-time | 2024-04-09 | 333 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45749900 | T2 DI PIT #6 JCT-RD MTN 14/121B RPR ANCW | ICW
LC | 125970190 | 014/121B | T2 DI PIT #6 JCT-RD MTN 14/121B RPR GYWW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-04-21 | 2023-04-10 | 2023-05-12 | On-time | 2024-04-09 | 333 | 2023-07-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45749658 | T2 DI PIT #6 JCT-RD MTN 14/121B RPR GYWW | ICW
LC | 125927138 | 042/004 | T2 DI ELK-GUALALA 42/4R COMPLETE | WILLITS | ETL.8410.POLE.WDPS | 2023-04-15 | 2023-04-06 |  | Late | 2024-04-05 |  | 2024-04-06 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 125971093 | ?001/002 | T2 DI SNTH LN-HLF MN BY ?1/2 RPR HRDW | METCALF | ETL.7212.POLE.WOOD | 2023-04-21 | 2023-04-10 | 2024-03-04 | On-time | 2024-04-09 | 36 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46012965 | T2 DI SNTH LN-HLF MN BY ?1/2 RPR HRDW | ICW
LC | 125971193 | 013/129B | T2 DI PIT#5-GRD MTN#1 13/129B RPR GYWW | TABLEMTN | ETL.5420.POLE.WOOD | 2023-04-21 | 2023-04-10 | 2023-05-05 | On-time | 2024-04-09 | 340 | 2023-07-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45749654 | T2 DI PIT#5-GRD MTN#1 13/129B RPR GYWW | ICW
LC | 125927199 | 009/002 | T2 DI LWR LK HMSTK 09/002 RPL STRW | WILLITS | ETL.1481.POLE.WOOD | 2023-04-15 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35488182 | T2 DI LWR LK HMSTK 09/002 RPL STRW | 70Y
LC | 125927240 | 035/010 | T2 DI PHILO JCT-ELK 35/10 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-04-15 | 2023-04-06 | 2024-06-14 | Late | 2024-04-05 | -70 | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493612 | T2 DI PHILO JCT-ELK 35/10 RPL POLE | 70Y
LC | 125971214 | 014/169 | T2 DI ELK CREEK TAP 14/169 RPR STRW | TABLEMTN | ETL.6921.POLE.WOOD | 2023-04-21 | 2023-04-10 | 2023-11-05 | On-time | 2024-04-09 | 156 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45999226 | T2 DI ELK CREEK TAP 14/169 RPR STRW | ICW
LC | 125927247 | 004/044 | T2 DI MONTA VISTA-BURNS 004/044 RMV VEG | MOSSLNDG | ETL.7590.POLE.WOOD | 2023-04-15 | 2023-04-05 | 2024-04-12 | Late | 2024-04-04 | -8 | 2024-04-05 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125971215 | 008/068 | T2 DI CABRILLO-SNTA YNZ SS 8/68 RPL INSW | PISMOBCH | ETL.1200.INSL.NCER | 2023-04-21 | 2023-04-10 | 2024-01-29 | On-time | 2024-04-09 | 71 | 2024-04-10 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31645483 | T2 DI CBRLL-SNT YNZ SW 2/12 RPL INSW | 93I
LC | 125971819 | 013/129C | T2 DI PIT#5-RND MTN#1 13/129C RPR GYWW | TABLEMTN | ETL.5420.POLE.WOOD | 2023-04-21 | 2023-04-10 | 2023-05-05 | On-time | 2024-04-09 | 340 | 2023-07-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45749655 | T2 DI PIT#5-RND MTN#1 13/129C RPR GYWW | ICW
LC | 125927275 | 001/012 | T2 DI S-ML SW S-MT#1 1/12 RPL INSS | VICTOR | ETL.3830.INSL | 2023-04-15 | 2023-04-06 |  | Late | 2024-04-05 |  | 2024-04-06 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35511003 | T2 DI S-ML SW S-MT#1 1/12 RPL INS | 93K
LC | 125971858 | 002/032 | T2 DI COLGATE-SMRTVL#1 2/32 RPR CNDW | SACTO | ETL.6510.INSL.NCER | 2023-04-21 | 2023-04-10 | 2023-12-14 | On-time | 2024-04-09 | 117 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46011720 | T2 DI COLGATE-SMRTVL#1 2/32 RPR CNDW | ICW
LC | 125972298 | 008/096 | T2 DI COLGATE-SMRTVL#1 8/96 RPR WDPK | SACTO | ETL.6510.POLE.WOOD | 2023-04-22 | 2023-04-10 | 2023-12-12 | On-time | 2024-04-09 | 119 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46011721 | T2 DI COLGATE-SMRTVL#1 8/96 RPR WDPK | ICW
LC | 125927318 | 013/007 | T2 DI LAYTONVILLE-WILLITS 13/7 RPL POLE | WILLITS | ETL.8360.POLE.WOOD | 2023-04-15 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495226 | T2 DI LAYTONVILLE-WILLITS 13/7 RPL POLE | 70Y
LC | 125972449 | 014/121C | T2 DI PIT#6-RD MTN 14/121C RPR GYWW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-04-22 | 2023-04-10 | 2023-05-12 | On-time | 2024-04-09 | 333 | 2023-07-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45749700 | T2 DI PIT#6-RD MTN 14/121C RPR GYWW | ICW
LC | 125972480 | 014/121C | T2 DI PIT#6-RD MTN 14/121C RPR ANCW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-04-22 | 2023-04-10 | 2023-05-12 | On-time | 2024-04-09 | 333 | 2023-10-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45749701 | T2 DI PIT#6-RD MTN 14/121C RPR ANCW | ICW
LC | 126099355 | 001/041 | T2 DI JJEFFERSON-STANFORD 01/041 RMV VEG | METCALF | ETL.7220.POLE.WOOD | 2023-05-10 | 2023-04-10 | 2024-03-26 | On-time | 2024-04-09 | 14 | 2024-04-10 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126099358 | 012/051 | T2 DI MONTA VSTA-JFRSN #1 12/51 RPR INSS | METCALF | ETL.5220.INSL | 2023-05-10 | 2023-04-10 | 2023-10-18 | On-time | 2024-04-09 | 174 | 2024-04-10 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46015860 | T2 DI MONTA VSTA-JFRSN #1 12/51 RPR INSS | ICS
LC | 125857799 | B016/369 | T2 EI DRM-GRS VLY-WMR B16/369 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2023-04-11 | 2023-04-11 | 2024-04-02 | On-time | 2024-04-10 | 8 | 2024-04-11 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35495129 | T2 EI DRM-GRS VLY-WMR B16/369 RPL STRW | 70Y
LC | 125927474 | 002/013 | T2 DI S-ML SW S-MT#1 2/13 RPR SPLS | VICTOR | ETL.3830.INSL | 2023-04-15 | 2023-04-06 |  | Late | 2024-04-05 |  | 2024-04-06 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Steel | Repair | 46080874 | T2 DI S-ML SW S-MT#1 2/13 RPR SPLS | ICS
LC | 125857843 | B016/368 | T2 EI DRM-GRSS VLY-WMR B16/368 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2023-04-11 | 2023-04-11 | 2024-04-02 | On-time | 2024-04-10 | 8 | 2024-04-11 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495128 | T2 EI DRM-GRSS VLY-WMR B16/368 RPL STRW | 70Y
LC | 125858184 | 015/314 | T2 EI COLGATE-PALERMO 15/314 RPR STRW | TABLEMTN | ETL.6500.POLE.WOOD | 2023-04-11 | 2023-04-11 | 2023-10-30 | On-time | 2024-04-10 | 163 | 2024-04-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46011667 | T2 EI COLGATE-PALERMO 15/314 RPR STRW | ICW
LC | 125927611 | 025/178 | T2 EI TRINITY-COTTONWD 25/178C RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-15 | 2023-04-15 |  | Late | 2024-04-14 |  | 2024-04-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011633 | ELECTRIC TLINE WORK | ICW
LC | 125927711 | 009/114 | T2 DI WST PNT-VLY SPGS 9/114 RPL POLE | VICTOR | ETL.8350.POLE.WOOD | 2023-04-15 | 2023-04-06 |  | Late | 2024-04-05 |  | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35511451 | T2 DI WST PNT-VLY SPGS 9/114 RPL POLE | 70Y
LC | 125859386 | 018/004 | T2 EI FULTON-HOPLAND 018/004 RMV VEG | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-04-11 | 2023-04-11 | 2024-04-08 | On-time | 2024-04-10 | 2 | 2024-04-11 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125927856 | 024/000 | T2 DI PHILO JCT-ELK 24/0 RPR SPLW | WILLITS | ETL.7780.INSL.CERA | 2023-04-15 | 2023-04-06 | 2024-05-22 | Late | 2024-04-05 | -47 | 2024-04-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46213882 | T2 DI PHILO JCT-ELK 24/0 RPR SPLW | ICW
LC | 125860034 | 003/039 | T2 EI HILLSDALE JCT-HMB 3/39 RPR GYWW | METCALF | ETL.7060.POLE.WOOD | 2023-04-11 | 2023-04-11 | 2024-04-08 | On-time | 2024-04-10 | 2 | 2024-04-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46012974 | T2 EI HILLSDALE JCT-HMB 3/39 RPR GYWW | ICW
LC | 125860178 | 048/213 | T2 EI RND MTN-TBL MTN #1 48/213 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2023-04-11 | 2023-04-11 | 2024-02-23 | On-time | 2024-04-10 | 47 | 2024-04-11 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46009046 | T2 EI RND MTN-TBL MTN #1 48/213 RPR STRT | ICQ
LC | 125860240 | B016/379 | T2 EI DRM-GRS VLY-WMR B16/379 RPL STRW | SACTO | ETL.6760.POLE.WOOD | 2023-04-11 | 2023-04-11 | 2024-04-04 | On-time | 2024-04-10 | 6 | 2024-04-11 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495130 | T2 EI DRM-GRS VLY-WMR B16/379 RPL STRW | 70Y
LC | 125860474 | 001/035 | T2 EI COLGATE-GRASS VALLEY 1/35 RPR HRDW | SACTO | ETL.6490.POLE.WOOD | 2023-04-11 | 2023-04-11 | 2024-01-29 | On-time | 2024-04-10 | 72 | 2024-04-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46011668 | T2 EI COLGATE-GRASS VALLEY 1/35 RPR HRDW | ICW
LC | 125860708 | 013/115 | T2 EI CRAG VIEW-CASCADE 13/115 INS MKBL | TABLEMTN | ETL.1350.TOWR | 2023-04-11 | 2023-04-11 | 2023-12-04 | On-time | 2024-04-10 | 128 | 2024-04-11 | 671 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | FAA Lighting-Steel | Replace | 31644617 | T2 EI CRAG VIEW-CASCADE 13/115 INS MKBL | 93P
LC | 125861706 | 004/043 | T2 EI HLLSDL JCT-HF MN BY 4/43L RPR GYWW | METCALF | ETL.7060.POLE.WDPS | 2023-04-11 | 2023-04-11 | 2024-04-08 | On-time | 2024-04-10 | 2 | 2024-04-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46012976 | T2 EI HLLSDL JCT-HF MN BY 4/43L RPR GYWW | ICW
LC | 125928099 | 47 | T2 DI NARROWS #2 TAP 2/33 RPL SWTC | SACTO | ETL.6521.SWIT | 2023-04-15 | 2023-04-05 |  | Late | 2024-04-04 |  | 2024-04-05 | 427T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Switch-Wood | Replace | 35524384 | T2 DI NARROWS #2 TAP 2/33 RPL SWTC | 93H
LC | 125928112 | 009/007 | T2 DI LWR LK HMSTK HMSTK 09/007 RPL STRW | WILLITS | ETL.1481.POLE.WOOD | 2023-04-15 | 2023-04-07 |  | Late | 2024-04-06 |  | 2023-10-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35488185 | T2 DI LWR LK HMSTK 09/007 RPL STRW | 70Y
LC | 125862621 | 009/112 | T2 DRUM-SUMMIT #1_009/112R RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2023-04-11 | 2023-04-11 | 2023-08-31 | On-time | 2024-04-10 | 223 | 2024-04-11 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31618288 | T2 DRUM-SUMMIT #1_009/112R RPL POLE | 70Y
LC | 125928130 | 030/000 | T2 DI PHILO JCT-ELK 30/0 RPR ANCW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-15 | 2023-04-06 | 2024-06-10 | Late | 2024-04-05 | -66 | 2024-04-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46213880 | T2 DI PHILO JCT-ELK 30/0 RPR ANCW | ICW
LC | 125928136 | 016/003 | T2 DI LTNVLL-WLLTS 16/3 RPL ANCW | WILLITS | ETL.8360.POLE.NWOD | 2023-04-15 | 2023-04-06 |  | Late | 2024-04-05 |  | 2024-04-06 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35493703 | T2 DI LTNVLL-WLLTS 16/3 RPL ANCW | 93E
LC | 125862650 | 009/112 | T2 DRUM-SUMMIT #1_009/112L RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2023-04-11 | 2023-04-11 | 2023-08-31 | On-time | 2024-04-10 | 223 | 2024-04-11 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31618288 | T2 DRUM-SUMMIT #1_009/112R RPL POLE | 70Y
LC | 125862651 | 010/115 | T2 DRUM-SUMMIT #1-_010/115 INS HRD | SACTO | ETL.1440.INSL.NCER | 2023-04-11 | 2023-04-11 | 2023-08-02 | On-time | 2024-04-10 | 252 | 2024-04-11 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45824491 | T2 DRUM-SUMMIT #1 010/122 INS WEIGHT | ICW
LC | 125928305 | 035/009 | T2 DI PHILO JCT-ELK 35/9 RPL INSW | WILLITS | ETL.7780.INSL.NCER | 2023-04-15 | 2023-04-06 | 2024-06-12 | Late | 2024-04-05 | -68 | 2023-10-06 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35493708 | T2 DI PHILO JCT-ELK 35/9 RPL INSW | 93I
LC | 125863440 | 014/174 | T2 EI KESWICK-TRINITY 14/174 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-11 | 2023-04-11 | 2023-12-08 | On-time | 2024-04-10 | 124 | 2024-04-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011747 | T2 EI KESWICK-TRINITY 14/174 RPR GYWW | ICW
LC | 125928485 | 000/015 | T2 DI KSWCK-CSCD 0/15 RPL STRW | TABLEMTN | ETL.7260.POLE.WOOD | 2023-04-15 | 2023-04-05 | 2024-06-04 | Late | 2024-04-04 | -61 | 2024-04-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493315 | T2 DI KSWCK-CSCD 0/15 RPL STRW | 70Y
LC | 125865514 | 012/216 | T2 DI COLMN RD BLFF 12/216 RPL STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-11 | 2023-04-11 | 2024-03-06 | On-time | 2024-04-10 | 35 | 2024-04-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494799 | T2 DI CLMN-RED BLUFF 011/194 RPL STRW | 70Y
LC | 125866135 | 000/000D | T2 EI HAT CRK #1-PIT #1 0/0D RPR INSW | TABLEMTN | ETL.7020.INSL.CERA | 2023-04-11 | 2023-04-11 | 2023-11-03 | On-time | 2024-04-10 | 159 | 2024-04-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011760 | T2 EI HAT CRK #1-PIT #1 0/0D RPR INSW | ICW
LC | 125866361 | 010/090 | T2 EI CRG VW- CSCD 010/090L RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-11 | 2023-04-11 | 2023-12-05 | On-time | 2024-04-10 | 127 | 2024-04-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011644 | T2 EI CRG VW- CSCD 010/090L RPR GYWW | ICW
LC | 125866444 | 010/090 | T2 EI CRG VW- CSCD 010/090R RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-11 | 2023-04-11 | 2023-12-05 | On-time | 2024-04-10 | 127 | 2024-04-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011645 | T2 EI CRG VW- CSCD 010/090R RPR GYWW | ICW
LC | 125922770 | 023/003A | T2 DI FORT BRAGG-ELK 23/3A RMV VEG | WILLITS | ETL.2060.POLE.WOOD | 2023-04-14 | 2023-04-11 | 2024-04-02 | On-time | 2024-04-10 | 8 | 2024-04-11 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125928870 | 029/007 | T2 EI MENDOCNO-WILTS-FRT BRG 29/7 COTTER | WILLITS | ETL.7550.INSL.NCER | 2023-04-15 | 2023-04-15 |  | Late | 2024-04-14 |  | 2023-10-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46213884 | T2 EI MENDOCNO-WILTS-FRT BRG 29/7 COTTER | ICW
LC | 125928871 | 029/011 | T2 EI MMDCNO-WLTS-FRT BRG 29/11 RPL ANCW | WILLITS | ETL.7550.POLE.WOOD | 2023-04-15 | 2023-04-15 |  | Late | 2024-04-14 |  | 2024-04-15 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35549337 | T2 EI MMDCNO-WLTS-FRT BRG 29/11 RPL ANCW | 93E
LC | 125926963 | 000/002 | T2 DI CRYSTAL SPRINGS TAP 000/002 COTTER | METCALF | ETL.7211.INSL.NCER | 2023-04-15 | 2023-04-11 | 2024-04-08 | On-time | 2024-04-10 | 2 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46012969 | T2 DI CRYSTAL SPRINGS TAP 000/002 COTTER | ICW
LC | 125928884 | 030/002 | T2 EI MMDCNO-WLTS-FRT BRG 30/02 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2023-04-15 | 2023-04-15 |  | Late | 2024-04-14 |  | 2024-04-15 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35521522 | T2 WV MNDCNO-WLTS-FRT BRG 14/13 RPL INSW | 93I
LC | 125927246 | 000/001 | T2 DI CRYSTAL SPRINGS TAP 00/01 RPL INSW | METCALF | ETL.7211.INSL | 2023-04-15 | 2023-04-11 | 2024-04-08 | On-time | 2024-04-10 | 2 | 2024-04-11 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35520649 | T2 DI CRYSTAL SPRINGS TAP 00/01 RPL INSW | 93I
LC | 125927248 | 000/001 | T2 DI CRYSTAL SPRINGS TAP 00/01 RPR CNDW | METCALF | ETL.7211.INSL | 2023-04-15 | 2023-04-11 | 2024-04-08 | On-time | 2024-04-10 | 2 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46012968 | T2 DI CRYSTAL SPRINGS TAP 00/01 RPR CNDW | ICW
LC | 125927394 | 003/003 | T2 DI FORT BRAGG-ELK 3/3 RPR GYWW | WILLITS | ETL.2060.POLE.NWOD | 2023-04-15 | 2023-04-11 | 2023-08-09 | On-time | 2024-04-10 | 245 | 2023-10-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45763985 | T2 DI FORT BRAGG-ELK 3/3 RPR GYWW | ICW
LC | 125927555 | 009/004 | T2 DI MELONES-CURTIS 9/4L RPR GYWW | VICTOR | ETL.2390.POLE.STPS | 2023-04-15 | 2023-04-11 | 2023-08-30 | On-time | 2024-04-10 | 224 | 2023-10-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45916319 | T2 DI MELONES-CURTIS 9/4L RPR GYWW | ICW
LC | 125929361 | 025/180 | T2 EI TRINITY-CTTNWD 25/180R RMV VEG | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-15 | 2023-04-15 |  | Late | 2024-04-14 |  | 2024-04-15 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 125929514 | 025/181 | T2 EI TRNTY-CTTNWD 25/181 RPR INSW | TABLEMTN | ETL.4040.INSL.CERA | 2023-04-15 | 2023-04-15 |  | Late | 2024-04-14 |  | 2024-04-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011631 | T2 EI TRNTY-CTTNWD 25/181 RPR INSW | ICW
LC | 125929733 | 024/000 | T2 EI FLTN-HPLND 24/0 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-04-15 | 2023-04-15 |  | Late | 2024-04-14 |  | 2024-04-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521329 | T2 EI FLTN-HPLND 24/0 RPL STRW | 70Y
LC | 125927857 | A011/200 | T2 DI COLMN-RED BLUF- A11/200 REFRAME | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-15 | 2023-04-11 | 2024-04-03 | On-time | 2024-04-10 | 7 | 2024-04-11 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35495340 | T2 DI COLMN-RED BLUF- A11/200 REFRAME | 93E
LC | 125932428 | 030/006 | T2 EI MMDCNO-WLTS-FRT BRG 30/06 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2023-04-17 | 2023-04-17 |  | Late | 2024-04-16 |  | 2024-04-17 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35521522 | T2 WV MNDCNO-WLTS-FRT BRG 14/13 RPL INSW | 93I
LC | 125928063 | 012/007 | T2 DI MELONES-CURTIS- 12/07 COTTER | VICTOR | ETL.2390.INSL.NCER | 2023-04-15 | 2023-04-11 | 2023-06-16 | On-time | 2024-04-10 | 299 | 2023-07-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45745597 | T2 DI MELONES-CURTIS- 12/07 COTTER | ICW
LC | 125932653 | 030/007 | T2 EI MMDCNO-WLTS-FRT BRG 30/07 RPL INSW | WILLITS | ETL.7550.INSL.NCER | 2023-04-17 | 2023-04-17 |  | Late | 2024-04-16 |  | 2024-04-17 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35521522 | T2 WV MNDCNO-WLTS-FRT BRG 14/13 RPL INSW | 93I
LC | 125932917 | 030/008 | T2 EI MMDCNO-WLTS-FRT BRG 30/08 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2023-04-17 | 2023-04-17 |  | Late | 2024-04-16 |  | 2024-04-17 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35521522 | T2 WV MNDCNO-WLTS-FRT BRG 14/13 RPL INSW | 93I
LC | 125933224 | 030/009 | T2 EI MMDCNO-WLTS-FRT BRG 30/09 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2023-04-17 | 2023-04-17 |  | Late | 2024-04-16 |  | 2024-04-17 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35521522 | T2 WV MNDCNO-WLTS-FRT BRG 14/13 RPL INSW | 93I
LC | 125933226 | 031/000 | T2 EI MMDCNO-WLTS-FRT BRG 31/0 COA | WILLITS | ETL.7550.POLE.NWOD | 2023-04-17 | 2023-04-17 |  | Late | 2024-04-16 |  | 2024-07-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213891 | T2 EI MMDCNO-WLTS-FRT BRG 31/00 RPR GYWW | ICW
LC | 125933290 | 021/294 | T2 EI CLAY-MARTEL 021/294 RPR POLE | VICTOR | ETL.8250.POLE.WOOD | 2023-04-17 | 2023-04-17 |  | Late | 2024-04-16 |  | 2024-04-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46017001 | T2 EI CLAY-MARTEL 021/294 RPR POLE | ICW
LC | 125933413 | 011/247 | T2 EI SALINAS-LAURELES 11/247 RPR INSW | MOSSLNDG | ETL.7930.INSL.NCER | 2023-04-17 | 2023-04-17 |  | Late | 2024-04-16 |  | 2024-04-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46266140 | T2 EI SALINAS-LAURELES 11/247 RPR INSW | ICW
LC | 125928486 | 013/228 | T2 DI COLEMAN-RED BLUFF 013/228 RPR CNDW | TABLEMTN | ETL.6440.INSL.NCER | 2023-04-15 | 2023-04-11 | 2024-03-07 | On-time | 2024-04-10 | 34 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45749615 | T2 DI COLEMAN-RED BLUFF 013/228 RPR CNDW | ICW
LC | 125928489 | 013/228 | T2 DI COLEMAN-RED BLUFF 013/228 RPL POLE | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-15 | 2023-04-11 | 2024-03-07 | On-time | 2024-04-10 | 34 | 2024-04-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495080 | T2 DI COLEMAN-RED BLUFF 013/228 RPL POLE | 70Y
LC | 125933775 | 025/123 | T2 DI MNTAVSTA-COYOTE SS-25/123 RPL INSS | MOSSLNDG | ETL.5090.INSL | 2023-04-17 | 2023-04-11 | 2024-03-13 | On-time | 2024-04-10 | 28 | 2024-04-11 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510133 | T2 DI MNTAVSTA-COYOTE SS-25/123 RPL INSS | 93K
LC | 125934293 | 026/185 | T2 EI TRNTY-CTTNWD 26/185L RMV VEG | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-17 | 2023-04-17 |  | Late | 2024-04-16 |  | 2023-10-17 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 125934412 | 051/222 | T2 EI RND MTN-TBL MTN #2 51/222 RPL INSS | TABLEMTN | ETL.6070.INSL | 2023-04-17 | 2023-04-17 | 2024-04-28 | Late | 2024-04-16 | -12 | 2024-04-17 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672626 | T2 EI RND MTN-TBL MTN #2 RPL INSS 2 TWRS | 93K
LC | 125933959 | 025/123 | T2 DI MTCLF-MNTAVSTA #3-25/123 RPR INSS | MOSSLNDG | ETL.5091.INSL | 2023-04-17 | 2023-04-11 | 2024-03-18 | On-time | 2024-04-10 | 23 | 2024-04-11 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46012977 | T2 DI MTCLF-MNTAVSTA #3-25/123 RPR INSS | ICS
LC | 125956214 | 010/180 | T2 DI COLEMAN-RED BLUFF 010/180 RPL POLE | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-20 | 2023-04-11 | 2024-03-19 | On-time | 2024-04-10 | 22 | 2024-04-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519424 | T2 DI COLEMAN-RED BLUFF 010/180 RPL POLE | 70Y
LC | 125965032 | 007/140 | T2 DI SMRTVL-CMP FR WST 7/140 RMV BUTT | SACTO | ETL.7970.POLE.WOOD | 2023-04-21 | 2023-04-11 | 2023-10-10 | On-time | 2024-04-10 | 183 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 46004017 | T2 DI SMRTVL-CMP FR WST 7/140 RMV BUTT | ICW
LC | 125965318 | 006/122 | T2 DI SMRTVIL-CMP FW 06/122 RMV BUTT | SACTO | ETL.7970.POLE.WOOD | 2023-04-21 | 2023-04-11 | 2023-10-10 | On-time | 2024-04-10 | 183 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 46004014 | T2 DI SMRTVIL-CMP FW 06/122 RMV BUTT | ICW
LC | 125965324 | 012/218 | T2 DI COLEMN-RED BLUFF 12/218 RPL STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-21 | 2023-04-11 | 2024-03-06 | On-time | 2024-04-10 | 35 | 2024-04-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494799 | T2 DI CLMN-RED BLUFF 011/194 RPL STRW | 70Y
LC | 125935336 | 021/303 | T2 EI CLAY-MARTEL 021/303 RPR POLE | VICTOR | ETL.8250.POLE.WOOD | 2023-04-17 | 2023-04-17 |  | Late | 2024-04-16 |  | 2024-04-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46017003 | T2 EI CLAY-MARTEL 021/303 RPR POLE | ICW
LC | 125965412 | 012/208 | T2 DI COLEMN-RED BLUFF 12/208 RPL STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-21 | 2023-04-11 | 2024-03-06 | On-time | 2024-04-10 | 35 | 2024-04-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494799 | T2 DI CLMN-RED BLUFF 011/194 RPL STRW | 70Y
LC | 125965604 | 006/125 | T2 DI SMRTVIL-CMP FRWST-6/125 RMV DBRS | SACTO | ETL.7970.POLE.WOOD | 2023-04-21 | 2023-04-11 | 2023-10-10 | On-time | 2024-04-10 | 183 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 46004016 | T2 DI SMRTVIL-CMP FRWST-6/125 RMV DBRS | ICW
LC | 125966186 | 011/194 | T2 DI CLMN-RED BLUFF 011/194 RPL STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-21 | 2023-04-11 | 2024-03-06 | On-time | 2024-04-10 | 35 | 2024-04-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494799 | T2 DI CLMN-RED BLUFF 011/194 RPL STRW | 70Y
LC | 125966333 | 012/214 | T2 DI COLEMN-RED BLUFF 12/214 RPL POLE | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-21 | 2023-04-11 | 2024-03-06 | On-time | 2024-04-10 | 35 | 2024-04-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494799 | T2 DI CLMN-RED BLUFF 011/194 RPL STRW | 70Y
LC | 125966604 | 010/178 | T2 DI CLMN-RED BLUFF 010/178 RPL STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-21 | 2023-04-11 | 2024-03-19 | On-time | 2024-04-10 | 22 | 2024-04-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495177 | T2 DI CLMN-RED BLUFF 010/178 RPL STRW | 70Y
LC | 125966639 | 012/223 | T2 DI COLEMN-RED BLUFF 12/223 RPL TIEW | TABLEMTN | ETL.6440.INSL.CERA | 2023-04-21 | 2023-04-11 | 2024-03-06 | On-time | 2024-04-10 | 35 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46011748 | T2 DI COLEMN-RED BLUFF 12/223 RPL TIEW | ICW
LC | 125968657 | 006/124 | T2 DI SMTVIL-CMP FW 6/124 RMV BUTT | SACTO | ETL.7970.POLE.WOOD | 2023-04-21 | 2023-04-11 | 2023-10-10 | On-time | 2024-04-10 | 183 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 46004015 | T2 DI SMTVIL-CMP FW 6/124 RMV BUTT | ICW
LC | 125969764 | 010/000 | T2 DI MELONES-CURTIS 10/0 X-BRACE | VICTOR | ETL.2390.POLE.WDPS | 2023-04-21 | 2023-04-11 | 2024-02-20 | On-time | 2024-04-10 | 50 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46016353 | T2 DI MELONES-CURTIS 10/0 X-BRACE | ICW
LC | 125969824 | 015/081 | T2 DI VACA-PARKWAY 15/81 RPL DMPS | SACTO | ETL.5850.INSL | 2023-04-21 | 2023-04-11 | 2023-11-21 | On-time | 2024-04-10 | 141 | 2024-04-11 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 45985058 | T2 DI VACA-PARKWAY 15/81 RPL DMPS | ICS
LC | 125937138 | 025/406 | T2 EI KESWICK-TRINITY 025/406 RPL INSW | TABLEMTN | ETL.7270.INSL.CERA | 2023-04-17 | 2023-04-17 | 2024-04-23 | Late | 2024-04-16 | -7 | 2024-04-17 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35513060 | T2 EI KESWICK-TRINITY 24/391 RPL INSW | 93I
LC | 125937298 | 025/405 | T2 EI KESWICK-TRINITY 025/405 REFRAME | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-17 | 2023-04-17 | 2024-04-23 | Late | 2024-04-16 | -7 | 2024-04-17 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35512899 | T2 EI KESWICK-TRINITY 024/385 REFRAME | 93E
LC | 125937300 | 025/403 | T2 EI KESWICK-TRINITY 025/403 RPR INSW | TABLEMTN | ETL.7270.INSL.CERA | 2023-04-17 | 2023-04-17 | 2024-04-23 | Late | 2024-04-16 | -7 | 2024-04-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46026272 | T2 EI KESWICK-TRINITY 025/403 RPR INSW | ICW
LC | 125937305 | 025/404 | T2 EI KESWICK-TRINITY 025/404 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-17 | 2023-04-17 | 2024-04-23 | Late | 2024-04-16 | -7 | 2024-04-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512896 | T2 DI KESWICK-TRINITY 21/329 RPL POLE | 70Y
LC | 125969867 | 009/165 | T2 DI CLMN RD BLF 09/165 RPR SPLW | TABLEMTN | ETL.6440.INSL.CERA | 2023-04-21 | 2023-04-11 | 2023-04-26 | On-time | 2024-04-10 | 350 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 45764673 | T2 DI CLMN RD BLF 09/165 RPR SPLW | ICW
LC | 125971059 | 009/053 | T2 DI VACA-PARKWAY 09/53 RPL HRDT | SACTO | ETL.5850.TOWR | 2023-04-21 | 2023-04-11 | 2024-03-25 | On-time | 2024-04-10 | 16 | 2024-04-11 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46009045 | T2 DI VACA-PARKWAY 09/53 RPL HRDT | ICQ
LC | 125938738 | 032/001 | T2 EI MNDCNO-WLTS-FRT BRG 32/01 RPR INSW | WILLITS | ETL.7550.INSL.NCER | 2023-04-17 | 2023-04-17 |  | Late | 2024-04-16 |  | 2023-10-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46216622 | T2 EI MNDCNO-WLTS-FRT BRG 32/01 RPR INSW | ICW
LC | 125940431 | 027/000 | T2 PHILO JCT-ELK 27/0 RPL TIED | WILLITS | ETL.7780.INSL.CERA | 2023-04-18 | 2023-04-18 |  | Late | 2024-04-17 |  | 2024-04-18 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46213855 | T2 PHILO JCT-ELK 27/0 RPL TIED | ICW
LC | 125971373 | A011/197 | T2 DI COLEMN-RED BLUFF A11/197 RPL POLE | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-21 | 2023-04-11 | 2024-04-03 | On-time | 2024-04-10 | 7 | 2024-04-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495178 | T2 DI COLEMN-RED BLUFF A11/197 RPL POLE | 70Y
LC | 125941285 | 028/195A | T2 EI TRINITY-COTTONWOOD 028/195A UNBURY | TABLEMTN | ETL.4040.POLE.NWOD | 2023-04-18 | 2023-04-18 |  | Late | 2024-04-17 |  | 2024-04-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46027004 | T2 EI TRINITY-COTTONWOOD 028/195A UNBURY | ICW
LC | 125941579 | 016/008 | T2 EI HMBLDT BY-RO DLL JCT 16/8 RPL STRW | EUREKA | ETL.7100.POLE.WOOD | 2023-04-18 | 2023-04-18 |  | Late | 2024-04-17 |  | 2024-04-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35502390 | T2 EI HMBLDT BY-RO DLL JCT 16/8 RPL STRW | 70Y
LC | 125941618 | 028/195B | T2 EI TRINITY-COTTONWOOD 28/195B RMV VEG | TABLEMTN | ETL.4040.POLE.NWOD | 2023-04-18 | 2023-04-18 | 2024-06-20 | Late | 2024-04-17 | -64 | 2024-04-18 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125971397 | 014/255 | T2 DI COLEMAN-RED BLUFF 014/255 RPR CNDW | TABLEMTN | ETL.6440.INSL.NCER | 2023-04-21 | 2023-04-11 | 2024-03-07 | On-time | 2024-04-10 | 34 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46011746 | T2 DI COLEMAN-RED BLUFF 014/255 RPR CNDW | ICW
LC | 125971460 | 000/001 | T2 DI JEFFERSON #1 00/01 RPR STRW | METCALF | ETL.6831.POLE.WOOD | 2023-04-21 | 2023-04-11 | 2024-02-22 | On-time | 2024-04-10 | 48 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46012966 | T2 DI JEFFERSON #1 00/01 RPR STRW | ICW
LC | 125971747 | 010/086B | T2 DI PIT #6 JCT-RND MTN 10/86B RPR GYWW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-04-21 | 2023-04-11 | 2023-05-19 | On-time | 2024-04-10 | 327 | 2023-07-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45749659 | T2 DI PIT #6 JCT-RND MTN 10/86B RPR GYWW | ICW
LC | 125941942 | 016/006 | T2 EI HMBLDT BY-RO DLL JCT 16/6 RPL STRW | EUREKA | ETL.7100.POLE.WOOD | 2023-04-18 | 2023-04-18 |  | Late | 2024-04-17 |  | 2024-04-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35502389 | T2 EI HMBLDT BY-RO DLL JCT 16/6 RPL STRW | 70Y
LC | 125971879 | 009/169 | T2 DI COLEMAN-RED BLUFF 09/169 RPR CNDW | TABLEMTN | ETL.6440.INSL | 2023-04-21 | 2023-04-11 | 2024-03-25 | On-time | 2024-04-10 | 16 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46011755 | T2 DI COLEMAN-RED BLUFF 09/169 RPR CNDW | ICW
LC | 125941966 | 028/195C | T2 EI TRNTY-CTTNWD 028/195C RMV VEG | TABLEMTN | ETL.4040.POLE.NWOD | 2023-04-18 | 2023-04-18 | 2024-06-20 | Late | 2024-04-17 | -64 | 2024-04-18 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125942254 | 009/192 | T2 EI VALLEY SPRINGS #1 9/192 RPL STRW | VICTOR | ETL.8210.POLE.WOOD | 2023-04-18 | 2023-04-18 |  | Late | 2024-04-17 |  | 2024-04-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512411 | T2 EI VALLEY SPRINGS #1 009/192 RPL POLE | 70Y
LC | 125942362 | 024/391 | T2 EI KESWICK-TRINITY 24/391 RPL INSW | TABLEMTN | ETL.7270.INSL.CERA | 2023-04-18 | 2023-04-18 | 2024-04-30 | Late | 2024-04-17 | -13 | 2024-04-18 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35513060 | T2 EI KESWICK-TRINITY 24/391 RPL INSW | 93I
LC | 125971898 | 024/115 | T2 DI MNTA VSTA-COYTE SS 24/115 RPL INSS | MOSSLNDG | ETL.5090.INSL | 2023-04-21 | 2023-04-11 | 2024-03-11 | On-time | 2024-04-10 | 30 | 2024-04-11 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513894 | MONTA VISTA-COYOTE SW STA 24/115 RPL IN | 93K
LC | 125942807 | 024/005 | T2 EI GARBERVILLE-LAYTONVL 24/5 RPR STRW | WILLITS | ETL.8365.POLE.WOOD | 2023-04-18 | 2023-04-18 |  | Late | 2024-04-17 |  | 2024-04-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46219470 | T2 EI GARBERVILLE-LAYTONVL 24/5 RPR POLE | ICW
LC | 125943319 | 024/385 | T2 EI KESWICK-TRINITY 024/385 REFRAME | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-18 | 2023-04-18 | 2024-04-23 | Late | 2024-04-17 | -6 | 2024-04-18 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35512899 | T2 EI KESWICK-TRINITY 024/385 REFRAME | 93E
LC | 125972495 | 011/189 | T2 DI CLMN-RED BLUFF 011/189 RPL STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-22 | 2023-04-11 | 2024-03-26 | On-time | 2024-04-10 | 15 | 2024-04-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495177 | T2 DI CLMN-RED BLUFF 010/178 RPL STRW | 70Y
LC | 125972505 | 009/154 | T2 DI COLEMN-RED BLF 9/154 RPR STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-22 | 2023-04-11 | 2024-03-25 | On-time | 2024-04-10 | 16 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46011758 | T2 DI COLEMN-RED BLF 9/154 RPR STRW | ICW
LC | 125972513 | A011/195 | T2 DI COLEMN-RED BLUFF A11/195 RPR POLE | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-22 | 2023-04-11 | 2024-04-03 | On-time | 2024-04-10 | 7 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46011743 | T2 DI COLEMN-RED BLUFF A11/195 RPR POLE | ICW
LC | 125972623 | 009/155 | T2 DI COLEMAN-RED BLUFF 9/155 RPR POLE | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-22 | 2023-04-11 | 2024-03-25 | On-time | 2024-04-10 | 16 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46011757 | T2 DI COLEMAN-RED BLUFF 9/155 RPR POLE | ICW
LC | 125944674 | 053/230 | T2 EI RND MTN-TBL MTN #2 53/230 BNT STEL | TABLEMTN | ETL.6070.TOWR | 2023-04-18 | 2023-04-18 |  | Late | 2024-04-17 |  | 2024-04-18 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46028565 | T2 EI RND MTN-TBL MTN #2 53/230 BNT STEL | ICQ
LC | 125972730 | 012/211 | T2 DI COLEMAN-RED BLUFF 12/211 RPL DMPW | TABLEMTN | ETL.6440.INSL.NCER | 2023-04-22 | 2023-04-11 | 2024-03-06 | On-time | 2024-04-10 | 35 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46011749 | T2 DI COLEMAN-RED BLUFF 12/211 RPL DMPW | ICW
LC | 125972773 | 010/002 | T2 DI MELS-CURTIS 10/2R RPR POLE | VICTOR | ETL.2390.POLE.WDPS | 2023-04-22 | 2023-04-11 | 2024-02-20 | On-time | 2024-04-10 | 50 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46161636 | T2 DI MELS-CURTIS 10/2R RPR POLE | ICW
LC | 125972776 | 010/002 | T2 DI MELS-CURTIS 10/2L RPR POLE | VICTOR | ETL.2390.POLE.WDPS | 2023-04-22 | 2023-04-11 | 2024-02-20 | On-time | 2024-04-10 | 50 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46161637 | T2 DI MELS-CURTIS 10/2L RPR POLE | ICW
LC | 125972805 | 014/259 | T2 DI COLEMN-RED BLUFF 14/259 RPR GYWW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-22 | 2023-04-11 | 2023-07-04 | On-time | 2024-04-10 | 281 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 125972914 | 011/196 | T2 DI COLEMAN-RED BLUFF 11/196 RPL DAMW | TABLEMTN | ETL.6440.INSL.NCER | 2023-04-22 | 2023-04-11 | 2024-03-06 | On-time | 2024-04-10 | 35 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46011750 | T2 DI COLEMAN-RED BLUFF 11/196 RPL DAMW | ICW
LC | 125973066 | 009/159 | T2 DI CLMN-RED BLUFF 009/159 RPR IBWW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-22 | 2023-04-11 | 2024-03-25 | On-time | 2024-04-10 | 16 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46011756 | T2 DI CLMN-RED BLUFF 009/159 RPR IBWW | ICW
LC | 125974049 | A011/199 | T2 DI COLEMN-RED BLUFF A11/199C RPL POLE | TABLEMTN | ETL.6440.POLE.WDPS | 2023-04-22 | 2023-04-11 | 2023-05-22 | On-time | 2024-04-10 | 324 | 2024-04-11 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31643365 | T2 DI COLEMN-RED BLUFF A11/199C RPL POLE | 70Y
LC | 125974070 | A011/199 | T2 DI COLEMN-RED BLUFF A11/199L RPL POLE | TABLEMTN | ETL.6440.POLE.WDPS | 2023-04-22 | 2023-04-11 | 2023-05-22 | On-time | 2024-04-10 | 324 | 2024-04-11 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31643365 | T2 DI COLEMN-RED BLUFF A11/199C RPL POLE | 70Y
LC | 125974113 | A011/199 | T2 DI COLEMN-RED BLUFF A11/199R RPL POLE | TABLEMTN | ETL.6440.POLE.WDPS | 2023-04-22 | 2023-04-11 | 2023-05-22 | On-time | 2024-04-10 | 324 | 2024-04-11 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31643365 | T2 DI COLEMN-RED BLUFF A11/199C RPL POLE | 70Y
LC | 125946699 | 034/000 | T2 EI MNDCNO-WLLTS-FB 034/000 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2023-04-18 | 2023-04-18 |  | Late | 2024-04-17 |  | 2024-04-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521521 | T2 EI MNDCNO-WLLTS-FRT BRGG 7/5 RPL POLE | 70Y
LC | 125946725 | 034/001 | T2 EI MNDCNO-WLTS-FRT BRG 34/01 RPL ANCW | WILLITS | ETL.7550.POLE.WOOD | 2023-04-18 | 2023-04-18 |  | Late | 2024-04-17 |  | 2024-04-18 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35521378 | T2 MNDCNO-WLITS-FRT BRG 2/13 RPL ANCW | 93E
LC | 125974999 | 005/002 | T2 DI FT BRG-ELK 5/2L RMV VEG OG | WILLITS | ETL.2060.POLE.WDPS | 2023-04-22 | 2023-04-11 | 2024-03-22 | On-time | 2024-04-10 | 19 | 2024-04-11 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125947106 | 006/003 | HUMBOLDT-MAPLE CREEK 6/3 RPR GO95 CLEAR | EUREKA | ETL.7130.POLE.WOOD | 2023-04-18 | 2023-04-18 | 2024-05-20 | Late | 2024-04-17 | -33 | 2024-04-18 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31642676 | HUMBOLDT-MAPLE CREEK 6/3 RPR GO95 CLEAR | 93G
LC | 126044697 | 004/092 | T2 DEL MONTE-VIEJO 4/92 GO95 CLEAR | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-05-03 | 2023-04-11 | 2023-06-10 | On-time | 2024-04-10 | 305 | 2023-07-11 | 401 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31644161 | T2 DEL MONTE-VIEJO 4/92 GO95 CLEAR | 93G
LC | 125870910 | B016/362 | T2 EI DRM-GRSS VLY-WMR B16/362 RPR STRW | SACTO | ETL.6760.POLE.WOOD | 2023-04-12 | 2023-04-12 | 2024-04-02 | On-time | 2024-04-11 | 9 | 2024-04-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46011669 | T2 EI DRM-GRSS VLY-WMR B16/362 RPR STRW | ICW
LC | 125872077 | 049/216 | T2 EI RND MTN-TBL MTN #2 49/216 COTTER | TABLEMTN | ETL.6070.TOWR | 2023-04-12 | 2023-04-12 | 2023-05-25 | On-time | 2024-04-11 | 322 | 2023-07-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45749656 | T2 EI RND MTN-TBL MTN #2 49/216 COTTER | ICS
LC | 125872329 | 050/217 | T2 EI RND MTN-TBL MTN #1 50/217 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2023-04-12 | 2023-04-12 | 2023-11-15 | On-time | 2024-04-11 | 148 | 2024-04-12 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46009048 | T2 EI RND MTN-TBL MTN #1 50/217 RPR STRT | ICQ
LC | 125872777 | 027/453 | T2 EI KESWICK-TRINITY 27/453 RE-TIE | TABLEMTN | ETL.7270.INSL.CERA | 2023-04-12 | 2023-04-12 | 2023-07-23 | On-time | 2024-04-11 | 263 | 2023-07-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45752727 | T2 EI KESWICK-TRINITY 27/453 RE-TIE | ICW
LC | 125873095 | 019/005 | T2 EI FULTON-HOPLAND -_019/005 RPL HRDW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-04-12 | 2023-04-12 | 2023-05-23 | On-time | 2024-04-11 | 324 | 2024-04-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45882951 | T2 EI FULTON-HOPLAND -_019/005 RPL HRDW | ICW
LC | 125947446 | 032/131 | T2 DI DIABLO-MIDWAY #3 32/131 RPR GYWT | PISMOBCH | ETL.5980.TOWR | 2023-04-18 | 2023-04-18 | 2024-04-18 | Late | 2024-04-17 | -1 | 2024-04-18 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46179820 | T2 DI DIABLO-MIDWAY #3 32/131 RPR GYWT | ICQ
LC | 125873712 | 019/004 | T2 EI FULTON-HOPLAND 019/004 RPR GYWW | LAKEVLLE | ETL.6890.POLE.NWOD | 2023-04-12 | 2023-04-12 | 2023-11-09 | On-time | 2024-04-11 | 154 | 2024-04-12 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46045922 | T2 EI FULTON-HOPLAND 019/004 RPR GYWW | ICS
LC | 125873868 | 017/006 | T2 EI FORT BRAGG-ELK 017/006 RMV VEG | WILLITS | ETL.2060.POLE.WOOD | 2023-04-12 | 2023-04-12 | 2024-04-11 | On-time | 2024-04-11 | 0 | 2024-04-12 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125874121 | 017/005 | T2 EI FORT BRAGG-ELK 017/005 RMV VEG | WILLITS | ETL.2060.POLE.WOOD | 2023-04-12 | 2023-04-12 | 2024-04-11 | On-time | 2024-04-11 | 0 | 2024-04-12 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125875208 | 002/032 | T2 WV JOLON TAP 002/032 RPL DMPS | MOSSLNDG | ETL.7321.INSL.NCER | 2023-04-12 | 2023-04-12 | 2023-12-11 | On-time | 2024-04-11 | 122 | 2024-04-12 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 46015916 | T2 WV JOLON TAP 002/032 RPL DMPS | ICS
LC | 125875255 | 050/219 | T2 EI RND MTN-TBL MTN #2 -_50/219 BNT ST | TABLEMTN | ETL.6070.TOWR | 2023-04-12 | 2023-04-12 | 2023-11-15 | On-time | 2024-04-11 | 148 | 2024-04-12 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46009049 | T2 EI RND MTN-TBL MTN #2 -_50/219 BNT ST | ICQ
LC | 125947738 | 008/121 | T2 DI DLTA-MTN GT JCT 8/121 RPL TIED | TABLEMTN | ETL.6750.INSL.CERA | 2023-04-18 | 2023-04-05 |  | Late | 2024-04-04 |  | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45999423 | T2 DI DLTA-MTN GT JCT 8/121 RPL TIED | ICW
LC | 125947770 | 000/009 | T2 DI NARROWS #2 TAP 0/9 GO95 | SACTO | ETL.6521.POLE.WOOD | 2023-04-18 | 2023-04-05 |  | Late | 2024-04-04 |  | 2024-04-05 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35481578 | T2 DI NARROWS #2 TAP 0/9 GO95 | 93G
LC | 125875883 | 002/032 | T2 WV JOLON TAP_002/032 RPL DAMPERS | MOSSLNDG | ETL.7321.INSL.NCER | 2023-04-12 | 2023-04-12 | 2023-12-11 | On-time | 2024-04-11 | 122 | 2024-04-12 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46015914 | T2 WV JOLON TAP_002/032 RPL DAMPERS | ICW
LC | 125875950 | 012/104 | T2 EI CRAG VIEW-CASCADE 012/104 RPL HRDW | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-12 | 2023-04-12 | 2024-02-28 | On-time | 2024-04-11 | 43 | 2024-04-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46011643 | T2 EI CRAG VIEW-CASCADE 012/104 RPL HRDW | ICW
LC | 125949481 | 025/001 | T2 EI GARBERVILL-LAYTONVIL 25/1 RPR INSW | WILLITS | ETL.8365.INSL.NCER | 2023-04-19 | 2023-04-19 |  | Late | 2024-04-18 |  | 2024-04-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46219469 | T2 EI GARBERVILL-LAYTONVIL 25/1 RPR INSW | ICW
LC | 125878711 | 011/102 | T2 EI CRAG VIEW-CASCADE 11/102L RPL POLE | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-12 | 2023-04-12 | 2024-02-29 | On-time | 2024-04-11 | 42 | 2024-04-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 125878977 | 011/102 | T2 EI CRAG VIEW-CASCADE 11/102R RPL POLE | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-12 | 2023-04-12 | 2024-02-29 | On-time | 2024-04-11 | 42 | 2024-04-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 125950193 | 010/227 | T2 EI SALINAS-LAURELES 10/227 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-04-19 | 2023-04-19 |  | Late | 2024-04-18 |  | 2024-04-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35507058 | T2 EI SALINAS-LAURELES 10/227 RPL STRW | 70Y
LC | 125881859 | 051/220 | T2 EI RND MTN-TBL MTN #2 52/220 BNT STEL | TABLEMTN | ETL.6070.TOWR | 2023-04-12 | 2023-04-12 | 2024-03-13 | On-time | 2024-04-11 | 29 | 2024-04-12 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46009050 | T2 EI RND MTN-TBL MTN #2 52/220 BNT STEL | ICQ
LC | 125882338 | 026/195 | T2 EI DRUM-RIO OSO #2 026/195 RPL INSS | SACTO | ETL.1430.INSL.CERA | 2023-04-12 | 2023-04-12 | 2024-01-17 | On-time | 2024-04-11 | 85 | 2024-04-12 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671114 | T2 EI DRUM-RIO OSO #2 RPL INSS | 93K
LC | 125884292 | 008/048 | T2 BALCH-SANGER 008/048 RPR FOUND | FRESNO | ETL.1050.TOWR | 2023-04-12 | 2023-04-12 | 2023-07-11 | On-time | 2024-04-11 | 275 | 2023-07-12 | 527 | TLQ | CREW | E - Schd Compl Yr 0 | Closed | TR2 | Other | Emergency-Steel | Replace | 31642142 | T2 BALCH-SANGER - 115 KV_008/048 | 92S
LC | 125950447 | 025/003 | T2 EI GARBERVILLE-LAYTONVL 25/3 RPR STRW | WILLITS | ETL.8365.POLE.WOOD | 2023-04-19 | 2023-04-19 |  | Late | 2024-04-18 |  | 2023-10-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46219468 | T2 EI GARBERVILLE-LAYTONVL 25/3 RPR POLE | ICW
LC | 125908135 | 010/045 | T2 DI MT VTA-JEFFR #1 10/45 COTTER | METCALF | ETL.5220.INSL | 2023-04-14 | 2023-04-12 | 2023-10-18 | On-time | 2024-04-11 | 176 | 2024-04-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46012972 | T2 DI MT VTA-JEFFR #1 10/45 COTTER | ICS
LC | 125911081 | 002/022 | T2 DI BKS CRK-RK CK-CTA 2/22 HANGER | TABLEMTN | ETL.4430.TOWR | 2023-04-14 | 2023-04-12 | 2024-01-15 | On-time | 2024-04-11 | 87 | 2024-04-12 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46028541 | T2 DI BKS CRK-RK CK-CTA 2/22 HANGER | ICQ
LC | 125951221 | 054/234 | T2 EI RND MTN-TBL MTN #1 54/234 RPL ANCT | TABLEMTN | ETL.6060.TOWR | 2023-04-19 | 2023-04-19 |  | Late | 2024-04-18 |  | 2024-04-19 | 93Z | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Tower | Replace | 31673791 | T2 EI RND MTN-TBL MTN #1 54/234 RPL ANCS | 93Z
LC | 125914630 | 001/032 | T2 DI JEFFERSON-STANFORD 001/032 RMV VEG | METCALF | ETL.7220.POLE.WOOD | 2023-04-14 | 2023-04-12 | 2024-03-26 | On-time | 2024-04-11 | 16 | 2024-04-12 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125920046 | 001/015 | T2 DI ROCK CREEK POE 01/015 RPL INST | TABLEMTN | ETL.5630.INSL.CERA | 2023-04-14 | 2023-04-12 | 2024-02-25 | On-time | 2024-04-11 | 46 | 2024-04-12 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671289 | T2 DI ROCK CREEK-POE 3 TWRS RPL INSS | 93K
LC | 125951647 | 023/370 | T2 EI KSWK-TRTY-WRVLE 023/370 RPR INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-19 | 2023-04-19 | 2024-04-19 | Late | 2024-04-18 | -1 | 2024-04-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46026981 | T2 EI KSWK-TRTY-WRVLE 023/370 RPR INSW | ICW
LC | 125951700 | 023/367 | T2 EI KESWICK-TRINITY 023/367 RPL HRDW | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-19 | 2023-04-19 | 2024-04-30 | Late | 2024-04-18 | -12 | 2024-04-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46026980 | T2 EI KESWICK-TRINITY 023/367 RPL HRDW | ICW
LC | 125922926 | 012/170 | T2 DI ATSCDRO-SN LS OBS 12/170 BNT STEEL | PISMOBCH | ETL.8490.TOWR | 2023-04-14 | 2023-04-12 | 2024-01-29 | On-time | 2024-04-11 | 73 | 2024-04-12 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46031620 | T2 DI ATSCDRO-SN LS OBS 12/170 BNT STEEL | ICQ
LC | 125952583 | 054/235 | T2 EI RND MT-TBL MTN #2 54/235 RPR CNDS | TABLEMTN | ETL.6070.INSL.NCER | 2023-04-19 | 2023-04-19 | 2024-05-03 | Late | 2024-04-18 | -15 | 2024-04-19 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46229501 | T2 EI RND MT-TBL MTN #2 54/235 RPR CNDS | ICS
LC | 125922990 | 003/015 | T2 DI SAN LUS OBSPO CAYCS 3/15 COTTER | PISMOBCH | ETL.9090.INSL | 2023-04-14 | 2023-04-12 | 2024-04-09 | On-time | 2024-04-11 | 2 | 2024-04-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46079007 | T2 DI SAN LUS OBSPO CAYCS 3/15 COTTER | ICS
LC | 125926834 | 004/042 | T2 DI MONTA VST-BRNS 4/42 RPR GYW | MOSSLNDG | ETL.7590.POLE.STPS | 2023-04-15 | 2023-04-12 | 2024-02-28 | On-time | 2024-04-11 | 43 | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46016599 | T2 DI MONTA VST-BRNS 4/42 RPR GYW | ICW
LC | 125928328 | 014/077 | T2 DI VACA-PARKWAY- 14/77 COTTER | SACTO | ETL.5850.INSL | 2023-04-15 | 2023-04-12 | 2023-11-21 | On-time | 2024-04-11 | 142 | 2024-04-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45985056 | T2 DI VACA-PARKWAY- 14/77 COTTER | ICS
LC | 125965517 | A012/208 | T2 DI CLMN RD BLF 12/208 RPR JUMW | TABLEMTN | ETL.6440.INSL.NCER | 2023-04-21 | 2023-04-12 | 2023-05-15 | On-time | 2024-04-11 | 332 | 2023-10-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45749608 | T2 DI CLMN RD BLF 12/208 RPR JUMW | ICW
LC | 125968351 | 014/124 | T2 DI PIT #6-RD MTN 14/124L RPL STRW | TABLEMTN | ETL.5440.POLE.WDPS | 2023-04-21 | 2023-04-12 | 2023-11-15 | On-time | 2024-04-11 | 148 | 2024-04-12 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31655583 | PIT #6 JCT-ROUND MTN 14/123&14/124 REPL | 70Y
LC | 125953194 | 021/006 | T2 EI BRIDGEVILL-GARBERVLL 21/6 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2023-04-19 | 2023-04-19 |  | Late | 2024-04-18 |  | 2024-04-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35502381 | T2 EI BRIDGEVILL-GARBERVLL 21/6 RPL POLE | 70Y
LC | 125968355 | 014/124 | T2 DI PIT #6-RD MTN 14/124R RPL STRW | TABLEMTN | ETL.5440.POLE.WDPS | 2023-04-21 | 2023-04-12 | 2023-11-15 | On-time | 2024-04-11 | 148 | 2024-04-12 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31655583 | PIT #6 JCT-ROUND MTN 14/123&14/124 REPL | 70Y
LC | 125969424 | 001/027 | T2NT DI JEFFERSON-STANFORD 1/27 RMV STEP | METCALF | ETL.7220.POLE.WOOD | 2023-04-21 | 2023-04-12 | 2023-11-07 | On-time | 2024-04-11 | 156 | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45997324 | T2NT DI JEFFERSON-STANFORD 1/27 RMV STEP | ICW
LC | 125972556 | 014/123 | T2 DI PIT#6JCT RND MTN 14/123R RPL STRW | TABLEMTN | ETL.5440.POLE.WDPS | 2023-04-22 | 2023-04-12 | 2023-11-14 | On-time | 2024-04-11 | 149 | 2023-10-12 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31655583 | PIT #6 JCT-ROUND MTN 14/123&14/124 REPL | 70Y
LC | 125972557 | 014/123 | T2 DI PIT#6JCT RND MTN 14/123L RPL STRW | TABLEMTN | ETL.5440.POLE.WDPS | 2023-04-22 | 2023-04-12 | 2023-11-14 | On-time | 2024-04-11 | 149 | 2023-10-12 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31655583 | PIT #6 JCT-ROUND MTN 14/123&14/124 REPL | 70Y
LC | 125954512 | 026/001 | T2 EI GARBERVILLE-LAYTONVL 26/1 RPL STRW | WILLITS | ETL.8365.POLE.WOOD | 2023-04-19 | 2023-04-19 |  | Late | 2024-04-18 |  | 2024-04-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487987 | T2 EI GARBERVILLE-LAYTONVL 26/1 RPL POLE | 70Y
LC | 125972709 | 012/107C | T2 DI PIT#6 JCT RND MTN 12/107C RPR GYWW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-04-22 | 2023-04-12 | 2023-05-06 | On-time | 2024-04-11 | 341 | 2023-07-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45749703 | T2 DI PIT#6 JCT RND MTN 12/107C RPR GYWW | ICW
LC | 125972915 | 010/193 | T2NT DI VALLEY SPRNGS #2 10/193 BACKFILL | VICTOR | ETL.9460.POLE.WOOD | 2023-04-22 | 2023-04-12 | 2023-09-02 | On-time | 2024-04-11 | 222 | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45907575 | T2NT DI VALLEY SPRNGS #2 10/193 BACKFILL | ICW
LC | 125973037 | 012/107B | T2 DI PIT#6 JCT RND MTN 12/107B RPR GYWW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-04-22 | 2023-04-12 | 2023-05-06 | On-time | 2024-04-11 | 341 | 2023-07-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45749705 | T2 DI PIT#6 JCT RND MTN 12/107B RPR GYWW | ICW
LC | 125973087 | A013/213 | T2 DI COLEMAN-RED BLFF A13/213 RPR GYWW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-22 | 2023-04-12 | 2023-11-20 | On-time | 2024-04-11 | 143 | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011698 | T2 DI COLEMAN-RED BLFF A13/213 RPR GYWW | ICW
LC | 125973096 | 008/000 | T2 DI MELONES-CURTIS 8/0R RPR POLE | VICTOR | ETL.2390.POLE.WDPS | 2023-04-22 | 2023-04-12 | 2023-10-27 | On-time | 2024-04-11 | 167 | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45976983 | T2 DI MELONES-CURTIS 8/0R RPR POLE | ICW
LC | 125955396 | 044/005 | T2 DI ELK-GUALALA 44/5L RPL POLE | WILLITS | ETL.8410.POLE.WDPS | 2023-04-19 | 2023-04-06 | 2024-04-25 | Late | 2024-04-05 | -20 | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487275 | T2 DI ELK-GUALALA 44/5L RPL POLE | 70Y
LC | 125955679 | 018/003 | T2 DI MNDCNO-PHL JT-HPLND 18/3 RPL STRW | WILLITS | ETL.7520.POLE.WOOD | 2023-04-19 | 2023-04-07 |  | Late | 2024-04-06 |  | 2023-07-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495642 | T2 DI MNDCNO-PHL JT-HPLND 18/3 RPL STRW | 70Y
LC | 125955727 | 013/001 | T2 DI LWR LAKE-HMSTK 013/001 RPL STRW | WILLITS | ETL.1481.POLE.WOOD | 2023-04-19 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35488188 | T2 DI LWR LAKE-HMSTK 013/001 RPL STRW | 70Y
LC | 125973627 | 002/021 | T2 DI BCKS CRK-RCK CRK-CRST 2/21 RP SPLS | TABLEMTN | ETL.4430.INSL.NCER | 2023-04-22 | 2023-04-12 | 2024-01-18 | On-time | 2024-04-11 | 84 | 2024-04-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Steel | Repair | 46011622 | T2 DI BCKS CRK-RCK CRK-CRST 2/21 RP SPLS | ICS
LC | 125955779 | 025/178 | 125955779NITY-CTTNWD 25/178L RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-19 | 2023-04-14 | 2024-06-24 | Late | 2024-04-13 | -72 | 2023-10-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011637 | T2 DI TRINITY-CTTNWD 25/178L RPR GYWW | ICW
LC | 125973661 | 001/025 | T2 DI JEFFERSON-STANFORD 001/025 RMV VEG | METCALF | ETL.7220.POLE.WOOD | 2023-04-22 | 2023-04-12 | 2024-03-26 | On-time | 2024-04-11 | 16 | 2024-04-12 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125955808 | 018/010 | T2 DI MNDO-PHILO-JCT-HPLND 18/10 RPL STR | WILLITS | ETL.7520.POLE.WOOD | 2023-04-19 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495642 | T2 DI MNDCNO-PHL JT-HPLND 18/3 RPL STRW | 70Y
LC | 125955819 | 000/012 | T2 DI MLNS-RCTRCK 000/012 RPL STRW | VICTOR | ETL.2400.POLE.WOOD | 2023-04-19 | 2023-04-06 | 2024-05-13 | Late | 2024-04-05 | -38 | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507611 | T2 DI MLNS-RCTRCK 000/012 RPL STRW | 70Y
LC | 125973982 | 012/107A | T2 DI PIT#6JCT-RND MTN 12/107A COMPLETE | TABLEMTN | ETL.5440.POLE.NWOD | 2023-04-22 | 2023-04-12 | 2023-05-19 | On-time | 2024-04-11 | 328 | 2024-04-12 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace
LC | 125955836 | 012/009 | T2 DI MNDO-PHILO-JCT-HPLND 12/9 RPL STRW | WILLITS | ETL.7520.POLE.WOOD | 2023-04-19 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495641 | T2 DI MNDCN PHL JCT HPLND 11/07 RPL POLE | 70Y
LC | 125955855 | 036/000 | T2 DI PHILO JCT-ELK 036/000 RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-19 | 2023-04-06 | 2024-06-13 | Late | 2024-04-05 | -69 | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493613 | T2 DI PHILO JCT-ELK 036/000 RPL STRW | 70Y
LC | 125974342 | 009/003 | T2 DI MELONES-CURTIS 009/003 RPR GYWW | VICTOR | ETL.2390.POLE.STPS | 2023-04-22 | 2023-04-12 | 2023-05-30 | On-time | 2024-04-11 | 317 | 2023-10-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45763206 | T2 DI MELONES-CURTIS 009/003 RPR GYWW | ICW
LC | 125974344 | 009/003 | T2 DI MELONES-CURTIS 009/003 RPR GYWW | VICTOR | ETL.2390.POLE.STPS | 2023-04-22 | 2023-04-12 | 2023-05-30 | On-time | 2024-04-11 | 317 | 2023-10-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45763205 | T2 DI MELONES-CURTIS 009/003 RPR GYWW | ICW
LC | 125974345 | 009/003 | T2 DI MELONES-CURTIS 009/003 RPR ANCW | VICTOR | ETL.2390.POLE.STPS | 2023-04-22 | 2023-04-12 | 2023-05-30 | On-time | 2024-04-11 | 317 | 2023-10-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45763204 | T2 DI MELONES-CURTIS 009/003 RPR ANCW | ICW
LC | 125974346 | 009/003 | T2 DI MELONES-CURTIS 009/003 RPR ANCW | VICTOR | ETL.2390.POLE.STPS | 2023-04-22 | 2023-04-12 | 2023-05-30 | On-time | 2024-04-11 | 317 | 2023-10-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45763203 | T2 DI MELONES-CURTIS 009/003 RPR ANCW | ICW
LC | 125956374 | 009/004 | T2 DI MELONES-CURTIS 09/04L CANCEL | VICTOR | ETL.2390.POLE.STPS | 2023-04-20 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35530995 | T2 DI MELONES-CURTIS 09/04L RPL ANCW | 93E
LC | 125956499 | 001/027 | T2 DELTA-MTN GATE JCT 1/27 RPL POLE | TABLEMTN | ETL.6750.POLE.WOOD | 2023-04-20 | 2023-04-19 |  | Late | 2024-04-18 |  | 2024-04-19 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507617 | T2 DELTA-MTN GATE JCT 1/27 RPL POLE | 70Y
LC | 125974421 | A012/211 | T2 DI CLMN-RED BLUFF A012/211 RPR INSW | TABLEMTN | ETL.6440.INSL.NCER | 2023-04-22 | 2023-04-12 | 2023-11-13 | On-time | 2024-04-11 | 150 | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011699 | T2 DI CLMN-RED BLUFF A012/211 RPR INSW | ICW
LC | 125974516 | 001/029 | T2 DI JEFFERSON-STANFORD 001/029 RMV VEG | METCALF | ETL.7220.POLE.WOOD | 2023-04-22 | 2023-04-12 | 2024-03-26 | On-time | 2024-04-11 | 16 | 2024-04-12 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125956780 | 003/064 | T2 DI SMRTVL-MRYSV 3/64 RPL STRW | SACTO | ETL.7980.POLE.WOOD | 2023-04-20 | 2023-04-10 | 2024-05-07 | Late | 2024-04-09 | -28 | 2024-04-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495176 | T2 DI SMRTVL-MRYSV 3/64 RPL STRW | 70Y
LC | 125983805 | 012/105 | T2 DI PIT #6 JCT-RND MTN 12/105 RPR STRW | TABLEMTN | ETL.5440.POLE.WDPS | 2023-04-24 | 2023-04-12 | 2023-11-13 | On-time | 2024-04-11 | 150 | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46011628 | T2 DI PIT #6 JCT-RND MTN 12/105 RPR STRW | ICW
LC | 125957243 | 010/122 | T2 DRUM-SUMMIT #1 010/122 INS WEIGHT | SACTO | ETL.1440.INSL.CERA | 2023-04-20 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Hardware-Wood | Install | 45824491 | T2 DRUM-SUMMIT #1 010/122 INS WEIGHT | ICW
LC | 125984277 | 000/006 | T2 DI JEFFERSON-STANFORD 00/06 RPR GYWW | METCALF | ETL.7220.POLE.WOOD | 2023-04-24 | 2023-04-12 | 2024-04-01 | On-time | 2024-04-11 | 10 | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46012978 | T2 DI JEFFERSON-STANFORD 00/06 RPR GYWW | ICW
LC | 125957564 | 027/005 | T2 EI GRBRVLL-LYTNVLL 027/05 COTTER | WILLITS | ETL.8365.INSL.NCER | 2023-04-20 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46219466 | T2 EI GRBRVLL-LYTNVLL 027/05 COTTER | ICW
LC | 125957641 | 032/006 | T2 EI MNDCNO-WLTS-FRT BRG 32/6 RPR INSW | WILLITS | ETL.7550.INSL.NCER | 2023-04-20 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46216623 | T2 EI MNDCNO-WLTS-FRT BRG 32/06 RPR INSW | ICW
LC | 125957844 | 022/349 | T2 EI KESWICK-TRINITY 22/349 GO95 | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-20 | 2023-04-20 | 2024-04-26 | Late | 2024-04-19 | -7 | 2024-04-20 | 401 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35512895 | T2 EI KESWICK-TRINITY 22/349 GO95 | 93G
LC | 125958107 | 021/004 | T2 EI CLEAR LAKE-KONOCTI 21/04 RPL POLE | WILLITS | ETL.6852.POLE.WOOD | 2023-04-20 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487139 | T2 EI CLEAR LAKE-KONOCTI 21/04 RPL POLE | 70Y
LC | 125958230 | 020/001 | T2 EI BRIDGEVILL-GARBERVLL 20/1 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2023-04-20 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504905 | T2 EI BRIDGEVILL-GARBERVLL 20/1 RPL POLE | 70Y
LC | 125984515 | A012/210 | T2 DI COLE- RED BL A12/210 RPR GYWW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-24 | 2023-04-12 | 2023-11-13 | On-time | 2024-04-11 | 150 | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011740 | T2 DI COLE- RED BL A12/210 RPR GYWW | ICW
LC | 125985022 | 001/024 | T2 DI JFFRSON STNFRD 01/024 RMV VEG | METCALF | ETL.7220.POLE.WOOD | 2023-04-25 | 2023-04-12 | 2024-03-26 | On-time | 2024-04-11 | 16 | 2024-04-12 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126000180 | 002/002 | T2 DI RACETRACK TAP 002/002 RPR HRDD | VICTOR | ETL.2393.POLE.WOOD | 2023-04-26 | 2023-04-12 | 2023-10-30 | On-time | 2024-04-11 | 164 | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46004169 | T2 DI RACETRACK TAP 002/002 RPR HRDD | ICW
LC | 125958596 | 020/000 | T2 EI BRIDGEVILL-GARBERVLL 20/0 RPL STRW | EUREKA | ETL.6220.POLE.WOOD | 2023-04-20 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504904 | T2 EI BRIDGEVILL-GARBERVLL 20/0 RPL POLE | 70Y
LC | 125896990 | 010/094 | T2 EI CRAG VIEW-CASCADE 10/94 RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-13 | 2023-04-13 | 2023-12-05 | On-time | 2024-04-12 | 129 | 2024-04-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011642 | T2 EI CRAG VIEW-CASCADE 10/94 RPR GYWW | ICW
LC | 125959160 | 024/384 | T2 KESWICK-TRINITY 24/384 COTTER | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-20 | 2023-04-20 | 2024-04-20 | Late | 2024-04-19 | -1 | 2024-04-20 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46026987 | T2 KESWICK-TRINITY 24/384 COTTER | ICW
LC | 125959181 | 020/010 | T2 EI BRIDGEVLL-GARBERVLL 20/10 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2023-04-20 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504906 | T2 EI BRIDGEVLL-GARBERVLL 20/10 RPL POLE | 70Y
LC | 125959228 | 026/008 | T2 EI GRBRVLL-LYTNVLL 026/08 RPR POLE | WILLITS | ETL.8365.POLE.WOOD | 2023-04-20 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46219467 | T2 EI GRBRVLL-LYTNVLL 026/08 RPR POLE | ICW
LC | 125897774 | 015/342 | T2 EI DRUM-GRAS VALY-WMR 15/342 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2023-04-13 | 2023-04-13 | 2024-01-12 | On-time | 2024-04-12 | 91 | 2024-04-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46011672 | T2 EI DRUM-GRAS VALY-WMR 15/342 RPR POLE | ICW
LC | 125897944 | 076/311 | T2 EI ROND MTN-TBL MTN #2 76/311 BNT STL | TABLEMTN | ETL.6070.TOWR | 2023-04-13 | 2023-04-13 | 2023-11-17 | On-time | 2024-04-12 | 147 | 2024-04-13 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46009051 | T2 EI ROND MTN-TBL MTN #2 76/311 BNT STL | ICQ
LC | 125959700 | 026/007 | T2 EI GRBRVILE-LYTNVLL 26/7 RPR GYWW | WILLITS | ETL.8365.POLE.NWOD | 2023-04-20 | 2023-04-20 |  | Late | 2024-04-19 |  | 2023-07-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46236304 | T2 EI GRBRVILE-LYTNVLL 26/7 RPR GYWW | ICW
LC | 125959981 | 021/002 | T2 EI BRIDGEVILL-GARBERVLL 21/2 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2023-04-20 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504909 | T2 EI BRIDGEVILL-GARBERVLL 21/2 RPL POLE | 70Y
LC | 125960019 | 010/011 | T2 DI LWR LK HMSTK HMSTK 10/011 RPL STRW | WILLITS | ETL.1481.POLE.WOOD | 2023-04-20 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35488186 | T2 DI LWR LK HMSTK 10/011 RPL STRW | 70Y
LC | 125960449 | 064/003 | T2 ELK-GUALALA 64/003 GO95 CLEARANCE | WILLITS | ETL.8410.POLE.WOOD | 2023-04-20 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35521129 | T2 ELK-GUALALA 64/002 GO95 CLEARANCE | 93G
LC | 125900686 | 015/131 | T2 CRAG VIEW-CASCADE 015/131 RPR CNDW | TABLEMTN | ETL.1350.INSL.CERA | 2023-04-13 | 2023-04-13 | 2024-02-28 | On-time | 2024-04-12 | 44 | 2024-04-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46011641 | T2 CRAG VIEW-CASCADE 015/131 RPR CNDW | ICW
LC | 125960659 | 020/014 | T2 EI BRIDGEVLL-GARBERVLL 20/14 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2023-04-20 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504907 | T2 EI BRIDGEVLL-GARBERVLL 20/14 RPL POLE | 70Y
LC | 125960761 | 026/006 | T2 EI GRBRVLLE-LYTNVLLE 26/6 RPL STRW | WILLITS | ETL.8365.POLE.WOOD | 2023-04-20 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35488086 | T2 EI GARBERVLLE-LAYTONVLL 26/6 RPL POLE | 70Y
LC | 125960959 | 042/274A | T2 DI TRINITY-CTTNWD 042/274A RPR JUMW | TABLEMTN | ETL.4040.INSL.NCER | 2023-04-20 | 2023-04-14 |  | Late | 2024-04-13 |  | 2023-07-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46194289 | T2 DI TRINITY-CTTNWD 042/274A RPR JUMW | ICW
LC | 125901958 | 015/193 | T2 EI KESWICK-TRINITY 015/193 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-13 | 2023-04-13 | 2023-12-11 | On-time | 2024-04-12 | 123 | 2024-04-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011685 | T2 EI KESWICK-TRINITY 015/193 RPR GYWW | ICW
LC | 125961273 | 034/005 | T2 EI MMDCNO-WLTS-FRT BRG 34/05 RPL INSW | WILLITS | ETL.7550.INSL.NCER | 2023-04-20 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35521522 | T2 WV MNDCNO-WLTS-FRT BRG 14/13 RPL INSW | 93I
LC | 125961312 | 029/005 | T2 DI PHILO JCT-ELK 029/005 RPL ANCW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-20 | 2023-04-13 | 2024-06-10 | Late | 2024-04-12 | -59 | 2024-04-13 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35495649 | T2 DI PHILO JCT-ELK 029/005 RPL ANCW | 93E
LC | 125902158 | 031/183 | T2 EI TMBLR-SN LS BSP 031/183 RPR CNDS | PISMOBCH | ETL.3960.INSL.NCER | 2023-04-13 | 2023-04-13 | 2024-04-02 | On-time | 2024-04-12 | 10 | 2024-04-13 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46088479 | T2 EI TMBLR-SN LS BSP 031/183 RPR CNDS | ICS
LC | 125903052 | 000/012 | T2 EI COLGATE-GRASS VLLY 0/012 RPL STRW | SACTO | ETL.6490.POLE.WOOD | 2023-04-13 | 2023-04-13 | 2024-03-20 | On-time | 2024-04-12 | 23 | 2024-04-13 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495582 | T2 EI COLGATE-GRASS VLLY 0/012 RPL STRW | 70Y
LC | 125962179 | 028/421 | T2 EI CLAY-MARTEL 28/421 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2023-04-20 | 2023-04-20 | 2024-06-05 | Late | 2024-04-19 | -47 | 2024-04-20 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31653149 | T2 EI CLAY-MARTEL 27/399 RPL POLE | 70Y
LC | 125962305 | 011/007 | T2 DI MNDCN PHL JCT HPLND 11/07 RPL POLE | WILLITS | ETL.7520.POLE.WOOD | 2023-04-20 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495641 | T2 DI MNDCN PHL JCT HPLND 11/07 RPL POLE | 70Y
LC | 125903363 | 002/003 | T2 EI CHWCHILLA-KERCKHOFF 2/3 RPR STRW | FRESNO | ETL.1250.POLE.WOOD | 2023-04-13 | 2023-04-13 | 2023-11-08 | On-time | 2024-04-12 | 156 | 2024-04-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46024065 | T2 EI CHWCHILLA-KERCKHOFF 2/3 RPR STRW | ICW
LC | 125963106 | 010/007 | T2 DI LWR LAKE HMSTK 10/07 RPR INSW | WILLITS | ETL.1481.INSL.CERA | 2023-04-20 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46219478 | T2 DI LWR LAKE HMSTK 10/07 RPR INSW | ICW
LC | 125926903 | 010/126 | T2 DI KESWICK-TRINITY 010/126 RPR GYWW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-15 | 2023-04-13 | 2024-03-25 | On-time | 2024-04-12 | 18 | 2024-04-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011689 | T2 DI KESWICK-TRINITY 010/126 RPR GYWW | ICW
LC | 125926941 | 006/087 | T2 DI KESWICK-TRINITY 006/087 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-15 | 2023-04-13 | 2024-02-15 | On-time | 2024-04-12 | 57 | 2024-04-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011697 | T2 DI KESWICK-TRINITY 006/087 RPR GYWW | ICW
LC | 125927140 | 010/130 | T2 DI KESWICK-TRINITY 010/130 COTTER | TABLEMTN | ETL.7270.INSL.CERA | 2023-04-15 | 2023-04-13 | 2024-03-06 | On-time | 2024-04-12 | 37 | 2024-04-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011687 | T2 DI KESWICK-TRINITY 010/130 COTTER | ICW
LC | 125927278 | 007/103 | T2 DI KSWCK-TRNITY 7/103 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-15 | 2023-04-13 | 2024-03-04 | On-time | 2024-04-12 | 39 | 2024-04-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011693 | T2 DI KSWCK-TRNITY 7/103 RPR GYWW | ICW
LC | 125927322 | 007/103 | T2 DI KSWCK-TRNITY 7/103 RPR ANCW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-15 | 2023-04-13 | 2024-04-01 | On-time | 2024-04-12 | 11 | 2024-04-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46011692 | T2 DI KSWCK-TRNITY 7/103 RPR ANCW | ICW
LC | 125927873 | 007/097 | T2 DI KESWICK-TRINITY 007/097 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-15 | 2023-04-13 | 2024-02-22 | On-time | 2024-04-12 | 50 | 2024-04-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011695 | T2 DI KESWICK-TRINITY 007/097 RPR GYWW | ICW
LC | 125928952 | 006/088A | T2 DI KESWICK-TRINITY 006/088A RPR JMPW | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-15 | 2023-04-13 | 2024-03-26 | On-time | 2024-04-12 | 17 | 2024-04-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46011696 | T2 DI KESWICK-TRINITY 006/088A RPR JMPW | ICW
LC | 125963542 | 005/023 | T2 DI PITTSBURG-SN RAMON 5/23 RPR INS | CONCORD | ETL.5470.INSL | 2023-04-20 | 2023-04-17 | 2024-05-15 | Late | 2024-04-16 | -29 | 2024-04-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45997108 | T2 DI PITTSBURG-SN RAMON 5/23 RPR INS | ICS
LC | 125963655 | 003/008 | T2 DI MNDCNO-PHLO JCT-HPLND 3/8 INS GYWW | WILLITS | ETL.7520.POLE.NWOD | 2023-04-20 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Missing | Guy Wire-Wood | Install | 45828951 | T2 DI MNDCNO-PHLO JCT-HPLND 3/8 RPR STRT | ICW
LC | 125963719 | A006/075 | T2 DI PALRMO-OROVLE #2 A06/75 RPL POLE | TABLEMTN | ETL.7740.POLE.WOOD | 2023-04-20 | 2023-04-07 |  | Late | 2024-04-06 |  | 2024-04-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35493843 | T2 DI PALRMO-OROVLE #2 A06/75 RPL POLE | 70Y
LC | 125963744 | 008/154 | T2 DI KESWICK-CASCADE 008/154 RPR INSW | TABLEMTN | ETL.7260.INSL.CERA | 2023-04-20 | 2023-04-10 | 2024-06-17 | Late | 2024-04-09 | -69 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011764 | T2 DI KESWICK-CASCADE 008/154 RPR INSW | ICW
LC | 125947355 | 010/125 | T2 DI KESWICK-TRINITY 010/125 COTTER | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-18 | 2023-04-13 | 2024-02-12 | On-time | 2024-04-12 | 60 | 2024-04-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011690 | T2 DI KESWICK-TRINITY 010/125 COTTER | ICW
LC | 125954352 | 007/102 | T2 DI KESWICK-TRINITY 7/102 RPL CONN | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-19 | 2023-04-13 | 2024-03-25 | On-time | 2024-04-12 | 18 | 2024-04-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46011694 | T2 DI KESWICK-TRINITY 7/102 RPL CONN | ICW
LC | 125955767 | 010/123 | T2 DI KESWICK-TRINITY 10/123 RPR JMPW | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-19 | 2023-04-13 | 2023-05-24 | On-time | 2024-04-12 | 324 | 2023-07-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45749603 | T2 DI KESWICK-TRINITY 10/123 RPR JMPW | ICW
LC | 125983808 | 011/147 | T2 DI KSWCK-TRNITY 11/147 REFRAME | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-24 | 2023-04-13 | 2024-03-25 | On-time | 2024-04-12 | 18 | 2024-04-13 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35509871 | T2 DI KSWCK-TRNITY 11/147 REFRAME | 93E
LC | 125965391 | 009/113 | T2 DI COLGATE-SMRTVL #2 09/113 RPR STRW | SACTO | ETL.6520.POLE.WOOD | 2023-04-21 | 2023-04-07 | 2024-05-02 | Late | 2024-04-06 | -26 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46001402 | T2 DI COLGATE-SMRTVL #2 09/113 RPR STRW | ICW
LC | 125983931 | 010/129 | T2 DI KSWCK TRNITY 10/129 INS HRDD | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-24 | 2023-04-13 | 2024-03-06 | On-time | 2024-04-12 | 37 | 2024-04-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 46011688 | T2 DI KSWCK TRNITY 10/129 INS HRDD | ICW
LC | 125984012 | 006/085A | T2 DI KSWCK TRNITY 06/085A RPL ANCW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-24 | 2023-04-13 | 2024-03-26 | On-time | 2024-04-12 | 17 | 2024-04-13 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35495644 | T2 DI KSWCK TRNITY 06/085A RPL ANCW | 93E
LC | 125965489 | 013/011 | T2 EI MNDCN-WLTS-FRT BRG 13/011 RPR CNDW | WILLITS | ETL.7550.INSL.NCER | 2023-04-21 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46214048 | T2 EI MNDCN-WLTS-FRT BRG 13/011 RPR CNDW | ICW
LC | 125984498 | 006/082 | T2 DI KESWICK-TRINITY 6/082 RPL INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-24 | 2023-04-13 | 2024-03-27 | On-time | 2024-04-12 | 16 | 2024-04-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35495643 | T2 DI KESWICK-TRINITY 6/082 RPL INSW | 93I
LC | 125965551 | 003/065 | T2 DI SMTVIL-CMP FR W 3/65 RPL POLE | SACTO | ETL.7970.POLE.WOOD | 2023-04-21 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35529598 | T2 DI SMTVIL-CMP FR W 3/65 RPL POLE | 70Y
LC | 125984859 | 011/138 | T2 DI KSWCK TRNITY 11/138 RPR INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-25 | 2023-04-13 | 2024-03-24 | On-time | 2024-04-12 | 19 | 2024-04-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011686 | T2 DI KSWCK TRNITY 11/138 RPR INSW | ICW
LC | 125984924 | 008/113 | T2 DI KSWCK TRNITY 08/113 RPR HRDW | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-25 | 2023-04-13 | 2024-03-24 | On-time | 2024-04-12 | 19 | 2024-04-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011691 | T2 DI KSWCK TRNITY 08/113 RPR HRDW | ICW
LC | 125965628 | 006/118 | T2 DI SMRTVL CMP FR WST 06/118 RPL POLE | SACTO | ETL.7970.POLE.WOOD | 2023-04-21 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 372T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481544 | T2 DI SMRTVL CMP FR WST 06/118 RPL POLE | 70Y
LC | 125965694 | 002/043 | T2 DI SMRTVLL-MRYSVLL 2/043 RPL POLE | SACTO | ETL.7980.POLE.WOOD | 2023-04-21 | 2023-04-10 | 2024-05-08 | Late | 2024-04-09 | -29 | 2024-04-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495693 | T2 DI SMRTVLL-MRYSVLL 1/037 RPL POLE | 70Y
LC | 126008454 | 020/013 | T2 DI BRGVILL-GRBRV 20/13 RPR STRW | EUREKA | ETL.6220.POLE.NWOD | 2023-04-27 | 2023-04-13 | 2024-01-24 | On-time | 2024-04-12 | 79 | 2024-04-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46070824 | T2 DI BRGVILL-GRBRV 20/13 RPR STRW | ICW
LC | 125965921 | 028/424 | T2 EI CLAY-MARTEL 028/424 COMPLETED | VICTOR | ETL.8250.POLE.WOOD | 2023-04-21 | 2023-04-21 | 2024-06-05 | Late | 2024-04-20 | -46 | 2024-04-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46025798 | T2 EI CLAY-MARTEL 028/424 RPR STRW | ICW
LC | 125966104 | 001/037 | T2 DI SMRTVLL-MRYSVLL 1/037 RPL POLE | SACTO | ETL.7980.POLE.WOOD | 2023-04-21 | 2023-04-10 | 2024-05-14 | Late | 2024-04-09 | -35 | 2024-04-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495693 | T2 DI SMRTVLL-MRYSVLL 1/037 RPL POLE | 70Y
LC | 125908120 | 004/052 | T2 SNEATH LANE-PACIFICA 04/52 RPR GYWW | METCALF | ETL.7575.POLE.WOOD | 2023-04-14 | 2023-04-14 | 2024-04-06 | On-time | 2024-04-13 | 7 | 2023-10-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46013035 | T2 SNEATH LANE-PACIFICA 04/52 RPR GYWW | ICW
LC | 125966328 | 013/009 | T2 EI MNDCN-WLTS-FRT BRG 013/09 RPR GRWW | WILLITS | ETL.7550.POLE.WOOD | 2023-04-21 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 46213894 | T2 EI MNDCN-WLTS-FRT BRG 013/09 RPR GRWW | ICW
LC | 125909450 | 007/159 | T2 EI SALINAS-LAURELES -_007/159 RPR INS | MOSSLNDG | ETL.7930.INSL | 2023-04-14 | 2023-04-14 | 2024-03-23 | On-time | 2024-04-13 | 21 | 2024-04-14 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46049292 | T2 EI SALINAS-LAURELES -_007/159 RPR INS | ICW
LC | 125966504 | 006/134 | T2 DI KESWICK-CASCADE 6/134 REGRADE | TABLEMTN | ETL.7260.POLE.NWOD | 2023-04-21 | 2023-04-10 | 2024-06-17 | Late | 2024-04-09 | -69 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Regrade | 46011766 | T2 DI KESWICK-CASCADE 6/134 REGRADE | ICW
LC | 125910977 | 011/097 | T2 EI CRAG VIEW-CASCADE 011/097 RMV NEST | TABLEMTN | ETL.1350.TOWR | 2023-04-14 | 2023-04-14 | 2023-12-05 | On-time | 2024-04-13 | 130 | 2024-04-14 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46011655 | T2 EI CRAG VIEW-CASCADE 011/097 RMV NEST | ICS
LC | 125910992 | 011/097 | T2 EI CRAG VIEW-CASCADE 011/097 INS DMPS | TABLEMTN | ETL.1350.INSL | 2023-04-14 | 2023-04-14 | 2023-12-05 | On-time | 2024-04-13 | 130 | 2024-04-14 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 46011654 | T2 EI CRAG VIEW-CASCADE 011/097 INS DMPS | ICS
LC | 125911624 | 075/306 | T2 EI ROND MTN-TBL MTN #2 75/306 BNT STL | TABLEMTN | ETL.6070.TOWR | 2023-04-14 | 2023-04-14 | 2024-02-12 | On-time | 2024-04-13 | 61 | 2024-04-14 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46028567 | T2 EI ROND MTN-TBL MTN #2 75/306 BNT STL | ICQ
LC | 125966758 | 002/050 | T2 DI SMRTVIL-CMP FRWST 2/50 RPL POLE | SACTO | ETL.7970.POLE.WOOD | 2023-04-21 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481543 | T2 DI SMRTVIL-CMP FRWST-02/50 RPL POLE | 70Y
LC | 125914224 | 009/078 | T2 EI CRG-VIEW-CSCD 009/078R RPL POLE | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-14 | 2023-04-14 | 2024-02-26 | On-time | 2024-04-13 | 47 | 2024-04-14 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 125966958 | 021/005 | T2 DI PHILO JCT-ELK 21/5 RPR GYWW | WILLITS | ETL.7780.POLE.NWOD | 2023-04-21 | 2023-04-10 | 2024-05-30 | Late | 2024-04-09 | -51 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213873 | T2 DI PHILO JCT-ELK 21/5 RPR GYWW | ICW
LC | 125967025 | 007/080 | T2 DI COLGATE-SMARTVIL #2 07/80 RPR STRW | SACTO | ETL.6520.POLE.WOOD | 2023-04-21 | 2023-04-07 | 2024-05-01 | Late | 2024-04-06 | -25 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46001403 | T2 DI COLGATE-SMARTVIL #2 07/80 RPR STRW | ICW
LC | 125915415 | 075/310 | T2 EI ROND MTN-TBL MTN #2 75/310 BNT STL | TABLEMTN | ETL.6070.TOWR | 2023-04-14 | 2023-04-14 | 2023-11-21 | On-time | 2024-04-13 | 144 | 2024-04-14 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46028568 | T2 EI ROND MTN-TBL MTN #2 75/310 BNT STL | ICQ
LC | 125967089 | 005/061 | T2 DI COLGATE-SMRVL#1 5/61 RPL POLE | SACTO | ETL.6510.POLE.WOOD | 2023-04-21 | 2023-04-10 | 2024-05-08 | Late | 2024-04-09 | -29 | 2024-04-10 | 372T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481567 | T2 DI COLGATE-SMRVL#1 5/61 RPL POLE | 70Y
LC | 125967238 | 004/020 | T2 DI PITTSBRG SN RMN 04/020 COTTER | CONCORD | ETL.5470.INSL | 2023-04-21 | 2023-04-17 | 2024-06-02 | Late | 2024-04-16 | -47 | 2024-04-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45997110 | T2 DI PITTSBRG SN RMN 04/020 COTTER | ICS
LC | 125916257 | 009/076 | T2 EI CRG VW-CSCD 09/076 INS DMPW | TABLEMTN | ETL.1350.INSL.NCER | 2023-04-14 | 2023-04-14 | 2024-02-27 | On-time | 2024-04-13 | 46 | 2024-04-14 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46011638 | T2 EI CRG VW-CSCD 09/076 INS DMPW | ICW
LC | 125917755 | 025/410 | T2 EI KESWICK-TRINITY 025/410 RPR POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-14 | 2023-04-14 | 2023-07-21 | On-time | 2024-04-13 | 267 | 2023-10-14 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45749936 | T2 EI KESWICK-TRINITY-_025/410 RPR POLE | ICW
LC | 125919601 | 005/006 | T2 EI FORT BRAGG-ELK 05/06 RPR INSW | WILLITS | ETL.2060.INSL.CERA | 2023-04-14 | 2023-04-14 | 2024-02-22 | On-time | 2024-04-13 | 51 | 2024-04-14 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46089956 | T2 EI FORT BRAGG-ELK 05/06 RPR INSW | ICW
LC | 125922628 | 008/073 | T2 EI CRAG VIEW-CASCDE 008/073R RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-14 | 2023-04-14 | 2023-11-28 | On-time | 2024-04-13 | 137 | 2024-04-14 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011639 | T2 EI CRAG VIEW-CASCDE 008/073R RPR GYWW | ICW
LC | 125922919 | 030/221 | T2 EI DRUM-RIO OSO #2 030/221 RPL INSS | SACTO | ETL.1430.INSL.CERA | 2023-04-14 | 2023-04-14 | 2023-11-04 | On-time | 2024-04-13 | 161 | 2024-04-14 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31673014 | T2 EI DRUM-RIO OSO #2 RPL INSS 2 TWRS | 93K
LC | 125967890 | 003/063 | T2NT DI SMRTVIL-CMP FRWST-03/63 RMV BUTT | SACTO | ETL.7970.POLE.WOOD | 2023-04-21 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 46011679 | T2NT DI SMRTVIL-CMP FRWST-03/63 RMV BUTT | ICW
LC | 125968071 | 009/112 | T2 DI COLGAT-SMARTVIL #2 09/112 RPR STRW | SACTO | ETL.6520.POLE.WOOD | 2023-04-21 | 2023-04-07 | 2024-05-02 | Late | 2024-04-06 | -26 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46001405 | T2 DI COLGAT-SMARTVIL #2 09/112 RPR STRW | ICW
LC | 125968079 | 007/085 | T2 DI COLGAT-SMARTVIL #2 07/85 RPR STRW | SACTO | ETL.6520.POLE.WOOD | 2023-04-21 | 2023-04-07 | 2024-05-01 | Late | 2024-04-06 | -25 | 2024-04-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46001407 | T2 DI COLGAT-SMARTVIL #2 07/85 RPR STRW | ICW
LC | 125923102 | 030/218 | T2 EI DRUM-RIO OSO #2 030/218 RPL INSS | SACTO | ETL.1430.INSL | 2023-04-14 | 2023-04-14 | 2023-11-04 | On-time | 2024-04-13 | 161 | 2024-04-14 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31673014 | T2 EI DRUM-RIO OSO #2 RPL INSS 2 TWRS | 93K
LC | 125924186 | 048/423 | T2 EI RND MTN-CTNWD #3 48/423 RPR INSS | TABLEMTN | ETL.5650.INSL | 2023-04-14 | 2023-04-14 | 2024-03-08 | On-time | 2024-04-13 | 36 | 2024-04-14 | 628 | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46011623 | T2 EI RND MTN-CTNWD #3 48/423 RPR INSS | ICS
LC | 125926995 | 027/194 | T2 DI TRNTY CTTNWD 27/194 RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-15 | 2023-04-14 | 2023-06-26 | On-time | 2024-04-13 | 292 | 2024-04-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46122551 | T2 DI TRNTY CTTNWD 27/194 RPR GYWW | ICW
LC | 125927033 | 027/194 | T2 DI TRNTY CTTNWD 27/194 COTTER | TABLEMTN | ETL.4040.INSL.CERA | 2023-04-15 | 2023-04-14 | 2023-06-26 | On-time | 2024-04-13 | 292 | 2023-07-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45749646 | T2 DI TRNTY CTTNWD 27/194 COTTER | ICW
LC | 125968525 | 005/008 | T2 WV TRINITY-MAPLE CREEK 5/8 INS DAMW | EUREKA | ETL.8170.INSL.NCER | 2023-04-21 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 46070694 | T2 WV TRINITY-MAPLE CREEK 5/8 INS DAMW | ICW
LC | 125968653 | 006/124 | T2 DI SMTVIL-CMP FW 6/124 REFRAME | SACTO | ETL.7970.POLE.WOOD | 2023-04-21 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 637 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31652380 | T2 DI SMTVIL-CMP FW 6/124 REFRAME | 93E
LC | 125946021 | 002/032 | T2 DI WEIMAR#1 002/032 COTTER | SACTO | ETL.7560.INSL.NCER | 2023-04-18 | 2023-04-14 | 2023-11-05 | On-time | 2024-04-13 | 160 | 2024-04-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011677 | T2 DI WEIMAR#1 002/032 COTTER | ICW
LC | 125955826 | 028/199 | T2 DI TRINITY-CTTNWD 28/199L RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-19 | 2023-04-14 | 2024-03-04 | On-time | 2024-04-13 | 40 | 2024-04-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011636 | T2 DI TRINITY-CTTNWD 28/199L RPR GYWW | ICW
LC | 125968829 | 008/142 | T2 DI SMARTVILLE-MARYSVIL 8/142 RPL POLE | SACTO | ETL.7980.POLE.WOOD | 2023-04-21 | 2023-04-10 | 2024-05-14 | Late | 2024-04-09 | -35 | 2024-04-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495694 | T2 DI SMARTVILLE-MARYSVIL 8/142 RPL POLE | 70Y
LC | 125968995 | 012/121C | T2 DI PIT#5-RND MTN#1 12/121C RPR GYWW | TABLEMTN | ETL.5420.POLE.NWOD | 2023-04-21 | 2023-04-10 | 2024-06-01 | Late | 2024-04-09 | -53 | 2023-10-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011625 | T2 DI PIT#5-RND MTN#1 12/121C RPR GYWW | ICW
LC | 125969339 | 003/026A | T2 DI PIT #7 TAP 3/26A RMV VEG | TABLEMTN | ETL.5442.POLE.NWOD | 2023-04-21 | 2023-04-10 | 2024-04-10 | Late | 2024-04-09 | -1 | 2024-04-10 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Trim
LC | 125985132 | 008/073 | T2 EI CRAG VIEW-CASCDE 008/073L RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-25 | 2023-04-14 | 2023-11-28 | On-time | 2024-04-13 | 137 | 2024-04-14 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011640 | T2 EI CRAG VIEW-CASCDE 008/073L RPR GYWW | ICW
LC | 125991823 | 017/144 | T2 DI CRG VIEW-CASCADE 17/144 RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-25 | 2023-04-14 | 2024-02-27 | On-time | 2024-04-13 | 46 | 2024-04-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 125992289 | 016/137 | T2 DI CRG VIEW-CASCADE 016/137R RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-25 | 2023-04-14 | 2024-02-26 | On-time | 2024-04-13 | 47 | 2024-04-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 125996262 | 017/144 | T2 DI CRG VIEW-CASCADE 17/144R RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-26 | 2023-04-14 | 2024-02-27 | On-time | 2024-04-13 | 46 | 2024-04-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 126006127 | 016/137 | T2 DI CRG VIEW-CASCADE 016/137L RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-27 | 2023-04-14 | 2024-02-26 | On-time | 2024-04-13 | 47 | 2024-04-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 126011577 | 004/036 | T2 DI CRAG VIEW-CASCADE 04/36 RPR OPGW | TABLEMTN | ETL.1350.TOWR | 2023-04-28 | 2023-04-14 | 2023-11-28 | On-time | 2024-04-13 | 137 | 2024-04-14 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46027000 | T2 DI CRAG VIEW-CASCADE 04/36 RPR OPGW | ICS
LC | 125927538 | 023/001 | T2 EI FLTN-HPLND 23/1 RPR GYWW | LAKEVLLE | ETL.6890.POLE.NWOD | 2023-04-15 | 2023-04-15 | 2023-11-09 | On-time | 2024-04-14 | 157 | 2024-04-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46045927 | T2 EI FLTN-HPLND 23/1 RPR GYWW | ICW
LC | 125970242 | 029/439 | T2 EI CLAY-MARTEL+ 029/439 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2023-04-21 | 2023-04-21 | 2024-06-06 | Late | 2024-04-20 | -47 | 2024-04-21 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31653149 | T2 EI CLAY-MARTEL 27/399 RPL POLE | 70Y
LC | 125970341 | 029/440 | T2 EI CLAY-MARTEL 29/440 COMPLETED | VICTOR | ETL.8250.POLE.WOOD | 2023-04-21 | 2023-04-21 | 2024-06-06 | Late | 2024-04-20 | -47 | 2024-04-21 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31653149 | T2 EI CLAY-MARTEL 27/399 RPL POLE | 70Y
LC | 125970584 | 001/023 | T2 DI DELTA-MTN GATE JCT 01/23 RPL TIED | TABLEMTN | ETL.6750.INSL | 2023-04-21 | 2023-04-10 |  | Late | 2024-04-09 |  | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46011769 | T2 DI DELTA-MTN GATE JCT 01/23 RPL TIED | ICW
LC | 125970682 | 013/111 | T2 DI PIT#6 JCT-RND MTN 13/111R RPL POLE | TABLEMTN | ETL.5440.POLE.WDPS | 2023-04-21 | 2023-04-10 | 2024-06-23 | Late | 2024-04-09 | -75 | 2024-04-10 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35529573 | T2 DI PIT #6 JCT-RND MTN RPL 3 POLE | 70Y
LC | 125970686 | 013/111 | T2 DI PIT#6 JCT-RND MTN 13/111L RPL POLE | TABLEMTN | ETL.5440.POLE.WDPS | 2023-04-21 | 2023-04-10 | 2024-06-23 | Late | 2024-04-09 | -75 | 2024-04-10 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35529573 | T2 DI PIT #6 JCT-RND MTN RPL 3 POLE | 70Y
LC | 125928041 | 009/083 | T2 DELTA-COTONWOOD 9/83 RPR SPLW | TABLEMTN | ETL.1350.INSL.NCER | 2023-04-15 | 2023-04-15 | 2024-02-27 | On-time | 2024-04-14 | 47 | 2024-04-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46011821 | T2 DELTA-COTONWOOD 9/83 RPR SPLW | ICW
LC | 125971054 | 000/005 | T2 DI COLGATE-SMARTVIL#1 00/05 RMV VEG | SACTO | ETL.6510.POLE.NWOD | 2023-04-21 | 2023-04-10 |  | Late | 2024-04-09 |  | 2024-04-10 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 125928286 | 020/279 | T2 EI CLAY-MARTEL 020/279 RPR INSW | VICTOR | ETL.8250.INSL.NCER | 2023-04-15 | 2023-04-15 | 2024-04-10 | On-time | 2024-04-14 | 4 | 2024-04-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46212826 | T2 EI CLAY-MARTEL 020/279 RPR INSW | ICW
LC | 125928467 | 016/202 | T2 EI KESWICK-TRINITY 16/202 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-15 | 2023-04-15 | 2023-06-27 | On-time | 2024-04-14 | 292 | 2023-07-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45770753 | T2 EI KESWICK-TRINITY 16/202 RPR GYWW | ICW
LC | 125928818 | 030/000 | T2 EI MMDCNO-WLTS-FRT BRG 30/00 RPR ANCW | WILLITS | ETL.7550.POLE.WOOD | 2023-04-15 | 2023-04-15 | 2024-03-05 | On-time | 2024-04-14 | 40 | 2024-04-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46210436 | T2 EI MMDCNO-WLTS-FRT BRG 30/00 RPR ANCW | ICW
LC | 125928819 | 029/006 | T2 EI MENDOCNO-WILTS-FRT BRG 29/6 UNBURY | WILLITS | ETL.7550.POLE.WOOD | 2023-04-15 | 2023-04-15 | 2023-05-03 | On-time | 2024-04-14 | 347 | 2024-04-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45739753 | T2 EI MENDOCNO-WILTS-FRT BRG 29/6 UNBURY | ICW
LC | 125928878 | 014/331 | T2 EI DRM-GRS VLY-WMR 14/331 COTTER | SACTO | ETL.6760.INSL.NCER | 2023-04-15 | 2023-04-15 | 2024-01-11 | On-time | 2024-04-14 | 94 | 2024-04-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46011675 | T2 EI DRM-GRS VLY-WMR 14/331 COTTER | ICW
LC | 125929230 | 020/283 | T2 EI CLAY-MARTEL 020/283 RPR INSW | VICTOR | ETL.8250.INSL.NCER | 2023-04-15 | 2023-04-15 | 2023-10-23 | On-time | 2024-04-14 | 174 | 2024-04-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46016358 | T2 EI CLAY-MARTEL 020/283 RPR INSW | ICW
LC | 125971281 | 007/065 | T2 DI CABRILLO-SNTA YNZ SS 7/65 RPR STRW | PISMOBCH | ETL.1200.POLE.NWOD | 2023-04-21 | 2023-04-10 |  | Late | 2024-04-09 |  | 2024-04-10 | 630 | TLO |  | E - Schd Compl Yr 0 | Open | TR2 | Missing | Structure – Cathodic Protection | Install | 45864445 | T2 DI CABRILLO-SNTA YNZ SS 7/65 RPR STRW | ICW
LC | 125929274 | 025/200 | T2 EI MIDDLE FRK-GLD HLL 025/200 RPR GYW | SACTO | ETL.5140.POLE.STPS | 2023-04-15 | 2023-04-15 | 2024-02-14 | On-time | 2024-04-14 | 60 | 2024-04-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011676 | T2 EI MIDDLE FRK-GLD HLL 025/200 RPR GYW | ICW
LC | 125929309 | 009/079 | T2 EI CRAG VIEW-CASCADE 009/079 RPR POLE | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-15 | 2023-04-15 | 2024-01-24 | On-time | 2024-04-14 | 81 | 2024-04-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46011634 | T2 EI CRAG VIEW-CASCADE 009/079 RPR POLE | ICW
LC | 125932366 | 021/299 | T2 EI CLAY-MARTEL 021/299 RPR POLE | VICTOR | ETL.8250.POLE.WOOD | 2023-04-17 | 2023-04-17 | 2024-01-17 | On-time | 2024-04-16 | 90 | 2024-04-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46017002 | T2 EI CLAY-MARTEL 021/299 RPR POLE | ICW
LC | 125971431 | 013/000A | T2 DI LYTNVIL WILTS 13/000A RPR SPLW | WILLITS | ETL.8360.INSL.NCER | 2023-04-21 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46222490 | T2 DI LYTNVIL WILTS 13/000A RPR SPLW | ICW
LC | 125932617 | 025/183 | T2 EI TRNITY-COTTNWD 25/183R RPR XBRACE | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-17 | 2023-04-17 | 2023-07-31 | On-time | 2024-04-16 | 260 | 2023-10-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45749649 | T2 EI TRNITY-COTTNWD 25/183R RPR XBRACE | ICW
LC | 125934537 | 020/289 | T2 EI CLAY-MARTEL 020/289 RPR POLE | VICTOR | ETL.8250.POLE.WOOD | 2023-04-17 | 2023-04-17 | 2023-10-23 | On-time | 2024-04-16 | 176 | 2024-04-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46016359 | T2 EI CLAY-MARTEL 020/289 RPR POLE | ICW
LC | 125934948 | 009/069 | T2 EI GREEN VLY-LAGAS 009/069L RPL ANCW | MOSSLNDG | ETL.1720.POLE.WDPS | 2023-04-17 | 2023-04-17 | 2024-02-16 | On-time | 2024-04-16 | 60 | 2024-04-17 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35508485 | T2 EI GREEN VLY-LAGAS 009/069L RPL ANCW | 93E
LC | 125935251 | 009/069 | T2 EI GREEN VLY-LAGAS 009/069C RPL ANCW | MOSSLNDG | ETL.1720.POLE.WDPS | 2023-04-17 | 2023-04-17 | 2024-02-16 | On-time | 2024-04-16 | 60 | 2024-04-17 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35508485 | T2 EI GREEN VLY-LAGAS 009/069L RPL ANCW | 93E
LC | 125971808 | 008/143 | T2 DI SMARTVL-MARYSVL 8/143 RPL POLE | SACTO | ETL.7980.POLE.WOOD | 2023-04-21 | 2023-04-10 | 2024-05-14 | Late | 2024-04-09 | -35 | 2024-04-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495694 | T2 DI SMARTVILLE-MARYSVIL 8/142 RPL POLE | 70Y
LC | 125971815 | 002/067 | T2 DI DLTA-MTN GT JCT 2/067 RPL STRW | TABLEMTN | ETL.6750.POLE.WOOD | 2023-04-21 | 2023-04-10 |  | Late | 2024-04-09 |  | 2024-04-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495124 | T2 DI DLTA-MTN GT JCT 2/067 RPL STRW | 70Y
LC | 125935276 | 052/224 | T2 EI RND MTN-TBL MTN #2 52/224 BNT STEL | TABLEMTN | ETL.6070.TOWR | 2023-04-17 | 2023-04-17 | 2023-11-09 | On-time | 2024-04-16 | 159 | 2024-04-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46028562 | T2 EI RND MTN-TBL MTN #2 52/224 BNT STEL | ICQ
LC | 125935343 | 108/002 | T2 EI HMBLDT-BRIDGVILE 108/002R RPR GYWW | EUREKA | ETL.1810.POLE.WDPS | 2023-04-17 | 2023-04-17 | 2023-10-04 | On-time | 2024-04-16 | 195 | 2023-10-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45752864 | T2 EI HMBLDT-BRIDGVILE 108/002R RPR GYWW | ICW
LC | 125935387 | 108/002 | T2 EI HUMBLDT-BRDVILE 108/002C RPR GYWW | EUREKA | ETL.1810.POLE.WDPS | 2023-04-17 | 2023-04-17 | 2023-10-04 | On-time | 2024-04-16 | 195 | 2023-10-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45752864 | T2 EI HMBLDT-BRIDGVILE 108/002R RPR GYWW | ICW
LC | 125935421 | 009/069 | T2 EI GREEN VLY-LAGAS 009/069R RPL ANCW | MOSSLNDG | ETL.1720.POLE.WDPS | 2023-04-17 | 2023-04-17 | 2024-02-16 | On-time | 2024-04-16 | 60 | 2024-04-17 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35508485 | T2 EI GREEN VLY-LAGAS 009/069L RPL ANCW | 93E
LC | 125971978 | 339 | T2 DI PIT#7 TAP 3/29A RPR SWITCH | TABLEMTN | ETL.5442.SWIT | 2023-04-21 | 2023-04-10 | 2024-06-20 | Late | 2024-04-09 | -72 | 2024-04-10 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 46011629 | T2 DI PIT#7 TAP 3/29A RPR SWITCH | ICE
LC | 125935626 | 108/002 | T2 EI HUMBLDT-BRDVILE 108/002L RPR GYWW | EUREKA | ETL.1810.POLE.WDPS | 2023-04-17 | 2023-04-17 | 2023-10-04 | On-time | 2024-04-16 | 195 | 2023-10-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45752864 | T2 EI HMBLDT-BRIDGVILE 108/002R RPR GYWW | ICW
LC | 125936482 | 000/004 | T2 EI CLGT-GRS VLY 0/4 RPR STRW | SACTO | ETL.6490.POLE.WOOD | 2023-04-17 | 2023-04-17 | 2024-03-07 | On-time | 2024-04-16 | 40 | 2024-04-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46030910 | T2 EI CLGT-GRS VLY 0/4 RPR STRW | ICW
LC | 125936487 | 016/211 | T2 EI KESWICK-TRINITY 16/211 RPL STRW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-17 | 2023-04-17 | 2024-04-15 | On-time | 2024-04-16 | 1 | 2024-04-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512715 | T2 DI KESWICK-TRINITY 9/118 RPL POLE | 70Y
LC | 125936538 | 013/264 | T2 EI CTTNWOOD-RED BLUFF 13/264 RPR INSW | TABLEMTN | ETL.6660.INSL.NCER | 2023-04-17 | 2023-04-17 | 2023-11-20 | On-time | 2024-04-16 | 148 | 2024-04-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46020285 | T2 EI CTTNWOOD-RED BLUFF 13/264 RPR INSW | ICW
LC | 125936816 | 013/265 | T2 EI CTTNWOOD-RED BLUFF 13/265 RPL HRDD | TABLEMTN | ETL.6660.POLE.NWOD | 2023-04-17 | 2023-04-17 | 2023-11-20 | On-time | 2024-04-16 | 148 | 2024-04-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46020286 | T2 EI CTTNWOOD-RED BLUFF 13/265 RPL HRDD | ICW
LC | 125937129 | 052/227 | T2 EI RND MTN-TBL MTN #2 52/227 BNT STEL | TABLEMTN | ETL.6070.TOWR | 2023-04-17 | 2023-04-17 | 2023-11-09 | On-time | 2024-04-16 | 159 | 2024-04-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46028564 | T2 EI RND MTN-TBL MTN #2 52/227 BNT STEL | ICQ
LC | 125937445 | 007/153 | T2 EI VALLEY SPRINGS #1 007/153 RPL HRDW | VICTOR | ETL.8210.INSL.NCER | 2023-04-17 | 2023-04-17 | 2024-03-21 | On-time | 2024-04-16 | 26 | 2024-04-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46080878 | T2 EI VALLEY SPRINGS #1 007/153 RPL HRDW | ICW
LC | 125937917 | 022/309 | T2 EI CLAY-MARTEL 022/309 RPR INSW | VICTOR | ETL.8250.INSL.NCER | 2023-04-17 | 2023-04-17 | 2024-01-17 | On-time | 2024-04-16 | 90 | 2024-04-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46017004 | T2 EI CLAY-MARTEL 022/309 RPR INSW | ICW
LC | 125944328 | 033/133 | T2 DI DIABLO-MIDWAY #2 033/133 RPR SHLS | PISMOBCH | ETL.5970.TOWR | 2023-04-18 | 2023-04-17 | 2024-02-20 | On-time | 2024-04-16 | 56 | 2024-04-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46078963 | T2 DI DIABLO-MIDWAY #2 033/133 RPR SHLS | ICS
LC | 125947425 | 038/152 | T2 DI DIABLO-MIDWAY #2 38/152 RPR SHLS | PISMOBCH | ETL.5970.TOWR | 2023-04-18 | 2023-04-17 | 2024-03-11 | On-time | 2024-04-16 | 36 | 2024-04-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46078964 | T2 DI DIABLO-MIDWAY #2 38/152 RPR SHIELD | ICS
LC | 125972681 | 094/480 | T2 DI MALIN-RND MTN #2 94/480 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-04-22 | 2023-04-19 | 2024-05-11 | Late | 2024-04-18 | -23 | 2024-04-19 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46240384 | T2 DI MALIN-RND MTN #2 94/480 RPR OPGW | ICS
LC | 125963048 | 000/010 | T2 DI CLGTE GRS VLY 00/010 COMPLETE | SACTO | ETL.6490.POLE.NWOD | 2023-04-20 | 2023-04-17 | 2024-03-18 | On-time | 2024-04-16 | 29 | 2024-04-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46030912 | T2 DI CLGTE GRS VLY 00/010 RPR GYWW | ICW
LC | 125963529 | 005/023 | T2 DI PITTSBURG-SN RAMON 5/23 REGRADE | CONCORD | ETL.5490.TOWR | 2023-04-20 | 2023-04-17 | 2023-07-24 | On-time | 2024-04-16 | 267 | 2024-04-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45899302 | T2 DI PITTSBURG-SN RAMON 5/23 REGRADE | ICQ
LC | 125971148 | 006/026 | T2 DI PTTSBURG TASSAJARA 06/026 RPR CNDS | CONCORD | ETL.5470.INSL.NCER | 2023-04-21 | 2023-04-17 | 2024-02-26 | On-time | 2024-04-16 | 50 | 2024-04-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 45997113 | T2 DI PTTSBURG TASSAJARA 06/026 RPR CNDS | ICS
LC | 125991642 | 002/052 | T2 DI CLGT-GRASS VALLEY 2/052 RPL CRSW | SACTO | ETL.6490.POLE.WOOD | 2023-04-25 | 2023-04-17 | 2024-03-07 | On-time | 2024-04-16 | 40 | 2024-04-17 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35508971 | T2 DI CLGT-GRASS VALLEY 2/052 RPL CRSW | 93E
LC | 125992250 | 002/067 | T2 DI CLGT-GRASS VALLEY 2/67 RPL STRW | SACTO | ETL.6490.POLE.WOOD | 2023-04-25 | 2023-04-17 | 2024-03-22 | On-time | 2024-04-16 | 25 | 2024-04-17 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508972 | T2 DI CLGT-GRSS VLLY 2/65 RPL STRW | 70Y
LC | 126007609 | 005/025 | T2 DI PITTBRG SN RAMON 5/25 BENT STEEL | CONCORD | ETL.5490.TOWR | 2023-04-27 | 2023-04-17 | 2024-02-13 | On-time | 2024-04-16 | 63 | 2024-04-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46058956 | T2 DI PITTBRG SN RAMON 5/25 BENT STEEL | ICQ
LC | 126008028 | 002/056 | T2 DI CLGT-GRASS VLLY 002/056 RPR STRW | SACTO | ETL.6490.POLE.WOOD | 2023-04-27 | 2023-04-17 | 2024-01-26 | On-time | 2024-04-16 | 81 | 2024-04-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46030916 | T2 DI CLGT-GRASS VLLY 002/056 RPR STRW | ICW
LC | 125972804 | 029/000 | T2 EI GRBRVLL-LYTNVLL 29/0 RPR JMPW | WILLITS | ETL.8365.INSL.NCER | 2023-04-22 | 2023-04-22 |  | Late | 2024-04-21 |  | 2024-04-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46219465 | T2 EI GRBRVLL-LYTNVLL 29/0 RPR JMPW | ICW
LC | 126008534 | 000/014 | T2 DI COLGATE-GRASS VALLEY 0/14 RPR INSW | SACTO | ETL.6490.INSL.CERA | 2023-04-27 | 2023-04-17 | 2024-03-18 | On-time | 2024-04-16 | 29 | 2024-04-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46030917 | T2 DI COLGATE-GRASS VALLEY 0/14 RPR INSW | ICW
LC | 125972887 | 000/003 | T2 DI RACETRACK TAP 0/3 RPL POLE | VICTOR | ETL.2393.POLE.WOOD | 2023-04-22 | 2023-04-13 |  | Late | 2024-04-12 |  | 2024-04-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508484 | T2 DI RACETRACK TAP 0/3 RPL POLE | 70Y
LC | 126008536 | 000/014 | T2 DI COLGATE-GRASS VALLEY 0/14 RPR STRW | SACTO | ETL.6490.POLE.WOOD | 2023-04-27 | 2023-04-17 | 2024-03-18 | On-time | 2024-04-16 | 29 | 2024-04-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46030918 | T2 DI COLGATE-GRASS VALLEY 0/14 RPR STRW | ICW
LC | 126011519 | 002/065 | T2 DI CLGT-GRSS VLLY 2/65 RPL STRW | SACTO | ETL.6490.POLE.WOOD | 2023-04-28 | 2023-04-17 | 2024-03-22 | On-time | 2024-04-16 | 25 | 2024-04-17 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508972 | T2 DI CLGT-GRSS VLLY 2/65 RPL STRW | 70Y
LC | 125972923 | 034/002 | T2 EI MNDCNO-WLTS-FRT BRG 34/02 COTTER | WILLITS | ETL.7550.INSL.NCER | 2023-04-22 | 2023-04-22 |  | Late | 2024-04-21 |  | 2024-04-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46214049 | T2 EI MNDCNO-WLTS-FRT BRG 34/02 COTTER | ICW
LC | 126014037 | 004/021 | T2NT DI PTSBRG-SN RAMON 004/021 RPL HRDT | CONCORD | ETL.5490.TOWR | 2023-04-28 | 2023-04-17 | 2023-08-02 | On-time | 2024-04-16 | 258 | 2024-04-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45908567 | T2NT DI PTSBRG-SN RAMON 004/021 RPL HRDT | ICQ
LC | 126016248 | 002/054 | T2 DI COLGATE-GRS VLLY 2/54 RPR STRW | SACTO | ETL.6490.POLE.WOOD | 2023-04-28 | 2023-04-17 | 2024-01-26 | On-time | 2024-04-16 | 81 | 2024-04-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46031041 | T2 DI COLGATE-GRS VLLY 2/54 RPR STRW | ICW
LC | 126017508 | 002/064 | T2 DI COLGATE-GRASS VLLY 2/64 RPR INSW | SACTO | ETL.6490.INSL.NCER | 2023-04-29 | 2023-04-17 | 2024-03-06 | On-time | 2024-04-16 | 41 | 2024-04-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46031043 | T2 DI COLGATE-GRASS VLLY 2/64 RPR INSW | ICW
LC | 126114605 | 093/477 | T2 DI MLN-ROUND MTN #2 93/477 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-05-12 | 2023-04-17 | 2024-01-16 | On-time | 2024-04-16 | 91 | 2024-04-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46027041 | T2 DI MLN-ROUND MTN #2 93/477 RPR SHLS | ICS
LC | 125941152 | 022/312-GUY | T2 EI CLAY-MARTEL 22/312-GUY RPR GYWW | VICTOR | ETL.8250.POLE.WOOD | 2023-04-18 | 2023-04-18 | 2024-01-17 | On-time | 2024-04-17 | 91 | 2024-04-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46011998 | T2 EI CLAY-MARTEL 22/312-GUY RPR GYWW | ICW
LC | 125941635 | 028/195B | T2 EI TRINITY-COTTNWOOD 28/195B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-04-18 | 2023-04-18 | 2024-03-04 | On-time | 2024-04-17 | 44 | 2024-04-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46027005 | T2 EI TRINITY-COTTNWOOD 28/195B RPR GYWW | ICW
LC | 125941647 | 009/191 | T2 EI VALLEY SPRINGS #1 009/191 RPR INSW | VICTOR | ETL.8210.INSL.NCER | 2023-04-18 | 2023-04-18 | 2024-03-28 | On-time | 2024-04-17 | 20 | 2024-04-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081368 | T2 EI VALLEY SPRINGS #1 009/191 RPR INSW | ICW
LC | 125941924 | 024/394 | T2 EI KESWICK-TRINITY 24/394 RMV VEG | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-18 | 2023-04-18 | 2024-04-16 | On-time | 2024-04-17 | 1 | 2024-04-18 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125941948 | 028/195C | T2 EI TRNTY-CTTNWD 028/195C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-04-18 | 2023-04-18 | 2024-03-04 | On-time | 2024-04-17 | 44 | 2024-04-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46027006 | T2 EI TRNTY-CTTNWD 028/195C RPR GYWW | ICW
LC | 125973346 | 014/000 | T2 DI LTNVL-WILLTS 14/0 CANCEL | WILLITS | ETL.8360.POLE.NWOD | 2023-04-22 | 2023-04-12 |  | Late | 2024-04-11 |  | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46222491 | T2 DI LTNVL-WILLTS 14/0 CANCEL | ICW
LC | 125942656 | 024/390 | T2 EI KESWICK-TRINITY 24/390 COMPLETE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-18 | 2023-04-18 | 2023-07-13 | On-time | 2024-04-17 | 279 | 2023-07-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45749935 | T2 EI KESWICK-TRINITY 024/390 RPR GYWW | ICW
LC | 125973385 | 029/005 | T2 DI FRT RSS-GUALALA 029/005 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-04-22 | 2023-04-12 |  | Late | 2024-04-11 |  | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46045923 | T2 DI FRT RSS-GUALALA 029/005 RPR INSW | ICW
LC | 125943341 | 022/316 | T2 EI CLAY-MARTEL 022/316 RPR INSW | VICTOR | ETL.8250.INSL.CERA | 2023-04-18 | 2023-04-18 | 2024-01-16 | On-time | 2024-04-17 | 92 | 2024-04-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46017005 | T2 EI CLAY-MARTEL 022/316 RPR INSW | ICW
LC | 125973568 | 030/452 | T2 EI CLAY-MARTEL+ 030/452 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2023-04-22 | 2023-04-22 |  | Late | 2024-04-21 |  | 2024-04-22 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31653149 | T2 EI CLAY-MARTEL 27/399 RPL POLE | 70Y
LC | 125943629 | 005/133 | T2 EI HMLTN BRNCH-CHSTR 5/133 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2023-04-18 | 2023-04-18 | 2023-08-10 | On-time | 2024-04-17 | 251 | 2024-04-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45904662 | T2 EI HMLTN BRNCH-CHSTR 5/133 RPR STRW | ICW
LC | 125944143 | 053/229 | T2 EI RND MTN-TBL MTN #1 50/229 BNT STEL | TABLEMTN | ETL.6060.TOWR | 2023-04-18 | 2023-04-18 | 2023-12-20 | On-time | 2024-04-17 | 119 | 2024-04-18 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46028418 | T2 EI RND MTN-TBL MTN #1 50/229 BNT STEL | ICQ
LC | 125973699 | 000/005 | T2 DI MNDCNO-HRTLY 000/005 REFRAME | WILLITS | ETL.7510.POLE.WOOD | 2023-04-22 | 2023-04-12 |  | Late | 2024-04-11 |  | 2024-04-12 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35488480 | T2 DI MNDCNO-HRTLY 000/005 REFRAME | 93E
LC | 125945112 | B019/425 | T2 EI DRM-GRS VLY-WMAR B019/425 RPR INSW | SACTO | ETL.6760.INSL.CERA | 2023-04-18 | 2023-04-18 | 2024-01-12 | On-time | 2024-04-17 | 96 | 2024-04-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46030911 | T2 EI DRM-GRS VLY-WMAR B019/425 RPR INSW | ICW
LC | 125945293 | 025/006 | T2 GARBERVILLE-LAYTONVILLE 25/6 RPR GO95 | WILLITS | ETL.8365.POLE.WOOD | 2023-04-18 | 2023-04-18 | 2023-10-02 | On-time | 2024-04-17 | 198 | 2024-04-18 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31642673 | T2 GARBERVILLE-LAYTONVILLE - 60 KV_025/0 | 93G
LC | 125945295 | 019/274 | T2 EI KESWICK-TRINITY 019/274 RPL STRW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-18 | 2023-04-18 | 2024-04-17 | On-time | 2024-04-17 | 0 | 2024-04-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35516510 | T2 EI KESWICK-TRINITY 019/274 RPL STRW | 70Y
LC | 125945407 | 005/030 | T2 EI TULUCAY-VACA-VACA 005/030 COTTER | SACTO | ETL.5800.INSL.NCER | 2023-04-18 | 2023-04-18 | 2023-11-15 | On-time | 2024-04-17 | 154 | 2024-04-18 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45985057 | T2 EI TULUCAY-VACA-VACA 005/030 COTTER | ICS
LC | 125974077 | 030/455 | T2 EI CLAY-MARTEL+ 030/455 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2023-04-22 | 2023-04-22 | 2024-06-08 | Late | 2024-04-21 | -48 | 2024-04-22 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31653149 | T2 EI CLAY-MARTEL 27/399 RPL POLE | 70Y
LC | 125945436 | 023/323 | T2 EI CLAY-MARTEL 023/323 RPR POLE | VICTOR | ETL.8250.POLE.WOOD | 2023-04-18 | 2023-04-18 | 2024-01-18 | On-time | 2024-04-17 | 90 | 2024-04-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46017006 | T2 EI CLAY-MARTEL 023/323 RPR POLE | ICW
LC | 125974118 | 035/002 | T2 EI MNDCNO-WLLTS-FRT BRG 35/2 COA | WILLITS | ETL.7550.POLE.WOOD | 2023-04-22 | 2023-04-22 |  | Late | 2024-04-21 |  | 2024-04-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46214053 | T2 EI MNDCNO-WLLTS-FRT BRG 35/2 RPR GYWW | ICW
LC | 125945563 | 053/231 | T2 EI RND MTN-TBL MTN #1 53/231 BNT STEL | TABLEMTN | ETL.6060.TOWR | 2023-04-18 | 2023-04-18 | 2023-10-31 | On-time | 2024-04-17 | 169 | 2024-04-18 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46028560 | T2 EI RND MTN-TBL MTN #1 53/231 BNT STEL | ICQ
LC | 125946178 | 000/013 | T2 IGNACIO-BOLINAS #1 0/13 RPR GO95 | LAKEVLLE | ETL.7140.POLE.WOOD | 2023-04-18 | 2023-04-18 | 2023-09-13 | On-time | 2024-04-17 | 217 | 2024-04-18 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31642677 | T2 IGNACIO-BOLINAS #1 - 60 KV_000/013 | 93G
LC | 125946367 | 012/246 | T2 EI COTTONWD-RD BLFF 12/246 RPR POLE | TABLEMTN | ETL.6660.POLE.WOOD | 2023-04-18 | 2023-04-18 | 2023-11-22 | On-time | 2024-04-17 | 147 | 2024-04-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46025230 | T2 EI COTTONWD-RD BLFF 12/246 RPR POLE | ICW
LC | 125947105 | 003/006 | T2 HUMBOLDT-MAPLE CREEK 3/6 RPR GO95 | EUREKA | ETL.7130.POLE.WOOD | 2023-04-18 | 2023-04-18 | 2023-11-15 | On-time | 2024-04-17 | 154 | 2024-04-18 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31642674 | T2 HUMBOLDT-MAPLE CREEK - 60 KV_003/006 | 93G
LC | 125947107 | 019/280 | T2 EI KESWICK-TRINITY 019/280 RPR STRW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-18 | 2023-04-18 | 2024-04-17 | On-time | 2024-04-17 | 0 | 2024-04-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46026274 | T2 EI KESWICK-TRINITY 019/280 RPR STRW | ICW
LC | 125947111 | 004/037A | T2 EI TRINITY-COTTONWD 004/037A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-04-18 | 2023-04-18 | 2023-08-28 | On-time | 2024-04-17 | 233 | 2024-04-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45957601 | T2 EI TRINITY-COTTONWD 004/037A RPR GYWW | ICW
LC | 125947146 | 008/159 | T2 EI VALLEY SPRINGS #1 008/159 RPR POLE | VICTOR | ETL.8210.POLE.WOOD | 2023-04-18 | 2023-04-18 | 2024-03-21 | On-time | 2024-04-17 | 27 | 2024-04-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081370 | T2 EI VALLEY SPRINGS #1 008/159 RPR POLE | ICW
LC | 125952437 | 033/134 | T2 DI DIABLO MIDWAY#2 33/134 RPR SHLS | PISMOBCH | ETL.5980.TOWR | 2023-04-19 | 2023-04-18 | 2024-02-20 | On-time | 2024-04-17 | 57 | 2024-04-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46088500 | T2 DI DIABLO MIDWAY#2 33/134 RPR SHLS | ICS
LC | 125974532 | 019/387 | T2 EI CRB-WSTWD 019/387 RPR INSW | TABLEMTN | ETL.6300.INSL | 2023-04-22 | 2023-04-22 |  | Late | 2024-04-21 |  | 2023-07-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46026998 | T2 EI CRB-WSTWD 019/387 RPR INSW | ICW
LC | 125965061 | 000/003 | T2 DI COLGATE-GRASS VALLEY 00/003 COTTER | SACTO | ETL.6490.INSL.CERA | 2023-04-21 | 2023-04-18 | 2024-03-18 | On-time | 2024-04-17 | 30 | 2024-04-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46030913 | T2 DI COLGATE-GRASS VALLEY 00/003 COTTER | ICS
LC | 125974695 | A001/021 | T2 DI SMARTVIL-CAMP FW A1/21 RPL STRW | SACTO | ETL.7970.POLE.WOOD | 2023-04-22 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481545 | T2 DI SMARTVIL-CAMP FW A1/21 RPL STRW | 70Y
LC | 125974843 | 035/004 | T2 EI MNDCNO-WLTS-FT BRG 35/04 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2023-04-22 | 2023-04-22 | 2024-05-04 | Late | 2024-04-21 | -13 | 2024-04-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46214054 | T2 EI MNDCNO-WLTS-FT BRG 35/04 RPR GYWW | ICW
LC | 125974865 | 032/004 | T2 DI PHILO JCT-ELK 32/4 RPL HRDD | WILLITS | ETL.7780.POLE.WOOD | 2023-04-22 | 2023-04-11 | 2024-06-21 | Late | 2024-04-10 | -72 | 2024-04-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46213868 | T2 DI PHILO JCT-ELK 32/4 RPL HRDD | ICW
LC | 125967719 | 030/209 | T2 DI TRINY-COTNWD 30/209L RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-21 | 2023-04-18 | 2023-06-27 | On-time | 2024-04-17 | 295 | 2023-07-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45749650 | T2 DI TRINY-COTNWD 30/209L RPR GYWW | ICW
LC | 125967793 | 030/209 | T2 DI TRINY-COTNWD 30/209R RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-21 | 2023-04-18 | 2023-06-27 | On-time | 2024-04-17 | 295 | 2023-07-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45749651 | T2 DI TRINY-COTNWD 30/209R RPR GYWW | ICW
LC | 125975118 | 004/114 | T2 EI COLGATE-ALLEGHANY 4/114 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2023-04-22 | 2023-04-22 |  | Late | 2024-04-21 |  | 2024-04-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506669 | T2 EI COLGATE-ALLEGHANY 004/114 RPL POLE | 70Y
LC | 125967844 | 030/209 | T2 DI TRINY-COTNWD 30/209 RPR INSW | TABLEMTN | ETL.4040.INSL.CERA | 2023-04-21 | 2023-04-18 | 2023-06-27 | On-time | 2024-04-17 | 295 | 2024-04-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45749652 | T2 DI TRINY-COTNWD 30/209 RPR INSW | ICW
LC | 125975271 | 035/007 | T2 EI MNDCNO-WLTS-FT BRG 35/07 RPR GYWW | WILLITS | ETL.7550.POLE.NWOD | 2023-04-22 | 2023-04-22 |  | Late | 2024-04-21 |  | 2024-04-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46214055 | T2 EI MNDCNO-WLTS-FT BRG 35/07 RPR GYWW | ICW
LC | 125973275 | 000/002 | T2 DI COLGATE-GRASS VALLEY 00/002 COTTER | SACTO | ETL.6490.INSL.CERA | 2023-04-22 | 2023-04-18 | 2024-03-18 | On-time | 2024-04-17 | 30 | 2024-04-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46030915 | T2 DI COLGATE-GRASS VALLEY 00/002 COTTER | ICW
LC | 125974038 | 029/206 | T2 DI TRINITY-COTTONWOD 029/206 COTTER | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-22 | 2023-04-18 | 2024-03-04 | On-time | 2024-04-17 | 44 | 2024-04-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46027007 | T2 DI TRINITY-COTTONWOD 029/206 COTTER | ICW
LC | 126013618 | 000/005 | T2 DI COLGATE-GRASS VALLEY 0/5 RPR STRW | SACTO | ETL.6490.POLE.WOOD | 2023-04-28 | 2023-04-18 | 2024-03-07 | On-time | 2024-04-17 | 41 | 2024-04-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46031040 | T2 DI COLGATE-GRASS VALLEY 0/5 RPR STRW | ICW
LC | 125948043 | 005/070 | T2 GREEN VLLEY-PAUL SWEET 5/70 COTR KEY | MOSSLNDG | ETL.1730.INSL.CERA | 2023-04-19 | 2023-04-19 | 2023-12-12 | On-time | 2024-04-18 | 128 | 2024-04-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46031414 | T2 GREEN VLLEY-PAUL SWEET 5/70 COTR KEY | ICW
LC | 125977885 | 009/008 | T2 DI MELONES-RACETRACK 09/008 RPR STRW | VICTOR | ETL.2400.POLE.WOOD | 2023-04-24 | 2023-04-12 | 2024-05-08 | Late | 2024-04-11 | -27 | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46080903 | T2 DI MELONES-RACETRACK 09/008 RPR STRW | ICW
LC | 125949365 | 027/194 | T2 EI TRNTY-CTTNWD 027/194 RPR HRDD | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-19 | 2023-04-19 | 2023-06-26 | On-time | 2024-04-18 | 297 | 2024-04-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45909827 | T2 EI TRNTY-CTTNWD 027/194 RPR HRDD | ICW
LC | 125978362 | 006/049 | T2 EI TRINITY-COTTONWOOD 06/049 RPR CNDW | TABLEMTN | ETL.4040.INSL.CERA | 2023-04-24 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46037312 | T2 EI TRINITY-COTTONWOOD 06/049 RPR CNDW | ICW
LC | 125978576 | 037/002 | T2 EI MNDCNO-WLTS-FRT BRGG 37/2 RPL INSW | WILLITS | ETL.7550.INSL.NCER | 2023-04-24 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35558799 | T2 EI MNDCNO-WLTS-FRT BRGG 37/2 RPL INSW | 93I
LC | 125978816 | 031/468 | T2 EI CLAY-MARTEL+ 031/468 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2023-04-24 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31653149 | T2 EI CLAY-MARTEL 27/399 RPL POLE | 70Y
LC | 125949762 | 007/136 | T2 EI VALLEY SPRINGS #1 007/136 RPR POLE | VICTOR | ETL.8210.POLE.WOOD | 2023-04-19 | 2023-04-19 | 2024-03-25 | On-time | 2024-04-18 | 24 | 2024-04-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081373 | T2 EI VALLEY SPRINGS #1 007/136 RPR POLE | ICW
LC | 125950147 | 054/233 | T2 EI RND MTN-TBL MTN #2 54/233 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2023-04-19 | 2023-04-19 | 2024-03-27 | On-time | 2024-04-18 | 22 | 2024-04-19 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46028566 | T2 EI RND MTN-TBL MTN #2 54/233 RPR STRT | ICQ
LC | 125950212 | 054/233 | T2 EI RND MTN-TBL MTN #1 54/2 BENT STEEL | TABLEMTN | ETL.6060.TOWR | 2023-04-19 | 2023-04-19 | 2023-10-31 | On-time | 2024-04-18 | 170 | 2024-04-19 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46028561 | T2 EI RND MTN-TBL MTN #1 54/2 BENT STEEL | ICQ
LC | 125979262 | 031/470 | T2 EI CLAY-MARTEL 31/470 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2023-04-24 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35524739 | T2 EI CLAY-MARTEL+ 031/470 RPL STRW | 70Y
LC | 125979317 | 000/005A | T2 EI CRYSTL SPRNGS TP 0/5A RMV VEG | METCALF | ETL.7211.POLE.NWOD | 2023-04-24 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation-Tower | Cage Clearing
LC | 125979612 | 000/010 | T2 DI MELONES-CURTIS 0/10R RPL POLE | VICTOR | ETL.2390.POLE.WDPS | 2023-04-24 | 2023-03-30 | 2024-05-15 | Late | 2024-03-29 | -47 | 2024-03-30 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507608 | T2 DI MELONES-CURTIS 0/10L RPL POLE | 70Y
LC | 125979631 | 000/003 | T2 EI PINE GROVE TAP 000/003 RPL POLE | VICTOR | ETL.8351.POLE.WOOD | 2023-04-24 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525753 | T2 EI PINE GROVE TAP 000/003 RPL POLE | 70Y
LC | 125950367 | 004/049 | T2 EI SNTH LN-PCFCA 4/49 WASH INSW | METCALF | ETL.7575.INSL.CERA | 2023-04-19 | 2023-04-19 | 2024-02-23 | On-time | 2024-04-18 | 55 | 2024-04-19 | 622 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Contaminated | Insulator | Ground Wash | 46080473 | T2 EI SNTH LN-PCFCA 4/49 WASH INSW | ICD
LC | 125950369 | 004/049 | T2 EI SNTH LN-PCFCA 4/49L RPR ANCW | METCALF | ETL.7575.POLE.WDPS | 2023-04-19 | 2023-04-19 | 2024-02-23 | On-time | 2024-04-18 | 55 | 2024-04-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46080474 | T2 EI SNTH LN-PCFCA 4/49L RPR ANCW | ICW
LC | 125981088 | 010/053 | T2 EI RND MTN-TBLE MTN #2 10/53 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2023-04-24 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45758969 | T2 EI RND MTN-TBLE MTN #2 10/53 RPR STRT | ICQ
LC | 125950517 | 004/049 | T2 EI SNTH LN-PCFCA 4/49C RPR ANCW | METCALF | ETL.7575.POLE.WDPS | 2023-04-19 | 2023-04-19 | 2024-02-23 | On-time | 2024-04-18 | 55 | 2024-04-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46080475 | T2 EI SNTH LN-PCFCA 4/49C RPR ANCW | ICW
LC | 125981367 | 038/001 | T2 EI MNDCNO-WLTS-FRT BRGG 38/1 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2023-04-24 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35550569 | T2 EI MNDCNO-WLLTS-FRT BRGG 38/1 RPL PL | 70Y
LC | 125981368 | 038/001 | T2 EI MNDCN-WLTS-FRT BRGG 38/1 RPR ANCW | WILLITS | ETL.7550.POLE.WOOD | 2023-04-24 | 2023-04-24 |  | Late | 2024-04-23 |  | 2023-10-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46214080 | T2 EI MNDCNO-WLLTS-FRT BRGG 38/1 RPR ANC | ICW
LC | 125981487 | 055/236 | T2 EI RND MTN-TBL MTN #2 55/236 RPR SPLS | TABLEMTN | ETL.6070.INSL.NCER | 2023-04-24 | 2023-04-24 | 2024-05-03 | Late | 2024-04-23 | -10 | 2024-04-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Steel | Repair | 46037398 | T2 EI RND MTN-TBL MTN #2 55/236 RPR JMPS | ICS
LC | 125950715 | 004/049 | T2 EI SNTH LN-PCFCA 4/49R RPR ANCW | METCALF | ETL.7575.POLE.WDPS | 2023-04-19 | 2023-04-19 | 2024-02-23 | On-time | 2024-04-18 | 55 | 2024-04-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46080476 | T2 EI SNTH LN-PCFCA 4/49R RPR ANCW | ICW
LC | 125982110 | 031/475 | T2 EI CLAY-MARTEL 31/475 RPL STRW | VICTOR | ETL.8250.POLE.WDPS | 2023-04-24 | 2023-04-24 | 2024-06-11 | Late | 2024-04-23 | -49 | 2024-04-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35524739 | T2 EI CLAY-MARTEL+ 031/470 RPL STRW | 70Y
LC | 125982312 | 031/475 | T2 EI CLAY-MARTEL 31/475 RPL STRW | VICTOR | ETL.8250.POLE.WDPS | 2023-04-24 | 2023-04-24 | 2024-06-11 | Late | 2024-04-23 | -49 | 2024-04-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35524739 | T2 EI CLAY-MARTEL+ 031/470 RPL STRW | 70Y
LC | 125982444 | 031/475 | T2 EI CLAY-MARTEL 31/475 RPL STRW | VICTOR | ETL.8250.POLE.WDPS | 2023-04-24 | 2023-04-24 | 2024-06-11 | Late | 2024-04-23 | -49 | 2024-04-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35524739 | T2 EI CLAY-MARTEL+ 031/470 RPL STRW | 70Y
LC | 125951339 | 008/166 | T2 EI VALLEY SPRINGS #1 008/166 RPR POLE | VICTOR | ETL.8210.POLE.WOOD | 2023-04-19 | 2023-04-19 | 2024-03-26 | On-time | 2024-04-18 | 23 | 2024-04-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081375 | T2 EI VALLEY SPRINGS #1 008/166 RPR POLE | ICW
LC | 125951608 | 028/171 | T2 EI TMBLR-SN LUS OBISP 28/171 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2023-04-19 | 2023-04-19 | 2024-04-01 | On-time | 2024-04-18 | 17 | 2024-04-19 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674043 | T2 EI TEMBLR-SN LUS OBSP 29/175 RPL INST | 93K
LC | 125952652 | 019/284 | T2 EI KESWICK-TRINITY 019/284 RPR ANCW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-19 | 2023-04-19 | 2023-07-13 | On-time | 2024-04-18 | 280 | 2023-10-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45749934 | T2 EI KESWICK-TRINITY 019/284 RPR ANCW | ICW
LC | 125983280 | :016/005 | T2 WV EAGLE RCK-REDBUD :016/005 INS DMPW | WILLITS | ETL.1480.INSL.NCER | 2023-04-24 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 45763184 | T2 WV EAGLE RCK-REDBUD :016/005 INS DMPW | ICW
LC | 125952656 | 019/281 | T2 EI KESWICK-TRINITY 019/281 RPR GYWW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-19 | 2023-04-19 | 2024-04-17 | On-time | 2024-04-18 | 1 | 2024-04-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46026277 | T2 EI KESWICK-TRINITY 019/281 RPR GYWW | ICW
LC | 125983469 | 084/588 | T2 EI BRIDGEVILLE-CTNWD 84/588R RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-04-24 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505113 | T2 EI BRIDGEV-COTTONWOOD 84/592 RPL POLE | 70Y
LC | 125983479 | 084/588 | T2 EI BRIDGVILL-CTNWD 84/588L RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-04-24 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505113 | T2 EI BRIDGEV-COTTONWOOD 84/592 RPL POLE | 70Y
LC | 125983661 | 157 | T2 DI MELONES-CURTIS 009/002A RPR SPLS | VICTOR | ETL.2390.SWIT | 2023-04-24 | 2023-04-12 |  | Late | 2024-04-11 |  | 2024-04-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Steel | Repair | 46161639 | T2 DI MELONES-CURTIS 009/002A RPR SPLS | ICS
LC | 125952671 | 020/288 | T2 EI KESWICK-TRINITY 020/288 RPR POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-19 | 2023-04-19 | 2024-04-18 | On-time | 2024-04-18 | 0 | 2024-04-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46026279 | T2 EI KESWICK-TRINITY 020/288 RPR POLE | ICW
LC | 125952733 | 004/002 | T2 EI MENDOCINO-HARTLEY 4/2 RPR GYWW | WILLITS | ETL.7510.POLE.NWOD | 2023-04-19 | 2023-04-19 | 2024-01-26 | On-time | 2024-04-18 | 83 | 2024-04-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46089305 | T2 EI MENDOCINO-HARTLEY 4/2 RPR GYWW | ICW
LC | 125983866 | :017/012 | T2 WV EAGLE RCK-REDBUD :017/012 RPL POLE | WILLITS | ETL.1480.POLE.WOOD | 2023-04-24 | 2023-04-24 |  | Late | 2024-04-23 |  | 2023-07-24 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487500 | T2 WV EAGLE RCK-REDBUD :017/012 RPL POLE | 70Y
LC | 125952886 | 008/164 | T2 EI VALLEY SPRINGS #1 008/164 RPL POLE | VICTOR | ETL.8210.POLE.WOOD | 2023-04-19 | 2023-04-19 | 2024-03-27 | On-time | 2024-04-18 | 22 | 2024-04-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35511455 | T2 EI VALLEY SPRINGS #1 008/164 RPL POLE | 70Y
LC | 125983954 | 337 | T2 DI PIT #7 TAP 03/29 RPR SWITCH | TABLEMTN | ETL.5442.SWIT | 2023-04-24 | 2023-04-12 | 2024-06-17 | Late | 2024-04-11 | -67 | 2024-04-12 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 46011630 | T2 DI PIT #7 TAP 03/29 RPR SWITCH | ICE
LC | 125953349 | 008/163 | T2 EI VALLEY SPRINGS #1 008/163 RPR POLE | VICTOR | ETL.8210.POLE.WOOD | 2023-04-19 | 2023-04-19 | 2024-03-26 | On-time | 2024-04-18 | 23 | 2024-04-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081378 | T2 EI VALLEY SPRINGS #1 008/163 RPR POLE | ICW
LC | 125953872 | 008/162 | T2 EI VALLEY SPRINGS #1 008/162 RPR POLE | VICTOR | ETL.8210.POLE.WOOD | 2023-04-19 | 2023-04-19 | 2024-03-26 | On-time | 2024-04-18 | 23 | 2024-04-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081380 | T2 EI VALLEY SPRINGS #1 008/162 RPR POLE | ICW
LC | 125984082 | 039/258 | T2 DI TRINITY-CTTNWD 39/258L RPL HRDD | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-24 | 2023-04-14 | 2024-05-29 | Late | 2024-04-13 | -46 | 2024-04-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46011635 | T2 DI TRINITY-CTTNWD 39/258L RPL HRDD | ICW
LC | 125984249 | 006/085B | T2 DI KESWICK-TRINITY-06/85B RMV VEG | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-24 | 2023-04-13 |  | Late | 2024-04-12 |  | 2024-04-13 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 125954899 | 009/175 | T2 EI VALLEY SPRINGS #1 009/175 RPR POLE | VICTOR | ETL.8210.POLE.WOOD | 2023-04-19 | 2023-04-19 | 2024-03-27 | On-time | 2024-04-18 | 22 | 2024-04-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081382 | T2 EI VALLEY SPRINGS #1 009/175 RPR POLE | ICW
LC | 125984283 | 011/141 | T2 DI KESWICK-TRINITY 11/141 COMPLETE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-24 | 2023-04-13 |  | Late | 2024-04-12 |  | 2024-04-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46214191 | T2 DI KESWICK-TRINITY 11/141 COMPLETE | ICW
LC | 125984337 | 001/012 | T2 DI LYTNVIL-COVELO 1/12 RPR GYWW | WILLITS | ETL.7390.POLE.WOOD | 2023-04-24 | 2023-04-12 |  | Late | 2024-04-11 |  | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46219472 | T2 DI LYTNVIL-COVELO 1/12 RPR GYWW | ICW
LC | 125984382 | 036/004 | T2 DI FRT RSS-GUALALA 36/4 RPR CRSW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-04-24 | 2023-04-12 |  | Late | 2024-04-11 |  | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46045924 | T2 DI FRT RSS-GUALALA 36/4 RPR CRSW | ICW
LC | 125984476 | 016/001 | T2 DI LYTNVLL-WLLTS 016/001 RPL HRDD | WILLITS | ETL.8360.POLE.WOOD | 2023-04-24 | 2023-04-12 |  | Late | 2024-04-11 |  | 2024-04-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46222492 | T2 DI LYTNVLL-WLLTS 016/001 RPL HRDD | ICW
LC | 125984477 | 016/001 | T2 DI LYTNVLL-WLLTS 016/001 CANCEL | WILLITS | ETL.8360.POLE.WOOD | 2023-04-24 | 2023-04-12 |  | Late | 2024-04-11 |  | 2024-04-12 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35495228 | T2 DI LYTNVLL-WLLTS 016/001 RPL ANCW | 93E
LC | 125968694 | 013/203 | T2 DI GOLD HILL #1 013/203 COTTER | SACTO | ETL.6950.INSL.NCER | 2023-04-21 | 2023-04-19 | 2024-04-07 | On-time | 2024-04-18 | 11 | 2024-04-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46030914 | T2 DI GOLD HILL #1 013/203 COTTER | ICW
LC | 125972680 | 094/480 | T2 DI MALIN-ROUND MTN #2 94/480 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2023-04-22 | 2023-04-19 | 2023-11-14 | On-time | 2024-04-18 | 156 | 2024-04-19 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46028412 | T2 DI MALIN-ROUND MTN #2 94/480 RPR GYWS | ICS
LC | 125972704 | 009/080 | T2 DI CRAG VIEW-CASCADE 09/80 COTTER | TABLEMTN | ETL.1350.INSL.CERA | 2023-04-22 | 2023-04-19 | 2024-02-12 | On-time | 2024-04-18 | 66 | 2024-04-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46027008 | T2 DI CRAG VIEW-CASCADE 09/80 COTTER | ICW
LC | 125973451 | 089/453A | T2 DI MALIN-ROUND MTN#2 89/453A RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-04-22 | 2023-04-19 | 2024-01-18 | On-time | 2024-04-18 | 91 | 2024-04-19 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45752475 | T2 DI MALIN-ROUND MTN#2 89/453A RPR OPGW | ICS
LC | 125984928 | 008/112 | T2 DI KSWCK TRNITY 08/112 RMV VEG | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-25 | 2023-04-13 |  | Late | 2024-04-12 |  | 2023-10-13 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 125974222 | 094/478 | T2 DI MALIN ROUND MTN #2 94/478 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2023-04-22 | 2023-04-19 | 2024-01-12 | On-time | 2024-04-18 | 97 | 2024-04-19 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46027047 | T2 DI MALIN ROUND MTN #2 94/478 RPR INSS | ICS
LC | 125974223 | 094/478 | T2 DI MALIN ROUND MTN #2 94/478 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-04-22 | 2023-04-19 | 2024-01-12 | On-time | 2024-04-18 | 97 | 2024-04-19 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46027048 | T2 DI MALIN ROUND MTN #2 94/478 RPR SHLS | ICS
LC | 125985592 | 031/008 | T2 EI GARBRVILE-LAYTNVLE 031/08 RPR JMPW | WILLITS | ETL.8365.INSL.NCER | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46219462 | T2 EI GARBRVILE-LAYTNVLE 031/08 RPR JMPW | ICW
LC | 125985937 | 000/016 | T2 LAYTONVILLE-COVELO 000/016 CANCEL | WILLITS | ETL.7390.INSL.NCER | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46219464 | T2 LAYTONVILLE-COVELO 000/016 RPR INSW | ICW
LC | 125985989 | 038/005 | T2 EI MNDCNO-WLLTS-FRT BRG 38/5 CANCEL | WILLITS | ETL.7550.POLE.WOOD | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46048775 | T2 EI MNDCNO-WLLTS-FRT BRGG 38/5 RPR GYW | ICW
LC | 125986030 | 038/005 | T2 EI MNDCNO-WLLTS-FRT BRG 38/5 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35550569 | T2 EI MNDCNO-WLLTS-FRT BRGG 38/1 RPL PL | 70Y
LC | 125986109 | 032/482 | T2 EI CLAY-MARTEL 32/482L RPR GYWW | VICTOR | ETL.8250.POLE.STPS | 2023-04-25 | 2023-04-25 | 2024-06-12 | Late | 2024-04-24 | -49 | 2024-04-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46031267 | T2 EI CLAY-MARTEL 32/482L RPR GYWW | ICW
LC | 125986505 | 032/483 | T2 EI CLAY-MARTEL+ 032/483 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2023-04-25 | 2023-04-25 | 2024-06-12 | Late | 2024-04-24 | -49 | 2024-04-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35524739 | T2 EI CLAY-MARTEL+ 031/470 RPL STRW | 70Y
LC | 125986734 | 018/012 | T2 DI PHILO JCT-ELK 018/012 RPL INSW | WILLITS | ETL.7780.INSL.NCER | 2023-04-25 | 2023-04-12 | 2024-05-08 | Late | 2024-04-11 | -27 | 2024-04-12 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35495056 | T2 DI PHILO JCT-ELK 018/012 RPL INSW | 93I
LC | 125986830 | 032/486 | T2 EI CLAY-MARTEL+ 032/486 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2023-04-25 | 2023-04-25 | 2024-06-12 | Late | 2024-04-24 | -49 | 2024-04-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35524739 | T2 EI CLAY-MARTEL+ 031/470 RPL STRW | 70Y
LC | 126010307 | 090/461 | T2 DI MLN-RND MTN #2 90/461 UNBURY | TABLEMTN | ETL.6020.TOWR | 2023-04-28 | 2023-04-19 | 2023-11-01 | On-time | 2024-04-18 | 169 | 2024-04-19 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46028410 | T2 DI MLN-RND MTN #2 90/461 UNBURY | ICQ
LC | 126010733 | 091/467 | T2 DI MLN-RND MTN #2 91/467 RPL HRDT | TABLEMTN | ETL.6020.TOWR | 2023-04-28 | 2023-04-19 | 2023-11-01 | On-time | 2024-04-18 | 169 | 2024-04-19 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46028411 | T2 DI MLN-RND MTN #2 91/467 RPL HRDT | ICQ
LC | 126014127 | 009/082 | T2 DI CRAG VIEW-CSCD 009/082 RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-28 | 2023-04-19 | 2024-02-14 | On-time | 2024-04-18 | 64 | 2024-04-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46027009 | T2 DI CRAG VIEW-CSCD 009/082 RPR GYWW | ICW
LC | 126014326 | 090/460B | T2 DI MALIN-RND MTN #2 90/460B RPR STRT | TABLEMTN | ETL.6020.TOWR | 2023-04-28 | 2023-04-19 | 2023-11-01 | On-time | 2024-04-18 | 169 | 2024-04-19 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46028409 | T2 DI MALIN-RND MTN #2 90/460B RPR STRT | ICQ
LC | 126014958 | 086/438 | T2 DI MLN-RND MTN#2 86/438 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2023-04-28 | 2023-04-19 | 2024-03-29 | On-time | 2024-04-18 | 20 | 2024-04-19 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45937181 | T2 DI MLN-RND MTN#2 86/438 RPR INSS | ICS
LC | 126015334 | 009/078 | T2 DI CRAG VIEW-CSCD 9/78L RPL STRW | TABLEMTN | ETL.1350.POLE.WDPS | 2023-04-28 | 2023-04-19 | 2024-02-26 | On-time | 2024-04-18 | 52 | 2024-04-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35492476 | T2 EI CRAG VIEW-CASCADE RPL 9 STRW | 70Y
LC | 125987994 | 011/099 | T2 EI DELTA-MTN GTE JCT 11/99 RPL SPLS | TABLEMTN | ETL.6750.INSL | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Steel | Replace | 46036990 | T2 EI DELTA-MTN GTE JCT 11/99 RPL SPLS | ICS
LC | 126016104 | 001/003 | T2 DI MENDOCINO-HRTLY 1/3 RPL CRSW | WILLITS | ETL.7510.POLE.WOOD | 2023-04-28 | 2023-04-19 | 2024-02-20 | On-time | 2024-04-18 | 58 | 2024-04-19 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35488485 | T2 DI MENDOCINO-HRTLY 1/3 RPL CRSW | 93E
LC | 126016374 | 086/435 | T2 DI MLN-RND MTN #2 86/435 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2023-04-28 | 2023-04-19 | 2024-03-26 | On-time | 2024-04-18 | 23 | 2024-04-19 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46083368 | T2 DI MLN-RND MTN #2 86/435 RPR INSS | ICS
LC | 126017056 | 090/457 | T2 DI MALIN RND MTN #2 90/457 RPL SHLS | TABLEMTN | ETL.6020.TOWR | 2023-04-29 | 2023-04-19 | 2024-01-16 | On-time | 2024-04-18 | 93 | 2024-04-19 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 46027046 | T2 DI MALIN RND MTN #2 90/457 RPL SHLS | ICS
LC | 126017290 | 080/405B | T2 DI MALIN-RND MTN #2 80/405B COMPLETE | TABLEMTN | ETL.6020.TOWR | 2023-04-29 | 2023-04-19 | 2023-05-24 | On-time | 2024-04-18 | 330 | 2024-04-19 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45771361 | T2 DI MALIN-RND MTN #2 80/405B RPR ANCHS | ICS
LC | 126017607 | 080/405C | T2 DI MALIN-ROND MTN #2 80/405C RPR ANCS | TABLEMTN | ETL.6020.TOWR | 2023-04-29 | 2023-04-19 | 2023-08-23 | On-time | 2024-04-18 | 239 | 2023-10-19 | 628 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45758180 | T2 DI MALIN-ROND MTN #2 80/405C RPR ANCS | ICS
LC | 126018581 | 086/437 | T2 DI MLN-RND MT #2 86/437 RPL HRDT | TABLEMTN | ETL.6020.TOWR | 2023-04-29 | 2023-04-19 | 2024-04-04 | On-time | 2024-04-18 | 14 | 2024-04-19 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46028408 | T2 DI MLN-RND MT #2 86/437 RPL HRDT | ICQ
LC | 125990060 | A000/021 | T2 EI VALLEY SPRINGS #1 A0/021C RPL STRW | VICTOR | ETL.8210.POLE.WDPS | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35529771 | T2 EI VALLEY SPRINGS #1 A0/021A RPL STRW | 70Y
LC | 125990061 | A000/021 | T2 EI VALLEY SPRINGS #1 A0/021R RPL STRW | VICTOR | ETL.8210.POLE.WDPS | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35529771 | T2 EI VALLEY SPRINGS #1 A0/021A RPL STRW | 70Y
LC | 125990063 | A000/021 | T2 EI VALLEY SPRINGS#1 A0/021L RPL STRW | VICTOR | ETL.8210.POLE.WDPS | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35529771 | T2 EI VALLEY SPRINGS #1 A0/021A RPL STRW | 70Y
LC | 126018587 | 086/437 | T2 DI MLN-RND MT #2 86/437 RPR CNDS | TABLEMTN | ETL.6020.INSL.NCER | 2023-04-29 | 2023-04-19 | 2024-03-26 | On-time | 2024-04-18 | 23 | 2024-04-19 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46027045 | T2 DI MLN-RND MT #2 86/437 RPR CNDS | ICS
LC | 125990233 | 007/011 | T2 WV TULUCAY-NAPA #1 7/011 INS DAMW | LAKEVLLE | ETL.8180.INSL.NCER | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 46031743 | T2 WV TULUCAY-NAPA #1 7/011 INS DAMW | ICW
LC | 125990265 | 057/245 | T2 EI RND MTN-TBL MTN #2 057/245 RMV VEG | TABLEMTN | ETL.6070.TOWR | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 125990278 | 032/002 | T2 DI PHILO JCT ELK 032/002L RPR GYWW | WILLITS | ETL.7780.POLE.WDPS | 2023-04-25 | 2023-04-12 | 2024-06-14 | Late | 2024-04-11 | -64 | 2023-10-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213858 | T2 DI PHILO JCT ELK 032/002L RPR GYWW | ICW
LC | 125990733 | 032/002 | T2 DI PHILO JCT ELK 032/002 RPL ANCW | WILLITS | ETL.7780.POLE.WDPS | 2023-04-25 | 2023-04-12 | 2024-06-14 | Late | 2024-04-11 | -64 | 2024-04-12 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35495058 | T2 DI PHILO JCT ELK 032/002L RPL ANCW | 93E
LC | 125990863 | 032/002 | T2 DI PHILO JCT ELK 032/002L RPL ANCW | WILLITS | ETL.7780.POLE.WDPS | 2023-04-25 | 2023-04-12 | 2024-06-14 | Late | 2024-04-11 | -64 | 2024-04-12 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35495058 | T2 DI PHILO JCT ELK 032/002L RPL ANCW | 93E
LC | 125990878 | 032/002 | T2 DI PHILO JCT ELK 032/002 CNCL | WILLITS | ETL.7780.POLE.WDPS | 2023-04-25 | 2023-04-12 | 2024-04-16 | Late | 2024-04-11 | -5 | 2024-04-12 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125990903 | 032/002 | T2 DI PHILO JCT ELK 032/002 CNCL | WILLITS | ETL.7780.POLE.WDPS | 2023-04-25 | 2023-04-12 | 2024-04-16 | Late | 2024-04-11 | -5 | 2024-04-12 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125990925 | 003/095 | T2 EI COLGATE-ALLEGHANY 3/95 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507013 | T2 EI COLGATE-ALLEGHANY 3/95 RPL POLE | 70Y
LC | 125990931 | 000/009 | T2 EI PIT #1-COTTONWOOD 0/9 RMV NEST | TABLEMTN | ETL.5390.TOWR | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46037315 | T2 EI PIT #1-COTTONWOOD 0/9 RMV NEST | ICS
LC | 125990933 | 003/099 | T2 EI COLGATE-ALLEGHANY 3/99 RPL INSW | SACTO | ETL.6470.INSL.CERA | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35507014 | T2 EI COLGATE-ALLEGHANY 3/99 RPL INSW | 93I
LC | 125990964 | 032/004 | T2 EI GARBRVILE-LYTNVLE 32/4 RPR CNDW | WILLITS | ETL.8365.INSL.NCER | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46219461 | T2 EI GARBRVILE-LYTNVLE 032/004 RPR CNDW | ICW
LC | 125956327 | 016/003 | T2 FORT BRAGG-ELK 16/3 RPL IBWW | WILLITS | ETL.2060.INSL.CERA | 2023-04-20 | 2023-04-20 | 2024-03-14 | On-time | 2024-04-19 | 36 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 46089958 | T2 FORT BRAGG-ELK 16/3 RPL IBWW | ICW
LC | 125956512 | 023/364 | T2 EI KESWICK-TRINITY 23/364 RPR POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-20 | 2023-04-20 | 2024-04-18 | On-time | 2024-04-19 | 1 | 2024-04-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46026986 | T2 EI KESWICK-TRINITY 23/364 RPR POLE | ICW
LC | 125991336 | 033/507 | T2 EI CLAY-MARTEL 33/507 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2023-04-25 | 2023-04-25 | 2024-06-13 | Late | 2024-04-24 | -50 | 2024-04-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35524739 | T2 EI CLAY-MARTEL+ 031/470 RPL STRW | 70Y
LC | 125956729 | 008/066B | T2 EI CRAG VIEW-CASCADE 8/066B INS DAMW | TABLEMTN | ETL.1350.INSL.NCER | 2023-04-20 | 2023-04-20 | 2024-02-27 | On-time | 2024-04-19 | 52 | 2024-04-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 45749905 | T2 EI CRAG VIEW-CASCADE 8/066 INS DAMW | ICW
LC | 125991427 | 025/008 | T2 EI GARBERVLE-LAYTONVLE 25/08 RPR JMPW | WILLITS | ETL.8365.INSL.NCER | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46219463 | T2 EI GARBERVLE-LAYTONVLE 25/08 RPR JMPW | ICW
LC | 125957019 | 023/358 | T2 EI KESWICK-TRINITY 23/358 RPR POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-20 | 2023-04-20 | 2024-04-19 | On-time | 2024-04-19 | 0 | 2024-04-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46026985 | T2 EI KESWICK-TRINITY 23/358 RPR POLE | ICW
LC | 125957371 | A002/041 | T2 EI VALLEY SPRINGS #1 A02/041 RPL POLE | VICTOR | ETL.8210.POLE.WOOD | 2023-04-20 | 2023-04-20 | 2024-03-15 | On-time | 2024-04-19 | 35 | 2024-04-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35511449 | T2 EI VALLEY SPRINGS #1 A02/041 RPL POLE | 70Y
LC | 125991660 | 006/028 | T2 PITTSBURG-SAN MATEO 6/28 RPL INSS | CONCORD | ETL.5463.INSL.NCER | 2023-04-25 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 532 | TLN | PATR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671783 | PITTSBURG-SAN MATEO RPL INSS IN 2 TWRS. | 93K
LC | 125958326 | A002/043 | T2 EI VALLEY SPRINGS #1 A02/043 RPL POLE | VICTOR | ETL.8210.POLE.WOOD | 2023-04-20 | 2023-04-20 | 2024-03-15 | On-time | 2024-04-19 | 35 | 2024-04-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35511449 | T2 EI VALLEY SPRINGS #1 A02/041 RPL POLE | 70Y
LC | 125958501 | 001/017 | T2 NARROWS #1 TAP 1/17 GO95 CLEAR | SACTO | ETL.6511.POLE.WOOD | 2023-04-20 | 2023-04-20 | 2023-12-16 | On-time | 2024-04-19 | 125 | 2024-04-20 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31643882 | T2 NARROWS #1 TAP 1/17 GO95 CLEAR | 93G
LC | 125958524 | 000/001 | T2 WV KRCKHFF #1-KRCKHFF #2 0/1 BENT STL | FRESNO | ETL.1880.TOWR | 2023-04-20 | 2023-04-20 | 2023-05-25 | On-time | 2024-04-19 | 330 | 2024-04-20 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45770692 | T2 WV KRCKHFF #1-KRCKHFF #2 0/1 BENT STL | ICQ
LC | 125991857 | 018/002 | T2 DI PHILO JCT-ELK 018/002 COTTER | WILLITS | ETL.7780.INSL.NCER | 2023-04-25 | 2023-04-20 | 2024-05-01 | Late | 2024-04-19 | -12 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46090047 | T2 DI PHILO JCT-ELK 018/002 COTTER | ICW
LC | 125958657 | 029/205 | T2 EI TRINITY-COTTONWD 29/205L RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-20 | 2023-04-20 | 2024-03-04 | On-time | 2024-04-19 | 46 | 2024-04-20 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46027001 | T2 EI TRINITY-COTTONWD 29/205L RPR GYWW | ICS
LC | 125959551 | 009/184 | T2 VALLEY SPRINGS #1 09/184 GO95 CLEARNC | VICTOR | ETL.8210.POLE.WOOD | 2023-04-20 | 2023-04-20 | 2024-03-27 | On-time | 2024-04-19 | 23 | 2024-04-20 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31643881 | T2 VALLEY SPRINGS #1 09/184 GO95 CLEARNC | 93G
LC | 125959631 | 034/295 | T2 EI RND MTN-CTTNWD #3 34/295 RPR FOND | TABLEMTN | ETL.5650.TOWR | 2023-04-20 | 2023-04-20 | 2023-11-01 | On-time | 2024-04-19 | 170 | 2024-04-20 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46028417 | T2 EI RND MTN-CTTNWD #3 34/295 RPR FOND | ICQ
LC | 125960534 | 065/004 | T2 ELK-GUALALA 65/004 GO95 | WILLITS | ETL.8410.POLE.WOOD | 2023-04-20 | 2023-04-20 | 2024-01-29 | On-time | 2024-04-19 | 81 | 2024-04-20 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31643833 | T2 ELK-GUALALA 65/004 GO95 | 93G
LC | 125961202 | 035/298 | T2 EI RND MTN-CTTNWD #3 35/298 COTTER | TABLEMTN | ETL.5650.INSL | 2023-04-20 | 2023-04-20 | 2024-04-16 | On-time | 2024-04-19 | 3 | 2024-04-20 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46027018 | T2 EI RND MTN-CTTNWD #3 35/298 COTTER | ICS
LC | 125961459 | 020/301 | T2 EI KESWICK-TRINITY 20/301 COTTER | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-20 | 2023-04-20 | 2024-04-18 | On-time | 2024-04-19 | 1 | 2024-04-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46026982 | T2 EI KESWICK-TRINITY 20/301 COTTER | ICW
LC | 125961530 | 020/306 | T2 EI KESWICK-TRINITY 23/306 COTTER | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-20 | 2023-04-20 | 2024-04-18 | On-time | 2024-04-19 | 1 | 2024-04-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46026983 | T2 EI KESWICK-TRINITY 23/306 COTTER | ICW
LC | 125992240 | 005/007 | T2 DI LAYTONVILLE-WILLITS 005/007 COTTER | WILLITS | ETL.8360.INSL.NCER | 2023-04-25 | 2023-04-20 | 2024-07-01 | Late | 2024-04-19 | -73 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46222493 | T2 DI LAYTONVILLE-WILLITS 005/007 COTTER | ICW
LC | 125963391 | 009/003 | T2 DI MELONES-RACETRACK 009/003 RPR GYWW | VICTOR | ETL.2400.POLE.NWOD | 2023-04-20 | 2023-04-20 | 2024-02-27 | On-time | 2024-04-19 | 52 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46080900 | T2 DI MELONES-RACETRACK 009/003 RPR GYWW | ICW
LC | 125984067 | 013/105 | T2 DI TGR CK-ELEC 13/105 RPR FOND | VICTOR | ETL.5780.TOWR | 2023-04-24 | 2023-04-20 | 2023-12-04 | On-time | 2024-04-19 | 137 | 2024-04-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46018174 | T2 DI TGR CK-ELEC 13/105 RPR FOND | ICQ
LC | 125991797 | :004/030B | T2 DI ROCK CK-POE :4/30B RPR GYWS | TABLEMTN | ETL.5630.POLE.NWOD | 2023-04-25 | 2023-04-20 | 2023-12-18 | On-time | 2024-04-19 | 123 | 2024-04-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46028416 | T2 DI ROCK CK-POE :4/30B RPR GYWS | ICS
LC | 125991901 | 004/009 | T2 DI MELONES-CURTIS 4/9L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2023-04-25 | 2023-04-20 | 2024-03-17 | On-time | 2024-04-19 | 33 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46161743 | T2 DI MELONES-CURTIS 4/9L RPR STRW | ICW
LC | 125992314 | 006/001 | T2 DI LAYTONVILLE-WILLITS 006/001 COTTER | WILLITS | ETL.8360.INSL.NCER | 2023-04-25 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46222494 | T2 DI LAYTONVILLE-WILLITS 006/001 COTTER | ICW
LC | 125991902 | 004/009 | T2 DI MELONES-CURTIS 4/9R RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2023-04-25 | 2023-04-20 | 2024-03-17 | On-time | 2024-04-19 | 33 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46161744 | T2 DI MELONES-CURTIS 4/9R RPR STRW | ICW
LC | 125991906 | 149 | T2 DI MELONES-CURTIS 4/9 RPR INSW | VICTOR | ETL.2390.SWIT | 2023-04-25 | 2023-04-20 | 2024-03-17 | On-time | 2024-04-19 | 33 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46161748 | T2 DI MELONES-CURTIS 4/9 RPR INSW | ICW
LC | 125992052 | 012/059A | T2 DI FULTON PUEBLO 12/059A RPR GYWW | LAKEVLLE | ETL.1600.POLE.WOOD | 2023-04-25 | 2023-04-20 | 2023-05-02 | On-time | 2024-04-19 | 353 | 2023-07-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45745574 | T2 DI FULTON PUEBLO 12/059A RPR GYWW | ICW
LC | 125992098 | 005/002 | T2 DI LAYTONVILLE-WILLITS 05/002 RMV VEG | WILLITS | ETL.8360.POLE.WOOD | 2023-04-25 | 2023-04-20 | 2024-03-15 | On-time | 2024-04-19 | 35 | 2024-04-20 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 125992139 | 147 | T2 DI MELONES-CURTIS 04/04 RPR SWITCH | VICTOR | ETL.2390.SWIT | 2023-04-25 | 2023-04-20 | 2024-02-23 | On-time | 2024-04-19 | 56 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 46161749 | T2 DI MELONES-CURTIS 04/04 RPR SWITCH | ICW
LC | 125994071 | 082/577 | T2 EI BRDGVLLE-CTTNWD 082/577 RPR ANCW | EUREKA | ETL.1110.POLE.WDPS | 2023-04-26 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46171858 | T2 EI BRDGVLLE-CTTNWD 082/577 RPR ANCW | ICW
LC | 125994098 | 082/577 | T2 EI BRDGVLLE-CTTNWD 82/577L RPR ADSS | EUREKA | ETL.1110.POLE.WDPS | 2023-04-26 | 2023-04-26 |  | Late | 2024-04-25 |  | 2023-07-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | ADSS - Wood | Repair | 45758142 | T2 EI BRDGVLLE-CTTNWD 082/577 RPR ADSS | ICW
LC | 125994328 | 017/092 | T2 EI RND MTN-TABLE MT #1 17/92 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2023-04-26 | 2023-04-26 |  | Late | 2024-04-25 |  | 2023-10-26 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45869270 | T2 EI RND MTN-TABLE MT #1 17/92 RPR STRT | ICQ
LC | 125994439 | 082/579 | T2 EI BRDGVLE-CTNWD 082/579R RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-04-26 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172020 | T2 EI BRDGVLE-CTNWD 082/579R RPR GYWW | ICW
LC | 125994506 | 082/579 | T2 EI BRDGVLE-CTNWD 082/579L RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-04-26 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172020 | T2 EI BRDGVLE-CTNWD 082/579R RPR GYWW | ICW
LC | 125992218 | 004/004 | T2 DI MELONES-CURTIS 04/04 UNBURY | VICTOR | ETL.2390.POLE.NWOD | 2023-04-25 | 2023-04-20 | 2024-02-23 | On-time | 2024-04-19 | 56 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46161750 | T2 DI MELONES-CURTIS 04/04 UNBURY | ICW
LC | 125992274 | 002/027 | T2 DI BUCKS CRK-ROCK CRK 02/27 HANGER | TABLEMTN | ETL.4430.TOWR | 2023-04-25 | 2023-04-20 | 2024-01-15 | On-time | 2024-04-19 | 95 | 2024-04-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46028542 | T2 DI BUCKS CRK-ROCK CRK 02/27 HANGER | ICQ
LC | 125995560 | 082/576 | T2 EI BRDGVLLE-CTTNWD 082/576R RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-04-26 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171857 | T2 EI BRDGVLLE-CTTNWD 082/576R RPR GYWW | ICW
LC | 125995588 | 082/576 | T2 EI BRDGVLLE-CTTNWD 082/576L RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-04-26 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171857 | T2 EI BRDGVLLE-CTTNWD 082/576R RPR GYWW | ICW
LC | 125995770 | 041/002 | T2 EI MNDCN-WLLTS-FRT BRGG 41/2 RPR INSW | WILLITS | ETL.7550.INSL.NCER | 2023-04-26 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46214088 | T2 EI MNDCN-WLLTS-FRT BRGG 41/2 RPR INSW | ICW
LC | 125992276 | 002/027 | T2 DI BUCKS CRK-ROCK CRK 02/27 RPL INSS | TABLEMTN | ETL.4430.INSL.CERA | 2023-04-25 | 2023-04-20 | 2024-01-15 | On-time | 2024-04-19 | 95 | 2024-04-20 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672630 | T2 DI BUCKS CRK-ROCK CRK 02/27 RPL INSS | 93K
LC | 125997542 | 010/004 | T2 DI MLNES CURTIS 10/004 RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2023-04-26 | 2023-04-20 | 2024-02-21 | On-time | 2024-04-19 | 58 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46161752 | T2 DI MLNES CURTIS 10/004 RPR STRW | ICW
LC | 125996440 | 080/565 | T2 EI BRDGVLLE-CTTNWD 080/565R RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-04-26 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505101 | T2 EI BRDGVLLE-CTTNWD 080/565R RPL STRW | 70Y
LC | 125996524 | 080/565 | T2 EI BRDGVLLE-CTTNWD 080/565L RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-04-26 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505101 | T2 EI BRDGVLLE-CTTNWD 080/565R RPL STRW | 70Y
LC | 126009963 | 006/040 | T2 DI STANISLS-MNTCA #2 6/40 RPR INSS | VICTOR | ETL.3820.INSL.NCER | 2023-04-28 | 2023-04-20 | 2024-01-04 | On-time | 2024-04-19 | 106 | 2024-04-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46022546 | T2 DI STANISLS-MNTCA #2 6/40 RPR INSS | ICS
LC | 126009964 | 006/040 | T2 DI STANISLS-MNTCA #2 6/40 BNT STEEL | VICTOR | ETL.3820.TOWR | 2023-04-28 | 2023-04-20 | 2023-11-27 | On-time | 2024-04-19 | 144 | 2024-04-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46018173 | T2 DI STANISLS-MNTCA #2 6/40 BNT STEEL | ICQ
LC | 126010293 | 010/099 | T2 DI PIT#5-ROUND MTN#1 10/99 RPR STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2023-04-28 | 2023-04-20 | 2023-05-11 | On-time | 2024-04-19 | 344 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45770427 | T2 DI PIT#5-ROUND MTN#1 10/99 RPR STRW | ICW
LC | 126015156 | 011/000 | T2 DI MELONES-CURTIS 11/0 RPR GYWW | VICTOR | ETL.2390.POLE.WDPS | 2023-04-28 | 2023-04-20 | 2024-02-21 | On-time | 2024-04-19 | 58 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46161758 | T2 DI MELONES-CURTIS 11/0 RPR GYWW | ICW
LC | 126015444 | 004/006 | T2 DI MELONES-CURTIS 4/6 RPL INSW | VICTOR | ETL.2390.INSL.NCER | 2023-04-28 | 2023-04-20 | 2024-03-19 | On-time | 2024-04-19 | 31 | 2024-04-20 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35525752 | T2 DI MELONES-CURTIS 4/6 RPL INSW | 93I
LC | 126016787 | 000/001 | T2 DI COLGATE-GRS VLLY 0/1 RPR ANCW | SACTO | ETL.6490.POLE.NWOD | 2023-04-28 | 2023-04-20 | 2024-03-18 | On-time | 2024-04-19 | 32 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46031042 | T2 DI COLGATE-GRS VLLY 0/1 RPR ANCW | ICW
LC | 125999186 | 036/008 | T2 EI MNDCN-WLLTS-FRT BRGG 36/8 RPL STRW | WILLITS | ETL.7550.POLE.WOOD | 2023-04-26 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521521 | T2 EI MNDCNO-WLLTS-FRT BRGG 7/5 RPL POLE | 70Y
LC | 125999332 | 009/037 | T2 EI TESLA-METCALF 009/037 MASTIC | METCALF | ETL.6110.TOWR | 2023-04-26 | 2023-04-26 | 2024-05-09 | Late | 2024-04-25 | -14 | 2024-04-26 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46058959 | T2 EI TESLA-METCALF 009/037 MASTIC | ICQ
LC | 126017464 | 004/013 | T2 DI MELONES-RACETRACK 4/13 RPR ANCW | VICTOR | ETL.2400.POLE.WOOD | 2023-04-29 | 2023-04-20 | 2023-08-01 | On-time | 2024-04-19 | 262 | 2023-10-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45763207 | T2 DI MELONES-RACETRACK 4/13 RPR ANCW | ICW
LC | 126018428 | 014/122 | T2 DI CV-CASC 14/122R RPR SHLW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-29 | 2023-04-20 | 2024-01-26 | On-time | 2024-04-19 | 84 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 46027010 | T2 DI CV-CASC 14/122R RPR SHLW | ICW
LC | 126018429 | 014/122 | T2 DI CV-CASC 14/122C RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-29 | 2023-04-20 | 2024-01-26 | On-time | 2024-04-19 | 84 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46027011 | T2 DI CV-CASC 14/122C RPR GYWW | ICW
LC | 125999982 | 033/499 | T2 EI CLAY-MARTEL+ 033/499 RPL STRW | VICTOR | ETL.8250.POLE.WOOD | 2023-04-26 | 2023-04-26 | 2024-06-14 | Late | 2024-04-25 | -50 | 2024-04-26 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35524739 | T2 EI CLAY-MARTEL+ 031/470 RPL STRW | 70Y
LC | 126018495 | 014/122 | T2 DI CRAG VIEW-CASCADE 14/122 RPR INSW | TABLEMTN | ETL.1350.INSL.NCER | 2023-04-29 | 2023-04-20 | 2024-02-27 | On-time | 2024-04-19 | 52 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46027012 | T2 DI CRAG VIEW-CASCADE 14/122 RPR INSW | ICW
LC | 126000290 | 032/130 | T2 EI DIABLO-MIDWAY #2 32/130 RPR GYWT | PISMOBCH | ETL.5970.TOWR | 2023-04-26 | 2023-04-26 | 2024-05-21 | Late | 2024-04-25 | -26 | 2024-04-26 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46179477 | T2 EI DIABLO-MIDWAY #2 032/130 RPR GYWT | ICQ
LC | 126018788 | 029/208 | T2 DI TRNTY-CTTNWD 29/208L RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-29 | 2023-04-20 | 2024-03-06 | On-time | 2024-04-19 | 44 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46027013 | T2 DI TRNTY-CTTNWD 29/208L RPR GYWW | ICW
LC | 126029614 | 033/008 | T2 DI FRT RS GUALALA 33/008 COMPLETE | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-02 | 2023-04-20 | 2023-06-22 | On-time | 2024-04-19 | 302 | 2023-10-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45753056 | T2 DI FRT RS GUALALA 33/008 RPR ANCW | ICW
LC | 126000448 | 031/214 | T2 DI TRINITY-CTNWD 31/214L RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-26 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46027015 | T2 DI TRINITY-CTNWD 31/214L RPR GYWW | ICW
LC | 126000480 | 031/214 | T2 DI TRINITY-CTNWD 31/214C RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-26 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46027016 | T2 DI TRINITY-CTNWD 31/214C RPR GYWW | ICW
LC | 126000482 | 031/214 | T2 DI TRINITY-CTNWD 31/214R RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-26 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46027017 | T2 DI TRINITY-CTNWD 31/214R RPR GYWW | ICW
LC | 126148786 | 080/408 | T2 DI MALN-ROUND MTN #2 80/408 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-05-17 | 2023-04-20 | 2023-08-29 | On-time | 2024-04-19 | 234 | 2023-07-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45805349 | T2 DI MALN-ROUND MTN #2 80/408 RPR OPGW | ICS
LC | 126155327 | 080/409 | T2 DI MALN RND-MT #2 80/409 RPR FOND | TABLEMTN | ETL.6020.TOWR | 2023-05-17 | 2023-04-20 | 2023-11-08 | On-time | 2024-04-19 | 163 | 2024-04-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46028407 | T2 DI MALN RND-MT #2 80/409 RPR FOND | ICQ
LC | 126001704 | 034/007 | T2 EI PHILO JCT-ELK 34/007R RPL STRW | WILLITS | ETL.7780.POLE.WDPS | 2023-04-27 | 2023-04-02 |  | Late | 2024-04-01 |  | 2024-04-02 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35492687 | T2 EI PHILO JCT-ELK 34/007C RPL STRW | 70Y
LC | 126001729 | 034/007 | T2 EI PHILO JCT-ELK 34/007L RPL STRW | WILLITS | ETL.7780.POLE.WDPS | 2023-04-27 | 2023-04-02 |  | Late | 2024-04-01 |  | 2024-04-02 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35492687 | T2 EI PHILO JCT-ELK 34/007C RPL STRW | 70Y
LC | 126001755 | 007/001 | T2 DI FORT BRAGG-ELK 7/1 CANCEL | WILLITS | ETL.2060.POLE.WDPS | 2023-04-27 | 2023-04-05 |  | Late | 2024-04-04 |  | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46090128 | T2 DI FORT BRAGG-ELK 07/01 RPR ANCW | ICW
LC | 126001758 | 007/001 | T2 DI FORT BRAGG-ELK 07/01 CANCEL | WILLITS | ETL.2060.POLE.WDPS | 2023-04-27 | 2023-04-05 |  | Late | 2024-04-04 |  | 2024-04-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46090130 | T2 DI FORT BRAGG-ELK 07/01 RPR ANCW | ICW
LC | 128119973 | 008/066A | T2 EI CRAG VIEW-CASCADE 8/066A INS DAMW | TABLEMTN | ETL.1350.INSL.NCER | 2024-02-01 | 2023-04-20 | 2024-02-27 | On-time | 2024-04-19 | 52 | 2024-04-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46190524 | T2 EI CRAG VIEW-CASCADE 8/066A INS DAMW | ICW
LC | 128119976 | 008/066C | T2 EI CRAG VIEW-CASCADE 8/066C INS DAMW | TABLEMTN | ETL.1350.INSL.NCER | 2024-02-01 | 2023-04-20 | 2024-02-27 | On-time | 2024-04-19 | 52 | 2024-04-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46190526 | T2 EI CRAG VIEW-CASCADE 8/066C INS DAMW | ICW
LC | 125965459 | A002/046 | T2 EI VLLY SPRNGS #1 A002/046 RPL STRW | VICTOR | ETL.8210.POLE.WOOD | 2023-04-21 | 2023-04-21 | 2024-03-15 | On-time | 2024-04-20 | 36 | 2024-04-21 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35511449 | T2 EI VALLEY SPRINGS #1 A02/041 RPL POLE | 70Y
LC | 126002534 | A013/287-GUY | T2 EI SLNS-LRLS A013/287-GUY RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507040 | T2 DI SALINAS-LAUR A12/268-GUY RPL STRW | 70Y
LC | 126002535 | 039/007 | T2 EI MNDCN-WLLTS-FRT BRGG 39/7 RPR INSW | WILLITS | ETL.7550.INSL.NCER | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46048769 | T2 EI MNDCNO-WLLTS-FRT BRGG 39/7 RPL HRD | ICW
LC | 126002549 | 039/007 | T2 EI MNDCNO-WLTS-FRT BRGG 39/7 RPR SPLW | WILLITS | ETL.7550.INSL.NCER | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 46048768 | T2 EI MNDCNO-WLTS-FRT BRGG 39/7 RPR SPLW | ICW
LC | 126002762 | 039/005 | T2 EI MNDCN-WLLTS-FRT BRGG 39/5 RPR INSW | WILLITS | ETL.7550.INSL.NCER | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46048770 | T2 EI MNDCNO-WLLTS-FRT BRGG 39/5 RPL HRD | ICW
LC | 125965582 | 021/006 | T2 EI FULTON-HOPLAND 021/006 RPR GYWW | LAKEVLLE | ETL.6890.POLE.NWOD | 2023-04-21 | 2023-04-21 | 2023-05-25 | On-time | 2024-04-20 | 331 | 2024-04-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45571521 | T2 DI FLTN-HPLND 21/004 RPR INSW | ICW
LC | 126003737 | 083/586 | T2 EI BRIDGVLE-COTTNWD 83/586R RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505113 | T2 EI BRIDGEV-COTTONWOOD 84/592 RPL POLE | 70Y
LC | 126003867 | 083/586 | T2 EI BRIDGVLE-COTTNWD 83/586L RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505113 | T2 EI BRIDGEV-COTTONWOOD 84/592 RPL POLE | 70Y
LC | 125966945 | 082/332 | T2 EI RND MTN-TBLE MTN #2 082/3 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2023-04-21 | 2023-04-21 | 2023-11-17 | On-time | 2024-04-20 | 155 | 2024-04-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46028570 | T2 EI RND MTN-TBLE MTN #2 082/3 RPR STRT | ICQ
LC | 125967048 | A002/052 | T2 EI VLLY SPRNGS #1 A002/052 RPL STRW | VICTOR | ETL.8210.POLE.WOOD | 2023-04-21 | 2023-04-21 | 2024-03-16 | On-time | 2024-04-20 | 35 | 2024-04-21 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35511450 | T2 EI VLLY SPRNGS #1 A002/052 RPL STRW | 70Y
LC | 125967506 | 002/004 | T2 WV TRINITY-MAPLE CREEK 2/4 INS DAMW | EUREKA | ETL.8170.INSL.NCER | 2023-04-21 | 2023-04-21 | 2024-01-11 | On-time | 2024-04-20 | 100 | 2024-04-21 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46070693 | T2 WV TRINITY-MAPLE CREEK 2/4 INS DAMW | ICW
LC | 126004149 | 079/560 | T2 EI BRDGVL-CTTNWD 79/560R RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171850 | T2 EI BRDGVL-CTTNWD 079/560R RPR GYWW | ICW
LC | 126004219 | 079/560 | T2 EI BRIGDVL-CTTNWD 79/560L RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171850 | T2 EI BRDGVL-CTTNWD 079/560R RPR GYWW | ICW
LC | 126004251 | 039/001 | T2 EI MNDCNO-WLLTS-FRT BRG 39/1 WSH INSW | WILLITS | ETL.7550.INSL.NCER | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 622 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Contaminated | Insulator | Ground Wash | 46214091 | T2 EI MNDCNO-WLLTS-FRT BRG 39/1 WSH INSW | ICD
LC | 126004252 | 039/001 | T2 EI MNDCNO-WLLTS-FRT BRG 39/1 RPL HRDW | WILLITS | ETL.7550.POLE.WOOD | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46048773 | T2 EI MNDCNO-WLLTS-FRT BRG 39/1 RPL HRDW | ICW
LC | 126004261 | 039/001 | T2 EI MNDCNO-WLLTS-FRT BRGG 39/1 COTTER | WILLITS | ETL.7550.INSL.NCER | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46048771 | T2 EI MNDCNO-WLLTS-FRT BRGG 39/1 COTTER | ICW
LC | 125967827 | 003/025 | T2 WV WISHON-COPPERMINE 003/025 UNBURY | FRESNO | ETL.9330.TOWR | 2023-04-21 | 2023-04-21 | 2023-11-08 | On-time | 2024-04-20 | 164 | 2024-04-21 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46031629 | T2 WV WISHON-COPPERMINE 003/025 UNBURY | ICQ
LC | 126004338 | 004/004 | T2 EI LAYTONVILLE-COVELO 4/4 RPR GYWW | WILLITS | ETL.7390.POLE.NWOD | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46219460 | T2 EI LAYTONVILLE-COVELO 004/004 RPR GYW | ICW
LC | 125968106 | 028/001 | T2 EI GARBERVLL-LAYTONVLL 28/1 RPR ANCW | WILLITS | ETL.8365.POLE.WOOD | 2023-04-21 | 2023-04-21 | 2023-05-03 | On-time | 2024-04-20 | 353 | 2023-10-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45741224 | T2 EI GARBERVLL-LAYTONVLL 28/1 RPR ANCW | ICW
LC | 125968975 | 081/328 | T2 EI RND MTN-TBL MTN #2 81/328 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2023-04-21 | 2023-04-21 | 2023-11-17 | On-time | 2024-04-20 | 155 | 2024-04-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46028569 | T2 EI RND MTN-TBL MTN #2 81/328 RPR STRT | ICQ
LC | 126004521 | 036/000 | T2 WV RIO DELL JCT-BRDGVLE 36/0 INS DAMW | EUREKA | ETL.7850.INSL.NCER | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 46171118 | T2 WV RIO DELL JCT-BRDGVLE 36/0 INS DAMW | ICW
LC | 126004781 | 079/561 | T2 EI BRDGVLL-CTTNWD 79/561C GO95 | EUREKA | ETL.1110.POLE.WDPS | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35505111 | T2 EI BRDGVLL-CTTNWD 079/561C GO95 | 93G
LC | 125970917 | 009/180 | T2 EI VALLEY SPRINGS #1 009/180 RPL STRW | VICTOR | ETL.8210.POLE.WOOD | 2023-04-21 | 2023-04-21 | 2024-03-27 | On-time | 2024-04-20 | 24 | 2024-04-21 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35511457 | T2 EI VALLEY SPRINGS #1 009/180 RPL STRW | 70Y
LC | 126005473 | 061/260 | T2 EI RND MTN-TBL MTN #2 61/260 RPL HRDT | TABLEMTN | ETL.6070.TOWR | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | Missing | Hardware-Tower | Install | 46031695 | T2 EI RND MTN-TBL MTN #2 61/260 RPL HRDT | ICQ
LC | 125971392 | 024/377 | T2 EI KESWICK-TRINITY 024/377 RPL STRW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-21 | 2023-04-21 | 2024-04-19 | On-time | 2024-04-20 | 1 | 2024-04-21 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512896 | T2 DI KESWICK-TRINITY 21/329 RPL POLE | 70Y
LC | 125971448 | 009/177 | T2 EI VALLEY SPRINGS #1 009/177 RPR STRW | VICTOR | ETL.8210.POLE.WOOD | 2023-04-21 | 2023-04-21 | 2024-03-26 | On-time | 2024-04-20 | 25 | 2024-04-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081384 | T2 EI VALLEY SPRINGS #1 009/177 RPR STRW | ICW
LC | 125971796 | 009/188 | T2 EI VALLEY SPRINGS #1 009/188 RPR INSW | VICTOR | ETL.8210.INSL.NCER | 2023-04-21 | 2023-04-21 | 2024-03-27 | On-time | 2024-04-20 | 24 | 2024-04-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081385 | T2 EI VALLEY SPRINGS #1 009/188 RPR INSW | ICW
LC | 126005843 | 038/156 | T2 DI DIABLO MIDWAY #3 38/156 RPR GYWT | PISMOBCH | ETL.5980.TOWR | 2023-04-27 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46193874 | T2 DI DIABLO MIDWAY #3 38/156 RPR GYWT | ICQ
LC | 126005941 | 078/557 | T2 EI BRDGEVILLE-COTTNWD 78/557 RPL INSS | EUREKA | ETL.1110.INSL.CERA | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509119 | T2 DI BRDGVL-CTNWD RPL INSS 6 TWRS | 93K
LC | 125977819 | 051/000 | T2 DI ELK GUALALA 51/000 RPR ANCW | WILLITS | ETL.8410.POLE.WOOD | 2023-04-24 | 2023-04-21 | 2024-01-12 | On-time | 2024-04-20 | 99 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46079884 | T2 DI ELK GUALALA 51/000 RPR ANCW | ICW
LC | 126006258 | 009/014 | T2 EI VLY SPRGS-MRTL #1 009/014 RPL STRW | VICTOR | ETL.8240.POLE.WOOD | 2023-04-27 | 2023-04-27 | 2024-05-23 | Late | 2024-04-26 | -27 | 2024-04-27 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35510571 | T2 EI VLY SPRGS-MRTL #1 009/014 RPL STRW | 70Y
LC | 126006558 | 001/007 | T2 NRTH DUBLN-CAYTNO 01/07 RPR OPGW | CONCORD | ETL.4500.TOWR | 2023-04-27 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 628 | TLN | PATR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45999069 | T2 NRTH DUBLN-CAYTNO 01/07 RPR OPGW | ICS
LC | 126006852 | 042/173 | T2 DI DIABLO-MIDWAY #3 42/173 RPR GYWT | PISMOBCH | ETL.5980.TOWR | 2023-04-27 | 2023-04-26 | 2024-05-03 | Late | 2024-04-25 | -8 | 2024-04-26 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46232878 | T2 DI DIABLO-MIDWAY #3 42/173 RPR GYWT | ICQ
LC | 125991411 | 051/003 | T2 DI ELK GUALALA 51/003 RPL STRW | WILLITS | ETL.8410.POLE.WOOD | 2023-04-25 | 2023-04-21 | 2024-01-09 | On-time | 2024-04-20 | 102 | 2024-04-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487278 | T2 DI ELK GUALALA 51/003 RPL STRW | 70Y
LC | 126007873 | 034/003 | T2 DI FORT ROSS-GUALALA 034/003 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-04-27 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46045932 | T2 DI FORT ROSS-GUALALA 034/003 RPR INSW | ICW
LC | 125992461 | 002/027 | T2 DI NARROWS #1 TAP 002/027 COTTER | SACTO | ETL.6511.INSL.NCER | 2023-04-25 | 2023-04-21 | 2024-02-21 | On-time | 2024-04-20 | 59 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46032256 | T2 DI NARROWS #1 TAP 002/027 COTTER | ICW
LC | 126000497 | 002/018 | T2 DI ELECTRA-BELLOTA 2/18 BNT STEEL | VICTOR | ETL.4670.TOWR | 2023-04-26 | 2023-04-21 | 2024-04-19 | On-time | 2024-04-20 | 1 | 2024-04-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46048278 | T2 DI ELECTRA-BELLOTA 2/18 BNT STEEL | ICQ
LC | 126007929 | ;004/019 | T2 DI CARIBOU #2 ;004/019 RPR GYWW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-04-27 | 2023-04-21 | 2023-11-09 | On-time | 2024-04-20 | 163 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46026990 | T2 DI CARIBOU #2 ;004/019 RPR GYWW | ICW
LC | 126008015 | 034/001 | T2 DI FORT ROSS-GUALALA 034/001 RPL POLE | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-04-27 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487817 | T2 DI FORT ROSS-GUALALA 034/001 RPL POLE | 70Y
LC | 126007940 | 006/069 | T2 DI MTN GT JCT-CSCD 6/69 RPL STRW | TABLEMTN | ETL.7640.POLE.WOOD | 2023-04-27 | 2023-04-21 | 2024-02-16 | On-time | 2024-04-20 | 64 | 2024-04-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515663 | T2 DI MTN GT JCT-CSCD 6/69 RPL STRW | 70Y
LC | 126007948 | 012/052 | T2 DI MNT VST-JFFRSN#1 12/52 BNT STEEL | METCALF | ETL.5220.TOWR | 2023-04-27 | 2023-04-21 | 2024-01-08 | On-time | 2024-04-20 | 103 | 2024-04-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46058957 | T2 DI MNT VST-JFFRSN#1 12/52 BNT STEEL | ICQ
LC | 126008023 | 004/002 | T2 DI FRT BRG ELK 04/002 RPL INSW | WILLITS | ETL.2060.INSL.CERA | 2023-04-27 | 2023-04-21 | 2024-04-15 | On-time | 2024-04-20 | 5 | 2024-04-21 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35487301 | T2 DI FRT BRG ELK 04/002 RPL INSW | 93I
LC | 126008382 | 010/004 | T2 DI LAYTONVILLE-WILLITS 10/04 COTTER | WILLITS | ETL.8360.INSL.NCER | 2023-04-27 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45747821 | T2 DI LAYTONVILLE-WILLITS 10/04 COTTER | ICW
LC | 126008142 | :000/003 | T2 DI CARIBOUT#2 :0/3 RPR INSW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-04-27 | 2023-04-21 | 2023-11-27 | On-time | 2024-04-20 | 145 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46026988 | T2 DI CARIBOUT#2 :0/3 RPR INSW | ICW
LC | 126008501 | 003/001 | T2 DI MELONES-CURTIS 003/001R RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2023-04-27 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35522964 | T2 DI MELONES-CURTIS 003/001R RPL STRW | 70Y
LC | 126008503 | 003/001 | T2 DI MELONES-CURTIS 003/001L RPL STRW | VICTOR | ETL.2390.POLE.WDPS | 2023-04-27 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35522964 | T2 DI MELONES-CURTIS 003/001R RPL STRW | 70Y
LC | 126008520 | 033/003 | T2 DI FORT ROSS-GUALALA 33/03 COTTER | LAKEVLLE | ETL.6980.INSL.NCER | 2023-04-27 | 2023-04-21 | 2024-06-14 | Late | 2024-04-20 | -55 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46045930 | T2 DI FORT ROSS-GUALALA 33/03 COTTER | ICW
LC | 126010014 | 003/002 | T2 DI MELONES-CURTIS 003/002 RPR GYWW | VICTOR | ETL.2390.POLE.WDPS | 2023-04-28 | 2023-04-21 | 2024-03-18 | On-time | 2024-04-20 | 33 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46161754 | T2 DI MELONES-CURTIS 003/002 RPR GYWW | ICW
LC | 126010473 | 051/005 | T2 DI ELK-GUALALA 51/5 RPR INSW | WILLITS | ETL.8410.INSL.NCER | 2023-04-28 | 2023-04-21 | 2024-01-09 | On-time | 2024-04-20 | 102 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079885 | T2 DI ELK-GUALALA 51/5 RPR INSW | ICW
LC | 126009913 | 001/030 | T2 DI JEFFERSON-STANFORD 1/30 COMPLETE | METCALF | ETL.7220.POLE.WOOD | 2023-04-28 | 2023-04-21 | 2024-05-23 | Late | 2024-04-20 | -33 | 2024-04-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507602 | T2 DI JEFFERSON-STANFORD 1/30 RPL STRW | 70Y
LC | 126010475 | 051/005 | T2 DI ELK-GUALALA 51/5 RPR GYWW | WILLITS | ETL.8410.POLE.WOOD | 2023-04-28 | 2023-04-21 | 2024-01-09 | On-time | 2024-04-20 | 102 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079886 | T2 DI ELK-GUALALA 51/5 RPR GYWW | ICW
LC | 126009962 | 006/040 | T2 DI STANISLS-MNTCA #2 6/40 UNBURY | VICTOR | ETL.3820.TOWR | 2023-04-28 | 2023-04-20 | 2024-06-07 | Late | 2024-04-19 | -49 | 2024-04-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46134779 | T2NT DI STANISLS-MNTCA #2 6/40 UNBURY | ICQ
LC | 126010560 | 051/005 | T2 DI ELK-GUALALA 51/5 RPR ANCW | WILLITS | ETL.8410.POLE.WOOD | 2023-04-28 | 2023-04-21 | 2024-01-09 | On-time | 2024-04-20 | 102 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46079887 | T2 DI ELK-GUALALA 51/5 RPR ANCW | ICW
LC | 126010569 | 019/210 | T2 DI ELK CREEK TAP 19/210 RPR GYWW | TABLEMTN | ETL.6921.POLE.NWOD | 2023-04-28 | 2023-04-21 | 2023-11-06 | On-time | 2024-04-20 | 166 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999228 | T2 DI ELK CREEK TAP 19/210 RPR GYWW | ICW
LC | 126010760 | 006/114 | T2 DI COLGATE-PALERMO 6/114 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2023-04-28 | 2023-04-21 | 2024-04-18 | On-time | 2024-04-20 | 2 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46030919 | T2 DI COLGATE-PALERMO 6/114 RPR STRW | ICW
LC | 126010025 | 009/110 | T2 DI WST PNT-VLY SPR 9/110 RPL POLE | VICTOR | ETL.8350.POLE.WOOD | 2023-04-28 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525536 | T2 DI WST PNT-VLY SPR 9/110 RPL POLE | 70Y
LC | 126010803 | A007/087 | T2 DI PALERMO-OROVILLE #2 A07/087 UNBURY | TABLEMTN | ETL.7740.POLE.NWOD | 2023-04-28 | 2023-04-21 | 2023-08-03 | On-time | 2024-04-20 | 261 | 2023-10-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45770978 | T2 DI PALERMO-OROVILLE #2 A07/087 UNBURY | ICW
LC | 126011310 | 000/008 | T2 DI COLEM- RED BLF 0/8 RPR WDPKR | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-28 | 2023-04-21 | 2024-03-05 | On-time | 2024-04-20 | 46 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46026991 | T2 DI COLEM- RED BLF 0/8 RPR WDPKR | ICW
LC | 126011634 | 003/029 | T2 DI BCKS CRK-ROCK CRK-03/29 RPR STRT | TABLEMTN | ETL.4430.TOWR | 2023-04-28 | 2023-04-21 | 2023-11-02 | On-time | 2024-04-20 | 170 | 2024-04-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46025858 | T2 DI BCKS CRK-ROCK CRK-03/29 RPR STRT | ICQ
LC | 126011950 | 001/043 | T2 DI JEFFERSON-STANFORD 1/43 RPR GYWW | METCALF | ETL.7220.POLE.WOOD | 2023-04-28 | 2023-04-21 | 2024-04-03 | On-time | 2024-04-20 | 17 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46080478 | T2 DI JEFFERSON-STANFORD 1/43 RPR GYWW | ICW
LC | 126012413 | 002/025 | T2 DI NARROWS #2 TAP 02/25 COTTER | SACTO | ETL.6521.INSL.CERA | 2023-04-28 | 2023-04-21 | 2024-02-21 | On-time | 2024-04-20 | 59 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46032422 | T2 DI NARROWS #2 TAP 02/25 COTTER | ICW
LC | 126012553 | 020/008 | T2 DI FORT BRAGG-ELK 20/8 RPR INSW | WILLITS | ETL.2060.INSL.NCER | 2023-04-28 | 2023-04-21 | 2024-03-11 | On-time | 2024-04-20 | 40 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46090137 | T2 DI FORT BRAGG-ELK 20/8 RPR INSW | ICW
LC | 126013754 | 001/044 | T2 DI JEFF-STNFD 1/44 RPL HRDW | METCALF | ETL.7220.POLE.WOOD | 2023-04-28 | 2023-04-21 | 2024-04-01 | On-time | 2024-04-20 | 19 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46080479 | T2 DI JEFF-STNFD 1/44 RPL HRDW | ICW
LC | 126014954 | 007/030 | T2 DI MNT-VST-JFFRSN #1 7/030 RPL INSS | METCALF | ETL.5220.INSL.NCER | 2023-04-28 | 2023-04-21 | 2024-01-05 | On-time | 2024-04-20 | 106 | 2024-04-21 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674005 | T2 DI MNT-VST-JFFRSN #1 RPL INSS IN 2 TW | 93K
LC | 126015065 | 019/212 | T2 DI ELK CREEK TAP 19/212 RPR JUMW | TABLEMTN | ETL.6921.INSL.NCER | 2023-04-28 | 2023-04-21 | 2023-12-12 | On-time | 2024-04-20 | 130 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45999229 | T2 DI ELK CREEK TAP 19/212 RPR JUMW | ICW
LC | 126017166 | 056/012 | T2 DI ELK-GUALALA 56/12 RPL STRW | WILLITS | ETL.8410.POLE.WOOD | 2023-04-29 | 2023-04-21 | 2024-01-23 | On-time | 2024-04-20 | 88 | 2024-04-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487383 | T2 DI ELK-GUALALA 057/006 RPL STRW | 70Y
LC | 126017174 | 007/004 | T2 DI MELONES-CURTIS 007/004L RPL XBRACE | VICTOR | ETL.2390.POLE.WDPS | 2023-04-29 | 2023-04-21 | 2023-10-06 | On-time | 2024-04-20 | 197 | 2024-04-21 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31670905 | T2 DI MELONES-CURTIS 007/004L RPL XBRACE | 93E
LC | 126017531 | 051/001 | T2 DI ELK GUALALA 51/01 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-04-29 | 2023-04-21 | 2024-01-11 | On-time | 2024-04-20 | 100 | 2024-04-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487277 | T2 DI ELK GUALALA 51/01 RPL POLE | 70Y
LC | 126017763 | 014/005 | T2 DI CARIBOU-PLMS JCT 14/5 RMV VEG | TABLEMTN | ETL.6290.POLE.WOOD | 2023-04-29 | 2023-04-21 | 2024-03-06 | On-time | 2024-04-20 | 45 | 2024-04-21 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126018074 | 018/003 | T2 DI FORT BRAGG-ELK 18/3 UNBURY | WILLITS | ETL.2060.POLE.WOOD | 2023-04-29 | 2023-04-21 | 2024-02-28 | On-time | 2024-04-20 | 52 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46090346 | T2 DI FORT BRAGG-ELK 18/3 UNBURY | ICW
LC | 126019629 | 009/000 | T2 DI FORT BRAGG-ELK 9/0 RPL INSW | WILLITS | ETL.2060.INSL.CERA | 2023-04-29 | 2023-04-21 | 2024-02-25 | On-time | 2024-04-20 | 55 | 2024-04-21 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35487734 | T2 DI FORT BRAGG-ELK 9/0 RPL INSW | 93I
LC | 126037917 | 021/105 | T2 DI FULTON-IGNACIO #1 21/105 RPL INSS | LAKEVLLE | ETL.4680.INSL | 2023-05-03 | 2023-04-21 | 2023-11-27 | On-time | 2024-04-20 | 145 | 2024-04-21 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510350 | T2 DI FULTON-IGNACIO #1 21/105 RPL INSS | 93K
LC | 126010977 | 004/008 | T2 DI LAKEVLL #1 4/8 RPR POLE | LAKEVLLE | ETL.7360.POLE.WOOD | 2023-04-28 | 2023-04-24 | 2024-05-09 | Late | 2024-04-23 | -16 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46031752 | T2 DI LAKEVLL #1 4/8 RPR POLE | ICW
LC | 126011014 | 004/008 | T2 DI LAKEVLL #1 4/8 COTTER | LAKEVLLE | ETL.7360.POLE.WOOD | 2023-04-28 | 2023-04-24 | 2024-05-09 | Late | 2024-04-23 | -16 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46031742 | T2 DI LAKEVLL #1 4/8 COTTER | ICW
LC | 126011108 | 002/028 | T2 DI NARROWS #1 TAP 002/028 RPR STRW | SACTO | ETL.6511.POLE.WOOD | 2023-04-28 | 2023-04-21 | 2024-05-10 | Late | 2024-04-20 | -20 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46032258 | T2 DI NARROWS #1 TAP 002/028 RPR STRW | ICW
LC | 126011200 | 002/028 | T2 DI NARROWS #1 TAP 002/028 RPR INSW | SACTO | ETL.6511.INSL.NCER | 2023-04-28 | 2023-04-21 | 2024-05-10 | Late | 2024-04-20 | -20 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46032259 | T2 DI NARROWS #1 TAP 002/028 RPR INSW | ICW
LC | 125972718 | 009/187 | T2 EI VALLEY SPRINGS #1 009/187 RPR INSW | VICTOR | ETL.8210.INSL.NCER | 2023-04-22 | 2023-04-22 | 2024-03-27 | On-time | 2024-04-21 | 25 | 2024-04-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46161635 | T2 EI VALLEY SPRINGS #1 009/187 RPR INSW | ICW
LC | 125972953 | 012/087 | T2 EI GREEN VALLEY-LLAGS 12/87R RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2023-04-22 | 2023-04-22 | 2024-04-09 | On-time | 2024-04-21 | 12 | 2024-04-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35507495 | T2 EI GREEN VALLEY-LLAGS 12/87R RPL POLE | 70Y
LC | 125972954 | 012/087 | T2 EI GREEN VALLEY-LLAGS 12/87C RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2023-04-22 | 2023-04-22 | 2024-04-09 | On-time | 2024-04-21 | 12 | 2024-04-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35507495 | T2 EI GREEN VALLEY-LLAGS 12/87R RPL POLE | 70Y
LC | 125973300 | 030/447 | T2 EI CLAY-MARTEL+ 030/447 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2023-04-22 | 2023-04-22 | 2024-02-27 | On-time | 2024-04-21 | 54 | 2024-04-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46025799 | T2 EI CLAY-MARTEL+ 030/447 RPR STRW | ICW
LC | 126011567 | 016/325 | T2 EI CARIBOU-WESTWOOD 16/325 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2023-04-28 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519122 | T2 EI CARIBOU-WESTWOOD 16/325 RPL POLE | 70Y
LC | 125973308 | 024/378 | T2 EI KESWICK-TRINITY 024/378 RPL HRDD | TABLEMTN | ETL.7270.INSL | 2023-04-22 | 2023-04-22 | 2024-04-20 | On-time | 2024-04-21 | 1 | 2024-04-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46026999 | T2 EI KESWICK-TRINITY 024/378 RPL HRDD | ICW
LC | 125973362 | 034/008 | T2 EI MNDCNO-WLLTS-FRT BRG 34/8 RPR GYWW | WILLITS | ETL.7550.POLE.NWOD | 2023-04-22 | 2023-04-22 | 2024-04-08 | On-time | 2024-04-21 | 13 | 2024-04-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46214052 | T2 EI MNDCNO-WLLTS-FRT BRG 34/8 RPR GYWW | ICW
LC | 125974637 | 001/026 | T2 EI APPLE HILL #1 TAP 1/26 RPR GYWW | SACTO | ETL.1531.POLE.NWOD | 2023-04-22 | 2023-04-22 | 2024-01-12 | On-time | 2024-04-21 | 100 | 2024-04-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46032248 | T2 EI APPLE HILL #1 TAP 1/26 RPR GYWW | ICW
LC | 126011691 | 005/007 | T2 EI VLLY SPRINGS-MRTL #1 5/7 RPR GYWW | VICTOR | ETL.8240.POLE.NWOD | 2023-04-28 | 2023-04-28 | 2024-05-22 | Late | 2024-04-27 | -25 | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46080909 | T2 EI VLLY SPRINGS-MRTL #1 5/7 RPR GYWW | ICW
LC | 126011731 | :000/004 | T2 DI CARIBOU #2 :000/004 INS HRDD | TABLEMTN | ETL.6280.POLE.WOOD | 2023-04-28 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Missing | Hardware-Wood | Install | 46036992 | T2 DI CARIBOU #2 :000/004 INS HRDD | ICW
LC | 125974983 | 030/457 | T2 EI CLAY-MARTEL+ 030/457 RPR GYWW | VICTOR | ETL.8250.POLE.NWOD | 2023-04-22 | 2023-04-22 | 2023-11-27 | On-time | 2024-04-21 | 146 | 2024-04-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46025920 | T2 EI CLAY-MARTEL+ 030/457 RPR GYWW | ICW
LC | 126011915 | 032/005 | T2 DI FORT ROSS-GUALALA 32/05 COTTER | LAKEVLLE | ETL.6980.INSL.NCER | 2023-04-28 | 2023-04-21 | 2024-06-12 | Late | 2024-04-20 | -53 | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46045928 | T2 DI FORT ROSS-GUALALA 32/05 COTTER | ICW
LC | 125975150 | 030/003 | T2 EI GARBERVILL-LAYTONVLL 30/3 RPR ANCW | WILLITS | ETL.8365.POLE.WOOD | 2023-04-22 | 2023-04-22 | 2023-05-05 | On-time | 2024-04-21 | 352 | 2023-10-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45741222 | T2 EI GARBERVILL-LAYTONVLL 30/3 RPR ANCW | ICW
LC | 125975381 | 018/255 | T2 EI KESWICK-TRINITY 18/255 RPR CNDW | TABLEMTN | ETL.7270.INSL.NCER | 2023-04-22 | 2023-04-22 | 2024-04-16 | On-time | 2024-04-21 | 5 | 2024-04-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46036994 | T2 EI KESWICK-TRINITY 18/255 RPR CNDW | ICW
LC | 125975382 | 018/253 | T2 EI KESWICK-TRINITY 18/253 RPR STRW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-04-22 | 2023-04-22 | 2024-04-17 | On-time | 2024-04-21 | 4 | 2024-04-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46026997 | T2 EI KESWICK-TRINITY 18/253 RPR STRW | ICW
LC | 126012062 | 078/553 | T2 EI BRDGVLLE CTTNWD 78/553 RPL ANCT | EUREKA | ETL.1110.POLE.STPS | 2023-04-28 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 93Z | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Tower | Replace | 31680988 | T2 EI BRDGVLLE CTTNWD 78/553 RPL ANCS | 93Z
LC | 126012063 | 041/008 | T2 EI MNDCNO-WLTS-FRT BRG 41/08 RPR SPLW | WILLITS | ETL.7550.INSL.NCER | 2023-04-28 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46214094 | T2 EI MNDCNO-WLTS-FRT BRG 41/08 RPR SPLW | ICW
LC | 126012152 | 036/000 | T2 DI FRT RSS-GUALALA-GL 36/0 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-04-28 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487817 | T2 DI FORT ROSS-GUALALA 034/001 RPL POLE | 70Y
LC | 126012245 | 002/044 | T2 DI COLEMAN-RD BLFF 2/44 GO95 | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-28 | 2023-04-24 | 2024-05-23 | Late | 2024-04-23 | -30 | 2024-04-24 | 401T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35513214 | T2 DI COLMAN-RED BLUFF 2/40 GO95 | 93G
LC | 125975390 | 018/251 | T2 EI KESWICK-TRINITY 18/251 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-22 | 2023-04-22 | 2024-04-16 | On-time | 2024-04-21 | 5 | 2024-04-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46026996 | T2 EI KESWICK-TRINITY 18/251 RPR GYWW | ICW
LC | 126488399 | 012/087 | T2 EI GREEN VALLEY-LLAGS 12/87L RPL POLE | MOSSLNDG | ETL.1720.POLE.WDPS | 2023-06-30 | 2023-04-22 | 2024-04-09 | On-time | 2024-04-21 | 12 | 2024-04-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35507495 | T2 EI GREEN VALLEY-LLAGS 12/87R RPL POLE | 70Y
LC | 125978817 | 031/468 | T2 EI CLAY-MARTEL 31/468 COTTER | VICTOR | ETL.8250.INSL.NCER | 2023-04-24 | 2023-04-24 | 2023-06-30 | On-time | 2024-04-23 | 298 | 2023-07-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45762959 | T2 EI CLAY-MARTEL+ 031/468 COTTER | ICW
LC | 125978932 | 022/085 | T2 EI EXCHEQUER-INDN FLT 22/85 BNT STEEL | FRESNO | ETL.8650.TOWR | 2023-04-24 | 2023-04-24 | 2023-12-13 | On-time | 2024-04-23 | 132 | 2024-04-24 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45763391 | T2 EI EXCHEQUER-INDN FLT 22/85 BNT STEEL | ICQ
LC | 125979067 | 001/016 | T2 EI CRAG VIEW-CASCADE 01/016 RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-24 | 2023-04-24 | 2023-08-08 | On-time | 2024-04-23 | 259 | 2023-10-24 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45758185 | T2 EI CRAG VIEW-CASCADE 01/016 RPR GYWW | ICS
LC | 125979713 | 001/016 | T2 EI CRAG VIEW-CASCADE 01/016 RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-24 | 2023-04-24 | 2023-08-10 | On-time | 2024-04-23 | 257 | 2023-10-24 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45758182 | T2 EI CRAG VIEW-CASCADE 01/016 RPR GYWW | ICS
LC | 126013164 | 063/263 | T2 WV RND MTN-TBL MTN #2 63/263 INS DMPS | TABLEMTN | ETL.6070.INSL.NCER | 2023-04-28 | 2023-04-28 | 2024-05-03 | Late | 2024-04-27 | -6 | 2024-04-28 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46037402 | T2 WV RND MTN-TBL MTN #2 63/263 INS DMPS | ICW
LC | 126013171 | 033/225 | T2 EI TRINITY-COTTONWOOD 33/225 RPR INSW | TABLEMTN | ETL.4040.INSL.CERA | 2023-04-28 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46239922 | T2 EI TRINITY-COTTONWOOD 33/225 RPR INSW | ICW
LC | 125980357 | 010/053 | T2 EI RND MTN-TABLE MN #1 10/53 RPR OPGW | TABLEMTN | ETL.6060.TOWR | 2023-04-24 | 2023-04-24 | 2023-11-17 | On-time | 2024-04-23 | 158 | 2024-04-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46037403 | T2 EI RND MTN-TABLE MN #1 10/53 RPR OPGW | ICS
LC | 126013304 | 018/094 | T2 DI FULT-IGCIO #1 18/94 RPL INSS | LAKEVLLE | ETL.4680.INSL | 2023-04-28 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31678225 | T2 DI FULTON-IGNCIO #1 RPL INSS IN 5 TWR | 93K
LC | 125981319 | 018/256 | T2 EI KESWICK-TRINITY 18/256 RPR STRW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-04-24 | 2023-04-24 | 2024-04-16 | On-time | 2024-04-23 | 7 | 2024-04-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46037265 | T2 EI KESWICK-TRINITY 18/256 RPR STRW | ICW
LC | 125981942 | 018/404 | T2 WV VOLTA-DESCHUTES 18/404 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-04-24 | 2023-04-24 | 2024-02-06 | On-time | 2024-04-23 | 77 | 2024-04-24 | 372 | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31645822 | T2 WV VOLTA-DESCHUTES 18/404 RPL POLE | 70Y
LC | 125982510 | 018/409 | T2 WV VOLTA-DESCHUTES 18/409 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-04-24 | 2023-04-24 | 2024-04-15 | On-time | 2024-04-23 | 8 | 2024-04-24 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485605 | T2 DI VLTA DSHUTS 16/343 RPL STRW | 70Y
LC | 125982594 | 59 | T2 EI EXCHEQUER-INDIN FLT 21/80 RPL HRWS | FRESNO | ETL.8650.SWIT | 2023-04-24 | 2023-04-24 | 2023-12-11 | On-time | 2024-04-23 | 134 | 2024-04-24 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Steel | Replace | 45954706 | T2 EI EXCHEQUER-INDIN FLT 21/80 RPL HRWS | ICS
LC | 125982595 | 014/047 | T2 EI EXCHEQUR-INDN FLT 14/47 UNBURY | FRESNO | ETL.8650.TOWR | 2023-04-24 | 2023-04-24 | 2023-12-07 | On-time | 2024-04-23 | 138 | 2024-04-24 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46031625 | T2 EI EXCHEQUR-INDN FLT 14/47 UNBURY | ICQ
LC | 125983281 | 056/240 | T2 EI RND MTN-TBL MTN #1 56/240 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2023-04-24 | 2023-04-24 | 2023-12-05 | On-time | 2024-04-23 | 140 | 2024-04-24 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46031686 | T2 EI RND MTN-TBL MTN #1 56/240 RPR STRT | ICQ
LC | 126013852 | 035/007 | T2 DI FORT ROSS-GUALALA 35/07 RPL INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-04-28 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 508 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31677268 | T2 DI FORT ROSS-GUALALA 35/07 RPL INSW | 93I
LC | 126013856 | 001/026 | T2 DI COLEMAN-RED BLUFF 1/26 RPR CNDW | TABLEMTN | ETL.6440.INSL.CERA | 2023-04-28 | 2023-04-24 | 2024-05-20 | Late | 2024-04-23 | -27 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46029288 | T2 DI COLEMAN-RED BLUFF 1/26 RPR CNDW | ICW
LC | 126009934 | ;004/026 | T2 DI CARIBOU #2 ;4/26 RPR POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2023-04-28 | 2023-04-24 | 2023-11-10 | On-time | 2024-04-23 | 165 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46037161 | T2 DI CARIBOU #2 ;4/26 RPR POLE | ICW
LC | 126010097 | 005/101 | T2 DI COLEMAN-RED BLUFF 05/101 RPL STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-28 | 2023-04-24 | 2024-03-18 | On-time | 2024-04-23 | 36 | 2024-04-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35500379 | T2 COLEMAN-RD BLFF 4/80 RPL POLE | 70Y
LC | 126014083 | 000/009 | T2 DI PIT #7 TAP 000/009 RPR SHIELD | TABLEMTN | ETL.5442.POLE.STPS | 2023-04-28 | 2023-04-25 |  | Late | 2024-04-24 |  | 2023-07-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Shield Wire - Wood | Repair | 46037384 | T2 DI PIT #7 TAP 000/009 RPR SHIELD | ICW
LC | 126010240 | 005/096 | T2 DI COLEMAN-RED BLUFF 5/96 RPR SPLW | TABLEMTN | ETL.6440.INSL | 2023-04-28 | 2023-04-24 | 2024-03-20 | On-time | 2024-04-23 | 34 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46036836 | T2 DI COLEMAN-RED BLUFF 5/96 RPR SPLW | ICW
LC | 126014186 | 010/244 | T2 EI SANTA ROSA-CORONA 10/244 RPR GYWW | LAKEVLLE | ETL.4309.POLE.WOOD | 2023-04-28 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46204133 | T2 EI SANTA ROSA-CORONA 10/244 RPR GYWW | ICW
LC | 126010525 | :005/033 | T2 DI ROCK CREEK-POE :5/33 RPLC INSS | TABLEMTN | ETL.5630.INSL.CERA | 2023-04-28 | 2023-04-24 | 2024-02-27 | On-time | 2024-04-23 | 56 | 2024-04-24 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509199 | T2 DI ROCK CREEK-POE :5/33 RPLC INSS | 93K
LC | 126010651 | A014/226 | T2 DI COLMAN-RED BLUF A14/226 RPR STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-28 | 2023-04-24 | 2024-03-07 | On-time | 2024-04-23 | 47 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46029297 | T2 DI COLMAN-RED BLUF A14/226 RPR STRW | ICW
LC | 126010779 | A016/241 | T2 DI CLMN-RD BLF A016/241 RPR GYWW | TABLEMTN | ETL.6440.POLE.NWOD | 2023-04-28 | 2023-04-24 | 2024-03-05 | On-time | 2024-04-23 | 49 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46029299 | T2 DI CLMN-RD BLF A016/241 RPR GYWW | ICW
LC | 126014299 | 007/133 | T2 DI COLEMAN-RED BLUFF 07/133L RPR GYWW | TABLEMTN | ETL.6440.POLE.WDPS | 2023-04-28 | 2023-04-25 | 2024-05-23 | Late | 2024-04-24 | -29 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46029344 | T2 DI COLEMAN-RED BLUFF 07/133L RPR GYWW | ICW
LC | 126014303 | 008/142 | T2 DI COLEMAN-RED BLUFF 008/142 RPL POLE | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-28 | 2023-04-25 | 2024-05-21 | Late | 2024-04-24 | -27 | 2024-04-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501123 | T2 DI COLEMAN-RED BLUFF 008/139 RPL POLE | 70Y
LC | 126010976 | 004/008 | T2 DI LAKEVLL #1 4/8 RPR ANCW | LAKEVLLE | ETL.7360.POLE.WOOD | 2023-04-28 | 2023-04-24 | 2023-06-20 | On-time | 2024-04-23 | 308 | 2023-10-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45770996 | T2 DI LAKEVLL #1 4/8 RPR ANCW | ICW
LC | 126014413 | 007/133 | T2 DI COLEMAN-RED BLUFF 07/133R RPR GYWW | TABLEMTN | ETL.6440.POLE.WDPS | 2023-04-28 | 2023-04-25 | 2024-05-23 | Late | 2024-04-24 | -29 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46029342 | T2 DI COLEMAN-RED BLUFF 07/133R RPR GYWW | ICW
LC | 126014435 | 073/528 | T2 EI BRDGVLLE CTTNWD 73/528 RPR ADSS | EUREKA | ETL.1110.POLE.WDPS | 2023-04-28 | 2023-04-28 |  | Late | 2024-04-27 |  | 2023-10-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | ADSS - Wood | Repair | 46092993 | T2 EI BRDGVLLE CTTNWD 73/528 RPL HRDW | ICW
LC | 126014462 | 007/133 | T2 DI COLEMAN-RED BLUFF 07/133C RPL HRDW | TABLEMTN | ETL.6440.POLE.WDPS | 2023-04-28 | 2023-04-25 | 2024-05-23 | Late | 2024-04-24 | -29 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46029343 | T2 DI COLEMAN-RED BLUFF 07/133C RPL HRDW | ICW
LC | 126014502 | 006/129 | T2 WV COLEMAN-SOUTH 006/129 RPR SPLW | TABLEMTN | ETL.6450.INSL.NCER | 2023-04-28 | 2023-04-28 | 2024-05-03 | Late | 2024-04-27 | -6 | 2024-04-28 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46036838 | T2 WV COLEMAN-SOUTH 006/129 RPR SPLW | ICW
LC | 126011822 | 001/029 | T2 DI CLMN-RED BLUFF 001/029 RPL HRDD | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-28 | 2023-04-24 | 2024-03-26 | On-time | 2024-04-23 | 28 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46029289 | T2 DI CLMN-RED BLUFF 001/029 RPL HRDD | ICW
LC | 126014667 | 001/016 | T2 DI CLMN-RED BLUFF 001/016 RPL HRDD | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-28 | 2023-04-24 | 2024-05-23 | Late | 2024-04-23 | -30 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46029285 | T2 DI CLMN-RED BLUFF 001/016 RPL HRDD | ICW
LC | 126014754 | 001/016 | T2 DI CLMN-RED BLUFF 001/016 RPR INSW | TABLEMTN | ETL.6440.INSL | 2023-04-28 | 2023-04-24 | 2024-05-23 | Late | 2024-04-23 | -30 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46029286 | T2 DI CLMN-RED BLUFF 001/016 RPR INSW | ICW
LC | 126012771 | A014/230 | T2 DI COLM- RD BLF A14/230 RPR INSW | TABLEMTN | ETL.6440.INSL.NCER | 2023-04-28 | 2023-04-24 | 2024-04-03 | On-time | 2024-04-23 | 20 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46029298 | T2 DI COLM- RD BLF A14/230 RPR INSW | ICW
LC | 126012826 | 082/419C | T2 DI MLN-RND MTN #2 82/419C RPR FOND | TABLEMTN | ETL.6020.TOWR | 2023-04-28 | 2023-04-24 | 2023-10-25 | On-time | 2024-04-23 | 181 | 2024-04-24 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46030990 | T2 DI MLN-RND MTN #2 82/419C RPR FOND | ICQ
LC | 126014832 | 032/011 | T2 DI FORT ROSS-GUALALA 32/11 RPL INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-04-28 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35487816 | T2 DI FORT ROSS-GUALALA 32/11 RPL INSW | 93I
LC | 126013173 | 005/087 | T2 DI COLEMAN-RED BLUFF 5/87 RPLC STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-28 | 2023-04-24 | 2024-03-18 | On-time | 2024-04-23 | 36 | 2024-04-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35500379 | T2 COLEMAN-RD BLFF 4/80 RPL POLE | 70Y
LC | 126013956 | 005/102 | T2 DI COLEMAN-RED BLUFF 5/102 RPL INSW | TABLEMTN | ETL.6440.INSL.CERA | 2023-04-28 | 2023-04-24 | 2024-03-20 | On-time | 2024-04-23 | 34 | 2024-04-24 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35501121 | T2 DI COLEMAN-RED BLUFF 5/95 RPL INSW | 93I
LC | 126014510 | 001/031 | T2 DI CLMN-RED BLUFF 001/031 RPR CNDW | TABLEMTN | ETL.6440.INSL.NCER | 2023-04-28 | 2023-04-24 | 2024-03-26 | On-time | 2024-04-23 | 28 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46029290 | T2 DI CLMN-RED BLUFF 001/031 RPR CNDW | ICW
LC | 126014988 | 000/007 | T2 DI MENDO-HARTLEY 00/07 RPL STRW | WILLITS | ETL.7510.POLE.WOOD | 2023-04-28 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35488482 | T2 DI MENDO-HARTLEY 00/07 RPL STRW | 70Y
LC | 126015247 | 001/028 | T2 DI CLMN-RED BLUFF 001/028 REFRAME | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-28 | 2023-04-24 | 2024-03-11 | On-time | 2024-04-23 | 43 | 2024-04-24 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35500377 | T2 DI CLMN-RED BLUFF 001/028 REFRAME | 93E
LC | 126016566 | 004/075 | T2 DI COLEMAN-RED BLUFF 4/75 RPR INSW | TABLEMTN | ETL.6440.INSL | 2023-04-28 | 2023-04-24 | 2024-03-20 | On-time | 2024-04-23 | 34 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46029294 | T2 DI COLEMAN-RED BLUFF 4/75 RPR INSW | ICW
LC | 126015218 | 000/005 | T2 DI COLE- RD BLF 0/5 RPR GYWW | TABLEMTN | ETL.6440.POLE.NWOD | 2023-04-28 | 2023-04-24 | 2024-05-20 | Late | 2024-04-23 | -27 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46029282 | T2 DI COLE- RD BLF 0/5 RPR GYWW | ICW
LC | 126015239 | 072/525 | T2 EI BRDGVLLE-CTTNWD 72/525 RPR STRW | EUREKA | ETL.1110.POLE.STPS | 2023-04-28 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45864903 | T2 EI BRDGVLLE-CTTNWD 72/525 RPR STRW | ICW
LC | 126016685 | 006/074 | T2 DI MTN GT JCT-CSCD 6/74 RPR INSW | TABLEMTN | ETL.7640.INSL.CERA | 2023-04-28 | 2023-04-24 | 2023-08-20 | On-time | 2024-04-23 | 247 | 2023-10-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45749919 | T2 DI MTN GT JCT-CSCD 6/74 RPR INSW | ICW
LC | 126015248 | ;004/018 | T2 DI CARIBOU#2 ;4/18 RPL HRDD | TABLEMTN | ETL.6280.POLE.WOOD | 2023-04-28 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46037160 | T2 DI CARIBOU#2 ;4/18 RPL HRDD | ICW
LC | 126015304 | 037/005 | T2 DI FORT RSS-GUALALA 37/5 RPL INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-04-28 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35487980 | T2 DI FORT RSS-GUALALA 37/5 RPL INSW | 93I
LC | 126017881 | 000/007 | T2 DI CLMN-RED BLUFF 000/007 RPL HRDD | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-29 | 2023-04-24 | 2024-03-05 | On-time | 2024-04-23 | 49 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46029283 | T2 DI CLMN-RED BLUFF 000/007 RPL HRDD | ICW
LC | 126017882 | 000/007 | T2 DI CLMN-RED BLUFF 000/007 RPR STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-29 | 2023-04-24 | 2024-03-05 | On-time | 2024-04-23 | 49 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46029284 | T2 DI CLMN-RED BLUFF 000/007 RPR STRW | ICW
LC | 126015347 | 016/337 | T2 EI CARIBOU-WESTWOOD 16/337 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2023-04-28 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519125 | T2 EI CARIBOU-WESTWOOD 16/337 RPL POLE | 70Y
LC | 126015348 | 016/333 | T2 EI CARIBOU-WESTWOOD 16/333 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2023-04-28 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519123 | T2 EI CARIBOU-WESTWOOD 16/333 RPL POLE | 70Y
LC | 126017899 | 005/095 | T2 DI COLEMAN-RED BLUFF 5/95 RPL INSW | TABLEMTN | ETL.6440.INSL | 2023-04-29 | 2023-04-24 | 2024-03-20 | On-time | 2024-04-23 | 34 | 2024-04-24 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35501121 | T2 DI COLEMAN-RED BLUFF 5/95 RPL INSW | 93I
LC | 126015360 | 016/329 | T2 EI CARIBOU-WESTWD 16/329 GO95 RPL | TABLEMTN | ETL.6300.POLE.WOOD | 2023-04-28 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35542516 | T2 EI CARIBOU-WESTWOOD 16/329 GO95 | 93G
LC | 126018077 | A013/216 | T2 DI COLEMAN-RD BLFF A13/216 RPL INSW | TABLEMTN | ETL.6440.INSL.NCER | 2023-04-29 | 2023-04-24 | 2024-04-01 | On-time | 2024-04-23 | 22 | 2024-04-24 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35501124 | T2 DI COLEMAN-RD BLFF A13/216 RPL INSW | 93I
LC | 126015630 | A007/094 | T2 DI PALERMO-OROVILLE #2 A7/94 RPL HRDD | TABLEMTN | ETL.7740.POLE.WOOD | 2023-04-28 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46026994 | T2 DI PALERMO-OROVILLE #2 A7/94 RPL HRDD | ICW
LC | 126018242 | 000/003 | T2 DI MONTN GATE JCT-CASCAD 0/3 RPL HRDW | TABLEMTN | ETL.7640.POLE.WOOD | 2023-04-29 | 2023-04-24 | 2023-08-20 | On-time | 2024-04-23 | 247 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45935273 | T2 DI MONTN GATE JCT-CASCAD 0/3 RPL HRDW | ICW
LC | 126015748 | 072/523 | T2 EI BRDGVLLE CTTNWD 72/523L RPR OPGW | EUREKA | ETL.1110.POLE.WDPS | 2023-04-28 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Wood | Repair | 46171728 | T2 EI BRDGVLLE CTTNWD 72/523L RPR SHLW | ICW
LC | 126015761 | 072/523 | T2 EI BRDGVLLE CTTNWD 72/523L RPR GRWW | EUREKA | ETL.1110.POLE.WDPS | 2023-04-28 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 46171728 | T2 EI BRDGVLLE CTTNWD 72/523L RPR SHLW | ICW
LC | 126015762 | 072/523 | T2 EI BRDGVLLE CTTNWD 72/523L RPR GYWW | EUREKA | ETL.1110.POLE.WDPS | 2023-04-28 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171728 | T2 EI BRDGVLLE CTTNWD 72/523L RPR SHLW | ICW
LC | 126015774 | 011/003 | T2 EI VLY SPRNGS-MRTL #1 11/3 RPR INSW | VICTOR | ETL.8240.INSL.NCER | 2023-04-28 | 2023-04-28 | 2024-05-21 | Late | 2024-04-27 | -24 | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46080944 | T2 EI VLY SPRNGS-MRTL #1 11/3 RPR INSW | ICW
LC | 126015790 | A007/094 | T2 DI PALERMO-OROVILLE #2 A7/94 RPR INSW | TABLEMTN | ETL.7740.INSL.CERA | 2023-04-28 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46026995 | T2 DI PALERMO-OROVILLE #2 A7/94 RPR INSW | ICW
LC | 126018445 | 083/421 | T2 DI MALIN-RND MTN #2 83/421 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2023-04-29 | 2023-04-24 | 2024-01-12 | On-time | 2024-04-23 | 102 | 2024-04-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46037388 | T2 DI MALIN-RND MTN #2 83/421 RPR INSS | ICS
LC | 126018542 | 013/007 | T2 DI MENDOCINO-HARTLEY 13/007 RPR JMPW | WILLITS | ETL.7510.INSL.NCER | 2023-04-29 | 2023-04-24 | 2024-02-15 | On-time | 2024-04-23 | 68 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46089312 | T2 DI MENDOCINO-HARTLEY 13/007 RPR JMPW | ICW
LC | 126016029 | 008/138 | T2 WV PT #1-HT CRK #2-BRNY 8/138 INS DMP | TABLEMTN | ETL.7040.INSL.NCER | 2023-04-28 | 2023-04-28 | 2024-05-15 | Late | 2024-04-27 | -18 | 2024-04-28 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46037275 | T2 WV PT #1-HT CRK #2-BRNY 8/138 INS DMP | ICW
LC | 126018544 | 013/007 | T2 DI MENDOCINO-HARTLEY 13/007R RPR GYWW | WILLITS | ETL.7510.POLE.STPS | 2023-04-29 | 2023-04-24 | 2024-02-15 | On-time | 2024-04-23 | 68 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46089313 | T2 DI MENDOCINO-HARTLEY 13/007R RPR GYWW | ICW
LC | 126016136 | 000/019 | T2 DI HALSEY-PLACER 0/19 RMV VEG | SACTO | ETL.6990.POLE.WOOD | 2023-04-28 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126018582 | A014/225 | T2 DI CLMN-RED BLUF A14/225 RPL STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-29 | 2023-04-24 | 2024-04-02 | On-time | 2024-04-23 | 21 | 2024-04-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519425 | T2 DI CLMN-RED BLUF A14/225 RPL STRW | 70Y
LC | 126018595 | A015/234 | T2 DI CLMN-RED BLUFF A015/234 RPL PL | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-29 | 2023-04-24 | 2024-04-04 | On-time | 2024-04-23 | 19 | 2024-04-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501131 | T2 DI CLMN-RED BLUFF A015/234 RPL PL | 70Y
LC | 126018888 | 000/005A | T2 DI ROCK CREEK-POE 0/5A RPR ANCS | TABLEMTN | ETL.5630.POLE.NWOD | 2023-04-29 | 2023-04-24 | 2023-08-03 | On-time | 2024-04-23 | 264 | 2023-10-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45895042 | T2 DI ROCK CREEK-POE 0/5A RPR ANCS | ICS
LC | 126019222 | 008/004 | T2 DI MENDOCNO-HRTLY 8/4 RPR INSW | WILLITS | ETL.7510.INSL.NCER | 2023-04-29 | 2023-04-24 | 2024-02-13 | On-time | 2024-04-23 | 70 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46089483 | T2 DI MENDOCNO-HRTLY 8/4 RPR INSW | ICW
LC | 126019224 | 008/004 | T2 DI MENDOCNO-HRTLY 8/4C RMV VEGN | WILLITS | ETL.7510.POLE.STPS | 2023-04-29 | 2023-04-24 | 2024-04-15 | On-time | 2024-04-23 | 8 | 2024-04-24 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126016422 | 086/435 | T2 DI MLN-RND MTN #2 86/435 RPR GYWT | TABLEMTN | ETL.6020.TOWR | 2023-04-28 | 2023-04-19 |  | Late | 2024-04-18 |  | 2024-04-19 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46236274 | T2 DI MLN-RND MTN #2 86/435 RPR GYWT | ICQ
LC | 126019225 | 008/004 | T2 DI MENDOCNO-HRTLY 8/4C RPR GYWW | WILLITS | ETL.7510.POLE.STPS | 2023-04-29 | 2023-04-24 | 2024-02-13 | On-time | 2024-04-23 | 70 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46089484 | T2 DI MENDOCNO-HRTLY 8/4C RPR GYWW | ICW
LC | 126019227 | 082/419B | T2 DI MLN-RND MTN #2 82/419B RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-04-29 | 2023-04-24 | 2024-01-12 | On-time | 2024-04-23 | 102 | 2024-04-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46037387 | T2 DI MLN-RND MTN #2 82/419B RPR SHLS | ICS
LC | 126016772 | 002/040 | T2 DI COLMAN-RED BLUFF 2/40 GO95 | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-28 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35513214 | T2 DI COLMAN-RED BLUFF 2/40 GO95 | 93G
LC | 126019492 | :000/008 | T2 DI CARIBOU #2 :00/08 RPR STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-04-29 | 2023-04-24 | 2023-11-27 | On-time | 2024-04-23 | 148 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46036999 | T2 DI CARIBOU #2 :00/08 RPR STRW | ICW
LC | 126016805 | 000/006A | T2 DI BKS CRK-RCK CRK-CRSTA 0/6A BNT STL | TABLEMTN | ETL.4430.POLE.NWOD | 2023-04-28 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46025857 | T2 DI BKS CRK-RCK CRK-CRSTA 0/6A BNT STL | ICQ
LC | 126019497 | :000/008 | T2 DI CARIBOU #2 :00/08 INS HRDD | TABLEMTN | ETL.6280.POLE.WOOD | 2023-04-29 | 2023-04-24 | 2023-11-27 | On-time | 2024-04-23 | 148 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 46036995 | T2 DI CARIBOU #2 :00/08 INS HRDD | ICW
LC | 126017102 | 001/019 | T2 DI CLMN-RED BLUFF 001/019 RPR INSW | TABLEMTN | ETL.6440.INSL | 2023-04-29 | 2023-04-24 | 2024-05-20 | Late | 2024-04-23 | -27 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46029287 | T2 DI CLMN-RED BLUFF 001/019 RPR INSW | ICW
LC | 126017104 | 001/019 | T2 DI CLMN-RED BLUFF 01/19 RPR STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-29 | 2023-04-24 | 2024-05-20 | Late | 2024-04-23 | -27 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46037260 | T2 DI CLMN-RED BLUFF 01/19 RPR STRW | ICW
LC | 126019501 | A013/218 | T2 DI COLMAN-RD BLUFF A13/218 RPL STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-29 | 2023-04-24 | 2024-04-01 | On-time | 2024-04-23 | 22 | 2024-04-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501125 | T2 DI COLMAN-RD BLUFF A13/218 RPL STRW | 70Y
LC | 126019990 | 004/084 | T2 DI COLE- RD BLF 4/84 RPL STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-29 | 2023-04-24 | 2024-03-14 | On-time | 2024-04-23 | 40 | 2024-04-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35500379 | T2 COLEMAN-RD BLFF 4/80 RPL POLE | 70Y
LC | 126020043 | 000/005B | T2 DI ROCK CREEK-POE 0/5B RPR ANCS | TABLEMTN | ETL.5630.POLE.NWOD | 2023-04-29 | 2023-04-24 | 2023-08-03 | On-time | 2024-04-23 | 264 | 2023-10-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45894260 | T2 DI ROCK CREEK-POE 0/5B RPR ANCS | ICS
LC | 126020391 | 012/002 | T2 DI MENDOCINO-HARTLEY 12/2 RPL POLE | WILLITS | ETL.7510.POLE.WOOD | 2023-04-29 | 2023-04-24 | 2024-02-15 | On-time | 2024-04-23 | 68 | 2024-04-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494505 | T2 DI MENDOCINO-HARTLEY 12/2 RPL POLE | 70Y
LC | 126020794 | 009/071 | T2 DI ROCK CREEK-POE 9/71 RPL HRDT | TABLEMTN | ETL.5630.TOWR | 2023-04-29 | 2023-04-24 | 2023-12-28 | On-time | 2024-04-23 | 117 | 2024-04-24 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46071998 | T2 DI ROCK CREEK-POE 9/71 RPL HRDT | ICQ
LC | 126017225 | 027/006B | T2 DI PHLO JT-ELK 27/6B RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-29 | 2023-04-25 | 2024-06-07 | Late | 2024-04-24 | -44 | 2023-07-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35522274 | T2 DI PHLO JT-ELK 27/6B RPL POLE | 70Y
LC | 126022587 | 001/032 | T2 DI COLEMAN-RED BLUFF 01/32 RPL STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-05-01 | 2023-04-24 | 2024-03-28 | On-time | 2024-04-23 | 26 | 2024-04-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35500376 | T2 COLEMAN-RED BLUFF 001/021 RPL POLE | 70Y
LC | 126017254 | 008/139 | T2 DI COLEMAN-RED BLUFF 008/139 RPL POLE | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-29 | 2023-04-25 | 2024-05-21 | Late | 2024-04-24 | -27 | 2024-04-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501123 | T2 DI COLEMAN-RED BLUFF 008/139 RPL POLE | 70Y
LC | 126029528 | 005/089 | T2 DI COLEMAN-RED BLUFF 05/89 RPR INSW | TABLEMTN | ETL.6440.INSL | 2023-05-02 | 2023-04-24 | 2024-03-20 | On-time | 2024-04-23 | 34 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46029295 | T2 DI COLEMAN-RED BLUFF 05/89 RPR INSW | ICW
LC | 126017271 | 007/005 | T2 DI FORT BRAGG-ELK 007/005L RPR GYWW | WILLITS | ETL.2060.POLE.WDPS | 2023-04-29 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46090138 | T2 DI FORT BRAGG-ELK 007/005 RPR GYWW | ICW
LC | 126017272 | 007/005 | T2 DI FORT BRAGG-ELK 007/005R RPR GYWW | WILLITS | ETL.2060.POLE.WDPS | 2023-04-29 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46090342 | T2 DI FORT BRAGG-ELK 007/005 RPR GYWW | ICW
LC | 126017274 | 007/005 | T2 DI FORT BRAGG-ELK 007/005C CANCEL | WILLITS | ETL.2060.POLE.WDPS | 2023-04-29 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46090343 | T2 DI FORT BRAGG-ELK 007/005 RPL HRDD | ICW
LC | 126017275 | 007/005 | T2 DI FORT BRAGG-ELK 007/005R CANCEL | WILLITS | ETL.2060.POLE.WDPS | 2023-04-29 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46090344 | T2 DI FORT BRAGG-ELK 007/005 RPL HRDD | ICW
LC | 126017280 | 033/001 | T2 DI PHILO JCT-ELK 33/1 INS HRDW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-29 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Missing | Hardware-Wood | Install | 46213851 | T2 DI PHILO JCT-ELK 33/1 INS HRDW | ICW
LC | 126017284 | 026/185 | T2 DI TRINITY-CTTNWD 26/185L RPR STRW | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-29 | 2023-04-18 |  | Late | 2024-04-17 |  | 2024-04-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46027002 | T2 DI TRINITY-CTTNWD 26/185L UNBURY PL | ICW
LC | 126017286 | 026/185 | T2 DI TRINITY-CTTNWD 26/185L RPR ANCW | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-29 | 2023-04-18 |  | Late | 2024-04-17 |  | 2023-10-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46027003 | T2 DI TRINITY-CTTNWD 26/185L UNBRY ANCW | ICW
LC | 126036043 | 009/129 | T2 DI DLTA-MTN GT JCT 9/129L RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2023-05-02 | 2023-04-24 | 2023-10-11 | On-time | 2024-04-23 | 195 | 2024-04-24 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31618690 | T2 EI DLT-MTN GT JCT-MTN 9/129R RPL STRW | 70Y
LC | 126036129 | A014/224 | T2 DI COLEMAN-RED BLUFF A14/224 RPL STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-05-02 | 2023-04-24 | 2024-04-02 | On-time | 2024-04-23 | 21 | 2024-04-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501126 | T2 DI COLEMAN-RED BLUFF A14/224 RPL STRW | 70Y
LC | 126017375 | 054/010 | T2 DI ELK-GUALALA 54/10 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-04-29 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487317 | T2 DI ELK-GUALALA 54/10 RPL POLE | 70Y
LC | 126036180 | 000/004 | T2 DI MTN GATE JCT-CASCADE 0/4 RPR SWTC | TABLEMTN | ETL.7640.POLE.WOOD | 2023-05-02 | 2023-04-24 | 2024-02-17 | On-time | 2024-04-23 | 66 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 46037267 | T2 DI MTN GATE JCT-CASCADE 0/4 RPR SWTC | ICW
LC | 126036631 | A014/232 | T2 DI COLEMAN-RD BLFF A14/232 RPL PL | TABLEMTN | ETL.6440.POLE.WOOD | 2023-05-02 | 2023-04-24 | 2024-04-02 | On-time | 2024-04-23 | 21 | 2024-04-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501128 | T2 DI COLEMAN-RD BLFF A14/232 RPL PL | 70Y
LC | 126017386 | 000/001 | T2 DI COLGATE-SMARTVILL #1 0/1 RPL INSW | SACTO | ETL.6510.INSL.NCER | 2023-04-29 | 2023-04-25 | 2024-05-07 | Late | 2024-04-24 | -13 | 2023-10-25 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35481565 | T2 DI COLGATE-SMARTVILL #1 0/1 RPL INSW | 93I
LC | 126045421 | A016/243 | T2 DI COLE-RB A16/243 RPR STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-05-03 | 2023-04-24 | 2024-04-03 | On-time | 2024-04-23 | 20 | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46029340 | T2 DI COLE-RB A16/243 RPR STRW | ICW
LC | 126017389 | 000/003 | T2 DI STNSLS-MLNS SW STA MN 0/3 RPR STRT | VICTOR | ETL.3830.TOWR | 2023-04-29 | 2023-04-20 | 2024-06-29 | Late | 2024-04-19 | -71 | 2024-04-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46018172 | T2 DI STNSLS-MLNS SW STA MN 0/3 RPR STRT | ICQ
LC | 125987131 | 028/215 | T2 EI MDDLE FRK-GLD HLL 28/215R RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2023-04-25 | 2023-04-25 | 2024-02-14 | On-time | 2024-04-24 | 70 | 2024-04-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46032251 | T2 EI MDDLE FRK-GLD HLL 28/215R RPR GYWW | ICW
LC | 126017499 | 031/214 | T2 EI TRNTY-CTTNWD 031/214 COTTER | TABLEMTN | ETL.4040.INSL.CERA | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46037313 | T2 EI TRNTY-CTTNWD 031/214 COTTER | ICW
LC | 125987251 | 028/215 | T2 EI MDDLE FRK-GLD HLL 28/215C RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2023-04-25 | 2023-04-25 | 2024-02-14 | On-time | 2024-04-24 | 70 | 2024-04-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46032252 | T2 EI MDDLE FRK-GLD HLL 28/215C RPR GYWW | ICW
LC | 125987372 | 028/215 | T2 EI MDDLE FRK-GLD HLL 28/215L RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2023-04-25 | 2023-04-25 | 2024-02-14 | On-time | 2024-04-24 | 70 | 2024-04-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46032254 | T2 EI MDDLE FRK-GLD HLL 28/215L RPR GYWW | ICW
LC | 125987444 | 000/015 | T2 COLGATE-CHALLENGE 000/015 COTTER | SACTO | ETL.6480.INSL.NCER | 2023-04-25 | 2023-04-25 | 2024-03-14 | On-time | 2024-04-24 | 41 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046406 | T2 COLGATE-CHALLENGE 000/015 COTTER | ICW
LC | 126017538 | 005/081 | T2 DI VALLEY SPRINGS-CLAY 5/81 RPL STRW | VICTOR | ETL.8264.POLE.WOOD | 2023-04-29 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35533749 | T2 DI VALLEY SPRINGS-CLAY 5/081 RPL STRW | 70Y
LC | 125987624 | 059/252 | T2 EI RND MTN-TBL MTN #1 59/252 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2023-04-25 | 2023-04-25 | 2023-12-05 | On-time | 2024-04-24 | 141 | 2024-04-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46031689 | T2 EI RND MTN-TBL MTN #1 59/252 RPR STRT | ICQ
LC | 125987993 | 011/099 | T2 EI CRAG VIEW-CASCADE 11/99 COTR KEY | TABLEMTN | ETL.1350.INSL | 2023-04-25 | 2023-04-25 | 2024-02-28 | On-time | 2024-04-24 | 56 | 2024-04-25 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46037279 | T2 EI CRAG VIEW-CASCADE 11/99 COTR KEY | ICS
LC | 125988546 | 059/250 | T2 EI RND MTN-TBL MTN #1 59/250 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2023-04-25 | 2023-04-25 | 2024-01-12 | On-time | 2024-04-24 | 103 | 2024-04-25 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46031688 | T2 EI RND MTN-TBL MTN #1 59/250 RPR GYWS | ICS
LC | 125988576 | 057/243 | T2 EI RND MTN-TBL MTN #1 57/243 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2023-04-25 | 2023-04-25 | 2023-12-05 | On-time | 2024-04-24 | 141 | 2024-04-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46031687 | T2 EI RND MTN-TBL MTN #1 57/243 RPR STRT | ICQ
LC | 125989169 | 038/219 | T2 EI TMLR-SN LS OBISP 38/219 RPR ROAD | PISMOBCH | ETL.3960.TOWR | 2023-04-25 | 2023-04-25 | 2023-10-08 | On-time | 2024-04-24 | 199 | 2024-04-25 | 932 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Repair | 45926542 | T3NT TMBLOR-SN LUS OBSPO 52/291 RPR ROAD | CHS
LC | 126017712 | 007/125 | T2 DI CLMN-RED BLUF 07/125 RPR STRW | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-29 | 2023-04-25 | 2024-05-23 | Late | 2024-04-24 | -29 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46029341 | T2 DI CLMN-RED BLUF 07/125 RPR STRW | ICW
LC | 126017715 | 030/007 | T2 DI PHLO JT-ELK-ELK 30/7 COTTER | WILLITS | ETL.7780.INSL.NCER | 2023-04-29 | 2023-04-25 | 2024-06-11 | Late | 2024-04-24 | -48 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46213849 | T2 DI PHLO JT-ELK 30/7 COTTER | ICW
LC | 126017730 | 033/010 | T2 DI FT RS-GUALAL-GLL 33/10 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-04-29 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506663 | T2 DI FT RS-GUALAL-GLL 33/10 RPL STRW | 70Y
LC | 126017753 | 017/001 | T2 DI PHILO JCT-ELK 17/1 RPR CRSW | WILLITS | ETL.7780.POLE.NWOD | 2023-04-29 | 2023-04-20 | 2024-05-01 | Late | 2024-04-19 | -12 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46090345 | T2 DI PHILO JCT-ELK 17/1 RPR CRSW | ICW
LC | 125989293 | 058/249 | T2 EI RND MTN-TBL MTN #1 58/249 RPL HRDT | TABLEMTN | ETL.6060.TOWR | 2023-04-25 | 2023-04-25 | 2024-01-12 | On-time | 2024-04-24 | 103 | 2024-04-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46050916 | T2 EI RND MTN-TBL MTN #1 58/249 RPL HRDT | ICQ
LC | 125989740 | 016/086 | T2 EI RND MTN-TBLE MTN #2 16/86 RPR ANCS | TABLEMTN | ETL.6070.TOWR | 2023-04-25 | 2023-04-25 | 2023-10-30 | On-time | 2024-04-24 | 177 | 2024-04-25 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 46030994 | T2 EI RND MTN-TBLE MTN #2 16/86 RPR ANCS | ICS
LC | 125990005 | A000/020 | T2 EI VLLY SPRNGS #1 A000/020 RPR STRW | VICTOR | ETL.8210.POLE.WOOD | 2023-04-25 | 2023-04-25 | 2024-03-15 | On-time | 2024-04-24 | 40 | 2024-04-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46161740 | T2 EI VLLY SPRNGS #1 A000/020 RPR STRW | ICW
LC | 125990087 | 017/087 | T2 EI RND MTN-TBLE MTN #2 17/87 RPR ANCS | TABLEMTN | ETL.6070.TOWR | 2023-04-25 | 2023-04-25 | 2023-10-30 | On-time | 2024-04-24 | 177 | 2024-04-25 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 46030995 | T2 EI RND MTN-TBLE MTN #2 17/87 RPR ANCS | ICS
LC | 126017910 | 009/005 | T2 DI MELONES-RACETRACK 9/5 RPR GYWW | VICTOR | ETL.2400.POLE.WOOD | 2023-04-29 | 2023-04-20 | 2024-05-08 | Late | 2024-04-19 | -19 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46080956 | T2 DI MELONES-RACETRACK 9/5 RPR GYWW | ICW
LC | 125991223 | 015/127A | T2 EI CRAG VIEW-CASCADE 15/127A RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2023-04-25 | 2023-04-25 | 2023-12-10 | On-time | 2024-04-24 | 136 | 2024-04-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46037304 | T2 EI CRAG VIEW-CASCADE 15/127A RPR GYWW | ICW
LC | 125991323 | 008/172 | T2 EI VALLEY SPRINGS #1 008/172 RPR STRW | VICTOR | ETL.8210.POLE.WOOD | 2023-04-25 | 2023-04-25 | 2024-03-26 | On-time | 2024-04-24 | 29 | 2024-04-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46161741 | T2 EI VALLEY SPRINGS #1 008/172 RPR STRW | ICW
LC | 125991526 | 015/127C | T2 EI CRAG VIEW-CASCADE 15/127C RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2023-04-25 | 2023-04-25 | 2023-12-10 | On-time | 2024-04-24 | 136 | 2024-04-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46037309 | T2 EI CRAG VIEW-CASCADE 15/127C RPR GYWW | ICW
LC | 126017968 | 001/015 | T2 DI COLGATE-SMARTVILL #1 1/15 RPR INSW | SACTO | ETL.6510.INSL.NCER | 2023-04-29 | 2023-04-27 | 2024-05-06 | Late | 2024-04-26 | -10 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46032428 | T2 DI COLGATE-SMARTVILL #1 1/15 RPR INSW | ICW
LC | 126017982 | 030/007 | T2 DI PHLO JT-ELK 30/7C CANCEL | WILLITS | ETL.7780.POLE.WDPS | 2023-04-29 | 2023-04-25 |  | Late | 2024-04-24 |  | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46213848 | T2 DI PHLO JT-ELK 30/7C RPR STRW | ICW
LC | 125991667 | 015/127B | T2 EI CRAG VIEW-CASCADE 15/127B RPR GYWW | TABLEMTN | ETL.1350.POLE.NWOD | 2023-04-25 | 2023-04-25 | 2023-12-10 | On-time | 2024-04-24 | 136 | 2024-04-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46037305 | T2 EI CRAG VIEW-CASCADE 15/127B RPR GYWW | ICW
LC | 126017995 | 015/063 | T2 EI DIABLO-GATES #1 015/063 RPR GYWT | PISMOBCH | ETL.5960.TOWR | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46175234 | T2 EI DIABLO-GATES #1 015/063 RPR GYWT | ICQ
LC | 126012036 | A016/242 | T2 DI COLEMAN-RED BLUFF A16/242 RPR CNDW | TABLEMTN | ETL.6440.INSL.NCER | 2023-04-28 | 2023-04-25 | 2023-05-17 | On-time | 2024-04-24 | 343 | 2023-07-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45749921 | T2 DI COLEMAN-RED BLUFF A16/242 RPR CNDW | ICW
LC | 126018055 | 031/008B | T2 DI PHILO JCT-ELK 31/008B RPL ANCW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-29 | 2023-04-25 | 2024-06-08 | Late | 2024-04-24 | -45 | 2024-04-25 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35522279 | T2 DI PHILO JCT-ELK 31/008A RPL ANCW | 93E
LC | 126015654 | :007/055 | T2 DI ELK CREEK TAP :007/055 RPL HRDT | TABLEMTN | ETL.5630.TOWR | 2023-04-28 | 2023-04-25 | 2024-01-08 | On-time | 2024-04-24 | 107 | 2024-04-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46071999 | T2 DI ELK CREEK TAP :007/055 RPL HRDT | ICQ
LC | 126015869 | 001/005 | T2 DI STNLS MNTCA#2 01/005 UNBURY | VICTOR | ETL.3820.TOWR | 2023-04-28 | 2023-04-25 | 2023-11-27 | On-time | 2024-04-24 | 149 | 2024-04-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46048279 | T2 DI STNLS MNTCA#2 01/005 UNBURY | ICQ
LC | 126016137 | 000/019 | T2 DI HALSEY-PLACER 0/19 RPR FIBR | SACTO | ETL.6990.POLE.WOOD | 2023-04-28 | 2023-04-25 | 2024-03-18 | On-time | 2024-04-24 | 37 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Other Fiber - Wood | Repair | 45749385 | T2 DI HALSEY-PLACER 00/19 RPR FIBER | ICW
LC | 126016219 | 001/006 | T2 DI STLS MLS SW STA MTCA #1 1/6 UNBURY | VICTOR | ETL.3830.TOWR | 2023-04-28 | 2023-04-25 | 2023-11-27 | On-time | 2024-04-24 | 149 | 2024-04-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46048800 | T2 DI STLS MLS SW STA MTCA #1 1/6 UNBURY | ICQ
LC | 126018336 | 012/099 | T2 DI PIT#6 JCT-RND MT 12/99 RPL STRW | TABLEMTN | ETL.5440.POLE.WDPS | 2023-04-29 | 2023-04-20 | 2024-06-22 | Late | 2024-04-19 | -64 | 2024-04-20 | 372 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35529573 | T2 DI PIT #6 JCT-RND MTN RPL 3 POLE | 70Y
LC | 126018337 | 012/099 | T2 DI PIT#6 JCT-RND MT 12/99 RPL STRW | TABLEMTN | ETL.5440.POLE.WDPS | 2023-04-29 | 2023-04-20 | 2024-06-22 | Late | 2024-04-19 | -64 | 2024-04-20 | 372 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35529573 | T2 DI PIT #6 JCT-RND MTN RPL 3 POLE | 70Y
LC | 126017147 | 000/001 | T2 DI HALSEY-PLACER 00/01 RPR FIBER | SACTO | ETL.6990.POLE.NWOD | 2023-04-29 | 2023-04-25 | 2023-05-19 | On-time | 2024-04-24 | 341 | 2023-07-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45749386 | T2 DI HALSEY-PLACER 00/01 RPR FIBER | ICW
LC | 126017258 | 023/004 | T2 DI COAL#1-SAN MIG 23/4 RPR INSS | PISMOBCH | ETL.8580.INSL.CERA | 2023-04-29 | 2023-04-25 | 2024-03-15 | On-time | 2024-04-24 | 40 | 2024-04-25 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46079018 | T2 DI COAL#1-SAN MIG 23/4 RPR INSS | ICS
LC | 126017381 | 000/001 | T2 DI COLGATE-SMARTVILLE #1 0/1 RPR GYWW | SACTO | ETL.6510.POLE.NWOD | 2023-04-29 | 2023-04-25 | 2023-05-09 | On-time | 2024-04-24 | 351 | 2023-07-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45749456 | T2 DI COLGATE-SMARTVILLE #1 0/1 RPR GYWW | ICW
LC | 126017387 | 000/001 | T2 DI COLGATE-SMRTVILL #1 0/1 RPR GYWW | SACTO | ETL.6510.POLE.NWOD | 2023-04-29 | 2023-04-25 | 2023-05-09 | On-time | 2024-04-24 | 351 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45907455 | T2 DI COLGATE-SMRTVILL #1 0/1 RPR GYWW | ICW
LC | 126017516 | A015/237 | T2 DI COLE- RD BLF A15/237 RPL PL | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-29 | 2023-04-25 | 2024-04-04 | On-time | 2024-04-24 | 20 | 2024-04-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35501132 | T2 DI COLE- RD BLF A15/237 RPL PL | 70Y
LC | 126017573 | 005/007 | T2 DI VLY SPRGS-MAR #1 5/7 COTTER | VICTOR | ETL.8240.INSL.NCER | 2023-04-29 | 2023-04-25 | 2023-05-18 | On-time | 2024-04-24 | 342 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45762956 | T2 DI VLY SPRGS-MAR #1 5/7 COTTER | ICW
LC | 126017637 | 030/007 | T2 DI PHLO JT-ELK 30/7L RPR GYWW | WILLITS | ETL.7780.POLE.WDPS | 2023-04-29 | 2023-04-25 | 2023-09-11 | On-time | 2024-04-24 | 226 | 2023-10-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45752865 | T2 DI PHLO JT-ELK 30/7L RPR GYWW | ICW
LC | 126017638 | 030/007 | T2 DI PHLO JT-ELK 30/7C RPR GYWW | WILLITS | ETL.7780.POLE.WDPS | 2023-04-29 | 2023-04-25 | 2023-09-11 | On-time | 2024-04-24 | 226 | 2023-10-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45752868 | T2 DI PHLO JT-ELK 30/7C RPR GYWW | ICW
LC | 126017639 | 030/007 | T2 DI PHLO JT-ELK 30/7R RPR GYWW | WILLITS | ETL.7780.POLE.WDPS | 2023-04-29 | 2023-04-25 | 2023-09-11 | On-time | 2024-04-24 | 226 | 2023-10-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45752870 | T2 DI PHLO JT-ELK 30/7R RPR GYWW | ICW
LC | 126018419 | 000/001A | T2 DI MONTN GATE JCT-CASCADE 0/1A UNBURY | TABLEMTN | ETL.7640.POLE.WOOD | 2023-04-29 | 2023-04-25 | 2023-08-28 | On-time | 2024-04-24 | 240 | 2023-10-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45758186 | T2 DI MONTN GATE JCT-CASCADE 0/1A UNBURY | ICW
LC | 126019163 | 002/026 | T2 DI MTN GATE JCT-CSCD 2/26 RPR INSW | TABLEMTN | ETL.7640.INSL.CERA | 2023-04-29 | 2023-04-25 | 2024-02-17 | On-time | 2024-04-24 | 67 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46037268 | T2 DI MTN GATE JCT-CSCD 2/26 RPR INSW | ICW
LC | 126019312 | 000/003 | T2 DI JEFFERSON-STNFD 0/3 RPL HRDW | METCALF | ETL.7220.POLE.NWOD | 2023-04-29 | 2023-04-25 | 2023-07-06 | On-time | 2024-04-24 | 293 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45750556 | T2 DI JEFFERSON-STNFD 0/3 RPL HRDW | ICW
LC | 126018715 | 032/001 | T2 DI FORT ROSS-GUALALA 32/01 GRND WASH | LAKEVLLE | ETL.6980.INSL.NCER | 2023-04-29 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 622 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Contaminated | Insulator | Ground Wash | 46234526 | T2 DI FORT ROSS-GUALALA 32/01 RPL INSW | ICD
LC | 126019316 | 000/003 | T2 DI JEFFERSON-STNFD 0/3 RPR INSW | METCALF | ETL.7220.INSL.NCER | 2023-04-29 | 2023-04-25 | 2023-07-06 | On-time | 2024-04-24 | 293 | 2023-07-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45749208 | T2 DI JEFFERSON-STNFD 0/3 RPR INSW | ICW
LC | 126018801 | 027/403 | T2 EI CLAY-MARTEL 27/403 COMPLETED | VICTOR | ETL.8250.POLE.WOOD | 2023-04-29 | 2023-04-29 | 2024-06-04 | Late | 2024-04-28 | -37 | 2024-04-29 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31653149 | T2 EI CLAY-MARTEL 27/399 RPL POLE | 70Y
LC | 126019319 | 000/003 | T2 DI JEFFERSON-STNFD 0/3 RPR CRSW | METCALF | ETL.7220.POLE.NWOD | 2023-04-29 | 2023-04-25 | 2023-07-06 | On-time | 2024-04-24 | 293 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45750557 | T2 DI JEFFERSON-STNFD 0/3 RPR CRSW | ICW
LC | 126018985 | 027/399 | T2 EI CLAY-MARTEL 27/399 RPL POLE | VICTOR | ETL.8250.POLE.WOOD | 2023-04-29 | 2023-04-29 | 2024-06-07 | Late | 2024-04-28 | -40 | 2024-04-29 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31653149 | T2 EI CLAY-MARTEL 27/399 RPL POLE | 70Y
LC | 126019410 | 004/044 | T2 DI MTN GATE JCT-CASCADE 4/44 RPL INSW | TABLEMTN | ETL.7640.INSL.CERA | 2023-04-29 | 2023-04-25 | 2024-02-16 | On-time | 2024-04-24 | 68 | 2024-04-25 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35484838 | T2 DI MTN GATE JCT-CASCADE 4/44 RPL INSW | 93I
LC | 126019604 | 000/001 | T2 DI COLGATE-PALERMO 000/001 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2023-04-29 | 2023-04-25 | 2024-04-17 | On-time | 2024-04-24 | 7 | 2023-10-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506912 | T2 DI COLGATE-PALERMO 000/001 RPL STRW | 70Y
LC | 126019646 | 000/003 | T2 DI CLGT PH-CLGT SS 000/003 RPR FOND | SACTO | ETL.6460.POLE.NWOD | 2023-04-29 | 2023-04-25 | 2024-04-11 | On-time | 2024-04-24 | 13 | 2024-04-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46072120 | T2 DI CLGT PH-CLGT SS 000/003 RPR FOND | ICQ
LC | 126019759 | 000/001C | T2 DI MTN GATE JCT-CASCADE 0/1C RPR GYWW | TABLEMTN | ETL.7640.POLE.WOOD | 2023-04-29 | 2023-04-25 | 2023-08-20 | On-time | 2024-04-24 | 248 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45935272 | T2 DI MTN GATE JCT-CASCADE 0/1C RPR GYWW | ICW
LC | 126020397 | 023/005 | T2 DI COALINGA #1-SN MGL 23/5 RPL INSS | PISMOBCH | ETL.8580.INSL.CERA | 2023-04-29 | 2023-04-25 | 2024-03-15 | On-time | 2024-04-24 | 40 | 2024-04-25 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513941 | T2 DI COALINGA #1-SN MGL 23/5 RPL INSS | 93K
LC | 126022660 | :004/025 | T2 DI ROCK CREEK-POE 004/25 RPR JUMS | TABLEMTN | ETL.5630.INSL.CERA | 2023-05-01 | 2023-04-25 | 2023-08-04 | On-time | 2024-04-24 | 264 | 2023-07-25 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45895472 | T2 DI ROCK CREEK-POE 004/25 RPR JUMS | ICS
LC | 126026784 | :005/038 | T2 DI ROCK CREEK POE :05/038 RPL INSS | TABLEMTN | ETL.5630.INSL.CERA | 2023-05-01 | 2023-04-25 | 2024-02-27 | On-time | 2024-04-24 | 57 | 2024-04-25 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509199 | T2 DI ROCK CREEK-POE :5/33 RPLC INSS | 93K
LC | 126030552 | 031/006 | T2 DI PHILO JCT-ELK 31/6 RPR CNDW | WILLITS | ETL.7780.INSL.NCER | 2023-05-02 | 2023-04-25 | 2023-09-12 | On-time | 2024-04-24 | 225 | 2023-07-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45753055 | T2 DI PHILO JCT-ELK 031/006 RPR CNDW | ICW
LC | 126034193 | 001/011 | T2 DI MTN GTE JT CSCDE 01/011 RPR GYWW | TABLEMTN | ETL.7640.POLE.WDPS | 2023-05-02 | 2023-04-25 | 2023-08-20 | On-time | 2024-04-24 | 248 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45935270 | T2 DI MTN GTE JT CSCDE 01/011 RPR GYWW | ICW
LC | 126034356 | 001/011 | T2 DI MTN GTE JT CSCDE 01/011 RPL ANCW | TABLEMTN | ETL.7640.POLE.WDPS | 2023-05-02 | 2023-04-25 | 2023-08-21 | On-time | 2024-04-24 | 247 | 2024-04-25 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35484837 | T2 DI MTN GTE JT CSCDE 01/011 RPL ANCW | 93E
LC | 126035958 | 001/034 | T2 DI HALSEY-PLACER 001/034 RPL POLE | SACTO | ETL.6990.POLE.WOOD | 2023-05-02 | 2023-04-25 | 2024-04-24 | On-time | 2024-04-24 | 0 | 2024-04-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35482601 | T2 DI HALSEY-PLACER 001/034 RPL POLE | 70Y
LC | 126036074 | 003/037 | T2 DI MTN GATE JCT-CASCAD 3/37L RPR POLE | TABLEMTN | ETL.7640.POLE.WDPS | 2023-05-02 | 2023-04-25 | 2024-02-01 | On-time | 2024-04-24 | 83 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46037269 | T2 DI MTN GATE JCT-CASCAD 3/37L RPR POLE | ICW
LC | 126036105 | 004/051 | T2 DI MTN GATE JCT-CASCADE 4/51 RPL POLE | TABLEMTN | ETL.7640.POLE.WOOD | 2023-05-02 | 2023-04-25 | 2024-02-16 | On-time | 2024-04-24 | 68 | 2024-04-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35510365 | T2 DI MTN GATE JCT-CASCADE 4/51 RPL POLE | 70Y
LC | 126036152 | 011/047 | T2 DI MNT-VST-JFFRSN #1 11/47 BNT STEEL | METCALF | ETL.5220.TOWR | 2023-05-02 | 2023-04-25 | 2024-01-25 | On-time | 2024-04-24 | 90 | 2024-04-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46058958 | T2 DI MNT-VST-JFFRSN #1 11/47 BNT STEEL | ICQ
LC | 126036639 | 016/005 | T2 DI LOWER LK-HOMESTAKE 16/5 RPR ANCW | WILLITS | ETL.1481.POLE.WOOD | 2023-05-02 | 2023-04-25 | 2023-06-12 | On-time | 2024-04-24 | 317 | 2023-10-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45753057 | T2 DI LOWER LK-HOMESTAKE 16/5 RPR ANCW | ICW
LC | 126036738 | 004/050 | T2 DI MNTN GT JCT-CSCD 4/50 RPL POLE | TABLEMTN | ETL.7640.POLE.WOOD | 2023-05-02 | 2023-04-25 | 2024-02-16 | On-time | 2024-04-24 | 68 | 2024-04-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484839 | T2 DI MNTN GT JCT-CSCDE 4/46 RPL POLE | 70Y
LC | 126036815 | 004/046 | T2 DI MNTN GT JCT-CSCDE 4/46 RPL POLE | TABLEMTN | ETL.7640.POLE.WOOD | 2023-05-02 | 2023-04-25 | 2024-02-16 | On-time | 2024-04-24 | 68 | 2024-04-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484839 | T2 DI MNTN GT JCT-CSCDE 4/46 RPL POLE | 70Y
LC | 126038064 | 004/039 | T2 DI MTN GTE JT CSCDE 04/39R RPR STRW | TABLEMTN | ETL.7640.POLE.WDPS | 2023-05-03 | 2023-04-25 | 2024-02-16 | On-time | 2024-04-24 | 68 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46037271 | T2 DI MTN GTE JT CSCDE 04/39R RPR STRW | ICW
LC | 126050312 | 003/037 | T2 DI MTN GATE JCT-CASCAD 3/37R RPR POLE | TABLEMTN | ETL.7640.POLE.WDPS | 2023-05-04 | 2023-04-25 | 2024-02-01 | On-time | 2024-04-24 | 83 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46037270 | T2 DI MTN GATE JCT-CASCAD 3/37R RPR POLE | ICW
LC | 126019503 | 030/210 | T2 DI TRINTY-CTTNWD 30/210C RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-04-29 | 2023-04-20 |  | Late | 2024-04-19 |  | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46027014 | T2 DI TRINTY-CTTNWD 30/210C RPR GYWW | ICW
LC | 126019552 | 074/533 | T2 EI BRDGVLLE-CTTNWD 74/533 RPR GRDW | EUREKA | ETL.1110.POLE.WDPS | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 46171733 | T2 EI BRDGVLLE-CTTNWD 74/533 RPR GRDW | ICW
LC | 125993756 | 005/111 | T2 BURNS-LONE STAR #2 5/111 RPR INSW | MOSSLNDG | ETL.6240.INSL.NCER | 2023-04-26 | 2023-04-26 | 2024-04-16 | On-time | 2024-04-25 | 9 | 2024-04-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081509 | T2 BURNS-LONE STAR #2 5/111 RPR INSW | ICW
LC | 125993797 | 014/124 | T2 EI CRAG VIEW-CASCADE 14/124L RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-26 | 2023-04-26 | 2023-12-10 | On-time | 2024-04-25 | 137 | 2024-04-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46037310 | T2 EI CRAG VIEW-CASCADE 14/124L RPR GYWW | ICW
LC | 125993801 | 014/124 | T2 EI CRAG VIEW-CASCADE 014/124 INS DAMW | TABLEMTN | ETL.1350.INSL.NCER | 2023-04-26 | 2023-04-26 | 2023-12-10 | On-time | 2024-04-25 | 137 | 2024-04-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46037311 | T2 EI CRAG VIEW-CASCADE 014/124 INS DAMW | ICW
LC | 125994535 | 001/013 | T2 WV TRINITY-MAPLE CREEK 1/13 REFRAME | EUREKA | ETL.8170.POLE.WOOD | 2023-04-26 | 2023-04-26 | 2024-01-17 | On-time | 2024-04-25 | 99 | 2024-04-26 | 637T | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31639945 | T2 TRINITY-MAPLE CREEK 1/11 RPL EMRG | 921
LC | 125994692 | 017/092 | T2 EI RND MTN-TBLE MTN #2 17/92 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2023-04-26 | 2023-04-26 | 2023-10-30 | On-time | 2024-04-25 | 178 | 2024-04-26 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46030996 | T2 EI RND MTN-TBLE MTN #2 17/92 RPR STRT | ICQ
LC | 125996071 | 033/515 | T2 EI CLAY-MARTEL 033/515 RPR INSW | VICTOR | ETL.8250.INSL.NCER | 2023-04-26 | 2023-04-26 | 2023-10-26 | On-time | 2024-04-25 | 182 | 2024-04-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46031269 | T2 EI CLAY-MARTEL 033/515 RPR INSW | ICW
LC | 125996559 | 033/511 | T2 EI CLAY-MARTEL 033/511 RPR INSW | VICTOR | ETL.8250.INSL.CERA | 2023-04-26 | 2023-04-26 | 2023-11-27 | On-time | 2024-04-25 | 150 | 2024-04-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46031268 | T2 EI CLAY-MARTEL 033/511 RPR INSW | ICW
LC | 126019790 | 009/074A | T2 EI PIT #1-COTTONWD 9/74A RMV NEST | TABLEMTN | ETL.5390.TOWR | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2023-07-29 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46037380 | T2 EI PIT #1-COTTONWOOD 9/074A RMV NEST | ICS
LC | 126019793 | 014/183 | T2 DI DLTA-MTN GTE JCT 14/183 RPL POLE | TABLEMTN | ETL.6750.POLE.WDPS | 2023-04-29 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35550487 | T2 DI DLTA-MTN GTE JCT 14/183 RPL POLE | 70Y
LC | 126019810 | 014/183 | T2 DI DLTA-MTN GTE JCT 14/183R RPL POLE | TABLEMTN | ETL.6750.POLE.WDPS | 2023-04-29 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35550487 | T2 DI DLTA-MTN GTE JCT 14/183 RPL POLE | 70Y
LC | 126019852 | 008/143 | T2 DI COLEMAN-RED BLUFF 008/143 RPL POLE | TABLEMTN | ETL.6440.POLE.WOOD | 2023-04-29 | 2023-04-24 | 2024-05-21 | Late | 2024-04-23 | -28 | 2024-04-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501123 | T2 DI COLEMAN-RED BLUFF 008/139 RPL POLE | 70Y
LC | 125996729 | 014/118 | T2 EI CRAG VIEW-CASCADE 14/118L RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-26 | 2023-04-26 | 2023-08-08 | On-time | 2024-04-25 | 261 | 2023-10-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45758190 | T2 EI CRAG VIEW-CASCADE 14/118L RPR GYWW | ICW
LC | 125997052 | 014/118 | T2 EI CRAG VIEW-CASCADE 14/118R RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-26 | 2023-04-26 | 2023-08-10 | On-time | 2024-04-25 | 259 | 2023-10-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45758189 | T2 EI CRAG VIEW-CASCADE 14/118R RPR GYWW | ICW
LC | 125997314 | 014/118 | T2 EI CRAG VIEW-CASCADE 14/118C RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-04-26 | 2023-04-26 | 2023-08-10 | On-time | 2024-04-25 | 259 | 2023-10-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45758188 | T2 EI CRAG VIEW-CASCADE 14/118C RPR GYWW | ICW
LC | 126020039 | 031/008A | T2 DI PHILO JCT-ELK 31/008A RPL ANCW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-29 | 2023-04-25 | 2024-06-08 | Late | 2024-04-24 | -45 | 2024-04-25 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35522279 | T2 DI PHILO JCT-ELK 31/008A RPL ANCW | 93E
LC | 125999710 | 001/015 | T2 WV GRANITE ROCK TAP 01/15 INS DMPW | MOSSLNDG | ETL.8311.INSL.NCER | 2023-04-26 | 2023-04-26 | 2024-02-13 | On-time | 2024-04-25 | 72 | 2024-04-26 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46081589 | T2 WV GRANITE ROCK TAP 01/15 INS DMPW | ICW
LC | 126020077 | 031/008C | T2 DI PHILO JCT-ELK 031/008C RPL ANCW | WILLITS | ETL.7780.POLE.WOOD | 2023-04-29 | 2023-04-25 | 2024-06-08 | Late | 2024-04-24 | -45 | 2024-04-25 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35522279 | T2 DI PHILO JCT-ELK 31/008A RPL ANCW | 93E
LC | 126020243 | 001/012 | T2 DI PIT #7 TAP 001/012L RPR GYWW | TABLEMTN | ETL.5442.POLE.STPS | 2023-04-29 | 2023-04-26 | 2024-06-26 | Late | 2024-04-25 | -62 | 2023-10-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46037385 | T2 DI PIT #7 TAP 001/012L RPR GYWW | ICW
LC | 125999735 | 039/158 | T2 DI DIABLO-MIDWAY #2 39/158 RPR SHLS | PISMOBCH | ETL.5970.INSL.NCER | 2023-04-26 | 2023-04-26 | 2024-04-24 | On-time | 2024-04-25 | 1 | 2024-04-26 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46078966 | T2 DI DIABLO-MIDWAY #2 39/158 RPR SHIELD | ICS
LC | 126020329 | 008/060 | T2 DI VACA-SUISUN 8/60 RPR STRT | SACTO | ETL.4070.TOWR | 2023-04-29 | 2023-04-20 | 2024-05-03 | Late | 2024-04-19 | -14 | 2024-04-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46028571 | T2 DI VACA-SUISU 8/60 RPR STRT BNT STEEL | ICQ
LC | 126000294 | 033/135 | T2 EI DIABLO-MIDWAY #2 033/135 RPR GYWT | PISMOBCH | ETL.5970.TOWR | 2023-04-26 | 2023-04-26 | 2024-04-19 | On-time | 2024-04-25 | 6 | 2024-04-26 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46179478 | T2 EI DIABLO-MIDWAY #2 033/135 RPR GYWT | ICQ
LC | 126000414 | 043/176 | T2 DI DIABLO-MIDWAY #2 43/176 RPR SHLS | PISMOBCH | ETL.5970.TOWR | 2023-04-26 | 2023-04-26 | 2023-05-23 | On-time | 2024-04-25 | 338 | 2023-07-26 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45749281 | T2 DI DIABLO-MIDWAY #2 43/176 RPR SHLS | ICS
LC | 126020414 | 61 | T2 DI CARIBOU #2 :007/011 RPR SWTC | TABLEMTN | ETL.6280.SWIT | 2023-04-29 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 46026989 | T2 DI CARIBOU #2 :007/011 RPR SWTC | ICW
LC | 126020417 | 009/080 | T2 DI CBRLL-SNT YNZ SW 9/80 RPL INSW | PISMOBCH | ETL.1200.INSL.NCER | 2023-04-29 | 2023-04-24 | 2024-06-21 | Late | 2024-04-23 | -59 | 2024-04-24 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35529361 | T2 DI CBRLL-SNT YNZ SW 9/80 RPL INSW | 93I
LC | 126020480 | 029/000 | T2 EI MNDCNO-WLLTS-FRT BRG 29/0 RPR POLE | WILLITS | ETL.7550.POLE.WOOD | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46227298 | T2 EI MNDCNO-WLLTS-FRT BRG 29/0 RPR POLE | ICW
LC | 126020481 | 029/000 | T2 EI MNDCNO-WLLTS-FRT BRG 29/0 WSH INSW | WILLITS | ETL.7550.INSL.CERA | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 622 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Contaminated | Insulator | Ground Wash | 46227299 | T2 EI MNDCNO-WLLTS-FRT BRG 29/0 WSH INSW | ICD
LC | 126020484 | 029/001 | T2 EI MNDCNO-WLLTS-FRT BRG 29/1 WSH INSW | WILLITS | ETL.7550.INSL.NCER | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 622 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Contaminated | Insulator | Ground Wash | 46227300 | T2 EI MNDCNO-WLLTS-FRT BRG 29/1 WSH INSW | ICD
LC | 126020486 | 028/007 | T2 EI MNDOCN-WILTS-FRT BRG 28/7 RPL HRDD | WILLITS | ETL.7550.POLE.WOOD | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Missing | Hardware-Wood | Install | 46227294 | T2 EI MNDOCN-WILTS-FRT BRG 28/7 RPL HRDD | ICW
LC | 126020487 | 028/005 | T2 EI MNDCNO-WLTS-FORT BRG 28/5 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46222744 | T2 EI MNDCNO-WLTS-FORT BRG 28/5 RPR STRW | ICW
LC | 126020490 | 028/004 | T2 EI MNDCINO-WLTS-FRT BRG 28/4 RPR IBWW | WILLITS | ETL.7550.POLE.WOOD | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 46222743 | T2 EI MNDCINO-WLTS-FRT BRG 28/4 RPR IBWW | ICW
LC | 126017984 | ;003/014 | T2 DI CARIBOU #2 ;03/14 RPR IBWW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-04-29 | 2023-04-26 | 2023-11-09 | On-time | 2024-04-25 | 168 | 2024-04-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46037176 | T2 DI CARIBOU #2 ;03/14 RPR IBWW | ICW
LC | 126020539 | 003/011 | T2 DI LWR LAKE-HOMESTKE 003/11 CANCEL | WILLITS | ETL.1481.POLE.WOOD | 2023-04-29 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46213266 | T2 DI LWR LAKE-HOMESTKE 003/011 RPL HRDW | ICW
LC | 126020611 | 072/519 | T2 EI BRDGVLL-CTTNWD 72/519R RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505109 | T2 DI BRDGVIL-CTTNWOOD 82/577R RPL STRW | 70Y
LC | 126020650 | 072/519 | T2 EI BRDGVLL-CTTNWD 72/519L RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505109 | T2 DI BRDGVIL-CTTNWOOD 82/577R RPL STRW | 70Y
LC | 126020769 | 071/517 | T2 EI BRDGEVLE-COTTONWD 71/517R RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171725 | T2 EI BRDGEVLE-COTTONOD 71/517 RPR GYWW | ICW
LC | 126018052 | :007/056 | T2 DI ROCK CREEK-POE :007/056 RPR INSS | TABLEMTN | ETL.5630.INSL.CERA | 2023-04-29 | 2023-04-26 | 2024-02-27 | On-time | 2024-04-25 | 58 | 2024-04-26 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46037318 | T2 DI ROCK CREEK-POE :007/056 RPR INSS | ICS
LC | 126019962 | 000/006 | T2 DI SPLDNG-SMMT 0/6 COTTER | SACTO | ETL.8060.INSL.NCER | 2023-04-29 | 2023-04-26 | 2024-03-27 | On-time | 2024-04-25 | 29 | 2024-04-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45749453 | T2 DI SPLDNG-SMMT 000/006 COTTER | ICW
LC | 126020802 | 071/517 | T2 EI BRIDGEVL-COTTONWD 71/517L RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171725 | T2 EI BRDGEVLE-COTTONOD 71/517 RPR GYWW | ICW
LC | 126020316 | :000/012 | T2 DI CARIBOU #2 :000/012 COTTER | TABLEMTN | ETL.6280.INSL.NCER | 2023-04-29 | 2023-04-26 | 2023-06-03 | On-time | 2024-04-25 | 327 | 2023-10-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45749917 | T2 DI CARIBOU #2 :000/012 COTTER | ICW
LC | 126020990 | 071/516 | T2 EI BRDGEVILE-COTONWOD 71/516 RPL ANCW | EUREKA | ETL.1110.POLE.WDPS | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35505104 | T2 DI BRDGVL-CTNWD 70/509L RPL XBRACE | 93E
LC | 126020381 | 019/117 | T2 DI SLO-OCEANO 019/117 COTTER | PISMOBCH | ETL.3530.INSL.NCER | 2023-04-29 | 2023-04-26 | 2023-05-17 | On-time | 2024-04-25 | 344 | 2024-04-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45766250 | T2 DI SLO-OCEANO 019/117 COTTER | ICW
LC | 126021105 | 018/379 | T2 EI CARIBOU-WESTWOOD 18/379 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519127 | T2 DI CARIBOU-WSWD 018/369 RPL PL | 70Y
LC | 126021127 | ;005/011 | T2 EI CARIBOU #2 ;005/011 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527154 | T2 DI CARIBOU #2 ;005/010 RPL STRW | 70Y
LC | 126021141 | 016/336 | T2 EI CARIBOU-WESTWOOD 16/336 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2023-04-29 | 2023-04-29 |  | Late | 2024-04-28 |  | 2024-04-29 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519124 | T2 EI CARIBOU-WESTWOOD 16/336 RPL POLE | 70Y
LC | 126021149 | 043/175 | T2 EI DIABLO-MIDWAY #2 43/175 RPR GYWT | PISMOBCH | ETL.5970.TOWR | 2023-04-29 | 2023-04-29 | 2024-05-03 | Late | 2024-04-28 | -5 | 2024-04-29 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46179723 | T2 EI DIABLO-MIDWAY #2 43/175 RPR GYWT | ICQ
LC | 126032249 | 019/177 | T2 DI BRDGVIL CTTNWD 19/177 COTTER | TABLEMTN | ETL.1110.INSL.NCER | 2023-05-02 | 2023-04-26 | 2024-01-16 | On-time | 2024-04-25 | 100 | 2024-04-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46037303 | T2 DI BRDGVIL CTTNWD 19/177 COTTER | ICW
LC | 126038142 | 087/443 | T2 DI MALIN ROUND MNTN#2 87/443 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2023-05-03 | 2023-04-26 | 2023-11-08 | On-time | 2024-04-25 | 169 | 2024-04-26 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46030992 | T2 DI MALIN ROUND MNTN#2 87/443 RPR GYWS | ICS
LC | 126022648 | 035/003 | T2 DI FRT RS GUALALA 35/003 RPL POLE | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-01 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35549291 | T2 DI FRT RS GUALALA 35/003 RPL POLE | 70Y
LC | 126045122 | :006/046 | T2 DI ROCK CREEK-POE :6/46 RPL INSS | TABLEMTN | ETL.5630.INSL | 2023-05-03 | 2023-04-26 | 2023-03-04 | On-time | 2024-04-25 | 418 | 2024-04-26 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31645080 | T2 DI ROCK CREEK-POE :6/46 RPL INSS | 93K
LC | 126023123 | 006/009 | T2 EI VALLEY SPRNGS-MRTL #1 6/9 RPR POLE | VICTOR | ETL.8240.POLE.WOOD | 2023-05-01 | 2023-05-01 | 2024-05-22 | Late | 2024-04-30 | -22 | 2024-05-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46080961 | T2 EI VALLEY SPRNGS-MRTL #1 6/9 RPR POLE | ICW
LC | 126024439 | ;003/001 | T2 EI CARIBOU #2 ;003/001 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-01 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527152 | T2 EI CARIBOU #2 ;003/001 RPL POLE | 70Y
LC | 126024454 | 009/128 | T2 DI DLTA MTN GTE JT 9/128R RPR STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2023-05-01 | 2023-04-24 |  | Late | 2024-04-23 |  | 2024-04-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46037261 | T2 DI DLTA MTN GTE JT 09/128R RPR STRW | ICW
LC | 126024648 | 026/001 | T2 EI MI-WUK-CURTIS 026/001 RPR POLE | VICTOR | ETL.1073.POLE.WDPS | 2023-05-01 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46058677 | T2 EI MI-WUK-CURTIS 026/001 RPR POLE | ICW
LC | 126024758 | 007/124 | T2 DI COLEMAN-RED BLUFF 07/124 RPL INSW | TABLEMTN | ETL.6440.INSL | 2023-05-01 | 2023-04-25 | 2024-05-23 | Late | 2024-04-24 | -29 | 2024-04-25 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35501121 | T2 DI COLEMAN-RED BLUFF 5/95 RPL INSW | 93I
LC | 126024812 | 008/058 | T2 WV COTTONWOOD #2 8/58 RPR INSS | TABLEMTN | ETL.6630.INSL.NCER | 2023-05-01 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45880239 | T2 WV COTTONWOOD #2 8/58 RPR INSS | ICS
LC | 126025329 | 017/345 | T2 EI CARIBOU-WESTWOOD 17/345 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-01 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519126 | T2 EI CARIBOU-WESTWOOD 17/345 RPL STRW | 70Y
LC | 126025391 | 042/172 | T2 EI DIABLO-MIDWAY #2 42/172 RPR GYWT | PISMOBCH | ETL.5970.TOWR | 2023-05-01 | 2023-05-01 | 2024-05-03 | Late | 2024-04-30 | -3 | 2024-05-01 | 543 | TLQ | PATR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46179722 | T2 EI DIABLO-MIDWAY #2 42/172 RPR GYWT | ICQ
LC | 126001527 | 007/098 | T2 KESWICK-TRINITY 7/98R RPR GYWW | TABLEMTN | ETL.7270.POLE.STPS | 2023-04-27 | 2023-04-27 | 2024-02-15 | On-time | 2024-04-26 | 71 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46037266 | T2 KESWICK-TRINITY 7/98R RPR GYWW | ICW
LC | 126025516 | 005/025 | T2 EI DIABLO-GATES #1 005/025 RPR GYWT | PISMOBCH | ETL.5960.TOWR | 2023-05-01 | 2023-05-01 | 2024-05-01 | Late | 2024-04-30 | -1 | 2024-05-01 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46175229 | T2 EI DIABLO-GATES #1 005/025 RPR GYWT | ICQ
LC | 126002052 | 001/019 | T2 COTTONWOOD-PANORAMA 01/19 BACKFILL | TABLEMTN | ETL.1340.POLE.NWOD | 2023-04-27 | 2023-04-27 | 2024-04-22 | On-time | 2024-04-26 | 4 | 2024-04-27 | 630 | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46036837 | T2 COTTONWOOD-PANORAMA 01/19 BACKFILL | ICW
LC | 126025528 | 005/024 | T2 EI DIABLO-GATES #1 005/024 RPR GYWT | PISMOBCH | ETL.5960.TOWR | 2023-05-01 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46175228 | T2 EI DIABLO-GATES #1 005/024 RPR GYWT | ICQ
LC | 126025646 | 005/104 | T2 WV COLEMAN-SOUTH 005/104 INS HRDW | TABLEMTN | ETL.6450.POLE.WOOD | 2023-05-01 | 2023-05-01 | 2024-05-03 | Late | 2024-04-30 | -3 | 2024-05-01 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 46036959 | T2 WV COLEMAN-SOUTH 005/104 INS HRDW | ICW
LC | 126025955 | 005/027 | T2 EI DIABLO-GATES #1 005/027 RPR GYWT | PISMOBCH | ETL.5960.TOWR | 2023-05-01 | 2023-05-01 | 2024-05-01 | Late | 2024-04-30 | -1 | 2024-05-01 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46175230 | T2 EI DIABLO-GATES #1 005/027 RPR GYWT | ICQ
LC | 126026221 | A006/078 | T2 DI PLMO-ORVIL #2 A06/078 RPL STRW | TABLEMTN | ETL.7740.POLE.WOOD | 2023-05-01 | 2023-04-21 |  | Late | 2024-04-20 |  | 2024-04-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35531672 | T2 DI PLMO-ORVIL #2 A06/078 RPL STRW | 70Y
LC | 126026535 | 000/028 | T2 EI COLLINS PINE TAP 000/028 INS HRDW | TABLEMTN | ETL.7001.INSL.CERA | 2023-05-01 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46037500 | T2 EI COLLINS PINE TAP 000/028 INS HRDW | ICW
LC | 126026714 | 017/349 | T2 EI CARIBOU-WESTWOOD 17/349 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-01 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519126 | T2 EI CARIBOU-WESTWOOD 17/345 RPL STRW | 70Y
LC | 126002092 | 033/142 | T2 EI MORRO BAY-SOLAR 33/142 COTTER | PISMOBCH | ETL.5310.INSL | 2023-04-27 | 2023-04-27 | 2024-02-24 | On-time | 2024-04-26 | 62 | 2024-04-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46073327 | T2 EI MORRO BAY-SOLAR 33/142 COTTER | ICS
LC | 126026965 | 028/001 | T2 EI MNDCNO-WLLTS-FRT BRG 28/1 RPR GYWW | WILLITS | ETL.7550.POLE.NWOD | 2023-05-01 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46261853 | T2 EI MNDCNO-WLLTS-FRT BRG 28/1 RPR GYWW | ICW
LC | 126027000 | 027/008 | T2 EI MNDOCN-WLTS-FRT BRAG 27/8 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2023-05-01 | 2023-05-01 |  | Late | 2024-04-30 |  | 2023-11-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46227529 | T2 EI MNDOCN-WLTS-FRT BRAG 27/8 RPR STRW | ICW
LC | 126027002 | 027/007 | T2 EI MNDCNO-WLLTS-FRT BRG 27/7 RPR POLE | WILLITS | ETL.7550.POLE.WOOD | 2023-05-01 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46227528 | T2 EI MNDCNO-WLLTS-FRT BRG 27/7 RPR POLE | ICW
LC | 126027005 | 027/006 | T2 EI MNDCNO-WLLTS-FRT BRGG 27/6 RPL HRD | WILLITS | ETL.7550.POLE.WOOD | 2023-05-01 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Missing | Hardware-Wood | Install | 46227526 | T2 EI MNDCNO-WLLTS-FRT BRGG 27/6 RPL HRD | ICW
LC | 126027043 | 017/350 | T2 EI CARIBOU-WESTWOOD 17/350 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-01 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519126 | T2 EI CARIBOU-WESTWOOD 17/345 RPL STRW | 70Y
LC | 126002171 | 001/018 | T2 EI COLGATE-PALERMO 001/018 INS DAMW | SACTO | ETL.6500.INSL.NCER | 2023-04-27 | 2023-04-27 | 2024-04-16 | On-time | 2024-04-26 | 10 | 2024-04-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46032257 | T2 EI COLGATE-PALERMO 001/018 INS DAMW | ICW
LC | 126027751 | 012/011 | T2 WV LOWER LAKE-HOMESTKE 12/11 CNCL | WILLITS | ETL.1481.POLE.WOOD | 2023-05-01 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 630 | TLN | CREW | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45763186 | T2 WV LOWER LAKE-HOMESTKE 12/11 RPR IBWW | ICW
LC | 126028058 | 026/005 | T2 DI PHILO JT ELK 26/005C RPR STRW | WILLITS | ETL.7780.POLE.WDPS | 2023-05-01 | 2023-04-20 | 2024-05-22 | Late | 2024-04-19 | -33 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46213853 | T2 DI PHILO JT ELK 26/005C RPR STRW | ICW
LC | 126028072 | 003/027 | T2 DI UKIAH-HPLAND-CLVERDL 3/27 RPL POLE | WILLITS | ETL.4050.POLE.WOOD | 2023-05-01 | 2023-05-01 |  | Late | 2024-04-30 |  | 2023-11-01 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35520172 | T2 DI UKIAH-HPLAND-CLVERDL 3/27 RPL POLE | 70Y
LC | 126028205 | 026/005 | T2 DI PHILO JT ELK 26/005 RPR STRW | WILLITS | ETL.7780.POLE.WDPS | 2023-05-01 | 2023-04-20 | 2024-05-22 | Late | 2024-04-19 | -33 | 2024-04-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46213852 | T2 DI PHILO JT ELK 26/005 RPR STRW | ICW
LC | 126028305 | 006/043 | T2 WV COTTONWOOD #2 6/43 RPR INSS | TABLEMTN | ETL.6630.INSL.NCER | 2023-05-01 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45880237 | T2 WV COTTONWOOD #2 6/43 RPR INSS | ICS
LC | 126003297 | 001/016 | T2 WV GRANITE ROCK TAP 01/16 INS DMPW | MOSSLNDG | ETL.8311.INSL.NCER | 2023-04-27 | 2023-04-27 | 2024-02-13 | On-time | 2024-04-26 | 73 | 2024-04-27 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46081591 | T2 WV GRANITE ROCK TAP 01/16 INS DMPW | ICW
LC | 126004035 | 001/026 | T2 EI COLGATE-PALERMO 001/026 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2023-04-27 | 2023-04-27 | 2023-08-28 | On-time | 2024-04-26 | 242 | 2024-04-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45749524 | T2 EI COLGATE-PALERMO 001/026 RPR STRW | ICW
LC | 126004037 | 000/007 | T2 WV SAN BRUNO TAP 0/7 INS DMPW | METCALF | ETL.7572.INSL | 2023-04-27 | 2023-04-27 | 2024-04-12 | On-time | 2024-04-26 | 14 | 2024-04-27 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46080477 | T2 WV SAN BRUNO TAP 0/7 INS DMPW | ICW
LC | 126004099 | 061/258 | T2 EI RND MTN-TBL MTN#2 61/258 BNT STEEL | TABLEMTN | ETL.6070.TOWR | 2023-04-27 | 2023-04-27 | 2023-11-01 | On-time | 2024-04-26 | 177 | 2024-04-27 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46031691 | T2 EI RND MTN-TBL MTN#2 61/258 BNT STEEL | ICQ
LC | 126004263 | 039/001 | T2 EI MNDCNO-WLLTS-FRT BRG 39/1 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2023-04-27 | 2023-04-27 | 2024-03-05 | On-time | 2024-04-26 | 52 | 2024-04-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46048772 | T2 EI MNDCNO-WLLTS-FRT BRG 39/1 RPR GYWW | ICW
LC | 126030224 | 031/006 | T2 DI PHILO JCT-ELK 031/006L RPR GYWW | WILLITS | ETL.7780.POLE.WDPS | 2023-05-02 | 2023-04-25 | 2024-06-11 | Late | 2024-04-24 | -48 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213847 | T2 DI PHILO JCT-ELK 031/006L RPR GYWW | ICW
LC | 126030305 | 039/254C | T2 EI TRINITY-COTTON 39/254C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-02 | 2023-05-02 | 2024-05-28 | Late | 2024-05-01 | -27 | 2023-11-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046108 | T2 EI TRINITY-COTTON 39/254C RPR GYWW | ICW
LC | 126030371 | 031/006 | T2 DI PHILO JCT-ELK 031/006R RPR GYWW | WILLITS | ETL.7780.POLE.WDPS | 2023-05-02 | 2023-04-25 | 2024-06-11 | Late | 2024-04-24 | -48 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213846 | T2 DI PHILO JCT-ELK 031/006R RPR GYWW | ICW
LC | 126030372 | 031/006 | T2 DI PHILO JCT-ELK 031/006C RPR GYWW | WILLITS | ETL.7780.POLE.WDPS | 2023-05-02 | 2023-04-25 | 2024-06-11 | Late | 2024-04-24 | -48 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213845 | T2 DI PHILO JCT-ELK 031/006C RPR GYWW | ICW
LC | 126030522 | 039/254B | T2 EI TRINITY-COTTON 39/254B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-02 | 2023-05-02 | 2024-05-28 | Late | 2024-05-01 | -27 | 2023-11-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046109 | T2 EI TRINITY-COTTON 39/254B RPR GYWW | ICW
LC | 126004440 | 034/140 | T2 EI DIABLO-MIDWAY #2 34/140 COMPLETE | PISMOBCH | ETL.5970.TOWR | 2023-04-27 | 2023-04-27 | 2024-04-19 | On-time | 2024-04-26 | 7 | 2024-04-27 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46179479 | T2 EI DIABLO-MIDWAY #2 34/140 RPR GYWT | ICQ
LC | 126030906 | 039/254A | T2 EI TRINITY-COTTON 39/254A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-02 | 2023-05-02 | 2024-05-28 | Late | 2024-05-01 | -27 | 2023-11-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046110 | T2 EI TRINITY-COTTON 39/254A RPR GYWW | ICW
LC | 126004474 | 060/254 | T2 EI RND MTN-TBL MTN#2 60/254 BNT STEEL | TABLEMTN | ETL.6070.TOWR | 2023-04-27 | 2023-04-27 | 2023-11-01 | On-time | 2024-04-26 | 177 | 2024-04-27 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46031690 | T2 EI RND MTN-TBL MTN#2 60/254 BNT STEEL | ICQ
LC | 126031686 | 041/267C | T2 EI TRINITY-COTTON 41/267C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-02 | 2023-05-02 | 2024-05-29 | Late | 2024-05-01 | -28 | 2023-11-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46227556 | T2 EI TRINITY-COTTON 41/267C RPR GYWW | ICW
LC | 126004784 | 061/259 | T2 EI RND MTN-TBL MTN#2 61/259 BNT STEEL | TABLEMTN | ETL.6070.TOWR | 2023-04-27 | 2023-04-27 | 2023-11-01 | On-time | 2024-04-26 | 177 | 2024-04-27 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46031692 | T2 EI RND MTN-TBL MTN#2 61/259 BNT STEEL | ICQ
LC | 126005557 | 015/304 | T2 SALINAS-LAURELES 015/304 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-04-27 | 2023-04-27 | 2024-02-28 | On-time | 2024-04-26 | 58 | 2024-04-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507083 | T2 SALINAS-LAURELES 015/304 RPL STRW | 70Y
LC | 126005680 | 009/008 | T2 EI VLY SPRGS-MRTL #1 009/008 RPR INSW | VICTOR | ETL.8240.INSL.NCER | 2023-04-27 | 2023-04-27 | 2024-02-29 | On-time | 2024-04-26 | 57 | 2024-04-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46080907 | T2 EI VLY SPRGS-MRTL #1 009/008 RPR INSW | ICW
LC | 126005725 | 045/394 | T2 EI PIT #1-COTTONWD 45/394 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-04-27 | 2023-04-27 | 2023-10-25 | On-time | 2024-04-26 | 184 | 2024-04-27 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46030993 | T2 EI PIT #1-COTTONWD 45/394 UNBURY | ICQ
LC | 126017185 | 005/075 | T2 DI VLY SPNGS CLY 05/75 RPR IBWW | VICTOR | ETL.8264.POLE.WOOD | 2023-04-29 | 2023-04-27 | 2024-02-01 | On-time | 2024-04-26 | 85 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46080951 | T2 DI VLY SPNGS CLY 05/75 RPR IBWW | ICW
LC | 126032279 | 041/267B | T2 EI TRINITY-COTTON 41/267B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-02 | 2023-05-02 | 2024-05-29 | Late | 2024-05-01 | -28 | 2024-05-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46227555 | T2 EI TRINITY-COTTON 41/267B RPR GYWW | ICW
LC | 126017188 | 005/075 | T2 DI VLY SPNGS CLY 05/75 RPR STRW | VICTOR | ETL.8264.POLE.WOOD | 2023-04-29 | 2023-04-27 | 2024-02-01 | On-time | 2024-04-26 | 85 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46080954 | T2 DI VLY SPNGS CLY 05/75 RPR STRW | ICW
LC | 126017314 | 057/011 | T2 DI ELK-GUALALA 57/11 RPL HRDW | WILLITS | ETL.8410.POLE.WOOD | 2023-04-29 | 2023-04-27 | 2024-01-19 | On-time | 2024-04-26 | 98 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46070985 | T2 DI ELK-GUALALA 57/11 RPL HRDW | ICW
LC | 126017379 | 006/096 | T2 DI VLY SPNGS CLY 06/96 RPL POLE | VICTOR | ETL.8264.POLE.WOOD | 2023-04-29 | 2023-04-27 | 2024-02-03 | On-time | 2024-04-26 | 83 | 2024-04-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514992 | T2 DI VLY SPNGS CLY 06/96 RPL POLE | 70Y
LC | 126017964 | 001/015 | T2 DI COLGATE-SMARTVILL #1 1/15 RPR ANCW | SACTO | ETL.6510.POLE.STPS | 2023-04-29 | 2023-04-27 | 2023-05-09 | On-time | 2024-04-26 | 353 | 2023-10-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45749387 | T2 DI COLGATE-SMARTVILL #1 1/15 RPR ANCW | ICW
LC | 126017965 | 001/015 | T2 DI OLGATE-SMARTVILLE #1 1/15 RPR ANCW | SACTO | ETL.6510.POLE.STPS | 2023-04-29 | 2023-04-27 | 2023-05-09 | On-time | 2024-04-26 | 353 | 2023-10-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45749388 | T2 DI OLGATE-SMARTVILLE #1 1/15 RPR ANCW | ICW
LC | 126017966 | 001/015 | T2 DI COLGATE-SMARTVILL #1 1/15 RPR ANCW | SACTO | ETL.6510.POLE.STPS | 2023-04-29 | 2023-04-27 | 2023-05-09 | On-time | 2024-04-26 | 353 | 2023-10-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45749390 | T2 DI COLGATE-SMARTVILL #1 1/15 RPR ANCW | ICW
LC | 126018085 | 006/089 | T2 DI VLY SPNGS CLY 06/89 RPR INSW | VICTOR | ETL.8264.INSL.NCER | 2023-04-29 | 2023-04-27 | 2024-02-02 | On-time | 2024-04-26 | 84 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46080958 | T2 DI VLY SPNGS CLY 06/89 RPR INSW | ICW
LC | 126020790 | 003/011 | T2 DI LWR LAKE-HOMESTKE 003/011 COTTER | WILLITS | ETL.1481.INSL.CERA | 2023-04-29 | 2023-04-27 | 2023-07-18 | On-time | 2024-04-26 | 283 | 2023-10-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45747929 | T2 DI LWR LAKE-HOMESTKE 003/011 COTTER | ICW
LC | 126035950 | 006/088 | T2 DI VALLEY SPRINGS-CLAY 6/088 RPR GYWW | VICTOR | ETL.8264.POLE.WOOD | 2023-05-02 | 2023-04-27 | 2024-02-02 | On-time | 2024-04-26 | 84 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46080968 | T2 DI VALLEY SPRINGS-CLAY 6/088 RPR GYWW | ICW
LC | 126035952 | 006/088 | T2 DI VALLEY SPRINGS-CLAY 6/088 RPR GRWW | VICTOR | ETL.8264.POLE.WOOD | 2023-05-02 | 2023-04-27 | 2024-02-02 | On-time | 2024-04-26 | 84 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 46080970 | T2 DI VALLEY SPRINGS-CLAY 6/088 RPR GRWW | ICW
LC | 126035955 | 006/088 | T2 DI VALLEY SPRINGS-CLAY 06/088 RMV VEG | VICTOR | ETL.8264.POLE.WOOD | 2023-05-02 | 2023-04-27 | 2023-10-17 | On-time | 2024-04-26 | 192 | 2024-04-27 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126036157 | 007/100 | T2 DI VALLEY SPRINGS-CLAY 7/100 RPR GRWW | VICTOR | ETL.8264.POLE.WOOD | 2023-05-02 | 2023-04-27 | 2024-02-01 | On-time | 2024-04-26 | 85 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 46081017 | T2 DI VALLEY SPRINGS-CLAY 7/100 RPR GRWW | ICW
LC | 126034342 | 019/082 | T2 EI MRRO BAY-SLAR SS #2 19/82 COMPLETE | PISMOBCH | ETL.5310.INSL | 2023-05-02 | 2023-05-02 | 2024-05-09 | Late | 2024-05-01 | -8 | 2024-05-02 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510135 | T2 EI MRRO BAY-SLAR SS #2 19/82 RPL INSS | 93K
LC | 126036323 | 053/264 | T2 DI MALIN-ROUND MTN #2 53/264 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2023-05-02 | 2023-04-27 | 2023-12-20 | On-time | 2024-04-26 | 128 | 2024-04-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46037391 | T2 DI MALIN-ROUND MTN #2 53/264 RPR INSS | ICS
LC | 126036402 | 013/083 | T2 DI CAYUCOS-CMBR 13/83C COMPLETE | PISMOBCH | ETL.8560.POLE.WDPS | 2023-05-02 | 2023-04-27 | 2023-07-26 | On-time | 2024-04-26 | 275 | 2023-07-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45892803 | T2 DI CAYUCOS-CMBR 13/83C RPR GYWW | ICW
LC | 126036424 | 006/094 | T2 DI VLY SPRNGS CLY 6/94 RPR GRWW | VICTOR | ETL.8264.POLE.WOOD | 2023-05-02 | 2023-04-27 | 2023-05-11 | On-time | 2024-04-26 | 351 | 2023-10-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45759753 | T2 DI VLY SPRNGS CLY 6/94 RPR GRWW | ICW
LC | 126036505 | 052/261 | T2 DI MALIN-ROUND MTN#2 52/261 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-05-02 | 2023-04-27 | 2023-08-28 | On-time | 2024-04-26 | 242 | 2024-04-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45758006 | T2 DI MALIN-ROUND MTN#2 52/261 RPR OPGW | ICS
LC | 126036513 | 085/431 | T2 DI MLN-RND MTN #2 85/431 UNBURY | TABLEMTN | ETL.6020.TOWR | 2023-05-02 | 2023-04-27 | 2023-10-25 | On-time | 2024-04-26 | 184 | 2024-04-27 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46030991 | T2 DI MLN-RND MTN #2 85/431 UNBURY | ICQ
LC | 126034383 | 017/346 | T2 EI COLGTE-PALERMO 017/346 RMV ENCRCH | SACTO | ETL.6500.POLE.NWOD | 2023-05-02 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 931 | TLS | INSP | E - Schd Compl Yr 0 | Open | TR2 | Encroachment | Right of Way | Remove
LC | 126036623 | 055/001 | T2 DI ELK-GUALALA 55/1 COTTER | WILLITS | ETL.8410.INSL.NCER | 2023-05-02 | 2023-04-27 | 2024-01-17 | On-time | 2024-04-26 | 100 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46070986 | T2 DI ELK-GUALALA 55/1 COTTER | ICW
LC | 126034669 | 003/074 | T2 EI CSCDE-BNTN-DSCHTS 03/74 RPR STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-02 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046092 | T2 EI CSCDE-BNTN-DSCHTS 03/74 RPR STRW | ICW
LC | 126036670 | 011/158 | T2 DI VALEY SPRINGS-CLAY 11/158 RPR POLE | VICTOR | ETL.8264.POLE.WOOD | 2023-05-02 | 2023-04-27 | 2023-11-17 | On-time | 2024-04-26 | 161 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46049921 | T2 DI VALEY SPRINGS-CLAY 11/158 RPR POLE | ICW
LC | 126036677 | ;009/006 | T2 DI CARIBOU-PLUMAS JCT ;9/6 COA | TABLEMTN | ETL.6290.POLE.NWOD | 2023-05-02 | 2023-04-27 | 2024-03-19 | On-time | 2024-04-26 | 38 | 2024-04-27 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126036706 | 008/118 | T2 DI VLY SPRNGS CLY 8/118 RPL HRDW | VICTOR | ETL.8264.POLE.WOOD | 2023-05-02 | 2023-04-27 | 2024-02-04 | On-time | 2024-04-26 | 82 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46081019 | T2 DI VLY SPRNGS CLY 8/118 RPL HRDW | ICW
LC | 126039973 | ?000/003 | T2 DI SNTH LN-HLF MN BY ;0/3 RPL DAMW | METCALF | ETL.7212.INSL.NCER | 2023-05-03 | 2023-04-27 | 2023-07-21 | On-time | 2024-04-26 | 280 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 45888004 | T2 DI SNTH LN-HLF MN BY ;0/3 RPL DAMW | ICW
LC | 126035329 | 016/067 | T2 EI DIABLO-GATES #1 016/067 CANCEL | PISMOBCH | ETL.5960.TOWR | 2023-05-02 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46175235 | T2 EI DIABLO-GATES #1 016/067 RPR GYWT | ICQ
LC | 126035358 | 026/011 | T2 EI MNDCN-WLLTS-FRT BRG 26/11 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2023-05-02 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521531 | T2 EI MNDCN-WILLITS-FORT BRG 22/2 RPL PL | 70Y
LC | 126035425 | 025/009 | T2 EI PHILO JCT-ELK 25/9C RPR ANCW | WILLITS | ETL.7780.POLE.WDPS | 2023-05-02 | 2023-05-02 | 2024-05-21 | Late | 2024-05-01 | -20 | 2024-05-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46213843 | T2 EI PHILO JCT-ELK 25/9C RPR ANCW | ICW
LC | 126035441 | 026/005 | T2 EI MNDCNO-WLLTS-FRT BRG 26/5 WSH INSW | WILLITS | ETL.7550.INSL.CERA | 2023-05-02 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 622 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Contaminated | Insulator | Ground Wash | 46227533 | T2 EI MNDCNO-WLLTS-FRT BRG 26/5 WSH INSW | ICD
LC | 126045147 | 087/441 | T2 DI MALN-RND MONTAIN#2 87/441 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2023-05-03 | 2023-04-27 | 2024-03-26 | On-time | 2024-04-26 | 31 | 2024-04-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46037392 | T2 DI MALN-RND MONTAIN#2 87/441 RPR INSS | ICS
LC | 126045545 | 057/008 | T2 DI ELK-GUALALA-57/8 UNBURY | WILLITS | ETL.8410.POLE.NWOD | 2023-05-03 | 2023-04-27 | 2024-01-18 | On-time | 2024-04-26 | 99 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46070987 | T2 DI ELK-GUALALA-57/8 UNBURY | ICW
LC | 126045546 | 057/008 | T2 DI ELK-GUALALA 57/8 COTTER | WILLITS | ETL.8410.INSL.NCER | 2023-05-03 | 2023-04-27 | 2024-01-18 | On-time | 2024-04-26 | 99 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46070988 | T2 DI ELK-GUALALA 57/8 COTTER | ICW
LC | 126045618 | 052/260 | T2 DI MALIN-RND MTN #2 52/260 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2023-05-03 | 2023-04-27 | 2023-12-20 | On-time | 2024-04-26 | 128 | 2024-04-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46037390 | T2 DI MALIN-RND MTN #2 52/260 RPR INSS | ICS
LC | 126045829 | 007/107 | T2 DI VLY SPRINGS-CLY 7/107 RPL POLE | VICTOR | ETL.8264.POLE.WOOD | 2023-05-03 | 2023-04-27 | 2024-02-03 | On-time | 2024-04-26 | 83 | 2024-04-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514992 | T2 DI VLY SPNGS CLY 06/96 RPL POLE | 70Y
LC | 126053654 | 007/103 | T2 DI VLLY SPRINGS-CLY 7/103 RPR GRWW | VICTOR | ETL.8264.POLE.WOOD | 2023-05-04 | 2023-04-27 | 2023-05-11 | On-time | 2024-04-26 | 351 | 2023-10-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 45759754 | T2 DI VLLY SPRINGS-CLY 7/103 RPR GRWW | ICW
LC | 126054580 | 055/003 | T2 DI ELK-GUALALA 55/3 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-05-04 | 2023-04-27 | 2024-01-19 | On-time | 2024-04-26 | 98 | 2024-04-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487318 | T2 DI ELK-GUALALA 55/3 RPL POLE | 70Y
LC | 126010853 | 041/006 | T2 EI MNDCNO-WLTS-FRT BRG 41/06 RPR GYWW | WILLITS | ETL.7550.POLE.WOOD | 2023-04-28 | 2023-04-28 | 2024-03-19 | On-time | 2024-04-27 | 39 | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213821 | T2 EI MNDCNO-WLTS-FRT BRG 41/06 RPR GYWW | ICW
LC | 126011395 | 047/414 | T2 EI PIT #1-COTTONWD 47/414 RPR FND | TABLEMTN | ETL.5390.TOWR | 2023-04-28 | 2023-04-28 | 2023-07-05 | On-time | 2024-04-27 | 297 | 2023-10-28 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45770968 | T2 EI PIT #1-COTTONWD 47/414 RPR FND | ICQ
LC | 126011429 | 047/411 | T2 EI PIT #1-COTTONWOOD 47/411 RPR FND | TABLEMTN | ETL.5390.TOWR | 2023-04-28 | 2023-04-28 | 2023-11-13 | On-time | 2024-04-27 | 166 | 2024-04-28 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46044431 | T2 EI PIT #1-COTTONWOOD 47/411 RPR FND | ICQ
LC | 126011654 | 047/409 | T2 EI PIT #1-COTNWD 47/409 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2023-04-28 | 2023-04-28 | 2023-11-02 | On-time | 2024-04-27 | 177 | 2024-04-28 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46044430 | T2 EI PIT #1-COTNWD 47/409 RPR FOND | ICQ
LC | 126036197 | 002/027 | T2 DI COLG-SMRTVLL#2 2/27 RPR GYWW | SACTO | ETL.6520.POLE.NWOD | 2023-05-02 | 2023-04-27 | 2024-05-02 | Late | 2024-04-26 | -6 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46032433 | T2 DI COLG-SMRTVLL#2 2/27 RPR GYWW | ICW
LC | 126036199 | 002/027 | T2 DI COLG-SMRTVLL#2 2/27 RMV VEG | SACTO | ETL.6520.POLE.NWOD | 2023-05-02 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126036228 | 006/129 | T2 DI CARIBOU-PLUMAS JCT 6/129 RPR ANCW | TABLEMTN | ETL.6290.POLE.NWOD | 2023-05-02 | 2023-04-25 | 2024-05-06 | Late | 2024-04-24 | -12 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46037257 | T2 DI CARIBOU-PLUMAS JCT 6/129 RPR ANCW | ICW
LC | 126036229 | :002/014 | T2 DI ROCK CREEK-POE :2/14 RPR GYWS | TABLEMTN | ETL.5630.TOWR | 2023-05-02 | 2023-04-21 | 2024-04-22 | Late | 2024-04-20 | -2 | 2024-04-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46028414 | T2 DI ROCK CREEK-POE :2/14 RPR GYWS | ICS
LC | 126036232 | 001/022 | T2 DI CLGT-SMRTVLL #2 1/022 RPR STRW | SACTO | ETL.6520.POLE.WOOD | 2023-05-02 | 2023-04-27 | 2024-05-02 | Late | 2024-04-26 | -6 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46032434 | T2 DI CLGT-SMRTVLL #2 1/022 RPR STRW | ICW
LC | 126036260 | 084/428 | T2 DI MALIN-RND MTN#2 84/428 RPR GYWT | TABLEMTN | ETL.6020.TOWR | 2023-05-02 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46257566 | T2 DI MALIN-RND MTN#2 84/428 RPR GYWT | ICQ
LC | 126012023 | 047/408 | T2 EI PIT #1-COTTONWOOD 47/408 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2023-04-28 | 2023-04-28 | 2023-11-02 | On-time | 2024-04-27 | 177 | 2024-04-28 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46044429 | T2 EI PIT #1-COTTONWOOD 47/408 RPR FOND | ICQ
LC | 126036372 | 011/155 | T2 DI VALLEY SPRINGS-CLY 11/155 RPL POLE | VICTOR | ETL.8264.POLE.WOOD | 2023-05-02 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525530 | T2 DI VALLEY SPRINGS-CLY 11/155 RPL POLE | 70Y
LC | 126012363 | 016/326 | T2 EI COLGATE-PALERMO 16/326 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2023-04-28 | 2023-04-28 | 2024-04-27 | On-time | 2024-04-27 | 0 | 2024-04-28 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506918 | T2 EI COLGATE-PALERMO 16/326 RPL STRW | 70Y
LC | 126012594 | 006/016 | T2 WV TULUCAY-NAPA #1 6/016 RPR INSW | LAKEVLLE | ETL.8180.INSL.NCER | 2023-04-28 | 2023-04-28 | 2024-01-15 | On-time | 2024-04-27 | 103 | 2024-04-28 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46096602 | T2 WV TULUCAY-NAPA #1 6/016 RPR INSW | ICW
LC | 126013416 | 047/405 | T2 EI PIT #1 COTTONWOOD 047/405 RPR FOND | TABLEMTN | ETL.5390.POLE.STPS | 2023-04-28 | 2023-04-28 | 2023-11-02 | On-time | 2024-04-27 | 177 | 2024-04-28 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46044426 | T2 EI PIT #1 COTTONWOOD 047/405 RPR FOND | ICQ
LC | 126013417 | 047/407 | T2 EI PIT #1-COTTONWD 47/407 RPR FOUND | TABLEMTN | ETL.5390.TOWR | 2023-04-28 | 2023-04-28 | 2023-11-02 | On-time | 2024-04-27 | 177 | 2024-04-28 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46044428 | T2 EI PIT #1-COTTONWD 47/407 RPR FOUND | ICQ
LC | 126013419 | 047/405 | T2 EI PIT #1 COTTONWOOD 047/405 RPR FOND | TABLEMTN | ETL.5390.POLE.STPS | 2023-04-28 | 2023-04-28 | 2023-11-02 | On-time | 2024-04-27 | 177 | 2024-04-28 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46044425 | T2 EI PIT #1 COTTONWOOD 047/405 RPR FOND | ICQ
LC | 126036552 | 026/000 | 126036552LO JCT-ELK 26/000 RPR GYWW | WILLITS | ETL.7780.POLE.WDPS | 2023-05-02 | 2023-04-25 | 2024-06-15 | Late | 2024-04-24 | -52 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213850 | T2 DI PHILO JCT-ELK 26/000 RPR GYWW | ICW
LC | 126036555 | 026/000 | T2 DI PHILO JCT-ELK 26/000R RPL ANCW | WILLITS | ETL.7780.POLE.WDPS | 2023-05-02 | 2023-04-25 | 2024-06-15 | Late | 2024-04-24 | -52 | 2024-04-25 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35522272 | T2 DI PHILO JCT-ELK 025/007 RPL ANCW | 93E
LC | 126013421 | 047/406 | T2 EI PIT #1-COTTONWOOD 47/406 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2023-04-28 | 2023-04-28 | 2023-11-02 | On-time | 2024-04-27 | 177 | 2024-04-28 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46044427 | T2 EI PIT #1-COTTONWOOD 47/406 RPR FOND | ICQ
LC | 126014209 | 016/329 | T2 EI COLGATE-PALERMO 16/329 RMV VEG | SACTO | ETL.6500.POLE.WOOD | 2023-04-28 | 2023-04-28 | 2024-02-08 | On-time | 2024-04-27 | 79 | 2024-04-28 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126014256 | 016/333 | T2 EI COLGATE-PALERMO 016/333 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2023-04-28 | 2023-04-28 | 2024-03-26 | On-time | 2024-04-27 | 32 | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46032424 | T2 EI COLGATE-PALERMO 016/333 RPR STRW | ICW
LC | 126014257 | 016/332 | T2 EI COLGATE-PALERMO 16/332 RPR INSW | SACTO | ETL.6500.INSL.CERA | 2023-04-28 | 2023-04-28 | 2024-04-26 | On-time | 2024-04-27 | 1 | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46032425 | T2 EI COLGATE-PALERMO 16/332 RPR INSW | ICW
LC | 126036640 | 002/022 | T2 DI LKVILL-SNOMA#1 2/22 RPR JUMS | LAKEVLLE | ETL.2070.INSL.NCER | 2023-05-02 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46204132 | T2 DI LKVILL-SNOMA#1 2/22 RPR JUMS | ICS
LC | 126036641 | 002/022 | T2 DI LKVILL-SNOMA#1 2/22 RPL INSS | LAKEVLLE | ETL.2063.INSL.NCER | 2023-05-02 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31677637 | T2 DI LKVILL-SNOMA#1 2/22 RPL INSS | 93K
LC | 126036642 | 002/022 | T2 DI LKVILL-SNOMA#2 2/22 RPL INSS | LAKEVLLE | ETL.2070.INSL.NCER | 2023-05-02 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31677664 | DI LKEVIL SNOMA#2 RPL INSS IN 2 TWRS. | 93K
LC | 126036663 | ;002/015 | T2 DI CARIBOU #2 ;002/015 RPR CRSW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-02 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46037169 | T2 DI CARIBOU #2 ;002/015 RPR CRSW | ICW
LC | 126014767 | 012/002 | T2 EI VLY SPRNGS-MRTL #1 12/2 RPL HRDD | VICTOR | ETL.8240.POLE.WOOD | 2023-04-28 | 2023-04-28 | 2024-01-09 | On-time | 2024-04-27 | 109 | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46080933 | T2 EI VLY SPRNGS-MRTL #1 12/2 RPL HRDD | ICW
LC | 126014772 | 012/002 | T2 EI VLY SPRINGS-MRTL #1 12/2 RPR INSW | VICTOR | ETL.8240.INSL.NCER | 2023-04-28 | 2023-04-28 | 2024-01-09 | On-time | 2024-04-27 | 109 | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46080943 | T2 EI VLY SPRINGS-MRTL #1 12/2 RPR INSW | ICW
LC | 126036678 | 036/003A | T2 DI PHILO JCT-ELK 36/3A RPR GYWW | WILLITS | ETL.7780.POLE.WOOD | 2023-05-02 | 2023-04-25 | 2024-05-24 | Late | 2024-04-24 | -30 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213844 | T2 DI PHILO JCT-ELK 36/3A RPR GYWW | ICW
LC | 126014927 | 038/176A | T2 WV RND MN-TBL MTN #1 38/176A INS HRDS | TABLEMTN | ETL.6060.TOWR | 2023-04-28 | 2023-04-28 | 2024-04-17 | On-time | 2024-04-27 | 10 | 2024-04-28 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Steel | Install | 46037404 | T2 WV RND MN-TBL MTN #1 38/176A INS HRDS | ICS
LC | 126015309 | 016/331 | T2 EI CARIBOU-WESTWOOD 16/331 RPR POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2023-04-28 | 2023-04-28 | 2024-03-13 | On-time | 2024-04-27 | 45 | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46037259 | T2 EI CARIBOU-WESTWOOD 16/331 RPR POLE | ICW
LC | 126015349 | 016/327 | T2 EI CARIBOU-WESTWOOD 16/327 RPR INSW | TABLEMTN | ETL.6300.INSL | 2023-04-28 | 2023-04-28 | 2024-03-18 | On-time | 2024-04-27 | 40 | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46045957 | T2 EI CARIBOU-WESTWOOD 16/327 RPR INSW | ICW
LC | 126036817 | 001/011 | T2 DI PIT #7 TAP 1/11L RPR SHLD | TABLEMTN | ETL.5442.POLE.STPS | 2023-05-02 | 2023-04-25 | 2024-06-26 | Late | 2024-04-24 | -63 | 2024-04-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Wood | Repair | 46219745 | T2 DI PIT #7 TAP 1/11L RPR SHLD | ICW
LC | 126015988 | 000/006 | T2 EI APPLE HILL #1 TAP 0/6 RPR INSW | SACTO | ETL.1531.INSL | 2023-04-28 | 2023-04-28 | 2023-05-03 | On-time | 2024-04-27 | 360 | 2024-04-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45748014 | T2 EI APPLE HILL #1 TAP 0/6 RPR INSW | ICW
LC | 126016233 | 024/193 | T2 WV CRESTA-RIO OSO 24/193 RPR INSW | TABLEMTN | ETL.4590.INSL.NCER | 2023-04-28 | 2023-04-28 | 2024-02-23 | On-time | 2024-04-27 | 64 | 2024-04-28 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46037314 | T2 WV CRESTA-RIO OSO 24/193 RPR INSW | ICS
LC | 126036523 | 010/008 | T2 DI FORT BRAGG-ELK 10/8 RMV VEG | WILLITS | ETL.2060.POLE.NWOD | 2023-05-02 | 2023-04-28 | 2024-04-04 | On-time | 2024-04-27 | 23 | 2024-04-28 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126045105 | 057/001 | T2 DI FORT ROSS-GUALALA 57/1 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-05-03 | 2023-04-28 | 2023-11-01 | On-time | 2024-04-27 | 178 | 2024-04-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45757810 | T2 DI FORT ROSS-GUALALA 57/1 RPR INSW | ICW
LC | 126039505 | 043/283 | T2 EI TRINITY-COTTONWD 043/283 RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-03 | 2023-05-03 |  | Late | 2024-05-02 |  | 2023-11-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046104 | T2 EI TRINITY-COTTONWD 043/283 RPR GYWW | ICW
LC | 126045530 | 046/003 | T2 DI FORT RSS-GUALA 46/3 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-05-03 | 2023-04-28 | 2023-08-15 | On-time | 2024-04-27 | 256 | 2023-07-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45757809 | T2 DU FT RSS-GUALA 46/3 RPR INSW | ICW
LC | 126045626 | 001/012 | T2 DI LTNVLL-COVEL 1/12 RMV VEG | WILLITS | ETL.7390.POLE.WOOD | 2023-05-03 | 2023-04-28 | 2024-03-18 | On-time | 2024-04-27 | 40 | 2024-04-28 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126045662 | 009/067 | T2 DI ROCK CREEK-POE 9/067 RPR FOND | TABLEMTN | ETL.5630.TOWR | 2023-05-03 | 2023-04-28 | 2023-12-28 | On-time | 2024-04-27 | 121 | 2024-04-28 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46049865 | T2 DI ROCK CREEK-POE 9/067 RPR FOND | ICQ
LC | 126045722 | 082/416 | T2 DI MALIN-RND MNT #2 82/416 RPR SHIELD | TABLEMTN | ETL.6020.TOWR | 2023-05-03 | 2023-04-28 | 2024-01-12 | On-time | 2024-04-27 | 106 | 2024-04-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46037395 | T2 DI MALIN-RND MNT #2 82/416 RPR SHIELD | ICS
LC | 126045727 | 057/003 | T2 DI FT RSS-GUALA 57/3 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-05-03 | 2023-04-28 | 2023-11-01 | On-time | 2024-04-27 | 178 | 2023-07-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45757811 | T2 DI FT RSS-GUALA 57/3 RPR INSW | ICW
LC | 126045810 | 006/118 | T2 DI VALLEY SPRINGS #2 06/118L RPR GYWW | VICTOR | ETL.9460.POLE.WDPS | 2023-05-03 | 2023-04-28 | 2024-02-15 | On-time | 2024-04-27 | 72 | 2024-04-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46081042 | T2 DI VALLEY SPRINGS #2 06/118L RPR GYWW | ICW
LC | 126045814 | 006/118 | T2 DI VALLEY SPRINGS #2 06/118C RPR GYWW | VICTOR | ETL.9460.POLE.WDPS | 2023-05-03 | 2023-04-28 | 2024-02-15 | On-time | 2024-04-27 | 72 | 2024-04-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46081044 | T2 DI VALLEY SPRINGS #2 06/118C RPR GYWW | ICW
LC | 126040229 | 024/000 | T2 EI MI-WUK-CURTIS 24/0 RPR STRW | VICTOR | ETL.1073.POLE.WDPS | 2023-05-03 | 2023-05-03 |  | Late | 2024-05-02 |  | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46058678 | T2 EI MI-WUK-CURTIS 24/000 RPR STRW | ICW
LC | 126045815 | 006/118 | T2 DI VALLEY SPRINGS #2 06/118L RPR POLE | VICTOR | ETL.9460.POLE.WDPS | 2023-05-03 | 2023-04-28 | 2024-02-15 | On-time | 2024-04-27 | 72 | 2024-04-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081046 | T2 DI VALLEY SPRINGS #2 06/118L RPR POLE | ICW
LC | 126040673 | 042/278C | T2 EI TRINITY-COTTON 42/278C RPR POLE | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-03 | 2023-05-03 |  | Late | 2024-05-02 |  | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046153 | T2 EI TRINITY-COTTON 42/278C RPR EROSION | ICW
LC | 126045851 | 004/007 | F | WILLITS | ETL.7540.POLE.NWOD | 2023-05-03 | 2023-04-28 | 2023-06-12 | On-time | 2024-04-27 | 320 | 2023-10-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45753058 | T2 DI MNDCNO-WLLTS 004/007 RPR ANCW | ICW
LC | 126054197 | 000/004 | T2 DI ROCK CREEK-POE 0/4 UNBURY | TABLEMTN | ETL.5630.TOWR | 2023-05-04 | 2023-04-28 | 2024-01-08 | On-time | 2024-04-27 | 110 | 2024-04-28 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46049864 | T2 DI ROCK CREEK-POE 0/4 UNBURY | ICQ
LC | 126054553 | A001/018 | T2 DI SMRTVLLE-CMP FR WST A1/18 RMV NEST | SACTO | ETL.7970.POLE.NWOD | 2023-05-04 | 2023-04-28 | 2024-01-04 | On-time | 2024-04-27 | 114 | 2024-04-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 46032438 | T2 DI SMRTVLLE-CMP FR WST A1/18 RMV NEST | ICW
LC | 126054554 | A001/018 | T2 DI SMRTVLLE-CMP FR WST A1/18 RPR GYWW | SACTO | ETL.7970.POLE.NWOD | 2023-05-04 | 2023-04-28 | 2023-12-20 | On-time | 2024-04-27 | 129 | 2024-04-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46032439 | T2 DI SMRTVLLE-CMP FR WST A1/18 RPR GYWW | ICW
LC | 126054629 | 010/005 | T2 DI FORT BRAGG-ELK 10/5 RMV VEG | WILLITS | ETL.2060.POLE.WOOD | 2023-05-04 | 2023-04-28 | 2024-04-11 | On-time | 2024-04-27 | 16 | 2024-04-28 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126055968 | 003/005 | T2 DI MENDO-HARTLY 3/5 COTTER | WILLITS | ETL.7510.INSL.NCER | 2023-05-05 | 2023-04-28 | 2024-01-26 | On-time | 2024-04-27 | 92 | 2024-04-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46089485 | T2 DI MENDO-HARTLY 3/5 COTTER | ICW
LC | 126056096 | 004/006 | T2 DI MENDOCINO-HARTLEY 4/6C RPL POLE | WILLITS | ETL.7510.POLE.WDPS | 2023-05-05 | 2023-04-28 | 2023-09-21 | On-time | 2024-04-27 | 219 | 2024-04-28 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31662271 | T2 EI MENDOCINO-HARTLEY 4/5 RPL POLE | 70Y
LC | 126056098 | 004/006 | T2 DI MENDOCINO-HARTLEY 4/6R RPL POLE | WILLITS | ETL.7510.POLE.WDPS | 2023-05-05 | 2023-04-28 | 2023-09-21 | On-time | 2024-04-27 | 219 | 2024-04-28 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31662271 | T2 EI MENDOCINO-HARTLEY 4/5 RPL POLE | 70Y
LC | 126042751 | 008/146 | T2 EI PT #1-HT CRK #2-BNY 8/146 COTTER | TABLEMTN | ETL.7040.INSL.NCER | 2023-05-03 | 2023-05-03 | 2024-05-14 | Late | 2024-05-02 | -12 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046163 | T2 EI PT #1-HT CRK #2-BNY 8/146 RPL HRDD | ICW
LC | 126056196 | 083/423 | T2 DI MALIN-ROUND MTN #2 83/423 UNBURY | TABLEMTN | ETL.6020.TOWR | 2023-05-05 | 2023-04-28 | 2023-12-13 | On-time | 2024-04-27 | 136 | 2024-04-28 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46044420 | T2 DI MALIN-ROUND MTN #2 83/423 UNBURY | ICQ
LC | 126043570 | 008/145 | T2 EI PT #1-HT CRK #2-BNY 8/145 RPR STRW | TABLEMTN | ETL.7040.POLE.WOOD | 2023-05-03 | 2023-05-03 | 2024-05-14 | Late | 2024-05-02 | -12 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046162 | T2 EI PT #1-HT CRK #2-BNY 8/146 RPR STRW | ICW
LC | 126043636 | 016/084 | T2NT EI RND MT-TBL MT #1 16/84 RMV VEG | TABLEMTN | ETL.6070.TOWR | 2023-05-03 | 2023-05-03 |  | Late | 2024-05-02 |  | 2024-05-03 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126043748 | 008/144 | T2 EI PT #1-HT CRK #2-BNY 8/144 RPR STRW | TABLEMTN | ETL.7040.POLE.WOOD | 2023-05-03 | 2023-05-03 | 2024-05-13 | Late | 2024-05-02 | -11 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046161 | T2 EI PT #1-HT CRK #2-BNY 8/144 RPR STRW | ICW
LC | 126043945 | 021/199 | T2 WV UKH HPLND CLVDL 021/199 RPL POLE | WILLITS | ETL.4050.POLE.WOOD | 2023-05-03 | 2023-05-03 |  | Late | 2024-05-02 |  | 2024-05-03 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35520173 | T2 WV UKH HPLND CLVDL 021/199 RPL POLE | 70Y
LC | 126044469 | 007/086 | T2 EI DRUM-SUMMIT #1 7/86 COMPLETED | SACTO | ETL.1440.POLE.WDPS | 2023-05-03 | 2023-05-03 | 2024-05-15 | Late | 2024-05-02 | -13 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046412 | T2 EI DRUM-SUMMIT #1 7/86 RPR GYWW | ICW
LC | 126044473 | 007/088C | T2 EI DRUM-SUMMIT #1 7/88C RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-05-03 | 2023-05-03 | 2024-05-16 | Late | 2024-05-02 | -14 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046414 | T2 EI DRUM-SUMMIT #1 7/088C RPR GYW | ICW
LC | 126044479 | 007/088B | T2 EI DRUM-SUMMIT #1 7/88B RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-05-03 | 2023-05-03 | 2024-05-16 | Late | 2024-05-02 | -14 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046417 | T2 EI DRUM-SUMMIT #1 7/088B RPR GYW | ICW
LC | 126056453 | :003/019 | T2 DI ROCK CREEK-POE :3/19 COTTER | TABLEMTN | ETL.5630.INSL.CERA | 2023-05-05 | 2023-04-28 | 2024-02-28 | On-time | 2024-04-27 | 59 | 2024-04-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46037319 | T2 DI ROCK CREEK-POE :3/19 COTTER | ICS
LC | 126063449 | 008/084 | T2 DI PIT #5-ROUND MTN #1 8/84R RPR GYWW | TABLEMTN | ETL.5420.POLE.STPS | 2023-05-06 | 2023-04-28 | 2024-01-09 | On-time | 2024-04-27 | 109 | 2024-04-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46037381 | T2 DI PIT #5-ROUND MTN #1 8/84R RPR GYWW | ICW
LC | 126063851 | :004/029A | T2 DI ROCK CREEK-POE :4/29A RPR GYWS | TABLEMTN | ETL.5630.POLE.NWOD | 2023-05-06 | 2023-04-28 | 2024-04-22 | On-time | 2024-04-27 | 5 | 2024-04-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46072122 | T2 DI ROCK CREEK-POE :4/29A RPR GYWS | ICS
LC | 126044984 | 012/171 | T2 DI VALLEY SPRNGS-CLY 12/171 RPL STRW | VICTOR | ETL.8264.POLE.WOOD | 2023-05-03 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514993 | T2 DI VALEY SPRNGS-CLAY 12/167 RPL POLE | 70Y
LC | 126063917 | :004/029B | T2 DI ROCK CREEK-POE :4/29B RPR GYWS | TABLEMTN | ETL.5630.POLE.NWOD | 2023-05-06 | 2023-04-28 | 2024-04-22 | On-time | 2024-04-27 | 5 | 2024-04-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46072123 | T2 DI ROCK CREEK-POE :4/29B RPR GYWS | ICS
LC | 126064108 | :004/029C | T2 DI ROCK CREEK-POE :4/29C RPR GYWS | TABLEMTN | ETL.5630.POLE.NWOD | 2023-05-06 | 2023-04-28 | 2024-04-22 | On-time | 2024-04-27 | 5 | 2024-04-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46072124 | T2 DI ROCK CREEK-POE :4/29C RPR GYWS | ICS
LC | 126228839 | 001/021AA | T2 DI MTN QUARRIES 1/21AA R RPR GYWW | SACTO | ETL.6991.POLE.STPS | 2023-05-25 | 2023-04-28 | 2023-12-18 | On-time | 2024-04-27 | 131 | 2024-04-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046473 | T2 DI MTN QUARRIES 1/21AA R RPR GYWW | ICW
LC | 126045163 | 030/162 | T2 EI EXCHQUER-INDN FLT 30/162 RMV VEG | FRESNO | ETL.8650.POLE.NWOD | 2023-05-03 | 2023-05-03 |  | Late | 2024-05-02 |  | 2024-05-03 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126018569 | 048/423 | T2 EI PIT #1-COTTONWOOD 48/423 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2023-04-29 | 2023-04-29 | 2023-11-07 | On-time | 2024-04-28 | 173 | 2024-04-29 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46044433 | T2 EI PIT #1-COTTONWOOD 48/423 RPR FOND | ICQ
LC | 126018596 | 020/165 | T2 EI MDDL FRK-GLD HLL 020/165R RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2023-04-29 | 2023-04-29 | 2024-02-13 | On-time | 2024-04-28 | 75 | 2024-04-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46032429 | T2 EI MDDL FRK-GLD HLL 020/165R RPR GYWW | ICW
LC | 126019023 | 027/400 | T2 EI CLAY-MARTEL 27/400 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2023-04-29 | 2023-04-29 | 2023-11-27 | On-time | 2024-04-28 | 153 | 2024-04-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46069026 | T2 EI CLAY-MARTEL 27/400 RPR STRW | ICW
LC | 126045280 | 019/176 | T2 DI BRIDGEVLLE-CTTNWD 19/176L RPL POLE | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-03 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501390 | T2 DI BRDGVIL CTTNWD RPL 7 STRCTS | 70Y
LC | 126045281 | 019/176 | T2 DI BRIDGEVLLE-CTTNWD 19/176R RPL POLE | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-03 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501390 | T2 DI BRDGVIL CTTNWD RPL 7 STRCTS | 70Y
LC | 126045298 | 007/004 | T2 DI CARIBU-PLM JCT 7/4 RPL STRW | TABLEMTN | ETL.6290.POLE.WOOD | 2023-05-03 | 2023-04-26 | 2024-05-07 | Late | 2024-04-25 | -12 | 2024-04-26 | 372T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518836 | T2 DI CARIBU-PLM JCT 7/4 RPL STRW | 70Y
LC | 126019098 | 034/235A | T2 EI TRINITY-COTTONWOOD 34/235A RPR GYW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-04-29 | 2023-04-29 | 2023-07-28 | On-time | 2024-04-28 | 275 | 2023-10-29 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45758192 | T2 EI TRINITY-COTTONWOOD 34/235A RPR GYW | ICS
LC | 126045453 | 006/132 | T2 DI CRBU-PLMS JCT-NWD 6/132 RPR ANCW | TABLEMTN | ETL.6290.POLE.NWOD | 2023-05-03 | 2023-04-27 | 2024-05-06 | Late | 2024-04-26 | -10 | 2023-10-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46037258 | T2 DI CARIBOU-PLUMAS JCT-NONWD 6/132 RPR | ICW
LC | 126019099 | 027/402 | T2 EI CLAY-MARTEL 27/402 RPR STRW | VICTOR | ETL.8250.POLE.WOOD | 2023-04-29 | 2023-04-29 | 2023-11-27 | On-time | 2024-04-28 | 153 | 2024-04-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46069027 | T2 EI CLAY-MARTEL 27/402 RPR STRW | ICW
LC | 126019389 | 034/235C | T2 EI TRINITY-CTTNWD 034/235C RPR ANCS | TABLEMTN | ETL.4040.POLE.NWOD | 2023-04-29 | 2023-04-29 | 2023-07-28 | On-time | 2024-04-28 | 275 | 2023-10-29 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45752885 | T2 EI TRINITY-CTTNWD 034/235C RPR ANCS | ICS
LC | 126019447 | 021/166 | T2 EI MDDL FRK-GLD HLL 021/166R RPL POLE | SACTO | ETL.5140.POLE.WDPS | 2023-04-29 | 2023-04-29 | 2023-10-13 | On-time | 2024-04-28 | 198 | 2024-04-29 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31635930 | T3 DI MID FRK-GLD HIL RPL POLES | 70Y
LC | 126045549 | 035/001 | T2 DI BRDGVL-GRBRVL 35/1 RPR INSS | EUREKA | ETL.6220.INSL.NCER | 2023-05-03 | 2023-04-28 | 2024-05-01 | Late | 2024-04-27 | -4 | 2024-04-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45752867 | T2 DI BRIDGEVILLE-GARBERVLE 35/1 COTTER | ICS
LC | 126019448 | 021/166 | T2 EI MDDL FRK-GLD HLL 021/166C RPL POLE | SACTO | ETL.5140.POLE.WDPS | 2023-04-29 | 2023-04-29 | 2023-10-13 | On-time | 2024-04-28 | 198 | 2024-04-29 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31635930 | T3 DI MID FRK-GLD HIL RPL POLES | 70Y
LC | 126019450 | 021/166 | T2 EI MDDL FRK-GLD HLL 021/166L RPL POLE | SACTO | ETL.5140.POLE.WDPS | 2023-04-29 | 2023-04-29 | 2023-10-13 | On-time | 2024-04-28 | 198 | 2024-04-29 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31635930 | T3 DI MID FRK-GLD HIL RPL POLES | 70Y
LC | 126045625 | 001/012 | T2 DI LTNVLL-COVEL 1/12 RPL HRDD | WILLITS | ETL.7390.POLE.WOOD | 2023-05-03 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46219459 | T2 DI LTNVLL-COVEL 1/12 RPL HRDD | ICW
LC | 126019470 | 034/235C | T2 EI TRINITY-COTTONWOOD 34/235C RPR GYW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-04-29 | 2023-04-29 | 2023-07-28 | On-time | 2024-04-28 | 275 | 2023-10-29 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45752884 | T2 EI TRINITY-COTTONWOOD 34/235C RPR GYW | ICS
LC | 126045632 | 006/132 | T2 DI CARIBOU #2-6/132 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-03 | 2023-04-27 |  | Late | 2024-04-26 |  | 2023-10-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46233793 | T2 DI CARIBOU #2-6/132 RPR GYWW | ICW
LC | 126045648 | 000/014 | T2 DI CLGT-SMRTVLL 000/014R RPR GYWW | SACTO | ETL.6510.POLE.STPS | 2023-05-03 | 2023-04-26 | 2024-05-06 | Late | 2024-04-25 | -11 | 2023-10-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46032436 | T2 DI CLGT-SMRTVLL 000/014R RPR GYWW | ICW
LC | 126019715 | 048/417 | T2 EI PIT #1-COTTONWOOD 48/417 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2023-04-29 | 2023-04-29 | 2023-11-13 | On-time | 2024-04-28 | 167 | 2024-04-29 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46044432 | T2 EI PIT #1-COTTONWOOD 48/417 RPR FOND | ICQ
LC | 126045671 | 010/083 | T2 DI PIT#6-JCT ROUND MTN 10/83 RPL INSS | TABLEMTN | ETL.5440.INSL.CERA | 2023-05-03 | 2023-04-28 | 2024-06-23 | Late | 2024-04-27 | -57 | 2024-04-28 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35514086 | T2 DI PIT#6-JCT ROUND MTN 10/83 RPL INSS | 93K
LC | 126045720 | 008/077 | T2 DI PIT #5-RM #1 8/77L RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2023-05-03 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526327 | T2 DI PIT#5-RND MT#1 RPL 4 STRW | 70Y
LC | 126045721 | 008/077 | T2 DI PIT#5-RM#1 8/77R RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2023-05-03 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526327 | T2 DI PIT#5-RND MT#1 RPL 4 STRW | 70Y
LC | 126019771 | 074/532 | T2 EI BRIDGEVILLE-COTTON 74/532 RPR FOND | EUREKA | ETL.1110.TOWR | 2023-04-29 | 2023-04-29 | 2023-11-09 | On-time | 2024-04-28 | 171 | 2024-04-29 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46044438 | T2 EI BRIDGEVILLE-COTTON 74/532 RPR FOND | ICQ
LC | 126019785 | 010/013 | T2 EI VLY SPRS-MRTL #1 10/13 RPL STRW | VICTOR | ETL.8240.POLE.WOOD | 2023-04-29 | 2023-04-29 | 2023-07-12 | On-time | 2024-04-28 | 291 | 2023-10-29 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31649138 | T2 EI VLY SPRS-MRTL #1 10/13 RPL STRW | 70Y
LC | 126045728 | 057/003 | T2 DI FORT ROSS-GUALALA 57/3 RPR STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-03 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46045939 | T2 DI FORT ROSS-GUALALA 57/3 RPR STRW | ICW
LC | 126045741 | 001/015 | T2 DI CLGT-SMRTVL #2 001/015 RPR STRW | SACTO | ETL.6520.POLE.WDPS | 2023-05-03 | 2023-04-27 | 2024-05-03 | Late | 2024-04-26 | -7 | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46032437 | T2 DI CLGT-SMRTVL #2 001/015 RPR STRW | ICW
LC | 126019938 | 021/167 | T2 EI MDDL FRK-GLD HLL 021/167R RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2023-04-29 | 2023-04-29 | 2024-02-13 | On-time | 2024-04-28 | 75 | 2024-04-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46032431 | T2 EI MDDL FRK-GLD HLL 021/167R RPR GYWW | ICW
LC | 126020908 | 008/069A | T2 EI TRINITY-COTTONWOOD 8/69A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-04-29 | 2023-04-29 | 2023-08-28 | On-time | 2024-04-28 | 244 | 2023-10-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45916259 | T2 EI TRINITY-COTTONWOOD 8/69A RPR GYWW | ICW
LC | 126021026 | 008/069B | T2 EI TRINITY-COTTONWOOD 8/69B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-04-29 | 2023-04-29 | 2023-08-28 | On-time | 2024-04-28 | 244 | 2024-04-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45986451 | T2 EI TRINITY-COTTONWOOD 8/69B RPR GYWW | ICW
LC | 126021358 | 021/171 | T2 EI MDDL FRK-GLD HLL 21/171R RPL POLE | SACTO | ETL.5140.POLE.WDPS | 2023-04-29 | 2023-04-29 | 2023-10-21 | On-time | 2024-04-28 | 190 | 2024-04-29 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31635930 | T3 DI MID FRK-GLD HIL RPL POLES | 70Y
LC | 126021374 | 021/171 | T2 EI MDDL FRK-GLD HLL 21/171L RPL POLE | SACTO | ETL.5140.POLE.WDPS | 2023-04-29 | 2023-04-29 | 2023-10-21 | On-time | 2024-04-28 | 190 | 2024-04-29 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31635930 | T3 DI MID FRK-GLD HIL RPL POLES | 70Y
LC | 126045868 | 007/017 | T2 DI MONTE RIO-FULTON 7/17 RPL TIED | LAKEVLLE | ETL.7630.INSL.CERA | 2023-05-03 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46031744 | T2 DI MONTE RIO-FULTON 07/17 RPL TIEW | ICW
LC | 126047006 | 004/009 | T2 EI LAYTONVILLE-COVELO 004/09 RPL POLE | WILLITS | ETL.7390.POLE.WOOD | 2023-05-04 | 2023-05-03 |  | Late | 2024-05-02 |  | 2024-05-03 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35522929 | T2 EI LAYTONVILLE-COVELO 004/09 RPL POLE | 70Y
LC | 126429377 | 020/165 | T2 EI MID FRK-GLD HLL 20/165L RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2023-06-22 | 2023-04-29 | 2024-02-13 | On-time | 2024-04-28 | 75 | 2024-04-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46032460 | T2 EI MID FRK-GLD HLL 20/165L RPR GYWW | ICW
LC | 126025428 | 010/200 | T2 VALLEY SPRINGS #1 010/200 RPR INSW | VICTOR | ETL.8210.INSL.NCER | 2023-05-01 | 2023-05-01 | 2023-10-28 | On-time | 2024-04-30 | 185 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45989867 | T2 VALLEY SPRINGS #1 010/200 RPR INSW | ICW
LC | 126025517 | 005/024 | T2 EI DIABLO-GATES #1 005/024 MASTIC | PISMOBCH | ETL.5960.TOWR | 2023-05-01 | 2023-05-01 | 2023-11-11 | On-time | 2024-04-30 | 171 | 2024-05-01 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46051192 | T2 EI DIABLO-GATES #1 005/024 MASTIC | ICQ
LC | 126027378 | 000/008 | T2NT WV CHRISTIE-WILLW PASS 0/8 RPR JMPW | CONCORD | ETL.6370.INSL.NCER | 2023-05-01 | 2023-05-01 | 2024-02-22 | On-time | 2024-04-30 | 68 | 2024-05-01 | 508 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31629701 | T2 DI CHRISTIE-WLLOW PSS 0/8 RPL INSW | 93I
LC | 126048088 | 052/468 | T2 EI PIT #1-COTTONWOOD 52/468 RPR GYWT | TABLEMTN | ETL.5390.TOWR | 2023-05-04 | 2023-05-04 |  | Late | 2024-05-03 |  | 2024-05-04 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46257407 | T2 EI PIT #1-COTTONWOOD 52/468 RPR GYWT | ICQ
LC | 126048174 | 043/287B | T2 EI TRINITY-COTTON 43/287B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-04 | 2023-05-04 |  | Late | 2024-05-03 |  | 2023-11-04 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46217379 | T2 EI TRINITY-COTTON 43/287B RPR GYWW | ICW
LC | 126048184 | 043/287A | T2 EI TRINITY-COTTON 43/287A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-04 | 2023-05-04 |  | Late | 2024-05-03 |  | 2023-11-04 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46217378 | T2 EI TRINITY-COTTON 43/287A RPR GYWW | ICW
LC | 126049091 | 024/002 | T2 GRBERVIL-LAYTNVIL 24/02 RPR JUMW | WILLITS | ETL.8365.INSL.NCER | 2023-05-04 | 2023-05-04 |  | Late | 2024-05-03 |  | 2024-05-04 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46236307 | T2 GRBERVIL-LAYTNVIL 24/02 RPR JUMW | ICW
LC | 126029028 | X005/024 | T2 EI DIABLO-MESA X5/24 RPR FOND | PISMOBCH | ETL.4620.TOWR | 2023-05-01 | 2023-05-01 | 2023-11-11 | On-time | 2024-04-30 | 171 | 2024-05-01 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46051193 | T2 EI DIABLO-MESA X5/24 RPR FOND | ICQ
LC | 126049311 | 022/005 | T2 EI MNDCNO-WLTS-FRT BRG 22/5 RPR POLE | WILLITS | ETL.7550.POLE.WOOD | 2023-05-04 | 2023-05-04 |  | Late | 2024-05-03 |  | 2024-05-04 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46227561 | T2 EI MNDCNO-WLTS-FRT BRG 22/5 RPR POLE | ICW
LC | 126049426 | 043/287C | T2 EI TRINITY-COTTON 43/287C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-04 | 2023-05-04 |  | Late | 2024-05-03 |  | 2023-11-04 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46217440 | T2 EI TRINITY-COTTON 43/287C RPR GYWW | ICW
LC | 126049493 | 027/322 | T2 EI DRUM-SUMMIT #2 027/322 INST HNG PL | SACTO | ETL.1450.TOWR | 2023-05-04 | 2023-05-03 |  | Late | 2024-05-02 |  | 2024-05-03 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | Missing | Hardware-Tower | Install | 45751839 | T2 EI DRUM-SUMMIT #2 027/322 INST HNG PL | ICQ
LC | 126029106 | 079/401 | T2 EI MALIN-ROND MNTN #2 79/401 RPL ANCS | TABLEMTN | ETL.6020.TOWR | 2023-05-01 | 2023-05-01 | 2023-07-24 | On-time | 2024-04-30 | 281 | 2023-08-01 | 93Z | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Replace | 31643847 | T2 MALIN-ROUND MONTIN #2 79/401 RPL ANCS | 93Z
LC | 126054399 | 023/207 | T2 DI BRDGVIL-COTONWD 23/207 RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-04 | 2023-05-01 | 2023-12-01 | On-time | 2024-04-30 | 151 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046117 | T2 DI BRDGVIL-COTONWD 23/207 RPR GYWW | ICW
LC | 126049781 | 001/030-GUY | T2 EI JFFRSN-STNFRD 1/30-GUY RMV VEG | METCALF | ETL.7220.POLE.WOOD | 2023-05-04 | 2023-05-04 |  | Late | 2024-05-03 |  | 2024-05-04 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Trim
LC | 126049782 | 001/030-GUY | T2 EI JFFRSN-STNFRD 1/30-GUY RPL STRW | METCALF | ETL.7220.POLE.WOOD | 2023-05-04 | 2023-05-04 | 2024-05-23 | Late | 2024-05-03 | -20 | 2024-05-04 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507602 | T2 DI JEFFERSON-STANFORD 1/30 RPL STRW | 70Y
LC | 126054420 | 023/207 | T2 DI BRIDGVIL-COTONWD 23/207 RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-04 | 2023-05-01 | 2023-12-01 | On-time | 2024-04-30 | 151 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046116 | T2 DI BRIDGVIL-COTONWD 23/207 RPR GYWW | ICW
LC | 126054545 | :001/008 | T2 DI CARIBOU #2 :001/008 RPR INSW | TABLEMTN | ETL.6280.INSL.CERA | 2023-05-04 | 2023-05-01 | 2023-07-14 | On-time | 2024-04-30 | 291 | 2023-11-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45752737 | T2 DI CARIBOU #2 :001/008 RPR INSW | ICW
LC | 126054585 | 006/007 | T2 DI MENDO-HARTLY 6/7 COTTER | WILLITS | ETL.7510.INSL.NCER | 2023-05-04 | 2023-05-01 | 2023-09-22 | On-time | 2024-04-30 | 221 | 2023-11-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45762727 | T2 DI MENDO-HARTLY 6/7 COTTER | ICW
LC | 126054671 | 005/126 | T2 DI SALINAS-LAURELES 5/126 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-04 | 2023-05-01 | 2024-03-22 | On-time | 2024-04-30 | 39 | 2024-05-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507055 | T2 DI SALINAS-LAURELES 5/126 RPL POLE | 70Y
LC | 126050338 | 015/302 | T2 EI CARIBOU-WESTWOOD 015/302 INS HRDD | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-04 | 2023-05-04 |  | Late | 2024-05-03 |  | 2024-05-04 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Missing | Hardware-Wood | Install | 46046323 | T2 EI CARIBOU-WESTWOOD 015/302 INS HRDD | ICW
LC | 126054675 | 009/206 | T2 DI SALINAS-LAURELES 009/206 RPR ANCW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-04 | 2023-05-01 | 2023-06-05 | On-time | 2024-04-30 | 330 | 2023-11-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45767321 | T2 DI SALINAS-LAURELES 009/206 RPR ANCW | ICW
LC | 126051246 | 059/252 | T2 RND MTN-TBLE MN #2 59/252 RPL INSS | TABLEMTN | ETL.6070.INSL | 2023-05-04 | 2023-05-04 | 2024-05-05 | Late | 2024-05-03 | -2 | 2024-05-04 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672626 | T2 EI RND MTN-TBL MTN #2 RPL INSS 2 TWRS | 93K
LC | 126051415 | 068/283 | T2 EI RND MTN-TM #2 68/283 COMPLETE | TABLEMTN | ETL.6070.TOWR | 2023-05-04 | 2023-05-04 | 2024-06-13 | Late | 2024-05-03 | -41 | 2024-05-04 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46072130 | T2 EI RND MTN-TM #2 068/283 RPR ANCS | ICS
LC | 126053120 | 024/008 | T2 WV KONOCTI-MIDDLETOWN 24/008 RPL PL | WILLITS | ETL.6380.POLE.WOOD | 2023-05-04 | 2023-05-04 |  | Late | 2024-05-03 |  | 2024-05-04 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35522937 | T2 WV KONOCTI-MIDDLETOWN 24/008 RPL PL | 70Y
LC | 126054762 | 006/072 | T2 DI PIT #5-RND MTN #1 6/72 RPR STRT | TABLEMTN | ETL.5420.TOWR | 2023-05-04 | 2023-05-01 | 2023-11-08 | On-time | 2024-04-30 | 174 | 2024-05-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46044437 | T2 DI PIT #5-RND MTN #1 6/72 RPR STRT | ICQ
LC | 126056286 | 005/003 | T2 DI FORT SEWARD TAP 5/3 RPR GYWW | EUREKA | ETL.6222.POLE.WOOD | 2023-05-05 | 2023-05-01 | 2024-04-16 | On-time | 2024-04-30 | 14 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46045961 | T2 DI FORT SEWARD TAP 5/3 RPR GYWW | ICW
LC | 126056322 | 006/007 | T2 DI FORT SEWARD TAP 6/7 RPL HRDD | EUREKA | ETL.6222.POLE.WOOD | 2023-05-05 | 2023-05-01 | 2024-04-15 | On-time | 2024-04-30 | 15 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46045963 | T2 DI FORT SEWARD TAP 6/7 RPL HRDD | ICW
LC | 126053658 | 006/004 | T2 DI LYTNVLL-WLLTS 06/04 RPR STRW | WILLITS | ETL.8360.POLE.WOOD | 2023-05-04 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46222742 | T2 DI LYTNVLL-WLLTS 06/04 RPR STRW | ICW
LC | 126054022 | 051/220 | T2 EI RND MTN-TBLE MN #1 51/220 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2023-05-04 | 2023-05-04 |  | Late | 2024-05-03 |  | 2023-11-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45855691 | T2 EI RND MTN-TBLE MN #1 51/220 RPR STRT | ICQ
LC | 126056357 | 005/010 | T2 DI FORT SEWARD TAP 5/10 RPR GYWW | EUREKA | ETL.6222.POLE.NWOD | 2023-05-05 | 2023-05-01 | 2023-06-23 | On-time | 2024-04-30 | 312 | 2023-08-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45753859 | T2 DI FORT SEWARD TAP 5/10 RPR GYWW | ICW
LC | 126054296 | 008/174 | T2 DI SALINAS-LAUR 8/174 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-04 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35507057 | T2 DI SALINAS-LAUR 8/174 RPL POLE | 70Y
LC | 126054376 | 014/178 | T2 DI DLT-MTN GT JT-MTN 14/178R RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2023-05-04 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35558793 | T2 DI DLT-MTN GT JT-MTN 14/178R RPL STRW | 70Y
LC | 126056373 | 008/191 | T2 DI SALINAS-LAURELES 008/191 RPR GYWW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-05 | 2023-05-01 | 2024-03-28 | On-time | 2024-04-30 | 33 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46049295 | T2 DI SALINAS-LAURELES 008/191 RPR GYWW | ICW
LC | 126054419 | 023/202 | T2 DI BRDGVLLE-CTTNWD 23/202L RPR GYWW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-04 | 2023-05-01 | 2024-05-29 | Late | 2024-04-30 | -29 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46230764 | T2 DI BRDGVLLE-CTTNWD 23/202L RPR GYWW | ICW
LC | 126056405 | 022/199 | T2 DI BRDGVLL-CTTNWD 22/199 RPL HRDD | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-01 | 2024-01-17 | On-time | 2024-04-30 | 104 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46046143 | T2 DI BRDGVLL-CTTNWD 22/199 RPL HRDD | ICW
LC | 126056750 | 006/066 | T2 DI PIT #5-ROUND MTN #1 6/66L COTTER | TABLEMTN | ETL.5420.INSL.CERA | 2023-05-05 | 2023-05-01 | 2023-06-27 | On-time | 2024-04-30 | 308 | 2023-08-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45763408 | T2 DI PIT #5-ROUND MTN #1 6/66L COTTER | ICW
LC | 126056751 | 023/203 | T2 DI BRIDGVL-CTTNWD 23/203L RPR ADSS | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-05 | 2023-05-01 | 2024-01-17 | On-time | 2024-04-30 | 104 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 46046119 | T2 DI BRIDGVL-CTTNWD 23/203L RPR ADSS | ICW
LC | 126056849 | 023/201 | T2 DI BRIDGVL-CTTNWD 23/201R RPL HRDW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-01 | 2023-12-08 | On-time | 2024-04-30 | 144 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46046142 | T2 DI BRIDGVL-CTTNWD 23/201R RPL HRDW | ICW
LC | 126056910 | 023/201 | T2 DI BRIDGVL-CTTNWD 023/201 RPR INSW | TABLEMTN | ETL.1110.INSL.CERA | 2023-05-05 | 2023-05-01 | 2023-12-08 | On-time | 2024-04-30 | 144 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046141 | T2 DI BRIDGVL-CTTNWD 023/201 RPR INSW | ICW
LC | 126054587 | 054/008 | T2 DI ELK-GUALALA 054/008 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-05-04 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487316 | T2 DI ELK-GUALALA 054/008 RPL POLE | 70Y
LC | 126054596 | 023/208 | T2 DI BRIDGEVILLE-CTTNWD 23/208 RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-04 | 2023-05-01 | 2024-05-29 | Late | 2024-04-30 | -29 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46237023 | T2 DI BRIDGEVILLE-CTTNWD 23/208 RPR GYWW | ICW
LC | 126056914 | 023/201 | T2 DI BRIDGVL-CTTNWD 23/201L RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-01 | 2023-12-08 | On-time | 2024-04-30 | 144 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 46046140 | T2 DI BRIDGVL-CTTNWD 23/201L RPR ADSS | ICW
LC | 126054663 | 008/069 | T2 DI PIT#6 JCT-RND MNTN 8/69 RPL INSS | TABLEMTN | ETL.5440.INSL | 2023-05-04 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509003 | T2 DI PIT#6 JCT-RND MNTN 8/69 RPL INSS | 93K
LC | 126056918 | 052/000 | T2 DI FORT ROSS-GUALALA 52/0 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-05 | 2023-05-01 | 2023-08-14 | On-time | 2024-04-30 | 260 | 2023-08-01 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31656223 | T2 DI FORT ROSS-GUALALA 52/0 RPL STRW | 70Y
LC | 126057054 | 012/076 | T2 DI CAYUCOS-CAMBRIA 12/76 COTTER | PISMOBCH | ETL.8560.POLE.NWOD | 2023-05-05 | 2023-05-01 | 2024-01-14 | On-time | 2024-04-30 | 107 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46090114 | T2 DI CAYUCOS-CAMBRIA 12/76 COTTER | ICW
LC | 126057055 | 022/593 | T2 DI CARIBOU #2 22/593 RPR GYWW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-05 | 2023-05-01 | 2023-11-09 | On-time | 2024-04-30 | 173 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046080 | T2 DI CARIBOU #2 22/593 RPR GYWW | ICW
LC | 126054766 | 051/253 | T2 DI MALIN-RD MTN #2 51/253 RPR GYWT | TABLEMTN | ETL.6020.TOWR | 2023-05-04 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46236878 | T2 DI MALIN-RD MTN #2 51/253 RPR GYWT | ICQ
LC | 126054767 | 051/253 | T2 DI MALIN-RD MTN #2 51/253 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-05-04 | 2023-04-28 | 2024-05-09 | Late | 2024-04-27 | -12 | 2024-04-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46037394 | T2 DI MALIN-RD MTN #2 51/253 RPR OPGW | ICS
LC | 126057321 | 006/008 | T2 DI FORT SEWARD TAP 6/8 RPR ANCW | EUREKA | ETL.6222.POLE.WOOD | 2023-05-05 | 2023-05-01 | 2024-04-15 | On-time | 2024-04-30 | 15 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46045965 | T2 DI FORT SEWARD TAP 6/8 RPR ANCW | ICW
LC | 126056017 | 006/069 | T2 DI PIT #5-RND MTN #1 6/069 RPL INSS | TABLEMTN | ETL.5420.INSL.CERA | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510810 | T2 DI PIT #5-RND MTN #1 6/069 RPL INSS | 93K
LC | 126057695 | 004/057 | T2 DI MANILLE TAP 004/057 RPR INSW | PISMOBCH | ETL.1372.INSL.NCER | 2023-05-05 | 2023-05-01 | 2023-06-28 | On-time | 2024-04-30 | 307 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46078201 | T2 DI MANILLE TAP 004/057 RPR INSW | ICW
LC | 126056029 | 047/009 | T2 DI FORT ROSS-GUALALA 47/9 RPL POLE | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-05 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35518742 | T2 EI FORT ROSS-GUALALA 46/004 RPL STRW | 70Y
LC | 126057779 | 022/200 | T2 DI BRIDGEVL-CTTNWD 22/200R RPL HRDW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-01 | 2023-06-21 | On-time | 2024-04-30 | 314 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45909825 | T2 DI BRIDGEVL-CTTNWD 22/200R RPL HRDW | ICW
LC | 126057873 | 022/200 | T2 DI BRIDGEVL-CTTNWD 22/200 RPR CRSW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-01 | 2023-06-21 | On-time | 2024-04-30 | 314 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45909822 | T2 DI BRIDGEVL-CTTNWD 22/200 RPR CRSW | ICW
LC | 126056100 | 012/169 | T2 DI VALEY SPRINGS-CLAY 12/169 RPL POLE | VICTOR | ETL.8264.POLE.WOOD | 2023-05-05 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35514993 | T2 DI VALEY SPRNGS-CLAY 12/167 RPL POLE | 70Y
LC | 126056192 | 083/423 | T2 DI MALIN-ROUND MTN #2 83/423 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2023-05-05 | 2023-04-28 |  | Late | 2024-04-27 |  | 2024-04-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46037396 | T2 DI MALIN-ROUND MTN #2 83/423 RPR INSS | ICS
LC | 126057972 | 005/065 | T2 DI MANVILLE TAP 5/65 RPR INSW | PISMOBCH | ETL.1372.INSL.NCER | 2023-05-05 | 2023-05-01 | 2024-03-26 | On-time | 2024-04-30 | 35 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46090116 | T2 DI MANVILLE TAP 5/65 RPR INSW | ICW
LC | 126056246 | 017/329 | T2 DI SALINAS-LAURELES 17/329 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-05 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507089 | T2 DI SALINAS-LAURELES 17/329 RPL STRW | 70Y
LC | 126057974 | 004/059C | T2 DI MANVILLE TAP 4/59C RPR GYWW | PISMOBCH | ETL.1372.POLE.NWOD | 2023-05-05 | 2023-05-01 | 2024-02-01 | On-time | 2024-04-30 | 89 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46090117 | T2 DI MANVILLE TAP 4/59C RPR GYWW | ICW
LC | 126058570 | 022/193 | T2 DI BRIDGEVL-CTTNWD 22/193 RPR OPGW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-01 | 2024-01-17 | On-time | 2024-04-30 | 104 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 46046144 | T2 DI BRIDGEVL-CTTNWD 22/193 RPR OPGW | ICW
LC | 126058821 | 004/062 | T2 DI MANVILLE TAP 004/062 RPR JUMW | PISMOBCH | ETL.1372.INSL.NCER | 2023-05-05 | 2023-05-01 | 2024-03-26 | On-time | 2024-04-30 | 35 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46090118 | T2 DI MANVILLE TAP 004/062 RPR JUMW | ICW
LC | 126060169 | 007/005 | T2 DI FORT SEWARD TAP 7/5 RPL HRDW | EUREKA | ETL.6222.POLE.NWOD | 2023-05-05 | 2023-05-01 | 2024-04-04 | On-time | 2024-04-30 | 26 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46045966 | T2 DI FORT SEWARD TAP 7/5 RPL HRDW | ICW
LC | 126056365 | 012/167 | T2 DI VALEY SPRNGS-CLAY 12/167 RPL POLE | VICTOR | ETL.8264.POLE.WOOD | 2023-05-05 | 2023-04-27 |  | Late | 2024-04-26 |  | 2024-04-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514993 | T2 DI VALEY SPRNGS-CLAY 12/167 RPL POLE | 70Y
LC | 126060215 | 022/194 | T2 DI BRIDGEVL-CTTNWD 22/194 RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-01 | 2023-06-21 | On-time | 2024-04-30 | 314 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45979881 | T2 DI BRIDGEVL-CTTNWD 22/194 RPR ADSS | ICW
LC | 126060570 | 022/196 | T2 DI BRIDGEVL-CTTNWD 22/196 RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-05 | 2023-05-01 | 2023-06-21 | On-time | 2024-04-30 | 314 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45940334 | T2 DI BRIDGEVL-CTTNWD 22/196 RPR GYWW | ICW
LC | 126061284 | 023/204 | T2 DI BRIDGEVL-CTTNWD 023/204R RPR STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-01 | 2023-12-08 | On-time | 2024-04-30 | 144 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046118 | T2 DI BRIDGEVL-CTTNWD 023/204R RPR STRW | ICW
LC | 126061336 | 051/005 | T2 DI FORT ROSS-GUALALA 051/005 RPR GYWW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-05 | 2023-05-01 | 2023-11-01 | On-time | 2024-04-30 | 181 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46042595 | T2 DI FORT ROSS-GUALALA 051/005 RPR GYWW | ICW
LC | 126061419 | 023/204 | T2 DI BRDGEVL-CTTNWD 023/204C REPULL GYW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-01 | 2023-08-12 | On-time | 2024-04-30 | 262 | 2023-11-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45895046 | T2 DI BRDGEVL-CTTNWD 023/204C REPULL GYW | ICW
LC | 126056828 | :001/017 | T2 DI CARIBOU #2 :1/17 RPR INSW | TABLEMTN | ETL.6280.INSL.CERA | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046085 | T2 DI CARIBOU #2 :001/017 RPR INSW | ICW
LC | 126061741 | 006/005 | T2 DI FORT SEWARD TAP 6/5 RPL HRDW | EUREKA | ETL.6222.POLE.WOOD | 2023-05-05 | 2023-05-01 | 2024-04-17 | On-time | 2024-04-30 | 13 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46045962 | T2 DI FORT SEWARD TAP 6/5 RPL HRDW | ICW
LC | 126062013 | 012/075 | T2 DI CAYUCOS-CAMBRIA 12/75 RPR GYWW | PISMOBCH | ETL.8560.POLE.WDPS | 2023-05-05 | 2023-05-01 | 2024-01-15 | On-time | 2024-04-30 | 106 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46090119 | T2 DI CAYUCOS-CAMBRIA 12/75 RPR GYWW | ICW
LC | 126062019 | 012/075 | T2 DI CAYUCOS-CAMBRIA 12/75 RPL INSW | PISMOBCH | ETL.8560.INSL.NCER | 2023-05-05 | 2023-05-01 | 2024-01-15 | On-time | 2024-04-30 | 106 | 2024-05-01 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35513606 | T2 DI CAYUCOS-CAMBRIA 12/75 RPL INSW | 93I
LC | 126062342 | 003/024 | T2 DI BUTTE VALLEY-CARIBOU 3/24 RPR STRT | TABLEMTN | ETL.1180.TOWR | 2023-05-05 | 2023-05-01 | 2024-04-08 | On-time | 2024-04-30 | 22 | 2024-05-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46049862 | T2 DI BUTTE VALLEY-CARIBOU 3/24 RPR STRT | ICQ
LC | 126062921 | 021/188 | T2 DI BRIDGEVL-CTTNWD 21/188 RPL HRDW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-01 | 2024-01-17 | On-time | 2024-04-30 | 104 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46046146 | T2 DI BRIDGEVL-CTTNWD 21/188 RPL HRDW | ICW
LC | 126062923 | 021/188 | T2 DI BRIDGEVL-CTTNWD 21/188 RPR XARM | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-01 | 2024-01-17 | On-time | 2024-04-30 | 104 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46046145 | T2 DI BRIDGEVL-CTTNWD 21/188 RPR XARM | ICW
LC | 126057062 | 018/334 | T2 DI SALINAS-LAURELES 018/334 RPR POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-05 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081078 | T2 DI SALINAS-LAURELES 018/334 RPR POLE | ICW
LC | 126057067 | 003/010 | T2 WV LAYTONVILLE-COVELO 03/10 INS DMPW | WILLITS | ETL.7390.INSL.NCER | 2023-05-05 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 45763188 | T2 WV LAYTONVILLE-COVELO 03/10 INS DMPW | ICW
LC | 126063126 | 054/003 | T2 DI FORT ROSS-GUALALA 54/3 RMV VEG | WILLITS | ETL.6980.POLE.WOOD | 2023-05-05 | 2023-05-01 | 2024-04-01 | On-time | 2024-04-30 | 29 | 2024-05-01 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126063207 | 006/076B | T2 DI JOLON TAP 6/76B COTTER | MOSSLNDG | ETL.7321.INSL.CERA | 2023-05-05 | 2023-05-01 | 2023-12-09 | On-time | 2024-04-30 | 143 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46076989 | T2 DI JOLON TAP 6/76B COTTER | ICW
LC | 126063209 | 006/076B | T2 DI JOLON TAP 6/76B RPR POLE | MOSSLNDG | ETL.7321.POLE.WOOD | 2023-05-05 | 2023-05-01 | 2023-12-09 | On-time | 2024-04-30 | 143 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46076990 | T2 DI JOLON TAP 6/76B RPR POLE | ICW
LC | 126057580 | 039/255A | T2 EI TRINITY-CTTNWOOD 039/255A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-05 | 2023-05-05 | 2024-05-29 | Late | 2024-05-04 | -25 | 2024-05-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46239920 | T2 EI TRINITY-CTTNWOOD 039/255A RPR GYWW | ICW
LC | 126063908 | 021/191 | T2 DI BRIDGEVIL-CTTNWD 21/191 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-05-06 | 2023-05-01 | 2023-09-02 | On-time | 2024-04-30 | 241 | 2024-05-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45763375 | T2 DI BRIDGEVIL-CTTNWD 21/191 RPR SHIELD | ICS
LC | 126070389 | 49 | T2 DI FRT RS GUALALA 43/00 COTTER | LAKEVLLE | ETL.6980.SWIT | 2023-05-08 | 2023-05-01 | 2024-04-15 | On-time | 2024-04-30 | 15 | 2024-05-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46045969 | T2 DI FRT RS GUALALA 43/00 COTTER | ICS
LC | 126101684 | 057/005 | T2 DI FORT ROSS-GUALALA 057/005 RPR GYWW | LAKEVLLE | ETL.6980.POLE.NWOD | 2023-05-10 | 2023-05-01 | 2023-11-01 | On-time | 2024-04-30 | 181 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46042596 | T2 DI FORT ROSS-GUALALA 057/005 RPR GYWW | ICW
LC | 126162966 | 013/313 | T2 DRUM-GRSS VLLY-WEIMAR 13/313 RPR POLE | SACTO | ETL.6760.POLE.WOOD | 2023-05-18 | 2023-05-01 | 2024-01-10 | On-time | 2024-04-30 | 111 | 2024-05-01 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046472 | T2 DRUM-GRSS VLLY-WEIMAR 13/313 RPR POLE | ICW
LC | 126057954 | ;000/022 | T2 DI CARIBOU #2 ;0/22 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527047 | T2 DI CARIBOU#2 ;000/020 RPL POLE | 70Y
LC | 126349251 | 022/196 | T2 DI BRIDGEVL-CTTNWD 22/196L RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-12 | 2023-05-01 | 2023-06-21 | On-time | 2024-04-30 | 314 | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45973130 | T2 DI BRIDGEVL-CTTNWD 22/196L RPR GYWW | ICW
LC | 126029284 | 026/428 | T2 KESWICK-TRINITY 026/428 REFRAME | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-02 | 2023-05-02 | 2024-04-30 | On-time | 2024-05-01 | 1 | 2024-05-02 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35512899 | T2 EI KESWICK-TRINITY 024/385 REFRAME | 93E
LC | 126057973 | 002/045 | T2 DI COLEMAN-RED BLF 2/45 RPL POLE | TABLEMTN | ETL.6440.POLE.WOOD | 2023-05-05 | 2023-04-28 | 2024-05-23 | Late | 2024-04-27 | -26 | 2024-04-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35500376 | T2 COLEMAN-RED BLUFF 001/021 RPL POLE | 70Y
LC | 126031148 | 051/222 | T2 ROUND MTN-TBL MTN #1 51/222 RPL INSS | TABLEMTN | ETL.6060.INSL.CERA | 2023-05-02 | 2023-05-02 | 2024-04-19 | On-time | 2024-05-01 | 12 | 2024-05-02 | 532 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672627 | T2 ROUND MTN-TBL MTN #1 51/222 RPL INSS | 93K
LC | 126058022 | 039/255B | T2 EI TRINITY-CTTNWD 039/255B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-05 | 2023-05-05 | 2024-05-29 | Late | 2024-05-04 | -25 | 2024-05-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46054033 | T2 EI TRINITY-CTTNWD 039/255B RPR GYWW | ICW
LC | 126031864 | 024/638 | T2 EI CARIBOU #2 24/638 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-02 | 2023-05-02 | 2023-11-10 | On-time | 2024-05-01 | 173 | 2024-05-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046097 | T2 EI CARIBOU #2 24/638 RPR GYWW | ICW
LC | 126058121 | 053/005 | T2 DI TRINTY-MPL CRK 53/5 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506531 | T2 DI TRINTY-MPL CR 53/5 RPL STRW | 70Y
LC | 126058200 | 013/111 | T2 EI TGR CRK-VLLY SPRNGS 13/111 REGRADE | VICTOR | ETL.5790.TOWR | 2023-05-05 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46048801 | T2 EI TGR CRK-VLLY SPRNGS 13/111 REGRADE | ICQ
LC | 126058216 | 009/071 | T2 DI PIT #6 JCT-RND MTN 9/71L RPL POLE | TABLEMTN | ETL.5440.POLE.WDPS | 2023-05-05 | 2023-04-28 | 2024-06-21 | Late | 2024-04-27 | -55 | 2024-04-28 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35529573 | T2 DI PIT #6 JCT-RND MTN RPL 3 POLE | 70Y
LC | 126058222 | 039/255C | T2 EI TRINITY-CTTNWD 039/255C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-05 | 2023-05-05 | 2024-05-29 | Late | 2024-05-04 | -25 | 2024-05-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046101 | T2 EI TRINITY-CTTNWD 039/255C RPR GYWW | ICW
LC | 126058295 | 004/056 | T2 DI MANVILLE TAP 004/056 RMV VEG | PISMOBCH | ETL.1372.POLE.STPS | 2023-05-05 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126031913 | 036/167 | T2 IGNACIO-SOBRANTE 036/167 RPR FENCE | LAKEVLLE | ETL.4920.TOWR | 2023-05-02 | 2023-05-02 | 2023-08-24 | On-time | 2024-05-01 | 251 | 2024-05-02 | 932 | TLR | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Fence / Gate | Repair | 45947769 | T2 IGNACIO-SOBRANTE 036/167 RPR FENCE | CHS
LC | 126058528 | :001/006 | T2 DI CARIBOU #2 :1/6 RPL ANCW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35515666 | T2 DI CARIBOU #2 :001/006 RPL ANCW | 93E
LC | 126032026 | 005/117 | T2 EI HMLTN BRNCH-CHSTR 5/117 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-05-02 | 2023-05-02 | 2023-10-02 | On-time | 2024-05-01 | 212 | 2024-05-02 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31656780 | T2 EI HMLTN BRNCH-CHSTR 5/117 RPL POLE | 70Y
LC | 126032268 | 005/118 | T2 EI HMLTN BRNCH-CHSTR 5/118 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-05-02 | 2023-05-02 | 2023-10-02 | On-time | 2024-05-01 | 212 | 2024-05-02 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31656780 | T2 EI HMLTN BRNCH-CHSTR 5/117 RPL POLE | 70Y
LC | 126032498 | 008/093B | T2 EI DRUM-SUMMIT #1 08/093 RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-05-02 | 2023-05-02 | 2023-09-05 | On-time | 2024-05-01 | 239 | 2023-11-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45916508 | T2 EI DRUM-SUMMIT #1 08/093 RPR GYWW | ICW
LC | 126032521 | 008/093A | T2 EI DRUM-SUMMIT #1 08/093 RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-05-02 | 2023-05-02 | 2023-08-02 | On-time | 2024-05-01 | 273 | 2023-11-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45895459 | T2 EI DRUM-SUMMIT #1 08/093 RPR GYWW | ICW
LC | 126033027 | X005/027 | T2 EI DIABLO-MESA X5/27 BENT STEEL | PISMOBCH | ETL.4620.TOWR | 2023-05-02 | 2023-05-02 | 2023-11-11 | On-time | 2024-05-01 | 172 | 2024-05-02 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46051195 | T2 EI DIABLO-MESA X5/27 BENT STEEL | ICQ
LC | 126058934 | 053/007 | T2 DI TRINITY-MAPLE CRK 53/7 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506534 | T2 DI TRINITY-MAPLE CRK 53/7 RPL STRW | 70Y
LC | 126033061 | 003/070 | T2 VALLEY SPRINGS #1 003/070 RPR INSW | VICTOR | ETL.8210.INSL.NCER | 2023-05-02 | 2023-05-02 | 2024-03-28 | On-time | 2024-05-01 | 34 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46161846 | T2 VALLEY SPRINGS #1 003/070 RPR INSW | ICW
LC | 126033067 | 035/298 | T2 EI PIT #1-COTTONWOOD 35/298 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2023-05-02 | 2023-05-02 | 2023-12-13 | On-time | 2024-05-01 | 140 | 2024-05-02 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46044422 | T2 EI PIT #1-COTTONWOOD 35/298 RPR FOND | ICQ
LC | 126033110 | 035/299 | T2 EI PIT #1-COTTONWOOD 35/299 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2023-05-02 | 2023-05-02 | 2023-12-06 | On-time | 2024-05-01 | 147 | 2024-05-02 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46044480 | T2 EI PIT #1-COTTONWOOD 35/299 RPR FOND | ICQ
LC | 126059219 | 015/137 | T2 DI BRDGVLLE-CTTNWD 15/137L RPR GYWS | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046115 | T2 DI BRDGVLLE-CTTNWD 15/137L RPR GYWS | ICW
LC | 126059260 | 023/620 | T2 DI CARIBOU #2 23/620 RPR INSW | TABLEMTN | ETL.6280.INSL.NCER | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046094 | T2 DI CARIBOU #2 23/620 RPR INSW | ICW
LC | 126059263 | 023/620 | T2 DI CARIBOU#2 023/620 RPL ANCW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35515872 | T2 DI CARIBOU#2 023/620 RPL ANCW | 93E
LC | 126033113 | 035/300 | T2 EI PIT #1-COTTONWOOD 35/300 RPR FOUND | TABLEMTN | ETL.5390.TOWR | 2023-05-02 | 2023-05-02 | 2023-12-06 | On-time | 2024-05-01 | 147 | 2024-05-02 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46044423 | T2 EI PIT #1-COTTONWOOD 35/300 RPR FOUND | ICQ
LC | 126033124 | 035/302 | T2 EI PIT #1-COTTONWD 35/302 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2023-05-02 | 2023-05-02 | 2023-11-13 | On-time | 2024-05-01 | 170 | 2024-05-02 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46044424 | T2 EI PIT #1-COTTONWD 35/302 RPR FOND | ICQ
LC | 126059462 | 002/007 | T2 DI MAPLE CREEK-HOOPA 002/007 RPR JMPW | EUREKA | ETL.7490.INSL.NCER | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2023-08-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46190015 | T2 DI MAPLE CREEK-HOOPA 002/007 RPR JMPW | ICW
LC | 126033256 | 033/183 | T2 EI EXCHQUER-INDN FLT 33/183 RPR STRS | FRESNO | ETL.8650.POLE.NWOD | 2023-05-02 | 2023-05-02 | 2023-12-15 | On-time | 2024-05-01 | 138 | 2024-05-02 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45977782 | T2 EI EXCHQUER-INDN FLT 33/183 RPR STRS | ICQ
LC | 126034077 | 005/124 | T2 EI HMLTN BRNCH-CHSTR 5/124 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-05-02 | 2023-05-02 | 2023-10-03 | On-time | 2024-05-01 | 211 | 2024-05-02 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31656780 | T2 EI HMLTN BRNCH-CHSTR 5/117 RPL POLE | 70Y
LC | 126034232 | 066/275 | T2 EI RND MTN-TBL MTN #1 66/275 RPR ANCS | TABLEMTN | ETL.6060.TOWR | 2023-05-02 | 2023-05-02 | 2023-08-04 | On-time | 2024-05-01 | 271 | 2023-11-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45752734 | T2 EI RND MTN-TBL MTN #1 66/275 RPR ANCS | ICS
LC | 126034347 | 017/345 | T2 EI COLGATE-PALERMO 017/345 RPR INSW | SACTO | ETL.6500.INSL.CERA | 2023-05-02 | 2023-05-02 | 2024-04-27 | On-time | 2024-05-01 | 4 | 2024-05-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046410 | T2 EI COLGATE-PALERMO 017/345 RPR INSW | ICW
LC | 126034370 | 017/341 | T2 EI COLGATE-PALERMO 017/341 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2023-05-02 | 2023-05-02 | 2024-04-26 | On-time | 2024-05-01 | 5 | 2024-05-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35506919 | T2 EI COLGATE-PALERMO 017/341 RPL STRW | 70Y
LC | 126034375 | 017/339 | T2 EI COLGATE-PALERMO 017/339 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2023-05-02 | 2023-05-02 | 2024-04-26 | On-time | 2024-05-01 | 5 | 2024-05-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046411 | T2 EI COLGATE-PALERMO 017/339 RPR STRW | ICW
LC | 126034380 | 017/345 | T2 EI COLGATE-PALERMO 017/345 RMV VEG | SACTO | ETL.6500.POLE.WOOD | 2023-05-02 | 2023-05-02 | 2024-04-11 | On-time | 2024-05-01 | 20 | 2024-05-02 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Trim
LC | 126060378 | 002/006 | T2 DI MAPLE CREEK-HOOPA 2/6 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46045972 | T2 DI MPL CR-HOOPA 2/6 RPR GYWW | ICW
LC | 126034388 | 066/275 | T2NT EI RND MTN-TM #2 066/275 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2023-05-02 | 2023-05-02 | 2024-01-11 | On-time | 2024-05-01 | 111 | 2024-05-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072127 | T2NT EI RND MTN-TM #2 066/275 RPR STRT | ICQ
LC | 126060440 | 17 | T2 DI CARIBOU #2 6/135 RPR SWITCH 17 | TABLEMTN | ETL.6280.SWIT | 2023-05-05 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 623 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Out of Adjustment | Switch | Repair | 46046206 | T2 DI CARIBOU #2 6/135 RPR SWITCH 17 | ICE
LC | 126034976 | 033/184 | T2 EI EXCHQUR-INDN FLAT 33/184 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-05-02 | 2023-05-02 | 2023-12-11 | On-time | 2024-05-01 | 142 | 2024-05-02 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45977783 | T2 EI EXCHQUR-INDN FLAT 33/184 UNBURY | ICQ
LC | 126034984 | 034/195 | T2 EI EXCHQUR-INDN FLAT 34/195 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-05-02 | 2023-05-02 | 2023-12-11 | On-time | 2024-05-01 | 142 | 2024-05-02 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45977788 | T2 EI EXCHQUR-INDN FLAT 34/195 UNBURY | ICQ
LC | 126060684 | 024/646 | T2 DI CARIBOU #2 24/646 RPL STRW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527491 | T2 DI CARIBOU #2 24/646 RPL STRW | 70Y
LC | 126034985 | 035/198 | T2 EI EXCHQUR-INDN FLAT 35/198 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-05-02 | 2023-05-02 | 2023-12-11 | On-time | 2024-05-01 | 142 | 2024-05-02 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45977792 | T2 EI EXCHQUR-INDN FLAT 35/198 UNBURY | ICQ
LC | 126035317 | 035/203 | T2 EI EXCHQUR-INDN FLAT 035/203 RPR FOND | FRESNO | ETL.8650.TOWR | 2023-05-02 | 2023-05-02 | 2023-12-11 | On-time | 2024-05-01 | 142 | 2024-05-02 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45977797 | T2 EI EXCHQUR-INDN FLAT 035/203 RPR FOND | ICQ
LC | 126035894 | X006/029 | T2 EI DIABLO-MESA X6/29 RPR FOND | PISMOBCH | ETL.4620.TOWR | 2023-05-02 | 2023-05-02 | 2023-11-11 | On-time | 2024-05-01 | 172 | 2024-05-02 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46051196 | T2 EI DIABLO-MESA X6/29 RPR FOND | ICQ
LC | 126056019 | 030/252 | T2 DI BRDGVLL-CTTNWD 30/252 RPR STRW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-05 | 2023-05-02 | 2024-01-19 | On-time | 2024-05-01 | 103 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046113 | T2 DI BRDGVLL-CTTNWD 30/252 RPR STRW | ICW
LC | 126061506 | 004/030 | T2 WV COTTONWOOD #2 4/30 RPR INSW | TABLEMTN | ETL.6630.INSL.NCER | 2023-05-05 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45880234 | T2 WV COTTONWOOD #2 4/30 RPR INSW | ICS
LC | 126061611 | :002/002 | T2 DI CARIBOU #2 :2/2 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527043 | T2 DI CARIBOU #2 :002/002 RPL STRW | 70Y
LC | 126057298 | 062/313 | T2 DI MLN-RND MTN #2 62/313 RPR ANCS | TABLEMTN | ETL.6020.TOWR | 2023-05-05 | 2023-05-02 | 2023-11-07 | On-time | 2024-05-01 | 176 | 2024-05-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 46044196 | T2 DI MLN-RND MTN #2 62/313 RPR ANCS | ICS
LC | 126057505 | 001/019 | T2 DI CLGT-SMRTVLL #2 1/19 UNBURY ANCW | SACTO | ETL.6520.POLE.WOOD | 2023-05-05 | 2023-05-02 | 2023-07-10 | On-time | 2024-05-01 | 296 | 2023-11-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45763455 | T2 DI CLGT-SMRTVLL #2 1/19 UNBURY ANCW | ICW
LC | 126061792 | 000/013 | T2 EI MONTICELLO PH TAP 0/13 RPR SWTC | LAKEVLLE | ETL.1602.POLE.NWOD | 2023-05-05 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 623 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Out of Adjustment | Switch | Repair | 46096604 | T2 EI MONTICELLO PH TAP 0/13 RPR SWTC | ICE
LC | 126061857 | 015/138 | T2 DI BRDGVLL-CTTNWD 15/138 RPR CRSW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46046114 | T2 DI BRDGVLL-CTTNWD 15/138 RPR CRSW | ICW
LC | 126061892 | 021/007 | T2 EI MNDCN-WLITS-FRT BRG 21/7 RPR WDPK | WILLITS | ETL.7550.POLE.WOOD | 2023-05-05 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46214095 | T2 EI MNDCN-WLITS-FRT BRG 21/7 RPR WDPK | ICW
LC | 126061902 | 011/112 | T2 WV PIT #5-ROUND MTN #2 11/112 RPR INS | TABLEMTN | ETL.5430.INSL.NCER | 2023-05-05 | 2023-05-05 | 2024-06-25 | Late | 2024-05-04 | -52 | 2024-05-05 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46045952 | T2 WV PIT #5-ROUND MTN #2 11/112 RPR INS | ICS
LC | 126061967 | 021/004 | T2 EI MNDCNO-WLTS-FRT BRG 21/4 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2023-05-05 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46216624 | T2 EI MNDCINO-WLITS-FRT BRG 21/4 RPR WDP | ICW
LC | 126057893 | ;003/020 | T2 DI CARIBOU #2 ;003/020 RPR STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-05 | 2023-05-02 | 2023-11-09 | On-time | 2024-05-01 | 174 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046089 | T2 DI CARIBOU #2 ;003/020 RPR STRW | ICW
LC | 126057958 | ;004/007 | T2 DI CARIBOU #2 ;004/007 RPR GYWW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-05 | 2023-05-02 | 2023-11-09 | On-time | 2024-05-01 | 174 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046091 | T2 DI CARIBOU #2 ;004/007 RPR GYWW | ICW
LC | 126058523 | 030/254 | T2 DI BRGVLL-CTTWD 030/254L RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-02 | 2024-01-19 | On-time | 2024-05-01 | 103 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 46046111 | T2 DI BRGVLL-CTTWD 030/254L RPR ADSS | ICW
LC | 126058579 | 000/005 | T2 DI MPL CRK-HOOPA 0/5 RPR ANCW | EUREKA | ETL.7490.POLE.NWOD | 2023-05-05 | 2023-05-02 | 2023-08-01 | On-time | 2024-05-01 | 274 | 2023-11-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45759941 | T2 DI MPL CRK-HOOPA 0/5 RPR ANCW | ICW
LC | 126062085 | 021/003 | T2 EI MNDIN-WLLTS-FRT BRG 21/3 RPL ANCHR | WILLITS | ETL.7550.POLE.NWOD | 2023-05-05 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35521378 | T2 MNDCNO-WLITS-FRT BRG 2/13 RPL ANCW | 93E
LC | 126062106 | 044/295A | T2NT EI TRINITY-CTTNWD 44/295A RMV BUTT | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-05 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Pole Butt | Structure-Wood | Remove | 46211349 | T2NT EI TRINITY-CTTNWD 044/295A RMV BUTT | ICW
LC | 126059080 | 003/000 | T2 DI MPLE CRK-HPA 3/0 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-05-05 | 2023-05-02 | 2023-09-19 | On-time | 2024-05-01 | 225 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45759779 | T2 DI MPLE CRK-HPA 3/0 RPR GYWW | ICW
LC | 126059084 | ;004/000 | T2 DI CARIBOU #2 ;004/000 RPR STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-05 | 2023-05-02 | 2023-11-10 | On-time | 2024-05-01 | 173 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046090 | T2 DI CARIBOU #2 ;004/000 RPR STRW | ICW
LC | 126062205 | 048/236 | T2 DI MLN-RND MTN #2 48/236 RPR GYWT | TABLEMTN | ETL.6020.TOWR | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46248593 | T2 DI MLN-RND MTN #2 48/236 RPR GYWT | ICQ
LC | 126062325 | 021/009 | T2 EI MNDCIN-WILTS-FRT BRG 21/9 RPL PL | WILLITS | ETL.7550.POLE.WOOD | 2023-05-05 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521521 | T2 EI MNDCNO-WLLTS-FRT BRGG 7/5 RPL POLE | 70Y
LC | 126062330 | 014/284 | T2 EI CARIBOU-WESTWOOD 014/284 RMV VEG | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-05 | 2023-05-05 | 2024-05-05 | Late | 2024-05-04 | -1 | 2024-05-05 | 932 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Brush Fuel | Road | Remove
LC | 126059327 | 021/190 | T2 DI BRDGVLL-CTTNWD 21/190 RPL HRDW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-02 | 2023-06-21 | On-time | 2024-05-01 | 315 | 2023-11-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45763403 | T2 DI BRDGVLL-CTTNWD 21/190 RPL HRDW | ICW
LC | 126062352 | 013/118 | T2 WV PIT #6 JCT-RND MTN 13/118 RPR INS | TABLEMTN | ETL.5440.INSL.CERA | 2023-05-05 | 2023-05-05 | 2024-06-22 | Late | 2024-05-04 | -49 | 2024-05-05 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46045956 | T2 WV PIT #6 JCT-RND MTN 13/118 RPR INS | ICW
LC | 126059461 | 002/007 | T2 DI MAPLE CREEK-HOOPA 2/7 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-05-05 | 2023-05-02 | 2023-09-07 | On-time | 2024-05-01 | 237 | 2023-11-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45759778 | T2 DI MAPLE CREEK-HOOPA 2/7 RPR GYWW | ICW
LC | 126062405 | 044/295B | T2NT EI TRINITY-CTTNWD 44/295B RMV BUTT | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-05 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Pole Butt | Structure-Wood | Remove | 46211351 | T2NT EI TRINITY-CTTNWD 044/295B RMV BUTT | ICW
LC | 126059463 | 002/007 | T2 DI MAPLE CREEK-HOOPA 2/7 RPR ANCW | EUREKA | ETL.7490.POLE.NWOD | 2023-05-05 | 2023-05-02 | 2023-08-02 | On-time | 2024-05-01 | 273 | 2023-11-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45759943 | T2 DI MAPLE CREEK-HOOPA 2/7 RPR ANCW | ICW
LC | 126059536 | 001/035 | T2 DI JFFRSN-STNFRD 1/35 RPR INSW | METCALF | ETL.7220.INSL.CERA | 2023-05-05 | 2023-05-02 | 2023-11-07 | On-time | 2024-05-01 | 176 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45997325 | T2 DI JFFRSN-STNFRD 1/35 RPR INSW | ICW
LC | 126059670 | 001/020 | T2 DI COLGTE-SMRV#2 1/20L UNBURY ANCW | SACTO | ETL.6520.POLE.STPS | 2023-05-05 | 2023-05-02 | 2023-07-10 | On-time | 2024-05-01 | 296 | 2023-11-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45763457 | T2 DI COLGTE-SMRV#2 1/20L UNBURY ANCW | ICW
LC | 126060143 | 018/462 | T2 DI CARIBOU #2 018/462 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-05 | 2023-05-02 | 2023-11-10 | On-time | 2024-05-01 | 173 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046093 | T2 DI CARIBOU #2 018/462 RPR GYWW | ICW
LC | 126062698 | 023/612 | T2 DI CARIBOU #2 23/612 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-05 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046082 | T2 DI CARIBOU #2 23/612 RPL GYWW | ICW
LC | 126062715 | 044/295C | T2NT EI TRINITY-CTTNWD 44/295C RMV BUTT | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-05 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Pole Butt | Structure-Wood | Remove | 46211352 | T2NT EI TRINITY-CTTNWD 044/295C RMV BUTT | ICW
LC | 126062748 | 100/003A | T2 EI HMBLDT-TRNTY 100/3A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-05 | 2023-05-05 | 2024-05-30 | Late | 2024-05-04 | -26 | 2023-11-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171112 | T2 EI HMBLDT-TRNTY 100/3A RPR GYWW | ICW
LC | 126060303 | 063/316 | T2 DI MLN-RND MTN #2 63/316 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2023-05-05 | 2023-05-02 | 2023-11-07 | On-time | 2024-05-01 | 176 | 2024-05-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46044197 | T2 DI MLN-RND MTN #2 63/316 RPR GYWS | ICS
LC | 126062763 | 042/011 | T2 DI FORT ROSS-GUALALA 42/11 RPR STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-05 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46045967 | T2 DI FORT ROSS-GUALALA 42/11 RPR STRW | ICW
LC | 126060429 | 024/647 | T2 DI CARIBOU #2 24/647 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-05 | 2023-05-02 | 2023-11-09 | On-time | 2024-05-01 | 174 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046098 | T2 DI CARIBOU #2 24/647 RPR GYWW | ICW
LC | 126061191 | 024/649 | T2 DI CARIBOU #2 24/649 RPR CRSW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-05 | 2023-05-02 | 2023-11-09 | On-time | 2024-05-01 | 174 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46046099 | T2 DI CARIBOU #2 24/649 RPR CRSW | ICW
LC | 126062929 | 022/597 | T2 DI CARIBOU #2 22/597 COTTER | TABLEMTN | ETL.6280.INSL.CERA | 2023-05-05 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046081 | T2 DI CARIBOU #2 22/597 COTTER | ICW
LC | 126061762 | 035/003 | T2 DI BRDGVLL-GRBRVLL 35/3 RPR GYWW | EUREKA | ETL.6220.POLE.NWOD | 2023-05-05 | 2023-05-02 | 2024-02-01 | On-time | 2024-05-01 | 90 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46087929 | T2 DI BRDGVLL-GRBRVLL 35/3 RPR GYWW | ICW
LC | 126063108 | 062/002 | T2 DI GRBRVLLE-LYTNVLLE 62/2 CANCEL | WILLITS | ETL.8365.INSL.NCER | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46073330 | T2 DI GRBRVLLE-LYTNVLLE 62/2 RPR INSS | ICS
LC | 126061989 | 001/006 | T2 DI MAPLE CRK-HOOPA 001/006 COA | EUREKA | ETL.7490.POLE.STPS | 2023-05-05 | 2023-05-02 | 2024-01-24 | On-time | 2024-05-01 | 98 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46045971 | T2 DI MAPLE CRK-HOOPA 001/006 RPR GYWW | ICW
LC | 126062529 | 030/253 | T2 DI BRDGVLL-CTTNWD 030/253L RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-02 | 2023-08-25 | On-time | 2024-05-01 | 250 | 2023-08-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45763400 | T2 DI BRDGVLL-CTTNWD 030/253L RPR ADSS | ICW
LC | 126062600 | 030/253 | T2 DI BRDGVLL-CTTNWD 030/253 RPR ANCW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-05 | 2023-05-02 | 2024-01-19 | On-time | 2024-05-01 | 103 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46046112 | T2 DI BRDGVLL-CTTNWD 030/253 RPR ANCW | ICW
LC | 126063227 | 001/020 | T2 DI CLGT-SMRTVLL #1 1/20R RPR GYWW | SACTO | ETL.6510.POLE.STPS | 2023-05-05 | 2023-05-02 | 2024-05-06 | Late | 2024-05-01 | -5 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046461 | T2 DI CLGT-SMRTVLL #1 1/20R RPL GYWW | ICW
LC | 126063285 | 053/266 | T2 DI MLN-RND MTN #2 53/266 RPR GYWT | TABLEMTN | ETL.6020.TOWR | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46257486 | T2 DI MLN-RND MTN #2 53/266 RPR GYWT | ICQ
LC | 126063301 | 024/630A | T2 DI CARIBOU #2 024/630A RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046096 | T2 DI CARIBOU #2 024/630A RPR GYWW | ICW
LC | 126063304 | 054/268 | T2NT DI MLN-RND MTN #2 54/268 RPR GYWT | TABLEMTN | ETL.6020.TOWR | 2023-05-05 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46132324 | T2NT DI MLN-RND MTN #2 54/268 RPR GYWT | ICQ
LC | 126063101 | 004/002 | T2 DI FRUITLAND TAP 4/2 RPR GYWW | EUREKA | ETL.6221.POLE.WOOD | 2023-05-05 | 2023-05-02 | 2023-07-13 | On-time | 2024-05-01 | 293 | 2023-11-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45763983 | T2 DI FRUITLAND TAP 4/2 RPR GYWW | ICW
LC | 126063315 | ;000/024 | T2 DI CARIBOU #2 ;0/24 RPR SPLW | TABLEMTN | ETL.6280.INSL.NCER | 2023-05-05 | 2023-05-02 | 2023-11-28 | On-time | 2024-05-01 | 155 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46046088 | T2 DI CARIBOU #2 ;0/24 RPR SPLW | ICW
LC | 126063342 | 054/268 | T2 DI MLN-RND MTN #2 54/268 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-05-05 | 2023-05-02 | 2024-01-23 | On-time | 2024-05-01 | 99 | 2024-05-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46050042 | T2 DI MLN-RND MTN #2 54/268 RPR OPGW | ICS
LC | 126063769 | ;005/004 | T2 DI CARIBOU #2 ;005/004 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-06 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527153 | T2 DI CARIBOU #2 ;005/004 RPL STRW | 70Y
LC | 126063971 | 022/587 | T2 DI CARIBOU #2 022/587 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-06 | 2023-05-02 | 2023-07-19 | On-time | 2024-05-01 | 287 | 2023-11-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45855121 | T2 DI CARIBOU #2 022/587 RPR GYWW | ICW
LC | 126064035 | 001/039 | T2 DI JEFFERSON-STANFORD1/39 RPR GYWW | METCALF | ETL.7220.POLE.WOOD | 2023-05-06 | 2023-05-02 | 2023-11-07 | On-time | 2024-05-01 | 176 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45997327 | T2 DI JEFFERSON-STANFORD1/39 RPR GYWW | ICW
LC | 126064256 | :001/012 | T2 DI CARIBOU #2 :001/012 RPL HRDD | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-06 | 2023-05-02 | 2023-11-27 | On-time | 2024-05-01 | 156 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46046084 | T2 DI CARIBOU #2 :001/012 RPL HRDD | ICW
LC | 126064428 | 055/271 | T2 DI MLN-RND MTN #2 55/271 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-05-06 | 2023-05-02 | 2024-01-23 | On-time | 2024-05-01 | 99 | 2024-05-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46046048 | T2 DI MLN-RND MTN #2 55/271 RPR SHLS | ICS
LC | 126064531 | 000/003 | T2 DI MPL CRK-HOOPA 0/3 RPR ANCW | EUREKA | ETL.7490.POLE.WOOD | 2023-05-06 | 2023-05-02 | 2023-08-01 | On-time | 2024-05-01 | 274 | 2023-11-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45759940 | T2 DI MPL CRK-HOOPA 0/3 RPR ANCW | ICW
LC | 126064564 | :003/018 | T2 DI ROCK CREEK-POE-TWR :3/18 REGRADE | TABLEMTN | ETL.5630.TOWR | 2023-05-06 | 2023-05-02 | 2024-04-19 | On-time | 2024-05-01 | 12 | 2024-05-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46049863 | T2 DI ROCK CREEK-POE-TWR :3/18 REGRADE | ICQ
LC | 126063931 | 021/191 | T2 DI BRIDGEVILLE-CTTNWD 21/191 RPL INSS | TABLEMTN | ETL.1110.INSL | 2023-05-06 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509192 | T2 DI BRIDGEVILLE-CTTNWD RPL INSS 9 TWRS | 93K
LC | 126064587 | 054/267 | T2 DI MLN-RND MTN #2 54/267 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-05-06 | 2023-05-02 | 2024-01-23 | On-time | 2024-05-01 | 99 | 2024-05-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46046045 | T2 DI MLN-RND MTN #2 54/267 RPR SHLS | ICS
LC | 126064677 | 054/270 | T2 DI MLN-RND MTN #2 054/270 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-05-06 | 2023-05-02 | 2024-01-23 | On-time | 2024-05-01 | 99 | 2024-05-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46046047 | T2 DI MLN-RND MTN #2 054/270 RPR SHLS | ICS
LC | 126064029 | 042/001 | T2 DI FORT ROSS-GUALALA 42/1 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-06 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518741 | T2 DI FORT ROSS-GUALALA 42/1 RPL STRW | 70Y
LC | 126064866 | 000/000D | T2 DI HAT CRK #1-PIT #1 0/0D RPR GYWW | TABLEMTN | ETL.7020.POLE.NWOD | 2023-05-06 | 2023-05-02 | 2023-11-06 | On-time | 2024-05-01 | 177 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46037503 | T2 DI HAT CRK #1-PIT #1 0/0D RPR GYWW | ICW
LC | 126064069 | 024/629B | T2 DI CARIBOU #2 24/629B COTTER | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-06 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046095 | T2 DI CARIBOU #2 024/629B COTTER | ICW
LC | 126069225 | 003/012 | T2 DI FRUITLAND TAP 03/012 RPR GYWW | EUREKA | ETL.6221.POLE.WOOD | 2023-05-08 | 2023-05-02 | 2024-02-01 | On-time | 2024-05-01 | 90 | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46087881 | T2 DI FRUITLAND TAP 03/012 RPR GYWW | ICW
LC | 126069545 | 001/019 | T2 DI CLGTE SMRTVIL#1 01/019 RPL ANCHOR | SACTO | ETL.6510.POLE.STPS | 2023-05-08 | 2023-05-02 | 2023-07-24 | On-time | 2024-05-01 | 282 | 2024-05-02 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31645615 | T2 DI CLGTE SMRTVIL#1 01/019 RPL ANCHOR | 93E
LC | 126070502 | 000/008 | T2 DI CLGTE-SMRTVIL#2 00/08 RPR GYWW | SACTO | ETL.6520.POLE.WOOD | 2023-05-08 | 2023-05-02 | 2023-07-28 | On-time | 2024-05-01 | 278 | 2023-08-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45763443 | T2 DI CLGTE SMRTVIL#2 00/08 RPR GYWW | ICW
LC | 126070506 | 000/008 | T2 DI CLGTE SMRTVIL#2 00/08 RPR STRW | SACTO | ETL.6520.POLE.WOOD | 2023-05-08 | 2023-05-02 | 2023-07-28 | On-time | 2024-05-01 | 278 | 2023-08-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45763445 | T2 DI CLGTE SMRTVIL#2 00/08 RPR STRW | ICW
LC | 126064312 | 100/003B | T2 EI HMBLDT-TRNTY 100/3B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-06 | 2023-05-06 | 2024-05-30 | Late | 2024-05-05 | -25 | 2023-11-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171112 | T2 EI HMBLDT-TRNTY 100/3A RPR GYWW | ICW
LC | 126064317 | :006/007 | T2 DI CARIBOU #2 :6/7 RPL INSW | TABLEMTN | ETL.6280.INSL.CERA | 2023-05-06 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35515753 | T2 DI CARIBOU #2 :4/0 RPL INSW | 93I
LC | 126064332 | 054/000 | T2 DI TRINITY-MAPLE CREEK 54/0L RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-05-06 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46044508 | T2 DI TRINITY-MAPLE CREEK 54/0L RPR GYWW | ICW
LC | 126071123 | 002/005 | T2 DI MAPLE CREEK-HOOPA 02/005 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-05-08 | 2023-05-02 | 2023-09-19 | On-time | 2024-05-01 | 225 | 2023-11-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45890146 | T2 DI MAPLE CREEK-HOOPA 02/005 RPR GYWW | ICW
LC | 126039012 | 024/643 | T2 EI CARIBOU #2 24/643 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-03 | 2023-05-03 | 2023-11-10 | On-time | 2024-05-02 | 174 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046301 | T2 EI CARIBOU #2 24/643 RPR GYWW | ICW
LC | 126039517 | 014/124 | T2 EI CRAG VIEW-CASCADE 14/124R RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-05-03 | 2023-05-03 | 2023-12-10 | On-time | 2024-05-02 | 144 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046106 | T2 EI CRAG VIEW-CASCADE 14/124R RPR GYWW | ICW
LC | 126039518 | 014/124 | T2 EI CRAG VIEW-CASCADE 14/124C RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-05-03 | 2023-05-03 | 2023-12-10 | On-time | 2024-05-02 | 144 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046105 | T2 EI CRAG VIEW-CASCADE 14/124C RPR GYWW | ICW
LC | 126039521 | 006/141 | T2 EI HMLTN BRNCH-CHSTR 6/141 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2023-05-03 | 2023-05-03 | 2023-10-06 | On-time | 2024-05-02 | 209 | 2024-05-03 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483296 | T2 EI HMLTN BRNCH-CHSTR 6/141 RPL STRW | 70Y
LC | 126039744 | 006/142 | T2 EI HAMILTN BRNCH-CHSTR 6/142 RPR POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-05-03 | 2023-05-03 | 2023-09-27 | On-time | 2024-05-02 | 218 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45937199 | T2 EI HAMILTN BRNCH-CHSTR 6/142 RPR POLE | ICW
LC | 126039747 | 017/142 | T2 WV PIT #1-COTTONWOOD 17/142 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2023-05-03 | 2023-05-03 | 2024-05-01 | On-time | 2024-05-02 | 1 | 2024-05-03 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46044421 | T2 WV PIT #1-COTTONWOOD 17/142 RPR STRT | ICQ
LC | 126064538 | :002/003 | T2 DI CARIBOU #2 :2/3 RPL INSW | TABLEMTN | ETL.6280.INSL.CERA | 2023-05-06 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35515665 | T2 DI CARIBOU #2 :2/3 RPL INSW | 93I
LC | 126040109 | 056/312 | T2 EI TEMBLOR-SN LS OBISPO 56/312 COTTER | PISMOBCH | ETL.3960.INSL | 2023-05-03 | 2023-05-03 | 2023-08-01 | On-time | 2024-05-02 | 275 | 2023-08-03 | 628 | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45895018 | T2 EI TEMBLOR-SN LS OBISPO 56/312 COTTER | ICS
LC | 126064585 | ;000/023 | T2 DI CARIBOU #2 ;000/023 RPL DMPW | TABLEMTN | ETL.6280.INSL.NCER | 2023-05-06 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46046087 | T2 DI CARIBOU #2 ;000/023 RPL DAMW | ICW
LC | 126040551 | 063/266 | T2 EI RND MTN-TBLE MN #1 63/266 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2023-05-03 | 2023-05-03 | 2024-01-11 | On-time | 2024-05-02 | 112 | 2024-05-03 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072128 | T2 EI RND MTN-TBLE MN #1 63/266 RPR STRT | ICQ
LC | 126064634 | 042/277B | T2 EI TRINITY-CTTNWD 42/277B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-06 | 2023-05-06 | 2024-05-28 | Late | 2024-05-05 | -23 | 2023-11-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046056 | T2 EI TRINITY-CTTNWD 042/277B RPR GYWW | ICW
LC | 126064643 | 042/277B | T2 EI TRINITY-CTTNWD 042/277B RMV STEP | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-06 | 2023-05-06 | 2024-05-28 | Late | 2024-05-05 | -23 | 2024-05-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046055 | T2 EI TRINITY-CTTNWD 042/277B RMV STEP | ICW
LC | 126040873 | 006/146 | T2 EI HAMILTN BRNCH-CHSTR 6/146 RPR POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-05-03 | 2023-05-03 | 2023-09-27 | On-time | 2024-05-02 | 218 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45937220 | T2 EI HAMILTN BRNCH-CHSTR 6/146 RPR POLE | ICW
LC | 126064672 | 054/270 | T2 DI MLN-RND MTN #2 054/270 RPL HRDT | TABLEMTN | ETL.6020.TOWR | 2023-05-06 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46072126 | T2 DI MLN-RND MTN #2 054/270 RPL HRDT | ICQ
LC | 126041008 | 056/311 | T2 EI TMBLR-SN LS OBSPO 56/311 RPL INSS | PISMOBCH | ETL.3960.INSL | 2023-05-03 | 2023-05-03 | 2024-04-03 | On-time | 2024-05-02 | 29 | 2024-05-03 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513945 | T2 EI TMBLR-SN LS OBSPO 56/311 RPL INSS | 93K
LC | 126064685 | 042/277A | T2 EI TRINITY-CTTNWD 042/277A RMV STEP | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-06 | 2023-05-06 | 2024-06-20 | Late | 2024-05-05 | -46 | 2024-05-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046057 | T2 EI TRINITY-CTTNWD 042/277A RMV STEP | ICW
LC | 126064691 | 100/003C | T2 EI HMBLDT-TRNTY 100/3C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-06 | 2023-05-06 | 2024-05-30 | Late | 2024-05-05 | -25 | 2023-11-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171112 | T2 EI HMBLDT-TRNTY 100/3A RPR GYWW | ICW
LC | 126041138 | 001/014 | T2 WV FLINT TAP 1/14 RPR ADSS | SACTO | ETL.3341.POLE.NWOD | 2023-05-03 | 2023-05-03 | 2024-02-20 | On-time | 2024-05-02 | 72 | 2024-05-03 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45985258 | T2 WV FLINT TAP 1/14 RPR ADSS | ICW
LC | 126041562 | 106/003C | T2 EI HUMBOLDT-TRINITY 106/3C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-03 | 2023-05-03 | 2024-04-02 | On-time | 2024-05-02 | 30 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46044504 | T2 EI HUMBOLDT-TRINITY 106/3C RPR GYWW | ICW
LC | 126041762 | 106/003B | T2 EI HUMBOLDT-TRINITY 106/3B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-03 | 2023-05-03 | 2024-04-02 | On-time | 2024-05-02 | 30 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46044503 | T2 EI HUMBOLDT-TRINITY 106/3B RPR GYWW | ICW
LC | 126041767 | 009/083 | T2 WV BRDGVLL-CTTNWD 9/83 RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-03 | 2023-05-03 | 2023-12-02 | On-time | 2024-05-02 | 152 | 2024-05-03 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 46046107 | T2 WV BRDGVLL-CTTNWD 9/83 RPR ADSS | ICW
LC | 126042010 | 106/003A | T2 EI HUMBOLDT-TRINITY 106/3A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-03 | 2023-05-03 | 2024-04-02 | On-time | 2024-05-02 | 30 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46044502 | T2 EI HUMBOLDT-TRINITY 106/3A RPR GYWW | ICW
LC | 126042281 | 110/000A | T2 EI HUMBOLDT-TRINITY 110/000A RPR STRW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-03 | 2023-05-03 | 2024-04-01 | On-time | 2024-05-02 | 31 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46044505 | T2 EI HUMBOLDT-TRINITY 110/000A RPR STRW | ICW
LC | 126043152 | 007/153 | T2 EI HAMILTN BRNCH-CHSTR 7/153 RPR GYWW | TABLEMTN | ETL.7000.POLE.NWOD | 2023-05-03 | 2023-05-03 | 2023-09-28 | On-time | 2024-05-02 | 217 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45937221 | T2 EI HAMILTN BRNCH-CHSTR 7/153 RPR GYWW | ICW
LC | 126064812 | 022/192 | T2 DI BRDGVLL-CTTNWD 22/192L RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-06 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501390 | T2 DI BRDGVIL CTTNWD RPL 7 STRCTS | 70Y
LC | 126064814 | 022/192 | T2 DI BRDGVLL-CTTNWD 22/192R RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-06 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501390 | T2 DI BRDGVIL CTTNWD RPL 7 STRCTS | 70Y
LC | 126044549 | 024/647 | T2NT EI CARIBOU #2 24/647 RPR JUMW | TABLEMTN | ETL.6280.INSL.CERA | 2023-05-03 | 2023-05-03 | 2023-11-09 | On-time | 2024-05-02 | 175 | 2024-05-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46046302 | T2NT EI CARIBOU #2 24/647 RPR JUMW | ICW
LC | 126044799 | 030/156 | T2 EI EXCHQUER-INDN FLT 30/156 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-05-03 | 2023-05-03 | 2023-12-12 | On-time | 2024-05-02 | 142 | 2024-05-03 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45977755 | T2 EI EXCHQUER-INDN FLT 30/156 UNBURY | ICQ
LC | 126045164 | 030/159 | T2 EI EXCHQUER-INDN FLT 30/159 RPR JUMS | FRESNO | ETL.8650.INSL.NCER | 2023-05-03 | 2023-05-03 | 2023-12-14 | On-time | 2024-05-02 | 140 | 2023-08-03 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45854967 | T2 EI EXCHQUER-INDN FLT 30/159 RPR JUMS | ICS
LC | 126045185 | 031/165 | T2 EI EXCHQUR-INDN FLT 31/165 COTTER | FRESNO | ETL.8650.INSL.NCER | 2023-05-03 | 2023-05-03 | 2023-12-13 | On-time | 2024-05-02 | 141 | 2024-05-03 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45957626 | T2 EI EXCHQUR-INDN FLT 31/165 COTTER | ICS
LC | 126065033 | 016/145 | T2 DI BRIDGEVL-CTTNWD 16/145R RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-06 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501390 | T2 DI BRDGVIL CTTNWD RPL 7 STRCTS | 70Y
LC | 126065036 | 016/145 | T2 DI BRIDGEVL-CTTNWD 16/145L RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-06 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501390 | T2 DI BRDGVIL CTTNWD RPL 7 STRCTS | 70Y
LC | 126045186 | 031/167A | T2 EI EXCHQUR-INDN FLT 31/167A COTTER | FRESNO | ETL.8650.INSL.NCER | 2023-05-03 | 2023-05-03 | 2023-12-13 | On-time | 2024-05-02 | 141 | 2023-08-03 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45854968 | T2 EI EXCHQUR-INDN FLT 31/167A COTTER | ICS
LC | 126045557 | 19 | T2 DRM-GRSS VLLY-WMR 15/353 RPR SWTCH | SACTO | ETL.6760.SWIT | 2023-05-03 | 2023-05-03 | 2023-09-08 | On-time | 2024-05-02 | 237 | 2024-05-03 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 45875874 | T2 DRM-GRSS VLLY-WMR 15/353 RPR SWTCH | ICE
LC | 126047177 | 014/180 | T2 DI KESWICK-TRINITY 014/180 RPL TIED | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-04 | 2023-05-03 | 2023-08-01 | On-time | 2024-05-02 | 275 | 2023-08-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45770755 | T2 DI KESWICK-TRINITY 014/180 RPL TIED | ICW
LC | 126065049 | 17 | T2 DI LYTNVLL-WLLTS 22/009 CANCEL | WILLITS | ETL.8360.SWIT | 2023-05-06 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46227530 | T2 DI LYTNVLL-WLLTS 22/009 RPR SPLS | ICW
LC | 126049497 | 027/323 | T2 DI DRM-SUMMIT #2 27/323 INSTL HNGR PL | SACTO | ETL.1450.TOWR | 2023-05-04 | 2023-05-03 | 2023-08-28 | On-time | 2024-05-02 | 248 | 2024-05-03 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Tower | Install | 45751838 | T2 DI DRM-SUMMIT #2 27/323 INSTL HNGR PL | ICQ
LC | 126063800 | 017/236 | T2 DI KSWCK-TRINITY 017/236 RPL HRDD | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-04-16 | On-time | 2024-05-02 | 16 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46046174 | T2 DI KSWCK-TRINITY 017/236 RPL HRDD | ICW
LC | 126063829 | 021/311 | T2 DI KESWK-TRINTY 21/311 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-06 | 2023-05-03 | 2024-04-18 | On-time | 2024-05-02 | 14 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046241 | T2 DI KESWK-TRINTY 21/311 RPR GYWW | ICW
LC | 126063896 | 029/497 | T2 DI KESWICK-TRINITY 029/497 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-04-27 | On-time | 2024-05-02 | 5 | 2024-05-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35513062 | T2 DI KESWICK-TRINITY 029/497 RPL POLE | 70Y
LC | 126065274 | 009/117 | T2 DI KESWICK-TRINITY 9/117 RMV VEG | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-06 | 2023-05-03 | 2024-06-20 | Late | 2024-05-02 | -49 | 2024-05-03 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126063937 | 022/335 | T2 DI KSWCK-TRINITY 022/335 RPR ANCW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-02-21 | On-time | 2024-05-02 | 71 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46046243 | T2 DI KSWCK-TRINITY 022/335 RPR ANCW | ICW
LC | 126064178 | 015/183 | T2 DI KESWK-TRINTY 15/183 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-06 | 2023-05-03 | 2024-02-12 | On-time | 2024-05-02 | 80 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046169 | T2 DI KESWK-TRINTY 15/183 RPR GYWW | ICW
LC | 126064262 | 017/237 | T2 DI KSWCK-TRINITY 017/237 RPL HRDD | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-04-16 | On-time | 2024-05-02 | 16 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46046175 | T2 DI KSWCK-TRINITY 017/237 RPL HRDD | ICW
LC | 126064369 | 023/363 | T2 DI KESWIK-TRINTY 23/363 RPR SPLW | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-06 | 2023-05-03 | 2024-04-18 | On-time | 2024-05-02 | 14 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46046252 | T2 DI KESWIK-TRINTY 23/363 RPR SPLW | ICW
LC | 126064420 | 019/281 | T2 DI KSWCK-TRINITY 019/281 RMV VEG | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-04-04 | On-time | 2024-05-02 | 28 | 2024-05-03 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126065874 | 042/274B | T2 EI TRINITY-CTTNWD 042/274B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-06 | 2023-05-06 | 2024-05-28 | Late | 2024-05-05 | -23 | 2023-11-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046100 | T2 EI TRINITY-CTTNWD 042/274B RPR GYWW | ICW
LC | 126064498 | 019/271 | T2 DI KESWICK-TRINITY 19/271 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-06 | 2023-05-03 | 2024-04-17 | On-time | 2024-05-02 | 15 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046176 | T2 DI KESWICK-TRINITY 19/271 RPR GYWW | ICW
LC | 126064521 | 028/479 | T2 DI KESWICK-TRINITY 028/479 RPL STRW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-04-25 | On-time | 2024-05-02 | 7 | 2024-05-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35513061 | T2 DI KESWICK-TRINITY 028/479 RPL STRW | 70Y
LC | 126064671 | 027/447 | T2 DI KESWICK-TRINITY 27/447 RPR INSW | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-06 | 2023-05-03 | 2023-07-22 | On-time | 2024-05-02 | 285 | 2023-08-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45762940 | T2 DI KESWICK-TRINITY 27/447 RPR INSW | ICW
LC | 126066117 | 042/274C | T2 EI TRINITY-CTTNWD 042/274C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-06 | 2023-05-06 | 2024-05-28 | Late | 2024-05-05 | -23 | 2023-11-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046059 | T2 EI TRINITY-CTTNWD 042/274C RPR GYWW | ICW
LC | 126066146 | 023/008 | T2 EI MNDCIN-WLITS-FRT BRG 23/8 CNCL | WILLITS | ETL.7550.INSL.CERA | 2023-05-06 | 2023-05-06 |  | Late | 2024-05-05 |  | 2024-05-06 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35521532 | T2 EI MNDCIN-WLITS-FRT BRG 23/8 RPL INSW | 93I
LC | 126066190 | 022/002 | T2 EI MNDCN-WILLITS-FORT BRG 22/2 RPL PL | WILLITS | ETL.7550.POLE.WOOD | 2023-05-06 | 2023-05-06 |  | Late | 2024-05-05 |  | 2024-05-06 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521531 | T2 EI MNDCN-WILLITS-FORT BRG 22/2 RPL PL | 70Y
LC | 126066194 | 023/002 | T2 EI MNDCN-WLITS-FRT BRG 23/2 RPL PL | WILLITS | ETL.7550.POLE.WOOD | 2023-05-06 | 2023-05-06 |  | Late | 2024-05-05 |  | 2024-05-06 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521531 | T2 EI MNDCN-WILLITS-FORT BRG 22/2 RPL PL | 70Y
LC | 126066198 | 021/010 | T2 EI MNDCN-WLITS-FRT BRG 21/10 RPR GYWW | WILLITS | ETL.7550.POLE.NWOD | 2023-05-06 | 2023-05-06 |  | Late | 2024-05-05 |  | 2024-05-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46246780 | T2 EI MNDCN-WLITS-FRT BRG 21/10 RPR GYWW | ICW
LC | 126066201 | 022/001 | T2 EI MNDCINO-WLITS-FRT BRG 22/1 RPL PL | WILLITS | ETL.7550.POLE.WOOD | 2023-05-06 | 2023-05-06 |  | Late | 2024-05-05 |  | 2024-05-06 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521521 | T2 EI MNDCNO-WLLTS-FRT BRGG 7/5 RPL POLE | 70Y
LC | 126064710 | 028/490 | T2 DI KESWK-TRINTY 28/490L COMPLETE | TABLEMTN | ETL.7270.POLE.STPS | 2023-05-06 | 2023-05-03 | 2024-03-04 | On-time | 2024-05-02 | 59 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046316 | T2 DI KESWK-TRINTY 28/490L RPR GYWW | ICW
LC | 126064711 | 028/490 | T2 DI KESWK-TRINTY 28/490C COMPLETE | TABLEMTN | ETL.7270.POLE.STPS | 2023-05-06 | 2023-05-03 | 2024-03-04 | On-time | 2024-05-02 | 59 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046317 | T2 DI KESWK-TRINTY 28/490C RPR GYWW | ICW
LC | 126064713 | 028/490 | T2 DI KESWK-TRINTY 28/490R COMPLETE | TABLEMTN | ETL.7270.POLE.STPS | 2023-05-06 | 2023-05-03 | 2024-03-04 | On-time | 2024-05-02 | 59 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046318 | T2 DI KESWK-TRINTY 28/490R RPR GYWW | ICW
LC | 126064750 | 021/329 | T2 DI KESWICK-TRINITY 21/329 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-04-18 | On-time | 2024-05-02 | 14 | 2024-05-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512896 | T2 DI KESWICK-TRINITY 21/329 RPL POLE | 70Y
LC | 126064757 | 021/329 | T2 DI KESWICK-TRINITY 21/329 RPR JMPW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-06 | 2023-05-03 | 2023-07-21 | On-time | 2024-05-02 | 286 | 2023-11-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45805407 | T2 DI KESWICK-TRINITY 21/329 RPR JMPW | ICW
LC | 126064783 | 019/272 | T2 DI KESWK-TRINTY 19/272 RPR INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-06 | 2023-05-03 | 2024-04-17 | On-time | 2024-05-02 | 15 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046177 | T2 DI KESWK-TRINTY 19/272 RPR INSW | ICW
LC | 126064784 | 015/182 | T2 DI KESWICK-TRINITY 15/182C RPR GYWW | TABLEMTN | ETL.7270.POLE.STPS | 2023-05-06 | 2023-05-03 | 2023-12-08 | On-time | 2024-05-02 | 146 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046168 | T2 DI KESWICK-TRINITY 15/182C RPR GYWW | ICW
LC | 126064945 | 025/412 | T2 DI KESWICK-TRINITY 25/412 RPR GYWW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-04-27 | On-time | 2024-05-02 | 5 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046305 | T2 DI KESWICK-TRINITY 25/412 RPR GYWW | ICW
LC | 126064962 | 016/200 | T2 DI KESWK-TRINTY 16/200 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-06 | 2023-05-03 | 2023-06-27 | On-time | 2024-05-02 | 310 | 2023-08-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45763372 | T2 DI KESWK-TRINTY 16/200 RPR GYWW | ICW
LC | 126064968 | 022/347 | T2 DI KESWK-TRINTY 22/347 RPR CRSW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-04-24 | On-time | 2024-05-02 | 8 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46046246 | T2 DI KESWK-TRINTY 22/347 RPR CRSW | ICW
LC | 126066760 | 015/143 | T2 DI BRDGVLL-CTTNWD 15/143L RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-06 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501390 | T2 DI BRDGVIL CTTNWD RPL 7 STRCTS | 70Y
LC | 126065041 | 027/458 | T2 DI KESWICK-TRINITY 27/458 RPR JMPW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-06 | 2023-05-03 | 2024-04-26 | On-time | 2024-05-02 | 6 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46046312 | T2 DI KESWICK-TRINITY 27/458 RPR JMPW | ICW
LC | 126066762 | 015/143 | T2 DI BRDGVLL-CTTNWD 15/143C RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-06 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501390 | T2 DI BRDGVIL CTTNWD RPL 7 STRCTS | 70Y
LC | 126066764 | 015/143 | T2 DI BRDGVLL-CTTNWD 15/143R RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-06 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501390 | T2 DI BRDGVIL CTTNWD RPL 7 STRCTS | 70Y
LC | 126065042 | 023/371 | T2 DI KESWICK-TRINITY 23/371C RPR GYWW | TABLEMTN | ETL.7270.POLE.WDPS | 2023-05-06 | 2023-05-03 | 2024-04-19 | On-time | 2024-05-02 | 13 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046253 | T2 DI KESWICK-TRINITY 23/371C RPR GYWW | ICW
LC | 126065044 | 023/371 | T2 DI KESWICK-TRINITY 23/371 RPL INSW | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-06 | 2023-05-03 | 2024-04-19 | On-time | 2024-05-02 | 13 | 2024-05-03 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35512898 | T2 DI KESWICK-TRINITY 23/371 RPL INSW | 93I
LC | 126065155 | 017/231 | T2 DI KESWK-TRINTY 17/231 RPR SPLW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-06 | 2023-05-03 | 2024-04-15 | On-time | 2024-05-02 | 17 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46046173 | T2 DI KESWK-TRINTY 17/231 RPR SPLW | ICW
LC | 126065176 | 029/505 | T2 DI KESWICK-TRINITY 29/505 COTTER | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-06 | 2023-05-03 | 2024-04-25 | On-time | 2024-05-02 | 7 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046319 | T2 DI KESWICK-TRINITY 29/505 COTTER | ICW
LC | 126065179 | 024/395 | T2 DI KSEWICK-TRINITY 024/395 RPL HRDD | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-04-30 | On-time | 2024-05-02 | 2 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46046300 | T2 DI KSEWICK-TRINITY 024/395 RPL HRDD | ICW
LC | 126065434 | 017/228 | T2 DI KSWCK-TRINITY 017/228 RPR CNDW | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-06 | 2023-05-03 | 2024-04-15 | On-time | 2024-05-02 | 17 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46046172 | T2 DI KSWCK-TRINITY 017/228 RPR CNDW | ICW
LC | 126065701 | 026/443 | T2 DI KESWK-TRINTY 26/443 RPR GYWW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-04-22 | On-time | 2024-05-02 | 10 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046311 | T2 DI KESWK-TRINTY 26/443 RPR GYWW | ICW
LC | 126065706 | 025/413 | T2 DI KESWICK-TRINITY 26/413 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-06 | 2023-05-03 | 2024-02-22 | On-time | 2024-05-02 | 70 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046306 | T2 DI KESWICK-TRINITY 26/413 RPR GYWW | ICW
LC | 126065721 | 029/499 | T2 DI KESWICK-TRINITY 29/499 RPR ANCW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2023-07-13 | On-time | 2024-05-02 | 294 | 2023-11-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45762942 | T2 DI KESWICK-TRINITY 29/499 RPR ANCW | ICW
LC | 126065944 | 016/212 | T2 DI KESWK-TRINTY 16/212 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-06 | 2023-05-03 | 2024-02-12 | On-time | 2024-05-02 | 80 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046170 | T2 DI KESWK-TRINTY 16/212 RPR GYWW | ICW
LC | 126066013 | 023/373 | T2 DI KESWICK-TRINITY 023/373 RPR GYWW | TABLEMTN | ETL.7270.POLE.WDPS | 2023-05-06 | 2023-05-03 | 2024-04-19 | On-time | 2024-05-02 | 13 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046254 | T2 DI KESWICK-TRINITY 023/373 RPR GYWW | ICW
LC | 126069220 | A006/130 | T2 DI LAKEVILLE #2 A006/130 RPL POLE | LAKEVLLE | ETL.7340.POLE.WOOD | 2023-05-08 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35530994 | T2 DI LAKEVILLE #2 A006/130 RPL POLE | 70Y
LC | 126066077 | 024/390 | T2 DI KESWICK-TRINITY 24/390 RPR JMPW | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-06 | 2023-05-03 | 2024-04-23 | On-time | 2024-05-02 | 9 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46046258 | T2 DI KESWICK-TRINITY 24/390 RPR JMPW | ICW
LC | 126069280 | ;005/013 | T2 DI CARIBOU #2 ;05/013 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-08 | 2023-05-01 |  | Late | 2024-04-30 |  | 2024-05-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527489 | T2 DI CARIBOU #2 ;05/013 RPL STRW | 70Y
LC | 126066261 | 029/492 | T2 DI KESWICK-TRNTY STL 29/492C RPR GYWW | TABLEMTN | ETL.7270.POLE.STPS | 2023-05-06 | 2023-05-03 | 2023-07-14 | On-time | 2024-05-02 | 293 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45939649 | T2 DI KESWICK-TRNTY STL 29/492C RPR GYWW | ICW
LC | 126066332 | 014/170 | T2 DI KESWICK-TRINITY 14/170 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-04-12 | On-time | 2024-05-02 | 20 | 2024-05-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512715 | T2 DI KESWICK-TRINITY 9/118 RPL POLE | 70Y
LC | 126070032 | 054/001 | T2 DI TRINITY-MAPLE CREEK 054/001 COTTER | EUREKA | ETL.8170.INSL.NCER | 2023-05-08 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46044511 | T2 DI TRINITY-MAPLE CREEK 054/001 COTTER | ICW
LC | 126066341 | 009/118 | T2 DI KESWICK-TRINITY 9/118 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-03-25 | On-time | 2024-05-02 | 38 | 2024-05-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512715 | T2 DI KESWICK-TRINITY 9/118 RPL POLE | 70Y
LC | 126066423 | 025/411 | T2 DI KESWICK-TRINITY 025/411 RPL INSW | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-06 | 2023-05-03 | 2024-04-27 | On-time | 2024-05-02 | 5 | 2024-05-03 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35513060 | T2 EI KESWICK-TRINITY 24/391 RPL INSW | 93I
LC | 126066547 | 023/360 | T2 DI KESWICK-TRINITY 23/360 GO95 | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-04-23 | On-time | 2024-05-02 | 9 | 2024-05-03 | 401T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35512897 | T2 DI KESWICK-TRINITY 23/360 GO95 | 93G
LC | 126066589 | 026/446 | T2 DI KESWICK-TRINITY 26/446 RPR JMPW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-06 | 2023-05-03 | 2024-04-26 | On-time | 2024-05-02 | 6 | 2023-08-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46194276 | T2 DI KESWICK-TRINITY 26/446 RPR JMPRW | ICW
LC | 126071430 | 015/136 | T2 DI BRDGVIL CTTNWD 15/136L RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-08 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501390 | T2 DI BRDGVIL CTTNWD RPL 7 STRCTS | 70Y
LC | 126072171 | 054/000 | T2 DI TRINITY-MAPLE CREEK 54/0R RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-05-08 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46044509 | T2 DI TRINITY-MAPLE CREEK 54/0R RPR GYWW | ICW
LC | 126072172 | 054/000 | T2 DI TRINITY-MAPLE CREEK 54/0C RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-05-08 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46044510 | T2 DI TRINITY-MAPLE CREEK 54/0C RPR GYWW | ICW
LC | 126066727 | 007/098B | T2 DI KESWICK-TRINITY 7/98 RPR INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-06 | 2023-05-03 | 2024-03-26 | On-time | 2024-05-02 | 37 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46046160 | T2 DI KESWICK-TRINITY 7/98 RPR INSW | ICW
LC | 126072542 | 033/006 | T2 EI FULTON-HOPLAND 33/6 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-05-08 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46073467 | T2 EI FULTON-HOPLAND 33/06 RPR STRW | ICW
LC | 126073119 | 033/011 | T2 EI FULTON-HOPLAND 33/11 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-05-08 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35521334 | T2 EI FULTON-HOPLAND 33/11 RPL STRW | 70Y
LC | 126073706 | 025/652 | T2 DI CARIBOU#2 25/652 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-08 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527492 | T2 DI CARIBOU#2 25/652 RPL STRW | 70Y
LC | 126074182 | 035/002 | T2 EI FULTON-HOPLAND 35/2 RPL ANCW | LAKEVLLE | ETL.6890.POLE.NWOD | 2023-05-08 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35521336 | T2 EI FULTON-HOPLAND 035/002 RPL ANCW | 93E
LC | 126074282 | 014/002 | T2 EI HMBLDT BY-RO DLL JCT 14/2 RPL STRW | EUREKA | ETL.7100.POLE.WOOD | 2023-05-08 | 2023-05-08 | 2024-05-10 | Late | 2024-05-07 | -3 | 2024-05-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506676 | T2 EI HMBLDT BY-RO DLL JCT 14/2 RPL STRW | 70Y
LC | 126074355 | 034/007 | T2 EI FULTON-HOPLAND 34/7 RPR STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-05-08 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46073469 | T2 EI FULTON-HOPLAND 034/007 RPR STRW | ICW
LC | 126066761 | 015/187 | T2 DI KESWICK-TRINITY 15/187 RPR JUMW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-06 | 2023-05-03 | 2024-04-29 | On-time | 2024-05-02 | 3 | 2023-11-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46053903 | T2 DI KESWICK-TRINITY 15/187 RPR JUMW | ICW
LC | 126074560 | 034/012 | T2 EI FULTON-HOPLAND 34/12 RPL ANCW | LAKEVLLE | ETL.6890.POLE.NWOD | 2023-05-08 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35547777 | T2 EI FULTON-HOPLAND 34/12 RPL ANCW | 93E
LC | 126066961 | 012/156 | T2 DI KESWICK-TRINITY 12/156 RPR JUMP | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-06 | 2023-05-03 | 2024-04-12 | On-time | 2024-05-02 | 20 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46046164 | T2 DI KESWICK-TRINITY 12/156 RPR JUMP | ICW
LC | 126066992 | 022/339 | T2 DI KESWICK-TRINITY 22/339 BACKFILL | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-02-21 | On-time | 2024-05-02 | 71 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 46046244 | T2 DI KESWICK-TRINITY 22/339 BACKFILL | ICW
LC | 126067111 | 026/439 | T2 DI KSWCK-TRINITY 026/439 RPR ANCW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-02-22 | On-time | 2024-05-02 | 70 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46046309 | T2 DI KSWCK-TRINITY 026/439 RPR ANCW | ICW
LC | 126067118 | 026/439 | T2 DI KSWCK-TRINITY 026/439 RPR INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-06 | 2023-05-03 | 2024-04-22 | On-time | 2024-05-02 | 10 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046310 | T2 DI KSWCK-TRINITY 026/439 RPR INSW | ICW
LC | 126067227 | 025/409 | T2 DI KESWICK-TRINITY 025/409 RPR WDPK | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-02-21 | On-time | 2024-05-02 | 71 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046303 | T2 DI KESWICK-TRINITY 025/409 RPR WDPK | ICW
LC | 126067264 | 023/359 | T2 DI KSWCK-TRINITY 23/359 RPR GYWW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-04-23 | On-time | 2024-05-02 | 9 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046249 | T2 DI KSWCK-TRINITY 23/359 RPR GYWW | ICW
LC | 126076259 | 002/071 | T2 EI COLGATE-ALLEGHANY 2/71 RPR STRW | SACTO | ETL.6470.POLE.WOOD | 2023-05-08 | 2023-05-08 | 2024-06-19 | Late | 2024-05-07 | -43 | 2024-05-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46049065 | T2 EI COLGATE-ALLEGHANY 002/071 RPR POLE | ICW
LC | 126067269 | 025/402 | T2 DI KESWICK-TRINITY 025/402 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-04-23 | On-time | 2024-05-02 | 9 | 2024-05-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512896 | T2 DI KESWICK-TRINITY 21/329 RPL POLE | 70Y
LC | 126067285 | 025/419 | T2 DI KSWCK-TRINITY 025/419 RPL HRDD | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2024-04-20 | On-time | 2024-05-02 | 12 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46046307 | T2 DI KSWCK-TRINITY 025/419 RPL HRDD | ICW
LC | 126077757 | 005/068C | T2 EI GREEN VALLEY-PAL SWT 5/68C RMV VEG | MOSSLNDG | ETL.1730.POLE.WOOD | 2023-05-09 | 2023-05-09 | 2024-06-10 | Late | 2024-05-08 | -33 | 2024-05-09 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126067290 | 014/179 | T2 DI KESWICK-TRINITY 14/179 RPR GYWW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-06 | 2023-05-03 | 2023-12-08 | On-time | 2024-05-02 | 146 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053902 | T2 DI KESWICK-TRINITY 14/179 RPR GYWW | ICW
LC | 126078005 | 033/000 | T2 EI FULTON-HOPLAND 33/000 RPR SPLW | LAKEVLLE | ETL.6890.INSL | 2023-05-09 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46073478 | T2 EI FULTON-HOPLAND 33/000 RPR SPLW | ICW
LC | 126078169 | 051/005 | T2 DI TRINITY-MAPLE CREEK 51/05 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-09 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506522 | T2 DI TRINITY-MAPLE CREEK 51/05 RPL POLE | 70Y
LC | 126078395 | 037/248C | T2 EI TRINITY-CTTNWOOD 037/248C RPL GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-09 | 2023-05-09 | 2024-05-30 | Late | 2024-05-08 | -22 | 2024-05-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 46062547 | T2 EI TRINITY-CTTNWOOD 037/248C RPL GYWS | ICW
LC | 126067295 | 022/341 | T2 DI KESWICK-TRINITY 22/341 RPL INSW | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-06 | 2023-05-03 | 2024-04-19 | On-time | 2024-05-02 | 13 | 2024-05-03 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35512894 | T2 DI KESWK-TRINTY 18/257 RPL INSW | 93I
LC | 126078619 | 022/602 | T2 EI CARIBOU #2 22/602 RPR GYWW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-09 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053923 | T2 EI CARIBOU #2 22/602 RPR GYWW | ICW
LC | 126078779 | 014/177 | T2 EI DELTA-MTN GTE JCT 14/177L RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2023-05-09 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31618696 | T2 DI DLTA-MTN GTE JCT 12/162 RPL STRW | 70Y
LC | 126078824 | 014/177 | T2 EI DELTA-MTN GTE JCT 14/177R RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2023-05-09 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31618696 | T2 DI DLTA-MTN GTE JCT 12/162 RPL STRW | 70Y
LC | 126067340 | 028/471 | T2 DI KSWCK-TRINITY 028/471 RPL INSW | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-06 | 2023-05-03 | 2024-04-26 | On-time | 2024-05-02 | 6 | 2024-05-03 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35513060 | T2 EI KESWICK-TRINITY 24/391 RPL INSW | 93I
LC | 126069405 | 021/323 | T2 DI KESWK-TRINTY 21/323 RPR GYWW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-08 | 2023-05-03 | 2023-11-11 | On-time | 2024-05-02 | 173 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999473 | T2 DI KESWK-TRINTY 21/323 RPR GYWW | ICW
LC | 126070142 | 022/340 | T2 DI KESWICK-TRINITY 22/340 RPR SPLW | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-08 | 2023-05-03 | 2024-04-19 | On-time | 2024-05-02 | 13 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46046245 | T2 DI KESWICK-TRINITY 22/340 RPR SPLW | ICW
LC | 126074491 | 019/273 | T2 DI KESWICK TRINITY 19/273 COTTER | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-08 | 2023-05-03 | 2024-04-17 | On-time | 2024-05-02 | 15 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046179 | T2 DI KESWICK TRINITY 19/273 COTTER | ICW
LC | 126075280 | 029/509 | T2 DI KESWICK-TRINITY 029/509 RPL STRW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-08 | 2023-05-03 | 2024-04-28 | On-time | 2024-05-02 | 4 | 2024-05-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35513061 | T2 DI KESWICK-TRINITY 028/479 RPL STRW | 70Y
LC | 126080372 | 019/495 | T2 EI CARIBOU #2 19/495 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-09 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053921 | T2 EI CARIBOU #2 19/495 RPR GYWW | ICW
LC | 126080392 | 019/497 | T2 EI CARIBOU #2 19/497 RPR STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-09 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46053922 | T2 EI CARIBOU #2 19/497 RPR STRW | ICW
LC | 126075491 | 026/435 | T2 DI KESWICK-TRINITY 26/435 COTTER | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-08 | 2023-05-03 | 2024-03-04 | On-time | 2024-05-02 | 59 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046308 | T2 DI KESWICK-TRINITY 26/435 COTTER | ICW
LC | 126080865 | 027/460 | T2 DI KESWICK-TRNTY 27/460 RPR GYWW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-09 | 2023-05-03 | 2024-04-26 | On-time | 2024-05-02 | 6 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046313 | T2 DI KESWICK-TRNTY 27/460 RPR GYWW | ICW
LC | 126084368 | 021/321 | T2 DI KESWICK-TRINITY 21/321 RPL HRDD | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-09 | 2023-05-03 | 2024-04-17 | On-time | 2024-05-02 | 15 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46046242 | T2 DI KESWICK-TRINITY 21/321 RPL HRDD | ICW
LC | 126084676 | 029/508 | T2 DI KESWICK-TRINITY 029/508 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-09 | 2023-05-03 | 2024-04-28 | On-time | 2024-05-02 | 4 | 2024-05-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35513062 | T2 DI KESWICK-TRINITY 029/497 RPL POLE | 70Y
LC | 126083306 | 002/011 | T2 TRINITY-MAPLE CRK 2/11 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-09 | 2023-05-09 | 2024-05-12 | Late | 2024-05-08 | -4 | 2024-05-09 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31644962 | T2 TRINITY-MAPLE CRK 2/11 RPL POLE | 70Y
LC | 126083496 | 002/012 | T2 TRINITY-MAPLE CRK 2/12 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-09 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31644962 | T2 TRINITY-MAPLE CRK 2/11 RPL POLE | 70Y
LC | 126083538 | 003/001 | T2 TRINITY-MAPLE CRK 3/1 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-09 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31644962 | T2 TRINITY-MAPLE CRK 2/11 RPL POLE | 70Y
LC | 126083932 | 038/155 | T2 EI DIABLO-MIDWAY #3 38/155 RPR GYWT | PISMOBCH | ETL.5980.TOWR | 2023-05-09 | 2023-05-09 | 2024-05-15 | Late | 2024-05-08 | -7 | 2024-05-09 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46193873 | T2 EI DIABLO-MIDWAY #3 38/155 RPR GYWT | ICQ
LC | 126084774 | 013/167 | T2 DI KSWCK-TRINITY 013/167 RPR GYWW | TABLEMTN | ETL.7270.POLE.WDPS | 2023-05-09 | 2023-05-03 | 2024-04-12 | On-time | 2024-05-02 | 20 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053901 | T2 DI KSWCK-TRINITY 013/167 RPR GYWW | ICW
LC | 126084779 | 013/163 | T2 DI KSWCK-TRINITY 013/163 RPL HRDD | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-09 | 2023-05-03 | 2023-12-11 | On-time | 2024-05-02 | 143 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46046166 | T2 DI KSWCK-TRINITY 013/163 RPL HRDD | ICW
LC | 126084848 | 015/189 | T2 DI KESWICK-TRINITY 15/189 RPL POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-09 | 2023-05-03 | 2024-04-29 | On-time | 2024-05-02 | 3 | 2024-05-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512715 | T2 DI KESWICK-TRINITY 9/118 RPL POLE | 70Y
LC | 126084943 | 021/322 | T2 DI KESWICK-TRINITY 021/322 COTTER | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-09 | 2023-05-03 | 2024-04-17 | On-time | 2024-05-02 | 15 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46053904 | T2 DI KESWICK-TRINITY 021/322 COTTER | ICW
LC | 126084991 | 014/178 | T2 DI KSWCK-TRINITY 014/178 RPR STRW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-09 | 2023-05-03 | 2024-04-12 | On-time | 2024-05-02 | 20 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046167 | T2 DI KSWCK-TRINITY 014/178 RPR STRW | ICW
LC | 126095055 | 013/162 | T2 DI KESWICK-TRINITY 013/162 COTTER | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-10 | 2023-05-03 | 2023-12-11 | On-time | 2024-05-02 | 143 | 2024-05-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046165 | T2 DI KESWICK-TRINITY 013/162 COTTER | ICW
LC | 126095250 | 013/162 | T2 DI KESWICK-TRINITY 013/162 RPR JMPW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-10 | 2023-05-03 | 2023-07-19 | On-time | 2024-05-02 | 288 | 2023-08-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45763991 | T2 DI KESWICK-TRINITY 013/162 RPR JMPW | ICW
LC | 126118956 | 048/023 | T2 DI TRNTY-MPL CRK 048/023 RPR ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-03 | 2023-06-15 | On-time | 2024-05-02 | 322 | 2023-11-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45767977 | T2 DI TRNTY-MPL CRK 048/023 RPR ANCW | ICW
LC | 126047360 | 024/381 | T2 DI KESWICK-TRINITY 024/381 RPR INSW | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-04 | 2023-05-04 | 2023-07-23 | On-time | 2024-05-03 | 285 | 2023-08-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45758008 | T2 DI KESWICK-TRINITY 024/381 RPR INSW | ICW
LC | 126047611 | 026/426 | T2 DI KESWICK-TRNTY 26/426 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-04 | 2023-05-04 | 2023-07-13 | On-time | 2024-05-03 | 295 | 2023-08-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45762941 | T2 DI KESWICK-TRNTY 26/426 RPR GYWW | ICW
LC | 126048048 | 004/046 | T2 EI PARADISE-TABLE MTN 4/46 INS DAMP | TABLEMTN | ETL.4316.INSL.NCER | 2023-05-04 | 2023-05-04 | 2024-01-30 | On-time | 2024-05-03 | 94 | 2024-05-04 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46046103 | T2 EI PARADISE-TABLE MTN 4/46 INS DAMP | ICW
LC | 126049146 | 006/050 | T2 EI PIT #1-COTTONWOOD 6/50 COMPLETED | TABLEMTN | ETL.5390.TOWR | 2023-05-04 | 2023-05-04 | 2024-01-23 | On-time | 2024-05-03 | 101 | 2024-05-04 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 46045951 | T2 EI PIT #1-COTTONWOOD 6/50 UNBURY | ICS
LC | 126049513 | 068/282 | T2 EI RND MTN-TBLE MN #2 68/282 RPR CNDW | TABLEMTN | ETL.6070.INSL | 2023-05-04 | 2023-05-04 | 2024-04-26 | On-time | 2024-05-03 | 7 | 2024-05-04 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46046049 | T2 EI RND MTN-TBLE MN #2 68/282 RPR CNDW | ICS
LC | 126049929 | 001/026-GUY | T2 EI JFFRSN-STNFRD 001/026-GUY RMV VEG | METCALF | ETL.7220.POLE.WOOD | 2023-05-04 | 2023-05-04 | 2023-12-06 | On-time | 2024-05-03 | 149 | 2024-05-04 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Trim
LC | 126050158 | 068/282 | T2 EI RND MTN-TBLE MN #1 68/282 COMPLETE | TABLEMTN | ETL.6060.INSL.NCER | 2023-05-04 | 2023-05-04 | 2024-04-20 | On-time | 2024-05-03 | 13 | 2024-05-04 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46046052 | T2 EI RND MTN-TBLE MN #1 68/282 RPR CNDS | ICS
LC | 126050159 | 068/282 | T2 EI RND MTN-TBLE MN #1 68/282 RPR STRT | TABLEMTN | ETL.6060.TOWR | 2023-05-04 | 2023-05-04 | 2024-02-22 | On-time | 2024-05-03 | 71 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072129 | T2 EI RND MTN-TBLE MN #1 68/282 RPR STRT | ICQ
LC | 126050575 | 053/475 | T2 EI PIT #1-COTTONWD 053/475 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-04 | 2023-05-04 | 2023-11-09 | On-time | 2024-05-03 | 176 | 2024-05-04 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46044434 | T2 EI PIT #1-COTTONWD 053/475 UNBURY | ICQ
LC | 126053492 | 033/182 | T2 DI EXCHR-IDN FLT-YSMT 33/182 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-05-04 | 2023-05-04 | 2023-12-15 | On-time | 2024-05-03 | 140 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45977780 | T2 DI EXCHR-IDN FLT-YSMT 33/182 UNBURY | ICQ
LC | 126053496 | 033/182 | T2 DI EXCHR-IDN FLT-YSMT 33/182 RPR STRT | FRESNO | ETL.8650.POLE.NWOD | 2023-05-04 | 2023-05-04 | 2023-12-15 | On-time | 2024-05-03 | 140 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45977781 | T2 DI EXCHR-IDN FLT-YSMT 33/182 RPR STRT | ICQ
LC | 126084412 | 016/213 | T2 DI KESWICK-TRINITY 16/213 RPR JUMW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-09 | 2023-05-04 | 2023-07-19 | On-time | 2024-05-03 | 289 | 2023-08-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45770758 | T2 DI KESWICK-TRINITY 16/213 RPR JUMW | ICW
LC | 126084444 | 017/222 | T2 DI KSWCK-TRINITY 17/222 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-09 | 2023-05-04 | 2024-02-13 | On-time | 2024-05-03 | 80 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046321 | T2 DI KSWCK-TRINITY 17/222 RPR GYWW | ICW
LC | 126084445 | 026/425 | T2 DI KESWICK-TRINITY 26/425 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-09 | 2023-05-04 | 2023-07-13 | On-time | 2024-05-03 | 295 | 2023-11-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45763374 | T2 DI KESWICK-TRINITY 26/425 RPR GYWW | ICW
LC | 126084578 | 018/250 | T2 DI KESWICK-TRINITY 18/250 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-09 | 2023-05-04 | 2024-04-16 | On-time | 2024-05-03 | 17 | 2023-11-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046297 | T2 DI KESWICK-TRINITY 18/250 RPR GYWW | ICW
LC | 126084585 | 019/269 | T2 DI KESWICK-TRINITY 19/269 RPL TIED | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-09 | 2023-05-04 | 2024-04-17 | On-time | 2024-05-03 | 16 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46046287 | T2 DI KESWICK-TRINITY 19/269 RPL TIED | ICW
LC | 126084587 | 019/269 | T2 DI KESWICK-TRINITY 19/269 RPR STRW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-09 | 2023-05-04 | 2024-04-17 | On-time | 2024-05-03 | 16 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046286 | T2 DI KESWICK-TRINITY 19/269 RPR STRW | ICW
LC | 126084645 | 019/287 | T2 DI KSWCK-TRNTY 19/287 RPR POLE | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-09 | 2023-05-04 | 2024-04-17 | On-time | 2024-05-03 | 16 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046284 | T2 DI KSWCK-TRNTY 19/287 RPR POLE | ICW
LC | 126084646 | 019/287 | T2 DI KSWCK-TRNTY 19/287 RPL HRDW | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-09 | 2023-05-04 | 2024-04-17 | On-time | 2024-05-03 | 16 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046283 | T2 DI KSWCK-TRNTY 19/287 RPL HRDW | ICW
LC | 126084680 | 019/269 | T2 DI KESWICK-TRINITY 19/269 RPR ANCW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-09 | 2023-05-04 | 2024-04-17 | On-time | 2024-05-03 | 16 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46046289 | T2 DI KESWICK-TRINITY 19/269 RPR ANCW | ICW
LC | 126084682 | 019/269 | T2 DI KESWICK-TRINITY 19/269 RPR JMPW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-09 | 2023-05-04 | 2024-04-17 | On-time | 2024-05-03 | 16 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46046288 | T2 DI KESWICK-TRINITY 19/269 RPR JMPW | ICW
LC | 126084722 | 023/356 | T2 DI KSWCK-TRNTY 23/356 RPR INSW | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-09 | 2023-05-04 | 2024-04-24 | On-time | 2024-05-03 | 9 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046219 | T2 DI KSWCK-TRNTY 23/356 RPR INSW | ICW
LC | 126084959 | 049/013 | T2 DI TRINTY-MPL CR 49/13 RPL PL | EUREKA | ETL.8170.POLE.WOOD | 2023-05-09 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506451 | T2 DI TRINTY-MPL CR 49/13 RPL PL | 70Y
LC | 126084728 | 026/433 | T2 DI KESWICK-TRINITY 26/433 RPR CRSW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-09 | 2023-05-04 | 2024-04-20 | On-time | 2024-05-03 | 13 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46046210 | T2 DI KESWICK-TRINITY 26/433 RPR CRSW | ICW
LC | 126084729 | 025/417 | T2 DI KESWICK-TRINITY 25/417 RPR WDPK | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-09 | 2023-05-04 | 2024-02-22 | On-time | 2024-05-03 | 71 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046214 | T2 DI KESWICK-TRINITY 25/417 RPR WDPK | ICW
LC | 126084792 | 024/379 | T2 DI KSWCK-TRNTY 24/379 RPR STRW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-09 | 2023-05-04 | 2024-04-20 | On-time | 2024-05-03 | 13 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046217 | T2 DI KSWCK-TRNTY 24/379 RPR STRW | ICW
LC | 126084864 | 012/157 | T2 DI KESWICK-TRINITY 012/157 RPL INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-09 | 2023-05-04 | 2024-04-12 | On-time | 2024-05-03 | 21 | 2024-05-04 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31657756 | T2 KESWICK-TRINITY 10/123 GO95 | 93G
LC | 126084870 | A000/020 | T2 DI COLGATE-CHALENGE A00/20 RPR STRW | SACTO | ETL.6480.POLE.WOOD | 2023-05-09 | 2023-05-04 | 2024-04-08 | On-time | 2024-05-03 | 25 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046465 | T2 DI COLGATE-CHALENGE A00/20 RPR STRW | ICW
LC | 126092974 | 035/008 | T2 MNDCNO-WLLTS-FRT BRGG 35/8 RPR HRDW | WILLITS | ETL.7550.POLE.WOOD | 2023-05-10 | 2023-05-10 |  | Late | 2024-05-09 |  | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46214096 | T2 MNDCNO-WLLTS-FRT BRGG 35/8 RPR HRDW | ICW
LC | 126084911 | 018/255 | T2 DI KESWICK-TRINITY 18/255 RPR INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-09 | 2023-05-04 | 2024-04-16 | On-time | 2024-05-03 | 17 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046293 | T2 DI KESWICK-TRINITY 18/255 RPR INSW | ICW
LC | 126084912 | 018/255 | T2 DI KESWICK-TRINITY 18/255 RPR JMPW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-09 | 2023-05-04 | 2024-04-16 | On-time | 2024-05-03 | 17 | 2023-08-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46201033 | T2 DI KESWICK-TRINITY 18/255 RPR JMPW | ICW
LC | 126084914 | 018/255 | T2 DI KESWICK-TRINITY 18/255 RPR STRW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-09 | 2023-05-04 | 2024-04-16 | On-time | 2024-05-03 | 17 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046291 | T2 DI KESWICK-TRINITY 18/255 RPR STRW | ICW
LC | 126095398 | 039/009 | T2 DI TRNTY-MPLE CREEK 39/9 RPL DAMW | EUREKA | ETL.8170.INSL.NCER | 2023-05-10 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46172184 | T2 DI TRNTY-MPLE CREEK 39/9 RPL DAMW | ICW
LC | 126084931 | 016/215 | T2 DI KESWICK-TRINITY 16/215 RPR CONN | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-09 | 2023-05-04 | 2023-07-19 | On-time | 2024-05-03 | 289 | 2023-08-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45805351 | T2 DI KESWICK-TRINITY 16/215 RPR CONN | ICW
LC | 126085042 | 018/245 | T2 DI KESWICK-TRINITY 018/245 RPR GYWW | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-09 | 2023-05-04 | 2024-04-16 | On-time | 2024-05-03 | 17 | 2023-11-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046299 | T2 DI KESWICK-TRINITY 018/245 RPR GYWW | ICW
LC | 126085047 | 018/245 | T2 DI KESWICK-TRINITY 18/245 RPR JMPW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-09 | 2023-05-04 | 2024-04-16 | On-time | 2024-05-03 | 17 | 2023-08-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46194277 | T2 DI KESWICK-TRINITY 18/245 RPR JMPW | ICW
LC | 126096360 | 047/013 | T2 DI TRNTY-MPL CREEK 47/13 RPL HRDD | EUREKA | ETL.8170.POLE.WOOD | 2023-05-10 | 2023-05-10 |  | Late | 2024-05-09 |  | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46172252 | T2 DI TRNTY-MPL CREEK 47/13 RPL HRDD | ICW
LC | 126085072 | 014/171A | T2 DI KESWICK-TRINITY 14/171A RPL HRDD | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-09 | 2023-05-04 | 2023-12-11 | On-time | 2024-05-03 | 144 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46046324 | T2 DI KESWICK-TRINITY 14/171A RPL HRDD | ICW
LC | 126085153 | 025/421 | T2 DI KESWICK-TRINITY 25/421 RPR WDPK | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-09 | 2023-05-04 | 2024-04-20 | On-time | 2024-05-03 | 13 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046213 | T2 DI KESWICK-TRINITY 25/421 RPR WDPK | ICW
LC | 126095829 | 016/202 | T2 DI KESWCK-TRNTY 16/202 RPR JUMW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-10 | 2023-05-04 | 2023-07-19 | On-time | 2024-05-03 | 289 | 2023-11-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45805411 | T2 DI KESWCK-TRNTY 16/202 RPR JUMW | ICW
LC | 126097568 | 038/251A | T2 EI TRINITY-CTTNWD 038/251A RPL ANCW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-10 | 2023-05-10 |  | Late | 2024-05-09 |  | 2024-05-10 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35561429 | T2 EI TRINITY-CTTNWD 038/251A RPL ANCW | 93E
LC | 126099616 | 022/344 | T2 DI KESWCK-TRNTY 22/344 MASTIC | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-10 | 2023-05-04 | 2024-02-21 | On-time | 2024-05-03 | 72 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046282 | T2 DI KESWCK-TRNTY 22/344 MASTIC | ICW
LC | 126100705 | 024/380 | T2 DI KESWCK-TRNTY 24/380 RPR INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-10 | 2023-05-04 | 2024-04-20 | On-time | 2024-05-03 | 13 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046216 | T2 DI KESWCK-TRNTY 24/380 RPR INSW | ICW
LC | 126102081 | 021/324 | T2 DI KESWCK-TRNTY 21/324 RPL INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-10 | 2023-05-04 | 2023-11-11 | On-time | 2024-05-03 | 174 | 2024-05-04 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31645688 | T2 DI KESWCK-TRNTY 21/324 RPL INSW | 93I
LC | 126097690 | 013/262 | T2 EI CARIBOU-WESTWD 13/262 RPR STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-10 | 2023-05-10 |  | Late | 2024-05-09 |  | 2024-05-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46129637 | T2 EI CARIBOU-WESTWD 13/262 RPR STRW | ICW
LC | 126102315 | 019/284 | T2 DI KESWCK-TRNTY 19/284 RPL INSW | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-10 | 2023-05-04 | 2024-04-17 | On-time | 2024-05-03 | 16 | 2024-05-04 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35515825 | T2 DI KESWCK-TRNTY 19/284 RPL INSW | 93I
LC | 126098120 | 022/581 | T2 EI CARIBOU #2 22/581 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-10 | 2023-05-10 |  | Late | 2024-05-09 |  | 2024-05-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053960 | T2 EI CARIBOU #2 022/581 RPR GYWW | ICW
LC | 126098224 | A001/022 | T2 WV SMARTVILLE-CAMP FW A01/22 INS DMPW | SACTO | ETL.7970.INSL.NCER | 2023-05-10 | 2023-05-10 |  | Late | 2024-05-09 |  | 2024-05-10 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 46049070 | T2 WV SMARTVILLE-CAMP FW A01/22 INS DMPW | ICW
LC | 126102708 | 025/416 | T2 DI KESWICK-TRINITY 25/416 RPR WDPK | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-10 | 2023-05-04 | 2024-02-22 | On-time | 2024-05-03 | 71 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046215 | T2 DI KESWICK-TRINITY 25/416 RPR WDPK | ICW
LC | 126102802 | 012/155 | T2 DI KESWK-TRINTY 12/155 RPR JUMW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-10 | 2023-05-04 | 2024-04-12 | On-time | 2024-05-03 | 21 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46046325 | T2 DI KESWK-TRINTY 12/155 RPR JUMW | ICW
LC | 126102804 | 012/155 | T2 DI KESWK-TRINTY 12/155 RPR ANCW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-10 | 2023-05-04 | 2023-06-27 | On-time | 2024-05-03 | 311 | 2023-11-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45770975 | T2 DI KESWK-TRINTY 12/155 RPR ANCW | ICW
LC | 126102831 | 026/434 | T2 DI KESWICK-TRINITY 26/434 RPR HRDW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-10 | 2023-05-04 | 2024-04-20 | On-time | 2024-05-03 | 13 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46046209 | T2 DI KESWICK-TRINITY 26/434 RPR HRDW | ICW
LC | 126098633 | 022/578 | T2 EI CARIBOU #2 22/578 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-10 | 2023-05-10 |  | Late | 2024-05-09 |  | 2024-05-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053939 | T2 EI CARIBOU #2 022/578 RPR GYWW | ICW
LC | 126098792 | 003/040 | T2 EI PT #1-HT CRK #2-BRNY 3/40 RPL STRW | TABLEMTN | ETL.7040.POLE.WOOD | 2023-05-10 | 2023-05-10 | 2024-05-14 | Late | 2024-05-09 | -5 | 2024-05-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485424 | T2 EI PT #1-HT CRK #2-BRNY 3/40 RPL STRW | 70Y
LC | 126102998 | 018/257 | T2 DI KESWK-TRINTY 18/257 RPL INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-10 | 2023-05-04 | 2024-04-16 | On-time | 2024-05-03 | 17 | 2024-05-04 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35512894 | T2 DI KESWK-TRINTY 18/257 RPL INSW | 93I
LC | 126103027 | 012/158 | T2 DI KESWICK-TRINITY 12/158 RPR ANCW | TABLEMTN | ETL.7270.POLE.WOOD | 2023-05-10 | 2023-05-04 | 2023-06-27 | On-time | 2024-05-03 | 311 | 2023-11-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45805409 | T2 DI KESWICK-TRINITY 12/158 RPR ANCW | ICW
LC | 126099404 | 000/011 | T2 EI PINE GROVE TAP 000/011 RPL POLE | VICTOR | ETL.8351.POLE.WOOD | 2023-05-10 | 2023-05-10 |  | Late | 2024-05-09 |  | 2024-05-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525753 | T2 EI PINE GROVE TAP 000/003 RPL POLE | 70Y
LC | 126103049 | 018/254 | T2 DI KESWK-TRINTY 18/254 RPR CNDW | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-10 | 2023-05-04 | 2024-04-16 | On-time | 2024-05-03 | 17 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46046295 | T2 DI KESWK-TRINTY 18/254 RPR CNDW | ICW
LC | 126099701 | 004/056 | T2 EI BURNS-LONE STAR #1 004/56 RMV VEG | MOSSLNDG | ETL.6230.POLE.NWOD | 2023-05-10 | 2023-05-10 |  | Late | 2024-05-09 |  | 2024-05-10 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126103124 | 012/039 | T2 DI EXCHEQUR-INDIAN FLT 12/39 RPL HRDT | FRESNO | ETL.8650.TOWR | 2023-05-10 | 2023-05-04 | 2023-12-08 | On-time | 2024-05-03 | 147 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46051189 | T2 DI EXCHEQUR-INDIAN FLT 12/39 RPL HRDT | ICQ
LC | 126103126 | 012/039 | T2 DI EXCHEQUER-INDIAN FLAT 12/39 UNBURY | FRESNO | ETL.8650.TOWR | 2023-05-10 | 2023-05-04 | 2023-12-08 | On-time | 2024-05-03 | 147 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46051190 | T2 DI EXCHEQUER-INDIAN FLAT 12/39 UNBURY | ICQ
LC | 126103184 | 029/148 | T2 DI EXCHQUER-INDIAN FLAT 29/148 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-05-10 | 2023-05-04 | 2023-12-15 | On-time | 2024-05-03 | 140 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45977754 | T2 DI EXCHQUER-INDIAN FLAT 29/148 UNBURY | ICQ
LC | 126101174 | 005/067 | T2 EI WST POINT-VLEY SPRNGS 5/6 RPR POLE | VICTOR | ETL.8350.POLE.WOOD | 2023-05-10 | 2023-05-10 |  | Late | 2024-05-09 |  | 2024-05-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46200345 | T2 EI WST POINT-VLEY SPRNGS 5/6 RPR POLE | ICW
LC | 126103188 | 012/037 | T2 DI EXCHQR-IDN FT-YSMTE 12/37 COMPLETE | FRESNO | ETL.8650.INSL.NCER | 2023-05-10 | 2023-05-04 | 2024-05-02 | On-time | 2024-05-03 | 1 | 2023-08-04 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46190169 | T2 DI EXCHQR-IDN FT-YSMTE 12/37 RPR JMPS | ICS
LC | 126103282 | 020/076 | T2 DI EXCHR INDN FLT-YSMT 20/76 INS HRDT | FRESNO | ETL.8650.TOWR | 2023-05-10 | 2023-05-04 | 2023-12-13 | On-time | 2024-05-03 | 142 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Tower | Install | 46051301 | T2 DI EXCHR INDN FLT-YSMT 20/76 INS HRDT | ICQ
LC | 126101381 | 012/145A | T2 EI DRUM-SUMMIT #1 12/145A RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-05-10 | 2023-05-10 | 2024-06-23 | Late | 2024-05-09 | -45 | 2024-05-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46049071 | T2 EI DRUM-SUMMIT #1 12/145A RPR GYWW | ICW
LC | 126103288 | 020/076 | T2 DI EXCHR IND FLT-YSMT 20/76 BNT STEEL | FRESNO | ETL.8650.TOWR | 2023-05-10 | 2023-05-04 | 2023-12-13 | On-time | 2024-05-03 | 142 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46051302 | T2 DI EXCHR IND FLT-YSMT 20/76 BNT STEEL | ICQ
LC | 126103419 | 026/438 | T2 DI KESWICK-TRINITY 026/438 COTTER | TABLEMTN | ETL.7270.INSL.CERA | 2023-05-10 | 2023-05-04 | 2023-07-22 | On-time | 2024-05-03 | 286 | 2023-08-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45770759 | T2 DI KESWICK-TRINITY 026/438 COTTER | ICW
LC | 126103462 | 035/202 | T2 DI EXCHQR-IDN FLT-YSMT 35/202 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-05-10 | 2023-05-04 | 2023-12-11 | On-time | 2024-05-03 | 144 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45977795 | T2 DI EXCHQR-IDN FLT-YSMT 35/202 UNBURY | ICQ
LC | 126103498 | 001/009 | T2 DI EXCHEQUER-INDIAN FLT 1/9 BNT STEEL | FRESNO | ETL.8650.TOWR | 2023-05-10 | 2023-05-04 | 2023-12-05 | On-time | 2024-05-03 | 150 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46051187 | T2 DI EXCHEQUER-INDIAN FLT 1/9 BNT STEEL | ICQ
LC | 126103533 | 001/010 | T2 DI EXCHEQUER-INDIN FLT 1/10 BNT STEEL | FRESNO | ETL.8650.TOWR | 2023-05-10 | 2023-05-04 | 2023-12-05 | On-time | 2024-05-03 | 150 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46051188 | T2 DI EXCHEQUER-INDIN FLT 1/10 BNT STEEL | ICQ
LC | 126102489 | 082/417 | T2 EI MALIN-ROUND MTN #2 82/417 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2023-05-10 | 2023-05-10 |  | Late | 2024-05-09 |  | 2024-05-10 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46057502 | T2 EI MALIN-ROUND MTN #2 82/417 RPR GYWS | ICS
LC | 126102496 | 082/418 | T2 EI MALIN-ROUND MTN #2 82/418 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2023-05-10 | 2023-05-10 |  | Late | 2024-05-09 |  | 2024-05-10 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46057503 | T2 EI MALIN-ROUND MTN #2 82/418 RPR GYWS | ICS
LC | 126102556 | 077/314 | T2 EI RND MT-TBL MT #1 77/314 BNT STEEL | TABLEMTN | ETL.6060.TOWR | 2023-05-10 | 2023-05-10 |  | Late | 2024-05-09 |  | 2024-05-10 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072133 | T2 EI RND MTN-TABL MTN #1 77/314 BNT STL | ICQ
LC | 126103616 | 015/049 | T2 DI EXCHEQR-IND FL-YSM 15/49 BNT STEEL | FRESNO | ETL.8650.TOWR | 2023-05-10 | 2023-05-04 | 2023-12-07 | On-time | 2024-05-03 | 148 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46051191 | T2 DI EXCHEQR-IND FL-YSM 15/49 BNT STEEL | ICQ
LC | 126103619 | 016/056 | T2 DI EXCHEQUER-INDIAN FLAT 16/56 UNBURY | FRESNO | ETL.8650.TOWR | 2023-05-10 | 2023-05-04 | 2023-12-08 | On-time | 2024-05-03 | 147 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46051198 | T2 DI EXCHEQUER-INDIAN FLAT 16/56 UNBURY | ICQ
LC | 126111408 | 019/069 | T2 DI EXCHEQUER-INDN FLT 19/69 RPR FOND | FRESNO | ETL.8650.TOWR | 2023-05-11 | 2023-05-04 | 2023-12-14 | On-time | 2024-05-03 | 141 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46051300 | T2 DI EXCHEQUER-INDN FLT 19/69 RPR FOND | ICQ
LC | 126111585 | 031/167 | T2 DI EXCHEQUR-INDN FLT 31/167 BNT STEEL | FRESNO | ETL.8650.POLE.NWOD | 2023-05-11 | 2023-05-04 | 2023-12-12 | On-time | 2024-05-03 | 143 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45977757 | T2 DI EXCHEQUR-INDN FLT 31/167 BNT STEEL | ICQ
LC | 126111598 | 025/113 | T2 DI EXCHQR-IDN FT-YSMT 25/113 RPR FOND | FRESNO | ETL.8650.POLE.NWOD | 2023-05-11 | 2023-05-04 | 2023-12-14 | On-time | 2024-05-03 | 141 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45977743 | T2 DI EXCHQR-IDN FT-YSMT 25/113 RPR FOND | ICQ
LC | 126111661 | 023/087 | T2 DI EXCHQR-INDN FT-YSMT 23/87 UNBURY | FRESNO | ETL.8650.TOWR | 2023-05-11 | 2023-05-04 | 2023-12-14 | On-time | 2024-05-03 | 141 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45977479 | T2 DI EXCHQR-INDN FT-YSMT 23/87 UNBURY | ICQ
LC | 126111811 | 39 | T2 DI EXQR-INDN FT-YSMTE 14/45A RPR SWTC | FRESNO | ETL.8650.SWIT | 2023-05-11 | 2023-05-04 | 2024-05-02 | On-time | 2024-05-03 | 1 | 2024-05-04 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 46045666 | T2 DI EXQR-INDN FT-YSMTE 14/45A RPR SWTC | ICE
LC | 126111892 | 015/051 | T2 DI EXQR-INDN FT-YSMT 15/51 BNT STEEL | FRESNO | ETL.8650.TOWR | 2023-05-11 | 2023-05-04 | 2023-12-07 | On-time | 2024-05-03 | 148 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46051197 | T2 DI EXQR-INDN FT-YSMT 15/51 BNT STEEL | ICQ
LC | 126111938 | 003/017 | T2 DI EXCHEQUER-INDIAN FLAT 3/17 JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-05-11 | 2023-05-04 | 2024-02-14 | On-time | 2024-05-03 | 79 | 2023-08-04 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46190168 | T2 DI EXCHEQUER-INDIAN FLAT 3/17 JMPS | ICS
LC | 126112051 | 028/137 | T2 DI EXCHEQUER IDIAN FLAT 28/137 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-05-11 | 2023-05-04 | 2023-12-12 | On-time | 2024-05-03 | 143 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45977747 | T2 DI EXCHEQUER IDIAN FLAT 28/137 UNBURY | ICQ
LC | 126103169 | A000/021 | T2 DI COLGATE-CHALLENGE A000/21 RPL POLE | SACTO | ETL.6480.POLE.WOOD | 2023-05-10 | 2023-05-04 |  | Late | 2024-05-03 |  | 2024-05-04 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35483350 | T2 DI COLGATE-CHALLENGE A000/21 RPL POLE | 70Y
LC | 126112167 | 035/203 | T2 DI EXCHQUR-INDN FLT 35/203 INS STEP | FRESNO | ETL.8650.TOWR | 2023-05-11 | 2023-05-04 | 2023-12-15 | On-time | 2024-05-03 | 140 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45977799 | T2 DI EXCHQUR-INDN FLT 35/203 INS STEP | ICQ
LC | 126112195 | 035/196 | T2 DI EXCHQUR-INDN FLT 35/196 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-05-11 | 2023-05-04 | 2023-12-11 | On-time | 2024-05-03 | 144 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45977789 | T2 DI EXCHQUR-INDN FLT 35/196 UNBURY | ICQ
LC | 126103263 | 020/076 | T2 DI EXCHEQUR FLAT-YOSMIT 20/76 RMV VEG | FRESNO | ETL.8650.TOWR | 2023-05-10 | 2023-05-04 | 2024-06-27 | Late | 2024-05-03 | -55 | 2024-05-04 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126112197 | 035/196 | T2 DI EXCHQUR-INDN FLT 35/196 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-05-11 | 2023-05-04 | 2023-12-11 | On-time | 2024-05-03 | 144 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45977790 | T2 DI EXCHQUR-INDN FLT 35/196 UNBURY | ICQ
LC | 126112239 | 033/189 | T2 DI EXCHQR-INDN FLT 33/189 COTTER | FRESNO | ETL.8650.INSL.NCER | 2023-05-11 | 2023-05-04 | 2023-12-12 | On-time | 2024-05-03 | 143 | 2024-05-04 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45954710 | T2 DI EXCHQR-INDN FLT 33/189 COTTER | ICS
LC | 126103336 | 019/514 | T2 EI CARIBOU #2 19/514 RPR INSW | TABLEMTN | ETL.6280.INSL.NCER | 2023-05-10 | 2023-05-10 |  | Late | 2024-05-09 |  | 2024-05-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46053938 | T2 EI CARIBOU #2 19/514 RPR INSW | ICW
LC | 126112425 | 022/085A | T2NT DI EXCHQUR-INDN FLT 22/85A RPR JUM | FRESNO | ETL.8650.INSL.NCER | 2023-05-11 | 2023-05-04 | 2023-12-11 | On-time | 2024-05-03 | 144 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45954711 | T2NT DI EXCHQUR-INDN FLT 22/85A RPR JUM | ICW
LC | 126113751 | 017/062 | T2 DI EXCHEQUER-INDIAN FLAT 17/62 UNBURY | FRESNO | ETL.8650.TOWR | 2023-05-12 | 2023-05-04 | 2023-12-14 | On-time | 2024-05-03 | 141 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46051199 | T2 DI EXCHEQUER-INDIAN FLAT 17/62 UNBURY | ICQ
LC | 126113877 | 035/203A | T2 DI EXCHQUR-INDIAN FLAT 35/203A UNBURY | FRESNO | ETL.8650.TOWR | 2023-05-12 | 2023-05-04 | 2023-12-11 | On-time | 2024-05-03 | 144 | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45977860 | T2 DI EXCHQUR-INDIAN FLAT 35/203A UNBURY | ICQ
LC | 126121773 | 45 | T2 DI COLGATE-CHALNGE A00/16 RPL HRDD | SACTO | ETL.6480.SWIT | 2023-05-12 | 2023-05-04 | 2024-04-10 | On-time | 2024-05-03 | 23 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46046466 | T2 DI COLGATE-CHALNGE A00/16 RPL HRDD | ICW
LC | 126121873 | 018/251 | T2 DI KESWICK-TRINITY 18/251 RPR INSW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-12 | 2023-05-04 | 2024-04-16 | On-time | 2024-05-03 | 17 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046296 | T2 DI KESWICK-TRINITY 18/251 RPR INSW | ICW
LC | 126121913 | 35 | T2 DI COLGATE-CHALENGE 00/16 RPR SWTC | SACTO | ETL.6480.SWIT | 2023-05-12 | 2023-05-04 | 2024-04-08 | On-time | 2024-05-03 | 25 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 46046468 | T2 DI COLGATE-CHALENGE 00/16 RPR SWTC | ICW
LC | 126121915 | 000/016 | T2 DI COLGATE-CHALNGE 00/16 RPR STRW | SACTO | ETL.6480.POLE.WOOD | 2023-05-12 | 2023-05-04 | 2024-04-30 | On-time | 2024-05-03 | 3 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46046469 | T2 DI COLGATE-CHALNGE 00/16 RPR STRW | ICW
LC | 126121916 | 35 | T2 DI COLGATE-CHALENGE 00/16 RPR INSW | SACTO | ETL.6480.SWIT | 2023-05-12 | 2023-05-04 | 2024-04-08 | On-time | 2024-05-03 | 25 | 2024-05-04 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046470 | T2 DI COLGATE-CHALENGE 00/16 RPR INSW | ICW
LC | 126058068 | 038/176 | T2 WV RND MTN-TBLE MN #1 38/176 COMPLETE | TABLEMTN | ETL.6060.INSL.NCER | 2023-05-05 | 2023-05-05 | 2024-04-17 | On-time | 2024-05-04 | 17 | 2024-05-05 | 532 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31617249 | T2 EI RND MTN-TBL MTN #1 23/118 RPL INSS | 93K
LC | 126058836 | 054/484 | T2 EI PIT #1-COTTONWOOD 54/484 MASTIC | TABLEMTN | ETL.5390.TOWR | 2023-05-05 | 2023-05-05 | 2023-11-13 | On-time | 2024-05-04 | 173 | 2024-05-05 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46044435 | T2 EI PIT #1-COTTONWOOD 54/484 MASTIC | ICQ
LC | 126058871 | 000/004 | T2 WV WEIMAR-HALSEY 000/004 INS DMPW | SACTO | ETL.8340.INSL.NCER | 2023-05-05 | 2023-05-05 | 2024-01-23 | On-time | 2024-05-04 | 102 | 2024-05-05 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46046418 | T2 WV WEIMAR-HALSEY 000/004 INS DMPW | ICW
LC | 126058954 | 022/174 | T2 EI MDL FRK-GLD HLL 022/174L RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2023-05-05 | 2023-05-05 | 2024-02-13 | On-time | 2024-05-04 | 81 | 2024-05-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46046460 | T2 EI MDL FRK-GLD HLL 022/174L RPR GYWW | ICW
LC | 126105521 | 096/003 | T2 EI HUMBOLDT-TRINITY 96/3 REFRAME | EUREKA | ETL.1820.POLE.STPS | 2023-05-11 | 2023-05-11 |  | Late | 2024-05-10 |  | 2024-05-11 | 637T | TLN | PATR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35505974 | T2 EI HUMBOLDT-TRINITY 96/3 REFRAME | 93E
LC | 126105967 | 000/001A | T2 EI BELDEN TAP 000/001A COTTER | TABLEMTN | ETL.4441.INSL.NCER | 2023-05-11 | 2023-05-11 | 2024-06-12 | Late | 2024-05-10 | -33 | 2024-05-11 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46060978 | T2 EI BELDEN TAP 000/001A COTTER | ICS
LC | 126062084 | 021/003 | T2 EI MNDCN-WLTS-FRT BRG 21/3 RPR GYW | WILLITS | ETL.7550.POLE.NWOD | 2023-05-05 | 2023-05-05 | 2023-06-14 | On-time | 2024-05-04 | 325 | 2023-08-05 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45762720 | T2 EI MNDCN-WLTS-FRT BRG 21/3 RPR GYW | ICS
LC | 126062112 | 044/295A | T2 EI TRINITY-CTTNWD 044/295A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-05 | 2023-05-05 | 2023-06-14 | On-time | 2024-05-04 | 325 | 2023-08-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45763402 | T2 EI TRINITY-CTTNWD 044/295A RPR GYWW | ICW
LC | 126106744 | A000/007 | T2 WV SMARTVILLE-CAMP FW A00/07 INS DMPW | SACTO | ETL.7970.INSL.NCER | 2023-05-11 | 2023-05-11 |  | Late | 2024-05-10 |  | 2024-05-11 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 46053999 | T2 WV SMARTVILLE-CAMP FW A00/07 INS DMPW | ICW
LC | 126062152 | 021/008 | T2 EI MNDCINO-WLTS-FRT BRG 21/8 RPR GYWW | WILLITS | ETL.7550.POLE.NWOD | 2023-05-05 | 2023-05-05 | 2023-06-14 | On-time | 2024-05-04 | 325 | 2023-08-05 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45762721 | T2 EI MNDCINO-WLTS-FRT BRG 21/8 RPR GYWW | ICS
LC | 126062399 | 026/006 | T2 EI MNDCINO-WLTS-FRT BRG 26/6 RPR GYWW | WILLITS | ETL.7550.POLE.NWOD | 2023-05-05 | 2023-05-05 | 2023-06-13 | On-time | 2024-05-04 | 326 | 2023-08-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45762723 | T2 EI MNDCINO-WLTS-FRT BRG 26/6 RPR GYWW | ICW
LC | 126062414 | 044/295B | T2 EI TRINITY-CTTNWD 044/295B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-05 | 2023-05-05 | 2023-06-14 | On-time | 2024-05-04 | 325 | 2024-05-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45906894 | T2 EI TRINITY-CTTNWD 044/295B RPR GYWW | ICW
LC | 126062489 | 003/034 | T2 EI PIT #1-HAT CREEK #2 3/34 COTR KEY | TABLEMTN | ETL.7040.INSL.NCER | 2023-05-05 | 2023-05-05 | 2024-04-22 | On-time | 2024-05-04 | 12 | 2023-11-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46046207 | T2 EI PIT #1-HAT CREEK #2 3/34 COTR KEY | ICW
LC | 126107168 | 018/150 | T2 EI PIT #1-COTTONWOOD 018/150 RPR JMPS | TABLEMTN | ETL.5390.INSL.NCER | 2023-05-11 | 2023-05-11 |  | Late | 2024-05-10 |  | 2024-05-11 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46060979 | T2 EI PIT #1-COTTONWOOD 018/150 RPR JMPS | ICS
LC | 126062750 | 044/295C | T2 EI TRINITY-CTTNWD 044/295C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-05 | 2023-05-05 | 2023-06-14 | On-time | 2024-05-04 | 325 | 2024-05-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45906893 | T2 EI TRINITY-CTTNWD 044/295C RPR GYWW | ICW
LC | 126103166 | 021/078 | T2 DI EXCHQR-IDN FT-YSMT 21/78 RPR JUMS | FRESNO | ETL.8650.INSL.NCER | 2023-05-10 | 2023-05-05 | 2024-02-26 | On-time | 2024-05-04 | 68 | 2024-05-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46045664 | T2 DI EXCHQR-IDN FT-YSMT 21/78 RPR JUMS | ICS
LC | 126103446 | 001/007 | T2 DI EXCHQUR-INDN FLT 1/7 RPR STRT | FRESNO | ETL.8650.TOWR | 2023-05-10 | 2023-05-05 | 2023-12-05 | On-time | 2024-05-04 | 151 | 2024-05-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46051186 | T2 DI EXCHQUR-INDN FLT 1/7 RPR STRT | ICQ
LC | 126107509 | 011/257 | T2 EI SALINAS-LAURELES 011/257 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-11 | 2023-05-11 | 2024-06-14 | Late | 2024-05-10 | -35 | 2024-05-11 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507059 | T2 EI SALINAS-LAURELES 011/257 RPL POLE | 70Y
LC | 126103514 | 028/138 | T2 DI EXCHQR-IDIAN FLAT 28/138 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-05-10 | 2023-05-05 | 2023-12-12 | On-time | 2024-05-04 | 144 | 2024-05-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45977748 | T2 DI EXCHQR-IDIAN FLAT 28/138 UNBURY | ICQ
LC | 126111305 | 026/117 | T2 DI EXCHQUR-INDN FLT 26/117 RPR STRT | FRESNO | ETL.8650.POLE.NWOD | 2023-05-11 | 2023-05-05 | 2023-12-14 | On-time | 2024-05-04 | 142 | 2024-05-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45977744 | T2 DI EXCHQUR-INDN FLT 26/117 RPR STRT | ICQ
LC | 126107841 | 008/137 | T2 EI PT #1-HT CK #2-BRNY 8/137 RPL STRW | TABLEMTN | ETL.7040.POLE.WOOD | 2023-05-11 | 2023-05-11 | 2024-05-14 | Late | 2024-05-10 | -4 | 2024-05-11 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485424 | T2 EI PT #1-HT CRK #2-BRNY 3/40 RPL STRW | 70Y
LC | 126107850 | 011/137 | T2 EI DRUM-SUMMIT #1 011/137 RPR CNDW | SACTO | ETL.1440.INSL.CERA | 2023-05-11 | 2023-05-11 |  | Late | 2024-05-10 |  | 2024-05-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46054060 | T2 EI DRUM-SUMMIT #1 011/137 RPR CNDW | ICW
LC | 126111306 | 026/117 | T2 DI EXCHQUR-INDN FLT 26/117 RPR FOND | FRESNO | ETL.8650.POLE.NWOD | 2023-05-11 | 2023-05-05 | 2023-12-14 | On-time | 2024-05-04 | 142 | 2024-05-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45977745 | T2 DI EXCHQUR-INDN FLT 26/117 RPR FOND | ICQ
LC | 126111998 | 075/379 | T2 DI MLN-ROND MNTN #2 75/379 RPR SHIELD | TABLEMTN | ETL.6020.INSL.NCER | 2023-05-11 | 2023-05-05 | 2024-01-22 | On-time | 2024-05-04 | 103 | 2024-05-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46046051 | T2 DI MLN-ROND MNTN #2 75/379 RPR SHIELD | ICS
LC | 126112172 | 013/043 | T2 DI EXCQR-INDN FT-YSMTE 13/43 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-05-11 | 2023-05-05 | 2024-05-02 | On-time | 2024-05-04 | 2 | 2023-11-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46179072 | T2 DI EXCQR-INDN FT-YSMTE 13/43 RPR JMPS | ICS
LC | 126108855 | 011/228 | T2 EI CARIBOU-WESTWOOD 11/228 RPR HRDW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-11 | 2023-05-11 |  | Late | 2024-05-10 |  | 2024-05-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 46053964 | T2 EI CARIBOU-WESTWOOD 11/228 RPR HRDW | ICW
LC | 126108977 | 011/264 | T2 EI SALINAS-LAURELES 011/264 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-11 | 2023-05-11 |  | Late | 2024-05-10 |  | 2024-05-11 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35507125 | T2 EI SALINAS-LAURELES 011/264 RPL POLE | 70Y
LC | 126113790 | 032/180 | T2 DI EXCHQUR-INDN FLT 32/180 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-05-12 | 2023-05-05 | 2023-12-15 | On-time | 2024-05-04 | 141 | 2024-05-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45977759 | T2 DI EXCHQUR-INDN FLT 32/180 UNBURY | ICQ
LC | 126113798 | 032/180 | T2 DI EHQR-INDN FLT-YSMT 32/180 RPR STRT | FRESNO | ETL.8650.POLE.NWOD | 2023-05-12 | 2023-05-05 | 2023-12-15 | On-time | 2024-05-04 | 141 | 2024-05-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45977758 | T2 DI EHQR-INDN FLT-YSMT 32/180 RPR STRT | ICQ
LC | 126109708 | 007/057 | T2 EI BUTTE VLLY-CARIBOU 7/57L RPR GYWW | TABLEMTN | ETL.1180.POLE.STPS | 2023-05-11 | 2023-05-11 | 2024-06-03 | Late | 2024-05-10 | -24 | 2024-05-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062550 | T2 EI BUTTE VLLY-CARIBOU 7/57L RPR GYWW | ICW
LC | 126109913 | 011/265 | T2 EI SALINAS-LAURELES 011/265 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-11 | 2023-05-11 | 2024-06-12 | Late | 2024-05-10 | -33 | 2024-05-11 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507126 | T2 EI SALINAS-LAURELES 011/265 RPL POLE | 70Y
LC | 126110352 | 002/005 | T2 WV GARCIA TAP 2/005 INS DAMW | WILLITS | ETL.8411.INSL.NCER | 2023-05-11 | 2023-05-11 |  | Late | 2024-05-10 |  | 2024-05-11 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 46255911 | T2 WV GARCIA TAP 2/005 INS DAMW | ICW
LC | 126113900 | 034/194 | T2 DI EXCHQUR-INDN FLT 34/194 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-05-12 | 2023-05-05 | 2023-12-11 | On-time | 2024-05-04 | 145 | 2024-05-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45977786 | T2 DI EXCHQUR-INDN FLT 34/194 UNBURY | ICQ
LC | 126113902 | 034/194 | T2 DI EXCHQUR-INDN FLT 34/194 RPR STRT | FRESNO | ETL.8650.POLE.NWOD | 2023-05-12 | 2023-05-05 | 2023-12-11 | On-time | 2024-05-04 | 145 | 2024-05-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45977787 | T2 DI EXCHQUR-INDN FLT 34/194 RPR STRT | ICQ
LC | 126113908 | 063/317 | T2 DI MALIN-ROUND MT #2 63/317 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2023-05-12 | 2023-05-05 | 2023-11-07 | On-time | 2024-05-04 | 179 | 2024-05-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46044198 | T2 DI MALIN-ROUND MT #2 63/317 RPR GYWS | ICS
LC | 126111039 | 011/268 | T2 EI SALINAS-LAURELES 011/268 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-11 | 2023-05-11 |  | Late | 2024-05-10 |  | 2024-05-11 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507135 | T2 EI SALINAS-LAURELES 011/268 RPL POLE | 70Y
LC | 126114013 | 016/149 | T2 DI BRIGVILL-CTTWD 016/149L RPR ADSS | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-12 | 2023-05-05 | 2023-08-10 | On-time | 2024-05-04 | 268 | 2023-11-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45770969 | T2 DI BRIGVILL-CTTWD 016/149L RPR ADSS | ICW
LC | 126114117 | 030/163 | T2 DI EXCHEQUER-INDIAN FLT 30/163 COTTER | FRESNO | ETL.8650.INSL.NCER | 2023-05-12 | 2023-05-05 | 2023-12-14 | On-time | 2024-05-04 | 142 | 2024-05-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45954713 | T2 DI EXCHEQUER-INDIAN FLT 30/163 COTTER | ICS
LC | 126114255 | 022/084 | T2 DI EXCHQUR-INDN FLT 22/84 RPR JUMS | FRESNO | ETL.8650.INSL.NCER | 2023-05-12 | 2023-05-05 | 2023-12-12 | On-time | 2024-05-04 | 144 | 2023-08-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45954650 | T2 DI EXCHQUR-INDN FLT 22/84 RPR JUMS | ICS
LC | 126114891 | 021/079A | T2 DI EXCHQUR-INDIN FLT 21/79A RPR SHL | FRESNO | ETL.8650.POLE.NWOD | 2023-05-12 | 2023-05-05 | 2024-02-26 | On-time | 2024-05-04 | 68 | 2024-05-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46045667 | T2 DI EXCHQUR-INDIN FLT 21/79A RPR SHL | ICS
LC | 126121684 | 074/378 | T2 DI MLN-RND MONTN #2 74/378 RPR SHIELD | TABLEMTN | ETL.6020.TOWR | 2023-05-12 | 2023-05-05 | 2024-01-22 | On-time | 2024-05-04 | 103 | 2024-05-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46046050 | T2 DI MLN-RND MONTN #2 74/378 RPR SHIELD | ICS
LC | 126121685 | 074/378 | T2 DI MLN-ROND MOTIN #2 74/378 RPL HRDT | TABLEMTN | ETL.6020.TOWR | 2023-05-12 | 2023-05-05 | 2023-11-08 | On-time | 2024-05-04 | 178 | 2024-05-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46044199 | T2 DI MLN-ROND MOTIN #2 74/378 RPL HRDT | ICQ
LC | 126122402 | 028/142 | T2 DI EXCHQR-INDIAN FLAT 28/142 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-05-13 | 2023-05-05 | 2023-12-12 | On-time | 2024-05-04 | 144 | 2024-05-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45977750 | T2 DI EXCHQR-INDIAN FLAT 28/142 UNBURY | ICQ
LC | 126111307 | 026/117 | T2 DI EXCHQUR-INDN FLT 26/117 RMV VEG | FRESNO | ETL.8650.POLE.NWOD | 2023-05-11 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126122404 | 028/142 | T2 DI EXCHQR-IND FLAT 28/142 RPR STRT | FRESNO | ETL.8650.POLE.NWOD | 2023-05-13 | 2023-05-05 | 2023-12-12 | On-time | 2024-05-04 | 144 | 2024-05-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45977752 | T2 DI EXCHQR-IND FLAT 28/142 RPR STRT | ICQ
LC | 126064534 | 100/001 | T2 EI HUMBOLDT-TRINITY 100/001L RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-05-06 | 2023-05-06 | 2023-08-15 | On-time | 2024-05-05 | 264 | 2023-11-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45759944 | T2 EI HUMBOLDT-TRINITY 100/001L RPR GYWW | ICW
LC | 126111420 | 044/183 | T2 DI DIABLO MIDWAY#3 44/183 INS DMPS | PISMOBCH | ETL.5980.INSL.NCER | 2023-05-11 | 2023-05-11 | 2024-05-24 | Late | 2024-05-10 | -14 | 2024-05-11 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 46073333 | T2 DI DIABLO MIDWAY#3 44/183 INS DMPS | ICS
LC | 126111427 | 044/183 | T2 DI DIABLO MIDWAY#3 44/183 COTTER | PISMOBCH | ETL.5980.INSL.NCER | 2023-05-11 | 2023-05-11 | 2024-05-24 | Late | 2024-05-10 | -14 | 2024-05-11 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46073334 | T2 DI DIABLO MIDWAY#3 44/183 RPR INSS | ICS
LC | 126111541 | 019/069 | T2 DI EXCHEQUER-INDN FLT 19/69 RMV VEGN | FRESNO | ETL.8650.TOWR | 2023-05-11 | 2023-05-04 | 2024-06-27 | Late | 2024-05-03 | -55 | 2024-05-04 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation-Tower | Cage Clearing
LC | 126065116 | 100/001 | T2 EI HUMBOLDT-TRINITY 100/001R RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-05-06 | 2023-05-06 | 2023-08-15 | On-time | 2024-05-05 | 264 | 2023-11-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45759945 | T2 EI HUMBOLDT-TRINITY 100/001R RPR GYWW | ICW
LC | 126066399 | 023/182 | T2 EI MDDL FRK-GLD HLL 023/182R RPR GYWW | SACTO | ETL.5140.POLE.STPS | 2023-05-06 | 2023-05-06 | 2023-05-18 | On-time | 2024-05-05 | 353 | 2023-08-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45763541 | T2 EI MDDL FRK-GLD HLL 023/182R RPR GYWW | ICW
LC | 126111656 | 067/281 | T2 EI ROND MTN-TBL MTN #1 67/281 BNT STL | TABLEMTN | ETL.6060.TOWR | 2023-05-11 | 2023-05-11 |  | Late | 2024-05-10 |  | 2024-05-11 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072138 | T2 EI ROND MTN-TBL MTN #1 67/281 BNT STL | ICQ
LC | 126066749 | 098/003 | T2 EI COTTONWOOD-HUMBOLDT 98/3 RPR HRDW | EUREKA | ETL.1820.POLE.WDPS | 2023-05-06 | 2023-05-06 | 2024-04-08 | On-time | 2024-05-05 | 27 | 2024-05-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46171111 | T2 EI COTTONWOOD-HUMBOLDT 98/3 RPR HRDW | ICW
LC | 126069169 | 018/249 | T2 KESWICK-TRINITY 18/249 RPL DMPW | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-08 | 2023-05-08 | 2024-04-16 | On-time | 2024-05-07 | 21 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46053909 | T2 KESWICK-TRINITY 18/249 RPL DMPW | ICW
LC | 126072494 | 003/077 | T2 EI COLGATE-ALLEGHANY 003/077 RPR IBWW | SACTO | ETL.6470.INSL.NCER | 2023-05-08 | 2023-05-08 | 2024-01-31 | On-time | 2024-05-07 | 97 | 2024-05-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 46049064 | T2 EI COLGATE-ALLEGHANY 003/077 RPR IBWW | ICW
LC | 126111749 | 030/121 | T2 DI DIABLO-MIDWAY #3 30/121 RPR GYWT | PISMOBCH | ETL.5980.TOWR | 2023-05-11 | 2023-05-11 | 2024-05-11 | Late | 2024-05-10 | -1 | 2024-05-11 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46179819 | T2 DI DIABLO-MIDWAY #3 30/121 RPR GYWT | ICQ
LC | 126074979 | 007/083 | T2 EI GREEN VLLY-PAUL SWT 7/83L RPR GYWW | MOSSLNDG | ETL.1730.POLE.WDPS | 2023-05-08 | 2023-05-08 | 2023-12-12 | On-time | 2024-05-07 | 147 | 2024-05-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46081511 | T2 EI GREEN VLLY-PAUL SWT 7/83L RPR GYWW | ICW
LC | 126075056 | 013/003 | T2 DI MELONES-CURTIS 13/03 RPR CRSW | VICTOR | ETL.2390.POLE.WDPS | 2023-05-08 | 2023-05-08 | 2024-02-21 | On-time | 2024-05-07 | 76 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46161859 | T2 DI MELONES-CURTIS 13/03 RPR CRSW | ICW
LC | 126075402 | 013/003 | T2 DI MELONES-CURTIS 13/03 RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2023-05-08 | 2023-05-08 | 2024-02-21 | On-time | 2024-05-07 | 76 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46162140 | T2 DI MELONES-CURTIS 13/03 RPR STRW | ICW
LC | 126076216 | 034/140 | T2 EI DIABLO-MIDWAY #3 34/140 RPR ROAD | PISMOBCH | ETL.5980.TOWR | 2023-05-08 | 2023-05-08 | 2023-12-01 | On-time | 2024-05-07 | 158 | 2024-05-08 | 932 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Repair | 45824504 | T3 EI DIABLO-MIDWAY #3 23/093 RPR ROAD | CHS
LC | 126076262 | 003/080 | T2 EI COLGATE-ALLEGHANY 003/080 RPR IBWW | SACTO | ETL.6470.INSL.NCER | 2023-05-08 | 2023-05-08 | 2024-01-31 | On-time | 2024-05-07 | 97 | 2024-05-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 46049067 | T2 EI COLGATE-ALLEGHANY 003/080 RPR IBWW | ICW
LC | 126076635 | 003/016 | T2 EI MORRO BAY MESA 3/16 RPR FOND | PISMOBCH | ETL.5290.TOWR | 2023-05-08 | 2023-05-08 | 2024-02-22 | On-time | 2024-05-07 | 75 | 2024-05-08 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46051303 | T2 EI MORRO BAY MESA 3/16 RPR FOND | ICQ
LC | 126116975 | 003/006 | T2 DI TRINITY-MAPLE CREEK 3/6 RPL HRDD | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-08 | 2024-02-20 | On-time | 2024-05-07 | 77 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46077571 | T2 DI TRINITY-MAPLE CREEK 3/6 RPL HRDD | ICW
LC | 126117023 | 003/006 | T2 DI TRINITY-MAPLE CREEK 3/6 RPR INSW | EUREKA | ETL.8170.INSL.NCER | 2023-05-12 | 2023-05-08 | 2024-02-20 | On-time | 2024-05-07 | 77 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46070765 | T2 DI TRINITY-MAPLE CREEK 3/6 RPR INSW | ICW
LC | 126111966 | 016/065 | T2 DI DIABLO-GATES #1 16/65 RPR STRT | PISMOBCH | ETL.5960.TOWR | 2023-05-11 | 2023-05-10 |  | Late | 2024-05-09 |  | 2024-05-10 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46051306 | T2 DI DIABLO-GATES#1 16/65 RPR STRT | ICQ
LC | 126120998 | :001/012 | T2 DI ROCK CREEK-POE :01/12 RPL HRDT | TABLEMTN | ETL.5630.TOWR | 2023-05-12 | 2023-05-08 | 2024-04-19 | On-time | 2024-05-07 | 18 | 2024-05-08 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46072132 | T2 DI ROCK CREEK-POE :01/12 RPL HRDT | ICQ
LC | 126112041 | 044/004 | T2 DI FT ROSS-GUALALA 44/4 GO95 CLEAR | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-11 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 401 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35487981 | T2 DI FT ROSS-GUAL 44/4 GO95 | 93G
LC | 126112042 | 044/004 | T2 DI FT ROSS-GUAL 44/4 RPR CRSW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-11 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46050718 | T2 DI FT ROSS-GUAL 44/4 RPR CRSW | ICW
LC | 126112044 | 044/004 | T2 DI FT ROSS-GUAL 44/4 RPR STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-11 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46050719 | T2 DI FT ROSS-GUAL 44/4 RPR STRW | ICW
LC | 126121792 | :001/009 | T2 DI ROCK CRK-POE :01/09 RPR SHLS | TABLEMTN | ETL.5630.TOWR | 2023-05-12 | 2023-05-08 | 2024-02-28 | On-time | 2024-05-07 | 69 | 2024-05-08 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46060977 | T2 DI ROCK CRK-POE :01/09 RPR SHLS | ICS
LC | 126121796 | 016/000 | T2 DI MNDCN-PHL JC-HPLND 16/0 COMPLETE | WILLITS | ETL.7520.POLE.WOOD | 2023-05-12 | 2023-05-08 | 2024-03-21 | On-time | 2024-05-07 | 47 | 2024-05-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506670 | T2 DI MNDCN-PHL JC-HPLND 16/0 RPL POLE | 70Y
LC | 126112157 | X009/039 | T2 DI DIABLO-MESA X09/39 RPL INSS | PISMOBCH | ETL.4620.INSL | 2023-05-11 | 2023-05-11 | 2024-05-16 | Late | 2024-05-10 | -6 | 2024-05-11 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513943 | T2 DI DIABLO-MESA X09/39 RPL INSS | 93K
LC | 126121889 | 048/027 | T2 DI TRNTY-MPL CRK 48/27 RPR ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-08 | 2023-06-15 | On-time | 2024-05-07 | 327 | 2023-11-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45767976 | T2 DI TRNTY-MPL CRK 48/27 RPR ANCW | ICW
LC | 126112168 | 031/125 | T2 DI DIABLO-MIDWAY #2 31/125 RPR GYWT | PISMOBCH | ETL.5970.TOWR | 2023-05-11 | 2023-05-11 | 2024-05-11 | Late | 2024-05-10 | -1 | 2024-05-11 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46179474 | T2 DI DIABLO-MIDWAY #2 31/125 RPR GYWT | ICQ
LC | 126121909 | 041/009 | T2 DI FT RSS-GUALALA 41/9 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-05-12 | 2023-05-08 | 2023-11-01 | On-time | 2024-05-07 | 188 | 2023-08-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45765774 | T2 DI FT RSS-GUALALA 41/9 RPR INSW | ICW
LC | 126112178 | 041/002 | T2 DI FT ROSS-GUAL 41/2 RPR GYWW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-11 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46227562 | T2 DI FT ROSS-GUAL 41/2 RPR GYWW | ICW
LC | 126112189 | 066/005 | T2 DI ELK-GUALALA 66/5 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-05-11 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487250 | T2 DI ELK-GUALALA 66/5 RPL POLE | 70Y
LC | 126121933 | 048/008 | T2 DI TRNTY-MPL CRK 048/008 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-05-12 | 2023-05-08 | 2024-04-08 | On-time | 2024-05-07 | 29 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172259 | T2 DI TRNTY-MPL CRK 048/008 RPR GYWW | ICW
LC | 126122476 | 041/010 | T2 DI ELK-GUALALA 041/010L RPR GYWW | WILLITS | ETL.8410.POLE.WDPS | 2023-05-13 | 2023-05-08 | 2023-08-31 | On-time | 2024-05-07 | 250 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46004109 | T2 DI ELK-GUALALA 041/010L RPR GYWW | ICW
LC | 126112235 | 034/190 | T2 DI EXCHQUR-INDN FLT 34/190 RPR STRT | FRESNO | ETL.8650.TOWR | 2023-05-11 | 2023-05-04 |  | Late | 2024-05-03 |  | 2024-05-04 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45977784 | T2 DI EXCHQUR-INDN FLT 34/190 RPR STRT | ICQ
LC | 126122477 | 041/010 | T2 DI ELK-GUALALA 041/010R RPR GYWW | WILLITS | ETL.8410.POLE.WDPS | 2023-05-13 | 2023-05-08 | 2023-08-31 | On-time | 2024-05-07 | 250 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45977837 | T2 DI ELK-GUALALA 041/010R RPR GYWW | ICW
LC | 126112366 | 040/164 | T2 DI DIABLO-MIDWAY #3 40/164 BNT STEEL | PISMOBCH | ETL.5980.TOWR | 2023-05-11 | 2023-05-11 |  | Late | 2024-05-10 |  | 2024-05-11 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46051309 | T2 DI DIABLO-MIDWAY #3 040/164 BNT STEEL | ICQ
LC | 126123118 | 003/007 | T2 DI TRINITY-MAPLE CRK 3/7 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-14 | 2023-05-08 | 2024-02-20 | On-time | 2024-05-07 | 77 | 2024-05-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35496185 | T2 DI TRINITY-MAPLE CRK 3/7 RPL STRW | 70Y
LC | 126123156 | 050/008 | T2 DI TRINITY-MPL CR 50/8 RPR INSW | EUREKA | ETL.8170.INSL.CERA | 2023-05-14 | 2023-05-08 | 2024-03-29 | On-time | 2024-05-07 | 39 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46172293 | T2 DI TRINITY-MPL CR 50/8 RPR INSW | ICW
LC | 126125350 | 005/002 | T2 DI TRINITY-MAPLE CREEK 05/02 RPR ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-14 | 2023-05-08 | 2023-11-07 | On-time | 2024-05-07 | 182 | 2023-11-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45772985 | T2 DI TRINITY-MAPLE CREEK 05/02 RPR ANCW | ICW
LC | 126113779 | 004/002 | T2 DI MLNS-CRTS 004/002 GO95 CLEAR | VICTOR | ETL.2390.POLE.WDPS | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 401 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35522263 | T2 DI MLNS-CRTS 004/002 MITIGATION | 93G
LC | 126125678 | 005/005C | T2 DI TRINITY MAPLE CREEK 05/005C COTTER | EUREKA | ETL.8170.POLE.NWOD | 2023-05-14 | 2023-05-08 | 2023-06-03 | On-time | 2024-05-07 | 339 | 2023-11-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45772986 | T2 DI TRINITY MAPLE CREEK 05/005C COTTER | ICW
LC | 126126417 | 003/020 | T2 DI TRINITY-MAPLE CREEK 3/20C RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-05-14 | 2023-05-08 | 2024-01-11 | On-time | 2024-05-07 | 117 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46070766 | T2 DI TRINITY-MAPLE CREEK 3/20C RPR GYWW | ICW
LC | 126126436 | 039/011 | T2 DI FT ROSS-GUALALA 39/11 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-05-14 | 2023-05-08 | 2023-06-22 | On-time | 2024-05-07 | 320 | 2023-08-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45765773 | T2 DI FT ROSS-GUALALA 39/11 RPR INSW | ICW
LC | 126126484 | 013/001 | T2 DI MLNS-CURTIS 13/1 RPR POLE | VICTOR | ETL.2390.POLE.WDPS | 2023-05-14 | 2023-05-08 | 2023-10-15 | On-time | 2024-05-07 | 205 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45976990 | T2 DI MLNS-CURTIS 13/1 RPR POLE | ICW
LC | 126126499 | 003/006 | T2 DI MNDCN-HRTLY 3/6 RPR JUMW | WILLITS | ETL.7510.INSL.CERA | 2023-05-14 | 2023-05-08 | 2024-02-14 | On-time | 2024-05-07 | 83 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46089486 | T2 DI MNDCN-HRTLY 3/6 RPR JUMW | ICW
LC | 126126523 | 003/006 | T2 DI MNDCN-HRTLY 3/6 RPR CRSW | WILLITS | ETL.7510.POLE.WOOD | 2023-05-14 | 2023-05-08 | 2024-02-14 | On-time | 2024-05-07 | 83 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46089487 | T2 DI MNDCN-HRTLY 3/6 RPR CRSW | ICW
LC | 126113960 | 063/317 | T2 DI MALIN-ROUND MTN #2 63/317 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-05-12 | 2023-05-05 | 2024-05-09 | Late | 2024-05-04 | -5 | 2024-05-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45771531 | T2 DI MALIN-ROUND MTN #2 63/317 RPR OPGW | ICS
LC | 126113983 | 007/006A | T2 DI MLNS-CRTS 007/006A RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46162141 | T2 DI MLNS-CRTS 007/006A RPR STRW | ICW
LC | 126113985 | 007/006A | T2 DI MLNS-CRTS 007/006A L RPR STRW | VICTOR | ETL.2390.POLE.WDPS | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46162142 | T2 DI MLNS-CRTS 007/006A L RPR STRW | ICW
LC | 126126526 | 003/006 | T2 DI MNDCN-HRTLY 3/6 RPL ANCW | WILLITS | ETL.7510.POLE.WOOD | 2023-05-14 | 2023-05-08 | 2024-04-05 | On-time | 2024-05-07 | 32 | 2024-05-08 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35488485 | T2 DI MENDOCINO-HRTLY 1/3 RPL CRSW | 93E
LC | 126126617 | 012/005 | T2 DI EXCHEQUER-MARIPOSA 12/05 COMPLETE | FRESNO | ETL.8640.POLE.NWOD | 2023-05-14 | 2023-05-08 | 2023-06-06 | On-time | 2024-05-07 | 336 | 2023-08-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45765937 | T2 DI EXCHEQUER-MARIPOSA 12/05 RPR GYWW | ICW
LC | 126126640 | 002/010 | T2 DI TRINITY-MAPLE CREEK 2/10 RPR SPLW | EUREKA | ETL.8170.INSL.NCER | 2023-05-14 | 2023-05-08 | 2024-02-19 | On-time | 2024-05-07 | 78 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46070763 | T2 DI TRINITY-MAPLE CREEK 2/10 RPR SPLW | ICW
LC | 126126727 | 001/000 | T2 DI TRINITY-MAPLE CRK 1/0 RPR JUMW | EUREKA | ETL.8170.INSL.NCER | 2023-05-14 | 2023-05-08 | 2023-08-02 | On-time | 2024-05-07 | 279 | 2023-08-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45772982 | T2 DI TRINITY-MAPLE CRK 1/0 RPR JUMW | ICW
LC | 126114287 | 012/270 | T2NT EI SALINAS-LAURELES 012/270 RMV VEG | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126114335 | 000/018 | T2 DI TRINITY-MAPLE CREEK 0/18 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 | 2024-05-11 | Late | 2024-05-08 | -3 | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35485472 | T2 DI TRINITY-MAPLE CREEK 0/18 RPL POLE | 70Y
LC | 126114407 | 001/016 | T2 DI TRNTY-MPL CRK 001/016 RPR CRSW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46070698 | T2 DI TRNTY-MPL CRK 001/016 RPR CRSW | ICW
LC | 126126769 | 003/052 | T2 DI MANVILLE TAP 3/52 RPL SPLW | PISMOBCH | ETL.1372.INSL.NCER | 2023-05-14 | 2023-05-08 | 2024-01-16 | On-time | 2024-05-07 | 112 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Replace | 46090146 | T2 DI MANVILLE TAP 3/52 RPL SPLW | ICW
LC | 126126799 | :000/004 | T2 DI ROCK-CREEK-POE :0/4 RPL INSS | TABLEMTN | ETL.5630.INSL | 2023-05-14 | 2023-05-08 | 2024-02-28 | On-time | 2024-05-07 | 69 | 2024-05-08 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509199 | T2 DI ROCK CREEK-POE :5/33 RPLC INSS | 93K
LC | 126126841 | 001/006 | T2 DI TRINITY-MAPLE CREEK 1/6 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-14 | 2023-05-08 | 2023-08-02 | On-time | 2024-05-07 | 279 | 2023-08-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45860425 | T2 DI TRINITY-MAPLE CREEK 1/6 RPR GYWW | ICW
LC | 126130430 | 001/013 | T2 DI TRNTY-MPLE CREEK 1/13 RPR STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-15 | 2023-05-08 | 2024-01-17 | On-time | 2024-05-07 | 111 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46070697 | T2 DI TRNTY-MPLE CREEK 1/13 RPR STRW | ICW
LC | 126115076 | 005/000 | T2 DI TRNTY-MPL CRK 5/0L RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46070771 | T2 DI TRNTY-MPL CRK 005/000 RPR GYWW | ICW
LC | 126132050 | 002/013 | T2 DI TRNTY-MPLE CREEK 2/13 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-05-15 | 2023-05-08 | 2024-01-11 | On-time | 2024-05-07 | 117 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46070764 | T2 DI TRNTY-MPLE CREEK 2/13 RPR GYWW | ICW
LC | 126077758 | 003/017 | T2 EI MORRO BAY MESA 3/17 RPR FOND | PISMOBCH | ETL.5290.TOWR | 2023-05-09 | 2023-05-09 | 2024-02-22 | On-time | 2024-05-08 | 76 | 2024-05-09 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46051304 | T2 EI MORRO BAY MESA 3/17 RPR FOND | ICQ
LC | 126115152 | 022/008 | T2 DI TRINITY-MAPLE CREEK 22/8 RPR CRSW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 | 2024-06-13 | Late | 2024-05-08 | -36 | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46079369 | T2 DI TRINITY-MAPLE CREEK 22/08 RPR CRSW | ICW
LC | 126115155 | 022/008 | T2 DI TRINITY-MAPLE CREEK 22/08 RPL TIED | EUREKA | ETL.8170.INSL.CERA | 2023-05-12 | 2023-05-09 | 2024-06-13 | Late | 2024-05-08 | -36 | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46079369 | T2 DI TRINITY-MAPLE CREEK 22/08 RPR CRSW | ICW
LC | 126115285 | 043/005 | T2 DI TRINITY-MPL CRK 43/5 REFRAME | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35506292 | T2 DI TRINITY-MPL CRK 43/5 REFRAME | 93E
LC | 126078572 | 006/072 | T2 EI GREEN VALLEY-PAUL 06/072R RPR POLE | MOSSLNDG | ETL.1730.POLE.WDPS | 2023-05-09 | 2023-05-09 | 2023-12-12 | On-time | 2024-05-08 | 148 | 2024-05-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081513 | T2 EI GREEN VALLEY-PAUL 06/072R RPR POLE | ICW
LC | 126115466 | 043/007 | T2 DI TRINITY-MPL CRK 43/7 REFRAME | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35506293 | T2 DI TRINITY-MPL CRK 43/7 REFRAME | 93E
LC | 126115469 | 042/007 | T2 DI TRINITY-MPLE CRK 42/7 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506766 | T2 DI TRINITY-MPLE CRK 42/7 RPL STRW | 70Y
LC | 126115589 | 007/014 | T2 DI TRINITY-MAPLE CREEK 7/14 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485476 | T2 DI TRINITY-MAPLE CREEK 7/14 RPL POLE | 70Y
LC | 126115608 | :001/001 | T2 EI CARIBOU #2 :001/001 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526758 | T2 EI CARIBOU #2 :001/001 RPL STRW | 70Y
LC | 126115736 | 046/000 | T2 DI TRINITY-MPL CRK 46/0 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 | 2024-06-06 | Late | 2024-05-08 | -29 | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172198 | T2 DI TRINITY-MPL CRK 46/0 RPR GYWW | ICW
LC | 126115738 | 050/004 | T2 DI TRINITY-MPLE CRK 50/4 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506458 | T2 DI TRINITY-MPLE CRK 50/4 RPL STRW | 70Y
LC | 126079084 | 006/072 | T2 EI GREEN VALLEY-PAUL 06/072L RMV VEG | MOSSLNDG | ETL.1730.POLE.WDPS | 2023-05-09 | 2023-05-09 | 2023-12-12 | On-time | 2024-05-08 | 148 | 2024-05-09 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126116039 | 007/087C | T2 EI DRUM-SUMMIT #2 7/87C COMPLETE | SACTO | ETL.1450.POLE.NWOD | 2023-05-12 | 2023-05-12 | 2024-05-16 | Late | 2024-05-11 | -5 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053873 | T2 EI DRUM-SUMMIT #2 7/87C RPR GYWW | ICW
LC | 126116075 | 007/087A | T2 EI DRUM-SUMMIT #2 7/87A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-05-12 | 2023-05-12 | 2024-05-16 | Late | 2024-05-11 | -5 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053874 | T2 EI DRUM-SUMMIT #2 7/87A RPR GYWW | ICW
LC | 126079085 | 006/072 | T2 EI GREEN VALLEY-PAUL 06/072L RPR POLE | MOSSLNDG | ETL.1730.POLE.WDPS | 2023-05-09 | 2023-05-09 | 2023-12-12 | On-time | 2024-05-08 | 148 | 2024-05-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081515 | T2 EI GREEN VALLEY-PAUL 06/072L RPR POLE | ICW
LC | 126116369 | 012/271 | T2NT EI SALINAS-LAURELES 012/271 RMV VEG | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126116417 | 019/450 | T2 DRUM-GRASS VALLEY 019/450 RPR HRDW | SACTO | ETL.6760.POLE.WOOD | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Missing | Hardware-Wood | Install | 46053875 | T2 DRUM-GRASS VALLEY 019/450 RPR HRDW | ICW
LC | 126116511 | :001/002 | T2 EI CARIBOU #2 :001/002 COTTER | TABLEMTN | ETL.6280.INSL.CERA | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46053975 | T2 EI CARIBOU #2 :001/002 COTTER | ICW
LC | 126080087 | 013/103 | T2 EI TIGER CREEK-ELECTRA 13/103 UNBURY | VICTOR | ETL.5780.TOWR | 2023-05-09 | 2023-05-09 | 2024-03-20 | On-time | 2024-05-08 | 49 | 2024-05-09 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46073331 | T2 EI TIGER CREEK-ELECTRA 13/103 UNBURY | ICQ
LC | 126116896 | 025/005 | T2 DI TRINITY-MAPLE CRK 25/5 RPR CRSW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46170563 | T2 DI TRINITY-MAPLE CRK 25/5 RPR CRSW | ICW
LC | 126080182 | 014/176 | T2 DELTA-MTN GATE JCT 14/176 RPL STRW | TABLEMTN | ETL.6750.POLE.WOOD | 2023-05-09 | 2023-05-09 | 2023-06-11 | On-time | 2024-05-08 | 332 | 2024-05-09 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31618696 | T2 DI DLTA-MTN GTE JCT 12/162 RPL STRW | 70Y
LC | 126080185 | 014/176 | T2 DELTA-MTN GATE JCT 14/176 RPL STRW | TABLEMTN | ETL.6750.POLE.WOOD | 2023-05-09 | 2023-05-09 | 2023-06-11 | On-time | 2024-05-08 | 332 | 2024-05-09 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31618696 | T2 DI DLTA-MTN GTE JCT 12/162 RPL STRW | 70Y
LC | 126080452 | 004/019 | T2 EI MORRO BAY MESA 4/19 RPR FOND | PISMOBCH | ETL.5290.TOWR | 2023-05-09 | 2023-05-09 | 2024-02-22 | On-time | 2024-05-08 | 76 | 2024-05-09 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46051305 | T2 EI MORRO BAY MESA 4/19 RPR FOND | ICQ
LC | 126117228 | 070/510 | T2 EI BRDGVLL-CTTNWD 70/510R RPR STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46171721 | T2 EI BRDGVLL-CTTNWD 070/510R RPR POLE | ICW
LC | 126117281 | 070/510 | T2 EI BRDGVLL-CTTNWD 70/510L RPR STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46171721 | T2 EI BRDGVLL-CTTNWD 070/510R RPR POLE | ICW
LC | 126082294 | 019/501 | T2 EI CARIBOU #2 019/501 RPR ANCW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-09 | 2023-05-09 | 2023-06-07 | On-time | 2024-05-08 | 336 | 2023-11-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45770971 | T2 EI CARIBOU #2 019/501 RPR ANCW | ICW
LC | 126117584 | 005/024B | T2 DI PITTSBURG-SAN RAMON 5/24B COTTER | CONCORD | ETL.5490.INSL | 2023-05-12 | 2023-04-17 | 2024-05-05 | Late | 2024-04-16 | -19 | 2023-10-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45999071 | T2 DI PITTSBURG-SAN RAMON 05/024B COTTER | ICS
LC | 126083104 | 019/502 | T2 EI CARIBOU #2 019/502 RPR ANCW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-09 | 2023-05-09 | 2023-06-07 | On-time | 2024-05-08 | 336 | 2023-11-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45770972 | T2 EI CARIBOU #2 019/502 RPR ANCW | ICW
LC | 126083946 | 003/018 | T2 EI SAN LUS OBSPO-CYUCS 3/18 RPR GYWW | PISMOBCH | ETL.9090.POLE.NWOD | 2023-05-09 | 2023-05-09 | 2024-04-09 | On-time | 2024-05-08 | 29 | 2024-05-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46090141 | T2 EI SAN LUS OBSPO-CYUCS 3/18 RPR GYWW | ICW
LC | 126084119 | 005/063 | T2 EI BURNS-LONE STAR #1 5/63 RPR GYWW | MOSSLNDG | ETL.6230.POLE.NWOD | 2023-05-09 | 2023-05-09 | 2024-04-11 | On-time | 2024-05-08 | 27 | 2024-05-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46081517 | T2 EI BURNS-LONE STAR #1 5/63 RPR GYWW | ICW
LC | 126084141 | 004/051 | T2 EI BURNS-LNE STAR #1 4/51 RPR COND | MOSSLNDG | ETL.6230.INSL.NCER | 2023-05-09 | 2023-05-09 | 2024-04-11 | On-time | 2024-05-08 | 27 | 2024-05-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45854253 | T2 EI BURNS-LNE STAR #1 4/51 RPR COND | ICW
LC | 126084841 | 031/005 | T2 DI TRINITY-MAPLE CREEK 31/05 COMPLETE | EUREKA | ETL.8170.INSL | 2023-05-09 | 2023-05-09 | 2023-06-07 | On-time | 2024-05-08 | 336 | 2023-08-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45763982 | T2 DI TRINITY-MAPLE CREEK 31/05 RPR INSW | ICW
LC | 126115096 | 013/274 | T2 DI VOLTA-DESCHUTES 13/274 RPL STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-12 | 2023-05-09 | 2024-04-24 | On-time | 2024-05-08 | 14 | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485603 | T2 DI VOLTA-DESCHUTES 13/274 RPL STRW | 70Y
LC | 126117766 | 071/512 | T2 EI BRDGVLL-CTTNWD 071/512R UNBURY | EUREKA | ETL.1110.POLE.STPS | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Tower | Repair | 46253988 | T2 EI BRDGVLL-CTTNWD 071/512R UNBURY | ICQ
LC | 126115150 | 013/281 | T2 DI VOLTA-DESCHUTES 13/281 RPL STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-12 | 2023-05-09 | 2024-04-23 | On-time | 2024-05-08 | 15 | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485603 | T2 DI VOLTA-DESCHUTES 13/274 RPL STRW | 70Y
LC | 126117893 | 071/512 | T2 EI BRDGVLL-CTTNWD 071/512L RPR GYWT | EUREKA | ETL.1110.POLE.STPS | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46253987 | T2 EI BRDGVLL-CTTNWD 071/512L RPR GYWT | ICQ
LC | 126116892 | 010/227 | T2 DI VOLTA-DESCHUTES 10/227 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-12 | 2023-05-09 | 2024-02-22 | On-time | 2024-05-08 | 76 | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485602 | T2 DI VOLTA-DESCH 9/197 RPL POLE | 70Y
LC | 126117351 | 013/280 | T2 DI VOLTA-DESCHUTES 13/280 RPL STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-12 | 2023-05-09 | 2024-04-23 | On-time | 2024-05-08 | 15 | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485603 | T2 DI VOLTA-DESCHUTES 13/274 RPL STRW | 70Y
LC | 126118027 | 024/001 | T2 DI TRINITY-MAPLE CREEK 24/01 RPL PL | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503539 | T2 DI TRINITY-MAPLE CREEK 24/01 RPL POLW | 70Y
LC | 126117601 | 043/013 | T2 DI TRINITY-MPL CR 43/13 REFRAME | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 | 2023-11-01 | On-time | 2024-05-08 | 189 | 2023-11-09 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31655106 | T2 DI TRINITY-MPL CR 43/13 REFRAME | 93E
LC | 126118179 | 053/001 | T2 DI TRINITY-MPL CR 53/1 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506530 | T2 DI TRINITY-MPL CR 53/1 RPL STRW | 70Y
LC | 126117609 | 013/292 | T2 DI VOLTA-DESCHUTES 13/292 RPR INSW | TABLEMTN | ETL.8290.INSL.NCER | 2023-05-12 | 2023-05-09 | 2024-01-16 | On-time | 2024-05-08 | 113 | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46053918 | T2 DI VOLTA-DESCHUTES 13/292 RPR INSW | ICW
LC | 126118240 | 050/007 | T2 DI TRINITY-MPL CRK 50/7 RPL INSW | EUREKA | ETL.8170.INSL | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35536595 | T2 DI TRINITY-MPL CRK 50/7 RPL INSW | 93I
LC | 126118241 | 050/007 | T2 DI TRINITY-MAPLE CREEK 50/7 RPL DAMW | EUREKA | ETL.8170.INSL | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2023-11-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46096682 | T2 DI TRINITY-MAPLE CREEK 50/7 RPL DAMW | ICW
LC | 126118246 | 050/007 | T2 DI TRINITY-MAPLE CREEK 50/7 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2023-11-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096682 | T2 DI TRINITY-MAPLE CREEK 50/7 RPL DAMW | ICW
LC | 126118320 | 043/009 | T2 DI TRINITY-MPL CR 43/9 REFRAME | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35506296 | T2 DI TRINITY-MPL CR 43/9 REFRAME | 93E
LC | 126118321 | 000/012 | T2 DI TRINITY-MPL CRK 0/12 RPL PL | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485471 | T2 DI TRINITY-MPL CRK 0/12 RPL PL | 70Y
LC | 126117720 | 022/004 | T2 DI TRINITY-MPL CRK 22/4 REFRAME | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 | 2023-06-08 | On-time | 2024-05-08 | 335 | 2023-08-09 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31651611 | T2 DI TRINITY-MPL CRK 22/4 REFRAME | 93E
LC | 126118559 | 042/010 | T2 DI TRINITY MPL CRK 42/10 RPL PL | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506772 | T2 DI TRINITY MPL CRK 42/10 RPL PL | 70Y
LC | 126117889 | 009/199 | T2 DI VOLTA-DESCHUTES 9/199 RPR POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-12 | 2023-05-09 | 2024-01-23 | On-time | 2024-05-08 | 106 | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46063190 | T2 DI VOLTA-DESCHUTES 9/199 RPR POLE | ICW
LC | 126118792 | 070/506 | T2 EI BRDGVLL-CTTNWD 070/506R RPR GYWW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171679 | T2 EI BRDGVLL-CTTNWD 070/506R RPR GYWW | ICW
LC | 126118793 | 070/506 | T2 EI BRDGVLL-CTTNWD 070/506R RPR POLE | EUREKA | ETL.1110.POLE.WDPS | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46171720 | T2 EI BRDGVLL-CTTNWD 070/506R RPR POLE | ICW
LC | 126118873 | 070/506 | T2 EI BRDGVLL-CTTNWD 070/506L RPR POLE | EUREKA | ETL.1110.POLE.WDPS | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46171720 | T2 EI BRDGVLL-CTTNWD 070/506R RPR POLE | ICW
LC | 126118741 | 007/166 | T2 DI VOLTA-DESCHUTES-7/166 RPL TIED | TABLEMTN | ETL.8290.INSL.CERA | 2023-05-12 | 2023-05-09 | 2024-01-23 | On-time | 2024-05-08 | 106 | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46063191 | T2 DI VOLTA-DESCHUTES-7/166 RPL TIED | ICW
LC | 126118916 | 007/144 | T2 DI KSWCK CSCDE 7/144 RPR SPLW | TABLEMTN | ETL.7260.INSL.CERA | 2023-05-12 | 2023-04-10 | 2024-06-17 | Late | 2024-04-09 | -69 | 2024-04-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46011765 | T2 DI KSWCK CSCDE 07/144 RPR SPLW | ICW
LC | 126118954 | 048/012 | T2 DI TRNTY-MPL CRK 048/012 RPR JMPW | EUREKA | ETL.8170.INSL.NCER | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2023-11-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46172281 | T2 DI TRNTY-MPL CRK 048/012 RPR JMPW | ICW
LC | 126119010 | 016/340 | T2 DI VOLTA-DESCHUTES 16/340 RPR STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-12 | 2023-05-09 | 2024-02-14 | On-time | 2024-05-08 | 84 | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46053920 | T2 DI VOLTA-DESCHUTES 16/340 RPR STRW | ICW
LC | 126118960 | :001/005 | T2 EI CARIBOU #2 :001/005 RPR STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46053976 | T2 EI CARIBOU #2 :001/005 RPR STRW | ICW
LC | 126118964 | 012/278 | T2 EI SALINAS-LAURELES 012/278 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507136 | T2 EI SALINAS-LAURELES 012/278 RPL POLE | 70Y
LC | 126119791 | 019/003 | T2 DI TRINITY-MAPLE CREEK 19/03 COMPLETE | EUREKA | ETL.8170.INSL | 2023-05-12 | 2023-05-09 | 2023-06-01 | On-time | 2024-05-08 | 342 | 2023-08-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45765776 | T2 DI TRINITY-MAPLE CREEK 19/03 RPL TIED | ICW
LC | 126119018 | 037/001 | T2 DI TRINITY MPLE CRK 37/1 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506411 | T2 DI TRINITY MPLE CRK 37/1 RPL STRW | 70Y
LC | 126120264 | 018/014 | T2 DI TRINITY-MAPLE CREEK 18/14 COMPLETE | EUREKA | ETL.8170.INSL | 2023-05-12 | 2023-05-09 | 2023-06-01 | On-time | 2024-05-08 | 342 | 2023-08-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45765775 | T2 DI TRINITY-MAPLE CREEK 18/14 RPL TIED | ICW
LC | 126120842 | 019/435 | T2 DI VOLTA-DESCHTES 019/435 RPL INSW | TABLEMTN | ETL.8290.INSL | 2023-05-12 | 2023-05-09 | 2024-04-18 | On-time | 2024-05-08 | 20 | 2024-05-09 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35485516 | T2 DI VOLTA-DESCHTES 019/435 RPL INSW | 93I
LC | 126126220 | 012/271 | T2 DI VOLTA-DESCHUTES 12/271 RPR STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-14 | 2023-05-09 | 2024-01-23 | On-time | 2024-05-08 | 106 | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46053916 | T2 DI VOLTA-DESCHUTES 12/271 RPR STRW | ICW
LC | 126126224 | 012/271 | T2 DI VOLTA-DESCHUTES 12/271 RPR INSW | TABLEMTN | ETL.8290.INSL | 2023-05-14 | 2023-05-09 | 2024-01-23 | On-time | 2024-05-08 | 106 | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46053917 | T2 DI VOLTA-DESCHUTES 12/271 RPR INSW | ICW
LC | 126119370 | 035/236 | T2 EI TRNTY-CTTNWD 035/236L RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-12 | 2023-05-12 | 2024-05-31 | Late | 2024-05-11 | -20 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062551 | T2 EI TRNTY-CTTNWD 035/236L RPR GYWW | ICW
LC | 126119372 | 035/236 | T2 EI TRNTY-CTTNWD 035/236L UNBURY | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-12 | 2023-05-12 | 2024-05-31 | Late | 2024-05-11 | -20 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46062552 | T2 EI TRNTY-CTTNWD 035/236L UNBURY | ICW
LC | 126126402 | 014/301 | T2 DI VOLTA-DESCH 14/301 RPR INSW | TABLEMTN | ETL.8290.INSL.CERA | 2023-05-14 | 2023-05-09 | 2024-01-23 | On-time | 2024-05-08 | 106 | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46053919 | T2 DI VOLTA-DESCH 14/301 RPR INSW | ICW
LC | 126119419 | 019/002 | T2 DI TRINITY-MAPLE CRK 19/2 REFRAME | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35502986 | T2 DI TRINITY-MAPLE CRK 19/2 REFRAME | 93E
LC | 126119686 | 035/236 | T2 EI TRNTY-CTTNWD 035/236C RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-12 | 2023-05-12 | 2024-05-31 | Late | 2024-05-11 | -20 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062555 | T2 EI TRNTY-CTTNWD 035/236C RPR GYWW | ICW
LC | 126126405 | 010/225 | T2 DI VOLTA-DESCH 10/225 RPR POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-14 | 2023-05-09 | 2024-03-05 | On-time | 2024-05-08 | 64 | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46063192 | T2 DI VOLTA-DESCH 10/225 RPR POLE | ICW
LC | 126126451 | 015/339 | T2 DI VOLTA-DESCH 15/339 RPL STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-14 | 2023-05-09 | 2024-02-13 | On-time | 2024-05-08 | 85 | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521024 | T2 DI VOLTA-DESCH 15/339 RPL STRW | 70Y
LC | 126119839 | 052/008 | T2 DI TRNTY-MPL CRK 052/008 RPR JMPW | EUREKA | ETL.8170.INSL.NCER | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2023-08-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46190013 | T2 DI TRNTY-MPL CRK 052/008 RPR JMPW | ICW
LC | 126119964 | 049/003 | T2 DI TRNTY-MPL CRK 49/3L RPL HRDD | EUREKA | ETL.8170.POLE.STPS | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46172286 | T2 DI TRNTY-MPL CRK 049/003 RPL HRDD | ICW
LC | 126126561 | 009/204 | T2 DI VOLTA-DESCH 9/204 RPL HRDD | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-14 | 2023-05-09 | 2024-02-22 | On-time | 2024-05-08 | 76 | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46054063 | T2 DI VOLTA-DESCH 9/204 RPL HRDD | ICW
LC | 126120056 | 042/006 | T2 DI TRINITY-MAPLE CRK 42/6 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35509126 | T2 DI TRINITY-MAPLE CRK 42/6 RPL POLE | 70Y
LC | 126120099 | 007/084A | T2 EI DRUM-SUMMIT #2 7/84A COMPLETE | SACTO | ETL.1450.POLE.NWOD | 2023-05-12 | 2023-05-12 | 2024-05-16 | Late | 2024-05-11 | -5 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053992 | T2 EI DRUM-SUMMIT #2 7/84A RPR GYWW | ICW
LC | 126120145 | 035/236 | T2 EI TRNTY-CTTNWD 035/236R UNBURY | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-12 | 2023-05-12 | 2024-05-31 | Late | 2024-05-11 | -20 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46062553 | T2 EI TRNTY-CTTNWD 035/236R UNBURY | ICW
LC | 126126584 | 003/018A | T2 DI TRINITY-MAPLE CRK 3/18A RPL TIEW | EUREKA | ETL.8170.INSL.CERA | 2023-05-14 | 2023-05-09 | 2024-02-20 | On-time | 2024-05-08 | 78 | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46070772 | T2 DI TRINITY-MAPLE CRK 3/18A RPL TIEW | ICW
LC | 126120177 | 035/236 | T2 EI TRNTY-CTTNWD 035/236R RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-12 | 2023-05-12 | 2024-05-31 | Late | 2024-05-11 | -20 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062554 | T2 EI TRNTY-CTTNWD 035/236R RPR GYWW | ICW
LC | 126120241 | 045/330A | T2 EI CARIBOU-TABLE MTN 45/330A COTTER | TABLEMTN | ETL.4440.INSL.CERA | 2023-05-12 | 2023-05-12 | 2024-06-08 | Late | 2024-05-11 | -28 | 2024-05-12 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46250265 | T2 EI CARIBOU-TABLE MTN 45/330A COTTER | ICS
LC | 126146933 | 019/439 | T2 DI VLTA-DESCHTES 19/439 REFRAME | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-16 | 2023-05-09 | 2024-04-16 | On-time | 2024-05-08 | 22 | 2024-05-09 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35485512 | T2 DI VLTA-DESCHTES 19/439 REFRAME | 93E
LC | 126154451 | 019/429 | T2 DI VLTA DSHUTS 19/429 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-17 | 2023-05-09 | 2024-04-15 | On-time | 2024-05-08 | 23 | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485605 | T2 DI VLTA DSHUTS 16/343 RPL STRW | 70Y
LC | 126095268 | 015/086 | T2 BAHIA-MORAGA 12/070 RPL HNGR | CONCORD | ETL.4340.INSL.NCER | 2023-05-10 | 2023-05-10 | 2024-04-22 | On-time | 2024-05-09 | 17 | 2024-05-10 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hanger Plate - Tower | Replace | 46059040 | T2 BAHIA-MORAGA 12/070 RPL HNGR | ICQ
LC | 126096152 | 016/096 | T2 PARKWAY-MORAGA 16/96 RPLC INSS | CONCORD | ETL.5930.INSL.CERA | 2023-05-10 | 2023-05-10 | 2023-05-09 | On-time | 2024-05-09 | 366 | 2024-05-10 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31645583 | T2 PARKWAY-MORAGA 16/96 RPLC INSS | 93K
LC | 126096223 | 005/064 | T2 EI BURNS-LONE STAR #1 05/064 RPR GYWW | MOSSLNDG | ETL.6230.POLE.NWOD | 2023-05-10 | 2023-05-10 | 2024-04-11 | On-time | 2024-05-09 | 28 | 2024-05-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46081519 | T2 EI BURNS-LONE STAR #1 05/064 RPR GYWW | ICW
LC | 126096417 | 010/055 | T2 RND MTN-TBL MTN #1 10/055 RPR INSS | TABLEMTN | ETL.6060.INSL | 2023-05-10 | 2023-05-10 | 2023-11-17 | On-time | 2024-05-09 | 174 | 2024-05-10 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46049820 | T2 RND MTN-TBL MTN #1 10/055 RPR INSS | ICS
LC | 126120914 | 012/282 | T2 EI SALINAS-LAURELES 012/282 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-12 | 2023-05-12 | 2024-06-15 | Late | 2024-05-11 | -35 | 2024-05-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35507180 | T2 EI SALINAS-LAURELES 012/282 RPL STRW | 70Y
LC | 126120920 | 033/000C | T2 EI PHILO JCT-ELK 33/0C RPL HRDW | WILLITS | ETL.7780.POLE.WOOD | 2023-05-12 | 2023-05-12 | 2024-06-11 | Late | 2024-05-11 | -31 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46213842 | T2 EI PHILO JCT-ELK 33/0C RPL HRDW | ICW
LC | 126120940 | 007/084C | T2 EI DRUM-SUMMIT #2 7/84C COMPLETE | SACTO | ETL.1450.POLE.NWOD | 2023-05-12 | 2023-05-12 | 2024-05-16 | Late | 2024-05-11 | -5 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053994 | T2 EI DRUM-SUMMIT #2 7/84C RPR GYWW | ICW
LC | 126096735 | 013/264 | T2 EI CARIBOU-WESTWOOD 13/264 RMV VEG | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-10 | 2023-05-10 | 2024-03-08 | On-time | 2024-05-09 | 62 | 2024-05-10 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Trim
LC | 126097374 | 012/056 | T2 EI MORRO BAY-MESA 12/56 RPR FOND | PISMOBCH | ETL.5290.TOWR | 2023-05-10 | 2023-05-10 | 2024-02-21 | On-time | 2024-05-09 | 78 | 2024-05-10 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46051307 | T2 EI MORRO BAY-MESA 12/56 RPR FOND | ICQ
LC | 126121178 | ;000/032 | T2 DI CARIBOU #2 ;000/32 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2023-11-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053907 | T2 DI CARIBOU #2 ;000/32 RPR GYWW | ICW
LC | 126121195 | 003/012 | T2 DI TRINITY-MAPLE CREEK 3/012 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-08 | 2024-05-11 | Late | 2024-05-07 | -4 | 2024-05-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35496185 | T2 DI TRINITY-MAPLE CRK 3/7 RPL STRW | 70Y
LC | 126121233 | :001/013 | T2 EI CARIBOU #2 :001/013 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526759 | T2 EI CARIBOU #2 :001/013 RPL POLE | 70Y
LC | 126097576 | 038/251A | T2 EI TRINITY-CTTNWD 038/251A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-10 | 2023-05-10 | 2023-07-06 | On-time | 2024-05-09 | 308 | 2023-08-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805353 | T2 EI TRINITY-CTTNWD 038/251A RPR GYWW | ICW
LC | 126121319 | 051/006 | T2 EI TRINITY-MAPLE CREEK 51/6 GO95 | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35529605 | T2 EI TRINITY-MAPLE CREEK 51/6 GO95 | 93G
LC | 126121337 | 013/284 | T2 EI SALINAS-LAURELES 013/284 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35507017 | T2 EI SALINAS-LAURELES 013/284 RPL STRW | 70Y
LC | 126097595 | 028/140 | T2 EI ROUND MTN-TBL MTN #1 28/140 UNBURY | TABLEMTN | ETL.6060.TOWR | 2023-05-10 | 2023-05-10 | 2024-02-06 | On-time | 2024-05-09 | 93 | 2024-05-10 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46057519 | T2 EI ROUND MTN-TBL MTN #1 28/140 UNBURY | ICQ
LC | 126121506 | 048/029 | T2 DI TRNTY-MPL CRK 048/029 RPL ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35506445 | T2 DI TRNTY-MPL CRK 048/029 RPL ANCW | 93E
LC | 126121682 | 074/378 | T2 DI MALN-ROND MONTN #2 74/378 RPL ANCT | TABLEMTN | ETL.6020.TOWR | 2023-05-12 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 93Z | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Tower | Replace | 31677426 | T2 DI MALN RND-MT #2 RPL ANCHOR TWR 74/3 | 93Z
LC | 126097596 | 028/140 | T2 EI ROND MTN-TBL MTN #1 28/140 BNT STL | TABLEMTN | ETL.6060.TOWR | 2023-05-10 | 2023-05-10 | 2023-12-11 | On-time | 2024-05-09 | 150 | 2024-05-10 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46057540 | T2 EI ROND MTN-TBL MTN #1 28/140 BNT STL | ICQ
LC | 126097889 | 038/251B | T2 EI TRINITY-CTTNWD 038/251B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-10 | 2023-05-10 | 2023-07-06 | On-time | 2024-05-09 | 308 | 2023-08-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805355 | T2 EI TRINITY-CTTNWD 038/251B RPR GYWW | ICW
LC | 126121690 | 049/011 | T2 DI TRNTY-MPL CRK 049/011 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506447 | T2 DI TRNTY-MPL CRK 049/011 RPL STRW | 70Y
LC | 126098262 | 038/251C | T2 EI TRINITY-CTTNWD 038/251C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-10 | 2023-05-10 | 2023-07-06 | On-time | 2024-05-09 | 308 | 2024-05-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805356 | T2 EI TRINITY-CTTNWD 038/251C RPR GYWW | ICW
LC | 126121712 | 003/021 | T2 DI BTTE VLY-CARIBOU 3/21 RPL INSS | TABLEMTN | ETL.1180.INSL.CERA | 2023-05-12 | 2023-05-08 | 2024-06-05 | Late | 2024-05-07 | -29 | 2024-05-08 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35511333 | T2 DI BTTE VLY-CARIBOU RPL INSS 2 TWRS | 93K
LC | 126121742 | 086/004C | T2 EI HUMBOLDT-TRINITY 86/4C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-12 | 2023-05-12 |  | Late | 2024-05-11 |  | 2023-08-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096239 | T2 EI HUMBOLDT-TRINITY 86/4C RPR GYWW | ICW
LC | 126121752 | 051/010 | T2 DI TRNTY-MPL CRK 51/10L RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506527 | T2 DI TRNTY-MPL CRK 51/10L RPL STRW | 70Y
LC | 126121753 | 051/010 | T2 DI TRNTY-MPL CRK 051/010C RPL PL | EUREKA | ETL.8170.POLE.WDPS | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506527 | T2 DI TRNTY-MPL CRK 51/10L RPL STRW | 70Y
LC | 126121754 | 051/010 | T2 DI TRNTY-MPL CRK 051/010R RPL PL | EUREKA | ETL.8170.POLE.WDPS | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506527 | T2 DI TRNTY-MPL CRK 51/10L RPL STRW | 70Y
LC | 126098331 | 078/318 | T2 EI RND MTN-TBL MTN #2 78/318 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2023-05-10 | 2023-05-10 | 2023-12-29 | On-time | 2024-05-09 | 132 | 2024-05-10 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072137 | T2 EI RND MTN-TBL MTN #2 78/318 RPR STRT | ICQ
LC | 126098335 | 029/141 | T2 EI ROND MTN-TBL MTN #2 29/141 BNT STL | TABLEMTN | ETL.6070.TOWR | 2023-05-10 | 2023-05-10 | 2024-02-06 | On-time | 2024-05-09 | 93 | 2024-05-10 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46057548 | T2 EI ROND MTN-TBL MTN #2 29/141 BNT STL | ICQ
LC | 126098336 | 029/141 | T2 EI RND MTN-TBL MTN #2 29/141 RPR GYWS | TABLEMTN | ETL.6070.TOWR | 2023-05-10 | 2023-05-10 | 2024-02-06 | On-time | 2024-05-09 | 93 | 2024-05-10 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46057549 | T2 EI RND MTN-TBL MTN #2 29/141 RPR GYWS | ICS
LC | 126121853 | 004/012 | T2 DI TRNTY-MPL CRK 004/012 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35496183 | T2 DI TRNTY-MPL CRK 004/012 RPL POLE | 70Y
LC | 126100287 | 029/144 | T2 EI RND MTN-TBL MTN #1 29/144 RPR GYWS | TABLEMTN | ETL.6060.TOWR | 2023-05-10 | 2023-05-10 | 2024-02-06 | On-time | 2024-05-09 | 93 | 2024-05-10 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46057541 | T2 EI RND MTN-TBL MTN #1 29/144 RPR GYWS | ICS
LC | 126100384 | 096/005C | T2 EI HUMBOLDT-TRINITY 96/5C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-10 | 2023-05-10 | 2024-04-08 | On-time | 2024-05-09 | 31 | 2024-05-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096237 | T2 EI HUMBOLDT-TRINITY 96/5C RPR GYWW | ICW
LC | 126121908 | 041/009 | T2 DI FT RSS-GUALALA 41/9L RPL STRW | LAKEVLLE | ETL.6980.POLE.WDPS | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2023-11-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518740 | T2 DI FT RSS-GUALALA 41/9L RPL STRW | 70Y
LC | 126101304 | 014/076 | T2 ETLI00000879 014/076 INS DAMS | MOSSLNDG | ETL.2840.INSL.NCER | 2023-05-10 | 2023-05-10 | 2023-06-01 | On-time | 2024-05-09 | 343 | 2024-05-10 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 45769787 | T2 ETLI00000879 014/076 INS DAMS | ICS
LC | 126101371 | 012/146 | T2 EI DRUM-SUMMIT #1 012/146L COMPLETE | SACTO | ETL.1440.POLE.STPS | 2023-05-10 | 2023-05-10 | 2023-07-14 | On-time | 2024-05-09 | 300 | 2024-05-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45935597 | T2 EI DRUM-SUMMIT #1 012/146L COMPLETE | ICW
LC | 126101446 | 077/315 | T2 EI RND MTN-TBL MTN#2 77/315 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2023-05-10 | 2023-05-10 | 2023-12-29 | On-time | 2024-05-09 | 132 | 2024-05-10 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072134 | T2 EI RND MTN-TBL MTN#2 77/315 RPR STRT | ICQ
LC | 126101450 | 077/315 | T2 EI RND MTN-TBL MTN#2 77/315 RPR GYWS | TABLEMTN | ETL.6070.TOWR | 2023-05-10 | 2023-05-10 | 2023-12-26 | On-time | 2024-05-09 | 135 | 2024-05-10 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Replace | 46072135 | T2 EI RND MTN-TBL MTN#2 77/315 RPR GYWS | ICS
LC | 126121931 | 050/011 | T2 DI TRNTY-MPL CRK 050/011 RPR STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46170743 | T2 DI TRNTY-MPL CRK 050/011 RPR STRW | ICW
LC | 126102575 | 003/049 | T2 EI BURNS-LONE STAR #1 3/49 COTTER | MOSSLNDG | ETL.6230.INSL | 2023-05-10 | 2023-05-10 | 2024-04-11 | On-time | 2024-05-09 | 28 | 2024-05-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081541 | T2 EI BURNS-LONE STAR #1 3/49 COTTER | ICW
LC | 126121942 | 041/009 | T2 DI FT RSS-GUALALA 41/9C RPL STRW | LAKEVLLE | ETL.6980.POLE.WDPS | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2023-11-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518740 | T2 DI FT RSS-GUALALA 41/9L RPL STRW | 70Y
LC | 126121946 | 041/009 | T2 DI FT RSS-GUALALA 41/9R RPL STRW | LAKEVLLE | ETL.6980.POLE.WDPS | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2023-11-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518740 | T2 DI FT RSS-GUALALA 41/9L RPL STRW | 70Y
LC | 126122012 | 042/008 | T2 DI TRINITY-MPL CRK 42/08 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506769 | T2 DI TRINITY-MPL CRK 42/08 RPL POLE | 70Y
LC | 126122050 | 051/004 | T2 DI TRNTY-MPL CRK 051/004 GO95 | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35529604 | T2 DI TRNTY-MPL CRK 051/004 GO95 | 93G
LC | 126122052 | 006/001 | T2 DI LAKEVILLE #1 6/1 RPL POLE | LAKEVLLE | ETL.7360.POLE.WOOD | 2023-05-12 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521156 | T2 DI LAKEVILLE #1 6/1 RPL POLE | 70Y
LC | 126122058 | 041/004 | T2 DI FT ROSS-GUALALA 41/4 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-12 | 2023-05-05 |  | Late | 2024-05-04 |  | 2024-05-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35555332 | T2 DI FT ROSS-GUALALA 41/4 RPL STRW | 70Y
LC | 126122061 | 044/005 | T2 DI TRINITY-MPL CRK 44/5 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-12 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506297 | T2 DI TRINITY-MPL CRK 44/5 RPL STRW | 70Y
LC | 126102925 | 077/314 | T2 EI RND MTN-TBL MTN#2 77/314 RMV VEG | TABLEMTN | ETL.6070.TOWR | 2023-05-10 | 2023-05-10 | 2024-05-07 | On-time | 2024-05-09 | 2 | 2024-05-10 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126109303 | 009/039 | T2 DI DIABLO-GATES #1 9/39 RPR SHLS | PISMOBCH | ETL.5960.TOWR | 2023-05-11 | 2023-05-10 | 2024-03-04 | On-time | 2024-05-09 | 66 | 2024-05-10 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46078942 | T2 DI DIABLO-GATES #1 9/39 RPR SHLS | ICS
LC | 126109493 | 015/063 | T2 DI DIABLO-GATES# 1 RPR SHLS | PISMOBCH | ETL.5960.TOWR | 2023-05-11 | 2023-05-10 | 2024-04-08 | On-time | 2024-05-09 | 31 | 2024-05-10 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46078946 | T2 DI DIABLO GATES#1 RPR SHLS | ICS
LC | 126122343 | 024/010 | T2 DI TRINITY-MPLE CRK 24/10 BACKFILL | EUREKA | ETL.8170.POLE.WOOD | 2023-05-13 | 2023-05-09 | 2024-06-13 | Late | 2024-05-08 | -36 | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Regrade | 46172033 | T2 DI TRINITY-MPLE CRK 24/10 BACKFILL | ICW
LC | 126122349 | 005/004 | T2 DI TRINITY-MPL CRK-05/04 RPR INSW | EUREKA | ETL.8170.INSL.NCER | 2023-05-13 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46070773 | T2 DI TRINITY-MPL CRK-05/04 RPR INSW | ICW
LC | 126111748 | X008/037 | T2 DI MORRO BAY-DIABLO X008/037 RPL INSS | PISMOBCH | ETL.5260.INSL | 2023-05-11 | 2023-05-10 | 2024-05-02 | On-time | 2024-05-09 | 7 | 2024-05-10 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513944 | T2 DI MORRO BAY-DIABLO X008/037 RPL INSS | 93K
LC | 126111964 | 016/065 | T2 DI DIABLO-GATES #1 16/65 RPR SHLS | PISMOBCH | ETL.5960.TOWR | 2023-05-11 | 2023-05-10 | 2024-04-10 | On-time | 2024-05-09 | 29 | 2024-05-10 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46078947 | T2 DI DIABLO-GATES#1 16/65 RPR SHLS | ICS
LC | 126122331 | 012/261 | T2 DI VOLTA-DESCHUTES 012/261 RPL HRDW | TABLEMTN | ETL.8290.POLE.NWOD | 2023-05-13 | 2023-05-10 | 2024-02-26 | On-time | 2024-05-09 | 73 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46053931 | T2 DI VOLTA-DESCHUTES 012/261 RPL HRDW | ICW
LC | 126122333 | 012/261 | T2 DI VOLTA-DESCHUTES 012/261 RPR INSW | TABLEMTN | ETL.8290.INSL.NCER | 2023-05-13 | 2023-05-10 | 2024-02-26 | On-time | 2024-05-09 | 73 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46053932 | T2 DI VOLTA-DESCHUTES 012/261 RPR INSW | ICW
LC | 126122357 | 016/354 | T2 DI VLTA-DSCHTS 016/354 RPR STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-13 | 2023-05-10 | 2024-04-17 | On-time | 2024-05-09 | 22 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46053936 | T2 DI VLTA-DSCHTS 016/354 RPR STRW | ICW
LC | 126122374 | 009/133-GUY | T2 DI GOLD HILL #1 9/133-GUY RPR GYWW | SACTO | ETL.6950.POLE.WOOD | 2023-05-13 | 2023-05-10 | 2024-04-03 | On-time | 2024-05-09 | 36 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46049063 | T2 DI GOLD HILL #1 9/133-GUY RPR GYWW | ICW
LC | 126122440 | 008/181 | T2 DI VLTA-DSCHTS 008/181 RPR SPLW | TABLEMTN | ETL.8290.INSL | 2023-05-13 | 2023-05-10 | 2024-02-27 | On-time | 2024-05-09 | 72 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46074150 | T2 DI VLTA-DSCHTS 008/181 RPR SPLW | ICW
LC | 126123059 | 079/400 | T2 DI MALIN-ROUND MTN #2 79/400 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-05-14 | 2023-04-19 | 2024-05-11 | Late | 2024-04-18 | -23 | 2024-04-19 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46027043 | T2 DI MALIN-ROUND MTN #2 79/400 RPR SHLS | ICS
LC | 126123080 | 015/327 | T2 DI VOLTA-DESCHUTES 15/327 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-14 | 2023-05-10 | 2024-02-14 | On-time | 2024-05-09 | 85 | 2024-05-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485603 | T2 DI VOLTA-DESCHUTES 13/274 RPL STRW | 70Y
LC | 126126517 | 014/304 | T2 DI VOLTA-DESCHUTES 14/304 RPR STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-14 | 2023-05-10 | 2024-01-16 | On-time | 2024-05-09 | 114 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46053934 | T2 DI VOLTA-DESCHUTES 14/304 RPR STRW | ICW
LC | 126123125 | 048/007 | T2 DI TRINITY-MPL CR 48/7 COTTER | EUREKA | ETL.8170.INSL | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46172258 | T2 DI TRINITY-MPL CR 48/7 COTTER | ICW
LC | 126123151 | 049/014 | T2 DI TRINITY-MPL CR 49/14 COTTER | EUREKA | ETL.8170.INSL | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46172289 | T2 DI TRINITY-MPL CR 49/14 COTTER | ICW
LC | 126126597 | 013/279 | T2 DI VOLTA-DESCHUTES 13/279 RPR STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-14 | 2023-05-10 | 2024-02-26 | On-time | 2024-05-09 | 73 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46053933 | T2 DI VOLTA-DESCHUTES 13/279 RPR STRW | ICW
LC | 126123160 | 051/008 | T2 DI TRINITY-MAPLE CRK 51/8 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506525 | T2 DI TRINITY-MAPLE CRK 51/8 RPL STRW | 70Y
LC | 126126616 | 008/189 | T2 DI VLTA-DSCHTS 008/189 RPR INSW | TABLEMTN | ETL.8290.INSL | 2023-05-14 | 2023-05-10 | 2024-01-23 | On-time | 2024-05-09 | 107 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46063196 | T2 DI VLTA-DSCHTS 008/189 RPR INSW | ICW
LC | 126124734 | 037/320 | T2 EI CASCADE-CTTNWOOD 37/320 RPL INSW | TABLEMTN | ETL.1240.INSL.CERA | 2023-05-14 | 2023-05-13 |  | Late | 2024-05-12 |  | 2024-05-13 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35518945 | T2 EI CASCADE-CTTNWOOD 37/320 RPL INSLW | 93I
LC | 126126634 | 010/231 | T2 DI VOLTA-DESCH 10/231 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-14 | 2023-05-10 | 2024-02-22 | On-time | 2024-05-09 | 77 | 2024-05-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485602 | T2 DI VOLTA-DESCH 9/197 RPL POLE | 70Y
LC | 126126637 | 015/325 | T2 DI VOLTA-DESCHUTES 15/325 RPR CNDW | TABLEMTN | ETL.8290.INSL.CERA | 2023-05-14 | 2023-05-10 | 2023-05-23 | On-time | 2024-05-09 | 352 | 2023-08-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45766272 | T2 DI VOLTA-DESCHUTES 15/325 RPR CNDW | ICW
LC | 126126777 | 010/226 | T2 DI VOLTA-DESCH 10/226 RPR POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-14 | 2023-05-10 | 2024-02-22 | On-time | 2024-05-09 | 77 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46063198 | T2 DI VOLTA-DESCH 10/226 RPR POLE | ICW
LC | 126126801 | 008/173 | T2 DI VOLTA-DESCH 8/173 RPR INSW | TABLEMTN | ETL.8290.INSL | 2023-05-14 | 2023-05-10 | 2024-01-23 | On-time | 2024-05-09 | 107 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46063195 | T2 DI VOLTA-DESCH 8/173 RPR INSW | ICW
LC | 126124819 | 005/089 | T2 EI PT #1-HT CRK #2-BRNY 5/89 RPL POLE | TABLEMTN | ETL.7040.POLE.WOOD | 2023-05-14 | 2023-05-13 | 2024-05-15 | Late | 2024-05-12 | -3 | 2024-05-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485424 | T2 EI PT #1-HT CRK #2-BRNY 3/40 RPL STRW | 70Y
LC | 126126809 | 009/197 | T2 DI VOLTA-DESCH 9/197 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-14 | 2023-05-10 | 2024-02-26 | On-time | 2024-05-09 | 73 | 2024-05-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485602 | T2 DI VOLTA-DESCH 9/197 RPL POLE | 70Y
LC | 126126835 | 015/320 | T2 DI VOLTA-DESCHUTES 15/320 RPR INSW | TABLEMTN | ETL.8290.INSL.NCER | 2023-05-14 | 2023-05-10 | 2024-04-24 | On-time | 2024-05-09 | 15 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46053935 | T2 DI VOLTA-DESCHUTES 15/320 RPR INSW | ICW
LC | 126125337 | 050/003 | T2 DI TRINITY-MPL CRK 50/3 GO95 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35529656 | T2 DI TRINITY-MPL CRK 50/3 GO95 RPL POLE | 93G
LC | 126126847 | 010/221 | T2 DI VOLTA-DESCH 10/221 RPR INSW | TABLEMTN | ETL.8290.INSL.NCER | 2023-05-14 | 2023-05-10 | 2024-02-22 | On-time | 2024-05-09 | 77 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46063197 | T2 DI VOLTA-DESCH 10/221 RPR INSW | ICW
LC | 126125353 | 050/002 | T2 DI TRINITY-MPL CR 50/2 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-14 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506456 | T2 DI TRINITY-MPL CR 50/2 RPL PL | 70Y
LC | 126125670 | 004/015 | T2 DI TRINITY-MAPLE CREEK 04/15 RPR JMPW | EUREKA | ETL.8170.INSL.NCER | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2023-08-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46070767 | T2 DI TRINITY-MAPLE CREEK 04/15 RPR JMPW | ICW
LC | 126125674 | 004/015 | T2 DI TRINITY-MAPLE CREEK 04/15 RPR ANCW | EUREKA | ETL.8170.POLE.WDPS | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46070768 | T2 DI TRINITY-MAPLE CREEK 04/15 RPR ANCW | ICW
LC | 126125675 | 004/015 | T2 DI TRINITY-MAPLE CREEK 04/15 RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46070770 | T2 DI TRINITY-MAPLE CREEK 04/15 RPR GYWW | ICW
LC | 126126851 | 007/167 | T2 DI VOLTA-DESCHUTES 07/167 RPR POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-14 | 2023-05-10 | 2024-01-23 | On-time | 2024-05-09 | 107 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46063194 | T2 DI VOLTA-DESCHUTES 07/167 RPR POLE | ICW
LC | 126147578 | 019/440 | T2 DI VLTA-DSHUTS 19/440 REFRAME | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-16 | 2023-05-10 | 2024-04-16 | On-time | 2024-05-09 | 23 | 2024-05-10 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35485512 | T2 DI VLTA-DESCHTES 19/439 REFRAME | 93E
LC | 126152235 | 017/383 | T2 DI VLTA DSHUTS 17/383 RPR CNDW | TABLEMTN | ETL.8290.INSL | 2023-05-17 | 2023-05-10 | 2024-04-16 | On-time | 2024-05-09 | 23 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46053937 | T2 DI VLTA DSHUTS 17/383 RPR CNDW | ICW
LC | 126126265 | 048/002 | T2 DI TRINITY-MAPLE CRK 48/2 COTTER | EUREKA | ETL.8170.INSL.NCER | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2023-11-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46172255 | T2 DI TRINITY-MAPLE CRK 48/2 RPR INSW | ICW
LC | 126126399 | 021/010 | T2 DI MNDCN-HRTLY 21/10 RPL HRDD | WILLITS | ETL.7510.POLE.WOOD | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46073468 | T2 DI MNDCN-HRTLY 21/10 RPL HRDD | ICW
LC | 126152264 | 015/324 | T2 DI VOLTA-DESCHTES 015/324 RPR CNDW | TABLEMTN | ETL.8290.INSL.NCER | 2023-05-17 | 2023-05-10 | 2023-05-24 | On-time | 2024-05-09 | 351 | 2023-08-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45824054 | T2 DI VOLTA-DESCHTES 015/324 RPR CNDW | ICW
LC | 126153206 | 010/214 | T2 DI VLTA DSHUTS 10/214 RPR POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-17 | 2023-05-10 | 2024-01-23 | On-time | 2024-05-09 | 107 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062482 | T2 DI VLTA DSHUTS 10/214 RPR POLE | ICW
LC | 126154075 | 007/162 | T2 DI VLTA DSHUTS 07/162 RPR INSW | TABLEMTN | ETL.8290.INSL.NCER | 2023-05-17 | 2023-05-10 | 2024-02-26 | On-time | 2024-05-09 | 73 | 2024-05-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46063193 | T2 DI VLTA DSHUTS 07/162 RPR INSW | ICW
LC | 126156111 | 016/343 | T2 DI VLTA DSHUTS 16/343 COMPLETE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-17 | 2023-05-10 | 2024-02-14 | On-time | 2024-05-09 | 85 | 2024-05-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485605 | T2 DI VLTA DSHUTS 16/343 RPL STRW | 70Y
LC | 126156524 | 015/331 | T2 DI VLTA DSHUTS 15/331 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-17 | 2023-05-10 | 2024-02-13 | On-time | 2024-05-09 | 86 | 2024-05-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485603 | T2 DI VOLTA-DESCHUTES 13/274 RPL STRW | 70Y
LC | 126126473 | 003/020 | T2 DI TRINITY-MAPLE CREEK 3/20 RPR JMPRW | EUREKA | ETL.8170.INSL.NCER | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2023-08-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46193769 | T2 DI TRINITY-MAPLE CREEK 3/20 RPR JMPRW | ICW
LC | 126103859 | 000/007 | T2 COLGATE-CHALLENGE 000/007 RPR INSW | SACTO | ETL.6480.INSL.NCER | 2023-05-11 | 2023-05-11 | 2024-04-09 | On-time | 2024-05-10 | 31 | 2024-05-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46053961 | T2 COLGATE-CHALLENGE 000/007 RPR INSW | ICW
LC | 126126490 | 035/287 | T2 DI BRDGVLL-CTTNWD 35/287R RPL HRDD | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-14 | 2023-05-08 | 2024-06-01 | Late | 2024-05-07 | -25 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46054036 | T2 DI BRDGVLL-CTTNWD 35/287R RPL HRDD | ICW
LC | 126126491 | 035/287 | T2 DI BRDGVLL-CTTNWD 35/287L RPL ANCW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35525611 | T2 DI BRIDGVLL-COTTONWD 35/281L RPL ANCW | 93E
LC | 126104381 | 007/010-GUY | T2 EI MELONES-RACETRACK 7/10GUY RPL POLE | VICTOR | ETL.2400.POLE.WOOD | 2023-05-11 | 2023-05-11 | 2023-11-15 | On-time | 2024-05-10 | 177 | 2024-05-11 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31605930 | T2 DI MELONES-RACETRACK 0/8 RPL POLE | 70Y
LC | 126126500 | 052/005 | T2 DI TRINITY-MAPLE CREEK 52/5 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506529 | T2 DI TRINITY-MAPLE CREEK 52/5 RPL STRW | 70Y
LC | 126126503 | 043/002 | T2 DI TRINITY-MAPLE CRK 43/2 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-14 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506290 | T2 DI TRINITY-MAPLE CRK 43/2 RPL STRW | 70Y
LC | 126105408 | 095/000 | T2 EI HUMBOLDT-TRINITY 95/0L RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-05-11 | 2023-05-11 | 2024-03-12 | On-time | 2024-05-10 | 59 | 2024-05-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096238 | T2 EI HUMBOLDT-TRINITY 95/0L RPR GYWW | ICW
LC | 126106022 | 095/000 | T2 EI HUMBOLDT-TRINITY 95/0C RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-05-11 | 2023-05-11 | 2024-03-12 | On-time | 2024-05-10 | 59 | 2024-05-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096238 | T2 EI HUMBOLDT-TRINITY 95/0L RPR GYWW | ICW
LC | 126106228 | 095/000 | T2 EI HUMBOLDT-TRINITY 95/0R RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-05-11 | 2023-05-11 | 2024-03-12 | On-time | 2024-05-10 | 59 | 2024-05-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096238 | T2 EI HUMBOLDT-TRINITY 95/0L RPR GYWW | ICW
LC | 126106819 | 018/149 | T2 EI PIT #1-COTTONWOOD 018/149 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-11 | 2023-05-11 | 2023-11-14 | On-time | 2024-05-10 | 178 | 2024-05-11 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46057506 | T2 EI PIT #1-COTTONWOOD 018/149 UNBURY | ICQ
LC | 126126575 | 040/006 | T2 DI FT ROSS-GUALALA 4/6 RPR GYWW | LAKEVLLE | ETL.6980.POLE.STPS | 2023-05-14 | 2023-05-08 | 2024-06-25 | Late | 2024-05-07 | -49 | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073473 | T2 DI FT ROSS-GUALALA 4/6 RPR GYWW | ICW
LC | 126106854 | 031/217 | T2 EI TRNTY-CTTNWD 031/217R UNBURY | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-11 | 2023-05-11 | 2023-07-28 | On-time | 2024-05-10 | 287 | 2023-11-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45805428 | T2 EI TRNTY-CTTNWD 031/217R UNBURY | ICW
LC | 126126588 | 052/006 | T2 DI TRINITY-MAPLE CREEK 52/06 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-05-14 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096686 | T2 DI TRINITY-MAPLE CREEK 52/06 RPR GYWW | ICW
LC | 126106855 | 031/217 | T2 EI TRNTY-CTTNWD 031/217R RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-11 | 2023-05-11 | 2023-07-28 | On-time | 2024-05-10 | 287 | 2024-05-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 126107134 | 027/136B | T2 EI RND MTN-TBL MTN#2 27/136B RPR GYWS | TABLEMTN | ETL.6070.POLE.NWOD | 2023-05-11 | 2023-05-11 | 2024-02-14 | On-time | 2024-05-10 | 86 | 2024-05-11 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46057547 | T2 EI RND MTN-TBL MTN#2 27/136B RPR GYWS | ICS
LC | 126107202 | 007/164 | T2 EI HAMLTN BRNCH-CHSTR 7/164 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-05-11 | 2023-05-11 | 2023-10-06 | On-time | 2024-05-10 | 217 | 2024-05-11 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663421 | T2 EI HAMLTN BRNCH-CHSTR 7/164 RPL POLE | 70Y
LC | 126107264 | 027/136A | T2 EI ROUND MTN-TABLE MTN #1 RPR INSS | TABLEMTN | ETL.6060.INSL | 2023-05-11 | 2023-05-11 | 2023-11-11 | On-time | 2024-05-10 | 181 | 2024-05-11 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46073828 | T2 EI ROUND MTN-TABLE MTN #1 RPR INSS | ICS
LC | 126107329 | 031/217 | T2 EI TRNTY-CTTNWD 031/217C RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-11 | 2023-05-11 | 2023-07-28 | On-time | 2024-05-10 | 287 | 2024-05-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 126107693 | 013/276 | T2 WV KILARC-DESCHUTES 113/276 INS DAMP | TABLEMTN | ETL.7300.INSL.NCER | 2023-05-11 | 2023-05-11 | 2024-04-04 | On-time | 2024-05-10 | 36 | 2024-05-11 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46053966 | T2 WV KILARC-DESCHUTES 113/276 INS DAMP | ICW
LC | 126107799 | 011/136A | T2 EI DRUM-SUMMIT #1 011/136A RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-05-11 | 2023-05-11 | 2023-06-20 | On-time | 2024-05-10 | 325 | 2023-08-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45809305 | T2 EI DRUM-SUMMIT #1 011/136A RPR GYWW | ICW
LC | 126107860 | 011/136B | T2 EI DRUM-SUMMIT #1 011/136B RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-05-11 | 2023-05-11 | 2023-06-20 | On-time | 2024-05-10 | 325 | 2023-08-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45809306 | T2 EI DRUM-SUMMIT #1 011/136B RPR GYWW | ICW
LC | 126107867 | 031/217 | T2 EI TRNTY-CTTNWD 031/217L RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-11 | 2023-05-11 | 2023-07-28 | On-time | 2024-05-10 | 287 | 2024-05-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45984919 | T2 EI TRNTY-CTTNWD 031/217L RPR GYWW | ICW
LC | 126108576 | 027/135 | T2 EI RND MTN-TBL MTN#1 27/135 UNBURY | TABLEMTN | ETL.6060.TOWR | 2023-05-11 | 2023-05-11 | 2023-12-11 | On-time | 2024-05-10 | 151 | 2024-05-11 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Steel | Repair | 46057518 | T2 EI RND MTN-TBL MTN#1 27/135 UNBURY | ICS
LC | 126109022 | 027/134 | T2 EI ROND MTN-TBL MTN #2 27/134 BNT STL | TABLEMTN | ETL.6070.TOWR | 2023-05-11 | 2023-05-11 | 2024-04-30 | On-time | 2024-05-10 | 10 | 2024-05-11 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46057546 | T2 EI ROND MTN-TBL MTN #2 27/134 BNT STL | ICQ
LC | 126110492 | 077/313 | T2 EI RND MTN-TBL MTN#2 77/313 CANCEL | TABLEMTN | ETL.6070.TOWR | 2023-05-11 | 2023-05-11 | 2024-04-04 | On-time | 2024-05-10 | 36 | 2024-05-11 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126126833 | 053/007 | T2 DI FT ROSS-GUALALA 53/7 RPL POLE | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487984 | T2 DI FT ROSS-GUALALA 53/7 RPL POLE | 70Y
LC | 126110503 | 037/161 | T2 EI MOSS LANDING-LOS BNS 37/161 COTTER | MOSSLNDG | ETL.6040.INSL | 2023-05-11 | 2023-05-11 | 2024-02-22 | On-time | 2024-05-10 | 78 | 2024-05-11 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46073332 | T2 EI MOSS LANDING-LOS BNS 37/161 COTTER | ICS
LC | 126110810 | 016/335 | T2 WV KILARC-DESCHUTES 16/335 INS DAMP | TABLEMTN | ETL.7300.INSL.NCER | 2023-05-11 | 2023-05-11 | 2024-04-07 | On-time | 2024-05-10 | 33 | 2024-05-11 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46053969 | T2 WV KILARC-DESCHUTES 16/335 INS DAMP | ICW
LC | 126111064 | 042/171 | T2 DI DIABLO MIDWAY#2 42/171 RPR INSS | PISMOBCH | ETL.5970.INSL.NCER | 2023-05-11 | 2023-05-11 | 2024-03-27 | On-time | 2024-05-10 | 44 | 2024-05-11 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46078971 | T2 DI DIABLO MIDWAY#2 42/171 RPR INSS | ICS
LC | 126126849 | 001/006 | T2 DI TRINITY-MAPLE CREEK 1/6 RPR CRSW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46070695 | T2 DI TRINITY-MAPLE CREEK 1/6 RPR CRSW | ICW
LC | 126111155 | 027/134 | T2 EI RND MTN-TBL MTN#1 27/134 UNBURY | TABLEMTN | ETL.6060.TOWR | 2023-05-11 | 2023-05-11 | 2024-02-14 | On-time | 2024-05-10 | 86 | 2024-05-11 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Steel | Repair | 46057517 | T2 EI RND MTN-TBL MTN#1 27/134 UNBURY | ICS
LC | 126126912 | 003/010 | T2 DI TRNTY-MPL CRK 3/10 GO95 | EUREKA | ETL.8170.POLE.WOOD | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35496184 | T2 DI TRNTY-MPL CRK 3/10 GO95 | 93G
LC | 126126947 | 012/007 | T2 DI EXCHEQUER-MARIPOSA 12/07 RPL ANCW | FRESNO | ETL.8640.POLE.NWOD | 2023-05-14 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35506436 | T2 DI EXCHEQUER-MARIPOSA 12/07 RPL ANCW | 93E
LC | 126111232 | 011/267 | T2 EI SALINAS-LAURELES 11/267 RPL INSW | MOSSLNDG | ETL.7930.INSL | 2023-05-11 | 2023-05-11 | 2024-03-08 | On-time | 2024-05-10 | 63 | 2024-05-11 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081160 | T2 EI SALINAS-LAURELES 11/267 RPL INSW | ICW
LC | 126111273 | 011/267 | T2NT EI SALINAS-LAURELES 011/267 RMV VEG | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-11 | 2023-05-11 | 2024-05-10 | On-time | 2024-05-10 | 0 | 2024-05-11 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126111299 | 027/133 | T2 EI ROND MTN-TBL MTN #2 27/133 BNT STL | TABLEMTN | ETL.6070.TOWR | 2023-05-11 | 2023-05-11 | 2024-04-30 | On-time | 2024-05-10 | 10 | 2024-05-11 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46057543 | T2 EI ROND MTN-TBL MTN #2 27/133 BNT STL | ICQ
LC | 126129180 | :001/016 | T2 EI CARIBOU #2 :001/016 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2023-11-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527042 | T2 EI CARIBOU #2 :001/015 RPL STRW | 70Y
LC | 126111310 | 027/133 | T2 EI RND MTN-TBL MTN #2 27/133 RPR GYWS | TABLEMTN | ETL.6070.TOWR | 2023-05-11 | 2023-05-11 | 2024-04-30 | On-time | 2024-05-10 | 10 | 2024-05-11 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46057542 | T2 EI RND MTN-TBL MTN #2 27/133 RPR GYWS | ICS
LC | 126129203 | :001/015 | T2 EI CARIBOU #2 :001/015 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2023-11-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527042 | T2 EI CARIBOU #2 :001/015 RPL STRW | 70Y
LC | 126111750 | 081/413 | T2 EI MALN-RND MTN #2 81/413 RPR SHIELDS | TABLEMTN | ETL.6020.TOWR | 2023-05-11 | 2023-05-11 | 2024-01-12 | On-time | 2024-05-10 | 119 | 2024-05-11 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46060968 | T2 EI MALN-RND MTN #2 81/413 RPR SHIELDS | ICS
LC | 126129222 | 005/086 | T2 EI PIT #1-HAT CRK #2-BRNY 5/86 COTTER | TABLEMTN | ETL.7040.INSL.NCER | 2023-05-15 | 2023-05-13 | 2024-05-15 | Late | 2024-05-12 | -3 | 2024-05-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46054028 | T2 EI PIT #1-HAT CRK #2-BRNY 5/86 COTTER | ICW
LC | 126111851 | 067/281 | T2 EI ROND MTN-TBL MTN #2 67/281 BNT STL | TABLEMTN | ETL.6070.TOWR | 2023-05-11 | 2023-05-11 | 2024-01-23 | On-time | 2024-05-10 | 108 | 2024-05-11 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072139 | T2 EI ROND MTN-TBL MTN #2 67/281 BNT STL | ICQ
LC | 126111852 | 067/281 | T2 EI RND MTN-TBL MTN #2 67/281 RPR GYWS | TABLEMTN | ETL.6070.TOWR | 2023-05-11 | 2023-05-11 | 2024-01-23 | On-time | 2024-05-10 | 108 | 2024-05-11 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Replace | 46072160 | T2 EI RND MTN-TBL MTN #2 67/281 RPR GYWS | ICS
LC | 126129228 | 024/005 | T2 EI MNDCNO-WLLTS-FRT BRG 24/5 RPL ANCW | WILLITS | ETL.7550.POLE.WOOD | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2024-05-13 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35521378 | T2 MNDCNO-WLITS-FRT BRG 2/13 RPL ANCW | 93E
LC | 126129233 | 008/091A | T2 EI DRUM-SUMMIT #2 8/91A COMPLETE | SACTO | ETL.1450.POLE.NWOD | 2023-05-15 | 2023-05-13 | 2024-05-17 | Late | 2024-05-12 | -5 | 2024-05-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053871 | T2 EI DRUM-SUMMIT #2 8/91A RPR GYWW | ICW
LC | 126129244 | 031/273 | T2 EI CASCADE-COTONWOD 31/273L RPL POLE | TABLEMTN | ETL.1240.POLE.WDPS | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2024-05-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518946 | T2 EI CASCADE-COTONWOD 31/273L RPL POLE | 70Y
LC | 126129247 | 040/262A | T2 EI TRINITY-CTTNWD 40/262A COMPLETE | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-15 | 2023-05-13 | 2024-05-28 | Late | 2024-05-12 | -16 | 2023-11-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062558 | T2 EI TRINITY-CTTNWD 040/262A RPR GYWW | ICW
LC | 126129264 | 086/004A | T2 EI HUMBOLDT-TRINITY 86/4A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2023-08-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096239 | T2 EI HUMBOLDT-TRINITY 86/4C RPR GYWW | ICW
LC | 126112152 | X009/039 | T2 DI MORRO BAY-DIABLO X09/39 RPL INSS | PISMOBCH | ETL.5260.INSL | 2023-05-11 | 2023-05-11 | 2024-05-03 | On-time | 2024-05-10 | 7 | 2024-05-11 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513944 | T2 DI MORRO BAY-DIABLO X008/037 RPL INSS | 93K
LC | 126114189 | 045/184 | T2 DI DIABLO-MIDWAY #3 45/184 COTTER | PISMOBCH | ETL.5980.INSL.NCER | 2023-05-12 | 2023-05-11 | 2024-03-22 | On-time | 2024-05-10 | 49 | 2024-05-11 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46073680 | T2 DI DIABLO-MIDWAY #3 45/184 COTTER | ICS
LC | 126121365 | 013/051 | T2 DI DIABLO-MIDWAY #3 13/51 BENT STEEL | PISMOBCH | ETL.5980.TOWR | 2023-05-12 | 2023-05-11 | 2024-02-22 | On-time | 2024-05-10 | 78 | 2024-05-11 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46051308 | T2 DI DIABLO-MIDWAY #3 13/51 BENT STEEL | ICQ
LC | 126129071 | 044/183 | DI T2 DIABLO-MIDWAY#2 44/183 RPR INSS | PISMOBCH | ETL.5970.INSL.NCER | 2023-05-15 | 2023-05-11 | 2023-11-16 | On-time | 2024-05-10 | 176 | 2024-05-11 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46060981 | DI T2 DIABLO-MIDWAY#2 44/183 RPR INSS | ICS
LC | 126129310 | 005/084 | T2 EI PT #1-HT CRK #2-BRNY 5/84 RPR WDPK | TABLEMTN | ETL.7040.POLE.WOOD | 2023-05-15 | 2023-05-13 | 2024-05-15 | Late | 2024-05-12 | -3 | 2024-05-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46054027 | T2 EI PT #1-HT CRK #2-BRNY 5/84 RPR WDPK | ICW
LC | 126156646 | 016/344 | T2 DI VOLTA-DESCHUTES 16/344 RPR STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-17 | 2023-05-11 | 2024-04-29 | On-time | 2024-05-10 | 11 | 2024-05-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46053970 | T2 DI VOLTA-DESCHUTES 16/344 RPR STRW | ICW
LC | 126129315 | 024/003 | T2 EI MDCNO-WLTS-FRT BRG 24/3 CANCEL | WILLITS | ETL.7550.INSL.CERA | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2024-05-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46227563 | T2NT EI MDCNO-WLTS-FRT BRG 24/3 RPR INSW | ICW
LC | 126156760 | 018/393 | T2 DI VLTA-DESCHTES 18/393 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-17 | 2023-05-11 | 2024-02-06 | On-time | 2024-05-10 | 94 | 2024-05-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485605 | T2 DI VLTA DSHUTS 16/343 RPL STRW | 70Y
LC | 126129325 | 031/273 | T2 EI CASCADE-COTONWOD 31/273R RPL POLE | TABLEMTN | ETL.1240.POLE.WDPS | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2024-05-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518946 | T2 EI CASCADE-COTONWOD 31/273L RPL POLE | 70Y
LC | 126129337 | :002/005 | T2 EI CARIBOU #2 :2/5 RPL ANCW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2024-05-13 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35515752 | T2 EI CARIBOU #2 :002/005 RPL ANCW | 93E
LC | 126156788 | 018/416 | T2 DI VOLTA-DESCHUTES 18/416 RPR CNDW | TABLEMTN | ETL.8290.INSL.NCER | 2023-05-17 | 2023-05-11 | 2024-04-15 | On-time | 2024-05-10 | 25 | 2024-05-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46053973 | T2 DI VOLTA-DESCHUTES 18/416 RPR CNDW | ICW
LC | 126129382 | 024/008 | T2 EI MNDCNO-WLLTS-FRT BRG 24/8 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2024-05-13 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35521532 | T2 EI MNDCIN-WLITS-FRT BRG 23/8 RPL INSW | 93I
LC | 126156811 | 016/348 | T2 DI VOLTA-DESCHUTES 16/348 RPL INSW | TABLEMTN | ETL.8290.INSL | 2023-05-17 | 2023-05-11 | 2024-02-12 | On-time | 2024-05-10 | 88 | 2024-05-11 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35485601 | T2 DI VLTA-DSCHTS 011/233 RPL INSW | 93I
LC | 126129418 | 024/003 | T2 EI MNDCNO-WLTS-FRT BRG 24/3 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2023-11-13 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35521532 | T2 EI MNDCIN-WLITS-FRT BRG 23/8 RPL INSW | 93I
LC | 126129421 | 016/319 | T2 EI SALINAS-LAURELES 016/319 RPL ANCW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-15 | 2023-05-13 | 2024-06-20 | Late | 2024-05-12 | -39 | 2024-05-13 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35556830 | T2 EI SALINAS-LAURELES 016/319 RPL ANCW | 93E
LC | 126156816 | 019/421 | T2 DI VOLTA-DESCHUTES19/421 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-17 | 2023-05-11 | 2024-02-06 | On-time | 2024-05-10 | 94 | 2024-05-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485605 | T2 DI VLTA DSHUTS 16/343 RPL STRW | 70Y
LC | 126129435 | 057/006 | T2 EI FORT ROSS-GUALALA 57/06 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2024-05-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46073720 | T2 EI FORT ROSS-GUALALA 57/06 RPR INSW | ICW
LC | 126156840 | 011/244 | T2 DI VOLTA-DESCHUTES 011/244 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-17 | 2023-05-11 | 2024-02-27 | On-time | 2024-05-10 | 73 | 2024-05-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485602 | T2 DI VOLTA-DESCH 9/197 RPL POLE | 70Y
LC | 126156941 | 016/355 | T2 DI VOLTA-DESCHUTES 16/355 RPR STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-17 | 2023-05-11 | 2024-04-25 | On-time | 2024-05-10 | 15 | 2024-05-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46053971 | T2 DI VOLTA-DESCHUTES 16/355 RPR STRW | ICW
LC | 126129463 | 086/004B | T2 EI HUMBOLDT-TRINITY 86/4B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2023-08-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096239 | T2 EI HUMBOLDT-TRINITY 86/4C RPR GYWW | ICW
LC | 126129466 | 008/092C | T2 EI DRUM-SUMMIT #2 8/92C COMPLETE | SACTO | ETL.1450.POLE.NWOD | 2023-05-15 | 2023-05-13 | 2024-05-17 | Late | 2024-05-12 | -5 | 2024-05-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053872 | T2 EI DRUM-SUMMIT #2 8/92C RPR GYWW | ICW
LC | 126129481 | 024/007 | T2 EI MNDCNO-WLLTS-FRT BRG 24/7 RPL INSW | WILLITS | ETL.7550.INSL.CERA | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2024-05-13 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35521532 | T2 EI MNDCIN-WLITS-FRT BRG 23/8 RPL INSW | 93I
LC | 126156972 | 017/382 | T2 DI VLTA-DSCHTS 17/382 RPL POLE | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-17 | 2023-05-11 | 2024-04-16 | On-time | 2024-05-10 | 24 | 2024-05-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485518 | T2 DI VLTA-DSCHTS 17/382 RPL POLE | 70Y
LC | 126129485 | 056/005 | T2 EI FORT ROSS-GUALALA 56/05 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2024-05-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46073479 | T2 EI FORT ROSS-GUALALA 56/05 RPR INSW | ICW
LC | 126129487 | 040/262B | T2 EI TRINITY-CTTNWD 040/262B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-15 | 2023-05-13 | 2024-05-28 | Late | 2024-05-12 | -16 | 2023-11-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062559 | T2 EI TRINITY-CTTNWD 040/262B RPR GYWW | ICW
LC | 126129498 | 056/006 | T2 EI FORT ROSS-GUALALA 56/6 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2024-05-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518743 | T2 EI FORT ROSS-GUALALA 52/01 RPL POLE | 70Y
LC | 126156974 | 011/233 | T2 DI VLTA-DSCHTS 011/233 RPL INSW | TABLEMTN | ETL.8290.INSL.NCER | 2023-05-17 | 2023-05-11 | 2024-02-22 | On-time | 2024-05-10 | 78 | 2024-05-11 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35485601 | T2 DI VLTA-DSCHTS 011/233 RPL INSW | 93I
LC | 126129519 | 017/324 | T2 EI SALINAS-LAURELES 17/324 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2024-05-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35507088 | T2 EI SALINAS-LAURELES 017/324 RPL STRW | 70Y
LC | 126156985 | 017/373 | T2 DI VOLTA-DESCHUTES 17/373 RPR CNDW | TABLEMTN | ETL.8290.INSL | 2023-05-17 | 2023-05-11 | 2024-04-17 | On-time | 2024-05-10 | 23 | 2024-05-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46053972 | T2 DI VOLTA-DESCHUTES 17/373 RPR CNDW | ICW
LC | 126129521 | 041/348 | T2 EI PIT #1-CTTNWD 41/348 BENT STEEL | TABLEMTN | ETL.5390.TOWR | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2024-05-13 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46255045 | T2 EI PIT #1-COTTONWOOD 41/348 BENT STL | ICQ
LC | 126129538 | 041/351 | T2 EI PIT #1-COTTONWOD 41/351 BNT STEEL | TABLEMTN | ETL.5390.TOWR | 2023-05-15 | 2023-05-13 |  | Late | 2024-05-12 |  | 2024-05-13 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46250422 | T2 EI PIT #1-COTTONWOOD 41/351 BENT STL | ICQ
LC | 126129797 | 016/317B | T2 EI SALINAS-LAURELES 16/317B RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35507085 | T2 EI SALINAS-LAURELES 016/317A RPL STRW | 70Y
LC | 126129866 | 016/317C | T2 EI SALINAS-LAURELES 16/317C RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507085 | T2 EI SALINAS-LAURELES 016/317A RPL STRW | 70Y
LC | 126129871 | 032/222C | T2 EI TRINITY-COTTON 32/222C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-15 | 2023-05-15 | 2024-05-29 | Late | 2024-05-14 | -15 | 2024-05-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076616 | T2 EI TRINITY-COTTON 32/222C RPR GYWW | ICW
LC | 126130010 | 016/317A | T2 EI SALINAS-LAURELES 16/317A RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35507085 | T2 EI SALINAS-LAURELES 016/317A RPL STRW | 70Y
LC | 126157003 | 014/309 | T2 DI VOLTA-DESCHUTES 14/309 RPL GYWW | TABLEMTN | ETL.8290.POLE.NWOD | 2023-05-17 | 2023-05-11 | 2024-01-23 | On-time | 2024-05-10 | 108 | 2024-05-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053968 | T2 DI VOLTA-DESCHUTES 14/309 RPL GYWW | ICW
LC | 126130240 | 032/222B | T2 EI TRINITY-COTTON 32/222B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-15 | 2023-05-15 | 2024-05-29 | Late | 2024-05-14 | -15 | 2023-11-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062591 | T2 EI TRINITY-COTTON 32/222B RPR GYWW | ICW
LC | 126130256 | ;000/009 | T2 DI CARIBOU #2 ;000/009 RPR GYWW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-15 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053906 | DI T2 CARIBOU#2 000/009 RPR GYWW | ICW
LC | 126157030 | 016/351 | T2 DI VOLTA-DESCHUTES 16/351 RPL STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-17 | 2023-05-11 | 2024-02-12 | On-time | 2024-05-10 | 88 | 2024-05-11 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485605 | T2 DI VLTA DSHUTS 16/343 RPL STRW | 70Y
LC | 126130416 | :002/009 | T2 EI CARIBOU #2 :2/9 COTTER | TABLEMTN | ETL.6280.INSL.CERA | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46062583 | T2 EI CARIBOU #2 :002/009 COTTER | ICW
LC | 126158722 | 019/432 | T2 DI VLTA DSHUTS 19/432 RPR STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-18 | 2023-05-11 | 2024-04-15 | On-time | 2024-05-10 | 25 | 2024-05-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46053974 | T2 DI VLTA DSHUTS 19/432 RPR STRW | ICW
LC | 126130606 | 018/005 | T2 WV KONOCTI-MIDDLETOWN 18/5 RPL INSW | WILLITS | ETL.6380.INSL.NCER | 2023-05-15 | 2023-05-15 | 2024-06-25 | Late | 2024-05-14 | -42 | 2024-05-15 | 508 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31620564 | T2 DI KONOCTI MIDDLETOWN 13/2 RPL INSW | 93I
LC | 126130705 | ;000/027 | T2 EI CARIBOU #2 ;000/027 RPR JUMP | TABLEMTN | ETL.6280.INSL.CERA | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46062585 | T2 EI CARIBOU #2 ;000/027 RPR JUMP | ICW
LC | 126159338 | 007/161 | T2 DI VLTA DSHUTS 07/161 RPR CNDW | TABLEMTN | ETL.8290.INSL.NCER | 2023-05-18 | 2023-05-11 | 2024-02-27 | On-time | 2024-05-10 | 73 | 2024-05-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46063199 | T2 DI VLTA DSHUTS 07/161 RPR CNDW | ICW
LC | 126160319 | 012/263 | T2 DI VOLTA-DESCHUTES 012/263 RPR GYWW | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-18 | 2023-05-11 | 2024-01-23 | On-time | 2024-05-10 | 108 | 2024-05-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053965 | T2 DI VOLTA-DESCHUTES 012/263 RPR GYWW | ICW
LC | 126173247 | 014/302 | T2 DI VOLTA-DESCHUTES 14/302 RPR STRW | TABLEMTN | ETL.8290.POLE.WOOD | 2023-05-19 | 2023-05-11 | 2024-01-23 | On-time | 2024-05-10 | 108 | 2024-05-11 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46053967 | T2 DI VOLTA-DESCHUTES 14/302 RPR STRW | ICW
LC | 126131578 | 081/573 | T2 EI BRDGVL-CTNWD 81/573 RPL INSS | EUREKA | ETL.1110.INSL.NCER | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509119 | T2 DI BRDGVL-CTNWD RPL INSS 6 TWRS | 93K
LC | 126131618 | 072/296 | T2 EI ROND MTN-TBL MTN #1 72/296 BNT STL | TABLEMTN | ETL.6060.TOWR | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072172 | T2 EI ROND MTN-TBL MTN #1 72/296 BNT STL | ICQ
LC | 126114795 | 012/269 | T2 EI SALINAS-LAURELES 012/269 RPR INSW | MOSSLNDG | ETL.7930.INSL.NCER | 2023-05-12 | 2023-05-12 | 2024-03-08 | On-time | 2024-05-11 | 64 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081161 | T2 EI SALINAS-LAURELES 012/269 RPR INSW | ICW
LC | 126132047 | 081/572 | T2 EI BRDGEVL-CTTNWD 81/572R RPL ANCHOR | EUREKA | ETL.1110.POLE.STPS | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35505107 | T2 EI BRDGEVL-CTTNWD 81/572R RPL ANCHOR | 93E
LC | 126115382 | 015/320 | T2 WV KILARC-DESCHUTES 15/320 INS DMPW | TABLEMTN | ETL.7300.INSL.NCER | 2023-05-12 | 2023-05-12 | 2024-04-05 | On-time | 2024-05-11 | 36 | 2024-05-12 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46054022 | T2 WV KILARC-DESCHUTES 15/320 INS DMPW | ICW
LC | 126132076 | 081/572 | T2 EI BRDGEVL-CTTNWD 81/572L RPL ANCHOR | EUREKA | ETL.1110.POLE.STPS | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35505107 | T2 EI BRDGEVL-CTTNWD 81/572R RPL ANCHOR | 93E
LC | 126132123 | :007/062 | T2 EI PIT #3-PIT #1 :7/62 RPL INSS | TABLEMTN | ETL.5400.INSL.NCER | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509001 | T2 EI PIT #3-PIT #1 :007/062 RPL INSS | 93K
LC | 126132166 | 013/009 | T2 MENDOCNO-WLLTS-FRT BRGG 13/9 RPR SWTC | WILLITS | ETL.7550.POLE.WOOD | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 46214097 | T2 MENDOCNO-WLLTS-FRT BRGG 13/9 RPR POLE | ICW
LC | 126132190 | 000/010 | T2 EI CSCD-BNTN-DSCHTS 0/10 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35521345 | T2 EI CSCD-BNTN-DSCHTS 0/010 RPL STRW | 70Y
LC | 126115838 | 015/325 | T2 WV KILARC-DESCHUTES 15/325 INS DMPW | TABLEMTN | ETL.7300.INSL.NCER | 2023-05-12 | 2023-05-12 | 2024-04-05 | On-time | 2024-05-11 | 36 | 2024-05-12 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46054023 | T2 WV KILARC-DESCHUTES 15/325 INS DMPW | ICW
LC | 126116302 | 034/151 | T2 EI MOSS LANDNG-LS BNS 34/151 RPR ANCS | MOSSLNDG | ETL.6040.TOWR | 2023-05-12 | 2023-05-12 | 2023-06-22 | On-time | 2024-05-11 | 324 | 2023-11-12 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45857036 | T2 EI MOSS LANDNG-LS BNS 34/151 RPR ANCS | ICS
LC | 126117145 | 015/327 | T2 WV KILARC-DESCHUTES 15/327 INS DMPW | TABLEMTN | ETL.7300.INSL.NCER | 2023-05-12 | 2023-05-12 | 2024-04-05 | On-time | 2024-05-11 | 36 | 2024-05-12 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46054025 | T2 WV KILARC-DESCHUTES 15/327 INS DMPW | ICW
LC | 126117614 | 015/329 | T2 WV KILARC-DESCHUTES 15/329 INS DMPW | TABLEMTN | ETL.7300.INSL.NCER | 2023-05-12 | 2023-05-12 | 2024-04-05 | On-time | 2024-05-11 | 36 | 2024-05-12 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46054026 | T2 WV KILARC-DESCHUTES 15/329 INS DMPW | ICW
LC | 126117636 | 035/154 | T2 EI MOSS LANDING-LOS BNS 35/154 COTTER | MOSSLNDG | ETL.6040.INSL.NCER | 2023-05-12 | 2023-05-12 | 2024-02-22 | On-time | 2024-05-11 | 79 | 2024-05-12 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46073681 | T2 EI MOSS LANDING-LOS BNS 35/154 COTTER | ICS
LC | 126117690 | 024/207 | T2 EI CSCD-CTNWD 024/207 RPR GYWW | TABLEMTN | ETL.1240.POLE.NWOD | 2023-05-12 | 2023-05-12 | 2024-04-12 | On-time | 2024-05-11 | 29 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46053981 | T2 EI CSCD-CTNWD 024/207 RPR GYWW | ICW
LC | 126117935 | 052/467 | T2NT EI PIT #1-COTTONWD 52/467 BNT STEEL | TABLEMTN | ETL.5390.TOWR | 2023-05-12 | 2023-05-12 | 2023-11-22 | On-time | 2024-05-11 | 171 | 2024-05-12 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46057515 | T2NT EI PIT #1-COTTONWD 52/467 BNT STEEL | ICQ
LC | 126117957 | 024/193A | T2 EI MDDLE FRK-GLD HLL 24/193A RPR GYWW | SACTO | ETL.5140.POLE.NWOD | 2023-05-12 | 2023-05-12 | 2023-06-13 | On-time | 2024-05-11 | 333 | 2023-11-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45844382 | T2 EI MDDLE FRK-GLD HLL 24/193A RPR GYWW | ICW
LC | 126133634 | ;000/021 | T2 EI CARIBOU #2 ;000/021 REFRAME | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2023-11-15 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35515861 | T2 EI CARIBOU #2 ;000/021 REFRAME | 93E
LC | 126118099 | 024/193B | T2 EI MDDLE FRK-GLD HLL 24/19B RPR GYWW | SACTO | ETL.5140.POLE.NWOD | 2023-05-12 | 2023-05-12 | 2023-06-13 | On-time | 2024-05-11 | 333 | 2023-11-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45844383 | T2 EI MDDLE FRK-GLD HLL 24/19B RPR GYWW | ICW
LC | 126118196 | 024/193C | T2 EI MDDLE FRK-GLD HLL 24/193C RPR GYWW | SACTO | ETL.5140.POLE.NWOD | 2023-05-12 | 2023-05-12 | 2023-06-13 | On-time | 2024-05-11 | 333 | 2023-08-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45844384 | T2 EI MDDLE FRK-GLD HLL 24/193C RPR GYWW | ICW
LC | 126133805 | 072/294 | T2 EI RND MTN-TBL MTN#2 72/294 RPR HRDT | TABLEMTN | ETL.6070.TOWR | 2023-05-15 | 2023-05-15 | 2024-06-25 | Late | 2024-05-14 | -42 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46072169 | T2 EI RND MTN-TBL MTN#2 72/294 RPR HRDT | ICQ
LC | 126134375 | 084/592 | T2 EI BRDGVLLE-CTTNWD 84/592R RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505113 | T2 EI BRIDGEV-COTTONWOOD 84/592 RPL POLE | 70Y
LC | 126134404 | 084/592 | T2 EI BRDGVLLE-CTTNWD 84/592L RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505113 | T2 EI BRIDGEV-COTTONWOOD 84/592 RPL POLE | 70Y
LC | 126134507 | :006/004 | T2 EI CARIBOU #2 :006/004 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527045 | T2 EI CARIBOU #2 :006/004 RPL STRW | 70Y
LC | 126134556 | 002/064 | T2 WV PLACER-DEL MAR 2/64 RMV ENCROACH | SACTO | ETL.7800.POLE.NWOD | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 931 | TLS | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Encroachment | Right of Way | Remove
LC | 126118428 | 013/167 | T2 KESWICK-TRINITY 13/167 RPR HARDWARE | TABLEMTN | ETL.7270.INSL.NCER | 2023-05-12 | 2023-05-12 | 2024-04-12 | On-time | 2024-05-11 | 29 | 2024-05-12 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46054021 | T2 KESWICK-TRINITY 13/167 RPR HARDWARE | ICW
LC | 126134683 | 084/594 | T2 EI BRDGVLLE-CTTNWD 84/594 RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505113 | T2 EI BRIDGEV-COTTONWOOD 84/592 RPL POLE | 70Y
LC | 126134686 | 084/594 | T2 EI BRDGVLLE-COTTNWD 84/594 RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505113 | T2 EI BRIDGEV-COTTONWOOD 84/592 RPL POLE | 70Y
LC | 126118895 | 012/263 | T2 WV KILARC-DESCHUTES 12/263 INS DMPW | TABLEMTN | ETL.7300.INSL | 2023-05-12 | 2023-05-12 | 2024-04-04 | On-time | 2024-05-11 | 37 | 2024-05-12 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46053979 | T2 WV KILARC-DESCHUTES 12/263 INS DMPW | ICW
LC | 126119092 | 005/003 | T2 EI LAYTONVILLE-COVELO 5/3L RPR GYWW | WILLITS | ETL.7390.POLE.STPS | 2023-05-12 | 2023-05-12 | 2024-05-10 | On-time | 2024-05-11 | 1 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46219458 | T2 EI LAYTONVILLE-COVELO 5/3L RPR GYWW | ICW
LC | 126134986 | 009/177 | T2 EI CARIBOU-WESTWOOD 9/177 RPR STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062587 | T2 EI CARIBOU-WESTWOOD 9/177 RPR STRW | ICW
LC | 126119165 | 005/003 | T2 EI LAYTONVILLE-COVELO 5/3C RPR GYWW | WILLITS | ETL.7390.POLE.STPS | 2023-05-12 | 2023-05-12 | 2024-05-10 | On-time | 2024-05-11 | 1 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46219457 | T2 EI LAYTONVILLE-COVELO 5/3C RPR GYWW | ICW
LC | 126119169 | 012/266 | T2 WV KILARC-DESCHUTES 12/266 INS DMPW | TABLEMTN | ETL.7300.INSL.NCER | 2023-05-12 | 2023-05-12 | 2024-04-04 | On-time | 2024-05-11 | 37 | 2024-05-12 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46054020 | T2 WV KILARC-DESCHUTES 12/266 INS DMPW | ICW
LC | 126119285 | 005/003 | T2 EI LAYTONVILLE-COVELO 5/3R RPR GYWW | WILLITS | ETL.7390.POLE.STPS | 2023-05-12 | 2023-05-12 | 2024-05-10 | On-time | 2024-05-11 | 1 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46219456 | T2 EI LAYTONVILLE-COVELO 5/3R RPR GYWW | ICW
LC | 126119404 | 042/364 | T2 EI ROUND MTN-COTTNWD #3 42/364 MASTIC | TABLEMTN | ETL.5650.TOWR | 2023-05-12 | 2023-05-12 | 2024-01-02 | On-time | 2024-05-11 | 130 | 2024-05-12 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46057516 | T2 EI ROUND MTN-COTTNWD #3 42/364 MASTIC | ICQ
LC | 126119727 | 005/094 | T2 WV COLEMAN-RED BLUFF 5/094 REFRAME | TABLEMTN | ETL.6440.POLE.WOOD | 2023-05-12 | 2023-05-12 | 2024-03-20 | On-time | 2024-05-11 | 52 | 2024-05-12 | 637 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31629251 | T2 DI COLEMAN-RED BLUFF 005/094 RPL CRSW | 93E
LC | 126120004 | 005/110 | T2 EI CTONWOOD-RED BLUFF 05/110 RPR PL | TABLEMTN | ETL.6660.POLE.WOOD | 2023-05-12 | 2023-05-12 | 2024-04-09 | On-time | 2024-05-11 | 32 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46053982 | T2 EI CTONWOOD-RED BLUFF 05/110 RPR PL | ICW
LC | 126120168 | 012/279 | T2 EI SALINAS-LAURELES 012/279 RPR INSW | MOSSLNDG | ETL.7930.INSL | 2023-05-12 | 2023-05-12 | 2024-02-20 | On-time | 2024-05-11 | 81 | 2024-05-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081163 | T2 EI SALINAS-LAURELES 012/279 RPR INSW | ICW
LC | 126120367 | 002/058 | T2 WV KILARC-DESCHUTES 2/58 INS DMPW | TABLEMTN | ETL.7300.INSL.NCER | 2023-05-12 | 2023-05-12 | 2024-03-18 | On-time | 2024-05-11 | 54 | 2024-05-12 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46053978 | T2 WV KILARC-DESCHUTES 2/58 INS DMPW | ICW
LC | 126120446 | 036/159 | T2 EI MSS LANDING-LS BNS 36/159 RPR ANCS | MOSSLNDG | ETL.6040.TOWR | 2023-05-12 | 2023-05-12 | 2023-06-22 | On-time | 2024-05-11 | 324 | 2023-11-12 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45857037 | T2 EI MSS LANDING-LS BNS 36/159 RPR ANCS | ICS
LC | 126120715 | 042/360 | T2 EI PIT #1-COTTONWOOD 42/360 MASTIC | TABLEMTN | ETL.5390.TOWR | 2023-05-12 | 2023-05-12 | 2024-02-13 | On-time | 2024-05-11 | 88 | 2024-05-12 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46057514 | T2 EI PIT #1-COTTONWOOD 42/360 MASTIC | ICQ
LC | 126120747 | 012/281 | T2 EI SALINAS-LAURELES 012/281 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-12 | 2023-05-12 | 2024-02-21 | On-time | 2024-05-11 | 80 | 2024-05-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35507139 | T2 EI SALINAS-LAURELES 012/281 RPL STRW | 70Y
LC | 126135558 | 048/005 | T2 EI TRNTY-MPL CRK 048/05 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172257 | T2 EI TRNTY-MPL CRK 048/05 RPR GYWW | ICW
LC | 126135584 | 047/010 | T2 EI TRNTY-MPL CRK 47/10 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-15 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172248 | T2 EI TRNTY-MPL CRK 47/10 RPR GYWW | ICW
LC | 126136355 | 051/003 | T2 DI TRINITY-MAPLE CREEK 51/3 COTTER | EUREKA | ETL.8170.INSL.NCER | 2023-05-16 | 2023-05-09 |  | Late | 2024-05-08 |  | 2023-11-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45770301 | T2 DI TRINITY-MAPLE CREEK 51/3 COTTER | ICW
LC | 126136587 | 000/015 | T2 EI CSCD-BNTN-DSCHTS 0/15 RPR STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2024-05-21 | Late | 2024-05-15 | -6 | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062642 | T2 EI CSCD-BNTN-DSCHTS 0/015 RPR STRW | ICW
LC | 126121160 | 010/120 | T2 WV COLGATE-SMRTVL #2 10/120 INS DMPW | SACTO | ETL.6520.INSL.NCER | 2023-05-12 | 2023-05-12 | 2024-02-21 | On-time | 2024-05-11 | 80 | 2024-05-12 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46053996 | T2 WV COLGATE-SMRTVL #2 10/120 INS DMPW | ICW
LC | 126121279 | 020/092 | T2 EI MORRO BAY-MESA 20/92 RPR FOND | PISMOBCH | ETL.5290.TOWR | 2023-05-12 | 2023-05-12 | 2024-02-21 | On-time | 2024-05-11 | 80 | 2024-05-12 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46051310 | T2 EI MORRO BAY-MESA 20/92 RPR FOND | ICQ
LC | 126136992 | 009/176 | T2 EI CARIBOU-WESTWOOD 9/176 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35551695 | T2 EI CARIBOU-WESTWOOD 9/176 RPL STRW | 70Y
LC | 126122199 | 030/122 | T2 DI DIABLO-MIDWY #2 30/122 RPR INSS | PISMOBCH | ETL.5970.INSL.NCER | 2023-05-13 | 2023-05-12 | 2024-03-27 | On-time | 2024-05-11 | 45 | 2024-05-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46214029 | T2 DI DIABLO-MIDWY #2 30/122 RPR INSS | ICS
LC | 126175107 | 013/101 | T2 DI CARIBOU-TBL MTN 13/101 BENT STEEL | TABLEMTN | ETL.4440.TOWR | 2023-05-19 | 2023-05-12 | 2024-04-12 | On-time | 2024-05-11 | 29 | 2024-05-12 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072163 | T2 DI CARIBOU-TBL MTN 13/101 BENT STEEL | ICQ
LC | 126137864 | 003/002 | T2 EI LAURLS-OTTR 3/2 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491362 | T2 EI LAURLS-OTTR 2/9 RPL STRW | 70Y
LC | 126138242 | 002/015 | T2 EI LAURLS-OTTR 2/15 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491362 | T2 EI LAURLS-OTTR 2/9 RPL STRW | 70Y
LC | 126138408 | 013/285 | T2 EI SALINAS-LAURELES 013/285 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2024-06-17 | Late | 2024-05-15 | -33 | 2024-05-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35507017 | T2 EI SALINAS-LAURELES 013/284 RPL STRW | 70Y
LC | 126190363 | 012/093 | T2 DI CARIBOU-TBL MTN 12/93 RMV ANCHOR | TABLEMTN | ETL.4440.TOWR | 2023-05-19 | 2023-05-12 | 2024-01-19 | On-time | 2024-05-11 | 113 | 2024-05-12 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Tower | Repair | 45947735 | T2 DI CARIBOU-TBL MTN 12/93 RMV ANCHOR | ICQ
LC | 126138986 | 009/172 | T2 EI CARIBOU-WESTWOOD 9/172 RPR STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062655 | T2 EI CARIBOU-WESTWOOD 9/172 RPR STRW | ICW
LC | 126190364 | 012/093 | T2 DI CARIBOU-TBL MTN 12/93 RMV GUY | TABLEMTN | ETL.4440.TOWR | 2023-05-19 | 2023-05-12 | 2024-01-19 | On-time | 2024-05-11 | 113 | 2024-05-12 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 45947736 | T2 DI CARIBOU-TBL MTN 12/93 RMV GUY | ICQ
LC | 126139199 | 005/102 | T2 EI CARIBOU-WESTWOOD 5/102R RPR GYWW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062646 | T2 EI CARIBOU-WESTWOOD_5/102R RPR GYWW | ICW
LC | 126139225 | ;000/003 | T2 EI CARIBOU #2 ;000/003 RPL GYWW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2023-11-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46250279 | T2 EI CARIBOU #2 ;000/003 RPL GYWW | ICW
LC | 126139257 | 034/007A | T2 DI TRINITY-MAPLE CREEK 34/7A RPR CRSW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-16 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46096668 | T2 DI TRINITY-MAPLE CREEK 34/7A RPR CRSW | ICW
LC | 126192130 | 049/004 | T2 DI TRINITY-MAPLE CREEK 49/04 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-20 | 2023-05-12 | 2024-03-29 | On-time | 2024-05-11 | 43 | 2024-05-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096680 | T2 DI TRINITY-MAPLE CREEK 49/04 RPR GYWW | ICW
LC | 126193376 | 024/172 | T2 DI CARIBOU TBL MTN 24/172 COMPLETE | TABLEMTN | ETL.4440.INSL.CERA | 2023-05-20 | 2023-05-12 | 2023-06-22 | On-time | 2024-05-11 | 324 | 2024-05-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45858064 | T2 DI CARIBOU TBL MTN 24/172 COTTER | ICS
LC | 126194063 | 019/136B | T2 DI CARIBOU-TABLE MTN 19/136B RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-05-20 | 2023-05-12 | 2024-04-15 | On-time | 2024-05-11 | 26 | 2024-05-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061144 | T2 DI CARIBOU-TABLE MTN 19/136B RPR GYWS | ICS
LC | 126140618 | 017/007 | T2 EI MNDCNO-WLTS-FRT BRG 17/7 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46214140 | T2 EI MNDCNO-WLTS-FRT BRG 17/7 RPR STRW | ICW
LC | 126140641 | 017/002 | T2 EI MNDCNO-WLTS-FRT BRG 17/2 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46214099 | T2 EI MNDCNO-WLTS-FRT BRG 17/2 RPR STRW | ICW
LC | 126124669 | 041/347 | T2 EI PIT #1-COTTONWOOD 41/347 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-14 | 2023-05-13 | 2024-01-08 | On-time | 2024-05-12 | 125 | 2024-05-13 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46057510 | T2 EI PIT #1-COTTONWOOD 41/347 UNBURY | ICQ
LC | 126124742 | 032/221 | T2 EI TRINITY-COTTONWOOD 32/221 RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-14 | 2023-05-13 | 2023-07-06 | On-time | 2024-05-12 | 311 | 2023-08-13 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45805449 | T2 EI TRINITY-COTTONWOOD 32/221 RPR GYWW | ICS
LC | 126141353 | 004/083 | T2 EI CARIBOU-WESTWD 4/83 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519112 | T2 DI CARIB-WSTWD 4/78 RPL STRW | 70Y
LC | 126141519 | 027/007A | T2 DI TRINITY-MAPLE CREEK 27/7A RPR CRSW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-16 | 2023-05-09 | 2024-06-18 | Late | 2024-05-08 | -41 | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46172039 | T2 DI TRINITY-MAPLE CREEK 27/7A RPR CRSW | ICW
LC | 126124753 | 058/008 | T2 EI FORT ROSS-GUALALA 58/08 RPR GYWW | LAKEVLLE | ETL.6980.POLE.NWOD | 2023-05-14 | 2023-05-13 | 2023-08-15 | On-time | 2024-05-12 | 271 | 2023-11-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805696 | T2 EI FORT ROSS-GUALALA 58/08 RPR GYWW | ICW
LC | 126124805 | 041/350 | T2 EI PIT #1-COTTONWOOD 41/350 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-14 | 2023-05-13 | 2024-01-08 | On-time | 2024-05-12 | 125 | 2024-05-13 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46057511 | T2 EI PIT #1-COTTONWOOD 41/350 UNBURY | ICQ
LC | 126124817 | 041/352 | T2 EI PIT #1-CTTONWD 41/352 RPR GYWS | TABLEMTN | ETL.5390.TOWR | 2023-05-14 | 2023-05-13 | 2024-01-02 | On-time | 2024-05-12 | 131 | 2024-05-13 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061147 | T2 EI PIT #1-CTTONWD 41/352 RPR GYWS | ICS
LC | 126124831 | 010/205 | T2 EI CARIBOU-WESTWOOD 10/205 RPR GYWW | TABLEMTN | ETL.6300.POLE.NWOD | 2023-05-14 | 2023-05-13 | 2024-03-13 | On-time | 2024-05-12 | 60 | 2024-05-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46054031 | T2 EI CARIBOU-WESTWOOD 10/205 RPR GYWW | ICW
LC | 126124856 | 032/221 | T2 EI TRINITY-COTTONWOOD 32/221 RPL ANCW | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-14 | 2023-05-13 | 2023-07-06 | On-time | 2024-05-12 | 311 | 2023-08-13 | 637 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31646471 | T2 EI TRINITY-COTTONWOOD 32/221 RPL ANCW | 93E
LC | 126129189 | :001/009 | T2 EI CARIBOU #2 :001/009 COTTER | TABLEMTN | ETL.6280.INSL.CERA | 2023-05-15 | 2023-05-13 | 2023-07-14 | On-time | 2024-05-12 | 303 | 2023-11-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45770970 | T2 EI CARIBOU #2 :001/009 COTTER | ICW
LC | 126129204 | 032/221 | T2 EI TRINITY-COTTNWOOD 32/221C RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-15 | 2023-05-13 | 2023-07-06 | On-time | 2024-05-12 | 311 | 2023-08-13 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45805357 | T2 EI TRINITY-COTTNWOOD 32/221C RPR GYWW | ICS
LC | 126129224 | 041/353 | T2 EI PIT #1-COTTONWOOD 41/353 RPR GYWS | TABLEMTN | ETL.5390.TOWR | 2023-05-15 | 2023-05-13 | 2024-01-02 | On-time | 2024-05-12 | 131 | 2024-05-13 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061148 | T2 EI PIT #1-COTTONWOOD 41/353 RPR GYWS | ICS
LC | 126129225 | 032/221 | T2 EI TRINITY-COTTNWOOD 32/221L RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-15 | 2023-05-13 | 2023-07-06 | On-time | 2024-05-12 | 311 | 2023-08-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805359 | T2 EI TRINITY-COTTNWOOD 32/221L RPR GYWW | ICW
LC | 126129267 | 078/399 | T2 EI MALN-ROUND MTN #2 078/399 RPR ANCS | TABLEMTN | ETL.6020.TOWR | 2023-05-15 | 2023-05-13 | 2023-08-25 | On-time | 2024-05-12 | 261 | 2023-11-13 | 628 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45771602 | T2 EI MALN-ROUND MTN #2 078/399 RPR ANCT | ICS
LC | 126129288 | 042/354 | T2 EI PIT #1-COTTONWOOD 42/354 MASTIC | TABLEMTN | ETL.5390.TOWR | 2023-05-15 | 2023-05-13 | 2024-01-02 | On-time | 2024-05-12 | 131 | 2024-05-13 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46057512 | T2 EI PIT #1-COTTONWOOD 42/354 MASTIC | ICQ
LC | 126144774 | 048/014 | T2 DI TRNITY MPL CRK 48/014 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-16 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172282 | T2 DI TRNITY MPL CRK 48/014 RPR GYWW | ICW
LC | 126129299 | :014/075 | T2 EI CHC-SALINAS :14/75 COTR KEY | MOSSLNDG | ETL.2900.INSL.CERA | 2023-05-15 | 2023-05-13 | 2023-07-02 | On-time | 2024-05-12 | 315 | 2023-08-13 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45854257 | T2 EI CHC-SALINAS :14/75 COTR KEY | ICS
LC | 126129308 | :015/080 | T2 EI CHC-SALINAS :15/80 RPR ANMS | MOSSLNDG | ETL.2900.TOWR | 2023-05-15 | 2023-05-13 | 2024-03-12 | On-time | 2024-05-12 | 61 | 2024-05-13 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Animal Guard-Steel | Install | 46073683 | T2 EI CHC-SALINAS :15/80 RPR ANMS | ICS
LC | 126129313 | 016/321 | T2 EI SALINAS-LAURELES 016/321 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-15 | 2023-05-13 | 2024-02-29 | On-time | 2024-05-12 | 73 | 2024-05-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35507087 | T2 EI SALINAS-LAURELES 016/321 RPL STRW | 70Y
LC | 126129318 | 010/195 | T2 EI CARIBOU-WESTWOOD 10/195 COMPLETE | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-15 | 2023-05-13 | 2024-03-19 | On-time | 2024-05-12 | 54 | 2024-05-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46054030 | T2 EI CARIBOU-WESTWOOD 10/195 RPR STRW | ICW
LC | 126146422 | 004/082 | T2 EI CARIBOU-WESTWOOD 4/82 RPR GYWW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062645 | T2 EI CARIBOU-WESTWOOD 4/82 RPR GYWW | ICW
LC | 126146431 | 004/082 | T2 EI CARIBOU-WESTWOOD 4/82 RPL ANCW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35519111 | T2 EI CARIBOU-WESTWOOD 4/82 RPL ANCW | 93E
LC | 126129373 | :015/080 | T2 EI CHC-SALINAS :15/80 BENT STEEL | MOSSLNDG | ETL.2900.TOWR | 2023-05-15 | 2023-05-13 | 2024-03-08 | On-time | 2024-05-12 | 65 | 2024-05-13 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46073315 | T2 EI CHC-SALINAS :15/80 BENT STEEL | ICQ
LC | 126129392 | 065/469 | T2 EI BRDVLL-CTTNWD 65/469L RMV VEG | EUREKA | ETL.1110.POLE.STPS | 2023-05-15 | 2023-05-13 | 2024-04-24 | On-time | 2024-05-12 | 18 | 2024-05-13 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126129422 | 032/221 | T2 EI TRINITY-COTTNWOOD 32/221L RPL ANCW | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-15 | 2023-05-13 | 2023-07-06 | On-time | 2024-05-12 | 311 | 2023-08-13 | 637 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31646471 | T2 EI TRINITY-COTTONWOOD 32/221 RPL ANCW | 93E
LC | 126146948 | 053/004 | T2 EI FORT ROSS-GUALALA 53/04 RPL POLE | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518743 | T2 EI FORT ROSS-GUALALA 52/01 RPL POLE | 70Y
LC | 126129436 | 042/355 | T2 EI PIT #1-COTTONWOOD 42/355 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-15 | 2023-05-13 | 2024-01-02 | On-time | 2024-05-12 | 131 | 2024-05-13 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46057513 | T2 EI PIT #1-COTTONWOOD 42/355 UNBURY | ICQ
LC | 126147162 | 034/233 | T2 EI TRINITY-COTTNWOOD 34/233C RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-16 | 2023-05-16 | 2024-05-29 | Late | 2024-05-15 | -14 | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062666 | T2 EI TRINITY-COTTNWOOD 34/233C RPR GYWW | ICW
LC | 126147165 | 034/232B | T2 EI TRINITY-COTTON 34/232B RPR ANCW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46062664 | T2 EI TRINITY-COTTON 34/232B RPR ANCW | ICW
LC | 126147166 | 034/232A | T2 EI TRINITY-COTTON 34/232A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076617 | T2 EI TRINITY-COTTON 34/232A RPR GYWW | ICW
LC | 126147167 | 034/233 | T2 EI TRINITY-COTTNWOOD 34/233L RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-16 | 2023-05-16 | 2024-05-29 | Late | 2024-05-15 | -14 | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062669 | T2 EI TRINITY-COTTNWOOD 34/233L RPR GYWW | ICW
LC | 126147198 | 034/232B | T2 EI TRINITY-COTTON 34/232B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062663 | T2 EI TRINITY-COTTON 34/232B RPR GYWW | ICW
LC | 126147199 | 034/233 | T2 EI TRINITY-COTTNWOOD 34/233R RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-05-16 | 2023-05-16 | 2024-05-29 | Late | 2024-05-15 | -14 | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062667 | T2 EI TRINITY-COTTNWOOD 34/233R RPR GYWW | ICW
LC | 126147200 | 034/232C | T2 EI TRINITY-COTTON 34/232C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062665 | T2 EI TRINITY-COTTON 34/232C RPR GYWW | ICW
LC | 126147286 | 048/015 | T2 DI TRNITY MPL CRK 48/015 RPR SPLW | EUREKA | ETL.8170.INSL | 2023-05-16 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46172283 | T2 DI TRNITY MPL CRK 48/015 RPR SPLW | ICW
LC | 126129452 | 010/194 | T2 EI CARIBOU-WESTWOOD 10/194 RPR STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-15 | 2023-05-13 | 2024-03-19 | On-time | 2024-05-12 | 54 | 2024-05-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46054029 | T2 EI CARIBOU-WESTWOOD 10/194 RPR STRW | ICW
LC | 126129484 | 016/322 | T2 EI SALINAS-LAURELES 016/322 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-15 | 2023-05-13 | 2023-10-20 | On-time | 2024-05-12 | 205 | 2024-05-13 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31653831 | T2 DI SALINAS LAURELES 16/320 RPL STRW | 70Y
LC | 126147440 | 001/038 | T2 EI CSCD-BNTN-DSCHTS 1/38 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35521346 | T2 EI CSCD-BNTN-DSCHTS 1/038 RPL POLE | 70Y
LC | 126129499 | 012/089 | T2 EI GREEN VALLEY-LLAGAS 12/89 RPL INSW | MOSSLNDG | ETL.1720.INSL.CERA | 2023-05-15 | 2023-05-13 | 2024-04-10 | On-time | 2024-05-12 | 32 | 2024-05-13 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35508487 | T2 EI GREEN VALLEY-LLAGAS 12/89 RPL INSW | 93I
LC | 126147546 | 024/009 | T2 DI TRINITY-MAPLE CREEK 24/9 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-16 | 2023-05-09 |  | Late | 2024-05-08 |  | 2024-05-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503770 | T2 DI TRINITY-MAPLE CREEK 24/9 RPL POLE | 70Y
LC | 126129520 | 012/088 | T2 EI GREEN VALLEY-LLAGAS 12/88 RPR INSW | MOSSLNDG | ETL.1720.INSL.NCER | 2023-05-15 | 2023-05-13 | 2024-03-22 | On-time | 2024-05-12 | 51 | 2024-05-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081595 | T2 EI GREEN VALLEY-LLAGAS 12/88 RPR INSW | ICW
LC | 126128066 | 000/002 | T2 EI COLGATE-CHALLENGE 0/002 RPR GYWW | SACTO | ETL.6480.POLE.NWOD | 2023-05-15 | 2023-05-15 | 2024-04-08 | On-time | 2024-05-14 | 36 | 2024-05-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062586 | T2 EI COLGATE-CHALLENGE 0/002 RPR GYWW | ICW
LC | 126130145 | :015/078 | T2 EI CHC-SALINAS :15/78 RPR ANMS | MOSSLNDG | ETL.2900.TOWR | 2023-05-15 | 2023-05-15 | 2024-03-12 | On-time | 2024-05-14 | 63 | 2024-05-15 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Animal Guard-Steel | Install | 46079085 | T2 EI CHC-SALINAS :15/78 RPR ANMS | ICS
LC | 126130314 | 009/188 | T2 EI CARIBOU-WESTWOOD 9/188 RPR STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-15 | 2023-05-15 | 2024-03-18 | On-time | 2024-05-14 | 57 | 2024-05-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062588 | T2 EI CARIBOU-WESTWOOD 9/188 RPR STRW | ICW
LC | 126147921 | 007/040 | T2 EI EAGLE ROCK-CORTINA 7/40 RPL INSS | SACTO | ETL.1470.INSL.CERA | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510800 | T2 EI EAGLE ROCK-CORTINA RPL INSS 2 TWRS | 93K
LC | 126130851 | 004/098 | T2 WV CLGT-GRSS VLLY 004/098 RPR GRWW | SACTO | ETL.6490.POLE.NWOD | 2023-05-15 | 2023-05-15 | 2024-01-26 | On-time | 2024-05-14 | 109 | 2024-05-15 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 46062491 | T2 WV CLGT-GRSS VLLY 004/098 RPR GRWW | ICW
LC | 126147937 | ;002/000 | T2 EI CARIBOU #2 ;2/0 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-16 | 2023-05-16 |  | Late | 2024-05-15 |  | 2023-11-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527147 | T2 EI CARIBOU #2 ;2/0 RPL POLE | 70Y
LC | 126131268 | 072/296 | T2 EI RND MTN-TBL MTN#2 72/296 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2023-05-15 | 2023-05-15 | 2023-12-29 | On-time | 2024-05-14 | 137 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072170 | T2 EI RND MTN-TBL MTN#2 72/296 RPR STRT | ICQ
LC | 126131528 | 039/336 | T2 EI RND MTN-COTTNWD #3 39/336 RPL INSS | TABLEMTN | ETL.5650.INSL | 2023-05-15 | 2023-05-15 | 2024-04-11 | On-time | 2024-05-14 | 33 | 2024-05-15 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35512111 | T2 EI RND MTN-COTTNWD #3 39/336 RPL INSS | 93K
LC | 126131620 | 072/296 | T2 EI RND MTN-TBL MTN #1 72/296 RPR GYWT | TABLEMTN | ETL.6060.TOWR | 2023-05-15 | 2023-05-15 | 2024-01-02 | On-time | 2024-05-14 | 133 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46072173 | T2 EI RND MTN-TBL MTN #1 72/296 RPR GYWT | ICS
LC | 126147987 | 039/004 | T2 EI TRNTY-MPL CRK 039/004 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-05-16 | 2023-05-16 | 2024-06-01 | Late | 2024-05-15 | -17 | 2023-11-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172183 | T2 EI TRNTY-MPL CRK 039/004 RPR GYWW | ICW
LC | 126132302 | 035/237C | T2 EI TRINITY-CTTNWD 035/237C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-15 | 2023-05-15 | 2023-07-03 | On-time | 2024-05-14 | 316 | 2023-08-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805364 | T2 EI TRINITY-CTTNWD 035/237C RPR GYWW | ICW
LC | 126148103 | 031/223 | T2 EI CARIBOU-TABLE MTN 031/223 RPR CNDS | TABLEMTN | ETL.4440.INSL.CERA | 2023-05-16 | 2023-05-16 | 2024-06-05 | Late | 2024-05-15 | -21 | 2024-05-16 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46061164 | T2 EI CARIBOU-TABLE MTN 031/223 RPR CNDS | ICS
LC | 126132484 | 035/237B | T2 EI TRINITY-CTTNWD 035/237B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-15 | 2023-05-15 | 2023-07-03 | On-time | 2024-05-14 | 316 | 2023-08-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805367 | T2 EI TRINITY-CTTNWD 035/237B RPR GYWW | ICW
LC | 126132821 | 012/257 | T2 EI CTTNWD-RD BLFF 012/257 RPR INSW | TABLEMTN | ETL.6660.INSL.NCER | 2023-05-15 | 2023-05-15 | 2024-04-08 | On-time | 2024-05-14 | 36 | 2024-05-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46062492 | T2 EI CTTNWD-RD BLFF 012/257 RPR INSW | ICW
LC | 126133024 | 081/571 | T2 EI BRDGEVL-CTTNWD 81/571L RPR GYWW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-15 | 2023-05-15 | 2024-04-01 | On-time | 2024-05-14 | 43 | 2023-11-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805437 | T2 EI BRDGEVL-CTTNWD 81/571L REPUL GUY | ICW
LC | 126133069 | 012/258 | T2 EI CTTNWD-RD BLFF 012/258 RMV BUTT | TABLEMTN | ETL.6660.POLE.NWOD | 2023-05-15 | 2023-05-15 | 2024-05-07 | On-time | 2024-05-14 | 7 | 2024-05-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 46062493 | T2 EI CTTNWD-RD BLFF 012/258 RMV BUTT | ICW
LC | 126133405 | 008/070 | T2 WV ATASCDRO-CAYUCS 08/70 RPR JMPW | PISMOBCH | ETL.8480.INSL.NCER | 2023-05-15 | 2023-05-15 | 2024-03-12 | On-time | 2024-05-14 | 63 | 2024-05-15 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46090148 | T2 WV ATASCDRO-CAYUCS 08/70 RPR JMPW | ICW
LC | 126148855 | 077/393 | T2 EI MALIN-ROUND MTN #2 77/393 RPL ANCT | TABLEMTN | ETL.6020.TOWR | 2023-05-17 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 93Z | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Tower | Replace | 31690310 | T2 EI MALIN-ROUND MTN #2 77/393 RPL ANCT | 93Z
LC | 126148862 | 078/397 | T2 EI MALIN-ROUND MTN #2 78/397 RPL ANCT | TABLEMTN | ETL.6020.TOWR | 2023-05-17 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 93ZT | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Tower | Replace | 31680989 | T2 EI MALIN-ROUND MTN #2 RPL ANCS 3 TWRS | 93Z
LC | 126133428 | :022/115 | T2 EI CZY HRS CN SLN SL :22/115 COTTER | MOSSLNDG | ETL.2910.INSL.CERA | 2023-05-15 | 2023-05-15 | 2024-01-20 | On-time | 2024-05-14 | 115 | 2024-05-15 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46079089 | T2 EI CZY HRS CN SLN SL :22/115 COTTER | ICS
LC | 126149650 | 001/044 | T2 EI CSCD-BNTN-DSCHTS 1/44 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-17 | 2023-05-17 | 2024-05-19 | Late | 2024-05-16 | -3 | 2024-05-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521347 | T2 EI CSCD-BNTN-DSCHTS 1/44 RPL STRW | 70Y
LC | 126133549 | 035/237A | T2 EI TRINITY-CTTNWD 035/237A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-15 | 2023-05-15 | 2023-07-03 | On-time | 2024-05-14 | 316 | 2023-08-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805365 | T2 EI TRINITY-CTTNWD 035/237A RPR GYWW | ICW
LC | 126133639 | 013/293 | T2 EI SALINAS-LAURELES 013/293 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-15 | 2023-05-15 | 2024-02-23 | On-time | 2024-05-14 | 81 | 2024-05-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35507081 | T2 EI SALINAS-LAURELES 013/293 RPL STRW | 70Y
LC | 126133804 | 072/294 | T2 EI RND MTN-TBL MTN#2 72/294 RPR STRT | TABLEMTN | ETL.6070.TOWR | 2023-05-15 | 2023-05-15 | 2024-01-02 | On-time | 2024-05-14 | 133 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072168 | T2 EI RND MTN-TBL MTN#2 72/294 RPR STRT | ICQ
LC | 126134582 | 002/011 | T2 EI LAURLS-OTTR 2/11 RPR INSW | MOSSLNDG | ETL.7380.INSL | 2023-05-15 | 2023-05-15 | 2024-01-18 | On-time | 2024-05-14 | 117 | 2024-05-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081168 | T2 EI LAURLS-OTTR 2/11 RPR INSW | ICW
LC | 126150186 | 000/011 | T2 EI LAURLS-OTTR 0/11 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-17 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487993 | T2 EI LAURLS-OTTR 0/8 RPL STRW | 70Y
LC | 126134724 | 013/290 | T2 EI SALINAS-LAURELES 013/290 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-15 | 2023-05-15 | 2024-02-23 | On-time | 2024-05-14 | 81 | 2024-05-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35507080 | T2 EI SALINAS-LAURELES 013/290 RPL STRW | 70Y
LC | 126150541 | 075/538 | T2 EI BRDGVLL-CTTNWD 75/538R RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-17 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505109 | T2 DI BRDGVIL-CTTNWOOD 82/577R RPL STRW | 70Y
LC | 126150545 | 075/538 | T2 EI BRDGVLLE-CTTNWD 75/538L RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-17 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505109 | T2 DI BRDGVIL-CTTNWOOD 82/577R RPL STRW | 70Y
LC | 126150667 | 054/003 | T2 EI FORT ROSS-GUALALA 54/03 RPR CNDW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-05-17 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46073725 | T2 EI FORT ROSS-GUALALA 54/03 RPR CNDW | ICW
LC | 126150861 | 008/161 | T2 EI CARIBOU-WSTWD 8/161 GO95 CLEAR | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-17 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35517651 | T2 EI CARIBOU-WSTWD 8/161 GO95 CLEAR | 93G
LC | 126134769 | 002/009 | T2 EI LAURLS-OTTR 2/9 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-15 | 2023-05-15 | 2024-01-27 | On-time | 2024-05-14 | 108 | 2024-05-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491362 | T2 EI LAURLS-OTTR 2/9 RPL STRW | 70Y
LC | 126135309 | :021/111 | T2 EI CHC-SALINAS :21/111 RPR ANMS | MOSSLNDG | ETL.2900.TOWR | 2023-05-15 | 2023-05-15 | 2024-01-20 | On-time | 2024-05-14 | 115 | 2024-05-15 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Animal Guard-Steel | Install | 46079090 | T2 EI CHC-SALINAS :21/111 RPR ANMS | ICS
LC | 126151194 | 017/247 | T2 DI VLLY SPRNGS-CLAY 017/247 INS DMPS | VICTOR | ETL.8264.INSL.NCER | 2023-05-17 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Steel | Install | 46157200 | T2 DI VLLY SPRNGS-CLAY 017/247 INS DMPS | ICS
LC | 126135326 | 075/384 | T2 EI MALIN-ROUND MTN#2 75/384 UNBURY | TABLEMTN | ETL.6020.TOWR | 2023-05-15 | 2023-05-15 | 2023-12-04 | On-time | 2024-05-14 | 162 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46057410 | T2 EI MALIN-ROUND MTN#2 75/384 UNBURY | ICQ
LC | 126135327 | 075/383 | T2 EI MALIN-ROUND MTN #2 75/383 RPR ANCS | TABLEMTN | ETL.6020.TOWR | 2023-05-15 | 2023-05-15 | 2023-11-15 | On-time | 2024-05-14 | 181 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 46057408 | T2 EI MALIN-ROUND MTN #2 75/383 RPR ANCS | ICS
LC | 126135328 | 075/383 | T2 EI MALIN-RND MTN#2 75/383 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2023-05-15 | 2023-05-15 | 2023-11-15 | On-time | 2024-05-14 | 181 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46057409 | T2 EI MALIN-RND MTN#2 75/383 RPR GYWS | ICS
LC | 126135361 | 074/378 | T2 EI MALIN-ROUND MTN #2 74/378 RPR GYWW | TABLEMTN | ETL.6020.TOWR | 2023-05-15 | 2023-05-15 | 2023-11-15 | On-time | 2024-05-14 | 181 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46057406 | T2 EI MALIN-ROUND MTN #2 74/378 RPR GYWW | ICS
LC | 126135362 | 074/378 | T2 EI MALIN-ROUND MTN #2 74/378 UNBURY | TABLEMTN | ETL.6020.TOWR | 2023-05-15 | 2023-05-15 | 2023-11-15 | On-time | 2024-05-14 | 181 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46057407 | T2 EI MALIN-ROUND MTN #2 74/378 UNBURY | ICQ
LC | 126135462 | 018/100 | T2 EI BALCH-SANGER 18/100 RPR FOND | FRESNO | ETL.1050.TOWR | 2023-05-15 | 2023-05-15 | 2024-01-09 | On-time | 2024-05-14 | 126 | 2024-05-15 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46070739 | T2 EI BALCH-SANGER 18/100 RPR FOND | ICQ
LC | 126135525 | 076/387 | T2 EI MALIN-ROUND MONTN #2 76/387 UNBURY | TABLEMTN | ETL.6020.TOWR | 2023-05-15 | 2023-05-15 | 2023-12-05 | On-time | 2024-05-14 | 161 | 2024-05-15 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46057416 | T2 EI MALIN-ROUND MONTN #2 76/387 UNBURY | ICQ
LC | 126135536 | 076/386 | T2 EI MALIN-ROUND MTN #2 76/386 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2023-05-15 | 2023-05-15 | 2023-12-05 | On-time | 2024-05-14 | 161 | 2024-05-15 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46057412 | T2 EI MALIN-ROUND MTN #2 76/386 RPR GYWS | ICS
LC | 126135537 | 076/387 | T2 EI MALIN-ROUND MTN #2 76/387 COMPLETE | TABLEMTN | ETL.6020.TOWR | 2023-05-15 | 2023-05-15 | 2024-02-22 | On-time | 2024-05-14 | 82 | 2024-05-15 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46057414 | T2 EI MALIN-ROUND MTN #2 76/387 RPR GYWT | ICS
LC | 126152980 | 002/054 | T2 EI CASADE-BENTON-DSCHTS 2/54 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-17 | 2023-05-17 | 2024-05-21 | Late | 2024-05-16 | -5 | 2024-05-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35521350 | T2 EI CASADE-BENTON-DSCHTS 2/54 RPL STRW | 70Y
LC | 126135538 | 077/390 | T2 EI MALIN-ROUND MTN #2 77/390 COA | TABLEMTN | ETL.6020.TOWR | 2023-05-15 | 2023-05-15 | 2024-02-08 | On-time | 2024-05-14 | 96 | 2024-05-15 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46057418 | T2 EI MALIN-ROUND MTN #2 77/390 RPR GYWT | ICS
LC | 126153046 | 019/000 | T2 EI MNDCNO-WLTS-FRT BRG 19/0 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2023-05-17 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46214142 | T2 EI MNDCNO-WLTS-FRT BRG 19/0 RPR STRW | ICW
LC | 126148922 | 031/478 | T2 ETLI00000404 031/478 RPR INSW | VICTOR | ETL.8250.INSL.NCER | 2023-05-17 | 2023-05-15 | 2023-11-27 | On-time | 2024-05-14 | 169 | 2024-05-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46069022 | T2 ETLI00000404 031/478 RPR INSW | ICW
LC | 126173228 | 011/088B | T2 DI CARIBOU-TABLE MTN 11/88B RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-05-19 | 2023-05-15 | 2024-04-10 | On-time | 2024-05-14 | 34 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061150 | T2 DI CARIBOU-TABLE MTN 11/88B RPR GYWS | ICS
LC | 126173820 | 001/010 | T2 DI KRCKHFF#1-KRCKHFF#2 1/10 BNT STEEL | FRESNO | ETL.1880.TOWR | 2023-05-19 | 2023-05-15 | 2024-01-23 | On-time | 2024-05-14 | 112 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46070855 | T2 DI KRCKHFF#1-KRCKHFF#2 1/10 BNT STEEL | ICQ
LC | 126173822 | 001/010 | T2 DI KRCKHFF#1-KRCKHFF#2 1/10 RPL HRDS | FRESNO | ETL.1880.TOWR | 2023-05-19 | 2023-05-15 | 2024-01-23 | On-time | 2024-05-14 | 112 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46070856 | T2 DI KRCKHFF#1-KRCKHFF#2 1/10 RPL HRDS | ICQ
LC | 126174102 | 078/399 | T2 DI MALIN-RD MTN #2 78/399 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-05-19 | 2023-05-15 | 2024-01-12 | On-time | 2024-05-14 | 123 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46060972 | T2 DI MALIN-RD MTN #2 78/399 RPR OPGW | ICS
LC | 126153348 | 050/013 | T2 EI FORT ROSS-GUALALA 50/13 RPL POLE | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-17 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518742 | T2 EI FORT ROSS-GUALALA 46/004 RPL STRW | 70Y
LC | 126174551 | 013/005 | T2 DI MELONES-CURTIS 13/5 RPR POLE | VICTOR | ETL.2390.POLE.WDPS | 2023-05-19 | 2023-05-15 | 2023-08-07 | On-time | 2024-05-14 | 281 | 2024-05-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45907875 | T2 DI MELONES-CURTIS 13/5 RPR POLE | ICW
LC | 126174811 | 011/086B | T2 DI CRIBOU-TBL MTN 11/86B RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-05-19 | 2023-05-15 | 2024-04-10 | On-time | 2024-05-14 | 34 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061149 | T2 DI CRIBOU-TBL MTN 11/86B RPR GYWS | ICS
LC | 126175313 | 027/193 | T2 DI CARIBOU-TBL MTN 27/193L RPR GYWS | TABLEMTN | ETL.4440.POLE.STPS | 2023-05-19 | 2023-05-15 | 2024-02-07 | On-time | 2024-05-14 | 97 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061152 | T2 DI CARIBOU-TBL MTN 27/193L RPR GYWS | ICS
LC | 126154082 | 039/003 | T2 EI TRNTY-MPL CRK 039/003 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-05-17 | 2023-05-17 | 2024-06-01 | Late | 2024-05-16 | -16 | 2024-05-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172182 | T2 EI TRNTY-MPL CRK 039/003 RPR GYWW | ICW
LC | 126175315 | 027/193 | T2 DI CARIBOU-TBL MTN 27/193R RPR GYWS | TABLEMTN | ETL.4440.POLE.STPS | 2023-05-19 | 2023-05-15 | 2024-02-07 | On-time | 2024-05-14 | 97 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061153 | T2 DI CARIBOU-TBL MTN 27/193R RPR GYWS | ICS
LC | 126175317 | 027/193 | T2 DI CARIBOU-TBL MTN 27/193C RPR GYWS | TABLEMTN | ETL.4440.POLE.STPS | 2023-05-19 | 2023-05-15 | 2024-02-07 | On-time | 2024-05-14 | 97 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061154 | T2 DI CARIBOU-TBL MTN 27/193C RPR GYWS | ICS
LC | 126175708 | 078/398A | T2 DI MALIN-RD MTN#2 78/398A RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-05-19 | 2023-05-15 | 2024-05-11 | On-time | 2024-05-14 | 3 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46060971 | T2 DI MALIN-RD MTN#2 78/398A RPR SHLS | ICS
LC | 126175781 | 078/398A | T2 DI MALIN-RD MTN #2 78/398A COMPLETE | TABLEMTN | ETL.6020.TOWR | 2023-05-19 | 2023-05-15 | 2024-02-26 | On-time | 2024-05-14 | 78 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46057500 | T2 DI MALIN-RD MTN #2 78/398A UNBURY | ICQ
LC | 126176217 | 006/045 | T2 DI WISHON-COPPERMINE 6/45 UNBURY | FRESNO | ETL.9330.TOWR | 2023-05-19 | 2023-05-15 | 2024-04-22 | On-time | 2024-05-14 | 22 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46070931 | T2 DI WISHON-COPPERMINE 6/45 UNBURY | ICQ
LC | 126154603 | 018/009 | T2 EI MNDCNO-WLTS-FRT BRG 18/9 RPR INSW | WILLITS | ETL.7550.INSL.NCER | 2023-05-17 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46214141 | T2 EI MNDCNO-WLTS-FRT BRG 18/9 RPR INSW | ICW
LC | 126177991 | 057/285 | T2 DI MALIN-ROUND MTN #2 57/285 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-05-19 | 2023-05-15 | 2024-01-22 | On-time | 2024-05-14 | 113 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46060970 | T2 DI MALIN-ROUND MTN #2 57/285 RPR OPGW | ICS
LC | 126186190 | 057/284 | T2 DI MALIN-ROUND MTN #2 57/284 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-05-19 | 2023-05-15 | 2024-01-22 | On-time | 2024-05-14 | 113 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46060969 | T2 DI MALIN-ROUND MTN #2 57/284 RPR OPGW | ICS
LC | 126154903 | 038/008 | T2 EI TRNTY-MPL CRK 038/008 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-17 | 2023-05-17 | 2024-06-01 | Late | 2024-05-16 | -16 | 2024-05-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171899 | T2 EI TRNTY-MPL CRK 038/008 RPR GYWW | ICW
LC | 126154907 | 038/000 | 2 EI TRNTY-MPL CRK 38/000 RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-05-17 | 2023-05-17 | 2024-06-01 | Late | 2024-05-16 | -16 | 2024-05-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46252358 | T2 EI TRNTY-MPL CRK 38/000 RPR GYWW | ICW
LC | 126154920 | 037/010 | T2 EI TRNTY-MPL CRK 037/010 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-17 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35506416 | T2 EI TRNTY-MPL CRK 037/009 RPL POLE | 70Y
LC | 126155293 | 001/045 | T2 WV CTNWOOD-BENTON #1 1/45 RPL STRW | TABLEMTN | ETL.6640.POLE.WOOD | 2023-05-17 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521896 | T2 EI COTTONWOOD-BENTON #1 1/40 RPL POLE | 70Y
LC | 126186199 | 004/030 | T2 DI WISHON-COPPERMINE 4/30 COMPLETE | FRESNO | ETL.9330.TOWR | 2023-05-19 | 2023-05-15 | 2024-04-23 | On-time | 2024-05-14 | 21 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46070925 | T2 DI WISHON-COPPERMINE 4/30 BNT STEEL | ICQ
LC | 126155430 | 080/409 | T2 DI MALN RND-MT #2 80/409 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-05-17 | 2023-04-20 | 2024-05-11 | Late | 2024-04-19 | -22 | 2024-04-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46027050 | T2 DI MALN RND-MT #2 80/409 RPR OPGW | ICS
LC | 126187409 | 006/010 | T2 DI MELNES-RCTRCK 006/010 RPR STRW | VICTOR | ETL.2400.POLE.WOOD | 2023-05-19 | 2023-05-15 | 2024-05-10 | On-time | 2024-05-14 | 4 | 2024-05-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46171468 | T2 DI MELNES-RCTRCK 006/010 RPR STRW | ICW
LC | 126189694 | 081/415 | T2 DI MALIN-RND MNTN #2 81/415 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-05-19 | 2023-05-15 | 2024-01-12 | On-time | 2024-05-14 | 123 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46060974 | T2 DI MALIN-RND MNTN #2 81/415 RPR OPGW | ICS
LC | 126155628 | 008/091B | T2 EI DRUM-SUMMIT #2 8/91B COMPLETE | SACTO | ETL.1450.POLE.NWOD | 2023-05-17 | 2023-05-17 | 2024-05-17 | Late | 2024-05-16 | -1 | 2024-05-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062677 | T2 EI DRUM-SUMMIT #2 8/091B RPR GYWW | ICW
LC | 126189732 | 019/135 | T2 DI CARIBOU-TABLE MTN 19/135 BENT STL | TABLEMTN | ETL.4440.TOWR | 2023-05-19 | 2023-05-15 | 2024-04-15 | On-time | 2024-05-14 | 29 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072165 | T2 DI CARIBOU-TABLE MTN 19/135 BENT STL | ICQ
LC | 126155720 | 008/091C | T2 EI DRUM-SUMMIT #2 8/91C COMPLETE | SACTO | ETL.1450.POLE.NWOD | 2023-05-17 | 2023-05-17 | 2024-05-17 | Late | 2024-05-16 | -1 | 2024-05-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062678 | T2 EI DRUM-SUMMIT #2 8/091C RPR GYWW | ICW
LC | 126190468 | 080/410 | T2 DI MALIN-RND MNTN #2- 80/410 COTTER | TABLEMTN | ETL.6020.TOWR | 2023-05-19 | 2023-05-15 | 2024-01-12 | On-time | 2024-05-14 | 123 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46060973 | T2 DI MALIN-RND MNTN #2- 80/410 COTTER | ICS
LC | 126198097 | 055/274 | T2 DI MALIN RND MTN #2 55/274 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-05-22 | 2023-05-15 | 2024-01-23 | On-time | 2024-05-14 | 112 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45805439 | T2 DI MALIN RND MTN #2 55/274 RPR OPGW | ICS
LC | 126205039 | 003/029 | T2 DI WISHON-COPPERMINE 3/29 RPL DMPS | FRESNO | ETL.9330.INSL.NCER | 2023-05-22 | 2023-05-15 | 2024-04-23 | On-time | 2024-05-14 | 21 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 46058738 | T2 DI WISHON-COPPERMINE 3/29 RPL DMPS | ICS
LC | 126205398 | 004/033 | T2 DI WISHON-COPPERMINE 4/33 COMPLETE | FRESNO | ETL.9330.INSL.CERA | 2023-05-22 | 2023-05-15 | 2024-04-23 | On-time | 2024-05-14 | 21 | 2024-05-15 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510276 | T2 DI WISHON-COPPERMINE 3/24 RPL INSS | 93K
LC | 126212565 | 013/008 | T2 DI MELONES-CURT 13/8L RPR POLE | VICTOR | ETL.2390.POLE.WDPS | 2023-05-23 | 2023-05-15 | 2023-10-02 | On-time | 2024-05-14 | 225 | 2024-05-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45976992 | T2 DI MELONES-CURT 13/8L RPR POLE | ICW
LC | 126212566 | 013/008 | T2 DI MELONES-CURT 13/8R RPR POLE | VICTOR | ETL.2390.POLE.WDPS | 2023-05-23 | 2023-05-15 | 2023-10-02 | On-time | 2024-05-14 | 225 | 2024-05-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45976993 | T2 DI MELONES-CURT 13/8R RPR POLE | ICW
LC | 126212600 | A001/009 | T2 DI CHOWCHILLA KERCKHOFF A1/9 RPL INSS | FRESNO | ETL.1250.INSL.NCER | 2023-05-23 | 2023-05-15 | 2024-01-23 | On-time | 2024-05-14 | 112 | 2024-05-15 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35512409 | T2 DI CHOWCHILLA KERCKHOFF A1/9 RPL INSS | 93K
LC | 126212609 | 004/035 | T2 DI WSHN-CPPERMNE 4/35 BNT STEEL | FRESNO | ETL.9330.TOWR | 2023-05-23 | 2023-05-15 | 2024-04-24 | On-time | 2024-05-14 | 20 | 2023-08-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45804957 | T2 DI WISHON-COPPERMINE 04/35 BNT STEEL | ICQ
LC | 126212719 | 011/012 | T2 DI TRINITY-MAPLE CREEK 11/12 RPL INSW | EUREKA | ETL.8170.INSL.NCER | 2023-05-23 | 2023-05-15 | 2024-02-22 | On-time | 2024-05-14 | 82 | 2024-05-15 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35485477 | T2 DI TRINITY-MAPLE CREEK 11/12 RPL INSW | 93I
LC | 126212891 | :008/060 | T2 DI ROCK CRK-POE :8/60 RPL INSS | TABLEMTN | ETL.5630.INSL | 2023-05-23 | 2023-05-15 | 2024-02-26 | On-time | 2024-05-14 | 78 | 2024-05-15 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509199 | T2 DI ROCK CREEK-POE :5/33 RPLC INSS | 93K
LC | 126213033 | 018/000 | T2 DI EXCHEQUER-MARI 18/0 RPR CNDW | FRESNO | ETL.8640.INSL.NCER | 2023-05-23 | 2023-05-15 | 2023-08-26 | On-time | 2024-05-14 | 262 | 2024-05-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45809567 | T2 DI EXCHEQUER-MARI 18/0 RPR CNDW | ICW
LC | 126214191 | 017/124 | T2 DI CRBU TBL MTN 17/124L UNBURY | TABLEMTN | ETL.4440.POLE.STPS | 2023-05-24 | 2023-05-15 | 2024-04-12 | On-time | 2024-05-14 | 32 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Tower | Repair | 46200434 | T2 DI CRBU TBL MTN 17/124L UNBURY | ICQ
LC | 126214192 | 017/124 | T2 DI CRBU TBL MTN 17/124C UNBURY | TABLEMTN | ETL.4440.POLE.STPS | 2023-05-24 | 2023-05-15 | 2024-04-12 | On-time | 2024-05-14 | 32 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Tower | Repair | 46193822 | T2 DI CRBU TBL MTN 17/124C UNBURY | ICQ
LC | 126214193 | 017/124 | T2 DI CRBU TBL MTN 17/124R UNBURY | TABLEMTN | ETL.4440.POLE.STPS | 2023-05-24 | 2023-05-15 | 2024-04-12 | On-time | 2024-05-14 | 32 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Tower | Repair | 46193823 | T2 DI CRBU TBL MTN 17/124R UNBURY | ICQ
LC | 126214390 | 006/010 | T2 DI TRNTY MPL CRK 06/10 RPR ANCW | EUREKA | ETL.8170.POLE.WDPS | 2023-05-24 | 2023-05-15 | 2024-01-22 | On-time | 2024-05-14 | 113 | 2024-05-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46070774 | T2 DI TRNTY MPL CRK 06/10 RPR ANCW | ICW
LC | 126223218 | 003/024 | T2 DI WISHON-COPPERMINE 3/24 COMPLETE | FRESNO | ETL.9330.TOWR | 2023-05-25 | 2023-05-15 | 2024-04-22 | On-time | 2024-05-14 | 22 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46070923 | T2 DI WISHON-COPPERMINE 3/24 RPR STRT | ICQ
LC | 126223304 | 003/024 | T2 DI WISHON-COPPERMINE 3/24 RPL INSS | FRESNO | ETL.9330.INSL.NCER | 2023-05-25 | 2023-05-15 | 2024-04-23 | On-time | 2024-05-14 | 21 | 2024-05-15 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510276 | T2 DI WISHON-COPPERMINE 3/24 RPL INSS | 93K
LC | 126223338 | 003/024 | T2 DI WISHON-COPPERMINE 3/24 COMPLETE | FRESNO | ETL.9330.INSL.NCER | 2023-05-25 | 2023-05-15 | 2024-04-23 | On-time | 2024-05-14 | 21 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Steel | Repair | 46058960 | T2 DI WISHON-COPPERMINE 3/24 RPR SPLS | ICS
LC | 126244355 | 063/318 | T2 DI MALN-ROUND MTN #2 63/318 RPL SPCR | TABLEMTN | ETL.6020.INSL.NCER | 2023-05-30 | 2023-05-15 | 2023-12-20 | On-time | 2024-05-14 | 146 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Spacer-Steel | Replace | 45937119 | T2 DI MALN-ROUND MTN #2 63/318 RPL SPCR | ICS
LC | 126136609 | 012/245 | T2 EI CTTNWD-RD BLFF 012/255 RPR INSW | TABLEMTN | ETL.6660.INSL.NCER | 2023-05-16 | 2023-05-16 | 2024-04-08 | On-time | 2024-05-15 | 37 | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46062494 | T2 EI CTTNWD-RD BLFF 012/255 RPR INSW | ICW
LC | 126136974 | 013/288 | T2 EI SALINAS-LAURELES 013/288 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2024-02-22 | On-time | 2024-05-15 | 83 | 2024-05-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507018 | T2 EI SALINAS-LAURELES 013/288 RPL STRW | 70Y
LC | 126137542 | 011/091 | T2 EI PIT #1-COTTONWOOD 11/091 BNT STEEL | TABLEMTN | ETL.5390.TOWR | 2023-05-16 | 2023-05-16 | 2024-03-28 | On-time | 2024-05-15 | 48 | 2024-05-16 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Steel | Repair | 46061163 | T2 EI PIT #1-COTTONWOOD 11/091 BNT STEEL | ICS
LC | 126137778 | 009/102C | T2 EI DRUM-SUMMIT #2 9/102C RPL HRDW | SACTO | ETL.1450.INSL.CERA | 2023-05-16 | 2023-05-16 | 2023-06-12 | On-time | 2024-05-15 | 338 | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45806201 | T2 EI DRUM-SUMMIT #2 9/102C RPL HRDW | ICW
LC | 126137840 | 067/280 | T2 EI ROND MTN-TBL MTN #1 67/280 BNT STL | TABLEMTN | ETL.6060.TOWR | 2023-05-16 | 2023-05-16 | 2024-01-03 | On-time | 2024-05-15 | 133 | 2024-05-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46072179 | T2 EI ROND MTN-TBL MTN #1 67/280 BNT STL | ICQ
LC | 126138542 | 067/279 | T2 EI RND MTN-TBL MTN #1 67/279 RPR GYWT | TABLEMTN | ETL.6060.TOWR | 2023-05-16 | 2023-05-16 | 2024-01-03 | On-time | 2024-05-15 | 133 | 2024-05-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46072178 | T2 EI RND MTN-TBL MTN #1 67/279 RPR GYWT | ICS
LC | 126160362 | 013/126 | T2 EI WOODLEAF-PALERMO 13/126 RPR INSW | TABLEMTN | ETL.4220.INSL.NCER | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46062730 | T2 EI WOODLEAF-PALERMO 13/126 RPR INSW | ICW
LC | 126139092 | 002/014 | T2 EI LAURLS-OTTR 2/14 RPR STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2024-03-11 | On-time | 2024-05-15 | 65 | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081169 | T2 EI LAURLS-OTTR 2/14 RPR STRW | ICW
LC | 126139736 | 003/018A | T2 METCALF-SANTA TERESA 03/018A RPL INSS | METCALF | ETL.2480.INSL | 2023-05-16 | 2023-05-16 | 2023-07-26 | On-time | 2024-05-15 | 294 | 2024-05-16 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31650780 | T2 METCALF-SANTA TERESA 03/018A RPL INSS | 93K
LC | 126161170 | 060/007 | T2 WV HUMBOLDT-TRINITY 60/7 RPR CNDW | EUREKA | ETL.1820.INSL.NCER | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46096521 | T2 WV HUMBOLDT-TRINITY 60/7 RPR CNDW | ICW
LC | 126161256 | 018/333 | T2 EI SALINAS-LAURELES 018/333 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35507090 | T2 EI SALINAS-LAURELES 018/333 RPL STRW | 70Y
LC | 126139775 | 003/018B | T2 METCALF-EDENVALE #2 003/018B RPL INSS | METCALF | ETL.2490.INSL | 2023-05-16 | 2023-05-16 | 2023-07-27 | On-time | 2024-05-15 | 293 | 2024-05-16 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31650781 | T2 METCALF-EDENVALE #2 003/018B RPL INSS | 93K
LC | 126161405 | 009/071 | T2 DI PIT #6 JCT-RND MTN 9/71R RPL POLE | TABLEMTN | ETL.5440.POLE.WDPS | 2023-05-18 | 2023-04-28 | 2024-06-21 | Late | 2024-04-27 | -55 | 2024-04-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35529573 | T2 DI PIT #6 JCT-RND MTN RPL 3 POLE | 70Y
LC | 126139849 | 009/171 | T2 EI CARIBOU-WESTWOOD 9/171 COMPLETE | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2024-05-04 | On-time | 2024-05-15 | 11 | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062654 | T2 EI CARIBOU-WESTWOOD 9/171 RPR STRW | ICW
LC | 126162474 | 003/087 | T2 EI CSCD-BNTN-DSCHTS 3/87 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521351 | T2 EI CSCD-BNTN-DSCHTS 3/87 RPL STRW | 70Y
LC | 126140983 | :020/107 | T2 EI CHC-SALINAS :20/107 RPR ANMS | MOSSLNDG | ETL.2900.TOWR | 2023-05-16 | 2023-05-16 | 2023-12-18 | On-time | 2024-05-15 | 149 | 2024-05-16 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Animal Guard-Steel | Install | 46073684 | T2 EI CHC-SALINAS :20/107 RPR ANMS | ICS
LC | 126141040 | 067/278 | T2 EI RND MTN-TBL MTN #1 67/278 RPR GYWT | TABLEMTN | ETL.6060.TOWR | 2023-05-16 | 2023-05-16 | 2024-01-03 | On-time | 2024-05-15 | 133 | 2024-05-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46072177 | T2 EI RND MTN-TBL MTN #1 67/278 RPR GYWT | ICS
LC | 126162644 | 006/114 | T2 EI CARIBOU-WESTWOOD 06/114L RPL PL | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519115 | T2 EI CARIBOU-WESTWOOD 06/114L RPL PL | 70Y
LC | 126141620 | 009/170 | T2 EI CARIBOU-WESTWOOD 9/170 COMPLETE | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2024-05-04 | On-time | 2024-05-15 | 11 | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062653 | T2 EI CARIBOU-WESTWOOD 9/170 RPR STRW | ICW
LC | 126162897 | 002/045 | T2 EI CARIBOU-WSTWD 2/45 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519109 | T2 DI CARIBOU-WSTWD 002/043 RPL STRW | 70Y
LC | 126162921 | 017/328 | T2 EI SALINAS-LAURELES 17/328 INST DMPW | MOSSLNDG | ETL.7930.INSL | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 630 | TLN | PATR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 46081178 | T2 EI SALINAS-LAURELES 17/328 INST DMPW | ICW
LC | 126162926 | 006/114 | T2 EI CARIBOU-WESTWOOD 06/114C RPL PL | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519115 | T2 EI CARIBOU-WESTWOOD 06/114L RPL PL | 70Y
LC | 126142448 | 008/097 | T2 EI DRUM-SUMMIT #2 8/097L RPR GYWW | SACTO | ETL.1450.POLE.WDPS | 2023-05-16 | 2023-05-16 | 2023-07-15 | On-time | 2024-05-15 | 305 | 2023-08-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45844385 | T2 EI DRUM-SUMMIT #2 8/097L RPR GYWW | ICW
LC | 126142449 | 008/097 | T2 EI DRUM-SUMMIT NO. 2 8/097 RPR GYWW | SACTO | ETL.1450.POLE.WDPS | 2023-05-16 | 2023-05-16 | 2023-07-15 | On-time | 2024-05-15 | 305 | 2023-08-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45844386 | T2 EI DRUM-SUMMIT NO. 2 8/097 RPR GYWW | ICW
LC | 126142931 | 000/003 | T2 EI SPAULDING-SUMMIT 00/003 RPR CONDW | SACTO | ETL.8060.INSL.NCER | 2023-05-16 | 2023-05-16 | 2024-03-27 | On-time | 2024-05-15 | 49 | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46062640 | T2 EI SPAULDING-SUMMIT 00/003 RPR CONDW | ICW
LC | 126163061 | 010/121 | T2 EI DRUM-SUMMIT #1 1/121 RPR WDPKR | SACTO | ETL.1440.POLE.WDPS | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062720 | T2 EI DRUM-SUMMIT #1 1/121 RPR WDPKR | ICW
LC | 126163287 | 006/114 | T2 EI CARIBOU-WESTWOOD 06/114R RPL POLE | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519115 | T2 EI CARIBOU-WESTWOOD 06/114L RPL PL | 70Y
LC | 126143111 | :020/106 | T2 EI CHC-SALINAS :20/106 RPR ANMS | MOSSLNDG | ETL.2900.TOWR | 2023-05-16 | 2023-05-16 | 2024-01-30 | On-time | 2024-05-15 | 106 | 2024-05-16 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Animal Guard-Steel | Install | 46073685 | T2 EI CHC-SALINAS :20/106 RPR ANMS | ICS
LC | 126163401 | 002/060 | T2 EI COLGATE-ALLEGHANY 02/060 RPL STRW | SACTO | ETL.6470.POLE.WOOD | 2023-05-18 | 2023-05-18 | 2024-06-19 | Late | 2024-05-17 | -33 | 2024-05-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508685 | T2 COLGATE-ALLEGHANY 00/01 RPL POLE | 70Y
LC | 126163402 | 012/059 | T2 WV TULUCAY-VACA 12/59 RPL INSS | LAKEVLLE | ETL.5800.INSL | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 532T | TLN | CREW | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510309 | T2 WV TULUCAY-VACA RPL INSS IN 3 TWRS. | 93K
LC | 126143158 | 002/004 | T2 EI LAURLS-OTTR 2/4 RPR ANCW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2024-01-23 | On-time | 2024-05-15 | 113 | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46081171 | T2 EI LAURLS-OTTR 2/4 RPR ANCW | ICW
LC | 126164092 | 014/128 | T2 EI SN LS OBSP-CAYCOS 14/128 RPL STRW | PISMOBCH | ETL.9090.POLE.WOOD | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35520658 | T2 EI SN LS OBSP-CAYCOS 14/128 RPL POLE | 70Y
LC | 126143522 | 002/003 | T2 EI LAURLS-OTTR 2/3 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2024-03-11 | On-time | 2024-05-15 | 65 | 2024-05-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503052 | T2 DI LAURELES-OTTER 002/000 RPL POLE | 70Y
LC | 126164458 | 017/330 | T2 EI SALINAS-LAURELES 17/330 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507089 | T2 DI SALINAS-LAURELES 17/329 RPL STRW | 70Y
LC | 126143572 | 012/101 | T2 EI PIT #1-COTTONWOOD 012/101 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-16 | 2023-05-16 | 2023-11-14 | On-time | 2024-05-15 | 183 | 2024-05-16 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46057504 | T2 EI PIT #1-COTTONWOOD 012/101 UNBURY | ICQ
LC | 126144405 | 002/001 | T2 EI LAURLS-OTTR 2/1 COTTER | MOSSLNDG | ETL.7380.INSL | 2023-05-16 | 2023-05-16 | 2024-01-22 | On-time | 2024-05-15 | 114 | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081172 | T2 EI LAURLS-OTTR 2/1 COTTER | ICW
LC | 126164592 | A004/104 | T2 EI CASCADE-BENTON A4/104 RPL PL | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31655017 | T2 CASCADE-BENTON-DESCHUTES A4/104 GO95 | 93G
LC | 126144694 | :020/105 | T2 EI CHC-SALINAS :20/105 RPR ANMS | MOSSLNDG | ETL.2900.TOWR | 2023-05-16 | 2023-05-16 | 2023-12-18 | On-time | 2024-05-15 | 149 | 2024-05-16 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Animal Guard-Steel | Install | 46079091 | T2 EI CHC-SALINAS :20/105 RPR ANMS | ICS
LC | 126165188 | 010/127A | T2 EI DRUM-SUMMIT #2 10/127A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-05-18 | 2023-05-18 | 2024-06-26 | Late | 2024-05-17 | -40 | 2023-11-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062726 | T2 EI DRUM-SUMMIT #2 10/127A RPR GYWW | ICW
LC | 126165206 | 010/125B | T2 EI DRUM-SUMMIT #1 10/125B RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062721 | T2 EI DRUM-SUMMIT #1 10/125B RPR GYWW | ICW
LC | 126144739 | 012/102 | T2 EI PIT #1-COTTONWOOD 012/102 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-16 | 2023-05-16 | 2023-11-13 | On-time | 2024-05-15 | 184 | 2024-05-16 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46057505 | T2 EI PIT #1-COTTONWOOD 012/102 UNBURY | ICQ
LC | 126144978 | 008/044 | T2 EI EAGLE ROCK-CORTINA 8/44 RPL INSS | SACTO | ETL.1470.INSL.CERA | 2023-05-16 | 2023-05-16 | 2024-03-04 | On-time | 2024-05-15 | 72 | 2024-05-16 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510800 | T2 EI EAGLE ROCK-CORTINA RPL INSS 2 TWRS | 93K
LC | 126165341 | 010/126 | T2 EI DRUM-SUMMIT #1 10/126 RPR INSW | SACTO | ETL.1440.INSL | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46062722 | T2 EI DRUM-SUMMIT #1 10/126 RPR INSW | ICW
LC | 126165342 | 010/126 | T2 EI DRUM-SUMMIT #1 10/126 RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2023-11-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062723 | T2 EI DRUM-SUMMIT #1 10/126 RPR GYWW | ICW
LC | 126165439 | 010/126 | T2 EI DRUM-SUMMIT #1 10/126 RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2023-11-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062724 | T2 EI DRUM-SUMMIT #1 10/126 RPR GYWW | ICW
LC | 126165525 | 010/126 | T2 EI DRUM-SUMMIT #1 10/126 RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2023-11-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062725 | T2 EI DRUM-SUMMIT #1 10/126 RPR GYWW | ICW
LC | 126145748 | :020/104 | T2 EI CHC-SALINAS :20/104 RPR ANMS | MOSSLNDG | ETL.2900.TOWR | 2023-05-16 | 2023-05-16 | 2024-01-30 | On-time | 2024-05-15 | 106 | 2024-05-16 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Animal Guard-Steel | Install | 46079094 | T2 EI CHC-SALINAS :20/105 RPR ANMS | ICS
LC | 126145799 | :008/000 | T2 EI BLLTA-RVRBNK-MLNS SW :8/0 RPR GYWS | VICTOR | ETL.1070.POLE.NWOD | 2023-05-16 | 2023-05-16 | 2023-11-17 | On-time | 2024-05-15 | 180 | 2024-05-16 | 628 | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Replace | 46058302 | T2 EI BLLTA-RVRBNK-MLNS SW :8/0 RPR GYWS | ICS
LC | 126165919 | 003/013 | T2 EI HUMBOLDT-MAPLE CREEK 3/13 RPR WDPK | EUREKA | ETL.7130.POLE.WOOD | 2023-05-18 | 2023-05-08 |  | Late | 2024-05-07 |  | 2024-05-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46096690 | T2 EI HUMBOLDT-MAPLE CREEK 3/13 RPR WDPK | ICW
LC | 126146190 | 018/096 | T2 EI BALCH-SANGER 18/096 RPR FOND | FRESNO | ETL.1050.TOWR | 2023-05-16 | 2023-05-16 | 2024-01-09 | On-time | 2024-05-15 | 127 | 2024-05-16 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46070738 | T2 EI BALCH-SANGER 18/096 RPR FOND | ICQ
LC | 126146896 | 006/104 | T2 WV TEMPLTN-ATSCDRO 06/104 RPL POLE | PISMOBCH | ETL.9410.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2024-05-15 | On-time | 2024-05-15 | 0 | 2024-05-16 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35523961 | T2 WV TEMPLTN-ATSCDRO 06/104 RPL POLE | 70Y
LC | 126146922 | :020/102 | T2 EI CHC-SALINAS :20/102 RPR ANMS | MOSSLNDG | ETL.2900.TOWR | 2023-05-16 | 2023-05-16 | 2024-01-30 | On-time | 2024-05-15 | 106 | 2024-05-16 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Animal Guard-Steel | Install | 46073686 | T2 EI CHC-SALINAS :20/102 RPR ANMS | ICS
LC | 126147156 | 001/010 | T2 EI LAURLS-OTTR 1/10 RPR STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2024-02-02 | On-time | 2024-05-15 | 103 | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081174 | T2 EI LAURLS-OTTR 1/10 RPR STRW | ICW
LC | 126167224 | 011/262 | T2 EI SALINAS-LAURELES 11/262 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507124 | T2 EI SALINAS-LAURELES 11/262 RPL POLE | 70Y
LC | 126147319 | 001/011 | T2 EI LAURLS-OTTR 1/11 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2024-01-31 | On-time | 2024-05-15 | 105 | 2024-05-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491360 | T2 LAURELES-OTTER 001/008 RPL POLE | 70Y
LC | 126167279 | 037/002 | T2 EI TRNTY-MPL CRK 037/002 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506412 | T2 EI TRNTY-MPL CRK 037/002 RPL POLE | 70Y
LC | 126167290 | 037/007 | T2 EI TRINITY-MAPLE CRK 37/7 RPR INSW | EUREKA | ETL.8170.INSL.NCER | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46171897 | T2 EI TRINITY-MAPLE CRK 37/7 RPR INSW | ICW
LC | 126167291 | 037/000 | T2 EI TRNTY-MPL CRK 037/000 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096669 | T2 DI TRINITY-MAPLE CREEK 37/0 RPR INSW | ICW
LC | 126167292 | 037/005 | T2 EI TRINITY-MPLE CREEK 37/5L RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-18 | 2023-05-18 | 2024-06-01 | Late | 2024-05-17 | -15 | 2023-11-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171895 | T2 EI TRINITY-MPLE CREEK 37/5L RPR GYWW | ICW
LC | 126167293 | 037/009 | T2 EI TRNTY-MPL CRK 037/009 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506416 | T2 EI TRNTY-MPL CRK 037/009 RPL POLE | 70Y
LC | 126167300 | 037/005 | T2 EI TRINITY-MPLE CREEK 37/5R RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-18 | 2023-05-18 | 2024-06-01 | Late | 2024-05-17 | -15 | 2023-11-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171895 | T2 EI TRINITY-MPLE CREEK 37/5L RPR GYWW | ICW
LC | 126167377 | 008/101 | T2 WV DIVIDE-CABRILLO #1 8/101 RPL DMPW | PISMOBCH | ETL.1380.INSL.NCER | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46090149 | T2 WV DIVIDE-CABRILLO #1 8/101 RPL DMPW | ICW
LC | 126167412 | 000/018 | T2 EI PLUMAS-SIERRA TAP 0/18 RPR STRW | TABLEMTN | ETL.6291.POLE.WOOD | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062716 | T2 EI PLUMAS-SIERRA TAP 00/018 RPR STRW | ICW
LC | 126147332 | :019/101 | T2 EI CHC-SALINAS :19/101 RPR ANMS | MOSSLNDG | ETL.2900.TOWR | 2023-05-16 | 2023-05-16 | 2024-01-30 | On-time | 2024-05-15 | 106 | 2024-05-16 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Animal Guard-Steel | Install | 46073687 | T2 EI CHC-SALINAS :19/101 RPR ANMS | ICS
LC | 126168047 | 011/261 | T2 EI SALINAS-LAURELES 11/261 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-18 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507123 | T2 EI SALINAS-LAURELES 11/261 RPL POLE | 70Y
LC | 126147488 | 009/089 | T2 WV PARADISE-BUTTE 009/089 INS DAMW | TABLEMTN | ETL.4396.INSL.CERA | 2023-05-16 | 2023-05-16 | 2024-01-24 | On-time | 2024-05-15 | 112 | 2024-05-16 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46062652 | T2 WV PARADISE-BUTTE 009/089 INS DAMW | ICW
LC | 126147553 | 008/164 | T2 EI CARIBOU-WESTWOOD 8/164 RPR STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2024-05-04 | On-time | 2024-05-15 | 11 | 2024-05-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062651 | T2 EI CARIBOU-WESTWOOD 8/164 RPR STRW | ICW
LC | 126168949 | 081/002C | T2 EI HMBLDT-TRNTY 81/002C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-18 | 2023-05-18 | 2024-05-31 | Late | 2024-05-17 | -14 | 2024-05-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46252615 | T2 EI HMBLDT-TRNTY 81/002C RPR GYWW | ICW
LC | 126169095 | 081/002A | T2 EI HMBLDT-TRNTY 81/002A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-18 | 2023-05-18 | 2024-05-31 | Late | 2024-05-17 | -14 | 2024-05-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46252614 | T2 EI HMBLDT-TRNTY 81/002A RPR GYWW | ICW
LC | 126169180 | 081/002B | T2 EI HMBLDT-TRNTY 81/002B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-18 | 2023-05-18 | 2024-05-31 | Late | 2024-05-17 | -14 | 2024-05-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46252616 | T2 EI HMBLDT-TRNTY 81/002B RPR GYWW | ICW
LC | 126147767 | 011/260 | T2 EI SALINAS-LAURELES 011/260 RMV VEG | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2024-04-11 | On-time | 2024-05-15 | 34 | 2024-05-16 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126147882 | 011/260 | T2 EI SALINAS-LAURELES 011/260 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2024-03-05 | On-time | 2024-05-15 | 71 | 2024-05-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507122 | T2 EI SALINAS-LAURELES 011/260 RPL POLE | 70Y
LC | 126173636 | 052/003 | T2 DI FORT ROSS-GUALALA 052/003 RPR STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-19 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46073722 | T2 DI FORT ROSS-GUALALA 052/003 RPR STRW | ICW
LC | 126173703 | 052/003 | T2 DI FORT ROSS-GUALALA 052/003 RPR GYWW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-19 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073723 | T2 DI FORT ROSS-GUALALA 052/003 RPR GYWW | ICW
LC | 126173707 | 052/003 | T2 DI FORT ROSS-GUALALA 052/003 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-05-19 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46073724 | T2 DI FORT ROSS-GUALALA 052/003 RPR INSW | ICW
LC | 126173725 | 003/017 | T2 DI MLNS-RCTRCK 003/017 RMV VEG | VICTOR | ETL.2400.POLE.NWOD | 2023-05-19 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126147888 | 075/384 | T2 EI MALIN-ROUND MTN#2 75/384 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2023-05-16 | 2023-05-16 | 2023-12-05 | On-time | 2024-05-15 | 162 | 2024-05-16 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46057411 | T2 EI MALIN-ROUND MTN#2 75/384 RPR GYWS | ICS
LC | 126147935 | ;002/006 | T2 EI CARIBOU #2 ;2/6 RPR GYWW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2023-07-11 | On-time | 2024-05-15 | 309 | 2023-08-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805372 | T2 EI CARIBOU #2 ;2/6 RPR GYWW | ICW
LC | 126147938 | ;002/006 | T2 EI CARIBOU #2 ;2/6 RPL ANCW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-16 | 2023-05-16 | 2023-07-11 | On-time | 2024-05-15 | 309 | 2023-08-16 | 637 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31646520 | T2 EI CARIBOU #2 ;2/6 RPL ANCW | 93E
LC | 126147978 | 039/006 | T2 EI TRNTY-MPL CRK 39/6C REPULY GUY | EUREKA | ETL.8170.POLE.STPS | 2023-05-16 | 2023-05-16 | 2023-10-06 | On-time | 2024-05-15 | 222 | 2023-11-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45770992 | T2 EI TRNTY-MPL CRK 39/6C REPULY GUY | ICW
LC | 126147982 | 075/380B | T2 EI MLN-RND MTN#2 75/380B RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-05-16 | 2023-05-16 | 2023-08-29 | On-time | 2024-05-15 | 260 | 2023-08-16 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45805377 | T2 EI MLN-RND MTN#2 75/380B RPR SHLS | ICS
LC | 126147988 | 039/006 | T2 EI TRINITY-MAPLE CRK 39/6R REPUL GUY | EUREKA | ETL.8170.POLE.STPS | 2023-05-16 | 2023-05-16 | 2023-10-06 | On-time | 2024-05-15 | 222 | 2023-11-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45770994 | T2 EI TRINITY-MAPLE CRK 39/6R REPUL GUY | ICW
LC | 126148267 | 077/391 | T2 EI MALIN-ROUND MTN #2 77/391 RPR FOND | TABLEMTN | ETL.6020.TOWR | 2023-05-16 | 2023-05-16 | 2024-02-22 | On-time | 2024-05-15 | 83 | 2024-05-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Steel | Repair | 46057419 | T2 EI MALIN-ROUND MTN #2 77/391 RPR FOND | ICS
LC | 126174909 | 011/084 | T2 DI CARIBOU-TBL MTN 11/84 RPR STRT | TABLEMTN | ETL.4440.TOWR | 2023-05-19 | 2023-05-15 | 2024-06-06 | Late | 2024-05-14 | -23 | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46069073 | T2 DI CARIBOU-TBL MTN 11/84 RPR STRT | ICQ
LC | 126175104 | 005/107 | T2 EI CARIBOU-WESTWOOD 05/107 RPR GYWW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062831 | T2 EI CARIBOU-WESTWOOD 05/107 RPR GYWW | ICW
LC | 126148268 | 076/386 | T2 EI MALIN-ROUND MONTN #2 76/386 UNBURY | TABLEMTN | ETL.6020.TOWR | 2023-05-16 | 2023-05-16 | 2023-11-05 | On-time | 2024-05-15 | 192 | 2024-05-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Steel | Repair | 46057413 | T2 EI MALIN-ROUND MONTN #2 76/386 UNBURY | ICS
LC | 126175158 | 010/127B | T2 EI DRUM-SUMMIT #2 10/127B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-05-19 | 2023-05-18 | 2024-06-26 | Late | 2024-05-17 | -40 | 2023-11-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062727 | T2 EI DRUM-SUMMIT #2 10/127B RPR GYWW | ICW
LC | 126148482 | 076/386 | T2 EI MALIN-ROUND MTN #2 76/386 RPR ANCT | TABLEMTN | ETL.6020.TOWR | 2023-05-16 | 2023-05-16 | 2023-09-11 | On-time | 2024-05-15 | 247 | 2024-05-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Tower | Repair | 46189798 | T2 EI MALIN-ROUND MTN #2 76/386 RPR ANCT | ICQ
LC | 126148483 | 076/388 | T2 EI MALIN-ROUND MTN #2 76/388 CANCEL | TABLEMTN | ETL.6020.TOWR | 2023-05-16 | 2023-05-16 | 2024-02-08 | On-time | 2024-05-15 | 97 | 2024-05-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46057417 | T2 EI MALIN-ROUND MTN #2 76/388 RPR GYWT | ICS
LC | 126174514 | :001/008 | T2 DI ROCK CRK-POE :1/8 RPR GYWS | TABLEMTN | ETL.5630.TOWR | 2023-05-19 | 2023-05-16 | 2024-05-01 | On-time | 2024-05-15 | 14 | 2024-05-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46072175 | T2 DI ROCK CRK-POE :1/8 RPR GYWS | ICS
LC | 126175344 | 000/001 | T2 DI MTN GATE TAP 0/1 RPL POLE | TABLEMTN | ETL.7641.POLE.WOOD | 2023-05-19 | 2023-05-16 | 2024-02-18 | On-time | 2024-05-15 | 87 | 2024-05-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485420 | T2 DI MTN GATE TAP 0/1 RPL POLE | 70Y
LC | 126175380 | 010/127C | T2 EI DRUM-SUMMIT #2 10/127C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-05-19 | 2023-05-18 | 2024-06-26 | Late | 2024-05-17 | -40 | 2023-11-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062728 | T2 EI DRUM-SUMMIT #2 10/127C RPR GYWW | ICW
LC | 126175405 | 008/112 | T2 WV DIVIDE-CABRILLO #1 8/112 RPL DMPW | PISMOBCH | ETL.1380.INSL.NCER | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46090150 | T2 WV DIVIDE-CABRILLO #1 8/112 RPL DMPW | ICW
LC | 126175624 | 005/108 | T2 EI CARIBOU-WESTWOOD 05/108 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519113 | T2 EI CARIBOU-WESTWOOD 05/108 RPL STRW | 70Y
LC | 126175682 | 047/003 | T2 DI FORT ROSS-GUALALA 47/3 COTTER | LAKEVLLE | ETL.6980.INSL.NCER | 2023-05-19 | 2023-05-16 | 2023-08-15 | On-time | 2024-05-15 | 274 | 2023-08-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45805698 | T2 DI FORT ROSS-GUALALA 47/3 COTTER | ICW
LC | 126176271 | :000/006 | T2 DI ROCK CRK-POE :0/6 RPR GYWS | TABLEMTN | ETL.5630.POLE.NWOD | 2023-05-19 | 2023-05-16 | 2024-05-01 | On-time | 2024-05-15 | 14 | 2024-05-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46072174 | T2 DI ROCK CRK-POE :0/6 RPR GYWS | ICS
LC | 126178071 | 011/215 | T2 DI CARIBOU-WSWD 011/215 RPR STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-19 | 2023-05-16 | 2024-03-18 | On-time | 2024-05-15 | 58 | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062658 | T2 DI CARIBOU-WSWD 011/215 RPR STRW | ICW
LC | 126176112 | 005/109 | T2 EI CARIBOU-WESTWOD 05/109 RPR HRDW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Missing | Hardware-Wood | Install | 46062832 | T2 EI CARIBOU-WESTWOD 05/109 RPR HRDW | ICW
LC | 126178901 | 008/059 | T2 DI WISHON-COPPERMINE 8/59 UNBURY | FRESNO | ETL.9330.TOWR | 2023-05-19 | 2023-05-16 | 2024-02-13 | On-time | 2024-05-15 | 92 | 2024-05-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46070932 | T2 DI WISHON-COPPERMINE 8/59 UNBURY | ICQ
LC | 126176230 | 014/109 | T2 DI CARIBOU-TABLE MTN 14/109 RPR JUMS | TABLEMTN | ETL.4440.INSL.CERA | 2023-05-19 | 2023-05-12 | 2024-06-08 | Late | 2024-05-11 | -28 | 2023-11-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46061140 | T2 DI CARIBOU-TABLE MTN 14/109 RPR JUMP | ICS
LC | 126176239 | 014/109 | T2 DI CARIBOU-TABLE MTN 14/109 RPR INSS | TABLEMTN | ETL.4440.INSL.CERA | 2023-05-19 | 2023-05-12 | 2024-06-08 | Late | 2024-05-11 | -28 | 2024-05-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46061141 | T2 DI CARIBOU-TABLE MTN 14/109 RPR INSS | ICS
LC | 126179057 | 008/059 | T2 DI WISHON-COPPERMINE 8/59 RPR INSS | FRESNO | ETL.9330.INSL.NCER | 2023-05-19 | 2023-05-16 | 2024-04-23 | On-time | 2024-05-15 | 22 | 2024-05-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46058736 | T2 DI WISHON-COPPERMINE 8/59 RPR INSS | ICS
LC | 126181650 | 004/034 | T2 DI WISHON-COPPERMINE 4/34 BNT STEEL | FRESNO | ETL.9330.TOWR | 2023-05-19 | 2023-05-16 | 2024-04-22 | On-time | 2024-05-15 | 23 | 2024-05-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46070930 | T2 DI WISHON-COPPERMINE 4/34 BNT STEEL | ICQ
LC | 126186195 | 004/031 | T2 DI WISHON-COPPERMINE 4/31 COMPLETE | FRESNO | ETL.9330.TOWR | 2023-05-19 | 2023-05-16 | 2024-04-22 | On-time | 2024-05-15 | 23 | 2024-05-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46070929 | T2 DI WISHON-COPPERMINE 4/31 RPR STRT | ICQ
LC | 126176592 | 045/394 | T2 EI PIT #1-CTNWD 45/394 RPL TOWER ANCH | TABLEMTN | ETL.5390.TOWR | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 93Z | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Steel | Replace | 31677645 | T2 EI PIT #1-CTNWD 45/394 RPL TOWER ANCH | 93Z
LC | 126176630 | 011/127 | T2 EI DRUM-SUMMIT #1 11/127L RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526569 | T0 EI DRUM-SUMMIT #1 013/150 RPL STRW | 70Y
LC | 126187134 | 000/004 | T2 DI MTN GATE TAP 0/4 RPL STRW | TABLEMTN | ETL.7641.POLE.WOOD | 2023-05-19 | 2023-05-16 | 2024-02-18 | On-time | 2024-05-15 | 87 | 2024-05-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485421 | T2 DI MTN GATE TAP 0/4 RPL STRW | 70Y
LC | 126188686 | 003/023 | T2 DI WISHON-COPPERMINE 003/023 UNBURY | FRESNO | ETL.9330.TOWR | 2023-05-19 | 2023-05-16 | 2024-02-14 | On-time | 2024-05-15 | 91 | 2024-05-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46070922 | T2 DI WISHON-COPPERMINE 003/023 UNBURY | ICQ
LC | 126189156 | 006/048 | T2 DI BUTTE VLY-CARI 6/48 BNT STEEL | TABLEMTN | ETL.1180.TOWR | 2023-05-19 | 2023-05-16 | 2024-04-09 | On-time | 2024-05-15 | 36 | 2024-05-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072176 | T2 DI BUTTE VLY-CARI 6/48 BNT STEEL | ICQ
LC | 126189603 | 005/036C | T2 DI BUTTE VLY-CARI 5/36C RPR GYWS | TABLEMTN | ETL.1180.POLE.NWOD | 2023-05-19 | 2023-05-16 | 2024-05-02 | On-time | 2024-05-15 | 13 | 2024-05-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061158 | T2 DI BUTTE VLY-CARI 5/36C RPR GYWS | ICS
LC | 126205392 | 007/017 | T2 DI CARIBOU-PLMAS JCT-WD 7/17 RPR INSW | TABLEMTN | ETL.6290.INSL.CERA | 2023-05-22 | 2023-05-16 | 2024-05-07 | On-time | 2024-05-15 | 8 | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46062647 | T2 DI CARIBOU-PLMAS JCT-WD 7/17 RPR INSW | ICW
LC | 126179420 | 004/045 | T2 PARADISE-BUTTE 004/045 RMV ENCR | TABLEMTN | ETL.4396.POLE.NWOD | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2023-11-19 | 931 | TLS | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Encroachment | Right of Way | Remove
LC | 126180690 | 011/240 | T2 EI CSCD-BNTN-DSCHTS 11/240 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521770 | T2 EI CSCD-BNTN-DSCHTS 11/239 RPL STRW | 70Y
LC | 126207216 | 005/041C | T2 DI BUTTE VALLEY-CARIBO 5/41C RPR GYWS | TABLEMTN | ETL.1180.POLE.NWOD | 2023-05-23 | 2023-05-16 | 2024-04-23 | On-time | 2024-05-15 | 22 | 2024-05-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061160 | T2 DI BUTTE VALLEY-CARIBO 5/41C RPR GYWS | ICS
LC | 126212475 | 005/036B | T2 DI BTTE VLLY-CRB 05/36B RPR GYWS | TABLEMTN | ETL.1180.POLE.NWOD | 2023-05-23 | 2023-05-16 | 2024-05-02 | On-time | 2024-05-15 | 13 | 2024-05-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061157 | T2 DI BTTE VLLY-CRB 05/36B RPR GYWS | ICS
LC | 126212641 | 005/036A | T2 DI BTTE VLLY-CRB 5/36A COMPLETE | TABLEMTN | ETL.1180.POLE.NWOD | 2023-05-23 | 2023-05-16 | 2024-05-02 | On-time | 2024-05-15 | 13 | 2024-05-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061156 | T2 DI BTTE VLLY-CRB 05/36A RPR GYWS | ICS
LC | 126212645 | 000/008 | T2 DI MOUNTAIN GATE TAP-00/08 RPR INSW | TABLEMTN | ETL.7641.INSL.NCER | 2023-05-23 | 2023-05-16 | 2024-02-17 | On-time | 2024-05-15 | 88 | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46062490 | T2 DI MOUNTAIN GATE TAP-00/08 RPR INSW | ICW
LC | 126186476 | 011/239 | T2 EI CSCD-BNTN-DSCHTS 11/239 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35521770 | T2 EI CSCD-BNTN-DSCHTS 11/239 RPL STRW | 70Y
LC | 126186531 | ;002/025 | T2 DI CARIBOU#2 ;2/25 RPR INSW | TABLEMTN | ETL.6280.INSL.CERA | 2023-05-19 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46062596 | T2 DI CARIBOU#2 ;2/25 RPR INSW | ICW
LC | 126186694 | 011/238 | T2 EI CSCD-BNTN-DSCHTS 11/238 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521352 | T2 EI CSCD-BNTN-DSCHTS 11/238 RPL STRW | 70Y
LC | 126186702 | 018/467 | T2 DI CARIBOU #2 18/467 COTTER | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-19 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062661 | T2 DI CARIBOU #2 18/467 COTTER | ICW
LC | 126186797 | 002/051 | T2 DI CASCADE-BNT-DESCHTES 2/51 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-19 | 2023-05-16 | 2024-05-27 | Late | 2024-05-15 | -12 | 2024-05-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35521349 | T2 DI CASCADE-BNT-DESCHTES 2/51 RPL STRW | 70Y
LC | 126186846 | 004/077 | T2 EI CARIBOU-WW 4/77 RPR ANCW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2023-11-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46062830 | T2 EI CARIBOU-WW 4/77 RPR ANCW | ICW
LC | 126186986 | 014/179B | T2 DI DLTA-MTN GT JCT-MTN 14/179 COTTER | TABLEMTN | ETL.6750.INSL.NCER | 2023-05-19 | 2023-05-15 | 2024-06-25 | Late | 2024-05-14 | -42 | 2024-05-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46062589 | T2 DI DLTA-MTN GT JCT-MTN 14/179 COTTER | ICW
LC | 126186987 | 014/179B | T2 DI DELT-MN GT JCT-MN 14/179B RPR GYWW | TABLEMTN | ETL.6750.POLE.NWOD | 2023-05-19 | 2023-05-15 | 2024-06-25 | Late | 2024-05-14 | -42 | 2024-05-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062590 | T2 DI DELTA-MN GT JCT-MN 14/179B RPR GYW | ICW
LC | 126187048 | 012/092 | T2 DI CARIBOU-TBL MTN 12/92 BENT STEEL | TABLEMTN | ETL.4440.TOWR | 2023-05-19 | 2023-05-12 | 2024-06-06 | Late | 2024-05-11 | -26 | 2024-05-12 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072162 | T2 DI CARIBOU-TBL MTN 12/92 BENT STEEL | ICQ
LC | 126187068 | 005/004 | T2 EI LAYTONVILLE-COVELO 5/4L RPL POLE | WILLITS | ETL.7390.POLE.WDPS | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491306 | T2 DI LAYTONVILLE-COVELO 5/4R RPL POLE | 70Y
LC | 126187069 | 005/005 | T2 EI LAYTONVILLE-COVELO 5/5 RPR GYWW | WILLITS | ETL.7390.POLE.NWOD | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46219453 | T2 EI LAYTONVILLE-COVELO 5/5 RPR GYWW | ICW
LC | 126212948 | ;001/007 | T2 DI CARIBOU #2 ;001/007 COTTER | TABLEMTN | ETL.6280.INSL.NCER | 2023-05-23 | 2023-05-16 | 2023-07-22 | On-time | 2024-05-15 | 298 | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45805371 | T2 DI CARIBOU #2 ;001/007 COTTER | ICW
LC | 126187239 | 024/177 | T2 DI CRBOU-TBL MTN 24/177 COTTER | TABLEMTN | ETL.4440.INSL | 2023-05-19 | 2023-05-15 | 2024-06-05 | Late | 2024-05-14 | -22 | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46061151 | T2 DI CRBOU-TBL MTN 24/177 COTTER | ICS
LC | 126213006 | 009/184 | T2 DI CRBU-WSTWD-09/184 RMV VEG | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-23 | 2023-05-16 | 2024-05-15 | On-time | 2024-05-15 | 0 | 2024-05-16 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126213165 | 001/048 | T2 DI CSCD-BNTN-DSCHTS 1/48 RPL HRDD | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-23 | 2023-05-16 | 2024-05-15 | On-time | 2024-05-15 | 0 | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46062644 | T2 DI CSCD-BNTN-DSCHTS 1/48 RPL HRDD | ICW
LC | 126219975 | 005/041A | T2 DI BUTTE VLLEY-CARIBOU 5/41A RPR GYWS | TABLEMTN | ETL.1180.POLE.NWOD | 2023-05-24 | 2023-05-16 | 2024-04-23 | On-time | 2024-05-15 | 22 | 2024-05-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061159 | T2 DI BUTTE VLLEY-CARIBOU 5/41A RPR GYWS | ICS
LC | 126221071 | ;002/016 | T2 DI CARIBOU #2 ;2/16 RPR JUMP | TABLEMTN | ETL.6280.INSL.NCER | 2023-05-24 | 2023-05-16 | 2023-07-22 | On-time | 2024-05-15 | 298 | 2023-08-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45805374 | T2 DI CARIBOU #2 ;2/16 RPR JUMP | ICW
LC | 126221787 | 000/005 | T2 DI MOUNTAIN GATE TAP 00/05 RPR CNDW | TABLEMTN | ETL.7641.INSL.NCER | 2023-05-24 | 2023-05-16 | 2024-02-17 | On-time | 2024-05-15 | 88 | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46062489 | T2 DI MOUNTAIN GATE TAP 00/05 RPR CNDW | ICW
LC | 126188774 | 003/075 | T2 EI CARIBOU-WSWD 3/75C RPL STRW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519110 | T2 EI CARIBOU-WSWD 003/075 RPL POLE | 70Y
LC | 126189046 | 016/011 | T2 EI EXCHEQUER-MARIPOSA 16/011 RPL INSW | FRESNO | ETL.8640.INSL.NCER | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35506438 | T2 EI EXCHEQUER-MARIPOSA 16/011 RPL INSW | 93I
LC | 126222597 | :002/014 | T2 DI CARIBOU #2 :2/14 RPR JUMP | TABLEMTN | ETL.6280.INSL.CERA | 2023-05-25 | 2023-05-16 | 2023-07-14 | On-time | 2024-05-15 | 306 | 2023-08-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45805369 | T2 DI CARIBOU #2 :2/14 RPR JUMP | ICW
LC | 126189204 | 003/075 | T2 EI CARIBOU-WSWD 3/75R RPL STRW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519110 | T2 EI CARIBOU-WSWD 003/075 RPL POLE | 70Y
LC | 126230285 | 026/440 | T2 DI KSWCK-TRNTY 26/440 RPL HRDD | TABLEMTN | ETL.7270.POLE.NWOD | 2023-05-25 | 2023-05-16 | 2024-04-22 | On-time | 2024-05-15 | 23 | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46062662 | T2 DI KSWCK-TRNTY 26/440 RPL HRDD | ICW
LC | 126189263 | ;002/000A | T2 DI CARIBOU #2 ;002/000A RPR JUMW | TABLEMTN | ETL.6280.INSL.NCER | 2023-05-19 | 2023-05-16 |  | Late | 2024-05-15 |  | 2023-08-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46062595 | T2 DI CARIBOU #2 ;002/000A RPR JUMW | ICW
LC | 126189285 | 020/004A | T2 EI TRINITY-MAPLE CREEK 20/4A RPL ROAD | EUREKA | ETL.8170.POLE.NWOD | 2023-05-19 | 2023-05-19 | 2024-05-20 | Late | 2024-05-18 | -2 | 2024-05-19 | 374 | TLR | PATR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Road | Replace | 31679032 | T2 EI TRINITY-MAPLE CREEK 20/4A RPL ROAD | 71Y
LC | 126189293 | 005/009 | T2 DI TRINITY-MAPLE CREEK 5/09L RMV VEG | TABLEMTN | ETL.8170.POLE.STPS | 2023-05-19 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126189414 | 004/033A | T2 DI BTT VLLY-CARIBOU 4/033A RPR GYWS | TABLEMTN | ETL.1180.POLE.NWOD | 2023-05-19 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061155 | T2 DI BTT VLLY-CARIBOU 4/033A RPR GYWS | ICS
LC | 126240154 | 014/305 | T2 DI LAKEVILLE #2 14/305 RPR JMPS | LAKEVLLE | ETL.7340.INSL.NCER | 2023-05-27 | 2023-05-16 | 2024-04-20 | On-time | 2024-05-15 | 25 | 2024-05-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46079110 | T2 DI LAKEVILLE #2 14/305 RPR JMPS | ICS
LC | 126149841 | 001/045 | T2 EI CSCD-BNTN-DSCHTS 1/45 RPR GYWW | TABLEMTN | ETL.6310.POLE.NWOD | 2023-05-17 | 2023-05-17 | 2024-05-15 | On-time | 2024-05-16 | 1 | 2024-05-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062671 | T2 EI CSCD-BNTN-DSCHTS 1/45 RPR GYWW | ICW
LC | 126189691 | 081/415 | T2 DI MALIN-RND MNTN #2 81/415 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2023-05-19 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46050973 | T2 DI MALIN-RND MNTN #2 81/415 RPR INSS | ICS
LC | 126149842 | 001/045 | T2 EI CSCD-BNTN-DSCHTS 1/45 RPR JUMW | TABLEMTN | ETL.6310.INSL.CERA | 2023-05-17 | 2023-05-17 | 2024-05-15 | On-time | 2024-05-16 | 1 | 2024-05-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46062672 | T2 EI CSCD-BNTN-DSCHTS 1/45 RPR JUMW | ICW
LC | 126189705 | 003/075 | T2 EI CARIBOU-WSWD 3/75L RPL STRW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519110 | T2 EI CARIBOU-WSWD 003/075 RPL POLE | 70Y
LC | 126149873 | 000/008 | T2 EI LAURLS-OTTR 0/8 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-17 | 2023-05-17 | 2024-03-16 | On-time | 2024-05-16 | 61 | 2024-05-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487993 | T2 EI LAURLS-OTTR 0/8 RPL STRW | 70Y
LC | 126189972 | 012/097 | T2 DI CARIBOU-TBL MTN 12/97 RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2023-05-19 | 2023-05-12 | 2024-06-07 | Late | 2024-05-11 | -27 | 2024-05-12 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35508877 | T2 EI CARIBOU-TABLE MTN RPL INSS 12 STRT | 93K
LC | 126190351 | 020/534 | T2 DI CARIBOU #2 20/534 CANCEL | TABLEMTN | ETL.6280.INSL.NCER | 2023-05-19 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35515869 | T2 DI CARIBOU #2 020/534 RPL INSW | 93I
LC | 126149989 | :019/097 | T2 EI CHC-SALINAS-SOLED :19/97 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-17 | 2023-05-17 | 2024-02-01 | On-time | 2024-05-16 | 105 | 2024-05-17 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081532 | T2 EI CHC-SALINAS-SOLED :19/97 RPL RPTS | ICB
LC | 126150378 | :018/096 | T2 EI CHC-SALINAS-SOLEDA :18/96 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-17 | 2023-05-17 | 2024-02-02 | On-time | 2024-05-16 | 104 | 2024-05-17 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081534 | T2 EI CHC-SALINAS-SOLEDA :18/96 RPL RPTS | ICB
LC | 126150906 | 038/329 | T2 EI PIT #1-COTTONWOOD 38/329 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-17 | 2023-05-17 | 2024-05-08 | On-time | 2024-05-16 | 8 | 2024-05-17 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46057509 | T2 EI PIT #1-COTTONWOOD 38/329 UNBURY | ICQ
LC | 126190390 | 035/256 | T2 EI MIDDLE FRK-GOLD 035/256 RMV ENCR | SACTO | ETL.5140.TOWR | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2023-11-19 | 931 | TLS | INSP | E - Schd Compl Yr 0 | Open | TR2 | Encroachment | Right of Way | Remove
LC | 126151109 | :018/095 | T2 EI CHC-SALINAS-SOLED :18/95 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-17 | 2023-05-17 | 2024-03-01 | On-time | 2024-05-16 | 76 | 2024-05-17 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081543 | T2 EI CHC-SALINAS-SOLED :18/95 RPL RPTS | ICB
LC | 126190526 | 011/129 | T2 EI DRUM-SUMMIT #1 11/129C RPR CNDW | SACTO | ETL.1440.INSL.NCER | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46062844 | T2 EI DRUM-SUMMIT #1 11/129C RPR CNDW | ICW
LC | 126190528 | 011/129 | T2 EI DRUM-SUMMIT #1 11/129R RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062845 | T2 EI DRUM-SUMMIT #1 11/129R RPR GYWW | ICW
LC | 126190534 | 011/129 | T2 EI DRUM-SUMMIT #1 11/129L RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062846 | T2 EI DRUM-SUMMIT #1 11/129L RPR GYWW | ICW
LC | 126151338 | 000/010 | T2 EI LAURLS-OTTR 0/10 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-17 | 2023-05-17 | 2024-03-16 | On-time | 2024-05-16 | 61 | 2024-05-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487993 | T2 EI LAURLS-OTTR 0/8 RPL STRW | 70Y
LC | 126190821 | 036/005 | T2 EI TRNTY-MPL CRK 036/005R RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-19 | 2023-05-19 |  | Late | 2024-05-18 |  | 2023-11-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170740 | T2 EI TRNTY-MPL CRK 036/005R RPR GYWW | ICW
LC | 126191958 | 027/194 | T2 DI CARIBOU-TBL MTN 27/194 RPL INSS | TABLEMTN | ETL.4440.INSL | 2023-05-20 | 2023-05-12 | 2024-06-12 | Late | 2024-05-11 | -32 | 2024-05-12 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35508877 | T2 EI CARIBOU-TABLE MTN RPL INSS 12 STRT | 93K
LC | 126192112 | 69 | T2 CLAY-MARTEL 34/518 RPR JMPW | VICTOR | ETL.8250.SWIT | 2023-05-20 | 2023-05-20 | 2024-06-18 | Late | 2024-05-19 | -30 | 2024-05-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46069023 | T2 CLAY-MARTEL 34/518 RPR JMPW | ICW
LC | 126151365 | 008/163 | T2 EI CTONWD-RD BLF 8/163 COTTER KEY | TABLEMTN | ETL.6660.INSL.NCER | 2023-05-17 | 2023-05-17 | 2024-04-10 | On-time | 2024-05-16 | 36 | 2024-05-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46062495 | T2 EI CTONWD-RD BLF 8/163 COTTER KEY | ICW
LC | 126192331 | 016/122 | T2 DI CARIBOU-TABLE MTN 16/122 RPR SHLS | TABLEMTN | ETL.4440.TOWR | 2023-05-20 | 2023-05-12 | 2024-06-07 | Late | 2024-05-11 | -27 | 2024-05-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46061142 | T2 DI CARIBOU-TABLE MTN 16/122 RPR SHLS | ICS
LC | 126151651 | 019/010 | T2 WV MNDCNO-PHLO J-HPLND 19/10 RPL INSW | WILLITS | ETL.7520.INSL.CERA | 2023-05-17 | 2023-05-17 | 2024-03-20 | On-time | 2024-05-16 | 57 | 2024-05-17 | 508T | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35506671 | T2 WV MNDCNO-PHLO J-HPLND 19/10 RPL INSW | 93I
LC | 126192477 | 066/481 | T2 EI BRIDGEVILE-CTTNWD 66/481R COTTER | EUREKA | ETL.1110.INSL.NCER | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46171674 | T2 EI BRIDGEVILE-CTTNWD 66/481L COTTER | ICW
LC | 126192486 | 002/055 | T2 EI HAT CRK #1-WESTWD 2/55 RMV STEP | TABLEMTN | ETL.7030.POLE.NWOD | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46062869 | T2 EI HAT CRK #1-WESTWD 2/55 RMV STEP | ICW
LC | 126152647 | 010/043 | T2 EI TESLA-METCALF 10/43 BNT STEEL | METCALF | ETL.6110.TOWR | 2023-05-17 | 2023-05-17 | 2024-04-12 | On-time | 2024-05-16 | 34 | 2024-05-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46059041 | T2 EI TESLA-METCALF 10/43 BNT STEEL | ICQ
LC | 126152859 | 002/053 | T2 EI CASCDE-BENTON-DSCHTS 2/53 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-17 | 2023-05-17 | 2023-08-14 | On-time | 2024-05-16 | 276 | 2023-11-17 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31650672 | T2 EI CASCDE-BENTON-DSCHTS 2/53 RPL STRW | 70Y
LC | 126192634 | 066/481 | T2 EI BRIDGEVILE-CTTNWD 66/481L COTTER | EUREKA | ETL.1110.INSL.NCER | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46171674 | T2 EI BRIDGEVILE-CTTNWD 66/481L COTTER | ICW
LC | 126152871 | 008/177 | T2 EI CTNWD-RED BLUFF 8/177 RPR WDPKR | TABLEMTN | ETL.6660.POLE.WOOD | 2023-05-17 | 2023-05-17 | 2024-04-10 | On-time | 2024-05-16 | 36 | 2024-05-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062496 | T2 EI CTNWD-RED BLUFF 8/177 RPR WDPKR | ICW
LC | 126152923 | 037/325 | T2 EI PIT #1-COTTONWOOD 37/325 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-17 | 2023-05-17 | 2024-05-08 | On-time | 2024-05-16 | 8 | 2024-05-17 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46057507 | T2 EI PIT #1-COTTONWOOD 37/325 UNBURY | ICQ
LC | 126153032 | 001/004 | T2 EI LAURLS-OTTR 1/4 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-17 | 2023-05-17 | 2024-01-17 | On-time | 2024-05-16 | 120 | 2024-05-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35489959 | T2 EI LAURLS-OTTR 1/1 RPL STRW | 70Y
LC | 126193061 | 012/005 | T2 EI MNDCN-WLLTS-FRT BRGG 12/5 RPR POLE | WILLITS | ETL.7550.POLE.WOOD | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46214143 | T2 EI MNDCN-WLLTS-FRT BRGG 12/5 RPR POLE | ICW
LC | 126153098 | 037/326 | T2 EI PIT #1-COTTONWOOD 37/326 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-17 | 2023-05-17 | 2024-05-08 | On-time | 2024-05-16 | 8 | 2024-05-17 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46057508 | T2 EI PIT #1-COTTONWOOD 37/326 UNBURY | ICQ
LC | 126153131 | :017/092 | T2 EI CHC-SALINAS-SOLED :17/92 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-17 | 2023-05-17 | 2024-02-20 | On-time | 2024-05-16 | 86 | 2024-05-17 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081545 | T2 EI CHC-SALINAS-SOLED :17/92 RPL RPTS | ICB
LC | 126193374 | 036/262 | T2 EI MID FORK-GOLD HILL 36/262 RPL INSS | SACTO | ETL.5140.INSL | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35508879 | T2 EI MID FORK-GOLD HILL 36/262 RPL INSS | 93K
LC | 126153155 | 005/118 | T2 WV KILARC-DESCHUTES 5/118 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-05-17 | 2023-05-17 | 2024-04-03 | On-time | 2024-05-16 | 43 | 2024-05-17 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515350 | T2 EI KILARC-DESCHUTES 4/101 RPL POLE | 70Y
LC | 126153186 | :018/093 | T2 EI CHC-SALINAS-SOLEDAD :18/93 COTTER | MOSSLNDG | ETL.2910.INSL.CERA | 2023-05-17 | 2023-05-17 | 2024-02-01 | On-time | 2024-05-16 | 105 | 2024-05-17 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46079095 | T2 EI CHC-SALINAS-SOLEDAD :18/93 COTTER | ICS
LC | 126193558 | 018/194 | T2 EI WOODLEAF-PALERMO 18/194 RPL POLE | TABLEMTN | ETL.4220.POLE.WOOD | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525903 | T2 DI WDLEF-PLRMO RPL 5 STRW | 70Y
LC | 126153514 | 003/066 | T2 WV TEMPLTN-ATSCDRO 03/66 RPL POLE | PISMOBCH | ETL.9410.POLE.WOOD | 2023-05-17 | 2023-05-17 | 2024-05-14 | On-time | 2024-05-16 | 2 | 2023-08-17 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35523960 | T2 WV TEMPLTN-ATSCDRO 03/66 RPL POLE | 70Y
LC | 126193765 | 002/059 | T2 EI HAT CREEK #1-WESTWD 2/59 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514556 | T2 EI HAT CREEK #1-WESTWD 2/59 RPL STRW | 70Y
LC | 126193767 | 002/061 | T2 EI HAT CRK #1-WESTWD 2/061 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514556 | T2 EI HAT CREEK #1-WESTWD 2/59 RPL STRW | 70Y
LC | 126193769 | 053/000 | T2 EI FORT ROSS-GUALALA 53/00 RPR GYWW | LAKEVLLE | ETL.6980.POLE.NWOD | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073727 | T2 EI FORT ROSS-GUALALA 53/00 RPR GYWW | ICW
LC | 126153681 | 015/080 | T2 EI BALCH-SANGER 15/80 RPR INSS | FRESNO | ETL.1050.INSL.CERA | 2023-05-17 | 2023-05-17 | 2024-04-12 | On-time | 2024-05-16 | 34 | 2024-05-17 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46058734 | T2 EI BALCH-SANGER 15/80 RPR INSS | ICS
LC | 126193963 | 002/052 | T2 EI CARIBOU-WSTWD 2/52 RPR ANCW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46062868 | T2 EI CARIBOU-WSTWD 2/52 RPR ANCW | ICW
LC | 126154281 | 001/006 | T2 EI LAURLS-OTTR 1/6 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-17 | 2023-05-17 | 2024-01-17 | On-time | 2024-05-16 | 120 | 2024-05-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35489959 | T2 EI LAURLS-OTTR 1/1 RPL STRW | 70Y
LC | 126194151 | 011/008 | T2 EI MNDCN-WLLTS-FRT BRGG 11/8 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521521 | T2 EI MNDCNO-WLLTS-FRT BRGG 7/5 RPL POLE | 70Y
LC | 126194178 | 005/104 | T2 EI HT CRK #1-WSTWD 5/104 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514557 | T2 EI HT CRK #1-WSTWD 5/104 RPL STRW | 70Y
LC | 126194262 | 011/007 | T2 EI MNDCN-WLLTS-FRT BRGG 11/7 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521521 | T2 EI MNDCNO-WLLTS-FRT BRGG 7/5 RPL POLE | 70Y
LC | 126194322 | 019/136A | T2 DI CARIBOU-TABLE MTN 19/136A RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-05-20 | 2023-05-12 | 2024-06-05 | Late | 2024-05-11 | -25 | 2024-05-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Replace | 46061143 | T2 DI CARIBOU-TABLE MTN 19/136A RPR GYWS | ICS
LC | 126194481 | 035/003 | T2 EI TRINTY-MPLE CRK 35/03L RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170573 | T2 EI TRINTY-MPLE CRK 35/03L RPR GYWW | ICW
LC | 126194483 | 036/001 | T2 EI TRINTY-MPLE CRK 36/01R RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170577 | T2 EI TRINTY-MPLE CRK 36/01L RPR GYWW | ICW
LC | 126194484 | 035/003 | T2 EI TRINTY-MPLE CRK 35/03 RPR INSW | EUREKA | ETL.8170.INSL.NCER | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46170573 | T2 EI TRINTY-MPLE CRK 35/03L RPR GYWW | ICW
LC | 126194497 | 036/001 | T2 EI TRINTY-MPLE CRK 36/01L RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170577 | T2 EI TRINTY-MPLE CRK 36/01L RPR GYWW | ICW
LC | 126194499 | 035/003 | T2 EI TRINTY-MPLE CRK 35/03C RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170573 | T2 EI TRINTY-MPLE CRK 35/03L RPR GYWW | ICW
LC | 126194631 | 005/107 | T2 EI HAT CRK #1-WSTWD 5/107 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514557 | T2 EI HT CRK #1-WSTWD 5/104 RPL STRW | 70Y
LC | 126154326 | 001/007 | T2 EI LAURLS-OTTR 1/7 RPR INSW | MOSSLNDG | ETL.7380.INSL | 2023-05-17 | 2023-05-17 | 2024-01-17 | On-time | 2024-05-16 | 120 | 2024-05-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081177 | T2 EI LAURLS-OTTR 1/7 RPR INSW | ICW
LC | 126154531 | 001/001 | T2 EI LAURLS-OTTR 1/1 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-17 | 2023-05-17 | 2024-01-16 | On-time | 2024-05-16 | 121 | 2024-05-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35489959 | T2 EI LAURLS-OTTR 1/1 RPL STRW | 70Y
LC | 126154533 | :016/088 | T2 EI CHC-SALINAS-SOLED :16/88 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-17 | 2023-05-17 | 2024-02-20 | On-time | 2024-05-16 | 86 | 2024-05-17 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081547 | T2 EI CHC-SALINAS-SOLED :16/88 RPL RPTS | ICB
LC | 126194946 | 052/007 | T2 EI FORT ROSS-GUALALA 52/07 RPL ANCW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35517027 | T2 EI FORT ROSS-GUALALA 52/07 RPL ANCW | 93E
LC | 126194990 | 052/001 | T2 EI FORT ROSS-GUALALA 52/01 RPL POLE | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518743 | T2 EI FORT ROSS-GUALALA 52/01 RPL POLE | 70Y
LC | 126194991 | 013/277 | T2 EI CARIBOU-WESTWOOD 13/277 RPR STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-20 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062870 | T2 EI CARIBOU-WESTWOOD 13/277 RPR STRW | ICW
LC | 126154703 | 007/083C | T2 EI DRUM-SUMMIT #1 7/83C COMPLETE | SACTO | ETL.1440.POLE.NWOD | 2023-05-17 | 2023-05-17 | 2024-05-15 | On-time | 2024-05-16 | 1 | 2024-05-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062673 | T2 EI DRUM-SUMMIT #1 007/083C RPR GYWW | ICW
LC | 126154736 | 001/009 | T2 EI LAURLS-OTTR 1/9 RPL POLE | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-17 | 2023-05-17 | 2024-01-31 | On-time | 2024-05-16 | 106 | 2024-05-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491360 | T2 LAURELES-OTTER 001/008 RPL POLE | 70Y
LC | 126155528 | :016/085 | T2 EI CHC-SALINAS-SOLE :16/85 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-17 | 2023-05-17 | 2024-02-21 | On-time | 2024-05-16 | 85 | 2024-05-17 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081551 | T2 EI CHC-SALINAS-SOLE :16/85 RPL RPTS | ICB
LC | 126198231 | 022/008 | T2 LAYTONVILLE-WILLITS 22/008 RPR COND | WILLITS | ETL.8360.INSL.CERA | 2023-05-22 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 45770767 | T2 LAYTONVILLE-WILLITS 22/008 RPR COND | ICW
LC | 126155581 | 004/077 | T2 WV TEMPLTN-ATSCDRO 04/77 RPL POLE | PISMOBCH | ETL.9410.POLE.WOOD | 2023-05-17 | 2023-05-17 | 2024-05-14 | On-time | 2024-05-16 | 2 | 2024-05-17 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35523960 | T2 WV TEMPLTN-ATSCDRO 03/66 RPL POLE | 70Y
LC | 126198235 | 069/498 | T2 EI BRIDGEVILE-CTTNWD 69/498R RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-22 | 2023-05-20 |  | Late | 2024-05-19 |  | 2023-11-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505102 | T2 EI BRIDGEVILE-CTTNWD 69/497L RPL STRW | 70Y
LC | 126198237 | 069/497 | T2 EI BRIDGEVILE-CTTNWD 69/497L RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-22 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505102 | T2 EI BRIDGEVILE-CTTNWD 69/497L RPL STRW | 70Y
LC | 126155654 | :016/086 | T2 EI CHC-SALINAS-SOLE :16/86 RPR RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-17 | 2023-05-17 | 2024-02-20 | On-time | 2024-05-16 | 86 | 2024-05-17 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081553 | T2 EI CHC-SALINAS-SOLE :16/86 RPR RPTS | ICB
LC | 126198270 | 069/497 | T2 EI BRIDGEVILE-CTTNWD 69/497R RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-22 | 2023-05-20 |  | Late | 2024-05-19 |  | 2024-05-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505102 | T2 EI BRIDGEVILE-CTTNWD 69/497L RPL STRW | 70Y
LC | 126198281 | 069/498 | T2 EI BRIDGEVILE-CTTNWD 69/498L RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-22 | 2023-05-20 |  | Late | 2024-05-19 |  | 2023-11-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505102 | T2 EI BRIDGEVILE-CTTNWD 69/497L RPL STRW | 70Y
LC | 126199048 | 011/003 | T2 EI MNDCN-WLLTS-FRT BRGG 11/3 CANCEL | WILLITS | ETL.7550.POLE.WOOD | 2023-05-22 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521521 | T2 EI MNDCNO-WLLTS-FRT BRGG 7/5 RPL POLE | 70Y
LC | 126199370 | 010/203 | T2 EI HAT CREEK #1-WSTWD 10/203 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-06-10 | Late | 2024-05-21 | -20 | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514553 | T2 EI HAT CREEK #1-WSTWD 10/203 RPL STRW | 70Y
LC | 126199573 | 046/008 | T2 EI FORT ROSS-GUALALA 46/008 RPR STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-22 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46073732 | T2 EI FORT ROSS-GUALALA 46/008 RPR STRW | ICW
LC | 126199574 | 010/117 | T2 EI DRUM-SUMMIT #2 10/117C RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2023-05-22 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484103 | T2 EI DRUM-SUMMIT #2_010/117C RPL POLE | 70Y
LC | 126156015 | :016/084 | T2 EI CHC-SALINAS-SOLE :16/84 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-17 | 2023-05-17 | 2024-02-21 | On-time | 2024-05-16 | 85 | 2024-05-17 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081555 | T2 EI CHC-SALINAS-SOLE :16/84 RPL RPTS | ICB
LC | 126199875 | 011/006 | T2 EI MNDCN-WLLT-FRT BRGG 11/6 WASH INSS | WILLITS | ETL.7550.INSL.NCER | 2023-05-22 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 622 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Contaminated | Insulator | Ground Wash | 46214144 | T2 EI MNDCN-WLLTS-FRT BRGG 11/6 WASH INS | ICD
LC | 126199878 | 010/206 | T2 EI HAT CREEK #1-WSTWD 10/206 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-06-10 | Late | 2024-05-21 | -20 | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514558 | T2 EI HAT CREEK #1-WSTWD 10/206 RPL STRW | 70Y
LC | 126156670 | 078/399 | T2 EI MALIN-ROUND MTN #2 78/399 COMPLETE | TABLEMTN | ETL.6020.TOWR | 2023-05-17 | 2023-05-17 | 2024-02-26 | On-time | 2024-05-16 | 80 | 2024-05-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46057501 | T2 EI MALIN-ROUND MTN #2 78/399 RPR GYWT | ICS
LC | 126156874 | 014/076 | T2 EI BALCH-SANGER 14/76 RPL INSS | FRESNO | ETL.1050.INSL.CERA | 2023-05-17 | 2023-05-17 | 2024-04-12 | On-time | 2024-05-16 | 34 | 2024-05-17 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510274 | T2 DI BALCH-SANGER 04/27 RPL INSS | 93K
LC | 126200401 | 010/208 | T2 EI HAT CREEK #1-WSTWD 10/208 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-06-10 | Late | 2024-05-21 | -20 | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514558 | T2 EI HAT CREEK #1-WSTWD 10/206 RPL STRW | 70Y
LC | 126200511 | 001/027 | T2 EI CARBOU-WESTWD 01/27L RPR GYWW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-22 | 2023-05-22 |  | Late | 2024-05-21 |  | 2023-11-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073800 | T2 EI CARBOU-WESTWD 01/27L RPR GYWW | ICW
LC | 126200523 | 001/027 | T2 EI CARBOU-WESTWD 01/27R RPR GYWW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-22 | 2023-05-22 |  | Late | 2024-05-21 |  | 2023-11-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073801 | T2 EI CARBOU-WESTWD 01/27R RPR GYWW | ICW
LC | 126200594 | 046/004 | T2 EI FORT ROSS-GUALALA 46/004 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-22 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35518742 | T2 EI FORT ROSS-GUALALA 46/004 RPL STRW | 70Y
LC | 126200599 | 010/210 | T2 EI HAT CREEK #1-WSTWD 10/210 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-06-11 | Late | 2024-05-21 | -21 | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514558 | T2 EI HAT CREEK #1-WSTWD 10/206 RPL STRW | 70Y
LC | 126156875 | 014/076 | T2 EI BALCH-SANGER 014/076 UNBURY | FRESNO | ETL.1050.TOWR | 2023-05-17 | 2023-05-17 | 2024-01-08 | On-time | 2024-05-16 | 129 | 2024-05-17 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46070737 | T2 EI BALCH-SANGER 014/076 UNBURY | ICQ
LC | 126201130 | 011/212 | T2 EI HAT CREEK #1-WSTWD 11/212 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-06-12 | Late | 2024-05-21 | -22 | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514559 | T2 EI HAT CREEK #1-WSTWD 11/212 RPL STRW | 70Y
LC | 126201140 | 010/211 | T2 EI HAT CREEK #1-WSTWD 10/211 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-06-11 | Late | 2024-05-21 | -21 | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514558 | T2 EI HAT CREEK #1-WSTWD 10/206 RPL STRW | 70Y
LC | 126201540 | 001/024 | T2 EI CARIBOU-WESTWD 1/24 RPL INSW | TABLEMTN | ETL.6300.INSL.NCER | 2023-05-22 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35519107 | T2 EI CARIBOU-WESTWOOD 01/024 RPL INSW | 93I
LC | 126201541 | 001/024 | T2 EI CARIBOU-WESTWD 1/24 RPR ANCW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-22 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46073799 | T2 EI CARIBOU-WESTWOOD 01/024 RPR ANCHOR | ICW
LC | 126201620 | 001/023 | T2 EI CARIBOU-WESTWOOD 01/023 RPR ANCW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-22 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46073798 | T2 EI CARIBOU-WESTWOOD 01/023 RPR ANCW | ICW
LC | 126201832 | 011/218 | T2 EI HAT CREEK #1-WSTWD 11/218 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-06-12 | Late | 2024-05-21 | -22 | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514559 | T2 EI HAT CREEK #1-WSTWD 11/212 RPL STRW | 70Y
LC | 126202001 | 011/219 | T2 EI HAT CREEK #1-WSTWD 11/219 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-06-13 | Late | 2024-05-21 | -23 | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514559 | T2 EI HAT CREEK #1-WSTWD 11/212 RPL STRW | 70Y
LC | 126156876 | 014/075 | T2 EI BALCH-SANGER 014/075 UNBURY | FRESNO | ETL.1050.TOWR | 2023-05-17 | 2023-05-17 | 2024-01-08 | On-time | 2024-05-16 | 129 | 2024-05-17 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46070736 | T2 EI BALCH-SANGER 014/075 UNBURY | ICQ
LC | 126158482 | 005/032 | T2 EI SBRNT STNDRD OL SS#2 5/32 HANGER | CONCORD | ETL.3800.TOWR | 2023-05-18 | 2023-05-17 | 2023-05-31 | On-time | 2024-05-16 | 351 | 2024-05-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45775232 | T2 EI SBRNT STNDRD OL SS#2 5/32 HANGER | ICQ
LC | 126202138 | 011/220 | T2 EI HAT CREEK #1-WSTWD 11/220 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-06-13 | Late | 2024-05-21 | -23 | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514559 | T2 EI HAT CREEK #1-WSTWD 11/212 RPL STRW | 70Y
LC | 126202195 | 053/1036 | T2 EI HAT CRK #1-WESTWD 53/1036 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-22 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514875 | T2 EI HAT CRK #1-WESTWD 53/1036 RPL POLE | 70Y
LC | 126221437 | 042/338B | T2 DI BRDGVLL-CTTNWD 42/338B RPR GYWS | TABLEMTN | ETL.1110.POLE.NWOD | 2023-05-24 | 2023-05-17 | 2024-04-23 | On-time | 2024-05-16 | 23 | 2024-05-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061172 | T2 DI BRDGVLL-CTTNWD 42/338B RPR GYWS | ICS
LC | 126202295 | 011/221 | T2 EI HAT CREEK #1-WSTWD 11/221 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-06-13 | Late | 2024-05-21 | -23 | 2024-05-22 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35514680 | T2 EI HAT CREEK #1-WSTWD 11/221 REFRAME | 93E
LC | 126202373 | 009/007 | T2 FULTON-HOPLAND 9/7 RPL STRW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-05-22 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35521253 | T2 FULTON-HOPLAND 9/007 RPL STRW | 70Y
LC | 126221503 | 000/005 | T2 DI BUTTE VALLEY-CARIBOU 0/5 BNT STEEL | TABLEMTN | ETL.1180.TOWR | 2023-05-24 | 2023-05-17 | 2024-05-13 | On-time | 2024-05-16 | 3 | 2024-05-17 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072180 | T2 DI BUTTE VALLEY-CARIBOU 0/5 BNT STEEL | ICQ
LC | 126221579 | 002/007 | T2 DI FRUITLAND TP 2/7 RPR ANCW | EUREKA | ETL.6221.POLE.NWOD | 2023-05-24 | 2023-05-17 | 2023-06-12 | On-time | 2024-05-16 | 339 | 2023-11-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45805730 | T2 DI FRUITLAND TP 2/7 RPR ANCW | ICW
LC | 126202524 | 011/222 | T2 EI HAT CREEK #1-WSTWD 11/222 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-06-14 | Late | 2024-05-21 | -24 | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35514860 | T2 EI HAT CREEK #1-WSTWD 11/222 RPL STRW | 70Y
LC | 126221593 | 021/010 | T2 DI BRDGVLL-GRBRVLL 21/10 RPR JMPW | EUREKA | ETL.6220.INSL.NCER | 2023-05-24 | 2023-05-17 | 2023-11-27 | On-time | 2024-05-16 | 171 | 2023-08-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45825062 | T2 DI BRDGVLL-GRBRVLL 21/10 RPR JMPW | ICW
LC | 126202607 | 105/002 | T2 HUMBOLDT-TRINITY 105/2R RPR POLE | EUREKA | ETL.1820.POLE.WDPS | 2023-05-22 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46096664 | T2 HUMBOLDT-TRINITY 105/002R RPR POLE | ICW
LC | 126202677 | 045/006 | T2 EI FORT ROSS-GUALALA 45/006 RPR ANCW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-06-24 | Late | 2024-05-21 | -34 | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46073730 | T2 EI FORT ROSS-GUALALA 45/006 RPR ANCW | ICW
LC | 126202896 | 011/225 | T2 EI HAT CREEK #1-WSTWD 11/225 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-06-14 | Late | 2024-05-21 | -24 | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514860 | T2 EI HAT CREEK #1-WSTWD 11/222 RPL STRW | 70Y
LC | 126203137 | 034/000 | T2 EI TRINTY-MPLE CRK 34/0C RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-22 | 2023-05-22 | 2024-06-13 | Late | 2024-05-21 | -23 | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172098 | T2 EI TRINTY-MPLE CRK 34/0C RPR GYWW | ICW
LC | 126203301 | 011/228 | T2 EI HAT CREEK #1-WSTWD 11/228 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-06-13 | Late | 2024-05-21 | -23 | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514860 | T2 EI HAT CREEK #1-WSTWD 11/222 RPL STRW | 70Y
LC | 126203561 | 010/120 | T2 EI DRUM-SUMMIT#2 10/120R RPR STRW | SACTO | ETL.1450.POLE.WDPS | 2023-05-22 | 2023-05-22 | 2024-06-26 | Late | 2024-05-21 | -36 | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46101305 | T2 EI DRUM-SUMMIT#2 10/120 RPR STRW | ICW
LC | 126221693 | 007/087B | T2 DI DRUM-SUMMIT #2 7/87B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-05-24 | 2023-05-17 | 2024-05-16 | On-time | 2024-05-16 | 0 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062676 | T2 DI DRUM-SUMMIT #2 007/087B RPR GYWW | ICW
LC | 126204171 | 053/1032 | T2 EI HAT CRK #1-WESTWD 53/1032 RPR SPLW | TABLEMTN | ETL.7030.INSL | 2023-05-22 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Replace | 46075850 | T2 EI HAT CRK #1-WESTWD 53/1032 RPR SPLW | ICW
LC | 126204216 | 012/231 | T2 EI HAT CREK #1-WESTWD 12/231 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-06-13 | Late | 2024-05-21 | -23 | 2024-05-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514861 | T2 EI HAT CREK #1-WESTWD 12/231 RPL STRW | 70Y
LC | 126221762 | 042/338C | T2 DI BRDGVLL-CTTNWD 042/338C RPR GYWS | TABLEMTN | ETL.1110.POLE.NWOD | 2023-05-24 | 2023-05-17 | 2024-04-23 | On-time | 2024-05-16 | 23 | 2024-05-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061175 | T2 DI BRDGVLL-CTTNWD 042/338C RPR GYWS | ICS
LC | 126221773 | 000/013 | T2 DI FRUITLAND TP 0/13 COTTER | EUREKA | ETL.6221.INSL.CERA | 2023-05-24 | 2023-05-17 | 2024-03-28 | On-time | 2024-05-16 | 49 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46203460 | T2 DI FRUITLAND TP 0/13 COTTER | ICW
LC | 126204821 | 035/261 | T2 EI CARIBOU-TABL MTN 35/261 RPR INSS | TABLEMTN | ETL.4440.INSL | 2023-05-22 | 2023-05-22 | 2024-06-07 | Late | 2024-05-21 | -17 | 2024-05-22 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46073796 | T2 EI CARIBOU-TABL MTN 35/261 RPR INSS | ICS
LC | 126221823 | 042/338A | T2 DI BRDGVLL-CTTNWD 042/338A RPR GYWS | TABLEMTN | ETL.1110.POLE.NWOD | 2023-05-24 | 2023-05-17 | 2024-04-23 | On-time | 2024-05-16 | 23 | 2024-05-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061171 | T2 DI BRDGVLL-CTTNWD 042/338A RPR GYWS | ICS
LC | 126229579 | 007/085 | T2 DI DRUM SUMMIT#1 07/085 RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2023-05-25 | 2023-05-17 | 2024-05-15 | On-time | 2024-05-16 | 1 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062674 | T2 DI DRUM SUMMIT#1 07/085 RPR STRW | ICW
LC | 126229610 | 007/085 | T2 DI DRUM SUMMIT#1 07/085 RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2023-05-25 | 2023-05-17 | 2024-05-15 | On-time | 2024-05-16 | 1 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062675 | T2 DI DRUM SUMMIT#1 07/085 RPR STRW | ICW
LC | 126230071 | 001/002 | T2 DI FRUITLAND TAP 01/002 RPR GYWW | EUREKA | ETL.6221.POLE.NWOD | 2023-05-25 | 2023-05-17 | 2024-05-05 | On-time | 2024-05-16 | 11 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46179249 | T2 DI FRUITLAND TAP 01/002 RPR GYWW | ICW
LC | 126230074 | 001/002 | T2 DI FRUITLAND TAP 01/002 COA | EUREKA | ETL.6221.POLE.NWOD | 2023-05-25 | 2023-05-17 | 2024-05-06 | On-time | 2024-05-16 | 10 | 2024-05-17 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35515944 | T2 DI FRUITLAND TAP 01/002 RPL ANCW | 93E
LC | 126205300 | 046/005 | T2 DI HUMBOLDT-TRINITY 46/5 RPR JMPW | EUREKA | ETL.1820.INSL.NCER | 2023-05-22 | 2023-05-16 |  | Late | 2024-05-15 |  | 2023-08-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46096520 | T2 DI HUMBOLDT-TRINITY 46/5 RPR JMPW | ICW
LC | 126230083 | 022/155 | T2 DI CARIBOU-TABLE MTN 22/155L RPR GYWS | TABLEMTN | ETL.4440.POLE.STPS | 2023-05-25 | 2023-05-17 | 2024-04-17 | On-time | 2024-05-16 | 29 | 2024-05-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061166 | T2 DI CARIBOU-TABLE MTN 22/155L RPR GYWS | ICS
LC | 126230084 | 022/155 | T2 DI CARIBOU-TABLE MTN 22/155R RPR GYWS | TABLEMTN | ETL.4440.POLE.STPS | 2023-05-25 | 2023-05-17 | 2024-04-17 | On-time | 2024-05-16 | 29 | 2024-05-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061167 | T2 DI CARIBOU-TABLE MTN 22/155R RPR GYWS | ICS
LC | 126205461 | 001/049 | T2 DI CSCD-BNTN-DSCHTS 1/49 RPL POLE | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-22 | 2023-05-16 | 2024-05-19 | Late | 2024-05-15 | -4 | 2024-05-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521348 | T2 DI CSCD-BNTN-DSCHTS 1/49 RPL POLE | 70Y
LC | 126205716 | 004/040 | T2 PIT #1-COTTONWOOD 4/040 RMV ENRCH | TABLEMTN | ETL.5390.TOWR | 2023-05-23 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 931 | TLS |  | E - Schd Compl Yr 0 | Open | TR2 | Encroachment | Right of Way | Remove
LC | 126205888 | 018/482 | T2 EI CARIBOU #2 018/482 RPR INSW | TABLEMTN | ETL.6280.INSL.NCER | 2023-05-23 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46239926 | T2 EI CARIBOU #2 018/482 RPR INSW | ICW
LC | 126230085 | 022/155 | T2 DI CARIBOU-TABLE MTN 22/155C RPR GYWS | TABLEMTN | ETL.4440.POLE.STPS | 2023-05-25 | 2023-05-17 | 2024-04-17 | On-time | 2024-05-16 | 29 | 2024-05-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061168 | T2 DI CARIBOU-TABLE MTN 22/155C RPR GYWS | ICS
LC | 126236364 | 011/103 | T2 DI SAN LUIS O-CAYUCOS 11/103 RPR ANCW | PISMOBCH | ETL.9090.POLE.WOOD | 2023-05-26 | 2023-05-17 | 2024-04-08 | On-time | 2024-05-16 | 38 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46090152 | T2 DI SAN LUIS O-CAYUCOS 11/103 RPR ANCW | ICW
LC | 126207078 | 000/004A | T2 EI RINCON #1 TAP 00/004A RMV ENCR | LAKEVLLE | ETL.1601.POLE.NWOD | 2023-05-23 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 931 | TLS | INSP | E - Schd Compl Yr 0 | Open | TR2 | Encroachment | Right of Way | Remove
LC | 126236369 | 011/103 | T2 DI SLO-CAYUCOS 11/103 RPR INSW | PISMOBCH | ETL.9090.INSL.CERA | 2023-05-26 | 2023-05-17 | 2024-04-23 | On-time | 2024-05-16 | 23 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46090153 | T2 DI SLO-CAYUCOS 11/103 RPR INSW | ICW
LC | 126207259 | 014/016 | T2 DI EXCHEQUER MARIPOSA 14/016 RPR INSW | FRESNO | ETL.8640.INSL.NCER | 2023-05-23 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46058739 | T2 DI EXCHEQUER MARIPOSA 14/016 RPR INSW | ICW
LC | 126207408 | 080/410 | T2 EI MALIN-ROUND MTN #2 80/410 UNBURY | TABLEMTN | ETL.6020.TOWR | 2023-05-23 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46216007 | T2 EI MALIN-ROUND MTN #2 080/410 UNBURY | ICQ
LC | 126238428 | 015/187B | T2 DI MTN GTE JCT-CSCDE15/187B RPR INSW | TABLEMTN | ETL.7640.INSL.NCER | 2023-05-26 | 2023-05-17 | 2024-02-16 | On-time | 2024-05-16 | 90 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46062703 | T2 DI DLTA-MTN GTE JCT 15/187B RPR INSW | ICW
LC | 126207619 | 056/279 | T2 DI MALIN RND MTN#2 56/279 RPR GYWT | TABLEMTN | ETL.6020.TOWR | 2023-05-23 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46236747 | T2 DI MALIN RND MTN#2 56/279 RPR GYWT | ICQ
LC | 126238492 | 015/187A | T2 DI MTN GTE JCT-CSCDE 15/187A RPR GYWW | TABLEMTN | ETL.7640.POLE.NWOD | 2023-05-26 | 2023-05-17 | 2024-02-16 | On-time | 2024-05-16 | 90 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062701 | T2 DI DLTA-MTN GTE JCT 15/187A RPR GYWW | ICW
LC | 126159663 | :016/083 | T2 EI CHC-SALINAS-SOLE :16/83 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-18 | 2023-05-18 | 2024-02-21 | On-time | 2024-05-17 | 86 | 2024-05-18 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081557 | T2 EI CHC-SALINAS-SOLE :16/83 RPL RPTS | ICB
LC | 126159731 | 000/015 | T2 EI LAURLS-OTTR 0/15 RPL STRW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-18 | 2023-05-18 | 2023-10-05 | On-time | 2024-05-17 | 225 | 2023-11-18 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31651464 | T2 EI LAURLS-OTTR 0/15 RPL STRW | 70Y
LC | 126208469 | A005/114 | T2 EI CSCD-BNTN-DSCHTS A5/114 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-23 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521774 | T2 EI CSCD-BNTN-DSCHTS A5/114 RPL STRW | 70Y
LC | 126208684 | 013/269 | T2 EI CARIBOU-WESTWOOD 13/269 RPR INSW | TABLEMTN | ETL.6300.INSL | 2023-05-23 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46073814 | T2 EI CARIBOU-WESTWOOD 13/269 RPR INSW | ICW
LC | 126160388 | 008/135 | T2 WV TEMPLTN-ATSCDRO 08/135 RPL POLE | PISMOBCH | ETL.9410.POLE.WOOD | 2023-05-18 | 2023-05-18 | 2024-05-17 | On-time | 2024-05-17 | 0 | 2024-05-18 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35523962 | T2 WV TEMPLTN-ATSCDRO 08/135 RPL POLE | 70Y
LC | 126160558 | 004/073 | T2 WV TEMPLTN-ATSCDRO 04/73 RPL POLE | PISMOBCH | ETL.9410.POLE.WOOD | 2023-05-18 | 2023-05-18 | 2024-05-14 | On-time | 2024-05-17 | 3 | 2023-08-18 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35523960 | T2 WV TEMPLTN-ATSCDRO 03/66 RPL POLE | 70Y
LC | 126209402 | 012/142C | T2 EI DRUM-SUMMIT #2 12/142C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-05-23 | 2023-05-23 | 2024-06-17 | Late | 2024-05-22 | -26 | 2023-11-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101306 | T2 EI DRUM-SUMMIT #2 12/142C RPR GYWW | ICW
LC | 126209403 | 012/142A | T2 EI DRUM-SUMMIT #2 12/142A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-05-23 | 2023-05-23 | 2024-06-17 | Late | 2024-05-22 | -26 | 2024-05-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101307 | T2 EI DRUM-SUMMIT #2 12/142A RPR GYWW | ICW
LC | 126161333 | :013/069 | T2 EI CHC-SALINAS-SOLE :13/69 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-18 | 2023-05-18 | 2023-12-18 | On-time | 2024-05-17 | 151 | 2024-05-18 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081559 | T2 EI CHC-SALINAS-SOLE :13/69 RPL RPTS | ICB
LC | 126161465 | 014/001 | T2 EI OAKHURST TAP 014/001 RPR GYWW | FRESNO | ETL.1252.POLE.NWOD | 2023-05-18 | 2023-05-18 | 2023-06-13 | On-time | 2024-05-17 | 339 | 2023-11-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45804958 | T2 EI OAKHURST TAP 014/001 RPR GYWW | ICW
LC | 126162482 | 004/088 | T2 EI CSCD-BNTN-DSCHTS 4/88 COMPLETED | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-18 | 2023-05-18 | 2024-05-13 | On-time | 2024-05-17 | 4 | 2024-05-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062718 | T2 EI CSCD-BNTN-DSCHTS 4/88 RPR STRW | ICW
LC | 126162637 | :013/072 | T2 EI CHC-SALINAS-SOLE :13/72 RPR FOND | MOSSLNDG | ETL.2900.TOWR | 2023-05-18 | 2023-05-18 | 2024-03-08 | On-time | 2024-05-17 | 70 | 2024-05-18 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46073688 | T2 EI CHC-SALINAS-SOLE :13/72 RPR FOND | ICQ
LC | 126210796 | 012/144B | T2 EI DRUM-SUMMIT #2 12/144B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-05-23 | 2023-05-23 | 2024-06-22 | Late | 2024-05-22 | -31 | 2024-05-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101308 | T2 EI DRUM-SUMMIT #2 012/144B RPR GYWW | ICW
LC | 126162660 | :013/072 | T2 EI CHC-SALINAS-SOLE :13/72 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-18 | 2023-05-18 | 2024-03-13 | On-time | 2024-05-17 | 65 | 2024-05-18 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081581 | T2 EI CHC-SALINAS-SOLE :13/72 RPL RPTS | ICB
LC | 126162992 | 013/070 | T2 EI BALCH-SANGER 013/070 UNBURY | FRESNO | ETL.1050.TOWR | 2023-05-18 | 2023-05-18 | 2024-01-08 | On-time | 2024-05-17 | 130 | 2024-05-18 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46070735 | T2 EI BALCH-SANGER 013/070 UNBURY | ICQ
LC | 126163023 | 014/007 | T2 EI OAKHURST TAP 014/007 RPR GYWW | FRESNO | ETL.1252.POLE.NWOD | 2023-05-18 | 2023-05-18 | 2024-03-01 | On-time | 2024-05-17 | 77 | 2024-05-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46058735 | T2 EI OAKHURST TAP 014/007 RPR GYWW | ICW
LC | 126211328 | 017/000 | T2 EI MENDCINO-WILS-FT BG 17/00 RPR HRDW | WILLITS | ETL.7550.POLE.WOOD | 2023-05-23 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46214145 | T2 EI MENDCINO-WILS-FT BG 17/00 RPR HRDW | ICW
LC | 126211393 | 043/007 | T2 EI FT ROSS-GUALALA 43/7 GRND WASH | LAKEVLLE | ETL.6980.INSL.NCER | 2023-05-23 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 622 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Contaminated | Insulator | Ground Wash | 46073733 | T2 EI FT ROSS-GUALALA 43/7 GRND WASH | ICD
LC | 126211475 | 042/011A | T2 DI FORT ROSS GUALALA 42/11A CANCEL | LAKEVLLE | ETL.6980.POLE.NWOD | 2023-05-23 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35517026 | T2 DI FORT ROSS GUALALA 42/11A RPL ANCW | 93E
LC | 126163336 | :014/073 | T2 EI CHC-SALINAS-SOLE :14/73 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-18 | 2023-05-18 | 2024-03-13 | On-time | 2024-05-17 | 65 | 2024-05-18 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081583 | T2 EI CHC-SALINAS-SOLE :14/73 RPL RPTS | ICB
LC | 126163987 | 013/069 | T2 EI BALCH-SANGER 013/069 MASTIC | FRESNO | ETL.1050.TOWR | 2023-05-18 | 2023-05-18 | 2024-01-08 | On-time | 2024-05-17 | 130 | 2024-05-18 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46070734 | T2 EI BALCH-SANGER 013/069 MASTIC | ICQ
LC | 126164186 | 037/244A | T2 EI TRINITY-CTTNWD 037/244C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-18 | 2023-05-18 | 2023-07-03 | On-time | 2024-05-17 | 319 | 2023-08-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805401 | T2 EI TRINITY-CTTNWD 037/244C RPR GYWW | ICW
LC | 126211801 | 012/147A | T2 EI DRUM-SUMMIT #2 12/147A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-05-23 | 2023-05-23 | 2024-06-22 | Late | 2024-05-22 | -31 | 2024-05-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101309 | T2 EI DRUM-SUMMIT #2 012/147A RPR GYWW | ICW
LC | 126211812 | 012/147B | T2 EI DRUM-SUMMIT #2 12/147B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-05-23 | 2023-05-23 | 2024-06-22 | Late | 2024-05-22 | -31 | 2024-05-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101310 | T2 EI DRUM-SUMMIT #2 12/147B RPR GYWW | ICW
LC | 126164504 | :013/068 | T2 EI CHC-SALINAS-SOLE :13/68 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-18 | 2023-05-18 | 2024-02-20 | On-time | 2024-05-17 | 87 | 2024-05-18 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081585 | T2 EI CHC-SALINAS-SOLE :13/68 RPL RPTS | ICB
LC | 126164520 | :013/068 | T2 EI CHC-SALINAS-SOLE :13/68 COTTER | MOSSLNDG | ETL.2910.INSL.CERA | 2023-05-18 | 2023-05-18 | 2024-02-20 | On-time | 2024-05-17 | 87 | 2024-05-18 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46073689 | T2 EI CHC-SALINAS-SOLE :13/68 COTTER | ICS
LC | 126212443 | 006/008 | T2 EI LAYTONVILLE-COVELO 6/8 RPR GYWW | WILLITS | ETL.7390.POLE.NWOD | 2023-05-23 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46219449 | T2 EI LAYTONVILLE-COVELO 6/8 RPR GYWW | ICW
LC | 126164751 | 037/244B | T2 EI TRINITY-CTTNWD 037/244B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-18 | 2023-05-18 | 2023-07-03 | On-time | 2024-05-17 | 319 | 2023-08-18 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805400 | T2 EI TRINITY-CTTNWD 037/244B RPR GYWW | ICW
LC | 126165212 | 037/244C | T2 EI TRINITY-CTTNWD 037/244A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-18 | 2023-05-18 | 2023-07-03 | On-time | 2024-05-17 | 319 | 2023-08-18 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45805379 | T2 EI TRINITY-CTTNWD 037/244A RPR GYWW | ICS
LC | 126165259 | :012/067 | T2 EI CHC-SALINAS-SOLE :12/67 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-18 | 2023-05-18 | 2024-02-20 | On-time | 2024-05-17 | 87 | 2024-05-18 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081588 | T2 EI CHC-SALINAS-SOLE :12/67 RPL RPTS | ICB
LC | 126165538 | 038/224 | T2 WV INDN FLA-YSMT 38/224 RPR GYWT | FRESNO | ETL.1112.POLE.NWOD | 2023-05-18 | 2023-05-18 | 2023-12-11 | On-time | 2024-05-17 | 158 | 2024-05-18 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46070848 | T2 WV INDN FLA-YSMT 38/224 RPR GYWT | ICQ
LC | 126165747 | :012/065 | T2 EI CHC-SALINAS-SOLE :12/65 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-18 | 2023-05-18 | 2024-02-20 | On-time | 2024-05-17 | 87 | 2024-05-18 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081590 | T2 EI CHC-SALINAS-SOLE :12/65 RPL RPTS | ICB
LC | 126166532 | 021/437 | T2 WV COLGATE-PALERMO 21/437 INST DMPW | SACTO | ETL.6500.INSL.NCER | 2023-05-18 | 2023-05-18 | 2024-04-27 | On-time | 2024-05-17 | 20 | 2024-05-18 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46062878 | T2 WV COLGATE-PALERMO 21/437 INST DMPW | ICW
LC | 126166572 | :012/064 | T2 EI CHC-SALINAS-SOLE :12/64 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-18 | 2023-05-18 | 2024-02-16 | On-time | 2024-05-17 | 91 | 2024-05-18 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081592 | T2 EI CHC-SALINAS-SOLE :12/64 RPL RPTS | ICB
LC | 126166574 | :012/064 | T2 EI CHC-SALINAS-SOLE :12/64 RPR INSS | MOSSLNDG | ETL.2900.INSL.CERA | 2023-05-18 | 2023-05-18 | 2024-02-16 | On-time | 2024-05-17 | 91 | 2024-05-18 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46073690 | T2 EI CHC-SALINAS-SOLE :12/64 RPR INSS | ICS
LC | 126212817 | 001/035 | T2 DI CARIBOU-WESTWOOD 1/35L RPL STRW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-23 | 2023-05-16 |  | Late | 2024-05-15 |  | 2023-11-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519108 | T2 DI CARIBOU-WESTWOOD 1/35L RPLC STRW | 70Y
LC | 126212840 | 001/035 | T2 DI CARIBOU-WESTWOOD 1/35R RPL STRW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-23 | 2023-05-16 |  | Late | 2024-05-15 |  | 2023-11-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519108 | T2 DI CARIBOU-WESTWOOD 1/35L RPLC STRW | 70Y
LC | 126212842 | 001/035 | T2 DI CARIBOU-WESTWOOD 1/35C RPL STRW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-23 | 2023-05-16 |  | Late | 2024-05-15 |  | 2023-11-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519108 | T2 DI CARIBOU-WESTWOOD 1/35L RPLC STRW | 70Y
LC | 126167076 | :012/063 | T2 EI CHC-SALINAS-SOLE :12/63 RPL RPTS | MOSSLNDG | ETL.2900.TOWR | 2023-05-18 | 2023-05-18 | 2024-02-16 | On-time | 2024-05-17 | 91 | 2024-05-18 | 593 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46081594 | T2 EI CHC-SALINAS-SOLE :12/63 RPL RPTS | ICB
LC | 126167278 | 037/008 | T2 EI TRNTY-MPL CRK 037/008 CANCEL | EUREKA | ETL.8170.POLE.WOOD | 2023-05-18 | 2023-05-18 | 2023-06-14 | On-time | 2024-05-17 | 338 | 2023-08-18 | 625 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Land/Enviro Issue | Other | Access Issue
LC | 126213004 | 009/184 | T2 DI CRBU-WSTWD-09/184 RPL HRDD | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-23 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46062657 | T2 DI CRBU-WSTWD-09/184 RPL HRDD | ICW
LC | 126167995 | 012/065A | T2 EI BALCH-SANGER 012/065A RPR GYWT | FRESNO | ETL.1050.POLE.NWOD | 2023-05-18 | 2023-05-18 | 2024-01-08 | On-time | 2024-05-17 | 130 | 2024-05-18 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46070722 | T2 EI BALCH-SANGER 012/065A RPR GYWT | ICQ
LC | 126168075 | 012/065C | T2 EI BALCH-SANGER 012/065C RPR GYWT | FRESNO | ETL.1050.POLE.NWOD | 2023-05-18 | 2023-05-18 | 2024-01-08 | On-time | 2024-05-17 | 130 | 2024-05-18 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46070733 | T2 EI BALCH-SANGER 012/065C RPR GYWT | ICQ
LC | 126213090 | ;001/014 | T2 DI CARIBOU #2 ;01/14R RPR GYWW | TABLEMTN | ETL.6280.POLE.STPS | 2023-05-23 | 2023-05-16 |  | Late | 2024-05-15 |  | 2023-08-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062594 | T2 DI CARIBOU #2 ;01/14R RPR GYWW | ICW
LC | 126168180 | 011/261 | T2 EI SALINAS-LAURELES 11/261 RMV VEG | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-05-18 | 2023-05-18 | 2024-04-11 | On-time | 2024-05-17 | 36 | 2024-05-18 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126229769 | 002/023 | T2 DI CTTNWD #2 02/23 COTTER | TABLEMTN | ETL.6630.INSL.CERA | 2023-05-25 | 2023-05-18 | 2023-07-31 | On-time | 2024-05-17 | 291 | 2023-08-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45805403 | T2 DI CTTNWD #2 02/23 COTTER | ICS
LC | 126230235 | 030/005 | T2 DI FORT ROSS-GUALALA 30/05 CANCEL | WILLITS | ETL.6980.POLE.WOOD | 2023-05-25 | 2023-05-18 | 2024-04-16 | On-time | 2024-05-17 | 31 | 2024-05-18 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126230291 | 007/040 | T2 DI MRR BY-SN LS OBSP #1 7/40 HANGER | PISMOBCH | ETL.2810.INSL.NCER | 2023-05-25 | 2023-05-18 | 2024-03-24 | On-time | 2024-05-17 | 54 | 2024-05-18 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hanger Plate - Tower | Replace | 46070857 | T2 DI MRR BY-SN LS OBSP #1 7/40 HANGER | ICQ
LC | 126230390 | 007/040 | T2 DI MRR BY-SN LS OBSP #2 7/40 HANGER | PISMOBCH | ETL.2820.INSL | 2023-05-25 | 2023-05-18 | 2024-04-30 | On-time | 2024-05-17 | 17 | 2024-05-18 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hanger Plate - Tower | Replace | 46070858 | T2 DI MRR BY-SN LS OBSP #1 7/40 HANGER | ICQ
LC | 126233016 | 007/005 | T2 DI MENDOCINO-HARTLEY 007/005 RPR POLE | WILLITS | ETL.7510.POLE.WOOD | 2023-05-26 | 2023-05-18 | 2024-01-26 | On-time | 2024-05-17 | 112 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46089488 | T2 DI MENDOCINO-HARTLEY 007/005 RPR POLE | ICW
LC | 126214395 | 010/017 | T2 DI TRINITY-MAPLE CREEK 10/017 RMV VEG | TABLEMTN | ETL.8170.POLE.WDPS | 2023-05-24 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126214660 | 011/127 | T2 EI DRUM-SUMMIT #1 11/127R RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2023-05-24 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526569 | T0 EI DRUM-SUMMIT #1 013/150 RPL STRW | 70Y
LC | 126214823 | 036/291 | T2 DI BRDGVIL CTTNWD 36/291R RPL HRDD | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-24 | 2023-05-15 | 2024-06-03 | Late | 2024-05-14 | -20 | 2024-05-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 46062592 | T2 DI BRDGVIL CTTNWD 36/291R RPL HRDD | ICW
LC | 126214827 | 036/291 | T2 DI BRDGVIL CTTNWD 36/291L RPL ANCW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-24 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35501422 | T2 DI BRDGVIL CTTNWD 36/291L RPL ANCW | 93E
LC | 126215632 | ;002/006 | T2 DI CARIBOU #2 ;2/6 RPL INSW | TABLEMTN | ETL.6280.INSL.CERA | 2023-05-24 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35515862 | T2 DI CARIBOU #2 ;2/6 RPL INSW | 93I
LC | 126216098 | 018/185 | T2 EI WOODLEAF-PALERMO 18/185 RPL STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-05-24 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525949 | T2 EI WOODLEAF-PALERMO 18/185 RPL STRW | 70Y
LC | 126238111 | 000/003 | T2 DI CARIBOU #2 00/03 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-26 | 2023-05-18 | 2024-05-08 | On-time | 2024-05-17 | 9 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062713 | T2 DI CARIBOU #2 00/03 RPR GYWW | ICW
LC | 126238604 | 042/339A | T2 DI BRDGVL-CTTNWD 42/339A RPR GYWS | TABLEMTN | ETL.1110.POLE.NWOD | 2023-05-26 | 2023-05-18 | 2024-04-23 | On-time | 2024-05-17 | 24 | 2024-05-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061184 | T2 DI BRDGVL-CTTNWD 42/339A RPR GYWS | ICS
LC | 126216657 | 008/149 | T2 DI CRBU-WSTWD 8/149 COTTER | TABLEMTN | ETL.6300.INSL | 2023-05-24 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46236159 | T2 DI CRBU-WSTWD 8/149 RPR INSW | ICW
LC | 126216797 | 009/187 | T2 DI CARIBOU-WSTWD 09/187 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-24 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519117 | T2 DI CARIBOU-WSTWD 09/187 RPL POLE | 70Y
LC | 126238735 | 042/339B | T2 DI BRDGVL-CTNWD-42/339B RPR INSW | TABLEMTN | ETL.1110.INSL.CERA | 2023-05-26 | 2023-05-18 | 2023-10-30 | On-time | 2024-05-17 | 200 | 2023-11-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45810541 | T2 DI BRDGVL-CTNWD-42/339B RPR INSW | ICW
LC | 126217158 | 049/243 | T2 DI MALN RND-MT #2 49/243 RPL ANCT | TABLEMTN | ETL.6020.TOWR | 2023-05-24 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 93Z | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Tower | Replace | 31685780 | T2 DI MALN RND-MT #2 49/243 RPL ANCHOR | 93Z
LC | 126238736 | 042/339B | T2 DI BRIDGVIL-COTONWOD-42/339B RPR GYWS | TABLEMTN | ETL.1110.POLE.NWOD | 2023-05-26 | 2023-05-18 | 2024-04-23 | On-time | 2024-05-17 | 24 | 2024-05-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061185 | T2 DI BRIDGVIL-COTONWOD-42/339B RPR GYWS | ICS
LC | 126218457 | 006/058 | T2 EI WOODLEAF-PALERMO 6/058 RPR GYWW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-05-24 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076621 | T2 EI WOODLEAF-PALERMO 6/058 RPR GYWW | ICW
LC | 126238839 | 038/008 | T2 DI FORT ROSS-GUALALA 38/08 RPR GYWW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-26 | 2023-05-18 | 2024-03-26 | On-time | 2024-05-17 | 52 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073726 | T2 DI FORT ROSS-GUALALA 38/08 RPR GYWW | ICW
LC | 126238897 | 039/312 | T2 DI BRIDGEVIL-COTONWD 39/312L RPR OPGW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-26 | 2023-05-18 | 2023-10-30 | On-time | 2024-05-17 | 200 | 2023-08-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45810533 | T2 DI BRIDGEVIL-COTONWD 39/312L RPR OPGW | ICW
LC | 126219613 | 012/246 | T2 EI HAT CREEK #1-WSTWD 12/246 RPL HRDW | TABLEMTN | ETL.7030.POLE.NWOD | 2023-05-24 | 2023-05-24 | 2024-06-12 | Late | 2024-05-23 | -20 | 2024-05-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46076200 | T2 EI HAT CREEK #1-WSTWD 12/246 RPL HDWW | ICW
LC | 126219614 | 012/243 | T2 EI HAT CREEK #1-WSTWD 12/243 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-24 | 2023-05-24 | 2024-06-13 | Late | 2024-05-23 | -21 | 2024-05-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514861 | T2 EI HAT CREK #1-WESTWD 12/231 RPL STRW | 70Y
LC | 126219616 | 013/250 | T2 EI HAT CREEK #1-WSTWD 13/250 GO95 | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-24 | 2023-05-24 | 2024-06-12 | Late | 2024-05-23 | -20 | 2024-05-24 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35529296 | T2 EI HAT CREEK #1-WSTWD 13/250 GO95 | 93G
LC | 126219618 | 012/246 | T2 EI HAT CREEK #1-WSTWD 12/246 RPR INSW | TABLEMTN | ETL.7030.INSL.NCER | 2023-05-24 | 2023-05-24 | 2024-06-12 | Late | 2024-05-23 | -20 | 2024-05-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46076201 | T2 EI HAT CREEK #1-WSTWD 12/246 RPR INSW | ICW
LC | 126239705 | 036/006 | T2 DI FT ROSS-GUALA 36/6L CANCEL | LAKEVLLE | ETL.6980.POLE.WDPS | 2023-05-27 | 2023-05-18 | 2024-04-30 | On-time | 2024-05-17 | 17 | 2024-05-18 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126240063 | 009/000 | T2 DI MENDO-HARTLEY 009/000 RPR GYWW | WILLITS | ETL.7510.POLE.WOOD | 2023-05-27 | 2023-05-18 | 2024-02-15 | On-time | 2024-05-17 | 92 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46089489 | T2 DI MENDO-HARTLEY 009/000 RPR GYWW | ICW
LC | 126253054 | 076/386 | T2 DI MALN-ROUND MTN #2 76/386 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-05-31 | 2023-05-18 | 2024-01-22 | On-time | 2024-05-17 | 116 | 2024-05-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 46060975 | T2 DI MALN-ROUND MTN #2 76/386 RPL OPGW | ICS
LC | 126174055 | 012/065B | T2 EI BALCH-SANGER 012/065B RPR GYWT | FRESNO | ETL.1050.POLE.NWOD | 2023-05-19 | 2023-05-19 | 2024-01-08 | On-time | 2024-05-18 | 131 | 2024-05-19 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46070732 | T2 EI BALCH-SANGER 012/065B RPR GYWT | ICQ
LC | 126176242 | 023/192 | T2 EI PIT #1-COTTONWOOD 23/192 COMPLETED | TABLEMTN | ETL.5390.TOWR | 2023-05-19 | 2023-05-19 | 2024-01-30 | On-time | 2024-05-18 | 109 | 2024-05-19 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46072185 | T2 EI PIT #1-COTTONWOOD 23/192 UNBURY | ICQ
LC | 126176243 | 023/192 | T2 EI PIT #1-COTTONWOOD 23/192 COMPLETED | TABLEMTN | ETL.5390.TOWR | 2023-05-19 | 2023-05-19 | 2024-01-30 | On-time | 2024-05-18 | 109 | 2024-05-19 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061190 | T2 EI PIT #1-COTTONWOOD 23/192 RPR GYWS | ICS
LC | 126179067 | 006/043 | T2 EI BUTTE VALLEY-CARIBOU 6/43 RPR GYWT | TABLEMTN | ETL.1180.TOWR | 2023-05-19 | 2023-05-19 | 2024-04-14 | On-time | 2024-05-18 | 34 | 2023-08-19 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46228915 | T2 EI BUTTE VALLEY-CARIBOU 6/43 RPR GYWT | ICQ
LC | 126220988 | 018/012 | T2 EI TRINITY-MAPLE CREEK 18/12 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-24 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35502983 | T2 EI TRINITY-MAPLE CREEK 18/12 RPL POLE | 70Y
LC | 126220997 | 042/337C | T2 DI BRDGVLL-CTTNWD 42/337C RPR GYWW | TABLEMTN | ETL.1110.POLE.NWOD | 2023-05-24 | 2023-05-17 | 2024-06-04 | Late | 2024-05-16 | -19 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062712 | T2 DI BRDGVLL-CTTNWD 42/337C RPR GYWW | ICW
LC | 126220999 | 018/015 | T2 EI TRINITY-MAPLE CREK 18/15R RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-24 | 2023-05-24 |  | Late | 2024-05-23 |  | 2023-11-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46229541 | T2 EI TRINITY-MAPLE CREK 18/15R RPR GYWW | ICW
LC | 126221020 | 019/003 | T2 EI TRINITY-MAPLE CREEK 19/3 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-24 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35502987 | T2 EI TRINITY-MAPLE CREEK 19/3 RPL POLE | 70Y
LC | 126221021 | 018/014 | T2 EI TRINITY-MAPLE CREEK 18/14 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-24 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35502984 | T2 EI TRINITY-MAPLE CREEK 18/14 RPL POLE | 70Y
LC | 126187619 | 016/134 | T2 EI PIT #1-COTTONWOOD 016/134 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-19 | 2023-05-19 | 2024-01-25 | On-time | 2024-05-18 | 114 | 2024-05-19 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46072183 | T2 EI PIT #1-COTTONWOOD 016/134 UNBURY | ICQ
LC | 126221096 | 020/537 | T2 DI CARIBOU #2 20/537 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-24 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062704 | T2 DI CARIBOU #2 20/537 RPR GYWW | ICW
LC | 126187641 | :010/054 | T2 EI CZY HRS CYN-SLS-SLD :10/54 COTTER | MOSSLNDG | ETL.2900.INSL.CERA | 2023-05-19 | 2023-05-19 | 2024-03-01 | On-time | 2024-05-18 | 78 | 2024-05-19 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46079106 | T2 EI CZY HRS CYN-SLS-SLD :10/54 COTTER | ICS
LC | 126188647 | 017/135 | T2 EI PIT #1-COTTONWOOD 017/135 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-19 | 2023-05-19 | 2024-01-25 | On-time | 2024-05-18 | 114 | 2024-05-19 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46072184 | T2 EI PIT #1-COTTONWOOD 017/135 UNBURY | ICQ
LC | 126221268 | :002/005 | T2 DI CARIBOU # :2/5 RPR STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-24 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062670 | T2 DI CARIBOU # :2/5 RPR POLE | ICW
LC | 126221271 | 041/326 | T2 DI BRDGVLL-CTTNWD 41/326 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-05-24 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46061169 | T2 DI BRDGVLL-CTTNWD 41/326 RPR SHLW | ICS
LC | 126221273 | 041/326 | T2 DI BRDGVLL-CTTNWD 41/326 RPL INSS | TABLEMTN | ETL.1110.INSL.CERA | 2023-05-24 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509192 | T2 DI BRIDGEVILLE-CTTNWD RPL INSS 9 TWRS | 93K
LC | 126189208 | 022/001 | T2 WV BRDGVLE-GRBERVLE 22/1 INST DMPW | EUREKA | ETL.6220.INSL.NCER | 2023-05-19 | 2023-05-19 | 2024-01-24 | On-time | 2024-05-18 | 115 | 2024-05-19 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46087897 | T2 WV BRDGVLE-GRBERVLE 22/1 INST DMPW | ICW
LC | 126221438 | 042/338B | T2 DI BRDGVLL-CTTNWD 42/338B RPL INSS | TABLEMTN | ETL.1110.INSL.CERA | 2023-05-24 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509192 | T2 DI BRIDGEVILLE-CTTNWD RPL INSS 9 TWRS | 93K
LC | 126189629 | A012/061 | T2 EI SILVERADO-FULTON JCT A12/61 RPL PL | LAKEVLLE | ETL.1610.POLE.WOOD | 2023-05-19 | 2023-05-19 | 2024-04-10 | On-time | 2024-05-18 | 38 | 2024-05-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527643 | T2 EI SILVERADO-FULTON JCT A12/61 RPL PL | 70Y
LC | 126221505 | 042/334 | T2 DI BRDGVLL-CTTNWD 42/334 RPR OPGW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-24 | 2023-05-17 | 2024-05-31 | Late | 2024-05-16 | -15 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Wood | Repair | 46062707 | T2 DI BRDGVLL-CTTNWD 42/334 RPR OPGW | ICW
LC | 126221538 | 042/335 | T2 DI BRDGVLL-CTTNWD 42/335 COMPLETE | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-24 | 2023-05-17 | 2024-05-31 | Late | 2024-05-16 | -15 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Wood | Repair | 46062708 | T2 DI BRDGVLL-CTTNWD 42/335 RPR OPGW | ICW
LC | 126221564 | 042/335 | T2 DI BRDGVLL-CTTNWD 42/335R RPL POLE | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-24 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35562831 | T2 DI BRDGVLL-CTTNWD 42/335R RPL POLE | 70Y
LC | 126190383 | 035/256 | T2 EI MID FORK-GOLD HILL 35/256 COTR KEY | SACTO | ETL.5140.INSL | 2023-05-19 | 2023-05-19 | 2024-02-14 | On-time | 2024-05-18 | 94 | 2024-05-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46062866 | T2 EI MID FORK-GOLD HILL 35/256 COTR KEY | ICW
LC | 126190596 | 013/107 | T2 TIGR CRK-VLY SPRNGS 13/107 INST DMPW | VICTOR | ETL.5790.INSL.CERA | 2023-05-19 | 2023-05-19 | 2024-01-26 | On-time | 2024-05-18 | 113 | 2024-05-19 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 46079107 | T2 TIGR CRK-VLY SPRNGS 13/107 INST DMPW | ICS
LC | 126221604 | 041/330 | T2 DI BRDGVLL-CTTNWD 41/330 RPR OPGW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-24 | 2023-05-17 | 2024-05-31 | Late | 2024-05-16 | -15 | 2024-05-17 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46061170 | T2 DI BRDGVLL-CTTNWD 41/330 RPR OPGW | ICS
LC | 126232140 | 018/206 | T2 DI ELK CREEK TAP 18/206 RPR GYWW | TABLEMTN | ETL.6921.POLE.NWOD | 2023-05-26 | 2023-05-19 | 2023-11-07 | On-time | 2024-05-18 | 193 | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45999230 | T2 DI ELK CREEK TAP 18/206 RPR GYWW | ICW
LC | 126237160 | 001/036 | T2 DI DELTA-MTN GTE JCT 1/36 RPL HRDW | TABLEMTN | ETL.6750.POLE.WOOD | 2023-05-26 | 2023-05-19 | 2023-10-12 | On-time | 2024-05-18 | 219 | 2023-08-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45805404 | T2 DI DELTA-MTN GTE JCT 1/36 RPL HRDW | ICW
LC | 126221644 | 004/028 | T2 DI BUTTE VLLY-CARIBOU 4/28 RPL INSS | TABLEMTN | ETL.1180.INSL.CERA | 2023-05-24 | 2023-05-16 | 2024-06-05 | Late | 2024-05-15 | -21 | 2024-05-16 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35511333 | T2 DI BTTE VLY-CARIBOU RPL INSS 2 TWRS | 93K
LC | 126221662 | 040/320 | T2 DI BRDGVLL-GRBRVLL 40/320 RPL HRDD | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-24 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46062705 | T2 DI BRDGVLL-GRBRVLL 40/320 RPL HRDD | ICW
LC | 126238130 | 000/011 | T2 DI MOUNTAIN GATE TAP 00/11 RPL STRW | TABLEMTN | ETL.7641.POLE.WOOD | 2023-05-26 | 2023-05-19 | 2024-02-19 | On-time | 2024-05-18 | 89 | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485422 | T2 DI MOUNTAIN GATE TAP 00/11 RPL STRW | 70Y
LC | 126221724 | 011/216 | T2 DI CARIBOU-WESTWOOD 11/216 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-24 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519118 | T2 DI CARIBOU-WESTWOOD 11/216 RPL STRW | 70Y
LC | 126221735 | 042/338C | T2 DI BRDGVLL-CTTNWD 42/338C RPR OPGW | TABLEMTN | ETL.1110.POLE.NWOD | 2023-05-24 | 2023-05-17 | 2024-06-07 | Late | 2024-05-16 | -22 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Wood | Repair | 46256223 | T2 DI BRDGVLL-CTTNWD 42/338C RPR OPGW | ICW
LC | 126221738 | 042/338C | T2 DI BRDGVLL-CTTNWD 042/338C RPL INSS | TABLEMTN | ETL.1110.INSL.CERA | 2023-05-24 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509192 | T2 DI BRIDGEVILLE-CTTNWD RPL INSS 9 TWRS | 93K
LC | 126238670 | 002/026 | T2 DI MTN QUARRIES TAP 002/026 RPR GYWW | SACTO | ETL.6991.POLE.NWOD | 2023-05-26 | 2023-05-19 | 2024-01-16 | On-time | 2024-05-18 | 123 | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062778 | T2 DI MTN QUARRIES TAP 002/026 RPR GYWW | ICW
LC | 126221774 | 000/013 | T2 DI FRUITLAND TP 0/13 RPR JUMW | EUREKA | ETL.6221.INSL.CERA | 2023-05-24 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46203461 | T2 DI FRUITLAND TP 0/13 RPR JUMW | ICW
LC | 126240597 | 19 | T2 DI KESWICK-TRINITY 011/151 COTTER | TABLEMTN | ETL.7270.SWIT | 2023-05-27 | 2023-05-19 | 2023-06-27 | On-time | 2024-05-18 | 326 | 2023-08-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45810499 | T2 DI KESWICK-TRINITY 011/151 COTTER | ICW
LC | 126240869 | 012/002 | T2 DI TRNTY MPL CRK 12/02 RPR JUMW | EUREKA | ETL.8170.INSL.CERA | 2023-05-27 | 2023-05-19 | 2024-01-23 | On-time | 2024-05-18 | 116 | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46070776 | T2 DI TRNTY MPL CRK 12/02 RPR JUMW | ICW
LC | 126221826 | 042/338A | T2 DI BRDGVLL-CTTNWD 042/338A RPL INSS | TABLEMTN | ETL.1110.INSL.CERA | 2023-05-24 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509192 | T2 DI BRIDGEVILLE-CTTNWD RPL INSS 9 TWRS | 93K
LC | 126221892 | 011/219 | T2 DI CARIBOU-WESTWD 11/219 RPR JUMW | TABLEMTN | ETL.6300.INSL | 2023-05-24 | 2023-05-16 |  | Late | 2024-05-15 |  | 2023-08-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46073813 | T2 DI CARIBOU-WESTWD 11/219 RPR JUMW | ICW
LC | 126222591 | ;001/012 | T2 DI CARIBOU #2 ;001/012 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-05-25 | 2023-05-16 |  | Late | 2024-05-15 |  | 2023-08-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062593 | T2 DI CARIBOU #2 ;001/012 RPR GYWW | ICW
LC | 126240937 | 012/002 | T2 DI TRNTY MPL CRK 12/02 RPR INSW | EUREKA | ETL.8170.INSL.CERA | 2023-05-27 | 2023-05-19 | 2024-01-23 | On-time | 2024-05-18 | 116 | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46070777 | T2 DI TRNTY MPL CRK 12/02 RPR INSW | ICW
LC | 126222629 | 008/160 | T2 DI CARIBOU-WESTWD 8/160 RPL INSW | TABLEMTN | ETL.6300.INSL | 2023-05-25 | 2023-05-17 |  | Late | 2024-05-16 |  | 2023-08-17 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35543569 | T2 DI CARIBOU-WESTWOOD 8/160 RPL INSW | 93I
LC | 126222806 | 007/005 | T2 EI MNDCNO-WLLTS-FRT BRGG 7/5 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2023-05-25 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521521 | T2 EI MNDCNO-WLLTS-FRT BRGG 7/5 RPL POLE | 70Y
LC | 126243599 | 015/290 | T2 DI HAT CREEK#1 WESTWD 15/290 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-19 | 2024-05-02 | On-time | 2024-05-18 | 16 | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512700 | T2 DI HAT CREEK#1 WESTWD 15/290 RPL POLE | 70Y
LC | 126247351 | 019/207 | T2 DI ELK CREEK TAP 19/207 RMV STEP | TABLEMTN | ETL.6921.POLE.NWOD | 2023-05-30 | 2023-05-19 | 2023-12-12 | On-time | 2024-05-18 | 158 | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45999231 | T2 DI ELK CREEK TAP 19/207 RMV STEP | ICW
LC | 126192427 | 066/481 | T2 EI BRIDGEVILE-CTTNWD 66/481R RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-05-20 | 2023-05-20 | 2024-04-03 | On-time | 2024-05-19 | 46 | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171674 | T2 EI BRIDGEVILE-CTTNWD 66/481L COTTER | ICW
LC | 126223344 | 011/228 | T2 DI CARIBOU-WSTWD 11/228 RPR GYWW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-25 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805375 | T2 DI CARIBOU-WSTWD 11/228 RPR GYWW | ICW
LC | 126223368 | A007/146 | T2 EI CASCDE-BNTN-DSCHTS A7/146 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-25 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521774 | T2 EI CSCD-BNTN-DSCHTS A5/114 RPL STRW | 70Y
LC | 126223452 | 011/228 | T2 DI CARIBOU-WSTWD 11/228 RPR ANCW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-25 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46062659 | T2 DI CARIBOU-WSTWD 11/228 RPR ANCW | ICW
LC | 126192506 | 066/481 | T2 EI BRIDGEVILE-CTTNWD 66/481C RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-05-20 | 2023-05-20 | 2024-04-03 | On-time | 2024-05-19 | 46 | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171674 | T2 EI BRIDGEVILE-CTTNWD 66/481L COTTER | ICW
LC | 126223690 | 015/299 | T2 EI HAT CRK #1-WSTWD 15/299 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-25 | 2023-05-25 | 2024-06-11 | Late | 2024-05-24 | -18 | 2024-05-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514862 | T2 EI HAT CRK #1-WSTWD 14/271 RPL STRW | 70Y
LC | 126224083 | A007/148 | T2 EI CASCDE-BNTN-DSCHTS A7/148 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-25 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521776 | T2 EI CASCDE-BNTN-DSCHTS A7/148 RPL POLE | 70Y
LC | 126224316 | 015/298 | T2 EI HAT CREK #1-WESTWD 15/298 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-25 | 2023-05-25 | 2024-06-11 | Late | 2024-05-24 | -18 | 2024-05-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514862 | T2 EI HAT CRK #1-WSTWD 14/271 RPL STRW | 70Y
LC | 126224326 | 014/271 | T2 EI HAT CRK #1-WSTWD 14/271 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-25 | 2023-05-25 | 2024-06-14 | Late | 2024-05-24 | -21 | 2024-05-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514862 | T2 EI HAT CRK #1-WSTWD 14/271 RPL STRW | 70Y
LC | 126224610 | ;022/005 | T2 EI KNCTI MDDLTWN ;22/5 COMPLETE | WILLITS | ETL.6380.POLE.WOOD | 2023-05-25 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35522936 | T2 EI KONOCTI MIDDLETOWN ;22/5 RPL STRW | 70Y
LC | 126192524 | 001/005 | T2 EI TRINITY-MAPLE CREEK 1/5 RPR STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-20 | 2023-05-20 | 2024-02-23 | On-time | 2024-05-19 | 86 | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46070778 | T2 EI TRINITY-MAPLE CREEK 1/5 RPR STRW | ICW
LC | 126192663 | 066/481 | T2 EI BRIDGEVILE-CTTNWD 66/481L RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-05-20 | 2023-05-20 | 2024-04-03 | On-time | 2024-05-19 | 46 | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171674 | T2 EI BRIDGEVILE-CTTNWD 66/481L COTTER | ICW
LC | 126192843 | 044/290C | T2 EI TRINTY-COTTNWD 44/290C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-20 | 2023-05-20 | 2023-07-28 | On-time | 2024-05-19 | 296 | 2023-11-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805448 | T2 EI TRINTY-COTTNWD 44/290C RPR GYWW | ICW
LC | 126192999 | 019/158 | T2 EI PIT #1-COTTONWOOD 019/158 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-20 | 2023-05-20 | 2024-01-25 | On-time | 2024-05-19 | 115 | 2024-05-20 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46072186 | T2 EI PIT #1-COTTONWOOD 019/158 UNBURY | ICQ
LC | 126193102 | 044/290B | T2 EI TRINTY-COTTNWD 44/290B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-20 | 2023-05-20 | 2023-07-28 | On-time | 2024-05-19 | 296 | 2023-11-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805447 | T2 EI TRINTY-COTTNWD 44/290B RPR GYWW | ICW
LC | 126226410 | 012/242 | T2 DI CARIBOU-WSTWD 12/242 RPL ANCW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-25 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46062660 | T2 DI CARIBOU-WSTWD 12/242 RPL ANCW | ICW
LC | 126226415 | ;009/000 | T2 DI CARIBOU PLUMAS JT 09/000 RPR CRSW | TABLEMTN | ETL.6290.POLE.WOOD | 2023-05-25 | 2023-05-16 | 2024-05-20 | Late | 2024-05-15 | -5 | 2024-05-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46062597 | T2 DI CARIBOU PLUMAS JT 09/000 RPR CRSW | ICW
LC | 126193307 | 044/290A | T2 EI TRINTY-COTTNWD 44/290A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-05-20 | 2023-05-20 | 2023-07-28 | On-time | 2024-05-19 | 296 | 2023-11-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805446 | T2 EI TRINTY-COTTNWD 44/290A RPR GYWW | ICW
LC | 126228756 | 039/169 | T2 EI FULTON-LAKEVILLE+ 39/169 COTTER | LAKEVLLE | ETL.4950.INSL.CERA | 2023-05-25 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46079108 | T2 EI FULTON-LAKEVILLE+ 039/169 COTTER | ICS
LC | 126193489 | 012/003 | T2 EI MNDCN-WLLTS-FRT BRGG 12/3 RPR POLE | WILLITS | ETL.7550.POLE.WOOD | 2023-05-20 | 2023-05-20 | 2023-06-15 | On-time | 2024-05-19 | 339 | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45848803 | T2 EI MNDCN-WLLTS-FRT BRGG 12/3 RPR POLE | ICW
LC | 126193764 | T001/010 | T2 EI TULUCAY-NAPA #1 T001/010 RPR ANCW | LAKEVLLE | ETL.8180.POLE.WOOD | 2023-05-20 | 2023-05-20 | 2024-01-18 | On-time | 2024-05-19 | 122 | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46096605 | T2 EI TULUCAY-NAPA #1 T001/010 RPR ANCW | ICW
LC | 126229261 | 026/005 | T2 EI TRINITY-MAPLE CREEK 26/05 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-25 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504063 | T2 EI TRINITY-MAPLE CREEK 26/05 RPL STRW | 70Y
LC | 126193931 | 036/154 | T2 COBRN-LS AGLAS SW STA 36/154 RPL INSS | MOSSLNDG | ETL.4460.INSL | 2023-05-20 | 2023-05-20 | 2023-05-26 | On-time | 2024-05-19 | 359 | 2024-05-20 | 532 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31646491 | T2 COBRN-LS AGLAS SW STA 36/154 RPL INSS | 93K
LC | 126194671 | 019/160 | T2 EI PIT #1-COTTONWOOD 019/160 UNBUR;Y | TABLEMTN | ETL.5390.TOWR | 2023-05-20 | 2023-05-20 | 2024-01-25 | On-time | 2024-05-19 | 115 | 2024-05-20 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46072187 | T2 EI PIT #1-COTTONWOOD 019/160 UNBUR;Y | ICQ
LC | 126194707 | T002/012 | T2 EI TULUCAY-NAPA #1 T002/012 RPR SPLW | LAKEVLLE | ETL.8180.INSL.NCER | 2023-05-20 | 2023-05-20 | 2024-01-18 | On-time | 2024-05-19 | 122 | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46096606 | T2 EI TULUCAY-NAPA #1 T002/012 RPR SPLW | ICW
LC | 126229757 | 043/340 | T2 DI BRDGVLL-CTTNWD 43/340 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-05-25 | 2023-05-18 | 2024-06-07 | Late | 2024-05-17 | -21 | 2024-05-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46061188 | T2 DI BRDGVLL-CTTNWD 43/340 RPR OPGW | ICS
LC | 126194920 | 020/165 | T2 EI PIT #1-COTTONWOOD 020/165 RPL HRDT | TABLEMTN | ETL.5390.TOWR | 2023-05-20 | 2023-05-20 | 2024-01-29 | On-time | 2024-05-19 | 111 | 2024-05-20 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46072188 | T2 EI PIT #1-COTTONWOOD 020/165 RPL HRDT | ICQ
LC | 126229810 | 020/011 | T2 DI MAPLE CRK-HOOPA 20/011 RPR ANCW | EUREKA | ETL.7490.POLE.NWOD | 2023-05-25 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45813253 | T2 DI MAPLE CRK-HOOPA 20/011 RPR ANCW | ICW
LC | 126229940 | 039/315 | T2 DI BRDGVLL-CTTNWD 39/315 COTTER | TABLEMTN | ETL.1110.INSL.CERA | 2023-05-25 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46061181 | T2 DI BRDGVLL-CTTNWD 39/315 COTTER | ICS
LC | 126229946 | 039/315 | T2 DI BRDGVLL-CTTNWD 39/315 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-05-25 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46088773 | T2 DI BRDGVLL-CTTNWD 39/315 RPR SHLS | ICS
LC | 126195389 | 009/054 | T2 EI BALCH-SANGER 9/054 BNT STEEL | FRESNO | ETL.1050.TOWR | 2023-05-20 | 2023-05-20 | 2024-04-12 | On-time | 2024-05-19 | 37 | 2024-05-20 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46070721 | T2 EI BALCH-SANGER 9/054 BNT STEEL | ICQ
LC | 126195482 | 008/051 | T2 EI BALCH-SANGER 8/051 REGRADE | FRESNO | ETL.1050.TOWR | 2023-05-20 | 2023-05-20 | 2024-01-19 | On-time | 2024-05-19 | 121 | 2024-05-20 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46070720 | T2 EI BALCH-SANGER 8/051 REGRADE | ICQ
LC | 126230077 | 013/264 | T2 DI HAT CRK #1-WSTWD 13/264 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-25 | 2023-05-18 | 2024-06-15 | Late | 2024-05-17 | -29 | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512607 | T2 DI HAT CRK #1-WSTWD 13/264 RPL STRW | 70Y
LC | 126198232 | 069/499 | T2 EI BRIDGEVILE-CTTNWD 69/499R RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-05-22 | 2023-05-20 | 2024-04-02 | On-time | 2024-05-19 | 47 | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171677 | T2 EI BRIDGEVILE-CTTNWD 69/499RRPR GYWW | ICW
LC | 126198238 | 069/499 | T2 EI BRIDGEVILE-CTTNWD 69/499L RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-05-22 | 2023-05-20 | 2024-04-02 | On-time | 2024-05-19 | 47 | 2024-05-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171677 | T2 EI BRIDGEVILE-CTTNWD 69/499RRPR GYWW | ICW
LC | 126454701 | 014/333 | T2 DRM-GRS VLY-WMR 14/333 RPR GYWW | SACTO | ETL.6760.POLE.NWOD | 2023-06-26 | 2023-05-20 | 2024-01-11 | On-time | 2024-05-19 | 129 | 2024-05-20 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062871 | T2 DRM-GRS VLY-WMR 14/333 RPR GYWW | ICW
LC | 126230107 | 041/331 | T2 DI BRDGVL-CTNWD- 41/331L RPL HRDD | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-25 | 2023-05-18 | 2024-06-03 | Late | 2024-05-17 | -17 | 2023-11-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46062777 | T2 DI BRDGVL-CTNWD- 41/331L RPL HRDD | ICW
LC | 126230183 | 042/337B | T2 DI BRDGVL-COTTWD 42/337B RPR OPGW | TABLEMTN | ETL.1110.POLE.NWOD | 2023-05-25 | 2023-05-17 | 2024-06-04 | Late | 2024-05-16 | -19 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Wood | Repair | 46062711 | T2 DI BRDGVL-COTTWD 42/337B RPR OPGW | ICW
LC | 126230186 | 001/035 | T2 DI WINTU TAP 01/35 RPL STRW | TABLEMTN | ETL.6311.POLE.WOOD | 2023-05-25 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35526663 | T2 DI WINTU TAP 01/35 RPL STRW | 70Y
LC | 126199811 | 000/004 | T2 WV COLEMAN-SOUTH 00/004 RPL PL | TABLEMTN | ETL.6450.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-05-03 | On-time | 2024-05-21 | 18 | 2024-05-22 | 372 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31617794 | T2 DI COLEMAN-SOUTH 0/4 GO95 CLEARNC | 93G
LC | 126230234 | 050/001 | T2 DI TRINITY-MAPLE CREEK 50/1L RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-05-25 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506453 | T2 DI TRINITY-MAPLE CREEK 50/1L RPL POLE | 70Y
LC | 126200027 | 028/168 | T2 EI TMBLR-SN LS OBSPO 28/168 RPL INSS | PISMOBCH | ETL.3960.INSL.CERA | 2023-05-22 | 2023-05-22 | 2024-04-01 | On-time | 2024-05-21 | 50 | 2024-05-22 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513945 | T2 EI TMBLR-SN LS OBSPO 56/311 RPL INSS | 93K
LC | 126230236 | 050/001 | T2 DI TRINITY-MAPLE CREEK 50/1R RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-05-25 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506453 | T2 DI TRINITY-MAPLE CREEK 50/1L RPL POLE | 70Y
LC | 126230282 | 050/001 | T2 DI TRINITY-MAPLE CREEK 50/1C RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-05-25 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506453 | T2 DI TRINITY-MAPLE CREEK 50/1L RPL POLE | 70Y
LC | 126200090 | 005/112 | T2 EI COTTONWD-RED BLUFF 5/112 RPR STRW | TABLEMTN | ETL.6660.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-04-10 | On-time | 2024-05-21 | 41 | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46075847 | T2 EI COTTONWD-RED BLUFF 5/112 RPR STRW | ICW
LC | 126201108 | T002/007 | T2 EI TULUCAY-NAPA #1 T02/07 RPR SPLW | LAKEVLLE | ETL.8180.INSL.NCER | 2023-05-22 | 2023-05-22 | 2024-01-18 | On-time | 2024-05-21 | 124 | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46096608 | T2 EI TULUCAY-NAPA #1 T02/07 RPR SPLW | ICW
LC | 126230299 | 007/040 | T2 DI MRR BY-SN LS OBSP #1 7/40 RPL INSS | PISMOBCH | ETL.2820.INSL | 2023-05-25 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35538927 | T2 DI MRR BY-SN LS OBSP #1 7/40 RPL INSS | 93K
LC | 126230311 | 016/323 | T2 DI HAT CRK #1-WSTW 016/323 RPR CRSW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-25 | 2023-05-19 | 2024-06-16 | Late | 2024-05-18 | -29 | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46062860 | T2 DI HAT CRK #1-WSTW 016/323 RPR CRSW | ICW
LC | 126230327 | 008/067 | T2 DI PIT#6 JCT-RND MT 8/67 RPL INSS | TABLEMTN | ETL.5440.INSL.CERA | 2023-05-25 | 2023-05-18 | 2024-06-21 | Late | 2024-05-17 | -35 | 2024-05-18 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509003 | T2 DI PIT#6 JCT-RND MNTN 8/69 RPL INSS | 93K
LC | 126230360 | 016/312 | T2 DI HT CRK #1-WESTWOOD 16/312 RPR STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-25 | 2023-05-18 | 2024-06-16 | Late | 2024-05-17 | -30 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062737 | T2 DI HT CRK #1-WESTWOOD 16/312 RPR STRW | ICW
LC | 126230363 | 003/065 | T2 DI HAT CRK #1-WSTW 3/65 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-25 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512488 | T2 DI HAT CRK #1-WSTW 3/65 RPL POLE | 70Y
LC | 126202107 | T002/002 | T2 EI TULUCAY-NAPA #1 T02/02 RPR GYWW | LAKEVLLE | ETL.8180.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-01-13 | On-time | 2024-05-21 | 129 | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46077716 | T2 EI TULUCAY-NAPA #1 T02/02 RPR GYWW | ICW
LC | 126230433 | 004/087 | T2 DI HAT CRK #1-WSTW 4/087 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-25 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512494 | T2 DI HAT CRK #1-WSTWD 4/86 RPL STRW | 70Y
LC | 126230493 | 037/295 | T2 DI BRDGVL-CTNWD 37/295L RPR HRDW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-25 | 2023-05-18 | 2024-06-03 | Late | 2024-05-17 | -17 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46062764 | T2 DI BRDGVL-CTNWD 37/295L RPR HRDW | ICW
LC | 126230498 | 035/286 | T2 DI BRDGVL-CTNWD 35/286 RPR INSS | TABLEMTN | ETL.1110.INSL.CERA | 2023-05-25 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46061177 | T2 DI BRDGVL-CTNWD 35/286 RPR INSS | ICS
LC | 126230538 | 036/293 | T2 DI BRDGVL-CTNWD 36/293L RPR GRWW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-25 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 46062763 | T2 DI BRDGVL-CTNWD 36/293L RPR GRWW | ICW
LC | 126230540 | 014/274 | T2 DI HAT CRK #1-WSTWD 014/274 RPR CRSW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-25 | 2023-05-19 | 2024-06-13 | Late | 2024-05-18 | -26 | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46062852 | T2 DI HAT CRK #1-WSTWD 014/274 RPR CRSW | ICW
LC | 126230568 | 006/052 | T2 DI PIT #6 JCT-RND MTN 6/52 RPR SWITCH | TABLEMTN | ETL.5440.TOWR | 2023-05-25 | 2023-05-17 | 2024-06-20 | Late | 2024-05-16 | -35 | 2024-05-17 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 46061192 | T2 DI PIT #6 JCT-RND MTN 6/52 RPR SWITCH | ICE
LC | 126230663 | 038/305 | T2 DI BRIDGVLL-COTTONWD 38/305L RPL POLE | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-25 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501390 | T2 DI BRDGVIL CTTNWD RPL 7 STRCTS | 70Y
LC | 126230665 | 038/305 | T2 DI BRIDGVLL-COTTONWD 38/305R RPL POLE | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-25 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501390 | T2 DI BRDGVIL CTTNWD RPL 7 STRCTS | 70Y
LC | 126232030 | 042/337A | T2 DI BRIDEGVL-COTTNWD 42/337A RPR GYWW | TABLEMTN | ETL.1110.POLE.NWOD | 2023-05-26 | 2023-05-17 | 2024-06-04 | Late | 2024-05-16 | -19 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062709 | T2 DI BRIDEGVL-COTTNWD 42/337A RPR GYWW | ICW
LC | 126202108 | T002/002 | T2 EI TULUCAY-NAPA #1 T02/02 RPR STRW | LAKEVLLE | ETL.8180.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-01-13 | On-time | 2024-05-21 | 129 | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46096607 | T2 EI TULUCAY-NAPA #1 T02/02 RPR STRW | ICW
LC | 126232195 | 037/294 | T2 DI BRDGVLL-COTTONWD 037/294 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-05-26 | 2023-05-18 | 2024-06-03 | Late | 2024-05-17 | -17 | 2024-05-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46061178 | T2 DI BRDGVLL-COTTONWD 037/294 RPR OPGW | ICS
LC | 126232240 | 036/289 | T2 DI BRDGVL-CTTNWD 36/289L RPR GRWW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-26 | 2023-05-18 | 2024-06-01 | Late | 2024-05-17 | -15 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 46062761 | T2 DI BRDGVL-CTTNWD 36/289L RPR GRWW | ICW
LC | 126232296 | 000/007 | T2 DI CARIBOU-WESTWOOD 0/7 RPR CNDW | TABLEMTN | ETL.6300.INSL.NCER | 2023-05-26 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46073797 | T2 DI CARIBOU-WESTWOOD 0/7 RPR CNDW | ICW
LC | 126232366 | 039/309 | T2 DI BRIDGEVILLE-CTTNWD 39/309 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-05-26 | 2023-05-18 | 2024-05-31 | Late | 2024-05-17 | -14 | 2024-05-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46061180 | T2 DI BRIDGEVILLE-CTTNWD 39/309 RPR OPGW | ICS
LC | 126202241 | 045/007 | T2 EI FORT ROSS-GUALALA 45/007 RPR GYWW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-03-26 | On-time | 2024-05-21 | 56 | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073731 | T2 EI FORT ROSS-GUALALA 45/007 RPR GYWW | ICW
LC | 126232822 | 036/006 | T2 DI TRNTY MPLE CRK 36/06 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-26 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170741 | T2 DI TRNTY MPLE CRK 36/06 RPR GYWW | ICW
LC | 126232912 | 007/035 | T2 DI IGNACIO-ALTO 7/35 RPL INSS | LAKEVLLE | ETL.7150.INSL.CERA | 2023-05-26 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31677490 | DI IGNACIO-ALTO- RPL INSS IN 2 TWRS. | 93K
LC | 126202389 | 021/174 | T2 EI PIT #1-COTTONWOOD 21/174 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2023-05-22 | 2023-05-22 | 2024-01-29 | On-time | 2024-05-21 | 113 | 2024-05-22 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46072193 | T2 EI PIT #1-COTTONWOOD 21/174 RPR FOND | ICQ
LC | 126202450 | 021/176 | T2 EI PIT #1-COTTONWOOD 21/176 RPR FOND | TABLEMTN | ETL.5390.TOWR | 2023-05-22 | 2023-05-22 | 2024-01-29 | On-time | 2024-05-21 | 113 | 2024-05-22 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46072194 | T2 EI PIT #1-COTTONWOOD 21/176 RPR FOND | ICQ
LC | 126233537 | 041/325 | T2 DI BRDGVLL-CTTNWD 41/325 GROUND WIRE | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-26 | 2023-05-17 | 2024-06-13 | Late | 2024-05-16 | -28 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 46062706 | T2 DI BRDGVLL-CTTNWD 41/325 GROUND WIRE | ICW
LC | 126233708 | 083/587 | T2 DI BRDGVIL CTTNWD 83/587 RPR SHLS | EUREKA | ETL.1110.TOWR | 2023-05-26 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46102195 | T2 DI BRDGVIL CTTNWD 83/587 RPR SHLS | ICS
LC | 126234238 | 009/102A | T2 DI DRUM SUMMIT#2 9/102A RPR GYWW | SACTO | ETL.1450.POLE.WOOD | 2023-05-26 | 2023-05-22 | 2024-06-16 | Late | 2024-05-21 | -26 | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079219 | T2 DI DRUM SUMMIT#2 09/102A RPR GYWW | ICW
LC | 126202571 | 001/022B | T2 EI CARIBOU-WSTWD 01/022B RPR ANCW | TABLEMTN | ETL.6300.POLE.NWOD | 2023-05-22 | 2023-05-22 | 2023-08-12 | On-time | 2024-05-21 | 283 | 2023-11-22 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45945200 | T2 EI CARIBOU-WSTWD 01/022B RPR ANCW | ICS
LC | 126234476 | 041/327 | T2 DI BRDGVLL-CTTNWD 41/327L RPR OPGW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-26 | 2023-05-18 |  | Late | 2024-05-17 |  | 2023-08-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Wood | Repair | 46062776 | T2 DI BRDGVLL-CTTNWD 41/327L RPR OPGW | ICW
LC | 126234503 | 041/327 | T2 DI BRDGVLL-CTTNWD 41/327 RPL INSW | TABLEMTN | ETL.1110.INSL.CERA | 2023-05-26 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35501427 | T2 DI BRDGVLL-CTTNWD 41/327 RPL INSW | 93I
LC | 126234536 | 026/011 | T2 DI MAPLE CREEK-HOOPA 026/011 RPL POLE | EUREKA | ETL.7490.POLE.WOOD | 2023-05-26 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526562 | T2 DI MAPLE CREEK-HOOPA 026/011 RPL POLE | 70Y
LC | 126234577 | 012/241 | T2 DI HAT CRK #1-WSTWD 12/241 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-26 | 2023-05-18 | 2024-06-13 | Late | 2024-05-17 | -27 | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512604 | T2 DI HAT CRK #1-WSTWD 12/241 RPL STRW | 70Y
LC | 126234580 | 009/102C | T2 DI DRUM SUMMIT#2 9/102C RPL ANCW | SACTO | ETL.1450.POLE.NWOD | 2023-05-26 | 2023-05-22 | 2024-06-16 | Late | 2024-05-21 | -26 | 2024-05-22 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35484102 | T2 DI DRUM SUMMIT#2 09/102C RPL ANCW | 93E
LC | 126234685 | 011/096 | T2 DI CABRLLO-SANTA YNZ SS 11/96 RMV VEG | PISMOBCH | ETL.1200.POLE.WOOD | 2023-05-26 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126203901 | 011/230 | T2 EI HAT CREK #1-WSTWOD 11/230 RPR INSW | TABLEMTN | ETL.7030.INSL | 2023-05-22 | 2023-05-22 | 2023-07-28 | On-time | 2024-05-21 | 298 | 2023-11-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45847707 | T2 EI HAT CREK #1-WSTWOD 11/230 RPR INSW | ICW
LC | 126235064 | 005/062 | T2 DI PIT #5-RND MTN #1 5/62R RPL POLE | TABLEMTN | ETL.5420.POLE.WDPS | 2023-05-26 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526327 | T2 DI PIT#5-RND MT#1 RPL 4 STRW | 70Y
LC | 126235460 | :007/003 | T2 DI CARIBOU #2 :007/003 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-26 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527046 | T2 DI CARIBOU #2 :007/003 RPL STRW | 70Y
LC | 126204287 | 045/000 | T2 EI FORT ROSS-GUALALA 45/000 RPR GYWW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-04-18 | On-time | 2024-05-21 | 33 | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073729 | T2 EI FORT ROSS-GUALALA 45/000 RPR GYWW | ICW
LC | 126235727 | 008/157 | T2 DI CARIBOU-WESTWD 8/157 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-26 | 2023-05-16 |  | Late | 2024-05-15 |  | 2024-05-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519116 | T2 DI CARIBOU-WESTWOOD 08/157 RPL STRW | 70Y
LC | 126235791 | A005/109 | T2 DI IGNACIO-ALTO A005/109 RPL POLE | LAKEVLLE | ETL.1042.POLE.WOOD | 2023-05-26 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35530636 | T2 DI IGNACIO-ALTO A005/109 RPL POLE | 70Y
LC | 126235928 | 005/003 | T2 EI MENDCN-WLLTS-FRT BRGG 5/3 RPR STRW | WILLITS | ETL.7550.POLE.WOOD | 2023-05-26 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46214147 | T2 EI MENDCN-WLLTS-FRT BRGG 5/3 RPR POLE | ICW
LC | 126235948 | 037/296 | T2 DI BRDGVL-CTNWD 37/296L RPR GRWW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-26 | 2023-05-18 | 2024-06-03 | Late | 2024-05-17 | -17 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 46062765 | T2 DI BRDGVL-CTNWD 37/296L RPR GRWW | ICW
LC | 126204379 | 006/026 | T2 EI MORRO BAY-SLR SS #1 6/26 RPL INSS | PISMOBCH | ETL.5300.INSL | 2023-05-22 | 2023-05-22 | 2024-05-08 | On-time | 2024-05-21 | 13 | 2024-05-22 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35534595 | T2 EI MORRO BAY-SLR SS #1 6/26 RPL INSS | 93K
LC | 126204905 | 003/006 | T2 EI TRINITY-MAPLE CREEK 3/6 RPR ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-22 | 2023-05-22 | 2024-02-20 | On-time | 2024-05-21 | 91 | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46070779 | T2 EI TRINITY-MAPLE CREEK 3/6 RPR ANCW | ICW
LC | 126204947 | 065/000 | T2 EI HUMBOLDT-TRINITY 65/0L RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-05-22 | 2023-05-22 | 2024-04-12 | On-time | 2024-05-21 | 39 | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096532 | T2 EI HUMBOLDT-TRINITY 065/000L RPR GYWW | ICW
LC | 126236375 | 009/104C | T2 DI DRUM SUMMIT#2 9/104C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-05-26 | 2023-05-22 | 2024-05-22 | Late | 2024-05-21 | -1 | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101311 | T2 DI DRUM SUMMIT#2 09/104C RPR GYWW | ICW
LC | 126236634 | 017/004 | T2 DI MAPLE CREEK-HOOPA 17/04 RPR INSW | EUREKA | ETL.7490.INSL.NCER | 2023-05-26 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46203520 | T2 DI MAPLE CREEK-HOOPA 17/04 RPR INSW | ICW
LC | 126236683 | 007/148 | T2 DI HAT CRK #1-WSTW 7/148 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-26 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512496 | T2 DI HAT CREEK#1 07/147 RPL PL | 70Y
LC | 126237058 | 035/005 | T2 EI FORT ROSS-GUALALA 35/005 RPL INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-05-26 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35548554 | T2 EI FORT ROSS-GUALALA 35/005 RPL INSW | 93I
LC | 126237088 | 073/370 | T2 EI MLN-RND MTN #2 73/370 COMPLETE | TABLEMTN | ETL.6020.TOWR | 2023-05-26 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation-Tower | Cage Clearing
LC | 126204949 | 065/000 | T2 EI HUMBOLDT-TRINITY 65/0R RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-05-22 | 2023-05-22 | 2024-04-12 | On-time | 2024-05-21 | 39 | 2024-05-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096532 | T2 EI HUMBOLDT-TRINITY 065/000L RPR GYWW | ICW
LC | 126205171 | 007/044 | T2 EI BALCH-SANGER 7/044 REGRADE | FRESNO | ETL.1050.POLE.NWOD | 2023-05-22 | 2023-05-22 | 2024-01-30 | On-time | 2024-05-21 | 112 | 2024-05-22 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46069699 | T2 EI BALCH-SANGER 7/044 REGRADE | ICQ
LC | 126237197 | 027/000 | T2 PHILO JCT-ELK 27/0 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-05-26 | 2023-05-26 | 2024-06-04 | Late | 2024-05-25 | -10 | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35522273 | T2 PHILO JCT-ELK 27/0 RPL POLE | 70Y
LC | 126237312 | 038/302 | T2 DI BRDGVL-CTNWD 38/302L RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-26 | 2023-05-18 | 2024-06-03 | Late | 2024-05-17 | -17 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062767 | T2 DI BRDGVL-CTNWD 38/302L RPR GYWW | ICW
LC | 126237315 | 038/302 | T2 DI BRDGVL-CTNWD- 38/302R RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-26 | 2023-05-18 | 2024-06-03 | Late | 2024-05-17 | -17 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062768 | T2 DI BRDGVL-CTNWD- 38/302R RPR GYWW | ICW
LC | 126237347 | 015/305 | T2 DI CARIBOU-WSWD 15/305 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-05-26 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519121 | T2 DI CARIBOU-WSWD 15/305 RPL STRW | 70Y
LC | 126233450 | 036/004 | T2 DI TRNTY MPLE CRK 36/04L RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-26 | 2023-05-22 | 2023-10-06 | On-time | 2024-05-21 | 228 | 2023-11-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45813255 | T2 DI TRNTY MPLE CRK 36/04 RPR GYWW | ICW
LC | 126237404 | 073/000 | T2 EI HUMBOLDT-TRINITY 73/0R RPR STRW | EUREKA | ETL.1820.POLE.STPS | 2023-05-26 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46096539 | T2 EI HUMBOLDT-TRINITY 73/0R RPR STRW | ICW
LC | 126237406 | 073/000 | T2 EI HUMBOLDT-TRINITY 73/0L RPR STRW | EUREKA | ETL.1820.POLE.STPS | 2023-05-26 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46096539 | T2 EI HUMBOLDT-TRINITY 73/0R RPR STRW | ICW
LC | 126237583 | 003/014 | T2 DI LOWER LK-HMSTK 3/14 RPR STRW | WILLITS | ETL.1481.POLE.WOOD | 2023-05-26 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46213264 | T2 DI LOWER LK-HMSTK 3/14 RPR STRW | ICW
LC | 126237734 | 014/282 | T2 DI HAT CRK #1-WSTWD 14/282 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-26 | 2023-05-18 | 2024-06-12 | Late | 2024-05-17 | -26 | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512616 | T2 DI HAT CRK #1-WSTWD 14/282 RPL STRW | 70Y
LC | 126237849 | 014/278 | T2 DI HAT CRK #1-WSTWD 14/278 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-26 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35552843 | T2 DI HAT CRK #1-WSTWD 14/278 REFRAME | 93E
LC | 126237861 | 013/266 | T2 DI HAT CRK #1-WSTWD 13/266 RPR STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-26 | 2023-05-18 | 2024-06-15 | Late | 2024-05-17 | -29 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062735 | T2 DI HAT CRK #1-WSTWD 13/266 RPR STRW | ICW
LC | 126237901 | 003/071 | T2 DI HAT CRK #1-WSTW 003/071 RPL CRSW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-26 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35512490 | T2 DI HAT CRK #1-WSTW 003/071 RPL CRSW | 93E
LC | 126237991 | 013/263 | T2 DI HAT CRK #1-WSTW 13/263 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-26 | 2023-05-18 | 2024-06-14 | Late | 2024-05-17 | -28 | 2024-05-18 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35512605 | T2 DI HAT CR#1-WW 13/261 RPL CRSW | 93E
LC | 126237994 | 008/162 | T2 DI HAT CRK #1-WSTW 008/162 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-26 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35550228 | T2 DI HT CRK#1-WSWD 8/157 REFRAME | 93E
LC | 126234445 | 081/570 | T2 DI BRDGVIL CTTNWD 81/570 RPL HRDT | EUREKA | ETL.1110.TOWR | 2023-05-26 | 2023-05-22 | 2024-04-22 | On-time | 2024-05-21 | 29 | 2024-05-22 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46072196 | T2 DI BRDGVIL CTTNWD 81/570 RPL HRDT | ICQ
LC | 126238059 | 003/076 | T2 DI HAT CRK #1-WSTWD 3/76 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-26 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512493 | T2 DI HAT CRK #1-WSTWD 3/76 RPL STRW | 70Y
LC | 126238077 | 013/257 | T2 DI HAT CRK #1-WSTWD 13/257 RPL HRDW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-26 | 2023-05-18 | 2024-06-12 | Late | 2024-05-17 | -26 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46062733 | T2 DI HAT CRK #1-WSTWD 13/257 RPL HRDW | ICW
LC | 126234735 | 008/017 | T2 DI CARIBOU-PLMS JCT 8/017 RPR JMPW | TABLEMTN | ETL.6290.INSL.NCER | 2023-05-26 | 2023-05-22 | 2023-09-29 | On-time | 2024-05-21 | 235 | 2023-11-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45810524 | T2 DI CARIBOU-PLMS JCT 8/017 RPR JMPW | ICW
LC | 126235553 | 022/086 | T2 DI EXCHEQUR-INDIAN FLT 22/86 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-05-26 | 2023-05-22 | 2023-12-12 | On-time | 2024-05-21 | 161 | 2023-08-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45895179 | T2 DI EXCHEQUR-INDIAN FLT 22/86 RPR JMPS | ICS
LC | 126238155 | 021/005 | T2 EI TRINITY-MAPLE CREEK 21/5 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-26 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503524 | T2 EI TRINITY-MAPLE CREEK 21/5 RPL POLE | 70Y
LC | 126238172 | 025/004 | T2 EI TRINITY-MAPLE CREEK 25/4 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-26 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504061 | T2 EI TRINITY-MAPLE CREEK 25/04 RPL STRW | 70Y
LC | 126238983 | 017/001A | T2 DI TRINITY-MAPLE CRK 17/001A RPR JUMW | EUREKA | ETL.8170.INSL.NCER | 2023-05-26 | 2023-05-22 | 2024-05-14 | On-time | 2024-05-21 | 7 | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46070803 | T2 DI TRINITY-MAPLE CRK 17/001A RPR JUMW | ICW
LC | 126238221 | 084/590 | T2 DI BRDGVIL CTTNWD 84/590L RPL POLE | EUREKA | ETL.1110.POLE.WDPS | 2023-05-26 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505113 | T2 EI BRIDGEV-COTTONWOOD 84/592 RPL POLE | 70Y
LC | 126238227 | 009/104B | T2 DI DRUM SUMMIT#2 9/104B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-05-26 | 2023-05-22 | 2024-05-22 | Late | 2024-05-21 | -1 | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101312 | T2 DI DRUM SUMMIT#2 09/104B RPR GYWW | ICW
LC | 126239113 | 009/103 | T2 DI DRUM-SUMMIT #2 9/103 RPL HRDT | SACTO | ETL.1450.TOWR | 2023-05-26 | 2023-05-22 | 2024-04-10 | On-time | 2024-05-21 | 41 | 2024-05-22 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46072192 | T2 DI DRUM-SUMMIT #2 9/103 RPL HRDT | ICQ
LC | 126238302 | 255 | T2NT DI PIT #6 JCT-RND MTN 6/51 RPR SWTC | TABLEMTN | ETL.5440.SWIT | 2023-05-26 | 2023-05-23 | 2024-06-20 | Late | 2024-05-22 | -29 | 2024-05-23 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 46075852 | T2NT DI PIT #6 JCT-RND MTN 6/51 RPR SWTC | ICE
LC | 126238389 | 009/104A | T2 DI DRUM SUMMIT#2 9/104A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-05-26 | 2023-05-22 | 2024-05-22 | Late | 2024-05-21 | -1 | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101313 | T2 DI DRUM SUMMIT#2 09/104A RPR GYWW | ICW
LC | 126238413 | 042/339C | T2 DI BRIDGEVILE-COTNWD 42/339C RPR GYWS | TABLEMTN | ETL.1110.POLE.NWOD | 2023-05-26 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46061186 | T2 DI BRIDGEVILE-COTNWD 42/339C RPR GYWS | ICS
LC | 126238414 | 042/339C | T2 DI BRIDEGVILE-CTTNWD 42/339C RPR INSW | TABLEMTN | ETL.1110.INSL.CERA | 2023-05-26 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46061187 | T2 DI BRIDEGVILE-COTONWOD 42/339C COTTER | ICS
LC | 126238418 | 034/005 | T2 DI FORT ROSS-GUALALA 34/5 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-26 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506664 | T2 DI FORT ROSS-GUALALA 34/05 RPL STRW | 70Y
LC | 126238423 | 083/583 | T2 DI BRDGVIL CTTNWD 83/583L RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-05-26 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172021 | T2 DI BRDGVIL CTTNWD 83/583L RPR GYWW | ICW
LC | 126238426 | 083/583 | T2 DI BRDGVIL CTTNWD 83/583 RMV VEG | EUREKA | ETL.1110.POLE.STPS | 2023-05-26 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126239114 | 219 | T2 DI DRUM-SUMMIT #2 9/103 RPR SWITCH | SACTO | ETL.1450.SWIT | 2023-05-26 | 2023-05-22 | 2024-04-10 | On-time | 2024-05-21 | 41 | 2024-05-22 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 46097961 | T2 DI DRUM-SUMMIT #2 9/103 RPR SWITCH | ICE
LC | 126238490 | 083/583 | T2 DI BRDGVIL CTTNWD 83/583 COTTER | EUREKA | ETL.1110.INSL.NCER | 2023-05-26 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46172021 | T2 DI BRDGVIL CTTNWD 83/583L RPR GYWW | ICW
LC | 126238491 | 083/583 | T2 DI BRDGVIL CTTNWD 83/583R RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-05-26 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172021 | T2 DI BRDGVIL CTTNWD 83/583L RPR GYWW | ICW
LC | 126240104 | 018/095 | T2 DI RND MNT-TBL MTN#2 18/95 RPR SHIELD | TABLEMTN | ETL.6070.TOWR | 2023-05-27 | 2023-05-22 | 2023-11-11 | On-time | 2024-05-21 | 192 | 2024-05-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46073829 | T2 DI RND MNT-TBL MTN#2 18/95 RPR SHIELD | ICS
LC | 126238554 | 005/109 | T2 DI HAT CRK#1-WESTWD 5/109 GO95 RPL PL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-26 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35529611 | T2 DI HAT CRK #1-WESTWOOD 5/109 GO95 | 93G
LC | 126240339 | 082/578 | T2NT DI BRDGEVLE-COT 82/578L RPR ADSS | EUREKA | ETL.1110.POLE.STPS | 2023-05-27 | 2023-05-22 | 2023-10-30 | On-time | 2024-05-21 | 204 | 2023-08-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45810537 | T2NT DI BRDGEVLE-COT 82/578L RPR SHLW | ICW
LC | 126238607 | 022/600 | T2 DI CARIBOU #2 22/600 RPL HRDD | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-26 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46062738 | T2 DI CARIBOU #2 22/600 RPL HRDD | ICW
LC | 126240436 | 013/013 | T2 DI CARIBOU-PLUMAS 13/13 RPR GYWW | TABLEMTN | ETL.6290.POLE.NWOD | 2023-05-27 | 2023-05-22 | 2024-05-08 | On-time | 2024-05-21 | 13 | 2023-11-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073788 | T2 DI CARIBOU-PLUMAS 13/13 RPR GYWW | ICW
LC | 126240460 | 013/013 | T2 DI CARIBOU-PLUMAS 13/13 RPR JMPRW | TABLEMTN | ETL.6290.INSL.NCER | 2023-05-27 | 2023-05-22 | 2024-05-08 | On-time | 2024-05-21 | 13 | 2023-08-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46194279 | T2 DI CARIBOU-PLUMAS 13/13 RPR JMPRW | ICW
LC | 126241039 | 000/004 | T2 DI CARIBOU-WESTWOOD 0/4 RPR ANCW | TABLEMTN | ETL.6300.POLE.NWOD | 2023-05-27 | 2023-05-22 | 2023-08-08 | On-time | 2024-05-21 | 287 | 2023-11-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45810521 | T2 DI CARIBOU-WESTWOOD 0/4 RPR ANCW | ICW
LC | 126238786 | 009/181 | T2 DI HAT CRK #1-WSTW 9/181 RPR CRSW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-26 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46062840 | T2 DI HAT CRK #1-WSTW 9/181 RPR CRSW | ICW
LC | 126251022 | :008/058A | T2 DI ROCK CREEK-POE :8/58A RPR GYWS | TABLEMTN | ETL.5630.POLE.NWOD | 2023-05-30 | 2023-05-22 | 2024-04-23 | On-time | 2024-05-21 | 28 | 2024-05-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46072189 | T2 DI ROCK CREEK-POE :8/58A RPR GYWS | ICS
LC | 126251402 | :008/058C | T2 DI ROCK CREEK-POE :8/58C RPR GYWS | TABLEMTN | ETL.5630.POLE.NWOD | 2023-05-30 | 2023-05-22 | 2024-04-23 | On-time | 2024-05-21 | 28 | 2024-05-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46072191 | T2 DI ROCK CREEK-POE :8/58C RPR GYWS | ICS
LC | 126251596 | :008/058B | T2 DI ROCK CREEK-POE :8/58B RPR GYWS | TABLEMTN | ETL.5630.POLE.NWOD | 2023-05-30 | 2023-05-22 | 2024-04-23 | On-time | 2024-05-21 | 28 | 2024-05-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46072190 | T2 DI ROCK CREEK-POE :8/58B RPR GYWS | ICS
LC | 126238831 | 035/281 | T2 DI BRDGVL-CTNWD-35/281L RPR STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-26 | 2023-05-18 | 2024-06-01 | Late | 2024-05-17 | -15 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062739 | T2 DI BRDGVL-CTNWD-35/281L RPR STRW | ICW
LC | 126238832 | 035/281 | T2 DI BRIDGVLL-COTTONWD 35/281L RPL ANCW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-26 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35525611 | T2 DI BRIDGVLL-COTTONWD 35/281L RPL ANCW | 93E
LC | 126251832 | 017/000 | T2 DI TRINITY-MAPLE CREEK 017/000 COTTER | EUREKA | ETL.8170.INSL.NCER | 2023-05-30 | 2023-05-22 | 2024-05-14 | On-time | 2024-05-21 | 7 | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46070802 | T2 DI TRINITY-MAPLE CREEK 017/000 COTTER | ICW
LC | 126238861 | 008/157 | T2 DI HT CRK#1-WSWD 8/157 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-26 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35550228 | T2 DI HT CRK#1-WSWD 8/157 REFRAME | 93E
LC | 126238862 | 078/557 | T2 DI BRDGVLL-CTTNWD 078/557 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-05-26 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46079109 | T2 DI BRDGVLL-CTTNWD 078/557 RPR OPGW | ICS
LC | 126238891 | 039/312 | T2 DI BRIDEGVL-COTTNWD 39/312L RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-26 | 2023-05-18 | 2024-06-06 | Late | 2024-05-17 | -20 | 2023-11-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062771 | T2 DI BRIDEGVL-COTTNWD 39/312L RPR GYWW | ICW
LC | 126238892 | 039/312 | T2 DI BRIDEGVL-COTTNWD 39/312R RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-26 | 2023-05-18 | 2024-06-06 | Late | 2024-05-17 | -20 | 2023-11-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062772 | T2 DI BRIDEGVL-COTTNWD 39/312R RPR GYWW | ICW
LC | 126238893 | 039/312 | T2 DI BRIDEGVL-COTTNWD 39/312C RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-26 | 2023-05-18 | 2024-06-06 | Late | 2024-05-17 | -20 | 2023-11-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062773 | T2 DI BRIDEGVL-COTTNWD 39/312C RPR GYWW | ICW
LC | 126251878 | 016/008 | T2 DI TRINITY-MAPLE CREEK 16/08 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-05-30 | 2023-05-22 | 2024-01-16 | On-time | 2024-05-21 | 126 | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46070801 | T2 DI TRINITY-MAPLE CREEK 16/08 RPR GYWW | ICW
LC | 126268004 | 57 | T2 DI TRNTY-MPL CRK 17/1B RPR SWTC | EUREKA | ETL.8170.SWIT | 2023-06-01 | 2023-05-22 | 2024-05-14 | On-time | 2024-05-21 | 7 | 2024-05-22 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 46070804 | T2 DI TRNTY-MPL CRK 17/1B RPR SWTC | ICE
LC | 126268005 | 017/001B | T2 DI TRNTY-MPL CRK 17/1B RPL HRDD | EUREKA | ETL.8170.POLE.NWOD | 2023-06-01 | 2023-05-22 | 2024-05-14 | On-time | 2024-05-21 | 7 | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46070805 | T2 DI TRNTY-MPL CRK 17/1B RPL HRDD | ICW
LC | 126239016 | 041/328 | T2 DI BRDGVL-CTTNWD 41/328R RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-26 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501390 | T2 DI BRDGVIL CTTNWD RPL 7 STRCTS | 70Y
LC | 126239017 | 041/328 | T2 DI BRDGVLE-CTTNWD 41/328L RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-26 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501390 | T2 DI BRDGVIL CTTNWD RPL 7 STRCTS | 70Y
LC | 126268287 | 012/000 | T2 DI TRNTY-MPL CREEK 12/0L RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-01 | 2023-05-22 | 2024-01-22 | On-time | 2024-05-21 | 120 | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46070800 | T2 DI TRNTY-MPL CREEK 12/0L RPR GYWW | ICW
LC | 126239062 | 048/000 | T2 DI TRNTY-MPL CRK 48/0 RPR INSW | EUREKA | ETL.8170.INSL | 2023-05-26 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46172254 | T2 DI TRNTY-MPL CRK 48/0 RPR INSW | ICW
LC | 126239066 | 048/000 | T2 DI TRNTY-MPL CRK 48/0 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-26 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172254 | T2 DI TRNTY-MPL CRK 48/0 RPR INSW | ICW
LC | 126239077 | 013/258 | T2 DI HAT CRK #1-WSTW 13/258 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-26 | 2023-05-19 | 2024-06-11 | Late | 2024-05-18 | -24 | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512604 | T2 DI HAT CRK #1-WSTWD 12/241 RPL STRW | 70Y
LC | 126239107 | 010/194 | T2 DI HT CRK#1-WSTWD 10/194 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-26 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35512601 | T2 DI HT CRK#1-WSTWD 10/194 REFRAME | 93E
LC | 126268289 | 012/000 | T2 DI TRNTY-MPL CREEK 12/0C RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-01 | 2023-05-22 | 2024-01-22 | On-time | 2024-05-21 | 120 | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46070800 | T2 DI TRNTY-MPL CREEK 12/0L RPR GYWW | ICW
LC | 126268331 | 012/000 | T2 DI TRNTY-MPL CREEK 12/0R RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-01 | 2023-05-22 | 2024-01-22 | On-time | 2024-05-21 | 120 | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46070800 | T2 DI TRNTY-MPL CREEK 12/0L RPR GYWW | ICW
LC | 126268334 | 012/000 | T2 DI TRNTY-MPL CREEK 12/0L RMV VEG | TABLEMTN | ETL.8170.POLE.WDPS | 2023-06-01 | 2023-05-22 | 2024-04-26 | On-time | 2024-05-21 | 25 | 2024-05-22 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126239873 | 007/137 | T2 DI CRBU-WSTWD 7/137L RPR GYWW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-27 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073810 | T2 DI CRBU-WSTWD 7/137L RPR GYWW | ICW
LC | 126268340 | 012/000 | T2 DI TRNTY-MPL CREEK 12/0C RMV VEG | TABLEMTN | ETL.8170.POLE.WDPS | 2023-06-01 | 2023-05-22 | 2024-04-26 | On-time | 2024-05-21 | 25 | 2024-05-22 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126239941 | 028/419 | T2 EI CLAY-MARTEL 28/419 RPL POLE | VICTOR | ETL.8250.POLE.WOOD | 2023-05-27 | 2023-05-27 | 2024-06-05 | Late | 2024-05-26 | -10 | 2024-05-27 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31653149 | T2 EI CLAY-MARTEL 27/399 RPL POLE | 70Y
LC | 126239990 | 025/012 | T2 DI MAPLE CREEK-HOOPA 025/012 RPR POLE | EUREKA | ETL.7490.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46190234 | T2 DI MAPLE CREEK-HOOPA 025/012 RPR POLE | ICW
LC | 126239993 | 025/012 | T2 DI MAPLE CREEK-HOOPA 025/012 RPL TIED | EUREKA | ETL.7490.INSL | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46190235 | T2 DI MAPLE CREEK-HOOPA 025/012 RPL TIED | ICW
LC | 126240023 | C006/031 | T2 DI PALERMO-COLGATE C6/31 INS HRDT | TABLEMTN | ETL.5360.TOWR | 2023-05-27 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46072197 | T2 DI PALERMO-COLGATE C6/31 INS HRDT | ICQ
LC | 126240033 | 67 | T2 DI CARIBOU-WSWD 019/398 RPL SWTC | TABLEMTN | ETL.6300.SWIT | 2023-05-27 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 427T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Switch-Wood | Replace | 35519104 | T2 DI CARIBOU-WSWD 019/398 RPL SWTC | 93H
LC | 126268341 | 012/000 | T2 DI TRNTY-MPL CREEK 12/0R RMV VEG | TABLEMTN | ETL.8170.POLE.WDPS | 2023-06-01 | 2023-05-22 | 2024-04-26 | On-time | 2024-05-21 | 25 | 2024-05-22 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126279376 | 081/571 | T2 DI BRDGVLL-CTTNWD 081/571 RPR GYWW | EUREKA | ETL.1110.POLE.WDPS | 2023-06-02 | 2023-05-22 | 2024-04-02 | On-time | 2024-05-21 | 49 | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171855 | T2 DI BRDGVLL-CTTNWD 081/571 RPR GYWW | ICW
LC | 126240083 | 007/153 | T2 DI HT CRK#1-WSTWD 7/153 CANCEL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35512498 | T2 DI HT CRK#1-WSTWD 7/153 REFRAME | 93E
LC | 126240089 | 004/083 | T2 DI HAT CRK #1-WSTW 004/083 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518644 | T2 DI HAT CRK #1-WSTW 004/083 RPL POLE | 70Y
LC | 126282380 | 017/001 | T2 DI TRNTY-MPL CRK 17/1 COMPLETE | EUREKA | ETL.8170.POLE.NWOD | 2023-06-02 | 2023-05-22 | 2024-05-14 | On-time | 2024-05-21 | 7 | 2023-11-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45844365 | T2 DI TRNTY-MPL CRK 38/12 RPL HRDD | ICW
LC | 126240113 | 013/255 | T2 DI HAT CRK #1-WSTW 013/255 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35557048 | T2 DI HAT CRK #1-WSTW 013/255 RPL POLE | 70Y
LC | 126282387 | 55 | T2 DI TRNTY-MPL CRK 17/1 RPR SWTC 55 | EUREKA | ETL.8170.SWIT | 2023-06-02 | 2023-05-22 | 2024-05-14 | On-time | 2024-05-21 | 7 | 2023-11-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 45844366 | T2 DI TRNTY-MPL CRK 38/12 RPR SWTC | ICW
LC | 126282671 | 007/080 | T2 DI DRUM SUMMIT #2 7/80 COMPLETE | SACTO | ETL.1450.POLE.WDPS | 2023-06-02 | 2023-05-22 | 2024-05-16 | On-time | 2024-05-21 | 5 | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46079380 | T2 DI DRUM SUMMIT #2 7/80 RPL HRDD | ICW
LC | 126240164 | 007/150 | T2 DI HT CRK#1-WSTWD 7/150 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35512497 | T2 DI HT CRK#1-WSTWD 7/150 REFRAME | 93E
LC | 126240183 | 000/007 | T2 DI MONTICELLO PH TAP 0/7 RPL STRW | LAKEVLLE | ETL.1602.POLE.WOOD | 2023-05-27 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35547991 | T2 DI MONTICELLO PH TAP 0/7 RPL STRW | 70Y
LC | 126240194 | 017/342 | T2 DI HT CRK #1-WESTWD 17/342 RPR STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 | 2024-06-13 | Late | 2024-05-18 | -26 | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062863 | T2 DI HT CRK #1-WESTWD 17/342 RPR STRW | ICW
LC | 126240211 | 037/000 | T2 DI TRINITY-MAPLE CREEK 37/0 RPR INSW | EUREKA | ETL.8170.INSL.NCER | 2023-05-27 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46096669 | T2 DI TRINITY-MAPLE CREEK 37/0 RPR INSW | ICW
LC | 126240217 | 037/000 | T2 DI TRINITY-MAPLE CREEK 37/0 RPR JUMW | EUREKA | ETL.8170.INSL.NCER | 2023-05-27 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46096669 | T2 DI TRINITY-MAPLE CREEK 37/0 RPR INSW | ICW
LC | 126240219 | 037/000 | T2 DI TRINITY-MAPLE CREEK 37/0 RPR CRSW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-27 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46096669 | T2 DI TRINITY-MAPLE CREEK 37/0 RPR INSW | ICW
LC | 126240237 | 007/147 | T2 DI HAT CREEK#1 07/147 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512496 | T2 DI HAT CREEK#1 07/147 RPL PL | 70Y
LC | 126510695 | 036/004 | T2 DI TRNTY MPLE CRK 36/04R RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-07-06 | 2023-05-22 | 2023-10-06 | On-time | 2024-05-21 | 228 | 2023-11-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45881343 | T2 DI TRNTY MPLE CRK 36/04R RPR GYWW | ICW
LC | 126240255 | 082/579 | T2 DI BRDGEVLE-COT 82/579R RPL ANCW | EUREKA | ETL.1110.POLE.STPS | 2023-05-27 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35505110 | T2 DI BRDGEVLE-COT 82/579R RPL ANCW | 93E
LC | 126240258 | 081/572 | T2 DI BRDGEVLE-COT 81/572 RPL DAMW | EUREKA | ETL.1110.INSL.NCER | 2023-05-27 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46171856 | T2 DI BRDGEVLE-COT 81/572 RPL DAMW | ICW
LC | 126240259 | 039/314 | T2 DI BRDGVL-CTNWD 39/314L RPR STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-27 | 2023-05-18 | 2024-06-16 | Late | 2024-05-17 | -30 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062774 | T2 DI BRDGVL-CTNWD 39/314L RPR STRW | ICW
LC | 126510701 | 036/004 | T2 DI TRNTY MPLE CRK 36/04C RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-07-06 | 2023-05-22 | 2023-10-06 | On-time | 2024-05-21 | 228 | 2023-11-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45881343 | T2 DI TRNTY MPLE CRK 36/04R RPR GYWW | ICW
LC | 126240277 | 017/333 | T2 DI HT CRK #1-WESTWOOD 17/333 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 | 2024-06-16 | Late | 2024-05-18 | -29 | 2024-05-19 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35512704 | T2 DI HT CRK #1-WESTWOOD 17/333 REFRAME | 93E
LC | 126240292 | 081/572 | T2 DI BRDGEVLE-COT 81/572L RPR ADSS | EUREKA | ETL.1110.POLE.STPS | 2023-05-27 | 2023-05-23 |  | Late | 2024-05-22 |  | 2023-08-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | ADSS - Wood | Repair | 45810543 | T2 DI BRDGEVLE-COT 81/572L RPR ADSS | ICW
LC | 126240293 | 039/314 | T2 DI BRDGVL-CTNWD 39/314L RPL ANCW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-05-27 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35525611 | T2 DI BRIDGVLL-COTTONWD 35/281L RPL ANCW | 93E
LC | 126240295 | 081/572 | T2 DI BRDGEVLE-COT 81/572 RPR CNDW | EUREKA | ETL.1110.INSL.NCER | 2023-05-27 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46171856 | T2 DI BRDGEVLE-COT 81/572 RPL DAMW | ICW
LC | 126240298 | 039/310 | T2 DI BRDGEVLE-COT 39/310L RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-27 | 2023-05-18 | 2024-06-14 | Late | 2024-05-17 | -28 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062769 | T2 DI BRDGEVLE-COT 39/310L RPR GYWW | ICW
LC | 126240299 | 039/310 | T2 DI BRDGEVLE-COT 39/310R RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-27 | 2023-05-18 | 2024-06-14 | Late | 2024-05-17 | -28 | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46062770 | T2 DI BRDGEVLE-COT 39/310R RPR GYWW | ICW
LC | 126240303 | 009/183 | T2 DI HT CRK #1-WSTW 9/183 GO95 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35518527 | T2 DI HT CRK #1-WSTW 9/183 GO95 RPL STRW | 93G
LC | 126206672 | 022/181 | T2 EI PIT #1-COTTONWOOD 022/181 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-23 | 2023-05-23 | 2024-01-29 | On-time | 2024-05-22 | 114 | 2024-05-23 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46072199 | T2 EI PIT #1-COTTONWOOD 022/181 UNBURY | ICQ
LC | 126207012 | 006/127 | T2 EI COTTONWD-RED BLUFF 6/127 RMV BUTT | TABLEMTN | ETL.6660.POLE.NWOD | 2023-05-23 | 2023-05-23 | 2024-05-07 | On-time | 2024-05-22 | 15 | 2024-05-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 46075851 | T2 EI COTTONWD-RED BLUFF 6/127 RMV BUTT | ICW
LC | 126240343 | 008/161 | T2 DI HAT CREEK#1 08/161 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512600 | T2 DI HAT CRK #1-WESTWD 008/155 RPL STRW | 70Y
LC | 126240363 | 229 | T2 DI BRDGVL-CTNWD 41/332 RPL HRDS | TABLEMTN | ETL.1110.SWIT | 2023-05-27 | 2023-05-18 | 2024-06-06 | Late | 2024-05-17 | -20 | 2024-05-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Steel | Replace | 46061182 | T2 DI BRDGVL-CTNWD 41/332 RPL HRDS | ICS
LC | 126240366 | 041/332 | T2 DI BRDGVL-CTNWD 41/332L RPR OPGW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-27 | 2023-05-18 | 2024-06-03 | Late | 2024-05-17 | -17 | 2024-05-18 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46061183 | T2 DI BRDGVL-CTNWD 41/332L RPR OPGW | ICS
LC | 126207605 | 022/184 | T2 EI PIT #1-COTTONWOOD 22/184 COMPLETED | TABLEMTN | ETL.5390.TOWR | 2023-05-23 | 2023-05-23 | 2024-01-29 | On-time | 2024-05-22 | 114 | 2024-05-23 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46072200 | T2 EI PIT #1-COTTONWOOD 022/184 UNBURY | ICQ
LC | 126208402 | 57 | T2 EI TULUCAY-NAPA #1 T3/05 RPR SWTC | LAKEVLLE | ETL.8180.SWIT | 2023-05-23 | 2023-05-23 | 2024-05-18 | On-time | 2024-05-22 | 4 | 2024-05-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 46170761 | T2 EI TULUCAY-NAPA #1 T03/05 RPR SWTCH | ICW
LC | 126240454 | 017/343 | T2 DI HT CRK #1-WESTWD 17/343 RPR STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 | 2024-06-15 | Late | 2024-05-18 | -28 | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46062864 | T2 DI HT CRK #1-WESTWD 17/343 RPR STRW | ICW
LC | 126208406 | 022/185 | T2 EI PIT #1-COTTONWOOD 22/185 COMPLETED | TABLEMTN | ETL.5390.TOWR | 2023-05-23 | 2023-05-23 | 2024-01-29 | On-time | 2024-05-22 | 114 | 2024-05-23 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46072201 | T2 EI PIT #1-COTTONWOOD 22/185 UNBURY | ICQ
LC | 126240468 | 007/138 | T2 DI CARIBOU-WW 7/138L RPR GYWW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-27 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46262781 | T2 DI CARIBOU-WW 7/138L RPR GYWW | ICW
LC | 126240470 | 004/080 | T2 DI HAT CRK #1-WSTWD 4/80 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512493 | T2 DI HAT CRK #1-WSTWD 3/76 RPL STRW | 70Y
LC | 126240478 | 037/006 | T2 DI TRINITY-MAPLE CRK 37/006 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-05-27 | 2023-05-22 | 2024-06-01 | Late | 2024-05-21 | -11 | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171896 | T2 DI TRINITY-MAPLE CRK 37/006 RPR GYWW | ICW
LC | 126240479 | 004/093 | T2 DI HAT CRK #1-WESTWOOD 4/93 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512494 | T2 DI HAT CRK #1-WSTWD 4/86 RPL STRW | 70Y
LC | 126208427 | 022/186 | T2 EI PIT #1-COTTONWOOD 22/186 COMPLETED | TABLEMTN | ETL.5390.TOWR | 2023-05-23 | 2023-05-23 | 2024-01-29 | On-time | 2024-05-22 | 114 | 2024-05-23 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46072202 | T2 EI PIT #1-COTTONWOOD 22/186 UNBURY | ICQ
LC | 126208787 | 023/188 | T2 EI PIT #1 CTTNWD 023/188 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-23 | 2023-05-23 | 2024-01-30 | On-time | 2024-05-22 | 113 | 2024-05-23 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46072203 | T2 EI PIT #1 CTTNWD 023/188 UNBURY | ICQ
LC | 126240513 | 002/020 | T2 DI COTTONWOOD #1 2/20 RPL INSS | TABLEMTN | ETL.6620.INSL.CERA | 2023-05-27 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513982 | T2 DI COTTONWOOD #1 RPL INSS 4 TWRS | 93K
LC | 126240520 | 037/006 | T2 DI TRINITY-MAPLE CRK 37/006 RPR INSW | EUREKA | ETL.8170.INSL.NCER | 2023-05-27 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46171896 | T2 DI TRINITY-MAPLE CRK 37/006 RPR GYWW | ICW
LC | 126240526 | 006/127 | T2 DI HAT CRK #1-WESTWOOD 6/127 RPR CRSW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46062835 | T2 DI HAT CRK #1-WESTWOOD 6/127 RPR CRSW | ICW
LC | 126240527 | 006/127 | T2 DI HAT CRK #1-WESTWOOD 6/127 GO95 | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35538397 | T2 DI HAT CRK #1-WESTWOOD 6/127 GO95 | 93G
LC | 126240540 | 010/201 | T2 DI HT CRK #1-WSTWD 10/201 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512603 | T2 DI HT CRK#1-WSTWD 10/201 RPL PL | 70Y
LC | 126240558 | 000/008 | T2 DI MENDOCINO-HARTLEY 000/008 RPL POLE | WILLITS | ETL.7510.POLE.WOOD | 2023-05-27 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35488482 | T2 DI MENDO-HARTLEY 00/07 RPL STRW | 70Y
LC | 126209187 | 005/023 | T2 EI MORRO BAY-SLR SS #1 5/23 RPL INSS | PISMOBCH | ETL.5300.INSL | 2023-05-23 | 2023-05-23 | 2024-05-08 | On-time | 2024-05-22 | 14 | 2024-05-23 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35526914 | T2 EI MORRO BAY-SLR SS #1 5/23 RPL INSS | 93K
LC | 126240625 | 034/008 | T2 DI TRINTY-MPLE CRK 34/08R RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-27 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170569 | T2 DI TRINTY-MPLE CRK 34/08R RPR GYWW | ICW
LC | 126240667 | 036/000A | T2 DI TRINITY-MAPLE CRK 36/0A RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-27 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170576 | T2 DI TRINITY-MAPLE CRK 36/0A RPR GYWW | ICW
LC | 126240675 | 000/006 | T2 DI HAT CRK #1-WSTWD 0/6 GO95 RPL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35529610 | T2 DI HAT CRK#1-WSTWD 00/06 GO95 | 93G
LC | 126240688 | 005/103 | T2 DI HAT CRK #1-WESTWOOD 5/103 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512495 | T2 DI HAT CRK #1-WESTWOOD 5/103 RPL POLE | 70Y
LC | 126240689 | 017/005 | T2 DI TRINITY-MAPLE CRK 17/5 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-27 | 2023-05-22 |  | Late | 2024-05-21 |  | 2023-11-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079440 | T2 DI TRINITY-MAPLE CRK 17/5 RPR GYWW | ICW
LC | 126209503 | 006/038 | T2 EI BALCH-SANGER 6/38 BNT STEEL | FRESNO | ETL.1050.TOWR | 2023-05-23 | 2023-05-23 | 2024-04-29 | On-time | 2024-05-22 | 23 | 2024-05-23 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46069696 | T2 EI BALCH-SANGER 6/38 BNT STEEL | ICQ
LC | 126240726 | 017/005 | T2 DI TRINITY-MAPLE CRK 17/5 RPR JMPW | EUREKA | ETL.8170.INSL.NCER | 2023-05-27 | 2023-05-22 |  | Late | 2024-05-21 |  | 2023-08-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46193764 | T2 DI TRINITY-MAPLE CRK 17/5 RPR JMPW | ICW
LC | 126240729 | 013/261 | T2 DI HAT CRK #1-WSTWD 13/261 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-18 | 2024-06-11 | Late | 2024-05-17 | -25 | 2024-05-18 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35512605 | T2 DI HAT CR#1-WW 13/261 RPL CRSW | 93E
LC | 126240747 | 026/013 | T2 DI MAPLE CREEK-HOOPA 026/013 RPL ANCW | EUREKA | ETL.7490.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35526563 | T2 DI MAPLE CREEK-HOOPA 026/013 RPL ANCW | 93E
LC | 126240749 | 004/088 | T2 DI HAT CRK #1-WSTWD 4/88 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512494 | T2 DI HAT CRK #1-WSTWD 4/86 RPL STRW | 70Y
LC | 126240770 | 078/559 | T2 DI BRIDGVIL-COTT 78/559L RPR GYWW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-27 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171848 | T2 DI BRIDGVIL-COTT 78/559L RPR GYWW | ICW
LC | 126209516 | 006/037 | T2 EI BALCH-SANGER 6/037 RPL INSS | FRESNO | ETL.1050.INSL.CERA | 2023-05-23 | 2023-05-23 | 2024-04-10 | On-time | 2024-05-22 | 42 | 2024-05-23 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510274 | T2 DI BALCH-SANGER 04/27 RPL INSS | 93K
LC | 126209847 | 007/009 | T2 EI TULUCAY-NAPA #1 07/09 RPR GYWW | LAKEVLLE | ETL.8180.POLE.WOOD | 2023-05-23 | 2023-05-23 | 2024-01-15 | On-time | 2024-05-22 | 128 | 2024-05-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096609 | T2 EI TULUCAY-NAPA #1 07/09 RPR GYWW | ICW
LC | 126240802 | 000/004 | T2 DI HAT CR#1-WW 0/4 RPL HRDD | TABLEMTN | ETL.7030.POLE.NWOD | 2023-05-27 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46062714 | T2 DI HAT CR#1-WW 0/4 RPL HRDD | ICW
LC | 126240806 | 015/306 | T2 DI HT CRK #1-WESTWD 15/306 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-18 | 2024-06-10 | Late | 2024-05-17 | -24 | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512700 | T2 DI HAT CREEK#1 WESTWD 15/290 RPL POLE | 70Y
LC | 126240816 | 005/110 | T2 DI HAT CRK #1-WSTWD 5/110 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512495 | T2 DI HAT CRK #1-WESTWOOD 5/103 RPL POLE | 70Y
LC | 126211052 | 005/034 | T2 EI BALCH-SANGER 005/034 INS ATCG | FRESNO | ETL.1050.TOWR | 2023-05-23 | 2023-05-23 | 2024-01-26 | On-time | 2024-05-22 | 117 | 2024-05-23 | 988 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Anti-Climbing Guard | Structure-Tower | Install | 31682717 | T2 EI BALCH-SANGER 005/034 INS ATCG | 93A
LC | 126240923 | 97 | T2 DI CARIBOU-WSTWD A15/305 RPR SWTC | TABLEMTN | ETL.6300.SWIT | 2023-05-27 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 623 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Out of Adjustment | Switch | Repair | 45810531 | T2 DI CARIBOU-WSTWD A15/305 RPR SWTC | ICE
LC | 126211053 | 005/034 | T2 EI BALCH-SANGER 005/034 RPL INSS | FRESNO | ETL.1050.INSL.CERA | 2023-05-23 | 2023-05-23 | 2024-04-10 | On-time | 2024-05-22 | 42 | 2024-05-23 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35542729 | T2 EI BALCH-SANGER 005/034 RPL INSS | 93K
LC | 126211054 | 005/034 | T2 EI BALCH-SANGER 005/034 UNBURY | FRESNO | ETL.1050.TOWR | 2023-05-23 | 2023-05-23 | 2024-01-26 | On-time | 2024-05-22 | 117 | 2024-05-23 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46069694 | T2 EI BALCH-SANGER 005/034 UNBURY | ICQ
LC | 126240957 | 013/262 | T2 DI HAT CREEK#1 WSTWD 13/262 RPR CRSW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 | 2024-06-15 | Late | 2024-05-18 | -28 | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46062850 | T2 DI HAT CREEK#1 WSTWD 13/262 RPR CRSW | ICW
LC | 126240985 | 001/032 | T2 DI HAT CREEK #1-WSTWOOD 1/32 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512485 | T2 DI HAT CRK #1-WW 0/17 RPL STRW | 70Y
LC | 126240989 | 003/063 | T2 DI HAT CRK #1-WSTWD 3/63 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512487 | T2 DI HAT CRK #1-WSTWD 3/63 RPL POLE | 70Y
LC | 126241007 | 006/132 | T2 DI HT CRK #1-WSTWD 6/132 RPR CRSW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46062836 | T2 DI HT CRK #1-WSTWD 6/132 RPR CROSSARM | ICW
LC | 126211699 | 048/001B | T2 EI HUMBOLDT-TRINITY 048/001B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-23 | 2023-05-23 | 2023-08-17 | On-time | 2024-05-22 | 279 | 2023-08-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805727 | T2 EI HUMBOLDT-TRINITY 048/001B RPR GYWW | ICW
LC | 126241048 | 017/339 | T2 DI HAT CREEK #1 WESTWD 17/339 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-27 | 2023-05-19 | 2024-06-16 | Late | 2024-05-18 | -29 | 2024-05-19 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 31650750 | T2 DI HAT CREEK #1 WESTWD 17/339 REFRAME | 93E
LC | 126242388 | 101/000 | T2 HUMBOLDT-TRINITY 101/000 RPL INSW | EUREKA | ETL.1820.INSL.CERA | 2023-05-29 | 2023-05-29 |  | Late | 2024-05-28 |  | 2024-05-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46096663 | T2 HUMBOLDT-TRINITY 101/000 RPL INSW | ICW
LC | 126243283 | 086/004A | T2 HUMBOLDT-TRINITY 86/4A RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46096592 | T2 HUMBOLDT-TRINITY 86/4A RPR INSW | ICW
LC | 126243420 | 004/081 | T2 DI HAT CREEK#1 WSTWD 4/81 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512493 | T2 DI HAT CRK #1-WSTWD 3/76 RPL STRW | 70Y
LC | 126243511 | 002/052 | T2 DI HAT CREEK #1-WSTWOOD 2/52 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512485 | T2 DI HAT CRK #1-WW 0/17 RPL STRW | 70Y
LC | 126211727 | 048/001C | T2 EI HUMBOLDT-TRINITY 048/001C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-23 | 2023-05-23 | 2023-08-17 | On-time | 2024-05-22 | 279 | 2023-08-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805729 | T2 EI HUMBOLDT-TRINITY 048/001C RPR GYWW | ICW
LC | 126243808 | 002/058 | T2 DI HAT CREEK#1 WSTWD 2/58 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512486 | T2 DI HAT CREEK#1 WSTWD 2/58 RPL POLE | 70Y
LC | 126243870 | 055/276 | T2 DI MALN-ROUND MTN #2 55/276 RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2023-05-30 | 2023-05-15 |  | Late | 2024-05-14 |  | 2024-05-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46072166 | T2 DI MALN-ROUND MTN #2 55/276 RPR GYWS | ICS
LC | 126211728 | 048/001A | T2 EI HUMBOLDT-TRINITY 048/001A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-23 | 2023-05-23 | 2023-08-17 | On-time | 2024-05-22 | 279 | 2023-08-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45805726 | T2 EI HUMBOLDT-TRINITY 048/001A RPR GYWW | ICW
LC | 126212314 | 065/002 | T2 EI HUMBOLDT-TRINITY 65/02L RPL HRDW | EUREKA | ETL.1820.POLE.WDPS | 2023-05-23 | 2023-05-23 | 2024-04-11 | On-time | 2024-05-22 | 41 | 2024-05-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46096533 | T2 EI HUMBOLDT-TRINITY 65/02L RPL HRDW | ICW
LC | 126212340 | 065/002 | T2 EI HUMBOLDT-TRINITY 65/02L RPR ANCW | EUREKA | ETL.1820.POLE.WDPS | 2023-05-23 | 2023-05-23 | 2024-04-09 | On-time | 2024-05-22 | 43 | 2024-05-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46096533 | T2 EI HUMBOLDT-TRINITY 65/02L RPL HRDW | ICW
LC | 126244589 | 016/315 | T2 DI HAT CREEK#1 WSTWD 16/315 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-19 | 2024-06-15 | Late | 2024-05-18 | -28 | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512703 | T2 DI HAT CREEK#1 WSTWD 16/311 RPL STRW | 70Y
LC | 126213412 | 002/035 | T2 EI COLEMAN-RED BLUFF 2/035 RPL INSW | TABLEMTN | ETL.6440.INSL.CERA | 2023-05-23 | 2023-05-23 | 2024-03-26 | On-time | 2024-05-22 | 57 | 2024-05-23 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35500378 | T2 EI COLEMAN-RED BLUFF 2/035 RPL INSW | 93I
LC | 126244938 | 003/078 | T2 DI HAT CREEK#1 WSTWD 03/078 RPL HRDD | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46062828 | T2 DI HAT CREEK#1 WSTWD 03/078 RPL HRDD | ICW
LC | 126245786 | 015/307 | T2 EI HAT CREEK #1-WSTWD 15/307 RPL INSW | TABLEMTN | ETL.7030.INSL.NCER | 2023-05-30 | 2023-05-30 | 2024-06-10 | Late | 2024-05-29 | -12 | 2024-05-30 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35514539 | T2 EI HAT CREEK #1-WSTWD 15/307 RPL INSW | 93I
LC | 126232523 | 083/586 | T2 DI BRDGVIL CTTNWD 83/586 RPR ADSS | EUREKA | ETL.1110.POLE.WDPS | 2023-05-26 | 2023-05-23 | 2023-10-30 | On-time | 2024-05-22 | 205 | 2023-11-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45810540 | T2NT DI BRDGVIL CTTNWD 83/586 RPR ADSS | ICW
LC | 126247034 | 022/171 | T2 DI DRUM RIO OSO#1 2/171 RPL HRDT | SACTO | ETL.1420.INSL.NCER | 2023-05-30 | 2023-05-25 |  | Late | 2024-05-24 |  | 2023-11-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45824919 | T2 DI DRUM RIO OSO#1 2/171 RPL TIP PLT | ICQ
LC | 126236104 | 035/007 | T2 DI BRDGVIL GRBRVIL 35/007 RPR GYWW | EUREKA | ETL.6220.POLE.NWOD | 2023-05-26 | 2023-05-23 | 2024-02-01 | On-time | 2024-05-22 | 111 | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46087930 | T2 DI BRDGVIL GRBRVIL 35/007 RPR GYWW | ICW
LC | 126238805 | 000/001 | T2 DI WSHN CPPRMINE 00/001 RPL HRDT | FRESNO | ETL.9330.TOWR | 2023-05-26 | 2023-05-23 | 2024-04-23 | On-time | 2024-05-22 | 29 | 2024-05-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46070920 | T2 DI WSHN CPPRMINE 00/001 RPL HRDT | ICQ
LC | 126247270 | 016/313 | T2 EI HAT CREEK #1-WSTWD 16/313 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-30 | 2024-06-17 | Late | 2024-05-29 | -19 | 2024-05-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514863 | T2 EI HAT CREEK #1-WSTWD 16/313 RPL STRW | 70Y
LC | 126238806 | 000/001 | T2 DI WSHN CPPRMINE 00/001 COMPLETE | FRESNO | ETL.9330.TOWR | 2023-05-26 | 2023-05-23 | 2024-04-23 | On-time | 2024-05-22 | 29 | 2024-05-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46072109 | T2 DI WSHN CPPRMINE 00/001 RPR GYWT | ICQ
LC | 126247434 | 014/121B | T2 EI PT #6 JCT-RND MTN 14/121B RPR GYWW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-05-30 | 2023-05-30 | 2024-06-21 | Late | 2024-05-29 | -23 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076166 | T2 EI PT #6 JCT-RND MTN 14/121B RPR GYWW | ICW
LC | 126238809 | 000/001 | T2 DI WSHN CPPRMINE 00/001 RPR ANCS | FRESNO | ETL.9330.TOWR | 2023-05-26 | 2023-05-23 | 2023-08-09 | On-time | 2024-05-22 | 287 | 2023-11-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45809568 | T2 DI WSHN CPPRMINE 00/001 RPR ANCS | ICS
LC | 126247914 | 009/178 | T2 DI HAT CREEK#1 WSTWD 09/178 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512600 | T2 DI HAT CRK #1-WESTWD 008/155 RPL STRW | 70Y
LC | 126248207 | 016/321 | T2 EI HT CRK #1-WESTWD 16/321 COMPLETED | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-30 | 2024-06-15 | Late | 2024-05-29 | -17 | 2024-05-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514863 | T2 EI HAT CREEK #1-WSTWD 16/313 RPL STRW | 70Y
LC | 126248511 | 007/151 | T2 DI HAT CREEK#1 WSTWD 007/151 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512496 | T2 DI HAT CREEK#1 07/147 RPL PL | 70Y
LC | 126249048 | :014/074 | T2 CRAZY HORSE CNYN-SLNS :014/74 RMV VEG | MOSSLNDG | ETL.2900.TOWR | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation-Tower | Cage Clearing
LC | 126249145 | 017/330 | T2 EI HT CRK #1-WSTWD 17/330 RPL HRDW | TABLEMTN | ETL.7030.INSL | 2023-05-30 | 2023-05-30 | 2024-06-16 | Late | 2024-05-29 | -18 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46076244 | T2 EI HT CRK #1-WSTWD 17/330 RPL HRDW | ICW
LC | 126239876 | 007/137 | T2 DI CRBU-WSTWD 7/137L RPL ANCW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-05-27 | 2023-05-23 | 2023-08-08 | On-time | 2024-05-22 | 288 | 2023-11-23 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31650862 | T2 DI CRBU-WSTWD 7/137L RPL ANCW | 93E
LC | 126240036 | 029/250 | T2 DI BRIDGEVIL-COTONWOD 29/250 RPR ADSS | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-27 | 2023-05-23 | 2023-08-25 | On-time | 2024-05-22 | 271 | 2023-08-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45810538 | T2 DI BRIDGEVIL-COTONWOD 29/250 RPR ADSS | ICW
LC | 126250135 | 002/002 | T2 EI BRICE JCT-MARIPOSA 2/2 RPL POLE | FRESNO | ETL.8651.POLE.WOOD | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525548 | T2NT EI BRICE JCT-MARIPOSA 2/2 RPL POLE | 70Y
LC | 126250372 | 053/379 | T2 EI CRBU-TBL MTN 53/379 RPL INSS | TABLEMTN | ETL.4440.INSL | 2023-05-30 | 2023-05-30 | 2024-06-08 | Late | 2024-05-29 | -10 | 2024-05-30 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35508877 | T2 EI CARIBOU-TABLE MTN RPL INSS 12 STRT | 93K
LC | 126250483 | 028/003 | T2 EI TRINITY-MAPLE CREEK 028/003 COTTER | EUREKA | ETL.8170.INSL.CERA | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46172082 | T2 EI TRINITY-MAPLE CREEK 028/003 COTTER | ICW
LC | 126240142 | 002/014 | T2 DI BALCH-SANGER 02/014 RPR FOND | FRESNO | ETL.1050.TOWR | 2023-05-27 | 2023-05-23 | 2024-01-31 | On-time | 2024-05-22 | 112 | 2024-05-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46069691 | T2 DI BALCH-SANGER 02/014 RPR FOND | ICQ
LC | 126250512 | 028/001 | T2 EI TRINITY-MAPLE CREEK 28/1 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-05-30 | 2023-05-30 | 2024-06-13 | Late | 2024-05-29 | -15 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46246396 | T2 EI TRINITY-MAPLE CREEK 28/1 RPR GYWW | ICW
LC | 126250582 | 87 | T2 EI TRINITY-MAPLE CREEK 21/4A RPL SWTC | EUREKA | ETL.8170.SWIT | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 427T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Switch-Wood | Replace | 35503362 | T2 EI TRINITY-MAPLE CREEK 21/4A RPL SWTC | 93H
LC | 126250584 | 027/006 | T2 EI TRNTY-MPL CRK 027/006L RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504077 | T2 DI TRNTY-MPL CRK 27/6R RPL POLE | 70Y
LC | 126250586 | 027/006 | T2 EI TRNTY-MPL CRK 027/006C RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504077 | T2 DI TRNTY-MPL CRK 27/6R RPL POLE | 70Y
LC | 126240252 | 082/579 | T2NT DI BRDGEVLE-COT 82/579L RPR ADSS | EUREKA | ETL.1110.POLE.STPS | 2023-05-27 | 2023-05-23 | 2023-10-30 | On-time | 2024-05-22 | 205 | 2023-08-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45847742 | T2NT DI BRDGEVLE-COT 82/579L RPR ADSS | ICW
LC | 126250720 | 079/560 | T2 DI BRDGVIL CTTNWD 79/560L RPR OPGW | EUREKA | ETL.1110.POLE.STPS | 2023-05-30 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46171850 | T2 EI BRDGVL-CTTNWD 079/560R RPR GYWW | ICW
LC | 126240266 | 004/030 | T2 DI HAAS-MCCALL 4/30 COMPLETED | FRESNO | ETL.4850.POLE.NWOD | 2023-05-27 | 2023-05-23 | 2024-05-07 | On-time | 2024-05-22 | 15 | 2024-05-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46072110 | T2 DI HAAS-MCCALL 04/030 RPR SHLS | ICS
LC | 126240323 | 009/134C | T2 DI DLTA-MTN GATE JCT 9/134C RPR GYWW | TABLEMTN | ETL.6750.POLE.NWOD | 2023-05-27 | 2023-05-23 | 2024-05-16 | On-time | 2024-05-22 | 6 | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073819 | T2 DI DLTA-MTN GATE JCT 9/134C RPR GYWW | ICW
LC | 126240495 | 000/012 | T2 DI WSHN CPPRMINE 00/012 RPR INSS | FRESNO | ETL.9330.INSL.CERA | 2023-05-27 | 2023-05-23 | 2024-04-23 | On-time | 2024-05-22 | 29 | 2024-05-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46072111 | T2 DI WSHN CPPRMINE 00/012 RPR INSS | ICS
LC | 126240696 | 001/010 | T2 DI BALCH SANGER 01/010 UNBURY | FRESNO | ETL.1050.TOWR | 2023-05-27 | 2023-05-23 | 2024-02-09 | On-time | 2024-05-22 | 103 | 2024-05-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46069688 | T2 DI BALCH SANGER 01/010 UNBURY | ICQ
LC | 126251270 | 024/006 | T2 RIO DELL JCT-BRIDGEVILLE 24/6 GO95 | EUREKA | ETL.7850.POLE.WOOD | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31651478 | T2 RIO DELL JCT-BRIDGEVILLE 24/6 GO95 | 93G
LC | 126251295 | 029/006 | T2 RIO DELL JCT-BRIDGEVILLE 29/6 GO95 | EUREKA | ETL.7850.POLE.WOOD | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31651701 | T2 RIO DELL JCT-BRIDGEVILLE 28/6 GO95 | 93G
LC | 126251309 | 035/006 | T2 DI TRINITY-MAPLE CREEK 35/6C RPL ANCW | EUREKA | ETL.8170.POLE.WDPS | 2023-05-30 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35506410 | T2 DI TRINITY-MAPLE CREEK 35/6C RPL ANCW | 93E
LC | 126251316 | 028/006 | T2 RIO DELL JCT-BRIDGEVILLE 28/6 GO95 | EUREKA | ETL.7850.POLE.WOOD | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31651701 | T2 RIO DELL JCT-BRIDGEVILLE 28/6 GO95 | 93G
LC | 126240798 | 000/013 | T2 DI WSHN-CPPRMN 000/013 COMPLETE | FRESNO | ETL.9330.INSL.CERA | 2023-05-27 | 2023-05-23 | 2024-04-23 | On-time | 2024-05-22 | 29 | 2024-05-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46072112 | T2 DI WSHN-CPPRMN 000/013 RPR INSS | ICS
LC | 126251218 | 002/020 | T2 DI BALCH-SANGER 002/020 RPL INSS | FRESNO | ETL.1050.INSL.CERA | 2023-05-30 | 2023-05-23 | 2024-04-08 | On-time | 2024-05-22 | 44 | 2024-05-23 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510274 | T2 DI BALCH-SANGER 04/27 RPL INSS | 93K
LC | 126251910 | 002/017 | T2 DI BUTTE VALLEY-CARIBOU 2/17 RPR STRT | TABLEMTN | ETL.1180.TOWR | 2023-05-30 | 2023-05-23 | 2024-05-13 | On-time | 2024-05-22 | 9 | 2024-05-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072198 | T2 DI BUTTE VALLEY-CARIBOU 2/17 RPR STRT | ICQ
LC | 126252011 | 004/027 | T2 DI BALCH-SANGER 04/27 RPL INSS | FRESNO | ETL.1050.INSL.CERA | 2023-05-30 | 2023-05-23 | 2024-04-08 | On-time | 2024-05-22 | 44 | 2024-05-23 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510274 | T2 DI BALCH-SANGER 04/27 RPL INSS | 93K
LC | 126252082 | 010/127 | T2 DI CLGT-SMRTVL #1 10/127 RPR GYWW | SACTO | ETL.6510.POLE.STPS | 2023-05-30 | 2023-05-23 | 2024-03-06 | On-time | 2024-05-22 | 77 | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079213 | T2 DI CLGT-SMRTVL #1 10/127 RPR GYWW | ICW
LC | 126251421 | 080/000 | T2 EI HMBLDT-TRNTY 80/0C RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-05-30 | 2023-05-30 | 2024-05-30 | Late | 2024-05-29 | -1 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171109 | T2 EI HMBLDT-TRNTY 80/0C RPR GYWW | ICW
LC | 126251422 | 080/000 | T2 EI HMBLDT-TRNTY 80/0L RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-05-30 | 2023-05-30 | 2024-05-30 | Late | 2024-05-29 | -1 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171109 | T2 EI HMBLDT-TRNTY 80/0C RPR GYWW | ICW
LC | 126251423 | 080/000 | T2 EI HMBLDT-TRNTY 80/0R RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-05-30 | 2023-05-30 | 2024-05-30 | Late | 2024-05-29 | -1 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171109 | T2 EI HMBLDT-TRNTY 80/0C RPR GYWW | ICW
LC | 126251425 | 033/006 | T2 RIO DLL JCT-BRDGVLLE 33/6 GO95 CLEAR | EUREKA | ETL.7850.POLE.WOOD | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2023-08-30 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31651704 | T2 RIO DELL JCT-BRIDGEVILLE 33/6 GO95 | 93G
LC | 126251427 | 033/011 | T2 RIO DLL JCT-BRDGVLLE 33/11 GO95 CLEAR | EUREKA | ETL.7850.POLE.WOOD | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31615349 | T2 EI RIO DLL JCT-BRDGVLLE 33/9 RPL STRW | 70Y
LC | 126251459 | 035/006 | T2 DI TRINITY-MPL CREEK 35/6R ANTI SPLIT | EUREKA | ETL.8170.POLE.WDPS | 2023-05-30 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46170575 | T2 DI TRINITY-MPL CREEK 35/6R ANTI SPLIT | ICW
LC | 126251531 | 034/002 | T2 RIO DELL JCT-BRIDGEVILLE 34/2 GO95 | EUREKA | ETL.7850.POLE.WOOD | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31615349 | T2 EI RIO DLL JCT-BRDGVLLE 33/9 RPL STRW | 70Y
LC | 126252252 | 009/089 | T2 DI PIT #5-RND MTN #1 9/89L BACKFILL | TABLEMTN | ETL.5420.POLE.STPS | 2023-05-30 | 2023-05-23 | 2024-01-18 | On-time | 2024-05-22 | 125 | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 46076165 | T2 DI PIT #5-RND MTN #1 9/89L BACKFILL | ICW
LC | 126251683 | 038/009 | T2 DI TRINITY-MAPLE CRK-38/09 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-30 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506722 | T2 DI TRINITY-MAPLE CRK-38/09 RPL POLE | 70Y
LC | 126251686 | 026/503 | T2 DI HAT CRK#1-WSTWD 26/503 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-24 | 2024-06-24 | Late | 2024-05-23 | -32 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514547 | T2 DI HAT CRK#1-WSTWD 26/503 RPL STRW | 70Y
LC | 126251688 | 026/503 | T2 DI HAT CRK#1-WSTWD 26/503 CANCEL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076217 | T2 DI HAT CRK#1-WSTWD 26/503 RPR GYWW | ICW
LC | 126251702 | 017/335 | T2 DI HT CRK#1 WSTWD 17/335 GO95 USAGE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35538372 | T2 DI HAT CREEK#1 WSTWD 17/335 GO95 | 93G
LC | 126251709 | 036/003 | T2 DI TRNTY-MPL CRK 36/3C RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-30 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170578 | T2 DI TRNTY-MPL CRK 36/3C RPR GYWW | ICW
LC | 126251823 | 009/103 | T2 DI DRUM-SUMMT #1 9/103L RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2023-05-30 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46101314 | T2 DI DRUM-SUMMT #1 9/103L RPR STRW | ICW
LC | 126251825 | 009/103 | T2 DI DRUM-SUMMT#1 9/103R RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2023-05-30 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46101315 | T2 DI DRUM-SUMMT#1 9/103R RPR STRW | ICW
LC | 126252273 | 009/089 | T2 DI PIT #5-RND MTN #1 9/89C RPR GYWW | TABLEMTN | ETL.5420.POLE.STPS | 2023-05-30 | 2023-05-23 | 2024-01-18 | On-time | 2024-05-22 | 125 | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076162 | T2 DI PIT #5-RND MTN #1 9/89C RPR GYWW | ICW
LC | 126252274 | 009/089 | T2 DI PIT #5-RND MTN #1 9/89R RPR GYWW | TABLEMTN | ETL.5420.POLE.STPS | 2023-05-30 | 2023-05-23 | 2024-01-17 | On-time | 2024-05-22 | 126 | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076163 | T2 DI PIT #5-RND MTN #1 9/89R RPR GYWW | ICW
LC | 126252276 | 009/089 | T2 DI PIT #5-RND MTN #1 9/89L RPR GYWW | TABLEMTN | ETL.5420.POLE.STPS | 2023-05-30 | 2023-05-23 | 2024-01-18 | On-time | 2024-05-22 | 125 | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076164 | T2 DI PIT #5-RND MTN #1 9/89L RPR GYWW | ICW
LC | 126252008 | 014/276 | T2 DI HAT CRK #1-WSTWD 14/276 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-19 | 2024-06-13 | Late | 2024-05-18 | -26 | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35512607 | T2 DI HAT CRK #1-WSTWD 13/264 RPL STRW | 70Y
LC | 126252278 | 007/029 | T2 DI MONTA VST-JEFF #1 7/29 RPL INSS | METCALF | ETL.5220.INSL | 2023-05-30 | 2023-05-23 | 2023-10-17 | On-time | 2024-05-22 | 218 | 2024-05-23 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31656805 | T2 DI MONTA VST-JEFF #1 7/29 RPL INSS | 93K
LC | 126252049 | 000/017 | T2 DI HAT CRK #1-WW 0/17 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512485 | T2 DI HAT CRK #1-WW 0/17 RPL STRW | 70Y
LC | 126252076 | 003/079 | T2 DI HAT CRK#1-WSTWD 3/79 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514556 | T2 EI HAT CREEK #1-WESTWD 2/59 RPL STRW | 70Y
LC | 126252080 | 008/018 | T2 DI LWR LK-HMSTK 8/18 CANCEL | WILLITS | ETL.1481.INSL.NCER | 2023-05-30 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46219448 | T2 DI LWR LK-HMSTK 8/18 RPR INSW | ICW
LC | 126252284 | 007/029 | T2 DI MNTA VSTA-JFF #2 007/029 RPL INSS | METCALF | ETL.5230.INSL | 2023-05-30 | 2023-05-23 | 2023-06-14 | On-time | 2024-05-22 | 343 | 2024-05-23 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31651363 | T2 DI MNTA VSTA-JFF #2 007/029 RPL INSS | 93K
LC | 126254669 | 003/029 | T2 DI HAAS-MCCALL 3/29 COMPLETED | FRESNO | ETL.4850.TOWR | 2023-05-31 | 2023-05-23 | 2024-05-07 | On-time | 2024-05-22 | 15 | 2024-05-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46072140 | T2 DI HAAS-MCCALL 03/029 RPR SHLS | ICS
LC | 126259879 | 028/241 | T2 DI BRDGVIL CTTNWD 28/241 RPR ADSS | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-01 | 2023-05-23 | 2024-01-19 | On-time | 2024-05-22 | 124 | 2024-05-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46073755 | T2 DI BRDGVIL CTTNWD 28/241 RPR ADSS | ICS
LC | 126252153 | 018/352 | T2 DI HAT CREK #1-WESTWOD 18/352 GO95 | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-19 | 2024-06-15 | Late | 2024-05-18 | -28 | 2024-05-19 | 401T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35512705 | T2 DI HAT CREK #1-WESTWOD 18/352 GO95 | 93G
LC | 126252163 | 081/574 | T2 DI BRDGVL-CTNWD-81/574R RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-30 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505109 | T2 DI BRDGVIL-CTTNWOOD 82/577R RPL STRW | 70Y
LC | 126252164 | 081/574 | T2 DI BRDGVL-CTNWD-81/574L RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-05-30 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505109 | T2 DI BRDGVIL-CTTNWOOD 82/577R RPL STRW | 70Y
LC | 126252173 | 036/007 | T2 DI TRNTY-MPL CRK 36/7 RPR STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-30 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46170742 | T2 DI TRNTY-MPL CRK 36/7 RPR STRW | ICW
LC | 126252180 | 004/086 | T2 DI HAT CRK #1-WSTWD 4/86 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512494 | T2 DI HAT CRK #1-WSTWD 4/86 RPL STRW | 70Y
LC | 126260517 | 029/246 | T2 DI BRDGVIL CTTNWD 29/246L RPL HDWW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-06-01 | 2023-05-23 | 2024-01-19 | On-time | 2024-05-22 | 124 | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 46073757 | T2 DI BRDGVIL CTTNWD 29/246L RPL HDWW | ICW
LC | 126262462 | 003/023 | T2 DI BALCH-SANGER 3/23 RPR STRT | FRESNO | ETL.1050.TOWR | 2023-06-01 | 2023-05-23 | 2024-01-31 | On-time | 2024-05-22 | 112 | 2024-05-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46069692 | T2 DI BALCH-SANGER 3/23 RPR STRT | ICQ
LC | 126267512 | 005/034 | T2 DI HAAS MCCALL 5/34 COMPLETE | FRESNO | ETL.4850.INSL | 2023-06-01 | 2023-05-23 | 2024-05-08 | On-time | 2024-05-22 | 14 | 2024-05-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46072143 | T2 DI HAAS MCCALL 5/34 RPR INSS | ICS
LC | 126252272 | 001/010 | T2 DI PIT#7 TAP 1/10L RPR GYWW | TABLEMTN | ETL.5442.POLE.STPS | 2023-05-30 | 2023-05-23 |  | Late | 2024-05-22 |  | 2023-11-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076161 | T2 DI PIT#7 TAP 1/10L RPR GYWW | ICW
LC | 126267762 | 004/028 | T2 DI BALCH SANGER 04/028 RPL INSS | FRESNO | ETL.1050.INSL.CERA | 2023-06-01 | 2023-05-23 | 2024-04-09 | On-time | 2024-05-22 | 43 | 2024-05-23 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35524289 | T2 DI BALCH SANGER 04/028 RPL INSS | 93K
LC | 126268112 | 006/039 | T2 DI KINGS RIVER-SANGER 6/39 COMPLETE | FRESNO | ETL.2030.INSL.CERA | 2023-06-01 | 2023-05-23 | 2024-04-30 | On-time | 2024-05-22 | 22 | 2024-05-23 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35515173 | T2 DI KINGS RIVER-SANGER 6/39 RPL INSS* | 93K
LC | 126268115 | 006/039 | T2 DI BALCH-SANGER 6/39 RPL HRDT | FRESNO | ETL.1050.POLE.NWOD | 2023-06-01 | 2023-05-23 | 2024-01-26 | On-time | 2024-05-22 | 117 | 2024-05-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46069697 | T2 DI BALCH-SANGER 6/39 RPL HRDT | ICQ
LC | 126268119 | 000/011 | T2 DI WISHON-CPPRMN 0/11 RPL HRDT | FRESNO | ETL.9330.TOWR | 2023-06-01 | 2023-05-23 | 2024-04-22 | On-time | 2024-05-22 | 30 | 2024-05-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46070921 | T2 DI WISHON-CPPRMN 0/11 RPL HRDT | ICQ
LC | 126252279 | 008/155 | T2 DI HAT CRK #1-WESTWD 008/155 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-30 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512600 | T2 DI HAT CRK #1-WESTWD 008/155 RPL STRW | 70Y
LC | 126268557 | 010/127 | T2 DI CLGTE-SMRTVIL #1 10/127C RPR GYWW | SACTO | ETL.6510.POLE.STPS | 2023-06-01 | 2023-05-23 | 2024-03-06 | On-time | 2024-05-22 | 77 | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079214 | T2 DI CLGTE-SMRTVIL #1 10/127C RPR GYWW | ICW
LC | 126268566 | 010/127 | T2 DI CLGTE-SMRTVIL #1 10/127R RPR GYWW | SACTO | ETL.6510.POLE.STPS | 2023-06-01 | 2023-05-23 | 2024-03-06 | On-time | 2024-05-22 | 77 | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079215 | T2 DI CLGTE-SMRTVIL #1 10/127R RPR GYWW | ICW
LC | 128286633 | 005/034 | T2 EI KNGS RVR-SNGR-RDLY 5/34 RPL INSS | FRESNO | ETL.2030.INSL.CERA | 2024-03-14 | 2023-05-23 | 2024-04-29 | On-time | 2024-05-22 | 23 | 2024-05-23 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35538202 | T2 EI KNGS RVR-SNGR-RDLY 5/34 RPL INSS | 93K
LC | 126215227 | 023/156 | T2 EI POE-RIO OSO 23/156 RPL INSS | TABLEMTN | ETL.5540.INSL.CERA | 2023-05-24 | 2023-05-24 | 2024-01-29 | On-time | 2024-05-23 | 115 | 2024-05-24 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672704 | T2 EI POE-RIO OSO 5TWR RPL INSS | 93K
LC | 126216261 | T002/016 | T2 EI TULUCAY-NAPA #1 T02/16 RPR GYWW | LAKEVLLE | ETL.8180.POLE.WOOD | 2023-05-24 | 2023-05-24 | 2024-01-18 | On-time | 2024-05-23 | 126 | 2024-05-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096610 | T2 EI TULUCAY-NAPA #1 T02/16 RPR GYWW | ICW
LC | 126252361 | 015/002A | T2 LAYTONVILLE-WILLITS 15/2A GO95 | WILLITS | ETL.8360.POLE.WOOD | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31651477 | T2 LAYTONVILLE-WILLITS 15/2A GO95 | 93G
LC | 126252363 | 015/002B | T2 LAYTONVILLE-WILLITS 15/2B GO95 | WILLITS | ETL.8360.POLE.WOOD | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31651477 | T2 LAYTONVILLE-WILLITS 15/2A GO95 | 93G
LC | 126252364 | 015/002C | T2 LAYTONVILLE-WILLITS 15/2C GO95 | WILLITS | ETL.8360.POLE.WOOD | 2023-05-30 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31651477 | T2 LAYTONVILLE-WILLITS 15/2A GO95 | 93G
LC | 126252591 | :002/009 | T2 CARIBOU #2 :2/9 RPL HRDW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46073758 | T2 CARIBOU #2 :2/9 RPL HRDW | ICW
LC | 126252700 | 036/000B | T2 DI TRNTY MPL CRK 36/000B RPR INSW | EUREKA | ETL.8170.INSL.CERA | 2023-05-31 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46170576 | T2 DI TRINITY-MAPLE CRK 36/0A RPR GYWW | ICW
LC | 126252791 | 084/591 | T2 DI BRDGVIL-CTTNWD 84/591 RPR ADSS | EUREKA | ETL.1110.POLE.WDPS | 2023-05-31 | 2023-05-22 |  | Late | 2024-05-21 |  | 2023-08-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | ADSS - Wood | Repair | 46172022 | T2 DI BRDGVIL-CTTNWD 84/591 RPR ADSS | ICW
LC | 126252873 | 008/007 | T2 DI TRNTY MPL CRK 08/7 RPR CNDW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-31 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46070775 | T2 DI TRNTY MPL CRK 08/7 RPR CNDW | ICW
LC | 126216452 | 016/132 | T2 EI PIT #1-COTTONWOOD 016/132 COMPLETE | TABLEMTN | ETL.5390.TOWR | 2023-05-24 | 2023-05-24 | 2024-01-25 | On-time | 2024-05-23 | 119 | 2024-05-24 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46072204 | T2 EI PIT #1-COTTONWOOD 016/132 UNBURY | ICQ
LC | 126253197 | A000/002 | T2 DI TRINITY-MAPLE CREEK A0/2 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-05-31 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46070810 | T2 DI TRINITY-MAPLE CREEK A0/2 RPR GYWW | ICW
LC | 126253498 | 001/011 | T2 EI MNDCN-WLLTS-FT BRG 01/011 RMV VEG | WILLITS | ETL.7550.POLE.WOOD | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126217029 | 001/015 | T2 EI TRINITY-MAPLE CREEK 1/15 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-05-24 | 2023-05-24 | 2024-05-11 | On-time | 2024-05-23 | 12 | 2024-05-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521149 | T2 EI TRINITY-MAPLE CREEK 1/15 RPL POLE | 70Y
LC | 126253559 | 018/006 | T2 FORT BRAGG-ELK 18/6 CNCL | WILLITS | ETL.2060.POLE.WOOD | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35487325 | T2 EI FORT BRAGG-ELK 18/04 RPL STRW | 70Y
LC | 126253608 | 012/004 | T2 FORT BRAGG-ELK 12/04 GO95 CLEAR | WILLITS | ETL.2060.POLE.WOOD | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656729 | T2 FORT BRAGG-ELK 8/14 GO95 CLEAR | 93G
LC | 126254169 | 001/008 | T2 EI MNDCNO-WLTS-FT BRG 1/8 CANCEL | WILLITS | ETL.7550.POLE.WOOD | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46214149 | T2 EI MNDCNO-WLTS-FT BRG 01/08 RPR HRDW | ICW
LC | 126254217 | 014/285 | T2 DI HAT CREEK#1 WSTWD 14/285 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-31 | 2023-05-18 | 2024-06-12 | Late | 2024-05-17 | -26 | 2024-05-18 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35512618 | T2 DI HAT CREEK#1 WSTWD 14/285 REFRAME | 93E
LC | 126254345 | 037/002 | T2 DI TRINITY-MC 37/2 RPR JMPW | EUREKA | ETL.8170.INSL.NCER | 2023-05-31 | 2023-05-22 |  | Late | 2024-05-21 |  | 2023-08-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46193768 | T2 DI TRINITY-MC 37/2 RPR JMPW | ICW
LC | 126217848 | 012/242 | T2 EI COTTONWOOD-RED BLUFF 12/242 COTTER | TABLEMTN | ETL.6660.INSL.NCER | 2023-05-24 | 2023-05-24 | 2024-04-08 | On-time | 2024-05-23 | 45 | 2024-05-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45810530 | T2 EI COTTONWD-RED BLUFF 12/242 COTTER | ICW
LC | 126254693 | 040/005 | T2 EI FORT ROSS-GUALALA 40/05 RPR JMPW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46073738 | T2 EI FORT ROSS-GUALALA 40/05 RPR JMPW | ICW
LC | 126254700 | 040/004 | T2 EI FORT ROSS-GUALALA 40/04 RPR GYWW | LAKEVLLE | ETL.6980.POLE.NWOD | 2023-05-31 | 2023-05-31 | 2024-06-10 | Late | 2024-05-30 | -11 | 2024-05-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46254607 | T2 EI FORT ROSS-GUALALA 40/04 RPR GYWW | ICW
LC | 126254855 | 029/245 | T2 DI BRIDGEVLL-COTT 29/245L RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-05-31 | 2023-05-23 | 2024-05-30 | Late | 2024-05-22 | -8 | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073756 | T2 DI BRIDGEVLL-COTT 29/245L RPR GYWW | ICW
LC | 126255017 | 015/137A | T2 EI SLO-CAYUCOS 15/137A RPL INSW | PISMOBCH | ETL.9090.INSL.CERA | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35520659 | T2 EI SLO-CAYUCOS 15/137A RPL INSS | 93I
LC | 126255080 | 034/008 | T2 DI TRINTY-MPLE CRK 34/08L RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-31 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170569 | T2 DI TRINTY-MPLE CRK 34/08R RPR GYWW | ICW
LC | 126255254 | 034/008 | T2 DI TRINTY-MPLE CRK 34/08C RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-31 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170569 | T2 DI TRINTY-MPLE CRK 34/08R RPR GYWW | ICW
LC | 126255267 | 007/075 | T2 WV PIT #5-RND MTN #1 07/075 INS DMPW | TABLEMTN | ETL.5420.INSL.NCER | 2023-05-31 | 2023-05-31 | 2024-06-01 | Late | 2024-05-30 | -2 | 2024-05-31 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46076167 | T2 WV PIT #5-RND MTN #1 07/075 INS DMPW | ICW
LC | 126255431 | 000/005 | T2 EI RND MTN-TABLE MTN #1 0/5 RPR GYWT | TABLEMTN | ETL.6060.TOWR | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46228988 | T2 EI RND MTN-TABLE MTN #1 0/05 RPR GYWT | ICQ
LC | 126255863 | 003/074 | T2 DI HAT CREEK #1-WSTWD 3/74 RPR CRSW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-31 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46062824 | T2 DI HAT CREEK #1-WSTWD 3/74 RPR CRSW | ICW
LC | 126255865 | 003/074 | T2 DI HAT CREEK #1-WSTWD 3/74 RPL HRDD | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-31 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46062825 | T2 DI HAT CREEK #1-WSTWD 3/74 RPL HRDD | ICW
LC | 126218836 | 008/175 | T2 EI HMLTN BRNCH-CHSTR 8/175 RPR GYWW | TABLEMTN | ETL.7000.POLE.NWOD | 2023-05-24 | 2023-05-24 | 2023-09-29 | On-time | 2024-05-23 | 237 | 2024-05-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45937222 | T2 EI HMLTN BRNCH-CHSTR 8/175 RPR GYWW | ICW
LC | 126256471 | 040/006 | T2 EI FORT ROSS-GUALALA 40/06R RPR GYWW | LAKEVLLE | ETL.6980.POLE.STPS | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073739 | T2 EI FORT ROSS-GUALALA 40/06R RPR GYWW | ICW
LC | 126256521 | 016/314 | T2 DI HAT CRK #1-WW 16/314 RPR CRSW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-31 | 2023-05-19 | 2024-06-17 | Late | 2024-05-18 | -30 | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46062857 | T2 DI HAT CRK #1-WW 16/314 RPR CRSW | ICW
LC | 126256525 | 016/314 | T2 DI HAT CRK #1-WW 16/314 RPL HRDW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-31 | 2023-05-19 | 2024-06-17 | Late | 2024-05-18 | -30 | 2024-05-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46062858 | T2 DI HAT CRK #1-WW 16/314 ANTI SPLIT | ICW
LC | 126256745 | :013/071 | T2 CRZY HRSE CNYN-SLNS :13/71 RMV ENCRCH | MOSSLNDG | ETL.2900.TOWR | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2023-11-30 | 931 | TLS |  | E - Schd Compl Yr 0 | Open | TR2 | Encroachment | Right of Way | Remove
LC | 126218926 | 004/027 | T2 EI BALCH-SANGER 4/027 RPR FOND | FRESNO | ETL.1050.TOWR | 2023-05-24 | 2023-05-24 | 2024-04-08 | On-time | 2024-05-23 | 45 | 2024-05-24 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46069693 | T2 EI BALCH-SANGER 4/027 RPR FOND | ICQ
LC | 126220136 | 008/180 | T2 EI HAMILTN BRNCH-CHSTR 8/180 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2023-05-24 | 2023-05-24 | 2023-10-05 | On-time | 2024-05-23 | 231 | 2024-05-24 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663250 | T2 EI HAMILTN BRNCH-CHSTR 8/180 RPL STRW | 70Y
LC | 126257464 | 055/003 | T2 EI HMBLDT TRNTY 055/003R RPR JMPW | EUREKA | ETL.1820.INSL.NCER | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46171102 | T2 EI HMBLDT TRNTY 055/003R RPR JMPW | ICW
LC | 126258044 | 028/114 | T2 EI DIABLO-MIDWAY #2 28/114 RPR FOND | PISMOBCH | ETL.5970.TOWR | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 45825183 | T2 EI DIABLO-MIDWAY #2 28/114 RPR FOND | ICQ
LC | 126220238 | 017/354 | T2 WV KILARC-DESCHUTES 17/354 INS DMPW | TABLEMTN | ETL.7300.INSL.NCER | 2023-05-24 | 2023-05-24 | 2024-04-05 | On-time | 2024-05-23 | 48 | 2024-05-24 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46073820 | T2 WV KILARC-DESCHUTES 17/354 INS DMPW | ICW
LC | 126258094 | 020/387 | T2 EI HAT CRK #1-WESTWD 020/387 COMPLETE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514865 | T2 EI HAT CRK #1-WESTWD 020/387 RPL POLE | 70Y
LC | 126258107 | 033/011 | T2 EI FORT ROSS-GUALALA 033/011 RPL STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35561834 | T2 EI FORT ROSS-GUALALA 033/011 RPL STRW | 70Y
LC | 126258269 | 020/007 | T2 DI TRINITY-MAPLE CREEK 20/7L RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-31 | 2023-05-31 | 2024-06-19 | Late | 2024-05-30 | -20 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45823639 | T2 DI TRINITY-MAPLE CREEK 20/7L RPR GYWW | ICW
LC | 126258359 | 006/070 | T2 WV PIT #5-RND MTN #1 006/070 INS DMPS | TABLEMTN | ETL.5420.INSL.NCER | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Steel | Install | 46076082 | T2 WV PIT #5-RND MTN #1 006/070 INS DMPS | ICS
LC | 126220331 | 007/006 | T2 EI MNDCNO-WLLTS-FRT BRGG 7/6 RPR POLE | WILLITS | ETL.7550.POLE.WOOD | 2023-05-24 | 2023-05-24 | 2024-05-11 | On-time | 2024-05-23 | 12 | 2024-05-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46214146 | T2 EI MNDCNO-WLLTS-FRT BRGG 7/6 RPR POLE | ICW
LC | 126258376 | 045/008 | T2 TRINITY-MAPLE CREEK 45/8 RPL TIE WIRE | EUREKA | ETL.8170.INSL | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2023-08-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46079271 | T2 TRINITY-MAPLE CREEK 45/8 RPL TIE WIRE | ICW
LC | 126258457 | 027/003 | T2 EI TRINITY-MAPLE CREEK 27/3 RPR INSW | EUREKA | ETL.8170.INSL | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2023-11-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45844364 | T2 EI TRINITY-MAPLE CREEK 27/03 RPR INSW | ICW
LC | 126258459 | 027/003 | T2 EI TRINITY-MAPLE CREEK 27/3 RPL ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35550661 | T2 EI TRINITY-MAPLE CREEK 27/3 RPL ANCW | 93E
LC | 126258512 | 013/108A | T2 EI PT #6 JCT-RND MTN 13/108A RPR GYWW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076168 | T2 EI PT #6 JCT-RND MTN 13/108A RPR GYWW | ICW
LC | 126258667 | 013/108B | T2 EI PT #6 JCT-RND MTN 13/108B RPR GYWW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076169 | T2 EI PT #6 JCT-RND MTN 13/108B RPR GYWW | ICW
LC | 126258716 | 047/000 | T2 FORT ROSS-GUALALA 47/0 GO95 | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31653342 | T2 FORT ROSS-GUALALA 035/008 GO95 CLEAR | 93G
LC | 126258790 | 020/007 | T2 DI TRINITY-MAPLE CREEK 20/7C RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-31 | 2023-05-31 | 2024-06-25 | Late | 2024-05-30 | -26 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45823637 | T2 DI TRINITY-MAPLE CREEK 20/7C RPR GYWW | ICW
LC | 126258791 | 020/007 | T2 DI TRINITY-MAPLE CREEK 20/7R RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-05-31 | 2023-05-31 | 2024-06-19 | Late | 2024-05-30 | -20 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45823638 | T2 DI TRINITY-MAPLE CREEK 20/7R RPR GYWW | ICW
LC | 126258918 | 035/008 | T2 FORT ROSS-GUALALA 35/8 GO95 CLEAR | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31653342 | T2 FORT ROSS-GUALALA 035/008 GO95 CLEAR | 93G
LC | 126220482 | 005/126 | T2 WV COLGATE-GRSS VALLEY 5/126 RPR POLE | SACTO | ETL.6490.POLE.NWOD | 2023-05-24 | 2023-05-24 | 2024-01-30 | On-time | 2024-05-23 | 114 | 2024-05-24 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46063684 | T2 WV COLGATE-GRSS VALLEY 5/126 RPR POLE | ICW
LC | 126220718 | 008/181 | T2 EI HMLTN BRNCH-CHSTR 8/181 RPR GYWW | TABLEMTN | ETL.7000.POLE.NWOD | 2023-05-24 | 2023-05-24 | 2023-09-24 | On-time | 2024-05-23 | 242 | 2024-05-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45937223 | T2 EI HMLTN BRNCH-CHSTR 8/181 RPR GYWW | ICW
LC | 126259421 | 034/007 | T2 RIO DL JCT-BRIDGVILLE 34/7 GO95 CLEAR | EUREKA | ETL.7850.POLE.WOOD | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656734 | T2 RIO DL JCT-BRIDGVILLE 34/7 GO95 CLEAR | 93G
LC | 126259466 | 034/010 | T2 RIO DELL JCT-BRDGVLL 34/10 GO95 | EUREKA | ETL.7850.POLE.WOOD | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31652879 | T2 RIO DELL JCT-BRDGVLL 34/10 GO95 | 93G
LC | 126259580 | A000/004 | T2 SMTVL-CMP FR WST A0/4 GO95 | SACTO | ETL.7970.POLE.WOOD | 2023-05-31 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31653040 | T2 SMTVL-CMP FR WST A0/4 GO95 | 93G
LC | 126220924 | 004/005 | T2 EI TRINITY-MAPLE CREEK 4/5 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-24 | 2023-05-24 | 2023-08-01 | On-time | 2024-05-23 | 296 | 2023-08-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45824892 | T2 EI TRINITY-MAPLE CREEK 4/5 RPR GYWW | ICW
LC | 126259839 | 086/004C | T2 HUMBOLDT-TRINITY 86/04C RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46096593 | T2 HUMBOLDT-TRINITY 86/04C RPR INSW | ICW
LC | 126221213 | 067/005C | T2 EI HMBLDT-TRNTY 067/005C RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2023-05-24 | 2023-05-24 | 2024-04-11 | On-time | 2024-05-23 | 42 | 2024-05-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171107 | T2 EI HMBLDT-TRNTY 067/005B RPR GYWW | ICW
LC | 126260446 | 016/310 | T2 DI HAT CREEK#1 WSTWD 16/310 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-01 | 2023-05-19 | 2024-06-16 | Late | 2024-05-18 | -29 | 2024-05-19 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35512701 | T2 DI HAT CREEK#1 WSTWD 16/310 REFRAME | 93E
LC | 126221215 | 067/005B | T2 EI HMBLDT-TRNTY 067/005B RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2023-05-24 | 2023-05-24 | 2024-04-11 | On-time | 2024-05-23 | 42 | 2024-05-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171107 | T2 EI HMBLDT-TRNTY 067/005B RPR GYWW | ICW
LC | 126221626 | 049/000B | T2 EI HUMBOLDT-TRINITY 49/0B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-24 | 2023-05-24 | 2024-01-23 | On-time | 2024-05-23 | 121 | 2024-05-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096522 | T2 EI HUMBOLDT-TRINITY 49/0A RPR GYWW | ICW
LC | 126221628 | 049/000A | T2 EI HUMBOLDT-TRINITY 49/0A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-24 | 2023-05-24 | 2024-01-23 | On-time | 2024-05-23 | 121 | 2024-05-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096522 | T2 EI HUMBOLDT-TRINITY 49/0A RPR GYWW | ICW
LC | 126222334 | 049/000C | T2 EI HMBLDT-TRNTY 049/000C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-25 | 2023-05-24 | 2024-01-23 | On-time | 2024-05-23 | 121 | 2024-05-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096522 | T2 EI HUMBOLDT-TRINITY 49/0A RPR GYWW | ICW
LC | 126261270 | 005/116 | T2 DI HAT CRK #1-WSTWD 5/116 RPR GYWW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-01 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076178 | T2 DI HAT CRK #1-WSTWD 5/116 RPR GYWW | ICW
LC | 126262235 | 011/105 | T2 EI WDLF-PALERMO 11/105 RPL STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525905 | T2 EI WDLF-PALERMO 11/105 RPL STRW | 70Y
LC | 126262382 | 003/023 | T2 DI BALCH-SANGER 3/23 RMV VEG | FRESNO | ETL.1050.TOWR | 2023-06-01 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126252230 | 001/005 | T2 DI TRNTY-MPL CRK 1/5 RPR SPLW | EUREKA | ETL.8170.INSL.NCER | 2023-05-30 | 2023-05-24 | 2024-02-23 | On-time | 2024-05-23 | 90 | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46070811 | T2 DI TRNTY-MPL CRK 1/5 RPR SPLW | ICW
LC | 126263415 | 038/000 | T2 DI TRNTY MPL CRK 38/000 RPL INSW | EUREKA | ETL.8170.INSL.CERA | 2023-06-01 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35506418 | T2 DI TRNTY MPL CRK 38/000 RPL INSW | 93I
LC | 126263671 | 019/374 | T2 EI HAT CRK #1-WESTWD 19/374 RPL TIED | TABLEMTN | ETL.7030.INSL | 2023-06-01 | 2023-06-01 | 2024-06-14 | Late | 2024-05-31 | -14 | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46076250 | T2 EI HAT CRK #1-WESTWD 019/374 RPR INSW | ICW
LC | 126264415 | 056/006A | T2 EI HUMBOLDT-TRINITY 56/6A RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096525 | T2 EI HUMBOLDT-TRINITY 56/6A RPR GYWW | ICW
LC | 126264490 | 056/006B | T2 EI HUMBOLDT-TRINITY 56/06B RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096525 | T2 EI HUMBOLDT-TRINITY 56/6A RPR GYWW | ICW
LC | 126264559 | 056/006C | T2 EI HUMBOLDT-TRINITY 56/6C RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096525 | T2 EI HUMBOLDT-TRINITY 56/6A RPR GYWW | ICW
LC | 126264717 | 021/411 | T2 EI HAT CREEK #1-WSTWD 21/411 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514865 | T2 EI HAT CRK #1-WESTWD 020/387 RPL POLE | 70Y
LC | 126264862 | 015/104 | T2 EI GNC-LT-SSLT #1 015/104 COMPLETED | LAKEVLLE | ETL.7160.POLE.WOOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2023-12-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096613 | T2 EI GNC-LT-SSLT #1 015/104 RPR GYWW | ICW
LC | 126265394 | 012/101 | T2 EI PIT #6 JT-ROND MNT 12/101 RPL HRDW | TABLEMTN | ETL.5440.POLE.STPS | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46262871 | T2 EI PIT #6 JT-ROND MNT 12/101 RPL HRDW | ICW
LC | 126268746 | 052/1018 | T2 DI HAT CRK #1-WSTWD 52/1018 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-01 | 2023-05-24 | 2023-11-17 | On-time | 2024-05-23 | 188 | 2023-11-24 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31655448 | T2 DI HAT CRK #1-WSTWD 52/1018 RPL STRW | 70Y
LC | 126265871 | 035/239A | T2 EI TRINTY-COTTNWD 35/239A RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076664 | T2 EI TRINTY-COTTNWD 35/239A RPR GYWW | ICW
LC | 126266065 | 016/311 | T2 DI HAT CREEK#1 WSTWD 16/311 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-01 | 2023-05-19 | 2024-06-16 | Late | 2024-05-18 | -29 | 2024-05-19 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512703 | T2 DI HAT CREEK#1 WSTWD 16/311 RPL STRW | 70Y
LC | 126266489 | 021/409 | T2 EI HAT CREEK #1-WSTWD 21/409 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-01 | 2023-06-01 | 2024-06-19 | Late | 2024-05-31 | -19 | 2024-06-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35514005 | T2 EI HAT CRK #1-WESTWOOD 21/405 RPL PL | 70Y
LC | 126266513 | 035/239B | T2 EI TRINTY-COTTNWD 35/239B RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076666 | T2 EI TRINTY-COTTNWD 35/239B RPR GYWW | ICW
LC | 126266540 | 021/408 | T2 EI HAT CRK #1-WSTWD 21/408 RPR VBRACE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-01 | 2023-06-01 | 2024-06-23 | Late | 2024-05-31 | -23 | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46076254 | T2 EI HAT CREEK #1-WSTWD 21/408 RPR POLE | ICW
LC | 126266561 | 021/405 | T2 EI HAT CRK #1-WESTWD 21/405 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-01 | 2023-06-01 | 2024-06-19 | Late | 2024-05-31 | -19 | 2024-06-01 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514005 | T2 EI HAT CRK #1-WESTWOOD 21/405 RPL PL | 70Y
LC | 126266562 | 021/404 | T2 EI HAT CRK #1-WESTWD 21/405 RPR STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46076252 | T2 EI HAT CRK #1-WESTWD 21/405 RPR WDPKR | ICW
LC | 126266598 | 035/239C | T2 EI TRINTY-COTTNWD 35/239C RPR ANCW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46218912 | T2 EI TRINTY-COTTNWD 35/239C RPR ANCW | ICW
LC | 126266617 | 035/239C | T2 EI TRINTY-COTTNWD 35/239C RPR GYWW | TABLEMTN | ETL.4040.POLE.NWOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076667 | T2 EI TRINTY-COTTNWD 35/239C RPR GYWW | ICW
LC | 126285643 | 011/005 | T2 DI TRINITY-MAPLE CREEK 11/5 COTTER | EUREKA | ETL.8170.POLE.NWOD | 2023-06-03 | 2023-05-24 | 2024-02-17 | On-time | 2024-05-23 | 96 | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46070813 | T2 DI TRINITY-MAPLE CREEK 11/5 COTTER | ICW
LC | 126266999 | 014/099 | T2 EI IGNC-ALT-SSLTO #1 14/99 COTTER | LAKEVLLE | ETL.7160.POLE.WOOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46070945 | T2 EI IGNC-ALT-SSLTO #1 14/99 COTTER | ICW
LC | 126267015 | 075/001A | T2 EI HUMBOLDT-TRINITY 75/1AR RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2023-12-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45860428 | T2 EI CTNWD-HUMBLDT NO. 1 75/1A RPR GYWW | ICW
LC | 126267024 | 040/005 | T2 DI TRNTY MPL CRK 40/005L RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-06-01 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172188 | T2 DI TRNTY MPL CRK 40/005L RPR GYWW | ICW
LC | 126267036 | 075/001A | T2 EI HUMBOLDT-TRINITY 75/1AL RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2023-12-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46190592 | T2 EI HUMBOLDT-TRINITY 75/1AL RPR GYWW | ICW
LC | 126267087 | 018/096 | T2 EI RND MTN-TBLE MTN #2 18/96 REGRADE | TABLEMTN | ETL.6070.TOWR | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46072211 | T2 EI RND MTN-TBLE MTN #2 18/96 REGRADE | ICQ
LC | 126267098 | 004/043 | T2 EI WOODLEAF-PALERMO 004/043 RMV VEG | TABLEMTN | ETL.4220.POLE.STPS | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2023-12-01 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Trim
LC | 126267118 | 004/043 | T2 EI WDLF-PALRMO 4/43L RPR GYWW | TABLEMTN | ETL.4220.POLE.STPS | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2023-12-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076663 | T2 EI WOODLEAF-PALERMO 004/043L RPR GYWW | ICW
LC | 126298825 | 001/007 | T2 DI TRINITY-MAPLE CRK 1/7 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-05 | 2023-05-24 | 2024-05-11 | On-time | 2024-05-23 | 12 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485472 | T2 DI TRINITY-MAPLE CREEK 0/18 RPL POLE | 70Y
LC | 126267433 | 026/007 | T2 DI TRNTY-MPL CRK 26/7 RPR IBWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2023-09-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45825043 | T2 DI TRNTY-MPL CRK 26/7 RPL HRDD | ICW
LC | 126267465 | 033/002 | T2 EI TRINITY-MAPLE CREEK 33/2R RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-01 | 2023-06-01 | 2024-06-14 | Late | 2024-05-31 | -14 | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172097 | T2 EI TRINITY-MAPLE CREEK 33/02 RPR GYWW | ICW
LC | 126267467 | 033/002 | T2 EI TRINITY-MAPLE CREEK 33/2C RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-01 | 2023-06-01 | 2024-06-14 | Late | 2024-05-31 | -14 | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172097 | T2 EI TRINITY-MAPLE CREEK 33/02 RPR GYWW | ICW
LC | 126267469 | 033/002 | T2 EI TRINITY-MAPLE CREEK 33/2L RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-01 | 2023-06-01 | 2024-06-14 | Late | 2024-05-31 | -14 | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172097 | T2 EI TRINITY-MAPLE CREEK 33/02 RPR GYWW | ICW
LC | 126267472 | 032/003A | T2 EI TRINITY-MAPLE CREEK 32/3A RPL HRDD | EUREKA | ETL.8170.INSL.NCER | 2023-06-01 | 2023-06-01 | 2024-06-14 | Late | 2024-05-31 | -14 | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46172094 | T2 EI TRINITY-MAPLE CREEK 32/3A RPL HRDD | ICW
LC | 126267473 | 032/004 | T2 EI TRINITY-MAPLE CRK 32/4C RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-01 | 2023-06-01 | 2024-06-14 | Late | 2024-05-31 | -14 | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172095 | T2 EI TRINITY-MAPLE CRK 032/04C RPR GYWW | ICW
LC | 126267485 | 018/096 | T2 EI RND MTN-TBL MTN#1 18/96 BNT STEEL | TABLEMTN | ETL.6060.TOWR | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072210 | T2 EI RND MTN-TBLE MTN #1 18/96 BNT STL | ICQ
LC | 126267500 | 018/096 | T2 EI RND MTN-TBLE MTN #1 18/96 REGRADE | TABLEMTN | ETL.6060.TOWR | 2023-06-01 | 2023-06-01 | 2024-06-17 | Late | 2024-05-31 | -17 | 2024-06-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46072209 | T2 EI RND MTN-TBLE MTN #1 18/96 REGRADE | ICQ
LC | 126298848 | 001/003 | T2 DI TRNTY-MPL CRK 1/3 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-05 | 2023-05-24 | 2024-05-11 | On-time | 2024-05-23 | 12 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35485472 | T2 DI TRINITY-MAPLE CREEK 0/18 RPL POLE | 70Y
LC | 126298995 | 008/099A | T2 DI DRUM-SUMMIT #2 8/99A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-05 | 2023-05-24 | 2024-05-22 | On-time | 2024-05-23 | 1 | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101322 | T2 DI DRUM-SUMMIT #2 8/99A RPR GYWW | ICW
LC | 126267547 | 001/022 | T2 EI HAAS-WOODCHUCK 1/22 RPR ANCW | FRESNO | ETL.8730.POLE.WOOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46155497 | T2 EI HAAS-WOODCHUCK 1/22 RPR ANCW | ICW
LC | 126267549 | 001/021 | T2 EI HAAS-WOODCHUCK 1/21 RPR ANCW | FRESNO | ETL.8730.POLE.WOOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46155498 | T2 EI HAAS-WOODCHUCK 001/021 RPR ANCW | ICW
LC | 126267584 | 001/025 | T2 EI HAAS-WOODCHUCK 1/25 RPL DMPW | FRESNO | ETL.8730.INSL.NCER | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 46155499 | T2 EI HAAS-WOODCHUCK 1/25 RPL DMPW | ICW
LC | 126267587 | 000/019 | T2 EI HAAS-WOODCHUCK 0/19 RPL ANCW | FRESNO | ETL.8730.POLE.WOOD | 2023-06-01 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35500715 | T2 EI HAAS-WOODCHUCK 0/19 RPL ANCW | 93E
LC | 126299087 | 008/099C | T2 DI DRUM-SUMMIT #2 8/99C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-05 | 2023-05-24 | 2024-05-22 | On-time | 2024-05-23 | 1 | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101325 | T2 DI DRUM-SUMMIT #2 8/99C RPR GYWW | ICW
LC | 126223630 | 027/222 | T2 EI PIT #1-COTTONWOOD 27/222 UNBURY | TABLEMTN | ETL.5390.TOWR | 2023-05-25 | 2023-05-25 | 2024-01-30 | On-time | 2024-05-24 | 115 | 2024-05-25 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46072205 | T2 EI PIT #1-COTTONWOOD 27/222 UNBURY | ICQ
LC | 126224737 | 011/096 | T2 EI SAN LUIS OBSPO-CYCS 11/96 RPR GYWW | PISMOBCH | ETL.9090.POLE.WOOD | 2023-05-25 | 2023-05-25 | 2024-04-23 | On-time | 2024-05-24 | 31 | 2024-05-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46090151 | T2 EI SAN LUIS OBSPO-CYCS 11/96 RPR GYWW | ICW
LC | 126267858 | 010/119B | T2 DI DRUM SUMMIT#2 10/119B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-01 | 2023-05-23 | 2024-05-23 | Late | 2024-05-22 | -1 | 2024-05-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101317 | T2 DI DRUM SUMMIT#2 10/119B RPR GYWW | ICW
LC | 126225469 | A007/153 | T2 EI CASCDE-BNTN-DSCHTS A7/153 RPR POLE | TABLEMTN | ETL.6310.POLE.WOOD | 2023-05-25 | 2023-05-25 | 2024-05-13 | On-time | 2024-05-24 | 11 | 2024-05-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46073818 | T2 EI CASCDE-BNTN-DSCHTS A7/153 RPR POLE | ICW
LC | 126267898 | 040/002 | T2 DI TRINITY-MAPLE CREEK 40/02 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-01 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506726 | T2 DI TRINITY-MAPLE CREEK 40/02 RPL STRW | 70Y
LC | 126267921 | 005/108 | T2 DI HAT CRK #1-WSTWD 5/108 GO95 | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-01 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35513921 | T2 DI HT CRK#1-WSTWD 0/7 G095 | 93G
LC | 126226034 | 068/001 | T2 EI HUMBOLDT-TRINITY 68/01L RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-05-25 | 2023-05-25 | 2024-04-11 | On-time | 2024-05-24 | 43 | 2024-05-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096537 | T2 EI HUMBOLDT-TRINITY 68/01L RPR GYWW | ICW
LC | 126226037 | 068/001 | T2 EI HUMBOLDT-TRINITY 68/01R RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-05-25 | 2023-05-25 | 2024-04-11 | On-time | 2024-05-24 | 43 | 2024-05-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096537 | T2 EI HUMBOLDT-TRINITY 68/01L RPR GYWW | ICW
LC | 126268029 | 025/481 | T2 DI HAT CREEK #1-WSTWD 25/481 RPL HRDD | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-01 | 2023-05-24 | 2024-06-19 | Late | 2024-05-23 | -27 | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46076215 | T2 DI HAT CREEK #1-WSTWD 25/481 RPL HRDD | ICW
LC | 126226407 | 049/001 | T2 EI HUMBOLDT-TRINITY 49/1L RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-05-25 | 2023-05-25 | 2024-01-23 | On-time | 2024-05-24 | 122 | 2024-05-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096523 | T2 EI HUMBOLDT-TRINITY 49/1L RPR GYWW | ICW
LC | 126268096 | :007/006 | T2 DI CARIBOU #2 :7/6 RPR INSW | TABLEMTN | ETL.6280.INSL.CERA | 2023-06-01 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46073782 | T2 DI CARIBOU #2 :7/6 RPR INSW | ICW
LC | 126226680 | 049/001 | T2 EI HUMBOLDT-TRINITY 49/1C RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-05-25 | 2023-05-25 | 2024-01-23 | On-time | 2024-05-24 | 122 | 2024-05-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096523 | T2 EI HUMBOLDT-TRINITY 49/1L RPR GYWW | ICW
LC | 126229159 | 024/182 | T2 EI PARADISE-TBLE MTN 24/182C RPR GYWW | TABLEMTN | ETL.4316.POLE.STPS | 2023-05-25 | 2023-05-25 | 2024-01-25 | On-time | 2024-05-24 | 120 | 2024-05-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076622 | T2 EI PARADISE-TBLE MTN 24/182C RPR GYWW | ICW
LC | 126229525 | 021/004 | T2 EI TRINITY-MAPLE CREEK 21/4 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-05-25 | 2023-05-25 | 2023-10-11 | On-time | 2024-05-24 | 226 | 2023-11-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45853865 | T2 EI TRINITY-MAPLE CREEK 21/4 RPR GYWW | ICW
LC | 126268133 | 011/230 | T2 DI HAT CRK #1-WSTWD 011/230 RPR GYWW | TABLEMTN | ETL.7030.POLE.NWOD | 2023-06-01 | 2023-05-24 | 2024-06-13 | Late | 2024-05-23 | -21 | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076179 | T2 DI HAT CRK #1-WSTWD 011/230 RPR GYWW | ICW
LC | 126268143 | 023/449 | T2 DI HAT CRK #1-WSTWD 23/449 RPR CRSW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-01 | 2023-05-24 | 2024-06-25 | Late | 2024-05-23 | -33 | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46076214 | T2 DI HAT CRK #1-WSTWD 23/449 RPR CRSW | ICW
LC | 126268240 | 010/118 | T2 DI DRUM-SUMMIT #2 10/118L RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2023-06-01 | 2023-05-23 | 2024-06-26 | Late | 2024-05-22 | -35 | 2024-05-23 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484103 | T2 EI DRUM-SUMMIT #2_010/117C RPL POLE | 70Y
LC | 126268241 | 010/118 | T2 DI DRUM-SUMMIT #2 10/118R RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2023-06-01 | 2023-05-23 | 2024-06-26 | Late | 2024-05-22 | -35 | 2024-05-23 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484103 | T2 EI DRUM-SUMMIT #2_010/117C RPL POLE | 70Y
LC | 126268282 | 023/447 | T2 DI HAT CRK #1-WSTWD 23/447 COTTER | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-01 | 2023-05-24 | 2024-06-22 | Late | 2024-05-23 | -30 | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076213 | T2 DI HAT CRK #1-WSTWD 23/447 COTTER | ICW
LC | 126230191 | 073/373 | T2 EI MALIN-ROUND MTN #2 74/373 RPR CNDS | TABLEMTN | ETL.6020.INSL.NCER | 2023-05-25 | 2023-05-25 | 2024-03-26 | On-time | 2024-05-24 | 59 | 2024-05-25 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46056063 | T2 EI MALIN-ROUND MTN #2 74/373 RPR CNDS | ICS
LC | 126275956 | 018/381 | T2 DI CARIBOU WESTWOOD 018/381 COTTER | TABLEMTN | ETL.6300.INSL.NCER | 2023-06-02 | 2023-05-25 | 2024-03-20 | On-time | 2024-05-24 | 65 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46073817 | T2 DI CARIBOU WESTWOOD 018/381 COTTER | ICW
LC | 126277247 | 002/017 | T2 DI HAAS MCCALL 2/17 COTTER | FRESNO | ETL.4850.INSL | 2023-06-02 | 2023-05-25 | 2024-05-09 | On-time | 2024-05-24 | 15 | 2024-05-25 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46072145 | T2 DI HAAS MCCALL 02/017 RPR INSS | ICS
LC | 126277248 | 002/017 | T2 DI HAAS MCCALL 2/17 RPL HRDT | FRESNO | ETL.4850.TOWR | 2023-06-02 | 2023-05-25 | 2024-01-31 | On-time | 2024-05-24 | 114 | 2024-05-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46070849 | T2 DI HAAS MCCALL 2/17 RPL HRDT | ICQ
LC | 126277913 | 006/037 | T2 DI BALCH-SANGER 6/37 UNBURY | FRESNO | ETL.1050.TOWR | 2023-06-02 | 2023-05-25 | 2024-01-26 | On-time | 2024-05-24 | 119 | 2024-05-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46069695 | T2 DI BALCH-SANGER 6/37 UNBURY | ICQ
LC | 126278813 | 004/093 | T2 DI CARIBOU-WESTWOOD 004/093C UNBURY | TABLEMTN | ETL.6300.POLE.STPS | 2023-06-02 | 2023-05-25 | 2024-05-03 | On-time | 2024-05-24 | 21 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46073804 | T2 DI CARIBOU-WESTWOOD 004/093C UNBURY | ICW
LC | 126268362 | 023/443 | T2 DI HAT CRK #1-WSTWOD 23/443 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-01 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514120 | T2 DI HAT CRK #1-WSTWOD 23/443 RPL POLE | 70Y
LC | 126278814 | 004/093 | T2 DI CARIBOU-WESTWOOD 004/093R UNBURY | TABLEMTN | ETL.6300.POLE.STPS | 2023-06-02 | 2023-05-25 | 2024-05-03 | On-time | 2024-05-24 | 21 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46073805 | T2 DI CARIBOU-WESTWOOD 004/093R UNBURY | ICW
LC | 126278815 | 004/093 | T2 DI CARIBOU-WESTWOOD 004/093L UNBURY | TABLEMTN | ETL.6300.POLE.STPS | 2023-06-02 | 2023-05-25 | 2024-05-03 | On-time | 2024-05-24 | 21 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46073806 | T2 DI CARIBOU-WESTWOOD 004/093L UNBURY | ICW
LC | 126278819 | 004/093 | T2 DI CARIBOU-WESTWOOD 004/093 COTTER | TABLEMTN | ETL.6300.INSL.NCER | 2023-06-02 | 2023-05-25 | 2024-05-03 | On-time | 2024-05-24 | 21 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46073807 | T2 DI CARIBOU-WESTWOOD 004/093 COTTER | ICW
LC | 126279506 | 006/040 | T2 DI BALCH SANGER 06/040 RPL HRDT | FRESNO | ETL.1050.TOWR | 2023-06-02 | 2023-05-25 | 2024-01-25 | On-time | 2024-05-24 | 120 | 2024-05-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46135585 | T2 DI BALCH SANGER 06/040 RPL HRDT | ICQ
LC | 126269949 | 053/1034 | T2 DI HT CRK#1-WSTWD 53/1034 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514339 | T2 DI HT CRK#1-WSTWD 53/1034 RPL POLE | 70Y
LC | 126270092 | 027/537 | T2 DI HAT CRK #1-WSTW 27/537 GO95 RPL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-24 | 2024-06-26 | Late | 2024-05-23 | -34 | 2024-05-24 | 401T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35522538 | T2 DI HAT CRK #1-WSTW 027/537 GO95 CLR | 93G
LC | 126270187 | 047/003 | T2 DI TRINITY-MAPLE CREEK 47/3 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-02 | 2023-05-24 | 2024-06-06 | Late | 2024-05-23 | -14 | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096679 | T2 DI TRINITY-MAPLE CREEK 47/3 RPR GYWW | ICW
LC | 126275893 | 031/595 | T2 DI HAT CREEK #1-WESTWD COMPLETE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-25 | 2024-06-23 | Late | 2024-05-24 | -30 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46076239 | T2 DI HAT CREEK#1 WESTWOOD#1 RPR CRSW | ICW
LC | 126280744 | 006/043 | T2 DI HAAS-MC CALL 006/043 RPR INSS | FRESNO | ETL.4850.INSL | 2023-06-02 | 2023-05-25 | 2024-05-08 | On-time | 2024-05-24 | 16 | 2024-05-25 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46072056 | T2 DI HAAS-MC CALL 006/043 RPR INSS | ICS
LC | 126282495 | 005/039 | T2 DI HAAS-MC CALL 005/039 BNT STEEL | FRESNO | ETL.4850.TOWR | 2023-06-02 | 2023-05-25 | 2024-05-07 | On-time | 2024-05-24 | 17 | 2024-05-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46070850 | T2 DI HAAS-MC CALL 005/039 BNT STEEL | ICQ
LC | 126276206 | 003/024 | T2 DI BALCH-SANGER 3/24 RMV VEG | FRESNO | ETL.1050.TOWR | 2023-06-02 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126282499 | 018/375 | T2 DI CARIBOU-WESTWOOD 018/375 COTTER | TABLEMTN | ETL.6300.INSL | 2023-06-02 | 2023-05-25 | 2024-03-20 | On-time | 2024-05-24 | 65 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46073816 | T2 DI CARIBOU-WESTWOOD 018/375 COTTER | ICW
LC | 126276554 | 047/010 | T2 DI TRNTY-MPL CRK 47/10 RPR ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-02 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46172248 | T2 EI TRNTY-MPL CRK 47/10 RPR GYWW | ICW
LC | 126276834 | 082/577 | T2 DI BRDGVIL-CTTNWOOD 82/577R RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-06-02 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505109 | T2 DI BRDGVIL-CTTNWOOD 82/577R RPL STRW | 70Y
LC | 126276905 | 012/141A | T2 DI DRUM-SUMMIT #1 12/141A RPL ANCW | SACTO | ETL.1440.POLE.WOOD | 2023-06-02 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35484107 | T2 DI DRUM-SUMMIT#1 11/134L RPL ANCW | 93E
LC | 126282561 | 008/055 | T2 DI HAAS-MC CALL 8/55 BNT STEEL | FRESNO | ETL.4850.TOWR | 2023-06-02 | 2023-05-25 | 2024-01-23 | On-time | 2024-05-24 | 122 | 2024-05-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46070852 | T2 DI HAAS-MC CALL 008/055 BNT STEEL | ICQ
LC | 126277042 | 015/293 | T2 DI HAT CRK #1-WSTWD 15/293 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-24 | 2024-06-12 | Late | 2024-05-23 | -20 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35513923 | T2 DI HAT CRK #1-WESTWD 10/200 RPL STRW | 70Y
LC | 126282636 | 006/004B | T2 DI FORT SEWARD TAP 6/004B RPL ANCW | EUREKA | ETL.6222.POLE.NWOD | 2023-06-02 | 2023-05-25 | 2024-04-23 | On-time | 2024-05-24 | 31 | 2024-05-25 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35504386 | T2 DI FORT SEWARD TAP 6/004B RPL ANCW | 93E
LC | 126282770 | 006/004C | T2 DI FORT SEWARD TAP 6/004C RPL ANCW | EUREKA | ETL.6222.POLE.NWOD | 2023-06-02 | 2023-05-25 | 2024-04-23 | On-time | 2024-05-24 | 31 | 2024-05-25 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35504386 | T2 DI FORT SEWARD TAP 6/004B RPL ANCW | 93E
LC | 126282776 | 006/004A | T2 DI FORT SEWARD TAP 6/004A RPR GYWW | EUREKA | ETL.6222.POLE.NWOD | 2023-06-02 | 2023-05-25 | 2024-04-23 | On-time | 2024-05-24 | 31 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46183735 | T2 DI FORT SEWARD TAP 6/004A RPR GYWW | ICW
LC | 126283369 | 006/045 | T2 DI HAAS-MCCALL 6/45 RPL INSS | FRESNO | ETL.4850.INSL | 2023-06-03 | 2023-05-25 | 2024-05-08 | On-time | 2024-05-24 | 16 | 2024-05-25 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510275 | T2 DI HAAS-MCCALL 6/45 RPL INSS | 93K
LC | 126277466 | 034/669 | T2 DI HAT CRK #1-WSTWD 34/669 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514264 | T2 EI HAT CREEK #1-WSTWD 34/667 RPL POLE | 70Y
LC | 126277746 | 031/603 | T2 DI HAT CRK #1-WSTWD 31/603 RPL HRDD | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-25 | 2024-06-19 | Late | 2024-05-24 | -26 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46076240 | T2 DI HAT CRK #1-WSTWD 31/603 ANTI SPLIT | ICW
LC | 126277757 | 000/007 | T2 DI HT CRK#1-WSTWD 0/7 GO95 RPL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35513921 | T2 DI HT CRK#1-WSTWD 0/7 G095 | 93G
LC | 126277864 | 033/645 | T2 DI HAT CREEK#1 WSTWD 33/645 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-25 | 2024-06-27 | Late | 2024-05-24 | -34 | 2024-05-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514210 | T2 DI HT CRK #1-WSTWD 33/644 RPL POLE | 70Y
LC | 126283655 | 010/060 | T2 DI HAAS-MCCALL 10/60 RPR STRT | FRESNO | ETL.4850.TOWR | 2023-06-03 | 2023-05-25 | 2024-04-09 | On-time | 2024-05-24 | 45 | 2024-05-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46070853 | T2 DI HAAS-MCCALL 10/60 RPR STRT | ICQ
LC | 126277963 | :001/004 | T2 EI FULTON-PUEBLO :01/04 RPL STRW | LAKEVLLE | ETL.1600.POLE.WOOD | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35555009 | T2 EI FULTON-PUEBLO :01/04 RPL STRW | 70Y
LC | 126283917 | 006/044 | T2 DI HAAS-MCCALL 006/044 BNT STEEL | FRESNO | ETL.4850.TOWR | 2023-06-03 | 2023-05-25 | 2024-01-31 | On-time | 2024-05-24 | 114 | 2024-05-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46070851 | T2 DI HAAS-MCCALL 006/044 BNT STEEL | ICQ
LC | 126278089 | 47 | T2 DI TRNTY-MPL CREEK 28/8 RPR SWTC | EUREKA | ETL.8170.SWIT | 2023-06-02 | 2023-05-25 |  | Late | 2024-05-24 |  | 2023-11-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 45825063 | T2 DI TRNTY-MPL CREEK 28/8 RPR SWTC | ICW
LC | 126284104 | ;009/003 | T2 DI CARIBOU-PLUMAS JCT ;9/3 RPR SPLW | TABLEMTN | ETL.6290.INSL.NCER | 2023-06-03 | 2023-05-25 | 2024-05-20 | On-time | 2024-05-24 | 4 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46073786 | T2 DI CARIBOU-PLUMAS JCT ;9/3 RPR SPLW | ICW
LC | 126284672 | A013/219 | T2 DI COLEMAN-RED BLUFF A13/219 RPR INSW | TABLEMTN | ETL.6440.INSL.NCER | 2023-06-03 | 2023-05-25 | 2024-04-03 | On-time | 2024-05-24 | 51 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46076615 | T2 DI COLEMAN-RED BLUFF A13/219 RPR INSW | ICW
LC | 126278197 | 074/001B | T2 EI HUMBOLDT-TRINITY 74/1B RPR JMPW | EUREKA | ETL.1820.INSL.CERA | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46096581 | T2 EI HUMBOLDT-TRINITY 74/1B RPR JMPW | ICW
LC | 126278348 | 023/444 | T2 DI HT CRK#1-WSTWD 23/444 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518529 | T2 DI HT CRK#1-WSTWD 23/444 RPL POLE | 70Y
LC | 126278591 | 047/000 | T2 DI TRNTY-MPL CRK 47/0 RPR CRSW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-02 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46172242 | T2 DI TRNTY-MPL CRK 47/0 RPR CRSW | ICW
LC | 126285141 | 009/172 | T2 DI CARIBOU-WESTWOOD 09/172 RPR ANCW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-03 | 2023-05-25 | 2023-08-07 | On-time | 2024-05-24 | 291 | 2023-11-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45847723 | T2 DI CARIBOU-WESTWOOD 09/172 RPR ANCW | ICW
LC | 126293951 | 029/005 | T2 DI TRNTY-MPL CREEK 29/5 RPR ANCW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-05 | 2023-05-25 | 2023-11-22 | On-time | 2024-05-24 | 184 | 2023-11-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45834366 | T2 DI TRNTY-MPL CREEK 29/5 RPR ANCW | ICW
LC | 126298945 | 000/009 | T2 DI CLGT-SMRTVL1 0/9L UNBURY | SACTO | ETL.6510.POLE.STPS | 2023-06-05 | 2023-05-25 | 2024-05-08 | On-time | 2024-05-24 | 16 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46079216 | T2 DI CLGT-SMRTVL1 0/9L UNBURY | ICW
LC | 126299656 | 000/009 | T2 DI CLGTE PLRMO 0/9L RPR GYWW | SACTO | ETL.6500.POLE.STPS | 2023-06-06 | 2023-05-25 | 2024-04-16 | On-time | 2024-05-24 | 38 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46063685 | T2 DI CLGTE PLRMO 0/9L RPR GYWW | ICW
LC | 126306536 | 017/347 | T2 DI CARIBOU-WESTWOOD 17/347 RPR GYWW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-06 | 2023-05-25 | 2024-03-19 | On-time | 2024-05-24 | 66 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073815 | T2 DI CARIBOU-WESTWOOD 17/347 RPR GYWW | ICW
LC | 126504485 | 021/454 | T2 KILARC-DESCHUTES 21/454 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-07-05 | 2023-05-25 | 2024-03-12 | On-time | 2024-05-24 | 73 | 2023-11-25 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31662469 | T2 KILARC-DESCHUTES 21/454 RPL STRW | 70Y
LC | 126279423 | 081/571 | T2 DI BRDGVLL-CTTNWD 081/571R RPL ANCW | EUREKA | ETL.1110.POLE.WDPS | 2023-06-02 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 637 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31652581 | T2 DI BRDGVLL-CTTNWD 081/571 RPL ANCW | 93E
LC | 126279426 | 081/571 | T2 DI BRDGVLL-CTTNWD 081/571L RPL ANCW | EUREKA | ETL.1110.POLE.WDPS | 2023-06-02 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 637 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31652581 | T2 DI BRDGVLL-CTTNWD 081/571 RPL ANCW | 93E
LC | 126279436 | 011/091 | T2 EI PIT #6 JCT-RND MNT 11/091 RPR INSS | TABLEMTN | ETL.5440.INSL.NCER | 2023-06-02 | 2023-06-02 | 2024-06-24 | Late | 2024-06-01 | -23 | 2024-06-02 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46076084 | T2 EI PIT #6 JCT-RND MNT 11/091 RPR INSS | ICS
LC | 126279450 | 006/080 | T2 DI DRUM-SUMMIT #1 6/80 RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2023-06-02 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126237097 | 017/356 | T2 WV KILARC-DESCHUTES 017/356 INS DMPW | TABLEMTN | ETL.7300.INSL.NCER | 2023-05-26 | 2023-05-26 | 2024-04-05 | On-time | 2024-05-25 | 50 | 2024-05-26 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46073821 | T2 WV KILARC-DESCHUTES 017/356 INS DMPW | ICW
LC | 126237402 | 018/383 | T2 WV KILARC-DESCHUTES 018/383 INS DMPW | TABLEMTN | ETL.7300.INSL.NCER | 2023-05-26 | 2023-05-26 | 2023-03-11 | On-time | 2024-05-25 | 441 | 2024-05-26 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46073822 | T2 WV KILARC-DESCHUTES 018/383 INS DMPW | ICW
LC | 126279729 | :001/011 | T2 EI FULTON-PUEBLO :01/11 RPL STRW | LAKEVLLE | ETL.1600.POLE.WOOD | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35541735 | T2 EI FULTON-PUEBLO :01/11 RPL STRW | 70Y
LC | 126279751 | 006/080 | T2 DI DRUM-SUMMIT #1 6/80 RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2023-06-02 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126280001 | 004/101 | T2 DI CARIBOU-PLUMAS JCT 04/101 RPR STRW | TABLEMTN | ETL.6290.POLE.NWOD | 2023-06-02 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46073787 | T2 DI CARIBOU-PLUMAS JCT 04/101 REGRADE | ICW
LC | 126280598 | 000/014 | T2 EI IGNACIO-BOLINAS #1 00/014 RPL STRW | LAKEVLLE | ETL.7140.POLE.WOOD | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526312 | T2 EI IGNACIO-BOLINAS #1 00/014 RPL STRW | 70Y
LC | 126280740 | 011/064 | T2 DI HAAS MCCALL 011/064 BNT STEEL | FRESNO | ETL.4850.TOWR | 2023-06-02 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46070854 | T2 DI HAAS MCCALL 011/064 BNT STEEL | ICQ
LC | 126238176 | 026/000 | T2 EI TRINITY-MAPLE CREEK 26/00 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-26 | 2023-05-26 | 2023-08-23 | On-time | 2024-05-25 | 276 | 2023-08-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45844363 | T2 EI TRINITY-MAPLE CREEK 26/00 RPR GYWW | ICW
LC | 126280796 | 044/863 | T2 EI HAT CRK #1-WESTWD 44/863 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518534 | T2 DI HT CRK#1-WSTWD 041/788 RPL STRW | 70Y
LC | 126280798 | 044/859 | T2 EI HAT CRK #1-WESTWD 44/859 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518534 | T2 DI HT CRK#1-WSTWD 041/788 RPL STRW | 70Y
LC | 126280811 | 044/858 | T2 EI HAT CRK #1-WSTWD 44/858 GO95 RPL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35529176 | T2 EI HAT CRK #1-WSTWD 44/858 GO95 | 93G
LC | 126280851 | 044/854 | T2 EI HAT CRK #1-WSTWD 44/854 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514324 | T2 EI HAT CRK #1-WSTWD 44/847 RPL STRW | 70Y
LC | 126280863 | 044/852 | T2 EI HAT CRK #1-WSTWD 44/852 RPR STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46076603 | T2 EI HAT CRK #1-WSTWD 44/852 RPR STRW | ICW
LC | 126280868 | 044/849 | T2 EI HAT CRK #1-WSTWD 44/849 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2023-12-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514324 | T2 EI HAT CRK #1-WSTWD 44/847 RPL STRW | 70Y
LC | 126280871 | 044/847 | T2 EI HAT CRK #1-WSTWD 44/847 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514324 | T2 EI HAT CRK #1-WSTWD 44/847 RPL STRW | 70Y
LC | 126281011 | 047/012 | T2 DI TRNTY-MPL CRK 47/12 RPR ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-02 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46172251 | T2 DI TRNTY-MPL CRK 47/12 RPR ANCW | ICW
LC | 126281013 | 047/012 | T2 DI TRNTY-MPL CRK 47/12 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-02 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172251 | T2 DI TRNTY-MPL CRK 47/12 RPR ANCW | ICW
LC | 126281037 | 033/634 | T2 DI HAT CRK#1 WSTWD 33/634 GO95 | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-25 | 2024-06-26 | Late | 2024-05-24 | -33 | 2024-05-25 | 401T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35524098 | T2 DI HAT CRK#1 WSTWD 33/634 GO95 | 93G
LC | 126238236 | 015/119 | T2 EI PIT #1-COTTONWOOD 15/119 COMPLETED | TABLEMTN | ETL.5390.TOWR | 2023-05-26 | 2023-05-26 | 2024-01-23 | On-time | 2024-05-25 | 123 | 2024-05-26 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46072206 | T2 EI PIT #1-COTTONWOOD 15/119 UNBURY | ICQ
LC | 126281513 | 028/009 | T2 DI TRNTY-MPL CREEK 028/009 RPR JMPW | EUREKA | ETL.8170.INSL.NCER | 2023-06-02 | 2023-05-25 |  | Late | 2024-05-24 |  | 2023-08-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46193439 | T2 DI TRNTY-MPL CREEK 028/009 RPR JMPW | ICW
LC | 126281714 | 047/011 | T2 DI TRNTY-MPL CRK 47/11 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-02 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172250 | T2 DI TRNTY-MPL CRK 47/11 RPR GYWW | ICW
LC | 126281831 | 020/390 | T2 EI HAT CRK #1-WESTWD 20/390 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 | 2024-06-18 | Late | 2024-06-01 | -17 | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514001 | T2 EI HAT CRK #1-WESTWD 020/390 RPL POLE | 70Y
LC | 126281832 | 021/417 | T2 EI HAT CREEK #1-WSTWD 21/417 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 | 2024-06-21 | Late | 2024-06-01 | -20 | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514006 | T2 EI HAT CREEK #1-WSTWD 21/416 RPL POLE | 70Y
LC | 126281834 | 020/392 | T2 EI HAT CRK #1-WESTWD 020/392 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 | 2024-06-18 | Late | 2024-06-01 | -17 | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514001 | T2 EI HAT CRK #1-WESTWD 020/390 RPL POLE | 70Y
LC | 126281836 | 021/414 | T2 EI HAT CREEK #1-WSTWD 21/414 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 | 2024-06-20 | Late | 2024-06-01 | -19 | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35514005 | T2 EI HAT CRK #1-WESTWOOD 21/405 RPL PL | 70Y
LC | 126281837 | 018/361 | T2 EI HAT CRK #1-WESTWD 018/361 RPR CRSW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 | 2024-06-15 | Late | 2024-06-01 | -14 | 2024-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46076600 | T2 EI HAT CRK #1-WESTWD 018/361 RPR CRSW | ICW
LC | 126281840 | 020/400 | T2 EI HAT CRK #1-WESTWD 20/400 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 | 2024-06-19 | Late | 2024-06-01 | -18 | 2024-06-02 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35514002 | T2 EI HAT CRK #1-WESTWD 20/400 REFRAME | 93E
LC | 126281842 | 021/416 | T2 EI HAT CREEK #1-WSTWD 21/416 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 | 2024-06-21 | Late | 2024-06-01 | -20 | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514006 | T2 EI HAT CREEK #1-WSTWD 21/416 RPL POLE | 70Y
LC | 126281858 | 020/394 | T2 EI HAT CRK #1-WESTWD 20/394 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 | 2024-06-18 | Late | 2024-06-01 | -17 | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514001 | T2 EI HAT CRK #1-WESTWD 020/390 RPL POLE | 70Y
LC | 126281865 | 021/415 | T2 EI HAT CREEK #1-WSTWD 21/415 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-06-02 | 2024-06-20 | Late | 2024-06-01 | -19 | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514005 | T2 EI HAT CRK #1-WESTWOOD 21/405 RPL PL | 70Y
LC | 126281868 | 038/001 | T2 DI TRNTY-MPL CRK 38/1 RPLC ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-02 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35506419 | T2 DI TRNTY-MPL CRK 38/1 RPLC ANCW | 93E
LC | 126281895 | 092/470B | T2 DI MALN RND MTN#2 92/470B RPL HRDT | TABLEMTN | ETL.6020.TOWR | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46075985 | T2 DI MALN RND MTN#2 92/470B RPL HRDT | ICQ
LC | 126238988 | 001/012 | T2 EI BALCH-SANGER 001/012 UNBURY | FRESNO | ETL.1050.TOWR | 2023-05-26 | 2023-05-26 | 2024-02-08 | On-time | 2024-05-25 | 107 | 2024-05-26 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46069689 | T2 EI BALCH-SANGER 001/012 UNBURY | ICQ
LC | 126282003 | 031/610 | T2 DI HAT CRK#1 WSTWD 31/610 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-25 | 2024-06-19 | Late | 2024-05-24 | -26 | 2024-05-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514160 | T2 DI HAT CRK#1 WSTWD 31/610 RPL POLE | 70Y
LC | 126282110 | 031/599 | T2 DI HAT CREEK#1 WESTWD 31/599 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-25 | 2024-06-23 | Late | 2024-05-24 | -30 | 2024-05-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514138 | T2 EI HAT CREEK #1-WESTWD 31/597 RPL PL | 70Y
LC | 126282219 | 029/568 | T2 DI HT CRK #1-WSTWD 29/568 GO95 RPL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-24 | 2024-06-25 | Late | 2024-05-23 | -33 | 2024-05-24 | 401T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35522533 | T2 DI HT CRK #1-WSTWD 29/568 GO95 | 93G
LC | 126239036 | 001/013 | T2 EI BALCH-SANGER 001/013 UNBURY | FRESNO | ETL.1050.TOWR | 2023-05-26 | 2023-05-26 | 2024-01-30 | On-time | 2024-05-25 | 116 | 2024-05-26 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46069690 | T2 EI BALCH-SANGER 001/013 UNBURY | ICQ
LC | 126283255 | 009/077 | T2 DI WDLEF PLRMO 09/077 RMV VEG | TABLEMTN | ETL.4220.POLE.STPS | 2023-06-03 | 2023-05-26 | 2024-03-14 | On-time | 2024-05-25 | 72 | 2024-05-26 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126283795 | 018/192C | T2 DI WDLEF PLRMO 18/192C RPR GYWW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-03 | 2023-05-26 | 2024-02-20 | On-time | 2024-05-25 | 95 | 2024-05-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076633 | T2 DI WDLEF PLRMO 18/192C RPR GYWW | ICW
LC | 126292228 | 008/075 | T2 DI WOODLEAF-PALERMO 8/75 COTTER | TABLEMTN | ETL.4220.INSL.CERA | 2023-06-05 | 2023-05-26 | 2023-06-23 | On-time | 2024-05-25 | 337 | 2023-08-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45847748 | T2 DI WOODLEAF-PALERMO 8/75 COTTER | ICW
LC | 126293441 | 012/117 | T2 DI WOODLEAF-PALERMO 12/117 COTTER | TABLEMTN | ETL.4220.INSL.NCER | 2023-06-05 | 2023-05-26 | 2023-06-23 | On-time | 2024-05-25 | 337 | 2023-08-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45847750 | T2 DI WOODLEAF-PALERMO 12/117 COTTER | ICW
LC | 126296241 | 006/055 | T2 DI WDLEAF PLRMO 06/055 COTTER | TABLEMTN | ETL.4220.INSL.CERA | 2023-06-05 | 2023-05-26 | 2023-06-23 | On-time | 2024-05-25 | 337 | 2023-08-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45847745 | T2 DI WDLEAF PLRMO 06/055 COTTER | ICW
LC | 126298306 | 015/159 | T2 DI WOODLEAF-PALERMO 15/159 COTTER | TABLEMTN | ETL.4220.INSL.CERA | 2023-06-05 | 2023-05-26 | 2023-06-23 | On-time | 2024-05-25 | 337 | 2023-08-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45847758 | T2 DI WOODLEAF-PALERMO 15/159 COTTER | ICW
LC | 126282385 | 032/000 | T2 EI TRINITY-MAPLE CREEK 32/0L RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504385 | T2 EI TRINITY-MAPLE CREEK 32/0C RPL POLE | 70Y
LC | 126298308 | 015/159 | T2 DI WOODLEAF-PALERMO 15/159 RPR GYWW | TABLEMTN | ETL.4220.POLE.NWOD | 2023-06-05 | 2023-05-26 | 2023-06-23 | On-time | 2024-05-25 | 337 | 2023-08-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45847756 | T2 DI WOODLEAF-PALERMO 15/159 RPR GYWW | ICW
LC | 126282393 | 032/000 | T2 EI TRINITY-MAPLE CREEK 32/0R RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504385 | T2 EI TRINITY-MAPLE CREEK 32/0C RPL POLE | 70Y
LC | 126282394 | 032/000 | T2 EI TRINITY-MAPLE CREEK 32/0C RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504385 | T2 EI TRINITY-MAPLE CREEK 32/0C RPL POLE | 70Y
LC | 126282395 | 031/005 | T2 EI TRINITY-MAPLE CRK 031/005 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504384 | T2 EI TRINITY-MAPLE CRK 031/005 RPL POLE | 70Y
LC | 126282401 | 031/607 | T2 DI HAT CREEK#1 WESTWD 31/607 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-25 | 2024-06-19 | Late | 2024-05-24 | -26 | 2024-05-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514139 | T2 EI HAT CRK #1-WSTWD 31/605 RPL STRW | 70Y
LC | 126282403 | 005/111 | T2 DI CRBOU WSTWD 05/111 RPL INSW | TABLEMTN | ETL.6300.INSL.CERA | 2023-06-02 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35519114 | T2 DI CRBOU WSTWD 05/111 RPL INSW | 93I
LC | 126282408 | 048/006 | T2 DI TRNTY MPL CRK 48/006 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-02 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506443 | T2 DI TRNTY MPL CRK 48/006 RPL STRW | 70Y
LC | 126298927 | 018/195 | T2 DI WOODLEAF-PALERMO 018/195 RPR POLE | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-05 | 2023-05-26 | 2024-02-20 | On-time | 2024-05-25 | 95 | 2024-05-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46076634 | T2 DI WOODLEAF-PALERMO 018/195 RPR POLE | ICW
LC | 126299690 | 016/167 | T2 DI WOODLEAF-PALERMO 016/167 RPR STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-06 | 2023-05-26 | 2024-02-20 | On-time | 2024-05-25 | 95 | 2024-05-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46076630 | T2 DI WOODLEAF-PALERMO 016/167 RPR STRW | ICW
LC | 126308472 | 017/178 | T2 DI WOODLEAF-PALERMO 17/178 RPR GYWW | TABLEMTN | ETL.4220.POLE.NWOD | 2023-06-07 | 2023-05-26 | 2024-02-20 | On-time | 2024-05-25 | 95 | 2024-05-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076631 | T2 DI WOODLEAF-PALERMO 17/178 RPR GYWW | ICW
LC | 126282447 | 035/679 | T2 DI HAT CRK #1-WSTWD 35/679 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514270 | T2 DI HAT CRK #1-WSTWD 35/679 RPL POLE | 70Y
LC | 126240658 | 001/008 | T2 LAURELES-OTTER 001/008 RPL POLE | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-05-27 | 2023-05-27 | 2024-01-31 | On-time | 2024-05-26 | 116 | 2024-05-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491360 | T2 LAURELES-OTTER 001/008 RPL POLE | 70Y
LC | 126244020 | 012/270 | T2 SALINAS-LAURELES 12/270 COTTER | MOSSLNDG | ETL.7930.INSL | 2023-05-30 | 2023-05-30 | 2023-08-21 | On-time | 2024-05-29 | 282 | 2023-08-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45812036 | T2 SALINAS-LAURELES 12/270 COTTER | ICW
LC | 126282515 | 015/304 | T2 DI CARIBOU-WESTWOOD 15/304 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-02 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519105 | T2 DI CARIBOU-WESTWOOD 15/304 RPL STRW | 70Y
LC | 126282525 | 022/002 | T2 EI TRINITY-MAPLE CREEK 22/2 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503527 | T2 EI TRINITY-MAPLE CREEK 22/2 RPL POLE | 70Y
LC | 126282528 | 021/406 | T2 DI HAT CRK #1-WSTWD 21/406 RPR CRSW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-24 | 2024-06-23 | Late | 2024-05-23 | -31 | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46076205 | T2 DI HAT CRK #1-WSTWD 21/406 RPR CRSW | ICW
LC | 126282552 | 004/101 | T2 DI CARIBOU#2 04/101 RPR STRW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-06-02 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46076236 | T2 DI CARIBOU#2 04/101 INS CORROCOTE | ICW
LC | 126244094 | 011/010 | T2 EI TRINITY-MAPLE CRK 11/010 RPR IBWW | EUREKA | ETL.8170.POLE.WOOD | 2023-05-30 | 2023-05-30 | 2024-02-17 | On-time | 2024-05-29 | 102 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46070815 | T2 EI TRINITY-MAPLE CRK 11/010 RPR IBWW | ICW
LC | 126282587 | 001/030 | T2 EI HAAS-WOODCHUCK 1/30 RPR ANCW | FRESNO | ETL.8730.POLE.WOOD | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46155740 | T2 EI HAAS-WOODCHUCK 1/30 RPR ANCW | ICW
LC | 126282589 | 001/034 | T2 EI HAAS-WOODCHUCK 1/34 RPR ANCW | FRESNO | ETL.8730.POLE.WOOD | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46155741 | T2 EI HAAS-WOODCHUCK 1/34 RPR ANCW | ICW
LC | 126282594 | 035/002 | T2 DI TRNTY-MPL CRK 35/2 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-02 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170572 | T2 DI TRNTY-MPL CRK 35/2 RPR GYWW | ICW
LC | 126282611 | 031/601 | T2 DI HAT CREEK#1 WESTWD 31/601 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-25 | 2024-06-24 | Late | 2024-05-24 | -31 | 2024-05-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514138 | T2 EI HAT CREEK #1-WESTWD 31/597 RPL PL | 70Y
LC | 126282616 | 029/564 | T2 DI HAT CRK #1-WSTWD 29/564 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-05-24 | 2024-06-19 | Late | 2024-05-23 | -27 | 2024-05-24 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35514132 | T2 DI HAT CRK #1-WSTWD 29/564 REFRAME | 93E
LC | 126282625 | 023/452 | T2 DI HT CRK #1-WSTWD 23/452 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514120 | T2 DI HAT CRK #1-WSTWOD 23/443 RPL POLE | 70Y
LC | 126244744 | 005/047 | T2 EI BRIDGEVILLE-COTTONWD 5/47 RPL DMPW | TABLEMTN | ETL.1110.INSL.NCER | 2023-05-30 | 2023-05-30 | 2023-12-02 | On-time | 2024-05-29 | 179 | 2024-05-30 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46073753 | T2 EI BRIDGEVILLE-COTTONWD 5/47 RPL DMPW | ICW
LC | 126282643 | 030/589 | T2 DI HT CRK #1-WSTWD 30/589 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-24 | 2024-06-22 | Late | 2024-05-23 | -30 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514136 | T2 DI HAT CRK #1-WSTWD 30/585 RPL PL | 70Y
LC | 126282661 | 002/044 | T2 EI HAAS-WOODCHUCK 2/44 RPR ANCW | FRESNO | ETL.8730.POLE.WOOD | 2023-06-02 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46155742 | T2 EI HAAS-WOODCHUCK 2/44 RPR ANCW | ICW
LC | 126245889 | 000/001B | T2 MTN GATE JCT-CASCADE 0/1B RPR SPLW | TABLEMTN | ETL.7640.POLE.WOOD | 2023-05-30 | 2023-05-30 | 2024-02-19 | On-time | 2024-05-29 | 100 | 2024-05-30 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46073748 | T2 MTN GATE JCT-CASCADE 0/1B RPR SPLW | ICW
LC | 126282672 | 028/541 | T2 DI HT CRK #1-WSTWD 28/541 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-24 | 2024-06-27 | Late | 2024-05-23 | -35 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514127 | T2 DI HT CRK #1-WSTWD 28/541 RPL STRW | 70Y
LC | 126282742 | A000/001 | T2 DI TRNTY-MPL CRK A00/01 RPR INSW | EUREKA | ETL.8170.INSL.NCER | 2023-06-02 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46070807 | T2 DI TRNTY-MPL CRK A00/01 RPR INSW | ICW
LC | 126282744 | A000/001 | T2 DI TRNTY-MPL CRK A00/01 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-02 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46070809 | T2 DI TRNTY-MPL CRK A00/01 RPR GYWW | ICW
LC | 126247166 | 003/036 | T2 EI BRIDGEVILLE-COTTONWD 2/28 RPL DMPW | TABLEMTN | ETL.1110.INSL.NCER | 2023-05-30 | 2023-05-30 | 2023-12-04 | On-time | 2024-05-29 | 177 | 2024-05-30 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46073751 | T2 EI BRIDGEVILLE-COTTONWD 2/28 RPL DMPW | ICW
LC | 126247233 | 034/006 | T2 EI FORT ROSS-GUALALA 034/006 RPR GYWW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-05-30 | 2023-05-30 | 2024-03-26 | On-time | 2024-05-29 | 64 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073735 | T2 EI FORT ROSS-GUALALA 034/006 RPR GYWW | ICW
LC | 126282779 | 030/577 | T2 DI HAT CRK #1-WSTWD 30/577 RPR GYWW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-02 | 2023-05-24 | 2024-06-17 | Late | 2024-05-23 | -25 | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076220 | T2 DI HAT CRK #1-WSTWD 30/577 RPR GYWW | ICW
LC | 126283093 | 047/004 | T2 DI TRNTY-MPL CRK 047/004 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-03 | 2023-05-24 | 2024-06-07 | Late | 2024-05-23 | -15 | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172245 | T2 DI TRNTY-MPL CRK 047/004 RPR GYWW | ICW
LC | 126283096 | 030/581 | T2 DI HAT CRK #1-WSTWD 30/581 COMPLETE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-05-24 | 2024-06-21 | Late | 2024-05-23 | -29 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514135 | T2 DI HAT CRK #1-WSTWD 30/579 RPL POLE | 70Y
LC | 126283119 | 010/083 | T2 DI WOODLEAF-PALERMO 010/83 RPL STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525818 | T2 DI WOODLEAF-PALERMO 010/83 RPL STRW | 70Y
LC | 126283154 | 015/156 | T2 DI WDLF-PALERMO 015/156 RPR STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46076628 | T2 DI WDLF-PALERMO 015/156 RPR STRW | ICW
LC | 126283159 | 011/101 | T2 DI WDLF-PALERMO 11/101L RPL STRW | TABLEMTN | ETL.4220.POLE.WDPS | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525903 | T2 DI WDLEF-PLRMO RPL 5 STRW | 70Y
LC | 126283160 | 011/101 | T2 DI WDLF-PALERMO 11/101R RPL STRW | TABLEMTN | ETL.4220.POLE.WDPS | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525903 | T2 DI WDLEF-PLRMO RPL 5 STRW | 70Y
LC | 126283193 | 008/099 | T2 DI DRUM SUMMIT#1 08/099 RPR INSW | SACTO | ETL.1440.INSL.NCER | 2023-06-03 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46101320 | T2 DI DRUM SUMMIT#1 08/099 RPR INSW | ICW
LC | 126283198 | 005/097 | T2 DI CARIBOU-WSTWD 5/97 RPR GYWW | TABLEMTN | ETL.6300.POLE.NWOD | 2023-06-03 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073808 | T2 DI CARIBOU-WSTWD 5/97 RPR GYWW | ICW
LC | 126283202 | 031/001 | T2 DI TRINITY-MAPLE CREEK 31/1L RPL ANCW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-03 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35504382 | T2 DI TRINITY-MAPLE CREEK 31/01 RPL ANCW | 93E
LC | 126283208 | 009/077 | T2 DI WDLEF PLRMO 9/77L RPR GYWW | TABLEMTN | ETL.4220.POLE.STPS | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076623 | T2 DI WDLEF PLRMO 09/077 RPR GYWW | ICW
LC | 126283211 | 030/593 | T2 DI HAT CREEK#1 WESTWD 30/593 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-05-24 | 2024-06-22 | Late | 2024-05-23 | -30 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514137 | T2 DI HT CRK #1-WESTWD 30/590 RPL POLE | 70Y
LC | 126283219 | 036/005 | T2 DI TRINITY-MAPLE CRK 36/05L RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-06-03 | 2023-05-24 |  | Late | 2024-05-23 |  | 2023-11-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170740 | T2 EI TRNTY-MPL CRK 036/005R RPR GYWW | ICW
LC | 126283220 | 009/077 | T2 DI WDLEF PLRMO 9/77R RPR GYWW | TABLEMTN | ETL.4220.POLE.STPS | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076624 | T2 DI WDLEF PLRMO 09/077 RPR GYWW | ICW
LC | 126247721 | 005/048 | T2 EI BRIDGEVILLE-COTTONWD 5/48 RPL DMPW | TABLEMTN | ETL.1110.INSL.NCER | 2023-05-30 | 2023-05-30 | 2023-12-02 | On-time | 2024-05-29 | 179 | 2024-05-30 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46073754 | T2 EI BRIDGEVILLE-COTTONWD 5/48 RPL DMPW | ICW
LC | 126283286 | 029/574 | T2 DI HAT CRK #1-WSTWD 29/574 GO95 RPL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-05-24 | 2024-06-25 | Late | 2024-05-23 | -33 | 2023-11-24 | 401T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35522533 | T2 DI HT CRK #1-WSTWD 29/568 GO95 | 93G
LC | 126283364 | 034/000 | T2 DI TRNTY MPL CRK 34/0R RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-06-03 | 2023-05-25 | 2024-06-13 | Late | 2024-05-24 | -20 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172098 | T2 EI TRINTY-MPLE CRK 34/0C RPR GYWW | ICW
LC | 126249731 | 011/003 | T2 EI TRINITY-MAPLE CRK 11/003 RPR CNDW | EUREKA | ETL.8170.INSL.CERA | 2023-05-30 | 2023-05-30 | 2024-02-22 | On-time | 2024-05-29 | 97 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46070814 | T2 EI TRINITY-MAPLE CRK 11/003 RPR CNDW | ICW
LC | 126283421 | 034/000 | T2 DI TRNTY MPL CRK 34/0 RPR INSW | EUREKA | ETL.8170.INSL.NCER | 2023-06-03 | 2023-05-25 | 2024-06-13 | Late | 2024-05-24 | -20 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46172098 | T2 EI TRINTY-MPLE CRK 34/0C RPR GYWW | ICW
LC | 126283424 | 034/000 | T2 DI TRNTY MPL CRK 34/0R RMV VEG | EUREKA | ETL.8170.POLE.STPS | 2023-06-03 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126283449 | 030/585 | T2 DI HAT CRK #1-WSTWD 30/585 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-05-24 | 2024-06-21 | Late | 2024-05-23 | -29 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514136 | T2 DI HAT CRK #1-WSTWD 30/585 RPL PL | 70Y
LC | 126283477 | 034/000 | T2 DI TRNTY MPL CRK 34/0L RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-06-03 | 2023-05-25 | 2024-06-13 | Late | 2024-05-24 | -20 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172098 | T2 EI TRINTY-MPLE CRK 34/0C RPR GYWW | ICW
LC | 126283521 | 018/192A | T2 DI WDLEF PLRMO 18/192A RPL INSW | TABLEMTN | ETL.4220.INSL | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35523389 | T2 DI WOODLEAF-PALERMO 018/192B RPL INSW | 93I
LC | 126283527 | 018/192B | T2 DI WOODLEAF-PALERMO 18/192B RPL INSW | TABLEMTN | ETL.4220.INSL.NCER | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35523389 | T2 DI WOODLEAF-PALERMO 018/192B RPL INSW | 93I
LC | 126283600 | 052/1023 | T2 DI HAT CRK #1-WSTWD 52/1023 RPR STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46076233 | T2 DI HAT CRK #1-WSTWD 52/1023 RPR STRW | ICW
LC | 126249785 | ;000/012 | T2 DI CARIBOU #2 ;000/012 RPR JMPW | TABLEMTN | ETL.6280.INSL.CERA | 2023-05-30 | 2023-05-30 | 2023-07-26 | On-time | 2024-05-29 | 308 | 2023-08-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45857970 | T2 DI CARIBOU #2 ;000/012 RPR JMPW | ICW
LC | 126250503 | 006/005 | T2 HUMBOLDT-MAPLE CREEK 6/5 GO95 | EUREKA | ETL.7130.POLE.WOOD | 2023-05-30 | 2023-05-30 | 2024-05-21 | On-time | 2024-05-29 | 8 | 2024-05-30 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31651475 | T2 HUMBOLDT-MAPLE CREEK 6/5 GO95 | 93G
LC | 126250625 | 020/161 | T2 EI PARADISE-TBL MTN 20/161L RPR GYWW | TABLEMTN | ETL.4316.POLE.STPS | 2023-05-30 | 2023-05-30 | 2024-01-26 | On-time | 2024-05-29 | 124 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073823 | T2 EI PARADISE-TBL MTN 20/161L RPR GYWW | ICW
LC | 126250800 | 020/161 | T2 EI PARADISE-TBL MTN 20/161C RPR GYWW | TABLEMTN | ETL.4316.POLE.STPS | 2023-05-30 | 2023-05-30 | 2024-01-26 | On-time | 2024-05-29 | 124 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076636 | T2 EI PARADISE-TBL MTN 20/161C RPR GYWW | ICW
LC | 126283793 | 018/192C | T2 DI WDLEF PLRMO 18/192C RPL INSW | TABLEMTN | ETL.4220.INSL.NCER | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35523389 | T2 DI WOODLEAF-PALERMO 018/192B RPL INSW | 93I
LC | 126283794 | 009/167 | T2 DI CARIBOU-WESTWOOD 9/167 RPR INSW | TABLEMTN | ETL.6300.INSL.NCER | 2023-06-03 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46073812 | T2 DI CARIBOU-WESTWOOD 09/167 RPL INSW | ICW
LC | 126250943 | 020/164 | T2 EI PARADISE-TBL MTN 20/164 RPR WDPKR | TABLEMTN | ETL.4316.POLE.WOOD | 2023-05-30 | 2023-05-30 | 2024-01-25 | On-time | 2024-05-29 | 125 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46076638 | T2 EI PARADISE-TBL MTN 20/164 RPR WDPKR | ICW
LC | 126283822 | 030/210 | T2 EI TRINITY-COTTONWD 30/210R RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46075857 | T2 EI TRINITY-COTTONWD 30/210R RPR GYWW | ICS
LC | 126283826 | 025/496 | T2 DI HAT CRK #1-WSTWD 25/496 RPL ANCW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35514121 | T2 DI HAT CRK #1-WSTWD 25/496 RPL ANCW | 93E
LC | 126250944 | 020/164 | T2 EI PARADISE-TBL MTN 20/164 RPR IBWW | TABLEMTN | ETL.4316.POLE.WOOD | 2023-05-30 | 2023-05-30 | 2024-01-25 | On-time | 2024-05-29 | 125 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46076639 | T2 EI PARADISE-TBL MTN 20/164 RPR IBWW | ICW
LC | 126250946 | 020/161 | T2 EI PARADISE-TBL MTN 20/161R RPR GYWW | TABLEMTN | ETL.4316.POLE.STPS | 2023-05-30 | 2023-05-30 | 2024-01-26 | On-time | 2024-05-29 | 124 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076637 | T2 EI PARADISE-TBL MTN 20/161R RPR GYWW | ICW
LC | 126284089 | 029/007 | T2 DI TRINITY-MAPLE CREEK 29/7L RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-06-03 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46265474 | T2 DI TRINITY-MAPLE CREEK 29/7L RPR GYWW | ICW
LC | 126284096 | 030/210 | T2 EI TRINITY-COTTONWD 30/210L RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46075856 | T2 EI TRINITY-COTTONWD 30/210L RPR GYWW | ICS
LC | 126284100 | 005/051 | T2 DI WDLEF PLRMO 5/51L RPR GYWW | TABLEMTN | ETL.4220.POLE.WDPS | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2023-11-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073745 | T2 DI WDLEF PLRMO 05/051 RPR GYWW | ICW
LC | 126284101 | 029/007 | T2 DI TRINITY-MAPLE CREEK 29/7C RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-06-03 | 2023-05-25 | 2024-06-15 | Late | 2024-05-24 | -22 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172087 | T2 DI TRINITY-MAPLE CREEK 29/7L RPR GYWW | ICW
LC | 126284103 | 005/051 | T2 DI WDLEF PLRMO 5/51R RPR GYWW | TABLEMTN | ETL.4220.POLE.WDPS | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2023-11-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073746 | T2 DI WDLEF PLRMO 05/051 RPR GYWW | ICW
LC | 126251410 | 078/002A | T2 EI HUMBOLDT-TRINITY 78/02A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-30 | 2023-05-30 | 2024-05-14 | On-time | 2024-05-29 | 15 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096588 | T2 EI HUMBOLDT-TRINITY 78/02A RPR GYWW | ICW
LC | 126284139 | 010/338 | T2 EI SPLDING-SMMIT 10/338 RPL INSW | SACTO | ETL.8060.INSL.NCER | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35508782 | T2 EI SPLDING-SMMIT 10/338 RPL INSW | 93I
LC | 126284492 | 030/182 | T2 HELMS-GREGG #1 030/182 RMV NEST | FRESNO | ETL.4870.TOWR | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46080577 | T2 HELMS-GREGG #1 030/182 RMV NEST | ICS
LC | 126284493 | 010/117 | T2 DI DRUM-SUMMIT#2 10/117L RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2023-06-03 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484103 | T2 EI DRUM-SUMMIT #2_010/117C RPL POLE | 70Y
LC | 126284497 | 010/117 | T2 DI DRUM-SUMMIT#2 10/117R RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2023-06-03 | 2023-05-22 |  | Late | 2024-05-21 |  | 2024-05-22 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484103 | T2 EI DRUM-SUMMIT #2_010/117C RPL POLE | 70Y
LC | 126284664 | 030/591 | T2 DI HAT CREEK#1 WESTWD 30/591 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-05-24 | 2024-06-22 | Late | 2024-05-23 | -30 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514137 | T2 DI HT CRK #1-WESTWD 30/590 RPL POLE | 70Y
LC | 126251412 | 078/002C | T2 EI HUMBOLDT-TRINITY 78/02C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-30 | 2023-05-30 | 2024-05-14 | On-time | 2024-05-29 | 15 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096588 | T2 EI HUMBOLDT-TRINITY 78/02A RPR GYWW | ICW
LC | 126284794 | 006/034 | T2 DI FULTON PUEBLO 6/34 RPR STRT | LAKEVLLE | ETL.1600.TOWR | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46204143 | T2 DI FULTON PUEBLO 06/034 RPR STRT | ICQ
LC | 126284833 | 006/034 | T2 DI FULTON PUEBLO 6/34 CANCEL | LAKEVLLE | ETL.1600.TOWR | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46102301 | T2 DI FULTON PUEBLO 06/034 RPL HRDT | ICQ
LC | 126284835 | 001/028 | T2 DI CARIBOU-WSWD 1/28L RPR GYWW | TABLEMTN | ETL.6300.POLE.STPS | 2023-06-03 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073802 | T2 DI CARIBOU-WSWD 001/028L RPR GYWW | ICW
LC | 126284838 | 001/028 | T2 DI CARIBOU-WSWD 1/28R RPR GYWW | TABLEMTN | ETL.6300.POLE.STPS | 2023-06-03 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073803 | T2 DI CARIBOU-WSWD 001/028 RPR GYWW | ICW
LC | 126285049 | 005/045 | T2 DI WDLF-PALERMO 005/045 RPR INSW | TABLEMTN | ETL.4220.INSL.CERA | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46073743 | T2 DI WDLF-PALERMO 005/045 RPR INSW | ICW
LC | 126251414 | 078/002B | T2 EI HUMBOLDT-TRINITY 78/02B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-30 | 2023-05-30 | 2024-05-14 | On-time | 2024-05-29 | 15 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096588 | T2 EI HUMBOLDT-TRINITY 78/02A RPR GYWW | ICW
LC | 126251415 | 078/001C | T2 EI HUMBOLDT-TRINITY 78/01C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-05-30 | 2023-05-30 | 2024-05-29 | On-time | 2024-05-29 | 0 | 2024-05-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096589 | T2 EI HUMBOLDT-TRINITY 78/01C RPR GYWW | ICW
LC | 126285273 | 018/193 | T2 DI WOODLEAF-PALERMO 018/193R RPL POLE | TABLEMTN | ETL.4220.POLE.WDPS | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525903 | T2 DI WDLEF-PLRMO RPL 5 STRW | 70Y
LC | 126285275 | 018/193 | T2 DI WOODLEAF-PALERMO 018/193L RPL POLE | TABLEMTN | ETL.4220.POLE.WDPS | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525903 | T2 DI WDLEF-PLRMO RPL 5 STRW | 70Y
LC | 126285285 | 004/100 | T2 DI CARIBOU #2 4/100 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-06-03 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073783 | T2 DI CARIBOU #2 4/100 RPR GYWW | ICW
LC | 126285288 | 033/640 | T2 DI HT CRK #1-WSTWD 33/640 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514209 | T2 EI HAT CRK #1-WESTWD 33/633 RPL PL | 70Y
LC | 126285380 | 047/001 | T2 DI TRNTY-MPL CRK 47/1 RPL HRDD | EUREKA | ETL.8170.POLE.WOOD | 2023-06-03 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46172244 | T2 DI TRNTY-MPL CRK 47/1 RPL HRDD | ICW
LC | 126285384 | 047/001 | T2 DI TRNTY-MPL CRK 47/01 REFRAME | EUREKA | ETL.8170.POLE.WOOD | 2023-06-03 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35506439 | T2 DI TRNTY-MPL CRK 47/01 REFRAME | 93E
LC | 126285406 | 034/003 | T2 DI TRNTY MPL CRK 34/003 UNBURY | EUREKA | ETL.8170.POLE.WOOD | 2023-06-03 | 2023-05-25 | 2024-05-31 | Late | 2024-05-24 | -7 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46171892 | T2 DI TRNTY MPL CRK 34/003 UNBURY | ICW
LC | 126285409 | 034/003 | T2 DI TRNTY MPL CRK 34/003 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-03 | 2023-05-25 | 2024-05-31 | Late | 2024-05-24 | -7 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171892 | T2 DI TRNTY MPL CRK 34/003 UNBURY | ICW
LC | 126252136 | 052/003 | T2 ELK-GUALALA 52/003 GO95 | WILLITS | ETL.8410.POLE.WOOD | 2023-05-30 | 2023-05-30 | 2023-08-30 | On-time | 2024-05-29 | 273 | 2024-05-30 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31651472 | T2 ELK-GUALALA 52/003 GO95 | 93G
LC | 126252139 | 000/001 | T2 EI BALCH-SANGER 000/001 UNBURY | FRESNO | ETL.1050.TOWR | 2023-05-30 | 2023-05-30 | 2024-01-29 | On-time | 2024-05-29 | 121 | 2024-05-30 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46069495 | T2 EI BALCH-SANGER 000/001 UNBURY | ICQ
LC | 126285688 | 034/234 | T2 EI TRINITY-COTTONWD 34/234L RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46075858 | T2 EI TRINITY-COTTONWD 34/234L RPR GYWW | ICS
LC | 126285689 | 034/234 | T2 EI TRINITY-COTTONWD 34/234C RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46075859 | T2 EI TRINITY-COTTONWD 34/234C RPR GYWW | ICS
LC | 126285691 | 034/234 | T2 EI TRINITY-COTTONWD 34/234R RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076080 | T2 EI TRINITY-COTTONWD 34/234R RPR GYWW | ICS
LC | 126285701 | 039/001 | T2 DI TRNTY-MPL CRK 39/01 RPR JMPW | EUREKA | ETL.8170.INSL.NCER | 2023-06-03 | 2023-05-24 |  | Late | 2024-05-23 |  | 2023-08-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46190014 | T2 DI TRNTY-MPL CRK 39/01 RPR JMPW | ICW
LC | 126285707 | 039/001 | T2 DI TRNTY-MPL CRK 39/1 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-03 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506723 | T2 DI TRNTY-MPL CRK 39/01 RPL POLE | 70Y
LC | 126285708 | 026/001 | T2 DI TRNTY-MAPLE CREEK 26/1 RPR INSW | EUREKA | ETL.8170.INSL.CERA | 2023-06-03 | 2023-05-25 | 2024-06-24 | Late | 2024-05-24 | -31 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46170564 | T2 DI TRNTY-MAPLE CREEK 26/1 RPR INSW | ICW
LC | 126252268 | 007/135 | T2 VALLEY SPRINGS #1 7/135 GO95 | VICTOR | ETL.8210.POLE.WOOD | 2023-05-30 | 2023-05-30 | 2024-03-25 | On-time | 2024-05-29 | 65 | 2024-05-30 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31651706 | T2 VALLEY SPRINGS #1 7/135 GO95 | 93G
LC | 126285896 | 000/002 | T2 DI FITCH MOUNTA #1 TAP 0/2 REFRAME | LAKEVLLE | ETL.6891.POLE.NWOD | 2023-06-03 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35488082 | T2 DI FITCH MOUNTA #1 TAP 00/02 REFRAME | 93E
LC | 126285995 | 011/100 | T2 DI WDLEF-PLRMO 11/100 RPL STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525903 | T2 DI WDLEF-PLRMO RPL 5 STRW | 70Y
LC | 126286021 | 030/000 | T2 DI TRNTY-MPL CRK 30/00R RPR ANCHW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-03 | 2023-05-25 | 2024-06-15 | Late | 2024-05-24 | -22 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46172088 | T2 DI TRNTY-MPL CRK 30/00R UNBURY | ICW
LC | 126286024 | 030/000 | T2 DI TRNTY-MPL CRK 30/00 RPR JMPRW | EUREKA | ETL.8170.INSL.NCER | 2023-06-03 | 2023-05-25 |  | Late | 2024-05-24 |  | 2023-08-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46193761 | T2 DI TRNTY-MPL CRK 30/00 RPR JMPRW | ICW
LC | 126286027 | 030/000 | T2 DI TRNTY-MPL CRK 30/00C RPL HRDD | EUREKA | ETL.8170.POLE.WDPS | 2023-06-03 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46172088 | T2 DI TRNTY-MPL CRK 30/00R UNBURY | ICW
LC | 126286125 | 034/001 | T2 DI TRNTY-MPL CRK 34/1 UNBURY | EUREKA | ETL.8170.POLE.NWOD | 2023-06-03 | 2023-05-25 | 2024-05-31 | Late | 2024-05-24 | -7 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46172099 | T2 DI TRNTY-MPL CRK 34/1 UNBURY | ICW
LC | 126286126 | 034/001 | T2 DI TRNTY-MPL CRK 34/1 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-03 | 2023-05-25 | 2024-05-31 | Late | 2024-05-24 | -7 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172099 | T2 DI TRNTY-MPL CRK 34/1 UNBURY | ICW
LC | 126286163 | 006/058 | T2 DI WDLEF PLRMO 06/058 RPL INSW | TABLEMTN | ETL.4220.INSL | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35525814 | T2 DI WDLEF PLRMO 06/058 RPL INSW | 93I
LC | 126252323 | 063/010 | T2 ELK-GUALALA 63/010 GO95 | WILLITS | ETL.8410.POLE.WOOD | 2023-05-30 | 2023-05-30 | 2023-09-06 | On-time | 2024-05-29 | 266 | 2023-11-30 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31651473 | T2 ELK-GUALALA 60/011 GO95 | 93G
LC | 126286262 | 018/188 | T2 DI WOODLEAF-PALERMO 018/188 RPR CNDW | TABLEMTN | ETL.4220.INSL.NCER | 2023-06-03 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46076632 | T2 DI WOODLEAF-PALERMO 018/188 RPR CNDW | ICW
LC | 126286302 | 022/006 | T2 EI TRINITY-MAPLE CREEK 22/6 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503528 | T2 EI TRINITY-MAPLE CREEK 22/6 RPL POLE | 70Y
LC | 126286786 | 028/202B | T2 EI CARIBOU-TABLE MTN 28/202B RPL INSS | TABLEMTN | ETL.4440.INSL.NCER | 2023-06-03 | 2023-06-03 | 2024-06-06 | Late | 2024-06-02 | -4 | 2024-06-03 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35508877 | T2 EI CARIBOU-TABLE MTN RPL INSS 12 STRT | 93K
LC | 126286810 | 002/048 | T2 EI HAAS-WOODCHUCK 2/48 COTTER | FRESNO | ETL.8730.POLE.WOOD | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46155743 | T2 EI HAAS-WOODCHUCK 002/048 COTTER | ICW
LC | 126286811 | 002/056 | T2 EI HAAS-WOODCHUCK 2/56 RMV IDLE | FRESNO | ETL.8730.POLE.WOOD | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 673T | TLM | INSP | E - Schd Compl Yr 0 | Open | TR2 | Idle | Structure-Wood | Remove | 35543487 | T2 EI HAAS-WOODCHUCK 2/56 RMV IDLE | 93J
LC | 126286812 | 002/054 | T2 EI HAAS-WOODCHUCK 002/054 RPR GYWW | FRESNO | ETL.8730.POLE.WOOD | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2023-12-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46155744 | T2 EI HAAS-WOODCHUCK 002/054 RPR GYWW | ICW
LC | 126286815 | 003/058 | T2 EI HAAS-WOODCHUCK 003/058 RPR GYWW | FRESNO | ETL.8730.POLE.WOOD | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2023-12-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46155745 | T2 EI HAAS-WOODCHUCK 003/058 RPR GYWW | ICW
LC | 126286874 | 028/202A | T2 EI CARIBOU-TABLE MTN 28/202A RPL INSS | TABLEMTN | ETL.4440.INSL | 2023-06-03 | 2023-06-03 | 2024-06-06 | Late | 2024-06-02 | -4 | 2024-06-03 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35508877 | T2 EI CARIBOU-TABLE MTN RPL INSS 12 STRT | 93K
LC | 126286946 | 022/422 | T2 EI HAT CREEK #1-WSTWD 22/422 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-06-03 | 2024-06-18 | Late | 2024-06-02 | -16 | 2024-06-03 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514008 | T2 EI HAT CREEK #1-WSTWD 21/420 RPL POLE | 70Y
LC | 126287041 | 021/419 | T2 EI HAT CREEK #1-WSTWD 21/419 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514006 | T2 EI HAT CREEK #1-WSTWD 21/416 RPL POLE | 70Y
LC | 126287042 | 021/420 | T2 EI HAT CREEK #1-WSTWD 21/420 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-06-03 | 2024-06-22 | Late | 2024-06-02 | -20 | 2024-06-03 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514008 | T2 EI HAT CREEK #1-WSTWD 21/420 RPL POLE | 70Y
LC | 126287044 | 022/423 | T2 EI HAT CRK #1-WSTWD 22/423 RPR GYWW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-06-03 | 2024-06-18 | Late | 2024-06-02 | -16 | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076608 | T2 EI HAT CRK #1-WSTWD 22/423 RPR GYWW | ICW
LC | 126287063 | 022/427 | T2 EI HAT CRK #1-WESTWD 22/427 RPL HRDW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-06-03 | 2024-06-18 | Late | 2024-06-02 | -16 | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46251999 | T2 EI HAT CRK #1-WESTWD 22/427 RPR HRDD | ICW
LC | 126287067 | 022/432 | T2 EI HAT CRK #1-WSTWD 22/432 COMPELTE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2023-12-03 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35514075 | T2 EI HAT CRK #1-WSTWD 22/432 REFRAME | 93E
LC | 126287068 | 022/430 | T2 EI HAT CREEK #1-WSTWD 22/430 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514010 | T2 DI HAT CREEK#1-WESTWD 22/428 RPL POLE | 70Y
LC | 126287088 | 022/433 | T2 EI HAT CRK #1-WSTWD 22/433 COMPELTE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35524389 | T2 EI HAT CRK #1-WSTWD 22/433 GO95 | 93G
LC | 126287102 | 022/435 | T2 EI HAT CRK #1-WSTWD 22/435 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-03 | 2023-06-03 | 2024-06-23 | Late | 2024-06-02 | -21 | 2024-06-03 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35514079 | T2 EI HAT CRK #1-WSTWD 22/435 RPL POLE | 70Y
LC | 126252345 | 000/003 | T2 EI BALCH-SANGER 000/003 UNBURY | FRESNO | ETL.1050.TOWR | 2023-05-30 | 2023-05-30 | 2024-01-29 | On-time | 2024-05-29 | 121 | 2024-05-30 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46069687 | T2 EI BALCH-SANGER 000/003 UNBURY | ICQ
LC | 126252352 | 060/011 | T2 ELK-GUALALA 60/011 GO95 | WILLITS | ETL.8410.POLE.WOOD | 2023-05-30 | 2023-05-30 | 2023-09-06 | On-time | 2024-05-29 | 266 | 2023-11-30 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31651473 | T2 ELK-GUALALA 60/011 GO95 | 93G
LC | 126298667 | 011/103-GUY | T2 DI WDLF-PLRMO 11/103G RPR ANCW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-05 | 2023-05-30 | 2024-02-19 | On-time | 2024-05-29 | 100 | 2024-05-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46076635 | T2 DI WDLF-PLRMO 11/103G RPR ANCW | ICW
LC | 126298861 | 010/081C | T2 DI CARIBOU-TABLE MNTN 10/81C RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-05 | 2023-05-30 | 2024-01-24 | On-time | 2024-05-29 | 126 | 2024-05-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46073789 | T2 DI CARIBOU-TABLE MNTN 10/81C RPR GYWS | ICS
LC | 126287212 | 029/005 | T2 EI TRINITY-MAPLE CRK 29/005 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-03 | 2023-06-03 | 2024-06-15 | Late | 2024-06-02 | -13 | 2023-12-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172086 | T2 EI TRINITY-MAPLE CRK 29/005 RPR GYWW | ICW
LC | 126298914 | 009/075 | T2 DI PRDS-TBL MTN 009/075 RPL INSS | TABLEMTN | ETL.4316.INSL.NCER | 2023-06-05 | 2023-05-30 | 2024-01-30 | On-time | 2024-05-29 | 120 | 2024-05-30 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672700 | T2 EI PARADISE-TABLE MTN 11/093 RPL INSW | 93K
LC | 126298970 | 021/145B | T2 DI CARIBOU-TABLE MTN 21/145B RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-05 | 2023-05-30 | 2024-04-16 | On-time | 2024-05-29 | 43 | 2024-05-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46073793 | T2 DI CARIBOU-TABLE MTN 21/145B RPR GYWS | ICS
LC | 126287779 | 071/002B | T2 EI HUMBOLDT-TRINITY 71/2BL RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-04 | 2023-06-03 |  | Late | 2024-06-02 |  | 2023-12-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45881351 | T2 EI HUMBOLDT-TRINITY 71/2BL RPR GYWW | ICW
LC | 126299021 | 021/146C | T2 DI CARIBOU-TABLE MNT 21/146C RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-05 | 2023-05-30 | 2024-04-16 | On-time | 2024-05-29 | 43 | 2024-05-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46073795 | T2 DI CARIBOU-TABLE MNT 21/146C RPR GYWS | ICS
LC | 126299584 | 021/146A | T2 DI CARIBOU-TABLE MTN 21/146A RPR ANCS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-06 | 2023-05-30 | 2023-06-15 | On-time | 2024-05-29 | 349 | 2023-11-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45847799 | T2 DI CARIBOU-TABLE MTN 21/146A RPR ANCS | ICS
LC | 126299585 | 021/146A | T2 DI CARIBOU-TABLE MTN 21/146A RPR GYWT | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-06 | 2023-05-30 | 2024-04-16 | On-time | 2024-05-29 | 43 | 2024-05-30 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46193824 | T2 DI CARIBOU-TABLE MTN 21/146A RPR GYWT | ICQ
LC | 126299885 | 021/145A | T2 DI CARIBOU-TBL MTN 21/145A RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-06 | 2023-05-30 | 2024-04-16 | On-time | 2024-05-29 | 43 | 2024-05-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46073792 | T2 DI CARIBOU-TBL MTN 21/145A RPR GYWS | ICS
LC | 126299958 | 021/146B | T2 DI CARIBOU-TABLE MTN 21/146B RPR GYWT | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-06 | 2023-05-30 | 2024-04-16 | On-time | 2024-05-29 | 43 | 2024-05-30 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46193825 | T2 DI CARIBOU-TABLE MTN 21/146B RPR GYWT | ICQ
LC | 126289001 | 063/458 | T2 EI BRDGEVLE-COTTNWD 63/458 RPR INSS | EUREKA | ETL.1110.INSL.NCER | 2023-06-04 | 2023-06-04 |  | Late | 2024-06-03 |  | 2024-06-04 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46210881 | T2 EI BRDGEVLE-COTTNWD 63/458 RPR INSS | ICS
LC | 126306079 | 014/297 | T2 DI VLTA-DSCHTS 14/297 RMV DEBRIS | TABLEMTN | ETL.8290.POLE.NWOD | 2023-06-06 | 2023-05-30 | 2024-01-16 | On-time | 2024-05-29 | 134 | 2024-05-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 46059571 | T2 DI VLTA-DSCHTS 14/297 RMV DEBRIS | ICW
LC | 126292086 | 029/003 | T2 DI TRNTY MPL CRK 29/003 RPL HRDD | EUREKA | ETL.8170.POLE.WOOD | 2023-06-05 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46172084 | T2 DI TRNTY MPL CRK 29/003 RPL HRDD | ICW
LC | 126292088 | 029/003 | T2 DI TRNTY MPL CRK 29/003 RMV VEG | EUREKA | ETL.8170.POLE.WOOD | 2023-06-05 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126306191 | 021/145C | T2 DI CRIBU-TBLE MTN 21/145C RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-06 | 2023-05-30 | 2024-04-16 | On-time | 2024-05-29 | 43 | 2024-05-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46073794 | T2 DI CRIBU-TBLE MTN 21/145C RPR GYWS | ICS
LC | 126292300 | 032/620 | T2 DI HAT CREEK #1-WSTWD 32/620 RPL PL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-05 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514162 | T2 EI HAT CRK #1-WESTWOOD 32/619 RPL PL | 70Y
LC | 126292433 | 032/616 | T2 DI HAT CREEK#1 WSTWD 32/616 COMPLETE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-05 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514161 | T2 DI HAT CREEK#1 WSTWD 32/616 RPL POLE | 70Y
LC | 126292436 | 020/543 | T2 DI CARIBOU#2 20/543 RMV VEG | TABLEMTN | ETL.6280.POLE.NWOD | 2023-06-05 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126292452 | 011/108 | T2 DI WOODLEAF-PALERMO 11/108 RPL STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-05 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525944 | T2 DI WOODLEAF-PALERMO 11/108 RPL STRW | 70Y
LC | 126292459 | 010/198 | T2 DI CTRVL-TBL MTN-ORVL 10/198 RPR STRW | TABLEMTN | ETL.6330.POLE.WOOD | 2023-06-05 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46073750 | T2 DI CTRVL-TBL MTN-ORVL 10/198 RPR STRW | ICW
LC | 126306352 | 024/182 | T2 DI PARDIS-TBL MTN 24/182R RPR GYWW | TABLEMTN | ETL.4316.POLE.STPS | 2023-06-06 | 2023-05-30 | 2024-01-25 | On-time | 2024-05-29 | 125 | 2024-05-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076660 | T2 DI PARDIS-TBL MTN 24/182R RPR GYWW | ICW
LC | 126292820 | 010/198 | T2 DI CTRVL-TBL MTN-ORVL 10/198 RPR INSW | TABLEMTN | ETL.6330.INSL.NCER | 2023-06-05 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46073749 | T2 DI CTRVL-TBL MTN-ORVL 10/198 RPL HRDD | ICW
LC | 126306353 | 024/182 | T2 DI PARDIS-TBL MTN 24/182L RPR GYWW | TABLEMTN | ETL.4316.POLE.STPS | 2023-06-06 | 2023-05-30 | 2024-01-25 | On-time | 2024-05-29 | 125 | 2024-05-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076662 | T2 DI PARDIS-TBL MTN 24/182L RPR GYWW | ICW
LC | 126306394 | 040/005 | T2 DI ELK GUALALA 40/5 RPL SPLW | WILLITS | ETL.8410.INSL.NCER | 2023-06-06 | 2023-05-30 | 2024-01-09 | On-time | 2024-05-29 | 141 | 2024-05-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Replace | 46070984 | T2 DI ELK GUALALA 40/5 RPL SPLW | ICW
LC | 126306687 | 007/088A | T2 DI DRM-SMMT #1 007/088A RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-06 | 2023-05-30 | 2024-05-16 | On-time | 2024-05-29 | 13 | 2024-05-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101329 | T2 DI DRM-SMMT #1 007/088A RPR GYWW | ICW
LC | 126294011 | 010/091 | T2 DI WOODLEAF-PALERMO 10/91 RPL POLE | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-05 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525900 | T2 DI WOODLEAF-PALERMO 10/91 RPL POLE | 70Y
LC | 126294207 | 014/285 | T2 DI CARIBOU-WESTWOOD 014/285 RPL POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-05 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519120 | T2 DI CARIBOU-WESTWOOD 014/285 RPL POLE | 70Y
LC | 126308351 | 010/050 | T2 DI CORTINA-MENDCNO #1 10/50 RPR OPGW | SACTO | ETL.1330.TOWR | 2023-06-07 | 2023-05-30 | 2023-08-14 | On-time | 2024-05-29 | 289 | 2023-08-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45845933 | T2 DI CORTINA-MENDCNO #1 10/50 RPR OPGW | ICS
LC | 126311976 | 022/105 | T2 DI CRTNA MNDCNO#1 22/105 RPR SHLS | WILLITS | ETL.1330.TOWR | 2023-06-07 | 2023-05-30 | 2023-11-07 | On-time | 2024-05-29 | 204 | 2023-08-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45845932 | T2 DI CRTNA MNDCNO#1 22/105 RPR SHLS | ICS
LC | 126312817 | 005/028 | T2 DI EAGLE RCK CRTNA 5/28 COTTER | SACTO | ETL.1470.INSL.CERA | 2023-06-07 | 2023-05-30 | 2023-12-04 | On-time | 2024-05-29 | 177 | 2023-08-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45845934 | T2 DI EAGLE RCK CRTN 5/28 COTTER | ICS
LC | 126253509 | 008/014 | T2 FORT BRAGG-ELK 8/14 GO95 CLEAR | WILLITS | ETL.2060.POLE.WOOD | 2023-05-31 | 2023-05-31 | 2024-02-24 | On-time | 2024-05-30 | 96 | 2024-05-31 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656729 | T2 FORT BRAGG-ELK 8/14 GO95 CLEAR | 93G
LC | 126296184 | 084/427 | T2 EI MLN-RND MTN #2 84/427 BNT STEEL | TABLEMTN | ETL.6020.TOWR | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46102308 | T2 EI MLN-RND MTN #2 84/427 BNT STEEL | ICQ
LC | 126256142 | 000/006 | T2 EI RND MTN-TABLE MTN #2 0/6 RPL HRDT | TABLEMTN | ETL.6070.TOWR | 2023-05-31 | 2023-05-31 | 2023-07-30 | On-time | 2024-05-30 | 305 | 2024-05-31 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 45906711 | T2 EI RND MTN-TABLE MTN #2 0/6 RPL HRDT | ICQ
LC | 126296242 | 032/000 | T2 DI PHILO JCT-ELK 32/00C COTTER | WILLITS | ETL.7780.POLE.WDPS | 2023-06-05 | 2023-05-25 | 2024-06-17 | Late | 2024-05-24 | -24 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213841 | T2 DI PHILO JCT-ELK 32/00C COTTER | ICW
LC | 126296265 | 024/006 | T2 EI MNDN-WLTS-FRT BRG 24/6 REPULL GUY | WILLITS | ETL.7550.POLE.NWOD | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46102309 | T2 EI MNDN-WLTS-FRT BRG 24/6 REPULL GUY | ICS
LC | 126257159 | 021/114G | T2 EI BALCH-SANGER 021/114G RPR SWTC | FRESNO | ETL.1050.POLE.NWOD | 2023-05-31 | 2023-05-31 | 2024-03-01 | On-time | 2024-05-30 | 90 | 2024-05-31 | 623 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 46072141 | T2 EI BALCH-SANGER 021/114G RPR SWTC | ICE
LC | 126296914 | 039/756 | T2 EI HAT CREEK #1-WSTWD 39/756 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514277 | T2 EI HAT CREEK #1-WSTWD 39/756 RPL POLE | 70Y
LC | 126296917 | 039/760 | T2 EI HAT CREEK #1-WSTWD 39/760 RPL TIED | TABLEMTN | ETL.7030.INSL | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46079292 | T2 EI HAT CREEK #1-WSTWD 39/760 RPL TIED | ICW
LC | 126296918 | 039/763 | T2 EI HAT CRK #1-WSTWD 39/763 RPR INSW | TABLEMTN | ETL.7030.INSL.NCER | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079294 | T2 EI HAT CRK #1-WSTWD 39/763 RPR INSW | ICW
LC | 126296925 | 039/762 | T2 EI HAT CREEK #1-WSTWD 39/762 RPL INSW | TABLEMTN | ETL.7030.INSL.CERA | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35514278 | T2 EI HAT CREEK #1-WSTWD 39/762 RPL INSW | 93I
LC | 126296934 | 040/780 | T2 EI HAT CRK #1-WSTWD 40/780 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514320 | T2 EI HAT CRK #1-WSTWD 40/780 RPL STRW | 70Y
LC | 126257463 | 054/004 | T2 EI HUMBOLDT-TRINITY 54/4C RPR ANCW | EUREKA | ETL.1820.POLE.WDPS | 2023-05-31 | 2023-05-31 | 2024-04-29 | On-time | 2024-05-30 | 31 | 2024-05-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46096524 | T2 EI HUMBOLDT-TRINITY 54/4C RPR ANCW | ICW
LC | 126296940 | 040/781 | T2 EI HAT CRK #1-WSTWD 40/781 RPL INSW | TABLEMTN | ETL.7030.INSL | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35514279 | T2 EI HAT CRK #1-WSTWD 40/781 RPL INSW | 93I
LC | 126296941 | 040/767 | T2 EI HAT CRK #1-WSTWD 40/767 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35531496 | T2 EI HAT CRK #1-WSTWD 40/767 RPL STRW | 70Y
LC | 126258065 | 003/036 | T2 EI BRIDGEVILLE-COTTONWD 3/36 DUP CNCL | TABLEMTN | ETL.1110.INSL.NCER | 2023-05-31 | 2023-05-31 | 2023-12-04 | On-time | 2024-05-30 | 178 | 2024-05-31 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 46073752 | T2 EI BRIDGEVILLE-COTTONWD 3/36 RPL DMPW | ICW
LC | 126258375 | 026/196 | T2 EI DRUM-RIO OSO #2 026/196 RPL INSS | SACTO | ETL.1430.INSL.CERA | 2023-05-31 | 2023-05-31 | 2024-01-17 | On-time | 2024-05-30 | 134 | 2024-05-31 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35508878 | T2 EI DRUM-RIO OSO #2 RPL INSS 2 TWRS | 93K
LC | 126258926 | 028/003 | T2 MONTE RIO-FORT ROSS 28/03 GO95 CLEAR | LAKEVLLE | ETL.6979.POLE.WOOD | 2023-05-31 | 2023-05-31 | 2023-08-02 | On-time | 2024-05-30 | 302 | 2024-05-31 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31653341 | T2 MONTE RIO-FORT ROSS 28/03 GO95 CLEAR | 93G
LC | 126297154 | 009/078 | T2 EI PIT #6 JCT-ROUND MTN 9/78 RPL INSS | TABLEMTN | ETL.5440.INSL | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509003 | T2 DI PIT#6 JCT-RND MNTN 8/69 RPL INSS | 93K
LC | 126297204 | 023/441 | T2 EI HAT CREEK #1-WSTWD 23/441 COMPLETE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35514075 | T2 EI HAT CRK #1-WSTWD 22/432 REFRAME | 93E
LC | 126297205 | 022/439 | T2 EI HAT CRK#1 WSTWD 22/439 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-05 | 2023-06-05 | 2024-06-23 | Late | 2024-06-04 | -19 | 2024-06-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514079 | T2 EI HAT CRK #1-WSTWD 22/435 RPL POLE | 70Y
LC | 126297216 | 023/446 | T2 EI HAT CRK#1 WSTWD 23/446 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514120 | T2 DI HAT CRK #1-WSTWOD 23/443 RPL POLE | 70Y
LC | 126297230 | 027/521 | T2 EI HAT CRK #1-WSTWD 27/521 COMPLETED | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35514124 | T2 EI HAT CREEK #1-WSTWD 27/521 RPL POLE | 70Y
LC | 126259091 | 042/000 | T2 EI FORT ROSS-GUALALA 42/00R RPR GYWW | LAKEVLLE | ETL.6980.POLE.WDPS | 2023-05-31 | 2023-05-31 | 2024-03-26 | On-time | 2024-05-30 | 65 | 2024-05-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073760 | T2 EI FORT ROSS-GUALALA 42/00R RPR GYWW | ICW
LC | 126260558 | 076/004C | T2 EI HUMBOLDT-TRINITY 76/4C RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2023-06-01 | 2023-05-31 | 2024-04-20 | On-time | 2024-05-30 | 40 | 2024-05-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096587 | T2 EI HUMBOLDT-TRINITY 76/4A RPR GYWW | ICW
LC | 126298230 | 089/009 | T2 EI HUMBOLDT-TRINITY 089/009C RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096596 | T2 EI HUMBOLDT-TRINITY 089/009C RPR GYWW | ICW
LC | 126260559 | 076/004B | T2 EI HUMBOLDT-TRINITY 76/4B RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2023-06-01 | 2023-05-31 | 2024-04-20 | On-time | 2024-05-30 | 40 | 2024-05-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096587 | T2 EI HUMBOLDT-TRINITY 76/4A RPR GYWW | ICW
LC | 126260650 | 076/004A | T2 EI HUMBOLDT-TRINITY 76/4A RPR GYWW | EUREKA | ETL.1820.POLE.WOOD | 2023-06-01 | 2023-05-31 | 2024-04-20 | On-time | 2024-05-30 | 40 | 2024-05-31 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096587 | T2 EI HUMBOLDT-TRINITY 76/4A RPR GYWW | ICW
LC | 126298444 | 028/006 | T2 EI TRINITY-MAPLE CREEK 28/06 RPR INSW | EUREKA | ETL.8170.INSL.NCER | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46172083 | T2 EI TRINITY-MAPLE CREEK 28/06 RPR INSW | ICW
LC | 126298446 | 028/004 | T2 EI TRINITY-MAPLE CREEK 28/04 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504079 | T2 EI TRINITY-MAPLE CREEK 28/04 RPL STRW | 70Y
LC | 126298492 | 089/010 | T2 EI HUMBOLDT TRINITY 089/010L RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-06-05 | 2023-06-05 | 2024-06-05 | Late | 2024-06-04 | -1 | 2024-06-05 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46102312 | T2 EI HUMBOLDT TRINITY 089/010L RPR GYWW | ICS
LC | 126298545 | 013/129 | T2 DI WDLF-PLRMO 13/129 RPL STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-05 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525947 | T2 DI WDLF-PLRMO 13/129 RPL STRW | 70Y
LC | 126298637 | 023/008 | T2 EI TRINITY-MAPLE CREEK 23/8 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503537 | T2 EI TRINITY-MAPLE CREEK 23/8 RPL POLE | 70Y
LC | 126298657 | 013/127 | T2 DI WDLF-PLRMO 13/127 RPL INSW | TABLEMTN | ETL.4220.INSL | 2023-06-05 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35517253 | T2 DI WDLF-PLRMO 13/127 RPL INSW | 93I
LC | 126298658 | 013/127 | T2 DI WDLF-PLRMO 13/127 RPR STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-05 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46076627 | T2 DI WDLF-PLRMO 13/127 RPR STRW | ICW
LC | 126298666 | 014/135 | T2 DI WDLF-PALERMO 014/135 RPL STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-05 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525948 | T2 DI WDLF-PALERMO 014/135 RPL STRW | 70Y
LC | 126305858 | 014/107C | T2 DI CARIBOU-TBL MTN 14/107C RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-06 | 2023-05-31 | 2024-04-11 | On-time | 2024-05-30 | 49 | 2024-05-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46073790 | T2 DI CARIBOU-TBL MTN 14/107C RPR GYWS | ICS
LC | 126298689 | 024/008 | T2 EI TRINITY-MAPLE CREEK 24/08 RMV VEG | TABLEMTN | ETL.8170.POLE.WOOD | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126298692 | 038/007 | T2 DI TRINITY-MAPLE CREEK 38/7 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-05 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506479 | T2 DI TRINITY-MAPLE CREEK 38/7 RPL STRW | 70Y
LC | 126298712 | 024/006 | T2 EI TRINITY-MAPLE CREEK 24/6 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503766 | T2 EI TRINITY-MAPLE CREEK 24/6 RPL POLE | 70Y
LC | 126298714 | 024/008 | T2 EI TRINITY-MAPLE CREEK 24/8 RPL INSW | EUREKA | ETL.8170.INSL.NCER | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35503768 | T2 EI TRINITY-MAPLE CREEK 24/08 RPL INSW | 93I
LC | 126298730 | 024/004 | T2 EI TRINITY-MAPLE CREEK 24/4 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503765 | T2 EI TRINITY-MAPLE CREEK 24/4 RPL POLE | 70Y
LC | 126298733 | 024/007 | T2 EI TRINITY-MAPLE CREEK 24/7 COTTER | EUREKA | ETL.8170.INSL.NCER | 2023-06-05 | 2023-06-05 | 2024-06-19 | Late | 2024-06-04 | -15 | 2024-06-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46172032 | T2 EI TRINITY-MAPLE CREEK 24/7 RPR INSW | ICW
LC | 126306640 | 011/054 | T2 DI CRTNA-MNDCNO#111/54 RPR CNDS | SACTO | ETL.1330.INSL.CERA | 2023-06-06 | 2023-05-31 | 2024-03-05 | On-time | 2024-05-30 | 86 | 2024-05-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46101328 | T2 DI CRTNA-MNDCNO#111/54 RPR CNDS | ICS
LC | 126306703 | 029/207 | T2 DI CRBOU-TBL MTN 29/207 RPR STRT | TABLEMTN | ETL.4440.TOWR | 2023-06-06 | 2023-05-31 | 2024-05-30 | On-time | 2024-05-30 | 0 | 2024-05-31 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46072208 | T2 DI CRBOU-TBL MTN 29/207 RPR STRT | ICQ
LC | 126306796 | 021/007 | T2 DI TRNTY-MPL CRK 21/7 RPR ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-05-31 | 2023-09-19 | On-time | 2024-05-30 | 254 | 2023-11-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45853863 | T2 DI TRNTY-MPL CRK 21/7 RPR ANCW | ICW
LC | 126298867 | 012/109 | T2 DI WDLF-PALERMO 012/109 RPL STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-05 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525944 | T2 DI WOODLEAF-PALERMO 11/108 RPL STRW | 70Y
LC | 126298869 | 010/092 | T2 DI WDLF-PLRMO 10/92 GO95 RPL | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-05 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35525819 | T2 DI WDLF-PLRMO 10/92 GO95 | 93G
LC | 126298878 | 026/498 | T2 DI HAT CRK #1-WESTWD 26/498 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-05 | 2023-05-24 | 2024-06-18 | Late | 2024-05-23 | -26 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514200 | T2 DI HAT CRK #1-WESTWD 26/498 RPL POLE | 70Y
LC | 126298902 | 012/113 | T2 DI WOODLEAF-PALERMO 12/113 RPL STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-05 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35522922 | T2 DI WOODLEAF-PALERMO 12/113 RPL STRW | 70Y
LC | 126306880 | 034/164 | T2 DI CRTN-MNDCN #1 34/164 RPR SHLS | WILLITS | ETL.1330.TOWR | 2023-06-06 | 2023-05-31 | 2023-11-07 | On-time | 2024-05-30 | 205 | 2023-08-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45845925 | T2 DI CRTN-MNDCN #1 34/164 RPR SHLS | ICS
LC | 126306912 | 023/006 | T2 DI TRINITY-MC CREEK 23/6 RPR INSW | EUREKA | ETL.8170.INSL.CERA | 2023-06-06 | 2023-05-31 | 2023-10-15 | On-time | 2024-05-30 | 228 | 2023-08-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45845901 | T2 DI TRINITY-MC CREEK 23/6 RPR INSW | ICW
LC | 126307035 | 049/238 | T2 DI CORTINA-MNDCINO #1 49/238 RPR OPGW | WILLITS | ETL.1330.TOWR | 2023-06-06 | 2023-05-31 | 2023-11-08 | On-time | 2024-05-30 | 204 | 2023-08-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45854658 | T2 DI CORTINA-MNDCINO #1 49/238 RPR OPGW | ICS
LC | 126307053 | 013/007 | T2 DI TRINITY-MAPLE CREEK 013/007 COTTER | EUREKA | ETL.8170.INSL.NCER | 2023-06-06 | 2023-05-31 | 2024-01-17 | On-time | 2024-05-30 | 134 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46070820 | T2 DI TRINITY-MAPLE CREEK 013/007 COTTER | ICW
LC | 126307067 | 022/007 | T2 DI TRNTY-MPLE CREEK 22/7 COTTER | EUREKA | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-05-31 | 2024-05-15 | On-time | 2024-05-30 | 15 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172030 | T2 DI TRINITY-MC CREEK 22/7 COTTER | ICW
LC | 126299020 | 012/115 | T2 DI WDLF-PALERMO 012/115 RPL STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-05 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525946 | T2 DI WDLF-PALERMO 012/115 RPL STRW | 70Y
LC | 126307116 | 022/000 | T2 DI TRNTY-MPLE CRK-WD 22/0 RPR ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-05-31 | 2024-05-19 | On-time | 2024-05-30 | 11 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46172029 | T2 DI TRNTY-MPLE CRK-WD 22/0 RPR ANCW | ICW
LC | 126299079 | 026/317 | T2 DI DRUM-SUMMIT#1 26/317L RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2023-06-05 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101324 | T2 DI DRUM-SUMMIT#1 26/317L RPR GYWW | ICW
LC | 126307181 | 013/061 | T2 DI CORTINA-MENDO#1 13/61 RPR INSS | SACTO | ETL.1330.INSL.CERA | 2023-06-06 | 2023-05-31 | 2024-03-05 | On-time | 2024-05-30 | 86 | 2024-05-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46101331 | T2 DI CORTINA-MENDO#1 13/61 RPR INSS | ICS
LC | 126299116 | 012/143A | T2 DI DRUM-SUMMIT #1 12/143A RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-05 | 2023-05-30 | 2024-06-23 | Late | 2024-05-29 | -25 | 2024-05-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101326 | T2 DI DRUM-SUMMIT #1 12/143A RPR GYWW | ICW
LC | 126299281 | 007/188 | T2 EI CTTNWD-BNTN #17/188 RPR INSW | TABLEMTN | ETL.6640.INSL.CERA | 2023-06-05 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079283 | T2 EI CTTNWD-BNTN #1 007/188 RPR CNDW | ICW
LC | 126299472 | 026/169 | T2 POE-RIO OSO 026/169 RMV ENCR | TABLEMTN | ETL.5540.TOWR | 2023-06-06 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 931 | TLS | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Encroachment | Right of Way | Remove
LC | 126309877 | 013/006 | T2 DI TRINITY-MPL CRK 13/6 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-07 | 2023-05-31 | 2023-08-01 | On-time | 2024-05-30 | 303 | 2023-11-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45845905 | T2 DI TRINITY-MPL CRK 13/6 RPR GYWW | ICW
LC | 126309990 | 013/006 | T2 DI TRINITY-MAPLE CREEK 013/006 COTTER | EUREKA | ETL.8170.INSL.NCER | 2023-06-07 | 2023-05-31 | 2024-01-18 | On-time | 2024-05-30 | 133 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46070819 | T2 DI TRINITY-MAPLE CREEK 013/006 COTTER | ICW
LC | 126299641 | 011/103 | T2 DI WDLEAF-PLRMO 11/103 RPL STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-06 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525903 | T2 DI WDLEF-PLRMO RPL 5 STRW | 70Y
LC | 126309992 | 013/002 | T2 DI TRINITY-MAPLE CREEK 13/02 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-07 | 2023-05-31 | 2024-01-18 | On-time | 2024-05-30 | 133 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46070817 | T2 DI TRINITY-MAPLE CREEK 13/02 RPR GYWW | ICW
LC | 126310512 | 013/002 | T2 DI TRINITY-MAPLE CREEK 13/02 RPR CRSW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-07 | 2023-05-31 | 2024-01-18 | On-time | 2024-05-30 | 133 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46070817 | T2 DI TRINITY-MAPLE CREEK 13/02 RPR GYWW | ICW
LC | 126299882 | 021/145A | T2 DI CARIBOU-TBL MTN 21/145A RPR CNDS | TABLEMTN | ETL.4440.INSL.NCER | 2023-06-06 | 2023-05-30 | 2024-06-08 | Late | 2024-05-29 | -10 | 2024-05-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46073791 | T2 DI CARIBOU-TBL MTN 21/145A RPR CNDS | ICS
LC | 126310983 | 014/003 | T2 DI TRINITY-MPL CRK 14/3 RPR JUMW | EUREKA | ETL.8170.INSL.CERA | 2023-06-07 | 2023-05-31 | 2024-01-19 | On-time | 2024-05-30 | 132 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46070822 | T2 DI TRINITY-MPL CRK 14/3 RPR JUMW | ICW
LC | 126312320 | 037/176 | T2 DI MENDOCINO-REDBUD#1 37/176 RPR INSS | WILLITS | ETL.2410.INSL.CERA | 2023-06-07 | 2023-05-31 | 2023-09-19 | On-time | 2024-05-30 | 254 | 2023-08-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45845923 | T2 DI MENDOCINO-REDBUD#1 37/176 RPR INSS | ICS
LC | 126300244 | 053/1030 | T2 DI HAT CRK#1 WSTWD 53/1030 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514338 | T2 DI HAT CRK#1 WSTWD 53/1030 RPL STRW | 70Y
LC | 126301788 | 145 | T2 DI WOODLEAF-PALERMO 006/053 RPR SWTC | TABLEMTN | ETL.4220.SWIT | 2023-06-06 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 623 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Out of Adjustment | Switch | Repair | 46073747 | T2 DI WOODLEAF-PALERMO 006/053 RPR SWTC | ICE
LC | 126314546 | 023/007 | T2 DI TRNTY-MPL CRK 23/7 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-07 | 2023-05-31 | 2024-05-15 | On-time | 2024-05-30 | 15 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172031 | T2 DI TRNTY-MPL CRK 023/007 RPR GYWW | ICW
LC | 126303543 | A007/157 | T2 EI CASCDE-BNTN-DSCHTS A7/157 RPL POLE | TABLEMTN | ETL.6310.POLE.WOOD | 2023-06-06 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35521776 | T2 EI CASCDE-BNTN-DSCHTS A7/148 RPL POLE | 70Y
LC | 126303656 | 041/794 | T2 EI HAT CRK #1-WSTWD 41/794 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514320 | T2 EI HAT CRK #1-WSTWD 40/780 RPL STRW | 70Y
LC | 126314789 | 022/104 | T2 DI CRTN-MNDCN #1 22/104 RPR INSS | WILLITS | ETL.1470.INSL.CERA | 2023-06-07 | 2023-05-31 | 2024-05-15 | On-time | 2024-05-30 | 15 | 2024-05-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46102361 | T2 DI CRTN-MNDCN #1 22/104 RPR INSS | ICS
LC | 126314851 | 013/063 | T2 DI EGLE RCK-CRTNA #1 13/63 RPR OPGW | SACTO | ETL.1330.TOWR | 2023-06-07 | 2023-05-31 | 2024-03-05 | On-time | 2024-05-30 | 86 | 2024-05-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46101332 | T2 DI EGLE RCK-CRTNA #1 13/63 RPR OPGW | ICS
LC | 126303722 | 041/787 | T2 EI HAT CRK #1-WSTWD 41/787 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514320 | T2 EI HAT CRK #1-WSTWD 40/780 RPL STRW | 70Y
LC | 126303723 | 041/789 | T2 EI HAT CRK #1-WESTWD 41/789 GO95 RPL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35529173 | T2 EI HAT CRK #1-WESTWD 41/789 GO95 | 93G
LC | 126315106 | 021/006 | T2 DI TRNTY MPLE CRK 21/6 RPR ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-07 | 2023-05-31 | 2024-05-18 | On-time | 2024-05-30 | 12 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46172028 | T2 DI TRNTY MPLE CRK 21/006 RPR ANCW | ICW
LC | 126303876 | 041/002 | T2 EI TRINITY-MAPLE CREEK 41/2 RPR ROAD | EUREKA | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 932 | TLR | INSP | E - Schd Compl Yr 0 | Open | TR2 | Brush Fuel | Road | Remove | 45985764 | T2 EI TRINITY-MAPLE CREEK 41/2 RPR ROAD | CHS
LC | 126315156 | 029/139 | T2 DI MENDOCINO-REDBUD 29/139 RPR INSS | WILLITS | ETL.2410.INSL.CERA | 2023-06-07 | 2023-05-31 | 2023-11-16 | On-time | 2024-05-30 | 196 | 2023-08-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45845927 | T2 DI MENDOCINO-REDBUD 29/139 RPR INSS | ICS
LC | 126304565 | 087/443 | T2 EI MLN-RND MT #2 87/443 RPR STRT | TABLEMTN | ETL.6020.TOWR | 2023-06-06 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45869271 | T2 EI MLN-RND MT #2 87/443 RPR TOWR LEAN | ICQ
LC | 126315261 | 019/005 | T2 DI TRNTY MPLE CRK 19/5 CANCEL | EUREKA | ETL.8170.POLE.WOOD | 2023-06-07 | 2023-05-31 | 2024-04-30 | On-time | 2024-05-30 | 30 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46172025 | T2 DI TRNTY MPLE CRK 19/005 RPR ANCW | ICW
LC | 126304745 | 029/559 | T2 EI HAT CREEK #1-WSTWD 29/559 RPR GYWW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-06-06 | 2024-06-19 | Late | 2024-06-05 | -14 | 2024-06-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079322 | T2 EI HAT CREEK #1-WSTWD 29/559 RPR GYWW | ICW
LC | 126304749 | 029/569 | T2 EI HAT CREEK #1-WSTWD 29/569 GO95 RPL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35522533 | T2 DI HT CRK #1-WSTWD 29/568 GO95 | 93G
LC | 126304787 | 053/1037 | T2 EI HAT CRK #1-WSTWD 53/1037 RPR STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46079328 | T2 EI HAT CRK #1-WSTWD 53/1037 RPR STRW | ICW
LC | 126305450 | 040/192 | T2 DI CORTINA-MNDCN #1 40/192 RPR OPGW | WILLITS | ETL.1330.TOWR | 2023-06-06 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46079117 | T2 DI CORTINA-MENDOCINO #1 40/192 COTTER | ICS
LC | 126305485 | 015/156 | T2 EI IGNACIO-ALTO 15/156 RPR INSW | LAKEVLLE | ETL.7150.INSL.NCER | 2023-06-06 | 2023-06-06 |  | Late | 2024-06-05 |  | 2023-12-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46078102 | T2 EI IGNACIO-ALTO 15/156 RPR INSW | ICW
LC | 126315333 | 012/006 | T2 DI TRINITY-MAPLE CREEK 012/006 COTTER | EUREKA | ETL.8170.INSL.NCER | 2023-06-07 | 2023-05-31 | 2024-01-23 | On-time | 2024-05-30 | 128 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46070816 | T2 DI TRINITY-MAPLE CREEK 012/006 COTTER | ICW
LC | 126316112 | 021/008 | T2 DI TRNTY MPLE CRK 21/008 RMV VEG | TABLEMTN | ETL.8170.POLE.NWOD | 2023-06-08 | 2023-05-31 | 2024-05-15 | On-time | 2024-05-30 | 15 | 2024-05-31 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126320259 | 011/056 | T2 DI EAGLE RCK CRTN 11/056 RPL DAMS | SACTO | ETL.1470.INSL.NCER | 2023-06-08 | 2023-05-31 | 2024-03-04 | On-time | 2024-05-30 | 87 | 2024-05-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 46176321 | T2 DI EAGLE RCK CRTN 11/056 RPL DAMS | ICS
LC | 126322381 | 021/004 | T2 DI TRNTY-MAPLE CRK 21/04 RPR ANCW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-08 | 2023-05-31 | 2023-10-11 | On-time | 2024-05-30 | 232 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45853864 | T2 DI TRNTY-MAPLE CRK 21/04 RPR ANCW | ICW
LC | 126322732 | 013/004 | T2 DI TRNTY-MPL CRK 013/004 RPL HRDD | EUREKA | ETL.8170.INSL.CERA | 2023-06-08 | 2023-05-31 | 2024-01-18 | On-time | 2024-05-30 | 133 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46070818 | T2 DI TRNTY-MPL CRK 013/004 RPL HRDD | ICW
LC | 126259838 | :017/090 | T2 CRZY HRSE CNYN-SLNS#2 :017/090 COTTER | MOSSLNDG | ETL.2910.INSL.CERA | 2023-06-01 | 2023-06-01 | 2024-02-01 | On-time | 2024-05-31 | 120 | 2024-06-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46081536 | T2 CRZY HRSE CNYN-SLNS#2 :017/090 COTTER | ICS
LC | 126265705 | 008/135 | T2 EI PIT 1-HATCRK 2-BRNY 8/135 RPR CNDW | TABLEMTN | ETL.7040.INSL.NCER | 2023-06-01 | 2023-06-01 | 2024-05-14 | On-time | 2024-05-31 | 17 | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46076249 | T2 EI PIT 1-HATCRK 2-BRNY 8/135 RPR CNDW | ICW
LC | 126305737 | 007/059 | T2 EI PIT #6-ROUND MTN_007/059 RPR INSW | TABLEMTN | ETL.5440.INSL.NCER | 2023-06-06 | 2023-06-06 | 2024-06-21 | Late | 2024-06-05 | -16 | 2024-06-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46240004 | T2 EI PIT #4-ROUND MTN_007/059 RPR INSW | ICW
LC | 126266957 | 008/136 | T2 EI PIT#1-HAT CRK#2-BRNY 8/136 RMV VEG | TABLEMTN | ETL.7040.POLE.WOOD | 2023-06-01 | 2023-06-01 | 2023-08-17 | On-time | 2024-05-31 | 288 | 2023-12-01 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126267183 | 005/108 | T2 EI CTRVL-TBL MTN-OROVL 5/108 RPR GYWW | TABLEMTN | ETL.6330.POLE.NWOD | 2023-06-01 | 2023-06-01 | 2024-02-01 | On-time | 2024-05-31 | 120 | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076613 | T2 EI CTRVL-TBL MTN-OROVL 5/108 RPR GYWW | ICW
LC | 126305851 | 015/073 | T2 DI CORTINA-MENDO #1 15/73 RPL HRDT | WILLITS | ETL.1330.TOWR | 2023-06-06 | 2023-05-31 | 2024-06-05 | Late | 2024-05-30 | -6 | 2024-05-31 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Tower | Install | 46079118 | T2 DI CORTINA-MENDO #1 15/73 RPL HRDT | ICQ
LC | 126267501 | 018/096 | T2 EI RND MTN-TBLE MTN #1 18/96 RPR CNDT | TABLEMTN | ETL.6060.INSL | 2023-06-01 | 2023-06-01 | 2024-04-15 | On-time | 2024-05-31 | 46 | 2024-06-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46079114 | T2 EI RND MTN-TBLE MTN #1 18/96 RPR CNDT | ICS
LC | 126306027 | 033/644 | T2 DI HT CRK #1-WSTWD 33/644 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-05-25 | 2024-06-25 | Late | 2024-05-24 | -32 | 2024-05-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514210 | T2 DI HT CRK #1-WSTWD 33/644 RPL POLE | 70Y
LC | 126267829 | 047/194 | T2 MIDWAY-WHIRLWIND 47/194 INS RPTS | MIDWAY | ETL.6030.TOWR | 2023-06-01 | 2023-06-01 | 2024-01-09 | On-time | 2024-05-31 | 143 | 2024-06-01 | 530 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Raptor Guard-Steel | Install | 31651949 | T2 MIDWAY-WHIRLWIND 47/192 INS RPTS | 93R
LC | 126267831 | 047/192 | T2 MIDWAY-WHIRLWIND 47/192 INS RPTS | MIDWAY | ETL.6030.TOWR | 2023-06-01 | 2023-06-01 | 2024-01-09 | On-time | 2024-05-31 | 143 | 2024-06-01 | 530 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Raptor Guard-Steel | Install | 31651949 | T2 MIDWAY-WHIRLWIND 47/192 INS RPTS | 93R
LC | 126267871 | 047/190 | T2 MIDWAY-WHIRLWIND 47/190 INS RPTS | MIDWAY | ETL.6030.TOWR | 2023-06-01 | 2023-06-01 | 2024-01-09 | On-time | 2024-05-31 | 143 | 2024-06-01 | 593 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Raptor Guard-Steel | Replace | 46190134 | T2 MIDWAY-WHIRLWIND 47/190 INS RPTS | ICB
LC | 126268053 | 017/000 | T2 EI TRINITY-MAPLE CREEK 17/0 RPR STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-01 | 2023-06-01 | 2024-05-16 | On-time | 2024-05-31 | 15 | 2024-06-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46070823 | T2 EI TRINITY-MAPLE CREEK 17/0 RPR STRW | ICW
LC | 126306166 | 006/029 | T2 DI FULTON-PUEBL 6/29 RPR STRT | LAKEVLLE | ETL.1600.TOWR | 2023-06-06 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46079119 | T2 DI FULTON-PUEBL 6/29 RPR STRT | ICQ
LC | 126320439 | 024/005 | T2 DI TRNTY MPLE CRK 24/5 RPR INSW | EUREKA | ETL.8170.INSL.NCER | 2023-06-08 | 2023-06-01 | 2023-10-15 | On-time | 2024-05-31 | 229 | 2023-09-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45845903 | T2 DI TRNTY MPLE CRK 24/005 RPR INSW | ICW
LC | 126306207 | 007/037 | T2 DI EAGLE ROCK-CORTINA 7/37 RPL INSS | SACTO | ETL.1470.INSL.CERA | 2023-06-06 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31676909 | T2 DI EAGLE ROCK-CORTINA 7/37 RPL INSS | 93K
LC | 126306237 | 052/1022 | T2 EI HAT CRK #1-WSTWD 52/1022 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35562836 | T2 EI HAT CRK #1-WSTWD 52/1022 RPL STRW | 70Y
LC | 126306289 | 032/626 | T2 DI HAT CRK #1-WESTWD 32/626 GO95 | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-05-25 | 2024-06-22 | Late | 2024-05-24 | -29 | 2024-05-25 | 401T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35523010 | T2 DI HAT CRK #1-WESTWD 32/622 GO95 | 93G
LC | 126322274 | 059/287 | T2 DI CORTNA-MENDCNO #1 59/287 RPR OPGW | WILLITS | ETL.1330.TOWR | 2023-06-08 | 2023-06-01 | 2023-11-08 | On-time | 2024-05-31 | 205 | 2023-09-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45845921 | T2 DI CORTNA-MENDCNO #1 59/287 RPR OPGW | ICS
LC | 126322275 | 059/287 | T2 DI CORTNA-MENDCNO #1 59/287 BNT STEEL | WILLITS | ETL.1330.TOWR | 2023-06-08 | 2023-06-01 | 2023-07-25 | On-time | 2024-05-31 | 311 | 2023-09-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45867437 | T2 DI CORTNA-MENDCNO #1 59/287 BNT STEEL | ICQ
LC | 126322298 | 009/046 | T2 DI CORTINA-MNDNC #1 009/46 RPR OPGW | SACTO | ETL.1330.TOWR | 2023-06-08 | 2023-06-01 | 2023-08-14 | On-time | 2024-05-31 | 291 | 2023-09-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45845922 | T2 DI CORTINA-MNDNC #1 009/46 RPR OPGW | ICS
LC | 126306397 | 010/093 | T2 DI WOODLEAF-PALERMO 010/093 RPL STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-06 | 2023-05-26 |  | Late | 2024-05-25 |  | 2023-11-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525900 | T2 DI WOODLEAF-PALERMO 10/91 RPL POLE | 70Y
LC | 126306405 | 042/009C | T2 EI TRINITY-MAPLE CREEK 42/9C RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506771 | T2 EI TRINITY-MAPLE CREEK 42/9A RPL POLE | 70Y
LC | 126306406 | 042/009B | T2 EI TRINITY-MAPLE CREEK 42/9B RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506771 | T2 EI TRINITY-MAPLE CREEK 42/9A RPL POLE | 70Y
LC | 126306411 | 047/007 | T2 DI TRINITY-MAPLE CREEK 47/7 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-05-24 |  | Late | 2024-05-23 |  | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506441 | T2 DI TRINITY-MAPLE CREEK 47/7 RPL POLE | 70Y
LC | 126322350 | 014/066 | T2 DI CORTINA-MNDCNO#1 14/66 COMPLETE | WILLITS | ETL.1330.TOWR | 2023-06-08 | 2023-06-01 | 2023-08-23 | On-time | 2024-05-31 | 282 | 2023-09-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45861687 | T2 DI CORTINA-MNDCNO#1 14/66 RPR OPGW | ICS
LC | 126306493 | 042/009A | T2 EI TRINITY-MAPLE CREEK 42/9A RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506771 | T2 EI TRINITY-MAPLE CREEK 42/9A RPL POLE | 70Y
LC | 126306505 | 027/004 | T2 DI TRNTY-MAPLE CREEK 27/4 RPL CRSW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35504071 | T2 DI TRNTY-MAPLE CREEK 27/4 RPL CRSW | 93E
LC | 126306507 | 027/004 | T2 DI TRNTY-MAPLE CREEK 27/4 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-05-31 | 2024-06-19 | Late | 2024-05-30 | -20 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172037 | T2 DI TRNTY-MAPLE CREEK 27/4 RPR GYWW | ICW
LC | 126306509 | 027/004 | T2 DI TRNTY-MAPLE CREEK 27/4 RMV VEG | TABLEMTN | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126306523 | 032/622 | T2 DI HAT CRK #1-WESTWD 32/622 GO95 | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-05-25 | 2024-06-18 | Late | 2024-05-24 | -25 | 2024-05-25 | 401T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35523010 | T2 DI HAT CRK #1-WESTWD 32/622 GO95 | 93G
LC | 126306527 | 029/006 | T2 DI TRINITY-MAPLE CRK 29/6 RPL ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35504380 | T2 DI TRINITY-MAPLE CRK 29/6 RPL ANCW | 93E
LC | 126322366 | 028/200 | T2NT DI CARIBOU-TBL MTN 28/200 RPL HRDT | TABLEMTN | ETL.4440.TOWR | 2023-06-08 | 2023-06-01 | 2024-02-06 | On-time | 2024-05-31 | 115 | 2024-06-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46072212 | T2NT DI CARIBOU-TBL MTN 28/200 RPL HRDT | ICQ
LC | 126306605 | 052/255 | T2 DI MNDCN-RDBD #1 52/255 RPR INSS | WILLITS | ETL.2410.INSL.CERA | 2023-06-06 | 2023-05-31 |  | Late | 2024-05-30 |  | 2023-11-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46079140 | T2 DI MNDCN-RDBD #1 52/255 RPR INSS | ICS
LC | 126322651 | 005/031 | T2 DI CORTINA-MN#1 5/31 COTTER | SACTO | ETL.1330.TOWR | 2023-06-08 | 2023-06-01 | 2024-03-05 | On-time | 2024-05-31 | 87 | 2024-06-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46101336 | T2 DI CORTINA-MN#1 5/31 COTTER | ICS
LC | 126306641 | 011/054 | T2 DI CRTNA-MNDCNO#111/54 RPR CNDS | SACTO | ETL.1470.INSL.NCER | 2023-06-06 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46102315 | T2 DI CRTNA-MNDCNO#111/54 RPR CNDS | ICS
LC | 126324222 | 013/064 | T2 DI CRTNA-MNDCNO 13/64 COTTER | SACTO | ETL.1330.INSL.NCER | 2023-06-09 | 2023-06-01 | 2024-03-05 | On-time | 2024-05-31 | 87 | 2024-06-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46101337 | T2 DI CRTNA-MNDCNO 13/64 COTTER | ICS
LC | 126306701 | 030/579 | T2 DI HAT CRK #1-WSTWD 30/579 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-05-24 | 2024-06-20 | Late | 2024-05-23 | -28 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514135 | T2 DI HAT CRK #1-WSTWD 30/579 RPL POLE | 70Y
LC | 126324601 | 007/038 | T2 DI CRTNA-MNDCNO #1 007/038 RPL INSS | SACTO | ETL.1330.INSL.NCER | 2023-06-09 | 2023-06-01 | 2024-03-05 | On-time | 2024-05-31 | 87 | 2024-06-01 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513063 | T2 DI CRTNA-MNDCNO #1 007/038 RPL INSS | 93K
LC | 126306704 | 028/545 | T2 DI HAT CRK #1-WSTWD 28/545 COMPLETE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-05-24 | 2024-06-19 | Late | 2024-05-23 | -27 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514131 | T2 DI HAT CRK #1-WSTWD 28/545 RPL POLE | 70Y
LC | 126306764 | 033/650 | T2 DI HAT CREEK #1-WESTWD 33/650 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-05-25 | 2024-06-18 | Late | 2024-05-24 | -25 | 2024-05-25 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35514215 | T2 DI HAT CREEK #1-WESTWD 33/650 REFRAME | 93E
LC | 126324979 | 009/081 | T2 DI PARADISE-TABLE MTN 009/081 COTTER | TABLEMTN | ETL.4316.INSL.NCER | 2023-06-09 | 2023-06-01 | 2024-01-30 | On-time | 2024-05-31 | 122 | 2024-06-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46075854 | T2 DI PARADISE-TABLE MTN 009/081 COTTER | ICS
LC | 126306812 | 029/562 | T2 DI HT CRK #1-WSTWD 029/562 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-05-24 | 2024-06-19 | Late | 2024-05-23 | -27 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514131 | T2 DI HAT CRK #1-WSTWD 28/545 RPL POLE | 70Y
LC | 126306862 | 018/009 | T2 DI TRINITY-MAPLE CREEK 18/9 RMV VEG | TABLEMTN | ETL.8170.POLE.NWOD | 2023-06-06 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126327352 | 015/122 | T2 DI PRDS-TBL MTN-15/122 RPL INSS | TABLEMTN | ETL.4316.INSL | 2023-06-09 | 2023-06-01 | 2024-01-29 | On-time | 2024-05-31 | 123 | 2024-06-01 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31654456 | T2 DI PRDS-TBL MTN-15/122 RPL INSS | 93K
LC | 126306891 | 011/137C | T2 DI DRUM SUMMIT #2 1/137C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-06 | 2023-05-30 | 2024-06-19 | Late | 2024-05-29 | -21 | 2024-05-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101330 | T2 DI DRUM SUMMIT #2 001/137C RPR GYWW | ICW
LC | 126306910 | 023/006 | T2 DI TRINITY-MC CREEK 23/6 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503536 | T2 DI TRINITY-MC CREEK 23/6 RPL POLE | 70Y
LC | 126329010 | 064/319 | T2 DI MALIN-RM#2 64/319 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-06-09 | 2023-06-01 | 2024-05-10 | On-time | 2024-05-31 | 21 | 2024-06-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46076091 | T2 DI MALIN-RM#2 64/319 RPR SHLS | ICS
LC | 126342586 | 061/306 | T2 DI MALIN-RND MNTN #2 61/306 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-06-10 | 2023-06-01 | 2024-01-23 | On-time | 2024-05-31 | 129 | 2024-06-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46076088 | T2 DI MALIN-RND MNTN #2 61/306 RPR OPGW | ICS
LC | 126307046 | 022/428 | T2 DI HAT CREEK#1-WESTWD 22/428 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-05-24 | 2024-06-20 | Late | 2024-05-23 | -28 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514010 | T2 DI HAT CREEK#1-WESTWD 22/428 RPL POLE | 70Y
LC | 126342587 | 061/306 | T2 DI MALIN-RND MNTN #2 61/306 COTTER | TABLEMTN | ETL.6020.INSL.NCER | 2023-06-10 | 2023-06-01 | 2023-12-20 | On-time | 2024-05-31 | 163 | 2024-06-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46076089 | T2 DI MALIN-RND MNTN #2 61/306 COTTER | ICS
LC | 126307054 | 059/288 | T2 DI MENDOCINO-REDBUD 59/288 RPL INSS | WILLITS | ETL.2410.INSL.CERA | 2023-06-06 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31676908 | DI MENDOCINO-REDBUD RPL INSS IN 3 TWRS | 93K
LC | 126347284 | 014/117 | T2 DI PARADISE-TABLE MTN-14/117 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2023-06-11 | 2023-06-01 | 2024-01-29 | On-time | 2024-05-31 | 123 | 2024-06-01 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672700 | T2 EI PARADISE-TABLE MTN 11/093 RPL INSW | 93K
LC | 126307075 | 029/570 | T2 DI HAT CRK #1-WSTWD 29/570 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-06 | 2023-05-24 | 2024-06-20 | Late | 2024-05-23 | -28 | 2024-05-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514134 | T2 DI HAT CRK#1-WSTWD-29/565 RPL POLE | 70Y
LC | 126307079 | 016/160 | T2 DI WOODLEAF-PALERMO 16/160 RPR STRW | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-06 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46076629 | T2 DI WOODLEAF-PALERMO 16/160 RPR STRW | ICW
LC | 126307087 | 054/266 | T2 DI CRTN-MNDCN #1 054/266 BNT STEEL | WILLITS | ETL.1330.TOWR | 2023-06-06 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46102317 | T2 DI CRTN-MNDCN #1 054/266 BNT STEEL | ICQ
LC | 126307112 | 021/001 | T2 DI TRINITY-MAPLE CREEK 21/1L RMV VEG | TABLEMTN | ETL.8170.POLE.WDPS | 2023-06-06 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126307113 | 021/001 | T2 DI TRINITY-MAPLE CREEK 21/1C RPL INSW | EUREKA | ETL.8170.INSL.CERA | 2023-06-06 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35553317 | T2 DI TRINITY-MAPLE CREEK 21/1C RPL INSW | 93I
LC | 126307114 | 022/000 | T2 DI TRNTY-MPLE CRK-WD 22/0 RPL INSW | EUREKA | ETL.8170.INSL.CERA | 2023-06-06 | 2023-05-31 |  | Late | 2024-05-30 |  | 2023-08-31 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35556190 | T2 DI TRNTY-MPLE CRK-WD 22/0 RPL INSW | 93I
LC | 126349167 | 062/309 | T2 DI MALIN RND MTN#2 62/309 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-06-12 | 2023-06-01 | 2024-01-23 | On-time | 2024-05-31 | 129 | 2024-06-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46076090 | T2 DI MALIN RND MTN#2 62/309 RPR OPGW | ICS
LC | 126307130 | 009/078 | T2 DI WOODLEAF-PALERMO 9/78R RPL STRW | TABLEMTN | ETL.4220.POLE.WDPS | 2023-06-06 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35540606 | T2 DI WOODLEAF-PALERMO 9/78R RPL STRW | 70Y
LC | 126307170 | 030/004 | T2 DI TRNTY-MPL CRK-STL 30/4 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-05-25 | 2024-06-14 | Late | 2024-05-24 | -21 | 2024-05-25 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46203593 | T2 DI TRNTY-MPL CRK-STL 30/4 RPR GYWW | ICW
LC | 126307171 | 030/004 | T2 DI TRNTY-MPL CRK 30/4 RPL ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35504381 | T2 DI TRNTY-MPL CRK 30/4 RPL ANCW | 93E
LC | 126307175 | 029/002 | T2 DI TRINITY-MPL CRK 29/2 RMV VEG | EUREKA | ETL.8170.POLE.WOOD | 2023-06-06 | 2023-05-25 |  | Late | 2024-05-24 |  | 2024-05-25 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126268698 | 093/005 | T2 HUMBOLDT-TRINITY 93/05 COTTER | EUREKA | ETL.1820.INSL.NCER | 2023-06-02 | 2023-06-02 | 2023-08-07 | On-time | 2024-06-01 | 299 | 2023-09-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45845904 | T2 HUMBOLDT-TRINITY 93/05 COTTER | ICW
LC | 126276178 | 011/097A | T2 EI PIT #6 JCT-RND MTN 11/97A RPR GYWW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-06-02 | 2023-06-02 | 2024-05-17 | On-time | 2024-06-01 | 15 | 2024-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076171 | T2 EI PIT #6 JCT-RND MTN 11/97A RPR GYWW | ICW
LC | 126276406 | 011/100 | T2 EI CRAG VIEW-CASCADE 11/100L RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-06-02 | 2023-06-02 | 2024-02-28 | On-time | 2024-06-01 | 94 | 2024-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076668 | T2 EI CRAG VIEW-CASCADE 11/100L RPR GYWW | ICW
LC | 126309754 | 034/006 | T2 DI TRNTY MPL CRK 34/006 RPL HRDD | EUREKA | ETL.8170.POLE.WOOD | 2023-06-07 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46096667 | T2 DI TRINITY-MAPLE CREEK 34/06 RPR GYWW | ICW
LC | 126309756 | 034/006 | T2 DI TRINITY-MAPLE CREEK 34/06 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-07 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096667 | T2 DI TRINITY-MAPLE CREEK 34/06 RPR GYWW | ICW
LC | 126276939 | 015/051 | T2 EI EXCHEQUER-INDIAN FLT 15/051 UNBURY | FRESNO | ETL.8650.TOWR | 2023-06-02 | 2023-06-02 | 2023-12-07 | On-time | 2024-06-01 | 177 | 2024-06-02 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46082228 | T2 EI EXCHEQUER-INDIAN FLT 15/051 UNBURY | ICQ
LC | 126277118 | 036/314 | T2 EI RND MTN-CTTNWD #3 36/314 RPL INSS | TABLEMTN | ETL.5650.INSL | 2023-06-02 | 2023-06-02 | 2024-04-16 | On-time | 2024-06-01 | 46 | 2024-06-02 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513132 | T2 EI RND MTN-CTTNWD #3 2 TWRS RPL INSS | 93K
LC | 126277389 | 000/010 | T2 EI IGNACIO-BOLINAS #1 00/010 RMV VEG | LAKEVLLE | ETL.7140.POLE.WOOD | 2023-06-02 | 2023-06-02 | 2024-04-16 | On-time | 2024-06-01 | 46 | 2024-06-02 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126310365 | 057/285 | T2 EI MLN-RND MTN #2 57/285 RPR GYWT | TABLEMTN | ETL.6020.TOWR | 2023-06-07 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46102318 | T2 EI MALIN-RUND MTN #2 057/285 RPR GYWS | ICS
LC | 126278062 | 016/057 | T2 EI EXCHEQUER-INDIAN FLT 16/057 UNBURY | FRESNO | ETL.8650.TOWR | 2023-06-02 | 2023-06-02 | 2023-12-08 | On-time | 2024-06-01 | 176 | 2024-06-02 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46082229 | T2 EI EXCHEQUER-INDIAN FLT 16/057 UNBURY | ICQ
LC | 126310525 | 014/355 | T2 EI CTTNWD-BNTN #1 014/355 RPL ANC | TABLEMTN | ETL.6640.POLE.NWOD | 2023-06-07 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35515943 | T2 EI CTTNWD-BNTN #1 014/355 RPL ANC | 93E
LC | 126310526 | 092/001A | T2 EI HUMBOLDT-TRINITY 92/01A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-07 | 2023-06-07 | 2024-06-09 | Late | 2024-06-06 | -3 | 2024-06-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096660 | T2 EI HUMBOLDT-TRINITY 92/01A RPR GYWW | ICW
LC | 126310587 | 092/001B | T2 EI HUMBOLDT-TRINITY 92/01B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-07 | 2023-06-07 | 2024-06-09 | Late | 2024-06-06 | -3 | 2024-06-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096660 | T2 EI HUMBOLDT-TRINITY 92/01A RPR GYWW | ICW
LC | 126310668 | 092/001C | T2 EI HUMBOLDT-TRINITY 92/01C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-07 | 2023-06-07 | 2024-06-09 | Late | 2024-06-06 | -3 | 2024-06-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096660 | T2 EI HUMBOLDT-TRINITY 92/01A RPR GYWW | ICW
LC | 126310703 | 092/004 | T2 EI HUMBOLDT-TRINITY 092/04 ANTI SPLIT | EUREKA | ETL.1820.POLE.WDPS | 2023-06-07 | 2023-06-07 | 2024-06-07 | Late | 2024-06-06 | -1 | 2024-06-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46096661 | T2 EI HUMBOLDT-TRINITY 092/04 ANTI SPLIT | ICW
LC | 126310918 | 030/580 | T2 EI HAT CREEK #1-WSTWD 30/580 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2024-06-20 | Late | 2024-06-06 | -14 | 2024-06-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514135 | T2 DI HAT CRK #1-WSTWD 30/579 RPL POLE | 70Y
LC | 126310956 | 030/587 | T2 EI HAT CREEK #1-WSTWD 30/587 COMPLETE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2024-06-21 | Late | 2024-06-06 | -15 | 2024-06-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514136 | T2 DI HAT CRK #1-WSTWD 30/585 RPL PL | 70Y
LC | 126278148 | 074/002 | T2 EI HUMBOLDT-TRINITY 74/2L RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-02 | 2023-06-02 | 2024-05-13 | On-time | 2024-06-01 | 19 | 2024-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096582 | T2 EI HUMBOLDT-TRINITY 74/2L RPR GYWW | ICW
LC | 126278194 | 074/002 | T2 EI HUMBOLDT-TRINITY 74/2R RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-02 | 2023-06-02 | 2024-05-13 | On-time | 2024-06-01 | 19 | 2024-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096582 | T2 EI HUMBOLDT-TRINITY 74/2L RPR GYWW | ICW
LC | 126312180 | 031/187 | T2 EI HELMS-GREGG #1 031/187 COTTER | FRESNO | ETL.4870.INSL.CERA | 2023-06-07 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46080580 | T2 EI HELMS-GREGG #1 031/187 COTTER | ICS
LC | 126279036 | 028/185 | T2 EI POE-RIO OSO-RIO OS 28/185 RPL INSS | TABLEMTN | ETL.5540.INSL.CERA | 2023-06-02 | 2023-06-02 | 2024-01-29 | On-time | 2024-06-01 | 124 | 2024-06-02 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672704 | T2 EI POE-RIO OSO 5TWR RPL INSS | 93K
LC | 126279670 | 027/182 | T2 EI POE-RIO OSO-RIO OS 27/182 RPL INSS | TABLEMTN | ETL.5540.INSL.CERA | 2023-06-02 | 2023-06-02 | 2024-01-29 | On-time | 2024-06-01 | 124 | 2024-06-02 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672704 | T2 EI POE-RIO OSO 5TWR RPL INSS | 93K
LC | 126281171 | 003/074 | T2 EI CNTRVL-TBL MTN-ORVL 3/74 RPL STRW | TABLEMTN | ETL.6330.POLE.WOOD | 2023-06-02 | 2023-06-02 | 2024-05-24 | On-time | 2024-06-01 | 8 | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508683 | T2 EI CNTRVL-TBL MTN-ORVL 3/74 RPL STRW | 70Y
LC | 126313133 | 014/356 | T2 EI CTTNWD-BNTN #1 014/356 COTTER | TABLEMTN | ETL.6640.INSL.CERA | 2023-06-07 | 2023-06-07 |  | Late | 2024-06-06 |  | 2023-12-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079335 | T2 EI CTTNWD-BNTN #1 014/356 COTTER | ICW
LC | 126313262 | 093/003C | T2 EI HUMBOLDT-TRINITY 93/03C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-07 | 2023-06-07 | 2024-06-07 | Late | 2024-06-06 | -1 | 2024-06-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096662 | T2 EI HUMBOLDT-TRINITY 93/03A RPR GYWW | ICW
LC | 126313396 | 093/003B | T2 EI HUMBOLDT-TRINITY 93/03B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-07 | 2023-06-07 | 2024-06-07 | Late | 2024-06-06 | -1 | 2024-06-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096662 | T2 EI HUMBOLDT-TRINITY 93/03A RPR GYWW | ICW
LC | 126313426 | 093/003A | T2 EI HUMBOLDT-TRINITY 93/03A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-07 | 2023-06-07 | 2024-06-07 | Late | 2024-06-06 | -1 | 2024-06-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096662 | T2 EI HUMBOLDT-TRINITY 93/03A RPR GYWW | ICW
LC | 126313718 | 030/592 | T2 EI HT CRK #1-WESTWOOD 30/592 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2024-06-22 | Late | 2024-06-06 | -16 | 2024-06-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514137 | T2 DI HT CRK #1-WESTWD 30/590 RPL POLE | 70Y
LC | 126281951 | 003/076 | T2 EI CNTRVL-TBL MTN-ORVL 3/76 RPL STRW | TABLEMTN | ETL.6330.POLE.WOOD | 2023-06-02 | 2023-06-02 | 2024-05-23 | On-time | 2024-06-01 | 9 | 2024-06-02 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508684 | T2 EI CNTRVL-TBL MTN-ORVL 3/76 RPL STRW | 70Y
LC | 126282312 | 027/178 | T2 EI POE-RIO OSO-RIO OS 27/178 RPL INSS | TABLEMTN | ETL.5540.INSL.CERA | 2023-06-02 | 2023-06-02 | 2024-01-30 | On-time | 2024-06-01 | 123 | 2024-06-02 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672704 | T2 EI POE-RIO OSO 5TWR RPL INSS | 93K
LC | 126282313 | 011/080 | T2 EI GNC-LT-SSLT #1 011/08 UNBURY | LAKEVLLE | ETL.7160.TOWR | 2023-06-02 | 2023-06-02 | 2024-03-13 | On-time | 2024-06-01 | 80 | 2024-06-02 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46059296 | T2 EI GNC-LT-SSLT #1 011/08 UNBURY | ICQ
LC | 126282365 | 071/000B | T2 EI HUMBOLDT-TRINITY 71/00B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-02 | 2023-06-02 | 2023-08-23 | On-time | 2024-06-01 | 283 | 2023-12-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45881348 | T2 EI HUMBOLDT-TRINITY 71/00A RPR GYWW | ICW
LC | 126282367 | 071/000A | T2 EI HUMBOLDT-TRINITY 71/00A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-02 | 2023-06-02 | 2023-08-23 | On-time | 2024-06-01 | 283 | 2023-12-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45881348 | T2 EI HUMBOLDT-TRINITY 71/00A RPR GYWW | ICW
LC | 126282368 | 071/000C | T2 EI HUMBOLDT-TRINITY 71/00C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-02 | 2023-06-02 | 2023-08-23 | On-time | 2024-06-01 | 283 | 2023-12-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45881348 | T2 EI HUMBOLDT-TRINITY 71/00A RPR GYWW | ICW
LC | 126282384 | 032/001 | T2 EI TRINITY-MAPLE CRK 032/001 RMV VEG | TABLEMTN | ETL.8170.TOWR | 2023-06-02 | 2023-06-02 | 2024-05-15 | On-time | 2024-06-01 | 17 | 2024-06-02 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation-Tower | Cage Clearing
LC | 126282440 | 070/004 | T2 EI HUMBOLDT-TRINITY 70/04C RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-06-02 | 2023-06-02 | 2024-04-20 | On-time | 2024-06-01 | 42 | 2024-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096538 | T2 EI HUMBOLDT-TRINITY 70/04C RPR GYWW | ICW
LC | 126282442 | 070/004 | T2 EI HUMBOLDT-TRINITY 70/04R RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-06-02 | 2023-06-02 | 2024-04-20 | On-time | 2024-06-01 | 42 | 2024-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096538 | T2 EI HUMBOLDT-TRINITY 70/04C RPR GYWW | ICW
LC | 126282444 | 070/004 | T2 EI HUMBOLDT-TRINITY 70/04L RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-06-02 | 2023-06-02 | 2024-04-20 | On-time | 2024-06-01 | 42 | 2024-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096538 | T2 EI HUMBOLDT-TRINITY 70/04C RPR GYWW | ICW
LC | 126324267 | 059/296 | T2 DI MALIN-ROUND MTN #2 59/296 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-06-09 | 2023-06-02 | 2024-01-22 | On-time | 2024-06-01 | 131 | 2024-06-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46076094 | T2 DI MALIN-ROUND MTN #2 59/296 RPR OPGW | ICS
LC | 126325421 | 005/010B | T2 DI LWR LK-HMSTK 005/010B RPR GYWW | WILLITS | ETL.1481.POLE.NWOD | 2023-06-09 | 2023-06-02 | 2023-07-28 | On-time | 2024-06-01 | 309 | 2023-09-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45854657 | T2 DI LWR LK-HMSTK 005/010B RPR GYWW | ICW
LC | 126314180 | 011/246 | T2 DI SALINAS-LAURELES 011/246 RPL HRDW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-07 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46081226 | T2 DI SALINAS-LAURELES 011/246 RPL HRDW | ICW
LC | 126314283 | 035/168 | T2 DI CRTNA MNDCNO#1 35/168 RPL INSS | WILLITS | ETL.1330.INSL.CERA | 2023-06-07 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31676905 | EI CORTINA-MENDOCN #1 RPL INSS IN 5 TWRS | 93K
LC | 126314285 | 035/168 | T2 DI CRTNA MNDCNO#1 35/168 RPL HRDT | WILLITS | ETL.1330.TOWR | 2023-06-07 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46102319 | T2 DI CRTNA MNDCNO#1 35/168 RPL HRDT | ICQ
LC | 126314303 | 092/471B | T2 EI MALIN-RND MTN #2 92/471B RPL ANCT | TABLEMTN | ETL.6020.TOWR | 2023-06-07 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 93Z | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Tower | Replace | 31684729 | T2 EI MALIN-RND MTN #2 92/471B RPL ANCS | 93Z
LC | 126325425 | 005/010C | T2 DI LOWER LAKE-HOMESTAK 5/10C COTR KEY | WILLITS | ETL.1481.INSL.NCER | 2023-06-09 | 2023-06-02 | 2023-07-28 | On-time | 2024-06-01 | 309 | 2023-09-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45853693 | T2 DI LOWER LAKE-HOMESTAK 5/10C COTR KEY | ICW
LC | 126325720 | 028/008 | T2 DI PHILO JCT ELK 28/8 COMPLETE | WILLITS | ETL.7780.INSL.CERA | 2023-06-09 | 2023-06-02 | 2023-09-11 | On-time | 2024-06-01 | 264 | 2023-09-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45853687 | T2 DI PHILO JCT ELK 28/8 RPL TIED | ICW
LC | 126314785 | 022/104 | T2 DI CRTN-MNDCN #1 22/104 RPR INSS | WILLITS | ETL.1330.INSL.CERA | 2023-06-07 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46102360 | T2 DI CRTN-MNDCN #1 22/104 RPR INSS | ICS
LC | 126326146 | 003/014 | T2 DI HMBLDT BY-HMBLDT #1 3/14 RPR STRT | EUREKA | ETL.1800.TOWR | 2023-06-09 | 2023-06-02 | 2024-03-11 | On-time | 2024-06-01 | 82 | 2024-06-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46074158 | T2 DI HMBLDT BY-HMBLDT #1 3/14 RPR STRT | ICQ
LC | 126314817 | 019/007 | T2 DI TRINITY-MAPLE CREEK 19/7 RPR JMPW | EUREKA | ETL.8170.INSL.NCER | 2023-06-07 | 2023-06-01 | 2024-06-19 | Late | 2024-05-31 | -19 | 2023-09-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46193765 | T2 DI TRINITY-MAPLE CREEK 19/7 RPR JMPW | ICW
LC | 126314819 | 019/007 | T2 DI TRINITY-MAPLE CREEK 19/7 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-07 | 2023-06-01 | 2024-06-18 | Late | 2024-05-31 | -18 | 2023-12-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096665 | T2 DI TRINITY-MAPLE CREEK 19/7 RPR GYWW | ICW
LC | 126327178 | 060/300 | T2 DI MALIN-RND MTN #2 60/300 RPR JUMS | TABLEMTN | ETL.6020.INSL.NCER | 2023-06-09 | 2023-06-02 | 2023-12-21 | On-time | 2024-06-01 | 163 | 2024-06-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46055618 | T2 DI MALIN-RND MTN #2 60/300 RPR JUMS | ICS
LC | 126314854 | 023/108 | T2 DI CORTINA-MENDO #1 23/108 RPR OPGW | WILLITS | ETL.1330.TOWR | 2023-06-07 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46266301 | T2 DI CORTINA-MENDO #1 23/108 RPR OPGW | ICS
LC | 126314857 | 028/000 | T2 DI TRINITY-MPL CRK 28/0 RMV VEG | TABLEMTN | ETL.8170.POLE.NWOD | 2023-06-07 | 2023-05-31 | 2024-07-02 | Late | 2024-05-30 | -33 | 2024-05-31 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126314924 | 010/085 | T2 DI WOODLEAF-PALERMO 010/085 RPL POLE | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-07 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525818 | T2 DI WOODLEAF-PALERMO 010/83 RPL STRW | 70Y
LC | 126327243 | 060/300 | T2 DI MALIN-RND MTN #2 60/300 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-06-09 | 2023-06-02 | 2024-01-22 | On-time | 2024-06-01 | 131 | 2024-06-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46076096 | T2 DI MALIN-RND MTN #2 60/300 RPR OPGW | ICS
LC | 126328139 | 016/011 | T2 DI FORT BRAGG-ELK 016/011 COTTER | WILLITS | ETL.2060.INSL.NCER | 2023-06-09 | 2023-06-02 | 2023-08-11 | On-time | 2024-06-01 | 295 | 2023-09-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45853691 | T2 DI FORT BRAGG-ELK 016/011 COTTER | ICW
LC | 126314979 | 043/840 | T2 EI HAT CRK #1-WESTWOD 43/840 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-07 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514323 | T2 EI HAT CRK #1-WESTWOD 43/840 RPL POLE | 70Y
LC | 126314984 | 019/012 | T2 DI TRNTY MPLE CRK 19/012 RMV VEG | TABLEMTN | ETL.8170.POLE.WOOD | 2023-06-07 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126314993 | 043/839 | T2 EI HAT CREEK #1-WSTWD 43/839 RPR INSW | TABLEMTN | ETL.7030.INSL.NCER | 2023-06-07 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079337 | T2 EI HAT CREEK #1-WSTWD 43/839 RPR INSW | ICW
LC | 126315002 | 043/830 | T2 EI HAT CRK #1-WSTWD 43/830 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-07 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514321 | T2 DI HAT CREEK #1-WSTWD 42/810 RPL STRW | 70Y
LC | 126315013 | 043/831 | T2 EI HAT CRK #1-WSTWD 43/831 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-07 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514321 | T2 DI HAT CREEK #1-WSTWD 42/810 RPL STRW | 70Y
LC | 126315031 | 055/273 | T2 DI MENDOCINO-REDBUD 55/273 RPL INSS | WILLITS | ETL.2410.INSL.CERA | 2023-06-07 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31676908 | DI MENDOCINO-REDBUD RPL INSS IN 3 TWRS | 93K
LC | 126315035 | 055/273 | T2 DI CORTINA-MEDCINO #1 55/273 RPR OPGW | WILLITS | ETL.1330.TOWR | 2023-06-07 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45864498 | T2 DI CORTINA-MEDCINO #1 55/273 RPR OPGW | ICS
LC | 126315081 | 020/008 | T2 DI TRINITY-MAPLE CREEK 20/8L RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-07 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503379 | T2 DI TRINITY-MAPLE CREEK 20/8R RPL STRW | 70Y
LC | 126315084 | 020/008 | T2 DI TRINITY-MAPLE CREEK 20/8C RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-07 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503379 | T2 DI TRINITY-MAPLE CREEK 20/8R RPL STRW | 70Y
LC | 126315085 | 020/008 | T2 DI TRINITY-MAPLE CREEK 20/8R RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-07 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503379 | T2 DI TRINITY-MAPLE CREEK 20/8R RPL STRW | 70Y
LC | 126328789 | 064/322 | T2 DI MALIN-RND MNTN #2 64/322 COTTER | TABLEMTN | ETL.6020.INSL.NCER | 2023-06-09 | 2023-06-02 | 2023-12-20 | On-time | 2024-06-01 | 164 | 2024-06-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45937180 | T2 DI MALIN-RND MNTN #2 64/322 COTTER | ICS
LC | 126330590 | 017/010 | T2 DI FRT BRGG-ELK 17/010 RPL STRW | WILLITS | ETL.2060.POLE.WOOD | 2023-06-09 | 2023-06-02 | 2024-03-15 | On-time | 2024-06-01 | 78 | 2024-06-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487710 | T2 EI FORT BRAGG-ELK 016/005 RPL POLE | 70Y
LC | 126315196 | 024/008 | T2 DI TRNTY-MPL CRK 024/008 RPR CRSW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-07 | 2023-06-01 | 2024-06-18 | Late | 2024-05-31 | -18 | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46079371 | T2 DI TRNTY-MPL CRK 024/008 RPR CRSW | ICW
LC | 126315198 | 024/008 | T2 DI TRNTY-MPL CRK 024/008 RPL HRDD | EUREKA | ETL.8170.POLE.WOOD | 2023-06-07 | 2023-06-01 | 2024-06-18 | Late | 2024-05-31 | -18 | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46079371 | T2 DI TRNTY-MPL CRK 024/008 RPR CRSW | ICW
LC | 126315244 | 020/096 | T2 DI CRTNA-MNDCNO #1 20/096 RPR OPGW | WILLITS | ETL.1330.TOWR | 2023-06-07 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46102363 | T2 DI CRTNA-MNDCNO #1 20/096 RPR OPGW | ICS
LC | 126315247 | 027/006 | T2 DI TRNTY-MPL CRK 27/6R RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-07 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504077 | T2 DI TRNTY-MPL CRK 27/6R RPL POLE | 70Y
LC | 126330715 | 013/005 | T2 DI PHILO JCT-ELK-ELK 13/05 RPR STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-06-09 | 2023-06-02 | 2024-04-30 | On-time | 2024-06-01 | 32 | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46090347 | T2 DI PHILO JCT-ELK-ELK 13/05 RPR STRW | ICW
LC | 126315280 | 012/140 | T2 DI DRUM-SUMMIT #2 12/140L RPR STRW | SACTO | ETL.1450.POLE.WDPS | 2023-06-07 | 2023-05-31 | 2024-06-17 | Late | 2024-05-30 | -18 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46101333 | T2 DI DRUM-SUMMIT #2 012/140L RPR POLE | ICW
LC | 126315281 | 012/140 | T2 DI DRUM-SUMMIT #2 12/140R RPR STRW | SACTO | ETL.1450.POLE.WDPS | 2023-06-07 | 2023-05-31 | 2024-06-17 | Late | 2024-05-30 | -18 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46101334 | T2 DI DRUM-SUMMIT #2 012/140R RPR POLE | ICW
LC | 126315290 | 025/000 | T2 DI TRNTY-MPL CRK 25/00L RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-07 | 2023-06-01 |  | Late | 2024-05-31 |  | 2023-12-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503777 | T2 DI TRNTY-MPL CRK 25/00R RPR STRW | 70Y
LC | 126315291 | 025/000 | T2 DI TRNTY-MPL CRK 25/00C RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-07 | 2023-06-01 |  | Late | 2024-05-31 |  | 2023-12-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503777 | T2 DI TRNTY-MPL CRK 25/00R RPR STRW | 70Y
LC | 126315292 | 025/000 | T2 DI TRNTY-MPL CRK 25/00R RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-07 | 2023-06-01 |  | Late | 2024-05-31 |  | 2023-12-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503777 | T2 DI TRNTY-MPL CRK 25/00R RPR STRW | 70Y
LC | 126315300 | 027/003 | T2 DI TRIN MAPLE CRK 027/003 REFRAME | EUREKA | ETL.8170.POLE.WOOD | 2023-06-07 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35504069 | T2 DI TRIN MAPLE CRK 027/003 REFRAME | 93E
LC | 126315305 | 027/003 | T2 DI TRIN MAPLE CRK 27/3 RPR ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-07 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46172035 | T2 DI TRIN MAPLE CRK 027/003 RPR ANCW | ICW
LC | 126315311 | 026/003 | T2 DI TRINITY-MC 26/3 RPR ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-07 | 2023-06-01 | 2024-06-20 | Late | 2024-05-31 | -20 | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46170565 | T2 DI TRINITY-MC 26/3 RPR ANCW | ICW
LC | 126315315 | 026/003 | T2 DI TRINITY-MC 26/3 RPL TIED | EUREKA | ETL.8170.INSL.CERA | 2023-06-07 | 2023-06-01 | 2024-06-20 | Late | 2024-05-31 | -20 | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46170565 | T2 DI TRINITY-MC 26/3 RPR ANCW | ICW
LC | 126315316 | 026/003 | T2 DI TRNTY-MPLE CREEK 26/3 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-07 | 2023-06-01 | 2024-06-20 | Late | 2024-05-31 | -20 | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170565 | T2 DI TRINITY-MC 26/3 RPR ANCW | ICW
LC | 126315323 | 005/050 | T2 DI WOODLEAF-PALERMO 06/50L RPR GYWW | TABLEMTN | ETL.4220.POLE.STPS | 2023-06-07 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46073744 | T2 DI WOODLEAF-PALERMO 06/50L RPR GYWW | ICW
LC | 126330716 | 013/005 | T2 DI PHILO JCT-ELK-ELK 13/05 RPR GYWW | WILLITS | ETL.7780.POLE.WOOD | 2023-06-09 | 2023-06-02 | 2024-04-30 | On-time | 2024-06-01 | 32 | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45853695 | T2 DI PHILO JCT-ELK-ELK 13/05 RPR GYWW | ICW
LC | 126315346 | 018/012 | T2 DI TRNTY MPLE CRK 18/012 RMV VEG | TABLEMTN | ETL.8170.POLE.WOOD | 2023-06-07 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126315374 | 058/285 | T2 DI CORTINA-MNDCINO #1 58/285 RPR OPGW | WILLITS | ETL.1330.TOWR | 2023-06-07 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46234701 | T2 DI CORTINA-MNDCINO #1 58/285 RPR OPGW | ICS
LC | 126315392 | 026/004 | T2 DI TRINITY-MPL CRK 26/4R RPL HRDD | EUREKA | ETL.8170.POLE.WDPS | 2023-06-07 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46170566 | T2 DI TRINITY-MC 26/4R RPL HRDD | ICW
LC | 126315393 | 026/004 | T2 DI TRINITY-MPL CRK 26/4C RPL HRDD | EUREKA | ETL.8170.POLE.WDPS | 2023-06-07 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46170566 | T2 DI TRINITY-MC 26/4R RPL HRDD | ICW
LC | 126315397 | 026/004 | T2 DI TRINITY-MC 26/4 RPR JMPR | EUREKA | ETL.8170.INSL.NCER | 2023-06-07 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46170566 | T2 DI TRINITY-MC 26/4R RPL HRDD | ICW
LC | 126315398 | 026/004 | T2 DI TRINITY-MPL CRK 26/4L RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-07 | 2023-06-01 |  | Late | 2024-05-31 |  | 2023-12-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170566 | T2 DI TRINITY-MC 26/4R RPL HRDD | ICW
LC | 126315399 | 026/004 | T2 DI TRINITY-MPL CRK 26/4R RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-07 | 2023-06-01 |  | Late | 2024-05-31 |  | 2023-12-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170566 | T2 DI TRINITY-MC 26/4R RPL HRDD | ICW
LC | 126315401 | 023/008 | T2 DI TRINITY-MAPLE CRK 23/8 RPR JUMW | EUREKA | ETL.8170.INSL.NCER | 2023-06-07 | 2023-05-31 |  | Late | 2024-05-30 |  | 2023-08-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46193770 | T2 DI TRINITY-MAPLE CRK 23/8 RPR JMPW | ICW
LC | 126315412 | 011/137 | T2 DI DRUM-SUMMIT #1 11/137R RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2023-06-07 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101335 | T2 DI DRUM-SUMMIT #1 11/137R RPR GYWW | ICW
LC | 126315430 | 026/004 | T2 DI TRINITY-MPL CRK 26/4C RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-07 | 2023-06-01 |  | Late | 2024-05-31 |  | 2023-12-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170566 | T2 DI TRINITY-MC 26/4R RPL HRDD | ICW
LC | 126315435 | 026/004 | T2 DI TRINITY-MC 26/4 RPR INSW | EUREKA | ETL.8170.INSL.NCER | 2023-06-07 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46170566 | T2 DI TRINITY-MC 26/4R RPL HRDD | ICW
LC | 126330831 | 017/003 | T2 DI FORT BRAGG-ELK 017/003 COTTER | WILLITS | ETL.2060.INSL.CERA | 2023-06-09 | 2023-06-02 | 2023-08-11 | On-time | 2024-06-01 | 295 | 2023-09-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45853689 | T2 DI FORT BRAGG-ELK 017/003 COTTER | ICW
LC | 126330924 | 017/004 | T2 DI FORT BRAGG-ELK 017/004 RPR INSW | WILLITS | ETL.2060.INSL.CERA | 2023-06-09 | 2023-06-02 | 2023-08-11 | On-time | 2024-06-01 | 295 | 2023-09-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45853688 | T2 DI FORT BRAGG-ELK 017/004 RPR INSW | ICW
LC | 126315905 | 014/279 | T2 DI CARIBOU-WESTWOOD 014/279 RPR GYWW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-08 | 2023-06-07 |  | Late | 2024-06-06 |  | 2023-12-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079333 | T2 DI CARIBOU-WESTWOOD 014/279 RPR GYWW | ICW
LC | 126315906 | 014/279 | T2 DI CARIBOU-WESTWOOD 014/279 RPL HRDW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-08 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46079334 | T2 DI CARIBOU-WESTWOOD 014/279 RPL HRDW | ICW
LC | 126315978 | 019/000 | T2 DI TRNTY MPLE CRK 19/000 RMV VEG | TABLEMTN | ETL.8170.POLE.STPS | 2023-06-08 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126316044 | 027/007 | T2 DI TRNTY MPLE CRK 27/7 RPL GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-08 | 2023-05-31 | 2024-06-18 | Late | 2024-05-30 | -19 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 46172038 | T2 DI TRNTY MPLE CRK 27/007 RPR GYWW | ICW
LC | 126331145 | 061/308 | T2 DI MLN-RND MTN #2 61/308 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-06-09 | 2023-06-02 | 2024-01-23 | On-time | 2024-06-01 | 130 | 2024-06-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46076098 | T2 DI MLN-RND MTN #2 61/308 RPR SHLS | ICS
LC | 126316155 | 036/175 | T2 DI CRTNA MNDCNO#1 36/175 RPR OPGW | WILLITS | ETL.1330.TOWR | 2023-06-08 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45845924 | T2 DI CRTNA MNDCNO#1 36/175 RPR SHLS | ICS
LC | 126316529 | 016/077 | T2 DI EGL RCK-CRTN 16/077 COA | WILLITS | ETL.1470.INSL.CERA | 2023-06-08 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46102364 | T2 DI CRTNA MNDCNO#1 16/077 RPR INSS | ICS
LC | 126316586 | 016/077 | T2 DI CRTNA MNDCNO#1 16/077 RPL INSS | WILLITS | ETL.1330.INSL.CERA | 2023-06-08 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35549336 | T2 DI CRTNA MNDCNO#1 16/077 RPL INSS | 93K
LC | 126317577 | 024/006 | T2 WV RIO DEL JCT-BRDGVLE 24/6 RPR SPLW | EUREKA | ETL.7850.INSL.NCER | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 46171114 | T2 WV RIO DEL JCT-BRDGVLE 24/06 RPR SPLW | ICW
LC | 126331156 | 016/004 | T2 DI FORT BRAGG-ELK 016/004 RPR GYWW | WILLITS | ETL.2060.POLE.WOOD | 2023-06-09 | 2023-06-02 | 2024-03-14 | On-time | 2024-06-01 | 79 | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46090349 | T2 DI FORT BRAGG-ELK 016/004 RPR GYWW | ICW
LC | 126340919 | 020/009 | T2 DI PHILO JCT-ELK 20/9 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-06-10 | 2023-06-02 | 2024-05-20 | On-time | 2024-06-01 | 12 | 2024-06-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35522270 | T2 DI PHILO JCT-ELK 20/9 RPL POLE | 70Y
LC | 126341288 | 025/008 | T2 DI PHILO JCT ELK 25/8C RPR GYWW | WILLITS | ETL.7780.POLE.WDPS | 2023-06-10 | 2023-06-02 | 2024-05-21 | On-time | 2024-06-01 | 11 | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213840 | T2 DI PHILO JCT ELK 25/8C RPR GYWW | ICW
LC | 126317910 | A008/176 | T2 EI CSCD-BTN-DSCHTS A008/176 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521779 | T2 EI CSCD-BTN-DSCHTS A008/176 RPL STRW | 70Y
LC | 126318001 | 022/004 | T2 TRINITY-MAPLE CREEK 022/004 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31652104 | T2 TRINITY-MAPLE CREEK 022/004 RPL POLE | 70Y
LC | 126318063 | 027/005 | T2 DI TRNTY MPLE CRK 27/005C RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-08 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504072 | T2 DI TRNTY MPLE CRK 27/005L RPL STRW | 70Y
LC | 126318068 | 027/005 | T2 DI TRNTY MPLE CRK 27/005R RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-08 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504072 | T2 DI TRNTY MPLE CRK 27/005L RPL STRW | 70Y
LC | 126318091 | 027/005 | T2 DI TRNTY MPLE CRK 27/005L RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-08 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504072 | T2 DI TRNTY MPLE CRK 27/005L RPL STRW | 70Y
LC | 126341569 | 013/001 | T2 DI PHILO JCT-ELK- 13/01 RPL INSW | WILLITS | ETL.7780.INSL.NCER | 2023-06-10 | 2023-06-02 | 2023-09-11 | On-time | 2024-06-01 | 264 | 2023-12-02 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31652554 | T2 DI PHILO JCT-ELK- 13/01 RPL INSW | 93I
LC | 126318440 | 009/082 | T2 DI WOODLEAF-PALERMO 009/082 RPL POLE | TABLEMTN | ETL.4220.POLE.WOOD | 2023-06-08 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525815 | T2 DI WOODLEAF-PALERMO 009/082 RPL POLE | 70Y
LC | 126341618 | 006/003 | T2 DI LAKEVILLE #1 06/03 RPR STRW | LAKEVLLE | ETL.7360.POLE.WOOD | 2023-06-10 | 2023-06-02 | 2024-05-18 | On-time | 2024-06-01 | 14 | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46073761 | T2 DI LAKEVILLE #1 06/03 RPR STRW | ICW
LC | 126318536 | 025/001 | T2 DI TRINITY-MAPLE CREEK 25/1R RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-08 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31651955 | T2 DI TRINITY-MAPLE CREEK 25/1L RPL POLE | 70Y
LC | 126318540 | 025/001 | T2 DI TRINITY-MAPLE CREEK 25/1C RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-08 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31651955 | T2 DI TRINITY-MAPLE CREEK 25/1L RPL POLE | 70Y
LC | 126318541 | 025/001 | T2 DI TRINITY-MAPLE CREEK 25/1L RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-08 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31651955 | T2 DI TRINITY-MAPLE CREEK 25/1L RPL POLE | 70Y
LC | 126341843 | 003/001 | T2 DI PHILO JCT-ELK 03/01 REFRAME | WILLITS | ETL.7780.POLE.NWOD | 2023-06-10 | 2023-06-02 | 2024-05-03 | On-time | 2024-06-01 | 29 | 2024-06-02 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35506672 | T2 DI PHILO JCT-ELK 03/01 REFRAME | 93E
LC | 126341851 | 042/183 | T2 DI COBURN-LA SW ST 42/183 RPR SHLS | MOSSLNDG | ETL.4460.TOWR | 2023-06-10 | 2023-06-02 | 2024-05-29 | On-time | 2024-06-01 | 3 | 2024-06-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46081721 | T2 DI COBURN-LA SW ST 42/183 RPR SHLS | ICS
LC | 126342032 | 037/163 | T2 DI CBRN-LASAGLS SS PNCH-37/163 BNT ST | MOSSLNDG | ETL.4460.TOWR | 2023-06-10 | 2023-06-02 | 2023-07-10 | On-time | 2024-06-01 | 327 | 2023-09-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45881312 | T2 DI CBRN-LASAGLS SS PNCH-37/163 BNT ST | ICQ
LC | 126319321 | 028/134 | T2 DI MENDOCINO REDBUD#1 28/134 RPR INSS | WILLITS | ETL.2410.INSL.CERA | 2023-06-08 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46102365 | T2 DI MENDOCINO REDBUD#1 28/134 RPR INSS | ICS
LC | 126319492 | 025/004 | T2 DI TRNTY-MPLE CREEK 25/4 RPR JMPW | EUREKA | ETL.8170.INSL.NCER | 2023-06-08 | 2023-06-01 |  | Late | 2024-05-31 |  | 2023-09-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46193760 | T2 DI TRNTY-MPL CREEK 025/004 RPR JMPW | ICW
LC | 126342349 | 014/303 | T2 DI LAKEVLL#2 14/303 RPR GYWW | LAKEVLLE | ETL.7340.POLE.WOOD | 2023-06-10 | 2023-06-02 | 2024-04-19 | On-time | 2024-06-01 | 43 | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096617 | T2 DI LAKEVLL#2 14/303 RPR GYWW | ICW
LC | 126342789 | 013/295B | T2 DI SALINAS-LAURELES 13/295B RPR STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-10 | 2023-06-02 | 2024-02-23 | On-time | 2024-06-01 | 99 | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081307 | T2 DI SALINAS-LAURELES 13/295B RPR STRW | ICW
LC | 126319634 | 031/611 | T2 EI HAT CRK #1-WSTWD 31/611 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-06-19 | Late | 2024-06-07 | -12 | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514160 | T2 DI HAT CRK#1 WSTWD 31/610 RPL POLE | 70Y
LC | 126319637 | 031/612 | T2 EI HAT CRK #1-WSTWD 31/612 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-06-19 | Late | 2024-06-07 | -12 | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514160 | T2 DI HAT CRK#1 WSTWD 31/610 RPL POLE | 70Y
LC | 126319639 | 031/609 | T2 EI HAT CRK #1-WSTWD 31/609 RPR STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-06-19 | Late | 2024-06-07 | -12 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46079353 | T2 EI HAT CRK #1-WSTWD 31/609 RPR STRW | ICW
LC | 126319731 | 031/605 | T2 EI HAT CRK #1-WSTWD 31/605 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-06-19 | Late | 2024-06-07 | -12 | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514139 | T2 EI HAT CRK #1-WSTWD 31/605 RPL STRW | 70Y
LC | 126319740 | 031/604 | T2 EI HAT CRK #1-WSTWD 31/604 RPR STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-06-19 | Late | 2024-06-07 | -12 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46079352 | T2 EI HAT CRK #1-WSTWD 31/604 RPR STRW | ICW
LC | 126319743 | 031/601 | T2 EI HT CRK #1-WESTWOOD 31/601 RMV VEG | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126319820 | A008/177 | T2 EI CSCD-BTN-DSCHTS A008/177 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521821 | T2 EI CSCD-BTN-DSCHTS A008/177 RPL STRW | 70Y
LC | 126320256 | 014/001 | T2 EI HMBLDT BY-RO DLL JCT 14/1 RPL POLE | EUREKA | ETL.7100.POLE.WOOD | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487394 | T2 EI HMBLDT BY-RO DLL JCT 14/1 RPL POLE | 70Y
LC | 126342892 | 013/295A | T2 DI SALINAS-LAURELES 13/295A RMV VEG | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-10 | 2023-06-02 | 2024-04-12 | On-time | 2024-06-01 | 50 | 2024-06-02 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126320385 | A008/181 | T2 EI CSCD-BNTN-DSCTS A008/181 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35521821 | T2 EI CSCD-BTN-DSCHTS A008/177 RPL STRW | 70Y
LC | 126342896 | 003/017 | T2 DI HUMBLT BAY-HUM#1 3/17 RPL INSS | EUREKA | ETL.1800.INSL | 2023-06-10 | 2023-06-02 | 2024-03-13 | On-time | 2024-06-01 | 80 | 2024-06-02 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510808 | T2 DI HUMBLT BAY-HUM#1 3/17 RPL INSS | 93K
LC | 126320566 | 031/149 | T2 DI CRTNA MNDCNO #1 31/149 RPR OPGW | WILLITS | ETL.1330.TOWR | 2023-06-08 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45845926 | T2 DI CRTNA MNDCNO #1 31/149 RPR SHLS | ICS
LC | 126320598 | 014/000 | T2 EI HMBLDT BY-RO DLL JCT 14/0 RMV VEG | EUREKA | ETL.7100.POLE.WOOD | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 932 | TLR | PATR | E - Schd Compl Yr 0 | Open | TR2 | Brush Fuel | Road | Remove | 46102404 | T2 EI HMBLDT BY-RO DLL JCT 14/0 RMV VEG | CHS
LC | 126320599 | 014/000 | T2 EI HMBLDT BY-RO DLL JCT 14/0 RMV VEG | EUREKA | ETL.7100.POLE.WOOD | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126345181 | 004/019 | T2 DI HUMBLT BAY HMBLT#1 04/19 BNT STEEL | EUREKA | ETL.1800.TOWR | 2023-06-10 | 2023-06-02 | 2024-03-13 | On-time | 2024-06-01 | 80 | 2024-06-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46074159 | T2 DI HUMBLT BAY HMBLT#1 04/19 BNT STEEL | ICQ
LC | 126345239 | 041/176 | T2 DI CBRN LS AGULS SWSTA 41/176 RPR SHL | MOSSLNDG | ETL.4460.TOWR | 2023-06-10 | 2023-06-02 | 2024-05-30 | On-time | 2024-06-01 | 2 | 2024-06-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46081723 | T2 DI CBRN LS AGULS SWSTA 41/176 RPR SHL | ICS
LC | 126320763 | 033/159 | T2 DI MENDOCINO-REDBUD 33/159 RPR INSS | WILLITS | ETL.2410.INSL.CERA | 2023-06-08 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46102366 | T2 DI MENDOCINO-REDBUD 33/159 RPR INSS | ICS
LC | 126346087 | 062/311 | T2 DI MALIN-ROUND MNTN#2 62/311 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-06-11 | 2023-06-02 | 2024-01-23 | On-time | 2024-06-01 | 130 | 2024-06-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46076099 | T2 DI MALIN-ROUND MNTN#2 62/311 RPR OPGW | ICS
LC | 126346166 | 092/470C | T2 DI MALIN-RND MNTN#2 92/470C RPR ANCS | TABLEMTN | ETL.6020.TOWR | 2023-06-11 | 2023-06-02 | 2023-09-18 | On-time | 2024-06-01 | 257 | 2024-06-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45855683 | T2 DI MALIN-RND MNTN#2 92/470C RPR ANCS | ICS
LC | 126347129 | 002/027A | T2 DI MNTN QUARRIES TAP 2/27A COTR KEY | SACTO | ETL.6991.INSL.NCER | 2023-06-11 | 2023-06-02 | 2023-12-04 | On-time | 2024-06-01 | 180 | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46077559 | T2 DI MNTN QUARRIES TAP 2/27A COTR KEY | ICW
LC | 126347360 | 073/373 | T2 DI MLIN-RND MT #2 73/373 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-06-11 | 2023-06-02 | 2024-01-22 | On-time | 2024-06-01 | 131 | 2024-06-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46076160 | T2 DI MLIN-RND MT #2 73/373 RPR OPGW | ICS
LC | 126348327 | 017/008 | T2 DI FRT BRG ELK 17/008 COMPLETE | WILLITS | ETL.2060.POLE.WOOD | 2023-06-11 | 2023-06-02 | 2024-03-15 | On-time | 2024-06-01 | 78 | 2024-06-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487710 | T2 EI FORT BRAGG-ELK 016/005 RPL POLE | 70Y
LC | 126350132 | 060/299 | T2 DI MLIN-ROUND MTN #2 060/299 COTTER | TABLEMTN | ETL.6020.INSL.NCER | 2023-06-12 | 2023-06-02 | 2023-12-20 | On-time | 2024-06-01 | 164 | 2024-06-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46055617 | T2 DI MLIN-ROUND MTN #2 060/299 COTTER | ICS
LC | 126350273 | 060/298 | T2 DI MALIN-ROUND MTN #2 60/298 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-06-12 | 2023-06-02 | 2024-01-22 | On-time | 2024-06-01 | 131 | 2024-06-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46076095 | T2 DI MALIN-ROUND MTN #2 60/298 RPR OPGW | ICS
LC | 126320974 | 024/003 | T2 DI TRNTY MPLE CRK 24/003 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-08 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503761 | T2 DI TRNTY MPLE CRK 24/003 RPL STRW | 70Y
LC | 126350274 | 060/301 | T2 DI MALIN RND MTN #2 60/301 RPR OPGW | TABLEMTN | ETL.6020.INSL.NCER | 2023-06-12 | 2023-06-02 | 2024-01-22 | On-time | 2024-06-01 | 131 | 2024-06-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46076097 | T2 DI MALIN RND MTN #2 60/301 RPR OPGW | ICS
LC | 126351439 | 059/294 | T2 DI MALIN-ROUND MTN #2 59/294 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-06-12 | 2023-06-02 | 2024-01-22 | On-time | 2024-06-01 | 131 | 2024-06-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46076093 | T2 DI MALIN-ROUND MTN #2 59/294 RPR OPGW | ICS
LC | 126451514 | 011/100 | T2 EI CRAG VIEW-CASCADE 11/100R RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-06-26 | 2023-06-02 | 2024-02-28 | On-time | 2024-06-01 | 94 | 2024-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076669 | T2 EI CRAG VIEW-CASCADE 11/100R RPR GYWW | ICW
LC | 126451515 | 011/100 | T2 EI CRAG VIEW-CASCADE 11/100C RPR GYWW | TABLEMTN | ETL.1350.POLE.STPS | 2023-06-26 | 2023-06-02 | 2024-02-28 | On-time | 2024-06-01 | 94 | 2024-06-02 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076670 | T2 EI CRAG VIEW-CASCADE 11/100C RPR GYWW | ICW
LC | 126283701 | 011/087 | T2 EI PIT#4-ROUND MTN 11/87 RPR GYWW | TABLEMTN | ETL.5440.POLE.STPS | 2023-06-03 | 2023-06-03 | 2024-05-17 | On-time | 2024-06-02 | 16 | 2024-06-03 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46076087 | T2 EI PIT#4-ROUND MTN 11/87 RPR GYWW | ICS
LC | 126283776 | 010/086A | T2 EI PIT #6 JCT-RND MTN 10/86A RPR GYWW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-06-03 | 2023-06-03 | 2024-05-17 | On-time | 2024-06-02 | 16 | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076172 | T2 EI PIT #6 JCT-RND MTN 10/86A RPR GYWW | ICW
LC | 126321290 | 070/000 | T2 EI HUMBOLDT-TRINITY 070/000L RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505973 | T2 EI HUMBOLDT-TRINITY 070/000L RPL STRW | 70Y
LC | 126283778 | 011/093 | T2 EI PARADISE-TABLE MTN 11/093 RPL INSW | TABLEMTN | ETL.4316.INSL.CERA | 2023-06-03 | 2023-06-03 | 2024-01-29 | On-time | 2024-06-02 | 125 | 2024-06-03 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672700 | T2 EI PARADISE-TABLE MTN 11/093 RPL INSW | 93K
LC | 126321303 | 070/000 | T2 EI HUMBOLDT-TRINITY 070/000R RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505973 | T2 EI HUMBOLDT-TRINITY 070/000L RPL STRW | 70Y
LC | 126321309 | 008/208 | T2 EI CTTNWD-BNTN #1 008/208 RPL POLE | TABLEMTN | ETL.6640.POLE.WOOD | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521933 | T2 EI CTTNWD-BNTN #1 008/208 RPL POLE | 70Y
LC | 126321499 | 008/207 | T2 EI COTTONWOOD-BENTON 008/207 RMV VEG | TABLEMTN | ETL.6640.POLE.WOOD | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Trim
LC | 126321694 | 019/001 | T2 DI TRNTY MPLE CRK 19/001 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-08 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35502985 | T2 DI TRNTY MPLE CRK 19/001 RPL STRW | 70Y
LC | 126283959 | 027/176 | T2 EI OE-RIO OSO-RIO OSO 27/176 RPL INSS | TABLEMTN | ETL.5540.INSL.CERA | 2023-06-03 | 2023-06-03 | 2024-01-29 | On-time | 2024-06-02 | 125 | 2024-06-03 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672704 | T2 EI POE-RIO OSO 5TWR RPL INSS | 93K
LC | 126322008 | 043/010 | T2 EI TRINITY-MAPLE CRK 43/10 GO95 RPL P | EUREKA | ETL.8170.POLE.WOOD | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35529177 | T2 EI TRINITY-MAPLE CRK 43/10 GO95 RPL P | 93G
LC | 126322009 | 044/004 | T2 EI TRINITY-MAPLE CREEK 44/4 RPR INSW | EUREKA | ETL.8170.INSL.NCER | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46096676 | T2 EI TRINITY-MAPLE CREEK 44/4 RPR INSW | ICW
LC | 126322030 | 004/006 | T2 MNDCNO-PHLO JCT-HPLND 4/6 GO95 CLEAR | WILLITS | ETL.7520.POLE.NWOD | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654784 | T2 MNDCNO-PHLO JCT-HPLND 4/6 GO95 CLEAR | 93G
LC | 126285199 | 011/096A | T2 EI PARADISE-TABLE MTN 11/96A INS DAMS | TABLEMTN | ETL.4316.INSL.NCER | 2023-06-03 | 2023-06-03 | 2024-01-26 | On-time | 2024-06-02 | 128 | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46076671 | T2 EI PARADISE-TABLE MTN 11/96A INS DAMS | ICW
LC | 126322084 | 009/048 | T2 DI EAGLE RCK-CRTNA 9/48 RPR CNDS | SACTO | ETL.1470.INSL.CERA | 2023-06-08 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46079141 | T2 DI EAGLE RCK-CRTNA 9/48 RPR CNDS | ICS
LC | 126322096 | 026/127 | T2 DI CORTINA-MENDO#1 26/127 RPL INSS | WILLITS | ETL.1330.INSL.CERA | 2023-06-08 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31676905 | EI CORTINA-MENDOCN #1 RPL INSS IN 5 TWRS | 93K
LC | 126285639 | 027/004B | T2 EI MONTE RIO-FORT ROSS 27/4B RPR POLE | LAKEVLLE | ETL.6979.POLE.WOOD | 2023-06-03 | 2023-06-03 | 2023-08-10 | On-time | 2024-06-02 | 297 | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45575374 | T2 EI MONTE RIO-FORT ROSS 27/4C RPR WDPK | ICW
LC | 126285728 | 027/004C | T2 EI MONTE RIO-FORT ROSS 27/4C RPR GYWW | LAKEVLLE | ETL.6979.POLE.WOOD | 2023-06-03 | 2023-06-03 | 2023-08-10 | On-time | 2024-06-02 | 297 | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45575374 | T2 EI MONTE RIO-FORT ROSS 27/4C RPR WDPK | ICW
LC | 126286175 | 012/099 | T2 EI PARADISE-TABL MTN 12/099 INS DAMPS | TABLEMTN | ETL.4316.INSL.NCER | 2023-06-03 | 2023-06-03 | 2024-01-29 | On-time | 2024-06-02 | 125 | 2024-06-03 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 46075855 | T2 EI PARADISE-TABL MTN 12/099 INS DAMPS | ICS
LC | 126286494 | 011/099A | T2 EI PARADISE-TABLE MTN 11/99A INS DAMS | TABLEMTN | ETL.4316.INSL.NCER | 2023-06-03 | 2023-06-03 | 2024-01-29 | On-time | 2024-06-02 | 125 | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46076672 | T2 EI PARADISE-TABLE MTN 11/99A INS DAMS | ICW
LC | 126287187 | 067/002C | T2 EI HUMBOLDT-TRINITY 67/2C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-03 | 2023-06-03 | 2024-05-14 | On-time | 2024-06-02 | 19 | 2023-12-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096535 | T2 EI HUMBOLDT-TRINITY 67/2A RPR GYWW | ICW
LC | 126287188 | 067/002A | T2 EI HUMBOLDT-TRINITY 67/2A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-03 | 2023-06-03 | 2024-05-14 | On-time | 2024-06-02 | 19 | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096535 | T2 EI HUMBOLDT-TRINITY 67/2A RPR GYWW | ICW
LC | 126287200 | 015/111A | T2 EI HELMS-GREGG #1 015/111A RMV NEST | FRESNO | ETL.4870.TOWR | 2023-06-03 | 2023-06-03 | 2024-01-08 | On-time | 2024-06-02 | 146 | 2024-06-03 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46080578 | T2 EI HELMS-GREGG #1 015/111A RMV NEST | ICS
LC | 126322453 | 067/336 | T2 EI MALIN-ROUND MTN #2 67/336 RPR ANCT | TABLEMTN | ETL.6020.TOWR | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Tower | Repair | 46257549 | T2 EI MALIN-ROUND MTN #2 67/336 RPR ANCS | ICQ
LC | 126287206 | 067/002B | T2 EI HUMBOLDT-TRINITY 67/2B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-03 | 2023-06-03 | 2024-05-14 | On-time | 2024-06-02 | 19 | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096535 | T2 EI HUMBOLDT-TRINITY 67/2A RPR GYWW | ICW
LC | 126322522 | 060/297 | T2 DI CORTINA-MNDCINO #1 60/297 RPR FOND | WILLITS | ETL.1330.TOWR | 2023-06-08 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46102368 | T2 DI CORTINA-MNDCINO #1 60/297 RPR FOND | ICQ
LC | 126322530 | 044/011 | T2 EI TRINITY-MPLE CREEK 44/11R RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506423 | T2 EI TRINITY-MPLE CREEK 44/11R RPL POLE | 70Y
LC | 126322531 | 045/004 | T2 EI TRNTY MPL CRK 45/004R RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506431 | T2 EI TRNTY MPL CRK 45/004R RPL POLE | 70Y
LC | 126322534 | 044/011 | T2 EI TRINITY-MPLE CREEK 44/11L RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506423 | T2 EI TRINITY-MPLE CREEK 44/11R RPL POLE | 70Y
LC | 126322540 | 045/004 | T2 EI TRNTY MPL CRK 45/004L RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506431 | T2 EI TRNTY MPL CRK 45/004R RPL POLE | 70Y
LC | 126322541 | 044/011 | T2 EI TRINITY-MPLE CREEK 44/11C RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506423 | T2 EI TRINITY-MPLE CREEK 44/11R RPL POLE | 70Y
LC | 126322545 | 045/003 | T2 EI TRNTY-MPL CRK 45/3 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506428 | T2 EI TRNTY-MPL CRK 45/3 RPL STRW | 70Y
LC | 126322552 | 026/008 | T2 DI TRINITY-MAPLE CRK 26/8R RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-08 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170567 | T2 DI TRINITY-MAPLE CRK 26/8 COTTER | ICW
LC | 126322554 | 026/008 | T2 DI TRINITY-MAPLE CRK 26/8L RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-08 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46170567 | T2 DI TRINITY-MAPLE CRK 26/8 COTTER | ICW
LC | 126322570 | 038/745 | T2 EI HT CRK #1-WSTWD 38/745 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35514276 | T2 EI HT CRK #1-WESTWOOD 38/737 REFRAME | 93E
LC | 126322585 | 028/001 | T2 DI TRNTY-MAPLE CRK 28/01 RPR ANCW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-08 | 2023-05-31 | 2024-06-13 | Late | 2024-05-30 | -14 | 2024-05-31 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46172081 | T2 DI TRNTY-MAPLE CRK 28/01 RPR ANCW | ICW
LC | 126322593 | 026/008 | T2 DI TRINITY-MAPLE CRK 26/8 COTTER | EUREKA | ETL.8170.INSL.NCER | 2023-06-08 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46170567 | T2 DI TRINITY-MAPLE CRK 26/8 COTTER | ICW
LC | 126322596 | 005/031 | T2 DI EAGLE ROCK-CORTINA 5/31 RPL INSS | SACTO | ETL.1470.INSL.CERA | 2023-06-08 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31676909 | T2 DI EAGLE ROCK-CORTINA 7/37 RPL INSS | 93K
LC | 126287223 | 010/086C | T2 EI PIT #6 JCT-RND MTN 10/86C RPR GYWW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-06-03 | 2023-06-03 | 2024-05-17 | On-time | 2024-06-02 | 16 | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076173 | T2 EI PIT #6 JCT-RND MTN 10/86C RPR GYWW | ICW
LC | 126322713 | 054/267 | T2 DI MENDOCINO-REDBUD 054/267 RPL INSS | WILLITS | ETL.2410.INSL.CERA | 2023-06-08 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31676908 | DI MENDOCINO-REDBUD RPL INSS IN 3 TWRS | 93K
LC | 126287224 | 010/084 | T2 EI PIT#4-ROUND MTN 10/84L RPR GYWW | TABLEMTN | ETL.5440.POLE.STPS | 2023-06-03 | 2023-06-03 | 2024-01-24 | On-time | 2024-06-02 | 130 | 2024-06-03 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46076086 | T2 EI PIT#4-ROUND MTN 10/84L RPR GYWW | ICS
LC | 126322793 | 026/000 | T2 DI TRNTY-MPLE CREEK 26/0 RPR JMPW | EUREKA | ETL.8170.INSL.NCER | 2023-06-08 | 2023-06-01 |  | Late | 2024-05-31 |  | 2023-09-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46190011 | T2 DI TRINITY-MAPLE CREEK 26/0 RPR JMPW | ICW
LC | 126323001 | 013/054 | T2 EI TESLA-METCALF 13/54 RPR GYWT | CONCORD | ETL.6110.TOWR | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2023-12-08 | 543 | TLQ | CREW | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46080481 | T2 EI TESLA-METCALF 013/054 RPR GYWS | ICS
LC | 126323002 | 013/054 | T2 EI TESLA-METCALF 13/54 RPR ANCT | CONCORD | ETL.6110.TOWR | 2023-06-08 | 2023-06-08 |  | Late | 2024-06-07 |  | 2023-09-08 | 543 | TLQ | CREW | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Tower | Repair | 46080482 | T2 EI TESLA-METCALF 013/054 RPR ANCS | ICS
LC | 126288009 | 071/003 | T2 EI HMBLDT-TRINITY 71/003R RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-06-04 | 2023-06-03 | 2024-04-20 | On-time | 2024-06-02 | 43 | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171108 | T2 EI CTTNWD-HMBLDT 71/003R RPR GYWW | ICW
LC | 126288033 | 071/003 | T2 EI HMBLDT-TRINITY 71/003L RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-06-04 | 2023-06-03 | 2024-04-20 | On-time | 2024-06-02 | 43 | 2024-06-03 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171108 | T2 EI CTTNWD-HMBLDT 71/003R RPR GYWW | ICW
LC | 126324219 | 002/033 | T2 DI LAKEVILLE #1 2/33 RPL INSW | LAKEVLLE | ETL.7360.INSL | 2023-06-09 | 2023-06-03 | 2024-05-13 | On-time | 2024-06-02 | 20 | 2024-06-03 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35517037 | T2 DI LAKEVILLE #1 2/33 RPL INSW | 93I
LC | 126324240 | 016/319 | T2 DI SALINAS LAURELES 16/319 COA | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-09 | 2023-06-03 | 2024-05-13 | On-time | 2024-06-02 | 20 | 2024-06-03 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126324550 | 057/003A | T2 DI HUMBOLDT-TRINITY 57/3A COTTER | EUREKA | ETL.1820.INSL.NCER | 2023-06-09 | 2023-06-03 | 2024-03-26 | On-time | 2024-06-02 | 68 | 2024-06-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46096527 | T2 DI HUMBOLDT-TRINITY 57/3A COTTER | ICW
LC | 126324393 | 058/292 | T2 DI MALIN-RND MTN #2 58/292 RPL ANCT | TABLEMTN | ETL.6020.TOWR | 2023-06-09 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 93Z | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Tower | Replace | 31685781 | T2 DI MALIN-ROUND MTN #2 58/292 RPL ANCS | 93Z
LC | 126325535 | 056/006B | T2 DI HMBLDT-TRNTY 056/006B RPR ANCW | EUREKA | ETL.1820.POLE.WOOD | 2023-06-09 | 2023-06-03 | 2024-04-13 | On-time | 2024-06-02 | 50 | 2024-06-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46171103 | T2 DI HMBLDT-TRNTY 056/006A RPR ANCW | ICW
LC | 126328004 | 000/010 | T2 DI LAURELES OTTER 00/010 COTTER | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-06-09 | 2023-06-03 | 2023-07-02 | On-time | 2024-06-02 | 336 | 2023-09-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45858892 | T2 DI LAURELES OTTER 00/010 COTTER | ICW
LC | 126324672 | 011/138 | T2 DI DRUM-SUMMIT #2 11/138L RPR GYWW | SACTO | ETL.1450.POLE.WDPS | 2023-06-09 | 2023-06-01 | 2024-06-18 | Late | 2024-05-31 | -18 | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101338 | T2 DI DRUM-SUMMIT #2 11/138 RPR GYWW | ICW
LC | 126324673 | 011/138 | T2 DI DRUM-SUMMIT #2 11/138R RPR GYWW | SACTO | ETL.1450.POLE.WDPS | 2023-06-09 | 2023-06-01 | 2024-06-18 | Late | 2024-05-31 | -18 | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101339 | T2 DI DRUM-SUMMIT #2 11/138 RPR GYWW | ICW
LC | 126324674 | 011/138 | T2 DI DRUM-SUMMIT #2 11/138C RPR GYWW | SACTO | ETL.1450.POLE.WDPS | 2023-06-09 | 2023-06-01 | 2024-06-18 | Late | 2024-05-31 | -18 | 2024-06-01 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46101360 | T2 DI DRUM-SUMMIT #2 11/138 RPR GYWW | ICW
LC | 126328454 | 016/320 | T2 DI SALINAS LAURELES 16/320 COMPLETE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-09 | 2023-06-03 | 2023-11-27 | On-time | 2024-06-02 | 188 | 2023-12-03 | 372 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31653831 | T2 DI SALINAS LAURELES 16/320 RPL STRW | 70Y
LC | 126325349 | 028/001 | T2 DI PHILO JCT-ELK 28/1 RPL HRDW | WILLITS | ETL.7780.POLE.NWOD | 2023-06-09 | 2023-06-02 | 2024-06-08 | Late | 2024-06-01 | -7 | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46213818 | T2 DI PHILO JCT-ELK 028/001 RPL HRDW | ICW
LC | 126325377 | 002/057 | T2 EI CTTNWD-BENTON #1 2/57 RPL INSW | TABLEMTN | ETL.6640.POLE.WOOD | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35515942 | T2 EI CTTNWD-BENTON #1 2/57 RPL INSW | 93I
LC | 126328510 | 006/068 | T2 DI CLGT-SMRTVLL #2 6/068 RPL STRW | SACTO | ETL.6520.POLE.WOOD | 2023-06-09 | 2023-06-03 | 2024-05-01 | On-time | 2024-06-02 | 32 | 2024-06-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35481574 | T2 DI CLGT-SMRTVLL #2 6/068 RPL STRW | 70Y
LC | 126328847 | 056/006C | T2 DI HMBLDT-TRNTY 056/006C RPR ANCW | EUREKA | ETL.1820.POLE.WOOD | 2023-06-09 | 2023-06-03 | 2024-04-13 | On-time | 2024-06-02 | 50 | 2024-06-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46171103 | T2 DI HMBLDT-TRNTY 056/006A RPR ANCW | ICW
LC | 126325494 | 000/017 | T2 DI LAURELES OTTER 00/0017 RPL HRDD | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-06-09 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 630 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46081228 | T2 DI LAURELES OTTER 00/0017 RPL HRDD | ICW
LC | 126330730 | 056/006A | T2 DI HMBLDT-TRNTY 056/006A RPR ANCW | EUREKA | ETL.1820.POLE.WOOD | 2023-06-09 | 2023-06-03 | 2024-04-13 | On-time | 2024-06-02 | 50 | 2024-06-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46171103 | T2 DI HMBLDT-TRNTY 056/006A RPR ANCW | ICW
LC | 126325685 | 057/001B | T2 DI HMBLDT TRNTY 57/001B RPL POLE | EUREKA | ETL.1820.POLE.WOOD | 2023-06-09 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31656098 | T2 EI HUMBOLDT-TRINITY 57/1C RPL POLE | 70Y
LC | 126330893 | 003/016 | T2 DI HMBLDT BAY-HMBLDT #1 3/16 RPR STRT | EUREKA | ETL.1800.TOWR | 2023-06-09 | 2023-06-03 | 2024-03-11 | On-time | 2024-06-02 | 83 | 2024-06-03 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46075987 | T2 DI HMBLDT BAY-HMBLDT #1 3/16 RPR STRT | ICQ
LC | 126325721 | 028/008 | T2 DI PHILO JCT ELK 28/8 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-06-09 | 2023-06-02 | 2024-06-19 | Late | 2024-06-01 | -18 | 2024-06-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35522275 | T2 DI PHILO JCT ELK 28/8 RPL POLE | 70Y
LC | 126326117 | 005/038 | T2 DI SN LUS OBSPO-CYUCOS 5/38R RPL ANCW | PISMOBCH | ETL.9090.POLE.WDPS | 2023-06-09 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35520680 | T2 DI SAN LUIS O-CS 5/38R RPL ANCW | 93E
LC | 126326118 | 005/038 | T2 DI SAN LUIS O-CS 5/38 RPR INSW | PISMOBCH | ETL.9090.INSL.NCER | 2023-06-09 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46090159 | T2 DI SAN LUIS O-CS 5/38 RPR INSW | ICW
LC | 126326119 | 005/038 | T2 DI SAN LUIS O-CS 5/38C RPR STRW | PISMOBCH | ETL.9090.POLE.WDPS | 2023-06-09 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46090180 | T2 DI SAN LUIS O-CS 5/38C RPR STRW | ICW
LC | 126331170 | 001/036 | T2 DI JFFRSN-STNFRD 001/036 RPR ADSS | METCALF | ETL.7220.POLE.WOOD | 2023-06-09 | 2023-06-03 | 2023-11-07 | On-time | 2024-06-02 | 208 | 2024-06-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45997326 | T2 DI JFFRSN-STNFRD 001/036 RPR ADSS | ICW
LC | 126326154 | 000/012 | T2 DI LAURELES-OTTER 000/012 RMV VEG | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-06-09 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126326290 | 005/038 | T2 DI SAN LUIS O-CS 5/38L RPR STRW | PISMOBCH | ETL.9090.POLE.WDPS | 2023-06-09 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46090181 | T2 DI SAN LUIS O-CS 5/38L RPR STRW | ICW
LC | 126326291 | 005/038 | T2 DI SAN LUIS O-CS 5/38R RPR STRW | PISMOBCH | ETL.9090.POLE.WDPS | 2023-06-09 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46090182 | T2 DI SAN LUIS O-CS 5/38R RPR STRW | ICW
LC | 126326295 | 027/011 | T2 DI PHILO JCT ELK 27/11 RPR ANCW | WILLITS | ETL.7780.POLE.WOOD | 2023-06-09 | 2023-06-02 | 2024-06-05 | Late | 2024-06-01 | -4 | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46213819 | T2 DI PHILO JCT ELK 27/11 RPR ANCW | ICW
LC | 126326479 | 042/805 | T2 EI HT CRK #1-WSTWD 42/805 RPR GYWW | TABLEMTN | ETL.7030.POLE.NWOD | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091804 | T2 EI HT CRK #1-WSTWD 42/805 RPR GYWW | ICW
LC | 126342850 | 009/039 | T2 DI MNTA VSTA-JFRSN #2 09/039 RPL INSS | METCALF | ETL.5230.INSL | 2023-06-10 | 2023-06-03 | 2024-03-19 | On-time | 2024-06-02 | 75 | 2024-06-03 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674006 | T2 DI MONTA VISTA-JEFF #2 RPL INSS IN 7 | 93K
LC | 126326511 | 027/535 | T2 EI HT CREEK #1-WESTWD 27/535 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514124 | T2 EI HAT CREEK #1-WSTWD 27/521 RPL POLE | 70Y
LC | 126326513 | 027/536 | T2 EI HAT CRK #1-WESTWD 27/536 COMPLETE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-09 | 2023-06-09 | 2024-06-19 | Late | 2024-06-08 | -11 | 2024-06-09 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514124 | T2 EI HAT CREEK #1-WSTWD 27/521 RPL POLE | 70Y
LC | 126326521 | 027/528 | T2 EI HT CREEK #1-WESTWD 27/528 COMPLETE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-09 | 2023-06-09 | 2024-06-18 | Late | 2024-06-08 | -10 | 2024-06-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091803 | T2 EI HT CREEK #1-WESTWD 27/528 RPR WDPK | ICW
LC | 126343018 | 009/038 | T2 DI MNTA VSTA-JFFRSN #1 9/38 RPL INSS | METCALF | ETL.5220.INSL | 2023-06-10 | 2023-06-03 | 2024-01-05 | On-time | 2024-06-02 | 149 | 2024-06-03 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674005 | T2 DI MNT-VST-JFFRSN #1 RPL INSS IN 2 TW | 93K
LC | 126288104 | 063/460A | T2 EI BRDGEVLE-COTTNWD 63/460A UNBURY | EUREKA | ETL.1110.POLE.NWOD | 2023-06-04 | 2023-06-04 | 2024-04-16 | On-time | 2024-06-03 | 48 | 2024-06-04 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46102302 | T2 EI BRDGEVLE-COTTNWD 63/460A UNBURY | ICQ
LC | 126326661 | 011/381 | T2 EI SPAULDING-SUMMIT 11/381 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46127491 | T2 EI SPAULDING-SUMMIT 11/381 RPR GYWW | ICW
LC | 126326754 | 032/007 | T2 DI PHILO JCT ELK 32/7 RPL HRDW | WILLITS | ETL.7780.POLE.WOOD | 2023-06-09 | 2023-06-02 | 2024-06-20 | Late | 2024-06-01 | -19 | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46213816 | T2 DI PHILO JCT ELK 32/7 RPL HRDW | ICW
LC | 126326959 | 007/097 | T2 EI IGNACIO-BOLINAS #2 7/97 RPR IBWW | LAKEVLLE | ETL.7180.INSL.CERA | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2023-12-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 46222139 | T2 EI IGNACIO-BOLINAS #2 7/97 RPR IBWW | ICW
LC | 126288105 | 063/460C | T2 EI BRDGEVLE-COTTNWD 63/460C UNBURY | EUREKA | ETL.1110.POLE.NWOD | 2023-06-04 | 2023-06-04 | 2024-04-16 | On-time | 2024-06-03 | 48 | 2024-06-04 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46102303 | T2 EI BRDGEVLE-COTTNWD 63/460C UNBURY | ICQ
LC | 126288110 | 063/460B | T2 EI BRDGEVLE-COTTNWD 63/460B UNBURY | EUREKA | ETL.1110.POLE.NWOD | 2023-06-04 | 2023-06-04 | 2024-04-16 | On-time | 2024-06-03 | 48 | 2024-06-04 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46102304 | T2 EI BRDGEVLE-COTTNWD 63/460B UNBURY | ICQ
LC | 126289044 | :024/124 | T2 EI CRZY HRS CYN SLNS :24/124 RPL INSS | MOSSLNDG | ETL.2900.INSL.CERA | 2023-06-04 | 2023-06-04 | 2023-08-20 | On-time | 2024-06-03 | 288 | 2023-09-04 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31652121 | T2 CRZY HRS CNYN-SLINS :24/124 RPLC INSS | 93K
LC | 126292495 | T001/007 | T2 TULUCAY-NAPA #1 T1/7 RPL HDWW | LAKEVLLE | ETL.8180.POLE.WOOD | 2023-06-05 | 2023-06-05 | 2024-01-18 | On-time | 2024-06-04 | 138 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46096618 | T2 TULUCAY-NAPA #1 T1/7 RPL HDWW | ICW
LC | 126327273 | 056/279 | T2 DI CRTN-MNDCN #1 56/279 RPR STRT | WILLITS | ETL.1330.TOWR | 2023-06-09 | 2023-06-01 | 2024-06-04 | Late | 2024-05-31 | -4 | 2024-06-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46079143 | T2 DI CRTN-MNDCN #1 56/279 RPR STRT | ICQ
LC | 126293710 | 063/012 | T2 EI ELK-GUALALA 63/012 RPL HDWW | WILLITS | ETL.8410.INSL.NCER | 2023-06-05 | 2023-06-05 | 2024-01-30 | On-time | 2024-06-04 | 126 | 2024-06-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46079895 | T2 EI ELK-GUALALA 63/012 RPL HDWW | ICW
LC | 126295572 | 009/081 | T2 EI PARADISE-TABLE MTN 09/081 INS DMPS | TABLEMTN | ETL.4316.INSL.NCER | 2023-06-05 | 2023-06-05 | 2024-01-30 | On-time | 2024-06-04 | 126 | 2024-06-05 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 46079284 | T2 EI PARADISE-TABLE MTN 09/081 INS DMPS | ICS
LC | 126295811 | 074/000 | T2 EI HUMBOLDT-TRINITY 74/0R RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-06-05 | 2023-06-05 | 2024-05-14 | On-time | 2024-06-04 | 21 | 2024-06-05 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46096580 | T2 EI HUMBOLDT-TRINITY 74/0R RPR GYWW | ICS
LC | 126295812 | 074/000 | T2 EI HUMBOLDT-TRINITY 74/0C RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-06-05 | 2023-06-05 | 2024-05-14 | On-time | 2024-06-04 | 21 | 2024-06-05 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46096580 | T2 EI HUMBOLDT-TRINITY 74/0R RPR GYWW | ICS
LC | 126296054 | 051/207B | T2 EI DIABLO-GATES #1 51/207B RPR GYWT | PISMOBCH | ETL.5960.TOWR | 2023-06-05 | 2023-06-05 | 2024-05-15 | On-time | 2024-06-04 | 20 | 2024-06-05 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46175254 | T2 EI DIABLO-GATES #1 51/207B RPR GYWT | ICQ
LC | 126327639 | 003/071 | T2 DI CARIBOU-WTWD 3/71L RPR GYWW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-06-09 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076255 | T2 DI CARIBOU-WTWD 3/71L RPR GYWW | ICW
LC | 126327702 | 003/071 | T2 DI CARIBOU-WTWD 3/71R RPR GYWW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-06-09 | 2023-06-02 |  | Late | 2024-06-01 |  | 2023-12-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076256 | T2 DI CARIBOU-WTWD 3/71R RPR GYWW | ICW
LC | 126296613 | 008/050 | T2 BALCH-SANGER 08/50 RPR JMPS | FRESNO | ETL.1050.INSL.NCER | 2023-06-05 | 2023-06-05 | 2024-04-11 | On-time | 2024-06-04 | 54 | 2024-06-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46080514 | T2 BALCH-SANGER 08/50 RPR JMPS | ICS
LC | 126327886 | 013/286 | T2 DI SALINAS-LAURELES 13/286 RPR SPLW | MOSSLNDG | ETL.7930.INSL | 2023-06-09 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46081236 | T2 DI SALINAS-LAURELES 13/286 RPR SPLW | ICW
LC | 126296936 | 010/081C | T2 EI PIT #6 JCT-RND MTN 10/81C RPR GYWW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-06-05 | 2023-06-05 | 2024-01-18 | On-time | 2024-06-04 | 138 | 2024-06-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079287 | T2 EI PIT #6 JCT-RND MTN 10/81C RPR GYWW | ICW
LC | 126296944 | 010/081A | T2 EI PIT #6 JCT-RND MTN 10/81A RPR GYWW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-06-05 | 2023-06-05 | 2024-01-18 | On-time | 2024-06-04 | 138 | 2024-06-05 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46079285 | T2 EI PIT #6 JCT-RND MTN 10/81A RPR GYWW | ICS
LC | 126296947 | 010/081B | T2 EI PIT #6 JCT-RND MTN 10/81B RPR GYWW | TABLEMTN | ETL.5440.POLE.NWOD | 2023-06-05 | 2023-06-05 | 2024-01-16 | On-time | 2024-06-04 | 140 | 2024-06-05 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079286 | T2 EI PIT #6 JCT-RND MTN 10/81B RPR GYWW | ICW
LC | 126297115 | 006/127 | T2 EI KILARC-DESCHUTES 006/127 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-05 | 2023-06-05 | 2024-04-03 | On-time | 2024-06-04 | 62 | 2024-06-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515638 | T2 EI KILARC-DESCHUTES 006/127 RPL STRW | 70Y
LC | 126328125 | 049/211 | T2 DI CBRN LS AGLS SWSTA 49/211 RMV NEST | MOSSLNDG | ETL.4460.TOWR | 2023-06-09 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46081695 | T2 DI CBRN LS AGLS SWSTA 49/211 RMV NEST | ICS
LC | 126328129 | 049/211 | T2 DI CBRN LS AGLS SWSTA 49/211 RPL INSS | MOSSLNDG | ETL.4460.INSL | 2023-06-09 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513892 | T2 DI CBRN LS AGLS SWSTA 49/211 RPL INSS | 93K
LC | 126297379 | 006/128 | T2 EI KILARC-DESCHUTES 006/128 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-05 | 2023-06-05 | 2024-04-03 | On-time | 2024-06-04 | 62 | 2024-06-05 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515669 | T2 EI KILARC-DESCHUTES 006/128 RPL STRW | 70Y
LC | 126328147 | 006/077 | T2 EI HAT CREEK #1-PIT #1 06/077 RPL PL | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521450 | T2 EI HAT CREEK #1-PIT #1 06/076 RPL PL | 70Y
LC | 126328148 | 006/076 | T2 EI HAT CREEK #1-PIT #1 06/076 RPL PL | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521450 | T2 EI HAT CREEK #1-PIT #1 06/076 RPL PL | 70Y
LC | 126328315 | 011/374 | T2 EI SPAULDING-SUMMIT 11/374 RPR JMPW | SACTO | ETL.8060.INSL.NCER | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46127492 | T2 EI SPAULDING-SUMMIT 11/374 RPR JMPW | ICW
LC | 126298079 | 012/100 | T2 EI PARADISE-TABLE MTN 12/100 RPR CNDS | TABLEMTN | ETL.4316.INSL.NCER | 2023-06-05 | 2023-06-05 | 2024-01-29 | On-time | 2024-06-04 | 127 | 2024-06-05 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46079288 | T2 EI PARADISE-TABLE MTN 12/100 RPR CNDS | ICS
LC | 126326655 | 004/040 | T2 DI BCK CRK-RCK CRK-CRST 4/40 HANGER | TABLEMTN | ETL.4430.TOWR | 2023-06-09 | 2023-06-05 | 2024-01-15 | On-time | 2024-06-04 | 141 | 2024-06-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46028543 | T2 DI BCK CRK-RCK CRK-CRST 4/40 HANGER | ICQ
LC | 126326657 | 004/040 | T2 DI BCK CRK-RCK CRK-CRST 4/40 RPL INSS | TABLEMTN | ETL.4430.INSL.CERA | 2023-06-09 | 2023-06-05 | 2024-01-16 | On-time | 2024-06-04 | 140 | 2024-06-05 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672630 | T2 DI BUCKS CRK-ROCK CRK 02/27 RPL INSS | 93K
LC | 126327094 | 015/307 | T2 DI SALINAS LAURELES 15/307 COTTER | MOSSLNDG | ETL.7930.INSL.NCER | 2023-06-09 | 2023-06-05 | 2023-09-01 | On-time | 2024-06-04 | 277 | 2023-09-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45854259 | T2 DI SALINAS LAURELES 15/307 COTTER | ICW
LC | 126327099 | 014/303 | T2 DI SALINAS LAURELES 14/303 RPL HRDD | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-09 | 2023-06-05 | 2024-02-29 | On-time | 2024-06-04 | 96 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46081231 | T2 DI SALINAS LAURELES 14/303 RPL HRDD | ICW
LC | 126327364 | 031/167A | T2 DI EXCHQUR-INDN FLT 31/167A RPR CONN | FRESNO | ETL.8650.INSL.NCER | 2023-06-09 | 2023-06-05 | 2023-12-13 | On-time | 2024-06-04 | 174 | 2023-09-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45883708 | T2 DI EXCHQUR-INDN FLT 31/167A RPR CONN | ICS
LC | 126327500 | 001/003 | T2 DI LAURELES OTTER 01/003 RPR ANCW | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-06-09 | 2023-06-05 | 2024-01-17 | On-time | 2024-06-04 | 139 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46081233 | T2 DI LAURELES OTTER 01/003 RPR ANCW | ICW
LC | 126329226 | 015/005 | T2 DI LWR LK-HMSTK 15/5 RPL INSW | WILLITS | ETL.1481.INSL.CERA | 2023-06-09 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35488189 | T2 DI LWR LK-HMSTK 015/005 RLPC INSW | 93I
LC | 126327506 | 001/003 | T2 DI LAURELES OTTER 01/003 COTTER | MOSSLNDG | ETL.7380.INSL.NCER | 2023-06-09 | 2023-06-05 | 2024-01-17 | On-time | 2024-06-04 | 139 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081232 | T2 DI LAURELES OTTER 01/003 COTTER | ICW
LC | 126327968 | 030/158A | T2 DI EXCHQUR-INDN FLT 30/158A RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-06-09 | 2023-06-05 | 2023-12-14 | On-time | 2024-06-04 | 173 | 2023-09-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45854971 | T2 DI EXCHQUR-INDN FLT 30/158A RPR JMPS | ICS
LC | 126328081 | 030/158A | T2 DI EXCHQUR-INDN FLT 30/158A RPR INSS | FRESNO | ETL.8650.INSL.NCER | 2023-06-09 | 2023-06-05 | 2023-12-14 | On-time | 2024-06-04 | 173 | 2023-09-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45854972 | T2 DI EXCHQUR-INDN FLT 30/158A RPR INSS | ICS
LC | 126328333 | 002/000 | T2 DI LAURELES-OTTER 002/000 RPL POLE | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-06-09 | 2023-06-05 | 2024-01-31 | On-time | 2024-06-04 | 125 | 2024-06-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503052 | T2 DI LAURELES-OTTER 002/000 RPL POLE | 70Y
LC | 126329128 | 017/326B | T2 DI SALINAS-LAURELES 17/326B RPR CRSW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-09 | 2023-06-05 | 2023-10-20 | On-time | 2024-06-04 | 228 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45996744 | T2 DI SALINAS-LAURELES 17/326B RPR CRSW | ICW
LC | 126329223 | 017/326B | T2 DI SALINAS-LAURELES 17/326B RPR ANCW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-09 | 2023-06-05 | 2023-11-06 | On-time | 2024-06-04 | 211 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45996746 | T2 DI SALINAS-LAURELES 17/326B RPR ANCW | ICW
LC | 126329476 | 000/010 | T2 DI CLGTE SMRTVIL #2 00/10 RMV VEG | SACTO | ETL.6520.POLE.WOOD | 2023-06-09 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126329227 | 017/326B | T2 DI SALINAS-LAURELES 17/326B RPR STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-09 | 2023-06-05 | 2023-11-06 | On-time | 2024-06-04 | 211 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45996747 | T2 DI SALINAS-LAURELES 17/326B RPR STRW | ICW
LC | 126329307 | 012/274 | T2 DI SALINAS LAURELES 12/274 COA | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-09 | 2023-06-05 | 2024-05-09 | On-time | 2024-06-04 | 26 | 2024-06-05 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126329554 | :004/000 | T2 DI CARIBOU #2 :4/0 RPL INSW | TABLEMTN | ETL.6280.INSL.CERA | 2023-06-09 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35515753 | T2 DI CARIBOU #2 :4/0 RPL INSW | 93I
LC | 126329309 | 012/274 | T2 DI SALINAS LAURELES 12/274 RPR GYWW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-09 | 2023-06-05 | 2024-03-08 | On-time | 2024-06-04 | 88 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46081303 | T2 DI SALINAS LAURELES 12/274 RPR GYWW | ICW
LC | 126329762 | 065/325 | T2 DI MALIN-RND MTN #2 65/325 UNBURY | TABLEMTN | ETL.6020.TOWR | 2023-06-09 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46072214 | T2 DI MALIN-RND MTN #2 65/325 UNBURY | ICQ
LC | 126329895 | 056/001 | T2 EI ELK-GUALALA 56/1 GO95 CLEAR | WILLITS | ETL.8410.POLE.WOOD | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35495166 | T2 EI ELK-GUALALA 56/1 GO95 CLEAR | 93G
LC | 126329550 | 015/312 | T2 DI SALINAS-LAURELES 15/312 RPR GYWW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-09 | 2023-06-05 | 2023-10-21 | On-time | 2024-06-04 | 227 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45996748 | T2 DI SALINAS-LAURELES 15/312 RPR GYWW | ICW
LC | 126329552 | 015/312 | T2 DI SALINAS-LAURELES 15/312 COTTER | MOSSLNDG | ETL.7930.INSL | 2023-06-09 | 2023-06-05 | 2023-10-21 | On-time | 2024-06-04 | 227 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45996749 | T2 DI SALINAS-LAURELES 15/312 COTTER | ICW
LC | 126330263 | 058/288 | T2 DI MLN-RND MT #2 58/288 UNBURY | TABLEMTN | ETL.6020.TOWR | 2023-06-09 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46075980 | T2 DI MLN-RND MT #2 58/288 UNBURY | ICQ
LC | 126330276 | 066/001X | T2 HUMBOLDT-TRINITY 66/001X RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46171105 | T2 HUMBOLDT-TRINITY 66/001X RPR INSW | ICW
LC | 126330305 | 007/015 | T2 DI TRINITY-MAPLE CRK 7/15 RPR ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-09 | 2023-06-05 | 2024-01-22 | On-time | 2024-06-04 | 134 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46079198 | T2 DI TRINITY-MAPLE CRK 7/15 RPR ANCW | ICW
LC | 126330399 | 088/001 | T2 EI HUMBOLDT-TRINTY 088/001L RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171110 | T2 EI HUMBOLDT-TRINTY 088/001L RPR GYWW | ICW
LC | 126330430 | 088/001 | T2 EI HUMBOLDT-TRINTY 088/001R RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171110 | T2 EI HUMBOLDT-TRINTY 088/001L RPR GYWW | ICW
LC | 126330440 | 007/015 | T2 DI TRINITY-MAPLE CRK 7/15 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-09 | 2023-06-05 | 2024-01-22 | On-time | 2024-06-04 | 134 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079198 | T2 DI TRINITY-MAPLE CRK 7/15 RPR ANCW | ICW
LC | 126330441 | 015/311 | T2 DI SALINAS-LAURELES 15/311 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-09 | 2023-06-05 | 2024-06-22 | Late | 2024-06-04 | -18 | 2024-06-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507084 | T2 DI SALINAS-LAURELES 15/310 RPL POLE | 70Y
LC | 126330562 | 033/001 | T2 DI TRINITY-MAPLE CREEK 33/1L RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-09 | 2023-06-05 | 2024-06-17 | Late | 2024-06-04 | -13 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172096 | T2 DI TRINITY-MAPLE CREEK 33/1L RPR GYWW | ICW
LC | 126330736 | 009/111C | T2 DI DRUM-SUMMIT #1 009/111C RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-09 | 2023-06-05 | 2024-05-23 | On-time | 2024-06-04 | 12 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098217 | T2 DI DRUM-SUMMIT #1 009/111C RPR GYWW | ICW
LC | 126330592 | 033/001 | T2 DI TRINITY-MAPLE CREEK 33/1R RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-09 | 2023-06-05 | 2024-06-17 | Late | 2024-06-04 | -13 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172096 | T2 DI TRINITY-MAPLE CREEK 33/1L RPR GYWW | ICW
LC | 126330593 | 033/001 | T2 DI TRINITY-MAPLE CREEK 33/1C RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-09 | 2023-06-05 | 2024-06-17 | Late | 2024-06-04 | -13 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172096 | T2 DI TRINITY-MAPLE CREEK 33/1L RPR GYWW | ICW
LC | 126341160 | 011/252 | T2 DI SALINAS-LAURELES 11/252 COTTER | MOSSLNDG | ETL.7930.INSL.NCER | 2023-06-10 | 2023-06-05 | 2024-03-03 | On-time | 2024-06-04 | 93 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081301 | T2 DI SALINAS-LAURELES 11/252 COTTER | ICW
LC | 126330671 | 042/821 | T2 EI HT CRK #1-WSTWD 42/821 RPL HRDW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46091806 | T2 EI HT CRK #1-WSTWD 42/821 RPL HRDW | ICW
LC | 126330673 | 042/820 | T2 EI HT CRK #1-WSTWD 42/820 RPL HRDW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46091805 | T2 EI HT CRK #1-WSTWD 42/820 RPL HRDW | ICW
LC | 126341204 | 013/001 | T2 DI TRINITY-MAPLE CRK 13/1L RPR ANCW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-10 | 2023-06-05 | 2024-02-16 | On-time | 2024-06-04 | 109 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46079262 | T2 DI TRINITY-MAPLE CRK 13/1L RPR ANCW | ICW
LC | 126341230 | 015/007 | T2 DI CARIBOU-PLMS JCT 15/7 RPR GYWW | TABLEMTN | ETL.6290.POLE.NWOD | 2023-06-10 | 2023-06-05 | 2024-05-09 | On-time | 2024-06-04 | 26 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079289 | T2 DI CARIBOU-PLMS JCT 15/7 RPR GYWW | ICW
LC | 126330726 | 042/822 | T2 EI HT CRK #1-WSTWD 42/822 RPR POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091808 | T2 EI HT CRK #1-WSTWD 42/822 RPR POLE | ICW
LC | 126341297 | 011/250 | T2 DI SALINAS-LAURELES 11/250 COTTER | MOSSLNDG | ETL.7930.INSL.NCER | 2023-06-10 | 2023-06-05 | 2024-03-19 | On-time | 2024-06-04 | 77 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081300 | T2 DI SALINAS-LAURELES 11/250 COTTER | ICW
LC | 126330732 | ;000/004 | T2 DI CARIBOU #2 ;0/4 COTR KEY | TABLEMTN | ETL.6280.INSL.CERA | 2023-06-09 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079281 | T2 DI CARIBOU #2 ;0/4 COTR KEY | ICW
LC | 126341312 | 015/002 | T2 DI TRNTY-MPL CRK 015/002 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-10 | 2023-06-05 | 2024-01-18 | On-time | 2024-06-04 | 138 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079265 | T2 DI TRNTY-MPL CRK 015/002 RPR GYWW | ICW
LC | 126330745 | 005/042 | T2 DI PIT#4 TAP 05/042 RPL INSS | TABLEMTN | ETL.5432.INSL.CERA | 2023-06-09 | 2023-06-03 | 2024-06-24 | Late | 2024-06-02 | -22 | 2024-06-03 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509002 | T2 DI PIT#4 TAP RPL INSS 3 TWRS | 93K
LC | 126330749 | 005/043 | T2 DI PIT#4 TAP 05/043 COTTER | TABLEMTN | ETL.5432.INSL.CERA | 2023-06-09 | 2023-06-03 | 2024-06-24 | Late | 2024-06-02 | -22 | 2024-06-03 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46076085 | T2 DI PIT#4 TAP 05/043 COTTER | ICS
LC | 126341473 | 015/007 | T2 DI TRINITY-MAPLE CRK 15/7L RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-06-10 | 2023-06-05 | 2024-01-17 | On-time | 2024-06-04 | 139 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079266 | T2 DI TRINITY-MAPLE CRK 15/7L RPR GYWW | ICW
LC | 126341479 | 073/370 | T2 DI MALIN-RND MNTN #2 73/370 COTTER | TABLEMTN | ETL.6020.INSL.NCER | 2023-06-10 | 2023-06-05 | 2024-01-22 | On-time | 2024-06-04 | 134 | 2024-06-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46056062 | T2 DI MALIN-RND MNTN #2 73/370 COTTER | ICS
LC | 126330879 | 046/010 | T2 DI TRINITY-MAPLE CRK 46/10 RPR ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-09 | 2023-06-05 | 2024-06-06 | Late | 2024-06-04 | -2 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46172241 | T2 DI TRINITY-MAPLE CRK 46/10 RPR ANCW | ICW
LC | 126330921 | 051/007 | T2 DI FRT RSS-GUALALA 51/7 COTTER | LAKEVLLE | ETL.6980.INSL.NCER | 2023-06-09 | 2023-06-02 | 2024-06-25 | Late | 2024-06-01 | -24 | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46073762 | T2 DI FORT ROSS-GUALALA 51/7 COTR KEY | ICW
LC | 126341978 | 012/279 | T2 DI SALINAS-LAURELES 12/279 RPL HRDW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-10 | 2023-06-05 | 2024-02-20 | On-time | 2024-06-04 | 105 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46081306 | T2 DI SALINAS-LAURELES 12/279 RPL HRDW | ICW
LC | 126330929 | 017/011 | T2 DI FORT BRAGG-ELK 017/011 RPL HRDW | WILLITS | ETL.2060.POLE.WOOD | 2023-06-09 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46090348 | T2 DI FORT BRAGG-ELK 017/011 RPL HRDW | ICW
LC | 126330979 | 016/003 | T2 DI MAPLE CREEK-HOOPA 16/3 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-06-09 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46203523 | T2 DI MAPLE CREEK-HOOPA 16/3 RPR GYWW | ICW
LC | 126330982 | 016/003 | T2 DI MAPLE CREEK-HOOPA 16/3 RPR ANCW | EUREKA | ETL.7490.POLE.NWOD | 2023-06-09 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46203524 | T2 DI MAPLE CREEK-HOOPA 16/3 RPR ANCW | ICW
LC | 126342164 | 012/280 | T2 DI SALINAS-LAURELES 12/280 RPL INSW | MOSSLNDG | ETL.7930.INSL | 2023-06-10 | 2023-06-05 | 2024-02-29 | On-time | 2024-06-04 | 96 | 2024-06-05 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35507138 | T2 DI SALINAS-LAURELES 12/280 RPL INSW | 93I
LC | 126331006 | 015/013 | T2 FORT BRAGG-ELK 015/013 GO95 CLEAR | WILLITS | ETL.2060.POLE.WOOD | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654427 | EQUET2 FORT BRAGG-ELK 004/007 GO95 CLEAR | 93G
LC | 126331026 | 015/310 | T2 DI SALINAS-LAURELES 15/310 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-09 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507084 | T2 DI SALINAS-LAURELES 15/310 RPL POLE | 70Y
LC | 126331125 | 005/072 | T2 EI HAT CRK #1-PIT #1 005/072 RPL PL | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521449 | T2 EI HAT CRK #1-PIT #1 005/072 RPL PL | 70Y
LC | 126342286 | 002/008 | T2 DI LAURELES-OTTER 002/008 RPL POLE | MOSSLNDG | ETL.7380.POLE.WOOD | 2023-06-10 | 2023-06-05 | 2024-03-11 | On-time | 2024-06-04 | 85 | 2024-06-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503052 | T2 DI LAURELES-OTTER 002/000 RPL POLE | 70Y
LC | 126342658 | 017/013 | T2 DI TRINITY-MAPLE CRK 17/13 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-10 | 2023-06-05 | 2024-05-15 | On-time | 2024-06-04 | 20 | 2023-12-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079363 | T2 DI TRINITY-MAPLE CRK 17/13 RPR GYWW | ICW
LC | 126331166 | 006/074 | T2 EI HAT CREEK #1-PIT #1 06/074 RPL PL | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521449 | T2 EI HAT CRK #1-PIT #1 005/072 RPL PL | 70Y
LC | 126342907 | 007/058 | T2 DI BKS CRK-RCK CRK-CRA 7/58 RPR FOND | TABLEMTN | ETL.4430.TOWR | 2023-06-10 | 2023-06-05 | 2024-03-25 | On-time | 2024-06-04 | 71 | 2024-06-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46102371 | T2 DI BKS CRK-RCK CRK-CRA 7/58 RPR FOND | ICQ
LC | 126331172 | 016/008 | T2 DI FORT BRAGG-ELK 016/008 RMV VEG | WILLITS | ETL.2060.POLE.WOOD | 2023-06-09 | 2023-06-03 |  | Late | 2024-06-02 |  | 2024-06-03 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126343757 | 010/000 | T2 DI CARIBOU-PLU JCT 10/0 RPL INSW | TABLEMTN | ETL.6290.INSL.CERA | 2023-06-10 | 2023-06-05 | 2024-05-07 | On-time | 2024-06-04 | 28 | 2024-06-05 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35518837 | T2 DI CARIBOU-PLU JCT 10/0 RPL INSW | 93I
LC | 126331348 | 009/003 | T2 FORT BRAGG-ELK 009/003 GO95 CLEAR | WILLITS | ETL.2060.POLE.WOOD | 2023-06-09 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654427 | EQUET2 FORT BRAGG-ELK 004/007 GO95 CLEAR | 93G
LC | 126344081 | 016/002 | T2 DI TRINITY-MC 16/2 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-10 | 2023-06-05 | 2024-01-17 | On-time | 2024-06-04 | 139 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079267 | T2 DI TRINITY-MC 16/2 RPR GYWW | ICW
LC | 126344452 | 011/254 | T2 DI SALINAS-LAURELES 11/254 RPR GYWW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-10 | 2023-06-05 | 2024-03-04 | On-time | 2024-06-04 | 92 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46081315 | T2 DI SALINAS-LAURELES 11/254 RPR GYWW | ICW
LC | 126344454 | 011/254 | T2 DI SALINAS-LAURELES 11/254 RPR STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-10 | 2023-06-05 | 2024-03-04 | On-time | 2024-06-04 | 92 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081316 | T2 DI SALINAS-LAURELES 11/254 RPR STRW | ICW
LC | 126344954 | 27 | T2 DI SALINAS-LAURELES 11/248 RPR SWTC | MOSSLNDG | ETL.7930.SWIT | 2023-06-10 | 2023-06-05 | 2023-10-20 | On-time | 2024-06-04 | 228 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 45996807 | T2 DI SALINAS-LAURELES 11/248 RPR SWTC | ICW
LC | 126345523 | 014/000 | T2 DI TRINITY-MAPLE CREEK 14/0 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-10 | 2023-06-05 | 2024-01-19 | On-time | 2024-06-04 | 137 | 2024-06-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46079264 | T2 DI TRINITY-MAPLE CREEK 14/0 RPR GYWW | ICS
LC | 126341279 | 023/001 | T2 DI TRNTY-MPL CRK 023/001 RMV VEG | TABLEMTN | ETL.8170.POLE.WOOD | 2023-06-10 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126346195 | 014/009 | T2 DI TRINITY-MC 14/9 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-11 | 2023-06-05 | 2023-08-01 | On-time | 2024-06-04 | 308 | 2023-12-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45853834 | T2 DI TRINITY-MC 14/9 RPR GYWW | ICW
LC | 126348080 | 017/354 | T2 DI CARIBOU-WSWD 017/354 RPR ANCW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-11 | 2023-06-05 | 2023-08-07 | On-time | 2024-06-04 | 302 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45855601 | T2 DI CARIBOU-WSWD 017/354 RPR ANCW | ICW
LC | 126341302 | 023/001 | T2 DI TRNTY-MPL CRK 023/001 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-06-10 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503529 | T2 DI TRNTY-MPL CRK 023/001 RPL POLE | 70Y
LC | 126352048 | 072/364B | T2 DI MALIN RND MTN#2 72/364B COMPLETE | TABLEMTN | ETL.6020.TOWR | 2023-06-12 | 2023-06-05 | 2023-08-29 | On-time | 2024-06-04 | 280 | 2023-09-05 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45855682 | T2 DI MALIN RND MTN#2 72/364B RPR SHLS | ICS
LC | 126341399 | 003/040 | T2 DI PIT#5-RND MT#1 3/40R RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2023-06-10 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526327 | T2 DI PIT#5-RND MT#1 RPL 4 STRW | 70Y
LC | 126341438 | 027/002A | T2 DI TRNTY-MPL CRK-27/02A REFRAME | EUREKA | ETL.8170.POLE.WOOD | 2023-06-10 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35504067 | T2 DI TRNTY-MPL CRK-27/02A RPL CRSW | 93E
LC | 126341469 | 014/006 | T2 DI PHILO JCT-ELK- 14/06 RMV VEG | WILLITS | ETL.7780.POLE.WOOD | 2023-06-10 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126352972 | 009/104 | T2 DI DRUM SUMMIT#1 09/104 RPR GYWW | SACTO | ETL.1440.POLE.STPS | 2023-06-12 | 2023-06-05 | 2024-05-22 | On-time | 2024-06-04 | 13 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098242 | T2 DI DRUM SUMMIT#1 09/104 RPR GYWW | ICW
LC | 126302344 | 063/001 | T2 EI ELK-GUALALA 63/1 RPL HDWW | WILLITS | ETL.8410.POLE.WOOD | 2023-06-06 | 2023-06-06 | 2024-01-25 | On-time | 2024-06-05 | 132 | 2024-06-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 46089302 | T2 EI ELK-GUALALA 63/1 RPL HDWW | ICW
LC | 126341484 | 000/002 | T2 DI BRIDGEVIL GARBRVIL 00/002 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2023-06-10 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504387 | T2 DI BRIDGEVIL GARBRVIL 00/002 RPL POLE | 70Y
LC | 126341486 | 013/001B | T2 DI BRIDGEVLE-GARBER 13/1B RPR GYWW | EUREKA | ETL.6220.POLE.NWOD | 2023-06-10 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46087889 | T2 DI BRIDGEVLE-GARBER 13/1B RPR GYWW | ICW
LC | 126341506 | 033/003 | T2 DI PHILO JCT-ELK 033/003 RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-06-10 | 2023-06-02 | 2024-06-14 | Late | 2024-06-01 | -13 | 2024-06-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35522440 | T2 PHILO JCT-ELK 033/001 RPL POLE | 70Y
LC | 126303694 | 088/002 | T2 EI COTTONWOOD-HUMBOLDT 88/2 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-06 | 2023-06-06 | 2023-08-16 | On-time | 2024-06-05 | 294 | 2023-12-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45861697 | T2 EI COTTONWOOD-HUMBOLDT 88/2 RPR GYWW | ICW
LC | 126341561 | 058/005 | T2 DI ELK-GUALALA 058/005 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-06-10 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487368 | T2 DI ELK-GUALALA 058/005 RPL POLE | 70Y
LC | 126303695 | 088/002 | T2 EI COTTONWOOD-HUMBOLDT 88/2 RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-06 | 2023-06-06 | 2023-08-16 | On-time | 2024-06-05 | 294 | 2023-12-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45861696 | T2 EI COTTONWOOD-HUMBOLDT 88/2 RPR GYWW | ICW
LC | 126303766 | 016/162 | T2 EI IGNACIO-ALTO 16/162 RPR STRW | LAKEVLLE | ETL.7150.POLE.WOOD | 2023-06-06 | 2023-06-06 | 2024-01-29 | On-time | 2024-06-05 | 128 | 2024-06-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46100615 | T2 EI IGNACIO-ALTO 16/162 RPR STRW | ICW
LC | 126304116 | 007/060 | T2 EI PARADISE-TABLE MTN 007/060 UNBURY | TABLEMTN | ETL.4316.TOWR | 2023-06-06 | 2023-06-06 | 2023-12-27 | On-time | 2024-06-05 | 161 | 2024-06-06 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46102205 | T2 EI PARADISE-TABLE MTN 007/060 UNBURY | ICQ
LC | 126341722 | 114/003 | T2 EI HMBLT-BRDGVL 114/3 RPR CNDW | EUREKA | ETL.1810.INSL.NCER | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46170401 | T2 EI HMBLT-BRDGVL 114/3 RPR CNDW | ICW
LC | 126304737 | 007/063 | T2 EI PARADISE-TABLE MTN 007/063 UNBURY | TABLEMTN | ETL.4316.TOWR | 2023-06-06 | 2023-06-06 | 2023-12-27 | On-time | 2024-06-05 | 161 | 2024-06-06 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46102209 | T2 EI PARADISE-TABLE MTN 007/063 UNBURY | ICQ
LC | 126341768 | 009/107 | T2 DI DRUM-SUMMIT #1 9/107 RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2023-06-10 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126341842 | 000/001F | T2 DI LWR LK-HMSTK 0/1F RPL STRW | WILLITS | ETL.1481.POLE.WOOD | 2023-06-10 | 2023-06-03 |  | Late | 2024-06-02 |  | 2023-09-03 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 46219445 | T2 DI LWR LK-HMSTK 00/01F RPR STRW | ICW
LC | 126305506 | 007/061 | T2 EI PARADISE-TABLE MTN 007/061 UNBURY | TABLEMTN | ETL.4316.TOWR | 2023-06-06 | 2023-06-06 | 2023-12-27 | On-time | 2024-06-05 | 161 | 2024-06-06 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46102207 | T2 EI PARADISE-TABLE MTN 007/061 UNBURY | ICQ
LC | 126305646 | 009/103 | T2 DRUM-SUMMIT #2 09/103 RPL DMPS | SACTO | ETL.1450.INSL | 2023-06-06 | 2023-06-06 | 2024-04-10 | On-time | 2024-06-05 | 56 | 2024-06-06 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 46101327 | T2 DRUM-SUMMIT #2 09/103 RPL DMPS | ICS
LC | 126341853 | 009/058 | T2 DI HAAS-MC CLL 9/58 RPR STRT | FRESNO | ETL.4850.TOWR | 2023-06-10 | 2023-06-02 |  | Late | 2024-06-01 |  | 2023-09-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46133436 | T2 DI HAAS-MC CLL 9/58 BNT STEEL | ICQ
LC | 126305703 | 007/147 | T2 EI KILARC-DESCHUTES 007/147 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-06 | 2023-06-06 | 2024-04-03 | On-time | 2024-06-05 | 63 | 2024-06-06 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515672 | T2 EI KILARC-DESCHUTES 007/147 RPL STRW | 70Y
LC | 126305710 | 006/134 | T2 EI KILARC-DESCHUTES 006/134 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-06 | 2023-06-06 | 2024-04-03 | On-time | 2024-06-05 | 63 | 2024-06-06 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515670 | T2 EI KILARC-DESCHUTES 006/134 RPL STRW | 70Y
LC | 126342125 | 003/076 | T2 DI CARIBOU-WESTWOOD 3/76L RPR GYWW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-06-10 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076257 | T2 DI CARIBOU-WESTWOOD 003/076L RPR GYWW | ICW
LC | 126342126 | 003/076 | T2 DI CARIBOU-WESTWOOD 3/76C RPR GYWW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-06-10 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46076258 | T2 DI CARIBOU-WESTWOOD 003/076C RPR GYWW | ICW
LC | 126305713 | 006/138 | T2 EI KILARC-DESCHUTES 006/138 RPL SPLW | TABLEMTN | ETL.7300.INSL.NCER | 2023-06-06 | 2023-06-06 | 2024-04-02 | On-time | 2024-06-05 | 64 | 2024-06-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Replace | 46079137 | T2 EI KILARC-DESCHUTES 006/138 RPL SPLW | ICW
LC | 126342141 | 014/001 | T2 DI BRDGVLL-GRBRVLL 014/001 RPL INSW | EUREKA | ETL.6220.INSL.NCER | 2023-06-10 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35504396 | T2 DI BRDGVLL-GRBRVLL 014/001 RPL INSW | 93I
LC | 126342144 | 031/007 | T2 DI PHILO JCT-ELK 31/07 RPL STRW | WILLITS | ETL.7780.POLE.WOOD | 2023-06-10 | 2023-06-02 | 2024-06-08 | Late | 2024-06-01 | -7 | 2024-06-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35522277 | T2 DI PHILO JCT-ELK- 31/07 RPL STRW | 70Y
LC | 126305715 | 007/149 | T2 EI KILARC-DESCHUTES 007/149 RPR INSW | TABLEMTN | ETL.7300.INSL.NCER | 2023-06-06 | 2023-06-06 | 2024-04-02 | On-time | 2024-06-05 | 64 | 2024-06-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079138 | T2 EI KILARC-DESCHUTES 007/149 RPR INSW | ICW
LC | 126342178 | 013/000 | T2 DI BRIDGEVLE-GARBER 13/0 RPL STRW | EUREKA | ETL.6220.POLE.WOOD | 2023-06-10 | 2023-06-07 |  | Late | 2024-06-06 |  | 2023-09-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504395 | T2 DI BRIDGEVLE-GARBER 13/0 RPL POLE | 70Y
LC | 126342211 | 017/219 | T2 WST PNT-VLY SPRNGS 17/219 RPL INSW | VICTOR | ETL.8350.INSL.NCER | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 508T | TLN | PATR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35525538 | T2 WST PNT-VLY SPRNGS 17/219 RPL INSW | 93I
LC | 126342214 | 032/150 | T2 TRACY-LOS BANOS 32/150 CNCL | VICTOR | ETL.6130.TOWR | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair
LC | 126305724 | 006/140 | T2 EI KILARC-DESCHUTES 006/140 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-06 | 2023-06-06 | 2024-04-03 | On-time | 2024-06-05 | 63 | 2024-06-06 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515670 | T2 EI KILARC-DESCHUTES 006/134 RPL STRW | 70Y
LC | 126305747 | 026/192A | T2 EI CARIBOU-TABLE MTN 26/192A RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-06 | 2023-06-06 | 2024-04-25 | On-time | 2024-06-05 | 41 | 2024-06-06 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46079320 | T2 EI CARIBOU-TABLE MTN 26/192A RPR GYWS | ICS
LC | 126342354 | 015/000 | T2 DI PHILO JCT-ELK 15/00 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-06-10 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35517324 | T2 DI PHILO JCT-ELK 15/00 RPL POLE | 70Y
LC | 126342410 | 071/360A | T2 DI MALIN-RND MTN #2 71/360A RPR FOND | TABLEMTN | ETL.6020.TOWR | 2023-06-10 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46269434 | T2 DI MALIN-RND MTN #2 71/360A RPR FOND | ICQ
LC | 126305783 | 026/192B | T2 EI CARIBOU-TABLE MTN 26/192B RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-06 | 2023-06-06 | 2024-04-25 | On-time | 2024-06-05 | 41 | 2024-06-06 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46079321 | T2 EI CARIBOU-TABLE MTN 26/192B RPR GYWS | ICS
LC | 126306119 | 062/002 | T2 EI HUMBOLDT-TRINITY 62/2 RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-06-06 | 2023-06-06 | 2024-03-26 | On-time | 2024-06-05 | 71 | 2024-06-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096530 | T2 EI HUMBOLDT-TRINITY 62/2 RPR GYWW | ICW
LC | 126306146 | 008/124 | T2 WV VALLEY SPRINGS-CLY 8/124 INS DMPW | VICTOR | ETL.8264.INSL.NCER | 2023-06-06 | 2023-06-06 | 2024-02-01 | On-time | 2024-06-05 | 125 | 2024-06-06 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46162155 | T2 WV VALLEY SPRINGS-CLY 8/124 INS DMPW | ICW
LC | 126306156 | 29 | T2 SALINS-LAURLS A011/250 SW 29 RPR SWTC | MOSSLNDG | ETL.7930.SWIT | 2023-06-06 | 2023-06-06 | 2023-10-10 | On-time | 2024-06-05 | 239 | 2023-12-06 | 623 | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 45851829 | T2 SALINS-LAURLS A011/250 SW 29 RPR SWTC | ICE
LC | 126306480 | 043/000 | T2 EI TRINITY-MAPLE CRK 43/000L RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-06-06 | 2023-06-06 | 2024-06-04 | On-time | 2024-06-05 | 1 | 2024-06-06 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46203577 | T2 EI TRINITY-MAPLE CRK 43/000L RPR GYWW | ICW
LC | 126344197 | 003/014 | T2 DI TRINITY-MC 3/14 RPR STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-10 | 2023-06-06 | 2024-01-12 | On-time | 2024-06-05 | 145 | 2024-06-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46079260 | T2 DI TRINITY-MC 3/14 RPR STRW | ICW
LC | 126345266 | 023/003 | T2 DI TRINITY-MAPLE CRK 23/3 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-10 | 2023-06-06 | 2023-10-07 | On-time | 2024-06-05 | 242 | 2023-12-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45853828 | T2 DI TRINITY-MAPLE CRK 23/3 RPR GYWW | ICW
LC | 126342881 | 035/006 | T2 FRT RSS-GUALALA 35/6 GO95 CLEAR | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654781 | T2 FORT ROSS-GUALALA 35/006 GO95 | 93G
LC | 126345614 | 016/001 | T2 DI TRNTY-MPL CRK 016/001 RPL HRDD | EUREKA | ETL.8170.POLE.WOOD | 2023-06-10 | 2023-06-06 | 2023-08-01 | On-time | 2024-06-05 | 309 | 2023-09-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45853874 | T2 DI TRNTY-MPL CRK 016/001 RPL HRDD | ICW
LC | 126348089 | 029/209B | T2 DI CARIBOU-TBL MTN 29/209B RPL INSS | TABLEMTN | ETL.4440.INSL.NCER | 2023-06-11 | 2023-06-06 | 2024-06-05 | On-time | 2024-06-05 | 0 | 2024-06-06 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35508877 | T2 EI CARIBOU-TABLE MTN RPL INSS 12 STRT | 93K
LC | 126353627 | 029/209C | T2 DI CRBOU TBL MTN 29/209C RPL INSS | TABLEMTN | ETL.4440.INSL.NCER | 2023-06-12 | 2023-06-06 | 2024-06-05 | On-time | 2024-06-05 | 0 | 2024-06-06 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35508877 | T2 EI CARIBOU-TABLE MTN RPL INSS 12 STRT | 93K
LC | 126353806 | 029/209A | T2 DI CRBOU TBL MTN 29/209A RPL INSS | TABLEMTN | ETL.4440.INSL | 2023-06-12 | 2023-06-06 | 2024-06-05 | On-time | 2024-06-05 | 0 | 2024-06-06 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35508877 | T2 EI CARIBOU-TABLE MTN RPL INSS 12 STRT | 93K
LC | 126342934 | 045/008 | T2 DI TRNTY-MPL CRK 45/008 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-10 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506433 | T2 DI TRNTY-MPL CRK 45/008 RPL STRW | 70Y
LC | 126342971 | 002/100 | T2 EI SPAULDING-SUMMIT 2/100 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518599 | T2 EI SPAULDING-SUMMIT 02/100 RPL POLE | 70Y
LC | 126485325 | 008/124 | T2 WV PARDEE #1 8/124 INS DMPW | VICTOR | ETL.8231.INSL.NCER | 2023-06-30 | 2023-06-06 | 2024-01-02 | On-time | 2024-06-05 | 155 | 2024-06-06 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46078394 | T2 WV PARDEE #1 8/124 INS DMPW | ICW
LC | 126312737 | 008/142 | T2 TEMPLETON-ATASCADERO 8/142 REPLUMB | PISMOBCH | ETL.9410.INSL | 2023-06-07 | 2023-06-07 | 2024-05-17 | On-time | 2024-06-06 | 20 | 2024-06-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46090156 | T2 TEMPLETON-ATASCADERO 8/142 REPLUMB | ICW
LC | 126343026 | 006/001 | T2 HUMBOLDT-MAPLE CREEK 6/001 GO95 | EUREKA | ETL.7130.POLE.WDPS | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654782 | T2 HUMBOLDT-MAPLE CREEK 6/001 GO95 | 93G
LC | 126343126 | 032/619 | T2 EI HAT CRK #1-WESTWOOD 32/619 RPL PL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514162 | T2 EI HAT CRK #1-WESTWOOD 32/619 RPL PL | 70Y
LC | 126343128 | 031/597 | T2 EI HAT CREEK #1-WESTWD 31/597 RPL PL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-10 | 2023-06-10 | 2024-06-23 | Late | 2024-06-09 | -14 | 2024-06-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514138 | T2 EI HAT CREEK #1-WESTWD 31/597 RPL PL | 70Y
LC | 126313743 | 030/590 | T2 EI HAT CREEK #1-WSTD 30/590 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2024-05-31 | On-time | 2024-06-06 | 6 | 2024-06-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514137 | T2 DI HT CRK #1-WESTWD 30/590 RPL POLE | 70Y
LC | 126313812 | 007/156 | T2 EI KILARC-DESCHUTES 7/156 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2024-04-03 | On-time | 2024-06-06 | 64 | 2024-06-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515672 | T2 EI KILARC-DESCHUTES 007/147 RPL STRW | 70Y
LC | 126343248 | ;004/006 | T2 DI CARIBOU #2 ;4/6 RPR GYWW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-06-10 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45863864 | T2 DI CARIBOU #2 ;4/6 RPR GYWW | ICW
LC | 126313815 | 007/159 | T2 EI KILARC-DESCHUTES 7/159 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2024-04-05 | On-time | 2024-06-06 | 62 | 2024-06-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515673 | T2 EI KILARC-DESCHUTES 7/159 RPL POLE | 70Y
LC | 126313830 | 007/157 | T2 EI KILARC-DESCHUTES 7/157 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2024-04-05 | On-time | 2024-06-06 | 62 | 2024-06-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515672 | T2 EI KILARC-DESCHUTES 007/147 RPL STRW | 70Y
LC | 126343418 | 000/001 | T2 DI BUTTE VLY-CARBOU 0/1 RPR GYWT | TABLEMTN | ETL.1180.TOWR | 2023-06-10 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46256529 | T2 DI BUTTE VLY-CARBOU 0/1 RPR GYWT | ICQ
LC | 126343433 | 002/106 | T2 EI SPAULDING-SUMMIT 02/106 RPR STRW | SACTO | ETL.8060.POLE.WOOD | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46127493 | T2 EI SPAULDING-SUMMIT 02/106 RPR STRW | ICW
LC | 126343443 | 001/014 | T2 DI PIT #4 TAP 001/014 RPR SHIELD | TABLEMTN | ETL.5432.TOWR | 2023-06-10 | 2023-06-07 | 2024-06-25 | Late | 2024-06-06 | -19 | 2024-06-07 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46079329 | T2 DI PIT #4 TAP 001/014 RPR SHIELD | ICS
LC | 126314079 | 008/169 | T2 EI KILARC-DESCHUTES 8/169 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2024-04-07 | On-time | 2024-06-06 | 60 | 2024-06-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515674 | T2 EI KILARC-DESCHUTES 8/166 RPL POLE | 70Y
LC | 126314106 | 003/080 | T2 EI KILARC-DESCHUTES 3/80 RPR STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2024-02-15 | On-time | 2024-06-06 | 112 | 2024-06-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46079133 | T2 EI KILARC-DESCHUTES 3/80 RPR STRW | ICW
LC | 126343625 | 043/344 | T2 EI BRDGVLE-CTTNWD 43/344 RMV VEG | TABLEMTN | ETL.1110.TOWR | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126314107 | 007/161 | T2 EI KILARC-DESCHUTES 07/161 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2024-04-05 | On-time | 2024-06-06 | 62 | 2024-06-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515673 | T2 EI KILARC-DESCHUTES 7/159 RPL POLE | 70Y
LC | 126314129 | 007/163 | T2 EI KILARC-DESCHUTES 07/163 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2024-04-05 | On-time | 2024-06-06 | 62 | 2024-06-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515673 | T2 EI KILARC-DESCHUTES 7/159 RPL POLE | 70Y
LC | 126314131 | 008/168 | T2 EI KILARC-DESCHUTES 8/168 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2024-04-05 | On-time | 2024-06-06 | 62 | 2024-06-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515674 | T2 EI KILARC-DESCHUTES 8/166 RPL POLE | 70Y
LC | 126314133 | 007/164 | T2 EI KILARC-DESCHUTES 7/164 REFRAME | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2024-04-05 | On-time | 2024-06-06 | 62 | 2024-06-07 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35515129 | T2 EI KILARC-DESCHUTES 7/164 REFRAME | 93E
LC | 126314136 | 008/166 | T2 EI KILARC-DESCHUTES 8/166 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2024-04-07 | On-time | 2024-06-06 | 60 | 2024-06-07 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515674 | T2 EI KILARC-DESCHUTES 8/166 RPL POLE | 70Y
LC | 126343855 | 032/625 | T2 EI HT CREEK #1-WESTWD 032/625 RPL PL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-10 | 2023-06-10 | 2024-06-22 | Late | 2024-06-09 | -13 | 2024-06-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514202 | T2 EI HT CRK #1-WESTWOOD 32/623 RPL PL | 70Y
LC | 126314140 | 007/164 | T2 EI KILARC-DESCHUTES 7/164 RPR STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2024-04-05 | On-time | 2024-06-06 | 62 | 2024-06-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46079139 | T2 EI KILARC-DESCHUTES 7/164 RPR STRW | ICW
LC | 126314470 | 009/078 | T2 EI PARADISE-TABLE MTN 09/078 INS DMPS | TABLEMTN | ETL.4316.INSL.NCER | 2023-06-07 | 2023-06-07 | 2024-01-30 | On-time | 2024-06-06 | 128 | 2024-06-07 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 46079332 | T2 EI PARADISE-TABLE MTN 09/078 INS DMPS | ICS
LC | 126314940 | 041/009 | T2 EI TRNITY-MPLE CRK 41/9 RMV CON DEBRI | EUREKA | ETL.8170.POLE.STPS | 2023-06-07 | 2023-06-07 | 2023-07-13 | On-time | 2024-06-06 | 329 | 2024-06-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Conductor-Wood | Remove
LC | 126314942 | 041/001 | T2 EI TRNTY-MPL CRK 041/1 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-07 | 2023-06-07 | 2023-11-02 | On-time | 2024-06-06 | 217 | 2023-12-07 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45845900 | T2 EI TRNTY-MPL CRK 041/1 RPR GYWW | ICW
LC | 126315498 | 012/048 | T2 EI TESLA-METCALF 12/048 RPR INSS | CONCORD | ETL.6110.INSL.NCER | 2023-06-07 | 2023-06-07 | 2024-05-10 | On-time | 2024-06-06 | 27 | 2024-06-07 | 628 | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46093507 | T2 EI TESLA-METCALF 12/048 RPR INSS | ICS
LC | 126341712 | 014/002 | T2 DI BRIDGEVILLE-GARBER 14/2 RPR GYWW | EUREKA | ETL.6220.POLE.NWOD | 2023-06-10 | 2023-06-07 | 2024-03-22 | On-time | 2024-06-06 | 76 | 2024-06-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45853871 | T2 DI BRIDGEVILLE-GARBER 14/2 RPR GYWW | ICW
LC | 126344053 | 17 | T2 DI MPL CRK-HOOPA 6/5 RPR SWTC | EUREKA | ETL.7490.SWIT | 2023-06-10 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 623 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Out of Adjustment | Switch | Repair | 46210538 | T2 DI MPL CRK-HOOPA 6/5 RPR SWTC | ICE
LC | 126342855 | A012/259 | T2 DI SLNS-LAURELES A012/259 RPR STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-10 | 2023-06-07 | 2024-04-17 | On-time | 2024-06-06 | 50 | 2024-06-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081308 | T2 DI SLNS-LAURELES A012/259 RPR STRW | ICW
LC | 126343448 | 005/004 | T2 DI MPL CRK-HOOPA 5/4 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-06-10 | 2023-06-07 | 2023-09-07 | On-time | 2024-06-06 | 273 | 2023-12-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45885328 | T2 DI MPL CRK-HOOPA 5/4 RPR GYWW | ICW
LC | 126344097 | 013/283 | T2 DI SALINAS-LAURELES 13/283 RPR SPLW | MOSSLNDG | ETL.7930.INSL | 2023-06-10 | 2023-06-05 | 2024-06-15 | Late | 2024-06-04 | -11 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46081312 | T2 DI SALINAS-LAURELES 13/283 RPR SPLW | ICW
LC | 126344191 | 015/008 | T2 DI TRINITY-MC 15/8 RPR JMPW | EUREKA | ETL.8170.INSL.NCER | 2023-06-10 | 2023-06-06 |  | Late | 2024-06-05 |  | 2023-09-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46193766 | T2 DI TRINITY-MC 15/8 RPR JMPW | ICW
LC | 126343593 | 001/010 | T2 DI PIT #4 TAP 001/010 RPL INSS | TABLEMTN | ETL.5432.INSL.CERA | 2023-06-10 | 2023-06-07 | 2023-10-05 | On-time | 2024-06-06 | 245 | 2024-06-07 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31669701 | T2 DI PIT #4 TAP 001/010 RPL INSS | 93K
LC | 126344222 | A012/260 | T2 DI SALINAS-LAURELES A12/260 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-10 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507045 | T2 DI SALINAS-LAURELES A12/260 RPL POLE | 70Y
LC | 126344239 | 046/001 | T2 DI TRNTY-MPL CRK 46/001 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-10 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506437 | T2 DI TRNTY-MPL CRK 46/001 RPL STRW | 70Y
LC | 126344344 | 028/012 | T2 DI PHILO JCT-ELK 28/012 COA | WILLITS | ETL.7780.POLE.WOOD | 2023-06-10 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213817 | T2 DI PHILO JCT-ELK 28/012 RPR GYWW | ICW
LC | 126344422 | 000/003 | T2 DI BRGVIL GRBRVIL 00/003 RPL POLE | EUREKA | ETL.6220.POLE.WOOD | 2023-06-10 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35504388 | T2 DI BRGVIL GRBRVIL 00/003 RPL POLE | 70Y
LC | 126343987 | 000/002 | T2 DI CLGTE PLMRO 0/2 RPR GYWW | SACTO | ETL.6500.POLE.NWOD | 2023-06-10 | 2023-06-07 | 2024-04-16 | On-time | 2024-06-06 | 51 | 2024-06-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46125120 | T2 DI CLGTE PLMRO 00/002 RPR GYWW | ICW
LC | 126344059 | 075/380C | T2 DI MLN-RND MT #2 75/380C RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2023-06-10 | 2023-06-07 | 2023-12-21 | On-time | 2024-06-06 | 168 | 2024-06-07 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46056064 | T2 DI MLN-RND MT #2 75/380C RPR INSS | ICS
LC | 126344465 | 013/005 | T2 DI BRDGVL-GRBRVL 13/5 RPR GYWW | EUREKA | ETL.6220.POLE.NWOD | 2023-06-10 | 2023-06-07 | 2023-10-24 | On-time | 2024-06-06 | 226 | 2023-12-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45903633 | T2 DI BRDGVL-GRBRVL 13/5 RPR GYWW | ICW
LC | 126344505 | 013/005 | T2 DI BRDGVL-GRBRVL 13/5 RPL ANCW | EUREKA | ETL.6220.POLE.NWOD | 2023-06-10 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 637 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31652769 | T3 DI BRDGVIL GRBRVIL 09/012 RPL ANCW | 93E
LC | 126344565 | 006/033 | T2 DI IGNC-SN RFL #1 6/33 RPR INSS | LAKEVLLE | ETL.1850.INSL | 2023-06-10 | 2023-06-07 |  | Late | 2024-06-06 |  | 2023-12-07 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46271534 | T2 DI IGNC-SN RFL #1 6/33 RPR INSS | ICS
LC | 126344623 | 006/033 | T2 DI IGNC-ALTO 6/33 RPL INSS | LAKEVLLE | ETL.7150.INSL.CERA | 2023-06-10 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35524576 | T2 DI IGNC-ALTO RPL INSS IN TWR 6/33 . | 93K
LC | 126344705 | 027/000 | T2 DI TRINITY-MAPLE CRK 27/0L RPR HRDD | EUREKA | ETL.8170.POLE.WDPS | 2023-06-10 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46239611 | T2 DI TRINITY-MAPLE CRK 27/0L RPR IBWW | ICW
LC | 126344706 | 027/000 | T2 DI TRINITY-MAPLE CRK 27/0C RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-10 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46238992 | T2 DI TRINITY-MAPLE CRK 27/0C RPR GYWW | ICW
LC | 126344707 | 027/000 | T2 DI TRINITY-MAPLE CRK 27/0 RPL INSLW | EUREKA | ETL.8170.INSL.NCER | 2023-06-10 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35551283 | T2 DI TRINITY-MAPLE CRK 27/0 RPL INSLW | 93I
LC | 126345636 | 000/006 | T2 DI ELECTRA-BELLOTA 0/6 COTTER | VICTOR | ETL.4670.INSL | 2023-06-10 | 2023-06-07 | 2023-12-06 | On-time | 2024-06-06 | 183 | 2024-06-07 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46078396 | T2 DI ELECTRA-BELLOTA 0/6 COTTER | ICS
LC | 126345157 | ;010/091 | T2 EI PARADISE-TABL MTN ;010/091 RMV VEG | TABLEMTN | ETL.4316.TOWR | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation-Tower | Cage Clearing
LC | 126346021 | 014/000 | T2 DI BRIDGEVLL-GARBERVLL 14/0L RPR GYWW | EUREKA | ETL.6220.POLE.STPS | 2023-06-11 | 2023-06-07 | 2023-10-24 | On-time | 2024-06-06 | 226 | 2023-12-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45903634 | T2 DI BRIDGEVLL-GARBERVLL 14/0L RPR GYWW | ICW
LC | 126345184 | 008/003 | T2 EI HMBLDT-MAPLE CRK 08/003L RPL STRW | EUREKA | ETL.7130.POLE.WDPS | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508490 | T2 EI HMBLDT-MAPLE CRK 08/003L RPL STRW | 70Y
LC | 126345220 | 024/006 | T2 EI MAPLE CRK-HOOPA 24/6 RPR GYWW | EUREKA | ETL.7490.POLE.WOOD | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46203527 | T2 EI MAPLE CRK-HOOPA 24/6 RPR GYWW | ICW
LC | 126345223 | 021/002 | T2 EI MAPLE CREEK-HOOPA 021/002 RPR POLE | EUREKA | ETL.7490.POLE.WOOD | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46190238 | T2 EI MAPLE CREEK-HOOPA 021/002 RPR POLE | ICW
LC | 126346022 | 014/000 | T2 DI BRIDGEVLL-GARBERVLL 14/0C RPR GYWW | EUREKA | ETL.6220.POLE.STPS | 2023-06-11 | 2023-06-07 | 2023-10-24 | On-time | 2024-06-06 | 226 | 2023-12-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45903635 | T2 DI BRIDGEVLL-GARBERVLL 14/0C RPR GYWW | ICW
LC | 126345265 | 023/003 | T2 DI TRINITY-MAPLE CRK 23/3 RMV VEG | TABLEMTN | ETL.8170.POLE.NWOD | 2023-06-10 | 2023-06-06 |  | Late | 2024-06-05 |  | 2024-06-06 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126346024 | 014/000 | T2 DI BRIDGEVLL-GARBERVLL 14/0R RPR GYWW | EUREKA | ETL.6220.POLE.STPS | 2023-06-11 | 2023-06-07 | 2023-10-24 | On-time | 2024-06-06 | 226 | 2023-12-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45903636 | T2 DI BRIDGEVLL-GARBERVLL 14/0R RPR GYWW | ICW
LC | 126345289 | 021/102 | T2 DI FLTN-IGNACIO #1 21/102 RPL INSS | LAKEVLLE | ETL.4680.INSL | 2023-06-10 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31678225 | T2 DI FULTON-IGNCIO #1 RPL INSS IN 5 TWR | 93K
LC | 126345499 | 002/015 | T2 DI PIT #4 TAP 002/015 RPR SHLS | TABLEMTN | ETL.5432.TOWR | 2023-06-10 | 2023-06-07 | 2024-06-25 | Late | 2024-06-06 | -19 | 2024-06-07 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46079330 | T2 DI PIT #4 TAP 002/015 RPR SHLS | ICS
LC | 126346037 | 025/009 | T2 DI MAPLE CREEK-HOOPA 25/9 RMV VEG | EUREKA | ETL.7490.POLE.NWOD | 2023-06-11 | 2023-06-07 | 2023-07-06 | On-time | 2024-06-06 | 336 | 2024-06-07 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126345546 | 052/1020 | T2 EI HT CRK #1-WSTWD 52/1020 RPR POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091816 | T2 EI HT CRK #1-WSTWD 52/1020 RPR POLE | ICW
LC | 126345558 | 032/623 | T2 EI HT CRK #1-WESTWOOD 32/623 RPL PL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514202 | T2 EI HT CRK #1-WESTWOOD 32/623 RPL PL | 70Y
LC | 126345590 | 040/775 | T2 EI HT CRK #1-WSTWD 40/775 RPR STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091814 | T2 EI HT CRK #1-WSTWD 40/775 RPR POLE | ICW
LC | 126345592 | 052/1021 | T2 EI HT CRK #1-WSTWD 52/1021 RPR POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091817 | T2 EI HT CRK #1-WSTWD 52/1021 RPR POLE | ICW
LC | 126347546 | A012/258 | T2 DI SLNS-LRLS-LRLS A12/258 RPR INSW | MOSSLNDG | ETL.7930.INSL | 2023-06-11 | 2023-06-07 | 2024-04-17 | On-time | 2024-06-06 | 50 | 2024-06-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081318 | T2 DI SLNS-LRLS-LRLS A12/258 RPR INSW | ICW
LC | 126348168 | 006/004 | T2 DI MPL CRK-HOOPA 006/004 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-06-11 | 2023-06-07 | 2023-08-09 | On-time | 2024-06-06 | 302 | 2023-12-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45853827 | T2 DI MPL CRK-HOOPA 006/004 RPR GYWW | ICW
LC | 126351256 | 006/002 | T2 DI MAPLE CREEK-HOOPA 006/002 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-06-12 | 2023-06-07 | 2023-09-07 | On-time | 2024-06-06 | 273 | 2023-09-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45853873 | T2 DI MAPLE CREEK-HOOPA 006/002 RPR GYWW | ICW
LC | 126345696 | ;002/002 | T2 DI CARIBOU #2 ;002/002 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2023-06-10 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527150 | T2 DI CARIBOU #2 ;002/002 RPL POLE | 70Y
LC | 126345823 | 113/005 | T2 EI HMBLT-BRDGVL 113/5 RPR CNDW | EUREKA | ETL.1810.INSL.NCER | 2023-06-10 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46102373 | T2 EI HMBLT-BRDGVL 113/5 RPR CNDW | ICS
LC | 126365364 | 000/002 | T2 DI COLGATE-SMARTVIL #1 0/2 RPL INSW | SACTO | ETL.6510.INSL.NCER | 2023-06-13 | 2023-06-07 | 2024-05-07 | On-time | 2024-06-06 | 30 | 2024-06-07 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35481566 | T2 DI COLGATE-SMARTVIL #1 00/02 RPL INSW | 93I
LC | 126467765 | 011/000 | T2 FULTON-HOPLAND 11/0 RPL ANCW | LAKEVLLE | ETL.6890.POLE.WOOD | 2023-06-28 | 2023-06-07 | 2023-09-27 | On-time | 2024-06-06 | 253 | 2023-12-07 | 637 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31654958 | T2 FULTON-HOPLAND 11/0 RPL ANCW | 93E
LC | 126315844 | 012/097 | T2 PIT #1-COTTONWOOD 12/97 RMV NEST | TABLEMTN | ETL.5390.TOWR | 2023-06-08 | 2023-06-08 | 2024-04-18 | On-time | 2024-06-07 | 50 | 2024-06-08 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46079348 | T2 PIT #1-COTTONWOOD 12/97 RMV NEST | ICS
LC | 126317662 | 014/103A | T2 EI HELMS-GREGG #1 14/103A RPR SPLS | FRESNO | ETL.4870.INSL.CERA | 2023-06-08 | 2023-06-08 | 2023-10-31 | On-time | 2024-06-07 | 220 | 2023-09-08 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Steel | Replace | 45883703 | T2 EI HELMS-GREGG #1 014/103A RPR SPLS | ICS
LC | 126317735 | A008/175 | T2 EI CSCD-BTN-DSCHTS A008/175 RPR INSW | TABLEMTN | ETL.6310.INSL.CERA | 2023-06-08 | 2023-06-08 | 2024-05-13 | On-time | 2024-06-07 | 25 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079356 | T2 EI CSCD-BTN-DSCHTS A008/175 RPR INSW | ICW
LC | 126346025 | 025/009 | T2 DI MAPLE CREEK-HOOPA 25/9 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-06-11 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46190236 | T2 DI MAPLE CREEK-HOOPA 25/9 RPR GYWW | ICW
LC | 126317902 | 008/141 | T2 WV TEMPLETON-ATASCADERO 8/141 RPL PL | PISMOBCH | ETL.9410.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-05-17 | On-time | 2024-06-07 | 21 | 2024-06-08 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35523962 | T2 WV TEMPLTN-ATSCDRO 08/135 RPL POLE | 70Y
LC | 126318326 | 091/004C | T2 EI HUMBOLDT-TRINITY 91/4C COMPLETE | EUREKA | ETL.1820.POLE.NWOD | 2023-06-08 | 2023-06-08 | 2024-06-05 | On-time | 2024-06-07 | 2 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096599 | T2 EI HUMBOLDT-TRINITY 91/04A RPR GYWW | ICW
LC | 126318530 | 091/004B | T2 EI HUMBOLDT-TRINITY 91/4B COMPLETE | EUREKA | ETL.1820.POLE.NWOD | 2023-06-08 | 2023-06-08 | 2024-06-05 | On-time | 2024-06-07 | 2 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096599 | T2 EI HUMBOLDT-TRINITY 91/04A RPR GYWW | ICW
LC | 126318603 | 091/004A | T2 EI HUMBOLDT-TRINITY 91/4A COMPLETE | EUREKA | ETL.1820.POLE.NWOD | 2023-06-08 | 2023-06-08 | 2024-06-05 | On-time | 2024-06-07 | 2 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096599 | T2 EI HUMBOLDT-TRINITY 91/04A RPR GYWW | ICW
LC | 126319151 | 006/056 | T2 EI PARADISE-TABLE MTN 06/056 RMV NEST | TABLEMTN | ETL.4316.TOWR | 2023-06-08 | 2023-06-08 | 2024-01-30 | On-time | 2024-06-07 | 129 | 2024-06-08 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46079347 | T2 EI PARADISE-TABLE MTN 06/056 RMV NEST | ICS
LC | 126319152 | 006/055AB | T2 EI PARADISE-TABLE MTN 6/55AB RPR GYWW | TABLEMTN | ETL.4316.POLE.STPS | 2023-06-08 | 2023-06-08 | 2024-01-26 | On-time | 2024-06-07 | 133 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079346 | T2 EI PARADISE-TABLE MTN 6/55AB RPR GYWW | ICW
LC | 126319619 | 031/608 | T2 EI HAT CRK #1-WSTWD 31/608 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2023-07-26 | On-time | 2024-06-07 | 317 | 2023-12-08 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31652163 | T2 EI HAT CRK #1-WSTWD 31/608 RPL STRW | 70Y
LC | 126319633 | 031/613 | T2 EI HAT CRK #1-WSTWD 31/613 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2023-07-26 | On-time | 2024-06-07 | 317 | 2023-12-08 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31652163 | T2 EI HAT CRK #1-WSTWD 31/608 RPL STRW | 70Y
LC | 126320638 | 014/000 | T2 EI HMBLDT BY-RO DLL JCT 14/0 RPL POLE | EUREKA | ETL.7100.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-05-10 | On-time | 2024-06-07 | 28 | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506675 | T2 EI HMBLDT BY-RO DLL JCT 14/0 RPL POLE | 70Y
LC | 126320695 | 006/015 | T2 EI CARIBOU PLUMAS JT 06/015 RPR GYWW | TABLEMTN | ETL.6290.POLE.NWOD | 2023-06-08 | 2023-06-08 | 2024-05-02 | On-time | 2024-06-07 | 36 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Pole-Wood | Repair | 46079345 | T2 EI CARIBOU PLUMAS JT 06/015 RPR GYWW | ICW
LC | 126320817 | 009/197 | T2 EI KILARC-DESCHUTES 9/197 RPR INSW | TABLEMTN | ETL.7300.INSL.NCER | 2023-06-08 | 2023-06-08 | 2024-04-04 | On-time | 2024-06-07 | 64 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079280 | T2 EI KILARC-DESCHUTES 9/197 RPR INSW | ICW
LC | 126346294 | 017/004 | T2 DI TRNTY-MPL CRK 17/04R RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-11 | 2023-06-05 |  | Late | 2024-06-04 |  | 2023-12-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079361 | T2 DI TRNTY-MPL CRK 017/004 RPR ANCHOR | ICW
LC | 126346295 | 017/004 | T2 DI TRNTY-MPL CRK 017/004 RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-11 | 2023-06-05 |  | Late | 2024-06-04 |  | 2023-12-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079361 | T2 DI TRNTY-MPL CRK 017/004 RPR ANCHOR | ICW
LC | 126346316 | 067/340 | T2 DI MALIN RD MTN#2 67/340 RPR FOND | TABLEMTN | ETL.6020.TOWR | 2023-06-11 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46132326 | T2 DI MALIN RD MTN#2 67/340 MASTIC | ICQ
LC | 126346975 | 003/033 | T2 DI LAKEVILLE-SONOMA #2 3/33 RPL DMPS | LAKEVLLE | ETL.2070.INSL.NCER | 2023-06-11 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46204146 | T2 DI LAKEVILLE-SONOMA #2 3/33 RPL DMPS | ICS
LC | 126347013 | 001/010 | T2 EI PALERMO-OROVILE #2 01/010 RPL INSS | TABLEMTN | ETL.7740.INSL.CERA | 2023-06-11 | 2023-06-11 |  | Late | 2024-06-10 |  | 2024-06-11 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513070 | T2 EI PALERMO-OROVILE #2 01/010 RPL INSS | 93K
LC | 126347014 | 001/010 | T2 EI PALERMO-WYANDOTTE 01/010 RPL INSS | TABLEMTN | ETL.4315.INSL.CERA | 2023-06-11 | 2023-06-11 |  | Late | 2024-06-10 |  | 2024-06-11 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513069 | T2 EI PALERMO-WYANDOTTE 01/010 RPL INSS | 93K
LC | 126347044 | 024/000 | T2 DI TRINITY-MAPL CRK 24/0 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-11 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503538 | T2 DI TRINITY-MAPL CRK 24/0 RPL STRW | 70Y
LC | 126320837 | 010/212 | T2 EI KILARC-DESCHUTES 10/212 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-04-04 | On-time | 2024-06-07 | 64 | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515679 | T2 EI KILARC-DESCHUTES 10/208 RPL POLE | 70Y
LC | 126320850 | 009/194 | T2 EI KILARC-DESCHUTES 9/194 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-04-05 | On-time | 2024-06-07 | 63 | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515678 | T2 EI KILARC-DESCHUTES 9/193 RPL STRW | 70Y
LC | 126320852 | 010/209 | T2 EI KILARC-DESCHUTES 10/209 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-04-04 | On-time | 2024-06-07 | 64 | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515679 | T2 EI KILARC-DESCHUTES 10/208 RPL POLE | 70Y
LC | 126347092 | 046/009 | T2 DI TRINITY-MAPLE CREEK 46/09 RMV STEP | EUREKA | ETL.8170.POLE.NWOD | 2023-06-11 | 2023-06-05 | 2024-06-06 | Late | 2024-06-04 | -2 | 2024-06-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46096678 | T2 DI TRINITY-MAPLE CREEK 46/09 RMV STEP | ICW
LC | 126320857 | 010/208 | T2 EI KILARC-DESCHUTES 10/208 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-04-04 | On-time | 2024-06-07 | 64 | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515679 | T2 EI KILARC-DESCHUTES 10/208 RPL POLE | 70Y
LC | 126320872 | 009/204 | T2 EI KILARC-DESCHUTES 9/204 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-04-04 | On-time | 2024-06-07 | 64 | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515678 | T2 EI KILARC-DESCHUTES 9/193 RPL STRW | 70Y
LC | 126347202 | 006/126 | T2 DI CRBOU WSTWD 06/126 RPR ANCW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-11 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46091798 | T2 DI CRBOU WSTWD 06/126 RPR ANCW | ICW
LC | 126320877 | 009/193 | T2 EI KILARC-DESCHUTES 9/193 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-04-05 | On-time | 2024-06-07 | 63 | 2024-06-08 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515678 | T2 EI KILARC-DESCHUTES 9/193 RPL STRW | 70Y
LC | 126347314 | 012/259-GUY | T2 DI LAKEVILLE #2 12/259-GUY RPR GYWW | LAKEVLLE | ETL.7340.POLE.WOOD | 2023-06-11 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096619 | T2 DI LAKEVILLE #2 12/259-GUY RPR GYWW | ICW
LC | 126321084 | 058/000 | T2 EI ELK-GUALALA 058/000 RPR POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-01-19 | On-time | 2024-06-07 | 140 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46087975 | T2 EI ELK-GUALALA 058/000 RPR POLE | ICW
LC | 126321091 | A008/182 | T2 EI CSCD-BNTN-DSCTS A8/182 RPR GYWW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-05-16 | On-time | 2024-06-07 | 22 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079357 | T2 EI CSCD-BNTN-DSCTS A008/182 RPR GYWW | ICW
LC | 126321142 | 090/010C | T2 EI HUMBOLDT-TRINITY 90/10C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-08 | 2023-06-08 | 2024-06-05 | On-time | 2024-06-07 | 2 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096598 | T2 EI HUMBOLDT-TRINITY 90/10A RPR GYWW | ICW
LC | 126347392 | 005/066 | T2 EI HAT CREEK #1-PIT #1 5/66 RPL STRW | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-11 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521448 | T2 EI HAT CREEK #1-PIT #1 05/066 RPL PL | 70Y
LC | 126347401 | 005/068 | T2 EI HAT CREEK #1-PIT #1 5/68 RPL STRW | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-11 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521448 | T2 EI HAT CREEK #1-PIT #1 05/066 RPL PL | 70Y
LC | 126347408 | 005/062 | T2 EI HAT CREEK #1-PIT #1 5/62 RPL STRW | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-11 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521447 | T2 EI HAT CREEK #1-PIT #1 05/061 RPL PL | 70Y
LC | 126347420 | 005/061 | T2 EI HAT CREEK #1-PIT #1 5/61 RPL STRW | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-11 | 2023-06-10 |  | Late | 2024-06-09 |  | 2023-12-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521447 | T2 EI HAT CREEK #1-PIT #1 05/061 RPL PL | 70Y
LC | 126347422 | 005/064 | T2 EI HAT CREEK #1-PIT #1 5/64 RPL STRW | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-11 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521447 | T2 EI HAT CREEK #1-PIT #1 05/061 RPL PL | 70Y
LC | 126321223 | 090/010B | T2 EI HUMBOLDT-TRINITY 90/10B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-08 | 2023-06-08 | 2024-06-07 | On-time | 2024-06-07 | 0 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096598 | T2 EI HUMBOLDT-TRINITY 90/10A RPR GYWW | ICW
LC | 126321228 | 064/000C | T2 EI HUMBOLDT-TRINITY 64/0C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-08 | 2023-06-08 | 2024-04-12 | On-time | 2024-06-07 | 56 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096531 | T2 EI HUMBOLDT-TRINITY 64/0A RPR GYWW | ICW
LC | 126321229 | 064/000A | T2 EI HUMBOLDT-TRINITY 64/0A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-08 | 2023-06-08 | 2024-04-12 | On-time | 2024-06-07 | 56 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096531 | T2 EI HUMBOLDT-TRINITY 64/0A RPR GYWW | ICW
LC | 126321300 | 064/000B | T2 EI HUMBOLDT-TRINITY 64/0B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-08 | 2023-06-08 | 2024-04-12 | On-time | 2024-06-07 | 56 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096531 | T2 EI HUMBOLDT-TRINITY 64/0A RPR GYWW | ICW
LC | 126321826 | 019/003 | T2 EXCHEQUER-MARIPOSA 19/3 RPL POLE | FRESNO | ETL.8640.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-05-23 | On-time | 2024-06-07 | 15 | 2024-06-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506442 | T2 EXCHEQUER-MARIPOSA 19/3 RPL POLE | 70Y
LC | 126322062 | 043/013 | T2 EI TRINITY-MAPLE CREEK 43/13 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-08 | 2023-06-08 | 2024-06-04 | On-time | 2024-06-07 | 3 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096674 | T2 EI TRINITY-MAPLE CREEK 43/13 RPR GYWW | ICW
LC | 126322234 | 090/010A | T2 EI HUMBOLDT-TRINITY 90/10A COMPLETED | EUREKA | ETL.1820.POLE.NWOD | 2023-06-08 | 2023-06-08 | 2024-06-05 | On-time | 2024-06-07 | 2 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096598 | T2 EI HUMBOLDT-TRINITY 90/10A RPR GYWW | ICW
LC | 126322499 | 044/009 | T2 EI TRNTY-MPL CRK 44/9 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-08 | 2023-06-08 | 2024-06-06 | On-time | 2024-06-07 | 1 | 2024-06-08 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172195 | T2 EI TRNTY-MPL CRK 44/9 RPR GYWW | ICW
LC | 126347583 | 001/036 | T2 DI CARIBOU-WESTWOOD 001/036 RPR GYWW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-11 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091792 | T2 DI CARIBOU-WESTWOOD 001/036 RPR GYWW | ICW
LC | 126347687 | 004/091 | T2 DI CARIBOU-WSWD 004/091 RPR STRW | TABLEMTN | ETL.6300.POLE.NWOD | 2023-06-11 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091796 | T2 DI CARIBOU-WSWD 004/091 RPR STRW | ICW
LC | 126345973 | 013/007 | T2 DI PHILO JCT-ELK 13/7 RPR INSW | WILLITS | ETL.7780.INSL.NCER | 2023-06-11 | 2023-06-08 | 2024-04-30 | On-time | 2024-06-07 | 38 | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46089117 | T2 DI PHILO JCT-ELK 13/7 RPR INSW | ICW
LC | 126346007 | 013/007 | T2 DI PHILO JCT-ELK 13/7 RPR GYWW | WILLITS | ETL.7780.POLE.NWOD | 2023-06-11 | 2023-06-08 | 2024-04-30 | On-time | 2024-06-07 | 38 | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46089118 | T2 DI PHILO JCT-ELK 13/7 RPR GYWW | ICW
LC | 126347807 | 002/016 | T2 DI PIT#4 TP 2/16 RPL DMPS | TABLEMTN | ETL.5432.INSL.CERA | 2023-06-11 | 2023-06-08 | 2024-06-25 | Late | 2024-06-07 | -18 | 2024-06-08 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 46079340 | T2 DI PIT#4 TP 2/16 RPL DMPS | ICS
LC | 126347847 | 005/107 | T2 DI CRBOU WSTWD 05/107 RPR ANCW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-11 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46079343 | T2 DI CRBOU WSTWD 05/107 RPR ANCW | ICW
LC | 126347858 | 007/000 | T2 DI MPL CRK-HOOPA 7/0 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-06-11 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46203525 | T2 DI MPL CRK-HOOPA 7/0 RPR GYWW | ICW
LC | 126347867 | 000/013 | T2 DI MPL CRK-HOOPA 0/13 RPR JMPW | EUREKA | ETL.7490.INSL.NCER | 2023-06-11 | 2023-06-09 |  | Late | 2024-06-08 |  | 2023-09-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46203497 | T2 DI MPL CRK-HOOPA 0/13 RPR JMPW | ICW
LC | 126347906 | 005/107 | T2 DI CRBOU WSTWD 05/107 RPR INSW | TABLEMTN | ETL.6300.INSL.NCER | 2023-06-11 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079344 | T2 DI CRBOU WSTWD 05/107 RPR INSW | ICW
LC | 126346231 | 017/003 | T2 DI LAYTONVILLE-WILLITS 17/3C RPR GYWW | WILLITS | ETL.8360.POLE.STPS | 2023-06-11 | 2023-06-08 | 2024-06-06 | On-time | 2024-06-07 | 1 | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46227568 | T2 DI LAYTONVILLE-WILLITS 17/3C RPR GYWW | ICW
LC | 126347937 | 011/011 | T2 DI BRDGVL-GRBRVL 11/11 RPL HRDD | EUREKA | ETL.6220.POLE.WOOD | 2023-06-11 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46087887 | T2 DI BRDGVL-GRBRVL 11/11 RPL HRDD | ICW
LC | 126347959 | ;000/020 | T2 DI CARIBOU#2 ;000/020 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2023-06-11 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527047 | T2 DI CARIBOU#2 ;000/020 RPL POLE | 70Y
LC | 126347965 | 027/001 | T2 DI TRNTY-MPL CRK 27/1 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-11 | 2023-06-05 | 2024-06-13 | Late | 2024-06-04 | -9 | 2023-12-05 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172034 | T2 DI TRNTY-MPL CRK 027/001 RPR GYWW | ICW
LC | 126347966 | 027/001 | T2 DI TRNTY-MPL CRK 027/001 RMV VEG | TABLEMTN | ETL.8170.POLE.NWOD | 2023-06-11 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126346235 | 017/003 | T2 DI LAYTONVILLE-WILLITS 17/3R RPR GYWW | WILLITS | ETL.8360.POLE.STPS | 2023-06-11 | 2023-06-08 | 2024-06-06 | On-time | 2024-06-07 | 1 | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46227569 | T2 DI LAYTONVILLE-WILLITS 17/3R RPR GYWW | ICW
LC | 126347050 | 009/109 | T2 DI DRUM-SUMMIT #2 9/109L RPR GYWW | SACTO | ETL.1450.POLE.WDPS | 2023-06-11 | 2023-06-08 | 2024-05-23 | On-time | 2024-06-07 | 15 | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098218 | T2 DI DRUM-SUMMIT #2 9/109L RPR GYWW | ICW
LC | 126347052 | 009/109 | T2 DI DRUM-SUMMIT #2 9/109R RPR GYWW | SACTO | ETL.1450.POLE.WDPS | 2023-06-11 | 2023-06-08 | 2024-05-23 | On-time | 2024-06-07 | 15 | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098219 | T2 DI DRUM-SUMMIT #2 9/109R RPR GYWW | ICW
LC | 126347058 | 009/109 | T2 DI DRUM-SUMMIT #2 9/109L RPR STRW | SACTO | ETL.1450.POLE.WDPS | 2023-06-11 | 2023-06-08 | 2024-05-23 | On-time | 2024-06-07 | 15 | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46098240 | T2 DI DRUM-SUMMIT #2 9/109L RPR STRW | ICW
LC | 126348255 | 003/030 | T2 DI ROCK CREEK-POE 3/30 RPR FOND | TABLEMTN | ETL.5630.TOWR | 2023-06-11 | 2023-06-05 | 2024-06-07 | Late | 2024-06-04 | -3 | 2024-06-05 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46102374 | T2 DI ROCK CREEK-POE 003/030 RPR FOND | ICQ
LC | 126348257 | 019/289 | T2 DI GOLD HILL #1 019/289 RPL INSW | SACTO | ETL.6950.INSL.NCER | 2023-06-11 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35517330 | T2 DI GOLD HILL #1 019/289 RPL INSW | 93I
LC | 126348308 | 040/005 | T2 RIO DELL JCT-BRIDGEVILLE 40/5 GO95 | EUREKA | ETL.7850.POLE.WOOD | 2023-06-11 | 2023-06-11 |  | Late | 2024-06-10 |  | 2024-06-11 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31613218 | T2 RIO DELL JCT-BRIDGEVILL 39/1 RPL POLE | 70Y
LC | 126347436 | 066/332 | T2 DI MALIN-ROND MTN #2 66/332 COMPLETE | TABLEMTN | ETL.6020.TOWR | 2023-06-11 | 2023-06-08 | 2024-05-10 | On-time | 2024-06-07 | 28 | 2024-06-08 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46079354 | T2 DI MALIN-ROND MTN #2 66/332 RPR OPGW | ICS
LC | 126348781 | 027/005 | T2 MAPLE CREEK-HOOPA 27/005 GO95 CLEAR | EUREKA | ETL.7490.POLE.NWOD | 2023-06-11 | 2023-06-11 |  | Late | 2024-06-10 |  | 2024-06-11 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654783 | T2 MAPLE CREEK-HOOPA 27/005 GO95 | 93G
LC | 126347473 | 29 | T2 DI CARIBOU #2 25/651 RPR SWTCHW | TABLEMTN | ETL.6280.SWIT | 2023-06-11 | 2023-06-08 | 2023-07-27 | On-time | 2024-06-07 | 316 | 2023-09-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 45855519 | T2 DI CARIBOU #2 25/651 RPR SWTCHW | ICW
LC | 126348807 | A000/005 | T2 SMARTVILLE-CAMP FAR WEST A000/5 GO95 | SACTO | ETL.7970.POLE.WOOD | 2023-06-11 | 2023-06-11 |  | Late | 2024-06-10 |  | 2024-06-11 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31653040 | T2 SMTVL-CMP FR WST A0/4 GO95 | 93G
LC | 126348808 | A000/012 | T2 SMARTVILLE-CAMP FAR WEST A000/12 GO95 | SACTO | ETL.7970.POLE.WOOD | 2023-06-11 | 2023-06-11 |  | Late | 2024-06-10 |  | 2024-06-11 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31653040 | T2 SMTVL-CMP FR WST A0/4 GO95 | 93G
LC | 126348813 | 035/002 | T2 RIO DELL JCT-BRIDGEVILLE 35/2 GO95 | EUREKA | ETL.7850.POLE.WOOD | 2023-06-11 | 2023-06-11 |  | Late | 2024-06-10 |  | 2024-06-11 | 401T | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35517206 | T2 RIO DELL JCT-BRIDGEVILLE 35/2 GO95 | 93G
LC | 126347519 | 004/039 | T2 DI ROCK CRK-POE 4/39 RPL INSS | TABLEMTN | ETL.5630.INSL | 2023-06-11 | 2023-06-08 | 2024-02-25 | On-time | 2024-06-07 | 103 | 2024-06-08 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509199 | T2 DI ROCK CREEK-POE :5/33 RPLC INSS | 93K
LC | 126347540 | 006/007 | T2 DI MAPLE CREEK-HOOPA 6/7 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-06-11 | 2023-06-08 | 2023-09-07 | On-time | 2024-06-07 | 274 | 2023-12-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45885329 | T2 DI MAPLE CREEK-HOOPA 6/7 RPR GYWW | ICW
LC | 126347726 | 002/018 | T2 DI PIT#4 TP 2/18 RPR SHLS | TABLEMTN | ETL.5432.TOWR | 2023-06-11 | 2023-06-08 | 2023-10-03 | On-time | 2024-06-07 | 248 | 2023-12-08 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45855689 | T2 DI PIT#4 TP 2/18 RPR SHLS | ICS
LC | 126355339 | 008/010 | T2 DI TRINITY-MAPLE CREEK 08/10 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-12 | 2023-06-08 | 2024-01-23 | On-time | 2024-06-07 | 136 | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079278 | T2 DI TRINITY-MAPLE CREEK 008/10 COTTER | ICW
LC | 126355405 | 008/010 | T2 DI TRINITY-MAPLE CREEK 008/10 COTTER | EUREKA | ETL.8170.INSL.CERA | 2023-06-12 | 2023-06-08 | 2024-01-23 | On-time | 2024-06-07 | 136 | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079278 | T2 DI TRINITY-MAPLE CREEK 008/10 COTTER | ICW
LC | 126365257 | 009/110 | T2 DI DRUM-SUMMIT #1 009/110C RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2023-06-13 | 2023-06-08 | 2024-05-22 | On-time | 2024-06-07 | 16 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098243 | T2 DI DRUM-SUMMIT #1 009/110C RPR GYWW | ICW
LC | 126365408 | 009/133A | T2 DI DELTA-MTN GATE JCT 9/133A RPR GYWW | TABLEMTN | ETL.6750.POLE.NWOD | 2023-06-13 | 2023-06-08 | 2023-07-12 | On-time | 2024-06-07 | 331 | 2023-12-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45866265 | T2 DI DELTA-MTN GATE JCT 9/133A RPR GYWW | ICW
LC | 126365409 | 009/133B | T2 DI DELTA-MTN GATE JCT 9/133B RPR GYWW | TABLEMTN | ETL.6750.POLE.NWOD | 2023-06-13 | 2023-06-08 | 2023-07-12 | On-time | 2024-06-07 | 331 | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45926048 | T2 DI DELTA-MTN GATE JCT 9/133B RPR GYWW | ICW
LC | 126365431 | 009/133C | T2 DI DELTA-MTN GATE JCT 9/133A RPR GYWW | TABLEMTN | ETL.6750.POLE.NWOD | 2023-06-13 | 2023-06-08 | 2023-07-12 | On-time | 2024-06-07 | 331 | 2023-12-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45866266 | T2 DI DELTA-MTN GATE JCT 9/133A RPR GYWW | ICW
LC | 126365432 | 009/133C | T2 DI DELTA-MTN GATE JCT 9/133C RPR GYWW | TABLEMTN | ETL.6750.POLE.NWOD | 2023-06-13 | 2023-06-08 | 2023-07-12 | On-time | 2024-06-07 | 331 | 2023-12-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45866267 | T2 DI DELTA-MTN GATE JCT 9/133C RPR GYWW | ICW
LC | 126365433 | 009/133A | T2 DI DELTA-MTN GATE JCT 9/133A RPR ANCW | TABLEMTN | ETL.6750.POLE.NWOD | 2023-06-13 | 2023-06-08 | 2023-07-12 | On-time | 2024-06-07 | 331 | 2023-12-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45866264 | T2 DI DELTA-MTN GATE JCT 9/133A RPR ANCW | ICW
LC | 126349268 | 005/062 | T2 PIT #5-ROUND MTN #1 05/62L RPL POLE | TABLEMTN | ETL.5420.POLE.WDPS | 2023-06-12 | 2023-05-18 |  | Late | 2024-05-17 |  | 2024-05-18 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526327 | T2 DI PIT#5-RND MT#1 RPL 4 STRW | 70Y
LC | 126349518 | 029/573 | T2 EI HAT CRK #1-WESTWOOD 29/573 RPL PL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-12 | 2023-06-12 | 2024-06-20 | Late | 2024-06-11 | -9 | 2024-06-12 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514134 | T2 DI HAT CRK#1-WSTWD-29/565 RPL POLE | 70Y
LC | 126349887 | 053/260 | T2 EI CORTINA-MENDOCN #1 53/260 CNCL | WILLITS | ETL.1330.INSL.CERA | 2023-06-12 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31676905 | EI CORTINA-MENDOCN #1 RPL INSS IN 5 TWRS | 93K
LC | 126365434 | 009/133B | T2 DI DELTA-MTN GATE JCT 9/133B RPR ANCW | TABLEMTN | ETL.6750.POLE.NWOD | 2023-06-13 | 2023-06-08 | 2023-07-12 | On-time | 2024-06-07 | 331 | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45907332 | T2 DI DELTA-MTN GATE JCT 9/133B RPR ANCW | ICW
LC | 126365610 | 001/012 | T2 DI KIRCKHFF#1-KIRCKHF#2 1/12 RPR GYWT | FRESNO | ETL.1880.POLE.NWOD | 2023-06-13 | 2023-06-08 | 2024-01-23 | On-time | 2024-06-07 | 136 | 2024-06-08 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46102375 | T2 DI KIRCKHFF#1-KIRCKHF#2 1/12 RPR GYWT | ICQ
LC | 126365730 | 005/108 | T2 DI KILARC-DESCHUTES 5/108 RPR GYWW | TABLEMTN | ETL.7300.POLE.NWOD | 2023-06-13 | 2023-06-08 | 2023-10-18 | On-time | 2024-06-07 | 233 | 2023-12-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45855518 | T2 DI KILARC-DESCHUTES 5/108 RPR GYWW | ICW
LC | 126350378 | 059/294 | T2 DI MALIN-ROUND MTN #2 59/294 UNBURY | TABLEMTN | ETL.6020.TOWR | 2023-06-12 | 2023-06-02 |  | Late | 2024-06-01 |  | 2024-06-02 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46075981 | T2 DI MALIN-ROUND MTN #2 59/294 UNBURY | ICQ
LC | 126375884 | 010/002 | T2 DI LAKEVILLE #1 10/2 RPR GYWW | LAKEVLLE | ETL.7360.POLE.WOOD | 2023-06-14 | 2023-06-08 | 2024-05-07 | On-time | 2024-06-07 | 31 | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079840 | T2 DI LAKEVILLE #1 10/2 RPR GYWW | ICW
LC | 126404666 | 025/007 | T2 DI PHILO JCT-ELK 025/007 RPL ANCW | WILLITS | ETL.7780.POLE.WOOD | 2023-06-20 | 2023-06-08 | 2024-05-22 | On-time | 2024-06-07 | 16 | 2024-06-08 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35522272 | T2 DI PHILO JCT-ELK 025/007 RPL ANCW | 93E
LC | 126324160 | A006/137 | T2 CSCDE-BNTN-DESCHUTES A6/137 RPL HRDW | TABLEMTN | ETL.6310.INSL.NCER | 2023-06-09 | 2023-06-09 | 2024-05-13 | On-time | 2024-06-08 | 26 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46091809 | T2 CSCDE-BNTN-DESCHUTES A6/137 RPL HRDW | ICW
LC | 126327594 | 006/101 | T2 EI SN MTEO-HLSDLE JCT 06/101 RPL HRDW | METCALF | ETL.7950.POLE.WOOD | 2023-06-09 | 2023-06-09 | 2024-04-17 | On-time | 2024-06-08 | 52 | 2024-06-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46080487 | T2 EI SN MTEO-HLSDLE JCT 06/101 RPL HRDW | ICW
LC | 126327843 | 026/190 | T2 EI CARIBOU-TABLE MTN 026/190 INS DMPS | TABLEMTN | ETL.4440.INSL.CERA | 2023-06-09 | 2023-06-09 | 2024-06-07 | On-time | 2024-06-08 | 1 | 2024-06-09 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 46083529 | T2 EI CARIBOU-TABLE MTN 026/190 INS DMPS | ICS
LC | 126327903 | B020/442 | T2 DRM-GRSS VLLY-WMAR B20/442 RPL HRDW | SACTO | ETL.6760.POLE.WOOD | 2023-06-09 | 2023-06-09 | 2024-01-12 | On-time | 2024-06-08 | 148 | 2024-06-09 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46125243 | T2 DRM-GRSS VLLY-WMAR B20/442 RPL HRDW | ICW
LC | 126352109 | 024/187 | T2 EI PRDS-TBL MTN 24/187B RPR ANCW | TABLEMTN | ETL.4316.POLE.NWOD | 2023-06-12 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46093363 | T2 EI PRDS-TBL MTN 24/187B RPR ANCW | ICW
LC | 126352284 | 011/258 | T2 DI SALINAS-LAURELES 11/258 RPL POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-12 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507120 | T2 DI SALINAS-LAURELES 11/258 RPL POLE | 70Y
LC | 126329314 | 010/053 | T2 WV TULUCAY-VACA-VACA 010/053 RPR INSS | SACTO | ETL.5800.INSL.NCER | 2023-06-09 | 2023-06-09 | 2024-05-28 | On-time | 2024-06-08 | 11 | 2024-06-09 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 31608467 | T2 DI TULUCAY-VACA RPL INSS 4TWR | 93K
LC | 126353261 | 000/005C | T2 EI ROCK CREEK-POE 0/05C RPR FOND | TABLEMTN | ETL.5630.POLE.NWOD | 2023-06-12 | 2023-06-12 | 2024-06-27 | Late | 2024-06-11 | -16 | 2024-06-12 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46132646 | T2 EI ROCK CREEK-POE 00/005B RPR FOND | ICQ
LC | 126329318 | 004/101 | T2 EI KILARC-DESCHUTES 4/101 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-09 | 2023-06-09 | 2024-04-03 | On-time | 2024-06-08 | 66 | 2024-06-09 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515350 | T2 EI KILARC-DESCHUTES 4/101 RPL POLE | 70Y
LC | 126353534 | 016/001 | T2 DI TRNTY-MPL CRK 16/01 RPR JMPRW | EUREKA | ETL.8170.INSL.NCER | 2023-06-12 | 2023-06-06 |  | Late | 2024-06-05 |  | 2023-09-06 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46190012 | T2 DI TRNTY-MPL CRK 16/01 RPR JMPRW | ICW
LC | 126329350 | 005/109 | T2 EI KILARC-DESCHUTES 5/109 RPR WDPK | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-09 | 2023-06-09 | 2024-04-02 | On-time | 2024-06-08 | 67 | 2024-06-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088725 | T2 EI KILARC-DESCHUTES 5/109 RPR WDPK | ICW
LC | 126329610 | 068/343 | T2 EI MALIN-ROUND MTN #2 68/343 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2023-06-09 | 2023-06-09 | 2023-12-21 | On-time | 2024-06-08 | 170 | 2024-06-09 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46083464 | T2 EI MALIN-ROUND MTN #2 68/343 RPR INSS | ICS
LC | 126353847 | 033/633 | T2 EI HAT CRK #1-WESTWD 33/633 RPL PL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-12 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514209 | T2 EI HAT CRK #1-WESTWD 33/633 RPL PL | 70Y
LC | 126353848 | 032/632 | T2 EI HAT CRK #1-WESTWD 32/632 RPL PL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-12 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514202 | T2 EI HT CRK #1-WESTWOOD 32/623 RPL PL | 70Y
LC | 126353910 | 005/026 | T2 EI MORRO BAY-TEMPLETON 5/26 CANCEL | PISMOBCH | ETL.5933.INSL | 2023-06-12 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35524360 | T0 EI MORRO BAY-TEMPLETON 14/58 RPL INSS | 93K
LC | 126353912 | 005/026 | T2 EI MORRO BAY-TEMPLETON 5/026 CNCL | PISMOBCH | ETL.5280.INSL | 2023-06-12 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35524297 | T0 EI MORRO BY-CALIF 14/58 RPL INSS | 93K
LC | 126330209 | 005/051 | T2 EI PARADISE-TABLE MTN 05/051 UNBURY | TABLEMTN | ETL.4316.TOWR | 2023-06-09 | 2023-06-09 | 2024-04-04 | On-time | 2024-06-08 | 65 | 2024-06-09 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46132393 | T2 EI PARADISE-TABLE MTN 05/051 UNBURY | ICQ
LC | 126353982 | 033/638 | T2 EI HAT CRK #1-WESTWD 33/638 RPL PL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-12 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514209 | T2 EI HAT CRK #1-WESTWD 33/633 RPL PL | 70Y
LC | 126353986 | 033/642 | T2 EI HAT CREEK #1-WSTWD 33/642 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-12 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35514209 | T2 EI HAT CRK #1-WESTWD 33/633 RPL PL | 70Y
LC | 126353992 | 033/639 | T2 EI HT CRK #1-WSTWD 33/639 RPR STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-12 | 2023-06-12 | 2024-06-18 | Late | 2024-06-11 | -7 | 2024-06-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091819 | T2 EI HAT CRK #1-WESTWD 33/639 RPR WDPKR | ICW
LC | 126354133 | 012/413 | T2 EI SPAULDING-SUMMIT 12/413 RPL POLE | SACTO | ETL.8060.POLE.WOOD | 2023-06-12 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508783 | T2 EI SPAULDING-SUMMIT 12/413 RPL POLE | 70Y
LC | 126330210 | 005/048 | T2 EI PARADISE-TABLE MTN 05/048 UNBURY | TABLEMTN | ETL.4316.TOWR | 2023-06-09 | 2023-06-09 | 2024-04-04 | On-time | 2024-06-08 | 65 | 2024-06-09 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46132394 | T2 EI PARADISE-TABLE MTN 05/048 UNBURY | ICQ
LC | 126330624 | 111/005 | T2 EI HMBLDT-BRIDGVILE 111/005R RPR GYWW | EUREKA | ETL.1810.POLE.WDPS | 2023-06-09 | 2023-06-09 | 2024-01-11 | On-time | 2024-06-08 | 149 | 2024-06-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46134940 | T2 EI HMBLDT-BRIDGVILE 111/005R RPR GYWW | ICW
LC | 126330846 | 111/005 | T2 EI HMBLDT-BRIDGVILE 111/005L RPR GYWW | EUREKA | ETL.1810.POLE.WDPS | 2023-06-09 | 2023-06-09 | 2024-01-11 | On-time | 2024-06-08 | 149 | 2024-06-09 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46134941 | T2 EI HMBLDT-BRIDGVILE 111/005L RPR GYWW | ICW
LC | 126331005 | 004/007 | T2 FORT BRAGG-ELK 4/7 GO95 CLEAR | WILLITS | ETL.2060.POLE.WOOD | 2023-06-09 | 2023-06-09 | 2024-02-27 | On-time | 2024-06-08 | 102 | 2024-06-09 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654427 | EQUET2 FORT BRAGG-ELK 004/007 GO95 CLEAR | 93G
LC | 126354838 | 023/626 | T2 DI CARIBOU#2 23/626 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-06-12 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079351 | T2 DI CARIBOU#2 23/626 RPR GYWW | ICW
LC | 126355266 | 005/024 | T2 EI MORRO BAY-TEMPLETON 5/24 RPL INSS | PISMOBCH | ETL.5933.INSL | 2023-06-12 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35524360 | T0 EI MORRO BAY-TEMPLETON 14/58 RPL INSS | 93K
LC | 126331264 | 007/119 | T2 SISQUOC-SNTA YNEZ SS 7/119 GO95 | PISMOBCH | ETL.3700.POLE.WOOD | 2023-06-09 | 2023-06-09 | 2024-06-07 | On-time | 2024-06-08 | 1 | 2024-06-09 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656735 | T2 SISQUOC-SNTA YNEZ SS 7/119 GO95 | 93G
LC | 126331265 | 007/120 | T2 SISQUOC-SNTA YNEZ SS 7/120 GO95 | PISMOBCH | ETL.3700.POLE.WOOD | 2023-06-09 | 2023-06-09 | 2024-06-06 | On-time | 2024-06-08 | 2 | 2024-06-09 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656735 | T2 SISQUOC-SNTA YNEZ SS 7/119 GO95 | 93G
LC | 126355514 | ;023/007 | T2 KONCTI-MIDDLTWN ;023/007 RPR INSW | WILLITS | ETL.6380.INSL.CERA | 2023-06-12 | 2023-06-12 | 2024-06-24 | Late | 2024-06-11 | -13 | 2024-06-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46213762 | T2 KONCTI-MIDDLTWN ;023/007 RPR INSW | ICW
LC | 126331352 | 008/010 | T2 FORT BRAGG-ELK 008/010 GO95 CLEAR | WILLITS | ETL.2060.POLE.WOOD | 2023-06-09 | 2023-06-09 | 2024-02-23 | On-time | 2024-06-08 | 106 | 2024-06-09 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654427 | EQUET2 FORT BRAGG-ELK 004/007 GO95 CLEAR | 93G
LC | 126355843 | 003/010 | T2 DI MLNES RCTRCK 03/10 RPL POLE | VICTOR | ETL.2400.POLE.WOOD | 2023-06-12 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35529728 | T2 DI MLNES RCTRCK 03/10 RPL POLE | 70Y
LC | 126346114 | 031/166 | T2 DI EXCHQUR-INDN FLT 31/166 RPR INSS | FRESNO | ETL.8650.INSL.NCER | 2023-06-11 | 2023-06-09 | 2023-12-13 | On-time | 2024-06-08 | 178 | 2024-06-09 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45954715 | T2 DI EXCHQUR-INDN FLT 31/166 RPR INSS | ICS
LC | 126356157 | 004/048 | T2 EI HAT CREEK #1-PIT #1 4/48 RPL POLE | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-12 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35517036 | T2 EI HAT CREEK #1-PIT #1 4/48 RPL POLE | 70Y
LC | 126356158 | 004/055 | T2 EI HAT CREEK #1-PIT #1 4/55 RPL STRW | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-12 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521446 | T2 EI HAT CREEK #1-PIT #1 4/54 RPL STRW | 70Y
LC | 126346136 | 029/153 | T2 DI EXCHQUR-INDN FLT 29/153 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-06-11 | 2023-06-09 | 2023-12-14 | On-time | 2024-06-08 | 177 | 2023-09-09 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45954651 | T2 DI EXCHQUR-INDN FLT 29/153 RPR JMPS | ICS
LC | 126356197 | 004/047 | T2 EI HAT CREEK #1-PIT #1 4/47 CANCEL | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-12 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521445 | T2 EI HAT CREEK #1-PIT #1 03/037 RPL PL | 70Y
LC | 126356201 | 004/054 | T2 EI HAT CREEK #1-PIT #1 4/54 RPL STRW | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-12 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521446 | T2 EI HAT CREEK #1-PIT #1 4/54 RPL STRW | 70Y
LC | 126346258 | 067/340 | T2 DI MALIN RD MTN#2 67/340 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-06-11 | 2023-06-09 | 2024-05-10 | On-time | 2024-06-08 | 29 | 2024-06-09 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46083463 | T2 DI MALIN RD MTN#2 67/340 RPR SHLS | ICS
LC | 126356258 | 112/005 | T2 EI HMBLT-BRDGVL 112/5 RPR INSW | EUREKA | ETL.1810.INSL.NCER | 2023-06-12 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46170402 | T2 EI HMBLT-BRDGVL 112/5 RPR INSW | ICW
LC | 126346270 | 000/003 | T2 DI CARIBOU-PLUMAS JCT 0/3 RPR GYWW | TABLEMTN | ETL.6290.POLE.NWOD | 2023-06-11 | 2023-06-09 | 2024-05-06 | On-time | 2024-06-08 | 33 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091788 | T2 DI CARIBOU-PLUMAS JCT 0/3 RPR GYWW | ICW
LC | 126346271 | 000/003 | T2 DI CARIBOU-PLUMAS JCT 0/3 RPR ANCW | TABLEMTN | ETL.6290.POLE.NWOD | 2023-06-11 | 2023-06-09 | 2024-05-06 | On-time | 2024-06-08 | 33 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46091789 | T2 DI CARIBOU-PLUMAS JCT 0/3 RPR ANCW | ICW
LC | 126347152 | 026/115 | T2 DI EXCHQUR-INDN FLT 26/115 COTTER | FRESNO | ETL.8650.INSL.NCER | 2023-06-11 | 2023-06-09 | 2023-12-13 | On-time | 2024-06-08 | 178 | 2024-06-09 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45954719 | T2 DI EXCHQUR-INDN FLT 26/115 COTTER | ICS
LC | 126356390 | 031/006 | T2 EI TRINTY-MPLE CRK 31/06 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-12 | 2023-06-12 | 2024-06-14 | Late | 2024-06-11 | -3 | 2024-06-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172093 | T2 EI TRINTY-MPLE CRK 31/06 RPR GYWW | ICW
LC | 126347344 | 001/040 | T2 DI KILARC DSHUTS 01/040 RPR STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-11 | 2023-06-09 | 2024-03-18 | On-time | 2024-06-08 | 82 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088927 | T2 DI KILARC DSHUTS 01/040 RPR STRW | ICW
LC | 126358981 | 010/227 | T2 SALINAS-LAURELES 10/227 RMV VEG | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-13 | 2023-06-13 | 2024-06-26 | Late | 2024-06-12 | -14 | 2024-06-13 | 564 | TLV | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Trim
LC | 126359082 | 061/305 | T2 DI MALIN-ROUND MTN #2 61/305 RPR GYWT | TABLEMTN | ETL.6020.TOWR | 2023-06-13 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46236026 | T2 DI MALIN-ROUND MTN #2 61/305 RPR GYWT | ICQ
LC | 126359120 | :018/002 | T2 WV GL RCK-REDBD :18/2 INS ANCW | WILLITS | ETL.1480.POLE.NWOD | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 637 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Anchor-Wood | Install | 31606966 | CWSP-HIGHLANDS 1102 T-POLE REPLACEMENTS | 08W
LC | 126347349 | 001/040 | T2 DI KILARC DSHUTS 01/040 RMV BUTT | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-11 | 2023-06-09 | 2024-04-06 | On-time | 2024-06-08 | 63 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 46091793 | T2 DI KILARC DSHUTS 01/040 RMV BUTT | ICW
LC | 126359278 | 003/037 | T2 EI HAT CREEK #1-PIT #1 03/037 RPL PL | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX | TNT | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521445 | T2 EI HAT CREEK #1-PIT #1 03/037 RPL PL | 70Y
LC | 126359291 | 004/038 | T2 EI HAT CREEK #1-PIT #1 04/038 RPL PL | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521445 | T2 EI HAT CREEK #1-PIT #1 03/037 RPL PL | 70Y
LC | 126347487 | 008/124 | T2 DI DELTA-MTN GATE 8/124L RPR GYWW | TABLEMTN | ETL.6750.POLE.STPS | 2023-06-11 | 2023-06-09 | 2024-02-02 | On-time | 2024-06-08 | 127 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091799 | T2 DI DELTA-MTN GATE 8/124L RPR GYWW | ICW
LC | 126347488 | 008/124B | T2 DI DELTA-MTN GATE 8/124B RPR GYWW | TABLEMTN | ETL.6750.POLE.NWOD | 2023-06-11 | 2023-06-09 | 2024-02-02 | On-time | 2024-06-08 | 127 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096845 | T2 DI DELTA-MTN GATE 8/124B RPR GYWW | ICW
LC | 126359669 | 001/040 | T2 EI COTTONWOOD-BENTON #1 1/40 RPL POLE | TABLEMTN | ETL.6640.POLE.WOOD | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35521896 | T2 EI COTTONWOOD-BENTON #1 1/40 RPL POLE | 70Y
LC | 126347530 | 008/124 | T2 DI DELTA-MTN GATE 8/124R RPR GYWW | TABLEMTN | ETL.6750.POLE.STPS | 2023-06-11 | 2023-06-09 | 2024-02-02 | On-time | 2024-06-08 | 127 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091800 | T2 DI DELTA-MTN GATE 8/124R RPR GYWW | ICW
LC | 126360093 | 001/042 | T2 EI CTTNWD-BNTN #1 1/42 RPR POLE | TABLEMTN | ETL.6640.POLE.WOOD | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091824 | T2 EI CTTNWD-BNTN #1 1/42 RPR POLE | ICW
LC | 126360236 | 001/043 | T2 EI CTTNWD-BNTN #1 1/43 RPL HRDW | TABLEMTN | ETL.6640.INSL.NCER | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46091825 | T2 EI CTTNWD-BNTN #1 1/43 RPL HRDW | ICW
LC | 126347806 | 009/188 | T2 DI KILARC DESCHUTES 09/188 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-11 | 2023-06-09 | 2024-04-06 | On-time | 2024-06-08 | 63 | 2024-06-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515677 | T2 DI KILARC DESCHUTES 09/188 RPL POLE | 70Y
LC | 126347909 | 002/047 | T2 DI KILARC DSHUTS 02/047 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-11 | 2023-06-09 | 2024-03-18 | On-time | 2024-06-08 | 82 | 2024-06-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515349 | T2 DI KILARC DSHUTS 02/047 RPL STRW | 70Y
LC | 126361244 | 039/187 | T2 EI CORTINA-MNDCINO #1 39/187 RPL INSS | WILLITS | ETL.1330.INSL.CERA | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31676905 | EI CORTINA-MENDOCN #1 RPL INSS IN 5 TWRS | 93K
LC | 126348036 | 016/328 | T2 DI CARIBOU-WESTWOOD 16/328 RPR POLE | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-11 | 2023-06-09 | 2024-03-13 | On-time | 2024-06-08 | 87 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091802 | T2 DI CARIBOU-WESTWOOD 16/328 RPR POLE | ICW
LC | 126361829 | 111/001 | T2 EI HUMBOLDT-BRDGVLLE 111/1R RPL POLE | EUREKA | ETL.1810.POLE.WDPS | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505118 | T2 EI HUMBOLDT-BRIDGEVILLE 111/1 RPL PL | 70Y
LC | 126361975 | 111/001 | T2 EI HUMBOLDT-BRDGVLLE 111/1L RPL POLE | EUREKA | ETL.1810.POLE.WDPS | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505118 | T2 EI HUMBOLDT-BRIDGEVILLE 111/1 RPL PL | 70Y
LC | 126349266 | 077/314 | T2 RND MTN-TBL MTN#1 77/314 RPR COTTER | TABLEMTN | ETL.6060.INSL.CERA | 2023-06-12 | 2023-06-09 | 2024-04-12 | On-time | 2024-06-08 | 57 | 2024-06-09 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46083505 | T2 RND MTN-TBL MTN#1 77/314 RPR COTTER | ICS
LC | 126362444 | 018/095 | T2 EI RND MTN-TBL MTN #2 18/95 UNBURY | TABLEMTN | ETL.6070.TOWR | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46132842 | T2 EI RND MTN-TBL MTN #2 18/95 UNBURY | ICQ
LC | 126362543 | 016/005 | T2 EI MAPLE CREEK-HOOPA 16/5 RPR GYWW | EUREKA | ETL.7490.POLE.WOOD | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46203529 | T2 EI MAPLE CREEK-HOOPA 16/5 RPR GYWW | ICW
LC | 126362547 | 111/000 | T2 EI HUMBOLDT-BRIDGEVILLE 111/0 RPR CND | EUREKA | ETL.1810.INSL.NCER | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46096228 | T2 EI HUMBOLDT-BRIDGEVILLE 111/0 RPR CND | ICW
LC | 126365171 | 002/055 | T2 DI KILARC-DESCHUTES 2/55 RPR GYWW | TABLEMTN | ETL.7300.POLE.NWOD | 2023-06-13 | 2023-06-09 | 2024-02-02 | On-time | 2024-06-08 | 127 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091794 | T2 DI KILARC-DESCHUTES 2/55 RPR GYWW | ICW
LC | 126365278 | 001/030 | T2 DI KILARC-DESCHUTES 1/30 GO95 | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-13 | 2023-06-09 | 2024-03-19 | On-time | 2024-06-08 | 81 | 2024-06-09 | 401T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35526169 | T2 DI KILARC-DESCHUTES 1/30 GO95 | 93G
LC | 126363350 | 110/008 | T2 EI HUMBOLDT-BRIDGEVLE 110/8 RPR COND | EUREKA | ETL.1810.INSL.NCER | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46096227 | T2 EI HUMBOLDT-BRIDGEVLE 110/8 RPR COND | ICS
LC | 126363511 | :006/011 | T2 EI FULTON-PUEBLO :006/011 RPL POLE | LAKEVLLE | ETL.1600.POLE.WOOD | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35530627 | T2 EI FULTON-PUEBLO :006/011 RPL PL | 70Y
LC | 126363985 | 009/014 | T2 MELONES-RACETRACK 9/14 RPL STRW | VICTOR | ETL.2400.POLE.WOOD | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35527462 | T2 MELONES-RACETRACK 09/14 RPL POLE | 70Y
LC | 126365287 | 002/045 | T2 DI KILARC DSHUTS 2/45 RPL ANCW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-13 | 2023-06-09 | 2024-03-18 | On-time | 2024-06-08 | 82 | 2024-06-09 | 637 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31655479 | T2 DI KILARC DSHUTS 02/045 RPL ANCW | 93E
LC | 126364610 | ;002/013 | T2 CARIBOU #2 ;002/013 RPR STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091820 | T2 CARIBOU #2 ;002/013 RPR STRW | ICW
LC | 126364695 | 059/003A | T2 EI HUMBOLDT-TRINITY 59/3A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2023-12-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46255216 | T2 EI HUMBOLDT-TRINITY 59/3A RPR GYWW | ICW
LC | 126364696 | 059/003B | T2 EI HUMBOLDT-TRINITY 59/3B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2023-12-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46255217 | T2 EI HUMBOLDT-TRINITY 59/3B RPR GYWW | ICW
LC | 126364697 | 059/003C | T2 EI HUMBOLDT-TRINITY 59/3C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2023-09-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46255218 | T2 EI HUMBOLDT-TRINITY 59/3C RPR GYWW | ICW
LC | 126364717 | 033/648 | T2 EI HAT CREEK #1-WSTWD 33/648 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-13 | 2023-06-13 | 2024-06-26 | Late | 2024-06-12 | -14 | 2024-06-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514210 | T2 DI HT CRK #1-WSTWD 33/644 RPL POLE | 70Y
LC | 126364766 | 005/033 | T2 MATNZ-SBRNT 5/33 RPL HNGR | CONCORD | ETL.2270.INSL.NCER | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hanger Plate - Tower | Replace | 46098827 | T2 OLEUM-MARTINEZ 004/032 RPL HNGR | ICQ
LC | 126365010 | 066/001 | T2 WV HUMBOLDT-TRINITY 66/1 INS GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-13 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Guy Wire-Wood | Install | 46096534 | T2 WV HUMBOLDT-TRINITY 66/1 INS GYWW | ICW
LC | 126365120 | 019/391 | T2 DI CARIBOU-WESTWOOD 19/391 RPR STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-13 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46079349 | T2 DI CARIBOU-WESTWOOD 19/391 RPR STRW | ICW
LC | 126365288 | 002/045 | T2 DI KILARC DSHUTS 2/45 COTTER | TABLEMTN | ETL.7300.INSL.NCER | 2023-06-13 | 2023-06-09 | 2024-02-20 | On-time | 2024-06-08 | 109 | 2023-12-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45855517 | T2 DI KILARC DSHUTS 02/045 COTTER | ICW
LC | 126365177 | 014/000A | T2 DI BRIDGEVL-GARBERVL 14/0A RPL HRDW | EUREKA | ETL.6220.POLE.WOOD | 2023-06-13 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46087892 | T2 DI BRIDGEVL-GARBERVL 14/0A RPL HRDW | ICW
LC | 126365296 | 001/034 | T2 DI KILARC-DSCHTS 001/034 RPR STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-13 | 2023-06-09 | 2024-02-14 | On-time | 2024-06-08 | 115 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091791 | T2 DI KILARC-DSCHTS 001/034 RPR STRW | ICW
LC | 126365345 | 012/272 | T2 DI KILARC-DESCHUTES 12/272 RPR STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-13 | 2023-06-09 | 2024-03-09 | On-time | 2024-06-08 | 91 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088693 | T2 DI KILARC-DESCHUTES 12/272 RPR STRW | ICW
LC | 126365349 | 013/289 | T2 DI KILARC-DESCH 13/289 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-13 | 2023-06-09 | 2024-04-04 | On-time | 2024-06-08 | 65 | 2024-06-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515740 | T2 DI KILARC-DESCHUTES 12/257 RPL POLE | 70Y
LC | 126365421 | 001/035 | T2 DI KILARC-DESCHUTES 1/35 RPR INSW | TABLEMTN | ETL.7300.INSL.CERA | 2023-06-13 | 2023-06-09 | 2024-03-20 | On-time | 2024-06-08 | 80 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46088929 | T2 DI KILARC-DESCHUTES 1/35 RPR INSW | ICW
LC | 126365423 | 008/183 | T2 DI KILARC-DESCHUTES 8/183 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-13 | 2023-06-09 | 2024-04-06 | On-time | 2024-06-08 | 63 | 2024-06-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515676 | T2 DI KILARC-DESCHUTES 8/183 RPL POLE | 70Y
LC | 126365308 | 046/002 | T2 DI TRNTY-MPL CRK 46/2 RPL IBWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-13 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46172240 | T2 DI TRNTY-MPL CRK 46/2 RPL IBWW | ICW
LC | 126365424 | 001/035 | T2 DI KILARC-DESCHUTES 1/35 RPR CNDW | TABLEMTN | ETL.7300.INSL.CERA | 2023-06-13 | 2023-06-09 | 2024-03-21 | On-time | 2024-06-08 | 79 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46088930 | T2 DI KILARC-DESCHUTES 1/35 RPR CNDW | ICW
LC | 126365441 | 000/006 | T2 DI COLGTE-PALRMO 0/6 RPR STRW | SACTO | ETL.6500.POLE.WOOD | 2023-06-13 | 2023-06-09 | 2024-04-16 | On-time | 2024-06-08 | 53 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46125121 | T2 DI COLGTE-PALRMO 0/6 RPR STRW | ICW
LC | 126365534 | 029/146 | T2 DI EXCHEQUER-INDN FLT 29/146 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-06-13 | 2023-06-09 | 2023-12-13 | On-time | 2024-06-08 | 178 | 2023-09-09 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45854973 | T2 DI EXCHEQUER-INDN FLT 29/146 RPR JMPS | ICS
LC | 126365774 | 001/033 | T2 DI KILARC-DESCHUTES 1/33 RPR STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-13 | 2023-06-09 | 2024-02-14 | On-time | 2024-06-08 | 115 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088931 | T2 DI KILARC-DESCHUTES 1/33 RPR STRW | ICW
LC | 126374997 | 009/197 | T2 DI KILARC-DSCHTES 009/197 RPL TIEW | TABLEMTN | ETL.7300.INSL.NCER | 2023-06-14 | 2023-06-09 | 2024-04-04 | On-time | 2024-06-08 | 65 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46088698 | T2 DI KILARC-DSCHTES 009/197 RPL TIEW | ICW
LC | 126375011 | 009/197 | T2 DI KILARC-DSCHTES 9/197 RPR CRSW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-09 | 2024-04-04 | On-time | 2024-06-08 | 65 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46088696 | T2 DI KILARC-DSCHTES 9/197 RPR CRSW | ICW
LC | 126375048 | 021/452 | T2 DI KILARC-DESCHUTES 021/452 RPR POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-09 | 2024-03-14 | On-time | 2024-06-08 | 86 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088234 | T2 DI KILARC-DESCHUTES 021/452 RPR POLE | ICW
LC | 126365427 | 012/244 | T2 DI CARIBOU-WESTWOOD 12/244 RPR INSW | TABLEMTN | ETL.6300.INSL | 2023-06-13 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46091801 | T2 DI CARIBOU-WESTWOOD 12/244 RPR INSW | ICW
LC | 126375163 | 016/332 | T2 DI KILARC-DESCHUTES 16/332 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-09 | 2024-04-07 | On-time | 2024-06-08 | 62 | 2024-06-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515741 | T2 DI KILARC-DESCHUTES 16/332 RPL POLE | 70Y
LC | 126375216 | 003/081 | T2 DI KILARC-DSCHTES 003/081 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-09 | 2024-03-18 | On-time | 2024-06-08 | 82 | 2024-06-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35529595 | T2 DI KILARC-DSCHTES 003/081 RPL POLE | 70Y
LC | 126375221 | 001/038 | T2 DI KILARC-DESCHUTES 1/38 RPL HRDD | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-09 | 2024-03-19 | On-time | 2024-06-08 | 81 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46171566 | T2 DI KILARC-DESCHUTES 1/38 RPL HRDD | ICW
LC | 126375255 | 067/337 | T2 DI MALIN-RND MTN 067/337 RPR SHLDW | TABLEMTN | ETL.6020.TOWR | 2023-06-14 | 2023-06-09 | 2024-05-10 | On-time | 2024-06-08 | 29 | 2024-06-09 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46083462 | T2 DI MALIN-RND MTN 067/337 RPR SHLDW | ICS
LC | 126375503 | 005/114-GUY | T2 DI KLRC-DSCHTS 5/114-GUY RPR GYWW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-09 | 2024-02-14 | On-time | 2024-06-08 | 115 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088723 | T2 DI KLRC-DSCHTS 5/114-GUY RPR GYWW | ICW
LC | 126375687 | 008/170 | T2 DI KILARC-DESCHUTES 08/170 RPR INSW | TABLEMTN | ETL.7300.INSL.CERA | 2023-06-14 | 2023-06-09 | 2024-04-02 | On-time | 2024-06-08 | 67 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46088699 | T2 DI KILARC-DESCHUTES 08/170 RPR INSW | ICW
LC | 126375708 | 026/114 | T2 DI EXCHQR-INDN FLT 26/114 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-06-14 | 2023-06-09 | 2023-12-12 | On-time | 2024-06-08 | 179 | 2023-09-09 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45954652 | T2 DI EXCHQR-INDN FLT 26/114 RPR JMPS | ICS
LC | 126375718 | 011/214 | T2 DI CARIBOU-WESTWOOD 11/214 RMV VEGN | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-14 | 2023-06-09 | 2024-04-16 | On-time | 2024-06-08 | 53 | 2024-06-09 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126365547 | 013/290 | T2 DI KILARC DSHUTS 13/290 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-13 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35554815 | T2 DI KILARC DSHUTS 13/290 RPL POLE | 70Y
LC | 126365551 | 003/069 | T2 DI CARIBOU-WSTWD 003/069R RPR GYWW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-06-13 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079341 | T2 DI CARIBOU-WSTWD 003/069 RPR GYWR | ICW
LC | 126365553 | 003/069 | T2 DI CARIBOU-WSTWD 003/069L RPR GYWW | TABLEMTN | ETL.6300.POLE.WDPS | 2023-06-13 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079342 | T2 DI CARIBOU-WSTWD 003/069 RPR GYWR | ICW
LC | 126375875 | 029/151 | T2 DI EXCHQR-INDN FLT 29/151 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-06-14 | 2023-06-09 | 2023-12-13 | On-time | 2024-06-08 | 178 | 2023-09-09 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45954653 | T2 DI EXCHQR-INDN FLT 029/151 RPR JMPSTL | ICS
LC | 126365611 | 004/078 | T2 DI CARIB-WSTWD 4/78 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-13 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519112 | T2 DI CARIB-WSTWD 4/78 RPL STRW | 70Y
LC | 126382930 | 018/388 | T2 DI KILARC DSHUTS 18/388 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-15 | 2023-06-09 | 2024-03-15 | On-time | 2024-06-08 | 85 | 2024-06-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515345 | T2 DI KILARC DSHUTS 18/388 RPL STRW | 70Y
LC | 126365721 | 007/133 | T2 DI CARIBOU-WESTWOOD-PL 7/133 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-13 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35556416 | T2 DI CARIBOU-WESTWOOD-PL 7/133 RPL STRW | 70Y
LC | 126384058 | 035/201 | T2 DI EXCHQR-INDN FLT 35/201 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-06-15 | 2023-06-09 | 2023-12-12 | On-time | 2024-06-08 | 179 | 2023-09-09 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45954654 | T2 DI EXCHQR-INDN FLT 35/201 RPR JUMPER | ICS
LC | 126384059 | 035/201 | T2 DI EXCHQR-INDN FLT 35/201 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-06-15 | 2023-06-09 | 2023-12-11 | On-time | 2024-06-08 | 180 | 2024-06-09 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45977793 | T2 DI EXCHQR-INDN FLT 35/201 UNBURY | ICQ
LC | 126365800 | 007/139 | T2 DI CARIBOU-WEST-WD PL 7/139 RPR GYWW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-13 | 2023-06-08 |  | Late | 2024-06-07 |  | 2024-06-08 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46262783 | T2 DI CARIBOU-WEST-WD PL 7/139 RPR GYWW | ICW
LC | 126366105 | 072/368 | T2 EI MALIN-ROUND MTN #2 72/368 RPR GYWT | TABLEMTN | ETL.6020.TOWR | 2023-06-14 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46089576 | T2 EI MALIN-ROUND MTN #2 72/368 RPR GYWT | ICQ
LC | 126366469 | 023/175 | T2 DRUM-RIO OSO #1 23/175 RMV ENCRCH | SACTO | ETL.1420.TOWR | 2023-06-14 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 931 | TLS |  | E - Schd Compl Yr 0 | Open | TR2 | Encroachment | Right of Way | Remove
LC | 126367350 | 079/002 | T2 EI HUMBOLDT-TRINITY 79/2 COTR KEY | EUREKA | ETL.1820.INSL.CERA | 2023-06-14 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46096591 | T2 EI HUMBOLDT-TRINITY 79/2 COTR KEY | ICW
LC | 126384348 | 001/032 | T2 DI KILARC-DESCH 1/32 RPR STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-15 | 2023-06-09 | 2024-04-03 | On-time | 2024-06-08 | 66 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091790 | T2 DI KILARC-DESCH 1/32 RPR STRW | ICW
LC | 126368876 | :013/020 | T2 EI EAGLE ROCK-CORTINA :013/020 RPL PL | WILLITS | ETL.1470.POLE.WOOD | 2023-06-14 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35487305 | T2 EI EAGLE ROCK-CORTINA :013/020 RPL PL | 70Y
LC | 126369805 | 044/864 | T2 EI HAT CRK #1-WESTWD 044/864 GO95 | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-14 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35529175 | T2 EI HAT CRK #1-WESTWD 044/864 GO95 | 93G
LC | 126371448 | 031/150 | T2 EI CORTINA-MENDOCN #1 31/150 RPL INSS | WILLITS | ETL.1330.INSL.CERA | 2023-06-14 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31676905 | EI CORTINA-MENDOCN #1 RPL INSS IN 5 TWRS | 93K
LC | 126384471 | 002/044 | T2 DI KILARC-DESCHTS 2/44 RPR STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-15 | 2023-06-09 | 2024-04-03 | On-time | 2024-06-08 | 66 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088926 | T2 DI KILARC-DESCHTS 2/44 RPR STRW | ICW
LC | 126387284 | 000/020 | T2 DI KLRC-DSCHTS 0/20 RPR CRSW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-16 | 2023-06-09 | 2024-03-19 | On-time | 2024-06-08 | 81 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46088932 | T2 DI KLRC-DSCHTS 0/20 RPR CRSW | ICW
LC | 126395220 | 004/099 | T2 DI KILARC-DESHUTES 04/099 RPL SPLW | TABLEMTN | ETL.7300.INSL.NCER | 2023-06-17 | 2023-06-09 | 2024-04-02 | On-time | 2024-06-08 | 67 | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Replace | 46088727 | T2 DI KILARC-DESHUTES 04/099 RPL SPLW | ICW
LC | 126372937 | 034/667 | T2 EI HAT CREEK #1-WSTWD 34/667 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-14 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514264 | T2 EI HAT CREEK #1-WSTWD 34/667 RPL POLE | 70Y
LC | 126453069 | 067/336 | T2 DI MALIN RND MTN#2 67/336 COMPLETE | TABLEMTN | ETL.6020.TOWR | 2023-06-26 | 2023-06-09 | 2023-08-28 | On-time | 2024-06-08 | 285 | 2023-09-09 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45881986 | T2 DI MALIN RND MTN#2 67/336 RPR SHLS | ICS
LC | 126374918 | 036/691 | T2 EI HAT CRK #1-WESTWD 36/691 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-14 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518531 | T2 EI HAT CREEK #1-WESTWOD 36/691 RPL PL | 70Y
LC | 126374969 | 035/689 | T2 EI HAT CREEK #1-WSTWD 35/689 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-14 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514270 | T2 DI HAT CRK #1-WSTWD 35/679 RPL POLE | 70Y
LC | 126341523 | 49 | T2 EI DRM SPLDNG 8/214 #49 RPR SWTC | SACTO | ETL.6770.SWIT | 2023-06-10 | 2023-06-10 | 2023-10-06 | On-time | 2024-06-09 | 247 | 2023-09-10 | 623 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 45870708 | T2 EI DRM SPLDNG 8/214 #49 RPR SWTC | ICE
LC | 126342139 | 005/065 | T2 BURNS-LONE STAR #1 05/65 GO95 | MOSSLNDG | ETL.6230.POLE.WOOD | 2023-06-10 | 2023-06-10 | 2024-06-01 | On-time | 2024-06-09 | 8 | 2024-06-10 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31655006 | T2 BURNS-LONE STAR #1 05/65 GO95 | 93G
LC | 126375041 | 017/001 | T2 DI MAPLE CREEK-HOOPA 017/001 COTTER | EUREKA | ETL.7490.INSL.NCER | 2023-06-14 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46190237 | T2 DI MAPLE CREEK-HOOPA 017/001 COTTER | ICW
LC | 126342828 | 114/001 | T2 EI HMBLT-BRDGVL 114/1L RPR STRW | EUREKA | ETL.1810.POLE.WDPS | 2023-06-10 | 2023-06-10 | 2024-04-02 | On-time | 2024-06-09 | 68 | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46170400 | T2 EI HMBLT-BRDGVL 114/1L RPR STRW | ICW
LC | 126342990 | 043/342 | T2 EI BRDGVLL-CTTNWD 43/342 RPR FOND | TABLEMTN | ETL.1110.TOWR | 2023-06-10 | 2023-06-10 | 2024-06-07 | On-time | 2024-06-09 | 2 | 2024-06-10 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46125089 | T2 EI BRDGVLL-CTTNWD 43/342 RPR FOND | ICQ
LC | 126343200 | 114/000 | T2 EI HMBLT-BRDGVL 114/0R RPR STRW | EUREKA | ETL.1810.POLE.STPS | 2023-06-10 | 2023-06-10 | 2024-04-02 | On-time | 2024-06-09 | 68 | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46170219 | T2 EI HMBLT-BRDGVL 114/0L RPR STRW | ICW
LC | 126343281 | 114/000 | T2 EI HMBLT-BRDGVL 114/0L RPR STRW | EUREKA | ETL.1810.POLE.STPS | 2023-06-10 | 2023-06-10 | 2024-04-02 | On-time | 2024-06-09 | 68 | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46170219 | T2 EI HMBLT-BRDGVL 114/0L RPR STRW | ICW
LC | 126375356 | 021/446 | T2 DI KILARC-DESCHUTES 21/446 RPR STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088232 | T2 DI KILARC-DESCHUTES 21/446 RPR STRW | ICW
LC | 126375409 | 066/335 | T2 DI MLN-RND MT #2 66/335 RPL ANCT | TABLEMTN | ETL.6020.TOWR | 2023-06-14 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 93Z | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Tower | Replace | 31684765 | T2 DI MLN-RND MT #2 66/335 RPL ANCS | 93Z
LC | 126343282 | 114/000 | T2 EI HMBLT-BRDGVL 114/0L RPR GYWW | EUREKA | ETL.1810.POLE.STPS | 2023-06-10 | 2023-06-10 | 2024-01-11 | On-time | 2024-06-09 | 150 | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45881483 | T2 EI HMBLT-BRDGVL 114/0L RPR GYWW | ICW
LC | 126343694 | :010/062 | T2 EI EAGLE RCK-REDBUD :10/062 RMV BRSH | WILLITS | ETL.1480.TOWR | 2023-06-10 | 2023-06-10 | 2023-11-22 | On-time | 2024-06-09 | 200 | 2024-06-10 | 932 | TLR | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Brush Fuel | Road | Remove
LC | 126343738 | 113/008 | T2 EI HMBLT-BRDGVL 113/8 COTTER | EUREKA | ETL.1810.INSL.NCER | 2023-06-10 | 2023-06-10 | 2024-04-04 | On-time | 2024-06-09 | 66 | 2024-06-10 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46102372 | T2 EI HMBLT-BRDGVL 113/8 COTTER | ICS
LC | 126343843 | 087/001 | T2 EI HMBLT-TRNTY 87/1R RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-06-10 | 2023-06-10 | 2023-08-16 | On-time | 2024-06-09 | 298 | 2023-09-10 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45881480 | T2 EI HMBLT-TRNTY 87/1R RPR GYWW | ICS
LC | 126343844 | 087/001 | T2 EI HMBLT-TRNTY 87/1L RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-06-10 | 2023-06-10 | 2023-08-16 | On-time | 2024-06-09 | 298 | 2023-09-10 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45881480 | T2 EI HMBLT-TRNTY 87/1R RPR GYWW | ICS
LC | 126343918 | 087/002B | T2 EI HUMBOLDT-TRINITY 87/2B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-10 | 2023-06-10 | 2024-06-03 | On-time | 2024-06-09 | 6 | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096595 | T2 EI HUMBOLDT-TRINITY 87/2B RPR GYWW | ICW
LC | 126343966 | 087/002A | T2 EI HUMBOLDT-TRINITY 87/2A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-10 | 2023-06-10 | 2024-06-03 | On-time | 2024-06-09 | 6 | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46252213 | T2 EI HUMBOLDT-TRINITY 87/2A RPR GYWW | ICW
LC | 126343968 | 087/000C | T2 EI HUMBOLDT-TRINITY 87/0C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-10 | 2023-06-10 | 2024-06-03 | On-time | 2024-06-09 | 6 | 2024-06-10 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46096594 | T2 EI HUMBOLDT-TRINITY 87/0A RPR GYWW | ICW
LC | 126375726 | 018/369 | T2 DI CARIBOU-WSWD 018/369 RPL PL | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-14 | 2023-06-09 |  | Late | 2024-06-08 |  | 2024-06-09 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519127 | T2 DI CARIBOU-WSWD 018/369 RPL PL | 70Y
LC | 126343971 | 087/000B | T2 EI HUMBOLDT-TRINITY 87/0B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-10 | 2023-06-10 | 2024-06-03 | On-time | 2024-06-09 | 6 | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096594 | T2 EI HUMBOLDT-TRINITY 87/0A RPR GYWW | ICW
LC | 126343972 | 087/000A | T2 EI HUMBOLDT-TRINITY 87/0A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-10 | 2023-06-10 | 2024-06-03 | On-time | 2024-06-09 | 6 | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096594 | T2 EI HUMBOLDT-TRINITY 87/0A RPR GYWW | ICW
LC | 126345662 | 070/352 | T2 EI MALIN-ROUND MTN #2 70/352 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2023-06-10 | 2023-06-10 | 2023-12-21 | On-time | 2024-06-09 | 171 | 2024-06-10 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46056061 | T2 EI MALIN-ROUND MTN #2 70/352 RPR INSS | ICS
LC | 126349014 | 001/023 | T2 EI KILARC-DESCHUTES 01/023 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-12 | 2023-06-10 | 2024-03-19 | On-time | 2024-06-09 | 82 | 2024-06-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515348 | T2 EI KILARC-DESCHUTES 01/023 RPL STRW | 70Y
LC | 126349023 | 004/094 | T2 EI KILARC-DESCHUTES 004/094 RPR POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-12 | 2023-06-10 | 2024-04-02 | On-time | 2024-06-09 | 68 | 2024-06-10 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088688 | T2 EI KILARC-DESCHUTES 004/094 RPR POLE | ICW
LC | 126349024 | 003/070 | T2 EI KILARC-DESCHUTES 3/070 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-12 | 2023-06-10 | 2024-03-18 | On-time | 2024-06-09 | 83 | 2024-06-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515349 | T2 DI KILARC DSHUTS 02/047 RPL STRW | 70Y
LC | 126364435 | 015/312 | T2 DI KILARC DSHUTS 15/312 RPL HRDD | TABLEMTN | ETL.7300.POLE.NWOD | 2023-06-13 | 2023-06-10 | 2024-04-05 | On-time | 2024-06-09 | 65 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46088666 | T2 DI KILARC DSHUTS 15/312 RPL HRDD | ICW
LC | 126365542 | 020/414 | T2 DI KILARC-DESCHUTES 020/414 RPR POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-13 | 2023-06-10 | 2024-03-11 | On-time | 2024-06-09 | 90 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088233 | T2 DI KILARC-DESCHUTES 020/414 RPR POLE | ICW
LC | 126365677 | 003/073 | T2 DI KILARC-DSCHTS 003/073 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-13 | 2023-06-10 | 2024-03-18 | On-time | 2024-06-09 | 83 | 2024-06-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515349 | T2 DI KILARC DSHUTS 02/047 RPL STRW | 70Y
LC | 126375700 | 017/365 | T2 DI KILARC-DSCHTS 017/365 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-10 | 2024-04-06 | On-time | 2024-06-09 | 64 | 2024-06-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515743 | T2 DI KILARC-DSCHTS 017/364 RPL STRW | 70Y
LC | 126375709 | 008/182 | T2 DI KILARC-DESCHUTES 8/182 RPR STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-10 | 2024-02-13 | On-time | 2024-06-09 | 117 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088679 | T2 DI KILARC-DESCHUTES 8/182 RPR STRW | ICW
LC | 126375724 | 001/024 | T2 DI KILARC-DESCHUTES 1/24 RPR INSW | TABLEMTN | ETL.7300.INSL.CERA | 2023-06-14 | 2023-06-10 | 2024-02-15 | On-time | 2024-06-09 | 115 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46088924 | T2 DI KILARC-DESCHUTES 1/24 RPR INSW | ICW
LC | 126375740 | 001/024 | T2 DI KLRC-DSCHTS 1/24 RPR STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-10 | 2024-02-15 | On-time | 2024-06-09 | 115 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088925 | T2 DI KLRC-DSCHTS 1/24 RPR STRW | ICW
LC | 126375793 | 014/303 | T2 DI KILARC-DSCHTS 014/303 RPL DMPW | TABLEMTN | ETL.7300.INSL.NCER | 2023-06-14 | 2023-06-10 | 2024-04-04 | On-time | 2024-06-09 | 66 | 2024-06-10 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 46088743 | T2 DI KILARC-DSCHTS 014/303 RPL DMPW | ICS
LC | 126375794 | 017/364 | T2 DI KILARC-DSCHTS 017/364 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-10 | 2024-04-06 | On-time | 2024-06-09 | 64 | 2024-06-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515743 | T2 DI KILARC-DSCHTS 017/364 RPL STRW | 70Y
LC | 126376167 | 001/002 | T2 MNDCNO-WLLTS-FRT BRGG 1/2 RPL POLE | WILLITS | ETL.7550.POLE.WOOD | 2023-06-15 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35496268 | T2 MNDCNO-WLLTS-FRT BRGG 1/2 RPL POLE | 70Y
LC | 126377024 | 000/007 | T2 EI HT CRK#1-PT#1 0/7 RPL INSS | TABLEMTN | ETL.7020.INSL.CERA | 2023-06-15 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513068 | T2 EI HAT CREEK#1-PIT#1 RPL INSS 3 TWRS | 93K
LC | 126375797 | 017/355 | T2 DI KILARC-DESCHUTES 17/355 RPR INSW | TABLEMTN | ETL.7300.INSL.NCER | 2023-06-14 | 2023-06-10 | 2024-04-05 | On-time | 2024-06-09 | 65 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46088660 | T2 DI KILARC-DESCHUTES 17/355 RPR INSW | ICW
LC | 126377033 | 004/022 | T2 EI MORRO BAY-TEMPLETON 4/022 RPL INSS | PISMOBCH | ETL.5933.INSL | 2023-06-15 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35521160 | T2 EI MORRO BAY-TEMPLETON 4/022 RPL INSS | 93K
LC | 126377070 | 000/002 | T2 EI HAT CREEK#1-PIT#1 000/002 RPL INSS | TABLEMTN | ETL.7020.INSL.CERA | 2023-06-15 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513068 | T2 EI HAT CREEK#1-PIT#1 RPL INSS 3 TWRS | 93K
LC | 126375851 | 008/173 | T2 DI KILARC-DESCHUTES 08/173 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-10 | 2024-04-07 | On-time | 2024-06-09 | 63 | 2024-06-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515675 | T2 EI KILARC-DESCHUTES 08/171 RPL POLE | 70Y
LC | 126375862 | 015/330 | T2 DI KILARC-DESCHUTES 15/330 RPR INSW | TABLEMTN | ETL.7300.INSL.NCER | 2023-06-14 | 2023-06-10 | 2024-04-08 | On-time | 2024-06-09 | 62 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46088661 | T2 DI KILARC-DESCHUTES 15/330 RPR INSW | ICW
LC | 126377106 | 082/577 | T2 DI BRDGVIL-CTTNWOOD 82/577L RPL STRW | EUREKA | ETL.1110.POLE.WDPS | 2023-06-15 | 2023-05-23 |  | Late | 2024-05-22 |  | 2024-05-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35505109 | T2 DI BRDGVIL-CTTNWOOD 82/577R RPL STRW | 70Y
LC | 126375892 | 015/318 | T2 DI KILARC-DSCHTES 015/318 RPR ANCW | TABLEMTN | ETL.7300.POLE.NWOD | 2023-06-14 | 2023-06-10 | 2024-02-12 | On-time | 2024-06-09 | 118 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46088664 | T2 DI KILARC-DSCHTES 015/318 RPR ANCW | ICW
LC | 126375893 | 004/095 | T2 DI KLRC-DSCHTS 4/95 RPR POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-10 | 2024-04-02 | On-time | 2024-06-09 | 68 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088684 | T2 DI KLRC-DSCHTS 4/95 RPR POLE | ICW
LC | 126375902 | 011/235 | T2 DI KILARC-DESCHUTES 011/235 RPR GYWW | TABLEMTN | ETL.7300.POLE.NWOD | 2023-06-14 | 2023-06-10 | 2024-02-13 | On-time | 2024-06-09 | 117 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088671 | T2 DI KILARC-DESCHUTES 011/235 RPR GYWW | ICW
LC | 126375927 | 008/174 | T2 DI KILARC-DESCHUTES 8/174 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-10 | 2024-04-07 | On-time | 2024-06-09 | 63 | 2024-06-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515675 | T2 EI KILARC-DESCHUTES 08/171 RPL POLE | 70Y
LC | 126375938 | 008/172 | T2 DI KILARC-DESCHUTES 08/172 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-10 | 2024-04-08 | On-time | 2024-06-09 | 62 | 2024-06-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515675 | T2 EI KILARC-DESCHUTES 08/171 RPL POLE | 70Y
LC | 126375944 | 016/351 | T2 DI KILARC-DESCHUTES 16/351 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-10 | 2024-04-06 | On-time | 2024-06-09 | 64 | 2024-06-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515742 | T2 DI KILARC-DESCHUTES 16/351 RPL POLE | 70Y
LC | 126379630 | 008/005 | T2 EI MAPLE CREEK-HOOPA 8/5 RPL ANCW | EUREKA | ETL.7490.POLE.NWOD | 2023-06-15 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35506536 | T2 EI MAPLE CREEK-HOOPA 8/5 RPL ANCW | 93E
LC | 126379988 | 005/038 | T2 WV SOBRANTE-MORAGA 5/38 RESAG | CONCORD | ETL.3742.INSL.NCER | 2023-06-15 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 45999072 | T2 WV SOBRANTE-MORAGA 5/38 RESAG | ICS
LC | 126375992 | 019/401 | T2 DI KILARC-DESCHUTES 19/401 RPR STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-10 | 2024-02-12 | On-time | 2024-06-09 | 118 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091813 | T2 DI KILARC-DESCHUTES 19/401 RPR STRW | ICW
LC | 126383152 | 013/291 | T2 DI KILARC-DESCHUTES 13/291 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-15 | 2023-06-10 | 2024-04-04 | On-time | 2024-06-09 | 66 | 2024-06-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518956 | T2 DI KILARC-DESCHUTES 13/291 RPL STRW | 70Y
LC | 126382444 | 006/063 | T2 EI IGNACIO-BOLINAS #1 06/63L RPL POLE | LAKEVLLE | ETL.7140.POLE.WDPS | 2023-06-15 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526313 | T2 EI IGNACIO-BOLINAS #1 06/63L RPL POLE | 70Y
LC | 126384136 | 016/343 | T2 DI KILARC-DESCHUTES 16/343 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-15 | 2023-06-10 | 2024-04-07 | On-time | 2024-06-09 | 63 | 2024-06-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515741 | T2 DI KILARC-DESCHUTES 16/332 RPL POLE | 70Y
LC | 126382760 | 006/063 | T2 EI IGNACIO-BOLINAS #1 06/63C RPL POLE | LAKEVLLE | ETL.7140.POLE.WDPS | 2023-06-15 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526313 | T2 EI IGNACIO-BOLINAS #1 06/63L RPL POLE | 70Y
LC | 126384158 | 009/195 | T2 DI KILARC-DESCHUTES 009/195 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-15 | 2023-06-10 | 2024-04-05 | On-time | 2024-06-09 | 65 | 2024-06-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515678 | T2 EI KILARC-DESCHUTES 9/193 RPL STRW | 70Y
LC | 126383032 | 006/063 | T2 EI IGNACIO-BOLINAS #1 06/63R RPL POLE | LAKEVLLE | ETL.7140.POLE.WDPS | 2023-06-15 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526313 | T2 EI IGNACIO-BOLINAS #1 06/63L RPL POLE | 70Y
LC | 126384242 | 014/308 | T2 DI KLRC-DSCHTS 14/308 RPR STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-15 | 2023-06-10 | 2024-04-07 | On-time | 2024-06-09 | 63 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088668 | T2 DI KLRC-DSCHTS 14/308 RPR STRW | ICW
LC | 126384500 | 006/141 | T2 DI KILARC-DESCHUTES 06/141 RPL SPLW | TABLEMTN | ETL.7300.INSL.NCER | 2023-06-15 | 2023-06-10 | 2024-04-02 | On-time | 2024-06-09 | 68 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Spacer-Wood | Replace | 46088680 | T2 DI KILARC-DESCHUTES 06/141 RPL SPLW | ICW
LC | 126384503 | 006/141 | T2 DI KILARC-DESCHUTES 6/141 GO95 RPL | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-15 | 2023-06-10 | 2024-04-02 | On-time | 2024-06-09 | 68 | 2024-06-10 | 401T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35515127 | T2 DI KILARC-DESCHUTES 6/141 GO95 RPL | 93G
LC | 126384532 | 012/257 | T2 DI KILARC-DESCHUTES 12/257 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-15 | 2023-06-10 | 2024-04-04 | On-time | 2024-06-09 | 66 | 2024-06-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515740 | T2 DI KILARC-DESCHUTES 12/257 RPL POLE | 70Y
LC | 126384622 | 009/186 | T2 DI KILARC-DESCHUTES 09/186 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-15 | 2023-06-10 | 2024-04-06 | On-time | 2024-06-09 | 64 | 2024-06-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515676 | T2 DI KILARC-DESCHUTES 8/183 RPL POLE | 70Y
LC | 126386473 | 011/243 | T2 DI KILARC-DESCHUTES 11/243 RPR GYWW | TABLEMTN | ETL.7300.POLE.NWOD | 2023-06-16 | 2023-06-10 | 2024-02-13 | On-time | 2024-06-09 | 117 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088670 | T2 DI KILARC-DESCHUTES 11/243 RPR GYWW | ICW
LC | 126386523 | 006/140 | T2 DI KILARC-DESCHUTES 06/140 RPL SPLW | TABLEMTN | ETL.7300.INSL.CERA | 2023-06-16 | 2023-06-10 | 2024-04-03 | On-time | 2024-06-09 | 67 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Replace | 46088682 | T2 DI KILARC-DESCHUTES 06/140 RPL SPLW | ICW
LC | 126394171 | 000/021 | T2 DI KILARC-DESHUTES 00/21 BACKFILL | TABLEMTN | ETL.7300.POLE.NWOD | 2023-06-16 | 2023-06-10 | 2024-02-15 | On-time | 2024-06-09 | 115 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091812 | T2 DI KILARC-DESHUTES 00/21 BACKFILL | ICW
LC | 126394963 | 016/347 | T2 DI KILARC DESCHUTES 16/347 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-17 | 2023-06-10 | 2024-04-07 | On-time | 2024-06-09 | 63 | 2024-06-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515741 | T2 DI KILARC-DESCHUTES 16/332 RPL POLE | 70Y
LC | 126384064 | 036/697 | T2 EI HAT CRK #1-WESTWOOD 36/697 RPL PL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-15 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514271 | T2 EI HAT CRK #1-WESTWOOD 36/696 RPL PL | 70Y
LC | 126384065 | 036/693 | T2 EI HAT CRK #1-WESTWD 36/693 GO95 RPL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-15 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35526164 | T2 EI HAT CRK #1-WESTWD 36/693 GO95 | 93G
LC | 126384072 | 036/696 | T2 EI HAT CRK #1-WESTWOOD 36/696 RPL PL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-15 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514271 | T2 EI HAT CRK #1-WESTWOOD 36/696 RPL PL | 70Y
LC | 126395709 | 011/231 | T2 DI KILARC-DESCHUTES 11/231 RPR GYWW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-17 | 2023-06-10 | 2023-10-18 | On-time | 2024-06-09 | 235 | 2023-12-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45857974 | T2 DI KILARC-DESCHUTES 11/231 RPR GYWW | ICW
LC | 126384077 | 037/711 | T2 EI HAT CRK #1-WSTWD 37/711 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-15 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514272 | T2 EI HAT CRK #1-WSTWD 37/711 RPL PL | 70Y
LC | 126384080 | 036/708 | T2 EI HAT CREK #1-WESTWD 36/708 RMV VEG | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-15 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126384093 | 037/713 | T2 EI HAT CRK #1-WESTWOD 37/713 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-15 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514272 | T2 EI HAT CRK #1-WSTWD 37/711 RPL PL | 70Y
LC | 126384129 | :015/009 | T2 DI GL RCK-RDBD :15/9 UNBURY | WILLITS | ETL.1480.POLE.WOOD | 2023-06-15 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46214265 | T2 DI GL RCK-RDBD :15/9 UNBURY | ICW
LC | 126405638 | 010/226 | T2 DI KILARC-DESCHUTES 010/226 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-20 | 2023-06-10 | 2024-04-02 | On-time | 2024-06-09 | 68 | 2024-06-10 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515679 | T2 EI KILARC-DESCHUTES 10/208 RPL POLE | 70Y
LC | 126384140 | :016/003 | T2 DI EGLE RCK-RDBUD :016/003 RPR SPLW | WILLITS | ETL.1480.INSL.CERA | 2023-06-15 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46214266 | T2 DI EGLE RCK-RDBUD :016/003 RPR SPLW | ICW
LC | 126384146 | :015/002 | T2 DI EGLE RCK-RDBUD :015/002 GO95 | WILLITS | ETL.1480.POLE.WOOD | 2023-06-15 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35487313 | T2 DI EGLE RCK-RDBUD :015/002 GO95 | 93G
LC | 126384148 | :015/002 | T2 DI EGLE RCK-RDBUD :015/002 RPR STRW | WILLITS | ETL.1480.POLE.WOOD | 2023-06-15 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46214264 | T2 DI EGLE RCK-RDBUD :015/002 RPR STRW | ICW
LC | 126418853 | 011/233 | T2 DI KILARC-DESCHUTES 11/233 COTTER | TABLEMTN | ETL.7300.INSL.NCER | 2023-06-21 | 2023-06-10 | 2024-04-02 | On-time | 2024-06-09 | 68 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46088676 | T2 DI KILARC-DESCHUTES 11/233 COTTER | ICW
LC | 126384188 | :016/012 | T2 DI EGLE RCK-RDBUD :016/012 COTTER | WILLITS | ETL.1480.INSL.NCER | 2023-06-15 | 2023-06-12 |  | Late | 2024-06-11 |  | 2023-12-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46214268 | T2 DI EGLE RCK-RDBUD :016/012 COTTER | ICW
LC | 126419041 | 011/233 | T2 DI KILARC-DESCHUTES 11/233 RPR JMPR | TABLEMTN | ETL.7300.INSL.NCER | 2023-06-21 | 2023-06-10 | 2024-04-02 | On-time | 2024-06-09 | 68 | 2024-06-10 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46088674 | T2 DI KILARC-DESCHUTES 11/233 RPR JMPR | ICW
LC | 126348789 | 016/316C | T2 SALINAS-LAURELES 16/316C GO95 | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-11 | 2023-06-11 | 2024-02-28 | On-time | 2024-06-10 | 103 | 2024-06-11 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31652485 | T2 SALINAS-LAURELES 16/316A GO95 | 93G
LC | 126384232 | 000/001 | T2 DI MPL CRK-HOOPA 000/001 RPR JMPW | EUREKA | ETL.7490.INSL.NCER | 2023-06-15 | 2023-06-09 |  | Late | 2024-06-08 |  | 2023-12-09 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46203526 | T2 DI MPL CRK-HOOPA 000/001 RPR JMPW | ICW
LC | 126348814 | 016/316A | T2 SALINAS-LAURELES 16/316A GO95 | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-11 | 2023-06-11 | 2024-02-28 | On-time | 2024-06-10 | 103 | 2024-06-11 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31652485 | T2 SALINAS-LAURELES 16/316A GO95 | 93G
LC | 126348819 | 027/397 | T2 CLAY-MARTEL 027/397 GO95 | VICTOR | ETL.8250.POLE.WOOD | 2023-06-11 | 2023-06-11 | 2024-06-04 | On-time | 2024-06-10 | 6 | 2024-06-11 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31652873 | T2 CLAY-MARTEL 027/397 GO95 | 93G
LC | 126348850 | 016/316B | T2 SALINAS-LAURELES16/316B GO95 | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-11 | 2023-06-11 | 2024-02-28 | On-time | 2024-06-10 | 103 | 2024-06-11 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31652485 | T2 SALINAS-LAURELES 16/316A GO95 | 93G
LC | 126348881 | 000/005 | T2 JEFFERSON-LAS PULGAS 0/005 GO95 | METCALF | ETL.7200.POLE.WOOD | 2023-06-11 | 2023-06-11 | 2023-12-12 | On-time | 2024-06-10 | 181 | 2024-06-11 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654580 | T0 JEFFERSON-LAS PULGAS - 60 KV_003/063 | 93G
LC | 126348920 | 015/303 | T2 COLGATE-PALERMO 15/303 GO95 | SACTO | ETL.6500.POLE.WOOD | 2023-06-11 | 2023-06-11 | 2023-10-31 | On-time | 2024-06-10 | 223 | 2023-12-11 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31655124 | T2 COLGATE-PALERMO 15/303 GO95 | 93G
LC | 126350403 | 027/398 | T2 CLAY-MARTEL 027/398 GO95 | VICTOR | ETL.8250.POLE.WOOD | 2023-06-12 | 2023-06-12 | 2024-06-04 | On-time | 2024-06-11 | 7 | 2024-06-12 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31652873 | T2 CLAY-MARTEL 027/397 GO95 | 93G
LC | 126351190 | 000/019 | T2 EI KILARC-DESCHUTES 0/019 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-12 | 2023-06-12 | 2024-03-19 | On-time | 2024-06-11 | 84 | 2024-06-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515347 | T2 EI KILARC-DESCHUTES 0/015 RPL STRW | 70Y
LC | 126351272 | 000/015 | T2 EI KILARC-DESCHUTES 0/015 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-12 | 2023-06-12 | 2024-03-19 | On-time | 2024-06-11 | 84 | 2024-06-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515347 | T2 EI KILARC-DESCHUTES 0/015 RPL STRW | 70Y
LC | 126384551 | :013/020 | DISTRIBUION GUY WIRE | WILLITS | ETL.1480.POLE.WOOD | 2023-06-15 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46214260 | T2 DI EGL RCK-REDBUD :013/020 RPR GYWW | ICW
LC | 126384559 | :015/004 | T2 DI EGL RCK-REDBUD :015/4 RPR SWITCH | WILLITS | ETL.1480.POLE.NWOD | 2023-06-15 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 623 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Out of Adjustment | Switch | Repair | 46216626 | T2 DI EGL RCK-REDBUD :015/4 RPR SWITCH | ICE
LC | 126384571 | :015/007 | T2 DI EGLE RCK-RDBUD :015/007 RPL POLE | WILLITS | ETL.1480.POLE.WOOD | 2023-06-15 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515750 | T2 DI EGLE RCK-RDBUD :015/007 RPL POLE | 70Y
LC | 126384593 | :013/009 | T2 DI EGLE RCK-RDBUD :013/009 RPL INSW | WILLITS | ETL.1480.INSL.CERA | 2023-06-15 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35487312 | T2 DI EGLE RCK-RDBUD :013/009 RPL INSW | 93I
LC | 126353530 | 001/026 | T2 EI KILARC-DESCHUTES 1/026 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-12 | 2023-06-12 | 2024-03-19 | On-time | 2024-06-11 | 84 | 2024-06-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515348 | T2 EI KILARC-DESCHUTES 01/023 RPL STRW | 70Y
LC | 126384644 | :014/006 | T2 DI EAGLE RCK-RDBUD :14/006 RPR INSW | WILLITS | ETL.1480.INSL.NCER | 2023-06-15 | 2023-06-12 |  | Late | 2024-06-11 |  | 2023-12-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46214261 | T2 DI EAGLE RCK-RDBUD 014/006 RPR INSW | ICW
LC | 126353930 | 001/028 | T2 EI KILARC-DESCHUTES 1/028 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-12 | 2023-06-12 | 2024-03-19 | On-time | 2024-06-11 | 84 | 2024-06-12 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515348 | T2 EI KILARC-DESCHUTES 01/023 RPL STRW | 70Y
LC | 126354365 | 078/003B | T2 EI HUMBOLDT-TRINITY 78/3B RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-12 | 2023-06-12 | 2024-05-30 | On-time | 2024-06-11 | 12 | 2024-06-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096590 | T2 EI HUMBOLDT-TRINITY 78/3A RPR GYWW | ICW
LC | 126354402 | 078/003C | T2 EI HUMBOLDT-TRINITY 78/3C RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-12 | 2023-06-12 | 2024-05-30 | On-time | 2024-06-11 | 12 | 2024-06-12 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46096590 | T2 EI HUMBOLDT-TRINITY 78/3A RPR GYWW | ICW
LC | 126354403 | 078/003A | T2 EI HUMBOLDT-TRINITY 78/3A RPR GYWW | EUREKA | ETL.1820.POLE.NWOD | 2023-06-12 | 2023-06-12 | 2024-05-30 | On-time | 2024-06-11 | 12 | 2024-06-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096590 | T2 EI HUMBOLDT-TRINITY 78/3A RPR GYWW | ICW
LC | 126354700 | 005/025 | T2 EI MORRO BAY-TEMPLETON 5/25 RPR OPGW | PISMOBCH | ETL.5933.TOWR | 2023-06-12 | 2023-06-12 | 2023-11-01 | On-time | 2024-06-11 | 223 | 2023-09-12 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45907954 | T2 EI MORRO BAY-TEMPLETON 5/025 RPR OPGW | ICS
LC | 126355708 | 014/126 | T2 PIT #6 JCT-ROUND MTN 14/126 RPR INSW | TABLEMTN | ETL.5440.INSL.CERA | 2023-06-12 | 2023-06-12 | 2023-11-15 | On-time | 2024-06-11 | 209 | 2024-06-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair
LC | 126356156 | 004/044 | T2 EI HAT CREEK #1-PIT #1 04/044 RPL PL | TABLEMTN | ETL.7020.POLE.WOOD | 2023-06-12 | 2023-06-12 | 2023-08-17 | On-time | 2024-06-11 | 299 | 2024-06-12 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31654377 | T2 EI HAT CREEK #1-PIT #1 04/044 RPL PL | 70Y
LC | 126387062 | 009/054 | T2 DI VACA-PRKWY 009/054 RPL INSS | SACTO | ETL.5850.INSL | 2023-06-16 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672706 | T2 DI VACA-PRKWY 009/054 RPL INSS | 93K
LC | 126387069 | :013/015 | T2 DI EGL RCK-RDBUD :013/015 RPR STRW | WILLITS | ETL.1480.POLE.WOOD | 2023-06-16 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46214079 | T2 DI EGL RCK-RDBUD :013/015 RPR STRW | ICW
LC | 126387278 | 000/002 | T2 DI MNTCLLO PH TAP 000/002 RPR CNDW | LAKEVLLE | ETL.1602.INSL | 2023-06-16 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46204148 | T2 DI MNTCLLO PH TAP 000/002 RPR CNDW | ICW
LC | 126387279 | 000/002 | T2 DI MNTCLLO PH TAP 000/002 RPR INSW | LAKEVLLE | ETL.1602.INSL | 2023-06-16 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46204149 | T2 DI MNTCLLO PH TAP 000/002 RPR INSW | ICW
LC | 126387282 | :013/012 | T2 DI EGL RCK-RDBD :13/12 RPR INSW | WILLITS | ETL.1480.INSL.CERA | 2023-06-16 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46214078 | T2 DI EGL RCK-RDBD :13/12 RPR INSW | ICW
LC | 126356170 | 112/005 | T2 EI HMBLT-BRDGVL 112/5R RPR GYWW | EUREKA | ETL.1810.POLE.STPS | 2023-06-12 | 2023-06-12 | 2023-10-03 | On-time | 2024-06-11 | 252 | 2023-09-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45881482 | T2 EI HMBLT-BRDGVL 112/5R RPR GYWW | ICW
LC | 126387354 | 018/003 | T2 DI MENDCNO-HRTLY 018/003 RPL POLE | WILLITS | ETL.7510.POLE.WOOD | 2023-06-16 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35494504 | T2 DI MENDCNO-HRTLY 018/003 RPL POLE | 70Y
LC | 126387392 | :019/012 | T2 DI EAGLE RCK-REDBUD :19/12 RPL HRDD | WILLITS | ETL.1480.POLE.WOOD | 2023-06-16 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46213896 | T2 DI EAGLE RCK-REDBUD :19/12 RPL HRDD | ICW
LC | 126387490 | :019/012 | T2 DI EAGLE RCK-REDBUD :19/12 RPL ANCW | WILLITS | ETL.1480.POLE.WOOD | 2023-06-16 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35487314 | T2 DI EAGLE RCK-REDBUD :19/12 RPL ANCW | 93E
LC | 126356238 | 112/005 | T2 EI HMBLT-BRDGVL 112/5C RPR GYWW | EUREKA | ETL.1810.POLE.STPS | 2023-06-12 | 2023-06-12 | 2023-10-03 | On-time | 2024-06-11 | 252 | 2023-09-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45881482 | T2 EI HMBLT-BRDGVL 112/5R RPR GYWW | ICW
LC | 126387608 | 003/070 | T2 DI DLTA-MTN GT JCT 3/70 RPL STRW | TABLEMTN | ETL.6750.POLE.WOOD | 2023-06-16 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508688 | T2 DI DLTA-MTN GT JCT 3/070 RPL PL | 70Y
LC | 126356291 | 112/005 | T2 EI HMBLT-BRDGVL 112/5L RPR GYWW | EUREKA | ETL.1810.POLE.STPS | 2023-06-12 | 2023-06-12 | 2023-10-03 | On-time | 2024-06-11 | 252 | 2023-09-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45881482 | T2 EI HMBLT-BRDGVL 112/5R RPR GYWW | ICW
LC | 126387977 | 041/010B | T2 DI TRNTY MPL CRK 41/10B RPR INSW | EUREKA | ETL.8170.INSL.CERA | 2023-06-16 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46172190 | T2 DI TRNTY MPL CRK 041/010B RPR INSW | ICW
LC | 126388064 | 005/115 | T2 DI KSWCK-CSCD 005/115 RPL STRW | TABLEMTN | ETL.7260.POLE.WOOD | 2023-06-16 | 2023-06-13 | 2024-06-13 | Late | 2024-06-12 | -1 | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521890 | T2 DI KSWCK-CSCD 005/115 RPL STRW | 70Y
LC | 126388104 | :014/009 | T2 DI EGLE RCK-RDBD :14/9 RPR STRW | WILLITS | ETL.1480.POLE.NWOD | 2023-06-16 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46214262 | T2 DI EGL RCK-RDBD :14/9 RPR STRW | ICW
LC | 126356299 | 072/003 | T2 EI HUMBOLDT-TRININTY 72/3L RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-12 | 2023-06-12 | 2023-08-23 | On-time | 2024-06-11 | 293 | 2023-12-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45881352 | T2 EI CTNWD-HMBLT 72/3L RPR GYWW | ICW
LC | 126388365 | ;002/017 | T2 EI CARIBOU #2 ;002/017 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-06-16 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35527151 | T2 EI CARIBOU #2 ;002/017 RPL STRW | 70Y
LC | 126388487 | 038/742 | T2 DI HAT CK WSTWD#1 38/742 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-16 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514274 | T2 DI HAT CREEK #1-WSTWD 38/730 RPL STRW | 70Y
LC | 126388511 | 108/004 | T2 EI HUMBOLDT-BRDGVLLE 108/4R RPR GYWW | EUREKA | ETL.1810.POLE.STPS | 2023-06-16 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46134799 | T2 EI HUMBOLDT-BRDGVLLE 108/4R RPR GYWW | ICW
LC | 126356380 | 072/003 | T2 EI HUMBOLDT-TRINITY 72/3C RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-12 | 2023-06-12 | 2023-08-23 | On-time | 2024-06-11 | 293 | 2023-12-12 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45881352 | T2 EI CTNWD-HMBLT 72/3L RPR GYWW | ICW
LC | 126356392 | 068/344 | T2 EI MALIN-ROUND MTN #2 68/344 COMPLETE | TABLEMTN | ETL.6020.INSL.NCER | 2023-06-12 | 2023-06-12 | 2024-05-11 | On-time | 2024-06-11 | 31 | 2024-06-12 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46092910 | T2 EI MALIN-ROUND MTN #2 68/344 COTTER | ICS
LC | 126383738 | 067/338 | T2 DI MALIN-ROUND MTN #2 067/338 COTTER | TABLEMTN | ETL.6020.INSL.NCER | 2023-06-15 | 2023-06-12 | 2023-12-21 | On-time | 2024-06-11 | 173 | 2024-06-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46055619 | T2 DI MALIN-ROUND MTN #2 067/338 COTTER | ICS
LC | 126384195 | 004/019 | T2 DI PITTSBURG-SAN RAMON 4/19 COMPLETE | CONCORD | ETL.5490.TOWR | 2023-06-15 | 2023-06-12 | 2024-06-06 | On-time | 2024-06-11 | 5 | 2024-06-12 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46127699 | T2 DI PITTSBURG-SAN RAMON 4/19 BNT STEEL | ICQ
LC | 126389100 | 000/025 | T2 DI SPULDG #3 SPULDG#1 00/025 RPR GYWW | SACTO | ETL.8050.POLE.NWOD | 2023-06-16 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46127247 | T2 DI SPULDG #3 SPULDG#1 00/025 RPR GYWW | ICW
LC | 126389103 | 030/001 | T2 DI TRINITY-MAPLE CREEK 30/1 RPR JMPW | EUREKA | ETL.8170.INSL.CERA | 2023-06-16 | 2023-06-13 |  | Late | 2024-06-12 |  | 2023-09-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45860427 | T2 DI TRINITY-MAPLE CREEK 30/01 RPR JMPW | ICW
LC | 126384222 | :012/074 | T2 DI EAGLE RCK-CORTINA :12/74 COTTER | WILLITS | ETL.1470.INSL.NCER | 2023-06-15 | 2023-06-12 | 2024-05-13 | On-time | 2024-06-11 | 29 | 2023-09-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45854655 | T2 DI EAGLE RCK-CORTINA :12/74 COTTER | ICS
LC | 126389447 | 057/419A | T2 EI BRDGVIL CTTNWD 57/419A RPR GYWS | TABLEMTN | ETL.1110.POLE.NWOD | 2023-06-16 | 2023-06-16 | 2024-06-26 | Late | 2024-06-15 | -11 | 2024-06-16 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46088656 | T2 EI BRDGVIL CTTNWD 57/419A RPR GYWS | ICS
LC | 126384280 | 004/019 | T2 DI PITTSBURG-SAN RAMON 4/19 RPR INSS | CONCORD | ETL.5490.INSL | 2023-06-15 | 2023-06-12 | 2024-05-02 | On-time | 2024-06-11 | 40 | 2024-06-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45999073 | T2 DI PITTSBURG-SAN RAMON 4/19 RPR INSS | ICS
LC | 126384494 | :011/065 | T2 DI EAGLE RCK-CRTNA :011/065 RPR INSS | WILLITS | ETL.1470.INSL.NCER | 2023-06-15 | 2023-06-12 | 2024-05-14 | On-time | 2024-06-11 | 28 | 2024-06-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46176322 | T2 DI EAGLE RCK-CRTNA :011/065 RPR INSS | ICS
LC | 126388934 | 068/344A | T2 DI MALIN-ROUND MTN#2 68/344A RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-06-16 | 2023-06-12 | 2024-05-10 | On-time | 2024-06-11 | 32 | 2024-06-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45858065 | T2 DI MALIN-ROUND MTN#2 68/344A RPR SHLS | ICS
LC | 126390173 | 001/041 | T2 DI SPAULDING-SUMMT 1/41 RPR JUMW | SACTO | ETL.8060.INSL.NCER | 2023-06-16 | 2023-06-14 | 2024-06-21 | Late | 2024-06-13 | -8 | 2023-09-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46127494 | T2 DI SPAULDING-SUMMT 1/41 RPR JMPW | ICW
LC | 126390176 | 001/041 | T2 DI SPAULDING-SUMMT 1/41 RPR GYWW | SACTO | ETL.8060.POLE.NWOD | 2023-06-16 | 2023-06-14 | 2024-06-21 | Late | 2024-06-13 | -8 | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46127495 | T2 DI SPAULDING-SUMMT 1/41 RPL GYWW | ICW
LC | 126392560 | :012/070 | T2 DI EAGLE ROCK-CORTINA :12/70 RPR INSS | WILLITS | ETL.1470.INSL.NCER | 2023-06-16 | 2023-06-12 | 2024-05-13 | On-time | 2024-06-11 | 29 | 2024-06-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46176323 | T2 DI EAGLE ROCK-CORTINA :12/70 RPR INSS | ICS
LC | 126395128 | 067/339 | T2 DI MLN-RND MT#2 67/339 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-06-17 | 2023-06-12 | 2024-05-10 | On-time | 2024-06-11 | 32 | 2024-06-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46083465 | T2 DI MLN-RND MT#2 67/339 RPR OPGW | ICS
LC | 126407877 | :011/064 | T2 DI EGL RCK-CORTINA :11/64 RPR INSS | WILLITS | ETL.1470.INSL.NCER | 2023-06-20 | 2023-06-12 | 2024-05-13 | On-time | 2024-06-11 | 29 | 2023-09-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45861683 | T2 DI EGL RCK-RDBD :11/64 RPR INSS | ICS
LC | 126390744 | :014/010 | T2 DI EGL RCK-RDBD :14/10 RPR SPLW | WILLITS | ETL.1480.INSL.NCER | 2023-06-16 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46214263 | T2 DI EGL RCK-RDBD :14/10 RPR SPLW | ICW
LC | 126412159 | 033/187 | T2 DI EXCHEQUER-INDN FLT 33/187 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-06-20 | 2023-06-12 | 2023-12-12 | On-time | 2024-06-11 | 182 | 2023-09-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45883714 | T2 DI EXCHEQUER-INDN FLT 33/187 RPR JMPS | ICS
LC | 126390878 | 024/003 | T2 DI MPL CRK-HOOPA 24/003 RMV VEG | EUREKA | ETL.7490.POLE.NWOD | 2023-06-16 | 2023-06-15 | 2024-06-20 | Late | 2024-06-14 | -6 | 2024-06-15 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126390970 | 006/001 | T2 DI MAPLE CRK-HOOP 6/1 RPR JUMW | EUREKA | ETL.7490.INSL.NCER | 2023-06-16 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46203531 | T2 DI MAPLE CRK-HOOP 6/1 RPR JUMW | ICW
LC | 126391317 | 005/038 | T2 DI PIT #4 TAP 005/038 RPR INSS | TABLEMTN | ETL.5432.INSL.CERA | 2023-06-16 | 2023-06-15 | 2024-06-24 | Late | 2024-06-14 | -10 | 2024-06-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46083534 | T2 DI PIT #4 TAP 005/038 RPR INSS | ICS
LC | 126391426 | 007/006 | T2 DI MPL CRK-HOOPA 007/006 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-06-16 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46203530 | T2 DI MPL CRK-HOOPA 007/006 RPR GYWW | ICW
LC | 126586015 | 000/010 | T2 DI CRUSHER TP 0/10 RPR GYWW | MOSSLNDG | ETL.6241.POLE.WDPS | 2023-07-14 | 2023-06-12 | 2024-05-20 | On-time | 2024-06-11 | 22 | 2023-12-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46081757 | T2 DI CRUSHER TP 0/10 RPR GYWW | ICW
LC | 126359248 | 009/191 | T2 EI KILARC-DESCHUTES 009/191 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-13 | 2023-06-13 | 2024-04-02 | On-time | 2024-06-12 | 71 | 2024-06-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515677 | T2 DI KILARC DESCHUTES 09/188 RPL POLE | 70Y
LC | 126359504 | :012/002 | T2 EI EAGLE ROCK-CORTINA :012/2 RPL PL | WILLITS | ETL.1470.POLE.WOOD | 2023-06-13 | 2023-06-13 | 2024-05-14 | On-time | 2024-06-12 | 29 | 2024-06-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35487303 | T2 EI EAGLE ROCK-CORTINA :012/2 RPL PL | 70Y
LC | 126392178 | 028/551 | T2 DI HT CRK #1-WSTWD 28/551 RPR INSW | TABLEMTN | ETL.7030.INSL.NCER | 2023-06-16 | 2023-06-13 | 2024-06-19 | Late | 2024-06-12 | -7 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46091832 | T2 DI HT CRK #1-WSTWD 28/551 RPR INSW | ICW
LC | 126392264 | 012/138 | T2 DI DRM-SMMT #1 012/138L RPL ANCW | SACTO | ETL.1440.POLE.WDPS | 2023-06-16 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 637 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35484107 | T2 DI DRUM-SUMMIT#1 11/134L RPL ANCW | 93E
LC | 126392266 | 011/128 | T2 DI DRUM-SUMMIT #2 11/128L RPR GYWW | SACTO | ETL.1450.POLE.STPS | 2023-06-16 | 2023-06-14 | 2024-06-17 | Late | 2024-06-13 | -4 | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098246 | T2 DI DRUM-SUMMIT #2 11/128 RPR GYWW | ICW
LC | 126392267 | 012/138 | T2 DI DRUM-SUMMIT #1 012/138C RPL ANCW | SACTO | ETL.1440.POLE.WDPS | 2023-06-16 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 637 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35484107 | T2 DI DRUM-SUMMIT#1 11/134L RPL ANCW | 93E
LC | 126359563 | 024/182 | T2 PARADISE-TBLE MTN 24/182 RPL INSW | TABLEMTN | ETL.4316.INSL.NCER | 2023-06-13 | 2023-06-13 | 2024-01-30 | On-time | 2024-06-12 | 134 | 2024-06-13 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35484834 | T2 DI PARADISE TBL MTN 23/181 RPL INSW | 93I
LC | 126359815 | 009/189 | T2 EI KILARC-DESCHUTES 09/189 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-13 | 2023-06-13 | 2024-04-06 | On-time | 2024-06-12 | 67 | 2024-06-13 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515677 | T2 DI KILARC DESCHUTES 09/188 RPL POLE | 70Y
LC | 126392421 | 020/007 | T2 DI MPL CRK-HOOPA 20/007 RPL POLE | EUREKA | ETL.7490.POLE.WOOD | 2023-06-16 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526560 | T2 DI MPL CRK-HOOPA 20/007 RPL POLE | 70Y
LC | 126392509 | 000/013 | T2 DI MONTCELLO PH TAP 0/13 RMV NEST | LAKEVLLE | ETL.1602.POLE.NWOD | 2023-06-16 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46204153 | T2 DI MONTCELLO PH TAP 0/13 RMV NEST | ICS
LC | 126360471 | :013/000 | T2 EI EGLE ROCK-CRTINA :013/0 RPL PL | WILLITS | ETL.1470.POLE.WOOD | 2023-06-13 | 2023-06-13 | 2024-05-14 | On-time | 2024-06-12 | 29 | 2024-06-13 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487303 | T2 EI EAGLE ROCK-CORTINA :012/2 RPL PL | 70Y
LC | 126392804 | 042/003C | T2 DI TRINTY-MPLE CRK 42/03C RPR POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-06-16 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46172192 | T2 DI TRINTY-MPLE CRK 42/03C RPR POLE | ICW
LC | 126361042 | 071/361 | T2 EI MALIN-ROUND MTN #2 71/361 RPR ANCS | TABLEMTN | ETL.6020.TOWR | 2023-06-13 | 2023-06-13 | 2023-10-09 | On-time | 2024-06-12 | 247 | 2023-12-13 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45855681 | T2 EI MALIN-ROUND MTN #2 71/361 RPR ANCS | ICS
LC | 126393214 | 048/371 | T2 DI BRDGVLL-CTTNWD 48/371 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-06-16 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46088641 | T2 DI BRDGVLL-CTTNWD 48/371 RPR OPGW | ICS
LC | 126361246 | 000/009 | T2 EI JEFFERSON-STANFORD 00/09 COTTER | METCALF | ETL.7220.INSL.NCER | 2023-06-13 | 2023-06-13 | 2023-07-11 | On-time | 2024-06-12 | 337 | 2023-12-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45864808 | T2 EI JEFFERSON-STANFORD 00/09 COTTER | ICW
LC | 126362440 | 004/104 | T2 EI CASCDE-BNT-DESCHTES 4/104 RPR GYWW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-06-13 | 2023-06-13 | 2023-08-16 | On-time | 2024-06-12 | 301 | 2023-12-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 45870611 | T2 EI CASCDE-BNT-DESCHTES 4/104 RPR GYWW | ICW
LC | 126393385 | 048/372 | T2 DI BRDGVLL-CTTNWD 48/372 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-06-16 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46088642 | T2 DI BRDGVLL-CTTNWD 48/372 RPR OPGW | ICS
LC | 126362765 | 111/000 | T2 EI HUMBOLDT-BRIDGVLE 111/0 RPL BRACES | EUREKA | ETL.1810.POLE.WDPS | 2023-06-13 | 2023-06-13 | 2023-10-19 | On-time | 2024-06-12 | 237 | 2023-09-13 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 45882388 | T2 EI HUMBOLDT-BRIDGVLE 111/0 RPL BRACES | ICW
LC | 126363195 | 014/101 | T2 EI CAYUCOS-CAMBRIA 014/101 RPR GYWW | PISMOBCH | ETL.8560.POLE.NWOD | 2023-06-13 | 2023-06-13 | 2024-01-14 | On-time | 2024-06-12 | 150 | 2024-06-13 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46090184 | T2 EI CAYUCOS-CAMBRIA 014/101 RPR GYWW | ICS
LC | 126389090 | 018/005 | T2 DI TRINITY-MAPLE CREEK 18/5 RPR JMPW | EUREKA | ETL.8170.INSL.NCER | 2023-06-16 | 2023-06-13 | 2023-10-17 | On-time | 2024-06-12 | 239 | 2023-09-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45860426 | T2 DI TRINITY-MAPLE CREEK 18/05 RPR JMPW | ICW
LC | 126393660 | 037/719 | T2 EI HAT CRK #1-WESTWD 37/719 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-16 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514273 | T2 EI HAT CRK #1-WESTWOOD 37/719 RPL PL | 70Y
LC | 126393663 | 037/721 | T2 EI HAT CRK #1-WESTWD 37/721 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-16 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35563005 | T2 EI HAT CRK #1-WESTWD 37/721 RPL STRW | 70Y
LC | 126393671 | 037/724 | T2 EI HAT CRK #1-WESTWD 37/724 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-16 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514273 | T2 EI HAT CRK #1-WESTWOOD 37/719 RPL PL | 70Y
LC | 126393680 | 038/737 | T2 EI HT CRK #1-WESTWD 38/737 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-16 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35514276 | T2 EI HT CRK #1-WESTWOOD 38/737 REFRAME | 93E
LC | 126393687 | 037/717 | T2 EI HAT CRK #1-WESTWD 37/717 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-16 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514272 | T2 EI HAT CRK #1-WSTWD 37/711 RPL PL | 70Y
LC | 126393688 | 037/723 | T2 EI HAT CRK #1-WESTWD 37/723 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-16 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35560712 | T2 EI HAT CRK #1-WESTWD 37/723 RPL STRW | 70Y
LC | 126390467 | 015/002 | T2 DI CARIBOU-PLUMAS JCT 15/2 RPL HRDW | TABLEMTN | ETL.6290.POLE.WOOD | 2023-06-16 | 2023-06-13 | 2024-05-09 | On-time | 2024-06-12 | 34 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46091831 | T2 DI CARIBOU-PLUMAS JCT 15/2 RPL HRDW | ICW
LC | 126391702 | 001/010 | `2 DI HT CRK#1-PIT#1 001/010 RPR STRC | TABLEMTN | ETL.7020.TOWR | 2023-06-16 | 2023-06-13 | 2024-05-15 | On-time | 2024-06-12 | 28 | 2024-06-13 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46132290 | T2 DI HT CRK#1-PIT#1 001/010 RPR STRC | ICQ
LC | 126392836 | 032/177 | T2 DI EXCHEQUER-INDN FLT 32/177 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-06-16 | 2023-06-13 | 2023-12-13 | On-time | 2024-06-12 | 182 | 2024-06-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45883710 | T2 DI EXCHEQUER-INDN FLT 32/177 RPR JMPS | ICS
LC | 126393891 | 021/551 | T2 DI CARIBOU #2 21/551 RPL ANCW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-06-16 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35515871 | T2 DI CARIBOU #2 21/551 RPL ANCW | 93E
LC | 126393650 | 001/016 | T2 DI PIT #1-HAT CREEK #2 1/16 RPL INSL | TABLEMTN | ETL.7040.INSL.CERA | 2023-06-16 | 2023-06-13 | 2024-05-14 | On-time | 2024-06-12 | 29 | 2024-06-13 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31654447 | T2 DI PIT #1-HAT CREEK #2 1/16 RPL INSL | 93K
LC | 126394054 | 000/001 | T2 DI EAGLE RCK-REDBUD 000/001 RPR STRT | WILLITS | ETL.1480.TOWR | 2023-06-16 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46179148 | T2 DI EAGLE RCK-REDBUD 000/001 RPR STRT | ICQ
LC | 126394068 | 001/009 | T2 DI HAT CRK#1-PIT#1 1/9 RPR STRT | TABLEMTN | ETL.7020.TOWR | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46132291 | T2 DI HAT CRK#1-PIT#1 1/9 RPR STRT | ICQ
LC | 126394193 | 032/178 | T2 DI EXCHEQUER-INDN FLT 32/178 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-06-16 | 2023-06-13 | 2023-12-13 | On-time | 2024-06-12 | 182 | 2024-06-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45883711 | T2 DI EXCHEQUER-INDN FLT 32/178 RPR JMPS | ICS
LC | 126394229 | 069/350 | T2 DI MLN-RND MNTN#2 69/350 COMPLETE | TABLEMTN | ETL.6020.TOWR | 2023-06-16 | 2023-06-13 | 2024-06-05 | On-time | 2024-06-12 | 7 | 2024-06-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 46132327 | T2 DI MALIN-ROUND MNTN#2 69/350 RPR ANCS | ICS
LC | 126394165 | 017/010 | T2 DI TRINITY-MAPLE CREEK 17/10 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-06-16 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35502981 | T2 DI TRINITY-MAPLE CREEK 17/10 RPL POLE | 70Y
LC | 126394168 | 000/012 | T2 DI SPLDNG-SMMT 0/12 RPL ANCW | SACTO | ETL.8060.POLE.WOOD | 2023-06-16 | 2023-06-14 | 2024-06-22 | Late | 2024-06-13 | -9 | 2024-06-14 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35508692 | T2 DI SPLDNG-SMMT 0/12 RPL ANCW | 93E
LC | 126394266 | 070/354A | T2 DI MLIN-RND MTN#2 70/354A RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-06-16 | 2023-06-13 | 2024-01-18 | On-time | 2024-06-12 | 146 | 2024-06-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 45866420 | T2 DI MLIN-RND MTN#2 70/354A RPR SHIELD | ICS
LC | 126394296 | 011/004 | T2 DI CARIBOU-PLMS JCT 11/4 RPR GYYWW | TABLEMTN | ETL.6290.POLE.WOOD | 2023-06-16 | 2023-06-13 | 2024-05-07 | On-time | 2024-06-12 | 36 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091827 | T2 DI CARIBOU-PLMS JCT 11/4 RPR GYYWW | ICW
LC | 126394355 | 013/008 | T2 DI TRNTY-MPL CRK 13/8L RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-06-16 | 2023-06-13 | 2024-01-19 | On-time | 2024-06-12 | 145 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079376 | T2 DI TRNTY-MPL CRK 13/8L RPR GYWW | ICW
LC | 126394409 | 013/009 | T2 DI TRINITY-MAPLE CRK 013/009 COTTER | EUREKA | ETL.8170.INSL.NCER | 2023-06-16 | 2023-06-13 | 2024-01-19 | On-time | 2024-06-12 | 145 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079377 | T2 DI TRINITY-MAPLE CRK 013/009 COTTER | ICW
LC | 126394740 | 013/000 | T2 DI TRNTY-MPLE CRK 13/0L RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 | 2024-01-19 | On-time | 2024-06-12 | 145 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079279 | T2 DI TRNTY-MPLE CRK 13/0R RPR GYWW | ICW
LC | 126394308 | 030/002 | T2 DI TRNTY-MPL CRK 30/2C RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-16 | 2023-06-13 | 2024-06-17 | Late | 2024-06-12 | -5 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172089 | T2 DI TRNTY-MPL CRK 30/2C RPR GYWW | ICW
LC | 126394742 | 013/000 | T2 DI TRNTY-MPLE CRK 13/0C RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 | 2024-01-19 | On-time | 2024-06-12 | 145 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079279 | T2 DI TRNTY-MPLE CRK 13/0R RPR GYWW | ICW
LC | 126394743 | 013/000 | T2 DI TRNTY-MPLE CRK 13/0R RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 | 2024-01-19 | On-time | 2024-06-12 | 145 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079279 | T2 DI TRNTY-MPLE CRK 13/0R RPR GYWW | ICW
LC | 126394747 | 013/000 | T2 DI TRNTY-MPLE CRK 13/0R RPR STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 | 2024-01-19 | On-time | 2024-06-12 | 145 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46164509 | T2 DI TRNTY-MPLE CRK 13/0R RPR STRW | ICW
LC | 126394793 | 013/000 | T2 DI TRNTY-MPLE CRK 13/0 COTTER | EUREKA | ETL.8170.INSL.CERA | 2023-06-17 | 2023-06-13 | 2024-01-19 | On-time | 2024-06-12 | 145 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46079374 | T2 DI TRNTY-MPLE CRK 13/0 COTTER | ICW
LC | 126394835 | 069/351 | T2 DI MLN-RND MT#2 69/351 COMPLETE | TABLEMTN | ETL.6020.TOWR | 2023-06-17 | 2023-06-13 | 2024-06-05 | On-time | 2024-06-12 | 7 | 2024-06-13 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46132328 | T2 DI MLN-RND MT#2 69/351 UNBURY | ICQ
LC | 126394853 | 069/351 | T2 DI MALIN-ROUND MTN #2 69/351 RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-06-17 | 2023-06-13 | 2023-08-29 | On-time | 2024-06-12 | 288 | 2023-09-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45858066 | T2 DI MALIN-ROUND MTN #2 69/351 RPR SHLS | ICS
LC | 126394669 | 008/005 | T2 DI MAPLE CRK-HOOPA 8/5 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-06-17 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46203534 | T2 DI MAPLE CRK-HOOPA 8/5 RPR GYWW | ICW
LC | 126394876 | 043/000 | T2 DI TRINITY-MAPLE CREEK 43/0C RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-06-17 | 2023-06-13 | 2024-06-04 | On-time | 2024-06-12 | 8 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096672 | T2 DI TRINITY-MAPLE CREEK 43/0C RPR GYWW | ICW
LC | 126394877 | 030/162 | T2 DI EXCHEQUER-INDN FLT 30/162 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-06-17 | 2023-06-13 | 2023-12-14 | On-time | 2024-06-12 | 181 | 2023-09-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45883712 | T2 DI EXCHEQUER-INDN FLT 30/162 RPR JMPS | ICS
LC | 126394878 | 043/000 | T2 DI TRINITY-MAPLE CREEK 43/0R RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-06-17 | 2023-06-13 | 2024-06-04 | On-time | 2024-06-12 | 8 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096672 | T2 DI TRINITY-MAPLE CREEK 43/0C RPR GYWW | ICW
LC | 126394974 | 068/347 | T2 DI MALIN-ROUND MTN #2 68/347 RPR OPGW | TABLEMTN | ETL.6020.TOWR | 2023-06-17 | 2023-06-13 | 2024-01-22 | On-time | 2024-06-12 | 142 | 2024-06-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46083466 | T2 DI MALIN-ROUND MTN #2 68/347 RPR OPGW | ICS
LC | 126394787 | 001/016 | T2 DI PT #1-HT CRK #2-BRNY 1/16 DUP CNCL | TABLEMTN | ETL.7040.INSL.CERA | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35519936 | T2 DI PT #1-HT CRK #2-BRNY 1/16 RPL INSS | 93K
LC | 126394789 | 004/024 | T2 DI PITTSBURG-CLAYTON #4 4/24 RPL INSS | CONCORD | ETL.3291.INSL | 2023-06-17 | 2023-06-14 | 2024-06-24 | Late | 2024-06-13 | -11 | 2024-06-14 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671944 | T2 DI PITTSBURG-CLAYTON #4 4/24 RPL INSS | 93K
LC | 126395023 | 002/019 | T2 DI PT #1-HT CRK #2-BRNY 2/19 COTTER | TABLEMTN | ETL.7040.INSL.NCER | 2023-06-17 | 2023-06-13 | 2023-10-17 | On-time | 2024-06-12 | 239 | 2024-06-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45857968 | T2 DI PT #1-HT CRK #2-BRNY 2/19 COTTER | ICS
LC | 126394810 | 004/024 | T2 DI PITTSBURG-CLAYTON #3 4/24 RPL INSS | CONCORD | ETL.3290.INSL | 2023-06-17 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671780 | DI PITTSBURG-CLAYTON #3 4/24 RPL INSS | 93K
LC | 126394829 | 038/732 | T2 DI HAT CRK#1 WSTWD 38/732 GO95 RPL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-17 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35525300 | T2 DI HAT CRK#1 WSTWD 38/732 GO95 | 93G
LC | 126395173 | 045/004 | T2 DI TRNTY MPL CRK 45/4 RPR JUMW | EUREKA | ETL.8170.INSL.CERA | 2023-06-17 | 2023-06-13 | 2023-11-03 | On-time | 2024-06-12 | 222 | 2023-09-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45867434 | T2 DI TRNTY MPL CRK 45/004 RPR JUMW | ICW
LC | 126395342 | 029/152 | T2 DI EXCHEQUER-INDN FLT 29/152 RPR JMPS | FRESNO | ETL.8650.INSL.NCER | 2023-06-17 | 2023-06-13 | 2023-12-14 | On-time | 2024-06-12 | 181 | 2023-09-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45883713 | T2 DI EXCHEQUER-INDN FLT 29/152 RPR JMPS | ICS
LC | 126394858 | 008/003A | T2 DI MPL CRK-HOOPA 008/003A RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-06-17 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46203532 | T2 DI MPL CRK-HOOPA 008/003A RPR GYWW | ICW
LC | 126395418 | 001/012 | T2 DI TRINITY-MAPLE CRK 001/012 RPR STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-17 | 2023-06-13 | 2024-01-18 | On-time | 2024-06-12 | 146 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46079372 | T2 DI TRINITY-MAPLE CRK 001/012 RPR STRW | ICW
LC | 126395474 | 044/003 | T2 DI TRINITY-MAPLE CREEK 44/3 RPR JMPW | EUREKA | ETL.8170.INSL.CERA | 2023-06-17 | 2023-06-13 | 2023-11-01 | On-time | 2024-06-12 | 224 | 2023-09-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45867433 | T2 DI TRINITY-MAPLE CREEK 44/03 RPR JMPW | ICW
LC | 126395476 | 044/003 | T2 DI TRINITY-MAPLE CREEK 44/3R RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 | 2024-06-06 | On-time | 2024-06-12 | 6 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096675 | T2 DI TRINITY-MAPLE CREEK 44/3R RPR GYWW | ICW
LC | 126394903 | 040/006 | T2 DI TRNTY-MAPLE CREEK 40/6L RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172189 | T2 DI TRNTY-MAPLE CREEK 40/6L RPR GYWW | ICW
LC | 126394904 | 040/006 | T2 DI TRNTY-MPL CRK 40/6C RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172189 | T2 DI TRNTY-MAPLE CREEK 40/6L RPR GYWW | ICW
LC | 126394907 | 040/006 | T2 DI TRNTY-MPL CRK 40/6R RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172189 | T2 DI TRNTY-MAPLE CREEK 40/6L RPR GYWW | ICW
LC | 126395477 | 002/017 | T2 DI HAT CRK#1-PIT#1 002/017 RPR INSS | TABLEMTN | ETL.7020.INSL.CERA | 2023-06-17 | 2023-06-13 | 2023-08-16 | On-time | 2024-06-12 | 301 | 2023-12-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45857967 | T2 DI HAT CRK#1-PIT#1 2/17 RPR INSS | ICS
LC | 126394936 | :015/005 | T2 DI EAGLE ROCK-REDBUD :15/5 RPR SPLW | WILLITS | ETL.1480.INSL.CERA | 2023-06-17 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46216627 | T2 DI EAGLE ROCK-REDBUD :15/5 RPR SPLW | ICW
LC | 126395674 | 042/011 | T2 DI TRNTY-MPL CRK 42/11 RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-17 | 2023-06-13 | 2024-06-04 | On-time | 2024-06-12 | 8 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172193 | T2 DI TRNTY-MPL CRK 42/11 RPR GYWW | ICW
LC | 126394973 | 008/003B | T2 DI MPL CRK-HOOPA 008/003B RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-06-17 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46203533 | T2 DI MPL CRK-HOOPA 008/003B RPR GYWW | ICW
LC | 126395755 | 070/357A | T2 DI MLN-RND MTN #2 70/357A RPR SHIELD | TABLEMTN | ETL.6020.TOWR | 2023-06-17 | 2023-06-13 | 2024-01-22 | On-time | 2024-06-12 | 142 | 2024-06-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46083470 | T2 DI MLN-RND MTN #2 70/357A RPR SHIELD | ICS
LC | 126395006 | 037/720 | T2 DI HAT CRK#1 WSTWD 37/720 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-17 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514273 | T2 EI HAT CRK #1-WESTWOOD 37/719 RPL PL | 70Y
LC | 126396044 | 055/003 | T2 DI HMBLDT TRNTY 55/003L RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-17 | 2023-06-13 | 2024-04-27 | On-time | 2024-06-12 | 46 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171102 | T2 EI HMBLDT TRNTY 055/003R RPR JMPW | ICW
LC | 126395054 | 007/004 | T2 DI MAPLE CREEK-HOOPA 7/004 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46203528 | T2 DI MAPLE CREEK-HOOPA 7/004 RPR GYWW | ICW
LC | 126395123 | 067/339 | T2 DI MALIN-ROUND MTN #2 67/339 RPR ANCT | TABLEMTN | ETL.6020.TOWR | 2023-06-17 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Tower | Repair | 46257541 | T2 DI MALIN-ROUND MTN #2 67/339 RPR ANCT | ICQ
LC | 126396049 | 055/003 | T2 DI HMBLDT-TRNTY 55/003R RPR GYWW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-17 | 2023-06-13 | 2024-04-27 | On-time | 2024-06-12 | 46 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171102 | T2 EI HMBLDT TRNTY 055/003R RPR JMPW | ICW
LC | 126396061 | 005/110 | T2 DI CARIBOU-WESTWOOD 5/110 COTTER | TABLEMTN | ETL.6300.INSL.NCER | 2023-06-17 | 2023-06-13 | 2023-08-07 | On-time | 2024-06-12 | 310 | 2023-09-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45857971 | T2 DI CARIBOU-WESTWOOD 5/110 COTTER | ICW
LC | 126396066 | 030/160 | T2 DI EXCHEQUER-INDIAN FLT 30/160 UNBURY | FRESNO | ETL.8650.POLE.NWOD | 2023-06-17 | 2023-06-13 | 2023-12-12 | On-time | 2024-06-12 | 183 | 2024-06-13 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 45977756 | T2 DI EXCHEQUER-INDIAN FLT 30/160 UNBURY | ICQ
LC | 126396733 | 009/009 | T2 DI TRINITY-MAPLE CRK 009/009 RPR JUMW | EUREKA | ETL.8170.INSL.CERA | 2023-06-17 | 2023-06-13 | 2024-02-17 | On-time | 2024-06-12 | 116 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46079373 | T2 DI TRINITY-MAPLE CRK 009/009 RPR JUMW | ICW
LC | 126396823 | 014/293 | T2 DI CARIBOU-WESTWOOD 14/293 RPR GYWW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-17 | 2023-06-13 | 2024-03-18 | On-time | 2024-06-12 | 86 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091828 | T2 DI CARIBOU-WESTWOOD 14/293 RPR GYWW | ICW
LC | 126395275 | 045/004 | T2 DI TRNTY MPL CRK 45/004C RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506431 | T2 EI TRNTY MPL CRK 45/004R RPL POLE | 70Y
LC | 126396824 | 014/293 | T2 DI CARIBOU-WESTWOOD 14/293 RPR ANCW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-17 | 2023-06-13 | 2024-03-18 | On-time | 2024-06-12 | 86 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46091829 | T2 DI CARIBOU-WESTWOOD 14/293 RPR ANCW | ICW
LC | 126396948 | 070/355A | T2 DI MALIN-RND MTN #2 70/355A RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-06-17 | 2023-06-13 | 2023-08-29 | On-time | 2024-06-12 | 288 | 2023-09-14 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45860252 | T2 DI MALIN-RND MTN #2 70/355A RPR SHLS | ICS
LC | 126395346 | 045/002 | T2 DI TRINITY-MAPLE CREEK 45/2L RPR GYWW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096677 | T2 DI TRINITY-MAPLE CREEK 45/2L RPR GYWW | ICW
LC | 126395359 | 012/101 | T2 DI CABRLLO-SANTA YNEZ 12/101 RPL INSW | PISMOBCH | ETL.1200.INSL.NCER | 2023-06-17 | 2023-06-14 | 2024-06-21 | Late | 2024-06-13 | -8 | 2024-06-14 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35523059 | T2 DI CABRLLO-SANTA YNEZ 12/101 RPL INSW | 93I
LC | 126397901 | 047/009 | T2 DI TRNTY-MPL CRK 47/9 RPR JUMW | EUREKA | ETL.8170.INSL.NCER | 2023-06-17 | 2023-06-13 | 2023-11-01 | On-time | 2024-06-12 | 224 | 2023-09-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45854093 | T2 DI TRNTY-MPL CRK 47/009 RPR JUMW | ICW
LC | 126398374 | 015/001 | T2 DI CARIBOU-PLUMAS JCT 15/1 RPL HRDW | TABLEMTN | ETL.6290.POLE.WOOD | 2023-06-17 | 2023-06-13 | 2024-05-09 | On-time | 2024-06-12 | 34 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46091830 | T2 DI CARIBOU-PLUMAS JCT 15/1 RPL HRDW | ICW
LC | 126414127 | 000/001 | T2 DI BRDGVIL GRBRVIL 00/001 RPR GYWW | EUREKA | ETL.6220.POLE.NWOD | 2023-06-21 | 2023-06-13 | 2023-10-24 | On-time | 2024-06-12 | 232 | 2023-12-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45860430 | T2 DI BRDGVIL GRBRVIL 00/001 RPR GYWW | ICW
LC | 126417282 | 070/355 | T2 DI MALIN RND MTN#2 70/355 UNBURY | TABLEMTN | ETL.6020.TOWR | 2023-06-21 | 2023-06-13 | 2023-08-27 | On-time | 2024-06-12 | 290 | 2023-12-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45870660 | T2 DI MALIN RND MTN#2 70/355 UNBURY | ICS
LC | 126395698 | 000/008 | T2 DI ELECTRA-BELLOTA 0/8 RPL INSS | VICTOR | ETL.4670.INSL.CERA | 2023-06-17 | 2023-06-14 | 2024-06-17 | Late | 2024-06-13 | -4 | 2024-06-14 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35515631 | T2 DI ELECTRA-BELLOTA 0/8 RPL INSS | 93K
LC | 126417817 | 000/009 | T2 DI KESWICK-CASCDE 0/9 RPR CNDW | TABLEMTN | ETL.7260.INSL.NCER | 2023-06-21 | 2023-06-13 | 2024-06-06 | On-time | 2024-06-12 | 6 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46091821 | T2 DI KESWICK-CASCDE 0/9 RPR CNDW | ICW
LC | 126420660 | :011/068 | T2 DI EGLE RCK-CORTINA :11/68 RPR INSS | WILLITS | ETL.1470.INSL.NCER | 2023-06-21 | 2023-06-13 | 2024-05-14 | On-time | 2024-06-12 | 29 | 2024-06-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45861680 | T2 DI EGLE RCK-CORTINA :11/68 RPR INSS | ICS
LC | 126395858 | 002/022 | T2 DI HAT CRK#1-PIT#1 2/22 COTTER | TABLEMTN | ETL.7020.INSL.CERA | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45857969 | T2 DI HAT CRK#1-PIT#1 2/22 COTTER | ICS
LC | 126395993 | 044/010 | T2 DI TRINITY-MC 44/10 RPR POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46172197 | T2 DI TRINITY-MC 44/10 RPR POLE | ICW
LC | 126421002 | 070/353 | T2 DI MLN-RND MTN #2 70/353 UNBURY | TABLEMTN | ETL.6020.TOWR | 2023-06-21 | 2023-06-13 | 2023-10-09 | On-time | 2024-06-12 | 247 | 2023-12-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45870619 | T2 DI MLN-RND MTN #2 70/353 UNBURY | ICS
LC | 126421608 | 070/356 | T2 DI MLN-RND MTN #2 70/356 RPR INSS | TABLEMTN | ETL.6020.INSL.NCER | 2023-06-21 | 2023-06-13 | 2023-12-21 | On-time | 2024-06-12 | 174 | 2024-06-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46083469 | T2 DI MLN-RND MTN #2 70/356 RPR INSS | ICS
LC | 126396050 | 047/361 | T2 DI BRDGVL-CTTNWD 47/361 RPL INSS | TABLEMTN | ETL.1110.INSL.CERA | 2023-06-17 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509192 | T2 DI BRIDGEVILLE-CTTNWD RPL INSS 9 TWRS | 93K
LC | 126430727 | 028/240 | T2 DI BRIDGVLL-CTTONWD 28/240L RPR SHLDW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-06-22 | 2023-06-13 | 2023-08-26 | On-time | 2024-06-12 | 291 | 2023-09-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45881435 | T2 DI BRIDGVLL-CTTONWD 28/240L RPR SHLDW | ICW
LC | 126396064 | 043/012A | T2 DI TRNTY-MPL CRK 43/12A RPR GYWW | EUREKA | ETL.8170.POLE.NWOD | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46172194 | T2 DI TRNTY-MPL CRK 43/12A RPR GYWW | ICW
LC | 126430801 | 028/240 | T2 DI BRIDGVLL-CTTONWD 28/240R RPR ANCHR | TABLEMTN | ETL.1110.POLE.WDPS | 2023-06-22 | 2023-06-13 | 2024-01-19 | On-time | 2024-06-12 | 145 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46093355 | T2 DI BRIDGVLL-CTTONWD 28/240R RPR ANCHR | ICW
LC | 126430802 | 028/240 | T2 DI BRIDGVLL-CTTONWD 28/240R RPR GYWW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-06-22 | 2023-06-13 | 2024-01-19 | On-time | 2024-06-12 | 145 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46093354 | T2 DI BRIDGVLL-CTTONWD 28/240R RPR GYWW | ICW
LC | 126430868 | 070/357 | T2 DI MALIN RND MTN#2 70/357 COMPLETE | TABLEMTN | ETL.6020.TOWR | 2023-06-22 | 2023-06-13 | 2024-06-06 | On-time | 2024-06-12 | 6 | 2024-06-13 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46132331 | T2 DI MALIN RND MTN#2 70/357 UNBURY | ICQ
LC | 126433129 | 028/239 | T2 DI BRIDGEVLL-CTTNWD 28/239R RPL HRDW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-06-23 | 2023-06-13 | 2024-02-01 | On-time | 2024-06-12 | 132 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46093357 | T2 DI BRIDGEVLL-CTTNWD 28/239R RPL HRDW | ICW
LC | 126396276 | 057/004 | T2 DI HUMBOLDT-TRINITY 57/4 RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2023-06-17 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46096528 | T2 DI HUMBOLDT-TRINITY 57/4 RPR GYWW | ICW
LC | 126433134 | 028/239 | T2 DI BRIDGEVLL-CTTNWD 28/239L RPL HRDW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-06-23 | 2023-06-13 | 2024-02-01 | On-time | 2024-06-12 | 132 | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46093356 | T2 DI BRIDGEVLL-CTTNWD 28/239L RPL HRDW | ICW
LC | 126396360 | 040/003 | T2 DI TRNTY-MPL CRK 40/003L RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506727 | T2 DI TRNTY-MPL CRK 40/003L RPL POLE | 70Y
LC | 126396364 | 040/003 | T2 DI TRNTY-MPL CRK 40/003C RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506727 | T2 DI TRNTY-MPL CRK 40/003L RPL POLE | 70Y
LC | 126396367 | 040/003 | T2 DI TRNTY-MPL CRK 40/003R RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506727 | T2 DI TRNTY-MPL CRK 40/003L RPL POLE | 70Y
LC | 126460219 | 071/358 | T2 DI MALIN RND MTN#2 71/358 RPR ANCS | TABLEMTN | ETL.6020.TOWR | 2023-06-27 | 2023-06-13 | 2023-08-14 | On-time | 2024-06-12 | 303 | 2023-12-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45870661 | T2 DI MALIN RND MTN#2 71/358 RPR ANCS | ICS
LC | 126396470 | 044/349 | T2 DI BRDGVIL CTTNWD 44/349 RPL HRDT | TABLEMTN | ETL.1110.TOWR | 2023-06-17 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46125148 | T2 DI BRDGVIL CTTNWD 44/349 RPL HRDT | ICQ
LC | 126396615 | 019/000 | T2 DI PHILO JCT ELK 19/000 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-06-17 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35531140 | T2 DI PHILO JCT ELK 19/000 RPL POLE | 70Y
LC | 126396623 | 020/002 | T2 DI TRNTY-MPLE CRK 20/2R RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35502988 | T2 DI TRNTY-MPLE CRK 20/2L RPL POLE | 70Y
LC | 126396625 | 020/002 | T2 DI TRNTY-MPLE CRK 20/2C RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35502988 | T2 DI TRNTY-MPLE CRK 20/2L RPL POLE | 70Y
LC | 126396627 | 020/002 | T2 DI TRNTY-MPLE CRK 20/2L RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35502988 | T2 DI TRNTY-MPLE CRK 20/2L RPL POLE | 70Y
LC | 126396660 | ;003/002 | T2 DI CARIBOU #2 ;3/2 RPR INSW | TABLEMTN | ETL.6280.INSL.CERA | 2023-06-17 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46091833 | T2 DI CARIBOU #2 ;3/2 RPR INSW | ICW
LC | 126396663 | ;003/002 | T2 DI CARIBOU #2 3/2 RPL HRDW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-06-17 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46091834 | T2 DI CARIBOU #2 3/2 RPL HRDW | ICW
LC | 126460970 | 069/348A | T2 DI MALIN RND MTN#2 69/348A RPR SHLS | TABLEMTN | ETL.6020.TOWR | 2023-06-27 | 2023-06-13 | 2024-01-22 | On-time | 2024-06-12 | 142 | 2024-06-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46083467 | T2 DI MALIN RND MTN#2 69/348A RPR SHLS | ICS
LC | 126465260 | 070/352 | T2 DI MALIN RND MTN#2 70/352 UNBURY | TABLEMTN | ETL.6020.TOWR | 2023-06-27 | 2023-06-13 | 2023-08-27 | On-time | 2024-06-12 | 290 | 2023-12-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45870617 | T2 DI MALIN RND MTN#2 70/352 UNBURY | ICS
LC | 126367353 | 016/075 | T2 EI FULTON-PUEBLO 16/075 RMV VEG | LAKEVLLE | ETL.1600.TOWR | 2023-06-14 | 2023-06-14 | 2024-05-09 | On-time | 2024-06-13 | 35 | 2024-06-14 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126371646 | :014/005 | T2 EI EAGLE ROCK-CORTINA :014/005 RPL PL | WILLITS | ETL.1470.POLE.WOOD | 2023-06-14 | 2023-06-14 | 2024-05-15 | On-time | 2024-06-13 | 29 | 2024-06-14 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35487308 | T2 EI EAGLE ROCK-CORTINA :014/005 RPL PL | 70Y
LC | 126396901 | 043/344 | T2 DI BRDGVIL CTTNWD 43/344 INS COTTER | TABLEMTN | ETL.1110.INSL.CERA | 2023-06-17 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46088643 | T2 DI BRDGVIL CTTNWD 43/344 INS COTTER | ICS
LC | 126372827 | 008/175 | T2 EI KILARC-DESCHUTES 08/175 RPR GYWW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-14 | 2024-02-13 | On-time | 2024-06-13 | 121 | 2024-06-14 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088618 | T2 EI KILARC-DESCHUTES 08/175 RPR GYWW | ICW
LC | 126396963 | 039/760 | T2 DI HAT CRK#1 WSTWD 39/760 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-17 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514277 | T2 EI HAT CREEK #1-WSTWD 39/756 RPL POLE | 70Y
LC | 126396979 | :012/069 | T2NT DI EGL RCK-REDBUD :012/069 RMV NEST | WILLITS | ETL.1480.TOWR | 2023-06-17 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46193829 | T2NT DI EGL RCK-REDBUD :012/069 RMV NEST | ICS
LC | 126372847 | 008/171 | T2 EI KILARC-DESCHUTES 08/171 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-14 | 2023-06-14 | 2024-04-08 | On-time | 2024-06-13 | 66 | 2024-06-14 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515675 | T2 EI KILARC-DESCHUTES 08/171 RPL POLE | 70Y
LC | 126397079 | 057/006 | T2 DI HUMBOLDT-TRIN 57/6R GO95 RPL | EUREKA | ETL.1820.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35506775 | T2 DI HUMBOLDT-TRIN 57/6L GO95 RPL | 93G
LC | 126374887 | 001/013 | T2 OLEUM-NRTH TR-CHRISTIE 1/13 RPR STRT | CONCORD | ETL.3180.TOWR | 2023-06-14 | 2023-06-14 | 2023-10-17 | On-time | 2024-06-13 | 240 | 2023-12-14 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45895299 | T2 OLEUM-NRTH TR-CHRISTIE 1/13 RPR STRT | ICQ
LC | 126397114 | 021/000 | T2 EI TRINITY-MAPLE CREEK 21/0C RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-17 |  | Late | 2024-06-16 |  | 2024-06-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503523 | T2 DI TRINITY-MAPLE CRK 21/0L RPL POLE | 70Y
LC | 126397141 | 057/006 | T2 DI HUMBOLDT-TRIN 57/6C GO95 RPL | EUREKA | ETL.1820.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35506775 | T2 DI HUMBOLDT-TRIN 57/6L GO95 RPL | 93G
LC | 126397145 | 057/006 | T2 DI HUMBOLDT-TRIN 57/6L GO95 RPL | EUREKA | ETL.1820.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 401T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35506775 | T2 DI HUMBOLDT-TRIN 57/6L GO95 RPL | 93G
LC | 126375677 | 030/000 | T2 COALINGA #1-SAN MIGUEL 30/00 RPR GYWS | PISMOBCH | ETL.8580.TOWR | 2023-06-14 | 2023-06-14 | 2024-02-24 | On-time | 2024-06-13 | 110 | 2024-06-14 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46088504 | T2 COALINGA #1-SAN MIGUEL 30/00 RPR GYWS | ICS
LC | 126377027 | 009/070 | T2 EI ROCK CREEK-POE 9/70 RMV VEG | TABLEMTN | ETL.5630.TOWR | 2023-06-15 | 2023-06-14 | 2024-01-31 | On-time | 2024-06-13 | 134 | 2024-06-14 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Trim
LC | 126377072 | 000/007 | T2 EI PT#1-HT CRK#2-BRNY 0/7 RPL INSS | TABLEMTN | ETL.7040.INSL.CERA | 2023-06-15 | 2023-06-14 | 2024-05-15 | On-time | 2024-06-13 | 29 | 2024-06-14 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509000 | T2 EI PT#1-HT CRK#2-BRNY 0/7 RPL INSS | 93K
LC | 126397499 | 043/001 | T2 DI TRNTY-MAPLE CREEK 43/1L RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506773 | T2 DI TRNTY-MAPLE CREEK 43/1L RPL STRW | 70Y
LC | 126397551 | 026/224 | T2 DI BRDGVL-CTNWD 26/224 RPL INSS | TABLEMTN | ETL.1110.INSL | 2023-06-17 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509192 | T2 DI BRIDGEVILLE-CTTNWD RPL INSS 9 TWRS | 93K
LC | 126397558 | 001/074 | T2 DI SPAULDNG-SUMMIT 1/74 RPL HRDW | SACTO | ETL.8060.POLE.WOOD | 2023-06-17 | 2023-06-15 | 2024-06-26 | Late | 2024-06-14 | -12 | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46127496 | T2 DI SPAULDNG-SUMMIT 1/74 RPL HRDW | ICW
LC | 126397571 | 043/001 | T2 DI TRNTY-MAPLE CREEK 43/1C RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506773 | T2 DI TRNTY-MAPLE CREEK 43/1L RPL STRW | 70Y
LC | 126397572 | 043/001 | T2 DI TRNTY-MAPLE CREEK 43/1R RPL STRW | EUREKA | ETL.8170.POLE.WDPS | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506773 | T2 DI TRNTY-MAPLE CREEK 43/1L RPL STRW | 70Y
LC | 126397576 | 041/002 | T2 DI TRNTY-MAPLE CREEK 41/2 RPL STRW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506764 | T2 DI TRNTY-MAPLE CREEK 41/2 RPL STRW | 70Y
LC | 126397617 | ;005/009 | T2 DI CARIBOU #2 ;005/009 RPR SPLICE | TABLEMTN | ETL.6280.INSL.NCER | 2023-06-17 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46091867 | T2 DI CARIBOU #2 5/9 RPR SPLICE | ICW
LC | 126377073 | 000/002 | T2 EI PT#1-HT CRK#2-BRNY 0/2 RPL INSS | TABLEMTN | ETL.7040.INSL.CERA | 2023-06-15 | 2023-06-14 | 2024-05-14 | On-time | 2024-06-13 | 30 | 2024-06-14 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509000 | T2 EI PT#1-HT CRK#2-BRNY 0/7 RPL INSS | 93K
LC | 126397765 | ;000/025 | T2 DI CARIBOU #2 ;000/025 RPR SPLICE | TABLEMTN | ETL.6280.INSL.NCER | 2023-06-17 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46091865 | T2 DI CARIBOU #2 0/25 RPR SPLICE | ICW
LC | 126397791 | 002/045 | T2 DI DEL MONTE-VIEJO 2/45 RPL HRDD | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-17 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46081620 | T2 DI DEL MONTE-VIEJO 2/45 RPL HRDD | ICW
LC | 126397792 | 002/045 | T2 DI DEL MONTE-VIEJO 2/45 GO95 CLEAR | MOSSLNDG | ETL.6710.INSL.CERA | 2023-06-17 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 401 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35515353 | T2 DI DEL MONTE-VIEJO 2/045 RPL INSW | 93I
LC | 126387060 | 009/054 | T2 DI VACA-PRKWY 009/054 RPR STRT | SACTO | ETL.5850.TOWR | 2023-06-16 | 2023-06-14 | 2024-06-04 | On-time | 2024-06-13 | 9 | 2024-06-14 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46132843 | T2 DI VACA-PRKWY 009/054 RPR STRT | ICQ
LC | 126387529 | 011/008 | T2 DI CRBOU-PLMS JCT 011/008 RPR GYWW | TABLEMTN | ETL.6290.POLE.WOOD | 2023-06-16 | 2023-06-14 | 2024-05-07 | On-time | 2024-06-13 | 37 | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091839 | T2 DI CRBOU-PLMS JCT 011/008 RPR GYWW | ICW
LC | 126389182 | 000/002 | T2 DI BALCH-SANGR 000/002 UNBURY | FRESNO | ETL.1050.TOWR | 2023-06-16 | 2023-06-14 | 2024-01-29 | On-time | 2024-06-13 | 136 | 2024-06-14 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46124966 | T2 DI BALCH-SANGR 000/002 UNBURY | ICQ
LC | 126391533 | 004/020 | T2 DI PTTSBRG-EASTSHORE 4/20 RPL HRDT | CONCORD | ETL.5462.TOWR | 2023-06-16 | 2023-06-14 | 2024-02-09 | On-time | 2024-06-13 | 125 | 2024-06-14 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46127801 | T2 DI PTTSBRG-EASTSHORE 4/20 RPL HRDT | ICQ
LC | 126397962 | 021/450 | T2 DI KILARC-DESCHUTES 021/450 COMPLETE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126397963 | 021/450 | T2 DI KILARC-DESCHUTES 021/450 RPL POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-17 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515346 | T2 DI KILARC-DESCHUTES 021/450 RPL POLE | 70Y
LC | 126393765 | 086/603B | T2 DI BRDGVLL-CTTNWD 86/603B RPR ANCW | EUREKA | ETL.1110.POLE.WOOD | 2023-06-16 | 2023-06-14 | 2024-03-27 | On-time | 2024-06-13 | 78 | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46172023 | T2 DI BRDGVLL-CTTNWD 86/603B RPR ANCW | ICW
LC | 126394298 | 002/021 | T2 DI HAAS-MC CALL 2/21 COMPLETE | FRESNO | ETL.4850.TOWR | 2023-06-16 | 2023-06-14 | 2024-05-07 | On-time | 2024-06-13 | 37 | 2024-06-14 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46080582 | T2 DI HAAS-MC CALL 002/021 RPR SHLS | ICS
LC | 126394393 | 006/046 | T2 DI ROCK CREEK-POE 006/046 RPL INSS | TABLEMTN | ETL.5630.INSL.CERA | 2023-06-16 | 2023-06-14 | 2024-02-24 | On-time | 2024-06-13 | 110 | 2024-06-14 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509199 | T2 DI ROCK CREEK-POE :5/33 RPLC INSS | 93K
LC | 126394933 | 004/038 | T2 DI ROCK CREEK-POE 4/38 RPL INSS | TABLEMTN | ETL.5630.INSL | 2023-06-17 | 2023-06-14 | 2024-02-26 | On-time | 2024-06-13 | 108 | 2024-06-14 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509199 | T2 DI ROCK CREEK-POE :5/33 RPLC INSS | 93K
LC | 126395140 | 047/364 | T2 DI BRDGVLE-CTTNWD 47/364 RPR INSS | TABLEMTN | ETL.1110.INSL.CERA | 2023-06-17 | 2023-06-14 | 2023-08-28 | On-time | 2024-06-13 | 290 | 2023-09-14 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45866320 | T2 DI BRDGVLE-CTTNWD 47/364 RPR INSS | ICS
LC | 126395141 | 047/364 | T2 DI BRDGVLE-CTNWD 47/364 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-06-17 | 2023-06-14 | 2023-08-28 | On-time | 2024-06-13 | 290 | 2023-09-14 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45866321 | T2 DI BRDGVLE-CTNWD 47/364 RPR OPGW | ICS
LC | 126398394 | 035/283 | T2 EI BRDGVLLE-CTTNWD 35/283 RPL INSW | TABLEMTN | ETL.1110.INSL.CERA | 2023-06-17 | 2023-06-17 |  | Late | 2024-06-16 |  | 2024-06-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46093347 | T2 EI BRDGVLLE-CTTNWD 35/283 RPL INSW | ICW
LC | 126395291 | 004/034 | T2 DI BCKS CRK RCK CRK CRA 4/34 RPL INSS | TABLEMTN | ETL.4430.INSL.CERA | 2023-06-17 | 2023-06-14 | 2024-01-18 | On-time | 2024-06-13 | 147 | 2024-06-14 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672630 | T2 DI BUCKS CRK-ROCK CRK 02/27 RPL INSS | 93K
LC | 126399153 | 035/683 | T2 EI HAT CREEK #1-WSTWD 35/683 RPR HRDW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-17 | 2023-06-17 |  | Late | 2024-06-16 |  | 2024-06-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46091880 | T2 EI HAT CREEK #1-WSTWD 35/683 RPR HRDW | ICW
LC | 126399156 | 038/735 | T2 EI HAT CRK #1-WESTWD 38/735 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-17 | 2023-06-17 |  | Late | 2024-06-16 |  | 2024-06-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514274 | T2 DI HAT CREEK #1-WSTWD 38/730 RPL STRW | 70Y
LC | 126399214 | 038/736 | T2 EI HAT CRK #1-WESTWOOD 38/736 RPL PL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-17 | 2023-06-17 |  | Late | 2024-06-16 |  | 2024-06-17 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518531 | T2 EI HAT CREEK #1-WESTWOD 36/691 RPL PL | 70Y
LC | 126395367 | 008/060 | T2 DI ROCK CREEK-POE 8/60 RPL INSS | TABLEMTN | ETL.5630.INSL.NCER | 2023-06-17 | 2023-06-14 | 2024-02-24 | On-time | 2024-06-13 | 110 | 2024-06-14 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35519937 | T2 DI ROCK CREEK-POE RPL INSS 2 TWRS | 93K
LC | 126396263 | 014/013 | T2 DI CARIBOU-PLUMAS JCT 14/13 RPR GYWW | TABLEMTN | ETL.6290.POLE.WOOD | 2023-06-17 | 2023-06-14 | 2024-05-09 | On-time | 2024-06-13 | 35 | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091861 | T2 DI CARIBOU-PLUMAS JCT 14/13 RPR GYWW | ICW
LC | 126401597 | 021/103 | T2 EI EAGLE ROCK-CORTINA 21/103 CNCL | WILLITS | ETL.1470.INSL.CERA | 2023-06-19 | 2023-06-19 |  | Late | 2024-06-18 |  | 2024-06-19 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46176324 | T2 EI EAGLE ROCK-CORTINA 21/103 COTTER | ICS
LC | 126401721 | 004/116 | T2 EI HAMILTN BRNCH-CHSTR 4/116 RPR GYWW | TABLEMTN | ETL.7000.POLE.NWOD | 2023-06-19 | 2023-06-19 |  | Late | 2024-06-18 |  | 2024-06-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091883 | T2 EI HAMILTN BRNCH-CHSTR 4/116 RPR GYWW | ICW
LC | 126401836 | 026/227 | T2 EI BRIDGE-COTTON 26/227L RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-06-19 | 2023-06-19 |  | Late | 2024-06-18 |  | 2024-06-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487484 | T2 EI BRIDGE-COTTON 26/227L RPL STRW | 70Y
LC | 126401979 | 033/269 | T2 EI BRDGVLLE-CTTNWD 33/269 RPL INSW | TABLEMTN | ETL.1110.INSL.CERA | 2023-06-19 | 2023-06-19 |  | Late | 2024-06-18 |  | 2024-06-19 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35521270 | T2 EI BRDGVLLE-CTTNWD 33/269 RPL INSW | 93I
LC | 126402135 | 067/002B | T2 HUMBOLDT-TRINITY 67/2B RPR INSW | EUREKA | ETL.1820.INSL.NCER | 2023-06-19 | 2023-06-19 |  | Late | 2024-06-18 |  | 2023-09-19 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46096536 | T2 HUMBOLDT-TRINITY 67/2B RPR INSW | ICW
LC | 126402490 | 004/114 | T2 EI HAMILTN BRNCH-CHSTR 4/114 RPR CNDW | TABLEMTN | ETL.7000.INSL.CERA | 2023-06-19 | 2023-06-19 |  | Late | 2024-06-18 |  | 2023-12-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46091882 | T2 EI HAMILTN BRNCH-CHSTR 4/114 RPR CNDW | ICW
LC | 126396272 | 057/004 | T2 DI HUMBOLDT-TRINITY 57/4 RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-06-17 | 2023-06-14 | 2024-04-29 | On-time | 2024-06-13 | 45 | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096528 | T2 DI HUMBOLDT-TRINITY 57/4 RPR GYWW | ICW
LC | 126403037 | 053/1040 | T2 EI HAT CRK #1-WESTWOOD 53/1040 RPL PL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-19 | 2023-06-19 |  | Late | 2024-06-18 |  | 2024-06-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35551999 | T2 DI HAT CRK #1-WSTWD 53/1041 RPL STRW | 70Y
LC | 126396875 | 008/082A | T2 DI BRIDGEVL-CTTNWD 008/082A RPR ADSS | TABLEMTN | ETL.1110.POLE.WOOD | 2023-06-17 | 2023-06-14 | 2023-07-30 | On-time | 2024-06-13 | 319 | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45881434 | T2 DI BRIDGEVILL-COTTONWD 8/82A RPR ADSS | ICW
LC | 126403705 | :017/002 | T2 EI EGL RCK-CRTN :17/2 RPR STRW | WILLITS | ETL.1470.POLE.WOOD | 2023-06-19 | 2023-06-19 |  | Late | 2024-06-18 |  | 2024-06-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46176325 | T2 EI EAGLE ROCK-CORTINA :017/002 RPR PL | ICW
LC | 126397089 | 004/028 | T2 DI PITTSBURG-CLAYTON #1 4/28 RPL INSS | CONCORD | ETL.3280.INSL | 2023-06-17 | 2023-06-14 | 2024-06-11 | On-time | 2024-06-13 | 2 | 2024-06-14 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671639 | T2 DI PITTSBURG-CLAYTON #1 4/28 RPL INSS | 93K
LC | 126397762 | 047/366 | T2 DI BRDGVL-CTNWD 47/366 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-06-17 | 2023-06-14 | 2023-08-28 | On-time | 2024-06-13 | 290 | 2023-09-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 45866333 | T2 DI BRDGVL-CTNWD 47/366 RPR OPGW | ICW
LC | 126397983 | 001/054 | T2 DI SPLDNG-SMMT 001/054 RPR GYWW | SACTO | ETL.8060.POLE.NWOD | 2023-06-17 | 2023-06-14 | 2023-06-26 | On-time | 2024-06-13 | 353 | 2023-09-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45856878 | T2 DI SPLDNG-SMMT 001/054 RPR GYWW | ICW
LC | 126397986 | 004/092 | T2 DI CARIBOU-WESTWOOD 004/092 COTTER | TABLEMTN | ETL.6300.INSL.NCER | 2023-06-17 | 2023-06-14 | 2023-08-07 | On-time | 2024-06-13 | 311 | 2023-09-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45857972 | T2 DI CARIBOU-WESTWOOD 004/092 COTTER | ICW
LC | 126398269 | 007/016 | T2 DI CARIBOU-PLUMAS JCT 7/16 RPL HRDW | TABLEMTN | ETL.6290.POLE.WOOD | 2023-06-17 | 2023-06-14 | 2024-05-07 | On-time | 2024-06-13 | 37 | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46091836 | T2 DI CARIBOU-PLUMAS JCT 7/16 RPL HRDW | ICW
LC | 126414768 | 007/019 | T2 DI CARIBOU PLUMAS JT 07/019 RPR STRW | TABLEMTN | ETL.6290.POLE.WOOD | 2023-06-21 | 2023-06-14 | 2024-05-07 | On-time | 2024-06-13 | 37 | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091837 | T2 DI CARIBOU PLUMAS JT 07/019 RPR STRW | ICW
LC | 126415908 | 006/013 | T2 DI CARIBOU PLUMAS JT 6/13 RPL ANCW | TABLEMTN | ETL.6290.POLE.WOOD | 2023-06-21 | 2023-06-14 | 2024-05-07 | On-time | 2024-06-13 | 37 | 2024-06-14 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35518835 | T2 DI CARIBOU PLUMAS JT 06/013 RPL ANCW | 93E
LC | 126418479 | 014/010 | T2 DI CARIBOU PLUMAS JT 14/010 RPR GYWW | TABLEMTN | ETL.6290.POLE.WOOD | 2023-06-21 | 2023-06-14 | 2024-05-09 | On-time | 2024-06-13 | 35 | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091860 | T2 DI CARIBOU PLUMAS JT 14/010 RPR GYWW | ICW
LC | 126404437 | 022/154C | T2 EI CARIBOU-TABLE MTN 22/154C RMV VEG | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-19 | 2023-06-19 |  | Late | 2024-06-18 |  | 2024-06-19 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126423790 | 046/358 | T2 DI BRDGVLLE-CTTNWD 46/358 COTTER | TABLEMTN | ETL.1110.INSL.CERA | 2023-06-22 | 2023-06-14 | 2023-10-30 | On-time | 2024-06-13 | 227 | 2023-12-14 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45866330 | T2 DI BRDGVLLE-CTTNWD 46/358 COTTER | ICS
LC | 126430648 | 073/372 | T2 DI MLN-RND MTN #2 73/372 RPR JUMPS | TABLEMTN | ETL.6020.INSL.NCER | 2023-06-22 | 2023-06-14 | 2023-12-21 | On-time | 2024-06-13 | 175 | 2024-06-14 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45866378 | T2 DI MLN-RND MTN #2 73/372 RPR JUMPS | ICS
LC | 126430947 | 046/359 | T2 DI BRDGVL-CTNWD 46/359 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-06-22 | 2023-06-14 | 2023-10-30 | On-time | 2024-06-13 | 227 | 2023-09-14 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45866279 | T2 DI BRDGVL-CTNWD 46/359 RPR OPGW | ICS
LC | 126406277 | 042/000 | T2 DI TRINITY-MAPLE CRK 042/00L RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-20 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506765 | T2 DI TRINITY-MAPLE CRK 042/00L RPL POLE | 70Y
LC | 126430986 | 012/011 | T2 DI CARIBOU-PLUMAS JCT 12/11 RPL STRW | TABLEMTN | ETL.6290.POLE.WOOD | 2023-06-22 | 2023-06-14 | 2024-05-08 | On-time | 2024-06-13 | 36 | 2023-12-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518839 | T2 DI CRBOU PLUMAS JT 11/014 RPL POLE | 70Y
LC | 126430987 | 011/007 | T2 DI CARIBOU-PLUMAS JCT 11/7 RPR GYWW | TABLEMTN | ETL.6290.POLE.WOOD | 2023-06-22 | 2023-06-14 | 2024-05-07 | On-time | 2024-06-13 | 37 | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091838 | T2 DI CARIBOU-PLUMAS JCT 11/7 RPR GYWW | ICW
LC | 126406847 | 042/000 | T2 DI TRINITY-MAPLE CRK 042/00C RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-20 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506765 | T2 DI TRINITY-MAPLE CRK 042/00L RPL POLE | 70Y
LC | 126407010 | 042/000 | T2 DI TRINITY-MAPLE CRK 042/00R RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-20 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506765 | T2 DI TRINITY-MAPLE CRK 042/00L RPL POLE | 70Y
LC | 126407019 | :016/006 | T2 DI EGL RK RDBD :016/006 RPR ANCW | WILLITS | ETL.1480.POLE.WOOD | 2023-06-20 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46214267 | T2 DI EGL RK RDBD :016/006 RPR ANCW | ICW
LC | 126432742 | 000/001 | T2 DI MNTCLLO PH TAP 000/001 RPR GYWW | LAKEVLLE | ETL.1602.POLE.WOOD | 2023-06-23 | 2023-06-14 | 2023-08-18 | On-time | 2024-06-13 | 300 | 2023-12-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45881124 | T2 DI MNTCLLO PH TAP 000/001 RPR GYWW | ICW
LC | 126407325 | 004/001 | T2 WV HUMBOLDT-MAPLE CRK 4/1 RPL INSW | EUREKA | ETL.7130.INSL.NCER | 2023-06-20 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 508 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31617163 | T2 DI HUMBOLDT-MAPLE CRK 3/005 RPL INSW | 93I
LC | 126465764 | 001/043 | T2 DI SPALDING-SUMMIT 1/43 RPR JMPW | SACTO | ETL.8060.INSL.NCER | 2023-06-27 | 2023-06-14 | 2023-10-04 | On-time | 2024-06-13 | 253 | 2023-12-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45872461 | T2 DI SPALDING-SUMMIT 1/43 RPR JMPW | ICW
LC | 126585457 | 008/062 | T2 DI ROCK CREEK POE 8/62 RPL INSS | TABLEMTN | ETL.5630.INSL.CERA | 2023-07-14 | 2023-06-14 | 2024-02-24 | On-time | 2024-06-13 | 110 | 2024-06-14 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509199 | T2 DI ROCK CREEK-POE :5/33 RPLC INSS | 93K
LC | 126408974 | 002/009 | T2 BRCBRG JCT-MRPSA TAP 2/9 RPL STRW | FRESNO | ETL.8651.POLE.WOOD | 2023-06-20 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525548 | T2NT EI BRICE JCT-MARIPOSA 2/2 RPL POLE | 70Y
LC | 126410704 | :016/005 | T2 EI EGLE ROCK-CRTINA :16/5 COTTER | WILLITS | ETL.1470.INSL.NCER | 2023-06-20 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45882390 | T2 EI EGLE ROCK-CRTINA :16/5 COTTER KEY | ICW
LC | 126378072 | 030/245 | T2 CRESTA-RIO OSO_030/245 RMV NEST | TABLEMTN | ETL.4590.TOWR | 2023-06-15 | 2023-06-15 | 2024-02-22 | On-time | 2024-06-14 | 113 | 2024-06-15 | 628 | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46083538 | T2 CRESTA-RIO OSO_030/245 RMV NEST | ICS
LC | 126378079 | 027/174 | T2 EI POE-RIO OSO 027/174 RMV NEST | TABLEMTN | ETL.5540.TOWR | 2023-06-15 | 2023-06-15 | 2024-01-30 | On-time | 2024-06-14 | 136 | 2024-06-15 | 628 | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46083537 | T2 EI POE-RIO OSO 027/174 RMV NEST | ICS
LC | 126412105 | 000/015 | T2 WV HALSEY-PLACER 0/15 COA | SACTO | ETL.6990.POLE.WOOD | 2023-06-20 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | ADSS - Wood | Repair
LC | 126378122 | 109/007 | T2 EI HUMBOLDT-BRIDGEVILLE 109/7L COTTER | EUREKA | ETL.1810.INSL.NCER | 2023-06-15 | 2023-06-15 | 2023-11-21 | On-time | 2024-06-14 | 206 | 2024-06-15 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45881481 | T2 EI HUMBOLDT-BRIDGEVILLE 109/7L COTTER | ICS
LC | 126378149 | 023/186 | T2 CRESTA-RIO OSO 023/186 RMV NEST | TABLEMTN | ETL.4590.TOWR | 2023-06-15 | 2023-06-15 | 2024-02-23 | On-time | 2024-06-14 | 112 | 2024-06-15 | 628 | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46083536 | T2 CRESTA-RIO OSO 023/186 RMV NEST | ICS
LC | 126378985 | 040/002 | T2 WV ELK-GUALALA 040/002 RPL INSW | WILLITS | ETL.8410.INSL.CERA | 2023-06-15 | 2023-06-15 | 2024-01-11 | On-time | 2024-06-14 | 155 | 2024-06-15 | 508 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31613963 | T2 DI ELK-GUALALA 37/9 RPL STRW | 70Y
LC | 126378991 | 006/068 | T2 EI IGNCIO-BLNS #1 06/68 RPR GYWW | LAKEVLLE | ETL.7140.POLE.NWOD | 2023-06-15 | 2023-06-15 | 2023-09-18 | On-time | 2024-06-14 | 270 | 2023-12-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45881125 | T2 EI IGNCIO-BLNS #1 06/68 RPR GYWW | ICW
LC | 126412988 | 004/039 | T2 EI ROCK CREEK-POE 004/039 RPR STRT | TABLEMTN | ETL.5630.TOWR | 2023-06-20 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46132647 | T2 EI ROCK CREEK-POE 004/039 RPR STRT | ICQ
LC | 126413074 | 032/267 | T2 EI BRDGEVLE-COTONWOD 032/267 REFRAME | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-20 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35521267 | T2 EI BRDGEVLE-COTONWOD 032/267 REFRAME | 93E
LC | 126380606 | 001/010 | T2 EI OLEUM-NTH TWR-CHRST 1/10 RPR STRT | CONCORD | ETL.3180.TOWR | 2023-06-15 | 2023-06-15 | 2023-08-04 | On-time | 2024-06-14 | 315 | 2023-09-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45906565 | T2 EI OLEUM-NTH TWR-CHRST 1/10 RPR STRT | ICQ
LC | 126413272 | 022/155 | T2 EI BUTT VLY-TBL MT 22/155 RMV NEST | TABLEMTN | ETL.4440.POLE.STPS | 2023-06-20 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46088166 | T2 EI BUTT VLY-TBL MT 22/155 RMV NEST | ICS
LC | 126382414 | :015/019 | T2 EI EAGLE ROCK-CORTINA :015/019 RPL PL | WILLITS | ETL.1470.POLE.WOOD | 2023-06-15 | 2023-06-15 | 2024-05-14 | On-time | 2024-06-14 | 31 | 2024-06-15 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35487310 | T2 EI EGLE RCK-CORTINA :015/018 RPL PL | 70Y
LC | 126413813 | 000/001 | T2 COLGATE-ALLEGHANY 00/01 RPL POLE | SACTO | ETL.6470.POLE.WOOD | 2023-06-21 | 2023-06-21 | 2024-06-21 | Late | 2024-06-20 | -1 | 2024-06-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508685 | T2 COLGATE-ALLEGHANY 00/01 RPL POLE | 70Y
LC | 126382457 | :015/018 | T2 EI EGLE RCK-CORTINA :015/018 RPL PL | WILLITS | ETL.1470.POLE.WOOD | 2023-06-15 | 2023-06-15 | 2024-05-14 | On-time | 2024-06-14 | 31 | 2024-06-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35487310 | T2 EI EGLE RCK-CORTINA :015/018 RPL PL | 70Y
LC | 126414105 | 005/004 | T2 EI LAYTONVILLE-COVELO 5/4C RPL POLE | WILLITS | ETL.7390.POLE.WDPS | 2023-06-21 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491306 | T2 DI LAYTONVILLE-COVELO 5/4R RPL POLE | 70Y
LC | 126383129 | 109/002 | T2 EI HUMBOLDT-BRIDGEVILLE 109/2 COTTER | EUREKA | ETL.1810.POLE.STPS | 2023-06-15 | 2023-06-15 | 2024-02-27 | On-time | 2024-06-14 | 108 | 2024-06-15 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46096230 | T2 EI HUMBOLDT-BRIDGEVILLE 109/2 COTTER | ICS
LC | 126414559 | 043/003 | T2 DI TRINITY-MAPLE CRK 043/003 RPL POLE | EUREKA | ETL.8170.POLE.WOOD | 2023-06-21 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506291 | T2 DI TRINITY-MAPLE CRK 043/003 RPL POLE | 70Y
LC | 126383274 | 032/263 | T2 EI BRDGVL-CTNWD 32/263 COTTER | TABLEMTN | ETL.1110.INSL.CERA | 2023-06-15 | 2023-06-15 | 2023-08-11 | On-time | 2024-06-14 | 308 | 2023-09-15 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45881436 | T2 EI BRDGVL-CTNWD 32/263 COTTER | ICS
LC | 126383335 | 055/004 | T2 EI ELK-GUALALA 055/004 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-06-15 | 2023-06-15 | 2024-01-18 | On-time | 2024-06-14 | 148 | 2024-06-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35495165 | T2 EI ELK-GUALALA 055/004 RPL POLE | 70Y
LC | 126415313 | 001/008 | T2 DI HAT CREEK#1 PIT#1 01/008 RPL INSS | TABLEMTN | ETL.7020.INSL.CERA | 2023-06-21 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513068 | T2 EI HAT CREEK#1-PIT#1 RPL INSS 3 TWRS | 93K
LC | 126383853 | 001/013 | T2 CHRST-FRNKLN #2 1/13 GO95 CLR | CONCORD | ETL.6360.POLE.WOOD | 2023-06-15 | 2023-06-15 | 2024-05-12 | On-time | 2024-06-14 | 33 | 2024-06-15 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31655019 | T2 CHRST-FRNKLN #2 1/13 GO95 CLR | 93G
LC | 126383904 | 109/000 | T2 EI HUMBOLDT-BRIDGEVLLE 109/0 RPR GYWW | EUREKA | ETL.1810.POLE.WDPS | 2023-06-15 | 2023-06-15 | 2024-02-27 | On-time | 2024-06-14 | 108 | 2024-06-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096229 | T2 EI HUMBOLDT-BRIDGEVLLE 109/0 RPR GYWW | ICW
LC | 126415880 | 042/001 | T2 DI TRINITY-MAPLE CREEK 42/1R RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-06-21 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096670 | T2 DI TRINITY-MAPLE CREEK 42/1R RPR GYWW | ICW
LC | 126415883 | 042/001 | T2 DI TRINITY-MAPLE CREEK 42/1L RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-06-21 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096670 | T2 DI TRINITY-MAPLE CREEK 42/1R RPR GYWW | ICW
LC | 126415884 | 042/001 | T2 DI TRINITY-MAPLE CREEK 42/1C RPR GYWW | EUREKA | ETL.8170.POLE.STPS | 2023-06-21 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46096670 | T2 DI TRINITY-MAPLE CREEK 42/1R RPR GYWW | ICW
LC | 126384076 | 036/706 | T2 EI HAT CRK #1-WESTWOOD 36/706 RPL PL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-15 | 2023-06-15 | 2024-04-29 | On-time | 2024-06-14 | 46 | 2024-06-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514271 | T2 EI HAT CRK #1-WESTWOOD 36/696 RPL PL | 70Y
LC | 126415925 | 004/155 | T2 EI SPAULDING-SUMMIT 4/155 RPL INSW | SACTO | ETL.8060.INSL.NCER | 2023-06-21 | 2023-06-21 | 2024-06-26 | Late | 2024-06-20 | -6 | 2024-06-21 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35508780 | T2 EI SPAULDING-SUMMIT 4/155 RPL INSW | 93I
LC | 126416423 | 017/014 | T2 DI TRINITY-MAPLE CRK 017/014 RPL ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-21 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35553687 | T2 DI TRINITY-MAPLE CRK 017/014 RPL ANCW | 93E
LC | 126416443 | 058/002A | T2 WV HMBLD TRNTY 058/002A (L) RPR GYWW | EUREKA | ETL.1820.POLE.STPS | 2023-06-21 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171104 | T2 WV HMBLD TRNTY 058/002A (L) RPR GYWW | ICW
LC | 126416704 | 042/003D | T2 DI TRINITY-MAPLE CREEK 42/3D COTTER | EUREKA | ETL.8170.POLE.NWOD | 2023-06-21 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46096671 | T2 DI TRINITY-MAPLE CREEK 42/3D COTTER | ICS
LC | 126386338 | 001/032 | T2 EI KILARC-DESCHUTES 1/032 RPL STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-16 | 2023-06-15 | 2024-03-20 | On-time | 2024-06-14 | 86 | 2024-06-15 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515348 | T2 EI KILARC-DESCHUTES 01/023 RPL STRW | 70Y
LC | 126386509 | 001/035 | T2 EI KILARC-DESCHUTES 01/35 RPR STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-16 | 2023-06-15 | 2024-03-20 | On-time | 2024-06-14 | 86 | 2024-06-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088923 | T2 EI KILARC-DESCHUTES 01/35 RPR STRW | ICW
LC | 126389051 | 000/004 | T2 DI PIT #3 PIT #1 000/004 COMPLETED | TABLEMTN | ETL.5400.INSL.NCER | 2023-06-16 | 2023-06-15 | 2024-05-14 | On-time | 2024-06-14 | 31 | 2024-06-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46083533 | T2 DI PIT #3 PIT #1 000/004 COTTER | ICS
LC | 126417432 | 023/276 | T2 EI DRUM-SUMMIT #1 023/276R RPR INSW | SACTO | ETL.1440.INSL.NCER | 2023-06-21 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46098248 | T2 EI DRUM-SUMMIT #1 023/276R RPR INSW | ICW
LC | 126389767 | 055/411 | T2 DI BRIDGEVLL-COTTN 55/411 RPR INSS | TABLEMTN | ETL.1110.INSL | 2023-06-16 | 2023-06-15 | 2023-08-28 | On-time | 2024-06-14 | 291 | 2023-09-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45858061 | T2 DI BRIDGEVLL-COTTN 55/411 RPR INSS | ICS
LC | 126418389 | 023/271 | T2 EI DRUM SUMMIT#1 23/271 RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2023-06-21 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126390466 | ;000/012 | T2 DI CARIBOU#2 ;0/12 RPL INSW | TABLEMTN | ETL.6280.INSL.CERA | 2023-06-16 | 2023-06-15 | 2023-11-28 | On-time | 2024-06-14 | 199 | 2023-09-15 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31653686 | T2 DI CARIBOU#2 ;00/012 RPL INSW | 93I
LC | 126418596 | 069/350A | T2 EI MALIN-RND MTN #2 69/350A BNT STEEL | TABLEMTN | ETL.6020.TOWR | 2023-06-21 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46132330 | T2 EI MALIN-RND MTN #2 69/350A BNT STEEL | ICQ
LC | 126390612 | 000/010 | T2 DI MPL CRK HOOPA 00/010 RPR ANCW | EUREKA | ETL.7490.POLE.WOOD | 2023-06-16 | 2023-06-15 | 2024-01-24 | On-time | 2024-06-14 | 142 | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46045971 | T2 DI MAPLE CRK-HOOPA 001/006 RPR GYWW | ICW
LC | 126418989 | 031/002 | T2 FORT ROSS-GUALALA 031/002 RPL POLE | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-06-21 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 372T | TLX | CREW | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35518698 | T2 FORT ROSS-GUALALA 031/002 RPL POLE | 70Y
LC | 126391544 | 007/059 | T2 DI BCK CRK-RCK CRK-CRST 7/59 RPL HRDT | TABLEMTN | ETL.4430.TOWR | 2023-06-16 | 2023-06-15 | 2024-03-25 | On-time | 2024-06-14 | 81 | 2024-06-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Tower | Install | 46127858 | T2 DI BCK CRK-RCK CRK-CRST 7/59 RPL HRDT | ICQ
LC | 126419634 | 040/321 | T2 EI BRIDGEVLL-COTTONWD 40/321 RMV VEG | TABLEMTN | ETL.1110.POLE.WDPS | 2023-06-21 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126392298 | 005/037 | T2 DI PIT #4 TAP 005/037 COTTER | TABLEMTN | ETL.5432.INSL.CERA | 2023-06-16 | 2023-06-15 | 2023-10-02 | On-time | 2024-06-14 | 256 | 2024-06-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46029000 | T2 DI PIT #4 TAP 005/037 COTTER | ICS
LC | 126392299 | 005/037 | T2 DI PIT #4 TAP 5/37 RPR JUMS | TABLEMTN | ETL.5432.INSL.CERA | 2023-06-16 | 2023-06-15 | 2023-10-02 | On-time | 2024-06-14 | 256 | 2023-09-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45858063 | T2 DI PIT #4 TAP 005/037 RPR JUMS | ICS
LC | 126393651 | 001/003 | T2 DI MPL CRK HOOPA 01/003L RPR GYWW | EUREKA | ETL.7490.POLE.WDPS | 2023-06-16 | 2023-06-15 | 2023-10-02 | On-time | 2024-06-14 | 256 | 2023-12-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45864452 | T2 DI MPL CRK HOOPA 01/003L RPR GYWW | ICW
LC | 126393654 | 001/003 | T2 DI MPL CRK HOOPA 01/003R RPR GYWW | EUREKA | ETL.7490.POLE.WDPS | 2023-06-16 | 2023-06-15 | 2024-01-24 | On-time | 2024-06-14 | 142 | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45864453 | T2 DI MPL CRK HOOPA 01/003R RPR GYWW | ICW
LC | 126393657 | 001/003 | T2 DI MPL CRK HOOPA 01/003C RPR GYWW | EUREKA | ETL.7490.POLE.WDPS | 2023-06-16 | 2023-06-15 | 2023-10-02 | On-time | 2024-06-14 | 256 | 2023-12-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45864451 | T2 DI MPL CRK HOOPA 01/003C RPR GYWW | ICW
LC | 126421453 | 044/345 | T2 DI BRGVLE-CTNWD 44/345 RPR INSS | TABLEMTN | ETL.1110.INSL.CERA | 2023-06-21 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46088648 | T2 DI BRGVLE-CTNWD 44/345 RPR INSLS | ICS
LC | 126393764 | 001/003 | T2 DI MPL CRK HOOPA 01/003 RPR ANCW | EUREKA | ETL.7490.POLE.WDPS | 2023-06-16 | 2023-06-15 | 2024-01-24 | On-time | 2024-06-14 | 142 | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46045971 | T2 DI MAPLE CRK-HOOPA 001/006 RPR GYWW | ICW
LC | 126397029 | 056/414 | T2 DI BRDGVL-CTNWD 56/414 RPL HRDS | TABLEMTN | ETL.1110.TOWR | 2023-06-17 | 2023-06-15 | 2024-06-12 | On-time | 2024-06-14 | 2 | 2024-06-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46125143 | T2 DI BRDGVL-CTNWD 56/414 RPL HRDS | ICQ
LC | 126397413 | 000/000A | T2 DI MALACHA TAP 0/A COTTER | TABLEMTN | ETL.5910.INSL.CERA | 2023-06-17 | 2023-06-15 | 2024-01-31 | On-time | 2024-06-14 | 135 | 2024-06-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46083531 | T2 DI MALACHA TAP 0/A COTTER | ICS
LC | 126397829 | ;002/005 | T2 DI CARIBOU #2 2/5 RPL TIE WIRE | TABLEMTN | ETL.6280.INSL.CERA | 2023-06-17 | 2023-06-15 | 2023-07-22 | On-time | 2024-06-14 | 328 | 2023-12-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 45870609 | T2 DI CARIBOU #2 2/5 RPL TIE WIRE | ICW
LC | 126397859 | 004/080 | T2 DI DEL MONTE-VIEJO 4/080 RPR INSW | MOSSLNDG | ETL.6710.INSL.CERA | 2023-06-17 | 2023-06-15 | 2024-05-13 | On-time | 2024-06-14 | 32 | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081623 | T2 DI DEL MONTE-VIEJO 4/080 RPR INSW | ICW
LC | 126421594 | 040/770 | T2 DI HT CRK #1-WSTWD 040/770 RPR HRDD | TABLEMTN | ETL.7030.POLE.NWOD | 2023-06-21 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46091875 | T2 DI HT CRK #1-WSTWD 040/770 RPR HRDD | ICW
LC | 126421599 | 029/001 | T2 DI PHILO JCT-ELK 29/1 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-06-21 | 2023-06-16 | 2024-06-18 | Late | 2024-06-15 | -3 | 2024-06-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35522275 | T2 DI PHILO JCT ELK 28/8 RPL POLE | 70Y
LC | 126397933 | 003/073 | T2 DI DEL MONTE-VIEJO 3/073 RPR INSW | MOSSLNDG | ETL.6710.INSL.NCER | 2023-06-17 | 2023-06-15 | 2024-05-11 | On-time | 2024-06-14 | 34 | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081626 | T2 DI DEL MONTE-VIEJO 3/073 RPR INSW | ICW
LC | 126421619 | 038/730 | T2 DI HAT CREEK #1-WSTWD 38/730 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-21 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514274 | T2 DI HAT CREEK #1-WSTWD 38/730 RPL STRW | 70Y
LC | 126421663 | 013/011 | T2 DI BRDGVL-GRBRVL 13/011 RPR SPLW | EUREKA | ETL.6220.INSL.NCER | 2023-06-21 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46087891 | T2 DI BRDGVL-GRBRVL 13/011 RPR SPLW | ICW
LC | 126421674 | 027/234 | T2 DI BRDGVL-CTNWD-27/234C RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-06-21 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521266 | T2 DI BRDGVL-CTNWD- RPL 3 STRW | 70Y
LC | 126421675 | 027/234 | T2 DI BRDGVL-CTNWD-27/234L RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-06-21 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521266 | T2 DI BRDGVL-CTNWD- RPL 3 STRW | 70Y
LC | 126421679 | 027/234 | T2 DI BRDGVL-CTNWD-27/234R RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-06-21 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521266 | T2 DI BRDGVL-CTNWD- RPL 3 STRW | 70Y
LC | 126398071 | 000/017 | T2 DI CARIBOU-PLUMAS JCT 0/17 RPR INSW | TABLEMTN | ETL.6290.INSL.NCER | 2023-06-17 | 2023-06-15 | 2024-05-06 | On-time | 2024-06-14 | 39 | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator Bond Wire-Wood | Repair | 46091868 | T2 DI CARIBOU-PLUMAS JCT 0/17 RPR INSW | ICW
LC | 126421486 | 002/044 | T2 DI DEL MONTE-VJ VJ 02/44 RPL ANCW | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-21 | 2023-06-15 | 2024-05-11 | On-time | 2024-06-14 | 34 | 2024-06-15 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35515352 | T2 DI DEL MONTE-VJ VJ 02/44 RPL ANCW | 93E
LC | 126429964 | 004/109 | T2 DI DL MNTE VEJO 04/109 RPL POLE | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-22 | 2023-06-15 | 2024-05-08 | On-time | 2024-06-14 | 37 | 2024-06-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515358 | T2 DI DEL MONTE-VIEJO 4/106 RPL STRW | 70Y
LC | 126421777 | 006/158 | T2 DI DL MNTE-VJO-VJO 6/158 RPL STRW | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-21 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515622 | T2 DI DL MNTE-VJO-VJO 6/158 RPL STRW | 70Y
LC | 126421778 | 002/055 | T2 DI DEL MNTE-VIEJO 2/55 RPL STRW | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-21 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515354 | T2 DI DEL MNTE-VIEJO 02/054 RPL STRW | 70Y
LC | 126421794 | 045/355 | T2 DI BRDGVL-CTNWD-45/355R RPR GYWT | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-21 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46236027 | T2 DI BRDGVL-CTNWD-45/355R RPR GYWT | ICQ
LC | 126421795 | 045/355 | T2 DI BRDGVL-CTNWD-45/355C RPR GYWT | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-21 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46236028 | T2 DI BRDGVL-CTNWD-45/355C RPR GYWT | ICQ
LC | 126421796 | 045/355 | T2 DI BRDGVL-CTNWD-45/355L RPR OPGW | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-21 | 2023-06-16 |  | Late | 2024-06-15 |  | 2023-12-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46088651 | T2 DI BRDGVL-CTNWD-45/355L RPR OPGW | ICS
LC | 126430551 | 011/014 | T2 DI CRBOU PLUMAS JT 11/014 RPL POLE | TABLEMTN | ETL.6290.POLE.WOOD | 2023-06-22 | 2023-06-15 | 2024-05-08 | On-time | 2024-06-14 | 37 | 2024-06-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518839 | T2 DI CRBOU PLUMAS JT 11/014 RPL POLE | 70Y
LC | 126421851 | 045/355 | T2 DI BRDGVL-CTNWD 45/355C RPR STRT | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-21 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46089577 | T2 DI BRDGVL-CTNWD 45/355C RPR STRT | ICQ
LC | 126422319 | 021/006 | T2 TRINITY-MAPLE CREEK 21/006 RPL INSW | EUREKA | ETL.8170.INSL.CERA | 2023-06-22 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35503525 | T2 TRINITY-MAPLE CREEK 21/006 RPL INSW | 93I
LC | 126422741 | 009/325 | T2 SPAULDING-SUMMIT 9/325 RPR STRW | SACTO | ETL.8060.POLE.WOOD | 2023-06-22 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46102229 | T2 SPAULDING-SUMMIT 9/325 RPR STRW | ICW
LC | 126423454 | 026/317 | T2 DI DRUM-SMMT #1 26/317R RPL HRWD | SACTO | ETL.1440.POLE.WDPS | 2023-06-22 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46101361 | T2 DI DRUM-SMMT #1 26/317R RPL HRWD | ICW
LC | 126423455 | 026/317 | T2 DI DRUM-SMMT #1 26/317C RPL HRWD | SACTO | ETL.1440.POLE.WDPS | 2023-06-22 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46101362 | T2 DI DRUM-SMMT #1 26/317C RPL HRWD | ICW
LC | 126423570 | 004/034 | T2 DI PIT#4 TAP 04/034 RPL INSS | TABLEMTN | ETL.5432.INSL.CERA | 2023-06-22 | 2023-06-14 | 2024-06-24 | Late | 2024-06-13 | -11 | 2024-06-14 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509002 | T2 DI PIT#4 TAP RPL INSS 3 TWRS | 93K
LC | 126423768 | 013/255 | T2 EI COLGATE-PALERMO 13/255 RPL STRW | SACTO | ETL.6500.POLE.WOOD | 2023-06-22 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 372 | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31600088 | T2 DI COLGATE-PALERMO A013/262 RPL STRW | 70Y
LC | 126430796 | 000/009 | T2 DI MAPLE CRK-HOOPA 0/9 RPR ANCW | EUREKA | ETL.7490.POLE.WOOD | 2023-06-22 | 2023-06-15 | 2024-01-24 | On-time | 2024-06-14 | 142 | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46045971 | T2 DI MAPLE CRK-HOOPA 001/006 RPR GYWW | ICW
LC | 126430824 | 004/093 | T2 DI DEL MNTE-VIEJO 4/93 RPR ANCW | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-22 | 2023-06-15 | 2024-05-01 | On-time | 2024-06-14 | 44 | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46081632 | T2 DI DEL MNTE-VIEJO 4/93 RPR ANCW | ICW
LC | 126430921 | 008/040 | T2 DI SILVRDO-FLTN JCT 8/40 RPR SPLCS | LAKEVLLE | ETL.1610.INSL.NCER | 2023-06-22 | 2023-06-15 | 2024-04-11 | On-time | 2024-06-14 | 64 | 2024-06-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Steel | Repair | 46190768 | T2 DI SILVRDO-FLTN JCT 8/40 RPR SPLCS | ICS
LC | 126424625 | 048/005 | T2 EI HUMBOLDT-TRINITY 48/5R RPL POLE | EUREKA | ETL.1820.POLE.WDPS | 2023-06-22 | 2023-04-11 |  | Late | 2024-04-10 |  | 2024-04-11 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35542069 | T2 EI HUMBOLDT-TRINITY 48/5L RPL POLE | 70Y
LC | 126425705 | 003/091-GUY | T2 EI HAMLTN BRNCH-CHSTR 3/91-G RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-22 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Guy Pole-Wood | Replace | 31654290 | T2 EI HAMILTON BRNCH-CHSTR 3/91 RPL POLE | 70Y
LC | 126426707 | 032/006 | T2 RIO DELL JCT-BRIDGEVLLE 32/6 RPL CNDW | EUREKA | ETL.7850.INSL.NCER | 2023-06-22 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 638 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Replace | 31655133 | T2 RIO DELL JCT-BRIDGEVLLE 32/6 RPL CNDW | 93C
LC | 126426856 | 034/008 | T2 RIO DLL JCT-BRDGVLE 34/8 GO95 CLEAR | EUREKA | ETL.7850.POLE.WOOD | 2023-06-22 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 401 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31656734 | T2 RIO DL JCT-BRIDGVILLE 34/7 GO95 CLEAR | 93G
LC | 126430924 | 008/040 | T2 DI FULTON-PUEBLO 8/40 RPL DAMPS | LAKEVLLE | ETL.1600.INSL.NCER | 2023-06-22 | 2023-06-15 | 2024-04-11 | On-time | 2024-06-14 | 64 | 2024-06-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 46096641 | T2 DI FULTON-PUEBLO 8/40 RPL DAMPS | ICS
LC | 126428075 | 015/119 | T2 EI PIT #1-COTTONWD 15/119 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2023-06-22 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46089578 | T2 EI PIT #1-COTTONWD 15/119 RPR STRT | ICQ
LC | 126428135 | 003/088 | T2 EI HAMILTON BRNCH-CHSTR 3/88 RPR POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-22 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091898 | T2 EI HAMILTON BRNCH-CHSTR 3/88 RPR POLE | ICW
LC | 126428421 | 003/087 | T2 EI HAMILTON BRNCH-CHSTR 3/87 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-22 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521273 | T2 EI HAMILTON BRNCH-CHSTR 3/86 RPL POLE | 70Y
LC | 126437652 | 008/041 | T2 DI FULTON-PUEBLO 8/41 RMV NEST | LAKEVLLE | ETL.1600.TOWR | 2023-06-23 | 2023-06-15 | 2024-04-11 | On-time | 2024-06-14 | 64 | 2024-06-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46096642 | T2 DI FULTON-PUEBLO 8/41 RMV NEST | ICS
LC | 126428678 | 003/086 | T2 EI HAMILTON BRNCH-CHSTR 3/86 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-22 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521273 | T2 EI HAMILTON BRNCH-CHSTR 3/86 RPL POLE | 70Y
LC | 126429270 | 004/060 | T2 WV WEIMAR #1 4/60 INST DMPW | SACTO | ETL.7560.INSL.NCER | 2023-06-22 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 46127518 | T2 WV WEIMAR #1 4/60 INST DMPW | ICW
LC | 126438111 | 007/051 | T2 DI ROCK CREEK-POE 007/051 RPL INSS | TABLEMTN | ETL.5630.INSL.CERA | 2023-06-23 | 2023-06-15 | 2024-02-24 | On-time | 2024-06-14 | 111 | 2024-06-15 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509199 | T2 DI ROCK CREEK-POE :5/33 RPLC INSS | 93K
LC | 126429450 | 008/043 | T2 DI FULTON PUEBLO 08/043 BNT STEEL | LAKEVLLE | ETL.1600.TOWR | 2023-06-22 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46170907 | T2 DI FULTON PUEBLO 08/043 BNT STEEL | ICQ
LC | 126466015 | 004/110 | T2 DI DEL MNTE-VIEJO 4/110 RPL STRW | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-27 | 2023-06-15 | 2024-05-09 | On-time | 2024-06-14 | 36 | 2024-06-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515358 | T2 DI DEL MONTE-VIEJO 4/106 RPL STRW | 70Y
LC | 126386937 | 108/006 | T2 EI HUMBOLDT-BRIDGE 108/6 RPR ADSS | EUREKA | ETL.1810.TOWR | 2023-06-16 | 2023-06-16 | 2024-02-27 | On-time | 2024-06-15 | 109 | 2024-06-16 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46096231 | T2 EI HUMBOLDT-BRIDGE 108/6 RPR ADSS | ICS
LC | 126387044 | 001/005 | T2 DINOSAUR POINT TAP 1/5 GO95 CLEAR | FRESNO | ETL.8961.POLE.WOOD | 2023-06-16 | 2023-06-16 | 2024-04-07 | On-time | 2024-06-15 | 69 | 2024-06-16 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31653340 | T2 DINOSAUR POINT TAP 1/005 GO95 CLEAR | 93G
LC | 126430152 | 003/082 | T2 EI HAMILTON BRNCH-CHSTR 3/82 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-22 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521272 | T2 EI HAMILTON BRNCH-CHSTR 2/74 RPL POLE | 70Y
LC | 126430275 | 004/036 | T2 DI ROCK CREEK-POE 04/36 RPR FOND | TABLEMTN | ETL.5630.TOWR | 2023-06-22 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46132649 | T2 DI ROCK CREEK-POE 04/36 RPR FOND | ICQ
LC | 126387707 | 015/113 | T2 HELMS-GREGG #1 015/113 RPR INSS | FRESNO | ETL.4870.INSL.CERA | 2023-06-16 | 2023-06-16 | 2024-05-15 | On-time | 2024-06-15 | 31 | 2024-06-16 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46081898 | T2 HELMS-GREGG #1 015/113 RPR INSS | ICS
LC | 126388261 | 000/001 | T2 WV SANTA YNEZ TAP 0/1 INS DMPW | PISMOBCH | ETL.3701.POLE.WOOD | 2023-06-16 | 2023-06-16 | 2024-03-06 | On-time | 2024-06-15 | 101 | 2024-06-16 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46088505 | T2 WV SANTA YNEZ TAP 0/1 INS DMPW | ICW
LC | 126389831 | 027/201 | T2 EI DRUM-RIO OSO #2 27/201 RPL INSS | SACTO | ETL.1430.INSL.CERA | 2023-06-16 | 2023-06-16 | 2024-01-17 | On-time | 2024-06-15 | 150 | 2024-06-16 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35508878 | T2 EI DRUM-RIO OSO #2 RPL INSS 2 TWRS | 93K
LC | 126430510 | 056/413B | T2 DI BRIDGVLLE-CTTNWD 56/413B RPR OPGW | TABLEMTN | ETL.1110.POLE.NWOD | 2023-06-22 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46088646 | T2 DI BRIDGVLLE-CTTNWD 56/413B RPR OPGW | ICS
LC | 126389981 | 011/054 | T2 EI SLVRD FLTN JCT 011/054 RPR SPLS | LAKEVLLE | ETL.1610.INSL.NCER | 2023-06-16 | 2023-06-16 | 2024-04-11 | On-time | 2024-06-15 | 65 | 2024-06-16 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 46175534 | T2 EI SLVRD FLTN JCT 011/054 RPR SPLS | ICS
LC | 126430538 | 002/079 | T2 EI HAMILTON BRNCH-CHSTR 2/79 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-22 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521272 | T2 EI HAMILTON BRNCH-CHSTR 2/74 RPL POLE | 70Y
LC | 126390783 | 011/394 | T2 EI SPAULDING-SUMMIT 11/394 RPR INSW | SACTO | ETL.8060.INSL.NCER | 2023-06-16 | 2023-06-16 | 2024-01-16 | On-time | 2024-06-15 | 151 | 2024-06-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46127517 | T2 EI SPAULDING-SUMMIT 11/394 RPR INSW | ICW
LC | 126393285 | 002/050 | T2 EI KILARC-DESCHUTES 02/50 RPR INSW | TABLEMTN | ETL.7300.INSL.NCER | 2023-06-16 | 2023-06-16 | 2024-02-22 | On-time | 2024-06-15 | 114 | 2024-06-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46088922 | T2 EI KILARC-DESCHUTES 02/50 RPR INSW | ICW
LC | 126393295 | 002/050 | T2 EI KILARC-DESCHUTES 02/50 RPR STRW | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-16 | 2023-06-16 | 2024-02-22 | On-time | 2024-06-15 | 114 | 2024-06-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091869 | T2 EI KILARC-DESCHUTES 02/50 RPR STRW | ICW
LC | 126430602 | 016/001 | T2 DI PHILO JCT-ELK 16/001 RPL POLE | WILLITS | ETL.7780.POLE.WOOD | 2023-06-22 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506674 | T2 DI PHILO JCT-ELK 16/001 RPL POLE | 70Y
LC | 126430608 | 004/032 | T2 DI PIT#4 TAP 04/32 RPL INSS | TABLEMTN | ETL.5432.INSL.CERA | 2023-06-22 | 2023-06-14 | 2024-06-25 | Late | 2024-06-13 | -12 | 2024-06-14 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509002 | T2 DI PIT#4 TAP RPL INSS 3 TWRS | 93K
LC | 126394006 | 031/259 | T2 EI BRIDGEVILLE-CTTNWD 31/259L COTTER | TABLEMTN | ETL.1110.INSL.CERA | 2023-06-16 | 2023-06-16 | 2024-05-30 | On-time | 2024-06-15 | 16 | 2024-06-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46093351 | T2 EI BRIDGEVILLE-CTTNWD 31/259L COTTER | ICW
LC | 126394129 | 023/159A | T2 EI CARIBOU-TABLE MTN 23/159A INS DMPS | TABLEMTN | ETL.4440.INSL.CERA | 2023-06-16 | 2023-06-16 | 2024-06-07 | On-time | 2024-06-15 | 8 | 2024-06-16 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 46087818 | T2 EI CARIBOU-TABLE MTN 23/159A INS DMPS | ICS
LC | 126430694 | 000/001 | T2 DI PIT #7 TAP 00/001 RPR INSS | TABLEMTN | ETL.5442.INSL.CERA | 2023-06-22 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46083532 | T2 DI PIT#7 TAP 00/001 RPR INSS | ICS
LC | 126394138 | 056/011 | T2 EI ELK-GUALALA 056/011 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-06-16 | 2023-06-16 | 2024-01-16 | On-time | 2024-06-15 | 151 | 2024-06-16 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487383 | T2 DI ELK-GUALALA 057/006 RPL STRW | 70Y
LC | 126394233 | 010/088 | T2 EI CRESTA-RIO OSO 010/088 UNBURY | TABLEMTN | ETL.4590.TOWR | 2023-06-16 | 2023-06-16 | 2024-06-07 | On-time | 2024-06-15 | 8 | 2024-06-16 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46128013 | T2 EI CRESTA-RIO OSO 010/088 UNBURY | ICQ
LC | 126430791 | 001/055 | T2 DI SPLDG SUMMIT 1/55C RPL HRDD | SACTO | ETL.8060.POLE.WDPS | 2023-06-22 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46127498 | T2 DI SPLDG SUMMIT 01/55C RPL HRDD | ICW
LC | 126430795 | 001/055 | T2 DI SPLDG SUMMIT 1/55 RPL INSW | SACTO | ETL.8060.INSL.NCER | 2023-06-22 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35508693 | T2 DI SPLDG SUMMIT 01/055 RPL INSW | 93I
LC | 126394341 | :017/015 | T2 EI EGLE RCK-CORTINA :017/015 RPR GYWW | WILLITS | ETL.1470.POLE.WOOD | 2023-06-16 | 2023-06-16 | 2023-11-27 | On-time | 2024-06-15 | 201 | 2023-12-16 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Replace | 45882387 | T2 EI EGLE RCK-CORTINA :017/015 RPR GYWW | ICW
LC | 126396284 | 006/150 | T2 DI DL MNTE VIEJO 06/150 RPL HRDD | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-17 | 2023-06-16 | 2024-05-23 | On-time | 2024-06-15 | 23 | 2024-06-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46081538 | T2 DI DL MNTE VIEJO 06/150 RPL HRDD | ICW
LC | 126430806 | 045/353 | T2 DI BRDGEVILLE-CTTNWD 45/353L RPR GYWT | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-22 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46236029 | T2 DI BRDGEVILLE-CTTNWD 45/353L RPR GYWT | ICQ
LC | 126396397 | 044/349 | T2 DI BRDGVIL CTTNWD 44/349 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-06-17 | 2023-06-16 | 2023-08-17 | On-time | 2024-06-15 | 303 | 2023-09-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45881438 | T2 DI BRDGVIL CTTNWD 44/349 RPR SHLS | ICS
LC | 126421235 | 008/074 | T2 DI CRESTA-RIO OSO 008/074 UNBURY | TABLEMTN | ETL.4590.TOWR | 2023-06-21 | 2023-06-16 | 2024-05-09 | On-time | 2024-06-15 | 37 | 2024-06-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46128015 | T2 DI CRESTA-RIO OSO 008/074 UNBURY | ICQ
LC | 126430854 | 045/353 | T2 DI BRDGEVIL-CTTNWD 45/353L RPR ANCT | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-22 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Tower | Repair | 46236030 | T2 DI BRDGEVIL-CTTNWD 45/353L RPR ANCT | ICQ
LC | 126421311 | 018/210 | T2 DI DRUM-SUMMIT #1 18/210 RPR ANCW | SACTO | ETL.1440.POLE.STPS | 2023-06-21 | 2023-06-16 | 2024-05-17 | On-time | 2024-06-15 | 29 | 2024-06-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46098249 | T2 DI DRUM-SUMMIT #1 18/210 RPR ANCW | ICW
LC | 126430896 | ;000/031 | T2 DI CARIBOU #2 ;00/31 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-06-22 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35538377 | T2 DI CARIBOU #2 ;00/31 RPL STRW | 70Y
LC | 126421413 | 049/373 | T2 DI BRDGVL-CTNWD 49/373 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-06-21 | 2023-06-16 | 2023-08-28 | On-time | 2024-06-15 | 292 | 2023-09-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45860251 | T2 DI BRDGVL-CTNWD 49/373 RPR OPGW | ICS
LC | 126421501 | 003/070 | T2 DI DEL MONTE-VIEJO 3/70 RPL ANCW | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-21 | 2023-06-16 | 2024-05-06 | On-time | 2024-06-15 | 40 | 2024-06-16 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35515355 | T2 DI DEL MONTE-VIEJO 3/70 RPL ANCW | 93E
LC | 126421506 | 046/357 | T2 DI BRDGVL-CTNWD 46/357 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-06-21 | 2023-06-16 | 2023-08-28 | On-time | 2024-06-15 | 292 | 2023-09-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45866322 | T2 DI BRDGVL-CTNWD 46/357 RPR OPGW | ICS
LC | 126421813 | 050/378 | T2 DI BRDGVLE-CTNWD 50/378 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-06-21 | 2023-06-16 | 2023-08-28 | On-time | 2024-06-15 | 292 | 2023-09-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45866325 | T2 DI BRDGVLE-CTNWD 50/378 RPR OPGW | ICS
LC | 126430305 | 010/085 | T2 DI CRESTA-RIO OSO 10/085 UNBURY | TABLEMTN | ETL.4590.TOWR | 2023-06-22 | 2023-06-16 | 2024-05-15 | On-time | 2024-06-15 | 31 | 2024-06-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46128017 | T2 DI CRESTA-RIO OSO 10/085 UNBURY | ICQ
LC | 126430461 | 004/082 | T2 DI CARIBOU-WESTWOOD 4/82 COTTER | TABLEMTN | ETL.6300.INSL.NCER | 2023-06-22 | 2023-06-16 | 2023-08-14 | On-time | 2024-06-15 | 306 | 2023-12-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45870610 | T2 DI CARIBOU-WESTWOOD 4/82 COTTER | ICW
LC | 126430621 | 010/083 | T2 DI CRESTA-RIO OSO 010/083 UNBURY | TABLEMTN | ETL.4590.TOWR | 2023-06-22 | 2023-06-16 | 2024-05-09 | On-time | 2024-06-15 | 37 | 2024-06-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46128018 | T2 DI CRESTA-RIO OSO 010/083 UNBURY | ICQ
LC | 126430807 | 045/353 | T2 DI BRDGEVILLE-CTTNWD 45/353L RPR SHLD | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-22 | 2023-06-16 | 2023-08-17 | On-time | 2024-06-15 | 303 | 2023-09-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45881980 | T2 DI BRDGEVILLE-CTTNWD 45/353L RPR SHLD | ICS
LC | 126432580 | 044/346 | T2 DI BRDGVLLE-CTTNWD 44/346 RPR FOND | TABLEMTN | ETL.1110.TOWR | 2023-06-23 | 2023-06-16 | 2024-06-12 | On-time | 2024-06-15 | 3 | 2024-06-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46125090 | T2 DI BRDGVLLE-CTTNWD 44/346 RPR FOND | ICQ
LC | 126431032 | 003/048 | T2 DI LAKEVILLE #1 3/48 RPL STRW | LAKEVLLE | ETL.7360.POLE.WOOD | 2023-06-22 | 2023-06-14 |  | Late | 2024-06-13 |  | 2023-12-14 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521898 | T2 DI LAKEVILLE #1 3/48 RPLC STRW | 70Y
LC | 126431040 | 000/006 | T2 DI PIT #5-RND MTN #1 0/6 RPL INSS | TABLEMTN | ETL.5420.INSL | 2023-06-22 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35515146 | T2 DI PIT #5-RND MTN #1 0/6 RPL INSS | 93K
LC | 126431105 | 011/091 | T2 DI CRESTA-RIO OSO 011/091 RMV VEGN | TABLEMTN | ETL.4590.TOWR | 2023-06-22 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126431167 | :000/003 | T2 EI ROCK CREEK-POE :0/3 RPR GYWT | TABLEMTN | ETL.5630.TOWR | 2023-06-22 | 2023-06-22 |  | Late | 2024-06-21 |  | 2023-12-22 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46257567 | T2 EI ROCK CREEK-POE :0/3 RPR GYWT | ICQ
LC | 126432670 | 049/374 | T2 DI BRDGVLLE-CTTNWD 49/374 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-06-23 | 2023-06-16 | 2023-10-29 | On-time | 2024-06-15 | 230 | 2023-09-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45866323 | T2 DI BRDGVLLE-CTTNWD 49/374 RPR OPGW | ICS
LC | 126432767 | 005/134 | T2 DI DEL MNTE-VIEJO 5/134 RPL SPLW | MOSSLNDG | ETL.6710.INSL.NCER | 2023-06-23 | 2023-06-16 | 2024-05-16 | On-time | 2024-06-15 | 30 | 2024-06-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Replace | 46081635 | T2 DI DEL MNTE-VIEJO 5/134 RPL SPLW | ICW
LC | 126432562 | 023/001 | T2 DI FORT BRAGG ELK 023/001 RPL HRDD | WILLITS | ETL.2060.POLE.WOOD | 2023-06-23 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46090350 | T2 DI FORT BRAGG ELK 023/001 RPL HRDD | ICW
LC | 126432787 | 045/351 | T2 DI BRIDGEVILLE-CTTNWD 45/351 RPR OPGW | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-23 | 2023-06-16 | 2023-08-17 | On-time | 2024-06-15 | 303 | 2023-09-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45881345 | T2 DI BRIDGEVILLE-CTTNWD 45/351 RPR OPGW | ICS
LC | 126432995 | 026/228 | T2 DI BRIDGE-COTTON 26/228 RPR WDPKR | TABLEMTN | ETL.1110.POLE.WDPS | 2023-06-23 | 2023-06-16 | 2024-02-01 | On-time | 2024-06-15 | 135 | 2024-06-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46093352 | T2 DI BRIDGE-COTTON 26/228 RPR WDPKR | ICW
LC | 126432604 | 023/001-GUY | T2 DI FRT BRAGG ELK 23/001 COA | WILLITS | ETL.2060.POLE.WOOD | 2023-06-23 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46090351 | T2 DI FRT BRAGG ELK 23/001 RPR GYWW | ICW
LC | 126433692 | 003/069 | T2 DI DEL MONTE-VJ-VJ 3/69 RPR INSW | MOSSLNDG | ETL.6710.INSL.NCER | 2023-06-23 | 2023-06-16 | 2024-05-06 | On-time | 2024-06-15 | 40 | 2024-06-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081661 | T2 DI DEL MONTE-VJ-VJ 3/69 RPR INSW | ICW
LC | 126434061 | 006/160 | T2 DI DEL MNT-VIEJO 006/160 RMV VEG | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-23 | 2023-06-16 | 2024-04-12 | On-time | 2024-06-15 | 64 | 2024-06-16 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126434063 | 006/160 | T2 DI DEL MNT-VIEJO 006/160 RPL HRDD | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-23 | 2023-06-16 | 2024-05-23 | On-time | 2024-06-15 | 23 | 2024-06-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46081726 | T2 DI DEL MNT-VIEJO 006/160 RPL HRDD | ICW
LC | 126434233 | 038/729 | T2 DI HAT CRK #1-WSTWD 38/729 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-23 | 2023-06-16 | 2024-04-30 | On-time | 2024-06-15 | 46 | 2024-06-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514866 | T2 DI HAT CRK #1-WESTWD 37/726 RPL STRW | 70Y
LC | 126432776 | 069/349A | T2 DI MALIN-RD MTN #2 69/349A RPR GYWS | TABLEMTN | ETL.6020.TOWR | 2023-06-23 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46132332 | T2 DI MALIN-RD MTN #2 69/349A RPR GYWS | ICS
LC | 126434353 | 014/104C | T2 DI CARIBOU-TABLE MTN 14/104C RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-23 | 2023-06-16 | 2024-04-10 | On-time | 2024-06-15 | 66 | 2024-06-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46087817 | T2 DI CARIBOU-TABLE MTN 14/104C RPR GYWS | ICS
LC | 126432810 | 064/465 | T2 DI BRDGVLLE-CTTNWD 64/465 COTTER | EUREKA | ETL.1110.INSL.CERA | 2023-06-23 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46171667 | T2 DI BRDGVLLE-CTTNWD 64/465 COTTER | ICS
LC | 126432815 | 064/465 | T2 DI BRDGVLLE-CTTNWD 64/465 COTTER | EUREKA | ETL.1110.TOWR | 2023-06-23 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46125140 | T2 DI BRDGVLLE-CTTNWD 64/465 COTTER | ICQ
LC | 126432890 | 004/104 | T2 DI DEL MONTE-VIEJO 4/104 RMV VEG | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-23 | 2023-06-16 | 2024-06-17 | Late | 2024-06-15 | -2 | 2024-06-16 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126432891 | 004/104 | T2 DI DEL MONTE-VIEJO 4/104 RPL HRDD | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-23 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46081638 | T2 DI DEL MONTE-VIEJO 4/104 RPL HRDD | ICW
LC | 126434683 | 010/086 | T2 DI CRESTA-RIO OSO 10/86 UNBURY | TABLEMTN | ETL.4590.TOWR | 2023-06-23 | 2023-06-16 | 2024-05-15 | On-time | 2024-06-15 | 31 | 2024-06-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46128019 | T2 DI CRESTA-RIO OSO 10/86 UNBURY | ICQ
LC | 126435908 | 050/379 | T2 DI BRDGVLLE-CTTNWD 50/379 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-06-23 | 2023-06-16 | 2023-08-28 | On-time | 2024-06-15 | 292 | 2023-09-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45866326 | T2 DI BRDGVLLE-CTTNWD 50/379 RPR OPGW | ICS
LC | 126433047 | 073/528 | T2 DI BRDGVL-CTTNWD 73/528 RPR GRND | EUREKA | ETL.1110.POLE.WDPS | 2023-06-23 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 46171731 | T2 DI BRDGVLL-CTTNWD 073/528 RPR POLE | ICW
LC | 126436437 | 053/399 | T2 DI BRDGVLLE-CTTNWD 53/399L RPR GYWT | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-23 | 2023-06-16 | 2024-06-12 | On-time | 2024-06-15 | 3 | 2024-06-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46255048 | T2 DI BRDGVLLE-CTTNWD 53/399L RPR GYWT | ICQ
LC | 126436438 | 053/399 | T2 DI BRDGVLLE-CTTNWD 53/399R RPR GYWT | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-23 | 2023-06-16 | 2024-06-12 | On-time | 2024-06-15 | 3 | 2024-06-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46255049 | T2 DI BRDGVLLE-CTTNWD 53/399R RPR GYWT | ICQ
LC | 126436655 | :009/070 | T2 DI ROCK CRK-POE :9/70 RPL INSS | TABLEMTN | ETL.5630.INSL | 2023-06-23 | 2023-06-16 | 2024-02-25 | On-time | 2024-06-15 | 111 | 2024-06-16 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35519937 | T2 DI ROCK CREEK-POE RPL INSS 2 TWRS | 93K
LC | 126439037 | 008/072B | T2 DI CRESTA-RIO OSO 08/72B RPR JUMS | TABLEMTN | ETL.4590.INSL.NCER | 2023-06-23 | 2023-06-16 | 2024-02-21 | On-time | 2024-06-15 | 115 | 2024-06-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46087816 | T2 DI CRESTA-RIO OSO 08/72B RPR JUMS | ICS
LC | 126457285 | 037/726 | T2 DI HAT CRK #1-WESTWD 37/726 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-26 | 2023-06-16 | 2024-04-30 | On-time | 2024-06-15 | 46 | 2024-06-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514866 | T2 DI HAT CRK #1-WESTWD 37/726 RPL STRW | 70Y
LC | 126457473 | 045/352 | T2 DI BRDGVLE-CTNWD 45/352 RPR SHLDWR ST | TABLEMTN | ETL.1110.TOWR | 2023-06-26 | 2023-06-16 | 2023-08-17 | On-time | 2024-06-15 | 303 | 2023-09-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45881439 | T2 DI BRDGVLE-CTNWD 45/352 RPR SHLDWR ST | ICS
LC | 126433834 | 004/035 | T2 DI ROCK CRK-POE 4/35 RPR FOND | TABLEMTN | ETL.5630.TOWR | 2023-06-23 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46132651 | T2 DI ROCK CRK-POE 4/35 RPR FOND | ICQ
LC | 126460190 | 054/403 | T2 DI BRDGVL-CTTNWD 54/403 RPR SHLS | TABLEMTN | ETL.1110.TOWR | 2023-06-27 | 2023-06-16 | 2023-10-29 | On-time | 2024-06-15 | 230 | 2023-09-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45866327 | T2 DI BRDGVL-CTTNWD 54/403 RPR SHLS | ICS
LC | 126469328 | 004/114 | T2 DI DEL MONTE-VIEJO 4/114 RPL STRW | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-28 | 2023-06-16 | 2024-05-11 | On-time | 2024-06-15 | 35 | 2024-06-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515359 | T2 DI DEL MONTE-VIEJO 4/114 RPL STRW | 70Y
LC | 126434110 | 002/086 | T2 DI SPLDNG-SMMT 2/86 RPL SWTC | SACTO | ETL.8060.POLE.WOOD | 2023-06-23 | 2023-06-15 | 2024-06-28 | Late | 2024-06-14 | -14 | 2024-06-15 | 427T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Wood | Replace | 35518746 | T2 DI SPLDNG-SMMT 002/086 RPL POLE | 93H
LC | 126434218 | 013/450 | T2 EI SPAULDING-SUMMIT 13/450 RPR GYWW | SACTO | ETL.8060.POLE.NWOD | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46102230 | T2 EI SPAULDING-SUMMIT 13/450 RPR GYWW | ICW
LC | 126397304 | 035/282 | T2 EI BRDGVLLE-CTTNWD 35/282L RPR GRWW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-06-17 | 2023-06-17 | 2024-06-01 | On-time | 2024-06-16 | 15 | 2024-06-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 46214608 | T2 EI BRDGVLLE-CTTNWD 35/282L RPR GRWW | ICW
LC | 126434238 | 039/753 | T2 DI HT CRK #1-WSTWD 39/753 RPR STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-23 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091873 | T2 DI HT CRK #1-WSTWD 39/753 RPR STRW | ICW
LC | 126434254 | 013/450 | T2 EI SPAULDING-SUMMIT 13/450 RPL ANCW | SACTO | ETL.8060.POLE.NWOD | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35508784 | T2 EI SPAULDING-SUMMIT 13/450 RPL ANCW | 93E
LC | 126399102 | 008/001 | T2 EI MAPLE CREEK-HOOPA 08/001 RPR GYWW | EUREKA | ETL.7490.POLE.NWOD | 2023-06-17 | 2023-06-17 | 2023-10-05 | On-time | 2024-06-16 | 255 | 2024-06-17 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45881153 | T2 EI MAPLE CREEK-HOOPA 08/001 RPR GYWW | ICW
LC | 126434519 | 064/464 | T2 DI BRIDGEVILLE-CTTNWD 64/464 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-23 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46204233 | T2 DI BRIDGEVILLE-CTTNWD 64/464 RPR OPGW | ICS
LC | 126434531 | 064/464 | T2 DI BRIDGEVILLE-COTTONWD 64/464 COTTER | EUREKA | ETL.1110.INSL.CERA | 2023-06-23 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46171666 | T2 DI BRIDGEVILLE-CTTNWD 64/464 RPR OPGW | ICS
LC | 126399216 | 009/079 | T2 EI CRESTA-RIO OSO 009/079 UNBURY | TABLEMTN | ETL.4590.TOWR | 2023-06-17 | 2023-06-17 | 2024-05-09 | On-time | 2024-06-16 | 38 | 2024-06-17 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46128014 | T2 EI CRESTA-RIO OSO 009/079 UNBURY | ICQ
LC | 126434596 | 066/475 | T2 DI BRDGVLLE-CTTNWD 66/475 COTTER | EUREKA | ETL.1110.INSL.CERA | 2023-06-23 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46171670 | T2 DI BRDGVLLE-CTTNWD 66/475 COTTER | ICS
LC | 126434661 | 072/521 | T2 DI BRDGVLE-CTTNWD 72/521R RPL ANCW | EUREKA | ETL.1110.POLE.STPS | 2023-06-23 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35546613 | T2 DI BRDGVLE-CTTNWD 72/521L RPL ANCW | 93E
LC | 126434663 | 072/521 | T2 DI BRDGVLE-CTTNWD 72/521L RPL ANCW | EUREKA | ETL.1110.POLE.STPS | 2023-06-23 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35546613 | T2 DI BRDGVLE-CTTNWD 72/521L RPL ANCW | 93E
LC | 126401422 | :015/009 | T2 EI EAGLE ROCK-CORTINA :015/9 RPL PL | WILLITS | ETL.1470.POLE.WOOD | 2023-06-19 | 2023-06-19 | 2024-03-17 | On-time | 2024-06-18 | 93 | 2024-06-19 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35487309 | T2 EI EAGLE ROCK-CORTINA :015/9 RPL PL | 70Y
LC | 126434840 | 004/106 | T2 DI DEL MONTE-VIEJO 4/106 RPL STRW | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-23 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515358 | T2 DI DEL MONTE-VIEJO 4/106 RPL STRW | 70Y
LC | 126434933 | 068/342 | T2 DI MLN-RND MTN #2 68/342 UNBURRY | TABLEMTN | ETL.6020.TOWR | 2023-06-23 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46102378 | T2 DI MLN-RND MTN #2 68/342 UNBURRY | ICQ
LC | 126403491 | 023/108 | T2 EI EAGLE ROCK-REDBUD 23/108 RPR INSS | WILLITS | ETL.1480.INSL.CERA | 2023-06-19 | 2023-06-19 | 2023-06-20 | On-time | 2024-06-18 | 364 | 2023-09-19 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45854263 | T2 EI EAGLE ROCK-REDBUD 23/108 RPR INSS | ICS
LC | 126404009 | 058/424 | T2 EI BRIDGEVL-CTTNWD 58/424R RPR GYWS | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-19 | 2023-06-19 | 2023-08-24 | On-time | 2024-06-18 | 299 | 2023-09-19 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45894596 | T2 EI BRIDGEVL-CTTNWD 58/424R RPR GYWS | ICS
LC | 126434954 | 046/224 | T2 DI IGNACIO-SOBR 46/224 RPL INSS | CONCORD | ETL.4920.INSL.CERA | 2023-06-23 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671638 | T2 DI IGNCO-SBRNTE RPL INSS IN 6 TWRS. | 93K
LC | 126404049 | 058/424 | T2 EI BRIDGEVL-CTTNWD 58/424C RPR GYWS | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-19 | 2023-06-19 | 2023-08-23 | On-time | 2024-06-18 | 300 | 2023-09-19 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45894597 | T2 EI BRIDGEVL-CTTNWD 58/424C RPR GYWS | ICS
LC | 126404068 | 058/424 | T2 EI BRIDGEVL-CTTNWD 58/424L RPR GYWS | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-19 | 2023-06-19 | 2023-08-26 | On-time | 2024-06-18 | 297 | 2023-09-19 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45894598 | T2 EI BRIDGEVL-CTTNWD 58/424L RPR GYWS | ICS
LC | 126404142 | :016/012 | T2 EI EAGLE ROCK-CORTINA :16/12 RPR GYWW | WILLITS | ETL.1470.POLE.WOOD | 2023-06-19 | 2023-06-19 | 2024-05-15 | On-time | 2024-06-18 | 34 | 2024-06-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46176326 | T2 EI EAGLE ROCK-CORTINA :16/12 RPR GYWW | ICW
LC | 126435277 | 068/344 | T2 DI MLN-RND MTN #2 68/344 RPR JUMS | TABLEMTN | ETL.6020.INSL.NCER | 2023-06-23 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45866379 | T2 DI MLN-RND MTN #2 68/344 RPR JUMS | ICS
LC | 126435427 | 045/218 | T2 DI IGNACIO-SBRNTE #2 45/218 RPR INSS | LAKEVLLE | ETL.4960.INSL | 2023-06-23 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46204155 | T2 DI IGNACIO-SBRNTE #2 45/218 RPR INSS | ICS
LC | 126404378 | 033/272 | T2 EI BRDGVLLE-CTTNWD 33/272R RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-19 | 2023-06-19 | 2024-06-01 | On-time | 2024-06-18 | 17 | 2024-06-19 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46093346 | T2 EI BRDGVLLE-CTTNWD 33/272R RPR GYWW | ICW
LC | 126404422 | 022/154C | T2 EI CARIBOU-TABLE MTN 22/154C RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-19 | 2023-06-19 | 2024-04-17 | On-time | 2024-06-18 | 62 | 2024-06-19 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46127946 | T2 EI CARIBOU-TABLE MTN 22/154C RPR GYWS | ICS
LC | 126435621 | 075/543 | T2 DI BRIDGEVLL-CTTONWD 75/543L RPR OPGW | EUREKA | ETL.1110.POLE.WDPS | 2023-06-23 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 46093344 | T2 DI BRIDGEVLL-CTTONWD 75/543L RPR OPGW | ICW
LC | 126435641 | 067/000 | T2 HUMBOLDT-TRINITY 067/000C RPL HRDW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46249701 | T2 HUMBOLDT-TRINITY 067/000C RPL HRDW | ICW
LC | 126435651 | 011/241 | T2 DI CSCDE BNTN DSHUTS 11/241 RPL HRDD | TABLEMTN | ETL.6310.POLE.WOOD | 2023-06-23 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46091887 | T2 DI CSCDE BNTN DSHUTS 11/241 RPL HRDD | ICW
LC | 126435653 | 064/463 | T2 DI BRDGVLLE-CTTNWD 64/463 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-23 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45881346 | T2 DI BRDGVLLE-CTTNWD 64/463 RPR OPGW | ICS
LC | 126404427 | 022/152 | T2 EI CARIBOU-TABLE MTN 022/152 INS DMPS | TABLEMTN | ETL.4440.INSL.CERA | 2023-06-19 | 2023-06-19 | 2024-06-07 | On-time | 2024-06-18 | 11 | 2024-06-19 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 46088161 | T2 EI CARIBOU-TABLE MTN 022/152 INS DMPS | ICS
LC | 126404432 | 022/154A | T2 EI CARIBOU-TABLE MTN 22/154A UNBURY | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-19 | 2023-06-19 | 2024-04-17 | On-time | 2024-06-18 | 62 | 2024-06-19 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46091123 | T2 EI CARIBOU-TABLE MTN 22/154A MASTIC | ICQ
LC | 126404440 | 022/154A | T2 EI CARIBOU-TABLE MTN 22/154A RPR ANCS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-19 | 2023-06-19 | 2024-01-08 | On-time | 2024-06-18 | 162 | 2023-12-19 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 45866376 | T2 EI CARIBOU-TABLE MTN 22/154A RPR ANCS | ICS
LC | 126435915 | 000/004 | T2 DI PIT #5-RND MTN #1 0/4 RPL INSS | TABLEMTN | ETL.5420.INSL.CERA | 2023-06-23 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671287 | T2 DI PIT #5-RND MTN #1 0/4 RPL INSS | 93K
LC | 126406836 | 008/042 | T2 EI FULTON-PUEBLO 008/042 RPR SPLS | LAKEVLLE | ETL.1600.INSL.NCER | 2023-06-20 | 2023-06-20 | 2024-04-11 | On-time | 2024-06-19 | 69 | 2024-06-20 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Steel | Repair | 46078104 | T2 EI FULTON-PUEBLO 008/042 RPR SPLS | ICS
LC | 126436120 | 021/000 | T2 DI TRINITY-MAPLE CRK 21/0R RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-23 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503523 | T2 DI TRINITY-MAPLE CRK 21/0L RPL POLE | 70Y
LC | 126436126 | 021/000 | T2 DI TRINITY-MAPLE CRK 21/0L RPL POLE | EUREKA | ETL.8170.POLE.WDPS | 2023-06-23 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35503523 | T2 DI TRINITY-MAPLE CRK 21/0L RPL POLE | 70Y
LC | 126436229 | 013/448 | T2 EI SPAULDING-SUMMIT 13/448 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46102231 | T2 EI SPAULDING-SUMMIT 13/448 RPR GYWW | ICW
LC | 126406837 | 008/042 | T2 EI SLVRD-FULTON JCT 8/42 RPR SPLS | LAKEVLLE | ETL.1610.INSL.NCER | 2023-06-20 | 2023-06-20 | 2024-04-11 | On-time | 2024-06-19 | 69 | 2024-06-20 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Steel | Repair | 46190769 | T2 EI SLVRD-FULTON JCT 8/42 RPR SPLS | ICS
LC | 126436396 | 064/467 | T2 DI BRDGVLLE-CTTNWD 64/467 COTTER | EUREKA | ETL.1110.INSL.NCER | 2023-06-23 | 2023-06-22 |  | Late | 2024-06-21 |  | 2023-12-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45866277 | T2 DI BRDGVLLE-CTTNWD 64/467 COTTER | ICS
LC | 126407095 | 001/014 | T2 WV OLEUM-G #1 001/014 REGRADE | CONCORD | ETL.3150.TOWR | 2023-06-20 | 2023-06-20 | 2024-01-29 | On-time | 2024-06-19 | 142 | 2024-06-20 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46098829 | T2 WV OLEUM-G #1 001/014 REGRADE | ICQ
LC | 126408075 | 004/045 | T2 PIT #5-RND MTN #2 4/045L RMV VEG | TABLEMTN | ETL.5430.POLE.STPS | 2023-06-20 | 2023-06-20 | 2024-04-22 | On-time | 2024-06-19 | 58 | 2024-06-20 | 564 | TLV | PATR | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126436439 | 053/399 | T2 DI BRDGVLLE-CTTNWD 53/399C RPR GYWT | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-23 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46255050 | T2 DI BRDGVLLE-CTTNWD 53/399C RPR GYWT | ICQ
LC | 126436463 | 009/198 | T2 EI HAMILTN BRNCH-CHSTR 9/198 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521274 | T2 EI HAMILTN BRNCH-CHSTR 9/191 RPL POLE | 70Y
LC | 126411815 | 068/489 | T2 EI BRIDGVL-CTTNWD 068/489L RPR GYWW | EUREKA | ETL.1110.POLE.WDPS | 2023-06-20 | 2023-06-20 | 2024-04-03 | On-time | 2024-06-19 | 77 | 2024-06-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171675 | T2 EI BRIDGVL-CTTNWD 068/489L RPR GYWW | ICW
LC | 126411818 | 068/489 | T2 EI BRIDGVL-CTTNWD 068/489R RPR GYWW | EUREKA | ETL.1110.POLE.WDPS | 2023-06-20 | 2023-06-20 | 2024-04-03 | On-time | 2024-06-19 | 77 | 2024-06-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171675 | T2 EI BRIDGVL-CTTNWD 068/489L RPR GYWW | ICW
LC | 126412601 | 005/006 | T2 HUMBOLDT-MAPLE CREEK 5/6 COTTER | EUREKA | ETL.7130.INSL.NCER | 2023-06-20 | 2023-06-20 | 2023-11-21 | On-time | 2024-06-19 | 211 | 2023-09-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45890143 | T2 HUMBOLDT-MAPLE CREEK 5/6 COTTER | ICW
LC | 126436767 | 055/410 | T2 DI BRDGVLLE-CTTNWD 55/410 RPR OPGW | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-23 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46088645 | T2 DI BRDGVLLE-CTTNWD 055/410 RPR OPGW | ICS
LC | 126436848 | 055/407 | T2 DI BRDGVLL-CTTNWD 55/407 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-06-23 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46088644 | T2 DI BRDGVLL-CTTNWD 055/407 RPR OPGW | ICS
LC | 126436867 | 053/399 | T2 DI BRDGVLL-CTTNWD 53/399 RPL INSS | TABLEMTN | ETL.1110.INSL.CERA | 2023-06-23 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509192 | T2 DI BRIDGEVILLE-CTTNWD RPL INSS 9 TWRS | 93K
LC | 126437197 | 009/195 | T2 EI HAMILTN BRNCH-CHSTR 9/195 RPR POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091949 | T2 EI HAMILTN BRNCH-CHSTR 9/195 RPR POLE | ICW
LC | 126412794 | 002/059 | T2 KILARC-DESCHUTES 002/059 INS DMPW | TABLEMTN | ETL.7300.INSL.NCER | 2023-06-20 | 2023-06-20 | 2024-03-19 | On-time | 2024-06-19 | 92 | 2024-06-20 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 46088921 | T2 KILARC-DESCHUTES 002/059 INS DMPW | ICW
LC | 126437484 | A000/013 | T2 DI CARIBOU#2 A000/013 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-06-23 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091879 | T2 DI CARIBOU#2 A000/013 RPR GYWW | ICW
LC | 126437570 | 018/590 | T2 EI SPAULDING-SUMMIT 18/590 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508795 | T2 EI SPAULDING-SUMMIT 18/590 RPL STRW | 70Y
LC | 126412939 | 003/021 | T2 WV LM-NRTH TWR-CHRST A3/021 COMPLETE | CONCORD | ETL.3180.TOWR | 2023-06-20 | 2023-06-20 | 2024-02-29 | On-time | 2024-06-19 | 111 | 2024-06-20 | 543 | TLQ | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46127802 | T2 WV LM-NRTH TWR-CHRST A3/021 RPL HRDS | ICQ
LC | 126437819 | 026/308 | T2 EI DRM-SMMT #1 26/308R RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2023-06-23 | 2023-06-23 | 2024-06-23 | Late | 2024-06-22 | -1 | 2023-12-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098252 | T2 EI DRUM-SUMMIT #1 26/308 RPR GYWW | ICW
LC | 126413075 | 032/265 | T2 EI BRDVLL CTTNWD 032/265L RPR GYWS | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-20 | 2023-06-20 | 2024-06-04 | On-time | 2024-06-19 | 15 | 2024-06-20 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46088659 | T2 EI BRDVLL CTTNWD 032/265L RPR GYWS | ICS
LC | 126437940 | 004/089 | T2 DI DEL MONTE-VIEJO 4/89 RPL STRW | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-06-23 | 2023-06-15 |  | Late | 2024-06-14 |  | 2024-06-15 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515357 | T2 DI DEL MONTE-VIEJO 004/089 RPL STRW | 70Y
LC | 126413284 | 056/010 | T2 EI ELK-GUALALA 056/010 RPL POLE | WILLITS | ETL.8410.POLE.WOOD | 2023-06-20 | 2023-06-20 | 2024-01-16 | On-time | 2024-06-19 | 155 | 2024-06-20 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487383 | T2 DI ELK-GUALALA 057/006 RPL STRW | 70Y
LC | 126438091 | 026/308 | T2 EI DRM-SMMT #1 26/308C RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2023-06-23 | 2023-06-23 | 2024-06-23 | Late | 2024-06-22 | -1 | 2023-12-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098253 | T2 EI DRUM-SUMMIT #1 26/308 RPR GYWW | ICW
LC | 126421719 | 011/090 | T2 DI CRESTA-RIO OSO 011/090 RPL INSS | TABLEMTN | ETL.4590.INSL | 2023-06-21 | 2023-06-20 | 2024-02-21 | On-time | 2024-06-19 | 119 | 2024-06-20 | 532T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513983 | T2 DI CRESTA-RIO OSO RPL INSS 4 TWRS | 93K
LC | 126438209 | 014/343 | T2 EI CTTNWD-BNTN #1 14/343 RPR INSS | TABLEMTN | ETL.6640.INSL.NCER | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46091951 | T2 EI CTTNWD-BNTN #1 14/343 RPR INS | ICW
LC | 126430488 | 000/001 | T2 DI VIEJO-MONTEREY 00/01 RPR STRW | MOSSLNDG | ETL.8270.POLE.WOOD | 2023-06-22 | 2023-06-20 | 2023-09-16 | On-time | 2024-06-19 | 277 | 2024-06-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46003780 | T2 DI VIEJO-MONTEREY 00/01 RPR STRW | ICW
LC | 126438744 | 007/072 | T2 IGNACIO-BOLINAS #1 07/072 RMV ENCR | LAKEVLLE | ETL.7140.POLE.NWOD | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 931 | TLS |  | E - Schd Compl Yr 0 | Open | TR2 | Encroachment | Right of Way | Remove
LC | 126430630 | 000/007 | T2 DI VIEJO-MNTRY-MNTRY 0/7 RMV VEG | MOSSLNDG | ETL.8270.POLE.WOOD | 2023-06-22 | 2023-06-20 | 2024-06-11 | On-time | 2024-06-19 | 8 | 2024-06-20 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126431004 | 001/022A | T2 DI CARIBU-WSTWOOD 1/22A COMPLETE | TABLEMTN | ETL.6300.POLE.NWOD | 2023-06-22 | 2023-06-20 | 2024-05-04 | On-time | 2024-06-19 | 46 | 2024-06-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091885 | T2 DI CARIBU-WSTWOOD 1/22A RPR GYWW | ICW
LC | 126431013 | 007/012 | T2 DI TRINITY-MPL CRK 07/12 RPR ANCW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-22 | 2023-06-20 | 2024-01-22 | On-time | 2024-06-19 | 149 | 2024-06-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46079276 | T2 DI TRINITY-MPL CRK 07/12 RPR ANCW | ICW
LC | 126439606 | 012/420 | T2 EI SPAULDING SUMMIT 12/420 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35508783 | T2 EI SPAULDING-SUMMIT 12/413 RPL POLE | 70Y
LC | 126439669 | 016/518 | T2 EI SPAULDING-SUMMIT 16/518 RPL PL | SACTO | ETL.8060.POLE.WOOD | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508791 | T2 EI SPAULDING-SUMMIT 16/518 RPL PL | 70Y
LC | 126439768 | 024/290A | T2 EI DRUM-SUMMIT #1 24/290A COTTER | SACTO | ETL.1440.INSL.NCER | 2023-06-23 | 2023-06-23 | 2024-06-23 | Late | 2024-06-22 | -1 | 2024-06-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46098256 | T2 EI DRUM-SUMMIT #1 24/290A COTTER | ICW
LC | 126431017 | 007/012 | T2 DI TRINITY-MPL CRK 07/12 RPR GYWW | EUREKA | ETL.8170.POLE.WOOD | 2023-06-22 | 2023-06-20 | 2024-01-22 | On-time | 2024-06-19 | 149 | 2024-06-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46079276 | T2 DI TRINITY-MPL CRK 07/12 RPR ANCW | ICW
LC | 126432585 | 011/092 | T2 DI CRESTA-RIO OSO 11/92 UNBURY | TABLEMTN | ETL.4590.TOWR | 2023-06-23 | 2023-06-20 | 2023-12-28 | On-time | 2024-06-19 | 174 | 2024-06-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46102807 | T2 DI CRESTA-RIO OSO 11/92 UNBURY | ICQ
LC | 126439926 | 012/422 | T2 EI SPAULDING SUMMIT 12/422 RPR JUMP | SACTO | ETL.8060.INSL.CERA | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46102238 | T2 EI SPAULDING SUMMIT 12/422 RPR JUMP | ICW
LC | 126432761 | 012/097 | T2 DI CRESTA-RIO OSO 12/97 RPL INSS | TABLEMTN | ETL.4590.INSL | 2023-06-23 | 2023-06-20 | 2024-02-21 | On-time | 2024-06-19 | 119 | 2024-06-20 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513983 | T2 DI CRESTA-RIO OSO RPL INSS 4 TWRS | 93K
LC | 126433141 | 043/206 | T2 DI IGNACIO-SOBRANTE 43/206 COTTER | CONCORD | ETL.4920.INSL.CERA | 2023-06-23 | 2023-06-20 | 2023-09-15 | On-time | 2024-06-19 | 278 | 2023-09-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45870832 | T2 DI IGNACIO-SOBRANTE 43/206 COTTER | ICS
LC | 126433202 | 013/087 | T2 DI JFFSN-MRTN 13/87 RPR OPGW | METCALF | ETL.5710.POLE.NWOD | 2023-06-23 | 2023-06-20 | 2024-06-11 | On-time | 2024-06-19 | 8 | 2024-06-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46062383 | T2 DI JFFSN-MRTN 13/87 RPR SHLS | ICS
LC | 126439948 | 010/075A | T2 EI CARIBOU-TABLE MTN 10/75A RMV VEG | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126434395 | 011/056 | T2 DI TULUCAY VACA 13/056 RPL DAMS | SACTO | ETL.5800.INSL | 2023-06-23 | 2023-06-20 | 2023-11-15 | On-time | 2024-06-19 | 217 | 2024-06-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 45985240 | T2 DI TULUCAY VACA 13/056 RPL DAMS | ICS
LC | 126434715 | 014/097 | T2 DI MLLBR-SNTH LN 14/97 RPR STRT | METCALF | ETL.7570.POLE.NWOD | 2023-06-23 | 2023-06-20 | 2024-04-29 | On-time | 2024-06-19 | 51 | 2024-06-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46101936 | T2 DI MLLBR-SNTH LN 14/97 RPR STRT | ICQ
LC | 126435134 | 020/005 | T2 DI TRNTY-MPL CRK 20/5 RPR INSW | EUREKA | ETL.8170.INSL.NCER | 2023-06-23 | 2023-06-20 | 2024-06-13 | On-time | 2024-06-19 | 6 | 2024-06-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46172027 | T2 DI TRNTY-MPL CRK 20/5 RPR INSW | ICW
LC | 126436505 | 001/010 | T2 DI TRINITY-MC 1/10 RPL INSW | EUREKA | ETL.8170.INSL.NCER | 2023-06-23 | 2023-06-20 | 2024-01-18 | On-time | 2024-06-19 | 153 | 2024-06-20 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35485474 | T2 DI TRINITY-MC 1/10 RPL INSW*GC | 93I
LC | 126439974 | 024/290B | T2 EI DRUM-SUMMIT #1 24/290B COA | SACTO | ETL.1440.POLE.NWOD | 2023-06-23 | 2023-06-23 | 2024-06-23 | Late | 2024-06-22 | -1 | 2024-06-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46098257 | T2 EI DRUM-SUMMIT #1 024/290B RPR ANCW | ICW
LC | 126440067 | 024/290C | T2 EI DRUM-SUMMIT #1 24/290C COA | SACTO | ETL.1440.POLE.NWOD | 2023-06-23 | 2023-06-23 | 2024-06-23 | Late | 2024-06-22 | -1 | 2024-06-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46268816 | T2 EI DRUM-SUMMIT #1 24/290C COA | ICW
LC | 126436689 | 021/004 | T2 DI BRIDGEVLL-GRBR 21/4 RPR GYWW | EUREKA | ETL.6220.POLE.NWOD | 2023-06-23 | 2023-06-20 | 2023-09-22 | On-time | 2024-06-19 | 271 | 2023-12-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45890181 | T2 DI BRIDGEVLL-GRBR 21/4 RPR GYWW | ICW
LC | 126440167 | 010/081A | T2 EI CARIBOU-TABLE MTN 010/81A RPR FOND | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46127950 | T2 EI CARIBOU-TABLE MTN 010/81A RPR FOND | ICQ
LC | 126440216 | 010/081C | T2 EI CRIBOU-TABLE MTN 10/081C RPR FOND | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46127951 | T2 EI CRIBOU-TABLE MTN 10/081C RPR FOND | ICQ
LC | 126440558 | 009/071 | T2 EI CARIBOU-TABLE MTN 09/71 RMV VEG | TABLEMTN | ETL.4440.TOWR | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation-Tower | Cage Clearing
LC | 126440559 | 009/072 | T2 EI CARIBOU-TABLE MTN 09/72 RMV VEG | TABLEMTN | ETL.4440.TOWR | 2023-06-23 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation-Tower | Cage Clearing
LC | 126437429 | 005/026 | T2 DI TULUCAY-VACA 005/026 RPL INSS | SACTO | ETL.5800.INSL | 2023-06-23 | 2023-06-20 | 2024-03-14 | On-time | 2024-06-19 | 97 | 2024-06-20 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672705 | T2 DI TULUCAY-VACA RPL INSS | 93K
LC | 126437923 | 019/221 | T2 DI DRUM-SUMMIT#1 19/221R RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2023-06-23 | 2023-06-20 | 2023-08-09 | On-time | 2024-06-19 | 315 | 2023-09-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45872468 | T2 DI DRUM-SUMMIT#1 19/221R RPR GYWW | ICW
LC | 126438074 | 022/179 | T2 DI CRST-RI OSO 22/179 RPL INSS | TABLEMTN | ETL.4590.INSL.NCER | 2023-06-23 | 2023-06-20 | 2024-02-23 | On-time | 2024-06-19 | 117 | 2024-06-20 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513983 | T2 DI CRESTA-RIO OSO RPL INSS 4 TWRS | 93K
LC | 126457067 | 014/093 | T2 DI JEFFERSON-MARTIN 014/093 RPR OPGW | METCALF | ETL.5710.POLE.NWOD | 2023-06-26 | 2023-06-20 | 2023-09-13 | On-time | 2024-06-19 | 280 | 2023-09-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45864870 | T2 DI JEFFERSON-MARTIN 014/093 RPR OPGW | ICS
LC | 126457136 | 014/093 | T2 DI JEFFERSON-MARTIN 014/093 COTTER | METCALF | ETL.5710.INSL.NCER | 2023-06-26 | 2023-06-20 | 2023-09-13 | On-time | 2024-06-19 | 280 | 2024-06-20 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45978509 | T2 DI JEFFERSON-MARTIN 014/093 COTTER | ICS
LC | 126442428 | 007/176 | T2 EI CTTNWD-BNTN #1 7/176 RPL HRDW | TABLEMTN | ETL.6640.INSL.NCER | 2023-06-24 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46091956 | T2 EI CTTNWD-BNTN #1 7/176 RPL HRDW | ICW
LC | 126457484 | 020/239A | T2 DI DRUM-SUMMIT #2 20/239A RPR GYWW | SACTO | ETL.1450.POLE.WOOD | 2023-06-26 | 2023-06-20 | 2024-06-16 | On-time | 2024-06-19 | 3 | 2024-06-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098388 | T2 DI DRUM-SUMMIT #2 20/239A RPR GYWW | ICW
LC | 126443274 | 012/429 | T2 EI SPAULDING-SUMMIT 12/429 RPR INSW | SACTO | ETL.8060.INSL.NCER | 2023-06-24 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46102234 | T2 EI SPAULDING-SUMMIT 12/429 RPR INSW | ICW
LC | 126443508 | 017/531 | T2 EI SPAULDING-SUMMIT 17/531 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2023-06-24 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508793 | T2 EI SPAULDING-SUMMIT 17/531 RPL PL | 70Y
LC | 126444180 | 000/005 | T2 EI BCKS CRK-RCK CRK-CRST 0/5 RPR JMPW | TABLEMTN | ETL.4430.INSL.NCER | 2023-06-24 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46087811 | T2 EI BCKS CRK-RCK CRK-CRST 0/5 RPL INSS | ICS
LC | 126444327 | 024/283 | T2 EI DRUM-SUMMIT #1 24/283R RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2023-06-24 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126465995 | 040/193 | T2 DI IGNCO-SBRNTE 40/193 RPL INSS | CONCORD | ETL.4920.INSL.CERA | 2023-06-27 | 2023-06-20 | 2024-03-17 | On-time | 2024-06-19 | 94 | 2024-06-20 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671638 | T2 DI IGNCO-SBRNTE RPL INSS IN 6 TWRS. | 93K
LC | 126466405 | 011/095 | T2 DI CRESTA-RIO OSO 11/95 RPR FOND | TABLEMTN | ETL.4590.TOWR | 2023-06-27 | 2023-06-20 | 2024-06-07 | On-time | 2024-06-19 | 12 | 2024-06-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46128020 | T2 DI CRESTA-RIO OSO 11/95 RPR FOND | ICQ
LC | 126466406 | 011/095 | T2 DI CRESTA-RIO OSO 11/95 RPR STRT | TABLEMTN | ETL.4590.TOWR | 2023-06-27 | 2023-06-20 | 2023-08-18 | On-time | 2024-06-19 | 306 | 2023-09-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45866427 | T2 DI CRESTA-RIO OSO 11/95 RPR STRT | ICQ
LC | 126470066 | 17 | T2 DI MILLBR-SNTH LN 14/91 RPL PT | METCALF | ETL.7570.SWIT | 2023-06-28 | 2023-06-20 | 2023-10-10 | On-time | 2024-06-19 | 253 | 2024-06-20 | 435 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Steel | Replace | 31656321 | T2 DI MILLBR-SNTH LN 14/91 RPL SWITCH | 93S
LC | 126446497 | 024/287A | T2 EI DRUM-SUMMIT #2 024/287A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-25 | 2023-06-25 |  | Late | 2024-06-24 |  | 2023-12-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098259 | T2 EI DRUM-SUMMIT #2 024/287A RPR GYWW | ICW
LC | 126477387 | 018/208 | T2 DI DRUM-SUMMIT #1 18/208C UNBRY ANCW | SACTO | ETL.1440.POLE.WDPS | 2023-06-29 | 2023-06-20 | 2023-08-05 | On-time | 2024-06-19 | 319 | 2023-12-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45872474 | T2 DI DRUM-SUMMIT #1 18/208C UNBRY ANCW | ICW
LC | 126588607 | 032/265 | T2 EI BRDGVLL-CTTNWD 032/265R RPR GYWW | TABLEMTN | ETL.1110.POLE.STPS | 2023-07-14 | 2023-06-20 | 2024-06-04 | On-time | 2024-06-19 | 15 | 2024-06-20 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46093345 | T2 EI BRDGVLL-CTTNWD 032/265R RPR GYWW | ICW
LC | 126415187 | 040/318 | T2 EI BRDGVL-CTNWD 40/318 COTTER | TABLEMTN | ETL.1110.INSL.CERA | 2023-06-21 | 2023-06-21 | 2023-08-15 | On-time | 2024-06-20 | 310 | 2023-09-21 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45881437 | T2 EI BRDGVL-CTNWD 40/318 COTTER | ICS
LC | 126415444 | :017/007 | T2 EI EAGLE ROCK-CORTINA :017/007 RPR PL | WILLITS | ETL.1470.POLE.WOOD | 2023-06-21 | 2023-06-21 | 2024-05-15 | On-time | 2024-06-20 | 36 | 2024-06-21 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46176327 | T2 EI EAGLE ROCK-CORTINA :017/007 RPR PL | ICW
LC | 126446930 | 002/074 | T2 EI HAMILTON BRNCH-CHSTR 2/74 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-25 | 2023-06-25 |  | Late | 2024-06-24 |  | 2024-06-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521272 | T2 EI HAMILTON BRNCH-CHSTR 2/74 RPL POLE | 70Y
LC | 126415565 | 005/032 | T2 WV MONTA VISTA-CYTE SS 5/32 RPR INSS | MOSSLNDG | ETL.5090.INSL.CERA | 2023-06-21 | 2023-06-21 | 2024-03-11 | On-time | 2024-06-20 | 101 | 2024-06-21 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 31616428 | T2 MONTA VISTA-CYTE SS RPL INSS 3TWR | 93K
LC | 126416722 | 159 | T2 SOBRNTE-GRZLY-CLARMNT #1 0/6 INS DMPS | CONCORD | ETL.3740.SWIT | 2023-06-21 | 2023-06-21 | 2024-04-09 | On-time | 2024-06-20 | 72 | 2024-06-21 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 45999076 | T2 SOBRNTE-GRZLY-CLARMNT #1 0/6 INS DMPS | ICS
LC | 126416755 | 000/008 | T2 EI PALERMO-OROVILLE #2 0/8 RPL DMPS | TABLEMTN | ETL.7740.INSL.CERA | 2023-06-21 | 2023-06-21 | 2023-07-19 | On-time | 2024-06-20 | 337 | 2024-06-21 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 45895045 | T2 EI PALERMO-OROVILLE #2 0/8 RPL DMPS | ICS
LC | 126421494 | 020/141 | T2 EI CARIBOU-TABLE MTN 020/141 UNBURY | TABLEMTN | ETL.4440.TOWR | 2023-06-21 | 2023-06-21 | 2024-04-11 | On-time | 2024-06-20 | 70 | 2024-06-21 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46127947 | T2 EI CARIBOU-TABLE MTN 020/141 UNBURY | ICQ
LC | 126421516 | 019/138 | T2 EI CARIBOU-TABLE MTN 019/138 INS DMPS | TABLEMTN | ETL.4440.INSL.CERA | 2023-06-21 | 2023-06-21 | 2024-06-07 | On-time | 2024-06-20 | 13 | 2024-06-21 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Steel | Install | 46088169 | T2 EI CARIBOU-TABLE MTN 019/138 INS DMPS | ICS
LC | 126447446 | 018/582 | T2 EI SPAULDING-SUMMIT 18/582 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2023-06-25 | 2023-06-25 |  | Late | 2024-06-24 |  | 2024-06-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508794 | T2 EI SPAULDING-SUMMIT 18/582 RPL STRW | 70Y
LC | 126421723 | 014/104A | T2 EI CARIBOU-TABLE MTN 14/104A COTTER | TABLEMTN | ETL.4440.INSL.CERA | 2023-06-21 | 2023-06-21 | 2024-06-07 | On-time | 2024-06-20 | 13 | 2024-06-21 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46088168 | T2 EI CARIBOU-TABLE MTN 14/104A COTTER | ICS
LC | 126421750 | 003/124 | T2 DI SPAULDNG-SUMMIT 3/124 COMPLETED | SACTO | ETL.8060.INSL.NCER | 2023-06-21 | 2023-06-21 | 2024-06-17 | On-time | 2024-06-20 | 3 | 2024-06-21 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46102228 | T2 DI SPAULDNG-SUMMIT 3/124 RPR INSW | ICW
LC | 126434559 | 001/015 | T2 DI PIT #5-RND MTN #1 1/15 RPR OPGW | TABLEMTN | ETL.5420.POLE.STPS | 2023-06-23 | 2023-06-21 | 2024-01-08 | On-time | 2024-06-20 | 164 | 2024-06-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46088167 | T2 DI PIT #5-RND MTN #1 1/15 RPR OPGW | ICS
LC | 126448585 | 021/248 | T2 EI DRUM-SUMMIT #1 021/248L RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2023-06-25 | 2023-06-25 |  | Late | 2024-06-24 |  | 2024-06-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126449023 | 025/014 | T2 RIO DELL JCT-BRDGEVLLE 25/14 RPL POLE | EUREKA | ETL.7850.POLE.WOOD | 2023-06-25 | 2023-06-25 |  | Late | 2024-06-24 |  | 2024-06-25 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31655105 | T2 RIO DELL JCT-BRDGEVLLE 25/14 RPL POLE | 70Y
LC | 126449062 | 025/013 | T2 RIO DELL JCT-BRDGEVLLE 25/13 RPL POLE | EUREKA | ETL.7850.POLE.WOOD | 2023-06-25 | 2023-06-25 |  | Late | 2024-06-24 |  | 2024-06-25 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35502397 | T2 RIO DELL JCT-BRDGEVLLE 25/13 RPL POLE | 70Y
LC | 126449270 | 018/577 | T2 EI SPAULDING-SUMMIT 18/577 RPR ANCW | SACTO | ETL.8060.POLE.WOOD | 2023-06-25 | 2023-06-25 |  | Late | 2024-06-24 |  | 2024-06-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46102235 | T2 EI SPAULDING-SUMMIT 18/577 RPR ANCW | ICW
LC | 126449272 | 018/584 | T2 EI SPAULDING-SUMMIT 18/584 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2023-06-25 | 2023-06-25 |  | Late | 2024-06-24 |  | 2024-06-25 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508794 | T2 EI SPAULDING-SUMMIT 18/582 RPL STRW | 70Y
LC | 126451347 | 025/009 | T2 HARTLEY-CLEARLAKE 25/9 RPL POLE | WILLITS | ETL.7515.POLE.WOOD | 2023-06-26 | 2023-05-12 |  | Late | 2024-05-11 |  | 2024-05-12 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35488477 | T2 HARTLEY-CLEARLAKE 25/9 RPL POLE | 70Y
LC | 126435139 | 000/005 | T2 DI MELONES-RACETRACK 0/5 COTTER | VICTOR | ETL.2400.INSL.CERA | 2023-06-23 | 2023-06-21 | 2023-07-31 | On-time | 2024-06-20 | 325 | 2023-09-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45872384 | T2 DI MELONES-RACETRACK 0/5 COTTER | ICW
LC | 126435485 | 004/098 | T2 DI CARIBOU-PLMS JCT 4/098 RPR GYWW | TABLEMTN | ETL.6290.POLE.NWOD | 2023-06-23 | 2023-06-21 | 2024-05-06 | On-time | 2024-06-20 | 45 | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091892 | T2 DI CARIBOU-PLMS JCT 4/098 RPR GYWW | ICW
LC | 126435489 | 004/098 | T2 DI CARIBOU-PLMS JCT 4/098 RPR JMPW | TABLEMTN | ETL.6290.INSL.NCER | 2023-06-23 | 2023-06-21 | 2024-05-06 | On-time | 2024-06-20 | 45 | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46091893 | T2 DI CARIBOU-PLMS JCT 4/098 RPR JMPW | ICW
LC | 126435779 | 000/004 | T2 DI MELONES-RACETRACK 0/4 COTTER | VICTOR | ETL.2400.INSL.CERA | 2023-06-23 | 2023-06-21 | 2023-07-31 | On-time | 2024-06-20 | 325 | 2023-09-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45872382 | T2 DI MELONES-RACETRACK 0/4 COTTER | ICW
LC | 126435984 | 045/219 | T2 DI LKVLL-SBRNT #2 45/219 RPR INSS | LAKEVLLE | ETL.4960.INSL | 2023-06-23 | 2023-06-21 | 2023-09-22 | On-time | 2024-06-20 | 272 | 2023-09-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45861685 | T2 DI LKVLL-SBRNT #2 45/219 RPR INSS | ICS
LC | 126438889 | 044/212 | T2 DI LKVL-SBRNTE #2 44/212 RPL INSS | CONCORD | ETL.4960.INSL | 2023-06-23 | 2023-06-21 | 2024-05-22 | On-time | 2024-06-20 | 29 | 2024-06-21 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671786 | DI LKVL-SBRNTE #2 RPL INSS IN 2 WRS. | 93K
LC | 126454583 | 000/001 | T2 CAPE HORN TAP 0/1 CANCEL | SACTO | ETL.6761.POLE.WOOD | 2023-06-26 | 2023-05-19 |  | Late | 2024-05-18 |  | 2024-05-19 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506911 | T2 CAPE HORN TAP 0/1 RPL PL | 70Y
LC | 126456913 | ;000/009 | T2 DI SNTH LN-HLF MN BY ;0/9 RPR ANCW | METCALF | ETL.7212.POLE.WDPS | 2023-06-26 | 2023-06-21 | 2024-03-09 | On-time | 2024-06-20 | 103 | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46080094 | T2 DI SNTH LN-HLF MN BY ;0/9 RPR ANCW | ICW
LC | 126454708 | 025/006 | T2 HARTLEY-CLEARLAKE 25/6 RPR POLE | WILLITS | ETL.7515.POLE.WOOD | 2023-06-26 | 2023-05-26 |  | Late | 2024-05-25 |  | 2024-05-26 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46227565 | T2 HARTLEY-CLEARLAKE 25/6 RPR POLE | ICW
LC | 126455035 | 018/000 | T2 KONOCTI MIDDLETOWN 18/0 RPR GYWW | WILLITS | ETL.6380.POLE.NWOD | 2023-06-26 | 2023-06-01 |  | Late | 2024-05-31 |  | 2024-06-01 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46213763 | T2 KONOCTI MIDDLETOWN 18/0 RPR GYWW | ICW
LC | 126456681 | 055/386 | T2 EI PARADISE-TABLE MTN 55/386 RPL INSS | TABLEMTN | ETL.4316.INSL.CERA | 2023-06-26 | 2023-06-26 |  | Late | 2024-06-25 |  | 2024-06-26 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35550238 | T2 EI PARADISE-TABLE MTN 55/386 RPL INSS | 93K
LC | 126456765 | 041/788 | T2 DI HT CRK#1-WSTWD 041/788 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-26 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518534 | T2 DI HT CRK#1-WSTWD 041/788 RPL STRW | 70Y
LC | 126456922 | 006/100 | T2 DI SAN MTO-HLLSDL JCT 6/100C RPL STRW | METCALF | ETL.7950.POLE.WDPS | 2023-06-26 | 2023-06-21 | 2024-04-19 | On-time | 2024-06-20 | 62 | 2024-06-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35511447 | T2 DI SAN MTO-HLLSDL JCT 6/100C RPL STRW | 70Y
LC | 126456923 | 006/100 | T2 DI SAN MTO-HLLSDL JCT 6/100R RPL STRW | METCALF | ETL.7950.POLE.WDPS | 2023-06-26 | 2023-06-21 | 2024-04-19 | On-time | 2024-06-20 | 62 | 2024-06-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35511447 | T2 DI SAN MTO-HLLSDL JCT 6/100C RPL STRW | 70Y
LC | 126456927 | 006/100 | T2 DI SAN MTO-HLLSDL JCT 6/100L RPL STRW | METCALF | ETL.7950.POLE.WDPS | 2023-06-26 | 2023-06-21 | 2024-04-19 | On-time | 2024-06-20 | 62 | 2024-06-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35511447 | T2 DI SAN MTO-HLLSDL JCT 6/100C RPL STRW | 70Y
LC | 126456963 | ;001/011 | T2 DI SNTH LN-HLF MN BY ;1/11 RPL HRDW | METCALF | ETL.7212.POLE.WOOD | 2023-06-26 | 2023-06-21 | 2024-03-09 | On-time | 2024-06-20 | 103 | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46080095 | T2 DI SNTH LN-HLF MN BY ;1/11 RPL HRDW | ICW
LC | 126456928 | 005/023 | T2 DI HMBLT BAY-HMBLT #1 5/23 RMV VEG | EUREKA | ETL.1800.TOWR | 2023-06-26 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126457231 | 004/099 | T2 DI CARIBOU-PLUMAS JCT 4/99 RPR GYWW | TABLEMTN | ETL.6290.POLE.NWOD | 2023-06-26 | 2023-06-21 | 2023-09-23 | On-time | 2024-06-20 | 271 | 2023-12-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45866272 | T2 DI CARIBOU-PLUMAS JCT 4/99 RPR GYWW | ICW
LC | 126457397 | 007/009 | T2 DI TULUCAY-NAPA #1 7/9 RPR ANCW | LAKEVLLE | ETL.8180.POLE.WOOD | 2023-06-26 | 2023-06-21 | 2024-01-15 | On-time | 2024-06-20 | 157 | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46096643 | T2 DI TULUCAY-NAPA #1 7/9 RPR ANCW | ICW
LC | 126457414 | 047/226 | T2 DI LAKEVIL-SOBRANT #2 47/226 RPL INSS | CONCORD | ETL.4960.INSL.CERA | 2023-06-26 | 2023-06-21 | 2024-05-22 | On-time | 2024-06-20 | 29 | 2024-06-21 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671786 | DI LKVL-SBRNTE #2 RPL INSS IN 2 WRS. | 93K
LC | 126457556 | 021/103 | T2 DI TIDEWATR-SOBRANTE 21/103 RPR SHLDS | CONCORD | ETL.5770.TOWR | 2023-06-26 | 2023-06-21 | 2024-05-05 | On-time | 2024-06-20 | 46 | 2024-06-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45999078 | T2 DI TIDEWATR-SOBRANTE 21/103 RPR SHLDS | ICS
LC | 126457582 | :000/005 | T2 DI STNSLS MLNS SS MNTC :0/5 BNT STEEL | VICTOR | ETL.3830.TOWR | 2023-06-26 | 2023-06-21 | 2023-11-28 | On-time | 2024-06-20 | 205 | 2023-09-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45870833 | T2 DI STNSLS MLNS SS MNTC :0/5 BNT STEEL | ICQ
LC | 126457107 | 071/361 | T2 DI MALIN-RND MTN #2 71/361 RPR STRT | TABLEMTN | ETL.6020.TOWR | 2023-06-26 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46252359 | T2 DI MALIN-RND MTN #2 71/361 RPR STRT | ICQ
LC | 126457131 | 000/008 | T2 DI VIEJO-MONTEREY- 00/08 RPR INSW | MOSSLNDG | ETL.8270.INSL | 2023-06-26 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46081733 | T2 DI VIEJO-MONTEREY- 00/08 RPR INSW | ICW
LC | 126465906 | ;000/006 | T2 DI SNEATH LNE-HLF MN BY ;0/6 RPL INSW | METCALF | ETL.7212.INSL.NCER | 2023-06-27 | 2023-06-21 | 2024-03-09 | On-time | 2024-06-20 | 103 | 2024-06-21 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35533879 | T2 DI SNEATH LNE-HLF MN BY ;0/6 RPL INSW | 93I
LC | 126457193 | ;000/019 | T2 DI CARIBOU #2 ;000/019 RPR GYW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-06-26 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091897 | T2DI CARIBOU-PLUMAS JCT 0/19 RPR GYW | ICW
LC | 126465950 | 020/097 | T2 DI TDWTR-SBRNT 020/097 COTTER | CONCORD | ETL.5670.INSL | 2023-06-27 | 2023-06-21 | 2023-12-09 | On-time | 2024-06-20 | 194 | 2024-06-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45989101 | T2 DI TDWTR-SBRNT 020/097 COTTER | ICS
LC | 126457239 | 029/009 | T2 DI PHILO JCT-ELK- 29/09 RPL ANCW | WILLITS | ETL.7780.POLE.WOOD | 2023-06-26 | 2023-06-16 | 2024-06-20 | Late | 2024-06-15 | -5 | 2024-06-16 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35522276 | T2 DI PHILO JCT-ELK- 29/09 RPL ANCW | 93E
LC | 126457262 | 002/043 | T2 DI CARIBOU-WSTWD 002/043 RPL STRW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-26 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35519109 | T2 DI CARIBOU-WSTWD 002/043 RPL STRW | 70Y
LC | 126466182 | 011/054 | T2 DI VACA-LKVLE 11/54 RPL INSS | LAKEVLLE | ETL.5840.INSL.CERA | 2023-06-27 | 2023-06-21 | 2024-04-18 | On-time | 2024-06-20 | 63 | 2024-06-21 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31678228 | T2 WV VACA-LAKEVILLE #1 RPL INSS IN 4 TW | 93K
LC | 126457306 | 018/086 | T2 DI VACA-LAKEVILLE #1 18/86 RMV VEG | LAKEVLLE | ETL.5840.TOWR | 2023-06-26 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126466395 | 069/501 | T2 DI BRDGVLL-CTTNWD 069/501 RPR SHLW | EUREKA | ETL.1110.POLE.WDPS | 2023-06-27 | 2023-06-21 | 2024-04-02 | On-time | 2024-06-20 | 79 | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 46171678 | T2 DI BRDGVLL-CTTNWD 069/501 RPR SHLW | ICW
LC | 126466421 | 004/091 | T2 DI CARIBOU-PLMAS JCT 4/91 RMV STEP | TABLEMTN | ETL.6290.POLE.NWOD | 2023-06-27 | 2023-06-21 | 2024-05-06 | On-time | 2024-06-20 | 45 | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46091891 | T2 DI CARIBOU-PLMAS JCT 4/91 RMV STEP | ICW
LC | 126457336 | 065/471 | T2 DI BRIDGEVILLE-CTTNWD 65/471 INS HRDT | EUREKA | ETL.1110.TOWR | 2023-06-26 | 2023-06-22 | 2024-06-26 | Late | 2024-06-21 | -5 | 2024-06-22 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Tower | Install | 46125099 | T2 DI BRIDGEVILLE-CTTNWD 65/471 INS HRDT | ICQ
LC | 126457344 | 073/526 | T2 DI BRIDGVL-COTTONWD 73/526 RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-06-26 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171730 | T2 DI BRIDGVL-COTTONWD 73/526 RPR GYWW | ICW
LC | 126457346 | 073/526 | T2 DI BRIDGVL-COTTONWD 73/526 RPR OPGW | EUREKA | ETL.1110.POLE.STPS | 2023-06-26 | 2023-06-21 |  | Late | 2024-06-20 |  | 2023-09-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Wood | Repair | 45866332 | T2 DI BRIDGVL-COTTONWD 73/526 RPR OPGW | ICW
LC | 126466424 | 075/540 | T2 DI BRDGVL-CTNWD 75/540 RPL HRDT | EUREKA | ETL.1110.TOWR | 2023-06-27 | 2023-06-21 | 2024-06-13 | On-time | 2024-06-20 | 7 | 2024-06-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46125094 | T2 DI BRDGVL-CTNWD 75/540 RPL HRDT | ICQ
LC | 126472722 | 021/101 | T2 DI TDWTR SBRNTE 21/101 RMV NEST | CONCORD | ETL.5770.TOWR | 2023-06-28 | 2023-06-21 | 2023-12-06 | On-time | 2024-06-20 | 197 | 2024-06-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 45999141 | T2 DI TDWTR SBRNTE 21/101 RMV NEST | ICS
LC | 126472880 | 021/101 | T2NT DI TDWTR SBRNTE 21/101 RMV VEG | CONCORD | ETL.5770.TOWR | 2023-06-28 | 2023-06-21 | 2024-05-24 | On-time | 2024-06-20 | 27 | 2024-06-21 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation-Tower | Cage Clearing
LC | 126472881 | 021/101 | T2 DI TESORO-SBRNTE 21/101 RPL INSS | CONCORD | ETL.5670.INSL | 2023-06-28 | 2023-06-21 | 2024-03-11 | On-time | 2024-06-20 | 101 | 2024-06-21 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671687 | T2 DI TESORO-SBRNTE 21/101 RPL INSS | 93K
LC | 126457415 | 047/226 | T2 DI IGNACIO-SOBRANTE 47/226 RPL INSS | CONCORD | ETL.4920.INSL.CERA | 2023-06-26 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671638 | T2 DI IGNCO-SBRNTE RPL INSS IN 6 TWRS. | 93K
LC | 126473249 | ;000/010 | T2 DI SNTH LN-HLF MN BY ;0/10 RPL STRW | METCALF | ETL.7212.POLE.WOOD | 2023-06-28 | 2023-06-21 | 2024-05-21 | On-time | 2024-06-20 | 30 | 2024-06-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35506432 | T2 DI SNTH LN-HLF MN BY ;0/10 RPL STRW | 70Y
LC | 126457440 | 080/567 | T2 DI BRDGVLE-CTNWD 80/567 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-26 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45870608 | T2 DI BRDGVLE-CTNWD 80/567 RPR OPGW | ICS
LC | 126474727 | 038/176 | T2 DI IGNCO-SBRNT 038/176 RPL INSS | CONCORD | ETL.4920.INSL.CERA | 2023-06-28 | 2023-06-21 | 2024-03-17 | On-time | 2024-06-20 | 95 | 2024-06-21 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671638 | T2 DI IGNCO-SBRNTE RPL INSS IN 6 TWRS. | 93K
LC | 126457478 | 000/008 | T2 DI BALCH-SANGER 0/8 RMV VEG | FRESNO | ETL.1050.TOWR | 2023-06-26 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126474859 | ;001/012 | T2 DI SNTH LN-HALF MN BY ;01/12 RPR GYWW | METCALF | ETL.7212.POLE.WOOD | 2023-06-28 | 2023-06-21 | 2024-03-07 | On-time | 2024-06-20 | 105 | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46080097 | T2 DI SNTH LN-HALF MN BY ;01/12 RPR GYWW | ICW
LC | 126474890 | ;001/012 | T2 DI SNTH LN-HALF MN BY ;01/12 RPR SPLW | METCALF | ETL.7212.INSL.NCER | 2023-06-28 | 2023-06-21 | 2024-03-07 | On-time | 2024-06-20 | 105 | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46080098 | T2 DI SNTH LN-HALF MN BY ;01/12 RPR SPLW | ICW
LC | 126457485 | C010/041 | T2 DI MOSS LANDING-COBURN C10/41 RMV VEG | MOSSLNDG | ETL.5330.TOWR | 2023-06-26 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126476566 | 068/495 | T2 DI BRIDGEVILLE-CTTNWD 68/495 RPR OPGW | EUREKA | ETL.1110.POLE.WDPS | 2023-06-29 | 2023-06-21 | 2024-04-02 | On-time | 2024-06-20 | 79 | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 46132883 | T2 DI BRIDGEVILLE-CTTNWD 68/495 RPR OPGW | ICW
LC | 126479583 | 034/000 | T2 DI PHILO JCT ELK 34/000 RPL ANCW | WILLITS | ETL.7780.POLE.WOOD | 2023-06-29 | 2023-06-21 | 2024-05-21 | On-time | 2024-06-20 | 30 | 2024-06-21 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35499972 | T2 DI PHILO JCT ELK 34/000 RPL ANCW | 93E
LC | 126481574 | 047/227 | T2 DI IGNCO-SBRNT 047/227 RPL INSS | CONCORD | ETL.4920.INSL.CERA | 2023-06-29 | 2023-06-21 | 2024-03-19 | On-time | 2024-06-20 | 93 | 2024-06-21 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671638 | T2 DI IGNCO-SBRNTE RPL INSS IN 6 TWRS. | 93K
LC | 126481610 | 047/227 | T2 DI LKVLL-SBRNT #2 047/227 RPR INSS | CONCORD | ETL.4960.INSL | 2023-06-29 | 2023-06-21 | 2024-05-25 | On-time | 2024-06-20 | 26 | 2024-06-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45997241 | T2 DI LKVLL-SBRNT #2 047/227 RPR INSS | ICS
LC | 126457581 | :000/005 | T2 DI STNSLS MLNS SS MNTC :0/5 RMV VEG | VICTOR | ETL.3830.TOWR | 2023-06-26 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126481960 | 008/008 | T2 DI TULUCAY-NAPA #1 08/08 RMV VEG | LAKEVLLE | ETL.8180.POLE.NWOD | 2023-06-29 | 2023-06-21 | 2024-06-06 | On-time | 2024-06-20 | 14 | 2024-06-21 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126481968 | 008/005 | T2 DI TULUCAY-NAPA #1 08/05 RPR STRW | LAKEVLLE | ETL.8180.POLE.WOOD | 2023-06-29 | 2023-06-21 | 2024-01-16 | On-time | 2024-06-20 | 156 | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46096646 | T2 DI TULUCAY-NAPA #1 08/05 RPR STRW | ICW
LC | 126460210 | 071/358 | T2 DI MALIN RND MTN#2 71/358 RPR GYWT | TABLEMTN | ETL.6020.TOWR | 2023-06-27 | 2023-06-13 |  | Late | 2024-06-12 |  | 2024-06-13 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46262507 | T2 DI MALIN RND MTN#2 71/358 RPR GYWT | ICQ
LC | 126423988 | 053/396 | T2 BRIDGEVILLE-CTNWD 53/396 RPR INSS | TABLEMTN | ETL.1110.INSL | 2023-06-22 | 2023-06-22 | 2023-08-26 | On-time | 2024-06-21 | 300 | 2023-12-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45866328 | T2 BRIDGEVILLE-CTNWD 53/396 RPR INSS | ICS
LC | 126424172 | 025/008 | T2 EI MONTE R-FRT RSS 025/008 INS HRDW | LAKEVLLE | ETL.6979.POLE.WOOD | 2023-06-22 | 2023-06-22 | 2023-08-09 | On-time | 2024-06-21 | 317 | 2024-06-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Wood | Install | 45659893 | DI MONTE RIO-FORT ROSS 23/04 RPR GYWW | ICW
LC | 126461546 | 009/191 | T2 EI HAMILTN BRNCH-CHSTR 9/191 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-27 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521274 | T2 EI HAMILTN BRNCH-CHSTR 9/191 RPL POLE | 70Y
LC | 126461722 | 000/019 | T2 WV DELTA-MTN GATE JCT 0/19 RPL STRW | TABLEMTN | ETL.6750.POLE.WOOD | 2023-06-27 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508687 | T2 WV DELTA-MTN GATE JCT 0/19 RPL STRW | 70Y
LC | 126462147 | 009/190 | T2 EI HAMILTN BRNCH-CHSTR 9/190 RPR STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-27 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091964 | T2 EI HAMILTN BRNCH-CHSTR 9/190 RPR POLE | ICW
LC | 126462433 | 008/189 | T2 EI HAMILTN BRNCH-CHSTR 8/189 RPR INSW | TABLEMTN | ETL.7000.INSL.NCER | 2023-06-27 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46091963 | T2 EI HAMILTN BRNCH-CHSTR 8/189 RPR INSW | ICW
LC | 126464023 | 005/062 | T2 EI IGNACIO-BOLINAS #2 5/062 RPL POLE | LAKEVLLE | ETL.7180.POLE.WOOD | 2023-06-27 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527646 | T2 EI IGNACIO-BOLINAS #2 5/062 RPL POLE | 70Y
LC | 126464176 | 018/589 | T2 EI SPAULDING-SUMMIT 18/589 RPR JUMW | SACTO | ETL.8060.INSL.NCER | 2023-06-27 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46102236 | T2 EI SPAULDING-SUMMIT 18/589 RPR JMPW | ICW
LC | 126464693 | 003/012 | T2 LOWR LAK-HOMSTAK 3/12 RPR POLE | WILLITS | ETL.1481.POLE.WOOD | 2023-06-27 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46213262 | T2 LOWR LAK-HOMSTAK 3/12 RPR POLE | ICW
LC | 126464993 | 018/211 | T2 EI IGNACIO-BOLNS #2 18/211 RPR INSW | LAKEVLLE | ETL.7180.INSL.CERA | 2023-06-27 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46171055 | T2 EI IGNACIO-BOLNS #2 18/211 RPR INSW | ICW
LC | 126427285 | 023/187 | T2 EI PIT #1-COTTONWOOD 23/187 RPR STRT | TABLEMTN | ETL.5390.TOWR | 2023-06-22 | 2023-06-22 | 2024-01-30 | On-time | 2024-06-21 | 143 | 2024-06-22 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46132395 | T2 EI PIT #1-COTTONWOOD 23/187 RPR STRT | ICQ
LC | 126428488 | 019/221 | T2 EI DRUM-SUMMIT #1 019/221L RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2023-06-22 | 2023-06-22 | 2023-08-09 | On-time | 2024-06-21 | 317 | 2023-09-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45872469 | T2 EI DRUM-SUMMIT #1 019/221L RPR GYWW | ICW
LC | 126465753 | 008/171 | T2 DI HAT CREEK #1-WSTWD 8/171 TP CNCL | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-27 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091895 | T2 DI HAT CREEK #1-WSTWD 8/171 RPR GYWW | ICW
LC | 126465762 | 011/242 | T2 DI CASCADE-BEN-DESCH 11/242 RPL POLE | TABLEMTN | ETL.6310.POLE.WOOD | 2023-06-27 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521771 | T2 DI CASCADE-BEN-DESCH 11/242 RPL POLE | 70Y
LC | 126429846 | 002/020 | T2 EI BCKS CRK-RCK CK-CRST 2/20 RPL INSS | TABLEMTN | ETL.4430.INSL.CERA | 2023-06-22 | 2023-06-22 | 2024-01-19 | On-time | 2024-06-21 | 154 | 2024-06-22 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672630 | T2 DI BUCKS CRK-ROCK CRK 02/27 RPL INSS | 93K
LC | 126429862 | 002/020 | T2 EI BCKS CRK-RCK CK-CRST 2/20 RPR FOND | TABLEMTN | ETL.4430.TOWR | 2023-06-22 | 2023-06-22 | 2024-01-04 | On-time | 2024-06-21 | 169 | 2024-06-22 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46127859 | T2 EI BCKS CRK-RCK CK-CRST 2/20 RPR FOND | ICQ
LC | 126430529 | 001/019 | T2 EI BCKS CRK-RCK CRK-CRT 1/19 RPR FOND | TABLEMTN | ETL.4430.TOWR | 2023-06-22 | 2023-06-22 | 2024-01-04 | On-time | 2024-06-21 | 169 | 2024-06-22 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Earth Covered Tower | Foundation/Concrete-Tower | Repair | 46127880 | T2 EI BCKS CRK-RCK CRK-CRT 1/19 RPR FOND | ICQ
LC | 126465838 | 008/000 | T2 DI TULUCAY-NAPA #1 8/000 RPL HRDD | LAKEVLLE | ETL.8180.POLE.WOOD | 2023-06-27 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46096644 | T2 DI TULUCAY-NAPA #1 8/000 RPL HRDD | ICW
LC | 126430540 | :001/013 | T2 EI BCKS CRK-RCK CRK:1/013 RPL INSS | TABLEMTN | ETL.4430.INSL.NCER | 2023-06-22 | 2023-06-22 | 2024-01-19 | On-time | 2024-06-21 | 154 | 2024-06-22 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672630 | T2 DI BUCKS CRK-ROCK CRK 02/27 RPL INSS | 93K
LC | 126465853 | 054/405 | T2 DI BRIDGEVILLE-CTTNWD 54/405 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-06-27 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46088655 | T2 DI BRIDGEVILLE-CTTNWD 54/405 RPR OPGW | ICS
LC | 126430541 | 003/028 | T2 EI BCKS CRK-RCK CRK-CRA 3/28 RPL INSS | TABLEMTN | ETL.4430.INSL.CERA | 2023-06-22 | 2023-06-22 | 2024-01-16 | On-time | 2024-06-21 | 157 | 2024-06-22 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672630 | T2 DI BUCKS CRK-ROCK CRK 02/27 RPL INSS | 93K
LC | 126465920 | 008/000 | T2 DI TULUCAY-NAPA #1 8/000 RPR INSW | LAKEVLLE | ETL.8180.INSL.CERA | 2023-06-27 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46096645 | T2 DI TULUCAY-NAPA #1 8/000 RPR INSW | ICW
LC | 126430962 | 011/083 | T2 EI CARIBOU-TABLE MTN 11/083 COTER KEY | TABLEMTN | ETL.4440.TOWR | 2023-06-22 | 2023-06-22 | 2024-06-06 | On-time | 2024-06-21 | 15 | 2024-06-22 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46127948 | T2 EI CARIBOU-TABLE MTN 11/083 COTER KEY | ICQ
LC | 126430964 | 011/083 | T2 EI CARIBOU-TABLE MTN 011/083 RPR FOND | TABLEMTN | ETL.4440.TOWR | 2023-06-22 | 2023-06-22 | 2024-04-10 | On-time | 2024-06-21 | 72 | 2024-06-22 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46127949 | T2 EI CARIBOU-TABLE MTN 011/083 RPR FOND | ICQ
LC | 126431238 | 000/004 | T2 CHRISTIE-FRANKLIN #1 0/4 GO95 CLEAR | CONCORD | ETL.6350.POLE.WOOD | 2023-06-22 | 2023-06-22 | 2023-10-23 | On-time | 2024-06-21 | 242 | 2024-06-22 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31655018 | T2 CHRISTIE-FRANKLIN #1 0/4 GO95 CLEAR | 93G
LC | 126431361 | 000/001 | T2 CASTAIC TAP 0/1 GO95 | MIDWAY | ETL.9253.POLE.WOOD | 2023-06-22 | 2023-06-22 | 2023-10-14 | On-time | 2024-06-21 | 251 | 2024-06-22 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654460 | T2 CASTAIC TAP 0/1 GO95 | 93G
LC | 126432957 | 019/127 | T2 DI TESLA-NEWARK #2 19/127 RMV VEG | CONCORD | ETL.5354.TOWR | 2023-06-23 | 2023-06-22 | 2024-01-12 | On-time | 2024-06-21 | 161 | 2024-06-22 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126433198 | 000/009 | T2 DI SLT SPNGS-TGR CK 0/9 RPR STRT | VICTOR | ETL.3500.TOWR | 2023-06-23 | 2023-06-22 | 2023-09-22 | On-time | 2024-06-21 | 273 | 2023-09-22 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 45870836 | T2 DI SLT SPNGS-TGR CK 0/9 RPR STRT | ICQ
LC | 126466033 | 042/205 | T2 DI IGNACIO-SOBRNTE 42/205 RPL INSS | CONCORD | ETL.4920.INSL.CERA | 2023-06-27 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671638 | T2 DI IGNCO-SBRNTE RPL INSS IN 6 TWRS. | 93K
LC | 126466065 | 066/476 | T2 DI BRDGVIL CTTNWD 66/476 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-27 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45866278 | T2 DI BRDGVIL CTTNWD 66/476 RPR OPGW | ICS
LC | 126434951 | 046/224 | T2 DI IGNACIO-SOBR 46/224 RPR INSS | CONCORD | ETL.4960.INSL | 2023-06-23 | 2023-06-22 | 2024-05-22 | On-time | 2024-06-21 | 30 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45997217 | T2 DI IGNACIO-SOBR 46/224 RPR INSS | ICS
LC | 126466111 | 078/555 | T2 DI BRIDGEVL-COTNWD 78/555 RPR OPGW | EUREKA | ETL.1110.INSL.NCER | 2023-06-27 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 46171847 | T2 DI BRIDGEVL-COTNWD 78/555 RPR OPGW | ICW
LC | 126466115 | 072/524 | T2 DI BRIDGEVL-CTTNWD 72/524L RPR ADSS | EUREKA | ETL.1110.POLE.WDPS | 2023-06-27 | 2023-06-21 |  | Late | 2024-06-20 |  | 2023-09-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | ADSS - Wood | Repair | 46171729 | T2 DI BRIDGEVL-CTTNWD 72/524R RPR POLE | ICW
LC | 126434952 | 046/224 | T2 DI IGNACIO-SOBR 46/224 RMV NEST | CONCORD | ETL.4920.TOWR | 2023-06-23 | 2023-06-22 | 2023-11-24 | On-time | 2024-06-21 | 210 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46000789 | T2 DI IGNACIO-SOBR 46/224 RMV NEST | ICS
LC | 126436328 | 000/003 | T2 DI KM GREEN TAP 0/3 RPL DAMS | VICTOR | ETL.3505.INSL.NCER | 2023-06-23 | 2023-06-22 | 2024-06-11 | On-time | 2024-06-21 | 10 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 46257546 | T2 DI KM GREEN TAP 0/3 RPL DAMS | ICS
LC | 126466200 | 072/524 | T2 DI BRIDGEVL-CTTNWD 72/524R RPR POLE | EUREKA | ETL.1110.POLE.WDPS | 2023-06-27 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46171729 | T2 DI BRIDGEVL-CTTNWD 72/524R RPR POLE | ICW
LC | 126438348 | 000/007 | T2 DI BALCH-SANGER 0/7 RPR INSS | FRESNO | ETL.1050.INSL.CERA | 2023-06-23 | 2023-06-22 | 2023-10-18 | On-time | 2024-06-21 | 247 | 2023-12-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45883716 | T2 DI BALCH-SANGER 0/7 RPR INSS | ICS
LC | 126466229 | 073/530 | T2 DI BRDGVLLE-CTTNWD 73/530 RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-06-27 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171732 | T2 DI BRDGVLLE-CTTNWD 73/530 RPR GYWW | ICW
LC | 126457330 | 065/471 | T2 DI BRIDGEVILLE-CTTNWD 65/471 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-26 | 2023-06-22 | 2024-04-06 | On-time | 2024-06-21 | 76 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46171669 | T2 DI BRIDGEVILLE-CTTNWD 65/471 RPR OPGW | ICS
LC | 126466239 | 005/040 | T2 DI COTTONWOOD #2 5/40 RPL INSS | TABLEMTN | ETL.6630.INSL.CERA | 2023-06-27 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35514087 | T2 DI COTTONWOOD #2 5/40 RPL INSS | 93K
LC | 126466254 | 068/496 | T2 DI BRDGVLL-CTTNWD 068/496 COTTER | EUREKA | ETL.1110.TOWR | 2023-06-27 | 2023-06-21 | 2024-06-25 | Late | 2024-06-20 | -5 | 2024-06-21 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Tower | Install | 46125095 | T2 DI BRDGVLL-CTTNWD 068/496 COTTER | ICQ
LC | 126457333 | 065/471 | T2 DI BRIDGEVILLE-CTTNWD 65/471 RPL DMPS | EUREKA | ETL.1110.INSL.NCER | 2023-06-26 | 2023-06-22 | 2024-04-06 | On-time | 2024-06-21 | 76 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Steel | Replace | 46204232 | T2 DI BRIDGEVILLE-CTTNWD 65/471 RPL DMPS | ICS
LC | 126466286 | 005/116 | T2 DI CARIBOU #2 5/116 RPR GYWW | TABLEMTN | ETL.6280.POLE.NWOD | 2023-06-27 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091947 | T2 DI CARIBOU #2 5/116 RPR GYWW | ICW
LC | 126457390 | 014/007B | T2 DI CARIBOU-PLUMAS JCT 14/7B RPR INSW | TABLEMTN | ETL.6290.INSL.NCER | 2023-06-26 | 2023-06-22 | 2024-05-08 | On-time | 2024-06-21 | 44 | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46091943 | T2 DI CARIBOU-PLUMAS JCT 14/7B RPR INSW | ICW
LC | 126466304 | 048/004 | T2 DI FORT ROSS-GUALALA 48/4 RPL HRDW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-06-27 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46190203 | T2 DI FORT ROSS-GUALALA 48/4 RPL HRDW | ICW
LC | 126457401 | 062/452 | T2 DI BRIDGEVILLE-CTTNWD 62/452 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-26 | 2023-06-22 | 2024-04-06 | On-time | 2024-06-21 | 76 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46171664 | T2 DI BRIDGEVILLE-CTTNWD 62/452 RPR OPGW | ICS
LC | 126457479 | 000/008 | T2 DI BALCH-SANGER 0/8 RPR STRT | FRESNO | ETL.1050.TOWR | 2023-06-26 | 2023-06-22 | 2024-02-12 | On-time | 2024-06-21 | 130 | 2024-06-22 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46124970 | T2 DI BALCH-SANGER 0/8 RPR STRT | ICQ
LC | 126457523 | 000/004 | T2 DI KM GREEN TAP 0/4 COMPLETE | VICTOR | ETL.3505.POLE.NWOD | 2023-06-26 | 2023-06-22 | 2023-07-20 | On-time | 2024-06-21 | 337 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45870835 | T2 DI KM GREEN TAP 0/4 RPR OPGW | ICS
LC | 126466373 | 065/468 | T2 DI BRIDGEVILLE-CTTNWD 65/468 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-27 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45870607 | T2 DI BRIDGEVILLE-CTTNWD 65/468 RPR OPGW | ICS
LC | 126457540 | 000/008 | T2 DI BALCH-SANGER 0/8 RPL HDWT | FRESNO | ETL.1050.TOWR | 2023-06-26 | 2023-06-22 | 2024-02-12 | On-time | 2024-06-21 | 130 | 2024-06-22 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46124969 | T2 DI BALCH-SANGER 0/8 RPL HDWT | ICQ
LC | 126465781 | 063/461C | T2 DI BRIDGEVLLE-CTTNWD 63/461C RPR GYWS | EUREKA | ETL.1110.POLE.NWOD | 2023-06-27 | 2023-06-22 | 2024-04-05 | On-time | 2024-06-21 | 77 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46147376 | T2 DI BRIDGEVLLE-CTTNWD 63/461C RPR GYWS | ICS
LC | 126466399 | 069/501 | T2 DI BRDGVLL-CTTNWD 069/501 RPL INSW | EUREKA | ETL.1110.INSL.NCER | 2023-06-27 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 508T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35505103 | T2 DI BRDGVLL-CTTNWD 069/501 RPL INSW | 93I
LC | 126466118 | 002/036 | T2 DI COLGATE-SMRTVL #1 2/36 RPL INSW | SACTO | ETL.6510.INSL.NCER | 2023-06-27 | 2023-06-22 | 2023-07-22 | On-time | 2024-06-21 | 335 | 2023-09-22 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31654026 | T2 DI COLGATE-SMRTVL #1 2/36 RPL INSW | 93I
LC | 126466202 | 063/459 | T2 DI BRIDGEVL-COTT 63/459 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-27 | 2023-06-22 | 2024-04-08 | On-time | 2024-06-21 | 74 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45866276 | T2 DI BRIDGEVL-COTT 63/459 RPR OPGW | ICS
LC | 126466235 | 002/031 | T2 DI COLGATE-SMRTVL #2 2/31 RPR INSW | SACTO | ETL.6520.INSL.NCER | 2023-06-27 | 2023-06-22 | 2024-05-02 | On-time | 2024-06-21 | 50 | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46102285 | T2 DI COLGATE-SMRTVL #2 2/31 RPR INSW | ICW
LC | 126466255 | 009/062 | T2 DI COTTONWOOD #2 009/062 COTTER | TABLEMTN | ETL.6630.INSL.CERA | 2023-06-27 | 2023-06-22 | 2024-04-12 | On-time | 2024-06-21 | 70 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46090275 | T2 DI COTTONWOOD #2 009/062 COTTER | ICS
LC | 126469839 | 020/134 | T2 DI TESLA-NEWARK #2 20/134 RPR GYWS | CONCORD | ETL.5354.TOWR | 2023-06-28 | 2023-06-22 | 2024-01-30 | On-time | 2024-06-21 | 143 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 45997205 | T2 DI TESLA-NEWARK #2 20/134 RPR GYWS | ICS
LC | 126470545 | 020/134 | T2 DI TESLA-NEWARK #2 20/134 COTTER | CONCORD | ETL.5354.INSL.NCER | 2023-06-28 | 2023-06-22 | 2024-01-30 | On-time | 2024-06-21 | 143 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45997210 | T2 DI TESLA-NEWARK #2 20/134 COTTER | ICS
LC | 126466471 | 011/259 | T2 DI SLNAS-LRLES-LRLES 11/259 COMPLETED | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-27 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35507121 | T2 DI SLNAS-LRLES-LRLES 11/259 RPL STRW | 70Y
LC | 126472069 | 063/458 | T2 DI BRDGVIL CTTNWD 63/458 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-28 | 2023-06-22 | 2024-04-08 | On-time | 2024-06-21 | 74 | 2023-09-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45870604 | T2 DI BRDGVIL CTTNWD 63/458 RPR OPGW | ICS
LC | 126472233 | 065/469 | T2 DI BRDGVILE CTTNWD 65/469L RPR GYWS | EUREKA | ETL.1110.POLE.STPS | 2023-06-28 | 2023-06-22 | 2024-04-08 | On-time | 2024-06-21 | 74 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46147377 | T2 DI BRDGVILE CTTNWD 65/469L RPR GYWS | ICS
LC | 126472238 | 065/469 | T2 DI BRDGVIL CTTNWD 65/469 RPR OPGW | EUREKA | ETL.1110.POLE.STPS | 2023-06-28 | 2023-06-22 | 2024-04-08 | On-time | 2024-06-21 | 74 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46171668 | T2 DI BRDGVIL CTTNWD 65/469 RPR OPGW | ICS
LC | 126473980 | 045/217 | T2 DI LAKEVILLE-SBRNT #2 45/217 RPR INSS | CONCORD | ETL.4960.INSL.CERA | 2023-06-28 | 2023-06-22 | 2024-05-25 | On-time | 2024-06-21 | 27 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45997219 | T2 DI LAKEVILLE-SBRNT #2 45/217 RPR INSS | ICS
LC | 126474044 | 043/210 | T2 DI LAKEVILLE-SBRNT #2 43/210 COTTER | CONCORD | ETL.4960.INSL | 2023-06-28 | 2023-06-22 | 2024-05-22 | On-time | 2024-06-21 | 30 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45997215 | T2 DI LAKEVILLE-SBRNT #2 43/210 COTTER | ICS
LC | 126474046 | 020/234B | T2 DI DRUM-SMMT #1 20/234B COMPLETE | SACTO | ETL.1440.POLE.NWOD | 2023-06-28 | 2023-06-22 | 2024-05-15 | On-time | 2024-06-21 | 37 | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098393 | T2 DI DRUM-SMMT #1 20/234B RPR GYWW | ICW
LC | 126474500 | 020/238A | T2 DI DRUM-SUMMIT #1 20/238A RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-28 | 2023-06-22 | 2024-05-15 | On-time | 2024-06-21 | 37 | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098394 | T2 DI DRUM-SUMMIT #1 20/238A RPR GYWW | ICW
LC | 126474533 | 003/038 | T2 DI COLGATE-SMARTVILLE #2 03/38 COTTER | SACTO | ETL.6520.INSL.NCER | 2023-06-28 | 2023-06-22 | 2024-05-02 | On-time | 2024-06-21 | 50 | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46102288 | T2 DI COLGATE-SMARTVILLE #2 03/38 COTTER | ICW
LC | 126474589 | 003/038 | T2 DI COLGATE-SMARTVLLE #2 3/38 RPR GYWW | SACTO | ETL.6520.POLE.NWOD | 2023-06-28 | 2023-06-22 | 2023-07-28 | On-time | 2024-06-21 | 329 | 2023-12-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45872463 | T2 DI COLGATE-SMARTVLLE #2 3/38 RPR GYWW | ICW
LC | 126474808 | 020/238C | T2 DI DRUM-SMMT #1 20/238C RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-28 | 2023-06-22 | 2024-05-15 | On-time | 2024-06-21 | 37 | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098395 | T2 DI DRUM-SMMT #1 20/238C RPR GYWW | ICW
LC | 126474874 | 020/238B | T2 DI DRUM-SMMT #1 20/238B RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-28 | 2023-06-22 | 2024-05-15 | On-time | 2024-06-21 | 37 | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098396 | T2 DI DRUM-SMMT #1 20/238B RPR GYWW | ICW
LC | 126476552 | 013/099 | T2 DI SALT SPNGS TGR CK 13/99 COTTER | VICTOR | ETL.3500.INSL | 2023-06-29 | 2023-06-22 | 2024-04-26 | On-time | 2024-06-21 | 56 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46162201 | T2 DI SALT SPNGS TGR CK 13/99 COTTER | ICS
LC | 126479929 | 019/221 | T2 EI DRUM-SUMMIT #1 019/221C RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2023-06-29 | 2023-06-22 | 2023-08-09 | On-time | 2024-06-21 | 317 | 2023-09-22 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45872470 | T2 EI DRUM-SUMMIT #1 019/221C RPR GYWW | ICW
LC | 126481788 | 002/035 | T2 DI COLGATE-SMRTVL#1 02/35 RPR GYWW | SACTO | ETL.6510.POLE.NWOD | 2023-06-29 | 2023-06-22 | 2024-05-09 | On-time | 2024-06-21 | 43 | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46102291 | T2 DI COLGATE-SMRTVL#1 02/35 RPR GYWW | ICW
LC | 126471577 | 075/542 | T2 DI BRDGVILLE CTTNWD 75/542 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-28 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46204231 | T2 DI BRDGVILLE CTTNWD 75/542 RPR OPGW | ICS
LC | 126471788 | 075/542 | T2 DI BRDGVIL CTTNWD 75/542 COTTER | EUREKA | ETL.1110.TOWR | 2023-06-28 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Steel | Replace | 46171842 | T2 DI BRDGVILLE CTTNWD 75/542 RPR OPGW | ICS
LC | 126481910 | 000/005 | T2 DI BALCH-SANGER 0/5 RPR STRT | FRESNO | ETL.1050.TOWR | 2023-06-29 | 2023-06-22 | 2024-02-13 | On-time | 2024-06-21 | 129 | 2024-06-22 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46124968 | T2 DI BALCH-SANGER 0/5 RPR STRT | ICQ
LC | 126482084 | 003/045 | T2 DI COLGATE-SMRTVL#2 3/45 RPL STRW | SACTO | ETL.6520.POLE.WOOD | 2023-06-29 | 2023-06-22 | 2024-05-01 | On-time | 2024-06-21 | 51 | 2024-06-22 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481571 | T2 DI COLGATE-SMRTVL#2 3/45 RPL STRW | 70Y
LC | 126484237 | 014/007A | T2 DI CARIBOU-PLMS JCT 14/007A RPR GYWW | TABLEMTN | ETL.6290.POLE.NWOD | 2023-06-30 | 2023-06-22 | 2024-05-08 | On-time | 2024-06-21 | 44 | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091941 | T2 DI CARIBOU-PLMS JCT 14/007A RPR GYWW | ICW
LC | 126484238 | 014/007A | T2 DI CARIBOU-PLMS JCT 14/007A RPR CRSW | TABLEMTN | ETL.6290.POLE.NWOD | 2023-06-30 | 2023-06-22 | 2024-05-08 | On-time | 2024-06-21 | 44 | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46091942 | T2 DI CARIBOU-PLMS JCT 14/007A RPR CRSW | ICW
LC | 126472839 | 071/516 | T2 DI BRDGVL-CTTNWD 71/516L RPR GYWW | EUREKA | ETL.1110.POLE.WDPS | 2023-06-28 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171724 | T2 DI BRDGVL-CTTNWD 71/516L RPR GYWW | ICW
LC | 126485701 | 000/007 | T2 DI HAAS-MCCALL 0/7 RPR SHLS | FRESNO | ETL.4850.TOWR | 2023-06-30 | 2023-06-22 | 2024-05-06 | On-time | 2024-06-21 | 46 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46080585 | T2 DI HAAS-MCCALL 0/7 RPR SHLS | ICS
LC | 126485815 | 003/039 | T2 DI CLGT-SMRTVLL #2 3/39 RPL STRW | SACTO | ETL.6520.POLE.WOOD | 2023-06-30 | 2023-06-22 | 2024-05-02 | On-time | 2024-06-21 | 50 | 2024-06-22 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481569 | T2 DI CLGT-SMRTVLL #2 3/39 RPL STRW | 70Y
LC | 126473010 | 071/516 | T2 DI BRDGVL-CTTNWD 71/516L RPR ANCW | EUREKA | ETL.1110.POLE.WDPS | 2023-06-28 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46171724 | T2 DI BRDGVL-CTTNWD 71/516L RPR GYWW | ICW
LC | 126489720 | 002/006 | T2 DI HUMBOLDT-MAPLE CRK 2/6 RPL HRDW | EUREKA | ETL.7130.POLE.WOOD | 2023-06-30 | 2023-06-22 | 2024-05-28 | On-time | 2024-06-21 | 24 | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46171119 | T2 DI HUMBOLDT-MAPLE CRK 2/6 RPL HRDW | ICW
LC | 126473831 | 051/004 | T2 DI FRT RSS-GLL-GLL 51/004 RPL HRDD | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-06-28 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46190204 | T2 DI FRT RSS-GLL-GLL 51/004 RPL HRDD | ICW
LC | 126473832 | 051/004 | T2 DI FRT RSS-GUALALA 51/004 RPR INSW | LAKEVLLE | ETL.6980.INSL.NCER | 2023-06-28 | 2023-06-21 | 2024-06-25 | Late | 2024-06-20 | -5 | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46190205 | T2 DI FRT RSS-GUALALA 51/004 RPR INSW | ICW
LC | 126489886 | 002/006-GUY | T2 DI HUMBOLDT-MAPLE CREEK 02/06 RMV VEG | EUREKA | ETL.7130.POLE.WOOD | 2023-06-30 | 2023-06-22 | 2023-09-11 | On-time | 2024-06-21 | 284 | 2024-06-22 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126491262 | 003/042 | T2 DI COLGATE-SMRTVL#1 03/42 RPR GYWW | SACTO | ETL.6510.POLE.NWOD | 2023-06-30 | 2023-06-22 | 2024-05-09 | On-time | 2024-06-21 | 43 | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46102293 | T2 DI COLGATE-SMRTVL#1 03/42 RPR GYWW | ICW
LC | 126473981 | 045/217 | T2 DI IGNACIO-SOBRANTE 45/217 RPR INSS | CONCORD | ETL.4920.INSL.CERA | 2023-06-28 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46000791 | T2 DI IGNACIO-SOBRANTE 45/217 RPR INSS | ICS
LC | 126491475 | 004/053 | T2 DI CLGT-SMRTVLL #2 4/53 RPL POLE | SACTO | ETL.6520.POLE.WOOD | 2023-06-30 | 2023-06-22 | 2024-04-30 | On-time | 2024-06-21 | 52 | 2024-06-22 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481573 | T2 DI CLGT-SMRTVLL #2 4/53 RPL POLE | 70Y
LC | 126492791 | 005/064 | T2 DI COLGATE-SM#1 5/64L RPL POLE | SACTO | ETL.6510.POLE.WDPS | 2023-07-01 | 2023-06-22 | 2024-05-10 | On-time | 2024-06-21 | 42 | 2024-06-22 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481555 | T2 DI COLGATE-SM#1 5/64L RPL POLE | 70Y
LC | 126492792 | 005/064 | T2 DI COLGATE-SM#1 5/64C RPL POLE | SACTO | ETL.6510.POLE.WDPS | 2023-07-01 | 2023-06-22 | 2024-05-10 | On-time | 2024-06-21 | 42 | 2024-06-22 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481555 | T2 DI COLGATE-SM#1 5/64L RPL POLE | 70Y
LC | 126474049 | 012/260 | T2 DI LAKEVILLE #2 012/260 RPL HRDW | LAKEVLLE | ETL.7340.POLE.WOOD | 2023-06-28 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46096647 | T2 DI LAKEVILLE #2 012/260 RPL HRDW | ICW
LC | 126492793 | 005/064 | T2 DI COLGATE-SM#1 5/64R RPL POLE | SACTO | ETL.6510.POLE.WDPS | 2023-07-01 | 2023-06-22 | 2024-05-10 | On-time | 2024-06-21 | 42 | 2024-06-22 | 372 | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481555 | T2 DI COLGATE-SM#1 5/64L RPL POLE | 70Y
LC | 126474090 | ;005/010 | T2 DI CARIBOU #2 ;005/010 RPL STRW | TABLEMTN | ETL.6280.POLE.WOOD | 2023-06-28 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527154 | T2 DI CARIBOU #2 ;005/010 RPL STRW | 70Y
LC | 126492929 | 004/052 | T2 DI COLGATE-SMARTVILLE #1 4/52 RPR GYW | SACTO | ETL.6510.POLE.NWOD | 2023-07-01 | 2023-06-22 | 2023-07-19 | On-time | 2024-06-21 | 338 | 2023-12-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45886239 | T2 DI COLGATE-SMARTVILLE #1 4/52 RPR GYW | ICW
LC | 126474134 | 059/432 | T2 DI BRDGVLE-CTNWD 59/432 COTTER | EUREKA | ETL.1110.INSL.CERA | 2023-06-28 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46171661 | T2 DI BRDGVLE-CTNWD 59/432 COTTER | ICS
LC | 126474223 | 057/422 | T2 DI BRIDGVL-CTNWD 57/422L RPR OPGW | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-28 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46088704 | T2 DI BRIDGVL-CTNWD 57/422L RPR OPGW | ICS
LC | 126493536 | 003/043 | T2 DI CLGTE SMRTVIL#2 3/43 RPR INSW | SACTO | ETL.6520.INSL.NCER | 2023-07-01 | 2023-06-22 | 2024-05-01 | On-time | 2024-06-21 | 51 | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46102295 | T2 DI CLGTE SMRTVIL#2 3/43 RPR INSW | ICW
LC | 126474312 | 059/428 | T2 DI BRDGVL-CTTNWD 59/428 COTTER | EUREKA | ETL.1110.TOWR | 2023-06-28 | 2023-06-23 | 2024-06-24 | Late | 2024-06-22 | -2 | 2024-06-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Hardware-Tower | Install | 46125141 | T2 DI BRDGVL-CTTNWD 59/428 COTTER | ICQ
LC | 126474363 | 057/422 | T2 DI BRIDGVL-CTNWD 57/422L RPR GYWT | TABLEMTN | ETL.1110.POLE.STPS | 2023-06-28 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46255052 | T2 DI BRIDGVL-CTNWD 57/422L RPR GYWT | ICQ
LC | 126474366 | 072/522 | T2 DI BRIDGVL-CTNWD 75/522L RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-06-28 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171727 | T2 DI BRIDGVL-CTNWD 75/522L RPR GYWW | ICW
LC | 126474367 | 072/522 | T2 DI BRIDGVL-CTNWD 75/522R RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-06-28 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171727 | T2 DI BRIDGVL-CTNWD 75/522L RPR GYWW | ICW
LC | 126493952 | 011/099 | T2 DI CBRLLO-SNTA YNZ SS 11/99 RPR GYWW | PISMOBCH | ETL.1200.POLE.NWOD | 2023-07-01 | 2023-06-22 | 2024-01-30 | On-time | 2024-06-21 | 143 | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46090185 | T2 DI CBRLLO-SNTA YNZ SS 11/99 RPR GYWW | ICW
LC | 126474416 | 005/127 | T2 DI DEL MNTE-VIEJO 5/127 RPR CNDW | MOSSLNDG | ETL.6710.INSL.CERA | 2023-06-28 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Conductor-Wood | Repair | 46081736 | T2 DI DEL MNTE-VIEJO 5/127 RPR CNDW | ICW
LC | 126494816 | 000/006 | T2 DI HAAS-MC CALL 0/6 RPL INSS | FRESNO | ETL.4850.INSL | 2023-07-01 | 2023-06-22 | 2024-05-06 | On-time | 2024-06-21 | 46 | 2024-06-22 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510275 | T2 DI HAAS-MCCALL 6/45 RPL INSS | 93K
LC | 126474492 | 058/425B | T2 DI BRDGVLL-CTTNWD 58/425B RPR GYWT | TABLEMTN | ETL.1110.POLE.NWOD | 2023-06-28 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46255053 | T2 DI BRDGVLL-CTTNWD 58/425B RPR GYWT | ICQ
LC | 126474498 | 058/425B | T2 DI BRDGVLL-CTTNWD 58/425B COTTER | TABLEMTN | ETL.1110.INSL.NCER | 2023-06-28 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46088707 | T2 DI BRDGVLL-CTTNWD 58/425B COTTER | ICS
LC | 126494936 | 001/010 | T2 DI HAAS-MC CALL 01/10 BNT STEEL | FRESNO | ETL.4850.TOWR | 2023-07-01 | 2023-06-22 | 2024-01-30 | On-time | 2024-06-21 | 143 | 2024-06-22 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46132984 | T2 DI HAAS-MC CALL 01/10 BNT STEEL | ICQ
LC | 126474501 | 071/513 | T2 DI BRIDGEVIL-CTTNWD 71/513 RPR SHLD | EUREKA | ETL.1110.POLE.STPS | 2023-06-28 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46171722 | T2 DI BRIDGEVIL-CTTNWD 71/513 RPR SHLD | ICS
LC | 126495262 | 079/563 | T2 DI BRDGVLLE-CTNWD 79/563L RPR OPGW | EUREKA | ETL.1110.POLE.STPS | 2023-07-01 | 2023-06-22 | 2024-04-06 | On-time | 2024-06-21 | 76 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46171851 | T2 DI BRDGVLLE-CTNWD 79/563L RPR OPGW | ICS
LC | 126495561 | 063/454 | T2 DI BRDGVL-CTNWD-63/454 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-07-01 | 2023-06-22 | 2024-04-06 | On-time | 2024-06-21 | 76 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46171665 | T2 DI BRDGVL-CTNWD-63/454 RPR OPGW | ICS
LC | 126474575 | 000/019 | T2 DI CARIBOU-WSWD 000/019 RPL ANCW | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-28 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35545400 | T2 DI CARIBOU-WSWD 000/019 RPL ANCW | 93E
LC | 126515911 | 001/009 | T2 DI HAAS-MCCALL 1/9 COMPLETE | FRESNO | ETL.4850.INSL.NCER | 2023-07-06 | 2023-06-22 | 2024-05-07 | On-time | 2024-06-21 | 45 | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45883718 | T2 DI HAAS-MCCALL 001/009 RPR JUMS | ICS
LC | 126435254 | 037/168 | T2 WV VACA-LAKEVILLE #1 037/168 RPL INSS | LAKEVLLE | ETL.5840.INSL | 2023-06-23 | 2023-06-23 | 2024-04-15 | On-time | 2024-06-22 | 68 | 2024-06-23 | 532 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31678228 | T2 WV VACA-LAKEVILLE #1 RPL INSS IN 4 TW | 93K
LC | 126474674 | 074/532 | T2 DI BRIDGEVL-COTT 74/532 JMPS | EUREKA | ETL.1110.INSL.NCER | 2023-06-28 | 2023-06-21 |  | Late | 2024-06-20 |  | 2023-09-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 46203419 | T2 DI BRIDGEVL-COTT 74/532 JMPS | ICS
LC | 126474683 | 004/085 | T2 DI CARIBOU-WESTWOOD 4/85 RPR GYWW | TABLEMTN | ETL.6300.POLE.NWOD | 2023-06-28 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091899 | T2 DI CARIBOU-WESTWOOD 4/85 RPR GYWW | ICW
LC | 126435819 | 025/299C | T2 EI DRUM-SUMMIT #1 025/299C RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-23 | 2023-06-23 | 2023-08-04 | On-time | 2024-06-22 | 323 | 2023-09-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45864946 | T2 EI DRUM-SUMMIT #1 025/299C RPR GYWW | ICW
LC | 126439055 | 023/279 | T2 EI DRUM-SUMMIT #2 023/279 RPR GYWW | SACTO | ETL.1450.POLE.STPS | 2023-06-23 | 2023-06-23 | 2024-06-20 | On-time | 2024-06-22 | 2 | 2023-12-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098254 | T2 EI DRUM-SUMMIT #2 023/279 RPR GYWW | ICW
LC | 126439769 | 024/290A | T2 EI DRUM-SUMMIT #1 24/290A RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-23 | 2023-06-23 | 2023-08-05 | On-time | 2024-06-22 | 322 | 2023-09-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45864947 | T2 EI DRUM-SUMMIT #1 24/290A RPR GYWW | ICW
LC | 126474800 | 000/003 | T2 DI BLACK TAP 000/003 RPR SHLS | TABLEMTN | ETL.5431.INSL.CERA | 2023-06-28 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46083513 | T2 DI BLACK TAP 000/003 RPR SHLS | ICS
LC | 126474804 | 000/003 | T2 DI BLACK TAP 000/003 RPL INSS | TABLEMTN | ETL.5431.INSL.CERA | 2023-06-28 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513066 | T2 DI BLACK TAP 000/003 RPL INSS | 93K
LC | 126474805 | 000/003 | T2 DI BLACK TAP 000/003 RMV NEST | TABLEMTN | ETL.5431.TOWR | 2023-06-28 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 46083514 | T2 DI BLACK TAP 000/003 RMV NEST | ICS
LC | 126439792 | 000/003B | T2 EI BCKS CRK-RK CRK-CRST 0/3B RPR ANCS | TABLEMTN | ETL.4430.POLE.NWOD | 2023-06-23 | 2023-06-23 | 2024-05-14 | On-time | 2024-06-22 | 39 | 2024-06-23 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 46125508 | T2 EI BCKS CRK-RK CRK-CRST 0/3B RPR ANCS | ICS
LC | 126439932 | 000/003C | T2 EI BKS CRK-RCK CRK-CRST 0/3C COMPLETE | TABLEMTN | ETL.4430.POLE.NWOD | 2023-06-23 | 2023-06-23 | 2024-05-14 | On-time | 2024-06-22 | 39 | 2024-06-23 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 46125509 | T2 EI BUCKS CRK-RCK CRK-CRST 0/3C UNBURY | ICS
LC | 126439943 | 010/075C | T2 EI CARIBOU-TABLE MTN 10/75C RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-23 | 2023-06-23 | 2024-04-09 | On-time | 2024-06-22 | 74 | 2024-06-23 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46088171 | T2 EI CARIBOU-TABLE MTN 10/75C RPR GYWS | ICS
LC | 126439944 | 010/075A | T2 EI CARIBOU-TABLE MTN 10/75A RPR GYWS | TABLEMTN | ETL.4440.POLE.NWOD | 2023-06-23 | 2023-06-23 | 2024-04-09 | On-time | 2024-06-22 | 74 | 2024-06-23 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46088170 | T2 EI CARIBOU-TABLE MTN 10/75A RPR GYWS | ICS
LC | 126439952 | 010/075A | T2 EI CARIBOU-TABLE MTN 10/75A RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2023-06-23 | 2023-06-23 | 2024-06-06 | On-time | 2024-06-22 | 16 | 2024-06-23 | 532T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35508877 | T2 EI CARIBOU-TABLE MTN RPL INSS 12 STRT | 93K
LC | 126439956 | 010/075B | T2 EI CARIBOU-TABLE MTN 10/75B RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2023-06-23 | 2023-06-23 | 2024-06-06 | On-time | 2024-06-22 | 16 | 2024-06-23 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35508877 | T2 EI CARIBOU-TABLE MTN RPL INSS 12 STRT | 93K
LC | 126439957 | 010/075C | T2 EI CARIBOU-TABLE MTN 10/75C RPL INSS | TABLEMTN | ETL.4440.INSL.CERA | 2023-06-23 | 2023-06-23 | 2024-06-06 | On-time | 2024-06-22 | 16 | 2024-06-23 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35508877 | T2 EI CARIBOU-TABLE MTN RPL INSS 12 STRT | 93K
LC | 126439973 | 024/290B | T2 EI DRUM-SUMMIT #1 024/290B RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-23 | 2023-06-23 | 2023-08-05 | On-time | 2024-06-22 | 322 | 2023-09-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45864948 | T2 EI DRUM-SUMMIT #1 024/290B RPR GYWW | ICW
LC | 126440081 | 024/290C | T2 EI DRUM-SUMMIT #1 24/290C RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-23 | 2023-06-23 | 2023-08-05 | On-time | 2024-06-22 | 322 | 2023-09-23 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45864949 | T2 EI DRUM-SUMMIT #1 24/290C RPR GYWW | ICW
LC | 126440578 | 001/012 | T2 EI BCK CRK-RCK CRK-CRST 1/12 RPR FOND | TABLEMTN | ETL.4430.TOWR | 2023-06-23 | 2023-06-23 | 2024-04-13 | On-time | 2024-06-22 | 70 | 2024-06-23 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46127881 | T2 EI BCK CRK-RCK CRK-CRST 1/12 RPR FOND | ICQ
LC | 126477033 | 015/489 | T2 EI SPAULDING-SUMMIT 15/489 INS JUMP | SACTO | ETL.8060.INSL.NCER | 2023-06-29 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35508788 | T2 EI SPAULDING-SUMMIT 15/489 INS JUMP | 93I
LC | 126440598 | 003/029 | T2 EI BCKS CRK-RCK CRK-CRA 3/29 RPL INSS | TABLEMTN | ETL.4430.INSL.CERA | 2023-06-23 | 2023-06-23 | 2024-01-16 | On-time | 2024-06-22 | 158 | 2024-06-23 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672630 | T2 DI BUCKS CRK-ROCK CRK 02/27 RPL INSS | 93K
LC | 126477137 | 019/224 | T2 DI DRUM-SUMMIT #1 19/224 RPL HRDD | SACTO | ETL.1440.POLE.WDPS | 2023-06-29 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46098397 | T2 DI DRUM-SUMMIT #1 19/224 RPL HRDD | ICW
LC | 126477353 | 013/104 | T2 WV TIGER CREEK-ELECTRA 13/104 INS DMP | VICTOR | ETL.5780.INSL.NCER | 2023-06-29 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Wood | Install | 46219948 | T2 WV TIGER CREEK-ELECTRA 13/104 INS DMP | ICW
LC | 126465765 | 001/015 | T2 DI MTN GTE JCT-CASCADE 1/15L RPR GYWW | TABLEMTN | ETL.7640.POLE.STPS | 2023-06-27 | 2023-06-23 | 2023-08-18 | On-time | 2024-06-22 | 309 | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46095264 | T2 DI MTN GTE JCT-CASCADE 1/15L RPR GYWW | ICW
LC | 126477389 | A015/318-GUY | T2 DI SLNS-LAURLS A15/318 INSP ANCHRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-29 | 2023-06-16 |  | Late | 2024-06-15 |  | 2024-06-16 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Structure-Wood | Inspect
LC | 126465845 | 002/024A | T2 DI MONTA VISTA-BURNS 02/024A RPL HRDW | MOSSLNDG | ETL.7590.POLE.WOOD | 2023-06-27 | 2023-06-23 | 2024-02-29 | On-time | 2024-06-22 | 114 | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46081539 | T2 DI MONTA VISTA-BURNS 02/024A RPL HRDW | ICW
LC | 126465935 | 002/024C | T2 DI NARROWS #1 TAP 2/24C RMV BUTT | SACTO | ETL.6511.POLE.WOOD | 2023-06-27 | 2023-06-23 | 2024-05-10 | On-time | 2024-06-22 | 43 | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Wood | Remove | 46102237 | T2 DI NARROWS #1 TAP 2/24C RMV BUTT | ICW
LC | 126477803 | 043/253 | T2 DI COTTLE MELONES 43/253 RPR GYWS | VICTOR | ETL.4530.POLE.NWOD | 2023-06-29 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46081049 | T2 DI COTTLE MELONES 43/253 RPR GYWS | ICS
LC | 126477806 | 043/253 | T2 DI COTTLE MELONES 43/253 RPR ANCS | VICTOR | ETL.4530.POLE.NWOD | 2023-06-29 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Steel | Repair | 46081051 | T2 DI COTTLE MELONES 43/253 RPR ANCS | ICS
LC | 126477981 | 052/392 | T2 DI BRDGVLLE-COTTONWD 52/392 BNT STEEL | TABLEMTN | ETL.1110.TOWR | 2023-06-29 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46125145 | T2 DI BRDGVLLE-COTTONWD 52/392 BNT STEEL | ICQ
LC | 126477982 | 052/392 | T2 DI BRIDGEVILLE-CTTNWD 52/392 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-06-29 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46088701 | T2 DI BRIDGEVILLE-CTTNWD 52/392 RPR OPGW | ICS
LC | 126465939 | 002/024C | T2 DI NARROWS #1 TAP 2/24C RPR GYWW | SACTO | ETL.6511.POLE.WOOD | 2023-06-27 | 2023-06-23 | 2024-05-10 | On-time | 2024-06-22 | 43 | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46102283 | T2 DI NARROWS #1 TAP 2/24C RPR GYWW | ICW
LC | 126478063 | 014/477 | T2 EI SPAULDING-SUMMIT 14/477 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2023-06-29 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508785 | T2 DI SPAULDING-SUMMIT 14/456 RPL POLE | 70Y
LC | 126478067 | 015/478 | T2 EI SPAULDING-SUMMIT 15/478 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2023-06-29 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508785 | T2 DI SPAULDING-SUMMIT 14/456 RPL POLE | 70Y
LC | 126465972 | 002/024C | T2 DI NARROWS #1 TAP 2/24C RPR INSW | SACTO | ETL.6511.INSL.CERA | 2023-06-27 | 2023-06-23 | 2024-05-10 | On-time | 2024-06-22 | 43 | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46102284 | T2 DI NARROWS #1 TAP 2/24C RPR INSW | ICW
LC | 126478650 | 013/106 | T2 WV TIGER CREEK-ELECTRA 13/106 INS DMP | VICTOR | ETL.5780.INSL.NCER | 2023-06-29 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Missing | Damper-Steel | Install | 46219949 | T2 WV TIGER CREEK-ELECTRA 13/106 INS DMP | ICS
LC | 126466098 | 001/026-GUY | T2 DI JEFFERSON-STANFRD 01/26-G RPR GYWW | METCALF | ETL.7220.POLE.WOOD | 2023-06-27 | 2023-06-23 | 2024-04-02 | On-time | 2024-06-22 | 81 | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46080484 | T2 DI JEFFERSON-STANFRD 01/26-G RPR GYWW | ICW
LC | 126466297 | 000/012 | T2 DI COLGATE-SMARTVLE#2 0/12 RPR INSW | SACTO | ETL.6520.INSL.CERA | 2023-06-27 | 2023-06-23 | 2024-05-03 | On-time | 2024-06-22 | 50 | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46102286 | T2 DI COLGATE-SMARTVLE#2 0/12 RPR INSW | ICW
LC | 126479350 | 005/095 | T2 DI CARIBOU-WESTWOOD 5/95 RPR ANCW | TABLEMTN | ETL.6300.POLE.NWOD | 2023-06-29 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46091940 | T2 DI CARIBOU-WESTWOOD 5/95 RPR ANCW | ICW
LC | 126466336 | 001/026 | T2 DI JEFFERSON-STANFORD 1/26 RPR ANCW | METCALF | ETL.7220.POLE.WOOD | 2023-06-27 | 2023-06-23 | 2024-04-03 | On-time | 2024-06-22 | 80 | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46213077 | T2 DI JEFFERSON-STANFORD 1/26 RPR ANCW | ICW
LC | 126479432 | 002/069 | T2 DI CASCDE-BENTN-DSHTS 2/69 RPL STRW | TABLEMTN | ETL.6310.POLE.WOOD | 2023-06-29 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35521350 | T2 EI CASADE-BENTON-DSCHTS 2/54 RPL STRW | 70Y
LC | 126466339 | 001/026 | T2 DI JEFFERSON-STANFORD 01/026 RPR GYWW | METCALF | ETL.7220.POLE.WOOD | 2023-06-27 | 2023-06-23 | 2024-04-01 | On-time | 2024-06-22 | 82 | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46080485 | T2 DI JEFFERSON-STANFORD 01/026 RPR GYWW | ICW
LC | 126479921 | 008/159 | T2 MNTA VSTA-LS GATS 8/159 RPL POLE | METCALF | ETL.7610.POLE.WOOD | 2023-06-29 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35512410 | T2 MNTA VSTA-LS GATS 8/159 RPL POLE | 70Y
LC | 126466369 | 002/024B | T2 DI NARROWS #1 TAP 2/24B RPR GYWW | SACTO | ETL.6511.POLE.WOOD | 2023-06-27 | 2023-06-23 | 2024-05-10 | On-time | 2024-06-22 | 43 | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46102287 | T2 DI NARROWS #1 TAP 2/24B RPR GYWW | ICW
LC | 126480252 | 015/495 | T2 EI SPAULDING-SUMMIT 15/495 RPL POLE | SACTO | ETL.8060.POLE.WOOD | 2023-06-29 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508789 | T2 EI SPAULDING-SUMMIT 15/495 RPL POLE | 70Y
LC | 126480322 | 057/420 | T2 DI BRIDGEVILLE-COTTON 57/420 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-06-29 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 46088703 | T2 DI BRIDGEVILLE-COTTON 57/420 RPR OPGW | ICS
LC | 126480944 | 057/418 | T2 DI BRDGVL CTTNWD 57/418 RPL HRDT | TABLEMTN | ETL.1110.TOWR | 2023-06-29 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46125142 | T2 DI BRDGVL CTTNWD 57/418 RPL HRDT | ICQ
LC | 126466392 | 029/011 | T2 DI PHILO JCT-ELK 029/011 COTTER | WILLITS | ETL.7780.INSL.NCER | 2023-06-27 | 2023-06-23 | 2024-06-07 | On-time | 2024-06-22 | 15 | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46213815 | T2 DI PHILO JCT-ELK 029/011 COTTER | ICW
LC | 126466404 | 012/104 | T2 DI CBRL-ST YNZ SW 12/104 RPL INSW | PISMOBCH | ETL.1200.INSL.NCER | 2023-06-27 | 2023-06-23 | 2024-06-21 | On-time | 2024-06-22 | 1 | 2024-06-23 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35523059 | T2 DI CABRLLO-SANTA YNEZ 12/101 RPL INSW | 93I
LC | 126481518 | 010/058 | T2 DI LONE TREE-CAYETANO 10/58 RPL INSS | CONCORD | ETL.6160.INSL.CERA | 2023-06-29 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31671785 | DI LONE TREE-CAYETANO RPL INSS IN TWR 01 | 93K
LC | 126466441 | 011/154-GUY | T2DI VY SPRINGS-CLAY-WD 11/154G RPR GYWW | VICTOR | ETL.8264.POLE.WOOD | 2023-06-27 | 2023-06-23 | 2024-02-07 | On-time | 2024-06-22 | 136 | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46162159 | T2DI VY SPRINGS-CLAY-WD 11/154G RPR GYWW | ICW
LC | 126474052 | 058/427 | T2 DI BRIDGVL-CTNWD 58/427 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-28 | 2023-06-23 | 2024-04-05 | On-time | 2024-06-22 | 78 | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46171639 | T2 DI BRIDGVL-CTNWD 58/427 RPR OPGW | ICS
LC | 126474103 | 059/430 | T2 DI BRIDGEVLL-CTTNWD 59/430 RPR SHLS | EUREKA | ETL.1110.TOWR | 2023-06-28 | 2023-06-23 | 2024-04-05 | On-time | 2024-06-22 | 78 | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46171660 | T2 DI BRIDGEVLL-CTTNWD 59/430 RPR SHLS | ICS
LC | 126474296 | A000/002 | T2 DI KM GREEN TAP A0/2 RPL INSS | VICTOR | ETL.3505.INSL.NCER | 2023-06-28 | 2023-06-23 | 2024-06-14 | On-time | 2024-06-22 | 8 | 2024-06-23 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672549 | T2 DI KM GREEN TAP A0/2 RPL INSS | 93K
LC | 126474459 | 059/431 | T2 DI BRDGVLL-CTTNWD 59/431 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-28 | 2023-06-23 | 2023-10-31 | On-time | 2024-06-22 | 235 | 2023-09-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45870517 | T2 DI BRDGVLL-CTTNWD 59/431 RPR SHLS | ICS
LC | 126481823 | 060/434A | T2 DI BRIDGEVLE-COTONWD 60/434A RPR OPGW | EUREKA | ETL.1110.POLE.NWOD | 2023-06-29 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45870600 | T2 DI BRIDGEVLE-COTONWD 60/434A RPR OPGW | ICS
LC | 126474572 | 059/433 | T2 DI BRDGVLE-CTNWD 59/433 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-28 | 2023-06-23 | 2023-11-01 | On-time | 2024-06-22 | 234 | 2023-09-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45870519 | T2 DI BRDGVLE-CTNWD 59/433 RPR SHIELD | ICS
LC | 126474650 | A000/008 | T2 DI KM GREEN TAP A0/8 RPL INSS | VICTOR | ETL.3505.INSL.NCER | 2023-06-28 | 2023-06-23 | 2023-07-21 | On-time | 2024-06-22 | 337 | 2024-06-23 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31669348 | T2 DI KM GREEN TAP A0/8 RPL INSS | 93K
LC | 126474708 | 000/003 | T2 DI BLACK TAP 000/003 COMPLETE | TABLEMTN | ETL.5431.TOWR | 2023-06-28 | 2023-06-23 | 2024-05-22 | On-time | 2024-06-22 | 31 | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46083512 | T2 DI BLACK TAP 000/003 RPR GYWS | ICS
LC | 126481896 | 020/094 | T2 DI TDWTR-SOBRANTE 02/94 RPL HRDT | CONCORD | ETL.5770.TOWR | 2023-06-29 | 2023-06-23 | 2024-06-26 | Late | 2024-06-22 | -4 | 2024-06-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46132501 | T2 DI TDWTR-SOBRANTE 02/94 RPL HRDT | ICQ
LC | 126474778 | A014/294 | T2 DI SALINAS-LRLS A014/294 RPR ANCW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-28 | 2023-06-23 | 2023-08-08 | On-time | 2024-06-22 | 319 | 2023-12-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45881499 | T2 DI SALINAS-LRLS A014/294 RPR ANCW | ICW
LC | 126477760 | 001/028 | T2 DI JFFRSN-STNFRD 1/28 RMV VEG | METCALF | ETL.7220.POLE.WOOD | 2023-06-29 | 2023-06-23 | 2024-05-21 | On-time | 2024-06-22 | 32 | 2024-06-23 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126479249 | 003/014 | T2 DI MNTA VSTA-JFRSN #2 3/14 RPL INSS | METCALF | ETL.5230.INSL | 2023-06-29 | 2023-06-23 | 2024-03-19 | On-time | 2024-06-22 | 95 | 2024-06-23 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31674006 | T2 DI MONTA VISTA-JEFF #2 RPL INSS IN 7 | 93K
LC | 126481941 | 011/055 | T2 DI TULUCAY-VACA #1 011/055 RPL INSS | LAKEVLLE | ETL.5800.INSL | 2023-06-29 | 2023-06-26 |  | Late | 2024-06-25 |  | 2024-06-26 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510309 | T2 WV TULUCAY-VACA RPL INSS IN 3 TWRS. | 93K
LC | 126481953 | ;002/008 | T2 DI CARIBOU #2 ;2/8 RPL TIED | TABLEMTN | ETL.6280.INSL.NCER | 2023-06-29 | 2023-06-24 |  | Late | 2024-06-23 |  | 2023-09-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Tie Wire-Wood | Replace | 46045958 | T2 DI CARIBOU #2 ;2/008 RPL TIED | ICW
LC | 126479381 | 002/024A | T2 DI NARROWS#1 TAP 02/024A RPR GYWW | SACTO | ETL.6511.POLE.WOOD | 2023-06-29 | 2023-06-23 | 2024-05-10 | On-time | 2024-06-22 | 43 | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46102290 | T2 DI NARROWS#1 TAP 02/024A RPR GYWW | ICW
LC | 126481018 | 057/418 | T2 DI BRDGVL CTTNWD 57/418 RPL SPLS | TABLEMTN | ETL.1110.INSL.NCER | 2023-06-29 | 2023-06-23 | 2023-11-06 | On-time | 2024-06-22 | 229 | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Steel | Replace | 45895041 | T2 DI BRDGVL CTTNWD 57/418 RPL SPLS | ICS
LC | 126481984 | A001/015 | T2 DI KM GREEN TAP A001/015 RPR INSS | VICTOR | ETL.3505.INSL.NCER | 2023-06-29 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46081387 | T2 DI KM GREEN TAP A001/015 RPR INSS | ICS
LC | 126481988 | 006/116 | T2 DI CARIBOU-WSWD 6/116 RMV VEG | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-29 | 2023-06-26 |  | Late | 2024-06-25 |  | 2024-06-26 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126482013 | :000/002 | T2 EI PIT #3-PIT #1 :000/002 RPR STRT | TABLEMTN | ETL.5400.TOWR | 2023-06-29 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 543 | TLQ | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46132562 | T2 EI PIT #3-PIT #1 :000/002 RPR STRT | ICQ
LC | 126481689 | 061/442 | T2 DI BRIDGEVILE COTTNWD 61/442 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-29 | 2023-06-23 | 2023-11-01 | On-time | 2024-06-22 | 234 | 2023-09-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45870603 | T2 DI BRIDGEVILE COTTNWD 61/442 RPR OPGW | ICS
LC | 126481890 | 020/094 | T2 DI TESORO-SOBRANTE-02/94 RPR INSS | CONCORD | ETL.5670.INSL | 2023-06-29 | 2023-06-23 | 2023-12-09 | On-time | 2024-06-22 | 196 | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45999144 | T2 DI TESORO-SOBRANTE-02/94 RPR INSS | ICS
LC | 126482037 | 069/502 | T2 DI BRDGVLL-CTTNWD 69/502 RPL INSS | EUREKA | ETL.1110.INSL.CERA | 2023-06-29 | 2023-06-21 |  | Late | 2024-06-20 |  | 2024-06-21 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509119 | T2 DI BRDGVL-CTNWD RPL INSS 6 TWRS | 93K
LC | 126481893 | 020/094 | T2 DI TDWTR-SOBRANTE 02/94 RMV NEST | CONCORD | ETL.5770.TOWR | 2023-06-29 | 2023-06-23 | 2023-12-02 | On-time | 2024-06-22 | 203 | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Debris/Nest/etc. | Structure-Steel | Remove | 45999146 | T2 DI TDWTR-SOBRANTE 02/94 RMV NEST | ICS
LC | 126484580 | 051/386 | T2 DI BRDGVLL-CTTNWD 51/386 RPR SHLS | TABLEMTN | ETL.1110.TOWR | 2023-06-30 | 2023-06-23 | 2023-10-29 | On-time | 2024-06-22 | 237 | 2023-09-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45872762 | T2 DI BRDGVLL-CTTNWD 051/386 RPR SHLS | ICS
LC | 126485774 | A000/004 | T2 DI KM GREEN TAP A0/4 RPL INSS | VICTOR | ETL.3505.INSL.NCER | 2023-06-30 | 2023-06-23 | 2024-06-14 | On-time | 2024-06-22 | 8 | 2024-06-23 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672549 | T2 DI KM GREEN TAP A0/2 RPL INSS | 93K
LC | 126484405 | 011/249 | T2 DI SLNS-LAURELES 011/249 RPR GYWW | MOSSLNDG | ETL.7930.POLE.NWOD | 2023-06-30 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46049296 | T2 DI SLNS-LAURELES 011/249 RPR GYWW | ICW
LC | 126484437 | 023/271 | T2 DI DRUM SUMMIT#1 23/271 RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2023-06-30 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126484518 | 008/053 | T2 DI COTTONWOOD #1 008/053 RPL INSS | TABLEMTN | ETL.6620.INSL.CERA | 2023-06-30 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513982 | T2 DI COTTONWOOD #1 RPL INSS 4 TWRS | 93K
LC | 126486432 | 006/069 | T2 DI CLGT-SMRTVLL #2 6/69 RPL HRDD | SACTO | ETL.6520.POLE.WOOD | 2023-06-30 | 2023-06-23 | 2023-08-06 | On-time | 2024-06-22 | 321 | 2023-09-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45907748 | T2 DI CLGT-SMRTVLL #2 6/69 RPL HRDD | ICW
LC | 126488502 | 061/444 | T2 DI BRDGVLL-CTTNWD 61/444 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-30 | 2023-06-23 | 2024-04-03 | On-time | 2024-06-22 | 80 | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46171663 | T2 DI BRDGVLL-CTTNWD 61/444 RPR OPGW | ICS
LC | 126484685 | A014/302 | T2 DI SLNAS LURLES A14/302 RMV VEG | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-30 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126484757 | 032/004 | T2 DI FRT RSS-GUALALA 32/004 RPR STRW | LAKEVLLE | ETL.6980.POLE.WOOD | 2023-06-30 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46190207 | T2 DI FRT RSS-GUALALA 32/004 RPR STRW | ICW
LC | 126484788 | 001/022 | T2 DI JEFFERSON-STANFORD 01/022 RMV VEG | METCALF | ETL.7220.POLE.WOOD | 2023-06-30 | 2023-06-26 |  | Late | 2024-06-25 |  | 2024-06-26 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126484873 | 018/088 | T2 DI TIDEWATER-SBRNTE 18/88 RPR SHLD | CONCORD | ETL.5770.INSL.NCER | 2023-06-30 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 45999147 | T2 DI TIDEWATER-SBRNTE 18/88 RPR SHLS | ICS
LC | 126484887 | 007/090 | T2 EI WST PNT-VLY SPNGS 7/90 RPL POLE | VICTOR | ETL.8350.POLE.WOOD | 2023-06-30 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525533 | T2 EI WST PNT-VLY SPNGS 7/90 RPL STRW | 70Y
LC | 126491001 | 012/009 | T2 DI CARIBOU-PLUMAS JCT 12/9 RPL ANCHRW | TABLEMTN | ETL.6290.POLE.WOOD | 2023-06-30 | 2023-06-23 | 2024-05-08 | On-time | 2024-06-22 | 45 | 2024-06-23 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35518838 | T2 DI CARIBOU-PLUMAS JCT 12/9 RPL ANCHRW | 93E
LC | 126485098 | 007/089 | T2 EI WST PNT-VLLY SPRNGS 7/089 RPL POLE | VICTOR | ETL.8350.POLE.WOOD | 2023-06-30 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | Rotten | Structure-Wood | Replace | 35525532 | T2 EI WST PNT-VLLY SPRNGS 7/089 RPL STRW | 70Y
LC | 126485163 | 065/473 | T2 DI BRIDGEVILLE-CTTNWD 65/473 RPR FOND | EUREKA | ETL.1110.TOWR | 2023-06-30 | 2023-06-22 | 2024-06-24 | Late | 2024-06-21 | -3 | 2024-06-22 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46125096 | T2 DI BRIDGEVILLE-CTTNWD 65/473 RPR FOND | ICQ
LC | 126491399 | 051/387 | T2 DI BRDGVLL-CTTNWD 051/387 RPR SHLS | TABLEMTN | ETL.1110.TOWR | 2023-06-30 | 2023-06-23 | 2023-10-29 | On-time | 2024-06-22 | 237 | 2023-09-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45881981 | T2 DI BRDGVLL-CTTNWD 051/387 RPR SHLS | ICS
LC | 126492190 | 000/013 | T2 DI CLGTE SMTVL #2 00/013 RPL STRW | SACTO | ETL.6520.POLE.WOOD | 2023-07-01 | 2023-06-23 | 2024-05-03 | On-time | 2024-06-22 | 50 | 2024-06-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35517565 | T2 DI CLGTE SMTVL #2 00/013 RPL STRW | 70Y
LC | 126485711 | 018/015 | T2 DI TRINITY-MAPLE CRK 18/15 RPR JUMW | EUREKA | ETL.8170.INSL.NCER | 2023-06-30 | 2023-06-26 |  | Late | 2024-06-25 |  | 2024-06-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46079366 | T2 DI TRINITY-MAPLE CRK 18/15 RPR JUMW | ICW
LC | 126485713 | 018/015 | T2 DI TRINITY-MAPLE CRK 18/15C RPR ANCW | EUREKA | ETL.8170.POLE.STPS | 2023-06-30 | 2023-06-26 |  | Late | 2024-06-25 |  | 2023-12-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46079366 | T2 DI TRINITY-MAPLE CRK 18/15 RPR JUMW | ICW
LC | 126485714 | 018/015 | T2 DI TRINITY-MAPLE CRK 18/15L RPR ANCW | EUREKA | ETL.8170.POLE.STPS | 2023-06-30 | 2023-06-26 |  | Late | 2024-06-25 |  | 2023-12-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46079366 | T2 DI TRINITY-MAPLE CRK 18/15 RPR JUMW | ICW
LC | 126485715 | 018/015 | T2 DI TRINITY-MAPLE CRK 18/15R RPR ANCW | EUREKA | ETL.8170.POLE.STPS | 2023-06-30 | 2023-06-26 |  | Late | 2024-06-25 |  | 2023-12-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46079366 | T2 DI TRINITY-MAPLE CRK 18/15 RPR JUMW | ICW
LC | 126492453 | 004/048 | T2 DI COLGAT-SMRTVL#2 4/48 RPL STRW | SACTO | ETL.6520.POLE.WOOD | 2023-07-01 | 2023-06-23 | 2024-04-30 | On-time | 2024-06-22 | 53 | 2024-06-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35481572 | T2 DI COLGAT-SMRTVL#2 4/48 RPL STRW | 70Y
LC | 126493441 | 061/441 | T2 DI BRDGVL CTTNWD 61/441 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-07-01 | 2023-06-23 | 2023-11-01 | On-time | 2024-06-22 | 234 | 2023-09-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45870602 | T2 DI BRDGVL CTTNWD 61/441 RPR SHLS | ICS
LC | 126494982 | 005/128 | T2 DI DEL MONTE-VIEJO 5/128 RPL STRW | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-07-01 | 2023-06-23 | 2024-05-16 | On-time | 2024-06-22 | 37 | 2024-06-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 35515620 | T2 DI DEL MONTE-VIEJO 5/128 RPL STRW | 70Y
LC | 126495475 | 060/439 | T2 DI BRDGVL-CTNWD 60/539 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-07-01 | 2023-06-23 | 2023-11-01 | On-time | 2024-06-22 | 234 | 2023-09-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45872655 | T2 BRDGVL-CTNWD 60/539 RPR OPGW | ICS
LC | 126495749 | 058/423 | T2 DI BRDGVL-CTNWD-58/423 RPR OPGW | TABLEMTN | ETL.1110.TOWR | 2023-07-01 | 2023-06-23 | 2023-10-31 | On-time | 2024-06-22 | 235 | 2023-09-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45870514 | T2 DI BRDGVL-CTNWD-58/423 RPR OPGW | ICS
LC | 126486052 | 065/472 | T2 DI BRDGVL-CTTNWD 65/472 RPR OPGS | EUREKA | ETL.1110.TOWR | 2023-06-30 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45872763 | T2 DI BRDGVL-CTTNWD 65/472 RPR SHLS | ICS
LC | 126486302 | 003/024 | T2 DI COTTONWOOD #1 3/24 RPL INSS | TABLEMTN | ETL.6620.INSL.CERA | 2023-06-30 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513982 | T2 DI COTTONWOOD #1 RPL INSS 4 TWRS | 93K
LC | 126495909 | 060/437 | T2 DI BRIDGVL-CTNWD-60/437 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-07-01 | 2023-06-23 | 2023-10-31 | On-time | 2024-06-22 | 235 | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45881982 | T2 DI BRIDGVL-CTNWD-60/437 RPR OPGW | ICS
LC | 126486442 | ;009/024 | T2 EI CARIBOU-PLUMAS JCT ;9/024 RPL POLE | TABLEMTN | ETL.6290.POLE.WOOD | 2023-06-30 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518833 | T2 EI CARIBOU-PLUMAS JCT ;9/024 RPL POLE | 70Y
LC | 126496115 | 060/435 | T2 DI BRDGVL-CTNWD-60/435 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-07-01 | 2023-06-23 | 2024-04-08 | On-time | 2024-06-22 | 75 | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46171662 | T2 DI BRDGVL-CTNWD-60/435 RPR OPGW | ICS
LC | 126441603 | 024/289A | T2 EI DRUM-SUMMIT #1 24/289A RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-24 | 2023-06-24 | 2023-08-07 | On-time | 2024-06-23 | 321 | 2023-09-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45872477 | T2 EI DRUM-SUMMIT #1 24/289A RPR GYWW | ICW
LC | 126486849 | 015/498 | T2 EI SPAULDING-SUMMIT 15/498 REFRAME | SACTO | ETL.8060.POLE.WOOD | 2023-06-30 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35508790 | T2 EI SPAULDING-SUMMIT 15/497 REFRAME | 93E
LC | 126441789 | 024/289B | T2 EI DRUM-SUMMIT #1 24/289B RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-24 | 2023-06-24 | 2023-08-07 | On-time | 2024-06-23 | 321 | 2023-09-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45872478 | T2 EI DRUM-SUMMIT #1 24/289B RPR GYWW | ICW
LC | 126486985 | ;009/022 | DISTRIBUTION GUY RMV VEG | TABLEMTN | ETL.6290.POLE.WOOD | 2023-06-30 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Trim
LC | 126441981 | 024/289C | T2 EI DRUM-SUMMIT #1 24/289C RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-24 | 2023-06-24 | 2023-08-07 | On-time | 2024-06-23 | 321 | 2024-06-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45872479 | T2 EI DRUM-SUMMIT #1 24/289C RPR GYWW | ICW
LC | 126487006 | 011/398 | T2 DI SPAULDING-SUMMIT 011/398 RPL INSW | SACTO | ETL.8060.INSL.NCER | 2023-06-30 | 2023-06-24 |  | Late | 2024-06-23 |  | 2023-12-24 | 508 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35508782 | T2 EI SPLDING-SMMIT 10/338 RPL INSW | 93I
LC | 126442611 | 004/047A | T2 EI HLSDALE JCT-HLF MN BY 4/47A COTTER | METCALF | ETL.7060.INSL | 2023-06-24 | 2023-06-24 | 2023-08-13 | On-time | 2024-06-23 | 315 | 2023-12-24 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45892358 | T2 EI HLSDALE JCT-HLF MN BY 4/47A COTTER | ICW
LC | 126444496 | 008/061 | T2 EI CARIBOU-TABLE MTN 008/061 RMV VEG | TABLEMTN | ETL.4440.TOWR | 2023-06-24 | 2023-06-24 | 2024-03-22 | On-time | 2024-06-23 | 93 | 2024-06-24 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126444497 | 008/061 | T2 EI CARIBOU-TABLE MTN 008/061 COTTER | TABLEMTN | ETL.4440.INSL.CERA | 2023-06-24 | 2023-06-24 | 2024-06-06 | On-time | 2024-06-23 | 17 | 2024-06-24 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46088172 | T2 EI CARIBOU-TABLE MTN 008/061 COTTER | ICS
LC | 126444607 | 003/031 | T2 EI ROCK CREEK-POE 003/031 RPL INSS | TABLEMTN | ETL.5630.INSL | 2023-06-24 | 2023-06-24 | 2024-02-26 | On-time | 2024-06-23 | 118 | 2024-06-24 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509199 | T2 DI ROCK CREEK-POE :5/33 RPLC INSS | 93K
LC | 126487402 | 015/497 | T2 EI SPAULDING-SUMMIT 15/497 REFRAME | SACTO | ETL.8060.POLE.WOOD | 2023-06-30 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 637T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35508790 | T2 EI SPAULDING-SUMMIT 15/497 REFRAME | 93E
LC | 126487422 | 018/218B | T2 DI DRUM SUMMIT#1 18/218B RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-30 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098423 | T2 DI DRUM SUMMIT#1 18/218B RPR GYWW | ICW
LC | 126481888 | 001/050 | T2 DI SPAULDING-SUMMIT 001/050 RPR GYWW | SACTO | ETL.8060.POLE.NWOD | 2023-06-29 | 2023-06-24 | 2023-09-27 | On-time | 2024-06-23 | 270 | 2023-12-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45872462 | T2 DI SPAULDING-SUMMIT 001/050 RPR GYWW | ICW
LC | 126482032 | 000/001 | T2 DI CRUSHER TAP 000/001 RPR GYWW | MOSSLNDG | ETL.6241.POLE.NWOD | 2023-06-29 | 2023-06-24 | 2024-04-01 | On-time | 2024-06-23 | 83 | 2024-06-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46081739 | T2 DI CRUSHER TAP 000/001 RPR GYWW | ICW
LC | 126487801 | 003/073 | T2 DI CARIBOU-WSTWD 003/073 COMPLETED | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-30 | 2023-06-26 |  | Late | 2024-06-25 |  | 2024-06-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46091961 | T2 DI CARIBOU-WSTWD 003/073 RPR ANCW | ICW
LC | 126487823 | 006/080 | T2 EI WEST PNT-VLLY SPRNGS 6/80 RPL POLE | VICTOR | ETL.8350.POLE.WOOD | 2023-06-30 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35525531 | T2 EI WEST PNT-VLLY SPRNGS 6/80 RPL STRW | 70Y
LC | 126488243 | 065/004 | T2 HUMBOLDT-TRINITY 65/4R RPL STRW | EUREKA | ETL.1820.POLE.WDPS | 2023-06-30 | 2023-01-16 |  | Late | 2024-01-16 |  | 2024-01-16 | 372 | TLX | CREW | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31655640 | T2 HUMBOLDT-TRINITY 65/4 RPL STRW | 70Y
LC | 126488347 | 015/136 | T2 DI BRDGVIL CTTNWD 15/136R RPL STRW | TABLEMTN | ETL.1110.POLE.WDPS | 2023-06-30 | 2023-05-02 |  | Late | 2024-05-01 |  | 2024-05-02 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35501390 | T2 DI BRDGVIL CTTNWD RPL 7 STRCTS | 70Y
LC | 126482033 | 15 | T2 DI CRUSHER TAP SW 15 0/1 RPR SWTC | MOSSLNDG | ETL.6241.SWIT | 2023-06-29 | 2023-06-24 | 2024-05-20 | On-time | 2024-06-23 | 34 | 2024-06-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Switch-Wood | Repair | 46081742 | T2 DI CRUSHER TAP SW 15 0/1 RPR SWTC | ICW
LC | 126486739 | 008/041 | T2 DI VACA-LAKEVILLE #1 8/41 RPL INSS | LAKEVLLE | ETL.5840.INSL.CERA | 2023-06-30 | 2023-06-24 | 2024-05-02 | On-time | 2024-06-23 | 52 | 2024-06-24 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31678228 | T2 WV VACA-LAKEVILLE #1 RPL INSS IN 4 TW | 93K
LC | 126488431 | 006/072 | T2 EI WST PNT-VLLY SPRNGS 6/72 RPR STRW | VICTOR | ETL.8350.POLE.WOOD | 2023-06-30 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46200347 | T2 EI WST PNT-VLLY SPRNGS 6/072 RPR STRW | ICW
LC | 126486880 | 013/066 | T2 DI TULUCAY-VACA 13/66 RPL INSS | SACTO | ETL.5800.INSL | 2023-06-30 | 2023-06-24 | 2023-11-15 | On-time | 2024-06-23 | 221 | 2024-06-24 | 532 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31672705 | T2 DI TULUCAY-VACA RPL INSS | 93K
LC | 126488732 | 006/074 | T2 EI WST PNT-VLLY SPRNGS 6/074 RPL POLE | VICTOR | ETL.8350.POLE.WOOD | 2023-06-30 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527133 | T2 EI WST PNT-VLLY SPRNGS 6/074 RPL STRW | 70Y
LC | 126489025 | 057/419C | T2 DI BRDGVIL CTTNWD 57/419C RMV VEG | TABLEMTN | ETL.1110.POLE.NWOD | 2023-06-30 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126491468 | 006/134 | T2 DI SALINAS-LAURELES 06/134 RPR ANCW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-06-30 | 2023-06-24 | 2024-03-21 | On-time | 2024-06-23 | 94 | 2024-06-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46082032 | T2 DI SALINAS-LAURELES 06/134 RPR ANCW | ICW
LC | 126492066 | 45 | T2 DI BEALE AFB(W)#2 TP 0/2 RPR SWTC 45 | SACTO | ETL.7971.SWIT | 2023-07-01 | 2023-06-24 | 2023-10-13 | On-time | 2024-06-23 | 254 | 2023-12-24 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 45871058 | T2 DI BEALE AFB(W)#2 TP 0/2 RPR SWTC 45 | ICE
LC | 126492067 | 35 | T2 DI BEALE AFB(W)#2 TP 0/2 RPR SWTC 35 | SACTO | ETL.7971.SWIT | 2023-07-01 | 2023-06-24 | 2023-10-13 | On-time | 2024-06-23 | 254 | 2023-12-24 | 623 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Out of Adjustment | Switch | Repair | 45871058 | T2 DI BEALE AFB(W)#2 TP 0/2 RPR SWTC 45 | ICE
LC | 126492252 | 011/399 | T2 DI SPAULDING-SUMMIT 011/399 RPL INSW | SACTO | ETL.8060.INSL.NCER | 2023-07-01 | 2023-06-24 | 2023-07-18 | On-time | 2024-06-23 | 341 | 2023-12-24 | 508 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 31654291 | T2 DI SPAULDING-SUMMIT 011/399 RPL INSW | 93I
LC | 126489984 | 080/566 | T2 DI BRIDGE-COTTNWD 80/566L RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-06-30 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171853 | T2 DI BRIDGE-COTTNWD 80/566L RPR GYWW | ICW
LC | 126489985 | 080/566 | T2 DI BRIDGE-COTTNWD 80/566R RPR GYWW | EUREKA | ETL.1110.POLE.STPS | 2023-06-30 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46171853 | T2 DI BRIDGE-COTTNWD 80/566L RPR GYWW | ICW
LC | 126490075 | 009/106 | T2 EI WST PNT-VLY SPNGS 9/106 RPR STRW | VICTOR | ETL.8350.POLE.WOOD | 2023-06-30 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46200348 | T2 EI WST PNT-VLY SPNGS 9/106 RPR STRW | ICW
LC | 126490077 | 009/106 | T2 EI WST PNT-VLY SPNGS 9/106 RPL INSW | VICTOR | ETL.8350.INSL.CERA | 2023-06-30 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35525535 | T2 EI WST PNT-VLY SPNGS 9/106 RPL INSW | 93I
LC | 126490083 | 237 | T2 DI BRDGVLL-CTTNWD 58/426 RPL SWITCH | TABLEMTN | ETL.1110.SWIT | 2023-06-30 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 435T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Switch-Steel | Replace | 35533712 | T2 DI BRDGVLL-CTTNWD 58/426 RPL SWITCH | 93S
LC | 126492382 | 026/126 | T2 DI MONTA VS-C SWST 26/126 RPR SHLS | MOSSLNDG | ETL.5090.INSL | 2023-07-01 | 2023-06-24 | 2024-03-04 | On-time | 2024-06-23 | 111 | 2024-06-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46081622 | T2 DI MONTA VS-C SWST 26/126 RPR SHLS | ICS
LC | 126490580 | 000/007 | T2 MAPLE CREEK-HOOPA 00/07 RPR INSW | EUREKA | ETL.7490.INSL.NCER | 2023-06-30 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46203537 | T2 MAPLE CREEK-HOOPA 00/07 RPR INSW | ICW
LC | 126490911 | 15 | T2 DI BEALE AFB #1 TAP 0/2 RPR SWTCH | SACTO | ETL.8001.SWIT | 2023-06-30 | 2023-06-24 |  | Late | 2024-06-23 |  | 2023-12-24 | 623 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Out of Adjustment | Switch | Repair | 46093539 | T2 DI BEALE AFB #1 TAP 0/2 RPR SWTCH | ICE
LC | 126492383 | 026/126 | T2 DI MONTA VS-C SWST 26/126 RPR INSS | MOSSLNDG | ETL.5090.INSL | 2023-07-01 | 2023-06-24 | 2024-03-04 | On-time | 2024-06-23 | 111 | 2024-06-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46081625 | T2 DI MONTA VS-C SWST 26/126 RPR INSS | ICS
LC | 126490943 | 079/564 | T2 DI BRIDGEVL-CTTNWD 79/564L RPR OPGW | EUREKA | ETL.1110.POLE.WDPS | 2023-06-30 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Repair | 46171852 | T2 DI BRIDGEVL-CTTNWD 79/564L RPR OPGW | ICW
LC | 126490944 | 079/564 | T2 DI BRIDGVL-CTTNWD 79/564L RPR GRWW | EUREKA | ETL.1110.POLE.WDPS | 2023-06-30 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 46171852 | T2 DI BRIDGEVL-CTTNWD 79/564L RPR OPGW | ICW
LC | 126492385 | 026/126 | T2 DI MONTA VS-C SWST 26/126 RPR FOND | MOSSLNDG | ETL.5090.TOWR | 2023-07-01 | 2023-06-24 | 2024-03-05 | On-time | 2024-06-23 | 110 | 2024-06-24 | 543 | TLQ |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Foundation/Concrete-Tower | Repair | 46087947 | T2 DI MONTA VS-C SWST 26/126 RPR FOND | ICQ
LC | 126494335 | 068/490 | T2 DI BRDGVLL-CTTNWD 68/490L COMPLETE | EUREKA | ETL.1110.POLE.WDPS | 2023-07-01 | 2023-06-24 | 2024-04-05 | On-time | 2024-06-23 | 79 | 2024-06-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46171676 | T2 DI BRDGVLL-CTTNWD 068/490L RPL HRDD | ICW
LC | 126496084 | 013/450 | T2 DI SPAULDING-SUMMIT 13/450 RPR JUNW | SACTO | ETL.8060.INSL.NCER | 2023-07-01 | 2023-06-24 | 2023-07-19 | On-time | 2024-06-23 | 340 | 2023-09-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45894324 | T2 DI SPAULDING-SUMMIT 13/450 RPR JUNW | ICW
LC | 126491171 | 021/248 | T2 DI DRUM-SUMMIT #1 021/248C RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2023-06-30 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126491173 | 021/248 | T2 DI DRUM-SUMMIT #1 021/248R RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2023-06-30 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126498701 | :000/003 | T2 DI STANS-MLNS SW ST RVRBN :0/3 COTTER | VICTOR | ETL.3840.INSL.NCER | 2023-07-03 | 2023-06-24 | 2024-03-19 | On-time | 2024-06-23 | 96 | 2024-06-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46162203 | T2 DI STANS-MLNS SW ST RVRBN :0/3 COTTER | ICS
LC | 126501094 | 000/006 | T2 DI CLMN-RED BLUFF 0/006 RPR GYWW | TABLEMTN | ETL.6440.POLE.NWOD | 2023-07-03 | 2023-06-24 | 2024-03-05 | On-time | 2024-06-23 | 110 | 2024-06-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46088747 | T2 DI CLMN-RED BLUFF 0/006 RPR GYWW | ICW
LC | 126491322 | 055/002 | T2 DI HUMBOLDT-TRINITY 55/02 RPR JMPW | EUREKA | ETL.1820.INSL.NCER | 2023-06-30 | 2023-06-21 |  | Late | 2024-06-20 |  | 2023-09-21 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46193771 | T2 DI HUMBOLDT-TRINITY 55/02 RPR JMPW | ICW
LC | 126491369 | 010/124 | T2 DI DRUM-SUMMIT#1 10/124L RPR POLE | SACTO | ETL.1440.POLE.WDPS | 2023-06-30 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46098424 | T2 DI DRUM-SUMMIT#1 10/124L RPR POLE | ICW
LC | 126501245 | A016/251 | T2 DI CLMN-RED BLUFF A16/251 RPR JUMW | TABLEMTN | ETL.6440.INSL.NCER | 2023-07-03 | 2023-06-24 | 2023-11-07 | On-time | 2024-06-23 | 229 | 2024-06-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 45881985 | T2 DI CLMN-RED BLUFF A016/251 RPR JUMW | ICW
LC | 126491410 | 010/124 | T2 DI DRUM-SUMMIT#1 10/124R RPR POLE | SACTO | ETL.1440.POLE.WDPS | 2023-06-30 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46098425 | T2 DI DRUM-SUMMIT#1 10/124R RPR POLE | ICW
LC | 126508994 | 007/016 | T2 DI MONTE RIO-FULTON 07/16 RMV VEG | LAKEVLLE | ETL.7630.POLE.WOOD | 2023-07-05 | 2023-06-24 | 2024-05-28 | On-time | 2024-06-23 | 26 | 2024-06-24 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126491471 | 033/651 | T2 DI HAT CRK #1-WSTWD 033/651 GO95 | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-30 | 2023-06-23 | 2024-06-26 | Late | 2024-06-22 | -4 | 2024-06-23 | 401T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | Overloaded | GO95 Clear Infract-Wood | Replace | 35525688 | T2 DI HAT CRK #1-WSTWD 033/651 GO95 | 93G
LC | 126509159 | 000/003B | T2 DI CRUSHER TP 0/3B RMV VEG OG | MOSSLNDG | ETL.6241.POLE.WOOD | 2023-07-05 | 2023-06-24 | 2024-05-08 | On-time | 2024-06-23 | 46 | 2023-12-24 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126491572 | 080/568 | T2 DI BRDGVLLE-CTNWD 80/568 RPR ADSS | EUREKA | ETL.1110.TOWR | 2023-06-30 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | ADSS - Steel | Repair | 46171854 | T2 DI BRDGVLLE-CTNWD 80/568 RPR ADSS | ICS
LC | 126509178 | 006/072 | T2 DI MTN GATE JCT-CAS 6/72 RPL INSW | TABLEMTN | ETL.7640.INSL | 2023-07-05 | 2023-06-24 | 2024-02-17 | On-time | 2024-06-23 | 127 | 2024-06-24 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35484838 | T2 DI MTN GATE JCT-CASCADE 4/44 RPL INSW | 93I
LC | 126509237 | 000/003A | T2 DI CRUSHER TP 0/3A RMV VEG OG | MOSSLNDG | ETL.6241.POLE.WOOD | 2023-07-05 | 2023-06-24 | 2024-05-08 | On-time | 2024-06-23 | 46 | 2023-12-24 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126492103 | 067/486 | T2 DI BRIDGEVL-COT 67/486 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-07-01 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45872761 | T2 DI BRIDGEVL-COT 67/486 RPR SHLS | ICS
LC | 126492123 | 070/509 | T2 DI BRDGVL-CTNWD 70/509L RPL XBRACE | EUREKA | ETL.1110.POLE.WDPS | 2023-07-01 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35505104 | T2 DI BRDGVL-CTNWD 70/509L RPL XBRACE | 93E
LC | 126516752 | 000/003C | T2 DI CRUSHER TAP- 00/03C RMV VEG | MOSSLNDG | ETL.6241.POLE.WOOD | 2023-07-06 | 2023-06-24 | 2024-05-08 | On-time | 2024-06-23 | 46 | 2023-12-24 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126445517 | 011/092 | T2 EI CRESTA-RIO OSO 011/092 RMV VEG | TABLEMTN | ETL.4590.TOWR | 2023-06-25 | 2023-06-25 | 2024-01-31 | On-time | 2024-06-24 | 145 | 2024-06-25 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126446536 | 026/320C | T2 EI DRUM-SUMMIT #2 26/320C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-25 | 2023-06-25 | 2024-06-23 | On-time | 2024-06-24 | 1 | 2024-06-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098260 | T2 EI DRUM-SUMMIT #2 26/320C RPR GYWW | ICW
LC | 126446578 | 026/320A | T2 EI DRUM-SUMMIT #2 26/320A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-25 | 2023-06-25 | 2024-06-23 | On-time | 2024-06-24 | 1 | 2024-06-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098261 | T2 EI DRUM-SUMMIT #2 26/320A RPR GYWW | ICW
LC | 126446656 | 026/320B | T2 EI DRUM-SUMMIT #2 26/320B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-25 | 2023-06-25 | 2024-06-23 | On-time | 2024-06-24 | 1 | 2024-06-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098262 | T2 EI DRUM-SUMMIT #2 26/320B RPR GYWW | ICW
LC | 126446718 | 024/287C | T2 EI DRUM-SUMMIT #2 024/287C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-25 | 2023-06-25 | 2024-06-20 | On-time | 2024-06-24 | 4 | 2023-12-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098263 | T2 EI DRUM-SUMMIT #2 024/287C RPR GYWW | ICW
LC | 126447082 | 026/317A | T2 EI DRUM-SUMMIT #2 26/317A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-25 | 2023-06-25 | 2024-06-23 | On-time | 2024-06-24 | 1 | 2023-12-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098264 | T2 EI DRUM-SUMMIT #2 26/317A RPR GYWW | ICW
LC | 126447115 | 026/317B | T2 EI DRUM-SUMMIT #2 26/317B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-25 | 2023-06-25 | 2024-06-23 | On-time | 2024-06-24 | 1 | 2023-12-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46097958 | T2 EI DRUM-SUMMIT #2 26/317B RPR GYWW | ICW
LC | 126447163 | 026/317C | T2 EI DRUM-SUMMIT #2 26/317C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-25 | 2023-06-25 | 2024-06-23 | On-time | 2024-06-24 | 1 | 2023-12-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46097959 | T2 EI DRUM-SUMMIT #2 26/317C RPR GYWW | ICW
LC | 126492660 | 008/102 | T2 EI WST PNT-VLY SPNGS 8/102 RPR STRW | VICTOR | ETL.8350.POLE.WOOD | 2023-07-01 | 2023-07-01 |  | Late | 2024-06-30 |  | 2024-07-01 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46200350 | T2 EI WST PNT-VLY SPNGS 8/102 RPR STRW | ICW
LC | 126492677 | 179 | T2 DI FULTON-PUEBLO 12/60 RPR SWTC | LAKEVLLE | ETL.1600.SWIT | 2023-07-01 | 2023-06-24 |  | Late | 2024-06-23 |  | 2023-09-24 | 623 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | Out of Adjustment | Switch | Repair | 46096648 | T2 DI FULTON-PUEBLO 12/60 RPR SWTC | ICE
LC | 126447391 | 026/315A | T2 EI DRUM-SUMMIT #2 26/315A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-25 | 2023-06-25 | 2024-06-23 | On-time | 2024-06-24 | 1 | 2023-12-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098380 | T2 EI DRUM-SUMMIT #2 26/315A RPR GYWW | ICW
LC | 126447398 | 026/315B | T2 EI DRUM-SUMMIT #2 26/315B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-25 | 2023-06-25 | 2024-06-23 | On-time | 2024-06-24 | 1 | 2023-12-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098381 | T2 EI DRUM-SUMMIT #2 26/315B RPR GYWW | ICW
LC | 126447450 | 026/315C | T2 EI DRUM-SUMMIT #2 26/315C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-25 | 2023-06-25 | 2024-06-23 | On-time | 2024-06-24 | 1 | 2023-12-25 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098382 | T2 EI DRUM-SUMMIT #2 26/315C RPR GYWW | ICW
LC | 126447691 | 021/250 | T2 EI DRUM-SUMMIT #1 21/250 RPL ANCW | SACTO | ETL.1440.POLE.STPS | 2023-06-25 | 2023-06-25 | 2023-08-08 | On-time | 2024-06-24 | 321 | 2023-09-25 | 637 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31654424 | T2 EI DRUM-SUMMIT #1 21/250 RPL ANCW | 93E
LC | 126448120 | 002/066 | T2 EI HMLTN BRNCH-CHSTR 2/66 RPL GYPL | TABLEMTN | ETL.7000.POLE.NWOD | 2023-06-25 | 2023-06-25 | 2023-10-04 | On-time | 2024-06-24 | 264 | 2024-06-25 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Guy Pole-Wood | Replace | 31663420 | T2 EI HMLTN BRNCH-CHSTR 2/66 RPL GYPL | 70Y
LC | 126492961 | 022/264 | T2 DI DRUM SUMMIT#1 22/264 RPR HRDW | SACTO | ETL.1440.POLE.STPS | 2023-07-01 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46098428 | T2 DI DRUM SUMMIT#1 22/264 RPR HRDW | ICW
LC | 126492964 | 002/054 | T2 DI DEL MNTE-VIEJO 02/054 RPL STRW | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-07-01 | 2023-06-28 |  | Late | 2024-06-27 |  | 2024-06-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35515354 | T2 DI DEL MNTE-VIEJO 02/054 RPL STRW | 70Y
LC | 126453221 | 027/321C | T2 EI DRUM-SUMMIT #2 27/321C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-26 | 2023-06-26 | 2024-06-23 | On-time | 2024-06-25 | 2 | 2024-06-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098383 | T2 EI DRUM-SUMMIT #2 027/321C RPR GYWW | ICW
LC | 126493027 | 010/143 | T2 DI DT-MTN GT JCT-MTN 10/143L RPL STRW | TABLEMTN | ETL.6750.POLE.WDPS | 2023-07-01 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491299 | T2 DI DLTA-MTN GATE 10/142 RPL POLE | 70Y
LC | 126493076 | 043/343 | T2 DI BRDGVL-CTNWD 43/343 RMV VEG | TABLEMTN | ETL.1110.TOWR | 2023-07-01 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126493133 | 043/343 | T2 DI BRDGVL-CTNWD 43/343 RPL INSS | TABLEMTN | ETL.1110.INSL.CERA | 2023-07-01 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509192 | T2 DI BRIDGEVILLE-CTTNWD RPL INSS 9 TWRS | 93K
LC | 126453430 | 027/321B | T2 EI DRUM-SUMMIT #2 27/321B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-26 | 2023-06-26 | 2024-06-23 | On-time | 2024-06-25 | 2 | 2024-06-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098384 | T2 EI DRUM-SUMMIT #2 027/321B RPR GYWW | ICW
LC | 126493277 | 053/1041 | T2 DI HAT CRK #1-WSTWD 53/1041 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-01 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 372T | TLX | TNT | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35551999 | T2 DI HAT CRK #1-WSTWD 53/1041 RPL STRW | 70Y
LC | 126453508 | 027/321A | T2 EI DRUM-SUMMIT #2 027/321A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-26 | 2023-06-26 | 2023-08-28 | On-time | 2024-06-25 | 302 | 2023-12-26 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45886112 | T2 EI DRUM-SUMMIT #2 027/321A RPR GYWW | ICW
LC | 126493530 | A000/006 | T2 DI KM GREEN TAP A0/6 RPR INSS | VICTOR | ETL.3505.INSL.NCER | 2023-07-01 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 126457055 | 040/770 | T2 EI HT CRK #1-WSTWD 40/770 COA | TABLEMTN | ETL.7030.POLE.NWOD | 2023-06-26 | 2023-06-26 | 2023-07-28 | On-time | 2024-06-25 | 333 | 2023-09-26 | 625 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Land/Enviro Issue | Other | Access Issue
LC | 126493855 | A001/012 | T2 DI KM GREEN TAP A001/012 RPL INSS | VICTOR | ETL.3505.INSL.NCER | 2023-07-01 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35562854 | T2 DI KM GREEN TAP A001/012 RPL INSS | 93K
LC | 126457056 | 040/768 | T2 EI HT CRK #1-WSTWD 40/768 COA | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-26 | 2023-06-26 | 2023-07-28 | On-time | 2024-06-25 | 333 | 2023-09-26 | 625 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Land/Enviro Issue | Other | Access Issue
LC | 126494171 | 008/001 | T2 DI MAPLE CREEK-HOOPA 08/01 RPL HRDW | EUREKA | ETL.7490.INSL.NCER | 2023-07-01 | 2023-06-28 |  | Late | 2024-06-27 |  | 2024-06-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46203535 | T2 DI MAPLE CREEK-HOOPA 08/01 RPL HRDW | ICW
LC | 126494172 | 008/001 | T2 DI MAPLE CREEK-HOOPA 08/01 RPR JUMW | EUREKA | ETL.7490.INSL.NCER | 2023-07-01 | 2023-06-28 |  | Late | 2024-06-27 |  | 2024-06-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46203536 | T2 DI MAPLE CREEK-HOOPA 08/01 RPR JUMW | ICW
LC | 126494173 | 012/062 | T2 DI TULUCAY-VACA #1 12/62 RPL INSS | LAKEVLLE | ETL.5800.INSL | 2023-07-01 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35510309 | T2 WV TULUCAY-VACA RPL INSS IN 3 TWRS. | 93K
LC | 126494174 | 008/045 | T2 DI VACA LAKEVILLE#1 8/45 RPL INSS | LAKEVLLE | ETL.5840.INSL.CERA | 2023-07-01 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31678228 | T2 WV VACA-LAKEVILLE #1 RPL INSS IN 4 TW | 93K
LC | 126457100 | 040/769 | T2 EI HT CRK #1-WSTWD 40/769 COA | TABLEMTN | ETL.7030.POLE.WOOD | 2023-06-26 | 2023-06-26 | 2023-07-28 | On-time | 2024-06-25 | 333 | 2023-09-26 | 625 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Land/Enviro Issue | Other | Access Issue
LC | 126494338 | 068/490 | T2 DI BRDGVLL-CTTNWD 68/490 COTTER | EUREKA | ETL.1110.INSL.NCER | 2023-07-01 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45872769 | T2 DI BRDGVLL-CTTNWD 068/490 COTTER | ICW
LC | 126494363 | :000/004 | T2 DI STN-MLNS SS-MNTCA :0/4 RPR STRT | VICTOR | ETL.3830.TOWR | 2023-07-01 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46087951 | T2 DI STN-MLNS SS-MNTCA :00/04 BNT STEEL | ICQ
LC | 126457432 | 007/060A | T2 EI HELMS-GREGG #1 7/60A RPR SHLS | FRESNO | ETL.4870.TOWR | 2023-06-26 | 2023-06-26 | 2024-05-15 | On-time | 2024-06-25 | 41 | 2024-06-26 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46080583 | T2 EI HELMS-GREGG #1 7/60A RPR SHLS | ICS
LC | 126494421 | 052/394 | T2 DI BRIDGEVL-COT 52/394 RPR INSS | TABLEMTN | ETL.1110.INSL.CERA | 2023-07-01 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46088702 | T2 DI BRIDGEVL-COT 52/394 RPR INSS | ICS
LC | 126457501 | 007/061A | T2 EI HELMS-GREGG #1 7/61A RPR SHLS | FRESNO | ETL.4870.TOWR | 2023-06-26 | 2023-06-26 | 2024-05-15 | On-time | 2024-06-25 | 41 | 2024-06-26 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46080606 | T2 EI HELMS-GREGG #1 7/61A RPR SHLS | ICS
LC | 126481570 | 000/012 | T2 DI CARIBOU-WSWD 000/012 RMV VEG | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-29 | 2023-06-26 | 2024-04-08 | On-time | 2024-06-25 | 78 | 2024-06-26 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126494547 | A001/011 | T2 DI KM GREEN TAP A1/11 RPR INSS | VICTOR | ETL.3505.INSL.NCER | 2023-07-01 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair
LC | 126494598 | 024/283 | T2 DI DRUM-SUMMIT #1 24/283L RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2023-07-01 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126481917 | 010/052 | T2 DI VACA-LAKVLLE #1 10/52 RPR SHLS | LAKEVLLE | ETL.5840.TOWR | 2023-06-29 | 2023-06-26 | 2024-05-02 | On-time | 2024-06-25 | 54 | 2024-06-26 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46190770 | T2 DI VACA-LAKVLLE #1 10/52 RPR SHLS | ICS
LC | 126481940 | 010/052 | T2 DI VACA-LAKVLLE #1 10/52 RPR INSS | SACTO | ETL.5840.INSL.NCER | 2023-06-29 | 2023-06-26 | 2024-03-15 | On-time | 2024-06-25 | 102 | 2024-06-26 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46097974 | T2 DI VACA-LAKVLLE #1 10/52 RPR INSS | ICS
LC | 126484684 | 011/220 | T2 DI CARBOU WSTWD 11/220 RMV VEG | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-30 | 2023-06-26 | 2024-03-08 | On-time | 2024-06-25 | 109 | 2024-06-26 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126485772 | 000/014 | T2 DI VIEJO MONTEREY 0/14 RMV VEG | MOSSLNDG | ETL.8270.POLE.WOOD | 2023-06-30 | 2023-06-26 | 2024-06-18 | On-time | 2024-06-25 | 7 | 2024-06-26 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126495267 | 011/259-GUY | T2 DI SALNS-LAURLS-11/259-GUY RMV VEG | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-07-01 | 2023-06-22 |  | Late | 2024-06-21 |  | 2024-06-22 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126485866 | 013/273 | T2 DI CARIBOU WSTWD 13/273 RMV VEG | TABLEMTN | ETL.6300.POLE.WOOD | 2023-06-30 | 2023-06-26 | 2024-03-08 | On-time | 2024-06-25 | 109 | 2024-06-26 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126485966 | 006/004B | T2 DI FORT SEWARD TAP 06/004 RPR INSW | EUREKA | ETL.6222.INSL.NCER | 2023-06-30 | 2023-06-26 | 2024-04-18 | On-time | 2024-06-25 | 68 | 2024-06-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46183735 | T2 DI FORT SEWARD TAP 6/004A RPR GYWW | ICW
LC | 126486808 | 029/008B | T2 DI PHILO JCT-ELK 29/8B RPL HRDD | WILLITS | ETL.7780.POLE.WOOD | 2023-06-30 | 2023-06-26 | 2023-09-17 | On-time | 2024-06-25 | 282 | 2024-06-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45882380 | T2 DI PHILO JCT-ELK 29/8B RPL HRDD | ICW
LC | 126487355 | 006/151 | T2 DI DEL MNTE VIEJO 06/151 RPR SPLW | MOSSLNDG | ETL.6710.INSL.NCER | 2023-06-30 | 2023-06-26 | 2024-05-23 | On-time | 2024-06-25 | 33 | 2024-06-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46081745 | T2 DI DEL MNTE VIEJO 06/151 RPR SPLW | ICW
LC | 126495659 | 016/513 | T2 DI SPLDNG-SMMT 016/513 RPL HRDD | SACTO | ETL.8060.POLE.WOOD | 2023-07-01 | 2023-06-28 |  | Late | 2024-06-27 |  | 2024-06-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46102296 | T2 DI SPLDNG-SMMT 016/513 RPL HRDD | ICW
LC | 126495702 | 029/565 | T2 DI HAT CRK#1-WSTWD-29/565 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-01 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514134 | T2 DI HAT CRK#1-WSTWD-29/565 RPL POLE | 70Y
LC | 126495729 | 051/389 | T2 DI BRIDGEVLL-COTT 51/389 RPL HRDT | TABLEMTN | ETL.1110.TOWR | 2023-07-01 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Tower | Replace | 46125147 | T2 DI BRIDGEVLL-COTT 51/389 RPL HRDT | ICQ
LC | 126490940 | 022/178 | T2 DI CRBRY SWST RND MTN 22/178 RPR CNDS | TABLEMTN | ETL.5410.INSL | 2023-06-30 | 2023-06-26 | 2023-09-15 | On-time | 2024-06-25 | 284 | 2024-06-26 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Conductor-Steel | Repair | 45939931 | T2 DI CRBRY SWST RND MTN 22/178 RPR CNDS | ICS
LC | 126491250 | 029/008A | T2 DI PHILO JCT-ELK-ELK 29/8A RPL HRDW | WILLITS | ETL.7780.POLE.WOOD | 2023-06-30 | 2023-06-26 | 2024-06-10 | On-time | 2024-06-25 | 15 | 2024-06-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46213814 | T2 DI PHILO JCT-ELK-ELK 29/8A RPL HRDW | ICW
LC | 126492181 | 029/008C | T2 DI PHILO-ELK JCT 29/8C RPL IBWW | WILLITS | ETL.7780.POLE.WOOD | 2023-07-01 | 2023-06-26 | 2023-09-17 | On-time | 2024-06-25 | 282 | 2023-09-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 45882382 | T2 DI PHILO-ELK JCT 29/8C RPL IBWW | ICW
LC | 126494475 | 026/008A | T2 DI PHILO JCT-ELK 26/8A COTTER | WILLITS | ETL.7780.POLE.NWOD | 2023-07-01 | 2023-06-26 | 2023-09-11 | On-time | 2024-06-25 | 288 | 2023-12-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45882391 | T2 DI PHILO JCT-ELK 26/8A COTTER | ICW
LC | 126495843 | 015/482 | T2 DI SPAULDING-SUMMIT 15/482 RPR INSW | SACTO | ETL.8060.INSL.NCER | 2023-07-01 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46102298 | T2 DI SPAULDING-SUMMIT 015/482 RPR INSW | ICW
LC | 126495893 | 010/360 | T2 DI SPAULDING-SUMMIT 010/360 RPR GYWW | SACTO | ETL.8060.POLE.NWOD | 2023-07-01 | 2023-06-28 |  | Late | 2024-06-27 |  | 2024-06-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46102299 | T2 DI SPAULDING-SUMMIT 010/360 RPR GYWW | ICW
LC | 126498461 | 011/368 | T2 DI SPAULDING-SUMMIT 011/368 RPR GYWW | SACTO | ETL.8060.POLE.WOOD | 2023-07-03 | 2023-06-26 | 2023-07-18 | On-time | 2024-06-25 | 343 | 2024-06-26 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45935484 | T2 DI SPAULDING-SUMMIT 011/368 RPR GYWW | ICW
LC | 126465532 | 024/291A | T2 DI DRUM SUMMIT#2 24/291A COTTER | SACTO | ETL.1450.POLE.NWOD | 2023-06-27 | 2023-06-27 | 2023-08-24 | On-time | 2024-06-26 | 307 | 2023-12-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45864952 | T2 DI DRUM SUMMIT#2 24/291A COTTER | ICW
LC | 126495946 | 007/143 | T2 DI HAT CRK#1-WSTWD 07/143 RPR CRSW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-01 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Repair | 46091948 | T2 DI HAT CRK#1-WSTWD 07/143 RPR CRSW | ICW
LC | 126487000 | 018/218C | T2 DI DRUM SUMMIT#1 18/218C RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-30 | 2023-06-27 | 2024-05-16 | On-time | 2024-06-26 | 41 | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098420 | T2 DI DRUM SUMMIT#1 18/218C RPR GYWW | ICW
LC | 126487039 | 018/218A | T2 DI DRUM SUMMIT#1 18/218A RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-30 | 2023-06-27 | 2024-05-17 | On-time | 2024-06-26 | 40 | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098421 | T2 DI DRUM SUMMIT#1 18/218A RPR GYWW | ICW
LC | 126496143 | 015/492 | T2 DI SPLDNG-SMMT 015/492 RPR JUMW | SACTO | ETL.8060.INSL.CERA | 2023-07-01 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Jumper-Wood | Repair | 46102322 | T2 DI SPLDNG-SMMT 015/492 RPR JUMW | ICW
LC | 126496204 | 078/553 | T2 DI BRDGVL-CTNWD-78/553L RPR GYWS | EUREKA | ETL.1110.POLE.STPS | 2023-07-01 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46147378 | T2 DI BRDGVL-CTNWD-78/553L RPR GYWS | ICS
LC | 126496205 | 078/553 | T2 DI BRDGVL-CTNWD-78/553C RPR GYWS | EUREKA | ETL.1110.POLE.STPS | 2023-07-01 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Steel | Repair | 46147375 | T2 DI BRDGVL-CTNWD-78/553C RPR GYWS | ICS
LC | 126488696 | 067/485 | T2 DI BRDGVIL CTTNWD 67/485 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-30 | 2023-06-27 | 2024-01-09 | On-time | 2024-06-26 | 169 | 2023-09-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 45872764 | T2 DI BRDGVIL CTTNWD 67/485 RPR SHLS | ICS
LC | 126490216 | 021/254A | T2 DI DRUM-SUMMIT #1 21/254A RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-30 | 2023-06-27 | 2023-08-09 | On-time | 2024-06-26 | 322 | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45872472 | T2 DI DRUM-SUMMIT #1 21/254A RPR GYWW | ICW
LC | 126490969 | 021/254C | T2 DI DRUM-SUMMIT #1 21/254C RPR GYWW | SACTO | ETL.1440.POLE.NWOD | 2023-06-30 | 2023-06-27 | 2023-08-09 | On-time | 2024-06-26 | 322 | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45872473 | T2 DI DRUM-SUMMIT #1 21/254C RPR GYWW | ICW
LC | 126499628 | 004/006 | T2 CLEAR LAKE-HOPLAND 4/6 RPR POLE | WILLITS | ETL.6390.POLE.WOOD | 2023-07-03 | 2023-06-25 |  | Late | 2024-06-24 |  | 2024-06-25 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46213456 | T2 CLEAR LAKE-HOPLAND 4/6 RPR POLE | ICW
LC | 126500007 | 006/001 | T2 CLEAR LAKE-HOPLAND 6/1 RPL POLE | WILLITS | ETL.6390.POLE.WOOD | 2023-07-03 | 2023-06-26 |  | Late | 2024-06-25 |  | 2024-06-26 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35557047 | T2 CLEAR LAKE-HOPLAND 6/1 RPL POLE | 70Y
LC | 126500920 | 005/132 | T2 DI DEL MONTE-VIEJO 5/132 RMV VEG | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-07-03 | 2023-06-28 |  | Late | 2024-06-27 |  | 2024-06-28 | 564 | TLV |  | E - Schd Compl Yr 0 | Open | TR2 | Overgrown | Vegetation | Remove
LC | 126500982 | ;002/003 | T2 DI CARIBOU#2 ;2/3 RPL POLE | TABLEMTN | ETL.6280.POLE.WOOD | 2023-07-03 | 2023-06-28 |  | Late | 2024-06-27 |  | 2024-06-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527150 | T2 DI CARIBOU #2 ;002/002 RPL POLE | 70Y
LC | 126492455 | 018/222B | T2 DI DRUM-SUMMIT#2 18/222B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-07-01 | 2023-06-27 | 2024-05-16 | On-time | 2024-06-26 | 41 | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098426 | T2 DI DRUM-SUMMIT#2 18/222B RPR GYWW | ICW
LC | 126501008 | 024/284 | T2 DI DRUM-SUMMIT #2 024/284L RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2023-07-03 | 2023-06-28 |  | Late | 2024-06-27 |  | 2024-06-28 | 372 | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527058 | T2 DI DRUM-SUMMIT #2 RPL 2 POLES | 70Y
LC | 126501009 | 024/284 | T2 DI DRUM-SUMMIT #2 024/284 RPR INSW | SACTO | ETL.1450.INSL.CERA | 2023-07-03 | 2023-06-28 |  | Late | 2024-06-27 |  | 2023-12-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46190304 | T2 DI DRUM-SUMMIT #2 024/284 RPR INSW | ICW
LC | 126492967 | 018/222A | T2 DI DRUM-SUMMIT#2 18/222A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-07-01 | 2023-06-27 | 2024-05-16 | On-time | 2024-06-26 | 41 | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098429 | T2 DI DRUM-SUMMIT#2 18/222A RPR GYWW | ICW
LC | 126494367 | 066/481 | T2 DI BRIDGVL-CTNWD 66/481L RPR OPGW | EUREKA | ETL.1110.POLE.STPS | 2023-07-01 | 2023-06-27 | 2024-04-03 | On-time | 2024-06-26 | 84 | 2023-09-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | OPGW - Wood | Repair | 46217269 | T2 DI BRIDGVL-CTNWD 66/481L RPR OPGW | ICW
LC | 126495737 | 008/178 | T2 DI SLNS-LAURELES 008/178 RPR GYWW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-07-01 | 2023-06-27 | 2024-03-25 | On-time | 2024-06-26 | 93 | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46049293 | T2 DI SLNS-LAURELES 008/178 RPR GYWW | ICW
LC | 126496211 | 018/217 | T2 DI DRUM-SUMMIT#2 18/217 COMPLETE | SACTO | ETL.1450.INSL.CERA | 2023-07-01 | 2023-06-27 | 2024-06-24 | On-time | 2024-06-26 | 2 | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46098433 | T2 DI DRUM-SUMMIT#2 18/217 RPR INSW | ICW
LC | 126517030 | 020/242C | T2 DI DRUM-SMMT#1 20/242C RPR STRW | SACTO | ETL.1440.POLE.WOOD | 2023-07-06 | 2023-06-27 | 2024-05-15 | On-time | 2024-06-26 | 42 | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46098471 | T2 DI DRUM-SMMT#1 20/242C RPR STRW | ICW
LC | 126517106 | 020/242B | T2 DI DRUM-SUMMIT #1 020/242B RPR GYWW | SACTO | ETL.1440.POLE.WOOD | 2023-07-06 | 2023-06-27 | 2024-05-15 | On-time | 2024-06-26 | 42 | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098473 | T2 DI DRUM-SUMMIT #1 020/242B RPR GYWW | ICW
LC | 126501279 | 063/460A | T2 DI BRIDGEVL-COTTNWD 63/460A RPR OPGW | EUREKA | ETL.1110.POLE.NWOD | 2023-07-03 | 2023-06-23 |  | Late | 2024-06-22 |  | 2024-06-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | OPGW - Steel | Repair | 45881984 | T2 DI BRIDGEVL-COTTNWD 63/460A RPR OPGW | ICS
LC | 126517270 | 018/217 | T2 DI DRUM-SUMMIT #1 18/217 RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2023-07-06 | 2023-06-27 | 2024-05-17 | On-time | 2024-06-26 | 40 | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098476 | T2 DI DRUM-SUMMIT #1 18/217 RPR GYWW | ICW
LC | 126522467 | 066/479 | T2 DI BRDGVL-CTNWD 66/479 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-07-07 | 2023-06-27 | 2024-04-08 | On-time | 2024-06-26 | 79 | 2024-06-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46171672 | T2 DI BRDGVL-CTNWD 66/479 RPR OPGW | ICS
LC | 126468233 | 005/113 | T2 BURNS-LONE STAR #2 5/113 GO95 CLEAR | MOSSLNDG | ETL.6240.POLE.WOOD | 2023-06-28 | 2023-06-28 | 2024-05-19 | On-time | 2024-06-27 | 39 | 2024-06-28 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654487 | T2 BURNS-LONE STAR #2 5/113 GO95 CLEAR | 93G
LC | 126503392 | 008/003 | T2 EI HMBLDT-MAPLE CRK 08/003R RPL STRW | EUREKA | ETL.7130.POLE.WDPS | 2023-07-05 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508490 | T2 EI HMBLDT-MAPLE CRK 08/003L RPL STRW | 70Y
LC | 126503394 | 008/003 | T2 EI HMBLDT-MAPLE CRK 08/003C RPL STRW | EUREKA | ETL.7130.POLE.WDPS | 2023-07-05 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 372T | TLX | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508490 | T2 EI HMBLDT-MAPLE CRK 08/003L RPL STRW | 70Y
LC | 126468519 | 021/260B | T2 EI DRUM-SUMMIT #2 21/260B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-28 | 2023-06-28 | 2024-06-16 | On-time | 2024-06-27 | 11 | 2024-06-28 | 630 | TLN | CREW | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098391 | T2 EI DRUM-SUMMIT #2 21/260B RPR GYWW | ICW
LC | 126504489 | 028/007 | T2 EI MONTE RIO-FORT ROSS 28/7 RPL POLE | LAKEVLLE | ETL.6979.POLE.WOOD | 2023-07-05 | 2023-05-31 |  | Late | 2024-05-30 |  | 2024-05-31 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35529658 | T2 EI MONTE RIO-FORT ROSS 28/7 RPL POLE | 70Y
LC | 126506938 | 006/145 | T2 DI SLNS-LAURELES 6/145 RPL STRW | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-07-05 | 2023-06-24 |  | Late | 2024-06-23 |  | 2023-12-24 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35563928 | T2 DI SLNS-LAURELES 6/145 RPL STRW | 70Y
LC | 126507148 | 000/027 | T2 DI COLLINS PINE TAP 0/027 RPR POLE | TABLEMTN | ETL.7001.POLE.WOOD | 2023-07-05 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091953 | T2 DI COLLINS PINE TAP 0/027 RPR POLE | ICW
LC | 126508463 | 007/097 | T2 DI VALLEY SPRINGS-CLAY 07/97 RPL STRW | VICTOR | ETL.8264.POLE.WOOD | 2023-07-05 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35524748 | T2 DI VALLEY SPRINGS-CLAY 07/97 RPL STRW | 70Y
LC | 126508898 | 015/501 | T2 DI SPAULDING-SUMMT 15/501 RPR INSW | SACTO | ETL.8060.INSL.NCER | 2023-07-05 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46102324 | T2 DI SPAULDING-SUMMT 15/501 RPR INSW | ICW
LC | 126508930 | 015/501 | T2 DI SPAULDING-SUMMT 15/501 RPL HRDD | SACTO | ETL.8060.POLE.WOOD | 2023-07-05 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46102325 | T2 DI SPAULDING-SUMMT 15/501 RPL HRDD | ICW
LC | 126468572 | 000/004 | T2 LONE STAR TAP 00/04 GO95 | MOSSLNDG | ETL.6231.POLE.WOOD | 2023-06-28 | 2023-06-28 | 2024-01-14 | On-time | 2024-06-27 | 165 | 2024-06-28 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654894 | T2 LONE STAR TAP 00/04 GO95 | 93G
LC | 126468575 | 000/005 | T2 LONE STAR TAP 00/05 GO95 | MOSSLNDG | ETL.6231.POLE.WOOD | 2023-06-28 | 2023-06-28 | 2024-01-14 | On-time | 2024-06-27 | 165 | 2024-06-28 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654894 | T2 LONE STAR TAP 00/04 GO95 | 93G
LC | 126508998 | 007/016 | T2 DI MONTE RIO-FULTON 07/16 RPR SPLW | LAKEVLLE | ETL.7630.INSL.NCER | 2023-07-05 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Repair | 46189841 | T2 DI MONTE RIO-FULTON 07/16 RPR SPLW | ICW
LC | 126468627 | 000/006 | T2 LONE STAR TAP 00/06 GO95 | MOSSLNDG | ETL.6231.POLE.WOOD | 2023-06-28 | 2023-06-28 | 2024-01-14 | On-time | 2024-06-27 | 165 | 2024-06-28 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654894 | T2 LONE STAR TAP 00/04 GO95 | 93G
LC | 126468708 | 021/260C | T2 EI DRUM-SUMMIT #2 21/260C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-06-28 | 2023-06-28 | 2024-06-16 | On-time | 2024-06-27 | 11 | 2024-06-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098392 | T2 EI DRUM-SUMMIT #2 21/260C RPR GYWW | ICW
LC | 126468733 | 004/087 | T2 EI KILARC-DESCHUTES 004/087 RPR POLE | TABLEMTN | ETL.7300.POLE.WOOD | 2023-06-28 | 2023-06-28 | 2024-02-14 | On-time | 2024-06-27 | 134 | 2024-06-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46088613 | T2 EI KILARC-DESCHUTES 004/087 RPR POLE | ICW
LC | 126471260 | 009/093 | T2 EI PIT #5-ROUND MTN #2 009/093 COTTER | TABLEMTN | ETL.5430.INSL.NCER | 2023-06-28 | 2023-06-28 | 2024-06-25 | On-time | 2024-06-27 | 2 | 2024-06-28 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46088429 | T2 EI PIT #5-ROUND MTN #2 009/093 COTTER | ICW
LC | 126509146 | 000/028 | T2 DI COLLINS PN TP 0/28 RPR GYWW | TABLEMTN | ETL.7001.POLE.WOOD | 2023-07-05 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46091954 | T2 DI COLLINS PN TP 0/28 RPR GYWW | ICW
LC | 126473922 | 021/142 | T2 EI HELMS-GREGG #2 021/142 COTTER | FRESNO | ETL.4880.INSL.CERA | 2023-06-28 | 2023-06-28 | 2024-05-22 | On-time | 2024-06-27 | 36 | 2024-06-28 | 628 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46080608 | T2 EI HELMS-GREGG #2 021/142 COTTER | ICS
LC | 126509170 | 000/003B | T2 DI CRUSHER TP 0/3B RPR GYWW | MOSSLNDG | ETL.6241.POLE.WOOD | 2023-07-05 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46081751 | T2 DI CRUSHER TP 0/3B RPR GYWW | ICW
LC | 126474016 | 045/387 | T2 EI RND MT-CTNWD #3 45/387 RPL INSS | TABLEMTN | ETL.5650.INSL | 2023-06-28 | 2023-06-28 | 2024-04-11 | On-time | 2024-06-27 | 77 | 2024-06-28 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35513132 | T2 EI RND MTN-CTTNWD #3 2 TWRS RPL INSS | 93K
LC | 126509182 | 018/591 | T2 DI SPAULDING-SUMMIT 18/591 COTTER | SACTO | ETL.8060.INSL.NCER | 2023-07-05 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46102326 | T2 DI SPAULDING-SUMMIT 018/591 COTTER | ICW
LC | 126474408 | 021/141 | T2 EI HELMS-GREGG #2 021/141 COTTER | FRESNO | ETL.4880.INSL.CERA | 2023-06-28 | 2023-06-28 | 2023-07-28 | On-time | 2024-06-27 | 335 | 2024-06-28 | 628 | TLN | PATR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 45930616 | T2 EI HELMS-GREGG #2 021/141 COTTER | ICS
LC | 126509286 | 013/250 | T2 DI VALLEY SPRINGS #2 013/250 COA | VICTOR | ETL.9460.POLE.WOOD | 2023-07-05 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair
LC | 126509323 | 014/465 | T2 DI SPLDING-SMMT 14/465 RPR INSW | SACTO | ETL.8060.INSL.NCER | 2023-07-05 | 2023-06-24 |  | Late | 2024-06-23 |  | 2024-06-24 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46102327 | T2 DI SPLDING-SMMT 14/465 RPR INSW | ICW
LC | 126489802 | 067/484 | T2 DI BRDGVIL CTTNWD 67/484 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-06-30 | 2023-06-28 | 2024-04-06 | On-time | 2024-06-27 | 82 | 2024-06-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46132881 | T2 DI BRDGVIL CTTNWD 67/484 RPR OPGW | ICS
LC | 126492199 | 010/177 | T2 DI SURF TAP 10/177 RPL INSW | PISMOBCH | ETL.1381.INSL.NCER | 2023-07-01 | 2023-06-28 | 2024-03-16 | On-time | 2024-06-27 | 103 | 2024-06-28 | 508T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35522473 | T2 DI SURF TAP 10/177 RPL INSW | 93I
LC | 126492702 | 011/184 | T2 DI SURF TAP 011/184 RPL DAMW | PISMOBCH | ETL.1381.INSL.NCER | 2023-07-01 | 2023-06-28 | 2024-03-16 | On-time | 2024-06-27 | 103 | 2024-06-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Damper-Wood | Replace | 45895017 | T2 DI SURF TAP 011/184 RPL DAMW | ICW
LC | 126493134 | 002/054-GUY | T2 DI DEL MONTE VIEJO 02/054G RPR GYWW | MOSSLNDG | ETL.6710.POLE.WOOD | 2023-07-01 | 2023-06-28 | 2024-05-09 | On-time | 2024-06-27 | 49 | 2024-06-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46081747 | T2 DI DEL MONTE VIEJO 02/054G RPR GYWW | ICW
LC | 126494471 | 032/176 | T2 DI EXCHQR-INDN FLT 32/176 RPR JUMS | FRESNO | ETL.8650.INSL.NCER | 2023-07-01 | 2023-06-28 | 2023-12-13 | On-time | 2024-06-27 | 197 | 2024-06-28 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Jumper-Steel | Repair | 45954724 | T2 DI EXCHQR-INDN FLT 32/176 RPR JUMS | ICS
LC | 126495546 | 012/139B | T2 DI DRUM-SUMMIT #2 12/139B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-07-01 | 2023-06-28 | 2024-06-17 | On-time | 2024-06-27 | 10 | 2023-12-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098430 | T2 DI DRUM-SUMMIT #2 012/139B RPR GYWW | ICW
LC | 126516824 | 018/593 | T2 DI SPLDING-SUMMIT 18/593 RPR STRT | SACTO | ETL.8060.TOWR | 2023-07-06 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Tower | Repair | 46132845 | T2 DI SPLDING-SUMMIT 18/593 RPR STRT | ICQ
LC | 126516827 | 025/298 | T2 DI DRUM-SUMMIT #2 25/298R RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2023-07-06 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484103 | T2 EI DRUM-SUMMIT #2_010/117C RPL POLE | 70Y
LC | 126516828 | 025/298 | T2 DI DRUM-SUMMIT #2 25/298L RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2023-07-06 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484103 | T2 EI DRUM-SUMMIT #2_010/117C RPL POLE | 70Y
LC | 126516978 | 010/356 | T2 DI SPAULDING-SUMMIT 10/356 RPL SPLW | SACTO | ETL.8060.INSL.NCER | 2023-07-06 | 2023-06-28 |  | Late | 2024-06-27 |  | 2024-06-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Wood | Replace | 46102328 | T2 DI SPAULDING-SUMMIT 10/356 RPL SPLW | ICW
LC | 126517002 | 066/477 | T2 DI BRDGVL-CTNWD 66/477 RPR OPGW | EUREKA | ETL.1110.TOWR | 2023-07-06 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Repair | 46171671 | T2 DI BRDGVL-CTNWD 66/477 RPR OPGW | ICS
LC | 126495654 | 024/286 | T2 DI DRUM-SUMMIT #1 24/286R RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2023-07-01 | 2023-06-28 | 2023-08-07 | On-time | 2024-06-27 | 325 | 2024-06-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45931237 | T2 DI DRUM-SUMMIT #1 24/286R RPR STRW | ICW
LC | 126495731 | 016/513 | T2 DI SPLDNG-SMMT 016/513 RPR ANCW | SACTO | ETL.8060.POLE.WOOD | 2023-07-01 | 2023-06-28 | 2023-08-16 | On-time | 2024-06-27 | 316 | 2023-12-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45886207 | T2 DI SPLDNG-SMMT 016/513 RPR ANCW | ICW
LC | 126495819 | 012/139A | T2 DI DRUM-SUMMIT #2 12/139A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-07-01 | 2023-06-28 | 2024-06-17 | On-time | 2024-06-27 | 10 | 2023-12-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098431 | T2 DI DRUM-SUMMIT #2 012/139A RPR GYWW | ICW
LC | 126517189 | 011/134 | T2 DI DRUM-SUMMIT#1 11/134 RPR INSW | SACTO | ETL.1440.INSL.NCER | 2023-07-06 | 2023-06-28 |  | Late | 2024-06-27 |  | 2024-06-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46098474 | T2 DI DRUM-SUMMIT#1 11/134 RPR INSW | ICW
LC | 126517207 | 023/272 | T2 DI DRUM-SUMMIT #1 023/272L RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2023-07-06 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126517208 | 023/272 | T2 DI DRUM-SUMMIT #1 023/272R RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2023-07-06 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126517230 | 011/134 | T2 DI DRUM-SUMMIT#1 11/134L RPL ANCW | SACTO | ETL.1440.POLE.WDPS | 2023-07-06 | 2023-06-28 |  | Late | 2024-06-27 |  | 2024-06-28 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35484107 | T2 DI DRUM-SUMMIT#1 11/134L RPL ANCW | 93E
LC | 126517231 | 011/134 | T2 DI DRUM-SUMMIT#1 11/134C RPL ANCW | SACTO | ETL.1440.POLE.WDPS | 2023-07-06 | 2023-06-28 |  | Late | 2024-06-27 |  | 2024-06-28 | 637T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 35484107 | T2 DI DRUM-SUMMIT#1 11/134L RPL ANCW | 93E
LC | 126495897 | 012/139C | T2 DI DRUM-SUMMIT #2 12/139C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-07-01 | 2023-06-28 | 2024-06-17 | On-time | 2024-06-27 | 10 | 2023-12-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098432 | T2 DI DRUM-SUMMIT #2 012/139C RPR GYWW | ICW
LC | 126501007 | 024/284 | T2 DI DRUM-SUMMIT #2 24/284R RPL POLE | SACTO | ETL.1450.POLE.WDPS | 2023-07-03 | 2023-06-28 | 2024-06-19 | On-time | 2024-06-27 | 8 | 2024-06-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527058 | T2 DI DRUM-SUMMIT #2 RPL 2 POLES | 70Y
LC | 126501198 | 014/016 | T2 DI CARIBOU-PLMS JCT 14/016 RPL STRW | TABLEMTN | ETL.6290.POLE.WOOD | 2023-07-03 | 2023-06-28 | 2024-05-09 | On-time | 2024-06-27 | 49 | 2024-06-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35518839 | T2 DI CRBOU PLUMAS JT 11/014 RPL POLE | 70Y
LC | 126519482 | 019/614 | T2 DI SPAULDING-SMMT 19/614 RPL ANCW | SACTO | ETL.8060.POLE.WOOD | 2023-07-07 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 637 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Replace | 31655179 | T2 DI SPAULDING-SMMT 19/614 RPL ANCW | 93E
LC | 126519636 | 042/818 | T2 DI HAT CREEK #1-WSTWD 42/818 RPL HRDD | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-07 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46091976 | T2 DI HAT CREEK #1-WSTWD 42/818 RPL HRDD | ICW
LC | 126519674 | 043/829 | T2 DI HAT CREEK #1-WSTWD 43/829 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-07 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514321 | T2 DI HAT CREEK #1-WSTWD 42/810 RPL STRW | 70Y
LC | 126519946 | 006/125 | T2 DI HAT CREEK #1-WESTWD 6/125 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-07 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35513922 | T2 DI HAT CREEK #1-WESTWD 6/125 RPL POLE | 70Y
LC | 126520127 | 027/318 | T2 DI DRUM-SMMT#1 27/318L RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2023-07-07 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46098477 | T2 DI DRUM-SMMT#1 27/318L RPR STRW | ICW
LC | 126520129 | 027/318 | T2 DI DRUM-SMMT#1 27/318C RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2023-07-07 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46098478 | T2 DI DRUM-SMMT#1 27/318C RPR STRW | ICW
LC | 126520214 | 027/318 | T2 DI DRUM-SMMT#1 27/318R RPR GYWW | SACTO | ETL.1440.POLE.WDPS | 2023-07-07 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098479 | T2 DI DRUM-SMMT#1 27/318R RPR GYWW | ICW
LC | 126522465 | 066/479 | T2 DI BRDGVL-CTNWD 66/479 RPL INSS | EUREKA | ETL.1110.INSL.CERA | 2023-07-07 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509119 | T2 DI BRDGVL-CTNWD RPL INSS 6 TWRS | 93K
LC | 126501222 | 001/025 | T2 DI DIVIDE-CBRLL #1 1/25 RPL POLE | PISMOBCH | ETL.1380.POLE.WOOD | 2023-07-03 | 2023-06-28 | 2024-06-17 | On-time | 2024-06-27 | 10 | 2024-06-28 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35511443 | T2 DI DIVIDE-CBRLL #1 1/25 RPL POLE | 70Y
LC | 126523050 | 010/126 | T2 DI DRUM-SUMMIT #1 10/126L RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2023-07-07 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126523052 | 010/126 | T2 DI DRUM-SUMMIT #1 10/126C RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2023-07-07 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126523054 | 010/126 | T2 DI DRUM-SUMMIT #1 10/126R RPL STRW | SACTO | ETL.1440.POLE.WDPS | 2023-07-07 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126524205 | 062/449 | T2 DI BRDGVL-CTNWD 62/449 RPL INSS | EUREKA | ETL.1110.INSL.CERA | 2023-07-07 | 2023-06-27 |  | Late | 2024-06-26 |  | 2024-06-27 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35509119 | T2 DI BRDGVL-CTNWD RPL INSS 6 TWRS | 93K
LC | 126501228 | 033/637 | T2 DI HT CRK#1-WSTWD 33/637 UNBURY | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-03 | 2023-06-28 | 2023-07-26 | On-time | 2024-06-27 | 337 | 2023-12-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45895478 | T2 DI HT CRK#1-WSTWD 33/637 UNBURY | ICW
LC | 126525896 | 024/478 | T2 DI HAT CRK #1-WSTWD 24/478 RPL POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-07 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514120 | T2 DI HAT CRK #1-WSTWOD 23/443 RPL POLE | 70Y
LC | 126526296 | 036/694 | T2 DI HT CRK #1-WSTWD 36/694 RPR STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-07 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091973 | T2 DI HT CRK #1-WSTWD 36/694 RPR STRW | ICW
LC | 126501307 | 019/220 | T2 DI DRUM-SMMT#1 19/220R RPR GYWW | SACTO | ETL.1440.POLE.STPS | 2023-07-03 | 2023-06-28 | 2023-08-05 | On-time | 2024-06-27 | 327 | 2023-12-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45872475 | T2 DI DRUM-SMMT#1 19/220R RPR GYWW | ICW
LC | 126526779 | 017/555 | T2 DI SPAULDING-SUMMIT 17/555 RPL STRW | SACTO | ETL.8060.POLE.WOOD | 2023-07-07 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35508793 | T2 EI SPAULDING-SUMMIT 17/531 RPL PL | 70Y
LC | 126501308 | 019/220 | T2 DI DRUM-SMMT#1 19/220L RPR GYWW | SACTO | ETL.1440.POLE.STPS | 2023-07-03 | 2023-06-28 | 2023-08-05 | On-time | 2024-06-27 | 327 | 2023-12-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45872476 | T2 DI DRUM-SMMT#1 19/220L RPR GYWW | ICW
LC | 126508987 | 023/281 | T2NT DI DRUM-SUMMIT #2 23/281 RPL HRDD | SACTO | ETL.1450.POLE.STPS | 2023-07-05 | 2023-06-28 | 2024-06-20 | On-time | 2024-06-27 | 7 | 2024-06-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46098462 | T2NT DI DRUM-SUMMIT #2 23/281 RPL HRDD | ICW
LC | 126527997 | 034/663 | T2 DI HT CRK #1-WSTWD 34/663 RPR GRWW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-08 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Ground Wire-Wood | Repair | 46091971 | T2 DI HT CRK #1-WSTWD 34/663 RPR GRWW | ICW
LC | 126528191 | 010/200 | T2 DI HAT CRK #1-WESTWD 10/200 RPL STRW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-08 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35513923 | T2 DI HAT CRK #1-WESTWD 10/200 RPL STRW | 70Y
LC | 126528393 | 010/121 | T2 DI DRM-SMMT #1 10/121R RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2023-07-08 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46098509 | T2 DI DRUM-SUMMIT #1 10/121 RPR STRW | ICW
LC | 126509063 | 021/410 | T2 DI HAT CREEK #1-WESTWD 21/410 REFRAME | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-05 | 2023-06-28 | 2024-06-19 | On-time | 2024-06-27 | 8 | 2024-06-28 | 637T | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Crossarm-Wood | Replace | 35514002 | T2 EI HAT CRK #1-WESTWD 20/400 REFRAME | 93E
LC | 126529036 | 025/303 | T2 DI DRUM-SUMMIT #1 25/303R COA | SACTO | ETL.1440.POLE.WDPS | 2023-07-08 | 2023-06-28 | 2024-06-23 | On-time | 2024-06-27 | 4 | 2024-06-28 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46098512 | T2 DI DRUM-SUMMIT #1 25/303R RPR STRW | ICW
LC | 126529415 | 053/1024 | T2 DI HAT CRK #1-WESTWD 53/1024 RPR ANCW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-08 | 2023-06-20 |  | Late | 2024-06-19 |  | 2024-06-20 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46091889 | T2 DI HAT CRK #1-WESTWD 53/1024 RPR ANCW | ICW
LC | 126587456 | 004/080 | T2 COLEMAN-RD BLFF 4/80 RPL POLE | TABLEMTN | ETL.6440.POLE.WOOD | 2023-07-14 | 2023-06-28 | 2024-03-14 | On-time | 2024-06-27 | 105 | 2024-06-28 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35500379 | T2 COLEMAN-RD BLFF 4/80 RPL POLE | 70Y
LC | 126475177 | 041/010 | T2 ELK-GUALALA 41/10 RPR INSW | WILLITS | ETL.8410.INSL.NCER | 2023-06-29 | 2023-06-29 | 2023-08-31 | On-time | 2024-06-28 | 302 | 2023-09-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 45902133 | T2 ELK-GUALALA 41/10 RPR INSW | ICW
LC | 126475326 | 016/322 | T2 COLGATE-PALERMO 16/322 RPR INSW | SACTO | ETL.6500.INSL.CERA | 2023-06-29 | 2023-06-29 | 2024-04-27 | On-time | 2024-06-28 | 62 | 2024-06-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46125123 | T2 COLGATE-PALERMO 16/322 RPR INSW | ICW
LC | 126536265 | 040/766 | T2 DI HT CRK #1-WSTWD 40/766 RPR ANCW | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-09 | 2023-06-30 |  | Late | 2024-06-29 |  | 2024-06-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 46091975 | T2 DI HT CRK #1-WSTWD 40/766 RPR ANCW | ICW
LC | 126536743 | 012/223 | T2 DI VALLEY SPRINGS #2 12/223 RPL POLE | VICTOR | ETL.9460.POLE.WOOD | 2023-07-09 | 2023-06-29 |  | Late | 2024-06-28 |  | 2024-06-29 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35524745 | T2 DI VALLEY SPRINGS #2 12/223 RPL POLE | 70Y
LC | 126476421 | 001/052 | T2 EI HMLTN BRNCH-CHSTR 1/52 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-29 | 2023-06-29 | 2023-10-04 | On-time | 2024-06-28 | 268 | 2024-06-29 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31663258 | T2 EI HMLTN BRNCH-CHSTR 1/52 RPL STRW | 70Y
LC | 126476886 | 001/046 | T2 EI HMLTN BRNCH-CHSTR 1/46 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-29 | 2023-06-29 | 2023-10-04 | On-time | 2024-06-28 | 268 | 2024-06-29 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31663257 | T2 EI HMLTN BRNCH-CHSTR 1/46 RPL STRW | 70Y
LC | 126477062 | 000/003 | T2 EI CRYSTAL SPRINGS TAP 0/3 RPR HRDW | METCALF | ETL.7211.POLE.WOOD | 2023-06-29 | 2023-06-29 | 2024-04-08 | On-time | 2024-06-28 | 81 | 2024-06-29 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46062380 | T2 EI CRYSTAL SPRINGS TAP 0/3 RPR HRDW | ICW
LC | 126477604 | 001/040 | T2 EI HMLTN BRNCH-CHSTR 1/40 RPR ANCW | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-29 | 2023-06-29 | 2023-08-10 | On-time | 2024-06-28 | 323 | 2023-12-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45870616 | T2 EI HMLTN BRNCH-CHSTR 1/40 RPR ANCW | ICW
LC | 126477987 | 001/043 | T2 EI HMLTN BRNCH-CHSTR 1/43 RPL STRW | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-29 | 2023-06-29 | 2023-10-04 | On-time | 2024-06-28 | 268 | 2024-06-29 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31663256 | T2 EI HMLTN BRNCH-CHSTR 1/43 RPL STRW | 70Y
LC | 126605399 | 044/005 | T2 DI ELK-GUALALA 44/5C RPL POLE | WILLITS | ETL.8410.POLE.WDPS | 2023-07-17 | 2023-04-06 | 2024-04-28 | Late | 2024-04-05 | -23 | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487275 | T2 DI ELK-GUALALA 44/5L RPL POLE | 70Y
LC | 126605464 | 044/005 | T2 DI ELK-GUALALA 44/5R RPL POLE | WILLITS | ETL.8410.POLE.WDPS | 2023-07-17 | 2023-04-06 | 2024-04-25 | Late | 2024-04-05 | -20 | 2024-04-06 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35487275 | T2 DI ELK-GUALALA 44/5L RPL POLE | 70Y
LC | 126666524 | 000/006 | T2 SMRTVLL-NICLAUS #2 00/06 RPR STRW | SACTO | ETL.8000.POLE.WOOD | 2023-07-25 | 2023-07-01 |  | Late | 2024-06-30 |  | 2024-07-01 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46127543 | T2 SMRTVLL-NICLAUS #2 00/06 RPR STRW | ICW
LC | 126772456 | 003/001 | T2 CLEAR LAKE-HOPLAND 3/001 RPL STRW | WILLITS | ETL.6390.POLE.WOOD | 2023-08-08 | 2023-04-26 |  | Late | 2024-04-25 |  | 2024-04-26 | 372T | TLX | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35529424 | T2 CLEAR LAKE-HOPLAND 3/001 RPL STRW | 70Y
LC | 126875529 | 028/171 | T2NT TMBLR-SN LIS OBISP 28/171 RPL SPLS | PISMOBCH | ETL.3960.INSL.NCER | 2023-08-21 | 2023-03-23 |  | Late | 2024-03-22 |  | 2024-03-23 | 628 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Splice-Steel | Replace | 46170943 | T2NT TMBLR-SN LIS OBISP 28/171 RPL SPLS | ICS
LC | 126478477 | 001/037 | T2 EI HMLTN BRNCH-CHSTR 1/40 RPR POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-29 | 2023-06-29 | 2023-10-03 | On-time | 2024-06-28 | 269 | 2024-06-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 45937196 | T2 EI HMLTN BRNCH-CHSTR 1/40 RPR POLE | ICW
LC | 126478936 | 007/067A | T2 EI PARADISE-TABLE MTN 7/67A RPR INSW | TABLEMTN | ETL.4316.INSL.CERA | 2023-06-29 | 2023-06-29 | 2024-01-30 | On-time | 2024-06-28 | 150 | 2024-06-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Wood | Repair | 46093343 | T2 EI PARADISE-TABLE MTN 7/67A RPR INSW | ICW
LC | 126480948 | 008/063A | T2 EI HELMS-GREGG #1 008/063A RPR SHIELD | FRESNO | ETL.4870.TOWR | 2023-06-29 | 2023-06-29 | 2024-05-15 | On-time | 2024-06-28 | 44 | 2024-06-29 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Wood | Replace | 46080609 | T2 EI HELMS-GREGG #1 008/063A RPR SHIELD | ICW
LC | 126501268 | 011/135B | T2 DI DRUM-SUMMIT #2 11/135B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-07-03 | 2023-06-29 | 2024-06-17 | On-time | 2024-06-28 | 11 | 2023-09-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098437 | T2 DI DRUM-SUMMIT #2 011/135B RPR GYWW | ICW
LC | 126501383 | 011/135C | T2 DI DRUM-SUMMIT #2 11/135C RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-07-03 | 2023-06-29 | 2024-06-17 | On-time | 2024-06-28 | 11 | 2023-12-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098438 | T2 DI DRUM-SUMMIT #2 011/135C RPR GYWW | ICW
LC | 126509022 | 024/287B | T2 DI DRM-SUMMIT #2 24/287B RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-07-05 | 2023-06-29 | 2024-06-20 | On-time | 2024-06-28 | 8 | 2024-06-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098463 | T2 DI DRM-SUMMIT #2 24/287B RPR GYWW | ICW
LC | 126509070 | 027/327 | T2 DI DRUM-SUMMIT#2 27/327C RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2023-07-05 | 2023-06-29 | 2024-06-20 | On-time | 2024-06-28 | 8 | 2024-06-29 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527058 | T2 DI DRUM-SUMMIT #2 RPL 2 POLES | 70Y
LC | 126509072 | 027/327 | T2 DI DRUM-SUMMIT #2 27/327R RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2023-07-05 | 2023-06-29 | 2024-06-20 | On-time | 2024-06-28 | 8 | 2024-06-29 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527058 | T2 DI DRUM-SUMMIT #2 RPL 2 POLES | 70Y
LC | 126509074 | 027/327 | T2 DI DRUM-SUMMIT #2 27/327L RPL STRW | SACTO | ETL.1450.POLE.WDPS | 2023-07-05 | 2023-06-29 | 2024-06-20 | On-time | 2024-06-28 | 8 | 2024-06-29 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35527058 | T2 DI DRUM-SUMMIT #2 RPL 2 POLES | 70Y
LC | 126516755 | 021/260A | T2 DI DRUM-SUMMIT #2 21/260A RPR GYWW | SACTO | ETL.1450.POLE.NWOD | 2023-07-06 | 2023-06-29 | 2024-06-16 | On-time | 2024-06-28 | 12 | 2024-06-29 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098469 | T2 DI DRUM-SUMMIT #2 21/260A RPR GYWW | ICW
LC | 126517069 | 019/495 | T2 DI CARIBOU #2 019/495 RMV VEG | TABLEMTN | ETL.6280.POLE.NWOD | 2023-07-06 | 2023-06-29 | 2024-03-20 | On-time | 2024-06-28 | 100 | 2024-06-29 | 564 | TLV |  | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Remove
LC | 126485038 | 001/015 | T2 EI SBRNT-GRZLY-CLRMNT #2 1/15 RMV VEG | CONCORD | ETL.3750.TOWR | 2023-06-30 | 2023-06-30 | 2024-02-26 | On-time | 2024-06-29 | 124 | 2024-06-30 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation-Tower | Cage Clearing
LC | 126487137 | 000/023 | T2 EI HAMILTON BRNCH-CHSTR 0/23 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-06-30 | 2023-06-30 | 2023-10-04 | On-time | 2024-06-29 | 269 | 2024-06-30 | 372 | TLX | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 31663253 | T2 EI HAMILTON BRNCH-CHSTR 0/23 RPL POLE | 70Y
LC | 126487323 | 000/024 | T2 EI HAMILTON BRNCH-CHSTR 0/24 RPR SPLW | TABLEMTN | ETL.7000.INSL.NCER | 2023-06-30 | 2023-06-30 | 2023-10-02 | On-time | 2024-06-29 | 271 | 2024-06-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Missing | Damper-Wood | Install | 45937193 | T2 EI HAMILTON BRNCH-CHSTR 0/24 RPR SPLW | ICW
LC | 126487449 | 000/025 | T2 EI HAMILTON BRANCH-CHSTR 0/25 COTTER | TABLEMTN | ETL.7000.POLE.NWOD | 2023-06-30 | 2023-06-30 | 2023-09-28 | On-time | 2024-06-29 | 275 | 2024-06-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 45937194 | T2 EI HAMILTON BRANCH-CHSTR 0/25 COTTER | ICW
LC | 126487670 | 000/025 | T2 EI HAMILTON BRNCH-CHSTR 0/25 RPR ANCW | TABLEMTN | ETL.7000.POLE.NWOD | 2023-06-30 | 2023-06-30 | 2023-09-28 | On-time | 2024-06-29 | 275 | 2024-06-30 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Anchor-Wood | Repair | 45937195 | T2 EI HAMILTON BRNCH-CHSTR 0/25 RPR ANCW | ICW
LC | 126489097 | 023/001 | T2 EI MNDCN-WILITS-FRT BRG 23/01 RMV VEG | WILLITS | ETL.7550.POLE.WOOD | 2023-06-30 | 2023-06-30 | 2023-07-31 | On-time | 2024-06-29 | 334 | 2023-09-30 | 564 | TLV | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Overgrown | Vegetation | Trim
LC | 126516647 | 010/121C | T2 DI DRUM-SMMT #2 10/121C COTTER | SACTO | ETL.1450.POLE.NWOD | 2023-07-06 | 2023-06-30 | 2024-05-23 | On-time | 2024-06-29 | 37 | 2024-06-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098468 | T2 DI DRUM-SMMT #2 10/121C COTTER | ICW
LC | 126517280 | 012/242 | T2 DI HAT CRK #1-WSTWD 12/242 RPL HRDD | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-06 | 2023-06-30 | 2024-06-13 | On-time | 2024-06-29 | 16 | 2024-06-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46091968 | T2 DI HAT CRK #1-WSTWD 12/242 RPL HRDD | ICW
LC | 126517369 | 031/602 | T2 DI HT CRK #1-WSTWD 31/602 RPR POLE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-06 | 2023-06-30 | 2024-06-19 | On-time | 2024-06-29 | 10 | 2024-06-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46091970 | T2 DI HT CRK #1-WSTWD 31/602 RPR POLE | ICW
LC | 126524324 | 013/095B | T2 DI HELMS-GRGG #2 13/95B RPR INSS | FRESNO | ETL.4880.INSL.CERA | 2023-07-07 | 2023-06-30 | 2024-05-21 | On-time | 2024-06-29 | 39 | 2024-06-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Repair | 46080610 | T2 DI HELMS-GRGG #2 13/95B RPR INSS | ICS
LC | 126526688 | 033/643 | T2 DI HT CRK #1-WSTWD 33/643 RPL HRDD | TABLEMTN | ETL.7030.POLE.NWOD | 2023-07-07 | 2023-06-30 | 2024-06-18 | On-time | 2024-06-29 | 11 | 2024-06-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46267996 | T2 DI HT CRK #1-WSTWD 33/643 RPL HRDD | ICW
LC | 126527831 | 031/600 | T2 DI HT CRK #1-WSTWD 31/600 COMPLETE | TABLEMTN | ETL.7030.POLE.WOOD | 2023-07-08 | 2023-06-30 | 2024-06-24 | On-time | 2024-06-29 | 5 | 2024-06-30 | 372T | TLX |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35514138 | T2 EI HAT CREEK #1-WESTWD 31/597 RPL PL | 70Y
LC | 126527903 | 010/077B | T2 DI HELMS-GREGG #2 010/077B RPL SHLS | FRESNO | ETL.4880.TOWR | 2023-07-08 | 2023-06-30 | 2024-05-21 | On-time | 2024-06-29 | 39 | 2024-06-30 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire / OPGW-Steel | Replace | 46080611 | T2 DI HELMS-GREGG #2 010/077B RPL SHLS | ICS
LC | 127033915 | 014/098 | T2 DI IGNCO ALTO SUSTO #1 14/98 RPL INSS | LAKEVLLE | ETL.7160.INSL.CERA | 2023-09-11 | 2023-03-06 |  | Late | 2024-03-05 |  | 2024-03-06 | 532 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 31677491 | DI IGNCO ALTO SUSLTO#2 14/98 RPL INSS | 93K
LC | 127126913 | 010/145 | T2 DI DLTA-MT GT JCT 10/145 RPL POLE | TABLEMTN | ETL.6750.POLE.WDPS | 2023-09-25 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491299 | T2 DI DLTA-MTN GATE 10/142 RPL POLE | 70Y
LC | 127126982 | 010/142 | T2 DI DLTA-MTN GATE 10/142 RPL POLE | TABLEMTN | ETL.6750.POLE.WDPS | 2023-09-25 | 2023-03-21 |  | Late | 2024-03-20 |  | 2024-03-21 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35491299 | T2 DI DLTA-MTN GATE 10/142 RPL POLE | 70Y
LC | 126528788 | 024/288 | T2 DI DRUM-SUMMIT #2 24/288 RPR GYWW | SACTO | ETL.1450.POLE.STPS | 2023-07-08 | 2023-06-30 | 2024-06-20 | On-time | 2024-06-29 | 9 | 2023-12-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46098511 | T2 DI DRUM-SUMMIT #2 24/288 RPR GYWW | ICW
LC | 127250234 | 009/221 | T2 EI COTTNWD-BNTON #1 9/221 RPL INSW | TABLEMTN | ETL.6640.INSL | 2023-10-11 | 2023-03-08 |  | Late | 2024-03-07 |  | 2024-03-08 | 508T | TLN | INSP | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Wood | Replace | 35495865 | T2 EI COTTNWD-BNTON #1 9/221 RPL INSW | 93I
LC | 127294481 | IG002/010 | T2 LAKEVILLE-IGNACIO #1 IG2/10 RPR CRSS | LAKEVLLE | ETL.4940.POLE.NWOD | 2023-10-17 | 2023-06-01 |  | Late | 2024-05-31 |  | 2023-12-01 | 628 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Crossarm-Steel | Repair | 46059536 | T2 LAKEVILLE-IGNACIO #1 IG2/10 RPR CRSL | ICS
LC | 127334201 | 003/040 | T2 DI PIT#5-RND MT#1 3/40L RPL STRW | TABLEMTN | ETL.5420.POLE.WDPS | 2023-10-24 | 2023-06-07 |  | Late | 2024-06-06 |  | 2024-06-07 | 372 | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35526327 | T2 DI PIT#5-RND MT#1 RPL 4 STRW | 70Y
LC | 127422509 | 068/342 | T2 EI MALIN-ROUND MTN #2 68/342 RPR GYWT | TABLEMTN | ETL.6020.TOWR | 2023-11-06 | 2023-06-14 |  | Late | 2024-06-13 |  | 2024-06-14 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46095413 | T2 EI MALIN-ROUND MTN #2 68/342 RPR GYWT | ICQ
LC | 127422894 | 071/361 | T2 EI MALIN-ROUND MTN #2 71/361 RPR GYWT | TABLEMTN | ETL.6020.TOWR | 2023-11-06 | 2023-06-12 |  | Late | 2024-06-11 |  | 2024-06-12 | 543 | TLQ |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Guy Wire-Tower | Repair | 46095414 | T2 EI MALIN-ROUND MTN #2 71/361 RPR GYWT | ICQ
LC | 126529835 | 024/291 | T2 DI DRUM-SUMMIT #1 24/291L RPR STRW | SACTO | ETL.1440.POLE.WDPS | 2023-07-08 | 2023-06-30 | 2024-06-23 | On-time | 2024-06-29 | 6 | 2024-06-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46098513 | T2 DI DRUM-SUMMIT #1 024/291L RPR STRW | ICW
LC | 127578532 | 013/003 | T2 EI FORT BRAGG-ELK 13/3 GO95 | WILLITS | ETL.2060.POLE.WOOD | 2023-12-14 | 2023-04-06 | 2024-04-09 | Late | 2024-04-05 | -4 | 2024-04-06 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35525614 | T2 EI FORT BRAGG-ELK 13/3 GO95 | 93G
LC | 127578677 | 022/010 | T2 EI FORT BRAGG-ELK 022/010 GO95 | WILLITS | ETL.2060.POLE.WOOD | 2023-12-14 | 2023-03-25 | 2024-04-19 | Late | 2024-03-24 | -26 | 2024-03-25 | 401T | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35525615 | T2 EI FORT BRAGG-ELK 022/010 GO95 | 93G
LC | 128035136 | 028/202C | T2 EI CARIBOU-TABLE MTN 28/202C RPL INSS | TABLEMTN | ETL.4440.INSL.NCER | 2024-01-12 | 2023-06-03 | 2024-06-06 | Late | 2024-06-02 | -4 | 2024-06-03 | 532 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35508877 | T2 EI CARIBOU-TABLE MTN RPL INSS 12 STRT | 93K
LC | 128079580 | 009/107 | T2 DRUM-SUMMIT #1 9/107R RPL POLE | SACTO | ETL.1440.POLE.WDPS | 2024-01-24 | 2023-06-05 |  | Late | 2024-06-04 |  | 2024-06-05 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35484106 | T2 DI DRUM-SUMMIT #1 RPL 11 POLE | 70Y
LC | 126531061 | A015/317 | T2 DI SALINAS-LRLS-LRLS A15/317 RPR POLE | MOSSLNDG | ETL.7930.POLE.WOOD | 2023-07-08 | 2023-06-30 | 2024-05-01 | On-time | 2024-06-29 | 59 | 2024-06-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46081668 | T2 DI SALINAS-LRLS-LRLS A15/317 RPR POLE | ICW
LC | 126536193 | 024/290A | T2 DI DRM-SMMT #1 24/290A RPL HRDW | SACTO | ETL.1440.POLE.NWOD | 2023-07-09 | 2023-06-30 | 2024-06-23 | On-time | 2024-06-29 | 6 | 2024-06-30 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46098517 | T2 DI DRM-SMMT #1 24/290A RPL HRDW | ICW
LC | 128130491 | 009/064 | T2 MORAGA-SAN LEANDRO #1 09/064 RPL INSS | CONCORD | ETL.2770.INSL | 2024-02-05 | 2023-03-29 |  | Late | 2024-03-28 |  | 2024-03-29 | 532T | TLN |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Insulator-Steel | Replace | 35533582 | T2 MORAGA-SAN LEANDRO #1 09/064 RPL INSS | 93K
LC | 126560771 | 001/033 | T2 EI HAMILTON BRNCH-CHSTR 1/33 RPL POLE | TABLEMTN | ETL.7000.POLE.WOOD | 2023-07-11 | 2023-06-30 | 2023-10-04 | On-time | 2024-06-29 | 269 | 2024-06-30 | 372 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | Rotten | Structure-Wood | Replace | 31663254 | T2 EI HAMILTON BRNCH-CHSTR 1/33 RPL POLE | 70Y
LC | 128305423 | 007/077 | T2 IGNACIO-BOLINAS #1 7/077 GO95 | LAKEVLLE | ETL.7140.POLE.WOOD | 2024-03-19 | 2023-04-18 |  | Late | 2024-04-17 |  | 2024-04-18 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 35524492 | IGNACIO-BOLINAS #1 7/78 GO95 WIR | 93G
LC | 128350794 | 025/178 | T2 EI TRINITY-COTTONWD 25/178R RPR GYWW | TABLEMTN | ETL.4040.POLE.STPS | 2024-03-22 | 2023-04-15 | 2024-06-24 | Late | 2024-04-14 | -71 | 2023-10-15 | 630 | TLN | INSP | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46227557 | T2 EI TRINITY-COTTONWD 25/178R RPR GYWW | ICW
LC | 128379338 | 028/007 | T2 RIO DLL JCT-BRGVLE 28/7 GO95 CLEAR | EUREKA | ETL.7850.POLE.WOOD | 2024-03-27 | 2023-05-30 |  | Late | 2024-05-29 |  | 2024-05-30 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31651701 | T2 RIO DELL JCT-BRIDGEVILLE 28/6 GO95 | 93G
LC | 128418710 | 007/001 | T2 FORT BRAGG-ELK 07/01L RPL HRDD | WILLITS | ETL.2060.POLE.WDPS | 2024-04-02 | 2023-04-14 |  | Late | 2024-04-13 |  | 2024-04-14 | 630 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Hardware-Wood | Replace | 46236305 | T2 FORT BRAGG-ELK 07/01L RPL HRDD | ICW
LC | 128549525 | 006/001 | T2 HUMBOLDT-MAPLE CREEK 6/001R GO95 | EUREKA | ETL.7130.POLE.WDPS | 2024-04-16 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654782 | T2 HUMBOLDT-MAPLE CREEK 6/001 GO95 | 93G
LC | 128549528 | 006/001 | T2 HUMBOLDT-MAPLE CREEK 6/001C GO95 | EUREKA | ETL.7130.POLE.WDPS | 2024-04-16 | 2023-06-10 |  | Late | 2024-06-09 |  | 2024-06-10 | 401 | TLN | OTHR | E - Schd Compl Yr 0 | Open | TR2 | Clearance | GO95 Clear Infract-Wood | To Be Corrected | 31654782 | T2 HUMBOLDT-MAPLE CREEK 6/001 GO95 | 93G
LC | 128655114 | 050/250 | T2 DI MLN-RD MNTN #2 50/250 RPR SHIELD | TABLEMTN | ETL.6020.TOWR | 2024-04-25 | 2023-05-02 | 2024-05-09 | Late | 2024-05-01 | -8 | 2024-05-02 | 628 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Shield Wire - Steel | Repair | 46236158 | T2 DI MLN-RD MNTN #2 50/250 RPR SHIELD | ICS
LC | 128840651 | 011/128 | T2 DI DRUM-SUMMIT #2 11/128R RPR GYWW | SACTO | ETL.1450.POLE.STPS | 2024-05-22 | 2023-06-14 | 2024-06-17 | Late | 2024-06-13 | -4 | 2024-06-14 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Guy Wire-Wood | Repair | 46253257 | T2 DI DRUM-SUMMIT #2 11/128R RPR GYWW | ICW
LC | 128842820 | 042/338C | T2 DI BRDGVLL-CTTNWD 42/338C RPR STRW | TABLEMTN | ETL.1110.POLE.NWOD | 2024-05-23 | 2023-05-17 | 2024-06-07 | Late | 2024-05-16 | -22 | 2024-05-17 | 630 | TLN |  | E - Schd Compl Yr 0 | Closed | TR2 | No Good/Out of Stdrd | Structure-Wood | Repair | 46253258 | T2 DI BRDGVLL-CTTNWD 42/338C RPR STRW | ICW
LC | 129116525 | 042/335 | T2 DI BRDGVLL-CTTNWD 42/335L RPL POLE | TABLEMTN | ETL.1110.POLE.WDPS | 2024-06-24 | 2023-05-17 |  | Late | 2024-05-16 |  | 2024-05-17 | 372T | TLX |  | E - Schd Compl Yr 0 | Open | TR2 | No Good/Out of Stdrd | Structure-Wood | Replace | 35562831 | T2 DI BRDGVLL-CTTNWD 42/335R RPL POLE | 70Y

## Time
| TR3 | TR2
2024-01-01 | 2023-07-04 | 2023-01-01
2024-06-30 | 2024-01-01 | 2023-07-01