## SB 1174 Reporting Instructions
SB 1174 Reporting
INSTRUCTIONS
*IMPORTANT* All fields, except "Notes", are mandatory. Returned data with blank fields will be considered incomplete. The Input Format described below must be followed for each field, i.e. date fields must have dates entered. Tab sections in black text refer to transmission projects, tab sections in red text refer to generation projects.
Pursuant to SB 1174 (Hertzberg, Stat. 2022, Ch. 229) and Pub. Util. Code § 399.13(a)(2)(B), electrical corporations that own transmission facilities are required to provide information within their RPS Procurement Plans detailing the impact that delays to transmission facilities and network system upgrades have had on renewable energy and energy storage resources with executed interconnection agreements. Electrical corporations should use this template to report the related data and include data on all projects currently in development, regardless of if it has been delayed or not. Electrical corporations shall list each of their transmission facility and system network upgrades that are currently in development, in the “Transmission Project Name” column/field on the “1. Transmission Delay Reporting” tab. For each project listed in the “Transmission Project Name” column/field on the “1. Transmission Delay Reporting” tab, fill in the corresponding data fields for the project. Fill in all construction and inservice dates for all projects regardless of if the project has been delayed or not. For each transmission facility and system network upgrade project, list every renewable energy and energy storage resource that depends on the project's completion in section 4: "GENERATION RESOURCE DEPENDENCIES". Additionally, electrical corporations are to fill in the "2. Generation Reporting" tab and list every renewable energy and energy storage resource (with executed interconnection agreements) currently in the CAISO, WDAT, or other interconnection queues. For each resource make sure to list every transmission facility and system network upgrade project that it depends on in section 3: "CONNECTING TRANSMISSION PROJECTS".
"1. Transmission Delay Reporting" TAB
Section 1: TRANSMISSION PROJECT DETAILS
Field # | Project Data Field | Input Format | Input Example | Input Description
1 | Transmission Project Name | Text string. | Manzanita Substation | Project's name at the date of filing this report and this is currently in development. Identify all prior project names and alternative names currently used in different venues, including the name as approved and included in the CAISO's TPP.
2 | Transmission Project Unique ID | Text string. | 78493 | Unique identification (ID) code(s) or number(s) for transmission project. List most specific (PG&E = Planning Order, SCE = SCE ID, SDG&E = Project ID).
3 | Description | Text string. | Project will repair the transmission line connecting 4th and Townsend to the East Northfork station which failed as a consequence of the 2019 San Clemente Hedge Fire. | Brief project summary, including assets to be installed.
4 | Status | Drop-down menu selection. | Construction (10%-25%) | See drop-down menu. Indicate the status of the project.
5 | Action Taken | Drop-down menu selection. | Upgrade/Retrofit | See drop-down menu. If two or more options are required, select "Multiple Options" and provide remaining responses, pipe-delimited, in "Notes" data field. If the purpose or purpose details relates to complying with a NERC, WECC, or CAISO requirement, list specific standard(s), requirement(s), and/or any contingencies that are being addressed.
6 | Purpose | Drop-down menu selection. | Reliability | See drop-down menu. In the "Notes" data field, please explain a purpose identified as "Other" or provide additional details on the purpose identified.
7 | Purpose Details | Drop-down menu selection. | Age/Condition - Anti Climb Guards | See drop-down menu. If the purpose details is to comply with a NERC, WECC, or CAISO requirement, list the standard, requirement, and/or any contingencies that are being addressed in the "Notes" data field.
Section 2: TRANSMISSION PROJECT VARIANCES
Field # | Project Data Field | Input Format | Input Example | Input Description
8 | Original Construction Start Date | Date, formatted YYYY-MM-DD. | 2025-07-30 | The expected construction start date when the project was first approved.
9 | Current Planned or Actual Construction Start Date | Date, formatted YYYY-MM-DD. | 2024-12-15 | At the time the data was extracted from the utility’s database(s) as provided in Section 2.1.5 of the Transmission Project Review Process Description. If the project has not been delayed, the original and current construction dates should match.
10 | Construction Start Date Change Initiator | Drop-down menu selection. | Utility | See drop-down menu. Select the party that initiated the change from the original construction start date. The initiator is the party closest to the source of the delay. Select N/A only if the project is NOT delayed.
11 | Construction Start Date Change Reason | Drop-down menu selection. | Land Rights | See drop-down menu. Select the reason for the change from the original construction start date. Select N/A only if the project is NOT delayed.
12 | Original In-service Date | Date, formatted YYYY-MM-DD. | 2025-06-01 | The expected in-service start date when the project was first approved.
13 | Current Planned or Actual In-service Date | Date, formatted YYYY-MM-DD. | 2021-01-01 | At the time the data was extracted from the utility’s database(s) as provided in Section 2.1.5 of the Transmission Project Review Process Description. If the project has not been delayed, the original and current in-service dates should match.
14 | In-service Date Change Initiator | Drop-down menu selection. | Customer | See drop-down menu. Select the party that initiated the change from the original in-service date. The initiator is the party closest to the source of the delay. Select N/A only if the project is NOT delayed.
15 | In-service Date Change Reason | Drop-down menu selection. | Financing | See drop-down menu. Select the reason for the change from the original in-service date. Select N/A only if the project is NOT delayed.
Section 3: TRANSMISSION PROJECT NOTES
Field # | Project Data Field | Input Format | Input Example | Input Description
16 | Notes | Text strings, inclusive of field identifiers in brackets, separated by line break. | [4. Status] PPA negotiation failure. [6. Purpose] Experimental breaker testing. | For all fields in which an option including "[See Notes]" was selected, please enter a description or explanation here.
Section 4: GENERATION RESOURCE DEPENDENCIES
Field # | Project Data Field | Input Format | Input Example | Input Description
17+ | Dependent In-Queue Generation Resource (CAISO and WDAT) | Text string. | 0002CONV | CAISO and WDAT queue numbers. Identify all generation resources (with executed interconnection agreements) that are operationally dependent on this project. List all queue position #s both CAISO and WDAT generation projects. Types of queue position labels include, but are not limited to: - ##, or, if two queues have combined then the queue number will reflect ##,##. - ####CONV is a two-to-three party contract conversion or is a conversion project repowering with new generation. - ####PREC, that is an existing two-party generating facility that has yet to complete a contract conversion. - #### for generation resources that are dynamic or pseudo-ties (projects in a balancing authority area other than the CAISO but are treated as Participating Generators under the CAISO Tariff). If the generation resource is connecting to a PTO's distribution system then Queue numbers can include "W", "WDT", "WD", "GFID", "RD" or "Rule 21". Submitter may add additional columns for additional generation projects as necessary.
"2. Generation Reporting" TAB
Section 1: GENERATION RESOURCES DETAILS
Field # | Project Data Field | Input Format | Input Example | Input Description
1 | Generation Facility Name | Text string. | Sierra Solar Farm Project | Name of generating facility (with executed interconnection agreement) that is currently in development.
2 | In-Queue Number (CAISO or WDAT) | Text string. | 0002CONV | CAISO queue or WDAT (Wholesale Distribution Access Tariff) queue number of the generating facility. Types of queue position labels include: - ##, or, if two queues have combined then the queue number will reflect ##,##. - ####CONV is a two-to-three party contract conversion or is a conversion project repowering with new generation. - ####PREC, that is an existing two-party generating facility that has yet to complete a contract conversion. - #### for generation resources that are dynamic or pseudo-ties (projects in a balancing authority area other than the CAISO but are treated as Participating Generators under the CAISO Tariff). If the generation resource is connecting to a Participating TO's distribution system then Queue numbers can include "W", "WDT", "WD", "GFID", "RD" or "Rule 21".
3 | Generator Resource ID | TEXT STRING IN CAPS, underscore(_), #(s), underscore (_), TEXT STRING IN CAPS, #(s). | HENRUA_6_ACDSR3 | The resource ID for this generating facility. Resource ID is assigned during "model build" stage of the New Resource Implementation (NRI) Process.
4 | Primary Developer | Text string. | SuperSun Renewables, LCC | Developer with the highest percentage interest in the project.
5 | Developer Parent Company Name | Text string. | Orion Energy Corp. | Parent company name of primary developer. For wholesale aggregated contracts, use name of aggregator (e.g., Shell, Barclays etc.).
6 | Nameplate Capacity | Number (decimal). | 100.5 | Total nameplate capacity of the whole project in MW. This should be the maximum MW it can deliver under the interconnection agreement.
7 | Expected Annual RPS Eligible Generation (MWh) | Number (decimal). | 29396.8 | The anticipated total energy generated by this RPS eligible resource each year in MWh.
8 | Planned Construction Start Date | Date, formatted YYYY-MM-DD. | 2024-06-17 | Identify planned construction start dates for in-queue resource or generation project.
9 | Planned In-service Date | Date, formatted YYYY-MM-DD. | 2025-09-01 | Identify planned in-service date for in-queue resource and generation project.
10 | Interconnection Request Type | Drop-down menu selection. | Fully deliverable | See drop-down menu. Select deliverability status sought in interconnection agreement.
11 | Technology Type | Drop-down menu selection. | Biogas | See drop-down menu. Select resource technology type.
12 | RPS Eligible | Drop-down menu selection. | Yes | Is this resource RPS-eligible? (Yes or No)
Section 2: GENERATION RESOURCES NOTES
Field # | Project Data Field | Input Format | Input Example | Input Description
13 | Notes | Text strings, inclusive of field identifiers in brackets, separated by line break. | [11. Technology Type] Mixed technology, solar and battery storage. | For all fields in which an option including "[See Notes]" was selected, please enter a description or explanation here.
Section 3: CONNECTING TRANSMISSION PROJECTS
Field # | Project Data Field | Input Format | Input Example | Input Description
14+ | Transmission Project Unique ID | Text string. | 78493 | Corresponding "Transmission Project Unique ID" from transmission projects in "1. Transmission Delay Reporting" tab, field 2, that this generating facility is dependent on. Submitter may add additional columns for additional transmission projects as necessary.

## 1. Transmission Delay Reporting
Transmission Delay Reporting
*IMPORTANT* All fields, except "Notes", are mandatory. Returned data with blank fields will be considered incomplete. The Input Format described on the instructions tab must be followed for each field, i.e. date fields must have dates entered. Tab sections in black text refer to transmission projects, tab sections in red text refer to generation projects.
Electrical corporations shall list each of their transmission facility and system network upgrades that are currently in development, in the “Transmission Project Name” column/field on the “1. Transmission Delay Reporting” tab. For each project listed in the “Transmission Project Name” column/field on the “1. Transmission Delay Reporting” tab, fill in the corresponding data fields for the project. Fill in all construction and inservice dates for all projects regardless of if the project has been delayed or not. For each transmission facility and system network upgrade project, list every renewable energy and energy storage resource that depends on the project's completion in section 4: "GENERATION RESOURCE DEPENDENCIES".
Section 1: TRANSMISSION PROJECT DETAILS | [6 empty] | Section 2: TRANSMISSION PROJECT VARIANCES | [7 empty] | Section 3: TRANSMISSION PROJECT NOTES | Section 4: GENERATION RESOURCE DEPENDENCIES
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Transmission Project Name | Transmission Project Unique ID | Description | Status | Action Taken | Purpose | Purpose Details | Original Construction Start Date | Current or Actual Planned Construction Start Date | Construction Start Date Change Initiator | Construction Start Date Change Reason | Original In-service Date | Current Planned or Actual In-service Date | In-service Date Change Initiator | In-service Date Change Reason | Notes | Dependent In-Queue Generation Resource (CAISO and WDAT) | Dependent In-Queue Generation Resource (CAISO and WDAT)2 | Dependent In-Queue Generation Resource (CAISO and WDAT)3 | Dependent In-Queue Generation Resource (CAISO and WDAT)4 | Dependent In-Queue Generation Resource (CAISO and WDAT)5 | Dependent In-Queue Generation Resource (CAISO and WDAT)6 | Dependent In-Queue Generation Resource (CAISO and WDAT)7 | Dependent In-Queue Generation Resource (CAISO and WDAT)8 | Dependent In-Queue Generation Resource (CAISO and WDAT)9 | Dependent In-Queue Generation Resource (CAISO and WDAT)10 | Dependent In-Queue Generation Resource (CAISO and WDAT)11 | Dependent In-Queue Generation Resource (CAISO and WDAT)12 | Dependent In-Queue Generation Resource (CAISO and WDAT)13 | Dependent In-Queue Generation Resource (CAISO and WDAT)14 | Dependent In-Queue Generation Resource (CAISO and WDAT)15 | Dependent In-Queue Generation Resource (CAISO and WDAT)16 | Dependent In-Queue Generation Resource (CAISO and WDAT)17 | Dependent In-Queue Generation Resource (CAISO and WDAT)18 | Dependent In-Queue Generation Resource (CAISO and WDAT)19 | Dependent In-Queue Generation Resource (CAISO and WDAT)20

## 2. Generation Reporting
Generation Reporting
*IMPORTANT* All fields, except "Notes", are mandatory. Returned data with blank fields will be considered incomplete. The Input Format described on the instructions tab must be followed for each field, i.e. date fields must have dates entered. Tab sections in black text refer to transmission projects, tab sections in red text refer to generation resources.
Electrical corporations are to fill in the "2. Generation Reporting" tab and list every renewable energy and energy storage resource (with executed interconnection agreements) currently in the CAISO, WDAT, or other interconnection queues. For each resource make sure to list every transmission facility and system network upgrade project that it depends on in section 3: "CONNECTING TRANSMISSION PROJECTS".
Section 1: GENERATION RESOURCES DETAILS | [11 empty] | Section 2: GENERATION PROJECT NOTES | Section 3: CONNECTING TRANSMISSION PROJECTS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
Generation Facility Name | In-Queue Number (CAISO or WDAT) | Generator Resource ID | Primary Developer | Developer Parent Company Name | Nameplate Capacity | Expected Annual RPS Eligible Generation | Planned Construction Start Date | Planned In-service Date | Interconnection Request Type | Technology Type | RPS Eligible | Notes | Transmission Project Unique ID | Transmission Project Unique ID2 | Transmission Project Unique ID3 | Transmission Project Unique ID4 | Transmission Project Unique ID5 | Transmission Project Unique ID6 | Transmission Project Unique ID7 | Transmission Project Unique ID8 | Transmission Project Unique ID9 | Transmission Project Unique ID10 | Transmission Project Unique ID11 | Transmission Project Unique ID12 | Transmission Project Unique ID13 | Transmission Project Unique ID14 | Transmission Project Unique ID15 | Transmission Project Unique ID16 | Transmission Project Unique ID17 | Transmission Project Unique ID18 | Transmission Project Unique ID19 | Transmission Project Unique ID20 | Transmission Project Unique ID21 | Transmission Project Unique ID22 | Transmission Project Unique ID23 | Transmission Project Unique ID24

## Definitions
Acronym List |  |  | Date Change Reasons Defined
| Acronym | Definition | Reason | Definition
| AFUDC | Allowance for Funds Used During Construction | Bundling Dependencies | Have other projects or work (outside of this project) been delayed that were necessary to complete before this project could move forward. This can be in any phase of the project (i.e. planning, engineering, construction, etc.)
| CAISO | California Independent System Operator | Clearances | Non-permit related clearance delays from any governmental entity with authority or jurisdiction over any phase of this project.
| CPUC | California Public Utilities Commission | Completed Early | Project completed before originally scheduled in-service date.
| FERC | Federal Energy Regulatory Commission | Customer Action | For this context: generators' (in most circumstances, interconnecting generators) actions that specifically impacted the timeline of this project.
| GO | General Order | Financing | Project delayed due to capital and financial availability constraints.
| ID | Identification | ISO Action | The CAISO de-prioritized or re-prioritized the project. De-prioritization would typically manifest with an on-hold project status.
| ISD | In-service Date | Land Rights | The project required easements, exercise of eminent domain, etc. that the utility has not been able to effect.
| IT | Information Technology | Material | Issues with equipment or components themselves but are not related to vendor error (see "Vendor Quality/Delays")
| IX | Interconnection | Outage | Outages (planned or unplanned) that impacted the in-service date.
| KV | Kilovolt | Permitting (Customer) | Impacts on the permitting process (or an existing permit) that affects the in-service date. Instances where the customer is waiting for permitting.
| MPAC | Modular Protection Automation & Control | Permitting (Utility) | Impacts on the permitting process (or an existing permit) that affects the in-service date. Instances where the utility is responsible for permitting.
| MVA | Megavolt-ampere | Project Design | Any redesigns or additional design work needed outside of the initially approved first project design but not related "Workforce", "Bundling Dependencies" or "Clearances".
| MW | Megawatt | Supply Chain Delays | Requested project resources have not been delivered as scheduled.
| MWh | Megawatt-hour | Vendor Quality/Delays | Issues with vendor/suppliers that are not related to the failure of equipment, material, or components (see "Material").
| N/A | Not applicable | Weather | An unforeseen weather event that causes a delay or set-back in construction work. Example: mudslides resulting from El Nino.
| NERC | North American Electric Reliability Corporation | Workforce Availability | Staffing impacts at any phase of the project (i.e. planning, engineering, construction, etc.).
| NRI | New Resource Implementation | Other [See Notes] | A date change reason or reason for delay that is not listed. Please describe the other delay reason in the "Notes" field.
| OAI | Operative as Installed
| PG&E | Pacific Gas and Electric
| PTO | Participating Transmission Owner
| RPS | Renewables Portfolio Standard
| RTU | Remote Terminal Unit
| SB | Senate Bill
| SCADA | Supervisory Control and Data Acquisition
| SCE | Southern California Edison
| SDG&E | San Diego Gas & Electric
| TDF | Transmission Development Form
| TPP | Transmission Planning Process
| TX | Transmission
| WDAT | Wholesale Distribution Access Tariff
| WECC | Western Electricity Coordinating Council

## Dropdown Lists
1. TRANSMISSION DELAY REPORTING | [7 empty] | 2. GENERATION REPORTING
4. STATUS | 5. ACTION TAKEN | 6. PURPOSE | 7. PURPOSE DETAILS | 10. CONSTRUCTION START DATE CHANGE INITIATOR | 11. CONSTRUCTION START DATE CHANGE REASON | 14. IN-SERVICE DATE CHANGE INITIATOR | 15. IN-SERVICE DATE CHANGE REASON | 10. INTERCONNECTION REQUEST TYPE | 11. TECHNOLOGY TYPE | 12. RPS ELIGIBLE
Abandoned | New | Address Results of Power Flow Analysis | 3rd Party Damage | Customer | Bundling Dependencies | Customer | Bundling Dependencies | Energy Only | Battery Storage | Yes
Canceled | Relocate | Address Results of Protection Studies | Age/Condition | Utility | Clearances | Utility | Clearances | Fully Deliverable | Biodiesel | No
Construction (10%-25%) | Removal | Age/End of Life | Age/Condition - 230/115/70/60 kV Relay Replacement | N/A | Completed Early | N/A | Completed Early | Partially Deliverable | Biogas
Construction (25%-50%) | Replace | Asset Condition | Age/Condition - 500 kV Relay Replacement |  | Customer Action |  | Customer Action | Other [See Notes] | Biomass
Construction (50%-75%) | Upgrade/Retrofit | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | Age/Condition - Anti Climb Guards |  | Financing |  | Financing |  | Conduit Hydro
Construction (over 75%) | N/A | Economic | Age/Condition - Insulator Replacement - Steel |  | ISO Action |  | ISO Action |  | Digester Gas
Construction (under 10%) | Multiple Options [See Notes] | Emergency Event | Age/Condition - Insulator Replacement - Wood |  | Land Rights |  | Land Rights |  | Geothermal
Engineering less than 50% complete |  | Field Test Results | Age/Condition - Raptor Protection - Steel |  | Material |  | Material |  | Hybrid
Engineering more than 50% complete |  | Generator Interconnection | Age/Condition - Replace 230/115/70/60 kV Breakers |  | Outage |  | Outage |  | Hybrid/Paired Solar and Battery
On Hold |  | Load Growth | Age/Condition - Replace 230/115/70/60 kV Transformers |  | Permitting (Customer) |  | Permitting (Customer) |  | Landfill Gas
Operational |  | Local Capacity Requirement | Age/Condition - Replace 500 kV Breakers |  | Permitting (Utility) |  | Permitting (Utility) |  | Muni Solid Waste
Permitting |  | Location, Environmental Conditions | Age/Condition - Replace 500 kV Transformers |  | Project Design |  | Project Design |  | Ocean/Tidal
Planning |  | Physical Security | Age/Condition - Replace Boardwalks |  | Supply Chain Delays |  | Supply Chain Delays |  | Pumped Storage
Other [See Notes] |  | Policy | Age/Condition - Replace Breakers |  | Vendor Quality/Delays |  | Vendor Quality/Delays |  | Solar
|  | Reliability | Age/Condition - Replace Civil Structures |  | Weather |  | Weather |  | Various
|  | Safety | Age/Condition - Replace Conductor |  | Workforce Availability |  | Workforce Availability |  | Wind
|  | Wildfire Mitigation | Age/Condition - Replace Insulators |  | Other [See Notes] |  | Other [See Notes] |  | Other [See Notes]
|  | Work Requested by Others | Age/Condition - Replace Other Substation Equipment |  | N/A |  | N/A
|  | Another Project Or Resource [See Notes] | Age/Condition - Replace Other T-Line Equipment
|  | Other [See Notes] | Age/Condition - Replace Reactors, Age/Condition - Replace Relays
Age/Condition - Replace Relays
Age/Condition - Replace SCADA/RTU
Age/Condition - Replace Steel Poles
Age/Condition - Replace Switches, Age/Condition - Replace Transformers
Age/Condition - Replace Underground System
Age/Condition - Replace Wood Poles
Age/Condition - Switch Replacement - Steel
Age/Condition - Switch Replacement - Wood
Age/Condition - Targeted Relay Replacement
Age/Condition - Wood Pole Reframe
Animal Abatement
Automation
Bus Upgrade
Compliance - Remove Idle Facilities
Construct Roads/Gates/Culverts
Emergency Response - Fire Related
Emergency Response - Storm Related
Environmental
Facility Relocation
Fire Protection
Generation Interconnection
GO95 Mitigation - Steel
Install SCADA/RTU
Line Reconductoring
Line Termination
Load Interconnection
Modular Protection and Automation Control
NERC CIP Compliance
NERC Compliance - GO 95
New Substation
New T-Line
Priority 1 Steel Structure Replacement
Priority 1 Wood Structure Replacement
Protection NERC Compliance
Relay Upgrades
Replace Breakers
Replace Other Substation Equipment
Replace Transformer
Safety - Line Right of Way Access
SCADA Emergency Replacement
SCADA Switch Installation
Security Upgrades
Seismic Upgrade - Replace Conductor
Special Protection Scheme
Substation Capacity
Substation Reliability
System Design Upgrade
System Operations
Targeted Line Reliability
T-Line Capacity
T-Line Emergency
T-Line Reliability
Tools, Transformer Addition/Replacement
Underground Emergency
Voltage Conversion
Voltage Support
Other [See Notes]